{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["765송부","345송부","154송부","한수원"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":10,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":7,"n_cols":16,"rows_kept":7,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2015년도 11월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기","성남","신안성신가평 T/L","765kV 신안성신가평T/L 항공장애표지구 정비(No.48~50)","765kV 신안성신가평T/L 항공장애표지구 정비(No.48~50,66~67) 대한불교 조계종 등 민원개소 항공장애표지구 풍소음 정비","2015-11-07 08:00","2015-11-07 18:00","2015-11-07 08:00","2015-11-07 18:00","당일",null,null,null,201509090194]
[2,"경기","성남","신안성S/S #5 M.Tr A-1","신안성S/S 765kV #5M.Tr GIB","신안성S/S 765kV #5M.Tr GIB 구조개선","2015-11-03 09:00","2015-11-27 18:00","2015-11-03 09:00","2015-11-27 18:00","연속",null,null,null,201509100567]
[3,"강원","태백","신태백S/S 765kV #1 BUS","765kV 신태백S/S 800kV GIS 증설공사","800kV GIS(8000A,50kA) 3CB 설치 기타 부대설비 1식","2015-11-15 10:00","2015-11-28 18:00","2015-11-15 10:00","2015-11-28 18:00","연속",null,null,null,201509070110]

{"sheet":"345송부","index":1,"n_rows":143,"n_cols":16,"rows_kept":143,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2015년도 11월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S 미금성동#1T/L CB (7171)","2015 성동PO 변전협력총액공사(성동SS 7171CB)","성동S/S 345kV GIS 보통점검(성동SS 7171CB)","2015-11-10 09:00","2015-11-10 18:00","2015-11-10 09:00","2015-11-10 18:00","당일",null,null,null,201509100516,"-"]
[2,"서울","성동","성동S/S #4 M.Tr A","성동S/S 345kV #4M.Tr 1, 2차 부싱 교체 및 정밀점검공사","성동S/S 345kV #4M.Tr 1,2차 부싱 교체 및 정밀점검공사","2015-11-16 09:00","2015-11-27 18:00","2015-11-16 09:00","2015-11-27 18:00","연속",null,null,null,201509100300,"-"]
[3,"서울","성동","성동S/S 미금성동#3T/L CB (7571)","2015 성동PO 변전협력총액공사(성동SS 7571CB)","성동S/S 345kV GIS 보통점검(성동SS 7571CB)","2015-11-13 09:00","2015-11-13 18:00","2015-11-13 09:00","2015-11-13 18:00","당일",null,null,null,201509100533,"-"]
[4,"서울","성동","성동S/S 미금성동#4T/L CB (7471)","2015 성동PO 변전협력총액공사(성동SS 7471CB)","성동S/S 345kV GIS 보통점검(성동SS 7471CB)","2015-11-11 09:00","2015-11-11 18:00","2015-11-11 09:00","2015-11-11 18:00","당일",null,null,null,201509100520,"-"]
[5,"서울","성동","성동S/S #1 M.Tr 1차 CB (7172)","2015 성동PO 변전협력총액공사(성동SS 7172CB)","성동S/S 345kV GIS 보통점검(성동SS 7172CB)","2015-11-06 09:00","2015-11-06 18:00","2015-11-06 09:00","2015-11-06 18:00","당일",null,null,null,201509100450,"-"]
[6,"서울","성동","성동S/S 미금성동#1T/L-#1 M.Tr 1차 CB (7100)","2015 성동PO 변전협력총액공사(성동SS 7100CB)","성동S/S 345kV GIS 보통점검(성동SS 7100CB)","2015-11-09 09:00","2015-11-09 18:00","2015-11-09 09:00","2015-11-09 18:00","당일",null,null,null,201509100462,"-"]
[7,"남서울","강남","신양재S/S 345kV #3 Sh.R","신양재S/S 345kV #3Sh.R 보호배전반 정기점검","신양재S/S 345kV #3Sh.R 보호배전반 정기점검","2015-11-03 10:00","2015-11-03 14:00","2015-11-03 10:00","2015-11-03 14:00","당일",null,null,null,201509140187,"-"]
[8,"남서울","강남","신양재S/S 345kV #4 Sh.R","신양재S/S 345kV #4Sh.R 보호배전반 정기점검","신양재S/S 345kV #4Sh.R 보호배전반 정기점검","2015-11-03 14:00","2015-11-03 18:00","2015-11-03 14:00","2015-11-03 18:00","당일",null,null,null,201509140188,"-"]
[9,"남서울","강남","신양재S/S #3 M.Tr A","신양재S/S #3M.Tr 보호배전반 대체","신양재S/S #3M.Tr 보호배전반 대체 - 병행작업 : #3M.TR 보통점검 (변전협력회사)","2015-11-23 09:00","2015-11-27 18:00","2015-11-23 09:00","2015-11-27 18:00","연속",null,null,null,201507140003,"-"]
[10,"남서울","동서울","동서울S/S SVC M.Tr A","동서울S/S SVC 냉각설비 제어PNL 부속품 교체","동서울S/S 냉각설비 제어PNL 부속품 교체","2015-11-03 10:00","2015-11-04 17:00","2015-11-03 10:00","2015-11-04 17:00","연속",null,null,null,201509140338,"-"]
[11,"남서울","영서","영서S/S #3 M.Tr A","345kV 영서S/S #3M.Tr A상 교체공사","- 345kV M.Tr 철거(100/133/167MVA) * 1Tank - 345kV M.Tr 설치(100/133/167MVA) * 1Tank - 기타 부대공사","2015-11-16 10:00","2015-12-08 18:00","2015-11-16 10:00","2015-12-08 18:00","연속",null,null,null,201509100428,"-"]
[12,"남서울","영서","영서S/S #3 M.Tr 1차 CB (7372)","362kV GCB 정밀점검","362kV GCB 정밀점검","2015-11-09 09:00","2015-11-11 14:00","2015-11-09 09:00","2015-11-11 14:00","연속",null,null,null,201509170071,"-"]
[13,"남서울","영서","영서S/S TIE-#3M.Tr 1차 CB (7300)","362kV GCB 정밀점검","362kV GCB 정밀점검","2015-11-11 14:00","2015-11-13 18:00","2015-11-04 10:00","2015-11-06 18:00","연속",null,null,null,201509170072,"-"]
[14,"남서울","직할","영등포S/S 345kV #2 Sh.R CB (7279)","다빈도 차단기 정밀점검","#2Sh.R GIS CB 정밀점검","2015-11-17 09:00","2015-11-20 18:00","2015-11-17 09:00","2015-11-20 18:00","연속",null,null,null,201509160036,"-"]
[15,"남서울","직할","영등포S/S 345kV #1 Sh.R CB (7179)","다빈도 차단기 정밀점검","#1Sh.R GIS CB 정밀점검","2015-11-10 09:00","2015-11-13 18:00","2015-11-10 09:00","2015-11-13 18:00","연속",null,null,null,201509160035,"-"]
[16,"남서울","직할","영등포S/S 345kV #3Sh.R GIS","GIS 초기점검","#3Sh.R GIS 초기점검","2015-11-09 09:00","2015-11-09 18:00","2015-11-09 09:00","2015-11-09 18:00","당일",null,null,null,201509160037,"-"]
[17,"인천","김포","신김포서인천CC T/L","345kV 신김포-서인천CC T/L 전선교체공사","전력선 직선슬리브 구간 해소를 통한 전력선 단선고장 및 안전사고 예방","2015-11-01 08:00","2015-11-02 18:00","2015-11-01 08:00","2015-11-02 18:00","연속",null,null,"신뢰도개선",201509100135,"-"]
[18,"인천","김포","345kV신김포S/S #1 M.Tr A","신김포S/S 154kV M.Tr용 GIS 설치공사","154kV GIS 2CCT 증설","2015-11-10 09:00","2015-11-11 18:00","2015-11-10 09:00","2015-11-11 18:00","연속",null,null,null,201509030006,"-"]
[19,"인천","김포","345kV신김포S/S #1 M.Tr A","신김포S/S 154kV M.Tr용 GIS 설치공사","154kV GIS 2CCT 증설","2015-11-02 09:00","2015-11-03 18:00","2015-11-02 09:00","2015-11-03 18:00","연속",null,null,null,201509030005,"-"]
[20,"인천","시흥","신시흥#1S/S #3 M.Tr A","신시흥#1S/S #3 M.Tr 보호반 대체공사","신시흥#1S/S #3 M.Tr 보호반 대체공사","2015-11-09 09:30","2015-11-13 18:00","2015-11-09 09:30","2015-11-13 18:00","연속",null,null,null,201509140253,"-"]
[21,"인천","시흥","신시흥#2S/S #6M.Tr A","신시흥#2S/S #6M.Tr 3차 GPT 교체","신시흥#2S/S #6M.Tr 3차 GPT 교체","2015-11-19 09:30","2015-11-19 18:00","2015-11-22 09:30","2015-11-22 18:00","당일",null,null,"신뢰도개선",201509150001,"-"]
[22,"인천","인천","신가좌S/S 신가좌신시흥#1T/L GIS","2015년 인천전력지사 362kV GIS 정밀점검 공사","신가좌S/S 신가좌신시흥#1T/L (7272) GIS 정밀점검","2015-11-03 08:00","2015-11-05 18:00","2015-11-03 08:00","2015-11-05 18:00","연속",null,null,null,201508060144,"-"]
[23,"인천","인천","신인천C/C 345kV #71 BUS","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- 345kV #71BUS 개조 - 345kV SEC-CB(70-71-0) 대체 - #71BUS 모선용 DS 대체","2015-11-06 09:00","2015-11-30 18:00","2015-11-06 09:00","2015-11-30 18:00","연속",null,null,null,201509110153,"-"]
[24,"인천","인천","인천CC서인천CC T/L","345kV신경서분기 지중T/L 건설공사","○ 사업규모 : 345kV 가교폴리에틸렌(XLPE) 절연케이블 1회선(복도체)×0.8, 0.4km ○ 소 재 지 : 인천광역시 서구 경서동 일원 ○ 공사기간 : 2015.9 ~ 2016. 2 (착공 후 180일간)","2015-11-03 09:00","2015-12-30 18:00","2015-11-03 09:00","2015-12-30 18:00","연속",null,null,"신뢰도개선",201509090014,"-"]
[25,"인천","인천","인천CC S/Y 345kV #71 BUS","345kV 인천CC S/Y 용량부족GIS 대체","#71 BUS 현장개조 및 70-71-0CB 대체, DS 4조 교체","2015-11-06 10:00","2015-12-05 17:00","2015-11-06 10:00","2015-12-05 17:00","연속",null,null,null,201508280103,"-"]
[26,"인천","직할","신부평S/S #4 M.Tr B","신부평S/S 345kV #4M.Tr B상 OFU 교체공사","신부평S/S 345kV #4M.Tr B상 OFU 교체공사","2015-11-02 09:30","2015-11-02 18:00","2015-11-02 09:30","2015-11-02 18:00","당일",null,null,null,201509150151,"-"]
[27,"인천","직할","신부평S/S 345kV #1 Sh.R","신부평S/S 345kV #1Sh.R 정밀점검","신부평S/S 345kV #1Sh.R 정밀점검","2015-11-09 09:00","2015-11-15 18:00","2015-11-09 09:00","2015-11-15 18:00","연속",null,null,null,201509100501,"-"]
[28,"경기북부","구리","미금S/S #2 M.Tr A","미금#2M.Tr 2차 GIS UHF센서 설치공사","- #2M.Tr 2차(170kV GIS) UHF센서 1대 설치","2015-11-10 09:00","2015-11-11 18:00","2015-11-10 09:00","2015-11-11 18:00","연속",null,null,null,201509090085,"-"]
[29,"경기북부","구리","신가평S/S 345kV #3 Sh.R","신가평S/S 345kV #3Sh.R 하자점검, 냉각용 방열기 청소","345kV #3Sh.R 보통점검, 냉각용 방열기 청소","2015-11-03 10:00","2015-11-04 17:00","2015-11-03 10:00","2015-11-04 17:00","연속",null,null,null,201509010063,"-"]
[30,"경기북부","구리","신가평S/S 345kV #4 Sh.R","신가평S/S 345kV #4Sh.R 하자점검, 냉각용 방열기 청소","345kV #4Sh.R 보통점검, 냉각용 방열기 청소","2015-11-05 10:00","2015-11-06 17:00","2015-11-05 10:00","2015-11-06 17:00","연속",null,null,null,201509010065,"-"]
[31,"경기북부","직할","동두천C/C 345kV #2BUS","동두천CC 345kV #2BUS","345kV #2BUS 휴전 방압변 가스누기 관련 제작사 하자보수 -설비 미생성으로 인한 변경신청","2015-11-03 10:00","2015-11-06 18:00","2015-11-03 10:00","2015-11-06 18:00","연속",null,null,null,201509110181,"-"]
[32,"경기북부","직할","양주S/S #3 M.Tr A","양주S/S #3 M.Tr A","15년 직할 변전협력회사 총액공사 -보호배전반 대체","2015-11-02 09:00","2015-11-05 18:00","2015-11-02 09:00","2015-11-05 18:00","연속",null,null,null,201509110134,"-"]
[33,"경기북부","직할","양주중부#2 T/L","345kV 양주-중부#2T/L 전선교체공사","접속개소 전선교체(No.3-5, 22-26, 37-38)","2015-11-13 07:00","2015-11-16 18:00","2015-11-13 07:00","2015-11-16 18:00","연속",null,null,null,201509110240,"-"]
[34,"경기북부","직할","양주중부#1 T/L","345kV 양주-중부#1T/L 전선교체공사","접속개소 전선교체(No.3-5, 22-26, 35-37, 37-38)","2015-11-07 07:00","2015-11-10 18:00","2015-11-07 07:00","2015-11-10 18:00","연속",null,null,null,201509110238,"-"]
[35,"경기","군포","서서울영서#1 T/L","서서울-영서#1T/L 보호PNL 교체공사","1.서서울S/S 서서울-영서#1T/L 보호PNL 교체 2.서서울S/S 서서울-영서#1T/L PT 교체[변전협력]","2015-11-02 09:00","2015-11-06 18:00","2015-11-02 09:00","2015-11-06 18:00","연속",null,null,"신뢰도개선",201507100103,"-"]
[36,"경기","군포","신온양서서울#1 T/L","신온양서서울외1개T/L 지장철탑이설공사","영인청북간 도로개설관련 지장철탑이설공사 신설 : 10기, 철거 : 18기","2015-11-13 07:00","2015-11-24 18:00","2015-11-13 07:00","2015-11-24 18:00","연속",null,null,null,201509100042,"-"]
[37,"경기","군포","신온양서서울#2 T/L","신온양서서울외1개T/L 지장철탑이설공사","영인청북간 도로개설관련 지장철탑이설공사 신설 : 10기, 철거 : 18기","2015-11-25 07:00","2015-12-06 18:00","2015-11-25 07:00","2015-12-06 18:00","연속",null,null,null,201509100043,"-"]
[38,"경기","군포","서서울영서#2 T/L","서서울-영서#2T/L 보호PNL 교체공사","서서울S/S 서서울-영서#2T/L 보호PNL 교체","2015-11-07 09:00","2015-11-11 18:00","2015-11-07 09:00","2015-11-11 18:00","연속",null,null,"신뢰도개선",201507100105,"-"]
[39,"경기","성남","신성남신양재#2 T/L","신성남S/S 345kV 신성남-신양재#2T/L","신성남S/S 신성남-신양재#2T/L PNL 대체","2015-11-16 09:00","2015-11-20 18:00","2015-11-16 09:00","2015-11-20 18:00","연속",null,null,null,201509100499,"-"]
[40,"경기","성남","신성남신양재#1 T/L","신성남S/S 345kV 신성남-신양재#1T/L","신성남S/S 신성남-신양재#1T/L PNL 대체","2015-11-02 09:00","2015-11-06 18:00","2015-11-02 09:00","2015-11-06 18:00","연속",null,null,null,201509100498,"-"]
[41,"경기","성남","신성남S/S #4M.Tr A","신성남S/S 345kV #4M.Tr PCT,NCT이설","신성남S/S #4M.Tr PCT,NCT이설","2015-11-10 09:00","2015-11-10 18:00","2015-11-10 09:00","2015-11-10 18:00","당일",null,null,null,201509100505,"-"]
[42,"경기","성남","신수원S/S 신수원삼성#2T/L GIS","신수원S/S 신수원-삼성#2T/L GIS","신수원S/S 신수원-삼성#2T/L 7472 GIS 보통점검","2015-11-26 09:00","2015-11-26 18:00","2015-11-26 09:00","2015-11-26 18:00","당일",null,null,null,201509100565,"-"]
[43,"경기","성남","신용인S/S #1 M.Tr B","신용인S/S 345kV #1M.Tr","345kV #1M.Tr TCC PNL 대체 345kV #1M.Tr B상 초기점검, 3차 PT 보통점검 #1S.Tr VCB 보통점검","2015-11-02 09:00","2015-11-04 18:00","2015-11-02 09:00","2015-11-04 18:00","연속",null,null,null,201509100427,"-"]
[44,"경기","성남","신용인신수원 T/L","신용인S/S 345kV 신용인-신수원T/L 집감반 감시 및 제어 수용","신용인S/S 345kV 신용인-신수원T/L 집감반 감시 및 제어 수용 78Bay BF PNL 대체","2015-11-09 09:00","2015-11-11 18:00","2015-11-09 09:00","2015-11-11 18:00","연속",null,null,null,201509100456,"-"]
[45,"경기","직할","화성S/S #1 M.Tr A","345kV 화성S/S #1M.Tr","화성S/S #1M.Tr 2차CB 조작시험","2015-11-14 10:00","2015-11-14 12:00","2015-11-14 10:00","2015-11-14 12:00","당일",null,null,null,201509090128,"-"]
[46,"경기","직할","아산화성#2 T/L","신온양서서울 외 1개T/L 지장철탑이설공사","영인청북간도로개설에따른 지장철탑이설공사 신설 : 10기, 철거 18기","2015-11-06 07:00","2015-11-11 18:00","2015-11-06 07:00","2015-11-11 18:00","연속",null,null,null,201509100041,"-"]
[47,"강원","동해","신제천동해#2 T/L","345kV 신제천-동해 T/L 전선마손 확인점검공사","345kV 신제천-동해#2T/L 전선마손 확인점검공사 (공사구간 : No.9 ~ No.70)","2015-11-30 09:00","2015-12-04 18:00","2015-11-30 09:00","2015-12-04 18:00","매일",null,null,null,201509230029,"-"]
[48,"강원","동해","신제천동해#1 T/L","345kV 신제천-동해 T/L 전선마손 확인점검공사","345kV 신제천-동해#1T/L 전선마손 확인점검공사 (공사구간 : No.9 ~ No.70)","2015-11-23 09:00","2015-11-27 18:00","2015-11-23 09:00","2015-11-27 18:00","매일",null,null,null,201509230028,"-"]
[49,"충북","직할","신제천S/S 345kV #1 BUS","345kV 신제천S/S GIS화 공사","345kV GIS 15CB, 154kV GIS 28CCT - 345kV GIS 설치공간 확보를 위한 #2M.Tr 1차 DS 철거 (작업안전확보)","2015-11-05 09:00","2015-11-05 18:00","2015-11-11 09:00","2015-11-11 18:00","당일",null,null,null,201509080193,"-"]
[50,"충북","직할","신제천신영주#2 T/L","2015년 가공송전선로 순시점검 위탁공사","지장수목벌채 (77~79호간)","2015-11-09 08:00","2015-11-10 18:00","2015-11-09 08:00","2015-11-10 18:00","매일",null,null,null,201509170075,"-"]
[51,"충북","청주","청원S/S #3 M.Tr A","15년 하반기 청주전력지사 170kV GIS 정밀점검","345kV #3M.Tr 2차 GIS 정밀점검","2015-11-18 09:00","2015-11-20 18:00","2015-11-18 09:00","2015-11-20 18:00","연속",null,null,null,201509150030,"-"]
[52,"충북","청주","신옥천청원#2 T/L","345kV 세종분기T/L 건설공사","기설 No.49 철거, 신설 No.1 설치 신설선로 연결","2015-11-04 09:00","2015-11-05 18:00","2015-11-04 09:00","2015-11-05 18:00","연속",null,null,null,201508180052,"-"]
[53,"충북","청주","청원S/S #4 M.Tr A","15년 청주전력지사 변전협력회사 총액공사","청원S/S #4 M.Tr 3차측 PT 대체","2015-11-16 09:00","2015-11-16 18:00","2015-11-16 09:00","2015-11-16 18:00","당일",null,null,null,201509060043,"-"]
[54,"충북","청주","청원신진천#1 T/L","15년 청주전력지사 변전협력회사 총액공사","청원,신진천S/S 청원,신진천#1T/L 보호배전반 및 청원S/S 71bay B/F반 대체","2015-11-09 09:00","2015-11-18 18:00","2015-11-09 09:00","2015-11-18 18:00","연속",null,null,null,201509060017,"-"]
[55,"충북","청주","신옥천청원#1 T/L","345kV 세종분기T/L 건설공사","가선로 구성","2015-11-02 09:00","2015-11-03 18:00","2015-11-02 09:00","2015-11-03 18:00","연속",null,null,null,201508180048,"-"]
[56,"충북","청주","청원신진천#2 T/L","15년 청주전력지사 변전협력회사 총액공사","1. 청원,신진천S/S 청원,신진천#2T/L 보호배전반 2. 청원S/S 72bay B/F반 대체 3. 청원S/S 청원-신진천#2T/L GIS (7271)보통점검 4. 청원S/S 청원-신진천#2T/L PT, LA 점검","2015-11-23 09:00","2015-12-02 18:00","2015-11-23 09:00","2015-12-02 18:00","연속",null,null,null,201509060018,"-"]
[57,"충북","청주","청원S/S #1 M.Tr A","15년 청주전력지사 변전협력회사 총액공사","1.청원S/S 72bay B/F반 대체 2.청원S/S #1M.Tr 1차 LA 점검","2015-11-23 09:00","2015-12-02 18:00","2015-11-23 09:00","2015-12-02 18:00","연속",null,null,null,201509060019,"-"]
[58,"충북","직할","신제천S/S #3 M.Tr A","345kV 신제천S/S GIS화 공사","154kV T-BUS 철거 (GIS 설치공간확보)","2015-11-02 08:00","2015-11-02 18:00","2015-11-02 08:00","2015-11-02 18:00","연속",null,null,null,201509250017,"-"]
[59,"충북","직할","신제천S/S 345kV #2 BUS","345kV 신제천S/S GIS화 공사","154kV T-BUS 철거 (GIS 설치공간확보)","2015-11-06 08:00","2015-11-06 18:00","2015-11-06 08:00","2015-11-06 18:00","연속",null,null,null,201509250018,"-"]
[60,"충북","직할","신제천S/S #2 M.Tr A","345kV 신제천S/S GIS화 공사","154kV T-BUS 철거 (GIS 설치공간확보)","2015-11-05 08:00","2016-06-20 18:00","2015-11-05 08:00","2015-11-14 18:00","연속",null,null,null,201509250019,"-"]
[61,"대전충남","대전","신계룡S/S #1 M.Tr A","○ 신계룡S/S 345kV #1M.Tr 정밀점검","○ 신계룡S/S 345kV #1M.Tr 정밀점검 - 345kV 7272 GIS 정밀점검 - 154kV 6144 GIS 보통점검","2015-11-02 09:00","2015-11-08 18:00","2015-11-02 09:00","2015-11-08 18:00","연속",null,null,null,201509110239,"-"]
[62,"대전충남","대전","신옥천신남원#2 T/L","○ 345kV 신옥천-신남원#2T/L 보호반 교체","○ 345kV 신옥천-신남원#2T/L 보호반 교체","2015-11-16 09:00","2015-11-20 18:00","2015-11-28 09:00","2015-12-03 18:00","연속",null,null,null,201505130160,"-"]
[63,"대전충남","대전","신옥천신계룡 T/L","345kV 신옥천-청양T/L 접속개소전선교체공사","[송전]신옥천-청양T/L 접속개소전선교체공사 - No.56~65","2015-11-06 07:00","2015-11-13 19:00","2015-11-06 07:00","2015-11-13 19:00","연속",null,null,null,201508180074,"-"]
[64,"대전충남","대전","신옥천S/S #3 M.Tr A","○ 345kV 신옥천S/S #3M.Tr(A,C상) 정밀 및 B상 초기점검","○ 345kV 신옥천S/S #3M.Tr(A,C상) 정밀점검 및 B상 초기점검 - 345kV #3M.Tr 도장공사 - 154kV 6344 GIS 보통점검","2015-11-23 09:00","2015-11-29 18:00","2015-11-23 09:00","2015-11-29 18:00","연속",null,null,null,201509110244,"-"]
[65,"대전충남","대전","신옥천S/S #1 M.Tr A","신옥천S/S 345kV 차단기 용량대체 공사","신옥천S/S 345kV 차단기 용량대체","2015-11-30 09:00","2015-12-02 18:00","2015-11-30 09:00","2015-12-02 18:00","당일",null,null,null,201509170070,"-"]
[66,"대전충남","서산","북당진S/S 345kV #2 BUS","당진복합4호기용 345kV SW 증설공사","345kV 63kA 6300A * 4CB 증설 345kV 63kA 8000A Main Bus 증설 * 1식","2015-11-15 09:00","2015-11-19 18:00","2015-11-15 09:00","2015-11-19 18:00","연속",null,null,null,201509090247,"-"]
[67,"대전충남","서산","북당진S/S 345kV #1 BUS","당진복합4호기용 345kV SW 증설공사","345kV 63kA 6300A * 4CB 증설 345kV 63kA 8000A Main Bus 증설 * 1식","2015-11-10 09:00","2015-11-14 18:00","2015-11-10 09:00","2015-11-14 18:00","연속",null,null,null,201509090246,"-"]
[68,"대전충남","서산","신당진태안화력#1 T/L","345kV 신당진-태안화력T/L 선종교체공사","345kV 신당진-태안화력T/L 선종교체공사","2015-11-05 07:00","2015-11-11 19:00","2015-11-05 07:00","2015-11-11 19:00","연속",null,null,"신뢰도개선",201509070152,"-"]
[69,"대전충남","서산","신당진 북당진 T/L T/L","345kV 신당진-북당진 외 1개T/L 용량증대 전력선 교체공사","- 선종교체 : ACSR 480SQ -> HTACSR/AW 480SQ - 공사구간 : 1~35호(잔여구간) 11.239km","2015-11-20 07:00","2015-11-30 18:00","2015-11-20 07:00","2015-11-30 18:00","연속",null,null,null,201509140037,"-"]
[70,"대전충남","서산","신당진태안화력#2 T/L","345kV 신당진-태안화력T/L 선종교체공사","345kV 신당진-태안화력T/L 선종교체공사","2015-11-20 07:00","2015-12-03 19:00","2015-11-20 07:00","2015-12-03 19:00","연속",null,null,"신뢰도개선",201509070153,"-"]
[71,"대전충남","서산","신서산태안화력#2 T/L","345kV 신당진-태안화력T/L 선종교체공사","345kV 신당진-태안화력T/L 선종교체공사","2015-11-16 07:00","2015-11-19 19:00","2015-11-17 07:00","2015-11-19 19:00","연속",null,null,"신뢰도개선",201509070155,"-"]
[72,"대전충남","서산","신서산S/S 345kV #5 Sh.R(신설)","신서산변전소 345kV #5Sh.R 교체공사","○ 345kV #5Sh.R 교체 후 소음측정","2015-11-04 09:00","2015-11-05 18:00","2015-11-04 09:00","2015-11-05 18:00","연속",null,null,null,201509140151,"-"]
[73,"대전충남","서산","신서산태안화력#1 T/L","345kV 신당진-태안화력T/L 선종교체공사","345kV 신당진-태안화력T/L 선종교체공사","2015-11-12 07:00","2015-11-15 19:00","2015-11-13 07:00","2015-11-16 19:00","연속",null,null,"신뢰도개선",201509070154,"-"]
[74,"대전충남","서산","태안T/P 3호기 1차 CB (7372)","태안T/P 345kV 73Bay 차단실패보호반 대체","태안T/P 345kV 73Bay 차단실패보호반 대체","2015-11-02 09:00","2015-11-06 18:00","2015-11-02 09:00","2015-11-06 18:00","연속",null,null,null,201509110329,"-"]
[75,"대전충남","서산","태안T/P TIE-3호기 1차 CB (7300)","태안T/P 345kV 73Bay 차단실패보호반 대체","태안T/P 345kV 73Bay 차단실패보호반 대체","2015-11-02 09:00","2015-11-06 18:00","2015-11-02 09:00","2015-11-06 18:00","연속",null,null,null,201509110330,"-"]
[76,"대전충남","아산","아산S/S 345kV #1 BUS","345kV 아산S/S #4M.Tr 증설공사","○ 362kV GIS 2CB 설치 (7751DS,7709-1ES 설치작업)","2015-11-02 10:00","2015-11-04 17:00","2015-11-02 10:00","2015-11-04 17:00","연속",null,null,null,201507310030,"-"]
[77,"대전충남","아산","아산S/S 345kV #2 BUS","345kV 아산S/S #4M.Tr 증설공사","○ 362kV GIS 2CB 설치 (7752DS,7709-8ES 설치작업)","2015-11-09 10:00","2015-11-11 17:00","2015-11-09 10:00","2015-11-11 17:00","연속",null,null,null,201507310031,"-"]
[78,"대전충남","청양","보령T/P #5,6 SU Tr 1차 CB (7471)","보령화력 362kV GIS 보통점검","○ 보령화력 345kV 7471 GIS 보통점검","2015-11-04 09:00","2015-11-04 18:00","2015-11-04 09:00","2015-11-04 18:00","당일",null,null,null,201509110336,"-"]
[79,"대전충남","청양","보령T/P 청양-보령#1T/L-#6 M.Tr 1차 CB (7600)","보령화력 362kV GIS 보통점검","○ 보령화력 345kV 7600 GIS 보통점검","2015-11-05 09:00","2015-11-06 18:00","2015-11-05 09:00","2015-11-06 18:00","연속",null,null,null,201509110340,"-"]
[80,"대전충남","청양","보령T/P #6 M.Tr 1차 CB (7671)","보령화력 362kV GIS 보통점검","○ 보령화력 345kV 7671 GIS 보통점검","2015-11-05 09:00","2015-11-06 18:00","2015-11-05 09:00","2015-11-06 18:00","연속",null,null,null,201509110337,"-"]
[81,"대전충남","청양","청양S/S #1 M.Tr A","청양S/S 345kV 변압기 보통점검","○ 청양S/S 345kV #1M.Tr 보통점검 ○ 청양S/S 154kV 6144 GIS 보통점검 (차단기 동작시간측정, 주회로 접촉저항 및 기타 부대작업) ○ 청양S/S 23kV PT 절연열화측정 ○ 청양S/S 23kV LA 교체","2015-11-16 09:00","2015-11-16 18:00","2015-11-16 09:00","2015-11-16 18:00","당일",null,null,null,201509110356,"-"]
[82,"전북","군산","군산S/S #4 M.Tr A","345kV 군산S/S #4M.Tr","군산S/S #4M.Tr OLTC 제어회로 점검공사 OLTC 제어회로 점검","2015-11-09 09:00","2015-11-09 18:00","2015-11-09 09:00","2015-11-09 18:00","당일",null,null,null,201509020048,"-"]
[83,"전북","직할","신남원신광주#2 T/L","345kV 신남원-신광주#2T/L","345kV 신남원-신광주#2T/L 송전선로 정밀점검 1.송전선로 정밀점검 : No.1~115호간","2015-11-09 09:00","2015-11-14 18:00","2015-11-09 09:00","2015-11-14 18:00","매일",null,null,null,201508180059,"-"]
[84,"전북","직할","신남원광양#2 T/L","345kV 신남원-광양#2T/L","장기사용 기타설비 대체공사(LA)","2015-11-06 09:00","2015-11-06 18:00","2015-11-05 09:00","2015-11-05 18:00","당일",null,null,"신뢰도개선_과도안정도",201508180314,"-"]
[85,"광주전남","강진","신강진S/S #1 M.Tr A","신강진S/S #1 M.Tr (신강진S/S 노후배전반 정비공사)","345kV 신강진S/S 노후배전반 정비공사 - 신강진S/S #1M.Tr 1,2,3차 관련 제어케이블 결선","2015-11-09 09:00","2015-11-13 18:00","2015-11-09 09:00","2015-11-13 18:00","연속",null,null,null,201508170331,"-"]
[86,"광주전남","광주","신광주S/S #1 M.Tr A","신광주S/S #1 M.Tr(변전협력회사 총액공사)","#1Sh.R PNL 대체","2015-11-02 09:00","2015-11-05 18:00","2015-11-02 09:00","2015-11-05 18:00","연속",null,null,null,201509140064,"-"]
[87,"광주전남","광주","신광주S/S #3 M.Tr A","신광주S/S #3 M.Tr(변전협력회사 총액공사)","#3Sh.R PNL 대체","2015-11-21 09:00","2015-11-24 18:00","2015-11-21 09:00","2015-11-24 18:00","연속",null,null,null,201509140065,"-"]
[88,"광주전남","순천","광양율촌CC T/L","광양-율촌CC T/L(피뢰기 설치공사)","피뢰기 설치 : 69~137호, 38기","2015-11-09 07:00","2015-11-12 18:00","2015-11-09 07:00","2015-11-12 18:00","연속",null,null,null,201509110392,"-"]
[89,"광주전남","순천","신남원광양#1 T/L","신남원-광양#1T/L(순천변전협력회사 총액공사)","15년 순천변전협력회사 총액공사 - LA(A,B,C상), CVT(B상) 교체","2015-11-17 09:00","2015-11-17 18:00","2015-11-30 09:00","2015-11-30 18:00","당일",null,null,null,201509110317,"-"]
[90,"광주전남","순천","광양여수TP T/L","광양-여수TP T/L(전력선 교체공사)","전력선 교체 : 94~98호, 2.249C-km","2015-11-16 07:00","2015-11-18 18:00","2015-11-16 07:00","2015-11-18 18:00","연속",null,null,null,201509110394,"-"]
[91,"광주전남","순천","율촌CC 여수TP T/L","율촌CC-여수TP T/L(피뢰기 설치공사)","피뢰기 설치 : 1~68호, 67기","2015-11-02 07:00","2015-11-08 18:00","2015-11-02 07:00","2015-11-08 18:00","연속",null,null,null,201509110390,"-"]
[92,"광주전남","직할","신광주한빛NP#2 T/L","신광주한빛NP#2 T/L(345kV 피뢰기 설치공사)","발전소 연계설비 피뢰기 설치","2015-11-06 09:00","2015-11-20 18:00","2015-11-06 09:00","2015-11-18 18:00","연속",null,null,"신뢰도개선",201509110383,"-"]
[93,"대구경북","경산","신경산S/S #4 M.Tr A","신경산S/S #4M.Tr 2차측 피뢰기 절연열화측정 및 누유보수","#4M.Tr 2차측 피뢰기 절연열화측정 및 C상 누유보수","2015-11-10 09:00","2015-11-10 12:00","2015-11-30 09:00","2015-11-30 12:00","당일",null,null,null,201509080137,"-"]
[94,"대구경북","경산","신경산S/S #1 M.Tr A","신경산S/S 345kV #1M.Tr 1차측 LA 절연열화측정 및 누유보수","345kV #1M.Tr 1차측 LA 절연열화측정 및 누유보수","2015-11-02 10:00","2015-11-02 15:00","2015-11-02 10:00","2015-11-02 15:00","당일",null,null,null,201509080136,"-"]
[95,"대구경북","구미","선산S/S #2 M.Tr A","선산S/S #2M.Tr 정밀점검","#2M.Tr 정밀점검","2015-11-02 09:00","2015-11-16 18:00","2015-11-02 09:00","2015-11-16 18:00","연속",null,null,null,201508070127,"-"]
[96,"대구경북","달성","고령S/S 345kV #1 BUS","보호반 판넬교체공사","보호반교체작업","2015-11-06 09:00","2015-11-07 18:00","2015-11-20 09:00","2015-11-21 18:00","연속",null,null,"신뢰도개선",201508030072,"-"]
[97,"대구경북","달성","고령S/S 345kV #2 BUS","보호반 판넬교체공사","보호반교체작업","2015-11-08 09:00","2015-11-09 18:00","2015-11-22 09:00","2015-11-23 18:00","연속",null,null,"신뢰도개선",201508030073,"-"]
[98,"대구경북","영주","신영주S/S 345kV #1 BUS","신영주S/S 362kV GIS화 공사","모선보호반 이설","2015-11-04 09:00","2015-11-05 18:00","2015-11-04 09:00","2015-11-05 18:00","연속",null,null,null,201509110186,"○"]
[99,"대구경북","영주","신영주S/S 345kV #2 BUS","신영주S/S 362kV GIS화 공사","모선보호반 이설","2015-11-06 09:00","2015-11-07 18:00","2015-11-06 09:00","2015-11-07 18:00","연속",null,null,null,201509110187,"-"]
[100,"대구경북","영주","신영주S/S #2 M.Tr A","신영주S/S 362kV GIS화 공사","GIS 기초 PHC 시공을 위한 안전이격 확보","2015-11-14 09:00","2015-11-17 18:00","2015-11-14 09:00","2015-11-17 18:00","연속",null,null,null,201509110189,"-"]
[101,"대구경북","영주","한울3N/P 345kV #2 BUS","한울 3발 362kV 용량부족 GIS 대체공사","362kV GIS 용량부족 GIS(40kA-&gt50kA)12CB 대체공사 전담운영체계공사","2015-11-16 09:00","2015-11-19 18:00","2015-11-16 09:00","2015-11-19 18:00","연속",null,null,null,201508030016,"-"]
[102,"대구경북","칠곡","북대구선산 T/L","송전선로 피로기 설치공사","345kV송전선로 피뢰기 설치공사","2015-11-09 08:00","2015-11-13 18:00","2015-11-23 08:00","2015-11-27 18:00","연속",null,null,null,201509080120,"-"]
[103,"대구경북","칠곡","서대구S/S 서대구-고령#2T/L-TIE CB (7200)","7200 GCB 보통점검","7200 GCB 보통점검","2015-11-18 09:30","2015-11-18 18:00","2015-11-18 09:30","2015-11-18 18:00","당일",null,null,null,201509070259,"-"]
[104,"대구경북","칠곡","서대구S/S 북,서대구#1/서-선#2T/L-TIE CB (7800)","7800 GCB 보통점검","7800 GCB 보통점검","2015-11-19 09:30","2015-11-19 18:00","2015-11-19 09:30","2015-11-19 18:00","당일",null,null,null,201509070261,"-"]
[105,"대구경북","포항","신포항S/S 345kV #1 BUS","신포항S/S 345kV #1BUS 휴전작업","CVT 대체","2015-11-25 09:00","2015-11-26 18:00","2015-11-25 09:00","2015-11-26 18:00","연속",null,null,null,201509090184,"○"]
[106,"대구경북","경산","울주신경산#2T/L","송전선로 정밀점검 및 애자 절연저항 측정","- 122기 정밀 점검, 애자 절연저항 측정","2015-11-09 09:00","2015-11-20 18:00","2015-11-09 09:00","2015-11-20 18:00","연속",null,null,null,201508110043,"-"]
[107,"부산울산","동부산","고리N/P S/Y 신고리#1,2 SAT CB (7671)","고리N/P S/Y 362kV GIS 유압설비보수","고리N/P S/Y 362kV 7671 GIS 유압설비보수","2015-11-23 13:00","2015-11-23 17:00","2015-11-23 13:00","2015-11-23 17:00","당일",null,null,null,201509100394,"-"]
[108,"부산울산","동부산","고리N/P S/Y 고리 #4 SUT B CB (7672)","고리N/P S/Y 362kV GIS 유압설비보수","고리N/P S/Y 362kV 7672 GIS 유압설비보수","2015-11-24 09:00","2015-11-24 13:00","2015-11-24 09:00","2015-11-24 13:00","당일",null,null,null,201509100398,"-"]
[109,"부산울산","동부산","고리N/P 신고리#1,2 SAT-고리#4 SUT B CB (7600)","고리N/P S/Y 362kV GIS 유압설비보수","고리N/P S/Y 362kV 7600 GIS 유압설비보수","2015-11-23 09:00","2015-11-23 13:00","2015-11-23 09:00","2015-11-23 13:00","당일",null,null,null,201509100391,"-"]
[110,"부산울산","동부산","신고리고리NP#2 T/L","345kV 신고리-고리NPT/L 송전용피뢰기 설치공사","구간: 신고리-고리#2T/L 1 ~ 8호 피뢰기설치(8기, 24set)","2015-11-10 09:00","2015-11-11 18:00","2015-11-10 09:00","2015-11-11 18:00","연속",null,null,null,201509070019,"-"]
[111,"부산울산","동부산","신양산고리NP#2 T/L","`14-15년 송전협력회사 총액공사","345kV 신양산-고리NP T/L 가공 Arm-Tie 교체공사 -교체 구간 및 수량: 345kV 신양산-고리NP T/L 7기 (No. 28, 29, 33, 34, 35,. 37, 38)","2015-11-05 08:00","2015-11-07 18:00","2015-11-05 08:00","2015-11-07 18:00","연속",null,null,null,201509080063,"-"]
[112,"부산울산","동부산","신양산북부산#2 T/L","345kV 신양산-북부산T/L 송전용피뢰기 설치공사","구간: 신양산-북부산#2T/L 1 ~ 63호 피뢰기설치(62기, 186set)","2015-11-23 09:00","2015-12-02 18:00","2015-11-23 09:00","2015-12-02 18:00","연속",null,null,null,201509070015,"-"]
[113,"부산울산","동부산","신양산고리NP#1 T/L","`14-15년 송전협력회사 총액공사","345kV 신양산-고리NP T/L 가공 Arm-Tie 교체공사 -교체 구간 및 수량: 345kV 신양산-고리NP T/L 7기 (No. 28, 29, 33, 34, 35,. 37, 38)","2015-11-02 08:00","2015-11-04 18:00","2015-11-02 08:00","2015-11-04 18:00","연속",null,null,null,201509080061,"-"]
[114,"부산울산","북부산","북부산신울산#2 T/L","345kV 북부산-신울산T/L 안전이격확보공사","본선로 구성(46호~50호)","2015-11-15 08:00","2015-11-19 18:00","2015-11-25 08:00","2015-11-28 18:00","연속",null,null,null,201509090010,"-"]
[115,"부산울산","서부산","서부산S/S #1 M.Tr A","서부산S/S 345kV #1M.Tr 보호배전반 대체","서부산S/S 345kV #1M.Tr 보호배전반 대체 [병행]#1M.Tr 1차 GIS(7272) 보통점검(곽재훈)","2015-11-16 10:00","2015-11-20 18:00","취소","취소","연속",null,null,null,201509100410,"-"]
[116,"부산울산","서부산","서부산북부산#2 T/L","345kV 서부산-북부산T/L 등 8개T/L 이설공사","345kV OF 2000㎟ 케이블 0.177km 이설","2015-11-06 08:00","2015-12-10 18:00","2015-11-06 08:00","2015-12-10 18:00","연속",null,null,null,201509080006,"-"]
[117,"부산울산","서부산","신녹산S/S #2 M.Tr A","신녹산S/S 345kV #2M.Tr 하자점검","신녹산S/S 345kV #2M.Tr 하자점검 [병행:#1M.Tr 1차 GIS(7272), 2차 GIS(6244), #2S.Tr, #2S.Tr GIS(4289), D/L S.Tr 하자점검_곽재훈]","2015-11-23 10:00","2015-11-26 18:00","2015-11-23 10:00","2015-11-26 18:00","연속",null,null,null,201509100419,"-"]
[118,"부산울산","울산","신온산S/S #3 M.Tr 1차 CB (7572)","2015년 362kV GIS 정밀점검공사","7572 GIS 정밀점검","2015-11-30 08:00","2015-12-02 18:00","2015-11-30 08:00","2015-12-02 18:00","연속",null,null,null,201509100651,"-"]
[119,"부산울산","울산","신온산S/S #2 M.Tr A","345kV M.Tr 보통점검 및 OLTC 정밀점검공사","M.Tr 보통점검 및 OLTC 정밀점검, 7400 GIS 정밀점검","2015-11-07 08:00","2015-11-08 18:00","2015-11-07 08:00","2015-11-08 18:00","연속",null,null,null,201509100647,"-"]
[120,"부산울산","울산","동울산신울산#1 T/L","345kV 동울산-신울산T/L 지장철탑 이설공사","○ 구간 : 345kV 동울산-신울산 T/L 118～122호간(1.834Km) ○ 철탑교체 : 1기(120호 : Ba2-45)&ltbr> ○ 본선로 구성(2회선) : 1기(120호 가철탑 : Ba2-4)","2015-11-25 08:00","2015-11-26 18:00","2015-11-25 08:00","2015-11-26 18:00","연속",null,null,null,201509090084,"○"]
[121,"부산울산","울산","동울산신울산#2 T/L","345kV 동울산-신울산T/L 지장철탑 이설공사","○ 구간 : 345kV 동울산-신울산 T/L 118～122호간(1.834Km) ○ 철탑교체 : 1기(120호 : Ba2-45)&ltbr> ○ 본선로 구성(2회선) : 1기(120호 가철탑 : Ba2-4)","2015-11-23 08:00","2015-11-24 18:00","2015-11-23 08:00","2015-11-24 18:00","연속",null,null,null,201509090083,"-"]
[122,"부산울산","울산","울주S/S 울주-월성NP#1T/L-TIE CB (7900)","2015년 362kV GIS 정밀점검공사","7900 GIS 정밀점검","2015-11-09 08:00","2015-11-11 18:00","2015-11-09 08:00","2015-11-11 18:00","연속",null,null,null,201509100649,"-"]
[123,"부산울산","울산","울주S/S #3 M.Tr A","345kV M.Tr 보통점검 및 OLTC 정밀점검공사","M.Tr 보통점검 및 OLTC 정밀점검, 7672 GIS 정밀점검, 6344,4384 보통점검","2015-11-16 08:00","2015-11-18 18:00","2015-11-16 08:00","2015-11-18 18:00","연속",null,null,null,201509100648,"-"]
[124,"부산울산","울산","울주S/S 울주-월성NP#2T/L CB (7A71)","2015년 362kV GIS 정밀점검공사","7A71 GIS 정밀점검","2015-11-13 08:00","2015-11-15 18:00","2015-11-13 08:00","2015-11-15 18:00","연속",null,null,null,201509100650,"-"]
[125,"경남","진주","의령S/S #1 M.Tr A","345kV #1M.Tr 보통점검","345kV #1M.Tr 보통점검","2015-11-04 09:30","2015-11-05 18:30","취소","취소","연속",null,null,null,201509100096,"-"]
[126,"경남","진주","신남원의령#1 T/L","345kV 고령-의령 #1T/L 정밀점검 공사 관련 안전이격","345kV 고령-의령 #1T/L 정밀점검 공사 관련 안전이격","2015-11-06 08:30","2015-11-07 18:00","2015-11-06 08:30","2015-11-07 18:00","연속",null,null,null,201509070022,"-"]
[127,"경남","진주","고령의령#1 T/L","345kV 고령-의령 #1T/L 정밀점검 공사(가공위탁)","고령-의령 #1T/L 1호~116호 정밀점검","2015-11-02 08:30","2015-11-08 18:00","2015-11-02 08:30","2015-11-08 18:00","연속",null,null,null,201509070018,"-"]
[128,"경남","함안","북경남서대구#2 T/L","북경남-서대구#2T/L 보호계전기 성능 확인 및 개선 작업","송전선로 보호계전기 성능 확인 및 개선 작업","2015-11-05 09:00","2015-11-05 18:00","2015-11-05 09:00","2015-11-05 18:00","당일",null,null,null,201509110126,"-"]
[129,"경남","함안","북경남S/S 북경남-서대구 #1T/L CB (7A72)","북경남S/S 345kV 7A72 GIS 초기점검 공사","북경남S/S 345kV 7A72 GIS 초기점검 공사","2015-11-03 09:30","2015-11-03 17:30","2015-11-03 09:30","2015-11-03 17:30","당일",null,null,null,201509060001,"-"]
[130,"경남","함안","북경남무주양수 T/L","345kV 북경남-무주T/L 정밀점검(칠곡전력지사 구간)","345kV 북경남-무주T/L 정밀점검(칠곡전력지사 구간)","2015-11-02 09:00","2015-11-06 18:00","2015-11-09 09:00","2015-11-13 18:00","연속",null,null,null,201509040083,"-"]
[131,"경남","함안","북경남S/S #6Sh.R - 북경남-서대구#2T/L CB (7900)","북경남S/S 345kV 7900 GIS 초기점검 공사","북경남S/S 345kV 7900 GIS 초기점검 공사","2015-11-13 09:30","2015-11-13 17:30","2015-11-13 09:30","2015-11-13 17:30","당일",null,null,null,201509060006,"-"]
[132,"경남","함안","북경남S/S #6 Sh.R CB (7979) (7979)","북경남S/S 345kV 7979 GIS 초기점검 공사","북경남S/S 345kV 7979 GIS 초기점검 공사","2015-11-18 09:30","2015-11-18 17:30","2015-11-18 09:30","2015-11-18 17:30","당일",null,null,null,201509060005,"-"]
[133,"경남","함안","신옥천북경남 T/L","345kV 신옥천-북경남T/L 정밀점검(칠곡전력지사 구간)","345kV 신옥천-북경남T/L 정밀점검(칠곡전력지사 구간)","2015-11-09 09:00","2015-11-13 18:00","2015-11-16 09:00","2015-11-20 18:00","연속",null,null,null,201509040085,"-"]
[134,"경남","함안","북경남S/S #7 Sh.R CB (7B79) (7B79)","북경남S/S 345kV 7B79 GIS 초기점검 공사","북경남S/S 345kV 7B79 GIS 초기점검 공사","2015-11-17 09:30","2015-11-17 17:30","2015-11-17 09:30","2015-11-17 17:30","당일",null,null,null,201509060007,"-"]
[135,"경남","함안","북경남대구#1 T/L","북경남S/S #5M.Tr 및 S.W증설공사","345KV 7692 ES 조작함내 히터 교체 작업(A, B상)","2015-11-06 14:00","2015-11-06 18:00","2015-11-06 14:00","2015-11-06 18:00","당일",null,null,null,201508210133,"-"]
[136,"경남","함안","북경남S/S #6 Sh.R CB (7971)","북경남S/S 345kV 7971 GIS 초기점검 공사","북경남S/S 345kV 7971 GIS 초기점검 공사","2015-11-05 09:30","2015-11-05 17:30","2015-11-05 09:30","2015-11-05 17:30","당일",null,null,null,201509060004,"-"]
[137,"경남","함안","신마산삼천포화력#1 T/L","신마산S/S 345kV 신마산-삼천포화력#1T/L CPD 교체공사","신마산S/S 345kV 신마산-삼천포화력#1T/L CPD 교체공사","2015-11-05 09:30","2015-11-05 17:30","2015-11-05 09:30","2015-11-05 17:30","당일",null,null,null,201509060014,"-"]
[138,"경남","함안","의령신마산#1 T/L","345kV 의령-신마산T/L 접속개소 전선교체공사","345kV 의령-신마산T/L 19-22, 23-33, 59-70호 전선교체","2015-11-09 07:00","2015-11-18 18:30","2015-11-09 07:00","2015-11-18 18:30","연속",null,null,null,201509090175,"-"]
[139,"경남","함안","의령신마산#2 T/L","345kV 의령-신마산T/L 접속개소 전선교체공사","345kV 의령-신마산T/L 19-22, 23-33, 59-70호 전선교체","2015-11-19 07:00","2015-11-28 18:30","2015-11-19 07:00","2015-11-28 18:30","연속",null,null,null,201509090176,"-"]

{"sheet":"154송부","index":2,"n_rows":302,"n_cols":16,"rows_kept":302,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2015년도 11월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","쌍문미아#1 T/L","미아S/S 170KV 장기사용 GIS 교체공사","170KV 장기사용 GIS 철거 및 신규 설치","2015-11-03 09:30","2015-11-30 15:00","2015-11-16 09:30","2015-12-16 15:00","연속",null,null,null,201508150004,"-"]
[2,"서울","성동","의정부상계#1 T/L","345kV 신의정부S/S 관련T/L 건설공사","○ 철탑기수 : 6기(C/H 1기, 4회선용 4각 철탑 5기) ○ 선로길이 : 4C- 1.896km ○ 선 종 : ACSR410㎟ × 2B","2015-11-21 07:00","2015-12-23 18:00","2015-11-23 07:00","2015-12-23 18:00","연속",null,null,null,201509020080,"-"]
[3,"서울","성동","의정부상계#2 T/L","345kV 신의정부S/S 관련T/L 건설공사","○ 철탑기수 : 6기(C/H 1기, 4회선용 4각 철탑 5기) ○ 선로길이 : 4C- 1.896km ○ 선 종 : ACSR410㎟ × 2B","2015-11-02 07:00","2015-11-20 18:00","2015-11-04 07:00","2015-11-22 18:00","연속",null,null,null,201509020079,"-"]
[4,"서울","성동","상봉휘경#1 T/L","휘경S/S 170kV 장기사용 GIS 대체공사","상봉휘경#1T/L GIS 대체","2015-11-19 09:00","2015-12-10 18:00","2015-11-19 09:00","2015-12-10 18:00","연속",null,null,null,201508030028,"-"]
[5,"서울","성동","성동휘경#2 T/L","휘경S/S 170kV 장기사용 GIS 대체공사","성동휘경#2T/L GIS 대체","2015-11-19 09:00","2015-12-10 18:00","2015-11-19 09:00","2015-12-10 18:00","연속",null,null,"신뢰도개선",201508030027,"-"]
[6,"서울","중부","수색상암#2 T/L","15년 중부전력지사 장기사용 배전반 대체공사","상암(667), 수색(677) 수색상암#2 T/L 배전반 대체공사","2015-11-30 10:00","2015-12-03 18:00","2015-11-30 10:00","2015-12-03 18:00","연속",null,null,null,201508210076,"-"]
[7,"서울","중부","수색상암#1 T/L","15년 중부전력지사 장기사용 배전반 대체공사","상암(657), 수색(667) 수색상암#1 T/L 배전반 대체공사","2015-11-23 10:00","2015-11-26 18:00","2015-11-23 10:00","2015-11-26 18:00","연속",null,null,null,201508100055,"-"]
[8,"서울","중부","중부용산#2 T/L","15년 중부전력지사 장기사용 배전반 대체공사","중부(6G7), 용산(637) 중부용산#2 T/L 배전반 대체공사","2015-11-09 10:00","2015-11-11 18:00","2015-11-09 10:00","2015-11-11 18:00","연속",null,null,null,201509170051,"-"]
[9,"서울","중부","중부용산#1 T/L","15년 중부전력지사 장기사용 배전반 대체공사","중부(647), 용산(627) 중부용산#1 T/L 배전반 대체공사","2015-11-02 10:00","2015-11-05 18:00","2015-11-02 10:00","2015-11-05 18:00","연속",null,null,null,201509170050,"-"]
[10,"서울","직할","중부신촌 T/L","신촌S/S 154kV 장기사용 GIS 대체","중부신촌T/L GIS 대체","2015-11-14 08:00","2015-12-03 18:00","2015-11-14 08:00","2015-12-03 18:00","연속",null,null,null,201509110410,"-"]
[11,"서울","직할","신촌순화 T/L","신촌S/S 154kV 장기사용 GIS 대체","신촌순화T/L GIS 교체","2015-11-14 08:00","2015-12-03 18:00","2015-11-14 08:00","2015-12-03 18:00","연속",null,null,null,201509110404,"-"]
[12,"남서울","강남","신양재역삼#1 T/L","지하(복합)변전소 인출구간 OF케이블 선종교체공사","가. 공사구간 ○ 154㎸ 신양재-역삼T/L : 역삼S/S∼J/B#13-1(3C×0.210㎞, 전력구) ○ 154㎸ 역삼-대치T/L : 역삼S/S∼J/B#14 (2C×0.319㎞, 전력구+관로) ○ 154㎸ 역삼-대치T/L : 대치S/S∼J/B#20 (2C×0.625㎞, 전력구+관로) 나. 케이블 포설 : 154㎸ XLPE 1,200㎟ × 2회","2015-11-02 09:00","2015-11-23 10:00","2015-11-30 10:00","2015-12-21 10:00","연속",null,null,null,201509080105,"-"]
[13,"남서울","강남","신양재역삼#2 T/L","지하(복합)변전소 인출구간 OF케이블 선종교체공사","가. 공사구간 ○ 154㎸ 신양재-역삼T/L : 역삼S/S∼J/B#13-1(3C×0.210㎞, 전력구) ○ 154㎸ 역삼-대치T/L : 역삼S/S∼J/B#14 (2C×0.319㎞, 전력구+관로) ○ 154㎸ 역삼-대치T/L : 대치S/S∼J/B#20 (2C×0.625㎞, 전력구+관로) 나. 케이블 포설 : 154㎸ XLPE 1,200㎟ × 2회","2015-11-23 10:00","2015-12-14 10:00","2015-11-09 09:00","2015-11-30 10:00","연속",null,null,null,201509080123,"-"]
[14,"남서울","동서울","동서울신장#2 T/L","동서울-신장#2T/L 6A6DS 완전개방 불량 보수 공사","동서울-신장#2T/L 6A6DS 완전개방 불량 보수 공사","2015-11-06 09:00","2015-11-06 17:00","2015-11-06 09:00","2015-11-06 17:00","당일",null,null,null,201509150110,"-"]
[15,"남서울","동서울","강동천호#1 T/L","154kV 강동-천호#1T/L 천호S/S측 인출구간 선종교체공사","천호S/S 강동-천호#1T/L EBG ~ 신설T/J 구간 OF케이블 -> XLPE케이블 교체","2015-11-02 09:00","2015-11-30 18:00","취소","취소","연속",null,null,"신뢰도개선",201509140254,"-"]
[16,"남서울","영서","가양S/S 154kV #2 BUS","가양S/S 장기사용 170kV GIS 대체","170kV GIS 5CCT 대체","2015-11-02 09:00","2015-11-16 18:00","2015-11-23 09:00","2015-12-07 18:00","연속",null,null,null,201507210039,"-"]
[17,"남서울","영서","사당신림 T/L","인적실수 예방을 위한 170kV GIS LCP반 회로보완","170kV GIS LRS SW교체","2015-11-16 10:00","2015-11-16 11:00","2015-11-02 10:00","2015-11-02 11:00","당일",null,null,null,201509160008,"-"]
[18,"남서울","영서","영서S/S 154kV #65 BUS","#60BUS CVT 교체","- 60BUS CVT 교체 - 60BUS 144kV LA 보통점검","2015-11-08 09:00","2015-11-08 18:00","2015-11-01 09:00","2015-11-01 18:00","당일",null,null,"신뢰도개선",201507100227,"-"]
[19,"남서울","영서","영서소래 T/L","170kV CVT 교체","170kV CVT 교체","2015-11-03 10:00","2015-11-03 18:00","2015-11-03 10:00","2015-11-03 18:00","당일",null,null,null,201507100202,"-"]
[20,"남서울","영서","영서S/S 154kV #60 BUS","#60BUS CVT 교체","- 60BUS CVT 교체 - 60BUS 144kV LA 보통점검 - 과열개소 보수","2015-11-07 09:00","2015-11-07 18:00","2015-10-31 09:00","2015-10-31 18:00","당일",null,null,"신뢰도개선",201507100225,"-"]
[21,"남서울","영서","중동화곡#1 T/L","인적실수 예방을 위한 170kV GIS LCP반 회로보완","170kV GIS LRS SW교체","2015-11-17 10:00","2015-11-17 11:00","2015-11-17 10:00","2015-11-17 11:00","당일",null,null,null,201509160020,"-"]
[22,"남서울","영서","중동화곡#2 T/L","인적실수 예방을 위한 170kV GIS LCP반 회로보완","170kV GIS LRS SW교체","2015-11-17 11:00","2015-11-17 12:00","2015-11-17 11:00","2015-11-17 12:00","당일",null,null,null,201509160021,"-"]
[23,"남서울","영서","고강화곡#2 T/L","인적실수 예방을 위한 170kV GIS LCP반 회로보완","170kV GIS LRS SW교체","2015-11-17 14:00","2015-11-17 15:00","2015-11-17 14:00","2015-11-17 15:00","당일",null,null,null,201509160023,"-"]
[24,"남서울","영서","고강화곡#1 T/L","인적실수 예방을 위한 170kV GIS LCP반 회로보완","170kV GIS LRS SW교체","2015-11-17 13:00","2015-11-17 14:00","2015-11-17 13:00","2015-11-17 14:00","당일",null,null,null,201509160022,"-"]
[25,"남서울","직할","신길S/S 154kV #2 BUS","신길S/S 170kV 장기사용 GIS 대체공사","신길S/S 170kV 장기사용 GIS 대체공사","2015-11-13 15:00","2015-11-21 18:00","2015-11-18 15:00","2015-11-29 18:00","연속",null,null,null,201508110046,"-"]
[26,"남서울","직할","대방신길#1 T/L","신길S/S 170kV 장기사용 GIS 대체공사","신길S/S 170kV 장기사용 GIS 대체공사","2015-11-22 09:00","2015-12-19 18:00","2015-11-02 11:00","2015-11-29 18:00","연속",null,null,null,201509070207,"-"]
[27,"남서울","직할","신길S/S 154kV #2 BUS","신길S/S 170kV 장기사용 GIS 대체공사","신길S/S 170kV 장기사용 GIS 대체공사","2015-11-22 09:00","2015-11-26 18:00","취소","취소","연속",null,null,null,201509070205,"-"]
[28,"남서울","직할","신길S/S 154kV #1 BUS","신길S/S 170kV 장기사용 GIS 대체공사","신길S/S 170kV 장기사용 GIS 대체공사","2015-11-26 09:00","2015-12-07 18:00","취소","취소","연속",null,null,null,201509070208,"-"]
[29,"남서울","직할","신길S/S 154kV #1 BUS","신길S/S 170kV 장기사용 GIS 대체공사","신길S/S 170kV 장기사용 GIS 대체공사","2015-11-02 15:00","2015-11-13 15:00","2015-11-05 15:00","2015-11-18 15:00","연속",null,null,null,201508110047,"-"]
[30,"남서울","직할","교대이수#1 T/L","154KV 교대-이수T/L 지장선로 이설공사 (방배로 1구간)","서초구청 하수암거 건설에 따른 지장선로 이설","2015-11-16 09:00","2015-12-04 18:00","2015-11-16 09:00","2015-12-04 18:00","연속",null,null,null,201509210117,"-"]
[31,"인천","김포","경서양촌#2 T/L","345kV 경서-양촌#2 T/L 정밀점검","철탑, 애자금구류 등 정밀점검(경서C/H~No.37)","2015-11-25 09:00","2015-11-26 18:00","취소","취소","매일",null,null,"신뢰도개선",201509100158,"-"]
[32,"인천","김포","경서양촌#1 T/L","345kV 경서-양촌#1 T/L 정밀점검","철탑, 애자금구류 등 정밀점검(경서C/H~No.37)","2015-11-23 09:00","2015-11-24 18:00","취소","취소","매일",null,null,"신뢰도개선",201509100157,"-"]
[33,"인천","김포","345kV신김포S/S 154kV #60 BUS","신김포S/S 154kV M.Tr용 GIS 설치공사","154kV GIS 2CCT 증설","2015-11-02 09:00","2015-11-09 18:00","취소","취소","연속",null,null,null,201509030004,"-"]
[34,"인천","김포","345kV신김포S/S 154kV #65 BUS","신김포S/S 154kV M.Tr용 GIS 설치공사","154kV GIS 2CCT 증설","2015-11-10 09:00","2015-11-17 18:00","취소","취소","연속",null,null,null,201509030003,"-"]
[35,"인천","김포","신김포양곡#1 T/L","양곡S/S 170kV 신김포양곡#1T/L GIS 정밀점검차","양곡S/S 170kV 신김포양곡#1T/L GIS 정밀점검","2015-11-07 08:00","2015-11-08 20:00","2015-10-31 08:00","2015-11-01 20:00","연속",null,null,null,201509210024,"-"]
[36,"인천","김포","양촌양곡#2 T/L","154kV 양촌-양곡T/L No.2, 9, 13 지장철탑 이설공사","□ 김포학운4산업단지 및 제 2외곽순환도로 조성에 따른 지장철탑 이설 □ 공사개요 : 154kV 양촌-양곡T/L No.2, 9, 13 이설 - No.2 ,9 본철탑 이설, No.13 가철탑 이설","2015-11-06 07:00","2015-11-11 18:00","2015-11-13 07:00","2015-11-18 18:00","연속",null,null,"신뢰도개선",201509110157,"-"]
[37,"인천","김포","양촌양곡#1 T/L","154kV 양촌-양곡T/L No.2, 9, 13 지장철탑 이설공사","□ 김포학운4산업단지 및 제 2외곽순환도로 조성에 따른 지장철탑 이설 □ 공사개요 : 154kV 양촌-양곡T/L No.2, 9, 13 이설 - No.2 ,9 본철탑 이설, No.13 가철탑 이설","2015-11-01 07:00","2015-11-05 18:00","2015-11-07 07:00","2015-11-11 18:00","연속",null,null,"신뢰도개선",201509110156,"-"]
[38,"인천","김포","양촌양곡#2 T/L","154kV 양촌-양곡T/L No.2, 9, 13 지장철탑 이설공사","□ 김포학운4산업단지 및 제 2외곽순환도로 조성에 따른 지장철탑 이설 □ 공사개요 : 154kV 양촌-양곡T/L No.2, 9, 13 이설 - No.2 ,9 본철탑 이설, No.13 가철탑 이설","2015-11-01 07:00","2015-11-01 18:00","2015-11-08 07:00","2015-11-08 18:00","당일",null,null,"신뢰도개선",201509140044,"-"]
[39,"인천","김포","양촌양곡#1 T/L","154kV 양촌-양곡T/L No.2, 9, 13 지장철탑 이설공사","□ 김포학운4산업단지 및 제 2외곽순환도로 조성에 따른 지장철탑 이설 □ 공사개요 : 154kV 양촌-양곡T/L No.2, 9, 13 이설 - No.2 ,9 본철탑 이설, No.13 가철탑 이설","2015-11-13 07:00","2015-11-16 18:00","2015-11-19 07:00","2015-11-22 18:00","연속",null,null,"신뢰도개선",201509110159,"-"]
[40,"인천","시흥","시화동시화#2 T/L","영인기술 보호배전반반 성능개선","- BFI 및 Trip 접점 변경","2015-11-07 14:00","2015-11-07 17:00","2015-11-07 14:00","2015-11-07 17:00","당일",null,null,null,201509040051,"-"]
[41,"인천","시흥","시화동시화#1 T/L","영인기술 보호배전반반 성능개선","- BFI 및 Trip 접점 변경","2015-11-07 10:00","2015-11-07 14:00","2015-11-07 10:00","2015-11-07 14:00","당일",null,null,null,201509040050,"-"]
[42,"인천","시흥","서서울소래 T/L","서서울-소래T/L 초기점검","서서울-소래T/L 초기점검(45,47호)","2015-11-04 09:00","2015-11-04 12:00","2015-11-04 09:00","2015-11-04 12:00","당일",null,null,null,201509070111,"-"]
[43,"인천","시흥","신시흥북시화#1 T/L","영인기술 보호배전반반 성능개선","- BFI 및 Trip 접점 변경","2015-11-08 10:00","2015-11-08 14:00","2015-11-08 10:00","2015-11-08 14:00","당일",null,null,null,201509040048,"-"]
[44,"인천","시흥","신시흥북시화#2 T/L","영인기술 보호배전반반 성능개선","- BFI 및 Trip 접점 변경","2015-11-08 14:00","2015-11-08 17:00","2015-11-08 14:00","2015-11-08 17:00","당일",null,null,null,201509040049,"-"]
[45,"인천","인천","경서북인천#2 T/L","북인천S/S 경서북인천#2T/L 보호반 대체 및 GIS 하자점검","북인천S/S 경서북인천#2T/L 보호반 대체 및 GIS 하자점검","2015-11-17 09:00","2015-11-21 18:00","2015-11-17 09:00","2015-11-21 18:00","연속",null,null,null,201508100047,"-"]
[46,"인천","인천","영종S/S 154kV #1 BUS TIE GIS","영종S/S 모선보호반 대체 공사(모선보호반 정지)","영종S/S 모선보호반 대체 공사(모선보호반 정지)","2015-11-02 09:00","2015-11-05 18:00","2015-11-02 09:00","2015-11-05 18:00","연속",null,null,null,201509040056,"-"]
[47,"인천","직할","계양원창 T/L","345kV가정루원시티 지중화 정비공사","345kV 가정루원시티 지중화 정비공사 ※ 금번작업 : 가공송전(계양-원창 No.13 직결), 지중종전, 변전 작업 -신설:3기[4회선(345kV 신가좌-인천CC No.18),2회선 C/H(154kV, 345kV)] -교체:1기[345kV 신가좌-인천CC No.19 Enclosing 공법으로 철탑교체] -철거:20기[345kV 5기, 154kV 15","2015-11-01 09:00","2015-11-15 18:00","2015-11-01 09:00","2015-11-15 18:00","연속",null,null,null,201508070184,"-"]
[48,"인천","직할","신부평고강#1 T/L","영인기술 보호배전반반 성능개선","- BFI 및 Trip 접점 변경","2015-11-01 10:00","2015-11-01 14:00","2015-11-01 10:00","2015-11-01 14:00","당일",null,null,null,201509040052,"-"]
[49,"인천","직할","신부평고강#2 T/L","영인기술 보호배전반반 성능개선","- BFI 및 Trip 접점 변경","2015-11-01 14:00","2015-11-01 17:00","2015-11-01 14:00","2015-11-01 17:00","당일",null,null,null,201509040053,"-"]
[50,"인천","직할","중동화곡#1 T/L","No.8~14 철탑 가공지선 교체공사","No.8~14 철탑 가공지선 교체공사","2015-11-07 09:00","2015-11-07 18:00","2015-11-07 09:00","2015-11-07 18:00","당일",null,null,null,201509100099,"-"]
[51,"인천","직할","중동화곡#2 T/L","No.8~14 철탑 가공지선 교체공사","No.8~14 철탑 가공지선 교체공사","2015-11-07 09:00","2015-11-07 18:00","2015-11-07 09:00","2015-11-07 18:00","당일",null,null,null,201509100100,"-"]
[52,"경기북부","구리","가평청평HP#2 T/L","가평S/S 170kV 장기사용 GIS 대체공사 (4차 설치분)","170kV GIS × 8Bay (TL 4, M.Tr 2, BT 1, PT 1) 철거 설치","2015-11-10 09:00","2015-11-29 18:00","2015-11-10 09:00","2015-11-29 18:00","연속",null,null,null,201507070172,"-"]
[53,"경기북부","구리","덕소별내#1 T/L","진건지구 지장철탑 이설공사","철탑 설치11기, 철거8기","2015-11-16 07:00","2015-11-25 18:00","2015-11-16 07:00","2015-11-25 18:00","연속",null,null,null,201509140218,"○"]
[54,"경기북부","구리","덕소별내#2 T/L","진건지구 지장철탑 이설공사","철탑 설치11기, 철거8기","2015-11-26 07:00","2015-12-05 18:00","2015-11-26 07:00","2015-12-05 18:00","연속",null,null,null,201509140220,"-"]
[55,"경기북부","구리","덕소별내#2 T/L","진건지구 지장철탑 이설공사","철탑 설치11기, 철거8기","2015-11-13 07:00","2015-11-15 18:00","2015-11-13 07:00","2015-11-15 18:00","연속",null,null,null,201509140216,"-"]
[56,"경기북부","구리","운천철원#1 T/L","154kV 철원S/S 옥외철구 GIS화 공사","옥외철구 GIS화","2015-11-10 09:00","2015-11-15 18:00","2015-11-10 09:00","2015-11-15 18:00","연속",null,null,null,201509140298,"○"]
[57,"경기북부","구리","철원화천#1 T/L","154kV 철원S/S 옥외철구 GIS화 공사","옥외철구 GIS화","2015-11-30 09:00","2015-12-05 18:00","2015-11-30 09:00","2015-12-05 18:00","연속",null,null,null,201509140305,"○"]
[58,"경기북부","구리","철원화천#2 T/L","154kV 철원S/S 옥외철구 GIS화 공사","옥외철구 GIS화","2015-11-23 09:00","2015-11-27 18:00","2015-11-23 09:00","2015-11-27 18:00","연속",null,null,null,201509140303,"-"]
[59,"경기북부","구리","청평P/P #2 M.Tr 2차 CB","청평P/P #2 M.Tr 2차 CB 관련 단로기 조작함 교체","154kV 단로기 조작함 교체 : 6236-1, 6236-2","2015-11-03 09:00","2015-11-04 18:00","2015-11-03 09:00","2015-11-04 18:00","매일",null,null,null,201509110325,"-"]
[60,"경기북부","직할","의정부도봉#1 T/L","345kV 신의정부S/S 관련T/L 송전선로 건설공사","○ 철탑기수 : 6기(C/H 1기, 4회선용 4각 철탑 5기) ○ 선로길이 : 4C- 1.896km ○ 선 종 : ACSR410㎟ × 2B","2015-11-02 07:00","2015-11-20 18:00","2015-11-02 07:00","2015-11-20 18:00","연속",null,null,null,201509020075,"-"]
[61,"경기북부","직할","의정부도봉#2 T/L","345kV 신의정부S/S 관련T/L 송전선로 건설공사","○ 철탑기수 : 6기(C/H 1기, 4회선용 4각 철탑 5기) ○ 선로길이 : 4C- 1.896km ○ 선 종 : ACSR410㎟ × 2B","2015-11-21 07:00","2015-12-02 18:00","2015-11-21 07:00","2015-12-02 18:00","연속",null,null,null,201509020077,"-"]
[62,"경기북부","직할","신의정부의정부#2 T/L","154kV 금오-상계 지중T/L 건설공사","케이블 포설 및 접속","2015-11-21 08:00","2015-12-21 18:00","2015-11-21 08:00","2015-12-21 18:00","연속",null,null,"신뢰도개선",201507160060,"-"]
[63,"경기북부","직할","양주금촌#1 T/L","345kV 양주-중부T/L 전력선교체공사(병행선로 휴전)","345kV 양주-중부T/L 전력선교체공사(병행선로 휴전) - 상단횡단 선로 병행휴전","2015-11-07 07:00","2015-11-09 18:00","2015-11-07 07:00","2015-11-09 18:00","매일",null,null,"신뢰도개선",201509110263,"-"]
[64,"경기북부","직할","양주금촌#2 T/L","345kV 양주-중부T/L 전력선교체공사(병행선로 휴전)","345kV 양주-중부T/L 전력선교체공사(병행선로 휴전) - 상단횡단 선로 병행휴전","2015-11-07 07:00","2015-11-09 18:00","2015-11-07 07:00","2015-11-09 18:00","매일",null,null,"신뢰도개선",201509110266,"-"]
[65,"경기북부","직할","양주일산#2 T/L","345kV 양주-중부T/L 전력선교체공사(병행선로 휴전)","345kV 양주-중부T/L 전력선교체공사(병행선로 휴전) - 상단횡단 선로 병행휴전","2015-11-07 07:00","2015-11-09 18:00","2015-11-07 07:00","2015-11-09 18:00","매일",null,null,null,201509110248,"-"]
[66,"경기북부","직할","양주금촌#2 T/L","345kV 양주-중부T/L 전력선교체공사(병행선로 휴전)","345kV 양주-중부T/L 전력선교체공사(병행선로 휴전) - 상단횡단 선로 병행휴전","2015-11-13 07:00","2015-11-15 18:00","2015-11-13 07:00","2015-11-15 18:00","매일",null,null,"신뢰도개선",201509110265,"-"]
[67,"경기북부","직할","양주금촌#1 T/L","345kV 양주-중부T/L 전력선교체공사(병행선로 휴전)","345kV 양주-중부T/L 전력선교체공사(병행선로 휴전) - 상단횡단 선로 병행휴전","2015-11-13 07:00","2015-11-15 18:00","2015-11-13 07:00","2015-11-15 18:00","매일",null,null,"신뢰도개선",201509110264,"-"]
[68,"경기북부","직할","양주일산#2 T/L","345kV 양주-중부T/L 전력선교체공사(병행선로 휴전)","345kV 양주-중부T/L 전력선교체공사(병행선로 휴전) - 상단횡단 선로 병행휴전","2015-11-13 07:00","2015-11-15 18:00","2015-11-13 07:00","2015-11-15 18:00","매일",null,null,null,201509110262,"-"]
[69,"경기북부","파주","지도능곡#1 T/L","2015년 하반기 파주전력 170kV GIS 정밀점검공사","지도S/S 지도-능곡#1T/L GIS 정밀점검","2015-11-17 09:00","2015-11-19 14:00","2015-11-17 09:00","2015-11-19 14:00","연속",null,null,null,201508180209,"-"]
[70,"경기북부","파주","불광서대문#1 T/L","2015년 하반기 파주전력 170kV GIS 정밀점검공사","불광S/S 불광-서대문#1T/L GIS 정밀점검","2015-11-23 09:00","2015-11-25 14:00","2015-11-23 09:00","2015-11-25 14:00","연속",null,null,null,201509150016,"-"]
[71,"경기북부","파주","신파주금촌#1 T/L","154kV 신파주-금촌#1T/L 안전이격확보공사","안전이격확보공사#1T/L 공중이동(가선로 구성)","2015-11-16 07:00","2015-11-17 18:00","2015-11-16 07:00","2015-11-17 18:00","연속",null,null,null,201509110368,"-"]
[72,"경기북부","파주","신파주금촌#2 T/L","154kV 신파주-금촌#2T/L 안전이격확보공사","안전이격확보공사 #2T/L 철탑 철거 및 신규설치","2015-11-18 07:00","2015-12-02 18:00","2015-11-18 07:00","2015-12-02 18:00","연속",null,null,null,201509110367,"-"]
[73,"경기북부","파주","일산S/S #2G/T GIS","일산S/S 축소형 Mosaic 배전반 대체공사","#2G/T GIS(6313 CB) 제어케이블 철거 후 포설 및 결선","2015-11-15 08:00","2015-11-15 18:00","2015-11-15 08:00","2015-11-15 18:00","연속",null,null,null,201509100181,"-"]
[74,"경기북부","파주","일산S/S #3G/T GIS","일산S/S 축소형 Mosaic 배전반 대체공사","#3G/T GIS(6413 CB) 제어케이블 철거 후 포설 및 결선","2015-11-14 08:00","2015-11-14 18:00","2015-11-14 08:00","2015-11-14 18:00","연속",null,null,null,201509100177,"-"]
[75,"경기북부","파주","일산지도#2 T/L","일산S/S 축소형 Mosaic 배전반 대체공사","일산지도#2 T/L(627 CB) 제어케이블 철거 후 포설 및 결선","2015-11-10 09:00","2015-11-11 18:00","2015-11-10 09:00","2015-11-11 18:00","연속",null,null,null,201509100184,"-"]
[76,"경기북부","파주","일산S/S #4G/T GIS","일산S/S 축소형 Mosaic 배전반 대체공사","#4G/T GIS(6513 CB) 제어케이블 철거 후 포설 및 결선","2015-11-08 08:00","2015-11-08 18:00","2015-11-08 08:00","2015-11-08 18:00","연속",null,null,null,201509100175,"-"]
[77,"경기북부","파주","일산S/S #1S/T GIS","일산S/S 축소형 Mosaic 배전반 대체공사","#1S/T GIS(6113 CB) 제어케이블 철거 후 포설 및 결선","2015-11-07 08:00","2015-11-07 18:00","2015-11-07 08:00","2015-11-07 18:00","연속",null,null,null,201509100173,"-"]
[78,"경기북부","파주","일산S/S 154kV #65 BUS","일산S/S 축소형 Mosaic 배전반 대체공사","154kV #65 BUS 제어케이블 철거 후 포설 및 결선","2015-11-06 09:00","2015-11-07 18:00","2015-11-06 09:00","2015-11-07 18:00","연속",null,null,null,201509100194,"-"]
[79,"경기북부","파주","양주일산#1 T/L","154kV 고양분기T/L 건설공사","○ 사업목적 : 경기도 고양시 풍동, 식사택지지구의 신규 부하공급 및 인근 송포, 일산, 호수변전소의 중부하 해소를 위함 ○ 사업규모 : 0.738km(1기 C/H) ○ 작업내용 : 154kV 양주-일산T/L No.39 → 신설C/H 교체 - 1차휴전 : 가선로 구성(#2T/L : 9/13~15, #1T/L : 9/16~20) - 2차휴전 : C/H 설치(#1T/L : 11/5~13, 안전이격거리확보) - 3차휴전 : 본선로 구성(#1T/L : 12/16~20, #2T/L : 12/21~25)","2015-11-05 07:00","2015-11-15 18:00","2015-11-05 07:00","2015-11-15 18:00","연속",null,null,null,201509110432,"○"]
[80,"경기북부","파주","일산S/S 154kV #60 BUS","일산S/S 축소형 Mosaic 배전반 대체공사","154kV #60BUS 제어케이블 철거 후 포설 및 결선","2015-11-04 09:00","2015-11-05 18:00","2015-11-04 09:00","2015-11-05 18:00","연속",null,null,null,201509100193,"-"]
[81,"경기북부","파주","일산S/S #1G/T GIS","일산S/S 축소형 Mosaic 배전반 대체공사","#1G/T GIS(6213 CB) 제어케이블 철거 후 포설 및 결선","2015-11-22 08:00","2015-11-22 18:00","2015-11-22 08:00","2015-11-22 18:00","연속",null,null,null,201509100182,"-"]
[82,"경기북부","파주","일산호수#1 T/L","일산S/S 축소형 Mosaic 배전반 대체공사","일산호수#1 T/L(687 CB) 제어케이블 철거 후 포설 및 결선","2015-11-20 09:00","2015-11-21 18:00","2015-11-20 09:00","2015-11-21 18:00","연속",null,null,null,201509100190,"-"]
[83,"경기북부","파주","일산호수#2 T/L","일산S/S 축소형 Mosaic 배전반 대체공사","일산호수#2 T/L(697 CB) 제어케이블 철거 후 포설 및 결선","2015-11-18 09:00","2015-11-19 18:00","2015-11-18 09:00","2015-11-19 18:00","연속",null,null,null,201509100189,"-"]
[84,"경기북부","파주","일산지도#1 T/L","일산S/S 축소형 Mosaic 배전반 대체공사","일산지도#1 T/L(617 CB) 제어케이블 철거 후 포설 및 결선","2015-11-16 09:00","2015-11-17 18:00","2015-11-16 09:00","2015-11-17 18:00","연속",null,null,null,201509100186,"-"]
[85,"경기","군포","서서울서안양 T/L","서서울-서안양T/L 초기점검","서서울-서안양T/L 초기점검(45.47호)","2015-11-04 13:00","2015-11-04 18:00","2015-11-04 13:00","2015-11-04 18:00","당일",null,null,null,201509070116,"-"]
[86,"경기","군포","일동S/S 154kV #1 BUS","일동S/S 154kV #60Bus","일동S/S 154kV 장기사용 GIS교체공사 : 서서울일동#2, #3MTr 1차 GIS","2015-11-16 09:00","2015-11-22 18:00","2015-11-16 09:00","2015-11-22 18:00","연속",null,null,null,201509080016,"-"]
[87,"경기","군포","일동S/S 154kV #1 BUS","일동S/S 154kV #60Bus","일동S/S 154kV 장기사용 GIS교체공사 : 서서울일동#2, #3MTr 1차 GIS","2015-11-29 09:00","2015-11-29 18:00","2015-11-29 09:00","2015-11-29 18:00","연속",null,null,null,201509080018,"-"]
[88,"경기","군포","일동S/S 154kV #2 BUS","일동S/S 154kV #65Bus","일동S/S 154kV 장기사용 GIS교체공사 : 서서울일동#2, #3MTr 1차 GIS","2015-11-23 09:00","2015-11-28 18:00","2015-11-23 09:00","2015-11-28 18:00","연속",null,null,null,201509080017,"-"]
[89,"경기","군포","서서울일동#2 T/L","일동S/S 154kV 서서울일동#2TL GIS 대체공사","일동S/S 154kV 장기사용 GIS교체공사 : 서서울일동#2T/L GIS","2015-11-13 09:00","2015-11-30 18:00","2015-11-13 09:00","2015-11-30 18:00","연속",null,null,null,201509080013,"-"]
[90,"경기","군포","일동S/S 154kV #2 BUS","일동S/S 154kV #65Bus","일동S/S 154kV 장기사용 GIS교체공사 : 서서울일동#2, #3MTr 1차 GIS","2015-11-13 09:00","2015-11-15 18:00","2015-11-13 09:00","2015-11-15 18:00","연속",null,null,null,201509080015,"-"]
[91,"경기","군포","일동S/S 154kV #2 BUS","일동S/S 154kV #65Bus","일동SS 154kV 장기사용 GIS 교체공사 : 일동S/S 서서울일동#1, #1MTr 1차 GIS 교체공사","2015-11-05 09:00","2015-11-10 18:00","2015-11-05 09:00","2015-11-10 18:00","연속",null,null,null,201508180109,"-"]
[92,"경기","군포","일동S/S 154kV #1 BUS","일동S/S 154kV #60Bus","일동SS 154kV 장기사용 GIS 교체공사 : 일동S/S 서서울일동#1, #1MTr 1차 GIS 교체공사","2015-11-11 09:00","2015-11-11 18:00","2015-11-11 09:00","2015-11-11 18:00","연속",null,null,null,201508180115,"-"]
[93,"경기","동부","왕암가남#1 T/L","154kV 왕암-가남T/L 노후취약지지물 교체공사(185,186호)","지지물 교체 철거(2기), 설치(2기)","2015-11-13 00:08","2015-11-15 19:00","2015-11-13 00:08","2015-11-15 19:00","연속",null,null,null,201509070145,"-"]
[94,"경기","동부","왕암가남#2 T/L","154kV 왕암-가남T/L 노후취약지지물 교체공사(185,186호)","지지물 교체 철거(2기), 설치(2기)","2015-11-13 00:08","2015-11-15 19:00","2015-11-13 00:08","2015-11-15 19:00","연속",null,null,null,201509070146,"-"]
[95,"경기","동부","이천율현#1 T/L","이천,율현S/S 이천율현#1T/L 보호PNL 대체","이천,율현S/S 이천율현#1T/L 보호PNL 대체","2015-11-06 09:00","2015-11-08 18:00","2015-11-06 09:00","2015-11-08 18:00","연속",null,null,"신뢰도개선",201509110341,"-"]
[96,"경기","성남","서안성안성#2 T/L","154kV 서운-안성#2T/L 가공지선 설치공사(안전확보)","○ 구간 : 서운-안성#2T/L S/T~No.1(상단 서안성-안성#2T/L) ○ 내용 : 미차폐구간 가공지선 설치","2015-11-08 08:00","2015-11-08 18:00","2015-11-08 08:00","2015-11-08 18:00","당일",null,null,null,201509110293,"-"]
[97,"경기","성남","신성남정자#1 T/L","신성남S/S 154kV 신성남-정자#1 T/L","신성남S/S 신성남-정자#1 T/L PNL 대체","2015-11-23 09:00","2015-11-25 18:00","2015-11-23 09:00","2015-11-25 18:00","연속",null,null,"신뢰도개선",201509100500,"-"]
[98,"경기","직할","남수원발안#2 T/L","154kV 남수원-발안T/L 27호 안전이격확보공사","ㅇ 남수원발안T/L 27호 철탑 철거 및 설치 ㅇ 애자련 철거 및 설치","2015-11-29 07:00","2015-12-07 18:00","2015-11-29 07:00","2015-12-07 18:00","연속",null,null,null,201509090098,"-"]
[99,"경기","직할","남수원발안#1 T/L","154kV 남수원-발안T/L 27호 안전이격확보공사","ㅇ 남수원발안T/L 27호 철탑 철거 및 설치 ㅇ 애자련 철거 및 설치","2015-11-29 07:00","2015-12-07 18:00","2015-11-29 07:00","2015-12-07 18:00","연속",null,null,null,201509090096,"-"]
[100,"경기","평택","송탄S/S 송탄-오성복합#1T/L(627) GIS","송탄S/S 154kV 송탄오성복합#1T/L GIS 대체 공사","송탄S/S 154kV 송탄오성복합#1T/L GIS 대체 공사","2015-11-09 09:00","2015-11-24 18:00","2015-11-09 09:00","2015-11-24 18:00","연속",null,null,null,201509080106,"○"]
[101,"경기","평택","송탄오성CC#2 T/L","154kV 송탄-오성CC#2T/L 전력선 이도조정공사","○ 구간 : 송탄-오성CC#2T/L No.11~13 ○ 내용 : 상단,중단,하단 전력선 이도조정","2015-11-01 08:00","2015-11-01 18:00","2015-11-01 08:00","2015-11-01 18:00","당일",null,null,null,201509110282,"-"]
[102,"경기","평택","원정S/S 평택T/P-원정#1T/L GIS","원정S/S 평택TP원정 #1T/L LA 교체공사","원정S/S 평택TP원정 #1T/L LA 교체공사","2015-11-01 09:00","2015-11-01 18:00","2015-11-01 09:00","2015-11-01 18:00","당일",null,null,null,201509040153,"-"]
[103,"경기","평택","원정S/S 원정-평택T/P#3T/L GIS","원정S/S 원정평택T/P #3T/L CVT 교체공사","원정S/S 원정평택T/P #3T/L CVT 교체공사","2015-11-08 09:00","2015-11-08 18:00","2015-11-08 09:00","2015-11-08 18:00","당일",null,null,null,201509040149,"-"]
[104,"경기","평택","추팔S/S 평택-추팔#1T/L GIS","추팔S/S 평택추팔#1T/L 노후보호반 대체","추팔S/S 평택추팔#1T/L 보호반 대체(평택, 추팔S/S 양단 노후보호반 대체)","2015-11-01 09:00","2015-11-03 18:00","2015-11-01 09:00","2015-11-03 18:00","연속",null,null,null,201509040146,"-"]
[105,"경기","평택","추팔S/S 평택-추팔#2T/L GIS","추팔S/S 평택추팔#2T/L 노후보호반 대체","추팔S/S 평택추팔#2T/L 보호반 대체(평택, 추팔S/S 양단 노후보호반 대체)","2015-11-04 09:00","2015-11-06 18:00","2015-11-04 09:00","2015-11-06 18:00","연속",null,null,null,201509040148,"-"]
[106,"경기","평택","평택S/S 오산-평택#1T/L CB","평택S/S 오산-평택#1T/L 공기압축기 기동용 압력계 교체","평택S/S 오산-평택#1T/L 공기압축기 기동용 압력계 교체","2015-11-07 10:00","2015-11-07 18:00","2015-11-07 10:00","2015-11-07 18:00","당일",null,null,null,201509080081,"-"]
[107,"강원","강릉","동해강릉 T/L","154kV 동해분기T/L 안전이격확보공사","지지물 설치/철거 : 1기, 계탑 : 2기, 가철주 설치 : 2기, 전력선 교체 : 2C-0.855km","2015-11-07 09:00","2015-11-18 18:00","2015-11-07 09:00","2015-11-18 18:00","연속",null,null,null,201507270042,"-"]
[108,"강원","강릉","동해영동TP T/L","154kV 동해분기T/L 안전이격확보공사","지지물 설치/철거 : 1기, 계탑 : 2기, 가철주 설치 : 2기, 전력선 교체 : 2C-0.855km","2015-11-19 09:00","2015-11-22 18:00","2015-11-19 09:00","2015-11-22 18:00","연속",null,null,null,201507270044,"-"]
[109,"강원","강릉","동해영동TP T/L","154kV 동해분기T/L 안전이격확보공사","지지물 설치/철거 : 1기, 계탑 : 2기, 가철주 설치 : 2기, 전력선 교체 : 2C-0.855km","2015-11-03 09:00","2015-11-06 18:00","2015-11-03 09:00","2015-11-06 18:00","연속",null,null,null,201507270043,"-"]
[110,"강원","강릉","주진평창#2 T/L","154kV 주진평창T/L 철탑기초보강공사","○ No.56~57 철탑기초보강공사","2015-11-23 09:00","2015-11-27 18:00","2015-11-23 09:00","2015-11-27 18:00","연속",null,null,null,201508240034,"-"]
[111,"강원","강릉","주진평창#1 T/L","154kV 주진평창T/L 철탑기초보강공사","○ No.56~57 철탑기초보강공사","2015-11-16 09:00","2015-11-20 18:00","2015-11-16 09:00","2015-11-20 18:00","연속",null,null,null,201508240033,"-"]
[112,"강원","동해","동해동영월 T/L","154kV 영월화력T/L No.236~237 안전이격확보공사","No.236~237 안전이격확보공사","2015-11-13 08:00","2015-11-23 18:00","2015-11-13 08:00","2015-11-23 18:00","연속",null,null,null,201509110161,"-"]
[113,"강원","동해","동해정선 T/L","154kV 영월화력T/L No.236~237 안전이격확보공사","No.236~237 안전이격확보공사","2015-11-02 08:00","2015-11-11 18:00","2015-11-02 08:00","2015-11-11 18:00","연속",null,null,null,201509110160,"-"]
[114,"강원","원주","횡성홍천#2 T/L","154kV 홍천T/L 안전이격 확보공사","철거 : 6기, 신설 4기, 전력선 교체 5.0 C-km","2015-11-16 09:00","2015-11-21 18:00","2015-11-16 09:00","2015-11-21 18:00","연속",null,null,null,201508210128,"-"]
[115,"강원","원주","횡성홍천#1 T/L","154kV 홍천T/L 안전이격 확보공사","철거 : 6기, 신설 4기, 전력선 교체 5.0 C-km","2015-11-16 09:00","2015-11-23 18:00","2015-11-16 09:00","2015-11-23 18:00","연속",null,null,null,201508210127,"-"]
[116,"강원","직할","상남인제#2 T/L","2015년 강원본부 직할 협력회사 총액공사","상남-인제#2T/L GIS 상시여자형 계전기 교체공사","2015-11-03 10:00","2015-11-03 18:00","2015-11-03 10:00","2015-11-03 18:00","당일",null,null,null,201509210190,"-"]
[117,"강원","태백","도계태백 T/L","태백변전소 배전반 이설공사","도계-태백T/L 보호배전반 이설","2015-11-13 09:00","2015-11-16 18:00","2015-11-13 09:00","2015-11-16 18:00","연속",null,null,null,201509080203,"-"]
[118,"강원","태백","이원태백 T/L","태백변전소 배전반 이설공사","이원-태백T/L 보호배전반 이설","2015-11-02 09:00","2015-11-08 18:00","2015-11-02 09:00","2015-11-08 18:00","연속",null,null,null,201509080201,"○"]
[119,"강원","태백","태백영월 T/L","태백변전소 배전반 이설공사","태백-영월T/L 보호배전반 이설","2015-11-17 09:00","2015-11-21 18:00","2015-11-30 09:00","2015-12-03 18:00","연속",null,null,null,201509080204,"○"]
[120,"강원","태백","태백울진#2(경동,석공장성T분기) T/L","154kV 삼척그린파워분기T/L 건설공사","1. 154kV 태백-울진#1,2T/L 전선교체(기설 141호∼기설 145호) ㅇ ACSR 330㎟ X S → HSTACIR 330㎟ X S 2. 신설 No.1호 (분기철탑) 계통연결 ㅇ 전선이동 : 가선로 → 신설철탑(No.1) ㅇ No.1 긴선, 점퍼연결","2015-11-22 09:00","2015-11-29 11:00","2015-11-22 09:00","2015-11-29 11:00","연속",null,null,null,201508240237,"-"]
[121,"강원","태백","태백고한 T/L","태백변전소 배전반 이설공사","태백-고한T/L 보호배전반 이설","2015-11-23 09:00","2015-11-26 18:00","2015-11-09 09:00","2015-11-11 18:00","연속",null,null,null,201509080206,"-"]
[122,"강원","태백","태백울진#1 T/L","154kV 삼척그린파워분기T/L 건설공사","1. 154kV 태백-울진#1,2T/L 전선교체(기설 141호∼기설 145호) ㅇ ACSR 330㎟ X S → HSTACIR 330㎟ X S 2. 신설 No.1호 (분기철탑) 계통연결 ㅇ 전선이동 : 가선로 → 신설철탑(No.1) ㅇ No.1 긴선, 점퍼연결","2015-11-28 08:00","2015-12-04 17:00","2015-11-28 08:00","2015-12-04 17:00","연속",null,null,null,201508240232,"-"]
[123,"충북","직할","단양영월CC#1 T/L","2014~15년 송전정비 협력회사 총액공사","불량애자 교체","2015-11-09 08:00","2015-11-10 18:00","2015-11-09 08:00","2015-11-10 18:00","매일",null,null,null,201509080160,"-"]
[124,"충북","직할","단양영월CC#2 T/L","2014~15년 송전정비 협력회사 총액공사","불량애자 교체","2015-11-11 08:00","2015-11-12 18:00","2015-11-11 08:00","2015-11-12 18:00","매일",null,null,null,201509080161,"-"]
[125,"충북","직할","신제천S/S 154kV #2 BUS TIE CB","345kV 신제천S/S GIS화 공사","345kV GIS 15CB, 154kV GIS 28CCT - 154kV GIS와 신축제어동 연결 덕트 설치구간 작업공간 확보","2015-11-09 09:00","2017-12-29 18:00","2015-11-09 09:00","2017-12-29 18:00","연속",null,null,null,201509080001,"-"]
[126,"충북","직할","신제천제천#2 T/L","154kV 신제천-제천T/L 27.5호 안전이격확보공사","154kV 신제천-제천T/L 27.5호 철탑교체","2015-11-17 08:00","2015-11-26 18:00","2015-11-17 08:00","2015-11-26 18:00","연속",null,null,null,201509080004,"-"]
[127,"충북","직할","신제천제천#1 T/L","154kV 신제천-제천T/L 27.5호 안전이격확보공사","154kV 신제천-제천T/L 27.5호 철탑교체","2015-11-17 08:00","2015-11-23 18:00","2015-11-17 08:00","2015-11-23 18:00","연속",null,null,null,201509080003,"-"]
[128,"충북","직할","신제천왕암#2 T/L","2015년 가공송전선로 순시점검 위탁공사","지장수목전지 (수목전동카트 시범사용)","2015-11-07 08:00","2015-11-07 18:00","2015-11-07 08:00","2015-11-07 18:00","당일",null,null,null,201509080168,"-"]
[129,"충북","직할","신제천-영월CC#1 T/L","2015년 가공송전선로 순시점검 위탁공사","송전선로용 피뢰기 설치개소 아킹혼 철거","2015-11-02 08:00","2015-11-05 18:00","2015-11-02 08:00","2015-11-05 18:00","매일",null,null,null,201509080154,"-"]
[130,"충북","직할","왕암북충주#1 T/L","2015년 가공송전선로 순시점검 위탁공사","불량애자 교체","2015-11-16 08:00","2015-11-16 18:00","2015-11-16 08:00","2015-11-16 18:00","당일",null,null,null,201509080165,"-"]
[131,"충북","직할","제천영월#2 T/L","2014~15년 송전정비 협력회사 총액공사","불량애자 및 국산애자 교체","2015-11-11 08:00","2015-11-12 18:00","2015-11-11 08:00","2015-11-12 18:00","매일",null,null,null,201509080158,"-"]
[132,"충북","직할","제천영월#1 T/L","2014~15년 송전정비 협력회사 총액공사","불량애자 및 국산애자 교체","2015-11-09 08:00","2015-11-10 18:00","2015-11-09 08:00","2015-11-10 18:00","매일",null,null,null,201509080157,"-"]
[133,"충북","충주","북충주충주#1 T/L","2015년도 가공송전선로 순시점검 위탁공사","송전선로 정밀점검 (북충주충주#1, #2T/L)","2015-11-02 09:00","2015-11-06 18:00","2015-11-02 09:00","2015-11-06 18:00","매일",null,null,null,201509070286,"-"]
[134,"충북","충주","충주충주HP#2 T/L","2015년도 가공송전선로 순시점검 위탁공사","송전선로 정밀점검 (충주충주H/P #1, #2T/L)","2015-11-04 09:00","2015-11-06 18:00","2015-11-04 09:00","2015-11-06 18:00","매일",null,null,null,201509070291,"-"]
[135,"충북","충주","북충주충주#2 T/L","2015년도 가공송전선로 순시점검 위탁공사","송전선로 정밀점검 (북충주충주#1, #2T/L)","2015-11-09 09:00","2015-11-16 18:00","2015-11-09 09:00","2015-11-16 18:00","매일",null,null,null,201509070287,"-"]
[136,"충북","충주","충주충주HP#1 T/L","2015년도 가공송전선로 순시점검 위탁공사","송전선로 정밀점검 (충주충주H/P #1, #2T/L)","2015-11-11 09:00","2015-11-16 18:00","2015-11-11 09:00","2015-11-16 18:00","매일",null,null,null,201509070289,"○"]
[137,"충북","직할","신제천주진#2 T/L","345kV 신제천S/S GIS화 공사","154kV T-BUS 철거 (GIS 설치공간확보)","2015-11-02 08:00","2015-11-02 18:00","2015-11-02 08:00","2015-11-02 18:00","당일",null,null,null,201509250016,"-"]
[138,"충북","직할","신제천남원주#1 T/L","345kV 신제천S/S GIS화 공사","154kV T-BUS 철거 (GIS 설치공간확보)","2015-11-03 08:00","2015-11-03 18:00","2015-11-03 08:00","2015-11-03 18:00","당일",null,null,null,201509240040,"-"]
[139,"충북","직할","신제천남원주#2 T/L","345kV 신제천S/S GIS화 공사","154kV T-BUS 철거 (GIS 설치공간확보)","2015-11-04 08:00","2015-11-04 18:00","2015-11-04 08:00","2015-11-04 18:00","당일",null,null,null,201509240041,"-"]
[140,"대전충남","대전","신옥천서대전#1 T/L","154kV 서대전S/S 지중케이블 계통정비공사","154kV 신옥천-서대전T/L 지중케이블 일부구간 케이블 선종 변경","2015-11-02 09:00","2015-11-24 18:00","2015-11-02 09:00","2015-11-24 18:00","연속",null,null,"신뢰도개선",201509040015,"-"]
[141,"대전충남","서산","태안안면#2 T/L","태안S/S 170kV 장기사용 GIS대체공사","○ 170KV GIS 대체(태안-안면#2T/L)","2015-11-13 09:00","2015-12-04 18:00","2015-11-13 09:00","2015-12-04 18:00","연속",null,null,null,201509110237,"-"]
[142,"대전충남","아산","온양풍세#1 T/L","온양S/S 154k 효성제 GIS 전자변 히터설치","○154kV 온양-풍세#1T/L 637 GIS 전자변 히터설치 ○154kV 온양-풍세#2T/L 6A7 GIS 전자변 히터설치 ○154kV BUS-TIE 6100 GIS 전자변 히터설치","2015-11-03 09:00","2015-11-03 11:30","2015-11-03 09:00","2015-11-03 11:30","당일",null,null,null,201509040072,"-"]
[143,"대전충남","아산","온양풍세#2 T/L","온양S/S 154k 효성제 GIS 전자변 히터설치","○154kV 온양-풍세#2T/L 647 GIS 전자변 히터설치 ○154kV 온양-풍세#2T/L 647 GIS 전자변 히터설치 ○154kV BUS-TIE 6100 GIS 전자변 히터설치","2015-11-03 13:00","2015-11-03 15:30","2015-11-03 13:00","2015-11-03 15:30","당일",null,null,null,201509040073,"-"]
[144,"대전충남","아산","인주S/S 154kV #1 BUS TIE CB","인주S/S 154kV 모선보호반 교체","○ 인주S/S 154kV 모선보호반 교체","2015-11-11 09:00","2015-11-11 18:00","2015-11-11 09:00","2015-11-11 18:00","당일",null,null,null,201509160117,"-"]
[145,"대전충남","청양","보령C/C 보령복합T/L GIS","보령C/C 154kV 보령LNG T/L 신규수용공사","- GIS(170kV 50KA 1250A * 1CCT) 설치 - 송전선로 보호배전반 설치(OCR Type) - 기타부대공사 * 1식 - 보령LNG T/L 무부하가압","2015-11-21 13:00","2015-11-23 13:00","2015-11-21 13:00","2015-11-23 13:00","연속",null,null,null,201509110350,"-"]
[146,"대전충남","청양","보령C/C 154kV #1 BUS","보령C/C 154kV 보령LNG T/L 신규수용공사","- GIS(170kV 50KA 1250A * 1CCT) 설치 - 송전선로 보호배전반 설치(OCR Type) - 기타부대공사 * 1식 - 보령LNG T/L 무부하가압","2015-11-21 13:00","2015-11-23 13:00","2015-11-21 13:00","2015-11-23 13:00","연속",null,null,null,201509110345,"-"]
[147,"대전충남","청양","대천서천화력#2 T/L","154kV 대천-서천화력T/L 정밀점검","0주작업 : 154kV 대천-서천화력#2T/L 정밀점검 -점검개소 : 서천S/T ~ No.1-46 0병행작업 : 대전충남본부 지장이설공사","2015-11-23 07:00","2015-11-26 18:00","2015-11-23 07:00","2015-11-26 18:00","매일",null,null,null,201509140181,"-"]
[148,"대전충남","청양","옥산서천화력#1 T/L","154kV 대천-서천화력T/L 정밀점검","안전이격","2015-11-17 07:00","2015-11-20 18:00","2015-11-17 07:00","2015-11-20 18:00","매일",null,null,null,201509140180,"-"]
[149,"대전충남","청양","대천서천화력#1 T/L","154kV 대천-서천화력T/L 정밀점검","0주작업 : 154kV 대천-서천화력#1T/L 정밀점검 -점검개소 : 서천S/T ~ No.1-46 0병행작업 : 대전충남본부 지장이설공사","2015-11-17 07:00","2015-11-20 18:00","2015-11-17 07:00","2015-11-20 18:00","매일",null,null,null,201509140179,"-"]
[150,"대전충남","청양","옥산서천화력#2 T/L","154kV 대천-서천화력T/L 정밀점검","안전이격","2015-11-23 07:00","2015-11-26 18:00","2015-11-23 07:00","2015-11-26 18:00","매일",null,null,null,201509140182,"-"]
[151,"대전충남","청양","신풍공주#1 T/L","154kV 신풍-공주#1T/L 보호배전반 교체공사","○ 154kV 신풍-공주#1T/L 보호배전반 교체","2015-11-17 09:00","2015-11-19 18:00","2015-11-17 09:00","2015-11-19 18:00","연속",null,null,null,201509110346,"-"]
[152,"전북","군산","군산S/S 60-61-0 SEC CB","154kV 군산S/S 60-61-0 SEC CB","군산P/O 노후배전반 대체공사(154kV #60-65BUS 모선보호반 교체) 1. 군산S/S 154kV #60-65BUS 모선보호반 대체","2015-11-02 09:00","2015-11-06 18:00","2015-11-02 09:00","2015-11-06 18:00","연속",null,null,null,201507060089,"-"]
[153,"전북","군산","군산S/S 154kV #1 BUS TIE CB","군산S/S 154kV #1 BUS TIE CB","군산P/O 노후배전반 대체공사(154kV #60-65BUS 모선보호반 교체) 1. 군산S/S 154kV #60-65BUS 모선보호반 대체","2015-11-02 09:00","2015-11-06 18:00","2015-11-02 09:00","2015-11-06 18:00","연속",null,null,null,201507060088,"-"]
[154,"전북","군산","군산S/S 65-66-0 SEC CB","154kV 군산S/S 65-66-0 SEC CB","군산P/O 노후배전반 대체공사(154kV #60-65BUS 모선보호반 교체) 1. 군산S/S 154kV #60-65BUS 모선보호반 대체","2015-11-02 09:00","2015-11-06 18:00","2015-11-02 09:00","2015-11-06 18:00","연속",null,null,null,201507060090,"-"]
[155,"전북","군산","군산동군산#2 T/L","154kV 군산-동군산#2 T/L","154kV 동군산-군산T/L 일부구간 지중화공사 신설 C/H 조립,가선 및 EBA 접속","2015-11-03 09:00","2015-11-29 18:00","2015-11-03 09:00","2015-11-29 18:00","연속",null,null,null,201509150094,"-"]
[156,"전북","군산","군산동군산#1 T/L","154kV 군산-동군산#1 T/L","154kV 동군산-군산T/L 일부구간 지중화공사 신설 C/H 전력선 가선 및 EBA 접속","2015-11-30 09:00","2015-12-07 18:00","2015-11-30 09:00","2015-12-07 18:00","연속",null,null,null,201509150095,"-"]
[157,"전북","군산","서군산소룡#1 T/L","154kV 서군산-소룡#1 T/L","154kV 서군산-소룡#1 T/L 공기압력계 교체공사 ○ 공기압력계 교체 1식","2015-11-02 09:00","2015-11-02 13:00","2015-11-02 09:00","2015-11-02 13:00","당일",null,null,null,201508180088,"-"]
[158,"전북","군산","서군산소룡#2 T/L","154kV 서군산-소룡#2T/L","154kV 서군산-소룡#2T/L 공기압력계 교체공사 ○ 공기압력계 교체 1식","2015-11-02 13:00","2015-11-02 18:00","2015-11-02 13:00","2015-11-02 18:00","당일",null,null,null,201508180089,"-"]
[159,"전북","김제","담양김제 T/L","154kV 담양-김제T/L","154kV 담양-김제T/L 50호 안전이격확보공사 담양-김제T/L 50호 교체","2015-11-09 07:00","2015-11-13 18:00","2015-11-09 07:00","2015-11-13 18:00","연속",null,null,null,201509040046,"-"]
[160,"전북","김제","섬진강H/P 154kV #1 BUS TIE CB","섬진강H/P 154kV #1 BUS TIE CB","섬진강수력 노후배전반 대체공사 섬진강HP 모선보호반 대체","2015-11-23 09:00","2015-11-27 18:00","2015-11-23 09:00","2015-11-27 18:00","연속",null,null,null,201508300003,"○"]
[161,"전북","김제","정공섬진강수력 T/L","154kV 정공-섬진강HP T/L","섬진강수력 노후배전반 대체공사 정공-섬진강HP T/L 노후배전반 대체","2015-11-16 09:00","2015-11-20 18:00","2015-11-16 09:00","2015-11-20 18:00","연속",null,null,null,201508300002,"○"]
[162,"전북","김제","김제섬진강HP T/L","154kV 김제-섬진강HP T/L","섬진강수력 노후배전반 대체공사 김제-섬진강HP T/L 노후배전반 대체","2015-11-08 09:00","2015-11-11 18:00","2015-11-08 09:00","2015-11-11 18:00","연속",null,null,null,201508300001,"-"]
[163,"전북","김제","김제섬진강HP T/L","154kV 김제-섬진강HP T/L","154kV #1,2 BUS 및 BUS-TIE CB 시험가압","2015-11-23 09:00","2015-11-25 18:00","2015-11-23 09:00","2015-11-25 18:00","연속",null,null,null,201509210217,"-"]
[164,"전북","김제","정공담양 T/L","154kV 정공-담양T/L","154kV 담양-김제T/L 135,136호 노후취약지지물 교체공사 담양-김제(정공-담양)T/L 135,136호 2기 지지물 교체","2015-11-05 07:00","2015-11-07 18:00","2015-11-05 07:00","2015-11-07 18:00","연속",null,null,null,201509040045,"○"]
[165,"전북","직할","무주용담수력 T/L","154kV 무주-용담수력T/L","154kV 무주-용담수력T/L 송전선로 정밀점검 송전선로 정밀점검 : 1호-83호","2015-11-23 09:00","2015-11-30 18:00","2015-11-23 09:00","2015-11-30 18:00","매일",null,null,null,201508130376,"-"]
[166,"전북","김제","신김제정공#2 T/L","345kV 신김제S/S ESS설치공사(GIS설치)","-170kV GIS * 1BAY 설치 - 기타 부대공사 * 1식","2015-11-27 08:00","2015-11-27 18:00","2015-11-27 08:00","2015-11-27 18:00","연속",null,null,null,201510010114,"-"]
[167,"전북","김제","신김제정공#1 T/L","345kV 신김제S/S ESS설치공사(GIS설치)","-170kV GIS * 1BAY 설치 -기타 부대공사 * 1식","2015-11-23 08:00","2015-11-23 18:00","2015-11-23 08:00","2015-11-23 18:00","매일",null,null,null,201510010113,"-"]
[168,"광주전남","강진","화원진도#2 T/L","154kV 화원진도#2 T/L(15년 강진 170kV개폐장치정밀점검)","2015년 강진 170kV개폐장치정밀점검 진도S/S 화원진도#2 T/L GIS 보통점검","2015-11-06 09:00","2015-11-06 18:00","2015-11-06 09:00","2015-11-06 18:00","당일",null,null,null,201509160228,"-"]
[169,"광주전남","강진","해남진도#2 T/L","해남S/S 170kV 장기사용 GIS 교체공사(해남-진도#2T/LGIS)","해남-화원T/L GIS 교체","2015-11-19 18:00","2015-12-10 18:00","2015-11-19 18:00","2015-12-10 18:00","연속",null,null,null,201509160144,"-"]
[170,"광주전남","강진","해남진도#2 T/L","해남S/S 170kV GIS교체공사(해남-진도#2T/L)","해남S/S 170kV GIS교체관련 안전이격거리확보","2015-11-10 09:00","2015-11-11 18:00","2015-11-10 09:00","2015-11-11 18:00","연속",null,null,null,201508130096,"-"]
[171,"광주전남","강진","해남진도#2 T/L","해남S/S 170kV GIS교체공사(해남-진도#2T/L 휴전)","해남S/S 170kV GIS교체관련 안전이격거리확보","2015-11-02 09:00","2015-11-03 18:00","2015-11-02 09:00","2015-11-03 18:00","연속",null,null,null,201508130087,"-"]
[172,"광주전남","광주","계림승주#2(서남권상수도T분기) T/L","154kV 계림-승주T/L 안전이격확보공사","철탑교체 8기 전력선 공중이동, 전력선 가선 작업","2015-11-07 07:00","2015-11-14 18:00","2015-11-07 07:00","2015-11-14 18:00","연속",null,null,null,201508170473,"-"]
[173,"광주전남","광주","담양일곡#1 T/L","담양-일곡#1T/L(변전 협력회사 총액)","담양S/S 154kV 담양-일곡#1, #2T/L 동시 트립시 BUS TIE CB 자동 투입회로 구성","2015-11-13 13:00","2015-11-13 15:00","2015-11-13 13:00","2015-11-13 15:00","당일",null,null,null,201509140324,"-"]
[174,"광주전남","광주","담양S/S 154kV #1 BUS","담양S/S 154kV #1 BUS(변전 협력회사 총액)","담양S/S 154kV 담양-일곡#1, #2T/L 동시 트립시 BUS TIE CB 자동 투입회로 구성","2015-11-13 13:00","2015-11-13 18:00","2015-11-13 13:00","2015-11-13 18:00","당일",null,null,null,201509140322,"-"]
[175,"광주전남","광주","담양일곡#2 T/L","담양-일곡#2 T/L(변전 협력회사 총액)","담양S/S 154kV 담양-일곡#1, #2T/L 동시 트립시 BUS TIE CB 자동 투입회로 구성","2015-11-13 16:00","2015-11-13 18:00","2015-11-13 16:00","2015-11-13 18:00","당일",null,null,null,201509140325,"-"]
[176,"광주전남","광주","북광주일곡#1 T/L","북광주-일곡#1 T/L(15년 변전총액공사)","북광주,일곡S/S 북광주-일곡#1 T/L 보호반 대체","2015-11-09 09:00","2015-11-11 18:00","2015-11-09 09:00","2015-11-11 18:00","연속",null,null,null,201509070020,"-"]
[177,"광주전남","광주","북광주일곡#2 T/L","북광주-일곡#2 T/L(15년 변전총액공사)","북광주,일곡S/S 북광주-일곡#2 T/L 보호반 대체","2015-11-23 09:00","2015-11-26 18:00","2015-11-23 09:00","2015-11-26 18:00","연속",null,null,null,201509070021,"-"]
[178,"광주전남","광주","신광주곡성#2 T/L","154KV 신광주-곡성T/L 안전이격확보공사","철탑교체 1기 전력선교체 0.12km","2015-11-20 07:00","2015-11-24 18:00","2015-11-20 07:00","2015-11-24 18:00","연속",null,null,null,201509070049,"-"]
[179,"광주전남","광주","신광주장성#2 T/L","154KV 신광주-장성T/L 댐퍼설치공사","댐퍼설치 450개","2015-11-29 07:00","2015-11-29 18:00","2015-11-29 07:00","2015-11-29 18:00","매일",null,null,null,201509070060,"-"]
[180,"광주전남","광주","신광주장성#1 T/L","154KV 신광주-장성T/L 댐퍼설치공사","댐퍼설치 450개","2015-11-25 07:00","2015-11-28 18:00","2015-11-25 07:00","2015-11-28 18:00","매일",null,null,null,201509070059,"-"]
[181,"광주전남","광주","신광주곡성#1 T/L","154KV 신광주-곡성T/L 안전이격확보공사","철탑교체 1기 전력선교체 0.12km","2015-11-15 07:00","2015-11-19 18:00","2015-11-15 07:00","2015-11-19 18:00","연속",null,null,null,201509070048,"-"]
[182,"광주전남","광주","신화순S/S 154kV #1 BUS TIE CB","신화순S/S 154kV #1 BUS TIE CB(15년 변전협력공사)","모선보호반 교체작업(60-65-0)","2015-11-02 09:00","2015-11-06 18:00","2015-11-02 09:00","2015-11-06 18:00","연속",null,null,null,201509220014,"-"]
[183,"광주전남","순천","광양순천#2 T/L","광양-순천#2T/L(SB댐퍼 설치공사)","2015년 송전정비 협력회사 총액공사 - SB댐퍼 설치 : 1~177호, 19기","2015-11-21 07:00","2015-11-22 18:00","2015-11-21 07:00","2015-11-22 18:00","연속",null,null,null,201509110398,"-"]
[184,"광주전남","순천","광양순천#1 T/L","광양-순천#1T/L(SB댐퍼 설치공사)","2015년 송전정비 협력회사 총액공사 - SB댐퍼 설치 : 1~177호, 19기","2015-11-19 07:00","2015-11-20 18:00","2015-11-19 07:00","2015-11-20 18:00","연속",null,null,null,201509110397,"-"]
[185,"광주전남","순천","서순천주암HP T/L","서순천-주암HP T/L(순천변전협력회사 총액공사)","15년 순천변전협력회사 총액공사 - 서순천S/S GIS 보통점검","2015-11-02 10:00","2015-11-02 18:00","2015-11-02 10:00","2015-11-02 18:00","당일",null,null,null,201509110313,"-"]
[186,"광주전남","순천","여수TP화치#2 T/L","여수TP-화치#2T/L(SB댐퍼 설치공사)","2015년 송전정비 협력회사 총액공사 - SB댐퍼 설치 : 2~17호, 7기","2015-11-6 07:00","2015-11-6 18:00","2015-11-6 07:00","2015-11-6 18:00","당일",null,null,null,201509110403,"-"]
[187,"광주전남","순천","여수TP화치#1 T/L","여수TP-화치#1T/L(SB댐퍼 설치공사)","2015년 송전정비 협력회사 총액공사 - SB댐퍼 설치 : 2~17호, 7기","2015-11-5 07:00","2015-11-5 18:00","2015-11-5 07:00","2015-11-5 18:00","당일",null,null,null,201509110402,"-"]
[188,"광주전남","순천","여수TP여천#1 T/L","여수TP-여천#1T/L(순천변전협력회사 총액공사)","15년 순천변전협력회사 총액공사 - 여천S/S 여수TP-여천#1T/L A,B,C상 LA 교체","2015-11-03 10:00","2015-11-03 18:00","2015-11-03 10:00","2015-11-03 18:00","당일",null,null,null,201509110314,"-"]
[189,"광주전남","순천","여천호남TP#2 T/L","여천-호남TP#2T/L(순천변전협력회사 총액공사)","15년 순천변전협력회사 총액공사 - 여천S/S 여천-호남TP#2T/L A,B,C상 LA 교체","2015-11-04 10:00","2015-11-04 18:00","2015-11-04 10:00","2015-11-04 18:00","당일",null,null,null,201509110315,"-"]
[190,"광주전남","순천","여수TP여천#1 T/L","여수TP-여천#1T/L(SB댐퍼 설치공사)","2015년 송전정비 협력회사 총액공사 - SB댐퍼 설치 : 1.1~15호, 4기","2015-11-13 07:00","2015-11-13 13:00","2015-11-13 07:00","2015-11-13 13:00","당일",null,null,null,201509110395,"-"]
[191,"광주전남","순천","여수TP여천#2 T/L","여수TP-여천#2T/L(SB댐퍼 설치공사)","2015년 송전정비 협력회사 총액공사 - SB댐퍼 설치 : 1.1~15호, 4기","2015-11-13 13:00","2015-11-13 18:00","2015-11-13 13:00","2015-11-13 18:00","당일",null,null,null,201509110396,"-"]
[192,"광주전남","순천","여천여수#1 T/L","여천여수#1 T/L(154kV 여천-여수T/L 송전용량증대 전선교체)","154kV 여천-여수T/L 송전용량증대 전선교체 공사","2015-11-23 07:00","2015-12-07 18:00","2015-11-23 07:00","2015-12-07 18:00","연속",null,null,null,201509160232,"-"]
[193,"광주전남","순천","여천호남TP#1 T/L","여천호남TP#1 T/L(154kV 여천-여수T/L 송전용량증대 전선교체)","154kV 여천-여수T/L 송전용량증대 전선교체 공사","2015-11-23 07:00","2015-11-30 18:00","2015-11-23 07:00","2015-11-30 18:00","연속",null,null,null,201509160233,"-"]
[194,"광주전남","순천","용성여수산단#1 T/L","용성-여수산단#1T/L(SB댐퍼 설치공사)","2015년 송전정비 협력회사 총액공사 - SB댐퍼 설치 : 4~13호, 9기","2015-11-29 07:00","2015-11-29 18:00","2015-11-29 07:00","2015-11-29 18:00","당일",null,null,null,201509110407,"-"]
[195,"광주전남","순천","용성여수산단#2 T/L","용성-여수산단#2T/L(SB댐퍼 설치공사)","2015년 송전정비 협력회사 총액공사 - SB댐퍼 설치 : 4~13호, 9기","2015-11-30 07:00","2015-11-30 18:00","2015-11-30 07:00","2015-11-30 18:00","당일",null,null,null,201509110408,"-"]
[196,"광주전남","순천","율촌화치#1 T/L","율촌-화치#1T/L(SB댐퍼 설치공사)","2015년 송전정비 협력회사 총액공사 - SB댐퍼 설치 : 13~61호, 13기","2015-11-23 07:00","2015-11-23 18:00","2015-11-23 07:00","2015-11-23 18:00","당일",null,null,null,201509110399,"-"]
[197,"광주전남","순천","율촌화치#2 T/L","율촌-화치#2T/L(SB댐퍼 설치공사)","2015년 송전정비 협력회사 총액공사 - SB댐퍼 설치 : 13~61호, 13기","2015-11-24 07:00","2015-11-24 18:00","2015-11-24 07:00","2015-11-24 18:00","당일",null,null,null,201509110400,"-"]
[198,"광주전남","직할","비아하남#1 T/L","하남S/S 비아-하남#1T/L","하남S/S 170kV 장기사용 GIS 대체공사 - 비아-하남#1T/L, BUS-TIE, #3M.Tr 철거 및 대체","2015-11-17 09:00","2015-12-04 18:00","2015-11-17 09:00","2015-12-04 18:00","연속",null,null,null,201507030003,"-"]
[199,"대구경북","경산","대구범물#1 T/L","직할가공송전정비협력회사총액공사","피뢰기 부동작 관련 아킹혼 정비","2015-11-05 08:00","2015-11-05 18:00","2015-11-05 08:00","2015-11-05 18:00","당일",null,null,null,201509100237,"-"]
[200,"대구경북","경산","신경산진량 T/L","2015-16년도 지중송전설비 위탁정비공사","자기제 피뢰기 3EA 교체 및 절연통보호장치 3EA 교체","2015-11-05 09:00","2015-11-05 18:00","2015-11-05 09:00","2015-11-05 18:00","당일",null,null,null,201509090059,"-"]
[201,"대구경북","달성","고령논공#1 T/L","고령 6F7 정밀점검","고령 6F7정밀","2015-11-19 09:30","2015-11-21 18:00","2015-11-19 09:30","2015-11-21 18:00","연속",null,null,null,201509100240,"-"]
[202,"대구경북","달성","고령다산#1 T/L","고령 6C7 정밀점검 테스트선로","고령 6C7 정밀테스트 선로","2015-11-24 13:00","2015-11-25 18:00","2015-11-24 13:00","2015-11-25 18:00","매일",null,null,null,201509100264,"-"]
[203,"대구경북","달성","고령쌍림#1 T/L","고령 6C7 , 쌍림 657정밀점검","고령 6C7, 쌍림 657정밀","2015-11-23 09:30","2015-11-25 18:00","2015-11-23 09:30","2015-11-25 18:00","연속",null,null,null,201509100242,"-"]
[204,"대구경북","달성","고령쌍림#2 T/L","고령 6B7 정밀점검","고령 6B7정밀","2015-11-12 09:30","2015-11-14 18:00","2015-11-12 09:30","2015-11-14 18:00","연속",null,null,null,201509100233,"-"]
[205,"대구경북","달성","고령다산#2 T/L","154kV 고령-다산#2T/L SB댐퍼 설치공사","- 고령-다산#2T/L SB댐퍼 설치공사(50기,고령-쌍림#2병가9기포함)","2015-11-05 08:00","2015-11-07 18:00","2015-11-05 08:00","2015-11-07 18:00","연속",null,null,null,201509080254,"-"]
[206,"대구경북","달성","고령쌍림#2 T/L","154kV 고령-쌍림#2T/L SB댐퍼 설치공사","- 고령-쌍림#2T/L SB댐퍼 설치공사(9기,고령-다산#2병가구간)","2015-11-05 08:00","2015-11-07 18:00","2015-11-05 08:00","2015-11-07 18:00","당일",null,null,null,201509080257,"-"]
[207,"대구경북","달성","고령쌍림#1 T/L","고령 6279 정밀점검 테스트선로","고령 6279정밀 테스트선로","2015-11-17 12:00","2015-11-18 18:00","2015-11-17 12:00","2015-11-18 18:00","매일",null,null,null,201509100247,"-"]
[208,"대구경북","달성","고령다산#1 T/L","154kV 고령-다산#1T/L SB댐퍼 설치공사","- 고령-다산#1T/L SB댐퍼 설치공사(50기,고령-쌍림#1병가9기포함)","2015-11-02 08:00","2015-11-04 18:00","2015-11-02 08:00","2015-11-04 18:00","연속",null,null,null,201509080252,"-"]
[209,"대구경북","달성","고령쌍림#1 T/L","154kV 고령-쌍림#1T/L SB댐퍼 설치공사","- 고령-쌍림#1T/L SB댐퍼 설치공사(9기,고령-다산#1병가구간)","2015-11-02 08:00","2015-11-04 18:00","2015-11-02 08:00","2015-11-04 18:00","당일",null,null,null,201509080256,"-"]
[210,"대구경북","달성","논공달성#2 T/L","논공S/S170kV GIS화 공사","O 154kV 송전선로 절체(옥외철구설비 GIS로 대체) - 인출변경(보강용 빔설치, 지중EBA 연결) - 송전선로 보호반 대체 및 시험 - 인출 단로기 철거(옥외철구) - 기타 부대작업 - 달성 송전 아킹혼 철거(21기)","2015-11-16 08:00","2015-11-17 18:00","2015-11-16 08:00","2015-11-17 18:00","연속",null,null,null,201509080032,"-"]
[211,"대구경북","달성","논공달성#1 T/L","논공S/S 인출 송전선로 지중케이블공사","인출 철구보강","2015-11-23 09:00","2015-11-23 18:00","2015-11-23 09:00","2015-11-23 18:00","당일",null,null,null,201509100502,"-"]
[212,"대구경북","달성","논공유가#1 T/L","논공S/S170kV GIS화 공사","O 154kV 송전선로 절체(옥외철구설비 GIS로 대체) - 인출변경(보강용 빔설치, 지중EBA 연결) - 송전선로 보호반 이설 및 시험 - 인출 단로기 철거(옥외철구) - 기타 부대작업","2015-11-16 08:00","2015-11-18 18:00","2015-11-16 08:00","2015-11-18 18:00","연속",null,null,null,201509080035,"-"]
[213,"대구경북","달성","다산강창#2 T/L","다산 6244 정밀점검 테스트선로","다산 6244정밀테스트서놀","2015-11-15 14:00","2015-11-15 15:00","2015-11-15 14:00","2015-11-15 15:00","당일",null,null,null,201509100278,"-"]
[214,"대구경북","달성","다산강창#1 T/L","다산 6344 정밀점검 테스트선로","다산 6344정밀테스트선로","2015-11-22 14:00","2015-11-22 15:00","2015-11-22 14:00","2015-11-22 15:00","당일",null,null,null,201509100280,"-"]
[215,"대구경북","달성","다산강창#1 T/L","다산 6244 정밀점검 테스트선로","다산 6244정밀테스트서놀","2015-11-08 14:00","2015-11-08 15:00","2015-11-08 14:00","2015-11-08 15:00","당일",null,null,null,201509100277,"-"]
[216,"대구경북","달성","성서달성#1 T/L","154kV 성서-달성#1T/L 아킹혼설치공사","- 성서-달성#1T/L 아킹혼설치공사(1기,강창-성서#2병가구간)","2015-11-21 08:00","2015-11-21 18:00","2015-11-21 08:00","2015-11-21 18:00","당일",null,null,null,201509080243,"-"]
[217,"대구경북","달성","강창성서#2 T/L","154kV 강창-성서#2T/L 아킹혼설치공사","- 강창-성서#2T/L 아킹혼설치공사(1기,성서-달성#1병가구간)","2015-11-21 08:00","2015-11-21 18:00","2015-11-21 08:00","2015-11-21 18:00","당일",null,null,null,201509080241,"-"]
[218,"대구경북","달성","쌍림합천#1 T/L","쌍림 657 정밀점검 테스트선로","고령 657 정밀테스트","2015-11-24 12:00","2015-11-25 18:00","2015-11-24 12:00","2015-11-25 18:00","매일",null,null,null,201509100263,"-"]
[219,"대구경북","영주","문경단양 T/L","15년 가공송전 위탁공사 154kV 단양T/L 정밀점검, 노후금구류 교체","15년 가공송전 위탁공사 154kV 단양T/L 정밀점검, 노후금구류 교체","2015-11-16 09:00","2015-11-19 18:00","2015-11-16 09:00","2015-11-19 18:00","연속",null,null,null,201509100563,"-"]
[220,"대구경북","영주","점촌문경 T/L","111-118호간 노후취약지지물 교체공사, 노후금구류 교체","111-118호간 노후취약지지물 교체공사, 노후금구류 교체, 15년 가공송전 위탁공사 154kV 단양T/L 정밀점검","2015-11-09 09:00","2015-11-14 18:00","2015-11-09 09:00","2015-11-14 18:00","연속",null,null,null,201509100560,"-"]
[221,"대구경북","영주","상주점촌#1 T/L","점촌S/S 상주-점촌#1T/L 장기사용 GIS 대체공사","점촌S/S 상주-점촌#1T/L 장기사용 GIS 대체공사","2015-11-05 08:00","2015-11-22 18:00","2015-11-05 08:00","2015-11-22 18:00","연속",null,null,null,201509100392,"-"]
[222,"대구경북","영주","점촌단양 T/L","111-118호간 노후취약지지물 교체공사, 노후금구류 교체","111-118호간 노후취약지지물 교체공사, 노후금구류 교체, 15년 가공송전 위탁공사 154kV 단양T/L 정밀점검","2015-11-01 09:00","2015-11-08 18:00","2015-11-01 09:00","2015-11-08 18:00","연속",null,null,null,201509100555,"-"]
[223,"대구경북","영주","점촌S/S 154kV #1 BUS TIE CB","점촌S/S 상주-점촌#2T/L, 6100CB 장기사용 GIS 대체공사","점촌S/S 상주-점촌#2T/L, 6100CB 장기사용 GIS 대체공사","2015-11-24 08:00","2015-12-10 18:00","2015-11-24 08:00","2015-12-10 18:00","연속",null,null,null,201509100415,"-"]
[224,"대구경북","영주","점촌문경 T/L","점촌S/S 상주-점촌#2T/L, 6100CB 장기사용 GIS 대체공사","점촌S/S 상주-점촌#2T/L, 6100CB 장기사용 GIS 대체공사","2015-11-18 08:40","2015-11-18 08:45","2015-11-18 08:40","2015-11-18 08:45","당일",null,null,null,201509100485,"-"]
[225,"대구경북","영주","상주점촌#2 T/L","점촌S/S 상주-점촌#2T/L 장기사용 GIS 대체공사","점촌S/S 상주-점촌#2T/L 장기사용 GIS 대체공사","2015-11-24 08:00","2015-12-10 18:00","2015-11-24 08:00","2015-12-10 18:00","연속",null,null,null,201509100411,"-"]
[226,"대구경북","영주","점촌단양 T/L","점촌S/S 상주-점촌#2T/L, 6100CB 장기사용 GIS 대체공사","점촌S/S 상주-점촌#2T/L, 6100CB 장기사용 GIS 대체공사","2015-11-18 08:45","2015-11-18 08:50","2015-11-18 08:45","2015-11-18 08:50","당일",null,null,null,201509100486,"-"]
[227,"대구경북","영주","점촌문경 T/L","점촌S/S 상주-점촌#2T/L, 6100CB 장기사용 GIS 대체공사","점촌S/S 상주-점촌#2T/L, 6100CB 장기사용 GIS 대체공사","2015-11-28 08:40","2015-11-28 08:45","2015-11-28 08:40","2015-11-28 08:45","당일",null,null,null,201509100542,"-"]
[228,"대구경북","영주","점촌단양 T/L","점촌S/S 상주-점촌#2T/L, 6100CB 장기사용 GIS 대체공사","점촌S/S 상주-점촌#2T/L, 6100CB 장기사용 GIS 대체공사","2015-11-28 08:45","2015-11-28 08:50","2015-11-28 08:45","2015-11-28 08:50","당일",null,null,null,201509100543,"-"]
[229,"대구경북","직할","내당두류#1 T/L","GIS(657) 보통점검","GIS(657) 보통점검 PNL 보통점검","2015-11-14 09:30","2015-11-14 18:00","2015-11-14 09:30","2015-11-14 18:00","당일",null,null,null,201509110111,"-"]
[230,"대구경북","직할","내당두류#2 T/L","GIS(667) 보통점검","GIS(667) 보통점검 PNL 보통점검","2015-11-15 09:30","2015-11-15 18:00","2015-11-15 09:30","2015-11-15 18:00","당일",null,null,null,201509110112,"-"]
[231,"대구경북","칠곡","서대구칠곡#2 T/L","서대구-칠곡#2T/L GIS 교체","서대구-칠곡#2T/L GIS 교체","2015-11-09 09:00","2015-11-22 18:00","2015-11-09 09:00","2015-11-22 18:00","연속",null,null,null,201509070125,"-"]
[232,"대구경북","포항","신포항영일#1 T/L","신포항S/S 신포항-영일#1T/L 휴전작업","CVT 교체작업","2015-11-11 09:00","2015-11-11 18:00","2015-11-11 09:00","2015-11-11 18:00","당일",null,null,null,201509090189,"-"]
[233,"대구경북","포항","신포항포항#1 T/L","345kV 신포항-신월성등 5개 T/L 피뢰기설치공사","피뢰기설치 : No.1~32호","2015-11-23 08:00","2015-11-30 18:00","2015-11-23 08:00","2015-11-30 18:00","연속",null,null,null,201509070007,"-"]
[234,"대구경북","포항","신포항영일#2 T/L","영일S/S 신포항-영일#2T/L 휴전작업","#2BUS 무부하가압용, CVT 대체","2015-11-07 20:00","2015-11-10 18:00","2015-11-07 20:00","2015-11-10 18:00","연속",null,null,null,201509080317,"-"]
[235,"대구경북","포항","신포항영일#2 T/L","영일S/S 신포항-영일#2T/L 휴전작업","모선보호반 대체 관련 준공시험","2015-11-20 09:30","2015-11-20 10:00","2015-11-20 09:30","2015-11-20 10:00","당일",null,null,null,201509180104,"-"]
[236,"대구경북","포항","신포항영일#1 T/L","영일S/S 신포항-영일#1T/L 휴전작업","모선보호반 대체 관련 준공시험","2015-11-20 10:00","2015-11-20 10:30","2015-11-20 10:00","2015-11-20 10:30","당일",null,null,null,201509180105,"-"]
[237,"대구경북","포항","신포항포항#1 T/L","포항S/S 신포항-포항#1T/L 휴전작업","모선보호반 대체관련 휴전","2015-11-18 14:30","2015-11-18 15:00","2015-11-18 14:30","2015-11-18 15:00","당일",null,null,null,201509100029,"-"]
[238,"대구경북","포항","신포항포항#2 T/L","포항S/S 신포항-포항#2T/L 휴전작업","모선보호반 대체관련 휴전","2015-11-18 11:00","2015-11-18 11:30","2015-11-18 11:00","2015-11-18 11:30","당일",null,null,null,201509100025,"-"]
[239,"대구경북","다산","다산강창#1 T/L","다산 6344 정밀점검 테스트선로","다산 6344정밀테스트선로","2015-11-29 14:00","2015-11-29 15:00","2015-11-29 14:00","2015-11-29 15:00","당일",null,null,null,201509100280,"-"]
[240,"부산울산","동부산","명례S/S 154KV #1 BUS TIE CB","명례S/S 170kV GIS 초기점검","명례S/S 170kV 6100 GIS 초기점검(사전조치필요로 거래소승인분)","2015-11-03 09:30","2015-11-03 17:00","2015-11-03 09:30","2015-11-03 17:00","당일",null,null,null,201509110333,"-"]
[241,"부산울산","북부산","구포모라#2 T/L","장기사용 배전반 대체공사","구포-모라#2T/L 보호배전반 대체","2015-11-30 09:00","2015-12-02 18:00","2015-11-30 09:00","2015-12-02 18:00","연속",null,null,null,201509100209,"-"]
[242,"부산울산","북부산","구포모라#1 T/L","장기사용 배전반 대체공사","구포-모라#1T/L 보호배전반 대체","2015-11-23 09:00","2015-11-25 18:00","2015-11-23 09:00","2015-11-25 18:00","연속",null,null,null,201509100208,"○"]
[243,"부산울산","북부산","매리김해#1 T/L","김해S/S 170kV 장기사용 GIS 대체공사","시험가압(#4M.Tr 1차 GIS #2BUS 고깔설치부)","2015-11-03 16:00","2015-11-03 18:00","2015-11-03 16:00","2015-11-03 18:00","당일",null,null,null,201509100146,"-"]
[244,"부산울산","북부산","김해S/S 154kV #1 BUS","김해S/S 170kV 장기사용 GIS 대체공사","#1BUS, 1DS, CB 철거, #1BUS 설치","2015-11-04 09:00","2015-11-17 18:00","2015-11-04 09:00","2015-11-17 18:00","연속",null,null,null,201509100124,"-"]
[245,"부산울산","북부산","매리김해#1 T/L","김해S/S 170kV 장기사용 GIS 대체공사","시험가압(#4M.Tr 1차 및 #1BUS)","2015-11-15 18:00","2015-11-17 18:00","2015-11-15 18:00","2015-11-17 18:00","연속",null,null,null,201509100148,"-"]
[246,"부산울산","북부산","김해S/S 154kV #2 BUS","김해S/S 170kV 장기사용 GIS 대체공사","#2BUS, 2DS 철거 및 설치","2015-11-18 09:00","2015-11-25 18:00","2015-11-18 09:00","2015-11-25 18:00","연속",null,null,null,201509100130,"-"]
[247,"부산울산","북부산","매리김해#1 T/L","김해S/S 170kV 장기사용 GIS 대체공사","시험가압(#4M.Tr 1차, #2BUS)","2015-11-23 18:00","2015-11-25 18:00","2015-11-23 18:00","2015-11-25 18:00","연속",null,null,null,201509100156,"-"]
[248,"부산울산","북부산","삼계김해 T/L","15년 가공송전 협력업체 공사","40-41호 이도불평형 정비","2015-11-28 08:00","2015-11-28 18:00","2015-11-28 08:00","2015-11-28 18:00","당일",null,null,null,201508280031,"-"]
[249,"부산울산","북부산","김해S/S 154kV #2 BUS","김해S/S 170kV 장기사용 GIS 대체공사","#2DS 철거(고깔설치), 상부BUS & BUSHING 철거","2015-11-01 09:00","2015-11-03 18:00","2015-11-01 09:00","2015-11-03 18:00","연속",null,null,null,201509100113,"-"]
[250,"부산울산","북부산","김해S/S 154kV #1 BUS TIE CB","김해S/S 170kV 장기사용 GIS 대체공사","BUS TIE 철거 및 #4M.Tr 1차 GIS 대체","2015-11-01 09:00","2015-11-25 18:00","2015-11-01 09:00","2015-11-25 18:00","연속",null,null,null,201509160007,"-"]
[251,"부산울산","북부산","물금삼랑진PP T/L","2015년도 가공송전설비 위탁공사","154kV 북부산-삼랑진PP#2T/L 아킹혼 철거 관련 안전 확보","2015-11-08 09:00","2015-11-08 18:00","2015-11-08 09:00","2015-11-08 18:00","당일",null,null,null,201509070248,"-"]
[252,"부산울산","북부산","북부산삼랑진PP#2 T/L","2015년도 가공송전설비 위탁공사","아킹혼 철거","2015-11-08 09:00","2015-11-08 18:00","2015-11-08 09:00","2015-11-08 18:00","당일",null,null,null,201509070247,"-"]
[253,"부산울산","북부산","서창산막#1 T/L","15년 가공송전 협력업체 공사","조류착지방지장치설치:1호-72호(40기)","2015-11-07 07:00","2015-11-08 18:00","2015-11-07 07:00","2015-11-08 18:00","연속",null,null,null,201508280025,"-"]
[254,"부산울산","북부산","서창산막#1 T/L","15년 가공송전 협력업체 공사","조류착지방지장치설치:1호-72호(40기)","2015-11-14 07:00","2015-11-15 18:00","2015-11-14 07:00","2015-11-15 18:00","연속",null,null,null,201508280026,"-"]
[255,"부산울산","북부산","서창산막#2 T/L","15년 가공송전 협력업체 공사","조류착지방지장치설치:1호-72호(40기)","2015-11-21 07:00","2015-11-22 18:00","2015-11-21 07:00","2015-11-22 18:00","연속",null,null,null,201508280027,"-"]
[256,"부산울산","북부산","서창산막#2 T/L","15년 가공송전 협력업체 공사","조류착지방지장치설치:1호-72호(40기)","2015-11-28 07:00","2015-11-29 18:00","2015-11-28 07:00","2015-11-29 18:00","연속",null,null,null,201508280028,"-"]
[257,"부산울산","북부산","엄궁학장#2 T/L","2015~2016년 지중송전 위탁정비공사","OF케이블 열화진단 관련 절연유 시료채취","2015-11-22 14:00","2015-11-22 18:00","2015-11-22 14:00","2015-11-22 18:00","당일",null,null,null,201509020073,"-"]
[258,"부산울산","북부산","엄궁학장#1 T/L","2015~2016년 지중송전 위탁정비공사","OF케이블 열화진단 관련 절연유 시료채취","2015-11-22 09:00","2015-11-22 13:00","2015-11-22 09:00","2015-11-22 13:00","당일",null,null,null,201509020072,"-"]
[259,"부산울산","북부산","학장개금#1 T/L","2015~2016년 지중송전 위탁정비공사","OF케이블 열화진단 관련 절연유 시료채취","2015-11-18 09:00","2015-11-18 13:00","2015-11-18 09:00","2015-11-18 13:00","당일",null,null,null,201509170092,"-"]
[260,"부산울산","북부산","학장개금#2 T/L","2015~2016년 지중송전 위탁정비공사","OF케이블 열화진단 관련 절연유 시료채취","2015-11-18 14:00","2015-11-18 18:00","2015-11-18 14:00","2015-11-18 18:00","당일",null,null,null,201509020074,"-"]
[261,"부산울산","울산","신온산온산#1 T/L","신온산S/S #4M.Tr 증설공사","- 345kV 주변압기 * 1Bank - 362kV GIS 2CB, 170kV GIS 2CCT","2015-11-14 18:00","2015-11-16 18:00","2015-11-14 18:00","2015-11-16 18:00","연속",null,null,null,201509140060,"-"]
[262,"부산울산","울산","신온산온산#1 T/L","신온산S/S #4M.Tr 증설공사","- 345kV 주변압기 * 1Bank - 362kV GIS 2CB, 170kV GIS 2CCT","2015-11-09 18:00","2015-11-11 18:00","2015-11-09 18:00","2015-11-11 18:00","연속",null,null,null,201509140059,"-"]
[263,"부산울산","울산","신울산영남TP#1 T/L","2014-15년 울산전력지사 변전협력 총액공사","변전소 양단 보호배전반 교체","2015-11-07 09:00","2015-11-08 18:00","2015-11-07 09:00","2015-11-08 18:00","연속",null,null,null,201509100644,"-"]
[264,"부산울산","울산","신울산울산#1 T/L","2014-15년 울산전력지사 변전협력 총액공사","변전소 양단 보호배전반 교체","2015-11-09 09:00","2015-11-10 18:00","2015-11-09 09:00","2015-11-10 18:00","연속",null,null,null,201509100645,"○"]
[265,"부산울산","울산","신울산영남TP#2 T/L","영남화력 GIS 철거 공사","6183,6283,6383 #2DS 철거부 시험가압(24H)","2015-11-28 18:00","2015-11-29 18:00","2015-11-28 18:00","2015-11-29 18:00","연속",null,null,null,201509100646,"-"]
[266,"부산울산","울산","울산T/P 154kV #2 BUS TIE CB","울산화력S/Y 154kV 보호제어설비 전담운영공사","61-66 모선보호반 대체, 제어케이블 수용","2015-11-04 13:00","2015-11-06 18:00","2015-11-04 13:00","2015-11-06 18:00","연속",null,null,null,201509100643,"-"]
[267,"부산울산","울산","울산T/P 154kV #1 BUS TIE CB","울산화력S/Y 154kV 보호제어설비 전담운영공사","60-65 모선보호반 대체, 제어케이블 수용","2015-11-02 08:00","2015-11-04 13:00","2015-11-02 08:00","2015-11-04 13:00","연속",null,null,null,201509100638,"○"]
[268,"부산울산","직할","정보대연 T/L","2014-2015년 송전정비 협력회사 총액공사","아킹혼링 철거","2015-11-09 08:00","2015-11-09 18:00","2015-11-09 08:00","2015-11-09 18:00","당일",null,null,null,201509070203,"-"]
[269,"부산울산","직할","개금범천#1 T/L","범천S/S 개금-범천 #1T/L(617) GIS 보통점검","범천S/S 개금-범천 #1T/L(617) GIS 보통점검","2015-11-23 10:00","2015-11-23 18:00","2015-11-23 10:00","2015-11-23 18:00","당일",null,null,null,201509090241,"-"]
[270,"부산울산","직할","개금범천#2 T/L","범천S/S 개금-범천 #2T/L(627) GIS 보통점검","범천S/S 개금-범천 #2T/L(627) GIS 보통점검","2015-11-24 10:00","2015-11-24 18:00","2015-11-24 10:00","2015-11-24 18:00","당일",null,null,null,201509090242,"-"]
[271,"경남","진주","의령동진주#1 T/L","154kV 의령-동진주#1T/L CB 617 초기점검","154kV 의령-동진주#1T/L CB 617 초기점검","2015-11-13 09:30","2015-11-15 18:30","2015-11-13 09:30","2015-11-15 18:30","연속",null,null,null,201507080213,"-"]
[272,"경남","진주","동진주진주#2 T/L","진주S/S 동진주-진주#2T/L GCB 대체","진주S/S GCB 대체 동진주S/S 동진주-진주#2T/L CB 637 초기점검","2015-11-06 09:30","2015-11-08 18:30","2015-11-06 09:30","2015-11-08 18:30","연속",null,null,null,201507080217,"-"]
[273,"경남","진주","동진주진주#1 T/L","154kV 동진주-진주#1T/L CB 647 초기점검","154kV 동진주-진주#1T/L CB 647 초기점검","2015-11-01 09:30","2015-11-01 18:30","2015-11-01 09:30","2015-11-01 18:30","당일",null,null,null,201507080218,"-"]
[274,"경남","진주","의령산청 T/L","의령-산청T/L GIS 정밀점검 및 시험가압","의령-산청T/L GIS 정밀점검 및 시험가압","2015-11-21 09:00","2015-11-22 18:30","2015-11-21 09:00","2015-11-22 18:30","연속",null,null,null,201509080153,"-"]
[275,"경남","진주","하동하동화력#1 T/L","광양-하동#2T/L GIS 정밀점검 시험가압","광양-하동#2T/L GIS 정밀점검 시험가압","2015-11-19 09:40","2015-11-19 10:00","2015-11-19 09:40","2015-11-19 10:00","당일",null,null,null,201509080176,"-"]
[276,"경남","진주","하동하동화력#1 T/L","광양-하동#1T/L GIS 정밀점검 시험가압","광양-하동#1T/L GIS 정밀점검 시험가압","2015-11-18 18:00","2015-11-18 18:20","2015-11-18 18:00","2015-11-18 18:20","당일",null,null,null,201509080171,"-"]
[277,"경남","진주","하동하동화력#1 T/L","광양-하동#1T/L GIS 정밀점검 시험가압","광양-하동#1T/L GIS 정밀점검 시험가압","2015-11-17 09:30","2015-11-17 09:50","2015-11-17 09:30","2015-11-17 09:50","당일",null,null,null,201509080169,"-"]
[278,"경남","진주","하동하동화력#1 T/L","광양-하동#2T/L GIS 정밀점검 시험가압","광양-하동#2T/L GIS 정밀점검 시험가압","2015-11-20 18:00","2015-11-20 18:20","2015-11-20 18:00","2015-11-20 18:20","당일",null,null,null,201509080178,"-"]
[279,"경남","진주","광양하동#1 T/L","154kV 광양-하동#1,2T/L 노후전력선 교체공사","1. 전력선교체구간 : 하동S/T∼37호 10.58km (31∼35호 구간 지장이설 시 교체) ※ ACSR 330㎟×S×2C (교체전, 30년 이상 사용) → HSTACIR/AW 330㎟×S×2C (교체후) 2. 철탑설치 및 철거 : 1기(22호) 3. 철탑계탑 : 2기(27호, 30호)","2015-11-16 09:00","2015-11-30 18:00","2015-11-16 09:00","2015-11-30 18:00","연속",null,null,null,201509030107,"-"]
[280,"경남","진주","광양하동#2 T/L","154kV 광양-하동#1,2T/L 노후전력선 교체공사","1. 전력선교체구간 : 하동S/T∼37호 10.58km (31∼35호 구간 지장이설 시 교체) ※ ACSR 330㎟×S×2C (교체전, 30년 이상 사용) → HSTACIR/AW 330㎟×S×2C (교체후) 2. 철탑설치 및 철거 : 1기(22호) 3. 철탑계탑 : 2기(27호, 30호)","2015-11-16 09:00","2015-11-30 18:00","2015-11-16 09:00","2015-11-30 18:00","연속",null,null,null,201509030108,"-"]
[281,"경남","통영","신고성고성 T/L","고성S/S 154kV 신고성-고성T/L CPD 대체공사","고성S/S 154kV 신고성-고성T/L CPD 대체공사","2015-11-21 09:30","2015-11-21 18:30","2015-11-21 09:30","2015-11-21 18:30","당일",null,null,null,201509100144,"-"]
[282,"경남","통영","삼천포사천#1 T/L","삼천포S/S 154kV 삼천포-사천#1T/L PT 대체공사","삼천포S/S 154kV 삼천포-사천#1T/L PT 대체공사","2015-11-05 09:30","2015-11-05 18:30","2015-11-05 09:30","2015-11-05 18:30","당일",null,null,null,201509100132,"-"]
[283,"경남","통영","삼천포사천#2 T/L","삼천포S/S 154kV 삼천포-사천#2T/L GIS 보통점검","삼천포S/S 154kV 삼천포-사천#2T/L GIS 보통점검","2015-11-06 09:30","2015-11-06 18:30","2015-11-06 09:30","2015-11-06 18:30","당일",null,null,null,201509100134,"-"]
[284,"경남","함안","신마산마산#1 T/L","154kV 신마산마산#1 T/L SB댐퍼 설치작업","154kV 신마산마산#1 T/L SB댐퍼 설치작업","2015-11-14 08:30","2015-11-15 18:00","2015-11-14 08:30","2015-11-15 18:00","연속",null,null,null,201509090052,"-"]
[285,"경남","함안","신마산차룡#1 T/L","신마산,차룡S/S 154kV 신마산-차룡#1T/L 보호배전반 교체공사","신마산,차룡S/S 154kV 신마산-차룡#1T/L 보호배전반 교체공사","2015-11-07 09:30","2015-11-08 17:30","2015-11-07 09:30","2015-11-08 17:30","연속",null,null,null,201507300047,"-"]
[286,"경남","함안","신마산S/S 154kV #60 BUS","신마산S/S 154kV #60BUS CPD 교체공사","신마산S/S 154kV #60BUS CPD 교체공사","2015-11-06 09:30","2015-11-06 17:30","2015-11-06 09:30","2015-11-06 17:30","당일",null,null,null,201509070195,"-"]
[287,"경남","함안","신마산마산#2 T/L","154kV 신마산마산#2 T/L SB댐퍼 설치작업","154kV 신마산마산#2 T/L SB댐퍼 설치작업","2015-11-28 08:30","2015-11-29 18:00","2015-11-28 08:30","2015-11-29 18:00","연속",null,null,null,201509090055,"-"]
[288,"경남","함안","신마산차룡#2 T/L","신마산,차룡S/S 154kV 신마산-차룡#2T/L 보호배전반 교체공사","신마산,차룡S/S 154kV 신마산-차룡#2T/L 보호배전반 교체공사","2015-11-21 09:30","2015-11-22 17:30","2015-11-21 09:30","2015-11-22 17:30","연속",null,null,null,201507300048,"-"]
[289,"경남","함안","진영한림정#2 T/L","진영 변전소 외벽 교체공사(안전이격확보)","진영 변전소 외벽 교체공사(안전이격확보)","2015-11-21 09:00","2015-11-21 18:00","2015-11-21 09:00","2015-11-21 18:00","당일",null,null,null,201509080249,"-"]
[290,"경남","함안","신김해진영#1 T/L","진영 변전소 외벽 교체공사(안전이격확보)","진영 변전소 외벽 교체공사(안전이격확보)","2015-11-15 09:00","2015-11-15 18:00","2015-11-15 09:00","2015-11-15 18:00","당일",null,null,null,201509080244,"-"]
[291,"경남","함안","신김해진영#2 T/L","진영 변전소 외벽 교체공사(안전이격확보)","진영 변전소 외벽 교체공사(안전이격확보)","2015-11-14 09:00","2015-11-14 18:00","2015-11-14 09:00","2015-11-14 18:00","당일",null,null,null,201509080247,"-"]
[292,"경남","함안","신김해진영#1 T/L","진영 변전소 외벽 교체공사(안전이격확보)","진영 변전소 외벽 교체공사(안전이격확보)","2015-11-06 09:00","2015-11-08 18:00","2015-11-06 09:00","2015-11-08 18:00","연속",null,null,null,201509080242,"-"]
[293,"경남","함안","신김해진영#2 T/L","진영 변전소 외벽 교체공사(안전이격확보)","진영 변전소 외벽 교체공사(안전이격확보)","2015-11-06 09:00","2015-11-08 18:00","2015-11-06 09:00","2015-11-08 18:00","연속",null,null,null,201509080246,"-"]
[294,"경남","함안","진영한림정#1 T/L","진영 변전소 외벽 교체공사(안전이격확보)","진영 변전소 외벽 교체공사(안전이격확보)","2015-11-22 09:00","2015-11-22 18:00","2015-11-22 09:00","2015-11-22 18:00","당일",null,null,null,201509080251,"-"]
[295,"경남","함안","진영초동#1 T/L","154kV 진영-초동T/L 안전이격확보공사","50-55호 철탑(6기) 철거 및 설치 50-55호 전선 철거 및 설치","2015-11-19 07:00","2015-11-28 18:30","2015-11-19 07:00","2015-11-28 18:30","연속",null,null,null,201509090177,"-"]
[296,"경남","함안","진영초동#2 T/L","154kV 진영-초동T/L 안전이격확보공사","50-55호 철탑(6기) 철거 및 설치 50-55호 전선 철거 및 설치","2015-11-19 07:00","2015-11-28 18:30","2015-11-19 07:00","2015-11-28 18:30","연속",null,null,null,201509090178,"-"]
[297,"경남","함안","한림정삼계#2 T/L","한림정삼계#2 T/L 불량애자교체","한림정삼계#2 T/L 불량애자교체","2015-11-22 08:30","2015-11-22 18:30","2015-11-22 08:30","2015-11-22 18:30","당일",null,null,null,201509090048,"-"]
[298,"경남","함안","한림정삼계#1 T/L","한림정삼계#1 T/L 애자련보강 및 불량애자교체","한림정삼계#1 T/L 애자련보강 및 불량애자교체","2015-11-21 08:30","2015-11-21 18:30","2015-11-21 08:30","2015-11-21 18:30","당일",null,null,null,201509090047,"-"]

{"sheet":"한수원","index":3,"n_rows":9,"n_cols":20,"rows_kept":9,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,16,3,16],[2,17,3,17],[2,18,3,18],[2,19,3,19],[2,14,3,14],[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2015년 11월 월간휴전계획표(한수원)"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업\n구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소간","사업소내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"월성본부","1발전소","#2 기동용변압기","월성 2호기 제15차 계획예방정비관련 소내전원절체시험\n*조작차단기 : CB7400, CB7472","- SST->UST 소내전원절체시험","2015-11-01 09:00","2015-11-02 18:00","2015-11-01 09:00","2015-11-02 18:00","수시\n조작","N"]
[2,"월성본부","1발전소","#2 주변압기","월성 2호기 제15차 계획예방정비관련 소내전원절체시험\n*조작차단기 : CB7300, CB7372","- UST->SST 소내전원절체시험","2015-11-01 09:00","2015-11-02 18:00","2015-11-01 09:00","2015-11-02 18:00","수시\n조작","N",null,null," "]
[3,"월성본부","1발전소","#2 주변압기","월성 2호기 제15차 계획예방정비관련 소내전원절체시험\n*조작차단기 : CB7300, CB7372","- 계통병입전 IPB링크 조립 및 예비계통병입","2015-11-02 18:00","2015-11-05 21:00","2015-11-02 18:00","2015-11-05 21:00","수시\n조작","N"]
[4,"한울본부","한울3발","#6 주변압기","6호기 8차 계획예방정비 \n* 조작차단기 : PCB 7C00, 7C72","○ 스위치야드 'C Bay' 교체공사\n○ 갑종보호반(GEN/MTR/UAT) 디지털 삼중화\n○ 주변압기 C상 교체 및 소내보조변압기 정밀점검","2015-10-11T13:00:00","2015-11-18T18:00:00","2015-10-11T13:00:00","2015-11-18T18:00:00","연속","Y"]
[5,"한울본부","한울3발","#6 주변압기","6호기 8차 계획예방정비 \n* 조작차단기 : PCB 7C00, 7C72","○ 소내전원 절체시험(UAT->SAT)","2015-11-20T18:00:00","2015-11-20T23:00:00","2015-11-20T18:00:00","2015-11-20T23:00:00","연속","Y"]