{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["765송부","345송부","154송부","한수원"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":5,"n_cols":16,"rows_kept":5,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'[1]765송부'!A1","v":"2016년도 1월 휴전계획서"}]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[null,"해당사항 없음"]

{"sheet":"345송부","index":1,"n_rows":11,"n_cols":16,"rows_kept":11,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"'[1]765송부'!A1","v":"2016년도 1월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","직할","신의정부S/S #2 M.Tr A","345kV 신의정부변전소 소음저감대책 시행공사","변압기 방음벽 설치(하자보수)","2016-01-12 07:30","2016-01-12 11:00","2016-01-12 07:30","2016-01-12 11:00","당일",null,null,null,201511190060]
[2,"경기북부","직할","양주S/S #3 M.Tr A","345kV 양주S/S #3M.Tr 설치공사","345kV 양주S/S #3M.Tr 설치 및 예비변압기 분리공사","2016-01-18 09:00","2016-01-21 18:00","2016-01-18 09:00","2016-01-21 18:00","연속",null,null,null,201511160158]
[3,"강원","동해","동해S/S #3 M.Tr A","동해S/S 취약설비 GIS화 공사","- #3M.Tr 2차측 이설 - 2차측 상모선 철거 및 인출분기모선 설치 - 감시반 이설(신규설비)","2016-01-19 08:00","2016-01-22 18:00","2016-01-19 08:00","2016-01-22 18:00","연속",null,null,null,201511130012]
[4,"전북","김제","신김제한빛NP#2 T/L","신김제한빛NP#2 T/L","보호배전반 교체","2016-01-11 09:00","2016-01-20 18:00","2016-01-01 09:00","2016-01-10 18:00","연속",null,null,null,201511200037]
[5,"부산울산","동부산","신고리고리NP#2 T/L","345kV 고리N/P 통합S/Y 토건공사","원자력기술위원회의 사면 추가보강 요청으로 인한 활선근접작업","2016-01-04 09:00","2016-01-15 18:00","2016-01-04 09:00","2016-01-15 18:00","연속",null,null,null,201511130042]
[6,"부산울산","동부산","신고리고리NP#1 T/L","345kV 고리N/P 통합S/Y 토건공사","원자력기술위원회의 사면 추가보강 요청으로 인한 활선근접작업","2016-01-18 09:00","2016-01-29 18:00","2016-01-18 09:00","2016-01-29 18:00","연속",null,null,null,201511130040]
[7,"인천","신김포","신김포서인천CCT/L","중간접속함 교체","중간접속함 교체","2016-01-31 09:00","2016-03-04 18:00","2016-01-31 09:00","2016-03-04 18:00","연속"]

{"sheet":"154송부","index":2,"n_rows":24,"n_cols":16,"rows_kept":24,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"'[1]765송부'!A1","v":"2016년도 1월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","직할","마포신촌 T/L","신촌S/S 154kV 장기사용 GIS 대체","마포신촌T/L GIS 대체","2016-01-11 08:00","2016-02-05 18:00","2016-01-11 08:00","2016-02-05 18:00","연속",null,null,null,201510140187]
[2,"서울","직할","방산중앙#1 T/L","중앙S/S 170kV GIS 대체공사","중앙S/S 170kV GIS 대체공사(#2M.Tr 1차, 방산중앙#1T/L)","2016-01-04 09:30","2016-01-24 18:00","2016-01-04 09:30","2016-01-24 18:00","당일",null,null,null,201510130082]
[3,"남서울","직할","교대이수#2 T/L","154kV 교대-이수T/L 지중선로 이설공사(방배로 1구간)","배경: 서초구청 시행 하수암거 설치에 따른 지중선로 이설 개요: 154KV 교대-이수T/L J/B#7~8, #9~10 (2구간, 0.66KM) XLPE1200 * 2회선","2016-02-01 09:00","2016-03-07 18:00","2016-02-01 09:00","2016-03-07 18:00","당일",null,null,null,201510130087]
[4,"인천","김포","양촌양곡#1 T/L","154kV 양촌-양곡T/L No.13 지장철탑 이설공사","□ 제 2외곽순환도로 조성에 따른 지장철탑 이설 □ 공사개요 : 154kV 양촌-양곡T/L No.13 이설 - No.13 본철탑 이설","2016-01-21 07:00","2016-01-23 18:00","취소","취소","당일",null,null,null,201510160113]
[5,"인천","김포","양촌양곡#2 T/L","154kV 양촌-양곡T/L No.13 지장철탑 이설공사","□ 제 2외곽순환도로 조성에 따른 지장철탑 이설 □ 공사개요 : 154kV 양촌-양곡T/L No.13 이설 - No.13 본철탑 이설","2016-01-18 07:00","2016-01-20 18:00","취소","취소","당일",null,null,null,201510150064]
[6,"경기북부","구리","의정부금오#2 T/L","154kV 용현S/S 건설공사","전철T/L 공급관련 모선직결작업","2016-01-11 07:30","2016-01-15 18:00","2016-01-11 07:30","2016-01-15 18:00","연속",null,null,null,201510140141]
[7,"경기북부","구리","의정부금오#1 T/L","154kV 용현S/S 건설공사","전철T/L 공급관련 모선직결작업","2016-01-04 07:30","2016-01-08 18:00","2016-01-04 07:30","2016-01-08 18:00","연속",null,null,null,201510140140]
[8,"강원","동해","동해이원#2 T/L","동해S/S 취약설비 GIS화 공사","- 154kV 동해-이원#2T/L 이설 - 상모선 철거 및 안출분기모선 설치 - 감시반 이설(신규설비)","2016-01-23 08:00","2016-01-25 18:00","2016-01-21 08:00","2016-01-23 18:00","연속",null,null,null,201508130084]
[9,"강원","동해","동해이원#1 T/L","동해S/S 취약설비 GIS화 공사","- 154kV 동해-이원#1T/L 이설 - 상모선 철거 및 안출분기모선 설치 - 감시반 이설(신규설비)","2016-01-16 08:00","2016-01-18 18:00","2016-01-28 08:00","2016-01-30 18:00","연속",null,null,null,201508130186]
[10,"강원","동해","동해동영월 T/L","동해S/S 취약설비 GIS화 공사","- 154kV 동해-동영월T/L 이설 - 상모선 철거 및 안출분기모선 설치 - 감시반 이설(신규설비)","2016-01-26 08:00","2016-01-28 18:00","2016-01-31 08:00","2016-02-02 18:00","연속",null,null,null,201508130093]
[11,"강원","동해","동해정선 T/L","동해S/S 취약설비 GIS화 공사","- 154kV 동해-정선T/L 이설 - 상모선 철거 및 안출분기모선 설치 - 감시반 이설(신규설비)","2016-01-29 08:00","2016-01-31 18:00","취소","취소","연속",null,null,null,201508130184]
[12,"강원","동해","동해북평#2 T/L","154kV 동북, 영동화력T/L 지중화공사","154kV 동해-북평#1,2T/L 지중화 - 154kV XLPE 1200SQ 3.5km","2016-01-21 09:00","2016-02-18 18:00","2016-01-28 09:00","2016-02-25 18:00","당일",null,null,null,201510150065]
[13,"강원","태백","도계태백 T/L","태백변전소 배전반 이설공사","도계-태백T/L 보호반 이설","2016-01-11 09:00","2016-01-14 18:00","2016-01-11 09:00","2016-01-14 18:00","연속",null,null,null,201510140038]
[14,"강원","태백","이원태백 T/L","태백변전소 배전반 이설공사","이원-태백T/L 보호반 이설","2016-01-04 09:00","2016-01-07 18:00","2016-01-04 09:00","2016-01-07 18:00","연속",null,null,null,201509080125]
[15,"대구경북","구미","선산금전#2 T/L","154kV 선산-산동T/L 건설공사","선금 23호 철탑부재보강 및 선산-금전#2T/L용 4각암설치(4조)","2016-01-09 08:00","2016-01-11 18:00","2016-01-09 08:00","2016-01-11 18:00","연속",null,null,null,201508190122]
[16,"대구경북","구미","선산산동#2 T/L","154kV 선산-산동T/L 건설공사","선산-금전 23호 철탑부재보강 및 상단 4각암설치 4개소(선산-금전#2) No.11~15구간 전력선 설치(상단 선산-금전#2T/L 제이스CC횡단구간) No.11~15구간 전력선 설치(하단 선산-산동#2T/L 제이스CC횡단구간) 기설 No.22~23구간 전력선 공중이동","2016-01-09 08:00","2016-01-21 18:00","2016-01-09 08:00","2016-01-21 18:00","연속",null,null,null,201508190133]
[17,"대구경북","구미","선산금전#1 T/L","154kV 선산-산동T/L 건설공사","No.11~15구간 전력선 설치(상단 선산-금전#1,2T/L 제이스CC횡단) No.11~15구간 전력선 설치(하단 선산-산동#1,2T/L 제이스CC횡단) 기설 No.22~23구간 전력선 공중이동(4각암 설치위치) 기설 No.23 보조암철거 4조(기설 선산-금전#2)","2016-01-12 08:00","2016-01-31 18:00","2016-01-12 08:00","2016-01-31 18:00","연속",null,null,null,201508190128]
[18,"대구경북","구미","선산산동#1 T/L","154kV 선산-산동T/L 건설공사","No.11~15구간 전력선 설치(상단 선산-금전#1T/L 제이스CC횡단구간) No.11~15구간 전력선 설치(하단 선산-산동#1T/L 제이스CC횡단구간)","2016-01-22 08:00","2016-01-31 18:00","2016-01-22 08:00","2016-01-31 18:00","당일",null,null,null,201510200045]
[19,"경남","직할","주촌삼계#2 T/L","주촌S/S 154kV 주촌-삼계#2T/L CB 하자점검","주촌S/S 154kV 주촌-삼계#2T/L CB 하자점검","2016-01-24 09:30","2016-01-24 17:30","2016-01-24 09:30","2016-01-24 17:30","당일",null,null,null,201510200029]
[20,"경남","직할","주촌삼계#1 T/L","주촌S/S 154kV 주촌-삼계#1T/L CB 하자점검","주촌S/S 154kV 주촌-삼계#1T/L CB 하자점검","2016-01-17 09:30","2016-01-17 17:30","2016-01-17 09:30","2016-01-17 17:30","당일",null,null,null,201510200030]

{"sheet":"한수원","index":3,"n_rows":11,"n_cols":20,"rows_kept":11,"cut":false,"hidden":false,"merged":[[4,14,5,14],[0,0,0,6],[4,0,5,0],[4,1,5,1],[4,2,5,2],[4,3,5,3],[4,4,5,4],[4,5,5,5],[4,6,4,7],[4,8,4,9],[4,10,5,10],[4,11,5,11],[4,12,5,12],[4,13,5,13],[4,15,5,15],[4,16,5,16],[4,17,5,17],[4,18,5,18],[4,19,5,19]]}
["2015년도 12월 및 2016년 01월 휴전계획표(한국수력원자력)"]
[]
[]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"월성본부","2발전소","#3 주변압기","월성3호기 14차 계획예방정비 관련 주/소내용 변압기 해압\n* 조작차단기 : CB7500,7572"," - 짝수모선 정전작업 및 등급4전원 모선절체시험을 위한 주/소내용변압기 해압 및 가압","2016-01-14 09:00","2016-01-23 23:00","2016-01-14 09:00","2016-01-23 23:00","연속",null,null,null," "]
[2,"월성본부","2발전소","#3 기동용변압기","월성3호기 14차 계획예방정비 관련 기동용변압기 해압 및 가압\n* 조작차단기 : CB7500, 7572, 7600, 7672"," - 등급4전원 모선절체시험을 위한 기동용변압기 해압 및 가압","2016-01-15 08:00","2016-01-16 12:00","2016-01-15 08:00","2016-01-16 12:00","연속",null,null,null," "]
[7,"한빛본부","한빛3발","#6 주변압기","한빛6호기 소내전원절체시험 수행\n*조작차단기 : 7E00 7E71","○ 한빛6호기 소내전원절체시험 수행","2016-01-10T09:00:00","2016-01-10T18:00:00","2016-01-10T09:00:00","2016-01-10T18:00:00","연속","N"]
[8,"한빛본부","한빛3발","모선#1","모선#1 보호반 설치\n*조작차단기 : 7E71  7D71 7C71 7B71","○ 모선#1 보호반 대체","2016-01-11T09:00:00","2016-01-15T18:00:00","2016-01-11T09:00:00","2016-01-15T18:00:00","연속","N"]
[9,"고리본부","신고리2발","#4 주변압기","4호기 비상분리모선(NSPB) 덕트 하부커버 교체작업","4호기 비상분리모선(NSPB) 덕트 하부커버 도장 박리 현상에 따른 교체작업","2016-01-18 09:00","2016-01-29 17:00","2016-01-18 09:00","2016-01-29 17:00","연속","N"]