{"text_format":"2","workbook":"xlsx","n_sheets":5,"sheets":["765송부","345송부","154송부","한수원","중부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":10,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":9,"n_cols":16,"rows_kept":9,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2016년도 2월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"강원","태백","신태백S/S 765kV #1 BUS","신태백S/S 800kV GIS 설치공사","800kV GIS(8000A/50kA) 3CB 설치","2016-02-11 10:00","2016-02-25 18:00","2016-02-11 10:00","2016-02-25 18:00","연속",null,null,null,201512180037]
[2,"강원","태백","신태백S/S 765kV #2 BUS","신태백S/S 800kV GIS 설치공사","800kV GIS(8000A/50kA) 3CB 설치","2016-02-26 10:00","2016-03-11 18:00","2016-02-26 10:00","2016-03-11 18:00","연속",null,null,null,201512180038]
[3,"대전충남","서산","당진T/P TIE Tr A","당진T/P 765kV Tie-Tr 보통점검","○당진T/P Tie-Tr 보통점검 및 보호반 교체 / 81Bay, 71Bay 차단실패 보호반 교체","2016-02-10 09:00","2016-02-24 18:00","취소","취소","연속",null,null,null,201512110047]
[4,"부산울산","동부산","신고리S/S #3 M.Tr A-1","345kV 고리N/P 통합S/Y 토건공사","원자력기술위원회의 사면 추가보강 요청으로 인한 활선근접작업","2016-02-11 10:00","2016-02-25 18:00","2016-02-11 10:00","2016-02-25 18:00","연속",null,null,null,201512220021]
[5,"부산울산","동부산","신고리S/S #1 M.Tr A-1","신고리S/S 765kV M.Tr Trip회로 개선","신고리 765kV #1M.Tr 시지연Trip 및 AC회로 개선(#1M.Tr 휴전시 345kV 신고리-고리#1T/L 휴전)","2016-02-26 10:00","2016-03-11 18:00","2016-02-26 10:00","2016-03-11 18:00","연속",null,null,null,201512160064]

{"sheet":"345송부","index":1,"n_rows":35,"n_cols":16,"rows_kept":35,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2016년도 2월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"인천","시흥","신시흥영흥TP#1 T/L","345kV 영흥T/L 피뢰기 설치 및 전력선 교체공사","- 피뢰기 설치 : 87기(261Set)","2016-02-20 08:00","2016-03-09 18:00","2016-02-20 08:00","2016-02-28 18:00","연속",null,null,"신뢰도개선",201512230057]
[2,"인천","시흥","신시흥영흥TP#3 T/L","345kV 영흥T/L 피뢰기 설치 및 전력선 교체공사","- 피뢰기 설치 : 33기(99Set),- 전력선 교체 : No.54~55(0.312C-km)","2016-02-29 08:00","2016-03-12 18:00","2016-02-29 08:00","2016-03-12 18:00","연속",null,null,null,201512230058]
[3,"인천","시흥","영흥TP연락#2 T/L","345kV 영흥T/L 피뢰기 설치 및 전력선 교체공사","- 피뢰기 설치 : 8기(24Set)","2016-02-20 08:00","2016-02-22 18:00","2016-02-20 08:00","2016-02-22 18:00","연속",null,null,null,201512230060]
[4,"인천","인천","신김포서인천CC T/L","345kV 신김포-서인천CCT/L 중간접속함 교체공사","중간접속함 54Set 전량 교체(PJ→맞춤형 PMJ)","2016-02-14 09:00","2016-03-20 18:00","2016-02-14 09:00","2016-03-20 18:00","연속",null,null,"신뢰도개선",201512230034]
[5,"인천","인천","인천CC S/Y 345kV #76 BUS","인천CC 용량부족 GIS 대체공사","- DS(7352) 1조 철거","2016-02-22 10:00","2016-02-26 18:00","2016-02-22 10:00","2016-02-26 18:00","연속",null,null,null,201512110017]
[6,"경기북부","직할","양주S/S #3 M.Tr A","345KV 양주S/S #3M.Tr 설치공사","#3M.Tr C상 설치","2016-02-25 09:00","2016-02-29 18:00","2016-02-25 09:00","2016-02-29 18:00","연속",null,null,null,201512170014]
[7,"강원","동해","동해S/S #1 M.Tr A","동해S/S 취약설비 GIS화 공사","- #1M.Tr 2차측 이설 - 2차측 상모선 철거 및 인출분기모선 설치 - 감시반 이설(신규설비)","2016-02-14 08:00","2016-02-17 18:00","2016-02-14 08:00","2016-02-17 18:00","연속",null,null,null,201512140007]
[8,"충북","직할","신제천S/S #1 M.Tr A","345kV 신제천S/S GIS화 공사","345kV GIS 15대, 154kV GIS 28CCT - 345kV GIS 설치공간확보","2016-02-16 08:00","2016-02-18 18:00","2016-02-16 08:00","2016-02-18 18:00","연속",null,null,null,201512150015]
[9,"충북","직할","신제천S/S 345kV #1 BUS","345kV 신제천S/S GIS화 공사","345kV GIS 15대, 154kV GIS 28CCT - 345kV GIS 설치공간확보 (#2M.Tr 분기모선 철거)","2016-02-21 08:00","2016-02-21 18:00","2016-02-21 08:00","2016-02-21 18:00","당일",null,null,null,201512150010]
[10,"충북","직할","신제천S/S 345kV #2 BUS","345kV 신제천S/S GIS화 공사","345kV GIS 15대, 154kV GIS 28CCT - 345kV GIS 설치공간확보 (#2M.Tr 분기모선 철거)","2016-02-20 08:00","2016-02-20 18:00","2016-02-20 08:00","2016-02-20 18:00","당일",null,null,null,201512150011]
[11,"충북","직할","신제천S/S 345kV #1 BUS","345kV 신제천S/S GIS화 공사","345kV GIS 15대, 154kV GIS 28CCT - 345kV GIS 설치공간확보 (#1M.Tr 분기모선 철거)","2016-02-17 08:00","2016-02-17 18:00","2016-02-17 08:00","2016-02-17 18:00","당일",null,null,null,201512150013]
[12,"충북","직할","신제천S/S #2 M.Tr A","345kV 신제천S/S GIS화 공사","345kV GIS 15대, 154kV GIS 28CCT - 345kV GIS 설치공간확보","2016-02-19 08:00","2016-06-30 18:00","2016-02-19 08:00","2016-06-30 18:00","연속",null,null,null,201512150008]
[13,"충북","청원","신옥천S/S #3 M.Tr A","신옥천S/S 345kV 차단기 용량부족대체공사","-345kV CB 18대 철거 18CB 설치 - 기타부대공사","2016-02-22 09:00","2016-02-24 18:00","취소","취소","연속",null,null,null,201512140045]
[14,"충북","청원","신옥천S/S #2 M.Tr A","신옥천S/S 345kV 차단기 용량부족대체공사","-345kV CB 18대 철거 18CB 설치 - 기타부대공사","2016-02-18 09:00","2016-02-20 18:00","취소","취소","연속",null,null,null,201512140044]
[15,"충북","청원","신옥천S/S #1 M.Tr A","신옥천S/S 345kV 차단기 용량부족대체공사","-345kV CB 18대 철거 18CB 설치 - 기타부대공사","2016-02-15 09:00","2016-02-17 18:00","취소","취소","연속",null,null,null,201512140043]
[16,"대전충남","서산","신서산신당진#1 T/L","345kV 신서산-신당진#1T/L No.9~10 정비공사","중단 2번 스페이서댐퍼 키퍼풀림 정비","2016-02-04 08:00","2016-02-04 18:00","2016-02-04 08:00","2016-02-04 18:00","당일",null,null,null,201512140095]
[17,"대구경북","영주","신영주S/S #3M.Tr A","신영주S/S 362kV GIS화 공사","○ 362kV GIS 반입 및 정치를 위한 안전이격확보","2016-02-01 09:00","2016-02-01 18:00","2016-02-01 09:00","2016-02-01 18:00","당일",null,null,null,201512080039]
[18,"대구경북","영주","신영주S/S #2 M.Tr A","신영주S/S 362kV GIS화 공사","○ 362kV GIS 반입 및 정치를 위한 안전이격확보","2016-02-15 09:00","2016-02-15 13:00","2016-02-15 09:00","2016-02-15 13:00","당일",null,null,null,201512080040]
[19,"대구경북","영주","신영주S/S #1 M.Tr A","신영주S/S 362kV GIS화 공사","○ 362kV GIS 반입 및 정치를 위한 안전이격확보","2016-02-15 13:00","2016-02-15 18:00","2016-02-15 13:00","2016-02-15 18:00","당일",null,null,null,201512080041]
[20,"대구경북","포항","신포항S/S #3 M.Tr A","신포항S/S #3M.Tr 휴전작업","7851,7852,78861,7821 DS 전자변 교체","2016-02-23 09:00","2016-02-24 18:00","2016-02-23 09:00","2016-02-24 18:00","연속",null,null,null,201512110246]
[21,"부산울산","울산","신온산S/S 신울산-신온산#2T/L 1차TIE CB (7100)","2016-17년 울산전력지사 변전협력 총액공사","7100 GIS 하자점검","2016-02-25 09:00","2016-02-25 18:00","2016-02-25 09:00","2016-02-25 18:00","당일",null,null,null,201512150153]
[22,"부산울산","울산","신온산S/S 북부산-신온산T/L CB (7371)","2016-17년 울산전력지사 변전협력 총액공사","7371 GIS 보통점검","2016-02-26 09:00","2016-02-26 18:00","2016-02-26 09:00","2016-02-26 18:00","당일",null,null,null,201512150154]
[23,"부산울산","울산","신온산S/S 신울산-신온산#1T/L 1차 CB (7271)","2016-17년 울산전력지사 변전협력 총액공사","7271 GIS 하자점검","2016-02-23 09:00","2016-02-23 18:00","2016-02-23 09:00","2016-02-23 18:00","당일",null,null,null,201512150151]
[24,"부산울산","울산","신온산S/S 신울산-신온산#2T/L 1차 CB (7171)","2016-17년 울산전력지사 변전협력 총액공사","7171 GIS 하자점검","2016-02-24 09:00","2016-02-24 18:00","2016-02-24 09:00","2016-02-24 18:00","당일",null,null,null,201512150152]
[25,"부산울산","울산","울주S/S 울주-신경산#2T/L CB (7771)","2016-17년 울산전력지사 변전협력 총액공사","7771 GIS 보통점검","2016-02-22 09:00","2016-02-22 18:00","2016-02-22 09:00","2016-02-22 18:00","당일",null,null,null,201512150150]
[26,"경남","직할","신김해S/S 해북#2T/L-#2 M.Tr 1차 CB (7400)","신김해S/S 해북#2T/L-#2M.Tr 1차 CB(7400) 보통점검","신김해S/S 해북#2T/L-#2M.Tr 1차 CB(7400) 보통점검","2016-02-23 09:30","2016-02-23 17:30","2016-02-23 09:30","2016-02-23 17:30","당일",null,null,null,201512100107]
[27,"경남","진주","의령S/S 의령-하동화력#2T/L-TIE CB (7200)","345kV 7200 보통점검","345kV 7200 보통점검","2016-02-17 09:30","2016-02-17 18:30","2016-02-17 09:30","2016-02-17 18:30","당일",null,null,null,201512170103]
[28,"경남","진주","의령S/S 예비 M.Tr(#2 BANK)","345kV 예비 변압기 보통점검","345kV 예비 변압기 보통점검","2016-02-29 09:30","2016-02-29 18:30","2016-02-29 09:30","2016-02-29 18:30","당일",null,null,null,201512170109]
[29,"경남","진주","의령S/S 의령-산청양수#2T/L-#1M.Tr 1차 CB (7300)","345kV 7300 보통점검","345kV 7300 보통점검","2016-02-18 09:30","2016-02-18 18:30","2016-02-18 09:30","2016-02-18 18:30","당일",null,null,null,201512170105]
[30,"경남","진주","의령S/S 의령-하동화력#2T/L CB (7271)","345kV 7271 보통점검","345kV 7271 보통점검","2016-02-16 09:30","2016-02-16 18:30","2016-02-16 09:30","2016-02-16 18:30","당일",null,null,null,201512170102]
[31,"경남","진주","의령S/S 의령-하동화력#1T/L-TIE CB (7100)","345kV 7100 보통점검","345kV 7100 보통점검","2016-02-15 09:30","2016-02-15 18:30","2016-02-15 09:30","2016-02-15 18:30","당일",null,null,null,201512170101]

{"sheet":"154송부","index":2,"n_rows":32,"n_cols":16,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2016년도 2월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","직할","중부신촌 T/L","신촌S/S 154kV 장기사용 GIS 대체","중부신촌T/L GIS 대체","2016-02-10 08:00","2016-02-29 18:00","2016-02-10 08:00","2016-02-29 18:00","연속",null,null,null,201512160090]
[2,"서울","직할","신촌순화 T/L","신촌S/S 154kV 장기사용 GIS 대체","중부신촌T/L GIS 대체","2016-02-10 08:00","2016-02-29 18:00","2016-02-10 08:00","2016-02-29 18:00","연속",null,null,null,201512160091]
[3,"남서울","직할","교대이수#2 T/L","154kV 교대-이수T/L 지중선로 이설공사(방배로 1구간)","배경: 서초구청 시행 하수암거 설치에 따른 지중선로 이설 개요: 154KV 교대-이수T/L J/B#7~8, #9~10 (2구간, 0.66KM) XLPE1200 * 2회선","2016-02-10 09:00","2016-03-18 18:00","2016-02-10 09:00","2016-03-18 18:00","연속",null,null,null,201510140145]
[4,"인천","김포","양촌양곡#1 T/L","154kV 양촌-양곡T/L No.13 지장철탑 이설공사","□ 제 2외곽순환도로 조성에 따른 지장철탑 이설 □ 공사개요 : 154kV 양촌-양곡T/L No.13 이설 - No.13 본철탑 이설","2016-02-25 07:00","2016-02-27 18:00","2016-02-25 07:00","2016-02-27 18:00","연속",null,null,"신뢰도개선",201512160084]
[5,"인천","김포","양촌양곡#2 T/L","154kV 양촌-양곡T/L No.13 지장철탑 이설공사","□ 제 2외곽순환도로 조성에 따른 지장철탑 이설 □ 공사개요 : 154kV 양촌-양곡T/L No.13 이설 - No.13 본철탑 이설","2016-02-22 07:00","2016-02-24 18:00","2016-02-22 07:00","2016-02-24 18:00","연속",null,null,"신뢰도개선",201512160083]
[6,"인천","인천","남인천S/S 154kV #1 BUS TIE GIS","남인천S/S 6100 GIS 보통점검 공사","남인천S/S 6100 GIS 보통점검 공사","2016-02-25 09:30","2016-02-25 18:00","2016-02-25 09:30","2016-02-25 18:00","당일",null,null,null,201512090050]
[7,"강원","동해","동해정선 T/L","동해S/S 취약설비 GIS화 공사","- 154kV 동해-정선T/L 이설 - 상모선 철거 및 안출분기모선 설치 - 감시반 이설(신규설비)","2016-02-03 08:00","2016-02-05 18:00","2016-02-03 08:00","2016-02-05 18:00","연속",null,null,null,201512140003]
[8,"강원","동해","동해강릉 T/L","동해S/S 취약설비 GIS화 공사","- 154kV 동해-강릉 T/L 이설 - 상모선 철거 및 안출분기모선 설치 - 감시반 이설(신규설비)","2016-02-18 08:00","2016-02-20 18:00","2016-02-18 08:00","2016-02-20 18:00","연속",null,null,null,201512140005]
[9,"강원","동해","동해영동TP T/L","동해S/S 취약설비 GIS화 공사","- 154kV 동해-영동TP T/L 이설 - 상모선 철거 및 안출분기모선 설치 - 감시반 이설(신규설비)","2016-02-11 08:00","2016-02-13 18:00","2016-02-11 08:00","2016-02-13 18:00","연속",null,null,null,201512140004]
[10,"대전충남","서산","대산석문#2 T/L","154kV 대산-석문T/L 전선접속개소 전력선 교체공사","No.23~27 전선접소개소 전력선 및 가공지선 교체[송전]","2016-02-25 07:00","2016-02-27 18:00","취소","취소","연속",null,null,"신뢰도개선",201512090077]
[11,"대전충남","서산","대산석문#1 T/L","154kV 대산-석문T/L 전선접속개소 전력선 교체공사","No.20~27 전선접소개소 전력선 및 가공지선 교체[송전]","2016-02-28 07:00","2016-03-02 18:00","취소","취소","연속",null,null,"신뢰도개선",201512090076]
[12,"대전충남","서산","아산송악#1 T/L","154kV아산-송악#1T/L 상간스페이서 설치 공사","No.136~137,142~143 상간스페이서 설치","2016-02-13 08:00","2016-02-13 18:00","2016-02-13 08:00","2016-02-13 18:00","당일",null,null,null,201512140011]
[13,"대전충남","아산","불당서천안#2 T/L","불당S/S 154kV 불당-서천안#2T/L 장기미동작 차단기 조작시험","○154kV 불당-서천안#2T/L 장기미동작 차단기 조작시험","2016-02-13 10:00","2016-02-13 11:00","2016-02-13 10:00","2016-02-13 11:00","당일",null,null,null,201512160016]
[14,"대전충남","아산","불당서천안#1 T/L","불당S/S 154kV 불당-서천안#1T/L 장기미동작 차단기 조작시험","○154kV 불당-서천안#1T/L 장기미동작 차단기 조작시험","2016-02-13 09:00","2016-02-13 10:00","2016-02-13 09:00","2016-02-13 10:00","당일",null,null,null,201512160015]
[15,"대전충남","청양","관창보령복합 T/L","보관T/L 안전이격확보공사관련 지질조사","철탑 부지 19,20호 지질조사","2016-02-13 09:00","2016-02-13 18:00","2016-02-13 09:00","2016-02-13 18:00","당일",null,null,null,201512090095]
[16,"대전충남","청양","보령T/P 154kV #1 BUS TIE CB","관내S/S 154kV 차단기 부동작 예방 조작시험","○ 보령화력 154kV CB 부동작 예방 조작시험","2016-02-03 13:00","2016-02-03 15:00","2016-02-03 13:00","2016-02-03 15:00","당일",null,null,null,201512100039]
[17,"대전충남","청양","서천T/P 154kV #1 BUS TIE CB","관내S/S 154kV 차단기 부동작 예방 조작시험","○ 서천화력 154kV CB 부동작 예방 조작시험","2016-02-03 09:00","2016-02-03 11:00","2016-02-03 09:00","2016-02-03 11:00","당일",null,null,null,201512100017]
[18,"전북","김제","고창영광 T/L","고창S/S 고창-영광T/L","축소형 고장기록장치 설치","2016-02-01 10:00","2016-02-01 18:00","2016-03-03 10:00","2016-03-03 18:00","당일",null,null,null,201512160009]
[19,"전북","김제","고창홍농 T/L","고창S/S 고창-홍농T/L","축소형 고장기록장치 설치","2016-02-02 10:00","2016-02-02 18:00","2016-03-04 10:00","2016-03-04 18:00","당일",null,null,null,201512160010]
[20,"광주전남","직할","장성영광#2 T/L","16~17년 직할 송전정비협력회사 총액공사","공사개요 전선접속개소해소 전선교체 1.28km","2016-02-24 08:00","2016-02-26 18:00","취소","취소","연속",null,null,"신뢰도개선",201512150017]
[21,"광주전남","직할","장성영광#1 T/L","16~17년 직할 송전정비협력회사 총액공사","공사개요 전선접속개소해소 전선교체 1.28km","2016-02-22 08:00","2016-02-23 18:00","취소","취소","연속",null,null,"신뢰도개선",201512150016]
[22,"대구경북","포항","신포항포항#2 T/L","신포항-포항#2T/L 휴전작업","신포항S/S 657CB, 651,652,656,658 DS, LA, PT 보통점검 포항S/S 687 GIS 보통점검, 포스코측 댐퍼보수 작업","2016-02-16 09:00","2016-02-16 18:00","2016-02-16 09:00","2016-02-16 18:00","당일",null,null,null,201512170138]
[23,"부산울산","동부산","웅촌서창#2 T/L","서창S/S #2M.Tr 1차 A,C상 부싱 교체","서창S/S #2M.Tr 1차 A,C상 부싱 교체 시험가압(웅촌-서창#2T/L)","2016-02-03 18:00","2016-02-04 18:00","2016-02-03 18:00","2016-02-04 18:00","연속",null,null,null,201512220015]
[24,"부산울산","북부산","김해S/S 154kV #2 BUS","2016년 김해S/S BUS-TIE 대체공사","#2DS 설치","2016-02-28 18:00","2016-03-07 18:00","2016-02-28 18:00","2016-03-07 18:00","연속",null,null,null,201512120009]
[25,"부산울산","북부산","매리김해#1 T/L","2016년 김해S/S BUS-TIE 대체공사","#2DS시험가압 48시간","2016-02-26 18:00","2016-02-28 18:00","2016-02-26 18:00","2016-02-28 18:00","연속",null,null,null,201512120012]
[26,"부산울산","북부산","김해S/S 154kV #1 BUS","2016년 김해S/S BUS-TIE 대체공사","#1DS, CB설치","2016-02-22 09:00","2016-02-28 18:00","2016-02-22 09:00","2016-02-28 18:00","연속",null,null,null,201512120008]
[27,"경남","통영","통영거제#2 T/L","거제S/S 154kV 통영-거제#2T/L 휴전(정밀점검시험가압)","거제S/S 154kV 통영-거제#2T/L 휴전(정밀점검시험가압) - #2 BUS 시험가압용","2016-02-07 17:30","2016-02-07 18:30","취소","취소","당일",null,null,null,201512150021]
[28,"경남","통영","통영거제#1 T/L","거제S/S 154kV 통영-거제#1T/L 휴전(정밀점검시험가압)","거제S/S 154kV 통영-거제#1T/L 휴전(정밀점검시험가압) - #1 BUS 및 삼성조선T/L 시험가압용","2016-02-08 17:30","2016-02-08 18:30","2016-02-06 09:30","2016-02-10 18:30","당일",null,null,null,201512150022]

{"sheet":"한수원","index":3,"n_rows":7,"n_cols":20,"rows_kept":7,"cut":false,"hidden":false,"merged":[[2,14,3,14],[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,15,3,15],[2,16,3,16],[2,17,3,17],[2,18,3,18],[2,19,3,19]]}
["2016년도 2월 월간 휴전계획표"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업\n구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소간","사업소내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"한울본부","한울2발","PCB 7500, 7572","한울3호기 제13차 계획예방정비 가스절연모선 교체","○ 한울3호기 계획예방정비 관련 #3 가스절연모선 교체\n * 조작차단기 : 기존 SWYD PCB 7500,7572\n ※ 휴전절차 : 차단기 개방 후 신설 SWYD 접속 변경","2016-02-12T10:00:00","2016-02-12T10:00:00","2016-02-12T10:00:00","2016-02-12T10:00:00","연속","Y"]
[2,"고리본부","2발전소","#4 기동용변압기(X01)","고리4호기 계획예방정비 관련 기동변압기 #1 정비\n* 조작차단기 : 7C00, 7C72","- 기동변압기 #1 정비","2016-02-20 09:00","2016-02-23 18:00","2016-02-20 09:00","2016-02-23 18:00","연속"]
[3,"고리본부","2발전소","#4 기동용변압기(X02)","고리4호기 계획예방정비 관련 기동변압기 #2 휴전\n* 조작차단기 : 7600, 7672","- 기동변압기 #2 정비","2016-02-29 09:00","2016-03-03 18:00","2016-02-29 09:00","2016-03-03 18:00","연속"]

{"sheet":"중부","index":4,"n_rows":5,"n_cols":20,"rows_kept":5,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,16,3,16],[2,17,3,17],[2,18,3,18],[2,19,3,19],[2,14,3,14],[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2016년도 2월 휴전계획표(한국중부발전)"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"보령화력","2발전소","5,6호기\n기동변압기\n(CB7400,7471)","법정검사 및\n정기점검","보호계전기 정정 및\n회로점검\n차단기 보통점검 : PCB7471,7400","2016-02-22T09:00:00","2016-02-26T18:00:00","2016-02-22T09:00:00","2016-02-26T18:00:00","연속","Y"]