{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["765송부","345송부","154송부","한수원"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":9,"n_cols":16,"rows_kept":9,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2016년도 8월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"부산울산","동부산","신고리N/P #3Tie-Tr","신고리S/S #1BUS 불량 벨로우즈 교체","신고리S/S #1BUS 불량 벨로우즈 교체관련 시험가압(#3M.Tr 사용)","2016-08-12 09:00","2016-08-12 11:00","2016-08-12 09:00","2016-08-12 11:00","연속",null,null,null,201606130223]
[2,"부산울산","동부산","신고리N/P 765kV #1 BUS","신고리S/S #1BUS 불량 벨로우즈 교체","신고리S/S #1BUS 불량 벨로우즈 교체(#1BUS 휴전) - 8251DS측 가스누기 보수","2016-08-08 09:00","2016-08-12 11:00","2016-08-08 09:00","2016-08-12 11:00","연속",null,null,null,201606130222]
[3,"경남","함안","북경남신고리NP#1 T/L","북경남S/S 800kV GIS 인출 스페이셔 교체공사및 차단부 보통점검","북경남S/S 800kV GIS 인출 스페이셔 72EA 교체및 8671, 8600 GIS 보통점검","2016-08-01 09:00","2016-09-18 18:00","2016-08-01 09:00","2016-09-18 18:00","연속",null,null,null,201606270083]
[4,"경남","함안","북경남S/S #5 M.Tr","북경남S/S 765kV M.Tr 초기점검공사및 차단부 이너노즐교체","북경남S/S 765kV M.Tr 초기점검공사및 차단부 이너노즐교체","2016-08-22 08:00","2016-08-31 18:00","2016-08-22 08:00","2016-08-31 18:00","연속",null,null,null,201606290063]
[5,"경남","함안","북경남S/S #3 M.Tr","북경남S/S 765kV M.Tr 초기점검공사및 차단부 이너노즐교체","북경남S/S 765kV M.Tr 초기점검공사및 차단부 이너노즐교체","2016-08-08 08:00","2016-08-17 18:00","2016-08-08 08:00","2016-08-17 18:00","연속",null,null,null,201606290062]

{"sheet":"345송부","index":1,"n_rows":38,"n_cols":16,"rows_kept":38,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2016년도 8월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"인천","인천","신가좌가정#2 T/L","피뢰기 설치공사(가공송전정비 협력회사 총액공사)","송전철탑 피뢰기 설치","2016-08-22 08:00","2016-08-23 18:00","2016-08-22 08:00","2016-08-23 18:00","매일",null,null,null,201606150147]
[2,"인천","인천","신가좌신시흥#2 T/L","피뢰기 설치공사(가공송전정비 협력회사 총액공사)","송전철탑 피뢰기 설치","2016-08-24 08:00","2016-08-29 18:00","2016-08-24 08:00","2016-08-29 18:00","매일",null,null,null,201606150148]
[3,"인천","인천","신경서S/S #1 M.Tr A","신경서S/S #1M.Tr 보호반 대체공사","신경서S/S #1M.Tr 보호반 대체공사","2016-08-29 09:00","2016-09-02 18:00","2016-08-29 09:00","2016-09-02 18:00","연속",null,null,null,201606110002]
[4,"강원","태백","신태백S/S #4 M.Tr 2차-TIE CB (7700)","신태백S/S 362kV GIS 정밀점검공사","#4 M.Tr 2차-TIE CB(7700) 정밀점검","2016-08-22 09:00","2016-08-24 18:00","2016-08-22 09:00","2016-08-24 18:00","연속",null,null,null,201606160015]
[5,"강원","태백","신태백S/S #4 M.Tr 2차 CB (7771)","신태백S/S 362kV GIS 정밀점검공사","#4 M.Tr 2차 CB(7771) 정밀점검","2016-08-18 09:00","2016-08-20 18:00","2016-08-18 09:00","2016-08-20 18:00","연속",null,null,null,201606160013]
[6,"강원","태백","신태백S/S 345kV #3 Sh.R CB (7571)","신태백S/S 362kV GIS 정밀점검공사","345kV #3 Sh.R CB(7571) 정밀점검","2016-08-11 09:00","2016-08-13 18:00","2016-08-11 09:00","2016-08-13 18:00","연속",null,null,null,201606160011]
[7,"강원","태백","신태백S/S#3 Sh.R-신태백-한울NP2#1T/L CB (7500)","신태백S/S 362kV GIS 정밀점검공사","#3Sh.R-신태백-한울NP2#1T/L CB(7500) 정밀점검","2016-08-08 09:00","2016-08-10 18:00","2016-08-08 09:00","2016-08-10 18:00","연속",null,null,null,201606160010]
[8,"충북","직할","신제천S/S #1 M.Tr A","신제천S/S 345kV GIS화 공사","345kV #1M.TR 1차측 차단기 철거 345kV GIS 설치","2016-08-11 08:00","2016-12-10 18:00","2016-08-11 08:00","2016-12-10 18:00","연속",null,null,null,201605230020]
[9,"충북","직할","곤지암신충주#2 T/L","장기사용 보호배전반 대체","장기사용 보호배전반 대체","2016-08-29 08:00","2016-09-02 18:00","2016-08-29 08:00","2016-09-02 18:00","연속",null,null,null,201606240076]
[10,"충북","직할","곤지암신충주#1 T/L","장기사용 보호배전반 대체","장기사용 보호배전반 대체","2016-08-22 08:00","2016-08-26 18:00","2016-08-22 08:00","2016-08-26 18:00","연속",null,null,null,201606240075]
[11,"충북","청주","신옥천S/S 345kV #1 BUS","345kV 신옥천S/S 용량부족차단기 대체공사","1. 설치공사시행 사전 안전이격확보 2. 하부모선 일부 변경 시공","2016-08-09 09:00","2016-08-10 18:00","2016-08-09 09:00","2016-08-10 18:00","연속",null,null,null,201606290067]
[12,"충북","청주","신옥천S/S #2 M.Tr A","신옥천S/S 345kV 차단기 용량부족대체공사","-345kV CB 18대 철거 18CB 설치 - 기타부대공사","2016-08-31 09:00","2016-09-07 18:00","2016-08-31 09:00","2016-09-07 18:00","연속",null,null,null,201606220014]
[13,"충북","청주","신옥천S/S #1 M.Tr A","신옥천S/S 345kV 차단기 용량부족대체공사","-345kV CB 18대 철거 18CB 설치 - 기타부대공사","2016-08-23 09:00","2016-08-29 18:00","2016-08-23 09:00","2016-08-29 18:00","연속",null,null,null,201606220013]
[14,"충북","청주","신옥천S/S #3 M.Tr A","신옥천S/S 345kV 차단기 용량부족대체공사","-345kV CB 18대 철거 18CB 설치 - 기타부대공사","2016-08-09 09:00","2016-08-16 18:00","2016-08-09 09:00","2016-08-16 18:00","연속",null,null,null,201606220015]
[15,"대전충남","청양","신계룡청양 T/L","345kV 신계룡-청양T/L 피뢰기 설치공사","131~225(95기) 피뢰기 설치공사","2016-08-29 09:00","2016-09-06 18:00","2016-08-29 09:00","2016-09-06 18:00","당일",null,null,null,201606090075]
[16,"전북","군산","군산S/S #4 M.Tr A","군산S/S #4 M.Tr","1. 예비변압기 보호배전반 설치","2016-08-29 09:00","2016-08-30 18:00","2016-08-29 09:00","2016-08-30 18:00","연속",null,null,null,201606130015]
[17,"전북","군산","군산S/S #1 M.Tr A","군산S/S #1 M.Tr","1. 예비변압기 보호배전반 설치","2016-08-22 09:00","2016-08-23 18:00","2016-08-22 09:00","2016-08-23 18:00","연속",null,null,null,201606130010]
[18,"전북","군산","군산S/S #2 M.Tr A","군산S/S #2 M.Tr","1. 예비변압기 보호배전반 설치","2016-08-24 09:00","2016-08-25 18:00","2016-08-24 09:00","2016-08-25 18:00","연속",null,null,null,201606130011]
[19,"전북","군산","군산S/S #3 M.Tr A","군산S/S #3 M.Tr","1. 예비변압기 보호배전반 설치","2016-08-26 09:00","2016-08-27 18:00","2016-08-26 09:00","2016-08-27 18:00","연속",null,null,null,201606130013]
[20,"전북","직할","신옥천신남원#1 T/L","345kV 신옥천-신남원#1T/L 휴전","345kV 신옥천-신남원#1T/L 고장발생 원인규명","2016-08-22 09:30","2016-09-10 18:00","취소","취소","연속",null,null,null,201606160066]
[21,"전북","직할","신남원S/S 345kV #1 BUS","신남원S/S 345kV #1BUS 휴전","345kV 신옥천-신남원#1T/L 고장발생 원인규명","2016-08-22 09:30","2016-09-10 18:00","취소","취소","당일",null,null,null,201606160068]
[22,"광주전남","순천","광양하동화력#1 T/L","345kV 광양-하동TP#1T/L(피뢰기 설치공사)","345kV 신남원-광양 등 16개T/L 피뢰기 설치공사 - 광양-하동TP#1T/L 피뢰기 설치 : 26~73호, 48기","2016-08-22 07:00","2016-08-28 18:00","취소","취소","연속",null,null,null,201606130246]
[23,"대구경북","영주","신영주한울NP2#2 T/L","신영주S/S 362kV GIS화 공사","부하전환 및 송전선로 인출변경","2016-08-15 08:00","2016-08-25 18:00","일정변경","일정변경","연속",null,null,null,201606120013]
[24,"대구경북","영주","신영주S/S #1 M.Tr A","신영주S/S 362kV GIS화 공사","부하전환(보호반 이설)","2016-08-15 08:00","2016-08-25 18:00","일정변경","일정변경","연속",null,null,null,201606120016]
[25,"대구경북","영주","신영주S/S 345kV #1 BUS","신영주S/S 362kV GIS화 공사","인출 DS 리드철거를 위한 안전이격 확보","2016-08-15 08:00","2016-08-15 18:00","일정변경","일정변경","당일",null,null,null,201606120014]
[26,"대구경북","영주","신영주S/S 345kV #2 BUS","신영주S/S 362kV GIS화 공사","송전선로 연장 및 가공지선 신규설치","2016-08-06 08:00","2016-08-10 18:00","일정변경","일정변경","연속",null,null,null,201606120012]
[27,"대구경북","영주","신영주S/S 345kV #1 BUS","신영주S/S 362kV GIS화 공사","인출 DS 리드철거를 위한 안전이격 확보","2016-08-04 08:00","2016-08-04 18:00","일정변경","일정변경","당일",null,null,null,201606120011]
[28,"대구경북","영주","신영주한울NP2#1 T/L","신영주S/S 362kV GIS화 공사","부하전환(옥외철구 → GIS) 및 송전선로 인출 변경","2016-08-04 08:00","2016-08-14 18:00","일정변경","일정변경","연속",null,null,null,201606120010]
[29,"대구경북","영주","신영주S/S 345kV #1 BUS","신영주S/S 362kV GIS화 공사","○ #1BUS 모선연계용 ACSR 및 POST. 옥외철구 #1BUS 철거 ○ GIS 모선보호반 단독운전을 위한 CT비 변경(4000/5 → 6000/5)","2016-08-26 08:00","2016-08-28 18:00","일정변경","일정변경","연속",null,null,null,201606120018]
[30,"대구경북","영주","신영주S/S 345kV #2 BUS","신영주S/S 362kV GIS화 공사","송전선로 연장 및 가공지선 신규 설치","2016-08-17 08:00","2016-08-21 18:00","일정변경","일정변경","연속",null,null,null,201606120015]
[31,"대구경북","영주","신영주S/S 345kV #2 BUS","신영주S/S 362kV GIS화 공사","○ #2BUS 모선연계용 ACSR 및 옥외철구 #2BUS 철거 ○ GIS 모선보호반 단독운전을 위한 CT비 변경(4000/5 → 6000/5)","2016-08-29 08:00","2016-08-31 18:00","일정변경","일정변경","연속",null,null,null,201606120019]
[32,"대구경북","영주","신제천신영주#1 T/L","신영주S/S 362kV GIS화 공사","부하전환(보호반 이설)","2016-08-26 08:00","2016-09-05 18:00","일정변경","일정변경","연속",null,null,null,201606120017]
[33,"부산울산","동부산","신울산고리NP#2 T/L","345kV 신울산-고리NP T/L 9~12호 지장철탑이설공사","○ 장안-온산1 국도건설공사에 지장이 되는 송전철탑 이설공사 ○ 이설철탑 : 본철탑 11호 설치, 10~11호 전선교체 ○ 9, 12호 애자장치 보강","2016-08-25 09:00","2016-09-07 18:00","2016-08-25 09:00","2016-09-07 18:00","연속",null,null,null,201606090057]
[34,"부산울산","동부산","신울산고리NP#1 T/L","345kV 신울산-고리NP T/L 9~12호 지장철탑이설공사","○ 장안-온산1 국도건설공사에 지장이 되는 송전철탑 이설공사 ○ 이설철탑 : 본철탑 11호 설치, 10~11호 전선교체 ○ 9, 12호 애자장치 보강","2016-08-25 09:00","2016-09-07 18:00","2016-08-25 09:00","2016-09-07 18:00","연속",null,null,null,201606090054,"○ "]

{"sheet":"154송부","index":2,"n_rows":45,"n_cols":16,"rows_kept":45,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2016년도 8월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","금오상계#1 T/L","송전용 피뢰기 설치공사","송전용 피뢰기 설치 * 42세트(14기)","2016-08-24 08:00","2016-08-25 18:00","2016-08-24T08:00:00","2016-08-25T18:00:00","연속",null,null,null,201606170019]
[2,"서울","성동","군자화양#2 T/L","화양 및 세종로S/S 인출선로 선종교체공사","1. 사 업 명 : 화양 및 세종로S/S 인출선로 선종교체공사 2. 사업목적 : 지하복합변전소 화재 및 대형 재난사고 예방 3. 사업개요 ○ 사업구간 : 화양S/S ∼ 인출전력구, 세종로S/S ∼ 인출전력구 ○ 사업내용 : 154kV 6회선 0.6km 선종교체","2016-08-16 09:00","2016-09-21 18:00","2016-08-16T09:00:00","2016-09-21T18:00:00","연속",null,null,null,201605120127]
[3,"서울","중부","양주은평#2 T/L","복도체 스페이서 간격조정","복도체 스페이서 간격조정 * 5경간(13~18호간)","2016-08-26 08:00","2016-08-26 18:00","2016-08-26T08:00:00","2016-08-26T18:00:00","당일",null,null,null,201606170023]
[4,"인천","시흥","신시흥남동#2 T/L","154kV 신시흥-남동 #2T/L 접지선 교체공사","접지선 기준개정 관련 구형 접지선 교체","2016-08-30 09:00","2016-08-30 18:00","취소","취소","당일",null,null,"계통안정",201606160018]
[5,"인천","시흥","신시흥남동#1 T/L","154kV 신시흥-남동 #1T/L 접지선 교체공사","접지선 기준개정 관련 구형 접지선 교체","2016-08-29 09:00","2016-08-29 18:00","취소","취소","당일",null,null,"계통안정",201606160017]
[6,"인천","인천","신현포스코CC#1 T/L","154kV 신현포스코CCT/L 지장송전선로 이설 공사","한진중공업에서 시행하는 인천북항 배후부지 항만구역 조성공사에 지장되는 154kV 신현-포스코CC T/L 지장이설 필요 - 이설구간 : 154kV 신현-포스코CC #1T/L M/H #4~M/H #5 (약313m)","2016-08-25 09:00","2016-09-13 18:00","2016-08-25T09:00:00","2016-09-13T18:00:00","연속",null,null,null,201606150167]
[7,"경기북부","파주","원흥수색#1 T/L","154kV 원흥수색T/L No.13 지장송전선로 이설공사","#1T/L : 8.29~30(2일), #2T/L : 8.31~9.2(3일), #1T/L : 9.3~4(2일) 1. 구 간 : 154kV 원흥-수색T/L No.12∼14 2. 지지물 : 설치 1기(관형주) / 철거 1기(4각철탑) 3. 전력선 교체(용량증대) : HSTACIR 330㎟ (0.752km)","2016-08-29 09:00","2016-08-30 18:00","2016-08-29T09:00:00","2016-08-30T18:00:00","연속",null,null,null,201606160060]
[8,"경기북부","파주","원흥수색#2 T/L","154kV 원흥수색T/L No.13 지장송전선로 이설공사","#1T/L : 8.29~30(2일), #2T/L : 8.31~9.2(3일), #1T/L : 9.3~4(2일) 1. 구 간 : 154kV 원흥-수색T/L No.12∼14 2. 지지물 : 설치 1기(관형주) / 철거 1기(4각철탑) 3. 전력선 교체(용량증대) : HSTACIR 330㎟ (0.752km)","2016-08-31 09:00","2016-09-02 18:00","2016-08-31T09:00:00","2016-09-02T18:00:00","연속",null,null,null,201606160062]
[9,"경기","평택","송탄오성CC#1 T/L","송탄S/S 170kV 장기사용 GIS 대체공사","송탄S/S 154kV 송탄-오성CC#1T/L GIS 대체","2016-08-20 09:00","2016-09-07 18:00","2016-08-20T09:00:00","2016-09-07T18:00:00","당일",null,null,null,201606230116]
[10,"강원","동해","삼척GP S/S 154KV #61 BUS","삼척GP S/Y 154kV 삼척LNG T/L 신규수용공사","삼척LNG T/L 신규수용 154kV GIS 1CCT 증설 및 부대공사","2016-08-01 09:00","2016-08-05 18:00","2016-08-01 09:00","2016-08-05 18:00","연속",null,null,null,201606210065]
[11,"강원","동해","삼척GP S/S 154KV #66 BUS","삼척GP S/Y 154kV 삼척LNG T/L 신규수용공사","삼척LNG T/L 신규수용 154kV GIS 1CCT 증설 및 부대공사","2016-08-08 09:00","2016-08-12 18:00","2016-08-08 09:00","2016-08-12 18:00","연속",null,null,null,201606210066]
[12,"충북","직할","음성금왕#2 T/L","변전설비 취약개소 설비보강(금왕SS_음성금왕#2T/L)","금왕S/S 154kV 음성금왕#2 T/L LINE ES 조작불가 메카니즘부 점검","2016-08-23 10:00","2016-08-23 18:00","2016-08-23 10:00","2016-08-23 18:00","당일",null,null,null,201605230013]
[13,"충북","직할","점촌단양 T/L","16년 직할 변전협력회사 총액공사","단양S/S 154kV 점촌단양T/L 차단기 보통점검","2016-08-25 10:00","2016-08-25 18:00","2016-08-25 10:00","2016-08-25 18:00","당일",null,null,"취소예정",201606240074]
[14,"충북","직할","신제천영월CC#1 T/L","345kV 신제천S/S GIS화 공사","신제천-영월CC#1T/L 인출변경","2016-08-23 08:00","2016-08-23 18:00","2016-08-08 08:00","2016-08-10 18:00","당일",null,null,null,201606220066]
[15,"충북","직할","신제천남원주#1 T/L","345kV 신제천S/S GIS화 공사","신제천-남원주#1T/L 인출변경","2016-08-24 08:00","2016-08-24 18:00","2016-08-19 08:00","2016-08-21 18:00","당일",null,null,null,201606220067]
[16,"충북","직할","신제천왕암#1 T/L","345kV 신제천S/S GIS화 공사","신제천-왕암#1T/L 인출변경","2016-08-25 08:00","2016-08-25 18:00","취소","취소","당일",null,null,null,201606220068]
[17,"충북","직할","신제천주진#2 T/L","345kV 신제천S/S GIS화 공사","신제천-주진#2T/L 인출변경","2016-08-26 08:00","2016-08-31 18:00","2016-08-25 08:00","2016-08-30 18:00","연속",null,null,null,201606220069]
[18,"충북","직할","신제천제천#1 T/L","신제천S/S GIS화 공사","신제천제천#1T/L GIS 연결","2016-08-08 08:00","2016-08-08 18:00","2016-08-16 08:00","2016-08-18 18:00","당일",null,null,null,201606210069]
[19,"대전충남","아산","장재천안#1 T/L","154kV 장재-천안T/L 지장선로 일부지중화 임시선로 설치공사","154kV 장재-천안T/L 지장선로 일부지중화 임시선로 설치공사 - 5기 설치 가선로 구성","2016-08-18 07:00","2016-08-22 18:00","2016-08-18T07:00:00","2016-08-22T18:00:00","연속",null,null,null,201606280100]
[20,"대전충남","아산","장재천안#1 T/L","154kV 장재-천안T/L 지장선로 일부지중화 임시선로 설치공사","154kV 장재-천안T/L 지장선로 일부지중화 임시선로 설치공사 - 5기 설치 가선로 구성","2016-08-01 07:00","2016-08-12 18:00","2016-08-01T07:00:00","2016-08-12T18:00:00","연속",null,null,null,201606280098]
[21,"대전충남","아산","장재천안#2 T/L","154kV 장재-천안T/L 지장선로 일부지중화 임시선로 설치공사","154kV 장재-천안T/L 지장선로 일부지중화 임시선로 설치공사 - 5기 설치 가선로 구성","2016-08-13 07:00","2016-08-17 18:00","2016-08-13T07:00:00","2016-08-17T18:00:00","연속",null,null,null,201606280099]
[22,"전북","군산","군공군산CC#1 T/L","154kV 군공-군산복합T/L 지장 지중선로 이설공사","군장(동백)대교 건설관련 지장물 이설","2016-08-31 08:00","2016-09-20 18:00","취소","취소","연속",null,null,"계통안정",201606170001]
[23,"전북","군산","군산S/S 154kV #3 BUS TIE CB","군산S/S 154kV #3 BUS TIE CB","군산S/S 154kV 62-67 모선보호반 대체공사","2016-08-08 09:00","2016-08-12 18:00","2016-08-08 09:00","2016-08-12 18:00","연속",null,null,null,201606090008]
[24,"전북","군산","군산S/S 66-67-0 SEC CB","군산S/S 66-67-0 SEC CB","군산S/S 154kV 62-67 모선보호반 대체공사","2016-08-08 09:00","2016-08-12 18:00","2016-08-08 09:00","2016-08-12 18:00","연속",null,null,null,201606090053]
[25,"전북","군산","군산S/S 61-62-0 SEC CB","군산S/S 61-62-0 SEC CB","군산S/S 154kV 62-67 모선보호반 대체공사","2016-08-08 09:00","2016-08-12 18:00","2016-08-08 09:00","2016-08-12 18:00","연속",null,null,null,201606090052]
[26,"전북","군산","군산동군산#1 T/L","군산동군산#1 T/L","154kV 군산-동군산#1T/L 보호배전반 대체","2016-08-16 09:00","2016-08-19 18:00","2016-08-16 09:00","2016-08-19 18:00","연속",null,null,null,201606090067]
[27,"전북","군산","군산동군산#2 T/L","군산동군산#2 T/L","154kV 군산-동군산#2T/L 보호배전반 대체","2016-08-22 09:00","2016-08-26 18:00","2016-08-22 09:00","2016-08-26 18:00","연속",null,null,null,201606090068]
[28,"전북","군산","이리S/S 154kV #2 BUS","이리S/S 154kV #2 BUS","1. 이리S/S 154kV 과열발생개소 긴급점검","2016-08-02 13:30","2016-08-02 18:00","2016-08-02 13:30","2016-08-02 18:00","당일",null,null,null,201606230005]
[29,"전북","군산","이리S/S 154kV #1 BUS TIE CB","이리S/S 154kV #1 BUS TIE CB","1. 이리S/S 154kV 과열발생개소 긴급점검","2016-08-02 09:00","2016-08-02 18:00","2016-08-02 09:00","2016-08-02 18:00","당일",null,null,null,201606230003]
[30,"전북","군산","이리S/S 154kV #1 BUS","이리S/S 154kV #1 BUS","1. 이리S/S 154kV 과열발생개소 긴급점검","2016-08-02 09:00","2016-08-02 13:30","2016-08-02 09:00","2016-08-02 13:30","당일",null,null,null,201606230004]
[31,"전북","김제","정주고창#1 T/L","정주고창#1 T/L","고창S/S #2 BUS 시험가압","2016-08-03 11:00","2016-08-03 13:00","2016-08-03 11:00","2016-08-03 13:00","당일",null,null,null,201606190007]
[32,"전북","김제","정주고창#1 T/L","정주고창#1 T/L","고창S/S #1 BUS 시험가압","2016-08-02 11:00","2016-08-02 13:00","2016-08-02 11:00","2016-08-02 13:00","당일",null,null,null,201606190006]
[33,"광주전남","강진","강진남창#1 T/L","154kV 강진-남창#1T/L(차단기 대쉬볼트 오링교체)","2016~17년도 강진전력지사 변전협력회사 총액공사 - 8. 1 : 남창S/S 강진-남창#1T/L C상 대쉬볼트부위 누유로 오링교체","2016-08-01 09:00","2016-08-01 18:00","취소","취소","당일",null,null,"한전요청",201606130203]
[34,"광주전남","순천","여수TP화치#2 T/L","154kV 화치S/S 금호미쓰이화학T/L 신규수용공사","#66BUS측 모선 및 DS 증설구간 여수TP-화치#2T/L을 통한 48시간 무부하가압","2016-08-26 15:00","2016-08-28 15:00","2016-08-26 15:00","2016-08-28 15:00","연속",null,null,null,201606090180]
[35,"광주전남","순천","여수TP화치#2 T/L","154kV 화치S/S 금호미쓰이화학T/L 신규수용공사","#61BUS측 모선 및 DS 증설구간 여수TP-화치#2T/L을 통한 48시간 무부하가압","2016-08-31 15:00","2016-09-02 15:00","2016-08-31 15:00","2016-09-02 15:00","연속",null,null,null,201606090181]
[36,"부산울산","울산","효문방어진 T/L","154kV 방어진S/S 용량부족 차단기 대체공사","154kV 방어진S/S 용량부족 차단기 대체공사 관련 안전이격 확보","2016-08-01 09:00","2016-08-01 14:00","2016-08-01 09:00","2016-08-01 14:00","당일",null,null,null,201606130018]
[37,"부산울산","울산","방어진영남TP#1 T/L","154kV 방어진S/S 용량부족 차단기 대체공사","154kV 방어진S/S 용량부족 차단기 대체공사 관련 #1BUS 시험가압 선로","2016-08-03 08:00","2016-08-05 08:00","2016-08-03 08:00","2016-08-05 08:00","연속",null,null,null,201606130021]
[38,"부산울산","울산","효문방어진 T/L","154kV 방어진S/S 용량부족 차단기 대체공사","154kV 방어진S/S 용량부족 차단기 대체공사 관련 안전이격 확보","2016-08-05 09:00","2016-08-05 14:00","2016-08-05 09:00","2016-08-05 14:00","당일",null,null,null,201606130020]
[39,"부산울산","울산","방어진영남TP#1 T/L","154kV 방어진S/S 용량부족 차단기 대체공사","154kV 방어진S/S 용량부족 차단기 대체공사 관련 #1DS 시험가압 선로","2016-08-12 18:00","2016-08-14 18:00","2016-08-12 18:00","2016-08-14 18:00","연속",null,null,null,201606130022]
[40,"부산울산","울산","방어진영남TP#2 T/L","154kV 방어진S/S 용량부족 차단기 대체공사","154kV 방어진S/S 용량부족 차단기 대체공사 관련 #2BUS 시험가압 선로","2016-08-14 18:00","2016-08-14 20:00","2016-08-14 18:00","2016-08-14 20:00","당일",null,null,null,201606130024]
[41,"부산울산","울산","방어진영남TP#2 T/L","154kV 방어진S/S 용량부족 차단기 대체공사","154kV 방어진S/S 용량부족 차단기 대체공사 관련 #2BUS 시험가압 선로","2016-08-07 08:00","2016-08-09 08:00","2016-08-07 08:00","2016-08-09 08:00","연속",null,null,null,201606130023]

{"sheet":"한수원","index":3,"n_rows":19,"n_cols":20,"rows_kept":19,"cut":false,"hidden":false,"merged":[[0,0,0,7],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,19,3,19],[9,0,10,0],[9,1,10,1],[9,2,10,2],[9,3,10,3],[9,4,10,4],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,14,3,14],[9,12,10,12],[2,15,3,15],[2,16,3,16],[2,17,3,17],[2,18,3,18],[9,5,10,5],[9,6,9,7],[9,8,9,9],[9,10,10,10],[9,11,10,11],[9,19,10,19],[15,0,15,1],[16,0,17,0],[16,1,17,1],[16,2,17,2],[16,3,17,3],[16,4,17,4],[16,5,17,5],[16,6,16,7],[16,8,16,9],[9,13,10,13],[9,14,10,14],[9,15,10,15],[9,16,10,16],[9,17,10,17],[9,18,10,18],[16,16,17,16],[16,17,17,17],[16,18,17,18],[16,19,17,19],[16,10,17,10],[16,11,17,11],[16,12,17,12],[16,13,17,13],[16,14,17,14],[16,15,17,15]]}
["2016년도 8월 월간휴전계획표(한국수력원자력)"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"고리본부","신고리1발","#2 주변압기","2호기 3차 계획예방정비\n*조작차단기 : PCB 8100, 8171","○ 전력용변압기 일반점검 및 구내 선로 점검, 보호계전기 시험등","2016-07-30 10:00","2016-08-22 10:00","2016-07-30 10:00","2016-08-22 10:00","연속","Y",null,null,null,"N","N","Y","N","Y"]
[2,"고리본부","신고리1발","#2 주변압기","2호기 3차 계획예방정비\n*조작차단기 : PCB 8100, 8171","○ 소내 전원절체(UAT -> SAT) 시험 후 차단기 재투입","2016-08-31 10:00","2016-08-31 18:00","2016-08-31 10:00","2016-08-31 18:00","당일","Y",null,null,null,"N","N","Y","N","Y"]
[]
[]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"고리","1발전소","신울산-고리NP #1T/L","고리2호기 28차 계획예방정비","고리2호기 주변압기 및 소내보조변압기 점검","2016-08-17T09:00:00","2015-08-25T10:00:00","2016-08-17T09:00:00","2015-08-25T10:00:00","연속","Y",null,null,null,"N","N","Y","N","Y"]
[]
[]
[]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"고리본부","신고리1발","#2 SAT","2호기 3차 계획예방정비\n*조작 차단기 : PCB 6271, 6200","○ 대기보조변압기 일반점검 및 보호계전기 시험등\n○ 154kV SWYD 차단기 정밀점검\n(6271, 6200)","2016-8-22-10:00","2016-8-31-18:00","2016-8-22-10:00","2016-8-31-18:00","연속","Y",null,null,null,"N","N","N","N","Y"]