{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["765송부","345송부","154송부","Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":15,"n_cols":16,"rows_kept":15,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2016년도 9월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #4 M.Tr A-1","신가평S/S #4 M.Tr 냉각장치 회로개선","765kV M.Tr 냉각장치 회로개선","2016-09-29 09:00","2016-09-30 18:00","2016-09-29 09:00","2016-09-30 18:00","연속",null,null,null,201606170068]
[2,"경기북부","구리","신가평S/S #3 M.Tr A-1","신가평S/S #3 M.Tr 냉각장치 회로개선","765kV M.Tr 냉각장치 회로개선","2016-09-26 09:00","2016-09-28 18:00","2016-09-26 09:00","2016-09-28 18:00","연속",null,null,null,201606170067]
[3,"경기북부","구리","신가평S/S #2 M.Tr A-1","신가평S/S #2 M.Tr 냉각장치 회로개선","765kV M.Tr 냉각장치 회로개선","2016-09-21 09:00","2016-09-23 18:00","2016-09-21 09:00","2016-09-23 18:00","연속",null,null,null,201606170065]
[4,"강원","태백","신태백S/S #4 M.Tr A-1","신태백S/S 362kV GIS 정밀점검공사","7761DS, 7701DS, 7721DS 점검","2016-09-01 09:00","2016-09-03 18:00","2016-09-01 09:00","2016-09-03 18:00","연속",null,null,null,201607060097]
[5,"강원","태백","신태백S/S #2 M.Tr A-1","2016년 신태백S/S 765kV 주변압기 정밀점검 공사","○ 765/345kV #2M.Tr 정밀점검공사 ○ 800kV 8372CB GIS 정밀점검공사","2016-09-05 09:00","2016-11-06 18:00","2016-09-05 09:00","2016-11-06 18:00","연속",null,null,null,201607060073]
[6,"대전충남","서산","당진T/P 5호기 1차 CB","2016년 서산P/O 765/345kV GIS 점검공사","○765kV GIS 보통점검","2016-09-05 09:00","2016-09-06 18:00","2016-09-05 09:00","2016-09-06 18:00","연속",null,null,null,201602140085]
[7,"대전충남","서산","신서산S/S 신서산신안성#1T/L-# M.Tr 1차CB","2016년 서산P/O 765/345kV GIS 점검공사","○765kV GIS 보통점검","2016-09-09 09:00","2016-09-10 18:00","2016-09-09 09:00","2016-09-10 18:00","연속",null,null,null,201607120160]
[8,"대전충남","서산","신서산S/S #4 M.Tr 1차 CB","2016년 서산P/O 765/345kV GIS 점검공사","○765kV GIS 보통점검","2016-09-07 09:00","2016-09-08 18:00","2016-09-07 09:00","2016-09-08 18:00","연속",null,null,null,201607120159]
[9,"부산울산","동부산","신고리S/S #1 M.Tr A-1","신고리S/S #1M.Tr 오경보관련 RCP 내부부품 전량교체","신고리S/S #1M.Tr 오경보관련 RCP 내부부품 전량교체","2016-09-26 09:00","2016-09-30 18:00","2016-09-26 09:00","2016-09-30 18:00","연속",null,null,null,201607150066]
[10,"부산울산","동부산","신고리S/S #2 M.Tr A-1","신고리S/S 800kV GIS 보통점검 공사","신고리S/S 800kV 8671, 8600 GIS 보통점검(#2M.Tr 휴전)","2016-09-19 09:00","2016-09-23 18:00","2016-09-19 09:00","2016-09-23 18:00","연속",null,null,null,201607110514]
[11,"경남","함안","북경남S/S 북경남-신고리NP #2T/L CB","800kV GIS 차단기 내부이너노즐 교체공사","-8571 CB 내부 이너노즐(6EA) 교체","2016-09-01 08:00","2016-09-07 18:00","2016-09-01 08:00","2016-09-07 18:00","연속",null,null,null,201607050066]

{"sheet":"345송부","index":1,"n_rows":174,"n_cols":16,"rows_kept":174,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2016년도 9월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","미금성동#3 T/L","345kV 성동S/S 장기사용 모자익반 교체공사","345kV 성동S/S 장기사용 모자익반 교체공사","2016-09-03 09:00","2016-09-13 18:00","2016-09-03 09:00","2016-09-13 18:00","연속",null,null,null,201607190140]
[2,"서울","성동","성동S/S #4 M.Tr A","345kV 성동S/S 장기사용 모자익반 교체공사","345kV 성동S/S 장기사용 모자익반 교체공사","2016-09-03 09:00","2016-09-13 18:00","2016-09-03 09:00","2016-09-13 18:00","연속",null,null,null,201607190141]
[3,"서울","성동","성동S/S 345kV #1Sh.R","345kV 성동S/S 장기사용 모자익반 교체공사","345kV 성동S/S 장기사용 모자익반 교체공사","2016-09-19 09:00","2016-09-23 18:00","2016-09-19 09:00","2016-09-23 18:00","연속",null,null,null,201607190142]
[4,"서울","성동","성동S/S 345kV #2Sh.R","345kV 성동S/S 장기사용 모자익반 교체공사","345kV 성동S/S 장기사용 모자익반 교체공사","2016-09-26 09:00","2016-09-30 18:00","2016-09-26 09:00","2016-09-30 18:00","연속",null,null,null,201607190143]
[5,"남서울","강남","신양재S/S #1 M.Tr 1차 CB (7172)","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","2016-09-26 09:00","2016-09-28 18:00","2016-09-26 09:00","2016-09-28 18:00","연속",null,null,null,201607110043]
[6,"남서울","강남","신양재S/S 345kV #2 BUS","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","2016-09-28 09:00","2016-09-29 18:00","2016-09-28 09:00","2016-09-29 18:00","연속",null,null,null,201607110045]
[7,"남서울","동서울","곤지암동서울#1 T/L","345kV GIS 정밀점검","345kV GIS 정밀점검 - 곤지암-동서울#1 T/L","2016-09-19 09:00","2016-09-23 18:00","2016-09-19 09:00","2016-09-23 18:00","연속",null,null,null,201607120144]
[8,"남서울","동서울","동서울S/S 345kV #70 BUS","362kV GIS 정밀점검","362kV GIS 정밀점검 관련 곤지암-동서울#1T/L 모선측 DS 점검 362kV 70-71 SEC CB 보통점검","2016-09-19 09:00","2016-09-20 18:00","2016-09-19 09:00","2016-09-20 18:00","연속",null,null,null,201607150024]
[9,"남서울","동서울","동서울S/S 345kV #75 BUS","362kV GIS 정밀점검","362kV GIS 정밀점검 관련 곤지암-미금#1T/L 모선측 DS 점검 362kV 75-76 SEC CB 보통점검","2016-09-26 09:00","2016-09-27 18:00","2016-09-26 09:00","2016-09-27 18:00","연속",null,null,null,201607150025]
[10,"남서울","동서울","동서울미금#1 T/L","345kV GIS 정밀점검","345kV GIS 정밀점검 - 동서울-미금#1 T/L","2016-09-26 09:00","2016-09-30 18:00","2016-09-26 09:00","2016-09-30 18:00","연속",null,null,null,201607120146]
[11,"남서울","동서울","동서울S/S 75-76-0 SEC CB (75-76-0)","345kV GIS 보통점검","345kV GIS 보통점검 - 동서울S/S 75-76-0 SEC","2016-09-26 09:00","2016-09-27 18:00","2016-09-26 09:00","2016-09-27 18:00","당일",null,null,null,201607120141]
[12,"남서울","동서울","동서울S/S 70-71-0 SEC CB (70-71-0)","345kV GIS 보통점검","345kV GIS 보통점검 - 동서울S/S 70-71-0 SEC","2016-09-19 09:00","2016-09-20 18:00","2016-09-19 09:00","2016-09-20 18:00","당일",null,null,null,201607120140]
[13,"남서울","동서울","곤지암-동서울#1T/L-동서울-미금#1T/L CB (7100)","345kV GIS 정밀점검","345kV GIS 정밀점검 - 7100 BUS-TIE - 차단기 점검(9/24~25)","2016-09-19 09:00","2016-09-30 18:00","2016-09-19 09:00","2016-09-30 18:00","연속",null,null,null,201607120151]
[14,"인천","김포","345kV신김포S/S #1 M.Tr 1차 GIS","345kV신김포S/S #1 M.Tr 1차 GIS","7372 CB 불량 Accumulator 교체 작업 (현대중공업)","2016-09-01 09:00","2016-09-02 18:00","2016-09-01 09:00","2016-09-02 18:00","연속",null,null,null,201606290011]
[15,"인천","김포","신김포S/S 345KV 70-71 SEC","신김포S/S 345KV 70-71 SEC","70-71 CB 불량 Accumulator 교체 작업 (현대중공업)","2016-09-05 09:00","2016-09-06 18:00","2016-09-05 09:00","2016-09-06 18:00","연속",null,null,null,201606290012]
[16,"인천","김포","신김포S/S 345KV 75-76 SEC","신김포S/S 345KV 75-76 SEC","75-76 CB 불량 Accumulator 교체 작업 (현대중공업)","2016-09-07 09:00","2016-09-08 18:00","2016-09-07 09:00","2016-09-08 18:00","연속",null,null,null,201606290013]
[17,"인천","김포","345kV신김포S/S 신김포 - 신파주#1T/L GIS","345kV신김포S/S 신김포 - 신파주#1T/L GIS","7371 CB 불량 Accumulator 교체 작업 (현대중공업)","2016-09-29 09:00","2016-09-30 18:00","2016-09-29 09:00","2016-09-30 18:00","연속",null,null,null,201606290018]
[18,"인천","김포","신김포S/S 345KV 신김포-신인천T/L TIE","신김포S/S 345KV 신김포-신인천T/L TIE","7400 CB 불량 Accumulator 교체 작업 (현대중공업)","2016-09-22 09:00","2016-09-23 18:00","2016-09-22 09:00","2016-09-23 18:00","연속",null,null,null,201606290016]
[19,"인천","김포","신김포S/S 345KV 신김포-신파주#2T/L TIE","신김포S/S 345KV 신김포-신파주#2T/L TIE","7500 CB 불량 Accumulator 교체 작업 (현대중공업)","2016-09-27 09:00","2016-09-28 18:00","2016-09-27 09:00","2016-09-28 18:00","연속",null,null,null,201606290017]
[20,"인천","김포","신김포S/S 345KV 신김포 -신파주#1T/L TIE","신김포S/S 345KV 신김포 -신파주#1T/L TIE","7300 CB 불량 Accumulator 교체 작업 (현대중공업)","2016-09-20 09:00","2016-09-21 18:00","2016-09-20 09:00","2016-09-21 18:00","연속",null,null,null,201606290015]
[21,"인천","시흥","신시흥#1S/S #2 M.Tr A","신시흥#2S/S #2M.Tr B상 2차 부싱 과열개소 보수","신시흥#2S/S #2M.Tr B상 2차 부싱 과열개소 보수","2016-09-07 09:30","2016-09-07 18:00","2016-09-07 09:30","2016-09-07 18:00","연속",null,null,null,201607070154]
[22,"인천","시흥","신시흥#1S/S #1 M.Tr A","신시흥#1S/S #1 M.Tr C상 GPT 교체공사","신시흥#1S/S #1 M.Tr C상 GPT 교체공사","2016-09-21 09:30","2016-09-21 18:00","2016-09-21 09:30","2016-09-21 18:00","연속",null,null,null,201607080091]
[23,"인천","시흥","신시흥#1S/S #3 M.Tr 1차 GIS","신시흥#1S/S #3 M.Tr 1차 GIS(7872) 정밀점검","신시흥#1S/S #3 M.Tr 1차 GIS(7872) 정밀점검","2016-09-29 09:00","2016-10-01 18:00","2016-09-29 09:00","2016-10-01 18:00","연속",null,null,null,201607080195]
[24,"인천","시흥","신시흥#2S/S #5M.Tr A","신시흥#2S/S #5M.Tr 과열개소 보수","신시흥#2S/S #5M.Tr 과열개소 보수","2016-09-20 09:30","2016-09-20 18:00","2016-09-20 09:30","2016-09-20 18:00","연속",null,null,null,201607080089]
[25,"인천","시흥","신시흥#2S/S #6M.Tr A","신시흥#2S/S #6M.Tr A상 OFU 필터 교체 및 누유보수","신시흥#2S/S #6M.Tr A상 OFU 필터 교체 및 누유보수","2016-09-02 09:30","2016-09-02 18:00","2016-09-02 09:30","2016-09-02 18:00","당일",null,null,null,201607070153]
[26,"인천","시흥","신시흥#2S/S #4 M.Tr A","신시흥S/S #4M.Tr 과열개소 보수","신시흥S/S #4M.Tr 과열개소 보수","2016-09-19 10:00","2016-09-19 18:00","2016-09-19 10:00","2016-09-19 18:00","당일",null,null,null,201607080087]
[27,"인천","시흥","신시흥#2S/S #4 M.Tr 1차 GIS","신시흥#2S/S #4 M.Tr 1차 GIS(7672) 정밀점검","신시흥#2S/S #4 M.Tr 1차 GIS(7672) 정밀점검","2016-09-26 09:00","2016-09-28 18:00","2016-09-26 09:00","2016-09-28 18:00","연속",null,null,null,201607080193]
[28,"인천","시흥","영흥T/P 신시흥영흥TP#2T/L-#3G/T 1차 CB (7400)","영흥T/P 신시흥영흥TP#2T/L-#3G/T 1차 (7400) 정밀점검","영흥T/P 신시흥영흥TP#2T/L-#3G/T 1차 (7400) 정밀점검","2016-09-19 09:00","2016-09-21 18:00","2016-09-19 09:00","2016-09-21 18:00","연속",null,null,null,201607080103]
[29,"인천","시흥","신시흥영흥TP#3 T/L","345kV 영흥T/L 송전선로용 피뢰기 설치공사","345kV 영흥T/L 송전선로용 피뢰기 설치(74기)","2016-09-05 09:00","2016-09-08 18:00","취소","취소","매일",null,null,"계통안정",201606290034]
[30,"인천","시흥","신시흥영흥TP#1 T/L","345kV 영흥T/L 송전선로용 피뢰기 설치공사","345kV 영흥T/L 송전선로용 피뢰기 설치(74기)","2016-09-05 09:00","2016-09-09 18:00","취소","취소","매일",null,null,"계통안정",201606290033]
[31,"인천","시흥","영흥TP연락#2 T/L","345kV 영흥T/L 송전선로용 피뢰기 설치공사","345kV 영흥T/L 송전선로용 피뢰기 설치(74기)","2016-09-09 09:00","2016-09-09 18:00","취소","취소","당일",null,null,"계통안정",201607190055]
[32,"인천","시흥","영흥T/P #3 M.Tr(G.T) 1차 CB (7472)","영흥T/P #3 M.Tr(G.T) 1차 CB (7472) 정밀점검","영흥T/P #3 M.Tr(G.T) 1차 CB (7472) 정밀점검","2016-09-22 09:00","2016-09-24 18:00","2016-09-22 09:00","2016-09-24 18:00","연속",null,null,null,201607080105]
[33,"인천","인천","서인천C/C #3 M.Tr 1차 CB (7372)","서인천C/C #3 M.Tr 1차 GIS(7372) 초기점검","서인천C/C #3 M.Tr 1차 GIS(7372) 초기점검","2016-09-05 09:00","2016-09-05 18:00","2016-09-05 09:00","2016-09-05 18:00","당일",null,null,null,201607130064]
[34,"인천","인천","서인천C/C #2 M.Tr 1차 CB (7272)","서인천C/C #2M.Tr 1차 GIS(7272) 초기점검","서인천C/C #2M.Tr 1차 GIS(7272) 초기점검","2016-09-02 09:00","2016-09-02 18:00","2016-09-02 09:00","2016-09-02 18:00","당일",null,null,null,201607130062]
[35,"인천","인천","서인천C/C 신경서서인천CCT/L-#2 M.Tr 1차 (7200)","서인천C/C #2M.Tr 1차 GIS(7200) 초기점검","서인천C/C #2M.Tr 1차 GIS(7200) 초기점검","2016-09-01 09:00","2016-09-01 18:00","2016-09-01 09:00","2016-09-01 18:00","당일",null,null,null,201607130061]
[36,"인천","인천","신가좌신시흥#2 T/L","피뢰기 설치공사(가공송전정비 협력회사 총액공사)","송전철탑 피뢰기 설치","2016-09-19 08:00","2016-09-25 18:00","2016-09-19 08:00","2016-09-25 18:00","매일",null,null,null,201607150181]
[37,"인천","인천","신가좌가정#2 T/L","피뢰기 설치공사(가공송전정비 협력회사 총액공사)","송전철탑 피뢰기 설치","2016-09-26 08:00","2016-09-28 18:00","2016-09-26 08:00","2016-09-28 18:00","매일",null,null,null,201607150182]
[38,"인천","인천","신경서S/S 서인천서인천CCT/L CB (7472)","신경서S/S 신경서인천CCT/L GIS(7472) 초기점검","신경서S/S 신경서인천CCT/L GIS(7472) 초기점검","2016-09-09 09:00","2016-09-09 18:00","2016-09-09 09:00","2016-09-09 18:00","당일",null,null,null,201607130072]
[39,"인천","인천","신경서S/S 신경서서인천CCT/L-TIE CB (7400)","신경서S/S 신경서인천CCT/L-TIE GIS(7400) 초기점검","신경서S/S 신경서인천CCT/L-TIE GIS(7400) 초기점검","2016-09-08 09:00","2016-09-08 18:00","2016-09-08 09:00","2016-09-08 18:00","당일",null,null,null,201607130071]
[40,"인천","인천","신경서S/S 서인천인천CC#2T/L CB (7372)","신경서S/S 신경서인천CC #2T/L GIS(7372) 초기점검","신경서S/S 신경서인천CC #2T/L GIS(7372) 초기점검","2016-09-07 09:00","2016-09-07 18:00","2016-09-07 09:00","2016-09-07 18:00","당일",null,null,null,201607130069]
[41,"인천","인천","신인천C/C 345kV #77 BUS","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- 345kV #77BUS 개조 및 SEC-CB(76-77-0) 대체","2016-09-01 10:00","2016-09-30 17:00","2016-09-01 10:00","2016-09-30 17:00","연속",null,null,null,201607110445]
[42,"인천","인천","인천CC S/Y 포스코SY-인천CC#1T/L GIS","2016년 인천전력지사 362kV GIS 정밀점검 공사","인천복합S/Y 포스코SY인천CC#1T/L(7A71) GIS 정밀점검","2016-09-21 08:00","2016-09-23 18:00","2016-09-21 08:00","2016-09-23 18:00","연속",null,null,null,201606290055]
[43,"인천","인천","인천CC S/Y 포스코SY인천CC#1T/L-#2T/L GIS","2016년 인천전력지사 362kV GIS 정밀점검 공사","인천복합S/Y 포스코SY인천CC#1T/L-#2T/L(7A00) GIS 정밀점검","2016-09-26 08:00","2016-09-28 18:00","2016-09-26 08:00","2016-09-28 18:00","연속",null,null,null,201606290056]
[44,"인천","인천","인천CC S/Y 포스코SY인천CC#2T/L GIS","2016년 인천전력지사 362kV GIS 정밀점검 공사","인천복합S/Y 포스코SY인천CC#2T/L(7A72) GIS 정밀점검","2016-09-29 08:00","2016-10-01 18:00","2016-09-29 08:00","2016-10-01 18:00","연속",null,null,null,201606290058]
[45,"인천","직할","신부평S/S 345kV #1 BUS","신부평S/S 345kV 모선보호반 대체(#1BUS휴전)","신부평S/S 345kV 모선보호반 대체(#1BUS휴전)","2016-09-26 09:30","2016-09-30 18:00","2016-09-26 09:30","2016-09-30 18:00","연속",null,null,null,201607150093]
[46,"인천","직할","신부평S/S #3 M.Tr A","신부평S/S #3M.Tr 보호반 대체","신부평S/S #3M.Tr 보호반 대체","2016-09-19 09:30","2016-09-23 18:00","2016-09-19 09:30","2016-09-23 18:00","연속",null,null,null,201607150092]
[47,"인천","직할","신부평S/S #2 M.Tr A","신부평S/S #2M.Tr 보호반 대체","신부평S/S #2M.Tr 보호반 대체","2016-09-05 09:30","2016-09-09 18:00","2016-09-05 09:30","2016-09-09 18:00","연속",null,null,null,201607150091]
[48,"경기북부","구리","미금S/S #1 M.Tr A","미금S/S 345kV #1M.Tr 보호반 교체","미금S/S 345kV #1M.Tr 보호반 교체","2016-09-06 08:00","2016-09-09 18:00","2016-09-06 08:00","2016-09-09 18:00","연속",null,null,null,201607140049]
[49,"경기북부","구리","신가평S/S 345kV #4 Sh.R","신가평S/S 345kV #4Sh.R GIS 정밀점검","ㅇ신가평S/S 345kV #4Sh.R GIS 정밀점검 * 7679CB, 7621,7601DS","2016-09-26 09:30","2016-09-30 17:00","2016-09-26 09:30","2016-09-30 17:00","연속",null,null,null,201607080138]
[50,"경기북부","구리","신가평S/S 345kV #2 BUS","765kV 신가평S/S #1M.Tr 증설공사","○ 변압기 : 765kV 1,000MVA X 1Bank ○ 개폐장치 : 800kV X 2CB(1BAY), 362kV X 2CB(1BAY) ○ 보호배전반 설치 × 1식 ○ 제어케이블 포설 및 결선 × 1식 ○ 기초 및 접지시공 × 1식 ○ 기타 부대공사 × 1식","2016-09-12 09:00","2016-09-18 18:00","2016-09-12 09:00","2016-09-18 18:00","연속",null,null,null,201507170040]
[51,"경기북부","구리","신가평포천LNGCC#1 T/L","2016년 구리전력지사 362kV GIS 정밀점검 공사","신가평S/S 신가평포천LNGCC#1 T/L GIS 정밀점검 ㅇ 7400CB, 7402DS","2016-09-05 09:30","2016-09-07 17:00","2016-09-05 09:30","2016-09-07 17:00","연속",null,null,null,201607080122]
[52,"경기북부","구리","신가평S/S 345kV #1 BUS","765kV 신가평S/S #1M.Tr 증설공사","○ 변압기 : 765kV 1,000MVA X 1Bank ○ 개폐장치 : 800kV X 2CB(1BAY), 362kV X 2CB(1BAY) ○ 보호배전반 설치 × 1식 ○ 제어케이블 포설 및 결선 × 1식 ○ 기초 및 접지시공 × 1식 ○ 기타 부대공사 × 1식","2016-09-05 09:00","2016-09-11 18:00","2016-09-05 09:00","2016-09-11 18:00","연속",null,null,null,201507170039]
[53,"경기북부","구리","신가평S/S 345kV #3 Sh.R","신가평S/S 345kV #3Sh.R GIS 정밀점검","ㅇ신가평S/S 345kV #3Sh.R GIS 정밀점검 * 7479CB, 7421,7401DS","2016-09-19 09:30","2016-09-23 17:00","2016-09-19 09:30","2016-09-23 17:00","연속",null,null,null,201607080137]
[54,"경기북부","파주","신덕은S/S #2 M.Tr A","2016년 파주 변전협력 총액공사","345kV M.Tr 3차측 GPT 교체공사","2016-09-05 10:00","2016-09-09 18:00","2016-09-05 10:00","2016-09-09 18:00","연속",null,null,null,201606290094]
[55,"경기북부","파주","신덕은S/S #4 M.Tr A","2016년 파주 변전협력 총액공사","345kV M.Tr 3차측 GPT 교체공사","2016-09-01 10:00","2016-09-02 18:00","2016-09-01 10:00","2016-09-02 18:00","연속",null,null,null,201606290093]
[56,"경기북부","파주","신덕은S/S #3 M.Tr A","신덕은S/S #3M.Tr 2차 GIB 순환전류 저감공사","신덕은S/S #3M.Tr 2차 GIB 순환전류 저감을 위한 절연링 설치","2016-09-26 09:30","2016-09-28 18:00","2016-09-26 09:30","2016-09-28 18:00","연속",null,null,null,201607190126]
[57,"경기북부","파주","신파주S/S #2 M.Tr A","신파주S/S 154kV #2M.Tr 2차 GIS 정밀점검공사","신파주S/S 154kV #2M.Tr 2차 GIS 정밀점검공사","2016-09-29 09:00","2016-10-01 18:00","2016-09-29 09:00","2016-10-01 18:00","연속",null,null,null,201607140103]
[58,"경기북부","파주","신김포신파주#1 T/L","345kV 신김포-신파주TL 접속함 교체공사","- 대상선로 : 345kV 신김포-신파주#1TL - 교체대상 : J/B1~6, 9,10 등 8개소 48상 접속함 - 내용 : 접속함 교체(PJ Type --- PMJ Type 교체)","2016-09-01 09:00","2016-10-10 18:00","2016-09-24 09:00","2016-11-02 18:00","연속",null,null,"계통안정",201607110090]
[59,"경기북부","파주","신파주S/S #1 M.Tr A","신파주S/S 154kV #1M.Tr 2차 GIS 정밀점검공사","신파주S/S 154kV #1M.Tr 2차 GIS 정밀점검공사","2016-09-22 09:00","2016-09-24 18:00","2016-09-22 09:00","2016-09-24 18:00","연속",null,null,null,201607140102]
[60,"경기북부","파주","신파주양주#2 T/L","신파주S/S CLR 설치공사","1. 신김포-신파주#1T/L 3상GIB 설치 및 기타(근접작업) 2. CLR 설치 - 장비근접 작업으로 안전위한 휴전작업","2016-09-30 09:00","2016-10-05 18:00","2016-09-30 09:00","2016-10-05 18:00","연속",null,null,null,201607110428]
[61,"경기북부","파주","신파주양주#2 T/L","신파주S/S CLR 설치공사","1.신파주-신김포 #2T/L C상 WALL BUSHING 철거","2016-09-24 09:00","2016-09-24 18:00","2016-09-24 09:00","2016-09-24 18:00","당일",null,null,null,201607110416]
[62,"경기","동부","곤지암S/S #2 M.Tr A","16년 동부 변전협력회사 총액공사","곤지암S/S 345kV #1M.Tr OFU 필터교체","2016-09-02 09:00","2016-09-02 18:00","2016-09-02 09:00","2016-09-02 18:00","당일",null,null,null,201607140133]
[63,"경기","성남","서안성S/S 345kV #1 BUS","서안성S/S 345kV GIS 설치공사","345kV GIS 2CB 설치","2016-09-03 09:00","2016-09-11 18:00","2016-09-03 09:00","2016-09-11 18:00","연속",null,null,null,201607060168]
[64,"경기","성남","신안성서안성#2 T/L","서안성S/S 345kV GIS 설치공사","345kV GIS 2CB 설치","2016-09-03 09:00","2016-09-05 18:00","2016-09-03 09:00","2016-09-05 18:00","연속",null,null,null,201607060166]
[65,"경기","성남","서안성S/S 345kV #2 BUS","서안성S/S 345kV GIS 설치공사","345kV GIS 2CB 설치","2016-09-20 09:00","2016-09-28 18:00","2016-09-20 09:00","2016-09-28 18:00","연속",null,null,null,201607060173]
[66,"경기","성남","서안성S/S #3 M.Tr A","서안성S/S 345kV 및 154kV GIS 설치공사","345kV GIS 2CB 설치 154kV GIS 4CCT 설치","2016-09-20 09:00","2016-09-24 18:00","2016-09-20 09:00","2016-09-24 18:00","연속",null,null,null,201607060171]
[67,"경기","성남","신안성S/S #5 M.Tr 2차 CB (7C71)","신안성S/S 345kV 7C71 GIS 정밀점검","신안성S/S 345kV 7C71 GIS 정밀점검, 보조계전기교체","2016-09-27 09:00","2016-09-29 18:00","2016-09-27 09:00","2016-09-29 18:00","연속",null,null,null,201607110172]
[68,"경기","성남","신용인신수원 T/L","345kV 신용인S/S 용량부족 GIS 대체공사","345kV 신용인-신수원T/L 인출변경 345kV GIS (63kA 6300A)설치 * 2CB 용량대체","2016-09-01 09:00","2016-09-08 18:00","2016-09-01 09:00","2016-09-08 18:00","연속",null,null,null,201601140110]
[69,"경기","성남","신용인S/S 345kV #1 BUS","345kV 신용인S/S 용량부족 GIS 대체공사","345kV 모선 및 모선DS GIS 용량대체","2016-09-09 09:00","2016-10-23 18:00","2016-09-09 09:00","2016-10-23 18:00","연속",null,null,null,201601140112]
[70,"경기","성남","신용인S/S #1 M.Tr A","신용인S/S 154kV #1M.Tr 2차 GIS 정밀점검","신용인S/S 154kV #1M.Tr 2차 GIS 정밀점검","2016-09-08 09:00","2016-09-10 18:00","2016-09-08 09:00","2016-09-10 18:00","연속",null,null,null,201607250018]
[71,"강원","강릉","신양양S/S 345kV #1 BUS","2016년-17년 변전협력회사 총액공사","1. 345kV #1BUS PT GIS 보통점검 2. 모선보호반 점검(계통시험)","2016-09-12 09:00","2016-09-12 14:00","2016-09-12 09:00","2016-09-12 14:00","당일",null,null,null,201607070127]
[72,"강원","강릉","신양양S/S 345kV #2 BUS","2016년-17년 변전협력회사 총액공사","1. 345kV #2BUS PT GIS 보통점검 2. 모선보호반 점검(계통시험)","2016-09-12 14:00","2016-09-12 18:00","2016-09-12 14:00","2016-09-12 18:00","당일",null,null,null,201607070128]
[73,"강원","동해","동해S/S #3 M.Tr A","동해S/S 취약설비 GIS화 공사","- 154kV 한라T/L 옥외 설비(CB,DS,BUS) 철거 및 #3M.Tr 옥외설비(철구 및 BUS) 철거","2016-09-05 08:00","2016-09-05 18:00","2016-09-05 08:00","2016-09-05 18:00","당일",null,null,null,201607040018]
[74,"강원","태백","신태백S/S #4 M.Tr 2차 CB (7771)","신태백S/S 362kV GIS 정밀점검공사","7771CB 정밀점검","2016-09-04 09:00","2016-09-09 18:00","2016-09-04 09:00","2016-09-09 18:00","연속",null,null,null,201607150121]
[75,"강원","태백","신태백S/S 345kV #1 BUS","신태백S/S 362kV GIS 정밀점검공사","7751DS 정밀점검","2016-09-08 09:00","2016-09-09 18:00","2016-09-08 09:00","2016-09-09 18:00","연속",null,null,null,201607060098]
[76,"강원","태백","신태백S/S#3 Sh.R-신태백-한울NP2#1T/L CB (7500)","신태백S/S 362kV GIS 정밀점검공사","7500CB 정밀점검","2016-09-26 09:00","2016-10-01 18:00","2016-09-26 09:00","2016-10-01 18:00","연속",null,null,null,201607150130]
[77,"강원","태백","신태백S/S 345kV #2 BUS","신태백S/S 362kV GIS 정밀점검공사","7752DS 정밀점검","2016-09-23 09:00","2016-09-24 18:00","2016-09-23 09:00","2016-09-24 18:00","연속",null,null,null,201607060099]
[78,"강원","태백","신태백S/S #4 M.Tr 2차-TIE CB (7700)","신태백S/S 362kV GIS 정밀점검공사","7700CB 정밀점검","2016-09-19 09:00","2016-09-24 18:00","2016-09-19 09:00","2016-09-24 18:00","연속",null,null,null,201607150125]
[79,"강원","태백","신태백한울NP2#1 T/L","신태백S/S 362kV GIS 정밀점검공사","7502DS 정밀점검","2016-09-30 09:00","2016-10-01 18:00","2016-09-30 09:00","2016-10-01 18:00","연속",null,null,null,201607060100]
[80,"충북","직할","신충주S/S #3 M.Tr A","신충주S/S 345kV #3M.Tr 냉각팬 하자관련 제작사 수리","신충주S/S 345kV #3M.Tr A,B,C상 냉각팬(72개) 고무패킹 불량 전량교체","2016-09-05 09:00","2016-09-05 18:00","2016-09-05 09:00","2016-09-05 18:00","당일",null,null,null,201606100285]
[81,"충북","직할","신제천S/S #3 M.Tr A","345kV 신제천S/S GIS화 공사","신제천-주진#2T/L 인출변경","2016-09-01 08:00","2016-09-05 18:00","2016-09-01 08:00","2016-09-05 18:00","연속",null,null,null,201607260092]
[82,"충북","청주","신옥천세종#2 T/L","세종변전소 창호교체 공사","세종변전소 인출 창호교체 3개소","2016-09-07 13:00","2016-09-07 18:00","2016-09-07 13:00","2016-09-07 18:00","당일",null,null,null,201607190052]
[83,"충북","청주","신옥천북경남 T/L","345kV 신옥천-북경남T/L 안전이격 확보공사","○ 철탑설치 및 철거 : 4기(No.354～357) ○ 전력선 교체 : 1.762km-2c(No.352～358), ACSR 480㎟ X 2B ○ OPGW 이설 : 1.762km-1조(No.352～358)","2016-09-18 08:00","2016-09-25 17:00","2016-09-18 08:00","2016-09-25 17:00","연속",null,null,null,201607190136]
[84,"충북","청주","신옥천세종#1 T/L","345kV 신옥천-청원TL 스페이서 간격조정공사","스페이서 간격조정(1400개)","2016-09-05 08:00","2016-09-06 12:00","2016-09-05 08:00","2016-09-06 12:00","매일",null,null,null,201607110173]
[85,"충북","청주","세종청원#2 T/L","세종변전소 창호교체 공사","세종변전소 인출 창호교체 3개소","2016-09-07 08:00","2016-09-07 13:00","2016-09-07 08:00","2016-09-07 13:00","당일",null,null,null,201607190048]
[86,"충북","청주","청원S/S #4 M.Tr A","16년 청주 변전협력회사 총액공사","청원S/S #4 M.Tr C상 누유 보수 및 3차 PT 초기점검","2016-09-02 10:00","2016-09-02 18:00","2016-09-02 10:00","2016-09-02 18:00","당일",null,null,null,201607110198]
[87,"충북","청주","청원S/S #1 M.Tr A","16년 청주 변전협력회사 총액공사","청원S/S #1 M.Tr 1차 GIS 보통점검","2016-09-08 10:00","2016-09-09 18:00","2016-09-08 10:00","2016-09-09 18:00","연속",null,null,null,201607110199]
[88,"충북","청주","신옥천청양 T/L","신옥천S/S 345kV 차단기 용량부족대체공사","1.포스트 및 빔 설치,조립 2.철구보강 및 기타작업","2016-09-19 09:00","2016-09-21 18:00","2016-09-19 09:00","2016-09-21 18:00","매일",null,null,null,201607110198]
[89,"충북","청주","신옥천S/S 345kV #2 BUS","345kV 신옥천S/S 용량부족차단기 대체공사","1. 설치공사시행 사전 안전이격확보 2. 가공지선 포스트 철거 및 가공지선 철거","2016-09-01 09:00","2016-09-01 18:00","2016-09-08 09:00","2016-09-08 18:00","당일",null,null,"계통안정",201607110199]
[90,"충북","충주","서안성신진천#2 T/L","2016년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검 (신진천S/T~35호)","2016-09-01 09:00","2016-09-02 18:00",null,null,"매일",null,null,"계통안정",201607060062]
[91,"충북","충주","신진천S/S #3 M.Tr 1차 CB (7672)","신진천S/S 용량부족 GIS 대체공사","345kV GIS 40kA 4000A → GIS 63kA 6300A GIS 용량대체","2016-09-05 09:00","2016-11-30 18:00","취소","취소","연속",null,null,null,201607130166]
[92,"충북","충주","신진천S/S #3 M.Tr 1차-TIE CB (7600)","신진천S/S 용량부족 GIS 대체공사","345kV GIS 40kA 4000A → GIS 63kA 6300A GIS 용량대체","2016-09-05 09:00","2016-11-30 18:00","취소","취소","연속",null,null,null,201607130167]
[93,"충북","충주","신진천S/S #3 M.Tr A","신진천S/S 용량부족 GIS 대체공사","345kV GIS 40kA 4000A → GIS 63kA 6300A GIS 용량대체","2016-09-05 09:00","2016-11-30 18:00","2016-09-05 09:00","2016-11-30 18:00","연속",null,null,null,201607130165]
[94,"대전충남","대전","신옥천신계룡 T/L","154kV 신옥천-청양T/L 피뢰기 설치공사","피뢰기 설치","2016-09-08 07:00","2016-09-13 18:00","2016-09-08 07:00","2016-09-13 18:00","매일",null,null,null,201607080079]
[95,"대전충남","서산","신당진개폐소-태안화력#2 T/L","345kV 신서산-태안화력 등 2개T/L 피뢰기 설치공사","[송전]신당진-태안화력#2T/L No.0-1~127(384set) -아킹혼 철거 -피뢰기 설치","2016-09-19 09:00","2016-09-29 18:00","2016-09-19 09:00","2016-09-29 18:00","매일",null,null,null,201607080334]
[96,"대전충남","서산","신당진 북당진 T/L T/L","345kV 신서산-태안화력 등 2개T/L 피뢰기 설치공사","[송전]신당진-태안화력#2T/L No.0-1~127(384set) -아킹혼 철거 -피뢰기 설치","2016-09-28 07:00","2016-09-28 18:00","2016-09-28 07:00","2016-09-28 18:00","매일",null,null,null,201607080343]
[97,"대전충남","서산","신서산태안화력#2 T/L","345kV 신서산-태안화력 등 2개T/L 피뢰기 설치공사","[송전]신당진-태안화력#2T/L No.0-1~127(384set) -아킹혼 철거 -피뢰기 설치","2016-09-29 07:00","2016-10-11 18:00","2016-09-29 07:00","2016-10-11 18:00","매일",null,null,null,201607080346]
[98,"대전충남","서산","태안T/P 2호기 1차 CB (7272)","태안화력 345kV 장기사용 GIS 교체공사","1.72BAY GIS (7272,7200,7271) 철거(40KA 4000A) 2.72BAY GIS (7272,7200) 신품설치 (63KA 6300A)","2016-09-01 08:00","2016-10-15 18:00","2016-09-01 08:00","2016-10-15 18:00","연속",null,null,null,201607050057]
[99,"대전충남","서산","태안T/P 345kV #70 BUS","태안화력 345kV 장기사용 GIS 교체공사","1.72BAY GIS(7272,7200,7271) 철거(40KA, 4000A) 2 72BAY GIS(7272,7200) 설치(60kA, 6000A) 3 72BAY GIS(70BUS)철거,설치 4 72BAY GIS(75BUS)철거,설치","2016-09-26 09:00","2016-10-05 18:00","2016-09-26 09:00","2016-10-05 18:00","연속",null,null,null,201607120100]
[100,"대전충남","서산","태안T/P 345kV #75 BUS","태안화력 345kV 장기사용 GIS 교체공사","1.72BAY GIS(7272,7200,7271) 철거(40KA, 4000A) 2 72BAY GIS(7272,7200) 설치(60kA, 6000A) 3 72BAY GIS(70BUS)철거,설치 4 72BAY GIS(75BUS)철거,설치","2016-09-10 09:00","2016-09-21 18:00","2016-09-10 09:00","2016-09-21 18:00","연속",null,null,null,201607120099]
[101,"대전충남","서산","태안T/P 2호기 1차 CB(7271) (7271)","태안화력 345kV 장기사용 GIS 교체공사","1.72BAY GIS (7272,7200,7271) 철거(40KA 4000A) 2.72BAY GIS (7272,7200) 신품설치 (63KA 6300A)","2016-09-01 09:00","2016-10-15 18:00","2016-09-01 09:00","2016-10-15 18:00","연속",null,null,null,201607070152]
[102,"대전충남","서산","태안T/P 2호기 1차CB- TIE(7200) (7200)","태안화력 345kV 장기사용 GIS 교체공사","1.72BAY GIS (7272,7200,7271) 철거(40KA 4000A) 2.72BAY GIS (7272,7200) 신품설치 (63KA 6300A)","2016-09-01 08:00","2016-10-15 18:00","2016-09-01 08:00","2016-10-15 18:00","연속",null,null,null,201607050064]
[103,"대전충남","아산","신온양신탕정#1 T/L","[송전]154kV 신온양-한샘T/L 경과지변경 건설공사","[송전] 1. 기설 No.1호 ~ 신설 No.2호간 가공지선 연선 및 긴선에 따른 활선근접","2016-09-10 07:00","2016-09-10 16:00","2016-09-10 07:00","2016-09-10 16:00","당일",null,null,null,201606100202]
[104,"대전충남","아산","신탕정S/S #3 M.Tr A","신탕정S/S 345kV #3M.Tr 누유 관련 제작사 하자보수","○ 345kV #3M.Tr 누유 관련 제작사 하자보수","2016-09-19 09:00","2016-09-19 18:00","2016-09-19 09:00","2016-09-19 18:00","당일",null,null,null,201607080102]
[105,"대전충남","아산","아산S/S #1 M.Tr A","아산S/S 345kV #1M.Tr 정밀점검","○ 345kV #1M.Tr 정밀점검 ○ 병행) 23kV Sh.R 4179-1, 2 CB 보통점검 ○ 병행) 23kV #1M.Tr 3차 4179 CB, #1S.Tr 및 #1S.Tr 1차 4189 CB 보통점검","2016-09-20 09:00","2016-09-30 18:00","2016-09-20 09:00","2016-09-30 18:00","연속",null,null,null,201607080104]
[106,"대전충남","아산","신서산아산#1 T/L","[송전] 345kV 아산-화성 등 15개T/L 피뢰기 설치공사","ㅇ 345kV 신서산-아산#1T/L 72기 피뢰기 설치 ㅇ 기타 부대작업","2016-09-01 09:00","2016-09-07 18:00","2016-09-01 09:00","2016-09-07 18:00","매일",null,null,null,201607080053]
[107,"대전충남","아산","아산S/S #2 M.Tr A","아산S/S 345kV #2M.Tr 보호배전반 교체 공사","○ 345kV #2M.Tr 보호배전반 교체 공사 ○ 병행) #2M.Tr 1차 7572 GIS 보통 점검","2016-09-01 09:00","2016-09-07 18:00","2016-09-01 09:00","2016-09-07 18:00","연속",null,null,null,201607080100]
[108,"대전충남","청양","보령C/C 70-71-0 SEC CB (70-71-0)","보령복합 362kV GIS 보통점검","○ 345kV 70-71-0 GIS 보통점검","2016-09-07 09:00","2016-09-07 18:00","2016-09-07 09:00","2016-09-07 18:00","당일",null,null,null,201607070102]
[109,"대전충남","청양","보령C/C 보령연락#2T/L CB (7271)","보령복합 362kV GIS 보통점검","○ 345kV 7271 GIS 보통점검","2016-09-06 09:00","2016-09-06 18:00","2016-09-06 09:00","2016-09-06 18:00","당일",null,null,null,201607070101]
[110,"대전충남","청양","보령C/C 75-76-0 SEC CB (75-76-0)","보령복합 362kV GIS 보통점검","○ 345kV 75-76-0 GIS 보통점검","2016-09-08 09:00","2016-09-08 18:00","2016-09-08 09:00","2016-09-08 18:00","당일",null,null,null,201607070103]
[111,"대전충남","청양","청양S/S #2 M.Tr 1차 CB (7772)","청양S/S 362kV GIS 보통점검","○ 345kV 7772 GIS 보통점검","2016-09-23 09:00","2016-09-23 18:00","2016-09-23 09:00","2016-09-23 18:00","당일",null,null,null,201607070107]
[112,"대전충남","청양","청양S/S #2M.Tr -TIE CB (7700)","청양S/S 362kV GIS 보통점검","○ 345kV 7700 GIS 보통점검","2016-09-22 09:00","2016-09-22 18:00","2016-09-22 09:00","2016-09-22 18:00","당일",null,null,null,201607070106]
[113,"전북","군산","군산S/S #2 M.Tr A","군산S/S #2 M.Tr","1. 군산S/S 345kV #2M.Tr 정밀점검공사","2016-09-26 09:00","2016-10-02 18:00","2016-09-26 09:00","2016-10-02 18:00","연속",null,null,null,201607150006]
[114,"전북","직할","신옥천무주양수 T/L","345kV 무주양수S/Y 접속설비 대체공사","362kV GIS 철거(4CB) 후 설치(6CB) 및 기타부대작업","2016-09-21 09:00","2016-12-19 18:00","2016-09-26 09:00","2016-12-19 18:00","연속",null,null,"한전요청",201607070092]
[115,"전북","직할","북경남무주양수 T/L","345kV 무주양수S/Y 접속설비 대체공사","362kV GIS 철거(4CB) 후 설치(6CB) 및 기타부대작업","2016-09-21 09:00","2016-12-19 18:00","2016-09-26 09:00","2016-12-19 18:00","연속",null,null,"한전요청",201607070091]
[116,"광주전남","강진","신강진S/S #3 M.Tr A","신강진S/S #3 M.Tr(변전협력회사 총액공사)","2016~17년 강진전력지사 변전협력회사 총액공사 - #3M.Tr 보호반 대체","2016-09-05 09:00","2016-09-09 18:00","2016-09-05 09:00","2016-09-09 18:00","연속",null,null,null,201607110282]
[117,"광주전남","광주","신화순S/S #1 M.Tr A","신화순S/S 345kV #1M.Tr(3차 LA 대체)","신화순S/S 345kV #1M.Tr 3차측 23kV 대체","2016-09-27 10:00","2016-09-27 18:00","2016-09-27 10:00","2016-09-27 18:00","당일",null,null,null,201607080292]
[118,"광주전남","순천","광양S/S #2 M.Tr A","345kV 광양S/S #2M.Tr(3차 소내변압기 보호계전기 설치)","소내변압기 2차 보호용 OCGR 설치","2016-09-12 09:00","2016-09-13 18:00","2016-09-12 09:00","2016-09-13 18:00","당일",null,null,null,201607080365]
[119,"광주전남","순천","신강진광양#2 T/L","345kV 신강진-광양#2T/L(광양-하동TP#1T/L 4회선 병가구간)","345kV 광양-하동#1T/L 피뢰기 설치 작업 4회선 병가구간","2016-09-24 07:00","2016-09-25 18:00","취소","취소","매일",null,null,null,201607110361,"경남 의령하동 조기종료시 시행"]
[120,"광주전남","순천","신남원광양#2 T/L","345kV 신남원-광양#2T/L(송전선로 피뢰기 설치)","345kV 신남원-광양#2T/L 송전선로 피뢰기 설치 - 1~125호, 64기","2016-09-28 07:00","2016-09-29 18:00","2016-09-30 07:00","2016-10-06 18:00","연속",null,null,"한전요청",201607110105]
[121,"광주전남","순천","광양율촌CC T/L","345kV 광양-율촌CC T/L(송전선로 피뢰기 설치)","345kV 광양-율촌CC T/L 송전선로 피뢰기 설치 - 90~136호, 38기","2016-09-28 07:00","2016-09-29 18:00","2016-09-30 07:00","2016-10-06 18:00","연속",null,null,"한전요청",201607110102]
[122,"광주전남","순천","광양여수TP(구 광양여수TP#2) T/L","광양S/S 345kV 광양-여수TP T/L(LA대체 및 GIS 보통점검)","2016~17년 순천전력지사 변전협력회사 총액공사 - 광양S/S 광양-여수TP T/L A,B,C상 LA 대체 - 광양S/S GIS 보통점검","2016-09-05 10:00","2016-09-08 18:00","2016-09-05 10:00","2016-09-08 18:00","연속",null,null,null,201607110348]
[123,"광주전남","순천","광양하동화력#1 T/L","345kV 광양-하동TP #1T/L(송전선로 피뢰기 설치)","345kV 광양-하동TP #1T/L 송전선로 피뢰기 설치 - 26~73호, 48기","2016-09-24 07:00","2016-09-28 18:00","취소","취소","연속",null,null,null,201607110356,"경남 의령하동 조기종료시 시행"]
[124,"광주전남","순천","율촌CC 여수TP T/L","345kV 율촌CC-여수TP T/L(GIS 보통점검 및 CVT 대체)","2016~17년 순천전력지사 변전협력회사 총액공사 - 여수T/P GIS 보통점검 및 B상 CVT 대체 345kV 율촌CC-여수TP T/L 송전선로 피뢰기 설치 - 율촌분기 1~11호, 11기","2016-09-19 09:00","2016-09-21 18:00","2016-09-19 09:00","2016-09-21 18:00","연속",null,null,null,201607110096]
[125,"대구경북","경산","신경산대구#1 T/L","2016년 직할 가공송전선로 순시점검 위탁","- 하단의 경산-자인T/L 작업간 안전확보","2016-09-30 08:00","2016-09-30 18:00","2016-09-30 08:00","2016-09-30 18:00","당일",null,null,null,201607110390]
[126,"대구경북","경산","신경산대구#2 T/L","2016년 직할 가공송전선로 순시점검 위탁","- 하단의 경산-자인T/L 작업간 안전확보","2016-09-24 08:00","2016-09-24 18:00","2016-09-24 08:00","2016-09-24 18:00","당일",null,null,null,201607110389]
[127,"대구경북","경산","신경산S/S #2 M.Tr A","'16년 신경산S/S 170kV 장기사용 GIS 대체공사","신경산-경산#1T/L GIS 대체시 안전이격거리 확보","2016-09-23 09:00","2016-09-23 18:00","2016-09-23 09:00","2016-09-23 18:00","당일",null,null,null,201607290068]
[128,"대구경북","칠곡","서대구S/S #3 M.Tr A","서대구S/S 6344 정밀점검","서대구S/S 6344 정밀점검","2016-09-21 09:30","2016-09-23 18:00","2016-09-21 09:30","2016-09-23 18:00","연속",null,null,null,201607110359]
[129,"대구경북","포항","신포항청송PP T/L","345kV 신포항-청송PPT/L 피뢰기 설치공사","345kV 신포항-청송PPT/L No. 77~220 피뢰기 설치","2016-09-20 07:00","2016-09-30 18:00","2016-09-20 07:00","2016-09-30 18:00","매일",null,null,null,201607080080]
[130,"대구경북","포항","신포항S/S 345kV #1 BUS","신포항S/S #1BUS 휴전","-7771 CB 보통점검, 7751 불량 DS 점검 -78Bay #1BUS측 분기모선 교체","2016-09-26 09:00","2016-09-26 18:00","취소","취소","당일",null,null,"계통안정",201607080238]
[131,"대구경북","포항","신포항S/S 345kV #2 BUS","신포항S/S #2BUS 휴전","-78Bay #2BUS측 분기모선 교체","2016-09-27 09:00","2016-09-27 18:00","취소","취소","당일",null,null,"계통안정",201607080242]
[132,"부산울산","동부산","신양산신대연#2 T/L","신양산S/S 예비소내전원 이설관련 전주철거 안전이격","신양산S/S 예비소내전원 이설관련 전주철거 안전이격(신양산-신대연#2 T/L)","2016-09-02 09:30","2016-09-02 17:00","2016-09-02 09:30","2016-09-02 17:00","당일",null,null,null,201607110513]
[133,"부산울산","북부산","북부산S/S 신양산-북부산#2T/L CB (7771)","2016년 북부산변전협력회사 총액공사","북부산S/S 7771 GIS 하자점검","2016-09-07 09:00","2016-09-07 18:00","2016-09-07 09:00","2016-09-07 18:00","당일",null,null,null,201607110303]
[134,"부산울산","북부산","북부산울산TP T/L","345kV 북부산-울산화력 등 2개T/L 전선접속개소 전선교체공사","북부산-울산화력T/L 전선교체공사(No.90~117)","2016-09-19 07:00","2016-10-03 18:00","2016-09-19 07:00","2016-10-03 18:00","연속",null,null,null,201607110295]
[135,"부산울산","북부산","북부산S/S 서부산-북부산#1T/L CB (7471)","2016년 북부산변전협력회사 총액공사","345kV 서부산-북부산#1T/L 7471 GIS 보통점검","2016-09-23 09:00","2016-09-23 18:00","2016-09-23 09:00","2016-09-23 18:00","당일",null,null,null,201607110376]
[136,"부산울산","울산","동울산S/S #1 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","동울산S/S M.Tr 및 1, 2차 GIS 하자점검","2016-09-06 09:00","2016-09-07 18:00","2016-09-06 09:00","2016-09-07 18:00","연속",null,null,null,201607110523]
[137,"부산울산","울산","신온산S/S #4 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","신온산S/S #4M.Tr 및 1, 2차 GIS 초기점검","2016-09-08 09:00","2016-09-09 18:00","2016-09-08 09:00","2016-09-09 18:00","연속",null,null,null,201607110525]
[138,"부산울산","울산","신온산S/S #3 M.Tr A","신온산S/S 154kV #2Sh.C 고장 복구","-신온산S/S 154kV #2Sh.C 고장 복구 - 1. 154kV #2Sh.C용 GIS C/H 철거관련 안전이격거리 확보차 - 사유 : 제작사(현대중공업) 철거자재 개조 및 수리 관련 입고","2016-09-06 09:00","2016-09-06 18:00","2016-09-06 09:00","2016-09-06 18:00","연속",null,null,null,201607290033]
[139,"부산울산","울산","북부산신울산#1 T/L","2016년 362kV 개폐장치 정밀점검 공사","신울산S/S 7600 GIS 시험가압","2016-09-28 17:00","2016-09-28 18:00","2016-09-28 17:00","2016-09-28 18:00","당일",null,null,null,201607120007]
[140,"부산울산","울산","신울산S/S 345kV #70BUS","2016년 362kV 개폐장치 정밀점검 공사","신울산S/S 7600 GIS 시험가압","2016-09-28 17:00","2016-09-28 18:00","2016-09-28 17:00","2016-09-28 18:00","당일",null,null,null,201607120005]
[141,"부산울산","울산","신울산S/S #4 M.Tr 1차 TIE CB (7600)","2016년 362kV 개폐장치 정밀점검 공사","신울산 7600 GIS 정밀점검","2016-09-26 08:00","2016-09-28 18:00","2016-09-26 08:00","2016-09-28 18:00","연속",null,null,null,201607110533]
[142,"부산울산","울산","신울산S/S #4 M.Tr 1차 CB (7672)","2016년 362kV 개폐장치 정밀점검 공사","신울산 7672 GIS 정밀점검","2016-09-29 08:00","2016-10-01 18:00","2016-09-29 08:00","2016-10-01 18:00","연속",null,null,null,201607120002]
[143,"부산울산","울산","울산C/C 4복합 #4S/T 1차-TIE CB (7A00)","2016-17년 울산전력지사 변전협력회사 총액공사","울산복합 7A00 GIS 하자점검","2016-09-05 09:00","2016-09-05 18:00","2016-09-05 09:00","2016-09-05 18:00","당일",null,null,null,201607110515]
[144,"부산울산","울산","울주신경산#2 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","울주S/S 77Bay B/F PNL 대체","2016-09-05 09:00","2016-09-11 18:00","2016-09-05 09:00","2016-09-11 18:00","연속",null,null,null,201607110517]
[145,"부산울산","울산","울주S/S 345kV #1 BUS","2016-17년 울산전력지사 변전협력회사 총액공사","울주S/S #1BUS 보호반 대체","2016-09-26 09:00","2016-09-30 18:00","2016-09-26 09:00","2016-09-30 18:00","연속",null,null,null,201607110521]
[146,"부산울산","직할","신대연S/S #1M.Tr A","345kV 신대연S/S 변압기 소음저감설비 설치공사","○ 345kV M.Tr 소음저감설비 설치 x 1식 ○ 기타부대공사 x 1식","2016-09-01 08:00","2016-09-09 18:00","2016-09-01 08:00","2016-09-09 18:00","연속",null,null,null,201607110363]
[147,"부산울산","직할","신대연S/S #1Sh.R","신대연S/S #1Sh.R 및 7079 초기점검","신대연S/S #1Sh.R 및 7079 초기점검","2016-09-30 10:00","2016-09-30 18:00","2016-09-30 10:00","2016-09-30 18:00","당일",null,null,null,201607110325]
[148,"부산울산","직할","신대연S/S 신양산-신대연#1T/L CB (7171)","신대연S/S 7171 GIS 보통점검","신대연S/S 7171 GIS 보통점검","2016-09-19 10:00","2016-09-19 18:00","2016-09-19 10:00","2016-09-19 18:00","당일",null,null,null,201607110314]
[149,"부산울산","직할","신대연S/S 신양산-신대연#2T/L CB (7271)","신대연S/S 7271 GIS 보통점검","신대연S/S 7271 GIS 보통점검","2016-09-12 10:00","2016-09-12 18:00","2016-09-12 10:00","2016-09-12 18:00","당일",null,null,null,201607110319]
[150,"부산울산","직할","신대연S/S #2M.Tr A","345kV 신대연S/S 변압기 소음저감설비 설치공사","○ 345kV M.Tr 소음저감설비 설치 x 1식 ○ 기타부대공사 x 1식","2016-09-20 08:00","2016-09-28 18:00","2016-09-20 08:00","2016-09-28 18:00","연속",null,null,null,201607110364]
[151,"경남","직할","신마산신김해#2 T/L","345kV 신마산-신김해#2T/L 피뢰기 설치공사","345kV 신마산-신김해#2T/L 피뢰기 설치공사(22~27호)","2016-09-27 08:00","2016-09-30 18:00","2016-09-27 08:00","2016-09-30 18:00","매일",null,null,null,201607080210]
[152,"경남","직할","신김해북부산#1 T/L","345kV 신김해-북부산#1T/L 피뢰기 설치공사","345kV 신김해-북부산#1T/L 피뢰기 설치공사(101~106호)","2016-09-27 08:00","2016-09-30 18:00","2016-09-27 08:00","2016-09-30 18:00","매일",null,null,null,201607080208]
[153,"경남","직할","신김해신녹산#1 T/L","안전이격확보(154kV 신김해-삼정#2T/L 정밀점검)","154kV 신김해-삼정#2T/L 정밀점검 관련 안전이격확보 휴전","2016-09-23 08:00","2016-09-23 18:00","2016-09-23 08:00","2016-09-23 18:00","당일",null,null,null,201607080204]
[154,"경남","직할","신김해삼천포화력#1 T/L","345kV 신김해-삼천포화력#1T/L 과열개소 정비","345kV 신김해-삼천포화력#1T/L 접속단자 과열개소 정비","2016-09-22 08:00","2016-09-22 18:00","2016-09-22 08:00","2016-09-22 18:00","당일",null,null,null,201607200121]
[155,"경남","직할","신김해삼천포화력#2 T/L","345kV 신김해-삼천포화력#2T/L 점퍼선 불량조치 및 과열개소 정비","345kV 신김해-삼천포화력#2T/L 점퍼선 불량조치 및 과열개소 정비","2016-09-20 07:00","2016-09-21 18:00","2016-09-20 07:00","2016-09-21 18:00","매일",null,null,null,201607200123]
[156,"경남","진주","의령산청양수#1 T/L","산청P/P 의령-산청양수#1T/L CPD 교체공사","산청P/P 의령-산청양수#1T/L CPD 교체공사-3대(A,B,C상) ※ 안정 후 투입차단기 : 7100(산청PP), 황색차단기 : 7471,7400(의령)","2016-09-08 09:30","2016-09-08 18:30","2016-09-08 09:30","2016-09-08 18:30","당일",null,null,null,201607060180]
[157,"경남","진주","의령S/S 345kV #76 BUS","345kV 의령S/S #3M.Tr 증설공사(345kV GIS 설치)","345kV 의령S/S #3M.Tr 증설공사(345kV GIS 설치) -7872CB 신규설치 시험가압 및 상체크","2016-09-28 16:00","2016-09-29 16:00","2016-09-28 16:00","2016-09-29 16:00","연속",null,null,null,201607130001]
[158,"경남","진주","의령S/S 신남원-의령#1T/L-TIE CB (7800)","345kV 의령S/S #3M.Tr 증설공사(345kV GIS 설치)","345kV 의령S/S #3M.Tr 증설공사(345kV GIS 설치) -7872CB 신규설치 후 보호반 결선 및 준공시험을 위한 신남원-의령#1T/L 단모선운전","2016-09-29 17:00","2016-10-24 12:00","2016-09-29 17:00","2016-10-24 12:00","연속",null,null,null,201607130002]
[159,"경남","진주","의령S/S #2 M.Tr A","345kV 의령S/S #3M.Tr 증설(기존 예비모선과 접속)","345kV 의령S/S #3M.Tr 증설(기존 예비모선과 접속) - #2M.Tr 상부 갠트리와 #3M.Tr 상부 갠트리와 접속","2016-09-30 10:30","2016-10-02 12:00","2016-09-30 10:30","2016-10-02 12:00","연속",null,null,null,201607080227]
[160,"경남","진주","고령의령#1 T/L","의령S/S 고령-의령#1T/L CPD 교체공사","의령S/S 고령-의령#1T/L CPD 교체공사 - 3대(A,B,C상)","2016-09-11 09:30","2016-09-11 18:30","2016-09-11 09:30","2016-09-11 18:30","당일",null,null,null,201607060181]
[161,"경남","진주","의령S/S 345kV #76 BUS","345kV 의령S/S #3M.Tr 증설공사(345kV GIS 설치)","345kV 의령S/S #3M.Tr 증설공사(345kV GIS 설치) -345kV #76BUS(유도방지를 위한 안전확보) 및 7800CB 휴전","2016-09-19 13:00","2016-09-21 16:00","2016-09-19 13:00","2016-09-21 16:00","연속",null,null,null,201607080236]
[162,"경남","진주","의령S/S 신남원-의령#1T/L-TIE CB (7800)","345kV 의령S/S #3M.Tr 증설공사(345kV GIS 설치)","345kV 의령S/S #3M.Tr 증설공사(345kV GIS 설치) -345kV #76BUS 및 7800CB 휴전","2016-09-19 13:00","2016-09-22 10:00","2016-09-19 13:00","2016-09-22 10:00","연속",null,null,null,201607080241]
[163,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력T/L 6-8호 지장이설공사(요청자시행)","신설7호 설치 및 기설 7호 철거","2016-09-22 07:00","2016-09-25 19:00","2016-09-22 07:00","2016-09-25 19:00","연속",null,null,null,201607110001]
[164,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력T/L 6-8호 지장이설공사(요청자시행)","신설7호 설치 및 기설 7호 철거","2016-09-26 07:00","2016-09-29 19:00","2016-09-26 07:00","2016-09-29 19:00","연속",null,null,null,201607130075]
[165,"경남","진주","신남원의령#1 T/L","345kV 의령S/S #3M.Tr 증설공사(345kV GIS 설치)","345kV 의령S/S #3M.Tr 증설공사(345kV GIS 설치) -78Bay B/F 보호반 대체 -7872CB 설치 후 시험가압","2016-09-22 10:00","2016-09-29 17:00","2016-09-22 10:00","2016-09-29 17:00","연속",null,null,null,201607080245]
[166,"경남","진주","광양하동화력#2 T/L","광양-하동T/P#2T/L 보호반 PNL 대체공사","광양-하동T/P#2T/L 보호반 PNL 대체공사 - 병행작업 : 하동TP측 광양-하동T/P#2T/L(A,B,C) PT 하자점검 광양-하동T/P#2T/L(A,B,C) LA 대체공사","2016-09-22 09:30","2016-09-27 18:30","취소","취소","연속",null,null,null,201607130010,"의령하동T/P 취소시 시행 "]
[167,"경남","통영","삼천포T/P 신김해-삼천포화력#1T/L CB (7572)","삼천포T/P 345kV 7572 CB 가스누기 보수","345kV 7572 CB A상 옆 점검창 가스누기 보수","2016-09-01 09:30","2016-09-02 18:30","2016-09-01 09:30","2016-09-02 18:30","당일",null,null,null,201607130123]
[168,"경남","통영","신고성삼천포화력#2 T/L","[신고성,삼천포T/P]7B,7D Bay B/F 대체공사","[신고성,삼천포T/P]7B,7D Bay B/F 대체공사","2016-09-14 09:30","2016-09-17 18:30","2016-09-14 09:30","2016-09-17 18:30","연속",null,null,null,201607080150]
[169,"경남","통영","신고성S/S #2 M.Tr A","[신고성,삼천포T/P]7B,7D Bay B/F 대체공사","[신고성,삼천포T/P]7B,7D Bay B/F 대체공사","2016-09-14 09:30","2016-09-17 18:30","2016-09-14 09:30","2016-09-17 18:30","연속",null,null,null,201607080151]
[170,"경남","함안","신마산삼천포화력#1 T/L","345kV 신마산-삼천포화력 #1T/L 피뢰기 설치공사","345kV 신마산-삼천포화력 #1T/L 피뢰기 설치공사 (18,19,27,30,31,39~43,57~69,74,76~79,83~177호)","2016-09-03 08:30","2016-09-13 18:00","2016-09-03 08:30","2016-09-13 18:00","연속",null,null,null,201606290041]

{"sheet":"154송부","index":2,"n_rows":340,"n_cols":16,"rows_kept":340,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2016년도 9월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","구의광장#1 T/L","154㎸ 구의광장T/L 일부구간 선종교체공사","1. 배 경 □ 구의S/S(테크노마트) 화재 및 설비피해시 대형 인명 피해 예방 2. 구의변전소 현황 □ 수용선로 : 154kV OF 4회선, 배전 총 13회선 □ 형 태 : 주상복합형 지하변전소(지하4∼6층) ※ 테크노마트 : 지하6층∼지상 39층(상가, 주택 등 1,000여명 거주중) 3. 시행계획 : 154㎸","2016-09-01 09:00","2016-09-30 18:00","2016-09-01T09:00:00","2016-09-30T18:00:00","연속",null,null,null,201607130119,"-"]
[2,"서울","중부","은평녹번 T/L","녹번S/S 인출T/L 교체공사","1. 사 업 명 : 154kV 녹번S/S 인출T/L 선종 교체공사 2. 사업목적 : 녹번변전소(지하복합) 화재 및 대형 재난사고 예방 3. 사업개요 ○ 사업구간 : 154kV 녹번S/S ∼ 녹번분기전력구 ○ 사업내용 - 철거 : 154kV OF 2000㎟ 2C, 총길이1.8㎞","2016-09-19 09:00","2016-11-04 18:00","2016-09-19T09:00:00","2016-11-04T18:00:00","연속",null,null,null,201607120106,"-"]
[3,"서울","중부","동빙고반포#1 T/L","2016~2017년 중부전력지사 변전협력업체 총액공사","동빙고S/S 170kV GIS 보통점검","2016-09-05 10:00","2016-09-05 17:00","2016-09-05T10:00:00","2016-09-05T17:00:00","당일",null,null,null,201607190049,"-"]
[4,"서울","중부","순화동빙고 T/L","2016~2017년 중부전력지사 변전협력업체 총액공사","동빙고S/S 170kV GIS 보통점검","2016-09-07 10:00","2016-09-07 17:00","2016-09-06T10:00:00","2016-09-06T17:00:00","당일",null,null,null,201607190051,"-"]
[5,"서울","중부","동빙고반포#2 T/L","2016~2017년 중부전력지사 변전협력업체 총액공사","동빙고S/S 170kV GIS 보통점검","2016-09-06 10:00","2016-09-06 17:00","2016-09-24T10:00:00","2016-09-24T18:00:00","당일",null,null,null,201607190050,"-"]
[6,"서울","중부","수색은평#1 T/L","케이블헤드 부분방전 상시 진단시스템 설치공사","o 케이블헤드 부분방전 센서설치 o 단자 집합반 설치 등","2016-09-24 10:00","2016-09-24 18:00","2016-09-25T10:00:00","2016-09-25T18:00:00","당일",null,null,null,201607200020,"-"]
[7,"서울","중부","수색은평#2 T/L","케이블헤드 부분방전 상시 진단시스템 설치공사","o 케이블헤드 부분방전 센서설치 o 단자 집합반 설치 등","2016-09-25 10:00","2016-09-25 18:00","2016-09-07T10:00:00","2016-09-07T17:00:00","당일",null,null,null,201607200021,"-"]
[8,"서울","중부","용산동빙고 T/L","2016년 중부전력지사 170kV GIS 정밀점검","용산S/S 용산동빙고T/L GIS(617) 정밀점검","2016-09-08 08:00","2016-09-10 18:00","2016-09-08T08:00:00","2016-09-10T18:00:00","연속",null,null,null,201607140141,"-"]
[9,"서울","직할","불광서대문#2 T/L","케이블헤드 부분방전 상시 진단시스템 설치공사","- 종단접속부 부분방전센서(UWB) 센서 설치(1개/상) - 센서 단자 접속함 설치(1대)","2016-09-24 10:00","2016-09-24 18:00","2016-09-24T10:00:00","2016-09-24T18:00:00","당일",null,null,null,201607040178,"-"]
[10,"서울","직할","불광서대문#1 T/L","케이블헤드 부분방전 상시 진단시스템 설치공사","- 종단접속부 부분방전센서(UWB) 센서 설치(1개/상) - 센서 단자 접속함 설치(1대)","2016-09-25 10:00","2016-09-25 18:00","2016-09-25T10:00:00","2016-09-25T18:00:00","당일",null,null,null,201607040176,"-"]
[11,"서울","직할","신당한남 T/L","신당S/S 170kV 장기사용 GIS 대체공사(1차)","신당S/S 170kV 장기사용 GIS 대체공사(1차) - 신당한남T/L, #4M.Tr 1차 GIS 대체, 667 CB 철거, PT 신규 설치","2016-09-03 09:30","2016-09-30 18:00","2016-09-03T09:30:00","2016-09-30T18:00:00","연속",null,null,null,201607140187,"-"]
[12,"서울","직할","신촌순화 T/L","`16-17 직할 변전협력총액공사","신촌S/S 170kV 신촌순화T/L GIS 초기점검","2016-09-27 10:00","2016-09-27 18:00","2016-09-27T10:00:00","2016-09-27T18:00:00","당일",null,null,null,201607130134,"-"]
[13,"서울","직할","옥인운니#2 T/L","2016년 직할 170kV GIS 정밀점검","운니S/S 170kV GIS 옥인운니#2T/L 정밀점검","2016-09-23 09:30","2016-09-25 18:00","2016-09-23T09:30:00","2016-09-25T18:00:00","연속",null,null,null,201607130129,"-"]
[14,"서울","직할","옥인운니#1 T/L","2016년 직할 170kV GIS 정밀점검","운니S/S 170kV GIS 옥인운니#1T/L 정밀점검","2016-09-20 09:30","2016-09-22 18:00","2016-09-20T09:30:00","2016-09-22T18:00:00","연속",null,null,null,201607130128,"-"]
[15,"남서울","강남","신성남염곡#1 T/L","154KV 신성남-염곡T/L 이설공사(양재대로)","강남순환도시고속도로 건설에 따른 지장 송전선로 이설 154kV 신성남-염곡T/L J/B#17~18","2016-09-19 14:00","2016-10-17 10:00","2016-09-19T14:00:00","2016-10-17T10:00:00","연속",null,null,null,201607080298,"-"]
[16,"남서울","동서울","가락수서#1 T/L","154kV 가락-수서T/L 가락S/S 인출구간 선종교체공사","가락S/S 인출구간 OF케이블을 XLPE케이블로 교체","2016-09-26 09:00","2016-10-25 18:00","2016-09-26T09:00:00","2016-10-25T18:00:00","연속",null,null,null,201607140037,"-"]
[17,"남서울","영서","가양등촌#1 T/L","2016년 변전협력회사 총액공사_보통점검","가양S/S 170kV GIS 초기점검 및 PITR 활용 인출 인터록구성","2016-09-12 09:00","2016-09-12 18:00","2016-09-12T09:00:00","2016-09-12T18:00:00","당일",null,null,null,201607110286,"-"]
[18,"남서울","영서","가양등촌#2 T/L","2016년 변전협력회사 총액공사_보통점검","가양S/S 170kV GIS 초기점검 및 PITR 활용 인출 인터록구성","2016-09-13 09:00","2016-09-13 18:00","2016-09-13T09:00:00","2016-09-13T18:00:00","당일",null,null,null,201607110289,"-"]
[19,"남서울","직할","교대이수#1 T/L","154kV 교대-이수T/L 이설공사","J/B#7~#8, J/B#9~#10구간 이설","2016-09-01 09:00","2016-10-08 18:00","2016-09-01T09:00:00","2016-10-08T18:00:00","연속",null,null,null,201607130043,"-"]
[20,"인천","김포","경서양촌#2 T/L","154kV 경서양촌#2T/L 정밀점검","154kV 경서양촌#2T/L 정밀점검 시행","2016-09-21 08:00","2016-09-23 18:00","2016-09-21T08:00:00","2016-09-23T18:00:00","매일",null,null,null,201607250025,"-"]
[21,"인천","김포","신김포통진#1 T/L","154kV 신김포-통진 #1 T/L 중간접속함 교체공사","일진전기제 154kV 구형 조립식접속함(PMJ)을 Flat-type접속합으로 교체","2016-09-01 09:00","2016-09-11 18:00","2016-09-01T09:00:00","2016-09-11T18:00:00","연속",null,null,null,201606300021,"-"]
[22,"인천","김포","신김포통진#2 T/L","154kV 신김포-통진 #2 T/L 중간접속함 교체공사","일진전기제 154kV 구형 조립식접속함(PMJ)을 Flat-type접속합으로 교체","2016-09-13 09:00","2016-09-23 18:00","2016-09-13T09:00:00","2016-09-23T18:00:00","연속",null,null,null,201606300023,"-"]
[23,"인천","시흥","남동관교#2 T/L","154kV 남동-관교T/L 접지선 교체공사","중간접속함 접지선 교체","2016-09-02 09:00","2016-09-02 18:00","2016-09-02T09:00:00","2016-09-02T18:00:00","당일",null,null,null,201607050089,"-"]
[24,"인천","시흥","신시흥남동#2 T/L","154kV 남동T/L 아킹혼설치 및 오봉T/L 피뢰기 설치공사","154kV 남동T/L 아킹혼설치(30기) 및 오봉T/L 피뢰기 설치(34기)","2016-09-04 09:00","2016-09-04 18:00","2016-09-18T09:00:00","2016-09-18T18:00:00","당일",null,null,"계통안정",201606290036,"-"]
[25,"인천","시흥","신시흥남동#2 T/L","154kV 남동T/L 아킹혼설치 및 오봉T/L 피뢰기 설치공사","154kV 남동T/L 아킹혼설치(30기) 및 오봉T/L 피뢰기 설치(34기)","2016-09-11 09:00","2016-09-11 18:00","2016-09-11T09:00:00","2016-09-11T18:00:00","당일",null,null,null,201606290037,"-"]
[26,"인천","시흥","남동관교#1 T/L","154kV 남동-관교T/L 접지선 교체공사","중간접속함 접지선 교체","2016-09-01 09:00","2016-09-01 18:00","2016-09-01T09:00:00","2016-09-01T18:00:00","당일",null,null,null,201607050088,"-"]
[27,"인천","시흥","신시흥도림 T/L","154kV 남동T/L 아킹혼설치 및 오봉T/L 피뢰기 설치공사","154kV 남동T/L 아킹혼설치(30기) 및 오봉T/L 피뢰기 설치(34기)","2016-09-11 09:00","2016-09-11 13:00","2016-09-11T09:00:00","2016-09-11T13:00:00","당일",null,null,null,201606290040,"-"]
[28,"인천","시흥","신시흥도림 T/L","154kV 남동T/L 아킹혼설치 및 오봉T/L 피뢰기 설치공사","154kV 남동T/L 아킹혼설치(30기) 및 오봉T/L 피뢰기 설치(34기)","2016-09-04 09:00","2016-09-04 18:00","2016-09-18T09:00:00","2016-09-18T18:00:00","당일",null,null,"계통안정",201606290039,"-"]
[29,"인천","시흥","서시화S/S 154kV #1 BUS","서시화S/S 북시화서시화#1 T/LGIS 정밀점검공사","서시화S/S 북시화서시화#1 T/LGIS 정밀점검공사","2016-09-06 14:00","2016-09-07 18:00","2016-09-06T14:00:00","2016-09-07T18:00:00","연속",null,null,null,201607070146,"-"]
[30,"인천","시흥","서시화S/S 154kV #1 BUS","서시화S/S 북시화서시화#2 T/LGIS 정밀점검공사","서시화S/S 북시화서시화#2 T/LGIS 정밀점검공사","2016-09-09 14:00","2016-09-10 18:00","2016-09-09T14:00:00","2016-09-10T18:00:00","연속",null,null,null,201607070151,"-"]
[31,"인천","시흥","서시화S/S 154kV #2 BUS","서시화S/S 북시화서시화#2 T/LGIS 정밀점검공사","서시화S/S 북시화서시화#2 T/LGIS 정밀점검공사","2016-09-08 09:30","2016-09-09 14:00","2016-09-08T09:30:00","2016-09-09T14:00:00","연속",null,null,null,201607070150,"-"]
[32,"인천","시흥","북시화서시화#2 T/L","서시화S/S 북시화서시화#2 T/LGIS 정밀점검공사","서시화S/S 북시화서시화#2 T/LGIS 정밀점검공사","2016-09-08 09:30","2016-09-10 18:00","2016-09-08T09:30:00","2016-09-10T18:00:00","연속",null,null,null,201607070149,"-"]
[33,"인천","시흥","서시화S/S 154kV #2 BUS","서시화S/S 북시화서시화#1 T/LGIS 정밀점검공사","서시화S/S 북시화서시화#1 T/LGIS 정밀점검공사","2016-09-05 09:30","2016-09-06 14:00","2016-09-05T09:30:00","2016-09-06T14:00:00","연속",null,null,null,201607070144,"-"]
[34,"인천","시흥","북시화서시화#1 T/L","서시화S/S 북시화서시화#1 T/LGIS 정밀점검공사","서시화S/S 북시화서시화#1 T/LGIS 정밀점검공사","2016-09-05 09:30","2016-09-07 18:00","2016-09-05T09:30:00","2016-09-07T18:00:00","연속",null,null,null,201607070141,"-"]
[35,"인천","시흥","남동연수#2 T/L","연수S/S 170kV 장기사용 GIS 대체공사","- 154kV 남동연수#2T/L GIS 1CCT 대체 - 154kV #2M.Tr 1차 GIS 1CCT 대체 - 154kV 학익연수#1T/L GIS 1CCT 대체","2016-09-19 08:00","2016-10-18 18:00","2016-09-19T08:00:00","2016-10-18T18:00:00","연속",null,null,null,201607060017,"-"]
[36,"인천","시흥","학익연수#1 T/L","연수S/S 170kV 장기사용 GIS 대체공사","- 154kV 학익연수#1T/L GIS 1CCT 대체 - 154kV 남동연수#2T/L GIS 1CCT 대체 - 154kV #2M.Tr 1차 GIS 1CCT 대체","2016-09-19 08:00","2016-10-18 18:00","2016-09-19T08:00:00","2016-10-18T18:00:00","연속",null,null,null,201607060019,"-"]
[37,"인천","시흥","연수S/S 154kV #1 BUS","연수S/S 170kV 장기사용 GIS 대체공사","- 154kV 남동연수#2T/L GIS 1CCT 대체 - 154kV #2M.Tr 1차 GIS 1CCT 대체 - 154kV 학익연수#1T/L GIS 1CCT 대체","2016-09-22 08:00","2016-10-04 08:00","2016-09-22T08:00:00","2016-10-04T08:00:00","연속",null,null,null,201607060022,"-"]
[38,"인천","시흥","연수S/S 154kV #2 BUS","연수S/S 170kV 장기사용 GIS 대체공사","- 154kV 남동연수#2T/L GIS 1CCT 대체 - 154kV #2M.Tr 1차 GIS 1CCT 대체 - 154kV 학익연수#1T/L GIS 1CCT 대체","2016-09-19 08:00","2016-09-21 18:00","2016-09-19T08:00:00","2016-09-21T18:00:00","연속",null,null,null,201607060020,"-"]
[39,"인천","시흥","도림오봉 T/L","154kV 남동T/L 아킹혼설치 및 오봉T/L 피뢰기 설치공사","154kV 남동T/L 아킹혼설치(30기) 및 오봉T/L 피뢰기 설치(34기)","2016-09-11 13:00","2016-09-11 18:00","2016-09-11T13:00:00","2016-09-11T18:00:00","당일",null,null,null,201606290038,"-"]
[40,"인천","인천","계양원창 T/L","피뢰기 설치공사(가공송전정비 협력회사 총액공사)","송전철탑 피뢰기 설치","2016-09-28 08:00","2016-09-28 18:00","2016-09-28T08:00:00","2016-09-28T18:00:00","매일",null,null,null,201607150183,"-"]
[41,"인천","인천","인천CC S/Y 60-61 SEC GIS","인천CC #60-65 모선보호반 대체공사","인천CC #60-65 모선보호반 대체공사","2016-09-26 09:00","2016-09-30 18:00","2016-09-26T09:00:00","2016-09-30T18:00:00","연속",null,null,null,201607080075,"-"]
[42,"인천","인천","인천CC S/Y 154kV #1 BUS TIE GIS","인천CC #60-65 모선보호반 대체공사(6100휴전)","인천CC #60-65 모선보호반 대체공사(6100휴전) 6100 차단기 조작시험 병행(09/27 시행)","2016-09-26 09:00","2016-09-30 18:00","2016-09-26T09:00:00","2016-09-30T18:00:00","연속",null,null,null,201607080070,"-"]
[43,"인천","인천","인천CC S/Y 65-66 SEC GIS","인천CC #60-65 모선보호반 대체공사","인천CC #60-65 모선보호반 대체공사","2016-09-26 09:00","2016-09-30 18:00","2016-09-26T09:00:00","2016-09-30T18:00:00","연속",null,null,null,201607080074,"-"]
[44,"인천","인천","인천CC S/Y 60-61 SEC GIS","인천CC #61-66 모선보호반 대체공사","인천CC #61-66 모선보호반 대체공사","2016-09-19 09:00","2016-09-23 18:00","2016-09-19T09:00:00","2016-09-23T18:00:00","연속",null,null,null,201607080071,"-"]
[45,"인천","인천","인천CC S/Y 154kV #2 BUS TIE GIS","인천CC #61-66 모선보호반 대체공사(6200휴전)","인천CC #61-66 모선보호반 대체공사(6200휴전)","2016-09-19 09:00","2016-09-23 18:00","2016-09-19T09:00:00","2016-09-23T18:00:00","연속",null,null,null,201607080077,"-"]
[46,"인천","인천","인천CC S/Y 65-66 SEC GIS","인천CC #61-66 모선보호반 대체공사","인천CC #61-66 모선보호반 대체공사","2016-09-19 09:00","2016-09-23 18:00","2016-09-19T09:00:00","2016-09-23T18:00:00","연속",null,null,null,201607080073,"-"]
[47,"인천","직할","신부평S/S 154kV #1 BUS TIE GIS","신부평S/S 154kV 6100GIS 정밀점검","신부평S/S 154kV 6100GIS 정밀점검","2016-09-27 08:00","2016-09-28 18:00","취소","취소","연속",null,null,"한전요청",201607150083,"-"]
[48,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 154kV 신부평-부천#1T/L 정밀점검","신부평S/S 154kV 신부평-부천#1T/L 정밀점검","2016-09-08 08:00","2016-09-09 14:00","취소","취소","연속",null,null,"계통안정",201607150073,"-"]
[49,"인천","직할","신부평S/S 154kV #61 BUS","신부평S/S 154kV 6200GIS 정밀점검","신부평S/S 154kV 6200GIS 정밀점검","2016-09-29 08:00","2016-09-30 10:00","취소","취소","연속",null,null,"계통안정",201607150088,"-"]
[50,"인천","직할","신부평S/S 154kV #66 BUS","신부평S/S 154kV 6200GIS 정밀점검","신부평S/S 154kV 6200GIS 정밀점검","2016-09-30 10:00","2016-09-30 18:00","취소","취소","연속",null,null,"계통안정",201607150089,"-"]
[51,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 154kV #62M.Tr 정밀점검","신부평S/S 154kV #62M.Tr 정밀점검","2016-09-22 08:00","2016-09-23 14:00","취소","취소","연속",null,null,"계통안정",201607150070,"-"]
[52,"인천","직할","신부평S/S #62 M.Tr A","신부평S/S 154kV #62M.Tr 정밀점검","신부평S/S 154kV #62M.Tr 정밀점검","2016-09-22 08:00","2016-09-24 18:00","취소","취소","연속",null,null,"한전요청",201607150069,"-"]
[53,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 154kV #62M.Tr 정밀점검","신부평S/S 154kV #62M.Tr 정밀점검","2016-09-23 14:00","2016-09-24 18:00","취소","취소","연속",null,null,"계통안정",201607150071,"-"]
[54,"인천","직할","신부평S/S 154kV #2 BUS TIE GIS","신부평S/S 154kV 6200GIS 정밀점검","신부평S/S 154kV 6200GIS 정밀점검","2016-09-29 08:00","2016-09-30 18:00","취소","취소","연속",null,null,"한전요청",201607150087,"-"]
[55,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 154kV 신부평-중동#1T/L 정밀점검","신부평S/S 154kV 신부평-중동#1T/L 정밀점검","2016-09-05 08:00","2016-09-06 14:00","취소","취소","연속",null,null,"계통안정",201607150080,"-"]
[56,"인천","직할","신부평중동#1 T/L","신부평S/S 154kV 신부평-중동#1T/L 정밀점검","신부평S/S 154kV 신부평-중동#1T/L 정밀점검","2016-09-05 08:00","2016-09-07 18:00","취소","취소","연속",null,null,"한전요청",201607150079,"-"]
[57,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 154kV 신부평-중동#1T/L 정밀점검","신부평S/S 154kV 신부평-중동#1T/L 정밀점검","2016-09-06 14:00","2016-09-07 18:00","취소","취소","연속",null,null,"계통안정",201607150081,"-"]
[58,"인천","직할","신부평부천#1 T/L","신부평S/S 154kV 신부평-부천#1T/L 정밀점검","신부평S/S 154kV 신부평-부천#1T/L 정밀점검","2016-09-08 08:00","2016-09-10 18:00","취소","취소","연속",null,null,"한전요청",201607150072,"-"]
[59,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 154kV 6100GIS 정밀점검","신부평S/S 154kV 6100GIS 정밀점검","2016-09-27 08:00","2016-09-28 10:00","취소","취소","연속",null,null,"계통안정",201607150084,"-"]
[60,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 154kV 신부평-부천#2T/L 정밀점검","신부평S/S 154kV 신부평-부천#2T/L 정밀점검","2016-09-20 14:00","2016-09-21 18:00","취소","취소","연속",null,null,"계통안정",201607150078,"-"]
[61,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 154kV 신부평-부천#2T/L 정밀점검","신부평S/S 154kV 신부평-부천#2T/L 정밀점검","2016-09-19 08:00","2016-09-20 14:00","취소","취소","연속",null,null,"계통안정",201607150077,"-"]
[62,"인천","직할","신부평부천#2 T/L","신부평S/S 154kV 신부평-부천#2T/L 정밀점검","신부평S/S 154kV 신부평-부천#2T/L 정밀점검","2016-09-19 08:00","2016-09-21 18:00","취소","취소","연속",null,null,"한전요청",201607150076,"-"]
[63,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 154kV 신부평-부천#1T/L 정밀점검","신부평S/S 154kV 신부평-부천#1T/L 정밀점검","2016-09-09 14:00","2016-09-10 18:00","취소","취소","연속",null,null,"계통안정",201607150074,"-"]
[64,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 154kV 6100GIS 정밀점검","신부평S/S 154kV 6100GIS 정밀점검","2016-09-28 10:00","2016-09-28 18:00","취소","취소","연속",null,null,"계통안정",201607150086,"-"]
[65,"경기북부","구리","가평춘천HP T/L","154kV 가평변전소 모자익배전반 교체공사","모자익배전반교체, 제어,감시용 케이블 교체","2016-09-22 09:00","2016-09-24 18:00","2016-09-22T09:00:00","2016-09-24T18:00:00","연속",null,null,null,201606170089,"-"]
[66,"경기북부","구리","가평화천HP T/L","154kV 가평변전소 모자익배전반 교체공사","모자익배전반교체, 제어,감시용 케이블 교체","2016-09-19 09:00","2016-09-21 18:00","2016-09-19T09:00:00","2016-09-21T18:00:00","연속",null,null,null,201606170088,"-"]
[67,"경기북부","구리","가평청평HP#1 T/L","154kV 가평변전소 모자익배전반 교체공사","모자익배전반교체, 제어,감시용 케이블 교체","2016-09-08 09:00","2016-09-10 18:00","2016-09-08T09:00:00","2016-09-10T18:00:00","연속",null,null,null,201606170087,"-"]
[68,"경기북부","구리","가평청평HP#2 T/L","154kV 가평변전소 모자익배전반 교체공사","모자익배전반교체, 제어,감시용 케이블 교체","2016-09-05 09:00","2016-09-07 18:00","2016-09-05T09:00:00","2016-09-07T18:00:00","연속",null,null,null,201606170086,"-"]
[69,"경기북부","구리","덕소마석#2 T/L","154kV 덕소-마석#2T/L 전선접속개소 전선교체공사","ㅇ 전선접속개소 전선교체 - 구간 : No.9~10,28~29,36~42","2016-09-25 08:00","2016-09-30 18:00","2016-09-25T08:00:00","2016-09-30T18:00:00","연속",null,null,null,201607060076,"-"]
[70,"경기북부","구리","덕소마석#1 T/L","154kV 덕소-마석#1T/L 전선접속개소 전선교체공사","ㅇ 전선접속개소 전선교체 - 구간 : No.5~7,9~10,28~29","2016-09-19 08:00","2016-09-24 18:00","2016-09-19T08:00:00","2016-09-24T18:00:00","연속",null,null,null,201607060075,"○"]
[71,"경기북부","구리","미금광장 T/L","가운지금지구 지장송전선로 지중화공사","ㅇ 철탑 2기 설치 및 철거 ㅇ 지중케이블 포설 : 1.8km","2016-09-04 07:00","2016-09-30 18:00","2016-09-04T07:00:00","2016-09-30T18:00:00","연속",null,null,null,201607260033,"-"]
[72,"경기북부","구리","미금화양 T/L","가운지금지구 지장송전선로 지중화공사","ㅇ 철탑 2기 설치 및 철거 ㅇ 지중케이블 포설 : 1.8km","2016-09-01 07:00","2016-09-03 18:00","2016-09-01T07:00:00","2016-09-03T18:00:00","연속",null,null,null,201607260032,"-"]
[73,"경기북부","구리","별내도봉 T/L","154kV 별내-도봉T/L 전선접속개소 전선교체공사","ㅇ 전선접속개소 전선교체공사 - 구간 : No.11~12","2016-09-05 08:00","2016-09-05 18:00","2016-09-05T08:00:00","2016-09-05T18:00:00","당일",null,null,null,201607060078,"○"]
[75,"경기북부","구리","도봉진접 T/L","154kV 도봉-진접T/L 전선접속개소 전선교체공사","ㅇ 전선접속개소 전선교체공사 - 구간 : No.11~12","2016-09-05 08:00","2016-09-05 18:00","2016-09-06T08:00:00","2016-09-06T18:00:00","당일",null,null,"한전요청",201605030070,"-"]
[74,"경기북부","구리","신포천S/S 154kV #66 BUS","신포천-덕계 #1T/L 672DS 가스 누기 보수","신포천-덕계 #1T/L 672DS 가스 누기 보수 - UHF센서(누기부) 교체","2016-09-01 09:00","2016-09-02 18:00","2016-09-22T09:00:00","2016-09-23T18:00:00","연속",null,null,"한전요청",201607060079,"-"]
[76,"경기북부","구리","서홍천청평PP T/L","서홍천청평P/P T/P #2DS 불량보수","○서홍천청평P/P T/P #2DS 전동조작 불량보수 - 발청된 커넥터 교체","2016-09-06 09:00","2016-09-06 18:00","2016-09-06T09:00:00","2016-09-06T18:00:00","당일",null,null,null,201607080020,"-"]
[77,"경기북부","직할","신의정부용현#1 T/L","경보창구보완 및 경보회로 변경","신의정부S/S : LCP PNL 경보창구 보완 및 보호배전반 경보회로수정 용현S/S : 보호배전반 경보회로수정","2016-09-06 10:00","2016-09-06 18:00","2016-09-06T10:00:00","2016-09-06T18:00:00","당일",null,null,null,201607150043,"-"]
[78,"경기북부","직할","신의정부용현#2 T/L","경보창구보완 및 경보회로 변경","신의정부S/S : LCP PNL 경보창구 보완","2016-09-07 10:00","2016-09-07 14:00","2016-09-07T10:00:00","2016-09-07T14:00:00","당일",null,null,null,201607150046,"-"]
[79,"경기북부","직할","신의정부S/S 154kV #1 BUS TIE GIS","경보창구보완 및 경보회로 변경","신의정부S/S : LCP PNL 경보창구 보완","2016-09-07 14:00","2016-09-07 18:00","2016-09-07T14:00:00","2016-09-07T18:00:00","당일",null,null,null,201607150049,"-"]
[80,"경기북부","직할","신의정부S/S 60-61 SEC GIS","경보창구보완 및 경보회로 변경","신의정부S/S : LCP PNL 경보창구 보완","2016-09-08 10:00","2016-09-08 14:00","2016-09-08T10:00:00","2016-09-08T14:00:00","당일",null,null,null,201607150051,"-"]
[81,"경기북부","직할","신의정부S/S 65-66 SEC GIS","경보창구보완 및 경보회로 변경","신의정부S/S : LCP PNL 경보창구 보완","2016-09-08 14:00","2016-09-08 18:00","2016-09-08T14:00:00","2016-09-08T18:00:00","당일",null,null,null,201607150052,"-"]
[82,"경기북부","직할","신의정부S/S 154kV #2 BUS TIE GIS","경보창구보완 및 경보회로 변경","신의정부S/S : LCP PNL 경보창구 보완","2016-09-09 10:00","2016-09-09 14:00","2016-09-09T10:00:00","2016-09-09T14:00:00","당일",null,null,null,201607150057,"-"]
[83,"경기북부","직할","신의정부내촌#2 T/L","경보창구보완 및 경보회로 변경","신의정부S/S : LCP PNL 경보창구 보완","2016-09-09 14:00","2016-09-09 18:00","2016-09-09T14:00:00","2016-09-09T18:00:00","당일",null,null,null,201607150058,"-"]
[84,"경기북부","직할","신의정부S/S 154kV #3 BUS TIE GIS","경보창구보완 및 경보회로 변경","신의정부S/S : LCP PNL 경보창구 보완 및 DS 조작회로 점검","2016-09-12 10:00","2016-09-12 14:00","2016-09-12T10:00:00","2016-09-12T14:00:00","당일",null,null,null,201607150062,"-"]
[85,"경기북부","직할","양주쌍문#1 T/L","양주쌍문#1 T/L","2016년 직할변전협력회사 총액공사 - GIS 가스누기 보수","2016-09-01 10:00","2016-09-01 18:00","2016-09-01T10:00:00","2016-09-01T18:00:00","당일",null,null,null,201607140029,"○"]
[86,"경기북부","직할","양주고양#2 T/L","양주고양#2 T/L","2016년 직할변전협력회사 총액공사 - GIS 가스누기 보수","2016-09-02 10:00","2016-09-02 18:00","2016-09-02T10:00:00","2016-09-02T18:00:00","당일",null,null,null,201607140129,"○"]
[87,"경기북부","직할","양주S/S 154kV #61 BUS","양주S/S 154kV #61 BUS","2016년 직할변전협력회사 총액공사 -모선 접속개소 과열보수","2016-09-12 10:00","2016-09-12 14:00","2016-09-12T10:00:00","2016-09-12T14:00:00","당일",null,null,null,201607140125,"-"]
[88,"경기북부","직할","양주S/S 154kV #66 BUS","양주S/S 154kV #66 BUS","2016년 직할변전협력회사 총액공사 -모선 접속개소 과열보수","2016-09-12 14:00","2016-09-12 18:00","2016-09-12T14:00:00","2016-09-12T18:00:00","당일",null,null,null,201607140126,"-"]
[89,"경기북부","직할","양주S/S 154kV #62 BUS","양주S/S 154kV #62 BUS","2016년 직할변전협력회사 총액공사 -모선 접속개소 과열보수","2016-09-26 10:00","2016-09-26 14:00","2016-09-26T10:00:00","2016-09-26T14:00:00","당일",null,null,null,201607140128,"-"]
[90,"경기북부","직할","양주S/S 154kV #67 BUS","양주S/S 154kV #67 BUS","2016년 직할변전협력회사 총액공사 -모선 접속개소 과열보수","2016-09-26 14:00","2016-09-26 18:00","2016-09-26T14:00:00","2016-09-26T18:00:00","당일",null,null,null,201607140127,"-"]
[91,"경기북부","직할","양주S/S 154kV #65 BUS","양주S/S 154kV #65 BUS","2016년 직할변전협력회사 총액공사 -모선 접속개소 과열보수","2016-09-27 10:00","2016-09-27 18:00","2016-09-27T10:00:00","2016-09-27T18:00:00","당일",null,null,null,201607140036,"-"]
[92,"경기북부","직할","양주S/S 65-66-0 SEC CB","변전총액공사 (양주S/S #1모선보호반 교체 - 65-66-0 B/S)","변전총액공사 (양주S/S #1모선보호반 교체 - 65-66-0 B/S)","2016-09-05 10:00","2016-09-09 18:00","2016-09-05T10:00:00","2016-09-09T18:00:00","연속",null,null,null,201607140026,"-"]
[93,"경기북부","직할","양주S/S 154kV #1 BUS TIE CB","변전총액공사 (양주S/S #1모선보호반 교체 - 6100 B/T)","변전총액공사 (양주S/S #1모선보호반 교체 - 6100 B/T)","2016-09-05 10:00","2016-09-09 18:00","2016-09-05T10:00:00","2016-09-09T18:00:00","연속",null,null,null,201607130144,"-"]
[94,"경기북부","직할","양주S/S 60-61-0 SEC CB","변전총액공사 (양주S/S #1모선보호반 교체 - 60-61-0 B/S)","변전총액공사 (양주S/S #1모선보호반 교체 - 60-61-0 B/S)","2016-09-08 10:00","2016-09-09 18:00","2016-09-08T10:00:00","2016-09-09T18:00:00","연속",null,null,null,201607140028,"-"]
[95,"경기북부","직할","양주S/S 66-67-0 SEC CB","변전총액공사 (양주S/S #2모선보호반 교체 - 66-67-0 B/S)","변전총액공사 (양주S/S #2모선보호반 교체 - 66-67-0 B/S)","2016-09-19 10:00","2016-09-23 18:00","2016-09-19T10:00:00","2016-09-23T18:00:00","연속",null,null,null,201607140032,"-"]
[96,"경기북부","직할","양주S/S 65-66-0 SEC CB","변전총액공사 (양주S/S #2모선보호반 교체 - 65-66-0 B/S)","변전총액공사 (양주S/S #2모선보호반 교체 - 65-66-0 B/S)","2016-09-19 10:00","2016-09-23 18:00","2016-09-19T10:00:00","2016-09-23T18:00:00","연속",null,null,null,201607140030,"-"]
[97,"경기북부","직할","양주S/S 154kV #60 BUS","양주S/S 154kV #60 BUS","2016년 직할변전협력회사 총액공사 - GIS 가스누기 보수 및 모선 접속개소 과열보수","2016-09-01 10:00","2016-09-01 18:00","2016-09-04T10:00:00","2016-09-04T18:00:00","당일",null,null,"계통안정",201607140035,"-"]
[98,"경기북부","파주","고양일산#1 T/L","일산S/S 154kV 65-66SEC 정밀점검공사(안전이격확보)","일산S/S 154kV 65-66SEC 정밀점검공사(안전이격확보) 고양S/S 154kV 고양일산#1T/L GIS 초기점검(총액공사)","2016-09-03 10:00","2016-09-04 17:00","2016-09-03T10:00:00","2016-09-04T17:00:00","당일",null,null,null,201607130152,"○"]
[99,"경기북부","파주","고양일산#2 T/L","고양S/S 154kV 고양일산#2T/L GIS 초기점검공사","고양S/S 154kV 고양일산#2T/L GIS 초기점검(총액공사)","2016-09-27 10:00","2016-09-27 17:00","2016-09-27T10:00:00","2016-09-27T17:00:00","당일",null,null,null,201607130153,"-"]
[100,"경기북부","파주","월롱금촌#1 T/L","금촌S/S 월롱-금촌#1T/L GIS 전자변 교체(총액공사)","금촌S/S 월롱-금촌#1T/L GIS 전자변 교체(총액공사)","2016-09-20 10:00","2016-09-20 17:00","2016-09-20T10:00:00","2016-09-20T17:00:00","당일",null,null,null,201607140087,"-"]
[101,"경기북부","파주","신파주금촌#1 T/L","금촌S/S 신파주-금촌#1T/L GIS 전자변 교체(총액공사)","금촌S/S 신파주-금촌#1T/L GIS 전자변 교체(총액공사)","2016-09-08 10:00","2016-09-08 17:00","2016-09-08T10:00:00","2016-09-08T17:00:00","당일",null,null,null,201607140084,"-"]
[102,"경기북부","파주","월롱금촌#2 T/L","금촌S/S 월롱-금촌#2T/L GIS 전자변 교체(총액공사)","금촌S/S 월롱-금촌#2T/L GIS 전자변 교체(총액공사)","2016-09-22 10:00","2016-09-22 17:00","2016-09-22T10:00:00","2016-09-22T17:00:00","당일",null,null,null,201607140090,"-"]
[103,"경기북부","파주","일산S/S 154kV #61 BUS","2016년 파주전력지사 장기사용 170kV GIS 교체공사","일산S/S 170kV GIS(#61-66BUS PT) 철거, 설치","2016-09-04 08:30","2016-09-07 08:00","2016-09-04T08:30:00","2016-09-07T08:00:00","연속",null,null,null,201607140079,"-"]
[104,"경기북부","파주","일산S/S 154kV #66 BUS","2016년 파주전력지사 장기사용 170kV GIS 교체공사","일산S/S 170kV GIS(#61-66BUS PT) 철거, 설치","2016-09-03 08:00","2016-09-04 08:00","2016-09-03T08:00:00","2016-09-04T08:00:00","연속",null,null,null,201607140077,"-"]
[105,"경기북부","파주","일산S/S 154kV #66 BUS","2016년 파주전력지사 장기사용 170kV GIS 교체공사","일산S/S 170kV GIS(#61-66BUS PT) 철거, 설치","2016-09-09 08:00","2016-09-13 08:00","2016-09-09T08:00:00","2016-09-13T08:00:00","연속",null,null,null,201607140078,"-"]
[106,"경기북부","파주","일산S/S 154kV #60 BUS","일산S/S 154kV 60-61SEC GIS 정밀점검공사","일산S/S 154kV 60-61SEC GIS 정밀점검공사","2016-09-07 09:00","2016-09-08 18:00","2016-09-07T09:00:00","2016-09-08T18:00:00","연속",null,null,null,201607140081,"-"]
[107,"경기북부","파주","일산S/S 154kV #61-66 PT GIS","2016년 파주전력지사 장기사용 170kV GIS 교체공사","일산S/S 170kV GIS(#61-66BUS PT) 철거, 설치","2016-09-03 08:00","2016-09-13 18:00","2016-09-03T08:00:00","2016-09-13T18:00:00","연속",null,null,null,201607140073,"-"]
[108,"경기북부","파주","일산S/S 154kV #65 BUS","일산S/S 154kV 65-66SEC GIS 정밀점검공사","일산S/S 154kV 65-66SEC GIS 정밀점검공사","2016-09-01 09:00","2016-09-02 18:00","2016-09-01T09:00:00","2016-09-02T18:00:00","연속",null,null,null,201607140080,"-"]
[109,"경기북부","파주","지도S/S 154kV #1 BUS TIE GIS","2016년 파주전력지사 장기사용 170kV GIS 교체공사","지도S/S 170kV GIS 철거, 설치 - 일산지도#2T/L, #1M.Tr 1차, B/T, PT&ES","2016-09-19 08:00","2016-10-30 18:00","2016-09-19T08:00:00","2016-10-30T18:00:00","연속",null,null,null,201607140086,"-"]
[110,"경기북부","파주","지도능곡#2 T/L","154kV 송전선로 보호반 교체공사","154kV 송전선로 보호반 교체","2016-09-07 09:30","2016-09-09 18:00","2016-09-07T09:30:00","2016-09-09T18:00:00","연속",null,null,null,201607140059,"-"]
[111,"경기북부","파주","지도능곡#1 T/L","154kV 송전선로 보호반 교체공사","154kV 송전선로 보호반 교체","2016-09-04 09:30","2016-09-06 18:00","2016-09-04T09:30:00","2016-09-06T18:00:00","연속",null,null,null,201607140057,"-"]
[112,"경기북부","파주","일산지도#2 T/L","2016년 파주전력지사 장기사용 170kV GIS 교체공사","지도S/S 170kV GIS 교체공사 - 일산지도#2T/L, #1M.Tr 1차, B/T, PT&ES","2016-09-19 08:00","2016-10-30 18:00","2016-09-19T08:00:00","2016-10-30T18:00:00","연속",null,null,null,201607140106,"-"]
[113,"경기북부","파주","지도S/S 154kV BUS PT GIS","2016년 파주전력지사 장기사용 170kV GIS 교체공사","지도S/S 170kV GIS 철거, 설치 - 일산지도#2T/L, #1M.Tr 1차, B/T, PT&ES","2016-09-19 08:00","2016-10-30 18:00","2016-09-19T08:00:00","2016-10-30T18:00:00","연속",null,null,null,201607140089,"-"]
[114,"경기북부","파주","지도S/S 154kV #1 BUS","2016년 파주전력지사 장기사용 170kV GIS 교체공사","지도S/S 170kV GIS 철거, 설치 - 일산지도#2T/L, #1M.Tr 1차, B/T, PT&ES","2016-09-19 08:00","2016-09-27 18:00","2016-09-19T08:00:00","2016-09-27T18:00:00","연속",null,null,null,201607140092,"-"]
[115,"경기북부","파주","지도S/S 154kV #2 BUS","2016년 파주전력지사 장기사용 170kV GIS 교체공사","지도S/S 170kV GIS 철거, 설치 - 일산지도#2T/L, #1M.Tr 1차, B/T, PT&ES","2016-09-28 08:00","2016-10-30 18:00","2016-09-28T08:00:00","2016-10-30T18:00:00","연속",null,null,null,201607140094,"-"]
[116,"경기","군포","서서울남수원#2 T/L","서서울S/S 154kV CVT,LA 이설공사","서서울S/S 154kV CVT,LA 이설공사 - 서서울S/S 154kV 12개T/L BAY(9 ~10월 순차적이설) - CVT 1상 12개T/L = 12EA - LA 3상 12개T/L = 36EA","2016-09-27 07:00","2016-10-01 07:00","2016-09-27 07:00","2016-10-01 07:00","연속",null,null,null,201607110465,"-"]
[117,"경기","군포","서서울남수원#1 T/L","서서울S/S 154kV CVT,LA 이설공사","서서울S/S 154kV CVT,LA 이설공사 - 서서울S/S 154kV 12개T/L BAY(9 ~10월 순차적이설) - CVT 1상 12개T/L = 12EA - LA 3상 12개T/L = 36EA","2016-09-23 07:00","2016-09-27 07:00","2016-09-23 07:00","2016-09-27 07:00","연속",null,null,null,201607110471,"-"]
[118,"경기","군포","신안산남안산#2 T/L","신안산SS Mosaic 대체 공사","신안산SS Mosaic 대체 공사 - 신안산남안산#2 T/L 조작, 감시회로 이설","2016-09-26 09:00","2016-09-29 18:00","2016-09-26 09:00","2016-09-29 18:00","연속",null,null,null,201607110561,"-"]
[119,"경기","군포","신안산남안산#1 T/L","신안산SS Mosaic 대체 공사","신안산SS Mosaic 대체 공사 - 신안산남안산#1 T/L 조작, 감시회로 이설","2016-09-20 09:00","2016-09-23 18:00","2016-09-20 09:00","2016-09-23 18:00","연속",null,null,null,201607110562,"-"]
[120,"경기","동부","이천가남#2 T/L","16년 동부 변전협력회사 총액공사","가남S/S 이천-가남#2T/L GIS 보통점검","2016-09-02 09:00","2016-09-02 18:00","2016-09-02 09:00","2016-09-02 18:00","당일",null,null,null,201607040015,"-"]
[121,"경기","동부","이천가남#1 T/L","154kV 이천-가남#1T/L 초기점검",".14년도 지장이설구간 초기점검(7-1호 등 5기)","2016-09-01 10:00","2016-09-01 18:00","2016-09-01 10:00","2016-09-01 18:00","당일",null,null,null,201607110417,"-"]
[122,"경기","동부","곤지암초월#2 T/L","16년 동부 변전협력회사 총액공사","초월S/S 곤지암-초월#2T/L CVT,LA대체","2016-09-21 09:00","2016-09-21 18:00","2016-09-21 09:00","2016-09-21 18:00","당일",null,null,null,201607040014,"-"]
[123,"경기","동부","곤지암초월#1 T/L","16년 동부 변전협력회사 총액공사","초월S/S 곤지암-초월#1T/L GIS 보통점검, CVT,LA대체","2016-09-20 09:00","2016-09-20 18:00","2016-09-20 09:00","2016-09-20 18:00","당일",null,null,null,201607040013,"-"]
[124,"경기","성남","서판교중원#2 T/L","성남-장호원 도로개설에 따른 지장송전선로 이설공사","케이블 철거 및 신규포설 2구간 케이블 접속 3개소(NJ2, IJ1)","2016-09-20 09:00","2016-10-07 18:00","2016-09-20 09:00","2016-10-07 18:00","연속",null,null,null,201607190144,"-"]
[125,"경기","성남","율현용인#1 T/L","154kV 용인S/S 무인화대비 설비보강공사","154kV 용인S/S GIS 설치공사","2016-09-01 09:00","2016-09-13 18:00","2016-09-01 09:00","2016-09-13 18:00","연속",null,null,null,201607110377,"-"]
[126,"경기","성남","모현용인#2 T/L","154kV 용인S/S 무인화대비 설비보강공사","154kV 용인S/S GIS 설치공사","2016-09-05 09:00","2016-09-09 18:00","2016-09-05 09:00","2016-09-09 18:00","연속",null,null,null,201607110379,"-"]
[127,"경기","성남","율현용인#2 T/L","154kV 용인S/S 무인화대비 설비보강공사","154kV 용인S/S GIS 설치공사","2016-09-19 09:00","2016-10-03 18:00","2016-09-19 09:00","2016-10-03 18:00","연속",null,null,null,201607110385,"-"]
[128,"경기","성남","모현용인#2 T/L","154kV 용인S/S 무인화대비 설비보강공사","154kV 용인S/S GIS 설치공사","2016-09-19 09:00","2016-09-23 18:00","2016-09-19 09:00","2016-09-23 18:00","연속",null,null,null,201607110382,"-"]
[129,"경기","직할","발안구문천#2 T/L","154kV 발안구문천#2T/L 송전선로 정밀점검(구간 No.1~22)","16년 가공송전선로 순시점검 위탁공사 154kV 발안구문천#2T/L 송전선로 정밀점검(구간 No.1~22)","2016-09-21 09:00","2016-09-22 18:00","2016-09-21 09:00","2016-09-22 18:00","매일",null,null,null,201607110373,"-"]
[130,"경기","직할","발안구문천#1 T/L","154kV 발안구문천#1T/L 송전선로 정밀점검(구간 No.1~22)","16년 가공송전선로 순시점검 위탁공사 154kV 발안구문천#1T/L 송전선로 정밀점검(구간 No.1~22)","2016-09-19 09:00","2016-09-20 18:00","2016-09-19 09:00","2016-09-20 18:00","매일",null,null,null,201607110372,"-"]
[131,"경기","직할","안열#1T/L T/L","지중송전 위탁정비 OF케이블 절연유 점검","OF케이블 절연유 채취","2016-09-26 09:00","2016-09-27 18:00","2016-09-26 09:00","2016-09-27 18:00","연속",null,null,null,201607040010,"-"]
[132,"경기","직할","안열#2T/L T/L","지중송전 위탁정비 OF케이블 절연유 점검","OF케이블 절연유 채취","2016-09-28 09:00","2016-09-29 18:00","2016-09-28 09:00","2016-09-29 18:00","연속",null,null,null,201607040011,"-"]
[133,"경기","평택","만호S/S 154kV 만호-포승T/L GIS","만호S/S 만호-포승T/L GIS 초기점검","만호S/S 만호-포승T/L GIS 초기점검","2016-09-05 10:00","2016-09-05 18:00","2016-09-05 10:00","2016-09-05 18:00","당일",null,null,null,201607070003,"-"]
[134,"경기","평택","소사벌안성 T/L","154kV 소사벌-안성T/L 가공송전선로 정밀점검","154kV 소사벌-안성T/L 가공송전선로 정밀점검(44기)","2016-09-09 09:00","2016-09-11 18:00","2016-09-09 09:00","2016-09-11 18:00","매일",null,null,null,201607080360,"-"]
[135,"경기","평택","송탄오성CC#2 T/L","345kV 고덕S/S 건설공사","○ 송탄S/S : 송탄-오성CC #2T/L 보호반 철거 및 신설 ○ 고덕S/S : 송탄S/S 철거보호반 이설 설치 ○ 154kV 송탄-오성CC #2T/L 1π 분기 - 고덕-송탄, 고덕-오성CC 임시선로 구성 ○ 고덕-송탄, 고덕-오성CC 간 OPGW 포설 및 접속 ○ 고덕-평택, 송탄, 오성CC 광단국장치 개통 ○ 고덕-송탄, 오성CC PITR 회선구성","2016-09-21 09:00","2016-09-30 18:00","취소","취소","연속",null,null,"한전요청",201607060092,"-"]
[136,"경기","평택","송탄S/S 송탄-오성복합#2T/L(617) GIS","송탄S/S 송탄-오성복합#2T/L 장기사용 GIS 대체","송탄S/S 송탄-오성복합#2T/L 장기사용 GIS 대체","2016-09-22 09:00","2016-10-10 18:00","취소","취소","연속",null,null,"한전요청",201607140116,"-"]
[137,"경기","평택","포승청북#2 T/L","포승-청북 등 2개T/L 상간스페이서 설치공사","○ 154kV 청북-평택#1T/L, 포승-청북#2T/L 3경간 상간스페이서설치","2016-09-24 08:00","2016-09-25 18:00","2016-09-24 08:00","2016-09-25 18:00","매일",null,null,null,201607070140,"-"]
[138,"경기","평택","청북평택#1 T/L","포승-청북 등 2개T/L 상간스페이서 설치공사","○ 154kV 청북-평택#1T/L, 포승-청북#2T/L 3경간 상간스페이서설치","2016-09-24 08:00","2016-09-25 18:00","2016-09-24 08:00","2016-09-25 18:00","매일",null,null,null,201607070142,"-"]
[139,"경기","평택","둔포추팔#2 T/L","154kV 둔포-추팔T/L 애자교체공사","154kV 둔포-추팔#2T/L No.3,20 애자교체","2016-09-20 08:00","2016-09-20 18:00","2016-09-20 08:00","2016-09-20 18:00","당일",null,null,null,201607120094,"-"]
[140,"강원","강릉","속초간성#2 T/L","2016년-17년 변전협력회사 총액공사","속초간성#2T/L GIS 보통점검(속초)","2016-09-05 09:00","2016-09-05 18:00","2016-09-05 09:00","2016-09-05 18:00","당일",null,null,null,201607070148,"-"]
[141,"강원","강릉","속초간성#1 T/L","2016년-17년 변전협력회사 총액공사","1. 속초간성#1T/L GIS 보통점검(속초, 간성) 2. 속초간성#1T/L 피뢰기 보통점검(간성)","2016-09-01 09:00","2016-09-02 18:00","2016-09-01 09:00","2016-09-02 18:00","매일",null,null,null,201607070138,"-"]
[142,"강원","강릉","주문진양양#1 T/L","양양변전소 외장재 교체공사","- 드라이비트 철거 - 벽체, 난간 지지철물 및 메탈판넬 설치","2016-09-08 09:00","2016-09-23 18:00","2016-09-08 09:00","2016-09-23 18:00","매일",null,null,null,201607070129,"-"]
[143,"강원","강릉","신양양_양양#1 T/L","양양변전소 외장재 교체공사","- 드라이비트 철거 - 벽체, 난간 지지철물 및 메탈판넬 설치","2016-09-24 09:00","2016-10-02 18:00","2016-09-24 09:00","2016-10-02 18:00","연속",null,null,null,201607070159,"-"]
[144,"강원","강릉","주문진양양#2 T/L","양양변전소 외장재 교체공사","- 드라이비트 철거 - 벽체, 난간 지지철물 및 메탈판넬 설치","2016-09-01 09:00","2016-09-10 18:00","2016-09-01 09:00","2016-09-10 18:00","매일",null,null,null,201607070126,"-"]
[145,"강원","강릉","신제천주진#1 T/L","2016년 가공송전 순시점검 위탁공사","* 세부작업명 : 송전선로용 피뢰기 이설작업 - 작업대상 : 154kV 신제천-주진#1T/L No.92~93 - 작업내용 : 피뢰기 철거 및 아킹혼 취부","2016-09-21 09:00","2016-09-21 18:00","2016-09-21 09:00","2016-09-21 18:00","당일",null,null,null,201607040084,"-"]
[146,"강원","강릉","신제천주진#2 T/L","2016년 가공송전 순시점검 위탁공사","* 세부작업명 : 송전선로용 피뢰기 이설작업 - 작업대상 : 154kV 신제천-주진#2T/L No.92~93 - 작업내용 : 피뢰기 설치 및 아킹혼 철거","2016-09-22 09:00","2016-09-22 18:00","2016-09-22 09:00","2016-09-22 18:00","당일",null,null,null,201607040085,"-"]
[147,"강원","강릉","강릉횡계#1 T/L","횡계S/S 외장재 교체공사","- 드라이비트 철거 - 벽체, 난간 지지철물 및 메탈판넬 설치","2016-09-04 09:00","2016-09-13 18:00","2016-09-04 09:00","2016-09-13 18:00","매일",null,null,null,201607070162,"-"]
[148,"강원","강릉","강릉횡계#2 T/L","횡계S/S 외장재 교체공사","- 드라이비트 철거 - 벽체, 난간 지지철물 및 메탈판넬 설치","2016-09-11 09:00","2016-09-26 18:00","2016-09-11 09:00","2016-09-26 18:00","매일",null,null,null,201607070165,"-"]
[149,"강원","강릉","횡계평창#1 T/L","2016년-17년 변전협력회사 총액공사","횡계평창#1T/L GIS 보통점검(횡계, 평창)","2016-09-27 09:00","2016-09-28 18:00","2016-09-27 09:00","2016-09-28 18:00","매일",null,null,null,201607070156,"-"]
[150,"강원","강릉","횡계평창#2 T/L","2016년-17년 변전협력회사 총액공사","1. 횡계평창#2T/L GIS 보통점검(횡계, 평창) 2. 횡계평창#2T/L 피뢰기 보통점검(평창)","2016-09-29 09:00","2016-09-30 18:00","2016-09-29 09:00","2016-09-30 18:00","매일",null,null,null,201607070160,"-"]
[151,"강원","동해","삼척GP S/S 154KV #66 BUS","삼척GP S/Y 154kV 삼척LNG T/L 신규수용공사","삼척LNG T/L 신규수용 154kV GIS 1CCT 증설 및 부대공사","2016-09-07 09:00","2016-09-11 18:00","2016-09-07 09:00","2016-09-11 18:00","매일",null,null,null,201607260024,"-"]
[152,"강원","동해","삼척GP S/S 154KV #61 BUS","삼척GP S/Y 154kV 삼척LNG T/L 신규수용공사","삼척LNG T/L 신규수용 154kV GIS 1CCT 증설 및 부대공사","2016-09-02 09:00","2016-09-06 18:00","2016-09-02 09:00","2016-09-06 18:00","매일",null,null,null,201607260023,"-"]
[153,"강원","원주","여주문막#1 T/L","문막S/S 170kV 장기사용 GIS 대체공사","- 170kV GIS 철거/설치 X 5Bay(여주-문막#1,2T/L, #1,2M.Tr, BUS TIE) - 170kV PT&ES GIS 철거/설치 X 1Set","2016-09-21 09:00","2016-10-11 18:00","2016-09-21 09:00","2016-10-11 18:00","연속",null,null,null,201607050030,"-"]
[154,"강원","원주","홍천S/S 154kV #1 BUS","홍천변전소 170kV GIS 설치공사","154kV #1BUS 하단 170kV GIS 설치","2016-09-05 09:00","2017-03-31 18:00","2016-09-05 09:00","2017-03-31 18:00","연속",null,null,null,201607050021,"-"]
[155,"강원","원주","횡성홍천#2 T/L","홍천변전소 170kV GIS 설치공사","○ #4M.Tr 1차측 모선정비(GIS 모선연결용) - 활선이격거리 확보로 횡성홍천#2TL 휴전","2016-09-01 09:00","2016-09-02 18:00","2016-09-01 09:00","2016-09-02 18:00","연속",null,null,null,201607050022,"-"]
[156,"강원","직할","남춘천서홍천 T/L","춘천집단에너지 154kV 송전선로 건설공사","청평양수#3,4T/L 70호 보강 및 1호 신설 및 계통 연계","2016-09-19 09:00","2016-10-02 18:00","2016-09-19 09:00","2016-10-02 18:00","연속",null,null,null,201607040051,"-"]
[157,"강원","직할","화천H/P 154kV #2 BUS","화천H/P 154kV #2BUS CVT B상 교체공사","화천H/P 154kV #2BUS CVT B상 누유로 인한 교체공사 시행","2016-09-08 09:30","2016-09-09 13:00","2016-09-08 09:30","2016-09-09 13:00","매일",null,null,null,201607180100,"-"]
[158,"강원","직할","상남인제#1 T/L","154kV 인제-양구T/L 용량증대 전력선 교체공사 안전확보","154kV 인제-양구T/L 전구간 용량증대 전력선 교체공사 (인제-양구#1T/L 휴전작업안전확보)","2016-09-21 07:00","2016-09-24 18:00","2016-09-21 07:00","2016-09-24 18:00","매일",null,null,null,201607220012,"-"]
[159,"강원","직할","가평화천HP T/L","2016년 장기사용 기타노후설비 대체 공사","2016년 장기사용 기타노후설비 대체공사 - 가평화천HP T/L Line PT","2016-09-06 09:30","2016-09-06 18:00","2016-09-06 09:30","2016-09-06 18:00","당일",null,null,null,201607060071,"-"]
[160,"강원","직할","북춘천화천HP T/L","2016년 장기사용 기타노후설비 대체 공사","2016년 장기사용 기타노후설비 대체공사 - 북춘천화천HP T/L Line PT","2016-09-07 09:30","2016-09-07 18:00","2016-09-07 09:30","2016-09-07 18:00","당일",null,null,null,201607060072,"-"]
[161,"강원","직할","화천H/P 154kV #1 BUS","2016-17 강원지역본부 직할 협력회사 총액공사 기기점검","1.#1M.Tr 2차 DS A 2.#1M.Tr 2차 DS B 보통점검","2016-09-09 14:00","2016-09-09 18:00","2016-09-09 14:00","2016-09-09 18:00","당일",null,null,null,201607060144,"-"]
[162,"강원","태백","신제천-영월CC#1 T/L","'16~'17년 변전정비 협력회사 총액공사","영월CC 신제천-영월CC#1T/L 하자점검","2016-09-28 09:00","2016-09-28 18:00","2016-09-28 09:00","2016-09-28 18:00","당일",null,null,null,201607070009,"-"]
[163,"강원","태백","신제천-영월CC#2 T/L","'16~'17년 변전정비 협력회사 총액공사","영월CC 신제천-영월CC#2T/L 하자점검","2016-09-29 09:00","2016-09-29 18:00","2016-09-29 09:00","2016-09-29 18:00","당일",null,null,null,201607070011,"-"]
[164,"강원","태백","정선영월 T/L","2016~17년 충북지역본부 직할 송전정비 협력회사 총액공사","154kV 신제천-영월CCT/L 4회선 구간 작업에 따른 안전조치 시행 - 작업구간 : 154kV 신제천-영월CCT/L 1~3호 - 작업내용 : 조류착지방지장치 설치","2016-09-03 08:00","2016-09-03 18:00","2016-09-03 08:00","2016-09-03 18:00","당일",null,null,null,201607110378,"-"]
[165,"강원","태백","고한영월 T/L","'16~'17년 태백P/O 송전정비 총액공사","154kV 고한-영월T/L 피뢰기 설치공사 No.1~79(106기)","2016-09-01 08:00","2016-09-06 18:00","2016-09-01 08:00","2016-09-06 18:00","매일",null,null,null,201607120131,"-"]
[166,"강원","태백","태백영월 T/L","'16~'17년 변전정비 협력회사 총액공사","태백S/S 태백-영월T/L LA 교체공사","2016-09-12 09:00","2016-09-12 18:00","2016-09-12 09:00","2016-09-12 18:00","당일",null,null,null,201607070014,"-"]
[167,"강원","태백","태백고한 T/L","'16~17년 태백P/O송전정비 총액공사","154kV 태백-고한T/L 피뢰기설치공사 No.80~114","2016-09-07 08:00","2016-09-10 18:00","2016-09-07 08:00","2016-09-10 18:00","매일",null,null,null,201607080247,"-"]
[168,"충북","직할","신제천주진#2 T/L","345kV 신제천S/S GIS화 공사","신제천-주진#2T/L 인출변경","2016-09-01 08:00","2016-09-05 18:00","2016-09-01 08:00","2016-09-05 18:00","연속",null,null,null,201607260091,"-"]
[169,"충북","청주","서청주사직#1 T/L","16년 하반기 청주전력지사 170kV GIS 정밀점검공사","서청주S/S 서청주사직#1 T/L (677CB, 671, 672DS) 정밀점검","2016-09-23 09:30","2016-09-25 18:00","2016-09-23 09:30","2016-09-25 18:00","연속",null,null,null,201607110271,"-"]
[170,"충북","청주","신옥천S/S 154kV #61 BUS","16년 청주 변전협력회사 총액공사","신옥천S/S 154kV #61 BUS PT 보통점검","2016-09-05 10:00","2016-09-05 18:00","2016-09-05 10:00","2016-09-05 18:00","당일",null,null,null,201607110207,"-"]
[171,"충북","청주","신옥천S/S 154kV #65 BUS","16년 청주 변전협력회사 총액공사","신옥천S/S 154kV #65 BUS LA 보통점검","2016-09-06 10:00","2016-09-06 18:00","2016-09-06 10:00","2016-09-06 18:00","당일",null,null,null,201607110208,"-"]
[172,"충북","청주","청원죽림#1 T/L","16년 하반기 청주전력지사 170kV GIS 정밀점검공사","청원S/S 청원-죽림#1 T/L (637CB, 631, 632DS) 정밀점검","2016-09-30 09:30","2016-10-02 18:00","2016-09-30 09:30","2016-10-02 18:00","연속",null,null,null,201607110274,"-"]
[173,"충북","청주","청주대청HP T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","송전용 피뢰기설치(청주-대청HP) No.18~88(71기)","2016-09-23 09:00","2016-09-30 18:00","2016-09-23 09:00","2016-09-30 18:00","연속",null,null,null,201607110522,"-"]
[174,"충북","충주","금왕남음성#2 T/L","금왕남음성#2T/L 전력량 오차발생 관련 제어IED 점검","금왕남음성#2T/L 제어IED(제작사:세니온) C상 전류 출력값 오차발생관련 AI보드 점검","2016-09-06 08:00","2016-09-06 18:00","2016-09-06 08:00","2016-09-06 18:00","당일",null,null,null,201607260095,"-"]
[175,"충북","충주","서운만승 T/L","2016~17년 충주 송전정비 협력회사 총액공사(불량애자교체 등)","불량애자교체 및 조류착지방지 설치","2016-09-05 08:00","2016-09-05 18:00","2016-09-05 08:00","2016-09-05 18:00","당일",null,null,null,201607120086,"○"]
[176,"충북","충주","진천만승#1 T/L","2016~17년 충주 송전정비 협력회사 총액공사(불량애자교체)","불량애자교체","2016-09-05 08:00","2016-09-05 18:00","2016-09-05 08:00","2016-09-05 18:00","당일",null,null,null,201607120089,"○"]
[177,"충북","충주","충주풍동 T/L","2016~17년 충주 송전정비 협력회사 총액공사(불량애자교체 등)","불량애자교체, 압축인류크램프 교체","2016-09-09 08:00","2016-09-09 18:00","2016-09-09 08:00","2016-09-09 18:00","당일",null,null,null,201607120061,"○"]
[178,"충북","충주","풍동음성#2 T/L","2016~17년 충주 송전정비 협력회사 총액공사(불량애자교체 등)","불량애자교체 및 압축인류크램프 교체","2016-09-06 08:00","2016-09-06 18:00","2016-09-06 08:00","2016-09-06 18:00","당일",null,null,null,201607120085,"○"]
[179,"대전충남","대전","남대전신흥#1 T/L","○ 154kV 남대전-신흥#1T/L 보호반 로직개선","○ 154kV 남대전-신흥#1T/L 보호반 로직개선","2016-09-20 09:00","2016-09-20 13:00","2016-09-21T09:00:00","2016-09-21T13:00:00","당일",null,null,"한전요청",201607070072,"-"]
[180,"대전충남","대전","남대전신흥#3 T/L","○ 154kV 남대전-신흥#3T/L 보호반 로직개선","○ 154kV 남대전-신흥#3T/L 보호반 로직개선","2016-09-21 09:00","2016-09-21 13:00","2016-09-22T09:00:00","2016-09-22T13:00:00","당일",null,null,"한전요청",201607070074,"-"]
[181,"대전충남","대전","남대전신흥#2 T/L","○ 154kV 남대전-신흥#2T/L 보호반 로직개선","○ 154kV 남대전-신흥#2T/L 보호반 로직개선","2016-09-20 14:00","2016-09-20 18:00","2016-09-21T14:00:00","2016-09-21T18:00:00","당일",null,null,"한전요청",201607070073,"-"]
[182,"대전충남","대전","신계룡S/S #61M.Tr(ESS) A","○ 신계룡S/S ESS 2차측 23kV GIS Air 누기보수","○ 신계룡S/S ESS 2차측 23kV GIS Air 누기보수","2016-09-10 09:00","2016-09-13 18:00","2016-09-10T09:00:00","2016-09-13T18:00:00","연속",null,null,null,201607200118,"-"]
[183,"대전충남","서산","서산태안화력 T/L","345kV 신서산-태안화력 등 2개T/L 피뢰기 설치공사","[송전]신당진-태안화력#2T/L No.0-1~127(384set) -아킹혼 철거 -피뢰기 설치","2016-09-19 07:00","2016-09-20 18:00","2016-09-19T07:00:00","2016-09-20T18:00:00","매일",null,null,null,201607080337,"-"]
[184,"대전충남","서산","신당진서산#1 T/L","345kV 신서산-태안화력 등 2개T/L 피뢰기 설치공사","[송전]신당진-태안화력#2T/L No.0-1~127(384set) -아킹혼 철거 -피뢰기 설치","2016-09-27 07:00","2016-09-27 18:00","2016-09-27T07:00:00","2016-09-27T18:00:00","매일",null,null,null,201607080341,"-"]
[185,"대전충남","서산","신당진당진#2 T/L","154kV 신당진-당진T/L 국산애자교체공사","154kV 신당진-당진T/L 국산애자교체공사 - No.44","2016-09-30 12:00","2016-09-30 18:00","취소","취소","당일",null,null,"한전요청",201607110008,"-"]
[186,"대전충남","서산","신당진당진#1 T/L","154kV 신당진-당진T/L 국산애자교체공사","154kV 신당진-당진T/L 국산애자교체공사 - No.44","2016-09-30 07:00","2016-09-30 12:00","취소","취소","당일",null,null,"한전요청",201607110007,"-"]
[187,"대전충남","세종","부강월산#2 T/L","[변전]세종P/O 변전협력회사 총액공사","○ LA초기점검 ○ 장기 미동작 차단기조작시험","2016-09-05 09:30","2016-09-05 18:00","2016-09-05T09:30:00","2016-09-05T18:00:00","당일",null,null,null,201607060011,"-"]
[188,"대전충남","아산","신온양1석곡#1 T/L","[송전]154kV 신온양-한샘T/L 경과지변경 건설공사","[송전] 기설 No.1호 ~ 신설 No.2호간 전력선 가공지선 연선 및 긴선에 따른 활선 근접","2016-09-10 07:00","2016-09-11 19:00","2016-09-10T07:00:00","2016-09-11T19:00:00","연속",null,null,null,201606100204,"-"]
[189,"대전충남","아산","신온양1석곡#2 T/L","[송전]154kV 신온양-한샘T/L 경과지변경 건설공사","[송전] 기설 No.1호 ~ 신설 No.2호간 전력선 가공지선 연선 및 긴선에 따른 활선 근접","2016-09-10 07:00","2016-09-11 19:00","2016-09-10T07:00:00","2016-09-11T19:00:00","연속",null,null,null,201606100205,"-"]
[190,"대전충남","아산","신온양한샘#1 T/L","[송전]154kV 신온양-한샘T/L 경과지변경 건설공사","[송전] 기설 No.1호 ~ 신설 No.2호간 전력선 가공지선 연선 및 긴선에 따른 활선 근접","2016-09-10 07:00","2016-09-11 19:00","2016-09-10T07:00:00","2016-09-11T19:00:00","매일",null,null,null,201606160032,"-"]
[191,"대전충남","아산","아산송악#2 T/L","[송전] 345kV 아산-화성 등 15개T/L 피뢰기 설치공사","ㅇ 154kV 아산-송악#2T/L 67기 피뢰기 설치 ㅇ 기타 부대작업","2016-09-19 09:00","2016-09-24 18:00","2016-09-19T09:00:00","2016-09-24T18:00:00","매일",null,null,null,201607080055,"-"]
[192,"대전충남","아산","아산송악#1 T/L","[송전] 345kV 아산-화성 등 15개T/L 피뢰기 설치공사","ㅇ 345kV 신서산-아산#1T/L 72기 피뢰기 설치 ㅇ 345kV 신서산-아산#1T/L 병가 하단 ㅇ 기타 부대작업","2016-09-01 09:00","2016-09-07 18:00","2016-09-01T09:00:00","2016-09-07T18:00:00","매일",null,null,null,201607080054,"-"]
[193,"대전충남","아산","온양풍세#1 T/L","온양S/S 170kV 장기사용 GIS 보강공사","○170kV 장기사용 GIS 보강공사","2016-09-23 09:00","2016-09-25 18:00","2016-09-23T09:00:00","2016-09-25T18:00:00","연속",null,null,null,201607060122,"-"]
[194,"대전충남","아산","온양풍세#1 T/L","온양S/S 170kV 장기사용 GIS 보강공사","○170kV 장기사용 GIS 보강공사","2016-09-20 09:00","2016-09-20 18:00","2016-09-20T09:00:00","2016-09-20T18:00:00","당일",null,null,null,201607060119,"-"]
[195,"대전충남","아산","인주S/S 154kV #2 BUS","인주S/S 154kV 인주-탕정#1T/L GIS 정밀점검","○ 154kV 인주-탕정#1T/L GIS 정밀점검 (양 변전소 동시 작업) ○ 154kV 인주-탕정#1T/L LA 보통점검 (양 번전소 동시 작업) ○ H형 전자변 교체 (인주 측 GIS)","2016-09-01 09:00","2016-09-02 15:00","취소","취소","연속",null,null,"한전요청",201607080094,"-"]
[196,"대전충남","아산","인주탕정#1 T/L","인주S/S 154kV 인주-탕정#1T/L GIS 정밀점검","○ 154kV 인주-탕정#1T/L GIS 정밀점검 (양 변전소 동시 작업) ○ 154kV 인주-탕정#1T/L LA 보통점검 (양 번전소 동시 작업) ○ H형 전자변 교체 (인주 측 GIS)","2016-09-01 09:00","2016-09-03 18:00","취소","취소","연속",null,null,"계통안정",201607080093,"-"]
[197,"대전충남","아산","인주S/S 154kV #2 BUS","인주S/S 154kV 현대자동차 예비T/L GIS 증설공사","Ο 154kV 현대자동차 예비T/L GIS 증설공사","2016-09-26 09:00","2016-09-30 18:00","2016-09-26T09:00:00","2016-09-30T18:00:00","연속",null,null,null,201607060016,"-"]
[198,"대전충남","아산","인주S/S 154kV #2 BUS","인주S/S 154kV 인주-탕정#2T/L GIS 정밀점검","○ 154kV 인주-탕정#2T/L GIS 정밀점검 (양 변전소 동시 작업) ○ 154kV 인주-탕정#2T/L LA 보통점검 (양 번전소 동시 작업)","2016-09-05 09:00","2016-09-06 15:00","취소","취소","연속",null,null,"한전요청",201607080098,"-"]
[199,"대전충남","아산","인주탕정#2 T/L","인주S/S 154kV 인주-탕정#2T/L GIS 정밀점검","○ 154kV 인주-탕정#2T/L GIS 정밀점검 (양 변전소 동시 작업) ○ 154kV 인주-탕정#2T/L LA 보통점검 (양 번전소 동시 작업)","2016-09-05 09:00","2016-09-07 18:00","취소","취소","연속",null,null,"계통안정",201607080099,"-"]
[200,"대전충남","아산","인주S/S 154kV #1 BUS","인주S/S 154kV 인주-탕정#2T/L GIS 정밀점검","○ 154kV 인주-탕정#2T/L GIS 정밀점검 (양 변전소 동시 작업) ○ 154kV 인주-탕정#2T/L LA 보통점검 (양 번전소 동시 작업)","2016-09-06 15:00","2016-09-07 18:00","취소","취소","연속",null,null,"한전요청",201607080097,"-"]
[201,"대전충남","아산","인주S/S 154kV #1 BUS","인주S/S 154kV 현대자동차 예비T/L GIS 증설공사","Ο 154kV 현대자동차 예비T/L GIS 증설","2016-09-20 09:00","2016-09-25 18:00","2016-09-20T09:00:00","2016-09-25T18:00:00","연속",null,null,null,201607060015,"-"]
[202,"대전충남","아산","인주S/S 154kV #1 BUS","인주S/S 154kV 인주-탕정#1T/L GIS 정밀점검","○ 154kV 인주-탕정#1T/L GIS 정밀점검 (양 변전소 동시 작업) ○ 154kV 인주-탕정#1T/L LA 보통점검 (양 번전소 동시 작업) ○ H형 전자변 교체 (인주 측 GIS)","2016-09-02 15:00","2016-09-03 18:00","취소","취소","연속",null,null,"한전요청",201607080096,"-"]
[203,"대전충남","아산","장재천안#2 T/L","[송전]154kV 장재-천안#2T/L 정밀점검(풍세-장재 병가)","○ 154kV장재-천안#2T/L 정밀점검(풍세-장재 병가) - 병가구간 : 온양-풍세#2T/L, 풍세-장재#2T/L","2016-09-28 07:00","2016-09-29 18:00","2016-09-28T07:00:00","2016-09-29T18:00:00","당일",null,null,null,201607080377,"-"]
[204,"대전충남","아산","장재천안#1 T/L","[송전]154kV 장재-천안#1T/L 정밀점검(풍세-장재 병가)","○ 154kV장재-천안#1T/L 정밀점검(풍세-장재 병가)","2016-09-21 07:00","2016-09-22 18:00","2016-09-21T07:00:00","2016-09-22T18:00:00","당일",null,null,null,201607080378,"-"]
[205,"대전충남","아산","풍세장재#2 T/L","[송전]154kV 풍세-장재#2T/L 정밀점검(아산-온양 병가)","○ 154kV 풍세-장재#2T/L 정밀점검 - 병가구간 : 온양-풍세#2T/L, 장재-천안#2T/L","2016-09-20 07:00","2016-09-21 18:00","2016-09-20T07:00:00","2016-09-21T18:00:00","당일",null,null,null,201607080375,"-"]
[206,"대전충남","아산","풍세장재#1 T/L","[송전]154kV 풍세-장재#1T/L 정밀점검","○ 154kV 풍세-장재#1T/L 정밀점검 - 병가구간 : 온양-풍세#1T/L, 장재-천안#1t/l","2016-09-27 07:00","2016-09-28 18:00","2016-09-27T07:00:00","2016-09-28T18:00:00","당일",null,null,null,201607080374,"-"]
[207,"대전충남","아산","온양풍세#2 T/L","[송전]154kV 온양-풍세#2T/L 정밀점검","○ 154kV 온양-풍세#2T/L 정밀점검 - 병가구간 : 온양-풍세#2T/L, 장재-천안#2T/L","2016-09-26 07:00","2016-09-27 18:00","2016-09-26T07:00:00","2016-09-27T18:00:00","당일",null,null,null,201607080376,"-"]
[208,"전북","군산","군공군산CC#1 T/L","154kV 군공-군산복합 지장 지중선로 이설공사","군장대교 건선관련 지장물 이설","2016-09-03 08:00","2016-09-24 18:00","취소","취소","연속",null,null,"계통안정",201607070005,"-"]
[209,"전북","군산","군산S/S 154kV #67 BUS","군산S/S 154kV #67BUS","2016년 군산P/O 154kV 차단기 정밀점검 공사 - 154kV 6300, 6233 CB 정밀점검","2016-09-21 14:00","2016-09-23 18:00","2016-09-21 14:00","2016-09-23 18:00","연속",null,null,null,201607150054,"-"]
[210,"전북","군산","군산이리#2 T/L","154㎸ 군산-이리T/L 안전이격확보공사","- 가선로구성","2016-09-22 07:00","2016-09-23 18:00","2016-09-22 07:00","2016-09-23 18:00","연속",null,null,null,201607150152,"-"]
[211,"전북","군산","군산이리#1 T/L","군산S/S 154kV 군산이리#1T/L","2016년 군산P/O 154kV 차단기 정밀점검 공사 - 154kV 60-61-0 SEC CB 정밀점검","2016-09-06 13:00","2016-09-06 14:00","2016-09-06 13:00","2016-09-06 14:00","당일",null,null,null,201607150029,"-"]
[212,"전북","군산","군산이리#1 T/L","군산S/S 154kV 군산이리#1T/L","2016년 군산P/O 154kV 차단기 정밀점검 공사 - 154kV 60-61-0 SEC CB 정밀점검","2016-09-07 17:00","2016-09-07 18:00","2016-09-07 17:00","2016-09-07 18:00","당일",null,null,null,201607150030,"-"]
[213,"전북","군산","군산이리#1 T/L","군산S/S 154kV 군산이리#1T/L","2016년 군산P/O 154kV 차단기 정밀점검 공사 - 154kV 65-66-0 SEC CB 정밀점검","2016-09-09 13:00","2016-09-09 14:00","2016-09-09 13:00","2016-09-09 14:00","당일",null,null,null,201607150035,"-"]
[214,"전북","군산","군산이리#1 T/L","군산S/S 154kV 군산이리#1T/L","2016년 군산P/O 154kV 차단기 정밀점검 공사 - 154kV 65-66-0 SEC CB 정밀점검","2016-09-10 17:00","2016-09-10 18:00","2016-09-10 17:00","2016-09-10 18:00","당일",null,null,null,201607150036,"-"]
[215,"전북","군산","군산동군산#2 T/L","군산S/S 154kV 군산동군산#2T/L","2016년 군산P/O 154kV 차단기 정밀점검 공사 - 154kV 6300, 6233CB 정밀점검","2016-09-21 13:00","2016-09-21 14:00","2016-09-21 13:00","2016-09-21 14:00","당일",null,null,null,201607150055,"-"]
[216,"전북","군산","군산동군산#2 T/L","군산S/S 154kV 군산동군산#2T/L","2016년 군산P/O 154kV 차단기 정밀점검 공사 - 154kV 6300, 6233CB 정밀점검","2016-09-23 17:00","2016-09-23 18:00","2016-09-23 17:00","2016-09-23 18:00","당일",null,null,null,201607150056,"-"]
[217,"전북","군산","군산영등#1 T/L","군산S/S 154kV 군산영등#1T/L","2016년 군산P/O 154kV 차단기 정밀점검 공사 - 154kV 60-61-0 SEC CB 정밀점검","2016-09-07 17:00","2016-09-07 18:00","2016-09-07 17:00","2016-09-07 18:00","당일",null,null,null,201607200017,"-"]
[218,"전북","군산","군산영등#2 T/L","군산S/S 154kV 군산영등#2T/L","2016년 군산P/O 154kV 차단기 정밀점검 공사 - 154kV 65-66-0 SEC CB 정밀점검","2016-09-10 17:00","2016-09-10 18:00","2016-09-10 17:00","2016-09-10 18:00","당일",null,null,null,201607200018,"-"]
[219,"전북","군산","군산S/S 154kV #60 BUS","군산S/S 154kV #60BUS","2016년 군산P/O 154kV 차단기 정밀점검 공사 - 154kV 60-61-0 SEC CB 정밀점검","2016-09-05 08:00","2016-09-06 14:00","2016-09-05 08:00","2016-09-06 14:00","연속",null,null,null,201607150026,"-"]
[220,"전북","군산","군산S/S 60-61-0 SEC CB","군산S/S 154kV 60-61-0SEC CB","2016년 군산P/O 154kV 차단기 정밀점검 공사 - 154kV 60-61-0 SEC CB 정밀점검","2016-09-05 08:00","2016-09-07 18:00","2016-09-05 08:00","2016-09-07 18:00","연속",null,null,null,201607150059,"-"]
[221,"전북","군산","군산S/S 154kV #61 BUS","군산S/S 154kV #61BUS","2016년 군산P/O 154kV 차단기 정밀점검 공사 - 154kV 60-61-0 SEC CB 정밀점검","2016-09-06 14:00","2016-09-07 18:00","2016-09-06 14:00","2016-09-07 18:00","연속",null,null,null,201607150028,"-"]
[222,"전북","군산","군산S/S 154kV #65 BUS","군산S/S 154kV #65BUS","2016년 군산P/O 154kV 차단기 정밀점검 공사 - 154kV 65-66-0 SEC CB 정밀점검","2016-09-08 08:00","2016-09-09 14:00","2016-09-08 08:00","2016-09-09 14:00","연속",null,null,null,201607150034,"-"]
[223,"전북","군산","군산S/S 65-66-0 SEC CB","군산S/S 154kV 65-66-0SEC CB","2016년 군산P/O 154kV 차단기 정밀점검 공사 - 154kV 65-66-0 SEC CB 정밀점검","2016-09-08 08:00","2016-09-10 18:00","2016-09-08 08:00","2016-09-10 18:00","연속",null,null,null,201607150060,"-"]
[224,"전북","군산","군산S/S 154kV #66 BUS","군산S/S 154kV #66BUS","2016년 군산P/O 154kV 차단기 정밀점검 공사 - 154kV 65-66-0 SEC CB 정밀점검","2016-09-09 14:00","2016-09-10 18:00","2016-09-09 14:00","2016-09-10 18:00","연속",null,null,null,201607150037,"-"]
[225,"전북","군산","군산S/S 154kV #62 BUS","군산S/S 154kV #62BUS","2016년 군산P/O 154kV 차단기 정밀점검 공사 - 154kV 6300, 6233 CB 정밀점검","2016-09-19 08:00","2016-09-21 14:00","2016-09-19 08:00","2016-09-21 14:00","연속",null,null,null,201607150053,"-"]
[226,"전북","군산","군산S/S 154kV #3 BUS TIE CB","군산S/S 154kV #3 BUS TIE CB","2016년 군산P/O 154kV 차단기 정밀점검 공사 - 154kV 6300, 6233 CB 정밀점검","2016-09-19 08:00","2016-09-23 18:00","2016-09-19 08:00","2016-09-23 18:00","연속",null,null,null,201607150061,"-"]
[227,"전북","군산","군산영등#1 T/L","154㎸ 군산-이리T/L 안전이격확보공사","- 신설철탑조립(13,14,15호) 및 전력선공중이동,전력선교체(12~13호간)관련 상단(군산-영등T/L)안전이격확보관련 휴전","2016-09-24 07:00","2016-10-01 18:00","2016-09-24 07:00","2016-10-01 18:00","연속",null,null,null,201607150156,"-"]
[228,"전북","군산","군산이리#1 T/L","154㎸ 군산-이리T/L 안전이격확보공사","- 신설철탑조립(13,14,15호) 및 전력선공중이동 - 전력선교체(12~13호간)","2016-09-24 07:00","2016-10-01 18:00","2016-09-24 07:00","2016-10-01 18:00","연속",null,null,null,201607150153,"-"]
[229,"전북","군산","이리전주#1 T/L","154kV 이리-전주 #1T/L","이리-전주#1T/L 임시선로 구성","2016-09-19 08:00","2016-09-21 18:00","2016-09-19 08:00","2016-09-21 18:00","연속",null,null,null,201607200079,"-"]
[230,"전북","군산","이리백산#2 T/L","154kV 이리-백산T/L 선종교체공사","선종 교체 : No.8~No.35호간 HSTACIR/AW 240㎟ (19.22 C-km) 철탑 신설·철거 : 설치 6기, 철거 5기 (No.11,19,25,28.1,32,33)","2016-09-22 08:00","2016-10-02 18:00","2016-10-04 08:00","2016-10-14 18:00","연속",null,null,"한전요청",201607060146,"-"]
[231,"전북","군산","이리백산#2 T/L","154kV 이리-백산T/L 선종교체공사","선종 교체 : No.8~No.35호간 HSTACIR/AW 240㎟ (19.22 C-km) 철탑 신설·철거 : 설치 6기, 철거 5기 (No.11,19,25,28.1,32,33)","2016-09-01 08:00","2016-09-04 18:00","2016-09-13 08:00","2016-09-16 18:00","연속",null,null,"한전요청",201607060142,"-"]
[232,"전북","군산","이리백산#1 T/L","154kV 이리-백산T/L 선종교체공사","선종 교체 : No.8~No.35호간 HSTACIR/AW 240㎟ (19.22 C-km) 철탑 신설·철거 : 설치 6기, 철거 5기 (No.11,19,25,28.1,32,33)","2016-09-05 08:00","2016-09-21 18:00","2016-09-17 08:00","2016-10-03 18:00","연속",null,null,"한전요청",201607060150,"-"]
[233,"전북","김제","김제섬진강HP T/L","김제섬진강HP T/L","#1 BUS 시험가압","2016-09-29 13:00","2016-09-29 15:00","2016-09-29 13:00","2016-09-29 15:00","당일",null,null,null,201607180137,"-"]
[234,"전북","김제","김제섬진강HP T/L","김제섬진강HP T/L","#2 BUS 시험가압","2016-09-30 15:00","2016-09-30 17:00","2016-09-30 15:00","2016-09-30 17:00","당일",null,null,null,201607180138,"-"]
[235,"전북","김제","정공섬진강수력 T/L","정공섬진강수력 T/L","전담운영 대비 SCADA 제어회로 구성","2016-09-19 09:00","2016-09-20 18:00","2016-09-19 09:00","2016-09-20 18:00","연속",null,null,null,201607180129,"○"]
[236,"전북","김제","김제섬진강HP T/L","김제섬진강HP T/L","전담운영 대비 SCADA 제어회로 구성","2016-09-21 09:00","2016-09-22 18:00","2016-09-21 09:00","2016-09-22 18:00","연속",null,null,null,201607180131,"-"]
[237,"전북","김제","섬진강H/P 154kV #1 BUS TIE CB","섬진강H/P 154kV #1 BUS TIE CB","전담운영 대비 SCADA 제어회로 구성","2016-09-23 09:00","2016-09-24 18:00","2016-09-23 09:00","2016-09-24 18:00","연속",null,null,null,201607180132,"○"]
[238,"전북","김제","섬진강H/P #2 M.Tr 1차 CB","섬진강H/P 154kV #1 BUS TIE CB","전담운영 대비 SCADA 제어회로 구성","2016-09-26 09:00","2016-09-27 18:00","2016-09-26 09:00","2016-09-27 18:00","연속",null,null,null,201607180133,"-"]
[239,"전북","김제","섬진강H/P #1 M.Tr 1차 CB","섬진강H/P #1 M.Tr 1차 CB","전담운영 대비 SCADA 제어회로 구성","2016-09-28 09:00","2016-09-30 18:00","2016-09-28 09:00","2016-09-30 18:00","연속",null,null,null,201607180134,"○"]
[240,"광주전남","강진","강진남창#1 T/L","154kV 강진-남창#1T/L(신강진-강진T/L 정밀점검 안전확보)","154kV 강진-남창#1T/L(가공순시점검위탁공사) - 4회선병가 구간 안전확보(신강진-강진T/L 정밀점검)","2016-09-23 08:00","2016-09-23 18:00","2016-09-23 08:00","2016-09-23 18:00","당일",null,null,null,201607120045,"-"]
[241,"광주전남","강진","강진남창#2 T/L","154kV 강진-남창#2T/L(신강진-강진R/L 정밀점검 안전확보)","154kV 강진-남창#2T/L(가공순시점검위탁공사) - 4회선병가 구간 안전확보(신강진-강진T/L 정밀점검)","2016-09-26 08:00","2016-09-27 18:00","2016-09-26 08:00","2016-09-27 18:00","당일",null,null,null,201607120046,"-"]
[242,"광주전남","강진","해남해남CS#2 T/L","154kV 해남-해남CS #2T/L(남창-해남CS 병가구간 안전확보)","154kV 남창-해남CS #2T/L 휴전시 병가구간 안전거리확보","2016-09-29 08:00","2016-09-29 18:00","2016-09-29 08:00","2016-09-29 18:00","당일",null,null,null,201607110196,"-"]
[243,"광주전남","강진","남창해남CS#2 T/L","154kV 남창-해남CS #2T/L(SB댐퍼 설치공사)","154kV 남창-해남CS #2T/L 송전정비 협력회사 총액공사 - SB댐퍼 설치공사","2016-09-29 08:00","2016-09-29 18:00","2016-09-29 08:00","2016-09-29 18:00","당일",null,null,null,201607110197,"-"]
[244,"광주전남","강진","남창해남CS#1 T/L","154kV 남창-해남CS #1T/L(SB댐퍼 설치공사)","154kV 남창-해남CS #1T/L 송전정비 협력회사 총액공사 - SB댐퍼 설치공사","2016-09-28 08:00","2016-09-28 18:00","2016-09-28 08:00","2016-09-28 18:00","당일",null,null,null,201607110188,"-"]
[245,"광주전남","강진","해남해남CS#1 T/L","154kV 해남-해남CS #1T/L(남창-해남CS 병가구간 안전확보)","154kV 남창-해남CS #1T/L 휴전시 병가구간 안전거리확보","2016-09-28 08:00","2016-09-28 18:00","2016-09-28 08:00","2016-09-28 18:00","당일",null,null,null,201607110193,"-"]
[246,"광주전남","광주","북광주계림#2 T/L","154kV 북광주-계림#2T/L(북광주-계림#2T/L GIS 정밀점검)","CB, #1DS, #2DS, 상부BUS 정밀점검","2016-09-29 09:00","2016-10-01 18:00","2016-09-30 09:00","2016-10-02 18:00","연속",null,null,"한전요청",201607110083,"-"]
[247,"광주전남","광주","북광주계림#1 T/L","154kV 북광주-계림#1T/L(북광주-계림#1T/L GIS 정밀점검)","CB, #1DS, #2DS, 상부BUS 정밀점검","2016-09-26 09:00","2016-09-28 18:00","2016-09-27 09:00","2016-09-29 18:00","연속",null,null,"한전요청",201607110047,"-"]
[248,"광주전남","광주","북광주일곡#1 T/L","154kV 북광주-일곡등 2개T/L 전압제한기 교체공사","- 북광주-일곡#1,2T/L 전압제한기(SVL) 교체 - M/H #5,7,9,10,12,13(12개소, 36EA)","2016-09-20 09:00","2016-09-21 18:00","2016-09-20 09:00","2016-09-21 18:00","당일",null,null,null,201607050060,"-"]
[249,"광주전남","광주","북광주일곡#2 T/L","154kV 북광주-일곡등 2개T/L 전압제한기 교체공사","- 북광주-일곡#1,2T/L 전압제한기(SVL) 교체 - M/H #5,7,9,10,12,13(12개소, 36EA)","2016-09-22 09:00","2016-09-23 18:00","2016-09-22 09:00","2016-09-23 18:00","당일",null,null,null,201607050061,"-"]
[250,"광주전남","광주","신광주일곡#1 T/L","154kV 일곡-비아#1T/L 피뢰기 설치공사","일곡-비아#1T/L 피뢰기 설치 관련 하단 선로(신광주-일곡#1) 휴전요청","2016-09-26 08:00","2016-09-26 18:00","2016-09-26 08:00","2016-09-26 18:00","당일",null,null,null,201607220045,"-"]
[251,"광주전남","목포","고창영광 T/L","154kV 장성-영광T/L전선접속개소전선교체공사","0 상단측 전선교체 관련 하단선로 안전조치 0 하단측 고창-영광T/L 송전용 피뢰기 설치 : 45기 135set","2016-09-22 07:00","2016-09-25 18:00","취소","취소","연속",null,null,"계통안정",201607110477,"-"]
[252,"광주전남","목포","장성영광#2 T/L","154kV장성-영광T/L전선접속개소전선교체공사","0 전선 및 금구류 교체 : No.125~160 4회선 구간","2016-09-19 07:00","2016-09-25 18:00","취소","취소","연속",null,null,"계통안정",201607110468,"-"]
[253,"광주전남","목포","장성영광#1 T/L","154kV장성-영광T/L전선접속개소전선교체공사","0 전선 및 금구류 교체 : No.125~160 4회선 구간","2016-09-26 07:00","2016-10-04 18:00","취소","취소","연속",null,null,"계통안정",201607110470,"-"]
[254,"광주전남","목포","영광홍농 T/L","154kV 영광-홍농T/L(보호배전반 대체공사)","154kV 송전선로보호반 대체","2016-09-26 09:00","2016-09-30 18:00","취소","취소","연속",null,null,"계통안정",201607070096,"-"]
[255,"광주전남","순천","순천율촌#2 T/L","154kV 순천-율촌#2T/L(송전선로 피뢰기 설치)","154kV 순천-율촌#2T/L 송전선로 피뢰기 설치 - 57~67호, 11기","2016-09-22 07:00","2016-09-22 18:00","2016-09-24 07:00","2016-09-24 18:00","당일",null,null,"한전요청",201607110114,"-"]
[256,"광주전남","순천","승주주암HP T/L","154kV 승주-주암HP T/L(송전선로 피뢰기 설치)","154kV 승주-주암HP T/L 송전선로 피뢰기 설치 - 주암분기 1~5호, 5기","2016-09-23 07:00","2016-09-23 18:00","2016-09-23 07:00","2016-09-23 18:00","당일",null,null,null,201607110124,"-"]
[257,"광주전남","순천","여수TP화치#1 T/L","154kV 여수TP-화치#1T/L(송전선로 피뢰기 설치)","154kV 여수TP-화치#1T/L 송전선로 피뢰기 설치 - 1~1.1호, 2기","2016-09-23 13:00","2016-09-23 18:00","2016-09-23 13:00","2016-09-23 18:00","당일",null,null,null,201607110130,"-"]
[258,"광주전남","순천","여수TP용성#2 T/L","154kV 여수TP-용성#2T/L(송전선로 피뢰기 설치)","154kV 여수TP-용성#2T/L 송전선로 피뢰기 설치 - 1~3호, 4기","2016-09-23 07:00","2016-09-23 13:00","2016-09-23 07:00","2016-09-23 13:00","당일",null,null,null,201607110131,"-"]
[259,"광주전남","순천","호남TP여수TP#1 T/L","여수T/P 154kV 호남TP-여수TP #1T/L(CB Time 측정)","2016~17년 순천전력지사 변전협력회사 총액공사 - 여수T/P 호남TP-여수TP #1T/L 유압시스템 점검 및 CB Time 측정","2016-09-12 10:00","2016-09-12 18:00","2016-09-12 10:00","2016-09-12 18:00","당일",null,null,null,201607110226,"-"]
[260,"광주전남","순천","여천호남TP#1 T/L","154kV 여천-호남TP#1T/L(송전선로 피뢰기 설치)","154kV 여천-호남TP #1T/L 송전선로 피뢰기 설치 - 1~32호, 14기","2016-09-24 07:00","2016-09-24 18:00","2016-09-24 07:00","2016-09-24 18:00","당일",null,null,null,201607110156,"-"]
[261,"광주전남","순천","여천여수#1 T/L","154kV 여천-여수#1T/L(송전선로 점퍼 지지애자 교체)","154kV 여천-여수#1T/L 송전선로 점퍼 지지애자 교체 - 수량 : 1기","2016-09-09 07:00","2016-09-09 18:00","2016-09-09 07:00","2016-09-09 18:00","당일",null,null,null,201607110234,"-"]
[262,"광주전남","순천","용성여수산단#1 T/L","154kV 용성-여수산단#1T/(여수TP-용성#2T/L 4회선 병가구간)","154kV 여수TP-용성#2T/L 피뢰기 설치 4회선 병가구간","2016-09-23 07:00","2016-09-23 13:00","2016-09-23 07:00","2016-09-23 13:00","당일",null,null,null,201607110135,"-"]
[263,"광주전남","순천","율촌-여수산단#1 T/L","154kV 율촌-여수산단#1T/L(GIS 하자점검)","2016~17년 순천전력지사 변전협력회사 총액공사 - 율촌S/S : 율촌-여수산단#1T/L GIS 하자점검 - 여수산단 : 율촌-여수산단#1T/L GIS 하자점검","2016-09-19 10:00","2016-09-19 18:00","2016-09-01 10:00","2016-09-01 18:00","당일",null,null,null,201607110216,"-"]
[264,"광주전남","순천","율촌-여수산단#2 T/L","154kV 율촌-여수산단#2T/L(GIS 하자점검)","2016~17년 순천전력지사 변전협력회사 총액공사 - 율촌S/S : 율촌-여수산단#2T/L GIS 하자점검 - 여수산단 : 율촌-여수산단#2T/L GIS 하자점검","2016-09-20 10:00","2016-09-20 18:00","2016-09-02 10:00","2016-09-02 18:00","당일",null,null,null,201607110218,"-"]
[265,"광주전남","직할","신화순평동(구,신화순나주#1) T/L","154kV 신화순평동(구,신화순나주#1)T/L 피뢰기설치공사","16~17년 직할 송전정비 협력회사 총액공사 - 154kV 신화순평동(구,신화순나주#1)T/L 피뢰기설치공사","2016-09-21 08:00","2016-09-23 18:00","2016-09-24 08:00","2016-09-26 18:00","매일",null,null,"계통안정",201607080023,"-"]
[266,"광주전남","직할","평동S/S 154kV #1 BUS TIE GIS","154kV 평동S/S 154kV Sh.C(GIS 설치)","○ 154kV 평동S/S 154kV Sh.C 설치공사 - 170kV GIS 1CCT 설치 - #1,2BUS 무부하 가압","2016-09-01 09:30","2016-09-12 09:30","2016-08-30 09:30","2016-09-09 09:30","연속",null,null,"한전요청",201606130032,"-"]
[267,"대구경북","경산","신경산아화#2 T/L","154kV 금호변전소 건설공사","154kV 금호변전소 건설공사","2016-09-01 09:00","2016-09-04 18:00","2016-09-01 09:00","2016-09-04 18:00","연속",null,null,null,201607130040,"-"]
[268,"대구경북","경산","신경산경산#1 T/L","신경산S/S 장기사용 170kV GIS 대체공사","신경산-경산#1T/L GIS 대체","2016-09-21 09:00","2016-10-04 18:00","2016-09-21 09:00","2016-10-04 18:00","연속",null,null,null,201607190102,"-"]
[269,"대구경북","경산","신경산아화#1 T/L","154kV 금호변전소 건설공사","154kV 금호변전소 건설공사","2016-09-01 09:00","2016-09-04 18:00","2016-09-01 09:00","2016-09-04 18:00","연속",null,null,null,201607130039,"-"]
[270,"대구경북","안동","신영주안동#1 T/L","154kV 신영주-안동T/L 송전선로 피뢰기 설치공사","○ 154kV 신영주-안동#1T/L No.57-97 송전선로 피뢰기 설치공사","2016-09-07 07:00","2016-09-09 18:00","2016-09-07 07:00","2016-09-09 18:00","매일",null,null,null,201607110098,"-"]
[271,"대구경북","영주","점촌문경 T/L","문경S/S 617 GIS 정밀점검, 617 GIS 누유개소 보수(제작사)","문경S/S 617 GIS 정밀점검, 617 GIS 누유개소 보수(제작사)","2016-09-16 09:00","2016-09-18 18:00","2016-09-16 09:00","2016-09-18 18:00","연속",null,null,null,201607080121,"-"]
[272,"대구경북","직할","범물남대구#1 T/L","2016년 직할 가공송전협력회사 총액공사","- 범물-남대구#1 송전선로용 피뢰기 설치공사 - 노변-효목#1 송전선로용 피뢰기 설치공사간 안전확보","2016-09-25 07:30","2016-09-30 18:00","2016-09-25 07:30","2016-09-30 18:00","당일",null,null,null,201607110405,"-"]
[273,"대구경북","직할","노변효목#1 T/L","2016년 직할 가공송전협력회사 총액공사","- 노변-효목#1 송전선로용 피뢰기 설치공사 - 범물-남대구#1 송전선로용 피뢰기 설치공사간 안전확보","2016-09-25 07:30","2016-09-30 18:00","2016-09-25 07:30","2016-09-30 18:00","당일",null,null,null,201607110407,"-"]
[274,"대구경북","포항","건천천북#2 T/L","154kV 건천-천북#2T/L 정밀점검","154kV 건천-천북#2T/L 정밀점검(No.21-96)","2016-09-26 08:00","2016-09-28 18:00","2016-09-26 08:00","2016-09-28 18:00","연속",null,null,null,201607070179,"-"]
[275,"대구경북","포항","건천천북#1 T/L","154kV 건천-천북#1T/L 정밀점검","154kV 건천-천북#1T/L 정밀점검(No.21~96)","2016-09-20 08:00","2016-09-23 18:00","2016-09-20 08:00","2016-09-23 18:00","연속",null,null,null,201607070178,"-"]
[276,"부산울산","동부산","신울산명례#1 T/L","154kV 신울산-명례 등 4개T/L 전선접소개소 전선교체공사","○ 공사구간 : 1∼14호, 23∼36호, 39∼42호(10.740km)","2016-09-01 08:00","2016-09-11 18:00","2016-09-01 08:00","2016-09-11 18:00","연속",null,null,null,201607060178,"-"]
[277,"부산울산","동부산","신울산명례#2 T/L","154kV 신울산-명례 등 4개T/L 전선접소개소 전선교체공사","○ 공사구간 : 1∼14호, 23∼36호, 39∼42호(10.740km)","2016-09-20 08:00","2016-09-30 18:00","2016-09-20 08:00","2016-09-30 18:00","연속",null,null,null,201607060179,"-"]
[278,"부산울산","북부산","구포모라#2 T/L","154kV 구포-모라#2T/L 에어누기 보수","구포S/S 642DS 에어누기 보수","2016-09-06 13:00","2016-09-06 18:00","2016-09-06 13:00","2016-09-06 18:00","당일",null,null,null,201607110299,"-"]
[279,"부산울산","북부산","구포모라#1 T/L","154kV 구포-모라#1T/L 에어누기 보수","구포S/S 632, 636DS 에어누기 보수","2016-09-06 09:00","2016-09-06 13:00","2016-09-06 09:00","2016-09-06 13:00","당일",null,null,null,201607110298,"-"]
[280,"부산울산","북부산","매리김해#2 T/L","154kV 서창-산막 등 5개T/L 전선접속개소 전선교체공사","매리-김해#2T/L 전선교체공사(No.8~10)","2016-09-12 07:00","2016-09-13 18:00","2016-09-12 07:00","2016-09-13 18:00","연속",null,null,null,201607110281,"-"]
[281,"부산울산","북부산","매리김해#1 T/L","154kV 서창-산막 등 5개T/L 전선접속개소 전선교체공사","매리-김해#1T/L 전선교체공사(No.8~13, 35~38)","2016-09-05 07:00","2016-09-08 18:00","2016-09-05 07:00","2016-09-08 18:00","연속",null,null,null,201607110272,"-"]
[282,"부산울산","북부산","매리김해#2 T/L","154kV 서창-산막 등 5개T/L 전선접속개소 전선교체공사","매리-김해#1T/L 전선교체공사(No.8~13, 35~38)에 따른 작업자 안전거리 확보","2016-09-05 07:00","2016-09-08 18:00","2016-09-05 07:00","2016-09-08 18:00","연속",null,null,null,201607110276,"-"]
[283,"부산울산","북부산","매리김해#1 T/L","154kV 서창-산막 등 5개T/L 전선접속개소 전선교체공사","매리-김해#2T/L 전선교체공사(No.8~10)에 따른 작업자 안전거리 확보","2016-09-12 07:00","2016-09-13 18:00","2016-09-12 07:00","2016-09-13 18:00","연속",null,null,null,201607110279,"-"]
[284,"부산울산","북부산","북부산삼랑진PP#1 T/L","154kV 삼랑진양수T/L 접속설비 전선접속개소 전선교체공사","북부산-삼랑진양수#1T/L 전선교체공사(No.67~105)","2016-09-27 07:00","2016-10-26 18:00","2016-09-27 07:00","2016-10-26 18:00","연속",null,null,null,201607110297,"-"]
[285,"부산울산","북부산","서창산막#1 T/L","154kV 서창-산막 등 5개T/L 전선접속개소 전선교체공사","서창-산막#1T/L 전선교체공사(No.14~36)","2016-09-20 07:00","2016-09-26 18:00","2016-09-20 07:00","2016-09-26 18:00","연속",null,null,null,201607110287,"-"]
[286,"부산울산","북부산","서창산막#2 T/L","154kV 서창-산막 등 5개T/L 전선접속개소 전선교체공사","서창-산막#2T/L 전선교체공사(No.14~36)","2016-09-27 07:00","2016-10-03 18:00","2016-09-27 07:00","2016-10-03 18:00","연속",null,null,null,201607110290,"-"]
[287,"부산울산","북부산","삼계어방 T/L","154kV 서창-산막 등 5개T/L 전선접속개소 전선교체 공사","삼계-어방T/L 전선교체공사(No.16~17)","2016-09-04 12:00","2016-09-04 18:00","2016-09-04 12:00","2016-09-04 18:00","당일",null,null,null,201607180022,"-"]
[288,"부산울산","북부산","삼계김해 T/L","154kV 서창-산막 등 5개T/L 전선접속개소 전선교체 공사","삼계-어방T/L 전선교체공사(No.16~17)에 따른 작업자 안전거리확보","2016-09-04 12:00","2016-09-04 18:00","2016-09-04 12:00","2016-09-04 18:00","당일",null,null,null,201607180023,"-"]
[289,"부산울산","북부산","삼계어방 T/L","154kV 서창-산막 등 5개T/L 전선접속개소 전선교체 공사","삼계-김해T/L 전선교체공사(No.16~17)에 따른 작업자 안전거리확보","2016-09-04 07:00","2016-09-04 12:00","2016-09-04 07:00","2016-09-04 12:00","당일",null,null,null,201607180020,"-"]
[290,"부산울산","북부산","삼계김해 T/L","154kV 서창-산막 등 5개T/L 전선접속개소 전선교체 공사","삼계-김해T/L 전선교체공사(No.16~17)","2016-09-04 07:00","2016-09-04 12:00","2016-09-04 07:00","2016-09-04 12:00","당일",null,null,null,201607180019,"-"]
[291,"부산울산","북부산","양산산막#2 T/L","16년 가공송전 협력업체 총액공사","양산산막#2T/L 4호 애자련 교체공사","2016-09-09 07:30","2016-09-09 18:00","2016-09-09 07:30","2016-09-09 18:00","당일",null,null,null,201607180050,"-"]
[292,"부산울산","북부산","엄궁학장#1 T/L","학장S/S 170kV 장기사용 GIS 대체(4차)","학장S/S 엄궁-학장#2T/L, #1M.Tr 1차 GIS 대체(#2BUS측 시험가압)","2016-09-24 11:00","2016-09-24 13:00","2016-09-24 11:00","2016-09-24 13:00","당일",null,null,null,201607110277,"-"]
[293,"부산울산","북부산","엄궁학장#2 T/L","학장S/S 170kV 장기사용 GIS 대체(4차)","학장S/S 엄궁-학장#2T/L, #1M.Tr 1차 GIS 대체","2016-09-22 08:00","2016-10-13 18:00","2016-09-22 08:00","2016-10-13 18:00","연속",null,null,null,201607110257,"-"]
[294,"부산울산","북부산","엄궁학장#1 T/L","학장S/S 170kV 장기사용 GIS 대체(4차)","학장S/S 엄궁-학장#2T/L, #1M.Tr 1차 GIS 대체(#1BUS측 시험가압)","2016-09-30 18:00","2016-10-02 18:00","2016-09-30 18:00","2016-10-02 18:00","연속",null,null,null,201607110280,"-"]
[295,"부산울산","북부산","학장개금#2 T/L","2016년 북부산변전협력회사 총액공사","학장-개금#2T/L 보호배전반 대체","2016-09-08 09:00","2016-09-09 18:00","2016-09-08 09:00","2016-09-09 18:00","연속",null,null,null,201607110285,"-"]
[296,"부산울산","북부산","매리호포#2 T/L","154kV 서창-산막 등 5개T/L 전선접속개소 전선교체공사","호포-매리#2T/L 전선교체공사(No.14~16)","2016-09-03 07:00","2016-09-03 18:00","2016-09-03 07:00","2016-09-03 18:00","당일",null,null,null,201607110268,"-"]
[297,"부산울산","북부산","북부산호포 T/L","154kV 호포S/S #3M.Tr 증설공사","호포S/S 154kV 6333 GIS 설치 관련 test 선로(#1BUS 시험가압)","2016-09-09 18:00","2016-09-11 18:00","2016-09-09 18:00","2016-09-11 18:00","연속",null,null,null,201607130095,"-"]
[298,"부산울산","북부산","북부산호포 T/L","154kV 호포S/S #3M.Tr 증설공사","호포S/S 154kV 6333 GIS 설치 관련 test 선로(#2BUS 시험가압)","2016-09-23 18:00","2016-09-25 18:00","2016-09-23 18:00","2016-09-25 18:00","연속",null,null,null,201607130105,"-"]
[299,"부산울산","서부산","신녹산용원#2 T/L","용원S/S 신녹산-용원#2T/L GIS 하자점검","용원S/S 신녹산-용원#2T/L GIS 하자점검","2016-09-10 10:00","2016-09-10 18:00","2016-09-10 10:00","2016-09-10 18:00","당일",null,null,null,201607080044,"-"]
[300,"부산울산","울산","동울산효문#2 T/L","2016년 가공송전 순시점검 위탁공사","154kV 매곡-북울산#1T/L 정밀,초기점검 관련 안전이격 확보차","2016-09-26 09:00","2016-09-26 18:00","2016-09-26 09:00","2016-09-26 18:00","당일",null,null,null,201607150169,"-"]
[301,"부산울산","울산","동울산효문#1 T/L","2016년 가공송전 순시점검 위탁공사","154kV 매곡-북울산#2T/L 정밀,초기점검 관련 안전이격 확보차","2016-09-22 09:00","2016-09-22 18:00","2016-09-22 09:00","2016-09-22 18:00","당일",null,null,null,201607150165,"-"]
[302,"부산울산","울산","방어진영남TP#1 T/L","154kV 방어진S/S 용량부족 차단기 대체공사","154kV 방어진S/S 용량부족 차단기 대체공사 - 방어진S/S #1BUS 임시모선 설치관련 안전이격 확보","2016-09-21 09:00","2016-09-21 18:00","2016-09-21 09:00","2016-09-21 18:00","당일",null,null,null,201607130091,"-"]
[303,"부산울산","울산","방어진영남TP#1 T/L","154kV 방어진S/S 용량부족 차단기 대체공사","154kV 방어진S/S 용량부족 차단기 대체공사 - 방어진S/S #2BUS 단로기 설치관련 안전이격 확보","2016-09-25 09:00","2016-09-25 18:00","2016-09-25 09:00","2016-09-25 18:00","당일",null,null,null,201607130093,"-"]
[304,"부산울산","울산","방어진영남TP#2 T/L","154kV 방어진S/S 용량부족 차단기 대체공사","154kV 방어진S/S 용량부족 차단기 대체공사 - 방어진S/S 방어진-영남T/P #2T/L GIS 대체시행","2016-09-19 09:00","2016-10-04 20:00","2016-09-19 09:00","2016-10-04 20:00","연속",null,null,null,201607130090,"-"]
[305,"부산울산","울산","방어진영남TP#1 T/L","154kV 방어진S/S 용량부족 차단기 대체공사","154kV 방어진S/S 용량부족 차단기 대체공사 - 방어진S/S #1BUS 임시모선 예비가압 (48h) 선로","2016-09-23 08:00","2016-09-25 08:00","2016-09-23 08:00","2016-09-25 08:00","연속",null,null,null,201607130092,"-"]
[306,"부산울산","울산","방어진영남TP#1 T/L","154kV 방어진S/S 용량부족 차단기 대체공사","154kV 방어진S/S 용량부족 차단기 대체공사 - 방어진S/S #2BUS (DS) 예비가압 선로","2016-09-27 08:00","2016-09-29 08:00","2016-09-27 08:00","2016-09-29 08:00","연속",null,null,null,201607130094,"-"]
[307,"부산울산","울산","신울산울산#2 T/L","2016년 가공송전 순시점검 위탁공사","송전선로 정밀점검 - 작업구간 : 신울산S/S~No.17(C/H)","2016-09-12 09:00","2016-09-13 18:00","2016-09-12 09:00","2016-09-13 18:00","연속",null,null,null,201607100008,"-"]
[308,"부산울산","울산","신울산S/S 154kV #61 BUS","2016-17년 울산전력지사 변전협력회사 총액공사","신울산S/S SK에너지Polymer T/L #61BUS측 단로기 접촉자 교체","2016-09-30 08:00","2016-09-30 17:00","2016-09-30 08:00","2016-09-30 17:00","당일",null,null,null,201607120014,"-"]
[309,"부산울산","울산","용연처용#2 T/L","154kV 용연-울산TP #2T/L 송전선로용 피뢰기 설치공사","ㅁ 154kV 용연-울산TP #2T/L 피뢰기 설치작업 관련 이격거리 확보 [No.9, 9-1호]","2016-09-04 08:00","2016-09-04 13:00","2016-09-04 08:00","2016-09-04 13:00","당일",null,null,null,201607110034,"-"]
[310,"부산울산","울산","용연울산TP#2 T/L","154kV 용연-울산TP #2T/L 송전선로용 피뢰기 설치공사","ㅁ 피뢰기 설치 ㅇ 구간 : 154kV 용연-울산TP #2T/L No.1~9.2호(11기)","2016-09-03 08:00","2016-09-04 18:00","2016-09-03 08:00","2016-09-04 18:00","연속",null,null,null,201607110027,"-"]
[311,"부산울산","울산","신울산웅촌#1 T/L","2016년 하반기 170kV 개폐장치 정밀점검 공사","웅촌S/S 6279 GIS 정밀점검 관련 #1BUS 시험가압","2016-09-10 17:00","2016-09-10 18:00","2016-09-10 17:00","2016-09-10 18:00","당일",null,null,null,201607120020,"-"]
[312,"부산울산","울산","신울산웅촌#2 T/L","2016년 하반기 170kV 개폐장치 정밀점검 공사","웅촌S/S 6279 GIS 정밀점검 관련 #2BUS 시험가압","2016-09-08 17:00","2016-09-08 18:00","2016-09-08 17:00","2016-09-08 18:00","당일",null,null,null,201607120019,"-"]
[313,"부산울산","울산","신울산웅촌#2 T/L","2016년 하반기 170kV 개폐장치 정밀점검 공사","웅촌S/S 6179 GIS 정밀점검 관련 #2BUS 시험가압","2016-09-05 17:00","2016-09-05 18:00","2016-09-05 17:00","2016-09-05 18:00","당일",null,null,null,201607120018,"-"]
[314,"부산울산","울산","신울산웅촌#1 T/L","2016년 하반기 170kV 개폐장치 정밀점검 공사","웅촌S/S 6179 GIS 정밀점검 관련 #1BUS 시험가압","2016-09-07 17:00","2016-09-07 18:00","2016-09-07 17:00","2016-09-07 18:00","당일",null,null,null,201607120022,"-"]
[315,"부산울산","직할","우동대연 T/L","2016-2017년 서부산 송전정비 협력회사 총액공사","1~13호 스페이서 간격조정 및 SB댐퍼 설치","2016-09-22 08:00","2016-09-23 18:00","2016-09-22 08:00","2016-09-23 18:00","매일",null,null,null,201607050019,"-"]
[316,"부산울산","직할","정보대연 T/L","2016-2017년 서부산 송전정비 협력회사 총액공사","1~13호 스페이서 간격조정 및 SB댐퍼 설치","2016-09-20 08:00","2016-09-21 18:00","2016-09-20 08:00","2016-09-21 18:00","매일",null,null,null,201607050020,"-"]
[317,"경남","직할","창공월림#2 T/L","창공S/S 154kV GIS화 공사","창공-월림#2T/L GIS 이설","2016-09-05 14:00","2016-09-12 09:00","2016-09-05 14:00","2016-09-12 09:00","연속",null,null,null,201607110195,"-"]
[318,"경남","직할","창공완암#1 T/L","창공S/S 154kV GIS화 공사","창공-완암#1T/L GIS 이설","2016-09-05 14:00","2016-09-12 09:00","2016-09-05 14:00","2016-09-12 09:00","연속",null,null,null,201607110190,"-"]
[319,"경남","진주","개양S/S 154kV #1 BUS TIE CB","개양S/S 154kV TIE CB(6100) 보통점검","개양S/S 154kV TIE CB(6100) 보통점검","2016-09-24 09:30","2016-09-24 18:30","2016-09-24 09:30","2016-09-24 18:30","당일",null,null,null,201607060070,"-"]
[320,"경남","진주","개양S/S 154KV #1 BUS","개양S/S 무림페이퍼T/L GIS 정밀점검","개양S/S 무림페이퍼T/L GIS 정밀점검","2016-09-14 13:00","2016-09-15 20:00","2016-09-14 13:00","2016-09-15 20:00","연속",null,null,null,201607070194,"-"]
[321,"경남","진주","개양S/S 154KV #2 BUS","개양S/S 무림페이퍼T/L GIS 정밀점검","개양S/S 무림페이퍼T/L GIS 정밀점검","2016-09-14 08:00","2016-09-14 13:00","2016-09-14 08:00","2016-09-14 13:00","당일",null,null,null,201607070193,"-"]
[322,"경남","진주","무림파워텍 T/L","진주S/S 무림파워텍(657) 보통점검","진주S/S 무림파워텍(657) 보통점검","2016-09-14 09:30","2016-09-14 18:30","2016-09-14 09:30","2016-09-14 18:30","당일",null,null,null,201607060177,"-"]
[323,"경남","진주","쌍림합천#1 T/L","거창-합천#1T/L GIS 정밀점검공사","거창-합천#1T/L GIS 정밀점검공사","2016-09-25 16:00","2016-09-25 18:30","2016-09-25 16:00","2016-09-25 18:30","당일",null,null,null,201607070201,"-"]
[324,"경남","진주","쌍림합천#2 T/L","거창-합천#1T/L GIS 정밀점검공사","거창-합천#1T/L GIS 정밀점검공사","2016-09-24 12:00","2016-09-24 13:00","2016-09-24 12:00","2016-09-24 13:00","당일",null,null,null,201607070199,"-"]
[325,"경남","진주","거창합천#1 T/L","합천S/S 154kV #1 BUS TIE GIS 정밀점검공사","합천S/S 154kV #1 BUS TIE GIS 정밀점검공사","2016-09-22 16:00","2016-09-22 18:30","2016-09-22 16:00","2016-09-22 18:30","당일",null,null,null,201607070218,"-"]
[326,"경남","진주","거창합천#1 T/L","거창-합천#1T/L GIS 정밀점검공사","거창-합천#1T/L GIS 정밀점검공사","2016-09-23 09:30","2016-09-25 18:30","2016-09-23 09:30","2016-09-25 18:30","연속",null,null,null,201607070197,"-"]
[327,"경남","진주","거창합천#2 T/L","합천S/S 154kV #1 BUS TIE GIS 정밀점검공사","합천S/S 154kV #1 BUS TIE GIS 정밀점검공사","2016-09-21 12:00","2016-09-21 13:00","2016-09-21 12:00","2016-09-21 13:00","당일",null,null,null,201607070215,"-"]
[328,"경남","통영","거제S/S #1-2 Sh.C GIS","거제S/S 154kV #1-2Sh.C GIS 보통점검","거제S/S 154kV #1-2Sh.C GIS 보통점검","2016-09-29 09:30","2016-09-29 18:30","2016-09-29 09:30","2016-09-29 18:30","당일",null,null,null,201607080160,"-"]
[329,"경남","통영","거제S/S #1-1 Sh.C GIS","거제S/S 154kV #1-1Sh.C GIS 보통점검","거제S/S 154kV #1-1Sh.C GIS 보통점검","2016-09-28 09:30","2016-09-28 18:30","2016-09-28 09:30","2016-09-28 18:30","당일",null,null,null,201607080159,"-"]
[330,"경남","통영","신고성거제#2 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-거제T/L 가철탑 설치 및 전선이설","2016-09-25 07:00","2016-09-25 19:00","2016-09-18 07:00","2016-09-18 19:00","당일",null,null,"계통안정",201607080065,"-"]
[331,"경남","통영","신고성고성 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-통영T/L 가철탑 설치 및 전선이설","2016-09-18 07:00","2016-09-18 19:00","2016-09-25 07:00","2016-09-25 19:00","당일",null,null,"계통안정",201607080067,"-"]
[332,"경남","통영","신고성통영 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-통영T/L 가철탑 설치 및 전선이설","2016-09-17 07:00","2016-09-17 19:00","2016-09-24 07:00","2016-09-24 19:00","당일",null,null,"계통안정",201607080066,"-"]
[333,"경남","통영","신고성거제#1 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-거제T/L 가철탑 설치 및 전선이설","2016-09-24 07:00","2016-09-24 19:00","2016-09-17 07:00","2016-09-17 19:00","당일",null,null,"계통안정",201607080064,"-"]
[334,"경남","통영","신마산진동 T/L","154kV 진동-안정T/L 안전이격","154kV 진동-안정T/L 안전이격 - 공사구간 : No.1~85","2016-09-26 07:00","2016-09-27 19:00","2016-09-26 07:00","2016-09-27 19:00","매일",null,null,null,201607080331,"-"]
[335,"경남","통영","진동안정#2 T/L","154kV 진동-안정T/L 피뢰기 및 SB Damper 설치공사","154kV 진동-안정T/L 피뢰기 및 SB Damper 설치공사 - 공사구간 : No.1~85","2016-09-24 07:00","2016-09-30 19:00","2016-09-25 07:00","2016-10-01 19:00","매일",null,null,"계통안정",201607080280,"-"]
["추가1","대구경북","포항","신포항영일#2T/L","345kV 영포T/L 피뢰기설치공사 안전확보","345kV 영포T/L 피뢰기설치공사 안전확보","2016-09-21 08:00","2016-09-21 18:00","2016-09-21 08:00","2016-09-21 18:00","당일"]

{"sheet":"Sheet1","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}