{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["765송부","345송부","154송부","한수원"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":16,"n_cols":16,"rows_kept":16,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2016년도 11월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S 765kV #1 BUS","765kV 신가평S/S #1M.Tr 증설공사","○ 변압기 : 765kV 1,000MVA X 1Bank ○ 개폐장치 : 800kV X 2CB(1BAY), 362kV X 2CB(1BAY) ○ 보호배전반 설치 × 1식 ○ 제어케이블 포설 및 결선 × 1식 ○ 기초 및 접지시공 × 1식 ○ 기타 부대공사 × 1식","2016-11-01 09:00","2016-11-15 18:00","2016-11-01 09:00","2016-11-15 18:00","연속",null,null,null,201609050161]
[2,"경기북부","구리","신가평S/S 765kV #2 BUS","765kV 신가평S/S #1M.Tr 증설공사","○ 변압기 : 765kV 1,000MVA X 1Bank ○ 개폐장치 : 800kV X 2CB(1BAY), 362kV X 2CB(1BAY) ○ 보호배전반 설치 × 1식 ○ 제어케이블 포설 및 결선 × 1식 ○ 기초 및 접지시공 × 1식 ○ 기타 부대공사 × 1식","2016-11-16 09:00","2016-11-30 18:00","2016-11-16 09:00","2016-11-30 18:00","연속",null,null,null,201609050162]
[3,"경기북부","구리","신태백신가평#2 T/L","신가평S/S #1M.Tr 증설공사","oM.Tr(333.35MVA x 3대) oGIS(800kV 및 362kV) 2CB o기타부대설비 1식","2016-11-04 09:00","2016-11-04 18:00","2016-11-04 09:00","2016-11-04 18:00","당일",null,null,null,201609270025]
[4,"경기","성남","신안성S/S #2 M.Tr A-1","16-17년 변전협력회사 총액공사","권선온도에 따른 시지연 트립 회로 변경","2016-11-28 09:00","2016-12-02 18:00","2016-11-28 09:00","2016-12-02 18:00","연속",null,null,null,201609130293]
[5,"경기","성남","신안성S/S #4 M.Tr A-1","16-17년 변전협력회사 총액공사","권선온도에 따른 시지연 트립 회로 변경/ELCB교체/소내배전반교체/IVR 과열보수","2016-11-01 09:00","2016-11-18 18:00","2016-11-01 09:00","2016-11-18 18:00","연속",null,null,null,201609130296]
[6,"경기","성남","신안성S/S #3 M.Tr A-1","16-17년 변전협력회사 총액공사","권선온도에 따른 시지연 트립 회로 변경","2016-11-21 09:00","2016-11-25 18:00","2016-11-21 09:00","2016-11-25 18:00","연속",null,null,null,201609130291]
[7,"강원","태백","신태백S/S 신태백-신한울NP#2T/L GIS(8371)","신태백S/S 765kV 송전선로 보호반 교체공사","765kV 신태백-신한울N/P #2T/L 보호배전반 설치 및 연동시험","2016-11-21 09:00","2016-11-30 18:00","2016-11-21 09:00","2016-11-30 18:00","연속",null,null,null,201609060003]
[8,"강원","태백","신태백-신한울NP#2T/L-#2M.Tr1차 GIS(8300)","신태백S/S 765kV 송전선로보호반 교체공사","765kV 신태백-신한울N/P #2T/L 보호배전반 설치 및 연동시험","2016-11-21 09:00","2016-11-30 18:00","2016-11-21 09:00","2016-11-30 18:00","연속",null,null,null,201609060007]
[9,"대전충남","서산","당진T/P 5호기 1차 CB","2016년 서산P/O 765/345kV GIS 점검공사","○765kV GIS 보통점검","2016-11-28 10:00","2016-11-29 18:00","2016-11-28 10:00","2016-11-29 18:00","연속",null,null,null,201609090301]
[10,"대전충남","서산","신서산S/S #3 M.Tr 1차 CB","신서산S/S 765kV 변전설비 정밀점검","○ 신서산S/S 765kV 변전설비 정밀점검 - 765kV GIS CB, DS부 정밀점검","2016-11-04 10:00","2016-11-18 18:00","2016-11-04 10:00","2016-11-18 18:00","연속",null,null,null,201609190199]
[11,"대전충남","서산","신서산S/S #3 M.Tr","신서산S/S 765kV 변전설비 정밀점검","○ 신서산S/S 변전설비 정밀점검 - M.Tr 내부 정밀점검 - 765kV GIS, DS 부 내부정밀점검 - 3차측 C상(Right) 절연보강","2016-11-04 10:00","2016-11-11 18:00","2016-11-04 10:00","2016-11-11 18:00","연속",null,null,null,201609120265]
[12,"대전충남","서산","신서산S/S 765kV #2 BUS","신서산S/S 765kV 변전설비 정밀점검","○ 신서산S/S 765kV 변전설비 정밀점검 - 765kV GIS CB, DS부 정밀점검","2016-11-11 10:00","2016-11-18 18:00","2016-11-11 10:00","2016-11-18 18:00","연속",null,null,null,201609190196]

{"sheet":"345송부","index":1,"n_rows":199,"n_cols":16,"rows_kept":199,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2016년도 11월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","미금성동#1 T/L","345kV 성동S/S 장기사용 모자익반 교체공사","345kV 성동S/S 장기사용 모자익반 교체공사","2016-11-14 10:00","2016-11-22 18:00","2016-11-16 10:00","2016-11-22 18:00","연속",null,null,null,201609120461]
[2,"서울","성동","성동S/S #3 M.Tr A","345kV 성동S/S 장기사용 모자익반 교체공사","345kV 성동S/S 장기사용 모자익반 교체공사","2016-11-30 10:00","2016-12-06 18:00","2016-11-23 10:00","2016-11-30 18:00","연속",null,null,null,201609120464]
[3,"서울","성동","성동S/S #4 M.Tr A","345kV 성동S/S 장기사용 모자익반 교체공사","345kV 성동S/S 장기사용 모자익반 교체공사","2016-11-23 10:00","2016-11-29 18:00","2016-11-04 10:00","2016-11-15 18:00","연속",null,null,null,201609120463]
[4,"서울","성동","성동S/S #1 M.Tr A","345kV 성동S/S 장기사용 모자익반 교체공사","345kV 성동S/S 장기사용 모자익반 교체공사","2016-11-14 10:00","2016-11-22 18:00","2016-11-16 10:00","2016-11-22 18:00","연속",null,null,null,201609120462]
[5,"서울","중부","중부S/S #3 M.Tr A","2016~2017년 중부전력지사 변전협력업체 총액공사","중부S/S 345kV #3M.Tr 보호배전반 교체","2016-11-28 10:00","2016-12-02 18:00","2016-11-28 10:00","2016-12-02 18:00","연속",null,null,null,201609080082]
[6,"남서울","강남","신양재S/S 신성남-신양재#2T/L#2 M.Tr1차CB (7200)","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","2016-11-14 09:00","2016-11-16 18:00","2016-11-14 09:00","2016-11-16 18:00","연속",null,null,null,201607110073]
[7,"남서울","강남","신양재S/S 345kV #2 BUS","강남전력지사 362kV GIS 정밀점검 공사-변전전문회사","강남전력지사 362kV GIS 정밀점검 공사-변전전문회사","2016-11-23 10:00","2016-11-24 18:00","2016-11-23 10:00","2016-11-24 18:00","연속",null,null,null,201609220081]
[8,"남서울","강남","신양재S/S 345kV #2 BUS","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","2016-11-02 09:00","2016-11-04 18:00","2016-11-02 09:00","2016-11-04 18:00","연속",null,null,null,201607110064]
[9,"남서울","강남","신양재S/S #2 M.Tr 1차 CB (7272)","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","2016-11-07 09:00","2016-11-09 18:00","2016-11-07 09:00","2016-11-09 18:00","연속",null,null,null,201607110067]
[10,"남서울","강남","신양재S/S #2 M.Tr A","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","2016-11-09 09:00","2016-11-12 18:00","2016-11-09 09:00","2016-11-12 18:00","연속",null,null,null,201607110071]
[11,"남서울","강남","신성남신양재#2 T/L","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","2016-11-16 09:00","2016-11-17 18:00","2016-11-16 09:00","2016-11-17 18:00","연속",null,null,null,201607110074]
[12,"남서울","강남","신양재S/S #1 M.Tr 1차 CB (7172)","강남전력지사 362kV GIS 정밀점검 공사-변전전문회사","강남전력지사 362kV GIS 정밀점검 공사-변전전문회사","2016-11-21 10:00","2016-11-23 18:00","2016-11-21 10:00","2016-11-23 18:00","연속",null,null,null,201609220080]
[13,"남서울","동서울","신성남동서울#2 T/L","345kV 신성남-동서울T/L 정밀점검","대상 : No.1~No.22 (21기) 내용 : 철탑 기별 및 전선 충전부 점검","2016-11-21 09:00","2016-11-23 18:00","2016-11-21 09:00","2016-11-23 18:00","연속",null,null,null,201609200150]
[14,"남서울","영서","영서S/S #4 M.Tr A","2016년 영서P/O 변전협력회사 총액공사_보통점검","- 345kV GCB(7471) 보통점검 - 345kV GCB(7400) 보통점검","2016-11-07 09:00","2016-11-08 18:00","2016-11-07 09:00","2016-11-08 18:00","연속",null,null,null,201609190136]
[15,"남서울","영서","영서S/S #2 M.Tr 1차-영서#2T/L CB (7200)","2016년 영서P/O 변전협력회사 총액공사_보통점검","- 345kV #2 M.Tr 1차-영서#2T/L GCB(7200) 보통점검","2016-11-09 09:00","2016-11-09 18:00","2016-11-09 09:00","2016-11-09 18:00","당일",null,null,null,201609190146]
[16,"남서울","직할","영등포S/S #3 M.Tr A","변전총액공사(주변압기 보통점검)","변전총액공사(주변압기 보통점검)","2016-11-21 09:30","2016-11-22 18:00","2016-11-21 09:30","2016-11-22 18:00","연속",null,null,"신뢰도개선",201609210076]
[17,"남서울","직할","영등포S/S #2 M.Tr A","변전총액공사(주변압기 보통점검)","변전총액공사(주변압기 보통점검)","2016-11-14 09:30","2016-11-15 18:00","2016-11-14 09:30","2016-11-15 18:00","연속",null,null,"신뢰도개선",201609210074]
[18,"남서울","직할","영등포S/S #1 M.Tr A","변전총액공사(주변압기 보통점검)","변전총액공사(주변압기 보통점검)","2016-11-07 09:30","2016-11-08 18:00","2016-11-07 09:30","2016-11-08 18:00","연속",null,null,"신뢰도개선",201609210073]
[19,"인천","김포","신김포신인천CC T/L","345kV신김포-신인천CCT/L 피뢰기 열화진단","○ 피뢰기 및 C/H접속개소 점검 - 내 용 : 도블테스트, 절연저항, 누설전류, 금구류 오결합 여부 점검 - 구 간 : 345kV 신김포-신인천CCT/L EB-A","2016-11-02 09:00","2016-11-02 18:00","2016-11-05 09:00","2016-11-05 18:00","연속",null,null,null,201609280008]
[20,"인천","시흥","신시흥#1S/S #3 M.Tr 1차 GIS","신시흥#1S/S #3 M.Tr 1차 GIS(7872) 정밀점검","신시흥#1S/S #3 M.Tr 1차 GIS(7872) 정밀점검","2016-11-07 09:00","2016-11-09 18:00","2016-11-07 09:00","2016-11-09 18:00","연속",null,null,null,201609130042]
[21,"인천","시흥","신시흥#2S/S #4 M.Tr 1차 GIS","신시흥#2S/S #4 M.Tr 1차 GIS(7672) 정밀점검","신시흥#2S/S #4 M.Tr 1차 GIS(7672) 정밀점검","2016-11-02 09:00","2016-11-04 18:00","2016-11-02 09:00","2016-11-04 18:00","연속",null,null,null,201609130041]
[22,"인천","인천","신경서S/S 345kV #1 BUS","신경서S/S #1Sh.R 대체공사","- 345㎸ #1Sh.R 대체 × 1대 - 제어케이블 결선 및 분리 × 1식 - 각종 시험 및 연동시험 등 × 1식 - 기타 부대작업 × 1식","2016-11-24 09:00","2016-11-27 18:00","취소","취소","연속",null,null,null,201609090269]
[23,"인천","인천","신경서S/S 345kV #1 Sh.R","신경서S/S #1Sh.R 대체공사","- 345㎸ #1Sh.R 대체 × 1대 - 제어케이블 결선 및 분리 × 1식 - 각종 시험 및 연동시험 등 × 1식 - 기타 부대작업 × 1식","2016-11-14 09:00","2016-11-27 18:00","2016-11-21 09:00","2016-12-04 18:00","연속",null,null,null,201609090221]
[24,"인천","인천","신인천C/C 4MT201 CB (7872)","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- 78Bay(7872CB) 대체","2016-11-10 10:00","2016-11-16 17:00","2016-11-14 10:00","2016-11-22 17:00","연속",null,null,null,201609120285]
[25,"인천","인천","신인천C/C 3MT001 CB (7671)","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- 76Bay(7671CB) 대체","2016-11-02 10:00","2016-11-08 17:00","2016-11-02 10:00","2016-11-10 17:00","연속",null,null,null,201609120282]
[26,"인천","인천","인천CC S/Y #1Tie-Tr A","인천CC S/Y #1Tie-Tr A,B,C상 주변압기 정밀점검","인천CC S/Y #1Tie-Tr A,B,C상 주변압기 정밀점검","2016-11-07 09:00","2016-11-19 18:00","2016-11-07 09:00","2016-11-19 18:00","연속",null,null,null,201608160096]
[27,"인천","직할","서인천CC-신부평#3T/L-#3 M.Tr 1차 CB (7300)","신부평S/S 345kV BUSTIE GIS(7300) 정밀점검","신부평S/S 345kV BUSTIE GIS(7300) 정밀점검","2016-11-07 09:00","2016-11-09 18:00","2016-11-07 09:00","2016-11-09 18:00","연속",null,null,null,201609120388]
[28,"인천","직할","신부평S/S 서인천CC-신부평#3T/L CB (7371)","신부평S/S 서인천신부평#3T/L GIS(7371) 정밀점검","신부평S/S 서인천신부평#3T/L GIS(7371) 정밀점검","2016-11-01 09:00","2016-11-04 18:00","2016-11-01 09:00","2016-11-04 18:00","연속",null,null,null,201609120382]
[29,"인천","직할","신부평S/S 서인천CC-신부평#4T/L CB (7471)","신부평S/S 서인천신부평#4T/L GIS(7471) 정밀점검","신부평S/S 서인천신부평#4T/L GIS(7471) 정밀점검","2016-11-14 09:00","2016-11-16 18:00","2016-11-14 09:00","2016-11-16 18:00","연속",null,null,null,201609120390]
[30,"인천","직할","신부평S/S 345kV #3 Sh.R CB (7379)","신부평S/S 345kV #3Sh.R CB(7379) 정밀점검","신부평S/S 345kV #3Sh.R CB(7379) 정밀점검","2016-11-10 09:00","2016-11-12 18:00","2016-11-10 09:00","2016-11-12 18:00","연속",null,null,null,201609120389]
[31,"경기북부","구리","신가평S/S 345kV #2 Sh.R","2016~17 구리전력지사 변전협력회사 총액공사","신가평S/S 345kV #2Sh.R 7371,7300 CB 보통점검","2016-11-01 09:00","2016-11-01 18:00","2016-11-01 09:00","2016-11-01 18:00","당일",null,null,null,201609120005]
[32,"경기북부","구리","신포천동두천복합#2 T/L","신포천동두천CC T/L 초기점검","신포천동두천CC #2T/L No.6~22호 초기점검 시행","2016-11-14 09:00","2016-11-17 18:00","2016-11-14 09:00","2016-11-17 18:00","연속",null,null,null,201609120328]
[33,"경기북부","구리","신포천동두천복합#1 T/L","신포천동두천CC T/L 초기점검","신포천동두천CC #1T/L No.6~22호 초기점검 시행","2016-11-22 09:00","2016-11-25 18:00","2016-11-22 09:00","2016-11-25 18:00","연속",null,null,null,201609120323]
[34,"경기북부","직할","신의정부S/S #2 Sh.R 1차 GIS CB","16년 경기북부직할변전총액공사","GIS 보통점검","2016-11-30 09:00","2016-11-30 18:00","2016-11-30 09:00","2016-11-30 18:00","당일",null,null,null,201609120006]
[35,"경기북부","직할","양주중부#2 T/L","345kV 양주-중부TL 접속함 교체공사","- 대상선로 : 345kV 양주-중부#2TL - 교체대상 : J/B1~11 등 11개소 33상 접속함 - 내용 : 접속함 교체(PJ Type --- PMJ Type 교체)","2016-11-17 09:00","2016-12-14 18:00","2016-11-17 09:00","2016-12-14 18:00","연속",null,null,null,201607110232]
[36,"경기북부","파주","신파주신덕은#2 T/L","154kV 신덕은-원흥T/L 장기사용 전력선교체공사","전력선교체 : 4.319km * 4회선병행선로 : 345kV 신파주-신덕은T/L No.62~68호간","2016-11-29 08:00","2016-12-04 18:00","2016-11-29 08:00","2016-12-04 18:00","연속",null,null,null,201609130251]
[37,"경기북부","파주","신파주신덕은#1 T/L","154kV 신덕은-원흥T/L 장기사용 전력선교체공사","전력선교체 : 4.319km * 4회선병행선로 : 345 신파주-신덕은T/L No.62~68","2016-11-25 08:00","2016-11-28 18:00","2016-11-25 08:00","2016-11-28 18:00","연속",null,null,null,201609130252]
[38,"경기북부","파주","신덕은S/S #2 M.Tr A","신덕은S/S #2M.Tr 2차 GIB 순환전류 저감공사","신덕은S/S #2M.Tr 2차 GIB 순환전류 저감을 위한 절연링 설치","2016-11-22 09:30","2016-11-24 18:00","2016-11-22 09:30","2016-11-24 18:00","연속",null,null,null,201609110036]
[39,"경기북부","파주","신덕은동두천복합#2 T/L","345kV 신덕은동두천복합#2T/L 애자교체공사","345kV 신덕은동두천복합#2T/L No.135 등 9기 애자교체공사 (폴리머애자 시료발취)","2016-11-21 07:00","2016-11-26 18:00","2016-11-21 07:00","2016-11-26 18:00","연속",null,null,null,201608160158]
[40,"경기북부","파주","신덕은S/S #1 M.Tr A","신덕은S/S #1M.Tr 2차 GIB 순환전류 저감공사","신덕은S/S #1M.Tr 2차 GIB 순환전류 저감을 위한 절연링 설치","2016-11-15 09:30","2016-11-17 18:00","2016-11-15 09:30","2016-11-17 18:00","연속",null,null,null,201609110035]
[41,"경기북부","파주","신덕은동두천복합#1 T/L","신덕은동두천CC T/L 초기점검","신덕은동두천CC #1T/L No.1~17호 초기점검 시행","2016-11-14 09:00","2016-11-17 18:00","2016-11-14 09:00","2016-11-17 18:00","연속",null,null,null,201609120329]
[42,"경기북부","파주","신덕은S/S #4 M.Tr A","신덕은S/S #4M.Tr 2차 GIB 순환전류 저감공사","신덕은S/S #4M.Tr 2차 GIB 순환전류 저감을 위한 절연링 설치","2016-11-29 09:30","2016-12-01 18:00","2016-11-29 09:30","2016-12-01 18:00","연속",null,null,null,201609110037]
[43,"경기북부","파주","신파주양주#1 T/L","신파주S/S CLR 설치공사","1.신파주-신김포 #2T/L 3상 GIB 설치(3층 ~지상 1층)- 설치시 근접작업 2. CLR 설치 - 장비사용시 근접선로 안전작업위한 3. 기타작업 등","2016-11-13 09:00","2016-11-18 18:00","2016-11-13 09:00","2016-11-18 18:00","연속",null,null,null,201607110419]
[44,"경기북부","파주","신파주양주#1 T/L","신파주S/S CLR 설치공사","1.신파주-신김포 #2T/L A상 WALL BUSHING 철거","2016-11-07 09:00","2016-11-07 18:00","2016-11-07 09:00","2016-11-07 18:00","당일",null,null,null,201607110418]
[45,"경기북부","파주","신파주양주#2 T/L","신파주S/S CLR 설치공사","1. 신김포-신파주#1T/L A상 WALL BUSHING 철거(근접작업으로 안전)","2016-11-06 09:00","2016-11-06 18:00","2016-11-06 09:00","2016-11-06 18:00","당일",null,null,null,201607110427]
[46,"경기북부","파주","신김포신파주#2 T/L","신파주S/S CLR 설치공사","1. 362kV GIB 일부 철거 및 설치 2. 345kV CLR 설치 및 모선배선","2016-11-05 09:00","2016-11-25 18:00","2016-11-05 09:00","2016-11-25 18:00","연속",null,null,null,201607110414]
[47,"경기","군포","서서울영서#1 T/L","서서울S/S Local House 전력설비 이설공사","서서울S/S Local House 전력설비 이설공사 - 송전선로보호 PNL 신설 - 제어케이블 포설 및 결선","2016-11-14 07:00","2016-11-22 18:00","2016-11-14 07:00","2016-11-22 18:00","연속",null,null,null,201609120010]
[48,"경기","군포","신온양서서울#2 T/L","서서울S/S Local House 전력설비 이설공사","서서울S/S Local House 전력설비 이설공사 - 송전선로보호 PNL 신설 - 7772CB 교체(투입저항부 설치)","2016-11-06 07:00","2016-11-12 18:00","2016-11-06 07:00","2016-11-12 18:00","연속",null,null,null,201609120004]
[49,"경기","군포","서서울S/S #2 M.Tr A","서서울S/S Local House 전력설비 이설공사","서서울S/S Local House 전력설비 이설공사 - 송전선로보호 PNL 신설 - 제어케이블 포설 및 결선","2016-11-14 07:00","2016-11-22 18:00","2016-11-14 07:00","2016-11-22 18:00","연속",null,null,null,201609120016]
[50,"경기","군포","서서울S/S #1 M.Tr A","서서울S/S Local House 전력설비 이설공사","서서울S/S Local House 전력설비 이설공사 - 송전선로보호 PNL 신설 - 제어케이블 포설 및 결선","2016-11-24 07:00","2016-11-26 18:00","2016-11-24 07:00","2016-11-26 18:00","연속",null,null,null,201609120018]
[51,"경기","군포","서서울S/S 345kV #1 BUS GIS","서서울S/S Local House 전력설비 이설공사","서서울S/S Local House 전력설비 이설공사 - 모선보호 PNL 신설 - 제어케이블 포설 및 결선","2016-11-27 07:00","2016-11-28 18:00","2016-11-27 07:00","2016-11-28 18:00","연속",null,null,null,201609120022]
[52,"경기","군포","화성서서울#2 T/L","345kV 화성-신안산T/L 피뢰기 설치공사","- 345kV 화성-신안산T/L 3~6호간 피뢰기 설치 관련 안전이격거리확보","2016-11-10 07:00","2016-11-10 18:00","2016-11-10 07:00","2016-11-10 18:00","당일",null,null,null,201609050149]
[53,"경기","군포","서서울S/S 345kV #2 BUS GIS","서서울S/S Local House 전력설비 이설공사","서서울S/S Local House 전력설비 이설공사 - 모선보호 PNL 신설 - 제어케이블 포설 및 결선","2016-11-29 07:00","2016-11-30 18:00","2016-11-29 07:00","2016-11-30 18:00","연속",null,null,null,201609120024]
[54,"경기","군포","신안산S/S #4 M.Tr 1차 CB (7372)","345kV 신안산SS 감시제어반 교체 공사","345kV 신안산SS 감시제어반 교체 공사 - #4MTr 관련 조작 및 감시회로 이설","2016-11-01 09:00","2016-11-05 18:00","2016-11-01 09:00","2016-11-05 18:00","연속",null,null,null,201608050199]
[55,"경기","군포","신안산S/S #1 M.Tr 1차 CB (7172)","345kV 신안산SS 감시제어반 교체 공사","345kV 신안산SS 감시제어반 교체 공사 - #1MTr 관련 조작 및 감시회로 이설","2016-11-28 09:00","2016-12-02 18:00","2016-11-28 09:00","2016-12-02 18:00","연속",null,null,null,201608050201]
[56,"경기","군포","신안산S/S #3 M.Tr 1차 CB (7271)","345kV 신안산SS 감시제어반 교체 공사","345kV 신안산SS 감시제어반 교체 공사 - #3MTr 관련 조작 및 감시회로 이설","2016-11-21 09:00","2016-11-25 18:00","2016-11-21 09:00","2016-11-25 18:00","연속",null,null,null,201608050200]
[57,"경기","군포","화성신안산 T/L","345kV 화성-신안산T/L 피뢰기 설치공사","- 1~56호 피뢰기 설치","2016-11-10 07:00","2016-11-16 18:00","2016-11-10 07:00","2016-11-16 18:00","연속",null,null,null,201609050148]
[58,"경기","성남","신안성-서안성#1T/L CB (7371)","서안성S/S 신안성-서안성#1T/L CB 보통점검","서안성S/S 신안성-서안성#1T/L CB 보통점검","2016-11-15 09:00","2016-11-15 18:00","2016-11-15 09:00","2016-11-15 18:00","당일",null,null,null,201609070209]
[59,"경기","성남","서안성S/S #2 M.Tr A","서안성S/S #2M.Tr 보호반 회로변경","서안성S/S #2M.Tr 보호반 회로변경","2016-11-30 09:00","2016-11-30 14:00","2016-11-30 09:00","2016-11-30 14:00","당일",null,null,null,201609070204]
[60,"경기","성남","서안성S/S #1 M.Tr A","서안성S/S #1M.Tr 보통점검","서안성S/S #1M.Tr 보통점검 7172,6144 보통점검","2016-11-28 09:00","2016-11-29 18:00","2016-11-28 09:00","2016-11-29 18:00","연속",null,null,null,201609070203]
[61,"경기","성남","서안성신진천#2 T/L","서안성S/S 서안성신진천#2T/L 7171, 7100 GIS 보통점검","서안성S/S 서안성신진천#2T/L 7171, 7100 GIS 보통점검","2016-11-14 09:00","2016-11-14 18:00","2016-11-14 09:00","2016-11-14 18:00","당일",null,null,null,201609070206]
[62,"경기","성남","신성남S/S STATCOM Tr CB","신성남S/S STATCOM Tr 초기점검","신성남S/S STATCOM Tr,7000,7072,LA 초기점검","2016-11-21 09:00","2016-11-24 18:00","2016-11-21 09:00","2016-11-24 18:00","연속",null,null,null,201609090330]
[63,"경기","성남","신성남동서울#2 T/L","345kV 신용인-동서울T/L(태전) OPGW 증설공사","345kV 신용인-동서울T/L(태전) OPGW 증설공사 OPGW 120SQ 15km , 70SQ 30km 교체 및 증설","2016-11-21 07:00","2016-11-22 18:00","2016-11-21 07:00","2016-11-22 18:00","연속",null,null,null,201609080088]
[64,"경기","성남","신성남S/S #1M.Tr A","신성남S/S 모자익 대체공사(#1M.Tr TCC PNL)","신성남S/S 모자익 대체공사(#1M.Tr TCC PNL) BF반 대체","2016-11-28 09:00","2016-12-03 18:00","2016-11-28 09:00","2016-12-03 18:00","연속",null,null,null,201609070197]
[65,"경기","성남","신성남S/S #2 M.Tr A","신성남S/S 모자익 대체공사(#2M.Tr TCC PNL)","신성남S/S 모자익 대체공사(#2M.Tr TCC PNL)","2016-11-14 09:00","2016-11-18 18:00","2016-11-14 09:00","2016-11-18 18:00","연속",null,null,null,201609070195]
[66,"경기","성남","신성남S/S #4M.Tr A","신성남S/S 모자익 대체공사(#4M.Tr TCC PNL)","신성남S/S 모자익 대체공사(#4M.Tr TCC PNL)","2016-11-07 09:00","2016-11-12 18:00","2016-11-07 09:00","2016-11-12 18:00","연속",null,null,null,201609070196]
[67,"경기","성남","신수원S/S #2 M.Tr A","신수원S/S 345kV #2M.Tr 정밀점검","신수원S/S 345kV #2M.Tr 정밀점검","2016-11-07 09:00","2016-11-22 18:00","2016-11-07 09:00","2016-11-22 18:00","연속",null,null,null,201609200054]
[68,"경기","성남","신수원S/S 신안성-신수원#2T/L CB (7371)","신수원S/S 신안성-신수원#2T/L CB 보통점검","신수원S/S 신안성-신수원#2T/L CB 보통점검","2016-11-18 09:00","2016-11-18 18:00","2016-11-18 09:00","2016-11-18 18:00","당일",null,null,null,201609070210]
[69,"경기","성남","신안성S/S 신안성-신수원#1T/L CB (7972)","신안성S/S 345kV 7972 GIS 정밀점검","신안성S/S 345kV 7972 GIS 정밀점검, 보조계전기교체","2016-11-01 09:00","2016-11-03 18:00","2016-11-01 09:00","2016-11-03 18:00","연속",null,null,null,201609120164]
[70,"경기","성남","신안성S/S #6 Sh.R-신안성-신수원#1T/L CB (7900)","신안성S/S 345kV 7900 GIS 정밀점검","신안성S/S 345kV 7900 GIS 정밀점검, 보조계전기교체","2016-11-07 09:00","2016-11-09 18:00","2016-11-07 09:00","2016-11-09 18:00","연속",null,null,null,201609120166]
[71,"경기","성남","신안성S/S #6 Sh.R CB (7971) (7971)","신안성S/S 345kV 7971 GIS 정밀점검","신안성S/S 345kV 7971 GIS 정밀점검, 보조계전기교체","2016-11-14 09:00","2016-11-16 18:00","2016-11-14 09:00","2016-11-16 18:00","연속",null,null,null,201609120172]
[72,"경기","성남","신안성S/S #5 M.Tr 2차 CB (7C71)","신안성S/S 345kV 7C71 GIS 정밀점검","신안성S/S 345kV 7C71 GIS 정밀점검, 보조계전기교체","2016-11-21 09:00","2016-11-23 18:00","2016-11-21 09:00","2016-11-23 18:00","연속",null,null,null,201609070192]
[73,"경기","성남","신안성S/S #2 M.Tr 2차 CB (7571)","신안성S/S #2 M.Tr 2차 CB 보통점검","신안성S/S #2 M.Tr 2차 CB 보통점검","2016-11-29 09:00","2016-11-29 18:00","2016-11-29 09:00","2016-11-29 18:00","당일",null,null,null,201609070211]
[74,"경기","성남","신용인S/S 345kV #2 BUS","345kV 신용인S/S 용량부족 GIS 대체공사","345kV 모선 및 모선DS GIS 용량대체","2016-11-14 09:00","2016-12-23 18:00","2016-11-14 09:00","2016-12-23 18:00","연속",null,null,null,201601140113]
[75,"경기","성남","동서울신용인#1 T/L","345kV 신용인-동서울T/L(태전) OPGW 증설공사","345kV 신용인-동서울T/L(태전) OPGW 증설공사 OPGW 120SQ 15km , 70SQ 30km 교체 및 증설","2016-11-11 07:00","2016-12-10 18:00","2016-11-11 07:00","2016-12-10 18:00","연속",null,null,null,201609080086]
[76,"경기","성남","신시흥신성남#1 T/L"," 군포송정지구 345kV 신시흥-신성남T/L 지장이설공사\n","○ 사업유형 : 가공송전 ○ 전압 : 345kV ○ 사업목적 : 군포송정지구 택지 개발사업과 관련으로 345kV신시흥-신성남T/L 지장구간에 대하여 지중으로 건설하고자 가공구간의 임시선로 및 본선로 건설 ○ 사업구간 : 기설 345kV 신시흥-신성남T/L No.48 ~ No.53 ○ 규모 : 철탑 8기, A480B, 2.357km ○ ","2016-11-15 06:30","2016-11-29 18:00","2016-11-15 06:30","2016-11-29 18:00","연속",null,null,null,201608050143]
[77,"경기","성남","신시흥신성남#2 T/L"," 군포송정지구 345kV 신시흥-신성남T/L 지장이설공사\n","○ 사업유형 : 가공송전 ○ 전압 : 345kV ○ 사업목적 : 군포송정지구 택지 개발사업과 관련으로 345kV신시흥-신성남T/L 지장구간에 대하여 지중으로 건설하고자 가공구간의 임시선로 및 본선로 건설 ○ 사업구간 : 기설 345kV 신시흥-신성남T/L No.48 ~ No.53 ○ 규모 : 철탑 8기, A480B, 2.357km ○ ","2016-11-30 06:30","2016-12-14 18:00","2016-11-30 06:30","2016-12-14 18:00","연속",null,null,null,201608050146]
[78,"경기","직할","화성신시흥 T/L","화성S/S 화성신시흥T/L GIS 보통점검","화성S/S 화성신시흥T/L GIS(7800,7871) 보통점검, CVT교체","2016-11-05 09:00","2016-11-05 18:00","2016-11-05 09:00","2016-11-05 18:00","당일",null,null,null,201609070099]
[79,"경기","직할","아산화성#1 T/L","345kV 아산-화성T/L 피뢰기 설치공사","미군기지내(No.69-72) 송전용피뢰기 4기 설치","2016-11-19 08:00","2016-11-19 18:00","2016-11-19 08:00","2016-11-19 18:00","당일",null,null,null,201609090107]
[80,"경기","직할","화성평택TP#1 T/L","화성S/S 화성평택T/P#1T/L CVT교체","화성S/S 화성평택T/P#1T/L CVT교체, 전자변히터 설치","2016-11-06 09:00","2016-11-06 18:00","2016-11-06 09:00","2016-11-06 18:00","당일",null,null,null,201609070102]
[81,"강원","동해","동해S/S 동해-북평TP#3T/L CB (7572)","2016년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해북평TP#3T/L GIS 초기점검(7572) 2. 동해S/S 동해북평TP#3T/L PT 초기점검 3. 동해S/S 동해북평TP#3T/L LS 초기점검","2016-11-07 09:30","2016-11-07 18:00","2016-11-07 09:30","2016-11-07 18:00","당일",null,null,null,201609090201]
[82,"충북","직할","신제천S/S 345kV #1 BUS","345kV 신제천S/S GIS화 공사","345KV GIS 설치","2016-11-01 09:00","2016-11-10 18:00","2016-11-01 09:00","2016-11-10 18:00","연속",null,null,null,201609070240]
[83,"충북","직할","신제천신영주#2 T/L","신제천S/S 신제천신영주#2 T/L LA 대체","신제천신영주#2 T/L LA 대체 작업","2016-11-01 10:00","2016-11-01 18:00","2016-11-01 10:00","2016-11-01 18:00","당일",null,null,null,201609050118]
[84,"충북","직할","신제천동해#1 T/L","신제천S/S 신제천동해#1T/L LA 대체","신제천동해#1T/L LA 대체 작업","2016-11-07 10:00","2016-11-07 18:00","2016-11-07 10:00","2016-11-07 18:00","당일",null,null,null,201609050116]
[85,"충북","직할","신충주S/S #2 M.Tr","신충주S/S #3M.Tr C상 정밀점검 공사","본체 내부정밀점검","2016-11-07 09:00","2016-11-11 18:00","2016-11-07 09:00","2016-11-11 18:00","연속",null,null,null,201609190062]
[86,"충북","청주","신옥천S/S 345kV #2 BUS","345kV 신옥천S/S 용량부족차단기 대체공사","1.신설 GIS 가압을 위한 모선연결 2.기타부대공사","2016-11-25 09:00","2016-11-25 18:00","2016-11-25 09:00","2016-11-25 18:00","당일",null,null,null,201609070022]
[87,"충북","청주","신옥천신계룡 T/L","345kV 신옥천S/S 용량부족차단기 대체공사","1.POST 및 BEAM 조립 2.기존 옥외모선과 신설 GIS 모선연결 3.신설 GIS 초기가압","2016-11-18 09:00","2016-11-25 18:00","2016-11-18 09:00","2016-11-25 18:00","연속",null,null,null,201609190012]
[88,"충북","청주","신옥천청양 T/L","345kV 신옥천S/S 용량부족차단기 대체공사","1.POST 및 BEAM 조립 2.기타부대공사","2016-11-18 09:00","2016-11-20 18:00","2016-11-18 09:00","2016-11-20 18:00","연속",null,null,null,201609190014,"○"]
[89,"충북","청주","신옥천S/S 345kV #1 BUS","345kV 신옥천S/S 용량부족차단기 대체공사","1.신설 GIS 가압을 위한 모선연결 2.기타부대공사","2016-11-21 09:00","2016-11-22 18:00","2016-11-21 09:00","2016-11-22 18:00","연속",null,null,null,201609070019]
[90,"충북","충주","서안성신진천#1 T/L","2016~17년 충주 송전정비 협력회사 총액공사(피뢰기설치,조류,애자)","피뢰기설치(1~35호), 조류착지방지장치 설치(2~33호), 불량애자교체(20-1호)","2016-11-01 08:00","2016-11-05 18:00","2016-10-30 08:00","2016-11-05 18:00","연속",null,null,"신뢰도개선",201609090248]
[91,"대전충남","대전","신계룡S/S 신계룡T/L-#1 M.Tr 1차 CB (7200)","○ 345kV 신계룡S/S 7200CB 투입저항기교체","○ 345kV 신계룡S/S 7200CB 투입저항기교체","2016-11-03 09:00","2016-11-03 18:00","2016-11-03 09:00","2016-11-03 18:00","당일",null,null,null,201609130349]
[92,"대전충남","서산","신서산신당진#1 T/L","345kV 신당진S/S CLR 설치공사","CLR x 2조 설치","2016-11-18 09:00","2016-11-25 18:00","2016-11-18 09:00","2016-11-25 18:00","연속",null,null,null,201607210062]
[93,"대전충남","서산","신서산신당진#2 T/L","345kV 신당진S/S CLR 설치공사","CLR x 2조 설치","2016-11-26 09:00","2016-12-05 18:00","2016-11-26 09:00","2016-12-05 18:00","연속",null,null,null,201607210063]
[94,"대전충남","서산","신당진S/S 345kV #70 BUS","신당진변전소 345kV GIS 모선 변형 보강공사","신당진변전소 345kV GIS 모선(70,75BUS) 변형 - 70BUS(74-75BAY간) X 1개소 - 75BUS(73-74BAY간, 75-76BAY간) X 1개소","2016-11-02 09:00","2016-11-04 18:00","2016-11-02 09:00","2016-11-04 18:00","연속",null,null,null,201609200115]
[95,"대전충남","서산","신당진-신당진개폐소#1 T/L","신당진변전소 345kV GIS 모선 변형 보강공사","신당진변전소 345kV GIS 모선(70,75BUS) 변형 - 70BUS(74-75BAY간) X 1개소 - 75BUS(73-74BAY간, 75-76BAY간) X 1개소","2016-11-02 09:00","2016-11-04 18:00","2016-11-02 09:00","2016-11-04 18:00","연속",null,null,null,201609200113]
[96,"대전충남","서산","신당진S/S 345kV #75 BUS","신당진변전소 345kV GIS 모선 변형 보강공사","신당진변전소 345kV GIS 모선(70,75BUS) 변형 - 70BUS(74-75BAY간) X 1개소 - 75BUS(73-74BAY간, 75-76BAY간) X 1개소","2016-11-07 09:00","2016-11-09 18:00","2016-11-07 09:00","2016-11-09 18:00","연속",null,null,null,201609200116]
[97,"대전충남","서산","태안T/P 345kV #70 BUS","태안화력 345kV 장기사용 GIS 교체공사","1.74BAY GIS(7472,7400) 철거(40KA, 4000A) 2 74BAY GIS(7472,7400) 설치(60kA, 6000A) 3 74BAY GIS(70BUS)철거,설치 4 74BAY GIS(75BUS)철거,설치","2016-11-15 09:00","2016-11-25 18:00","2016-11-15 09:00","2016-11-25 18:00","연속",null,null,null,201607120102]
[98,"대전충남","서산","태안T/P 345kV #70 BUS","태안화력 345kV 장기사용 GIS 교체공사","1. 74BAY GIS(7472,7400) 철거(40KA, 4000A) 2. 74BAY GIS(7472,7400) 설치(60KA, 6000A) 3. 74BAY GIS(70BUS) 철거,설치 4. 74BAY GIS(75BUS) 철거, 설치","2016-11-26 14:00","2016-11-28 14:00","2016-11-26 14:00","2016-11-28 14:00","연속",null,null,null,201608160190]
[99,"대전충남","세종","세종S/S #2 M.Tr A","[변전] 345kV 세종S/S #2M.Tr 계전기 성능개선","○ 계전기 성능개선","2016-11-10 09:30","2016-11-10 18:00","2016-11-10 09:30","2016-11-10 18:00","당일",null,null,null,201609060098]
[100,"대전충남","세종","세종S/S #3 M.Tr A","[변전] 345kV 세종S/S #3M.Tr 계전기 성능개선","○ 계전기 성능개선","2016-11-11 09:30","2016-11-11 18:00","2016-11-11 09:30","2016-11-11 18:00","당일",null,null,null,201609060099]
[101,"대전충남","아산","신온양S/S #3 M.Tr A","신온양S/S 345kV #3M.Tr 보통 점검","○ 345kV #3M.Tr 보통 점검 및 1, 2차 LA 보통점검 ○ 병행) #3M.Tr 1차 7572 GIS 보통점검 ○ 병행) #3M.Tr 2차 6344 GIS 보통점검","2016-11-21 09:00","2016-11-22 18:00","2016-11-21 09:00","2016-11-22 18:00","연속",null,null,null,201609120054]
[102,"대전충남","아산","신온양S/S #4 M.Tr A","신온양S/S 345kV #4M.Tr 보호배전반 제작사 성능 개선","○ 345kV #4M.Tr 보호배전반 제작사 성능 개선","2016-11-23 09:00","2016-11-23 18:00","2016-11-23 09:00","2016-11-23 18:00","당일",null,null,null,201609120059]
[103,"대전충남","아산","아산화성#2 T/L","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L, 345kV 아산-화성T/L 병가구간 가선작업 신설18호~기설28호 구간 전선 가선작업 기설18호~기설28호 구간 전선 철거작업 발받침 철탑 4기 및 보호망 2개소 설치(154kV 인주-탕정T/L 31~32호)","2016-11-15 07:00","2016-12-01 18:00","2016-11-15 07:00","2016-12-01 18:00","연속",null,null,null,201609070092]
[104,"대전충남","청양","보령TP-신보령TP T/L","신보령연락T/L 휴전 작업","○ 송전선로 보호반 통신알람에 따른 CPU 교체","2016-11-16 09:00","2016-11-16 18:00","2016-11-16 09:00","2016-11-16 18:00","당일",null,null,null,201608260037]
[105,"대전충남","청양","보령T/P 345kV #70 BUS","보령화력 제2발전소 362kV GIS 교체공사","○ 보령화력 345kV 70-71-0 GIS 교체","2016-11-10 09:00","2016-11-12 18:00","2016-11-10 09:00","2016-11-12 18:00","연속",null,null,null,201608120041]
[106,"대전충남","청양","보령T/P 70-71-0 SEC CB (70-71-0)","보령화력 제2발전소 362kV GIS 교체공사","○ 보령화력 345kV 70-71-0 GIS 교체","2016-11-10 09:00","2016-12-15 18:00","2016-11-10 09:00","2016-12-15 18:00","연속",null,null,null,201608120032]
[107,"대전충남","청양","보령T/P 345kV #71 BUS","보령화력 제2발전소 362kV GIS 교체공사","○ 보령화력 345kV 70-71-0 GIS 교체","2016-11-10 09:00","2016-11-12 18:00","2016-11-10 09:00","2016-11-12 18:00","연속",null,null,null,201608120043]
[108,"대전충남","청양","보령T/P #3,4 SU Tr 1차 CB (7372)","보령화력 제2발전소 362kV GIS 교체공사","○ 보령화력 345kV 75-76-0 GIS 교체(무부하가압)","2016-11-07 09:00","2016-11-09 18:00","2016-11-07 09:00","2016-11-09 18:00","연속",null,null,null,201609130246]
[109,"대전충남","청양","보령T/P #3 M.Tr 1차-#3,4 SU Tr 1차 CB (7300)","보령화력 제2발전소 362kV GIS 교체공사","○ 보령화력 345kV 75-76-0 GIS 교체(무부하가압)","2016-11-07 09:00","2016-11-09 18:00","2016-11-07 09:00","2016-11-09 18:00","연속",null,null,null,201609130245]
[110,"전북","군산","군산신김제#1 T/L","군산신김제#1 T/L 전선접속개소교체공사","○ 전선교체 - 구간 : No.90 ~ 93 , No.106 ~ 109 114~115, 127 ~ 128","2016-11-28 07:00","2016-12-10 18:00","2016-11-28 07:00","2016-12-10 18:00","연속",null,null,null,201609190138]
[111,"전북","김제","신김제S/S #1 M.Tr A","신김제S/S #1 M.Tr A","변압기 보통점검","2016-11-07 09:00","2016-11-10 18:00","2016-11-07 09:00","2016-11-10 18:00","연속",null,null,null,201608170091]
[112,"전북","김제","신김제S/S #4 M.Tr A","신김제S/S #4 M.Tr A","계전기 성능개선(제작사)","2016-11-11 09:00","2016-11-11 18:00","2016-11-11 09:00","2016-11-11 18:00","당일",null,null,null,201608300010]
[113,"전북","직할","신남원신광주#1 T/L","345kV 신남원S/S M.Tr 설치","362kV GIS CB×1대 증설","2016-11-28 10:00","2016-11-30 16:00","2016-11-28 10:00","2016-11-30 16:00","연속",null,null,null,201609190015]
[114,"전북","직할","신남원S/S 신남원-광양#1 - TIE GIS","2016년 전북직할 345kV 차단기 정밀점검공사","-. 345kV GIS(차단기) 정밀점검공사","2016-11-07 09:30","2016-11-10 18:00","2016-11-07 09:30","2016-11-10 18:00","연속",null,null,null,201608160126]
[115,"전북","직할","신남원의령#2 T/L","2016년 전북직할 345kV 차단기 정밀점검공사","-. 345kV GIS(차단기) 정밀점검공사 관련 무부하 시험가압","2016-11-18 10:00","2016-11-18 14:00","2016-11-18 10:00","2016-11-18 14:00","당일",null,null,null,201608160115]
[116,"전북","직할","신남원S/S 신남원-의 령#2 - TIE GIS","2016년 전북직할 345kV 차단기 정밀점검(7400)공사","-. 345kV GIS(차단기) 정밀점검공사","2016-11-15 09:30","2016-11-18 18:00","2016-11-15 09:30","2016-11-18 18:00","연속",null,null,null,201608160113]
[117,"전북","직할","신남원S/S 신남원-신광주#1 - TIE CB (7700)","345kV 신남원S/S M.Tr 설치","362kV GIS CB×1대 증설","2016-11-30 16:00","2016-12-19 16:00","2016-11-30 16:00","2016-12-19 16:00","연속",null,null,null,201609190018]
[118,"전북","직할","신남원한빛NP#1 T/L","345kV 신남원-한빛#1T/L 전선교체 등 3개 공사","전선교체 : 20~58호 6.971C-km 사선애자청소 : 21~81호 61기 항공장애표시구 교체 : 87~163호 31개 경간","2016-11-16 07:00","2016-11-26 18:00","2016-11-16 07:00","2016-11-26 18:00","연속",null,null,null,201608110148]
[119,"전북","직할","신남원광양#1 T/L","2016년 전북직할 345kV 차단기 정밀점검공사","-. 345kV GIS(차단기) 정밀점검공사 관련 무부하 시험가압","2016-11-10 10:00","2016-11-10 14:00","2016-11-10 10:00","2016-11-10 14:00","당일",null,null,null,201608160123]
[120,"전북","직할","신남원S/S 345kV #2 BUS","345kV 신남원S/S M.Tr 설치","362kV GIS CB×1대 증설","2016-11-28 10:00","2016-12-19 16:00","2016-11-28 10:00","2016-12-19 16:00","연속",null,null,null,201609190016]
[121,"광주전남","강진","신화순신강진#1 T/L","345kV 신화순-신강진#2T/L(GIS 초기점검)","2016~17년도 강진전력지사 변전협력회사 총액공사 - 2016. 11. 3 : 신강진S/S 신화순-신강진#1T/L GIS, LA 점검 2016. 11. 4 : 신강진S/S 72Bay BUS-TIE 7200 GIS 초기점검","2016-11-03 09:00","2016-11-04 18:00","2016-11-03 09:00","2016-11-04 18:00","당일",null,null,null,201609120541]
[122,"광주전남","강진","신강진S/S #2 M.Tr A","345kV 신강진S/S #2M.Tr(1,2차 차단기 보통점검)","2016~17년도 강진전력지사 변전협력회사 총액공사 - 2016. 11. 2 : 신강진S/S #2M.Tr 1,2차 차단기 보통점검","2016-11-02 09:00","2016-11-02 18:00","2016-11-02 09:00","2016-11-02 18:00","당일",null,null,null,201609120540]
[123,"광주전남","광주","신광주S/S #3 M.Tr A","신광주 #3M.Tr(16년 광주 345kV M.Tr 정밀)","#3M.Tr A, B, C상 정밀점검 #3Sh.R 보호반 대체","2016-11-01 09:00","2016-11-08 18:00","2016-11-01 09:00","2016-11-08 18:00","연속",null,null,null,201609050114]
[124,"광주전남","광주","신광주신화순#2 T/L","345kV신광주-신화순T/L 지상고확보공사","철탑교체 2기 전선교체 2경간","2016-11-08 07:00","2016-11-11 18:00","2016-11-08 07:00","2016-11-11 18:00","연속",null,null,null,201609190197]
[125,"광주전남","광주","신광주S/S #1 M.Tr A","신광주S/S #1M.Tr(3차 DS,VCB 점검등)","VCB 4189 보통점검 DS 4175-1,2, 4185, 4186 보통점검 #1M.Tr 3차 LA 대체","2016-11-10 09:00","2016-11-11 18:00","2016-11-10 09:00","2016-11-11 18:00","연속",null,null,null,201609090058]
[126,"광주전남","광주","신광주신화순#1 T/L","345kV신광주-신화순T/L 지상고확보공사","철탑교체 2기 전선교체 2경간","2016-11-12 07:00","2016-11-15 18:00","2016-11-12 07:00","2016-11-15 18:00","연속",null,null,null,201609190198]
[127,"광주전남","목포","신광주한빛NP#1 T/L","345kV 신광주-한빛NP T/L 전선접속개소전선교체공사","0 No.37~57호간 전력선 및 금구류 교체","2016-11-28 07:00","2016-12-07 18:00","2016-11-28 07:00","2016-12-07 18:00","연속",null,null,null,201609110039]
[128,"광주전남","목포","신광주한빛NP#2 T/L","345kV 신광주-한빛NP T/L 전선접속개소전선교체공사","0 No.37~57호간 전력선 및 금구류 교체","2016-11-18 07:00","2016-11-27 18:00","2016-11-18 07:00","2016-11-27 18:00","연속",null,null,null,201609110038]
[129,"광주전남","목포","한빛1NP-한빛2NP #2 T/L","345kV 한빛연락#2T/L(보호배전반 대체공사)","- 345kV B/F 보호배전반 대체 - 기타 GIS 보통점검","2016-11-09 09:00","2016-11-15 18:00","2016-11-09 09:00","2016-11-15 18:00","연속",null,null,"신뢰도개선",201608160004]
[130,"광주전남","순천","신남원광양#2 T/L","345kV 신남원-광양#2T/L(송전선로 피뢰기 설치)","피뢰기 설치 : 1~125호, 64기","2016-11-11 07:00","2016-11-19 18:00","2016-11-11 07:00","2016-11-19 18:00","연속",null,null,null,201609120505]
[131,"광주전남","순천","광양율촌CC T/L","345kV 광양-율촌CC T/L(피뢰기 설치)","피뢰기 설치 : 90~136호, 38기","2016-11-11 07:00","2016-11-19 18:00","2016-11-11 07:00","2016-11-19 18:00","연속",null,null,null,201609120503]
[132,"광주전남","순천","여수T/P #1 Tie-Tr A","345kV 여수T/P #1M.Tr(2차 GIS 정밀점검)","2016년 순천전력지사 하반기 GIS 정밀점검공사 - #1M.Tr 2차 GIS 정밀점검","2016-11-21 09:00","2016-11-23 18:00","2016-11-21 09:00","2016-11-23 18:00","연속",null,null,null,201609200072]
[133,"광주전남","순천","여수T/P #2 Tie-Tr A","345kV 여수T/P #2M.Tr(2차 GIS 정밀점검)","2016년 순천전력지사 하반기 GIS 정밀점검공사 - #1M.Tr 2차 GIS 정밀점검","2016-11-24 09:00","2016-11-26 18:00","2016-11-24 09:00","2016-11-26 18:00","연속",null,null,null,201609200075]
[134,"대구경북","경산","신경산대구#2 T/L","신경산S/S 신경산-대구#2T/L GIS 휴전(노후배전반 대체공사)","신경산S/S 노후배전반 대체공사","2016-11-02 09:00","2016-11-05 18:00","2016-11-02 09:00","2016-11-05 18:00","연속",null,null,null,201609070115]
[135,"대구경북","경산","신경산대구#1 T/L","신경산S/S 신경산-대구#1T/L GIS 휴전(노후배전반 대체공사)","신경산S/S 노후배전반 대체공사","2016-11-24 09:00","2016-12-02 18:00","2016-11-24 09:00","2016-12-02 18:00","연속",null,null,null,201609070119]
[136,"대구경북","경산","신경산S/S #1 M.Tr A","신경산S/S 345kV #1M.Tr 휴전(노후배전반 대체공사)","신경산S/S 노후배전반 대체공사","2016-11-14 09:00","2016-11-18 18:00","2016-11-14 09:00","2016-11-18 18:00","연속",null,null,null,201609070118]
[137,"대구경북","경산","신경산S/S #2 M.Tr A","신경산S/S 345kV #2M.Tr 휴전(노후배전반 대체공사)","신경산S/S 노후배전반 대체공사","2016-11-24 09:00","2016-12-02 18:00","2016-11-24 09:00","2016-12-02 18:00","연속",null,null,null,201609070120]
[138,"대구경북","경산","울주신경산#1 T/L","신경산S/S 울주-신경산#1T/L GIS 휴전(노후배전반 대체공사)","신경산S/S 노후배전반 대체공사","2016-11-06 09:00","2016-11-10 18:00","2016-11-06 09:00","2016-11-10 18:00","연속",null,null,null,201609070116]
[139,"대구경북","경산","신경산S/S #3 M.Tr A","신경산S/S 170kV 장기사용 GIS 대체공사","GIS 대체공사 관련 안전확보","2016-11-07 09:00","2016-11-14 18:00","2016-11-07 09:00","2016-11-14 18:00","매일",null,null,null,201609170015]
[140,"대구경북","경산","울주신경산#2 T/L","신경산S/S 울주-신경산#2T/L GIS 휴전(노후배전반 대체공사)","신경산S/S 노후배전반 대체공사","2016-11-11 09:00","2016-11-15 18:00","2016-11-11 09:00","2016-11-15 18:00","연속",null,null,null,201609070117]
[141,"대구경북","경산","신경산S/S #2 M.Tr A","신경산S/S 170kV 장기사용 GIS 대체공사","GIS 대체작업시 안전이격 확보","2016-11-01 09:00","2016-11-06 18:00","2016-11-01 09:00","2016-11-06 18:00","연속",null,null,null,201609280036]
[142,"대구경북","구미","선산S/S #2 M.Tr 1차 CB (7172)","선산S/S 345kV 7172 GIS 휴전","- 345kV GIS 보통점검","2016-11-18 09:00","2016-11-18 18:00","2016-11-18 09:00","2016-11-18 18:00","당일",null,null,null,201609190254]
[143,"대구경북","달성","고령S/S #4 M.Tr A","2016년 하반기 주변압기정밀점검","주변압기 정밀점검","2016-11-26 09:00","2016-11-28 18:00","2016-11-11 09:00","2016-11-13 18:00","연속",null,null,null,201609070070]
[144,"대구경북","달성","고령S/S #4 M.Tr A","2016년 하반기 주변압기정밀점검","주변압기 정밀점검","2016-11-04 09:00","2016-11-06 18:00","2016-11-04 09:00","2016-11-06 18:00","연속",null,null,null,201609070068]
[145,"대구경북","달성","고령S/S #4 M.Tr A","2016년 하반기 주변압기정밀점검","주변압기 정밀점검","2016-11-18 09:00","2016-11-20 18:00","2016-11-18 09:00","2016-11-20 18:00","연속",null,null,null,201609070069]
[146,"대구경북","달성","서대구고령#1 T/L","345kV 서대구-고령T/L 안전이격확보공사","서대구-고령T/L 안전이격확보공사 - 철탑교체 : 16,18호 - 전선교체 12~19호","2016-11-26 08:00","2016-12-07 18:00","2016-11-25 08:00","2016-12-07 18:00","연속",null,null,null,201609130095]
[147,"대구경북","달성","서대구고령#2 T/L","345kV 서대구-고령T/L 안전이격확보공사","서대구-고령T/L 안전이격확보공사 - 철탑교체 : 16,18호관련 안전확보","2016-11-26 08:00","2016-11-27 18:00","2016-11-25 08:00","2016-11-27 18:00","매일",null,null,null,201609130097]
[148,"대구경북","영주","한울1NP-한울2NP #2 T/L","통합감시제어구축, 71Bay B/F계전기 교체","통합감시제어구축, 71Bay B/F계전기 교체","2016-11-01 09:00","2016-11-04 18:00","2016-11-14 09:00","2016-11-17 18:00","당일",null,null,null,201609090068]
[149,"대구경북","영주","한울1NP-한울2NP #2 T/L","7100, 7172CB 정밀점검관련 Test T/L","7100, 7172CB 정밀점검관련 Test T/L","2016-11-11 13:00","2016-11-11 16:00","2016-11-24 13:00","2016-11-24 16:00","당일",null,null,null,201609090071]
[150,"대구경북","영주","신태백한울NP3 T/L","한울 3발 362kV GIS 대체공사","362kV GIS 용량부족 GIS(40kA-&gt50kA)12CB 대체공사 전담운영체계공사","2016-11-21 10:00","2016-11-23 18:00","2016-11-21 10:00","2016-11-23 18:00","연속",null,null,null,201609080252]
[151,"대구경북","칠곡","서대구S/S #3 M.Tr A","서대구S/S #3M.Tr 보호반 교체","서대구S/S #3M.Tr 보호반 교체","2016-11-21 09:30","2016-11-24 18:00","취소","취소","연속",null,null,null,201609120118]
[152,"대구경북","포항","신월성N/P #1M.Tr 2차 CB (7472)","신월성S/Y 7400, 7472 차단기 정밀점검공사","신월성S/Y 7400, 7472 차단기 정밀점검공사","2016-11-15 09:30","2016-11-19 18:00","2016-11-15 09:30","2016-11-19 18:00","연속",null,null,null,201609130024]
[153,"대구경북","포항","신월성N/P 월성연락#1T/L-#1SA.Tr 1차 CB (7300)","신월성S/Y 7300, 7372 차단기 정밀점검공사","신월성S/Y 7300, 7372 차단기 정밀점검공사","2016-11-25 09:30","2016-11-29 18:00","2016-11-25 09:30","2016-11-29 18:00","연속",null,null,null,201609130034]
[154,"대구경북","포항","신월성N/P #1SA.Tr 1차 CB (7372)","신월성S/Y 7300, 7372 차단기 정밀점검공사","신월성S/Y 7300, 7372 차단기 정밀점검공사","2016-11-25 09:30","2016-11-29 18:00","2016-11-25 09:30","2016-11-29 18:00","연속",null,null,null,201609130036]
[155,"대구경북","포항","신월성N/P 신포항-신월성NP#3-#1M.Tr 2차CB (7400)","신월성S/Y 7400, 7472 차단기 정밀점검공사","신월성S/Y 7400, 7472 차단기 정밀점검공사","2016-11-15 09:30","2016-11-19 18:00","2016-11-15 09:30","2016-11-19 18:00","연속",null,null,null,201609130022]
[156,"대구경북","포항","신포항신월성NP#1 T/L","345kV신포항-신월성NP#1T/L 정밀점검","345kV신포항-신월성NP#1T/L 정밀점검(No.1~75)","2016-11-07 08:00","2016-11-10 18:00","2016-11-07 08:00","2016-11-10 18:00","연속",null,null,null,201609130094]
[157,"대구경북","포항","신포항S/S #1 M.Tr A","신포항S/S #1M.Tr 보호반 대체","신포항S/S #1M.Tr 보호반 대체","2016-11-15 09:00","2016-11-17 18:00","2016-11-15 09:00","2016-11-17 18:00","연속",null,null,null,201609130039]
[158,"대구경북","포항","신포항S/S 345kV #1 BUS","신포항S/S #1BUS 휴전작업","78Bay #1BUS측 분기모선 교체 7771CB, 7751 DS 점검","2016-11-22 09:00","2016-11-22 18:00","2016-11-22 09:00","2016-11-22 18:00","당일",null,null,null,201609130037]
[159,"대구경북","포항","신포항S/S 345kV #2 BUS","신포항S/S #2BUS 휴전작업","78Bay #2BUS측 분기모선 교체 #2BUS PT A, B, C 보통점검","2016-11-23 09:00","2016-11-23 18:00","2016-11-23 09:00","2016-11-23 18:00","당일",null,null,null,201609130038]
[160,"대구경북","포항","월성2N/P 주성#1T/L-#4 M.Tr 2차 CB (7700)","월성S/Y 7700, 7772 차단기 정밀점겅공사","월성S/Y 7700, 7772 차단기 정밀점겅공사","2016-11-01 09:30","2016-11-04 18:00","2016-11-01 09:30","2016-11-04 18:00","연속",null,null,null,201609120575]
[161,"대구경북","포항","월성2N/P #4 M.Tr 2차 CB (7772)","월성S/Y 7700, 7772 차단기 정밀점겅공사","월성S/Y 7700, 7772 차단기 정밀점겅공사","2016-11-01 09:30","2016-11-04 18:00","2016-11-01 09:30","2016-11-04 18:00","연속",null,null,null,201609120576]
[162,"대구경북","포항","울주월성NP#1 T/L","월성S/Y 애자코팅작업","월성S/Y 애자코팅작업","2016-11-02 09:30","2016-11-04 18:00","2016-11-02 09:30","2016-11-04 18:00","연속",null,null,null,201609120578]
[163,"대구경북","포항","울주월성NP#1 T/L","345kV 동울산-월성NP 등 2개T/L 계통변경공사","- 345kV 동울산-월성NP T/L No.39호 이설 - 345kV 동울산-월성NP T/L No.38호 보강 - 345kV 울주-월성NP T/L No.28호 보강, 29호 암교체","2016-11-04 08:00","2016-11-06 18:00","2016-11-04 08:00","2016-11-06 18:00","연속",null,null,null,201609130356]
[164,"대구경북","포항","동울산월성NP#1 T/L","345kV 동울산-월성NP 등 2개T/L 계통변경공사","- 345kV 동울산-월성NP T/L No.39호 이설 - 345kV 동울산-월성NP T/L No.38호 보강 - 345kV 울주-월성NP T/L No.28호 보강, 29호 암교체 - 월성S/Y 보호판넬 교체","2016-11-14 08:00","2016-11-23 18:00","2016-11-14 08:00","2016-11-23 18:00","연속",null,null,null,201609130358]
[165,"대구경북","포항","울주월성NP#1 T/L","345kV 동울산-월성NP 등 2개T/L 계통변경공사","- 345kV 동울산-월성NP T/L No.39호 이설 - 345kV 동울산-월성NP T/L No.38호 보강 - 345kV 울주-월성NP T/L No.28호 보강, 29호 암교체 - 월성S/Y, 울주S/S 보호판넬 교체","2016-11-14 08:00","2016-11-23 18:00","2016-11-14 08:00","2016-11-23 18:00","연속",null,null,null,201609130362]
[166,"대구경북","포항","울주월성NP#2 T/L","345kV 동울산-월성NP 등 2개T/L 계통변경공사","- 345kV 동울산-월성NP T/L No.39호 이설 - 345kV 동울산-월성NP T/L No.38호 보강 - 345kV 울주-월성NP T/L No.28호 보강, 29호 암교체 - 월성S/Y, 울주S/S 보호판넬 교체","2016-11-14 08:00","2016-11-16 18:00","2016-11-14 08:00","2016-11-16 18:00","연속",null,null,null,201609130363]
[167,"대구경북","포항","월성2N/P F2-#4 SS Tr 1차 CB (7800)","월성S/Y 7800, 7872 차단기 정밀점검공사","월성S/Y 7800, 7872 차단기 정밀점검공사","2016-11-10 09:30","2016-11-14 18:00","2016-11-10 09:30","2016-11-14 18:00","연속",null,null,null,201609130018]
[168,"대구경북","포항","월성2N/P #4 SS Tr 1차 CB (7872)","월성S/Y 7800, 7872 차단기 정밀점검공사","월성S/Y 7800, 7872 차단기 정밀점검공사","2016-11-10 09:30","2016-11-14 18:00","2016-11-10 09:30","2016-11-14 18:00","연속",null,null,null,201609130020]
[169,"대구경북","포항","동울산월성NP#2 T/L","345kV 동울산-월성NP 등 2개T/L 계통변경공사","- 345kV 동울산-월성NP T/L No.39호 이설 - 345kV 동울산-월성NP T/L No.38호 보강 - 345kV 울주-월성NP T/L No.28호 보강, 29호 암교체","2016-11-04 08:00","2016-11-13 18:00","2016-11-04 08:00","2016-11-13 18:00","연속",null,null,null,201609130354]
[170,"대구경북","포항","울주월성NP#2 T/L","345kV 동울산-월성NP 등 2개T/L 계통변경공사","- 345kV 동울산-월성NP T/L No.39호 이설 - 345kV 동울산-월성NP T/L No.38호 보강 - 345kV 울주-월성NP T/L No.28호 보강, 29호 암교체","2016-11-04 08:00","2016-11-13 18:00","2016-11-04 08:00","2016-11-13 18:00","연속",null,null,null,201609130355]
[171,"대구경북","포항","신포항신월성NP#3 T/L","신포항-신월성#3T/L 애자코팅작업","신포항-신월성#3T/L 애자코팅작업","2016-11-15 09:30","2016-11-16 18:00","2016-11-15 09:30","2016-11-16 18:00","연속",null,null,null,201609220087]
[172,"부산울산","동부산","신양산S/S #1 M.Tr A","신양산S/S 23kV #1-3Sh.R 대체","신양산S/S 23kV #1-3Sh.R 대체관련 시험가압(345kV #1M.Tr 사용)","2016-11-24 18:00","2016-11-26 18:00","2016-11-24 18:00","2016-11-26 18:00","연속",null,null,null,201609080295]
[173,"부산울산","북부산","북부산S/S #4 M.Tr A","345kV 북부산S/S 차단기용량대체 공사","345kV GIS 기초보강 PHC파일 작업 안전이격확보","2016-11-21 09:00","2016-11-27 18:00","2016-11-21 09:00","2016-11-27 18:00","연속",null,null,null,201609190132]
[174,"부산울산","북부산","신김해북부산#2 T/L","16년 가공송전설비 위탁업체 공사","ㅇ 초기점검 - 구간 : No.16~19호(4기)","2016-11-04 08:00","2016-11-04 18:00","2016-11-04 08:00","2016-11-04 18:00","당일",null,null,null,201609080280]
[175,"부산울산","북부산","북부산S/S 345kV #75 BUS","2016년 북부산변전협력회사 총액공사","#75BUS CVT 보통점검","2016-11-01 09:30","2016-11-01 18:00","2016-11-01 09:30","2016-11-01 18:00","당일",null,null,null,201609090346]
[176,"부산울산","서부산","서부산북부산#1 T/L","서부산S/S 345kV #1Sh.R 대체공사(시험가압)","서부산S/S 345kV #1Sh.R 대체공사(시험가압-48H)","2016-11-18 18:00","2016-11-20 18:00","취소","취소","연속",null,null,null,201609090316]
[177,"부산울산","울산","동울산S/S #3 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","동울산S/S #3M.Tr 1, 2차 GIS 하자점검","2016-11-04 09:00","2016-11-04 18:00","2016-11-04 09:00","2016-11-04 18:00","당일",null,null,null,201609080362]
[178,"부산울산","울산","동울산S/S #2 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","동울산S/S #2M.Tr 1, 2차 GIS 하자점검","2016-11-03 09:00","2016-11-03 18:00","2016-11-03 09:00","2016-11-03 18:00","당일",null,null,null,201609080361]
[179,"부산울산","울산","동울산신울산#1 T/L","345kV 동울산-신울산#1T/L 송전선로용피뢰기 설치공사","ㅇ 피뢰기 설치 - 구간 : No.70~140(71기) ㅇ 병행휴전 : 신울산S/S 7800 GIS 하자점검","2016-11-21 07:00","2016-11-29 18:00","2016-11-21 07:00","2016-11-29 18:00","연속",null,null,null,201609080101,"○"]
[180,"부산울산","울산","동울산신울산#2 T/L","345kV 동울산-신울산#2T/L 송전선로 정밀점검","정밀점검 : No.70~140(71기)","2016-11-30 09:00","2016-12-04 18:00","2016-11-30 09:00","2016-12-04 18:00","연속",null,null,null,201609090040]
[181,"부산울산","울산","울산C/C #3 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","울산C/C 345kV #3M.Tr 2차 GIS 하자점검","2016-11-12 09:00","2016-11-12 18:00","2016-11-12 09:00","2016-11-12 18:00","당일",null,null,null,201609190187]
[182,"부산울산","울산","울주신경산#1 T/L","2016년 362kV 개폐장치 정밀점검 공사","울주S/S 7971 CB 시험가압","2016-11-23 17:00","2016-11-23 18:00","2016-11-23 17:00","2016-11-23 18:00","당일",null,null,null,201609210135]
[183,"부산울산","울산","울주S/S 345kV #1 BUS","2016년 362kV 개폐장치 정밀점검 공사","울주S/S 7971 CB 시험가압","2016-11-23 17:00","2016-11-23 18:00","2016-11-23 17:00","2016-11-23 18:00","당일",null,null,null,201609210134]
[184,"부산울산","울산","울주월성NP#1 T/L","345kV 북부산-울산TP 등 4개 T/L 전선교체공사","345kV 울주-월성NP#1 T/L 전선접속개소 전선교체공사 - 공사구간 : No.4~6 - 공사물량 : No.4~5(1가닥), No.5~6(8가닥)","2016-11-13 08:00","2016-11-16 18:00","2016-11-05 08:00","2016-11-08 18:00","연속",null,null,null,201609080095]
[185,"부산울산","직할","신대연S/S #2M.Tr A","345kV 신대연S/S 변압기 소음저감설비 설치공사","345kV M.Tr 소음저감설비 설치 x 1식","2016-11-10 09:00","2016-11-16 18:00","2016-11-10 09:00","2016-11-16 18:00","연속",null,null,null,201609080058]
[186,"부산울산","직할","신대연S/S #1M.Tr A","345kV 신대연S/S 변압기 소음저감설비 설치공사","345kV 변압기 소음저감설비 설치작업개소 안전이격거리 확보","2016-11-01 08:00","2016-11-09 18:00","2016-11-01 08:00","2016-11-09 18:00","연속",null,null,null,201609260126]
[187,"경남","직할","신김해S/S #3 M.Tr A","신김해S/S #3M.Tr 2차 CB 보통점검","신김해S/S #3M.Tr 2차 CB 보통점검, 2차 부싱 절연유 가스분석","2016-11-07 09:30","2016-11-07 17:30","2016-11-07 09:30","2016-11-07 17:30","당일",null,null,null,201609050195]
[188,"경남","직할","신김해S/S #4 M.Tr A","신김해S/S #4M.Tr 2,3차 CB 보통점검","신김해S/S #4M.Tr 2,3차 CB 보통점검, 1차 LA 교체, 2차 LA 초기점검, 3차 PT 보통점검, 실리콘 러버히터 설치, 2차 부싱 절연유 가스분석, 보호계전기 교체","2016-11-03 09:30","2016-11-04 17:30","2016-11-03 09:30","2016-11-04 17:30","연속",null,null,null,201609050197]
[189,"경남","진주","의령S/S #1 M.Tr A","의령S/S #1 M.Tr 보호PNL 보호계전기 리콜","YPP제 345kV 변압기 보호계전기(T60) 오동작 관련 제작사 리콜","2016-11-15 09:30","2016-11-15 18:30","2016-11-15 09:30","2016-11-15 18:30","당일",null,null,null,201609190019]
[190,"경남","진주","의령S/S #2 M.Tr A","의령S/S #2M.Tr PNL 대체공사","의령S/S #2M.Tr PNL 대체공사(11/21~11/25) - 병행작업 : #2S.Tr VCB(4284) 초기점검 - #2M.Tr 3차 PT(A,B,C) 보통점검","2016-11-21 09:30","2016-11-25 18:30","2016-11-21 09:30","2016-11-25 18:30","연속",null,null,null,201609020027]
[191,"경남","함안","신마산S/S #3 M.Tr A","신마산 345kV #3M.Tr 냉각팬불량보수 및 PT 보통점검공사","신마산 345kV #3M.Tr B상 냉각팬불량보수 1,3차측 PT 보통점검","2016-11-07 09:30","2016-11-07 17:30","2016-11-07 09:30","2016-11-07 17:30","당일",null,null,"신뢰도개선",201609070174]
[192,"경남","함안","신마산S/S #1 M.Tr A","신마산 345kV #1M.Tr 3차측 PT 보통점검공사","신마산 345kV #1M.Tr 3차측 PT 보통점검","2016-11-01 09:30","2016-11-03 18:30","2016-11-01 09:30","2016-11-03 18:30","연속",null,null,"신뢰도개선",201609070176]
[193,"경남","함안","신마산S/S #2 M.Tr A","신마산 345kV 보호계전기 오동작관련 보호PNL 대체공사","신마산 345kV 보호계전기(67) 오동작관련 보호PNL 대체 - 6244GCB 보통점검 및 거리계전기(21) CT비 변경 - 7771, 7772 GCB 러버히터 설치","2016-11-04 08:30","2016-11-06 18:30","2016-11-04 08:30","2016-11-06 18:30","연속",null,null,"신뢰도개선",201609280042]
["추가1","광주전남",null,"한빛1N/P 345kV #2BUS","모선보호반 정기점검","모선보호반 정지점검","2016-11-16 09:00","2016-11-16 18:00","2016-11-16 09:00","2016-11-16 18:00","연속"]
["추가2","경남",null,"신고성S/S #2M.Tr","모선보호반 정기점검","중성선 B상 단자과열조치","2016-11-14 09:30","2016-11-15 18:30","2016-11-14 09:30","2016-11-15 18:30","연속"]

{"sheet":"154송부","index":2,"n_rows":460,"n_cols":16,"rows_kept":460,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2016년도 11월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","원남미아#1 T/L","2015-16 성동전력지사 지중송전설비 위탁정비공사","원남미아#1T/L OF케이블 절연유 시료채취","2016-11-15 10:00","2016-11-15 16:00","2016-11-15T10:00:00","2016-11-15T16:00:00","당일",null,null,null,201609130170,"-"]
[2,"서울","성동","쌍문미아#2 T/L","16년 성동 변전협력회사 총액공사 (미아S/S 쌍문미아#2T/L)","170kV GIS 초기점검 (미아S/S 쌍문미아#2T/L)","2016-11-10 10:00","2016-11-10 17:00","2016-11-10T10:00:00","2016-11-10T17:00:00","당일",null,null,null,201609120586,"-"]
[3,"서울","성동","쌍문미아#1 T/L","16년 성동 변전협력회사 총액공사 (미아S/S 쌍문미아#1T/L)","170kV GIS 초기점검 (미아S/S 쌍문미아#1T/L)","2016-11-09 10:00","2016-11-09 17:00","2016-11-09T10:00:00","2016-11-09T17:00:00","당일",null,null,null,201609120585,"-"]
[4,"서울","성동","도봉방학#1 T/L","방학S/S 154kV 도봉방학#1T/L ABB제 계전기 성능개선","방학S/S 154kV 도봉방학#1T/L ABB제 계전기 성능개선","2016-11-16 10:30","2016-11-16 18:00","2016-11-16T10:30:00","2016-11-16T18:00:00","당일",null,null,null,201609190053,"○"]
[5,"서울","성동","도봉방학#2 T/L","방학S/S 154kV 도봉방학#2T/L ABB제 계전기 성능개선","방학S/S 154kV 도봉방학#2T/L ABB제 계전기 성능개선","2016-11-17 10:30","2016-11-17 18:00","2016-11-17T10:30:00","2016-11-17T18:00:00","당일",null,null,null,201609190054,"-"]
[6,"서울","성동","화양성수 T/L","화양 및 세종로S/S 인출선로 선종교체공사","1. 사 업 명 : 화양 및 세종로S/S 인출선로 선종교체공사 2. 사업목적 : 지하복합변전소 화재 및 대형 재난사고 예방 3. 사업개요 ○ 사업구간 : 화양S/S ∼ 인출전력구, 세종로S/S ∼ 인출전력구 ○ 사업내용 : 154kV 6회선 0.6km 선종교체","2016-11-01 10:00","2016-11-30 17:00","2016-11-01T10:00:00","2016-11-30T17:00:00","연속",null,null,"신뢰도개선",201608310169,"-"]
[7,"서울","성동","휘경종암#2 T/L","16년 성동 변전협력회사 총액공사 (휘경S/S 휘경종암#2T/L)","170kV GIS 초기점검 (휘경S/S 휘경종암#2T/L)","2016-11-08 10:00","2016-11-08 17:00","2016-11-08T10:00:00","2016-11-08T17:00:00","당일",null,null,null,201609120588,"-"]
[8,"서울","성동","휘경종암#1 T/L","16년 성동 변전협력회사 총액공사 (휘경S/S 휘경종암#1T/L)","170kV GIS 초기점검 (휘경S/S 휘경종암#1T/L)","2016-11-07 10:00","2016-11-07 17:00","2016-11-07T10:00:00","2016-11-07T17:00:00","당일",null,null,null,201609120587,"-"]
[9,"서울","중부","수색상암#1 T/L","2016년 중부전력지사 170kV GIS 정밀점검","상암S/S 수색상암#1T/L GIS(657) 정밀점검","2016-11-09 08:00","2016-11-12 18:00","2016-11-09T08:00:00","2016-11-12T18:00:00","연속",null,null,null,201609080070,"-"]
[10,"서울","중부","수색상암#2 T/L","2016년 중부전력지사 170kV GIS 정밀점검","상암S/S 수색상암#2T/L GIS(667) 정밀점검","2016-11-02 08:00","2016-11-05 18:00","2016-11-02T08:00:00","2016-11-05T18:00:00","연속",null,null,null,201609080071,"-"]
[11,"서울","중부","수색S/S 154kV #1 BUS TIE CB","2016~2017년 중부전력지사 변전협력업체 총액공사","수색S/S 154kV 모선보호반 교체 및 GCB (6100) 보통점검","2016-11-01 10:00","2016-11-04 18:00","2016-11-01T10:00:00","2016-11-04T18:00:00","연속",null,null,null,201609080083,"-"]
[12,"서울","중부","수색S/S 154kV #1 BUS","2016~2017년 중부전력지사 변전협력업체 총액공사","수색S/S 154kV LS 보통점검(수색중부#1,원흥수색#1T/L)","2016-11-19 08:00","2016-11-19 14:00","2016-11-19T08:00:00","2016-11-19T14:00:00","당일",null,null,null,201609130309,"-"]
[13,"서울","중부","원흥수색#1 T/L","2016~2017년 중부전력지사 변전협력업체 총액공사","수색S/S 154kV 원흥수색#1T/L GCB,LS 보통점검 (687)","2016-11-19 08:00","2016-11-19 18:00","2016-11-19T08:00:00","2016-11-19T18:00:00","당일",null,null,null,201608100251,"-"]
[14,"서울","중부","수색S/S 154kV #2 BUS","2016~2017년 중부전력지사 변전협력업체 총액공사","수색S/S 154kV LS 보통점검(수색중부#1,원흥수색#1T/L)","2016-11-19 14:00","2016-11-19 18:00","2016-11-19T14:00:00","2016-11-19T18:00:00","당일",null,null,null,201609130310,"-"]
[15,"서울","중부","수색S/S 154kV #2 BUS","2016~2017년 중부전력지사 변전협력업체 총액공사","수색S/S 154kV LS 보통점검(수색상암#2T/L,6100 BUS-TIE)","2016-11-05 14:00","2016-11-05 18:00","2016-11-05T14:00:00","2016-11-05T18:00:00","당일",null,null,null,201609080079,"-"]
[16,"서울","중부","수색S/S 154kV #1 BUS","2016~2017년 중부전력지사 변전협력업체 총액공사","수색S/S 154kV LS 보통점검(수색상암#2T/L,6100 BUS-TIE)","2016-11-05 08:00","2016-11-05 14:00","2016-11-05T08:00:00","2016-11-05T14:00:00","당일",null,null,null,201609080077,"-"]
[17,"서울","중부","수색S/S 154kV #2 BUS","2016~2017년 중부전력지사 변전협력업체 총액공사","수색S/S 154kV LS 보통점검(수색상암#1T/L,수색은평#2T/L)","2016-11-12 14:00","2016-11-12 18:00","2016-11-12T14:00:00","2016-11-12T18:00:00","당일",null,null,null,201609080081,"-"]
[18,"서울","중부","수색S/S 154kV #1 BUS","2016~2017년 중부전력지사 변전협력업체 총액공사","수색S/S 154kV LS 보통점검(수색상암#1T/L,수색은평#2T/L)","2016-11-12 08:00","2016-11-12 14:00","2016-11-12T08:00:00","2016-11-12T14:00:00","당일",null,null,null,201609080080,"-"]
[19,"서울","중부","중부S/S 154kV #60 BUS","2016년 중부전력지사 170kV GIS 정밀점검 공사","중부S/S 중부용산#1T/L GIS(647) #1DS 정밀점검","2016-11-28 08:00","2016-11-29 14:00","2016-11-28T08:00:00","2016-11-29T14:00:00","연속",null,null,null,201607140159,"-"]
[20,"서울","중부","중부S/S 154kV #61 BUS","2016년 중부전력지사 170kV GIS 정밀점검 공사","중부S/S 중부마포T/L GIS(6B7) #1DS 정밀점검","2016-11-21 08:00","2016-11-22 14:00","2016-11-21T08:00:00","2016-11-22T14:00:00","연속",null,null,null,201607140160,"-"]
[21,"서울","중부","중부S/S 154kV #65 BUS","2016년 중부전력지사 170kV GIS 정밀점검 공사","중부S/S 중부용산#1T/L GIS(647) #2DS 정밀점검","2016-11-29 14:00","2016-11-30 18:00","2016-11-29T14:00:00","2016-11-30T18:00:00","연속",null,null,null,201607140156,"-"]
[22,"서울","중부","중부S/S 154kV #66 BUS","2016년 중부전력지사 170kV GIS 정밀점검 공사","중부S/S 중부마포T/L GIS(6B7) #2DS 정밀점검 중부S/S 중부아현T/L GIS(6F7) #2DS 정밀점검","2016-11-22 14:00","2016-11-24 14:00","2016-11-22T14:00:00","2016-11-24T14:00:00","연속",null,null,null,201607140152,"-"]
[23,"서울","중부","중부S/S 154kV #61 BUS","2016년 중부전력지사 170kV GIS 정밀점검 공사","중부S/S 중부아현T/L GIS(6F7) #1DS 정밀점검","2016-11-24 14:00","2016-11-25 18:00","2016-11-24T14:00:00","2016-11-25T18:00:00","연속",null,null,null,201607140161,"-"]
[24,"서울","중부","중부S/S 154kV #60 BUS","2016년 중부전력지사 170kV GIS 정밀점검 공사","중부S/S 수색중부#2T/L GIS(667) #1DS 정밀점검","2016-11-14 08:00","2016-11-15 14:00","2016-11-14T08:00:00","2016-11-15T14:00:00","연속",null,null,null,201607140150,"-"]
[25,"서울","중부","중부용산#1 T/L","2016년 중부전력지사 170kV GIS 정밀점검 공사","중부S/S 중부용산#1T/L(647) GIS 정밀점검","2016-11-28 08:00","2016-11-30 18:00","2016-11-28T08:00:00","2016-11-30T18:00:00","연속",null,null,null,201607140146,"-"]
[26,"서울","중부","중부S/S 154kV #65 BUS","2016년 중부전력지사 170kV GIS 정밀점검 공사","중부S/S 수색중부#1T/L GIS(657) #2DS 정밀점검 중부S/S 수색중부#2T/L GIS(667) #2DS 정밀점검","2016-11-15 14:00","2016-11-17 14:00","2016-11-15T14:00:00","2016-11-17T14:00:00","연속",null,null,null,201607140186,"-"]
[27,"서울","중부","중부S/S 154kV #60 BUS","2016년 중부전력지사 170kV GIS 정밀점검 공사","중부S/S 수색중부#1T/L GIS(657) #1DS 정밀점검","2016-11-17 14:00","2016-11-18 18:00","2016-11-17T14:00:00","2016-11-18T18:00:00","연속",null,null,null,201607140151,"-"]
[28,"서울","직할","서대문세종로 T/L","16년 직할 무동작차단기 조작시험","서대문,세종로S/S 서대문세종로 T/L 차단기 조작시험","2016-11-11 10:00","2016-11-11 14:00","2016-11-11T10:00:00","2016-11-11T14:00:00","당일",null,null,null,201609190236,"-"]
[29,"서울","직할","마장신당 T/L","신당S/S 170kV 장기사용 GIS 대체공사(4차)","신당S/S 170kV 장기사용 GIS 대체공사(4차) - #1M.Tr 1차, 마장신당T/L 대체","2016-11-25 09:30","2016-12-22 18:00","2016-11-25T09:30:00","2016-12-22T18:00:00","연속",null,null,null,201609190001,"-"]
[30,"서울","직할","운니원남#1 T/L","16-17 직할 변전협력 총액공사","실리콘러버 설치","2016-11-21 10:00","2016-11-21 13:00","2016-11-21T10:00:00","2016-11-21T13:00:00","당일",null,null,null,201609190240,"-"]
[31,"서울","직할","운니원남#2 T/L","16-17 직할 변전협력 총액공사","실리콘러버 설치","2016-11-21 13:00","2016-11-21 16:00","2016-11-21T13:00:00","2016-11-21T16:00:00","당일",null,null,null,201609190241,"-"]
[32,"남서울","강남","신양재역삼#2 T/L","송전선로 미동작차단기 시험 - 직영","송전선로 미동작차단기 시험 - 직영 -신양재-역삼#2T/L","2016-11-09 10:00","2016-11-09 18:00","2016-11-09T10:00:00","2016-11-09T18:00:00","당일",null,null,null,201609220095,"-"]
[33,"남서울","강남","신성남염곡#2 T/L","154KV 신성남-염곡T/L 이설공사(양재대로)","강남순환도시고속도로 건설에 따른 지장 송전선로 이설 154kV 신성남-염곡T/L J/B#17~18","2016-11-01 10:00","2016-11-25 10:00","2016-11-01T10:00:00","2016-11-25T10:00:00","연속",null,null,null,201607080299,"-"]
[34,"남서울","동서울","가락수서#2 T/L","154kV 가락-수서T/L 가락S/S 인출구간 선종교체공사","가락S/S 인출구간 OF케이블을 XLPE케이블로 교체","2016-11-01 09:00","2016-11-30 18:00","2016-11-01T09:00:00","2016-11-30T18:00:00","연속",null,null,null,201609230158,"-"]
[35,"남서울","동서울","동서울S/S 154kV #1 BUS TIE CB","새롬프로텍제 모선보호반 성능 개선","50BF 관련 로직 변경","2016-11-01 09:00","2016-11-01 12:00","2016-11-01T09:00:00","2016-11-01T12:00:00","당일",null,null,null,201609120219,"-"]
[36,"남서울","동서울","동서울S/S 66-67-0 SEC CB","새롬프로텍제 모선보호반 성능 개선","50BF 관련 로직 변경","2016-11-01 13:00","2016-11-01 19:00","2016-11-01T13:00:00","2016-11-01T19:00:00","당일",null,null,null,201609120228,"-"]
[37,"남서울","동서울","동서울S/S 65-66-0 SEC CB","새롬프로텍제 모선보호반 성능 개선","50BF 관련 로직 변경","2016-11-01 09:00","2016-11-01 16:00","2016-11-01T09:00:00","2016-11-01T16:00:00","당일",null,null,null,201609120225,"-"]
[38,"남서울","동서울","동서울S/S 61-62-0 SEC CB","새롬프로텍제 모선보호반 성능 개선","50BF 관련 로직 변경","2016-11-01 13:00","2016-11-01 19:00","2016-11-01T13:00:00","2016-11-01T19:00:00","당일",null,null,null,201609120227,"-"]
[39,"남서울","동서울","동서울S/S 60-61-0 SEC CB","새롬프로텍제 모선보호반 성능 개선","50BF 관련 로직 변경","2016-11-01 09:00","2016-11-01 16:00","2016-11-01T09:00:00","2016-11-01T16:00:00","당일",null,null,null,201609120224,"-"]
[40,"남서울","동서울","동서울S/S 154kV #67 BUS","170kV GCB 교체공사","170kV GCB 교체공사 - 동서울S/S #3M.Tr, 동서울-송파#1T/L GCB 교체공사","2016-11-28 09:00","2016-12-02 18:00","취소","취소","연속",null,null,"신뢰도개선",201609220075,"-"]
[41,"남서울","동서울","동서울송파#1 T/L","170kV GCB 교체공사","- 동서울S/S 동서울-송파#1T/L GCB 교체공사 - ILC반 교체공사","2016-11-28 09:00","2016-12-02 18:00","2016-11-28T09:00:00","2016-12-02T18:00:00","연속",null,null,null,201609220078,"-"]
[42,"남서울","동서울","동서울S/S 154kV #67 BUS","170kV GCB 교체공사","170kV GCB 교체공사 - 동서울S/S #4M.Tr GCB 교체공사","2016-11-21 09:00","2016-11-25 18:00","취소","취소","연속",null,null,"신뢰도개선",201609220073,"-"]
[43,"남서울","동서울","동서울S/S 154kV #2 BUS TIE CB","새롬프로텍제 모선보호반 성능 개선","50BF 관련 로직 변경","2016-11-01 16:00","2016-11-01 19:00","2016-11-01T16:00:00","2016-11-01T19:00:00","당일",null,null,null,201609120229,"-"]
[44,"남서울","동서울","동서울가락#1 T/L","170kV ILC반 교체공사","동서울-가락#1T/L 170kV ILC반 교체공사","2016-11-07 09:00","2016-11-09 18:00","2016-11-07T09:00:00","2016-11-09T18:00:00","연속",null,null,null,201608180188,"-"]
[45,"남서울","동서울","동서울가락#2 T/L","170kV ILC반 교체공사","동서울-가락#2T/L 170kV ILC반 교체공사","2016-11-21 09:00","2016-11-25 18:00","2016-11-21T09:00:00","2016-11-25T18:00:00","연속",null,null,null,201609220076,"-"]
[46,"남서울","동서울","잠실삼성#1 T/L","삼성S/S OF 송전선로 이설 및 선종교체공사","삼성#2S/S 건설로 인한 송전선로 이설 및 OF 송전선로의 선종교체 공사","2016-11-04 10:00","2016-11-30 18:00","2016-11-04T10:00:00","2016-11-30T18:00:00","연속",null,null,null,201609220005,"-"]
[47,"남서울","영서","상암등촌#1 T/L","2015-2016년 지중송전설비 위탁정비공사","지중송전 OF케이블 절연유 채유","2016-11-01 09:30","2016-11-01 14:00","2016-11-01T09:30:00","2016-11-01T14:00:00","당일",null,null,null,201609090250,"-"]
[48,"남서울","영서","상암등촌#2 T/L","2015-2016년 지중송전설비 위탁정비공사","지중송전 OF케이블 절연유 채유","2016-11-01 14:00","2016-11-01 18:00","2016-11-01T14:00:00","2016-11-01T18:00:00","당일",null,null,null,201609090251,"-"]
[49,"남서울","직할","사당봉천#2 T/L","봉천,노들변전소 OF케이블 선종교체공사","케이블철거 및 설치 : OF케이블에서 XLPE로 교체(260m X 3상) 이종 및 종단 접속 : 2개소 X 3상 PT 이설 및 기타 부대작업","2016-11-03 09:00","2016-11-30 18:00","2016-11-03T09:00:00","2016-11-30T18:00:00","연속",null,null,null,201609190047,"-"]
[50,"남서울","직할","봉천신길#2 T/L","변전총액공사(신길S/S 봉천-신길#2T/L GIS 초기)","변전총액공사(신길S/S 봉천-신길#2T/L GIS 초기)","2016-11-03 09:30","2016-11-03 18:00","2016-11-03T09:30:00","2016-11-03T18:00:00","연속",null,null,null,201608170111,"-"]
[51,"남서울","직할","대방신길#2 T/L","OF케이블 절연유 체유","절연유 체유 : 8개소","2016-11-02 10:00","2016-11-02 17:00","2016-11-02T10:00:00","2016-11-02T17:00:00","당일",null,null,null,201609200079,"-"]
[52,"남서울","직할","대방신길#1 T/L","OF케이블 절연유 체유","절연유 체유 : 10개소","2016-11-01 10:00","2016-11-01 17:00","2016-11-01T10:00:00","2016-11-01T17:00:00","당일",null,null,null,201609200078,"-"]
[53,"인천","시흥","남동S/S 154kV #2 BUS","남동S/S 신시흥남동#1 T/L GIS 정밀점검공사","남동S/S 신시흥남동#1 T/L GIS 정밀점검공사","2016-11-28 08:00","2016-11-29 14:00","2016-11-28T08:00:00","2016-11-29T14:00:00","연속",null,null,null,201609130059,"-"]
[54,"인천","시흥","신시흥남동#1 T/L","남동S/S 신시흥남동#1 T/L GIS 정밀점검공사","남동S/S 신시흥남동#1 T/L GIS 정밀점검공사","2016-11-28 08:00","2016-11-30 18:00","2016-11-28T08:00:00","2016-11-30T18:00:00","연속",null,null,null,201609130057,"-"]
[55,"인천","시흥","남동S/S 154kV #1 BUS","남동S/S 신시흥남동#1 T/L GIS 정밀점검공사","남동S/S 신시흥남동#1 T/L GIS 정밀점검공사","2016-11-29 14:00","2016-11-30 18:00","2016-11-29T14:00:00","2016-11-30T18:00:00","연속",null,null,null,201609130061,"-"]
[56,"인천","시흥","남동관교#1 T/L","2015-2016년 지중송전설비 위탁정비공사","지중송전OF선로 절연유 시료채취","2016-11-03 09:00","2016-11-03 18:00","2016-11-03T09:00:00","2016-11-03T18:00:00","당일",null,null,null,201609090085,"-"]
[57,"인천","시흥","남동S/S 154kV #1 BUS","남동S/S 신시흥남동#2 T/L GIS 정밀점검공사","신시흥. 남동S/S 신시흥남동#2 T/L GIS 정밀점검공사","2016-11-25 14:00","2016-11-26 18:00","2016-11-25T14:00:00","2016-11-26T18:00:00","연속",null,null,null,201609130056,"-"]
[58,"인천","시흥","남동S/S 신시흥남동#2T/L GIS","신시흥. 남동S/S 신시흥남동#2 T/L GIS 정밀점검공사","신시흥. 남동S/S 신시흥남동#2 T/L GIS 정밀점검공사","2016-11-21 08:00","2016-11-26 18:00","2016-11-21T08:00:00","2016-11-26T18:00:00","연속",null,null,null,201609130054,"-"]
[59,"인천","시흥","남동S/S 154kV #2 BUS","남동S/S 신시흥남동#2 T/L GIS 정밀점검공사","남동S/S 신시흥남동#2 T/L GIS 정밀점검공사","2016-11-24 08:00","2016-11-25 14:00","2016-11-24T08:00:00","2016-11-25T14:00:00","연속",null,null,null,201609130055,"-"]
[60,"인천","시흥","신시흥북시화#1 T/L","154kV 시화T/L 피뢰기설치 및 북시화T/L 아킹혼 철거공사","154kV 시화T/L 피뢰기설치(25기) 및 북시화T/L 아킹혼철거(7기)","2016-11-13 07:00","2016-11-13 18:00","2016-11-13T07:00:00","2016-11-13T18:00:00","당일",null,null,null,201608290163,"-"]
[61,"인천","시흥","서안양소래 T/L","154kV 서안양소래T/L 정밀점검","154kV 서안양소래T/L 정밀점검","2016-11-02 08:00","2016-11-04 18:00","2016-11-02T08:00:00","2016-11-04T18:00:00","매일",null,null,null,201609130102,"-"]
[62,"인천","시흥","신시흥시화#1 T/L","154kV 시화T/L 피뢰기설치공사","154kV 시화T/L 피뢰기설치(25기)","2016-11-06 07:00","2016-11-06 18:00","2016-11-06T07:00:00","2016-11-06T18:00:00","매일",null,null,null,201608290167,"-"]
[63,"인천","시흥","신시흥시화#1 T/L","154kV 시화T/L 피뢰기설치공사","154kV 시화T/L 피뢰기설치(25기)","2016-11-13 07:00","2016-11-13 18:00","2016-11-13T07:00:00","2016-11-13T18:00:00","당일",null,null,null,201609220021,"-"]
[64,"인천","시흥","신시흥#1S/S 154kV #66 BUS","신시흥/S/S 신시흥남동#2T/L GIS 정밀점검","신시흥/S/S 신시흥남동#2T/L GIS 정밀점검","2016-11-21 08:00","2016-11-22 14:00","2016-11-21T08:00:00","2016-11-22T14:00:00","연속",null,null,null,201609130052,"-"]
[65,"인천","시흥","신시흥#1S/S 154kV #61 BUS","신시흥/S/S 신시흥남동#2T/L GIS 정밀점검","신시흥/S/S 신시흥남동#2T/L GIS 정밀점검","2016-11-22 14:00","2016-11-23 18:00","2016-11-22T14:00:00","2016-11-23T18:00:00","연속",null,null,null,201609130053,"-"]
[66,"인천","시흥","연수S/S 154kV #1 BUS","연수S/S 170kV 장기사용 GIS 대체공사","- 154kV 학익연수#2T/L GIS 1CCT 대체","2016-11-04 10:00","2016-11-04 18:00","2016-11-04T10:00:00","2016-11-04T18:00:00","연속",null,null,null,201608090323,"-"]
[67,"인천","인천","송현포스코CC#1 T/L","154kV 송현-포스코 #1T/L C/H 및 피뢰기 점검","C/H 및 피뢰기 점검","2016-11-01 09:00","2016-11-01 18:00","2016-11-01T09:00:00","2016-11-01T18:00:00","당일",null,null,null,201609090077,"-"]
[68,"인천","인천","신현포스코CC#1 T/L","154kV 신현포스코CCT/L 지장송전선로 이설 공사","한진중공업에서 시행하는 인천북항 배후부지 항만구역 조성공사에 지장되는 154kV 신현-포스코CC T/L 지장이설 필요 - 이설구간 : 154kV 신현-포스코CC #1T/L M/H #4~M/H #5 (약313m)","2016-11-05 09:00","2016-11-20 18:00","2016-11-05T09:00:00","2016-11-20T18:00:00","연속",null,null,null,201609190121,"-"]
[69,"인천","인천","신현S/S 154kV #1 BUS","154kV 신현-포스코CC #1T/L M/H#4~#5 지장이설공사","154kV 신현-포스코CC #1T/L 지장이설관련 상체크시험","2016-11-19 13:00","2016-11-19 18:00","2016-11-19T13:00:00","2016-11-19T18:00:00","당일",null,null,null,201609230097,"-"]
[70,"인천","직할","계양북인천 T/L","154kV 계양-북인천T/L 스페이서 간격조정 공사","154kV 계양-북인천T/L 스페이서 간격조정 공사 시행","2016-11-01 08:00","2016-11-04 18:00","2016-11-01T08:00:00","2016-11-04T18:00:00","매일",null,null,null,201609120497,"-"]
[71,"인천","직할","임학계양#2 T/L","154kV 임학-계양#2 T/L 스페이서 간격조정 공사","154kV 임학-계양#2 T/L 스페이서 간격조정 공사 시행","2016-11-01 08:00","2016-11-04 18:00","2016-11-01T08:00:00","2016-11-04T18:00:00","매일",null,null,null,201609120496,"-"]
[72,"인천","직할","계양S/S 154kV #1 BUS","계양S/S 계양원창T/L GIS 정밀점검","계양S/S 계양원창T/L GIS 정밀점검","2016-11-21 08:00","2016-11-22 14:00","2016-11-21T08:00:00","2016-11-22T14:00:00","연속",null,null,null,201609190176,"-"]
[73,"인천","직할","계양S/S 154kV #2 BUS","계양S/S 계양원창T/L GIS 정밀점검","계양S/S 계양원창T/L GIS 정밀점검","2016-11-22 14:00","2016-11-23 18:00","2016-11-22T14:00:00","2016-11-23T18:00:00","연속",null,null,null,201609190178,"-"]
[74,"인천","직할","계양원창 T/L","계양S/S 계양원창T/L GIS 정밀점검","계양S/S 계양원창T/L GIS 정밀점검","2016-11-21 08:00","2016-11-23 18:00","2016-11-21T08:00:00","2016-11-23T18:00:00","연속",null,null,null,201609190144,"-"]
[75,"인천","직할","신가좌부개#2 T/L","154kV 신가좌-부개#2/L 보호반 대체","154kV 신가좌-부개#2/L 보호반 대체","2016-11-21 09:30","2016-11-24 18:00","2016-11-21T09:30:00","2016-11-24T18:00:00","연속",null,null,null,201609190155,"-"]
[76,"인천","직할","신가좌부개#1 T/L","154kV 신가좌-부개#1T/L 보호반 대체","154kV 신가좌-부개#1T/L 보호반 대체","2016-11-28 09:30","2016-12-02 18:00","2016-11-28T09:30:00","2016-12-02T18:00:00","연속",null,null,null,201609190154,"-"]
[77,"인천","직할","부개원미#1 T/L","부개S/S 154kV 부개-원미#1T/L GIS 정밀점검","부개S/S 154kV 부개-원미#1T/L GIS 정밀점검","2016-11-14 08:00","2016-11-16 18:00","2016-11-14T08:00:00","2016-11-16T18:00:00","연속",null,null,null,201609190131,"-"]
[78,"인천","직할","부개S/S 154kV #2 BUS","부개S/S 154kV 부개-원미#1T/L GIS 정밀점검","부개S/S 154kV 부개-원미#1T/L GIS 정밀점검","2016-11-15 14:00","2016-11-16 18:00","2016-11-15T14:00:00","2016-11-16T18:00:00","연속",null,null,null,201609190168,"-"]
[79,"인천","직할","부개S/S 154kV #1 BUS","부개S/S 154kV 부개-원미#2/L GIS 정밀점검","부개S/S 154kV 부개-원미#2/L GIS 정밀점검","2016-11-17 08:00","2016-11-18 14:00","2016-11-17T08:00:00","2016-11-18T14:00:00","연속",null,null,null,201609190169,"-"]
[80,"인천","직할","부개원미#2 T/L","부개S/S 154kV 부개-원미#2T/L GIS 정밀점검","부개S/S 154kV 부개-원미#2T/L GIS 정밀점검","2016-11-17 08:00","2016-11-19 18:00","2016-11-17T08:00:00","2016-11-19T18:00:00","연속",null,null,null,201609190133,"-"]
[81,"인천","직할","부개S/S 154kV #2 BUS","부개S/S 154kV 부개-원미#2/L GIS 정밀점검","부개S/S 154kV 부개-원미#2/L GIS 정밀점검","2016-11-18 14:00","2016-11-19 18:00","2016-11-18T14:00:00","2016-11-19T18:00:00","연속",null,null,null,201609190170,"-"]
[82,"인천","직할","부개S/S 154kV #1 BUS","부개S/S 154kV 부개-원미#1T/L GIS 정밀점검","부개S/S 154kV 부개-원미#1T/L GIS 정밀점검","2016-11-14 08:00","2016-11-15 14:00","2016-11-14T08:00:00","2016-11-15T14:00:00","연속",null,null,null,201609190166,"-"]
[83,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 154kV 신부평-중동#1T/L GIS 정밀점검","신부평S/S 154kV 신부평-중동#1T/L GIS 정밀점검","2016-11-29 14:00","2016-11-30 18:00","2016-11-29T14:00:00","2016-11-30T18:00:00","연속",null,null,"신뢰도개선",201609190183,"-"]
[84,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 154kV 신부평-중동#1T/L GIS 정밀점검","신부평S/S 154kV 신부평-중동#1T/L GIS 정밀점검","2016-11-28 08:00","2016-11-29 14:00","2016-11-28T08:00:00","2016-11-29T14:00:00","연속",null,null,"신뢰도개선",201609190182,"-"]
[85,"인천","직할","신부평중동#1 T/L","신부평S/S 154kV 신부평-중동#1T/L GIS 정밀점검","신부평S/S 154kV 신부평-중동#1T/L GIS 정밀점검","2016-11-28 08:00","2016-11-30 18:00","2016-11-28T08:00:00","2016-11-30T18:00:00","연속",null,null,null,201609190152,"-"]
[86,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 154kV #62M.Tr 1차 GIS 정밀점검","신부평S/S 154kV #62M.Tr 1차 GIS 정밀점검","2016-11-25 14:00","2016-11-26 18:00","2016-11-25T14:00:00","2016-11-26T18:00:00","연속",null,null,"신뢰도개선",201609190181,"-"]
[87,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 154kV #62M.Tr 1차 GIS 정밀점검","신부평S/S 154kV #62M.Tr 1차 GIS 정밀점검","2016-11-24 08:00","2016-11-25 14:00","2016-11-24T08:00:00","2016-11-25T14:00:00","연속",null,null,"신뢰도개선",201609190180,"-"]
[88,"인천","직할","부천원미#2 T/L","원미S/S 154kV 부천-원미#2T/L GIS 정밀점검","원미S/S 154kV 부천-원미#2T/L GIS 정밀점검","2016-11-10 08:00","2016-11-12 18:00","2016-11-10T08:00:00","2016-11-12T18:00:00","연속",null,null,null,201609190127,"-"]
[89,"인천","직할","부개원미#1 T/L","원미S/S 154kV 부개-원미#1T/L GIS 정밀점검","원미S/S 154kV 부개-원미#1T/L GIS 정밀점검","2016-11-01 08:00","2016-11-03 18:00","2016-11-01T08:00:00","2016-11-03T18:00:00","연속",null,null,null,201609190124,"-"]
[90,"인천","직할","부개원미#2 T/L","원미S/S 154kV 부개-원미#2T/L GIS 정밀점검","원미S/S 154kV 부개-원미#2T/L GIS 정밀점검","2016-11-04 08:00","2016-11-06 18:00","2016-11-04T08:00:00","2016-11-06T18:00:00","연속",null,null,null,201609190125,"-"]
[91,"인천","직할","부천원미#1 T/L","원미S/S 154kV 부천-원미#1T/L GIS 정밀점검","원미S/S 154kV 부천-원미#1T/L GIS 정밀점검","2016-11-07 08:00","2016-11-09 18:00","2016-11-07T08:00:00","2016-11-09T18:00:00","연속",null,null,null,201609190126,"-"]
[92,"인천","직할","중동화곡#1 T/L","중동S/S 154kV 중동-화곡#1T/L AIR누기보수","중동S/S 154kV 중동-화곡#1T/L AIR누기보수(662DS)","2016-11-20 09:30","2016-11-20 18:00","2016-11-20T09:30:00","2016-11-20T18:00:00","당일",null,null,null,201609190185,"-"]
[93,"경기북부","구리","가평청평HP#2 T/L","가평S/S 170kV 가평청평HP #2T/L GIS 보통점검(647)","가평S/S 170kV 가평청평HP #2T/L GIS 보통점검(647)","2016-11-08 09:00","2016-11-08 18:00","2016-11-08T09:00:00","2016-11-08T18:00:00","당일",null,null,null,201604120226,"-"]
[94,"경기북부","구리","가평춘천HP T/L","154kV 가평-춘천HP T/L 전선접속개소 전선교체공사","ㅇ 전선접속개소 전선교체공사 - 구간 : No.71~73,79~80,83~86,91~92,106~115,119~120","2016-11-11 08:00","2016-11-25 18:00","2016-11-11T08:00:00","2016-11-25T18:00:00","연속",null,null,null,201607060091,"-"]
[95,"경기북부","구리","가평화천HP T/L","154kV 가평-화천HP T/L 전선접속개소 전선교체공사","ㅇ 전선접속개소 전선교체공사 - 구간 : No.82~83,89~90,106~110,112~115,126~127","2016-11-02 08:00","2016-11-10 18:00","2016-11-02T08:00:00","2016-11-10T18:00:00","연속",null,null,null,201607060090,"-"]
[96,"경기북부","구리","가평청평HP#1 T/L","가평S/S 170kV 가평청평HP #1T/L GIS 보통점검(637)","가평S/S 170kV 가평청평HP #1T/L GIS 보통점검(637)","2016-11-07 09:00","2016-11-07 18:00","2016-11-07T09:00:00","2016-11-07T18:00:00","당일",null,null,null,201604120225,"-"]
[97,"경기북부","구리","구리신내#2 T/L","구리S/S 170kV 구리신내 #2T/L GIS 정밀점검공사(627CB)","구리S/S 170kV 구리신내 #2T/L GIS 정밀점검공사(627CB)","2016-11-14 09:00","2016-11-16 18:00","2016-11-14T09:00:00","2016-11-16T18:00:00","연속",null,null,null,201604080012,"-"]
[98,"경기북부","구리","미금구리#2 T/L","170kV 미금구리 #2T/L GIS 정밀점검공사","구리S/S 170kV 미금구리 #2T/L GIS 정밀점검공사(647CB) 11.28~30 미금S/S 170kV 미금구리 #2T/L GIS 정밀점검공사(627CB) 12.1~3","2016-11-28 09:00","2016-12-03 18:00","2016-11-28T09:00:00","2016-12-03T18:00:00","연속",null,null,null,201604080009,"-"]
[99,"경기북부","구리","덕소별내#2 T/L","덕소S/S 덕소-별내 #2T/L 2DS 정밀점검","과열 발생 관련 2DS 정밀점검","2016-11-03 14:00","2016-11-03 18:00","2016-11-03T14:00:00","2016-11-03T18:00:00","당일",null,null,null,201609060089,"-"]
[100,"경기북부","구리","덕소별내#1 T/L","덕소S/S 덕소-별내 #1T/L 1DS 정밀점검","과열 발생 관련 1DS 정밀점검","2016-11-02 09:00","2016-11-02 14:00","2016-11-02T09:00:00","2016-11-02T14:00:00","당일",null,null,null,201609060084,"○"]
[101,"경기북부","구리","덕소별내#2 T/L","덕소S/S 덕소-별내 #2T/L 1DS 정밀점검","과열 발생 관련 1DS 정밀점검","2016-11-02 14:00","2016-11-02 18:00","2016-11-02T14:00:00","2016-11-02T18:00:00","당일",null,null,null,201609060086,"-"]
[102,"경기북부","구리","덕소별내#1 T/L","덕소S/S 덕소-별내 #1T/L 2DS 정밀점검","과열 발생 관련 2DS 정밀점검","2016-11-03 09:00","2016-11-03 14:00","2016-11-03T09:00:00","2016-11-03T14:00:00","당일",null,null,null,201609060087,"○"]
[103,"경기북부","구리","미금구리#1 T/L","미금,구리S/S 170kV 미금구리 #1T/L GIS 정밀점검공사","미금S/S 170kV 미금구리 #1T/L GIS 정밀점검공사(617CB) 11.7~9 구리S/S 170kV 미금-구리 #1T/L GIS 정밀점검공사(637CB) 11.10~12","2016-11-07 09:00","2016-11-12 18:00","2016-11-07T09:00:00","2016-11-12T18:00:00","연속",null,null,null,201604080006,"-"]
[104,"경기북부","구리","신포천S/S 154kV #2 BUS TIE CB","신포천S/S 6200BUS-TIE 유면계 누유 보수","신포천S/S 6200BUS-TIE 유면계 누유 보수","2016-11-18 09:00","2016-11-18 14:00","2016-11-18T09:00:00","2016-11-18T14:00:00","당일",null,null,null,201609070341,"-"]
[105,"경기북부","구리","운천철원#2 T/L","전선접속개소 교체공사","o No.59-60간 상중하 3가닥 전선접속개소 교체공사","2016-11-28 08:00","2016-11-28 18:00","2016-11-28T08:00:00","2016-11-28T18:00:00","당일",null,null,null,201608190096,"-"]
[106,"경기북부","구리","운천철원#1 T/L","전선접속개소 교체공사","o No.35-39간 상중하 3가닥 전선접속개소 교체공사","2016-11-29 08:00","2016-11-30 18:00","2016-11-29T08:00:00","2016-11-30T18:00:00","연속",null,null,null,201608190099,"○"]
[107,"경기북부","직할","신포천동두천#1 T/L","'16-17 경기북부직할 변전협력 총액공사","동두천S/S 신포천-동두천#1T/L LA 보통점검","2016-11-03 09:00","2016-11-03 18:00","2016-11-03T09:00:00","2016-11-03T18:00:00","당일",null,null,null,201609120011,"-"]
[108,"경기북부","직할","동두천S/S 154kV #1 BUS TIE GIS","16년 경기북부직할변전총액공사","LCP PNL 교체 - SA 설비 철거","2016-11-21 09:00","2016-11-25 18:00","2016-11-21T09:00:00","2016-11-25T18:00:00","연속",null,null,null,201609120041,"-"]
[109,"경기북부","직할","신포천동두천#2 T/L","16년 경기북부직할변전총액공사","LCP PNL 교체 - SA 설비 철거","2016-11-21 09:00","2016-11-25 18:00","2016-11-21T09:00:00","2016-11-25T18:00:00","연속",null,null,null,201609120038,"-"]
[110,"경기북부","직할","신의정부송우#2 T/L","신의정부S/S 170kV GIS LCP PNL 경보창구 보완","GIS LCP PNL 경보창구 추가","2016-11-25 14:00","2016-11-25 18:00","2016-11-25T14:00:00","2016-11-25T18:00:00","당일",null,null,null,201609120427,"-"]
[111,"경기북부","직할","신의정부내촌#1 T/L","신의정부S/S 170kV GIS LCP PNL 경보창구 보완","GIS LCP PNL 경보창구 추가","2016-11-25 09:00","2016-11-25 14:00","2016-11-25T09:00:00","2016-11-25T14:00:00","당일",null,null,null,201609120426,"-"]
[112,"경기북부","직할","양주S/S 65-66-0 SEC CB","16년 경기북부직할변전총액공사","GCB보통점검","2016-11-29 09:00","2016-11-29 18:00","2016-11-29T09:00:00","2016-11-29T18:00:00","당일",null,null,null,201609120015,"-"]
[113,"경기북부","직할","양주S/S 60-61-0 SEC CB","16년 경기북부직할변전총액공사","GCB보통점검","2016-11-28 09:00","2016-11-28 18:00","2016-11-28T09:00:00","2016-11-28T18:00:00","당일",null,null,null,201609120012,"-"]
[114,"경기북부","직할","신포천전곡#1 T/L","전곡변전소 외장재 전면교체공사","- 건물 외부 마감재(드라이비트-&gt메탈판넬) 교체","2016-11-14 09:00","2016-11-22 18:00","2016-11-14T09:00:00","2016-11-22T18:00:00","연속",null,null,null,201607130080,"○"]
[115,"경기북부","직할","신포천전곡#2 T/L","전곡변전소 외장재 전면교체공사","- 건물 외부 마감재(드라이비트-메탈판넬) 교체","2016-11-23 09:00","2016-11-28 18:00","2016-11-23T09:00:00","2016-11-28T18:00:00","연속",null,null,null,201607130085,"-"]
[116,"경기북부","직할","운천전곡#1 T/L","전곡변전소 외장재 전면교체공사","- 건물 외부 마감재(드라이비트-&gt메탈판넬) 교체","2016-11-23 09:00","2016-11-28 18:00","2016-11-23T09:00:00","2016-11-28T18:00:00","연속",null,null,null,201607130083,"○"]
[117,"경기북부","직할","운천전곡#2 T/L","전곡변전소 외장재 전면교체공사","- 건물 외부 마감재(드라이비트-&gt메탈판넬) 교체","2016-11-14 09:00","2016-11-22 18:00","2016-11-14T09:00:00","2016-11-22T18:00:00","연속",null,null,null,201607130077,"-"]
[118,"경기북부","직할","양주은평#2 T/L","16년 경기북부직할변전총액공사","양주-은평#2T/L GCB보통점검","2016-11-08 09:00","2016-11-08 18:00","2016-11-08T09:00:00","2016-11-08T18:00:00","당일",null,null,null,201609120021,"-"]
[119,"경기북부","직할","양주은평#1 T/L","16년 경기북부직할변전총액공사","양주-은평#1T/L GCB보통점검","2016-11-07 09:00","2016-11-07 18:00","2016-11-07T09:00:00","2016-11-07T18:00:00","당일",null,null,null,201609120019,"-"]
[120,"경기북부","파주","고양일산#1 T/L","154kV 고양-일산#1T/L 피뢰기 설치공사","154kV 고양-일산#1T/L No.39~48 피뢰기 설치공사","2016-11-18 07:00","2016-11-20 18:00","2016-11-18T07:00:00","2016-11-20T18:00:00","연속",null,null,null,201608160159,"○"]
[121,"경기북부","파주","덕이호수#1 T/L","덕이,호수S/S 덕이-호수#1T/L GIS 조작시험","GIS 성능(개폐타임) 측정시험","2016-11-07 10:00","2016-11-07 17:00","2016-11-07T10:00:00","2016-11-07T17:00:00","당일",null,null,null,201609110032,"-"]
[122,"경기북부","파주","덕이호수#2 T/L","덕이,호수S/S 덕이-호수#2T/L GIS 조작시험","GIS 성능(개폐타임) 측정시험","2016-11-08 10:00","2016-11-08 17:00","2016-11-08T10:00:00","2016-11-08T17:00:00","당일",null,null,null,201609110033,"-"]
[123,"경기북부","파주","문발덕이#2 T/L","문발,덕이S/S 문발-덕이#2T/L GIS 조작시험","GIS 성능(개폐타임) 측정시험","2016-11-03 10:00","2016-11-03 17:00","2016-11-16T10:00:00","2016-11-16T17:00:00","당일",null,null,null,201609110031,"-"]
[124,"경기북부","파주","문발덕이#1 T/L","문발,덕이S/S 문발-덕이#1T/L GIS 조작시험","GIS 성능(개폐타임) 측정시험","2016-11-02 10:00","2016-11-02 17:00","2016-11-15T10:00:00","2016-11-15T17:00:00","당일",null,null,null,201609110030,"-"]
[125,"경기북부","파주","신파주문발#1 T/L","154kV 신파주-문발#1 T/L 피뢰기설치공사","154kV 신파주-문발#1 T/L No.1~5 피뢰기설치공사","2016-11-28 07:00","2016-11-28 18:00","2016-11-28T07:00:00","2016-11-28T18:00:00","당일",null,null,null,201608160161,"-"]
[126,"경기북부","파주","신덕은문산#1 T/L","154kV 신덕은-문산#1T/L 피뢰기설치공사","154kV 신덕은-문산#1T/L No.87, 107 피뢰기설치공사","2016-11-27 07:00","2016-11-27 18:00","2016-11-27T07:00:00","2016-11-27T18:00:00","당일",null,null,null,201608160163,"-"]
[127,"경기북부","파주","불광서대문#1 T/L","'16~17 파주전력지사 변전협력회사 총액공사","불광-서대문#1T/L CVT 보통점검","2016-11-07 10:00","2016-11-07 18:00","2016-11-07T10:00:00","2016-11-07T18:00:00","당일",null,null,"신뢰도개선",201609050041,"-"]
[128,"경기북부","파주","불광서대문#2 T/L","불광S/S 불광-서대문#2T/L GIS 정밀점검공사","불광S/S 불광-서대문#2T/L GIS 정밀점검공사","2016-11-08 09:00","2016-11-10 18:00","2016-11-08T09:00:00","2016-11-10T18:00:00","연속",null,null,"신뢰도개선",201609110027,"-"]
[129,"경기북부","파주","불광S/S 불광열병합#1T/L CB","불광S/S 불광-열병합#1T/L GIS 정밀점검공사","불광S/S 불광-열병합#1T/L GIS 정밀점검공사","2016-11-28 09:00","2016-11-30 18:00","2016-11-28T09:00:00","2016-11-30T18:00:00","연속",null,null,null,201609110028,"-"]
[130,"경기북부","파주","신덕은원흥#1 T/L","154kV 신덕은-원흥T/L 장기사용 전력선교체공사","전력선교체 : 4.319km","2016-11-25 08:00","2016-11-28 18:00","2016-11-25T08:00:00","2016-11-28T18:00:00","연속",null,null,"신뢰도개선",201609130244,"-"]
[131,"경기북부","파주","신덕은원흥#2 T/L","154kV 신덕은-원흥T/L 장기사용 전력선교체공사","전력선교체 : 4.319km","2016-11-29 08:00","2016-12-04 18:00","2016-11-29T08:00:00","2016-12-04T18:00:00","연속",null,null,"신뢰도개선",201609130248,"-"]
[132,"경기북부","파주","신파주문발#2 T/L","신파주,문발S/S 덕이-호수#2T/L GIS 조작시험","GIS 성능(개폐타임) 측정시험","2016-11-10 10:00","2016-11-10 17:00","2016-11-10T10:00:00","2016-11-10T17:00:00","당일",null,null,null,201609110034,"-"]
[133,"경기북부","파주","신파주송포#2 T/L","154kV 송전선로 보호반 교체공사","송전선로 보호반 교체","2016-11-02 09:00","2016-11-04 18:00","2016-11-02T09:00:00","2016-11-04T18:00:00","연속",null,null,null,201608120264,"-"]
[134,"경기북부","파주","월롱금촌#1 T/L","154kV 월롱금촌#1T/L 피뢰기설치공사","154kV 월롱금촌#1T/L No.14~19 피뢰기 설치공사","2016-11-21 07:00","2016-11-22 18:00","2016-11-21T07:00:00","2016-11-22T18:00:00","연속",null,null,null,201608160157,"-"]
[135,"경기북부","파주","일산송포#2 T/L","백마지하차도 지장송전선로 이설공사","지중송전선로 이설 : 일산-송포 관로 #2~3","2016-11-05 08:00","2016-12-02 18:00","2016-11-05T08:00:00","2016-12-02T18:00:00","연속",null,null,null,201609220019,"-"]
[136,"경기북부","파주","지도S/S 154kV #1 BUS","2016년 파주전력지사 장기사용 170kV GIS 교체공사","지도S/S 장기사용 170kV GIS 교체공사 - 일산지도#1T/L, #2M.Tr, PT&ES 철거, 설치","2016-11-23 08:00","2016-12-09 18:00","2016-11-23T08:00:00","2016-12-09T18:00:00","연속",null,null,null,201609190243,"-"]
[137,"경기북부","파주","지도S/S 154kV #2 BUS","2016년 파주전력지사 장기사용 170kV GIS 교체공사","지도S/S 장기사용 170kV GIS 교체공사 - 일산지도#1T/L, #2M.Tr, PT&ES 철거, 설치","2016-11-11 08:00","2016-11-22 18:00","2016-11-11T08:00:00","2016-11-22T18:00:00","연속",null,null,null,201609130133,"-"]
[138,"경기","군포","반월시화#1 T/L","반월S/S 154kV 현대화공사","- 반월시화#1T/L CVT 이설 - 반월시화#1T/L 아킹혼설치공사5호 1기 아킹혼 설치(군포송전)","2016-11-02 09:00","2016-11-03 18:00","2016-11-02T09:00:00","2016-11-03T18:00:00","연속",null,null,null,201608120302,"-"]
[139,"경기","군포","반월시화#2 T/L","반월S/S 154kV 현대화공사","반월-시화#2T/L CVT 이설 반월-시화#2T/L 1~13호 피뢰기 설치(군포송전)","2016-11-06 07:00","2016-11-07 18:00","2016-11-06T07:00:00","2016-11-07T18:00:00","연속",null,null,null,201609050126,"-"]
[140,"경기","군포","산본안양#2 T/L","154kV 산본안양#2T/L 송전선로 초기(구간 No.7~10)","16년 가공송전선로 순시점검 위탁공사 154kV 산본안양#2T/L 송전선로 초기점검(구간 No.7~10)","2016-11-10 13:00","2016-11-10 18:00","2016-11-10T13:00:00","2016-11-10T18:00:00","당일",null,null,null,201609090277,"-"]
[141,"경기","군포","산본안양#1 T/L","154kV 산본안양#1T/L 송전선로 초기(구간 No.7~10)","16년 가공송전선로 순시점검 위탁공사 154kV 산본안양#1T/L 송전선로 초기점검(구간 No.7~10)","2016-11-10 09:00","2016-11-10 12:00","2016-11-10T09:00:00","2016-11-10T12:00:00","당일",null,null,null,201609090276,"-"]
[142,"경기","군포","신안산성포#3 T/L","신안산SS 감시제어반 교체 공사","신안산SS 감시제어반 교체 공사 -신안산성포#3 T/L 감시, 조작회로 이설","2016-11-18 09:00","2016-11-20 18:00","2016-11-18T09:00:00","2016-11-20T18:00:00","연속",null,null,null,201609070058,"-"]
[143,"경기","군포","조암구문천#2 T/L","조암S/S 조암구문천#2T/L 보호배전반 교체 공사","조암S/S 조암구문천#2T/L 보호배전반 교체 젤파워제 보호반 교체","2016-11-09 09:00","2016-11-11 18:00","2016-11-09T09:00:00","2016-11-11T18:00:00","연속",null,null,null,201609050035,"-"]
[144,"경기","동부","오포모현#1 T/L","154kV 오포-모현#1T/L 낙뢰소산장치 철거공사","154kV 오포-모현#1T/L 4~18호 구간 낙뢰소산장치 철거","2016-11-03 07:00","2016-11-10 18:00","2016-11-03T07:00:00","2016-11-10T18:00:00","연속",null,null,null,201609070055,"-"]
[145,"경기","동부","중원야탑 T/L","성남-장호원 도로개설에 따른 지장송전선로 이설공사","케이블 철거 및 신규포설 2구간 케이블 접속 3개소(NJ2, IJ1)","2016-11-16 09:00","2016-11-26 18:00","2016-11-16T09:00:00","2016-11-26T18:00:00","연속",null,null,null,201609190130,"-"]
[146,"경기","성남","서안성남사#1 T/L","남사S/S 154kV 서안성남사#1T/L GIS 정밀점검","남사S/S 154kV 서안성남사#1T/L GIS 정밀점검","2016-11-02 09:00","2016-11-04 18:00","2016-11-02T09:00:00","2016-11-04T18:00:00","연속",null,null,null,201609070227,"-"]
[147,"경기","성남","용인남사#1 T/L","남사S/S 154kV 용인남사#1T/L GIS 정밀점검","남사S/S 154kV 용인남사#1T/L GIS 정밀점검","2016-11-28 09:00","2016-11-30 18:00","2016-11-28T09:00:00","2016-11-30T18:00:00","연속",null,null,null,201609070233,"-"]
[148,"경기","성남","서안성남사#2 T/L","남사S/S 154kV 서안성남사#2T/L GIS 정밀점검","남사S/S 154kV 서안성남사#2T/L GIS 정밀점검","2016-11-09 09:00","2016-11-11 18:00","2016-11-09T09:00:00","2016-11-11T18:00:00","연속",null,null,null,201609070230,"-"]
[149,"경기","성남","서안성안성#1 T/L","154kV 서운-안성T/L OPGW 증설","안성S/S S/T~No.04 OPGW 증설(4기)","2016-11-15 08:00","2016-11-16 18:00","2016-11-15T08:00:00","2016-11-16T18:00:00","연속",null,null,null,201609060033,"-"]
[150,"경기","성남","서안성안성#2 T/L","154kV 서운-안성T/L OPGW 증설","No.04~12 OPGW 증설(9기)","2016-11-17 08:00","2016-11-17 18:00","2016-11-17T08:00:00","2016-11-17T18:00:00","당일",null,null,null,201609060031,"-"]
[151,"경기","성남","용인S/S 154kV #1 BUS","154kV 용인S/S 무인화대비 설비보강공사","154kV 용인S/S #4M.Tr GIS 설치공사(상체크)","2016-11-06 09:00","2016-11-06 14:00","2016-11-06T09:00:00","2016-11-06T14:00:00","당일",null,null,null,201609200169,"-"]
[152,"경기","성남","용인S/S 154kV #2 BUS","154kV 용인S/S 무인화대비 설비보강공사","154kV 용인S/S #4M.Tr GIS 설치공사(상체크)","2016-11-06 14:00","2016-11-08 18:00","2016-11-06T14:00:00","2016-11-08T18:00:00","연속",null,null,null,201609200170,"-"]
[153,"경기","성남","용인S/S 154kV #1 BUS","154kV 용인S/S 무인화대비 설비보강공사","154kV 용인S/S #5M.Tr GIS 설치공사(상체크)","2016-11-14 09:00","2016-11-14 14:00","2016-11-14T09:00:00","2016-11-14T14:00:00","당일",null,null,null,201609200172,"-"]
[154,"경기","성남","율현용인#1 T/L","154kV 용인S/S 무인화대비 설비보강공사","154kV 용인S/S #5M.Tr GIS 설치공사(무부하가압)","2016-11-14 09:00","2016-11-16 18:00","2016-11-14T09:00:00","2016-11-16T18:00:00","연속",null,null,null,201609200167,"-"]
[155,"경기","성남","율현용인#2 T/L","154kV 용인S/S 무인화대비 설비보강공사","인출모선 철거작업에 따른 안전이격","2016-11-01 14:00","2016-11-01 18:00","2016-11-01T14:00:00","2016-11-01T18:00:00","당일",null,null,null,201609120186,"-"]
[156,"경기","성남","용인S/S 154kV #1 BUS TIE CB","154kV 용인S/S 무인화대비 설비보강공사","신설GIS(6100, 6200) 가압","2016-11-17 09:00","2016-11-19 18:00","2016-11-17T09:00:00","2016-11-19T18:00:00","연속",null,null,null,201609120162,"-"]
[157,"경기","성남","용인S/S 154kV #1 BUS","154kV 용인S/S 무인화대비 설비보강공사","GIS 임시모선 분리","2016-11-20 09:00","2016-11-21 18:00","2016-11-20T09:00:00","2016-11-21T18:00:00","연속",null,null,null,201609120165,"-"]
[158,"경기","성남","모현용인#2 T/L","154kV 모현-용인T/L 안전이격거리 확보공사(본선로 구성)","0 지지물 교체 : 1기(No.19) 0 가철탑 설치 및 철거 : 1기 0 전선교체 : 1.214km 0 기타공사 1식","2016-11-16 07:30","2016-11-20 18:00","2016-11-16T07:30:00","2016-11-20T18:00:00","연속",null,null,null,201608020055,"-"]
[159,"경기","성남","용인S/S 154kV #2 BUS","154kV 용인S/S 무인화대비 설비보강공사","154kV 용인S/S #5M.Tr GIS 설치공사(상체크)","2016-11-14 14:00","2016-11-16 18:00","2016-11-14T14:00:00","2016-11-16T18:00:00","연속",null,null,null,201609200173,"-"]
[160,"경기","성남","율현용인#1 T/L","154kV 용인S/S 무인화대비 설비보강공사","인출모선 철거작업에 따른 안전이격","2016-11-01 09:00","2016-11-01 14:00","2016-11-01T09:00:00","2016-11-01T14:00:00","당일",null,null,null,201609120185,"-"]
[161,"경기","성남","모현용인#1 T/L","154kV 모현-용인T/L 안전이격거리 확보공사(본선로 구성)","0 지지물 교체 : 1기(No.19) 0 가철탑 설치 및 철거 : 1기 0 전선교체 : 1.214km 0 기타공사 1식","2016-11-21 07:30","2016-11-25 18:00","2016-11-21T07:30:00","2016-11-25T18:00:00","연속",null,null,null,201608020056,"-"]
[162,"경기","성남","율현용인#1 T/L","154kV 용인S/S 무인화대비 설비보강공사","154kV 용인S/S #4M.Tr GIS 설치공사(무부하가압)","2016-11-06 09:00","2016-11-08 18:00","2016-11-06T09:00:00","2016-11-08T18:00:00","연속",null,null,null,201609200174,"-"]
[163,"경기","성남","용인S/S 154kV #2 BUS","154kV 용인S/S 무인화대비 설비보강공사","GIS 임시모선 분리","2016-11-22 09:00","2016-11-23 18:00","2016-11-22T09:00:00","2016-11-23T18:00:00","연속",null,null,null,201609120167,"-"]
[164,"경기","직할","조암구문천#1 T/L","154kV 구문천S/S #4M.Tr 증설공사","구문천S/S #4M.Tr 증설공사관련 무부하가압","2016-11-28 09:00","2016-11-30 18:00","2016-11-28T09:00:00","2016-11-30T18:00:00","연속",null,null,null,201609130209,"-"]
[165,"경기","직할","발안구문천#1 T/L","154kV 발안구문천#1T/L 송전선로 정밀점검(구간 No.1~22)","16년 가공송전선로 순시점검 위탁공사 154kV 발안구문천#1T/L 송전선로 정밀점검(구간 No.1~22)","2016-11-17 09:00","2016-11-18 18:00","2016-11-17T09:00:00","2016-11-18T18:00:00","매일",null,null,null,201609080067,"-"]
[166,"경기","직할","발안구문천#2 T/L","154kV 발안구문천#2T/L 송전선로 정밀점검(구간 No.1~22)","16년 가공송전선로 순시점검 위탁공사 154kV 발안구문천#2T/L 송전선로 정밀점검(구간 No.1~22)","2016-11-21 09:00","2016-11-22 18:00","2016-11-21T09:00:00","2016-11-22T18:00:00","매일",null,null,null,201609080068,"-"]
[167,"경기","직할","서서울남수원#1 T/L","'16-17년 경기본부 직할 송전정비 협력회사 총액공사","- 공 사 명 : 경기본부 직할 송전정비 협력회사 총액공사 - 공사내용 : 154kV 남수원-발안 #1T/L 피뢰기 설치(57기) - 기타사항 : 상기선로와 병가선로로 작업자와 자재의 안전한 이동을 위해 병행 휴전시행","2016-11-23 08:00","2016-11-24 18:00","2016-11-23T08:00:00","2016-11-24T18:00:00","연속",null,null,null,201609120302,"-"]
[168,"경기","직할","과천동안양#2 T/L","154kV 과천-동안양#1T/L 피뢰기 설치공사","- 154kV 과천-동안양#1T/L 1~8호 피뢰기 설치관련 안전이격거리확보","2016-11-17 07:00","2016-11-18 18:00","2016-11-17T07:00:00","2016-11-18T18:00:00","연속",null,null,null,201609050155,"-"]
[169,"경기","직할","과천동안양#1 T/L","154kV 과천-동안양#1T/L 피뢰기 설치공사","- 1~23호간 20기 피뢰기 설치","2016-11-17 07:00","2016-11-18 18:00","2016-11-17T07:00:00","2016-11-18T18:00:00","연속",null,null,null,201609050154,"-"]
[170,"경기","직할","서수원율전#2 T/L","'16-17년 경기본부 직할 송전정비 협력회사 총액공사","- 공 사 명 : 경기본부 직할 송전정비 협력회사 총액공사 - 공사내용 : 154kV 율전-동수원 #1T/L 피뢰기 설치(2기)","2016-11-29 08:00","2016-11-29 18:00","2016-11-29T08:00:00","2016-11-29T18:00:00","당일",null,null,null,201609120334,"-"]
[171,"경기","직할","율전의왕#2 T/L","154kV 율전-의왕#2T/L 아킹혼 설치공사","- 4~24호 아킹혼 설치","2016-11-03 07:00","2016-11-04 18:00","2016-11-03T07:00:00","2016-11-04T18:00:00","연속",null,null,null,201609050140,"-"]
[172,"경기","직할","의왕동안양#1 T/L","154kV 율전-의왕#2T/L 아킹혼 설치공사","- 154kV 율전-의왕#2T/L 13~24호 아킹혼 설치 안전이격거리확보 - 154kV 의왕-동안양#2T/L 41~48호 피뢰기 설치 안전이격거리확보","2016-11-03 07:00","2016-11-06 18:00","2016-11-03T07:00:00","2016-11-06T18:00:00","연속",null,null,null,201609050145,"-"]
[173,"경기","직할","의왕동안양#2 T/L","154kV 의왕-동안양#2T/L 피뢰기 설치공사","- 14~48호 피뢰기 설치","2016-11-05 07:00","2016-11-09 18:00","2016-11-05T07:00:00","2016-11-09T18:00:00","연속",null,null,null,201609050147,"-"]
[174,"경기","직할","발안향남#1 T/L","'16-17년 경기본부 직할 송전정비 협력회사 총액공사","- 공 사 명 : 경기본부 직할 송전정비 협력회사 총액공사 - 공사내용 : 154kV 남수원-발안 #1T/L 피뢰기 설치(57기) - 기타사항 : 상기선로와 병가선로로 작업자와 자재의 안전한 이동을 위해 병행 휴전시행","2016-11-26 08:00","2016-11-27 18:00","2016-11-26T08:00:00","2016-11-27T18:00:00","연속",null,null,null,201609120305,"-"]
[175,"경기","직할","화성발안#1 T/L","화성S/S 화성발안#1 T/L CVT교체","화성S/S 화성발안#1 T/L CVT교체","2016-11-16 09:00","2016-11-16 14:00","2016-11-16T09:00:00","2016-11-16T14:00:00","당일",null,null,null,201609070103,"-"]
[176,"경기","직할","화성발안#2 T/L","화성S/S 화성발안#2 T/L CVT교체","화성S/S 화성발안#2 T/L CVT교체","2016-11-16 14:00","2016-11-16 18:00","2016-11-16T14:00:00","2016-11-16T18:00:00","당일",null,null,null,201609070104,"-"]
[177,"경기","평택","서운안성#2 T/L","154kV 서운-안성T/L OPGW 증설","No.43~49 OPGW 증설(7기)","2016-11-19 08:00","2016-11-20 18:00","2016-11-19T08:00:00","2016-11-20T18:00:00","연속",null,null,null,201609060024,"-"]
[178,"경기","평택","서운만승 T/L","154kV 서운-만승T/L 소도체 이도조정공사","4회선병가구간(No.4-6) 소도체 이도조정","2016-11-07 08:00","2016-11-07 18:00","2016-11-07T08:00:00","2016-11-07T18:00:00","당일",null,null,null,201609090112,"○"]
[179,"경기","평택","서운안성#1 T/L","154kV 서운-안성T/L OPGW 증설","No.39~43 OPGW 증설(5기)","2016-11-26 08:00","2016-11-30 18:00","2016-11-26T08:00:00","2016-11-30T18:00:00","연속",null,null,null,201609060026,"○"]
[180,"경기","평택","서운삼죽 T/L","154kV 서운-안성T/L OPGW 증설","No.39~43 OPGW 증설(5기)","2016-11-26 08:00","2016-11-27 18:00","2016-11-26T08:00:00","2016-11-27T18:00:00","연속",null,null,null,201609060025,"-"]
[181,"경기","평택","서운삼죽 T/L","154kV 서운-안성T/L OPGW 증설","No.43~49 OPGW 증설(7기)","2016-11-19 08:00","2016-11-20 18:00","2016-11-19T08:00:00","2016-11-20T18:00:00","연속",null,null,null,201609060023,"-"]
[182,"경기","평택","서운안성#2 T/L","154kV 서운-안성T/L OPGW 증설","No.57~서운S/S S/T OPGW 증설(6기)","2016-11-05 08:00","2016-11-06 18:00","2016-11-05T08:00:00","2016-11-06T18:00:00","연속",null,null,null,201609060019,"-"]
[183,"경기","평택","서운안성#1 T/L","154kV 서운-안성T/L OPGW 증설","안성S/S S/T~No.12 OPGW 증설(13기)","2016-11-15 08:00","2016-11-18 18:00","2016-11-15T08:00:00","2016-11-18T18:00:00","연속",null,null,null,201609060029,"○"]
[184,"경기","평택","서운안성#2 T/L","154kV 서운-안성T/L OPGW 증설","No.49~57 OPGW 증설(9기)","2016-11-12 08:00","2016-11-13 18:00","2016-11-12T08:00:00","2016-11-13T18:00:00","연속",null,null,null,201609060022,"-"]
[185,"경기","평택","서운삼죽 T/L","154kV 서운-안성T/L OPGW 증설","No.49~57 OPGW 증설(9기)","2016-11-12 08:00","2016-11-13 18:00","2016-11-12T08:00:00","2016-11-13T18:00:00","연속",null,null,null,201609060021,"-"]
[186,"경기","평택","서운삼죽 T/L","154kV 서운-안성T/L OPGW 증설","No.57~서운S/S S/T OPGW 증설(6기)","2016-11-05 08:00","2016-11-06 18:00","2016-11-05T08:00:00","2016-11-06T18:00:00","연속",null,null,null,201609060017,"-"]
[187,"경기","평택","송탄소사벌 T/L","평택동삭2지구 지중화","154kV 송탄-안성(소사벌) No.8~11 지중화","2016-11-06 08:00","2016-11-14 18:00","2016-11-06T08:00:00","2016-11-14T18:00:00","연속",null,null,null,201609050011,"-"]
[188,"경기","평택","원정평택T/P#3 T/L","154kV 포승-평택화력#2T/L 직결공사","154kV 원정-평택화력#3T/L, 154kV 원정-포승T/L 직결공사 - 점퍼지지애자련 설치 - 점퍼선 설치 - 1∏ 철거","2016-11-18 08:00","2016-11-20 18:00","2016-11-18T08:00:00","2016-11-20T18:00:00","연속",null,null,null,201609050170,"-"]
[189,"경기","평택","원정포승 T/L","154kV 포승-평택화력#2T/L 직결공사","154kV 원정-평택화력#3T/L, 154kV 원정-포승T/L 직결공사 - 점퍼지지애자련 설치 - 점퍼선 설치 - 1∏ 철거","2016-11-18 08:00","2016-11-20 18:00","2016-11-18T08:00:00","2016-11-20T18:00:00","연속",null,null,null,201609050173,"-"]
[190,"경기","평택","평택추팔#2 T/L","154kV 평택-추팔T/L No.14, 15 안전이격 확보공사","철탑교체 2기(No.14, 15), 가철주 2기 전력선교체(접속개소 제거)","2016-11-30 08:00","2016-12-04 18:00","2016-11-30T08:00:00","2016-12-04T18:00:00","연속",null,null,null,201609050201,"-"]
[191,"경기","평택","평택추팔#1 T/L","154kV 평택-추팔T/L No.14, 15 안전이격 확보공사","철탑교체 2기(No.14, 15), 가철주 2기 전력선교체(접속개소 제거)","2016-11-28 08:00","2016-11-29 18:00","2016-11-28T08:00:00","2016-11-29T18:00:00","연속",null,null,null,201609050200,"-"]
[192,"경기","평택","포승평택TP T/L","154kV 포승-평택TPT/L 피뢰기 설치공사","4회선병가구간(No.26-41) 송전용피뢰기 16기 설치","2016-11-26 08:00","2016-11-27 18:00","2016-11-26T08:00:00","2016-11-27T18:00:00","매일",null,null,null,201609090111,"-"]
[193,"강원","강릉","신양양_양양#1 T/L","2016~17년 송전정비 협력회사 총액공사","○ 협력회사 전선교체(No.33~35, 49~52, 52~56)","2016-11-26 09:00","2016-12-01 18:00","2016-11-26 09:00","2016-12-01 18:00","연속",null,null,null,201609130080,"-"]
[194,"강원","강릉","신양양_양양#2 T/L","2016~17년 송전정비 협력회사 총액공사","○ 협력회사 전선교체(No.33~35, 49~52, 52~56) ○ KPS 정밀점검(신양양S/S~양양S/S)","2016-11-21 09:00","2016-11-25 18:00","2016-11-21 09:00","2016-11-25 18:00","연속",null,null,null,201609130078,"-"]
[195,"강원","강릉","신양양_양양#1 T/L","양양S/S 외장재 교체공사","노후외장재 교체","2016-11-08 09:00","2016-11-10 18:00","2016-11-08 09:00","2016-11-10 18:00","매일",null,null,null,201609130335,"-"]
[196,"강원","강릉","주문진양양#2 T/L","양양S/S 외장재 교체공사","노후외장재 교체","2016-11-04 09:00","2016-11-06 18:00","2016-11-04 09:00","2016-11-06 18:00","매일",null,null,null,201609130333,"-"]
[197,"강원","강릉","주문진양양#1 T/L","양양S/S 외장재 교체공사","노후외장재 교체","2016-11-02 09:00","2016-11-04 18:00","2016-11-02 09:00","2016-11-04 18:00","매일",null,null,null,201609130332,"-"]
[198,"강원","강릉","신양양_양양#2 T/L","양양S/S 외장재 교체공사","노후외장재 교체","2016-11-06 09:00","2016-11-08 18:00","2016-11-06 09:00","2016-11-08 18:00","매일",null,null,null,201609130334,"-"]
[199,"강원","강릉","신제천주진#1 T/L","154kV 신제천-주진T/L 전선접속개소 해소공사","대상 : 154kV 신제천-주진#1T/L No.8~14 등 4구간 내용 : 전선접속개소 전선교체","2016-11-21 08:00","2016-11-26 18:00","2016-11-21 08:00","2016-11-26 18:00","연속",null,null,null,201609120104,"-"]
[200,"강원","강릉","신제천주진#2 T/L","154kV 신제천-주진T/L 전선접속개소 해소공사","대상 : 154kV 신제천-주진#2T/L No.8~14 등 5구간 내용 : 전선접속개소 전선교체","2016-11-27 08:00","2016-12-01 18:00","2016-11-27 08:00","2016-12-01 18:00","연속",null,null,null,201609120109,"-"]
[201,"강원","강릉","강릉횡계#1 T/L","횡계S/S 외장재 교체공사","노후 외장재 교체","2016-11-03 09:00","2016-11-05 18:00","2016-11-03 09:00","2016-11-05 18:00","매일",null,null,null,201609130282,"-"]
[202,"강원","강릉","강릉횡계#2 T/L","횡계S/S 외장재 교체공사","노후 외장재 교체","2016-11-01 09:00","2016-11-03 18:00","2016-11-01 09:00","2016-11-03 18:00","매일",null,null,null,201609130281,"-"]
[203,"강원","동해","동해강릉 T/L","154kV 동해분기T/L No,66~68 안전이격확보공사","1. 154kV 동해분기T/L No.66~68 안전이격확보공사 - 신설3기, 철거3기, 전선교체 2, 2016~17년도 동해전력지사 송전정비협력회사 총액공사 - 전선교체 및 금구류 교체","2016-11-10 07:00","2016-11-19 18:00","2016-11-10 07:00","2016-11-19 18:00","연속",null,null,null,201609120451,"-"]
[204,"강원","동해","동해영동TP T/L","154kV 동해분기T/L No,66~68 안전이격확보공사","1. 154kV 동해분기T/L No.66~68 안전이격확보공사 - 신설3기, 철거3기, 전선교체 2, 2016~17년도 동해전력지사 송전정비협력회사 총액공사 - 전선교체 및 금구류 교체","2016-11-20 07:00","2016-11-26 18:00","2016-11-20 07:00","2016-11-26 18:00","연속",null,null,null,201609120474,"-"]
[205,"강원","동해","북평영동TP#1 T/L","2016~17년도 동해전력지사 송전정비협력회사 총액공사","1. 2016~17년도 동해전력지사 송전정비협력회사 총액공사 - 전선교체 및 금구류 교체 (154kV 동해-영동TPT/L No.96-97 및 No.87(4회선철탑 상단) 휴전작업에 따른 동시휴전요청_작업자안전확보)","2016-11-25 07:00","2016-11-25 18:00","2016-11-25 07:00","2016-11-25 18:00","당일",null,null,null,201609180002,"-"]
[206,"강원","동해","북평영동TP#2 T/L","2016~17년도 동해전력지사 송전정비협력회사 총액공사","1. 2016~17년도 동해전력지사 송전정비협력회사 총액공사 - 전선교체 및 금구류 교체 (154kV 동해-영동TPT/L No.96-97 및 No.87(4회선철탑 상단) 휴전작업에 따른 동시휴전요청_작업자안전확보)","2016-11-26 07:00","2016-11-26 18:00","2016-11-26 07:00","2016-11-26 18:00","당일",null,null,null,201609180003,"-"]
[207,"강원","원주","남원주원주#2 T/L","남원주S/S 외장재 교체공사","노후 외장재 교체공사","2016-11-05 09:00","2016-11-11 18:00","2016-11-05 09:00","2016-11-11 18:00","매일",null,null,null,201609130343,"-"]
[208,"강원","원주","남원주원주#1 T/L","남원주S/S 외장재 교체공사","노후 외장재 교체공사","2016-11-01 09:00","2016-11-07 18:00","2016-11-01 09:00","2016-11-07 18:00","매일",null,null,null,201609130345,"-"]
[209,"강원","원주","신제천남원주#1 T/L","남원주S/S 외장재 교체공사","노후 외장재 교체공사","2016-11-09 09:00","2016-11-15 18:00","2016-11-09 09:00","2016-11-15 18:00","매일",null,null,null,201609130347,"-"]
[210,"강원","원주","신제천남원주#2 T/L","남원주S/S 외장재 교체공사","노후 외장재 교체공사","2016-11-13 09:00","2016-11-19 18:00","2016-11-13 09:00","2016-11-19 18:00","매일",null,null,null,201609130348,"-"]
[211,"강원","원주","여주문막#2 T/L","문막S/S 170kV 장기사용 GIS 대체공사","- 170kV GIS 철거/설치 X 5Bay(여주-문막#1,2T/L, #1,2M.Tr, BUS TIE) - 170kV PT&ES GIS 철거/설치 X 1Set","2016-11-11 09:00","2016-12-01 18:00","2016-11-11 09:00","2016-12-01 18:00","연속",null,null,null,201609060020,"-"]
[212,"강원","원주","홍천소양강HP T/L","154kV 소양T/L 안전이격 확보공사","철탑교체 3기 및 전력선 교체","2016-11-21 07:30","2016-11-22 18:00","2016-11-21 07:30","2016-11-22 18:00","연속",null,null,null,201609130085,"-"]
[213,"강원","원주","홍천소양강HP T/L","154kV 소양T/L 안전이격 확보공사","철탑교체 3기 및 전력선 교체","2016-11-25 07:30","2016-11-28 18:00","2016-11-25 07:30","2016-11-28 18:00","연속",null,null,null,201609130088,"-"]
[214,"강원","직할","남춘천춘천 T/L","154kV 소양T/L 안전이격 확보공사","철탑교체 3기 및 전력선 교체","2016-11-29 07:30","2016-12-02 18:00","2016-11-29 07:30","2016-12-02 18:00","연속",null,null,null,201609130089,"-"]
[215,"강원","직할","남춘천춘천 T/L","154kV 소양T/L 안전이격 확보공사","철탑교체 3기 및 전력선 교체","2016-11-23 07:30","2016-11-24 18:00","2016-11-23 07:30","2016-11-24 18:00","연속",null,null,null,201609130087,"-"]
[216,"강원","직할","북춘천춘천HP T/L","2016년 하반기 장기미동작 차단기 조작시험","2016년 하반기 장기미동작 차단기 조작시험 시행","2016-11-03 10:00","2016-11-03 14:00","2016-11-03 10:00","2016-11-03 14:00","당일",null,null,null,201608020114,"-"]
[217,"강원","직할","인제양구#1 T/L","154kV 인제-양구T/L 인출 케이블 교체공사","인제S/S~인출C/H 용량증대 인출 케이블 교체","2016-11-14 08:00","2016-12-09 18:00","2016-11-14 08:00","2016-12-09 18:00","연속",null,null,null,201609220016,"-"]
[218,"강원","직할","가평화천HP T/L","154kV 화천T/L 안전이격 확보공사","○ 철탑신설 : 8기 ○ 전선교체 : 2C-4.677km","2016-11-30 08:00","2016-12-01 18:00","2016-11-30 08:00","2016-12-01 18:00","연속",null,null,null,201609130144,"-"]
[219,"강원","직할","북춘천화천HP T/L","154kV 화천T/L 안전이격 확보공사","○ 철탑신설 : 8기 ○ 전선교체 : 2C-4.677km","2016-11-28 08:00","2016-11-29 18:00","2016-11-28 08:00","2016-11-29 18:00","연속",null,null,null,201609130140,"-"]
[220,"강원","직할","가평화천HP T/L","154kV 화천T/L 안전이격 확보공사","○ 철탑신설 : 6기 ○ 전선교체 : 2C-2.925km ○ 정밀점검","2016-11-01 08:00","2016-11-06 18:00","2016-11-01 08:00","2016-11-06 18:00","연속",null,null,null,201609130107,"-"]
[221,"강원","태백","정선영월CC T/L","154kV 영월화력T/L 안전이격확보공사","영월화력TL No.3~7 전력선 가선","2016-11-07 08:00","2016-11-18 18:00","2016-11-07 08:00","2016-11-18 18:00","연속",null,null,null,201609130119,"-"]
[222,"강원","태백","동영월영월CC T/L","154kV 영월화력T/L 안전이격확보공사","동영월-영월CCT/L No.3~7 안전이격확보(전선가선)","2016-11-03 08:00","2016-11-06 18:00","2016-11-03 08:00","2016-11-06 18:00","연속",null,null,null,201609130101,"-"]
[223,"충북","직할","단양영월CC#2 T/L","154kV 단양-영월CCT/L 안전이격확보공사","○ 공사구간 : 154kV 단양-영월CC T/L 34 ∼ 36호, 42 ∼ 45호간 ○ 철탑교체 : 154kV 2회선용 6기 (35, 36, 42, 43, 44, 45호), 상부재교체 (34, 46호) ○ 전력선교체 : HSTACIR/AW 330㎟(S) × 2회선 (2.129km) ○ 가공지선교체 : OPGW 70㎟ × 1조","2016-11-05 08:00","2016-11-11 18:00","2016-11-21 08:00","2016-11-27 18:00","연속",null,null,null,201608090360,"-"]
[224,"충북","직할","점촌단양 T/L","효성제 GIS 제작사 하자보수","단양S/S 154kV 점촌단양T/L 가스밀도검출기 불량 교체(4개)","2016-11-19 09:00","2016-11-19 18:00","2016-11-19 09:00","2016-11-19 18:00","당일",null,null,null,201608260086,"-"]
[225,"충북","직할","왕암가남#2 T/L","2016년 가공송전선로 순시점검 위탁공사","154kV 왕암-북충주 휴전에 따른 병가선로 휴전(안전조치)","2016-11-11 08:00","2016-11-11 18:00","2016-11-11 08:00","2016-11-11 18:00","당일",null,null,null,201609090094,"-"]
[226,"충북","직할","왕암가남#2 T/L","154kV 왕암-가남T/L 132호 안전이격확보공사","철탑설치 2기, 철탑철거 1기","2016-11-19 08:00","2016-11-25 18:00","2016-11-19 08:00","2016-11-25 18:00","연속",null,null,null,201609060101,"-"]
[227,"충북","직할","왕암가남#1 T/L","154kV 왕암-가남T/L 132호 안전이격확보공사","철탑설치 2기, 철탑철거 1기","2016-11-17 08:00","2016-11-25 18:00","2016-11-17 08:00","2016-11-25 18:00","연속",null,null,null,201609060100,"-"]
[228,"충북","직할","왕암가남#1 T/L","2016년 가공송전선로 순시점검 위탁공사","154kV 왕암-북충주 휴전에 따른 병가선로 휴전(안전조치)","2016-11-16 08:00","2016-11-16 18:00","2016-11-16 08:00","2016-11-16 18:00","당일",null,null,null,201609090092,"-"]
[229,"충북","직할","음성금왕#2 T/L","2016~17년 충주 송전정비 협력회사 총액공사(4회선 병행휴전)","154kV 금왕-남음성#1T/L 4회선 구간 병행휴전","2016-11-16 08:00","2016-11-16 18:00","2016-11-16 08:00","2016-11-16 18:00","당일",null,null,null,201609090207,"○"]
[230,"충북","직할","음성S/S 154kV #1 BUS TIE GIS","16년 직할 변전협력회사 총액공사","음성S/S 154kV BUS TIE GIS(6100) 초기점검","2016-11-09 10:00","2016-11-09 18:00","2016-11-09 10:00","2016-11-09 18:00","당일",null,null,null,201608120332,"○"]
[231,"충북","청주","봉명상당#2 T/L","154kV 봉명-상당 T/L 접속함 Recall 공사","일진제 PMJ 접속함 42개소 Recall 공사","2016-11-04 09:00","2016-11-22 18:00","2016-11-04 09:00","2016-11-22 18:00","연속",null,null,null,201608020096,"-"]
[232,"충북","청주","세종청원#1 T/L","345kV 신옥천-세종 등 3개 T/L 피뢰기 설치공사","피뢰기 설치 (26기)","2016-11-16 07:00","2016-11-20 18:00","2016-11-16 07:00","2016-11-20 18:00","연속",null,null,null,201609290082,"-"]
[233,"충북","청주","신옥천세종#2 T/L","345kV 신옥천-세종 등 3개 T/L 피뢰기 설치공사","피뢰기 설치 55기","2016-11-09 07:00","2016-11-15 18:00","2016-11-09 07:00","2016-11-15 18:00","연속",null,null,null,201609290081,"-"]
[234,"충북","충주","진천덕산#2 T/L","2016~17년 충주 송전정비 협력회사 총액공사(상간스페이서 설치)","154kV 진천-덕산T/L No.3~4간 상간스페이서 설치","2016-11-25 08:00","2016-11-25 18:00","2016-11-25 08:00","2016-11-25 18:00","당일",null,null,null,201609290074,"-"]
[235,"충북","충주","남음성덕산#1 T/L","2016~17년 충주 송전정비 협력회사 총액공사(피뢰기,조류,항공)","피뢰기설치(2~21호), 조류착지방지장치 설치(14~20호), 항공번호찰 교체(5,10,15,20호)","2016-11-17 08:00","2016-11-20 18:00","2016-11-17 08:00","2016-11-20 18:00","매일",null,null,null,201609090245,"○"]
[236,"충북","충주","금왕남음성#1 T/L","2016~17년 충주 송전정비 협력회사 총액공사(피뢰기,조류,애자)","피뢰기설치(27~41호), 조류착지방지장치 설치(1~30호), 불량애자교체(23호)","2016-11-14 08:00","2016-11-16 18:00","2016-11-14 08:00","2016-11-16 18:00","매일",null,null,null,201609090206,"○"]
[237,"충북","충주","신진천S/S 65-66-0 SEC CB","개폐장치 보통점검","개폐장치 보통점검","2016-11-07 10:00","2016-11-07 18:00","2016-11-07 10:00","2016-11-07 18:00","당일",null,null,null,201609090159,"-"]
[238,"충북","충주","신진천S/S 154kV #2 BUS TIE CB","개폐장치 러버히터 설치","개폐장치 러버히터 설치","2016-11-08 10:00","2016-11-08 18:00","2016-11-08 10:00","2016-11-08 18:00","당일",null,null,null,201609090161,"-"]
[239,"충북","충주","진천S/S 154kV BUS TIE CB","장기미동작 차단기 조작시험","장기미동작 차단기 조작시험","2016-11-07 09:00","2016-11-07 10:00","2016-11-07 09:00","2016-11-07 10:00","당일",null,null,null,201609090144,"○"]
[240,"충북","충주","진천덕산#1 T/L","2016~17년 충주 송전정비 협력회사 총액공사(피뢰기 설치)","피뢰기설치(1~27호)","2016-11-21 08:00","2016-11-24 18:00","2016-11-21 08:00","2016-11-24 18:00","매일",null,null,null,201609090247,"○"]
[241,"대전충남","대전","금산무주#2 T/L","154kV 금산무주T/L 전선접속개소 전력선 교체공사","전선접속개소 전력선 교체","2016-11-07 07:00","2016-11-22 18:00","2016-11-07T07:00:00","2016-11-22T18:00:00","연속",null,null,null,201609090176,"-"]
[242,"대전충남","대전","금산무주#1 T/L","154kV 금산무주T/L 전선접속개소 전력선 교체공사","전선접속개소 전력선 교체","2016-11-23 07:00","2016-12-07 18:00","2016-11-23T07:00:00","2016-12-07T18:00:00","연속",null,null,null,201609090174,"-"]
[243,"대전충남","대전","신옥천서대전#1 T/L","154kV 신계룡-유성 등 9개T/L 피뢰기 설치공사","송전선로용 피뢰기 설치","2016-11-01 07:00","2016-11-06 18:00","2016-11-01T07:00:00","2016-11-06T18:00:00","매일",null,null,null,201609090163,"-"]
[244,"대전충남","대전","신계룡S/S #61M.Tr(ESS) CB","○ 신계룡S/S 154kV #61M.Tr 초기점검","○ 신계룡S/S 154kV #61M.Tr 초기점검 ○ 신계룡S/S 154kV #61M.Tr 1차 GIS 초기점검 ○ 신계룡S/S 154kV #61M.Tr 2차 GIS 초기점검 ○ 신계룡S/S 23kV #3S.Tr GIS 초기점검 ○ 신계룡S/S 23kV #1 BUS TIE GIS 초기점검 ○ 신계룡S/S 23kV ESS#1~6 GIS 초기점검","2016-11-08 09:00","2016-11-10 18:00","2016-11-08T09:00:00","2016-11-10T18:00:00","연속",null,null,null,201609130353,"-"]
[245,"대전충남","대전","신계룡가수원#2 T/L","○ 154kV 신계룡-가수원#2 T/L PNL 교체","○ 154kV 신계룡-가수원#2 T/L PNL 교체","2016-11-21 09:00","2016-11-23 18:00","2016-11-21T09:00:00","2016-11-23T18:00:00","연속",null,null,null,201609200058,"-"]
[246,"대전충남","서산","아산송악#2 T/L","154kV 아산-송악T/L 피뢰기설치 공사","154kV 아산-송악#2T/L 피뢰기설치 공사 - No.103~110(8기), 24set","2016-11-14 07:00","2016-11-14 18:00","2016-11-14T07:00:00","2016-11-14T18:00:00","당일",null,null,null,201609120124,"-"]
[247,"대전충남","서산","신당진당진#2 T/L","154kV 신당진-당진T/L 국산애자교체공사","154kV 신당진-당진T/L 국산애자교체공사 - No.44","2016-11-14 07:00","2016-11-15 18:00","2016-11-14T07:00:00","2016-11-15T18:00:00","매일",null,null,null,201609120122,"-"]
[248,"대전충남","서산","신당진당진#1 T/L","154kV 신당진-당진T/L 국산애자교체공사","154kV 신당진-당진T/L 국산애자교체공사 - No.44","2016-11-16 07:00","2016-11-16 18:00","2016-11-16T07:00:00","2016-11-16T18:00:00","당일",null,null,null,201609120123,"-"]
[249,"대전충남","서산","태안태안화력 T/L","변전협력업체 총액공사","○ 수동Trip 레버 연결선 ~ 제어케이블 혼촉분리 ○ 차단기 부동작 예방 조작시험","2016-11-02 10:00","2016-11-02 18:00","2016-11-02T10:00:00","2016-11-02T18:00:00","당일",null,null,null,201609120257,"-"]
[250,"대전충남","서산","서산태안 T/L","154kV 차단기 부동작 예방 조작시험","차단기 부동작 예방 조작시험","2016-11-01 10:00","2016-11-01 11:30","2016-11-01T10:00:00","2016-11-01T11:30:00","당일",null,null,null,201609130187,"-"]
[251,"대전충남","서산","태안T/P 154kV #1 BUS TIE CB","태안T/P 154kV GIS 초기점검(6100)","태안T/P 154kV #1BUS-TIE GIS 초기점검(6100)","2016-11-03 09:00","2016-11-03 18:00","2016-11-03T09:00:00","2016-11-03T18:00:00","당일",null,null,null,201609060092,"-"]
[252,"대전충남","세종","세종서세종#2 T/L","[변전] 세종P/O 협력회사 총액공사","○ GIS초기점검 -세종S/S, 서세종S/S 양측","2016-11-22 09:00","2016-11-22 18:00","2016-11-22T09:00:00","2016-11-22T18:00:00","당일",null,null,null,201609060097,"-"]
[253,"대전충남","세종","세종서세종#1 T/L","[변전] 세종P/O 협력회사 총액공사","○ GIS초기점검 -세종S/S, 서세종S/S 양측","2016-11-21 09:00","2016-11-21 18:00","2016-11-21T09:00:00","2016-11-21T18:00:00","당일",null,null,null,201609060096,"-"]
[254,"대전충남","세종","천안전의#1 T/L","154KV 천안-전의#1T/L 피뢰기설치공사","[송전] 천안-전의#1T/L 피뢰기설치 2기 No.1,38","2016-11-16 07:00","2016-11-16 13:00","2016-11-16T07:00:00","2016-11-16T13:00:00","당일",null,null,null,201609080061,"-"]
[255,"대전충남","세종","조치원전의#2 T/L","154KV 조치원-전의#2T/L 피뢰기설치공사","[송전] 조치원-전의#2T/L 피뢰기설치 50기 No.1~28,30,32~51,55","2016-11-07 07:00","2016-11-09 18:00","2016-11-07T07:00:00","2016-11-09T18:00:00","매일",null,null,null,201609080059,"-"]
[256,"대전충남","아산","서천안탕정#1 T/L","[송전] 345kV 아산-화성 등 15개T/L 피뢰기 설치공사","154kV 신온양-한샘#1T/L 피뢰기 설치공사 - 154kV 송전용 피뢰기 26기 설치 - 기타 부대공사","2016-11-16 09:00","2016-11-16 18:00","2016-11-16T09:00:00","2016-11-16T18:00:00","당일",null,null,null,201609130283,"-"]
[257,"대전충남","아산","신온양한샘#1 T/L","[송전]345kV 아산-화성 등15개T/L 피뢰기 설치공사","154kV 신온양-한샘#1T/L 피뢰기 설치 - 154kV 피뢰기 26기분(18~43호) - 기타 부대작업","2016-11-15 09:00","2016-11-16 18:00","2016-11-15T09:00:00","2016-11-16T18:00:00","매일",null,null,null,201609130273,"-"]
[258,"대전충남","아산","신탕정탕정#2 T/L","신탕정S/S 154kV 신탕정-탕정#2/L 보호반 제작사 성능 개선","○ 154kV 신탕정-탕정#2/L 보호배전반 제작사 성능 개선","2016-11-25 09:00","2016-11-25 18:00","2016-11-25T09:00:00","2016-11-25T18:00:00","당일",null,null,null,201609210039,"-"]
[259,"대전충남","아산","신탕정탕정#1 T/L","신탕정S/S 154kV 신탕정-탕정#1T/L 보호반 제작사 성능 개선","○ 154kV 신탕정-탕정#1T/L 보호배전반 제작사 성능 개선","2016-11-24 09:00","2016-11-24 18:00","2016-11-24T09:00:00","2016-11-24T18:00:00","당일",null,null,null,201609120063,"-"]
[260,"대전충남","아산","아산인주#2 T/L","인주S/S 154kV 아산-인주#2T/L GIS 정밀점검","○ 154kV 아산-인주#2T/L GIS 정밀점검 ○ 병행) 154kV 아산-인주#2T/L LA, CVT 보통점검","2016-11-04 09:00","2016-11-06 18:00","2016-11-04T09:00:00","2016-11-06T18:00:00","연속",null,null,null,201609120047,"-"]
[261,"대전충남","아산","인주S/S 154kV #1 BUS","인주S/S 154kV 인주-탕정#2T/L GIS 정밀점검","○ 154kV 인주-탕정#2T/L GIS 정밀점검 ○ 병행) 탕정S/S 154kV 인주-탕정#2T/L GIS 정밀점검 ○ 병행) 양 변전소 LA 보통 점검","2016-11-08 15:00","2016-11-09 18:00","2016-11-08T15:00:00","2016-11-09T18:00:00","연속",null,null,null,201609120113,"-"]
[262,"대전충남","아산","인주탕정#2 T/L","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L, 345kV 아산-화성T/L 병가구간 가선작업 신설18호~기설28호 구간 전선 가선작업 기설18호~기설28호 구간 전선 철거작업 발받침 철탑 4기 및 보호망 2개소 설치(154kV 인주-탕정T/L 31~32호)","2016-11-19 07:00","2016-11-20 19:00","2016-11-19T07:00:00","2016-11-20T19:00:00","매일",null,null,null,201609070110,"-"]
[263,"대전충남","아산","인주탕정#1 T/L","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L, 345kV 아산-화성T/L 병가구간 가선작업 신설18호~기설28호 구간 전선 가선작업 기설18호~기설28호 구간 전선 철거작업 발받침 철탑 4기 및 보호망 2개소 설치(154kV 인주-탕정T/L 31~32호)","2016-11-19 07:00","2016-11-20 19:00","2016-11-19T07:00:00","2016-11-20T19:00:00","매일",null,null,null,201609070100,"-"]
[264,"대전충남","아산","인주탕정#2 T/L","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L, 345kV 아산-화성T/L 병가구간 가선작업 신설18호~기설28호 구간 전선 가선작업 기설18호~기설28호 구간 전선 철거작업 발받침 철탑 4기 및 보호망 2개소 설치(154kV 인주-탕정T/L 31~32호)","2016-11-26 07:00","2016-11-27 19:00","2016-11-26T07:00:00","2016-11-27T19:00:00","매일",null,null,null,201609070111,"-"]
[265,"대전충남","아산","인주탕정#1 T/L","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L, 345kV 아산-화성T/L 병가구간 가선작업 신설18호~기설28호 구간 전선 가선작업 기설18호~기설28호 구간 전선 철거작업 발받침 철탑 4기 및 보호망 2개소 설치(154kV 인주-탕정T/L 31~32호)","2016-11-26 07:00","2016-11-27 19:00","2016-11-26T07:00:00","2016-11-27T19:00:00","매일",null,null,null,201609070101,"-"]
[266,"대전충남","아산","인주S/S 154kV #2 BUS","인주S/S 154kV 아산-인주#2T/L GIS 정밀점검","○ 154kV 아산-인주#2T/L GIS 정밀점검 ○ 병행) 154kV 아산-인주#2T/L LA, CVT 보통점검","2016-11-04 09:00","2016-11-05 15:00","2016-11-04T09:00:00","2016-11-05T15:00:00","연속",null,null,null,201609120115,"-"]
[267,"대전충남","아산","인주S/S 154kV #1 BUS","인주S/S 154kV 아산-인주#2T/L GIS 정밀점검","○ 154kV 아산-인주#2T/L GIS 정밀점검 ○ 병행) 154kV 아산-인주#2T/L LA, CVT 보통점검","2016-11-05 15:00","2016-11-06 18:00","2016-11-05T15:00:00","2016-11-06T18:00:00","연속",null,null,null,201609120117,"-"]
[268,"대전충남","아산","인주S/S 154kV #2 BUS","인주S/S 154kV 인주-탕정#2T/L GIS 정밀점검","○ 154kV 인주-탕정#2T/L GIS 정밀점검 ○ 병행) 탕정S/S 154kV 인주-탕정#2T/L GIS 정밀점검 ○ 병행) 양 변전소 LA 보통 점검","2016-11-07 09:00","2016-11-08 15:00","2016-11-07T09:00:00","2016-11-08T15:00:00","연속",null,null,null,201609120110,"-"]
[269,"대전충남","아산","인주탕정#2 T/L","인주S/S 154kV 인주-탕정#2T/L GIS 정밀점검","○ 154kV 인주-탕정#2T/L GIS 정밀점검 ○ 병행) 탕정S/S 154kV 인주-탕정#2T/L GIS 정밀점검 ○ 병행) 양 변전소 LA 보통 점검","2016-11-07 09:00","2016-11-09 18:00","2016-11-07T09:00:00","2016-11-09T18:00:00","연속",null,null,null,201609120046,"-"]
[270,"대전충남","아산","인주탕정#1 T/L","인주S/S 154kV 인주-탕정#1T/L GIS 정밀점검","○ 154kV 인주-탕정#1T/L GIS 정밀점검 ○ 병행) 탕정S/S 154kV 인주-탕정#1T/L GIS 정밀점검 ○ 병행) 양 변전소 LA 보통 점검","2016-11-01 09:00","2016-11-03 18:00","2016-11-01T09:00:00","2016-11-03T18:00:00","연속",null,null,null,201609120044,"-"]
[271,"대전충남","아산","인주S/S 154kV #2 BUS","인주S/S 154kV 인주-탕정#1T/L GIS 정밀점검","○ 154kV 인주-탕정#1T/L GIS 정밀점검 ○ 병행) 탕정S/S 154kV 인주-탕정#1T/L GIS 정밀점검 ○ 병행) 양 변전소 LA 보통 점검","2016-11-01 09:00","2016-11-02 15:00","2016-11-01T09:00:00","2016-11-02T15:00:00","연속",null,null,null,201609120100,"-"]
[272,"대전충남","아산","인주S/S 154kV #1 BUS","인주S/S 154kV 인주-탕정#1T/L GIS 정밀점검","○ 154kV 인주-탕정#1T/L GIS 정밀점검 ○ 병행) 탕정S/S 154kV 인주-탕정#1T/L GIS 정밀점검 ○ 병행) 양 변전소 LA 보통 점검","2016-11-02 15:00","2016-11-03 18:00","2016-11-02T15:00:00","2016-11-03T18:00:00","연속",null,null,null,201609120103,"-"]
[273,"대전충남","아산","인주탕정#2 T/L","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L, 345kV 아산-화성T/L 병가구간 가선작업 신설18호~기설28호 구간 전선 가선작업 기설18호~기설28호 구간 전선 철거작업 발받침 철탑 4기 및 보호망 2개소 설치(154kV 인주-탕정T/L 31~32호)","2016-11-13 07:00","2016-11-13 19:00","2016-11-13T07:00:00","2016-11-13T19:00:00","매일",null,null,null,201609070108,"-"]
[274,"대전충남","아산","인주탕정#1 T/L","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L, 345kV 아산-화성T/L 병가구간 가선작업 신설18호~기설28호 구간 전선 가선작업 기설18호~기설28호 구간 전선 철거작업 발받침 철탑 4기 및 보호망 2개소 설치(154kV 인주-탕정T/L 31~32호)","2016-11-13 07:00","2016-11-13 19:00","2016-11-13T07:00:00","2016-11-13T19:00:00","매일",null,null,null,201609070097,"-"]
[275,"대전충남","청양","관창보령화력 T/L","154kV 보관T/L 안전이격확보공사","작업구간 : No.15~21 작업내용 - 15~19호 전력선 신설, 19~21(상단) 전력선 교체","2016-11-19 07:00","2016-11-25 18:00","2016-11-19T07:00:00","2016-11-25T18:00:00","연속",null,null,null,201608110044,"-"]
[276,"대전충남","청양","동군산장항#2 T/L","장항S/S 154kV 동군산-장항#2T/L 노후불량 공기압력계 교체","장항S/S 154kV 동군산-장항#2T/L 노후불량 공기압력계 교체","2016-11-08 09:00","2016-11-08 18:00","2016-11-08T09:00:00","2016-11-08T18:00:00","당일",null,null,null,201609120150,"-"]
[277,"대전충남","청양","청양신풍#2 T/L","154kV 청양-신풍#2T/L 정밀점검","154kV 청양-신풍#2T/L 정밀점검","2016-11-08 08:00","2016-11-10 18:00","2016-11-08T08:00:00","2016-11-10T18:00:00","매일",null,null,null,201609070140,"-"]
[278,"전북","군산","군산복합S/Y S/T T/L CB","군산복합S/Y S/TG GIS 정밀점검공사","○ S/TG(6133) Bay 정밀점검(차단부 GAS 누기)","2016-11-02 09:00","2016-11-04 18:00","2016-11-02 09:00","2016-11-04 18:00","연속",null,null,null,"-","-"]
[279,"전북","군산","군공군산CC#1 T/L","154kV 군공-군산복합T/L 지장 지중선로 이설공사","군장(동백)대교 건설관련 지장물 이설","2016-11-01 08:00","2016-11-22 18:00","2016-11-01 08:00","2016-11-22 18:00","연속",null,null,null,"-","-"]
[280,"전북","군산","군공군산CC#2 T/L","154kV 군공-군산복합 지장 지중선로 이설공사","군장대교 건설관련 지장 송전설로 이설","2016-11-23 08:00","2016-12-12 18:00","2016-11-23 08:00","2016-12-12 18:00","연속",null,null,null,"-","-"]
[281,"전북","군산","서군산소룡#1 T/L","서군산소룡T/L 정밀점검공사","정밀점검 : 16기","2016-11-28 09:00","2016-11-28 18:00","2016-11-28 09:00","2016-11-28 18:00","당일",null,null,null,"-","-"]
[282,"전북","군산","서군산소룡#2 T/L","서군산소룡T/L 정밀점검공사","정밀점검 : 16기","2016-11-29 09:00","2016-11-29 18:00","2016-11-29 09:00","2016-11-29 18:00","당일",null,null,null,"-","-"]
[283,"전북","군산","이리백산#1 T/L","154kV 이리-백산T/L 선종교체공사","선종 교체 : No.8~No.35호간 HSTACIR/AW 240㎟ (19.22 C-km) 철탑 신설·철거 : 설치 6기, 철거 5기 (No.11,19,25,28.1,32,33)","2016-11-17 07:00","2016-11-26 18:00","2016-11-07 07:00","2016-11-16 18:00","연속",null,null,null,"-","-"]
[284,"전북","군산","군산이리#2 T/L","154kV 군산-이리#2T/L","임시선로 구성","2016-11-07 08:00","2016-11-09 18:00","2016-11-07 08:00","2016-11-09 18:00","연속",null,null,null,"-","-"]
[285,"전북","군산","군산이리#1 T/L","154kV 군산-이리#1T/L","26호 C/H 조립, 가선, 기설 26호 철거","2016-11-10 08:00","2016-11-16 18:00","2016-11-10 08:00","2016-11-16 18:00","연속",null,null,null,"-","-"]
[286,"전북","군산","군산이리#2 T/L","154kV 군산-이리#2T/L","26호 C/H 가선","2016-11-17 08:00","2016-11-18 18:00","2016-11-17 08:00","2016-11-18 18:00","연속",null,null,null,"-","-"]
[287,"전북","군산","이리백산#2 T/L","154kV 이리-백산T/L 선종교체공사","선종 교체 : No.8~No.35호간 HSTACIR/AW 240㎟ (19.22 C-km) 철탑 신설·철거 : 설치 6기, 철거 5기 (No.11,19,25,28.1,32,33)","2016-11-02 07:00","2016-11-16 18:00","2016-10-23 07:00","2016-11-06 18:00","연속",null,null,null,"-","-"]
[288,"전북","군산","팔봉두마#2 T/L","154kV 팔봉-두마T/L 안전이격확보공사","- 신설 철탑조립(27~30호) 및 전력선공중이동 - 28호 인클로징 철탑교체 시행","2016-11-07 07:00","2016-11-11 18:00","2016-11-07 07:00","2016-11-11 18:00","연속",null,null,null,"-","-"]
[289,"전북","군산","팔봉두마#1 T/L","154kV 팔봉-두마T/L 안전이격확보공사","- 신설 철탑조립(27~30호) 및 전력선공중이동 - 28호 인클로징 철탑교체 시행","2016-11-07 07:00","2016-11-11 18:00","2016-11-07 07:00","2016-11-11 18:00","연속",null,null,null,"-","-"]
[290,"전북","군산","이리전주#1 T/L","154kV 이리-전주#1T/L","C/H 플랫폼 조립관련 안전확보차","2016-11-19 09:00","2016-11-22 18:00","2016-11-19 09:00","2016-11-22 18:00","연속",null,null,null,"-","-"]
[291,"전북","군산","군산영등#2 T/L","군산이리#2 T/L 피뢰기설치공사 군산영등#2 T/L 안전이격확보","- 군산영등#2 T/L 안전이격확보","2016-11-07 09:00","2016-11-07 18:00","2016-11-07 09:00","2016-11-07 18:00","당일",null,null,null,"-","-"]
[292,"전북","김제","정주고창#2 T/L","154kV 정주-고창#2T/L 정밀점검","154kV 정주-고창#1T/L 정밀점검 (81~95호)","2016-11-16 09:00","2016-11-18 18:00","2016-11-16 09:00","2016-11-18 18:00","매일",null,null,null,"-","-"]
[293,"전북","김제","정주고창#1 T/L","154kV 정주-고창#1T/L 정밀점검","154kV 정주-고창#1T/L 정밀점검 (81~95호)","2016-11-06 09:00","2016-11-08 18:00","2016-11-06 09:00","2016-11-08 18:00","매일",null,null,null,"-","-"]
[294,"전북","김제","고창영광 T/L","154kV 고창-영광T/L 전선교체 등 2개 공사","전선교체 : 61~108호 10.627C-km 피뢰기 설치 : 46~155호 110기 330set","2016-11-16 07:00","2016-12-06 18:00","2016-11-16 07:00","2016-12-06 18:00","연속",null,null,null,"-","-"]
[295,"전북","김제","백산김제#2 T/L","154kV 백산-김제#2T/L 정밀점검","154kV 백산-김제#2T/L 1~15호 정밀점검","2016-11-17 09:00","2016-11-22 18:00","2016-11-07 09:00","2016-11-12 18:00","매일",null,null,null,"-","-"]
[296,"전북","김제","백산김제#1 T/L","154kV 이리-백산T/L 선종교체공사","병가선로 작업자 안전확보 휴전(백산-김제#1) -선종 교체 : 이리-백산T/L No.8~No.35호간 HSTACIR/AW 240㎟ (19.22 C-km) -철탑 신설·철거 : 설치 6기, 철거 5기 (No.11,19,25,28.1,32,33)","2016-11-23 08:00","2016-11-26 18:00","2016-11-13 08:00","2016-11-16 18:00","연속",null,null,null,"-","-"]
[297,"전북","김제","백산김제#1 T/L","154kV 이리-백산T/L 선종교체공사","병가선로 작업자 안전확보 휴전(백산-김제#1) -선종 교체 : 이리-백산T/L No.8~No.35호간 HSTACIR/AW 240㎟ (19.22 C-km) -철탑 신설·철거 : 설치 6기, 철거 5기 (No.11,19,25,28.1,32,33)","2016-11-13 08:00","2016-11-16 18:00","2016-11-03 08:00","2016-11-06 18:00","연속",null,null,null,"-","-"]
[298,"전북","김제","정공섬진강수력 T/L","정공섬진강수력 T/L","전담운영 대비 SCADA 제어회로 구성","2016-11-21 09:00","2016-11-26 18:00","2016-11-21 09:00","2016-11-26 18:00","연속",null,null,null,"○","○"]
[299,"전북","김제","김제섬진강HP T/L","김제섬진강HP T/L","전담운영 대비 SCADA 제어회로 구성","2016-11-28 09:00","2016-12-03 18:00","2016-11-28 09:00","2016-12-03 18:00","연속",null,null,null,"-","-"]
[300,"전북","김제","김제섬진강HP T/L","김제섬진강HP T/L","#1 BUS 시험가압","2016-11-01 13:00","2016-11-01 15:00","2016-11-01 13:00","2016-11-01 15:00","당일",null,null,null,"-","-"]
[301,"전북","김제","김제섬진강HP T/L","김제섬진강HP T/L","#2 BUS 시험가압","2016-11-02 15:00","2016-11-02 17:00","2016-11-02 15:00","2016-11-02 17:00","당일",null,null,null,"-","-"]
[302,"전북","김제","신김제S/S #61D.Tr CB","신김제S/S #61D.Tr A","ESS 관련 변전설비 초기점검","2016-11-14 09:00","2016-11-24 18:00","2016-11-14 09:00","2016-11-24 18:00","연속",null,null,null,"-","-"]
[303,"전북","김제","신김제전주#1 T/L","신김제-전주#1T/L","신김제S/S 신김제-전주#1T/L GIS정밀점검","2016-11-03 09:00","2016-11-05 18:00","2016-11-03 09:00","2016-11-05 18:00","연속",null,null,null,"-","-"]
[304,"전북","김제","정공담양 T/L","정공담양 T/L","노후 배전반 교체","2016-11-28 09:00","2016-12-01 18:00","2016-11-11 09:00","2016-11-15 18:00","연속",null,null,null,"-","-"]
[305,"전북","직할","신김제동전주#1 T/L","154kV 신김제-동전주#1T/L 점퍼지지애자 교체공사","96년 이전 점퍼지지애자 교체 298개","2016-11-23 07:30","2016-11-24 18:00","2016-11-23 07:30","2016-11-24 18:00","매일",null,null,null,"-","-"]
[306,"전북","직할","무주용담수력 T/L","154kV 금산무주T/L 전선접속개소 전력선 교체공사","금산-무주#2T/L 전선접속개소 전력선 교체관련 안전이격확보","2016-11-07 07:00","2016-11-16 18:00","2016-11-07 12:00","2016-11-16 18:00","매일",null,null,null,"-","-"]
[307,"전북","직할","북전주봉동#1 T/L","154kV 북전주-봉동T/L 정밀점검","내용 : 정밀점검 구간 : 1~9호","2016-11-01 09:00","2016-11-01 18:00","2016-11-05 09:00","2016-11-05 18:00","당일",null,null,null,"-","-"]
[308,"광주전남","강진","진도C/S #2Pole C.Tr CB","'16~'17년 #2HVDC 변환설비 위탁정비공사","#2HVDC 변환설비 연차점검","2016-11-04 09:00","2016-11-15 18:00","2016-11-04 09:00","2016-11-15 18:00","연속",null,null,null,"-","-"]
[309,"광주전남","강진","진도진도CS#1 T/L","진도-진도CS#1 T/L(송전선로 보호반 대체공사)","강진전력지사 변전협력회사 총액공사 - 진도-진도C/S#1T/L 송전선로 보호반 대체","2016-11-07 09:00","2016-11-10 18:00","2016-11-07 09:00","2016-11-10 18:00","연속",null,null,null,"-","-"]
[310,"광주전남","광주","계림승주#2(서남권상수도T분기) T/L","154kV 계림-승주T/L 지상고확보공사","철탑교체 14기 전선교체 4.656km","2016-11-08 07:00","2016-11-10 18:00","2016-11-08 07:00","2016-11-10 18:00","연속",null,null,null,"-","-"]
[311,"광주전남","광주","계림승주#1(서남권상수도T분기) T/L","154kV 계림-승주T/L 지상고확보공사","철탑교체 14기 전선교체 4.656km","2016-11-11 07:00","2016-11-24 18:00","2016-11-11 07:00","2016-11-24 18:00","연속",null,null,null,"-","-"]
[312,"광주전남","광주","계림승주#2(서남권상수도T분기) T/L","154kV 계림-승주T/L 지상고확보공사","철탑교체 14기 전선교체 4.656km","2016-11-25 07:00","2016-11-30 18:00","2016-11-25 07:00","2016-11-30 18:00","연속",null,null,null,"-","-"]
[313,"광주전남","광주","담양일곡#2 T/L","담양-일곡#2T/L 보호배전반 교체","담양-일곡#2T/L 보호배전반 교체","2016-11-14 09:00","2016-11-16 18:00","2016-11-18 09:00","2016-11-20 18:00","연속",null,null,null,"-","-"]
[314,"광주전남","광주","담양일곡#1 T/L","담양-일곡#1T/L 보호배전반 교체","담양-일곡#1T/L 보호배전반 교체","2016-11-07 09:00","2016-11-09 18:00","2016-11-21 09:00","2016-11-23 18:00","연속",null,null,null,"-","-"]
[315,"광주전남","광주","신광주일곡#1 T/L","154kV 신광주-일곡#1 T/L 안전거리확보(피뢰기설치)","일곡-비아 #1T/L 피뢰기설치공사","2016-11-01 08:00","2016-11-01 18:00","2016-11-09 08:00","2016-11-09 18:00","당일",null,null,null,"-","-"]
[316,"광주전남","순천","광양하동#2 T/L","154kV 광양-하동#2T/L(노후전력선 및 철탑 교체)","노후전력선 교체 : 37 ~92호 철탑교체 : 59,61,77,81호(4기)","2016-11-12 07:00","2016-11-14 18:00","2016-11-12 07:00","2016-11-14 18:00","연속",null,null,null,"-","-"]
[317,"광주전남","순천","광양하동#1 T/L","154kV 광양-하동#1T/L(노후전력선 및 철탑 교체)","노후전력선 교체 : 37 ~92호 철탑교체 : 59,61,77,81호(4기)","2016-11-09 07:00","2016-11-11 18:00","2016-11-09 07:00","2016-11-11 18:00","연속",null,null,null,"-","-"]
[318,"광주전남","순천","광양순천#2 T/L","154kV 광양-순천T/L C/H설치공사","C/H 1기 설치","2016-11-28 09:00","2016-12-01 18:00","2016-11-28 09:00","2016-12-01 18:00","연속",null,null,null,"-","-"]
[319,"광주전남","순천","서순천주암HP T/L","154kV 서순천-주암HP T/L(철탑 지상고 상향)","철탑 지상고 상향 : 22,23,24호(3기)","2016-11-21 07:00","2016-11-25 18:00","2016-11-21 07:00","2016-11-25 18:00","연속",null,null,null,"-","-"]
[320,"광주전남","순천","승주주암HP T/L","154kV 승주-주암HP T/L(점퍼지지애자 교체)","점퍼지지애자 교체 : 43,44,50호(3기)","2016-11-28 07:00","2016-11-28 18:00","2016-11-28 07:00","2016-11-28 18:00","당일",null,null,null,"-","-"]
[321,"광주전남","순천","여수T/P 154kV #60 BUS","여수T/P 154kV #60BUS(#1BUS-TIE GIS 정밀점검)","2016년 순천전력지사 하반기 GIS 정밀점검공사 - 154kV #1BUS-TIE GIS 정밀점검","2016-11-02 09:00","2016-11-03 13:00","2016-11-02 09:00","2016-11-03 13:00","연속",null,null,null,"-","-"]
[322,"광주전남","순천","여수T/P 154kV #1 BUS TIE GIS","여수T/P 154kV #1BUS-TIE(GIS 정밀점검공사)","2016년 순천전력지사 하반기 GIS 정밀점검공사 - 154kV #1BUS-TIE GIS 정밀점검","2016-11-02 09:00","2016-11-04 18:00","2016-11-02 09:00","2016-11-04 18:00","연속",null,null,null,"-","-"]
[323,"광주전남","순천","여수T/P 154kV #65 BUS","여수T/P 154kV #65BUS(#1BUS-TIE GIS 정밀점검)","2016년 순천전력지사 하반기 GIS 정밀점검공사 - 154kV #1BUS-TIE GIS 정밀점검","2016-11-03 13:00","2016-11-04 18:00","2016-11-03 13:00","2016-11-04 18:00","연속",null,null,null,"-","-"]
[324,"광주전남","순천","여수T/P 154kV #2 BUS TIE GIS","여수T/P 154kV #2BUS-TIE(GIS 정밀점검공사)","2016년 순천전력지사 하반기 GIS 정밀점검공사 - 154kV #2BUS-TIE GIS 정밀점검","2016-11-07 09:00","2016-11-09 18:00","2016-11-07 09:00","2016-11-09 18:00","연속",null,null,null,"-","-"]
[325,"광주전남","순천","여수T/P 154kV #61 BUS","여수T/P 154kV #61BUS(#2BUS-TIE GIS 정밀점검)","2016년 순천전력지사 하반기 GIS 정밀점검공사 - 154kV #2BUS-TIE GIS 정밀점검","2016-11-07 09:00","2016-11-08 13:00","2016-11-07 09:00","2016-11-08 13:00","연속",null,null,null,"-","-"]
[326,"광주전남","순천","여수T/P 154kV #66 BUS","여수T/P 154kV #66BUS(#2BUS-TIE GIS 정밀점검)","2016년 순천전력지사 하반기 GIS 정밀점검공사 - 154kV #2BUS-TIE GIS 정밀점검","2016-11-08 13:00","2016-11-09 18:00","2016-11-08 13:00","2016-11-09 18:00","연속",null,null,null,"-","-"]
[327,"광주전남","순천","여수T/P 154kV #66 BUS","345kV 여수T/P #66BUS(#2M.Tr 2차 GIS 정밀점검)","2016년 순천전력지사 하반기 GIS 정밀점검공사 - #2M.Tr 2차 GIS 정밀점검","2016-11-25 13:00","2016-11-26 18:00","2016-11-25 13:00","2016-11-26 18:00","연속",null,null,null,"-","-"]
[328,"광주전남","순천","여수T/P 154kV #61 BUS","345kV 여수T/P #61BUS(#2M.Tr 2차 GIS 정밀점검)","2016년 순천전력지사 하반기 GIS 정밀점검공사 - #2M.Tr 2차 GIS 정밀점검","2016-11-24 09:00","2016-11-25 13:00","2016-11-24 09:00","2016-11-25 13:00","연속",null,null,null,"-","-"]
[329,"광주전남","순천","여수T/P 154kV #65 BUS","여수T/P 154kV #65BUS(#1M.Tr 2차 GIS 정밀점검)","2016년 순천전력지사 하반기 GIS 정밀점검공사 - #1M.Tr 2차 GIS 정밀점검","2016-11-22 13:00","2016-11-23 18:00","2016-11-22 13:00","2016-11-23 18:00","연속",null,null,null,"-","-"]
[330,"광주전남","순천","여수T/P 154kV #60 BUS","여수T/P 154kV #60BUS(#1M.Tr 2차 GIS 정밀점검)","2016년 순천전력지사 하반기 GIS 정밀점검공사 - #1M.Tr 2차 GIS 정밀점검","2016-11-21 09:00","2016-11-22 13:00","2016-11-21 09:00","2016-11-22 13:00","연속",null,null,null,"-","-"]
[331,"광주전남","순천","여수T/P 154kV #66 BUS","여수T/P 154kV #66BUS(#65-66SEC GIS 정밀점검)","2016년 순천전력지사 하반기 GIS 정밀점검공사 - 154kV #65-66SEC GIS 정밀점검","2016-11-15 13:00","2016-11-16 18:00","2016-11-15 13:00","2016-11-16 18:00","연속",null,null,null,"-","-"]
[332,"광주전남","순천","여수T/P 65-66 SEC GIS","여수T/P 154kV #65-66SEC(GIS 정밀점검공사)","2016년 순천전력지사 하반기 GIS 정밀점검공사 - 154kV #65-66SEC GIS 정밀점검","2016-11-14 09:00","2016-11-16 18:00","2016-11-14 09:00","2016-11-16 18:00","연속",null,null,null,"-","-"]
[333,"광주전남","순천","여수T/P 154kV #65 BUS","여수T/P 154kV #65BUS(#65-66SEC GIS 정밀점검)","2016년 순천전력지사 하반기 GIS 정밀점검공사 - 154kV #65-66SEC GIS 정밀점검","2016-11-14 09:00","2016-11-15 13:00","2016-11-14 09:00","2016-11-15 13:00","연속",null,null,null,"-","-"]
[334,"광주전남","순천","여수T/P 154kV #61 BUS","여수T/P 154kV #61BUS(#60-61SEC GIS 정밀점검)","2016년 순천전력지사 하반기 GIS 정밀점검공사 - 154kV #60-61SEC GIS 정밀점검","2016-11-11 13:00","2016-11-12 18:00","2016-11-11 13:00","2016-11-12 18:00","연속",null,null,null,"-","-"]
[335,"광주전남","순천","여수T/P 60-61 SEC GIS","여수T/P 154kV #60-61SEC(GIS 정밀점검공사)","2016년 순천전력지사 하반기 GIS 정밀점검공사 - 154kV #60-61SEC GIS 정밀점검","2016-11-10 09:00","2016-11-12 18:00","2016-11-10 09:00","2016-11-12 18:00","연속",null,null,null,"-","-"]
[336,"광주전남","순천","여수T/P 154kV #60 BUS","여수T/P 154kV #60BUS(#60-61SEC GIS 정밀점검)","2016년 순천전력지사 하반기 GIS 정밀점검공사 - 154kV #60-61SEC GIS 정밀점검","2016-11-10 09:00","2016-11-11 13:00","2016-11-10 09:00","2016-11-11 13:00","연속",null,null,null,"-","-"]
[337,"광주전남","순천","여수TP여천#2 T/L","154kV 여천S/S 여수TP-여천#2T/L(LA 하자점검)","2016년 순천전력지사 변전협력회사 총액공사 - 여천S/S 여수TP-여천#2T/L LA 하자점검","2016-11-01 10:00","2016-11-01 18:00","2016-11-01 10:00","2016-11-01 18:00","당일",null,null,null,"-","-"]
[338,"광주전남","순천","여천여수#2 T/L","154kV 여천S/S 여천-여수#2T/L(LA 하자점검)","2016년 순천전력지사 변전협력회사 총액공사 - 여천S/S 여천-여수#2T/L LA 하자점검","2016-11-02 10:00","2016-11-02 18:00","2016-11-02 10:00","2016-11-02 18:00","당일",null,null,null,"-","-"]
[339,"광주전남","순천","용성여수산단#1 T/L","154kV 용성-여수산단#1T/L(송전선로 보호배전반 교체)","2016년 순천전력지사 변전협력회사 총액공사 - 용성-여수산단#1T/L 송전선로 보호배전반 교체","2016-11-14 10:00","2016-11-16 18:00","2016-11-14 10:00","2016-11-16 18:00","연속",null,null,null,"-","-"]
[340,"광주전남","순천","용성여수산단#2 T/L","용성S/S 154kV 롯데케미칼T/L 신규수용공사","가. GIS 챔버 분리(안전이격거리확보)","2016-11-15 09:00","2016-11-15 18:00","2016-11-15 09:00","2016-11-15 18:00","당일",null,null,null,"-","-"]
[341,"광주전남","순천","용성여수산단#2 T/L","154kV 용성-여수산단#2T/L(송전선로 보호배전반 교체)","2016년 순천전력지사 변전협력회사 총액공사 - 용성-여수산단#2T/L 송전선로 보호배전반 교체","2016-11-21 10:00","2016-11-23 18:00","2016-11-21 10:00","2016-11-23 18:00","연속",null,null,null,"-","-"]
[342,"광주전남","순천","용성여수산단#2 T/L","용성S/S 154kV 롯데케미칼T/L 신규수용공사","가. GIS 챔버 설치(안전이격거리확보)","2016-11-22 09:00","2016-11-22 18:00","2016-11-22 09:00","2016-11-22 18:00","당일",null,null,null,"-","-"]
[343,"광주전남","순천","용성여수산단#2 T/L","용성S/S 154kV 롯데케미칼T/L 신규수용공사","가. 무부하 가압(GIS ~ 케이블 ~ 롯데케미칼)","2016-11-25 17:00","2016-11-28 10:00","2016-11-25 17:00","2016-11-28 10:00","연속",null,null,null,"-","-"]
[344,"광주전남","직할","신화순평동 T/L CB","154kV 신화순-나주T/L No.43-48호 지장철탑 이설공사","송현-남평간 지방도 확포장 공사에 지장이 되는 154kV 신화순-나주T/L No.43-48호간 지장철탑 이설공사","2016-11-11 08:00","2016-11-17 18:00","2016-11-11 08:00","2016-11-17 18:00","연속",null,null,null,"-","-"]
[345,"광주전남","직할","신화순평동 T/L CB","154kV 신화순-나주T/L No.43-48호 지장철탑 이설공사","송현-남평간 지방도 확포장 공사에 지장이 되는 154kV 신화순-나주T/L No.43-48호간 지장철탑 이설공사","2016-11-01 08:00","2016-11-03 18:00","2016-11-01 08:00","2016-11-03 18:00","연속",null,null,null,"-","-"]
[346,"대구경북","경산","대구범물#2 T/L","2016년 직할 가공송전 순시점검 위탁공사","대구자인#1 정밀점검(No.1~55)간 안전확보","2016-11-14 08:00","2016-11-14 18:00","2016-11-14 08:00","2016-11-14 18:00","당일",null,null,null,201609080040,"-"]
[347,"대구경북","경산","대구범물#1 T/L","2016년 직할 가공송전 순시점검 위탁공사","대구자인#2 정밀점검(No.1~55)간 안전확보","2016-11-08 08:00","2016-11-08 18:00","2016-11-08 08:00","2016-11-08 18:00","당일",null,null,null,201609080037,"-"]
[348,"대구경북","경산","신경산진량 T/L","신경산S/S 170kV 장기사용 GIS 대체공사","1.신경산-진량T/L GIS 대체시 진량S/S 장기간 RADIAL 운전관련 계통보강사전작업 2. 신경산-진량T/L GIS 대체","2016-11-21 09:00","2016-11-23 18:00","2016-11-21 09:00","2016-11-23 18:00","연속",null,null,null,201609170012,"-"]
[349,"대구경북","경산","신경산노변 T/L","신경산S/S 170kV 장기사용 GIS 대체공사","신경산-진량T/L GIS 대체시 진량S/S 장기간 RADIAL 운전관련 계통보강 사전작업","2016-11-21 09:00","2016-12-09 18:00","2016-11-21 09:00","2016-12-09 18:00","연속",null,null,null,201609170011,"-"]
[350,"대구경북","구미","남인동인동#1 T/L","154kV 청리-상주 등 6개T/L 송전선로용 피뢰기 설치공사","○ 154kV 송전선로용 피뢰기 설치공사 - 154kV 남인동-인동T/L 49기(147 Set) 송전용 피뢰기 설치 - 154kV 금전-인동T/L 피뢰기 설치시 안전확보도 병행 (일부구간 금전인동T/L : 상단, 남인동인동T/L : 하단)","2016-11-10 08:00","2016-11-12 18:00","2016-11-10 08:00","2016-11-12 18:00","매일",null,null,null,201609080006,"-"]
[351,"대구경북","구미","상주영동 T/L","154kV 청리-상주 등 6개T/L 송전선로용 피뢰기 설치공사","○ 154kV 송전선로용 피뢰기 설치공사 - 154kV 청리-상주T/L 34기(102 Set) 송전용 피뢰기 설치시 안전확보 (일부구간 청리상주T/L : 상단, 상주영동T/L : 하단) ※ 154kV 청리상주T/L 노후취약지지물 교체공사(감독 : 구미전력지사 송전팀 장희규)에 대한 병행작업으로 안전확보를 위한 선로(상주-영동)만 휴전","2016-11-24 08:00","2016-11-24 18:00","2016-11-24 08:00","2016-11-24 18:00","당일",null,null,null,201609080009,"-"]
[352,"대구경북","구미","청리상주#1 T/L","154kV 청리-상주T/L 노후취약지지물 교체","사업개요 o 선종 : 330S*2C*0.8km o 철탑 : 3기 신설, 3기 철거 o 전선 : 청리-상주T/L No.41~45 교체","2016-11-21 09:00","2016-12-10 18:00","2016-11-21 09:00","2016-12-10 18:00","연속",null,null,null,201607110310,"-"]
[353,"대구경북","구미","청리상주#2 T/L","154kV 청리-상주T/L 노후취약지지물 교체","사업개요 o 선종 : 330S*2C*0.8km o 철탑 : 3기 신설, 3기 철거 o 전선 : 청리-상주T/L No.41~45 교체","2016-11-21 09:00","2016-12-10 18:00","2016-11-21 09:00","2016-12-10 18:00","연속",null,null,null,201607110315,"-"]
[354,"대구경북","달성","강창성서#2 T/L","송전선로 정밀점검","No.1-14 송전선로 정밀점검(14기)","2016-11-12 09:00","2016-11-13 18:00","취소","취소","연속",null,null,null,201609130142,"-"]
[355,"대구경북","달성","다산강창#1 T/L","안전확보 휴전","강창-성서#1(하단) No.1-4 송전선로 정밀점검시 다산-강창#2(상단) 안전확보 휴전","2016-11-20 08:30","2016-11-20 18:00","2016-11-20 08:30","2016-11-20 18:00","당일",null,null,null,201609130145,"-"]
[356,"대구경북","달성","강창성서#1 T/L","송전선로 피뢰기 설치 및 정밀점검","No.1-14 송전선로용 피뢰기 설치(12기) No.1-14 송전선로 정밀점검(14기)","2016-11-19 09:00","2016-11-20 18:00","2016-11-20 09:00","2016-11-20 18:00","연속",null,null,null,201609130130,"-"]
[357,"대구경북","달성","다산강창#2 T/L","안전확보 휴전","강창-성서#2(하단) No.1-4 송전선로 정밀점검시 다산-강창#2(상단) 안전확보 휴전","2016-11-13 08:30","2016-11-13 18:00","2016-11-13 08:30","2016-11-13 18:00","당일",null,null,null,201609130147,"-"]
[358,"대구경북","달성","고령다산#2 T/L","2016 가공송전 협력업체 총액공사","No.1-63 송전선로용 피뢰기 설치(63기)","2016-11-05 09:00","2016-11-13 18:00","2016-11-12 09:00","2016-11-13 18:00","연속",null,null,null,201609130168,"-"]
[359,"대구경북","달성","성서달성#1 T/L","안전확보 휴전","강창-성서#2(상단) No.13 송전선로 정밀점검시 성서-달성#1(하단) 안전확보 휴전","2016-11-12 08:30","2016-11-12 18:30","취소","취소","당일",null,null,null,201609130166,"-"]
[360,"대구경북","달성","성서달성#2 T/L","피뢰기설치 및 안전확보 휴전","11/24-11/25 : 피뢰기 설치 : No.1~20(19기) 11/24 : 안전확보휴전 : 강창-성서#1(상단) 송전선로 정밀점검","2016-11-18 08:30","2016-11-19 18:00","취소","취소","연속",null,null,null,201609130164,"-"]
[361,"대구경북","달성","고령쌍림#1 T/L","안전확보 휴전","고령다산#2 No.1-63 송전선로 피뢰기설치시 고령쌍림#1 안전확보 휴전","2016-11-05 08:30","2016-11-05 18:00","2016-11-12 08:30","2016-11-12 18:00","당일",null,null,null,201609200144,"-"]
[362,"대구경북","안동","신영주안동#2 T/L","154kV 신영주-안동#2T/L 송전선로 피뢰기 설치공사","○ 154kV 신영주-안동#2T/L No.57-97 송전선로 피뢰기 설치공사","2016-11-05 08:00","2016-11-06 18:00","2016-11-05 08:00","2016-11-06 18:00","매일",null,null,null,201609090231,"-"]
[363,"대구경북","안동","동안동임하HP T/L","동안동S/S 모선보호반 교체공사","동안동S/S 모선보호반 교체공사","2016-11-24 10:30","2016-11-24 11:00","2016-11-24 10:30","2016-11-24 11:00","당일",null,null,null,201609090231,"-"]
[364,"대구경북","영주","문경단양 T/L","154kV단양T/L 노후취약 지지물 교체공사","O 154kV단양T/L 노후취약 지지물 교체공사 O 154kV문경분기T/L 송전선로 피뢰기 설치공사","2016-11-26 07:00","2016-11-27 18:00","2016-11-26 07:00","2016-11-27 18:00","연속",null,null,null,201607080224,"-"]
[365,"대구경북","직할","범물남대구#2 T/L","남대구S/S 모선보호반 교체","모선보호반 교체","2016-11-03 07:00","2016-11-03 11:00","취소","취소","당일",null,null,null,201609070189,"-"]
[366,"대구경북","직할","범물남대구#1 T/L","남대구S/S 모선보호반 교체","모선보호반 교체","2016-11-03 11:00","2016-11-03 11:30","취소","취소","당일",null,null,null,201609070190,"-"]
[367,"대구경북","직할","산격침산#2 T/L","산격-침산#2T/L 보호반 교체","보호반 교체","2016-11-09 09:00","2016-11-10 18:00","취소","취소","연속",null,null,null,201609070207,"-"]
[368,"대구경북","직할","산격침산#1 T/L","산격-침산#1T/L 보호반 교체","보호반 교체","2016-11-07 09:00","2016-11-08 18:00","취소","취소","연속",null,null,null,201609070200,"-"]
[369,"대구경북","칠곡","관음구암#1 T/L","2016년 직할 가공송전 협력회사 총액공사","관음-구암#1 피뢰기 설치공사(No.1~45)","2016-11-20 08:00","2016-11-22 18:00","2016-11-20 08:00","2016-11-22 18:00","연속",null,null,null,201609080047,"-"]
[370,"대구경북","칠곡","관음구암#2 T/L","2016년 직할 가공송전 협력회사 총액공사","관음-구암#1 피뢰기 설치공사(No.2~10)간 안전확보","2016-11-20 08:00","2016-11-20 18:00","2016-11-20 08:00","2016-11-20 18:00","당일",null,null,null,201609080048,"-"]
[371,"대구경북","포항","아화건천#1 T/L","2016년 경산전력 가공송전 협력회사 총액공사","철탑피뢰기 설치[No.1~48]","2016-11-16 07:30","2016-11-19 18:00","2016-11-16 07:30","2016-11-19 18:00","연속",null,null,null,201609200101,"-"]
[372,"대구경북","포항","건천천북#2 T/L","2016년 경산전력 가공송전 협력회사 총액공사","철탑피뢰기 설치[No.1~20]","2016-11-26 07:30","2016-11-29 18:00","2016-11-26 07:30","2016-11-29 18:00","연속",null,null,null,201609200102,"-"]
[373,"대구경북","포항","신포항포항#1 T/L","154kV 신포항포항#1 T/L 피뢰기 설치공사","No.1~10, 12 피뢰기설치","2016-11-14 07:00","2016-11-14 18:00","2016-11-14 07:00","2016-11-14 18:00","당일",null,null,null,201609080254,"-"]
[374,"대구경북","포항","영일입실 T/L","154kV 상정-양북T/L 건설공사","목적 : 포항 블루밸리산업단지 전력수요 대비 및 상정S/S 단일계통 해소 구간 : 기설 154kV 영일-양북T/L No.29,31~기설 154kV 상정S/S 개요 : 철탑 39기, 14.725km","2016-11-21 09:00","2016-12-04 18:00","2016-11-21 09:00","2016-12-04 18:00","연속",null,null,null,201609010051,"-"]
[375,"대구경북","포항","영일양북 T/L","154kV 상정-양북T/L 건설공사","목적 : 포항 블루밸리산업단지 전력수요 대비 및 상정S/S 단일계통 해소 구간 : 기설 154kV 영일-양북T/L No.29,31~기설 154kV 상정S/S 개요 : 철탑 39기, 14.725km","2016-11-21 09:00","2016-12-04 18:00","2016-11-21 09:00","2016-12-04 18:00","연속",null,null,null,201609010050,"-"]
[376,"대구경북","포항","입실양북 T/L","154kV 영일-양북T/L 안전이격거리확보공사","- 154kV 영일-양북T/L 82~87,93호 철탑이설 -345kV 동울산-월성NP 등 2개T/L 계통변경공사 안전확보","2016-11-04 08:00","2016-11-13 18:00","2016-11-04 08:00","2016-11-20 18:00","연속",null,null,null,201609130368,"-"]
[377,"대구경북","포항","영일입실 T/L","154kV 영일-양북T/L 안전이격거리확보공사","- 154kV 영일-양북T/L 82~87,93호 철탑이설 -345kV 동울산-월성NP 등 2개T/L 계통변경공사 안전확보","2016-11-04 08:00","2016-11-13 18:00","2016-11-04 08:00","2016-11-20 18:00","연속",null,null,null,201609130370,"-"]
[378,"부산울산","동부산","노포정관#2 T/L","154kV 노포-정관T/L 지장철탑이설공사","지장철탑이설, 노포-정관T/L 8호, 작업구간 6~9호","2016-11-22 09:00","2016-11-24 18:00","2016-11-22 09:00","2016-11-24 18:00","연속",null,null,null,201609090105,"-"]
[379,"부산울산","동부산","노포정관#1 T/L","154kV 노포-정관T/L 지장철탑이설공사","지장철탑이설, 노포-정관T/L 8호, 작업구간 6~9호","2016-11-25 09:00","2016-12-09 18:00","2016-11-25 09:00","2016-12-09 18:00","연속",null,null,null,201609090106,"-"]
[380,"부산울산","동부산","웅촌서창#2 T/L","154kV 웅촌-서창T/L 지장철탑이설공사","구간:8-12호, 17.1-20호 철탑교체:9,10,11,18호","2016-11-03 09:00","2016-11-06 18:00","2016-11-30 09:00","2016-12-01 18:00","연속",null,null,null,201609080296,"-"]
[381,"부산울산","북부산","김해어방 T/L","2016년 북부산변전협력회사 총액공사","김해S/S 647 GIS 보통점검 및 피뢰기 점검, 어방S/S 617 GIS 보통점검","2016-11-20 09:00","2016-11-20 18:00","2016-11-13 09:00","2016-11-13 18:00","당일",null,null,null,201609120029,"-"]
[382,"부산울산","북부산","매리김해#1 T/L","154kV 삼랑진양수 등 3개T/L 피뢰기 설치공사","매리-김해#2T/L 피뢰기 설치 공사(No.1-50,49기)에 따른 작업자 안전거리확보","2016-11-22 08:00","2016-11-24 18:00","2016-11-21 08:00","2016-11-23 18:00","연속",null,null,null,201609060040,"-"]
[383,"부산울산","북부산","매리호포#2 T/L","154kV 삼랑진양수 등 3개T/L 피뢰기 설치공사","매리-김해#2T/L 피뢰기 설치 공사(No.1-50,49기)에 따른 작업자 안전거리확보","2016-11-21 08:00","2016-11-21 18:00","2016-11-20 08:00","2016-11-20 18:00","당일",null,null,null,201609060042,"-"]
[384,"부산울산","북부산","매리김해#2 T/L","154kV 삼랑진양수 등 3개T/L 피뢰기 설치공사","매리-김해#2T/L 피뢰기 설치 공사(No.1-50,49기)","2016-11-21 08:00","2016-11-25 18:00","2016-11-20 08:00","2016-11-24 18:00","연속",null,null,null,201609060014,"-"]
[385,"부산울산","북부산","삼계S/S 154kV #2 BUS","2016년 북부산 170kV GIS 정밀점검","삼계S/S #2M.Tr 1차6233 GIS 정밀점검(#2DS 및 차단부 점검)","2016-11-07 09:00","2016-11-07 20:00","2016-11-07 11:00","2016-11-07 20:00","당일",null,null,null,201609210004,"-"]
[386,"부산울산","북부산","삼계S/S 154kV #1 BUS","2016년 북부산 170kV GIS 정밀점검","삼계S/S #1M.Tr 1차 6133 GIS 정밀점검(#1DS측 점검)","2016-11-04 09:00","2016-11-04 20:00","2016-11-04 08:00","2016-11-05 11:00","당일",null,null,null,201609210001,"-"]
[387,"부산울산","북부산","주촌삼계#2 T/L","2016년 북부산 170kV GIS 정밀점검","삼계S/S #2M.Tr 1차 6233 GIS 정밀점검(#2DS 및 CB측 시험가압)","2016-11-07 19:00","2016-11-07 20:00","2016-11-07 19:00","2016-11-07 20:00","당일",null,null,null,201609090338,"-"]
[388,"부산울산","북부산","주촌삼계#1 T/L","2016년 북부산 170kV GIS 정밀점검","삼계S/S #2M.Tr 1차 6233 GIS 정밀점검(#1DS측 시험가압)","2016-11-06 19:00","2016-11-06 20:00","2016-11-07 10:00","2016-11-07 11:00","당일",null,null,null,201609090339,"-"]
[389,"부산울산","북부산","삼계S/S 154kV #1 BUS","2016년 북부산 170kV GIS 정밀점검","삼계S/S #2M.Tr 1차 6233 GIS 정밀점검(#1DS측 점검)","2016-11-06 09:00","2016-11-06 20:00","2016-11-06 08:00","2016-11-07 11:00","당일",null,null,null,201609210003,"-"]
[390,"부산울산","북부산","주촌삼계#2 T/L","2016년 북부산 170kV GIS 정밀점검","삼계S/S #1M.Tr 1차 6133 GIS 정밀점검(#2DS 및 CB측 시험가압)","2016-11-05 19:00","2016-11-05 20:00","2016-11-05 19:00","2016-11-05 20:00","당일",null,null,null,201609090340,"-"]
[391,"부산울산","북부산","주촌삼계#1 T/L","2016년 북부산 170kV GIS 정밀점검","삼계S/S #1M.Tr 1차 6133 GIS 정밀점검 (#1DS측 시험가압)","2016-11-04 19:00","2016-11-04 20:00","2016-11-05 10:00","2016-11-05 11:00","당일",null,null,null,201609090337,"-"]
[392,"부산울산","북부산","삼계S/S 154kV #2 BUS","2016년 북부산 170kV GIS 정밀점검","삼계S/S #1M.Tr 1차6133 GIS 정밀점검(#2DS 및 차단부 점검)","2016-11-05 09:00","2016-11-05 20:00","2016-11-05 11:00","2016-11-05 20:00","당일",null,null,null,201609210002,"-"]
[393,"부산울산","북부산","양산산막#1 T/L","16년 가공송전 협력업체 총액공사","양산산막#1 T/L 4호 애자련 교체공사","2016-11-29 07:30","2016-11-29 18:00","2016-11-29 07:30","2016-11-29 18:00","당일",null,null,null,201609020049,"-"]
[394,"부산울산","북부산","엄궁학장#2 T/L","학장S/S 170kV 장기사용 GIS 대체(5차)","학장S/S 엄궁-학장#1T/L 대체(#2DS 및 차단부 시험가압)","2016-11-07 16:00","2016-11-09 18:00","2016-11-07 16:00","2016-11-09 18:00","연속",null,null,null,201609120395,"-"]
[395,"부산울산","서부산","서부산S/S 154kV #65 BUS","서부산S/S 서부산-다대 #2T/L GIS 정밀점검","서부산S/S 서부산-다대 #2T/L GIS 정밀점검 (서부산-다대 #2T/L CB(667) + 2DS(662) 정밀점검)","2016-11-04 08:00","2016-11-05 20:00","2016-11-04 08:00","2016-11-05 20:00","연속",null,null,null,201609070326,"-"]
[396,"부산울산","서부산","서부산S/S 154kV #60 BUS","서부산S/S 서부산-다대 #2T/L GIS 정밀점검","서부산S/S 서부산-다대 #2T/L GIS 정밀점검 (서부산-다대 #2T/L 1DS(661) 정밀점검)","2016-11-03 08:00","2016-11-03 20:00","2016-11-03 08:00","2016-11-03 20:00","당일",null,null,null,201609070325,"-"]
[397,"부산울산","서부산","서부산S/S 154kV #65 BUS","서부산S/S 6100 GIS 정밀점검","서부산S/S 6100 GIS 정밀점검 (6100 CB + 6102 DS 정밀점검)","2016-11-01 08:00","2016-11-02 20:00","2016-11-01 08:00","2016-11-02 20:00","연속",null,null,null,201609070321,"-"]
[398,"부산울산","울산","동울산방어진 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","동울산, 방어진S/S 양단 GIS 초기점검","2016-11-10 09:00","2016-11-10 18:00","2016-11-10 09:00","2016-11-10 18:00","당일",null,null,null,201609080363,"-"]
[399,"부산울산","울산","동울산효문#3 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","동울산S/S 동울산-효문#3T/L 하자점검","2016-11-18 09:00","2016-11-18 18:00","2016-11-18 09:00","2016-11-18 18:00","당일",null,null,null,201609190186,"-"]
[400,"부산울산","울산","신울산언양#2 T/L","154kV 신울산-언양T/L 전선접속개소 전선교체공사","ㅁ 전력선 교체 : 154kV 신울산-언양#2 T/L No.21~27,34~36","2016-11-11 07:00","2016-11-14 18:00","2016-11-02 07:00","2016-11-05 18:00","연속",null,null,null,201609080114,"-"]
[401,"부산울산","울산","신울산언양#1 T/L","154kV 신울산-언양T/L 전선접속개소 전선교체공사","ㅁ 전력선 교체 : 154kV 신울산-언양#1 T/L No.21~27,34~36","2016-11-07 07:00","2016-11-10 18:00","2016-11-06 07:00","2016-11-09 18:00","연속",null,null,null,201609080113,"-"]
[402,"부산울산","울산","신울산영남TP#2 T/L","2016~2017년 울산전력지사 송전정비 협력회사 총액공사","154kV 신울산-영남TPT/L 노후애자금구류 교체 - 구간 : No.4~8(5기)","2016-11-19 09:00","2016-11-20 18:00","2016-11-19 09:00","2016-11-20 18:00","연속",null,null,null,201609090119,"-"]
[403,"부산울산","울산","신울산영남TP#1 T/L","2016~2017년 울산전력지사 송전정비 협력회사 총액공사","154kV 신울산-영남TPT/L 노후애자금구류 교체 - 구간 : No.4~8(5기)","2016-11-12 09:00","2016-11-13 18:00","2016-11-12 09:00","2016-11-13 18:00","연속",null,null,null,201609090118,"-"]
[404,"부산울산","울산","옥동외동#2 T/L","2016~2017년 울산전력지사 송전정비 협력회사 총액공사","154kV 외동-옥동T/L 정밀점검 - 구간 : No.35~외동S/S(28기)","2016-11-07 09:00","2016-11-10 18:00","2016-11-07 09:00","2016-11-10 18:00","연속",null,null,null,201609090114,"-"]
[405,"부산울산","울산","옥동외동#1 T/L","2016~2017년 울산전력지사 송전정비 협력회사 총액공사","154kV 외동-옥동T/L 정밀점검 - 구간 : No.35~외동S/S(28기)","2016-11-01 09:00","2016-11-04 18:00","2016-11-01 09:00","2016-11-04 18:00","연속",null,null,null,201609090113,"-"]
[406,"부산울산","울산","용연울산TP#2 T/L","2016년 하반기 170kV 개폐장치 정밀점검 공사","용연S/S 6A7 GIS 정밀점검 관련 #2BUS 시험가압","2016-11-14 17:00","2016-11-14 18:00","2016-11-14 17:00","2016-11-14 18:00","당일",null,null,null,201609100072,"-"]
[407,"부산울산","울산","용연처용#2 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","용연, 처용S/S 용연-처용#2T/L 보호반 대체","2016-11-02 09:00","2016-11-03 18:00","2016-11-02 09:00","2016-11-03 18:00","연속",null,null,null,201609080359,"-"]
[408,"부산울산","울산","용연울산TP#1 T/L","2016년 하반기 170kV 개폐장치 정밀점검 공사","용연S/S 6A7 GIS 정밀점검 관련 #1BUS 시험가압","2016-11-16 17:00","2016-11-16 18:00","2016-11-16 17:00","2016-11-16 18:00","당일",null,null,null,201609100073,"-"]
[409,"부산울산","울산","울산울산TP#2 T/L","울산울산TP#2 T/L 송전선로 정밀점검","작업내용 : 송전선로 정밀점검 작업구간 : 울산-울산TP#2 T/L No.1~13호(17기)","2016-11-28 09:00","2016-11-29 18:00","2016-11-28 09:00","2016-11-29 18:00","연속",null,null,null,201609090007,"-"]
[410,"부산울산","울산","울산울산TP#1 T/L","2016년 170kV 운휴 개폐장치 정밀점검공사","- 울산S/S 6B7 GIS 및 ESS 설비 시험가압(48h)","2016-11-30 18:00","2016-12-02 18:00","2016-11-30 18:00","2016-12-02 18:00","연속",null,null,null,201609100071,"○"]
[411,"부산울산","울산","울산울산TP#2 T/L","2016년 170kV 운휴 개폐장치 정밀점검공사","- 울산S/S 6B2DS, 6B7CB, 6B6DS(개방) 시험가압(1h)","2016-11-03 17:00","2016-11-03 18:00","2016-11-03 17:00","2016-11-03 18:00","당일",null,null,null,201609080154,"-"]
[412,"부산울산","울산","울산울산TP#1 T/L","울산울산TP#1 T/L 송전선로 정밀점검","작업내용 : 송전선로 정밀점검 작업구간 : 울산-울산TP#1 T/L No.1~13호(17기)","2016-11-15 09:00","2016-11-16 18:00","2016-11-15 09:00","2016-11-16 18:00","연속",null,null,null,201609090006,"○"]
[413,"부산울산","울산","울산울산TP#1 T/L","2016년 170kV 운휴 개폐장치 정밀점검공사","- 울산S/S 6B1DS 시험가압(1h)","2016-11-01 17:00","2016-11-01 18:00","2016-11-01 17:00","2016-11-01 18:00","당일",null,null,null,201609080150,"○"]
[414,"부산울산","울산","신울산웅촌#1 T/L","2016년 하반기 170kV 개폐장치 정밀점검 공사","웅촌S/S 6279 GIS 정밀점검 관련 #1BUS 시험가압","2016-11-09 17:00","2016-11-09 18:00","2016-11-09 17:00","2016-11-09 18:00","당일",null,null,null,201609100070,"-"]
[415,"부산울산","울산","신울산웅촌#2 T/L","2016년 하반기 170kV 개폐장치 정밀점검 공사","웅촌S/S 6279 GIS 정밀점검 관련 #2BUS 시험가압","2016-11-07 17:00","2016-11-07 18:00","2016-11-07 17:00","2016-11-07 18:00","당일",null,null,null,201609100069,"-"]
[416,"부산울산","울산","신울산웅촌#1 T/L","345kV 동울산-신울산T/L 송전선로용 피뢰기 설치공사(이격거리확보)","ㅇ 345kV 동울산-신울산T/L 송전선로용 피뢰기 설치 이격거리 확보 - 병가구간 : No.134호","2016-11-23 07:00","2016-11-23 13:00","2016-11-21 07:00","2016-11-21 18:00","당일",null,null,null,201609080111,"-"]
[417,"부산울산","직할","학장개금#1 T/L","16년도 직할 하반기 170kV GIS 정밀점검","개금S/S #3M.Tr 1차 GIS 정밀점검 1DS, CB 시험가압선로","2016-11-23 17:00","2016-11-23 18:00","2016-11-20 17:00","2016-11-20 18:00","당일",null,null,null,201609090314,"-"]
[418,"부산울산","직할","학장개금#2 T/L","16년도 직할 하반기 170kV GIS 정밀점검","개금S/S #3M.Tr 1차 GIS 정밀점검 2DS 시험가압선로","2016-11-21 18:00","2016-11-21 19:00","2016-11-18 18:00","2016-11-18 19:00","당일",null,null,null,201609090313,"-"]
[419,"부산울산","직할","수정범일#1 T/L","16년도 직할 하반기 170kV GIS 정밀점검","범일S/S #1M.Tr 1차 GIS 정밀점검 1DS, CB 시험가압선로","2016-11-30 17:00","2016-11-30 18:00","2016-11-16 17:00","2016-11-16 18:00","당일",null,null,null,201609090311,"-"]
[420,"부산울산","직할","수정범일#2 T/L","16년도 직할 하반기 170kV GIS 정밀점검","범일S/S #1M.Tr 1차 GIS 정밀점검 2DS 시험가압선로","2016-11-28 18:00","2016-11-28 19:00","2016-11-14 18:00","2016-11-14 19:00","당일",null,null,null,201609090309,"-"]
[421,"부산울산","직할","부산수정#2 T/L","2015-2016년도 서부산 지중송전 위탁정비공사","154kV 부산-수정#2T/L 절연유채유","2016-11-02 09:00","2016-11-02 18:00","2016-11-02 09:00","2016-11-02 18:00","당일",null,null,null,201609120040,"-"]
[422,"부산울산","직할","부산수정#1 T/L","2015-2016년도 서부산 지중송전 위탁정비공사","154kV 부산-수정#1T/L 절연유 채유","2016-11-01 09:00","2016-11-01 18:00","2016-11-01 09:00","2016-11-01 18:00","당일",null,null,null,201609120034,"-"]
[423,"경남","직할","마천진해#2 T/L","안전이격확보휴전(장유마천#2 T/L 피뢰기 설치)","안전이격확보휴전-장유마천#2 T/L 피뢰기 설치(1~61호)","2016-11-15 07:30","2016-11-16 18:00","2016-11-15 07:30","2016-11-16 18:00","매일",null,null,null,201609070278,"-"]
[424,"경남","직할","신김해주촌#1 T/L","초기점검(2016 가공송전선로 순시점검 위탁공사)","신김해주촌#1 T/L 초기점검(7~14호)","2016-11-05 08:00","2016-11-06 18:00","2016-11-05 08:00","2016-11-06 18:00","매일",null,null,null,201609070265,"-"]
[425,"경남","직할","신김해주촌#2 T/L","초기점검(2016 가공송전선로 순시점검 위탁공사)","신김해주촌#2 T/L 초기점검(7~14호)","2016-11-12 08:00","2016-11-13 18:00","2016-11-12 08:00","2016-11-13 18:00","매일",null,null,null,201609070266,"-"]
[426,"경남","직할","완암안민#1 T/L","정밀점검(2016 가공송전선로 순시점검 위탁공사)","완암안민#1 T/L 정밀점검(1~22호)","2016-11-19 08:00","2016-11-20 18:00","2016-11-19 08:00","2016-11-20 18:00","매일",null,null,null,201609070258,"-"]
[427,"경남","직할","완암안민#2 T/L","정밀점검(2016 가공송전선로 순시점검 위탁공사)","완암안민#2 T/L 정밀점검(1~22호)","2016-11-20 08:00","2016-11-20 18:00","2016-11-20 08:00","2016-11-20 18:00","당일",null,null,null,201609070261,"-"]
[428,"경남","직할","수출월림#1 T/L","월림S/S 수출-월림#1T/L 실리콘 러버히터 설치","월림S/S 수출-월림#1T/L 실리콘 러버히터 설치","2016-11-06 09:30","2016-11-06 13:30","2016-11-06 09:30","2016-11-06 13:30","당일",null,null,null,201609050198,"-"]
[429,"경남","직할","수출월림#2 T/L","월림S/S 수출-월림#2T/L 실리콘 러버히터 설치","월림S/S 수출-월림#2T/L 실리콘 러버히터 설치","2016-11-06 13:30","2016-11-06 17:30","2016-11-06 13:30","2016-11-06 17:30","당일",null,null,null,201609050199,"-"]
[430,"경남","직할","창공월림#2 T/L","창공-월림#2 피뢰기 설치(16~17 직할 송전협력 총액공사)","창공-월림#2 피뢰기 설치(1~17호)","2016-11-19 07:30","2016-11-20 18:00","2016-11-19 07:30","2016-11-20 18:00","매일",null,null,null,201609070267,"-"]
[431,"경남","직할","창공월림#1 T/L","창공-월림#2 피뢰기 설치(16~17 직할 송전협력 총액공사)","창공-월림T/L 10호 #1에 설치된 피뢰기를 #2로 이설.","2016-11-20 07:30","2016-11-20 12:00","2016-11-20 07:30","2016-11-20 12:00","당일",null,null,null,201609070268,"-"]
[432,"경남","직할","차룡창공#1 T/L","차룡-창공#1T/L 압축불량개소 조치(16~17 직할 송전협력 총액공사)","차룡-창공#1T/L 압축불량개소 조치(5호 부하측 및 6호 전원,부하측)","2016-11-05 07:00","2016-11-06 18:00","2016-11-05 07:00","2016-11-06 18:00","연속",null,null,null,201609070280,"-"]
[433,"경남","진주","개양S/S 154KV #2 BUS","154kV 개양S/S #4M.Tr 증설공사","170kV GIS 설치 : #2BUS DS 및 차단부","2016-11-09 09:00","2016-11-15 09:00","2016-11-09 09:00","2016-11-15 09:00","연속",null,null,null,201609080151,"-"]
[434,"경남","진주","개양S/S 154KV #1 BUS","154kV 개양S/S #4M.Tr 증설공사","170kV GIS 설치 : #1BUS DS 및 차단부","2016-11-03 09:00","2016-11-09 09:00","2016-11-03 09:00","2016-11-09 09:00","연속",null,null,null,201609080149,"-"]
[435,"경남","진주","가야개양 T/L","154kV 가야-개양T/L 안전이격 확보공사","154kV 가야-개양T/L 안전이격 확보공사 57~59호 인클로징,60호 교체","2016-11-02 07:00","2016-11-17 19:00","2016-11-02 07:00","2016-11-17 19:00","연속",null,null,null,201609070027,"-"]
[436,"경남","진주","거창합천#2 T/L","합천S/S 모자익 대체공사","합천S/S 모자익 대체공사 - 거창-합천#2T/L(11/10~11/11)","2016-11-10 09:30","2016-11-11 18:30","2016-11-10 09:30","2016-11-11 18:30","연속",null,null,null,201609020018,"-"]
[437,"경남","진주","합천합천수력#1 T/L","합천S/S 모자익 대체공사","합천S/S 모자익 대체공사 - 합천수력#1T/L(11/02~11/03)","2016-11-02 09:30","2016-11-03 18:30","2016-11-02 09:30","2016-11-03 18:30","연속",null,null,null,201609020015,"-"]
[438,"경남","진주","합천합천수력#2 T/L","합천S/S 모자익 대체공사","합천S/S 모자익 대체공사 - 합천수력#2T/L(11/04~11/05)","2016-11-04 09:30","2016-11-05 18:30","2016-11-04 09:30","2016-11-05 18:30","연속",null,null,null,201609020016,"-"]
[439,"경남","진주","거창합천#1 T/L","합천S/S 모자익 대체공사","합천S/S 모자익 대체공사 - 거창-합천#1T/L(11/08~11/09)","2016-11-08 09:30","2016-11-09 18:30","2016-11-08 09:30","2016-11-09 18:30","연속",null,null,null,201609020017,"-"]
[440,"경남","통영","삼천포사천#1 T/L","154kV 삼천포-사천#1T/L 전력선 교체공사","154kV 삼천포-사천#1T/L 전력선 교체공사 - 공사구간 : No.15~20, 41~45","2016-11-23 07:00","2016-11-30 18:00","2016-11-23 07:00","2016-11-30 18:00","연속",null,null,null,201609050102,"-"]
[441,"경남","통영","신고성통영 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-통영T/L 가철탑 설치 및 전선이설","2016-11-06 06:00","2016-11-06 13:00","2016-11-06 06:00","2016-11-06 13:00","당일",null,null,null,201609090028,"-"]
[442,"경남","통영","신고성거제#1 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-거제T/L 가철탑 설치 및 전선이설","2016-11-13 06:00","2016-11-13 13:00","2016-11-13 06:00","2016-11-13 13:00","당일",null,null,null,201609090024,"-"]
[443,"경남","통영","신고성거제#2 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-거제T/L 가철탑 설치 및 전선이설","2016-11-13 13:00","2016-11-13 20:00","2016-11-13 13:00","2016-11-13 20:00","당일",null,null,null,201609090026,"-"]
[444,"경남","통영","신고성거제#2 T/L","154kV 신고성-거제#2T/L 안전이격 휴전","154kV 신고성-거제#2T/L 안전이격 휴전","2016-11-20 07:00","2016-11-20 18:00","2016-11-20 07:00","2016-11-20 18:00","매일",null,null,null,201609050050,"-"]
[445,"경남","통영","신고성고성 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-통영T/L 가철탑 설치 및 전선이설","2016-11-06 13:00","2016-11-06 20:00","2016-11-06 13:00","2016-11-06 20:00","당일",null,null,null,201609090029,"-"]
[446,"경남","통영","신고성거제#2 T/L","154kV 신고성-거제#2T/L 안전이격휴전","154kV 신고성-거제#2T/L 안전이격휴전","2016-11-27 07:00","2016-11-27 18:00","2016-11-27 07:00","2016-11-27 18:00","매일",null,null,null,201609050052,"-"]
[447,"경남","함안","신마산마산#2 T/L","154kV 신마산-마산#2T/L 자기애관 규격 측정","154kV 신마산-마산#2T/L 자기애관 교체공사 관련 규격 측정","2016-11-13 08:00","2016-11-13 17:00","2016-11-13 08:00","2016-11-13 17:00","당일",null,null,null,201609080232,"-"]
[448,"경남","함안","진영한림정#2 T/L","154kV 한림정분기T/L 건설 공사","1, 2호 항공도장, 항공 등 취부 및 금구류 점검","2016-11-19 08:00","2016-11-20 18:00","2016-11-19 08:00","2016-11-20 18:00","연속",null,null,null,201609120435,"-"]
[449,"경남","함안","한림정삼계#1 T/L","154kV 한림정-삼계T/L 10호 안전이격 확보공사","한림정-삼계#1T/L 10호 본선로 구성","2016-11-19 08:00","2016-11-20 18:30","2016-11-19 08:00","2016-11-20 18:30","연속",null,null,null,201609010056,"-"]
[450,"경남","함안","진영한림정#1 T/L","154kV 한림정분기T/L 건설 공사","1, 2호 항공도장, 항공 등 취부 및 금구류 점검","2016-11-26 08:00","2016-11-27 18:00","2016-11-26 08:00","2016-11-27 18:00","연속",null,null,null,201609120438,"-"]
[451,"경남","함안","한림정삼계#2 T/L","154kV 한림정-삼계T/L 10호 안전이격 확보공사","한림정-삼계#2T/L 10호 본선로 구성","2016-11-26 08:00","2016-11-27 18:30","2016-11-26 08:00","2016-11-27 18:30","연속",null,null,null,201609010057,"-"]
["추가1","광주전남",null,"장성영광#2T/L","154kV장성-영광T/L전선접속개소전선교체공사","0 전선 및 금구류 교체 : No.125~160 4회선 구간","2016-11-11 07:00","2016-11-19 18:00","2016-11-18 07:00","2016-11-26 18:00","연속",null,null,null,"-","-"]
["추가2","광주전남",null,"장성영광#1T/L","154kV장성-영광T/L전선접속개소전선교체공사","0 전선 및 금구류 교체 : No.125~160 4회선 구간","2016-11-20 07:00","2016-11-30 18:00","2016-11-20 07:00","2016-11-30 18:00","연속",null,null,null,"-","-"]
["추가3","광주전남",null,"영광고창T/L","154kV 장성-영광T/L전선접속개소전선교체공사","전선교체 관련 안전이격","2016-11-14 07:00","2016-11-19 18:00","2016-11-14 07:00","2016-11-19 18:00","연속",null,null,null,"-","-"]
["추가4","광주전남",null,"영광홍농T/L","154kV 장성-영광T/L전선접속개소전선교체공사","전선교체 관련 안전이격","2016-11-20 07:00","2016-11-25 18:00","2016-11-20 07:00","2016-11-25 18:00","연속",null,null,null,"-","-"]
["추가5","광주전남",null,"홍농고창T/L","154kV 장성-영광T/L전선접속개소전선교체공사","전선교체 관련 안전이격","2016-11-26 07:00","2016-11-30 18:00","2016-11-26 07:00","2016-11-30 18:00","연속",null,null,null,"-","-"]

{"sheet":"한수원","index":3,"n_rows":11,"n_cols":20,"rows_kept":11,"cut":false,"hidden":false,"merged":[[0,0,0,6],[4,0,5,0],[4,1,5,1],[4,2,5,2],[4,3,5,3],[4,4,5,4],[4,5,5,5],[4,6,4,7],[4,19,5,19],[4,8,4,9],[4,10,5,10],[4,11,5,11],[4,12,5,12],[4,13,5,13],[4,14,5,14],[4,15,5,15],[4,16,5,16],[4,17,5,17],[4,18,5,18]]}
["2016년도 11월 월간휴전 계획"]
[]
[]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"한빛본부","1발전소","#1 기동용변압기\n (MC-X01)","한빛 1호기 제23차 계획예방정비 기동변압기 정비관련 휴전\n* 조작차단기 : 7200, 7271","- 기동변압기 X01 및 A계열 정비","2016-11-04 09:00","2016-11-09 16:00","2016-11-04 09:00","2016-11-09 16:00","연속","N"]
[2,"한빛본부","1발전소","#1 기동용변압기\n (MC-X02)","한빛 1호기 제23차 계획예방정비 기동변압기 정비관련 휴전\n* 조작차단기 : 7F72, 7F00","- 기동변압기 X02 및 B계열 정비","2016-11-24 09:00","2016-11-28 16:00","2016-11-24 09:00","2016-11-28 16:00","연속","N"]
[3,"한빛본부","2발전소","#4 기동변압기\n(04XN)","3호기 16차 계획예방정비\n* 조작차단기 : PCB 7500, 7571","○ O/H 관련 #3 기동변압기(04XN) 일반점검\n○ 보호계전기 개체 및 연동시험","2016-11-09T08:30:00","2015-11-15T22:00:00","2016-11-09T08:30:00","2015-11-15T22:00:00","연속","Y"]
[4,"월성본부","3발전소 ","신월성 1호기 주변압기","신월성 1호기 3차 OH기간 중 주변압기 점검\n조작차단기 : PCB 7400, 7472","신월성1호기 3차 계획예방정비 기간 중 MTR/UAT/EXTR 일반 점검 수행","2016-11-10 08:00","2016-11-24 18:00","2016-11-10 08:00","2016-11-24 18:00","연속","Y",null,null," ","N","N","Y","N","Y"]
[5,"월성본부","3발전소 ","신월성 1호기 대기보조변압기","신월성 1호기 3차 OH기간 중 대기보조변압기 점검\n조작차단기 : PCB 7300, 7372","신월성1호기 3차 계획예방정비 기간 중 대기보조변압기 일반 점검 수행","2016-11-25 08:00","2016-11-30 18:00","2016-11-25 08:00","2016-11-30 18:00","연속","Y",null,null," ","N","N","N","N","Y"]