{"text_format":"2","workbook":"xlsx","n_sheets":5,"sheets":["765송부","345송부","154송부","한수원","중부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":6,"n_cols":16,"rows_kept":6,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 2월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"대전충남","서산","신서산S/S #4 M.Tr 1차 CB (8572)","신서산S/S 765kV GIS 불량부품 교체공사","○765kV GIS 메인밸브교체","2017-02-08 09:00","2017-02-08 18:00","2017-02-08 09:00","2017-02-08 18:00","당일",null,null,null,201612130047]
[2,"부산울산","동부산","신고리S/S #1 M.Tr A-1","신고리S/S 765kV #1M.Tr 오경보 조치","신고리 765kV #1M.Tr 오경보관련 RCP 내부부품 전량교체","2017-02-06 09:00","2017-02-10 18:00","2017-02-06 09:00","2017-02-10 18:00","연속",null,null,null,201612090163]

{"sheet":"345송부","index":1,"n_rows":52,"n_cols":16,"rows_kept":52,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 2월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","강남","신양재S/S 345kV #2 Sh.R","345kV Sh.R 보통점검 -변전총액공사","345kV Sh.R 보통점검 -변전총액공사","2017-02-08 10:00","2017-02-08 18:00","2017-02-08 10:00","2017-02-08 18:00","당일",null,null,null,201612070047]
[2,"남서울","강남","신양재S/S 345kV #1 Sh.R","345kV Sh.R 보통점검 -변전총액공사","345kV Sh.R 보통점검 -변전총액공사","2017-02-07 10:00","2017-02-07 18:00","2017-02-07 10:00","2017-02-07 18:00","당일",null,null,null,201612070046]
[3,"인천","인천","서인천C/C 345kV #70 BUS","345kV 서(신)인천C/C 용량부족 GIS 대체공사","* 서인천C/C #70BUS 모선개조 및 DS 대체","2017-02-15 10:00","2017-03-20 18:00","취소","취소","연속",null,null,null,201612200011]
[4,"인천","직할","신부평S/S #3 M.Tr A","신부평S/S 345kV #3M.Tr 보호반 대체","신부평S/S 345kV #3M.Tr 보호반 대체","2017-02-20 09:30","2017-02-24 18:00","2017-02-20 09:30","2017-02-24 18:00","연속",null,null,null,201612150033]
[5,"인천","직할","신부평S/S #2 M.Tr A","신부평S/S 345kV #2M.Tr 보호반 대체","신부평S/S 345kV #2M.Tr 보호반 대체","2017-02-13 09:30","2017-02-17 18:00","2017-02-13 09:30","2017-02-17 18:00","연속",null,null,null,201612150032]
[6,"경기북부","구리","신가평미금#1 T/L","345kV 신가평-미금TL 접속함 교체공사","- 대상선로 : 345kV 신가평-미금#1TL - 교체대상 : J/B#1,2 접속함 12상 - 내용 : 접속함 교체(PJ Type -> PMJ Type 교체)","2017-02-20 09:00","2017-03-09 18:00","2017-02-20 09:00","2017-03-09 18:00","연속",null,null,null,201611150123]
[7,"강원","동해","삼척GP 동해-삼척GP #2T/L CB (7771)","2017년 동해전력지사 변전협력회사 총액공사","1. 동해-삼척GP #2T/L 7771 CB 하자점검","2017-02-21 10:00","2017-02-21 18:00","2017-02-21 10:00","2017-02-21 18:00","당일",null,null,null,201612070173]
[8,"강원","동해","삼척GP 삼척GP #2T/L - #1기동 Tr CB (7700)","2017년 동해전력지사 변전협력회사 총액공사","1. 삼척GP 삼척GP #2T/L - #1기동 Tr CB(7700) 하자점검","2017-02-22 10:00","2017-02-22 18:00","2017-02-22 10:00","2017-02-22 18:00","당일",null,null,null,201612070178]
[9,"강원","동해","삼척GP #1기동 Tr CB (7772)","2017년 동해전력지사 변전협력회사 총액공사","1. 삼척GP #1기동 Tr CB(7772) 하자점검","2017-02-23 10:00","2017-02-23 18:00","2017-02-23 10:00","2017-02-23 18:00","당일",null,null,null,201612070182]
[10,"충북","직할","신제천S/S 345kV #1 BUS","345kV 신제천S/S GIS화 공사","73Bay 기초 설치","2017-02-20 08:00","2017-02-22 18:00","2017-02-20 08:00","2017-02-22 18:00","연속",null,null,"신뢰도개선",201612220016]
[11,"충북","직할","신제천S/S #3 M.Tr A","345kV 신제천S/S GIS화 공사","#73Bay GIS 기초 및 제어케이블 덕트 설치","2017-02-20 08:00","2017-06-09 18:00","2017-02-20 08:00","2017-06-09 18:00","연속",null,null,"신뢰도개선",201612140127]
[12,"충북","청주","신옥천북경남 T/L","신옥천S/S 345 용량부족차단기 대체공사","0 신옥천-북경남T/L이설(15일): 신설 GIS 72Bay #2BUS측으로 인출 변경 - 가선(인하선 연결) - 변압기 보호반 기설 케이블 철거 및 신설 케이블 결선 - 보호반관련 시험 및 연동시험 - Post 보강 & Beam 교체 및 미사용분 철거 - 사용전검사 및 가압","2017-02-22 09:00","2017-03-08 18:00","2017-02-22 09:00","2017-03-08 18:00","연속",null,null,"신뢰도개선",201612160046]
[13,"충북","청주","신옥천세종#2 T/L","신옥천S/S 345 용량부족차단기 대체공사","0 신옥천-세종#2T/L(15일):신설 GIS 72Bay #1BUS측으로 인출 변경(GIB) - 기설 인출GIB 철거 및 신설 인출GIB 설치 - 가선(가공인출 및 인하선 연결) - 송전선로 보호반 기설 케이블 철거 및 신설 케이블 결선 - 보호반관련 시험 및 연동시험 - Post 보강 & Beam 교체 및 미사용분 철거","2017-02-22 09:00","2017-03-08 18:00","2017-02-22 09:00","2017-03-08 18:00","연속",null,null,"신뢰도개선",201612160047]
[14,"충북","청주","신옥천S/S 345kV #2 BUS","신옥천S/S 345 용량부족차단기 대체공사","0 舊 76Bay → 신설GIS 72Bay 인출변경 - 기설 76Bay #2BUS 철거작업","2017-02-22 13:00","2017-02-22 18:00","2017-02-22 13:00","2017-02-22 18:00","당일",null,null,"신뢰도개선",201612160049]
[15,"충북","청주","신옥천S/S 345kV #1 BUS","신옥천S/S 345 용량부족차단기 대체공사","0 舊 76Bay → 신설GIS 72Bay 인출변경 - 기설 76Bay #21US 철거작업","2017-02-22 08:00","2017-02-22 12:00","2017-02-22 08:00","2017-02-22 12:00","당일",null,null,"신뢰도개선",201612160048]
[16,"충북","청주","신옥천S/S 345kV #2 BUS","345kV 신옥천S/S 차단기 용량대체공사","기설 77Bay #2BUS 철거작업","2017-02-06 13:00","2017-02-06 18:00","2017-02-06 13:00","2017-02-06 18:00","당일",null,null,null,201612160045]
[17,"충북","청주","신옥천S/S #3 M.Tr A","345kV 신옥천S/S 차단기 용량대체공사","- 가선(인하선 연결) - 변압기 보호반 기설 케이블 철거 및 신설 케이블 결선 - 보호반관련 시험 및 연동시험 - 기설 Bay철거 및 신설 Bay 가압","2017-02-06 09:00","2017-02-13 18:00","2017-02-06 09:00","2017-02-13 18:00","연속",null,null,null,201612160043]
[18,"충북","청주","신옥천세종#1 T/L","345kV 신옥천S/S 차단기 용량대체공사","- 기설 인출GIB 철거 및 신설 인출GIB 설치 - 가선(가공인출 및 인하선 연결) - 송전선로 보호반 기설 케이블 철거 및 신설 케이블 결선 - 보호반관련 시험 및 연동시험,사용전검사 - 기설 Bay 철거 및 신설Bay 가압","2017-02-06 09:00","2017-02-20 18:00","2017-02-06 09:00","2017-02-20 18:00","연속",null,null,null,201612160042]
[19,"충북","청주","신옥천S/S 345kV #1 BUS","345kV 신옥천S/S 차단기 용량대체공사","기설 77Bay #1BUS 철거작업","2017-02-06 08:00","2017-02-06 12:00","2017-02-06 08:00","2017-02-06 12:00","당일",null,null,null,201612160044]
[20,"충북","청주","청원S/S #3 M.Tr A","16~17년 청주 변전협력회사 총액공사","청원S/S #3 M.Tr A상 2차 부싱단자 과열 보수","2017-02-16 09:00","2017-02-16 18:00","2017-02-16 09:00","2017-02-16 18:00","당일",null,null,null,201612190003]
[21,"충북","청주","신옥천신계룡 T/L","17년 청주전력지사 변전협력회사 총액공사","신옥천S/S 신옥천신계룡T/L[옥외철구GCB측구설비] ES(7492) 및 관련 설비점검","2017-02-02 09:30","2017-02-02 18:00","2017-02-02 09:30","2017-02-02 18:00","당일",null,null,"신뢰도개선",201612300019]
[22,"충북","청주","청원S/S #4 M.Tr A","차단기 개폐타임 측정","#4M.Tr 2차 차단기 개폐Time 측정","2017-02-27 10:00","2017-02-27 18:00","2017-02-27 10:00","2017-02-27 18:00","당일",null,null,null,201612200008]
[23,"충북","충주","신진천S/S 345kV #1 BUS","345kV 신진천S/S 용량부족 GIS 대체공사","345kV 신진천S/S GIS 40kA 4000A → 63kA 6300A 12CB 대체 - 345kV #1BUS 모선대체(약 56m) 및 7651DS 교체","2017-02-06 09:00","2017-03-07 18:00","2017-02-06 09:00","2017-03-07 18:00","연속",null,null,"신뢰도개선",201612070052]
[24,"대전충남","서산","신서산S/S #4 M.Tr 2차 CB (7871)","신서산S/S 345kV GIS 불량부품 교체","○345kV GIS 압력S/W 교체","2017-02-09 10:00","2017-02-09 18:00","2017-02-09 10:00","2017-02-09 18:00","당일",null,null,null,201612130048]
[25,"대전충남","아산","신온양신탕정#2 T/L","345kV 신온양-신탕정T/L 전선교체공사","※ 하단선 전선교체작업 안전이격확보 ○ 구간: 345kV 신온양-신탕정T/L No.3~신탕정S/T [하단선 교체] ○ 선로길이: 8.9km × 2C [지지물 23기]","2017-02-23 06:00","2017-03-15 18:30","2017-02-23 06:00","2017-03-15 18:30","연속",null,null,null,201612070180]
[26,"대전충남","아산","신탕정S/S 345kV #1 BUS","신탕정S/S 362kV GIS 용량대체공사","신탕정S/S 345kV 73Bay GIS 대체(50KA→63KA)","2017-02-19 10:00","2017-02-22 16:00","2017-02-19 10:00","2017-02-22 16:00","연속",null,null,null,201612080074]
[27,"대전충남","아산","신탕정S/S 345kV #2 BUS","신탕정S/S 362kV GIS 용량대체공사","신탕정S/S 345kV 73Bay GIS 대체(50KA→63KA)","2017-02-13 10:00","2017-02-17 16:00","2017-02-13 10:00","2017-02-17 16:00","연속",null,null,null,201612080073]
[28,"전북","김제","신김제한빛NP#1 T/L","345kV 신김제-한빛#1T/L 전력선 교체공사","공사명 : 345kV 신김제-한빛#1T/L 전력선 교체공사 공사구간 : No.25~28, No.31~36, No.36~42 (ACSR 480㎟ × 4B 10.266C-km)","2017-02-20 09:00","2017-03-05 18:00","2017-02-20 09:00","2017-03-05 18:00","연속",null,null,"신뢰도개선",201612190052]
[29,"전북","김제","신김제S/S #2 M.Tr A","신김제S/S #2 M.Tr A","73Bay B/F반 교체","2017-02-27 09:00","2017-03-03 18:00","2017-02-27 09:00","2017-03-03 18:00","연속",null,null,null,201612210064]
[30,"광주전남","강진","신강진S/S #1 M.Tr A","신강진S/S 345kV #1M.Tr(2차 차단기 보통점검)","2016~17년도 강진전력지사 변전협력회사 총액공사 - 17. 2. 6 : 신강진S/S #1M.Tr 2차 차단기 보통점검,피뢰기 하자점검 75BAY 과부하경보설비 구축","2017-02-27 09:00","2017-02-27 18:00","2017-02-27 09:00","2017-02-27 18:00","당일",null,null,null,201612090024]
[31,"광주전남","목포","신김제한빛NP#1 T/L","345kV 신김제-한빛#1T/L(송선선로보호반 대체)","345kV 송전선로보호반 대체 2면","2017-02-13 09:00","2017-02-24 18:00","취소","취소","연속",null,null,null,201612130017]
[32,"대구경북","경산","신경산S/S #1 M.Tr A","신경산S/S 345kV #1M.Tr 휴전","신경산S/S #60-65 BUS PRO 교체공사 관련 준공시험","2017-02-15 15:00","2017-02-15 15:30","2017-02-15 15:00","2017-02-15 15:30","당일",null,null,null,201612090196]
[33,"대구경북","경산","신경산S/S #2 M.Tr A","신경산S/S 345kV #2M.Tr 휴전","신경산S/S #60-65 BUS PRO 교체공사 관련 준공시험","2017-02-15 15:30","2017-02-15 16:00","2017-02-15 15:30","2017-02-15 16:00","당일",null,null,null,201612090197]
[34,"대구경북","경산","신경산S/S #3 M.Tr A","신경산S/S 345kV #3M.Tr 휴전","신경산S/S #61-66 BUS PRO 교체공사 관련 준공시험","2017-02-18 15:00","2017-02-18 15:30","2017-02-18 15:00","2017-02-18 15:30","당일",null,null,null,201612090198]
[35,"대구경북","경산","신경산S/S #4 M.Tr A","신경산S/S 345kV #4M.Tr 휴전","신경산S/S #62-67 BUS PRO 교체공사 관련 준공시험","2017-02-22 16:00","2017-02-22 16:30","2017-02-22 16:00","2017-02-22 16:30","당일",null,null,null,201612090199]
[36,"대구경북","구미","선산S/S #4 M.Tr A","선산S/S #4M.Tr 노후 보호PNL 대체","-선산S/S #4M.Tr 노후 보호PNL 대체 -#4M.TR 보통점검 -1,3차 PT 보통점검 -1,2,3차 LA 보통점검","2017-02-20 09:00","2017-02-24 18:00","2017-02-20 09:00","2017-02-24 18:00","연속",null,null,null,201612020026]
[37,"대구경북","달성","북경남고령#1 T/L","345kV 북경남-고령#1 T/L 초기점검","No.1~39 초기점검","2017-02-13 09:00","2017-02-17 18:00","2017-02-13 09:00","2017-02-17 18:00","연속",null,null,null,201612090111]
[38,"대구경북","달성","북경남고령#2 T/L","345kV 북경남-고령#2 T/L 초기점검","No.1~39 초기점검","2017-02-20 09:00","2017-02-24 18:00","2017-02-20 09:00","2017-02-24 18:00","연속",null,null,null,201612090114]
[39,"대구경북","달성","북경남대구#1 T/L","345kV 북경남-대구#1 T/L 초기점검","No.1~39 초기점검","2017-02-13 09:00","2017-02-17 18:00","취소","취소","연속",null,null,null,201612090112]
[40,"대구경북","달성","북경남대구#2 T/L","345kV 북경남-대구#2 T/L 초기점검","No.1~39 초기점검","2017-02-20 09:00","2017-02-24 18:00","취소","취소","연속",null,null,null,201612090113]
[41,"대구경북","칠곡","신포항북대구 T/L","신포항-북대구T/L 송전선로 보호반 교체","신포항-북대구T/L 송전선로 보호반 교체","2017-02-19 09:30","2017-02-25 18:00","2017-02-19 09:30","2017-02-25 18:00","연속",null,null,null,201612080064]
[42,"부산울산","동부산","신양산북부산#1 T/L","도로건설공사 관련 안전이격확보(교량 설치)","부산외곽도로 건설공사 교량설치 작업시 송전선로와의 안전이격거리확보 □ 공사명: 부산외곽순환 건설공사(10공구) □ 작업내용: 교량설치 작업 □ 휴전요청 사유: 크레인작업시 송전선로와의 안전이격거리 미확보 □ 작업구간: 345kV 신양산-북부산#1 T/L 40~41호 □ 발주처: 한국도로공사, 시공사: KCC건설 □ 붙임: 관련공문 1부","2017-02-20 08:00","2017-02-22 18:00","2017-02-20 08:00","2017-02-22 18:00","매일",null,null,null,201612120023]
[43,"부산울산","북부산","북부산S/S #2 M.Tr A","북부산S/S 154kV 취약설비 GIS화 공사","154kV GIS 반입관련 안전이격확보관련 #2M.Tr 휴전","2017-02-04 09:00","2017-02-04 18:00","2017-02-04 09:00","2017-02-04 18:00","당일",null,null,null,201612120012]
[44,"부산울산","서부산","서부산S/S 서부산#3T/L-#3 M.Tr 1차 CB (7300)","서부산S/S 서부산#3T/L-#3 M.Tr 1차(7300) 보통점검","서부산S/S 345kV 서부산#3T/L-#3 M.Tr 1차(7300) 보통점검","2017-02-21 10:00","2017-02-21 18:00","2017-02-21 10:00","2017-02-21 18:00","당일",null,null,null,201612090116]
[45,"부산울산","서부산","서부산북부산#1 T/L","서부산S/S 345kV #1Sh.R 대체공사(시험가압)","서부산S/S 345kV #1Sh.R 대체공사(시험가압-48H)","2017-02-25 10:00","2017-02-26 10:00","2017-02-25 10:00","2017-02-26 10:00","연속",null,null,null,201612090115]
[46,"부산울산","서부산","서부산S/S #3 M.Tr 1차 CB (7372)","서부산S/S #3 M.Tr 1차 CB(7372) 보통점검","서부산S/S #3 M.Tr 1차 CB(7372) 보통점검","2017-02-22 10:00","2017-02-22 18:00","2017-02-22 10:00","2017-02-22 18:00","당일",null,null,null,201612090118]
[47,"부산울산","서부산","서부산S/S 서부산-북부산#3T/L CB (7371)","서부산S/S 서부산-북부산#3T/L CB(7371) 보통점검","서부산S/S 서부산-북부산#3T/L CB(7371) 보통점검","2017-02-23 10:00","2017-02-23 18:00","2017-02-23 10:00","2017-02-23 18:00","당일",null,null,null,201612090121]
[48,"부산울산","울산","북부산신온산 T/L","울산복합화력 차단 고장파급방지시스템 회로구성","345kV 북부산-신온산T/L 고장검출 송신회로 구성","2017-02-05 09:00","2017-02-05 18:00","2017-02-05 09:00","2017-02-05 18:00","당일",null,null,null,201612150067]

{"sheet":"154송부","index":2,"n_rows":68,"n_cols":16,"rows_kept":68,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 2월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","직할","세종로옥인#1 T/L","화양 및 세종로S/S 인출선로 선종교체공사","1. 사 업 명 : 화양 및 세종로S/S 인출선로 선종교체공사 2. 사업목적 : 화양 및 세종로변전소(지하복합) 화재 및 대형 재난사고 예방 3. 사업개요 ○ 사업구간 : 화양S/S ∼ 인출전력구, 세종로S/S ∼ 인출전력구 ○ 사업내용 - 선종교체 : 154kV OF→XLPE(2000/1200/600㎟) 6회선, 총길이0.6㎞","2017-02-27 10:00","2017-03-31 17:00","2017-02-27T10:00:00","2017-03-31T17:00:00","연속",null,null,null,201612120079]
[2,"서울","직할","원남S/S 154kV #1 BUS TIE CB","16-17년 직할 변전협력총액공사","원남S/S 154kV 모선보호반 대체","2017-02-14 10:00","2017-02-16 18:00","2017-02-14T10:00:00","2017-02-16T18:00:00","연속",null,null,null,201612190125]
[3,"서울","중부","양주은평#2 T/L","2016~2017년 중부전력지사 변전협력업체 총액공사","은평S/S 154kV 양주은평#2T/L (627) AIR 누기 보수","2017-02-01 10:00","2017-02-01 12:00","2017-02-01T10:00:00","2017-02-01T12:00:00","연속",null,null,null,201612300024]
[4,"남서울","영서","봉천신길#1 T/L","봉천,노들변전소 OF케이블 선종교체공사","케이블철거 및 설치 : OF케이블에서 XLPE로 교체(255m X 3상) 이종 및 종단 접속 : 2개소 X 3상 PT 이설 및 기타 부대작업","2017-02-16 09:00","2017-03-17 18:00","2017-02-16T09:00:00","2017-03-17T18:00:00","연속",null,null,null,201612200019]
[5,"남서울","직할","영등포노들 T/L","봉천,노들변전소 OF케이블 선종교체공사","케이블철거 및 설치 : OF케이블에서 XLPE로 교체(172m X 3상) 이종 및 종단 접속 : 2개소 X 3상 PT 이설 및 기타 부대작업","2017-02-16 09:00","2017-03-17 18:00","2017-02-16T09:00:00","2017-03-17T18:00:00","연속",null,null,null,201612200020]
[6,"인천","시흥","도림오봉 T/L","2017~18년 인천전력지사 지중송전설비 위탁정비공사","EBA 절연유 시료채취","2017-02-23 09:00","2017-02-23 18:00","2017-02-23T09:00:00","2017-02-23T18:00:00","당일",null,null,null,201612140092]
[7,"인천","시흥","서안양소래 T/L","2017~18년 인천전력지사 지중송전설비 위탁정비공사","EBA 절연유 시료채취","2017-02-20 09:00","2017-02-20 18:00","2017-02-20T09:00:00","2017-02-20T18:00:00","당일",null,null,null,201612140090]
[8,"인천","시흥","신시흥오봉 T/L","2017~18년 인천전력지사 지중송전설비 위탁정비공사","EBA 절연유 시료채취","2017-02-24 09:00","2017-02-24 18:00","2017-02-24T09:00:00","2017-02-24T18:00:00","당일",null,null,null,201612140091]
[9,"인천","인천","신가좌신현#1 T/L","2017~18년 인천전력지사 지중송전설비 위탁정비공사","신현C/H 케이블헤드 점검","2017-02-16 09:00","2017-02-16 18:00","2017-02-16T09:00:00","2017-02-16T18:00:00","당일",null,null,"신뢰도개선",201612140093]
[10,"인천","인천","신가좌주안#1 T/L","2017~18년 인천전력지사 지중송전설비 위탁정비공사","신주C/H 케이블헤드 점검","2017-02-25 09:00","2017-02-25 18:00","2017-02-25T09:00:00","2017-02-25T18:00:00","당일",null,null,null,201612140083]
[11,"인천","인천","신가좌주안#2 T/L","2017~18년 인천전력지사 지중송전설비 위탁정비공사","신주C/H 케이블헤드 점검","2017-02-26 09:00","2017-02-26 18:00","2017-02-26T09:00:00","2017-02-26T18:00:00","당일",null,null,null,201612140084]
[12,"인천","인천","신가좌신현#2 T/L","2017~18년 인천전력지사 지중송전설비 위탁정비공사","신현C/H 케이블헤드 점검","2017-02-17 09:00","2017-02-17 18:00","2017-02-17T09:00:00","2017-02-17T18:00:00","당일",null,null,"신뢰도개선",201612140094]
[13,"경기","평택","평택추팔#1 T/L","154kV 평택-추팔T/L No.14,15 안전이격 확보공사","지지물 교체 : 2기 전력선교체 : 4가닥","2017-02-20 08:00","2017-02-24 18:00","2017-02-20T08:00:00","2017-02-24T18:00:00","연속",null,null,"신뢰도개선",201612190016]
[14,"경기","평택","평택추팔#2 T/L","154kV 평택-추팔T/L No.14,15 안전이격 확보공사","지지물 교체 : 2기 전력선교체 : 4가닥","2017-02-20 08:00","2017-02-24 18:00","2017-02-20T08:00:00","2017-02-24T18:00:00","연속",null,null,"신뢰도개선",201612190017]
[15,"강원","원주","홍천소양강HP T/L","홍천변전소 170kV GIS 설치공사","홍천변전소 170kV GIS 설치 - 154kV 홍천-소양강HP TL 붓싱 조립 - 170kV GIS 전체 내압시험 - 옥외철구용 차단기 ,단로기, 모선 철거 - LINE LA, CVT 기초설치 및 기기 이설","2017-02-27 09:00","2017-03-13 18:00","2017-02-27 09:00","2017-03-13 18:00","연속",null,null,null,201612080042]
[16,"대전충남","아산","신온양석곡#2 T/L","[송전]154kV 신온양-한샘T/L 경과지 변경 건설공사","[송전] 전력선 연선 및 긴선에 따른 No.7호 활선근접에 따른 휴전 (작업내용) - No.7 ~ 13호간 전력선 연선 및 긴선 * 2.013km - 애자금구류 및 피뢰기 설치 * 1식 - 기타 부대작업","2017-02-08 08:00","2017-02-12 18:00","2017-02-08T08:00:00","2017-02-12T18:00:00","연속",null,null,null,201611160064]
[17,"대전충남","아산","신온양석곡#1 T/L","[송전]154kV 신온양-한샘T/L 경과지 변경 건설공사","[송전] 전력선 연선 및 긴선에 따른 No.7호 활선근접에 따른 휴전 (작업내용) - No.7 ~ 13호간 전력선 연선 및 긴선 * 2.013km - 애자금구류 및 피뢰기 설치 * 1식 - 기타 부대작업","2017-02-08 08:00","2017-02-12 18:00","2017-02-08T08:00:00","2017-02-12T18:00:00","연속",null,null,null,201611160063]
[18,"대전충남","아산","신온양한샘#2 T/L","345kV 신온양-신탕정T/L 전선교체공사","○ 구간: 345kV 신온양-신탕정T/L No.3~신탕정S/T [하단선 교체] - 해당선로 : 신온양-한샘T/L No.3~12 구간","2017-02-23 06:00","2017-03-07 18:30","2017-02-23T06:00:00","2017-03-07T18:30:00","연속",null,null,null,201612070188]
[19,"대전충남","아산","아산온양#2 T/L","[송전] 154kV 아산-온양T/L 23호 안전이격확보공사","ㅇ 철탑교체 : 1기 ㅇ OPGW 이설 : 1기 ㅇ 기타 부대공사","2017-02-04 08:00","2017-02-05 18:00","2017-02-04T08:00:00","2017-02-05T18:00:00","연속",null,null,null,201612260102]
[20,"전북","김제","신김제남전주#2 T/L","154kV 신김제-남전주#2T/L 점퍼지지애자 교체공사","154kV 신김제-남전주#2T/L 점퍼지지애자 교체(2기) 154kV 신김제-전주#1T/L 점퍼지지애자 교체(3기) 154kV 임실-남전주#1T/L 점퍼지지애자 교체(7기) 병행","2017-02-10 07:00","2017-02-12 18:00","2017-02-11 07:00","2017-02-12 18:00","연속",null,null,null,201612190034]
[21,"전북","김제","신김제전주#1 T/L","154kV 신김제-전주#1T/L 점퍼지지애자 교체공사","154kV 신김제-전주#1T/L 점퍼지지애자 교체(3기) 154kV 임실-남전주#1T/L 점퍼지지애자 교체(7기) 병행 154kV 신김제-남전주#2T/L 점퍼지지애자 교체(2기) 병행","2017-02-10 07:00","2017-02-12 18:00","2017-02-10 07:00","2017-02-12 18:00","연속",null,null,null,201612190041]
[22,"전북","김제","신김제전주#2 T/L","154kV 신김제-전주#2T/L 점퍼지지애자 교체공사","154kV 신김제-전주#2T/L 점퍼지지애자 교체(1기) 154kV 임실-남전주#2T/L 점퍼지지애자 교체(2기) 병행","2017-02-09 07:00","2017-02-09 18:00","2017-02-09 07:00","2017-02-09 18:00","당일",null,null,null,201612190046]
[23,"전북","김제","정공정주#2 T/L","154kV 정공-정주#2T/L 점퍼지지애자 교체공사","154kV 정공-정주#2T/L 점퍼지지애자 교체(2기) 154kV 정공-담양T/L 점퍼지지애자 교체(3기) 병행","2017-02-08 07:00","2017-02-08 18:00","취소","취소","당일",null,null,null,201612190024]
[24,"전북","김제","정공섬진강수력 T/L","154kV 정공-섬진강수력T/L 점퍼지지애자 교체공사","154kV 정공-섬진강수력T/L 점퍼지지애자 교체(2기) 154kV 정공-정주#1T/L 점퍼지지애자 교체(4기) 병행","2017-02-06 07:00","2017-02-07 18:00","2017-02-06 07:00","2017-02-07 18:00","연속",null,null,null,201612190015]
[25,"전북","김제","정공담양 T/L","154kV 정공-담양T/L 점퍼지지애자 교체공사","154kV 정공-담양T/L 점퍼지지애자 교체(3기) 154kV 정공-정주#2T/L 점퍼지지애자 교체(2기) 병행","2017-02-08 07:00","2017-02-08 18:00","2017-02-08 07:00","2017-02-08 18:00","당일",null,null,null,201612190022]
[26,"전북","김제","정공담양 T/L","정공담양 T/L","보호배전반 교체","2017-02-13 09:00","2017-02-16 18:00","2017-02-13 09:00","2017-02-16 18:00","연속",null,null,null,201612190149]
[27,"전북","김제","정공정주#1 T/L","154kV 정공-정주#1T/L 점퍼지지애자 교체공사","154kV 정공-정주#1T/L 점퍼지지애자 교체(4기) 154kV 정공-섬진강수력T/L 점퍼지지애자 교체(2기) 병행","2017-02-06 07:00","2017-02-07 18:00","취소","취소","연속",null,null,null,201612190019]
[28,"전북","김제","정주고창#1 T/L","154kV 정주-고창#1T/L 점퍼지지애자 교체공사","154kV 정주-고창#1T/L 점퍼지지애자 교체(11기) 154kV 정주-부안#1T/L 점퍼지지애자 교체(11기) 병행","2017-02-13 07:00","2017-02-15 18:00","2017-02-13 07:00","2017-02-15 18:00","연속",null,null,null,201612190042]
[29,"전북","김제","정주고창#2 T/L","154kV 정주-고창#2T/L 점퍼지지애자 교체공사","154kV 정주-고창#2T/L 점퍼지지애자 교체(9기) 154kV 정주-부안#2T/L 점퍼지지애자 교체(9기) 병행","2017-02-16 07:00","2017-02-18 18:00","2017-02-16 07:00","2017-02-18 18:00","연속",null,null,null,201612190045]
[30,"전북","직할","신김제동전주#2 T/L","154kV 신김제-동전주#2T/L 점퍼지지애자 교체공사","96년 상반기 이전 국산 점퍼지지애자 교체 199개","2017-02-23 07:30","2017-02-23 18:00","2017-02-23 07:30","2017-02-23 18:00","당일",null,null,null,201612070065]
[31,"전북","직할","신김제동전주#1 T/L","154kV 신김제-동전주#1T/L 점퍼지지애자 교체공사","96년 상반기 이전 국산 점퍼지지애자 교체 108개","2017-02-22 12:00","2017-02-22 18:00","2017-02-22 12:00","2017-02-22 18:00","당일",null,null,null,201612070073]
[32,"광주전남","순천","순천S/S 154kV #2 BUS","154kV 순천,광양,율촌T/L 시가지 지중화사업","가. 154kV 순천-승주T/L : XLPE 2,000㎟ 2회선 1.9㎞ 나. 154kV 순천-광양T/L : XLPE 1,200㎟ 2회선(D) 2.8㎞ 다. 154kV 순천-율촌T/L : XLPE 1,200㎟ 2회선 0.1㎞","2017-02-24 16:00","2017-02-24 19:00","2017-02-24 16:00","2017-02-24 19:00","당일",null,null,null,201612130093]
[33,"광주전남","순천","순천승주#2 T/L","154kV 순천,광양,율촌T/L 시가지 지중화사업","가. 154kV 순천-승주T/L : XLPE 2,000㎟ 2회선 1.9㎞ 나. 154kV 순천-광양T/L : XLPE 1,200㎟ 2회선(D) 2.8㎞ 다. 154kV 순천-율촌T/L : XLPE 1,200㎟ 2회선 0.1㎞","2017-02-25 07:00","2017-02-26 20:00","2017-02-25 07:00","2017-02-26 20:00","연속",null,null,null,201612130094]
[34,"광주전남","순천","순천S/S 순천-율촌#1T/L CB","154kV 순천,광양,율촌T/L 시가지 지중화사업","가. 154kV 순천-승주T/L : XLPE 2,000㎟ 2회선 1.9㎞ 나. 154kV 순천-광양T/L : XLPE 1,200㎟ 2회선(D) 2.8㎞ 다. 154kV 순천-율촌T/L : XLPE 1,200㎟ 2회선 0.1㎞","2017-02-24 09:00","2017-05-14 18:00","2017-02-24 09:00","2017-05-14 18:00","연속",null,null,null,201612130091]
[35,"광주전남","순천","광양순천#1 T/L","154kV 순천,광양,율촌T/L 시가지 지중화사업","가. 154kV 순천-승주T/L : XLPE 2,000㎟ 2회선 1.9㎞ 나. 154kV 순천-광양T/L : XLPE 1,200㎟ 2회선(D) 2.8㎞ 다. 154kV 순천-율촌T/L : XLPE 1,200㎟ 2회선 0.1㎞","2017-02-22 08:00","2017-02-24 18:00","2017-02-22 08:00","2017-02-24 18:00","연속",null,null,null,201612130055]
[36,"광주전남","순천","승주S/S 154kV #2 BUS","154kV 순천,광양,율촌T/L 시가지 지중화사업","가. 154kV 순천-승주T/L : XLPE 2,000㎟ 2회선 1.9㎞ 나. 154kV 순천-광양T/L : XLPE 1,200㎟ 2회선(D) 2.8㎞ 다. 154kV 순천-율촌T/L : XLPE 1,200㎟ 2회선 0.1㎞","2017-02-26 16:00","2017-02-26 20:00","2017-02-26 16:00","2017-02-26 20:00","당일",null,null,null,201612130096]
[37,"광주전남","순천","순천율촌#2 T/L","154kV 순천-율촌#2T/L(고객요청공사 안전거리이격)","154kV 순천-율촌#2T/L(고객요청공사 안전거리이격) - No.70~71호","2017-02-25 08:00","2017-02-26 18:00","2017-02-18 08:00","2017-02-19 18:00","매일",null,null,null,201612220026]
[38,"광주전남","순천","순천율촌#1 T/L","154kV 순천-율촌#1T/L(고객요청공사 안전거리이격)","154kV 순천-율촌#1T/L(고객요청공사 안전거리이격) - No.70~71호","2017-02-25 08:00","2017-02-26 18:00","2017-02-18 08:00","2017-02-19 18:00","매일",null,null,null,201612220025]
[39,"대구경북","경산","신경산진량 T/L","신경산S/S 신경산-진량T/L 휴전","신경산S/S #61-66 BUS PRO 교체공사 관련 준공시험","2017-02-18 13:30","2017-02-18 14:00","2017-02-18 13:30","2017-02-18 14:00","당일",null,null,null,201612090092]
[40,"대구경북","경산","신경산노변 T/L","신경산S/S 신경산-노변T/L 휴전","신경산S/S #61-66 BUS PRO 교체공사 관련 준공시험","2017-02-18 13:00","2017-02-18 13:30","2017-02-18 13:00","2017-02-18 13:30","당일",null,null,null,201612090091]
[41,"부산울산","동부산","노포정관#2 T/L","154kV 노포-정관T/L 8호 지장철탑이설공사","노포-정관T/L 8호 지장이설 #2T/L 본선로 구성","2017-02-13 09:00","2017-02-15 18:00","2017-02-13 09:00","2017-02-15 18:00","연속",null,null,null,201612160022]
[42,"부산울산","동부산","노포정관#1 T/L","154kV 노포-정관T/L 8호 지장철탑이설공사","노포-정관T/L 8호 지장이설 본철탑 설치 및 #1T/L 본선로 구성","2017-02-06 09:00","2017-02-11 18:00","2017-02-06 09:00","2017-02-11 18:00","연속",null,null,null,201612160020]
[43,"부산울산","동부산","노포정관#2 T/L","154kV 노포-정관T/L 8호 지장철탑이설공사","노포-정관T/L 8호 지장이설 가선로 구성, 철탑교체 1기(8호)","2017-02-02 09:00","2017-02-04 18:00","2017-02-02 09:00","2017-02-04 18:00","연속",null,null,null,201612160019]
[44,"부산울산","동부산","웅촌서창#1 T/L","154kV 웅촌-서창T/L 지장철탑이설공사","8-12호 본선로 구성","2017-02-06 08:00","2017-02-09 18:00","2017-02-06 08:00","2017-02-09 18:00","연속",null,null,null,201612080043]
[45,"부산울산","동부산","웅촌서창#2 T/L","154kV 웅촌-서창T/L 지장철탑이설공사","8~12호,17-1~20호 본선로 구성","2017-02-10 08:00","2017-02-17 18:00","2017-02-10 08:00","2017-02-17 18:00","연속",null,null,null,201612080045]
[46,"부산울산","동부산","웅촌서창#1 T/L","154kV 웅촌-서창T/L 지장철탑이설공사","17-1~20호 본선로 구성","2017-02-18 08:00","2017-02-21 18:00","2017-02-18 08:00","2017-02-21 18:00","연속",null,null,null,201612080044]
[47,"부산울산","북부산","북부산구포#1 T/L","북부산S/S 154kV 취약설비 GIS화 공사","154kV GIS 반입관련 안전이격확보관련 북부산-구포#1T/L 6C7 CB 휴전","2017-02-04 09:00","2017-02-04 18:00","2017-02-04 09:00","2017-02-04 18:00","당일",null,null,null,201612120011]
[48,"부산울산","북부산","북부산양산 T/L","양산S/S 취약설비 현대화공사","양산S/S 154kV 북부산-양산T/L Line PT 이설","2017-02-28 09:00","2017-02-28 18:00","2017-02-28 09:00","2017-02-28 18:00","당일",null,null,null,201612060045]
[49,"부산울산","북부산","북부산양산 T/L","양산S/S 취약설비 현대화공사","양산S/S 154kV 북부산-양산T/L Line PT 이설관련 PT 이설위치 기초시공을 위한 터파기 작업 활선근접 안전이격확보","2017-02-23 09:00","2017-02-23 18:00","2017-02-23 09:00","2017-02-23 18:00","당일",null,null,null,201612060044]
[50,"부산울산","서부산","용원녹공#2 T/L","녹공S/S 154kV 용원-녹공#2T/L 실리콘 러버히터 설치","녹공S/S 154kV 용원-녹공#2T/L 실리콘 러버히터 설치","2017-02-25 14:00","2017-02-25 18:00","2017-02-25 14:00","2017-02-25 18:00","당일",null,null,null,201612090160]
[51,"부산울산","서부산","용원녹공#1 T/L","녹공S/S 154kV 용원-녹공#1T/L 실리콘 러버히터 설치","녹공S/S 154kV 용원-녹공#1T/L 실리콘 러버히터 설치","2017-02-25 10:00","2017-02-25 14:00","2017-02-25 10:00","2017-02-25 14:00","당일",null,null,null,201612090159]
[52,"부산울산","울산","신울산언양#1 T/L","세니온제 154kV 송전선로 보호반 성능개선","신울산, 언양S/S 신울산언양#1 T/L 펌웨어 업그레이드 및 연동시험","2017-02-23 09:00","2017-02-23 13:00","2017-02-23 09:00","2017-02-23 13:00","당일",null,null,null,201612130010]
[53,"부산울산","울산","신울산영남TP#2 T/L","세니온제 154kV 송전선로 보호반 성능개선","신울산, 영남T/P 신울산영남T/P#2 T/L 펌웨어 업그레이드 및 연동시험","2017-02-25 13:00","2017-02-25 18:00","2017-02-25 13:00","2017-02-25 18:00","당일",null,null,null,201612130015]
[54,"부산울산","울산","신울산웅촌#2 T/L","세니온제 154kV 송전선로 보호반 성능개선","신울산, 웅촌S/S 신울산웅촌#2 T/L 펌웨어 업그레이드 및 연동시험","2017-02-24 13:00","2017-02-24 18:00","2017-02-24 13:00","2017-02-24 18:00","당일",null,null,null,201612130009]
[55,"부산울산","울산","신울산영남TP#1 T/L","세니온제 154kV 송전선로 보호반 성능개선","신울산, 영남T/P 신울산영남T/P#1 T/L 펌웨어 업그레이드 및 연동시험","2017-02-25 09:00","2017-02-25 13:00","2017-02-25 09:00","2017-02-25 13:00","당일",null,null,null,201612130014]
[56,"부산울산","울산","신울산언양#2 T/L","세니온제 154kV 송전선로 보호반 성능개선","신울산, 언양S/S 신울산언양#2 T/L 펌웨어 업그레이드 및 연동시험","2017-02-23 13:00","2017-02-23 18:00","2017-02-23 13:00","2017-02-23 18:00","당일",null,null,null,201612130011]
[57,"부산울산","울산","신울산웅촌#1 T/L","세니온제 154kV 송전선로 보호반 성능개선","신울산, 웅촌S/S 신울산웅촌#1 T/L 펌웨어 업그레이드 및 연동시험","2017-02-24 09:00","2017-02-24 13:00","2017-02-24 09:00","2017-02-24 13:00","당일",null,null,null,201612130008]
[58,"부산울산","울산","신온산온산#1 T/L","2017년도 울산전력지사 170kV 개폐장치 정밀점검","온산S/S 611, 617, 616 시험가압","2017-02-22 17:00","2017-02-22 18:00","2017-02-22 17:00","2017-02-22 18:00","당일",null,null,null,201612150071]
[59,"부산울산","울산","신온산온산#3 T/L","2017년도 울산전력지사 170kV 개폐장치 정밀점검","온산S/S 612 DS 시험가압","2017-02-20 17:00","2017-02-20 18:00","2017-02-20 17:00","2017-02-20 18:00","당일",null,null,null,201612150070]
[60,"부산울산","울산","울주S/S #63M.Tr CB","경보제 계전기 성능개선","울주S/S #1EM.Tr 경보제 계전기 성능개선","2017-02-20 09:00","2017-02-20 18:00","2017-02-20 09:00","2017-02-20 18:00","당일",null,null,null,201612130007]
[61,"경남","진주","하동개양#2 T/L","154kV 하동-개양#2T/L 88호 철탑 암교체","154kV 하동-개양#2T/L 88호 철탑 절연간격확보 암교체 삼각암-&gt사각암","2017-02-25 06:00","2017-02-26 18:30","2017-02-25 06:00","2017-02-26 18:30","연속",null,null,null,201612150015]
[62,"경남","진주","하동개양#1 T/L","154kV 하동-개양#2T/L 88호 철탑 암교체","154kV 하동-개양#2T/L 88호 철탑 절연간격확보 암교체 안전이격 확보","2017-02-25 06:00","2017-02-26 18:30","2017-02-25 06:00","2017-02-26 18:30","연속",null,null,null,201612220036]
[63,"경남","진주","합천합천수력#2 T/L","합천S/S 축소형 모자익 교체공사","합천S/S 축소형 모자익 교체공사","2017-02-10 09:30","2017-02-11 18:30","2017-02-10 09:30","2017-02-11 18:30","연속",null,null,null,201612090074]
[64,"경남","진주","합천합천수력#1 T/L","합천S/S 축소형 모자익 교체공사","합천S/S 축소형 모자익 교체공사","2017-02-08 09:30","2017-02-09 18:30","2017-02-08 09:30","2017-02-09 18:30","연속",null,null,null,201612090073]

{"sheet":"한수원","index":3,"n_rows":16,"n_cols":20,"rows_kept":16,"cut":false,"hidden":false,"merged":[[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,19,3,19],[8,0,9,0],[8,1,9,1],[8,2,9,2],[8,3,9,3],[8,4,9,4],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,14,3,14],[8,12,9,12],[2,15,3,15],[2,16,3,16],[2,17,3,17],[2,18,3,18],[8,5,9,5],[8,6,8,7],[8,8,8,9],[8,10,9,10],[8,11,9,11],[8,19,9,19],[13,0,14,0],[13,1,14,1],[13,2,14,2],[13,3,14,3],[13,4,14,4],[13,5,14,5],[13,6,13,7],[13,8,13,9],[13,10,14,10],[8,13,9,13],[8,14,9,14],[8,15,9,15],[8,16,9,16],[8,17,9,17],[8,18,9,18],[13,17,14,17],[13,18,14,18],[13,19,14,19],[13,11,14,11],[13,12,14,12],[13,13,14,13],[13,14,14,14],[13,15,14,15],[13,16,14,16]]}
["2017년도 2월 월간 휴전계획표"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업\n구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소간","사업소내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"고리본부","신고리1발전소","#1 주변압기","1호기 4차 계획예방정비","소내전원절체(UAT -> SAT) 시험 후 차단기 재투입","2017-02-12T10:00:00","2017-02-12T22:00:00","2017-02-12T10:00:00","2017-02-12T22:00:00","당일","Y",null,null,null,"N","N","Y","N","Y"]
[2,"한울본부","신한울1발","PCB 8300, 8372","신한울 1호기 최초 전원가압","○ 신한울1호기 주변압기 가압 및 시운전시험\n * 조작차단기 : 기존 SWYD PCB 8300,8372\n ※ 조작절차 : 차단기 동작시험후  본가압(보호계전기 연동시험 등","2017-02-20T10:00:00","2017-03-20T10:00:00","2017-02-20T10:00:00","2017-03-20T10:00:00","연속","Y"]
[]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업\n구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소간","사업소내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"한빛본부","한빛3발","#5 주변압기","5호기 11차 계획예방정비\n#5 주변압기 점검\n* 조작차단기 : PCB 7D00, 7D71","○ 주변압기 일반점검\n○ 소내보조변압기 일반점검\n○ 보호계전기 개체/연동시험 등","2017-02-20T09:00:00","2017-03-05T18:00:00","2017-02-20T09:00:00","2017-03-05T18:00:00","연속","Y"]
[]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업\n구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소간","사업소내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"고리본부","신고리1발전소","#1 SAT","#1 대기보조변압기 A/B","1호기 4차 계획예방정비\n* 조작 차단기 : PCB 6100, 6172","2017-02-02T10:00:00","2017-02-12T22:00:00","2017-02-02T10:00:00","2017-02-12T22:00:00","연속","Y",null,null,null,"N","N","N","N","Y"]

{"sheet":"중부","index":4,"n_rows":5,"n_cols":21,"rows_kept":5,"cut":false,"hidden":false,"merged":[[2,20,3,20],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,14,3,14],[2,15,3,15],[2,16,3,16],[2,17,3,17],[2,18,3,18],[2,19,3,19],[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7]]}
["2017년도 2월 월간휴전계획표"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전소\n연계","사업소\n간","사업소\n내","발전소 정지\n계획(OH) 연계"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"보령화력","2발전소","3,4호기 기동변압기\n345kV CB7372,7300","기동용변압기\n갑종보호계전기 정기시험","제3,4호기 기동변압기 정기 점검 및 보호계전기 시험 ","2017-02-20T10:00:00","2017-02-24T17:00:00","2017-02-20T10:00:00","2017-02-24T17:00:00","연속",{"$nulls":9},"N"]