{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":9,"n_cols":16,"rows_kept":9,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 3월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #1 M.Tr A-1","신가평S/S #1M.Tr 증설사업(사용전검사 조치사항 수행차)","O 3차측 GPT 중성선 접지 재시공(별도 동대 설치, 별도직접 접지 시행) - 현상태(운전중)로 작업시 플로팅 현상 발생 예상되어 휴전 후 시행","2017-03-01 09:00","2017-03-02 18:00","2017-03-01 09:00","2017-03-02 18:00","당일",null,null,null,201701160074]
[2,"경기북부","구리","신가평S/S #4 M.Tr A-1","신가평S/S #4M.Tr 냉각장치 회로보완","765kV M.Tr 냉각장치 회로보완 × 1식","2017-03-06 09:00","2017-03-06 18:00","2017-03-06 09:00","2017-03-06 18:00","당일",null,null,null,201701170285]
[3,"경기","성남","신안성S/S #2 M.Tr A-1","765kV #2 M.Tr 보통점검","765kV #2 M.Tr 보통점검","2017-03-13 09:00","2017-03-31 18:00","2017-03-13 09:00","2017-03-31 18:00","연속",null,null,null,201608120282]
[4,"대전충남","서산","신서산신안성#2 T/L","765kV 신서산-신안성T/L 항공장애표시구 교체공사","765kV 신서산-신안성T/L 항공장애표시구 교체공사 ○ 구간 : 34~36호, 208~210호","2017-03-07 07:00","2017-03-07 18:00","2017-03-07 07:00","2017-03-07 18:00","당일",null,null,null,201701040124]
[5,"대전충남","서산","신서산신안성#1 T/L","765kV 신서산-신안성T/L 항공장애표시구 교체공사","765kV 신서산-신안성T/L 항공장애표시구 교체공사 ○ 구간 : 34~36호, 208~210호","2017-03-06 07:00","2017-03-06 18:00","2017-03-06 07:00","2017-03-06 18:00","당일",null,null,null,201701040123]

{"sheet":"345송부","index":1,"n_rows":157,"n_cols":16,"rows_kept":157,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 3월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","중부S/S 345kV #1Sh.R","2016~2017년 중부전력지사 변전협력업체 총액공사","중부S/S 345kV #1Sh.R GIS 유면계 불량교체","2017-03-02 10:00","2017-03-02 15:00","2017-03-02 10:00","2017-03-02 15:00","당일",null,null,null,201701170281]
[2,"남서울","강남","신양재S/S 345kV #3 Sh.R","345kV Sh.R 하자점검 - 변전총액공사","345kV Sh.R 하자점검 - 변전총액공사 -신양재S/S #3SH.R","2017-03-06 10:00","2017-03-06 18:00","2017-03-06 10:00","2017-03-06 18:00","당일",null,null,null,201701050105]
[3,"남서울","강남","신양재S/S 345kV #4 Sh.R","345kV Sh.R 하자점검 - 변전총액공사","345kV Sh.R 하자점검 - 변전총액공사 -신양재S/S #4SH.R","2017-03-07 10:00","2017-03-07 18:00","2017-03-07 10:00","2017-03-07 18:00","당일",null,null,null,201701050106]
[4,"남서울","동서울","신성남동서울#1 T/L","345kV 신성남-동서울T/L 전선접속개소 전선교체공사","345kV 신성남-동서울#1T/L 전선교체공사 내용 : #1T/L No.3-9, 13-15, 17-22 상중하단 전선접속개소 전선교체","2017-03-27 08:00","2017-04-11 18:00","2017-03-27 08:00","2017-04-11 18:00","연속",null,null,null,201701160109]
[5,"남서울","동서울","동서울미금#1 T/L","하남 지역현안1지구 지식산업센터 신축공사","하남 지역현안1지구 지식산업센터 신축공사 현장 휴전요청자 : 대우건설 해당설비 : 345kV 동서울-미금T/L No.16-17 작업내용 : 송전선로 아래 흙막이 공사 수행(15일간)","2017-03-06 08:00","2017-03-20 18:00","2017-03-06 08:00","2017-03-20 18:00","연속",null,null,null,201701180076]
[6,"인천","인천","서인천C/C 345kV #75 BUS","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- 서인천C/C 345kV #75BUS 모선개조 및 관련DS 대체","2017-03-06 10:00","2017-04-10 17:00","2017-03-06 10:00","2017-04-10 17:00","연속",null,null,null,201701100113]
[7,"인천","인천","신가좌S/S #1 M.Tr A","신가좌S/S #1M.Tr A상 OFU 누유보수공사","- 신가좌S/S #1M.Tr A상 OFU 누유보수공사 - 신가좌S/S #1M.Tr C상 절연유 보충","2017-03-06 09:00","2017-03-06 18:00","2017-03-06 09:00","2017-03-06 18:00","당일",null,null,null,201701250101]
[8,"인천","인천","신경서신인천CC T/L","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- 345kV 78Bay GIS(7871, 7800 CB) 대체","2017-03-06 10:00","2017-03-31 17:00","2017-03-20 10:00","2017-04-14 17:00","연속",null,null,null,201701100107]
[9,"인천","김포","가정 345kV #1 Sh.R CB","가정 345kV #1 Sh.R 기기점검","가정 345kV #1 Sh.R 기기점검","2017-03-09 10:00","2017-03-09 18:00","2017-03-09 10:00","2017-03-09 18:00","당일",null,null,null,201701100216]
[10,"인천","김포","가정 345kV #3 Sh.R CB","가정 345kV #3 Sh.R 기기점검","가정 345kV #3 Sh.R 기기점검","2017-03-10 10:00","2017-03-10 18:00","2017-03-10 10:00","2017-03-10 18:00","당일",null,null,null,201701100217]
[11,"인천","김포","신김포S/S 345KV #2Sh.R - TIE GIS CB","신김포S/S 345KV #2Sh.R - TIE GIS 기기점검","신김포S/S 345KV #2Sh.R - TIE GIS 기기점검","2017-03-29 10:00","2017-03-29 18:00","2017-03-29 10:00","2017-03-29 18:00","당일",null,null,null,201701100406]
[12,"인천","김포","345kV신김포S/S #1 M.Tr 1차 GIS (7372)CB","345kV신김포S/S #1 M.Tr 1차(7372) GIS 기기점검","345kV신김포S/S #1 M.Tr 1차(7372) GIS 기기점검","2017-03-21 10:00","2017-03-21 18:00","2017-03-21 10:00","2017-03-21 18:00","당일",null,null,null,201701100383]
[13,"인천","김포","345kV신김포S/S #2 M.Tr 1차 GIS (7472)CB","345kV신김포S/S #2 M.Tr 1차(7472) GIS 기기점검","345kV신김포S/S #2 M.Tr 1차(7472) GIS 기기점검","2017-03-22 10:00","2017-03-22 18:00","2017-03-22 10:00","2017-03-22 18:00","당일",null,null,null,201701100386]
[14,"인천","김포","345kV신김포S/S #2Sh.R 1차 (7271)GIS CB","345kV신김포S/S #2Sh.R 1차(7271) GIS 기기점검","345kV신김포S/S #2Sh.R 1차(7271) GIS 기기점검","2017-03-23 10:00","2017-03-23 18:00","2017-03-23 10:00","2017-03-23 18:00","당일",null,null,null,201701100390]
[15,"인천","김포","신김포S/S 345KV 70-71 SEC CB","신김포S/S 345KV 70-71 SEC GIS 기기점검","신김포S/S 345KV 70-71 SEC GIS 기기점검","2017-03-24 10:00","2017-03-24 18:00","2017-03-24 10:00","2017-03-24 18:00","당일",null,null,null,201701100396]
[16,"인천","김포","신김포S/S 345KV 75-76 SEC CB","신김포S/S 345KV 75-76 SEC GIS 기기점검","신김포S/S 345KV 75-76 SEC GIS 기기점검","2017-03-27 10:00","2017-03-27 18:00","2017-03-27 10:00","2017-03-27 18:00","당일",null,null,null,201701100399]
[17,"인천","김포","신김포S/S 345KV #1Sh.R - TIE GIS CB","신김포S/S 345KV #1Sh.R - TIE GIS 기기점검","신김포S/S 345KV #1Sh.R - TIE GIS 기기점검","2017-03-28 10:00","2017-03-28 18:00","2017-03-28 10:00","2017-03-28 18:00","당일",null,null,null,201701100404]
[18,"인천","시흥","신시흥영흥TP#4 T/L","345kV 신시흥신신안산T/L 피뢰기 설치공사","- 신시흥-신안산T/L 피뢰기 설치 관련 안전이격거리확보(1기)","2017-03-02 07:00","2017-03-02 10:00","취소","취소","당일",null,null,null,201701040143]
[19,"인천","시흥","신시흥#2S/S #5M.Tr A","신시흥#2S/S #5M.Tr 정밀점검","신시흥#2S/S #5M.Tr 정밀점검","2017-03-20 08:00","2017-03-31 18:00","2017-03-20 08:00","2017-03-31 18:00","연속",null,null,null,201701110046]
[20,"인천","시흥","신시흥#2S/S #6M.Tr A","신시흥#2S/S #6M.Tr 정밀점검","신시흥#2S/S #6M.Tr 정밀점검","2017-03-06 08:00","2017-03-17 18:00","2017-03-06 08:00","2017-03-17 18:00","연속",null,null,null,201701110038]
[21,"인천","직할","신부평S/S #3 M.Tr A","신부평S/S #3M.Tr 보호반 대체","신부평S/S #3M.Tr 보호반 대체","2017-03-20 09:30","2017-03-24 18:00","2017-03-20 09:30","2017-03-24 18:00","연속",null,null,null,201701030197]
[22,"인천","직할","신부평S/S #2 M.Tr A","신부평S/S #2M.Tr 보호반 대체","신부평S/S #2M.Tr 보호반 대체","2017-03-13 09:30","2017-03-17 18:00","2017-03-13 09:30","2017-03-17 18:00","연속",null,null,null,201701030196]
[23,"경기북부","구리","신가평S/S 345kV #2 Sh.R","신가평S/S 방음벽 설치공사","신가평S/S 방음벽 설치공사","2017-03-20 09:00","2017-03-23 18:00","2017-03-20 09:00","2017-03-23 18:00","당일",null,null,null,201701170210]
[24,"경기북부","구리","신가평S/S 345kV #3 Sh.R","신가평S/S 방음벽 설치공사","신가평S/S 방음벽 설치공사","2017-03-24 09:00","2017-03-27 18:00","2017-03-24 09:00","2017-03-27 18:00","당일",null,null,null,201701170211]
[25,"경기북부","구리","신가평S/S 345kV #4 Sh.R","신가평S/S 방음벽 설치공사","신가평S/S 방음벽 설치공사","2017-03-28 09:00","2017-03-31 18:00","2017-03-28 09:00","2017-03-31 18:00","당일",null,null,null,201701170214]
[26,"경기북부","구리","신포천S/S #1 M.Tr A","2016-17 구리전력지사 변전협력회사 총액공사","ㅇ345kV 신포천S/S #1M.Tr 1차 GIS 보통점검 - 신포천S/S #1M.Tr 1차 7172, 7100 Bay GIS 보통점검","2017-03-23 09:00","2017-03-23 18:00","2017-03-23 09:00","2017-03-23 18:00","당일",null,null,null,201701170273]
[27,"경기북부","구리","신포천S/S #2 M.Tr A","2016-17 구리전력지사 변전협력회사 총액공사","ㅇ345kV 신포천S/S #2M.Tr 1차 GIS 보통점검 - 신포천S/S #2M.Tr 1차 7272, 7200 Bay GIS 보통점검","2017-03-24 09:00","2017-03-24 18:00","2017-03-24 09:00","2017-03-24 18:00","당일",null,null,null,201701170274]
[28,"경기북부","구리","신포천S/S #3 M.Tr A","2016-17 구리전력지사 변전협력회사 총액공사","ㅇ345kV 신포천S/S #3M.Tr 1차 GIS 보통점검 - 신포천S/S #3M.Tr 1차 7472, 7400 Bay GIS 보통점검","2017-03-28 09:00","2017-03-28 18:00","2017-03-28 09:00","2017-03-28 18:00","당일",null,null,null,201701170275]
[29,"경기북부","구리","신포천S/S 345kV #1 Sh.R","2016-17 구리전력지사 변전협력회사 총액공사","ㅇ345kV 신포천S/S #1Sh.R GIS 보통점검 - 신포천S/S #1Sh.R 7372, 7379 Bay GIS 보통점검","2017-03-29 09:00","2017-03-29 18:00","2017-03-29 09:00","2017-03-29 18:00","당일",null,null,null,201701170276]
[30,"경기북부","구리","신포천포천CC#2 T/L","2016-17 구리전력지사 변전협력회사 총액공사","ㅇ345kV 신포천-포천CC#2T/L GIS 하자점검 - 신포천S/S 7471 Bay GIS 보통점검 - 포천CC 7371 Bay GIS 보통점검","2017-03-22 09:00","2017-03-22 18:00","2017-03-22 09:00","2017-03-22 18:00","당일",null,null,null,201701020070]
[31,"경기북부","구리","신포천포천CC#1 T/L","2016-17 구리전력지사 변전협력회사 총액공사","ㅇ345kV 신포천-포천CC#1T/L GIS 하자(보통)점검 - 신포천S/S 7371 Bay GIS 보통점검 - 포천CC 7171 Bay GIS 보통점검","2017-03-21 09:00","2017-03-21 18:00","2017-03-21 09:00","2017-03-21 18:00","당일",null,null,null,201701020069]
[32,"경기북부","직할","신의정부S/S 양주 #2 T/L-#1 Sh.R 1차 CB (7400)","신의정부S/S 양주 #2 T/L-#1 Sh.R 1차 CB(7400)","2017년 직할 변전협력회사 총액공사 - 7400 GIS 보통","2017-03-15 09:00","2017-03-15 18:00","2017-03-15 09:00","2017-03-15 18:00","당일",null,null,null,201701170053]
[33,"경기북부","직할","신의정부S/S #1 Sh.R 1차 CB (7472)","신의정부S/S #1 Sh.R 1차 CB (7472)","2017년 직할 변전협력회사 총액공사 - 7472 GIS 보통","2017-03-15 09:00","2017-03-15 18:00","2017-03-15 09:00","2017-03-15 18:00","당일",null,null,null,201701170052]
[34,"경기북부","직할","신의정부양주#2 T/L","신의정부양주#2 T/L","2017년 직할 변전협력회사 총액공사 - GIS 보통","2017-03-14 09:00","2017-03-14 18:00","2017-03-14 09:00","2017-03-14 18:00","당일",null,null,null,201701170043]
[35,"경기북부","직할","신의정부양주#1 T/L","신의정부양주#1 T/L","2017년 직할 변전협력회사 총액공사 - GIS 보통","2017-03-13 09:00","2017-03-13 18:00","2017-03-13 09:00","2017-03-13 18:00","당일",null,null,null,201701170042]
[36,"경기북부","직할","신의정부S/S #1 M.Tr A","신의정부S/S #1 M.Tr A","2017년 직할 변전협력회사 총액공사 - 과열개소 보수, 96T Air 배출, 가스이상발생 원인분석","2017-03-13 09:00","2017-03-17 18:00","2017-03-13 09:00","2017-03-17 18:00","연속",null,null,null,201701170075]
[37,"경기북부","직할","신의정부S/S #2 M.Tr A","신의정부S/S #1 M.Tr A","2017년 직할 변전협력회사 총액공사 - 과열개소 보수, 96T Air 배출","2017-03-08 09:00","2017-03-08 18:00","2017-03-08 09:00","2017-03-08 18:00","연속",null,null,null,201701170076]
[38,"경기북부","직할","신의정부S/S #3 M.Tr A","신의정부S/S #3 M.Tr A","2017년 직할 변전협력회사 총액공사 - 과열개소 보수, 96T Air 배출","2017-03-09 09:00","2017-03-09 18:00","2017-03-09 09:00","2017-03-09 18:00","연속",null,null,null,201701170077]
[39,"경기북부","직할","신의정부S/S #4 M.Tr A","신의정부S/S #4 M.Tr A","2017년 직할 변전협력회사 총액공사 - 과열개소 보수, 96T Air 배출","2017-03-10 09:00","2017-03-10 18:00","2017-03-10 09:00","2017-03-10 18:00","연속",null,null,null,201701170078]
[40,"경기북부","파주","신파주양주#2 T/L","345kV 신파주S/S CLR 설치공사","1. 신김포-신파주#1T/L 3상 GIB 설치 및 기타작업(근접 안전작업) 2. CLR 설치시 장비 활선 근접관련 안전 작업","2017-03-27 09:00","2017-04-01 18:00","2017-03-27 09:00","2017-04-01 18:00","연속",null,null,null,201701160068]
[41,"경기북부","파주","신파주양주#2 T/L","신파주S/S CLR 설치공사","1.신파주-신김포 #1T/L A상 WALL BUSHING 철거","2017-03-21 09:00","2017-03-21 18:00","2017-03-21 09:00","2017-03-21 18:00","당일",null,null,null,201701160067]
[42,"경기북부","파주","신김포신파주#1 T/L","345kV 신김포-신파주TL 접속함 교체공사","- 대상선로 : 345kV 신김포-신파주#1TL - 교체대상 : J/B1~6, 9,10 등 8개소 48상 접속함 - 내용 : 접속함 교체(PJ Type --- PMJ Type 교체)","2017-03-09 09:00","2017-04-18 18:00","2017-03-20 09:00","2017-04-29 18:00","연속",null,null,null,201612300027]
[43,"경기","군포","서서울S/S #4 M.Tr A","서서울S/S 345kV #4M.Tr 보통점검 공사","서서울S/S 345kV #4M.Tr 하자점검 공사 1차LA, 2차 LA, 1차PT 점검 공사","2017-03-13 09:00","2017-03-14 18:00","2017-03-13 09:00","2017-03-14 18:00","연속",null,null,null,201701030008]
[44,"경기","군포","서서울영서#1 T/L","345kV 신군포S/S 건설사업","- 신시흥-신성남 인입작업관련 근접거리 간섭휴전","2017-03-19 07:00","2017-03-23 18:00","2017-03-19 07:00","2017-03-23 18:00","연속",null,null,null,201701090315]
[45,"경기","군포","서서울S/S #1 M.Tr A","서서울S/S 345kV #1M.Tr 하자점검 공사","서서울S/S 345kV #1M.Tr 하자점검 공사 1차PT, 2차LA 점검 공사","2017-03-06 09:00","2017-03-07 18:00","2017-03-06 09:00","2017-03-07 18:00","연속",null,null,null,201701030005]
[46,"경기","군포","서서울S/S #3 M.Tr A","서서울S/S 345kV #3M.Tr 하자점검 공사","서서울S/S 345kV #3M.Tr 하자점검 공사 1차PT 점검 공사","2017-03-08 09:00","2017-03-09 18:00","2017-03-08 09:00","2017-03-09 18:00","연속",null,null,null,201701030007]
[47,"경기","군포","서서울S/S #2 M.Tr A","서서울S/S 345kV #2M.Tr LA, PT 보통점검 공사","서서울S/S 1차LA, 2차 LA, 1차PT 점검 공사","2017-03-10 09:00","2017-03-10 18:00","2017-03-10 09:00","2017-03-10 18:00","연속",null,null,null,201701030009]
[48,"경기","군포","서서울영서#1 T/L","345kV 신군포S/S 건설사업","- 신시흥-신성남 인입작업관련 근접거리 간섭휴전","2017-03-13 07:00","2017-03-16 18:00","2017-03-25 07:00","2017-03-28 18:00","연속",null,null,null,201701090314]
[49,"경기","군포","화성서서울#1 T/L","서서울S/S 345kV측 전력설비 이설공사","화성-서서울#1T/L 서서울S/S측 피뢰기(3대), CVT(3대) 위치변경","2017-03-01 08:00","2017-03-01 18:00","2017-03-01 08:00","2017-03-01 18:00","당일",null,null,null,201701090059]
[50,"경기","군포","신안산S/S #3 M.Tr A","17년 군포PO 변전협력회사 총액공사","신안산S/S #3M.Tr 1, 2차 GIS 보통점검(7271, 7200CB, 6344CB)","2017-03-15 09:00","2017-03-16 18:00","2017-03-15 09:00","2017-03-16 18:00","연속",null,null,null,201701030046]
[51,"경기","군포","신시흥신안산 T/L","345kV 신시흥신신안산T/L 피뢰기 설치공사","- 송전선로용 피뢰기 설치 : No.19~48호간(27기)","2017-03-02 07:00","2017-03-05 19:00","2017-03-14 07:00","2017-03-17 19:00","연속",null,null,"신뢰도개선",201701040144]
[52,"경기","성남","서안성S/S #4 M.Tr A","서안성S/S #4 M.Tr, GIS 초기점검","서안성S/S #4 M.Tr, GIS 초기점검 7500,7572,6344","2017-03-27 09:00","2017-03-30 18:00","2017-03-27 09:00","2017-03-30 18:00","연속",null,null,null,201701060121]
[53,"경기","성남","서안성신진천#1 T/L","협력회사 총액공사(피뢰기 설치 등)","피뢰기 설치 : 30기","2017-03-13 08:00","2017-03-16 18:00","취소","취소","연속",null,null,null,201701060028]
[54,"경기","성남","서안성신진천#2 T/L","345kV 서안성-신진천#2T/L 가공송전선로 정밀점검","345kV 서안성-신진천#2T/L 가공송전선로 정밀점검(63기)","2017-03-21 09:00","2017-03-25 17:00","2017-03-21 09:00","2017-03-25 17:00","연속",null,null,null,201701040084]
[55,"경기","성남","신성남동서울#2T/L","345kV 신시흥-신성남T/L(군포송정지구) OPGW 시설공사","345kV 신시흥-신성남T/L(군포송정지구) OPGW 시설공사","2017-03-17 07:00","2017-03-18 18:00","취소","취소","연속",null,null,null,201701060105]
[56,"경기","성남","신성남S/S #2 M.Tr A","신성남S/S #2M.Tr 모자익 대체공사","신성남S/S #2M.Tr 모자익 대체공사","2017-03-02 09:00","2017-03-14 18:00","2017-03-02 09:00","2017-03-14 18:00","연속",null,null,null,201608120293]
[57,"경기","성남","신성남S/S #6 M.Tr A","신성남S/S #6M.Tr 모자익 대체공사","신성남S/S #6M.Tr 모자익 대체공사","2017-03-20 09:00","2017-03-28 18:00","2017-03-20 09:00","2017-03-28 18:00","연속",null,null,null,201608120296]
[58,"경기","성남","신성남동서울#2T/L","345kV 신시흥-신성남T/L(군포송정지구) OPGW 시설공사","345kV 신시흥-신성남T/L(군포송정지구) OPGW 시설공사","2017-03-15 07:00","2017-03-16 18:00","2017-04-17 07:00","2017-04-18 18:00","연속",null,null,null,201701060101]
[59,"경기","성남","신수원S/S #3 M.Tr 1차 CB (7572)","7572CB LCP 불량 단자대교체","7572CB LCP 불량 단자대교체","2017-03-30 09:00","2017-03-30 15:00","2017-03-30 09:00","2017-03-30 15:00","당일",null,null,null,201701060313]
[60,"경기","성남","신안성신용인#2 T/L","신안성신용인#2T/L GIS 초기점검","신안성신용인#2T/L GIS 초기점검 7571,7500초기점검,CVT,LA 보통점검","2017-03-16 09:00","2017-03-17 18:00","2017-03-16 09:00","2017-03-17 18:00","연속",null,null,null,201701060065]
[61,"경기","성남","신안성신용인#1 T/L","신안성신용인#1T/L GIS 초기점검","신안성신용인#1T/L GIS 초기점검 7471,7400초기점검,CVT,LA 하자점검","2017-03-02 09:00","2017-03-03 18:00","2017-03-02 09:00","2017-03-03 18:00","연속",null,null,null,201701060060]
[62,"경기","성남","동서울신용인#1 T/L","345kV 신용인-동서울T/L OPGW 시설공사(태전)","신용인-동서울T/L OPGW - OPGW 120/70SQ 24/48C SM 44.866km 시설","2017-03-18 09:00","2017-03-18 18:00","취소","취소","당일",null,null,null,201701090092]
[63,"경기","성남","신용인S/S 345kV #1 Sh.R","신용인S/S 345kV #1Sh.R","신용인S/S 345kV #1Sh.R 7772,7779 초기점검","2017-03-10 09:00","2017-03-10 18:00","2017-03-10 09:00","2017-03-10 18:00","당일",null,null,null,201701060077]
[64,"경기","성남","신용인신수원 T/L","신용인신수원#T/L GIS 초기점검","신용인신수원#T/L 7771,7700 GIS 초기점검 CVT 보통점검, LA 하자점검","2017-03-09 09:00","2017-03-09 18:00","2017-03-09 09:00","2017-03-09 18:00","당일",null,null,null,201701060064]
[65,"경기","성남","신시흥신성남#2 T/L","군포송정지구 345kV신시흥-신성남T/L 지장이설공사","○ 사업유형 : 가공송전 ○ 전압 : 345kV ○ 사업목적 : 군포송정지구 택지 개발사업과 관련으로 345kV신시흥-신성남T/L 지장구간에 대하여 지중으로 건설하고자 가공구간의 임시선로 및 본선로 건설 ○ 사업구간 : 기설 345kV 신시흥-신성남T/L No.48 ~ No.53 ○ 규모 : 철탑 8기, A480B, 2.357km","2017-03-17 07:00","2017-03-31 18:00","취소","취소","연속",null,null,null,201701030042]
[66,"경기","성남","신시흥신성남#1 T/L","군포송정지구 345kV신시흥-신성남T/L 지장이설공사","○ 사업유형 : 가공송전 ○ 전압 : 345kV ○ 사업목적 : 군포송정지구 택지 개발사업과 관련으로 345kV신시흥-신성남T/L 지장구간에 대하여 지중으로 건설하고자 가공구간의 임시선로 및 본선로 건설 ○ 사업구간 : 기설 345kV 신시흥-신성남T/L No.48 ~ No.53 ○ 규모 : 철탑 8기, A480B, 2.357km","2017-03-02 07:00","2017-03-16 18:00","2017-03-14 07:00","2017-03-30 18:00","연속",null,null,null,201701030039]
[67,"충북","직할","곤지암신충주#2 T/L","2017년 OPGW 항공장애표시구 교체공사","345kV 곤지암신충주#2T/L 136~158호 항공장애표시구 31조 교체","2017-03-25 09:00","2017-03-25 18:00","취소","취소","당일",null,null,null,201701090098]
[68,"충북","직할","신제천신충주#1 T/L","2017년 OPGW 항공장애표시구 교체공사","345kV 신제천신충주#1T/L 136~158호 OPGW 항공장애표시구 31조 교체","2017-03-25 09:00","2017-03-25 18:00","취소","취소","당일",null,null,null,201701090096]
[69,"충북","청주","신옥천S/S 345kV #1 BUS","신옥천S/S 345 용량부족차단기 대체공사","기설 71Bay #1BUS 철거작업","2017-03-22 08:00","2017-03-22 12:00","2017-03-22 08:00","2017-03-22 12:00","당일",null,null,null,201701250056]
[70,"충북","청주","신옥천세종#1 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","항공장애구 설치 28경간 (237개)","2017-03-09 08:00","2017-03-15 18:00","2017-03-24 08:00","2017-03-30 18:00","매일",null,null,null,201701170064]
[71,"충북","청주","신옥천S/S 345kV #2 BUS","345kV 신옥천S/S 차단기 용량대체공사","기설 75Bay #2BUS 철거작업","2017-03-10 13:00","2017-03-10 18:00","2017-03-10 13:00","2017-03-10 18:00","당일",null,null,null,201701160145]
[72,"충북","청주","신옥천무주양수 T/L","신옥천S/S 345kV 차단기 용량대체공사","- 신설 GIS 73Bay #2BUS측으로 인출 변경 - 가선(인하선 연결) - 변압기 보호반 기설 케이블 철거 및 신설 케이블 결선 - 보호반관련 시험 및 연동시험","2017-03-10 09:00","2017-03-20 18:00","2017-03-10 09:00","2017-03-20 18:00","연속",null,null,null,201701160142,"O"]
[73,"충북","청주","신옥천S/S 345kV #1 BUS","신옥천S/S 345 용량부족차단기 대체공사","기설 77Bay #1BUS 철거작업","2017-03-10 08:00","2017-03-10 12:00","2017-03-10 08:00","2017-03-10 12:00","당일",null,null,null,201701160144]
[74,"충북","청주","신옥천S/S #1 M.Tr A","신옥천S/S 345kV 차단기 용량대체공사","- 신설 GIS 74Bay #1BUS측으로 인출 변경 - 가선(인하선 연결) - 변압기 보호반 기설 케이블 철거 및 신설 케이블 결선 - 보호반관련 시험 및 연동시험","2017-03-22 09:00","2017-03-29 18:00","2017-03-22 09:00","2017-03-29 18:00","연속",null,null,null,201701250062]
[75,"충북","청주","신옥천신남원#1 T/L","신옥천S/S 345kV 차단기 용량대체공사","- 신설 GIS 74Bay #2BUS측으로 인출 변경 - 가선(인하선 연결) - 보호반 기설 케이블 철거 및 신설 케이블 결선 - 보호반관련 시험 및 연동시험","2017-03-22 09:00","2017-04-05 18:00","2017-03-22 09:00","2017-04-05 18:00","연속",null,null,null,201701250061]
[76,"충북","청주","신옥천S/S 345kV #2 BUS","345kV 신옥천S/S 차단기 용량대체공사","기설 71Bay #2BUS 철거작업","2017-03-22 13:00","2017-03-22 18:00","2017-03-22 13:00","2017-03-22 18:00","당일",null,null,null,201701250059]
[77,"충북","청주","세종청원#1 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","항공장애구 설치 28경간 (237개)","2017-03-02 08:00","2017-03-08 18:00","2017-03-02 08:00","2017-03-08 18:00","매일",null,null,null,201701170061]
[78,"충북","청주","세종청원#2 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","항공장애구 설치 28경간 (237개)","2017-03-09 08:00","2017-03-15 18:00","2017-03-24 08:00","2017-03-30 18:00","매일",null,null,null,201701170063]
[79,"충북","청주","청원신진천#2 T/L","피뢰기 설치공사","피뢰기 설치","2017-03-09 09:00","2017-03-21 18:00","2017-03-01 09:00","2017-03-09 18:00","연속",null,null,null,201701160066]
[80,"충북","충주","서안성신진천#1 T/L","2016~17년 충주 송전정비 협력회사 총액공사(피뢰기 설치)","송전선로용 피뢰기 설치 36기(1~35호)","2017-03-13 08:00","2017-03-20 18:00","2017-03-01 08:00","2017-03-09 18:00","매일",null,null,null,201701030161]
[81,"충북","충주","신진천S/S 345kV #2 BUS","345kV 신진천S/S 용량부족 GIS 대체공사","345kV 신진천S/S GIS 40kA 4000A → 63kA 6300A 12CB 대체 - 345kV #2BUS 모선대체(약 56m) 및 7652DS 교체 - 7152, 7352 DS(수직절) 설치(7651, 7652 DS 철거분 활용)","2017-03-08 09:00","2017-04-05 18:00","2017-03-10 09:00","2017-04-07 18:00","연속",null,null,null,201612260080]
[82,"대전충남","서산","신당진S/S 345kV #70 BUS","신당진변전소 345kV GIS 모선 변형 보강공사","신당진변전소 345kV GIS 모선(70,75BUS) 변형 - 70BUS(74-75BAY간) X 1개소 - 75BUS(73-74BAY간, 75-76BAY간) X 각 1개소","2017-03-20 09:00","2017-03-22 18:00","2017-03-20 09:00","2017-03-22 18:00","당일",null,null,null,201701060074]
[83,"대전충남","서산","신당진-신당진개폐소#1T/L","신당진변전소 345kV GIS 모선 변형 보강공사","신당진변전소 345kV GIS 모선(70,75BUS) 변형 - 70BUS(74-75BAY간) X 1개소 - 75BUS(73-74BAY간, 75-76BAY간) X 각 1개소","2017-03-20 09:00","2017-03-22 18:00","2017-03-20 09:00","2017-03-22 18:00","당일",null,null,null,201701060072]
[84,"대전충남","서산","신당진S/S 345kV #75 BUS","신당진변전소 345kV GIS 모선 변형 보강공사","신당진변전소 345kV GIS 모선(70,75BUS) 변형 - 70BUS(74-75BAY간) X 1개소 - 75BUS(73-74BAY간, 75-76BAY간) X 각 1개소","2017-03-28 09:00","2017-03-30 18:00","2017-03-28 09:00","2017-03-30 18:00","당일",null,null,null,201701060076]
[85,"대전충남","서산","태안T/P 6호기 1차 CB (7672)","태안T/P 345kV GIS(7600) 보통점검","○ 태안T/P 345kV 개폐소태안TP#1TL - 6호기1차 GIS(7600) 보통점검","2017-03-08 09:00","2017-03-08 18:00","2017-03-08 09:00","2017-03-08 18:00","당일",null,null,null,201701170238]
[86,"대전충남","서산","태안T/P 6호기 1차 CB (7672)","태안T/P 345kV 6호기 1차(7672) GIS 보통점검","○ 태안T/P 345kV 6호기 1차(7672) GIS 보통점검","2017-03-07 09:00","2017-03-07 18:00","2017-03-07 09:00","2017-03-07 18:00","당일",null,null,null,201701170237]
[87,"대전충남","세종","세종S/S #3 M.Tr A","[변전] 세종P/O 협력회사 총액공사 외 1건","○ M.Tr A,B,C상 초기점검 ○ 7472,6344 CB GIS초기점검 ○ 3차 LA촉점검 ○ B상 상부 누유 확인 및 보수(16.06.29 발견) ○ 계전기 성능개선공사","2017-03-09 09:00","2017-03-10 18:00","2017-03-09 09:00","2017-03-10 18:00","연속",null,null,null,201701030011]
[88,"대전충남","세종","세종S/S #2 M.Tr A","[변전] 세종P/O 협력회사 총액공사 외 1건","○ M.Tr A,B,C상 초기점검 ○ 7372,6244,4189 CB GIS초기점검 ○ 3차 LA초기점검 ○ A상 OFU 하부 소량누유개소 확인 및 보수(16.05.12 발견) ○ 계전기 성능개선공사","2017-03-02 09:00","2017-03-03 18:00","2017-03-02 09:00","2017-03-03 18:00","연속",null,null,null,201701030010]
[89,"대전충남","세종","세종청원#1 T/L","[변전] 세종P/O 협력회사 총액공사","○ 7571, 7500 CB GIS초기점검","2017-03-13 09:00","2017-03-13 18:00","2017-03-13 09:00","2017-03-13 18:00","당일",null,null,null,201701160098]
[90,"대전충남","아산","신온양S/S 청양-신온양 #2 T/L - TIE CB (7600)","신온양S/S 345kV BUS-TIE 7600 GIS 보통점검","○ 345kV BUS-TIE 7600 GIS 보통 점검","2017-03-10 09:00","2017-03-10 18:00","2017-03-10 09:00","2017-03-10 18:00","연속",null,null,null,201701160088]
[91,"대전충남","아산","신온양S/S #4 M.Tr A","신온양S/S 345kV #4M.Tr 보통점검","○ 345kV #4M.Tr 보통점검 ○ 병행) 345kV #4M.Tr 1차 7772 GIS 보통점검 및 1, 2차 피뢰기 보통점검","2017-03-27 09:00","2017-03-28 18:00","2017-03-27 09:00","2017-03-28 18:00","연속",null,null,null,201701160086]
[92,"대전충남","아산","신탕정S/S 345kV #1 BUS","신탕정S/S 362kV 용량부족 GIS 대체공사","신탕정S/S 345kV 72Bay GIS 대체(50KA→63KA)","2017-03-22 10:00","2017-04-02 18:00","2017-03-22 10:00","2017-04-02 18:00","당일",null,null,null,201701170207]
[93,"대전충남","아산","신탕정S/S 345kV #2 BUS","신탕정S/S 362kV 용량부족 GIS 대체공사","신탕정S/S 345kV 72Bay GIS 대체(50KA→63KA)","2017-03-02 10:00","2017-03-21 18:00","2017-03-02 10:00","2017-03-21 18:00","당일",null,null,null,201701170205]
[94,"대전충남","아산","신탕정S/S #2 M.Tr A","신탕정S/S 362kV 용량부족 GIS 대체공사","○ 345kV 72BAY GIS 용량부족 대체 ○ 기타 부대작업- (50kA 4,000A)×3CB 철거 및 362kV GIS(63kA 6,300A)×3CB 설치공사","2017-03-02 10:00","2017-04-18 18:00","2017-03-02 10:00","2017-04-18 18:00","당일",null,null,null,201701170204]
[95,"대전충남","아산","신서산아산#1 T/L","345kV 신서산-아산T/L 소도체 이도조정공사","345kV 신서산-아산T/L 소도체 이도조정공사","2017-03-25 07:00","2017-03-27 18:00","2017-03-25 07:00","2017-03-27 18:00","연속",null,null,null,201701170111]
[96,"대전충남","아산","아산S/S #3 M.Tr A","아산S/S 345kV #3M.Tr 초기점검","○ 345kV #3M.Tr 초기점검 ○ 병행) 345kV #3M.Tr 1차 7772 GIS 초기점검 및 1, 2차 LA 초기점검 ○ 병행) 345kV 7700 GIS 초기점검 및 #3M.Tr 3차 PT 초기점검","2017-03-13 09:00","2017-03-14 18:00","2017-03-13 09:00","2017-03-14 18:00","연속",null,null,null,201701160089]
[97,"대전충남","아산","신서산아산#2 T/L","345kV 신서산-아산T/L 소도체 이도조정공사","345kV 신서산-아산T/L 소도체 이도조정공사","2017-03-31 07:00","2017-04-02 18:00","2017-03-31 07:00","2017-04-02 18:00","연속",null,null,null,201701170112]
[98,"전북","군산","청양군산#1 T/L","청양군산T/L 전선접속개소교체공사","전선교체(5~7,13~14,24~25,52~55)","2017-03-20 07:00","2017-04-03 18:00","2017-03-20 07:00","2017-04-03 18:00","연속",null,null,null,201701180074]
[99,"전북","김제","신김제S/S #3 M.Tr A","신김제S/S #3 M.Tr A","76Bay B/F 보호반 교체","2017-03-13 09:00","2017-03-17 18:00","2017-03-13 09:00","2017-03-17 18:00","연속",null,null,null,201611160101]
[100,"전북","김제","신김제S/S 신김제한빛NP#2T/L-TIE CB (7400)","장기 미동작 차단기 특별점검","차단기 동작특성 시험","2017-03-06 09:00","2017-03-06 12:00","2017-03-06 09:00","2017-03-06 12:00","당일",null,null,null,201701180204]
[101,"전북","김제","신김제S/S 신김제-한빛NP#2T/L CB (7471)","장기 미동작 차단기 특별점검","차단기 동작특성 시험","2017-03-06 14:00","2017-03-06 16:00","2017-03-06 14:00","2017-03-06 16:00","당일",null,null,null,201701180205]
[102,"전북","직할","신남원신광주#1 T/L","345kV 신남원S/S M.Tr 설치공사","345kV M.Tr 166.7MVA×4대 설치공사 가공지선설치 안전이격확보","2017-03-06 08:00","2017-03-06 18:00","2017-03-06 08:00","2017-03-06 18:00","당일",null,null,null,201701120027]
[103,"광주전남","강진","신강진S/S #1 M.Tr A","신강진S/S 345kV #1M.Tr(2차 차단기 보통점검)","2016~17년도 강진전력지사 변전협력회사 총액공사 - 17. 3. 1~2 : 신강진S/S #1M.Tr 차단기 보통점검,피뢰기 하자점검 75BAY 과부하경보설비 구축","2017-03-02 09:00","2017-03-03 18:00","2017-03-02 09:00","2017-03-03 18:00","당일",null,null,null,201701040153]
[104,"광주전남","강진","신강진S/S #3 M.Tr A","신강진S/S #3 M.Tr (#3M.Tr 정밀점검공사)","신강진S/S 3M.Tr 및 OLTC 정밀점검공사 - #3M.Tr 정밀점검공사","2017-03-06 09:00","2017-03-17 18:00","2017-03-06 09:00","2017-03-17 18:00","당일",null,null,null,201701020008]
[105,"광주전남","광주","신광주신화순#2 T/L","345kV 신광주-신화순T/L 전선접속개소해소공사","신광주-신화순T/L No.24~27, 65~71호 전선교체","2017-03-27 07:00","2017-03-31 18:00","2017-03-27 07:00","2017-03-31 18:00","연속",null,null,null,201701160092]
[106,"광주전남","광주","신광주S/S #1 M.Tr(예비) CB","신광주S/S #1 M.Tr(예비)(변전협력회사공사)","예비M.Tr 보통점검","2017-03-02 09:00","2017-03-02 18:00","2017-03-02 09:00","2017-03-02 18:00","당일",null,null,null,201701150003]
[107,"광주전남","광주","신광주S/S 한빛NP-신광주#2T/L-TIE CB(신) (7200)","신광주 345kV 신광주-한빛NP#2T/L-TIE 7200 CB 정밀점검","신광주 345kV 신광주-한빛NP#2T/L-TIE 7200 CB 정밀점검","2017-03-14 09:00","2017-03-17 18:00","2017-03-14 09:00","2017-03-17 18:00","연속",null,null,null,201701090034]
[108,"광주전남","광주","신남원신광주#2 T/L","신광주S/S 345kV 신남원-신광주#2T/L 7371,7300정밀점검","신광주S/S 345kV 신남원-신광주#2T/L 7371,7300 GIS 정밀점검","2017-03-20 09:00","2017-03-25 18:00","2017-03-20 09:00","2017-03-25 18:00","연속",null,null,null,201701160014]
[109,"광주전남","광주","신광주신화순#1 T/L","345kV 신광주-신화순T/L 전선접속개소해소공사","신광주-신화순T/L No.24~27, 65~71호 전선교체","2017-03-21 07:00","2017-03-25 18:00","2017-03-21 07:00","2017-03-25 18:00","연속",null,null,null,201701160090]
[110,"광주전남","광주","신광주S/S #2 M.Tr 1차 CB(신) (7472)","신광주 345kV #2 M.Tr 1차 CB(7472) 정밀점검","신광주 345kV #2 M.Tr 1차 CB(7472) 정밀점검","2017-03-27 09:00","2017-03-30 18:00","2017-03-27 09:00","2017-03-30 18:00","연속",null,null,null,201701160020]
[111,"광주전남","광주","신화순S/S #1 M.Tr(예비) CB","신화순S/S #1 M.Tr(예비)(변전협력회사공사)","예비M.Tr 보통점검","2017-03-10 09:00","2017-03-10 18:00","2017-03-10 09:00","2017-03-10 18:00","연속",null,null,null,201701150007]
[112,"광주전남","광주","신화순S/S #1 M.Tr A","신화순S/S #1 M.Tr(변전협력회사공사)","#1M.Tr 보통점검","2017-03-06 09:00","2017-03-07 18:00","2017-03-06 09:00","2017-03-07 18:00","연속",null,null,null,201701150004]
[113,"광주전남","광주","신화순S/S #2 M.Tr A","신화순S/S #2 M.Tr(변전협력회사공사)","#2M.Tr 보통점검","2017-03-08 09:00","2017-03-09 18:00","2017-03-08 09:00","2017-03-09 18:00","연속",null,null,null,201701150005]
[114,"광주전남","목포","한빛2NP-한빛3NP #4T/L","한빛-연락#4T/L(보호배전반대체)","7D B/F PNL 대체","2017-03-07 09:00","2017-03-13 18:00","2017-03-07 09:00","2017-03-13 18:00","당일",null,null,null,201612230006]
[115,"광주전남","목포","한빛3N/P 345kV #1BUS","한빛3N/P 345kV #1BUS(보호배전반대체)","7B B/F PNL대체","2017-03-02 13:00","2017-03-02 18:00","2017-03-02 13:00","2017-03-02 18:00","당일",null,null,null,201612230008]
[116,"광주전남","목포","한빛3N/P 345kV #1BUS","한빛3N/P 345kV #1BUS(보호배전반대체)","7D B/F PNL대체","2017-03-10 13:00","2017-03-10 18:00","2017-03-10 13:00","2017-03-10 18:00","당일",null,null,null,201612230009]
[117,"광주전남","목포","한빛3N/P 345kV #2BUS","한빛3N/P 345kV #2BUS(보호배전반대체)","7D B/F PNL대체","2017-03-10 09:00","2017-03-10 13:00","2017-03-10 09:00","2017-03-10 13:00","당일",null,null,null,201612230010]
[118,"광주전남","목포","한빛3N/P 345kV #2BUS","한빛3N/P 345kV #2BUS(보호배전반대체)","7B B/F PNL대체","2017-03-02 09:00","2017-03-02 13:00","2017-03-02 09:00","2017-03-02 13:00","당일",null,null,null,201612230007]
[119,"광주전남","순천","신남원광양#1 T/L","345kV 광양S/S 362kV GIS 대체공사","가. GIS(345kV 50kA 4000A) ×27 CB 철거 나. GIS(345kV 63kA 6300A) ×27 CB 설치 다. 기타 부대작업 × 1식","2017-03-10 10:00","2017-06-12 18:00","2017-03-10 10:00","2017-06-12 18:00","연속",null,null,null,201701170024]
[120,"광주전남","순천","광양S/S #1 M.Tr A","345kV 광양S/S #1M.Tr(2차 LA A,B,C상 교체)","2016~17년 순천전력지사 변전협력회사 총액공사 - #1M.Tr 2차 LA A,B,C상 교체","2017-03-07 10:00","2017-03-07 18:00","2017-03-07 10:00","2017-03-07 18:00","연속",null,null,null,201612120061]
[121,"광주전남","순천","광양S/S 345kV #75 BUS","345kV 광양S/S 362kV GIS 대체공사","가. GIS(345kV 50kA 4000A) ×27 CB 철거 나. GIS(345kV 63kA 6300A) ×27 CB 설치 다. 기타 부대작업 × 1식","2017-03-06 10:00","2017-03-09 18:00","2017-03-06 10:00","2017-03-09 18:00","연속",null,null,null,201701170041]
[122,"광주전남","순천","신남원광양#2 T/L","2016~17년 송전정비협력회사 총액공사","신남원-광양T/L No.205~208호 전선교체","2017-03-05 07:00","2017-03-09 18:00","2017-03-05 07:00","2017-03-09 18:00","연속",null,null,null,201701190096]
[123,"광주전남","순천","여수T/P #3 Tie-Tr","345kV 여수화력S/Y #3M.Tr (보호반 계전기 성능개선)","345kV 여수화력S/Y #3M.Tr (보호반 계전기 성능개선)","2017-03-06 09:00","2017-03-06 18:00","2017-03-06 09:00","2017-03-06 18:00","당일",null,null,null,201611110296]
[124,"대구경북","경산","신경산S/S #1 M.Tr A","신경산S/S #1M.Tr 휴전","#1M.Tr A 상 Bushing 교체","2017-03-14 09:00","2017-03-16 18:00","2017-03-14 09:00","2017-03-16 18:00","연속",null,null,null,201701040141]
[125,"대구경북","경산","신경산S/S #4 M.Tr A","신경산S/S #4M.Tr 휴전","옥외분전반 교체 및 누유보수","2017-03-21 09:00","2017-03-23 18:00","2017-03-21 09:00","2017-03-23 18:00","연속",null,null,null,201701050095]
[126,"대구경북","경산","신경산S/S #3 M.Tr A","'17년 신경산S/S 170kV 장기사용 GIS 대체공사","#62M.Tr 1차 GIS 대체 안전이격 확보","2017-03-30 09:00","2017-03-30 18:00","2017-03-30 09:00","2017-03-30 18:00","당일",null,null,null,201701170046]
[127,"대구경북","경산","신경산S/S #4 M.Tr A","신경산S/S 345kV #4M.Tr 휴전","신경산S/S #62-67 BUS PRO 교체공사 관련 준공시험","2017-03-08 16:00","2017-03-08 16:30","2017-03-08 16:00","2017-03-08 16:30","당일",null,null,null,201701100151]
[128,"대구경북","칠곡","서대구S/S 북대구서대구#1T/L CB (7871)","서대구S/S 362kV GCB 정밀점검공사","서대구S/S 북대구-서대구#1T/L CB(7871) 정밀점검","2017-03-30 09:00","2017-04-01 18:00","2017-03-30 09:00","2017-04-01 18:00","연속",null,null,null,201701050040]
[129,"대구경북","칠곡","서대구S/S 북대구서대구#2T/L CB (7772)","서대구S/S 362kV GCB 정밀점검공사","서대구S/S 북대구-서대구#2T/L CB(7772) 정밀점검","2017-03-27 09:00","2017-03-29 18:00","2017-03-27 09:00","2017-03-29 18:00","연속",null,null,null,201701050034]
[130,"대구경북","칠곡","서대구S/S #4 M.Tr A","서대구S/S #4M.Tr 정밀점검","서대구S/S #4M.Tr 정밀점검","2017-03-13 09:00","2017-03-19 18:00","2017-03-13 09:00","2017-03-19 18:00","연속",null,null,null,201701040193]
[131,"대구경북","칠곡","서대구S/S #2 M.Tr A","서대구S/S #2M.Tr 정밀점검","서대구S/S #2M.Tr 정밀점검","2017-03-06 09:00","2017-03-12 18:00","2017-03-06 09:00","2017-03-12 18:00","연속",null,null,null,201701040192]
[132,"대구경북","포항","신영일S/S #3예비M.Tr CB","신영일S/S 예비M.Tr, 3차 LA 보통점검","신영일S/S 예비M.Tr, 3차 LA 보통점검","2017-03-16 09:00","2017-03-16 18:00","2017-03-16 09:00","2017-03-16 18:00","당일",null,null,null,201610070313]
[133,"대구경북","포항","신포항신월성NP#4 T/L","신월성S/Y 신포항-신월성NP #4T/L 애자코팅","신월성S/Y 신포항-신월성NP #4T/L 인출부싱, CVT 애자코팅","2017-03-15 09:30","2017-03-16 18:00","2017-03-15 09:30","2017-03-16 18:00","연속",null,null,null,201701100432]
[134,"대구경북","포항","월성2N/P #3 M.Tr 2차 CB (7572)","월성S/Y 7500, 7572 차단기 정밀점검","월성S/Y 7500, 7572 차단기 정밀점검","2017-03-13 09:30","2017-03-17 18:00","2017-03-13 09:30","2017-03-17 18:00","연속",null,null,null,201701090070]
[135,"대구경북","포항","동울산월성NP#1 T/L","월성S/Y 동울산-월성NP #1T/L 인출부싱 애자코팅","월성S/Y 동울산-월성NP #1T/L 인출부싱 애자코팅","2017-03-14 09:30","2017-03-14 18:00","2017-03-14 09:30","2017-03-14 18:00","당일",null,null,null,201701090069,"○"]
[136,"대구경북","포항","월성2N/P 월성#1T/L-#3 M.Tr 2차 CB (7500)","월성S/Y 7500, 7572 차단기 정밀점검","월성S/Y 7500, 7572 차단기 정밀점검","2017-03-13 09:30","2017-03-17 18:00","2017-03-13 09:30","2017-03-17 18:00","연속",null,null,null,201701090072]
[137,"부산울산","동부산","신양산북부산#2 T/L","신양산S/S 345kV CVT 대체","1. 신양산 345kV 신양산-북부산#2T/L CVT 대체 2. 신양산 7371,7300GIS 보통점검","2017-03-22 09:30","2017-03-23 17:00","2017-03-22 09:30","2017-03-23 17:00","연속",null,null,null,201701100294]
[138,"부산울산","동부산","신양산북부산#1 T/L","신양산S/S 345kV CVT 대체","1. 신양산 345kV 신양산-북부산#1T/L CVT 대체 2. 신양산 7471,7400GIS 보통점검","2017-03-20 09:30","2017-03-21 17:00","2017-03-20 09:30","2017-03-21 17:00","연속",null,null,null,201701100290]
[139,"부산울산","동부산","신양산S/S #1 M.Tr A","신양산S/S #1M.Tr 관련 노후설비 대체","1. 신양산 #1M.Tr 1,2차 LA 대체 2. 옥외 #1M.Tr DC판넬 대체","2017-03-15 09:30","2017-03-17 17:00","2017-03-15 09:30","2017-03-17 17:00","연속",null,null,null,201701100286]
[140,"부산울산","울산","신온산S/S #1 M.Tr 1차 CB (7272)","2016-17년도 울산전력지사 변전협력회사 총액공사","신온산S/S 7272 GIS 보통점검","2017-03-10 09:00","2017-03-10 18:00","2017-03-10 09:00","2017-03-10 18:00","당일",null,null,null,201701100175]
[141,"부산울산","울산","신온산울산TP T/L","선도제 송전선로보호반 내부통신회로 개선","신온산S/S, 울산T/P 신온산울산TPT/L 선도제 송전선로보호반 내부통신회로 개선","2017-03-25 09:00","2017-03-25 18:00","2017-03-25 09:00","2017-03-25 18:00","당일",null,null,null,201701060229]
[142,"부산울산","울산","신온산S/S #1 M.Tr 1차-TIE CB (7200)","2016-17년도 울산전력지사 변전협력회사 총액공사","신온산S/S 7200 GIS 보통점검","2017-03-09 09:00","2017-03-09 18:00","2017-03-09 09:00","2017-03-09 18:00","당일",null,null,null,201701100173]
[143,"부산울산","울산","신온산S/S #2 M.Tr 1차 CB (7472)","2016-17년도 울산전력지사 변전협력회사 총액공사","신온산S/S 7472 GIS 보통점검","2017-03-14 09:00","2017-03-14 18:00","2017-03-14 09:00","2017-03-14 18:00","당일",null,null,null,201701100176]
[144,"부산울산","울산","신울산S/S 신울산-고리NP#2T/L CB (7372)","2016-17년도 울산전력지사 변전협력회사 총액공사","신울산S/S 7372 GIS 보통점검","2017-03-16 09:00","2017-03-16 18:00","2017-03-16 09:00","2017-03-16 18:00","당일",null,null,null,201701100187]
[145,"부산울산","울산","신울산S/S #2M.Tr 1차 CB (7371)","2016-17년도 울산전력지사 변전협력회사 총액공사","신울산S/S 7371 GIS 보통점검","2017-03-15 09:00","2017-03-15 18:00","2017-03-15 09:00","2017-03-15 18:00","당일",null,null,null,201701100178]
[146,"부산울산","울산","울산C/C #3 M.Tr A","울산복합화력 차단 고장파급방지시스템 회로구성","울산복합 345kV #3M.Tr 과부하 방지 차단회로 구성 M.Tr 및 1차 GIS 하자점검","2017-03-04 09:00","2017-03-05 18:00","2017-03-04 09:00","2017-03-05 18:00","연속",null,null,null,201701060231]
[147,"부산울산","울산","울주S/S #4 M.Tr 1차 CB (7872)","2016-17년도 울산전력지사 변전협력회사 총액공사","울주S/S 7872 GIS 보통점검","2017-03-22 09:00","2017-03-22 18:00","2017-03-22 09:00","2017-03-22 18:00","당일",null,null,null,201701100183]
[148,"부산울산","울산","울주S/S 울주-월성NP#2T/L-TIE CB (7A00)","2016-17년도 울산전력지사 변전협력회사 총액공사","울주S/S 7A00 GIS 보통점검","2017-03-23 09:00","2017-03-23 18:00","2017-03-23 09:00","2017-03-23 18:00","당일",null,null,null,201701100185]
[149,"경남","진주","광양하동화력#2 T/L","하동화력 345kV 광양-하동화력#2T/L PNL 대체","하동화력 345kV 광양-하동화력#2T/L PNL 대체 광양-하동화력#2(A,B,C) PT하자점검[병행작업]","2017-03-27 09:30","2017-04-04 18:30","2017-03-27 09:30","2017-04-04 18:30","연속",null,null,null,201701060216]
[150,"경남","통영","신고성S/S #3 M.Tr A","345kV 신고성S/S 23kV Sh.R 설치공사","이설분 #1S.Tr 설치","2017-03-27 09:00","2017-03-31 18:00","2017-03-27 09:00","2017-03-31 18:00","연속",null,null,null,201701100019]
[151,"경남","통영","신고성S/S #1 M.Tr A","345kV 신고성S/S 23kV Sh.R 설치공사","23kV 30Mvar 2Bank 설치, #1S.Tr 이설","2017-03-20 09:00","2017-03-24 18:00","2017-03-20 09:00","2017-03-24 18:00","연속",null,null,null,201701100018]
[152,"경남","함안","북경남S/S #6 Sh.R","북경남S/S #6Sh.R 송유펌프 누유보수","북경남S/S #6Sh.R 송유펌프 누유보수 - 송유펌프 교체","2017-03-02 09:30","2017-03-03 17:30","2017-03-02 09:30","2017-03-03 17:30","연속",null,null,null,201701100239]
[153,"인천","가정","가정개폐소 #2 Sh.R","#2Sh.R 내부진동 및 내부 가스 발생에 따른 긴급 하자보수","#2Sh.R 내부진동 및 내부 가스 발생에 따른 긴급 하자보수","2017-03-02 10:00","2017-06-20 18:00","2017-03-02 10:00","2017-06-20 18:00","연속",null,null,null,201701100239]

{"sheet":"154송부","index":2,"n_rows":276,"n_cols":16,"rows_kept":276,"cut":false,"hidden":false,"merged":[[104,13,105,13],[174,13,175,13],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 3월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","옥인S/S 154kV #1 BUS","화양 및 세종로S/S 인출선로 선종교체공사","1. 관련공사 : 화양 및 세종로S/S 인출선로 선종교체공사 2. 공사개요 : 세종로옥인#1T/L 1구간 선종교체(OF→XLPE) 3. 휴전사유 : 세종로옥인#1T/L 최초가압시 옥인S/S 단모선 운전 중 운니, 원남S/S Radial 해소","2017-03-29 10:00","2017-03-29 15:00","2017-03-29T10:00:00","2017-03-29T15:00:00","당일",null,null,null,201701260161,"-"]
[2,"남서울","강남","신사논현#1 T/L","154kV 신사-논일 지중T/L 건설공사","1. 구간 : 기설 154kV 신사논현T/L 분기점~154kV 논일S/S 2. 선종/회선길이 : XLPE2000, 2C-1.7km 3. 공사기간 : 2016.12 ~ 2017. 09 (10개월) 4. 준공목표 : 2017. 04","2017-03-09 09:00","2017-03-27 18:00","취소","취소","당일",null,null,"신뢰도개선",201701090263,"-"]
[3,"남서울","강남","역삼대치#1 T/L","154kV 논일-역삼, 논현-대치 지중T/L 건설공사","1. 구간 : 154kV 논일S/S, 논현S/S~기설 154kV 역삼대치T/L 분기점 2. 선종/회선길이 : XLPE1200, 2C-3.7km(논일-역삼),2C-3km(논현-대치) 3. 공사기간 : 2016.10 ~ 2017. 10 (12개월) 4. 준공목표 : 2017. 04","2017-03-01 09:00","2017-03-30 18:00","취소","취소","연속",null,null,"신뢰도개선",201701090260,"-"]
[4,"남서울","동서울","강남-대치#1 T/L","삼성S/S OF 송전선로 이설 및 선종교체공사","강남변전소 신설에 따른 송전선로 이설 및 선종교체","2017-03-02 09:00","2017-05-15 18:00","2017-03-02T09:00:00","2017-06-10T18:00:00","연속",null,null,null,201701120016,"-"]
[5,"남서울","동서울","강남-대치#2 T/L","삼성S/S OF 송전선로 이설 및 선종교체공사","강남S/S 신설에 따른 송전선로 이설 및 선종교체","2017-03-02 09:00","2017-05-15 18:00","2017-03-02T09:00:00","2017-06-10T18:00:00","연속",null,null,null,201701120017,"-"]
[6,"남서울","동서울","동서울가락#1 T/L","170kV GCB 정밀점검","동서울가락#1 T/L 170kV GCB 정밀점검","2017-03-27 09:00","2017-03-29 18:00","2017-03-27T09:00:00","2017-03-29T18:00:00","연속",null,null,null,201701180113,"-"]
[7,"남서울","동서울","동서울신장#1 T/L","345kV 신성남-동서울T/L 전선접속개소 전선교체공사","154kV동서울-신장#1T/L 전선교체공사 내용 : #1T/L No.7-8간 중단 전선접속개소 전선교체","2017-03-20 08:00","2017-03-22 18:00","2017-03-20T08:00:00","2017-03-22T18:00:00","연속",null,null,null,201701160108,"-"]
[8,"남서울","동서울","서종동서울#2 T/L","345kV 신성남-동서울T/L 전선접속개소 전선교체공사","154kV동서울-서종#2T/L 전선교체공사 내용 : - #2T/L No.77-79간 중하단 전선접속개소 전선교체 - #2T/L No.79-82간 상중하단 전선접속개소 전선교체","2017-03-13 08:00","2017-03-18 18:00","2017-03-13T08:00:00","2017-03-18T18:00:00","연속",null,null,null,201701130082,"-"]
[9,"남서울","동서울","서종동서울#1 T/L","345kV 신성남-동서울T/L 전선접속개소 전선교체공사","154kV동서울-서종#1T/L 전선교체공사 내용 : - #1T/L No.67-68간 중단 전선접속개소 전선교체 - #1T/L No.79-82간 상중하단 전선접속개소 전선교체","2017-03-06 08:00","2017-03-11 18:00","2017-03-06T08:00:00","2017-03-11T18:00:00","연속",null,null,null,201701130081,"-"]
[10,"남서울","영등포","가양S/S 154kV #2 BUS","영등포P/O 170kV GIS 정밀점검 공사(마곡-가양#1T/L)","- 170kV GIS 정밀점검(마곡-가양#1T/L) ※ 병행휴전작업 : GIS 보통점검 및 배전반 교체 등","2017-03-14 11:00","2017-03-15 18:00","2017-03-14T11:00:00","2017-03-15T18:00:00","연속",null,null,null,201701180009,"-"]
[11,"남서울","영등포","가양S/S 154kV #1 BUS","영등포P/O 170kV GIS 정밀점검 공사(마곡-가양#1T/L)","- 170kV GIS 정밀점검(마곡-가양#1T/L) ※ 병행휴전작업 : GIS 보통점검 및 배전반 교체 등","2017-03-13 09:00","2017-03-14 11:00","2017-03-13T09:00:00","2017-03-14T11:00:00","연속",null,null,null,201701180008,"-"]
[12,"남서울","영등포","가양S/S 154kV #1 BUS","영등포P/O 170kV GIS 정밀점검 공사(마곡-가양#2T/L)","- 170kV GIS 정밀점검(마곡-가양#2T/L) ※ 병행휴전작업 : GIS 보통점검 및 배전반 교체 등","2017-03-16 09:00","2017-03-17 11:00","2017-03-16T09:00:00","2017-03-17T11:00:00","연속",null,null,null,201701180010,"-"]
[13,"남서울","영등포","마곡가양#2 T/L","영등포P/O 170kV GIS 정밀점검 공사(마곡-가양#2T/L)","- 170kV GIS 정밀점검(마곡-가양#2T/L) ※ 병행휴전작업 : GIS 보통점검 또는 배전반 교체 등","2017-03-16 09:00","2017-03-18 18:00","2017-03-16T09:00:00","2017-03-18T18:00:00","연속",null,null,null,201701180002,"-"]
[14,"남서울","영등포","가양S/S 154kV #2 BUS","영등포P/O 170kV GIS 정밀점검 공사(마곡-가양#2T/L)","- 170kV GIS 정밀점검(마곡-가양#2T/L) ※ 병행휴전작업 : GIS 보통점검 및 배전반 교체 등","2017-03-17 11:00","2017-03-18 18:00","2017-03-17T11:00:00","2017-03-18T18:00:00","연속",null,null,null,201701180011,"-"]
[15,"남서울","영등포","마곡가양#1 T/L","영등포P/O 170kV GIS 정밀점검 공사(마곡-가양#1T/L)","- 170kV GIS 정밀점검(마곡-가양#1T/L) ※ 병행휴전작업 : GIS 보통점검 및 배전반 교체 등","2017-03-13 09:00","2017-03-15 18:00","2017-03-13T09:00:00","2017-03-15T18:00:00","연속",null,null,null,201701180001,"-"]
[16,"남서울","영등포","대방S/S 154kV #1 BUS","영등포P/O 170kV GIS 정밀점검 공사(독산-대방#1T/L)","- 170kV GIS 정밀점검(대방S/S 독산-대방#1T/L) ※ 병행휴전작업 : GIS 보통점검 또는 배전반 교체 등","2017-03-27 09:00","2017-03-28 11:00","2017-03-27T09:00:00","2017-03-28T11:00:00","연속",null,null,null,201701180016,"-"]
[17,"남서울","영등포","독산대방#1 T/L","영등포P/O 170kV GIS 정밀점검 공사(독산-대방#1T/L)","- 170kV GIS 정밀점검(대방S/S 독산-대방#1T/L) ※ 병행휴전작업 : GIS 보통점검 또는 배전반 교체 등","2017-03-27 09:00","2017-03-29 14:00","2017-03-27T09:00:00","2017-03-29T14:00:00","연속",null,null,null,201701180006,"-"]
[18,"남서울","영등포","대방S/S 154kV #2 BUS","영등포P/O 170kV GIS 정밀점검 공사(독산-대방#1T/L)","- 170kV GIS 정밀점검(대방S/S 독산-대방#1T/L) ※ 병행휴전작업 : GIS 보통점검 또는 배전반 교체 등","2017-03-28 11:00","2017-03-29 14:00","2017-03-28T11:00:00","2017-03-29T14:00:00","연속",null,null,null,201701180017,"-"]
[19,"남서울","영등포","독산대방#2 T/L","영등포P/O 170kV GIS 정밀점검 공사(독산-대방#2T/L)","- 170kV GIS 정밀점검(대방S/S 독산-대방#2T/L) ※ 병행휴전작업 : GIS 보통점검 또는 배전반 교체 등","2017-03-29 14:00","2017-03-31 18:00","2017-03-29T14:00:00","2017-03-31T18:00:00","연속",null,null,null,201701180007,"-"]
[20,"남서울","영등포","대방S/S 154kV #2 BUS","영등포P/O 170kV GIS 정밀점검 공사(독산-대방#2T/L)","- 170kV GIS 정밀점검(대방S/S 독산-대방#2T/L) ※ 병행휴전작업 : GIS 보통점검 또는 배전반 교체 등","2017-03-29 14:00","2017-03-30 14:00","2017-03-29T14:00:00","2017-03-30T14:00:00","연속",null,null,null,201701180018,"-"]
[21,"남서울","영등포","대방S/S 154kV #1 BUS","영등포P/O 170kV GIS 정밀점검 공사(독산-대방#2T/L)","- 170kV GIS 정밀점검(대방S/S 독산-대방#2T/L) ※ 병행휴전작업 : GIS 보통점검 또는 배전반 교체 등","2017-03-30 14:00","2017-03-31 18:00","2017-03-30T14:00:00","2017-03-31T18:00:00","연속",null,null,null,201701180019,"-"]
[22,"남서울","영등포","마곡가양#1 T/L","154kV마곡-가양T/L 지중선로 이설공사","1. 케이블철거 : 110m * 6상 2. 케이블설치 : 197m * 6t상 3. 케이블접속 : 2개소","2017-03-15 09:00","2017-04-06 18:00","2017-03-15T09:00:00","2017-04-06T18:00:00","연속",null,null,null,201701180115,"-"]
[23,"남서울","영등포","봉천신길#2 T/L","봉천,노들변전소 OF케이블 선종교체공사","케이블철거 및 설치 : OF케이블에서 XLPE로 교체(172m X 3상) 이종 및 종단 접속 : 2개소 X 3상 PT 이설 및 기타 부대작업","2017-03-20 09:00","2017-04-21 18:00","2017-03-20T09:00:00","2017-04-21T18:00:00","연속",null,null,null,201701190034,"-"]
[24,"남서울","영등포","영서시흥#2 T/L","17년 가공송전위탁공사(전력선부착 표시찰 설치공사)","1.내용 : 전력선부착 표시찰 설치공사","2017-03-22 13:00","2017-03-22 18:00","2017-03-22T13:00:00","2017-03-22T18:00:00","당일",null,null,null,201701180084,"-"]
[25,"남서울","영등포","영서시흥#1 T/L","17년 가공송전위탁공사(전력선부착 표시찰 설치공사)","1. 내용 : 전력선부착 표시찰 설치","2017-03-22 09:00","2017-03-22 13:00","2017-03-22T09:00:00","2017-03-22T13:00:00","당일",null,null,null,201701180079,"-"]
[26,"남서울","영등포","온수소래 T/L","17년 가공송전협력회사공사(송전선로용 피뢰기 설치공사)","1. 내용 : 송전선로용 피뢰기 설치 2. 장소 : 154kV 온수-소래T/L 소래C/H~No.22 3. 비고 : 154kV 서안양-소래T/L 작업안전 확보를 위한 병행휴전 요망 (4회선 철탑하단선로)","2017-03-06 09:00","2017-03-08 18:00","2017-03-06T09:00:00","2017-03-08T18:00:00","당일",null,null,null,201701180063,"-"]
[27,"남서울","직할","노들노량진 T/L","봉천,노들변전소 OF케이블 선종교체공사","케이블철거 및 설치 : OF케이블에서 XLPE로 교체(172m X 3상) 이종 및 종단 접속 : 2개소 X 3상 PT 이설 및 기타 부대작업","2017-03-20 09:00","2017-04-21 18:00","2017-03-20T09:00:00","2017-04-21T18:00:00","연속",null,null,null,201701190033,"-"]
[28,"남서울","직할","교대이수#1 T/L","154kV교대-이수T/L 지중선로 이설공사(방배 2공구)","1. 케이블철거 : 410m*6상 2. 케이블설치 : 410m*6상","2017-03-10 09:00","2017-03-25 18:00","취소","취소","연속",null,null,null,201701180119,"-"]
[29,"남서울","직할","교대이수#2 T/L","154kV교대-이수T/L 지중선로 이설공사(방배 2공구)","1. 케이블철거 : 410m*3상 2. 케이블설치 : 410m*3상 3. 접속개소 : 2개소","2017-03-26 09:00","2017-04-14 18:00","취소","취소","연속",null,null,null,201701180122,"-"]
[30,"인천","인천","주안관교#1 T/L","관교S/S 주안관교#1T/L GIS 보통점검 및 조작시험","관교S/S 주안관교#1T/L GIS 보통점검 및 조작시험 - 관교S/S 주안관교#1T/L GIS 보통점검 - 주안S/S 주안관교#1T/L GIS 조작시험","2017-03-07 09:00","2017-03-07 18:00","2017-03-07T09:00:00","2017-03-07T18:00:00","당일",null,null,null,201701130055,"-"]
[31,"인천","인천","관교만수 T/L","관교S/S 관교만수T/L GIS 보통점검","관교S/S 관교만수T/L GIS 보통점검 - 154kV 관교만수T/L GIS 보통점검","2017-03-09 09:00","2017-03-09 18:00","2017-03-09T09:00:00","2017-03-09T18:00:00","당일",null,null,null,201701130057,"-"]
[32,"인천","인천","주안관교#2 T/L","관교S/S 주안관교#2T/L GIS 보통점검 및 조작시험","관교S/S 주안관교#2T/L GIS 보통점검 및 조작시험 - 관교S/S 주안관교#2T/L GIS 보통점검 - 주안S/S 주안관교#2T/L GIS 조작시험","2017-03-08 09:00","2017-03-08 18:00","2017-03-08T09:00:00","2017-03-08T18:00:00","당일",null,null,null,201701130056,"-"]
[33,"인천","인천","경서북인천#2 T/L","북인천S/S 경서북인천#2T/L GIS 조작시험","북인천S/S 경서북인천#2T/L GIS 조작시험 - 154kV 경서북인천#2T/L GIS 조작시험","2017-03-10 09:00","2017-03-10 13:00","2017-03-10T09:00:00","2017-03-10T13:00:00","당일",null,null,null,201701130058,"-"]
[34,"인천","인천","계양북인천 T/L","북인천S/S 계양북인천T/L GIS 조작시험","북인천S/S 계양북인천T/L GIS 조작시험 - 154kV 계양북인천T/L GIS 조작시험","2017-03-10 13:00","2017-03-10 18:00","2017-03-10T13:00:00","2017-03-10T18:00:00","당일",null,null,null,201701130059,"-"]
[35,"인천","인천","신현송현#1 T/L","송현S/S 신현송현#1T/L GIS 보통점검공사","송현S/S 신현송현#1T/L GIS 보통점검공사 - 154kV 송현S/S 신현송현#1T/L GIS 보통점검","2017-03-14 09:00","2017-03-14 18:00","2017-03-14T09:00:00","2017-03-14T18:00:00","당일",null,null,null,201701130064,"-"]
[36,"인천","인천","신현송현#2 T/L","송현S/S 신현송현#2T/L GIS 보통점검공사","송현S/S 신현송현#2T/L GIS 보통점검공사 - 154kV 송현S/S 신현송현#2T/L GIS 보통점검","2017-03-15 09:00","2017-03-15 18:00","2017-03-15T09:00:00","2017-03-15T18:00:00","당일",null,null,null,201701130065,"-"]
[37,"인천","인천","신가좌S/S 66-67 SEC GIS","신가좌S/S 154kV 66-67 SEC GIS 보통점검공사","신가좌S/S 154kV 66-67 SEC GIS 보통점검공사 - 154kV 66-67 SEC GIS 보통점검공사","2017-03-24 09:00","2017-03-24 18:00","2017-03-24T09:00:00","2017-03-24T18:00:00","당일",null,null,null,201701130069,"-"]
[38,"인천","인천","신가좌S/S 61-62 SEC GIS","신가좌S/S 154kV 61-62 SEC GIS 보통점검공사","신가좌S/S 154kV 61-62 SEC GIS 보통점검공사 - 154kV 61-62 SEC GIS 보통점검공사","2017-03-23 09:00","2017-03-23 18:00","2017-03-23T09:00:00","2017-03-23T18:00:00","당일",null,null,null,201701130068,"-"]
[39,"인천","인천","신가좌S/S 154kV #2 BUS TIE GIS","신가좌S/S 154kV 6200BUS TIE GIS 보통점검공사","신가좌S/S 154kV 6200BUS TIE GIS 보통점검공사 - 154kV 6200BUS TIE GIS 보통점검공사","2017-03-21 09:00","2017-03-21 18:00","2017-03-21T09:00:00","2017-03-21T18:00:00","당일",null,null,null,201701130066,"-"]
[40,"인천","인천","신가좌S/S 154kV #3 BUS TIE GIS","신가좌S/S 154kV 6300BUS TIE GIS 보통점검공사","신가좌S/S 154kV 6300BUS TIE GIS 보통점검공사 - 154kV 6300BUS TIE GIS 보통점검공사","2017-03-22 09:00","2017-03-22 18:00","2017-03-22T09:00:00","2017-03-22T18:00:00","당일",null,null,null,201701130067,"-"]
[41,"인천","인천","신현포스코CC#1 T/L","154kV 신현-포스코CC T/L M/H#4~#5 지장이설공사","[한진중공업 시행] 인천북항 배후부지 항만구역 조성공사에 지장되는 지중송전설비 이설공사 필요 - 이설구간 : 154kV 신현-포스코CC #1T/L M/H #4~M/H #5 (약0.3km)","2017-03-20 09:00","2017-03-28 18:00","2017-03-20T09:00:00","2017-03-28T18:00:00","연속",null,null,null,201701130004,"-"]
[42,"인천","인천","신현포스코CC#2 T/L","154kV 신현-포스코CC T/L M/H#4~#5 지장이설공사","[한진중공업 시행] 인천북항 배후부지 항만구역 조성공사에 지장되는 지중송전설비 이설공사 필요 - 이설구간 : 154kV 신현-포스코CC #1T/L M/H #4~M/H #5 (약0.3km)","2017-03-30 09:00","2017-04-13 18:00","2017-03-30T09:00:00","2017-04-13T18:00:00","연속",null,null,null,201701130011,"-"]
[43,"인천","인천","신현S/S 154kV #1 BUS","154kV 신현-포스코CC #1T/L M/H#4~#5 지장이설공사","154kV 신현-포스코CC #1T/L 지장이설관련 상체크시험","2017-03-27 13:00","2017-03-27 18:00","2017-03-27T13:00:00","2017-03-27T18:00:00","당일",null,null,null,201701130013,"-"]
[44,"인천","인천","신가좌인천#1 T/L","신가좌S/S 신가좌인천#1T/L GIS 보통점검 및 보조계전기교체","신가좌S/S 154kV 신가좌인천#1T/L GIS 보통점검공사 - 154kV 신가좌인천#1T/L GIS 보통점검공사 - 154kV 신가좌인천#1T/L GIS 보조계전기 교체","2017-03-29 09:00","2017-03-29 18:00","2017-03-29T09:00:00","2017-03-29T18:00:00","당일",null,null,null,201701130070,"-"]
[45,"인천","김포","영종경서 T/L","경서S/S 영종경서#1T/L(637) GIS 장기미동작 차단기 점검","경서S/S 영종경서#1T/L(637) GIS 장기미동작 차단기 점검","2017-03-08 10:00","2017-03-08 16:00","2017-03-08T10:00:00","2017-03-08T16:00:00","당일",null,null,null,201701100165,"-"]
[46,"인천","김포","계양김포#2 T/L","김포S/S 계양-김포#2T/L(627) GIS 기기점검","김포S/S 계양-김포#2T/L(627) GIS 기기점검","2017-03-14 10:00","2017-03-14 18:00","2017-03-14T10:00:00","2017-03-14T18:00:00","당일",null,null,null,201701100369,"-"]
[47,"인천","김포","김포장기#1 T/L","김포S/S 김포-장기#1T/L(637) GIS 기기점검","김포S/S 김포-장기#1T/L(637) GIS 기기점검","2017-03-15 10:00","2017-03-15 18:00","2017-03-15T10:00:00","2017-03-15T18:00:00","당일",null,null,null,201701100376,"-"]
[48,"인천","김포","김포장기#2 T/L","김포S/S 김포-장기#2T/L(647) GIS 기기점검","김포S/S 김포-장기#2T/L(647) GIS 기기점검","2017-03-16 10:00","2017-03-16 18:00","2017-03-16T10:00:00","2017-03-16T18:00:00","당일",null,null,null,201701100379,"-"]
[49,"인천","김포","계양김포#1 T/L","김포S/S 계양-김포#1T/L(617) GIS 기기점검","김포S/S 계양-김포#1T/L(617) GIS 기기점검","2017-03-13 10:00","2017-03-13 18:00","2017-03-13T10:00:00","2017-03-13T18:00:00","당일",null,null,null,201701100367,"-"]
[50,"인천","김포","양촌양곡#2 T/L","양촌양곡#2T/L GIS 에어누기 보수","양촌양곡#2T/L GIS 에어누기 보수","2017-03-02 16:00","2017-03-02 18:00","2017-03-02T16:00:00","2017-03-02T18:00:00","당일",null,null,null,201701250096,"-"]
[51,"인천","시흥","서안양소래 T/L","17년 영등포전력지사 가공송전협력회사공사(송전선로용 피뢰기 설치공사)","1. 내용 : 송전선로용 피뢰기 설치 2. 장소 : 온수-소래T/L 3. 비고 : 작업안전을 위한 병행휴전(4회선 철탑 하단선로)","2017-03-06 09:00","2017-03-08 18:00","2017-03-06T09:00:00","2017-03-08T18:00:00","연속",null,null,null,201701180066,"-"]
[52,"인천","직할","계양원창 T/L","계양-원창T/L 차단부 접촉자 교체","계양-원창T/L 차단부 접촉자 교체","2017-03-22 09:30","2017-03-24 18:00","취소","취소","연속",null,null,null,201701030198,"-"]
[53,"인천","직할","중동화곡#2 T/L","154kV 신부평-중동#3T/L EBG 해체점검","154kV 신부평-중동#3T/L EBG 해체관련 크레인작업위한 병행휴전","2017-03-01 09:00","2017-03-01 14:00","2017-03-01T09:00:00","2017-03-01T14:00:00","당일",null,null,null,201701190042,"-"]
[54,"인천","직할","중동화곡#2 T/L","154kV 신부평-중동#3T/L EBG 해체점검","154kV 신부평-중동#3T/L EBG 해체관련 크레인작업위한 병행휴전","2017-03-05 14:00","2017-03-05 18:00","2017-03-05T14:00:00","2017-03-05T18:00:00","당일",null,null,null,201701190043,"-"]
[55,"인천","직할","신부평중동#3 T/L","154kV 신부평-중동#3T/L EBG 해체점검","EBG 가스분석결과 '이상'발생관련 154kV 신부평-중동#3T/L EBG 해체점검 및 SRC교체","2017-03-01 09:00","2017-03-05 18:00","2017-03-01T09:00:00","2017-03-05T18:00:00","연속",null,null,null,201701190037,"-"]
[56,"경기북부","구리","가평청평HP#2 T/L","154kV 가평-청평HP#2T/L 피뢰기 설치공사","ㅇ 피뢰기설치 - 대상 : No.2~7","2017-03-10 08:00","2017-03-11 18:00","2017-03-10T08:00:00","2017-03-11T18:00:00","연속",null,null,null,201701170175,"-"]
[57,"경기북부","구리","가평화천HP T/L","154kV 가평-청평HP T/L 피뢰기 설치관련 병가선로","ㅇ 피뢰기설치 - 대상 : No.2~7","2017-03-10 08:00","2017-03-11 18:00","2017-03-10T08:00:00","2017-03-11T18:00:00","연속",null,null,null,201701170182,"-"]
[58,"경기북부","구리","덕소마석#2 T/L","154kV 마석-청평HP#1T/L 피뢰기 설치공사 병가선로","ㅇ 피뢰기설치 - 대상 : 마석-청평HP#1T/L No.33,34,35","2017-03-08 09:00","2017-03-08 18:00","2017-03-08T09:00:00","2017-03-08T18:00:00","당일",null,null,null,201701170158,"○"]
[59,"경기북부","구리","덕소마석#1 T/L","170kV 덕소-마석 #1T/L GIS 보통점검","170kV 덕소-마석 #1T/L GIS 보통점검","2017-03-09 09:00","2017-03-09 18:00","2017-03-09T09:00:00","2017-03-09T18:00:00","당일",null,null,null,201701160169,"○"]
[60,"경기북부","구리","마석청평HP#2 T/L","154kV 덕소-마석#1T/L 피뢰기 설치공사 병가선로","ㅇ 피뢰기설치 - 대상 : 덕소-마석T/L No.1,2,3","2017-03-09 08:00","2017-03-09 18:00","2017-03-09T08:00:00","2017-03-09T18:00:00","당일",null,null,null,201701170155,"○"]
[61,"경기북부","구리","마석청평HP#1 T/L","170kV 마석-청평HP #1T/L GIS 보통점검","170kV 마석-청평HP #1T/L GIS 보통점검","2017-03-08 09:00","2017-03-08 18:00","2017-03-08T09:00:00","2017-03-08T18:00:00","당일",null,null,null,201701160170,"○"]
[62,"경기북부","구리","덕소별내#1 T/L","170kV 덕소-별내 #1T/L GIS 보통점검","170kV 덕소-별내 #1T/L GIS 보통점검","2017-03-06 09:00","2017-03-06 18:00","2017-03-06T09:00:00","2017-03-06T18:00:00","당일",null,null,null,201701160171,"○"]
[63,"경기북부","구리","덕소별내#2 T/L","170kV 덕소-별내 #2T/L GIS 보통점검","170kV 덕소-별내 #2/L GIS 보통점검","2017-03-07 09:00","2017-03-07 18:00","2017-03-07T09:00:00","2017-03-07T18:00:00","당일",null,null,null,201701160172,"○"]
[64,"경기북부","구리","신포천전곡#2 T/L","170kV 신포천-전곡 #2T/L GIS 보통점검","170kV 신포천-전곡 #2T/L GIS 보통점검","2017-03-21 10:00","2017-03-21 18:00","2017-03-21T10:00:00","2017-03-21T18:00:00","당일",null,null,null,201701160180,"○"]
[65,"경기북부","구리","신포천전곡#1 T/L","170kV 신포천-전곡 #1T/L GIS 보통점검","170kV 신포천-전곡 #1T/L GIS 보통점검","2017-03-22 09:00","2017-03-22 18:00","2017-03-22T09:00:00","2017-03-22T18:00:00","당일",null,null,null,201701160179,"○"]
[66,"경기북부","구리","신포천S/S 154kV #1 BUS TIE CB","신포천S/S 170kV #1BUSTIE GIS 보통점검","신포천S/S 170kV 1BUSTIE GIS 보통점검","2017-03-23 09:00","2017-03-23 18:00","2017-03-23T09:00:00","2017-03-23T18:00:00","당일",null,null,null,201701020080,"-"]
[67,"경기북부","구리","신포천S/S 154kV #2 BUS TIE CB","신포천S/S 170kV #2BUSTIE GIS 보통점검","신포천S/S 170kV 2BUSTIE GIS 보통점검","2017-03-24 09:00","2017-03-24 18:00","2017-03-24T09:00:00","2017-03-24T18:00:00","당일",null,null,null,201701020081,"○"]
[68,"경기북부","구리","신포천S/S 65-66-0 CB","신포천S/S 170kV 65-66SEC GIS 보통점검","신포천S/S 170kV 65-66SEC GIS 보통점검","2017-03-30 09:00","2017-03-30 18:00","2017-03-30T09:00:00","2017-03-30T18:00:00","당일",null,null,null,201701020079,"-"]
[69,"경기북부","구리","신포천S/S 60-61-0 CB","신포천S/S 170kV 60-61SEC GIS 보통점검","신포천S/S 170kV 60-61SEC GIS 보통점검","2017-03-27 09:00","2017-03-27 18:00","2017-03-27T09:00:00","2017-03-27T18:00:00","당일",null,null,null,201701020078,"-"]
[70,"경기북부","구리","운천철원#2 T/L","'17년도 가공송전 순시점검 위탁공사(정밀점검)","154kV 운천철원#2T/L 정밀점검 시행(No.1~67호)","2017-03-20 08:00","2017-03-25 18:00","2017-03-20T08:00:00","2017-03-25T18:00:00","연속",null,null,null,201701170086,"○"]
[71,"경기북부","구리","운천철원#1 T/L","'17년도 가공송전 순시점검 위탁공사(정밀점검)","154kV 운천철원#1T/L 정밀점검 시행(No.1~67호)","2017-03-26 08:00","2017-03-31 18:00","2017-03-26T08:00:00","2017-03-31T18:00:00","연속",null,null,null,201701170085,"○"]
[72,"경기북부","구리","신포천포천#2 T/L","16~07년 구리전력지사 변전총액공사","- 보호반 개조 - SA 설비 철거","2017-03-06 09:00","2017-03-10 18:00","2017-03-06T09:00:00","2017-03-10T18:00:00","연속",null,null,null,201611170001,"-"]
[73,"경기북부","직할","양주녹양#1 T/L","직할 변전총액공사 (양주-녹양#1T/L 보호반 교체)","직할 변전총액공사 (양주-녹양#1T/L 보호반 교체) 양주S/S 양주-녹양#1T/L 녹양S/S 양주-녹양#1T/L","2017-03-06 10:00","2017-03-10 18:00","취소","취소","연속",null,null,null,201701160078,"-"]
[74,"경기북부","직할","양주녹양#2 T/L","직할 변전총액공사 (양주-녹양#2T/L 보호반 교체)","직할 변전총액공사 (양주-녹양#2T/L 보호반 교체) 양주S/S 양주-녹양#2T/L 녹양S/S 양주-녹양#2T/L","2017-03-13 10:00","2017-03-17 18:00","취소","취소","연속",null,null,null,201701160079,"-"]
[75,"경기북부","직할","용현도봉#1 T/L","용현도봉#1 T/L","2017년 직할 변전협력회사 총액공사","2017-03-24 09:00","2017-03-24 18:00","2017-03-24T09:00:00","2017-03-24T18:00:00","당일",null,null,null,201701170027,"-"]
[76,"경기북부","직할","용현도봉#2 T/L","용현도봉#2 T/L","2017년 직할 변전협력회사 총액공사","2017-03-07 09:00","2017-03-07 18:00","2017-03-07T09:00:00","2017-03-07T18:00:00","당일",null,null,null,201701170039,"-"]
[77,"경기북부","직할","운천전곡#2 T/L","운천전곡#2 T/L","2017년 직할 변전협력회사 총액공사 - GIS 보통","2017-03-17 09:00","2017-03-17 18:00","2017-03-17T09:00:00","2017-03-17T18:00:00","당일",null,null,null,201701170055,"○"]
[78,"경기북부","직할","운천전곡#1 T/L","운천전곡#1 T/L","2017년 직할 변전협력회사 총액공사 - GIS 보통","2017-03-16 09:00","2017-03-16 18:00","2017-03-16T09:00:00","2017-03-16T18:00:00","당일",null,null,null,201701170054,"○"]
[79,"경기북부","파주","신포천백학#2 T/L","변전협력회사 공사(백학S/S 신포천-백학#2T/L GIS 보통점검)","백학S/S 신포천-백학#2T/L GIS 보통점검","2017-03-29 10:00","2017-03-29 18:00","2017-03-29T10:00:00","2017-03-29T18:00:00","당일",null,null,null,201701170176,"-"]
[80,"경기북부","파주","신포천백학#1 T/L","변전협력회사 공사(백학S/S 신포천-백학#1T/L GIS 보통점검)","백학S/S 신포천-백학#1T/L GIS 보통점검","2017-03-28 10:00","2017-03-28 18:00","2017-03-28T10:00:00","2017-03-28T18:00:00","당일",null,null,null,201701170174,"-"]
[81,"경기북부","파주","신덕은문산#2 T/L","변전협력회사 공사(신덕은S/S 신덕은-문산#2T/L GIS 보통점검)","신덕은S/S 신덕은-문산#2T/L GIS 보통점검","2017-03-08 10:00","2017-03-08 18:00","2017-03-08T10:00:00","2017-03-08T18:00:00","당일",null,null,null,201701170149,"-"]
[82,"경기북부","파주","신덕은문산#1 T/L","변전협력회사 공사(신덕은S/S 신덕은-문산#1T/L GIS 보통점검)","신덕은S/S 신덕은-문산#1T/L GIS 보통점검","2017-03-07 10:00","2017-03-07 18:00","2017-03-07T10:00:00","2017-03-07T18:00:00","당일",null,null,null,201701170148,"-"]
[83,"경기북부","파주","일산지도#1 T/L","변전협력회사 공사(일산S/S 일산-지도#1T/L GIS 초기점검)","일산S/S 일산-지도#1T/L GIS 초기점검","2017-03-21 10:00","2017-03-21 18:00","2017-03-03T10:00:00","2017-03-03T18:00:00","당일",null,null,"신뢰도개선",201701170146,"-"]
[84,"경기북부","파주","일산지도#2 T/L","변전협력회사 공사(일산S/S 일산-지도#2T/L GIS 초기점검)","일산S/S 일산-지도#2T/L GIS 초기점검","2017-03-22 10:00","2017-03-22 18:00","2017-03-06T10:00:00","2017-03-06T18:00:00","당일",null,null,"신뢰도개선",201701170147,"-"]
[85,"경기북부","파주","지도능곡#1 T/L","변전협력회사 공사(지도-능곡#1T/L GIS 보통점검)","지도S/S 지도-능곡#1T/L GIS 보통점검","2017-03-10 10:00","2017-03-10 18:00","2017-03-10T10:00:00","2017-03-10T18:00:00","당일",null,null,null,201701170144,"-"]
[86,"경기","군포","관양평촌#1 T/L","154kV 안양S/S 옥내화공사","(신)안양S/S 최초가압 시송전선로로 활용하기 위함 - 관양S/S 관양평촌#1T/L~평촌S/S 안양평촌#2T/L~(신)안양S/S","2017-03-28 09:00","2017-03-29 18:00","2017-03-28T09:00:00","2017-03-29T18:00:00","당일",null,null,null,201701110026,"-"]
[87,"경기","군포","시화성곡 T/L","시화S/S 154kV 시화-성곡T/L GIS 보통점검","- 시화S/S 시화-성곡T/L GIS 보통점검","2017-03-08 09:00","2017-03-08 18:00","2017-03-08T09:00:00","2017-03-08T18:00:00","연속",null,null,null,201701050163,"-"]
[88,"경기","군포","신시흥시화#1 T/L","시화S/S 154kV 신시흥-시화#1T/L LA 하자점검","- 시화S/S 154kV 신시흥-시화#1T/L LA 하자점검 - 인출 붓싱 B상 접속단자 과열점검","2017-03-15 09:00","2017-03-15 18:00","2017-03-15T09:00:00","2017-03-15T18:00:00","연속",null,null,null,201701050164,"-"]
[89,"경기","군포","안양평촌#2 T/L","154kV 안양S/S 옥내화 관련 인출 정비공사","내 용 : 154㎸ 안양변전소 옥내화에 따른 구내 인출정비 선종/회선길이 : 154㎸ XLPE 1,200/2,000㎟, 각 2회선-0.1㎞ 모선연계케이블 1회선- 0.15km","2017-03-02 09:00","2017-03-30 18:00","2017-03-02T09:00:00","2017-03-30T18:00:00","연속",null,null,null,201701060021,"-"]
[90,"경기","군포","산본안양#2 T/L","154kV 안양S/S 옥내화 건설공사","(구)안양S/S 평촌#2T/L GIS C/H와 )(신)안양S/S 산본#2T/L GIS C/H를 연결하여 모선연계선로를 구성하기 위하여 C/H 종단접속함 철거,설치","2017-03-10 09:00","2017-03-10 18:00","2017-03-10T09:00:00","2017-03-10T18:00:00","당일",null,null,null,201701090274,"-"]
[91,"경기","군포","산본안양#2 T/L","154kV 안양S/S 옥내화 건설공사","(구)안양S/S 평촌#2T/L GIS C/H와 )(신)안양S/S 산본#2T/L GIS C/H를 연결하여 모선연계선로를 구성하기 위하여 C/H 종단접속함 철거,설치","2017-03-06 09:00","2017-03-06 18:00","2017-03-06T09:00:00","2017-03-06T18:00:00","당일",null,null,null,201701090267,"-"]
[92,"경기","군포","안양평촌#1 T/L","154kV 안양S/S 옥내화 관련 인출 정비공사","내 용 : 154㎸ 안양변전소 옥내화에 따른 구내 인출정비 선종/회선길이 : 154㎸ XLPE 1,200/2,000㎟, 각 2회선-0.1㎞ 모선연계케이블 1회선- 0.15km","2017-03-31 09:00","2017-04-14 18:00","2017-03-31T09:00:00","2017-04-14T18:00:00","연속",null,null,null,201701060023,"-"]
[93,"경기","군포","일동원곡#1 T/L","154kV 일동-원곡T/L 22,23호 안전이격확보공사","- 철탑상향(인클로징공법) 2기(No.22,23) - 전선교체 : 1.366km(No.21~26)","2017-03-17 07:00","2017-03-21 19:00","2017-03-17T07:00:00","2017-03-21T19:00:00","연속",null,null,null,201701040146,"-"]
[94,"경기","군포","일동원곡#2 T/L","154kV 일동-원곡T/L 22,23호 안전이격확보공사","- 철탑상향(인클로징공법) 2기(No.22,23) - 전선교체 : 1.366km(No.21~26)","2017-03-17 07:00","2017-03-24 19:00","2017-03-17T07:00:00","2017-03-24T19:00:00","연속",null,null,null,201701040145,"-"]
[95,"경기","군포","서서울일동#2 T/L","154kV 서서울-일동#2T/L 애자교체공사","154kV 서서울-일동#2T/L 애자교체공사(24,24.99 2기) 상단 일동원곡#1T/L","2017-03-25 09:00","2017-03-25 18:00","2017-03-25T09:00:00","2017-03-25T18:00:00","당일",null,null,null,201701060314,"-"]
[96,"경기","군포","서서울일동#1 T/L","154kV 서서울-일동#1T/L 애자교체공사","154kV 서서울-일동#1T/L 애자교체공사(24,24.99 2기) 상단일동원곡#2T/L","2017-03-24 09:00","2017-03-24 18:00","2017-03-24T09:00:00","2017-03-24T18:00:00","당일",null,null,null,201701060315,"-"]
[97,"경기","동부","왕암가남#1 T/L","154kV 왕암-가남T/L 정밀점검","송전선로 정밀점검(156~220호, 66기)","2017-03-13 09:30","2017-03-16 18:00","2017-03-13T09:30:00","2017-03-16T18:00:00","연속",null,null,null,201701090039,"-"]
[98,"경기","동부","왕암가남#2 T/L","154kV 왕암-가남T/L 정밀점검","송전선로 정밀점검(156~220호, 66기)","2017-03-20 09:30","2017-03-23 18:00","2017-03-20T09:30:00","2017-03-23T18:00:00","연속",null,null,null,201701090068,"-"]
[99,"경기","성남","서안성S/S #61M.Tr(ESS) A","서안성S/S #61M.Tr(ESS) 하자점검","서안성S/S #61M.Tr(ESS) 하자점검","2017-03-22 09:00","2017-03-31 18:00","2017-03-22T09:00:00","2017-03-31T18:00:00","연속",null,null,null,201608120287,"-"]
[100,"경기","성남","신성남정자#1 T/L","신성남정자#1T/L 보호반 성능개선","신성남정자#1T/L 보호반 성능개선","2017-03-07 09:00","2017-03-07 18:00","2017-03-07T09:00:00","2017-03-07T18:00:00","당일",null,null,null,201701060061,"-"]
[101,"경기","성남","신성남서판교#1 T/L","신성남S/S 154kV SW 증설공사","GIS * 2CCT 증설","2017-03-16 14:00","2017-03-17 14:00","취소","취소","연속",null,null,null,201701090180,"-"]
[102,"경기","성남","신성남서판교#1 T/L","신성남S/S 154kV SW 증설공사","GIS * 2CCT 증설","2017-03-08 14:00","2017-03-09 14:00","취소","취소","연속",null,null,null,201701090179,"-"]
[103,"경기","성남","신용인S/S 154kV #60 BUS","154kV 신용인동백#1T/L GIS 정밀점검","154kV 신용인동백#1T/L GIS 정밀점검","2017-03-27 09:00","2017-03-28 14:00","2017-03-27T09:00:00","2017-03-28T14:00:00","연속",null,null,null,201701110079,"-"]
[104,"경기","성남","신용인S/S 154kV #60 BUS","154kV 신용인동백#2T/L GIS 정밀점검","154kV 신용인동백#2T/L GIS 정밀점검","2017-03-30 09:00","2017-03-31 14:00","2017-03-30T09:00:00","2017-03-31T14:00:00","연속",null,null,null,201701110084,"-"]
[105,"경기","성남","신용인S/S 154kV #65 BUS","154kV 신용인동백#1T/L GIS 정밀점검","154kV 신용인동백#1T/L GIS 정밀점검","2017-03-28 14:00","2017-03-29 18:00","2017-03-28T14:00:00","2017-03-29T18:00:00","연속",null,null,null,201701110080,"-"]
[106,"경기","성남","신용인S/S #63M.Tr(ESS) A","신용인S/S EM.Tr Bank 설비 하자점검","신용인S/S EM.Tr Bank 설비 하자점검","2017-03-13 09:00","2017-03-24 18:00","2017-03-13T09:00:00","2017-03-24T18:00:00","연속",null,null,null,201701060085,"-"]
[107,"경기","성남","신용인S/S 154kV #1 BUS TIE CB","신용인S/S 154kV #1 BUS TIE CB","신용인S/S 154kV #1 BUS TIE CB","2017-03-30 09:00","2017-03-30 18:00","2017-03-30T09:00:00","2017-03-30T18:00:00","당일",null,null,null,201701060131,"-"]
[108,"경기","성남","신용인S/S 154kV #65 BUS","154kV 신용인동백#2T/L GIS 정밀점검","154kV 신용인동백#2T/L GIS 정밀점검","2017-03-31 14:00","2017-04-01 18:00","2017-03-31T14:00:00","2017-04-01T18:00:00","연속",null,null,null,201701110082,"-"]
[109,"경기","성남","신성남정자#1 T/L","신성남S/S 154kV SW 증설공사","GIS * 1CCT 증설","2017-03-23 14:00","2017-03-24 14:00","2017-03-23T14:00:00","2017-03-24T14:00:00","연속",null,null,null,201701090184,"-"]
[110,"경기","성남","신성남정자#1 T/L","신성남S/S 154kV SW 증설공사","GIS * 1CCT 증설","2017-03-26 14:00","2017-03-27 14:00","2017-03-26T14:00:00","2017-03-27T14:00:00","연속",null,null,null,201701090185,"-"]
[111,"경기","직할","발안구문천#1 T/L","구문천S/S 154kV 발안구문천#1 T/L 유면계 누유보수","구문천S/S 154kV 발안구문천#1 T/L 유면계 누유보수","2017-03-08 09:00","2017-03-08 12:00","2017-03-08T09:00:00","2017-03-08T12:00:00","당일",null,null,null,201701050155,"-"]
[112,"경기","직할","조암구문천#2 T/L","구문천S/S 154kV 조암구문천#2 T/L 유면계 누유보수","구문천S/S 154kV 조암구문천#2 T/L 유면계 누유보수","2017-03-07 15:00","2017-03-07 18:00","2017-03-07T15:00:00","2017-03-07T18:00:00","당일",null,null,null,201701050154,"-"]
[113,"경기","직할","발안구문천#2 T/L","구문천S/S 154kV 발안구문천#2 T/L 유면계 누유보수","구문천S/S 154kV 발안구문천#2 T/L 유면계 누유보수","2017-03-08 12:00","2017-03-08 15:00","2017-03-08T12:00:00","2017-03-08T15:00:00","당일",null,null,null,201701050156,"-"]
[114,"경기","직할","조암구문천#1 T/L","구문천S/S 154kV 조암구문천#1 T/L 유면계 누유보수","구문천S/S 154kV 조암구문천#1 T/L 유면계 누유보수","2017-03-07 12:00","2017-03-07 15:00","2017-03-07T12:00:00","2017-03-07T15:00:00","당일",null,null,null,201701050152,"-"]
[115,"경기","직할","서서울서수원#1 T/L","서수원S/S 154kV 서서울서수원#1 T/L 피뢰기 교체","서수원S/S 154kV 서서울서수원#1 T/L 피뢰기 교체","2017-03-13 09:00","2017-03-13 18:00","2017-03-13T09:00:00","2017-03-13T18:00:00","당일",null,null,null,201701030165,"-"]
[116,"경기","직할","서서울서수원#2 T/L","서수원S/S 154kV 서서울서수원#2 T/L 피뢰기 교체","서수원S/S 154kV 서서울서수원#2 T/L 피뢰기 교체","2017-03-14 09:00","2017-03-14 18:00","2017-03-14T09:00:00","2017-03-14T18:00:00","당일",null,null,null,201701030166,"-"]
[117,"경기","직할","서수원율전#2 T/L","154kV 율전-동수원T/L 전력선 교체공사","154kV 율전-동수원T/L No.3~4, 16~20 전력선 교체공사","2017-03-03 08:00","2017-03-04 18:00","2017-03-03T08:00:00","2017-03-04T18:00:00","연속",null,null,null,201701120035,"-"]
[118,"경기","직할","서수원율전#1 T/L","154kV 율전-동수원T/L 전력선 교체공사","154kV 율전-동수원T/L No.3~4, 16~20 전력선 교체공사","2017-03-07 08:00","2017-03-08 18:00","2017-03-07T08:00:00","2017-03-08T18:00:00","연속",null,null,null,201701120037,"-"]
[119,"경기","직할","화성발안#2 T/L","화성S/S 154kV 화성발안#2T/L 피뢰기 교체","화성S/S 154kV 화성발안#2T/L 피뢰기 교체 및 발안S/S GIS 보통점검","2017-03-03 09:00","2017-03-03 18:00","2017-03-03T09:00:00","2017-03-03T18:00:00","당일",null,null,null,201701030148,"-"]
[120,"경기","직할","화성발안#1 T/L","화성S/S 154kV 화성발안#1T/L 피뢰기 교체","화성S/S 154kV 화성발안#1T/L 피뢰기 교체 및 발안S/S GIS 보통점검","2017-03-02 09:00","2017-03-02 18:00","2017-03-02T09:00:00","2017-03-02T18:00:00","당일",null,null,null,201701030146,"-"]
[121,"경기","평택","서운S/S 서운-안성#2T/L(6B7) GIS","서운S/S 서운-안성#2T/L 보통점검","서운S/S 서운-안성#2T/L 보통점검 안성S/S 전자변 히터설치","2017-03-16 10:00","2017-03-16 18:00","2017-03-16T10:00:00","2017-03-16T18:00:00","연속",null,null,null,201701040052,"○"]
[122,"경기","평택","서운S/S 서운-만승T/L(617) GIS","서운S/S 서운-만승T/L GIS 보통점검","서운S/S 서운-만승T/L GIS 보통점검","2017-03-27 10:00","2017-03-27 18:00","2017-03-27T10:00:00","2017-03-27T18:00:00","연속",null,null,null,201701040062,"○"]
[123,"경기","평택","서운S/S 서운-삼죽T/L(647) GIS","서운S/S 서운-삼죽T/L GIS 보통점검","서운S/S 서운-삼죽T/L GIS 보통점검, 43R 경보수용 삼죽S/S 43R 경보수용","2017-03-28 10:00","2017-03-28 18:00","2017-03-28T10:00:00","2017-03-28T18:00:00","연속",null,null,null,201701040063,"○"]
[124,"경기","평택","진위S/S 남사-진위#2T/L GIS","진위S/S 남사-진위#2T/L GIS 초기점검, 보호반 성능개선","진위S/S 남사-진위#2T/L GIS 초기점검, 보호반 성능개선","2017-03-03 10:00","2017-03-03 18:00","2017-03-03T10:00:00","2017-03-03T18:00:00","당일",null,null,null,201701040042,"-"]
[125,"경기","평택","남사진위#1 T/L","진위S/S 남사-진위#1T/L GIS 초기점검, 보호반 성능개선","진위S/S 남사-진위#1T/L GIS 초기점검, 보호반 성능개선","2017-03-02 10:00","2017-03-02 18:00","2017-03-02T10:00:00","2017-03-02T18:00:00","당일",null,null,null,201701040041,"-"]
[126,"경기","평택","평택추팔#2 T/L","154kV 평택-추팔T/L No.14,15 안전이격 확보공사","지지물 교체 : 2기 전력선교체 : 4가닥","2017-03-03 08:00","2017-03-07 18:00","2017-03-03T08:00:00","2017-03-07T18:00:00","연속",null,null,null,201701240004,"-"]
[127,"경기","평택","평택추팔#1 T/L","154kV 평택-추팔T/L No.14,15 안전이격 확보공사","지지물 교체 : 2기 전력선교체 : 4가닥","2017-03-03 08:00","2017-03-07 18:00","2017-03-03T08:00:00","2017-03-07T18:00:00","연속",null,null,null,201701240003,"-"]
[128,"경기","평택","평택C/C 평택복합#2T/L GIS","평택CC 평택복합#2T/L GIS 보통점검","평택CC 평택복합#2T/L GIS 보통점검","2017-03-24 10:00","2017-03-24 18:00","2017-03-24T10:00:00","2017-03-24T18:00:00","연속",null,null,null,201701060088,"-"]
[129,"강원","강릉","신제천주진#2 T/L","154kV 신제천-주진T/L 전선접속개소 해소공사","압축접속개소 전력선 교체 154kV 신제천-주진#2T/L No.39~41, 41~43","2017-03-13 08:00","2017-03-17 18:00","2017-03-13 08:00","2017-03-17 18:00","연속",null,null,null,201701100140,"-"]
[130,"강원","강릉","신제천주진#1 T/L","2016 가공송전 순시점검 위탁공사","송전선로 정밀점검 154kV 신제천-주진#1T/L : 신제천S/S ~ 주진S/S","2017-03-20 09:00","2017-03-24 18:00","2017-03-20 09:00","2017-03-24 18:00","매일",null,null,null,201701100141,"-"]
[131,"강원","동해","도계태백 T/L","2017년 동해전력지사 변전협력회사 총액공사","1. 도계S/S 도계-태백T/L GIS 보통점검 2. 도계S/S 도계-태백T/L LA 보통점검 3. 도계S/S 도계-태백T/L PT 보통점검","2017-03-07 10:00","2017-03-07 18:00","2017-03-07 10:00","2017-03-07 18:00","당일",null,null,null,201701100451,"-"]
[132,"강원","동해","이원도계 T/L","2017년 동해전력지사 변전협력회사 총액공사","1. 도계S/S 이원-도계T/L GIS 보통점검 2. 도계S/S 이원-도계T/L LA 보통점검 3. 도계S/S 이원-도계T/L PT 보통점검","2017-03-08 10:00","2017-03-08 18:00","2017-03-08 10:00","2017-03-08 18:00","당일",null,null,null,201701100452,"-"]
[133,"강원","동해","동해강릉 T/L","2017년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해-강릉T/L GIS 초기점검 2. 동해S/S 동해-강릉T/L LA 초기점검 3. 동해S/S 동해-강릉T/L PT 초기점검","2017-03-13 10:00","2017-03-13 18:00","2017-03-13 10:00","2017-03-13 18:00","당일",null,null,null,201701100457,"-"]
[134,"강원","동해","동해북평#2 T/L","2017년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해-북평#2T/L GIS 초기점검 2. 동해S/S 동해-북평#2T/L LA 초기점검","2017-03-10 10:00","2017-03-10 18:00","2017-03-10 10:00","2017-03-10 18:00","당일",null,null,null,201701100456,"-"]
[135,"강원","동해","동해북평#1 T/L","2017년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해-북평#1T/L GIS 초기점검 2. 동해S/S 동해-북평#1T/L LA 초기점검","2017-03-09 10:00","2017-03-09 18:00","2017-03-09 10:00","2017-03-09 18:00","당일",null,null,null,201701100453,"-"]
[136,"강원","동해","동해영동TP T/L","2017년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해-영동TP T/L GIS 초기점검 2. 동해S/S 동해-영동TP T/L LA 초기점검 3. 동해S/S 동해-영동TP T/L PT 초기점검","2017-03-14 10:00","2017-03-14 18:00","2017-03-14 10:00","2017-03-14 18:00","당일",null,null,null,201701100459,"-"]
[137,"강원","동해","동해이원#1 T/L","2017년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해-이원#1 T/L GIS 초기점검 2. 동해S/S 동해-이원#1 T/L LA 초기점검 3. 동해S/S 동해-이원#1 T/L PT 초기점검","2017-03-16 10:00","2017-03-16 18:00","2017-03-16 10:00","2017-03-16 18:00","당일",null,null,null,201701100464,"-"]
[138,"강원","동해","동해이원#2 T/L","2017년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해-이원#2 T/L GIS 초기점검 2. 동해S/S 동해-이원#2 T/L LA 초기점검 3. 동해S/S 동해-이원#2 T/L PT 초기점검","2017-03-17 10:00","2017-03-17 18:00","2017-03-17 10:00","2017-03-17 18:00","당일",null,null,null,201701100465,"-"]
[139,"강원","동해","동해정선 T/L","2017년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해-정선T/L GIS 초기점검 2. 동해S/S 동해-정선T/L LA 초기점검 3. 동해S/S 동해-정선T/L PT 초기점검","2017-03-21 10:00","2017-03-21 18:00","2017-03-21 10:00","2017-03-21 18:00","당일",null,null,null,201701100467,"-"]
[140,"강원","동해","동해동영월 T/L","2017년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해-동영월 T/L GIS 초기점검 2. 동해S/S 동해-동영월 T/L LA 초기점검 3. 동해S/S 동해-동영월 T/L PT 초기점검","2017-03-15 10:00","2017-03-15 18:00","2017-03-15 10:00","2017-03-15 18:00","당일",null,null,null,201701100460,"-"]
[141,"강원","동해","이원태백 T/L","2017년 동해전력지사 변전협력회사 총액공사","1. 이원S/S 이원-태백T/L LA 하자점검","2017-03-06 10:00","2017-03-06 18:00","2017-03-06 10:00","2017-03-06 18:00","당일",null,null,null,201701100447,"-"]
[142,"강원","원주","신제천남원주#1 T/L","남원주변전소 외장재 교체공사","남원주변전소 배면부 패널교체 (신제천남원주#1TL)","2017-03-07 08:00","2017-03-09 18:00","2017-03-07 08:00","2017-03-09 18:00","매일",null,null,null,201701120015,"-"]
[143,"강원","원주","신제천남원주#2 T/L","남원주변전소 외장재 교체공사","남원주변전소 배면부 패널교체 (신제천남원주#2TL)","2017-03-05 08:00","2017-03-08 18:00","2017-03-05 08:00","2017-03-08 18:00","매일",null,null,null,201701120014,"-"]
[144,"강원","원주","남원주원주#2 T/L","남원주변전소 외장재 교체공사","남원주변전소 배면부 패널교체 (남원주원주#2TL)","2017-03-03 08:00","2017-03-06 18:00","2017-03-03 08:00","2017-03-06 18:00","매일",null,null,null,201701120013,"-"]
[145,"강원","원주","남원주원주#1 T/L","남원주변전소 외장재 교체공사","남원주변전소 배면부 패널교체 (남원주원주#1TL)","2017-03-01 08:00","2017-03-04 18:00","2017-03-01 08:00","2017-03-04 18:00","매일",null,null,null,201701110033,"-"]
[146,"강원","원주","횡성홍천#2 T/L","홍천변전소 170kV GIS 설치공사","○ 170kV 송전선로 LINE측 붓싱 조립 - 진공 및 가스 주입 - 각종 시험 - 무부하 가압 ○ 기존 옥외철구 설비 철거 - GCB, DS 철거 - LINE CVT, LA 이설","2017-03-27 11:00","2017-04-03 09:30","2017-03-27 11:00","2017-04-03 09:30","연속",null,null,null,201701160122,"-"]
[147,"강원","원주","횡성홍천#1 T/L","홍천변전소 170kV GIS 설치공사","○ 170kV 송전선로 LINE측 붓싱 조립 - 진공 및 가스 주입 - 각종 시험 - 무부하 가압 ○ 기존 옥외철구 설비 철거 - GCB, DS 철거 - LINE CVT, LA 이설","2017-03-20 11:00","2017-03-27 09:30","2017-03-20 11:00","2017-03-27 09:30","연속",null,null,null,201701160117,"-"]
[148,"강원","원주","홍천남춘천 T/L","홍천변전소 170kV GIS 설치공사","○ 170kV 송전선로 LINE측 붓싱 조립 - 진공 및 가스 주입 - 각종 시험 - 무부하 가압 ○ 기존 옥외철구 설비 철거 - GCB, DS 철거 - LINE CVT, LA 이설","2017-03-06 11:00","2017-03-13 09:30","2017-03-06 11:00","2017-03-13 09:30","연속",null,null,null,201701160135,"-"]
[149,"강원","태백","정선영월CC T/L","2016~17년 충북지역본부 직할 송전정비 협력회사 총액공사","4회선 철탑(1호) 하단 휴전작업(아킹혼 철거)에 따른 상단회선 안전조치 - 작업대상 : 154kV 신제천-영월CC#1T/L 78호 (4회선 철탑 하단) - 안전조치 : 154kV 정선-영월CCT/L 1호 (4회선 철탑 상단)","2017-03-17 07:30","2017-03-17 18:00","2017-03-17 07:30","2017-03-17 18:00","당일",null,null,null,201701090113,"-"]
[150,"충북","직할","문경단양 T/L","2017년 OPGW 항공장애표시구 교체공사","154kV 문경-단양T/L 17~19호 항공장애표시구 14조 교체","2017-03-26 09:00","2017-03-26 18:00","2017-03-26 09:00","2017-03-26 18:00","당일",null,null,null,201701090095,"-"]
[151,"충북","직할","신제천영월CC#1 T/L","2016~17년 충북지역본부 직할 송전정비 협력회사 총액공사","조류착지방지장치 설치(43, 66호), 아킹혼 철거(78호)","2017-03-17 07:30","2017-03-17 18:00","2017-03-17 07:30","2017-03-17 18:00","당일",null,null,null,201701090112,"-"]
[152,"충북","직할","왕암가남#2 T/L","154kV 왕암-가남T/L 10-12 안전이격 확보공사","철탑 설치2기, 철거1기 장주볌경 1기 전력선 교체 : 11-11-1","2017-03-22 08:00","2017-03-23 18:00","2017-03-22 08:00","2017-03-23 18:00","연속",null,null,null,201701110002,"-"]
[153,"충북","직할","왕암가남#2 T/L","154kV 왕암-가남T/L 10-12 안전이격 확보공사","철탑 설치 2기, 철거 1기","2017-03-29 08:00","2017-03-31 18:00","2017-03-29 08:00","2017-03-31 18:00","연속",null,null,null,201701190088,"-"]
[154,"충북","직할","왕암가남#1 T/L","154kV 왕암-가남T/L 10-12 안전이격 확보공사","철탑 설치2기, 철거1기 장주볌경 1기 전력선 교체 : 11-11-1","2017-03-24 08:00","2017-03-28 18:00","2017-03-24 08:00","2017-03-28 18:00","연속",null,null,null,201701110001,"-"]
[155,"충북","직할","제천영월#1 T/L","2016~17년 충북지역본부 직할 송전정비 협력회사 총액공사","애자련 보강 (62, 63호)","2017-03-18 07:30","2017-03-18 18:00","2017-03-18 07:30","2017-03-18 18:00","당일",null,null,null,201701090109,"-"]
[156,"충북","직할","신제천제천#1 T/L","154kV 신제천-제천T/L 안전이격 확보공사","154kV 신제천-제천T/L 안전이격 확보공사 (철탑 3기 인상, #2T/L 전력선 교 체)","2017-03-06 08:00","2017-03-15 18:00","2017-03-06 08:00","2017-03-15 18:00","연속",null,null,null,201701090001,"-"]
[157,"충북","직할","신제천제천#2 T/L","154kV 신제천-제천T/L 안전이격 확보공사","154kV 신제천-제천T/L 안전이격 확보공사 (철탑 3기 인상, #2T/L 전력선 교 체)","2017-03-06 08:00","2017-03-15 18:00","2017-03-06 08:00","2017-03-15 18:00","연속",null,null,null,201701090002,"-"]
[158,"충북","직할","제천영월#2 T/L","2016~17년 충북지역본부 직할 송전정비 협력회사 총액공사","애자련 보강 (62, 63호)","2017-03-19 07:30","2017-03-19 18:00","2017-03-19 07:30","2017-03-19 18:00","당일",null,null,null,201701090110,"-"]
[159,"충북","충주","충주풍동 T/L","2017년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검","2017-03-27 09:00","2017-03-31 18:00","2017-03-27 09:00","2017-03-31 18:00","매일",null,null,null,201701020105,"○"]
[160,"충북","충주","충주충주HP#1 T/L","송전선로 LA, CVT 보통점검","송전선로 LA, CVT 보통점검","2017-03-13 10:00","2017-03-13 18:00","2017-03-13 10:00","2017-03-13 18:00","당일",null,null,null,201701050169,"○"]
[161,"충북","충주","충주충주HP#2 T/L","송전선로 LA, CVT 보통점검","송전선로 LA, CVT 보통점검","2017-03-14 10:00","2017-03-14 18:00","2017-03-14 10:00","2017-03-14 18:00","당일",null,null,null,201701050170,"○"]
[162,"충북","충주","풍동음성#1 T/L","154kV 풍동-음성 등 11개T/L 전력선 교체공사","전선접속개소 해소를 위한 전력선교체","2017-03-22 08:00","2017-03-26 18:00","2017-03-22 08:00","2017-03-26 18:00","연속",null,null,null,201701160153,"○"]
[163,"충북","충주","풍동음성#2 T/L","154kV 풍동-음성 등 11개T/L 전력선 교체공사","전선접속개소 해소를 위한 전력선교체","2017-03-27 08:00","2017-03-31 18:00","2017-03-27 08:00","2017-03-31 18:00","연속",null,null,null,201701160154,"○"]
[164,"대전충남","대전","금산무주#2 T/L","154kV 금산-무주T/L 전선접속개소 전력선 교체공사","전선접속개소 전력선 교체","2017-03-23 07:00","2017-03-29 18:00","2017-03-23T07:00:00","2017-03-29T18:00:00","연속",null,null,null,201701170084,"-"]
[165,"대전충남","대전","금산무주#1 T/L","154kV 금산-무주T/L 전선접속개소 전력선 교체공사","전선접속개소 전력선 교체","2017-03-20 07:00","2017-03-22 18:00","2017-03-20T07:00:00","2017-03-22T18:00:00","연속",null,null,null,201701170083,"-"]
[166,"대전충남","대전","남대전신흥#2 T/L","○ 154kV 신흥S/S 남대전-신흥#2T/L GIS 보통점검","○ 154kV 신흥S/S 남대전-신흥#2T/L GIS 보통점검","2017-03-07 09:00","2017-03-07 18:00","2017-03-07T09:00:00","2017-03-07T18:00:00","당일",null,null,null,201701170298,"-"]
[167,"대전충남","대전","남대전신흥#3 T/L","○ 154kV 신흥S/S 남대전-신흥#3T/L GIS 보통점검","○ 154kV 신흥S/S 남대전-신흥#3T/L GIS 보통점검","2017-03-08 09:00","2017-03-08 18:00","2017-03-08T09:00:00","2017-03-08T18:00:00","당일",null,null,null,201701170300,"-"]
[168,"대전충남","대전","남대전신흥#1 T/L","○ 154kV 신흥S/S 남대전-신흥#1T/L GIS 보통점검","○ 154kV 신흥S/S 남대전-신흥#1T/L GIS 보통점검","2017-03-06 09:00","2017-03-06 18:00","2017-03-06T09:00:00","2017-03-06T18:00:00","당일",null,null,null,201701170297,"-"]
[169,"대전충남","서산","GSEPS#1 T/L","송악S/S 154kV GSEPS#1T/L GIS 및 LA 보통점검","○ 송악S/S 154kV GSEPS#1T/L GIS 및 LA 보통점검","2017-03-18 09:00","2017-03-18 18:00","2017-03-18T09:00:00","2017-03-18T18:00:00","당일",null,null,null,201701170240,"-"]
[170,"대전충남","세종","조치원월산 T/L","[변전] 세종P/O 협력회사 총액공사","○ GIS보통점검","2017-03-06 09:00","2017-03-06 18:00","2017-03-06T09:00:00","2017-03-06T18:00:00","당일",null,null,null,201701160095,"-"]
[171,"대전충남","세종","천안전의#1 T/L","[송전] 154kV 천안-전의T/L 안전거리 확보공사","[송전] 철탑교체 : 3기(No.23~25), 전선교체 : 1.083km(No.22~26)","2017-03-13 09:00","2017-04-02 18:00","2017-03-10T09:00:00","2017-03-11T18:00:00","매일",null,null,"신뢰도개선",201701040080,"-"]
[172,"대전충남","세종","천안전의#2 T/L","[송전] 154kV 천안-전의T/L 안전거리 확보공사","[송전] 철탑교체 : 3기(No.23~25), 전선교체 : 1.083km(No.22~26)","2017-03-13 09:00","2017-04-02 18:00","2017-03-12T09:00:00","2017-04-09T18:00:00","매일",null,null,null,201701040082,"-"]
[173,"대전충남","아산","서천안탕정#1 T/L","서천안S/S 154kV 서천안-탕정#1T/L GIS 보통점검","○ 154kV 서천안-탕정#1T/L GIS 보통점검 ○ 병행) 탕정S/S 154kV 서천안-탕정#1T/L GIS, LA 보통점검","2017-03-23 09:00","2017-03-23 18:00","2017-03-23T09:00:00","2017-03-23T18:00:00","당일",null,null,null,201701160096,"-"]
[174,"대전충남","아산","서천안탕정#2 T/L","서천안S/S 154kV 서천안-탕정#2T/L GIS 보통점검","○ 154kV 서천안-탕정#2T/L GIS 보통점검 ○ 병행) 탕정S/S 154kV 서천안-탕정#2T/L GIS, LA 보통점검","2017-03-24 09:00","2017-03-24 18:00","2017-03-24T09:00:00","2017-03-24T18:00:00","당일",null,null,null,201701160097,"-"]
[175,"대전충남","아산","아산송악#1 T/L","154kV 아산-송약T/L 소도체 이도조정공사","154kV 아산-송약T/L 소도체 이도조정공사","2017-03-25 07:00","2017-03-27 18:00","2017-03-25T07:00:00","2017-03-27T18:00:00","연속",null,null,null,201701170110,"-"]
[176,"대전충남","아산","아산인주#2 T/L","[송전]345kV 아산-화성 등15개T/L 피뢰기 설치공사","154kV 아산-인주#2T/L 피뢰기 설치(10기분)","2017-03-10 08:00","2017-03-13 18:00","2017-03-10T08:00:00","2017-03-13T18:00:00","당일",null,null,null,201701170070,"-"]
[177,"대전충남","아산","아산송악#2 T/L","154kV 아산-송약T/L 소도체 이도조정공사","154kV 아산-송약T/L 소도체 이도조정공사","2017-03-30 07:00","2017-04-03 18:00","2017-03-30T07:00:00","2017-04-03T18:00:00","연속",null,null,null,201701170109,"-"]
[178,"대전충남","아산","장재S/S 주공#1T/L CB","장재S/S 154kV 주공#1T/L GIS 보통점검","○ 154kV 주공#1T/L GIS 보통점검","2017-03-17 09:00","2017-03-17 18:00","2017-03-17T09:00:00","2017-03-17T18:00:00","당일",null,null,null,201701170239,"-"]
[179,"전북","군산","군산복합S/Y G/T #2T/L CB","군산복합 #1 G/T CB","군산P/O 170kV 차단기 정밀점검 공사","2017-03-27 09:00","2017-03-29 18:00","2017-03-27 09:00","2017-03-29 18:00","연속",null,null,null,201701090013,"-"]
[180,"전북","군산","군산복합S/Y G/T #1T/L CB","군산복합 #1 G/T CB","군산P/O 170kV 차단기 정밀점검 공사","2017-03-23 09:00","2017-03-25 18:00","2017-03-23 09:00","2017-03-25 18:00","연속",null,null,null,201701090012,"-"]
[181,"전북","군산","동군산군산CC#1 T/L","군산복합 동군산-군산복합#1T/L","군산P/O 170kV 차단기 정밀점검 공사","2017-03-20 09:00","2017-03-22 18:00","2017-03-20 09:00","2017-03-22 18:00","연속",null,null,null,201701090010,"-"]
[182,"전북","군산","군산동군산#1 T/L","군산동군산T/L 안전이격확보공사","철탑신설 및 철거 : 4기(28,29,30,31)","2017-03-27 07:00","2017-03-31 18:00","2017-03-27 07:00","2017-03-31 18:00","연속",null,null,null,201701180137,"-"]
[183,"전북","군산","군산영등#2 T/L","154kV 군산-영등#2T/L 압축인류클램프 교체공사","클램프 교체 : No.10,15,17,53호","2017-03-22 08:00","2017-03-23 18:00","2017-03-22 08:00","2017-03-23 18:00","연속",null,null,null,201701160165,"-"]
[184,"전북","군산","군산영등#1 T/L","154kV 군산-영등#1T/L 압축인류클램프 교체공사","클램프 교체 : No.1,5,20,22호","2017-03-20 08:00","2017-03-21 18:00","2017-03-20 08:00","2017-03-21 18:00","연속",null,null,null,201701160164,"-"]
[185,"전북","군산","군산이리#2 T/L","154kV 군산-이리#2T/L (C/H설치공사)","인하선 설치, 지중가압 및 기설전선 철거","2017-03-13 07:00","2017-03-20 18:00","2017-03-13 07:00","2017-03-20 18:00","연속",null,null,null,201701190019,"-"]
[186,"전북","군산","이리전주#1 T/L","154kV 이리-전주#1T/L (C/H설치공사)","인하선 설치, 지중가압 및 기설전선 철거","2017-03-21 07:00","2017-03-31 18:00","2017-03-21 07:00","2017-03-31 18:00","연속",null,null,null,201701190023,"-"]
[187,"전북","군산","이리백산#1 T/L","154kV 이리-백산#1T/L (C/H설치공사)","인하선 설치, 지중가압 및 기설전선 철거","2017-03-21 07:00","2017-03-31 18:00","2017-03-21 07:00","2017-03-31 18:00","연속",null,null,null,201701190022,"-"]
[188,"전북","군산","팔봉봉동#2 T/L","팔봉봉동T/L 정밀점검공사","공사구간 : 1~37","2017-03-16 09:00","2017-03-18 18:00","취소","취소","매일",null,null,"신뢰도개선",201701180078,"-"]
[189,"전북","군산","팔봉봉동#1 T/L","팔봉봉동T/L 정밀점검공사","공사구간 : 1~37","2017-03-13 09:00","2017-03-15 18:00","취소","취소","매일",null,null,"신뢰도개선",201701180077,"-"]
[190,"전북","김제","정주고창#1 T/L","154kV 차단기 정밀점검","154kV #2 BUS 시험가압","2017-03-22 16:00","2017-03-22 18:00","2017-03-22 16:00","2017-03-22 18:00","연속",null,null,null,201701180193,"-"]
[191,"전북","김제","정주고창#1 T/L","154kV 차단기 정밀점검","154kV #1 BUS 시험가압","2017-03-21 11:00","2017-03-21 13:00","2017-03-21 11:00","2017-03-21 13:00","연속",null,null,null,201701180192,"-"]
[192,"전북","김제","김제섬진강HP T/L","(주)세니온제 송전선로 보호반 성능개선 공사","하드웨어(SMPU, AIU 모듈) 교체 시행","2017-03-22 10:00","2017-03-22 18:00","2017-03-22 10:00","2017-03-22 18:00","당일",null,null,null,201701230114,"-"]
[193,"전북","김제","섬진강H/P #1 M.Tr 1차 CB","154kV 차단기 정밀점검","차단기 내부 정밀점검","2017-03-06 09:00","2017-03-09 18:00","2017-03-06 09:00","2017-03-09 18:00","연속",null,null,null,201701180170,"○"]
[194,"전북","김제","신김제전주#2 T/L","154kV 신김제-전주#2T/L 점퍼지지애자 교체공사","154kV 신김제-전주#2T/L 점퍼지지애자 교체(1기) 154kV 임실-남전주#2T/L 점퍼지지애자 교체(2기) 병행","2017-03-09 07:00","2017-03-09 18:00","취소","취소","당일",null,null,null,201701160126,"-"]
[195,"전북","김제","신김제전주#1 T/L","154kV 신김제-전주#1T/L 점퍼지지애자 교체공사","154kV 신김제-전주#1T/L 점퍼지지애자 교체(3기) 154kV 임실-남전주#1T/L 점퍼지지애자 교체(7기) 병행 154kV 신김제-남전주#2T/L 점퍼지지애자 교체(2기) 병행","2017-03-10 07:00","2017-03-12 18:00","취소","취소","매일",null,null,null,201701160132,"-"]
[196,"전북","김제","정공섬진강수력 T/L","154kV 정공-섬진강수력T/L 점퍼지지애자 교체공사","154kV 정공-섬진강수력T/L 점퍼지지애자 교체(2기) 154kV 정공-정주#1T/L 점퍼지지애자 교체(4기) 병행","2017-03-06 07:00","2017-03-07 18:00","취소","취소","매일",null,null,null,201701160118,"○"]
[197,"전북","김제","정공정주#1 T/L","154kV 정공-정주#1T/L 점퍼지지애자 교체공사","154kV 정공-정주#1T/L 점퍼지지애자 교체(4기) 154kV 정공-섬진강수력T/L 점퍼지지애자 교체(2기) 병행","2017-03-06 07:00","2017-03-07 18:00","취소","취소","연속",null,null,null,201701160120,"-"]
[198,"전북","김제","정공담양 T/L","154kV 정공-담양T/L 점퍼지지애자 교체공사","154kV 정공-담양T/L 점퍼지지애자 교체(3기) 154kV 정공-정주#2T/L 점퍼지지애자 교체(2기) 병행","2017-03-08 07:00","2017-03-08 18:00","취소","취소","당일",null,null,null,201701160121,"○"]
[199,"전북","김제","정공정주#2 T/L","154kV 정공-정주#2T/L 점퍼지지애자 교체공사","154kV 정공-정주#2T/L 점퍼지지애자 교체(2기) 154kV 정공-담양T/L 점퍼지지애자 교체(3기) 병행","2017-03-08 07:00","2017-03-08 18:00","취소","취소","당일",null,null,null,201701160124,"-"]
[200,"전북","김제","신김제정공#1 T/L","(주)세니온제 송전선로 보호반 성능개선 공사","하드웨어(SMPU, AIU 모듈) 교체 시행","2017-03-23 10:00","2017-03-23 18:00","2017-03-23 10:00","2017-03-23 18:00","당일",null,null,null,201701230115,"-"]
[201,"전북","김제","정주고창#2 T/L","154kV 정주-고창#2T/L 점퍼지지애자 교체공사","154kV 정주-고창#2T/L 점퍼지지애자 교체(9기) 154kV 정주-부안#2T/L 점퍼지지애자 교체(9기) 병행","2017-03-16 07:00","2017-03-18 18:00","취소","취소","매일",null,null,null,201701160136,"-"]
[202,"전북","김제","정주고창#1 T/L","154kV 정주-고창#1T/L 점퍼지지애자 교체공사","154kV 정주-고창#1T/L 점퍼지지애자 교체(11기) 154kV 정주-부안#1T/L 점퍼지지애자 교체(11기) 병행","2017-03-13 07:00","2017-03-15 18:00","취소","취소","매일",null,null,null,201701160134,"-"]
[203,"전북","직할","곡성남원#1 T/L","154kV 곡성-남원#1T/L 점퍼지지애자 교체공사","96년 상반기 이전 국산 점퍼지지애자 교체 200개","2017-03-15 07:30","2017-03-15 18:00","2017-03-15 07:30","2017-03-15 18:00","당일",null,null,null,201701230102,"-"]
[204,"전북","직할","곡성남원#2 T/L","154kV 곡성-남원#2T/L 점퍼지지애자 교체공사","96년 상반기 이전 국산 점퍼지지애자 교체 131개 154kV 곡성-남원#2T/L 피뢰기 설치공사 병행(No.10, 15)","2017-03-16 07:30","2017-03-16 18:00","2017-03-16 07:30","2017-03-16 18:00","당일",null,null,null,201701230103,"-"]
[205,"전북","직할","무주진안 T/L","154kV 금산-무주T/L 전선접속개소 전력선 교체공사","154kV 금산-무주T/L 전선접속개소 전력선 교체 관련 안전이격 확보","2017-03-20 07:00","2017-03-22 18:00","2017-03-16 07:00","2017-03-18 18:00","연속",null,null,null,201701170108,"-"]
[206,"전북","직할","무주용담수력 T/L","154kV 금산-무주T/L 전선접속개소 전력선 교체공사","154kV 금산-무주T/L 전선접속개소 전력선 교체 관련 안전이격 확보","2017-03-23 07:00","2017-03-29 18:00","2017-03-19 10:00","2017-03-28 18:00","매일",null,null,null,201701170107,"-"]
[207,"광주전남","강진","화원진도#1 T/L","154kV 화원진도#1 T/L 정밀점검(가공송전순시점검 위탁공사)","154kV 화원진도#1 T/L 정밀점검(가공송전순시점검 위탁공사)","2017-03-20 08:00","2017-03-24 18:00","2017-03-20 08:00","2017-03-24 18:00","매일",null,null,null,201701170170,"-"]
[208,"광주전남","강진","화원진도#2 T/L","154kV 화원진도#2 T/L 정밀점검(가공송전순시점검 위탁공사)","154kV 화원진도#2 T/L 정밀점검(가공송전순시점검 위탁공사)","2017-03-27 08:00","2017-03-31 18:00","2017-03-27 08:00","2017-03-31 18:00","매일",null,null,null,201701170171,"-"]
[209,"광주전남","광주","신광주곡성#2 T/L","154kV 곡성-남원#1T/L 점퍼지지애자 교체공사","154kV 곡성-남원#1T/L 점퍼지지애자 교체공사 안전이격거리 확보(작업無)","2017-03-15 07:30","2017-03-15 18:00","2017-03-15 07:30","2017-03-15 18:00","당일",null,null,null,201701230104,"-"]
[210,"광주전남","광주","신광주곡성#1 T/L","154kV 곡성-남원#2T/L 점퍼지지애자 교체공사","154kV 곡성-남원#2T/L 점퍼지지애자 교체공사 안전이격거리 확보(작업無)","2017-03-16 07:30","2017-03-16 18:00","2017-03-16 07:30","2017-03-16 18:00","당일",null,null,null,201701230105,"-"]
[211,"광주전남","목포","장성영광#1 T/L","154kV장성-영광T/L전선접속개소전선교체공사","0 전선 및 금구류 교체 : No.69~160","2017-03-06 07:00","2017-03-20 18:00","2017-03-06 07:00","2017-03-20 18:00","연속",null,null,null,201701110040,"-"]
[212,"광주전남","목포","고창영광 T/L","154kV 장성-영광T/L전선접속개소전선교체공사","0 상단측 전선교체 관련 하단선로 안전조치 0 하단측 고창-영광T/L 송전용 피뢰기 설치 : 45기 135set","2017-03-21 07:00","2017-03-28 18:00","2017-03-21 07:00","2017-03-28 18:00","연속",null,null,null,201701110045,"-"]
[213,"광주전남","목포","장성영광#2 T/L","154kV장성-영광T/L전선접속개소전선교체공사","0 전선 및 금구류 교체 : No.69~160","2017-03-21 07:00","2017-04-04 18:00","2017-03-21 07:00","2017-04-04 18:00","연속",null,null,null,201701110044,"-"]
[214,"광주전남","목포","고창홍농 T/L","154kV 고창-홍농T/L전선접속개소전선교체공사","0 전선 및 금구류 교체 : No.42~46,61~63호 0 송전용 피뢰기 설치 : 27기 111set","2017-03-14 07:00","2017-03-20 18:00","2017-03-14 07:00","2017-03-20 18:00","연속",null,null,null,201701110043,"-"]
[215,"광주전남","순천","광양하동#1 T/L","154kV 광양-하동#1T/L(용량증대공사 하자조치)","154kV 광양-하동#1,2T/L 용량증대공사 하자조치 - 용량증대공사관련 하자조치","2017-03-13 07:00","2017-03-15 18:00","2017-03-13 07:00","2017-03-15 18:00","연속",null,null,null,201701110099,"-"]
[216,"광주전남","순천","광양하동#2 T/L","154kV 광양-하동#2T/L(용량증대공사 하자조치)","154kV 광양-하동#1,2T/L 용량증대공사 하자조치 - 용량증대공사관련 하자조치","2017-03-16 07:00","2017-03-18 18:00","2017-03-16 07:00","2017-03-18 18:00","연속",null,null,null,201701110100,"-"]
[217,"광주전남","순천","순천율촌#1 T/L","154kV 순천-율촌#1T/L(송전선로 보호배전반 교체)","2017년 순천전력지사 변전협력회사 총액공사 - 순천,율촌S/S 송전선로 보호배전반 교체","2017-03-04 09:00","2017-03-05 18:00","2017-03-04 09:00","2017-03-05 18:00","연속",null,null,null,201701240057,"-"]
[218,"광주전남","순천","여천여수#1 T/L","154kV 여천-여수#1T/L(여수S/S LA 교체)","2017년 순천전력지사 변전협력회사 총액공사 - 여수S/S LA 교체 - 보조계전기 교체","2017-03-20 10:00","2017-03-20 18:00","2017-03-20 10:00","2017-03-20 18:00","당일",null,null,null,201701110083,"-"]
[219,"광주전남","순천","여천여수#2 T/L","154kV 여천-여수#2T/L(여수S/S LA 교체)","2017년 순천전력지사 변전협력회사 총액공사 - 여수S/S LA 교체 - 보조계전기 교체","2017-03-23 10:00","2017-03-23 18:00","2017-03-23 10:00","2017-03-23 18:00","당일",null,null,null,201701110085,"-"]
[220,"광주전남","순천","여수산단개폐소 154kV #2 BUS TIE GIS","154kV 전력설비 보호반(새롬프로텍) 성능개선","154kV 전력설비 보호반(새롬프로텍) 성능개선","2017-03-06 09:00","2017-03-06 18:00","2017-03-06 09:00","2017-03-06 18:00","당일",null,null,null,201701100086,"-"]
[221,"광주전남","순천","여수산단개폐소 65-66 SEC GIS","154kV 전력설비 보호반(새롬프로텍) 성능개선","154kV 전력설비 보호반(새롬프로텍) 성능개선","2017-03-06 09:00","2017-03-06 18:00","2017-03-06 09:00","2017-03-06 18:00","당일",null,null,null,201701100083,"-"]
[222,"광주전남","순천","여수산단개폐소 60-61 SEC GIS","154kV 전력설비 보호반(새롬프로텍) 성능개선","154kV 전력설비 보호반(새롬프로텍) 성능개선","2017-03-06 09:00","2017-03-06 18:00","2017-03-06 09:00","2017-03-06 18:00","당일",null,null,null,201701100097,"-"]
[223,"광주전남","순천","여천호남TP#2 T/L","154kV 여천-호남TP#2T/L(A,B,C상 LA 교체)","2017년 순천전력지사 변전협력회사 총액공사 - 여천-호남TP#2T/L LA 교체","2017-03-02 10:00","2017-03-02 18:00","2017-03-02 10:00","2017-03-02 18:00","당일",null,null,null,201701100468,"-"]
[224,"광주전남","순천","용성여수산단#1 T/L","154kV 용성-여수산단#1T/L(송전선로보호배전반 교체)","2017년 순천전력지사 변전협력회사 총액공사 - 용성S/S 송전선로보호배전반 교체 - 여수산단개폐소 송전선로보호배전반 교체","2017-03-07 09:00","2017-03-09 18:00","2017-03-07 09:00","2017-03-09 18:00","연속",null,null,null,201701110087,"-"]
[225,"광주전남","순천","용성여수산단#2 T/L","154kV 용성-여수산단#2T/L(송전선로보호배전반 교체)","2017년 순천전력지사 변전협력회사 총액공사 - 용성S/S 송전선로보호배전반 교체 - 여수산단개폐소 송전선로보호배전반 교체","2017-03-13 09:00","2017-03-15 18:00","2017-03-13 09:00","2017-03-15 18:00","연속",null,null,null,201701110088,"-"]
[226,"광주전남","순천","율촌화치#2 T/L","154kV 율촌-화치#2T/L(율촌SS LA 교체)","2017년 순천전력지사 변전협력회사 총액공사 - 율촌S/S LA 교체","2017-03-14 10:00","2017-03-14 18:00","2017-03-14 10:00","2017-03-14 18:00","당일",null,null,null,201701110075,"-"]
[227,"광주전남","순천","율촌화치#1 T/L","154kV 율촌-화치#1T/L(율촌SS LA 교체)","2017년 순천전력지사 변전협력회사 총액공사 - 율촌S/S LA 교체","2017-03-13 10:00","2017-03-13 18:00","2017-03-13 10:00","2017-03-13 18:00","당일",null,null,null,201701110074,"-"]
[228,"대구경북","경산","신경산노변 T/L","신경산S/S 신경산-노변T/L 휴전","신경산S/S 신경산-노변T/L 보호PNL 대체공사 노변S/S 신경산-노변T/L 보호PNL 대체공사","2017-03-27 09:00","2017-03-28 18:00","2017-03-27 09:00","2017-03-28 18:00","연속",null,null,null,201701050202,"-"]
[229,"대구경북","구미","상주점촌#1 T/L","154kV 상주-점촌T/L 노후취약지지물 교체공사","가. 공사구간 : 154kV 상주-점촌T/L No.38~49호 나. 공사수량 1) 지지물 : 철거 6기(39~43호, 46호), 설치 4기(39, 41, 43, 46호) 2) 전력선 : ACSR 330㎟*S*2C 2.918km(재사용구간No..44~49호 포함) 3) 가공지선 : ACSR 97㎟*S*1C(OPGW 별도시행)","2017-03-25 08:00","2017-04-19 18:00","2017-03-25 08:00","2017-04-19 18:00","연속",null,null,null,201701130016,"-"]
[230,"대구경북","달성","강창성서#1 T/L","2017년 달성전력지사 상반기 정밀점검","강창 GIS 정밀점검","2017-03-17 07:00","2017-03-19 18:00","2017-03-17 07:00","2017-03-19 18:00","연속",null,null,null,201701040110,"-"]
[231,"대구경북","달성","다산강창#1 T/L","2017년 달성전력지사 상반기 정밀점검","6433,6100 무부하가압선로","2017-03-07 12:00","2017-03-10 18:00","2017-03-07 12:00","2017-03-10 18:00","매일",null,null,null,201701040109,"-"]
[232,"대구경북","달성","고령쌍림#2 T/L","안전확보 휴전","- 고령다산#2(상단) 송전피뢰기 설치를 위한 안전확보 휴전","2017-03-04 08:00","2017-03-05 18:00","2017-03-04 08:00","2017-03-05 18:00","연속",null,null,null,201701160131,"-"]
[233,"대구경북","달성","고령다산#2 T/L","154kV 고령다산#2T/L 피뢰기설치","- No.2~12호간 송전피뢰기 설치","2017-03-04 08:00","2017-03-05 18:00","2017-03-04 08:00","2017-03-05 18:00","연속",null,null,null,201701160111,"-"]
[234,"대구경북","달성","논공달성#2 T/L","EBA 자기애관 교체공사","자기애관을 폴리머애관으로 교체 GIS 정밀점검","2017-03-10 07:00","2017-03-12 18:00","2017-03-10 07:00","2017-03-12 18:00","연속",null,null,null,201701090252,"-"]
[235,"대구경북","달성","논공달성#1 T/L","EBA 자기애관 교체공사","자기애관을 폴리머애관으로 교체 GIS 정밀점검","2017-03-10 07:00","2017-03-12 18:00","2017-03-10 07:00","2017-03-12 18:00","연속",null,null,null,201701090251,"-"]
[236,"대구경북","달성","성서달성#1 T/L","EBA 자기애관 교체공사","자기애관을 폴리머애관으로 교체 GIS 정밀점검","2017-03-17 07:00","2017-03-19 18:00","2017-03-17 07:00","2017-03-19 18:00","연속",null,null,null,201701090254,"-"]
[237,"대구경북","달성","성서달성#2 T/L","EBA 자기애관 교체공사","자기애관을 폴리머애관으로 교체 GIS정밀점검","2017-03-24 07:00","2017-03-26 18:00","2017-03-24 07:00","2017-03-26 18:00","연속",null,null,null,201701090256,"-"]
[238,"대구경북","달성","대구범물#2 T/L","2017년 직할 가공송전정비협력회사총액공사","대구-범물#2T/L 불량개소 정비","2017-03-17 08:00","2017-03-19 18:00","2017-03-17 08:00","2017-03-19 18:00","매일",null,null,null,201701090305,"-"]
[239,"대구경북","달성","대구범물#1 T/L","2017년 직할 가공송전정비협력회사총액공사","대구-범물#1T/L 불량개소 정비","2017-03-10 08:00","2017-03-12 18:00","2017-03-10 08:00","2017-03-12 18:00","매일",null,null,null,201701090304,"-"]
[240,"대구경북","달성","상인봉덕#2 T/L","EBA 자기애관 교체공사","자기애관을 폴리머애관으로 교체","2017-03-13 09:00","2017-03-15 18:00","2017-03-13 09:00","2017-03-15 18:00","연속",null,null,null,201701090250,"-"]
[241,"대구경북","달성","상인봉덕#1 T/L","EBA 자기애관 교체공사","자기애관을 폴리머애관으로 교체","2017-03-13 09:00","2017-03-15 18:00","2017-03-13 09:00","2017-03-15 18:00","연속",null,null,null,201701090249,"-"]
[242,"대구경북","직할","범물남대구#2 T/L","남대구S/S 모선보호반 교체","모선보호반 교체","2017-03-09 10:30","2017-03-09 11:00","2017-03-23 10:30","2017-03-23 11:00","당일",null,null,null,201701100354,"-"]
[243,"대구경북","직할","범물남대구#1 T/L","남대구S/S 모선보호반 교체","모선보호반 교체","2017-03-09 11:30","2017-03-09 12:00","2017-03-23 11:30","2017-03-23 12:00","당일",null,null,null,201701100365,"-"]
[244,"부산울산","북부산","모라엄궁#1 T/L","2017년 장기사용 보호배전반 대체","모라-엄궁#1T/L 보호반 대체 (모라647,엄궁667 양측작업)","2017-03-06 09:00","2017-03-08 18:00","2017-03-06 09:00","2017-03-08 18:00","연속",null,null,null,201701050237,"○"]
[245,"부산울산","북부산","북부산삼랑진PP#2 T/L","북부산S/S 154kV 취약설비 GIS화 공사","154kV GIS 부싱설치 관련 안전이격관련 6H7 CB 휴전","2017-03-15 09:00","2017-03-15 18:00","2017-03-15 09:00","2017-03-15 18:00","당일",null,null,null,201701050240,"-"]
[246,"부산울산","북부산","북부산호포 T/L","북부산S/S 154kV 취약설비 GIS화 공사","154kV GIS 부싱설치 관련 안전이격관련 6J7 CB 휴전","2017-03-16 09:00","2017-03-16 18:00","2017-03-16 09:00","2017-03-16 18:00","당일",null,null,null,201701050241,"-"]
[247,"부산울산","북부산","북부산삼랑진PP#1 T/L","북부산S/S 154kV 취약설비 GIS화 공사","154kV GIS 부싱설치 관련 안전이격관련 6F7 CB 휴전","2017-03-17 09:00","2017-03-17 18:00","2017-03-17 09:00","2017-03-17 18:00","당일",null,null,null,201701050238,"○"]
[248,"부산울산","북부산","삼계김해 T/L","154kV 삼계T/L 지장철탑 이설공사(요청자시행)","기설No.40-신설No.41-1 및 신설No.42-기설No.43호간 공중이동, 긴선작업","2017-03-18 08:00","2017-03-19 18:00","2017-03-18 08:00","2017-03-19 18:00","연속",null,null,null,201701090123,"-"]
[249,"부산울산","북부산","한림정삼계#1 T/L","154kV 삼계T/L 지장철탑 이설공사(요청자시행)","기설No.40-신설No.41-1 및 신설No.42-기설No.43호간 공중이동, 긴선작업","2017-03-18 08:00","2017-03-19 18:00","2017-03-18 08:00","2017-03-19 18:00","연속",null,null,null,201701090124,"-"]
[250,"부산울산","북부산","한림정삼계#2 T/L","154kV 삼계T/L 지장철탑 이설공사(요청자시행)","기설No.40-신설No.41-1 및 신설No.42-기설No.43호간 공중이동, 긴선작업","2017-03-25 08:00","2017-03-26 18:00","2017-03-25 08:00","2017-03-26 18:00","연속",null,null,null,201701090127,"-"]
[251,"부산울산","북부산","삼계어방 T/L","154kV 삼계T/L 지장철탑 이설공사(요청자시행)","기설No.40-신설No.41-1 및 신설No.42-기설No.43호간 공중이동, 긴선작업","2017-03-25 08:00","2017-03-26 18:00","2017-03-25 08:00","2017-03-26 18:00","연속",null,null,null,201701090125,"-"]
[252,"부산울산","북부산","양산삼랑진PP T/L","양산S/S 취약설비 현대화공사","양산S/S 154kV 북부산-양산T/L 가수전기초터파기 안전이격확보","2017-03-13 09:00","2017-03-14 18:00","2017-03-13 09:00","2017-03-14 18:00","연속",null,null,null,201701100411,"-"]
[253,"부산울산","북부산","북부산양산 T/L","양산S/S 취약설비 현대화공사","양산S/S 154kV 북부산-양산T/L PT 이설 및 가수전기초터파기 안전이격확보","2017-03-13 09:00","2017-03-14 18:00","2017-03-13 09:00","2017-03-14 18:00","연속",null,null,null,201701100410,"-"]
[254,"부산울산","북부산","북부산양산 T/L","양산S/S 취약설비 현대화공사","양산S/S 154kV 북부산-양산T/L Line PT 이설 기초터파기 안전이격확보","2017-03-06 09:00","2017-03-06 18:00","2017-03-06 09:00","2017-03-06 18:00","당일",null,null,null,201701100409,"-"]
[255,"부산울산","울산","신온산온산#3 T/L","2017년도 울산전력지사 170kV 개폐장치 정밀점검","신온산S/S 697 GIS 정밀점검 신온산, 온산S/S 신온산온산#3T/L 보호반 펌웨어 업그레이드 및 연동시험","2017-03-01 09:00","2017-03-03 18:00","2017-03-01 09:00","2017-03-03 18:00","연속",null,null,null,201701060223,"-"]
[256,"부산울산","울산","신울산언양#2 T/L","154kV 신울산-언양T/L 전선접속개소 전선교체공사","ㅁ 전력선 교체 : 154kV 신울산-언양#2 T/L No.59~64","2017-03-30 07:00","2017-04-01 18:00","2017-03-30 07:00","2017-04-01 18:00","연속",null,null,null,201701190079,"-"]
[257,"부산울산","울산","신울산울산#2 T/L","2015-16년도 울산전력지사 변전협력회사 총액공사","신울산S/S 신울산-울산#2T/L ILC PNL 대체","2017-03-07 09:00","2017-03-08 18:00","2017-03-07 09:00","2017-03-08 18:00","연속",null,null,null,201701100153,"-"]
[258,"부산울산","울산","신울산언양#1 T/L","154kV 신울산-언양T/L 전선접속개소 전선교체공사","ㅁ 전력선 교체 : 154kV 신울산-언양#1 T/L No.59~64","2017-03-27 07:00","2017-03-29 18:00","2017-03-27 07:00","2017-03-29 18:00","연속",null,null,null,201701190077,"-"]
[259,"부산울산","울산","용연처용#2 T/L","용연S/S 170kV 장기사용 GIS 대체공사","용연S/S 657 GIS 대체관련 #2BUS 시험가압","2017-03-29 17:00","2017-03-29 18:00","2017-03-29 17:00","2017-03-29 18:00","당일",null,null,null,201701090140,"-"]
[260,"부산울산","울산","용연울산TP#2 T/L","용연S/S 170kV 장기사용 GIS 대체공사","용연S/S 657 GIS 대체","2017-03-28 08:00","2017-04-13 18:00","2017-03-28 08:00","2017-04-13 18:00","연속",null,null,null,201701090137,"-"]
[261,"부산울산","울산","신울산웅촌#1 T/L","2017년도 울산전력지사 170kV 개폐장치 정밀점검","웅촌S/S 647 GIS 정밀점검","2017-03-19 08:00","2017-03-21 18:00","2017-03-19 08:00","2017-03-21 18:00","연속",null,null,null,201701090161,"-"]
[262,"부산울산","울산","신울산웅촌#2 T/L","2017년도 울산전력지사 170kV 개폐장치 정밀점검","웅촌S/S 627 GIS 정밀점검","2017-03-22 08:00","2017-03-24 18:00","2017-03-22 08:00","2017-03-24 18:00","연속",null,null,null,201701090163,"-"]
[263,"부산울산","직할","서부산부민#2 T/L","2017년도 직할 변전협력회사 총액공사","부민S/S 서부산-부민#2T/L GIS 보통점검","2017-03-28 10:00","2017-03-28 18:00","2017-03-28 10:00","2017-03-28 18:00","당일",null,null,null,201701060122,"-"]
[264,"부산울산","직할","미남서면#1 T/L","2016-2017년 서부산 송전협력회사 총액공사","154kV 미남-서면T/L 9-10,13-14호 전선교체","2017-03-06 08:00","2017-03-12 18:00","2017-03-06 08:00","2017-03-12 18:00","연속",null,null,null,201701020076,"-"]
[265,"부산울산","직할","미남서면#2 T/L","2016-2017년 서부산 송전협력회사 총액공사","154kV 미남-서면T/L 9-10,13-14호 전선교체","2017-03-06 08:00","2017-03-12 18:00","2017-03-06 08:00","2017-03-12 18:00","연속",null,null,null,201701020077,"-"]
[266,"경남","직할","창공S/S 154kV #1 BUS TIE CB","창공S/S 154kV #1BUS-TIE CB 초기점검","창공S/S 154kV #1BUS-TIE CB 초기점검","2017-03-12 09:30","2017-03-12 17:30","2017-03-12 09:30","2017-03-12 17:30","당일",null,null,null,201701090131,"-"]
[267,"경남","진주","하동하동화력#2 T/L","154kV 하동-하동화력T/L 전선교체공사","154kV 하동-하동화력T/L 전선교체공사 - 154kV 하동-하동화력 #1,2T/L - 3~7, 10~12, 13~14, 21~22, 26~28, 30~34, 49~53호","2017-03-25 08:00","2017-04-06 18:00","2017-03-25 08:00","2017-04-06 18:00","연속",null,null,null,201701090327,"-"]
[268,"경남","통영","고성통영 T/L","154kV 고성분기T/L SB Damp. 설치","154kV 고성분기T/L SB Damp. 설치 No.1-8","2017-03-19 07:00","2017-03-19 18:00","2017-03-19 07:00","2017-03-19 18:00","당일",null,null,null,201701040075,"-"]
[269,"경남","통영","삼천포사천#2 T/L","154kV 삼천포-사천#2T/L 전선교체","154kV 삼천포-사천#2T/L 전선교체 No.15-18, 41-45","2017-03-26 07:00","2017-04-01 18:00","2017-03-26 07:00","2017-04-01 18:00","연속",null,null,null,201701040071,"-"]
[270,"경남","통영","삼천포사천#1 T/L","154kV 삼천포-사천#1T/L 전선교체","154kV 삼천포-사천#1T/L 전선교체 No.15-18, 41-45","2017-03-20 07:00","2017-03-26 18:00","2017-03-20 07:00","2017-03-26 18:00","연속",null,null,null,201701040069,"-"]
[271,"경남","통영","신고성거제#1 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","154kV 신고성-거제T/L 2호 설치 및 전력선 이설","2017-03-25 07:00","2017-03-26 18:00","2017-03-25 07:00","2017-03-26 18:00","연속",null,null,null,201701090055,"-"]
[272,"경남","통영","신고성통영 T/L","154kV 신고성-통영T/L 이도조정","154kV 신고성-통영T/L 이도조정 No.121-122","2017-03-18 07:00","2017-03-18 18:00","2017-03-18 07:00","2017-03-18 18:00","당일",null,null,null,201701040074,"-"]