{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":6,"n_cols":16,"rows_kept":6,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 7월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"대전충남","서산","신서산S/S 신서산-신안성#2T/L CB","'17년 서산P/O 765kV GIS 보통점검공사","신서산S/S 765kV 신서산-신안성 #2T/L GIS(8671) 보통점검","2017-07-03 09:00","2017-07-04 18:00","2017-07-03 09:00","2017-07-04 18:00","연속",null,null,null,201705150289]
[2,"부산울산","동부산","신고리S/S #2 M.Tr A-1","고리NP S/Y 7D01DS 가스누기 보수 시험가압","고리NP S/Y 7D01DS 가스누기 보수 시험가압(#72BUS + 신고리#2M.Tr=신고리-고리NP#2T/L)","2017-07-04 10:00","2017-07-04 11:00","취소","취소","당일",null,null,null,201705180024]

{"sheet":"345송부","index":1,"n_rows":130,"n_cols":16,"rows_kept":130,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 7월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","중부S/S #2 M.Tr A","345kV 중부S/S 모자익배전반 정비공사","중부S/S 345kV 72 BAY (7272) 모자익반 교체","2017-07-07 10:00","2017-07-14 18:00","2017-07-07 10:00","2017-07-14 18:00","연속",null,null,null,201705120163]
[2,"인천","김포","신김포S/S 345KV 75-76 SEC CB","신김포S/S 345KV 75-76 SEC GIS 기기점검","신김포S/S 345KV 75-76 SEC GIS 기기점검","2017-07-06 10:00","2017-07-06 18:00","2017-07-06 10:00","2017-07-06 18:00","당일",null,null,null,201705120180]
[3,"인천","김포","신김포S/S 345KV 70-71 SEC CB","신김포S/S 345KV 70-71 SEC GIS 기기점검","신김포S/S 345KV 70-71 SEC GIS 기기점검","2017-07-05 10:00","2017-07-05 18:00","2017-07-05 10:00","2017-07-05 18:00","당일",null,null,null,201705120179]
[4,"인천","김포","신김포S/S 345kV #1 Sh.R","신김포S/S 345kV #1 Sh.R 써지측정장치 설치공사","신김포S/S 345kV #1 Sh.R 써지측정장치 설치","2017-07-05 09:00","2017-07-07 18:00","2017-07-05 09:00","2017-07-07 18:00","연속",null,null,null,201705180037]
[5,"인천","인천","신가좌S/S #1 M.Tr A","신가좌S/S #1M.Tr 및 GPT 보통점검 공사","신가좌S/S #1M.Tr 휴전작업 - #1M.Tr 및 GPT 보통점검 공사 - #1M.Tr LA 보통점검 공사","2017-07-04 09:00","2017-07-05 18:00","2017-07-04 09:00","2017-07-05 18:00","연속",null,null,null,201705170177]
[6,"인천","인천","신가좌S/S TIE-#4 M.Tr 1차 CB (신) (7600 A)","신가좌S/S 7600 GIS 초기점검 공사","신가좌S/S 7600 GIS 초기점검 공사","2017-07-11 09:00","2017-07-11 18:00","2017-07-11 09:00","2017-07-11 18:00","당일",null,null,null,201705120002]
[7,"인천","인천","신가좌S/S #4 M.Tr 1차 CB (신) (7672 A)","신가좌S/S 7672 GIS 초기점검 공사","신가좌S/S 7672 GIS 초기점검 공사","2017-07-12 09:00","2017-07-12 18:00","2017-07-12 09:00","2017-07-12 18:00","당일",null,null,null,201705120003]
[8,"인천","인천","신경서S/S #1 M.Tr 1차 CB (7172)","인천전력지사 362kV GIS 정밀점검 공사(신경서S/S 7172)","인천전력지사 362kV GIS 정밀점검 공사(신경서S/S 7172) - 362kV GIS 정밀점검 공사","2017-07-20 08:00","2017-07-22 18:00","2017-07-11 08:00","2017-07-13 18:00","연속",null,null,null,201705100265]
[9,"인천","인천","인천T/P 인천복합 #2 S/T CB (7671)","인천전력지사 362kV GIS 정밀점검 공사(인천CC 7671)","인천전력지사 362kV GIS 정밀점검 공사(인천CC 7671) - 362kV GIS 정밀점검 공사","2017-07-17 08:00","2017-07-19 18:00","2017-07-06 08:00","2017-07-08 18:00","연속",null,null,null,201705100264]
[10,"인천","인천","인천T/P 인천복합 #3,4 G/T CB (7571)","인천전력지사 362kV GIS 정밀점검 공사(인천CC 7571)","인천전력지사 362kV GIS 정밀점검 공사(인천CC 7571) - 362kV GIS 정밀점검 공사","2017-07-10 08:00","2017-07-12 18:00","2017-07-03 08:00","2017-07-05 18:00","연속",null,null,null,201705100263]
[11,"인천","인천","포스코S/Y 신경서포스코SY#2T/L-TIE CB (7400)","362kV GIS 정밀점검 공사 (포스코S/Y 7400)","362kV GIS 정밀점검 공사 (포스코S/Y 7400) - GIS 정밀점검 공사","2017-07-03 08:00","2017-07-05 18:00","2017-07-03 08:00","2017-07-05 18:00","연속",null,null,null,201705100261]
[12,"인천","인천","포스코파워S/Y 신경서포스코SY#2T/L CB (7471)","362kV GIS 정밀점검 공사 (포스코S/Y 7471)","362kV GIS 정밀점검 공사 (포스코S/Y 7471) - GIS 정밀점검 공사","2017-07-06 08:00","2017-07-08 18:00","2017-07-06 08:00","2017-07-08 18:00","연속",null,null,null,201705100262]
[13,"경기북부","구리","미금S/S STATCOM M.Tr CB","미금S/S STATCOM M.Tr, AUX M.TR 정밀점검공사","미금S/S 345kV STATCOM M.Tr, AUX M.TR 정밀점검공사","2017-07-01 08:00","2017-07-09 18:00","2017-07-01 08:00","2017-07-09 18:00","연속",null,null,null,201705190120]
[14,"경기북부","구리","신가평포천LNGCC#2 T/L","항공장애표시구 교체","o No.67-68 항공장애표시구 교체 (4개) -사유 : 소음발생에 따른 민원 제기 -작업책임자 : 신태식(010-9744-3468)","2017-07-05 08:00","2017-07-05 18:00","2017-07-05 08:00","2017-07-05 18:00","당일",null,null,null,201705100108]
[15,"경기북부","구리","신가평S/S 345kV #4 Sh.R","765kV 신가평S/S 소음저감대책 공사","#2, 3, 4Sh.R 방음벽 및 흡음판 설치","2017-07-17 09:00","2017-07-21 18:00","2017-07-17 09:00","2017-07-21 18:00","매일",null,null,null,201705110058]
[16,"경기북부","구리","신가평S/S 345kV #3 Sh.R","765kV 신가평S/S 소음저감대책 공사","#2, 3, 4Sh.R 방음벽 및 흡음판 설치","2017-07-10 09:00","2017-07-14 18:00","2017-07-10 09:00","2017-07-14 18:00","매일",null,null,null,201705110056]
[17,"경기북부","구리","신가평포천LNGCC#1 T/L","항공장애표시구 교체","o No.67-68 항공장애표시구 교체 (3개) -사유 : 소음발생에 따른 민원 제기 -작업책임자 : 신태식(010-9744-3468)","2017-07-04 08:00","2017-07-04 18:00","2017-07-04 08:00","2017-07-04 18:00","당일",null,null,null,201705100105]
[18,"경기북부","구리","신가평S/S 345kV #2 Sh.R","765kV 신가평S/S 소음저감대책 공사","#2, 3, 4Sh.R 방음벽 및 흡음판 설치","2017-07-03 09:00","2017-07-07 18:00","2017-07-03 09:00","2017-07-07 18:00","매일",null,null,null,201705110055]
[19,"경기북부","구리","신포천포천CC#1 T/L","신포천-포천CC #1,2T/L 3상 접지BAR 설치","신포천-포천CC #1,2T/L 3상 접지BAR 설치 -A,B,C상 공통접지","2017-07-10 09:00","2017-07-11 18:00","2017-07-10 09:00","2017-07-11 18:00","연속",null,null,null,201705120062]
[20,"경기북부","구리","신포천포천CC#2 T/L","신포천-포천CC #1,2T/L 3상 접지BAR 설치","신포천-포천CC #1,2T/L 3상 접지BAR 설치 -A,B,C상 공통접지","2017-07-12 09:00","2017-07-13 18:00","2017-07-12 09:00","2017-07-13 18:00","연속",null,null,null,201705120063]
[21,"경기북부","직할","신의정부S/S #1 M.Tr A","17년도 경기북부 직할 345kV M.Tr 정밀점검","신의정부S/S #1M.Tr A상 가스이상 판정에 따른 정밀점검","2017-07-03 09:00","2017-07-07 18:00","취소","취소","연속",null,null,null,201705110003]
[22,"경기북부","직할","양주S/S #1 M.Tr A","17년 362kV GIS 장밀점검","7272,7200CB 정밀점검","2017-07-10 09:00","2017-07-14 18:00","2017-07-10 09:00","2017-07-14 18:00","연속",null,null,null,201705080093]
[23,"경기북부","직할","양주S/S 345kV #1 BUS","17년 362kV GIS 장밀점검","7171CB 정밀점검 7151EDS 정밀점검","2017-07-03 09:00","2017-07-03 20:00","취소","취소","연속",null,null,null,201705080083]
[24,"경기북부","직할","신의정부양주#1 T/L","17년 362kV GIS 장밀점검","7171CB 정밀점검","2017-07-03 09:00","2017-07-07 18:00","2017-07-03 09:00","2017-07-07 18:00","연속",null,null,null,201705080080]
[25,"경기북부","직할","양주S/S 345kV #2 BUS","17년 362kV GIS 장밀점검","7172,7100CB 정밀점검 7152EDS 정밀점검","2017-07-10 09:00","2017-07-10 20:00","취소","취소","연속",null,null,null,201705080090]
[26,"경기북부","파주","신덕은S/S 신덕은-장문CC #1T/L CB (7572)","신덕은S/S 362kV GIS 제작사 유압시스템 보수공사","O 7572 GIS 유압시스템 보수","2017-07-03 10:00","2017-07-04 18:00","2017-07-03 10:00","2017-07-04 18:00","연속",null,null,null,201705120250]
[27,"경기북부","파주","신덕은S/S 345kV #2 BUS","신덕은S/S 345kV SW 증설공사","ㅇ 345kV GIS 50kA 4000A 3CB 설치 ㅇ 기타 부대공사 1식 * LG Display 전력공급 송전선로 신설","2017-07-24 09:00","2017-07-31 18:00","2017-07-24 09:00","2017-07-31 18:00","연속",null,null,null,201704130155]
[28,"경기북부","파주","신덕은S/S 신덕은-장문CC #2T/L CB (7372)","신덕은S/S 362kV GIS 제작사 유압시스템 보수공사","O 7372 GIS 유압시스템 보수","2017-07-05 10:00","2017-07-06 18:00","2017-07-05 10:00","2017-07-06 18:00","연속",null,null,null,201705120251]
[29,"경기북부","파주","신덕은S/S 345kV #1 BUS","신덕은S/S 345kV SW 증설공사","ㅇ 345kV GIS 50kA 4000A 3CB 설치 ㅇ 기타 부대공사 1식 * LG Display 전력공급 송전선로 신설","2017-07-04 09:00","2017-07-12 18:00","2017-07-04 09:00","2017-07-12 18:00","연속",null,null,null,201705180079]
[30,"경기북부","파주","신파주S/S #1SVC Tr CB","신파주S/S SVC FC 투입용차단기 설치공사","SVC FC 투입용차단기 설치 병행 : #5 FC 투수블록 설치(토건 김기덕)","2017-07-10 09:00","2017-07-16 18:00","2017-07-10 09:00","2017-07-16 18:00","연속",null,null,null,201705190135]
[31,"경기북부","파주","신파주양주#2 T/L","345kV 신파주-양주#2T/L 접속개소 전선교체공사","345kV 신파주-양주#2T/L No.21~22 등 5개소","2017-07-01 07:00","2017-07-07 18:00","취소","취소","연속",null,null,null,201705100266]
[32,"경기","군포","서서울2S/S 345kV #76BUS GIS","345kV 신군포S/S 건설공사","- 모선PT 보조릴레리 불량건 교체작업","2017-07-04 08:00","2017-07-04 18:00","2017-07-04 08:00","2017-07-04 18:00","당일",null,null,null,201705180054]
[33,"경기","군포","서서울S/S #4 M.Tr A","서서울S/S 154kV 취약설비 GIS화 공사(#4MTr)","서서울S/S 154kV 취약설비 GIS화 공사(#4MTr) - T-Bus DS철거, 기초파쇄, 리드 연결","2017-07-01 09:00","2017-07-01 18:00","2017-07-01 09:00","2017-07-01 18:00","당일",null,null,null,201703140166]
[34,"경기","군포","서서울S/S #1 M.Tr","서서울S/S 154kV 취약설비 GIS화 공사(#1MTr)","서서울S/S 154kV 취약설비 GIS화 공사(#1MTr) - T-Bus DS철거, 기초파쇄, 리드 연결 - 345kV 1변압기 1차 LA 대체","2017-07-02 09:00","2017-07-02 18:00","2017-07-02 09:00","2017-07-02 18:00","당일",null,null,null,201703140167]
[35,"경기","군포","서서울S/S #2 M.Tr","서서울S/S 154kV 취약설비 GIS화 공사(#2MTr)","서서울S/S 154kV 취약설비 GIS화 공사(#2M.Tr) - T-Bus DS철거, 기초파쇄, 리드 연결","2017-07-08 09:00","2017-07-08 18:00","2017-07-08 09:00","2017-07-08 18:00","당일",null,null,null,201703140168]
[36,"경기","군포","서서울S/S #3 M.Tr","서서울S/S 154kV 취약설비 GIS화 공사(#3M.Tr)","서서울S/S 154kV 취약설비 GIS화 공사(#3.MTr) - T-Bus DS철거, 기초파쇄, 리드 연결","2017-07-09 09:00","2017-07-09 18:00","2017-07-09 09:00","2017-07-09 18:00","당일",null,null,null,201703140169]
[37,"경기","성남","신성남S/S #4M.Tr","17년 성남변전협력회사 총액공사","75Bay BF PNL대체 및 7572,6444 GIS 개폐타임 측정","2017-07-08 09:00","2017-07-14 18:00","2017-07-08 09:00","2017-07-14 18:00","연속",null,null,null,201705150068]
[38,"경기","성남","신안성신성남#2 T/L","345kV신용인-동서울T/L(태전)OPGW시설공사","신용인동서울T/L No.6~35구간 13km OPGW 교체","2017-07-09 07:00","2017-07-14 18:00","2017-07-09 07:00","2017-07-14 18:00","연속",null,null,null,201705120049]
[39,"경기","성남","동서울신용인#2 T/L","345kV 신용인-동서울T/L 태전지구 지중화사업","○ 설치 : ACSR480㎟×2B×2C×0.2km. C/H2기 ○ 철거 : ACSR480㎟×2B×2C×2.5km. 철탑8기","2017-07-08 08:00","2017-07-15 18:00","2017-07-08 08:00","2017-07-15 18:00","연속",null,null,null,201704100490]
[40,"경기","직할","화성S/S #2M.Tr A","화성S/S 배전반 정비공사","화성S/S 배전반 정비공사","2017-07-05 09:00","2017-07-11 18:00","2017-07-05 09:00","2017-07-11 18:00","연속",null,null,null,201705150104]
[41,"강원","강릉","신양양S/S #3 M.Tr A","2017년 변전협력회사 총액공사","3MTR 3차측 단로기 과열 보수","2017-07-04 10:00","2017-07-04 18:00","2017-07-04 10:00","2017-07-04 18:00","당일",null,null,null,201705080379]
[42,"강원","동해","동해S/S 동해-양양PP T/L CB (7471)","2017년 동해변전소 362kV GIS 정밀점검공사","1. 동해S/S 동해-양양PP T/L CB 정밀점검(7471)","2017-07-12 09:30","2017-07-14 18:00","2017-07-12 09:30","2017-07-14 18:00","연속",null,null,null,201705110172]
[43,"강원","동해","동해S/S #2 M.Tr 1차 CB (7472)","2017년 동해변전소 362kV GIS 정밀점검공사","1. 동해S/S #2 M.Tr 1차 CB (7472) 정밀점검","2017-07-06 09:30","2017-07-08 18:00","2017-07-06 09:30","2017-07-08 18:00","연속",null,null,null,201705260022]
[44,"강원","동해","동해S/S 동해-양양PP T/L-#2 M.Tr 1차 CB (7400)","2017년 동해변전소 362kV GIS 정밀점검공사","1. 동해S/S 74 Bay Tie CB (7400) 정밀점검","2017-07-09 09:30","2017-07-11 18:00","2017-07-09 09:30","2017-07-11 18:00","연속",null,null,null,201705260021]
[45,"강원","동해","삼척GP 동해-삼척GP #2T/L CB (7771)","LS산전 345kV GIS 차단기 원인분석 대책 공사(삼척GP)","차단기 성능개선(7771) 1.Puffer cylinder 강도 개선 제품 교체 2. 투입저항부 구조 개선 제품 교체 3. 조립공정 개선 제품으로 교체","2017-07-03 09:30","2017-07-07 18:00","2017-07-03 09:30","2017-07-07 18:00","연속",null,null,null,201705110223]
[46,"강원","동해","삼척GP 삼척GP #2T/L - #1기동 Tr CB (7700)","LS산전 345kV GIS 차단기 원인분석 대책 공사(삼척GP)","차단기 성능개선(7700) 1.Puffer cylinder 강도 개선 제품 교체 2. 투입저항부 구조 개선 제품 교체 3. 조립공정 개선 제품으로 교체","2017-07-08 09:30","2017-07-12 18:00","2017-07-08 09:30","2017-07-12 18:00","연속",null,null,null,201705110226]
[47,"충북","직할","신제천신충주#1 T/L","345kV 신제천S/S GIS화 공사","신제천-신영주#1, 신충주#1T/L 옥외철구 → GIS 이설","2017-07-04 08:00","2017-07-10 18:00","2017-07-03 08:00","2017-07-11 18:00","연속",null,null,null,201705160017]
[48,"충북","직할","신제천S/S 345kV #2 BUS","345kV 신제천S/S GIS화 공사","345kV 옥외철구 #2BUS 철거","2017-07-05 08:00","2017-07-05 18:00","2017-07-03 08:00","2017-07-03 18:00","당일",null,null,null,201705160021]
[49,"충북","직할","신제천S/S 345kV #1 BUS","345kV 신제천S/S GIS화 공사","345kV 옥외철구 #1BUS 철거","2017-07-04 08:00","2017-07-04 18:00","2017-07-04 08:00","2017-07-04 18:00","당일",null,null,null,201705160020]
[50,"충북","직할","신제천신영주#1 T/L","345kV 신제천S/S GIS화 공사","신제천-신영주#1, 신충주#1T/L 옥외철구 → GIS 이설","2017-07-04 08:00","2017-07-10 18:00","2017-07-03 08:00","2017-07-11 18:00","연속",null,null,null,201705160015]
[51,"충북","청주","청원S/S #4 M.Tr A","17년도 청주전력지사 170kV GIS 정밀점검공사","청원S/S #4 M.Tr 2차 GIS 정밀점검","2017-07-04 09:30","2017-07-06 18:00","취소","취소","연속",null,null,null,201705080326]
[52,"충북","충주","신진천S/S 345kV #2 BUS","345kV 신진천S/S 용량부족 GIS 대체공사","345kV GIS 40kA 4000A → 63kA 6300A 12CB 대체","2017-07-26 13:00","2017-07-26 14:00","2017-07-26 13:00","2017-07-26 14:00","당일",null,null,"신뢰도개선",201703300127]
[53,"충북","충주","신진천S/S 345kV #1 BUS","345kV 신진천S/S 용량부족 GIS 대체공사","345kV GIS 40kA 4000A → 63kA 6300A 12CB 대체","2017-07-25 13:00","2017-07-26 13:00","2017-07-25 13:00","2017-07-26 13:00","당일",null,null,"신뢰도개선",201703300125]
[54,"대전충남","서산","신당진S/S #1 M.Tr A","'17년 서산P/O 345kV 변압기 정밀점검공사","'17년 서산P/O 345kV 변압기 정밀점검공사","2017-07-03 09:00","2017-07-14 18:00","2017-07-03 09:00","2017-07-14 18:00","연속",null,null,null,201705160026]
[55,"대전충남","아산","청양신온양#2 T/L","[송전] 345kV 청양-신온양T/L 지장송전선로 이설공사","가. 공사구간 : 345kV 청양-신온양T/L No.130～137 나. 지 지 물 : 가철탑 설치/철거 2기","2017-07-02 07:00","2017-07-09 18:00","취소","취소","연속",null,null,"신뢰도개선",201704070052]
[56,"전북","군산","군산새만금#1 T/L","군장국가산단 인입철도 노반공사 안전이격확보","군장국가산단 인입철도 노반공사 안전이격확보 휴전","2017-07-01 08:00","2017-07-10 18:00","2017-07-17 08:00","2017-07-26 18:00","매일",null,null,null,201705160006]
[57,"전북","군산","군산새만금#2 T/L","군장국가산단 인입철도 노반공사 안전이격확보","군장국가산단 인입철도 노반공사 안전이격확보 휴전","2017-07-01 08:00","2017-07-10 18:00","2017-07-17 08:00","2017-07-26 18:00","매일",null,null,null,201705160007]
[58,"전북","군산","군산신김제#2 T/L","345kV 군산-신김제T/L 하자접속함 교체공사","LS제 하자 중간접속함 교체공사","2017-07-17 08:00","2017-08-05 18:00","2017-07-17 08:00","2017-08-05 18:00","연속",null,null,null,201704180155]
[59,"전북","군산","새만금S/S #3 M.Tr A","새만금S/S #3M.Tr","군산P/O 차단기 보통점검공사","2017-07-01 09:00","2017-07-10 18:00","2017-07-10 09:00","2017-07-12 18:00","연속",null,null,null,201705170055]
[60,"전북","군산","새만금S/S #2 M.Tr A","새만금S/S #2M.Tr","군산P/O 차단기 보통점검공사","2017-07-01 09:00","2017-07-10 18:00","2017-07-03 09:00","2017-07-05 18:00","연속",null,null,null,201705170054]
[61,"광주전남","강진","신강진S/S #3 M.Tr A","신강진S/S 345kV 취약설비 GIS화","신강진S/S 옥외철구에서 GIS로 변경","2017-07-01 15:00","2017-07-01 19:00","2017-07-01 15:00","2017-07-01 19:00","당일",null,null,null,201705190091]
[62,"광주전남","강진","신강진S/S #1 M.Tr A","신강진S/S 345kV #1M.Tr (96P Trip → 경보 회로변경)","문서번호 광전본(변전)-5632 주변압기 96P 운전형태 변경 알림 신강진S/S 345kV #1M.Tr 96P Trip → 경보 회로변경","2017-07-11 09:00","2017-07-11 18:00","2017-07-11 09:00","2017-07-11 18:00","당일",null,null,null,201705190075]
[63,"광주전남","강진","신강진S/S #2 M.Tr A","신강진S/S 345kV #2M.Tr (96P Trip → 경보 회로변경)","문서번호 광전본(변전)-5632 주변압기 96P 운전형태 변경 알림 신강진S/S 345kV #2M.Tr 96P Trip → 경보 회로변경","2017-07-12 09:00","2017-07-12 18:00","2017-07-12 09:00","2017-07-12 18:00","매일",null,null,null,201705190076]
[64,"광주전남","강진","신강진S/S #2 M.Tr A","신강진S/S 345kV 취약설비 GIS화","신강진S/S 옥외철구에서 GIS로 변경","2017-07-01 11:00","2017-07-01 15:00","2017-07-01 11:00","2017-07-01 15:00","당일",null,null,null,201705190090]
[65,"광주전남","강진","신강진S/S #1 M.Tr A","신강진S/S 345kV 취약설비 GIS화","신강진S/S 옥외철구에서 GIS로 변경","2017-07-01 07:00","2017-07-01 11:00","2017-07-01 07:00","2017-07-01 11:00","당일",null,null,null,201705190088]
[66,"광주전남","목포","한빛2NP-한빛3NP #3T/L","345kV 한빛연락#3T/L(보호배전반대체)","B/F PNL 대체 GIS 정밀점검","2017-07-19 09:00","2017-07-25 18:00","2017-07-19 09:00","2017-07-25 18:00","연속",null,null,null,201705100046]
[67,"광주전남","목포","신김제한빛NP#2T/L","345kV 신김제-한빛#2T/L(보호배전반대체)","송전선로보호반 , B/F 대체 GIS 정밀점검","2017-07-04 09:00","2017-07-17 18:00","2017-07-04 09:00","2017-07-17 18:00","연속",null,null,null,201705100045]
[68,"광주전남","순천","광양여수TPT/L","345kV 광양-여수TP T/L","345kV 신남원-광양 등 4개T/L 전선접속개소 해소공사 - 신남원-광양T/L 전선교체 4회선철탑 안전이격거리 확보","2017-07-09 07:00","2017-07-11 18:00","2017-07-09 07:00","2017-07-11 18:00","연속",null,null,null,201705160095]
[69,"대구경북","경산","울주신경산#2 T/L","신경산S/S 345kV 울주-신경산#2T/L 휴전","73BAY B/F반 교체작업","2017-07-17 09:00","2017-07-21 18:00","취소","취소","연속",null,null,null,201705150029]
[70,"대구경북","경산","울주신경산#1 T/L","신경산S/S 345kV 울주-신경산#1T/L 휴전","74BAY B/F반 교체작업","2017-07-03 09:00","2017-07-07 18:00","취소","취소","연속",null,null,null,201705150021]
[71,"대구경북","경산","신경산S/S #4 M.Tr A","신경산S/S 345kV #4M.Tr 휴전","76BAY B/F반 교체작업","2017-07-10 09:00","2017-07-14 18:00","취소","취소","연속",null,null,null,201705150023]
[72,"대구경북","경산","신경산S/S #3 M.Tr A","신경산S/S 345kV #3M.Tr 휴전","73BAY B/F반 교체작업 7372 CB 보통점검","2017-07-17 09:00","2017-07-21 18:00","2017-07-17 09:00","2017-07-22 18:00","연속",null,null,null,201705150028]
[73,"대구경북","구미","선산S/S #2 M.Tr A","선산S/S 154kV 옥외철구 GIS화 공사","GIS 기초 부지 확보 T-BUS 철거","2017-07-03 09:00","2017-07-04 18:00","2017-07-07 08:00","2017-07-07 20:00","당일",null,null,null,201705040116]
[74,"대구경북","구미","선산S/S #1 M.Tr A","선산S/S 154kV 옥외철구 GIS화 공사","GIS 기초 부지 확보 및 T-BUS 철거","2017-07-17 09:00","2017-07-18 18:00","2017-07-13 08:00","2017-07-14 20:00","연속",null,null,null,201705040212]
[75,"대구경북","구미","선산S/S #4 M.Tr A","선산S/S 154kV 옥외철구 GIS화 공사","GIS 기초 부지 확보 및 T-BUS 철거","2017-07-10 09:00","2017-07-11 18:00","2017-07-10 08:00","2017-07-10 20:00","당일",null,null,null,201705040211]
[76,"대구경북","안동","청송P/P 신포항-청송PPT/L GIS","17년도 청송P/P 362kV 7271 GIS 정밀점검","-17년도 청송P/P 362kV 7271 GIS 정밀점검","2017-07-10 09:00","2017-07-12 18:00","취소","취소","연속",null,null,null,201705150011]
[77,"대구경북","안동","청송P/P 345kV #1 BUS","17년도 청송P/P 362kV 7271 GIS 정밀점검","- 17년도 청송P/P 362kV 7271 GIS 정밀점검 - 무부하 가압선로(7171 → #1BUS→7271) - 병행작업 : 154kV PT 보통점검","2017-07-10 09:00","2017-07-12 18:00","취소","취소","연속",null,null,null,201705150013]
[78,"대구경북","안동","청송P/P 신영주-청송PPT/L GIS","17년도 청송P/P 362kV 7271 GIS 정밀점검","- 17년도 청송P/P 362kV 7271 GIS 정밀점검 - 무부하 가압선로(7171 → #1BUS→7271)","2017-07-10 09:00","2017-07-12 18:00","취소","취소","연속",null,null,null,201705150012]
[79,"대구경북","영주","신영주청송PP T/L","2016-17 변전협력업체 총액공사","신영주S/S 345kV 73Bay 초기점검","2017-07-03 09:00","2017-07-03 18:00","취소","취소","당일",null,null,null,201705080012]
[80,"대구경북","영주","신영주S/S 345kV #1 BUS","신영주S/S STATCOM 설치공사","345kV 79Bay #1 주모선 Docking","2017-07-06 09:30","2017-07-10 18:00","취소","취소","연속",null,null,null,201705100190]
[81,"대구경북","영주","신영주예천PP#1 T/L","2016-17 변전협력업체 총액공사","신영주S/S 345kV 76Bay 초기점검","2017-07-05 09:00","2017-07-05 18:00","취소","취소","당일"]
[82,"대구경북","영주","신영주예천PP#2 T/L","2016-17 변전협력업체 총액공사","신영주S/S 345kV 75Bay 초기점검","2017-07-04 09:00","2017-07-04 18:00","취소","취소","당일"]
[83,"대구경북","영주","신제천신영주#1 T/L","신영주S/S STATCOM 설치공사","345kV 79Bay 무부하가압 및 안전확보","2017-07-14 18:00","2017-07-15 18:00","취소","취소","연속"]
[84,"대구경북","영주","신영주S/S 345kV #2 BUS","신영주S/S STATCOM 설치공사","345kV 79Bay #2 주모선 Docking","2017-07-11 09:30","2017-07-15 18:00","취소","취소","연속"]
[85,"대구경북","칠곡","북대구S/S #3 M.Tr","북대구S/S 345kV Sh.R 설치공사","북대구S/S 345kV Sh.R*1Bank 설치","2017-07-25 09:00","2017-07-31 18:00","2017-07-10 09:00","2017-07-16 18:00","연속"]
[86,"대구경북","칠곡","북대구S/S TIE-#3 M.Tr 1차 CB (7600)","북대구S/S 345kV Sh.R 설치공사","북대구S/S 345kV Sh.R 설치(100MVar)","2017-07-25 09:00","2017-09-29 18:00","2017-07-10 09:00","2017-09-29 18:00","연속"]
[87,"대구경북","칠곡","북대구S/S 345kV #1 BUS","북대구S/S 345kV Sh.R 설치공사","북대구S/S 345kV Sh.R(100MVar) 설치","2017-07-25 09:00","2017-07-31 18:00","2017-07-10 09:00","2017-07-16 18:00","연속"]
[88,"대구경북","칠곡","북대구서대구#1 T/L","북대구S/S 345kV Sh.R 설치공사","북대구S/S 345kV Sh.R(100MVar) 설치(Test 선로)","2017-07-30 09:00","2017-07-31 18:00","2017-07-15 09:00","2017-07-16 18:00","연속"]
[89,"대구경북","칠곡","서대구S/S #1 M.Tr(예비) CB","서대구S/S 예비M.Tr 휴전","서대구S/S 예비M.Tr 보통점검","2017-07-04 09:30","2017-07-04 18:00","2017-07-04 09:30","2017-07-04 18:00","당일"]
[90,"대구경북","칠곡","북대구서대구#2 T/L","서대구S/S 북대구서대구#2 T/L 휴전(77Bay)","서대구S/S 북대구-서대구#2T/L PT 초기점검","2017-07-06 09:30","2017-07-06 18:00","2017-07-06 09:30","2017-07-06 18:00","당일"]
[91,"대구경북","포항","신영일S/S 신영일T/L-#4 M.Tr 1차 CB (7700)","신영일S/S 신영일T/L-#4 M.Tr 1차 7700 CB 동작시험","신영일S/S 신영일T/L-#4 M.Tr 1차 7700 CB 동작시험","2017-07-11 14:00","2017-07-11 18:00","2017-07-11 14:00","2017-07-11 18:00","당일"]
[92,"대구경북","포항","신영일S/S TIE-#3 M.Tr 1차 CB (7500)","신영일S/S TIE-#3 M.Tr 1차 7500 CB 동작시험","신영일S/S TIE-#3 M.Tr 1차 7500 CB 동작시험","2017-07-11 09:00","2017-07-11 14:00","2017-07-11 09:00","2017-07-11 14:00","당일"]
[93,"대구경북","포항","신영일S/S #3 M.Tr A","신영일S/S RTU교체에 따른 SCADA 정비공사","신영일S/S RTU교체에 따른 SCADA 정비공사","2017-07-01 09:00","2017-07-01 14:00","2017-07-02 09:00","2017-07-02 14:00","당일"]
[94,"대구경북","포항","신영일S/S #4 M.Tr A","신영일S/S RTU교체에 따른 SCADA 정비공사","신영일S/S RTU교체에 따른 SCADA 정비공사","2017-07-01 14:00","2017-07-01 18:00","2017-07-02 14:00","2017-07-02 18:00","당일"]
[95,"대구경북","포항","신영일S/S 신영일-안동CC T/L CB (7671)","신영일S/S 신영일-안동CC T/L 7671 CB 동작시험","신영일S/S 신영일-안동CC T/L 7671 CB 동작시험","2017-07-10 09:00","2017-07-10 14:00","2017-07-10 09:00","2017-07-10 14:00","당일",null,null,null,201705080368]
[96,"대구경북","포항","신영일S/S 신영일-안동CC T/L-TIE CB (7600)","신영일S/S 신영일-안동CC T/L-TIE 7600 CB 동작시험","신영일S/S 신영일-안동CC T/L-TIE 7600 CB 동작시험","2017-07-10 14:00","2017-07-10 18:00","2017-07-10 14:00","2017-07-10 18:00","당일",null,null,null,201705080371]
[97,"대구경북","포항","신포항S/S 신포항-신월성NP#4T/L CB (7272)","신포항S/S 신포항-신월성NP#4T/L 7272 CB 동작시험","신포항S/S 신포항-신월성NP#4T/L 7272 CB 동작시험","2017-07-07 09:00","2017-07-07 14:00","2017-07-07 09:00","2017-07-07 14:00","당일",null,null,null,201705080355]
[98,"대구경북","포항","신포항S/S 신포항POSCO #2T/L CB (7372)","신포항S/S 신포항POSCO #2T/L 7372 CB 동작시험","신포항S/S 신포항POSCO #2T/L 7372 CB 동작시험","2017-07-06 14:00","2017-07-06 18:00","2017-07-06 14:00","2017-07-06 18:00","당일",null,null,null,201705080351]
[99,"대구경북","포항","신포항S/S 신포항-신월성NP#3T/L-TIE CB (7300)","신포항S/S 신포항-신월성NP#3T/L-TIE 7300 CB 동작시험","신포항S/S 신포항-신월성NP#3T/L-TIE 7300 CB 동작시험","2017-07-06 09:00","2017-07-06 14:00","2017-07-06 09:00","2017-07-06 14:00","당일",null,null,null,201705080348]
[100,"대구경북","포항","신포항S/S 신포항-신월성NP#3T/L CB (7371)","신포항S/S 신포항-신월성NP#3T/L 7371 CB 동작시험","신포항S/S 신포항-신월성NP#3T/L 7371 CB 동작시험","2017-07-05 14:00","2017-07-05 18:00","2017-07-05 14:00","2017-07-05 18:00","당일",null,null,null,201705080347]
[101,"대구경북","포항","신포항S/S 신포항-신월성NP#2T/L CB (7472)","신포항S/S 신포항-신월성NP#2T/L 7472 CB 동작시험","신포항S/S 신포항-신월성NP#2T/L 7472 CB 동작시험","2017-07-05 09:00","2017-07-05 14:00","2017-07-05 09:00","2017-07-05 14:00","당일",null,null,null,201705080345]
[102,"대구경북","포항","신포항S/S 신포항POSCO #1T/L CB (7471)","신포항S/S 신포항POSCO #1T/L 7471 CB 동작시험","신포항S/S 신포항POSCO #1T/L 7471 CB 동작시험","2017-07-04 14:00","2017-07-04 18:00","2017-07-04 14:00","2017-07-04 18:00","당일",null,null,null,201705080341]
[103,"대구경북","포항","신포항S/S 신월성NP#2T/L-TIE CB (7400)","신포항S/S 신월성NP#2T/L-TIE 7400 CB 동작시험","신포항S/S 신월성NP#2T/L-TIE 7400 CB 동작시험","2017-07-04 09:00","2017-07-04 14:00","2017-07-04 09:00","2017-07-04 14:00","당일",null,null,null,201705080337]
[104,"대구경북","포항","신포항S/S 신포항-신월성NP#1T/L CB (7572)","신포항S/S 신포항-신월성NP#1T/L 7572 CB 동작시험","신포항S/S 신포항-신월성NP#1T/L 7572 CB 동작시험","2017-07-07 14:00","2017-07-07 18:00","2017-07-07 14:00","2017-07-07 18:00","당일",null,null,null,201705080356]
[105,"부산울산","동부산","고리2N/P 345kV #72 BUS","고리NP S/Y 7D01DS 가스누기 보수 시험가압","고리NP S/Y 7D01DS 가스누기 보수 시험가압(#72BUS + 신고리고리NP#2T/L)","2017-07-04 10:00","2017-07-04 11:00","2017-07-04 17:00","2017-07-04 18:00","당일",null,null,null,201705110261]
[106,"부산울산","동부산","고리N/P 신고리#3,4 SAT-고리#3 SUT B CB (7D00)","고리NP S/Y 7D01DS 가스누기 보수","고리NP S/Y 7D01DS 가스누기 보수(7D71, 7D00 동시휴전 필요)","2017-07-03 09:00","2017-07-04 11:00","2017-07-03 09:00","2017-07-04 18:00","연속",null,null,null,201705110247]
[107,"부산울산","동부산","고리N/P S/Y 신고리 #3, 4 SAT CB (7D71)","고리NP S/Y 7D01DS 가스누기 보수","고리NP S/Y 7D01DS 가스누기 보수(7D71, 7D00 동시휴전 필요)","2017-07-03 09:00","2017-07-04 11:00","2017-07-03 09:00","2017-07-04 18:00","연속",null,null,null,201705110243]
[108,"부산울산","동부산","신양산북부산#2 T/L","345kV 신양산-북부산T/L 38호 지장철탑이설공사","지장철탑이설, 구간 37~41호, 철탑설치 1기, 철거 1기(38호)","2017-07-03 08:00","2017-07-09 18:00","2017-07-03 08:00","2017-07-09 18:00","연속",null,null,null,201705040050]
[109,"부산울산","동부산","신양산북부산#1 T/L","345kV 신양산-북부산T/L 38호 지장철탑이설공사","지장철탑이설, 구간 37~41호, 철탑설치 1기, 철거 1기(38호)","2017-07-10 08:00","2017-07-16 18:00","2017-07-10 08:00","2017-07-16 18:00","연속",null,null,null,201705040054]
[110,"부산울산","북부산","북부산S/S #1 M.Tr A","345kV 북부산S/S 차단기용량대체공사","1. #1M.Tr LA 이설 및 7602 DS 철거(신 GIS 설치를 위한 공간 확보)","2017-07-10 09:00","2017-07-11 18:00","2017-07-10 09:00","2017-07-11 18:00","연속",null,null,null,201705110105]
[111,"부산울산","북부산","북부산S/S 서부산#3T/L-#4M.Tr 1차 CB(신) ((신)7800)","345kV 북부산S/S 차단기용량대체공사","1. #4M.Tr 인출변경(구 76BAY → 신 78BAY GIS) 2. PNL 이설 준공시험 3. 사용전검사","2017-07-02 09:00","2017-07-07 18:00","2017-07-02 09:00","2017-07-07 18:00","연속",null,null,null,201705110104]
[112,"부산울산","북부산","북부산S/S #4 M.Tr 1차 CB (7671)","345kV 북부산S/S 차단기용량대체공사","북부산S/S 신설GIS 설치공간을 확보(구. 7671 CB 철거)","2017-07-07 18:00","2017-12-31 18:00","2017-07-07 18:00","2017-12-31 18:00","연속",null,null,null,201705110111]
[113,"부산울산","북부산","신김해북부산#2 T/L","345kV 북부산-울산TP 등 4개T/L 전선접속개소 전선교체공사","345kV 신김해-북부산#2T/L 전선교체공사 No.10∼22호","2017-07-10 07:00","2017-07-15 18:00","2017-07-10 07:00","2017-07-15 18:00","연속",null,null,null,201705190092]
[114,"부산울산","북부산","신김해북부산#1 T/L","345kV 북부산-울산TP 등 4개T/L 전선접속개소 전선교체공사","345kV 신김해-북부산#1T/L 전선교체공사 No.10∼22호","2017-07-04 07:00","2017-07-09 18:00","2017-07-04 07:00","2017-07-09 18:00","연속",null,null,null,201705190089]
[115,"부산울산","북부산","북부산S/S #4M.Tr 1차 CB(신) ((신)7872)","345kV 북부산S/S 차단기용량대체공사","1. #4M.Tr 인출변경(구 76BAY → 신 78BAY GIS) 2. PNL 이설 준공시험 3. 사용전검사","2017-07-02 09:00","2017-07-07 18:00","2017-07-02 09:00","2017-07-07 18:00","연속",null,null,null,201705110103]
[116,"부산울산","북부산","북부산S/S #4 M.Tr 1차-#1 M.Tr 1차 CB (7600)","345kV 북부산S/S 차단기용량대체공사","북부산S/S 신설GIS 설치공간을 확보(구. 7600 CB 철거)","2017-07-07 18:00","2017-12-31 18:00","2017-07-07 18:00","2017-12-31 18:00","연속",null,null,null,201705110108]
[117,"부산울산","서부산","서부산북부산#1 T/L","#1 Sh.R용 차단기 7177 설치","#1 Sh.R용 차단기 7177 설치","2017-07-22 09:00","2017-07-25 18:00","2017-07-22 09:00","2017-07-25 18:00","연속",null,null,null,201705090007]
[118,"부산울산","울산","신울산신온산#1 T/L","2016~2017년 울산전력지사 송전정비 협력회사 총액공사","3호 폴리머 점퍼지지애자 교체","2017-07-05 08:00","2017-07-05 18:00","2017-07-05 08:00","2017-07-05 18:00","당일",null,null,null,201705100133]
[119,"부산울산","울산","신울산신온산#2 T/L","2016~2017년 울산전력지사 송전정비 협력회사 총액공사","14호 폴리머 점퍼지지애자 교체","2017-07-06 08:00","2017-07-06 18:00","2017-07-06 08:00","2017-07-06 18:00","당일",null,null,null,201705100135]
[120,"부산울산","울산","울주고리NP#1 T/L","유호제 T/L보호반 내부통신회로 개선","1. 유호제 T/L보호반 내부통신회로 개선 2. 고리NP S/Y 7B71 GIS 보통점검","2017-07-10 09:00","2017-07-10 18:00","2017-07-04 09:00","2017-07-04 18:00","당일",null,null,null,201705110234]
[121,"경남","진주","의령산청양수#2 T/L","345kV 의령-산청양수#2T/L 보호반 대체","345kV 의령-산청양수#2T/L 보호반 대체","2017-07-03 09:00","2017-07-21 18:00","2017-07-03 09:00","2017-07-21 18:00","연속",null,null,null,201705190014]
[122,"경남","진주","신남원의령#1 T/L","345kV 신남원-의령T/L 16기 안전이격 거리확보공사","안전이격 거리확보 전선교체(39~43, 129~136호)","2017-07-06 07:00","2017-07-15 20:00","2017-07-11 07:00","2017-07-20 20:00","연속",null,null,null,201703090136]
[123,"경남","통영","삼천포T/P 345kV #71 BUS","삼천포T/P 345kV #71BUS 가스누기 보수","삼천포T/P 345kV #71BUS 가스누기 보수","2017-07-08 09:30","2017-07-09 18:30","2017-07-08 09:30","2017-07-09 18:30","연속",null,null,null,201705190058]
[124,"경남","통영","신고성S/S #4M.Tr A","신고성S/S 345kV #4M.Tr 3차부싱 과열개소 보수","신고성S/S 345kV #4M.Tr 3차부싱(A,C상) 과열개소 보수","2017-07-08 09:30","2017-07-08 18:30","2017-07-08 09:30","2017-07-08 18:30","당일",null,null,null,201705190110]
[125,"경남","통영","신고성S/S 신고성-삼천포화력#2T/L CB (7D72)","신고성S/S 345kV 신고성-삼천포화력#2T/L CB(7D72)보통점검","신고성S/S 345kV 신고성-삼천포화력#2T/L(7D72)CB보통점검","2017-07-13 09:30","2017-07-13 18:30","2017-07-13 09:30","2017-07-13 18:30","당일",null,null,null,201705110281]
[126,"경남","통영","신고성S/S 신고성-삼천포화력#1T/L CB (7C72)","신고성S/S 345kV 신고성-삼천포화력#1T/L CB(7C72)보통점검","신고성S/S 345kV 신고성-삼천포화력#1T/L CB(7C72)보통점검","2017-07-05 09:30","2017-07-05 18:30","2017-07-05 09:30","2017-07-05 18:30","당일",null,null,null,201705110280]

{"sheet":"154송부","index":2,"n_rows":167,"n_cols":16,"rows_kept":167,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 7월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","쌍문S/S 154kV #2 BUS","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (쌍문S/S 양주쌍문#1T/L)","2017-07-11 10:00","2017-07-11 17:50","2017-07-11T10:00:00","2017-07-11T17:50:00","당일",null,null,null,201705100234]
[2,"서울","성동","쌍문S/S 154kV #1 BUS","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (쌍문S/S 양주쌍문#1T/L)","2017-07-10 09:20","2017-07-11 10:00","2017-07-10T09:20:00","2017-07-11T10:00:00","연속",null,null,null,201705100232]
[3,"서울","성동","양주쌍문#1 T/L","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (쌍문S/S 양주쌍문#1T/L)","2017-07-10 09:20","2017-07-11 17:50","2017-07-10T09:20:00","2017-07-11T17:50:00","연속",null,null,"신뢰도개선",201705100231]
[4,"서울","성동","왕십리S/S 154kV BUS TIE CB","17년 성동P/O 변전협력회사 총액공사","170kV GIS 보통점검 (왕십리S/S 154kV BUSTIE)","2017-07-12 10:00","2017-07-12 17:00","2017-07-12T10:00:00","2017-07-12T17:00:00","당일",null,null,null,201705170042]
[5,"서울","성동","성동왕십리 T/L","17년 성동P/O 변전협력회사 총액공사","170kV GIS 보통점검 (왕십리S/S 성동왕십리T/L)","2017-07-13 10:00","2017-07-13 17:00","2017-07-13T10:00:00","2017-07-13T17:00:00","당일",null,null,null,201705170043]
[6,"서울","성동","왕십리용두 T/L","17년 성동P/O 변전협력회사 총액공사","170kV GIS 보통점검 (왕십리S/S 왕십리용두T/L)","2017-07-03 10:00","2017-07-03 17:00","2017-07-03T10:00:00","2017-07-03T17:00:00","당일",null,null,null,201705120200]
[7,"서울","중부","양주은평#1 T/L","2017년 중부PO 170kV GIS 정밀점검공사","양주은평#1T/L(617) GIS 정밀점검","2017-07-03 08:00","2017-07-05 18:00","2017-07-03T08:00:00","2017-07-05T18:00:00","연속",null,null,null,201704130077]
[8,"서울","중부","양주은평#2 T/L","2017년 중부PO 170kV GIS 정밀점검공사","양주은평#2T/L(627) GIS 정밀점검","2017-07-06 08:00","2017-07-08 18:00","2017-07-06T08:00:00","2017-07-08T18:00:00","연속",null,null,null,201704130079]
[9,"남서울","강남","강남선릉#2 T/L","선릉S/S 170kV GIS 정밀점검 - 변전전문","선릉S/S 강남-선릉#2T/L GIS 정밀점검","2017-07-06 10:00","2017-07-08 18:00","2017-07-06T10:00:00","2017-07-08T18:00:00","연속",null,null,null,201705170100]
[10,"남서울","강남","강남선릉#1 T/L","선릉S/S 170kV GIS 정밀점검 - 변전전문","선릉S/S 강남-선릉#1T/L GIS 정밀점검","2017-07-03 10:00","2017-07-05 18:00","2017-07-03T10:00:00","2017-07-05T18:00:00","연속",null,null,null,201705170099]
[11,"남서울","영등포","가양S/S 154kV #2 BUS","가양S/S 170kV GIS 교체공사(안천T/L)","가양S/S 170kV GIS 철거 및 설치 - #2BUS DS 철거 및 충전분 마감처리","2017-07-10 09:00","2017-07-11 14:00","2017-07-10T09:00:00","2017-07-11T14:00:00","연속",null,null,null,201705290129]
[12,"남서울","영등포","가양S/S 154kV #2 BUS","가양S/S 170kV GIS 교체공사(안천T/L)","가양S/S 170kV GIS 철거 및 설치 - #2BUS DS 및 GIB 설치/시험가압","2017-07-14 14:00","2017-07-18 18:00","2017-07-14T14:00:00","2017-07-18T18:00:00","연속",null,null,null,201705290149]
[13,"남서울","영등포","가양S/S 154kV #1 BUS","가양S/S 170kV GIS 교체공사(안천T/L)","가양S/S 170kV GIS 철거 및 설치 - #1BUS DS 및 GIB 철거/설치/시험가압","2017-07-11 14:00","2017-07-14 14:00","2017-07-11T14:00:00","2017-07-14T14:00:00","연속",null,null,null,201705290146]
[14,"남서울","영등포","영서S/S 154kV #60 BUS","영서S/S 154kV #60BUS 옥외철구 GIS화 공사","영서S/S 154kV #60BUS 옥외철구 GIS화 공사","2017-07-01 09:00","2017-07-07 18:00","2017-07-01T09:00:00","2017-07-07T18:00:00","연속",null,null,null,201705190118]
[15,"인천","시흥","신시흥북시화#2 T/L","북시화 170kV 장기사용 GIS 대체(1차)","북시화 170kV 장기사용 BUS-TIE GIS 대체","2017-07-01 10:00","2017-07-02 18:00","취소","취소","연속",null,null,null,201705180064]
[16,"인천","시흥","소래S/S 154kV #2 BUS","소래S/S #3M.Tr 1차 GIS 정밀점검","소래S/S #3M.Tr 1차 GIS 정밀점검","2017-07-05 16:00","2017-07-05 18:00","2017-07-05T16:00:00","2017-07-05T18:00:00","연속",null,null,null,201705160151]
[17,"인천","시흥","신시흥오봉 T/L","오봉S/S 신시흥오봉T/L GIS 정밀점검","오봉S/S 신시흥오봉T/L GIS 정밀점검","2017-07-01 08:00","2017-07-02 18:00","2017-07-01T08:00:00","2017-07-02T18:00:00","연속",null,null,null,201705150197]
[18,"인천","시흥","오봉S/S 154kV #2 BUS","오봉S/S 신시흥오봉T/L GIS 정밀점검","오봉S/S 신시흥오봉T/L GIS 정밀점검","2017-07-02 16:00","2017-07-02 18:00","2017-07-02T16:00:00","2017-07-02T18:00:00","연속",null,null,null,201705150195]
[19,"인천","시흥","오봉S/S 154kV #2 BUS","오봉S/S 도림오봉T/L GIS 정밀점검","오봉S/S 도림오봉T/L GIS 정밀점검","2017-07-09 16:00","2017-07-09 18:00","2017-07-09T16:00:00","2017-07-09T18:00:00","연속",null,null,null,201705150199]
[20,"인천","시흥","도림오봉 T/L","오봉S/S 도림오봉T/L GIS 정밀점검","오봉S/S 도림오봉T/L GIS 정밀점검","2017-07-08 08:00","2017-07-09 18:00","2017-07-08T08:00:00","2017-07-09T18:00:00","연속",null,null,null,201705150202]
[21,"인천","인천","남인천학익#1 T/L","154kV 남인천-학익 #1T/L SVL 교체공사","신형 SVL 교체공사","2017-07-24 09:00","2017-07-24 18:00","2017-07-24T09:00:00","2017-07-24T18:00:00","연속",null,null,null,201705120027]
[22,"인천","인천","송현S/S 154kV #1 BUS","신현S/S 170kV GIS 대체공사(무부하가압)","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2,BUSTIE GIS 대체 - 기타 부대공사 1식","2017-07-15 10:00","2017-07-16 10:00","취소","취소","연속",null,null,null,201705150005]
[23,"인천","인천","송현S/S 154kV #1 BUS","신현S/S 170kV GIS 대체공사(무부하가압)","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2,BUSTIE GIS 대체 - 기타 부대공사 1식","2017-07-03 10:00","2017-07-04 10:00","취소","취소","연속",null,null,null,201705150006]
[24,"인천","인천","신가좌인천#3 T/L","154kV 신가좌-인천#3T/L SVL 교체공사","노후 SVL 교체공사","2017-07-18 09:00","2017-07-21 18:00","2017-07-18T09:00:00","2017-07-21T18:00:00","연속",null,null,null,201705160165]
[25,"인천","인천","신현S/S 154kV #1 BUS","신현S/S 170kV GIS 대체공사(가압전시험)","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2,BUSTIE GIS 대체 - 기타 부대공사 1식","2017-07-17 08:00","2017-07-17 18:00","취소","취소","연속",null,null,null,201705150008]
[26,"인천","인천","신현송현#1 T/L","신현S/S 170kV GIS 대체공사(무부하가압)","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2,BUSTIE GIS 대체 - 기타 부대공사 1식","2017-07-15 10:00","2017-07-16 10:00","취소","취소","연속",null,null,null,201705150004]
[27,"인천","인천","신현송현#1 T/L","신현S/S 170kV GIS 대체공사(무부하가압)","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2,BUSTIE GIS 대체 - 기타 부대공사 1식","2017-07-03 10:00","2017-07-04 10:00","취소","취소","연속",null,null,null,201705180044]
[28,"인천","인천","신현S/S 154kV #2 BUS","신현S/S 170kV GIS 대체공사","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2,BUSTIE GIS 대체 - 기타 부대공사 1식","2017-07-04 08:00","2017-07-16 18:00","취소","취소","연속",null,null,null,201705180043]
[29,"인천","인천","학익연수#1 T/L","154kV 학익-연수 #1T/L SVL 교체공사","신형 SVL 교체공사","2017-07-25 09:00","2017-07-25 11:00","2017-07-25T09:00:00","2017-07-25T11:00:00","연속",null,null,null,201705120029]
[30,"인천","인천","학익연수#2 T/L","154kV 학익-연수 #2T/L SVL 교체공사 및 절연유 시료채취","신형 SVL 교체공사 및 절연유 시료채취","2017-07-25 11:30","2017-07-25 18:00","2017-07-25T11:30:00","2017-07-25T18:00:00","연속",null,null,null,201705120030]
[31,"경기북부","구리","덕소별내#1 T/L","154kV 덕소-별내#1T/L 피뢰기 설치공사","ㅇ 피뢰기 설치공사 - 대상 : 154kV 덕소-별내#1T/L No.1,3,4,5,9,10,19.1,25,26호","2017-07-08 08:00","2017-07-09 18:00","2017-07-08T08:00:00","2017-07-09T18:00:00","연속",null,null,null,201705110065]
[32,"경기북부","구리","미금덕소#2 T/L","154kV 미금-덕소#1T/L 피뢰기 설치공사","ㅇ 피뢰기 설치공사 - 대상 : 154kV 미금-덕소#1T/L No.1~15호","2017-07-05 08:00","2017-07-07 18:00","2017-07-05T08:00:00","2017-07-07T18:00:00","연속",null,null,null,201705110063]
[33,"경기북부","구리","별내도봉 T/L","154kV 별내-도봉T/L 피뢰기 설치공사","ㅇ 피뢰기 설치공사 - 대상 : 154kV 별내-도봉T/L No.1호","2017-07-07 09:00","2017-07-07 18:00","2017-07-07T09:00:00","2017-07-07T18:00:00","당일",null,null,null,201705110062]
[34,"경기북부","직할","금오상계#1 T/L","'16-'17년 직할 가공송전정비 협력회사 총액공사","154kV 용현-도봉#2T/L 피뢰기설치공사(병가선로 휴전) - No.7.18.31~33,35~36호(7기) - 용현도봉#2, 금오상계#1T/L 초기점검 병행","2017-07-03 08:00","2017-07-04 18:00","취소","취소","연속",null,null,null,201705120169]
[35,"경기북부","직할","금오상계#2 T/L","2017년 직할 가공송전 순시점검 위탁공사","154kV 용현-도봉#1T/L, 금오상계#2T/L 초기점검 - No1~7호 7기 신설분","2017-07-05 08:00","2017-07-06 18:00","취소","취소","연속",null,null,null,201705120175]
[36,"경기북부","직할","녹양백석#2 T/L","154kV 남면, 백석S/S SW 증설공사","○ 백석S/S 170kV GIS 2CCT 설치 ○ 기타 부대공사 1식","2017-07-03 10:00","2017-07-07 10:00","2017-07-03T10:00:00","2017-07-07T10:00:00","연속",null,null,null,201705120122]
[37,"경기북부","직할","녹양백석#1 T/L","154kV 남면, 백석S/S SW 증설공사","○ 백석S/S 170kV GIS 2CCT 설치 ○ 기타 부대공사 1식","2017-07-01 10:00","2017-07-02 10:00","2017-07-01T10:00:00","2017-07-02T10:00:00","연속",null,null,null,201705120121]
[38,"경기북부","파주","양주고양#2 T/L","154kV 양주-고양#2T/L 접속개소 전선교체공사","154kV 양주-고양#2T/L No.9-10 등 7개소","2017-07-09 07:00","2017-07-13 18:00","2017-07-09T07:00:00","2017-07-13T18:00:00","연속",null,null,null,201705100269]
[39,"경기북부","파주","양주고양#1 T/L","154kV 양주-고양#1T/L 접속개소 전선교체공사","154kV 양주-고양#1T/L No.9-10 등 5개소","2017-07-05 07:00","2017-07-08 18:00","2017-07-05T07:00:00","2017-07-08T18:00:00","연속",null,null,null,201705100268]
[40,"경기북부","파주","양주금촌#2 T/L","154kV 양주-금촌#2T/L 접속개소 전선교체공사 관련안전조치","154kV 양주-고양#2T/L No.9-10 등 3개소 전선교체공사 관련 안전조치 (양주-고양#2, 양주-금촌#2 4회선 병가구간)","2017-07-10 07:00","2017-07-13 18:00","2017-07-10T07:00:00","2017-07-13T18:00:00","연속",null,null,null,201705100271]
[41,"경기북부","파주","양주금촌#1 T/L","154kV 양주-금촌#1T/L 접속개소 전선교체공사 관련안전조치","154kV 양주-고양#1T/L No.9-10 등 3개소 전선교체공사 관련 안전조치 (양주-고양#1, 양주-금촌#1 4회선 병가구간)","2017-07-05 07:00","2017-07-07 18:00","2017-07-05T07:00:00","2017-07-07T18:00:00","연속",null,null,null,201705100270]
[42,"경기북부","파주","지도능곡#2 T/L","17년 파주전력지사 170kV GIS 정밀점검공사","능곡S/S 지도-능곡#2T/L GIS 정밀점검","2017-07-03 08:00","2017-07-05 18:00","2017-07-03T08:00:00","2017-07-05T18:00:00","연속",null,null,null,201705160229]
[43,"경기북부","파주","문산월롱#2 T/L","154kV 문산-평화 등 2개T/L 지장송전선로 이설공사","문산천 문산지구 하천정비 지장송전선로 이설공사","2017-07-02 08:00","2017-07-06 18:00","취소","취소","연속",null,null,null,201704070061]
[44,"경기북부","파주","신덕은원흥#2 T/L","154kV 신덕은-원흥#2T/L 접속개소 전선교체공사 안전조치","154kV 양주-고양#1,2T/L 접속개소 전선교체공사 관련 안전조치 (154kV 신덕은-원흥#2, 154kV 양주-고양#1,2T/L 4회선 병가구간)","2017-07-08 07:00","2017-07-09 18:00","2017-07-08T07:00:00","2017-07-09T18:00:00","연속",null,null,null,201705100272]
[45,"경기북부","파주","신덕은문산#2 T/L","154kV 문산-평화 등 2개T/L 지장송전선로 이설공사","문산천 문산지구 하천정비 지장송전선로 이설공사(병가선로)","2017-07-02 08:00","2017-07-06 18:00","취소","취소","연속",null,null,null,201704070063]
[46,"경기","군포","서서울서수원#1 T/L","서서울S/S 154kV 취약설비 GIS화 공사(서수원#1)","서서울S/S 154kV 취약설비 GIS화 공사(서수원#1) - T-Bus DS철거, 기초파쇄, 리드 연결","2017-07-08 09:00","2017-07-08 18:00","2017-07-08T09:00:00","2017-07-08T18:00:00","당일",null,null,null,201703140160]
[47,"경기","군포","서서울서수원#2 T/L","서서울S/S 154kV 취약설비 GIS화 공사(서수원#2)","서서울S/S 154kV 취약설비 GIS화 공사(서수원#2) - T-Bus DS철거, 기초파쇄, 리드 연결","2017-07-09 09:00","2017-07-09 18:00","2017-07-09T09:00:00","2017-07-09T18:00:00","당일",null,null,null,201703140159]
[48,"경기","군포","서서울산본#1 T/L","서서울S/S 154kV 취약설비 GIS화 공사(산본#1)","서서울S/S 154kV 취약설비 GIS화 공사(산본#1) - T-Bus DS철거, 기초파쇄, 리드 연결 - 가공송전선로 정밀점검 : 1~19호 (송전병행)","2017-07-15 09:00","2017-07-15 18:00","2017-07-15T09:00:00","2017-07-15T18:00:00","당일",null,null,null,201703140165]
[49,"경기","군포","서서울산본#2 T/L","서서울S/S 154kV 취약설비 GIS화 공사(산본#2)","서서울S/S 154kV 취약설비 GIS화 공사(산본#2) - T-Bus DS철거, 기초파쇄, 리드 연결 - 가공송전선로 정밀점검 : 1~19호 (송전병행)","2017-07-16 09:00","2017-07-16 18:00","2017-07-16T09:00:00","2017-07-16T18:00:00","당일",null,null,null,201703140163]
[50,"경기","군포","서서울율전#1 T/L","서서울S/S 154kV 취약설비 GIS화 공사(율전#1)","서서울S/S 154kV 취약설비 GIS화 공사(율전#1) - T-Bus DS철거, 기초파쇄, 리드 연결","2017-07-03 09:00","2017-07-03 18:00","2017-07-03T09:00:00","2017-07-03T18:00:00","당일",null,null,null,201703140157]
[51,"경기","군포","서서울율전#2 T/L","서서울S/S 154kV 취약설비 GIS화 공사(율전#2)","서서울S/S 154kV 취약설비 GIS화 공사(율전#2) - T-Bus DS철거, 기초파쇄, 리드 연결","2017-07-04 09:00","2017-07-04 18:00","2017-07-04T09:00:00","2017-07-04T18:00:00","당일",null,null,null,201703140156]
[52,"경기","군포","산본안양#1 T/L","154kV 안양S/S 옥내화공사","산본-안양T/L관로공사를 위해 기설설비 철거를 위해 활선근접공사라 반드시 휴전이 필요함","2017-07-11 09:00","2017-07-12 18:00","2017-07-11T09:00:00","2017-07-12T18:00:00","연속",null,null,null,201705110175]
[53,"경기","군포","산본안양#1 T/L","154kV 안양S/S 옥내화공사","산본-안양T/L관로공사를 위해 기설설비 철거를 위해 활선근접공사라 반드시 휴전이 필요함","2017-07-04 09:00","2017-07-05 18:00","2017-07-04T09:00:00","2017-07-05T18:00:00","연속",null,null,null,201705110173]
[54,"경기","군포","산본안양#1 T/L","154kV 안양S/S 옥내화공사","산본-안양#1T/L 피뢰기(LA, 144kV) EBA기초위치로 이설","2017-07-20 09:00","2017-07-21 18:00","2017-07-20T09:00:00","2017-07-21T18:00:00","연속",null,null,null,201705100280]
[55,"경기","군포","산본안양#2 T/L","154kV 안양S/S 옥내화공사","산본-안양#2T/L 피뢰기(LA, 144kV) EBA기초위치로 이설","2017-07-24 09:00","2017-07-25 18:00","2017-07-24T09:00:00","2017-07-25T18:00:00","연속",null,null,null,201705100281]
[56,"경기","동부","산성성현#2 T/L","17년 동부 주기도래 점검","산성,성현S/S 성현-산성#2T/L GIS(보통)","2017-07-11 09:00","2017-07-11 18:00","2017-07-11T09:00:00","2017-07-11T18:00:00","당일",null,null,null,201705160228]
[57,"경기","동부","산성성현#1 T/L","17년 동부 주기도래 점검","산성,성현S/S 성현-산성#1T/L GIS(보통)","2017-07-10 09:00","2017-07-10 18:00","2017-07-10T09:00:00","2017-07-10T18:00:00","당일",null,null,null,201705160227]
[58,"경기","동부","초월성현#2 T/L","154kV 초월-성현T/L 6-7호간 항공장애표시구 설치공사","-항공장애표시구 설치(6-7호)","2017-07-05 08:00","2017-07-05 18:00","2017-07-05T08:00:00","2017-07-05T18:00:00","당일",null,null,null,201705190141]
[59,"경기","동부","초월성현#1 T/L","`16-17년 송전협력회사 총액공사","- 항공장애표시구 설치공사(6-7호 등)","2017-07-04 08:00","2017-07-04 18:00","2017-07-04T08:00:00","2017-07-04T18:00:00","당일",null,null,null,201705190137]
[60,"경기","성남","북동탄동탄열병합#2 T/L","17년 성남변전협력회사 총액공사","GIS 초기점검","2017-07-04 10:00","2017-07-04 18:00","2017-07-04T10:00:00","2017-07-04T18:00:00","당일",null,null,null,201705150051]
[61,"경기","성남","삼미동탄열병합#3 T/L","17년 성남변전협력회사 총액공사","GIS 초기점검","2017-07-07 10:00","2017-07-07 18:00","2017-07-07T10:00:00","2017-07-07T18:00:00","당일",null,null,null,201705150057]
[62,"경기","성남","삼미동탄열병합#2 T/L","17년 성남변전협력회사 총액공사","GIS 초기점검","2017-07-06 10:00","2017-07-06 18:00","2017-07-06T10:00:00","2017-07-06T18:00:00","당일",null,null,null,201705150055]
[63,"경기","성남","삼미동탄열병합#1 T/L","17년 성남변전협력회사 총액공사","GIS 초기점검","2017-07-05 10:00","2017-07-05 18:00","2017-07-05T10:00:00","2017-07-05T18:00:00","당일",null,null,null,201705150054]
[64,"경기","성남","북동탄동탄열병합#1 T/L","17년 성남변전협력회사 총액공사","GIS 초기점검","2017-07-03 10:00","2017-07-03 18:00","2017-07-03T10:00:00","2017-07-03T18:00:00","당일",null,null,null,201705150050]
[65,"경기","성남","서안성안성#2 T/L","154kV 서안성-안성T/L 전선접속개소 교체공사","154kV 서안성-안성T/L No.1~4, 7~8. 9~11 전선접속개소 교체공사","2017-07-08 08:00","2017-07-12 18:00","2017-07-08T08:00:00","2017-07-12T18:00:00","연속",null,null,null,201705160295]
[66,"경기","성남","서안성안성#1 T/L","154kV 서안성-안성T/L 전선접속개소 교체공사","154kV 서안성-안성T/L No.1~4, 7~8. 9~11 전선접속개소 교체공사","2017-07-03 08:00","2017-07-07 18:00","2017-07-03T08:00:00","2017-07-07T18:00:00","연속",null,null,null,201705160294]
[67,"경기","성남","신성남서판교#2 T/L","17년 성남변전협력회사 총액공사","#2DS 전자변 교체 및 개폐타임 측정","2017-07-14 10:00","2017-07-14 18:00","2017-07-14T10:00:00","2017-07-14T18:00:00","당일",null,null,null,201705150066]
[68,"경기","성남","신수원S/S 154kV #3BUS-TIE(6300) GIS","17년 성남변전협력회사 총액공사","GIS 보통점검","2017-07-10 09:00","2017-07-10 18:00","2017-07-10T09:00:00","2017-07-10T18:00:00","당일",null,null,null,201705150071]
[69,"경기","직할","화성S/S 154kV #66 BUS","화성S/S 345kV #2M.Tr 2차 GIS 정밀점검","화성S/S 345kV #2M.Tr 2차 GIS 정밀점검","2017-07-06 14:00","2017-07-07 18:00","2017-07-06T14:00:00","2017-07-07T18:00:00","연속",null,null,null,201705150103]
[70,"경기","직할","화성S/S 154kV #61 BUS","화성S/S 345kV #2M.Tr 2차 GIS 정밀점검","화성S/S 345kV #2M.Tr 2차 GIS 정밀점검","2017-07-05 09:00","2017-07-06 14:00","2017-07-05T09:00:00","2017-07-06T14:00:00","연속",null,null,null,201705150102]
[71,"경기","직할","화성S/S 154kV #67 BUS","화성S/S 154kV #68Sh.C GIS 정밀점검","화성S/S 154kV #68Sh.C GIS 정밀점검","2017-07-03 14:00","2017-07-04 18:00","2017-07-03T14:00:00","2017-07-04T18:00:00","연속",null,null,null,201705150101]
[72,"경기","직할","화성S/S 154kV #62 BUS","화성S/S 154kV #68Sh.C GIS 정밀점검","화성S/S 154kV #68Sh.C GIS 정밀점검","2017-07-02 09:00","2017-07-03 14:00","2017-07-02T09:00:00","2017-07-03T14:00:00","연속",null,null,null,201705150100]
[73,"경기","직할","화성S/S 154kV #66 BUS","화성S/S 154kV #63M.Tr 1차 GIS 정밀점검","화성S/S 154kV #63M.Tr 1차 GIS 정밀점검","2017-07-13 14:00","2017-07-14 18:00","2017-07-13T14:00:00","2017-07-14T18:00:00","연속",null,null,null,201705150107]
[74,"경기","직할","화성S/S 154kV #61 BUS","화성S/S 154kV #63M.Tr 1차 GIS 정밀점검","화성S/S 154kV #63M.Tr 1차 GIS 정밀점검","2017-07-12 09:00","2017-07-13 14:00","2017-07-12T09:00:00","2017-07-13T14:00:00","연속",null,null,null,201705150106]
[75,"경기","평택","서운안성#2 T/L","154kV 서안성-안성T/L 전선교체시 안전이격확보","154kV 서안성-안성T/L No.1~4, 7~8. 9~11 전선접속개소 교체공사","2017-07-08 08:00","2017-07-10 18:00","2017-07-08T08:00:00","2017-07-10T18:00:00","연속",null,null,"신뢰도개선",201705160301]
[76,"경기","평택","서운안성#1 T/L","154kV 서안성-안성T/L 전선교체시 안전이격확보","154kV 서안성-안성T/L No.1~4, 7~8. 9~11 전선접속개소 교체공사","2017-07-03 08:00","2017-07-05 18:00","2017-07-03T08:00:00","2017-07-05T18:00:00","연속",null,null,"신뢰도개선",201705160299]
[77,"경기","평택","원정평택T/P#2 T/L","원정S/S 원정-평택T/P #2T/L GIS 보통점검","원정S/S 원정-평택T/P #2T/L GIS 보통점검 / LA, CVT 대체","2017-07-02 10:00","2017-07-02 18:00","2017-07-02T10:00:00","2017-07-02T18:00:00","당일",null,null,null,201705120215]
[78,"경기","평택","원정평택T/P#1 T/L","원정S/S 원정-평택T/P #1T/L GIS 보통점검","원정S/S 원정-평택T/P #1T/L GIS 보통점검 / LA, CVT 대체","2017-07-01 10:00","2017-07-01 18:00","2017-07-01T10:00:00","2017-07-01T18:00:00","당일",null,null,null,201705120214]
[79,"경기","평택","청북S/S 만호-청북T/L GIS","청북S/S 154kV #1BUSTIE GIS 정밀점검공사(무부하가압선로)","청북S/S 154kV #1BUSTIE GIS 정밀점검공사(무부하가압선로)","2017-07-15 08:00","2017-07-16 18:00","2017-07-15T08:00:00","2017-07-16T18:00:00","연속",null,null,null,201705120205]
[80,"경기","평택","청북S/S 청북-평택#1T/L GIS","청북S/S 청북-평택#1T/L GIS 정밀점검공사","청북S/S 청북-평택#1T/L GIS 정밀점검공사","2017-07-08 09:00","2017-07-10 18:00","2017-07-08T09:00:00","2017-07-10T18:00:00","연속",null,null,null,201705120197]
[81,"강원","강릉","속초간성#2 T/L","2017년 간성S/S 170kV 장기사용 GIS 대체공사","속초간성#2TL GIS 대체","2017-07-24 08:30","2017-08-24 18:00","2017-07-24 08:30","2017-08-24 18:00","연속",null,null,null,201705160031]
[82,"강원","강릉","속초간성#1 T/L","2017년 간성S/S 170kV 장기사용 GIS 대체공사","GIS 대체 안전이격 확보","2017-07-26 08:30","2017-07-30 17:00","2017-07-26 08:30","2017-07-30 17:00","매일",null,null,null,201705160042]
[83,"강원","직할","남춘천춘천열병합#2 T/L","춘천집단에너지 건설공사 송전선로 이도조정 공사","○ 이도조정 : No.15호","2017-07-04 09:00","2017-07-05 18:00","2017-06-17 09:00","2017-06-18 18:00","연속",null,null,null,201705160046]
[84,"강원","직할","서홍천춘천열병합 T/L","춘천집단에너지 건설공사 송전선로 이도조정 공사","○ 이도조정 : No.15호","2017-07-04 09:00","2017-07-05 18:00","2017-06-17 09:00","2017-06-18 18:00","연속",null,null,null,201705160045]
[85,"강원","직할","남춘천춘천열병합#1 T/L","춘천집단에너지 건설공사 송전선로 이도조정 공사","○ 이도조정 : No.15호","2017-07-06 09:00","2017-07-07 18:00","2017-06-19 09:00","2017-06-19 18:00","연속",null,null,null,201705160051]
[86,"강원","직할","청평PP춘천열병합 T/L","춘천집단에너지 건설공사 송전선로 이도조정 공사","○ 이도조정 : No.15호","2017-07-06 09:00","2017-07-07 18:00","2017-06-19 09:00","2017-06-19 18:00","연속",null,null,null,201705160049]
[87,"충북","직할","금왕남음성#1 T/L","금왕S/S 금왕남음성#1T/L LA 대체","- 170kV LA 대체","2017-07-04 10:00","2017-07-04 18:00","2017-07-04 10:00","2017-07-04 18:00","당일",null,null,null,201704110226]
[88,"충북","직할","점촌단양 T/L","단양S/S 점촌단양T/L LA 보통점검","170kV LA 보통점검","2017-07-09 13:00","2017-07-09 18:00","2017-07-09 13:00","2017-07-09 18:00","당일",null,null,null,201704240138]
[89,"충북","직할","문경단양 T/L","단양S/S 문경단양T/L LA 보통점검","-170kV LA 보통점검","2017-07-09 09:00","2017-07-09 13:00","2017-07-09 09:00","2017-07-09 13:00","당일",null,null,null,201704240137]
[90,"충북","직할","음성금왕#2 T/L","음성S/S 음성금왕#2T/L CVT 보통점검","- 154kV CVT 보통점검","2017-07-05 10:00","2017-07-05 18:00","2017-07-05 10:00","2017-07-05 18:00","당일",null,null,null,201704240126]
[91,"충북","청주","서청주사직#2 T/L","17년도 청주전력지사 170kV GIS 정밀점검공사","서청주S/S 서청주사직#2 T/LGIS 정밀점검","2017-07-01 09:30","2017-07-03 18:00","2017-07-01 09:30","2017-07-03 18:00","연속",null,null,null,201705080315]
[92,"충북","청주","옥천보은 T/L","장기사용 GIS 대체공사 직결작업 관련 안전 작업 구간 확보","장기사용 GIS 대체공사 직결작업 관련 안전 작업 구간 확보","2017-07-01 08:00","2017-07-01 12:00","2017-07-01 08:00","2017-07-01 12:00","당일",null,null,null,201705260085]
[93,"대전충남","서산","신당진S/S 154kV #1 BUS TIE CB","'17년 변전협력회사 총액공사","신당진S/S 154kV #1BUS-TIE GIS(6100) 보통점검","2017-07-12 10:00","2017-07-12 18:00","2017-07-12T10:00:00","2017-07-12T18:00:00","당일",null,null,null,201705150293]
[94,"대전충남","아산","한샘둔포#2 T/L","한샘S/S 154kV 한샘-둔포#2T/L 보호배전반 교체","○ 154kV 한샘-둔포#2T/L 보호배전반 교체","2017-07-03 09:00","2017-07-06 18:00","취소","취소","연속",null,null,null,201705120198]
[95,"대전충남","청양","옥산서천화력#2 T/L","서천화력 임시전담설비 구축공사","-보호반이설 및 GIS 감시/제어 케이블 이설","2017-07-10 09:00","2017-07-14 18:00","2017-07-10T09:00:00","2017-07-14T18:00:00","연속",null,null,null,201705120210]
[96,"대전충남","청양","대천서천화력#1 T/L","서천화력 임시전담설비 구축공사","-보호반이설 및 GIS 감시/제어 케이블 이설","2017-07-17 09:00","2017-07-21 18:00","2017-07-17T09:00:00","2017-07-21T18:00:00","연속",null,null,null,201705120211]
[97,"대전충남","청양","서천T/P 154kV #1 BUS TIE CB","서천화력 S/Y 임시전담운영설비 구축공사","서천화력 폐지에 따른 S/Y 제어감시 이설(서천화력S/S) - 모선보호반 이설 (발전소 전자기기실-서천화력S/S 감시실)","2017-07-25 09:00","2017-07-28 18:00","2017-07-25T09:00:00","2017-07-28T18:00:00","연속",null,null,null,201705190033]
[98,"대전충남","청양","대천서천화력#2 T/L","서천화력 임시전담설비 구축공사","-보호반이설 및 GIS 감시/제어 케이블 이설","2017-07-24 09:00","2017-07-28 18:00","2017-07-24T09:00:00","2017-07-28T18:00:00","연속",null,null,null,201705120212]
[99,"대전충남","청양","옥산서천화력#1 T/L","서천화력 임시전담설비 구축공사","-보호반이설 및 GIS 감시/제어 케이블 이설","2017-07-03 09:00","2017-07-07 18:00","2017-07-03T09:00:00","2017-07-07T18:00:00","연속",null,null,null,201705120209]
[100,"전북","군산","동군산군산CC#1 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 2차 공정 - 군산-동군산#2T/L - 동군산-군산복합#1T/L - #1M.Tr 1차측","2017-07-04 08:00","2017-08-02 18:00","취소","취소","연속",null,null,null,201705080188]
[101,"전북","군산","동군산장항#1 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 2차 공정 - #1M.Tr 근접작업","2017-07-20 08:00","2017-07-22 18:00","2017-07-20 08:00","2017-07-22 18:00","연속",null,null,null,201705080195]
[102,"전북","군산","군산동군산#2 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 2차 공정 - 군산-동군산#2T/L - 동군산-군산복합#1T/L - #1M.Tr 1차측","2017-07-04 08:00","2017-08-02 18:00","취소","취소","연속",null,null,null,201705080186]
[103,"전북","군산","동군산장항#1 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 2차 공정 - #1M.Tr 근접작업으로 안전 이격거리 확보","2017-07-04 08:00","2017-07-06 19:00","2017-07-04 08:00","2017-07-06 19:00","연속",null,null,null,201705080191]
[104,"전북","군산","동군산장항#1 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 2차 공정 - #1BUS 시험가압","2017-07-19 08:00","2017-07-20 08:00","2017-07-19 08:00","2017-07-20 08:00","연속",null,null,null,201705080193]
[105,"전북","군산","팔봉영등#1 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 1차 공정 - 팔봉-영등#1T/L, BUS TIE 대체작업","2017-07-18 09:00","2017-08-10 18:00","취소","취소","연속",null,null,null,201705150244]
[106,"전북","김제","고창영광 T/L","김제P/O 154KV GIS 정밀점검","637 내부 정밀점검 시험가압","2017-07-22 13:00","2017-07-22 15:00","2017-07-22 13:00","2017-07-22 15:00","당일",null,null,null,201705160126]
[107,"전북","김제","고창영광 T/L","김제P/O 154KV GIS 정밀점검","637 내부 정밀점검 시험가압","2017-07-21 13:00","2017-07-21 15:00","2017-07-21 13:00","2017-07-21 15:00","당일",null,null,null,201705160124]
[108,"전북","김제","정주고창#2 T/L","154kV 정주-고창T/L 안전이격거리 확보공사","정주-고창#2T/L 철탑 이설 및 전력선 교체 철탑교체 : No.25,31,35호 전력선 교체 : No.24~27, 28~32, 34~37호","2017-07-23 07:00","2017-08-02 18:00","취소","취소","연속",null,null,null,201705180004]
[109,"전북","김제","정주고창#1 T/L","154KV 정주-고창T/L 안전이격 확보공사","정주-고창#1T/L 가선로 구성 No.24~26(25호 가철탑), 28~33, 34~37호","2017-07-20 07:00","2017-07-22 18:00","2017-07-22 07:00","2017-07-23 18:00","연속",null,null,null,201705180003]
[110,"전북","김제","고창영광 T/L","김제P/O 154KV GIS 정밀점검","647 내부 정밀점검 시험가압","2017-07-25 13:00","2017-07-25 15:00","2017-07-25 13:00","2017-07-25 15:00","당일",null,null,null,201705160138]
[111,"전북","김제","고창영광 T/L","김제P/O 154KV GIS 정밀점검","647 내부 정밀점검 시험가압","2017-07-26 13:00","2017-07-26 15:00","2017-07-26 13:00","2017-07-26 15:00","당일",null,null,null,201705160139]
[112,"전북","김제","고창영광 T/L","154KV 고창-영광T/L 점퍼지지애자 교체공사","정주-고창#2T/L No.84호 점퍼지지애자 교체공사시 안전거리 확보","2017-07-20 07:00","2017-07-20 18:00","2017-07-20 07:00","2017-07-20 18:00","당일",null,null,null,201705180125]
[113,"전북","김제","김제섬진강HP T/L","154kV 김제-섬전강T/L 피뢰기설치공사","공사명 : 154kV 김제-섬전강T/L 피뢰기설치공사 대상 : No.1~4 내영 : 송전선로용 피뢰기 설치","2017-07-11 07:00","2017-07-15 18:00","2017-07-12 07:00","2017-07-19 18:00","연속",null,null,null,201705110101]
[114,"전북","김제","신김제남전주#1 T/L","관내S/S 노후배전반 교체공사","양단 보호배전반 교체","2017-07-17 09:00","2017-07-20 18:00","취소","취소","연속",null,null,null,201705170157]
[115,"전북","김제","신김제남전주#2 T/L","관내S/S 노후배전반 교체공사","양단 보호배전반 교체","2017-07-11 09:00","2017-07-14 18:00","취소","취소","연속",null,null,null,201705170159]
[116,"전북","김제","신김제정공#2 T/L","관내S/S 노후배전반 교체공사","양단 보호배전반 교체","2017-07-24 09:00","2017-07-27 18:00","2017-07-24 09:00","2017-07-27 18:00","연속",null,null,null,201705170156]
[117,"전북","김제","담양김제 T/L","345kV 신김제-한빛#2T/L 190~205호간 전선접속개소 해소공사","345kV 신김제-한빛#2T/L 190~205호간 전선접속개소 해소공사","2017-07-11 07:00","2017-07-15 18:00","2017-07-24 07:00","2017-07-28 18:00","연속",null,null,null,201705290161]
[118,"광주전남","광주","신광주S/S 154kV #1 BUS TIE CB(신)","신광주S/S 154kV 61-66BUS 모선보호반 이설","- 154kV 61-66BUS 모선보호반 이설 - 보호용 Panel 시첨","2017-07-03 07:00","2017-07-07 18:00","2017-07-03 07:00","2017-07-07 18:00","연속",null,null,null,201703170067]
[119,"광주전남","광주","신광주S/S 154kV 60-61-0 GIS","17년 신광주S/S 취약설비 GIS화공사","60-65BUS 모선보호반이설","2017-07-03 07:00","2017-07-07 18:00","2017-07-03 07:00","2017-07-07 18:00","연속",null,null,null,201705220082]
[120,"광주전남","광주","신광주S/S 154kV #2 BUS TIE CB(신)","신광주S/S 154kV 61-66BUS 모선보호반 이설","-인출변경및 인출GIS연결 - 제어케이불 교체 - 옥외철구 및 내장모선 철거 - 보호용 Panel 시첨","2017-07-03 07:00","2017-07-07 18:00","2017-07-03 07:00","2017-07-07 18:00","연속",null,null,null,201703140392]
[121,"광주전남","광주","신광주S/S 154kV #65BUS PT GIS(신)","17년 신광주S/S 취약설비 GIS화공사","60-65BUS 모선보호반이설","2017-07-03 07:00","2017-07-07 18:00","2017-07-03 07:00","2017-07-07 18:00","연속",null,null,null,201705220083]
[122,"광주전남","광주","신광주S/S 154kV 65-66-0 GIS","17년 신광주S/S 취약설비 GIS화공사","60-65BUS 모선보호반이설","2017-07-03 07:00","2017-07-07 18:00","2017-07-03 07:00","2017-07-07 18:00","연속",null,null,null,201705220081]
[123,"광주전남","광주","신광주S/S 154kV #66BUS PT GIS(신)","17년 신광주S/S 취약설비 GIS화공사","60-65BUS 모선보호반이설","2017-07-03 07:00","2017-07-07 18:00","2017-07-03 07:00","2017-07-07 18:00","연속",null,null,null,201705220084]
[124,"광주전남","광주","신화순S/S #61 M.Tr(ESS) CB","신화순S/S #61 M.Tr(ESS)(변전협력회사공사)","#61 M.Tr, ESS용 S.Tr(3-2,4S.Tr), 154kV 및 23kV GIS 초기점검 ESS설비 연차점검","2017-07-03 09:00","2017-07-07 18:00","2017-07-03 09:00","2017-07-07 18:00","연속",null,null,null,201705040145]
[125,"광주전남","순천","순천율촌#1 T/L","154kV 순천-율촌#1T/L LA 대체(율촌)","17년 순천전력 변전협력 총액공사 - 154kV 순천-율촌#1T/L LA 대체(율촌)","2017-07-03 10:00","2017-07-03 18:00","2017-07-01 10:00","2017-07-01 18:00","당일",null,null,null,201705170181]
[126,"대구경북","구미","선산청리#2 T/L","선산S/S 154kV 옥외철구 GIS화 공사","GIS 기초 부지 확보 T-BUS 철거 및 CVT 이설","2017-07-07 09:00","2017-07-08 18:00","2017-07-01 08:00","2017-07-05 20:00","연속",null,null,null,201704280318]
[127,"대구경북","구미","선산청리#1 T/L","선산S/S 154kV 옥외철구 GIS화 공사","GIS 기초 부지 확보 T-BUS 철거 및 CVT 이설","2017-07-05 09:00","2017-07-06 18:00","2017-07-06 08:00","2017-07-10 20:00","연속",null,null,null,201704280317]
[128,"대구경북","달성","성서달성#2 T/L","EBA 자기애관 교체공사","자기애관을 폴리머 애관으로 교체","2017-07-08 08:00","2017-07-09 18:00","취소","취소","연속",null,null,null,201705080285]
[129,"대구경북","달성","성서달성#1 T/L","EBA 자기애관 교체공사","자기애관을 폴리머 애관으로 교체","2017-07-01 08:00","2017-07-02 18:00","취소","취소","연속",null,null,null,201705080284]
[130,"대구경북","안동","안동안동HP T/L","안동S/S 23kV 옥외철구 GIS화 공사","가. 23kV 옥외철구 설비 ⇒ 25.8kV 친환경개폐장치 대체 × 28Bay 나. 제어 및 전력케이블 철거·설치 × 1식 다. 철구 및 기기기초 철거·설치 × 1식 라. 접지 및 기타 부대작업 × 1식","2017-07-03 09:00","2017-07-05 18:00","2017-07-03 09:00","2017-07-05 18:00","연속",null,null,null,201704100532]
[131,"대구경북","직할","노변효목#1 T/L","PNL 대체","PNL 대체 GIS 보통점검","2017-07-03 09:30","2017-07-05 18:00","2017-07-24 09:30","2017-07-26 14:00","연속",null,null,null,201704280154]
[132,"대구경북","직할","노변효목#2 T/L","PNL 대체","PNL 대체 GIS 보통점검","2017-07-10 09:30","2017-07-12 18:00","2017-07-26 14:00","2017-07-28 18:00","연속",null,null,null,201704280155]
[133,"대구경북","칠곡","북대구S/S 154kV #61 BUS","2017년 칠곡전력지사 차단기 정밀점검공사","2017년 칠곡전력지사 차단기 정밀점검공사","2017-07-17 09:30","2017-07-18 14:00","취소","취소","연속",null,null,null,201705170149]
[134,"대구경북","포항","신포항상정#1 T/L","154kV 상정-양북T/L 건설공사","목적 : 포항 블루밸리산업단지 전력수요 대비 및 상정S/S 단일계통 해소 구간 : 기설 154kV 영일-양북T/L No.29,31~기설 154kV 상정S/S 개요 : 철탑 39기, 14.725km","2017-07-03 08:00","2017-07-12 18:00","취소","취소","연속",null,null,null,201704070220]
[135,"부산울산","동부산","명례고리NP T/L","명례S/S 170kV GIS 하자점검","명례S/S 170kV 637 GIS 하자점검","2017-07-07 09:30","2017-07-07 17:00","2017-07-07 09:30","2017-07-07 17:00","당일",null,null,null,201705110231]
[136,"부산울산","동부산","명례정관 T/L","명례S/S 170kV GIS 하자점검","1. 명례 170kV 647 GIS 하자점검 2. 정관 170kV 667 GIS 보통점검","2017-07-11 09:30","2017-07-11 17:00","2017-07-11 09:30","2017-07-11 17:00","당일",null,null,null,201705110229]
[137,"부산울산","동부산","신울산명례#1 T/L","명례S/S 170kV GIS 하자점검","명례S/S 170kV 617 GIS 하자점검","2017-07-03 09:30","2017-07-03 17:00","2017-07-03 09:30","2017-07-03 17:00","당일",null,null,null,201705110227]
[138,"부산울산","동부산","명례S/S 154KV #1 BUS TIE CB","명례S/S 170kV GIS 하자점검","명례S/S 170kV 6100 GIS 하자점검","2017-07-06 09:30","2017-07-06 17:00","2017-07-06 09:30","2017-07-06 17:00","당일",null,null,null,201705110230]
[139,"부산울산","동부산","신울산명례#2 T/L","명례S/S 170kV GIS 하자점검","명례S/S 170kV 627 GIS 하자점검","2017-07-10 09:30","2017-07-10 17:00","2017-07-10 09:30","2017-07-10 17:00","당일",null,null,null,201705110228]
[140,"부산울산","동부산","명례정관 T/L","154kV 정관S/S 정관에너지 계통연계공사","154kV 정관S/S 정관에너지 계통연계공사 : 정관S/S 정관에너지T/L GIS(687) ~ 부산정관에너지측 GIS 시험가압선로","2017-07-04 16:00","2017-07-05 16:00","2017-07-04 16:00","2017-07-05 16:00","연속",null,null,null,201705120110]
[141,"부산울산","동부산","수영정보#1 T/L","154kV 우동 등 3개S/S 지중케이블 선종교체공사","정보S/S EBG ~ S/J 구간 OF 1200 ---> XLPE 1200 교체","2017-07-03 09:00","2017-07-24 18:00","취소","취소","연속",null,null,null,201705120042]
[142,"부산울산","북부산","물금S/S 154KV #1 BUS TIE CB","154kV 물금분기T/L SW 증설공사(시험가압)","o 154kV GIS * 2CCT 설치 (#2BUS~C/H 시험가압)","2017-07-07 19:00","2017-07-08 18:00","2017-07-07 19:00","2017-07-08 18:00","당일",null,null,null,201705300017]
[143,"부산울산","북부산","호포물금 T/L","154kV 물금분기T/L SW 증설공사(시험가압)","o 154kV GIS * 2CCT 설치 (#2BUS,652,657,662,667 시험가압 선로)","2017-07-07 18:00","2017-07-07 19:00","2017-07-07 18:00","2017-07-07 19:00","당일",null,null,null,201705300016]
[144,"부산울산","서부산","서부산신평#2 T/L","154kV 서부산C/H 지장송전선로 이설공사","서부산C/H 1기 설치 및 철거 - 154kV 서부산-신평#1,2T/L 및 154kV YKT/L 이설","2017-07-02 06:00","2017-07-12 18:00","2017-07-02 06:00","2017-07-12 18:00","연속",null,null,null,201704050032]
[145,"부산울산","울산","동울산효문#2 T/L","154kV 동울산-효문#2T/L 송전선로용 피뢰기 설치공사","ㅁ 작업내용 : 송전용피뢰기 설치 ㅁ 수량 : 17기ㅁ 구간 : No.23~39","2017-07-13 07:00","2017-07-15 18:00","2017-07-13 07:00","2017-07-15 18:00","연속",null,null,null,201705080078]
[146,"부산울산","울산","방어진영남TP#1 T/L","154kV 방어진S/S 현중T/L GIS 대체공사","154kV 방어진S/S 현중T/L GIS 1CCT 대체 - 현대중공업 임시공급선로 설치/철거 및 GIS교체","2017-07-28 09:00","2017-07-28 18:00","2017-07-28 09:00","2017-07-28 18:00","당일",null,null,null,201705100138]
[147,"부산울산","울산","방어진S/S 154kV #1 BUS","154kV 방어진S/S 현중T/L GIS 대체공사","현대중공업T/L #1DS 철거 및 임시모선 설치","2017-07-29 09:00","2017-08-03 14:00","2017-07-29 09:00","2017-08-03 14:00","연속",null,null,null,201705100163]
[148,"부산울산","울산","방어진영남TP#2 T/L","154kV 방어진S/S 현중T/L GIS 대체공사","154kV 방어진S/S 현중T/L GIS 1CCT 대체 - 현대중공업 임시공급선로 설치철거 (안전이격거리확보)","2017-07-28 09:00","2017-07-28 18:00","2017-07-28 09:00","2017-07-28 18:00","당일",null,null,null,201705100142]
[149,"부산울산","울산","신울산S/S 154kV #63 BUS","2016-17년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV 6N1DS 불량조치작업","2017-07-11 08:00","2017-07-11 14:00","2017-07-11 08:00","2017-07-11 14:00","당일",null,null,null,201705180013]
[150,"부산울산","울산","신울산울산#2 T/L","2016-17년도 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV 6N7 ILC PNL 대체 및 GIS 보통점검 울산S/S 154kV 647 GIS 보통점검","2017-07-11 08:00","2017-07-12 18:00","2017-07-11 08:00","2017-07-12 18:00","연속",null,null,null,201705090069]
[151,"부산울산","울산","신울산언양#2 T/L","2016~2017년 울산전력지사 송전정비 협력회사 총액공사","154kV 신울산-옥동#1T/L 4호(병가철탑) 애자련교체작업시 근접으로인한 안전이격확보","2017-07-04 08:00","2017-07-04 12:00","2017-07-04 08:00","2017-07-04 12:00","당일",null,null,null,201705100093]
[152,"부산울산","울산","웅촌서창#2 T/L","2017년 170kV 개폐장치 정밀점검공사","웅촌S/S 154kV 6332,6333 GIS 정밀점검관련 시험가압","2017-07-04 17:00","2017-07-04 18:00","2017-07-04 17:00","2017-07-04 18:00","당일",null,null,null,201705090078]
[153,"부산울산","울산","온산처용#2 T/L","2017년 170kV 개폐장치 정밀점검공사","처용S/S 154kV 6332,6333 GIS 정밀점검관련 시험가압","2017-07-06 17:00","2017-07-06 18:00","2017-07-06 17:00","2017-07-06 18:00","당일",null,null,null,201705090075]
[154,"부산울산","직할","부산수정#1 T/L","부산S/S 부산-수정#1T/L GIS(637) 미동작점검","부산S/S 부산-수정#1T/L GIS(637) 미동작점검","2017-07-06 10:00","2017-07-06 12:00","2017-07-06 10:00","2017-07-06 12:00","당일",null,null,null,201705100170]
[155,"부산울산","직할","부산수정#2 T/L","부산S/S 부산-수정#2T/L GIS(647) 미동작점검","부산S/S 부산-수정#2T/L GIS(647) 미동작점검","2017-07-06 13:00","2017-07-06 15:00","2017-07-06 13:00","2017-07-06 15:00","당일",null,null,null,201705100171]
[156,"경남","직할","창공S/S 154kV #1 BUS GIS","창공S/S 154kV GIS화 공사","셰플러코리아T/L 이설(철구-&gtGIS)후 GIS<-&gtEBA간 24H 시험가압","2017-07-29 09:00","2017-07-30 09:00","2017-07-29 09:00","2017-07-30 09:00","연속",null,null,null,201705120128]
[157,"경남","직할","창공S/S 154kV #1 BUS GIS","창공S/S 154kV GIS화 공사","셰플러코리아T/L 이설시 T-BUS 분리작업(GIS-철구 연결 점퍼선 분리)","2017-07-30 09:00","2017-07-30 14:00","2017-08-01 09:00","2017-08-01 14:00","당일",null,null,null,201705120129]
[158,"경남","직할","창공S/S 154kV #2 BUS GIS","창공S/S 154kV GIS화 공사","셰플러코리아T/L 이설시 T-BUS 분리작업(GIS-철구 연결 점퍼선 분리)","2017-07-30 14:00","2017-07-30 19:00","2017-08-01 14:00","2017-08-01 19:00","당일",null,null,null,201705120130]
[159,"경남","진주","하동개양#2 T/L","154kV 하동-개양T/L 이도조정 및 전선교체(동시휴전)","154kV 하동-개양T/L 이도조정 및 전선교체(동시휴전)","2017-07-08 07:00","2017-07-09 18:00","취소","취소","연속",null,null,null,201705100055]
[160,"경남","진주","하동개양#1 T/L","154kV 하동-개양T/L 이도조정 및 전선교체(동시휴전)","154kV 하동-개양T/L 이도조정 및 전선교체(동시휴전)","2017-07-08 07:00","2017-07-09 18:00","취소","취소","연속",null,null,null,201705100054]
[161,"경남","진주","가야사봉 T/L","가야사봉 T/L CB(617) 장기미동작 점검","가야사봉 T/L CB(617) 장기미동작 점검","2017-07-01 09:30","2017-07-01 18:30","2017-07-02 09:30","2017-07-02 15:00","당일",null,null,null,201705110130]
[162,"경남","진주","진주개양#2 T/L","진주개양#2 T/L CB(627) 장기미동작 점검","진주개양#2 T/L CB(627) 장기미동작 점검 - 병행작업: 개양S/S 진주-개양#2T/L CB(617) 장기미동작","2017-07-02 09:30","2017-07-02 15:00","2017-07-02 09:30","2017-07-02 15:00","당일",null,null,null,201705110132]
[163,"경남","함안","신마산차룡#2 T/L","154kV 신마산-차룡T/L 접속개소 전선교체공사","154kV 신마산-차룡T/L 접속개소 전선교체공사 (5~7, 11~17, 36~38호)","2017-07-01 07:30","2017-07-02 18:30","2017-07-01 07:30","2017-07-02 18:30","연속",null,null,null,201705100222]