{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["765송부","345송부","154송부","한수원"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":10,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":5,"n_cols":16,"rows_kept":5,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2017년도 8월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[null,null,null,"해당사항 없음"]

{"sheet":"345송부","index":1,"n_rows":18,"n_cols":16,"rows_kept":18,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2017년도 8월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","직할","신의정부S/S 345kV #2 Sh.R","345kV #2Sh.R 대체공사","신의정부S/S #2Sh.R 대체 및 보호배전반 대체","2017-08-21 09:00","2017-09-02 18:00","2017-08-21 09:00","2017-09-02 18:00","연속",null,null,null,201706130067]
[2,"전북","직할","신남원신광주#1 T/L","345kV 신남원-신광주T/L 전력선교체공사(No.108~116)","전력선 교체 : 7.140C-㎞ (ACSR 480㎟×4B) 가공지선 교체 : 3.570㎞ (ACSR 120㎟×S)","2017-08-21 07:00","2017-08-27 18:00","취소","취소","연속",null,null,null,201706160021]
[3,"전북","직할","신남원신광주#2 T/L","345kV 신남원-신광주T/L 전력선교체공사(No.108~116)","전력선 교체 : 7.140C-㎞ (ACSR 480㎟×4B) 가공지선 교체 : 3.570㎞ (ACSR 120㎟×S)","2017-08-28 07:00","2017-09-03 18:00","취소","취소","연속",null,null,null,201706160022]
[4,"광주전남","광주","신광주S/S #1 M.Tr A","신광주S/S 154kV 취약설비 GIS화 공사","#1M.Tr 2차 인출정비","2017-08-05 09:00","2017-08-05 12:00","2017-08-05 09:00","2017-08-05 12:00","당일",null,null,null,201706050109]
[5,"광주전남","목포","한빛3N/P 345kV #1BUS","한빛3N/P 345kV #1BUS(보호배전반대체)","7C B/F PNL대체","2017-08-21 13:00","2017-08-21 18:00","2017-08-21 13:00","2017-08-21 18:00","당일",null,null,null,201706140120]
[6,"광주전남","목포","한빛3N/P 345kV #2BUS","한빛3N/P 345kV #2BUS(보호배전반대체)","7C B/F PNL대체","2017-08-02 09:00","2017-08-03 13:00","2017-08-01 09:00","2017-08-02 13:00","당일",null,null,null,201706140119]
[7,"광주전남","목포","한빛3N/P 345kV #1BUS","한빛3N/P 345kV #1BUS(보호배전반대체)","7E B/F PNL대체","2017-08-03 13:00","2017-08-03 18:00","2017-08-02 13:00","2017-08-02 18:00","당일",null,null,null,201705300001]
[8,"광주전남","목포","한빛2NP-한빛3NP #3T/L","345kV 한빛연락#3T/L(보호배전반대체)","B/F PNL 대체 GIS 정밀점검","2017-08-07 09:00","2017-08-22 18:00","2017-08-07 09:00","2017-08-22 18:00","연속",null,null,null,201705100046]
[9,"광주전남","목포","한빛3N/P 345kV #2BUS","한빛3N/P 345kV #2BUS(보호배전반대체)","7C B/F PNL대체","2017-08-20 09:00","2017-08-21 13:00","2017-08-21 09:00","2017-08-21 13:00","당일",null,null,null,201705300002]
[10,"대구경북","경산","신경산S/S #3 M.Tr A","신경산S/S 170kV 장기사용 GIS 대체(6344)","6344 GIS 대체","2017-08-28 09:00","2017-09-29 10:00","취소","취소","연속",null,null,null,201706100005]
[11,"대구경북","칠곡","북대구S/S 예비 M.Tr CB","북대구S/S 예비M.Tr 휴전","북대구S/S 예비M.Tr 보통점검","2017-08-01 09:30","2017-08-01 18:00","2017-08-01 09:30","2017-08-01 18:00","당일",null,null,null,201706090184]
[12,"대구경북","칠곡","서대구S/S #3 M.Tr A","서대구S/S #3 M.Tr 휴전","서대구S/S #3 M.Tr 을지훈련용 휴전","2017-08-22 09:30","2017-08-22 18:00","2017-08-21 09:30","2017-08-22 18:00","당일",null,null,null,201706200081]
[13,"경남","통영","신고성S/S #1 M.Tr A","345kV 신고성S/S 23kV Sh.R 설치공사","345kV #1M.Tr 3차 모선 절연카바 취부","2017-08-31 09:00","2017-08-31 12:00","2017-08-31 09:00","2017-08-31 12:00","당일",null,null,null,201706090013]
[14,"경남","통영","신고성S/S #4M.Tr A","345kV 신고성S/S 23kV Sh.R 설치공사","345kV #4M.Tr 3차 모선 절연카바 취부","2017-08-31 12:00","2017-08-31 18:00","2017-08-31 12:00","2017-08-31 18:00","당일",null,null,null,201706090015]

{"sheet":"154송부","index":2,"n_rows":56,"n_cols":16,"rows_kept":56,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2017년도 8월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","능곡상암#1 T/L","2016~2017년 중부전력지사 변전협력업체 총액공사","154kV 능곡상암#1T/L (617) 보호배전반 교체","2017-08-30 10:00","2017-09-01 18:00","2017-08-30 10:00","2017-09-01 18:00","연속",null,null,null,201706140084]
[2,"인천","시흥","동춘송도#2 T/L","154kV 동송도분기 지중T/L 건설공사","- 선종 및 회선 : 154kV XLPE 2000㎟, 4C-2.5km - 기설 154kV 동춘-송도T/L 분기(신설 154kV 동송도S/S)","2017-08-01 09:00","2017-08-30 18:00","취소","취소","연속"]
[3,"인천","인천","송현포스코CC#1 T/L","154kV 송현포스코CC#1T/L 정밀점검","154kV 송현포스코CC#1T/L 정밀점검 시행","2017-08-28 09:00","2017-08-30 18:00","2017-08-28 09:00","2017-08-30 18:00","매일"]
[4,"인천","인천","송현포스코CC#2 T/L","154kV 송현포스코CC#2T/L 정밀점검","154kV 송현포스코CC#2T/L 정밀점검 시행","2017-08-31 09:00","2017-09-02 18:00","2017-08-31 09:00","2017-09-02 18:00","매일"]
[5,"강원","강릉","속초간성#1 T/L","2017년 간성S/S 170kV 장기사용 GIS 대체공사","속초간성#1TL GIS 대체","2017-08-25 08:30","2017-09-15 18:00","2017-08-25 08:30","2017-09-15 18:00","연속"]
[6,"강원","강릉","강릉횡계#2 T/L","154kV 강릉-횡계#2T/L 피뢰기 설치공사","○ 154kV 횡계분기T/L 피뢰기 설치공사(No.1~49 등 52기) ○ 154kV 강릉수력T/L 피뢰기 설치공사(No.10~35 등 26기)","2017-08-08 07:00","2017-08-12 18:00","취소","취소","매일"]
[7,"강원","강릉","영동TP강릉 T/L","154kV 강릉-횡계#2T/L 피뢰기 설치공사","○ 154kV 강릉-횡계#2T/L 피뢰기 설치공사(영동TP-강릉T/L 4회선 병가철탑구간)","2017-08-12 07:00","2017-08-12 18:00","취소","취소","당일"]
[8,"강원","강릉","주진평창#2 T/L","154kV 주진-평창#2T/L 피뢰기 설치공사","○154kV 주진-평창#2T/L 피뢰기 설치공사(No.1~57 등 51기)","2017-08-04 07:00","2017-08-07 18:00","취소","취소","매일"]
[9,"강원","강릉","평창평창올림픽 T/L","2016~17년 송전정비협력회사 총액공사","○ 항공장애표시구 설치(평창-올림픽T/L No.1~횡계평창T/L No.8)","2017-08-02 07:00","2017-08-02 18:00","취소","취소","당일"]
[10,"강원","강릉","횡계평창#1 T/L","2016~17년 송전정비협력회사 총액공사","○ 항공장애표시구 설치(횡계평창#1T/L No.5~7)","2017-08-01 07:00","2017-08-01 18:00","취소","취소","당일"]
[11,"강원","강릉","횡계평창올림픽 T/L","154kV 횡계-올림픽T/L 피뢰기 설치공사","○ 154kV 횡계-올림픽T/L 피뢰기 설치공사(No.2~6 등 5기)","2017-08-03 07:00","2017-08-03 18:00","취소","취소","당일"]
[12,"강원","원주","남원주원주#1 T/L","154kV 원주북원주 등 8개T/L 송전선로용 피뢰기 설치공사","송전선로용 피뢰기설치 25기, 75set","2017-08-28 07:00","2017-08-30 18:00","2017-08-28 07:00","2017-08-30 18:00","매일"]
[13,"전북","군산","군산동군산#1 T/L","군산동군산#1 T/L 피뢰기설치공사","피뢰기설치 : 1기","2017-08-02 07:00","2017-08-02 12:00","2017-08-02 07:00","2017-08-02 12:00","당일"]
[14,"전북","군산","군산동군산#2 T/L","군산동군산#2 T/L 피뢰기설치공사","피뢰기설치 : 1기","2017-08-02 13:00","2017-08-02 18:00","2017-08-02 13:00","2017-08-02 18:00","당일"]
[15,"전북","군산","동군산장항#1 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 3차 공정 - #2BUS 시험가압","2017-08-04 18:00","2017-08-04 19:00","취소","취소","연속"]
[16,"전북","군산","동군산군산CC#2 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 3차 공정 - 군산-동군산#1T/L - 동군산-군산복합#2T/L","2017-08-03 08:00","2017-08-26 18:00","취소","취소","연속"]
[17,"전북","군산","군산동군산#1 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 3차 공정 - 군산-동군산#1T/L - 동군산-군산복합#2T/L","2017-08-03 08:00","2017-08-26 18:00","취소","취소","연속"]
[18,"전북","군산","동군산장항#1 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 3차 공정 - #1BUS 시험가압","2017-08-15 08:00","2017-08-16 08:00","취소","취소","연속"]
[19,"전북","군산","팔봉봉동#1 T/L","팔봉봉동#1 T/L 피뢰기설치공사","피뢰기설치 : 5기","2017-08-01 07:00","2017-08-01 18:00","취소","취소","당일"]
[20,"전북","군산","팔봉두마#1 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 1차 공정 - 팔봉-두마#1T/L, BUS TIE, PT&ES교체","2017-08-07 09:00","2017-09-04 18:00","취소","취소","연속"]
[21,"전북","군산","팔봉두마#2 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 1차 공정 - #2BUS 무부하 가압","2017-08-09 16:00","2017-08-09 18:00","취소","취소","당일"]
[22,"전북","군산","팔봉두마#2 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 1차 공정 - #1BUS 무무하가압","2017-08-20 18:00","2017-08-21 18:00","취소","취소","당일"]
[23,"전북","군산","팔봉영등#2 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 2차 공정 - 팔봉-영등#2T/L 대체작업","2017-08-11 09:00","2017-09-02 18:00","취소","취소","연속"]
[24,"전북","김제","정주고창#1 T/L","154kV 정주-고창T/L 안전이격거리 확보공사","정주-고창#1T/L 철탑 이설 및 전력선 교체 철탑교체 : No.25,31,35호 전력선 교체 : No.24~26, 28~33, 34~37호","2017-08-03 07:00","2017-08-13 18:00","취소","취소","연속"]
[25,"전북","김제","정주고창#1 T/L","154kV 정주-고창T/L 안전이격거리 확보공사","정주-고창#1T/L 철탑 이설 및 전력선 교체 철탑교체 : No.25,31,35호 전력선 교체 : No.24~26, 28~33, 34~37호","2017-08-24 07:00","2017-08-31 18:00","취소","취소","연속"]
[26,"전북","김제","정주고창#2 T/L","154kV 정주-고창T/L 안전이격거리 확보공사","정주-고창#2T/L 철탑 이설 및 전력선 교체 철탑교체 : No.25,31,35호 전력선 교체 : No.24~26, 28~33, 34~37호","2017-08-14 07:00","2017-08-23 18:00","취소","취소","연속"]
[27,"전북","김제","신김제정공#2 T/L","관내S/S 보호배전반 교체공사","신김제 및 남전주S/S 보호반 교체","2017-08-14 09:00","2017-08-17 18:00","취소","취소","연속"]
[28,"전북","김제","신김제남전주#1 T/L","관내S/S 보호배전반 교체공사","신김제 및 남전주S/S 보호반 교체","2017-08-21 09:00","2017-08-24 18:00","취소","취소","연속"]
[29,"전북","김제","신김제남전주#2 T/L","관내S/S 보호배전반 교체공사","신김제 및 남전주S/S 보호반 교체","2017-08-28 09:00","2017-08-31 18:00","취소","취소","연속"]
[30,"전북","김제","정공정주#1 T/L","김제P/O 154kV GIS 정밀점검 공사","차단기 내부점검","2017-08-01 09:00","2017-08-02 18:00","취소","취소","연속"]
[31,"광주전남","광주","신광주계림#1 T/L","신광주S/S 154kV 취약설비 GIS화공사","-게림#1T/L 피뢰기 점검","2017-08-04 08:00","2017-08-04 13:00","취소","취소","당일"]
[32,"광주전남","광주","신광주일곡#2 T/L","신광주S/S 154kV 취약설비 GIS화공사","-알곡#2T/L 피뢰기 점검","2017-08-04 13:00","2017-08-04 18:00","취소","취소","당일"]
[33,"광주전남","직할","하남장성#2 T/L","154kV 하남-장성#2T/L(노후 LA 대체)","17년 직할 변전협력회사 총액공사 - 하남-장성#2T/L 노후 LA 대체","2017-08-27 09:00","2017-08-27 18:00","취소","취소","당일"]
[34,"대구경북","경산","경산S/S ESS #1 EM.Tr CB","경산S/S ESS #1EM.Tr 휴전","1차성능점검 및 ESS 설비 정밀점검","2017-08-21 09:00","2017-09-01 18:00","2017-08-21 09:00","2017-09-01 18:00","연속"]
[35,"대구경북","경산","신경산청통#1 T/L","신경산S/S 170kV 장기사용 GIS 대체(신경산-청통#1T/L)","신경산-청통#1T/L(677 Bay) GIS 대체","2017-08-28 09:00","2017-09-29 10:00","취소","취소","연속"]
[36,"대구경북","경산","신경산S/S 154kV #61 BUS","신경산S/S 170kV 장기사용 GIS 대체관련 #61BUS 휴전","신경산-청통#1, 2T/L 및 6200, 6344 GIS 대체관련 #61BUS측 설치작업 및 무부하 가압","2017-08-31 09:00","2017-09-15 09:00","취소","취소","연속"]
[37,"대구경북","경산","신경산청통#2 T/L","신경산S/S 170kV 장기사용 GIS 대체(신경산-청통#2T/L)","신경산-청통#1T/L(687 Bay) GIS 대체","2017-08-28 09:00","2017-09-29 10:00","취소","취소","연속"]
[38,"대구경북","달성","달서S/S 154kV #1 BUS","달서S/S 170GIS 대체공사","달서S/S GIS 대체공사","2017-08-18 09:00","2017-08-27 18:00","취소","취소","연속"]
[39,"대구경북","달성","다사달서#2 T/L","달서S/S 170GIS 대체공사","달서S/S GIS 대체공사","2017-08-16 09:00","2017-09-04 18:00","취소","취소","연속"]
[40,"대구경북","달성","상인봉덕#2 T/L","EBG접지선 교체공사","EBG 접지선(150mm2)을 접지선(240mm2)으로 교체","2017-08-02 09:00","2017-08-02 18:00","취소","취소","당일"]
[41,"대구경북","달성","상인봉덕#1 T/L","EBG접지선 교체공사","EBG 접지선(150mm2)을 접지선(240mm2)으로 교체","2017-08-01 09:00","2017-08-01 18:00","취소","취소","당일"]
[42,"대구경북","칠곡","구미광평#2 T/L","광평S/S 구미-광평#2T/L 휴전","광평S/S 구미-광평#2T/L 유압작동유 누유개소 보수","2017-08-07 14:00","2017-08-07 18:00","취소","취소","당일"]
[43,"대구경북","칠곡","구미광평#1 T/L","광평S/S 구미-광평#1T/L 휴전","광평S/S 구미-광평#1T/L 유압작동유 누유개소 보수","2017-08-07 09:30","2017-08-07 14:00","취소","취소","당일"]
[44,"부산울산","울산","동울산방어진 T/L","154kV 방어진S/S 현중T/L GIS 대체공사","154kV 방어진S/S 현중T/L GIS 1CCT 대체 - 시험가압 선로","2017-08-02 14:00","2017-08-03 14:00","2017-08-02 14:00","2017-08-03 14:00","연속"]
[45,"부산울산","울산","동울산방어진 T/L","154kV 방어진S/S 현중T/L GIS 대체공사","154kV 방어진S/S 현중T/L GIS 1CCT 대체 - 시험가압 선로","2017-08-07 14:00","2017-08-08 14:00","2017-08-07 14:00","2017-08-08 14:00","연속"]
[46,"부산울산","울산","방어진영남TP#2 T/L","154kV 방어진S/S 현중T/L GIS 대체공사","154kV 방어진S/S 현중T/L GIS 1CCT 대체 - 현대중공업 임시공급선로 설치철거 (안전이격거리확보)","2017-08-13 09:00","2017-08-13 18:00","2017-08-13 09:00","2017-08-13 18:00","당일"]
[47,"부산울산","울산","방어진영남TP#1 T/L","154kV 방어진S/S 현중T/L GIS 대체공사","154kV 방어진S/S 현중T/L GIS 1CCT 대체 - 현대중공업 임시공급선로 설치철거","2017-08-13 09:00","2017-08-13 18:00","2017-08-13 09:00","2017-08-13 18:00","당일"]
[48,"부산울산","울산","동울산방어진 T/L","154kV 방어진S/S 현중T/L GIS 대체공사","154kV 방어진S/S 현중T/L GIS 1CCT 대체 - 시험가압 선로","2017-08-11 14:00","2017-08-12 14:00","2017-08-11 14:00","2017-08-12 14:00","연속"]
[49,"부산울산","울산","신울산언양#1 T/L","2017년 울산P/O 170kV 개폐장치 정밀점검공사","언양S/S 170kV 677 GIS 정밀점검","2017-08-01 08:00","2017-08-04 18:00","취소","취소","연속"]
[50,"부산울산","울산","신울산언양#2 T/L","2017년 울산P/O 170kV 개폐장치 정밀점검공사","언양S/S 170kV 687 GIS 정밀점검","2017-08-05 08:00","2017-08-08 18:00","취소","취소","연속"]
[51,"경남","직할","창공S/S 154kV #2 BUS GIS","창공S/S 154kV GIS화 공사","셰플러코리아T/L 이설시 T-BUS 분리작업(GIS-철구 연결 점퍼선 분리)","2017-08-01 14:00","2017-08-01 19:00","2017-08-01 14:00","2017-08-01 19:00","당일",null,null,null,201705120130]
[52,"경남","직할","창공S/S 154kV #1 BUS GIS","창공S/S 154kV GIS화 공사","셰플러코리아T/L 이설시 T-BUS 분리작업(GIS-철구 연결 점퍼선 분리)","2017-08-01 09:00","2017-08-01 14:00","2017-08-01 09:00","2017-08-01 14:00","당일",null,null,null,201705120129]

{"sheet":"한수원","index":3,"n_rows":6,"n_cols":20,"rows_kept":6,"cut":false,"hidden":false,"merged":[[3,19,4,19],[3,13,4,13],[3,14,4,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,18,4,18],[0,0,0,6],[3,12,4,12],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4],[3,5,4,5],[3,6,3,7],[3,8,3,9],[3,10,4,10],[3,11,4,11]]}
["2017년도 8월 휴전계획표(한국수력원자력)"]
[]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"한빛본부","한빛3발","#6 주변압기","6호기 11차 계획예방정비\n#6 주변압기 점검\n* 조작차단기 : CB 7E00, 7E71","○ 소내자동전원절체 시험 수행\n○ SAT 실부하 위상각 측정\n○ 보호계전기 개체/연동시험 등","2017-08-23T09:00:00","2017-08-23T18:00:00","2017-08-23T09:00:00","2017-08-23T18:00:00","연속","Y"]