{"text_format":"2","workbook":"xlsx","n_sheets":5,"sheets":["765송부","345송부","154송부","한수원","남부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":14,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":12,"n_cols":16,"rows_kept":12,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 9월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #2 M.Tr A-1","신가평S/S #2M.Tr 및 1차 GIS 정밀점검 등","신가평S/S #2M.Tr 정밀점검(안정훈) 및 1차 GIS 정밀점검(이기남), 2차 GIB 장경간 개조공사(모장순)","2017-09-11 09:00","2017-11-17 18:00","2017-09-11 09:00","2017-11-17 18:00","연속",null,null,null,201706270026]
[2,"경기","성남","신안성S/S #4 M.Tr A-1","신안성S/S 765kV #4M.Tr 정밀점검","신안성S/S #4M.Tr 정밀점검 신안성S/S 8772,8700 GIS 정밀점검 신안성S/S #4M.Tr 345kV GIS 구조개선","2017-09-09 09:00","2017-11-24 18:00","2017-09-09 09:00","2017-11-24 18:00","연속",null,null,null,201707130001]
[3,"강원","태백","신태백S/S #2 M.Tr A-1","신태백S/S 345kV 장경간 GIB 구조개선 공사","765kV #2M.Tr 2차 GIB 구조 개선 공사","2017-09-07 09:00","2017-10-27 18:00","2017-09-07 09:00","2017-10-27 18:00","연속",null,null,null,201707100124]
[4,"강원","태백","신태백신한울#1 T/L","2017년 신태백S/S 800kV GIS 정밀점검 공사","○ 신태백-신한울#1T/L (8471CB, 8461, 8401, 8421DS) 정밀점검","2017-09-09 09:00","2017-09-29 18:00","취소","취소","연속",null,null,null,201707060175]
[5,"대전충남","서산","당진T/P 765kV #1 BUS","'17년 변전협력회사 총액공사","당진화력 765kV 부싱 부식단자 교체 작업","2017-09-20 09:00","2017-09-20 18:00","2017-09-20 09:00","2017-09-20 18:00","당일",null,null,null,201707240112]
[6,"대전충남","서산","당진T/P 765kV #2 BUS","'17년 변전협력회사 총액공사","당진화력 765kV 부싱 부식단자 교체 작업","2017-09-21 09:00","2017-09-21 18:00","2017-09-21 09:00","2017-09-21 18:00","당일",null,null,null,201707240113]
[7,"대전충남","서산","신서산S/S 신서산-신안성#2T/L CB","'17년 서산P/O 765kV GIS 보통점검 공사","신서산S/S 765kV 신서산-신안성 #2T/L(8671) 보통점검","2017-09-15 09:00","2017-09-16 18:00","2017-09-15 09:00","2017-09-16 18:00","당일",null,null,null,201707070361]
[8,"부산울산","동부산","신고리S/S #1 M.Tr A-1","신고리S/S 765kV #1M.Tr OLTC 상판 온도센서 교체","신고리S/S 765kV #1M.Tr OLTC 상판 온도센서 교체","2017-09-14 09:30","2017-09-14 17:00","2017-09-14 09:30","2017-09-14 17:00","당일",null,null,null,201707100473]

{"sheet":"345송부","index":1,"n_rows":259,"n_cols":16,"rows_kept":259,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 9월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #2 M.Tr 1차 CB (7272)","17년 성동P/O 변전협력회사 총액공사","362kV GIS 보통점검 (성동S/S 345kV #2M.Tr 1차 7272)","2017-09-25 10:00","2017-09-25 17:00","2017-09-25 10:00","2017-09-25 17:00","당일",null,null,null,201707100168,"-"]
[2,"서울","성동","성동S/S 미금성동#2T/L CB (7271)","17년 성동P/O 변전협력회사 총액공사","362kV GIS 보통점검 (성동S/S 미금성동#2T/L 7271)","2017-09-27 10:00","2017-09-27 17:00","2017-09-27 10:00","2017-09-27 17:00","당일",null,null,null,201707100174,"-"]
[3,"서울","성동","성동S/S 미금성동#2T/L-#2 M.Tr 1차 CB (7200)","17년 성동P/O 변전협력회사 총액공사","362kV GIS 보통점검 (성동S/S 345kV 미금성동#2T/L-#2M.Tr 1차 7200)","2017-09-26 10:00","2017-09-26 17:00","2017-09-26 10:00","2017-09-26 17:00","당일",null,null,null,201707100172,"-"]
[4,"서울","중부","양주중부#1 T/L","345kV 중부S/S 모자익배전반 정비공사","중부S/S 345kV 71 BAY (7171) 모자익반 교체","2017-09-21 10:00","2017-09-29 18:00","2017-09-21 10:00","2017-09-29 18:00","연속",null,null,null,201707100033,"-"]
[5,"서울","중부","양주중부#2 T/L","345kV 중부S/S 모자익배전반 정비공사","중부S/S 345kV 72 BAY (7271) 모자익반 교체","2017-09-13 10:00","2017-09-20 18:00","2017-09-13 10:00","2017-09-20 18:00","연속",null,null,null,201707100034,"-"]
[6,"서울","중부","중부S/S #1 M.Tr A","345kV 중부S/S 모자익배전반 정비공사","중부S/S 345kV 71 BAY (7172) 모자익반 교체","2017-09-21 10:00","2017-09-29 18:00","2017-09-21 10:00","2017-09-29 18:00","연속",null,null,null,201707100027,"-"]
[7,"서울","중부","중부S/S #2 M.Tr A","345kV 중부S/S 모자익배전반 정비공사","중부S/S 345kV 72 BAY (7272) 모자익반 교체","2017-09-05 10:00","2017-09-12 18:00","2017-09-05 10:00","2017-09-12 18:00","연속",null,null,null,201707100026,"-"]
[8,"서울","중부","중부S/S 345kV #1 Sh.R","345kV 중부S/S 모자익배전반 정비공사","중부S/S 345kV 71 BAY (7179) 모자익반 교체","2017-09-21 10:00","2017-09-29 18:00","2017-09-21 10:00","2017-09-29 18:00","연속",null,null,null,201707100032,"-"]
[9,"서울","중부","중부S/S 345kV #2 Sh.R","345kV 중부S/S 모자익배전반 정비공사","중부S/S 345kV 72 BAY (7279) 모자익반 교체","2017-09-13 10:00","2017-09-20 18:00","2017-09-13 10:00","2017-09-20 18:00","연속",null,null,null,201707100031,"-"]
[10,"남서울","동서울","동서울미금#2 T/L","345kV 동서울-미금T/L 지중화공사(하남시 현안지구)","하남시 지역현안1지구 개발관련 요청자 부담 지중화공사 - 기설 가공송전선로 철거 : No.15~No.17(C/H) - 지중송전선로 신설 : 신설C/H ~ J/B#3","2017-09-09 08:00","2017-10-01 18:00","2017-09-09 08:00","2017-10-01 18:00","연속",null,null,null,201707120045,"-"]
[11,"남서울","영등포","영서S/S #1 M.Tr A","영서S/S 345kV GIS 정밀점검 공사","- 345kV 40kA 4000A GIS 내부점검(5CB)","2017-09-17 08:00","2017-09-20 18:00","2017-09-17 08:00","2017-09-20 18:00","연속",null,null,null,201707130114,"-"]
[12,"남서울","영등포","영서S/S #1M.Tr 1차 CB (7571)","영서S/S 345kV GIS 정밀점검 공사(7571 CB)","- 345kV 40kA 4000A GIS 내부점검(5CB)","2017-09-17 08:00","2017-09-18 18:00","2017-09-17 08:00","2017-09-18 18:00","연속",null,null,null,201707170030,"-"]
[13,"남서울","영등포","영서S/S #1M.Tr 1차-영서-영등포#1T/L CB (7500)","영서S/S 345kV GIS 정밀점검 공사(7500 CB)","- 345kV 40kA 4000A GIS 내부점검(5CB)","2017-09-16 08:00","2017-09-18 18:00","2017-09-16 08:00","2017-09-18 18:00","연속",null,null,null,201707170029,"-"]
[14,"남서울","영등포","영서S/S 345kV #70 BUS","영서S/S 345kV GIS 정밀점검 공사(70BUS)","- 345kV 40kA 4000A GIS 내부점검(5CB)","2017-09-18 08:00","2017-09-18 18:00","2017-09-18 08:00","2017-09-18 18:00","연속",null,null,null,201707170032,"-"]
[15,"남서울","영등포","영서S/S 345kV #70 BUS","영서S/S 345kV GIS 정밀점검 공사(70BUS)","- 345kV 40kA 4000A GIS 내부점검","2017-09-24 08:00","2017-09-24 18:00","2017-09-24 08:00","2017-09-24 18:00","연속",null,null,null,201707170045,"-"]
[16,"남서울","영등포","영서S/S 345kV #75 BUS","영서S/S 345kV GIS 정밀점검 공사","- 345kV 40kA 4000A GIS 내부점검(5CB)","2017-09-15 08:00","2017-09-15 18:00","2017-09-15 08:00","2017-09-15 18:00","연속",null,null,null,201707130118,"-"]
[17,"남서울","영등포","영서S/S 345kV #75 BUS","영서S/S 345kV GIS 정밀점검 공사","- 345kV 40kA 4000A GIS 내부점검","2017-09-22 08:00","2017-09-22 18:00","2017-09-22 08:00","2017-09-22 18:00","연속",null,null,null,201707170033,"-"]
[18,"남서울","영등포","영서S/S TIE-영서-영등포#2T/L CB (7600)","영서S/S 345kV GIS 정밀점검 공사(7600 CB)","- 345kV 40kA 4000A GIS 내부점검","2017-09-23 08:00","2017-09-24 18:00","2017-09-23 08:00","2017-09-24 18:00","연속",null,null,null,201707170039,"-"]
[19,"남서울","영등포","영서S/S 영서-영등포#1T/L CB (7572)","영서S/S 345kV GIS 정밀점검 공사(7572CB)","- 345kV 40kA 4000A GIS 내부점검(5CB)","2017-09-15 08:00","2017-09-17 10:00","2017-09-15 08:00","2017-09-17 10:00","연속",null,null,null,201707130112,"-"]
[20,"남서울","영등포","영서S/S 영서-영등포#2T/L CB (7672)","영서S/S 345kV GIS 정밀점검 공사(7672CB)","- 345kV 40kA 4000A GIS 내부점검","2017-09-22 08:00","2017-09-24 10:00","2017-09-22 08:00","2017-09-24 10:00","연속",null,null,null,201707170036,"-"]
[21,"남서울","영등포","영서영등포#1 T/L","영서S/S 345kV GIS 정밀점검 공사","- 345kV 40kA 4000A GIS 내부점검(5CB)","2017-09-16 08:00","2017-09-17 10:00","2017-09-16 08:00","2017-09-17 10:00","연속",null,null,null,201707170022,"-"]
[22,"남서울","영등포","영서영등포#2 T/L","영서S/S 345kV GIS 정밀점검 공사(영서-영등포#2T/L)","- 345kV 40kA 4000A GIS 내부점검","2017-09-23 08:00","2017-09-24 10:00","2017-09-23 08:00","2017-09-24 10:00","연속",null,null,null,201707170042,"-"]
[23,"남서울","직할","영등포S/S #1 M.Tr A","345kV #1M.Tr 보호배전반 교체공사","345kV #1M.Tr 보호배전반 교체공사","2017-09-11 09:30","2017-09-15 18:00","2017-09-11 09:30","2017-09-15 18:00","연속",null,null,null,201707170082,"-"]
[24,"남서울","직할","영등포S/S #2 M.Tr A","345kV #2M.Tr 보호배전반 교체공사","345kV #2M.Tr 보호배전반 교체공사","2017-09-18 09:30","2017-09-22 18:00","2017-09-18 09:30","2017-09-22 18:00","연속",null,null,null,201707170084,"-"]
[25,"남서울","직할","영등포S/S #3 M.Tr A","345kV #3M.Tr 보호배전반 교체공사","345kV #3M.Tr 보호배전반 교체공사","2017-09-25 09:30","2017-09-29 18:00","2017-09-25 09:30","2017-09-29 18:00","연속",null,null,null,201707170085,"-"]
[26,"인천","김포","신김포S/S 345kV #1 Sh.R","신김포S/S 345kV #1 Sh.R 개폐써지 측정기 설치공사","#1 Sh.R 인출측 GIB 개폐써지 측정기 설치","2017-09-06 10:00","2017-09-08 18:00","2017-09-11 10:00","2017-09-13 18:00","연속",null,null,null,201707070055,"-"]
[27,"인천","김포","신김포S/S 345KV 70-71 SEC","신김포S/S 345kV 70-71 SEC GIS 보통점검","신김포S/S 345kV 70-71 SEC GIS 보통점검","2017-09-20 10:00","2017-09-20 18:00","2017-09-19 10:00","2017-09-19 18:00","당일",null,null,null,201707130105,"-"]
[28,"인천","김포","신김포S/S 345KV 75-76 SEC","신김포S/S 345kV 75-76 SEC GIS 보통점검","신김포S/S 345kV 75-76 SEC GIS 보통점검","2017-09-21 10:00","2017-09-21 18:00","2017-09-20 10:00","2017-09-20 18:00","당일",null,null,null,201707130106,"-"]
[29,"인천","시흥","신시흥영흥TP#2 T/L","영흥S/Y 7400 CB C상 CT 교체공사","영흥S/Y 7400 CB C상 CT 교체공사","2017-09-20 08:00","2017-09-21 18:00","취소","취소","연속",null,null,null,201707170123,"-"]
[30,"인천","시흥","영흥T/P #2G/T 1차 CB (7272)","영흥T/P #2G/T 1차 CB (7272) 구조개선공사","영흥T/P #2G/T 1차 CB (7272) 구조개선공사","2017-09-25 08:00","2017-09-27 18:00","2017-09-25 08:00","2017-09-27 18:00","연속",null,null,null,201707140110,"-"]
[31,"인천","시흥","영흥T/P #3 M.Tr(G.T) 1차 CB (7472)","영흥S/Y 7400 CB C상 CT 교체공사","영흥S/Y 7400 CB C상 CT 교체공사","2017-09-20 08:00","2017-09-20 18:00","2017-09-20 08:00","2017-09-20 18:00","당일",null,null,null,201707170124,"-"]
[32,"인천","시흥","영흥T/P #4 M.Tr(G.T) 1차 CB (7572)","영흥T/P #4 M.Tr(G.T) 1차 CB (7572) 구조개선공사","영흥T/P #4 M.Tr(G.T) 1차 CB (7572) 구조개선공사","2017-09-18 08:00","2017-09-20 18:00","2017-09-18 08:00","2017-09-20 18:00","연속",null,null,null,201707140108,"-"]
[33,"인천","시흥","영흥T/P 신시흥영흥TP#4T/L-#4G/T 1차 CB (7500)","영흥T/P 신시흥영흥TP#4T/L-#4G/T 1차CB(7500) 구조개선","영흥T/P 신시흥영흥TP#4T/L-#4G/T 1차 CB (7500) 구조개선공사","2017-09-21 08:00","2017-09-23 18:00","2017-09-21 08:00","2017-09-23 18:00","연속",null,null,null,201707140109,"-"]
[34,"인천","시흥","영흥T/P 영흥TP연락#2T/L-#2G/T 1차 CB (7200)","영흥T/P 영흥TP연락#2T/L-#2G/T 1차CB(7200) 구조개선","영흥T/P 영흥TP연락#2T/L-#2G/T 1차 CB (7200) 구조개선공사","2017-09-28 08:00","2017-09-30 18:00","2017-09-28 08:00","2017-09-30 18:00","연속",null,null,null,201707140111,"-"]
[35,"인천","인천","서인천C/C #2 M.Tr","서인천복합S/Y #2M.Tr 345kV 주변압기 정밀점검 공사","서인천복합S/Y #2M.Tr 345kV 주변압기 정밀점검 공사","2017-09-02 09:00","2017-09-06 18:00","2017-09-02 09:00","2017-09-06 18:00","연속",null,null,null,201706130066,"-"]
[36,"인천","인천","서인천C/C #3 M.Tr","서인천복합S/Y #3M.Tr 345kV 주변압기 정밀점검 공사","서인천복합S/Y #3M.Tr 345kV 주변압기 정밀점검 공사 - #3M.Tr 변압기 정밀점검 및 각종시험 등 - 170kV GIS 정밀점검(#3M.Tr 2차 GIS) 병행 등","2017-09-09 09:00","2017-09-13 18:00","2017-09-09 09:00","2017-09-13 18:00","연속",null,null,null,201706130069,"-"]
[37,"인천","인천","서인천C/C #4 M.Tr","서인천복합S/Y #4M.Tr 345kV 주변압기 정밀점검 공사","서인천복합S/Y #4M.Tr 345kV 주변압기 정밀점검 공사 - #4M.Tr 변압기 정밀점검 및 각종시험 등 - 170kV GIS 정밀점검(#4M.Tr 2차 GIS) 병행 등","2017-09-16 09:00","2017-09-20 18:00","2017-09-16 09:00","2017-09-20 18:00","연속",null,null,null,201706130068,"-"]
[38,"인천","인천","서인천CC신부평#4 T/L","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- 서인천C/C 7A Bay(7A72 CB 및 관련EDS)","2017-09-09 10:00","2017-09-29 17:00","2017-09-09 10:00","2017-09-29 17:00","연속",null,null,null,201707130040,"-"]
[39,"인천","인천","신가좌S/S #1 M.Tr A","신가좌S/S #1M.Tr 휴전작업","신가좌S/S #1M.Tr 휴전작업 - M.Tr 및 LA보통점검 - 3차 Main VCB 보통점검 - 옥외분전반 대체공사(#1M.Tr측)","2017-09-27 09:00","2017-09-29 18:00","2017-09-27 09:00","2017-09-29 18:00","연속",null,null,null,201707130110,"-"]
[40,"인천","인천","신가좌신시흥#1 T/L","신가좌S/S 신가좌-신시흥#1T/L LA 및 GPT 보통점검","신가좌S/S 신가좌-신시흥#1T/L LA 및 GPT 보통점검","2017-09-25 09:00","2017-09-25 18:00","2017-09-25 09:00","2017-09-25 18:00","당일",null,null,null,201707130102,"-"]
[41,"인천","인천","신가좌신시흥#2 T/L","신가좌S/S 신가좌-신시흥#2T/L LA 및 GPT 보통점검","신가좌S/S 신가좌-신시흥#2T/L LA 및 GPT 보통점검","2017-09-26 09:00","2017-09-26 18:00","2017-09-26 09:00","2017-09-26 18:00","당일",null,null,null,201707130103,"-"]
[42,"인천","인천","신경서S/S #1 M.Tr 1차 CB (7172)","인천전력지사 362kV GIS 정밀점검공사(신경서 7172)","인천전력지사 362kV GIS 정밀점검공사(신경서 7172)","2017-09-25 08:30","2017-09-27 18:00","2017-09-25 08:30","2017-09-27 18:00","연속",null,null,null,201707130111,"-"]
[43,"인천","인천","신경서S/S #3 M.Tr 1차 CB (7572)","신경서S/S 3M.Tr 1차 GIS (7572) 조작시험","신경서S/S 3M.Tr 1차 GIS (7572) 조작시험","2017-09-14 09:00","2017-09-14 17:00","2017-09-14 09:00","2017-09-14 17:00","당일",null,null,null,201707130096,"-"]
[44,"인천","인천","신인천C/C 3MT001 CB (7671)","신인천복합S/Y 7671 GIS 초기점검","신인천복합S/Y 7671 GIS 초기점검","2017-09-15 09:00","2017-09-15 18:00","2017-09-15 09:00","2017-09-15 18:00","당일",null,null,null,201707130098,"-"]
[45,"인천","인천","신인천C/C 4MT001 CB (7972)","신인천복합S/Y 7972 GIS 초기점검","신인천복합S/Y 7972 GIS 초기점검","2017-09-28 09:00","2017-09-28 18:00","2017-09-28 09:00","2017-09-28 18:00","당일",null,null,null,201707130107,"-"]
[46,"인천","인천","신인천C/C 4MT201 CB (7872)","신인천복합S/Y 7872 GIS 초기점검","신인천복합S/Y 7872 GIS 초기점검","2017-09-29 09:00","2017-09-29 18:00","2017-09-29 09:00","2017-09-29 18:00","당일",null,null,null,201707130109,"-"]
[47,"인천","인천","신인천C/C TIE-4MT001 CB (7900)","신인천복합S/Y 7900(TIE-4MT001) GIS 초기점검","신인천복합S/Y 7900(TIE-4MT001) GIS 초기점검","2017-09-27 09:00","2017-09-27 18:00","2017-09-27 09:00","2017-09-27 18:00","당일",null,null,null,201707130104,"-"]
[48,"인천","인천","인천T/P 인천복합 #2 S/T CB (7671)","인천전력지사 362kV GIS 정밀점검공사(인천CC 7671)","인천전력지사 362kV GIS 정밀점검공사(인천CC 7671)","2017-09-14 08:30","2017-09-16 18:00","2017-09-14 08:30","2017-09-16 18:00","연속",null,null,null,201707130095,"-"]
[49,"인천","인천","인천T/P 인천복합 #3,4 G/T CB (7571)","인천전력지사 362kV GIS 정밀점검공사(인천CC 7571)","인천전력지사 362kV GIS 정밀점검공사(인천CC 7571)","2017-09-11 08:30","2017-09-13 18:00","2017-09-11 08:30","2017-09-13 18:00","연속",null,null,null,201707130094,"-"]
[50,"경기북부","구리","미금S/S #2 M.Tr A","미금S/S 345kV #2M.Tr 보호반 교체공사","미금S/S 345kV #2M.Tr 보호반 교체공사","2017-09-25 08:00","2017-09-28 18:00","2017-09-25 08:00","2017-09-28 18:00","연속",null,null,null,201707110135,"-"]
[51,"경기북부","구리","미금S/S 345kV #2 Sh.R","미금S/S 345kV #2 Sh.R 대체공사","○ 장기사용으로 인한 설비 노후화 및 설비고장발생 개연성 증가로 대체 필요","2017-09-13 09:00","2017-09-29 18:00","2017-09-13 09:00","2017-09-29 18:00","연속",null,null,null,201704180168,"-"]
[52,"경기북부","구리","미금S/S STATCOM M.Tr","미금S/S STATCOM M.Tr, AUX 정밀점검공사","미금S/S 345kV STATCOM M.Tr, AUX 정밀점검공사(M.Tr,GIS)","2017-09-11 08:00","2017-09-18 18:00","2017-09-11 08:00","2017-09-18 18:00","연속",null,null,null,201705310050,"-"]
[53,"경기북부","구리","미금S/S 미금-성동#1T/L GIS","미금S/S 미금-성동#1T/L GIS 보통점검 (7200)","미금S/S 미금-성동#1T/L GIS 보통점검 (7200)","2017-09-26 09:00","2017-09-26 18:00","2017-09-26 09:00","2017-09-26 18:00","당일",null,null,null,201706200036,"-"]
[54,"경기북부","구리","미금S/S 미금-성동#1T/L GIS","미금S/S 미금-성동#1T/L GIS 보통점검 (7271)","미금S/S 미금-성동#1T/L GIS 보통점검 (7271)","2017-09-25 09:00","2017-09-25 18:00","2017-09-25 09:00","2017-09-25 18:00","당일",null,null,null,201706200035,"-"]
[55,"경기북부","구리","미금S/S 미금-성동#4T/L GIS","미금S/S 미금-성동#4T/L GIS 보통점검 (7772)","미금S/S 미금-성동#4T/L GIS (7772)","2017-09-22 09:00","2017-09-22 18:00","2017-09-22 09:00","2017-09-22 18:00","당일",null,null,null,201706200038,"-"]
[56,"경기북부","구리","신가평S/S 345kV #4 Sh.R","7661,7621DS 점검","- DS결상 및 투입불량점검","2017-09-25 09:00","2017-09-25 18:00","2017-09-25 09:00","2017-09-25 18:00","당일",null,null,null,201707110037,"-"]
[57,"경기북부","구리","신가평미금#1 T/L","345kV 신가평-신의정부#2T/L 스페이서 댐퍼교체공사 병가선로","ㅇ 345kV 신가평-신의정부#2T/L 스페이서 댐퍼교체공사관련 병가선로 - 병가구간 : No.2,3,4,5,6,7호","2017-09-23 08:00","2017-09-23 18:00","2017-09-23 08:00","2017-09-23 18:00","당일",null,null,null,201707050117,"-"]
[58,"경기북부","구리","신가평미금#2 T/L","345kV 신가평-신의정부#1T/L 스페이서 댐퍼교체공사 병가선로","ㅇ 345kV 신가평-신의정부#1T/L 스페이서 댐퍼교체공사관련 병가선로 - 병가구간 : No.2,3,4,5,6,7호","2017-09-16 08:00","2017-09-16 18:00","2017-09-16 08:00","2017-09-16 18:00","당일",null,null,null,201707050116,"-"]
[59,"경기북부","구리","신가평신의정부#1 T/L","345kV 신가평-신의정부#1T/L 스페이서 댐퍼 교체공사","ㅇ 스페이서 댐퍼 교체공사 - 대상 : No.1~98호 경간","2017-09-11 08:00","2017-09-17 18:00","2017-09-11 08:00","2017-09-17 18:00","연속",null,null,null,201706140080,"-"]
[60,"경기북부","구리","신가평신의정부#2 T/L","345kV 신가평-신의정부#2T/L 스페이서 댐퍼 교체공사","ㅇ 스페이서 댐퍼 교체공사 - 대상 : No.1~98호 경간","2017-09-18 08:00","2017-09-24 18:00","2017-09-18 08:00","2017-09-24 18:00","연속",null,null,null,201706140092,"-"]
[61,"경기북부","구리","신포천S/S #1 M.Tr A","17년 154kV 차단기 보통점검","17년 154kV 차단기 보통점검","2017-09-21 14:00","2017-09-21 18:00","2017-09-21 14:00","2017-09-21 18:00","당일",null,null,null,201707070288,"-"]
[62,"경기북부","직할","양주S/S #1 M.Tr A","17년도 경기북부 직할 345kV 주변압기 정밀점검","17년도 경기북부 직할 345kV 주변압기 정밀점검","2017-09-11 09:00","2017-09-16 18:00","2017-09-11 09:00","2017-09-16 18:00","연속",null,null,null,201707100007,"-"]
[63,"경기북부","직할","양주S/S #3 M.Tr A","17년도 경기북부직할 362kV GIS 정밀점검","양주S/S #3 M.Tr 1차 GIS 정밀점검 23kV Sh.R 대체","2017-09-18 09:30","2017-09-23 18:00","2017-09-18 09:30","2017-09-23 18:00","연속",null,null,null,201707100290,"-"]
[64,"경기북부","직할","양주S/S #4 M.Tr A","17년도 경기북부직할 362kV GIS 정밀점검","양주S/S #4M.Tr 1차 GIS 정밀점검","2017-09-25 09:30","2017-09-29 18:00","2017-09-25 09:30","2017-09-29 18:00","연속",null,null,null,201707100294,"-"]
[65,"경기북부","직할","양주S/S 345kV #6 Sh.R","양주S/S 362kV #6Sh.R 1차 GIS 개조공사","362kV #6Sh.R 1차 GIS 공장반입 개조","2017-09-13 09:30","2017-10-20 18:00","2017-09-13 09:30","2017-10-20 18:00","연속",null,null,null,201707100282,"-"]
[66,"경기북부","파주","신덕은S/S #1 M.Tr A","17년 파주전력지사 170kV GIS 정밀점검공사","신덕은 #1M.Tr 2차 GIS 정밀점검","2017-09-18 09:00","2017-09-20 12:00","2017-09-18 09:00","2017-09-20 12:00","연속",null,null,null,201707110226,"-"]
[67,"경기북부","파주","신덕은S/S #2 M.Tr A","17년 파주전력지사 170kV GIS 정밀점검공사","신덕은 #2M.Tr 2차 GIS 정밀점검","2017-09-20 12:00","2017-09-22 18:00","2017-09-20 12:00","2017-09-22 18:00","연속",null,null,null,201707110227,"-"]
[68,"경기북부","파주","신덕은S/S #3 M.Tr A","17년 파주전력지사 170kV GIS 정밀점검공사","신덕은 #3M.Tr 2차 GIS 정밀점검","2017-09-24 09:00","2017-09-26 18:00","2017-09-24 09:00","2017-09-26 18:00","연속",null,null,null,201707170162,"-"]
[69,"경기북부","파주","신덕은S/S 345kV #1 BUS","345kV 신덕은S/S SW 증설공사","ㅇ 345kV GIS 50kA 4000A 3CB 설치 ㅇ 기타 부대공사 1식 * LG Display 전력공급 송전선로 신설","2017-09-27 09:00","2017-10-01 18:00","2017-09-27 09:00","2017-10-01 18:00","연속",null,null,null,201707100280,"-"]
[70,"경기북부","파주","신덕은동두천CC#1 T/L","154kV 남면-백석T/L OPGW 시설공사","1. OPGW 100,120SQ 24/48C SM 1.591km 시설 2. 광케이블(FOFC/ABC) 24/48C SM 7.756km 시설","2017-09-22 09:00","2017-09-25 18:00","2017-09-22 09:00","2017-09-25 18:00","연속",null,null,null,201707100213,"-"]
[71,"경기북부","파주","신덕은동두천CC#2 T/L","154kV 송전선로 피뢰기 설치공사","154KV 남면-백석#1T/L No.3~27 피뢰기 설치공사 병가구간","2017-09-18 07:00","2017-09-21 18:00","2017-09-18 07:00","2017-09-21 18:00","연속",null,null,null,201707170160,"-"]
[72,"경기북부","파주","신파주S/S #1SVC Tr B","신파주S/S SVC 콘덴서 투입용 차단기 설치공사","신파주S/S SVC 콘덴서 투입용 차단기 설치 (토목 투수블록 설치 병행)","2017-09-19 09:00","2017-09-24 18:00","2017-09-19 09:00","2017-09-24 18:00","연속",null,null,null,201707110238,"-"]
[73,"경기","군포","신안산S/S #1 M.Tr A","변압기 기계적 보호장치 정정작업","변압기 기계적 보호장치 운전변경 - 96T 트립에서 경보로 변경","2017-09-13 10:00","2017-09-13 12:00","2017-09-13 10:00","2017-09-13 12:00","당일",null,null,null,201706190074,"-"]
[74,"경기","동부","곤지암신충주#2 T/L","345kV 곤지암-신충주T/L 접속개소 전선교체공사","0 전선교체 : No.4~6 등 13개소, 38경간 0 가공지선 교체 : No.25~32등 2개소 14경간 0 금구류 교체 등","2017-09-12 07:30","2017-10-01 18:00","2017-09-12 07:30","2017-10-01 18:00","연속",null,null,null,201707100382,"-"]
[75,"경기","성남","서서울-신성남 #2T/L T/L","17년 성남변전협력회사 총액공사","71BAY BF 대체","2017-09-25 10:00","2017-09-29 18:00","2017-09-25 10:00","2017-09-29 18:00","연속",null,null,null,201707130035,"-"]
[76,"경기","성남","서안성신진천#1 T/L","345kV 서안성-신진천T/L 피뢰기 설치공사","○ 공사내용 : 송전용피뢰기 설치(30기, 90set) ○ 공사구간 : No.36-98","2017-09-09 08:00","2017-09-11 18:00","2017-09-09 08:00","2017-09-11 18:00","매일",null,null,null,201707110159,"-"]
[77,"경기","성남","신성남S/S #1M.Tr A","17년 성남변전협력회사 총액공사","71BAY BF 대체 및 7172 GIS 보통점검","2017-09-25 10:00","2017-09-29 18:00","2017-09-25 10:00","2017-09-29 18:00","연속",null,null,null,201707130034,"-"]
[78,"경기","성남","신성남S/S #1M.Tr A","신성남S/S 154kV GIS 대체공사","신성남-과천#1T/L, #1BUSTIE 대체 공사관련 무부하 가압","2017-09-23 09:00","2017-09-25 09:00","2017-09-23 09:00","2017-09-25 09:00","당일",null,null,null,201707130033,"-"]
[79,"경기","성남","신성남S/S #1M.Tr A","신성남S/S 154kV GIS 대체공사","신성남-과천#1T/L, #1BUSTIE 대체 공사관련 무부하 가압","2017-09-19 09:00","2017-09-19 21:00","2017-09-19 09:00","2017-09-19 21:00","당일",null,null,null,201707180071,"-"]
[80,"경기","성남","신성남S/S #6 M.Tr A","17년 성남변전협력회사 총액공사","C상 MDU 교체","2017-09-11 10:00","2017-09-11 18:00","2017-09-11 10:00","2017-09-11 18:00","연속",null,null,null,201707210007,"-"]
[81,"경기","성남","신용인신수원 T/L","345kV 신용인-신수원T/L등 2구간 OPGW 시설공사(화성동탄2)","345kV 신용인-신수원T/L 신용인S/T~No.11간 가공지선을 OPGW로 교체","2017-09-20 07:00","2017-09-25 18:00","2017-09-20 07:00","2017-09-25 18:00","연속",null,null,null,201707100105,"-"]
[82,"경기","직할","화성S/S #2M.Tr A","화성S/S 345kV #2M.Tr 배전반정비공사","화성S/S #2M.Tr 배전반정비공사, 보통점검, 2차 정밀점검","2017-09-11 09:00","2017-09-16 18:00","2017-09-11 09:00","2017-09-16 18:00","연속",null,null,null,201707070064,"-"]
[83,"경기","직할","화성서서울#1 T/L","화성S/S 345kV 화성서서울#1T/L(7400,7471) 보통점검","화성S/S 345kV 화성서서울#1T/L(7400,7471) 보통점검, LA교체","2017-09-26 10:00","2017-09-27 18:00","2017-09-26 10:00","2017-09-27 18:00","연속",null,null,null,201707070189,"-"]
[84,"경기","직할","화성신시흥 T/L","화성S/S 345kV 화성신시흥T/L LA교체, CVT보통","화성S/S 345kV 화성신시흥T/L LA교체, CVT보통","2017-09-23 10:00","2017-09-23 18:00","2017-09-23 10:00","2017-09-23 18:00","당일",null,null,null,201707070192,"-"]
[85,"경기","평택","화성평택T/P#1 T/L","154kV 포승-평택TPT/L 7호 안전이격공사 안전확보","○ 공사구간 : 154kV 포승-평택TPT/L No.6~8(6호 하단) ○ 공사규모 : 7호철탑 설치,철거 (2회선 가선로 구성)","2017-09-09 07:00","2017-09-11 18:00","2017-09-09 07:00","2017-09-11 18:00","매일",null,null,null,201707110177,"-"]
[86,"경기","평택","화성평택T/P#2 T/L","154kV 포승-평택TPT/L 7호 안전이격공사 안전확보","○ 공사구간 : 154kV 포승-평택TPT/L No.6~8(6호 하단) ○ 공사규모 : 7호철탑 설치,철거 (2회선 가선로 구성)","2017-09-16 07:00","2017-09-18 18:00","2017-09-16 07:00","2017-09-18 18:00","매일",null,null,null,201707110179,"-"]
[87,"강원","동해","동해S/S #1 M.Tr A","2017년 동해전력지사 변전협력회사 총액공사","1. 과열개소 보수 2. 2차 LA 절연열화측정","2017-09-11 09:00","2017-09-11 18:00","2017-09-11 09:00","2017-09-11 18:00","당일",null,null,null,201707070180,"-"]
[88,"강원","동해","동해S/S #2 M.Tr 1차 CB (7472)","2017년 동해변전소 362kV GIS 정밀점검공사","1. 동해S/S #2M.Tr 1차 CB 정밀점검(7472)","2017-09-21 08:00","2017-09-23 18:00","2017-09-21 08:00","2017-09-23 18:00","연속",null,null,null,201707070118,"-"]
[89,"강원","동해","동해S/S 73BAY TIE CB (7300)","2017년 동해변전소 362kV GIS 정밀점검공사","1. 동해S/S 73BAY TIE CB 정밀점검(7300)","2017-09-11 08:00","2017-09-13 18:00","2017-09-11 08:00","2017-09-13 18:00","연속",null,null,null,201707070104,"-"]
[90,"강원","동해","동해S/S 동해-양양PP T/L CB (7471)","2017년 동해변전소 362kV GIS 정밀점검공사","1. 동해S/S 동해-양양PP T/L CB 정밀점검(7471)","2017-09-14 08:00","2017-09-16 18:00","2017-09-14 08:00","2017-09-16 18:00","연속",null,null,null,201707070107,"-"]
[91,"강원","동해","동해S/S 동해-양양PP T/L-#2 M.Tr 1차 CB (7400)","2017년 동해변전소 362kV GIS 정밀점검공사","1. 동해S/S 74BAY TIE CB 정밀점검(7400)","2017-09-18 08:00","2017-09-20 18:00","2017-09-18 08:00","2017-09-20 18:00","연속",null,null,null,201707070115,"-"]
[92,"강원","동해","삼척GP S/S 345kV #71 BUS","345kV 삼척GP S/Y 362kV GIS 증설공사","1. 362kV GIS 50KA 2CB 설치 2. 부대공사 1식","2017-09-18 10:00","2017-09-21 18:00","2017-09-18 10:00","2017-09-21 18:00","연속",null,null,null,201707210021,"-"]
[93,"강원","동해","삼척GP S/S 345kV #76 BUS","345kV 삼척GP S/Y 362kV GIS 증설공사","1. 362kV GIS 50KA 2CB 설치 2. 부대공사 1식","2017-09-22 10:00","2017-09-25 18:00","2017-09-22 10:00","2017-09-25 18:00","연속",null,null,null,201707210022,"-"]
[94,"강원","동해","신제천동해#2 T/L","2016~2017년 송전정비 협력회사 총액공사","이도조정 및 스페이샤 댐퍼 교페 4구간","2017-09-19 07:00","2017-09-22 18:00","2017-09-19 07:00","2017-09-22 18:00","연속",null,null,null,201707030081,"-"]
[95,"강원","태백","신태백한울NP2#1 T/L","울태 345kV 신태백-한울NP2T/L 정밀점검 공사","○ 345kV 울태T/L 정밀점검","2017-09-17 09:00","2017-09-24 18:00","2017-09-17 09:00","2017-09-24 18:00","매일",null,null,null,201707060178,"-"]
[96,"강원","태백","신태백한울NP2#2 T/L","울태 345kV 신태백-한울NP2T/L 정밀점검 공사","○ 345kV 울태T/L 정밀점검 공사(송전) ○ 345kV 신태백-한울NP2#2T/L GIS 정밀점검 공사(변전)","2017-09-09 09:00","2017-09-16 18:00","2017-09-09 09:00","2017-09-16 18:00","연속",null,null,null,201707060176,"-"]
[97,"강원","태백","신태백한울NP3 T/L","16~17 태백전력지사 변전정비 총액공사","○ 신태백S/S 362kV 7400CB 보통점검","2017-09-20 10:00","2017-09-20 18:00","2017-09-20 10:00","2017-09-20 18:00","당일",null,null,null,201707060182,"-"]
[98,"강원","태백","신태백S/S 7472 CB (7472)","○ 16~17 태백전력지사 변전정비 총액공사","○ 7400CB 보통점검 관련 인접설비 개방","2017-09-20 10:00","2017-09-20 18:00","2017-09-20 10:00","2017-09-20 18:00","당일",null,null,null,201707310096,"-"]
[99,"충북","직할","신제천S/S #2 M.Tr A","345kV 신제천S/S GIS화 공사","#2M.Tr OLTC Tap Indicator 교체","2017-09-14 09:00","2017-09-14 18:00","2017-09-14 09:00","2017-09-14 18:00","당일",null,null,null,201707170050,"-"]
[100,"충북","직할","신제천S/S #3 M.Tr A","345kV 신제천S/S #3M.Tr 대체공사","#3M.Tr 대체","2017-09-18 08:00","2017-10-13 18:00","2017-09-18 08:00","2017-10-13 18:00","연속",null,null,null,201707240134,"-"]
[101,"충북","직할","신제천S/S #4 M.Tr A","#4M.Tr 3차 PT교체","#4M.Tr 3차 PT교체","2017-09-11 09:00","2017-09-13 18:00","2017-09-11 09:00","2017-09-13 18:00","연속",null,null,null,201707070052,"-"]
[102,"충북","직할","신제천신충주#1 T/L","2016~2017년 직할 송전정비 협력업체 총액공사","전력선 교체(175~176) 및 조류착지방지장치설치(5~158)","2017-09-12 07:30","2017-09-15 18:00","2017-09-12 07:30","2017-09-15 18:00","연속",null,null,null,201707130070,"-"]
[103,"충북","직할","신제천신충주#2 T/L","2016~2017년 직할 송전정비 협력업체 총액공사","전력선 교체(175~176) 및 조류착지방지장치설치(5~158)","2017-09-08 07:00","2017-09-10 18:00","2017-09-08 07:00","2017-09-10 18:00","연속",null,null,null,201707130069,"-"]
[104,"충북","직할","신충주S/S #3 M.Tr A","345kV 신충주S/S STATCOM용 GIS 설치공사","345kV GIS 2CB 설치 기타부대작업","2017-09-27 10:00","2017-09-28 10:00","2017-09-27 10:00","2017-09-28 10:00","연속",null,null,null,201707170157,"-"]
[105,"충북","직할","신충주S/S 345kV #1 BUS","345kV 신충주S/S STATCOM용 GIS 설치공사","345kV GIS 2CB 설치 기타부대작업","2017-09-18 10:00","2017-09-22 10:00","취소","취소","연속",null,null,null,201707060061,"-"]
[106,"충북","직할","신충주S/S 345kV #2 BUS","345kV 신충주S/S STATCOM용 GIS 설치공사","345kV GIS 2CB 설치 기타부대작업","2017-09-23 10:00","2017-09-27 10:00","2017-09-23 10:00","2017-09-27 10:00","연속",null,null,"신뢰도개선",201707060062,"-"]
[107,"충북","직할","신충주S/S 신제천-신충주#2 T/L GIS","345kV 신충주S/S STATCOM용 GIS 설치공사","345kV GIS 2CB 설치 기타부대작업","2017-09-22 10:00","2017-09-23 10:00","취소","취소","연속",null,null,null,201707060066,"-"]
[108,"충북","직할","신충주S/S 신제천-신충주#2 T/L GIS","345kV 신충주S/S STATCOM용 GIS 설치공사","345kV GIS 2CB 설치 기타부대작업","2017-09-27 10:00","2017-09-28 10:00","2017-09-27 10:00","2017-09-28 10:00","연속",null,null,null,201707060064,"-"]
[109,"충북","직할","신충주S/S 신제천-신충주#2T/L-TIE GIS","345kV 신충주S/S STATCOM용 GIS 설치공사","345kV GIS 2CB 설치 기타부대작업","2017-09-22 10:00","2017-09-23 10:00","취소","취소","연속",null,null,null,201707060098,"-"]
[110,"충북","직할","신충주S/S 신제천-신충주#2T/L-TIE GIS","345kV 신충주S/S STATCOM용 GIS 설치공사","345kV GIS 2CB 설치 기타부대작업","2017-09-27 10:00","2017-09-28 10:00","2017-09-27 10:00","2017-09-28 10:00","연속",null,null,null,201707060073,"-"]
[111,"충북","청주","신옥천S/S #1 M.Tr A","2017년 청주전력 변전협력회사 총액공사","#1M.Tr 2차 CB 공기조작부 분해 점검","2017-09-14 09:30","2017-09-14 18:00","2017-09-14 09:30","2017-09-14 18:00","당일",null,null,null,201707170056,"-"]
[112,"충북","청주","신옥천S/S #2 M.Tr A","2017년 청주전력 변전협력회사 총액공사","#2M.Tr 2차 CB 공기조작부 분해 점검","2017-09-15 09:30","2017-09-15 18:00","2017-09-15 09:30","2017-09-15 18:00","당일",null,null,null,201707170057,"-"]
[113,"충북","충주","신진천S/S #1 M.Tr A","345kV 신진천S/S 용량부족 GIS 대체공사","345kV #72BAY 3CB 철거 345kV #72BAY 3CB 기초보강 345kV #72BAY 3CB 신설","2017-09-18 09:00","2018-01-19 18:00","2017-09-18 09:00","2018-01-19 18:00","연속",null,null,null,201707040040,"-"]
[114,"충북","충주","신진천S/S #2 M.Tr A","전력관리처 자동화 파트 디지털메타 교체에 따른 데이터 일치 작업","전력관리처 자동화 파트 디지털메타 교체에 따른 데이터 일치 작업","2017-09-04 10:00","2017-09-08 18:00","2017-09-04 10:00","2017-09-08 18:00","당일",null,null,null,201707120064,"-"]
[115,"충북","충주","신진천S/S #3 M.Tr A","전력관리처 자동화 파트 디지털메타 교체에 따른 데이터 일치 작업","전력관리처 자동화 파트 디지털메타 교체에 따른 데이터 일치 작업","2017-09-14 10:00","2017-09-14 18:00","2017-09-14 10:00","2017-09-14 18:00","당일",null,null,null,201707120065,"-"]
[116,"충북","충주","청원신진천#2 T/L","345kV 신진천S/S 용량부족 GIS 대체공사","345kV #72BAY 3CB 철거 345kV #72BAY 3CB 기초보강 345kV #72BAY 3CB 신설","2017-09-18 09:00","2018-01-19 18:00","2017-09-18 09:00","2018-01-19 18:00","연속",null,null,null,201707040039,"-"]
[117,"대전충남","서산","신당진S/S #1 M.Tr A","'17년 서산P/O 345kV M.Tr 정밀점검 공사","신당진S/S 345kV #1M.Tr 정밀점검","2017-09-11 09:00","2017-09-29 18:00","2017-09-11 09:00","2017-09-29 18:00","당일",null,null,null,201707070304,"-"]
[118,"대전충남","서산","신당진S/S 7171 CB (7171)","'17년 변전협력회사 총액공사","신당진S/S 345kV 7171 GIS 보통점검","2017-09-20 10:00","2017-09-20 18:00","2017-09-20 10:00","2017-09-20 18:00","당일",null,null,null,201707070339,"-"]
[119,"대전충남","서산","신당진S/S 신서산-신당진#1T/L CB (7172)","'17년 변전협력회사 총액공사","신당진S/S 345kV 신서산-신당진 #1T/L GIS(7172) 보통점검 및 CVT 대체","2017-09-18 10:00","2017-09-18 18:00","2017-09-18 10:00","2017-09-18 18:00","당일",null,null,null,201707070337,"-"]
[120,"대전충남","서산","신당진S/S 신서산신당진#1T/L-TIE CB (7100)","'17년 서산P/O 345kV GIS 정밀점검 공사","신당진S/S 345kV 신서산신당진#1T/L-TIE GIS(7100) 정밀점검","2017-09-18 09:00","2017-09-21 18:00","2017-09-18 09:00","2017-09-21 18:00","당일",null,null,null,201707070331,"-"]
[121,"대전충남","서산","신서산S/S 신서산-신당진#2T/L CB (7772)","'17년 서산P/O 345kV GIS 정밀점검 공사","신서산S/S 345kV 신서산-신당진#2T/L GIS(7772) 정밀점검","2017-09-11 09:00","2017-09-14 18:00","2017-09-11 09:00","2017-09-14 18:00","당일",null,null,null,201707070310,"-"]
[122,"대전충남","서산","태안T/P 345kV #75 BUS","태안화력 345kV 용량부족 및 장기사용 GIS 교체공사","1.기존 40KA, 4000A CB 4대 철거(7300, 7372, 70710, 75760) 2 대체 63KA, 6300A CB 4대 철거(7300, 7372, 70710, 75760) ㅇ 금회휴전 시 - 9/1~9/29 : 75760 GIS (75, 76 BUS) 철거,설치 - 9/30~10/27 : 7300, 7372 GIS 철거,설치(계속)","2017-09-01 14:00","2017-10-27 15:00","2017-09-01 14:00","2017-10-27 15:00","연속",null,null,null,201707060223,"-"]
[123,"대전충남","서산","태안T/P 345kV #76 BUS","태안화력 345kV 용량부족 및 장기사용 GIS 교체공사","1.기존 40KA, 4000A CB 4대 철거(7300, 7372, 70710, 75760) 2 대체 63KA, 6300A CB 4대 철거(7300, 7372, 70710, 75760) ㅇ 금회휴전 시 - 9/1~9/29 : 75760 GIS (75, 76 BUS) 철거,설치","2017-09-01 14:00","2017-09-29 15:00","2017-09-01 14:00","2017-09-29 15:00","연속",null,null,null,201707060224,"-"]
[124,"대전충남","서산","태안T/P 3호기 1차 CB (7372)","태안화력 345kV 용량부족 및 장기사용 GIS 교체공사","1.기존 40KA, 4000A CB 4대 철거(7300, 7372, 70710, 75760) 2 대체 63KA, 6300A CB 4대 철거(7300, 7372, 70710, 75760) ㅇ 금회휴전 시 - 9/30~12/1 : 7300,7372 GIS 철거,설치","2017-09-30 14:00","2017-12-01 15:00","2017-09-30 14:00","2017-12-01 15:00","연속",null,null,null,201707060228,"-"]
[125,"대전충남","서산","태안T/P TIE-3호기 1차 CB (7300)","태안화력 345kV 용량부족 및 장기사용 GIS 교체공사","1.기존 40KA, 4000A CB 4대 철거(7300, 7372, 70710, 75760) 2 대체 63KA, 6300A CB 4대 철거(7300, 7372, 70710, 75760) ㅇ 금회휴전 시 - 9/30~12/1 : 7300,7372 GIS 철거,설치","2017-09-30 14:00","2017-12-01 15:00","2017-09-30 14:00","2017-12-01 15:00","연속",null,null,null,201707060227,"-"]
[126,"대전충남","서산","태안T/P 신당진-태안TP#2T/L CB (7971)","'17년 변전협력회사 총액공사","태안화력 345kV 개폐소-태안화력 #2T/L GIS(7971) 하자점검 및 LA 보통점검","2017-09-25 10:00","2017-09-25 18:00","2017-09-25 10:00","2017-09-25 18:00","당일",null,null,null,201707070356,"-"]
[127,"대전충남","아산","아산S/S 신서산-아산#2T/L-#1 M.Tr 1차 CB (7300)","아산S/S 345kV 7300 TIE GIS 정밀점검","○ 345kV 7300 TIE GIS 정밀점검","2017-09-25 09:00","2017-09-27 18:00","2017-09-25 09:00","2017-09-27 18:00","연속",null,null,null,201707060104,"-"]
[128,"대전충남","아산","아산S/S 아산#2T/L-아산-보령화력#1T/L CB (7200)","아산S/S 345kV 7200 TIE GIS 정밀점검","○ 345kV 7200 TIE GIS 정밀점검","2017-09-20 09:00","2017-09-22 18:00","2017-09-20 09:00","2017-09-22 18:00","연속",null,null,null,201707060102,"-"]
[129,"대전충남","아산","청양신온양#1 T/L","[송전]345kV 청양-신온양T/L 안전이격확보공사","ㅇ 철탑교체 2기 : 116,129호(Enclosing 상향공법) ㅇ 전선교체 : 127~130호가(4가닥) ㅇ OPGW 이설 : 전자제어파트 시행 ㅇ 기타 부대공사","2017-09-16 08:00","2017-09-24 18:00","2017-09-16 08:00","2017-09-24 18:00","연속",null,null,null,201707070125,"-"]
[130,"대전충남","청양","보령T/P 70-71-0 SEC CB (70-71-0)","보령화력 362kV GIS 초기점검","○ 345kV 70-71-0 GIS 초기점검","2017-09-07 09:00","2017-09-07 18:00","2017-09-07 09:00","2017-09-07 18:00","당일",null,null,null,201707060058,"-"]
[131,"대전충남","청양","보령T/P 75-76-0 SEC CB (75-76-0)","보령화력 362kV GIS 초기점검","○ 345kV 75-76-0 GIS 초기점검","2017-09-08 09:00","2017-09-08 18:00","2017-09-08 09:00","2017-09-08 18:00","당일",null,null,null,201707060059,"-"]
[132,"대전충남","청양","신옥천청양 T/L","청양S/S 신옥천-청양T/L 송전선로보호반 교체","청양S/S 신옥천-청양T/L 송전선로보호반 교체","2017-09-25 09:00","2017-09-29 18:00","2017-09-25 09:00","2017-09-29 18:00","연속",null,null,null,201707050009,"-"]
[133,"대전충남","청양","청양S/S #1 M.Tr 1차 CB (7671)","청양S/S 362kV GIS 보통점검","-7671CB","2017-09-14 09:00","2017-09-15 18:00","2017-09-14 09:00","2017-09-15 18:00","연속",null,null,null,201707060011,"-"]
[134,"대전충남","청양","청양S/S #2 M.Tr A","청양S/S #2M.Tr 1차 예비모선 정비 및 6242DS 가스 누기보수","○ #2M.Tr 1차 예비모선 정비 ○ 6242DS 가스 누기보수 ○ 6244 GIS 하자점검","2017-09-09 08:00","2017-09-10 18:00","2017-09-09 08:00","2017-09-10 18:00","연속",null,null,null,201707060016,"-"]
[135,"대전충남","청양","청양S/S 345kV #76 BUS","청양S/S #76BUS 보호반 교체","#76BUS 보호반 교체","2017-09-11 09:00","2017-09-13 18:00","2017-09-11 09:00","2017-09-13 18:00","연속",null,null,null,201707050008,"-"]
[136,"대전충남","청양","청양S/S 청양-신온양#2T/L CB (7571)","청양S/S 362kV GIS 보통점검","-7571CB","2017-09-06 09:00","2017-09-07 18:00","2017-09-06 09:00","2017-09-07 18:00","연속",null,null,null,201707060010,"-"]
[137,"대전충남","청양","청양S/S 청양신온양#2T/L-TIE CB (7500)","청양S/S 362kV GIS 보통점검","-7500CB","2017-09-04 09:00","2017-09-05 18:00","2017-09-04 09:00","2017-09-05 18:00","연속",null,null,null,201707060009,"-"]
[138,"전북","군산","군산신김제#1 T/L","군산신김제T/L 항공장애표시구 설치 공사","항공장애표시구설치 : 24~95","2017-09-20 07:00","2017-09-29 18:00","2017-09-20 07:00","2017-09-29 18:00","매일",null,null,null,201707240146,"-"]
[139,"전북","김제","군산신김제#1 T/L","신김제S/S 345kV #2BUS 가스누기 보수공사","신김제S/S 345kV #2 BUS 시험가압(2시간)","2017-09-13 14:00","2017-09-13 16:00","2017-09-13 14:00","2017-09-13 16:00","연속",null,null,null,201707190018,"-"]
[140,"전북","김제","군산신김제#2 T/L","신김제S/S 345kV #2BUS 가스누기 보수공사","신김제S/S 345kV #2 BUS 시험가압(2시간)","2017-09-13 14:00","2017-09-13 16:00","2017-09-13 14:00","2017-09-13 16:00","연속",null,null,null,201707250006,"-"]
[141,"전북","김제","신김제S/S #1 M.Tr A","관내S/S 345kV 변압기 보통점검","345kV 변압기 보통점검","2017-09-19 09:00","2017-09-19 18:00","2017-09-19 09:00","2017-09-19 18:00","당일",null,null,null,201707190022,"-"]
[142,"전북","김제","신김제S/S #2 M.Tr A","관내S/S 345kV 변압기 보통점검","345kV 변압기 보통점검","2017-09-18 09:00","2017-09-18 18:00","2017-09-18 09:00","2017-09-18 18:00","당일",null,null,null,201707190021,"-"]
[143,"전북","김제","신김제S/S #3 M.Tr A","관내S/S 345kV 변압기 보통점검","345kV 변압기 보통점검","2017-09-15 09:00","2017-09-15 18:00","2017-09-15 09:00","2017-09-15 18:00","당일",null,null,null,201707190020,"-"]
[144,"전북","김제","신김제S/S #4 M.Tr A","관내S/S 345kV 변압기 보통점검","345kV 변압기 보통점검","2017-09-14 09:00","2017-09-14 18:00","2017-09-14 09:00","2017-09-14 18:00","당일",null,null,null,201707190019,"-"]
[145,"전북","김제","신김제S/S 345kV #2 BUS","신김제S/S 345kV #2BUS 가스누기 보수공사","-. 플랜지 가스누기 보수공사","2017-09-04 09:00","2017-09-13 18:00","2017-09-04 09:00","2017-09-13 18:00","연속",null,null,null,201707130135,"-"]
[146,"전북","직할","신남원신광주#1 T/L","345kV 신남원-신광주T/L 전력선 교체공사(No.8~58)","○ 전력선교체 : No.8~10, 30~34 ○ 스페이서 댐퍼 설치/철거 : 180/150개","2017-09-01 07:00","2017-09-06 18:00","2017-09-01 07:00","2017-09-06 18:00","연속",null,null,null,201707110075,"-"]
[147,"전북","직할","신남원신광주#2 T/L","345kV 신남원-신광주T/L 전력선 교체공사(No.8~58)","○ 전력선교체 : No.8~10, 30~34 ○ 스페이서 댐퍼 설치/철거 : 180/150개","2017-09-07 07:00","2017-09-12 18:00","2017-09-07 07:00","2017-09-12 18:00","연속",null,null,null,201707110076,"-"]
[148,"전북","직할","신남원의령#1 T/L","신남원S/S 345kV 장기사용 T/L 보호반 대체공사","장기사용 345kV T/L 보호반 철거 및 설치 공사","2017-09-04 09:00","2017-09-09 18:00","2017-09-04 09:00","2017-09-10 18:00","연속",null,null,null,201707190027,"-"]
[149,"전북","직할","신남원의령#2 T/L","신남원S/S 345kV 장기사용 T/L 보호반 대체공사","장기사용 345kV T/L 보호반 철거 및 설치 공사","2017-09-11 09:00","2017-09-16 18:00","2017-09-11 09:00","2017-09-16 18:00","연속",null,null,null,201707190026,"-"]
[150,"광주전남","강진","신강진S/S #2 M.Tr A","신강진S/S 345kV #2M.Tr(강진 변전협력회사 총액공사)","신강진S/S #2M.Tr 1차 차단기 보통점검 등","2017-09-13 09:00","2017-09-15 18:00","2017-09-13 09:00","2017-09-15 18:00","연속",null,null,null,201707170140,"-"]
[151,"광주전남","강진","신강진S/S 345kV #1 BUS","신강진S/S 345kV #1BUS(강진 변전협력회사 총액공사)","신강진S/S 345kV #1BUS PT 보통점검","2017-09-18 09:00","2017-09-18 14:00","2017-09-09 09:00","2017-09-09 14:00","당일",null,null,null,201707170141,"-"]
[152,"광주전남","강진","신강진S/S 345kV #2 BUS","신강진S/S 345kV #2BUS(강진 변전협력회사 총액공사)","신강진S/S 345kV #2BUS PT 보통점검","2017-09-18 14:00","2017-09-18 19:00","2017-09-09 14:00","2017-09-09 19:00","당일",null,null,null,201707170142,"-"]
[153,"광주전남","광주","신광주S/S #1 M.Tr A","신광주S/S 취약설비 GIS화 공사","#1M.Tr 2차 인출정비","2017-09-11 09:00","2017-09-11 12:00","2017-09-11 09:00","2017-09-11 12:00","당일",null,null,null,201707070131,"-"]
[154,"광주전남","광주","신광주S/S #2 M.Tr A","축소형 모자익 교체에 따른 연동시험","축소형 모자익 교체에 따른 연동시험","2017-09-15 10:00","2017-09-15 11:00","2017-09-15 10:00","2017-09-15 11:00","당일",null,null,null,201707100135,"-"]
[155,"광주전남","광주","신광주S/S #3 M.Tr A","축소형 모자익 교체에 따른 연동시험","축소형 모자익 교체에 따른 연동시험","2017-09-15 14:00","2017-09-15 15:00","2017-09-15 14:00","2017-09-15 15:00","당일",null,null,null,201707100139,"-"]
[156,"광주전남","광주","신광주S/S #4 M.Tr A","신광주S/S Sh.C전력케이블설치 공사","#1.2.3 Sh.C GIS 인출용 케이블 헤드 설치","2017-09-13 09:00","2017-09-13 18:00","2017-09-13 09:00","2017-09-13 18:00","당일",null,null,null,201707070077,"-"]
[157,"광주전남","광주","신광주신화순#1 T/L","신광주신화순#1 T/L(변전협력회사공사)","LA교체","2017-09-27 09:00","2017-09-27 18:00","2017-09-27 09:00","2017-09-27 18:00","당일",null,null,null,201707170094,"-"]
[158,"광주전남","광주","신광주신화순#2 T/L","신광주신화순#2 T/L(변전협력회사공사)","LA교체","2017-09-28 09:00","2017-09-28 18:00","2017-09-28 09:00","2017-09-28 18:00","당일",null,null,null,201707170095,"-"]
[159,"광주전남","순천","광양S/S #1 M.Tr A","345kV 광양S/S 362kV GIS 대체공사","가. GIS(345kV 50kA 4000A) ×27 CB 철거 나. GIS(345kV 63kA 6300A) ×27 CB 설치 다. 기타 부대작업 × 1식","2017-09-18 10:00","2017-12-22 18:00","2017-09-25 10:00","2018-01-08 18:00","당일",null,null,null,201707040093,"-"]
[160,"광주전남","순천","광양S/S 345kV #75 BUS","광양S/S 345kV #75BUS GIS 보강공사","- 모선내부정밀점검 및 Bellows측 Moving Cond 교체 - 모선Level 조정작업(Stud Bolt 및 고정Plate 교체) - 기타 부대공사 1식","2017-09-25 09:00","2017-10-01 18:00","2017-10-23 09:00","2017-10-29 18:00","연속",null,null,null,201707180011,"-"]
[161,"광주전남","순천","광양율촌CC T/L","345kV 광양-율촌CC T/L","345kV 신남원-광양 전선접속개소 해소공사 - 광양-율촌CC T/L 전선접속개소 해소","2017-09-26 08:00","2017-10-19 18:00","2017-09-25 08:00","2017-10-19 18:00","연속",null,null,null,201707180027,"-"]
[162,"광주전남","순천","신남원광양#1 T/L","345kV 신남원-광양T/L 안전이격확보공사","345kV 신남원-광양T/L 인클로징 철탑상향(7기)","2017-09-09 07:00","2017-09-17 18:00","2017-09-17 07:00","2017-09-24 18:00","연속",null,null,null,201707130121,"-"]
[163,"광주전남","순천","광양율촌CC T/L","광양S/S 345kV #75BUS GIS 보강공사","- 모선 보강공사후 무부하 가압","2017-09-30 18:00","2017-10-01 18:00","2017-10-28 18:00","2017-10-29 18:00","연속",null,null,null,201707180012,"-"]
[164,"광주전남","순천","신남원광양#2 T/L","345kV 광양S/S 362kV GIS 대체공사","가. GIS(345kV 50kA 4000A) ×27 CB 철거 나. GIS(345kV 63kA 6300A) ×27 CB 설치 다. 기타 부대작업 × 1식","2017-09-18 10:00","2017-12-22 18:00","2017-09-25 10:00","2018-01-08 18:00","당일",null,null,null,201707040092,"-"]
[165,"대구","경산","신경산S/S #3 M.Tr A","17년 신경산S/S 170kV 장기사용 GIS 대체(5차 공정)","신경산-청통#1, 2T/L 및 6200, 6344 GIS 대체(4Bay 동시)","2017-09-04 09:00","2017-09-29 18:00","2017-09-09 09:00","2017-10-15 14:00","연속",null,null,null,201707060060,"-"]
[166,"대구","달성","고령S/S #3 M.Tr A","고령S/S 주변압기 정밀점검","고령S/S 주변압기 정밀점검","2017-09-08 09:00","2017-09-10 18:00","2017-09-08 09:00","2017-09-10 18:00","연속",null,null,null,201707100147,"-"]
[167,"대구","달성","고령S/S #3 M.Tr A","고령S/S 주변압기 정밀점검","고령S/S 주변압기 정밀점검","2017-09-15 09:00","2017-09-17 18:00","2017-09-15 09:00","2017-09-17 18:00","연속",null,null,null,201707100149,"-"]
[168,"대구","달성","고령S/S #3 M.Tr A","고령S/S 주변압기 정밀점검","고령S/S 주변압기 정밀점검","2017-09-22 09:00","2017-09-24 18:00","2017-09-22 09:00","2017-09-24 18:00","연속",null,null,null,201707100151,"-"]
[169,"대구","칠곡","북대구S/S #2 M.Tr 1차 CB (7472)","북대구S/S #2 M.Tr 1차 CB(7472) GIS 정밀점검","2017년 하반기 칠곡전력지사 362kV GIS 정밀점검공사","2017-09-25 09:30","2017-09-27 14:00","취소","취소","연속",null,null,null,201707100301,"-"]
[170,"대구","칠곡","북대구S/S #2 M.Tr A","2017년 칠곡전력지사 차단기 정밀점검공사","2017년 칠곡전력지사 차단기 정밀점검공사 (7472, 7400 GIS)","2017-09-25 09:30","2017-09-30 18:00","2017-09-25 09:30","2017-09-30 18:00","연속",null,null,null,201707140105,"-"]
[171,"대구","칠곡","북대구S/S TIE-#2 M.Tr 1차-TIE CB (7400)","북대구S/S TIE-#2 M.Tr 1차-TIE CB(7400) 정밀점검","2017년 하반기 칠곡전력지사 362kV GIS 정밀점검공사","2017-09-27 14:00","2017-09-29 18:00","취소","취소","연속",null,null,null,201707100302,"-"]
[172,"대구","칠곡","북대구선산 T/L","345kV 선산분기(북대구-선산) TL 피뢰기 설치공사","345kV 선산분기(북대구-선산 회선) No.31-64 피뢰기 설치공사","2017-09-09 08:00","2017-09-12 18:00","2017-09-11 08:00","2017-09-14 18:00","연속",null,null,null,201707100008,"-"]
[173,"대구","칠곡","서대구S/S #1M.Tr A","서대구S/S #1M.Tr 휴전","서대구S/S #1M.Tr 1,2차 LA 보통점검, 3차 LA교체, 1,3차 PT 보통점검, 2차 CB (6144) 특별점검","2017-09-25 09:30","2017-09-27 18:00","2017-09-25 09:30","2017-09-27 18:00","연속",null,null,null,201707100313,"-"]
[174,"대구","칠곡","서대구S/S #3 M.Tr A","서대구S/S #3M.Tr 휴전","서대구S/S #3M.Tr 1차 PT 교체, 3차 LA 교체, 2차 CB (6344) 특별점검","2017-09-18 09:30","2017-09-20 18:00","취소","취소","연속",null,null,null,201707100315,"-"]
[175,"대구","칠곡","북대구S/S #3M.Tr","345kV 북대구S/S #1Sh.R 설치공사","#1Sh.R 방호벽 콘크리트 타설관련 안전이격 확보","2017-09-11 10:00","2017-09-11 15:00","2017-09-11 10:00","2017-09-11 15:00","당일",null,null,null,201707260037,"-"]
[176,"대구","포항","선산신포항 T/L","기설 항공장애표시등 구조개선 및 피뢰기 설치공사","345kV 신포항-북대구T/L No.114~115, 147~148 가공지선 항공장애표시구 설치","2017-09-28 09:00","2017-09-28 18:00","취소","취소","당일",null,null,null,201707180048,"-"]
[177,"대구","포항","신월성N/P #2SA.Tr 1차 CB (7272)","신월성N/P #2SA.Tr 1차 7272 CB 보통점검","신월성N/P #2SA.Tr 1차 7272 CB 보통점검","2017-09-26 09:00","2017-09-26 18:00","2017-09-26 09:00","2017-09-26 18:00","당일",null,null,null,201707060154,"-"]
[178,"대구","포항","신포항S/S #1 M.Tr 1차 CB (7571)","신포항S/S #1 M.Tr 1차 7571 CB 동작시험","신포항S/S #1 M.Tr 1차 7571 CB 동작시험","2017-09-18 14:00","2017-09-18 18:00","2017-09-18 14:00","2017-09-18 18:00","당일",null,null,null,201707070146,"-"]
[179,"대구","포항","신포항S/S #4 M.Tr A","신포항S/S #4 M.Tr 7772, 6444 CB 동작시험","신포항S/S #4 M.Tr 7772, 6444 CB 동작시험","2017-09-21 09:00","2017-09-21 18:00","2017-09-21 09:00","2017-09-21 18:00","당일",null,null,null,201707070172,"-"]
[180,"대구","포항","신포항S/S 신영일T/L-TIE CB (7100)","신포항S/S 신영일T/L-TIE 7100 CB 동작시험","신포항S/S 신영일T/L-TIE 7100 CB 동작시험","2017-09-19 09:00","2017-09-19 14:00","2017-09-19 09:00","2017-09-19 14:00","당일",null,null,null,201707070148,"-"]
[181,"대구","포항","신포항S/S 신월성#1T/L-#1MTr 1차 CB (7500)","신포항S/S 신월성#1T/L-#1MTr 1차 7500 CB 동작시험","신포항S/S 신월성#1T/L-#1MTr 1차 7500 CB 동작시험","2017-09-18 09:00","2017-09-18 14:00","2017-09-18 09:00","2017-09-18 14:00","당일",null,null,null,201707070144,"-"]
[182,"대구","포항","신포항S/S 신포항-신영일T/L CB (7171)","신포항S/S 신포항-신영일T/L 7171 CB 동작시험","신포항S/S 신포항-신영일T/L 7171 CB 동작시험","2017-09-19 14:00","2017-09-19 18:00","2017-09-19 14:00","2017-09-19 18:00","당일",null,null,null,201707070150,"-"]
[183,"대구","포항","신포항S/S 신포항-청송T/L CB (7771)","신포항S/S 신포항-청송T/L 7771 CB 동작시험","신포항S/S 신포항-청송T/L 7771 CB 동작시험","2017-09-20 09:00","2017-09-20 14:00","2017-09-20 09:00","2017-09-20 14:00","당일",null,null,null,201707070156,"-"]
[184,"대구","포항","신포항S/S 신포항청송T/L-#4M 1차 CB (7700)","신포항S/S 신포항청송T/L-#4M 1차 7700 CB 동작시험","신포항S/S 신포항청송T/L-#4M 1차 7700 CB 동작시험","2017-09-20 14:00","2017-09-20 18:00","2017-09-20 14:00","2017-09-20 18:00","당일",null,null,null,201707070158,"-"]
[185,"대구","포항","신포항S/S 예비M.Tr","신포항S/S 예비M.Tr 부싱 설치","신포항S/S 예비M.Tr 부싱 설치","2017-09-11 09:00","2017-09-15 18:00","2017-09-11 09:00","2017-09-15 18:00","연속",null,null,null,201707060148,"-"]
[186,"대구","포항","신포항북대구 T/L","345kV 신포항-북대구T/L 피뢰기설치공사","345kV 신포항-북대구#2 T/L No149~No276 피뢰기 설치","2017-09-13 09:00","2017-09-27 18:00","취소","취소","연속",null,null,null,201707100104,"-"]
[187,"대구","포항","월성연락#2 T/L","월성연락#2 T/L EDS 설치","월성연락#2 T/L EDS 설치","2017-09-25 09:00","2017-09-29 18:00","2017-09-25 09:00","2017-09-29 18:00","연속",null,null,null,201707060153,"-"]
[188,"경북","구미","서대구선산#1 T/L","345kV 서대구-선산 등 11개T/L 송전선로용 피뢰기 설치공사","345kV 서대구-선산 #1 T/L 송전선로용 피뢰기 설치공사","2017-09-12 07:30","2017-09-12 18:00","2017-09-12 07:30","2017-09-12 18:00","당일",null,null,null,201707180025,"-"]
[189,"경북","구미","서대구선산#2 T/L","선산S/S 345KV 71BAY B/F PNL대체공사","--선산S/S 345KV 71BAY B/F PNL대체","2017-09-18 09:00","2017-09-22 18:00","2017-09-18 09:00","2017-09-22 18:00","연속",null,null,null,201707060188,"-"]
[190,"경북","구미","선산S/S #1 M.Tr A","선산S/S 345kV #1M.Tr 관련설비 점검","- 345kV M.Tr 초기점검 - 1차,2차,3차 LA초기점검 - 3차 GPT초기점검","2017-09-25 09:00","2017-09-26 18:00","2017-09-25 09:00","2017-09-26 18:00","연속",null,null,null,201707100203,"-"]
[191,"경북","구미","선산S/S #2 M.Tr A","선산S/S 345KV 71BAY B/F PNL대체공사","--선산S/S 345KV 71BAY B/F PNL대체","2017-09-18 09:00","2017-09-24 18:00","2017-09-18 09:00","2017-09-24 18:00","연속",null,null,null,201707060187,"-"]
[192,"경북","구미","선산S/S #3 M.Tr A","선산S/S 154kV 옥외철구 설비 GIS화 공사","GIS 기초 파일시공","2017-09-06 08:00","2017-09-10 18:00","2017-09-06 08:00","2017-09-10 18:00","연속",null,null,null,201707070321,"-"]
[193,"경북","구미","선산S/S #4 M.Tr A","선산S/S 154kV 옥외철구 설비 GIS화 공사","GIS 기초 파일시공","2017-09-01 08:00","2017-09-05 18:00","2017-09-01 08:00","2017-09-05 18:00","연속",null,null,null,201707070317,"-"]
[194,"경북","영주","(신)신영주S/S 345kV #1 BUS","345kV 신영주S/S STATCOM 설치공사","345kV 신영주S/S STATCOM 설치공사","2017-09-11 08:30","2017-09-15 18:00","취소","취소","연속",null,null,null,201707100514,"-"]
[195,"경북","영주","(신)신영주S/S 345kV #2 BUS","345kV 신영주S/S STATCOM 설치공사","345kV 신영주S/S STATCOM 설치공사","2017-09-18 08:30","2017-09-22 18:00","취소","취소","연속",null,null,null,201707100515,"-"]
[196,"경북","영주","(신)신영주S/S 신영주-안동CCT/L CB","2016-17 변전협력업체 총액공사","345kV 신영주S/S 신영주-안동 CC T/L CB(7471) 초기점검","2017-09-25 09:00","2017-09-25 14:00","2017-09-25 09:00","2017-09-25 14:00","당일",null,null,null,201707060213,"-"]
[197,"경북","영주","(신)신영주S/S 신영주-예천PP #1T/L CB","2016-17 변전협력업체 총액공사","345kV 신영주S/S 신영주-예천 PP #2 T/L CB(7671)초기점검","2017-09-27 09:00","2017-09-27 14:00","2017-09-27 09:00","2017-09-27 14:00","당일",null,null,null,201707060219,"-"]
[198,"경북","영주","(신)신영주S/S 신영주-예천PP #2T/L CB","2016-17 변전협력업체 총액공사","345kV 신영주S/S 신영주-예천 PP #2 T/L CB(7571) 초기점검","2017-09-26 09:00","2017-09-26 14:00","2017-09-26 09:00","2017-09-26 14:00","당일",null,null,null,201707060217,"-"]
[199,"경북","영주","(신)신영주-예천PP #1T/L-TIE CB","2016-17 변전협력업체 총액공사","345kV 신영주S/S 신영주-예천 PP #2 T/L CB(7600)초기점검","2017-09-27 14:00","2017-09-27 18:00","2017-09-27 14:00","2017-09-27 18:00","당일",null,null,null,201707060218,"-"]
[200,"경북","영주","(신)신영주-예천PP #2T/L-TIE CB","2016-17 변전협력업체 총액공사","345kV 신영주S/S 신영주-예천 PP #2 T/L CB(7500)초기점검","2017-09-26 14:00","2017-09-26 18:00","2017-09-26 14:00","2017-09-26 18:00","당일",null,null,null,201707060215,"-"]
[201,"경북","영주","신제천신영주#1 T/L","345kV 신영주S/S STATCOM 설치공사","345kV 신영주S/S STATCOM 설치공사","2017-09-11 08:30","2017-09-22 18:00","취소","취소","연속",null,null,null,201707100513,"-"]
[202,"경북","직할","신포항청송PP T/L","2017년도 상반기 안동P/O 362kV GIS 정밀점검공사","2017년도 상반기 안동P/O 362kV GIS 정밀점검공사","2017-09-18 09:00","2017-09-20 18:00","2017-09-18 09:00","2017-09-20 18:00","연속",null,null,null,201707030060,"-"]
[203,"경북","직할","안동복합S/Y 345kV #2 BUS","345kV 안동복합S/Y M.Tr 증설공사","345kV M.Tr * 2BANK 362kV GIS * 3CB 170kV GIS * 5CCT.","2017-09-11 10:00","2017-09-27 15:00","2017-09-11 10:00","2017-09-27 15:00","연속",null,null,null,201707200115,"-"]
[204,"경북","직할","안동복합S/Y 신영일-안동CC T/L CB (7371)","안동복합S/Y Gen 차단용 SPS 시험","안동복합S/Y Gen 차단용 SPS 시험(7371 접점 테스트)","2017-09-05 13:00","2017-09-05 14:00","2017-09-05 13:00","2017-09-05 14:00","당일",null,null,null,201707100115,"-"]
[205,"경북","직할","안동복합S/Y 신영일-안동CCT/L-TIE CB (7300)","안동복합S/Y Gen 차단용 SPS 시험","안동복합S/Y Gen 차단용 SPS 시험(7300 접점 테스트)","2017-09-05 14:00","2017-09-05 15:00","2017-09-05 14:00","2017-09-05 15:00","당일",null,null,null,201707100116,"-"]
[206,"경북","직할","안동복합S/Y 신영주-안동CC T/L CB (7271)","안동복합S/Y Gen 차단용 SPS 시험","안동복합S/Y Gen 차단용 SPS 시험(7271 접점 테스트)","2017-09-05 15:00","2017-09-05 16:00","2017-09-05 15:00","2017-09-05 16:00","당일",null,null,null,201707100117,"-"]
[207,"경북","직할","안동복합S/Y 신영주-안동CCT/L-TIE CB (7200)","안동복합S/Y Gen 차단용 SPS 시험","안동복합S/Y Gen 차단용 SPS 시험(7200 접점 테스트)","2017-09-05 16:00","2017-09-05 17:00","2017-09-05 16:00","2017-09-05 17:00","당일",null,null,null,201707100111,"-"]
[208,"부산울산","동부산","신양산S/S #4 M.Tr A","신양산S/S 345kV #4M.Tr 대체공사","1.신양산 #4M.Tr 대체 2. 7672GIS 보통점검 3. 6444GCB 보통점검 4.1,2차LA 대체","2017-09-11 09:00","2017-10-27 18:00","2017-09-11 09:00","2017-10-27 18:00","연속",null,null,null,201707100469,"-"]
[209,"부산울산","동부산","신양산고리NP#1 T/L","345kV 신양산-고리NPT/L 전선접속개소 전선교체공사","접속개소전선교체, 구간: 3~60호, 225,685m","2017-09-12 08:00","2017-09-26 18:00","2017-09-12 08:00","2017-09-26 18:00","연속",null,null,null,201707090001,"-"]
[210,"부산울산","북부산","북부산S/S #1 M.Tr A","345kV 북부산S/S 차단기용량대체공사","1. #1M.Tr LA 이설 및 7602 DS 철거(신 GIS 설치를 위한 공간 확보)","2017-09-23 08:00","2017-09-24 18:00","2017-09-23 08:00","2017-09-24 18:00","연속",null,null,null,201707070074,"-"]
[211,"부산울산","북부산","북부산S/S #4 M.Tr 1차 CB (7671)","345kV 북부산S/S 차단기용량대체공사","북부산S/S 신설GIS 설치공간을 확보(구. 7671 CB 철거)","2017-09-21 18:00","2018-05-09 18:00","2017-09-21 18:00","2018-05-09 18:00","연속",null,null,null,201707070087,"-"]
[212,"부산울산","북부산","북부산S/S #4 M.Tr 1차-#1 M.Tr 1차 CB (7600)","345kV 북부산S/S 차단기용량대체공사","북부산S/S 신설GIS 설치공간을 확보(구. 7600 CB 철거)","2017-09-21 18:00","2018-05-09 18:00","2017-09-21 18:00","2018-05-09 18:00","연속",null,null,null,201707070088,"-"]
[213,"부산울산","북부산","북부산S/S #4 M.Tr A","345kV 북부산S/S 차단기용량대체공사","1. #4M.Tr 인출변경(리드 분리 및 리드 연결) 2. PNL 이설 3. 시험가압 및 사용전검사","2017-09-13 08:00","2017-09-21 18:00","2017-09-13 08:00","2017-09-21 18:00","연속",null,null,null,201707070076,"-"]
[214,"부산울산","북부산","북부산S/S #4M.Tr 1차 CB(신) ((신)7872)","345kV 북부산S/S 차단기용량대체공사","1. #4M.Tr 인출변경(구 76BAY → 신 78BAY GIS) 2. PNL 이설 준공시험 3. 사용전검사","2017-09-16 09:00","2017-09-21 18:00","2017-09-16 09:00","2017-09-21 18:00","연속",null,null,null,201707070073,"-"]
[215,"부산울산","북부산","북부산S/S 345kV #4 Sh.R","345kV 북부산S/S 차단기용량대체공사","1. #4Sh.R 이설(Reactor 및 CB) 2. PNL 이설 3. 시험가압 및 사용전검사","2017-09-13 08:00","2017-10-24 18:00","2017-09-13 08:00","2017-10-24 18:00","연속",null,null,null,201707070078,"-"]
[216,"부산울산","북부산","북부산S/S 345kV #70 BUS","345kV 북부산S/S 차단기용량대체공사","1. #4Sh.R 모선 연결 리드 분리 및 붓싱(GIB) 철거","2017-09-13 08:00","2017-09-14 18:00","2017-09-13 08:00","2017-09-14 18:00","연속",null,null,null,201707070075,"-"]
[217,"부산울산","북부산","북부산S/S 345kV #75 BUS","345kV 북부산S/S 구내전력구 건설공사","구내 전력구 건설 터파기 가시설 설치 안전이격거리 확보","2017-09-23 08:00","2017-09-24 18:00","2017-09-23 08:00","2017-09-24 18:00","연속",null,null,null,201706230052,"-"]
[218,"부산울산","북부산","북부산S/S 서부산#3T/L-#4M.Tr 1차 CB(신) ((신)7800)","345kV 북부산S/S 차단기용량대체공사","1. #4M.Tr 인출변경(구 76BAY → 신 78BAY GIS) 2. PNL 이설 준공시험 3. 사용전검사","2017-09-16 09:00","2017-09-21 18:00","2017-09-16 09:00","2017-09-21 18:00","연속",null,null,null,201707070071,"-"]
[219,"부산울산","북부산","북부산신울산#1 T/L","345kV 북부산-신울산#1T/L 전선교체 및 피뢰기 설치공사","- 전선교체 : 8호-9호, 22호-27호,28호-36호 - 피뢰기설치 : 1호-110호","2017-09-09 07:00","2017-09-18 18:00","2017-09-09 07:00","2017-09-18 18:00","연속",null,null,null,201707070018,"-"]
[220,"부산울산","북부산","북부산신울산#2 T/L","345kV 북부산-신울산#2T/L 전선교체 및 피뢰기 설치공사","- 전선교체 : 8호-9호, 22호-27호,28호-36호 - 피뢰기설치 :1호-110호","2017-09-19 07:00","2017-09-28 18:00","2017-09-19 07:00","2017-09-28 18:00","연속",null,null,null,201707070016,"-"]
[221,"부산울산","서부산","서부산S/S #1 M.Tr A","서부산S/S 345kV #72 B/F(차단실패)및 #1M.Tr PNL","-서부산S/S 345kV #72BAY B/F(차단실패), #1M.TrPNL 교체 공사","2017-09-11 10:00","2017-09-24 18:00","2017-09-11 10:00","2017-09-24 18:00","연속",null,null,null,201707050011,"-"]
[222,"부산울산","서부산","서부산S/S #1,2 G/T-#3,4 G/T CB (7400)","서부산S/S #1,2 G/T-#3,4 G/T(7400) GIS 보통점검","서부산S/S #1,2 G/T-#3,4 G/T(7400) GIS 보통점검","2017-09-20 10:00","2017-09-20 18:00","2017-09-20 10:00","2017-09-20 18:00","당일",null,null,null,201707040099,"○"]
[223,"부산울산","서부산","서부산S/S #3,4 G/T CB (7472)","서부산S/S #3,4G/T(7472) GIS 보통점검","서부산S/S #3,4G/T(7472) GIS 보통점검","2017-09-19 10:00","2017-09-19 18:00","2017-09-19 10:00","2017-09-19 18:00","당일",null,null,null,201707040098,"○"]
[224,"부산울산","서부산","서부산S/S 서부산-북부산#3T/L CB (7371)","서부산S/S 서부산-북부산#3T/L CB(7371) 보통점검","서부산S/S 서부산-북부산#3T/L CB(7371) 보통점검","2017-09-28 10:00","2017-09-28 18:00","2017-09-28 10:00","2017-09-28 18:00","당일",null,null,null,201707040096,"-"]
[225,"부산울산","서부산","서부산북부산#2 T/L","서부산S/S 345kV #72 B/F(차단실패)및 #1M.Tr PNL","-서부산S/S 345kV #72BAY B/F(차단실패) 및 #1M.TrPNL 교체 공사","2017-09-11 10:00","2017-09-24 18:00","2017-09-11 10:00","2017-09-24 18:00","연속",null,null,null,201707050010,"-"]
[226,"부산울산","울산","신온산S/S #3 M.Tr 1차-TIE CB (7500)","345kV 신온산S/S S-OIL SW 증설공사","345kV 신온산S/S S-OIL SW 증설공사 - 345kV S-OIL #5,6T/L 상대단(S-OIL) 대국시험 및 최초가압","2017-09-19 09:00","2017-09-21 18:00","2017-09-26 09:00","2017-09-28 18:00","당일",null,null,null,201707050105,"-"]
[227,"부산울산","울산","신온산S/S 345kV #1 BUS","345kV 신온산S/S S-OIL SW 증설공사","345kV 신온산S/S S-OIL SW 증설공사 - 345kV S-OIL #5,6T/L 최초가압 (고객사 요청에 의해 48H 무부하 가압)","2017-09-20 18:00","2017-09-21 18:00","2017-09-27 18:00","2017-09-28 18:00","당일",null,null,null,201707050092,"-"]
[228,"부산울산","울산","신온산S/S S-OIL#5T/L 1차 CB (7172)","345kV 신온산S/S S-OIL SW 증설공사","345kV 신온산S/S S-OIL SW 증설공사 - 345kV S-OIL #5,6T/L 상대단(S-OIL) 대국시험 및 최초가압","2017-09-19 09:00","2017-09-21 18:00","2017-09-26 09:00","2017-09-28 18:00","당일",null,null,null,201707050110,"-"]
[229,"부산울산","울산","신온산S/S S-OIL#6T/L 1차 CB (7571)","345kV 신온산S/S S-OIL SW 증설공사","345kV 신온산S/S S-OIL SW 증설공사 - 345kV S-OIL #5,6T/L 상대단(S-OIL) 대국시험 및 최초가압","2017-09-19 09:00","2017-09-21 18:00","2017-09-26 09:00","2017-09-28 18:00","당일",null,null,null,201707050111,"-"]
[230,"부산울산","울산","신온산S/S 신울산-신온산#2T/L 1차TIE CB (7100)","345kV 신온산S/S S-OIL SW 증설공사","345kV 신온산S/S S-OIL SW 증설공사 - 345kV S-OIL #5,6T/L 상대단(S-OIL) 대국시험 및 최초가압","2017-09-19 09:00","2017-09-21 18:00","2017-09-26 09:00","2017-09-28 18:00","당일",null,null,null,201707050115,"-"]
[231,"부산울산","울산","신울산신온산#1 T/L","2016~2017년 울산전력지사 송전정비 협력회사 총액공사","3호 345kV 폴리머지지애자 발취","2017-09-14 08:00","2017-09-14 18:00","2017-09-14 08:00","2017-09-14 18:00","당일",null,null,null,201707070164,"-"]
[232,"부산울산","울산","신울산신온산#2 T/L","2016~2017년 울산전력지사 송전정비 협력회사 총액공사","14호 345kV 폴리머지지애자 발취","2017-09-15 08:00","2017-09-15 18:00","2017-09-15 08:00","2017-09-15 18:00","당일",null,null,null,201707070165,"-"]
[233,"부산울산","울산","신울산신온산#2 T/L","345kV 신온산S/S S-OIL SW 증설공사","345kV 신온산S/S S-OIL SW 증설공사 - 345kV S-OIL #5,6T/L 최초가압 (고객사 요청에 의해 48H 무부하 가압)","2017-09-20 18:00","2017-09-21 18:00","2017-09-27 18:00","2017-09-28 18:00","당일",null,null,null,201707050093,"-"]
[234,"부산울산","울산","울산C/C #3 M.Tr A","2016~17년 울산전력지사 변전협력회사 총액공사","1.울산C/C 345kV #3M.Tr 보통점검 2. SPS 회로구성","2017-09-16 08:00","2017-09-17 18:00","2017-09-16 08:00","2017-09-17 18:00","연속",null,null,null,201707100287,"-"]
[235,"부산울산","울산","울산C/C 북부산T/L-기력5호기 1차 CB (7500)","2016~17년 울산전력지사 변전협력회사 총액공사","SPS 회로구성 관련 울산C/C 7500CB 접점확인","2017-09-12 11:00","2017-09-12 13:00","2017-09-12 11:00","2017-09-12 13:00","당일",null,null,null,201707100272,"-"]
[236,"부산울산","울산","울산C/C 북부산-울산TPT/L CB (7571)","2016~17년 울산전력지사 변전협력회사 총액공사","SPS 회로구성 관련 울산C/C 7571CB 접점확인","2017-09-12 09:00","2017-09-12 11:00","2017-09-12 09:00","2017-09-12 11:00","당일",null,null,null,201707100270,"-"]
[237,"부산울산","울산","울산C/C 신온산T/L-기력6호기 1차 CB (7600)","2016~17년 울산전력지사 변전협력회사 총액공사","SPS 회로구성 관련 울산C/C 7600CB 접점확인","2017-09-12 16:00","2017-09-12 18:00","2017-09-12 16:00","2017-09-12 18:00","당일",null,null,null,201707100276,"-"]
[238,"부산울산","울산","울산C/C 신온산-울산TPT/L CB (7671)","2016~17년 울산전력지사 변전협력회사 총액공사","SPS 회로구성 관련 울산C/C 7671CB 접점확인","2017-09-12 14:00","2017-09-12 16:00","2017-09-12 14:00","2017-09-12 16:00","당일",null,null,null,201707100274,"-"]
[239,"부산울산","울산","울주월성NP#1 T/L","2016~17년 울산전력지사 변전협력회사 총액공사","울주S/S 345kV 울주-월성N/P#1T/L 1st Main 21계전기 불량조치 (부산울산본부 보호제어과 계전기 시험)","2017-09-14 09:00","2017-09-14 18:00","2017-09-14 09:00","2017-09-14 18:00","당일",null,null,null,201707130061,"-"]
[240,"경남","직할","신김해S/S #4 M.Tr A","신김해S/S #4M.Tr B상 유순환펌프 및 OLTC 계전기 교체","신김해S/S #4M.Tr B상 유순환펌프 및 OLTC 계전기 교체","2017-09-16 07:00","2017-09-17 18:00","2017-09-16 07:00","2017-09-17 18:00","연속",null,null,null,201707250041,"-"]
[241,"경남","직할","신김해S/S 신김해#1T/L-삼해#2T/L CB (7200)","신김해S/S 신김해#1T/L-삼해#2T/L 7200 CB 보통점검","신김해S/S 신김해#1T/L-삼해#2T/L 7200 CB 보통점검","2017-09-14 09:30","2017-09-14 17:30","2017-09-14 09:30","2017-09-14 17:30","당일",null,null,null,201707050029,"-"]
[242,"경남","직할","신김해S/S 신녹산#2T/L-#4M.Tr 1차 CB (7800)","신김해S/S 신녹산#2T/L-#4M.Tr 1차 7800 CB 보통점검","신김해S/S 신녹산#2T/L-#4M.Tr 1차 7800 CB 보통점검","2017-09-15 09:30","2017-09-15 17:30","2017-09-15 09:30","2017-09-15 17:30","당일",null,null,null,201707050030,"-"]
[243,"경남","직할","신김해북부산#1 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선교체(신김해-북부산T/L 59~62호 등 16개 구간)","2017-09-21 07:00","2017-10-18 18:00","2017-09-13 07:00","2017-10-11 18:00","연속",null,null,null,201707060129,"-"]
[244,"경남","직할","신김해북부산#2 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선교체(신김해-북부산T/L 59~62호 등 7개 구간)","2017-09-09 07:00","2017-09-20 18:00","2017-10-12 07:00","2017-10-23 18:00","연속",null,null,null,201707060125,"-"]
[245,"경남","직할","신마산신김해#1 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선 교체공사(안전거리 확보 휴전)","2017-09-20 07:00","2017-09-20 18:00","2017-10-23 07:00","2017-10-23 18:00","당일",null,null,null,201707060128,"-"]
[246,"경남","진주","의령S/S #3 M.Tr A","의령S/S #3 M.Tr (A,B,C) 초기점검","의령S/S #3 M.Tr (A,B,C) 초기점검 -#3M.Tr 1,2차 GIS(7872,6344) 초기점검[병행]","2017-09-28 09:00","2017-09-29 18:00","2017-09-28 09:00","2017-09-29 18:00","연속",null,null,null,201707030027,"-"]
[247,"경남","진주","의령산청양수#2 T/L","345kV 의령-산청양수#2T/L 보호반 대체","345kV 의령-산청양수#2T/L 보호반 대체 - CB(7200)A,B,C상 러버히터 설치[병행]","2017-09-11 09:00","2017-09-29 18:00","2017-09-11 09:00","2017-09-29 18:00","연속",null,null,null,201707030028,"-"]
[248,"경남","진주","하동T/P TIE-#7 M.Tr 1차 CB (7700)","하동T/P TIE-#7 M.Tr 1차 CB(7700) 정밀점검","하동T/P TIE-#7 M.Tr 1차 CB(7700) 정밀점검","2017-09-12 09:30","2017-09-14 18:30","2017-09-12 09:30","2017-09-14 18:30","연속",null,null,null,201707030017,"-"]
[249,"경남","통영","신고성S/S #1 M.Tr A","신고성S/S 345kV #1M.Tr 정밀점검","신고성S/S 345kV #1M.Tr 정밀점검 (병행)신고성S/S 345kV #1M.Tr 1차 CB 보통점검 345kV 신고성#1T/L-#1M.Tr 1차 CB 보통점검 #1M.Tr 2차 GIS 보통점검,3차 LA,PT 보통점검 3차모선 점검,지지애자닦기","2017-09-25 09:30","2017-10-01 18:30","2017-09-25 09:30","2017-10-01 18:30","연속",null,null,null,201707040192,"-"]
[250,"경남","통영","신고성S/S #2 M.Tr A","신고성S/S 345kV #2M.Tr 및 OLTC 정밀점검","신고성S/S 345kV #2M.Tr 및 OLTC 정밀점검 (병행)#2M.Tr 2차 GIS 보통점검,3차 LA,PT 보통점검 3차모선 점검,지지애자닦기","2017-09-18 09:30","2017-09-24 18:30","2017-09-18 09:30","2017-09-24 18:30","연속",null,null,null,201707040191,"-"]
[251,"경남","통영","신고성S/S 신고성-삼천포화력#1T/L CB (7C72)","신고성S/S 345kV 신고성-삼천포화력#1T/L CB(7C72)보통점검","신고성S/S 345kV 신고성-삼천포화력#1T/L CB(7C72)보통점검","2017-09-28 09:30","2017-09-28 18:30","2017-09-28 09:30","2017-09-28 18:30","당일",null,null,null,201707040186,"-"]
[252,"경남","통영","신고성S/S 신고성-삼천포화력#2T/L CB (7D72)","신고성S/S 345kV 신고성-삼천포화력#2T/L CB(7D72)보통점검","신고성S/S 345kV 신고성-삼천포화력#2T/L(7D72)CB보통점검","2017-09-21 09:30","2017-09-21 18:30","2017-09-21 09:30","2017-09-21 18:30","당일",null,null,null,201707040187,"-"]
[253,"경남","함안","신마산신김해#2 T/L","345kV 신마산-신김해 #2T/L 피뢰기 설치공사","송전선로용 피뢰기 설치 : 신마산-신김해 #2T/L 30~97호 (68기)","2017-09-03 08:00","2017-09-10 18:30","2017-09-03 08:00","2017-09-10 18:30","매일",null,null,null,201707170150,"-"]
[254,"경남","함안","의령신마산#1 T/L","345kV 의령-신마산 #1T/L 피뢰기 설치공사","송전선로용 피뢰기 설치 : 의령-신마산 #1T/L 1~115호 (115기)","2017-09-11 08:00","2017-09-25 18:30","2017-09-11 08:00","2017-09-25 18:30","매일",null,null,null,201707040033,"-"]
[255,"광주전남","광주","신강진광양#2T/L","피뢰기 설치공사","피뢰기 설치공사","2017-09-16 09:00","2017-09-20 18:00","2017-09-16 09:00","2017-09-20 18:00","매일"]

{"sheet":"154송부","index":2,"n_rows":420,"n_cols":16,"rows_kept":420,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 9월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","미금광장 T/L","17년 성동P/O 변전협력회사 총액공사","170kV GIS 하자점검 (광장S/S 미금광장T/L)","2017-09-28 10:00","2017-09-28 17:00","2017-09-28T10:00:00","2017-09-28T17:00:00","당일",null,null,null,201707120016,"-"]
[2,"서울","성동","성동S/S 60-61-0 SEC CB","17년 성동P/O 변전협력회사 총액공사","170kV GIS 보통점검 (성동S/S 154kV 60-61 SEC)","2017-09-20 10:00","2017-09-20 17:00","2017-09-20T10:00:00","2017-09-20T17:00:00","당일",null,null,null,201707100161,"-"]
[3,"서울","성동","성동S/S 65-66-0 SEC CB","17년 성동P/O 변전협력회사 총액공사","170kV GIS 보통점검 (성동S/S 154kV 65-66 SEC)","2017-09-21 10:00","2017-09-21 17:00","2017-09-21T10:00:00","2017-09-21T17:00:00","당일",null,null,null,201707100163,"-"]
[4,"서울","성동","성동휘경#1 T/L","17년 성동P/O 변전협력회사 총액공사","170kV GIS 보통점검 (성동S/S 성동휘경#1T/L)","2017-09-18 10:00","2017-09-18 17:00","2017-09-18T10:00:00","2017-09-18T17:00:00","당일",null,null,null,201707100158,"-"]
[5,"서울","성동","양주쌍문#1 T/L","17년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사 (쌍문S/S 양주쌍문#1T/L)","2017-09-04 09:30","2017-09-05 17:30","2017-09-04T09:30:00","2017-09-05T17:30:00","연속",null,null,null,201707100146,"-"]
[6,"서울","성동","화양성수 T/L","17년 성동P/O 변전협력회사 총액공사","장기사용 보호배전반 교체공사 (화양,성수S/S 화양성수T/L)","2017-09-11 10:00","2017-09-14 17:00","2017-09-11T10:00:00","2017-09-14T17:00:00","연속",null,null,null,201707100152,"-"]
[7,"서울","중부","양주은평#1 T/L","2017년 중부P/O 170kV GIS 정밀점검공사","양주은평#1T/L(617)Bay GIS 정밀점검","2017-09-11 08:00","2017-09-13 18:00","2017-09-11T08:00:00","2017-09-13T18:00:00","연속",null,null,null,201707100470,"-"]
[8,"서울","중부","양주은평#2 T/L","2017년 중부P/O 170kV GIS 정밀점검공사","양주은평#2T/L(627)Bay GIS 정밀점검","2017-09-06 08:00","2017-09-08 18:00","2017-09-06T08:00:00","2017-09-08T18:00:00","연속",null,null,null,201707100471,"-"]
[9,"서울","직할","불광서대문#2 T/L","17년 직할 변전협력 총액공사","170kV GIS 및 LIne PT 보통점검","2017-09-01 10:00","2017-09-01 18:00","취소","취소","당일",null,null,null,201707070340,"-"]
[10,"서울","직할","서소문S/S 154kV #1 BUS","17년 직할 변전협력 총액공사","154kV BUS PT 초기점검","2017-09-01 10:00","2017-09-01 14:00","2017-09-01T10:00:00","2017-09-01T14:00:00","당일",null,null,null,201707070341,"-"]
[11,"서울","직할","서소문S/S 154kV #2 BUS","17년 직할 변전협력 총액공사","154kV BUS PT 초기점검","2017-09-01 14:00","2017-09-01 18:00","2017-09-01T14:00:00","2017-09-01T18:00:00","당일",null,null,null,201707070342,"-"]
[12,"서울","직할","옥인운니#1 T/L","154kV 옥인 및 운니S/S 인출T/L 교체공사","1. 사 업 명 : 154kV 옥인 및 운니S/S 인출T/L 교체공사 2. 사업목적 : 옥인 및 운니변전소 화재 및 대형 재난사고 예방 3. 사업개요 ○ 사업구간 : 옥인S/S ∼ 옥인인출전력구, 운니S/S 운니인출전력구 ○ 사업내용 - 철거 : 154kV OF 2000㎟ 4C, OF 1200㎟ 4C 총길이1.4㎞ - 신설 : 154kV XLPE 2000㎟ 4C, XLPE 1200㎟ 4C 총길이1.4㎞","2017-09-04 09:20","2017-10-19 18:00","2017-09-04T09:00:00","2017-10-19T18:00:00","연속",null,null,null,201707070062,"-"]
[13,"서울","직할","종로서소문 T/L","17년 직할 변전협력 총액공사","17년 장기무동작 차단기 조작시험","2017-09-13 10:00","2017-09-13 18:00","2017-09-13T10:00:00","2017-09-13T18:00:00","당일",null,null,null,201707070392,"-"]
[14,"남서울","강남","동빙고반포#1 T/L","170kV GIS 조작시험 및 개폐타임 측정 - 변전협력","동빙고-반포#1T/L GIS 조작시험 및 개폐타임 측정","2017-09-22 10:00","2017-09-22 14:00","2017-09-22T10:00:00","2017-09-22T14:00:00","당일",null,null,null,201707170118,"-"]
[15,"남서울","강남","동빙고반포#2 T/L","170kV GIS 조작시험 및 개폐타임 측정 - 변전협력","동빙고-반포#2T/L GIS 조작시험 및 개폐타임 측정","2017-09-22 14:00","2017-09-22 18:00","2017-09-22T14:00:00","2017-09-22T18:00:00","당일",null,null,null,201707170119,"-"]
[16,"남서울","강남","신양재신사#1 T/L","170kV GIS 조작시험 및 개폐타임 측정 - 변전협력","신양재-신사#1T/L GIS 조작시험 및 개폐타임 측정(신양재,신사S/S)","2017-09-20 10:00","2017-09-20 14:00","취소","취소","당일",null,null,null,201707170115,"-"]
[17,"남서울","강남","신양재신사#2 T/L","170kV GIS 조작시험 및 개폐타임 측정 - 변전협력","신양재-신사#2T/L GIS 조작시험 및 개폐타임 측정(신양재,신사S/S)","2017-09-20 14:00","2017-09-20 18:00","취소","취소","당일",null,null,null,201707170116,"-"]
[18,"남서울","강남","신양재신사#3 T/L","170kV GIS 조작시험 및 개폐타임 측정 - 변전협력","신양재-신사#3T/L GIS 조작시험 및 개폐타임 측정(신양재,신사S/S)","2017-09-21 10:00","2017-09-21 14:00","취소","취소","당일",null,null,null,201707170117,"-"]
[19,"남서울","강남","역삼대치#1 T/L","154kV 논일-역삼, 논현-대치 지중T/L 건설공사","1. 구간 : 154kV 논일S/S,논현S/S~154kV 역삼대치T/L 분기점 2. 선종/회선길이 : XLPE1200,2C-3.7km(논일-역삼),2C-3km(논현-대치)","2017-09-04 09:00","2017-11-22 18:00","2017-09-04T09:00:00","2017-11-22T18:00:00","연속",null,null,null,201707110126,"-"]
[20,"남서울","강남","역삼대치#2 T/L","154kV 논일-역삼,논현-대치 지중T/L 건설공사","1. 구간 : 154kV 논일S/S,논현S/S~154kV 역삼대치T/L 분기점 2. 선종/회선길이 : XLPE1200,2C-3.7km(논일-역삼),2C-3km(논현-대치)","2017-09-04 09:00","2017-11-22 18:00","2017-09-04T09:00:00","2017-11-22T18:00:00","연속",null,null,null,201707110127,"-"]
[21,"남서울","동서울","가락수서#1 T/L","송전선로 보호반 교체","송전선로 보호반 교체(가락,수서) 차단기 조작시험","2017-09-11 09:00","2017-09-12 18:00","2017-09-11T09:00:00","2017-09-12T18:00:00","연속",null,null,null,201707180031,"-"]
[22,"남서울","동서울","가락수서#2 T/L","송전선로 보호반 교체","송전선로 보호반 교체(가락,수서) 차단기 조작시험","2017-09-13 09:00","2017-09-14 18:00","2017-09-13T09:00:00","2017-09-14T18:00:00","연속",null,null,null,201707180032,"-"]
[23,"남서울","동서울","강남-대치#1 T/L","강남전력구 감시시스템 설치공사","강남전력구 감시시스템 설치공사 관련 강남-대치#1,2T/L 유압데이터 취득센서 부착","2017-09-01 09:00","2017-09-01 13:00","2017-09-01T09:00:00","2017-09-01T13:00:00","당일",null,null,null,201707110092,"-"]
[24,"남서울","동서울","강남-대치#2 T/L","강남전력구 감시시스템 설치공사","강남전력구 감시시스템 설치공사 관련 강남-대치#1,2T/L 유압데이터 취득센서 부착","2017-09-01 13:00","2017-09-01 18:00","2017-09-01T13:00:00","2017-09-01T18:00:00","당일",null,null,null,201707110093,"-"]
[25,"남서울","동서울","동서울가락#1 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2017-09-29 10:00","2017-09-29 14:00","2017-09-29T10:00:00","2017-09-29T14:00:00","당일",null,null,null,201707250038,"-"]
[26,"남서울","동서울","동서울가락#2 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2017-09-29 14:00","2017-09-29 18:00","2017-09-29T14:00:00","2017-09-29T18:00:00","당일",null,null,null,201707250039,"-"]
[27,"남서울","동서울","동서울서종#1 T/L","170kV GCB 조작시험","170kV GCB 조작시험","2017-09-15 10:00","2017-09-15 12:00","취소","취소","당일",null,null,null,201707180036,"-"]
[28,"남서울","동서울","동서울서종#2 T/L","170kV GCB 조작시험","170kV GCB 조작시험","2017-09-15 13:00","2017-09-15 15:00","취소","취소","당일",null,null,null,201707180037,"-"]
[29,"남서울","동서울","동서울송파#1 T/L","송전선로 보호반 교체","송전선로 보호반 교체","2017-09-18 09:00","2017-09-19 18:00","2017-09-18T09:00:00","2017-09-19T18:00:00","연속",null,null,null,201707180033,"-"]
[30,"남서울","동서울","동서울송파#2 T/L","송전선로 보호반 교체","송전선로 보호반 교체","2017-09-20 09:00","2017-09-21 18:00","2017-09-20T09:00:00","2017-09-21T18:00:00","연속",null,null,null,201707180034,"-"]
[31,"남서울","동서울","동서울신장#1 T/L","170kV GCB 조작시험","170kV GCB 조작시험","2017-09-22 10:00","2017-09-22 14:00","2017-09-22T10:00:00","2017-09-22T14:00:00","당일",null,null,null,201707180038,"-"]
[32,"남서울","동서울","동서울신장#2 T/L","170kV GCB 조작시험","170kV GCB 조작시험","2017-09-22 14:00","2017-09-22 18:00","2017-09-22T14:00:00","2017-09-22T18:00:00","당일",null,null,null,201707180039,"-"]
[33,"남서울","영등포","독산대방#1 T/L","154kV T/L 보호반 교체(독산대방#1 T/L)","154kV T/L 보호반 교체(독산대방#1 T/L)","2017-09-25 09:00","2017-09-27 14:00","2017-09-25T09:00:00","2017-09-27T14:00:00","연속",null,null,null,201707170182,"-"]
[34,"남서울","영등포","독산대방#2 T/L","154kV T/L 보호반 교체(독산대방#2 T/L)","154kV T/L 보호반 교체(독산대방#2 T/L)","2017-09-27 14:00","2017-09-29 18:00","2017-09-27T14:00:00","2017-09-29T18:00:00","연속",null,null,null,201707170183,"-"]
[35,"남서울","영등포","시흥독산#1 T/L","154kV T/L 보호반 교체(시흥독산#1 T/L)","154kV T/L 보호반 교체(시흥독산#1 T/L)","2017-09-11 09:00","2017-09-13 14:00","2017-09-11T09:00:00","2017-09-13T14:00:00","연속",null,null,null,201707170180,"-"]
[36,"남서울","영등포","시흥독산#2 T/L","154kV T/L 보호반 교체(시흥독산#2 T/L)","154kV T/L 보호반 교체(시흥독산#2 T/L)","2017-09-13 14:00","2017-09-15 18:00","2017-09-13T14:00:00","2017-09-15T18:00:00","연속",null,null,null,201707170181,"-"]
[37,"남서울","영등포","영서S/S 154kV #60 BUS","영서S/S GIS화 공사 제어케이블 덕트시공","영서S/S GIS화 공사 제어케이블 덕트시공","2017-09-09 08:00","2017-09-09 18:00","2017-09-09T08:00:00","2017-09-09T18:00:00","당일",null,null,null,201707200040,"-"]
[38,"남서울","영등포","천왕구로#1 T/L","2017-2018 영서전력지사 지중송전설비 위탁정비공사","- 시스전압제한기(SVL) 보강공사","2017-09-25 15:00","2017-09-27 14:00","2017-09-25T15:00:00","2017-09-27T14:00:00","연속",null,null,null,201707170019,"-"]
[39,"남서울","영등포","천왕구로#2 T/L","2017-2018 영서전력지사 지중송전설비 위탁정비공사","- 시스전압제한기(SVL) 보강공사","2017-09-27 15:00","2017-09-29 14:00","2017-09-27T15:00:00","2017-09-29T14:00:00","연속",null,null,null,201707170020,"-"]
[40,"남서울","직할","신길S/S 154kV #1 BUS TIE CB","신길S/S BUS-TIE(6100) 조작 시험 및 개폐타임측정","신길S/S BUS-TIE(6100) 조작 시험 및 개폐타임측정","2017-09-18 10:00","2017-09-18 18:00","2017-09-18T10:00:00","2017-09-18T18:00:00","당일",null,null,null,201707170090,"-"]
[41,"인천","김포","경서양촌#1 T/L","'16-17년도 가공송전 협력공사(SB댐퍼 설치)","전력선 SB댐퍼 설치","2017-09-10 08:00","2017-09-11 18:00","2017-09-10T08:00:00","2017-09-11T18:00:00","매일",null,null,null,201707140079,"-"]
[42,"인천","김포","경서양촌#2 T/L","'16-17년도 가공송전 협력공사(SB댐퍼 설치, 피뢰기 설치)","전력선 SB댐퍼 설치 및 피뢰기 설치","2017-09-12 08:00","2017-09-13 18:00","2017-09-12T08:00:00","2017-09-13T18:00:00","매일",null,null,null,201707140080,"-"]
[43,"인천","김포","신김포양곡#2 T/L","신김포S/S 154kV 신김포양곡#2 T/L GIS 보통점검","신김포S/S 154kV 신김포양곡#2 T/L GIS 보통점검","2017-09-22 10:00","2017-09-22 18:00","2017-09-22T10:00:00","2017-09-22T18:00:00","당일",null,null,null,201707130108,"-"]
[44,"인천","김포","신김포장기#2 T/L","154kV 장기S/S #4M.Tr 증설공사","154kV M.Tr 1Bank 설치 154kV GIS 1CCT 설치 22.9kV GIS 1CCT 설치 기타 부대설비 설치","2017-09-26 10:00","2017-09-26 18:00","2017-09-26T10:00:00","2017-09-26T18:00:00","당일",null,null,null,201707130046,"-"]
[45,"인천","김포","신김포장기#2 T/L","154kV 장기S/S #4M.Tr 증설공사","154kV M.Tr 1Bank 설치 154kV GIS 1CCT 설치 22.9kV GIS 1CCT 설치 기타 부대설비 설치","2017-09-21 10:00","2017-09-21 18:00","2017-09-21T10:00:00","2017-09-21T18:00:00","당일",null,null,null,201707130045,"-"]
[46,"인천","김포","양촌양곡#2 T/L","'16-17년도 가공송전 협력공사(피뢰기 설치)","피뢰기 설치","2017-09-09 08:00","2017-09-09 18:00","2017-09-09T08:00:00","2017-09-09T18:00:00","당일",null,null,null,201707140082,"-"]
[47,"인천","김포","장기S/S 154kV #1 BUS","154kV 장기S/S #4M.Tr 증설공사","154kV M.Tr 1Bank 설치 154kV GIS 1CCT 설치 22.9kV GIS 1CCT 설치 기타 부대설비 설치","2017-09-21 10:00","2017-09-26 10:00","2017-09-21T10:00:00","2017-09-26T10:00:00","연속",null,null,null,201707130049,"-"]
[48,"인천","김포","장기S/S 154kV #2 BUS","154kV 장기S/S #4M.Tr 증설공사","154kV M.Tr 1Bank 설치 154kV GIS 1CCT 설치 22.9kV GIS 1CCT 설치 기타 부대설비 설치","2017-09-26 10:00","2017-09-29 16:00","2017-09-26T10:00:00","2017-09-29T16:00:00","연속",null,null,null,201707130050,"-"]
[49,"인천","시흥","도림오봉 T/L","154kV 신시흥-남동T/L 전력선교체 공사","154kV 신시흥-남동T/L 전력선교체 공사 -No.28~29(병가구간)","2017-09-01 08:00","2017-09-02 18:00","2017-09-01T08:00:00","2017-09-02T18:00:00","연속",null,null,null,201707110214,"-"]
[50,"인천","시흥","동춘송도#2 T/L","154kV 동송도분기 지중T/L 건설공사","공사목적 : 송도지역 전력계통보강 공사구간 : 154kV 동춘-송도T/L M/H#8~M/H#9(2ㅠ분기) 선종 및 규격 : 154KV XLPE 2000SQ 회선수 및 길이 : 4회선, 2.5KM","2017-09-01 09:30","2017-09-30 18:00","2017-09-01T09:30:00","2017-09-30T18:00:00","연속",null,null,null,201707100208,"-"]
[51,"인천","시흥","북시화S/S 154kV #1 BUS","북시화S/S 170kV GIS 대체공사 2차","170 GIS 기존 BUS-TIE 철거 및 신시흥-북시화#1TL, #1M.Tr 1차 대체","2017-09-17 13:00","2017-09-23 15:00","2017-09-17T13:00:00","2017-09-23T15:00:00","연속",null,null,null,201707060078,"-"]
[52,"인천","시흥","북시화S/S 154kV #1 BUS","북시화S/S 170kV GIS 대체공사 1차","170kV GIS 신규 BUS-TIE 설치","2017-09-15 08:00","2017-09-16 08:00","2017-09-15T08:00:00","2017-09-16T08:00:00","연속",null,null,null,201707060072,"-"]
[53,"인천","시흥","북시화S/S 154kV #1 BUS","북시화S/S 170kV GIS 대체공사 2차","170 GIS 기존 BUS-TIE 철거 및 신시흥-북시화#1TL, #1M.Tr 1차 대체","2017-09-29 08:00","2017-09-30 08:00","2017-09-29T08:00:00","2017-09-30T08:00:00","연속",null,null,null,201707060086,"-"]
[54,"인천","시흥","북시화S/S 154kV #1 BUS","북시화S/S 170kV GIS 대체공사 1차","170kV GIS 신규 BUS-TIE 설치","2017-09-09 08:00","2017-09-11 15:00","2017-09-09T08:00:00","2017-09-11T15:00:00","연속",null,null,null,201707060065,"-"]
[55,"인천","시흥","북시화S/S 154kV #1 BUS TIE CB","북시화S/S 170kV GIS 대체공사 1차","170kV GIS 신규 BUS-TIE 설치","2017-09-09 08:00","2017-09-16 08:00","2017-09-09T08:00:00","2017-09-16T08:00:00","연속",null,null,null,201707060067,"-"]
[56,"인천","시흥","북시화S/S 154kV #2 BUS","북시화S/S 170kV GIS 대체공사 2차","170 GIS 기존 BUS-TIE 철거 및 신시흥-북시화#1TL, #1M.Tr 1차 대체","2017-09-16 08:00","2017-09-17 13:00","2017-09-16T08:00:00","2017-09-17T13:00:00","연속",null,null,null,201707060076,"-"]
[57,"인천","시흥","북시화S/S 154kV #2 BUS","북시화S/S 170kV GIS 대체공사 1차","170kV GIS 신규 BUS-TIE 설치","2017-09-11 15:00","2017-09-15 08:00","2017-09-11T15:00:00","2017-09-15T08:00:00","연속",null,null,null,201707060068,"-"]
[58,"인천","시흥","북시화S/S 154kV #2 BUS","북시화S/S 170kV GIS 대체공사 2차","170 GIS 기존 BUS-TIE 철거 및 신시흥-북시화#1TL, #1M.Tr 1차 대체","2017-09-23 15:00","2017-09-29 08:00","2017-09-23T15:00:00","2017-09-29T08:00:00","연속",null,null,null,201707060083,"-"]
[59,"인천","시흥","북시화서시화#1 T/L","북시화S/S 170kV GIS 대체공사 2차","170GIS 기존 BUS-TIE 철거 및 신시흥-북시화#1TL, #1M.Tr 대체","2017-09-28 08:00","2017-09-29 08:00","2017-09-28T08:00:00","2017-09-29T08:00:00","연속",null,null,null,201707060094,"-"]
[60,"인천","시흥","북시화서시화#1 T/L","북시화S/S 170kV GIS 대체공사 2차","170GIS 기존 BUS-TIE 철거 및 신시흥-북시화#1TL, #1M.Tr 대체","2017-09-22 15:00","2017-09-23 15:00","2017-09-22T15:00:00","2017-09-23T15:00:00","연속",null,null,null,201707060088,"-"]
[61,"인천","시흥","북시화서시화#1 T/L","북시화S/S 170kV GIS 대체공사 1차","170kV GIS 신규 BUS-TIE 설치","2017-09-14 08:00","2017-09-15 08:00","2017-09-14T08:00:00","2017-09-15T08:00:00","연속",null,null,null,201707060069,"-"]
[62,"인천","시흥","소래S/S 154kV #2 BUS","소래S/S #3M.Tr 1차 GIS 정밀점검","소래S/S #3M.Tr 1차 GIS 정밀점검","2017-09-15 16:00","2017-09-15 18:00","2017-09-15T16:00:00","2017-09-15T18:00:00","연속",null,null,null,201707140101,"-"]
[63,"인천","시흥","신시흥남동#1 T/L","154kV 신시흥-남동T/L 피뢰기 설치 및 스페이서 간격조정 공사","154kV 신시흥-남동 등 2개T/L 피뢰기 설치 및 스페이서 간격조정 공사","2017-09-06 08:00","2017-09-10 18:00","2017-09-06T08:00:00","2017-09-10T18:00:00","연속",null,null,null,201707110210,"-"]
[64,"인천","시흥","신시흥남동#2 T/L","154kV 신시흥-남동T/L 전력선교체 및 스페이서 간격조정 공사","154kV 신시흥-남동T/L 전력선교체 및 스페이서 간격조정 공사","2017-09-01 08:00","2017-09-05 18:00","2017-09-01T08:00:00","2017-09-05T18:00:00","연속",null,null,null,201707110208,"-"]
[65,"인천","시흥","신시흥도림 T/L","154kV 신시흥-도림T/L 스페이서 간격조정 및 SB댐퍼설치 공사","154kV 신시흥-도림T/L 스페이서 간격조정 및 SB댐퍼설치 공사","2017-09-03 08:00","2017-09-05 18:00","2017-09-03T08:00:00","2017-09-05T18:00:00","연속",null,null,null,201707110218,"-"]
[66,"인천","시흥","신시흥북시화#1 T/L","154kV 신시흥북시화#1T/L 스페이서 간격조정 및 SB댐퍼 설치공사","154kV 신시흥북시화#1T/L 스페이서 간격조정 및 SB댐퍼 설치공사(9기)","2017-09-18 09:00","2017-09-19 18:00","2017-09-18T09:00:00","2017-09-19T18:00:00","연속",null,null,null,201707110201,"-"]
[67,"인천","시흥","신시흥북시화#1 T/L","북시화S/S 170kV GIS 대체공사 2차","170 GIS 기존 BUS-TIE 철거 및 신시흥-북시화#1TL, #1M.Tr 1차 대체","2017-09-16 08:00","2017-09-30 08:00","2017-09-16T08:00:00","2017-09-30T08:00:00","연속",null,null,null,201707060093,"-"]
[68,"인천","시흥","신시흥시화#1 T/L","154kV 신시흥시화#1T/L 스페이서 간격조정 및 SB댐퍼 설치공사","154kV 신시흥시화#1T/L 스페이서 간격조정 및 SB댐퍼 설치공사(25기)","2017-09-18 09:00","2017-09-21 18:00","2017-09-18T09:00:00","2017-09-21T18:00:00","연속",null,null,null,201707110203,"-"]
[69,"인천","시흥","신시흥오봉 T/L","154kV 신시흥-오봉T/L 피뢰기 설치 및 스페이서 간격조정 공사","154kV 신시흥-오봉T/L 피뢰기 설치 및 스페이서 간격조정 공사","2017-09-06 08:00","2017-09-10 18:00","2017-09-06T08:00:00","2017-09-10T18:00:00","연속",null,null,null,201707110221,"-"]
[70,"인천","인천","관교만수 T/L","154kV 만수S/S 인출구간 OF케이블 선종교체공사","단일계통 옥내형GIS변전소 내 OF케이블 선종교체를 통한 화재 및 정전고장 예방","2017-09-11 09:00","2017-09-28 18:00","2017-09-11T09:00:00","2017-09-28T18:00:00","연속",null,null,null,201707110237,"-"]
[71,"인천","인천","서인천C/C #4 G.Tr 1차 CB","서인천CC 170kV #4G.TR GIS 보통점검(6433)","서인천CC 170kV #4G.TR GIS 보통점검(6433) - 발전기 정지계획관련 병행 공사","2017-09-04 09:00","2017-09-04 18:00","2017-09-04T09:00:00","2017-09-04T18:00:00","당일",null,null,null,201707130113,"-"]
[72,"인천","인천","서인천C/C 154kV #60 BUS","서인천CC 154kV 60BUS PT 철공진방지장치 설치공사","서인천CC 154kV 60BUS PT 철공진방지장치 설치공사(효성)","2017-09-09 09:00","2017-09-09 14:00","2017-09-09T09:00:00","2017-09-09T14:00:00","당일",null,null,null,201707130091,"-"]
[73,"인천","인천","서인천C/C 154kV #61 BUS","서인천CC 154kV 61BUS PT 철공진방지장치 설치공사","서인천CC 154kV 61BUS PT 철공진방지장치 설치공사(효성)","2017-09-19 09:00","2017-09-20 17:00","2017-09-19T09:00:00","2017-09-20T17:00:00","연속",null,null,null,201707130097,"-"]
[74,"인천","인천","서인천C/C 154kV #65 BUS","서인천CC 154kV 65BUS PT 철공진방지장치 설치공사","서인천CC 154kV 65BUS PT 철공진방지장치 설치공사(효성)","2017-09-09 14:00","2017-09-09 18:00","2017-09-09T14:00:00","2017-09-09T18:00:00","당일",null,null,null,201707130092,"-"]
[75,"인천","인천","서인천C/C 154kV #66 BUS","2017년 170kV GIS 정밀점검 관련 UHF 센서설치공사","2017년 170kV GIS 정밀점검 관련 UHF 센서설치공사","2017-09-11 09:00","2017-09-13 18:00","2017-09-11T09:00:00","2017-09-13T18:00:00","연속",null,null,null,201707100127,"-"]
[76,"인천","인천","신가좌신현#2 T/L","신현S/S 170kV GIS 대체공사","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2대체 및 BUSTIE GIS 신규설치 - 기타 부대공사 1식","2017-09-03 08:00","2017-09-30 18:00","2017-09-09T08:00:00","2017-09-30T18:00:00","연속",null,null,null,201707110129,"-"]
[77,"인천","인천","신현S/S 154kV #1 BUS","신현S/S 170kV GIS 대체공사","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2,BUSTIE GIS 대체 - 기타 부대공사 1식","2017-09-05 08:00","2017-09-06 18:00","2017-09-11T08:00:00","2017-09-12T18:00:00","연속",null,null,null,201707110132,"-"]
[78,"인천","인천","신현S/S 154kV #1 BUS","신현S/S 170kV GIS 대체공사","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2,BUSTIE GIS 대체 - 기타 부대공사 1식","2017-09-23 08:00","2017-09-26 18:00","2017-09-25T08:00:00","2017-09-27T18:00:00","연속",null,null,null,201707110133,"-"]
[79,"인천","인천","신현S/S 154kV #2 BUS","신현S/S 170kV GIS 대체공사","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2,BUSTIE GIS 대체 - 기타 부대공사 1식","2017-09-03 08:00","2017-09-04 18:00","2017-09-09T08:00:00","2017-09-10T18:00:00","연속",null,null,null,201707110131,"-"]
[80,"인천","인천","신현S/S 154kV #2 BUS","신현S/S 170kV GIS 대체공사","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2,BUSTIE GIS 대체 - 기타 부대공사 1식","2017-09-27 08:00","2017-09-30 18:00","2017-09-28T08:00:00","2017-09-30T18:00:00","연속",null,null,null,201707110134,"-"]
[81,"인천","인천","신현송현#1 T/L","신현S/S 170kV GIS 대체공사(무부하가압)","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2,BUSTIE GIS 대체 - 기타 부대공사 1식","2017-09-26 10:00","2017-09-27 10:00","2017-09-26T18:00:00","2017-09-27T18:00:00","연속",null,null,null,201707110136,"-"]
[82,"인천","인천","신현송현#1 T/L","신현S/S 170kV GIS 대체공사(무부하가압)","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2,BUSTIE GIS 대체 - 기타 부대공사 1식","2017-09-29 10:00","2017-09-30 10:00","2017-09-29T18:00:00","2017-09-30T18:00:00","연속",null,null,null,201707110137,"-"]
[83,"인천","인천","신현포스코CC#2 T/L","신현S/S 170kV GIS 대체공사","- #4M.Tr 1차, 신가좌신현#2, 신현포스코#2대체 및 BUSTIE GIS 신규설치 - 기타 부대공사 1식","2017-09-03 08:00","2017-09-30 18:00","2017-09-09T08:00:00","2017-09-30T18:00:00","연속",null,null,null,201707110130,"-"]
[84,"인천","직할","고강화곡#1 T/L","고강S/S 고강화곡#1T/L 보호반 대체","고강S/S 고강화곡#1T/L 보호반 대체","2017-09-25 09:30","2017-09-29 18:00","2017-09-25T09:30:00","2017-09-29T18:00:00","연속",null,null,null,201707030025,"-"]
[85,"인천","직할","신부평S/S 154kV #1 BUS TIE CB","신부평S/S 6100TIE 170kV GIS 정밀점검","신부평S/S 6100TIE 170kV GIS 정밀점검","2017-09-25 08:00","2017-09-27 18:00","2017-09-25T08:00:00","2017-09-27T18:00:00","연속",null,null,null,201707190024,"-"]
[86,"인천","직할","신부평고강#2 T/L","'16-17년도 가공송전 협력공사(피뢰기 설치)","피뢰기 설치","2017-09-09 08:00","2017-09-09 18:00","2017-09-09T08:00:00","2017-09-09T18:00:00","당일",null,null,null,201707140081,"-"]
[87,"인천","직할","신부평부천#1 T/L","신부평S/S 신부평부천#1T/L 170kV GIS 정밀점검","신부평S/S 신부평부천#1T/L 170kV GIS 정밀점검","2017-09-11 08:00","2017-09-13 18:00","2017-09-11T08:00:00","2017-09-13T18:00:00","연속",null,null,null,201707060235,"-"]
[88,"인천","직할","신부평부천#2 T/L","신부평S/S 신부평부천#2T/L 170kV GIS 정밀점검","신부평S/S 신부평부천#2T/L 170kV GIS 정밀점검","2017-09-14 08:00","2017-09-16 18:00","2017-09-14T08:00:00","2017-09-16T18:00:00","연속",null,null,null,201707060237,"-"]
[89,"인천","직할","신부평중동#1 T/L","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검","2017-09-21 08:00","2017-09-23 18:00","2017-09-21T08:00:00","2017-09-23T18:00:00","연속",null,null,null,201707060239,"-"]
[90,"경기북부","구리","덕소팔당HP T/L","154kV 덕소-팔당 T/L 정밀점검","154kV 팔당 T/L 정밀점검 (No.1~No.34)","2017-09-18 08:00","2017-09-20 18:00","2017-09-18T08:00:00","2017-09-20T18:00:00","연속",null,null,null,201702140015,"-"]
[91,"경기북부","구리","덕소팔당HP청평HP T/L","154kV 덕소-팔당HP-청평HP T/L 정밀점검","154kV 팔당 T/L 정밀점검 (No.1~No.34)","2017-09-11 08:00","2017-09-13 18:00","2017-09-11T08:00:00","2017-09-13T18:00:00","연속",null,null,null,201702140017,"-"]
[92,"경기북부","구리","덕소별내#2 T/L","154kV 덕소-별내#2T/L EBA 자기애관 교체공사","지중송전 케이블헤드내 애관 교체(자기→폴리머) 3상","2017-09-14 08:00","2017-09-16 18:00","2017-09-14T08:00:00","2017-09-16T18:00:00","연속",null,null,null,201707120008,"○"]
[93,"경기북부","구리","덕소별내#1 T/L","154kV 덕소-별내#1T/L EBA 자기애관 교체공사","지중송전 케이블헤드내 애관 교체(자기→폴리머) 3상","2017-09-11 08:00","2017-09-13 18:00","2017-09-11T08:00:00","2017-09-13T18:00:00","연속",null,null,null,201707120007,"○"]
[94,"경기북부","구리","도봉진접 T/L","도봉-진접T/L 보호반 교체공사","도봉-진접T/L 보호반 교체","2017-09-21 08:00","2017-09-22 18:00","2017-09-21T08:00:00","2017-09-22T18:00:00","연속",null,null,null,201707040153,"-"]
[95,"경기북부","구리","마석S/S 덕소-마석#1T/L GIS","17년 154kV 차단기 보통점검","17년 154kV 차단기 보통점검","2017-09-27 09:00","2017-09-27 14:00","2017-09-27T09:00:00","2017-09-27T14:00:00","당일",null,null,null,201707070274,"-"]
[96,"경기북부","구리","마석S/S 마석-청평HP#1T/L GIS","17년 154kV 차단기 보통점검","17년 154kV 차단기 보통점검","2017-09-27 14:00","2017-09-27 18:00","2017-09-27T14:00:00","2017-09-27T18:00:00","당일",null,null,null,201707070276,"-"]
[97,"경기북부","구리","별내S/S 별내-도봉T/L GIS","17년 154kV 차단기 보통점검","17년 154kV 차단기 보통점검","2017-09-29 10:00","2017-09-29 18:00","2017-09-29T10:00:00","2017-09-29T18:00:00","당일",null,null,null,201707070279,"-"]
[98,"경기북부","구리","서종청평PP#1 T/L","154kV 서종-청평PPT/L 전선접속개소 전선교체공사","154kv 서종-청평PP T/L No.12~13등 5개구간","2017-09-11 08:00","2017-09-21 18:00","2017-09-11T08:00:00","2017-09-21T18:00:00","연속",null,null,null,201706150042,"-"]
[99,"경기북부","구리","서종청평PP#2 T/L","154kV 서종-청평PPT/L 전선접속개소 전선교체공사","154kv 서종-청평PP T/L No.12~13등 5개구간","2017-09-22 08:00","2017-10-02 18:00","2017-09-22T08:00:00","2017-10-02T18:00:00","연속",null,null,null,201706150044,"-"]
[100,"경기북부","구리","신포천S/S 154kV #1 BUS TIE GIS","17년 154kV 차단기 보통점검","17년 154kV 차단기 보통점검","2017-09-28 09:00","2017-09-28 14:00","2017-09-28T09:00:00","2017-09-28T14:00:00","당일",null,null,null,201707070396,"-"]
[101,"경기북부","구리","신포천S/S 154kV #2 BUS TIE GIS","17년 154kV 차단기 보통점검","17년 154kV 차단기 보통점검","2017-09-28 14:00","2017-09-28 18:00","2017-09-28T14:00:00","2017-09-28T18:00:00","당일",null,null,null,201707070397,"-"]
[102,"경기북부","구리","신포천덕계#2 T/L","16~17년 직할 가공송전정비 협력회사 총액공사","154kV 신포천-덕계#2T/L 피뢰기설치공사 - 59기 177SET 설치","2017-09-23 07:00","2017-09-28 18:00","2017-09-23T07:00:00","2017-09-28T18:00:00","연속",null,null,null,201707100245,"-"]
[103,"경기북부","구리","신포천전곡#1 T/L","16~17년 직할 가공송전정비 협력회사 총액공사","154kV 신포천-전곡#1T/L 피뢰기설치공사 - 35기 105SET 설치","2017-09-19 07:00","2017-09-23 18:00","2017-09-19T07:00:00","2017-09-23T18:00:00","연속",null,null,null,201707100233,"-"]
[104,"경기북부","구리","운천전곡#2 T/L","16~17년 직할 가공송전정비 협력회사 총액공사(병가)","154kV 신포천-전곡#1T/L 피뢰기설치공사 - 35기 105SET 설치 - 운천-전곡#2T/L 상단병가 선로 휴전 시행","2017-09-19 07:00","2017-09-19 18:00","2017-09-19T07:00:00","2017-09-19T18:00:00","당일",null,null,null,201707100235,"-"]
[105,"경기북부","직할","백석덕계#1 T/L","'17년 가공송전 순시점검 위탁공사(정밀점검)","154kV 신포천덕계#1T/L 정밀점검 시행(No.1~71호) -154kV 백석덕계#1T/L 하단병가선로","2017-09-10 08:00","2017-09-10 18:00","2017-09-10T08:00:00","2017-09-10T18:00:00","당일",null,null,null,201707100210,"-"]
[106,"경기북부","직할","백석덕계#2 T/L","16~17년 직할 가공송전정비 협력회사 총액공사(병가)","154kV 신포천-덕계#2T/L 피뢰기설치공사 - 59기 177SET 설치 - 백석덕계#2T/L 하단병가선로 휴전 시행","2017-09-24 07:00","2017-09-24 18:00","2017-09-24T07:00:00","2017-09-24T18:00:00","당일",null,null,null,201707100247,"-"]
[107,"경기북부","직할","신포천덕계#1 T/L","'17년 가공송전 순시점검 위탁공사(정밀점검)","154kV 신포천덕계#1T/L 정밀점검 시행(No.1~71호)","2017-09-10 08:00","2017-09-14 18:00","2017-09-10T08:00:00","2017-09-14T18:00:00","연속",null,null,null,201707100178,"-"]
[108,"경기북부","직할","신포천전곡#2 T/L","'17년 가공송전 순시점검 위탁공사(정밀점검)","154kV 신포천전곡#2T/L 정밀점검 시행(No.1~46호)","2017-09-14 08:00","2017-09-18 18:00","2017-09-14T08:00:00","2017-09-18T18:00:00","연속",null,null,null,201707100214,"-"]
[109,"경기북부","직할","운천전곡#1 T/L","'17년 가공송전 순시점검 위탁공사(정밀점검)","154kV 신포천전곡#2T/L 정밀점검 시행(No.1~46호) -154kV 운천전곡#1T/L 하단병가선로","2017-09-18 08:00","2017-09-18 18:00","2017-09-18T08:00:00","2017-09-18T18:00:00","당일",null,null,null,201707100219,"-"]
[110,"경기북부","파주","고양일산#2 T/L","2017년 파주전력지사 170kV GIS 교체공사","* 상기작업 인접Bay 크레인작업 안전조치 휴전 - 170kV GIS 철거, 설치(#5G/T, #4M.Tr 1차측) - 기타부대공사","2017-09-04 08:00","2017-09-23 08:00","2017-09-04T08:00:00","2017-09-23T08:00:00","연속",null,null,null,201707070171,"-"]
[111,"경기북부","파주","문산선유#1 T/L","17년 파주전력지사 170kV GIS 정밀점검공사","문산-선유#1T/L GIS 정밀점검","2017-09-11 09:00","2017-09-12 18:00","2017-09-11T09:00:00","2017-09-12T18:00:00","연속",null,null,null,201707110224,"-"]
[112,"경기북부","파주","문산선유#2 T/L","17년 파주전력지사 170kV GIS 정밀점검공사","문산-선유#2T/L GIS 정밀점검","2017-09-13 09:00","2017-09-14 18:00","2017-09-13T09:00:00","2017-09-14T18:00:00","연속",null,null,null,201707110225,"-"]
[113,"경기북부","파주","신덕은원흥#2 T/L","154kV 신덕은-원흥#2T/L 병가선로전선교체공사 안전확보","ㅇ 전선교체공사 병가선로 안전확보 구간 - 154kV 신덕은-원흥#2T/L No.16 ㅇ 전선교체공사 대상 - 154kV 양주-고양#1,2T/L No.28-29","2017-09-30 07:00","2017-10-01 18:00","2017-09-30T07:00:00","2017-10-01T18:00:00","연속",null,null,null,201707170147,"-"]
[114,"경기북부","파주","신덕은원흥#2 T/L","154kV 신덕은-원흥#2T/L 병가선로전선교체공사 안전확보","ㅇ 전선교체공사 병가선로 안전확보 구간 - 154kV 신덕은-원흥#2T/L No.16 ㅇ 전선교체공사 대상 - 154kV 양주-고양#1,2T/L No.28-29","2017-09-23 07:00","2017-09-24 18:00","2017-09-23T07:00:00","2017-09-24T18:00:00","연속",null,null,null,201707070202,"-"]
[115,"경기북부","파주","신파주송포#2 T/L","17년 파주전력지사 170kV GIS 정밀점검공사","신파주-송포#2T/L GIS 정밀점검","2017-09-27 09:00","2017-09-29 18:00","2017-09-27T09:00:00","2017-09-29T18:00:00","연속",null,null,null,201707110222,"-"]
[116,"경기북부","파주","양주고양#1 T/L","154kV 양주-고양#1T/L 접속개소 전선교체공사","ㅇ 공사대상 - 154kV 양주-고양#1T/L No.9-10 등 4개소","2017-09-23 08:00","2017-09-26 18:00","2017-09-23T08:00:00","2017-09-26T18:00:00","연속",null,null,null,201707070193,"-"]
[117,"경기북부","파주","양주고양#2 T/L","154kV 양주-고양#2T/L 접속개소 전선교체공사","ㅇ 공사대상 - 154kV 양주-고양#2T/L No.9-10 등 4개소","2017-09-27 07:00","2017-10-01 18:00","2017-09-27T07:00:00","2017-10-01T18:00:00","연속",null,null,null,201707070177,"-"]
[118,"경기북부","파주","일산S/S #5G/T GIS","2017년 파주전력지사 170kV GIS 교체공사","- 170kV GIS 철거, 설치(#5G/T, #4M.Tr 1차측) - 기타부대공사","2017-09-04 08:00","2017-09-23 08:00","2017-09-04T08:00:00","2017-09-23T08:00:00","연속",null,null,null,201707070174,"-"]
[119,"경기북부","파주","일산S/S 154kV #61 BUS","2017년 파주전력지사 170kV GIS 교체공사","- 170kV GIS 철거,설치(#5G/T, #4M.Tr 1차측) - 기타부대공사","2017-09-07 08:30","2017-09-13 08:00","2017-09-07T08:30:00","2017-09-13T08:00:00","연속",null,null,null,201707070282,"-"]
[120,"경기북부","파주","일산S/S 154kV #66 BUS","2017년 파주전력지사 170kV GIS 교체공사","- 170kV GIS 철거,설치(#5G/T, #4M.Tr 1차측) - 기타부대공사","2017-09-04 08:00","2017-09-07 08:00","2017-09-04T08:00:00","2017-09-07T08:00:00","연속",null,null,null,201707070281,"-"]
[121,"경기북부","파주","일산S/S 154kV #66 BUS","2017년 파주전력지사 170kV GIS 교체공사","- 170kV GIS 철거,설치(#5G/T, #4M.Tr 1차측) - 기타부대공사","2017-09-13 08:30","2017-09-23 08:00","2017-09-13T08:30:00","2017-09-23T08:00:00","연속",null,null,null,201707070283,"-"]
[122,"경기","군포","서서울남수원#1 T/L","154kV 서서울-남수원T/L 전선접속개소 전선교체공사","- 67~70호 전선교체 3가닥","2017-09-11 07:00","2017-09-13 19:00","2017-09-11T07:00:00","2017-09-13T19:00:00","연속",null,null,null,201707110096,"-"]
[123,"경기","군포","서서울남수원#2 T/L","154kV 서서울-남수원T/L 전선접속개소 전선교체공사","- 67~70호 전선교체 3가닥","2017-09-14 07:00","2017-09-16 19:00","2017-09-14T07:00:00","2017-09-16T19:00:00","연속",null,null,null,201707110097,"-"]
[124,"경기","군포","안양S/S 산본-안양#1T/L GIS","154kV 안양S/S 옥내화공사","안양S/S 구내 산본안양#1,2T/L 지중화공사를 위해 기설 GIS(2Bay) 철거 시 안전이격거리 확보를 위하여 휴전이 필요함 (EBA 공사를 위해 임시로 이설한 LA 이설 동시 추진)","2017-09-19 09:00","2017-09-20 18:00","취소","취소","연속",null,null,null,201707070044,"-"]
[125,"경기","군포","안양S/S 산본-안양#1T/L GIS","154kV 안양S/S 옥내화공사","안양S/S 구내 산본안양#1,2T/L 지중화공사를 위해 기설 GIS(2Bay) 철거 시 안전이격거리 확보를 위하여 휴전이 필요함","2017-09-12 09:00","2017-09-13 18:00","취소","취소","연속",null,null,null,201707070043,"-"]
[126,"경기","군포","안양S/S 산본-안양#2T/L GIS","154kV 안양S/S 옥내화공사","EBA 기초공사를 위해 임시로 이설한 LA를 EBA 정 위치로 이설","2017-09-21 09:00","2017-09-22 18:00","취소","취소","연속",null,null,null,201707070046,"-"]
[127,"경기","군포","안양평촌#2 T/L","17년 군포PO 154kV GIS 정밀점검","17년 군포PO 154kV GIS 정밀점검 평촌S/S 안양-평촌#2T/L","2017-09-27 09:00","2017-09-29 18:00","2017-09-27T09:00:00","2017-09-29T18:00:00","연속",null,null,null,201707050090,"-"]
[128,"경기","군포","평촌S/S 관양-평촌#2T/L GIS[2015]","154kV 평촌S/S SW 증설공사","- 170kV GIS 3CCT 설치 - 송전선로보호반 3면 설치 - 기타부대공사 1식","2017-09-25 10:30","2017-09-26 11:00","2017-09-25T10:30:00","2017-09-26T11:00:00","당일",null,null,null,201707110011,"-"]
[129,"경기","군포","반월시화#2T/L","154kV 신시흥시화#1T/L 스페이서 간격조정 및 SB댐퍼 설치공사","154kV 신시흥시화#1T/L 스페이서 간격조정 및 SB댐퍼 설치공사(25기) -No.18~25(8기) 병가구간","2017-09-21 08:00","2017-09-21 18:00","2017-09-21T08:00:00","2017-09-21T18:00:00","당일",null,null,null,201707110207,"-"]
[130,"경기","동부","곤지암초월#1 T/L","154kV 곤지암-초월T/L 송전선로 정밀점검","송전선로 정밀점검_58기","2017-09-13 09:00","2017-09-15 18:00","2017-09-13T09:00:00","2017-09-15T18:00:00","매일",null,null,null,201707110081,"-"]
[131,"경기","동부","곤지암초월#2 T/L","154kV 곤지암-초월T/L 송전선로 정밀점검","송전선로 정밀점검_58기","2017-09-25 09:00","2017-09-27 18:00","2017-09-25T09:00:00","2017-09-27T18:00:00","매일",null,null,null,201707110080,"-"]
[132,"경기","동부","성현산성#1 T/L","17년 동부변전 총액공사","산성S/S 성현-산성#1T/L GIS(보통)","2017-09-12 09:00","2017-09-12 18:00","2017-09-12T09:00:00","2017-09-12T18:00:00","당일",null,null,null,201707110164,"-"]
[133,"경기","동부","성현산성#2 T/L","17년 동부변전 총액공사","산성S/S 성현-산성#2T/L GIS(보통)","2017-09-20 09:00","2017-09-20 18:00","2017-09-20T09:00:00","2017-09-20T18:00:00","당일",null,null,null,201707110165,"-"]
[134,"경기","동부","이천가남#1 T/L","154kV 이천-가남T/L 송전선로 정밀점검","송전선로 정밀점검_44기","2017-09-19 09:00","2017-09-21 18:00","2017-09-19T09:00:00","2017-09-21T18:00:00","매일",null,null,null,201707140027,"-"]
[135,"경기","동부","이천가남#2 T/L","17년 동부변전 총액공사","이천S/S 이천-가남#2T/L GIS(보통)/인출DS 교체","2017-09-22 09:00","2017-09-24 18:00","2017-09-22T09:00:00","2017-09-24T18:00:00","연속",null,null,null,201707110168,"-"]
[136,"경기","동부","초월성현#1 T/L","17년 동부변전 총액공사","성현S/S 초월-성현#1T/L GIS(보통)/보호반대체 등","2017-09-09 09:00","2017-09-11 18:00","2017-09-09T09:00:00","2017-09-11T18:00:00","연속",null,null,null,201707110162,"-"]
[137,"경기","동부","초월성현#2 T/L","17년 동부변전 총액공사","성현S/S 초월-성현#2T/L GIS(보통)/보호반대체 등","2017-09-16 09:00","2017-09-18 18:00","2017-09-16T09:00:00","2017-09-18T18:00:00","연속",null,null,null,201707110163,"-"]
[138,"경기","성남","북동탄-동탄2열병합#1 T/L","17년 성남변전협력회사 총액공사","GIS 초기점검","2017-09-12 10:00","2017-09-12 18:00","2017-09-12T10:00:00","2017-09-12T18:00:00","당일",null,null,null,201707130024,"-"]
[139,"경기","성남","북동탄-동탄2열병합#2 T/L","17년 성남변전협력회사 총액공사","GIS 초기점검","2017-09-13 10:00","2017-09-13 18:00","2017-09-13T10:00:00","2017-09-13T18:00:00","당일",null,null,null,201707130025,"-"]
[140,"경기","성남","삼미-동탄2열병합#1 T/L","17년 성남변전협력회사 총액공사","GIS 초기점검","2017-09-15 10:00","2017-09-15 18:00","2017-09-15T10:00:00","2017-09-15T18:00:00","당일",null,null,null,201707130002,"-"]
[141,"경기","성남","삼미-동탄2열병합#2 T/L","17년 성남변전협력회사 총액공사","GIS 초기점검","2017-09-18 10:00","2017-09-18 18:00","2017-09-18T10:00:00","2017-09-18T18:00:00","당일",null,null,null,201707130022,"-"]
[142,"경기","성남","삼미-동탄2열병합#3 T/L","17년 성남변전협력회사 총액공사","GIS 초기점검","2017-09-19 10:00","2017-09-19 18:00","2017-09-19T10:00:00","2017-09-19T18:00:00","당일",null,null,null,201707130023,"-"]
[143,"경기","성남","신성남S/S 154kV #1 BUS TIE(6100) GIS","신성남S/S 154kV GIS 대체공사","#1BUSTIE GIS 대체","2017-09-09 09:00","2017-09-25 18:00","2017-09-09T09:00:00","2017-09-25T18:00:00","연속",null,null,null,201707130008,"-"]
[144,"경기","성남","신성남과천#1 T/L","신성남S/S 154kV GIS 대체공사","신성남-과천#1T/L GIS 대체","2017-09-09 09:00","2017-09-25 18:00","2017-09-09T09:00:00","2017-09-25T18:00:00","연속",null,null,null,201707130007,"-"]
[145,"경기","성남","신성남서판교#1 T/L","17년 성남변전협력회사 총액공사","GIS 보통점검","2017-09-29 10:00","2017-09-29 18:00","2017-09-29T10:00:00","2017-09-29T18:00:00","당일",null,null,null,201707130006,"-"]
[146,"경기","성남","신수원S/S 154kV #3BUS-TIE(6300) GIS","17년 성남변전협력회사 총액공사","GIS 보통점검","2017-09-22 10:00","2017-09-22 18:00","2017-09-22T10:00:00","2017-09-22T18:00:00","당일",null,null,null,201707130004,"-"]
[147,"경기","성남","율현용인#1 T/L","17년 성남변전협력회사 총액공사","GIS 초기점검, CVT 대체","2017-09-28 10:00","2017-09-28 18:00","2017-09-28T10:00:00","2017-09-28T18:00:00","당일",null,null,null,201707130020,"-"]
[148,"경기","직할","안열#2T/L T/L","154kV 안열#2T/L OF케이블 절연유 채유","OF케이블 절연유 채유(추적조사)","2017-09-13 09:00","2017-09-13 18:00","2017-09-13T09:00:00","2017-09-13T18:00:00","당일",null,null,null,201707060157,"-"]
[149,"경기","직할","율전의왕#1 T/L","율전#1C/H PD진단센서 및 집합반 설치공사","EBA에 PD진단센서를 설치하고 PD집합반에 연결","2017-09-30 09:00","2017-09-30 13:00","2017-09-30T09:00:00","2017-09-30T13:00:00","당일",null,null,null,201707060123,"-"]
[150,"경기","직할","율전의왕#2 T/L","율전#1C/H PD진단센서 및 집합반 설치공사","EBA에 PD진단센서를 설치하고 PD집합반에 연결","2017-09-30 13:00","2017-09-30 16:00","2017-09-30T13:00:00","2017-09-30T16:00:00","당일",null,null,null,201707060124,"-"]
[151,"경기","직할","화성S/S 154kV #60 BUS","화성S/S 154kV 화성조암#1T/L GIS 정밀점검공사","화성S/S 154kV 화성조암#1T/L GIS 정밀점검공사","2017-09-22 09:00","2017-09-22 18:00","2017-09-22T09:00:00","2017-09-22T18:00:00","당일",null,null,null,201707070105,"-"]
[152,"경기","직할","화성S/S 154kV #61 BUS","화성S/S 345kV #2M.Tr 2차 GIS 정밀점검공사","화성S/S 345kV #2M.Tr 2차 GIS 정밀점검공사","2017-09-15 09:00","2017-09-15 18:00","2017-09-15T09:00:00","2017-09-15T18:00:00","당일",null,null,null,201707070099,"-"]
[153,"경기","직할","화성S/S 154kV #66 BUS","화성S/S 154kV #63M.Tr 1차 GIS 정밀점검공사","화성S/S 154kV #63M.Tr 1차 GIS 정밀점검공사","2017-09-27 09:00","2017-09-27 14:00","2017-09-27T09:00:00","2017-09-27T14:00:00","당일",null,null,null,201707070101,"-"]
[154,"경기","직할","화성S/S 154kV #66 BUS","화성S/S 154kV 화성조암#2T/L GIS 정밀점검공사","화성S/S 154kV 화성조암#2T/L GIS 정밀점검공사","2017-09-20 09:00","2017-09-20 14:00","2017-09-20T09:00:00","2017-09-20T14:00:00","당일",null,null,null,201707070106,"-"]
[155,"경기","직할","화성발안#2 T/L","154kV 화성조암T/L 피뢰기설치공사","1~10호호 송전선로용 피뢰기 설치 관련 안전이격거리확보","2017-09-23 07:00","2017-09-24 19:00","2017-09-23T07:00:00","2017-09-24T19:00:00","매일",null,null,null,201707110038,"-"]
[156,"경기","직할","화성조암#1 T/L","화성S/S 154kV 화성조암#1T/L GIS 정밀점검공사","화성S/S 154kV 화성조암#1T/L GIS 정밀점검공사","2017-09-20 14:00","2017-09-22 18:00","2017-09-20T14:00:00","2017-09-22T18:00:00","연속",null,null,null,201707070120,"-"]
[157,"경기","직할","화성조암#2 T/L","화성S/S 154kV 화성조암#2T/L GIS 정밀점검공사","화성S/S 154kV 화성조암#2T/L GIS 정밀점검공사","2017-09-18 09:00","2017-09-20 14:00","2017-09-18T09:00:00","2017-09-20T14:00:00","연속",null,null,null,201707140026,"-"]
[158,"경기","평택","고덕-송탄 T/L T/L","지제역세권 지장송전선로 지중화공사","154kV 고덕-송탄T/L No.18, 25 이설, 154kV 송탄-안성T/L No.4 작업 안전거리 확보","2017-09-23 06:00","2017-09-24 18:00","2017-09-23T06:00:00","2017-09-24T18:00:00","연속",null,null,null,201707130138,"○"]
[159,"경기","평택","서안성안성#2 T/L","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - 기기번호 부여 변경작업","2017-09-13 09:30","2017-09-14 18:00","2017-09-13T09:30:00","2017-09-14T18:00:00","연속",null,null,null,201707100502,"-"]
[160,"경기","평택","서운안성#1 T/L","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - 기기번호 부여 변경작업","2017-09-11 09:30","2017-09-12 18:00","2017-09-11T09:30:00","2017-09-12T18:00:00","연속",null,null,null,201707100501,"○"]
[161,"경기","평택","송탄안성 T/L","지제역세권 지장송전선로 지중화공사","154kV 고덕-송탄T/L No.18, 25 이설, 154kV 송탄-안성T/L No.4 작업 안전거리 확보","2017-09-23 06:00","2017-09-24 18:00","2017-09-23T06:00:00","2017-09-24T18:00:00","연속",null,null,null,201707130139,"○"]
[162,"경기","평택","안성S/S 154kV #1 BUS","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - #1BUS 측 인터록 및 모선보호반 시험","2017-09-18 09:30","2017-09-23 18:00","2017-09-18T09:30:00","2017-09-23T18:00:00","연속",null,null,null,201706290156,"-"]
[163,"경기","평택","안성S/S 154kV #2 BUS","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - 154kV #2BUS PT 이설","2017-09-15 09:30","2017-09-15 18:00","2017-09-15T09:30:00","2017-09-15T18:00:00","연속",null,null,null,201706290155,"-"]
[164,"경기","평택","안성S/S 154kV #2 BUS","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - #2BUS측 인터록 및 모선보호반 시험","2017-09-25 09:30","2017-09-30 18:00","2017-09-25T09:30:00","2017-09-30T18:00:00","연속",null,null,null,201706290157,"-"]
[165,"경기","평택","평택오성CC#2 T/L","평택S/S 평택-오성복합 #2T/L GCB 조작시험(본사 지시사항)","평택S/S 평택-오성복합 #2T/L GCB 조작시험(본사 지시사항)","2017-09-09 09:00","2017-09-09 18:00","2017-09-09T09:00:00","2017-09-09T18:00:00","당일",null,null,null,201707110103,"-"]
[166,"경기","평택","포승만호#1 T/L","포승S/S 만호-포승T/L GIS보통점검","포승S/S 만호-포승T/L GIS보통점검 / 보호반 성능개선 / 변전소 전면정전 대비 모의고장 훈련","2017-09-14 10:00","2017-09-15 18:00","2017-09-14T10:00:00","2017-09-15T18:00:00","매일",null,null,null,201707110044,"-"]
[167,"경기","평택","포승평택TP#1 T/L","154kV 포승-평택TPT/L 7호 안전이격거리 확보공사","○ 공사구간 : 포승-평택TPT/L No.6~8 ○ 공사내용 : 2회선 가선로 구성 ○ 공사규모 : 철탑 1기설치,철거","2017-09-16 07:00","2017-09-18 18:00","2017-09-16T07:00:00","2017-09-18T18:00:00","연속",null,null,null,201707110161,"-"]
[168,"경기","평택","포승평택TP#2 T/L","154kV 포승-평택TPT/L 7호 안전이격거리 확보공사","○ 공사구간 : 포승-평택TPT/L No.6~8 ○ 공사내용 : 2회선 가선로 구성 ○ 공사규모 : 철탑 1기설치,철거","2017-09-09 07:00","2017-09-11 18:00","2017-09-09T07:00:00","2017-09-11T18:00:00","연속",null,null,null,201707110160,"-"]
[169,"강원","강릉","강릉횡계#1 T/L","154kV 강릉 등 3개T.L CH철탑 설치공사","154kV 강릉S/S 인출 송전선로 지중화 - 지지물 CH철탑 설치 2기(2, 4회선 각1기), 계탑 1기(35호), 가철탑 1기(35호) 설치","2017-09-06 09:00","2017-09-13 18:00","2017-09-06 09:00","2017-09-13 18:00","연속",null,null,null,201707050064,"-"]
[170,"강원","강릉","강릉횡계#2 T/L","154kV 강릉 등 3개T.L CH철탑 설치공사","154kV 강릉S/S 인출 송전선로 지중화 - 지지물 CH철탑 설치 2기(2, 4회선 각1기), 계탑 1기(35호), 가철탑 1기(35호) 설치","2017-09-14 09:00","2017-09-26 18:00","2017-09-14 09:00","2017-09-26 18:00","연속",null,null,null,201707050066,"-"]
[171,"강원","강릉","동해강릉 T/L","154kV 강릉 등 3개T.L CH철탑 설치공사","154kV 강릉S/S 인출 송전선로 지중화 - 지지물 CH철탑 설치 2기(2, 4회선 각1기), 계탑 1기(35호), 가철탑 1기(35호) 설치","2017-09-23 09:00","2017-09-24 18:00","2017-09-23 09:00","2017-09-24 18:00","연속",null,null,null,201707050069,"-"]
[172,"강원","강릉","동해강릉 T/L","154kV 강릉 등 3개T.L CH철탑 설치공사","154kV 강릉S/S 인출 송전선로 지중화 - 지지물 CH철탑 설치 2기(2, 4회선 각1기), 계탑 1기(35호), 가철탑 1기(35호) 설치","2017-09-06 09:00","2017-09-13 18:00","2017-09-06 09:00","2017-09-13 18:00","연속",null,null,null,201707050065,"-"]
[173,"강원","강릉","동해강릉 T/L","154kV 강릉 등 3개T.L CH철탑 설치공사","154kV 강릉S/S 인출 송전선로 지중화 - 지지물 CH철탑 설치 2기(2, 4회선 각1기), 계탑 1기(35호), 가철탑 1기(35호) 설치","2017-09-15 09:00","2017-09-15 18:00","2017-09-15 09:00","2017-09-15 18:00","당일",null,null,null,201707050068,"-"]
[174,"강원","강릉","속초간성#1 T/L","2017년 간성S/S 170kV 장기사용 GIS 대체공사","GIS 대체 안전이격 확보","2017-09-03 08:30","2017-09-07 17:00","2017-09-03 08:30","2017-09-07 17:00","매일",null,null,null,201707070302,"-"]
[175,"강원","강릉","속초간성#2 T/L","2017년 간성S/S 170kV 장기사용 GIS 대체공사","속초간성#2TL GIS 대체","2017-09-01 08:30","2017-10-02 18:00","2017-09-01 08:30","2017-10-02 18:00","연속",null,null,null,201707070291,"-"]
[176,"강원","강릉","신양양_양양#1 T/L","154kV 신양양-양양 #1T/L 피뢰기 설치공사","○154kV 신양양-양양 #1T/L 피뢰기 설치공사(No.1 등 58기)","2017-09-11 07:00","2017-09-15 18:00","2017-09-11 07:00","2017-09-15 18:00","매일",null,null,null,201707070400,"-"]
[177,"강원","강릉","신양양_양양#2 T/L","2017년 가공송전선로 순시점검 위탁공사","○ 154kV 주문진-양양 #1T/L KPS 정밀점검 (4회선 병가철탑구간)","2017-09-21 08:00","2017-09-21 18:00","2017-09-21 08:00","2017-09-21 18:00","당일",null,null,null,201707070406,"-"]
[178,"강원","강릉","신제천주진#2 T/L","154kV 원주북원주 등 8개T/L 송전선로용 피뢰기 설치공사","송전선로용 피뢰기 설치 110기 330set","2017-09-01 07:00","2017-09-06 18:00","2017-09-01 07:00","2017-09-06 18:00","매일",null,null,null,201707030035,"-"]
[179,"강원","강릉","영동T/P 154kV #1 BUS","2017년 변전협력회사 총액공사","154kV 탈황측 #1BUS CVT 교체","2017-09-11 10:00","2017-09-11 18:00","2017-09-11 10:00","2017-09-11 18:00","당일",null,null,null,201707070345,"-"]
[180,"강원","강릉","영동T/P 154kV #2 BUS","2017년 변전협력회사 총액공사","154kV 탈황측 #2BUS CVT 교체","2017-09-12 10:00","2017-09-12 18:00","2017-09-12 10:00","2017-09-12 18:00","당일",null,null,null,201707070346,"-"]
[181,"강원","강릉","영동TP강릉 T/L","154kV 강릉 등 3개T.L CH철탑 설치공사","154kV 강릉S/S 인출 송전선로 지중화 - 지지물 CH철탑 설치 2기(2, 4회선 각1기), 계탑 1기(35호), 가철탑 1기(35호) 설치","2017-09-14 09:00","2017-09-26 18:00","2017-09-14 09:00","2017-09-26 18:00","연속",null,null,null,201707050067,"-"]
[182,"강원","강릉","주진평창#2 T/L","154kV 주진-평창#2T/L 피뢰기 설치공사","○ 154kV 주진-평창 #2T/L 피뢰기 설치공사(No.1 등 51기)","2017-09-26 07:00","2017-09-28 18:00","2017-09-26 07:00","2017-09-28 18:00","매일",null,null,null,201707070409,"-"]
[183,"강원","강릉","평창-올림픽 T/L","2016~17년 송전정비협력회사 총액공사","○ 154kV 평창-올림픽T/L 항공장애표시구 설치(No.1~횡계평창No.7)","2017-09-14 07:00","2017-09-14 18:00","2017-09-14 07:00","2017-09-14 18:00","당일",null,null,null,201707070401,"-"]
[184,"강원","강릉","횡계-올림픽 T/L","154kV 횡계-올림픽T/L 피뢰기 설치공사","○ 154kV 횡계-올림픽T/L 피뢰기 설치공사(No.2 등 5기)","2017-09-25 07:00","2017-09-25 18:00","2017-09-25 07:00","2017-09-25 18:00","당일",null,null,null,201707070408,"-"]
[185,"강원","강릉","횡계평창#1 T/L","2016~17년 송전정비협력회사 총액공사","○ 154kV 횡계-평창 #1T/L 항공장애표시구 설치(No.5~7)","2017-09-15 07:00","2017-09-15 18:00","2017-09-15 07:00","2017-09-15 18:00","당일",null,null,null,201707070403,"-"]
[186,"강원","동해","도계태백 T/L","17년 동해전력지사 변전협력회사 총액공사","1. 도계S/S 보호배전반 대체","2017-09-21 09:30","2017-09-22 18:00","2017-09-21 09:30","2017-09-22 18:00","연속",null,null,null,201707070201,"-"]
[187,"강원","동해","동해이원#1 T/L","154kV 이원 등 4개T/L 송전선로용 피뢰기설치공사","송전선로용 피뢰기설치 - No.1~28 (28기, 54SET)","2017-09-18 08:00","2017-09-20 18:00","2017-09-18 08:00","2017-09-20 18:00","매일",null,null,null,201707100298,"-"]
[188,"강원","동해","동해정선 T/L","2017년 동해전력지사 170kV GIS 정밀점검공사","1. 정선S/S 동해-정선 T/L GIS 정밀점검(657) 2. LA보통점검","2017-09-25 10:00","2017-09-27 18:00","2017-09-25 10:00","2017-09-27 18:00","연속",null,null,null,201707070137,"-"]
[189,"강원","동해","삼척동해TP T/L","2017년 동해전력지사 170kV GIS 정밀점검공사","1. 삼척S/S 삼척-동해TP T/L GIS 정밀점검(687)","2017-09-14 09:00","2017-09-16 18:00","2017-09-14 09:00","2017-09-16 18:00","연속",null,null,null,201707070132,"-"]
[190,"강원","동해","이원도계(라파즈한라T분기) T/L","17년 동해전력지사 변전협력회사 총액공사","1. 이원S/S 보호배전반 대체 2. 도계S/S 보호배전반 대체","2017-09-13 09:00","2017-09-14 18:00","2017-09-13 09:00","2017-09-14 18:00","연속",null,null,null,201707070183,"-"]
[191,"강원","동해","이원동해TP T/L","2017∼18 강원지역본부 지중송전설비 위탁정비공사","지중송전선로 인출 도블측정","2017-09-13 09:00","2017-09-13 18:00","2017-09-13 09:00","2017-09-13 18:00","당일",null,null,null,201707100296,"-"]
[192,"강원","동해","이원태백 T/L","17년 동해전력지사 변전협력회사 총액공사","1. 이원S/S 보호배전반 대체","2017-09-19 09:00","2017-09-20 18:00","2017-09-19 09:00","2017-09-20 18:00","연속",null,null,null,201707070200,"-"]
[193,"강원","원주","남원주원주#2 T/L","원주전력지사 장기미동작 차단기 동작특성시험","남원주,원주S/S 남원주-원주#2T/L 장기미동작 차단기 동작특성시험","2017-09-08 10:00","2017-09-08 18:00","2017-09-08 10:00","2017-09-08 18:00","당일",null,null,null,201707100212,"-"]
[194,"강원","원주","북원주횡성#1 T/L","154kV 북원주-횡성T/L 안전이격 확보공사","철거 2기, 산설 2기, 전력선 교체 1.5km OPGW 교체 2.8km","2017-09-25 09:00","2017-09-30 18:00","2017-09-25 09:00","2017-09-30 18:00","연속",null,null,null,201707200035,"-"]
[195,"강원","원주","북원주횡성#2 T/L","154kV 북원주-횡성T/L 안전이격 확보공사","철거 2기, 신설 2기,전력선교체 1.5km,OPGW 교체 2.8km","2017-09-25 09:00","2017-09-30 18:00","2017-09-25 09:00","2017-09-30 18:00","연속",null,null,null,201707200037,"-"]
[196,"강원","원주","상남인제#2 T/L","2016~2017년 원주전력지사 변전협력회사 총액공사","상남S/S 154kV 상남인제#2T/L GIS 보통점검","2017-09-12 10:00","2017-09-12 18:00","2017-09-12 10:00","2017-09-12 18:00","당일",null,null,null,201707100216,"-"]
[197,"강원","원주","신제천남원주#1 T/L","원주전력지사 장기미동작 차단기 동작특성시험","남원주S/S 신제천-남원주#1T/L 장기미동작 차단기 동작특성시험","2017-09-07 10:00","2017-09-07 18:00","2017-09-07 10:00","2017-09-07 18:00","당일",null,null,null,201707100189,"-"]
[198,"강원","원주","홍천상남#1 T/L","154kV 원주북원주 등 8개T/L 송전선로용 피뢰기 설치공사","송전선로용 피뢰기설치 129기, 387set","2017-09-07 07:00","2017-09-13 18:00","2017-09-07 07:00","2017-09-13 18:00","매일",null,null,null,201707030037,"-"]
[199,"강원","원주","횡성홍천#1 T/L","154kV 원주북원주 등 8개T/L 송전선로용 피뢰기 설치공사","송전선로용 피뢰기설치 107기, 321set","2017-09-14 07:00","2017-09-18 18:00","2017-09-14 07:00","2017-09-18 18:00","매일",null,null,null,201707030041,"-"]
[200,"강원","직할","가평춘천HP T/L","2017년도 가공송전선로 순시점검 위탁공사","○ 대상선로 : 154kV 한강분기T/L ○ 작업내용 : 정밀점검(11기)","2017-09-19 08:00","2017-09-19 18:00","2017-09-19 08:00","2017-09-19 18:00","당일",null,null,null,201707100141,"-"]
[201,"강원","직할","가평화천HP T/L","154kV 화천T/L 안전이격 확보공사","○ 구간 : 154kV 화천T/L No.46~50간 ○ 철탑신설 : No.47,48,49 (설치 및 철거) ○ 전선교체 : No.46~50간 (2c-1.64km)","2017-09-11 08:00","2017-09-14 18:00","2017-09-11 08:00","2017-09-14 18:00","연속",null,null,null,201707100188,"-"]
[202,"강원","직할","북춘천춘천HP T/L","2016~2017년도 송전정비 협력회사 총액공사","○ 송전선로용 피뢰기 설치 - 대상선로 : 154kV 춘천수력T/L 전구간(24기)","2017-09-18 08:00","2017-09-19 18:00","2017-09-18 08:00","2017-09-19 18:00","매일",null,null,null,201707100123,"-"]
[203,"강원","직할","북춘천화천HP T/L","154kV 화천T/L 안전이격 확보공사","○ 구간 : 154kV 화천T/L No.46~50간 ○ 철탑신설 : No.47,48,49 (설치 및 철거) ○ 전선교체 : No.46~50간 (2c-1.64km)","2017-09-15 08:00","2017-09-18 18:00","2017-09-15 08:00","2017-09-18 18:00","연속",null,null,null,201707100193,"-"]
[204,"강원","직할","상남인제#1 T/L","2016~2017년도 강원직할 송전정비 협력회사 총액공사","○ 작업내용 : 송전선로용 피뢰기 설치 ○ 작업구간 : 전구간(120기)","2017-09-23 08:00","2017-09-30 18:00","2017-09-23 08:00","2017-09-30 18:00","매일",null,null,null,201707100132,"-"]
[205,"강원","직할","홍천남춘천 T/L","2016~2017년도 강원직할 송전정비 협력회사 총액공사","○ 작업내용 : 송전선로용 피뢰기 설치 ○ 작업구간 : 전구간 36기","2017-09-20 08:00","2017-09-22 18:00","2017-09-20 08:00","2017-09-22 18:00","매일",null,null,null,201707100130,"-"]
[206,"강원","태백","동영월영월CC T/L","154kV 영월화력T/L 스페이서 및 SB댐퍼 교체공사","○ 154kV 영월화력T/L 스페이서 및 SB댐퍼 교체공사","2017-09-09 09:00","2017-09-11 18:00","2017-09-09 09:00","2017-09-11 18:00","매일",null,null,null,201707060179,"-"]
[207,"강원","태백","동해동영월 T/L","154kV 영월화력T/L 스페이서 및 SB댐퍼 교체공사","○ 154kV 영월화력T/L 스페이서 및 SB댐퍼 교체공사","2017-09-12 09:00","2017-09-18 18:00","2017-09-12 09:00","2017-09-18 18:00","매일",null,null,null,201707060180,"-"]
[208,"강원","태백","정선영월CC T/L","154kV 영월화력T/L 스페이서 및 SB댐퍼 교체공사","○ 154kV 영월화력T/L 스페이서 및 SB댐퍼 교체공사","2017-09-19 09:00","2017-09-28 18:00","2017-09-19 09:00","2017-09-28 18:00","연속",null,null,null,201707060181,"-"]
[209,"충북","직할","단양S/S 점촌-단양T/L CB","단양S/S 154kV #3Sh.C 설치공사","154kV GIS 50kA 1250A 1CCT 증설 증설모선 무부하 가압시험을 위한 휴전 및 가압시행","2017-09-29 16:00","2017-09-29 17:00","2017-09-29 16:00","2017-09-29 17:00","당일",null,null,null,201707180076,"-"]
[210,"충북","직할","단양S/S 점촌-단양T/L CB","단양S/S 154kV #3Sh.C 설치공사","154kV GIS 50kA 1250A 1CCT 증설 증설모선 무부하 가압시험을 위한 휴전 및 가압시행","2017-09-22 16:00","2017-09-22 17:00","2017-09-22 16:00","2017-09-22 17:00","당일",null,null,null,201707180075,"-"]
[211,"충북","직할","문경단양 T/L","단양S/S 154kV #3Sh.C 설치공사","154kV GIS 1CCT 증설(기설 모선 철거 후 설치) - 안전이격확보 필요","2017-09-26 13:00","2017-09-26 18:00","2017-09-26 13:00","2017-09-26 18:00","당일",null,null,null,201707040048,"-"]
[212,"충북","직할","신제천영월CC#1 T/L","2016~2017 직할 송전정비 협력업체 총액공사","조류착지방설치(43,66,78호),아킹혼 철거(78호)","2017-09-19 08:00","2017-09-19 18:00","2017-09-19 08:00","2017-09-19 18:00","당일",null,null,null,201707120068,"-"]
[213,"충북","직할","신충주S/S 23kV #1ESS CB","신충주S/S ESS 설비 정기점검","ESS 설비 점검, 차단기 점검, 변압기 점검","2017-09-04 09:00","2017-09-08 18:00","2017-09-04 09:00","2017-09-08 18:00","연속",null,null,null,201707040041,"-"]
[214,"충북","직할","신충주S/S 23kV #2ESS CB","신충주S/S ESS 설비 정기점검","ESS 설비 점검, 차단기 점검, 변압기 점검","2017-09-04 09:00","2017-09-08 18:00","2017-09-04 09:00","2017-09-08 18:00","연속",null,null,null,201707040042,"-"]
[215,"충북","직할","신충주S/S 23kV #3ESS CB","신충주S/S ESS 설비 정기점검","ESS 설비 점검, 차단기 점검, 변압기 점검","2017-09-04 09:00","2017-09-08 18:00","2017-09-04 09:00","2017-09-08 18:00","연속",null,null,null,201707040043,"-"]
[216,"충북","직할","신충주S/S 23kV #4ESS CB","신충주S/S ESS 설비 정기점검","ESS 설비 점검, 차단기 점검, 변압기 점검","2017-09-04 09:00","2017-09-08 18:00","2017-09-04 09:00","2017-09-08 18:00","연속",null,null,null,201707040044,"-"]
[217,"충북","직할","음성금왕#1 T/L","2017년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검 (No.1~65)","2017-09-11 09:00","2017-09-15 18:00","2017-09-11 09:00","2017-09-15 18:00","매일",null,null,null,201707190055,"○"]
[218,"충북","직할","음성금왕#2 T/L","2017년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검 (No.1~65)","2017-09-18 09:00","2017-09-22 18:00","2017-09-18 09:00","2017-09-22 18:00","매일",null,null,null,201707190056,"○"]
[219,"충북","직할","점촌단양 T/L","단양S/S 154kV #3Sh.C 설치공사","154kV GIS 1CCT 증설(기설 모선 철거 후 설치) - 안전이격확보 필요","2017-09-26 08:00","2017-09-26 12:00","2017-09-26 08:00","2017-09-26 12:00","당일",null,null,null,201707040046,"-"]
[220,"충북","직할","풍동음성#1 T/L","음성S/S 풍동음성#1T/L LA 점검","- 170kV LA 보통점검","2017-09-22 10:00","2017-09-22 14:00","2017-09-22 10:00","2017-09-22 14:00","당일",null,null,null,201707100489,"○"]
[221,"충북","청주","상주보은 T/L","2017년 가공송전선로 순시점검 위탁공사","보은분기(상주-보은T/L) 정밀점검","2017-09-07 08:30","2017-09-08 18:00","2017-09-07 08:30","2017-09-08 18:00","매일",null,null,null,201707130056,"-"]
[222,"충북","청주","상주영동 T/L","2017년 가공송전선로 순시점검 위탁공사","영동분기(상주-영동T/L) 정밀점검","2017-09-25 08:30","2017-09-27 18:00","2017-09-25 08:30","2017-09-27 18:00","매일",null,null,null,201707130084,"-"]
[223,"충북","충주","금왕남음성#1 T/L","2017년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검 (No.1~26)","2017-09-19 09:00","2017-09-21 18:00","2017-09-19 09:00","2017-09-21 18:00","매일",null,null,null,201707190061,"○"]
[224,"충북","충주","금왕남음성#2 T/L","2017년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검 (No.1~26)","2017-09-12 09:00","2017-09-14 18:00","2017-09-12 09:00","2017-09-14 18:00","매일",null,null,null,201707190060,"○"]
[225,"충북","충주","남음성덕산#1 T/L","154kV 풍동-음성 등 9개T/L 전력선 교체공사(남음성-덕산#1)","전선접속개소해소를 위한 전선교체(154kV 남음성-덕산 #1T/L No.4~8, 8~10)","2017-09-20 07:00","2017-09-23 18:00","2017-09-20 07:00","2017-09-23 18:00","연속",null,null,null,201707070240,"○"]
[226,"충북","충주","남음성덕산#2 T/L","154kV 풍동-음성 등 9개T/L 전력선 교체공사(남음성-덕산#2)","전선접속개소해소를 위한 전선교체(154kV 남음성-덕산 #2T/L No.4~8, 10~11)","2017-09-27 07:00","2017-09-30 18:00","2017-09-27 07:00","2017-09-30 18:00","연속",null,null,null,201707070245,"○"]
[227,"충북","충주","충주풍동 T/L","2017년 가공송전선로 순시점검 위탁공사","스페이서 교체 (No.6~7)","2017-09-29 09:00","2017-09-29 18:00","2017-09-29 09:00","2017-09-29 18:00","당일",null,null,null,201707170080,"○"]
[228,"대전충남","대전","신계룡은진#1 T/L","은진S/S 154kV 모선 GIB화 공사 관련","은진S/S 154kV 모선 GIB화 공사 관련","2017-09-11 09:00","2017-09-30 18:00","2017-09-11T09:00:00","2017-09-30T18:00:00","연속",null,null,null,201707110001,"-"]
[229,"대전충남","대전","신계룡은진#2 T/L","은진S/S 154kV 모선 GIB화 공사 관련","은진S/S 154kV 모선 GIB화 공사 관련","2017-09-11 09:00","2017-09-30 18:00","2017-09-11T09:00:00","2017-09-30T18:00:00","연속",null,null,null,201707110002,"-"]
[230,"대전충남","대전","신옥천남대전#2 T/L","[송전] 154kV 팔봉-두마 등 4개T/L 피뢰기 설치공사","[송전] 154kV 신옥천-남대전#2T/L 피뢰기 설치","2017-09-16 07:00","2017-09-17 18:00","2017-09-09T07:00:00","2017-09-10T18:00:00","매일",null,null,null,201707060267,"-"]
[231,"대전충남","대전","신옥천남대전#3 T/L","[송전]154kV 조치원-대화 등 7개T/L 노후 피뢰기교체공사","154kV 신옥천남대전#3T/L C/H(No.30)용 피뢰기 교체공사 시행","2017-09-13 09:00","2017-09-13 18:00","2017-09-13T09:00:00","2017-09-13T18:00:00","당일",null,null,null,201707030092,"-"]
[232,"대전충남","서산","신당진S/S 154kV #1 BUS TIE CB","'17년 변전협력회사 총액공사","신당진S/S 154kV #1BUS-TIE GIS(6100) 보통점검","2017-09-21 10:00","2017-09-21 18:00","2017-09-21T10:00:00","2017-09-21T18:00:00","당일",null,null,null,201707070343,"-"]
[233,"대전충남","서산","신당진S/S 60-61-0 SEC CB","'17년 변전협력회사 총액공사","신당진S/S 154kV 60-61-0 BUS SEC GIS 보통점검","2017-09-14 10:00","2017-09-14 18:00","2017-09-14T10:00:00","2017-09-14T18:00:00","당일",null,null,null,201707070298,"-"]
[234,"대전충남","서산","신당진S/S 65-66-0 SEC CB","'17년 변전협력회사 총액공사","신당진S/S 154kV 65-66-0 BUS SEC GIS 보통점검","2017-09-15 10:00","2017-09-15 18:00","2017-09-15T10:00:00","2017-09-15T18:00:00","당일",null,null,null,201707070300,"-"]
[235,"대전충남","서산","태안태안화력 T/L","'17년 변전협력회사 총액공사","태안화력 154kV 태안-태안화력T/L GIS(627) 하자점검 및 LA 보통점검","2017-09-18 10:00","2017-09-18 18:00","2017-09-18T10:00:00","2017-09-18T18:00:00","당일",null,null,null,201707070301,"-"]
[236,"대전충남","세종","부강월산#2 T/L","154kV 부강-월산#2T/L 정밀점검","[송전]No.14~43 정밀점검","2017-09-11 07:00","2017-09-15 18:00","2017-09-11T07:00:00","2017-09-15T18:00:00","매일",null,null,null,201707040100,"-"]
[237,"대전충남","세종","서세종조치원 T/L","[송전]154kV서세종-조치원T/L EBA 절연유 교체공사","154kV서세종-조치원T/L EBA(C/H No.1) 절연유 교체공사 시행","2017-09-04 09:00","2017-09-07 18:00","2017-09-04T09:00:00","2017-09-07T18:00:00","연속",null,null,null,201707030091,"-"]
[238,"대전충남","세종","신풍공주#2 T/L","154kV 신풍-공주#2T/L 전선교체공사","[송전] No.60~65 전선교체","2017-09-18 07:00","2017-09-22 18:00","2017-09-18T07:00:00","2017-09-22T18:00:00","연속",null,null,null,201707040097,"-"]
[239,"대전충남","세종","월산서세종 T/L","[변전] 세종P/O 협력회사 총액공사","○ GIS 보통점검","2017-09-08 09:30","2017-09-08 18:00","2017-09-08T09:30:00","2017-09-08T18:00:00","당일",null,null,null,201707100173,"-"]
[240,"대전충남","세종","조치원전의#1 T/L","[변전] 세종P/O 협력회사 총액공사","○ 보호반 대체","2017-09-10 09:00","2017-09-12 18:00","2017-09-10T09:00:00","2017-09-12T18:00:00","당일",null,null,null,201707100170,"-"]
[241,"대전충남","세종","조치원전의#2 T/L","[변전] 세종P/O 협력회사 총액공사","○ 보호반 대체","2017-09-13 09:00","2017-09-15 18:00","2017-09-13T09:00:00","2017-09-15T18:00:00","당일",null,null,null,201707100171,"-"]
[243,"대전충남","아산","신온양한샘#1 T/L","신온양S/S 154kV 신온양-한샘#1T/L GIS 정밀점검","○ 154kV 신온양-한샘#1T/L GIS 정밀점검","2017-09-21 09:00","2017-09-22 18:00","2017-09-21T09:00:00","2017-09-22T18:00:00","연속",null,null,null,201707060097,"-"]
[243,"대전충남","아산","아산온양#1 T/L","아산S/S 154KV 장기사용 GIS 교체공사","1. 170KV GIS *7BAY GIS 철거설치 2. 제어케이블 철거설치 3. #1SC BAY 인출변경","2017-09-09 09:00","2017-09-10 16:00","2017-09-30T09:00:00","2017-10-03T18:00:00","연속",null,null,null,201705240066,"-"]
[244,"대전충남","아산","아산온양#2 T/L","아산S/S 154KV 장기사용 GIS 교체공사","1. 170KV GIS *7BAY GIS 철거설치 2. 제어케이블 철거설치 3. 온양#2T/L 인출변경 시험가압 (온양#1T/L측으로 이설)","2017-09-30 09:00","2017-10-03 16:00","2017-09-23T09:00:00","2017-09-24T18:00:00","연속",null,null,null,201707110072,"-"]
[245,"대전충남","아산","장재천안#1 T/L","[송전]154kV 장재-천안T/L 일부지중화 공사(요청자 시행)","154kV 장재-천안T/L 일부지중화 공사(요청자 시행)","2017-09-18 09:00","2017-09-22 18:00","2017-09-09T09:00:00","2017-11-30T18:00:00","연속",null,null,null,201707130126,"-"]
[246,"대전충남","아산","장재천안#2 T/L","[송전]154kV 장재-천안T/L 일부지중화 공사(요청자 시행)","154kV 장재-천안T/L 일부지중화 공사(요청자 시행)","2017-09-23 09:00","2017-09-27 18:00","2017-09-09T09:00:00","2017-11-30T18:00:00","연속",null,null,null,201707130127,"-"]
[247,"대전충남","청양","관창보령복합 T/L","154kV 보관T/L 정밀점검","점검구간 : No.1~14, 20~39","2017-09-19 07:00","2017-09-22 18:00","2017-09-19T07:00:00","2017-09-22T18:00:00","매일",null,null,null,201707100374,"-"]
[248,"대전충남","청양","관창보령화력 T/L","154kV 보관T/L 정밀점검","점검구간 : No.1~14, 20~39","2017-09-12 07:00","2017-09-15 18:00","2017-09-12T07:00:00","2017-09-15T18:00:00","매일",null,null,null,201707100372,"-"]
[249,"대전충남","청양","보령복합 T/L","154kV 보관T/L 정밀점검","점검구간 : No.1~2","2017-09-18 07:00","2017-09-18 18:00","2017-09-18T07:00:00","2017-09-18T18:00:00","매일",null,null,null,201707100376,"-"]
[250,"대전충남","청양","서천T/P 154kV #1 BUS TIE CB","서천T/P 170kV GIS 보통점검","-#1BUSTIE 6100 CB 보통점검","2017-09-14 09:00","2017-09-14 18:00","2017-09-20T09:00:00","2017-09-20T18:00:00","당일",null,null,null,201707060006,"-"]
[251,"대전충남","청양","청양신풍#1 T/L","청양S/S 170kV GIS 보통점검","○ GIS 보통점검","2017-09-14 08:00","2017-09-14 18:00","2017-09-14T08:00:00","2017-09-14T18:00:00","당일",null,null,null,201707060018,"-"]
[252,"대전충남","청양","청양신풍#2 T/L","청양S/S 170kV GIS 보통점검","○ GIS 보통점검","2017-09-15 08:00","2017-09-15 18:00","2017-09-15T08:00:00","2017-09-15T18:00:00","당일",null,null,null,201707060019,"-"]
[253,"전북","군산","군산동군산#2 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 2차 공정 - #2BUS 시험가압","2017-09-02 18:00","2017-09-02 19:00","2017-09-02 18:00","2017-09-02 19:00","당일",null,null,null,201707020004,"-"]
[254,"전북","군산","군산동군산#2 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 중 2차 공정 - #1BUS 시험가압 후 BUS 절체(#2 -> #1)","2017-09-14 08:00","2017-09-15 08:00","2017-09-14 08:00","2017-09-15 08:00","연속",null,null,null,201707020005,"-"]
[255,"전북","군산","군산서군산#1 T/L","군산P/O 노후배전반 대체공사","154kV 군산-서군산 #1T/L (양단) 송전선로 보호반 대체","2017-09-25 09:00","2017-09-29 18:00","2017-09-25 09:00","2017-09-29 18:00","연속",null,null,null,201707140038,"-"]
[256,"전북","군산","군산서군산#2 T/L","군산P/O 노후배전반 대체공사","154kV 군산-서군산 #2T/L (양단) 송전선로 보호반 대체","2017-09-18 09:00","2017-09-22 18:00","2017-09-18 09:00","2017-09-22 18:00","연속",null,null,null,201707140039,"-"]
[257,"전북","군산","동군산장항#1 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 2차 공정 - #2BUS 시험가압","2017-09-02 18:00","2017-09-02 19:00","2017-09-02 18:00","2017-09-02 19:00","당일",null,null,null,201706300106,"-"]
[258,"전북","군산","동군산장항#1 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 중 2차 공정 - #1BUS 시험가압 후 BUS 절체(#2 -> #1)","2017-09-14 08:00","2017-09-15 08:00","2017-09-14 08:00","2017-09-15 08:00","연속",null,null,null,201706300108,"-"]
[259,"전북","군산","동군산장항#2 T/L","동군산S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체작업 : 7CCT 중 2차 공정 - 동군산-장항#2T/L, #2M.Tr 1차 GIS","2017-09-01 08:00","2017-09-24 18:00","2017-09-01 08:00","2017-09-24 18:00","연속",null,null,null,201706300103,"-"]
[260,"전북","군산","팔봉두마#1 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 1차 공정 - 팔봉-두마#1T/L, 팔봉-영등#1T/L, BUS TIE, PT&ES교체","2017-09-01 09:00","2017-09-30 18:00","2017-09-01 09:00","2017-09-30 18:00","연속",null,null,null,201707200005,"-"]
[261,"전북","군산","팔봉두마#2 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 1차 공정 -#2BUS 무부하가압 및 모선절체","2017-09-04 16:00","2017-09-05 12:00","2017-09-04 16:00","2017-09-05 12:00","연속",null,null,null,201707200019,"-"]
[262,"전북","군산","팔봉두마#2 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 1차 공정 -#1BUS 무부하가압 및 모선절체","2017-09-16 18:00","2017-09-18 12:00","2017-09-16 18:00","2017-09-18 12:00","연속",null,null,null,201707200021,"-"]
[263,"전북","군산","팔봉두마#2 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 1차 공정 -#2BUS 무부하가압","2017-09-04 16:00","2017-09-05 12:00","2017-09-04 16:00","2017-09-05 12:00","연속",null,null,null,201706200033,"-"]
[264,"전북","군산","팔봉봉동#1 T/L","팔봉봉동#1 T/L 피뢰기설치공사","피뢰기설치 : 5기","2017-09-02 07:00","2017-09-02 18:00","취소","취소","당일",null,null,null,201706130037,"-"]
[265,"전북","군산","팔봉봉동#2 T/L","팔봉봉동#2 T/L 피뢰기설치공사","피뢰기설치 : 5기","2017-09-03 07:00","2017-09-03 18:00","2017-09-03 07:00","2017-09-03 18:00","당일",null,null,null,201707200081,"-"]
[266,"전북","군산","팔봉봉동#2 T/L","팔봉봉동#2 T/L 피뢰기설치공사","피뢰기설치 : 5기","2017-09-03 07:00","2017-09-03 18:00","취소","취소","당일",null,null,null,201707200081,"-"]
[267,"전북","군산","팔봉영등#1 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 1차 공정 - 팔봉-두마#1T/L, 팔봉-영등#1T/L, BUS TIE, PT&ES교체","2017-09-01 09:00","2017-09-30 18:00","취소","취소","연속",null,null,null,201707200006,"-"]
[268,"전북","군산","팔봉영등#1 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 2차 공정 - 팔봉-영등#1T/L, #2M.Tr 1차 교체","2017-09-01 09:00","2017-09-30 18:00","취소","취소","연속",null,null,null,201707110140,"-"]
[269,"전북","김제","백산김제#1 T/L","제작사 점검(유호제 T/L 보호반)","-제작사 시스템 점검","2017-09-06 09:00","2017-09-06 10:30","2017-09-06 09:00","2017-09-06 10:30","당일",null,null,null,201707050097,"-"]
[270,"전북","김제","백산김제#2 T/L","154kV 김제분기T/L 아킹혼 철거 작업","154kV 김제분기T/L 아킹혼 철거 작업","2017-09-04 09:00","2017-09-05 18:00","2017-09-04 09:00","2017-09-05 18:00","매일",null,null,null,201707050073,"-"]
[271,"전북","김제","백산김제#2 T/L","제작사 점검(유호제 T/L보호반)","-제작사 시스템 점검","2017-09-05 10:30","2017-09-05 12:00","2017-09-05 10:30","2017-09-05 12:00","당일",null,null,null,201707050099,"-"]
[272,"전북","김제","신김제남전주#1 T/L","남전주S/S #3M.Tr 1차 차단기 교체공사","GIS 철거 및 설치 안전이격 확보","2017-09-19 09:00","2017-09-20 18:00","2017-09-19 09:00","2017-09-20 18:00","매일",null,null,null,201707190016,"-"]
[273,"전북","김제","신김제남전주#1 T/L","남전주S/S #3M.Tr 1차 차단기 교체공사","GIS 철거 및 설치 안전이격 확보","2017-09-15 09:00","2017-09-17 18:00","2017-09-15 09:00","2017-09-17 18:00","매일",null,null,null,201707190015,"-"]
[274,"전북","김제","신김제남전주#1 T/L","남전주S/S #3M.Tr 1차 차단기 교체공사","GIS 철거 안전이격 확보","2017-09-12 09:00","2017-09-13 18:00","2017-09-12 09:00","2017-09-13 18:00","매일",null,null,null,201707190014,"-"]
[275,"전북","김제","신김제남전주#1 T/L","관내S/S 보호배전반 교체공사","신김제 및 남전주S/S 보호반 교체","2017-09-18 09:00","2017-09-22 18:00","2017-09-18 09:00","2017-09-22 18:00","연속",null,null,null,201706150179,"-"]
[276,"전북","김제","신김제남전주#2 T/L","관내S/S 보호배전반 교체공사","신김제 및 남전주S/S 보호반 교체","2017-09-25 09:00","2017-09-28 18:00","2017-09-25 09:00","2017-09-28 18:00","연속",null,null,null,201706150180,"-"]
[277,"전북","김제","신김제정공#2 T/L","관내S/S 보호배전반 교체공사","신김제 및 남전주S/S 보호반 교체","2017-09-11 09:00","2017-09-15 18:00","2017-09-11 09:00","2017-09-15 18:00","연속",null,null,null,201706150181,"-"]
[278,"전북","김제","이리백산#1 T/L","제작사 점검(유호제 T/L보호반)","-제작사 시스템 점검","2017-09-06 13:00","2017-09-06 14:00","2017-09-06 13:00","2017-09-06 14:00","당일",null,null,null,201707050100,"-"]
[279,"전북","김제","이리백산#2 T/L","154kV 김제분기T/L 아킹혼 철거 작업(안전이격거리 확보)","154kV 김제분기T/L 아킹혼 철거 작업(안전이격거리 확보)","2017-09-04 09:00","2017-09-05 18:00","2017-09-04 09:00","2017-09-05 18:00","매일",null,null,null,201707050074,"-"]
[280,"전북","김제","이리백산#2 T/L","제작사 점검(유호제 T/L보호반)","-제작사 시스템 점검","2017-09-05 14:30","2017-09-05 18:00","2017-09-05 14:30","2017-09-05 18:00","당일",null,null,null,201707050102,"-"]
[281,"전북","김제","정공정주#1 T/L","김제P/O 170KV GIS 정밀점검공사","정공-정주#1T/L GIS 내부정밀점검","2017-09-15 09:00","2017-09-17 18:00","2017-09-16 09:00","2017-09-17 18:00","연속",null,null,null,201707070212,"-"]
[282,"전북","김제","정공정주#2 T/L","154kV 정공-정주T/L 아킹혼 철거 작업","154kV 정공-정주T/L 아킹혼 철거 작업","2017-09-23 09:00","2017-09-24 18:00","2017-09-23 09:00","2017-09-24 18:00","매일",null,null,null,201707050075,"-"]
[283,"전북","김제","정주고창#1 T/L","154kV 정주-고창T/L 안전이격거리 확보공사","정주-고창#1T/L 철탑 이설 및 전력선 교체 철탑교체 : No.25,31,35호 전력선 교체 : No.24~26, 28~33, 34~37호","2017-09-03 07:00","2017-09-13 18:00","2017-09-03 07:00","2017-09-13 18:00","연속",null,null,null,201707170063,"-"]
[284,"전북","김제","정주고창#1 T/L","154kV 고창S/S #3 M.Tr 1차 리드선 교체","#3 M.Tr 1차 리드선 교체","2017-09-01 09:00","2017-09-01 18:00","2017-09-01 09:00","2017-09-01 18:00","당일",null,null,null,201707040207,"-"]
[285,"전북","김제","정주고창#1 T/L","154kV 정주-고창T/L 안전이격거리 확보공사","정주-고창#1T/L 철탑 이설 및 전력선 교체 철탑교체 : No.25,31,35호 전력선 교체 : No.24~26, 28~33, 34~37호","2017-09-24 07:00","2017-09-30 18:00","2017-09-24 07:00","2017-09-30 18:00","연속",null,null,null,201707170065,"-"]
[286,"전북","김제","정주고창#2 T/L","154kV 정주-고창T/L 안전이격거리 확보공사","정주-고창#2T/L 철탑 이설 및 전력선 교체 철탑교체 : No.25,31,35호 전력선 교체 : No.24~26, 28~33, 34~37호","2017-09-14 07:00","2017-09-23 18:00","2017-09-14 07:00","2017-09-23 18:00","연속",null,null,null,201707170064,"-"]
[287,"광주전남","강진","해남진도#1 T/L","154kV 해남진도#1T/L(현수애자 금구류 점검)","154kV 해남진도#1T/L(현수애자 금구류 점검) -2017년도 가공송전 순시점검 위탁공사","2017-09-12 09:00","2017-09-14 18:00","2017-09-12 09:00","2017-09-14 18:00","매일",null,null,null,201707200097,"-"]
[288,"광주전남","강진","해남진도#2 T/L","154kV 해남진도#2T/L(불량애자 교체)","154kV 해남진도#2T/L(불량애자 교체) -2017년도 가공송전 순시점검 위탁공사","2017-09-11 09:00","2017-09-11 18:00","2017-09-11 09:00","2017-09-11 18:00","당일",null,null,null,201707200093,"-"]
[289,"광주전남","강진","화원진도#1 T/L","154kV 화원-안좌#1T/L(정밀점검)","154kV 화원-안좌#1T/L(정밀점검)관련 4회선 병가구간 안전상 휴전 및 피뢰기공사 병행작업","2017-09-18 07:00","2017-09-20 18:00","2017-09-18 07:00","2017-09-20 18:00","매일",null,null,null,201707130089,"-"]
[290,"광주전남","강진","화원진도#2 T/L","154kV 화원-안좌#2T/L(정밀점검)","154kV 화원-안좌#2T/L(정밀점검)관련 4회선 병가구간 안전상 휴전","2017-09-21 07:00","2017-09-22 18:00","2017-09-21 07:00","2017-09-22 18:00","매일",null,null,null,201707130090,"-"]
[291,"광주전남","광주","곡성남원#1 T/L","곡성S/S 154kV 신광주-곡성#1T/L GIS 교체공사","곡성S/S 154kV #1BUS 무부하가압","2017-09-19 18:00","2017-09-20 18:00","2017-09-19 18:00","2017-09-20 18:00","연속",null,null,null,201707100092,"-"]
[292,"광주전남","광주","곡성남원#1 T/L","곡성S/S 154kV 신광주-곡성#1T/L GIS 교체공사","곡성S/S 154kV #2BUS 무부하가압","2017-09-13 09:00","2017-09-13 10:00","2017-09-13 09:00","2017-09-13 10:00","당일",null,null,null,201707100091,"-"]
[293,"광주전남","광주","신광주계림#1 T/L","신광주 취약설비 GIS화 관련 점검","-게림#1T/L 피뢰기 점검","2017-09-12 08:00","2017-09-12 13:00","2017-09-12 08:00","2017-09-12 13:00","당일",null,null,null,201707070084,"○"]
[294,"광주전남","광주","신광주계림#2 T/L","축소형 모자익 교체에 따른 연동시험","축소형 모자익 교체에 따른 연동시험","2017-09-15 11:00","2017-09-15 12:00","2017-09-15 11:00","2017-09-15 12:00","당일",null,null,null,201707100136,"○"]
[295,"광주전남","광주","신광주곡성#1 T/L","곡성S/S 154kV 신광주-곡성#1T/L GIS 교체공사","곡성S/S 154kV 신광주-곡성#1T/L GIS 교체공사","2017-09-11 09:00","2017-09-27 18:00","2017-09-11 09:00","2017-09-27 18:00","연속",null,null,null,201707100084,"-"]
[296,"광주전남","광주","신광주곡성#2 T/L","축소형 모자익 교체에 따른 연동시험","축소형 모자익 교체에 따른 연동시험","2017-09-09 09:00","2017-09-09 11:00","2017-09-09 09:00","2017-09-09 11:00","당일",null,null,null,201707100138,"-"]
[297,"광주전남","광주","신광주일곡#1 T/L","축소형 모자익 교체에 따른 연동시험","축소형 모자익 교체에 따른 연동시험","2017-09-15 09:00","2017-09-15 10:00","2017-09-15 09:00","2017-09-15 10:00","당일",null,null,null,201707100133,"○"]
[298,"광주전남","광주","신광주일곡#2 T/L","신광주 취약설비 GIS화 관련 점검","-알곡#2T/L 피뢰기 점검","2017-09-12 13:00","2017-09-12 18:00","2017-09-12 13:00","2017-09-12 18:00","당일",null,null,null,201707070085,"○"]
[299,"광주전남","광주","신광주장성#1 T/L","신광주S/S Sh.C전력케이블설치 공사","#1.2.3 Sh.C GIS 인출용 케이블 헤드 설치","2017-09-14 09:00","2017-09-14 18:00","2017-09-14 09:00","2017-09-14 18:00","당일",null,null,null,201707070079,"-"]
[300,"광주전남","광주","신광주장성#2 T/L","축소형 모자익 교체에 따른 연동시험","축소형 모자익 교체에 따른 연동시험","2017-09-15 08:00","2017-09-15 09:00","2017-09-15 08:00","2017-09-15 09:00","당일",null,null,null,201707100131,"-"]
[301,"광주전남","광주","신화순평동(구,신화순나주#1) T/L","신화순평동(구,신화순나주#1) T/L(변전협력회사공사)","GIS 보통점검","2017-09-26 09:00","2017-09-26 18:00","2017-09-26 09:00","2017-09-26 18:00","당일",null,null,null,201707170093,"-"]
[302,"광주전남","목포","나주엄다#1 T/L","154kV 나주-엄다#1T/L(장기 미동작 차단기 점검)","장기 미동작 차단기 점검","2017-09-20 09:00","2017-09-20 13:00","2017-09-20 09:00","2017-09-20 13:00","당일",null,null,null,201707180157,"-"]
[303,"광주전남","목포","나주엄다#2 T/L","154kV 나주-엄다#1T/L(장기 미동작 차단기 점검)","장기 미동작 차단기 점검","2017-09-20 13:00","2017-09-20 18:00","2017-09-20 13:00","2017-09-20 18:00","당일",null,null,null,201707180158,"-"]
[304,"광주전남","목포","장성영광#1 T/L","154kV 남악-북항 등 5개T/L 피뢰기 설치공사","154kV 장성-영광#1T/L 피뢰기 설치공사 ○ 송전용 피뢰기 설치 : 57기 171set","2017-09-26 07:00","2017-09-29 18:00","2017-10-10 07:00","2017-10-13 18:00","매일",null,null,null,201707170006,"-"]
[305,"광주전남","순천","호남TP여수TP#1 T/L","16~17년 변전협력회사 총액공사","여수화력S/Y 154kV 호남TP-여수TP#1T/L GIS 유압시스템 점검","2017-09-14 10:00","2017-09-14 18:00","2017-09-14 10:00","2017-09-14 18:00","당일",null,null,null,201707270125,"-"]
[306,"광주전남","순천","여수TP여천#1 T/L","154kV 여수TP-여천#1 T/L 송전선 순시점검","2017년 가공송전 순시점검 위탁공사 - 정밀점검 (1호~15호, 15기)","2017-09-25 08:00","2017-09-26 18:00","2017-09-25 08:00","2017-09-26 18:00","매일",null,null,null,201707180020,"-"]
[307,"광주전남","순천","여수TP여천#2 T/L","154kV 여수TP-여천#2 T/L 송전선 순시점검","2017년 가공송전 순시점검 위탁공사 - 정밀점검 (1호~15호, 15기)","2017-09-21 08:00","2017-09-22 18:00","2017-09-21 08:00","2017-09-22 18:00","매일",null,null,null,201707180022,"-"]
[308,"광주전남","직할","농성화정#2 T/L","154kV 농성S/S 농성-화정#2T/L(장기미동작 조작시험)","17년 직할 변전협력회사 총액공사 농성S/S 농성-화정#2T/L GIS 장기미동작 조작시험","2017-09-11 09:00","2017-09-11 18:00","2017-09-11 09:00","2017-09-11 18:00","당일",null,null,null,201707170004,"-"]
[309,"광주전남","직할","하남장성#1 T/L","154kV 하남-장성#1T/L 피뢰기 설치공사","○ 하남-장성#1T/L No.4,7호(2기) 피뢰기설치(비아하남#1T/L No.68,71 병가)","2017-09-13 08:00","2017-09-13 12:00","2017-09-10 08:00","2017-09-10 12:00","당일",null,null,null,201707060008,"-"]
[310,"광주전남","직할","하남장성#2 T/L","154kV 하남-장성#2T/L(노후 LA 대체)","17년 직할 변전협력회사 총액공사 - 하남-장성#2T/L 노후 LA 대체","2017-09-10 09:00","2017-09-10 18:00","2017-09-10 12:00","2017-09-10 18:00","당일",null,null,null,201706200078,"-"]
[311,"대구","경산","대구범물#1 T/L","범물S/S 대구-범물#1T/L 휴전","범물S/S 154kV 모선보호반 대체","2017-09-22 10:00","2017-09-22 10:30","2017-09-23 10:00","2017-09-23 10:30","당일",null,null,null,201707100385,"-"]
[312,"대구","경산","대구범물#2 T/L","범물S/S 대구-범물#2T/L 휴전","범물S/S 154kV 모선보호반 대체","2017-09-22 10:30","2017-09-22 11:00","2017-09-23 10:30","2017-09-23 11:00","당일",null,null,null,201707100386,"-"]
[313,"대구","경산","범물남대구#1 T/L","범물S/S 범물-남대구#1T/L 휴전","범물S/S 154kV 모선보호반 대체","2017-09-22 09:00","2017-09-22 09:30","2017-09-23 09:00","2017-09-23 09:30","당일",null,null,null,201707100383,"-"]
[314,"대구","경산","범물남대구#2 T/L","범물S/S 범물-남대구#2T/L 휴전","범물S/S 154kV 모선보호반 대체","2017-09-22 09:30","2017-09-22 10:00","2017-09-23 09:30","2017-09-23 10:00","당일",null,null,null,201707100384,"-"]
[315,"대구","경산","신경산S/S 154kV #61 BUS","신경산S/S 170kV 장기사용 GIS 대체(5차 공정)","4Bay 동시대체(677, 687, 6200, 6344)관련 #61BUS측 GIS 철거 및 설치","2017-09-07 09:00","2017-09-19 09:00","2017-09-12 09:00","2017-09-23 09:00","연속",null,null,null,201707190064,"-"]
[316,"대구","경산","신경산S/S 154kV #66 BUS","신경산S/S 170kV 장기사용 GIS 대체(5차 공정)","4Bay 동시대체(677, 687, 6200, 6344)관련 #66BUS측 GIS 철거 및 설치","2017-09-19 09:00","2017-09-28 10:00","2017-09-23 09:00","2017-10-14 09:00","연속",null,null,null,201707190066,"-"]
[317,"대구","경산","신경산청통#1 T/L","17년 신경산S/S 170kV 장기사용 GIS 대체(5차 공정)","신경산-청통#1, 2T/L 및 6200, 6344 GIS 대체(4Bay 동시)","2017-09-04 09:00","2017-09-29 18:00","2017-09-09 09:00","2017-10-15 14:00","연속",null,null,null,201707060056,"-"]
[318,"대구","경산","신경산청통#2 T/L","17년 신경산S/S 170kV 장기사용 GIS 대체(5차 공정)","신경산-청통#1, 2T/L 및 6200, 6344 GIS 대체(4Bay 동시)","2017-09-04 09:00","2017-09-29 18:00","2017-09-09 09:00","2017-10-15 14:00","연속",null,null,null,201707060057,"-"]
[319,"대구","달성","달서팔달#2 T/L","달서S/S GIS 대체공사","달서S/S GIS 대체공사","2017-09-08 09:00","2017-09-27 13:00","2017-09-08 09:00","2017-09-27 13:00","연속",null,null,null,201707070362,"-"]
[320,"대구","달성","대구청도#1 T/L","154kV 대구-청도T/L 장기사용지지물 교체공사","154kV 대구-청도T/L 31,32호 철탑교체 2기 (가철탑 2기) - 전력선 교체 26~33호","2017-09-06 08:00","2017-09-22 18:00","2017-09-13 07:00","2017-09-25 18:00","연속",null,null,null,201707040036,"-"]
[321,"대구","달성","대구청도#2 T/L","154kV 대구-청도T/L 장기사용지지물 교체공사","154kV 대구-청도T/L 31,32호 철탑교체 2기 (가철탑 2기) - 전력선 교체 26~33호","2017-09-23 08:00","2017-09-29 18:00","2017-09-26 07:00","2017-10-02 18:00","연속",null,null,null,201707040038,"-"]
[322,"대구","달성","대구청도#2 T/L","154kV 대구-청도T/L 장기사용지지물 교체공사","154kV 대구-청도T/L 31,32호 철탑교체 2기 (가철탑 2기) - 전력선 교체 26~33호","2017-09-01 08:00","2017-09-05 18:00","2017-09-08 07:00","2017-09-12 18:00","연속",null,null,null,201707040035,"-"]
[323,"대구","달성","상인봉덕#1 T/L","송전선로 정밀점검","154kV 상인-봉덕#1T/L 송전선로 정밀점검","2017-09-18 08:00","2017-09-19 18:00","2017-09-18 08:00","2017-09-19 18:00","연속",null,null,null,201707100192,"-"]
[324,"대구","달성","상인봉덕#2 T/L","송전선로 정밀점검","154kV 상인-봉덕#2T/L 송전선로 정밀점검","2017-09-20 08:00","2017-09-21 18:00","2017-09-20 08:00","2017-09-21 18:00","연속",null,null,null,201707100197,"-"]
[325,"대구","달성","성서달성#1 T/L","성서-달성T/L 접속개소 전력선 교체공사","- 성서-달성T/L No.16-20 접속개소 전력선 교체공사","2017-09-30 07:00","2017-10-02 18:00","2017-09-30 07:00","2017-10-02 18:00","연속",null,null,null,201707060020,"-"]
[326,"대구","직할","내당두류#1 T/L","차단기 개폐타임 측정","차단기 개폐타임 측정","2017-09-29 11:00","2017-09-29 14:00","취소","취소","당일",null,null,null,201707060170,"-"]
[327,"대구","직할","내당두류#2 T/L","차단기 개폐타임 측정","차단기 개폐타임 측정","2017-09-29 14:00","2017-09-29 16:00","취소","취소","당일",null,null,null,201707060171,"-"]
[328,"대구","직할","노변효목#1 T/L","보호반 교체","보호반 교체","2017-09-25 09:30","2017-09-27 14:00","2017-09-28 09:30","2017-09-28 10:00","연속",null,null,null,201707060173,"-"]
[329,"대구","직할","노변효목#2 T/L","보호반 교체","보호반 교체","2017-09-27 14:00","2017-09-29 18:00","2017-09-28 10:00","2017-09-28 10:30","연속",null,null,null,201707060174,"-"]
[330,"대구","직할","동인내당#2 T/L","OF케이블 선종교체공사(대상:154kV 동인내당 2T/L)","동인S/S 인출 OF케이블 교체공사","2017-09-09 08:00","2017-09-30 18:00","2017-09-09 08:00","2017-09-30 18:00","연속",null,null,null,201707070086,"-"]
[331,"대구","칠곡","북대구S/S 154kV #61 BUS","2017년 칠곡전력지사 차단기 정밀점검공사","2017년 칠곡전력지사 차단기 정밀점검공사","2017-09-21 09:30","2017-09-23 18:00","2017-09-21 09:30","2017-09-23 18:00","연속",null,null,null,201707140095,"-"]
[332,"경북","구미","선산청리#1 T/L","선산S/S 154kV 옥외철구 설비 GIS화 공사","GIS 기초 파일시공","2017-09-06 08:00","2017-09-10 18:00","2017-09-06 08:00","2017-09-10 18:00","연속",null,null,null,201707070319,"-"]
[333,"경북","구미","선산청리#2 T/L","선산S/S 154kV 옥외철구 설비 GIS화 공사","GIS 기초 파일시공","2017-09-01 08:00","2017-09-05 18:00","2017-09-01 08:00","2017-09-05 18:00","연속",null,null,null,201707070318,"-"]
[334,"경북","영주","신영주안동#1 T/L","154kV신영주-안동T/L 항공장애구 설치공사","항공장애표시구 설치","2017-09-18 08:00","2017-09-22 18:00","2017-09-18 08:00","2017-09-22 18:00","연속",null,null,null,201707100297,"○"]
[335,"경북","영주","신영주안동#2 T/L","2016-17년도 영주 송전정비 협력회사 총액공사","154kV 신영주-안동#2T/L 송전선로 피뢰기 설치","2017-09-23 07:00","2017-09-27 18:00","2017-09-23 07:00","2017-09-27 18:00","연속",null,null,null,201707100299,"○"]
[336,"경북","영주","신영주예천#2 T/L","2017년 예천S/S 170kV 장기사용 GIS 대체(1차 공정)","신영주-예천#2T/L 617, #2M.Tr 1차 6233 GIS 대체(2Bay 동시)","2017-09-08 09:00","2017-09-28 18:00","2017-09-08 09:00","2017-09-28 18:00","연속",null,null,null,201707090004,"○"]
[337,"경북","영주","예천S/S 154kV #1 BUS","2017년 예천S/S 170kV 장기사용 GIS 대체(#1DS철거/설치)","신영주-예천#2T/L 617, #2M.Tr 1차 6233 GIS 대체(2Bay 동시) 관련 #1DS(6231, 611) 철거 및 재설치","2017-09-12 10:00","2017-09-21 10:00","2017-09-12 10:00","2017-09-21 10:00","연속",null,null,null,201707090008,"-"]
[338,"경북","영주","예천점촌#2 T/L","2017년 예천S/S 170kV 장기사용 GIS 대체(1차 공정)","1. #2M.Tr 1차 6233 GIS 대체관련 안전이격 확보_2. 617, 6233 GIS 대체(2Bay 동시)관련 무부하 가압 Test T/L","2017-09-08 09:00","2017-09-28 18:00","2017-09-08 09:00","2017-09-28 18:00","연속",null,null,null,201707090006,"-"]
[339,"경북","직할","군위의성#1 T/L","의성S/S 옥외철구 설비 GIS화 공사","170kV GIS 설치(안전확보)","2017-09-06 08:00","2017-09-07 18:00","2017-09-06 08:00","2017-09-07 18:00","매일",null,null,null,201707100048,"-"]
[340,"경북","직할","군위의성#1 T/L","의성S/S 옥외철구 설비 GIS화 공사","170kV GIS 설치(안전확보)","2017-09-12 08:00","2017-09-12 18:00","2017-09-12 08:00","2017-09-12 18:00","매일",null,null,null,201707100075,"-"]
[341,"경북","직할","군위의성#1 T/L","의성S/S 옥외철구 설비 GIS화 공사","170kV GIS 설치(안전확보)","2017-09-25 08:00","2017-09-25 18:00","2017-09-25 08:00","2017-09-25 18:00","당일",null,null,null,201707100079,"-"]
[342,"경북","직할","군위의성#2 T/L","의성S/S 옥외철구 설비 GIS화 공사","170kV GIS 설치(안전확보)","2017-09-06 08:00","2017-09-07 18:00","2017-09-06 08:00","2017-09-07 18:00","매일",null,null,null,201707100050,"-"]
[343,"경북","직할","군위의성#2 T/L","의성S/S 옥외철구 설비 GIS화 공사","170kV GIS 설치(안전확보)","2017-09-12 08:00","2017-09-12 18:00","2017-09-12 08:00","2017-09-12 18:00","매일",null,null,null,201707100076,"-"]
[344,"경북","직할","군위의성#2 T/L","의성S/S 옥외철구 설비 GIS화 공사","170kV GIS 설치(안전확보)","2017-09-25 08:00","2017-09-25 18:00","2017-09-25 08:00","2017-09-25 18:00","당일",null,null,null,201707100080,"-"]
[345,"경북","직할","동안동임하HP T/L","154kV 울진-평해 등 3개T/L 항공장애구 설치공사","동안동-임하T/L(애자교체 병행), 구간 : No. 15, 16, 17, 18, 21, 22, 23, 25, 29, 수량 : GW 및 OPGW 57구","2017-09-19 07:00","2017-09-21 18:00","2017-09-19 07:00","2017-09-21 18:00","매일",null,null,null,201707070387,"-"]
[346,"경북","직할","안계의성#1 T/L","의성S/S 옥외철구 설비 GIS화 공사","170kV GIS 설치(안전확보)","2017-09-04 08:00","2017-09-05 18:00","2017-09-04 08:00","2017-09-05 18:00","매일",null,null,null,201707100043,"-"]
[347,"경북","직할","안계의성#1 T/L","의성S/S 옥외철구 설비 GIS화 공사","170kV GIS 설치(안전확보)","2017-09-11 08:00","2017-09-11 18:00","2017-09-11 08:00","2017-09-11 18:00","매일",null,null,null,201707100074,"-"]
[348,"경북","직할","안계의성#2 T/L","의성S/S 옥외철구 설비 GIS화 공사","170kV GIS 설치(안전확보)","2017-09-04 08:00","2017-09-05 18:00","2017-09-04 08:00","2017-09-05 18:00","매일",null,null,null,201707100046,"-"]
[349,"경북","직할","안계의성#2 T/L","의성S/S 옥외철구 설비 GIS화 공사","170kV GIS 설치(안전확보)","2017-09-11 08:00","2017-09-11 18:00","2017-09-11 08:00","2017-09-11 18:00","매일",null,null,null,201707100073,"-"]
[350,"부산울산","동부산","구서노포#1 T/L","154kV 울주-직동 등 4개 T/L 송전선로용 피뢰기 설치공사","154kV 구서-노포#1T/L 피뢰기 설치 : 13~18호","2017-09-16 09:00","2017-09-16 18:00","2017-09-16 09:00","2017-09-16 18:00","당일",null,null,null,201707100112,"-"]
[351,"부산울산","동부산","구서명장#1 T/L","154kV 울주-직동 등 4개T/L 피뢰기 설치공사","피뢰기 설치 : 1~13호","2017-09-27 09:00","2017-09-28 18:00","2017-09-27 09:00","2017-09-28 18:00","연속",null,null,null,201707140076,"-"]
[352,"부산울산","동부산","노포정관#2 T/L","154kV 울주-직동 등 4개 T/L 송전선로용 피뢰기 설치공사","154kV 구서-노포#1T/L 피뢰기 설치관련 안전이격","2017-09-16 09:00","2017-09-16 18:00","2017-09-16 09:00","2017-09-16 18:00","당일",null,null,null,201707100113,"-"]
[353,"부산울산","동부산","우동대연 T/L","154kV 우동 등 3개S/S 지중송전케이블 선종교체공사","우동S/S EBG ~ J/B#1 OF 1200(D) ---&gtXLPE 1200(D), 0.303km 케이블 선종교체","2017-09-10 09:00","2017-10-21 18:00","2017-09-10 09:00","2017-10-21 18:00","연속",null,null,null,201707070154,"-"]
[354,"부산울산","동부산","정관S/S 154KV#1 BUS TIE CB","정관S/S 170kV GIS 보통점검","정관S/S 170kV 6100 GIS 보통점검","2017-09-18 09:30","2017-09-18 17:00","2017-09-18 09:30","2017-09-18 17:00","당일",null,null,null,201707100480,"-"]
[355,"부산울산","북부산","김해어방 T/L","154kV 어방S/S SW증설공사","어방S/S #2BUS 시험가압 (154kV GIS 2CCT 설치/신설 #2DS투입, CB 개방)","2017-09-29 15:00","2017-09-30 15:00","2017-09-29 15:00","2017-09-30 15:00","연속",null,null,null,201707100129,"-"]
[356,"부산울산","북부산","김해어방 T/L","154kV 어방S/S SW증설공사","어방 S/S #1BUS 시험가압 (154kV GIS 2CCT 설치/ 신설 #1DS,CB OPEN)","2017-09-22 15:00","2017-09-23 15:00","2017-09-22 15:00","2017-09-23 15:00","연속",null,null,null,201707100128,"-"]
[357,"부산울산","북부산","매리김해#1 T/L","2017년 북부산 154kV GIS 정밀점검 공사","김해S/S 매리-김해#1T/L (617) GIS 정밀점검","2017-09-14 09:00","2017-09-16 15:00","2017-09-14 09:00","2017-09-16 15:00","연속",null,null,null,201707100368,"-"]
[358,"부산울산","북부산","매리김해#2 T/L","2017년 북부산 154kV GIS 정밀점검 공사","김해S/S 매리-김해#2T/L (627) GIS 정밀점검","2017-09-17 09:00","2017-09-19 15:00","2017-09-17 09:00","2017-09-19 15:00","연속",null,null,null,201707100369,"-"]
[359,"부산울산","북부산","물금S/S 154KV #1 BUS TIE CB","154kV 물금분기T/L SW 증설공사(시험가압)","물금S/S 154kV GIS * 2CCT 설치 (#2BUS~C/H 시험가압)","2017-09-24 19:00","2017-09-25 18:00","2017-09-24 19:00","2017-09-25 18:00","연속",null,null,null,201707070398,"-"]
[360,"부산울산","북부산","북부산구포#2 T/L","북부산S/S 154kV 취약설비 GIS화 공사","북부산S/S 북부산-구포#2T/L 인출변경 6B7 휴전","2017-09-22 08:00","2017-10-18 18:00","2017-09-22 08:00","2017-10-18 18:00","연속",null,null,null,201707100254,"-"]
[361,"부산울산","북부산","북부산구포#3 T/L","북부산S/S 154kV 취약설비 GIS화 공사","북부산S/S 북부산-구포#3T/L 인출변경 667 휴전","2017-09-09 08:00","2017-09-21 18:00","2017-09-09 08:00","2017-09-21 18:00","연속",null,null,null,201707100257,"-"]
[362,"부산울산","북부산","북부산삼랑진PP#2 T/L","154kV 물금분기 지중T/L 건설사업","-공사목적: 경상남도 양산시 중서부지역 계통보강 -위치 : 경상남도 양산시 물금읍 범어리 일원 -선로구간 : 154kV 물금S/S(옥내) ∼ J/B#3 -선종 및 회선수 : 154kV XLPE 2,500㎟ / 2회선-0.5km","2017-09-09 10:00","2017-09-29 18:00","2017-09-09 10:00","2017-09-29 18:00","연속",null,null,null,201707070100,"-"]
[363,"부산울산","북부산","호포매리#2 T/L","154kV 북부산-미남 등 8개T/L 피뢰기 설치공사","- 피뢰기설치공사 : 호포-매리#2T/L No.2-1,2-2,3,4,5호 5기","2017-09-10 07:00","2017-09-10 18:00","2017-09-10 07:00","2017-09-10 18:00","당일",null,null,null,201707070061,"-"]
[364,"부산울산","북부산","호포물금 T/L","154kV 물금분기T/L SW 증설공사(시험가압)","물금S/S 154kV GIS * 2CCT 설치 (#2BUS 시험가압 선로)","2017-09-24 18:00","2017-09-24 19:00","2017-09-24 18:00","2017-09-24 19:00","당일",null,null,null,201707070399,"-"]
[365,"부산울산","울산","동울산방어진 T/L","154kV 현대#1T/L 전선교체공사(안전확보)","ㅁ 154kV 현대#1T/L 전선접속개소 전선교체공사 관련 병가구간 안전 확보(실작업 없음)","2017-09-17 06:00","2017-09-17 14:00","2017-09-17 06:00","2017-09-17 14:00","당일",null,null,null,201707050028,"-"]
[366,"부산울산","울산","방어진영남TP#2 T/L","2017년 울산P/O 개폐장치 정밀점검공사","방어진S/S 170kV 6433 GIS 정밀점검관련 시험가압","2017-09-15 17:00","2017-09-15 18:00","2017-09-15 17:00","2017-09-15 18:00","당일",null,null,null,201707100207,"-"]
[367,"부산울산","울산","신온산온산#3 T/L","2017년 울산P/O 개폐장치 정밀점검공사","신온산S/S 170kV 696,697 GIS 정밀점검","2017-09-09 08:00","2017-09-10 18:00","2017-09-09 08:00","2017-09-10 18:00","연속",null,null,null,201707100199,"-"]
[368,"부산울산","울산","신울산S/S 154kV #63 BUS","2016~17년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV 6N1DS 점검 및 조정","2017-09-18 08:00","2017-09-18 14:00","2017-09-18 08:00","2017-09-18 14:00","당일",null,null,null,201707100303,"○"]
[369,"부산울산","울산","신울산S/S 154kV #67 BUS","2016~17년 울산전력지사 변전협력회사 총액공사","신울산S/S 170kV 6L2DS 접점점검 및 불량 조작함 교체","2017-09-09 09:00","2017-09-09 18:00","2017-09-09 09:00","2017-09-09 18:00","당일",null,null,null,201707100261,"-"]
[370,"부산울산","울산","신울산S/S 60-61-0 SEC CB","2016~17년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV 60-61-0 CB 보통점검","2017-09-13 09:00","2017-09-13 18:00","2017-09-13 09:00","2017-09-13 18:00","당일",null,null,null,201707100309,"-"]
[371,"부산울산","울산","신울산S/S 65-66-0 SEC CB","2016~17년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV 65-66-0 CB 보통점검","2017-09-28 09:00","2017-09-28 18:00","2017-09-28 09:00","2017-09-28 18:00","당일",null,null,null,201707100310,"-"]
[372,"부산울산","울산","신울산언양#1 T/L","154kV 신울산-언양T/L 전선접속개소 전선교체공사","ㅁ 전력선 교체 : 154kV 신울산-언양#1 T/L No.56~64","2017-09-18 07:00","2017-09-20 19:00","2017-09-18 07:00","2017-09-20 19:00","연속",null,null,null,201707070210,"-"]
[373,"부산울산","울산","신울산언양#2 T/L","154kV 신울산-언양T/L 전선접속개소 전선교체공사","ㅁ 전력선 교체 : 154kV 신울산-언양#2 T/L No.56~64","2017-09-21 06:00","2017-09-23 19:00","2017-09-21 06:00","2017-09-23 19:00","연속",null,null,null,201707070216,"-"]
[374,"부산울산","울산","신울산영남TP#1 T/L","154kV 두왕분기T/L 건설공사","1. 목적 : 154kV 두왕분기T/L 건설공사 관련 가선로 구성 2. 공사구간 : 154kV 신울산-영남TP T/L 36 ~ 38호 (안전이격)","2017-09-21 07:00","2017-09-22 19:00","2017-09-21 07:00","2017-09-22 19:00","매일",null,null,null,201707040047,"-"]
[375,"부산울산","울산","신울산영남TP#1 T/L","154kV 두왕분기T/L 건설공사","1. 목적 : 154kV 두왕분기T/L 건설공사 관련 가선로 구성 2. 공사구간 : 154kV 신울산-영남TP T/L 36 ~ 38호 (안전이격, 동시휴전)","2017-09-25 07:00","2017-09-26 19:00","2017-09-25 07:00","2017-09-26 19:00","매일",null,null,null,201707040057,"-"]
[376,"부산울산","울산","신울산영남TP#1 T/L","154kV 두왕분기T/L 건설공사","1. 목적 : 154kV 두왕분기T/L 건설공사 관련 가선로 구성 2. 공사구간 : 154kV 신울산-영남TP T/L 36 ~ 38호 (본 휴전)","2017-09-27 07:00","2017-09-28 19:00","2017-09-27 07:00","2017-09-28 19:00","연속",null,null,null,201707040059,"-"]
[377,"부산울산","울산","신울산영남TP#2 T/L","154kV 두왕분기T/L 건설공사","1. 목적 : 154kV 두왕분기T/L 건설공사 관련 가선로 구성 2. 공사구간 : 154kV 신울산-영남TP T/L 36 ~ 38호 (본 휴전)","2017-09-23 07:00","2017-09-24 19:00","2017-09-23 07:00","2017-09-24 19:00","연속",null,null,null,201707040050,"-"]
[378,"부산울산","울산","신울산영남TP#2 T/L","154kV 두왕분기T/L 건설공사","1. 목적 : 154kV 두왕분기T/L 건설공사 관련 가선로 구성 2. 공사구간 : 154kV 신울산-영남TP T/L 36 ~ 38호 (안전이격, 동시휴전)","2017-09-25 07:00","2017-09-26 19:00","2017-09-25 07:00","2017-09-26 19:00","매일",null,null,null,201707170159,"-"]
[379,"부산울산","울산","신울산영남TP#2 T/L","2016~17년 울산전력지사 변전협력회사 총액공사","신울산S/S 170kV 6L2DS 접점점검 및 불량 조작함 교체","2017-09-09 09:00","2017-09-09 18:00","2017-09-09 09:00","2017-09-09 18:00","당일",null,null,null,201707100260,"-"]
[380,"부산울산","울산","신울산울산#1 T/L","154kV 두왕분기T/L 건설공사","1. 목적 : 154kV 두왕분기T/L 건설공사 관련 가선로 구성 2. 공사구간 : 154kV 신울산-울산 T/L 5 ~ 7호 (본 휴전)","2017-09-21 07:00","2017-09-22 19:00","2017-09-21 07:00","2017-09-22 19:00","연속",null,null,null,201707040037,"○"]
[381,"부산울산","울산","신울산울산#2 T/L","2016~17년 울산전력지사 변전협력회사 총액공사","1.신울산S/S 154kV 6N7 ILC PNL 대체 2.신울산S/S 170kV 6N7 GCB 보통점검 3.울산S/S 170kV 647 GIS 보통점검 4.신울산S/S 154kV 6N7 CVT 대체 및 LA 보통점검","2017-09-18 08:00","2017-09-19 18:00","2017-09-18 08:00","2017-09-19 18:00","연속",null,null,null,201707100300,"-"]
[382,"부산울산","울산","신울산울산#2 T/L","154kV 두왕분기T/L 건설공사","1. 목적 : 154kV 두왕분기T/L 건설공사 관련 가선로 구성 2. 공사구간 : 154kV 신울산-울산 T/L 5 ~ 7호 (안전이격)","2017-09-23 07:00","2017-09-24 19:00","2017-09-23 07:00","2017-09-24 19:00","매일",null,null,null,201707040052,"-"]
[383,"부산울산","울산","신울산울산#2 T/L","154kV 두왕분기T/L 건설공사","1. 목적 : 154kV 두왕분기T/L 건설공사 관련 가선로 구성 2. 공사구간 : 154kV 신울산-울산 T/L 5 ~ 7호 (본휴전)","2017-09-25 07:00","2017-09-26 19:00","2017-09-25 07:00","2017-09-26 19:00","연속",null,null,null,201707040055,"-"]
[384,"부산울산","울산","신울산울산#2 T/L","154kV 두왕분기T/L 건설공사","1. 목적 : 154kV 두왕분기T/L 건설공사 관련 가선로 구성 2. 공사구간 : 154kV 신울산-울산 T/L 5 ~ 7호 (안전이격)","2017-09-27 07:00","2017-09-28 19:00","2017-09-27 07:00","2017-09-28 19:00","매일",null,null,null,201707170083,"-"]
[385,"부산울산","울산","신울산웅촌#1 T/L","2017년 가공송전선로 순시점검 위탁공사(울산전력지사)","154kV 신울산-웅촌T/L 송전선로 정밀점검(34기)","2017-09-11 09:00","2017-09-13 18:00","2017-09-11 09:00","2017-09-13 18:00","연속",null,null,null,201707040090,"-"]
[386,"부산울산","울산","신울산웅촌#2 T/L","2017년 가공송전선로 순시점검 위탁공사(울산전력지사)","154kV 신울산-웅촌T/L 송전선로 정밀점검(34기)","2017-09-14 09:00","2017-09-16 18:00","2017-09-14 09:00","2017-09-16 18:00","연속",null,null,null,201707040091,"-"]
[387,"부산울산","울산","언양산막#2 T/L","154kV 울주-직동 등 4개 T/L 송전선로용 피뢰기 설치공사","154kV 직동-언양#1T/L 피뢰기 설치관련 안전이격","2017-09-24 09:00","2017-09-24 18:00","2017-09-24 09:00","2017-09-24 18:00","당일",null,null,null,201707100108,"-"]
[388,"부산울산","울산","온산처용#2 T/L","2017년 울산P/O 개폐장치 정밀점검공사","처용S/S 170kV 6333 GIS 정밀점검관련 시험가압","2017-09-09 17:00","2017-09-09 18:00","2017-09-09 17:00","2017-09-09 18:00","당일",null,null,null,201707100205,"-"]
[389,"부산울산","울산","용연울산TP#1 T/L","용연S/S 170kV 장기사용 GIS 대체공사","용연S/S 170kV 617,61,612,616 GIS 대체","2017-09-11 08:00","2017-09-22 18:00","2017-09-11 08:00","2017-09-22 18:00","연속",null,null,null,201707100236,"-"]
[390,"부산울산","울산","용연처용#1 T/L","용연S/S 170kV 장기사용 GIS 대체공사","용연S/S 170kV #1BUS 시험가압","2017-09-16 18:00","2017-09-17 18:00","2017-09-16 18:00","2017-09-17 18:00","연속",null,null,null,201707100242,"-"]
[391,"부산울산","울산","용연처용#2 T/L","용연S/S 170kV 장기사용 GIS 대체공사","용연S/S 170kV 612DS 철거 및 마감관련 시험가압","2017-09-11 17:00","2017-09-11 18:00","2017-09-11 17:00","2017-09-11 18:00","당일",null,null,null,201707100241,"-"]
[392,"부산울산","울산","울산울산TP#1 T/L","2016~2017년 울산전력지사 송전정비 협력회사 총액공사","No.1~13호 노후애자금구류 교체 및 송전용 피뢰기 설치","2017-09-10 08:00","2017-09-11 18:00","2017-09-10 08:00","2017-09-11 18:00","연속",null,null,null,201707070169,"○"]
[393,"부산울산","울산","울산울산TP#2 T/L","2016~2017년 울산전력지사 송전정비 협력회사 총액공사","No.1~13호 노후애자금구류 교체 및 송전용 피뢰기 설치","2017-09-12 08:00","2017-09-13 18:00","2017-09-12 08:00","2017-09-13 18:00","연속",null,null,null,201707070170,"-"]
[394,"부산울산","울산","울주S/S #1EM.Tr A","울주S/S 154kV ESS 연간설비점검","울주S/S 154kV ESS 연간설비점검(본부 변전운영 예방정비) - 정밀점검 및 성능검증","2017-09-11 09:00","2017-09-21 18:00","2017-09-11 09:00","2017-09-21 18:00","연속",null,null,null,201707100293,"-"]
[395,"부산울산","울산","효문방어진 T/L","2017년 울산P/O 장기사용 개폐장치 대체공사","효문S/S 25.8kV #1-1,1-2,2-2Sh.C용 VCB 대체관련 안전이격","2017-09-19 07:00","2017-09-19 18:00","2017-09-19 07:00","2017-09-19 18:00","당일",null,null,null,201707100258,"-"]
[396,"경남","직할","신김해주촌#1 T/L","신김해S/S 신김해-주촌#1T/L CB 보통점검 및 PT 초기점검","신김해S/S 신김해-주촌#1T/L CB 보통점검 및 PT 초기점검","2017-09-23 09:30","2017-09-23 17:30","2017-09-23 09:30","2017-09-23 17:30","당일",null,null,null,201707050046,"-"]
[397,"경남","직할","신김해진영#1 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선 교체공사(안전거리 확보휴전)","2017-09-16 07:00","2017-09-17 18:00","2017-09-16 07:00","2017-09-17 18:00","매일",null,null,null,201707060130,"-"]
[398,"경남","직할","신김해진영#2 T/L","345kV 신마산-신김해 등 2개T/L 피뢰기 설치공사","송전선로용 피뢰기 설치공사(안전거리 확보휴전)","2017-09-10 08:00","2017-09-10 18:00","2017-09-10 08:00","2017-09-10 18:00","당일",null,null,null,201707170156,"-"]
[399,"경남","직할","신김해진영#2 T/L","345kV 신김해-북부산 등 2개 T/L 21개 구간 전력선 교체공사","전력선 교체공사(안전거리 확보휴전)","2017-09-16 07:00","2017-09-17 18:00","2017-09-16 07:00","2017-09-17 18:00","매일",null,null,null,201707060131,"-"]
[400,"경남","직할","신월동읍#1 T/L","2016~17년 경남지역본부 직할 송전협력회사 총액공사","애자교체(154kV 신월-동읍#1T/L, 34호 등 3개소)","2017-09-30 07:00","2017-09-30 18:00","2017-09-30 07:00","2017-09-30 18:00","당일",null,null,null,201707060135,"-"]
[401,"경남","진주","동진주진주#1 T/L","동진주-진주#1T/L GIS CB(647)하자점검","동진주-진주#1T/L GIS CB(647)하자점검 - 황색차단기","2017-09-24 09:00","2047-09-24 14:00","2017-09-24 09:00","2047-09-24 14:00","당일",null,null,null,201707030057,"○"]
[402,"경남","진주","동진주진주#2 T/L","동진주-진주#2T/L GIS CB(637)하자점검","동진주-진주#2T/L GIS CB(637)하자점검","2017-09-24 14:00","2047-09-24 18:00","2017-09-24 14:00","2047-09-24 18:00","당일",null,null,null,201707030058,"-"]
[403,"경남","진주","사천개양#1 T/L","154kV 사천-개양 등 2개T/L 지장송전선로 지중화공사","154kV 사천-개양 등 2개T/L 지장송전선로 지중화공사 관련 사천-개양C/H 설치공사(선하지, 동시휴전)","2017-09-09 07:00","2017-09-10 19:00","2017-09-09 07:00","2017-09-10 19:00","연속",null,null,null,201707050081,"-"]
[404,"경남","진주","사천개양#2 T/L","154kV 사천-개양 등 2개T/L 지장송전선로 지중화공사","154kV 사천-개양 등 2개T/L 지장송전선로 지중화공사 관련 사천-개양C/H 설치공사(선하지, 동시휴전)","2017-09-09 07:00","2017-09-10 19:00","2017-09-09 07:00","2017-09-10 19:00","연속",null,null,null,201707050082,"-"]
[405,"경남","진주","하동개양#1 T/L","154kV 하동-개양#1,2T/L 이도조정 및 전선교체(동시휴전)","154kV 하동-개양#1,2T/L 이도조정 및 전선교체(동시휴전) - No.94-98 전선교체 - No.89-91, 91-94 이도조정","2017-09-02 07:00","2017-09-03 19:00","2017-09-02 07:00","2017-09-03 19:00","연속",null,null,null,201704060012,"○"]
[406,"경남","진주","하동개양#2 T/L","154kV 하동-개양#1,2T/L 이도조정 및 전선교체(동시휴전)","154kV 하동-개양#1,2T/L 이도조정 및 전선교체(동시휴전) - No.94-98 전선교체 - No.89-91, 91-94 이도조정","2017-09-02 07:00","2017-09-03 19:00","2017-09-02 07:00","2017-09-03 19:00","연속",null,null,null,201704060013,"-"]
[407,"경남","진주","하동하동화력#1 T/L","154kV 하동-남해#1T/L 송전선로 정밀점검 안전이격","154kV 하동-남해#1T/L 송전선로 정밀점검","2017-09-25 08:30","2017-09-25 19:00","2017-09-25 08:30","2017-09-25 19:00","당일",null,null,null,201707170139,"-"]
[408,"경남","진주","하동하동화력#2 T/L","하동-개양#1T/L CB(657) 정밀점검","하동-개양#1T/L CB(657) 정밀점검 - 하동-하동화력#2T/L 및 #2BUS로 시험가압","2017-09-03 18:00","2017-09-03 18:30","2017-09-03 18:00","2017-09-03 18:30","당일",null,null,null,201707030013,"-"]
[409,"경남","진주","하동개양#1 T/L","154kV 하동-개양T/L 하동분기 OPGW 교체공사(동시휴전)","- No.89 - 하동S/T OPGW 교체","2017-09-16 07:00","2017-09-17 18:00","2017-09-16 07:00","2017-09-17 18:00","당일",null,null,null,201707280048,"○"]
[410,"경남","진주","하동개양#2 T/L","154kV 하동-개양T/L 하동분기 OPGW 교체공사(동시휴전)","- No.89 - 하동S/T OPGW 교체","2017-09-16 07:00","2017-09-17 18:00","2017-09-16 07:00","2017-09-17 18:00","당일",null,null,null,201707280050,"-"]
[411,"경남","통영","신고성고성 T/L","신고성S/S 154kV 신고성-고성T/L GIS 보통점검","신고성S/S 154kV 신고성-고성T/L GIS 보통점검,LA, PT보통점검 히터 일괄제어키트 설치","2017-09-23 09:30","2017-09-23 18:30","2017-09-23 09:30","2017-09-23 18:30","당일",null,null,null,201707040190,"-"]
[412,"경남","함안","신마산마산#1 T/L","154kV 신마산-마산T/L EBA 자기애관 교체공사","154kV 신마산-마산#1,2T/L EBA 자기애관 교체공사 (2002년 설치 EBA 자기애관 → 폴리머애관)","2017-09-16 07:00","2017-09-17 19:00","2017-09-16 07:00","2017-09-17 19:00","연속",null,null,null,201707050083,"-"]
[413,"경남","함안","신마산마산#2 T/L","154kV 신마산-마산T/L EBA 자기애관 교체공사","154kV 신마산-마산#1,2T/L EBA 자기애관 교체공사 (2002년 설치 EBA 자기애관 → 폴리머애관)","2017-09-23 07:00","2017-09-24 19:00","2017-09-23 07:00","2017-09-24 19:00","연속",null,null,null,201707050084,"-"]
[414,"경남","함안","신마산차룡#1 T/L","154kV 동읍-진영 등 12개T/L 피뢰기 설치공사","송전선로용 피뢰기 설치 안전거리 확보 : 신마산-동읍#2T/L 1~52호","2017-09-09 07:00","2017-09-10 18:00","2017-09-09 07:00","2017-09-10 18:00","연속",null,null,null,201707050053,"-"]
[415,"경남","함안","중리가야#1 T/L","가야S/S 170kV #1BUSTIE GIS 정밀점검 시험가압","가야S/S 170kV #1BUSTIE GIS 정밀점검 시험가압","2017-09-22 18:30","2017-09-22 19:30","2017-09-22 18:30","2017-09-22 19:30","당일",null,null,null,201707060251,"-"]
[416,"대전충남","아산","서천안탕정#1 T/L","서천안S/S 154kV 서천안-탕정#1T/L 보호배전반 교체","○ 154kV 서천안-탕정#1T/L 보호배전반 교체","2017-09-25 09:00","2017-09-28 18:00","2017-09-25T09:00:00","2017-09-28T18:00:00","연속"]

{"sheet":"한수원","index":3,"n_rows":6,"n_cols":20,"rows_kept":6,"cut":false,"hidden":false,"merged":[[0,0,0,6],[3,12,4,12],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4],[3,5,4,5],[3,6,3,7],[3,8,3,9],[3,10,4,10],[3,11,4,11],[3,19,4,19],[3,13,4,13],[3,14,4,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,18,4,18]]}
["2017년도 9월 휴전계획표(한국수력원자력)"]
[]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"월성본부","월성3발","신월성#2 주변압기","신월성2호기 2차 계획예방정비\n#2 MTR/UAT/EXTR 점검\n* 조작차단기 : CB 7100, 7172","○ MTR/UAT/EXTR 일반점검 등","2017-09-22T09:00:00","2017-09-29T18:00:00","2017-09-22T09:00:00","2017-09-29T18:00:00","연속","Y"]

{"sheet":"남부","index":4,"n_rows":8,"n_cols":20,"rows_kept":8,"cut":false,"hidden":false,"merged":[[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,18,4,18],[3,19,4,19],[3,8,3,9],[3,10,4,10],[3,11,4,11],[3,12,4,12],[3,13,4,13],[3,14,4,14],[0,0,0,6],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4],[3,5,4,5],[3,6,3,7]]}
["2017년도 9월 휴전계획표(한국남부발전)"]
[]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"부산울산","부산복합","2MTG002 주변압기(#3,4GT용)","주,보조 변압기 점검 및 발전기 차단기 정밀점검\n* 조작차단기 : CB 7400, 7472","주,보조 변압기 점검 및 발전기 차단기 정밀점검","2017-09-01T10:00:00","2017-09-29T18:00:00","2017-09-01T10:00:00","2017-09-29T18:00:00","연속"]
["154kV"]
[1,"부산울산","부산복합","2MTS201 주변압기(#2ST용)","주,보조 변압기 점검 및 발전기 차단기 정밀점검\n* 조작차단기 : CB 6L7","주,보조 변압기 점검 및 발전기 차단기 정밀점검","2017-09-01T10:00:00","2017-09-29T18:00:00","2017-09-01T10:00:00","2017-09-29T18:00:00","연속"]