{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["765송부","345송부","154송부","한수원"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":10,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":12,"n_cols":16,"rows_kept":12,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 11월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신안성신가평 T/L","항공장애표시구 교체공사","o No.117-118 간 항공장애표시구 소음민원 발생개소 16개 교체","2017-11-28 08:00","2017-11-28 18:00","2017-11-28 08:00","2017-11-28 18:00","당일",null,null,null,201708170028]
[2,"경기북부","구리","신태백신가평#2 T/L","17년 신가평변전소 765kV GIS 정밀점검공사","8371CB,83H1(HIGS),8361DS,8301DS,8321DS 정밀점검","2017-11-05 09:00","2017-11-24 18:00","취소","취소","연속",null,null,null,201709150018]
[3,"경기북부","구리","신가평S/S 765kV #1 BUS","17년 신가평변전소 765KV GIS 정밀점검공사","8351DS 정밀점검","2017-11-24 09:00","2017-11-30 18:00","2017-11-06 09:00","2017-11-13 18:00","연속",null,null,null,201709150021]
[4,"경기북부","구리","신가평S/S #1 M.Tr A-1","신가평S/S #1M.Tr 및 GIS 초기점검","신가평S/S #1M.Tr 및 GIS 초기점검","2017-11-01 09:00","2017-11-04 18:00","2017-11-01 09:00","2017-11-04 18:00","연속",null,null,null,201706260008]
[5,"강원","태백","신태백신가평#2 T/L","○ 2017년 신태백S/S 800kV GIS 초기점검 공사","○ 신태백S/S 신태백-신가평#2T/L GIS 초기점검","2017-11-20 10:00","2017-12-01 18:00","2017-11-24 10:00","2017-11-24 18:00","연속",null,null,null,201709050025]
[6,"강원","태백","신태백신가평#1 T/L","○ 2017년 신태백S/S 800kV GIS 초기점검 공사","○ 신태백S/S 신태백-신가평#1T/L GIS 초기점검","2017-11-13 10:00","2017-11-17 18:00","2017-11-23 10:00","2017-11-23 18:00","연속",null,null,null,201709050022]
[7,"강원","태백","신태백신한울#1 T/L","○ 2017년 신태백S/S 800kV GIS 정밀점검 공사","○ 신태백-신한울#1T/L GIS 정밀점검 공사","2017-11-04 10:00","2017-11-30 18:00","2017-11-27 10:00","2017-12-12 18:00","연속",null,null,null,201709050018]
[8,"부산울산","동부산","신고리S/S #1 M.Tr A-1","신고리S/S 765kV #1M.Tr OLTC 상판 온도센서 교체","신고리S/S 765kV #1M.Tr OLTC 상판 온도센서 교체","2017-11-01 09:30","2017-11-01 17:00","2017-11-01 09:30","2017-11-01 17:00","당일",null,null,null,201709080369]

{"sheet":"345송부","index":1,"n_rows":264,"n_cols":16,"rows_kept":264,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 11월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","미금성동#2 T/L","17년 성동P/O 변전협력회사 총액공사","362kV GIS 보통점검 (성동S/S 345kV 미금성동#2T/L)","2017-11-02 10:00","2017-11-02 17:00","2017-11-02 10:00","2017-11-02 17:00","당일",null,null,null,201709210021,"-"]
[2,"서울","성동","성동S/S #3 M.Tr A","17년 성동P/O 변전협력회사 총액공사","노후 보호배전반 교체공사 (성동S/S 345kV #3M.Tr)","2017-11-20 09:30","2017-11-24 17:00","2017-11-20 09:30","2017-11-24 17:00","연속",null,null,null,201709210044,"-"]
[3,"서울","성동","성동S/S #2 M.Tr A","17년 성동P/O 변전협력회사 총액공사","362kV GIS 보통점검 (성동S/S 345kV #2M.Tr 1차 7272)","2017-11-01 09:30","2017-11-01 18:30","2017-11-01 09:30","2017-11-01 18:30","당일",null,null,null,201709210018,"-"]
[4,"서울","중부","중부S/S 345kV #1 BUS","345kV 중부S/S SW 증설공사","345kV 50kA 4000A × 3CB설치","2017-11-07 09:20","2017-11-28 18:00","2017-11-07 09:20","2017-11-28 18:00","연속",null,null,null,201702020053,"-"]
[5,"서울","중부","중부S/S #3 M.Tr 1차-TIE CB (7400)","345kV 중부S/S SW 증설공사","345kV 50kA 4000A × 3CB설치","2017-11-07 09:20","2017-11-28 18:00","2017-11-07 09:20","2017-11-28 18:00","연속",null,null,null,201702020056,"-"]
[6,"남서울","동서울","곤지암동서울#2 T/L","345kV GIS 정밀점검","345kV GIS 정밀점검(7271,7200CB)","2017-11-06 09:00","2017-11-12 18:00","2017-11-06 09:00","2017-11-12 18:00","연속",null,null,null,201708210163,"-"]
[7,"남서울","동서울","동서울S/S 345kV #70 BUS","345kV GIS 정밀점검","345kV GIS 정밀점검(7251DS)","2017-11-06 09:00","2017-11-07 18:00","2017-11-06 09:00","2017-11-07 18:00","연속",null,null,null,201708210164,"-"]
[8,"남서울","동서울","신성남동서울#2 T/L","345kV 신성남-동서울#2T/L 항공구설치공사","345kV 신성남-동서울#2T/L No.17~18 항공구설치","2017-11-07 08:00","2017-11-07 18:00","2017-11-07 08:00","2017-11-07 18:00","당일",null,null,null,201709210065,"-"]
[9,"남서울","동서울","신성남동서울#1 T/L","345kV 신성남-동서울#1T/L 항공구설치공사","345kV 신성남-동서울#1T/L No.17~18 항공구설치","2017-11-08 08:00","2017-11-08 18:00","2017-11-08 08:00","2017-11-08 18:00","당일",null,null,null,201709210061,"-"]
[10,"남서울","동서울","곤지암동서울#1 T/L","345kV 곤지암-동서울#1T/L 항공구설치공사","345kV 곤지암-동서울#1T/L No.41~42 항공구설치","2017-11-09 08:00","2017-11-09 18:00","2017-11-09 08:00","2017-11-09 18:00","당일",null,null,null,201709210060,"-"]
[11,"남서울","동서울","동서울미금#2 T/L","345kV GIS 정밀점검","345kV GIS 정밀점검(7272CB)","2017-11-13 09:00","2017-11-17 18:00","2017-11-13 09:00","2017-11-17 18:00","연속",null,null,null,201708210182,"-"]
[12,"남서울","동서울","동서울S/S 345kV #75 BUS","345kV GIS 정밀점검","345kV GIS 정밀점검(7252DS)","2017-11-13 09:00","2017-11-14 18:00","2017-11-13 09:00","2017-11-14 18:00","연속",null,null,null,201708210168,"-"]
[13,"남서울","동서울","동서울S/S 70-71-0 SEC CB (70-71-0)","차단기 조작시험","차단기 조작시험","2017-11-20 13:00","2017-11-20 14:00","2017-11-20 13:00","2017-11-20 14:00","당일",null,null,null,201709140194,"-"]
[14,"남서울","동서울","동서울S/S 75-76-0 SEC CB (75-76-0)","차단기 조작시험","차단기 조작시험","2017-11-20 14:00","2017-11-20 15:00","2017-11-20 14:00","2017-11-20 15:00","당일",null,null,null,201709140195,"-"]
[15,"남서울","동서울","동서울S/S #1 M.Tr A","차단기 조작시험","차단기 조작시험(1차,3차,STR,Sh.R)","2017-11-21 10:00","2017-11-21 17:00","2017-11-21 10:00","2017-11-21 17:00","당일",null,null,null,201709140196,"-"]
[16,"남서울","동서울","동서울S/S 345kV #1 Sh.R","차단기 조작시험","차단기 조작시험","2017-11-20 10:00","2017-11-20 15:00","2017-11-20 10:00","2017-11-20 15:00","당일",null,null,null,201709140192,"-"]
[17,"남서울","영등포","서서울영서#1 T/L","345kV 서서울-영서#1T/L 정밀점검","지지물 : 45기 긍장 : 17.466km","2017-11-07 09:00","2017-11-10 18:00","2017-11-07 09:00","2017-11-10 18:00","연속",null,null,null,201709140098,"-"]
[18,"남서울","영등포","서서울영서#2 T/L","345kV 서서울-영서#2T/L 정밀점검","지지물 : 45기 긍장 : 17.466km","2017-11-13 09:00","2017-11-16 18:00","2017-11-13 09:00","2017-11-16 18:00","연속",null,null,null,201709140099,"-"]
[19,"남서울","영등포","영서S/S #1 M.Tr A","영서S/S #1 M.Tr 정밀점검","영서S/S #1 M.Tr 정밀점검 영서S/S #1M.Tr 2차 GCB 개폐타임 측정","2017-11-20 08:00","2017-12-01 18:00","2017-11-20 08:00","2017-12-01 18:00","연속",null,null,null,201709270099,"-"]
[20,"남서울","직할","영등포S/S 345kV #1 Sh.R","Sh.R 차단기 조작시험 및 개폐타임 측정","Sh.R 차단기 조작시험 및 개폐타임 측정","2017-11-21 09:00","2017-11-21 18:00","2017-11-21 09:00","2017-11-21 18:00","당일",null,null,null,201709140214,"-"]
[21,"남서울","직할","영등포S/S 345kV #2 Sh.R","Sh.R 차단기 조작시험 및 개폐타임 측정","Sh.R 차단기 조작시험 및 개폐타임 측정","2017-11-22 09:00","2017-11-22 18:00","2017-11-22 09:00","2017-11-22 18:00","당일",null,null,null,201709140216,"-"]
[22,"인천","김포","신김포신파주#2 T/L","345kV 신김포-신파주#2T/L 정밀점검","345kV 신김포-신파주#2T/L 정밀점검","2017-11-02 08:00","2017-11-03 18:00","2017-11-02 08:00","2017-11-03 18:00","매일",null,null,null,201709150073,"-"]
[23,"인천","김포","345kV가정 - 신부평 #1T/L GIS","345kV가정 - 신부평 #1T/L GIS(7272) 성능개선 공사","345kV가정 - 신부평 #1T/L GIS(7272) 성능개선 공사 - 투입저항부 및 Puffer Cylinder 성능개선공사","2017-11-27 09:00","2017-12-01 18:00","2017-11-27 09:00","2017-12-01 18:00","연속",null,null,null,201709280019,"-"]
[24,"인천","김포","가정인천CC# - 가정신부평#3 TIE GIS","가정인천CC#2 - 가정신부평#1 TIE GIS(7200) 성능개선 공사","가정인천CC#2 - 가정신부평#1 TIE GIS(7200) 성능개선 공사 - 투입저항부 및 Puffer Cylinder 성능개선공사","2017-11-20 09:00","2017-11-24 18:00","2017-11-20 09:00","2017-11-24 18:00","연속",null,null,null,201709280016,"-"]
[25,"인천","김포","345kV가정 - 인천CC #2T/L GIS","345kV가정 - 인천CC #2T/L GIS(7271) 성능개선 공사","345kV가정 - 인천CC #2T/L GIS(7271) 성능개선 공사 - 투입저항부 및 Puffer Cylinder 성능개선공사","2017-11-13 09:00","2017-11-18 18:00","2017-11-13 09:00","2017-11-18 18:00","연속",null,null,null,201709280007,"-"]
[26,"인천","시흥","신시흥#1S/S #3 M.Tr A","신시흥#1S/S #2S.Tr 2차측 CT설치공사","신시흥#1S/S #2S.Tr 2차측 CT설치공사","2017-11-18 09:30","2017-11-19 18:00","2017-11-18 09:30","2017-11-19 18:00","연속",null,null,null,201709140207,"-"]
[27,"인천","시흥","신시흥#1S/S 신시흥영흥TP#4T/L CB (7871)","신시흥#1S/S 345kV 7861 DS부 가스누기보수","신시흥#1S/S 345kV 7861 DS부 가스누기보수 CB-CT간 스페이셔 접촉부 누기(7871CB)","2017-11-01 08:00","2017-11-02 18:00","2017-11-06 08:00","2017-11-07 18:00","연속",null,null,"한전요청",201709140289,"-"]
[28,"인천","시흥","영흥T/P 신시흥영흥TP#4T/L-#4G/T 1차 CB (7500)","영흥T/P 신시흥영흥TP#4T/L-#4G 1차 CB(7500) 구조개선","영흥T/P 신시흥영흥TP#4T/L-#4G 1차 CB(7500) 구조개선공사","2017-11-13 08:00","2017-11-15 18:00","2017-11-13 08:00","2017-11-15 18:00","연속",null,null,null,201709140178,"-"]
[29,"인천","시흥","영흥T/P #2G/T 1차 CB (7272)","영흥T/P #2G/T 1차 CB (7272) 구조개선공사","영흥T/P #2G/T 1차 CB (7272) 구조개선공사","2017-11-17 08:00","2017-11-19 18:00","2017-11-17 08:00","2017-11-19 18:00","연속",null,null,null,201709140180,"-"]
[30,"인천","시흥","영흥T/P 영흥TP연락#2T/L-#2G/T 1차 CB (7200)","영흥T/P 영흥TP연락#2T/L-#2G/T 1차CB(7200) 구조개선","영흥T/P 영흥TP연락#2T/L-#2G/T 1차 CB (7200) 구조개선공사","2017-11-20 08:00","2017-11-22 18:00","2017-11-20 08:00","2017-11-22 18:00","연속",null,null,null,201709140182,"-"]
[31,"인천","시흥","영흥T/P #1 TIE Tr 1차 CB (7371)","영흥T/P #1 TIE Tr 1차 CB (7371) 구조개선공사","영흥T/P #1 TIE Tr 1차 CB (7371) 구조개선공사","2017-11-02 08:00","2017-11-04 18:00","2017-11-02 08:00","2017-11-04 18:00","연속",null,null,null,201709140174,"-"]
[32,"인천","시흥","영흥T/P #3 M.Tr(G.T) 1차 CB (7472)","영흥S/Y 7400 CB C상 CT 교체공사(7472 CB)","영흥S/Y 7400 CB C상 CT 교체공사(7472 CB)","2017-11-27 08:00","2017-11-29 18:00","취소","취소","연속",null,null,"계통안정",201709140183,"-"]
[33,"인천","시흥","신시흥영흥TP#2 T/L","영흥S/Y 7400 CB C상 CT 교체공사","영흥S/Y 7400 CB C상 CT 교체공사","2017-11-27 08:00","2017-11-29 18:00","취소","취소","연속",null,null,"계통안정",201709140184,"-"]
[34,"인천","시흥","영흥T/P #1 TIE Tr 1차-#2 TIE-Tr 1차 CB (7300)","영흥T/P #1TIE.Tr1차-#2TIE.Tr1차(7300) 구조개선공사","영흥T/P #1TIE.Tr1차-#2TIE.Tr1차(7300) 구조개선공사","2017-11-06 08:00","2017-11-08 18:00","2017-11-06 08:00","2017-11-08 18:00","연속",null,null,null,201709140177,"-"]
[35,"인천","인천","서인천CC신부평#2 T/L","서인천복합S/Y #1Sh.R 대체공사","서인천복합S/Y #1Sh.R 대체공사 - 기존 #1Sh.R 철거 - 신규 #1Sh.R 설치 및 GIB 개조","2017-11-27 09:00","2017-11-30 18:00","2017-11-27 09:00","2017-11-30 18:00","연속",null,null,null,201709110492,"-"]
[36,"인천","인천","서인천C/C 신부평#2T/L Sh.R(#1 Sh.R)","서인천복합S/Y #1Sh.R 대체공사","서인천복합S/Y #1Sh.R 대체공사 - 기존 #1Sh.R 철거 - 신규 #1Sh.R 설치 및 GIB 개조","2017-11-13 09:00","2017-12-08 18:00","2017-11-13 09:00","2017-12-08 18:00","연속",null,null,null,201709110491,"-"]
[37,"인천","인천","신가좌S/S #4 M.Tr A","신가좌S/S #4M.Tr 2차 GIS 대체공사","신가좌S/S #4M.Tr 2차 GIS 대체공사 - GIS 철거 및 조립 - #4M.Tr GPT 점검(병행) - PL-LA3, LD3(#4M.Tr측)대체공사 - 7672CB GIS 초기점검 병행","2017-11-20 09:00","2017-12-05 18:00","2017-11-20 09:00","2017-12-05 18:00","연속",null,null,null,201709160015,"-"]
[38,"인천","인천","신가좌가정#2 T/L","SB댐퍼 설치공사","345kV 신가좌-가정#2T/L SB댐퍼 설치공사","2017-11-09 08:00","2017-11-10 18:00","2017-11-09 08:00","2017-11-10 18:00","연속",null,null,null,201709150063,"-"]
[39,"인천","인천","신가좌가정#1 T/L","SB댐퍼 설치공사","345kV 신가좌-가정#1T/L SB댐퍼 설치공사","2017-11-07 08:00","2017-11-08 18:00","2017-11-07 08:00","2017-11-08 18:00","연속",null,null,null,201709150062,"-"]
[40,"인천","인천","신가좌S/S #4 M.Tr 1차 CB (신) (7672 A)","신가좌S/S 7672 GIS 초기점검 공사","신가좌S/S 7672 GIS 초기점검 공사","2017-11-03 09:00","2017-11-03 18:00","2017-11-03 09:00","2017-11-03 18:00","당일",null,null,null,201709160013,"-"]
[41,"인천","인천","신경서S/S #2 M.Tr A","신경서S/S #2M.Tr 휴전작업","신경서S/S #2M.Tr 휴전작업 - #2M.Tr OFU 필터(A,C상) 교체 - 붓싱과열 보수공사(A,B,C상)","2017-11-06 09:00","2017-11-07 18:00","2017-11-13 08:30","2017-11-14 18:00","연속",null,null,"한전요청",201709110508,"-"]
[42,"인천","인천","신경서S/S 신경서신인천CCT/L CB (7171)","신경서S/S 345kV 7151DS PD발생 보수공사","345kV #1BUS측 7151DS 내부 부분방전 발생 보수(7171CB)","2017-11-20 09:00","2017-11-23 18:00","2017-11-20 09:00","2017-11-23 18:00","연속",null,null,null,201709150106,"-"]
[43,"인천","인천","신경서S/S #3 M.Tr A","신경서S/S #3M.Tr 휴전작업","신경서S/S #3M.Tr 휴전작업 - M.Tr 및 LA 보통점검 - 1차 GIS 조작시험(병행)","2017-11-08 09:00","2017-11-09 18:00","2017-11-08 09:00","2017-11-09 18:00","연속",null,null,null,201709110507,"-"]
[44,"인천","인천","신경서S/S #1 M.Tr A","신경서S/S #1M.Tr 휴전작업(붓싱도블 측정)","신경서S/S #1M.Tr 휴전작업 - 붓싱 도블 재측정(본사지시)","2017-11-13 09:00","2017-11-14 18:00","2017-11-06 08:30","2017-11-07 18:00","연속",null,null,"한전요청",201709140061,"-"]
[45,"인천","인천","신경서S/S 345kV #1 BUS","신경서S/S 345kV 7151DS PD발생 보수공사","345kV #1BUS측 7151DS 내부 부분방전 발생 보수","2017-11-20 09:00","2017-11-23 18:00","2017-11-20 09:00","2017-11-23 18:00","연속",null,null,null,201709150105,"-"]
[46,"인천","인천","서인천C/C 345kV #75 BUS","345kV 서(신)인천C/C 모선용CLR 설치공사","- 345kV CLR(36옴 2,600A) *2조 설치 - 362kV GIS(50kA 4,000A) * 4CB 및 GIB 설치","2017-11-15 10:00","2017-11-29 17:00","2017-11-15 10:00","2017-11-29 17:00","연속",null,null,null,201709270014,"-"]
[47,"인천","인천","서인천C/C 345kV #75 BUS","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- 서인천C/C #75BUS 모선개조 및 관련EDS 교체","2017-11-15 10:00","2017-12-19 17:00","2017-11-15 10:00","2017-12-19 17:00","연속",null,null,null,201709270018,"-"]
[48,"인천","인천","서인천C/C #1 M.Tr","서인천복합S/Y #1M.Tr 휴전작업","- NGK제 부싱 절연유 채유","2017-11-10 09:00","2017-11-10 18:00","2017-11-10 09:00","2017-11-10 18:00","당일",null,null,null,201709250149,"-"]
[49,"인천","인천","신인천C/C 345kV #77 BUS","345kV 서(신)인천C/C 모선용CLR 설치공사","- 345kV CLR(36옴 2,600A) *2조 설치 - 362kV GIS(50kA 4,000A) * 4CB 및 GIB 설치","2017-11-03 10:00","2017-11-13 17:00","2017-11-03 10:00","2017-11-13 17:00","연속",null,null,null,201709270012,"-"]
[50,"인천","직할","신부평S/S 345kV #1 Sh.R CB (7179)","신부평S/S #1Sh.R 7179CB 362kV GIS 정밀점검","신부평S/S #1Sh.R 7179CB 362kV GIS 정밀점검","2017-11-06 09:30","2017-11-08 18:00","2017-11-06 09:30","2017-11-08 18:00","연속",null,null,null,201709060008,"-"]
[51,"인천","직할","신부평S/S 345kV #2Sh.R CB (7279)","신부평S/S #2Sh.R 7279CB 362kV GIS 정밀점검","신부평S/S #2Sh.R 7279CB 362kV GIS 정밀점검","2017-11-09 09:30","2017-11-11 18:00","2017-11-09 09:30","2017-11-11 18:00","연속",null,null,null,201709060009,"-"]
[52,"인천","직할","신부평S/S 서인천CC-신부평#1T/L CB (7171)","신부평S/S 서인천신부평#1T/L 7171CB 362kV GIS 정밀점검","신부평S/S 서인천-신부평#1T/L 7171CB 362kV GIS 정밀점검","2017-11-13 08:00","2017-11-15 18:00","2017-11-13 08:00","2017-11-15 18:00","연속",null,null,null,201709200233,"-"]
[53,"인천","직할","서인천CC-신부평#1T/L-#1 M.Tr 1차 CB (7100)","신부평S/S #1B/T 7100CB 362kV GIS 정밀점검","신부평S/S #1B/T 7100CB 362kV GIS 정밀점검","2017-11-20 08:00","2017-11-22 18:00","2017-11-20 08:00","2017-11-22 18:00","연속",null,null,null,201709060007,"-"]
[54,"인천","직할","신부평S/S #3 M.Tr A","신부평S/S #3M.Tr 보호반 대체","신부평S/S #3M.Tr 보호반 대체","2017-11-06 09:30","2017-11-10 18:00","2017-11-06 09:30","2017-11-10 18:00","연속",null,null,null,201709080335,"-"]
[55,"인천","직할","신부평S/S #2 M.Tr A","신부평S/S #2M.Tr 보호반 대체","신부평S/S #2M.Tr 보호반 대체","2017-11-01 09:30","2017-11-04 18:00","2017-11-01 09:30","2017-11-04 18:00","연속",null,null,null,201709080334,"-"]
[56,"인천","직할","서인천C/C-신부평#4T/L-#4 M.Tr 1차 CB (7400)","신부평S/S 7400CB 362kV GIS 보통점검","신부평S/S 7400CB 362kV GIS 보통점검","2017-11-24 09:30","2017-11-24 18:00","2017-11-24 09:30","2017-11-24 18:00","당일",null,null,null,201709200234,"-"]
[57,"인천","직할","신부평S/S #4 M.Tr 1차 CB (7472)","신부평S/S 7472CB 362kV GIS 보통점검","신부평S/S 7472CB 362kV GIS 보통점검","2017-11-23 09:30","2017-11-23 18:00","2017-11-23 09:30","2017-11-23 18:00","당일",null,null,null,201709200235,"-"]
[58,"경기북부","구리","신포천S/S #1 M.Tr A","신포천S/S 345kV #1M.Tr,#1S.Tr 보통점검","신포천S/S 345kV #1M.Tr,#1S.Tr 보통점검","2017-11-29 09:00","2017-11-30 18:00","2017-11-29 09:00","2017-11-30 18:00","연속",null,null,null,201705110015,"-"]
[59,"경기북부","구리","포천C/C #2S/U Tr 1차 GIS","포천C/C #2S/U Tr 1차 GIS 하자점검 (7271)","포천C/C #2S/U Tr 1차 GIS 하자점검 (7271) - 유압펌프 과다 동작으로 인한 내부 점검","2017-11-07 10:00","2017-11-08 18:00","2017-11-07 10:00","2017-11-08 18:00","연속",null,null,null,201709140314,"-"]
[60,"경기북부","직할","동두천C/C 신포천-동두천C/C#1T/L GIS","'17년 변전협력회사 총액공사(CLR점검)","345kV CLR(한류리액터)점검","2017-11-14 10:00","2017-11-14 18:00","2017-11-14 10:00","2017-11-14 18:00","당일",null,null,null,201709140241,"-"]
[61,"경기북부","직할","동두천C/C 신포천-동두천C/C#2T/L GIS","'17년 변전협력회사 총액공사(CLR점검)","345kV CLR(한류리액터)점검","2017-11-15 10:00","2017-11-15 18:00","2017-11-15 10:00","2017-11-15 18:00","당일",null,null,null,201709140242,"-"]
[62,"경기북부","직할","신의정부미금#1 T/L","17년 경기북부직할 변전총액공사","신의정부S/S 신의정부미금#1 T/L 보통점검","2017-11-27 09:00","2017-11-27 13:00","2017-11-27 09:00","2017-11-27 13:00","연속",null,null,null,201709140044,"-"]
[63,"경기북부","직할","신의정부양주#2 T/L","345kV 신의정부-양주T/L 전선접속개소 전선교체공사","345kV 신의정부-양주#1,2T/L 21.334km 전력선 교체 및 가공지선 10.090km 교체","2017-11-10 09:00","2017-12-09 18:00","2017-11-12 09:00","2017-12-11 18:00","연속",null,null,"한전요청",201705160114,"-"]
[64,"경기북부","직할","양주중부#1 T/L","양주S/S 345kV #5 Sh.R 1차 GIS 개조공사","양주S/S 345kV #5 Sh.R 1차 GIS 설치작업","2017-11-28 09:00","2017-11-30 18:00","2017-11-28 09:00","2017-11-30 18:00","연속",null,null,null,201709140046,"-"]
[65,"경기북부","파주","신덕은S/S 345kV #1 BUS","신덕은S/S 345kV SW 증설공사","ㅇ 345kV GIS 50kA 4000A 3CB 1식 설치 ㅇ 송전선로 보호반 및 BF반 설치 ㅇ 기타 부대공사 1식","2017-11-20 10:00","2017-11-21 10:00","2017-11-20 10:00","2017-11-21 10:00","연속",null,null,"주말로 조정 필요",201709140033,"-"]
[66,"경기북부","파주","신덕은S/S 345kV #2 BUS","신덕은S/S 345kV SW 증설공사","ㅇ 345kV GIS 50kA 4000A 3CB 1식 설치 ㅇ 송전선로 보호반 및 BF반 설치 ㅇ 기타 부대공사 1식","2017-11-21 11:00","2017-11-22 11:00","2017-11-21 11:00","2017-11-22 11:00","연속",null,null,"주말로 조정 필요",201709140034,"-"]
[67,"경기북부","파주","신덕은S/S #4 M.Tr A","17년 파주 변전협력 총액공사(신덕은 #4M.Tr 보통점검)","O 신덕은SS #4M.Tr 보통점검 O 3차 GPT 점검 O 기타부대공사","2017-11-23 09:30","2017-11-23 18:00","2017-11-23 09:30","2017-11-23 18:00","당일",null,null,null,201709060254,"-"]
[68,"경기북부","파주","신덕은동두천CC#1 T/L","LS제 362kV 차단기 유사고장방지 대책 시행공사(7571CB)","신덕은 7571 C 차단기 내부 성능 개선(puffer cylinder 교체 등)","2017-11-27 09:00","2017-12-03 18:00","2017-11-27 09:00","2017-12-03 18:00","연속",null,null,null,201709190216,"-"]
[69,"경기북부","파주","파주문산C/C 파주문산-발전단#1T/L-TIE CB (7100)","LS제 362kV 차단기 유사고장방지 대책 시행 공사(7100 CB)","파주문산CC 7100 CB 내부 차단기 성능개선(puffer cylinder 신품 교체등)","2017-11-15 09:00","2017-11-21 18:00","2017-11-15 09:00","2017-11-21 18:00","연속",null,null,null,201709070340,"-"]
[70,"경기북부","파주","파주문산C/C 파주문산-발전단#2T/L-TIE CB (7200)","LS제 362kV 차단기 유사고장방지 대책 시행 공사(7200 CB)","파주문산CC 7200 CB 내부 차단기 성능개선(puffer cylinder 신품 교체등)","2017-11-08 09:00","2017-11-14 18:00","2017-11-08 09:00","2017-11-14 18:00","연속",null,null,null,201709070337,"-"]
[71,"경기북부","파주","파주문산C/C 파주-발전단#3T/L-신덕은-파주 (7300)","LS제 362kV 차단기 유사고장방지 대책 시행 공사(7300 CB)","파주문산CC 7300 CB 내부 차단기 성능개선(puffer cylinder 신품 교체등)","2017-11-01 09:00","2017-11-07 18:00","2017-11-01 09:00","2017-11-07 18:00","연속",null,null,null,201709070335,"-"]
[72,"경기북부","파주","신덕은파주문산CC#2 T/L","345kV 장문복합-신덕은T/L OPGW 항공표시구 교체공사 시행","○345kV 장문복합-신덕은T/L OPGW 항공표시구 교체 - 교체내역 : No. 3~4호 및 4~5호 한쪽 끝단 백색구 → 적색구로 교체 - 교체사유 : 제2017-T00431호(2017. 8.10) “345kV 파주발전소-신덕은 T/L 항공장애 주간표지 설치관련 보완조치 요청“","2017-11-01 09:00","2017-11-01 18:00","취소","취소","당일",null,null,"한전요청",201708300029,"-"]
[73,"경기","군포","서서울#2신성남 #1T/L","군포송정지구 송전선로 지중화 사업","ㅇ 구간 : 345kV 서서울#2S/S~345kV 서서울#2-신성남T/L No.51 ㅇ 규모 : 345kV XLPE 2500㎟, 2회선(D)-1.3km","2017-11-27 09:00","2017-12-24 18:00","2017-11-27 09:00","2017-12-24 18:00","연속",null,null,null,201709080035,"-"]
[74,"경기","군포","서서울#2S/S #6 M.Tr A","서서울#2S/S 23kV Sh.R 설치공사","#6M.Tr 3차측 Sh.R 2BANK 및 VCB 3대 설치에 따른 모선연결 및 시험","2017-11-17 09:30","2017-11-20 18:00","2017-11-17 09:30","2017-11-20 18:00","연속",null,null,null,201709060075,"-"]
[75,"경기","군포","신온양서서울#2 T/L","345kV 신온양-서서울T/L 113,114호 안전이격확보공사","철탑 2기 교체 , 전선 가공지선 교체 : 3.007km","2017-11-08 07:00","2017-11-20 18:00","2017-11-08 07:00","2017-11-20 18:00","연속",null,null,"일정조정 필요(신태백신가평T/L 중복 방지)",201709040129,"-"]
[76,"경기","군포","신온양서서울#1 T/L","345kV 신온양-서서울T/L 113,114호 안전이격확보공사","철탑교체 2기, 전선, 가공지선 교체 : 3.007km","2017-11-21 07:00","2017-11-27 18:00","2017-11-21 07:00","2017-11-27 18:00","연속",null,null,"일정조정 필요(신태백신가평T/L 중복 방지)",201708140152,"-"]
[77,"경기","군포","서서울S/S #4 M.Tr A","345kV 서서울 #4MTR 3차 모선 지지가대 절연화 공사","345kV 서서울 #4MTR 3차 모선 지지가대 절연화 시행","2017-11-06 09:00","2017-11-10 18:00","2017-11-06 09:00","2017-11-10 18:00","연속",null,null,null,201709080191,"-"]
[78,"경기","군포","서서울S/S #3 M.Tr A","345kV 서서울 #3MTR 3차 모선 지지가대 절연화 공사","345kV 서서울 #3MTR 3차 모선 지지가대 절연화 시행","2017-11-27 09:00","2017-12-01 18:00","2017-11-27 09:00","2017-12-01 18:00","연속",null,null,null,201709080188,"-"]
[79,"경기","군포","서서울S/S #1 M.Tr A","345kV 서서울 #1MTR 3차 모선 지지가대 절연화 공사","345kV 서서울 #1MTR 3차 모선 지지가대 절연화 시행","2017-11-11 09:00","2017-11-15 18:00","2017-11-11 09:00","2017-11-15 18:00","연속",null,null,null,201709080186,"-"]
[80,"경기","군포","서서울S/S #2 M.Tr A","345kV 서서울 #2MTR 3차 모선 지지가대 절연화 공사","345kV 서서울 #2MTR 3차 모선 지지가대 절연화 시행","2017-11-21 09:00","2017-11-25 18:00","2017-11-21 09:00","2017-11-25 18:00","연속",null,null,null,201709080187,"-"]
[81,"경기","동부","곤지암S/S #3 M.Tr A","345kV 곤지암S/S #64D.Tr용 GIS 설치공사","154kV #66BUS 무부하 가압","2017-11-04 09:00","2017-11-05 09:00","2017-11-04 09:00","2017-11-05 09:00","연속",null,null,null,201709070204,"-"]
[82,"경기","동부","곤지암신충주#2 T/L","345kV 곤지암-신충주T/L No.97 안전이격 확보공사","0 철탑 교체 : 설치 및 철거1기(No.97) 0 임시철탑 철거 : 1기 0 전선 교체 : 92~102","2017-11-01 07:30","2017-11-07 18:00","2017-11-01 07:30","2017-11-07 18:00","연속",null,null,null,201709040026,"-"]
[83,"경기","동부","곤지암S/S #3 M.Tr A","17년 동부변전협력회사 총액공사","곤지암S/S #3M.Tr(보통)/7572(보통)/7500(보통)/6344(보통)","2017-11-25 09:00","2017-11-26 18:00","2017-11-25 09:00","2017-11-26 18:00","연속",null,null,null,201709120205,"-"]
[84,"경기","동부","곤지암S/S #3 M.Tr A","345kV 곤지암S/S #64D.Tr 증설사업","ㅇ 154kV #64D.Tr 및 전력케이블 무부하 가압","2017-11-19 09:00","2017-11-20 09:00","2017-11-19 09:00","2017-11-20 09:00","연속",null,null,null,201709070215,"-"]
[85,"경기","성남","서안성S/S #2 M.Tr A","17년 성남변전협력회사 총액공사","A상 누유보수","2017-11-07 10:00","2017-11-08 18:00","2017-11-07 10:00","2017-11-08 18:00","연속",null,null,null,201709130024,"-"]
[86,"경기","성남","신성남신양재#1 T/L","17년 성남변전 협력회사 총액공사","78BAy BF PNL 대체공사","2017-11-27 10:00","2017-12-01 18:00","2017-11-27 10:00","2017-12-01 18:00","연속",null,null,null,201709150149,"-"]
[87,"경기","성남","신성남S/S #3 M.Tr A","신성남S/S 154kV GIS 대체공사","60-61BUS SEC GIS 대체관련 안전거리 확보","2017-11-04 08:00","2017-11-04 18:00","2017-11-04 08:00","2017-11-04 18:00","당일",null,null,null,201709130077,"-"]
[88,"경기","성남","신성남S/S #3 M.Tr A","신성남S/S 154kV GIS 대체공사","65-66BUS SEC GIS 대체관련 안전거리 확보","2017-11-19 08:00","2017-11-19 18:00","2017-11-19 08:00","2017-11-19 18:00","당일",null,null,null,201709130084,"-"]
[89,"경기","성남","신성남S/S #3 M.Tr A","신성남S/S 154kV GIS 대체공사","65-66BUS SEC GIS 대체관련 안전거리 확보","2017-11-21 08:00","2017-11-21 18:00","2017-11-21 08:00","2017-11-21 18:00","당일",null,null,null,201709130083,"-"]
[90,"경기","성남","신성남S/S #1M.Tr A","신성남S/S 154kV GIS 대체공사","65-66BUS SEC GIS 대체관련 무부하가압","2017-11-26 18:00","2017-11-27 10:00","2017-11-26 18:00","2017-11-27 10:00","연속",null,null,null,201709130085,"-"]
[91,"경기","성남","신성남S/S #3 M.Tr A","신성남S/S 154kV GIS 대체공사","60-61BUS SEC GIS 대체관련 안전거리 확보","2017-11-02 08:00","2017-11-02 18:00","2017-11-02 08:00","2017-11-02 18:00","당일",null,null,null,201709130076,"-"]
[92,"경기","성남","신성남S/S #1M.Tr A","신성남S/S 154kV GIS 대체공사","60-61BUS SEC GIS 대체관련 무부하가압","2017-11-17 18:00","2017-11-18 18:00","2017-11-17 18:00","2017-11-18 18:00","연속",null,null,null,201709130080,"-"]
[93,"경기","성남","신성남S/S #1M.Tr A","신성남S/S 154kV GIS 대체공사","60-61BUS SEC GIS 대체관련 무부하가압","2017-11-09 18:00","2017-11-10 10:00","2017-11-09 18:00","2017-11-10 10:00","연속",null,null,null,201709130078,"-"]
[94,"경기","성남","신성남S/S 75-76 GIS","17년 성남변전협력회사 총액공사","조작시험 및 개폐타임 측정","2017-11-08 13:00","2017-11-08 18:00","2017-11-08 13:00","2017-11-08 18:00","연속",null,null,null,201709130027,"-"]
[95,"경기","성남","신성남S/S 70-71 GIS","17년 성남변전협력회사 총액공사","조작시험 및 개폐타임 측정","2017-11-08 10:00","2017-11-08 13:00","2017-11-08 10:00","2017-11-08 13:00","당일",null,null,null,201709130028,"-"]
[96,"경기","성남","신수원S/S #1 M.Tr A","17년 성남변전협력회사 총액공사","보호배전반 대체, 6144 조작시험, 96P전선관 개선","2017-11-30 10:00","2017-12-04 18:00","2017-11-30 10:00","2017-12-04 18:00","연속",null,null,null,201709130030,"-"]
[97,"경기","성남","신안성신수원#2 T/L","345kV 신용인-신수원T/L등 2구간 OPGW시설공사(화성동탄2)","공사장소 : 신용인S/S, 신안성S/S~동측C/H~서측C/H~신수원S/S 시설내역 : OPGW 120/70sq 24/48C 40.58km 비금속광케이블 24/48C 6.987km","2017-11-28 07:00","2017-11-29 18:00","2017-11-28 07:00","2017-11-29 18:00","연속",null,null,null,201709120233,"-"]
[98,"경기","성남","신안성신수원#1 T/L","345kV 신용인-신수원T/L등 2구간 OPGW시설공사(화성동탄2)","공사장소 : 신용인S/S, 신안성S/S~동측C/H~서측C/H~신수원S/S 시설내역 : OPGW 120/70sq 24/48C 40.58km 비금속광케이블 24/48C 6.987km","2017-11-18 07:00","2017-11-27 18:00","2017-11-18 07:00","2017-11-27 18:00","연속",null,null,null,201709120231,"-"]
[99,"경기","성남","신용인S/S 신용인-삼성T/L-TIE GIS","17년 성남변전협력회사 총액공사","7600 GIS 초기점검","2017-11-17 10:00","2017-11-17 13:00","2017-11-17 10:00","2017-11-17 13:00","당일",null,null,null,201709210008,"-"]
[100,"경기","성남","신용인S/S 신용인-삼성T/L GIS","17년 성남변전협력회사 총액공사","7671 GIS 초기점검","2017-11-15 10:00","2017-11-15 13:00","2017-11-15 10:00","2017-11-15 13:00","당일",null,null,null,201709130035,"-"]
[101,"경기","성남","신용인동서울#2 T/L","345kV 신용인-동서울#2T/L 정밀점검","345kV 신용인-동서울#2T/L 정밀점검","2017-11-06 09:00","2017-11-09 18:00","2017-11-06 09:00","2017-11-09 18:00","연속",null,null,null,201709070011,"-"]
[102,"경기","직할","화성S/S 345kV #1 CLR 70BUS GIS","화성S/S 345kV #1 CLR 70BUS GIS 조작시험","화성S/S 345kV #1 CLR 70BUS(7077) GIS 조작시험","2017-11-16 10:00","2017-11-16 13:00","2017-11-16 10:00","2017-11-16 13:00","당일",null,null,null,201709080133,"-"]
[103,"경기","직할","화성S/S 345kV #1 CLR 71BUS GIS","화성S/S 345kV #1 CLR 71BUS GIS 조작시험","화성S/S 345kV #1 CLR 71BUS(7177) GIS 조작시험","2017-11-16 13:00","2017-11-16 15:00","2017-11-16 13:00","2017-11-16 15:00","당일",null,null,null,201709080135,"-"]
[104,"경기","직할","화성S/S 345kV #2 CLR 76BUS GIS","화성S/S 345kV #2 CLR 71BUS GIS 조작시험","화성S/S 345kV #2 CLR 71BUS(7577) GIS 조작시험","2017-11-17 10:00","2017-11-17 13:00","2017-11-17 10:00","2017-11-17 13:00","당일",null,null,null,201709080140,"-"]
[105,"경기","직할","화성S/S 345kV #2 CLR 76BUS GIS","화성S/S 345kV #2 CLR 71BUS GIS 조작시험","화성S/S 345kV #2 CLR 71BUS(7677) GIS 조작시험","2017-11-17 13:00","2017-11-17 15:00","2017-11-17 13:00","2017-11-17 15:00","당일",null,null,null,201709080136,"-"]
[106,"강원","강릉","신양양S/S #1 M.Tr A","2017년 변전협력회사 총액공사","1. 3차측 단로기 과열보수 2. 장기미동작차단기 조작시험","2017-11-06 09:00","2017-11-06 18:00","2017-11-06 09:00","2017-11-06 18:00","당일",null,null,null,201709090033,"-"]
[107,"강원","강릉","양양P/P #1 M.Tr 1차 CB (7172)","양양양수S/Y 345kV GIS 정밀점검공사","7172 CB 정밀점검","2017-11-07 09:00","2017-11-10 18:00","2017-11-07 09:00","2017-11-10 18:00","연속",null,null,null,201708030005,"-"]
[108,"강원","동해","동해S/S 동해-양양PP T/L-#2 M.Tr 1차 CB (7400)","2017년 동해변전소 362kV GIS 정밀점검공사","1. 동해S/S 74BAY TIE CB 정밀점검(7400)","2017-11-27 09:00","2017-11-29 18:00","2017-11-27 09:00","2017-11-29 18:00","연속",null,null,null,201709110448,"-"]
[109,"강원","동해","동해S/S 동해-양양PP T/L CB (7471)","2017년 동해변전소 362kV GIS 정밀점검공사","1. 동해S/S 동해-양양PP T/L CB 정밀점검(7471)","2017-11-23 09:00","2017-11-25 18:00","2017-11-23 09:00","2017-11-25 18:00","연속",null,null,null,201709110446,"-"]
[110,"강원","동해","동해S/S 73BAY TIE CB (7300)","2017년 동해변전소 362kV GIS 정밀점검공사","1. 동해S/S 73BAY TIE CB 정밀점검(7300)","2017-11-20 09:00","2017-11-22 18:00","2017-11-20 09:00","2017-11-22 18:00","연속",null,null,null,201709110444,"-"]
[111,"강원","동해","동해S/S 동해-북평TP#3T/L CB (7572)","2017년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해-북평TP#3 T/L CB 하자점검(7572)","2017-11-15 09:30","2017-11-15 18:00","2017-11-15 09:30","2017-11-15 18:00","당일",null,null,null,201709060368,"-"]
[112,"강원","동해","동해S/S 동해-북평TP#1T/L CB (7272)","2017년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해-북평TP#1 T/L CB 하자점검(7272)","2017-11-13 09:30","2017-11-13 18:00","2017-11-13 09:30","2017-11-13 18:00","당일",null,null,null,201709060367,"-"]
[113,"강원","동해","동해S/S #2 M.Tr 1차 CB (7472)","2017년 동해변전소 362kV GIS 정밀점검공사","1. 동해S/S #2M.Tr 1차 CB 정밀점검(7472)","2017-11-30 09:00","2017-12-02 18:00","2017-11-30 09:00","2017-12-02 18:00","연속",null,null,null,201709110449,"-"]
[114,"강원","동해","동해S/S 동해-북평TP#2T/L CB (7372)","2017년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해-북평TP#2 T/L CB 하자점검(7372)","2017-11-14 09:30","2017-11-14 18:00","2017-11-14 09:30","2017-11-14 18:00","당일",null,null,null,201709060371,"-"]
[115,"강원","동해","삼척TP #2M.Tr A","2017년 동해전력지사 변전협력회사 총액공사","1. #2M.Tr 하자점검 2. #2M.Tr 1, 3차 PT 하자점검 3. #2M.Tr 2, 3차 LA 하자점검 4. #2M.Tr 1차 GIS(7472) 하자점검 5. #2M.Tr 2, 3차 GIS 하자점검 6. OFU 과열방지회로 구성","2017-11-01 09:30","2017-11-02 18:00","2017-11-01 09:30","2017-11-02 18:00","연속",null,null,null,201709060336,"-"]
[116,"강원","동해","동해삼척GP#1 T/L","345kV 동해-삼척GPT/L 전선접속개소 전선교체공사","○ 전선접속개소 해소 : NO.76~84 등 6개소,22.62C-km ○ 가공지선 접속개소 해소 : No.76~84 등 5개소 9.8C-km","2017-11-01 08:00","2017-11-15 18:00","2017-11-01 08:00","2017-11-15 18:00","연속",null,null,"일정조정 필요",201709110116,"-"]
[117,"강원","동해","삼척TP #3M.Tr A","2017년 동해전력지사 변전협력회사 총액공사","1. #3M.Tr 하자점검 2. #3M.Tr 1, 3차 PT 하자점검 3. #3M.Tr 2, 3차 LA 하자점검 4. #3M.Tr 1차 GIS(7472) 하자점검 5. #3M.Tr 2, 3차 GIS 하자점검 6. SFRA 측정 7. OFU 과열방지회로 구성","2017-11-06 09:30","2017-11-07 18:00","2017-11-06 09:30","2017-11-07 18:00","연속",null,null,null,201709060342,"-"]
[118,"강원","동해","삼척GP #2기동 Tr CB (7572)","2017년 동해전력지사 변전협력회사 총액공사","1. GIS 하자점검(7572) 2. 삼척GP #2 STEP-UP Tr 1차 PT 하자점검","2017-11-08 09:30","2017-11-08 18:00","2017-11-08 09:30","2017-11-08 18:00","당일",null,null,null,201709060365,"-"]
[119,"강원","동해","삼척GP #1기동 Tr CB (7772)","2017년 동해전력지사 변전협력회사 총액공사","1. 삼척GP #1 STEP-UP Tr 1차 PT 하자점검","2017-11-09 09:30","2017-11-09 18:00","2017-11-09 09:30","2017-11-09 18:00","당일",null,null,null,201709060360,"-"]
[120,"강원","동해","삼척GP 삼척GP #2T/L - #1기동 Tr CB (7700)","2017년 동해전력지사 변전협력회사 총액공사","1. 삼척GP #1 STEP-UP Tr 1차 PT 하자점검","2017-11-09 09:30","2017-11-09 18:00","2017-11-09 09:30","2017-11-09 18:00","당일",null,null,null,201709200115,"-"]
[121,"강원","동해","삼척GP한울NP1#2 T/L","345kV 삼척GP-한울NP1 T/L 지장철탑 이설공사","지지물 2기 신설(No.54, 55호), 가철탑 1기 설치(No.54) 전력선 교체 : No.54~No.58호간","2017-11-13 09:00","2017-11-15 18:00","2017-11-28 08:00","2017-11-30 18:00","연속",null,null,"한전요청",201709040049,"-"]
[122,"강원","동해","동해삼척GP#2 T/L","345kV 동해-삼척GPT/L 전선접속개소 전선교체공사","○ 전선접속개소 해소 : NO.76~84 등 6개소,22.62C-km ○ 가공지선 접속개소 해소 : No.76~84 등 5개소 9.8C-km","2017-11-16 08:00","2017-11-30 18:00","2017-11-16 08:00","2017-11-30 18:00","연속",null,null,"일정조정 필요",201709110117,"-"]
[123,"강원","동해","삼척GP한울NP1#1 T/L","345kV 삼척GP-한울NP1 T/L 지장철탑 이설공사","지지물 2기 신설(No.54, 55호), 가철탑 1기 설치(No.54) 전력선 교체 : No.54~No.58호간","2017-11-16 09:00","2017-11-24 18:00","2017-12-01 08:00","2017-12-09 18:00","연속",null,null,"한전요청",201709040050,"-"]
[124,"강원","동해","삼척GP한울NP1#2 T/L","345kV 삼척GP-한울NP1 T/L 지장철탑 이설공사","지지물 2기 신설(No.54, 55호), 가철탑 1기 설치(No.54) 전력선 교체 : No.54~No.58호간","2017-11-25 09:00","2017-12-03 18:00","2017-12-10 08:00","2017-12-18 18:00","연속",null,null,"한전요청",201709040051,"-"]
[125,"강원","태백","신태백한울NP2#1 T/L","○ 울태T/L 345kV 신태백-한울NP2T/L 정밀점검 공사","○ 345kV 울태T/L 정밀점검 공사","2017-11-20 09:00","2017-11-26 18:00","2017-11-20 09:00","2017-11-26 18:00","매일",null,null,null,201709080261,"-"]
[126,"강원","태백","신태백한울NP2#2 T/L","○ 울태T/L 345kV 신태백-한울NP2T/L 정밀점검 공사","○ 345kV 울태T/L 정밀점검 공사","2017-11-13 09:00","2017-11-19 18:00","2017-11-13 09:00","2017-11-19 18:00","연속",null,null,null,201709080260,"-"]
[127,"충북","직할","신제천동해#2 T/L","신제천S/S 7A71, 7A00 GIS 초기점검","- 345kV GIS 초기점검","2017-11-22 10:00","2017-11-22 18:00","2017-11-22 10:00","2017-11-22 18:00","당일",null,null,null,201709110484,"-"]
[128,"충북","직할","신제천S/S #2 M.Tr A","주변압기 3차측 PT 하자점검","3차측 PT 제작사 입고 및 분해점검","2017-11-01 09:00","2017-11-17 18:00","2017-11-01 09:00","2017-11-17 18:00","연속",null,null,null,201709110374,"-"]
[129,"충북","청주","신옥천신남원#2 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","항공장애표시구 설치 No.219~247 (9개)","2017-11-07 08:00","2017-11-07 19:00","2017-11-07 08:00","2017-11-07 19:00","매일",null,null,null,201709120098,"-"]
[130,"충북","청주","신옥천신남원#1 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","항공장애표시구 설치 No.219~247 (9개)","2017-11-06 08:00","2017-11-06 19:00","2017-11-06 08:00","2017-11-06 19:00","매일",null,null,null,201709120097,"-"]
[131,"충북","청주","청원S/S 345kV #2 BUS","청원S/S 345kV 장기사용 GIS 대체공사(전문)","○ 345kV GIS(가스절연개폐장치) 철거, 설치 × 1식 - GIS(40kA 4000A) 철거 × 6CB - GIS(50kA 4000A) 설치 × 6CB ○ 설치 GIS 기초 보강공사 × 1식 ○ 제어케이블 철거, 설치 및 기타 부대공사 × 1식","2017-11-25 09:00","2017-12-11 18:00","취소","취소","연속",null,null,"계통안정",201708170142,"-"]
[132,"충북","청주","청원S/S 345kV #1 BUS","청원S/S 345kV 장기사용 GIS 대체공사(전문)","○ 345kV GIS(가스절연개폐장치) 철거, 설치 × 1식 - GIS(40kA 4000A) 철거 × 6CB - GIS(50kA 4000A) 설치 × 6CB ○ 설치 GIS 기초 보강공사 × 1식 ○ 제어케이블 철거, 설치 및 기타 부대공사 × 1식","2017-11-08 09:00","2017-11-24 18:00","취소","취소","연속",null,null,"계통안정",201708170141,"-"]
[133,"충북","충주","청원신진천#2 T/L","345kV 신진천S/S 용량부족 GIS 대체공사","345kV #72BAY 3CB 철거 345kV #72BAY 3CB 기초보강 345kV #72BAY 3CB 신설","2017-11-01 09:00","2018-03-09 18:00","2017-11-01 09:00","2018-03-09 18:00","연속",null,null,null,201709180059,"-"]
[134,"충북","충주","신진천S/S #1 M.Tr A","345kV 신진천S/S 용량부족 GIS 대체공사","345kV #72BAY 3CB 철거 345kV #72BAY 3CB 기초보강 345kV #72BAY 3CB 신설","2017-11-01 09:00","2018-03-09 18:00","2017-11-01 09:00","2018-03-09 18:00","연속",null,null,null,201709180058,"-"]
[135,"대전충남","서산","신당진개폐소현대제철 T/L","'17년 변전협력회사 총액공사","신당진S/S 345kV 개폐소-현대제철T/L CVT,LA 대체","2017-11-04 09:00","2017-11-05 18:00","2017-11-04 09:00","2017-11-05 18:00","연속",null,null,null,201709080374,"-"]
[136,"대전충남","서산","신당진개폐소북당진 T/L","'17년 변전협력회사 총액공사","신당진S/S 345kV 개폐소-북당진T/L CVT,LA 초기점검","2017-11-06 09:00","2017-11-06 18:00","2017-11-06 09:00","2017-11-06 18:00","당일",null,null,null,201709080371,"-"]
[137,"대전충남","서산","신서산신당진#2 T/L","'17년 변전협력회사 총액공사","신당진S/S 345kV 신서산-신당진#2T/L CVT 대체","2017-11-08 09:00","2017-11-08 18:00","2017-11-08 09:00","2017-11-08 18:00","당일",null,null,null,201709080377,"-"]
[138,"대전충남","서산","신당진S/S 신서산-신당진#1T/L CB (7172)","'17년 변전협력회사 총액공사","신당진S/S 345kV 신서산-신당진#1T/L GIS(7172) 보통점검","2017-11-01 09:00","2017-11-01 18:00","2017-11-01 09:00","2017-11-01 18:00","당일",null,null,null,201709080366,"-"]
[139,"대전충남","서산","신당진S/S 7171 CB (7171)","'17년 변전협력회사 총액공사","신당진S/S 345kV 7171 GIS 보통점검","2017-11-02 09:00","2017-11-02 18:00","2017-11-02 09:00","2017-11-02 18:00","당일",null,null,null,201709080368,"-"]
[140,"대전충남","서산","신서산S/S 345kV #3 Sh.R","'17년 변전협력회사 총액공사","신서산S/S 345kV #3Sh.R 보통점검","2017-11-03 09:00","2017-11-03 18:00","2017-11-03 09:00","2017-11-03 18:00","당일",null,null,null,201709080370,"-"]
[141,"대전충남","서산","신당진개폐소태안화력#1 T/L","태안화력 345kV 용량부족 및 장기사용 GIS 교체공사","ㅇ 63KA, 6300A CB 4대 대체(7300, 7372, 70710, 75760) ㅇ 금회휴전 시 - 70710 GIS 조립(중장비사용) - 송전선로휴전사유 : 기기설치시 인출 활선 근접부 안전이격확보","2017-11-04 08:00","2017-11-05 17:00","2017-11-04 08:00","2017-11-05 17:00","매일",null,null,null,201709220012,"-"]
[142,"대전충남","서산","태안T/P 345kV #75 BUS","태안화력 345kV 용량부족 및 장기사용 GIS 교체공사","ㅇ 63KA, 6300A CB 4대 대체(7300, 7372, 70710, 75760) ㅇ 금회휴전 시 - 11/26~12/19 : 7300,7372 GIS (75 BUS측) 철거,설치","2017-11-26 09:00","2017-12-19 17:00","2017-11-26 09:00","2017-12-19 17:00","연속",null,null,null,201709220013,"-"]
[143,"대전충남","아산","아산S/S #4 M.Tr A","아산S/S 345kV #4M.Tr 보호배전반 교체공사","○ 345kV #4M.Tr 보호배전반 교체공사","2017-11-20 09:00","2017-11-26 18:00","2017-11-20 09:00","2017-11-26 18:00","연속",null,null,null,201708100282,"-"]
[144,"대전충남","청양","보령C/C 청양보령복합T/L CB (7371)","보령C/C 362kV GIS 정밀점검","-7371CB","2017-11-27 09:00","2017-11-29 18:00","2017-11-27 09:00","2017-11-29 18:00","연속",null,null,null,201709060372,"-"]
[145,"대전충남","청양","보령C/C 보령연락#2T/L-#2 M.Tr 1차 CB (7200)","보령C/C 362kV GIS 정밀점검","-7200CB","2017-11-20 09:00","2017-11-22 18:00","2017-11-20 09:00","2017-11-22 18:00","연속",null,null,null,201709060369,"-"]
[146,"대전충남","청양","보령C/C #2 M.Tr 1차 CB (7272)","보령C/C 362kV GIS 정밀점검","-7272CB","2017-11-23 09:00","2017-11-25 18:00","2017-11-23 09:00","2017-11-25 18:00","연속",null,null,null,201709060370,"-"]
[147,"대전충남","청양","청양군산#2 T/L","청양S/S 345kV 청양-군산#2T/L CVT 교체","CVT 교체","2017-11-15 09:00","2017-11-15 18:00","2017-11-15 09:00","2017-11-15 18:00","연속",null,null,null,201709040137,"-"]
[148,"대전충남","청양","청양군산#1 T/L","청양S/S 345kV 청양-군산#1T/L CVT 교체","CVT 교체","2017-11-08 09:00","2017-11-09 18:00","2017-11-08 09:00","2017-11-09 18:00","연속",null,null,null,201709040136,"-"]
[149,"대전충남","청양","신계룡청양 T/L","청양S/S 345kV 신계룡-청양T/L LA, CVT 교체","LA, CVT 교체","2017-11-01 09:00","2017-11-02 18:00","2017-11-02 09:00","2017-11-03 18:00","연속",null,null,"한전요청",201709040134,"-"]
[150,"대전충남","청양","청양보령화력#1 T/L","청양S/S 345kV 청양-보령화력#1T/L LA, CVT 교체","○ 청양S/S 345kV 청양-보령화력#1T/L LA, CVT 교체","2017-11-13 09:00","2017-11-14 18:00","2017-11-13 09:00","2017-11-14 18:00","연속",null,null,null,201709200144,"-"]
[151,"전북","군산","군산S/S #4 M.Tr A","군산S/S #4 M.Tr A","NGK 부싱 절연유 체취","2017-11-14 09:00","2017-11-14 18:00","2017-11-14 09:00","2017-11-14 18:00","당일",null,null,null,201709220093,"-"]
[152,"전북","직할","신남원S/S #1 M.Tr CB","신남원S/S #1 M.Tr CB(7772)","1. 신남원S/S 345kV 7772CB 초기점검","2017-11-15 10:00","2017-11-15 18:00","2017-11-15 10:00","2017-11-15 18:00","당일",null,null,null,201709220023,"-"]
[153,"전북","직할","신남원신광주#2 T/L","154kV 신남원-남원T/L 건설공사","(휴전작업 : 345kV 신남원-신광주T/L 병가관련 휴전) 154kV 신남원-남원T/L 건설공사 - 구 간 : 기설 345kV 신남원S/S ~ 기설 154kV 남원S/S - 전 력 선 : ACSR 410㎟ × 2B - 규 모 : 11.81㎞ / 철탑 : 31기","2017-11-27 08:00","2017-12-08 18:00","2017-11-27 08:00","2017-12-08 18:00","연속",null,null,null,201709150082,"-"]
[154,"전북","직할","신남원S/S 신남원-신광주#1 - TIE CB (7700)","신남원S/S 신남원-신광주#1 - TIE CB(7700)","1. 신남원S/S 345kV 7700CB 병행휴전","2017-11-16 10:00","2017-11-16 18:00","2017-11-16 10:00","2017-11-16 18:00","당일",null,null,null,201709220024,"-"]
[155,"전북","직할","신남원S/S #1 M.Tr A","345kV 신남원S/S 154kV #61D.Tr 증설공사","154kV 주변압기(15/20MVA×3)×1Bank 설치 170kV GIS(1250A, 50kA)×1CCT증설 25.8kV SIS × 6CCT설치","2017-11-28 10:00","2017-11-29 10:00","2017-11-28 10:00","2017-11-29 10:00","당일",null,null,null,201709270096,"-"]
[156,"전북","직할","신옥천신남원#2 T/L","345kV 신옥천-신남원T/L No.74 안전이격확보공사","□ 철탑철거 : 2기 [No.73(A-18), No.74(B-14)] □ 철탑설치 : 1기 [No.74(Ba2-60)] □ 전력선 교체 : 0.464km [HSTACIR 410㎟ x 2B] , 12가닥","2017-11-22 07:00","2017-12-03 18:00","2017-11-22 07:00","2017-12-03 18:00","연속",null,null,null,201709270095,"-"]
[157,"전북","직할","신옥천신남원#1 T/L","345kV 신옥천-신남원T/L No.74 안전이격확보공사","□ 철탑철거 : 2기 [No.73(A-18), No.74(B-14)] □ 철탑설치 : 1기 [No.74(Ba2-60)] □ 전력선 교체 : 0.464km [HSTACIR 410㎟ x 2B] , 12가닥","2017-11-19 07:00","2017-11-21 18:00","2017-11-19 07:00","2017-11-21 18:00","당일",null,null,null,201709270094,"-"]
[158,"광주전남","강진","신강진S/S #1 M.Tr A","345kV 신강진S/S #1M.Tr(신강진S/S 취약설비 GIS화공사)","공사명 : 신강진S/S 154kV 옥외철구 GIS화 공사(일반) 휴전일 : 2017. 11. 12 09:00 ~ 11.14 18:00 설비명 : 신강진S/S #1M.Tr","2017-11-12 09:00","2017-11-14 18:00","2017-11-12 09:00","2017-11-14 18:00","연속",null,null,"조건부 승인 - 부하수준에 따라 취소될 수 있음",201709110497,"-"]
[159,"광주전남","강진","신강진S/S #3 M.Tr A","345kV 신강진S/S #3M.Tr(신강진S/S 취약설비 GIS화공사)","공사명 : 신강진S/S 154kV 옥외철구 GIS화 공사(일반) 휴전일 : 2017. 11. 30 09:00 ~ 12.3 18:00 설비명 : 신강진S/S #3M.Tr","2017-11-30 09:00","2017-12-03 18:00","2017-11-30 09:00","2017-12-03 18:00","연속",null,null,"조건부 승인 - 부하수준에 따라 취소될 수 있음",201709110500,"-"]
[160,"광주전남","강진","신화순신강진#1 T/L","345kV 신화순-신강진#1T/L(피뢰기 설치공사)","345kV 신화순-신강진#1T/L(피뢰기 설치공사) - 345kV 신화순-신강진 등 10개T/L 송전선로용 피뢰기 설치공사","2017-11-28 07:00","2017-12-14 18:00","2017-11-17 07:00","2017-12-03 18:00","매일",null,null,"일정변경 - 한전요청",201709050069,"-"]
[161,"광주전남","강진","신강진광양#2 T/L","345kV 신강진-광양#2T/L(피뢰기 설치공사)","345kV 신강진-광양#2T/L(피뢰기 설치공사) - 345kV 신화순-신강진 등 10개T/L 송전선로용 피뢰기 설치공사","2017-11-09 07:00","2017-11-23 18:00","2017-12-04 07:00","2017-12-20 18:00","매일",null,null,"일정변경 - 한전요청",201709050065,"-"]
[162,"광주전남","강진","신강진S/S #2 M.Tr A","345kV 신강진S/S #2M.Tr(신강진S/S 취약설비 GIS화공사)","공사명 : 신강진S/S 154kV 옥외철구 GIS화 공사(일반) 휴전일 : 2017. 11. 23 09:00 ~ 11.25 18:00 설비명 : 신강진S/S #2M.Tr","2017-11-23 09:00","2017-11-25 18:00","2017-11-23 09:00","2017-11-25 18:00","연속",null,null,"조건부 승인 - 부하수준에 따라 취소될 수 있음",201709110498,"-"]
[163,"광주전남","광주","신광주S/S #1 M.Tr A","신광주S/S #1 M.Tr(변전협력회사공사)","#1M.Tr 부싱 절연유 채취 및 절연열화측정","2017-11-01 09:00","2017-11-01 18:00","2017-11-01 09:00","2017-11-01 18:00","당일",null,null,null,201709050145,"-"]
[164,"광주전남","광주","신광주S/S #3 M.Tr A","신광주S/S #3 M.Tr(변전협력회사공사)","#3M.Tr 부싱 절연유 채취 및 절연열화측정","2017-11-07 09:00","2017-11-07 18:00","2017-11-07 09:00","2017-11-07 18:00","당일",null,null,null,201709050147,"-"]
[165,"광주전남","광주","신화순S/S #3 M.Tr A","신화순S/S #3 M.Tr(누유보수,점검)","3차 부싱 누유개소 보수(정밀) 신화순S/S #3 M.Tr 3차 4389 VCB 보통점검 3-2ESS S.Tr 초기점검 #3S.Tr 유사고장 처리","2017-11-02 09:00","2017-11-03 18:00","2017-11-02 09:00","2017-11-03 18:00","연속",null,null,null,201707270044,"-"]
[166,"광주전남","순천","광양하동화력#1 T/L","345kV 광양-하동화력#1 T/L 가공송전 순시점검 위탁공사","2017년 가공송전 순시점검 위탁공사 - 정밀점검 (26~73호, 48기)","2017-11-26 08:00","2017-12-02 18:00","취소","취소","매일",null,null,"취소 - 계통안정",201709080274,"-"]
[167,"광주전남","순천","신강진광양#1 T/L","345kV 신강진광양#1 T/L 가공송전 순시점검 위탁공사","2017년 가공송전 순시점검 위탁공사 - 정밀점검 (26~73호, 48기) - 광양-하동TP #1T/L 병가구간","2017-11-26 08:00","2017-11-26 18:00","취소","취소","당일",null,null,"취소 - 계통안정",201709080275,"-"]
[168,"광주전남","순천","여수T/P #3 Tie-Tr","345kV 여수T/P #3 M.Tr 변압기 붓싱 절연유체유","345kV 여수T/P #3 M.Tr 변압기 붓싱 절연유체유","2017-11-21 09:00","2017-11-21 18:00","2017-11-21 09:00","2017-11-21 18:00","당일",null,null,null,201709120187,"-"]
[169,"대구","경산","신경산S/S #2 M.Tr A","신경산S/S 345kV #2M.TR 휴전","3차 LA A,B,C 상 교체","2017-11-03 09:00","2017-11-03 18:00","2017-11-03 09:00","2017-11-03 18:00","당일",null,null,null,201709110108,"-"]
[170,"대구","경산","신경산대구#1 T/L","2017년 경산전력지사 가공송전 순시점검 위탁공사","경산자인#2 T/L 선로 정밀점검 안전확보","2017-11-20 08:00","2017-11-22 18:00","2017-11-20 08:00","2017-11-22 18:00","연속",null,null,null,201709110352,"-"]
[171,"대구","경산","신경산대구#2 T/L","신경산S/S 신경산-대구#2T/L 휴전","72BAY B/F PNL 대체","2017-11-27 09:00","2017-12-01 18:00","2017-11-27 09:00","2017-12-01 18:00","연속",null,null,null,201708140282,"-"]
[172,"대구","경산","신경산S/S #4 M.Tr A","신경산S/S 345kV #4M.TR 휴전","#62-67 BUS PRO 교체공사","2017-11-08 16:00","2017-11-08 16:30","취소","취소","당일",null,null,"한전 요청",201709110097,"-"]
[173,"대구","달성","북경남고령#2 T/L","스페이서댐퍼 불량정비공사","345kV 북경남-고령#2T/L 스페이서댐퍼 불량정비공사 No.1~39","2017-11-06 08:00","2017-11-10 18:00","2017-11-06 08:00","2017-11-10 18:00","연속",null,null,null,201709110342,"-"]
[174,"대구","달성","북경남고령#1 T/L","스페이서댐퍼 불량정비공사","345kV 북경남-고령#1T/L 스페이서댐퍼 불량정비공사 No.1~39","2017-11-01 08:00","2017-11-04 18:00","2017-11-01 08:00","2017-11-04 18:00","연속",null,null,null,201709110337,"-"]
[175,"대구","달성","고령의령#2 T/L","달성전력지사 변전총액공사","달성전력지사 변전총액공사(송전선로 보호반 PNL 교체)","2017-11-18 09:00","2017-11-24 18:00","취소","취소","연속",null,null,"한전 요청",201709110003,"-"]
[176,"대구","달성","서대구고령#2 T/L","달성전력지사 변전총액공사","달성전력지사 변전총액공사(75B/F, 송전선로 보호반 PNL 교체)","2017-11-11 09:00","2017-11-17 18:00","2017-11-11 09:00","2017-11-17 18:00","연속",null,null,null,201709110002,"-"]
[177,"대구","달성","북경남대구#2 T/L","스페이서댐퍼 불량정비공사","345kV 북경남-대구#2T/L 스페이서댐퍼 불량정비공사 No.1~39","2017-11-06 08:00","2017-11-10 18:00","2017-11-06 08:00","2017-11-10 18:00","연속",null,null,null,201709110341,"-"]
[178,"대구","달성","북경남대구#1 T/L","스페이서댐퍼 불량정비공사","345kV 북경남-대구#1T/L 스페이서댐퍼 불량정비공사 No.1~39","2017-11-01 08:00","2017-11-04 18:00","2017-11-01 08:00","2017-11-04 18:00","연속",null,null,null,201709110334,"-"]
[179,"대구","칠곡","북대구S/S 북대구-선산T/L CB (7272)","북대구S/S 북대구-선산T/L CB (7272) 휴전","북대구S/S 북대구-선산T/L CB (7272) 장기미동작 점검","2017-11-13 14:00","2017-11-13 18:00","2017-11-13 14:00","2017-11-13 18:00","당일",null,null,null,201709110425,"-"]
[180,"대구","칠곡","북대구S/S 345kV #2 BUS","2017년 칠곡전력지사 차단기 정밀점검공사","2017년 칠곡전력지사 차단기 정밀점검공사(7352,7452)","2017-11-27 09:30","2017-11-28 18:00","2017-11-27 09:30","2017-11-28 18:00","연속",null,null,null,201709180159,"-"]
[181,"대구","칠곡","북대구S/S #1 M.Tr A","2017년 칠곡전력지사 차단기 정밀점검공사","2017년 칠곡전력지사 차단기 정밀점검공사(7372)","2017-11-20 09:30","2017-11-23 18:00","2017-11-20 09:30","2017-11-23 18:00","연속",null,null,null,201709180157,"-"]
[182,"대구","칠곡","북대구S/S #2 M.Tr A","2017년 칠곡전력지사 차단기 정밀점검공사","2017년 칠곡전력지사 차단기 정밀점검공사(7472, 7400)","2017-11-13 09:30","2017-11-18 18:00","2017-11-13 09:30","2017-11-18 18:00","연속",null,null,null,201709180156,"-"]
[183,"대구","칠곡","서대구선산#2 T/L","서대구선산#2 T/L 휴전","서대구 78Bay BF반 교체, 장기미동작 CB 점검","2017-11-06 09:30","2017-11-10 18:00","2017-11-06 09:30","2017-11-10 18:00","연속",null,null,null,201709110413,"-"]
[184,"대구","칠곡","서대구S/S #3 M.Tr A","서대구S/S #3 M.Tr 휴전","서대구 76Bay BF반 교체, #2M.Tr 2차 CB(6344) 장기미동작 점검, #3M.Tr 1차 CVT, 3차 LA 교체","2017-11-27 09:30","2017-12-01 18:00","2017-11-27 09:30","2017-12-01 18:00","연속",null,null,null,201709110438,"-"]
[185,"대구","칠곡","서대구S/S #4 M.Tr A","서대구S/S #4 M.Tr 휴전","서대구S/S #4 M.Tr 3차 LA 교체, 2차 CB(6244) 장기미동작 점검","2017-11-17 09:30","2017-11-17 18:00","2017-11-17 09:30","2017-11-17 18:00","당일",null,null,null,201709110432,"-"]
[186,"대구","칠곡","북대구서대구#1 T/L","북대구서대구#1 T/L 휴전","서대구 78Bay BF반 교체","2017-11-06 09:30","2017-11-10 18:00","2017-11-06 09:30","2017-11-10 18:00","연속",null,null,null,201709110414,"-"]
[187,"대구","칠곡","서대구S/S #2 M.Tr A","서대구S/S #2 M.Tr 휴전","서대구 75Bay BF반 교체, #2M.Tr 2차 CB(6244) 장기미동작 점검, #2M.Tr 3차 LA 교체","2017-11-20 09:30","2017-11-24 18:00","2017-11-20 09:30","2017-11-24 18:00","연속",null,null,null,201709110435,"-"]
[188,"대구","포항","신포항북대구 T/L","345kV 신포항-북대구T/L 피뢰기설치공사","345kV 신포항-북대구T/L No.149 ~ 276 피뢰기 설치공사","2017-11-01 09:00","2017-11-15 18:00","2017-11-01 09:00","2017-11-15 18:00","연속",null,null,null,201709110099,"-"]
[189,"대구","포항","선산신포항 T/L","기설 항공장애표시등 구조개선 및 피뢰기 설치공사","345kV 신포항-북대구T/L No.114~115, 147~148 가공지선 항공장애표시구 설치","2017-11-17 08:00","2017-11-17 18:00","2017-11-17 08:00","2017-11-17 18:00","당일",null,null,null,201709110006,"-"]
[190,"경북","영주","신영주S/S #1 M.Tr A","주변압기 부싱 절연열화진단","주변압기 부싱 절연열화진단","2017-11-02 09:00","2017-11-02 14:00","2017-11-02 09:00","2017-11-02 14:00","당일",null,null,null,201709150030,"○"]
[191,"경북","영주","(신)신영주S/S 345kV #1 BUS","신영주S/S STATCOM 설치공사","신영주S/S STATCOM 설치공사","2017-11-27 10:00","2017-11-28 10:00","2017-11-13 10:00","2017-11-14 10:00","연속",null,null,"계통안정",201709110231,"○"]
[192,"경북","영주","신제천신영주#1 T/L","신영주S/S STATCOM 설치공사","신영주S/S STATCOM 설치공사","2017-11-27 10:00","2017-11-29 10:00","2017-11-13 10:00","2017-11-15 10:00","연속",null,null,"계통안정",201709110236,"○"]
[193,"경북","영주","신영주S/S #2 M.Tr A","주변압기 부싱 절연열화진단","주변압기 부싱 절연열화진단","2017-11-02 14:00","2017-11-08 18:00","2017-11-02 14:00","2017-11-08 18:00","당일",null,null,null,201709010005,"○"]
[194,"경북","영주","(신)신영주S/S 345kV #2 BUS","신영주S/S STATCOM 설치공사","신영주S/S STATCOM 설치공사","2017-11-28 10:00","2017-11-29 10:00","2017-11-14 10:00","2017-11-15 10:00","연속",null,null,"계통안정",201709110235,"○"]
[195,"경북","영주","삼척GP한울NP1#2 T/L","한울1발S/Y 345kV 74BAY 차단기 정밀점검","7471,7400, 7472 CB 정밀점검(한수원 2호기 M.Tr O/H(7400, 7472) 병행)","2017-11-13 09:00","2017-11-20 18:00","취소","취소","연속",null,null,"한전요청",201709120142,"-"]
[196,"경북","직할","안동복합S/Y 신영주-안동CC T/L CB (7271)","안동복합S/Y SPS PNL 시험","안동복합S/Y SPS PNL 시험","2017-11-28 13:30","2017-11-28 14:00","2017-11-28 13:30","2017-11-28 14:00","당일",null,null,null,201708310050,"○"]
[197,"경북","직할","안동복합S/Y 신영주-안동CCT/L-TIE CB (7200)","안동복합S/Y SPS PNL 시험","안동복합S/Y SPS PNL 시험","2017-11-28 13:00","2017-11-28 13:30","2017-11-28 13:00","2017-11-28 13:30","당일",null,null,null,201708310049,"○"]
[198,"경북","직할","안동복합S/Y 신영일-안동CCT/L-TIE CB (7300)","안동복합S/Y SPS PNL 시험","안동복합S/Y SPS PNL 시험","2017-11-28 14:00","2017-11-28 14:30","2017-11-28 14:00","2017-11-28 14:30","당일",null,null,null,201708310051,"○"]
[199,"경북","직할","안동복합S/Y 신영일-안동CC T/L CB (7371)","안동복합S/Y SPS PNL 시험","안동복합S/Y SPS PNL 시험","2017-11-28 14:30","2017-11-28 15:00","2017-11-28 14:30","2017-11-28 15:00","당일",null,null,null,201708310052,"○"]
[200,"경북","직할","신포항청송PP T/L","2017년도 상반기 안동P/O 362kV GIS 정밀점검공사","2017년도 상반기 안동P/O 362kV GIS 정밀점검공사","2017-11-27 09:00","2017-11-29 18:00","2017-11-28 09:00","2017-11-30 18:00","연속",null,null,"계통안정",201709190089,"○"]
[201,"경북","직할","청송P/P 345kV #1 BUS","2017년도 상반기 안동P/O 362kV GIS 정밀점검공사","2017년도 상반기 안동P/O 362kV GIS 정밀점검공사","2017-11-27 09:00","2017-11-29 18:00","2017-11-28 09:00","2017-11-30 18:00","연속",null,null,"계통안정",201709190088,"○"]
[202,"경북","영주","신영주한울NP2#1 T/L","345kV 신영주-한울NP2 T/L 전선접속개소 전력선교체공사","□ 공사구간 : 345kV 신영주-한울NP2T/L 43∼75호 □ 공사내용 : 전력선 교체 ACSR 480㎟×4B×2C 22.272C-km","2017-11-13 07:00","2017-11-27 18:00","2017-11-20 07:00","2017-12-04 18:00","연속",null,null,"계통안정-주변휴전과 일정조정필요"]
[203,"경북","영주","신영주한울NP2#2 T/L","345kV 신영주-한울NP2 T/L 전선접속개소 전력선교체공사","□ 공사구간 : 345kV 신영주-한울NP2T/L 43∼75호 □ 공사내용 : 전력선 교체 ACSR 480㎟×4B×2C 22.272C-km","2017-11-28 07:00","2017-12-12 18:00","2017-12-05 07:00","2017-12-19 18:00","연속",null,null,"계통안정-주변휴전과 일정조정필요"]
[204,"부산울산","동부산","신양산S/S #1 M.Tr A","345kV 신양산S/S 현대화공사","T-BUS 철거","2017-11-01 09:00","2017-11-02 18:00","2017-11-01 09:00","2017-11-02 18:00","연속",null,null,null,201708300082,"-"]
[205,"부산울산","동부산","신양산S/S #2 M.Tr A","345kV 신양산S/S 현대화공사","T-BUS 철거","2017-11-05 09:00","2017-11-06 18:00","2017-11-05 09:00","2017-11-06 18:00","연속",null,null,null,201708300083,"-"]
[206,"부산울산","동부산","신양산S/S #4 M.Tr A","345kV 신양산S/S 현대화공사","T-BUS 철거","2017-11-11 09:00","2017-11-12 18:00","2017-11-11 09:00","2017-11-12 18:00","연속",null,null,null,201708300085,"-"]
[207,"부산울산","동부산","신양산S/S #3 M.Tr A","345kV 신양산S/S 현대화공사","T-BUS 철거","2017-11-07 09:00","2017-11-08 18:00","2017-11-07 09:00","2017-11-08 18:00","연속",null,null,null,201708300084,"-"]
[208,"부산울산","북부산","북부산S/S #1 M.Tr A","북부산S/S 154kV 취약설비 GIS화 공사","북부산S/S 345kV #1M.Tr 2차측 GIS 인출변경 휴전","2017-11-02 08:00","2017-11-10 18:00","2017-11-02 08:00","2017-11-10 18:00","연속",null,null,null,201709070192,"-"]
[209,"부산울산","북부산","북부산S/S 서부산#2T/L-#4Sh.R 1차 CB(신) ((신)7900)","345kV 북부산S/S 차단기용량대체공사","1. #4Sh.R 인출변경(#70BUS → 신 79BAY GIS) 2. PNL 이설 준공시험 3. 사용전검사","2017-11-09 09:00","2017-11-14 18:00","2017-11-09 09:00","2017-11-14 18:00","연속",null,null,null,201709070033,"-"]
[210,"부산울산","북부산","북부산S/S #4Sh.R 1차 CB(신) ((신)7972)","345kV 북부산S/S 차단기용량대체공사","1. #4Sh.R 인출변경(#70BUS → 신 79BAY GIS) 2. PNL 이설 준공시험 3. 사용전검사","2017-11-09 09:00","2017-11-14 18:00","2017-11-09 09:00","2017-11-14 18:00","연속",null,null,null,201709070032,"-"]
[211,"부산울산","북부산","서부산북부산#2 T/L","345kV 북부산S/S 차단기용량대체공사","#4Sh.R 이설 시험가압 선로","2017-11-11 10:00","2017-11-12 10:00","2017-11-11 10:00","2017-11-12 10:00","연속",null,null,null,201709070034,"-"]
[212,"부산울산","북부산","북부산S/S #2 M.Tr A","345kV 북부산S/S #2M.Tr 대체공사","북부산S/S #2M.Tr 대체 - 기설 변압기 철거 및 신규 변압기 설치","2017-11-11 09:00","2017-12-13 15:00","2017-11-11 09:00","2017-12-13 15:00","연속",null,null,null,201709050087,"-"]
[213,"부산울산","서부산","서부산S/S 345kV #2 Sh.R","서부산S/S 345kV #2Sh.R 열교환기 보수 및 하자점검","서부산S/S 345kV #2Sh.R 열교환기 보수 및 하자점검","2017-11-13 10:00","2017-11-19 18:00","2017-11-13 10:00","2017-11-19 18:00","연속",null,null,null,201709040052,"-"]
[214,"부산울산","울산","동울산월성NP#1 T/L","345kV 동울산-신울산T/L 피뢰기설치공사(안전확보)","345kV 동울산-신울산#1T/L 피뢰기설치공사(안전확보)","2017-11-20 09:00","2017-11-21 18:00","2017-11-20 09:00","2017-11-21 18:00","연속",null,null,null,201709110151,"○"]
[215,"부산울산","울산","동울산신울산#1 T/L","345kV 동울산-신울산T/L 피뢰기설치공사","345kV 동울산-신울산T/L No.1~70 피뢰기설치공사","2017-11-20 09:00","2017-11-26 18:00","2017-11-20 09:00","2017-11-26 18:00","연속",null,null,null,201709110147,"○"]
[216,"부산울산","울산","동울산S/S #3 M.Tr A","동울산S/S 154kV Sh.C 설치공사(154kV GIS 설치)","동울산S/S 154kV Sh.C 설치공사-154kV 모선분리에 따른 제어케이블 변경","2017-11-18 09:00","2017-11-18 14:00","2017-11-28 09:00","2017-11-28 14:00","당일",null,null,"일정변경 - 한전요청",201709080024,"-"]
[217,"부산울산","울산","신온산S/S #4 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","신온산S/S 345V #4M.Tr C상 요주의 변압기 내부점검","2017-11-22 09:00","2017-11-25 18:00","2017-11-22 09:00","2017-11-25 18:00","연속",null,null,null,201709060499,"-"]
[218,"부산울산","울산","북부산신온산 T/L","345kV 동울산-신울산#1 등 7개 T/L 전선접속개소 전선교체공사","- 전선접속개소 전선교체공사 : 22~24호(전체 12가닥) - 노후 애자금구류 교체","2017-11-17 07:00","2017-11-21 18:00","2017-11-17 07:00","2017-11-21 18:00","연속",null,null,null,201706160057,"-"]
[219,"부산울산","울산","신온산S/S #1 M.Tr A","2017년 관내 노후배전반 대체공사","신온산S/S 345kV #1M.Tr 보호반 대체","2017-11-27 09:00","2017-11-30 18:00","2017-11-27 09:00","2017-11-30 18:00","연속",null,null,null,201709180048,"-"]
[220,"부산울산","울산","신울산S/S #2 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","신울산S/S 345V #2M.Tr 2,3차 GCB 보통점검 및 #2S.Tr 보통점검","2017-11-13 09:00","2017-11-13 18:00","2017-11-12 09:00","2017-11-12 18:00","당일",null,null,"일정변경 - 한전요청",201709060493,"-"]
[221,"부산울산","울산","신울산S/S #4 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","신울산S/S 345kV #4M.Tr 2차 GCB 보통점검","2017-11-10 09:00","2017-11-10 18:00","2017-11-10 09:00","2017-11-10 18:00","당일",null,null,null,201709060494,"-"]
[222,"부산울산","울산","신울산S/S #1 M.Tr A","2017년 울산P/O 장기사용 개폐장치 대체공사","신울산S/S 345kV #1M.Tr 2차 GCB(6164) 대체","2017-11-06 07:00","2017-11-09 18:00","2017-11-06 07:00","2017-11-09 18:00","연속",null,null,null,201709060495,"-"]
[223,"부산울산","울산","신온산울산TP T/L","2016~2017년 울산전력지사 송전정비 협력회사 총액공사","노후애자금구류 교체 및 송전용 피뢰기 설치","2017-11-02 08:00","2017-11-15 18:00","2017-11-02 08:00","2017-11-15 18:00","연속",null,null,null,201709060253,"-"]
[224,"부산울산","울산","울주고리NP#2 T/L","345kV 울주-고리NPT/L 전선접속개소 전선교체공사","전선접속개소 전선교체, 구간: 7~19호, 68~74호, 5.867km","2017-11-17 08:00","2017-11-27 18:00","2017-11-17 08:00","2017-11-27 18:00","연속",null,null,null,201709060116,"-"]
[225,"부산울산","울산","울주S/S #3 M.Tr A","울주S/S #2M.Tr 증설공사","- M.Tr N상 모선 및 154kV 예비모선 연결 작업관련 안전이격 확보차","2017-11-02 09:00","2017-11-02 18:00","2017-11-02 09:00","2017-11-02 18:00","당일",null,null,null,201709080218,"-"]
[226,"부산울산","울산","울주고리NP#1 T/L","345kV 울주-고리NPT/L 전선접속개소 전선교체공사","전선접속개소 전선교체, 구간: 7~19호, 68~74호, 5.867km","2017-11-03 08:00","2017-11-15 18:00","2017-11-03 08:00","2017-11-15 18:00","연속",null,null,null,201709060115,"-"]
[227,"부산울산","울산","울주고리NP#2 T/L","울주S/S #2M.Tr 증설공사","- #2M.Tr 최초가압 시험가압 선로","2017-11-28 09:00","2017-11-29 18:00","2017-11-28 09:00","2017-11-29 18:00","연속",null,null,null,201709080247,"-"]
[228,"부산울산","울산","울주S/S 345kV #2 BUS","울주S/S #2M.Tr 증설공사","- #2M.Tr 최초가압","2017-11-28 09:00","2017-11-29 18:00","2017-11-28 09:00","2017-11-29 18:00","연속",null,null,null,201709080220,"-"]
[229,"부산울산","직할","신대연S/S 신양산-신대연#1T/L CB (7171)","LS산전 345kV GIS 차단기 불량관련 성능개선 공사(7171)","차단기 성능개선 - Puffer cylinder 강도 개선 제품으로 교체 - 투입저항부 구조 및 조림 공정 개선 제품으로 교체","2017-11-06 09:00","2017-11-12 16:00","2017-11-06 09:00","2017-11-12 16:00","연속",null,null,null,201708280138,"-"]
[230,"부산울산","직할","신양산신대연#1 T/L","LS산전 345kV GIS 차단기 불량관련 성능개선 공사(7171)","LS산전 345kV GIS 차단기 불량관련 성능개선 공사(7171) 시험가압선로","2017-11-11 16:00","2017-11-12 16:00","2017-11-11 16:00","2017-11-12 16:00","연속",null,null,null,201708290095,"-"]
[231,"부산울산","직할","신대연S/S TIE-#1M.Tr 1차 CB (7100)","LS산전 345kV GIS 차단기 불량관련 성능개선 공사(7100)","차단기 성능개선 - Puffer cylinder 강도 개선 제품으로 교체 - 투입저항부 구조 및 조림 공정 개선 제품으로 교체","2017-11-13 09:00","2017-11-19 16:00","2017-11-13 09:00","2017-11-19 16:00","연속",null,null,null,201708280139,"-"]
[232,"부산울산","직할","신대연S/S 신양산-신대연#2T/L CB (7271)","LS산전 345kV GIS 차단기 불량관련 성능개선 공사(7271)","차단기 성능개선 - Puffer cylinder 강도 개선 제품으로 교체 - 투입저항부 구조 및 조림 공정 개선 제품으로 교체","2017-11-20 09:00","2017-11-26 16:00","2017-11-20 09:00","2017-11-26 16:00","연속",null,null,null,201708280140,"-"]
[233,"부산울산","직할","신대연S/S TIE-#2M.Tr 1차 CB (7200)","LS산전 345kV GIS 차단기 불량관련 성능개선 공사(7200)","차단기 성능개선 - Puffer cylinder 강도 개선 제품으로 교체 - 투입저항부 구조 및 조림 공정 개선 제품으로 교체","2017-11-27 09:00","2017-12-03 16:00","2017-11-27 09:00","2017-12-03 16:00","연속",null,null,null,201708280141,"-"]
[234,"부산울산","직할","신양산신대연#2 T/L","LS산전 345kV GIS 차단기 불량관련 성능개선 공사(7271)","LS산전 345kV GIS 차단기 불량관련 성능개선 공사(7271) 시험가압선로","2017-11-25 16:00","2017-11-26 16:00","2017-11-25 16:00","2017-11-26 16:00","연속",null,null,null,201708290099,"-"]
[235,"부산울산","직할","신양산신대연#1 T/L","LS산전 345kV GIS 차단기 불량관련 성능개선 공사(7100)","LS산전 345kV GIS 차단기 불량관련 성능개선 공사(7100) 시험가압선로","2017-11-18 16:00","2017-11-19 16:00","2017-11-18 16:00","2017-11-19 16:00","연속",null,null,null,201708290098,"-"]
[236,"경남","직할","신김해삼천포화력#1 T/L","345kV 창원S/S 건설사업","345kV 창원S/S 무부하 가압 및 사용전 검사 345kV 창원분기T/L 건설공사 - No.1 철탑조립 및 가선, 사용전검사","2017-11-06 08:00","2017-11-19 18:00","2017-11-06 08:00","2017-11-19 18:00","연속",null,null,"신뢰도개선 - 과도불안정 방지",201709150104,"-"]
[237,"경남","직할","신마산신김해#1 T/L","신김해S/S 345kV #72BAY B/F PNL 교체","신김해S/S 345kV #72BAY B/F PNL 교체 ※71BAY 휴전 : 7271(직할휴전), 7200, 7272(통영전력지사 휴전) 병행작업 : 신김해S/S 신마산-신김해#1T/L PT, LA 보통점검","2017-11-20 08:00","2017-11-23 18:00","2017-11-20 09:30","2017-11-20 17:30","연속",null,null,"일정변경 - 한전요청",201709060439,"-"]
[238,"경남","직할","신마산신김해#2 T/L","신김해S/S 345kV #71BAY B/F PNL 교체","신김해S/S 345kV #71BAY B/F PNL 교체 ※71BAY 휴전 : 7171(직할휴전), 7100, 7172(남부건설처 휴전) 병행작업 : 신김해S/S 신마산-신김해#2T/L PT, LA 보통점검","2017-11-07 08:00","2017-11-10 18:00","2017-11-09 09:30","2017-11-09 17:30","연속",null,null,"일정변경 - 한전요청",201709060434,"-"]
[239,"경남","직할","신김해S/S #5 M.Tr A","신김해S/S #5M.Tr 2차 CB (6544) 보통점검","신김해S/S #5M.Tr 2차 CB (6544) 보통점검 병행 : 7632DS 가스누기 보수","2017-11-02 09:30","2017-11-02 17:30","2017-11-02 09:30","2017-11-02 17:30","당일",null,null,null,201709060432,"-"]
[240,"경남","직할","창원신김해#1 T/L","345kV 창원분기 T/L 건설공사","- 신김해-창원#2T/L 연선 안전이격거리 확보","2017-11-25 13:00","2017-11-25 18:00","2017-11-25 13:00","2017-11-25 18:00","당일",null,null,"신뢰도개선 - 과도불안정 방지",201709270225,"-"]
[241,"경남","진주","의령산청양수#1 T/L","345kV 의령-산청P/P#1T/L PT초기 및 LA보통점검","345kV 의령-산청P/P#1T/L PT(A,B,C)초기 및 LA(A,B,C)보통점검","2017-11-13 10:00","2017-11-14 18:00","2017-11-13 10:00","2017-11-14 18:00","당일",null,null,null,201709060097,"-"]
[242,"경남","진주","의령산청양수#2 T/L","345kV 의령-산청양수#2T/L 보호반 대체","345kV 의령-산청양수#2T/L 보호반 대체 -산청P/P CB(7200)A,B,C상 러버히터 설치[병행] -산청P/P LA(A,B,C) 보통점검[병행]","2017-11-20 09:00","2017-11-30 18:00","취소","취소","연속",null,null,"취소 - 한전요청",201709060100,"-"]
[243,"경남","진주","의령S/S #2 M.Tr A","고령-의령#2T/L PNL대체 준공시험 관련 안전성 확보","의령S/S 345kV 고령-의령#2T/L PNL대체 준공시험 관련 안전성 확보","2017-11-22 10:00","2017-11-22 18:00","2017-11-22 10:00","2017-11-22 18:00","당일",null,null,null,201709140323,"-"]
[244,"경남","진주","하동T/P 의령-하동TP#1T/L CB (7171)","하동T/P 의령-하동TP#1T/L CB(7171)개폐장치 조작시험","하동T/P 의령-하동TP#1T/L CB(7171)개폐장치 조작시험 - Time측정, 조작시험, Trip시험 등","2017-11-08 10:00","2017-11-08 14:00","2017-11-08 10:00","2017-11-08 14:00","당일",null,null,null,201709060074,"-"]
[245,"경남","진주","하동T/P 70-71-0 SEC CB (70-71-0)","하동T/P 70-71-0 SEC CB(70-71-0)개폐장치 조작시험","하동T/P 70-71-0 SEC CB(70-71-0)개폐장치 조작시험 - Time측정, 조작시험, Trip시험 등","2017-11-08 14:00","2017-11-08 18:00","2017-11-08 14:00","2017-11-08 18:00","당일",null,null,null,201709060076,"-"]
[246,"경남","진주","하동T/P 광양-하동TP#1T/L-#3 M.Tr 1차 CB (7300)","하동T/P 광양-하동TP#1T/L-#3 M.Tr (7300) 조작시험","하동T/P 광양-하동TP#1T/L-#3 M.Tr (7300) 조작시험 - Time측정, 조작시험, Trip시험 등","2017-11-09 10:00","2017-11-09 14:00","2017-11-09 10:00","2017-11-09 14:00","당일",null,null,null,201709060079,"-"]
[247,"경남","진주","하동T/P #3 M.Tr 1차 CB (7372)","하동T/P #3 M.Tr 1차 CB (7372) 개폐장치 조작시험","하동T/P #3 M.Tr 1차 CB (7372) 개폐장치 조작시험 - Time측정, 조작시험, Trip시험 등","2017-11-09 14:00","2017-11-09 18:00","2017-11-09 14:00","2017-11-09 18:00","당일",null,null,null,201709060081,"-"]
[248,"경남","진주","하동T/P TIE-#7 M.Tr 1차 CB (7700)","하동T/P TIE-#7 M.Tr 1차 CB (7700) 개폐장치 조작시험","하동T/P TIE-#7 M.Tr 1차 CB (7700) 개폐장치 조작시험 - Time측정, 조작시험, Trip시험 등","2017-11-10 10:00","2017-11-10 14:00","2017-11-10 10:00","2017-11-10 14:00","당일",null,null,null,201709060083,"-"]
[249,"경남","진주","하동T/P 75-76-0 SEC CB (75-76-0)","하동T/P 75-76-0 SEC CB (75-76-0) 개폐장치 조작시험","하동T/P 75-76-0 SEC CB (75-76-0) 개폐장치 조작시험 - Time측정, 조작시험, Trip시험 등","2017-11-10 14:00","2017-11-10 18:00","2017-11-10 14:00","2017-11-10 18:00","당일",null,null,null,201709060087,"-"]
[250,"경남","통영","삼천포T/P #3 M.Tr 1차 CB (7371)","삼천포T/P 345kV #3M.Tr 1차 장기미동작 CB(7371)점검","삼천포T/P 345kV #3M.Tr 1차 장기미동작 CB(7371)점검","2017-11-01 09:30","2017-11-01 14:30","2017-11-01 09:30","2017-11-01 14:30","당일",null,null,null,201709060114,"-"]
[251,"경남","통영","신김해삼천포화력#2 T/L","345kV 신김해-삼천포화력T/L 노후스페이서댐퍼 교체","345kV 신김해-삼천포화력T/L S/T~No.102 노후스페이서댐퍼 교체공사 및 전선교체","2017-11-20 07:30","2017-11-28 18:00","2017-11-20 07:30","2017-11-28 18:00","연속",null,null,"신뢰도개선 - 과도불안정 방지",201709070284,"-"]
[252,"경남","통영","삼천포T/P 신고성-삼천포화력#1T/L CB (7A71)","삼천포T/P 345kV 신고성-삼천포화력#1T/L CB(7A71)점검","삼천포T/P 345kV 신고성-삼천포화력#1T/L 장기미동작 CB(7A71)점검","2017-11-17 09:30","2017-11-17 14:30","2017-11-17 09:30","2017-11-17 14:30","당일",null,null,"신뢰도개선 - 전압불안정 방지",201709070298,"-"]
[253,"경남","통영","삼천포T/P 신마산#1T/L-#3 M.Tr 1차 CB (7300)","삼천포T/P345kV신마산#1T/L-#3 M.Tr1차 CB(7300)점검","삼천포T/P 345kV 신마산#1T/L-#3 M.Tr 1차 장기미동작 CB(7300) 점검","2017-11-01 14:30","2017-11-01 18:30","2017-11-01 14:30","2017-11-01 18:30","당일",null,null,null,201709060117,"-"]
[254,"경남","통영","삼천포T/P 신고성#1T/L-TIE CB (7A00)","삼천포T/P 345kV 신고성#1T/L-TIE CB(7A00)점검","삼천포T/P 345kV 신고성#1T/L-TIE 장기미동작 CB(7A00)점검","2017-11-17 14:30","2017-11-17 18:30","2017-11-17 14:30","2017-11-17 18:30","당일",null,null,"신뢰도개선 - 전압불안정 방지",201709070301,"-"]
[255,"경남","통영","신고성S/S #2 M.Tr A","신고성S/S 345kV #2M.Tr 1차 장기미동작 CB(7D71)점검","신고성S/S 345kV #2M.Tr 1차 장기미동작 CB(7D71)점검 신고성S/S 345kV 신고성#2T/L-#2M.Tr 1차 장기미동작 CB(7D00)점검","2017-11-02 09:30","2017-11-02 18:30","2017-11-02 09:30","2017-11-02 18:30","당일",null,null,"신뢰도개선 - 전압불안정 방지",201709060123,"-"]
[256,"경남","함안","북경남S/S #7 Sh.R GIS (7B71)","북경남S/S #7Sh.R 1차 GIS(7B71) 장기미동작 차단기 점검","북경남S/S #7Sh.R 1차 GIS(7B71) 장기미동작 차단기 점검","2017-11-15 13:30","2017-11-15 17:30","2017-11-15 13:30","2017-11-15 17:30","당일",null,null,null,201709070374,"-"]
[257,"경남","함안","북경남S/S #5 Sh.R GIS (7771)","북경남S/S #5Sh.R 1차 GIS(7771) 장기미동작 차단기 점검","북경남S/S #5Sh.R 1차 GIS(7771) 장기미동작 차단기 점검","2017-11-15 09:30","2017-11-15 13:30","2017-11-15 09:30","2017-11-15 13:30","당일",null,null,null,201709070373,"-"]
[258,"경남","함안","신마산S/S #1 M.Tr A","신마산S/S #1M.Tr 2차 GCB(6144) GCB 특별점검","신마산S/S #1M.Tr 2차 GCB(6144) GCB 특별점검 96D 경보회로 구성위치 현장확인","2017-11-01 09:30","2017-11-01 17:30","2017-11-01 09:30","2017-11-01 17:30","당일",null,null,null,201709070217,"-"]
[259,"경남","함안","신마산S/S #2 M.Tr A","신마산S/S #2M.Tr 2차 GCB(6244) 특별점검","신마산S/S #2M.Tr 2차 GCB(6244) 특별점검 3차 PT 보통점검, 1,2차 부싱 절연유 채유","2017-11-02 09:30","2017-11-02 17:30","2017-11-02 09:30","2017-11-02 17:30","당일",null,null,null,201709070220,"-"]
[260,"경남","함안","신마산S/S #4 M.Tr A","신마산S/S #4M.Tr 보통점검","신마산S/S #4M.Tr 보통점검 1,2차 부싱절연유 채유, 2차 LA 보통점검 #4M.Tr 2차 GCB(6444) 특별점검","2017-11-04 09:30","2017-11-05 17:30","2017-11-04 09:30","2017-11-05 17:30","연속",null,null,null,201709070222,"-"]

{"sheet":"154송부","index":2,"n_rows":467,"n_cols":16,"rows_kept":467,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 11월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","노원열병합 T/L","17년 성동P/O 변전협력회사 총액공사 (보통점검)","170kV GIS 보통점검 (상계S/S 노원열병합T/L)","2017-11-07 10:00","2017-11-07 18:00","2017-11-07T10:00:00","2017-11-07T18:00:00","당일",null,null,null,201709120241,"-"]
[2,"서울","직할","불광서대문#2 T/L","17년 직할 변전협력 총액공사","GIS 및 LIne PT 보통점검","2017-11-01 10:00","2017-11-01 18:00","2017-11-01T10:00:00","2017-11-01T18:00:00","당일",null,null,null,201709110291,"-"]
[3,"서울","직할","운니S/S 154kV #1 BUS","17년 직할 변전협력 총액공사","154kV BUS PT 보통점검","2017-11-29 10:00","2017-11-29 14:00","2017-11-29T10:00:00","2017-11-29T14:00:00","당일",null,null,null,201709190014,"-"]
[4,"서울","직할","운니S/S 154kV #2 BUS","17년 직할 변전협력 총액공사","154kV BUS PT 보통점검","2017-11-29 14:00","2017-11-29 18:00","2017-11-29T14:00:00","2017-11-29T18:00:00","당일",null,null,null,201709190015,"-"]
[5,"남서울","강남","신사S/S 154kV #1 BUS TIE CB","신사S/S GIS 조작시험 및 개폐타임측정 - 변전협력","170kV GIS 조작시험 및 개폐타임측정","2017-11-02 10:00","2017-11-02 18:00","2017-11-02T10:00:00","2017-11-02T18:00:00","당일",null,null,null,201709130277,"-"]
[6,"남서울","강남","신양재역삼#1 T/L","일진전기제 154kV 구형 조립식접속함(PMJ) 교체공사","154kV 신양재-역삼#1T/L 구형 조립식접속함(PMJ) 6상 2개소 시공사 : 일진전기 공사기간 : 30일","2017-11-20 09:00","2017-11-29 18:00","취소","취소","연속",null,null,null,201709200205,"-"]
[7,"남서울","강남","신양재역삼#3 T/L","일진전기제 154kV 구형 조립식접속함(PMJ) 교체공사","154kV 신양재-역삼#1T/L 구형 조립식접속함(PMJ) 6상 2개소 시공사 : 일진전기 공사기간 : 30일","2017-11-10 09:00","2017-11-19 18:00","2017-11-10T09:00:00","2017-11-19T18:00:00","연속",null,null,null,201709210117,"-"]
[8,"남서울","강남","신양재역삼#2 T/L","일진전기제 154kV 구형 조립식접속함(PMJ) 교체공사","154kV 신양재-역삼#2T/L 구형 조립식접속함(PMJ) 6상 2개소 시공사 : 일진전기 공사기간 : 30일","2017-11-29 09:00","2017-12-08 18:00","취소","취소","연속",null,null,null,201709200206,"-"]
[9,"남서울","강남","신양재S/S 154kV #1 BUS TIE CB","170kV GIS 조작시험 및 개폐타임측정 - 변전협력","170kV GIS 조작시험 및 개폐타임측정","2017-11-07 10:00","2017-11-07 14:00","2017-11-07T10:00:00","2017-11-07T14:00:00","당일",null,null,null,201709130125,"-"]
[10,"남서울","강남","신양재S/S 65-66-0 SEC CB","170kV GIS 조작시험 및 개폐타임측정 - 변전협력","170kV GIS 조작시험 및 개폐타임측정","2017-11-08 14:00","2017-11-08 18:00","2017-11-08T14:00:00","2017-11-08T18:00:00","당일",null,null,null,201709130129,"-"]
[11,"남서울","강남","신양재S/S 60-61-0 SEC CB","170kV GIS 조작시험 및 개폐타임측정 - 변전협력","170kV GIS 조작시험 및 개폐타임측정","2017-11-08 10:00","2017-11-08 14:00","2017-11-08T10:00:00","2017-11-08T14:00:00","당일",null,null,null,201709130128,"-"]
[12,"남서울","강남","신양재S/S 154kV #2 BUS TIE CB","170kV GIS 조작시험 및 개폐타임측정 - 변전협력","170kV GIS 조작시험 및 개폐타임측정","2017-11-07 14:00","2017-11-07 18:00","2017-11-07T14:00:00","2017-11-07T18:00:00","당일",null,null,null,201709130126,"-"]
[13,"남서울","강남","역삼S/S 154kV #1 BUS TIE CB","170kV GIS 조작시험 및 개폐타임측정 - 변전협력","170kV GIS 조작시험 및 개폐타임측정","2017-11-14 10:00","2017-11-14 18:00","2017-11-14T10:00:00","2017-11-14T18:00:00","당일",null,null,null,201709130142,"-"]
[14,"남서울","강남","반포S/S 154kV #1 BUS TIE CB","반포S/S 170kV GIS 조작시험 및 개폐타임측정 - 변전협력","6100 BUS TIE 조작시험 및 개폐타임측정","2017-11-30 10:00","2017-11-30 14:00","2017-11-30T10:00:00","2017-11-30T14:00:00","당일",null,null,null,201709270092,"-"]
[15,"남서울","동서울","강동풍납#2 T/L","170kV GIS 교체공사","170kV GIS 교체공사","2017-11-13 09:00","2017-11-28 18:00","취소","취소","연속",null,null,null,201709140108,"-"]
[16,"남서울","동서울","풍납석촌#2 T/L","차단기 조작시험","차단기 조작시험","2017-11-28 13:00","2017-11-28 15:00","취소","취소","당일",null,null,null,201709210107,"-"]
[17,"남서울","동서울","풍납석촌#1 T/L","차단기 조작시험","차단기 조작시험","2017-11-28 10:00","2017-11-28 12:00","취소","취소","당일",null,null,null,201709140202,"-"]
[18,"남서울","동서울","잠실강남#1 T/L","차단기 조작시험","차단기 조작시험","2017-11-23 10:00","2017-11-23 11:00","2017-11-23T10:00:00","2017-11-23T11:00:00","당일",null,null,null,201709140185,"-"]
[19,"남서울","동서울","송파잠실#1 T/L","차단기 조작시험","차단기 조작시험","2017-11-23 13:00","2017-11-23 14:00","2017-11-23T13:00:00","2017-11-23T14:00:00","당일",null,null,null,201709140187,"-"]
[20,"남서울","동서울","잠실S/S 154kV #1 BUS TIE CB","차단기 조작시험","차단기 조작시험","2017-11-23 13:00","2017-11-23 15:00","2017-11-23T13:00:00","2017-11-23T15:00:00","당일",null,null,null,201709140188,"-"]
[21,"남서울","동서울","잠실강남#2 T/L","차단기 조작시험","차단기 조작시험","2017-11-23 11:00","2017-11-23 12:00","2017-11-23T11:00:00","2017-11-23T12:00:00","당일",null,null,null,201709140186,"-"]
[22,"남서울","동서울","강동천호#1 T/L","차단기 조작시험","차단기 조작시험","2017-11-27 10:00","2017-11-27 12:00","2017-11-24T10:00:00","2017-11-24T12:00:00","당일",null,null,null,201709140197,"-"]
[23,"남서울","동서울","강동천호#2 T/L","차단기 조작시험","차단기 조작시험","2017-11-27 13:00","2017-11-27 15:00","2017-11-24T13:00:00","2017-11-24T15:00:00","당일",null,null,null,201709140198,"-"]
[24,"남서울","영등포","가양S/S 154kV #2 BUS","가양S/S 170kV 안천T/L GIS 대체공사","가양S/S 170kV 안천T/L GIS 대체공사 (고객선로)","2017-11-17 10:00","2017-11-19 10:00","2017-11-17T10:00:00","2017-11-21T10:00:00","연속",null,null,null,201709200009,"-"]
[25,"남서울","영등포","가양S/S 154kV #1 BUS","가양S/S 170kV 안천T/L GIS 대체공사","가양S/S 170kV 안천T/L GIS 대체공사 (고객선로)","2017-11-19 10:00","2017-11-21 10:00","2017-11-21T10:00:00","2017-11-26T10:00:00","연속",null,null,null,201709200010,"-"]
[26,"남서울","영등포","가양S/S 154kV #2 BUS","가양S/S 170kV 안천T/L GIS 대체공사","가양S/S 170kV 안천T/L GIS 대체공사 (고객선로)","2017-11-21 10:00","2017-11-23 18:00","2017-11-27T10:00:00","2017-12-01T18:00:00","연속",null,null,null,201709200011,"-"]
[27,"남서울","영등포","독산대방#1 T/L","독산대방#1 T/L 보호배전반 교체공사","독산대방#1 T/L 보호배전반 교체공사","2017-11-06 09:00","2017-11-08 14:00","2017-11-06T09:00:00","2017-11-08T14:00:00","연속",null,null,null,201709140321,"-"]
[28,"남서울","영등포","독산대방#2 T/L","독산대방#2 T/L 보호배전반 교체공사","독산대방#2 T/L 보호배전반 교체공사","2017-11-08 14:00","2017-11-10 18:00","2017-11-08T14:00:00","2017-11-10T18:00:00","연속",null,null,null,201709140322,"-"]
[29,"남서울","영등포","신정S/S 154kV #1 BUS","170kV PT GIS 보통점검(#1BUS)","170kV PT GIS 보통점검(#1BUS)","2017-11-08 10:00","2017-11-08 11:00","2017-11-15T10:00:00","2017-11-15T11:00:00","당일",null,null,null,201709270101,"-"]
[30,"남서울","영등포","신정S/S 154kV #2 BUS","170kV PT GIS 보통점검(#2BUS)","170kV PT GIS 보통점검(#2BUS)","2017-11-08 11:00","2017-11-08 12:00","2017-11-15T11:00:00","2017-11-15T12:00:00","당일",null,null,null,201709270102,"-"]
[31,"남서울","영등포","신정목동#1T/L","신정S/S 154kV 신정목동#1 T/L CB 조작시험","신정S/S 154kV 신정목동#1 T/L CB 조작시험 목동S/S 154kV 신정목동#1 T/L CB 조작시험","2017-11-09 10:00","2017-11-09 18:00","2017-11-09T10:00:00","2017-11-09T18:00:00","당일",null,null,null,201709270103,"-"]
[32,"남서울","영등포","신정목동#2T/L","신정S/S 154kV 신정목동#2 T/L CB 조작시험","신정S/S 154kV 신정목동#2T/L CB 조작시험","2017-11-10 10:00","2017-11-10 18:00","2017-11-10T10:00:00","2017-11-10T18:00:00","당일",null,null,null,201709270104,"-"]
[33,"남서울","영등포","등촌S/S 154kV #2 BUS","170kV GIS 정밀점검(#1B/T 및 상암-등촌#2T/L)","170kV GIS 정밀점검","2017-12-01 09:00","2017-12-01 18:00","취소","취소","연속",null,null,null,201705250016,"-"]
[34,"남서울","영등포","등촌S/S 154kV #1 BUS","170kV GIS 정밀점검(#1B/T 및 상암-등촌#2T/L)","170kV GIS 정밀점검","2017-11-30 09:00","2017-11-30 18:00","취소","취소","연속",null,null,null,201705250015,"-"]
[35,"남서울","영등포","상암등촌#2 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2017-11-30 09:00","2017-12-01 18:00","취소","취소","연속",null,null,null,201705250013,"-"]
[36,"남서울","영등포","등촌S/S 154kV #2 BUS","170kV GIS 정밀점검(#3M.Tr 1차 및 상암-등촌#1T/L)","170kV GIS 정밀점검","2017-11-28 14:00","2017-11-29 18:00","취소","취소","연속",null,null,null,201705250012,"-"]
[37,"남서울","영등포","등촌S/S 154kV #1 BUS","170kV GIS 정밀점검(#3M.Tr 1차 및 상암-등촌#1T/L)","170kV GIS 정밀점검","2017-11-27 09:00","2017-11-28 14:00","취소","취소","연속",null,null,null,201705250009,"-"]
[38,"남서울","영등포","상암등촌#1 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2017-11-27 09:00","2017-11-28 18:00","취소","취소","연속",null,null,null,201705250010,"-"]
[39,"남서울","영등포","등촌S/S 154kV #1 BUS","170kV GIS 정밀점검(#2M.Tr 1차 및 가양-등촌#2T/L)","170kV GIS 정밀점검","2017-11-25 09:00","2017-11-26 14:00","취소","취소","연속",null,null,null,201705250007,"-"]
[40,"남서울","영등포","등촌S/S 154kV #2 BUS","170kV GIS 정밀점검(#1M.Tr 1차 및 가양-등촌#1T/L)","170kV GIS 정밀점검","2017-11-24 14:00","2017-11-24 18:00","취소","취소","연속",null,null,null,201705250004,"-"]
[41,"남서울","영등포","등촌S/S 154kV #1 BUS","170kV GIS 정밀점검(#1M.Tr 1차 및 가양-등촌#1T/L)","170kV GIS 정밀점검","2017-11-24 09:00","2017-11-24 14:00","취소","취소","연속",null,null,null,201705250003,"-"]
[42,"남서울","영등포","가양등촌#1 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2017-11-24 09:00","2017-11-24 18:00","취소","취소","연속",null,null,null,201705250001,"-"]
[43,"남서울","영등포","가양등촌#2 T/L","2017-2018 영서전력지사 지중송전설비 위탁정비공사","- SVL 보강공사","2017-11-02 09:00","2017-11-02 18:00","2017-11-02T09:00:00","2017-11-02T18:00:00","연속",null,null,null,201709190073,"-"]
[44,"남서울","영등포","가양등촌#1 T/L","2017-2018 영서전력지사 지중송전설비 위탁정비공사","- SVL 보강공사 및 EBG 과열관련 보수공사","2017-11-01 09:00","2017-11-01 18:00","2017-11-01T09:00:00","2017-11-01T18:00:00","연속",null,null,null,201709190072,"-"]
[45,"남서울","영등포","가양등촌#2 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2017-11-25 09:00","2017-11-26 18:00","취소","취소","연속",null,null,null,201705250005,"-"]
[46,"남서울","영등포","등촌S/S 154kV #2 BUS","170kV GIS 정밀점검(#2M.Tr 1차 및 가양-등촌#2T/L)","170kV GIS 정밀점검","2017-11-26 14:00","2017-11-26 18:00","취소","취소","연속",null,null,null,201705250008,"-"]
[47,"남서울","영등포","마곡S/S 154kV #2 BUS","마곡S/S #3M.Tr 증설공사","154kV GIS 1CCT 설치","2017-11-09 10:00","2017-11-15 17:00","2017-11-09T10:00:00","2017-11-15T17:00:00","연속",null,null,"신뢰도개선",201709110189,"-"]
[48,"남서울","영등포","마곡S/S 154kV #1 BUS","마곡S/S #3M.Tr 증설공사","154kV GIS 1CCT 설치","2017-11-03 10:00","2017-11-08 17:00","2017-11-03T10:00:00","2017-11-08T17:00:00","연속",null,null,"신뢰도개선",201709110187,"-"]
[49,"남서울","영등포","봉천신길#2 T/L","'17-18 직할 지중송전 위탁정비공사","OF케이블 절연유 채유 채취장소 : 사당,봉천EBG, M/H#15-1, 17 등 8개소 24상","2017-11-10 18:00","2017-11-11 06:00","2017-11-10T18:00:00","2017-11-11T06:00:00","당일",null,null,null,201709200199,"-"]
[50,"남서울","영등포","봉천신길#1 T/L","'17-18 직할 지중송전 위탁정비공사","OF케이블 절연유 채유 채취장소 : 사당,봉천EBG, M/H#15-1, 17 등 8개소 24상","2017-11-09 18:00","2017-11-10 06:00","2017-11-09T18:00:00","2017-11-10T06:00:00","당일",null,null,null,201709200198,"-"]
[51,"남서울","영등포","영서시흥#1 T/L","17년 가공송전협력회사공사(송전선로용 피뢰기 설치공사)","송전선로용 피뢰기 설치공사","2017-11-02 09:00","2017-11-03 18:00","2017-11-02T09:00:00","2017-11-03T18:00:00","연속",null,null,null,201709130116,"-"]
[52,"남서울","영등포","중동화곡#1 T/L","2017-2018년 영서전력지사 지중송전설비 위탁정비공사","노후 폴리머피뢰기 교체 및 PD집합반 설치","2017-11-06 09:00","2017-11-07 18:00","2017-11-06T09:00:00","2017-11-07T18:00:00","연속",null,null,null,201709200005,"-"]
[53,"남서울","영등포","중동화곡#2 T/L","2017-2018년 영서전력지사 지중송전설비 위탁정비공사","노후 폴리머피뢰기 교체 및 PD집합반 설치","2017-11-08 09:00","2017-11-09 18:00","2017-11-08T09:00:00","2017-11-09T18:00:00","연속",null,null,null,201709200008,"-"]
[54,"남서울","직할","사당봉천#1 T/L","'17-18 직할 지중송전 위탁정비공사","OF케이블 절연유 채유 채취장소 : 사당EBG, M/H#8","2017-11-09 10:00","2017-11-09 16:00","2017-11-09T10:00:00","2017-11-09T16:00:00","당일",null,null,null,201709200197,"-"]
[55,"남서울","직할","신길S/S 154kV #1 BUS","154kV 신길S/S CPD PNL 교체 및 차단기 조작시험","154kV 신길S/S CPD PNL 교체 및 차단기 조작시험 및 개폐타임측정","2017-11-13 09:00","2017-11-13 12:00","취소","취소","당일",null,null,null,201709210069,"-"]
[56,"남서울","직할","신길S/S 154kV #1 BUS TIE CB","154kV 신길S/S CPD PNL 교체 및 차단기 조작시험","154kV 신길S/S CPD PNL 교체 및 차단기 조작시험 및 개폐타임측정","2017-11-13 09:00","2017-11-13 18:00","취소","취소","당일",null,null,null,201709210073,"-"]
[57,"남서울","직할","신길S/S 154kV #2 BUS","154kV 신길S/S CPD PNL 교체 및 차단기 조작시험","154kV 신길S/S CPD PNL 교체 및 차단기 조작시험 및 개폐타임측정","2017-11-13 12:00","2017-11-13 15:00","취소","취소","당일",null,null,null,201709210071,"-"]
[58,"남서울","직할","신길S/S 154kV #1 BUS","154kV 신길S/S CPD PNL 교체 및 차단기 조작시험","154kV 신길S/S CPD PNL 교체 및 차단기 조작시험 및 개폐타임측정","2017-11-13 15:00","2017-11-13 18:00","취소","취소","당일",null,null,null,201709210070,"-"]
[59,"인천","김포","양촌양곡#1 T/L","피뢰기 설치공사","154kV 양촌-양곡#1T/L 피뢰기 설치공사","2017-11-27 08:00","2017-11-27 18:00","2017-11-27T08:00:00","2017-11-27T18:00:00","당일",null,null,null,201709150071,"-"]
[60,"인천","시흥","동춘송도#1 T/L","154kV 동송도분기 지중T/L 건설공사","공사목적 : 송도지역 전력계통보강 공사구간 : 154kV 동춘-송도T/L M/H#8~M/H#9(2ㅠ분기) 선종 및 규격 : 154KV XLPE 2000SQ 회선수 및 길이 : 4회선, 2.5KM","2017-11-07 09:30","2017-12-05 18:00","2017-11-07T09:30:00","2017-12-05T18:00:00","연속",null,null,null,201709050004,"-"]
[61,"인천","시흥","북시화서시화#1 T/L","북시화S/S 170kV GIS 대체공사 3차","신시흥-북시화#2TL, #2M.Tr 1차 대체","2017-11-02 08:00","2017-11-03 08:00","2017-11-07T08:00:00","2017-11-08T08:00:00","연속",null,null,null,201708030081,"-"]
[62,"인천","시흥","신시흥북시화#1 T/L","북시화S/S 170kV GIS 대체공사 3차","신시흥북시화#2TL 붓싱교체 작업시 감전/유도에 의한 안전사고예방","2017-11-04 08:00","2017-11-04 18:00","취소","취소","당일",null,null,null,201709200106,"-"]
[63,"인천","시흥","북시화S/S 154kV #2 BUS","북시화S/S 170kV GIS 대체공사 4차","북시화S/S #3M.Tr 1차 GIS 대체","2017-11-06 08:00","2017-11-08 08:00","2017-11-09T08:00:00","2017-11-10T08:00:00","연속",null,null,null,201709110209,"-"]
[64,"인천","시흥","북시화S/S 154kV #1 BUS","북시화S/S 170kV GIS 대체공사 4차","북시화S/S #3M.Tr 1차 GIS 대체","2017-11-08 08:00","2017-11-12 08:00","2017-11-18T10:00:00","2017-11-18T18:00:00","연속",null,null,null,201709110210,"-"]
[65,"인천","시흥","북시화서시화#1 T/L","북시화S/S 170kV GIS 대체공사 4차","북시화S/S #3M.Tr 1차 GIS 대체 관련 모선 무부하가압용","2017-11-11 08:00","2017-11-12 08:00","2017-11-12T15:00:00","2017-11-13T15:00:00","연속",null,null,null,201709110251,"-"]
[66,"인천","시흥","북시화S/S 154kV #2 BUS","북시화S/S 170kV GIS 대체공사 4차","북시화S/S #3M.Tr 1차 GIS 대체","2017-11-12 08:00","2017-11-16 08:00","2017-11-13T15:00:00","2017-11-18T10:00:00","연속",null,null,null,201709110233,"-"]
[67,"인천","시흥","북시화서시화#1 T/L","북시화S/S 170kV GIS 대체공사 4차","북시화S/S #3M.Tr 1차 GIS 대체 관련 모선 무부하가압용","2017-11-15 08:00","2017-11-16 08:00","2017-11-17T08:00:00","2017-11-18T08:00:00","연속",null,null,null,201709110269,"-"]
[68,"인천","시흥","북시화S/S 154kV #1 BUS","북시화S/S 170kV GIS 대체공사 4차","북시화S/S #3M.Tr 1차 GIS 대체","2017-11-16 08:00","2017-11-16 17:00","2017-11-10T08:00:00","2017-11-13T15:00:00","연속",null,null,null,201709110243,"-"]
[69,"인천","시흥","신시흥북시화#1 T/L","북시화S/S 170kV GIS 대체공사 3차","신시흥북시화#2TL 붓싱교체 작업시 감전/유도에 의한 안전사고예방","2017-11-01 08:00","2017-11-01 18:00","2017-11-01T08:00:00","2017-11-01T18:00:00","당일",null,null,null,201709140310,"-"]
[70,"인천","시흥","북시화S/S 154kV #1 BUS","북시화S/S 170kV GIS 대체공사 3차","신시흥-북시화#2TL, #2M.Tr 1차 대체","2017-11-03 08:00","2017-11-04 08:00","2017-11-08T10:00:00","2017-11-08T18:00:00","연속",null,null,null,201708030085,"-"]
[71,"인천","시흥","온수소래 T/L","154kV 서안양소래T/L 피뢰기 설치 및 항공장애등 설치공사 등","154kV 서안양소래T/L(병가선로) - 피뢰기설치, 스페이서 간격조정, SB댐퍼 설치, 항공장애표시구 설치공사","2017-11-28 08:00","2017-11-29 18:00","취소","취소","연속",null,null,null,201709140273,"-"]
[72,"인천","시흥","서서울#2소래 T/L","154kV 서서울#2-소래T/L 안전이격확보공사 및 스페이서 간격조정 등","154kV 서서울#2-소래T/L - 안전이격확보공사, 스페이서 간격조정, SB댐퍼 설치, 항공장애표시구 설치공사","2017-11-20 08:00","2017-11-23 18:00","취소","취소","연속",null,null,null,201709210072,"-"]
[73,"인천","시흥","서안양소래 T/L","154kV 서안양소래T/L 안전이격확보공사 및 피뢰기 설치 등","154kV 서안양소래T/L -안전이격확보공사, 피뢰기설치, 스페이서 간격조정, SB댐퍼 설치, 항공장애표시구 설치공사","2017-11-28 08:00","2017-12-01 18:00","취소","취소","연속",null,null,null,201709140272,"-"]
[74,"인천","시흥","신시흥북시화#2 T/L","154kV 신시흥북시화#2T/L 스페이서 간격조정 및 SB댐퍼 설치공사","154kV 신시흥북시화#2T/L 스페이서 간격조정 및 SB댐퍼 설치공사","2017-11-04 08:00","2017-11-04 18:00","2017-11-04T08:00:00","2017-11-04T18:00:00","당일",null,null,null,201709140106,"-"]
[75,"인천","시흥","신시흥시화#2 T/L","154kV 신시흥시화#2T/L 스페이서 간격조정 및 SB댐퍼 설치공사","154kV 신시흥시화#2T/L 스페이서 간격조정 및 SB댐퍼 설치공사","2017-11-04 08:00","2017-11-05 18:00","2017-11-04T08:00:00","2017-11-05T18:00:00","연속",null,null,null,201709140105,"-"]
[76,"인천","시흥","신시흥#2S/S 154kV #66 Sh.C","신시흥#2S/S 154kV #65 Sh.C CELL 및 보호반 대체공사","신시흥#2S/S 154kV #65 Sh.C CELL 및 보호반 대체공사 #65, 66Sh.C 동일 보호반 사용중","2017-11-27 09:30","2017-12-01 18:00","취소","취소","연속",null,null,null,201709140211,"-"]
[77,"인천","시흥","신시흥#2S/S 154kV #65 Sh.C","신시흥#2S/S 154kV #65 Sh.C CELL 및 보호반 대체공사","신시흥#2S/S 154kV #65 Sh.C CELL 및 보호반 대체공사","2017-11-27 09:30","2017-12-01 18:00","취소","취소","연속",null,null,null,201709140212,"-"]
[78,"인천","시흥","학익연수#2 T/L","연수S/S 154kV 학익연수#2 T/L GIS 초기점검","연수S/S 154kV 학익연수#2 T/L GIS 초기점검","2017-11-19 10:00","2017-11-19 18:00","2017-11-19T10:00:00","2017-11-19T18:00:00","당일",null,null,null,201709140127,"-"]
[79,"인천","시흥","학익연수#1 T/L","연수S/S 154kV 학익연수#1 T/L GIS 초기점검","연수S/S 154kV 학익연수#1 T/L GIS 초기점검","2017-11-18 10:00","2017-11-18 18:00","2017-11-18T10:00:00","2017-11-18T18:00:00","당일",null,null,null,201709140122,"-"]
[80,"인천","인천","남동관교#2 T/L","관교S/S 남동-관교#2T/L 보호반대체공사","관교S/S 남동-관교#2T/L 보호반대체공사","2017-11-06 09:00","2017-11-10 18:00","2017-11-06T09:00:00","2017-11-10T18:00:00","연속",null,null,null,201709070149,"-"]
[81,"인천","인천","남인천학익#1 T/L","OF 케이블 절연유 보충","OF 케이블 절연유 보충","2017-11-25 09:00","2017-11-25 18:00","2017-11-25T09:00:00","2017-11-25T18:00:00","당일",null,null,null,201709060058,"-"]
[82,"인천","인천","남인천학익#2 T/L","OF 케이블 절연유 보충","OF 케이블 절연유 보충","2017-11-26 09:00","2017-11-26 18:00","2017-11-26T09:00:00","2017-11-26T18:00:00","당일",null,null,null,201709060060,"-"]
[83,"인천","인천","송현포스코CC#1 T/L","OF 케이블 절연유 보충","OF 케이블 절연유 보충","2017-11-23 09:00","2017-11-23 18:00","2017-11-23T09:00:00","2017-11-23T18:00:00","당일",null,null,null,201709060064,"-"]
[84,"인천","인천","신가좌S/S 154kV #67 BUS","신가좌S/S #4M.Tr 2차 GIS 대체공사(#67BUS)","신가좌S/S #4M.Tr 2차 GIS 대체공사 - GIS 철거 및 조립 - #4M.Tr GPT 점검(병행) - PL-LA3, LD3(#4M.Tr측)대체공사 - 7672CB GIS 초기점검 병행","2017-11-20 09:00","2017-11-21 09:00","2017-11-20T09:00:00","2017-11-21T09:00:00","연속",null,null,null,201709160016,"-"]
[85,"인천","인천","신가좌S/S 154kV #67 BUS","신가좌S/S #4M.Tr 2차 GIS 대체공사(#67BUS)","신가좌S/S #4M.Tr 2차 GIS 대체공사 - GIS 철거 및 조립 - #4M.Tr GPT 점검(병행) - PL-LA3, LD3(#4M.Tr측)대체공사 - 7672CB GIS 초기점검 병행","2017-11-29 09:00","2017-12-04 18:00","2017-11-29T09:00:00","2017-12-04T18:00:00","연속",null,null,null,201709160018,"-"]
[86,"인천","인천","신가좌S/S 154kV #62 BUS","신가좌S/S #4M.Tr 2차 GIS 대체공사(#62BUS)","신가좌S/S #4M.Tr 2차 GIS 대체공사 - GIS 철거 및 조립 - #4M.Tr GPT 점검(병행) - PL-LA3, LD3(#4M.Tr측)대체공사 - 7672CB GIS 초기점검 병행","2017-11-21 09:00","2017-11-28 18:00","2017-11-21T09:00:00","2017-11-28T18:00:00","연속",null,null,null,201709160017,"-"]
[87,"인천","인천","신현S/S 154kV #1 BUS","신현S/S 170kV GIS 대체공사","- #3M.Tr 1차, 신가좌신현#1, 신현포스코#1 대체 - 기타 부대공사 1식","2017-11-17 08:00","2017-11-17 18:00","2017-11-19T08:00:00","2017-11-19T18:00:00","연속",null,null,null,201708160213,"-"]
[88,"인천","인천","신현송현#1 T/L","신현S/S 170kV GIS 대체공사(무부하가압)","- #3M.Tr 1차, 신가좌신현#1, 신현포스코#1 대체 - 무부하가압","2017-11-15 18:00","2017-11-16 18:00","2017-11-17T18:00:00","2017-11-18T18:00:00","연속",null,null,null,201708160216,"-"]
[89,"인천","인천","신현S/S 154kV #2 BUS","신현S/S 170kV GIS 대체공사","- #3M.Tr 1차, 신가좌신현#1, 신현포스코#1 대체 - 기타 부대공사 1식","2017-11-06 08:00","2017-11-16 18:00","2017-11-08T08:00:00","2017-11-18T18:00:00","연속",null,null,null,201708160211,"-"]
[90,"인천","인천","신현송현#1 T/L","신현S/S 170kV GIS 대체공사(무부하가압)","- #3M.Tr 1차, 신가좌신현#1, 신현포스코#1 대체 - 무부하가압","2017-11-04 10:00","2017-11-05 10:00","2017-11-06T10:00:00","2017-11-07T10:00:00","연속",null,null,null,201708160040,"-"]
[91,"인천","인천","신가좌인천#3 T/L","구형 SVL 교체공사","구형 SVL 교체공사","2017-11-28 09:00","2017-11-30 18:00","2017-11-28T09:00:00","2017-11-30T18:00:00","연속",null,null,null,201709010115,"-"]
[92,"인천","인천","신가좌인천#2 T/L","OF 케이블 절연유 보충","OF 케이블 절연유 보충","2017-11-27 09:00","2017-11-27 18:00","2017-11-27T09:00:00","2017-11-27T18:00:00","당일",null,null,null,201709060062,"-"]
[93,"인천","인천","인천남인천#2 T/L","OF 케이블 절연유 보충","OF 케이블 절연유 보충","2017-11-21 09:00","2017-11-21 18:00","2017-11-21T09:00:00","2017-11-21T18:00:00","당일",null,null,null,201709060055,"-"]
[94,"인천","인천","신가좌인천#1 T/L","OF선로 절연유 보충","OF선로 절연유 보충","2017-11-24 09:00","2017-11-24 18:00","2017-11-24T09:00:00","2017-11-24T18:00:00","당일",null,null,null,201709060066,"-"]
[95,"인천","인천","인천CC포스코CC#1 T/L","인천CC 인천TP포스코CC#1T/L GIS 보통점검","인천CC 인천TP포스코CC#1T/L GIS 보통점검","2017-11-24 09:00","2017-11-24 18:00","2017-11-24T09:00:00","2017-11-24T18:00:00","연속",null,null,null,201708090259,"-"]
[96,"인천","직할","계양북인천 T/L","SB댐퍼 설치공사","154kV 계양-북인천T/L SB댐퍼 설치공사","2017-11-20 08:00","2017-11-23 18:00","2017-11-20T08:00:00","2017-11-23T18:00:00","매일",null,null,null,201709150065,"-"]
[97,"인천","직할","계양원창 T/L","SB댐퍼 설치공사","154kV 계양-원창T/L SB댐퍼 설치공사","2017-11-13 08:00","2017-11-17 18:00","2017-11-13T08:00:00","2017-11-17T18:00:00","매일",null,null,null,201709150064,"-"]
[98,"인천","직할","신부평고강#1 T/L","154kV 신부평-고강 #1T/L 절연유 교체","기중종단접속함(EBA) 절연유 교체","2017-11-04 09:00","2017-11-05 18:00","2017-11-04T09:00:00","2017-11-05T18:00:00","연속",null,null,null,201709210001,"-"]
[99,"인천","직할","임학계양#2 T/L","154kV 임학-계양#2T/L 자기애관 교체공사","기중종단접속함(EBA) 교체공사(자기애관→폴리머애관)","2017-11-20 09:00","2017-11-25 18:00","2017-11-20T09:00:00","2017-11-25T18:00:00","연속",null,null,null,201709060221,"-"]
[100,"인천","직할","임학계양#1 T/L","154kV 임학-계양#1T/L 자기애관 교체공사","기중종단접속함(EBA) 교체공사(자기애관→폴리머애관)","2017-11-13 09:00","2017-11-19 18:00","2017-11-13T09:00:00","2017-11-19T18:00:00","연속",null,null,null,201709060216,"-"]
[101,"인천","직할","중동화곡#2 T/L","중동S/S 154kV SW 증설공사","중동-화곡#2T/L GIS 인출측(가공) 기초 설치","2017-11-27 09:30","2017-11-28 17:30","취소","취소","연속",null,null,null,201709110459,"-"]
[102,"인천","직할","중동화곡#1 T/L","중동S/S 154kV SW 증설공사","중동-화곡#1T/L GIS 인출측(가공) 기초 설치","2017-11-25 09:30","2017-11-26 17:30","취소","취소","연속",null,null,null,201709110451,"-"]
[103,"경기북부","구리","가평화천HP T/L","154kV 화천T/L 정밀점검","154kV 가평-화천T/L 정밀점검","2017-11-06 08:00","2017-11-10 18:00","2017-11-13T08:00:00","2017-11-17T18:00:00","연속",null,null,null,201702140029,"-"]
[104,"경기북부","구리","가평춘천HP T/L","154kV 화천T/L 정밀점검","154kV 가평-춘천T/L 정밀점검","2017-11-13 08:00","2017-11-17 18:00","2017-11-08T08:00:00","2017-11-11T18:00:00","연속",null,null,"신뢰도개선",201702140031,"-"]
[105,"경기북부","구리","덕소별내#1 T/L","154kV 진건S/S 건설공사 등","- 154kV M.Tr 2Bank / 154kV GIS 7CCT / 22.9kV SIS 9CCT 설치 - 154kV 덕소-별내#1,2T/L 지중화 - 154kV 진건분기 지중송전선로 설치","2017-11-02 09:00","2017-11-15 18:00","2017-11-02T09:00:00","2017-11-15T18:00:00","연속",null,null,null,201708280085,"○"]
[106,"경기북부","구리","덕소별내#2 T/L","154kV 진건S/S 건설공사 등","- 154kV M.Tr 2Bank / 154kV GIS 7CCT / 22.9kV SIS 9CCT 설치 - 154kV 덕소-별내#1,2T/L 지중화 - 154kV 진건분기 지중송전선로 설치","2017-11-17 09:00","2017-11-28 18:00","2017-11-17T09:00:00","2017-11-28T18:00:00","연속",null,null,null,201708280089,"-"]
[107,"경기북부","구리","동서울서종#2 T/L","154kV 서종분기T/L 환경개선공사","○ 서종C/H 환경개선 - 철탑 철거, 조립 - 전력선 연긴선 등","2017-11-23 08:00","2017-11-29 18:00","취소","취소","연속",null,null,null,201709140302,"-"]
[108,"경기북부","구리","서종청평PP#2 T/L","154kV 서종분기T/L 환경개선공사","○ 서종C/H 환경개선 - 철탑 철거, 조립 - 전력선 연긴선 등","2017-11-23 08:00","2017-11-29 18:00","취소","취소","연속",null,null,null,201709140304,"-"]
[109,"경기북부","구리","동서울서종#1 T/L","154kV 서종분기T/L 환경개선공사","○ 서종C/H 환경개선 - 철탑 철거, 조립 - 전력선 연긴선 등","2017-11-23 08:00","2017-11-29 18:00","취소","취소","연속",null,null,null,201709140301,"-"]
[110,"경기북부","구리","서종청평PP#1 T/L","154kV 서종분기T/L 환경개선공사","○ 서종C/H 환경개선 - 철탑 철거, 조립 - 전력선 연긴선 등","2017-11-23 08:00","2017-11-29 18:00","취소","취소","연속",null,null,null,201709140303,"-"]
[111,"경기북부","구리","신포천전곡#1 T/L","16~17년 직할 가공송전정비 협력회사 총액공사(병가)","154kV 운천-전곡#2T/L 피뢰기설치공사 - 76기 228SET 피뢰기설치 - 4회선 병가선로 동시휴전(당일)","2017-11-22 08:00","2017-11-22 18:00","2017-11-22T08:00:00","2017-11-22T18:00:00","당일",null,null,null,201708100259,"○"]
[112,"경기북부","구리","운천전곡#2 T/L","16~17년 직할 가공송전정비 협력회사 총액공사","154kV 운천-전곡#2T/L 피뢰기설치공사 - 76기 228SET 피뢰기설치 - 76기 운천-전곡#2T/L 정밀점검(병행)","2017-11-15 08:00","2017-11-22 18:00","2017-11-15T08:00:00","2017-11-22T18:00:00","연속",null,null,null,201708100255,"○"]
[113,"경기북부","직할","운천전곡#1 T/L","'17년 가공송전 순시점검 위탁공사(정밀점검)","154kV 운천전곡#1T/L 정밀점검 시행(No.1~76호)","2017-11-01 08:00","2017-11-06 18:00","2017-11-01T08:00:00","2017-11-06T18:00:00","연속",null,null,null,201707100225,"○"]
[114,"경기북부","직할","신포천전곡#2 T/L","'17년 가공송전 순시점검 위탁공사(정밀점검)","154kV 운천전곡#1T/L 정밀점검 시행(No.1~76호) -154kV 신포천전곡T/L 상단병가선로","2017-11-01 08:00","2017-11-01 18:00","2017-11-01T08:00:00","2017-11-01T18:00:00","당일",null,null,null,201707100226,"○"]
[115,"경기북부","파주","월롱금촌#2 T/L","17년 파주전력지사 170kV GIS 정밀점검공사","금촌S/S 월롱-금촌#2T/L GIS 정밀점검(647)","2017-11-05 09:00","2017-11-07 18:00","취소","취소","연속",null,null,"신뢰도개선",201708280094,"-"]
[116,"경기북부","파주","월롱금촌#1 T/L","17년 파주전력지사 170kV GIS 정밀점검공사","금촌S/S 월롱-금촌#1T/L GIS 정밀점검(637)","2017-11-01 09:00","2017-11-03 18:00","취소","취소","연속",null,null,"신뢰도개선",201708280093,"-"]
[117,"경기북부","파주","지도능곡#2 T/L","17년 파주전력지사 170kV GIS 정밀점검공사","능곡S/S 지도-능곡#2T/L GIS 정밀점검(647)","2017-11-27 09:00","2017-11-29 18:00","2017-11-27T09:00:00","2017-11-29T18:00:00","연속",null,null,null,201708030008,"-"]
[118,"경기북부","파주","문산평화#1 T/L","154kV 문산-평화 등 2개T/L 지장송전선로 이설공사","문산천 문산지구 하천정비 지장송전선로 이설공사","2017-11-30 08:00","2017-12-04 18:00","2017-11-30T08:00:00","2017-12-04T18:00:00","연속",null,null,null,201709120131,"-"]
[119,"경기북부","파주","문산평화#2 T/L","154kV 문산-평화 등 2개T/L 지장송전선로 이설공사","문산천 문산지구 하천정비 지장송전선로 이설공사","2017-11-30 08:00","2017-12-04 18:00","2017-11-30T08:00:00","2017-12-04T18:00:00","연속",null,null,null,201709120132,"-"]
[120,"경기북부","파주","문산월롱#2 T/L","154kV 문산-평화 등 2개T/L 지장송전선로 이설공사","문산천 문산지구 하천정비 지장송전선로 이설공사","2017-11-26 08:00","2017-11-29 18:00","2017-11-26T08:00:00","2017-11-29T18:00:00","연속",null,null,null,201709120129,"-"]
[121,"경기북부","파주","문산월롱#1 T/L","154kV 문산-평화 등 2개T/L 지장송전선로 이설공사","문산천 문산지구 하천정비 지장송전선로 이설공사","2017-11-22 08:00","2017-11-25 18:00","2017-11-22T08:00:00","2017-11-25T18:00:00","연속",null,null,null,201709120127,"-"]
[122,"경기북부","파주","신덕은문산#1 T/L","154kV 문산-평화 등 2개T/L 지장송전선로 이설공사","문산천 문산지구 하천정비 지장송전선로 이설공사 (병가선로)","2017-11-22 08:00","2017-11-25 18:00","2017-11-22T08:00:00","2017-11-25T18:00:00","연속",null,null,null,201709120125,"-"]
[123,"경기북부","파주","신덕은문산#2 T/L","154kV 문산-평화 등 2개T/L 지장송전선로 이설공사","문산천 문산지구 하천정비 지장송전선로 이설공사(병가선로)","2017-11-26 08:00","2017-11-29 18:00","2017-11-26T08:00:00","2017-11-29T18:00:00","연속",null,null,null,201709120130,"-"]
[124,"경기북부","파주","신파주금촌#1 T/L","154kV 신파주-금촌#1T/L 피뢰기설치공사","설치대상 : No.1~5 내용 : 154kV 송전선로용 피뢰기 설치(상중하단) 15Set","2017-11-13 07:00","2017-11-15 18:00","2017-11-17T07:00:00","2017-11-19T18:00:00","연속",null,null,null,201709130195,"-"]
[125,"경기북부","파주","신파주문발#2 T/L","154kV 신파주-문발#2T/L 피뢰기설치공사","설치대상 : No.1~4 내용 : 154kV 송전선로용 피뢰기 설치(상중하단) 12Set","2017-11-15 07:00","2017-11-15 18:00","2017-11-17T07:00:00","2017-11-17T18:00:00","당일",null,null,null,201709130196,"-"]
[126,"경기북부","파주","일산지도#1 T/L","154kV 일산-지도#1T/L 피뢰기설치공사","설치대상 : 154kV 일산-지도#1T/L No.1~13 내용 : 154kV 송전선로용 피뢰기 설치(상,중,하단) 39Set","2017-11-20 07:00","2017-11-22 18:00","2017-11-20T07:00:00","2017-11-22T18:00:00","연속",null,null,null,201709130194,"-"]
[127,"경기북부","파주","고양일산#1 T/L","154kV 고양-일산#1T/L 피뢰기설치공사 안전확보","설치대상 : 154kV 일산-지도#1T/L No.1~13 휴전사유 : 154kV 일산-지도#1T/L 피뢰기설치공사 병가철탑 안전확보","2017-11-20 07:00","2017-11-22 18:00","2017-11-20T07:00:00","2017-11-22T18:00:00","연속",null,null,null,201709130193,"○"]
[128,"경기","군포","원곡반월#1 T/L","반월S/S 154kV 현대화공사","- 원곡반월#1T/L 모선이설 (옥외철구 -> GIS) - 원곡반월#1T/L 보호배전반 대체","2017-11-14 09:30","2017-11-23 18:00","2017-11-14T09:30:00","2017-11-23T18:00:00","연속",null,null,null,201709120101,"-"]
[129,"경기","군포","원곡반월#2 T/L","반월S/S 154kV 현대화공사","- 원곡반월#1T/L 모선이설 (옥외철구 -> GIS) - 원곡반월#1T/L 보호배전반 대체","2017-11-27 09:30","2017-12-06 18:00","2017-11-27T09:30:00","2017-12-06T18:00:00","연속",null,null,null,201709120102,"-"]
[130,"경기","군포","반월시화#1 T/L","154kV 신시흥시화#2T/L 스페이서 간격조정 및 SB댐퍼 설치공사","154kV 신시흥시화#2T/L 스페이서 간격조정 및 SB댐퍼 설치공사 (병가선로)","2017-11-05 08:00","2017-11-05 18:00","2017-11-05T08:00:00","2017-11-05T18:00:00","당일",null,null,null,201709140107,"-"]
[131,"경기","군포","서서울#2남수원 #2T/L","154kV 서서울-남수원T/L 지장철탑 이설공사","○ 기설철탑 1기 철거, 신설철탑 1기 설치","2017-11-25 07:00","2017-11-27 18:00","2017-11-25T07:00:00","2017-11-27T18:00:00","연속",null,null,null,201709130232,"-"]
[132,"경기","군포","서서울#2남수원 #1T/L","154kV 서서울-남수원T/L 지장철탑 이설공사","○ 기설철탑 1기 철거, 신설철탑 1기 설치","2017-11-28 07:00","2017-11-30 18:00","2017-11-28T07:00:00","2017-11-30T18:00:00","연속",null,null,null,201709130233,"-"]
[133,"경기","군포","서서울율전#2 T/L","율전#1C/H PD진단센서 및 집합반 설치공사","EBA하단 PD진단센서 설치(1상 1개소), 철탑하부 집합반 설치","2017-11-12 13:00","2017-11-12 18:00","2017-11-12T13:00:00","2017-11-12T18:00:00","당일",null,null,null,201709060108,"-"]
[134,"경기","군포","서서울율전#1 T/L","율전#1C/H PD진단센서 및 집합반 설치공사","EBA하단 PD진단센서 설치(1상 1개소), 철탑하부 집합반 설치","2017-11-12 09:00","2017-11-12 12:00","2017-11-12T09:00:00","2017-11-12T12:00:00","당일",null,null,null,201709060107,"-"]
[135,"경기","군포","서서울#2서안양 T/L ","154kV 서서울2서안양T/L 피뢰기 설치 및 스페이서 간격조정 공사 등","154kV 서서울#2-서안양T/L -피뢰기설치, 스페이서 간격조정, SB댐퍼 설치공사","2017-11-27 08:00","2017-11-27 18:00","취소","취소","당일",null,null,null,201709210074,"-"]
[136,"경기","군포","산본안양#2 T/L","154kV 안양S/S 인출변경 지중T/L 건설공사","선종/회선길이 : 154㎸ XLPE 1,200/2,000㎟, 각 2회선-0.13㎞ - 안양-평촌TL, 안양-산본TL 이설","2017-11-13 10:00","2017-12-07 18:00","2017-11-13T10:00:00","2017-12-07T18:00:00","연속",null,null,null,201709110012,"-"]
[137,"경기","군포","화성조암#2 T/L","154kV 화성-조암T/L 피뢰기설치공사","10기(2~4호, 11, 12, 26~29)","2017-11-12 07:00","2017-11-12 18:00","2017-11-12T07:00:00","2017-11-12T18:00:00","당일",null,null,null,201709060271,"-"]
[138,"경기","동부","왕암가남#1 T/L","154kV 왕암-가남T/L 182호 안전이격확보공사 등 2건","1. 182호 안전이격확보공사 (11/4~7) 2. 송전선로 피뢰기설치공사 (11/8~12)","2017-11-04 08:00","2017-11-12 18:00","2017-11-04T08:00:00","2017-11-12T18:00:00","연속",null,null,null,201709120103,"-"]
[139,"경기","동부","이천가남#2 T/L","154kV 왕암-가남T/L 송전선로 피뢰기설치공사","왕암-가남#1T/L 피뢰기설치공사 관련 4회선구간 안전거리 확보","2017-11-11 08:00","2017-11-12 18:00","2017-11-11T08:00:00","2017-11-12T18:00:00","매일",null,null,null,201709120105,"-"]
[140,"경기","동부","왕암가남#2 T/L","154kV 왕암-가남T/L 182호 안전이격확보공사","182호 안전이격확보공사","2017-11-04 08:00","2017-11-07 18:00","2017-11-04T08:00:00","2017-11-07T18:00:00","연속",null,null,null,201709120104,"-"]
[141,"경기","성남","용인남사#2 T/L","345kV 신용인-신수원T/L등 2구간 OPGW시설공사(화성동탄2)","공사장소 : 신용인S/S, 신안성S/S~동측C/H~서측C/H~신수원S/S 시설내역 : OPGW 120/70sq 24/48C 40.58km 비금속광케이블 24/48C 6.987km","2017-11-21 07:00","2017-11-23 18:00","2017-11-21T07:00:00","2017-11-23T18:00:00","연속",null,null,null,201709120237,"-"]
[142,"경기","성남","용인남사#1 T/L","345kV 신용인-신수원T/L등 2구간 OPGW시설공사(화성동탄2)","공사장소 : 신용인S/S, 신안성S/S~동측C/H~서측C/H~신수원S/S 시설내역 : OPGW 120/70sq 24/48C 40.58km 비금속광케이블 24/48C 6.987km","2017-11-18 07:00","2017-11-20 18:00","2017-11-18T07:00:00","2017-11-20T18:00:00","연속",null,null,null,201709120235,"-"]
[143,"경기","성남","동탄C/C S/T#1 GIS","17년 성남변전협력회사 총액공사","#1S/T 6233 초기점검","2017-11-22 10:00","2017-11-22 18:00","2017-11-22T10:00:00","2017-11-22T18:00:00","당일",null,null,null,201709210138,"-"]
[144,"경기","성남","동탄C/C S/T#2 GIS","17년 성남변전협력회사 총액공사","#2S/T 6333 초기점검","2017-11-23 10:00","2017-11-23 18:00","2017-11-23T10:00:00","2017-11-23T18:00:00","당일",null,null,null,201709210140,"-"]
[145,"경기","성남","서안성남사#1 T/L","345kV 신용인-신수원T/L등 2구간 OPGW시설공사(화성동탄2)","공사장소 : 신용인S/S, 신안성S/S~동측C/H~서측C/H~신수원S/S 시설내역 : OPGW 120/70sq 24/48C 40.58km 비금속광케이블 24/48C 6.987km","2017-11-21 07:00","2017-11-23 18:00","2017-11-21T07:00:00","2017-11-23T18:00:00","연속",null,null,null,201709120236,"-"]
[146,"경기","성남","서안성남사#2 T/L","345kV 신용인-신수원T/L등 2구간 OPGW시설공사(화성동탄2)","공사장소 : 신용인S/S, 신안성S/S~동측C/H~서측C/H~신수원S/S 시설내역 : OPGW 120/70sq 24/48C 40.58km 비금속광케이블 24/48C 6.987km","2017-11-18 07:00","2017-11-20 18:00","2017-11-18T07:00:00","2017-11-20T18:00:00","연속",null,null,null,201709120234,"-"]
[147,"경기","성남","신성남사당#1 T/L","신성남S/S 154kV GIS 대체공사","65-66BUS SEC GIS 대체관련 안전거리 확보","2017-11-18 08:00","2017-12-04 18:00","2017-11-18T08:00:00","2017-12-04T18:00:00","매일",null,null,null,201709130082,"-"]
[148,"경기","성남","신성남S/S 65-66 SEC GIS","신성남S/S 154kV GIS 대체공사","65-66BUS SEC GIS 대체","2017-11-18 08:00","2017-12-02 18:00","2017-11-18T08:00:00","2017-12-02T18:00:00","연속",null,null,null,201709130059,"-"]
[149,"경기","성남","신성남S/S 60-61 SEC GIS","신성남S/S 154kV GIS 대체공사","60-61BUS SEC GIS 대체","2017-11-01 08:00","2017-11-17 18:00","2017-11-01T08:00:00","2017-11-17T18:00:00","연속",null,null,null,201709130053,"-"]
[150,"경기","성남","신용인용인#2 T/L","345kV 신용인-신수원T/L등 2구간 OPGW시설공사(화성동탄2)","공사장소 : 신용인S/S, 신안성S/S~동측C/H~서측C/H~신수원S/S 시설내역 : OPGW 120/70sq 24/48C 40.58km 비금속광케이블 24/48C 6.987km","2017-11-28 07:00","2017-11-29 18:00","2017-11-28T07:00:00","2017-11-29T18:00:00","연속",null,null,null,201709120239,"-"]
[151,"경기","성남","신용인용인#1 T/L","345kV 신용인-신수원T/L등 2구간 OPGW시설공사(화성동탄2)","공사장소 : 신용인S/S, 신안성S/S~동측C/H~서측C/H~신수원S/S 시설내역 : OPGW 120/70sq 24/48C 40.58km 비금속광케이블 24/48C 6.987km","2017-11-24 07:00","2017-11-27 18:00","2017-11-24T07:00:00","2017-11-27T18:00:00","연속",null,null,null,201709120238,"-"]
[152,"경기","성남","용인남사#1 T/L","154kV 신용인-용인T/L No.2-4 전력선 교체공사(안전이격확보)","154kV 신용인-용인T/L No.2-4 전력선 교체공사(안전이격확보)","2017-11-30 07:00","2017-11-30 18:00","2017-11-30T07:00:00","2017-11-30T18:00:00","당일",null,null,null,201709110372,"-"]
[153,"경기","성남","신용인용인#1 T/L","154kV 신용인-용인T/L No.1-2 등 6개 구간 전력선 교체공사","154kV 신용인-용인T/L No.1-2 등 6개구간 전력선 교체공사","2017-11-30 07:00","2017-12-03 18:00","2017-11-30T07:00:00","2017-12-03T18:00:00","연속",null,null,null,201709110370,"-"]
[154,"경기","직할","조암구문천#2 T/L","345kV 아산-화성T/L 피뢰기설치공사(안전확보)","○ 공사내용 : 피뢰기 16기 설치(No.124 하단)","2017-11-23 13:00","2017-11-23 17:00","2017-11-23T13:00:00","2017-11-23T17:00:00","당일",null,null,null,201709070140,"-"]
[155,"경기","직할","조암구문천#2 T/L","구문천S/S 조암구문천#2T/L GIS 조작시험","구문천S/S 조암구문천#2T/L GIS 조작시험","2017-11-06 13:00","2017-11-06 15:00","2017-11-06T13:00:00","2017-11-06T15:00:00","당일",null,null,null,201709080094,"-"]
[156,"경기","직할","조암구문천#1 T/L","구문천S/S 조암구문천#1T/L GIS 조작시험","구문천S/S 조암구문천#1T/L GIS 조작시험","2017-11-06 10:00","2017-11-06 13:00","2017-11-06T10:00:00","2017-11-06T13:00:00","당일",null,null,null,201709080093,"-"]
[157,"경기","직할","조암구문천#2 T/L","345kV 신온양-서서울T/L 피뢰기설치공사(안전확보)","○ 공사내용 : 피뢰기 2기 설치(No.97 하단)","2017-11-08 08:00","2017-11-08 12:00","2017-11-08T08:00:00","2017-11-08T12:00:00","당일",null,null,null,201709070143,"-"]
[158,"경기","직할","발안향남#1 T/L","발안S/S 발안향남#1 T/L GIS 조작시험","발안S/S 발안향남#1 T/L GIS 조작시험","2017-11-07 10:00","2017-11-07 13:00","2017-11-07T10:00:00","2017-11-07T13:00:00","당일",null,null,null,201709080098,"-"]
[159,"경기","직할","발안향남#2 T/L","발안S/S 발안향남#2T/L GIS 조작시험","발안S/S 발안향남#2T/L GIS 조작시험","2017-11-07 13:00","2017-11-07 15:00","2017-11-07T13:00:00","2017-11-07T15:00:00","당일",null,null,null,201709080099,"-"]
[160,"경기","직할","서서울서수원#1 T/L","서수원S/S 서서울서수원#1T/L GIS 조작시험","서수원S/S 서서울서수원#1T/L GIS 조작시험","2017-11-10 10:00","2017-11-10 13:00","2017-11-10T10:00:00","2017-11-10T13:00:00","당일",null,null,null,201709080091,"-"]
[161,"경기","직할","서서울서수원#2 T/L","서수원S/S 서서울서수원#2T/L GIS 조작시험","서수원S/S 서서울서수원#2T/L GIS 조작시험","2017-11-10 13:00","2017-11-10 15:00","2017-11-10T13:00:00","2017-11-10T15:00:00","당일",null,null,null,201709080092,"-"]
[162,"경기","직할","오산향남#1 T/L","154kV 향남S/S #4M.Tr 증설공사","ㅇ 154kV 향남S/S #4M.Tr 증설공사 - 향남S/S 154kV #2BUS 무부하가압","2017-11-04 18:00","2017-11-05 18:00","2017-11-04T18:00:00","2017-11-05T18:00:00","연속",null,null,null,201709130205,"-"]
[163,"경기","직할","화성발안#1 T/L","345kV 신온양-서서울T/L 피뢰기설치공사(안전확보)","○ 공사내용 : 피뢰기 2기 설치(No.110 하단)","2017-11-08 13:00","2017-11-08 17:00","2017-11-08T13:00:00","2017-11-08T17:00:00","당일",null,null,null,201709070144,"-"]
[164,"경기","직할","화성발안#2 T/L","345kV 신온양-서서울T/L 113,114호 안전이격확보공사","345kV 신온양-서서울T/L 113,114호 안전이격확보공사 관련 안전이격거리확보(15호)","2017-11-11 07:00","2017-11-24 18:00","2017-11-11T07:00:00","2017-11-24T18:00:00","매일",null,null,null,201709060263,"-"]
[165,"경기","평택","고덕오성CC T/L","고덕S/S 고덕-오성복합T/L GIS 초기점검","고덕S/S 고덕-오성복합T/L GIS 초기점검","2017-11-11 09:00","2017-11-11 18:00","2017-11-11T09:00:00","2017-11-11T18:00:00","당일",null,null,null,201709110275,"-"]
[166,"경기","평택","서운삼죽 T/L","2016~17년 충주 송전정비 협력회사 총액공사(피뢰기 설치) 등","154kV 서운-만승T/L(서운-삼죽측) No.29~56 피뢰기설치, No.81~83 전력선교체","2017-11-14 08:00","2017-11-21 18:00","2017-11-14T08:00:00","2017-11-21T18:00:00","연속",null,null,null,201709110196,"-"]
[167,"경기","평택","송탄소사벌 T/L","154kV 소사벌S/S #3M.Tr 증설공사","○ 154kV 소사벌S/S #3M.Tr 증설공사 - 170kV #2BUS 무부하시험","2017-11-04 10:00","2017-11-05 10:00","2017-11-04T10:00:00","2017-11-05T10:00:00","연속",null,null,null,201709060096,"-"]
[168,"경기","평택","송탄소사벌 T/L","154kV 소사벌S/S #3M.Tr 증설공사","154kV 소사벌S/S #3M.Tr 무부하가압용","2017-11-25 10:00","2017-11-26 14:00","2017-11-25T10:00:00","2017-11-26T14:00:00","연속",null,null,null,201709060095,"-"]
[169,"경기","평택","고덕송탄 T/L","송탄S/S 고덕-송탄T/L GIS 초기점검","송탄S/S 고덕-송탄T/L GIS 초기점검 / 고덕S/S 고덕-송탄T/L GIS 초기점검","2017-11-12 10:00","2017-11-12 18:00","2017-11-12T10:00:00","2017-11-12T18:00:00","당일",null,null,null,201709110273,"-"]
[170,"경기","평택","서운안성#1 T/L","154kV 서운-안성T/L 전력선 교체공사","○ 공사구간 : No.2~6 ○ 공사규모 : 전력선 18가닥교체(3경간)","2017-11-05 07:00","2017-11-07 18:00","2017-11-05T07:00:00","2017-11-07T18:00:00","연속",null,null,null,201709070112,"-"]
[171,"경기","평택","송탄안성 T/L","154kV 송탄-안성T/L 전력선 교체공사","○ 공사구간 : No.28~34, 38~40 ○ 공사구간 : 18가닥(8경간)","2017-11-11 07:00","2017-11-15 18:00","2017-11-11T07:00:00","2017-11-15T18:00:00","연속",null,null,null,201709070125,"-"]
[172,"경기","평택","서안성안성#1 T/L","154kV 서운-안성T/L 전력선 교체공사(안전확보)","○ 공사구간 : No.2~6(4회선병가구간) ○ 공사규모 : 전력선 18가닥교체(3경간)","2017-11-05 07:00","2017-11-07 18:00","2017-11-05T07:00:00","2017-11-07T18:00:00","매일",null,null,null,201709070116,"-"]
[173,"경기","평택","서안성안성#2 T/L","154kV 서운-안성T/L 전력선 교체공사(안전확보)","○ 공사구간 : No.2~6(4회선병가구간) ○ 공사규모 : 전력선 18가닥교체(3경간)","2017-11-08 07:00","2017-11-10 18:00","2017-11-08T07:00:00","2017-11-10T18:00:00","매일",null,null,null,201709070115,"-"]
[174,"경기","평택","서운안성#2 T/L","154kV 서운-안성T/L 전력선 교체공사","○ 공사구간 : No.2~6 ○ 공사규모 : 전력선 18가닥교체(3경간)","2017-11-08 07:00","2017-11-10 18:00","2017-11-08T07:00:00","2017-11-10T18:00:00","연속",null,null,null,201709070113,"-"]
[175,"경기","평택","서운안성#2 T/L","154kV 안성S/S 안성-남안성T/L GIS 증설공사","154kV 안성S/S 안성-남안성T/L GIS 증설공사 - 기기번호 변경작업","2017-11-02 10:00","2017-11-03 18:00","2017-11-02T10:00:00","2017-11-03T18:00:00","연속",null,null,null,201709110379,"-"]
[176,"경기","평택","오산향남#1 T/L","154kV 오산향남, 오산평택T/L 지중화공사(No.14~17)","14~17호 0.58kM 지중화(전력구), CH철탑 2기, OPGW교체(8~26)","2017-11-20 08:00","2017-11-24 18:00","2017-11-20T08:00:00","2017-11-24T18:00:00","연속",null,null,null,201709140290,"-"]
[177,"경기","평택","오산향남#2 T/L","154kV 오산향남, 오산평택T/L 지중화공사(No.14~17)","14~17 0.58kM 지중화(전력구), CH철탑 2기, OPGW교체(26~45)","2017-11-25 08:00","2017-11-28 18:00","2017-11-25T08:00:00","2017-11-28T18:00:00","연속",null,null,null,201709140296,"-"]
[178,"경기","평택","오산평택#2 T/L","154kV 오산향남, 오산평택T/L 지중화공사(No.6~9)","6~9 0.58kM 지중화(전력구), CH철탑 2기, OPGW교체(26~45)","2017-11-25 08:00","2017-11-29 18:00","2017-11-25T08:00:00","2017-11-29T18:00:00","연속",null,null,null,201709140293,"-"]
[179,"경기","평택","오산평택#1 T/L","154kV 오산향남, 오산평택T/L 지중화공사(No.6~9)","6~9 0.58kM 지중화(전력구), CH철탑 2기, OPGW교체(8~26)","2017-11-20 08:00","2017-11-24 18:00","2017-11-20T08:00:00","2017-11-24T18:00:00","연속",null,null,null,201709140291,"-"]
[180,"경기","평택","청북S/S 청북-평택#1T/L GIS","평택전력지사 170kV GIS 정밀점검(청북-평택#1TL)","평택전력지사 170kV GIS 정밀점검(청북-평택#1TL)","2017-11-25 09:00","2017-11-27 18:00","2017-11-25T09:00:00","2017-11-27T18:00:00","연속",null,null,null,201709060040,"-"]
[181,"경기","평택","청북S/S 만호-청북T/L GIS","평택전력지사 170kV GIS 정밀점검(만호-청북TL)","평택전력지사 170kV GIS 정밀점검(만호-청북TL)","2017-11-07 09:00","2017-11-09 18:00","2017-11-07T09:00:00","2017-11-09T18:00:00","연속",null,null,null,201709060037,"-"]
[182,"경기","평택","청북S/S 청북-평택#2T/L GIS","평택전력지사 170kV GIS 정밀점검(청북-평택#2TL)","평택전력지사 170kV GIS 정밀점검(청북-평택#2TL)","2017-11-04 09:00","2017-11-06 18:00","2017-11-04T09:00:00","2017-11-06T18:00:00","연속",null,null,null,201709060036,"-"]
[183,"경기","평택","청북S/S 포승-청북T/L GIS","평택전력지사 170kV GIS 정밀점검(포승-청북TL)","평택전력지사 170kV GIS 정밀점검(포승-청북TL)","2017-11-17 09:00","2017-11-19 18:00","2017-11-17T09:00:00","2017-11-19T18:00:00","연속",null,null,null,201709060039,"-"]
[184,"경기","평택","평택추팔#1 T/L","154kV 평택-추팔T/L 안전이격거리 확보공사","○ 공사대상 : No.34,35,38 ○ 공사규모 : 철탑 3기 교체(가선로 구성)","2017-11-28 07:00","2017-12-02 18:00","2017-11-28T07:00:00","2017-12-02T18:00:00","연속",null,null,null,201709080242,"-"]
[185,"강원","강릉","동해강릉 T/L","2016~17년 송전정비협력회사 총액공사","○ BC-Link 설치 작업 (강릉T/L No.13~14, 57~58호간)","2017-11-14 07:00","2017-11-14 18:00","취소","취소","당일",null,null,null,201709110395,"-"]
[186,"강원","강릉","강릉횡계#1 T/L","2016~17년 송전정비협력회사 총액공사","○ BC-Link 설치 작업 (No.23~24호간)","2017-11-13 07:00","2017-11-13 18:00","취소","취소","당일",null,null,null,201709110392,"-"]
[187,"강원","강릉","속초S/S #1 EM.Tr A","2017년 변전협력회사 총액공사","1. ESS용 주변압기 초기점검 2. ESS용 1차, 2차 GIS 초기점검 3. ESS Feeder별 GIS 초기점검 4. 기타기기 점검","2017-11-13 09:00","2017-11-17 18:00","2017-11-13T09:00:00","2017-11-17T18:00:00","연속",null,null,null,201709090034,"-"]
[188,"강원","강릉","신양양_양양#1 T/L","154kV 신양양-양양 #1T/L 피뢰기 설치공사","○ 송전선로용 피뢰기 설치공사(No.1~30)","2017-11-13 07:00","2017-11-15 18:00","2017-11-13T07:00:00","2017-11-15T18:00:00","매일",null,null,null,201709110403,"-"]
[189,"강원","강릉","동해영동TP T/L","2016~17년 송전정비협력회사 총액공사","○ BC-Link 설치 작업 (강릉T/L No.6~7호간)","2017-11-17 07:00","2017-11-17 18:00","취소","취소","당일",null,null,null,201709110401,"-"]
[190,"강원","강릉","평창올림픽 T/L","2016~17년 송전정비협력회사 총액공사","○ BC-Link 설치 작업 (평창올림픽분기T/L No.1~횡계평창T/L No.7호간)","2017-11-21 07:00","2017-11-21 18:00","취소","취소","당일",null,null,null,201709110407,"-"]
[191,"강원","강릉","횡계평창T/L","2016~17년 송전정비협력회사 총액공사","○ BC-Link 설치 작업 (No.6~7호간)","2017-11-20 07:00","2017-11-20 18:00","취소","취소","당일",null,null,null,201709110404,"-"]
[192,"강원","동해","이원동해TP T/L","지중송전선로 도블측정","154kV 이원-동해TPT/L 지중송전선로 도블측정","2017-11-01 09:00","2017-11-01 18:00","2017-11-01T09:00:00","2017-11-01T18:00:00","당일",null,null,null,201709110190,"-"]
[193,"강원","동해","북평영동TP#1 T/L","154kV 영동화력T/L 안전이격확보공사","○ 안전이격확보공사 - 설치 : 2기 / 철거 : 2기","2017-11-17 08:00","2017-11-27 18:00","2017-11-17T08:00:00","2017-11-27T18:00:00","연속",null,null,null,201709110120,"-"]
[194,"강원","동해","북평영동TP#2 T/L","154kV 영동화력T/L 안전이격확보공사","○ 안전이격확보공사 - 설치 : 2기 / 철거 : 2기","2017-11-28 08:00","2017-12-06 18:00","2017-11-28T08:00:00","2017-12-06T18:00:00","연속",null,null,null,201709110122,"-"]
[195,"강원","동해","삼척동해TP T/L","2017년 동해전력지사 170kV GIS 정밀점검공사","1. 삼척S/S 삼척-동해TP T/L GIS 정밀점검(687)","2017-11-02 10:00","2017-11-04 18:00","2017-11-02T10:00:00","2017-11-04T18:00:00","연속",null,null,null,201709060327,"-"]
[196,"강원","원주","신제천남원주#2 T/L","154kV 원주북원주등 8개T/L 송전선로용 피뢰기 설치공사","송전선로용 피뢰기 설치 1기","2017-11-01 13:00","2017-11-01 18:00","2017-11-02T08:00:00","2017-11-02T18:00:00","당일",null,null,null,201709100008,"-"]
[197,"강원","원주","신제천남원주#1 T/L","154kV 원주북원주등 8개T/L 송전선로용 피뢰기 설치공사","송전선로용 피뢰기 설치 1기","2017-11-01 09:00","2017-11-01 12:00","2017-11-01T09:00:00","2017-11-01T18:00:00","당일",null,null,null,201709100007,"-"]
[198,"강원","직할","홍천남춘천 T/L","2016~2017년도 강원직할 송전정비 협력회사 총액공사","○ 송전선로용 피뢰기 설치 : 36기(108set)","2017-11-28 08:00","2017-11-30 18:00","2017-11-13T08:00:00","2017-11-15T18:00:00","매일",null,null,null,201709130127,"-"]
[199,"강원","직할","청평HP의암HP T/L","154kV 옥외GCB 긴급점검","옥외GCB 개폐타임 측정","2017-11-13 09:00","2017-11-13 18:00","2017-11-13T09:00:00","2017-11-13T18:00:00","당일",null,null,null,201709080021,"-"]
[200,"강원","태백","태백영월 T/L","○ 태백T/L 노후취약 지지물 교체공사","○ 태백T/L 노후취약 지지물 교체공사","2017-11-08 09:00","2017-11-14 18:00","2017-11-08T09:00:00","2017-11-14T18:00:00","매일",null,null,null,201708090177,"-"]
[201,"충북","직할","점촌단양T/L","2016~17년 직할 송전정비 협력회사 총액공사","- 전력선 교체(No.9~47) - SB댐퍼 설치(No.13~47)","2017-11-06 09:00","2017-11-14 18:00","2017-11-06 09:00","2017-11-14 18:00","연속",null,null,null,201709100014,"-"]
[202,"충북","직할","신제천영월CC#1 T/L","신제천S/S 신제천영월CC#1T/L GIS 초기점검","- 170kV GIS 초기점검","2017-11-15 10:00","2017-11-15 14:00","2017-11-15 10:00","2017-11-15 14:00","당일",null,null,null,201709110460,"-"]
[203,"충북","직할","신제천주진#2 T/L","신제천S/S 신제천주진#2T/L GIS 초기점검","- 170kV GIS 초기점검","2017-11-13 10:00","2017-11-13 14:00","2017-11-13 10:00","2017-11-13 14:00","당일",null,null,null,201709110456,"-"]
[204,"충북","직할","풍동음성#1 T/L","음성S/S 풍동음성#1T/L LA 점검","- 170kV LA 보통점검","2017-11-03 13:00","2017-11-03 17:00","2017-11-03 13:00","2017-11-03 17:00","당일",null,null,null,201708230016,"○"]
[205,"충북","직할","음성금왕#1 T/L","2017년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검 (No.40-64)","2017-11-06 09:00","2017-11-08 18:00","2017-11-06 09:00","2017-11-08 18:00","매일",null,null,null,201709110035,"○"]
[206,"충북","직할","음성금왕#2 T/L","2017년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검 (No.40-64)","2017-11-13 09:00","2017-11-15 18:00","2017-11-13 09:00","2017-11-15 18:00","매일",null,null,null,201709110049,"○"]
[207,"충북","직할","신제천왕암#2 T/L","154kV 왕암변전소 벽체 누수 보수공사","- 선홈통 주변 누수보수","2017-11-13 09:00","2017-11-13 18:00","2017-11-13 09:00","2017-11-13 18:00","연속",null,null,null,201709130221,"-"]
[208,"충북","직할","왕암북충주#1 T/L","154kV 왕암변전소 벽체 누수 보수공사","- 선홈통 주변 누수보수","2017-11-14 09:00","2017-11-14 18:00","2017-11-14 09:00","2017-11-14 18:00","당일",null,null,null,201709130222,"-"]
[209,"충북","직할","왕암북충주#2 T/L","154kV 왕암변전소 벽체 누수 보수공사","- 선홈통 주변 누수보수","2017-11-14 09:00","2017-11-14 18:00","2017-11-14 09:00","2017-11-14 18:00","당일",null,null,null,201709130223,"-"]
[210,"충북","직할","왕암북충주#1 T/L","154kV 왕암변전소 벽체 누수 보수공사","- 선홈통 주변 누수보수","2017-11-15 09:00","2017-11-15 18:00","2017-11-15 09:00","2017-11-15 18:00","당일",null,null,null,201709130225,"-"]
[211,"충북","직할","신제천왕암#1 T/L","154kV 왕암변전소 벽체 누수 보수공사","- 선홈통 주변 누수보수","2017-11-15 09:00","2017-11-15 18:00","2017-11-15 09:00","2017-11-15 18:00","매일",null,null,null,201709130224,"-"]
[212,"충북","직할","신제천왕암#1 T/L","154kV 왕암변전소 벽체 누수 보수공사","- 선홈통 주변 누수보수","2017-11-13 09:00","2017-11-13 18:00","2017-11-13 09:00","2017-11-13 18:00","매일",null,null,null,201709130220,"-"]
[213,"충북","청주","사직북청주#1 T/L","154kV 서청주-사직 등 6개T/L 접지설비 보강공사","사직-북청주#1T/L 비규격 접지선 교체 및 병행지선 설치","2017-11-18 09:00","2017-11-18 18:00","2017-11-18 09:00","2017-11-18 18:00","당일",null,null,null,201708310141,"-"]
[214,"충북","청주","사직북청주#2 T/L","154kV 서청주-사직 등 6개T/L 접지설비 보강공사","사직-북청주#2T/L 비규격 접지선 교체 및 병행지선 설치","2017-11-19 09:00","2017-11-19 18:00","2017-11-19 09:00","2017-11-19 18:00","당일",null,null,null,201708310142,"-"]
[215,"충북","청주","서청주사직#1 T/L","154kV 서청주-사직 등 6개T/L 접지설비 보강공사","서청주-사직#1T/L 비규격 접지선 교체 및 병행지선 설치","2017-11-11 09:00","2017-11-12 18:00","2017-11-11 09:00","2017-11-12 18:00","매일",null,null,null,201708310139,"-"]
[216,"충북","청주","서청주사직#2 T/L","154kV 서청주-사직 등 6개T/L 접지설비 보강공사","서청주-사직#2T/L 비규격 접지선 교체 및 병행지선 설치","2017-11-04 09:00","2017-11-05 18:00","2017-11-04 09:00","2017-11-05 18:00","연속",null,null,null,201708310140,"-"]
[217,"충북","청주","신옥천남대전#2 T/L","2017년 청주전력 변전협력회사 총액공사","신옥천S/S 154kV 신옥천-남대전#2T/L PT 보통점검","2017-11-20 14:00","2017-11-20 18:00","2017-11-20 14:00","2017-11-20 18:00","당일",null,null,null,201709120152,"-"]
[218,"충북","청주","신옥천남대전#1 T/L","2017년 청주전력 변전협력회사 총액공사","신옥천S/S 154kV 신옥천-남대전#1T/L LA 보통점검","2017-11-20 09:30","2017-11-20 14:00","2017-11-20 09:30","2017-11-20 14:00","당일",null,null,null,201709120149,"-"]
[219,"충북","청주","청원오송#1 T/L","154kV 청원-오송 등 2개T/L EBA 절연유 채취","154kV 청원-오송 등 2개T/L EBA 절연유 채취 대상 : 청원-오송, 오송-북청주 T/L 오송C/H EBA 12상","2017-11-26 09:00","2017-11-26 18:00","2017-11-26 09:00","2017-11-26 18:00","당일",null,null,null,201708310149,"-"]
[220,"충북","청주","신진천오창#1 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","항공장애표시구 설치 No.14~15, 46 ~47호 (4개)","2017-11-05 08:00","2017-11-05 12:00","2017-11-05 08:00","2017-11-05 12:00","매일",null,null,null,201709120095,"-"]
[221,"충북","청주","신진천오창#2 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","항공장애표시구 설치 No.14~15, 46 ~47호 (4개)","2017-11-05 13:00","2017-11-05 19:00","2017-11-05 13:00","2017-11-05 19:00","매일",null,null,null,201709120096,"-"]
[222,"충북","청주","청원부강#1 T/L","154kV 부강-신탄진연결T/L 건설사업","구간 : (기설) 154kV 부강T/L No.16 ~ (기설)154kV 청신T/L No.19 지 지 물 : 철탑 설치 11기, 철거 1기 선로길이 : 설치 2C - 4.9km 전 력 선 : HSTACIR/AW 240㎟ × S × 2C 공시선 : ACSR97㎟×1조(OPGW 97㎟×1조, 별도시행)","2017-11-06 08:00","2017-11-12 17:00","2017-11-06 08:00","2017-11-12 17:00","매일",null,null,null,201709050017,"-"]
[223,"충북","청주","청원신탄진 T/L","154kV 부강-신탄진T/L 송전용량증대 전선교체공사","○ 전력선교체 - 154kV 청원-신탄진T/L No.19 ~ 신탄진S/S - 154kV 청주-대청HPT/L (No.19 ~ 대청H/P) - 154kV 신탄진-대청HPT/L (신탄진S/S ~ 대청H/P) ○ 기타 : 피뢰기 설치 및 금구류 교체","2017-11-15 07:00","2017-11-22 18:00","2017-11-15 07:00","2017-11-22 18:00","연속",null,null,null,201709040013,"○"]
[224,"충북","충주","금왕남음성#2 T/L","2017년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검 (No.2-26)","2017-11-06 09:00","2017-11-08 18:00","2017-11-06 09:00","2017-11-08 18:00","매일",null,null,null,201709110045,"○"]
[225,"충북","충주","금왕남음성#1 T/L","2017년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검 (No.2-26)","2017-11-13 09:00","2017-11-15 18:00","2017-11-13 09:00","2017-11-15 18:00","매일",null,null,null,201709110051,"○"]
[226,"충북","충주","서운만승 T/L","154kV 풍동-음성 등 9개T/L 전력선 교체공사(서운-만승)","154kV 서운-만승T/L No.81~83 전력선교체","2017-11-11 08:00","2017-11-13 18:00","2017-11-11 08:00","2017-11-13 18:00","연속",null,null,null,201709110191,"○"]
[227,"충북","충주","증평괴산 T/L","154kV 증평S/S GIS화 공사","증평-괴산T/L GIS 이설작업","2017-11-13 09:00","2017-11-22 18:00","2017-11-13 09:00","2017-11-22 18:00","연속",null,null,null,201709110526,"-"]
[228,"충북","충주","증평초정#2 T/L","154kV 증평S/S GIS화 공사","증평-초정#2T/L GIS 이설작업","2017-11-13 09:00","2017-11-28 18:00","2017-11-13 09:00","2017-11-28 18:00","연속",null,null,null,201709110527,"-"]
[229,"충북","충주","진천만승#2 T/L","154kV 풍동-음성 등 9개T/L 전력선 교체공사(서운-만승)","154kV 진천-만승 #2T/L No.35~37 전력선교체","2017-11-14 08:00","2017-11-21 18:00","2017-11-14 08:00","2017-11-21 18:00","연속",null,null,null,201709110201,"○"]
[230,"충북","충주","진천만승#1 T/L","154kV 풍동-음성 등 9개T/L 전력선 교체공사(서운-만승)","154kV 진천-만승 #1T/L No.35~37 전력선교체","2017-11-11 08:00","2017-11-13 18:00","2017-11-11 08:00","2017-11-13 18:00","연속",null,null,null,201709110199,"○"]
[231,"대전충남","서산","신당진당진#1 T/L","[송전]154kV 신당진-당진#1T/L No.44 애자교체공사","154kV 신당진-당진#1T/L No.44 애자교체공사","2017-11-05 07:00","2017-11-05 18:00","2017-11-05T07:00:00","2017-11-05T18:00:00","당일",null,null,null,201709080331,"-"]
[232,"대전충남","서산","신당진당진#2 T/L","[송전]154kV 신당진-당진#2T/L No.44 애자교체공사","154kV 신당진-당진#2T/L No.44 애자교체공사","2017-11-04 07:00","2017-11-04 18:00","2017-11-04T07:00:00","2017-11-04T18:00:00","당일",null,null,null,201709080324,"-"]
[233,"대전충남","서산","서산해미 T/L","154kV 신당진-서산#2T/L No.2등 4기 피뢰기 설치공사","154kV 신당진-서산#2T/L No.2등 4기 피뢰기 설치공사관련 안전거리 확보 휴전","2017-11-11 07:00","2017-11-11 18:00","2017-11-11T07:00:00","2017-11-11T18:00:00","당일",null,null,null,201709180094,"-"]
[234,"대전충남","서산","서산홍성 T/L","[송전]154kV 서산-홍성T/L 안전이격 확보공사","[송전]154kV 서산-홍성T/L No.96호 저지상고 해소 안전이격 확보공사","2017-11-20 07:00","2017-11-26 18:00","2017-11-20T07:00:00","2017-11-26T18:00:00","연속",null,null,null,201709180088,"-"]
[235,"대전충남","서산","서산해미 T/L","[송전]154kV 서산-홍성T/L 안전이격 확보공사","[송전]154kV 서산-홍성T/L No.96호 저지상고 해소 안전이격 확보공사","2017-11-13 07:00","2017-11-18 18:00","2017-11-13T07:00:00","2017-11-18T18:00:00","연속",null,null,null,201709180090,"-"]
[236,"대전충남","아산","둔포추팔#2 T/L","둔포S/S 154kV 둔포-추팔#2T/L GIS 정밀점검","○ 154kV 둔포-추팔#2T/L GIS 정밀점검","2017-11-11 09:00","2017-11-12 18:00","2017-11-11T09:00:00","2017-11-12T18:00:00","연속",null,null,null,201709140255,"-"]
[237,"대전충남","아산","둔포추팔#1 T/L","둔포S/S 154kV 둔포-추팔#1T/L GIS 정밀점검","○ 154kV 둔포-추팔#1T/L GIS 정밀점검","2017-11-04 09:00","2017-11-05 18:00","2017-11-04T09:00:00","2017-11-05T18:00:00","연속",null,null,null,201709140254,"-"]
[238,"대전충남","아산","아산S/S 154kV #61 BUS","아산S/S 154KV 장기사용 GIS 교체공사","1. 170KV GIS *7BAY GIS 철거설치 2. 제어케이블 철거설치","2017-11-09 09:00","2017-11-20 09:00","2017-11-09T09:00:00","2017-11-20T09:00:00","연속",null,null,null,201707120039,"-"]
[239,"대전충남","아산","아산온양#2 T/L","아산S/S 154KV 장기사용 GIS 교체공사","1. 170KV GIS *7BAY GIS 철거설치 2. 제어케이블 철거설치 3. #1SC BAY 인출변경 환원","2017-11-18 08:00","2017-11-19 09:00","2017-11-18T08:00:00","2017-11-19T09:00:00","연속",null,null,null,201709070309,"-"]
[240,"대전충남","아산","아산온양#1 T/L","아산S/S 154KV 장기사용 GIS 교체공사","1. 170KV GIS *7BAY GIS 철거설치 2. 제어케이블 철거설치 3. #1SC BAY 인출변경 환원","2017-11-25 08:00","2017-11-26 20:00","2017-11-25T08:00:00","2017-11-26T20:00:00","연속",null,null,null,201707120044,"-"]
[241,"대전충남","아산","아산예산#2 T/L","아산S/S 154KV 장기사용 GIS 교체공사","1. 170KV GIS *7BAY GIS 철거설치 2. 제어케이블 철거설치 3. #1SC BAY 인출변경 환원","2017-11-27 09:00","2017-12-14 18:00","2017-11-27T09:00:00","2017-12-14T18:00:00","연속",null,null,null,201709070318,"-"]
[242,"대전충남","아산","아산S/S 154kV #61 BUS","아산S/S 154KV 장기사용 GIS 교체공사","1. 170KV GIS *7BAY GIS 철거설치 2. 제어케이블 철거설치","2017-11-27 09:00","2017-11-29 18:00","2017-11-27T09:00:00","2017-11-29T18:00:00","연속",null,null,null,201709070321,"-"]
[243,"대전충남","아산","아산S/S 154kV #66 BUS","아산S/S 154KV 장기사용 GIS 교체공사","1. 170KV GIS *7BAY GIS 철거설치 2. 제어케이블 철거설치","2017-11-30 09:00","2017-12-06 18:00","2017-11-30T09:00:00","2017-12-06T18:00:00","연속",null,null,null,201708090109,"-"]
[244,"대전충남","아산","아산S/S 154kV #66 BUS","아산S/S 154KV 장기사용 GIS 교체공사","1. 170KV GIS *7BAY GIS 철거설치 2. 제어케이블 철거설치","2017-11-03 10:00","2017-11-08 18:00","2017-11-03T10:00:00","2017-11-08T18:00:00","연속",null,null,null,201705240076,"-"]
[245,"대전충남","아산","풍세장재#2 T/L","풍세S/S 154kV 풍세-장재#2T/L 보호배전반 교체","○ 154kV 풍세-장재#2T/L 보호배전반 교체","2017-11-22 09:00","2017-11-25 18:00","취소","취소","연속",null,null,null,201709150075,"-"]
[246,"대전충남","아산","풍세장재#1 T/L","풍세S/S 154kV 풍세-장재#1T/L 보호배전반 교체","○ 154kV 풍세-장재#1T/L 보호배전반 교체","2017-11-15 09:00","2017-11-18 18:00","취소","취소","연속",null,null,null,201709150074,"-"]
[247,"대전충남","직할","용운대화#2 T/L","154kV 용운-대화T/L 안전거리 확보공사","철탑설치 : 3기(No.10,11,12) 철탑철거 : 4기(No.10,11,12,13) 전선교체 : No.8~14(2.18km) 기타부대공사","2017-11-10 07:00","2017-12-03 18:00","취소","취소","연속",null,null,null,201709060112,"-"]
[248,"대전충남","직할","용운대화#1 T/L","154kV 용운-대화T/L 안전거리 확보공사","철탑설치 : 3기(No.10,11,12) 철탑철거 : 4기(No.10,11,12,13) 전선교체 : No.8~14(2.18km) 기타부대공사","2017-11-10 07:00","2017-11-15 18:00","취소","취소","연속",null,null,null,201709060111,"-"]
[249,"대전충남","직할","덕진송강#1 T/L","17년 직할관내 154kV GIS 정밀점검","송강S/S 154kV 덕진-송강#1T/L GIS 정밀점검","2017-11-06 09:00","2017-11-07 18:00","2017-11-27T09:00:00","2017-11-28T18:00:00","연속",null,null,null,201709080237,"-"]
[250,"대전충남","청양","서천T/P 154kV #1 BUS TIE CB","서천T/P 임시전담설비 구축공사","-#1B/T","2017-11-23 09:00","2017-11-27 18:00","2017-11-23T09:00:00","2017-11-27T18:00:00","연속",null,null,null,201709270041,"-"]
[251,"대전충남","청양","대천서천화력#1 T/L","서천T/P 임시전담설비 구축공사","-대천서천화력#1T/L","2017-11-07 09:00","2017-11-14 18:00","2017-11-07T09:00:00","2017-11-14T18:00:00","연속",null,null,null,201709270038,"-"]
[252,"대전충남","청양","옥산서천화력#1 T/L","서천T/P 임시전담설비 구축공사","-옥산서천화력#1T/L","2017-11-15 09:00","2017-11-22 18:00","2017-11-15T09:00:00","2017-11-22T18:00:00","연속",null,null,null,201709270039,"-"]
[253,"전북","군산","군산S/S 154kV #3 BUS TIE CB","군산S/S 6300CB","동군산S/S 23kV GIS 대체공사관련 배전선로 부하절체","2017-11-07 13:00","2017-11-07 15:00","2017-11-07 13:00","2017-11-07 15:00","당일",null,null,null,201708250099,"-"]
[254,"전북","군산","군산S/S 154kV #1 BUS TIE CB","군산S/S 6100CB","동군산S/S 23kV GIS 대체공사관련 배전선로 부하절체(모선통합)","2017-11-07 13:00","2017-11-07 15:00","2017-11-07 13:00","2017-11-07 15:00","당일",null,null,null,201709270093,"-"]
[255,"전북","군산","군산서군산#2 T/L","군산서군산T/L 안전이격확보공사","- 철탑신설 :2 기(30, 31호) - 전선교체 : 31호~37호","2017-11-22 07:00","2017-12-16 18:00","2017-11-22 07:00","2017-12-16 18:00","연속",null,null,null,201709180124,"-"]
[256,"전북","군산","군산동군산#2 T/L","군산동군산T/L피뢰기설치공사","- 피뢰기설치 : 38호(1기)- - 군산서군산T/L 안전이격확보공사 OPGW 이설","2017-11-20 07:00","2017-11-20 18:00","2017-11-20 07:00","2017-11-20 18:00","연속",null,null,null,201709190020,"-"]
[257,"전북","군산","군산동군산#1 T/L","군산동군산T/L피뢰기설치공사","- 피뢰기설치 : 38호(1기)- - 군산서군산T/L 안전이격확보공사 OPGW 이설","2017-11-21 07:00","2017-11-21 18:00","2017-11-21 07:00","2017-11-21 18:00","연속",null,null,null,201709190019,"-"]
[258,"전북","군산","군산서군산#1 T/L","군산P/O 노후배전반 대체공사","154kV 군산-서군산 #1T/L 송전선로 보호반 대체(양단)","2017-11-17 10:00","2017-11-21 18:00","2017-11-17 10:00","2017-11-21 18:00","연속",null,null,null,201709150022,"-"]
[259,"전북","군산","팔봉봉동#1 T/L","팔봉봉동#1T/L 정밀점검공사","정밀점검 : 14기","2017-11-06 08:00","2017-11-08 18:00","2017-11-06 08:00","2017-11-08 18:00","매일",null,null,null,201709110078,"-"]
[260,"전북","군산","팔봉두마#2 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 4차 공정 - 팔봉-두마#1T/L, #2M.Tr 1차 교체","2017-11-18 18:00","2017-11-19 18:00","2017-11-18 18:00","2017-11-19 18:00","연속",null,null,null,201709120021,"-"]
[261,"전북","군산","팔봉봉동#2 T/L","팔봉봉동#2T/L 정밀점검공사","정밀점검 : 14기","2017-11-09 08:00","2017-11-11 18:00","2017-11-09 08:00","2017-11-11 18:00","매일",null,null,null,201709110080,"-"]
[262,"전북","군산","팔봉두마#1 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 4차 공정 - 팔봉-두마#1T/L, #2M.Tr 1차 교체","2017-11-06 08:00","2017-11-30 18:00","2017-11-06 08:00","2017-11-30 18:00","연속",null,null,null,201709120011,"-"]
[263,"전북","군산","팔봉두마#2 T/L","팔봉S/S 170kV 장기사용 GIS 대체공사","○ 170kV GIS 대체 : 8CCT 중 4차 공정 - 팔봉-두마#1T/L, #2M.Tr 1차 교체","2017-11-08 16:00","2017-11-08 18:00","2017-11-08 16:00","2017-11-08 18:00","당일",null,null,null,201709120016,"-"]
[264,"전북","김제","담양김제 T/L","154kV 담양-김제T/L 피뢰기 설치공사","공사명 : 154kV 담양-김제T/L 피뢰기설치공사 대상 : No.1~11 내용 : 송전선로용 피뢰기 설치","2017-11-12 09:00","2017-11-13 18:00","2017-11-03 09:00","2017-11-04 18:00","연속",null,null,null,201709210137,"-"]
[265,"전북","김제","백산김제#2 T/L","154kV 담양-김제T/L 피뢰기 설치공사(안전이격 거리확보)","공사명 : 154kV 담양-김제T/L 피뢰기설치공사 대상 : No.1~11 내용 : 송전선로용 피뢰기 설치","2017-11-12 09:00","2017-11-13 18:00","2017-11-03 09:00","2017-11-04 18:00","매일",null,null,null,201709210141,"-"]
[266,"전북","김제","신김제전주#2 T/L","154kV 신김제-전주#2T/L 피뢰기 설치공사","공사명 : 154kV 신김제-남전주#2T/L 피뢰기설치공사 대상 : No.1~30,38,48 내용 : 송전선로용 피뢰기 설치","2017-11-20 09:00","2017-11-23 18:00","2017-11-20 09:00","2017-11-23 18:00","연속",null,null,null,201709210129,"-"]
[267,"전북","김제","신김제정공#2 T/L","GIS 보통점검","GIS 보통점검","2017-11-02 09:00","2017-11-02 18:00","2017-11-02 09:00","2017-11-02 18:00","당일",null,null,null,201709110013,"-"]
[268,"전북","김제","신김제전주#1 T/L","154kV신김제-남전주#2T/L 피뢰기 공사(안전이격거리)","공사명 : 154kV 신김제-남전주#2T/L 피뢰기설치공사 대상 : No.1~30 내용 : 송전선로용 피뢰기 설치","2017-11-27 09:00","2017-11-30 18:00","2017-11-27 09:00","2017-11-30 18:00","연속",null,null,null,201709210130,"-"]
[269,"전북","김제","신김제남전주#1 T/L","관내S/S 보호배전반 교체공사","신김제 및 남전주S/S 보호반 교체","2017-11-20 09:00","2017-11-23 18:00","취소","취소","연속",null,null,null,201709200056,"-"]
[270,"전북","김제","신김제남전주#2 T/L","관내S/S 보호배전반 교체공사","신김제 및 남전주S/S 보호반 교체","2017-11-27 09:00","2017-11-30 18:00","취소","취소","연속",null,null,null,201709200060,"-"]
[271,"전북","김제","정공섬진강수력 T/L","주)세니온 154kV 송전선로 보호반 성능개선","주보호(87) : 재폐로 무전압 시간 기동조건 및 전압 활선‧사선 판단방식 개선 등 후비보호(21) : PT Failure 검출 로직 및 Zone3 영상전류 보상기능 개선","2017-11-14 10:00","2017-11-14 18:00","2017-11-14 10:00","2017-11-14 18:00","당일",null,null,null,201709180146,"○"]
[272,"전북","김제","백산김제#1 T/L","154kV 백산-김제T/L 선종교체공사","1. 공사개요 가. 공사구간 : 154kV 백산-김제T/L No.35 ～ 48호 나. 공사내용 ◯ 선종교체 : 8.95 C-km (ACSR 240㎟ → HSTACIR 240㎟) ◯ 철탑교체 : 신설 4기, 철거 4기 [No.40, 43, 46, 47호] ◯ 임시선로 구성 및 기타 부대공사","2017-11-14 09:00","2017-11-15 18:00","2017-11-11 09:00","2017-11-12 18:00","연속",null,null,null,201709270118,"-"]
[273,"전북","직할","신김제동전주#1 T/L","154kV 장기미동작 차단기 조작시험","154kV 장기미동작 차단기 조작시험","2017-11-10 08:00","2017-11-10 13:00","2017-11-10 08:00","2017-11-10 13:00","당일",null,null,null,201709200251,"-"]
[274,"전북","직할","신김제동전주#2 T/L","154kV 장기미동작 차단기 조작시험","154kV 장기미동작 차단기 조작시험","2017-11-10 13:00","2017-11-10 18:00","2017-11-10 13:00","2017-11-10 18:00","당일",null,null,null,201709200252,"-"]
[275,"전북","직할","무주진안 T/L","무주진안 T/L","1. 무주, 진안S/S 154kV 차단기 점검","2017-11-17 10:00","2017-11-17 18:00","2017-11-17 10:00","2017-11-17 18:00","당일",null,null,null,201708160082,"-"]
[276,"전북","직할","무주용담수력 T/L","154kV 무주-용담T/L 피뢰기 설치공사","○ 154kV 무주-용담T/L 피뢰기 설치공사 - 대상 : No.1, 46~83, 53 (40기)","2017-11-06 08:30","2017-11-09 18:00","2017-11-06 08:30","2017-11-09 18:00","매일",null,null,null,201709200186,"-"]
[277,"전북","직할","북전주진안 T/L","북전주S/S 장기사용 170kV GIS 대체공사 1차","북전주S/S 장기사용 170kV GIS 1차[2BAY 대체] - 154kV 동전주-북전주#1T/L GIS - 154kV #1M.Tr 1차 GIS 북전주-진안T/L 11/2 북전주S/S #2BUS 시험가압 선로","2017-11-02 17:00","2017-11-02 19:00","2017-11-02 17:00","2017-11-02 19:00","당일",null,null,null,201709200023,"-"]
[278,"전북","직할","북전주용담수력 T/L","154kkV 북전주-용담수력T/L 피뢰기 설치공사","○ 154kV 북전주-용담수력T/L 피뢰기 설치공사 - 대상 : 154kV 북전주-용담수력T/L No.50","2017-11-28 09:00","2017-11-28 18:00","2017-11-28 09:00","2017-11-28 18:00","당일",null,null,null,201709200195,"-"]
[279,"전북","직할","북전주진안 T/L","북전주S/S 장기사용 170kV GIS 대체공사 2차","북전주S/S 장기사용 170kV GIS 2차[1BAY 대체] - 154kV #2M.Tr 1차 GIS 북전주-진안T/L 11/26 북전주S/S #2BUS 시험가압 선로","2017-11-26 17:00","2017-11-26 19:00","2017-11-26 17:00","2017-11-26 19:00","당일",null,null,null,201709200139,"-"]
[280,"전북","직할","북전주진안 T/L","북전주S/S 장기사용 170kV GIS 대체공사 1차","북전주S/S 장기사용 170kV GIS 1차[2BAY 대체] - 154kV 동전주-북전주#1T/L GIS - 154kV #1M.Tr 1차 GIS 북전주-진안T/L 11/12 북전주S/S #1BUS 시험가압 선로","2017-11-12 13:00","2017-11-13 13:30","2017-11-12 13:00","2017-11-13 13:30","연속",null,null,null,201709200048,"-"]
[281,"전북","직할","북전주진안 T/L","154kV 북전주-진안 T/L 피뢰기 대체공사","장기사용 기타설비 대체공사 - 154kV 피뢰기 교체공사","2017-11-30 10:00","2017-11-30 18:00","2017-11-30 10:00","2017-11-30 18:00","당일",null,null,null,201708250103,"-"]
[282,"광주전남","강진","신강진대불#1 T/L","신강진S/S 154kV 송전선로 인출변경공사","-154kV 신강진-강진 S/T~1호 #1, #2 T/L -154kV 신강진-해남 S/T~1호 #1 T/L -154kV 신강진-대불 S/T~1호 #1, #2 T/L 인출변경공사","2017-12-04 07:00","2017-12-11 18:00","2017-12-04 07:00","2017-12-11 18:00","연속",null,null,null,201709110437,"-"]
[283,"광주전남","강진","신강진해남#2 T/L","154kV 신강진-해남#2T/L(피뢰기 설치공사)","154kV 신강진-해남#2T/L(피뢰기 설치공사) - 345kV 신화순-신강진 등 10개T/L 송전선로용 피뢰기 설치공사","2017-11-06 07:00","2017-11-16 18:00","2017-11-06 07:00","2017-11-16 18:00","매일",null,null,null,201709050066,"-"]
[284,"광주전남","강진","신강진대불#2 T/L","신강진S/S 154kV 송전선로 인출변경공사","-154kV 신강진-강진 S/T~1호 #1, #2 T/L -154kV 신강진-해남 S/T~1호 #1 T/L -154kV 신강진-대불 S/T~1호 #1, #2 T/L 인출변경공사","2017-11-19 09:00","2017-11-21 18:00","2017-11-19 09:00","2017-11-21 18:00","연속",null,null,null,201709110433,"-"]
[285,"광주전남","광주","계림승주#2(서남권상수도T분기) T/L","154kV 계림승주T/L 안전이격거리확보공사","철탑교체 : 4기 (No.51, 52, 53, 54) 전선교체 : No.50~52, 54~55","2017-11-06 08:00","2017-11-10 18:00","2017-11-04 08:00","2017-11-08 18:00","연속",null,null,null,201708160150,"○"]
[286,"광주전남","광주","계림충장#2 T/L","계림-충장#2 T/L(변전협력회사 공사)","계림-충장#2T/L 보호반 교체","2017-11-27 09:00","2017-11-29 18:00","2017-11-27 09:00","2017-11-29 18:00","연속",null,null,null,201709080010,"-"]
[287,"광주전남","광주","신광주곡성#1 T/L","곡성S/S 곡성-남원#1T/L 및 #2M.Tr 1차 GIS 교체공사","#2BUS 무부하가압","2017-11-03 09:00","2017-11-08 10:00","2017-11-03 09:00","2017-11-08 10:00","연속",null,null,null,201708080109,"-"]
[288,"광주전남","광주","곡성남원#1 T/L","곡성S/S 곡성-남원#1T/L 및 #2M.Tr 1차 GIS 교체공사","곡성S/S 곡성-남원#1T/L 및 #2M.Tr 1차 GIS 교체공사","2017-11-04 18:00","2017-11-29 18:00","2017-11-04 18:00","2017-11-29 18:00","연속",null,null,null,201708080106,"-"]
[289,"광주전남","광주","신광주곡성#1 T/L","곡성S/S 곡성-남원#1T/L 및 #2M.Tr 1차 GIS 교체공사","#1BUS 무부하가압","2017-11-15 18:00","2017-11-17 09:00","2017-11-15 18:00","2017-11-17 09:00","연속",null,null,null,201708080110,"-"]
[290,"광주전남","광주","신광주곡성#1 T/L","154kV 곡성-남원#2T/L 피뢰기 설치공사(병가구간 안전이격 확보)","○ 154kV 곡성-남원#2T/L 피뢰기 설치공사 -대상 : No.10, 15","2017-11-10 10:00","2017-11-10 18:00","2017-11-10 10:00","2017-11-10 18:00","당일",null,null,null,201709200194,"-"]
[291,"광주전남","광주","정공담양 T/L","154kV 장성-영광 등 3개T/L 피뢰기 설치공사","정공-담양T/L No.120~135(16기,48set) 장성-영광 #1T/L No.1~68(64기, 192set) 신화순-화순 #1T/L No.1~57(57기, 171set)","2017-11-13 07:00","2017-11-13 18:00","2017-11-13 07:00","2017-11-13 18:00","당일",null,null,null,201709120107,"○"]
[292,"광주전남","광주","담양일곡#1 T/L","154kV 담양-일곡T/L 안전이격확보공사","철탑교체 : 11기 (No.174, 186~189, 199, 200, 216, 220, 223, 224) 애자련 변경 : 1기 (No. 222)","2017-11-14 09:00","2017-11-15 18:00","2017-11-14 09:00","2017-11-15 18:00","연속",null,null,null,201709190074,"○"]
[293,"광주전남","광주","담양일곡#2 T/L","154kV 담양-일곡T/L 안전이격확보공사","철탑교체 : 11기 (No.174, 186~189, 199, 200, 216, 220, 223, 224) 애자련 변경 : 1기 (No. 222)","2017-11-16 09:00","2017-11-24 18:00","2017-11-16 09:00","2017-11-24 18:00","연속",null,null,null,201709190078,"○"]
[294,"광주전남","광주","담양일곡#1 T/L","154kV 담양-일곡T/L 안전이격확보공사","철탑교체 : 11기 (No.174, 186~189, 199, 200, 216, 220, 223, 224) 애자련 변경 : 1기 (No. 222)","2017-11-25 09:00","2017-11-30 18:00","2017-11-25 09:00","2017-11-30 18:00","연속",null,null,null,201709190079,"○"]
[295,"광주전남","광주","신화순나주#2 T/L","2017년 변전 협력회사 총액공사","신화순-나주#2/L LA교체","2017-11-22 09:00","2017-11-22 18:00","2017-11-22 09:00","2017-11-22 18:00","당일",null,null,null,201708250019,"-"]
[296,"광주전남","광주","신화순화순#2 T/L","2017년 변전 협력회사 총액공사","신화순화순#2T/L LA교체","2017-11-23 09:00","2017-11-23 18:00","2017-11-23 09:00","2017-11-23 18:00","당일",null,null,null,201708250028,"-"]
[297,"광주전남","광주","신화순평동T/L","154kV신화순평동T/L 피뢰기설치 안전거리확보","○신화순-매월#1T/L No.2~9(8기) 병가구간 안전거리확보 ○남광주-금천#1T/L No.75(1기) 병가구간 안전거리확보","2017-11-04 08:00","2017-11-04 18:00","2017-11-04 08:00","2017-11-04 18:00","당일",null,null,null,201709110397,"-"]
[298,"광주전남","광주","신화순화순#1 T/L","154kV 장성-영광 등 3개T/L 피뢰기 설치공사","정공-담양T/L No.120~135(16기,48set) 장성-영광 #1T/L No.1~68(64기, 192set) 신화순-화순 #1T/L No.1~57(57기, 171set)","2017-11-15 07:00","2017-11-19 18:00","2017-11-15 07:00","2017-11-19 18:00","연속",null,null,null,201709120110,"-"]
[299,"광주전남","광주","충장농성#2 T/L","2017년 광주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2017-11-22 09:00","2017-11-23 18:00","2017-11-22 09:00","2017-11-23 18:00","당일",null,null,null,201707310024,"-"]
[300,"광주전남","광주","충장농성#1 T/L","2017년 광주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2017-11-20 09:00","2017-11-21 18:00","2017-11-20 09:00","2017-11-21 18:00","당일",null,null,null,201707310023,"-"]
[301,"광주전남","광주","남광주화순#2 T/L","154kV남광주화순#2T/L 피뢰기설치 안전거리확보","○화순-승주#1T/L No.290~296(7기) 병가구간 안전거리확보","2017-11-10 08:00","2017-11-10 18:00","2017-11-10 08:00","2017-11-10 18:00","당일",null,null,null,201709110412,"-"]
[302,"광주전남","목포","장성영광#1 T/L","154kV 남악-북항 등 5개T/L 피뢰기 설치공사","154kV 장성-영광#1T/L 피뢰기 설치공사 ○ 송전용 피뢰기 설치 : 57기 171set","2017-11-20 07:00","2017-11-24 18:00","취소","취소","매일",null,null,null,201707170006,"-"]
[303,"광주전남","목포","고창홍농 T/L","154kV 고창-홍농T/L(170kV GIS 대체공사)","170kV GIS 대체","2017-11-17 09:00","2017-12-14 18:00","취소","취소","연속",null,null,null,201708090072,"-"]
[304,"광주전남","목포","홍농S/S 154kV #1 BUS TIE GIS","154kV BUS TIE(170kV GIS 대체공사)","170kV GIS 대체","2017-11-13 09:00","2017-12-08 18:00","2017-11-13 09:00","2017-12-08 18:00","연속",null,null,null,201708090091,"-"]
[305,"광주전남","순천","광양하동#2 T/L","154kV 광양하동#2 T/L LA 초기점검","17년 순천전력 변전협력 총액공사 - 광양S/S 154kV 광양하동#2 T/L LA 초기점검","2017-11-02 10:00","2017-11-02 18:00","2017-11-02 10:00","2017-11-02 18:00","당일",null,null,null,201709080207,"○"]
[306,"광주전남","순천","서순천주암HP T/L","154kV 승주-서순천T/L 안전이격확보공사","154kV 승주-서순천T/L 안전이격확보공사 -철탑교체 10기, 전선교체 10.132C-km","2017-11-18 07:00","2017-11-22 18:00","2017-11-18 07:00","2017-11-22 18:00","연속",null,null,null,201709120191,"-"]
[307,"광주전남","순천","광양순천#2 T/L","154kV 광양-순천#2 T/L 불량애자 정비","국산애자 절연성능 진단결과 불량애자 정비","2017-11-04 08:00","2017-11-04 18:00","2017-11-04 08:00","2017-11-04 18:00","당일",null,null,null,201709110184,"-"]
[308,"광주전남","순천","순천율촌#2 T/L","154kV 순천S/S 변전설비 철거공사","1. 154kV 순천S/S 옥외 변전설비 철거공사 - 순천-율촌#1,2T/L CB 철거","2017-11-02 09:00","2017-11-03 18:00","2017-11-02 09:00","2017-11-03 18:00","당일",null,null,null,201708040017,"○"]
[309,"광주전남","순천","승주서순천 T/L","154kV 승주-서순천T/L 안전이격확보공사","154kV 승주-서순천T/L 안전이격확보공사 -철탑교체 10기, 전선교체 10.132C-km","2017-11-15 07:00","2017-11-17 18:00","2017-11-15 07:00","2017-11-17 18:00","연속",null,null,null,201709120195,"-"]
[310,"광주전남","순천","순천승주#2 T/L","154kV 순천-승주#2 T/L 승주S/S GIS 보통점검","17년 순천전력 변전협력 총액공사 - 154kV 순천-승주#2 T/L 승주S/S GIS 보통점검","2017-11-14 10:00","2017-11-14 17:00","2017-11-14 10:00","2017-11-14 17:00","당일",null,null,null,201709080215,"○"]
[311,"광주전남","순천","승주주암HP T/L","154kV 승주-주암HP T/L 승주S/S GIS 보통점검","17년 순천전력 변전협력 총액공사 - 154kV 승주-주암HP T/L 승주S/S GIS 보통점검","2017-11-13 13:00","2017-11-13 17:00","2017-11-13 13:00","2017-11-13 17:00","당일",null,null,null,201709080213,"-"]
[312,"광주전남","순천","승주서순천 T/L","154kV 승주-서순천T/L 안전이격확보공사","154kV 승주-서순천T/L 안전이격확보공사 -철탑교체 10기, 전선교체 10.132C-km","2017-11-30 07:00","2017-12-09 18:00","2017-11-30 07:00","2017-12-09 18:00","연속",null,null,null,201709120193,"-"]
[313,"광주전남","순천","승주주암HP T/L","154kV 승주-서순천T/L 안전이격확보공사","154kV 승주-서순천T/L 안전이격확보공사 -철탑교체 10기, 전선교체 10.132C-km","2017-11-23 07:00","2017-11-29 18:00","2017-11-23 07:00","2017-11-29 18:00","연속",null,null,null,201709120197,"-"]
[314,"광주전남","순천","승주서순천 T/L","154kV승주-서순천T/L 피뢰기설치 안전거리확보","○ 화순-승주#1T/L No.2~4(3기) 피뢰기설치공사 병가구간 안전거리확보 ○ 승주S/S 170kV GIS 보통점검","2017-11-09 08:00","2017-11-09 18:00","2017-11-09 08:00","2017-11-09 18:00","당일",null,null,null,201709110419,"-"]
[315,"광주전남","순천","순천승주#1 T/L","154kV순천-승주#1T/L 피뢰기설치 안전거리확보","○화순-승주#1T/L No.1(1기) 병가구간 안전거리확보","2017-11-10 08:00","2017-11-10 18:00","2017-11-10 08:00","2017-11-10 18:00","당일",null,null,null,201709110416,"○"]
[316,"광주전남","순천","여수TP화치#2 T/L","154kV 여수TP-화치#2 T/L 여수화력 GIS 보통점검","17년 순천전력 변전협력 총액공사 - 여수화력 154kV 여수TP-화치#2 T/L 여수화력 GIS 보통점검","2017-11-07 13:00","2017-11-07 18:00","2017-11-07 13:00","2017-11-07 18:00","당일",null,null,null,201709080211,"-"]
[317,"광주전남","순천","여수TP용성#2 T/L","154kV 여수TP-용성#2T/L 여수화력 GIS 보통점검","17년 순천전력 변전협력 총액공사 - 여수화력 154kV 여수TP-용성#2 T/L 여수화력 GIS 보통점검 - 가공송전 순시점검 위탁공사","2017-11-13 10:00","2017-11-13 17:00","2017-11-13 10:00","2017-11-13 17:00","당일",null,null,"신뢰도 개선",201709080212,"-"]
[318,"광주전남","순천","여수TP화치#1 T/L","154kV 여수TP-화치#1 T/L 여수화력 GIS 보통점검","17년 순천전력 변전협력 총액공사 - 여수화력 154kV 여수TP-화치#1 T/L 여수화력 GIS 보통점검","2017-11-07 09:00","2017-11-07 13:00","2017-11-07 09:00","2017-11-07 13:00","당일",null,null,null,201709080210,"-"]
[319,"광주전남","순천","여천호남TP#1 T/L","154kV 여천-호남TP#1 T/L LA 초기점검","17년 순천전력 변전협력 총액공사 - 여천S/S 154kV 여천-호남TP#1 T/L LA 초기점검","2017-11-06 10:00","2017-11-06 12:00","2017-11-06 10:00","2017-11-06 12:00","당일",null,null,null,201709080208,"-"]
[320,"광주전남","순천","여천여수#1 T/L","154kV 여천-여수#1 T/L 여천S/S 공기압방식 차단기 특별점검","17년 순천전력 변전협력 총액공사 - 154kV 여천-여수#1 T/L 여천S/S 공기압방식 차단기 특별점검","2017-11-10 09:00","2017-11-10 12:00","2017-11-10 09:00","2017-11-10 12:00","당일",null,null,null,201709080227,"-"]
[321,"광주전남","순천","여천여수산단#1 T/L","154kV 여천-여수산단#1 T/L 여천S/S GIS 보통점검","17년 순천전력 변전협력 총액공사 - 154kV 여천여수산단#1 T/L 여천S/S GIS 보통점검","2017-11-06 13:00","2017-11-06 15:00","2017-11-06 13:00","2017-11-06 15:00","당일",null,null,null,201709080216,"-"]
[322,"광주전남","순천","여천여수산단#2 T/L","154kV 여천-여수산단#2 T/L 여천S/S GIS 보통점검","17년 순천전력 변전협력 총액공사 - 154kV 여천여수산단#2 T/L 여천S/S GIS 보통점검","2017-11-06 15:00","2017-11-06 17:00","2017-11-06 15:00","2017-11-06 17:00","당일",null,null,null,201709080217,"-"]
[323,"광주전남","순천","용성여수산단#2 T/L","154kV 용성-여수산단#2 T/L 가공송전 순시점검","2017년 가공송전 순시점검 위탁공사 - 정밀점검 (1~15호, 18기)","2017-11-13 08:00","2017-11-14 18:00","2017-11-13 08:00","2017-11-14 18:00","매일",null,null,null,201709110183,"-"]
[324,"광주전남","순천","용성여수산단#1 T/L","154kV 용성-여수산단#1 T/L 가공송전 순시점검","2017년 가공송전 순시점검 위탁공사 - 정밀점검 (1~15호, 18기)","2017-11-11 08:00","2017-11-12 18:00","2017-11-11 08:00","2017-11-12 18:00","매일",null,null,null,201709110179,"-"]
[325,"광주전남","순천","여수TP용성#1 T/L","154kV 여수TP-용성#1 T/L 가공송전 순시점검","2017년 가공송전 순시점검 위탁공사 - 정밀점검 (1~3호, 4기)","2017-11-12 08:00","2017-11-12 18:00","2017-11-12 08:00","2017-11-12 18:00","당일",null,null,null,201709110182,"-"]
[326,"광주전남","순천","율촌여수산단#2 T/L","154kV 율촌-여수산단#1 T/L 장기미동작 차단기 점검","17년 순천전력 변전협력 총액공사 - 154kV 율촌-여수산단#1 T/L 장기미동작 차단기 점검","2017-11-29 10:00","2017-11-29 15:00","2017-11-29 10:00","2017-11-29 15:00","당일",null,null,null,201709110321,"-"]
[327,"광주전남","순천","율촌여수산단#1 T/L","154kV 율촌-여수산단#1 T/L 장기미동작 차단기 점검","17년 순천전력 변전협력 총액공사 - 154kV 율촌-여수산단#1 T/L 장기미동작 차단기 점검","2017-11-28 10:00","2017-11-28 15:00","2017-11-28 10:00","2017-11-28 15:00","당일",null,null,null,201709110319,"-"]
[328,"광주전남","직할","나주금천#2 T/L","154kV나주-금천#2T/L 피뢰기설치 안전거리확보","○ 남광주-금천#1T/L No.82(1기) 피뢰기설치 병가구간 안전거리확보","2017-11-01 08:00","2017-11-01 12:00","2017-11-01 08:00","2017-11-01 12:00","당일",null,null,null,201709110409,"-"]
[329,"광주전남","직할","남광주화순#1 T/L","154kV 남광주화순#1T/L 피뢰기 설치공사","○ 남광주-화순#1T/L No.1~339(57기) 피뢰기설치","2017-11-20 08:00","2017-11-21 18:00","2017-11-20 08:00","2017-11-21 18:00","매일",null,null,null,201709110384,"-"]
[330,"광주전남","직할","남광주금천#1 T/L","154kV남광주-금천#1T/L 피뢰기설치공사","○남광주-금천#1T/L No.1~82(70기) 피뢰기설치","2017-11-01 08:00","2017-11-04 18:00","2017-11-01 08:00","2017-11-04 18:00","매일",null,null,null,201709110400,"-"]
[331,"광주전남","직할","농성화정#2 T/L","154kV 농성-화정#2T/L","2017년 직할 154kV GIS 정밀점검 공사 - 농성S/S 농성-화정#2T/L GIS 정밀점검","2017-11-13 09:00","2017-11-14 18:00","2017-11-27 09:00","2017-11-28 18:00","연속",null,null,null,201709130192,"-"]
[332,"광주전남","직할","농성화정#1 T/L","154kV 농성-화정#1T/L","2017년 직할 154kV GIS 정밀점검 공사 - 농성S/S 농성-화정#1T/L GIS 정밀점검","2017-11-10 09:00","2017-11-11 18:00","2017-11-23 09:00","2017-11-24 18:00","연속",null,null,null,201709130190,"-"]
[333,"광주전남","직할","매월화정#2 T/L","154kV 매월-화정#2T/L","2017년 직할 154kV GIS 정밀점검 공사 - 화정S/S 매월-화정#2T/L GIS 정밀점검","2017-11-06 09:00","2017-11-07 18:00","2017-11-06 09:00","2017-11-06 18:00","연속",null,null,null,201709130184,"-"]
[334,"대구","경산","노변효목#2 T/L","성능저하 국산애자 교체공사","154kV 노변-효목 T/L No.18 등 3기 애자교체공사","2017-11-18 08:00","2017-11-18 18:00","2017-11-19 08:00","2017-11-19 18:00","당일",null,null,null,201709200055,"-"]
[335,"대구","경산","노변효목#1 T/L","성능저하 국산애자 교체공사","154kV 노변-효목 T/L No.18 등 3기 애자교체공사","2017-11-17 08:00","2017-11-17 18:00","2017-11-18 08:00","2017-11-18 18:00","당일",null,null,null,201709200052,"-"]
[336,"대구","경산","범물남대구#2 T/L","성능저하 국산애자 교체공사(안전확보)","154kV 노변-효목 T/L No.18 등 3기 애자교체공사간 안전확보","2017-11-18 08:00","2017-11-18 18:00","2017-11-19 08:00","2017-11-19 18:00","당일",null,null,null,201709200061,"-"]
[337,"대구","경산","범물남대구#1 T/L","성능저하 국산애자 교체공사(안전확보)","154kV 노변-효목 T/L No.18 등 3기 애자교체공사간 안전확보","2017-11-17 08:00","2017-11-17 18:00","2017-11-18 08:00","2017-11-18 18:00","당일",null,null,null,201709200059,"-"]
[338,"대구","달성","강창성서#2 T/L","EBA 자기애관 교체공사","자기애관을 폴리머애관으로 교체","2017-11-27 08:00","2017-11-28 18:00","취소","취소","연속",null,null,null,201709040156,"-"]
[339,"대구","달성","강창성서#1 T/L","EBA 자기애관 교체공사","자기애관을 폴리머애관으로 교체","2017-11-25 08:00","2017-11-26 18:00","2017-11-25 08:00","2017-11-26 18:00","연속",null,null,null,201709040154,"-"]
[340,"대구","달성","고령다산#2 T/L","154kV 고령쌍림#2T/L 피뢰기 설치공사","- 고령쌍림#2T/L 피뢰기 설치 공사 안전 이격 - 고령쌍림, 쌍림합천TL 2~12호 병가","2017-11-27 08:00","2017-11-28 18:00","2017-11-27 08:00","2017-11-28 18:00","매일",null,null,null,201709110359,"-"]
[341,"대구","달성","유가구지#2 T/L","154kV 구지S/S #4M.Tr 증설공사","154kV 구지S/S #4M.Tr 증설공사","2017-11-01 09:00","2017-11-11 18:00","2017-11-01 09:00","2017-11-11 18:00","연속",null,null,null,201709190140,"-"]
[342,"대구","달성","다사달서#1 T/L","달서S/S 170kV 장기사용 GIS 대체공사","T/L GIS×1CCT, BUS-TIE GIS×1CCT, PT GIS×1CCT 대체","2017-11-01 09:00","2017-11-20 13:00","2017-11-01 09:00","2017-11-20 13:00","연속",null,null,null,201709070274,"-"]
[343,"대구","달성","다사달서#2 T/L","달서S/S 170kV 장기사용 GIS 대체공사","T/L GIS×1CCT, BUS-TIE GIS×1CCT, PT GIS×1CCT 대체","2017-11-03 15:00","2017-11-03 18:00","2017-11-03 15:00","2017-11-03 18:00","당일",null,null,null,201709070294,"-"]
[344,"대구","달성","다사달서#2 T/L","달서S/S 170kV 장기사용 GIS 대체공사","T/L GIS×1CCT, BUS-TIE GIS×1CCT, PT GIS×1CCT 대체","2017-11-11 13:00","2017-11-11 18:00","2017-11-11 13:00","2017-11-11 18:00","당일",null,null,null,201709070308,"-"]
[345,"대구","달성","다사달서#2 T/L","달서S/S 170kV 장기사용 GIS 대체공사","T/L GIS×1CCT, BUS-TIE GIS×1CCT, PT GIS×1CCT 대체","2017-11-19 13:00","2017-11-19 18:00","2017-11-19 13:00","2017-11-19 18:00","당일",null,null,null,201709070311,"-"]
[346,"대구","달성","달서팔달#1 T/L","달서S/S 170kV 장기사용 GIS 대체공사","T/L GIS×1CCT, M.Tr 1차 GIS×1CCT 대체","2017-11-24 09:00","2017-12-13 13:00","2017-11-24 09:00","2017-12-13 13:00","연속",null,null,null,201709070333,"-"]
[347,"대구","달성","대구봉덕#2 T/L","154kV 대구봉덕#2T/L 피뢰기 설치공사","- 대구봉덕#2T/L 33호 피뢰기 설치","2017-11-20 14:00","2017-11-20 18:00","2017-11-20 14:00","2017-11-20 18:00","당일",null,null,null,201709110318,"-"]
[348,"대구","달성","상인봉덕#1 T/L","154kV 상인봉덕#1T/L 피뢰기 설치공사","- 상인봉덕#1T/L 1호 피뢰기 설치","2017-11-20 08:00","2017-11-20 15:00","2017-11-20 08:00","2017-11-20 15:00","당일",null,null,null,201709110311,"-"]
[349,"대구","달성","고령쌍림#2 T/L","154kV 고령쌍림#2T/L 피뢰기 설치공사","- 고령쌍림#2T/L 피뢰기 설치 공사(63기) - 쌍림합천#1T/L 전력선 교체(2~9호) 및 피뢰기설치(19기) 안전이격","2017-11-27 08:00","2017-12-02 18:00","2017-11-27 08:00","2017-11-30 18:00","연속",null,null,null,201709110358,"-"]
[350,"대구","칠곡","북대구연락#1 T/L","EBA 자기애관 교체공사","자기애관을 폴리머애관으로 교체","2017-11-29 08:00","2017-11-30 18:00","2017-11-29 08:00","2017-11-30 18:00","연속",null,null,null,201709080011,"-"]
[351,"대구","칠곡","북대구구암#2 T/L","북대구-구암 안전이격확보 공사","- 구간 : 24~33호(8기 철거, 6기 신설, 전력선교체 : 2.411c-km)","2017-11-20 08:00","2017-11-29 18:00","2017-11-20 08:00","2017-11-29 18:00","연속",null,null,null,201709080296,"-"]
[352,"대구","칠곡","북대구구암#1 T/L","북대구-구암 안전이격확보 공사","- 구간 : 24~33호(8기 철거, 6기 신설, 전력선교체 : 2.411c-km)","2017-11-25 08:00","2017-12-04 18:00","2017-11-25 08:00","2017-12-04 18:00","연속",null,null,null,201709080297,"-"]
[353,"대구","칠곡","북대구연락#2 T/L","EBA 자기애관 교체공사","자기애관을 폴리머애관으로 교체","2017-11-29 08:00","2017-11-30 18:00","2017-11-29 08:00","2017-11-30 18:00","연속",null,null,null,201709080292,"-"]
[354,"대구","포항","아화건천#2 T/L","154kV 아화-건천T/L 안전이격 확보공사","철탑 및 전력선 교체(No.27~34)","2017-11-04 08:00","2017-11-13 18:00","2017-11-27 08:00","2017-12-06 18:00","연속",null,null,null,201709110274,"-"]
[355,"대구","포항","아화건천#1 T/L","154kV 아화-건천T/L 안전이격 확보공사","철탑 및 전력선 교체(No.27~34)","2017-11-04 08:00","2017-11-13 18:00","2017-11-27 08:00","2017-12-06 18:00","연속",null,null,null,201709110272,"-"]
[356,"경북","구미","상주S/S 154kV #1 BUS TIE CB","차단기 동작시험","차단기 동작시험","2017-11-13 15:00","2017-11-13 18:00","2017-11-13 15:00","2017-11-13 18:00","당일",null,null,null,201709210110,"-"]
[357,"경북","영주","예천S/S 154kV #2 BUS","2017년 예천S/S 170kV 장기사용 GIS 대체(#2DS설치)","신영주-예천#1T/L 647, #1M.Tr 1차 6133, BUS TIE 6100, PT GIS 대체(4Bay 동시) 관련 #2DS(6132, 642, 6102, #2BUS PT) 설치 및 BUS SEC DS(65-66-1) 설치","2017-11-07 10:00","2017-11-17 10:00","2017-11-07 10:00","2017-11-17 10:00","연속",null,null,null,201708080008,"-"]
[358,"경북","영주","점촌문경 T/L","2016-17년도 영주 송전정비 협력회사 총액공사","피뢰기 설치","2017-11-06 07:00","2017-11-09 18:00","2017-11-06 07:00","2017-11-09 18:00","연속",null,null,null,201708070137,"-"]
[359,"경북","직할","안계의성#2 T/L","의성S/S 옥외철구설비 GIS화 공사","-170kV GIS설치관련 중장비 안전이격 확보","2017-11-08 08:00","2017-11-09 14:00","2017-11-08 08:00","2017-11-09 14:00","매일",null,null,null,201709130054,"-"]
[360,"경북","직할","안계의성#1 T/L","의성S/S 옥외철구설비 GIS화 공사","-170kV GIS설치관련 중장비 안전이격 확보","2017-11-08 08:00","2017-11-09 14:00","2017-11-08 08:00","2017-11-09 14:00","매일",null,null,null,201709130055,"-"]
[361,"경북","직할","군위의성#1 T/L","의성S/S 옥외철구설비 GIS화 공사","-170kV GIS설치관련 중장비 안전이격 확보","2017-11-09 14:00","2017-11-10 18:00","2017-11-09 14:00","2017-11-10 18:00","매일",null,null,null,201709130056,"-"]
[362,"경북","직할","군위의성#2 T/L","의성S/S 옥외철구설비 GIS화 공사","-170kV GIS설치관련 중장비 안전이격 확보","2017-11-09 14:00","2017-11-10 18:00","2017-11-09 14:00","2017-11-10 18:00","매일",null,null,null,201709130057,"-"]
[363,"경북","직할","울진평해 T/L","154kV 울진 현종산 풍력발전단지 송전선로 건설공사","분기철탑 검설(기설 No.104 철거 및 신설 No.14 조립, 전력선 가선)","2017-11-21 09:00","2017-11-30 18:00","2017-11-21 09:00","2017-11-30 18:00","연속",null,null,null,201709080251,"-"]
[364,"부산울산","동부산","신양산S/S 154kV #61 T BUS","345kV 신양산S/S 현대화공사","T-BUS 철거","2017-11-03 09:00","2017-11-18 18:00","2017-11-03 09:00","2017-11-18 18:00","연속",null,null,null,201708300081,"-"]
[365,"부산울산","북부산","구포모라#2 T/L","2017년 북부산 154kV GIS 정밀점검 공사","모라S/S 구포-모라#2T/L (637) GIS 정밀점검","2017-11-30 09:00","2017-12-02 16:00","2017-11-30 09:00","2017-12-02 16:00","연속",null,null,null,201709070182,"-"]
[366,"부산울산","북부산","구포모라#1 T/L","2017년 북부산 154kV GIS 정밀점검 공사","모라S/S 구포-모라#1T/L (627) GIS 정밀점검","2017-11-27 09:00","2017-11-29 16:00","2017-11-27 09:00","2017-11-29 16:00","연속",null,null,null,201709070181,"○"]
[367,"부산울산","북부산","물금삼랑진PP T/L","2017년 북부산 154kV GIS 정밀점검 공사","물금S/S 물금-삼랑진PP T/L (627) GIS 정밀점검","2017-11-20 09:00","2017-11-22 16:00","2017-11-20 09:00","2017-11-22 16:00","연속",null,null,null,201709070179,"-"]
[368,"부산울산","북부산","북부산삼랑진PP#2 T/L","물금-삼랑진T/L 피뢰기설치관련 안전이격[신, 물금-삼랑진#2T/L]","물금-삼랑진T/L 피뢰기설치관련 안전이격[신, 물금-삼랑진#2T/L]","2017-11-21 07:00","2017-11-22 16:00","2017-11-21 07:00","2017-11-22 16:00","연속",null,null,null,201709060015,"-"]
[369,"부산울산","북부산","북부산삼랑진PP#2 T/L","북부산-호포T/L 피뢰기 설치관련 안전이격(신, 북부산-물금T/L)","북부산-호포T/L 피뢰기 설치관련 안전이격(신, 북부산-물금T/L)","2017-11-02 08:00","2017-11-03 18:00","2017-11-02 08:00","2017-11-03 18:00","연속",null,null,null,201709180069,"-"]
[370,"부산울산","북부산","북부산호포 T/L","북부산S/S 154kV 취약설비 GIS화 공사","북부산S/S 북부산-호포T/L 인출변경 6J7 휴전","2017-11-02 08:00","2017-11-10 18:00","2017-11-02 08:00","2017-11-10 18:00","연속",null,null,null,201709070191,"-"]
[371,"부산울산","북부산","북부산삼랑진PP#2 T/L","북부산S/S 154kV 취약설비 GIS화 공사","북부산S/S 북부산-삼랑진#2T/L 인출변경 6H7 휴전(신.북부산물금T/L)","2017-11-11 08:00","2017-11-17 18:00","2017-11-11 08:00","2017-11-17 18:00","연속",null,null,null,201709070194,"-"]
[372,"부산울산","북부산","북부산양산 T/L","북부산S/S 154kV 취약설비 GIS화 공사","북부산S/S 북부산-양산T/L 인출변경 6G7 휴전","2017-11-30 08:00","2017-12-06 18:00","2017-11-30 08:00","2017-12-06 18:00","연속",null,null,null,201709070198,"-"]
[373,"부산울산","북부산","서창산막#1 T/L","154kV 서창산막T/L 2~9호 지장철탑이설공사","154kV 서창산막T/L 지장이설 본선로 구성 2~9호(철탑3기신설, 전선교체 2.1km)","2017-11-12 08:00","2017-11-15 17:00","2017-11-12 08:00","2017-11-15 17:00","연속",null,null,null,201709040038,"-"]
[374,"부산울산","북부산","서창산막#2 T/L","154kV 서창산막T/L 2~9호 지장철탑이설공사","154kV 서창산막T/L 지장이설 본선로 구성 2~9호(철탑3기신설, 전선교체 2.1km)","2017-11-17 08:00","2017-11-21 17:00","2017-11-17 08:00","2017-11-21 17:00","연속",null,null,null,201709040077,"-"]
[375,"부산울산","북부산","한림정삼계#2 T/L","154kV 북부산-미남 등 8개T/L 피뢰기 설치공사","ㅇ 154kV 한림정-삼계#2T/L 피뢰기 설치공사 No.34~53호 20기","2017-11-04 07:00","2017-11-05 18:00","2017-11-04 07:00","2017-11-05 18:00","연속",null,null,null,201709060019,"-"]
[376,"부산울산","북부산","주촌삼계#2 T/L","154kV 북부산-미남 등 8개T/L 피뢰기 설치공사","ㅇ 삼계-한림정#2T/L 피뢰기설치관련 안전이격","2017-11-04 07:00","2017-11-05 18:00","2017-11-04 07:00","2017-11-05 18:00","연속",null,null,null,201709060018,"-"]
[377,"부산울산","북부산","삼계어방 T/L","154kV 북부산-미남 등 8개T/L 피뢰기 설치공사","ㅇ 154kV 한림정-삼계#2T/L 피뢰기 설치관련 안전이격","2017-11-04 07:00","2017-11-05 18:00","2017-11-04 07:00","2017-11-05 18:00","연속",null,null,null,201709060020,"-"]
[378,"부산울산","북부산","김해어방 T/L","2017년 북부산 154kV GIS 정밀점검 공사","어방S/S 6333 GIS 정밀점검 시험가압 1H (어방 617)","2017-11-19 15:00","2017-11-19 16:00","2017-11-19 15:00","2017-11-19 16:00","당일",null,null,null,201709070174,"-"]
[379,"부산울산","북부산","김해어방 T/L","2017년 북부산 154kV GIS 정밀점검 공사","어방S/S 6233 GIS 정밀점검 시험가압 1H (어방 617)","2017-11-15 15:00","2017-11-15 16:00","2017-11-15 15:00","2017-11-15 16:00","당일",null,null,null,201709070173,"-"]
[380,"부산울산","북부산","김해어방 T/L","2017년 북부산 154kV GIS 정밀점검 공사","어방S/S 6133 GIS 정밀점검 시험가압 1H (어방 617)","2017-11-09 15:00","2017-11-09 16:00","2017-11-09 15:00","2017-11-09 16:00","당일",null,null,null,201709070172,"-"]
[381,"부산울산","북부산","김해어방 T/L","2017년 북부산 154kV GIS 정밀점검 공사","어방S/S 6433 GIS 정밀점검 시험가압 1H (어방 617)","2017-11-03 15:00","2017-11-03 16:00","2017-11-03 15:00","2017-11-03 16:00","당일",null,null,null,201709070175,"-"]
[382,"부산울산","북부산","엄궁학장#1 T/L","엄궁S/S 170kV 장기사용 GIS 교체공사","엄궁S/S #2DS 및 PT 설치 후 #2BUS 시험가압 24H, #1BUS 최종시험가압 2H (엄궁 617)","2017-11-12 09:00","2017-11-13 11:00","2017-11-12 09:00","2017-11-13 11:00","연속",null,null,null,201709070159,"-"]
[383,"부산울산","북부산","엄궁학장#1 T/L","엄궁S/S 170kV 장기사용 GIS 교체공사","엄궁S/S #1DS 및 CB 설치 후 #1BUS 시험가압 24H (엄궁 617)","2017-11-01 18:00","2017-11-02 18:00","2017-11-01 18:00","2017-11-02 18:00","연속",null,null,null,201709070157,"-"]
[384,"부산울산","북부산","엄궁S/S 154kV #2 BUS","엄궁S/S 170kV 장기사용 GIS 교체공사","엄궁S/S 신)PT&ES, 6100, 6333 Bay #2DS 설치 및 #2BUS 시험가압 24h","2017-11-03 09:00","2017-11-13 09:00","2017-11-03 09:00","2017-11-13 09:00","연속",null,null,null,201709070163,"-"]
[385,"부산울산","북부산","엄궁S/S 154kV #1 BUS","엄궁S/S 170kV 장기사용 GIS 교체공사","엄궁S/S 신)PT&ES, 6100, 6333 Bay #1DS 투입 #1BUS 최종시험가압 2h","2017-11-13 09:00","2017-11-13 11:00","2017-11-13 09:00","2017-11-13 11:00","당일",null,null,null,201709070164,"-"]
[386,"부산울산","북부산","엄궁S/S 154kV #2 BUS","엄궁S/S 170kV 장기사용 GIS 교체공사","엄궁S/S 구)6100 Bay #2DS 철거 후 고깔시공 및 #2BUS 시험가압 1h","2017-11-14 08:00","2017-11-15 18:00","2017-11-14 08:00","2017-11-15 18:00","연속",null,null,null,201709070165,"-"]
[387,"부산울산","북부산","엄궁학장#1 T/L","엄궁S/S 170kV 장기사용 GIS 교체공사","엄궁S/S 구)6100 #1DS,CB 철거 및 고깔시공 후 #1Bus 시험가압 1h (엄궁 617)","2017-11-19 17:00","2017-11-19 18:00","2017-11-19 17:00","2017-11-19 18:00","당일",null,null,null,201709070162,"-"]
[388,"부산울산","북부산","엄궁S/S 154kV #1 BUS","엄궁S/S 170kV 장기사용 GIS 교체공사","엄궁S/S 구)6100 #1DS,CB 철거 후 고깔시공 및 #1BUS 시험가압 1h","2017-11-17 08:00","2017-11-19 18:00","2017-11-17 08:00","2017-11-19 18:00","연속",null,null,null,201709070168,"-"]
[389,"부산울산","북부산","엄궁학장#1 T/L","엄궁S/S 170kV 장기사용 GIS 교체공사","엄궁S/S 구)6100 #2DS 철거 및 고깔시공 후 #2Bus 시험가압 1h (엄궁 617)","2017-11-15 17:00","2017-11-15 18:00","2017-11-15 17:00","2017-11-15 18:00","당일",null,null,null,201709070160,"-"]
[390,"부산울산","북부산","호포매리#1 T/L","원동취수장 전원변경 사업","한국수자원공사 요청 작업 - 154kV 에서 22.9kV 로 전원변경 공사 - 담당자 : 이종석 차장","2017-11-11 09:00","2017-11-11 10:00","2017-11-11 09:00","2017-11-11 10:00","당일",null,null,null,201709080166,"-"]
[391,"부산울산","북부산","호포매리#2 T/L","원동취수장 전원변경 사업","한국수자원공사 요청 작업 - 154kV 에서 22.9kV 로 전원변경 공사 - 담당자 : 이종석 차장","2017-11-11 10:00","2017-11-11 11:00","2017-11-11 10:00","2017-11-11 11:00","당일",null,null,null,201709080167,"-"]
[392,"부산울산","서부산","용원녹공#2 T/L","녹공S/S 154kV 용원-녹공#2T/L(627) GIS 정밀점검","녹공S/S 154kV 용원-녹공#2T/L(627) GIS 정밀점검","2017-11-11 08:00","2017-11-12 18:00","취소","취소","연속",null,null,null,201709080014,"-"]
[393,"부산울산","서부산","용원녹공#1 T/L","녹공S/S 154kV 용원-녹공#1T/L(617) GIS 정밀점검","녹공S/S 154kV 용원-녹공#1T/L(617) GIS 정밀점검","2017-11-04 08:00","2017-11-05 18:00","취소","취소","연속",null,null,null,201709080013,"-"]
[394,"부산울산","울산","동울산방어진 T/L","동울산S/S 154kV Sh.C 설치공사(154kV GIS 설치)","동울산S/S 154kV Sh.C 설치공사-154kV 모선분리에 따른 제어케이블 변경","2017-11-18 14:00","2017-11-18 18:00","2017-11-18 14:00","2017-11-18 18:00","당일",null,null,null,201709080026,"-"]
[395,"부산울산","울산","동울산효문#3 T/L","동울산S/S 154kV Sh.C 설치공사(154kV GIS 설치)","동울산S/S 154kV Sh.C 설치공사-154kV 모선분리에 따른 제어케이블 변경","2017-11-17 14:00","2017-11-17 18:00","2017-11-17 14:00","2017-11-17 18:00","당일",null,null,null,201709080023,"-"]
[396,"부산울산","울산","동울산효문#1 T/L","동울산S/S 154kV Sh.C 설치공사(154kV GIS 설치)","동울산S/S 154kV Sh.C 설치공사-154kV 모선분리에 따른 제어케이블 변경","2017-11-17 09:00","2017-11-17 14:00","2017-11-17 09:00","2017-11-17 14:00","당일",null,null,null,201709080022,"-"]
[397,"부산울산","울산","방어진영남TP#2 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","방어진S/S 154V 빙어진-영남TP#2T/L GIS 초기점검","2017-11-05 09:00","2017-11-05 18:00","2017-11-05 09:00","2017-11-05 18:00","당일",null,null,null,201709060497,"-"]
[398,"부산울산","울산","동울산방어진 T/L","154kV 방어진S/S 현대미포조선T/L GIS 1CCT 증설","154kV 방어진S/S 현대미포조선T/L GIS 1CCT 증설- 시험가압 선로","2017-11-24 14:00","2017-11-25 14:00","2017-11-24 14:00","2017-11-25 14:00","연속",null,null,null,201709090001,"-"]
[399,"부산울산","울산","동울산방어진 T/L","154kV 방어진S/S 현대미포조선T/L GIS 1CCT 증설","154kV 방어진S/S 현대미포조선T/L GIS 1CCT 증설 - 시험가압 선로","2017-11-29 14:00","2017-11-30 14:00","2017-11-29 14:00","2017-11-30 14:00","연속",null,null,null,201709090002,"-"]
[400,"부산울산","울산","신울산명례#2 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV 신울산-명례#2T/L CVT 대체","2017-11-14 09:00","2017-11-14 18:00","2017-11-14 09:00","2017-11-14 18:00","당일",null,null,null,201709060482,"-"]
[401,"부산울산","울산","신울산S/S 154kV #61 BUS","2017년 울산P/O 장기사용 개폐장치 대체공사","신울산S/S 345kV #1M.Tr 2차 GCB(6164) 대체관련 안전이격","2017-11-06 07:00","2017-11-06 18:00","2017-11-06 07:00","2017-11-06 18:00","당일",null,null,null,201709060498,"-"]
[402,"부산울산","울산","신울산언양#1 T/L","154kV 신울산-언양T/L 전선접속개소 전선교체공사","ㅁ 전력선 교체 : 154kV 신울산-언양#1 T/L No.56~64","2017-11-06 07:00","2017-11-08 19:00","2017-11-06 07:00","2017-11-08 19:00","연속",null,null,null,201709060244,"-"]
[403,"부산울산","울산","신울산명례#1 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV 신울산-명례#1T/L CVT 대체","2017-11-13 09:00","2017-11-13 18:00","2017-11-13 09:00","2017-11-13 18:00","당일",null,null,null,201709060481,"-"]
[404,"부산울산","울산","신울산언양#2 T/L","154kV 신울산-언양T/L 전선접속개소 전선교체공사","ㅁ 전력선 교체 : 154kV 신울산-언양#2 T/L No.56~64","2017-11-09 06:00","2017-11-11 19:00","2017-11-09 06:00","2017-11-11 19:00","연속",null,null,null,201708230066,"-"]
[405,"부산울산","울산","신울산영남TP#1 T/L","154kV 두왕분기T/L 건설공사 관련 휴전 (안전이격)","154kV 두왕분기T/L 건설공사 본선로 구성관련 휴전 / 작업구간 : 154kV 신울산-울산#1 TL 4~6호(본작업) / 154kV 신울산-영남TP#1 TL 37~38호(안전이격)","2017-11-22 08:00","2017-11-23 19:00","2017-11-22 08:00","2017-11-23 19:00","매일",null,null,null,201709070044,"-"]
[406,"부산울산","울산","신울산울산#1 T/L","154kV 두왕분기T/L 건설공사 관련 휴전","154kV 두왕분기T/L 건설공사 본선로 구성관련 휴전 / 작업구간 : 154kV 신울산-울산#1 TL 4~6호","2017-11-22 08:00","2017-11-23 19:00","2017-11-22 08:00","2017-11-23 19:00","연속",null,null,"신뢰도개선",201709070037,"○"]
[407,"부산울산","울산","신울산울산#2 T/L","154kV 두왕분기T/L 건설공사 관련 휴전","154kV 두왕분기T/L 건설공사 본선로 구성관련 휴전 / 작업구간 : 154kV 신울산-울산#2 TL 4~6호","2017-11-20 08:00","2017-11-21 19:00","2017-11-20 08:00","2017-11-21 19:00","연속",null,null,"신뢰도개선",201709070035,"-"]
[408,"부산울산","울산","신울산영남TP#2 T/L","154kV 두왕분기T/L 건설공사 관련 휴전 (안전이격)","154kV 두왕분기T/L 건설공사 본선로 구성관련 휴전 / 작업구간 : 154kV 신울산-울산#2 TL 4~6호(본작업) / 154kV 신울산-영남TP#2 TL 37~38호(안전이격)","2017-11-20 08:00","2017-11-21 19:00","2017-11-20 08:00","2017-11-21 19:00","매일",null,null,null,201709070041,"-"]
[409,"부산울산","울산","신울산영남TP#1 T/L","154kV 두왕분기T/L 건설공사 관련 휴전 (안전이격)","154kV 두왕분기T/L 건설공사 본선로 구성관련 휴전 / 작업구간 : 154kV 신울산-울산#2 TL 4~6호(본작업) / 154kV 신울산-영남TP#1 TL 37~38호(안전이격)","2017-11-20 08:00","2017-11-21 19:00","2017-11-20 08:00","2017-11-21 19:00","매일",null,null,null,201709070040,"-"]
[410,"부산울산","울산","언양산막#2 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","언양S/S 170kV 언양-산막#2T/L GIS 개폐타임 측정","2017-11-03 14:00","2017-11-03 18:00","2017-11-03 14:00","2017-11-03 18:00","당일",null,null,null,201709060480,"-"]
[411,"부산울산","울산","언양산막#1 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","언양S/S 170kV 언양-산막#1T/L GIS 개폐타임 측정","2017-11-03 09:00","2017-11-03 14:00","2017-11-03 09:00","2017-11-03 14:00","당일",null,null,null,201709060479,"-"]
[412,"부산울산","울산","울산울산TP#2 T/L","울산T/P 170kV 6883 GIS 철거공사","울산T/P 170kV 6883 GIS 철거관련 가공지선 철거 안전이격","2017-11-02 14:00","2017-11-02 18:00","2017-11-02 14:00","2017-11-02 18:00","당일",null,null,null,201709060488,"-"]
[413,"부산울산","울산","울산T/P 154kV #66 BUS","울산T/P 170kV 6883 GIS 철거공사","울산T/P 170kV 6883 GIS 철거","2017-11-03 08:00","2017-11-07 18:00","2017-11-03 08:00","2017-11-07 18:00","연속",null,null,null,201709060486,"○"]
[414,"부산울산","울산","울산울산TP#2 T/L","울산T/P 170kV 6883 GIS 철거공사","울산T/P 170kV 6883 GIS 철거관련 #66BUS 시험가압","2017-11-06 18:00","2017-11-07 18:00","2017-11-06 18:00","2017-11-07 18:00","연속",null,null,null,201709060491,"-"]
[415,"부산울산","울산","울산울산TP#2 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","울산S/S 170kV 6232DS GIS 내부점검","2017-11-01 17:00","2017-11-01 18:00","2017-11-01 17:00","2017-11-01 18:00","당일",null,null,null,201709060491,"-"]
[416,"부산울산","울산","울산T/P 154kV #61 BUS","울산T/P 170kV 6883 GIS 철거공사","울산T/P 170kV 6883 GIS 철거","2017-11-08 08:00","2017-11-12 18:00","2017-11-08 08:00","2017-11-12 18:00","연속",null,null,null,201709180080,"-"]
[417,"부산울산","울산","울산울산TP#1 T/L","울산T/P 170kV 6883 GIS 철거공사","울산T/P 170kV 6883 GIS 철거관련 #61BUS 시험가압","2017-11-11 18:00","2017-11-12 18:00","2017-11-11 18:00","2017-11-12 18:00","연속",null,null,null,201709060492,"○"]
[418,"부산울산","울산","울산울산TP#1 T/L","2016~2017년도 울산전력지사 송전정비 협력회사 총액공사","노후애자금구류 교체","2017-11-17 09:00","2017-11-17 18:00","2017-11-17 09:00","2017-11-17 18:00","당일",null,null,null,201709110268,"○"]
[419,"부산울산","울산","울산T/P 1,2,3 SU Tr #2 1차 CB","울산T/P 170kV 6883 GIS 철거공사","울산T/P 170kV 6883 GIS 철거","2017-11-02 09:00","2017-11-12 18:00","2017-11-02 09:00","2017-11-12 18:00","연속",null,null,null,201709060485,"-"]
[420,"부산울산","울산","용연울산TP#3 T/L","울산T/P 170kV 6883 GIS 철거공사","울산T/P 170kV 6883 GIS 철거관련 가공지선 철거 안전이격","2017-11-02 09:00","2017-11-02 13:00","2017-11-02 09:00","2017-11-02 13:00","당일",null,null,null,201709060490,"-"]
[421,"부산울산","울산","효문방어진 T/L","2017년 울산P/O 장기사용 개폐장치 대체공사","효문S/S 25.8kV #1-1,1-2,2-2Sh.C용 VCB 대체관련 안전이격","2017-11-14 07:00","2017-11-14 18:00","2017-11-14 07:00","2017-11-14 18:00","당일",null,null,null,201709060500,"-"]
[422,"부산울산","직할","양정범천 T/L","2017년 직할 변전협력회사 총액공사","범천S/S 양정-범천T/L(637) GIS 노후 보조계전기 교체","2017-11-21 10:00","2017-11-22 18:00","2017-11-21 10:00","2017-11-22 18:00","연속",null,null,null,201709080328,"-"]
[423,"부산울산","직할","부민부산 T/L","부민S/S 부민-부산T/L GIS 하자점검","부민S/S 부민-부산T/L GIS 하자점검","2017-11-01 10:00","2017-11-01 18:00","2017-11-01 10:00","2017-11-01 18:00","당일",null,null,null,201709110004,"-"]
[424,"부산울산","직할","미남서면#2 T/L","154kV 미남-서면T/L 3~4호 안전이격 확보공사","154kV 미남-서면T/L No.2~4호 전선교체","2017-11-29 08:00","2017-12-05 18:00","취소","취소","연속",null,null,null,201709060110,"-"]
[425,"부산울산","직할","미남서면#1 T/L","154kV 미남-서면T/L 3~4호 안전이격 확보공사","154kV 미남-서면T/L No.2~4호 전선교체","2017-11-29 08:00","2017-12-05 18:00","취소","취소","연속",null,null,null,201709060109,"-"]
[426,"경남","직할","삼정완암#2 T/L","154kV 천선분기T/L 천선개폐소 인출입 가선공사","154kV 삼정-완암#2 T/L 2-4호, 2-5호 ~ 154kV 천선개폐소 구간 전력선 가선 작업","2017-11-30 08:00","2017-12-08 19:00","2017-11-30 08:00","2017-12-08 19:00","연속",null,null,null,201709070023,"-"]
[427,"경남","직할","삼정완암#1 T/L","154kV 천선분기T/L 천선개폐소 인출입 가선공사","154kV 삼정-완암#1 T/L 2-4호, 2-5호 ~ 154kV 천선개폐소 구간 전력선 가선 작업","2017-11-19 08:00","2017-11-27 19:00","2017-11-19 08:00","2017-11-27 19:00","연속",null,null,null,201709070019,"-"]
[428,"경남","직할","안민진해#2 T/L","154kV 천선분기T/L 천선개폐소 인출입 가선공사","154kV 안민-진해#2 T/L 2-4호, 2-5호 ~ 154kV 천선개폐소 구간 전력선 가선 작업","2017-11-30 08:00","2017-12-08 19:00","2017-11-30 08:00","2017-12-08 19:00","연속",null,null,null,201709070024,"-"]
[429,"경남","직할","안민진해#1 T/L","154kV 천선분기T/L 천선개폐소 인출입 가선공사","154kV 안민-진해#1 T/L 2-4호, 2-5호 ~ 154kV 천선개폐소 구간 전력선 가선 작업","2017-11-19 08:00","2017-11-27 19:00","2017-11-19 08:00","2017-11-27 19:00","연속",null,null,null,201709070022,"-"]
[430,"경남","직할","차룡창공#1 T/L","2016~17년 경남지역본부 직할 송전협력회사 총액공사","송전선로용 피뢰기 설치(4~8호)","2017-11-04 07:00","2017-11-04 18:00","2017-11-04 07:00","2017-11-04 18:00","당일",null,null,null,201709060403,"-"]
[431,"경남","직할","차룡창공#2 T/L","창공S/S 차룡-창공#2T/L CB (627) 초기점검","창공S/S 차룡-창공#2T/L CB (627) 초기점검 ※병행 : 차룡S/S 차룡-창공#2T/L CB (627) 보통점검","2017-11-11 09:30","2017-11-11 17:30","2017-11-11 09:30","2017-11-11 17:30","당일",null,null,null,201709050143,"-"]
[432,"경남","진주","사천개양#1 T/L","154kV 쌍림-합천 등 10개T/L 피뢰기설치공사(사천-개양T/L)","154kV 사천-개양T/L 피뢰기 설치공사(동시휴전)","2017-11-04 07:00","2017-11-04 18:00","2017-11-04 07:00","2017-11-04 18:00","매일",null,null,null,201709070087,"-"]
[433,"경남","진주","하동개양#1 T/L","154kV 하동-개양T/L 지장송전선로 지중화공사","154kV 하동-개양#1T/L 지장송전선로 지중화공사 (케이블 철거, 포설 및 접속, GIS챔버 철거 및 설치, C/H 설치)","2017-11-08 08:00","2017-11-19 18:00","취소","취소","연속",null,null,null,201709040150,"-"]
[434,"경남","진주","사천개양#2 T/L","154kV 쌍림-합천 등 10개T/L 피뢰기설치공사(사천-개양T/L)","154kV 사천-개양T/L 피뢰기 설치공사(동시휴전)","2017-11-04 07:00","2017-11-04 18:00","2017-11-04 07:00","2017-11-04 18:00","매일",null,null,null,201709070088,"-"]
[435,"경남","진주","하동개양#2 T/L","154kV 하동-개양T/L 지장송전선로 지중화공사","154kV 하동-개양#2T/L 지장송전선로 지중화공사 (케이블 철거, 포설 및 접속, GIS챔버 철거 및 설치, C/H 설치)","2017-11-18 07:00","2017-11-30 18:00","취소","취소","연속",null,null,null,201709040152,"-"]
[436,"경남","진주","함양거창#2 T/L","154kV 쌍림-합천 등 10개T/L 피뢰기설치공사(함양-거창T/L)","154kV 함양-거창#2T/L 피뢰기 설치공사","2017-11-11 07:00","2017-11-12 18:00","2017-11-11 07:00","2017-11-12 18:00","매일",null,null,null,201709070080,"-"]
[437,"경남","진주","의령동진주#1 T/L","154kV 쌍림-합천 등 10개T/L 피뢰기설치공사(의령-동진주T/L)","154kV 의령-동진주#1T/L 피뢰기 설치공사","2017-11-25 07:00","2017-11-26 18:00","2017-11-25 07:00","2017-11-26 18:00","매일",null,null,null,201709210017,"-"]
[438,"경남","진주","동진주S/S 154KV BUS TIE CB","154kV 동진주S/S #3M.Tr 증설공사","154kV 동진주S/S #3M.Tr 증설공사 : 6332DS 무부하 시험가압","2017-11-22 15:00","2017-11-23 15:00","2017-11-22 15:00","2017-11-23 15:00","연속",null,null,null,201709200152,"○"]
[439,"경남","진주","의령동진주#1 T/L","154kV 쌍림-합천 등 10개T/L 피뢰기설치공사(의령-동진주T/L)","154kV 의령-동진주#1T/L 피뢰기 설치공사","2017-11-11 07:00","2017-11-12 18:00","2017-11-11 07:00","2017-11-12 18:00","매일",null,null,null,201709070078,"-"]
[440,"경남","진주","동진주S/S 154KV BUS TIE CB","154kV 동진주S/S #3M.Tr 증설공사","154kV 동진주S/S #3M.Tr 증설공사 : 6331DS 무부하 시험가압","2017-11-09 15:00","2017-11-10 15:00","2017-11-09 15:00","2017-11-10 15:00","연속",null,null,null,201709200149,"○"]
[441,"경남","진주","가야사봉 T/L","154kV 송전선로 보호반 성능개선","154kV 송전선로 보호반 성능개선 - 가야-사봉T/L 보호반 - 병행작업: 가양S/S 가야-사봉T/L CB 장기미동작 점검 (함안전력 김민준)","2017-11-11 09:30","2017-11-11 13:30","2017-11-11 09:30","2017-11-11 13:30","당일",null,null,null,201709270210,"-"]
[442,"경남","진주","삼천포사천#1 T/L","사천S/S 삼천포-사천#1T/L PNL 대체","사천S/S 삼천포-사천#1T/L PNL 대체 -병행작업: 사천S/S 삼천포-사천#1T/L PT보통점검(이승현) 삼천포S/S 삼천포-사천#1T/L PNL 대체(통영전력 권동욱)","2017-11-29 09:30","2017-12-03 13:00","2017-11-29 09:30","2017-12-03 13:00","연속",null,null,null,201707310044,"-"]
[443,"경남","진주","진주개양#2 T/L","154kV 쌍림-합천 등 10개T/L 피뢰기설치공사(진주-개양T/L)","154kV 진주-개양#2T/L 피뢰기 설치공사","2017-11-05 07:00","2017-11-05 18:00","2017-11-05 07:00","2017-11-05 18:00","매일",null,null,null,201709070075,"-"]
[444,"경남","진주","동진주진주#1 T/L","154kV 쌍림-합천 등 10개T/L 피뢰기설치공사(동진주-진주T/L)","154kV 동진주-진주#1T/L 피뢰기 설치공사","2017-11-04 07:00","2017-11-04 18:00","2017-11-04 07:00","2017-11-04 18:00","매일",null,null,null,201709070074,"-"]
[445,"경남","진주","광양하동#1 T/L","154kV 쌍림-합천 등 10개T/L 피뢰기설치공사(광양-하동#1T/L)","154kV 광양-하동#1T/L 피뢰기 설치공사","2017-11-06 07:00","2017-11-07 18:00","2017-11-06 07:00","2017-11-07 18:00","매일",null,null,null,201709070077,"-"]
[446,"경남","진주","쌍림합천#2 T/L","154kV 쌍림-합천 등 10개T/L 피뢰기설치공사(쌍림-합천T/L)","154kV 쌍림-합천#2T/L 피뢰기 설치공사","2017-11-04 07:00","2017-11-05 18:00","2017-11-04 07:00","2017-11-05 18:00","매일",null,null,null,201709070079,"-"]
[447,"경남","통영","통영거제#2 T/L","거제S/S 154kV 통영-거제#2T/L 휴전(시험가압)","거제S/S 154kV #2Sh.C GIS 정밀점검관련(시험가압용)","2017-11-11 17:30","2017-11-11 18:30","2017-11-11 17:30","2017-11-11 18:30","당일",null,null,null,201709060270,"-"]
[448,"경남","통영","신고성삼천포#1 T/L","삼천포S/S 154kV 신고성-삼천포#1T/L 장기미동작 CB점검","삼천포S/S 154kV 신고성-삼천포#1T/L 장기미동작 CB점검","2017-11-06 09:30","2017-11-06 14:00","2017-11-06 09:30","2017-11-06 14:00","당일",null,null,null,201709060119,"-"]
[449,"경남","통영","신고성삼천포#2 T/L","삼천포S/S 154kV 신고성-삼천포#2T/L 장기미동작 CB점검","삼천포S/S 154kV 신고성-삼천포#2T/L 장기미동작 CB점검","2017-11-06 14:00","2017-11-06 18:30","2017-11-06 14:00","2017-11-06 18:30","당일",null,null,null,201709060118,"-"]
[450,"경남","통영","고성통영 T/L","통영S/S 154kV 고성-통영T/L 장기미동작 CB점검","통영S/S 154kV 고성-통영T/L 장기미동작 CB점검","2017-11-26 14:00","2017-11-26 18:30","2017-11-26 14:00","2017-11-26 18:30","당일",null,null,null,201709060257,"-"]
[451,"경남","통영","통영거제#2 T/L","154kV 통영-거제#2T/L 정밀점검","154kV 통영-거제#2T/L 송전선로 정밀점검 (병행)통영,거제S/S 통영-거제#2T/L 장기미동작 CB점검(변전)","2017-11-04 08:00","2017-11-05 18:00","2017-11-04 08:00","2017-11-05 18:00","매일",null,null,null,201709070255,"-"]
[452,"경남","통영","신고성통영 T/L","통영S/S 154kV 신고성-통영T/L 장기미동작 CB점검","통영S/S 154kV 신고성-통영T/L 장기미동작 CB점검","2017-11-26 09:30","2017-11-26 14:00","2017-11-26 09:30","2017-11-26 14:00","당일",null,null,null,201709060256,"-"]
[453,"경남","함안","중리가야#1 T/L","가야S/S 중리-가야#1T/L 보호배전반 대체","가야S/S 중리-가야#1T/L 보호배전반 대체 가야S/S 중리-가야#1T/L 170kV GIS보통점검, PT,LA 보통점검 중리S/S 중리-가야#1T/L 보호배전반 대체","2017-11-18 09:30","2017-11-19 17:30","2017-11-18 09:30","2017-11-19 17:30","연속",null,null,null,201709070241,"-"]
[454,"경남","함안","신마산마산#1 T/L","154kV 신마산-마산#1T/L 피뢰기 교체공사","154kV 신마산-마산#1T/L 피뢰기 교체공사(자기제→폴리머)","2017-11-26 08:00","2017-11-26 13:00","2017-11-26 08:00","2017-11-26 13:00","당일",null,null,null,201709040162,"-"]
[455,"경남","함안","신마산마산#2 T/L","154kV 신마산-마산#2T/L 피뢰기 교체공사","154kV 신마산-마산#2T/L 피뢰기 교체공사(자기제→폴리머)","2017-11-26 13:00","2017-11-26 18:00","2017-11-26 13:00","2017-11-26 18:00","당일",null,null,null,201709040165,"-"]
[456,"경남","함안","중리가야#2 T/L","154kV 중리가야T/L 정밀점검","154kV 중리가야T/L 정밀점검","2017-11-18 08:30","2017-11-19 18:00","2017-11-18 08:30","2017-11-19 18:00","매일",null,null,null,201709060149,"-"]
[457,"경남","함안","진영한림정#1 T/L","154kV 진영-한림정T/L 4호 지장송전선로 이설공사","- 지장송전선로 이설공사 : 가선로 구성 1기, 교체 1기","2017-11-25 07:00","2017-11-26 17:00","2017-11-25 07:00","2017-11-26 17:00","연속",null,null,null,201709070177,"-"]
[458,"경남","함안","진영한림정#2 T/L","154kV 진영-한림정T/L 4호 지장송전선로 이설공사","- 지장송전선로 이설공사 : 가선로 구성 1기, 교체 1기","2017-11-18 07:00","2017-11-19 17:00","2017-11-18 07:00","2017-11-19 17:00","연속",null,null,null,201709070176,"-"]
[459,"경남","함안","창녕구지#2 T/L","154kV 창녕-구지#2T/L 피뢰기 설치공사","ㅇ송전선로용 피뢰기 설치 - 창녕-구지#2T/L 42~81호","2017-11-05 09:00","2017-11-19 12:00","2017-11-05 09:00","2017-11-19 12:00","연속",null,null,null,201709060341,"-"]
[460,"경북","영주","봉화평해 T/L","345kV 신영주-한울NP2 T/L 전선접속개소 전력선교체공사","345kV 신영주-한울NP2T/L 공사관련 하단 안전확보","2017-11-28 10:00","2017-12-02 18:00","2017-11-28 10:00","2017-12-02 18:00","매일",{"$nulls":4},"-"]
[461,"경북","영주","봉화울진 T/L","345kV 신영주-한울NP2 T/L 전선접속개소 전력선교체공사","345kV 신영주-한울NP2T/L 공사관련 하단 안전확보","2017-11-28 10:00","2017-12-02 18:00","2017-11-28 10:00","2017-12-02 18:00","매일",{"$nulls":4},"-"]
[462,"경북","영주","봉화평해 T/L","345kV 신영주-한울NP2 T/L 전선접속개소 전력선교체공사","345kV 신영주-한울NP2T/L 공사관련 하단 안전확보","2017-11-13 10:00","2017-11-17 18:00","2017-11-13 10:00","2017-11-17 18:00","매일",{"$nulls":4},"-"]
[463,"경북","영주","봉화울진 T/L","345kV 신영주-한울NP2 T/L 전선접속개소 전력선교체공사","345kV 신영주-한울NP2T/L 공사관련 하단 안전확보","2017-11-13 10:00","2017-11-17 18:00","2017-11-13 10:00","2017-11-17 18:00","매일",{"$nulls":4},"-"]

{"sheet":"한수원","index":3,"n_rows":7,"n_cols":20,"rows_kept":7,"cut":false,"hidden":false,"merged":[[0,0,0,6],[4,12,5,12],[4,0,5,0],[4,1,5,1],[4,2,5,2],[4,3,5,3],[4,4,5,4],[4,5,5,5],[4,6,4,7],[4,8,4,9],[4,10,5,10],[4,11,5,11],[4,19,5,19],[4,13,5,13],[4,14,5,14],[4,15,5,15],[4,16,5,16],[4,17,5,17],[4,18,5,18]]}
["2017년도 11월 휴전계획표(한국수력원자력)"]
[]
[]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"한울본부","한울1발","한울#2 주변압기","한울2호기 21차 계획예방정비\n#2 MTR/UAT 점검\n* 조작차단기 : CB 7400, 7472","○ MTR/UAT 일반점검 등","2017-11-13T09:00:00","2017-12-04T18:00:00","2017-11-13T09:00:00","2017-12-04T18:00:00","연속","Y"]