{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["765송부","345송부","154송부","한수원"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":10,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":7,"n_cols":16,"rows_kept":7,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"\"2018년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2018년도 1월 휴전계획서"}]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"부산울산","동부산","북경남신고리NP#2 T/L","신고리원자력 발전기차단 SPS 회로구성","1. 신고리원자력 발전기차단 SPS 회로구성 2. [병행]8300 GIS 보통점검","2018-02-26 09:30","2018-03-02 17:00","2018-02-26 09:30","2018-03-02 17:00",null,"연속",null,null,201712110204]
[2,"부산울산","동부산","북경남신고리NP#1 T/L","신고리원자력 발전기차단 SPS 회로구성","1. 신고리원자력 발전기차단 SPS 회로구성 2. [병행]8200 GIS 보통점검","2018-02-19 09:30","2018-02-23 17:00","2018-02-19 09:30","2018-02-23 17:00",null,"연속",null,null,201712110203]
[3,"부산울산","동부산","신고리S/S #4GEN T/L CB","신고리S/S 8372 GIS 보통점검","신고리S/S 8372 GIS 보통점검","2018-02-26 09:30","2018-03-02 17:00","2018-02-26 09:30","2018-03-02 17:00",null,"연속",null,null,201712180020]

{"sheet":"345송부","index":1,"n_rows":66,"n_cols":16,"rows_kept":66,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"\"2018년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2018년도 1월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"인천","김포","가정인천CC# - 가정신부평#3 TIE GIS","가정인천CC#2 - 가정신부평#3 TIE GIS 성능개선 공사(7200)","1. Puffercylinder 강도 보강 2. 투입저항 접촉부 변경(구 → 평면) 3. 차단기 특성시험","2018-02-19 09:00","2018-02-23 18:00","2018-02-19 09:00","2018-02-23 18:00","연속",null,null,null,201712050003]
[2,"인천","김포","가정개폐소 345KV #1Sh.R - TIE GIS","가정 345KV #1Sh.R - TIE GIS(7600) 성능개선 공사","1. Puffercylinder 강도 보강 2. 투입저항 접촉부 변경(구 → 평면) 3. 차단기 특성시험","2018-02-05 09:00","2018-02-09 18:00","2018-02-05 09:00","2018-02-09 18:00","연속",null,null,null,201712050002]
[3,"인천","시흥","영흥T/P #3 M.Tr(G.T) 1차 CB (7472)","영흥S/Y 7400 CB C상 CT 교체공사","영흥S/Y 7400 CB C상 CT 교체공사","2018-02-21 08:00","2018-02-21 20:00","취소","취소","당일",null,null,null,201712180017]
[4,"인천","시흥","신시흥영흥TP#2 T/L","영흥S/Y 7400 CB C상 CT 교체공사","영흥S/Y 7400 CB C상 CT 교체공사","2018-02-21 08:00","2018-02-23 18:00","취소","취소","연속",null,null,null,201712180016]
[5,"인천","인천","서인천C/C 345kV #70 BUS","345kV 서인천C/C 모선용CLR 설치 및 용량부족 GIS 대체공사","- 345kV 서인천C/C 모선측 CLR용 GIS 설치(#70BUS) - 345kV 서인천C/C 용량부족 GIS 대체(#70BUS 모선개조)","2018-02-22 10:00","2018-03-08 17:00","2018-02-22 10:00","2018-03-08 17:00","연속",null,null,null,201712120097]
[6,"인천","인천","포스코파워S/Y 포스코SY-인천CC#1T/L CB (7171)","LS제 362kV 차단기 유사고장방지 하자처리공사(포스코S/Y 7171)","포스코S/Y 7171 차단기 내부 성능 개선(puffer cylinder 교체 등)","2018-02-26 09:00","2018-03-04 18:00","2018-02-26 09:00","2018-03-04 18:00","연속",null,null,null,201712120090]
[7,"경기북부","직할","양주S/S 345kV #6 Sh.R","양주S/S 362kV Sh.R용 1차 GIS 공장반입 구조개선 공사","362kV #6Sh.R용 1차 GIS 공장반입 구조개선 작업","2018-02-26 09:00","2018-04-15 18:00","2018-02-26 09:00","2018-04-15 18:00","연속",null,null,null,201712120083]
[8,"경기북부","파주","신파주양주#2 T/L","345kV 신파주-양주#2T/L 전선교체공사","No.20-22 하단(4가닥) 전선교체","2018-02-15 06:30","2018-02-18 18:00","2018-02-15 06:30","2018-02-18 18:00","연속",null,null,null,201712150067]
[9,"강원","태백","신태백한울NP2#1 T/L","○ 항공장애주간표시구 설치공사","○ 항공장애주간표시구 설치공사","2018-02-05 09:00","2018-02-06 18:00","2018-02-05 09:00","2018-02-06 18:00","매일",null,null,null,201712070171]
[10,"강원","태백","신태백한울NP2#2 T/L","○ 항공장애주간표시구 설치공사","○ 항공장애주간표시구 설치공사","2018-02-07 09:00","2018-02-08 18:00","2018-02-07 09:00","2018-02-08 18:00","매일",null,null,null,201712180048]
[11,"충북","직할","신제천S/S #3 M.Tr A","주변압기 기계적보호장치 회로보완 및 3차 PT 점검","주변압기 기계적보호장치 회로보완 및 3차 PT 점검","2018-02-27 09:00","2018-02-28 18:00","2018-02-27 09:00","2018-02-28 18:00","당일",null,null,null,201712140002]
[12,"충북","직할","신제천동해#2 T/L","7A09-2ES 조작함 하자보수","7A09-2ES 조작불량 제작사 하자보수","2018-02-27 10:00","2018-02-27 18:00","2018-02-27 10:00","2018-02-27 18:00","당일",null,null,null,201712050025]
[13,"충북","직할","STATCOM M.Tr 1차 - TIE GIS","신충주S/S STATCOM 설치공사","345kV STATCOM 가압","2018-02-27 14:00","2018-02-28 14:00","2018-02-27 14:00","2018-02-28 14:00","당일",null,null,null,201711090144]
[14,"충북","직할","STATCOM M.Tr 1차 GIS","신충주S/S STATCOM 설치공사","345kV STATCOM 가압","2018-02-27 14:00","2018-02-28 14:00","2018-02-27 14:00","2018-02-28 14:00","당일",null,null,null,201711090143]
[15,"충북","청주","청원S/S 청원-신진천#2T/L-#1 M.Tr 1차 CB (7200)","청원S/S 345kV 장기사용 GIS 대체공사(전문)","○ 345kV GIS(가스절연개폐장치) 철거, 설치 × 1식 - GIS(40kA 4000A) 철거 × 6CB - GIS(50kA 4000A) 설치 × 6CB ○ 설치 GIS 기초 보강공사 × 1식 ○ 제어케이블 철거, 설치 및 기타 부대공사 × 1식","2018-02-26 09:00","2018-05-06 18:00","2018-03-05 09:00","2018-05-13 18:00","연속",null,null,null,201712110126]
[16,"충북","청주","청원S/S #1 M.Tr A","청원S/S 345kV 장기사용 GIS 대체공사(전문)","○ 345kV GIS(가스절연개폐장치) 철거, 설치 × 1식 - GIS(40kA 4000A) 철거 × 6CB - GIS(50kA 4000A) 설치 × 6CB ○ 설치 GIS 기초 보강공사 × 1식 ○ 제어케이블 철거, 설치 및 기타 부대공사 × 1식","2018-02-26 09:00","2018-05-06 18:00","2018-03-05 09:00","2018-05-13 18:00","연속",null,null,null,201712110125]
[17,"충북","충주","청원신진천#2 T/L","345kV 신진천S/S 용량부족 GIS 대체공사","345kV #72BAY 3CB 철거 345kV #72BAY 3CB 기초보강 345kV #72BAY 3CB 신설","2018-02-26 10:00","2018-07-20 18:00","2018-03-05 10:00","2018-07-27 18:00","연속",null,null,null,201712150040]
[18,"충북","충주","신진천S/S #1 M.Tr A","345kV 신진천S/S 용량부족 GIS 대체공사","345kV #72BAY 3CB 철거 345kV #72BAY 3CB 기초보강 345kV #72BAY 3CB 신설","2018-02-26 10:00","2018-07-20 18:00","2018-03-05 10:00","2018-07-27 18:00","연속",null,null,null,201712150041]
[19,"대전충남","세종","신옥천세종#1 T/L","[변전] YPP제 계전기 성능개선","○ L90계전기 성능개선 ○ 대충본(계통)-11811(17.11.10) 관련(첨부)","2018-02-28 09:00","2018-02-28 18:00","2018-02-28 09:00","2018-02-28 18:00","당일",null,null,null,201712190022]
[20,"대전충남","세종","세종청원#2 T/L","[변전] YPP제 계전기 성능개선","○ L90계전기 성능개선 ○ 대충본(계통)-11811(17.11.10) 관련(첨부)","2018-02-27 09:00","2018-02-27 18:00","2018-02-27 09:00","2018-02-27 18:00","당일",null,null,null,201712190021]
[21,"대전충남","세종","세종청원#1 T/L","[변전] YPP제 계전기 성능개선","○ L90계전기 성능개선 ○ 대충본(계통)-11811(17.11.10) 관련(첨부)","2018-02-26 09:00","2018-02-26 18:00","2018-02-26 09:00","2018-02-26 18:00","당일",null,null,null,201712190020]
[22,"대전충남","세종","신옥천세종#2 T/L","[변전] YPP제 계전기 성능개선","○ L90계전기 성능개선 ○ 대충본(계통)-11811(17.11.10) 관련(첨부)","2018-02-23 09:00","2018-02-23 18:00","2018-02-23 09:00","2018-02-23 18:00","당일",null,null,null,201712190023]
[23,"대전충남","아산","아산S/S #2 M.Tr A","아산S/S 345kV #2M.Tr 부싱 긴급점검","○ 345kV #1M.Tr 부싱 긴급점검 - 부싱 절연열화 측정 - 부싱 절연유 채유","2018-02-05 09:00","2018-02-09 18:00","2018-02-05 09:00","2018-02-09 18:00","당일",null,null,null,201712180062]
[24,"대전충남","청양","보령T/P 청양-보령#1T/L CB (7672)","345kV차단기 부동작 예방조작시험","-7672CB","2018-02-27 09:00","2018-02-27 12:00","2018-02-27 09:00","2018-02-27 12:00","당일",null,null,null,201712260025]
[25,"대전충남","청양","보령T/P 아산-보령화력#2T/L CB (7571)","345kV차단기 부동작 예방조작시험","-7571CB","2018-02-28 13:00","2018-02-28 18:00","2018-02-28 13:00","2018-02-28 18:00","당일",null,null,null,201712260027]
[26,"대전충남","청양","보령T/P 청양-보령화력#1TL-#6 M.Tr 1차 CB (7600)","345kV차단기 부동작 예방조작시험","-7600CB","2018-02-27 13:00","2018-02-27 18:00","2018-02-27 13:00","2018-02-27 18:00","당일",null,null,null,201712260024]
[27,"대전충남","청양","보령T/P 아산-보령화력#2T/L-#5M.Tr1차 CB (7500)","345kV차단기 부동작 예방조작시험","-7500CB","2018-02-28 09:00","2018-02-28 12:00","2018-02-28 09:00","2018-02-28 12:00","당일",null,null,null,201712260026]
[28,"대전충남","청양","청양S/S 청양-군산#1T/L CB (7472)","345kV차단기 부동작 예방조작시험","-7472CB","2018-02-23 09:00","2018-02-23 12:00","2018-02-23 09:00","2018-02-23 12:00","당일",null,null,null,201712260022]
[29,"대전충남","청양","청양S/S 신옥천-청양T/L-청양-군산#1T/L CB (7400)","345kV차단기 부동작 예방조작시험","-7400CB","2018-02-22 13:00","2018-02-22 18:00","2018-02-22 13:00","2018-02-22 18:00","당일",null,null,null,201712260021]
[30,"대전충남","청양","청양S/S 신옥천-청양T/L CB (7471)","345kV차단기 부동작 예방조작시험","-7471CB","2018-02-22 09:00","2018-02-22 12:00","2018-02-22 09:00","2018-02-22 12:00","당일",null,null,null,201712260019]
[31,"대전충남","청양","청양S/S 청양-신온양#1T/L CB (7371)","345kV차단기 부동작 예방조작시험","-7371CB","2018-02-23 13:00","2018-02-23 18:00","2018-02-23 13:00","2018-02-23 18:00","당일",null,null,null,201712260023]
[32,"광주전남","강진","신강진S/S #1 M.Tr A","345kV 신강진S/S #1M.Tr(신강진S/S 취약설비 GIS화공사)","변압기 인출 재정비","2018-02-24 09:00","2018-02-25 18:00","2018-02-24 09:00","2018-02-25 18:00","연속",null,null,null,201712130002]
[33,"광주전남","강진","신강진광양#2 T/L","345kV 신강진-광양#2T/L(피뢰기 설치공사)","345kV 신강진-광양#2T/L(피뢰기 설치공사) - 345kV 신화순-신강진 등 10개T/L 송전선로용 피뢰기 설치공사","2018-02-28 07:00","2018-03-13 18:00","2018-02-28 07:00","2018-03-13 18:00","매일",null,null,null,201709050065]
[34,"광주전남","강진","신강진S/S #3 M.Tr A","345kV 신강진S/S #3M.Tr(신강진S/S 취약설비 GIS화공사)","변압기 인출 재정비","2018-02-10 07:00","2018-02-11 18:00","2018-02-10 07:00","2018-02-11 18:00","연속",null,null,null,201712200026]
[35,"광주전남","강진","신강진S/S #2 M.Tr A","345kV 신강진S/S #2M.Tr(신강진S/S 취약설비 GIS화공사)","변압기 인출 재정비","2018-02-03 07:00","2018-02-04 18:00","2018-02-03 07:00","2018-02-04 18:00","연속",null,null,null,201712200025]
[36,"광주전남","순천","광양S/S 345kV #76 BUS","광양S/S 345kV #76 BUS(7A00 차단기 시험가압)","7A00 차단기 내부 균압콘덴서 교체공사 시험가압","2018-02-27 15:00","2018-02-27 18:00","2018-02-27 15:00","2018-02-27 18:00","당일",null,null,null,201712220033]
[37,"광주전남","순천","신남원광양#2 T/L","345kV 주변압기 정밀점검공사","광양S/S 345kV #1M.Tr 정밀점검 및 C상 1차 부싱교체후 시험가압","2018-02-07 18:00","2018-02-08 18:00","2018-02-07 18:00","2018-02-08 18:00","연속",null,null,"신뢰도 개선",201712200032]
[38,"광주전남","순천","신강진광양#1 T/L","345kV 신강진-광양#1 T/L(7A00 차단기 시험가압)","7A00 차단기 내부 균압콘덴서 교체공사 시험가압","2018-02-27 15:00","2018-02-27 18:00","2018-02-27 15:00","2018-02-27 18:00","당일",null,null,null,201712220032]
[39,"대구","포항","신포항S/S 예비M.Tr CB","신포항S/S 예비M.Tr NGK제 부싱 내진보강","신포항S/S 예비M.Tr NGK제 부싱 내진보강","2018-02-28 09:00","2018-02-28 18:00","2018-02-28 09:00","2018-02-28 18:00","당일",null,null,null,201712190035]
[40,"대구","포항","신포항S/S #1 M.Tr A","신포항S/S #1 M.Tr NGK제 부싱 내진보강","신포항S/S #1 M.Tr NGK제 부싱 내진보강","2018-02-28 09:00","2018-02-28 18:00","2018-02-28 09:00","2018-02-28 18:00","당일",null,null,null,201712080104]
[41,"대구","포항","신포항S/S #3 M.Tr A","신포항S/S #3 M.Tr 보통점검","신포항S/S #3 M.Tr 보통점검","2018-02-26 09:00","2018-02-27 18:00","2018-02-26 09:00","2018-02-27 18:00","연속",null,null,null,201712080105]
[42,"대구","포항","월성2N/P F2-#4 SS Tr 1차 CB (7800)","월성2N/P F2-#4 SS Tr 1차 7800 CB 보통점검","월성2N/P F2-#4 SS Tr 1차 7800 CB 보통점검","2018-02-07 09:00","2018-02-07 18:00","2018-02-07 09:00","2018-02-08 18:00","당일",null,null,null,201712080100]
[43,"대구","포항","동울산월성NP#1 T/L","YPP송전선로보호반 성능개선","YPP송전선로보호반 성능개선","2018-02-01 09:00","2018-02-01 18:00","2018-02-01 09:00","2018-02-01 18:00","당일",null,null,null,201712200015]
[44,"대구","포항","월성2N/P 월성연락#2T/L CB (7871)","월성2N/P 월성연락#2T/L 7871 CB 보통점검","월성2N/P 월성연락#2T/L 7871 CB 보통점검","2018-02-09 09:00","2018-02-09 18:00","2018-02-09 09:00","2018-02-09 18:00","당일",null,null,null,201712080102]
[45,"대구","포항","월성2N/P #4 SS Tr 1차 CB (7872)","월성2N/P #4 SS Tr 1차 7872 CB 보통점검","월성2N/P #4 SS Tr 1차 7872 CB 보통점검","2018-02-08 09:00","2018-02-08 18:00","2018-02-08 09:00","2018-02-08 18:00","당일",null,null,null,201712080101]
[46,"경북","구미","선산S/S #4 M.Tr A","선산S/S 154kV 옥외철구 설비 GIS화 공사","#4M.Tr 2차 GIS 부싱 조립관련 안전이격 확보","2018-02-02 13:00","2018-02-02 18:00","2018-02-02 13:00","2018-02-02 18:00","당일",null,null,null,201712210063]
[47,"경북","구미","선산S/S #3 M.Tr A","선산S/S 154kV 옥외철구 설비 GIS화 공사","#3M.Tr 2차 GIS 부싱 조립관련 안전이격 확보","2018-02-02 09:00","2018-02-02 12:00","2018-02-02 09:00","2018-02-02 12:00","당일",null,null,null,201712210062]
[48,"경북","구미","선산S/S #2 M.Tr A","선산S/S 154kV 옥외철구 설비 GIS화 공사","#2M.Tr 2차 GIS 부싱 조립관련 안전이격 확보","2018-02-01 13:00","2018-02-01 18:00","2018-02-01 13:00","2018-02-01 18:00","당일",null,null,null,201712210061]
[49,"경북","구미","선산S/S #1 M.Tr A","선산S/S 154kV 옥외철구 설비 GIS화 공사","#1M.Tr 2차 GIS 부싱 조립관련 안전이격 확보","2018-02-01 09:00","2018-02-01 12:00","2018-02-01 09:00","2018-02-01 12:00","당일",null,null,null,201712210060]
[50,"경북","영주","신영주S/S STATCOM 1차 GIS","신영주S/S STATCOM 감시카메라 설치","신영주S/S STATCOM Valve Romm 감시카메라 설치","2018-02-26 09:00","2018-02-28 18:00","2018-02-26 09:00","2018-02-28 18:00","연속",null,null,null,201712180025]
[51,"부산울산","북부산","북부산S/S 345kV #70 BUS","345kV 북부산S/S 차단기용량대체공사","모선연결(78-76BAY 연결구간)","2018-02-26 08:00","2018-03-06 15:00","2018-02-26 08:00","2018-03-06 15:00","연속",null,null,null,201712060077]
[52,"부산울산","북부산","북부산S/S #1 M.Tr A","345kV 북부산S/S 차단기용량대체공사","#1M.Tr 인출변경(구. 76BAY → 신설 GIS 74BAY)","2018-02-28 08:00","2018-03-16 15:00","2018-02-28 08:00","2018-03-16 15:00","연속",null,null,null,201712060081]
[53,"부산울산","서부산","신녹산S/S #3 M.Tr A","신녹산S/S #3M.Tr 하자점검","신녹산S/S #3M.Tr 하자점검 [병행]#3M.Tr 1,2차 GIS 하자점검, #3S.Tr GIS 하자점검","2018-02-26 10:00","2018-03-01 18:00","2018-02-26 10:00","2018-03-01 18:00","연속",null,null,null,201712070008]
[54,"부산울산","울산","동울산신울산#1 T/L","345kV 동울산-신울산#1T/L 이도조정(하자보수)","345kV 동울산-신울산#1T/LNo.61~63 이도조정","2018-02-28 08:00","2018-03-01 18:00","취소","취소","연속",null,null,null,201712110012]
[55,"부산울산","울산","동울산신울산#2 T/L","345kV 동울산-신울산#2T/L 이도조정(하자보수)","345kV 동울산-신울산#2T/LNo.61~63 이도조정","2018-02-26 08:00","2018-02-27 18:00","취소","취소","연속",null,null,null,201712110013]
[56,"부산울산","울산","신울산S/S 신온산-동울산#2T/L TIE CB (7900)","345kV LS제 GIS 유사고장방지 공사","신울산S/S 345kV 7900 345kV LS제 GIS 유사고장방지 작업","2018-02-26 09:00","2018-03-04 18:00","2018-02-26 09:00","2018-03-04 18:00","연속",null,null,null,201712070179]
[57,"부산울산","울산","울주S/S #3 M.Tr A","2018-19년 울산전력지사 변전협력회사 총액공사","1.울주S/S 345kV #3M.Tr 보호반 대체 2.울주S/S 345kV #3M.Tr 부싱 보강작업","2018-02-26 09:00","2018-03-01 18:00","2018-02-26 09:00","2018-03-01 18:00","연속",null,null,null,201712070183]
[58,"경남","통영","신고성S/S #1 M.Tr A","345kV 구내 전력구공사","ㅇ 345kV 구내 전력구공사 - 개착식 전력구 : 324m","2018-02-19 09:00","2018-02-28 18:00","2018-02-19 09:00","2018-02-28 18:00","연속",null,null,"신뢰도 개선",201712070169]
[59,"경남","함안","신마산S/S #4 M.Tr A","신마산S/S #4M.Tr 1차 (7871) 조작시험","신마산S/S #4M.Tr 1차 (7871) 조작시험 및 2차(6444)하자점검","2018-02-27 09:30","2018-02-27 17:30","2018-02-27 09:30","2018-02-27 17:30","당일",null,null,null,201712070191]
[60,"경남","함안","신마산S/S 의령-신마산#2T/L CB (7571)","신마산S/S 의령-신마산#2T/L(7571) 조작시험","신마산S/S 의령-신마산#2T/L(7571) 조작시험","2018-02-28 09:30","2018-02-28 13:30","2018-02-28 09:30","2018-02-28 13:30","당일",null,null,null,201712070199]
[61,"경남","함안","신마산S/S #3 M.Tr A","345kV 신마산S/S 용량부족차단기 대체공사","#3M.Tr 1차측 전력구 시공관련 안전이격거리 확보차","2018-02-06 09:00","2018-02-18 18:00","2018-02-06 09:00","2018-02-18 18:00","연속",null,null,"신뢰도 개선",201712200029]
[62,"경남","함안","신마산S/S 신마산-신김해#1T/L CB (7471)","신마산S/S 신마산-심김해#1T/L(7471) GCB 조작시험","신마산S/S 신마산-심김해#1T/L(7471) GCB 개폐타임 측정","2018-02-26 09:30","2018-02-26 13:30","2018-02-26 09:30","2018-02-26 13:30","당일",null,null,null,201712070190]

{"sheet":"154송부","index":2,"n_rows":84,"n_cols":16,"rows_kept":84,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"\"2018년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2018년도 1월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","녹번옥인 T/L","154kV 옥인 및 운니S/S 인출T/L 교체공사","1. 사 업 명 : 154kV 옥인 및 운니S/S 인출T/L 교체공사 2. 사업목적 : 옥인 및 운니변전소 화재 및 대형 재난사고 예방 3. 사업개요 ○ 사업구간 : 옥인S/S ∼ 옥인인출전력구, 운니S/S 운니인출전력구 ○ 사업내용 - 철거 : 154kV OF 2000㎟ 4C, OF 1200㎟ 4C 총길이1.4㎞ - 신설 : 154kV XL","2018-02-20 09:10","2018-04-06 18:00","2018-02-26 09:00","2018-04-13 18:00","연속",null,null,null,201712010053]
[2,"인천","시흥","도림오봉 T/L","도림S/S 170kV 도림오봉 T/L GIS 보통점검","도림S/S 170kV 도림오봉 T/L GIS 보통점검","2018-02-26 09:00","2018-02-26 14:00","취소","취소","당일",null,null,null,201712170017]
[3,"인천","시흥","도림S/S 154kV #1 BUS TIE GIS","도림S/S 170kV #1 BUS TIE GIS 보통점검","도림S/S 170kV #1 BUS TIE GIS 보통점검","2018-02-26 14:00","2018-02-26 18:00","취소","취소","당일",null,null,null,201712170018]
[4,"인천","시흥","북시화서시화#2 T/L","북시화S/S 170kV 북시화서시화#2 T/L GIS CB 동작시험","북시화S/S 170kV 북시화서시화#2 T/L GIS CB 동작시험","2018-02-27 11:00","2018-02-27 15:00","2018-02-27 11:00","2018-02-27 15:00","당일",null,null,null,201712170022]
[5,"인천","시흥","북시화서시화#1 T/L","북시화S/S 170kV 북시화서시화#1 T/L GIS CB 동작시험","북시화S/S 170kV 북시화서시화#1 T/L GIS CB 동작시험","2018-02-27 09:00","2018-02-27 11:00","2018-02-27 09:00","2018-02-27 11:00","당일",null,null,null,201712170021]
[6,"인천","시흥","소래S/S 154kV #1 BUS TIE GIS","소래S/S 154kV #1 BUS TIE GIS CB 동작시험","소래S/S 154kV #1 BUS TIE GIS CB 동작시험","2018-02-26 09:00","2018-02-26 11:00","2018-02-26 09:00","2018-02-26 11:00","당일",null,null,null,201712170014]
[7,"인천","시흥","신시흥#1S/S 154kV #2 BUS TIE GIS","신시흥#1S/S 154kV #2 BUS TIE GIS 대체공사(6200)","신시흥#1S/S 154kV #2 BUS TIE GIS 대체공사(6200)","2018-02-10 09:00","2018-02-21 18:00","2018-02-10 09:00","2018-02-21 18:00","연속",null,null,null,201712170005]
[8,"인천","시흥","신시흥남동#2 T/L","신시흥#1S/S 154kV #2BUS TIE GIS 대체공사","신시흥#1S/S 154kV #2BUS TIE GIS 대체공사","2018-02-10 09:00","2018-02-10 18:00","2018-02-10 09:00","2018-02-10 18:00","당일",null,null,null,201712170004]
[9,"인천","시흥","신시흥남동#2 T/L","신시흥#1S/S 154kV #2BUS TIE GIS 대체공사","신시흥#1S/S 154kV #2BUS TIE GIS 대체공사","2018-02-15 09:00","2018-02-15 18:00","2018-02-15 09:00","2018-02-15 18:00","당일",null,null,null,201712170007]
[10,"인천","시흥","신시흥#1S/S 154kV #66 BUS","신시흥#1S/S 154kV #2 BUS TIE GIS 대체공사","신시흥#1S/S 154kV #2 BUS TIE GIS 대체공사","2018-02-17 09:00","2018-02-21 09:00","2018-02-17 09:00","2018-02-21 09:00","연속",null,null,null,201712170009]
[11,"인천","시흥","신시흥#1S/S 154kV #65 BUS","신시흥#1S/S 154kV #2 BUS TIE GIS 대체공사","신시흥#1S/S 154kV #2 BUS TIE GIS 대체공사","2018-02-20 09:00","2018-02-21 09:00","2018-02-20 09:00","2018-02-21 09:00","연속",null,null,null,201712170012]
[12,"인천","시흥","신시흥남동#2 T/L","신시흥#1S/S 154kV #2BUS TIE GIS 대체공사","신시흥#1S/S 154kV #2BUS TIE GIS 대체공사","2018-02-18 09:00","2018-02-18 18:00","2018-02-18 09:00","2018-02-18 18:00","당일",null,null,null,201712170011]
[13,"인천","시흥","신시흥#1S/S 154kV #66 BUS","신시흥#1S/S 154kV #2 BUS TIE GIS 대체공사(6200)","신시흥#1S/S 154kV #2 BUS TIE GIS 대체공사(6200)","2018-02-10 09:00","2018-02-11 09:00","2018-02-10 09:00","2018-02-11 09:00","연속",null,null,null,201712170002]
[14,"인천","시흥","신시흥#1S/S 154kV #61 BUS","신시흥#1S/S 154kV #2 BUS TIE GIS 대체공사","신시흥#1S/S 154kV #2 BUS TIE GIS 대체공사","2018-02-11 09:00","2018-02-17 09:00","2018-02-11 09:00","2018-02-17 09:00","연속",null,null,null,201712170006]
[15,"인천","시흥","신시흥#1S/S 154kV #60 BUS","신시흥#1S/S 154kV #2 BUS TIE GIS 대체공사","신시흥#1S/S 154kV #2 BUS TIE GIS 대체공사","2018-02-16 09:00","2018-02-17 09:00","2018-02-16 09:00","2018-02-17 09:00","연속",null,null,null,201712170008]
[16,"인천","시흥","신시흥#1S/S 154kV #61 BUS","신시흥#1S/S 154kV #2 BUS TIE GIS 대체공사","신시흥#1S/S 154kV #2 BUS TIE GIS 대체공사","2018-02-21 09:00","2018-02-21 18:00","2018-02-21 09:00","2018-02-21 18:00","당일",null,null,null,201712170013]
[17,"인천","시흥","신시흥남동#2 T/L","신시흥#1S/S 154kV #2BUS TIE GIS 대체공사","신시흥#1S/S 154kV #2BUS TIE GIS 대체공사","2018-02-17 09:00","2018-02-17 18:00","2018-02-17 09:00","2018-02-17 18:00","당일",null,null,null,201712170010]
[18,"인천","인천","관교S/S 154kV #1 BUS TIE GIS","관교S/S 6100 BUS TIE GIS 조작시험","관교S/S 6100 BUS TIE GIS 조작시험","2018-02-03 09:30","2018-02-03 14:00","2018-02-03 09:30","2018-02-03 14:00","당일",null,null,null,201712130060]
[19,"인천","인천","남인천학익#2 T/L","남인천S/S 남인천학익#2T/L GIS 조작시험","남인천S/S 남인천학익#2T/L GIS 조작시험","2018-02-04 14:00","2018-02-04 18:00","취소","취소","당일",null,null,null,201712130076]
[20,"인천","인천","남인천학익#1 T/L","남인천S/S 남인천학익#1T/L GIS 조작시험","남인천S/S 남인천학익#1T/L GIS 조작시험","2018-02-04 09:30","2018-02-04 14:00","취소","취소","당일",null,null,null,201712130075]
[21,"인천","인천","남인천S/S 154kV #1 BUS TIE GIS","남인천S/S 6100 부스타이 GIS 조작시험","남인천S/S 6100 부스타이 GIS 조작시험","2018-02-05 09:30","2018-02-05 14:00","2018-02-05 09:30","2018-02-05 14:00","당일",null,null,null,201712130074]
[22,"인천","인천","계양원창 T/L","원창S/S 계양원창T/L GIS 조작시험","원창S/S 계양원창T/L GIS 조작시험","2018-02-07 13:30","2018-02-07 17:30","취소","취소","당일",null,null,null,201712130062]
[23,"인천","인천","인천S/S 154kV #1 BUS TIE GIS","인천S/S 6100 BUS TIE GIS 조작시험","인천S/S 6100 BUS TIE GIS 조작시험","2018-02-27 09:00","2018-02-27 14:00","2018-02-27 09:00","2018-02-27 14:00","당일",null,null,null,201712140079]
[24,"인천","인천","신가좌주안#2 T/L","주안S/S 신가좌주안#2T/L GIS 보통점검 및 보조계전기 교체공사","주안S/S 신가좌주안#2T/L GIS 보통점검 및 보조계전기 교체공사","2018-02-28 09:00","2018-02-28 18:00","취소","취소","당일",null,null,"신뢰도개선",201712140076]
[25,"인천","인천","신가좌주안#1 T/L","주안S/S 신가좌주안#1T/L GIS 보통점검 및 보조계전기 교체공사","주안S/S 신가좌주안#1T/L GIS 보통점검 및 보조계전기 교체공사","2018-02-24 09:00","2018-02-24 18:00","취소","취소","당일",null,null,"신뢰도개선",201712140075]
[26,"인천","인천","주안관교#2 T/L","주안S/S 주안관교#2T/L GIS 보통점검 및 보조계전기 교체","주안S/S 주안관교#2T/L GIS 보통점검 및 보조계전기 교체 - 관교S/S 주안관교#2T/L GIS 조작시험","2018-02-23 09:00","2018-02-23 18:00","취소","취소","당일",null,null,null,201712130064]
[27,"인천","인천","주안관교#1 T/L","주안S/S 주안관교#1T/L GIS 보통점검 및 보조계전기 교체공사","주안S/S 주안관교#1T/L GIS 보통점검 및 보조계전기 교체공사 - 관교S/S 주안관교#1T/L GIS 조작시험","2018-02-22 09:00","2018-02-22 18:00","취소","취소","당일",null,null,null,201712130063]
[28,"인천","인천","학익연수#2 T/L","학익S/S 학익연수#2T/L 에어링 밸브 보수 공사","학익S/S 학익연수#2T/L 에어링 밸브 보수 공사","2018-02-06 09:30","2018-02-06 16:00","2018-02-06 09:30","2018-02-06 16:00","당일",null,null,null,201712130059]
[29,"경기북부","구리","별내진접 T/L","일진제 PMJ 중간접속함 교체공사","154kV 별내-진접T/L J/B#1~J/B#3 총 9상","2018-02-19 09:00","2018-02-26 18:00","2018-02-27 09:00","2018-03-06 18:00","연속",null,null,"한전요청",201712130028]
[30,"경기북부","직할","금오상계#1 T/L","경기북부직할 170kV GIS 정밀점검공사","금오-상계#1T/L GIS 정밀점검","2018-02-19 09:00","2018-02-20 18:00","2018-03-19 09:00","2018-03-20 18:00","연속",null,null,null,201712120076]
[31,"경기북부","직할","백석덕계#2 T/L","경기북부직할 170kV GIS 정밀점검","백석덕계#2 T/L GIS 정밀점검","2018-02-05 09:00","2018-02-08 18:00","2018-03-12 09:00","2018-03-15 18:00","연속",null,null,null,201712120080]
[32,"경기북부","직할","녹양백석#2 T/L","경기북부직할 170kV GIS 정밀점검공사","녹양-백석#2T/L GIS 정밀점검","2018-02-01 09:00","2018-02-02 18:00","2018-03-08 09:00","2018-03-09 18:00","연속",null,null,null,201712120077]
[33,"경기북부","직할","녹양백석#1 T/L","154kV 남면, 백석S/S SW 증설공사","○ 154kV 남면, 백석S/S SW 증설공사 최초가압","2018-02-12 14:00","2018-02-13 15:00","2018-02-10 14:00","2018-02-11 15:00","연속",null,null,null,201712140032]
[34,"경기북부","파주","신덕은원흥#1 T/L","345kV 신파주-양주#2T/L 전선교체공사 안전확보","345kV 신파주-양주#2T/L No.20-22 하단 4가닥 전선교체 하부횡단 154kV 신덕은-원흥#1T/L 휴전필수","2018-02-15 06:30","2018-02-18 18:00","2018-02-24 06:30","2018-02-24 18:00","연속",null,null,null,201712150068]
[35,"경기북부","파주","신덕은원흥#2 T/L","345kV 신파주-양주#2T/L 전선교체공사 안전확보","345kV 신파주-양주#2T/L No.20-22 하단 4가닥 전선교체 하부횡단 154kV 신덕은-원흥#2T/L 휴전필수","2018-02-15 06:30","2018-02-18 18:00","2018-02-24 06:30","2018-02-24 18:00","연속",null,null,null,201712150069]
[36,"강원","동해","울진삼척GP#1 T/L","○ 항공장애주간표시구 설치공사","○ 항공장애주간표시구 설치공사","2018-02-02 09:00","2018-02-03 18:00","2018-02-02 09:00","2018-02-03 18:00","매일",null,null,null,201712070173]
[37,"강원","태백","고한영월 T/L","○ 항공장애주간표시구 설치공사","○ 항공장애주간표시구 설치공사","2018-02-01 09:00","2018-02-01 18:00","2018-02-01 09:00","2018-02-01 18:00","매일",null,null,null,201712070170]
[38,"충북","직할","신제천제천#2 T/L","154kV 신제천-제천T/L 안전이격확보공사","철탑계탑 (No.27.6, 27.9)","2018-02-24 08:00","2018-03-05 18:00","2018-02-24 08:00","2018-02-25 18:00","연속",null,null,"신뢰도개선",201712200047]
[39,"충북","직할","신제천제천#1 T/L","154kV 신제천-제천T/L 안전이격확보공사","철탑계탑 (No.27.6, 27.9)","2018-02-24 08:00","2018-03-05 18:00","2018-02-26 08:00","2018-03-06 18:00","연속",null,null,"신뢰도개선",201712200046]
[40,"대전충남","대전","남대전신흥#1 T/L","남대전S/S 남대전-신흥#1T/L 장기미동작 차단기 조작시험","남대전S/S 남대전-신흥#1T/L 장기미동작 차단기 조작시험","2018-02-26 09:00","2018-02-26 12:00","2018-02-26 09:00","2018-02-26 12:00","당일",null,null,null,201712120072]
[41,"대전충남","대전","남대전신흥#2 T/L","남대전S/S 남대전-신흥#2T/L 장기미동작 차단기 조작시험","남대전S/S 남대전-신흥#2T/L 장기미동작 차단기 조작시험","2018-02-26 13:00","2018-02-26 15:00","2018-02-26 13:00","2018-02-26 15:00","당일",null,null,null,201712120073]
[42,"대전충남","대전","남대전신흥#3 T/L","남대전S/S 남대전-신흥#2T/L 장기미동작 차단기 조작시험","남대전S/S 남대전-신흥#2T/L 장기미동작 차단기 조작시험","2018-02-26 15:00","2018-02-26 17:00","2018-02-26 15:00","2018-02-26 17:00","당일",null,null,null,201712120074]
[43,"전북","김제","백산김제#1 T/L","154kV 백산-김제T/L 선종교체공사","작업내용 : No.21 본탑에서 #1 가탑이동(임시선로구성)","2018-02-28 08:00","2018-03-01 18:00","취소","취소","연속",null,null,"신뢰도개선",201712200044]
[44,"전북","김제","김제섬진강HP T/L","154kV 김제변전소 GIS 설치공사","- 170kV GIS(50KA 2000A) × 2CCT 설치","2018-02-24 10:00","2018-02-25 10:00","취소","취소","연속",null,null,"신뢰도개선",201712180089]
[45,"전북","김제","백산김제#2 T/L","154kV 백산-김제T/L 선종교체공사","작업내용 : No.21호 본탑에서 #2 가탑이동(임시선로구성)","2018-02-26 08:00","2018-02-27 18:00","취소","취소","연속",null,null,"신뢰도개선",201712200042]
[62,"광주전남","직할","나주금천#1 T/L","나주-금천#1T/L","2018년 직할 변전협력회사 총액공사 나주-금천#1T/L CB 장기미동작 차단기 개폐시험","2018-02-03 09:00","2018-02-03 13:00","2018-02-03 09:00","2018-02-03 13:00","당일",null,null,null,201712130037]
[61,"광주전남","직할","나주금천#2 T/L","나주-금천#2T/L","2018년 직할 변전협력회사 총액공사 나주-금천#2T/L CB 장기미동작 차단기 개폐시험","2018-02-03 13:00","2018-02-03 18:00","2018-02-03 13:00","2018-02-03 18:00","당일",null,null,null,201712110104]
[55,"광주전남","광주","담양일곡#1 T/L","154kV 담양-일곡T/L 안전이격확보공사","철탑교체 : 11기 (No.174, 186~189, 199, 200, 216, 220, 223, 224) 애자련 변경 : 1기 (No. 222)","2018-02-19 09:00","2018-02-20 18:00","취소","취소","연속",null,null,"신뢰도개선",201712110105]
[47,"광주전남","강진","해남C/S #1 C.Tr 1차 CB","154kV 해남C/S #4M.Tr 증설공사","170kV GIS 설치","2018-02-20 04:00","2018-02-20 05:00","2018-02-20 04:00","2018-02-20 05:00","당일",null,null,null,201712110107]
[48,"광주전남","강진","해남C/S #2 C.Tr 1차 CB(신규)","154kV 해남C/S #4M.Tr 증설공사","170kV GIS 설치","2018-02-20 04:00","2018-02-20 05:00","2018-02-20 04:00","2018-02-20 05:00","당일",null,null,null,201712110113]
[49,"광주전남","강진","해남C/S 154kV #1 BUS(신규) CB","154kV 해남C/S #4M.Tr 증설공사","#4M.Tr용 1차 170kV GIS 설치 #4M.Tr용 모선보호반 Bay 증설","2018-02-20 04:30","2018-02-25 04:30","2018-02-20 04:30","2018-02-25 04:30","연속",null,null,null,201712110114]
[59,"광주전남","순천","승주서순천 T/L","154kV 승주-서순천T/L 안전이격확보공사","154kV 승주-서순천T/L 안전이격확보공사 -철탑교체 10기, 전선교체 10.132C-km","2018-02-20 07:00","2018-02-21 18:00","취소","취소","당일",null,null,"신뢰도개선",201712110117]
[57,"광주전남","순천","승주서순천 T/L","154kV 승주-서순천 T/L(#2M.Tr 개조공사)","승주S/S 154kV #2M.Tr 개조공사","2018-02-20 14:00","2018-02-21 14:00","취소","취소","당일",null,null,"신뢰도개선",201712110118]
[58,"광주전남","순천","승주S/S 154kV #2 BUS","승주S/S 154kV #2 BUS(#2M.Tr 개조공사)","승주S/S 154kV #2M.Tr 개조공사","2018-02-20 14:00","2018-02-21 14:00","취소","취소","당일",null,null,"신뢰도개선",201712110112]
[56,"광주전남","광주","담양일곡#2 T/L","154kV 담양-일곡T/L 안전이격확보공사","철탑교체 : 11기 (No.174, 186~189, 199, 200, 216, 220, 223, 224) 애자련 변경 : 1기 (No. 222)","2018-02-21 09:00","2018-03-02 18:00","취소","취소","연속",null,null,"신뢰도개선",201712080118]
[60,"광주전남","순천","승주주암HP T/L","154kV 승주-서순천T/L 안전이격확보공사","154kV 승주-서순천T/L 안전이격확보공사 -철탑교체 10기, 전선교체 10.132C-km","2018-02-22 07:00","2018-03-02 13:00","취소","취소","당일",null,null,"신뢰도개선",201712080119]
[54,"광주전남","강진","남창해남CS#2 T/L","154kV 해남C/S #4M.Tr 증설공사","170kV GIS 설치","2018-02-24 04:30","2018-02-25 04:30","2018-02-24 04:30","2018-02-25 04:30","연속",null,null,null,201712130038]
[46,"광주전남","강진","신강진대불#2 T/L","154kV 신강진-대불#2T/L(변압기 2차측 인출정비)","-#1M.Tr 인출변경시 활선근접으로 휴전","2018-02-24 09:00","2018-02-24 18:00","2018-02-24 09:00","2018-02-24 18:00","당일",null,null,null,201712130040]
[50,"광주전남","강진","해남C/S #1 C.Tr 1차 CB","154kV 해남C/S #4M.Tr 증설공사","170kV GIS 설치","2018-02-25 04:00","2018-02-25 05:00","2018-02-25 04:00","2018-02-25 05:00","당일",null,null,null,201712280011]
[51,"광주전남","강진","해남C/S #2 C.Tr 1차 CB(신규)","154kV 해남C/S #4M.Tr 증설공사","170kV GIS 설치","2018-02-25 04:00","2018-02-25 05:00","2018-02-25 04:00","2018-02-25 05:00","당일",null,null,null,201712280013]
[52,"광주전남","강진","해남C/S 154kV #2 BUS(신규) CB","154kV 해남C/S #4M.Tr 증설공사","170kV GIS 설치","2018-02-25 04:30","2018-03-01 04:30","2018-02-25 04:30","2018-03-01 04:30","연속",null,null,null,201712190044]
[53,"광주전남","강진","남창해남CS#2 T/L","154kV 해남C/S #4M.Tr 증설공사","170kV GIS 설치","2018-02-28 04:30","2018-03-01 04:30","2018-02-28 04:30","2018-03-01 04:30","연속",null,null,null,201712190043]
[63,"대구","칠곡","북대구구암#2 T/L","154kV 북대구-구암T/L No.25~32 안전이격확보공사","○ 철탑철거 : 8기, 설치 : 6기 ○ 전력선교체 : 2.411 c-km(330 ㎟ S)","2018-02-26 08:00","2018-03-07 18:00","2018-02-26 08:00","2018-03-07 18:00","연속",null,null,null,201712130005]
[64,"대구","포항","상정양북 T/L","154kV 영일-양북T/L 안전이격거리확보공사","No.55~69 철탑 신설 8기 철탑 철거 12기","2018-02-26 08:00","2018-03-20 18:00","2018-02-26 08:00","2018-03-20 18:00","연속",null,null,null,201712110020]
[65,"대구","포항","영일입실 T/L","154kV 영일-양북T/L 안전이격거리확보공사","No.55~69 철탑 신설 8기 철탑 철거 12기","2018-02-26 08:00","2018-03-20 18:00","2018-02-26 08:00","2018-03-20 18:00","연속",null,null,null,201712110019]
[66,"경북","영주","문경단양 T/L","154kV 단양T/L OPGW 교체공사(No. 73 ~ 78)","OPGW 70SQ SM-24C 1.9km 교체","2018-02-07 09:00","2018-02-09 18:00","취소","취소","연속",null,null,"신뢰도개선",201712060042]
[67,"경북","직할","울진평해 T/L","154kV 울진 현종산 풍력발전단지 송전선로 건설공사","분기철탑 검설(기설 No.104 철거 및 신설 No.14 조립, 전력선 가선)","2018-02-02 09:00","2018-02-08 18:00","2018-02-02 09:00","2018-02-08 18:00","연속",null,null,null,201712200019]
[68,"경북","직할","봉화평해 T/L","154kV 울진 현종산 풍력발전단지 송전선로 건설공사","전력선 이설 및 긴선압축, 가선로 구성","2018-02-09 07:00","2018-02-14 18:00","2018-02-09 07:00","2018-02-14 18:00","연속",null,null,null,201712200023]
[69,"경북","직할","봉화평해 T/L","154kV 울진 현종산 풍력발전단지 송전선로 건설공사","전력선 신설 및 이설, 우회 가선로 구성, 가철탑 철거","2018-02-01 07:00","2018-02-01 18:00","2018-02-01 07:00","2018-02-01 18:00","당일",null,null,null,201712200018]
[70,"부산울산","서부산","신녹산용원#1 T/L","신녹산S/S 신녹산-용원#1T/L(617) 보통점검","신녹산S/S 신녹산-용원#1T/L(617) 보통점검","2018-02-26 10:00","2018-02-26 18:00","2018-02-26 10:00","2018-02-26 18:00","당일",null,null,null,201712070011]
[71,"부산울산","울산","방어진영남TP#2 T/L","154kV 현대미포조선T/L 공급계통 변경공사","154kV 방어진-영남T/L 6호 철거 및 신설 담당자 : 현대미포조선 류한진 과장(052-250-3645)","2018-02-26 08:00","2018-03-05 17:00","2018-02-26 08:00","2018-03-05 17:00","연속",null,null,null,201712150048]
[72,"부산울산","울산","방어진영남TP#1 T/L","154kV 현대미포조선T/L 공급계통 변경공사","154kV 방어진-영남#1T/L 이설(6호-&gt가철탑) 담당자 : 현대미포조선 류한진 과장(052-250-3645)","2018-02-24 08:00","2018-02-25 17:00","2018-02-24 08:00","2018-02-25 17:00","연속",null,null,null,201712150047]
[73,"부산울산","울산","신온산온산#2 T/L","2018-19년 울산전력지사 변전협력회사 총액공사","신온산S/S 154kV 신온산-온산#2T/L 612DS 가스누기보수","2018-02-26 09:00","2018-02-28 18:00","2018-02-26 09:00","2018-02-28 18:00","연속",null,null,null,201712070182]
[74,"경남","직할","창공월림#2 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2018-02-15 09:00","2018-02-17 17:00","2018-02-15 09:00","2018-02-17 17:00","연속",null,null,null,201711250006]
[75,"경남","직할","창공월림#1 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2018-02-15 07:00","2018-02-25 18:00","2018-02-15 07:00","2018-02-25 18:00","연속",null,null,null,201711250007]
[76,"경남","직할","창공완암#1 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2018-02-04 08:00","2018-02-11 17:00","2018-02-04 08:00","2018-02-11 17:00","연속",null,null,null,201711250002]
[77,"경남","직할","창공완암#2 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2018-02-19 07:00","2018-02-25 18:00","2018-02-19 07:00","2018-02-25 18:00","연속",null,null,null,201711250008]
[78,"경남","직할","창공월림#2 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2018-02-02 07:00","2018-02-11 18:00","2018-02-02 07:00","2018-02-11 18:00","연속",null,null,null,201711250001]
[79,"경남","통영","삼천포사천#1 T/L","154kV 삼천포-사천T/L 접속개소 전선교체공사","154kV 삼천포-사천T/L 20~21,22~25, 34~39, 51~53, 53~55호 구간 접속개소 전선교체공사","2018-02-24 07:00","2018-03-04 18:00","2018-02-24 07:00","2018-03-04 18:00","연속",null,null,null,201712050137]
[80,"충북","직할","신제천제천#2 T/L","154kV 신제천-제천T/L 안전이격확보공사","철탑계탑 (No.27.6, 27.9)","2018-02-24 08:00","2018-03-05 18:00","2018-03-07 08:00","2018-03-08 18:00","연속",null,null,"신뢰도개선"]

{"sheet":"한수원","index":3,"n_rows":18,"n_cols":20,"rows_kept":18,"cut":false,"hidden":false,"merged":[[0,0,0,6],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4],[3,5,4,5],[3,6,3,7],[3,19,4,19],[8,0,9,0],[8,1,9,1],[8,2,9,2],[8,3,9,3],[8,4,9,4],[3,8,3,9],[3,10,4,10],[3,11,4,11],[3,12,4,12],[3,13,4,13],[3,14,4,14],[8,12,9,12],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,18,4,18],[8,5,9,5],[8,6,8,7],[8,8,8,9],[8,10,9,10],[8,11,9,11],[8,19,9,19],[14,0,14,1],[15,0,16,0],[15,1,16,1],[15,2,16,2],[15,3,16,3],[15,4,16,4],[15,5,16,5],[15,6,15,7],[15,8,15,9],[8,13,9,13],[8,14,9,14],[8,15,9,15],[8,16,9,16],[8,17,9,17],[8,18,9,18],[15,16,16,16],[15,17,16,17],[15,18,16,18],[15,19,16,19],[15,10,16,10],[15,11,16,11],[15,12,16,12],[15,13,16,13],[15,14,16,14],[15,15,16,15]]}
["2018년도 02월 휴전계획표(한국수력원자력)"]
[]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"고리본부","3발전소","신#2 주변압기","신고리2호기 4차 O/H 중 주변압기 \n점검\n* 조작차단기 : CB 8100, 8171","○ 전력용변압기 일반점검 및 구내 선\n    로점검, 보호계전기 시험 등","2018-02-09 10:00","2018-02-23 18:00","2018-02-09 10:00","2018-02-23 18:00","연속","Y"]
[]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"한울본부","2발전소","#3 주변압기","한울3호기 14차 O/H 중 소내전원\n절체 시험\n* 조작차단기 : CB 7900, 7972","○ 소내전원 절체시험\n  - 절체시험 후 개방차단기 재투입","2018-02-22T18:00:00","2018-02-22T21:00:00","2018-02-22T18:00:00","2018-02-22T21:00:00","연속","Y"]
[2,"한울본부","3발전소","#5 대기보조변압기","한울5호기 10차 O/H 중 대기보조\n변압기 교체 작업\n* 조작차단기 : CB 7E00, 7E72","○ 대기보조변압기 02N 교체","2018-02-24T10:00:00","2018-03-16T23:00:00","2018-02-24T10:00:00","2018-03-16T23:00:00","연속","Y"]
[3,"한빛본부","2발전소","#4 기동용변압기\n  (03XN)","한빛4호기 14차 O/H 중 소내전원\n절체 시험\n* 조작차단기 : CB 7800, 7871","○ 소내전원 절체시험\n  - 절체시험 후 개방차단기 재투입","2018-02-01T10:00:00","2018-03-17T23:00:00","2018-02-01T10:00:00","2018-03-17T23:00:00","연속","Y"]
[]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"고리본부","3발전소","신#2 대기보조변압기","신고리2호기 2차 O/H 중 대기보조 \n변압기 일반점검\n* 조작차단기 : CB 6200, 6272","○ 대기보조변압기/차단기 일반점검 ","2018-02-24 10:00","2018-03-02 18:00","2018-02-24 10:00","2018-03-02 18:00","연속","Y"]