{"text_format":"2","workbook":"xlsx","n_sheets":5,"sheets":["765송부","345송부","154송부","한수원","중부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":19,"n_cols":16,"rows_kept":19,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2018년도 4월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S 765kV #2 BUS","#2BUS DS 정밀점검(8452DS)","#2BUS DS 정밀점검 - #3M.Tr 8452DS","2018-04-16 09:00","2018-04-30 18:00","2018-04-16 09:00","2018-04-30 18:00","연속",null,null,null,201801120054]
[2,"경기북부","구리","신안성신가평 T/L","765kV Trench제 부싱 상태 확인","765kV Trench제 부싱 부식 의심개소(드론기촬영) 육안점검","2018-04-10 09:00","2018-04-10 18:00","2018-04-10 09:00","2018-04-10 18:00","당일",null,null,null,201802200091]
[3,"경기북부","구리","신가평S/S #3 M.Tr A-1","신가평S/S 765kV #3M.Tr 정밀점검","1. 1차 GIS 정밀점검(8472,8400CB,8462,8422,8402DS) 2. M.Tr 정밀점검 3. 7751 DS Dash pot 교체","2018-04-10 09:00","2018-05-18 18:00","2018-04-10 09:00","2018-05-18 18:00","연속",null,null,null,201802080017]
[4,"경기","성남","신안성S/S 765kV #1 BUS","신안성S/S 765kV GIS 정밀점검 공사","신안성S/S #5M.Tr 정밀점검, 신안성S/S 8871,8800,8872 정밀점검 신안성S/S 88BAY B/F 대체, #5M.Tr 보호 PNL 대체, #3S.Tr,IVR 대체 신안성S/S 7C71,7C00 조작시험","2018-04-23 09:00","2018-05-04 18:00","2018-04-23 09:00","2018-05-04 18:00","연속",null,null,null,201802120575]
[5,"경기","성남","신서산신안성#1 T/L","신안성S/S 765kV GIS 정밀점검 공사","신안성S/S #5M.Tr 정밀점검, 신안성S/S 8871,8800,8872 정밀점검 신안성S/S 88BAY B/F 대체, #5M.Tr 보호 PNL 대체, #3S.Tr,IVR 대체 신안성S/S 7C71,7C00 조작시험","2018-04-11 09:00","2018-05-20 18:00","2018-04-11 09:00","2018-05-20 18:00","연속",null,null,null,201802120574]
[6,"대전충남","서산","신서산S/S #4 M.Tr 1차 GIS","18년 서산PO 765kV GIS 정밀점검공사","18년 서산PO 765kV GIS 정밀점검공사","2018-04-11 09:00","2018-04-24 18:00","2018-04-11 09:00","2018-04-24 18:00","당일",null,null,null,201802070477]
[7,"대전충남","서산","신서산S/S #4 M.Tr A-1","신서산S/S 765kV #4M.Tr 2차 GIB 장견간 구조개선 공사","신서산S/S 765kV #4M.Tr 2차 GIB 장견간 구조개선 공사","2018-04-11 09:00","2018-05-18 18:00","2018-04-11 09:00","2018-05-18 18:00","당일",null,null,null,201802070474]
[8,"대전충남","서산","신서산S/S 신서산신안성#1T/L-#4M.Tr1차GIS","18년 서산PO 765kV GIS 정밀점검공사","18년 서산PO 765kV GIS 정밀점검공사","2018-04-25 09:00","2018-05-08 18:00","2018-04-25 09:00","2018-05-08 18:00","당일",null,null,null,201802070481]
[9,"경북","영주","신한울S/S #2 M.Tr A-1","신한울S/S 765kV #2M.Tr 하자점검","신한울S/S 765kV #2M.Tr 하자점검","2018-04-03 09:00","2018-04-06 18:00","2018-04-03 09:00","2018-04-06 18:00","연속",null,null,null,201802190277]
[10,"경북","영주","신한울S/S 765kV #1BUS","신한울S/S 765kV #1BUS 휴전작업","BUS PT Fuse 제거작업(한수원 시행)","2018-04-02 09:00","2018-04-03 18:00","2018-04-02 09:00","2018-04-03 18:00","연속",null,null,null,201802130201]
[11,"경북","영주","신한울S/S #1 M.Tr A-1","신한울S/S 765kV #1M.Tr 하자점검","신한울S/S 765kV #2M.Tr 하자점검","2018-04-10 09:00","2018-04-13 18:00","2018-04-10 09:00","2018-04-13 18:00","연속",null,null,null,201802190278]
[12,"부산울산","동부산","신고리S/S #2M.Tr1차-#3GT/L TIE CB","신고리S/S 765kV GIS 보통점검공사","신고리S/S 765kV 8200 GIS 보통점검","2018-04-23 09:30","2018-04-26 18:00","2018-04-23 09:30","2018-04-26 18:00","연속",null,null,null,201802120283]
[13,"부산울산","동부산","신고리S/S #3GEN T/L CB","신고리S/S 765kV GIS 보통점검공사","신고리S/S 765kV 8272 GIS 보통점검","2018-04-23 09:30","2018-04-26 18:00","2018-04-23 09:30","2018-04-26 18:00","연속",null,null,null,201802120285]
[14,"부산울산","동부산","신고리S/S #2G T/L TIE CB","신고리S/S 765kV GIS 보통점검공사","신고리S/S 765kV 8100 GIS 보통점검","2018-04-16 09:30","2018-04-19 18:00","2018-04-16 09:30","2018-04-19 18:00","연속",null,null,null,201802120280]
[15,"부산울산","동부산","신고리S/S #2GEN T/L CB","신고리S/S 765kV GIS 보통점검공사","신고리S/S 765kV 8171 GIS 보통점검","2018-04-16 09:30","2018-04-19 18:00","2018-04-16 09:30","2018-04-19 18:00","연속",null,null,null,201802120281]

{"sheet":"345송부","index":1,"n_rows":246,"n_cols":16,"rows_kept":246,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2018년도 4월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","중부S/S 345kV #1 Sh.R","2018년 중부P/O 변전 협력회사 총액공사","345kV #1Sh.R 초기점검","2018-04-06 09:30","2018-04-06 18:00","2018-04-06 09:30","2018-04-06 18:00","당일",null,null,null,201802090095]
[2,"서울","중부","중부S/S #2 M.Tr A","2018년 중부P/O 변전 협력회사 총액공사","중부S/S #2M.Tr LA 초기점검","2018-04-04 10:00","2018-04-04 17:00","2018-04-04 10:00","2018-04-04 17:00","당일",null,null,null,201802090085]
[3,"남서울","동서울","신용인동서울#2 T/L","345kV신용인-동서울#2T/L 전선교체공사","345kV신용인-동서울#2T/L 전선접속개소 전선교체공사 - 82호 ~ 83호 중단 내외측 - 83호 ~ 87호 상중하단 내외측 - 87호 ~ 88호 상단 내측 - 93호 ~ 100호 상중하단 내외측","2018-04-30 07:30","2018-05-18 18:00","2018-04-30 07:30","2018-05-18 18:00","연속",null,null,null,201802060540]
[4,"남서울","동서울","동서울S/S #4 M.Tr A","154kV GCB 교체공사","#4M.Tr 2차 GCB 교체, M.Tr B,C상 정밀점검, M.Tr A상 보통점검, 1차 조작시험","2018-04-02 09:00","2018-04-06 18:00","2018-04-02 09:00","2018-04-06 18:00","연속",null,null,null,201802130158]
[5,"남서울","영등포","신광명S/S #3 M.Tr A","송전케이블 포설공사 및 345kV M.Tr 2차 이설","ㅇ 송전케이블 포설공사 이격거리 확보 ㅇ 345kV M.Tr 2차 이설","2018-04-25 08:00","2018-05-04 18:00","2018-04-25 08:00","2018-05-04 18:00","연속",null,null,null,201802200098]
[6,"남서울","영등포","신광명S/S #1 M.Tr A","송전케이블 포설공사 및 EBA가대 설치공사","ㅇ 송전케이블 포설공사 이격거리 확보 ㅇ EBA가대 설치","2018-04-02 08:00","2018-04-11 18:00","2018-04-02 08:00","2018-04-11 18:00","연속",null,null,"신뢰도개선",201802200087]
[7,"인천","김포","신김포S/S #2 M.Tr","신김포S/S 345kV #2M.Tr 보통점검","신김포S/S 345kV #2M.Tr 보통점검","2018-04-19 10:00","2018-04-20 18:00","2018-04-19 10:00","2018-04-20 18:00","연속",null,null,null,201802140107]
[8,"인천","김포","신김포S/S 345kV #1 Sh.R","신김포S/S 345kV #1Sh.R 하자점검","신김포S/S 345kV #1Sh.R 하자점검","2018-04-12 10:00","2018-04-12 18:00","2018-04-12 10:00","2018-04-12 18:00","당일",null,null,null,201802140108]
[9,"인천","김포","신김포서인천CC T/L","345kV신김포서인천CCT/L 정밀점검","345kV신김포서인천CCT/L 정밀점검","2018-04-13 09:00","2018-04-15 18:00","취소","취소","연속",null,null,null,201802140032]
[10,"인천","김포","신김포S/S #1 M.Tr","신김포S/S 345kV #1M.Tr 보통점검","신김포S/S 345kV #1M.Tr 보통점검","2018-04-17 10:00","2018-04-18 18:00","2018-04-17 10:00","2018-04-18 18:00","연속",null,null,null,201802140104]
[11,"인천","김포","신김포신인천CC T/L","345kV신김포신인천CCT/L 정밀점검","345kV신김포신인천CCT/L 정밀점검","2018-04-20 09:00","2018-04-22 18:00","취소","취소","연속",null,null,null,201802140033]
[12,"인천","시흥","신시흥#1S/S 345kV #76 BUS","신시흥#1S/S 345kV 71-76 모선보호반 대체공사","신시흥#1S/S 345kV 71-76 모선보호반 대체공사","2018-04-23 09:30","2018-04-27 18:00","2018-04-23 09:30","2018-04-27 18:00","연속",null,null,null,201802140275]
[13,"인천","시흥","신시흥#1S/S 신시흥영흥TP#4T/L-#3 M.Tr CB (7800)","신시흥영흥TP#4T/L-#3 M.Tr 1차 GIS(7800) 동작시험","신시흥#1S/S 345kV 신시흥영흥TP#4T/L-#3 M.Tr 1차 GIS(7800) 동작시험","2018-04-30 09:30","2018-04-30 18:00","2018-04-30 09:30","2018-04-30 18:00","당일",null,null,null,201802140276]
[14,"인천","시흥","신시흥#1S/S 345kV #71 BUS","신시흥#1S/S 345kV 71-76 모선보호반 대체공사","신시흥#1S/S 345kV 71-76 모선보호반 대체공사","2018-04-16 09:30","2018-04-20 18:00","2018-04-16 09:30","2018-04-20 18:00","연속",null,null,null,201802140268]
[15,"인천","시흥","영흥#2T/P #6G/T 1차 CB (7772)","영흥#2T/P #6G/T 1차 CB(7772) GIS 보통점검","영흥#2T/P #6G/T 1차 CB(7772) GIS 보통점검","2018-04-27 10:30","2018-04-27 18:00","2018-04-27 10:30","2018-04-27 18:00","당일",null,null,null,201802200112]
[16,"인천","시흥","영흥#2T/P 신시흥영흥TP#3T/L CB (7771)","영흥#2T/P 신시흥영흥TP#3T/L CB(7771) GIS 보통점검","영흥#2T/P 신시흥영흥TP#3T/L CB(7771) GIS 보통점검","2018-04-25 10:30","2018-04-25 18:00","2018-04-25 10:30","2018-04-25 18:00","당일",null,null,null,201802200108]
[17,"인천","시흥","영흥#2T/P 신시흥영흥TP#3T/L-#6G/T 1차 CB (7700)","영흥#2 신시흥영흥TP#3T/L-#6G/T 1차(7700) GIS 보통","영흥#2T/P 신시흥영흥TP#3T/L-#6G/T 1차 (7700) GIS 보통점검","2018-04-26 10:30","2018-04-26 18:00","2018-04-26 10:30","2018-04-26 18:00","당일",null,null,null,201802200111]
[18,"인천","시흥","영흥T/P #1G/T 1차 CB (7172)","영흥T/P #1G/T 1차 CB(7172) 구조개선","영흥T/P #1G/T 1차 CB(7172) 구조개선","2018-04-26 09:00","2018-04-28 18:00","취소","취소","연속",null,null,null,201802140213]
[19,"인천","시흥","영흥T/P 신시흥영흥TP#2T/L CB (7471)","영흥T/P 신시흥영흥TP#2T/L CB(7471) 구조개선","영흥T/P 신시흥영흥TP#2T/L CB(7471) 구조개선","2018-04-12 09:00","2018-04-14 18:00","취소","취소","연속",null,null,null,201802140170]
[20,"인천","시흥","영흥T/P 영흥TP연락#2T/L CB (7271)","영흥T/P 영흥TP연락#2T/L CB(7271) 구조개선","영흥T/P 영흥TP연락#2T/L CB(7271) 구조개선","2018-04-16 09:00","2018-04-18 18:00","취소","취소","연속",null,null,null,201802140208]
[21,"인천","시흥","영흥T/P #2 TIE Tr 1차 CB (7372)","영흥T/P #2 TIE Tr 1차 CB(7372) 구조개선","영흥T/P #2 TIE Tr 1차 CB(7372) 구조개선","2018-04-23 09:00","2018-04-25 18:00","취소","취소","연속",null,null,null,201802140212]
[22,"인천","시흥","영흥T/P 영흥TP연락#1T/L-#1 G/T 1차 CB (7100)","영흥T/P 영흥TP연락#1T/L-#1 G/T 1차 CB(7100)","영흥T/P 영흥TP연락#1T/L-#1 G/T 1차 CB(7100) 구조개선","2018-04-02 09:00","2018-04-04 18:00","취소","취소","연속",null,null,null,201802140159]
[23,"인천","시흥","영흥T/P 신시흥영흥TP#4T/L CB (7571)","영흥T/P 신시흥영흥TP#4T/L CB(7571) 구조개선","영흥T/P 신시흥영흥TP#4T/L CB(7571) 구조개선","2018-04-05 09:00","2018-04-07 18:00","취소","취소","연속",null,null,null,201802140160]
[24,"인천","인천","서인천C/C 345kV #70 BUS","345kV 서인천C/C 모선용CLR 설치 및 용량부족 GIS 대체공사","- 345kV 서인천C/C 모선측 CLR용 GIS 설치(#70BUS) - 345kV 서인천C/C 용량부족 GIS 대체(#70BUS 모선개조)","2018-04-26 10:00","2018-05-10 17:00","2018-04-26 10:00","2018-05-10 17:00","연속",null,null,null,201802080115]
[25,"인천","인천","신가좌S/S #2 M.Tr A","신가좌S/S #2M.Tr 보통점검","신가좌S/S #2M.Tr 및 LA 보통점검 신가좌S/S #2M.Tr 1차,2차,3차 GIS 조작시험","2018-04-30 09:00","2018-05-02 18:00","2018-04-30 09:00","2018-05-02 18:00","연속",null,null,null,201801310104]
[26,"인천","인천","신경서S/S #2 M.Tr A","신경서S/S #2M.Tr 보통점검","신경서S/S #2M.Tr 및 LA, GPT 보통점검 신경서S/S #2M.Tr 1차,2차,3차 GIS 보통점검 및 조작시험","2018-04-23 09:00","2018-04-25 18:00","2018-04-23 09:00","2018-04-25 18:00","연속",null,null,null,201801310103]
[27,"인천","인천","신경서S/S #1 M.Tr A","신경서S/S #1M.Tr 본체 상부 누유개소 점검","신경서S/S #1M.Tr 본체 상부 누유개소 점검","2018-04-06 09:30","2018-04-06 17:00","2018-04-06 09:30","2018-04-06 17:00","당일",null,null,null,201802200171]
[28,"인천","인천","포스코파워S/Y 신경서포스코SY#1T/L CB (7371)","포스코S/Y 7371 GIS 제작사 하자처리","포스코S/Y 7371 GIS 제작사 하자처리","2018-04-09 09:00","2018-04-14 18:00","2018-04-16 09:00","2018-04-21 18:00","연속",null,null,null,201801310087]
[29,"인천","인천","포스코SY인천CC#2T/L-#2GEN STEP UP TR CB (7200)","포스코S/Y 7200 GIS 제작사 하자처리","포스코S/Y 7200 GIS 제작사 하자처리","2018-04-02 09:00","2018-04-07 18:00","2018-04-09 09:00","2018-04-14 18:00","연속",null,null,null,201801310086]
[30,"인천","인천","포스코S/Y 신경서포스코SY#1T/L-TIE CB (7300)","포스코S/Y 7300 GIS 제작사 하자처리","포스코S/Y 7300 GIS 제작사 하자처리","2018-04-16 09:00","2018-04-21 18:00","2018-04-23 09:00","2018-04-28 18:00","연속",null,null,null,201801310088]
[31,"인천","인천","포스코파워S/Y 신경서포스코SY#2T/L CB (7471)","포스코S/Y 7471 GIS 제작사 하자처리","포스코S/Y 7471 GIS 제작사 하자처리","2018-04-23 09:00","2018-04-28 18:00","2018-04-30 09:00","2018-05-05 18:00","연속",null,null,null,201801310089]
[32,"인천","인천","포스코S/Y 신경서포스코SY#2T/L-TIE CB (7400)","포스코S/Y 7400 GIS 제작사 하자처리","포스코S/Y 7400 GIS 제작사 하자처리","2018-04-30 09:00","2018-05-05 18:00","취소","취소","연속",null,null,null,201801310090]
[33,"인천","직할","서인천CC신부평#1 T/L","신부평S/S 서인천신부평#1T/L 345kV 보호반 대체","신부평S/S 서인천신부평#1T/L 345kV 보호반 대체","2018-04-02 09:30","2018-04-06 18:00","2018-04-02 09:30","2018-04-06 18:00","연속",null,null,null,201802140325]
[34,"인천","직할","신부평S/S #1 M.Tr A","신부평S/S #1M.Tr 345kV 주변압기 정밀점검","신부평S/S #1M.Tr 345kV 주변압기 정밀점검","2018-04-02 08:00","2018-04-06 18:00","2018-04-02 08:00","2018-04-06 18:00","연속",null,null,null,201802140303]
[35,"인천","직할","서인천CC신부평#2 T/L","신부평S/S 서인천신부평#2T/L 345kV 보호반 대체","신부평S/S 서인천신부평#2T/L 345kV 보호반 대체","2018-04-09 09:30","2018-04-13 18:00","2018-04-09 09:30","2018-04-13 18:00","연속",null,null,null,201802140326]
[36,"인천","직할","신부평S/S 345kV #3 Sh.R","신부평S/S 345kV #3Sh.R 정밀점검","신부평S/S 345kV #3Sh.R 정밀점검","2018-04-23 08:00","2018-04-27 18:00","2018-04-23 08:00","2018-04-27 18:00","연속",null,null,null,201802140306]
[37,"인천","직할","신부평S/S 345kV #4 Sh.R","신부평S/S 345kV #4Sh.R 정밀점검","신부평S/S 345kV #4Sh.R 정밀점검","2018-04-30 08:00","2018-05-04 18:00","2018-04-30 08:00","2018-05-04 18:00","연속",null,null,null,201802140307]
[38,"인천","직할","신부평S/S 345kV #2 Sh.R","신부평S/S 345kV #2Sh.R 정밀점검","신부평S/S 345kV #2Sh.R 정밀점검","2018-04-16 08:00","2018-04-20 18:00","2018-04-16 08:00","2018-04-20 18:00","연속",null,null,null,201802140305]
[39,"인천","직할","신부평S/S #4 M.Tr A","신부평S/S #4M.Tr 345kV 주변압기 정밀점검","신부평S/S #4M.Tr 345kV 주변압기 정밀점검","2018-04-09 08:00","2018-04-13 18:00","2018-04-09 08:00","2018-04-13 18:00","연속",null,null,null,201802140304]
[40,"경기북부","고양","신덕은동두천CC#1 T/L","345kV 신덕은-동두천CC#1T/L 정밀점검","345kV 신덕은-동두천CC#1T/L 정밀점검 - 구간 : No.77~162 (86기)","2018-04-18 09:00","2018-04-27 18:00","2018-04-18 09:00","2018-04-27 18:00","연속",null,null,null,201802120301]
[41,"경기북부","고양","신덕은동두천CC#2 T/L","345kV 신덕은-동두천CC#2T/L 정밀점검","345kV 신덕은-동두천CC#2T/L 정밀점검 - 구간 : No.77~162 (86기)","2018-04-09 09:00","2018-04-17 18:00","2018-04-09 09:00","2018-04-17 18:00","연속",null,null,null,201802120302]
[42,"경기북부","고양","신덕은파주문산CC#2 T/L","18년도 고양전력 362kVGIS정밀점검공사(7302 정밀점검)","신덕은S/S 7302 DS 정밀점검","2018-04-14 08:00","2018-04-15 18:00","2018-04-14 08:00","2018-04-15 18:00","연속",null,null,null,201802050201]
[43,"경기북부","고양","신덕은S/S #3 M.Tr A","18년도 고양전력 362kVGIS정밀점검공사(7371,7300정밀점검)","신덕은S/S 7371,7300 GIS 정밀점검","2018-04-02 08:00","2018-04-06 18:00","2018-04-02 08:00","2018-04-06 18:00","연속",null,null,null,201802050197]
[44,"경기북부","구리","신가평신의정부#2 T/L","2018~19년도 구리전력지사 가공송전정비 협력회사 총액공사","345kV 신가평-신의정부#2T/L 불량압축인류크램프 교체공사 - 대상 : 신가평S/T, No.24,43,46,82,92호","2018-04-05 07:30","2018-04-07 18:00","2018-04-05 07:30","2018-04-07 18:00","연속",null,null,null,201801150111]
[45,"경기북부","구리","신가평신의정부#1 T/L","2018~19년도 구리전력지사 가공송전정비 협력회사 총액공사","345kV 신가평-신의정부#1T/L 불량압축인류크램프 교체공사 - 대상 : No.40,46,56,76,86호","2018-04-02 07:30","2018-04-04 18:00","2018-04-02 07:30","2018-04-04 18:00","연속",null,null,null,201801150109]
[46,"경기북부","구리","신가평미금#2 T/L","2018~19년도 구리전력지사 가공송전정비 협력회사 총액공사","345kV 신가평-미금#2T/L 불량압축인류크램프 교체공사 - 대상 : No.61,79,94,95호","2018-04-09 07:30","2018-04-10 18:00","2018-04-09 07:30","2018-04-10 18:00","연속",null,null,null,201801150114]
[47,"경기북부","구리","신포천S/S 345kV #2 BUS","18년 구리전력지사 345kV GIS 정밀점검 공사","18년 구리전력지사 345kV GIS 정밀점검 공사(#2BUS 누기보수) - 신포천S/S #2BUS 장기휴전 후 누기보수","2018-04-09 09:00","2018-05-04 18:00","2018-04-09 09:00","2018-05-04 18:00","연속",null,null,null,201802120455]
[48,"경기북부","구리","신포천S/S #2 M.Tr A","18년 구리전력지사 345kV GIS 정밀점검 공사","18년 구리전력지사 345kV GIS 정밀점검 공사(#2BUS 누기보수) - 신포천S/S #2BUS 장기휴전,크레인 사용 위험설비 휴전","2018-04-11 09:00","2018-04-13 18:00","2018-04-11 09:00","2018-04-13 18:00","매일",null,null,null,201802120494]
[49,"경기북부","구리","신포천S/S 345kV #1 Sh.R","18년 구리전력지사 345kV GIS 정밀점검 공사","18년 구리전력지사 345kV GIS 정밀점검 공사(7379GIS 정밀) - 신포천S/S 7379, 7372, 7300GIS 휴전 후 정밀점검","2018-04-16 09:00","2018-04-22 18:00","2018-04-16 09:00","2018-04-22 18:00","연속",null,null,null,201802120441]
[50,"경기북부","구리","신포천S/S #1 M.Tr A","18년 구리전력지사 345kV GIS 정밀점검 공사","18년 구리전력지사 345kV GIS 정밀점검 공사(#2BUS 누기보수) - 신포천S/S #2BUS 장기휴전,크레인 사용 #1,2M.Tr휴전","2018-04-11 09:00","2018-04-13 18:00","2018-04-11 09:00","2018-04-13 18:00","매일",null,null,null,201802120486]
[51,"경기북부","구리","신포천S/S #3 M.Tr A","18년 구리전력지사 345kV GIS 정밀점검 공사","18년 구리전력지사 345kV GIS 정밀점검 공사(#2BUS 누기보수) - 신포천S/S #2BUS 장기휴전,크레인 사용 위험설비 휴전","2018-04-20 09:00","2018-04-25 18:00","2018-04-20 09:00","2018-04-25 18:00","매일",null,null,null,201802120497]
[52,"경기북부","구리","신포천S/S #4 M.Tr A","18년 구리전력지사 345kV GIS 정밀점검 공사","18년 구리전력지사 345kV GIS 정밀점검 공사(#2BUS 누기보수) - 신포천S/S #2BUS 장기휴전,크레인 사용 위험설비 휴전","2018-04-26 09:00","2018-04-28 18:00","2018-04-26 09:00","2018-04-28 18:00","매일",null,null,null,201802120498]
[53,"경기북부","직할","신의정부S/S #2 M.Tr A","362kV GIS 보통점검 및 개폐타임측정","362kV GIS 개폐타임측정 신의정부S/S -7372 개폐타임측정","2018-04-26 09:00","2018-04-26 13:00","2018-04-26 09:00","2018-04-26 13:00","당일",null,null,null,201802130188]
[54,"경기북부","직할","신의정부양주#2 T/L","362kV GIS 개폐타임측정","362kV GIS 개폐타임측정 신의정부S/S -7471,7400 양주S/S -7271,7200","2018-04-18 09:00","2018-04-18 18:00","2018-04-18 09:00","2018-04-18 18:00","당일",null,null,null,201802130179]
[55,"경기북부","직할","신의정부양주#1 T/L","362kV GIS 개폐타임측정","362kV GIS 개폐타임측정 신의정부S/S -7371,7300 양주S/S -7171,7100","2018-04-17 09:00","2018-04-17 18:00","2018-04-17 09:00","2018-04-17 18:00","당일",null,null,null,201802130178]
[56,"경기북부","직할","신의정부S/S #1 M.Tr A","362kV GIS 개폐타임측정","362kV GIS 개폐타임측정 -7272,7200","2018-04-16 09:00","2018-04-16 18:00","2018-04-16 09:00","2018-04-16 18:00","당일",null,null,null,201802130176]
[57,"경기북부","직할","양주S/S #2 M.Tr A","양주변전소 옥외철구 GIS화 공사","양주변전소 옥외철구 GIS화 공사 - T-BUS 설비 철거","2018-04-19 09:00","2018-04-30 18:00","2018-04-19 09:00","2018-04-30 18:00","연속",null,null,null,201802220018]
[58,"경기북부","직할","양주중부#1 T/L","양주S/S 362kV Sh.R용 1차 GIS 공장반입 구조개선 공사","362kV #6Sh.R용 1차 GIS 공장반입 구조개선 작업 - GIS 설치작업","2018-04-01 14:00","2018-04-01 18:00","2018-04-01 14:00","2018-04-01 18:00","매일",null,null,null,201802130197]
[59,"경기북부","직할","양주중부#2 T/L","양주S/S 362kV Sh.R용 1차 GIS 공장반입 구조개선 공사","362kV #6Sh.R용 1차 GIS 공장반입 구조개선 작업 - GIS 설치작업","2018-04-01 08:00","2018-04-01 14:00","2018-04-01 08:00","2018-04-01 14:00","매일",null,null,null,201802130199]
[60,"경기","군포","345kV 서서울2-화성 #2T/L CB (7D71)","서서울#2S/S 362kV GIS DS 조작부 교체","1. 작업내용 : DS 조작부 축부분 자재교체 (모터 과부하 해소) 2. 작업개소 : 7D61,7D01 DS (2개소) 3. 시공업체 : 제작사 LS 산전 시공","2018-04-18 09:00","2018-04-18 18:00","2018-04-18 09:00","2018-04-18 18:00","당일",null,null,null,201802070374]
[61,"경기","군포","345kV 서서울2-화성 #1T/L CB (7C71)","서서울#2S/S 362kV GIS DS 조작부 교체","1. 작업내용 : DS 조작부 축부분 자재교체 (모터 과부하 해소) 2. 작업개소 : 7C61,7C01 DS (2개소) 3. 시공업체 : 제작사 LS 산전 시공","2018-04-19 09:00","2018-04-19 18:00","2018-04-19 09:00","2018-04-19 18:00","당일",null,null,null,201802070369]
[62,"경기","군포","서서울2S/S 345kV 7D BAY TIE CB (7D00)","서서울#2S/S 362kV GIS DS 조작부 교체","1. 작업내용 : DS 조작부 축부분 자재교체 (모터 과부하 해소) 2. 작업개소 : 7D61,7D01 DS (2개소) 3. 시공업체 : 제작사 LS 산전 시공","2018-04-19 09:00","2018-04-19 18:00","2018-04-19 09:00","2018-04-19 18:00","당일",null,null,null,201802070375]
[63,"경기","군포","서서울#2S/S #5 M.Tr","서서울#2S/S 362kV M.Tr 초기점검","서서울#2S/S 362kV M.Tr 초기점검","2018-04-20 09:00","2018-04-21 18:00","2018-04-20 09:00","2018-04-21 18:00","당일",null,null,null,201802130260]
[64,"경기","군포","서서울#2S/S #6 M.Tr","서서울#2S/S 362kV M.Tr 초기점검","서서울#2S/S 362kV M.Tr 초기점검","2018-04-23 09:00","2018-04-24 18:00","2018-04-23 09:00","2018-04-24 18:00","당일",null,null,null,201802130275]
[65,"경기","군포","서서울#2신시흥 #1T/L","서서울#2S/S 362kV GIS DS 조작부 교체","1. 작업내용 : DS 조작부 축부분 자재교체 (모터 과부하 해소) 2. 작업개소 : 7D02,7D62 DS (2개소) 3. 시공업체 : 제작사 LS 산전 시공","2018-04-26 09:00","2018-04-26 18:00","2018-04-26 09:00","2018-04-26 18:00","당일",null,null,null,201802050042]
[66,"경기","군포","서서울2S/S 345kV #71 BUS GIS","서서울#2S/S 362kV GIS DS 조작부 교체","1. 작업내용 : DS 조작부 축부분 자재교체 (모터 과부하 해소) 2. 작업개소 : 7A51,7C51,7DA51 DS 3. 시공업체 : 제작사 LS 산전 시공","2018-04-16 09:00","2018-04-17 18:00","2018-04-16 09:00","2018-04-17 18:00","당일",null,null,null,201802050032]
[67,"경기","군포","서서울2S/S 345kV #76BUS GIS","서서울#2S/S 362kV GIS DS 조작부 교체","1. 작업내용 : DS 조작부 축부분 자재교체 (모터 과부하 해소) 2. 작업개소 : 7A52,7B52,7C52,7DA52 DS (4개소) 3. 시공업체 : 제작사 LS 산전 시공","2018-04-18 09:00","2018-04-19 18:00","2018-04-18 09:00","2018-04-19 18:00","당일",null,null,null,201802050033]
[68,"경기","군포","서서울2S/S 345kV 7C BAY TIE CB (7C00)","서서울#2S/S 362kV GIS DS 조작부 교체","1. 작업내용 : DS 조작부 축부분 자재교체 (모터 과부하 해소) 2. 작업개소 : 7C61,7C01 DS (2개소) 3. 시공업체 : 제작사 LS 산전 시공","2018-04-18 09:00","2018-04-18 18:00","2018-04-18 09:00","2018-04-18 18:00","당일",null,null,null,201802070371]
[69,"경기","군포","서서울#2신시흥 #2T/L","서서울#2S/S 362kV GIS DS 조작부 교체","1. 작업내용 : DS 조작부 축부분 자재교체 (모터 과부하 해소) 2. 작업개소 : 7C02,7C62 DS (2개소) 3. 시공업체 : 제작사 LS 산전 시공","2018-04-25 09:00","2018-04-25 18:00","2018-04-25 09:00","2018-04-25 18:00","당일",null,null,null,201802050039]
[70,"경기","군포","서서울S/S #2 M.Tr","서서울S/S 154kV 취약설비 GIS화공사","서서울1변전소 2차 GIS설치 및 변압기보호반, 3차측 보호반 이설, 모선보호반이설, 변압기 2차측 인출철구 철거","2018-04-04 09:00","2018-04-11 18:00","2018-04-04 09:00","2018-04-11 18:00","연속",null,null,null,201801040152]
[71,"경기","군포","화성서서울#2 T/L","33호 철탑 교체 및 7~8호 등 64가닥 전선 교체","철탑교체 : 1기, 전선교체 : 7~8호 등 64가닥","2018-04-12 07:00","2018-04-21 18:00","2018-04-12 07:00","2018-04-21 18:00","연속",null,null,null,201801040019]
[72,"경기","군포","서서울S/S #1 M.Tr","서서울S/S 154kV 취약설비 GIS화공사","서서울1변전소 2차 GIS설치 및 변압기보호반, 3차측 보호반 이설, 모선보호반이설, 변압기 2차측 인출철구 철거","2018-04-22 09:00","2018-04-30 18:00","2018-04-22 09:00","2018-04-30 18:00","연속",null,null,null,201801040160]
[73,"경기","군포","신안산S/S 신시흥-신안산T/L CB (7371)","18년 군포P/O 변전협력총액공사","- 7371 차단기 조작시험(개폐타임 등)","2018-04-08 13:00","2018-04-08 16:00","2018-04-08 13:00","2018-04-08 16:00","당일",null,null,null,201802070185]
[74,"경기","군포","신안산S/S #4 M.Tr A","18년 군포P/O 변전협력총액공사","- 주변압기 보통점검 - 1차 차단기(7300,7372) 조작시험 - 2차 차단기(6444) 조작시험","2018-04-10 09:00","2018-04-11 18:00","2018-04-10 09:00","2018-04-11 18:00","연속",null,null,null,201802070193]
[75,"경기","군포","신안산S/S 화성-신안산T/L CB (7171)","18년 군포P/O 변전협력총액공사","- 7171 차단기 조작시험(개폐타임 등)","2018-04-09 10:00","2018-04-09 13:00","2018-04-09 10:00","2018-04-09 13:00","당일",null,null,null,201802070195]
[76,"경기","동부","곤지암동서울#2 T/L","곤지암S/S 362kV GIS 설치공사","곤지암S/S 362kV GIS 설치공사 관련 #1BUS 무부하가압용 수전선로 - 362kV GIS(63kA, 6300A) 2CB 설치(76Bay)","2018-04-27 17:00","2018-04-28 17:00","2018-04-27 17:00","2018-04-28 17:00","연속",null,null,null,201802130071]
[77,"경기","동부","곤지암S/S 345kV #1 BUS","곤지암S/S 362kV GIS 설치공사","곤지암S/S 362kV GIS 설치공사 관련 #1BUS측 설치 - 362kV GIS(63kA, 6300A) 2CB 설치(76Bay)","2018-04-23 09:30","2018-04-28 17:00","2018-04-23 09:30","2018-04-28 17:00","연속",null,null,null,201802130068]
[78,"경기","동부","곤지암S/S 345kV #2 BUS","곤지암S/S 362kV GIS 설치공사","곤지암S/S 362kV GIS 설치공사 관련 #2BUS측 설치 - 362kV GIS(63kA, 6300A) 2CB 설치(76Bay)","2018-04-30 09:30","2018-05-05 17:00","2018-04-30 09:30","2018-05-05 17:00","연속",null,null,null,201802130070]
[79,"경기","성남","신성남S/S #6 M.Tr A","신성남S/S #6M.Tr 2차 6644 정밀점검 등","신성남S/S #6M.Tr 2차 6644 정밀점검, UHF 센서설치 신성남S/S #6M.Tr 보통점검, 7800,7872 조작시험 #6M.Tr 1,2,3차 LA, 3차 PT 보통점검 #6M.Tr 1,2차 전자변히터, 수동트립장치 설치","2018-04-16 09:00","2018-04-18 18:00","2018-04-16 09:00","2018-04-18 18:00","연속",null,null,null,201802120582]
[80,"경기","성남","신성남S/S #1M.Tr A","신성남S/S #1M.Tr,6144 보통점검 등","신성남S/S #1M.Tr,6144 보통점검 7172 조작시험, 전자변히터 설치 2,3차 LA, 3차 PT 보통점검","2018-04-19 10:00","2018-04-20 18:00","2018-04-19 10:00","2018-04-20 18:00","연속",null,null,null,201802120588]
[81,"경기","성남","신성남S/S #4M.Tr A","신성남S/S #4M.Tr, 7572, 6444 보통점검 등","신성남S/S #4M.Tr, 7572, 6444 보통점검 2,3차 LA, 3차 PT 보통점검, 전자변 히터 설치","2018-04-24 10:00","2018-04-25 18:00","2018-04-24 10:00","2018-04-25 18:00","연속",null,null,null,201802120590]
[82,"경기","성남","신용인신수원 T/L","화성동탄2 345kV 신수원~신용인TL 지중화공사","가. 공사구간 : 기설 345kV 신용인∼신수원 TL No.13∼No.23호 (15호∼23호 병가) 기설 345kV 신안성∼신수원 TL No.55∼No.65호 (57호∼65호 병가) 동측, 서측C/H 구성공사","2018-04-22 08:00","2018-04-22 18:00","2018-04-22 08:00","2018-04-22 18:00","연속",null,null,null,201802090129]
[83,"경기","성남","신안성신수원#1 T/L","화성동탄2 345kV 신수원~신용인TL 지중화공사","가. 공사구간 : 기설 345kV 신용인∼신수원 TL No.13∼No.23호 (15호∼23호 병가) 기설 345kV 신안성∼신수원 TL No.55∼No.65호 (57호∼65호 병가) 동측, 서측C/H 구성공사","2018-04-22 08:00","2018-04-26 18:00","2018-04-22 08:00","2018-04-26 18:00","연속",null,null,null,201802090130]
[84,"경기","성남","신용인신수원 T/L","화성동탄2 345kV 신수원~신용인TL 지중화공사","가. 공사구간 : 기설 345kV 신용인∼신수원 TL No.13∼No.23호 (15호∼23호 병가) 기설 345kV 신안성∼신수원 TL No.55∼No.65호 (57호∼65호 병가) 동측, 서측C/H 구성공사","2018-04-27 08:00","2018-05-05 18:00","2018-04-27 08:00","2018-05-05 18:00","연속",null,null,null,201802090132]
[85,"경기","성남","신안성신수원#2 T/L","화성동탄2 345kV 신수원~신용인TL 지중화공사","가. 공사구간 : 기설 345kV 신용인∼신수원 TL No.13∼No.23호 (15호∼23호 병가) 기설 345kV 신안성∼신수원 TL No.55∼No.65호 (57호∼65호 병가) 동측, 서측C/H 구성공사","2018-04-15 08:00","2018-04-21 18:00","2018-04-15 08:00","2018-04-21 18:00","연속",null,null,null,201802090128]
[86,"경기","성남","신안성신수원#1 T/L","화성동탄2 345kV 신수원~신용인TL 지중화공사","가. 공사구간 : 기설 345kV 신용인∼신수원 TL No.13∼No.23호 (15호∼23호 병가) 기설 345kV 신안성∼신수원 TL No.55∼No.65호 (57호∼65호 병가) 동측, 서측C/H 구성공사","2018-04-08 08:00","2018-04-08 18:00","2018-04-08 08:00","2018-04-08 18:00","연속",null,null,null,201802090126]
[87,"경기","성남","신용인삼성 T/L","화성동탄2 345kV 신수원~신용인TL 지중화공사","가. 공사구간 : 기설 345kV 신용인∼신수원 TL No.13∼No.23호 (15호∼23호 병가) 기설 345kV 신안성∼신수원 TL No.55∼No.65호 (57호∼65호 병가) 동측, 서측C/H 구성공사","2018-04-08 08:00","2018-04-08 18:00","2018-04-08 08:00","2018-04-08 18:00","연속",null,null,null,201802090125]
[88,"경기","성남","신용인삼성 T/L","화성동탄2 345kV 신수원~신용인TL 지중화공사","가. 공사구간 : 기설 345kV 신용인∼신수원 TL No.13∼No.23호 (15호∼23호 병가) 기설 345kV 신안성∼신수원 TL No.55∼No.65호 (57호∼65호 병가) 동측, 서측C/H 구성공사","2018-04-11 08:00","2018-04-15 18:00","2018-04-11 08:00","2018-04-15 18:00","연속",null,null,null,201802090127]
[89,"경기","직할","화성S/S 345kV #1LCR 71BUS CB (7177)","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 철거시행","2018-04-23 09:00","2019-06-30 18:00","취소","취소","연속",null,null,null,201801300056]
[90,"경기","직할","화성S/S 345kV #2LCR 76BUS GIS CB (7677)","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 철거시행","2018-04-23 09:00","2019-06-30 18:00","취소","취소","연속",null,null,null,201801300058]
[91,"경기","직할","화성S/S 345kV #70 BUS","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 #70모선 분리","2018-04-23 09:00","2018-04-28 18:00","취소","취소","연속",null,null,null,201801300048]
[92,"경기","직할","화성S/S 345kV #1LCR 70BUS CB (7077)","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 철거시행","2018-04-23 09:00","2019-06-30 18:00","취소","취소","연속",null,null,null,201801300054]
[93,"경기","직할","화성S/S 345kV #2LCR 75BUS GIS CB (7577)","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 철거시행","2018-04-23 09:00","2019-06-30 18:00","취소","취소","연속",null,null,null,201801300057]
[94,"경기","직할","화성S/S 345kV #75 BUS","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 #75모선 분리","2018-04-29 09:00","2018-05-04 18:00","취소","취소","연속",null,null,null,201801300049]
[95,"경기","평택","평택T/P #2 M.Tr 1차 CB (7672)","평택T/P #2M.Tr 1차 CB(7672) 조작시험","평택T/P #2M.Tr 1차 CB(7672) 조작시험","2018-04-18 14:00","2018-04-18 18:00","2018-04-18 14:00","2018-04-18 18:00","당일",null,null,null,201802120452]
[96,"경기","평택","평택T/P #2 M.Tr 1차 CB (7672)","평택T/P #2M.Tr CB(7600) 조작시험","평택T/P #2M.Tr CB(7600) 조작시험","2018-04-18 10:00","2018-04-18 14:00","2018-04-18 10:00","2018-04-18 14:00","당일",null,null,null,201802120450]
[97,"강원","강릉","신양양S/S #1 M.Tr A","2018년 변전협력회사 총액공사","신양양S/S 154kV GIS 유압 메카니즘 보수","2018-04-02 10:00","2018-04-02 14:00","2018-04-02 10:00","2018-04-02 14:00","당일",null,null,null,201802010061]
[98,"강원","강릉","동해신양양 T/L","2018년 가공송전선로 순시점검 위탁공사","○ 345kV 동해-신양양T/L No.72~145호 철탑정밀점검","2018-04-16 08:00","2018-04-21 18:00","2018-04-16 08:00","2018-04-21 18:00","매일",null,null,null,201802060340]
[99,"강원","강릉","신양양S/S #2 M.Tr A","2018년 변전협력회사 총액공사","신양양S/S 154kV GIS 유압 메카니즘 보수","2018-04-02 14:00","2018-04-02 18:00","2018-04-02 14:00","2018-04-02 18:00","당일",null,null,null,201802010062]
[100,"강원","강릉","동해양양PP T/L","2018년 가공송전선로 순시점검 위탁공사","○ 345kV 동해-양양PP T/L No.72~145호 철탑정밀점검","2018-04-23 08:00","2018-04-28 18:00","2018-04-23 08:00","2018-04-28 18:00","매일",null,null,null,201802060341]
[101,"강원","태백","신태백한울NP2#1 T/L","18년 가공송전선로 순시점검 위탁공사","345kV 신태백-한울NP2 #1T/L 정밀점검","2018-04-02 09:00","2018-04-08 18:00","2018-04-02 09:00","2018-04-08 18:00","연속",null,null,null,201802050164]
[102,"충북","청주","신옥천무주양수 T/L","345kV 신옥천-북경남T/L 전선접속개소 전선교체공사","전선교체 22.661c-km","2018-04-22 08:00","2018-04-27 19:00","2018-04-22 08:00","2018-04-27 19:00","연속",null,null,null,201802060164]
[103,"충북","청주","신옥천북경남 T/L","345kV 신옥천-북경남T/L 전선접속개소 전선교체공사","전선교체 22.661c-km","2018-04-12 08:00","2018-04-21 19:00","2018-04-12 08:00","2018-04-21 19:00","연속",null,null,null,201802060150]
[104,"충북","청주","신옥천S/S #2 M.Tr A","신옥천S/S 장기사용 23kV 분로리액터 대체","#2M.Tr 3차측 인출 모선 보강 - AL Pipe 60Φ → AL Pipe 89Φ - ACSR 520SQ × 2B → ACSR 520SQ × 4B","2018-04-23 10:00","2018-04-25 18:00","2018-04-23 10:00","2018-04-25 18:00","연속",null,null,null,201802010046]
[105,"충북","청주","신옥천S/S #1 M.Tr A","신옥천S/S 장기사용 23kV 분로리액터 대체","#1M.Tr 3차측 인출 모선 보강(ACSR 520SQ×2B → ACSR 520SQ×4B)","2018-04-30 10:00","2018-05-02 18:00","2018-04-30 10:00","2018-05-02 18:00","연속",null,null,null,201802120029]
[106,"대전충남","서산","신당진개폐소북당진 T/L","345kV GSEPS분기T/L 정밀점검","345kV GSEPS분기T/L 정밀점검","2018-04-13 07:00","2018-04-13 18:00","2018-04-13 07:00","2018-04-13 18:00","매일",null,null,null,201802070169]
[107,"대전충남","서산","북당진현대제철 T/L","345kV GSEPS분기T/L 정밀점검","345kV GSEPS분기T/L 정밀점검","2018-04-12 07:00","2018-04-12 18:00","2018-04-12 07:00","2018-04-12 18:00","매일",null,null,null,201802070164]
[108,"대전충남","서산","북당진현대제철 T/L","345kV GSEPS분기T/L 정밀점검","345kV GSEPS분기T/L 정밀점검","2018-04-10 07:00","2018-04-10 18:00","2018-04-10 07:00","2018-04-10 18:00","매일",null,null,null,201802070162]
[109,"대전충남","서산","신당진개폐소북당진 T/L","345kV GSEPS분기T/L 정밀점검","345kV GSEPS분기T/L 정밀점검","2018-04-11 07:00","2018-04-11 18:00","2018-04-11 07:00","2018-04-11 18:00","매일",null,null,null,201802070168]
[110,"대전충남","세종","세종S/S 신옥천-세종#1T/L CB (7371)","[변전] 18년 변전협력회사 총액공사","○ GIS 하자점검","2018-04-10 09:30","2018-04-10 18:00","2018-04-10 09:30","2018-04-10 18:00","당일",null,null,null,201802080345]
[111,"대전충남","세종","세종S/S 신옥천-세종#2T/L CB (7471)","[변전] 18년 변전협력회사 총액공사","○ GIS 하자점검","2018-04-11 09:30","2018-04-11 18:00","2018-04-11 09:30","2018-04-11 18:00","당일",null,null,null,201802080346]
[112,"대전충남","세종","세종S/S 세종-청원#1T/L CB (7571)","[변전] 18년 변전협력회사 총액공사","○ GIS 하자점검","2018-04-12 09:30","2018-04-12 18:00","2018-04-12 09:30","2018-04-12 18:00","당일",null,null,null,201802080344]
[113,"대전충남","세종","세종S/S 세종-청원#2T/L CB (7271)","[변전] 18년 변전협력회사 총액공사","○ GIS 하자점검","2018-04-09 09:30","2018-04-09 18:00","2018-04-09 09:30","2018-04-09 18:00","당일",null,null,null,201802080343]
[114,"대전충남","세종","세종S/S 72 BAY TIE CB (7200)","[변전] 18년 변전협력회사 총액공사","○ GIS 하자점검","2018-04-02 09:30","2018-04-02 18:00","2018-04-02 09:30","2018-04-02 18:00","당일",null,null,null,201802080339]
[115,"대전충남","세종","세종S/S 345kV #2 BUS","[변전] 18년 변전협력회사 총액공사","○ #2BUS PT 하자점검","2018-04-06 14:00","2018-04-06 18:00","2018-04-06 14:00","2018-04-06 18:00","당일",null,null,null,201802080348]
[116,"대전충남","세종","세종S/S 74 BAY TIE CB (7400)","[변전] 18년 변전협력회사 총액공사","○ GIS 하자점검","2018-04-04 09:30","2018-04-04 18:00","2018-04-04 09:30","2018-04-04 18:00","당일",null,null,null,201802080341]
[117,"대전충남","세종","세종S/S 73 BAY TIE CB (7300)","[변전] 18년 변전협력회사 총액공사","○ GIS 하자점검","2018-04-03 09:30","2018-04-03 18:00","2018-04-03 09:30","2018-04-03 18:00","당일",null,null,null,201802080340]
[118,"대전충남","세종","세종S/S 345kV #1 BUS","[변전] 18년 변전협력회사 총액공사","○ #1BUS PT 하자점검","2018-04-06 09:30","2018-04-06 14:00","2018-04-06 09:30","2018-04-06 14:00","당일",null,null,null,201802080347]
[119,"대전충남","세종","세종S/S 75 BAY TIE CB (7500)","[변전] 18년 변전협력회사 총액공사","○ GIS 하자점검","2018-04-05 09:30","2018-04-05 18:00","2018-04-05 09:30","2018-04-05 18:00","당일",null,null,null,201802080342]
[120,"대전충남","아산","신온양신탕정#1 T/L","[송전]345kV 신온양-신탕정T/L 항공장애표시구 교체공사","345kV 신온양-신탕정T/L 항공장애표시구 교체공사","2018-04-19 07:00","2018-04-20 18:00","2018-04-19 07:00","2018-04-20 18:00","매일",null,null,null,201802120469]
[121,"대전충남","아산","신온양신탕정#2 T/L","[통신]345kV 신온양-신탕정T/L 항공장애표시구 교체공사","345kV 신온양-신탕정T/L 항공장애표시구 교체공사","2018-04-17 07:00","2018-04-18 18:00","2018-04-17 07:00","2018-04-18 18:00","매일",null,null,null,201802140133]
[122,"대전충남","아산","신탕정S/S TIE-#3M.Tr 1차 CB (7300)","신탕정S/S 345kV 7300 GIS 초기점검","○ 신탕정S/S 345kV 7300 GIS 초기점검","2018-04-24 09:00","2018-04-24 18:00","2018-04-24 09:00","2018-04-24 18:00","당일",null,null,null,201802060649]
[123,"대전충남","아산","신탕정S/S 신온양-신탕정#2-TIE CB (7400)","신탕정S/S 345kV 7400 GIS 초기점검","○ 신탕정S/S 345kV 7400 GIS 초기점검","2018-04-30 09:00","2018-04-30 18:00","2018-04-30 09:00","2018-04-30 18:00","당일",null,null,null,201802060645]
[124,"대전충남","아산","신탕정S/S 신온양-신탕정 #2 T/L CB (7471)","신탕정S/S 345kV 7471 GIS 초기점검","○ 신탕정S/S 345kV 7471 GIS 초기점검","2018-04-27 09:00","2018-04-27 18:00","2018-04-27 09:00","2018-04-27 18:00","당일",null,null,null,201802060646]
[125,"대전충남","아산","아산S/S #2 M.Tr A","아산S/S #75BAY B/F PNL 대체","○ 아산S/S #75BAY B/F PNL 대체","2018-04-23 09:00","2018-04-26 18:00","2018-04-23 09:00","2018-04-26 18:00","연속",null,null,null,201802060618]
[126,"대전충남","아산","신서산아산#1 T/L","154kV 합덕분기T/L 건설공사","기설 154kV 아산송악T/L 2Π분기~신설 154kV 합덕S/S 합덕S/S 신설에 따른 관형지지물 2기 신설(154kV 아산-송악 No.52~53)","2018-04-07 09:00","2018-04-08 18:00","2018-04-07 09:00","2018-04-08 18:00","매일",null,null,null,201801120161]
[127,"대전충남","청양","보령T/P 345kV #71 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7571 GIS 교체 ○ 보령화력 345kV 7500 GIS 교체 ○ 보령화력 345kV 7572 GIS 교체","2018-04-02 09:00","2018-04-03 18:00","2018-04-02 09:00","2018-04-03 18:00","연속",null,null,null,201802070143]
[128,"대전충남","청양","아산보령화력#2 T/L","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7571 GIS 교체 ○ 보령화력 345kV 7500 GIS 교체 ○ 보령화력 345kV 7572 GIS 교체","2018-04-02 09:00","2018-05-19 18:00","2018-04-02 09:00","2018-05-19 18:00","연속",null,null,null,201802070132]
[129,"대전충남","청양","보령T/P #5 M.Tr 1차 CB (7572)","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7571 GIS 교체 ○ 보령화력 345kV 7500 GIS 교체 ○ 보령화력 345kV 7572 GIS 교체","2018-04-02 09:00","2018-05-19 18:00","2018-04-02 09:00","2018-05-19 18:00","연속",null,null,null,201802070139]
[130,"대전충남","청양","보령T/P 345kV #76 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7571 GIS 교체 ○ 보령화력 345kV 7500 GIS 교체 ○ 보령화력 345kV 7572 GIS 교체","2018-04-04 09:00","2018-04-05 18:00","2018-04-04 09:00","2018-04-05 18:00","연속",null,null,null,201802070145]
[131,"대전충남","청양","보령T/P 345kV #71 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7571 GIS 교체 ○ 보령화력 345kV 7500 GIS 교체 ○ 보령화력 345kV 7572 GIS 교체","2018-04-10 09:00","2018-04-12 18:00","2018-04-10 09:00","2018-04-12 18:00","연속",null,null,null,201802070170]
[132,"대전충남","청양","보령T/P #2 M.Tr 1차 CB (7272)","관내S/S 345kV 차단기 부동작 예방조작시험","○보령T/P #2M.Tr 1차 CB(7272) 조작시험","2018-04-17 09:00","2018-04-17 18:00","2018-04-17 09:00","2018-04-17 18:00","당일",null,null,null,201802070285]
[133,"대전충남","청양","보령T/P 아산-보령화력#1T/L-#1 M.Tr 1차CB (7100)","보령T/P 345kV 차단기 보통점검","보령T/P 345kV 차단기 보통점검 - 7100CB","2018-04-19 09:00","2018-04-20 18:00","2018-04-19 09:00","2018-04-20 18:00","연속",null,null,null,201802120425]
[134,"대전충남","청양","보령T/P #1 M.Tr 1차 CB (7171)","보령T/P 345kV 차단기 보통점검","보령T/P 345kV 차단기 보통점검 - 7171CB","2018-04-19 09:00","2018-04-20 18:00","2018-04-19 09:00","2018-04-20 18:00","연속",null,null,null,201802120424]
[135,"대전충남","청양","보령T/P 345kV #71 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7571 GIS 교체 ○ 보령화력 345kV 7500 GIS 교체 ○ 보령화력 345kV 7572 GIS 교체","2018-04-25 09:00","2018-04-25 14:00","2018-04-25 09:00","2018-04-25 14:00","당일",null,null,null,201802070176]
[136,"대전충남","청양","보령T/P 345kV #76 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7571 GIS 교체 ○ 보령화력 345kV 7500 GIS 교체 ○ 보령화력 345kV 7572 GIS 교체","2018-04-25 14:00","2018-04-25 18:00","2018-04-25 14:00","2018-04-25 18:00","당일",null,null,null,201802070174]
[137,"대전충남","청양","보령T/P 345kV #76 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7571 GIS 교체 ○ 보령화력 345kV 7500 GIS 교체 ○ 보령화력 345kV 7572 GIS 교체","2018-04-13 09:00","2018-04-15 18:00","2018-04-13 09:00","2018-04-15 18:00","연속",null,null,null,201802070172]
[138,"전북","군산","군산신김제#1 T/L","군산신김제T/L 전선접속개소해소 및 항공자애표시구설치공사","○ 전선접속개소 해소공사 : No.52~144 ○ 항공장애표시구설치 : No.1~144","2018-04-11 07:00","2018-04-30 18:00","2018-04-11 07:00","2018-04-30 18:00","연속",null,null,null,201801190129]
[139,"전북","군산","군산신김제#2 T/L","군산신김제T/L 전선접속개소해소공사","○ 전선접속개소 해소공사 : No.52~144","2018-04-02 07:00","2018-04-10 18:00","2018-04-09 07:00","2018-04-10 18:00","연속",null,null,null,201801190122]
[140,"전북","군산","군산새만금#1 T/L","군산새만금#1 T/L 폴리머애자교체공사","폴리머애자교체 : No.7,12,13,29,30,85,86,87호","2018-04-23 07:00","2018-04-25 18:00","2018-04-23 07:00","2018-04-25 18:00","연속",null,null,null,201801190105]
[141,"전북","직할","무주P/P 71BAY BUS-TIE GIS","무주P/P 71Bay BUS TIE","1. 무주양수 345kV 무주P/P 71Bay BUS TIE(7100) 차단기 조작시험","2018-04-27 09:00","2018-04-27 18:00","2018-04-27 10:00","2018-04-27 12:00","당일",null,null,null,201802130046]
[142,"전북","직할","무주P/P #2M.Tr 1차 CB (7272)","관내S/S 154kV 이상 차단기 조작시험","무주P/P #2M.Tr 1차 CB(7272) 개폐타임 측정","2018-04-26 13:00","2018-04-26 15:00","2018-04-21 13:00","2018-04-21 15:00","당일",null,null,null,201802140201]
[143,"전북","직할","무주P/P 72BAY BUS-TIE GIS","무주P/P 72Bay BUS TIE","1. 무주양수 345kV 무주P/P 71Bay BUS TIE(7100) 차단기 조작시험","2018-04-28 09:00","2018-04-28 18:00","2018-04-27 13:00","2018-04-27 15:00","당일",null,null,null,201802130242]
[144,"전북","직할","무주P/P #1M.Tr 1차 CB (7172)","관내S/S 154kV 이상 차단기 조작시험","무주P/P #1M.Tr 1차 CB(7172) 개폐타임 측정","2018-04-26 10:00","2018-04-26 12:00","2018-04-21 10:00","2018-04-21 12:00","당일",null,null,null,201802140200]
[145,"전북","직할","북경남무주양수 T/L","345kV 신옥천-북경남T/L 전선접속개소 전선교체공사","전선교체 22.661c-km","2018-04-28 08:00","2018-05-03 19:00","2018-04-28 08:00","2018-05-03 19:00","연속",null,null,null,201802060221]
[146,"전북","직할","신남원S/S 신남원-한빛NP#1 T/L CB (7272)","관내S/S 154kV 이상 차단기 조작시험","362kV GIS CB(7272) 조작시험","2018-04-04 15:00","2018-04-04 17:00","2018-04-04 15:00","2018-04-04 17:00","당일",null,null,null,201802130255]
[147,"전북","직할","신남원S/S 신남원-의 령#1 T/L CB (7371)","관내S/S 154kV 이상 차단기 조작시험","362kV GIS CB(7371) 조작시험","2018-04-05 10:00","2018-04-05 12:00","2018-04-05 10:00","2018-04-05 12:00","당일",null,null,null,201802130286]
[148,"전북","직할","신옥천신남원#1-신남원한빛NP#1 T/L CB (7200)","관내S/S 154kV 이상 차단기 조작시험","362kV GIS CB(7200) 조작시험","2018-04-04 13:00","2018-04-04 15:00","2018-04-04 13:00","2018-04-04 15:00","당일",null,null,null,201802130250]
[149,"전북","직할","신옥천신남원#2-신남원한빛NP#2 T/L CB (7100)","관내S/S 154kV 이상 차단기 조작시험","362kV GIS CB(7100) 조작시험","2018-04-04 10:00","2018-04-04 12:00","2018-04-04 10:00","2018-04-04 12:00","당일",null,null,null,201802130248]
[150,"전북","직할","신남원신광주#1 T/L","154kV 신남원-남원T/L 건설공사","(휴전작업 : 345kV 신남원-신광주T/L 병가관련 휴전) 154kV 신남원-남원T/L 건설공사 - 구 간 : 기설 345kV 신남원S/S ~ 기설 154kV 남원S/S - 전 력 선 : ACSR 410㎟ × 2B - 규 모 : 11.81㎞ / 철탑 : 31기","2018-04-09 08:00","2018-04-20 18:00","2018-04-10 08:00","2018-04-21 18:00","연속",null,null,null,201801030056]
[151,"전북","직할","신남원S/S 신남원-의 령#1 - TIE CB (7300)","관내S/S 154kV 이상 차단기 조작시험","362kV GIS CB(7272) 조작시험","2018-04-05 13:00","2018-04-05 15:00","2018-04-05 13:00","2018-04-05 15:00","당일",null,null,null,201802130294]
[152,"전북","직할","신남원S/S 신남원-광양#1 - TIE CB (7500)","관내S/S 154kV 이상 차단기 조작시험","362kV GIS CB(7500) 조작시험","2018-04-06 15:00","2018-04-06 17:00","2018-04-06 15:00","2018-04-06 17:00","당일",null,null,null,201802130308]
[153,"전북","직할","신남원S/S 신남원-광양#1 T/L CB (7571)","관내S/S 154kV 이상 차단기 조작시험","362kV GIS CB(7571) 조작시험","2018-04-06 13:00","2018-04-06 15:00","2018-04-06 13:00","2018-04-06 15:00","당일",null,null,null,201802130306]
[154,"전북","직할","신남원S/S 신남원-의 령#2 - TIE CB (7400)","관내S/S 154kV 이상 차단기 조작시험","362kV GIS CB(7400) 조작시험","2018-04-06 10:00","2018-04-06 12:00","2018-04-06 10:00","2018-04-06 12:00","당일",null,null,null,201802130302]
[155,"전북","직할","신남원S/S 신남원-의 령#2 T/L CB (7471)","관내S/S 154kV 이상 차단기 조작시험","362kV GIS CB(7471) 조작시험","2018-04-05 15:00","2018-04-05 17:00","2018-04-05 15:00","2018-04-05 17:00","당일",null,null,null,201802130300]
[156,"전북","직할","신옥천신남원#1 T/L","345KV 신옥천-신남원T/L No.74 안전이격 확보공사","345KV 신옥천-신남원T/L No.74 안전이격 확보공사","2018-04-04 08:00","2018-04-10 18:00","2018-04-04 08:00","2018-04-10 18:00","연속",null,null,null,201801190170]
[157,"광주전남","강진","신화순신강진#2 T/L","345kV 신화순신강진#2 T/L (순시점검 위탁공사)","345kV 신화순신강진#2 T/L (순시점검 위탁공사) 정밀점검","2018-04-01 09:00","2018-04-05 18:00","취소","취소","매일",null,null,null,201802140019]
[158,"광주전남","광주","신광주S/S 신광주-신화순#1T/L CB(15년) (7671(신))","신광주S/S 신광주-신화순#1T/L CB(변전협력회사공사)","신광주S/S 7671 CB 하자점검","2018-04-26 09:00","2018-04-26 18:00","2018-04-26 09:00","2018-04-26 18:00","당일",null,null,null,201802050273]
[159,"광주전남","광주","신광주S/S #4 M.Tr A","신광주S/S #4 M.Tr(변압기 정밀점검)","345kV M.Tr 및 OLTC 정밀점검공사","2018-04-02 09:00","2018-04-09 18:00","2018-04-02 09:00","2018-04-09 18:00","연속",null,null,null,201801120095]
[160,"광주전남","광주","신화순S/S #3 M.Tr A","신광주S/S #3 M.Tr(변압기 정밀점검)","345kV M.Tr 및 OLTC 정밀점검공사","2018-04-12 09:00","2018-04-19 18:00","2018-04-12 09:00","2018-04-19 18:00","연속",null,null,null,201801120099]
[161,"광주전남","순천","광양S/S 광양제철#2T/L-KP복합#2T/L CB (7A00)","광양제철#2T/L-KP복합#2T/L CB(7A00 차단기 대체)","7A00 차단기 내부 균압콘덴서 교체공사","2018-04-23 09:00","2018-04-27 18:00","2018-04-23 09:00","2018-04-27 18:00","연속",null,null,null,201802200163]
[162,"광주전남","순천","광양S/S KP복합#2T/L CB (7A72)","광양S/S KP복합#2T/L 7A72CB(7A00 차단기 대체)","7A00 차단기 내부 균압콘덴서 교체공사","2018-04-23 09:00","2018-04-27 18:00","2018-04-23 09:00","2018-04-27 18:00","연속",null,null,null,201802200164]
[163,"광주전남","순천","광양S/S 345kV #76 BUS","광양S/S 345kV #76 BUS(7A00 차단기 시험가압)","7A00 차단기 내부 균압콘덴서 교체공사 시험가압","2018-04-26 15:00","2018-04-27 18:00","2018-04-26 15:00","2018-04-27 18:00","연속",null,null,null,201802200185]
[164,"광주전남","순천","광양하동화력#2 T/L","‘18-19년도 순천전력지사 변전협력회사 총액공사","광양 LA 초기점검","2018-04-10 10:00","2018-04-10 18:00","취소","취소","당일",null,null,null,201802120122]
[165,"광주전남","순천","신강진광양#1 T/L","345kV 신강진-광양#1 T/L(7A00 차단기 시험가압)","7A00 차단기 내부 균압콘덴서 교체공사 시험가압","2018-04-26 15:00","2018-04-27 18:00","2018-04-26 15:00","2018-04-27 18:00","연속",null,null,null,201802200186]
[166,"광주전남","순천","여수T/P #3 Tie-Tr","와이피피제 보호계전기 성능개선","와이피피제(L90,D60,F35) 보호계전기 모듈교체","2018-04-02 09:00","2018-04-02 18:00","2018-04-02 09:00","2018-04-02 18:00","당일",null,null,null,201802210182]
[167,"대구","달성","대구S/S #3 M.Tr A","달성전력지사 주변압기 정밀점검공사","달성전력지사 주변압기 정밀점검공사","2018-04-16 09:00","2018-04-23 18:00","2018-04-16 09:00","2018-04-23 18:00","연속",null,null,null,201802070068]
[168,"대구","달성","북경남대구#2 T/L","달성전력지사 GIS 정밀점검공사","달성전력지사 GIS 정밀점검공사(7371,7300)","2018-04-09 09:00","2018-04-14 18:00","취소","취소","연속",null,null,null,201802140046]
[169,"대구","칠곡","북대구선산 T/L","345kV선산분기T/L 전력선 교체공사","345kV북대구-선산T/L No.83~84 전력선 교체공사 (345kV선산분기T/L No.54~55)","2018-04-25 08:00","2018-04-27 18:00","2018-04-25 08:00","2018-04-27 18:00","연속",null,null,null,201802120422]
[170,"대구","칠곡","북대구서대구#1 T/L","서대구S/S 78Bay B/F PNL 대체작업","서대구S/S 78Bay B/F PNL 대체작업","2018-04-09 09:30","2018-04-13 18:00","2018-04-09 09:30","2018-04-13 18:00","연속",null,null,null,201801290180]
[171,"대구","칠곡","서대구고령#2 T/L","서대구S/S 서대구고령#2T/L DS 조작불량 점검 및 장기미동작점검","서대구S/S 서대구고령#2T/L DS 조작불량 점검 및 장기미동작점검","2018-04-05 09:30","2018-04-06 18:00","취소","취소","연속",null,null,null,201802020010]
[172,"대구","칠곡","서대구S/S #4 M.Tr A","서대구S/S #4M.Tr 휴전작업","서대구S/S 7771,7700 GCB 장기미동작점검, 6444하자점검, PT 초기점검","2018-04-02 09:30","2018-04-03 18:00","2018-04-02 09:30","2018-04-03 18:00","연속",null,null,null,201802020004]
[173,"대구","칠곡","북경남서대구#2 T/L","345kV북경남-서대구T/L 항공장애표지구 설치공사","345kV북경남-서대구T/L 항공장애표지구구 설치 안전확보 No.124~125, 161~162","2018-04-24 08:00","2018-04-24 18:00","2018-04-24 08:00","2018-04-24 18:00","당일",null,null,null,201802070204]
[174,"대구","칠곡","북경남서대구#1 T/L","345kV북경남-서대구T/L 항공장애표지구 설치공사","345kV북경남-서대구T/L 항공장애표지구 설치 안전확보 No.124~125, 161~162","2018-04-23 08:00","2018-04-23 18:00","2018-04-23 08:00","2018-04-23 18:00","당일",null,null,null,201802070202]
[175,"대구","칠곡","서대구선산#2 T/L","서대구S/S 78Bay B/F PNL 대체작업","서대구S/S 78Bay B/F PNL 대체작업","2018-04-09 09:30","2018-04-13 18:00","2018-04-09 09:30","2018-04-13 18:00","연속",null,null,null,201801290184]
[176,"대구","포항","신월성N/P #1M.Tr 2차 CB (7472)","2018년 포항전력지사 총액공사","신월성S/Y 7472 CB 보통점검","2018-04-23 09:00","2018-04-23 18:00","2018-04-23 09:00","2018-04-23 18:00","당일",null,null,null,201802130010]
[177,"대구","포항","선산신포항 T/L","345kV 신포항-북대구T/L 지장선로이설공사(임시선로 구성)","345kV 신포항-북대구T/L 지장선로이설공사 ○ 지지물 교체 2기, 전선교체 10.1km 345kV 신포항-북대구T/L 안전이격확보 ○ 지지물 교체 4기, 전선교체 5.6km","2018-04-28 08:00","2018-05-09 18:00","취소","취소","연속",null,null,null,201802060424]
[178,"대구","포항","신포항S/S #4 M.Tr A","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 8DS, T-BUS 철거 등","2018-04-25 08:00","2018-04-25 18:00","취소","취소","당일",null,null,null,201801070012]
[179,"대구","포항","신포항S/S #3 M.Tr A","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 8DS, T-BUS 철거 등","2018-04-23 08:00","2018-04-24 18:00","취소","취소","연속",null,null,null,201801070011]
[180,"대구","포항","신포항신월성NP#3 T/L","345kV 신포항-신월성NP#3,4 T/L 전력선교체공사","31~39호, 71~89호 ACSR 480㎟X4BX2C, 19.252C-km 전력선교체","2018-04-19 07:00","2018-04-28 18:00","2018-04-19 07:00","2018-04-28 18:00","연속",null,null,null,201802060239]
[181,"대구","포항","신포항신월성NP#4 T/L","345kV 신포항-신월성NP#3,4 T/L 전력선교체공사","31~39호, 71~89호 ACSR 480㎟X4BX2C, 19.252C-km 전력선교체","2018-04-29 07:00","2018-05-08 18:00","2018-04-29 07:00","2018-05-08 18:00","연속",null,null,null,201802060240]
[182,"대구","포항","신포항S/S #2 M.Tr A","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 8DS, T-BUS 철거 등","2018-04-16 08:00","2018-04-17 18:00","취소","취소","연속",null,null,null,201802080233]
[183,"대구","포항","신포항S/S #1 M.Tr A","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 8DS, T-BUS 철거 등","2018-04-11 08:00","2018-04-12 18:00","취소","취소","연속",null,null,null,201802080232,"○"]
[184,"대구","포항","신포항북대구 T/L","345kV 신포항-북대구T/L 지장선로이설공사(임시선로 구성)","345kV 신포항-북대구T/L 지장선로이설공사 ○ 지지물 교체 2기, 전선교체 10.1km 345kV 신포항-북대구T/L 안전이격확보 ○ 지지물 교체 4기, 전선교체 5.6km","2018-04-13 08:00","2018-04-27 18:00","취소","취소","연속",null,null,null,201802060422]
[185,"대구","포항","월성2N/P #2 SS Tr 1차 CB (7472)","2018년 포항전력지사 총액공사","월성S/Y 7472 CB 조작시험","2018-04-25 09:00","2018-04-25 18:00","2018-04-25 09:00","2018-04-25 18:00","당일",null,null,null,201802080282]
[186,"대구","포항","월성2N/P F1-#2 SS Tr 1차 CB (7400)","2018년 포항전력지사 총액공사","월성S/Y 7400 CB 보통점검","2018-04-24 09:00","2018-04-24 18:00","2018-04-24 09:00","2018-04-24 18:00","당일",null,null,null,201802080280]
[187,"대구","포항","월성2N/P #2 M.Tr 2차 CB (7372)","2018년 포항전력지사 총액공사","월성S/Y 7372 CB 보통점검","2018-04-05 09:00","2018-04-05 18:00","2018-04-04 09:00","2018-04-04 18:00","당일",null,null,null,201802130005]
[188,"경북","구미","선산S/S #2 M.Tr A","선산S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구-&gtGIS 부하전환 공사","2018-04-23 08:00","2018-04-27 18:00","2018-04-23 08:00","2018-04-27 18:00","연속",null,null,null,201802080315]
[189,"경북","구미","선산S/S #3 M.Tr A","2018년도 구미전력지사 변전협력 총액공사","M.Tr 보통점검, 3차 LA 보통점검, 23kV PT 보통점검 등","2018-04-02 09:00","2018-04-03 18:00","2018-04-02 09:00","2018-04-03 18:00","연속",null,null,null,201802070192]
[190,"경북","영주","한울2N/P 신한울SAT#1T/L-한울연락#3T/L CB (7F00)","한울2발S/Y 362kV GIS 기기점검","한울2발S/Y 362kV 7F00 GIS 하자점검","2018-04-16 14:00","2018-04-16 18:00","2018-04-16 14:00","2018-04-16 18:00","당일",null,null,null,201802050312]
[191,"경북","영주","한울2N/P 한울연락#3T/L CB (7F72)","한울2발S/Y 362kV GIS 기기점검","한울2발S/Y 362kV 7F72 GIS 하자점검","2018-04-17 09:00","2018-04-17 14:00","2018-04-17 09:00","2018-04-17 14:00","당일",null,null,null,201802050313]
[192,"경북","영주","한울2N/P 신한울SAT #1T/L CB (7F71)","한울2발S/Y 362kV GIS 기기점검","한울2발S/Y 362kV GIS 7F71 하자점검","2018-04-16 09:00","2018-04-16 14:00","2018-04-16 09:00","2018-04-16 14:00","당일",null,null,null,201802050310]
[193,"경북","영주","한울2N/P 한울연락#4T/L CB (7G72)","한울2발S/Y 362kV GIS 기기점검","한울2발S/Y 362kV 7G72 GIS 하자점검","2018-04-18 14:00","2018-04-18 18:00","2018-04-18 14:00","2018-04-18 18:00","당일",null,null,null,201802050316]
[194,"경북","영주","한울2N/P 신한울SAT#2T/L-한울연락#4T/L CB (7G00)","한울2발S/Y 362kV GIS 기기점검","한울2발S/Y 362kV 7G00 GIS 하자점검","2018-04-18 09:00","2018-04-18 14:00","2018-04-18 09:00","2018-04-18 14:00","당일",null,null,null,201802050315]
[195,"경북","영주","한울2N/P 신한울SAT #2T/L CB (7G71)","한울2발S/Y 362kV GIS 기기점검","한울2발S/Y 362kV 7G71 GIS 하자점검","2018-04-17 14:00","2018-04-17 18:00","2018-04-17 14:00","2018-04-17 18:00","당일",null,null,null,201802050314]
[196,"경북","영주","신한울한울#2 T/L","2018-19년도 영주전력지사 변전협력업체 총액공사","7E71, 7244 GIS 하자점검[한울3발S/Y 5호기 O/H]","2018-04-03 09:00","2018-04-06 18:00","2018-04-03 09:00","2018-04-06 18:00","연속",null,null,null,201802190276]
[197,"경북","영주","신한울한울#1 T/L","2018-19년도 영주전력지사 변전협력업체 총액공사","7D00, 7D72, 7D71 GIS 초기점검 및 7144 GIS 하자점검 [한울3발S/Y 5호기 M.Tr 휴전]","2018-04-10 09:00","2018-04-13 18:00","2018-04-10 09:00","2018-04-13 18:00","연속",null,null,null,201802120344]
[198,"부산울산","북부산","북부산신온산 T/L","345kV 북부산-울산화력 등 4개T/L 전선접속개소 전선교체공사","345kV 북부산-신온산T/L No.35~39, 74~79, 119~145호 전선교체","2018-04-15 07:00","2018-05-04 18:00","2018-04-15 07:00","2018-05-04 18:00","연속",null,null,null,201802050172]
[199,"부산울산","북부산","북부산S/S 345kV #70 BUS","345kV 북부산S/S 차단기용량대체공사","시험가압 선로(서부산#1T/L 인출변경구간)","2018-04-14 15:00","2018-04-15 15:00","취소","취소","연속",null,null,null,201801080295]
[200,"부산울산","북부산","북부산S/S #4 M.Tr A","북부산S/S 154kV 취약설비 GIS화 공사","북부산S/S 345kV #4M.Tr 2차 인출변경 및 모자익개조","2018-04-04 08:00","2018-04-11 18:00","2018-04-04 08:00","2018-04-11 18:00","연속",null,null,null,201802090041]
[201,"부산울산","북부산","북부산신울산#1 T/L","345kV 북부산S/S 차단기용량대체공사","시험가압선로(서부산#1T/L 인출변경구간)","2018-04-14 15:00","2018-04-15 15:00","취소","취소","연속",null,null,null,201801080299]
[202,"부산울산","울산","동울산신울산#1 T/L","345kV 동울산-신울산#1T/L 피뢰기설치공사","345kV 동울산-신울산#1T/L 피뢰기설치 No.2~34","2018-04-02 07:00","2018-04-05 18:00","2018-04-02 07:00","2018-04-05 18:00","연속",null,null,null,201802080190,"○"]
[203,"부산울산","울산","동울산월성NP#2 T/L","345kV 동울산-월성NP#2 T/L 전선접속개소 전선교체공사","- 전선접속개소 전선교체공사 : 14~17호(4가닥)","2018-04-02 07:00","2018-04-05 18:00","2018-04-02 07:00","2018-04-05 18:00","연속",null,null,null,201802080099]
[204,"부산울산","울산","신울산S/S 신울산#2T/L-#1M.Tr 1차 CB (7100)","345kV LS제 GIS 유사고장방지 공사","신울산S/S 345kV 7100 LS제 GIS 유사고장방지 작업","2018-04-16 09:00","2018-04-22 18:00","2018-04-16 09:00","2018-04-22 18:00","연속",null,null,null,201802090212]
[205,"부산울산","울산","신울산S/S 동울산-신울산#1T/L CB (7872)","345kV LS제 GIS 유사고장방지 공사","신울산S/S 345kV 7872 LS제 GIS 유사고장방지 작업","2018-04-09 09:00","2018-04-15 18:00","2018-04-09 09:00","2018-04-15 18:00","연속",null,null,null,201802090198]
[206,"부산울산","울산","동울산신울산#1 T/L","345kV LS제 GIS 유사고장방지 공사","신울산S/S 345kV 7872 LS제 GIS 유사고장방지 작업관련 시험가압","2018-04-15 17:00","2018-04-15 18:00","2018-04-15 17:00","2018-04-15 18:00","당일",null,null,null,201802090204,"○"]
[207,"부산울산","울산","신울산S/S 북부산-신울산#2T/L CB (7171)","345kV LS제 GIS 유사고장방지 공사","신울산S/S 345kV 7171 LS제 GIS 유사고장방지 작업","2018-04-02 09:00","2018-04-08 18:00","2018-04-02 09:00","2018-04-08 18:00","연속",null,null,null,201802090207]
[208,"부산울산","울산","북부산신울산#2 T/L","345kV LS제 GIS 유사고장방지 공사","신울산S/S 345kV 7171 LS제 GIS 유사고장방지 작업관련 시험가압","2018-04-08 17:00","2018-04-08 18:00","2018-04-08 17:00","2018-04-08 18:00","당일",null,null,null,201802090209]
[209,"부산울산","울산","신울산신온산#1 T/L","345kV LS제 GIS 유사고장방지 공사","신울산S/S 345kV 7800 LS제 GIS 유사고장방지 작업관련 시험가압","2018-04-01 17:00","2018-04-01 18:00","2018-04-01 17:00","2018-04-01 18:00","당일",null,null,null,201802090192]
[210,"부산울산","울산","북부산신울산#2 T/L","345kV LS제 GIS 유사고장방지 공사","신울산S/S 345kV 7100 LS제 GIS 유사고장방지 작업관련 시험가압","2018-04-22 17:00","2018-04-22 18:00","2018-04-22 17:00","2018-04-22 18:00","당일",null,null,null,201802090213]
[211,"부산울산","울산","동울산신울산#2 T/L","345kV 동울산-신울산T/L 51호 지장철탑 이설공사","1. 공사구간 : No.50~52 2.. 철탑교체 : 1기(No.51) 3. 가철탑설치 : 1기(2회선용) 4. 전선교체 : No.50~51 5. 금회 휴전은 가선로 구성(#2T/L) 작업임","2018-04-27 07:00","2018-04-29 18:00","2018-04-27 07:00","2018-04-29 18:00","연속",null,null,null,201802060338]
[212,"경남","직할","신김해창원#1 T/L","신김해S/S 345kV 71BAY B/F PNL 대체공사","신김해S/S 345kV 71BAY B/F PNL 대체공사","2018-04-02 09:00","2018-04-05 18:00","2018-04-02 09:00","2018-04-05 18:00","연속",null,null,null,201802050256]
[213,"경남","직할","신마산신김해#2 T/L","신김해S/S 345kV 71BAY B/F PNL 대체공사","신김해S/S 345kV 71BAY B/F PNL 대체공사","2018-04-02 09:00","2018-04-05 18:00","2018-04-02 09:00","2018-04-05 18:00","연속",null,null,null,201802050254]
[214,"경남","직할","신마산신김해#1 T/L","신김해S/S 345kV 72BAY B/F PNL 대체공사","신김해S/S 345kV 72BAY B/F PNL 대체공사","2018-04-16 09:00","2018-04-19 18:00","2018-04-16 09:00","2018-04-19 18:00","연속",null,null,null,201802050257]
[215,"경남","직할","신김해창원#2 T/L","신김해S/S 345kV 72BAY B/F PNL 대체공사","신김해S/S 345kV 72BAY B/F PNL 대체공사","2018-04-16 09:00","2018-04-19 18:00","2018-04-16 09:00","2018-04-19 18:00","연속",null,null,null,201802050259]
[216,"경남","직할","신김해S/S #3 M.Tr A","신김해S/S 345kV #3M.Tr 보통점검","신김해S/S 345kV #3M.Tr 보통점검","2018-04-09 09:30","2018-04-11 17:30","2018-04-09 09:30","2018-04-11 17:30","연속",null,null,null,201802050272]
[217,"경남","직할","창원삼천포TP#1 T/L","345kV 창원-삼천포화력T/L 전력선교체공사","전력선교체(114-117, 119-120, 129-132)","2018-04-23 07:00","2018-05-01 18:00","2018-04-23 07:00","2018-05-01 18:00","연속",null,null,null,201802060019]
[218,"경남","진주","의령S/S 70-71-0 SEC CB (70-71-0)","의령S/S 70-71-0 SEC CB 보통점검","의령S/S 70-71-0 SEC CB(황색차단기) 보통점검","2018-04-12 09:30","2018-04-12 18:30","2018-04-12 09:30","2018-04-12 18:30","당일",null,null,null,201802050318]
[219,"경남","진주","의령S/S 75-76-0 SEC CB (75-76-0)","의령S/S 75-76-0 SEC CB 보통점검","의령S/S 75-76-0 SEC CB 보통점검","2018-04-13 09:30","2018-04-13 18:30","2018-04-13 09:30","2018-04-13 18:30","당일",null,null,null,201802050319]
[220,"경남","진주","광양하동화력#1 T/L","345kV 광양-하동화력T/L 이도조정","345kV 광양-하동화력T/L 이도조정 - No.3∼7호","2018-04-23 07:00","2018-04-25 18:30","취소","취소","연속",null,null,null,201802060230]
[221,"경남","진주","광양하동화력#2 T/L","345kV 광양-하동화력T/L 이도조정","345kV 광양-하동화력T/L 이도조정 - No.17∼18호","2018-04-09 07:00","2018-04-11 18:30","2018-04-23 07:00","2018-04-25 18:30","연속",null,null,null,201802060227]
[222,"경남","진주","하동T/P 75-76-0 SEC CB (75-76-0)","하동T/P 75-76-0 SEC CB 보통점검","하동T/P 75-76-0 SEC CB 보통점검","2018-04-03 09:30","2018-04-03 18:30","2018-04-03 09:30","2018-04-03 18:30","당일",null,null,null,201802050317]
[223,"경남","통영","삼천포T/P 345kV #71 BUS","삼천포,신고성S/S 345KV 차단기 용량대체공사","SECTION CB(70-71-0) 이설","2018-04-02 09:00","2018-04-03 18:00","2018-04-07 09:00","2018-04-22 18:00","연속",null,null,null,201802050153]
[224,"경남","통영","삼천포T/P 345kV #70 BUS","삼천포,신고성S/S 345KV 차단기 용량대체공사","SECTION CB(70-71-0) 이설","2018-04-18 09:00","2018-04-22 18:00","취소","취소","연속",null,null,null,201802050152]
[225,"경남","통영","삼천포T/P 신고성-삼천포화력#1T/L CB (7A71)","삼천포,신고성S/S 용량부족차단기 대체공사(휴전설비:7A71)","70-71-0 CB 이설후 시험가압(휴전설비 : 차단기 7A71)","2018-04-21 18:00","2018-04-22 18:00","2018-04-21 18:00","2018-04-22 18:00","연속",null,null,null,201802140202]
[226,"경남","통영","삼천포T/P 345kV #71 BUS","삼천포,신고성S/S 345KV 차단기 용량대체공사","SECTION CB(70-71-0) 이설","2018-04-18 09:00","2018-04-22 18:00","취소","취소","연속",null,null,null,201802140181]
[227,"경남","통영","삼천포T/P 345kV #70 BUS","삼천포,신고성S/S 345KV 차단기 용량대체공사","SECTION CB(70-71-0) 이설","2018-04-02 09:00","2018-04-03 18:00","2018-04-07 09:00","2018-04-22 18:00","연속",null,null,null,201802140203]
[228,"경남","통영","삼천포T/P 70-71-0 SEC CB (70-71-0)","삼천포,신고성S/S 345KV 차단기 용량대체공사","SECTION CB(70-71-0) 이설","2018-04-02 09:00","2018-04-22 18:00","2018-04-07 09:00","2018-04-22 18:00","연속",null,null,null,201802050151]
[229,"경남","함안","신마산S/S #3 M.Tr A","345kV 신마산S/S 용량부족차단기 대체공사","#3M.Tr측 전력구 시공관련 안전이격거리 확보(가시설 2차 해체)","2018-04-23 09:30","2018-04-25 18:00","2018-04-23 09:30","2018-04-25 18:00","연속",null,null,null,201802050016]
[230,"경남","함안","신마산S/S #2 M.Tr A","345kV 신마산S/S 용량부족차단기 대체공사","#2M.Tr측 전력구 시공관련 안전이격거리 확보(가시설 1차 해체)","2018-04-26 09:30","2018-04-27 18:00","2018-04-26 09:30","2018-04-27 18:00","연속",null,null,null,201802050018]
[231,"경남","함안","신마산S/S 신김해#1T/L-의령#1T/L CB (7400)","신마산S/S 신마산-신김해#1-의령-신마산#1 GCB 조작시험","신마산S/S 7400 GCB 조작시험","2018-04-30 09:30","2018-04-30 13:30","2018-04-30 09:30","2018-04-30 13:30","당일",null,null,null,201802060494]
[232,"경남","함안","신마산S/S 의령-신마산#1T/L CB (7472)","신마산S/S 의령-신마산#1T/L GCB 조작시험","신마산S/S 7472 GCB 조작시험","2018-04-30 13:30","2018-04-30 17:30","2018-04-30 13:30","2018-04-30 17:30","당일",null,null,null,201802060482]
[233,"경남","함안","신마산S/S #5 M.Tr A","345kV 신마산S/S 용량부족차단기 대체공사","#5M.Tr측 전력구 시공관련 안전이격거리 확보(가시설 2차 해체)","2018-04-04 09:30","2018-04-06 18:00","2018-04-04 09:30","2018-04-06 18:00","연속",null,null,null,201802050015]
[234,"경남","함안","신마산삼천포화력#1 T/L","345kV 신마산-삼천포화력T/L 접속개소 전선교체공사","68~73호, 88~95호간 전력선 교체","2018-04-23 08:00","2018-05-07 18:30","2018-04-23 08:00","2018-05-07 18:30","연속",null,null,null,201802010110]
[235,"경남","함안","신마산S/S #1 M.Tr A","신마산S/S #1M.Tr 차단기 점검","신마산S/S #1M.Tr 차단기 점검 - 7671,7672 조작시험 - 6144 보통점검","2018-04-20 09:30","2018-04-20 17:30","2018-04-20 09:30","2018-04-20 17:30","당일",null,null,null,201802130304]
[236,"인천","시흥","신시흥영흥TP#2 T/L"," 345kV 신시흥영흥#2T/L 피뢰기 및 항공장애표시구 설치공사"," 345kV 신시흥영흥#2T/L 피뢰기 및 항공장애표시구 설치공사","2018-04-25 08:00","2018-04-29 18:00","2018-04-25 08:00","2018-04-29 18:00","연속","연속"]
[237,"인천","시흥","신시흥영흥TP#4 T/L"," 345kV 신시흥영흥#4T/L 피뢰기 및 항공장애표시구 설치공사"," 345kV 신시흥영흥#4T/L 피뢰기 및 항공장애표시구 설치공사","2018-04-25 08:00","2018-04-29 18:00","2018-04-25 08:00","2018-04-29 18:00","연속","연속"]
[238,"인천","시흥","신시흥신안산 T/L"," 345kV 신시흥영흥#4T/L 피뢰기 설치공사","345kV 신시흥영흥#4T/L 피뢰기 설치공사(병가구간) -영흥#4(상단), 신안산(하단)","2018-04-29 08:00","2018-04-29 11:00","2018-04-29 08:00","2018-04-29 11:00","당일","연속"]
[239,"인천","시흥","서서울2-신시흥 #1T/L T/L"," 345kV 신시흥영흥#4T/L 피뢰기 설치공사"," 345kV 신시흥영흥#4T/L 피뢰기 설치공사(병가구간) -영흥#4(상단), 서서울2신시흥#1(하단)","2018-04-29 11:00","2018-04-29 14:00","2018-04-29 11:00","2018-04-29 14:00","당일","연속"]
[240,"인천","시흥","서서울2-신시흥 #2T/L T/L"," 345kV 신시흥영흥#4T/L 항공장애표시구 설치공사"," 345kV 신시흥영흥#4T/L 항공장애표시구 설치공사(병가구간) -영흥#4(상단), 서서울2신시흥#2(하단)","2018-04-29 15:00","2018-04-29 18:00","2018-04-29 15:00","2018-04-29 18:00","당일","연속"]
[241,"부산울산","서부산","부산2CC주변압기 CB(서부산S/S7400,7472)","발전설비 정기검사 및 특성시험","발전설비 정기검사 및 특성시험","2018-04-11 10:00","2018-04-20 18:00","2018-04-11 10:00","2018-04-20 18:00","연속"]
[242,"부산울산","서부산","부산3CC주변압기 CB(서부산S/S 7500,7571)","발전설비 정기검사 및 특성시험","발전설비 정기검사 및 특성시험","2018-04-06 10:00","2018-04-13 18:00","2018-04-06 10:00","2018-04-13 18:00","연속"]

{"sheet":"154송부","index":2,"n_rows":436,"n_cols":16,"rows_kept":436,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2018년도 4월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","방학S/S 154kV #1 BUS TIE CB","2018년 성동P/O 변전협력회사 총액공사","170kV GIS 보통점검 (방학S/S 154kV BUSTIE)","2018-04-20 10:00","2018-04-20 17:00","2018-04-20 10:00","2018-04-20 17:00","당일",null,null,null,201802060604,"-"]
[2,"서울","성동","쌍문S/S 154kV #1 BUS TIE CB","2018년 성동P/O 변전협력회사 총액공사","170kV GIS 보통점검 (쌍문S/S 154kV BUSTIE)","2018-04-18 10:00","2018-04-18 17:00","2018-04-18 10:00","2018-04-18 17:00","당일",null,null,null,201802060597,"-"]
[3,"서울","성동","쌍문미아#1 T/L","2018년 성동P/O 변전협력회사 총액공사","170kV GIS 하자점검 (쌍문,미아S/S 쌍문미아#1T/L)","2018-04-24 10:00","2018-04-24 17:00","2018-04-24 10:00","2018-04-24 17:00","당일",null,null,null,201802210142,"-"]
[4,"서울","성동","쌍문미아#2 T/L","2018년 성동P/O 변전협력회사 총액공사","170kV GIS 하자점검 (쌍문,미아S/S 쌍문미아#2T/L)","2018-04-25 10:00","2018-04-25 17:00","2018-04-25 10:00","2018-04-25 17:00","당일",null,null,null,201802210143,"-"]
[5,"서울","성동","용두S/S 154kV #1 BUS TIE CB","2018년 성동P/O 변전협력회사 총액공사","170kV GIS 보통점검 (용두S/S 154kV BUSTIE)","2018-04-20 10:00","2018-04-20 17:00","2018-04-20 10:00","2018-04-20 17:00","당일",null,null,null,201802080004,"-"]
[6,"서울","성동","창동쌍문#1 T/L","2018년 성동P/O 변전협력회사 총액공사","170kV GIS 보통점검 (창동S/S 창동쌍문#1T/L)","2018-04-26 10:00","2018-04-26 17:00","2018-04-26 10:00","2018-04-26 17:00","당일",null,null,null,201802210144,"-"]
[7,"서울","성동","창동S/S 154kV #1 BUS TIE CB","2018년 성동P/O 변전협력회사 총액공사","170kV GIS 보통점검 (창동S/S 154kV BUSTIE)","2018-04-19 10:00","2018-04-19 17:00","2018-04-19 10:00","2018-04-19 17:00","당일",null,null,null,201802060606,"-"]
[8,"서울","성동","창동쌍문#2 T/L","2018년 성동P/O 변전협력회사 총액공사","170kV GIS 보통점검 (창동S/S 창동쌍문#2T/L)","2018-04-27 10:00","2018-04-27 17:00","2018-04-27 10:00","2018-04-27 17:00","당일",null,null,null,201802210145,"-"]
[9,"서울","성동","성동휘경#1 T/L","2018년 성동P/O 변전협력회사 총액공사","170kV GIS 하자점검 (휘경S/S 성동휘경#1T/L)","2018-04-23 10:00","2018-04-23 17:00","2018-04-23 10:00","2018-04-23 17:00","당일",null,null,null,201802210138,"-"]
[10,"서울","성동","성동휘경#2 T/L","2018년 성동P/O 변전협력회사 총액공사","170kV GIS 하자점검 (성동,휘경S/S 성동휘경#2T/L)","2018-04-03 10:00","2018-04-03 16:00","2018-04-03 10:00","2018-04-03 16:00","당일",null,null,null,201802060578,"-"]
[11,"서울","중부","수색상암#2 T/L","154kV 수색상암#2T/L 피뢰기 열화진단","154kV 수색상암#2T/L 피뢰기 열화진단","2018-04-10 09:00","2018-04-10 18:00","2018-04-10 09:00","2018-04-10 18:00","당일",null,null,null,201802090114,"-"]
[12,"서울","중부","수색상암#1 T/L","154kV 수색상암#1T/L 피뢰기 열화진단","154kV 수색상암#1T/L 피뢰기 열화진단","2018-04-09 09:00","2018-04-09 18:00","2018-04-09 09:00","2018-04-09 18:00","당일",null,null,null,201802090113,"-"]
[13,"서울","중부","원흥수색#2 T/L","154kV 원흥-수색#2T/L 피뢰기설치 공사","154kV 원흥-수색#2T/L No.24~No.27 피뢰기 설치 공사","2018-04-16 08:00","2018-04-16 18:00","2018-04-16 08:00","2018-04-16 18:00","당일",null,null,null,201802090470,"-"]
[14,"서울","중부","옥인서대문 T/L","154kV 옥인 및 운니S/S 인출T/L 교체공사","1. 사 업 명 : 154kV 옥인 및 운니S/S 인출T/L 교체공사 2. 사업목적 : 옥인 및 운니변전소 화재 및 대형 재난사고 예방 3. 사업개요 ○ 사업구간 : 옥인S/S ∼ 옥인인출전력구, 운니S/S 운니인출전력구 ○ 사업내용 - 철거 : 154kV OF 2000㎟ 4C, OF 1200㎟ 4C 총길이1.4㎞ - 신설 : 154kV XL","2018-04-23 09:00","2018-06-01 18:00","2018-04-25 09:00","2018-06-01 18:00","연속",null,null,null,201802200282,"-"]
[15,"서울","중부","중부S/S 154kV #1 BUS TIE GIS","2018 중부P/O 변전협력회사 총액공사","중부S/S 6100B/T GIS 보통점검","2018-04-05 10:00","2018-04-05 17:00","2018-04-05 10:00","2018-04-05 17:00","당일",null,null,null,201802120365,"-"]
[16,"서울","직할","중앙서소문 T/L","18년 직할 변전협력 총액공사","효성제 170kV GIS Spring Charging 관련 경보회로 개선 및 조작시험","2018-04-27 10:00","2018-04-27 18:00","2018-04-27 10:00","2018-04-27 18:00","당일",null,null,null,201802090545,"-"]
[17,"서울","직할","아현서소문 T/L","18년 직할 변전협력 총액공사","효성제 170kV GIS Spring Charging 관련 경보회로 개선 및 조작시험","2018-04-25 10:00","2018-04-25 18:00","2018-04-25 10:00","2018-04-25 18:00","당일",null,null,null,201802090531,"-"]
[18,"서울","직할","종로서소문 T/L","18년 변전협력 총액공사","효성제 170kV GIS Spring Charging 관련 경보회로 개선 및 조작시험","2018-04-26 10:00","2018-04-26 18:00","2018-04-26 10:00","2018-04-26 18:00","당일",null,null,null,201802090534,"-"]
[19,"남서울","강남","논일역삼#1 T/L","논일S/S 변전설비 기기점검공사","논일S/S 논일-역삼#1T/L GIS 초기점검 역삼S/S 논일-역삼#1T/L GIS 보통점검","2018-04-20 10:00","2018-04-20 14:00","2018-04-20 10:00","2018-04-20 14:00","당일",null,null,null,201802120376,"-"]
[20,"남서울","강남","논일역삼#2 T/L","논일S/S 변전설비 기기점검공사","논일S/S 논일-역삼#2T/L GIS 초기점검 역삼S/S 논일-역삼#2T/L GIS 보통점검","2018-04-20 14:00","2018-04-20 18:00","2018-04-20 14:00","2018-04-20 18:00","당일",null,null,null,201802120381,"-"]
[21,"남서울","강남","논현논일#2 T/L","170kV GIS 조작시험 및 개폐타임측정","논현,논일S/S 논현-논일#2T/L GIS 개폐타임측정 논일S/S 논현-논일#2T/L 모선ES 보수(제작사)","2018-04-05 14:00","2018-04-05 18:00","2018-04-05 14:00","2018-04-05 18:00","당일",null,null,null,201802120406,"-"]
[22,"남서울","강남","논현논일#1 T/L","170kV GIS 조작시험 및 개폐타임측정","논현,논일S/S 논현-논일#1T/L GIS 개폐타임측정","2018-04-05 10:00","2018-04-05 14:00","2018-04-05 10:00","2018-04-05 14:00","당일",null,null,null,201802120403,"-"]
[23,"남서울","강남","신양재신사#1 T/L","신사S/S 170kV GIS 정밀점검공사","신사S/S 신양재-신사#1T/L GIS 정밀점검 신양재S/S 신양재-신사#1T/L GIS 보통점검","2018-04-10 10:00","2018-04-11 18:00","2018-04-10 10:00","2018-04-11 18:00","연속",null,null,null,201802120341,"-"]
[24,"남서울","강남","신양재신사#2 T/L","신사S/S 170kV GIS 정밀점검공사","신사S/S 신양재-신사#2T/L GIS 정밀점검 신양재S/S 신양재-신사#2T/L GIS 보통점검","2018-04-12 10:00","2018-04-13 18:00","2018-04-12 10:00","2018-04-13 18:00","연속",null,null,null,201802120342,"-"]
[25,"남서울","강남","신양재과천#1 T/L","345kV 신양재S/S 154kV측 인출선로 재배치 공사","1. 목적 : 인출Bay 재조정을 통한 양모선 고장 시 대규모 정전방지 2. 구간 : 신양재S/S~J/B#1, 2Cx0.21km / 신양재S/S~J/B#24, 2Cx0.215km 3. 대상 : 신양재-역삼#1,2 ↔ 신양재-과천#1,2","2018-04-02 09:00","2018-05-14 18:00","2018-04-02 09:00","2018-05-14 18:00","연속",null,null,null,201802140263,"-"]
[26,"남서울","강남","신양재역삼#2 T/L","345kV 신양재S/S 154kV측 인출선로 재배치 공사","1. 목적 : 인출Bay 재조정을 통한 양모선 고장 시 대규모 정전방지 2. 구간 : 신양재S/S~J/B#1, 2Cx0.21km / 신양재S/S~J/B#24, 2Cx0.215km 3. 대상 : 신양재-역삼#1,2 ↔ 신양재-과천#1,2","2018-04-02 09:00","2018-05-14 18:00","2018-04-02 09:00","2018-05-14 18:00","연속",null,null,null,201802140261,"-"]
[27,"남서울","동서울","강남선릉#2 T/L","차단기 조작시험","차단기 조작시험","2018-04-09 14:00","2018-04-09 18:00","2018-04-09 14:00","2018-04-09 18:00","당일",null,null,null,201802130196,"-"]
[28,"남서울","동서울","강남선릉#1 T/L","차단기 조작시험","차단기 조작시험","2018-04-09 09:00","2018-04-09 14:00","2018-04-09 09:00","2018-04-09 14:00","당일",null,null,null,201802130195,"-"]
[29,"남서울","동서울","동남위례열병합#1 T/L","154kV 동남-위례-위례열병합 지중T/L 건설공사","154kV 동남-위례-위례열병합 지중T/L 건설공사&ltbr>- 154kV 동남-위례열병합 T/L 분기점 ~ 위례S/S 2pi 분기&ltbr>- 154kV XLPE 2000SQ 4C-0.2km","2018-04-29 09:00","2018-05-17 18:00","2018-04-29 09:00","2018-05-17 18:00","연속",null,null,null,201802120063,"-"]
[30,"남서울","동서울","동남수서 T/L","170kV GIS 보통점검","170kV GIS 보통점검(수서), 조작시험(동남)","2018-04-16 10:00","2018-04-16 18:00","2018-04-16 10:00","2018-04-16 18:00","당일",null,null,null,201802130173,"-"]
[31,"남서울","동서울","동남위례열병합#2 T/L","154kV 동남-위례-위례열병합 지중T/L 건설공사","154kV 동남-위례-위례열병합 지중T/L 건설공사&ltbr>- 154kV 동남-위례열병합 T/L 분기점 ~ 위례S/S 2pi 분기&ltbr>- 154kV XLPE 2000SQ 4C-0.2km","2018-04-12 09:00","2018-04-28 18:00","2018-04-12 09:00","2018-04-28 18:00","연속",null,null,null,201802120055,"-"]
[32,"남서울","동서울","가락동남 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2018-04-17 10:00","2018-04-17 18:00","2018-04-17 10:00","2018-04-17 18:00","당일",null,null,null,201802130175,"-"]
[33,"남서울","동서울","천호구의#1 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2018-04-16 09:00","2018-04-18 14:00","2018-04-16 09:00","2018-04-18 14:00","연속",null,null,null,201802130163,"-"]
[34,"남서울","동서울","강동천호#1 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검(천호), 조작시험(강동)","2018-04-09 09:00","2018-04-11 14:00","2018-04-09 09:00","2018-04-11 14:00","연속",null,null,null,201802130161,"-"]
[35,"남서울","동서울","강동천호#2 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검(천호), 조작시험(강동)","2018-04-11 14:00","2018-04-13 18:00","2018-04-11 14:00","2018-04-13 18:00","연속",null,null,null,201802130162,"-"]
[36,"남서울","동서울","천호구의#2 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2018-04-18 14:00","2018-04-20 18:00","2018-04-18 14:00","2018-04-20 18:00","연속",null,null,null,201802130164,"-"]
[37,"남서울","영등포","광명구공#1 T/L","2018~19 영등포전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2018-04-02 09:00","2018-04-02 18:00","2018-04-02 09:00","2018-04-02 18:00","당일",null,null,null,201802120545,"-"]
[38,"남서울","영등포","광명구공#2 T/L","2018~19 영등포전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2018-04-03 09:00","2018-04-03 18:00","2018-04-03 09:00","2018-04-03 18:00","당일",null,null,null,201802120548,"-"]
[39,"남서울","영등포","광명구공#3 T/L","2018~19 영등포전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2018-04-13 09:00","2018-04-13 18:00","2018-04-13 09:00","2018-04-13 18:00","당일",null,null,null,201802120549,"-"]
[40,"남서울","영등포","마곡가양#2 T/L","2018~19 영등포전력지사 변전협력회사 총액공사","170kV GIS 차단기 조작시험","2018-04-27 14:00","2018-04-27 18:00","2018-04-27 14:00","2018-04-27 18:00","당일",null,null,null,201802120495,"-"]
[41,"남서울","영등포","마곡가양#1 T/L","2018~19 영등포전력지사 변전협력회사 총액공사","170kV GIS 차단기 조작시험","2018-04-27 09:00","2018-04-27 14:00","2018-04-27 09:00","2018-04-27 14:00","당일",null,null,null,201802120493,"-"]
[42,"남서울","영등포","양평양천#2 T/L","2018~19 영등포전력지사 변전협력회사 총액공사","양천S/S 170kV GIS 보통점검","2018-04-04 09:00","2018-04-04 18:00","2018-04-04 09:00","2018-04-04 18:00","당일",null,null,null,201802120554,"-"]
[43,"남서울","영등포","양평양천#1 T/L","2018~19 영등포전력지사 변전협력회사 총액공사","양천S/S 170kV GIS 차단기 조작시험","2018-04-03 09:00","2018-04-03 18:00","2018-04-03 09:00","2018-04-03 18:00","당일",null,null,null,201802190301,"-"]
[44,"남서울","영등포","천왕구로#2 T/L","2018~19 영등포전력지사 변전협력회사 총액공사","170kV GIS 차단기 조작시험","2018-04-19 09:00","2018-04-19 18:00","2018-04-19 09:00","2018-04-19 18:00","당일",null,null,null,201802120482,"-"]
[45,"남서울","영등포","천왕구로#1 T/L","2018~19 영등포전력지사 변전협력회사 총액공사","170kV GIS 차단기 조작시험","2018-04-17 09:00","2018-04-17 18:00","2018-04-17 09:00","2018-04-17 18:00","당일",null,null,null,201802120481,"-"]
[46,"남서울","직할","대방신길#2 T/L","신길S/S 대방-신길#2T/L 하자점검","신길변전소 대방-신길#2T/L 하자점검","2018-04-16 14:00","2018-04-16 18:00","2018-04-16 14:00","2018-04-16 18:00","당일",null,null,null,201802090124,"-"]
[47,"남서울","직할","대방신길#1 T/L","신길S/S 대방-신길#1T/L 하자점검","신길변전소 대방-신길#1T/L 하자점검","2018-04-16 10:00","2018-04-16 14:00","2018-04-16 10:00","2018-04-16 14:00","당일",null,null,null,201802090123,"-"]
[48,"남서울","직할","영등포양평#1 T/L","영등포-양평#1T/L 보통점검","양평S/S 영등포-양평#1T/L 보통점검","2018-04-09 09:00","2018-04-09 14:00","2018-04-09 09:00","2018-04-09 14:00","당일",null,null,null,201802120065,"-"]
[49,"남서울","직할","영등포양평#2 T/L","영등포-양평#2T/L 보통점검","양평S/S 영등포-양평#2T/L 보통점검","2018-04-09 14:00","2018-04-09 18:00","2018-04-09 14:00","2018-04-09 18:00","당일",null,null,null,201802120070,"-"]
[50,"인천","김포","경서양촌#2 T/L","경서S/S 154kV 경서-양촌#2T/L GIS 보통점검","1. 경서S/S 154kV 경서-양촌#2T/L GIS(687 CB) 보통점검 2. 양촌S/S 154kV 경서-양촌#2T/L GIS(637 CB) 보통점검","2018-04-09 10:00","2018-04-09 18:00","2018-04-09 10:00","2018-04-09 18:00","당일",null,null,null,201802140100,"-"]
[51,"인천","김포","왕길양촌#2 T/L","왕길S/S 154kV 왕길양촌#2T/L GIS 초기점검","왕길S/S 154kV 왕길양촌#2T/L GIS 초기점검","2018-04-06 10:00","2018-04-06 18:00","2018-04-06 10:00","2018-04-06 18:00","당일",null,null,null,201802210005,"-"]
[52,"인천","김포","왕길양촌#1 T/L","왕길S/S 154kV 왕길양촌#1T/L GIS 초기점검","왕길S/S 154kV 왕길양촌#1T/L GIS 초기점검","2018-04-05 10:00","2018-04-05 18:00","2018-04-05 10:00","2018-04-05 18:00","당일",null,null,null,201802210004,"-"]
[53,"인천","김포","신경서왕길#2 T/L","왕길S/S 154kV 신경서왕길#2T/L GIS 보통점검","왕길S/S 154kV 신경서왕길#2T/L GIS 보통점검","2018-04-04 10:00","2018-04-04 18:00","2018-04-04 10:00","2018-04-04 18:00","당일",null,null,null,201802210003,"-"]
[54,"인천","김포","신경서왕길#1 T/L","왕길S/S 154kV 신경서왕길#1T/L GIS 보통점검","왕길S/S 154kV 신경서왕길#1T/L GIS 보통점검","2018-04-03 10:00","2018-04-03 18:00","2018-04-03 10:00","2018-04-03 18:00","당일",null,null,null,201802210002,"-"]
[55,"인천","김포","신김포장기#1 T/L","장기S/S 154kV 신김포장기#1T/L GIS 조작시험","장기S/S 154kV 신김포장기#1T/L GIS 조작시험","2018-04-10 09:00","2018-04-10 18:00","2018-04-10 09:00","2018-04-10 18:00","당일",null,null,null,201802210006,"-"]
[56,"인천","김포","신김포장기#2 T/L","장기S/S 154kV 신김포장기#2T/L GIS 조작시험","장기S/S 154kV 신김포장기#2T/L GIS 조작시험","2018-04-11 09:00","2018-04-11 18:00","2018-04-11 09:00","2018-04-11 18:00","당일",null,null,null,201802210007,"-"]
[57,"인천","시흥","신시흥도림 T/L","도림S/S 신시흥도림 T/L GIS 보통점검","도림S/S 신시흥도림 T/L GIS 보통점검","2018-04-07 09:00","2018-04-07 18:00","2018-04-07 09:00","2018-04-07 18:00","당일",null,null,null,201802140255,"-"]
[58,"인천","시흥","시화동시화#2 T/L","동시화S/S 시화동시화#2 T/L GIS 보통점검","동시화S/S 시화동시화#2 T/L GIS 보통점검","2018-04-06 10:00","2018-04-06 18:00","2018-04-06 10:00","2018-04-06 18:00","당일",null,null,null,201802140258,"-"]
[59,"인천","시흥","북시화S/S 154kV #2 BUS","북시화S/S 북시화서시화#3T/L GIS 정밀점검","북시화S/S 북시화서시화#3T/L GIS 정밀점검(무부하가압용)","2018-04-12 15:00","2018-04-12 18:00","취소","취소","당일",null,null,null,201802140233,"-"]
[60,"인천","시흥","북시화서시화#3 T/L","북시화S/S 북시화서시화#3T/L GIS 정밀점검","북시화S/S 북시화서시화#3T/L GIS 정밀점검","2018-04-11 08:00","2018-04-14 18:00","취소","취소","연속",null,null,null,201802140232,"-"]
[61,"인천","시흥","북시화S/S 154kV #2 BUS","북시화S/S #5 M.Tr 1차GIS 정밀점검","북시화S/S #5 M.Tr 1차GIS 정밀점검(무부하가압용)","2018-04-10 15:00","2018-04-10 18:00","취소","취소","당일",null,null,null,201802140229,"-"]
[62,"인천","시흥","동시화서시화 T/L","서시화S/S 154kV 동시화서시화 T/L GIS 정밀점검","서시화S/S 154kV 동시화서시화 T/L GIS 정밀점검","2018-04-18 08:00","2018-04-19 18:00","2018-04-18 08:00","2018-04-19 18:00","연속",null,null,null,201802140240,"-"]
[63,"인천","시흥","북시화서시화#1 T/L","서시화S/S 154kV #1 BUS TIE GIS 정밀점검(무부하)","서시화S/S 154kV #1 BUS TIE GIS 정밀점검(무부하)","2018-04-17 15:00","2018-04-17 18:00","2018-04-17 15:00","2018-04-17 18:00","당일",null,null,null,201802140239,"-"]
[64,"인천","시흥","온수소래 T/L","154kV 서안양소래T/L 항공장애표시구 설치공사","154kV 서안양소래T/L 항공장애표시구 설치공사 (온수소래T/L(상단) - 서안양소래T/L(하단), 병가)","2018-04-15 08:00","2018-04-15 18:00","2018-04-15 08:00","2018-04-15 18:00","당일",null,null,null,201802200337,"-"]
[65,"인천","시흥","소래S/S 154kV #2 BUS","소래S/S #4M.Tr 1차GIS 정밀점검","소래S/S #4M.Tr 1차GIS 정밀점검(무부하가압용)","2018-04-03 15:00","2018-04-03 18:00","취소","취소","당일",null,null,null,201802200339,"-"]
[66,"인천","시흥","서안양소래 T/L","154kV 서서울소래T/L 안전이격거리 확보공사","* 대상철탑 : No.73(관형지지물신설), No.74(인클로징철탑) * 시공내용 : 철탑 신설 및 전력선 가선작업 등 (추가공사 : 항공장애표시구 설치공사)","2018-04-15 08:00","2018-04-18 18:00","2018-04-15 08:00","2018-04-18 18:00","연속",null,null,null,201802120245,"-"]
[67,"인천","시흥","서서울#2소래 T/L","154kV 서서울소래T/L 안전이격거리 확보공사","* 대상철탑 : No.73(관형지지물신설), No.74(인클로징철탑) * 시공내용 : 철탑 신설 및 전력선 가선작업 등","2018-04-16 08:00","2018-04-18 18:00","2018-04-16 08:00","2018-04-18 18:00","연속",null,null,null,201802120243,"-"]
[68,"인천","인천","주안관교#1 T/L","절연유 시료채취 및 채유밸브 설치","절연유 시료채취 및 채유밸브 설치","2018-04-16 09:00","2018-04-16 18:00","2018-04-16 09:00","2018-04-16 18:00","당일",null,null,null,201801300015,"-"]
[69,"인천","인천","주안관교#2 T/L","절연유 시료채취 및 채유밸브 설치","절연유 시료채취 및 채유밸브 설치","2018-04-17 09:00","2018-04-17 18:00","2018-04-17 09:00","2018-04-17 18:00","당일",null,null,null,201801300016,"-"]
[70,"인천","인천","서인천C/C 154kV #65 BUS","서인천CC RTU대체공사관련 PT회로변경 공사","서인천CC RTU대체공사관련 PT회로변경 공사","2018-04-25 14:00","2018-04-25 18:00","2018-04-25 14:00","2018-04-25 18:00","당일",null,null,null,201802210063,"-"]
[71,"인천","인천","서인천C/C 154kV #60 BUS","서인천CC RTU대체공사관련 PT회로변경 공사","서인천CC RTU대체공사관련 PT회로변경 공사","2018-04-25 09:00","2018-04-25 14:00","2018-04-25 09:00","2018-04-25 14:00","당일",null,null,null,201802210062,"-"]
[72,"인천","인천","서인천C/C 154kV #66 BUS","서인천CC RTU대체공사관련 PT회로변경 공사","서인천CC RTU대체공사관련 PT회로변경 공사","2018-04-26 14:00","2018-04-26 18:00","2018-04-26 14:00","2018-04-26 18:00","당일",null,null,null,201802210065,"-"]
[73,"인천","인천","서인천C/C 154kV #61 BUS","서인천CC RTU대체공사관련 PT회로변경 공사","서인천CC RTU대체공사관련 PT회로변경 공사","2018-04-26 09:00","2018-04-26 14:00","2018-04-26 09:00","2018-04-26 14:00","당일",null,null,null,201802210064,"-"]
[74,"인천","인천","신현송현#1 T/L","신현S/S 170kV GIS 대체공사(3차)","○ 신현S/S 170kV GIS 대체공사(#2M.Tr, 신현송현#1T/L, 154kV PT)_3차 - '18.04.02 ~ 04.16 : 건축공사(가설공사 및 벽면철거) - '18.04.17 ~ 05.18 : 변전공사 ☞ #2M.Tr, 신현송현#1T/L, 154kV PT 대체 및 구 BUS-TIE 철거","2018-04-02 08:00","2018-05-18 18:00","2018-04-02 08:00","2018-05-18 18:00","연속",null,null,null,201802120009,"-"]
[75,"인천","인천","신현S/S 154kV #1 BUS","신현S/S 170kV GIS 대체공사(3차)","○ 신현S/S 170kV GIS 대체공사(#2M.Tr, 신현송현#1T/L, 154kV PT)_3차 ☞ #2M.Tr, 신현송현#1T/L, 154kV PT 대체 및 구 BUS-TIE 철거","2018-04-26 08:00","2018-05-03 18:00","2018-04-26 08:00","2018-05-03 18:00","연속",null,null,null,201802120016,"-"]
[76,"인천","인천","신가좌신현#1 T/L","신현S/S 170kV GIS 대체공사(3차)_#2BUS무부하","○ 신현S/S 170kV GIS 대체공사(#2M.Tr, 신현송현#1T/L, 154kV PT)_3차 ☞ #2M.Tr, 신현송현#1T/L, 154kV PT 대체 및 구 BUS-TIE 철거 ☞ #2BUS 무부하","2018-04-24 18:00","2018-04-25 18:00","2018-04-24 18:00","2018-04-25 18:00","연속",null,null,null,201802120015,"-"]
[77,"인천","인천","신현S/S 154kV #2 BUS","신현S/S 170kV GIS 대체공사(3차)","○ 신현S/S 170kV GIS 대체공사(#2M.Tr, 신현송현#1T/L, 154kV PT)_3차 ☞ #2M.Tr, 신현송현#1T/L, 154kV PT 대체 및 구 BUS-TIE 철거","2018-04-21 08:00","2018-04-25 18:00","2018-04-21 08:00","2018-04-25 18:00","연속",null,null,null,201802120013,"-"]
[78,"인천","인천","신가좌신현#1 T/L","신현S/S 170kV GIS 대체공사(3차)_#1BUS무부하","○ 신현S/S 170kV GIS 대체공사(#2M.Tr, 신현송현#1T/L, 154kV PT)_3차 ☞ #2M.Tr, 신현송현#1T/L, 154kV PT 대체 및 구 BUS-TIE 철거 ☞ #1BUS 무부하","2018-04-29 18:00","2018-04-30 18:00","2018-04-29 18:00","2018-04-30 18:00","연속",null,null,null,201802120020,"-"]
[79,"인천","인천","신현S/S 154kV #1 BUS","신현S/S 170kV GIS 대체공사(3차)","○ 신현S/S 170kV GIS 대체공사(#2M.Tr, 신현송현#1T/L, 154kV PT)_3차 ☞ #2M.Tr, 신현송현#1T/L, 154kV PT 대체 및 구 BUS-TIE 철거 ☞ #1BUS PT라인 임시PNL 이설","2018-04-17 08:00","2018-04-17 12:00","2018-04-17 08:00","2018-04-17 12:00","연속",null,null,null,201802120011,"-"]
[80,"인천","인천","영종S/S 공항열병합#2T/L CB","영종S/S 공항열병합#2T/L 보호반 대체공사","영종S/S 공항열병합#2T/L 보호반 대체공사","2018-04-23 09:00","2018-04-27 18:00","2018-04-23 09:00","2018-04-27 18:00","연속",null,null,null,201802200173,"-"]
[81,"인천","인천","영종S/S 공항열병합#1T/L CB","영종S/S 공항열병합#1T/L 보호반 대체공사","영종S/S 공항열병합#1T/L 보호반 대체공사","2018-04-16 09:00","2018-04-20 18:00","2018-04-16 09:00","2018-04-20 18:00","연속",null,null,null,201802200172,"-"]
[82,"인천","직할","계양북인천 T/L","계양S/S 계양북인천T/L 170kV GIS 보통점검","계양S/S 계양북인천T/L 170kV GIS 보통점검","2018-04-12 09:30","2018-04-12 18:00","2018-04-12 09:30","2018-04-12 18:00","당일",null,null,null,201802140337,"-"]
[83,"인천","직할","고강S/S 154kV #1 BUS","고강S/S #3M.Tr 1차 170kV GIS 정밀점검","고강S/S #3M.Tr 1차 170kV GIS 정밀점검(무부하가압)","2018-04-20 13:00","2018-04-20 16:00","2018-04-20 13:00","2018-04-20 16:00","당일",null,null,null,201802140332,"-"]
[84,"인천","직할","부개S/S 154kV #1 BUS","부개S/S #1M.Tr 1차 170kV GIS 정밀점검","부개S/S #1M.Tr 1차 170kV GIS 정밀점검(무부하 가압)","2018-04-24 13:00","2018-04-24 16:00","2018-04-24 13:00","2018-04-24 16:00","당일",null,null,null,201802140313,"-"]
[85,"인천","직할","부개S/S 154kV #1 BUS","부개S/S #3M.Tr 1차 170kV GIS 정밀점검","부개S/S #3M.Tr 1차 170kV GIS 정밀점검(무부하 가압)","2018-04-28 13:00","2018-04-28 16:00","2018-04-28 13:00","2018-04-28 16:00","연속",null,null,null,201802140324,"-"]
[86,"인천","직할","부개S/S 154kV #1 BUS","부개S/S #2M.Tr 1차 170kV GIS 정밀점검","부개S/S #2M.Tr 1차 170kV GIS 정밀점검(무부하 가압)","2018-04-26 13:00","2018-04-26 16:00","2018-04-26 13:00","2018-04-26 16:00","연속",null,null,null,201802140315,"-"]
[87,"인천","직할","신부평중동#1 T/L","154kV 신부평-중동 등 3개T/L 신부평변전소 인출Bay 정비공사","345kV 신부평변전소 154kV 지중T/L 인출Bay 정비(신부평S/S~J/B#1)","2018-04-30 09:00","2018-05-22 18:00","2018-04-30 09:00","2018-05-22 18:00","연속",null,null,null,201802010126,"-"]
[88,"경기북부","고양","양주고양#1 T/L","18~19 고양전력지사 변전협력총액공사","양주-고양#1T/L GIS 하자점검","2018-04-04 10:00","2018-04-04 18:00","2018-04-04 10:00","2018-04-04 18:00","당일",null,null,null,201802090072,"○"]
[89,"경기북부","고양","양주고양#2 T/L","18~19 고양전력지사 변전협력총액공사","양주-고양#2T/L GIS 하자점검","2018-04-05 10:00","2018-04-05 18:00","2018-04-05 10:00","2018-04-05 18:00","당일",null,null,null,201802090073,"-"]
[90,"경기북부","고양","고양일산#2 T/L","18~19 고양전력지사 변전협력총액공사","고양-일산#2T/L GIS 하자점검","2018-04-12 10:00","2018-04-12 18:00","2018-04-12 10:00","2018-04-13 18:00","당일",null,null,null,201802090077,"-"]
[91,"경기북부","고양","양주금촌#1 T/L","18~19 고양전력지사 변전협력총액공사","양주-금촌#1T/L GIS 보통점검","2018-04-24 10:00","2018-04-24 18:00","2018-04-24 10:00","2018-04-24 18:00","당일",null,null,null,201802090092,"-"]
[92,"경기북부","고양","양주금촌#2 T/L","18~19 고양전력지사 변전협력총액공사","양주-금촌#2T/L GIS 보통점검","2018-04-25 10:00","2018-04-25 18:00","2018-04-25 10:00","2018-04-25 18:00","당일",null,null,null,201802090094,"-"]
[93,"경기북부","고양","남면백석#1 T/L","345kV 신덕은-동두천CC#1T/L 정밀점검","345kV 신덕은-동두천CC#1T/L 정밀점검 병가구간 병행휴전 - 병행구간 : 345kV 신덕은-동두천CC No.77~101 (남면-백석No.3~27)","2018-04-18 09:00","2018-04-20 18:00","2018-04-18 09:00","2018-04-20 18:00","연속",null,null,null,201802120339,"-"]
[94,"경기북부","고양","지도능곡#1 T/L","18~19 고양전력지사 변전협력총액공사","지도-능곡#1T/L GIS 보통점검","2018-04-03 10:00","2018-04-03 18:00","2018-04-03 10:00","2018-04-03 18:00","당일",null,null,null,201802090069,"-"]
[95,"경기북부","고양","덕이호수#1 T/L","일진전기제 154kV 구형 PMJ접속함 교체공사(덕이호수#1T/L)","R-type 조립식 접속함 고장 지속발생에 따른 제작사 주관 리콜공사 - 공사주관 : 일진전기 - 교체대상 : 154kV 덕이-호수#1T/L J/B#1,2,3,6,7,8(총18상) - 작업팀 : 3팀 - 작업일정 : 2018. 4. 2 - 14. 끝.","2018-04-02 08:00","2018-04-14 18:00","2018-04-02 08:00","2018-04-14 18:00","연속",null,null,null,201802090111,"-"]
[96,"경기북부","고양","덕이호수#2 T/L","일진전기제 154kV 구형 PMJ접속함 교체공사(덕이호수#2T/L)","R-type 조립식 접속함 고장 지속발생에 따른 제작사 주관 리콜공사 - 공사주관 : 일진전기 - 교체대상 : 154kV 덕이-호수#2T/L J/B#1,2,3,6,7,8(총18상) - 작업팀 : 3팀 - 작업일정 : 2018. 4. 23 - 5.5. 끝.","2018-04-23 08:00","2018-05-05 18:00","2018-04-15 08:00","2018-04-27 18:00","연속",null,null,null,201802090112,"-"]
[97,"경기북부","고양","문산월롱#2 T/L","154kV 문산-평화 등 2개T/L 지장송전선로 이설공사","문산천 문산지구 하천정비 지장송전선로 이설공사","2018-04-21 08:00","2018-04-25 18:00","2018-04-22 08:00","2018-04-26 18:00","연속",null,null,null,201802120293,"-"]
[98,"경기북부","고양","문산월롱#1 T/L","154kV 문산-평화 등 2개T/L 지장송전선로 이설공사","문산천 문산지구 하천정비 지장송전선로 이설공사","2018-04-16 08:00","2018-04-20 18:00","2018-04-17 08:00","2018-04-21 18:00","연속",null,null,null,201802120289,"-"]
[99,"경기북부","고양","백학남면#2 T/L","2018년 가공송전선로 순시점검 위탁공사","154kV 백학-남면#2T/L 정밀점검","2018-04-23 08:00","2018-04-25 18:00","2018-04-23 08:00","2018-04-25 18:00","연속",null,null,null,201802130062,"-"]
[100,"경기북부","고양","백학남면#1 T/L","2018년 가공송전선로 순시점검 위탁공사","154kV 백학-남면#1T/L 정밀점검","2018-04-13 08:00","2018-04-17 18:00","2018-04-13 08:00","2018-04-17 18:00","연속",null,null,null,201802130065,"-"]
[101,"경기북부","고양","신파주송포#2 T/L","송포S/S 170kV GIS 교체공사","1. 공사개요 : 송포S/S 170kV GIS 7CCT 철거/설치 - 대상 :#1,2M.Tr 1차측, 일산송포#1,2T/L, B/T, S.C, BUS PT 2. 신파주-송포#2T/L(637) 휴전 사유 - #1M.Tr 1차측, 일산송포#1T/L, B/T, BUS PT 교체시 시험가압용 - B/T를 통한 시험가압 불가로 송전선로 선정","2018-04-12 18:00","2018-04-13 08:00","2018-04-12 18:00","2018-04-13 08:00","연속",null,null,null,201802120076,"-"]
[102,"경기북부","고양","신파주송포#2 T/L","송포S/S 170kV GIS 교체공사","1. 공사개요 : 송포S/S 170kV GIS 7CCT 철거/설치 - 대상 :#1,2M.Tr 1차측, 일산송포#1,2T/L, B/T, S.C, BUS PT 2. 신파주-송포#2T/L(637) 휴전 사유 - #1M.Tr 1차측, 일산송포#1T/L, B/T, BUS PT 교체시 시험가압용 - B/T를 통한 시험가압 불가로 송전선로 선정","2018-04-21 18:00","2018-04-23 08:00","2018-04-21 18:00","2018-04-23 08:00","연속",null,null,null,201802120086,"-"]
[103,"경기북부","고양","신덕은S/S 154kV #2 BUS TIE GIS","154kV 이상 차단기 조작시험(신덕은 6200B/T)","154kV 이상 차단기 조작시험(신덕은 6200B/T)","2018-04-23 13:00","2018-04-23 17:00","2018-04-23 13:00","2018-04-23 17:00","당일",null,null,null,201802090150,"-"]
[104,"경기북부","고양","신덕은S/S 154kV #1 BUS TIE GIS","154kV 이상 차단기 조작시험(신덕은 6100B/T)","154kV 이상 차단기 조작시험(신덕은 6100B/T)","2018-04-23 09:30","2018-04-23 12:00","2018-04-23 09:30","2018-04-23 12:00","당일",null,null,null,201802090149,"-"]
[105,"경기북부","고양","신덕은문산#2 T/L","154kV 문산-평화 등 2개T/L 지장송전선로 이설공사","문산천 문산지구 하천정비 지장송전선로 이설공사(병가선로)","2018-04-22 08:00","2018-04-26 18:00","2018-04-22 08:00","2018-04-26 18:00","연속",null,null,null,201802120295,"-"]
[106,"경기북부","고양","신덕은문산#1 T/L","154kV 문산-평화 등 2개T/L 지장송전선로 이설공사","문산천 문산지구 하천정비 지장송전선로 이설공사 (병가선로)","2018-04-17 08:00","2018-04-21 18:00","2018-04-17 08:00","2018-04-21 18:00","연속",null,null,null,201802120291,"-"]
[107,"경기북부","고양","고양일산#1 T/L","18~19 고양전력지사 변전협력총액공사","고양-일산#1T/L GIS 하자점검","2018-04-11 10:00","2018-04-11 18:00","2018-04-10 10:00","2018-04-11 18:00","당일",null,null,null,201802090079,"○"]
[108,"경기북부","구리","덕소마석#2 T/L","154kV 덕소-마석#2T/L 송전선로 정밀점검","덕소-마석#2T/L No.1~46 철탑 및 충전부 등 정밀점검","2018-04-11 08:00","2018-04-13 18:00","2018-04-11 08:00","2018-04-13 18:00","연속",null,null,null,201801050066,"-"]
[109,"경기북부","구리","덕소마석#1 T/L","154kV 덕소-마석#1T/L 송전선로 정밀점검","덕소-마석#1T/L No.1~46 철탑 및 충전부 등 정밀점검","2018-04-18 08:00","2018-04-20 18:00","2018-04-18 08:00","2018-04-20 18:00","연속",null,null,null,201801050064,"○"]
[110,"경기북부","구리","마석청평HP#1 T/L","154kV 마석-청평HP#1T/L 송전선로 정밀점검","마석-청평HP#1T/L No.1~35 철탑 및 충전부 등 정밀점검","2018-04-09 08:00","2018-04-11 18:00","2018-04-09 08:00","2018-04-11 18:00","연속",null,null,null,201801050058,"○"]
[111,"경기북부","구리","마석청평HP#2 T/L","154kV 마석-청평HP#2T/L 송전선로 정밀점검","마석-청평HP#2T/L No.1~35 철탑 및 충전부 등 정밀점검","2018-04-16 08:00","2018-04-18 18:00","2018-04-16 08:00","2018-04-18 18:00","연속",null,null,null,201801050063,"-"]
[112,"경기북부","구리","운천철원#2 T/L","2018 구리P/O 154 GIS, GCB 보통점검","2018 구리P/O 154 GIS, GCB 보통점검 - 운천S/S 운천철원#2 T/L GIS","2018-04-07 14:00","2018-04-07 18:00","2018-04-07 14:00","2018-04-07 18:00","당일",null,null,null,201801090125,"-"]
[113,"경기북부","구리","운천철원#1 T/L","2018 구리P/O 154 GIS, GCB 보통점검","2018 구리P/O 154 GIS, GCB 보통점검 - 운천S/S 운천철원#1 T/L GIS","2018-04-07 09:00","2018-04-07 14:00","2018-04-07 09:00","2018-04-07 14:00","당일",null,null,null,201801090128,"○"]
[114,"경기북부","구리","운천S/S 운천-전곡#1T/L GIS","운천S/S 154kV 운천-전곡#1T/L GIS 보통점검","운천S/S 154kV 운천-전곡#1T/L GIS 보통점검","2018-04-06 10:00","2018-04-06 18:00","2018-04-06 10:00","2018-04-06 18:00","당일",null,null,null,201802130119,"○"]
[115,"경기북부","구리","지제용문 T/L","18년도 154kV GIS 보통점검 공사","18년도 154kV GIS 보통점검 공사","2018-04-11 10:00","2018-04-11 18:00","2018-04-11 10:00","2018-04-11 18:00","당일",null,null,null,201801170006,"-"]
[116,"경기북부","구리","진건S/S 덕소-진건 #1T/L GIS","진건S/S 덕소-진건 #1 T/L 154kV GIS 보통점검","진건S/S 덕소-진건 #1 T/L 154kV GIS 보통점검","2018-04-19 10:00","2018-04-19 18:00","2018-04-19 10:00","2018-04-19 18:00","당일",null,null,null,201802090519,"○"]
[117,"경기북부","구리","진건S/S 덕소-진건 #2T/L GIS","진건S/S 154kV 덕소-진건 #2T/L GIS 보통점검","진건S/S 154kV 덕소-진건 #2T/L GIS 보통점검","2018-04-20 10:00","2018-04-20 18:00","2018-04-20 10:00","2018-04-20 18:00","당일",null,null,null,201802090520,"-"]
[118,"경기북부","구리","청평PP춘천열병합 T/L","청평P/P 154kV 청평PP-춘천열병합T/L GIS 보통점검","청평P/P 154kV 청평PP-춘천열병합T/L GIS 보통점검","2018-04-25 10:00","2018-04-25 18:00","2018-04-25 10:00","2018-04-25 18:00","당일",null,null,null,201802130127,"-"]
[119,"경기북부","직할","도봉S/S 도봉-진접T/L CB","'18년 변전협력회사 총액공사","GIS 보통점검","2018-04-16 09:00","2018-04-16 18:00","2018-04-16 09:00","2018-04-16 18:00","당일",null,null,null,201802130263,"-"]
[120,"경기북부","직할","도봉S/S 별내-도봉T/L CB","'18년 변전협력회사 총액공사","GIS 보통점검","2018-04-17 09:00","2018-04-17 18:00","2018-04-17 09:00","2018-04-17 18:00","당일",null,null,null,201802130265,"○"]
[121,"경기북부","직할","백석덕계#1 T/L","'18년 변전협력회사 총액공사","개폐타임 측정","2018-04-30 09:00","2018-04-30 14:00","2018-04-30 09:00","2018-04-30 14:00","당일",null,null,null,201802130346,"-"]
[122,"경기북부","직할","양주S/S 154kV #2 BUS TIE GIS","'18년 변전협력회사 총액공사","GIS 보통점검","2018-04-10 09:00","2018-04-10 18:00","2018-04-10 09:00","2018-04-10 18:00","당일",null,null,null,201802130256,"-"]
[123,"경기북부","직할","양주S/S 66-67 SEC GIS","'18년 변전협력회사 총액공사","GIS 보통점검","2018-04-12 09:00","2018-04-12 18:00","2018-04-12 09:00","2018-04-12 18:00","당일",null,null,null,201802130259,"-"]
[124,"경기북부","직할","양주S/S 154kV #3 BUS TIE GIS","'18년 변전협력회사 총액공사","GIS 보통점검","2018-04-11 09:00","2018-04-11 18:00","2018-04-11 09:00","2018-04-11 18:00","당일",null,null,null,201802130257,"-"]
[125,"경기북부","직할","양주은평#2 T/L","양주변전소 옥외철구 GIS화 공사","양주변전소 옥외철구 GIS화 공사 - T-BUS 설비 철거","2018-04-16 09:00","2018-04-18 18:00","2018-04-16 09:00","2018-04-18 18:00","연속",null,null,null,201802130264,"-"]
[126,"경기북부","직할","양주은평#1 T/L","양주변전소 옥외철구 GIS화 공사","양주변전소 옥외철구 GIS화 공사 - T-BUS 설비 철거","2018-04-12 09:00","2018-04-14 18:00","2018-04-12 09:00","2018-04-14 18:00","연속",null,null,null,201802130258,"-"]
[127,"경기북부","직할","양주불광#1 T/L","양주변전소 옥외철구 GIS화 공사","양주변전소 옥외철구 GIS화 공사 - T-BUS 설비 철거","2018-04-09 09:00","2018-04-11 18:00","2018-04-09 09:00","2018-04-11 18:00","연속",null,null,null,201802130254,"-"]
[128,"경기북부","직할","양주불광#2 T/L","양주변전소 옥외철구 GIS화 공사","양주변전소 옥외철구 GIS화 공사 - T-BUS 설비 철거","2018-04-04 09:00","2018-04-06 18:00","2018-04-04 09:00","2018-04-06 18:00","연속",null,null,null,201802130251,"-"]
[129,"경기북부","직할","용현S/S 용현-도봉#1T/L CB","'18년 변전협력회사 총액공사","GIS 보통점검","2018-04-24 09:00","2018-04-24 18:00","2018-04-24 09:00","2018-04-24 18:00","당일",null,null,null,201802130273,"-"]
[130,"경기북부","직할","전곡S/S 신포천-전곡#1T/L CB","'18년 변전협력회사 총액공사","GIS 보통점검","2018-04-04 09:00","2018-04-04 18:00","2018-04-04 09:00","2018-04-04 18:00","당일",null,null,null,201802130249,"○"]
[131,"경기북부","직할","전곡S/S 신포천-전곡#2T/L CB","'18년 변전협력회사 총액공사","GIS 보통점검","2018-04-05 09:00","2018-04-05 18:00","2018-04-05 09:00","2018-04-05 18:00","당일",null,null,null,201802130252,"-"]
[132,"경기","군포","서서울서수원#1 T/L","서서울S/S 154kV 취약설비 GIS화공사","서서울1변전소 서서울서수원1TL 2차 GIS설치 및 송전선로보호반 이설","2018-04-12 09:00","2018-04-16 18:00","2018-04-12 09:00","2018-04-16 18:00","연속",null,null,null,201801040153,"-"]
[133,"경기","군포","서서울서수원#2 T/L","서서울S/S 154kV 취약설비 GIS화공사","서서울1변전소 서서울서수원2TL 2차 GIS설치 및 송전선로보호반 이설","2018-04-17 09:00","2018-04-21 18:00","2018-04-17 09:00","2018-04-21 18:00","연속",null,null,null,201801040154,"-"]
[134,"경기","군포","서안양S/S 서서울2-서안양T/L GIS","서안양S/S 서서울2-서안양 T/L 조작시험","서안양S/S 서서울2-서안양 T/L 조작시험/ 서서울2S/S 서서울2-서안양 T/L 초기점검","2018-04-07 09:00","2018-04-07 18:00","2018-04-07 09:00","2018-04-07 18:00","당일",null,null,null,201802120336,"-"]
[135,"경기","군포","성곡S/S 성곡-중시화T/L GIS","성곡S/S 성곡-중시화T/L GIS 보통점검","성곡S/S 성곡-중시화T/L GIS 보통점검/ 중시화S/S 성곡-중시화T/L GIS 조작시험","2018-04-28 09:00","2018-04-28 18:00","2018-04-28 09:00","2018-04-28 18:00","당일",null,null,null,201802120418,"-"]
[136,"경기","군포","시화중시화 T/L","154kV 시화중시화T/L GIS 조작시험","- 시화, 중시화S/S 154kV 시화중시화T/L GIS 조작시험","2018-04-07 13:00","2018-04-07 18:00","2018-04-07 13:00","2018-04-07 18:00","당일",null,null,null,201802060421,"-"]
[137,"경기","군포","시화성곡 T/L","154kV 시화성곡T/L GIS 점검","- 시화S/S 154kV 시화성곡T/L GIS 조작시험 - 성곡S/S 154kV 시화성곡T/L GIS 보통점검","2018-04-08 09:00","2018-04-08 18:00","2018-04-08 09:00","2018-04-08 18:00","당일",null,null,null,201802060423,"-"]
[138,"경기","군포","신안산남안산#1 T/L","18년 군포P/O 변전협력총액공사","- 677CB 조작시험(개폐타임 등) 남안산S/S 신안산-남안산#1T/L 조작시험","2018-04-12 10:00","2018-04-12 13:00","2018-04-12 10:00","2018-04-12 13:00","당일",null,null,null,201802070219,"-"]
[139,"경기","군포","신안산남안산#2 T/L","18년 군포P/O 변전협력총액공사","- 687CB 조작시험(개폐타임 등) 남안산S/S 신안산-남안산#2T/L 조작시험","2018-04-12 13:00","2018-04-12 15:00","2018-04-12 13:00","2018-04-12 15:00","당일",null,null,null,201802070221,"-"]
[140,"경기","군포","안산안산복합#1 T/L","154kV 안산-안산복합#1T/L 맨홀내 접속함 방식층 보수공사","맨홀내 접속함 방식층 보수","2018-04-23 09:00","2018-05-02 18:00","2018-04-23 09:00","2018-05-02 18:00","연속",null,null,null,201802090267,"-"]
[141,"경기","군포","안산안산복합#2 T/L","154kV 안산-안산복합#2T/L 맨홀내 접속함 방식층 보수공사","맨홀내 접속함 방식층 보수","2018-04-23 09:00","2018-05-02 18:00","2018-04-23 09:00","2018-05-02 18:00","연속",null,null,null,201802090269,"-"]
[142,"경기","군포","화성조암#2 T/L","조암S/S 화성조암#2 T/L GIS 조작시험","화성조암#2T/L GIS 조작시험","2018-04-24 14:00","2018-04-24 18:00","2018-04-24 14:00","2018-04-24 18:00","당일",null,null,null,201802120208,"-"]
[143,"경기","군포","조암구문천#1 T/L","조암S/S 조암구문천#1T/L GIS 조작시험","조암구문천#1T/L GIS 조작시험","2018-04-25 10:00","2018-04-25 14:00","2018-04-25 10:00","2018-04-25 14:00","당일",null,null,null,201802120204,"-"]
[144,"경기","군포","조암구문천#2 T/L","조암S/S 조암구문천#2T/L GIS 조작시험","조암구문천#2T/L GIS 조작시험","2018-04-25 14:00","2018-04-25 18:00","2018-04-25 14:00","2018-04-25 18:00","당일",null,null,null,201802120206,"-"]
[145,"경기","군포","화성조암#1 T/L","조암S/S 화성조암#1 T/L GIS 조작시험","화성조암#1T/L GIS 조작시험","2018-04-24 10:00","2018-04-24 14:00","2018-04-24 10:00","2018-04-24 14:00","당일",null,null,null,201802120207,"-"]
[146,"경기","동부","성현분당#1 T/L","2018년 분당S/S 장기사용 GIS 대체공사","분당S/S 성현-분당#1T/L GIS 대체","2018-04-14 08:00","2018-04-28 18:00","2018-04-14 08:00","2018-04-28 18:00","연속",null,null,null,201801080365,"-"]
[147,"경기","동부","성현분당#2 T/L","2018년 분당S/S 장기사용 GIS 대체공사","분당S/S 성현-분당#2T/L GIS 대체","2018-04-30 08:00","2018-05-14 18:00","2018-04-30 08:00","2018-05-14 18:00","연속",null,null,null,201801080369,"-"]
[148,"경기","동부","여주문막#1 T/L","`18-19년 송전협력회사 총액공사","- 여주-문막 #1T/L 전력선 교체공사 11-12호 중단 등","2018-04-18 08:30","2018-04-27 18:00","2018-04-18 08:30","2018-04-27 18:00","연속",null,null,null,201802080042,"-"]
[149,"경기","성남","서안성남사#1 T/L","154kV 용인-남사T/L 피뢰기 설치공사(안전이격확보 휴전)","- (안전이격휴전)154kV 용인-남사T/L 피뢰기 설치(No.1-14, 42 SET) - 154kV 서안성-남사T/L No.1-14 병가","2018-04-16 07:00","2018-04-16 18:00","2018-04-16 07:00","2018-04-16 18:00","당일",null,null,null,201802220027,"-"]
[150,"경기","성남","서안성안성#2 T/L","154kV 서안성-안성T/L 피뢰기 설치공사","- 154kV 서안성-안성T/L 피뢰기 설치(No.1-34, 102 SET)","2018-04-13 07:00","2018-04-15 18:00","2018-04-13 07:00","2018-04-15 18:00","연속",null,null,null,201802120305,"-"]
[151,"경기","성남","서안성남사#1 T/L","154kV 서안성-안성T/L 피뢰기 설치공사(안전이격확보 휴전)","- (안전이격휴전)154kV 서안성-안성T/L 피뢰기 설치(No.1-34, 102 SET) - 154kV 서안성-안성T/L No.34 병가","2018-04-13 07:00","2018-04-13 18:00","2018-04-13 07:00","2018-04-13 18:00","매일",null,null,null,201802120308,"-"]
[152,"경기","성남","신성남서판교 #3 T/L","신성남-서판교#3T/L 초기점검","신성남S/S 신성남-서판교#3T/L 초기점검 서판교S/S 신성남-서판교#3T/L 초기점검","2018-04-30 10:00","2018-04-30 18:00","2018-04-30 10:00","2018-04-30 18:00","당일",null,null,null,201802120596,"-"]
[153,"경기","성남","신용인S/S 65-66 SEC(65-66-0) GIS","신용인S/S 65-66 GIS 정밀점검","신용인S/S 65-66 GIS 정밀점검, 전자변히터 설치","2018-04-23 09:00","2018-04-25 18:00","2018-04-23 09:00","2018-04-25 18:00","연속",null,null,null,201802120589,"-"]
[154,"경기","성남","신용인S/S 60-61 SEC960-61-0) GIS","신용인S/S #60-61 GIS 정밀점검","신용인S/S #60-61 GIS 정밀점검","2018-04-19 09:00","2018-04-21 18:00","2018-04-19 09:00","2018-04-21 18:00","연속",null,null,null,201802120587,"-"]
[155,"경기","성남","용인남사#1 T/L","용인-남사#1T/L 하자점검 및 조작시험","용인S/S 용인-남사#1T/L 하자점검 남사S/S 용인-남사#1T/L 조작시험","2018-04-17 10:00","2018-04-17 18:00","2018-04-17 10:00","2018-04-17 18:00","당일",null,null,null,201802120567,"-"]
[156,"경기","성남","용인남사#2 T/L","용인-남사#2T/L 하자점검 및 조작시험","용인S/S 용인-남사#2T/L 하자점검, CVT 초기점검 남사S/S 용인-남사#2T/L 조작시험","2018-04-16 07:00","2018-04-16 18:00","2018-04-16 07:00","2018-04-16 18:00","당일",null,null,null,201802120568,"-"]
[157,"경기","성남","신성남정자 #3 T/L","신성남-정자#3T/L 초기점검","신성남S/S 신성남-정자#3T/L 초기점검 정자S/S 신성남-정자#3T/L 초기점검","2018-04-26 10:00","2018-04-26 18:00","2018-04-26 10:00","2018-04-26 18:00","당일",null,null,null,201802120595,"-"]
[158,"경기","직할","발안구문천#1 T/L","18년 직할 변전협력회사 총액공사","발안S/S 발안구문천#1T/L GIS 조작시험 구문천S/S 발안구문천#1t/L GIS 조작시험","2018-04-25 10:00","2018-04-25 18:00","2018-04-25 10:00","2018-04-25 18:00","당일",null,null,null,201802120136,"-"]
[159,"경기","직할","발안구문천#1 T/L","154kV 발안-구문천T/L 피뢰기 설치공사","- 154kV 발안-구문천T/L 피뢰기 설치(No.2-6, 15 SET)","2018-04-17 07:00","2018-04-17 18:00","2018-04-17 07:00","2018-04-17 18:00","당일",null,null,null,201802120313,"-"]
[160,"경기","직할","발안구문천#2 T/L","18년 직할 변전협력회사 총액공사","발안S/S 발안구문천#2T/L GIS 조작시험 구문천S/S 발안구문천#2T/L GIS 조작시험","2018-04-27 10:00","2018-04-27 18:00","2018-04-27 10:00","2018-04-27 18:00","당일",null,null,null,201802120137,"-"]
[161,"경기","직할","서수원율전#1 T/L","154kV 서수원-율전T/L 정밀점검(구간 No.1~17)","154kV 서수원-율전T/L 정밀점검(구간 No.1~17)","2018-04-08 09:00","2018-04-09 18:00","2018-04-08 09:00","2018-04-09 18:00","매일",null,null,null,201802060350,"-"]
[162,"경기","직할","율전의왕#2 T/L","154kV 율전-의왕#2T/L 율전#1C/H EBA 절연유 채유","율전#1C/H EBA 절연유 채유","2018-04-25 09:00","2018-04-25 18:00","2018-04-25 09:00","2018-04-25 18:00","당일",null,null,null,201802090248,"-"]
[163,"경기","직할","서수원율전#2 T/L","154kV 서수원-율전T/L 정밀점검(구간 No.1~17)","154kV 서수원-율전T/L 정밀점검(구간 No.1~17)","2018-04-10 09:00","2018-04-11 18:00","2018-04-10 09:00","2018-04-11 18:00","매일",null,null,null,201802060352,"-"]
[164,"경기","직할","율전의왕#1 T/L","154kV 율전-의왕#1T/L 율전#1C/H EBA 절연유 채유","율전#1C/H EBA 절연유 채유","2018-04-24 09:00","2018-04-24 18:00","2018-04-24 09:00","2018-04-24 18:00","당일",null,null,null,201802090246,"-"]
[165,"경기","평택","만호청북#1 T/L","일진제 170kV GIS 인출측 DS 노즐 제작사 자체점검","일진제 170kV GIS 인출측 DS 노즐 제작사 자체점검","2018-04-20 09:00","2018-04-22 18:00","2018-04-20 09:00","2018-04-22 18:00","연속",null,null,null,201802120190,"-"]
[166,"경기","평택","포승만호 T/L","일진제 170kV GIS 인출측 DS 노즐 제작사 자체점검","일진제 170kV GIS 인출측 DS 노즐 제작사 자체점검","2018-04-13 09:00","2018-04-15 18:00","2018-04-13 09:00","2018-04-15 18:00","연속",null,null,null,201802120184,"-"]
[167,"경기","평택","서운만승 T/L","서운S/S 154kV 서운-만승T/L GIS CB 조작시험","서운S/S 154kV 서운-만승T/L GIS CB 조작시험","2018-04-04 10:00","2018-04-04 18:00","2018-04-04 10:00","2018-04-04 18:00","당일",null,null,null,201802120197,"-"]
[168,"경기","평택","송탄안성 T/L","지제역세권 개발 관련 지중화 본이설공사","154kV 송탄-오성복합T/L No.18~24 지중화 154kV 송탄-안성T/L No.5 이설","2018-04-01 07:00","2018-04-03 18:00","취소","취소","연속",null,null,null,201802060133,"-"]
[169,"경기","평택","송탄오성복합 T/L","지제역세권 개발 관련 지중화 본이설공사","154kV 송탄-오성복합T/L No.18~24 지중화 154kV 송탄-안성T/L No.5 이설","2018-04-01 07:00","2018-04-08 18:00","취소","취소","연속",null,null,null,201802060126,"-"]
[170,"경기","평택","송탄안성 T/L","지제역세권 개발 관련 지중화 본이설공사","154kV 송탄-오성복합T/L No.18~24 지중화 154kV 송탄-안성T/L No.5 이설","2018-04-09 07:00","2018-04-11 18:00","취소","취소","연속",null,null,null,201802060141,"-"]
[171,"경기","평택","송탄소사벌 T/L","지제역세권 개발 관련 지중화 본이설공사","154kV 송탄-오성복합T/L No.18~24 지중화 154kV 송탄-안성T/L No.5 이설","2018-04-04 07:00","2018-04-07 18:00","취소","취소","연속",null,null,null,201802060136,"-"]
[172,"경기","평택","고덕송탄 T/L","지제역세권 개발 관련 지중화 본이설공사","154kV 송탄-오성복합T/L No.18~24 지중화 154kV 송탄-안성T/L No.5 이설","2018-04-09 07:00","2018-04-12 18:00","취소","취소","연속",null,null,null,201802060139,"-"]
[173,"경기","평택","서운안성#2 T/L","154kV 서안성-안성T/L 피뢰기 설치공사(안전이격확보 휴전)","- (안전이격휴전)154kV 서안성-안성T/L 피뢰기 설치(No.1-34, 102 SET) - 154kV 서안성-안성T/L No.1-4 병가","2018-04-15 07:00","2018-04-15 18:00","2018-04-15 07:00","2018-04-15 18:00","당일",null,null,null,201802120307,"-"]
[174,"경기","평택","오산향남#2 T/L","154kV 오산향남#2T/L 송전금구류교체(No.14,15)","154kV 오산향남#2T/L 송전금구류교체(No.14,15)","2018-04-24 08:00","2018-04-24 18:00","2018-04-24 08:00","2018-04-24 18:00","당일",null,null,null,201802200234,"-"]
[175,"경기","평택","오산향남#1 T/L","154kV 오산평택T/L 피뢰기설치 안전작업거리 확보","154kV 오산평택#1T/L 피뢰기설치(No.6~8) 안전작업거리확보","2018-04-23 08:00","2018-04-23 18:00","2018-04-23 08:00","2018-04-23 18:00","당일",null,null,null,201802130126,"-"]
[176,"경기","평택","오산평택#1 T/L","154kV 오산평택#1T/L 가공송전선로 정밀점검","154kV 오산평택#1T/L 가공송전선로 정밀점검(75기)","2018-04-20 08:00","2018-04-23 17:00","2018-04-20 08:00","2018-04-23 17:00","매일",null,null,null,201802120272,"-"]
[177,"경기","평택","오산평택#2 T/L","154kV 오산평택#2T/L 가공송전선로 정밀점검","154kV 오산평택#2T/L 가공송전선로 정밀점검(75기)","2018-04-24 08:00","2018-04-27 17:00","2018-04-24 08:00","2018-04-27 17:00","매일",null,null,null,201802120273,"-"]
[178,"경기","평택","송탄진위#1 T/L","154kV 송탄-진위T/L 항공장애표시구 설치공사","항공장애표시구 설치(2경간)","2018-04-30 12:00","2018-04-30 18:00","2018-04-30 12:00","2018-04-30 18:00","당일",null,null,null,201802130123,"-"]
[179,"경기","평택","송탄진위#2 T/L","154kV 송탄-진위T/L 항공장애표시구 설치공사","항공장애표시구 설치(2경간)","2018-04-30 07:00","2018-04-30 12:00","2018-04-30 07:00","2018-04-30 12:00","당일",null,null,null,201802130122,"-"]
[180,"경기","평택","둔포추팔#1 T/L","추팔변전소 외벽보강공사 관련 안전이격","추팔변전소 외벽보강공사 관련 안전이격","2018-04-13 09:00","2018-04-15 18:00","2018-04-13 09:00","2018-04-15 18:00","매일",null,null,null,201802120193,"-"]
[181,"경기","평택","평택추팔#2 T/L","추팔변전소 외벽보강공사 관련 안전이격","추팔변전소 외벽보강공사 관련 안전이격","2018-04-13 09:00","2018-04-15 18:00","2018-04-13 09:00","2018-04-15 18:00","매일",null,null,null,201802120195,"-"]
[182,"경기","평택","청북평택#1 T/L","154kV 평택S/S SW증설공사(고덕-평택TL)","○ GIS(170kV 50kA 2000A CHD) x 2CCT 설치관련 GIS BUS 무부하가압용","2018-04-03 13:00","2018-04-05 18:00","2018-04-03 13:00","2018-04-05 18:00","연속",null,null,null,201802200343,"-"]
[183,"강원","강릉","영동TP강릉 T/L","154kV 강릉S/S 인출 송전선로 지중화공사","- (신설)No.36~강릉S/S간 송전선로 인출구간 지중화","2018-04-24 09:00","2018-05-20 18:00","2018-04-10 08:00","2018-04-13 18:00","연속",null,null,null,201802050192,"-"]
[184,"강원","강릉","동해강릉 T/L","154kV 강릉S/S 인출 송전선로 지중화공사","- (신설)No.36~강릉S/S간 송전선로 인출구간 지중화 : 154kV 영동T/P-강릉#2T/L 지중 케이블 포설시 안전거리 확보","2018-04-28 09:00","2018-05-07 18:00","2018-04-28 09:00","2018-05-07 18:00","연속",null,null,null,201802050188,"-"]
[185,"강원","강릉","주문진양양#1 T/L","154kV 주문진S/S #3M.Tr용 GIS 설치공사","○ GIS(170kV 50kA 1250A) ○ 기타부대공사x1식","2018-04-09 10:00","2018-04-10 10:00","2018-04-09 09:00","2018-04-09 18:00","당일",null,null,null,201801110366,"-"]
[186,"강원","강릉","주문진양양#1 T/L","154kV 주문진S/S #3M.Tr용 GIS 설치공사","○ GIS(170kV 50kA 1250A) ○ 기타부대공사x1식","2018-04-02 10:00","2018-04-03 10:00","2018-04-02 09:00","2018-04-02 18:00","당일",null,null,null,201801110363,"-"]
[187,"강원","강릉","주진평창#1 T/L","2018년 변전협력회사 총액공사","주진S/S 154kV GIS 유압 메카니즘 보수","2018-04-10 10:00","2018-04-10 18:00","2018-04-10 10:00","2018-04-10 18:00","당일",null,null,null,201802010070,"-"]
[188,"강원","강릉","신제천주진#2 T/L","2018년 변전협력회사 총액공사","주진S/S 154kV GIS 유압 메카니즘 보수","2018-04-09 16:00","2018-04-09 18:00","2018-04-09 16:00","2018-04-09 18:00","당일",null,null,null,201802010064,"-"]
[189,"강원","강릉","주진평창#2 T/L","2018년 변전협력회사 총액공사","주진S/S 154kV GIS 유압 메카니즘 보수","2018-04-11 10:00","2018-04-11 18:00","2018-04-11 10:00","2018-04-11 18:00","당일",null,null,null,201802010072,"-"]
[190,"강원","강릉","신제천주진#1 T/L","2018년 변전협력회사 총액공사","주진S/S 154kV GIS 유압 메카니즘 보수","2018-04-09 08:00","2018-04-09 16:00","2018-04-09 08:00","2018-04-09 16:00","당일",null,null,null,201802010063,"-"]
[191,"강원","강릉","횡계평창 T/L","2018년 변전협력회사 총액공사","  GIS 조작함 리미트 스위치 교체","2018-04-12 10:00","2018-04-12 18:00","2018-04-12 10:00","2018-04-12 18:00","당일",null,null,null,201802260027,"-"]
[192,"강원","강릉","평창올림픽T/L","2018년 변전협력회사 총액공사","  GIS 조작함 리미트 스위치 교체","2018-04-13 10:00","2018-04-13 18:00","2018-04-13 10:00","2018-04-13 18:00","당일",null,null,null,201802260028,"-"]
[193,"강원","동해","동해이원#1 T/L","2018년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 154kV 동해이원#1T/L GIS 하자점검 2. 이원S/S 154kV 동해이원#1T/L LA 초기점검(심기탁)","2018-04-17 10:00","2018-04-17 18:00","2018-04-17 10:00","2018-04-17 18:00","당일",null,null,null,201802050187,"-"]
[194,"강원","동해","동해이원#2 T/L","2018년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 154kV 동해이원#2T/L GIS 하자점검","2018-04-16 10:00","2018-04-16 18:00","2018-04-16 10:00","2018-04-16 18:00","당일",null,null,null,201802050189,"-"]
[195,"강원","동해","동해정선 T/L","2018년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 154kV 동해정선T/L GIS 하자점검 2. 동해S/S 154kV 동해정선T/L LA 하자점검 3. 정선S/S 154kV 동해정선T/L LA교체(A, B, C상)","2018-04-18 10:00","2018-04-18 18:00","취소","취소","당일",null,null,null,201802050186,"-"]
[196,"강원","동해","동해영동TP T/L","2018년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 154kV 동해영동TPT/L GIS 하자점검","2018-04-23 10:00","2018-04-23 18:00","2018-04-23 10:00","2018-04-23 18:00","당일",null,null,null,201802050193,"-"]
[197,"강원","동해","동해동영월 T/L","2018년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 154kV 동해동영월T/L GIS 하자점검","2018-04-19 10:00","2018-04-19 18:00","취소","취소","당일",null,null,null,201802050190,"-"]
[198,"강원","동해","울진삼척GP#2 T/L","항공장애표시구 설치공사","울진-삼척G/P #2T/L 항공장애표시구 설치공사","2018-04-02 08:00","2018-04-03 17:00","2018-04-02 08:00","2018-04-03 17:00","매일",null,null,null,201802050154,"-"]
[199,"강원","동해","정선영월CC T/L","154kV 정선S/S #1M.Tr 증설공사","154kV GIS 무부하가압","2018-04-16 10:00","2018-04-17 10:00","2018-04-16 10:00","2018-04-17 10:00","연속",null,null,null,201801120200,"-"]
[200,"강원","원주","남원주원주#1 T/L","2018년 원주전력지사 변전협력 총액공사","154kV GIS 보통점검","2018-04-03 09:00","2018-04-03 18:00","2018-04-03 09:00","2018-04-03 18:00","당일",null,null,null,201802060050,"-"]
[201,"강원","원주","홍천남춘천 T/L","2018년 원주전력 변전협력회사 총액공사","홍천S/S 170kV GIS 초기점검","2018-04-17 09:00","2018-04-17 17:00","2018-04-21 09:00","2018-04-21 17:00","당일",null,null,null,201802060062,"-"]
[202,"강원","원주","홍천소양강HP T/L","2018년 가공송전선로 순시점검 위탁공사 등 2건","정밀점검 항공장애표시구 설치 및 부분정비 시행","2018-04-02 09:00","2018-04-06 18:00","2018-04-02 09:00","2018-04-06 18:00","연속",null,null,null,201802070167,"-"]
[203,"강원","직할","서홍천춘천열병합 T/L","2018년~2019년 강원지역본부 직할 변전정비 총액공사","서홍천S/S 154kV 서홍천-춘천열병합 T/L GIS 보통점검","2018-04-12 10:00","2018-04-12 18:00","2018-04-12 10:00","2018-04-12 18:00","당일",null,null,null,201802050221,"-"]
[204,"강원","직할","서홍천청평PP T/L","2018년~2019년 강원지역본부 직할 변전정비 총액공사","서홍천S/S 154kV 서홍천-청평PP T/L GIS 보통점검","2018-04-11 10:00","2018-04-11 18:00","2018-04-11 10:00","2018-04-11 18:00","당일",null,null,null,201802050218,"-"]
[205,"강원","직할","청평HP의암HP T/L","2018년 직할 관내 차단기 정밀점검공사","154kV 청평HP-의암HP GCB 정밀점검 공사","2018-04-19 09:00","2018-04-21 18:00","취소","취소","연속",null,null,null,201802060305,"-"]
[206,"강원","직할","간성인제#2 T/L","154kV 인제S/S #3M.Tr 용량변경공사","- #3M.Tr 용량변경 - 변압기보호반 철거 및 설치 - 기타부대공사 1식","2018-04-25 09:00","2018-04-26 18:00","2018-04-25 09:00","2018-04-26 18:00","연속",null,null,null,201802050226,"-"]
[207,"강원","직할","상남인제#1 T/L","2018년~2019년 강원지역본부 직할 변전정비 총액공사","인제S/S 154kV 상남-인제 #1 T/L GIS 보통점검","2018-04-10 10:00","2018-04-10 18:00","2018-04-10 10:00","2018-04-10 18:00","당일",null,null,null,201802050216,"-"]
[208,"강원","직할","철원화천#1 T/L","철원S/S 154kV GIS 내부 발청 보수공사","- 154kV GIS 내부 LINK 발청 보수","2018-04-06 09:30","2018-04-06 13:00","2018-04-06 09:30","2018-04-06 13:00","당일",null,null,null,201801180005,"-"]
[209,"강원","직할","철원화천#2 T/L","철원S/S 154kV GIS 내부 발청 보수공사","- 154kV GIS 내부 LINK 발청 보수","2018-04-06 13:00","2018-04-06 16:00","2018-04-06 13:00","2018-04-06 16:00","당일",null,null,null,201801180006,"-"]
[210,"강원","직할","철원S/S 154kV #1 BUS TIE CB","철원S/S 154kV GIS 내부 발청 보수공사","- 154kV GIS 내부 LINK 발청 보수","2018-04-06 16:00","2018-04-06 19:00","2018-04-06 16:00","2018-04-06 19:00","당일",null,null,null,201801180016,"-"]
[211,"강원","직할","춘천소양강HP T/L","2018년 가공송전선로 순시점검 위탁공사","정밀점검(23기)","2018-04-09 09:00","2018-04-11 18:00","취소","취소","연속",null,null,null,201802200182,"-"]
[212,"강원","직할","북춘천화천HP T/L","154kV 화천T/L 안전이격 확보공사","○ No.35~38간 전력선 교체 ○ 154kV 북춘천-화천HPT/L No.35~38간 인수점검","2018-04-13 08:00","2018-04-16 18:00","2018-04-14 08:00","2018-04-15 18:00","연속",null,null,null,201802050214,"-"]
[213,"강원","직할","가평화천HP T/L","154kV 화천T/L 안전이격 확보공사","○ No.35~38간 전력선 교체 ○ 154kV 화천HP-가평T/L 인수점검","2018-04-09 08:00","2018-04-12 18:00","2018-04-09 08:00","2018-04-12 18:00","연속",null,null,null,201802050209,"-"]
[214,"강원","태백","정선영월CC T/L","항공장애표시구 설치공사","정선-영월CC T/L 항공장애표시구 설치공사","2018-04-09 08:00","2018-04-14 17:00","2018-04-09 08:00","2018-04-14 17:00","매일",null,null,null,201802050156,"-"]
[215,"강원","태백","태백영월 T/L","항공장애표시구 설치공사","태백-영월 T/L 항공장애표시구 설치공사","2018-04-18 08:00","2018-04-24 17:00","2018-04-18 08:00","2018-04-24 17:00","매일",null,null,null,201802050160,"-"]
[216,"강원","태백","태백삼척GP#1 T/L","항공장애표시구 설치공사","태백-삼척G/P #1T/L 항공장애표시구 설치공사","2018-04-02 08:00","2018-04-05 17:00","2018-04-02 08:00","2018-04-05 17:00","매일",null,null,null,201802050149,"-"]
[217,"충북","직할","신제천왕암#2 T/L","2018~2019년 직할 송전정비 협력회사 총액공사","전력선 교체공사 (No.9~35)","2018-04-01 09:00","2018-04-10 18:00","2018-04-01 09:00","2018-04-10 18:00","연속",null,null,null,201802070026,"-"]
[218,"충북","직할","신제천왕암#1 T/L","2018~2019년 직할 송전정비 협력회사 총액공사","전력선 교체공사 (No.9~35)","2018-04-11 09:00","2018-04-22 18:00","2018-04-11 09:00","2018-04-22 18:00","연속",null,null,null,201802070005,"-"]
[219,"충북","청주","서청주사직#2 T/L","2018년 청주전력 변전협력회사 총액공사","154kV 서청주사직#2T/L 보호반 대체작업","2018-04-14 09:00","2018-04-16 18:00","2018-04-14 09:00","2018-04-16 18:00","연속",null,null,null,201801300038,"-"]
[220,"충북","청주","신진천오창#2 T/L","18-19년 송전정비 협력회사 총액공사(청주전력)","항공장애표시구 설치 No.14~15(2개), 46~47호(1개)","2018-04-08 13:00","2018-04-08 19:00","2018-04-08 13:00","2018-04-08 19:00","당일",null,null,null,201801110437,"-"]
[221,"충북","청주","신진천오창#1 T/L","18-19년 송전정비 협력회사 총액공사(청주전력)","항공장애표시구 설치 No.14~15(1개), 46~47호 (1개)","2018-04-08 08:00","2018-04-08 12:00","2018-04-08 08:00","2018-04-08 12:00","당일",null,null,null,201801110436,"-"]
[222,"충북","청주","옥천보은 T/L","18-19년 송전정비 협력회사 총액공사(청주전력)","항공장애표시구설치 : No.14~18(9개)","2018-04-09 08:00","2018-04-09 12:00","2018-04-09 08:00","2018-04-09 12:00","당일",null,null,null,201802070509,"-"]
[223,"충북","청주","옥천영동 T/L","18-19년 송전정비 협력회사 총액공사(청주전력)","항공장애표시구설치 : No.14~18(8개)","2018-04-09 13:00","2018-04-09 18:00","2018-04-09 13:00","2018-04-09 18:00","당일",null,null,null,201802070511,"-"]
[224,"충북","청주","죽림S/S 청원-죽림#1T/L GIS","18~19년 청주전력 변전협력회사 총액공사","170kV GIS 보통점검/LA대체","2018-04-10 09:30","2018-04-10 18:00","2018-04-10 09:30","2018-04-10 18:00","당일",null,null,null,201802090144,"-"]
[225,"충북","청주","죽림S/S 청원-죽림#2T/L GIS","18~19년 청주전력 변전협력회사 총액공사","LA대체","2018-04-11 09:30","2018-04-11 18:00","2018-04-11 09:30","2018-04-11 18:00","당일",null,null,null,201802090145,"-"]
[226,"충북","청주","신옥천S/S #2 M.Tr 3차 CB","신옥천S/S 장기사용 23kV 분로리액터 대체","○ 23kV 분로리액터 4Bank 대체(유입식, 30Mvar → 건식, 45Mvar) ○ 23kv 진공차단기(VCB) 및 단로기(DS) 철거(3대), 설치(2대) ○ #2M.Tr 3차측 분기 모선 재배치 ○ 기기기초 및 철구 철거, 설치 ○ 제어케이블 철거 및 포·결선","2018-04-16 10:00","2018-06-29 18:00","2018-04-16 10:00","2018-06-29 18:00","연속",null,null,null,201802010043,"-"]
[227,"충북","충주","진천만승#2 T/L","18-19년 충주전력 변전 총액공사","송전선로 LA 등 초기점검","2018-04-11 10:00","2018-04-11 18:00","취소","취소","매일",null,null,null,201802110004,"-"]
[228,"충북","충주","서운만승 T/L","154kV 서운-만승 등 2개T/L 전력선교체공사","서운-만승T/L No.81~83(진천-만승 #1T/L No.35~37) 전력선교체","2018-04-24 07:00","2018-04-26 18:00","취소","취소","연속",null,null,null,201802140123,"-"]
[229,"충북","충주","음성증평 T/L","2018-19년 송전정비 협력회사 총액공사","전선 접속개소 전선교체 (No.40-41, 41-46, 59-60, 65-69, 78-80, 94-96)","2018-04-16 08:00","2018-04-25 18:00","2018-04-16 08:00","2018-04-25 18:00","연속",null,null,null,201801170186,"-"]
[230,"충북","충주","진천덕산#2 T/L","18-19년 충주전력 변전 총액공사","송전선로 LA 등 초기점검","2018-04-13 10:00","2018-04-13 18:00","취소","취소","매일",null,null,null,201802110006,"-"]
[231,"충북","충주","진천만승#1 T/L","154kV 서운-만승 등 2개T/L 전력선교체공사","서운-만승T/L No.81~83(진천-만승 #1T/L No.35~37) 전력선교체","2018-04-24 07:00","2018-04-26 18:00","취소","취소","연속",null,null,null,201802140127,"-"]
[232,"충북","충주","진천덕산#1 T/L","18-19년 충주전력 변전 총액공사","송전선로 LA 등 초기점검","2018-04-12 10:00","2018-04-12 18:00","취소","취소","매일",null,null,null,201802110005,"-"]
[233,"대전충남","서산","신당진당진#1 T/L","18년 변전협력회사 총액공사","당진S/S 154kV 신당진-당진#1T/L GCB,LA,CVT 보통점검","2018-04-17 09:00","2018-04-17 18:00","취소","취소","당일",null,null,null,201802070488,"-"]
[234,"대전충남","서산","신당진당진#2 T/L","18년 변전협력회사 총액공사","당진S/S 154kV 신당진-당진#2T/L GCB, LA, CVT 보통점검","2018-04-23 09:00","2018-04-24 18:00","취소","취소","당일",null,null,null,201802070495,"-"]
[235,"대전충남","서산","GSEPS#2 T/L","154kV GSEPS분기T/L 정밀점검","154kV GSEPS분기T/L 정밀점검","2018-04-12 07:00","2018-04-12 18:00","2018-04-12 07:00","2018-04-12 18:00","매일",null,null,null,201802070182,"-"]
[236,"대전충남","서산","GSEPS#1 T/L","154kV GSEPS분기T/L 정밀점검","154kV GSEPS분기T/L 정밀점검","2018-04-13 07:00","2018-04-13 18:00","2018-04-13 07:00","2018-04-13 18:00","매일",null,null,null,201802070184,"-"]
[237,"대전충남","서산","GSEPS#1 T/L","154kV GSEPS분기T/L 정밀점검","154kV GSEPS분기T/L 정밀점검","2018-04-11 07:00","2018-04-11 18:00","2018-04-11 07:00","2018-04-11 18:00","매일",null,null,null,201802070183,"-"]
[238,"대전충남","서산","GSEPS#2 T/L","154kV GSEPS분기T/L 정밀점검","154kV GSEPS분기T/L 정밀점검","2018-04-10 07:00","2018-04-10 18:00","2018-04-10 07:00","2018-04-10 18:00","매일",null,null,null,201802070179,"-"]
[239,"대전충남","세종","신풍공주#1 T/L","[송전]154kV 신풍-공주T/L 전선교체공사","[송전]154kV 신풍-공주#1T/L No.1-6~1-8, 1-14~4, 4~6호 전선교체","2018-04-16 07:00","2018-04-22 18:00","2018-04-16 07:00","2018-04-22 18:00","연속",null,null,null,201802130038,"-"]
[240,"대전충남","세종","신풍공주#2 T/L","[송전]154kV 신풍-공주T/L 전선교체공사","[송전]154kV 신풍-공주#2T/L No.1-6~1-8, 1-14~4, 4~6호 전선교체","2018-04-23 07:00","2018-04-28 18:00","2018-04-23 07:00","2018-04-28 18:00","연속",null,null,null,201802130040,"-"]
[241,"대전충남","세종","서세종조치원 T/L","154kV 서세종-조치원T/L EBA 절연유 채유","서세종-조치원T/L EBA 절연유 분석을 위한 채유 작업","2018-04-05 09:00","2018-04-05 18:00","2018-04-05 09:00","2018-04-05 18:00","당일",null,null,null,201802010094,"-"]
[242,"대전충남","아산","둔포추팔#1 T/L","둔포S/S 154kV 둔포-추팔#1T/L GIS 정밀점검","○ 둔포S/S 154kV 둔포-추팔#1T/L GIS 정밀점검","2018-04-03 09:00","2018-04-04 18:00","2018-04-09 09:00","2018-04-10 18:00","연속",null,null,null,201802060608,"-"]
[243,"대전충남","아산","둔포추팔#2 T/L","둔포S/S 154kV 둔포-추팔#2T/L GIS 정밀점검","○ 둔포S/S 154kV 둔포-추팔#2T/L GIS 정밀점검","2018-04-05 09:00","2018-04-06 18:00","2018-04-11 09:00","2018-04-12 18:00","연속",null,null,null,201802060609,"-"]
[244,"대전충남","아산","아산송악#1 T/L","154kV 합덕분기T/L 건설공사","기설 154kV 아산송악T/L 2Π분기~신설 154kV 합덕S/S 합덕S/S 신설에 따른 관형지지물 2기 신설(154kV 아산-송악 No.52~53)","2018-04-07 09:00","2018-04-10 18:00","2018-04-07 09:00","2018-04-10 18:00","연속",null,null,null,201801120163,"-"]
[245,"대전충남","아산","서천안탕정#1 T/L","탕정S/S #4M.Tr용 170kV GIS 설치공사","#1모선 증설구간 무부하가압","2018-04-14 16:00","2018-04-16 09:00","2018-04-14 16:00","2018-04-16 09:00","연속",null,null,null,201803020062,"-"]
[246,"대전충남","아산","서천안탕정#2 T/L","탕정S/S #4M.Tr용 170kV GIS 설치공사","#2모선 증설구간 무부하가압","2018-04-19 09:00","2018-04-20 09:00","2018-04-19 09:00","2018-04-20 09:00","연속",null,null,null,201803020065,"-"]
[247,"대전충남","청양","관창보령화력 T/L","154kV 보관T/L 전력선 교체공사","○ 교체길이 : 7개 구간 6.343[C-km] ○ 스페이서 교체 : 575개 ○ SB댐퍼 교체 : 322개 ○ 구형부식 애자장치 교체 : 18기 96련 ○ 기타부대공사","2018-04-09 07:00","2018-04-16 18:00","2018-04-09 07:00","2018-04-16 18:00","연속",null,null,null,201802090001,"-"]
[248,"대전충남","청양","관창보령복합 T/L","154kV 보관T/L 전력선 교체공사","○ 교체길이 : 7개 구간 6.343[C-km] ○ 스페이서 교체 : 575개 ○ SB댐퍼 교체 : 322개 ○ 구형부식 애자장치 교체 : 18기 96련 ○ 기타부대공사","2018-04-17 07:00","2018-04-24 18:00","2018-04-17 07:00","2018-04-24 18:00","연속",null,null,null,201802090002,"-"]
[249,"대전충남","청양","관창보령화력 T/L","154kV 보관T/L 전력선 교체공사","○ 교체길이 : 7개 구간 6.343[C-km] ○ 스페이서 교체 : 575개 ○ SB댐퍼 교체 : 322개 ○ 구형부식 애자장치 교체 : 18기 96련 ○ 기타부대공사","2018-04-25 07:00","2018-05-02 18:00","2018-04-25 07:00","2018-05-02 18:00","연속",null,null,null,201802090003,"-"]
[250,"대전충남","청양","청양신풍#1 T/L","[송전]154kV 청양-신풍T/L 전선교체공사","[송전]154kV 청양-신풍#1T/L No.1-6~1-8호 전선교체 및 안전거리확보","2018-04-20 07:00","2018-04-28 18:00","2018-04-20 07:00","2018-04-28 18:00","연속",null,null,null,201802130036,"-"]
[251,"대전충남","청양","청양신풍#2 T/L","[송전]154kV 청양-신풍T/L 전선교체공사","[송전]154kV 청양-신풍#2T/L No.1-6~1-8호 전선교체","2018-04-16 07:00","2018-04-19 18:00","2018-04-16 07:00","2018-04-19 18:00","연속",null,null,null,201802130035,"-"]
[252,"대전충남","청양","해미홍성 T/L","관내S/S 154kV 차단기 부동작 예방조작시험","○홍성S/S 154kV해미-홍성T/L 조작시험","2018-04-03 09:00","2018-04-03 18:00","2018-04-03 09:00","2018-04-03 18:00","당일",null,null,null,201802070284,"-"]
[253,"전북","군산","군공S/S 154kV #2 BUS","2018년 군산P/O 차단기 정밀점검공사","군공S/S 154kV 군공-군산복합#2T/L 차단기 정밀점검","2018-04-27 14:00","2018-04-28 18:00","2018-04-27 14:00","2018-04-28 18:00","연속",null,null,null,201802230188,"-"]
[254,"전북","군산","군공S/S 154kV #1 BUS","2018년 군산P/O 차단기 정밀점검공사","군공S/S 154kV 군공-군산복합#2T/L 차단기 정밀점검","2018-04-26 09:00","2018-04-27 14:00","2018-04-26 09:00","2018-04-27 14:00","연속",null,null,null,201802230187,"-"]
[255,"전북","군산","군공군산복합#2 T/L","2018년 군산P/O 차단기 정밀점검공사","군공S/S 154kV 군공-군산복합#2T/L 차단기 정밀점검","2018-04-26 09:00","2018-04-28 18:00","2018-04-26 09:00","2018-04-28 18:00","연속",null,null,null,201802230175,"-"]
[256,"전북","군산","군공군산복합#1 T/L","2018년 군산P/O 차단기 정밀점검공사","군공S/S 154kV 군공-군산복합#1T/L 차단기 정밀점검","2018-04-23 09:00","2018-04-25 18:00","2018-04-23 09:00","2018-04-25 18:00","연속",null,null,null,201802230174,"-"]
[257,"전북","군산","군공S/S 154kV #1 BUS","2018년 군산P/O 차단기 정밀점검공사","군공S/S 154kV 군공-군산복합#2T/L 차단기 정밀점검","2018-04-23 09:00","2018-04-24 14:00","2018-04-23 09:00","2018-04-24 14:00","연속",null,null,null,201802230185,"-"]
[258,"전북","군산","군공S/S 154kV #2 BUS","2018년 군산P/O 차단기 정밀점검공사","군공S/S 154kV 군공-군산복합#1T/L 차단기 정밀점검","2018-04-24 14:00","2018-04-25 18:00","2018-04-24 14:00","2018-04-25 18:00","연속",null,null,null,201802230186,"-"]
[259,"전북","군산","서군산S/S 군산-서군산#1T/L CB","군산P/O 154kV이상 차단기 조작시험공사","차단기 조작시험공사","2018-04-16 13:00","2018-04-16 16:00","2018-04-16 13:00","2018-04-16 16:00","당일",null,null,null,201802070111,"-"]
[260,"전북","군산","서군산S/S 군산-서군산#2T/L CB","군산P/O 154kV이상 차단기 조작시험공사","차단기 조작시험공사","2018-04-17 13:00","2018-04-17 16:00","2018-04-17 13:00","2018-04-17 16:00","당일",null,null,null,201802070116,"-"]
[261,"전북","군산","팔봉영등#1 T/L","팔봉-영등#1T/L 보호배전반 대체공사","팔봉-영등#1T/L 보호배전반 대체공사","2018-04-02 09:00","2018-04-06 18:00","취소","취소","연속",null,null,null,201802200191,"-"]
[262,"전북","군산","팔봉영등#2 T/L","팔봉-영등#2T/L 보호배전반 대체공사","팔봉-영등#2T/L 보호배전반 대체공사","2018-04-30 09:00","2018-05-04 18:00","취소","취소","연속",null,null,null,201802200192,"-"]
[263,"전북","군산","함열S/S 함열-영등#2T/L CB","함열S/S 170kV 장기사용 GIS 대체공사 (1차)","- 은진-함열T/L 등 170kV GIS 8CCT 대체 - 기초보강 및 기타부대공사 1식","2018-04-09 09:00","2018-04-27 18:00","2018-04-09 09:00","2018-04-24 18:00","연속",null,null,null,201802140037,"-"]
[264,"전북","군산","동군산군산복합#2 T/L","동군산-군산CC2TL","차단기 조작시험 점검공사","2018-04-04 15:00","2018-04-04 18:00","2018-04-07 15:00","2018-04-07 18:00","당일",null,null,null,201801110273,"-"]
[265,"전북","군산","군산복합S/Y S/T T/L CB","154kV 군산복합S/Y S/T T/L CB","군산CC 154kV STG T/L 차단기 유압펌프 점검작업","2018-04-04 09:00","2018-04-04 18:00","2018-04-07 09:00","2018-04-07 18:00","당일",null,null,null,201802260153,"-"]
[266,"전북","군산","동군산장항#1 T/L","동군산S/S 154kV 페이퍼T/L 철거공사","○ 154kV 페이퍼T/L 170kV GIS 철거","2018-04-03 08:00","2018-04-06 18:00","2018-04-03 08:00","2018-04-06 18:00","연속",null,null,null,201801230133,"-"]
[267,"전북","김제","고창영광 T/L","154kV 영광-고창T/L 정밀점검","154kV 영광-고창T/L 정밀점검(No.46~155)","2018-04-16 07:00","2018-04-20 18:00","취소","취소","매일",null,null,null,201801190114,"-"]
[268,"전북","김제","고창S/S 고창-홍농T/L CB","2018년도 154kV 차단기 정밀점검","-. 차단부 분해점검 및 이상부품 교체 -. 특성시험 및 경보시험 -. 기타 부대공사 1식","2018-04-09 09:00","2018-04-11 18:00","취소","취소","연속",null,null,null,201801160066,"-"]
[269,"전북","김제","백산김제#1 T/L","154kV 백산-김제T/L 선종교체공사","작업내용 : No. 21~30호 전선교체","2018-04-11 08:00","2018-04-16 18:00","2018-04-11 08:00","2018-04-15 18:00","연속",null,null,null,201801180121,"-"]
[270,"전북","김제","김제섬진강HP T/L","154kV 백산-김제T/L 선종교체공사","백산-김제T/L 4회선 구간 전력선 교체를 위한 안전확보 휴전","2018-04-08 09:00","2018-04-16 18:00","2018-04-25 08:00","2018-05-02 18:00","연속",null,null,null,201801230085,"-"]
[271,"전북","김제","신김제남전주#2 T/L","차단기 조작시험","차단기 조작시험","2018-04-03 09:00","2018-04-03 18:00","2018-04-24 09:00","2018-04-24 18:00","당일",null,null,null,201802120039,"-"]
[272,"전북","김제","신김제남전주#1 T/L","차단기 조작시험","차단기 조작시험","2018-04-02 09:00","2018-04-02 18:00","2018-04-23 09:00","2018-04-23 18:00","당일",null,null,null,201802120038,"-"]
[273,"전북","김제","신김제동전주#1 T/L","차단기 조작시험","차단기 조작시험","2018-04-04 09:00","2018-04-04 13:00","취소","취소","당일",null,null,null,201802120040,"-"]
[274,"전북","김제","신김제동전주#2 T/L","차단기 조작시험","차단기 조작시험","2018-04-04 13:00","2018-04-04 18:00","취소","취소","당일",null,null,null,201802120041,"-"]
[275,"전북","직할","무주용담수력 T/L","관내S/S 154kV 이상 차단기 조작시험","- 무주S/S 170kV 무주-용담수력T/L CB(657) 조작시험","2018-04-16 10:00","2018-04-20 18:00","2018-04-16 10:00","2018-04-20 18:00","연속",null,null,null,201802130318,"-"]
[276,"전북","직할","북전주용담수력 T/L","관내S/S 154kV 이상 차단기 조작시험","북전주S/S 북전주-용담수력T/L CB(647) 조작시험","2018-04-16 10:00","2018-04-20 18:00","2018-04-16 10:00","2018-04-20 18:00","연속",null,null,null,201802130322,"-"]
[277,"전북","직할","북전주봉동#1 T/L","관내S/S 154kV 이상 차단기 조작시험","북전주S/S 북전주-봉동#1T/L CB(667) 조작시험","2018-04-23 15:00","2018-04-23 17:00","취소","취소","당일",null,null,null,201802140195,"-"]
[278,"전북","직할","북전주봉동#2 T/L","관내S/S 154kV 이상 차단기 조작시험","북전주S/S 북전주-봉동#2T/L CB(657) 조작시험","2018-04-23 13:00","2018-04-23 15:00","취소","취소","당일",null,null,null,201802140194,"-"]
[279,"전북","직할","신김제전주#1 T/L","관내S/S 154kV 차단기 조작시험","전주S/S 신김제-전주#1T/L CB(657) 개폐타임 측정","2018-04-17 13:00","2018-04-17 15:00","2018-04-10 13:00","2018-04-10 15:00","당일",null,null,null,201802140145,"-"]
[280,"전북","직할","이리전주#1 T/L","관내S/S 154kV 차단기 조작시험","전주S/S 이리-전주#1T/L CB(637) 개폐타임 측정","2018-04-16 15:00","2018-04-16 17:00","2018-04-09 15:00","2018-04-09 17:00","당일",null,null,null,201802140142,"-"]
[281,"전북","직할","이리전주#2 T/L","관내S/S 154kV 차단기 조작시험","전주S/S 이리-전주#2T/L CB(647) 개폐타임 측정","2018-04-17 09:30","2018-04-17 11:30","2018-04-10 09:30","2018-04-10 11:30","당일",null,null,null,201802140144,"-"]
[282,"전북","직할","신김제전주#2 T/L","관내S/S 154kV 차단기 조작시험","전주S/S 신김제-전주#2T/L CB(667) 개폐타임 측정","2018-04-17 15:00","2018-04-17 17:00","2018-04-10 15:00","2018-04-10 17:00","당일",null,null,null,201802140146,"-"]
[283,"광주전남","강진","신강진대불#1 T/L","154kV 강진-장흥 등 4개T/L 접속개소해소공사","1. 154kV 강진-장흥 #1,#2 T/L 2. 154kV 대불-남악 #1,#2 T/L 3. 154kV 신강진-대불 #1,#2 T/L 4. 345kV 신화순-신강진 #1,#2 T/L","2018-04-10 07:00","2018-04-13 18:00","2018-04-10 07:00","2018-04-13 18:00","연속",null,null,null,201801110066,"-"]
[284,"광주전남","강진","신강진대불#2 T/L","154kV 강진-장흥 등 4개T/L 접속개소해소공사","1. 154kV 강진-장흥 #1,#2 T/L 2. 154kV 대불-남악 #1,#2 T/L 3. 154kV 신강진-대불 #1,#2 T/L 4. 345kV 신화순-신강진 #1,#2 T/L","2018-04-14 07:00","2018-04-19 18:00","2018-04-14 07:00","2018-04-19 18:00","연속",null,null,null,201801110076,"-"]
[285,"광주전남","광주","곡성남원#1 T/L","18년 광주 변전협력회사 총액공사","곡성S/S 곡성-남원#1T/L GIS 초기점검","2018-04-13 09:00","2018-04-13 18:00","2018-04-13 09:00","2018-04-13 18:00","당일",null,null,null,201802130084,"-"]
[286,"광주전남","광주","곡성남원#2 T/L","18년 광주 변전협력회사 총액공사","곡성S/S 곡성-남원#2T/L GIS 초기점검","2018-04-16 09:00","2018-04-16 18:00","2018-04-16 09:00","2018-04-16 18:00","당일",null,null,null,201802130085,"-"]
[287,"광주전남","광주","담양일곡#1 T/L","154kV 담양-일곡T/L 안전이격확보공사","철탑교체 : 11기 (No.174, 186~189, 199, 200, 216, 220, 223, 224) 애자련 변경 : 1기 (No. 222)","2018-04-07 09:00","2018-04-14 18:00","취소","취소","연속",null,null,null,201712080121,"○"]
[288,"광주전남","광주","신광주곡성#2 T/L","18년 변전협력회사 총액공사","신광주, 곡성S/S 신광주-곡성#2T/L GIS 초기점검","2018-04-05 09:00","2018-04-06 18:00","2018-04-05 09:00","2018-04-06 18:00","연속",null,null,null,201802120051,"-"]
[289,"광주전남","광주","신광주곡성#1 T/L","18년 변전협력회사 총액공사","신광주, 곡성S/S 신광주-곡성#1T/L GIS 초기점검","2018-04-03 09:00","2018-04-04 18:00","2018-04-03 09:00","2018-04-04 18:00","연속",null,null,null,201802120050,"-"]
[290,"광주전남","광주","하남장성#1 T/L ","154kV 장성-영광 등 3개T/L 피뢰기설치공사(4회선 안전이격확보)","안전이격거리확보","2018-04-18 08:00","2018-04-19 18:00","2018-04-29 08:00","2018-05-04 18:00","매일",null,null,null,201802090118,"-"]
[291,"광주전남","광주","하남장성#2 T/L","154kV 장성-영광 등 3개T/L 피뢰기설치공사(4회선 안전이격확보)","4회선 구간 안전이격거리 확보","2018-04-09 08:00","2018-04-10 18:00","2018-04-21 07:00","2018-04-26 18:00","매일",null,null,null,201802090117,"-"]
[292,"광주전남","광주","신광주장성#1 T/L","신광주 154kV 신광주-장성#1T/L GIS 초기점검","신광주 154kV 신광주-장성#1T/L GIS 초기점검 및 장성S/S측 장기 미동작차단기 점검","2018-04-23 09:00","2018-04-23 18:00","취소","취소","당일",null,null,null,201801120118,"-"]
[293,"광주전남","광주","신광주장성#2 T/L","신광주 154kV 신광주-장성#2T/L GIS 초기점검","신광주 154kV 신광주-장성#2T/L GIS 초기점검 및 장성S/S측 장기 미동작차단기 점검","2018-04-24 09:00","2018-04-24 18:00","취소","취소","당일",null,null,null,201801120121,"-"]
[294,"광주전남","목포","장성영광#1 T/L","154kV장성-영광T/L전선접속개소전선교체공사","0 전선 및 금구류 교체 : No.125~160호","2018-04-02 07:00","2018-04-09 18:00","2018-04-21 07:00","2018-04-26 18:00","매일",null,null,null,201802070260,"-"]
[295,"광주전남","목포","장성영광#2 T/L","154kV장성-영광T/L전선접속개소전선교체공사","0 전선 및 금구류 교체 : No.69~160","2018-04-11 07:00","2018-04-19 18:00","2018-04-29 07:00","2018-05-04 18:00","매일",null,null,null,201802070263,"-"]
[296,"광주전남","목포","고창영광 T/L","154kV 장성-영광T/L전선접속개소전선교체공사 (안전이격확보)","고창-영광T/L 전선교체공사 관련 4회선 구간 안전이격거리 확보차","2018-04-11 07:00","2018-04-17 18:00","2018-04-29 07:00","2018-05-04 18:00","매일",null,null,null,201802070444,"-"]
[297,"광주전남","목포","고창영광 T/L","154kV 영광S/S 재원태양광T/L 신규수용공사","170kV GIS(50kA 2000A) 1CCT 송전선로보호반 1식 제어케이블 포설 및 결선 1식 기기기초 1식 기타부대공사 1식","2018-04-01 09:00","2018-04-01 18:00","취소","취소","연속",null,null,null,201802090101,"-"]
[298,"광주전남","목포","고창영광 T/L","154kV 영광S/S 재원태양광T/L 신규수용공사","170kV GIS 재원태양광T/L 신규수용공사 무부하가압 시행","2018-04-07 09:00","2018-04-08 09:00","2018-04-07 09:00","2018-04-08 09:00","연속",null,null,null,201803020033,"-"]
[299,"광주전남","목포","영광홍농 T/L","154kV 장성-영광T/L전선접속개소전선교체공사 (안전이격확보)","영광-홍농T/L 전선교체공사 관련 4회선 구간 안전이격거리 확보차","2018-04-02 07:00","2018-04-08 18:00","2018-04-21 07:00","2018-04-26 18:00","매일",null,null,null,201802070437,"-"]
[300,"광주전남","순천","서순천주암HP T/L","154kV 승주-서순천T/L 안전이격확보공사","154kV 승주-서순천T/L 안전이격확보공사 -철탑교체 10기, 전선교체 10.132C-km","2018-04-11 07:00","2018-04-17 18:00","2018-04-11 07:00","2018-04-17 18:00","연속",null,null,null,201802200278,"-"]
[301,"광주전남","순천","승주서순천 T/L","154kV 승주-서순천T/L 안전이격확보공사","154kV 승주-서순천T/L 안전이격확보공사 -철탑교체 10기, 전선교체 10.132C-km","2018-04-01 07:00","2018-04-03 18:00","2018-04-01 07:00","2018-04-03 18:00","연속",null,null,null,201802200272,"-"]
[302,"광주전남","순천","승주주암HP T/L","154kV 승주-서순천T/L 안전이격확보공사","154kV 승주-서순천T/L 안전이격확보공사 -철탑교체 10기, 전선교체 10.132C-km","2018-04-04 07:00","2018-04-10 18:00","2018-04-04 07:00","2018-04-10 18:00","연속",null,null,null,201802200275,"-"]
[303,"광주전남","순천","승주서순천 T/L","154kV 승주-서순천T/L 안전이격확보공사","154kV 승주-서순천T/L 안전이격확보공사 -철탑교체 10기, 전선교체 10.132C-km","2018-04-18 07:00","2018-04-24 18:00","2018-04-18 07:00","2018-04-24 18:00","연속",null,null,null,201802200281,"-"]
[304,"광주전남","순천","여천여수산단#1 T/L","상반기 170kV GIS 정밀점검공사","여수산단 여천-여수산단#1T/L 정밀점검","2018-04-19 09:00","2018-04-20 18:00","2018-04-19 09:00","2018-04-20 18:00","연속",null,null,null,201802120170,"-"]
[305,"광주전남","순천","여수TP용성#2 T/L","154kV 여수TP-용성 #2T/L(자기애관 교체공사)","○ 154kV 여수TP-용성 #2T/L 자기애관을 폴리머애관으로 교체(6대)","2018-04-11 09:00","2018-04-12 18:00","2018-04-11 09:00","2018-04-12 18:00","연속",null,null,null,201801080174,"-"]
[306,"광주전남","순천","여수TP용성#1 T/L","154kV 여수TP-용성 #1T/L(자기애관 교체공사)","○ 154kV 여수TP-용성 #1T/L 자기애관을 폴리머애관으로 교체(6대)","2018-04-09 09:00","2018-04-10 18:00","2018-04-09 09:00","2018-04-10 18:00","연속",null,null,null,201801080173,"-"]
[307,"광주전남","직할","나주금천#1 T/L","154kV 나주S/S 옥내화 토건공사","- 나주S/S 옥내화 토건공사(전력구 시설) 송전전력구 114m, 관로 48m","2018-04-09 08:00","2018-04-10 18:00","2018-04-09 08:00","2018-04-10 18:00","연속",null,null,null,201802070156,"-"]
[308,"광주전남","직할","신화순나주#2 T/L","154kV 나주S/S 옥내화 토건공사","- 나주S/S 옥내화 토건공사(전력구 시설) 송전전력구 114m, 관로 48m","2018-04-07 13:00","2018-04-07 18:00","2018-04-07 13:00","2018-04-07 18:00","당일",null,null,null,201802190036,"-"]
[309,"광주전남","직할","나주엄다#2 T/L","154kV 나주S/S 옥내화 토건공사","- 나주S/S 옥내화 토건공사(전력구 시설) 송전전력구 114m, 관로 48m","2018-04-07 08:00","2018-04-07 13:00","2018-04-07 08:00","2018-04-07 13:00","당일",null,null,null,201802190032,"-"]
[310,"광주전남","직할","남광주S/S 남광주-금천#1T/L GIS","18-19년 직할 변전협력회사 총액공사","- 170kV GIS 보통점검","2018-04-23 09:00","2018-04-23 18:00","2018-04-23 09:00","2018-04-23 18:00","당일",null,null,null,201802060605,"-"]
[311,"대구","경산","진량노변 T/L","노변S/S 진량-노변T/L 휴전","170kV GIS 정밀점검","2018-04-21 09:00","2018-04-22 18:00","취소","취소","연속",null,null,null,201802050266,"-"]
[312,"대구","경산","범물남대구#1 T/L","범물S/S 범물-남대구#1T/L 휴전","GIS 보통점검","2018-04-06 09:00","2018-04-06 13:00","2018-04-06 09:00","2018-04-06 13:00","당일",null,null,null,201802020118,"-"]
[313,"대구","경산","범물남대구#2 T/L","범물S/S 범물-남대구#2T/L 휴전","GIS 보통점검","2018-04-06 13:00","2018-04-06 18:00","2018-04-06 13:00","2018-04-06 18:00","당일",null,null,null,201802020119,"-"]
[314,"대구","경산","신경산진량 T/L","진량S/S 신경산-진량T/L 휴전","170kV GIS 정밀점검","2018-04-28 09:00","2018-04-29 18:00","2018-04-28 09:00","2018-04-29 18:00","연속",null,null,null,201802050267,"-"]
[315,"대구","경산","하양봉무#2 T/L","345kV 선산-신포항T/L 전선접속개소 전력선 교체공사","345kV 신포항-북대구T/L No.66~67 선하 154kV 하양-봉무T/L No.43~44 경과선로 안전확보(21,27,28일 당일만 휴전, 즉시가압가능)","2018-04-21 08:00","2018-04-28 18:00","2018-04-21 08:00","2018-04-28 18:00","매일",null,null,null,201802120361,"-"]
[316,"대구","경산","하양봉무#1 T/L","345kV 선산-신포항T/L 전선접속개소 전력선 교체공사","345kV 신포항-북대구T/L No.66~67 선하 154kV 하양-봉무T/L No.43~44 경과선로 안전확보(21,27,28일 당일만 휴전, 즉시가압가능)","2018-04-21 08:00","2018-04-28 18:00","2018-04-21 08:00","2018-04-28 18:00","매일",null,null,null,201802120360,"-"]
[317,"대구","달성","대구봉덕#1 T/L","달성전력지사 GIS 정밀점검공사 TEST 선로","달성전력지사 GIS 정밀점검공사 TEST 선로","2018-04-17 13:00","2018-04-17 18:00","2018-04-17 13:00","2018-04-17 18:00","당일",null,null,null,201802070070,"-"]
[318,"대구","달성","상인봉덕#1 T/L","달성전력지사 GIS 정밀점검공사 TEST 선로","달성전력지사 GIS 정밀점검공사 TEST 선로","2018-04-26 13:00","2018-04-28 18:00","2018-04-26 13:00","2018-04-28 18:00","매일",null,null,null,201802070101,"-"]
[319,"대구","달성","대구봉덕#2 T/L","달성전력지사 GIS 정밀점검공사","달성전력지사 GIS 정밀점검공사","2018-04-30 09:00","2018-05-03 18:00","취소","취소","연속",null,null,null,201802070105,"-"]
[320,"대구","달성","대구봉덕#1 T/L","달성전력지사 GIS 정밀점검공사","달성전력지사 GIS 정밀점검공사","2018-04-26 09:00","2018-04-29 18:00","2018-04-26 09:00","2018-04-29 18:00","연속",null,null,null,201802070100,"-"]
[321,"대구","달성","강창성서#1 T/L","달성전력지사 GIS 정밀점검공사 TEST 선로","달성전력지사 GIS 정밀점검공사 TEST 선로","2018-04-14 13:00","2018-04-14 18:00","2018-04-14 13:00","2018-04-14 18:00","당일",null,null,null,201802070109,"-"]
[322,"대구","달성","강창성서#2 T/L","달성전력지사 GIS 정밀점검공사 TEST 선로","달성전력지사 GIS 정밀점검공사 TEST 선로","2018-04-20 13:00","2018-04-20 18:00","2018-04-20 13:00","2018-04-20 18:00","당일",null,null,null,201802070110,"-"]
[323,"대구","달성","달서팔달#1 T/L","154kV 달서-팔달 등 2개T/L 지장선로 이설공사","○ 목 적 : 대구광역시 매립장증설사업에 지장이 되어 이설 ○ 구 간 : 154kV 달서-팔달T/L No.10~13, 4회선 [하단 : 북대구-팔달T/L] ○ 수 량 : 철탑 이설 2기(가철탑 2기), 전력선교체 4C, 1.051km (A410㎟, HST410㎟)","2018-04-08 08:00","2018-05-03 18:00","취소","취소","연속",null,null,null,201802070069,"-"]
[324,"대구","달성","북대구팔달#1 T/L","154kV 달서-팔달 등 2개T/L 지장선로 이설공사","○ 목 적 : 대구광역시 매립장증설사업에 지장이 되어 이설 ○ 구 간 : 154kV 달서-팔달T/L No.10~13, 4회선 [하단 : 북대구-팔달T/L] ○ 수 량 : 철탑 이설 2기(가철탑 2기), 전력선교체 4C, 1.051km (A410㎟, HST410㎟)","2018-04-08 08:00","2018-05-03 18:00","취소","취소","연속",null,null,null,201802070072,"-"]
[325,"대구","직할","내당두류#2 T/L","GIS 정밀점검","GIS 정밀점검","2018-04-26 09:30","2018-04-28 18:00","2018-04-26 09:30","2018-04-28 18:00","연속",null,null,null,201802070326,"-"]
[326,"대구","직할","팔달내당#1 T/L","GIS 정밀점검","GIS 정밀점검","2018-04-16 09:30","2018-04-18 18:00","2018-04-16 09:30","2018-04-18 18:00","연속",null,null,null,201802070323,"-"]
[327,"대구","직할","팔달내당#2 T/L","GIS 정밀점검","GIS 정밀점검","2018-04-19 09:30","2018-04-21 18:00","2018-04-19 09:30","2018-04-21 18:00","연속",null,null,null,201802070324,"-"]
[328,"대구","직할","내당두류#1 T/L","GIS 정밀점검","GIS 정밀점검","2018-04-23 09:30","2018-04-25 18:00","2018-04-23 09:30","2018-04-25 18:00","연속",null,null,null,201802070325,"-"]
[329,"대구","직할","노변효목#1 T/L","GIS 보통점검","GIS 보통점검","2018-04-17 09:30","2018-04-17 18:00","2018-04-17 09:30","2018-04-17 18:00","당일",null,null,null,201802070343,"-"]
[330,"대구","직할","노변효목#2 T/L","GIS 보통점검","GIS 보통점검","2018-04-18 09:30","2018-04-18 18:00","2018-04-18 09:30","2018-04-18 18:00","당일",null,null,null,201802070345,"-"]
[331,"대구","칠곡","관음구암#2 T/L","345kV 선산-신포항T/L 전선접속개소 전력선 교체공사","345kV 신포항-북대구T/L No.49~50 선하 154kV 관음-구암T/L No.37~38 경과선로 안전확보(16,20일 당일만 휴전, 즉시가압가능)","2018-04-16 08:00","2018-04-20 18:00","2018-04-16 08:00","2018-04-20 18:00","매일",null,null,null,201802120357,"-"]
[332,"대구","칠곡","관음구암#1 T/L","345kV 선산-신포항T/L 전선접속개소 전력선 교체공사","345kV 신포항-북대구T/L No.49~50 선하 154kV 관음-구암T/L No.37~38 경과선로 안전확보(16,20일 당일만 휴전, 즉시가압가능)","2018-04-16 08:00","2018-04-20 18:00","2018-04-16 08:00","2018-04-20 18:00","매일",null,null,null,201802120355,"-"]
[333,"대구","포항","신포항S/S 154kV #65 BUS","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 상부모선, CB, DS 및 POST, BEAM 철거 등","2018-04-09 08:00","2018-04-10 18:00","취소","취소","연속",null,null,null,201801110047,"-"]
[334,"경북","구미","남인동인동#2 T/L","154kV 남인동-인동 등 2개T/L 전력선 교체공사","공사개요 가. 공사구간 : 154kV 남인동-인동T/L No.14∼18, 27∼31, 41∼46 154kV 산동-군위T/L No.29∼42, 58∼60","2018-04-23 07:30","2018-04-29 18:00","2018-04-23 07:30","2018-04-29 18:00","연속",null,null,null,201802050008,"-"]
[335,"경북","구미","선산청리#1 T/L","선산S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 공사","2018-04-09 08:00","2018-04-13 18:00","2018-04-09 08:00","2018-04-13 18:00","연속",null,null,null,201802200005,"-"]
[336,"경북","구미","남인동인동#1 T/L","2018년 구미전력지사 170kV 정밀점검(인동S/S 677GIS)","-170kV GIS 정밀점검(인동S/S 677GIS)","2018-04-16 07:30","2018-04-22 18:00","2018-04-16 07:30","2018-04-22 18:00","연속",null,null,null,201802060111,"-"]
[337,"경북","영주","신영주안동#1 T/L","2018-19 송전협력업체 총액공사","154kV 신영주-안동#1T/L 스페이서 교채공사(No.1-56)","2018-04-23 07:00","2018-04-26 18:00","2018-04-23 07:00","2018-04-26 18:00","연속",null,null,null,201802140028,"-"]
[338,"경북","영주","신영주안동#2 T/L","2018-19 송전협력업체 총액공사","154kV 신영주-안동#2T/L 스페이서 교체공사(No.1-56)","2018-04-27 07:00","2018-04-30 18:00","2018-04-27 07:00","2018-04-30 18:00","연속",null,null,null,201802140029,"-"]
[342,"경북","직할","봉화평해 T/L","154kV 울진 현종산 풍력발전단지 송전선로 건설공사","전력선 신설 및 이설, 우회 가선로 구성, 가철탑 철거","2018-04-13 07:00","2018-04-13 18:00","취소","취소","당일",null,null,null,201802210131,"-"]
[343,"경북","직할","봉화평해 T/L","154kV 울진 현종산 풍력발전단지 송전선로 건설공사","전력선 이설 및 긴선압축, 가선로 구성","2018-04-17 07:00","2018-04-20 18:00","취소","취소","연속",null,null,null,201802210140,"-"]
[344,"경북","직할","울진평해 T/L","154kV 울진 현종산 풍력발전단지 송전선로 건설공사","분기철탑 검설(기설 No.104 철거 및 신설 No.14 조립, 전력선 가선)","2018-04-14 07:00","2018-04-16 18:00","취소","취소","연속",null,null,null,201802210137,"-"]
[345,"부산울산","동부산","명례고리NP T/L","154kV 명례-고리NP T/L 9호 지장철탑이설공사","154kV 명례-고리NP T/L 9호 계탑 및 4~13호 전선교체(2.970km)","2018-04-14 08:00","2018-04-21 18:00","2018-04-14 08:00","2018-04-21 18:00","연속",null,null,null,201802010114,"-"]
[346,"부산울산","동부산","정관고리NP T/L","154kV 명례-고리NP T/L 9호 지장철탑이설공사","154kV 명례-고리NP T/L 9호 계탑 및 4~13호간 전선교체(2.970km)","2018-04-14 08:00","2018-04-21 18:00","2018-04-14 08:00","2018-04-21 18:00","연속",null,null,null,201802010115,"-"]
[347,"부산울산","동부산","구서명장#1 T/L","신양산-구서등 5개T/L자기애관 교체공사","구서명장#1 T/L 자기애관 교체공사","2018-04-26 09:00","2018-04-28 18:00","2018-04-26 09:00","2018-04-28 18:00","연속",null,null,null,201802190013,"-"]
[348,"부산울산","동부산","구서명장#2 T/L","신양산-구서등 5개T/L 자기애관 교체공사","구서명장#2 T/L 자기애관 교체공사","2018-04-30 09:00","2018-05-02 18:00","2018-04-30 09:00","2018-05-02 18:00","연속",null,null,null,201802190017,"-"]
[349,"부산울산","동부산","구서노포#2 T/L","18년 가공송전선로 순시점검 위탁공사","154kV 구서-노포T/L 정밀점검 구간 : 구서C/H ~ 노포S/S(18기)","2018-04-23 09:00","2018-04-25 18:00","2018-04-23 09:00","2018-04-25 18:00","매일",null,null,null,201802090498,"-"]
[350,"부산울산","동부산","구서노포#1 T/L","18년 가공송전선로 순시점검 위탁공사","154kV 구서-노포T/L 정밀점검 구간 : 구서C/H ~ 노포S/S(18기)","2018-04-18 09:00","2018-04-20 18:00","2018-04-18 09:00","2018-04-20 18:00","매일",null,null,null,201802090497,"-"]
[351,"부산울산","동부산","북부산미남#2 T/L","미남S/S 170kV GIS 조작시험","미남S/S 170kV GIS 조작시험(687)","2018-04-13 09:30","2018-04-13 14:00","2018-04-13 09:30","2018-04-13 14:00","당일",null,null,null,201802110037,"-"]
[352,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 장기사용 6333GIS 대체공사","서창S/S 장기사용 6333GIS 대체관련 1DS 시험가압(웅촌-서창#1T/L)","2018-04-23 17:00","2018-04-24 17:00","2018-04-23 17:00","2018-04-24 17:00","당일",null,null,null,201802200174,"-"]
[353,"부산울산","동부산","웅촌서창#1 T/L","154kV 웅촌-서창T/L 20호 지장철탑이설공사","구간 : 17.1~21 철탑교체 : 20호","2018-04-10 08:00","2018-04-14 18:00","취소","취소","연속",null,null,null,201802070046,"-"]
[354,"부산울산","동부산","웅촌서창#2 T/L","서창S/S 장기사용 6333GIS 대체공사","서창S/S 장기사용 6333GIS 대체관련 2DS 시험가압(웅촌-서창#2T/L)","2018-04-30 17:00","2018-05-01 17:00","2018-04-30 17:00","2018-05-01 17:00","당일",null,null,null,201802200177,"-"]
[355,"부산울산","동부산","웅촌서창#2 T/L","154kV 웅촌-서창T/L 20호 지장철탑이설공사","구간 : 17.1~21 철탑교체 : 20호","2018-04-02 08:00","2018-04-04 18:00","2018-04-02 08:00","2018-04-04 18:00","연속",null,null,null,201802070043,"-"]
[356,"부산울산","동부산","웅촌서창#1 T/L","154kV 웅촌-서창T/L 20호 지장철탑이설공사","구간 : 17.1~21 철탑교체 : 20호","2018-04-02 08:00","2018-04-04 18:00","취소","취소","연속",null,null,null,201802070041,"-"]
[357,"부산울산","동부산","노포정관#2 T/L","신양산-구서등 5개T/L 자기애관 교체공사","노포정관#2 T/L 자기애관 교체공사","2018-04-15 09:00","2018-04-17 18:00","2018-04-15 09:00","2018-04-17 18:00","연속",null,null,null,201802190027,"-"]
[358,"부산울산","동부산","노포정관#1 T/L","신양산-구서등 5개T/L 자기애관 교체공사","노포정관#1 T/L 자기애관 교체공사","2018-04-12 09:00","2018-04-14 18:00","2018-04-12 09:00","2018-04-14 18:00","연속",null,null,null,201802190021,"-"]
[359,"부산울산","동부산","정보대연 T/L","정보S/S 170kV GIS 정밀점검공사","정보S/S 170kV GIS 정밀점검관련 시험가압(정보-대연T/L)","2018-04-25 17:00","2018-04-25 18:00","2018-04-25 17:00","2018-04-25 18:00","당일",null,null,null,201802200068,"-"]
[360,"부산울산","동부산","수영정보#1 T/L","정보S/S 170kV GIS 정밀점검공사","정보S/S 170kV GIS 정밀점검공사(627)","2018-04-26 09:00","2018-04-27 18:00","2018-04-26 09:00","2018-04-27 18:00","당일",null,null,null,201802140294,"-"]
[361,"부산울산","북부산","북부산삼랑진PP T/L","154kV 삼랑진양수T/L 전선접속개소 전선교체","북부산-삼랑진T/L No.1~7, 12~24, 54~62호 전선교체","2018-04-22 07:00","2018-05-05 18:00","2018-04-22 07:00","2018-05-05 18:00","연속",null,null,null,201802050183,"○"]
[362,"부산울산","북부산","북부산호포 T/L","154kV 삼랑진양수T/L 전선접속개소 전선교체","북부산-물금T/L No.12~24호 전선교체관련 안전이격선로(비상시 가압가능)","2018-04-15 07:00","2018-04-21 18:00","2018-04-15 07:00","2018-04-21 18:00","매일",null,null,null,201802050178,"-"]
[363,"부산울산","북부산","북부산물금 T/L","154kV 삼랑진양수T/L 전선접소개소 전선교체","북부산-물금T/L No.1~7, 12~24호 전선교체","2018-04-12 07:00","2018-04-21 18:00","2018-04-12 07:00","2018-04-21 18:00","연속",null,null,null,201802050175,"-"]
[364,"부산울산","북부산","북부산물금 T/L","154kV 삼랑진양수T/L 전선접속개소 전선교체공사","북부산-호포T/L No.12~24호 전선교체관련 안전이격선로(비상시 가압가능)","2018-04-05 07:00","2018-04-11 18:00","2018-04-05 07:00","2018-04-11 18:00","매일",null,null,null,201802050174,"-"]
[365,"부산울산","북부산","북부산양산 T/L","154kV 삼랑진양수T/L 전선접속개소 전선교체","북부산-삼랑진T/L No.12~24, 54~62호 전선교체관련 안전이격선로(비상시 가압가능)","2018-04-26 07:00","2018-05-05 18:00","2018-04-26 07:00","2018-05-05 18:00","매일",null,null,null,201802050185,"-"]
[366,"부산울산","북부산","북부산호포 T/L","154kV 삼랑진양수T/L 전선접속개소 전선교체","154kV 북부산-호포T/L No.1~7, 12~24호 전선교체","2018-04-02 07:00","2018-04-11 18:00","2018-04-02 07:00","2018-04-11 18:00","연속",null,null,null,201802050173,"-"]
[367,"부산울산","서부산","용원녹공#1 T/L","녹공S/S 154kV 용원-녹공 #1T/L GIS(617) 정밀점검","녹공S/S 154kV 용원-녹공 #1T/L GIS(617) 정밀점검","2018-04-21 08:00","2018-04-22 22:00","취소","취소","연속",null,null,null,201802090291,"-"]
[368,"부산울산","서부산","녹공마천#2 T/L","녹공S/S 154kV 녹공-마천#2T/L(647) 개폐타임 측정","녹공S/S 154kV 녹공-마천#2T/L(647) 개폐타임 측정","2018-04-16 14:00","2018-04-16 18:00","2018-04-16 14:00","2018-04-16 18:00","당일",null,null,null,201802080048,"-"]
[369,"부산울산","서부산","녹공마천#1 T/L","녹공S/S 154kV 녹공-마천#1T/L(637) 개폐타임 측정","녹공S/S 154kV 녹공-마천#1T/L(637) 개폐타임 측정","2018-04-16 10:00","2018-04-16 14:00","2018-04-16 10:00","2018-04-16 14:00","당일",null,null,null,201802080047,"-"]
[370,"부산울산","서부산","용원녹공#2 T/L","녹공S/S 154kV 용원-녹공 #2T/L GIS(627) 정밀점검","녹공S/S 154kV 용원-녹공 #2T/L GIS(627) 정밀점검","2018-04-28 08:00","2018-04-29 22:00","취소","취소","연속",null,null,null,201802090296,"-"]
[371,"부산울산","서부산","서부산S/S #2 S/T CB","서부산S/S #2S/T GIS(6L7) 보통점검","서부산S/S #2S/T GIS(6L7) 보통점검","2018-04-11 10:00","2018-04-11 18:00","2018-04-11 10:00","2018-04-11 18:00","당일",null,null,null,201802080044,"-"]
[372,"부산울산","서부산","서부산신평#1 T/L","345kV 서부산S/S 154kV 인출선로 정비공사","154kV XLPE 2000㎟ 케이블 1C- 0.03km 철거, 설치","2018-04-19 08:00","2018-05-11 18:00","2018-04-19 08:00","2018-05-11 18:00","연속",null,null,null,201802090037,"-"]
[373,"부산울산","울산","신울산S/S 67-68-0 SEC CB","2018-19년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV #63-68 모선보호반 대체","2018-04-23 09:00","2018-04-26 18:00","2018-04-23 09:00","2018-04-26 18:00","연속",null,null,null,201802090236,"-"]
[374,"부산울산","울산","신울산S/S 154kV #3 BUS TIE CB","2018-19년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV #63-68 모선보호반 대체","2018-04-23 09:00","2018-04-26 18:00","2018-04-23 09:00","2018-04-26 18:00","연속",null,null,null,201802090231,"-"]
[375,"부산울산","울산","신울산S/S 62-63-0 SEC CB","2018-19년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV #63-68 모선보호반 대체","2018-04-23 09:00","2018-04-26 18:00","2018-04-23 09:00","2018-04-26 18:00","연속",null,null,null,201802090234,"-"]
[376,"부산울산","울산","온산처용#1 T/L","154㎸ 신울산-웅촌등 7개 T/L 자기애관 교체공사","지중송전선로용 자기애관(EBA) → 폴리머 애관 교체공사","2018-04-03 09:00","2018-04-06 18:00","2018-04-03 09:00","2018-04-06 18:00","연속",null,null,null,201802080178,"-"]
[377,"부산울산","울산","온산처용#2 T/L","154㎸ 신울산-웅촌등 7개 T/L 자기애관 교체공사","지중송전선로용 자기애관(EBA) → 폴리머 애관 교체공사","2018-04-09 09:00","2018-04-12 18:00","2018-04-09 09:00","2018-04-12 18:00","연속",null,null,null,201802080179,"-"]
[378,"부산울산","울산","울산T/P 154kV #61 BUS","2018년 울산P/O 170kV 개폐장치 정밀점검공사","울산T/P 170kV #1,2G/T(6533) GIS 정밀점검관련 2DS 정밀점검 및 시험가압","2018-04-04 08:00","2018-04-05 18:00","2018-04-04 08:00","2018-04-05 18:00","연속",null,null,null,201802090254,"-"]
[379,"부산울산","울산","용연울산TP#2 T/L","2018년 울산P/O 170kV 개폐장치 정밀점검공사","울산T/P 170kV #1,2G/T(6533) GIS 정밀점검관련 2DS 시험가압","2018-04-03 17:00","2018-04-03 18:00","2018-04-03 17:00","2018-04-03 18:00","당일",null,null,null,201802090252,"-"]
[380,"부산울산","울산","울산T/P #1,2 G/T CB","2018년 울산P/O 170kV 개폐장치 정밀점검공사","울산T/P 170kV #1,2G/T(6533) GIS 정밀점검","2018-04-03 08:00","2018-04-05 18:00","2018-04-03 08:00","2018-04-05 18:00","연속",null,null,null,201802090249,"-"]
[381,"부산울산","울산","울산T/P 154kV #66 BUS","2018년 울산P/O 170kV 개폐장치 정밀점검공사","울산T/P 170kV #1,2G/T(6533) GIS 정밀점검관련 2DS 정밀점검 및 시험가압","2018-04-03 08:00","2018-04-03 18:00","2018-04-03 08:00","2018-04-03 18:00","당일",null,null,null,201802090253,"-"]
[382,"부산울산","울산","울산울산TP#1 T/L","2018년 울산P/O 170kV 개폐장치 정밀점검공사","울산T/P 170kV S/T(6433) GIS 정밀점검관련 시험가압","2018-04-02 17:00","2018-04-02 18:00","2018-04-02 17:00","2018-04-02 18:00","당일",null,null,null,201802090250,"○"]
[383,"부산울산","울산","용연울산TP#1 T/L","2018년 울산P/O 170kV 개폐장치 정밀점검공사","울산T/P 170kV #1,2G/T(6533) GIS 정밀점검관련 6533,6531 시험가압","2018-04-05 17:00","2018-04-05 18:00","2018-04-05 17:00","2018-04-05 18:00","당일",null,null,null,201802090255,"-"]
[384,"부산울산","울산","울산T/P 154kV #65 BUS","2018년 울산P/O 170kV 개폐장치 정밀점검공사","울산T/P 170kV S/T(6433) GIS 정밀점검관련 시험가압","2018-04-02 17:00","2018-04-02 18:00","2018-04-02 17:00","2018-04-02 18:00","당일",null,null,null,201802090251,"-"]
[385,"부산울산","울산","울산T/P S/T CB","2018년 울산P/O 170kV 개폐장치 정밀점검공사","울산T/P 170kV S/T(6433) GIS 정밀점검","2018-04-01 08:00","2018-04-02 18:00","2018-04-01 08:00","2018-04-02 18:00","연속",null,null,null,201802090247,"-"]
[386,"부산울산","울산","울산S/S #1 EM.Tr CB","2018-19년 울산전력지사 변전협력회사 총액공사","울산S/S ESS용 모선보강작업","2018-04-09 09:00","2018-04-13 18:00","2018-04-09 09:00","2018-04-13 18:00","연속",null,null,null,201802090242,"-"]
[387,"부산울산","울산","울주S/S #1EM.Tr CB","2018-19년 울산전력지사 변전협력회사 총액공사","울주S/S 23kV E-GIS 조작관련 회로보완","2018-04-12 09:00","2018-04-12 18:00","2018-04-12 09:00","2018-04-12 18:00","당일",null,null,null,201802090243,"-"]
[388,"부산울산","울산","웅촌서창#1 T/L","2018년 울산P/O 170kV 개폐장치 정밀점검공사","웅촌S/S 170kV #1M.Tr 1차(6133) GIS 정밀점검관련 시험가압","2018-04-19 17:00","2018-04-19 18:00","2018-04-19 17:00","2018-04-19 18:00","당일",null,null,null,201802200016,"-"]
[389,"부산울산","울산","웅촌서창#1 T/L","2018년 울산P/O 170kV 개폐장치 정밀점검공사","웅촌S/S 170kV #1BUS-TIE(6100) GIS 정밀점검관련 시험가압","2018-04-17 17:00","2018-04-17 18:00","2018-04-17 17:00","2018-04-17 18:00","당일",null,null,null,201802200015,"-"]
[390,"부산울산","울산","효문방어진 T/L","2018-19년 울산전력지사 변전협력회사 총액공사","1.효문S/S 170kV 효문-방어진T/L GIS 보통점검 2.방어진S/S 170kV GIS 차단기 동작시험 3.#1-1,1-2,2-2Sh.C용 VCB 대체관련 안전이격","2018-04-11 07:00","2018-04-11 18:00","2018-04-11 07:00","2018-04-11 18:00","당일",null,null,null,201802130072,"-"]
[391,"부산울산","직할","우동대연 T/L","2018년 직할 변전협력회사 총액공사","대연S/S 우동-대연T/L(627) GIS 미동작점검","2018-04-04 10:00","2018-04-04 12:00","2018-04-04 10:00","2018-04-04 12:00","당일",null,null,null,201802090465,"-"]
[392,"부산울산","직할","서부산부민#1 T/L","345kV 서부산S/S 154kV 인출선로 정비공사","154kV XLPE 2000㎟ 케이블 1C- 0.03km 철거, 설치","2018-04-19 08:00","2018-05-11 18:00","2018-04-19 08:00","2018-05-11 18:00","연속",null,null,null,201802090042,"-"]
[393,"부산울산","직할","수정범일#1 T/L","154kV 범일 등 3개S/S 지중송전케이블 선종교체공사","154kV 수정-범일T/L 선종교체공사(OF1200 --&gtXLPE 1200, 0.7km) - 공사구간 : 수정S/S ~ S/J, 범일S/S ~ J/B#7-2","2018-04-16 09:00","2018-05-28 18:00","취소","취소","연속",null,null,null,201802090389,"-"]
[394,"부산울산","직할","수정범일#2 T/L","2018년 직할 변전협력회사 총액공사","수정S/S 수정-범일#2T/L(617) GIS 보통점검","2018-04-12 10:00","2018-04-12 17:00","2018-04-12 10:00","2018-04-12 17:00","당일",null,null,null,201802090468,"-"]
[395,"부산울산","직할","신대연양정#1 T/L","2018년 직할 관내 170kV GIS 정밀점검공사","양정S/S 명장-양정#2T/L GIS(647) 정밀점검 #1DS 시험가압선로","2018-04-07 17:00","2018-04-07 18:00","2018-04-07 17:00","2018-04-07 18:00","당일",null,null,null,201802090444,"-"]
[396,"부산울산","직할","신대연양정#1 T/L","2018년 직할 관내 170kV GIS 정밀점검","양정S/S 신대연-양정#1T/L(617) GIS 정밀점검","2018-04-09 08:00","2018-04-11 18:00","2018-04-09 08:00","2018-04-11 18:00","연속",null,null,null,201802090450,"-"]
[397,"부산울산","직할","신대연양정#2 T/L","2018년 직할 관내 170kV GIS 정밀점검공사","양정S/S 명장-양정#2T/L GIS(647) 정밀점검 #2DS 시험가압선로","2018-04-05 18:00","2018-04-05 19:00","2018-04-05 18:00","2018-04-05 19:00","당일",null,null,null,201802090438,"-"]
[398,"부산울산","직할","신대연양정#1 T/L","2018년 직할 관내 170kV GIS 정밀점검공사","양정S/S 명장-양정#1T/L GIS(637) 정밀점검 #1DS 시험가압선로","2018-04-04 17:00","2018-04-04 18:00","2018-04-04 17:00","2018-04-04 18:00","당일",null,null,null,201802090432,"-"]
[399,"부산울산","직할","신대연양정#2 T/L","2018년 직할 관내 170kV GIS 정밀점검","양정S/S 신대연-양정#2T/L(627) GIS 정밀점검","2018-04-12 08:00","2018-04-14 18:00","2018-04-12 08:00","2018-04-14 18:00","연속",null,null,null,201802090452,"-"]
[400,"부산울산","직할","양정범천 T/L","2018년 직할 관내 170kV GIS 정밀점검","양정S/S 양정-범천T/L(657) GIS 정밀점검","2018-04-18 08:00","2018-04-20 18:00","2018-04-18 08:00","2018-04-20 18:00","연속",null,null,null,201802090454,"-"]
[401,"부산울산","직할","신대연양정#2 T/L","2018년 직할 관내 170kV GIS 정밀점검공사","양정S/S 명장-양정#1T/L GIS(637) 정밀점검 #2DS 시험가압선로","2018-04-02 18:00","2018-04-02 19:00","2018-04-02 18:00","2018-04-02 19:00","당일",null,null,null,201802090426,"-"]
[402,"경남","직할","마천진해#1 T/L","2018년 경남지역본부 직할 송전협력회사 총액공사","마천진해#1 T/L 애자련보강공사(27, 28호)","2018-04-10 08:00","2018-04-11 18:00","2018-04-10 08:00","2018-04-11 18:00","매일",null,null,null,201802130295,"-"]
[403,"경남","직할","마천진해#2 T/L","2018년 경남지역본부 직할 송전협력회사 총액공사","마천진해#2 T/L 애자련보강공사(27, 28호)","2018-04-17 08:00","2018-04-18 18:00","2018-04-17 08:00","2018-04-18 18:00","매일",null,null,null,201802130298,"-"]
[404,"경남","직할","신월동읍#2 T/L","신월S/S 154kV 신월-동읍#2T/L CB 보통점검","신월S/S 154kV 신월-동읍#2T/L CB 보통점검","2018-04-23 09:30","2018-04-23 17:30","취소","취소","당일",null,null,null,201802050270,"-"]
[405,"경남","진주","사봉개양 T/L","154kV 사봉분기(증)T/L 및 사봉S/S SW 증설 공사","기설 154kV 개양-가야T/L No.44 ~ 기설 154kV 사봉S/S ○ 상단 → 하단 3상 이설 ○ 기설 No. 7 우측암 변경, 긴선분리 및 연결 ○ 신설 철탑(No.1) 우측회선 가선 ○ 보호반이설(사봉-개양T/L→사봉-개양#1T/L) 케이블결선, 준공시험","2018-04-21 07:00","2018-04-24 18:00","2018-04-21 07:00","2018-04-24 18:00","연속",null,null,null,201802060067,"-"]
[406,"경남","진주","의령동진주#1 T/L","의령S/S 154kV 의령-동진주#1T/L CB(617) 정밀점검","의령S/S 154kV 의령-동진주T/L CB(617) 정밀점검 병행:의령S/S 의령-동진주#1T/L LA(A,B,C) 보통점검 동진주S/S 의령-동진주#1T/L CB(617)개폐장치 조작시험","2018-04-28 09:30","2018-04-29 18:30","2018-04-28 09:30","2018-04-29 18:30","연속",null,null,null,201802050330,"-"]
[407,"경남","진주","의령함양 T/L","의령S/S 154kV 의령-함양T/L CB(637) 정밀점검","의령S/S 154kV 의령-함양T/L CB(637) 정밀점검 병행 : 함양S/S 154kV 의령-함양T/L PT,LA(A,B,C) 보통점검 함양S/S 의령-함양#1T/L CB(667) 개폐장치 조작시험 의령S/S 의령-함양T/L LA(A,B,C) 보통점검","2018-04-14 09:30","2018-04-15 18:30","2018-04-14 09:30","2018-04-15 18:30","연속",null,null,null,201802050329,"-"]
[408,"경남","진주","의령산청 T/L","의령S/S 154kV 의령-산청T/L CB(647) 정밀점검","의령S/S 154kV 의령-산청T/L CB(647) 정밀점검 병행 : 산청S/S 의령-산청T/L CB(627) 보통점검 산청S/S 의령-산청T/L LA(A,B,C) 보통점검 의령S/S 의령-산청T/L LA(A,B,C) 보통점검","2018-04-21 09:30","2018-04-22 18:30","2018-04-21 09:30","2018-04-22 18:30","연속",null,null,null,201712290080,"-"]
[409,"경남","진주","진주개양#2 T/L","154kV 하동-남해 등 3개T/L 전선접속개소 전선교체","154kV 진주-개양T/L 6-9호 전선접속개소 전선교체","2018-04-01 06:00","2018-04-01 20:00","2018-04-01 06:00","2018-04-01 20:00","매일",null,null,null,201802050046,"-"]
[410,"경남","진주","하동하동화력#1 T/L","154kV 하동-남해#1T/L 전선교체공사 안전이격거리확보","154kV 하동-남해#1T/L 전선교체공사 안전이격거리확보","2018-04-23 06:00","2018-04-24 20:00","2018-04-23 06:00","2018-04-24 20:00","연속",null,null,null,201802050036,"-"]
[411,"경남","진주","광양하동#1 T/L","154kV 광양-하동#1T/L 송전선로용 피뢰기설치","154kV 광양-하동#1T/L 송전선로용 피뢰기설치 : 20기 60Set(구간 : 1∼20호)","2018-04-07 07:00","2018-04-08 20:00","취소","취소","매일",null,null,null,201802050037,"-"]
[412,"경남","진주","광양하동#2 T/L","154kV 광양-하동#1T/L 송전선로용 피뢰기설치 안전거리확보","154kV 광양-하동#1T/L 송전선로용 피뢰기설치 안전거리확보","2018-04-07 07:00","2018-04-08 20:00","취소","취소","매일",null,null,null,201802050044,"-"]
[413,"경남","진주","하동하동화력#2 T/L","154kV 하동-남해#2T/L 전선교체공사 안전이격거리확보","154kV 하동-남해#2T/L 전선교체공사 안전이격거리확보","2018-04-16 06:00","2018-04-17 20:00","2018-04-16 06:00","2018-04-17 20:00","연속",null,null,null,201802060204,"-"]
[414,"경남","진주","함양거창#1 T/L","154kV 함양-거창#1T/L 애자련보강 및 항공구 취부","154kV 함양-거창#1T/L 22~23호 애자련 1련에서 2련으로 증결 154kV 함양-거창#1T/L 21~22,26~27,29~30,40~41,42~43,62~63호 항공구 취부","2018-04-27 07:00","2018-04-28 18:30","2018-04-27 07:00","2018-04-28 18:30","매일",null,null,null,201802060206,"-"]
[415,"경남","진주","함양거창#2 T/L","154kV 함양-거창#2T/L 애자련보강 및 항공구 취부","154kV 함양-거창#2T/L 22~23호 애자련 1련에서 2련으로 증결 154kV 함양-거창#2T/L 21~22,26~27,29~30,40~41,42~43,62~63호 항공구 취부","2018-04-29 07:00","2018-04-30 18:30","2018-04-29 07:00","2018-04-30 18:30","매일",null,null,null,201802060064,"-"]
[416,"경남","진주","합천수력#2 T/L","154kV 거창-합천#1T/L 송전선로 정밀점검 관련 안전이격","154kV 거창-합천#1T/L 송전선로 정밀점검 관련 안전이격 154kV 거창-합천T/L 4호 병가","2018-04-23 09:30","2018-04-23 17:00","2018-04-23 09:30","2018-04-23 17:00","당일",null,null,null,201802060065,"-"]
[417,"경남","진주","합천수력#1 T/L","154kV 거창-합천#2T/L 송전선로 정밀점검 관련 안전이격","154kV 거창-합천#2T/L 송전선로 정밀점검 관련 안전이격 154kV 거창-합천T/L 4호 병가","2018-04-30 09:30","2018-04-30 17:00","2018-04-30 09:30","2018-04-30 17:00","당일",null,null,null,201802140010,"-"]
[418,"경남","통영","삼천포사천#1 T/L","154kV 삼천포-사천#1T/L 접속개소 전선교체공사","154kV 삼천포-사천#1T/L 20~21,22~25, 34~39, 51~53, 53~55호 구간 접속개소 전선교체공사","2018-04-07 07:00","2018-04-15 18:00","취소","취소","연속",null,null,null,201802060349,"-"]
[419,"경남","통영","신고성거제#2 T/L","154kV 신고성-거제#2T/L 정밀점검","154kV 신고성-거제#2T/L 정밀점검(S/T~198호 : 총 197기)","2018-04-14 09:00","2018-04-15 18:00","취소","취소","매일",null,null,null,201802060351,"-"]
[420,"경남","통영","신고성거제#2 T/L","154kV 신고성-거제#2T/L 정밀점검","154kV 신고성-거제#2T/L 정밀점검(S/T~198호 : 총 197기) - 병행작업 : 154kV 신고성-거제#2T/L 해월구간 SB댐퍼 교체(132EA)","2018-04-28 09:00","2018-04-29 18:00","2018-04-28 09:00","2018-04-29 18:00","매일",null,null,null,201802140175,"-"]
[421,"경남","통영","통영거제#1 T/L","154kV 통영-거제#1T/L YPP 보호계전기 오동작방지대책","1. 통영S/S 154kV 통영-거제#1T/L YPP 보호계전기 오동작방지 대책시행 2. 거제S/S 154kV 통영-거제#1T/L YPP 보호계전기 오동작방지 대책시행 - 제작사, 계통 시험파트 입회","2018-04-01 09:30","2018-04-01 18:30","2018-04-01 09:30","2018-04-01 18:30","당일",null,null,null,201802060068,"-"]
[422,"경남","함안","가야개양 T/L","154kV 사봉분기(증)T/L 및 사봉S/S SW 증설 공사","기설 154kV 개양-가야T/L No.44 ~ 기설 154kV 사봉S/S ○ 분기철탑 점퍼선 연결 - 상단 : 가야-개양 → 좌상(가야-사봉#2) - 하단 : 가야-개양 → 우하(사봉-개양#2) ○ 신설 철탑(No.1) 좌측회선 가선 ○ 보호반철거, (가야-개양T/L→가야-사봉#2T/L)설치 및 결선, 준공시험","2018-04-28 08:00","2018-05-03 18:00","2018-04-28 08:00","2018-05-03 18:00","연속",null,null,null,201802060520,"-"]
[423,"경남","함안","마산수출#1 T/L","수출S/S 마산-수출#1T/L GIS 정밀점검","수출S/S 마산-수출#1T/L GIS 정밀점검 마산S/S 647 GIS 조작시험","2018-04-14 08:30","2018-04-15 17:30","2018-04-14 08:30","2018-04-15 17:30","연속",null,null,null,201802060543,"-"]
[424,"경남","함안","마산수출#2 T/L","수출S/S 6100 정밀점검 후 시험가압 관련 마산수출#2T/L 휴전","수출S/S 6100 정밀점검 후 시험가압 관련 마산수출#2T/L 휴전","2018-04-17 13:30","2018-04-17 17:30","2018-04-17 13:30","2018-04-17 17:30","당일",null,null,null,201802070031,"-"]
[425,"경남","함안","마산수출#1 T/L","수출S/S #3M.Tr 1차 GIS 정밀점검 시험가압","수출S/S #3M.Tr 1차 GIS 정밀점검 시험가압 관련 마산-수출#1T/L 휴전","2018-04-20 14:00","2018-04-20 17:30","2018-04-20 14:00","2018-04-20 17:30","당일",null,null,null,201802060521,"-"]
[426,"경남","함안","마산수출#2 T/L","수출S/S 마산-수출#2T/L GIS 정밀점검","수출S/S 마산-수출#2T/L GIS 정밀점검 마산S/S 637 GIS 조작시험","2018-04-21 08:30","2018-04-22 17:30","2018-04-21 08:30","2018-04-22 17:30","연속",null,null,null,201802060171,"-"]
[427,"경남","함안","신마산마산#1 T/L","신마산-마산#1T/L CB 조작시험","신마산S/S 687 GCB 조작시험 마산S/S 627 GIS 조작시험","2018-04-07 09:30","2018-04-07 17:30","취소","취소","당일",null,null,null,201802060209,"-"]
[428,"경남","함안","신마산마산#2 T/L","신마산S/S 신마산-마산#2T/L 보통점검","신마산S/S 신마산-마산#2T/L 677 GCB,PT,LA 보통점검 마산S/S 617 GIS 조작시험","2018-04-08 09:30","2018-04-08 17:30","취소","취소","당일",{"$nulls":4},"-"]
[429,"전북","군산","이리백산#1T/L","154kV백산-김제 선종 교체공사 안전이격 확보","154kV백산-김제 선종 교체공사 안전이격 확보","2018-04-16 08:00","2018-04-23 08:00","2018-04-11 08:00","2018-04-19 18:00","연속",{"$nulls":4},"-"]
[430,"전북","김제","백산김제#1T/L","154kV백산-김제 선종 교체공사 ","작업내용 : No. 21~30호 전선교체","2018-04-16 08:00","2018-04-20 18:00","2018-04-28 08:00","2018-05-02 18:00","연속",{"$nulls":4},"-"]
[431,"전북","김제","백산김제#2T/L","154kV백산-김제 선종 교체공사 ","작업내용 : No. 21~30호 전선교체","2018-04-21 08:00","2018-05-04 18:00","2018-04-16 08:00","2018-04-27 18:00","연속",{"$nulls":4},"-"]
[432,"서울","중부","당인리목동#2 T/L","당인리S/S 옥내화 공사","설비존치상태 건축공사 시행으로 건축물 상판 설치고정중 안정성 확보","2018-04-17 09:00","2018-04-30 18:00","2018-04-17 09:00","2018-04-30 18:00","연속","연속",null,null,"추가","-"]
[433,"서울","중부","당인리여의 T/L","당인리S/S 옥내화 공사","설비존치상태 건축공사 시행으로 건축물 상판 설치고정중 안정성 확보","2018-04-17 09:00","2018-04-30 18:00","2018-04-17 09:00","2018-04-30 18:00","연속","연속",null,null,"추가","-"]
[434,"서울","중부","의사당당인리 T/L","당인리S/S 옥내화 공사","설비존치상태 건축공사 시행으로 건축물 상판 설치고정중 안정성 확보","2018-04-17 09:00","2018-04-30 18:00","2018-04-17 09:00","2018-04-30 18:00","연속","연속",null,null,"추가","-"]
[435,"서울","중부","당인리목동#1 T/L","당인리S/S 옥내화 공사","설비존치상태 건축공사 시행으로 건축물 상판 설치고정중 안정성 확보","2018-04-17 09:00","2018-04-30 18:00","2018-04-17 09:00","2018-04-30 18:00","연속","연속",null,null,"추가","-"]

{"sheet":"한수원","index":3,"n_rows":9,"n_cols":20,"rows_kept":9,"cut":false,"hidden":false,"merged":[[4,19,5,19],[4,13,5,13],[4,14,5,14],[4,15,5,15],[4,16,5,16],[4,17,5,17],[4,18,5,18],[0,0,0,6],[4,12,5,12],[4,0,5,0],[4,1,5,1],[4,2,5,2],[4,3,5,3],[4,4,5,4],[4,5,5,5],[4,6,4,7],[4,8,4,9],[4,10,5,10],[4,11,5,11]]}
["2018년도 04월 휴전계획표(한국수력원자력)"]
[]
[]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"한빛본부","2발전소","#4 기동용변압기\n    (04XN)","한빛4호기 14차 O/H 중 GIB/GIS 개선\n* 조작차단기 : CB 7800, 7871","○ 기동변압기측(04XN) GIB/CV케이블 및\n    GIS 교체","2018-04-16T10:00:00","2018-06-09T18:00:00","2018-04-16T10:00:00","2018-06-09T18:00:00","연속","Y"]
[2,"월성본부","1발전소","#2 기동용변압기","월성2호기 17차 O/H 중 기동용\n변압기 점검\n* 조작차단기 : CB 7400, 7472","○ 기동용변압기 일반점검\n○ 기동용변압기 보호계전기 정기시험\n   (차단기 연동시험 포함)\n○ 갑종보호계전기반(SST, OF Cable)교체","2018-04-22T09:00:00","2018-05-12T18:00:00","2018-04-22T09:00:00","2018-05-12T18:00:00","연속","Y"]
[3,"월성본부","3발전소","신#1 주변압기","신월성1호기 4차 O/H 중 주변압기 점검\n* 조작차단기 : CB 7400, 7472","○ MTR/UAT/EXTR 일반점검 수행","2018-04-18T09:00:00","2018-05-07T18:00:00","2018-04-18T09:00:00","2018-05-07T18:00:00","연속","Y"]

{"sheet":"중부","index":4,"n_rows":15,"n_cols":20,"rows_kept":15,"cut":false,"hidden":false,"merged":[[10,19,11,19],[10,13,11,13],[10,14,11,14],[10,15,11,15],[10,16,11,16],[10,17,11,17],[10,18,11,18],[2,18,3,18],[10,5,11,5],[10,6,10,7],[10,8,10,9],[10,10,11,10],[10,11,11,11],[2,19,3,19],[10,0,11,0],[10,1,11,1],[10,2,11,2],[10,3,11,3],[10,4,11,4],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,14,3,14],[10,12,11,12],[2,15,3,15],[2,16,3,16],[2,17,3,17],[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7]]}
["2018년도 4월 휴전계획(한국중부발전)"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,null,"보령복합","GT#3,4 주변압기\n(CB 7300, 7372)","계획예방정비관련\n전기설비 점검","주변압기 점검 및 GCB 점검","2018-04-18T09:00:00","2018-06-29T18:00:00","2018-04-18T09:00:00","2018-06-29T18:00:00","연속"]
[2,null,"신보령","신보령-보령복합(연락)T/L\n(CB 7100, 7171, 7400. 7471)","GIS 보통점검","GIS 보통점검 실시","2018-04-02T09:00:00","2018-04-06T18:00:00","2018-04-02T09:00:00","2018-04-06T18:00:00","연속"]
[3,null,"신보령","#1 주변압기\n(7100, 7172)","변압기 점검","변압기 점검","2018-04-02T09:00:00","2018-04-07T18:00:00","2018-04-02T09:00:00","2018-04-07T18:00:00","연속"]
[]
[]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,null,"보령복합","GT #5 주변압기\n(CB 6133)","정기검사 수검","발전기 및 변압기 특성자료 취득 및 정기검사 수검","2018-04-17T09:00:00","2018-04-26T18:00:00","2018-04-17T09:00:00","2018-04-26T18:00:00","연속"]
[2,null,"보령복합","GT #6 주변압기\n(CB 6233)","정기검사 수검","발전기 및 변압기 특성자료 취득 및 정기검사 수검","2018-04-17T09:00:00","2018-04-26T18:00:00","2018-04-17T09:00:00","2018-04-26T18:00:00","연속"]
[3,null,"보령복합","ST #3 주변압기\n(CB 6333)","정기검사 수검","발전기 및 변압기 특성자료 취득 및 정기검사 수검","2018-04-17T09:00:00","2018-04-26T18:00:00","2018-04-17T09:00:00","2018-04-26T18:00:00","연속"]