{"text_format":"2","workbook":"xlsx","n_sheets":5,"sheets":["765송부","345송부","154송부","한수원","중부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":10,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":16,"n_cols":16,"rows_kept":16,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"\"2018년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2018년도 5월 휴전계획서"}]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"강원","태백","신태백신가평#1 T/L","765kV 신태백T/L 항공장애표시구 교체공사","No.170~173,No.199~202 항공장애표시구 교체","2018-05-21 08:00","2018-05-21 18:00","2018-05-21 08:00","2018-05-21 18:00","당일",null,null,null,201803230038]
[2,"강원","태백","신태백신가평#2 T/L","765kV 신태백T/L 항공장애표시구 교체공사","No.170~173,No.199~202 항공장애표시구 교체","2018-05-22 08:00","2018-05-22 18:00","2018-05-22 08:00","2018-05-22 18:00","당일",null,null,null,201803060100]
[3,"강원","태백","신태백S/S #4 M.Tr A-1","765kV 주변압기 정밀점검","신태백S/S 765kV #4M.Tr 정밀점검","2018-05-28 09:00","2018-07-31 18:00","2018-05-28 09:00","2018-07-31 18:00","연속",null,null,null,201803090365]
[4,"대전충남","서산","당진T/P Tie Tr","18년 서산PO 변전협력회사 총액공사","765kV Tie-Tr 유압펌프 교체 및 FAN 회로 오결선 정정 작업 기타 부대 작업 등등","2018-05-16 09:00","2018-05-18 18:00","2018-05-16 09:00","2018-05-18 18:00","당일",null,null,null,201803150027]
[5,"대전충남","서산","당진T/P 신서산-당진TP#1T/L-4호기 1차 CB","18년 서산PO 345/765kV GIS 점검공사","18년 서산PO 345/765kV GIS 점검공사","2018-05-10 09:00","2018-05-11 18:00","2018-05-10 09:00","2018-05-11 18:00","연속",null,null,null,201803190040]
[6,"대전충남","서산","당진T/P 4호기 1차 CB","18년 서산PO 345/765kV GIS 점검공사","18년 서산PO 345/765kV GIS 점검공사","2018-05-08 09:00","2018-05-09 18:00","2018-05-08 09:00","2018-05-09 18:00","연속",null,null,null,201803190039]
[7,"대전충남","서산","당진T/P 신서산-당진TP#1T/L-3호기 1차 CB","18년 서산PO 345/765kV GIS 점검공사","18년 서산PO 345/765kV GIS 점검공사","2018-05-03 09:00","2018-05-04 18:00","2018-05-03 09:00","2018-05-04 18:00","연속",null,null,null,201803190038]
[8,"대전충남","서산","당진T/P 5호기 1차 CB","18년 서산PO 345/765kV GIS 점검공사","당진화력 765kV 8572 GIS 보통점검","2018-05-01 09:00","2018-05-02 18:00","2018-05-01 09:00","2018-05-02 18:00","연속",null,null,null,201803190051]
[9,"경남","함안","북경남S/S #4 M.Tr A-1","북경남S/S 테크프로제 23kV 4488 GIS 유사고장조치","1.북경남S/S 테크프로제 23kV 4488 GIS 유사고장조치 2.4288 조치를 위한 KP분리작업","2018-05-14 09:30","2018-05-16 17:30","2018-05-14 09:30","2018-05-16 17:30","당일",null,null,null,201803060189]
[10,"경남","함안","북경남S/S #4 M.Tr A-1","북경남S/S 4288 GIS 유사고장조치 후 KP재접속","북경남S/S 4288 GIS 유사고장조치 후 KP재접속","2018-05-21 09:30","2018-05-21 17:30","2018-05-21 09:30","2018-05-21 17:30","당일",null,null,null,201803060191]
[11,"경남","함안","북경남S/S #3 M.Tr A-1","북경남S/S 테크프로제 23kV 4388 GIS 유사고장조치","북경남S/S 테크프로제 23kV 4388 GIS 유사고장조치","2018-05-09 09:30","2018-05-11 17:30","2018-05-09 09:30","2018-05-11 17:30","당일",null,null,null,201803060188]
[12,"경남","함안","북경남S/S #5 M.Tr A-1","북경남S/S 테크프로제 23kV 4588, 4288 GIS 유사고장조치","북경남S/S 테크프로제 23kV 4588, 4288 GIS 유사고장조치","2018-05-17 09:30","2018-05-20 17:30","2018-05-17 09:30","2018-05-20 17:30","당일",null,null,null,201803060190]

{"sheet":"345송부","index":1,"n_rows":262,"n_cols":16,"rows_kept":262,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"\"2018년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2018년도 5월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","강남","신양재S/S 345kV #3 Sh.R","신양재S/S 362kV GIS 모선DS 내부점검","345kV #3Sh.R GIS 모선DS(7451) 내부점검","2018-05-30 10:00","2018-05-31 18:00","2018-05-30 10:00","2018-06-01 18:00","연속",null,null,null,201803210012,"-"]
[2,"남서울","강남","신양재S/S 345kV #1 BUS","신양재S/S 362kV GIS 모선DS 내부점검","345kV #3Sh.R GIS 모선DS(7451) 내부점검","2018-05-30 10:00","2018-05-31 18:00","2018-05-30 10:00","2018-06-01 18:00","연속",null,null,null,201803210008,"-"]
[3,"남서울","동서울","동서울S/S 동서울-미금#2T/L CB (7272)","7262DS 구동모터 교체","7262DS 구동모터 교체","2018-05-08 09:00","2018-05-08 18:00","2018-05-08 09:00","2018-05-08 18:00","당일",null,null,null,201803190314,"-"]
[4,"남서울","동서울","신용인동서울#1 T/L","345kV신용인-동서울#1T/L 전선교체공사","345kV신용인-동서울#1T/L 전선접속개소 전선교체공사 - 82호 ~ 83호 중하단 내외측 - 83호 ~ 87호 상중하단 내외측 - 93호 ~ 100호 상중하단 내외측","2018-05-25 07:30","2018-06-08 18:00","2018-05-25 07:30","2018-06-08 18:00","연속",null,null,null,201802060538,"-"]
[5,"남서울","영등포","신광명S/S #1 M.Tr A","영서S/S 154kV 이하 옥외철구 GIS화 공사","가공-EBA 접속, 보호반 시험","2018-05-21 09:00","2018-06-01 18:00","2018-05-21 09:00","2018-06-01 18:00","연속",null,null,null,201803190200,"-"]
[6,"인천","김포","가정 345kV #3 Sh.R CB","가정개폐소 345kV #3Sh.R 하자점검","가정개폐소 345kV #3Sh.R 하자점검","2018-05-16 10:00","2018-05-16 18:00","2018-05-16 10:00","2018-05-16 18:00","당일",null,null,null,201803150131,"-"]
[7,"인천","김포","가정개폐소 345KV 70-71 SEC CB","가정개폐소 345kV 70-71 SEC CB 조작시험","가정개폐소 345kV 70-71 SEC CB 조작시험","2018-05-14 10:00","2018-05-14 13:00","2018-05-14 10:00","2018-05-14 13:00","당일",null,null,null,201803150134,"-"]
[8,"인천","김포","가정개폐소 345KV 75-76 SEC CB","가정개폐소 345kV 75-76 SEC CB 조작시험","가정개폐소 345kV 75-76 SEC CB 조작시험","2018-05-14 13:00","2018-05-14 16:00","2018-05-14 13:00","2018-05-14 16:00","당일",null,null,null,201803150135,"-"]
[9,"인천","김포","가정 345kV #2 Sh.R CB","가정개폐소 345kV #2Sh.R 초기점검","가정개폐소 345kV #2Sh.R 초기점검","2018-05-15 10:00","2018-05-15 18:00","2018-05-15 10:00","2018-05-15 18:00","당일",null,null,null,201803150130,"-"]
[10,"인천","시흥","신시흥#1S/S #3 M.Tr A","신시흥#1S/S #3 M.Tr 2차 GIS 정밀점검,1차동작시험","신시흥#1S/S #3 M.Tr 2차 GIS 정밀점검,1차동작시험","2018-05-08 08:00","2018-05-09 18:00","2018-05-08 08:00","2018-05-09 18:00","연속",null,null,null,201803150403,"-"]
[11,"인천","시흥","신시흥#1S/S #2 M.Tr","신시흥S/S #2M.Tr 보통점검,1차동작 2차보통점검","신시흥S/S #2M.Tr 보통점검,1차동작 2차보통점검","2018-05-21 10:00","2018-05-24 18:00","2018-05-21 10:00","2018-05-24 18:00","연속",null,null,null,201803150412,"-"]
[12,"인천","시흥","신시흥#1S/S #1 M.Tr A","신시흥S/S #1M.Tr 보통점검,1차동작 2차보통점검","신시흥S/S #1M.Tr 보통점검,1차동작 2차보통점검","2018-05-17 10:00","2018-05-19 18:00","2018-05-17 10:00","2018-05-19 18:00","연속",null,null,null,201803150413,"-"]
[13,"인천","시흥","신시흥#2S/S #4 M.Tr A","신시흥#2S/S #4 M.Tr 2차 GIS 정밀점검,1차동작시험","신시흥#2S/S #4 M.Tr 2차 GIS 정밀점검,1차동작시험","2018-05-14 09:00","2018-05-16 18:00","2018-05-14 09:00","2018-05-16 18:00","연속",null,null,null,201803150407,"-"]
[14,"인천","시흥","서서울#2신시흥 #2T/L","345kV 신시흥영흥#3T/L 항공장애표시구 설치공사(병가선로)","345kV 신시흥영흥#3T/L 항공장애표시구 설치공사(병가선로) -영흥#3(상단),서서울2신시흥#2(하단)","2018-05-31 08:00","2018-05-31 12:00","2018-05-30 08:00","2018-05-30 12:00","당일",null,null,null,201803130147,"-"]
[15,"인천","시흥","영흥1TP-영흥2TP #1T/L","345kV 영흥연락#1T/L 항공장애표시구 설치공사","345kV 영흥연락#1T/L 항공장애표시구 설치공사","2018-05-01 12:00","2018-05-02 18:00","취소","취소","연속",null,null,null,201803130050,"-"]
[16,"인천","시흥","영흥#2T/P 영흥TP연락#1T/L CB (7671)","영흥#2T/P 영흥TP연락#1T/L CB(7671) 보통점검","영흥#2T/P 영흥TP연락#1T/L CB(7671) 보통점검","2018-05-02 10:00","2018-05-02 18:00","2018-05-02 10:00","2018-05-02 18:00","당일",null,null,null,201803150355,"-"]
[17,"인천","시흥","신시흥영흥TP#1 T/L","345kV 신시흥영흥#1T/L 피뢰기 및 항공장애표시구 설치공사","345kV 신시흥영흥#1T/L 피뢰기 및 항공장애표시구 설치공사","2018-05-03 08:00","2018-05-08 18:00","취소","취소","연속",null,null,null,201803130037,"-"]
[18,"인천","시흥","영흥#2T/P 영흥TP연락#1T/L - #5G/T 1차 CB (7600)","영흥#2T/P 영흥TP연락#1T/L-#5G/T 1차 CB(7600) 보통","영흥#2T/P 영흥TP연락#1T/L - #5G/T 1차 CB(7600) 보통점검","2018-05-03 10:00","2018-05-03 18:00","2018-05-03 10:00","2018-05-03 18:00","당일",null,null,null,201803150356,"-"]
[19,"인천","시흥","영흥#2T/P #5G/T 1차 CB (7672)","영흥#2T/P #5G/T 1차 CB(7672) 보통점검","영흥#2T/P #5G/T 1차 CB(7672) 보통점검","2018-05-04 10:00","2018-05-04 18:00","2018-05-04 10:00","2018-05-04 18:00","당일",null,null,null,201803150357,"-"]
[20,"인천","시흥","영흥1TP-영흥2TP #2T/L","345kV 영흥연락#2T/L 피뢰기 및 항공장애표시구 설치공사","345kV 영흥연락#2T/L 피뢰기 및 항공장애표시구 설치공사","2018-05-07 08:00","2018-05-08 18:00","취소","취소","연속",null,null,null,201803130051,"-"]
[21,"인천","시흥","영흥#2T/P 신시흥영흥TP#3T/L CB (7771)","영흥#2T/P 신시흥영흥TP#3T/L CB(7771) 보통점검","영흥#2T/P 신시흥영흥TP#3T/L CB(7771) 보통점검","2018-05-08 10:00","2018-05-08 18:00","2018-05-08 10:00","2018-05-08 18:00","당일",null,null,null,201803150358,"-"]
[22,"인천","시흥","영흥#2T/P 신시흥영흥TP#3T/L-#6G/T 1차 CB (7700)","영흥#2T/P 신시흥영흥TP#3T/L-#6G/T 1차 CB(7700)보통","영흥#2T/P 신시흥영흥TP#3T/L-#6G/T 1차 CB(7700)보통점검","2018-05-09 10:00","2018-05-09 18:00","2018-05-09 10:00","2018-05-09 18:00","당일",null,null,null,201803150359,"-"]
[23,"인천","시흥","영흥#2T/P #6G/T 1차 CB (7772)","영흥#2T/P #6G/T 1차 CB(7772)보통점검","영흥#2T/P #6G/T 1차 CB(7772)보통점검","2018-05-10 10:00","2018-05-10 18:00","2018-05-10 10:00","2018-05-10 18:00","당일",null,null,null,201803150361,"-"]
[24,"인천","시흥","영흥#2T/P 영흥TP연락#2T/L CB (7971)","영흥#2T/P 영흥TP연락#2T/L CB(7971)보통점검","영흥#2T/P 영흥TP연락#2T/L CB(7971)보통점검","2018-05-11 10:00","2018-05-11 18:00","2018-05-11 10:00","2018-05-11 18:00","당일",null,null,null,201803150362,"-"]
[25,"인천","시흥","영흥#2T/P 영흥TP연락#2T/L - TIE CB (7900)","영흥#2T/P 영흥TP연락#2T/L - TIE CB(7900)보통점검","영흥#2T/P 영흥TP연락#2T/L - TIE CB(7900)보통점검","2018-05-28 10:00","2018-05-28 18:00","2018-05-28 10:00","2018-05-28 18:00","당일",null,null,null,201803150363,"-"]
[26,"인천","시흥","신시흥영흥TP#3 T/L","345kV 신시흥영흥#3T/L 피뢰기 및 항공장애표시구 설치공사","345kV 신시흥영흥#3T/L 피뢰기 및 항공장애표시구 설치공사","2018-05-31 08:00","2018-06-05 18:00","2018-05-30 08:00","2018-06-04 18:00","연속",null,null,null,201803130053,"-"]
[27,"인천","시흥","영흥1TP-영흥2TP #1T/L","345kV 영흥연락#1T/L 항공장애표시구 설치공사","345kV 영흥연락#1T/L 항공장애표시구 설치공사","2018-05-31 12:00","2018-06-01 18:00","2018-05-30 12:00","2018-05-31 18:00","연속",null,null,null,201803130054,"-"]
[28,"인천","시흥","신시흥영흥TP#3 T/L","345kV 신시흥영흥#3T/L 피뢰기 및 항공장애표시구 설치공사","345kV 신시흥영흥#3T/L 피뢰기 및 항공장애표시구 설치공사","2018-05-02 08:00","2018-05-06 18:00","취소","취소","연속",null,null,null,201803130038,"-"]
[29,"인천","시흥","영흥T/P #4 M.Tr(G.T) 1차 CB (7572)","영흥T/P #4 M.Tr(G.T) 1차 CB(7572)구조개선","영흥T/P #4 M.Tr(G.T) 1차 CB(7572) 구조개선공사","2018-05-28 09:00","2018-05-30 18:00","취소","취소","연속",null,null,null,201803150353,"-"]
[30,"인천","시흥","영흥T/P 신시흥영흥TP#4T/L-#4G/T 1차 CB (7500)","영흥T/P 신시흥영흥TP#4T/L-#4G/T 1차 CB(7500)구조개선","영흥T/P 신시흥영흥TP#4T/L-#4G/T 1차 CB(7500)구조개선","2018-05-31 09:00","2018-06-02 18:00","취소","취소","연속",null,null,null,201803200280,"-"]
[31,"인천","시흥","영흥T/P #3 M.Tr(G.T) 1차 CB (7472)","영흥T/P #3 M.Tr(G.T) 1차 CB(7472)구조개선","영흥T/P #3 M.Tr(G.T) 1차 CB(7472) 구조개선공사","2018-05-14 09:00","2018-05-16 18:00","취소","취소","연속",null,null,null,201803150352,"-"]
[32,"인천","시흥","영흥T/P #2 TIE Tr 1차 CB (7372)","영흥T/P #2 TIE Tr 1차 CB(7372) 구조개선","영흥T/P #2 TIE Tr 1차 CB(7372) 구조개선공사","2018-05-23 09:00","2018-05-25 18:00","취소","취소","연속",null,null,null,201803150350,"-"]
[33,"인천","인천","서인천C/C 345kV #70 BUS","345kV 서인천C/C 용량부족 GIS 대체공사","- 345kV 서인천C/C 용량부족 GIS 대체(#70BUS 모선개조)","2018-05-26 10:00","2018-06-09 17:00","2018-05-26 10:00","2018-06-09 17:00","연속",null,null,null,201803150326,"-"]
[34,"인천","인천","서인천C/C 345kV #75 BUS","345kV 서인천C/C 모선용CLR 설치 및 용량부족 GIS 대체공사","- 345kV 서인천C/C 모선측 CLR용 GIS 설치(#75BUS) - 345kV 서인천C/C 용량부족 GIS 대체(#75BUS 모선개조)","2018-05-11 10:00","2018-05-25 17:00","2018-05-11 10:00","2018-05-25 17:00","연속",null,null,null,201803090046,"-"]
[35,"인천","인천","신가좌가정#2 T/L","345kV 신가좌-가정#2T/L 항공장애표시구 설치공사","No.7~8 등 5경간 항공구 설치","2018-05-17 08:00","2018-05-17 17:00","2018-05-17 08:00","2018-05-17 17:00","당일",null,null,null,201803140108,"-"]
[36,"인천","인천","신가좌가정#1 T/L","345kV 신가좌-가정#1T/L 항공장애표시구 설치공사","No.7~8 등 5경간 항공구 설치","2018-05-14 08:00","2018-05-14 17:00","2018-05-14 08:00","2018-05-14 17:00","당일",null,null,null,201803140107,"-"]
[37,"인천","인천","신가좌S/S #2 M.Tr A","신가좌S/S #2M.Tr 보통점검 및 GIS 조작시험","신가좌S/S #2M.Tr 및 LA 보통점검 신가좌S/S #2-1,2-2Sh.R 하자점검 신가좌S/S 7372, 6244 GIS 조작시험 신가좌S/S 4279,4279-1,4279-2 VCB 조작시험","2018-05-02 09:00","2018-05-04 18:00","2018-05-02 09:00","2018-05-04 18:00","연속",null,null,null,201803120636,"-"]
[38,"인천","인천","신가좌신시흥#2 T/L","345kV 신가좌-신시흥#2T/L 항공장애표시구 설치공사","No.5~6 등 11경간 항공구 설치","2018-05-26 08:00","2018-05-27 17:00","2018-05-26 08:00","2018-05-27 17:00","매일",null,null,null,201803140115,"-"]
[39,"인천","인천","신가좌신시흥#1 T/L","345kV 신가좌-신시흥#1T/L 항공장애표시구 설치공사","No.5~6 등 11경간 항공구 설치","2018-05-19 08:00","2018-05-20 17:00","2018-05-19 08:00","2018-05-20 17:00","매일",null,null,null,201803140114,"-"]
[40,"인천","인천","신경서S/S 신경서포스코SY#2T/L CB (7571)","신경서S/S 7571 GIS 조작시험","신경서S/S 7571 GIS 조작시험","2018-05-17 14:00","2018-05-17 18:00","2018-05-17 14:00","2018-05-17 18:00","당일",null,null,null,201803120674,"-"]
[41,"인천","인천","신경서S/S 서인천서인천CCT/L CB (7472)","신경서S/S 7472 GIS 하자점검","신경서S/S 7472 GIS 하자점검","2018-05-17 09:00","2018-05-17 18:00","2018-05-17 09:00","2018-05-17 18:00","당일",null,null,null,201803120672,"-"]
[42,"인천","인천","신경서S/S 신경서인천CC#1T/L CB (7271)","신경서S/S 7271 GIS 조작시험","신경서S/S 7271 GIS 조작시험","2018-05-17 09:00","2018-05-17 14:00","2018-05-17 09:00","2018-05-17 14:00","당일",null,null,null,201803120673,"-"]
[43,"인천","인천","신경서S/S 신경서서인천CCT/L-TIE CB (7400)","신경서S/S 7400 GIS 하자점검","신경서S/S 7400 GIS 하자점검","2018-05-16 09:00","2018-05-16 18:00","2018-05-16 09:00","2018-05-16 18:00","당일",null,null,null,201803120671,"-"]
[44,"인천","인천","신경서S/S 서인천인천CC#2T/L CB (7372)","신경서S/S 7372 GIS 하자점검","신경서S/S 7372 GIS 하자점검","2018-05-15 09:00","2018-05-15 18:00","2018-05-15 09:00","2018-05-15 18:00","당일",null,null,null,201803120670,"-"]
[45,"인천","인천","신인천C/C 71-72 SEC GIS","신인천복합S/Y 71-72-0 GIS 조작시험","신인천복합S/Y 71-72-0 GIS 조작시험","2018-05-29 09:00","2018-05-28 13:00","2018-05-29 09:00","2018-05-28 13:00","당일",null,null,null,201803120683,"-"]
[46,"인천","인천","신인천C/C 76-77 SEC GIS","신인천복합S/Y 76-77-0 GIS 조작시험","신인천복합S/Y 76-77-0 GIS 조작시험","2018-05-29 16:00","2018-05-28 18:00","2018-05-29 16:00","2018-05-28 18:00","당일",null,null,null,201803120685,"-"]
[47,"인천","인천","신인천C/C 75-76 SEC GIS","신인천복합S/Y 75-76-0 GIS 조작시험","신인천복합S/Y 75-76-0 GIS 조작시험","2018-05-29 13:00","2018-05-28 16:00","2018-05-29 13:00","2018-05-28 16:00","당일",null,null,null,201803120684,"-"]
[48,"인천","인천","인천CC S/Y #1Tie-Tr A","인천복합S/Y #1Tie-Tr GIS 하자점검 및 조작시험","인천복합S/Y 7171, 7100 GIS 하자점검 인천복합S/Y 6244 GIS 조작시험","2018-05-30 09:00","2018-05-31 18:00","2018-05-30 09:00","2018-05-31 18:00","연속",null,null,null,201803120686,"-"]
[49,"인천","인천","포스코S/Y 신경서포스코SY#2T/L-TIE CB (7400)","포스코S/Y 7400 GIS 제작사 하자처리 공사","포스코S/Y 7400 GIS 제작사 하자처리 공사","2018-05-07 09:00","2018-05-12 18:00","2018-05-07 09:00","2018-05-12 18:00","연속",null,null,null,201803120035,"-"]
[50,"인천","직할","신부평S/S #3 M.Tr","신부평S/S #3M.Tr 345kV 주변압기 보통점검","신부평S/S #3M.Tr 345kV 주변압기 보통점검","2018-05-17 09:30","2018-05-18 18:00","2018-05-17 09:30","2018-05-18 18:00","연속",null,null,null,201803150098,"-"]
[51,"인천","직할","신부평S/S #2 M.Tr A","신부평S/S #2M.Tr 345kV 주변압기 보통점검","신부평S/S #2M.Tr 345kV 주변압기 보통점검","2018-05-15 09:30","2018-05-16 18:00","2018-05-15 09:30","2018-05-16 18:00","연속",null,null,null,201803150097,"-"]
[52,"인천","직할","서인천CC신부평#3 T/L","신부평S/S 서인천신부평#3T/L 345kV 보호반 대체","신부평S/S 서인천신부평#3T/L 345kV 보호반 대체","2018-05-28 09:30","2018-06-01 18:00","2018-05-28 09:30","2018-06-01 18:00","연속",null,null,null,201803150107,"-"]
[53,"인천","직할","신부평S/S 345kV #1 Sh.R","신부평S/S 345kV #1Sh.R 보통점검","신부평S/S 345kV #1Sh.R 보통점검","2018-05-23 09:30","2018-05-24 18:00","2018-05-23 09:30","2018-05-24 18:00","연속",null,null,null,201803150100,"-"]
[54,"인천","직할","서인천CC신부평#4 T/L","345kV 서인천CC-신부평#4T/L 절연유 채취","OF케이블 절연유채취","2018-05-24 09:00","2018-05-25 18:00","2018-05-24 09:00","2018-05-25 18:00","연속",null,null,null,201803150175,"-"]
[55,"경기북부","고양","신파주S/S #1 M.Tr A","18년도 고양전력지사 변전협력회사총액공사(신파주#1M.Tr)","신파주변전소 #1M.Tr 1,2,3차 조작시험 및 3차 GPT 점검","2018-05-15 10:00","2018-05-15 18:00","2018-05-15 10:00","2018-05-15 18:00","연속",null,null,null,201803080494,"-"]
[56,"경기북부","고양","신파주S/S #2 M.Tr A","18년도 고양전력지사 변전협력회사총액공사(신파주#2M.Tr)","신파주변전소 #2M.Tr 1,2,3차 조작시험 및 3차 GPT 점검","2018-05-16 10:00","2018-05-16 18:00","2018-05-16 10:00","2018-05-16 18:00","연속",null,null,null,201803080495,"-"]
[57,"경기북부","구리","미금S/S 345kV #4 Sh.R","미금S/S 345kV #4Sh.R 교체공사","미금S/S 345kV #4Sh.R 교체","2018-05-28 08:00","2018-06-09 18:00","2018-05-28 08:00","2018-06-09 18:00","연속",null,null,null,201801290119,"-"]
[58,"경기북부","구리","미금S/S 345kV #2 Sh.R","18-19변전협력회사 총액공사(Sh.R, GIS)","○72729 GIS 초기점검(오전), 7079MAIN GIS 보통점검(오후) ○#2Sh.R 초기점검(종일)","2018-05-15 09:00","2018-05-15 18:00","2018-05-15 09:00","2018-05-15 18:00","당일",null,null,null,201803150034,"-"]
[59,"경기북부","구리","미금S/S 345kV #1 Sh.R","18-19변전협력회사 총액공사(7079 MAIN GIS)","○7079 MAIN GIS 보통점검","2018-05-15 14:00","2018-05-15 18:00","2018-05-15 14:00","2018-05-15 18:00","당일",null,null,null,201803150037,"-"]
[60,"경기북부","구리","미금S/S 345kV #5 Sh.R","18-19변전협력회사 총액공사(7079 MAIN GIS)","○7079 MAIN GIS 보통점검","2018-05-15 14:00","2018-05-15 18:00","2018-05-15 14:00","2018-05-15 18:00","당일",null,null,null,201803150038,"-"]
[61,"경기북부","구리","신가평S/S 345kV #2 Sh.R","신가평S/S 345kV #2 Sh.R 7309-2ES 가스누기 보수","신가평S/S 345kV #2 Sh.R 7309-2ES 가스누기 보수","2018-05-21 09:00","2018-05-22 18:00","2018-05-21 09:00","2018-05-22 18:00","연속",null,null,null,201803090011,"-"]
[62,"경기북부","구리","신포천동두천CC#1 T/L","신포천S/S 345GIS #1BUS 가스누기 예방공사","○ 벨로우즈, GIB 플렌지부 등 오링, 액체패킹 재시공 ○ 크레인 작업시 위험구간 휴전","2018-05-16 09:00","2018-05-21 18:00","2018-05-16 09:00","2018-05-21 18:00","연속",null,null,null,201803150006,"-"]
[63,"경기북부","구리","신포천포천LNGCC#1 T/L","신포천S/S 345GIS #1BUS 가스누기 예방공사","○ 벨로우즈, GIB 플렌지부 등 오링, 액체패킹 재시공 ○ 크레인 작업시 위험구간 휴전","2018-05-10 09:00","2018-05-12 18:00","2018-05-10 09:00","2018-05-12 18:00","연속",null,null,null,201803150002,"-"]
[64,"경기북부","구리","신포천포천CC#2 T/L","신포천S/S 345GIS #1BUS 가스누기 예방공사","○ 벨로우즈, GIB 플렌지부 등 오링, 액체패킹 재시공 ○ 크레인 작업시 위험구간 휴전","2018-05-16 09:00","2018-05-18 18:00","2018-05-16 09:00","2018-05-18 18:00","연속",null,null,null,201803150005,"○"]
[65,"경기북부","구리","신포천포천CC#1 T/L","신포천S/S 345GIS #1BUS 가스누기 예방공사","○ 벨로우즈, GIB 플렌지부 등 오링, 액체패킹 재시공 ○ 크레인 작업시 위험구간 휴전","2018-05-13 09:00","2018-05-15 18:00","2018-05-13 09:00","2018-05-15 18:00","연속",null,null,null,201803150004,"○"]
[66,"경기북부","구리","신포천포천LNGCC#2 T/L","신포천S/S 345GIS #1BUS 가스누기 예방공사","○ 벨로우즈, GIB 플렌지부 등 오링, 액체패킹 재시공 ○ 크레인 작업시 위험구간 휴전","2018-05-10 09:00","2018-05-15 18:00","2018-05-10 09:00","2018-05-15 18:00","연속",null,null,null,201803150003,"-"]
[67,"경기북부","구리","신포천S/S 345kV #1 BUS","신포천S/S 345GIS #1BUS 가스누기 예방공사","○ 벨로우즈, GIB 플렌지부 등 오링, 액체패킹 재시공","2018-05-08 09:00","2018-05-27 18:00","2018-05-08 09:00","2018-05-27 18:00","연속",null,null,null,201803150001,"-"]
[68,"경기북부","구리","신포천동두천CC#2 T/L","신포천S/S 345GIS #1BUS 가스누기 예방공사","○ 벨로우즈, GIB 플렌지부 등 오링, 액체패킹 재시공 ○ 크레인 작업시 위험구간 휴전","2018-05-19 09:00","2018-05-21 18:00","2018-05-19 09:00","2018-05-21 18:00","연속",null,null,null,201803150007,"-"]
[69,"경기북부","직할","신의정부S/S 345kV #3 Sh.R CB","362kV GIS 개폐타임측정","#3Sh.R GIS(7879) 개폐타임 측정","2018-05-09 10:00","2018-05-09 18:00","2018-05-09 10:00","2018-05-09 18:00","당일",null,null,null,201803210252,"-"]
[70,"경기북부","직할","신의정부S/S #1 Sh.R CB","362kV GIS 개폐타임측정","#1 Sh.R GIS(7479) 개폐타임 측정","2018-05-11 10:00","2018-05-11 18:00","2018-05-11 10:00","2018-05-11 18:00","당일",null,null,null,201803210260,"-"]
[71,"경기북부","직할","신의정부S/S 345kV #2 Sh.R CB","362kV GIS 개폐타임측정","#2 Sh.R GIS(7772) 개폐타임 측정","2018-05-10 10:00","2018-05-10 18:00","2018-05-10 10:00","2018-05-10 18:00","당일",null,null,null,201803210257,"-"]
[72,"경기북부","직할","양주S/S #3 M.Tr A","양주변전소 옥외철구 GIS화 공사","주변압기 3차측 정비","2018-05-14 09:00","2018-05-18 18:00","2018-05-14 09:00","2018-05-18 18:00","연속",null,null,null,201803160181,"-"]
[73,"경기북부","직할","양주S/S 345kV #4 Sh.R(17년 설치) CB","362kV GIS 개폐타임측정","#4 Sh.R GIS 개폐타임 측정","2018-05-14 10:00","2018-05-14 18:00","2018-05-14 10:00","2018-05-14 18:00","당일",null,null,null,201803210262,"-"]
[74,"경기북부","직할","양주중부#1 T/L","양주S/S 362kV #6Sh.R용 GIS 공장반입 개조공사","#6Sh.R용 GIS 공장반입 개조작업 - GIS 설치작업","2018-05-22 09:00","2018-05-22 18:00","2018-05-22 09:00","2018-05-22 18:00","당일",null,null,null,201803130113,"-"]
[75,"경기북부","직할","양주중부#2 T/L","양주S/S 362kV #6Sh.R용 GIS 공장반입 개조공사","#6Sh.R용 GIS 공장반입 개조작업 - GIS 설치작업","2018-05-21 09:00","2018-05-21 18:00","2018-05-21 09:00","2018-05-21 18:00","당일",null,null,null,201803130112,"-"]
[76,"경기북부","직할","양주S/S #4 M.Tr A","양주변전소 옥외철구 GIS화 공사","주변압기 3차측 정비","2018-05-21 09:00","2018-05-25 18:00","2018-05-21 09:00","2018-05-25 18:00","연속",null,null,null,201803160183,"-"]
[77,"경기","군포","서서울S/S 345kV #1 BUS GIS","서서울2S/S 154kV Sh.C 증설사업 관련 인출정비","서서울S/S #1M.Tr 1차측 Bay 변경 시행(73Bay→74Bay) 서서울S/S #1M.Tr 1차측 인출변경 시행(Bushing→EB-G)","2018-05-22 09:00","2018-05-31 18:00","취소","취소","연속",null,null,null,201803130066,"-"]
[78,"경기","군포","화성서서울#1 T/L","33호 철탑 교체 및 7~8호 등 64가닥 전선 교체","철탑교체 : 1기, 전선교체 : 7~8호 등 64가닥","2018-05-01 07:00","2018-05-12 18:00","2018-04-25 07:00","2018-05-06 18:00","연속",null,null,"한전요청",201802120279,"-"]
[79,"경기","군포","화성신안산 T/L","345kV 신안산S/S 모자익 개조공사","○ 신안산S/S 용량부족 GIS 대체 및 SW 증설공사 - 345kV 신안산S/S 모자익 개조공사 ※ 병행작업 : 신안산S/S 건물증축공사(경기건설지사 토건부)","2018-05-16 09:00","2018-05-18 18:00","2018-05-16 09:00","2018-05-18 18:00","연속",null,null,"신뢰도개선",201803070082,"-"]
[80,"경기","동부","곤지암동서울#2 T/L","곤지암S/S 362kV GIS 설치공사","곤지암S/S 362kV GIS 설치공사 관련 #1BUS 무부하가압용 수전선로 - 362kV GIS(63kA, 6300A) 2CB 설치(76Bay)","2018-05-14 10:00","2018-05-15 10:00","2018-05-14 10:00","2018-05-15 10:00","연속",null,null,null,201803120044,"-"]
[81,"경기","동부","곤지암S/S 345kV #2 BUS","곤지암S/S 362kV GIS 설치공사","곤지암S/S 362kV GIS 설치공사 관련 #2BUS측 설치 - 362kV GIS(63kA, 6300A) 2CB 설치(76Bay)","2018-05-15 10:00","2018-05-20 18:00","2018-05-15 10:00","2018-05-20 18:00","연속",null,null,null,201803120047,"-"]
[82,"경기","동부","곤지암S/S 345kV #1 BUS","곤지암S/S 362kV GIS 설치공사","곤지암S/S 362kV GIS 설치공사 관련 #1BUS측 설치 - 362kV GIS(63kA, 6300A) 2CB 설치(76Bay)","2018-05-08 10:00","2018-05-15 10:00","2018-05-08 10:00","2018-05-15 10:00","연속",null,null,null,201803120043,"-"]
[83,"경기","동부","곤지암동서울#2 T/L","곤지암S/S 362kV GIS 설치공사","곤지암S/S 362kV GIS 설치공사 관련 #2BUS 무부하가압용 수전선로 - 362kV GIS(63kA, 6300A) 2CB 설치(76Bay)","2018-05-19 18:00","2018-05-20 18:00","2018-05-19 18:00","2018-05-20 18:00","연속",null,null,null,201803120048,"-"]
[84,"경기","동부","곤지암S/S #3 M.Tr A","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S #66BUS 무부하가압 용 수전변압기","2018-05-26 17:00","2018-05-27 17:00","2018-05-26 17:00","2018-05-27 17:00","연속",null,null,null,201803120085,"-"]
[85,"경기","성남","서안성S/S 345kV #1 BUS","345kV 서안성S/S GIS 용량대체 공사[전문]","ㅇGIS(362kV 63kA) x 11CB 설치 ㅇGIS(362kV 50kA) x 11CB 철거 등","2018-05-28 09:00","2018-06-03 18:00","2018-05-28 09:00","2018-06-03 18:00","연속",null,null,null,201803130024,"-"]
[86,"경기","성남","서안성신진천#1 T/L","345kV 신안성-서안성T/L OPGW 증설","No.93~서안성S/S OPGW 증설(7기)","2018-05-05 07:00","2018-05-08 18:00","취소","취소","연속",null,null,null,201803130193,"-"]
[87,"경기","성남","신성남동서울#2 T/L","서서울2-신성남#2T/L 항공장애 표시구 설치(안전이격)","서서울2-신성남#2T/L 항공장애 표시구 설치(안전이격)","2018-05-09 09:00","2018-05-09 18:00","2018-05-09 09:00","2018-05-09 18:00","당일",null,null,null,201803130221,"-"]
[88,"경기","성남","신성남동서울#1 T/L","345kV 신성남-동서울#1T/L C/H 및 LA점검","불곡산C/H 피뢰기 절연열화 측정(3개소)","2018-05-03 08:00","2018-05-03 18:00","2018-05-03 08:00","2018-05-03 18:00","당일",null,null,null,201803060140,"-"]
[89,"경기","성남","신성남동서울#2 T/L","345kV 신성남-동서울#2T/L C/H 및 LA점검","불곡산C/H 피뢰기 절연열화 측정(3개소)","2018-05-04 08:00","2018-05-04 18:00","2018-05-04 08:00","2018-05-04 18:00","당일",null,null,null,201803060141,"-"]
[90,"경기","성남","신성남S/S 70-71 GIS","신성남S/S 70-71 보통점검, 전자변히터","신성남S/S 70-71 보통점검, 전자변히터","2018-05-14 09:00","2018-05-14 18:00","2018-05-14 09:00","2018-05-14 18:00","당일",null,null,null,201803130207,"-"]
[91,"경기","성남","신성남S/S 75-76 GIS","신성남S/S 75-76 GIS 보통점검, 전자변히터","신성남S/S 75-76 GIS 보통점검, 전자변히터","2018-05-15 09:00","2018-05-15 18:00","2018-05-15 09:00","2018-05-15 18:00","당일",null,null,null,201803130227,"-"]
[92,"경기","성남","서서울#2신성남 #2T/L","345kV 서서울2-신성남#2T/L 송전선로 정밀점검","345kV 서서울2-신성남#2T/L 신성남S/S ~ 38호 송전선로 정밀점검","2018-05-09 09:00","2018-05-11 18:00","2018-05-09 09:00","2018-05-11 18:00","연속",null,null,null,201803070095,"-"]
[93,"경기","성남","신용인신수원 T/L","화성동탄2 345kV 신용인신수원 송전선로 지중화공사","대상선로:345kV신용인신수원, 신안성신수원#1, #2, 신용인삼성 -철탑기수 : 7기(임시선로 3기 별도) -이설긍장 : 2.23km -지중화구간 : 1.71km","2018-05-06 07:00","2018-05-06 18:00","2018-05-06 07:00","2018-05-06 18:00","연속",null,null,null,201803120233,"-"]
[94,"경기","성남","신안성신수원#1 T/L","화성동탄2 345kV 신용인신수원 송전선로 지중화공사","대상선로:345kV신용인신수원, 신안성신수원#1, #2, 신용인삼성 -철탑기수 : 7기(임시선로 3기 별도) -이설긍장 : 2.23km -지중화구간 : 1.71km","2018-05-06 07:00","2018-05-18 18:00","2018-05-06 07:00","2018-05-18 18:00","연속",null,null,null,201803120241,"-"]
[95,"경기","성남","신안성신수원#2 T/L","화성동탄2 345kV 신용인신수원 송전선로 지중화공사","대상선로:345kV신용인신수원, 신안성신수원#1, #2, 신용인삼성 -철탑기수 : 7기(임시선로 3기 별도) -이설긍장 : 2.23km -지중화구간 : 1.71km","2018-05-27 07:00","2018-06-03 18:00","2018-05-27 07:00","2018-06-03 18:00","연속",null,null,null,201803120248,"-"]
[96,"경기","성남","신안성S/S #7 Sh.R GIS (7B71)","신안성S/S #7Sh.R 7B71 결상 조치","신안성S/S #7Sh.R 7B71 결상 조치, DS 보조계전기 교체","2018-05-08 09:00","2018-05-08 18:00","2018-05-08 09:00","2018-05-08 18:00","당일",null,null,null,201803140034,"-"]
[97,"경기","성남","신안성신수원#1 T/L","154kV 신용인-용인T/L 피뢰기 설치(안전이격확보)","154kV 신용인-용인T/L No.12-14 피뢰기 설치(안전이격확보)","2018-05-27 07:00","2018-05-27 18:00","2018-05-27 07:00","2018-05-27 18:00","당일",null,null,null,201803120385,"-"]
[98,"경기","성남","신용인삼성T/L","화성동탄2 345kV 신용인신수원 송전선로 지중화공사","대상선로:345kV신용인신수원, 신안성신수원#1, #2, 신용인삼성 -철탑기수 : 7기(임시선로 3기 별도) -이설긍장 : 2.23km -지중화구간 : 1.71km","2018-05-19 07:00","2018-05-27 18:00","2018-05-19 07:00","2018-05-27 18:00","연속",null,null,null,201803120246,"-"]
[99,"경기","성남","신용인삼성T/L ","화성동탄2 345kV 신용인신수원 송전선로 지중화공사","대상선로:345kV신용인신수원, 신안성신수원#1, #2, 신용인삼성 -철탑기수 : 7기(임시선로 3기 별도) -이설긍장 : 2.23km -지중화구간 : 1.71km","2018-05-13 07:00","2018-05-13 18:00","2018-05-13 07:00","2018-05-13 18:00","연속",null,null,null,201803120244,"-"]
[100,"경기","직할","화성S/S 345kV #2LCR 75BUS GIS CB (7577)","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 철거시행","2018-05-14 09:00","2018-11-30 18:00","2018-05-14 09:00","2018-11-30 18:00","연속",null,null,null,201803120668,"-"]
[101,"경기","직할","화성S/S 345kV #1LCR 71BUS CB (7177)","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 철거시행","2018-05-14 09:00","2018-05-18 18:00","2018-05-14 09:00","2018-05-18 18:00","연속",null,null,null,201803120666,"-"]
[102,"경기","직할","화성S/S 345kV #2LCR 76BUS GIS CB (7677)","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 철거시행","2018-05-14 09:00","2018-11-30 18:00","2018-05-14 09:00","2018-11-30 18:00","연속",null,null,null,201803120667,"-"]
[103,"경기","직할","화성S/S 345kV #75 BUS","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 #75모선 분리","2018-05-14 09:00","2018-05-23 18:00","2018-05-14 09:00","2018-05-23 18:00","연속",null,null,null,201803120664,"-"]
[104,"경기","직할","화성S/S 345kV #1LCR 70BUS CB (7077)","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 철거시행","2018-05-14 09:00","2018-05-18 18:00","2018-05-14 09:00","2018-05-18 18:00","연속",null,null,null,201803210037,"-"]
[105,"경기","직할","아산화성#1 T/L","345kV 아산-화성T/L 전력선 교체공사","No.75-76 등 6섹션 전력선교체, 표시구 설치, 피뢰기설치","2018-05-30 07:00","2018-06-05 18:00","2018-05-30 07:00","2018-06-05 18:00","연속",null,null,null,201803120535,"-"]
[106,"경기","직할","화성S/S 75-76-0 SEC CB (75-76-0)","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 철거시행","2018-05-14 09:00","2018-11-30 18:00","2018-05-14 09:00","2018-11-30 18:00","연속",null,null,null,201803120669,"-"]
[107,"경기","직할","아산화성#2 T/L","345kV 아산-화성T/L 전력선 교체공사","No.75-76 등 6섹션 전력선교체, 표시구설치","2018-05-23 07:00","2018-05-29 18:00","2018-05-23 07:00","2018-05-29 18:00","연속",null,null,null,201803120534,"-"]
[108,"경기","평택","평택T/P #1 TIE Tr A","신평택발전 공사 관련 평택T/P 주변압기 보호PNL 이설","신평택발전 공사 관련 평택T/P 주변압기 보호PNL 이설 / #1Tie Tr(7400)","2018-05-01 09:00","2018-05-04 18:00","2018-05-01 09:00","2018-05-04 18:00","연속",null,null,null,201803130068,"-"]
[109,"경기","평택","평택T/P #2 TIE Tr A","신평택발전 공사 관련 평택T/P 주변압기 보호PNL 이설","신평택발전 공사 관련 평택T/P 주변압기 보호PNL 이설 / #2Tie Tr(7300)","2018-05-05 09:00","2018-05-08 18:00","2018-05-05 09:00","2018-05-08 18:00","연속",null,null,null,201803130069,"-"]
[110,"경기","평택","평택T/P #3 TIE Tr A","신평택발전 공사 관련 평택T/P 주변압기 보호PNL 이설","신평택발전 공사 관련 평택T/P 주변압기 보호PNL 이설 / #3Tie Tr(7100)","2018-05-14 09:00","2018-05-17 18:00","2018-05-14 09:00","2018-05-17 18:00","연속",null,null,null,201803130070,"-"]
[111,"경기","서서울","서서울S/S #3 M.Tr A","변압기 점검","변압기 점검","2018-05-24 09:00","2018-06-01 18:00","2018-05-24 09:00","2018-06-01 18:00","연속",{"$nulls":4},"-"]
[112,"강원","동해","신제천동해#1 T/L","345kV 동해T/L 전선접속개소 교체공사","No.180~No.226 전선접속개소 교체 7.9c-km","2018-05-23 08:00","2018-06-06 18:00","2018-05-23 08:00","2018-06-06 18:00","연속",null,null,null,201803060102,"-"]
[113,"강원","동해","동해S/S #3 M.Tr A","동해S/S STATCOM 설치공사","○ STATCOM(±400MVar) 설비 1식 ○ 변압기 345kV/49.5kV 1Bank ○ 제어반 및 제어케이블 1식 등","2018-05-14 09:00","2018-05-20 18:00","2018-05-14 09:00","2018-05-20 18:00","연속",null,null,null,201803120466,"-"]
[114,"강원","동해","동해삼척GP#1 T/L","345kV 동해-삼척GPT/L 전선접속개소 전선교체공사","No.39~65 전선교체공사","2018-05-28 08:00","2018-06-11 18:00","2018-05-28 08:00","2018-06-11 18:00","연속",null,null,null,201803120369,"-"]
[115,"강원","태백","신태백S/S 345kV #2 Sh.R","345kV Sh.R 보통점검","신태백S/S 345kV #2 Sh.R 보통점검","2018-05-28 09:00","2018-05-28 18:00","2018-05-28 09:00","2018-05-28 18:00","당일",null,null,null,201803090366,"-"]
[116,"강원","태백","신태백S/S 345kV #3 Sh.R","345kV Sh.R 보통점검","신태백S/S 345kV #3 Sh.R 보통점검","2018-05-29 09:00","2018-05-29 18:00","2018-05-29 09:00","2018-05-29 18:00","당일",null,null,null,201803090367,"-"]
[117,"충북","직할","신제천S/S 345kV #1 BUS","신제천S/S SVC용 362kV GIS 증설공사","362kV 63kA 6,300A 2CB 설치 기타부대공사","2018-05-08 09:30","2018-05-12 17:30","취소","취소","연속",null,null,null,201803050105,"-"]
[118,"충북","직할","신제천S/S 345kV #2 BUS","신제천S/S SVC용 362kV GIS 증설공사","362kV 63kA 6,300A 2CB 설치 기타부대공사","2018-05-14 09:30","2018-05-18 17:30","취소","취소","연속",null,null,null,201803050107,"-"]
[119,"충북","청주","신옥천북경남 T/L","345kV 신옥천-북경남T/L 전선접속개소 전선교체공사","전선교체 22.661c-km","2018-05-14 08:00","2018-05-23 19:00","취소","취소","연속",null,null,null,201803090404,"-"]
[120,"충북","청주","신옥천S/S #3 M.Tr A","18~19년 청주전력 변전협력회사 총액공사","신옥천S/S 345kV #3M.Tr 변압기 보호반 대체","2018-05-08 09:30","2018-05-11 18:00","2018-05-08 09:30","2018-05-11 18:00","연속",null,null,null,201802080356,"-"]
[121,"충북","청주","신옥천무주양수 T/L","345kV 신옥천-북경남T/L 전선접속개소 전선교체공사","전선교체 22.661c-km","2018-05-24 08:00","2018-06-02 19:00","2018-05-24 08:00","2018-06-02 19:00","연속",null,null,null,201803090405,"-"]
[122,"대전충남","대전","신옥천신계룡 T/L","[송전] 345kV 신옥천-청양T/L 전선교체공사","[송전] 345kV 신옥천-신계룡T/L 전선교체공사","2018-05-28 07:00","2018-06-12 18:00","2018-05-28 07:00","2018-06-12 18:00","연속",null,null,null,201803080706,"-"]
[123,"대전충남","서산","당진T/P #71 Tie-Tr 1차-1호기 1차 CB (7100)","18년 서산PO 변전협력회사 총액공사","당진화력 345kV 7100 GIS 보통점검","2018-05-23 09:00","2018-05-23 18:00","2018-05-23 09:00","2018-05-23 18:00","당일",null,null,null,201803120703,"-"]
[124,"대전충남","서산","당진T/P #71 Tie-Tr 1차 CB (7171)","18년 서산PO 변전협력회사 총액공사","당진화력 345kV 7171 CB 보통점검 (1호기 O/H)","2018-05-15 09:00","2018-05-15 18:00","2018-05-15 09:00","2018-05-15 18:00","당일",null,null,null,201803120702,"-"]
[125,"대전충남","서산","당진T/P #1TIE Tr 1차-2호기 1차 CB (7200)","18년 서산PO 변전협력회사 총액공사","당진화력 345kV 7200 CB 보통점검 (2호기 O/H)","2018-05-14 09:00","2018-05-14 18:00","2018-05-14 09:00","2018-05-14 18:00","당일",null,null,null,201803120701,"-"]
[126,"대전충남","서산","신서산S/S #4M.Tr2차-신서산신당진#1T/L CB (7800)","18년 서산 PO 변전협력회사 총액공사","신서산 345kV 7800 GIS 보통점검","2018-05-10 09:00","2018-05-10 18:00","2018-05-10 09:00","2018-05-10 18:00","당일",null,null,null,201803120700,"-"]
[127,"대전충남","서산","신당진개폐소태안화력#1 T/L","18년 서산PO 변전협력회사 총액공사","5.5(토) 태안화력S/Y 개폐소-태안화력#1T/L CVT, LA 대체(~일요일까지) 신당진개폐소 7A72 하자점검(토), 7A00 하자점검(일)","2018-05-05 09:00","2018-05-06 18:00","2018-05-05 09:00","2018-05-06 18:00","연속",null,null,null,201803150387,"-"]
[128,"대전충남","아산","신온양S/S #2 M.Tr A","신온양S/S 345kV #2M.Tr 하자점검 등","○ 신온양S/S 345kV #2M.Tr 하자점검 등","2018-05-03 09:00","2018-05-04 18:00","2018-05-03 09:00","2018-05-04 18:00","연속",null,null,null,201803120515,"-"]
[129,"대전충남","아산","신탕정S/S #1 M.Tr A","신탕정S/S 345kV #1M.Tr 보통점검 등","○ 신탕정S/S 345kV #1M.Tr 보통점검 등","2018-05-10 09:00","2018-05-11 18:00","2018-05-10 09:00","2018-05-11 18:00","연속",null,null,null,201803120522,"-"]
[130,"대전충남","아산","신탕정S/S #2 M.Tr A","신탕정S/S 345kV #2M.Tr 보통점검 등","○ 신탕정S/S 345kV #2M.Tr 보통점검 등","2018-05-16 09:00","2018-05-17 18:00","2018-05-16 09:00","2018-05-17 18:00","연속",null,null,null,201803120539,"-"]
[131,"대전충남","아산","아산S/S 345kV #2 BUS","아산S/S 345kV #3M.Tr 1차 7752DS 하자보수","○ 아산S/S 345kV #3M.Tr 1차 7752DS 수분 함유량 과다발생에 따른 하자보수","2018-05-14 09:00","2018-05-15 18:00","2018-05-14 09:00","2018-05-15 18:00","연속",null,null,null,201803190322,"-"]
[132,"대전충남","아산","아산S/S #3 M.Tr 1차 CB (7772)","아산S/S 345kV #3M.Tr 1차 7752DS 하자보수","○ 아산S/S 345kV #3M.Tr 1차 7752DS 수분 함유량 과다발생에 따른 하자보수","2018-05-14 09:00","2018-05-15 18:00","2018-05-14 09:00","2018-05-15 18:00","연속",null,null,null,201803190323,"-"]
[133,"대전충남","청양","보령C/C 345kV #76 BUS","보령복합 345kV #73Bay B/F 보호배전반 교체공사","○보령복합 345kV #73Bay B/F 보호배전반 교체공사","2018-05-24 14:00","2018-05-24 18:00","2018-05-24 14:00","2018-05-24 18:00","당일",null,null,null,201803160013,"-"]
[134,"대전충남","청양","보령C/C 345kV #71 BUS","보령복합 345kV #73Bay B/F 보호배전반 교체공사","○보령복합 345kV #73Bay B/F 보호배전반 교체공사","2018-05-24 09:00","2018-05-24 13:00","2018-05-24 09:00","2018-05-24 13:00","당일",null,null,null,201803160012,"-"]
[135,"대전충남","청양","보령C/C #1 M.Tr 1차 CB (7172)","345kV 차단기 부동작 예방조작시험","○ 보령C/C 7172 차단기 부동작 예방조작시험","2018-05-23 09:00","2018-05-23 12:00","2018-05-23 09:00","2018-05-23 12:00","당일",null,null,null,201803070229,"-"]
[136,"대전충남","청양","청양보령복합 T/L","보령복합 345kV #73Bay B/F 보호배전반 교체","○ 보령복합 345kV #73Bay B/F 보호배전반 교체 ○ 청양S/S 청양-보령복합T/L LA, CVT 교체 ○ YPP제 송전선로 보호배전반 성능개선","2018-05-21 09:00","2018-05-25 18:00","2018-05-21 09:00","2018-05-25 18:00","연속",null,null,null,201803080541,"-"]
[137,"대전충남","청양","보령C/C #3 M.Tr 1차 CB (7372)","보령복합 345kV #73Bay B/F 보호배전반 교체","○ 보령복합 345kV #73Bay B/F 보호배전반 교체","2018-05-21 09:00","2018-05-25 18:00","2018-05-21 09:00","2018-05-25 18:00","연속",null,null,null,201803080547,"-"]
[138,"대전충남","청양","보령TP보령CC#2 T/L","YPP제 345kV 송전선로 보호배전반 성능개선","○ YPP제 345kV 송전선로 보호배전반 성능개선","2018-05-25 09:00","2018-05-25 18:00","2018-05-25 09:00","2018-05-25 18:00","당일",null,null,null,201803080549,"-"]
[139,"대전충남","청양","보령C/C #4 M.Tr 1차-신보령연락T/L CB (7400)","345kV 차단기 부동작 예방조작시험","○ 보령C/C 7400 차단기 부동작 예방조작시험","2018-05-25 09:00","2018-05-25 12:00","2018-05-25 09:00","2018-05-25 12:00","당일",null,null,null,201803070233,"-"]
[140,"대전충남","청양","보령C/C 신보령연락T/L CB (7471)","345kV 차단기 부동작 예방조작시험","○ 보령C/C 7471 차단기 부동작 예방조작시험","2018-05-25 13:00","2018-05-25 15:00","2018-05-25 13:00","2018-05-25 15:00","당일",null,null,null,201803070234,"-"]
[141,"대전충남","청양","보령C/C #4 M.Tr 1차 CB (7472)","345kV 차단기 부동작 예방조작시험","○ 보령C/C 7472 차단기 부동작 예방조작시험","2018-05-25 15:00","2018-05-25 17:00","2018-05-25 15:00","2018-05-25 17:00","당일",null,null,null,201803070235,"-"]
[142,"대전충남","청양","보령C/C #2 M.Tr 1차 CB (7272)","345kV 차단기 부동작 예방조작시험","○ 보령C/C 7272 차단기 부동작 예방조작시험","2018-05-24 09:00","2018-05-24 12:00","2018-05-24 09:00","2018-05-24 12:00","당일",null,null,null,201803070231,"-"]
[143,"대전충남","청양","보령T/P 345kV #76 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7571 GIS 교체 ○ 보령화력 345kV 7500 GIS 교체 ○ 보령화력 345kV 7572 GIS 교체","2018-05-11 14:00","2018-05-11 18:00","2018-05-11 14:00","2018-05-11 18:00","연속",null,null,null,201803080515,"-"]
[144,"대전충남","청양","보령TP보령CC#2 T/L","관내S/S 345kV 피뢰기, CVT 보통점검","○ 345kV 보령연락#1T/L 피뢰기, CVT 보통점검","2018-05-17 09:00","2018-05-17 18:00","2018-05-17 09:00","2018-05-17 18:00","당일",null,null,null,201803120040,"-"]
[145,"대전충남","청양","아산보령화력#1 T/L","관내S/S 345kV 피뢰기, CVT 보통(초기)점검","○ 345kV 아산-보령화력#1T/L 피뢰기, CVT 보통(초기)점검","2018-05-18 09:00","2018-05-18 18:00","2018-05-18 09:00","2018-05-18 18:00","당일",null,null,null,201803120041,"-"]
[146,"대전충남","청양","보령T/P #3 M.Tr 1차-#3,4 SU Tr 1차 CB (7300)","관내S/S 345kV 차단기 부동작 예방조작시험","○보령T/P #3M.Tr 1차-#3,4SU.Tr 1차(7300) 조작시험","2018-05-09 13:00","2018-05-09 15:00","2018-05-09 13:00","2018-05-09 15:00","당일",null,null,null,201803150339,"-"]
[147,"대전충남","청양","보령T/P #3 M.Tr 1차 CB (7371)","관내S/S 345kV 차단기 부동작 예방조작시험","○보령T/P #3M.Tr 1차 CB(7371) 조작시험","2018-05-09 09:00","2018-05-09 12:00","2018-05-09 09:00","2018-05-09 12:00","당일",null,null,null,201803150338,"-"]
[148,"대전충남","청양","보령T/P 345kV #71 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7571 GIS 교체 ○ 보령화력 345kV 7500 GIS 교체 ○ 보령화력 345kV 7572 GIS 교체","2018-05-11 09:00","2018-05-11 14:00","2018-05-11 09:00","2018-05-11 14:00","연속",null,null,null,201803080513,"-"]
[149,"대전충남","청양","신옥천청양 T/L","[송전] 345kV 신옥천-청양T/L 전선교체공사","[송전] 345kV 신옥천-청양T/L 전선교체공사","2018-05-03 07:00","2018-05-27 18:00","2018-05-03 07:00","2018-05-27 18:00","연속",null,null,null,201803080707,"-"]
[150,"대전충남","청양","청양신보령화력 T/L","보령화력 345kV 송전선로 항공장구 설치","○ 보령화력 345kV 송전선로 항공장구 설치","2018-05-08 09:00","2018-05-27 18:00","2018-05-08 09:00","2018-05-27 18:00","연속",null,null,null,201803080552,"-"]
[151,"대전충남","청양","청양S/S #1 M.Tr A","2018년 청양S/S #1M.Tr 및 OLTC 정밀점검 공사","#1M.Tr 및 OLTC 정밀점검","2018-05-28 09:00","2018-06-15 18:00","2018-05-28 09:00","2018-06-15 18:00","연속",null,null,null,201803020117,"-"]
[152,"전북","군산","군산S/S 청양-군산#2T/L CB (7471)","군산P/O 154kV이상 차단기 조작시험","차단기 조작시험 (양단 조작시험 시행)","2018-05-03 09:00","2018-05-03 15:00","2018-05-03 09:00","2018-05-03 15:00","당일",null,null,null,201803150042,"-"]
[153,"전북","김제","신김제S/S #2 M.Tr A","2018년도 154kV 차단기 정밀점검","2018년도 154kV 차단기 정밀점검","2018-05-28 09:00","2018-05-30 18:00","2018-05-28 09:00","2018-05-30 18:00","연속",null,null,null,201801180168,"-"]
[154,"전북","김제","신김제S/S #1 M.Tr A","2018년도 154kV 차단기 정밀점검","2018년도 154kV 차단기 정밀점검","2018-05-14 09:00","2018-05-16 18:00","2018-05-14 09:00","2018-05-16 18:00","연속",null,null,null,201801180167,"-"]
[155,"전북","직할","무주P/P 신옥천-무주양수T/L CB (7171)","관내S/S 154kV 이상 차단기 조작시험","무주P/P 신옥천-무주양수T/L CB(7171) 개폐타임 측정","2018-05-15 10:00","2018-05-15 12:00","2018-05-15 10:00","2018-05-15 12:00","당일",null,null,null,201803150346,"-"]
[156,"전북","직할","무주P/P 북경남-무주양수T/L CB (7271)","관내S/S 154kV 이상 차단기 조작시험","무주P/P 북경남-무주양수T/L CB(7271) 개폐타임 측정","2018-05-15 13:00","2018-05-15 15:00","2018-05-15 13:00","2018-05-15 15:00","당일",null,null,null,201803150347,"-"]
[157,"전북","직할","북경남무주양수 T/L","345kV 신옥천-북경남T/L 전선접속개소 전선교체공사","전선교체 22.661c-km","2018-05-30 08:00","2018-06-04 19:00","2018-06-03 08:00","2018-06-08 19:00","연속",null,null,null,201803090408,"-"]
[158,"전북","직할","신남원S/S 신옥천-신남원#1 T/L GIS","관내S/S 154kV 이상 차단기 보통점검공사","362kV GIS CB(7271) 보통점검","2018-05-09 09:30","2018-05-09 18:00","2018-05-09 09:30","2018-05-09 18:00","당일",null,null,null,201803120259,"-"]
[159,"전북","직할","신남원S/S 신옥천-신남원#2 T/L GIS","관내S/S 154kV 이상 차단기 보통점검공사","362kV GIS CB(7100) 보통점검","2018-05-08 09:30","2018-05-08 18:00","2018-05-08 09:30","2018-05-08 18:00","당일",null,null,null,201803120251,"-"]
[160,"전북","직할","신옥천신남원#1 T/L","345kV 신옥천-신남원T/L No.74 안전이격 확보공사","가. 철탑철거 : 2기 [No.73(A-18), No.74(B-14)] 나. 철탑설치 : 1기 [No.74(Ba2-60)] 다. 전력선 교체 : 0.433km [HSTACIR 410㎟ x 2B] , 12가닥 라. 가선로 구성 : 가철탑 1기","2018-05-26 08:00","2018-06-01 18:00","2018-05-26 08:00","2018-06-01 18:00","연속",null,null,null,201803220144,"-"]
[161,"전북","직할","신옥천신남원#2 T/L","345kV 신옥천-신남원T/L No.74 안전이격 확보공사","가. 철탑철거 : 2기 [No.73(A-18), No.74(B-14)] 나. 철탑설치 : 1기 [No.74(Ba2-60)] 다. 전력선 교체 : 0.433km [HSTACIR 410㎟ x 2B] , 12가닥 라. 가선로 구성 : 가철탑 1기","2018-05-14 08:00","2018-05-25 18:00","2018-05-14 08:00","2018-05-25 18:00","연속",null,null,null,201803220142,"-"]
[162,"전북","직할","신옥천신남원#1 T/L","345kV 신옥천-신남원T/L No.74 안전이격 확보공사","가. 철탑철거 : 2기 [No.73(A-18), No.74(B-14)] 나. 철탑설치 : 1기 [No.74(Ba2-60)] 다. 전력선 교체 : 0.433km [HSTACIR 410㎟ x 2B] , 12가닥 라. 가선로 구성 : 가철탑 1기","2018-05-08 08:00","2018-05-13 18:00","2018-05-08 08:00","2018-05-13 18:00","연속",null,null,null,201803220141,"-"]
[163,"전북","직할","신남원S/S #1 M.Tr A","신남원S/S 345kV #1M.Tr 초기점검","345kV #1M.Tr 절연열화, SFRA, 경보시험 등 초기점검","2018-05-01 09:30","2018-05-02 18:00","2018-05-02 09:30","2018-05-03 18:00","연속",null,null,null,201803160137,"-"]
[164,"광주전남","강진","신화순신강진#2 T/L","345kV 신화순-신강진 T/L 접속개소해소공사","1. 345kV 신화순-신강진 #1,#2 T/L","2018-05-02 08:00","2018-05-06 18:00","2018-05-02 08:00","2018-05-06 18:00","연속",null,null,null,201802130108,"-"]
[165,"광주전남","광주","신광주신화순#1 T/L","345kV 신광주-신화순T/L 전선접속개소해소공사","신광주-신화순T/L No.45~57, 99~108호 전선교체","2018-05-08 07:00","2018-05-21 18:00","2018-05-08 07:00","2018-05-21 18:00","연속",null,null,null,201803060131,"-"]
[166,"광주전남","광주","신광주신화순#2 T/L","345kV 신광주-신화순T/L 전선접속개소해소공사","신광주-신화순T/L No.45~57, 99~108호 전선교체","2018-05-22 07:00","2018-06-04 18:00","2018-05-22 07:00","2018-06-04 18:00","연속",null,null,null,201803060132,"-"]
[167,"광주전남","광주","신화순S/S #2 M.Tr A","신화순S/S #2 M.Tr(변전협력회사공사)","신화순S/S 345kV 77Bay B/F PNL 교체, 7771,7700CB 보통점검 및 양단DS 리미트스위치 교체, 부싱절연유 채취","2018-05-14 09:00","2018-05-18 18:00","2018-05-14 09:00","2018-05-18 18:00","연속",null,null,null,201803150360,"-"]
[168,"광주전남","순천","신강진광양#2 T/L","광양S/S 362kV GIS 용량대체","광양S/S 362kV 신강진-광양#2T/L GIS","2018-05-31 09:00","2018-08-31 18:00","취소","취소","당일",null,null,null,201803230084,"-"]
[169,"광주전남","순천","광양S/S #3 M.Tr A","광양S/S 362kV GIS 용량대체","광양S/S 362kV #3M.Tr GIS 용량대체","2018-05-31 09:00","2018-08-31 18:00","취소","취소","당일",null,null,null,201803230085,"-"]
[170,"광주전남","순천","광양하동화력#2 T/L","345kV 광양-하동TPT/L 전력선 교체공사","345kV 광양-하동TP T/L No.50~54, 56~58, 59~72 전력선교체공사","2018-05-13 07:00","2018-05-27 18:00","2018-05-28 07:00","2018-06-11 18:00","연속",null,null,null,201803150113,"-"]
[171,"광주전남","순천","신강진광양#1 T/L","345kV 광양-하동TPT/L 전력선 교체공사","345kV 광양-하동TP T/L No.50~54, 56~58, 59~72 전력선교체공사 4회선 구간 안전이격확보","2018-05-13 07:00","2018-05-19 18:00","2018-05-28 07:00","2018-06-03 18:00","연속",null,null,null,201803150115,"-"]
[172,"광주전남","순천","광양하동화력#1 T/L","345kV 광양-하동TPT/L 전력선 교체공사","345kV 광양-하동TP T/L No.50~54, 56~58, 59~72 전력선교체공사","2018-05-28 07:00","2018-06-11 18:00","2018-05-13 07:00","2018-05-27 18:00","연속",null,null,null,201803150114,"-"]
[173,"광주전남","순천","신강진광양#2 T/L","345kV 광양-하동TPT/L 전력선 교체공사","345kV 광양-하동TP T/L No.50~54, 56~58, 59~72 전력선교체공사 4회선 구간 안전이격확보","2018-05-28 07:00","2018-06-03 18:00","2018-05-13 07:00","2018-05-19 18:00","연속",null,null,null,201803150116,"-"]
[174,"대구","경산","신경산대구#1 T/L","신경산대구T/L 전력선교체공사","전력선교체(No.39~51)","2018-05-24 07:00","2018-06-02 18:00","취소","취소","연속",null,null,null,201803120303,"-"]
[175,"대구","경산","신경산S/S #1 M.Tr A","18년 경산 변전협력회사 총액공사","C상 2차 부싱단자 과열보수","2018-05-03 09:00","2018-05-03 14:00","2018-05-03 09:00","2018-05-03 14:00","당일",null,null,null,201803160152,"-"]
[176,"대구","달성","고령S/S #3 M.Tr A","누유개소 하자처리","누유개소 하자처리","2018-05-11 09:00","2018-05-11 18:00","2018-05-11 09:00","2018-05-11 18:00","당일",null,null,null,201803080463,"-"]
[177,"대구","달성","북경남대구#2 T/L","달성전력지사 GIS 정밀점검공사","달성전력지사 GIS 정밀점검공사","2018-05-14 09:00","2018-05-19 18:00","2018-05-14 09:00","2018-05-19 18:00","연속",null,null,null,201803160186,"-"]
[178,"대구","칠곡","북대구선산 T/L","345kV선산분기T/L 전력선 교체공사","345kV북대구-선산T/L No.83~84 전력선 교체공사 (345kV선산분기T/L No.54~55)","2018-05-23 08:00","2018-05-25 18:00","2018-05-23 08:00","2018-05-27 18:00","연속",null,null,null,201803150331,"-"]
[179,"대구","포항","신월성N/P #1SA.Tr 1차 CB (7372)","2018년 포항전력지사 총액공사","신월성S/Y 7372 CB 보통점검","2018-05-10 09:00","2018-05-10 18:00","2018-05-11 09:00","2018-05-11 18:00","당일",null,null,null,201803210332,"○"]
[180,"대구","포항","신포항S/S #3 M.Tr A","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 8DS, T-BUS 철거 등","2018-05-28 08:00","2018-05-29 18:00","취소","취소","연속",null,null,null,201803050021,"-"]
[181,"대구","포항","신포항북대구 T/L","345kV 신포항-북대구T/L 지장선로이설공사(임시선로 구성)","345kV 신포항-북대구T/L 지장선로이설공사 ○ 지지물 교체 2기, 전선교체 10.1km 345kV 신포항-북대구T/L 안전이격확보 ○ 지지물 교체 4기, 전선교체 5.6km","2018-05-08 08:00","2018-05-22 18:00","2018-05-08 08:00","2018-05-22 18:00","연속",null,null,null,201803050160,"-"]
[182,"대구","포항","신포항청송PP T/L","신포항-청송PP T/L 과열개소 보수","신포항-청송PP T/L 과열개소 보수","2018-05-08 09:00","2018-05-09 18:00","취소","취소","연속",null,null,null,201803020009,"○"]
[183,"대구","포항","신포항S/S #4 M.Tr A","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 8DS, T-BUS 철거 등","2018-05-30 08:00","2018-05-31 18:00","취소","취소","연속",null,null,null,201803050022,"-"]
[184,"대구","포항","신포항S/S #1 M.Tr A","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 8DS, T-BUS 철거 등","2018-05-16 08:00","2018-05-17 18:00","취소","취소","연속",null,null,null,201803050019,"○"]
[185,"대구","포항","신포항S/S #2 M.Tr A","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 8DS, T-BUS 철거 등","2018-05-21 08:00","2018-05-22 18:00","취소","취소","연속",null,null,null,201803050020,"-"]
[186,"대구","포항","선산신포항 T/L","345kV 신포항-북대구T/L 지장선로이설공사(임시선로 구성)","345kV 신포항-북대구T/L 지장선로이설공사 ○ 지지물 교체 2기, 전선교체 10.1km 345kV 신포항-북대구T/L 안전이격확보 ○ 지지물 교체 4기, 전선교체 5.6km","2018-05-23 08:00","2018-06-03 18:00","2018-05-23 08:00","2018-06-03 18:00","연속",null,null,null,201803050161,"-"]
[187,"대구","포항","월성NP신월성NP#1T/L","2018년 포항전력지사 총액공사","신월성S/Y 7400 CB 보통점검 월성S/Y PT 보통점검","2018-05-08 09:00","2018-05-09 18:00","2018-05-09 09:00","2018-05-10 18:00","연속",null,null,null,201803020079,"○"]
[188,"대구","포항","월성2N/P #2 SS Tr 1차 CB (7472)","2018년 포항전력지사 총액공사","월성S/Y 7472 CB 보통점검","2018-05-03 09:00","2018-05-03 18:00","2018-05-03 09:00","2018-05-03 18:00","당일",null,null,null,201803210330,"-"]
[189,"경북","구미","선산S/S #1 M.Tr A","선산S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 공사 - 산동#1T/L POST 교체 등","2018-05-07 08:00","2018-05-15 18:00","2018-05-07 08:00","2018-05-15 18:00","연속",null,null,null,201803060003,"-"]
[190,"경북","구미","선산S/S #3 M.Tr A","선산S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 공사","2018-05-21 08:00","2018-05-24 18:00","2018-05-21 08:00","2018-05-24 18:00","연속",null,null,null,201803060006,"-"]
[191,"경북","영주","신제천신영주#1 T/L","345kV 신제천-신영주T/L 전선접속개소 전선교체공사","○ 공사구간 : 345kV 신제천-신영주 T/L No.175~181, 191~201 ○ 전력선 교체 : ACSR 480㎟ × 4B 14.560C-km","2018-05-01 07:00","2018-05-10 18:00","취소","취소","연속",null,null,null,201803060022,"-"]
[192,"경북","영주","신영주S/S STATCOM 1차 GIS","345kV 신영주S/S STATCOM 설치공사","STATCOM 제어동 감시카메라 설치(연기분)","2018-05-14 09:00","2018-05-17 18:00","2018-05-14 09:00","2018-05-17 18:00","연속",null,null,null,201803050103,"-"]
[193,"경북","영주","신제천신영주#2 T/L","345kV 신제천-신영주T/L 전선접속개소 전선교체공사","○ 공사구간 : 345kV 신제천-신영주 T/L No.175~181, 191~201 ○ 전력선 교체 : ACSR 480㎟ × 4B 14.560C-km","2018-05-11 07:00","2018-05-20 18:00","2018-05-23 07:00","2018-06-01 18:00","연속",null,null,null,201803060026,"-"]
[194,"경북","영주","신영주S/S #1 M.Tr A","2018-19년도 영주전력지사 변전협력업체 총액공사","-6144 GCB 하자점검 -4179-2 VCB 보통점검, #1-2Sh.R 초기점검 -현대제 362kV GIS 매커니즘 누유 보수","2018-05-28 09:00","2018-05-29 18:00","2018-05-28 09:00","2018-05-29 18:00","연속",null,null,null,201803080322,"-"]
[195,"경북","영주","신영주S/S #2 M.Tr A","2018-19년도 영주전력지사 변전협력업체 총액공사","-#2M.Tr, 6244 GCB, 4289 VCB, #2S.Tr, M.Tr 3차 PT, 2차 LA A,B,C상 보통점검 - M.Tr 3차 LA 초기점검","2018-05-30 09:00","2018-06-01 18:00","2018-05-30 09:00","2018-06-01 18:00","연속",null,null,null,201803080339,"-"]
[196,"경북","영주","신태백한울NP2#2 T/L","2018-19년도 영주전력지사 변전협력업체 총액공사","-한울2발S/Y 7771, 7700, 7772 GIS 하자점검","2018-05-24 09:00","2018-05-25 18:00","2018-05-24 09:00","2018-05-25 18:00","연속",null,null,null,201803080358,"-"]
[197,"경북","영주","신태백한울NP2#1 T/L","2018-19년도 영주전력지사 변전협력업체 총액공사","-한울2발S/Y 7871, 7800, 7872 GIS 하자점검","2018-05-22 09:00","2018-05-23 18:00","2018-05-22 09:00","2018-05-23 18:00","연속",null,null,null,201803080357,"-"]
[198,"경북","직할","안동CC #2 M.Tr","18~19 경북직할 변전협력업체 총액공사","안동복합S/S #2M.Tr 초기점검 7272,6244 GIS 초기점검","2018-05-16 09:00","2018-05-18 18:00","2018-05-16 09:00","2018-05-18 18:00","매일",null,null,null,201803050135,"○"]
[199,"경북","직할","안동CC #1 M.Tr","18~19 경북직할 변전협력업체 총액공사","안동복합S/S #1M.Tr 초기점검 7171,6144 GIS 초기점검","2018-05-08 09:00","2018-05-10 18:00","2018-05-08 09:00","2018-05-10 18:00","매일",null,null,null,201803050130,"-"]
[200,"경북","직할","안동복합S/Y #1M.Tr TIE GIS","18~19 직할 변전협력업체 총액공사","안동복합S/S 7100GIS 초기점검","2018-05-11 09:00","2018-05-11 18:00","2018-05-11 09:00","2018-05-11 18:00","당일",null,null,null,201803140021,"-"]
[201,"부산울산","동부산","신울산고리NP#2 T/L","345kV 신울산-고리NPT/L 54-55호 안전이격확보공사","철탑 : 설치(2기), 철거(2기), 전선교체 : 53-57호, 2,003km","2018-05-23 09:00","2018-06-06 18:00","2018-05-23 09:00","2018-06-06 18:00","연속",null,null,null,201803060031,"-"]
[202,"부산울산","동부산","신울산고리NP#1 T/L","345kV 신울산-고리NPT/L 54-55호 안전이격확보공사","철탑 : 설치(2기), 철거(2기), 전선교체 : 53-57호, 2,003km","2018-05-23 09:00","2018-06-06 18:00","2018-05-23 09:00","2018-06-06 18:00","연속",null,null,null,201803060030,"-"]
[203,"부산울산","북부산","북부산S/S 345kV #75 BUS","345kV 북부산S/S 차단기용량대체공사","모선연결 작업(74-71BAY : 71BAY 증설연결분)","2018-05-29 08:00","2018-06-06 15:00","2018-05-29 08:00","2018-06-06 15:00","연속",null,null,null,201801080309,"-"]
[204,"부산울산","북부산","신김해북부산#2 T/L","345kV 북부산-울산화력 등 4개T/L 전선교체공사","345kV 신김해-북부산#2T/L 전선교체 No.22~56호","2018-05-21 07:00","2018-06-04 18:00","2018-05-21 07:00","2018-06-04 18:00","연속",null,null,null,201803050045,"-"]
[205,"부산울산","서부산","서부산S/S #3 M.Tr A","서부산S/S 154kV #3M.Tr 2차 GIS(6344) 정밀점검","서부산S/S 154kV #3M.Tr 2차 GIS(6344) 정밀점검 [모선DS 점검제외]","2018-05-16 08:00","2018-05-17 18:00","2018-05-16 08:00","2018-05-17 18:00","연속",null,null,null,201803090031,"-"]
[206,"부산울산","서부산","서부산S/S 345kV #2 Sh.R","서부산S/S 345kV #2Sh.R CB(7277) 보통점검","서부산S/S 345kV #2Sh.R CB(7277) 보통점검","2018-05-21 10:00","2018-05-21 18:00","2018-05-21 10:00","2018-05-21 18:00","당일",null,null,null,201803070007,"-"]
[207,"부산울산","서부산","서부산S/S 서부산#2T/L-#1 M.Tr 1차 CB (7200)","서부산S/S 서부산#2T/L-#1 M.Tr 1차 CB(7200) 보통점검","서부산S/S 서부산#2T/L-#1 M.Tr 1차 CB(7200) 보통점검","2018-05-19 10:00","2018-05-19 18:00","2018-05-19 10:00","2018-05-19 18:00","당일",null,null,null,201803070006,"-"]
[208,"부산울산","서부산","서부산S/S 서부산-북부산#2T/L CB (7271)","서부산S/S 서부산-북부산#2T/L CB(7271) 보통점검","서부산S/S 서부산-북부산#2T/L CB(7271) 보통점검","2018-05-18 10:00","2018-05-18 18:00","2018-05-18 10:00","2018-05-18 18:00","당일",null,null,null,201803070005,"-"]
[209,"부산울산","울산","동울산신울산#1 T/L","가선로 구성","가선로 구성","2018-05-26 07:00","2018-06-08 18:00","2018-05-03 07:00","2018-05-06 18:00","연속",null,null,null,201803080382,"○"]
[210,"부산울산","울산","북부산신울산#2 T/L","345kV 북부산-신울산T/L 42호 지장철탑이설공사","철탑교체 1기(42호), 40~46호간 전선교체(2.087km)","2018-05-09 07:00","2018-05-11 18:00","2018-05-09 07:00","2018-05-11 18:00","연속",null,null,null,201803070020,"-"]
[211,"부산울산","울산","동울산신울산#2 T/L","345kV 동울산-신울산T/L 지장철탑 이설공사 및 전선교체공사","1. 지장이설 구간 : No.50~52(#2 본선로 구성) 2. 전선교체 : No.50~51, 70~75, 88~101, 107~113)","2018-05-12 07:00","2018-05-25 18:00","2018-05-19 07:00","2018-06-01 18:00","연속",null,null,null,201803080371,"-"]
[212,"부산울산","울산","북부산신울산#1 T/L","345kV 북부산-신울산T/L 42호 지장철탑이설공사","철탑교체 1기(42호), 40~46호간 전선교체(2.087km)","2018-05-12 07:00","2018-05-15 18:00","2018-05-12 07:00","2018-05-15 18:00","연속",null,null,null,201803070023,"-"]
[213,"부산울산","울산","북부산신울산#2 T/L","345kV 북부산-신울산T/L 42호 지장철탑이설공사","철탑교체 1기(42호), 40~46호간 전선교체(2.087km)","2018-05-16 07:00","2018-05-20 18:00","2018-05-16 07:00","2018-05-20 18:00","연속",null,null,null,201803070029,"-"]
[214,"부산울산","울산","울산C/C #2,3 S/T-#3,4 G/T CB (7700)","2018-19년 울산전력지사 변전협력회사 총액공사","울산C/C 345kV 77Bay B/F PNL 대체(7700)","2018-05-24 09:00","2018-05-29 18:00","2018-05-24 09:00","2018-05-29 18:00","연속",null,null,null,201803090146,"-"]
[215,"부산울산","울산","울산C/C #3,4 G/T 1차 CB (7772)","2018-19년 울산전력지사 변전협력회사 총액공사","울산C/C 345kV 77Bay B/F PNL 대체(7772)","2018-05-24 09:00","2018-05-29 18:00","2018-05-24 09:00","2018-05-29 18:00","연속",null,null,null,201803090147,"-"]
[216,"부산울산","울산","울산C/C #2,3 S/T CB (7771)","2018-19년 울산전력지사 변전협력회사 총액공사","울산C/C 345kV 77Bay B/F PNL 대체(7771)","2018-05-24 09:00","2018-05-29 18:00","2018-05-24 09:00","2018-05-29 18:00","연속",null,null,null,201803090145,"-"]
[217,"부산울산","울산","울주S/S 울주-신경산#1T/L-TIE CB (7800)","2018-19년 울산전력지사 변전협력회사 총액공사","울주S/S 345kV 7800 GIS 보통점검","2018-05-04 09:00","2018-05-04 18:00","2018-05-04 09:00","2018-05-04 18:00","당일",null,null,null,201803190223,"-"]
[218,"부산울산","울산","울주고리NP#2 T/L","2018-19년 울산전력지사 변전협력회사 총액공사","울주S/S 345kV 75Bay B/F PNL 대체","2018-05-14 09:00","2018-05-17 18:00","취소","취소","연속",null,null,null,201803090150,"-"]
[219,"부산울산","울산","울주S/S 울주-신경산#2T/L-TIE CB (7700)","2018-19년 울산전력지사 변전협력회사 총액공사","울주S/S 345kV 7700 GIS 보통점검","2018-05-03 09:00","2018-05-03 18:00","2018-05-03 09:00","2018-05-03 18:00","당일",null,null,null,201803190224,"-"]
[220,"부산울산","울산","신온산S/S #2 M.Tr A","2018-19년 울산전력지사 변전협력회사 총액공사","1.신온산S/S 345kV #2M.Tr 보호배전반, 74Bay B/F PNL 대체 2.신온산S/S 345kV 7400,7472,6244,4284 보통점검,차단기 동작시험","2018-05-06 09:00","2018-05-11 18:00","2018-05-06 09:00","2018-05-11 18:00","연속",null,null,null,201803090120,"-"]
[221,"부산울산","울산","신온산울산TP T/L","2018-19년 울산전력지사 변전협력회사 총액공사","1.신온산S/S 345kV 74Bay B/F PNL 대체 2.울산C/C 345kV 7671 GIS 보통점검 3.울산C/C 345kV 신온산-울산TPT/L Meter CT 케이블 이설","2018-05-06 09:00","2018-05-11 18:00","2018-05-06 09:00","2018-05-11 18:00","연속",null,null,null,201803090121,"-"]
[222,"부산울산","울산","신온산S/S #3 M.Tr A","새롬프로텍제 345kV 주변압기 보호반 성능개선","신온산S/S 345kV #3M.Tr 보호게전기 성능개선 및 시험","2018-05-30 14:00","2018-05-30 18:00","2018-05-30 14:00","2018-05-30 18:00","당일",null,null,null,201803290229,"-"]
[223,"부산울산","울산","신온산S/S #1 M.Tr A","새롬프로텍제 345kV 주변압기 보호반 성능개선","신온산S/S 345kV #1M.Tr 보호게전기 성능개선 및 시험","2018-05-30 09:00","2018-05-30 14:00","2018-05-30 09:00","2018-05-30 14:00","당일",null,null,null,201803290228,"-"]
[224,"부산울산","울산","울산C/C #2 M.Tr A","2018-19년 울산전력지사 변전협력회사 총액공사","울산C/C 345kV 78Bay B/F PNL 대체(7871)","2018-05-18 09:00","2018-05-23 18:00","2018-05-18 09:00","2018-05-23 18:00","연속",null,null,null,201803090142,"-"]
[225,"부산울산","울산","울산C/C #1 M.Tr A","2018-19년 울산전력지사 변전협력회사 총액공사","울산C/C 345kV 74Bay B/F PNL 대체(7471)","2018-05-12 09:00","2018-05-17 18:00","2018-05-12 09:00","2018-05-17 18:00","연속",null,null,null,201803090136,"-"]
[226,"부산울산","울산","울산C/C 기력4호기 1차 CB (7472)","2018-19년 울산전력지사 변전협력회사 총액공사","울산C/C 345kV 74Bay B/F PNL 대체(7472)","2018-05-12 09:00","2018-05-17 18:00","2018-05-12 09:00","2018-05-17 18:00","연속",null,null,null,201803090140,"-"]
[227,"부산울산","울산","울산C/C #5,6 G/T 1차 CB (7872)","2018-19년 울산전력지사 변전협력회사 총액공사","울산C/C 345kV 78Bay B/F PNL 대체(7872)","2018-05-18 09:00","2018-05-23 18:00","2018-05-18 09:00","2018-05-23 18:00","연속",null,null,null,201803090143,"-"]
[228,"경남","직할","신김해신녹산#1 T/L","2018년 가공송전선로 순시점검 위탁공사","정밀점검(1~22호)","2018-05-14 08:00","2018-05-17 18:00","2018-05-14 08:00","2018-05-17 18:00","매일",null,null,null,201803050175,"-"]
[229,"경남","직할","신마산신김해#1 T/L","2018년 가공송전선로 순시점검 위탁공사","신김해-북부산#2T/L 정밀정검 병가구간 안전이격확보 (신김해-북부산#2TL : 101~106호)","2018-05-25 08:00","2018-05-25 18:00","2018-05-25 08:00","2018-05-25 18:00","당일",null,null,null,201803050183,"-"]
[230,"경남","직할","신김해S/S #2 M.Tr A","신김해S/S 345kV 74BAY B/F PNL 대체공사","신김해S/S 345kV 74BAY B/F PNL 대체공사(신김해-북부산#2T/L 북부산 전력지사 휴전)","2018-05-28 09:00","2018-05-31 17:30","2018-05-28 09:00","2018-05-31 17:30","연속",null,null,null,201803190256,"-"]
[231,"경남","직할","신김해S/S #4 M.Tr A","신김해S/S 345kV 78BAY B/F PNL 대체공사","신김해S/S 345kV 78BAY B/F PNL 대체공사","2018-05-08 09:00","2018-05-11 17:30","2018-05-08 09:00","2018-05-11 17:30","연속",null,null,null,201803040005,"-"]
[232,"경남","직할","신김해S/S #5 M.Tr A","신김해S/S 345kV #5M.Tr 7632DS 부싱교체","신김해S/S 345kV #5M.Tr 7632DS 가스누기 관련 부싱교체","2018-05-02 09:30","2018-05-04 17:30","2018-05-02 09:30","2018-05-04 17:30","연속",null,null,null,201803040006,"-"]
[233,"경남","직할","신김해신녹산#2 T/L","신김해S/S 345kV 78BAY B/F PNL 대체공사","신김해S/S 345kV 78BAY B/F PNL 대체공사","2018-05-08 09:00","2018-05-11 17:30","2018-05-08 09:00","2018-05-11 17:30","연속",null,null,null,201803190255,"-"]
[234,"경남","직할","창원삼천포TP#2 T/L","345kV 창원-삼천포화력T/L 전력선교체공사","전력선교체(114-117, 119-120, 129-132)","2018-05-02 07:00","2018-05-13 18:00","2018-05-02 07:00","2018-05-13 18:00","연속",null,null,null,201802060023,"-"]
[235,"경남","진주","의령S/S 의령-산청양수#1T/L CB (7471)","의령S/S 의령-산청양수#1T/L CB(7471) 정밀점검","의령S/S 의령-산청양수#1T/L CB(7471) 정밀점검","2018-05-31 09:30","2018-06-02 18:30","2018-05-31 09:30","2018-06-02 18:30","연속",null,null,null,201803050294,"-"]
[236,"경남","진주","의령S/S 의령-신마산#2T/L CB (7A71)","의령S/S 의령-신마산#2T/L CB(7A71) 정밀점검","의령S/S 의령-신마산#2T/L CB(7A71) 정밀점검","2018-05-15 09:30","2018-05-17 18:30","2018-05-15 09:30","2018-05-17 18:30","연속",null,null,null,201803050278,"-"]
[237,"경남","진주","의령S/S 의령-신마산#2T/L-TIE CB (7A00)","의령S/S 의령-신마산#2T/L-TIE CB(7A00) 정밀점검","의령S/S 의령-신마산#2T/L-TIE CB(7A00) 정밀점검","2018-05-23 09:30","2018-05-25 18:30","2018-05-23 09:30","2018-05-25 18:30","연속",null,null,null,201803050282,"-"]
[238,"경남","진주","의령S/S 고령-의령#2T/L-#2 M.Tr 1차 CB (7500)","의령S/S 고령-의령#2T/L-#2 M.Tr1차CB(7500) 정밀점검","의령S/S 고령-의령#2T/L-#2 M.Tr 1차 CB(7500) 정밀점검","2018-05-28 09:30","2018-05-30 18:30","2018-05-28 09:30","2018-05-30 18:30","연속",null,null,null,201803050290,"-"]
[239,"경남","진주","하동T/P TIE-#7 M.Tr 1차 CB (7700)","하동T/P TIE-#7M.Tr 1차 CB(7700) 개폐장치 조작시험","하동T/P TIE-#7M.Tr 1차 CB(7700) 개폐장치 조작시험 -하동T/P 7호기 정지기간 : 03.30 ~ 06.11","2018-05-10 09:30","2018-05-10 14:00","2018-05-10 09:30","2018-05-10 14:00","당일",null,null,null,201803220070,"-"]
[240,"경남","진주","하동T/P #7 M.Tr 1차 CB (7772)","하동T/P #7M.Tr 1차 CB(7772) 개폐장치 조작시험","하동T/P #7M.Tr 1차 CB(7772) 개폐장치 조작시험 -하동T/P 7호기 정지기간 : 03.30 ~ 06.11","2018-05-10 14:00","2018-05-10 18:30","2018-05-10 14:00","2018-05-10 18:30","당일",null,null,null,201803220072,"-"]
[241,"경남","진주","하동T/P TIE-#8 M.Tr 1차 CB (7800)","하동T/P TIE-#8M.Tr 1차 CB(7800) 개폐장치 조작시험","하동T/P TIE-#8M.Tr 1차 CB(7800) 개폐장치 조작시험 -하동T/P 8호기 정지기간 : 05.09 ~ 05.15","2018-05-14 09:30","2018-05-14 14:00","2018-05-14 09:30","2018-05-14 14:00","당일",null,null,null,201803220075,"-"]
[242,"경남","진주","하동T/P #8 M.Tr 1차 CB (7872)","하동T/P #8M.Tr 1차 CB(7872) 개폐장치 조작시험","하동T/P #8M.Tr 1차 CB(7872) 개폐장치 조작시험 -하동T/P 8호기 정지기간 : 05.09 ~ 05.15","2018-05-14 14:00","2018-05-14 18:30","2018-05-14 14:00","2018-05-14 18:30","당일",null,null,null,201803220076,"-"]
[243,"경남","진주","하동T/P 의령-하동TP#1T/L CB (7171)","하동T/P 의령-하동TP #1T/L CB(7171) 정밀점검","하동T/P 의령-하동TP #1T/L CB(7171) 정밀점검","2018-05-02 09:30","2018-05-04 18:30","2018-05-02 09:30","2018-05-04 18:30","연속",null,null,null,201803050271,"-"]
[244,"경남","진주","의령하동화력#2 T/L","의령-하동화력#2T/L PNL 대체 공사","의령-하동화력#2T/L PNL 대체 공사 병행 : #2F/R PNL 대체 공사","2018-05-08 08:30","2018-05-12 18:30","2018-05-08 08:30","2018-05-12 18:30","연속",null,null,null,201803050317,"-"]
[245,"경남","진주","하동T/P 광양-하동TP#1T/L CB (7371)","하동T/P 광양-하동TP #1T/L CB(7371) 정밀점검","하동T/P 광양-하동TP #1T/L CB(7371) 정밀점검","2018-05-09 09:30","2018-05-11 18:30","2018-05-09 09:30","2018-05-11 18:30","연속",null,null,null,201803050275,"-"]
[246,"경남","통영","신고성S/S #3 M.Tr A","신고성S/S 구내 전력구 공사","신고성S/S 구내 전력구 공사 관련 안전거리 이격확보","2018-05-09 08:00","2018-05-18 18:00","2018-05-09 08:00","2018-05-18 18:00","연속",null,null,null,201803060169,"-"]
[247,"경남","통영","신고성S/S #4M.Tr A","신고성S/S 구내 전력구 공사","신고성S/S 구내 전력구 공사 관련 안전거리 이격확보","2018-05-31 08:00","2018-06-07 18:00","2018-05-31 08:00","2018-06-07 18:00","연속",null,null,null,201803060170,"-"]
[248,"경남","통영","신고성S/S #2 M.Tr A","신고성S/S 구내 전력구 공사","신고성S/S 구내 전력구 공사 관련 안전거리 이격확보","2018-05-21 08:00","2018-05-30 18:00","2018-05-21 08:00","2018-05-30 18:00","연속",null,null,null,201803060168,"-"]
[249,"경남","통영","신고성S/S #1 M.Tr A","신고성S/S 구내 전력구 공사","신고성S/S 구내 전력구 공사 관련 안전거리 이격확보","2018-05-01 08:00","2018-05-08 18:00","2018-05-01 08:00","2018-05-08 18:00","연속",null,null,null,201803060163,"-"]
[250,"경남","통영","삼천포T/P #6 M.Tr 1차 CB (7671)","삼천포T/P 345kV #6GEN 2차 CB(7671) 보통점검","1. 삼천포T/P 345kV #6GEN 2차 CB(7671) 보통점검 (삼천포T/P #6호기 O/H : 05.07~05.19)","2018-05-10 09:30","2018-05-10 18:30","2018-05-10 09:30","2018-05-10 18:30","연속",null,null,null,201803260069,"-"]
[251,"경남","통영","삼천포T/P 창원#2T/L-#6 M.Tr 1차 CB (7600)","삼천포T/P 창원#2T/L-#6GEN 2차 CB(7600) 보통점검","1. 삼천포T/P 345kV 창원#2T/L-#6GEN 2차 CB(7600) 보통점검 (삼천포T/P #6호기 O/H : 05.07~05.19)","2018-05-11 09:30","2018-05-11 18:30","2018-05-11 09:30","2018-05-11 18:30","연속",null,null,null,201803260070,"-"]
[252,"경남","함안","신마산S/S #2 M.Tr A","345kV 신마산S/S 용량부족차단기 대체공사","#2M.Tr측 전력구 시공관련 안전이격거리 확보(가시설 2차 해체)","2018-05-23 09:30","2018-05-25 18:00","2018-05-23 09:30","2018-05-25 18:00","연속",null,null,null,201803080496,"-"]
[253,"경남","함안","신마산삼천포화력#1 T/L","345kV 신마산-삼천포화력T/L 접속개소 전선교체공사","68~73호, 88~95호간 전력선 교체","2018-05-14 08:00","2018-05-28 18:30","2018-05-14 08:00","2018-05-28 18:30","연속",null,null,null,201803150020,"-"]
[254,"경남","함안","신마산삼천포화력#2 T/L","345kV 신마산-삼천포화력T/L 접속개소 전선교체공사","68~73호, 88~95호간 전력선 교체","2018-05-29 08:00","2018-06-12 18:30","2018-05-29 08:00","2018-06-12 18:30","연속",null,null,null,201803050039,"-"]
[255,"전북","직할","새만금S/S #1BUS","새만금S/S 345kV Sh.R 설치공사","새만금S/S 345kV Sh.R 설치공사","2018-05-16 09:00","2018-05-21 18:00","2018-05-16 09:00","2018-05-21 18:00","연속",{"$nulls":4},"-"]
[256,"전북","직할","새만금S/S #2BUS","새만금S/S 345kV Sh.R 설치공사","새만금S/S 345kV Sh.R 설치공사","2018-05-23 09:00","2018-05-28 18:00","2018-05-23 09:00","2018-05-28 18:00","연속",{"$nulls":4},"-"]
[257,"광주전남","율촌","율촌복합GT4주변압기 CB(7100,7172)","GIS 점검 및 주변압기 점검","GIS 점검 및 주변압기 점검","2018-05-19 09:00","2018-05-21 18:00","2018-05-19 09:00","2018-05-21 18:00","연속"]
[258,"광주전남","율촌","율촌복합ST2주변압기 CB(7200,7272)","GIS 점검 및 주변압기 점검","GIS 점검 및 주변압기 점검","2018-05-16 09:00","2018-05-21 18:00","2018-05-16 09:00","2018-05-21 18:00","연속"]

{"sheet":"154송부","index":2,"n_rows":486,"n_cols":16,"rows_kept":486,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"\"2018년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2018년도 5월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","상계S/S 노원열병합T/L CB","상계S/S 170kV GIS 대체공사","170kV GIS 대체공사","2018-05-05 09:00","2018-05-30 18:00","2018-05-05 09:00","2018-05-30 18:00","연속",null,null,null,201803120558,"-"]
[2,"서울","성동","금오상계#2 T/L","2018년 성동P/O 170kV GIS 정밀점검공사","2018년 성동P/O 170kV GIS 정밀점검공사 - 6개 S/S : T/L(10), M.Tr(8), TIE(2)","2018-05-03 09:30","2018-05-04 17:30","2018-05-03 09:30","2018-05-04 17:30","연속",null,null,null,201802190178,"-"]
[3,"서울","성동","금오상계#1 T/L","2018년 성동P/O 170kV GIS 정밀점검공사","2018년 성동P/O 170kV GIS 정밀점검공사 - 6개 S/S : T/L(10), M.Tr(8), TIE(2)","2018-05-01 09:30","2018-05-02 17:30","2018-05-01 09:30","2018-05-02 17:30","연속",null,null,null,201802190169,"-"]
[4,"서울","성동","성동S/S 154kV #66 BUS","변전소 인출선로 재배치 공사","성동S/S 154kV 인출선로 재배치 공사","2018-05-23 09:30","2018-05-28 18:00","2018-05-23 09:30","2018-05-28 18:00","연속",null,null,null,201803130108,"-"]
[5,"서울","성동","성동S/S 154kV #61 BUS","변전소 인출선로 재배치 공사","성동S/S 154kV 인출선로 재배치 공사","2018-05-29 09:30","2018-06-04 18:00","2018-05-29 09:30","2018-06-04 18:00","연속",null,null,null,201803130108,"-"]
[6,"서울","성동","성동종로 T/L","변전소 인출선로 재배치 공사","성동S/S 154kV 인출선로 재배치 공사 (성동종로T/L 이설공사)","2018-05-28 09:30","2018-07-31 17:00","2018-05-23 09:30","2018-07-31 17:00","연속",null,null,null,201803130108,"-"]
[7,"서울","성동","상봉휘경#2 T/L","휘경S/S 170kV GIS 대체공사","170kV GIS 대체공사","2018-05-29 09:00","2018-06-22 18:00","2018-05-29 09:00","2018-06-22 18:00","연속",null,null,null,201803120550,"-"]
[8,"서울","중부","당인리S/S 154kV #65 BUS","당인리S/S 옥내화 공사","#1M.Tr 교체에 따른 최초가압용 BUS 활용","2018-05-12 09:00","2018-05-14 09:00","2018-05-12 09:00","2018-05-14 09:00","연속",null,null,null,201803210275,"-"]
[9,"서울","중부","당인리S/S 154kV #65 BUS","당인리S/S 옥내화 공사","#2M.Tr 교체에 따른 최초가압용 BUS 활용","2018-05-26 09:00","2018-05-28 09:00","2018-05-26 09:00","2018-05-28 09:00","연속",null,null,null,201803210276,"-"]
[10,"서울","중부","중부당인리#2 T/L","당인리S/S 옥내화 공사","#2M.Tr 교체에 따른 최초가압용 T/L 활용","2018-05-26 09:00","2018-05-28 09:00","2018-05-26 09:00","2018-05-28 09:00","연속",null,null,null,201803210277,"-"]
[11,"서울","중부","중부당인리#2 T/L","당인리S/S 옥내화 공사","#1M.Tr 교체에 따른 최초가압용 T/L 활용","2018-05-12 09:00","2018-05-14 09:00","2018-05-12 09:00","2018-05-14 09:00","연속",null,null,null,201803210278,"-"]
[12,"서울","중부","수색S/S 154kV #1 BUS","2018년 중부P/O 변전협력회사 총액공사","#4M.Tr 1차 모선LS 보통점검","2018-05-12 08:00","2018-05-12 14:00","2018-05-12 08:00","2018-05-12 14:00","당일",null,null,null,201803130109,"-"]
[13,"서울","중부","수색S/S 154kV #2 BUS","2018년 중부P/O 변전협력회사 총액공사","#4M.Tr 1차 모선LS 보통점검","2018-05-12 14:00","2018-05-12 18:00","2018-05-12 14:00","2018-05-12 18:00","당일",null,null,null,201803130110,"-"]
[14,"서울","중부","옥인운니#1 T/L","154kV 옥인 및 운니S/S 인출T/L 교체공사","1. 사업목적 : 옥인 및 운니변전소 화재 및 대형 재난사고 예방 2. 사업구간 : 옥인S/S ∼ 옥인인출전력구, 운니S/S 운니인출전력구 3. 사업내용 - 철거 : 154kV OF 2000㎟ 4C, OF 1200㎟ 4C 총길이1.4㎞ - 신설 : 154kV XLPE 2000㎟ 4C, XLPE 1200㎟ 4C 총길이1.4㎞","2018-05-11 09:00","2018-06-11 09:00","2018-05-11 09:00","2018-06-11 09:00","연속",null,null,null,201803130117,"-"]
[15,"서울","중부","중부S/S 154kV #60 BUS","2018년 중부전력지사 170kV GIS 정밀점검공사(시험가압)","중부S/S 6233 GIS 정밀점검 관련 시험가압","2018-05-11 17:00","2018-05-11 18:00","2018-05-11 17:00","2018-05-11 18:00","연속",null,null,null,201803110020,"-"]
[16,"서울","직할","불광서대문#2 T/L","18년 직할 변전협력 총액공사","조작시험, 개폐타임측정","2018-05-10 10:00","2018-05-10 18:00","2018-05-10 10:00","2018-05-10 18:00","당일",null,null,null,201803060120,"-"]
[17,"서울","직할","서대문세종로 T/L","18년 직할 변전협력 총액공사","조작시험, 개폐타임측정","2018-05-08 10:00","2018-05-08 18:00","2018-05-08 10:00","2018-05-08 18:00","당일",null,null,null,201803060118,"-"]
[18,"서울","직할","불광서대문#1 T/L","18년 직할 변전협력 총액공사","조작시험, 개폐타임측정","2018-05-09 10:00","2018-05-09 18:00","2018-05-09 10:00","2018-05-09 18:00","당일",null,null,null,201803060119,"-"]
[19,"서울","직할","순화동빙고 T/L","18년 직할 변전소 170kV GIS 정밀점검 공사","GIS 정밀점검","2018-05-16 08:00","2018-05-17 18:00","2018-05-16 08:00","2018-05-17 18:00","당일",null,null,null,201803060247,"-"]
[20,"서울","직할","신촌순화 T/L","18년 직할 변전소 170kV GIS 정밀점검 공사","정밀점검","2018-05-14 08:00","2018-05-15 18:00","2018-05-14 08:00","2018-05-15 18:00","당일",null,null,null,201803060246,"-"]
[21,"남서울","강남","대치논현#1 T/L","170kV GIS 개폐타임측정 및 조작시험","170kV GIS 개폐타임측정 및 조작시험","2018-05-29 10:00","2018-05-29 14:00","2018-05-29 10:00","2018-05-29 14:00","당일",null,null,null,201803130158,"-"]
[22,"남서울","강남","대치논현#2 T/L","170kV GIS 개폐타임측정 및 조작시험","170kV GIS 개폐타임측정 및 조작시험","2018-05-29 14:00","2018-05-29 18:00","2018-05-29 14:00","2018-05-29 18:00","당일",null,null,null,201803130159,"-"]
[23,"남서울","강남","신양재신사#3 T/L","신양재S/S 170kV GIS 정밀점검공사","신양재S/S 신양재-신사#3T/L GIS 정밀점검 신사S/S 신양재-신사#3T/L GIS 개폐타임측정","2018-05-16 10:00","2018-05-17 18:00","2018-05-16 10:00","2018-05-17 18:00","연속",null,null,null,201803130130,"-"]
[24,"남서울","강남","신양재과천#2 T/L","345kV 신양재S/S 154kV측 인출선로 재배치 공사","1. 목적 : 인출Bay 재조정을 통한 양모선 고장 시 대규모 정전방지 2. 구간 : 신양재S/S~J/B#1, 2Cx0.21km / 신양재S/S~J/B#24, 2Cx0.215km 3. 대상 : 신양재-역삼#1,2 ↔ 신양재-과천#1,2","2018-05-18 09:00","2018-06-29 18:00","2018-05-18 09:00","2018-06-29 18:00","연속",null,null,null,201803210241,"-"]
[25,"남서울","강남","신양재역삼#1 T/L","345kV 신양재S/S 154kV측 인출선로 재배치 공사","1. 목적 : 인출Bay 재조정을 통한 양모선 고장 시 대규모 정전방지 2. 구간 : 신양재S/S~J/B#1, 2Cx0.21km / 신양재S/S~J/B#24, 2Cx0.215km 3. 대상 : 신양재-역삼#1,2 ↔ 신양재-과천#1,2","2018-05-18 09:00","2018-06-29 18:00","2018-05-18 09:00","2018-06-29 18:00","연속",null,null,null,201803200037,"-"]
[26,"남서울","동서울","강동상일#1 T/L","170kV GIS 보통점검","170kV GIS 보통점검(상일), 조작시험(강동)","2018-05-03 09:00","2018-05-03 14:00","2018-05-03 09:00","2018-05-03 14:00","당일",null,null,null,201803150189,"-"]
[27,"남서울","동서울","강동상일#2 T/L","170kV GIS 보통점검","170kV GIS 보통점검(상일), 조작시험(강동)","2018-05-03 14:00","2018-05-03 18:00","2018-05-03 14:00","2018-05-03 18:00","당일",null,null,null,201803150190,"-"]
[28,"남서울","동서울","상일하남열병합#1 T/L","170kV GIS 하자점검","170kV GIS 하자점검","2018-05-04 10:00","2018-05-04 18:00","2018-05-04 10:00","2018-05-04 18:00","당일",null,null,null,201803150191,"-"]
[29,"남서울","동서울","상일하남열병합#2 T/L","170kV GIS 하자점검","170kV GIS 하자점검","2018-05-04 10:00","2018-05-04 18:00","2018-05-04 10:00","2018-05-04 18:00","당일",null,null,null,201803150192,"-"]
[30,"남서울","동서울","상일S/S 154kV #2 BUS","상일에너지센터 #3M.Tr용 GIS 설치공사","ㅇ GIS(154kV 50kA 1250A) x 1CCT 설치 ㅇ 기타 부대설비 1식","2018-05-14 09:00","2018-05-17 18:00","2018-05-14 09:00","2018-05-17 18:00","연속",null,null,null,201803080309,"-"]
[31,"남서울","동서울","상일S/S 154kV #1 BUS","상일에너지센터 #3M.Tr용 GIS 설치공사","ㅇ GIS(154kV 50kA 1250A) x 1CCT 설치 ㅇ 기타 부대설비 1식","2018-05-08 10:00","2018-05-12 18:00","2018-05-08 10:00","2018-05-12 18:00","연속",null,null,null,201803080304,"-"]
[32,"남서울","동서울","풍납석촌#2 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2018-05-16 14:00","2018-05-18 18:00","2018-05-16 14:00","2018-05-18 18:00","연속",null,null,null,201803140167,"-"]
[33,"남서울","동서울","풍납석촌#1 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2018-05-14 09:00","2018-05-16 14:00","2018-05-14 09:00","2018-05-16 14:00","연속",null,null,null,201803140166,"-"]
[34,"남서울","영등포","신광명시흥#1 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사","가공-GIS 접속, 시흥S/S 보호반교체","2018-05-08 09:00","2018-05-11 18:00","2018-05-08 09:00","2018-05-11 18:00","연속",null,null,null,201803190084,"-"]
[35,"남서울","영등포","신광명천왕#1 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사","현대화 공사","2018-05-08 09:00","2018-05-25 18:00","취소","취소","연속",null,null,null,201803190201,"-"]
[36,"남서울","영등포","신광명천왕#2 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사","현대화 공사","2018-05-28 08:00","2018-06-15 18:00","2018-05-08 08:00","2018-05-18 18:00","연속",null,null,null,201803200059,"-"]
[37,"남서울","영등포","신광명시흥#2 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사","가공-GIS 접속, 시흥S/S 보호반교체","2018-05-14 09:00","2018-05-18 18:00","2018-05-14 09:00","2018-05-18 18:00","연속",null,null,null,201803190199,"-"]
[38,"남서울","영등포","고강화곡#1 T/L","2018~19 영등포전력지사 변전협력회사 총액공사","화곡S/S 154kV 고강-화곡 #1T/L GIS 차단기 조작시험","2018-05-17 09:00","2018-05-17 14:00","2018-05-17 09:00","2018-05-17 14:00","당일",null,null,null,201803150371,"-"]
[39,"남서울","영등포","고강화곡#2 T/L","2018~19 영등포전력지사 변전협력회사 총액공사","화곡S/S 154kV 고강-화곡 #2T/L GIS 차단기 조작시험","2018-05-17 14:00","2018-05-17 18:00","2018-05-17 14:00","2018-05-17 18:00","당일",null,null,null,201803150372,"-"]
[40,"남서울","직할","봉천신길#1 T/L","신길S/S 봉천-신길#1T/L 하자점검","봉천-신길#1T/L 하자점검","2018-05-04 10:00","2018-05-04 14:00","2018-05-04 10:00","2018-05-04 14:00","당일",null,null,null,201803050010,"-"]
[41,"남서울","직할","봉천신길#2 T/L","신길S/S 봉천-신길#2T/L 차단기 조작시험","봉천-신길#2T/L 차단기 조작시험","2018-05-04 14:00","2018-05-04 18:00","2018-05-04 14:00","2018-05-04 18:00","당일",null,null,null,201803050012,"-"]
[42,"남서울","직할","신길S/S 154kV #1 BUS TIE CB","신길S/S 6100 GIS 보통점검","신길S/S 6100 GIS 보통점검","2018-05-03 10:00","2018-05-03 17:00","2018-05-03 10:00","2018-05-03 17:00","당일",null,null,null,201802280250,"-"]
[43,"인천","김포","계양김포#1 T/L","김포S/S 154kV 계양-김포#1T/L GIS 조작시험","김포S/S 154kV 계양-김포#1T/L GIS 조작시험","2018-05-17 10:00","2018-05-17 15:00","2018-05-17 10:00","2018-05-17 15:00","당일",null,null,null,201803150128,"-"]
[44,"인천","김포","김포장기#1 T/L","김포S/S 154kV 김포-장기#1T/L GIS 조작시험","김포S/S 154kV 김포-장기#1T/L GIS 조작시험","2018-05-28 10:00","2018-05-28 15:00","2018-05-28 10:00","2018-05-28 15:00","당일",null,null,null,201803150126,"-"]
[45,"인천","김포","계양김포#2 T/L","김포S/S 154kV 계양-김포#2T/L GIS 조작시험","김포S/S 154kV 계양-김포#2T/L GIS 조작시험","2018-05-18 10:00","2018-05-18 15:00","2018-05-18 10:00","2018-05-18 15:00","당일",null,null,null,201803150129,"-"]
[46,"인천","김포","김포장기#2 T/L","김포S/S 154kV 김포-장기#2T/L GIS 조작시험","김포S/S 154kV 김포-장기#2T/L GIS 조작시험","2018-05-29 10:00","2018-05-29 15:00","2018-05-29 10:00","2018-05-29 15:00","당일",null,null,null,201803150127,"-"]
[47,"인천","김포","345kV신김포S/S 154kV #1 BUS TIE GIS","신김포S/S 154kV BUS-TIE GIS 조작시험","신김포S/S 154kV BUS-TIE GIS(6100 CB) 조작시험","2018-05-23 10:00","2018-05-23 14:00","2018-05-23 10:00","2018-05-23 14:00","당일",null,null,null,201803210063,"-"]
[48,"인천","김포","신김포장기#2 T/L","신김포S/S 154kV 신김포-장기#2T/L GIS 조작시험","신김포S/S 154kV 신김포-장기#2T/L GIS 조작시험","2018-05-03 10:00","2018-05-03 15:00","2018-05-03 10:00","2018-05-03 15:00","당일",null,null,null,201803210065,"-"]
[49,"인천","김포","신김포장기#1 T/L","신김포S/S 154kV 신김포-장기#1T/L GIS 조작시험","신김포S/S 154kV 신김포-장기#1T/L GIS 조작시험","2018-05-02 10:00","2018-05-02 15:00","2018-05-02 10:00","2018-05-02 15:00","당일",null,null,null,201803210064,"-"]
[50,"인천","김포","신김포양곡#2 T/L","양곡S/S 154kV 신김포-양곡#2T/L GIS 보통점검","양곡S/S 154kV 신김포-양곡#2T/L GIS 보통점검","2018-05-12 09:00","2018-05-12 17:00","2018-05-12 09:00","2018-05-12 17:00","당일",null,null,null,201803210066,"-"]
[51,"인천","김포","양촌양곡#2 T/L","양촌S/S 154kV 양촌-양곡#2T/L GIS 보통점검","양촌S/S 154kV 양촌-양곡#2T/L GIS 보통점검","2018-05-25 10:00","2018-05-25 18:00","2018-05-25 10:00","2018-05-25 18:00","당일",null,null,null,201803150133,"-"]
[52,"인천","김포","양촌양곡#1 T/L","양촌S/S 154kV 양촌-양곡#1T/L GIS 보통점검","양촌S/S 154kV 양촌-양곡#1T/L GIS 보통점검","2018-05-24 10:00","2018-05-24 18:00","2018-05-24 10:00","2018-05-24 18:00","당일",null,null,null,201803150132,"-"]
[53,"인천","시흥","시화동시화#1 T/L","시화동시화#1T/L 접지설비 보강공사","병행지선 설치공사","2018-05-26 09:00","2018-05-26 13:00","2018-05-26 09:00","2018-05-26 13:00","당일",null,null,null,201803140121,"-"]
[54,"인천","시흥","동시화서시화 T/L","서시화S/S 동시화서시화TL GIS 정밀점검","서시화S/S 동시화서시화TL GIS 정밀점검","2018-05-30 09:00","2018-05-31 18:00","취소","취소","연속",null,null,null,201803150400,"-"]
[55,"인천","시흥","북시화서시화#3 T/L","북시화서시화#3T/L 접지설비 보강공사","접지선 규격보강공사","2018-05-25 09:00","2018-05-25 18:00","2018-05-25 09:00","2018-05-25 18:00","당일",null,null,null,201803140137,"-"]
[56,"인천","시흥","서시화S/S 154kV #2 BUS","서시화S/S 동시화서시화TL GIS 정밀점검","서시화S/S 동시화서시화TL GIS 정밀점검[무부하용]","2018-05-31 15:00","2018-05-31 18:00","취소","취소","당일",null,null,null,201803150399,"-"]
[57,"인천","시흥","북시화서시화#1 T/L","북시화서시화#1T/L 접지설비 보강공사","병행지선 설치공사","2018-05-24 09:00","2018-05-24 13:00","2018-05-24 09:00","2018-05-24 13:00","당일",null,null,null,201803140122,"-"]
[58,"인천","시흥","북시화서시화#2 T/L","북시화서시화#2T/L 접지설비 보강공사","병행지선 설치공사","2018-05-24 14:00","2018-05-24 18:00","2018-05-24 14:00","2018-05-24 18:00","당일",null,null,null,201803140123,"-"]
[59,"인천","시흥","신시흥#1S/S 154kV #66 BUS","신시흥#1S/S 154kV #64 Sh.C GIS 정밀점검","신시흥#1S/S 154kV #64 Sh.C GIS 정밀점검[무부하용]","2018-05-30 15:00","2018-05-30 18:00","2018-05-30 15:00","2018-05-30 18:00","당일",null,null,null,201803150419,"-"]
[60,"인천","시흥","신시흥#1S/S 154kV #66 BUS","신시흥#1S/S #3 M.Tr 2차 GIS 정밀점검","신시흥#1S/S #3 M.Tr 2차 GIS 정밀점검[무부하용]","2018-05-09 15:00","2018-05-09 18:00","2018-05-09 15:00","2018-05-09 18:00","당일",null,null,null,201803150404,"-"]
[61,"인천","시흥","신시흥#2S/S 154kV #62 BUS","신시흥#2S/S #4 M.Tr 2차 GIS 정밀점검","신시흥#2S/S #4 M.Tr 2차 GIS 정밀점검","2018-05-15 14:00","2018-05-16 18:00","2018-05-15 14:00","2018-05-16 18:00","연속",null,null,null,201803150409,"-"]
[62,"인천","시흥","신시흥#2S/S 154kV #63 BUS","신시흥#2S/S 154kV #6400B/T GIS 정밀점검","신시흥#2S/S 154kV #6400B/T GIS 정밀점검","2018-05-11 08:00","2018-05-11 18:00","2018-05-11 08:00","2018-05-11 18:00","연속",null,null,null,201803200276,"-"]
[63,"인천","시흥","신시흥#2S/S 154kV #67 BUS","신시흥#2S/S #4 M.Tr 2차 GIS 정밀점검","신시흥#2S/S #4 M.Tr 2차 GIS 정밀점검","2018-05-14 09:00","2018-05-15 14:00","2018-05-14 09:00","2018-05-15 14:00","연속",null,null,null,201803150408,"-"]
[64,"인천","시흥","신시흥#2S/S 154kV #4 BUS TIE GIS","신시흥#2S/S 154kV #4 BUS TIE GIS 정밀점검","신시흥#2S/S 154kV #4 BUS TIE GIS 정밀점검","2018-05-10 08:00","2018-05-11 18:00","2018-05-10 08:00","2018-05-11 18:00","연속",null,null,null,201803200277,"-"]
[65,"인천","시흥","신시흥#2S/S 154kV #68 BUS","신시흥#2S/S 154kV #6400B/T GIS 정밀점검","신시흥#2S/S 154kV #6400B/T GIS 정밀점검","2018-05-10 08:00","2018-05-11 08:00","2018-05-10 08:00","2018-05-11 08:00","연속",null,null,null,201803200275,"-"]
[66,"인천","인천","남동관교#2 T/L","관교S/S 남동관교#2T/L 보호반 대체공사","관교S/S 남동관교#2T/L 보호반 대체공사 관교S/S 남동관교#2T/L GIS 보통점검","2018-05-21 09:00","2018-05-25 18:00","2018-05-21 09:00","2018-05-25 18:00","연속",null,null,null,201803120658,"-"]
[67,"인천","인천","남동관교#1 T/L","관교S/S 남동관교#1T/L 보호반 대체공사","관교S/S 남동관교#1T/L 보호반 대체공사 관교S/S 남동관교#1T/L GIS 보통점검","2018-05-14 09:00","2018-05-18 18:00","2018-05-14 09:00","2018-05-18 18:00","연속",null,null,null,201803120657,"-"]
[68,"인천","인천","계양북인천 T/L","154kV 계양-북인천T/L 항공장애표시구 설치공사","No.11~12 등 4경간 항공구 설치","2018-05-14 08:00","2018-05-16 17:00","2018-05-14 08:00","2018-05-16 17:00","당일",null,null,null,201803140112,"-"]
[69,"인천","인천","신가좌S/S 60-61 SEC GIS","신가좌S/S 60-61-0 GIS 조작시험","신가좌S/S 60-61-0 GIS 조작시험","2018-05-25 09:00","2018-05-25 18:00","2018-05-25 09:00","2018-05-25 18:00","당일",null,null,null,201803120680,"-"]
[70,"인천","인천","신가좌S/S 154kV #1 BUS TIE GIS","신가좌S/S 6100 GIS 조작시험","신가좌S/S 6100 GIS 조작시험","2018-05-24 09:00","2018-05-24 18:00","2018-05-24 09:00","2018-05-24 18:00","당일",null,null,null,201803120678,"-"]
[71,"인천","인천","신가좌신현#1 T/L","신현S/S 170kV GIS 대체공사(3차)_#2BUS무부하","○ 신현S/S 170kV GIS 대체공사(#2M.Tr, 신현송현#1T/L, 154kV PT)_3차 ☞ #2M.Tr, 신현송현#1T/L, 154kV PT 대체 및 구 BUS-TIE 철거 ☞ 최종 무부하","2018-05-18 18:00","2018-05-19 18:00","2018-05-18 18:00","2018-05-19 18:00","연속",null,null,null,201802120024,"-"]
[72,"인천","인천","신현S/S 154kV #2 BUS","신현S/S 170kV GIS 대체공사(3차)","○ 신현S/S 170kV GIS 대체공사(#2M.Tr, 신현송현#1T/L, 154kV PT)_3차 ☞ #2M.Tr, 신현송현#1T/L, 154kV PT 대체 및 구 BUS-TIE 철거","2018-05-15 08:00","2018-05-19 18:00","2018-05-15 08:00","2018-05-19 18:00","연속",null,null,null,201802120021,"-"]
[73,"인천","인천","신현S/S 154kV #2 BUS","신현S/S 170kV GIS 대체공사(3차)","○ 신현S/S 170kV GIS 대체공사(#2M.Tr, 신현송현#1T/L, 154kV PT)_3차 ☞ #2M.Tr, 신현송현#1T/L, 154kV PT 대체 및 구 BUS-TIE 철거","2018-05-21 08:00","2018-05-24 18:00","2018-05-21 08:00","2018-05-24 18:00","연속",null,null,null,201802200241,"-"]
[74,"인천","인천","신가좌신현#1 T/L","신현S/S 170kV GIS 대체공사(3차)_최종무부하","○ 신현S/S 170kV GIS 대체공사(#2M.Tr, 신현송현#1T/L, 154kV PT)_3차 ☞ #2M.Tr, 신현송현#1T/L, 154kV PT 대체 및 구 BUS-TIE 철거 ☞ 최종 무부하","2018-05-23 18:00","2018-05-24 18:00","2018-05-23 18:00","2018-05-24 18:00","연속",null,null,null,201802200242,"-"]
[75,"인천","인천","신현S/S 154kV #1 BUS","신현S/S 170kV GIS 대체공사(3차)","○ 신현S/S 170kV GIS 대체공사(#2M.Tr, 신현송현#1T/L, 154kV PT)_3차 ☞ #2M.Tr, 신현송현#1T/L, 154kV PT 대체 및 구 BUS-TIE 철거","2018-05-25 08:00","2018-05-25 18:00","2018-05-25 08:00","2018-05-25 18:00","연속",null,null,null,201802120025,"-"]
[76,"인천","인천","신현S/S 154kV #2 BUS","신현S/S 170kV GIS 대체공사(4차)","○ 신현S/S 170kV GIS 대체공사(#1M.Tr, 신현송현#2T/L_4차 ☞ #1M.Tr, 신현송현#2T/L 대체","2018-05-26 08:00","2018-05-27 18:00","2018-05-26 08:00","2018-05-27 18:00","연속",null,null,null,201803140005,"-"]
[77,"인천","인천","신현송현#2 T/L","신현S/S 170kV GIS 대체공사(4차)","○ 신현S/S 170kV GIS 대체공사(#1M.Tr, 신현송현#2T/L_4차 ☞ #1M.Tr, 신현송현#2T/L 대체","2018-05-26 08:00","2018-06-27 18:00","2018-05-26 08:00","2018-06-27 18:00","연속",null,null,null,201803140010,"-"]
[78,"인천","인천","신현S/S 154kV #1 BUS","신현S/S 170kV GIS 대체공사(4차)","○ 신현S/S 170kV GIS 대체공사(#1M.Tr, 신현송현#2T/L_4차 ☞ #1M.Tr, 신현송현#2T/L 대체","2018-05-28 08:00","2018-05-29 18:00","2018-05-28 08:00","2018-05-29 18:00","연속",null,null,null,201803140006,"-"]
[79,"인천","인천","계양원창 T/L","154kV 계양-원창T/L 항공장애표시구 설치공사","No.11~12 등 4경간 항공구 설치","2018-05-21 08:00","2018-05-21 17:00","2018-05-21 08:00","2018-05-21 17:00","당일",null,null,null,201803140111,"-"]
[80,"인천","인천","주안만수 T/L","주안,만수S/S 주안만수T/L GIS 보통점검","주안S/S 주안만수T/L GIS 보통점검 만수S/S 주안만수T/L GIS 조작시험","2018-05-10 09:00","2018-05-10 18:00","2018-05-10 09:00","2018-05-10 18:00","당일",null,null,null,201803120647,"-"]
[81,"인천","직할","임학계양#2 T/L","154kV 임학-계양#2T/L 항공장애표시구 설치공사","No.16~17 항공구 설치","2018-05-15 08:00","2018-05-16 17:00","2018-05-15 08:00","2018-05-16 17:00","당일",null,null,null,201803140113,"-"]
[82,"인천","직할","임학계양#1 T/L","154kV 임학-계양#1T/L 항공장애표시구 설치공사","No.16~17 항공구 설치","2018-05-21 08:00","2018-05-21 17:00","2018-05-21 08:00","2018-05-21 17:00","당일",null,null,null,201803140110,"-"]
[83,"인천","직할","신가좌부개#1 T/L","154kV 신가좌-부개#1T/L 절연유 채취","OF케이블 절연유채취","2018-05-15 09:00","2018-05-17 18:00","2018-05-15 09:00","2018-05-17 18:00","연속",null,null,null,201803150173,"-"]
[84,"인천","직할","부개S/S 154kV #1 BUS","부개S/S #1M.Tr 1차 170kV GIS 정밀점검","부개S/S #1M.Tr 1차 170kV GIS 정밀점검(무부하 가압)","2018-05-30 13:00","2018-05-30 18:00","2018-05-30 13:00","2018-05-30 18:00","당일",null,null,null,201803190006,"-"]
[85,"인천","직할","신가좌부개#2 T/L","154kV 신가좌-부개#2T/L 절연유 채취","OF케이블 절연유채취","2018-05-15 09:00","2018-05-17 18:00","2018-05-15 09:00","2018-05-17 18:00","연속",null,null,null,201803150174,"-"]
[86,"인천","직할","신부평임학#2 T/L","154kV 신부평-중동 등 3개T/L 신부평변전소 인출Bay 정비공사","345kV 신부평변전소 154kV 지중T/L 인출Bay 정비(신부평S/S~J/B#1)","2018-05-23 09:00","2018-06-14 18:00","2018-06-10 09:00","2018-07-03 18:00","연속",null,null,null,201803130157,"-"]
[87,"인천","직할","신부평임학#1 T/L","신부평S/S 신부평임학#1,2T/L 170kV GIS 보통점검","신부평S/S 신부평임학#1,2T/L 170kV GIS 보통점검","2018-05-10 09:30","2018-05-10 14:00","2018-05-10 09:30","2018-05-10 14:00","당일",null,null,null,201803150061,"-"]
[88,"인천","직할","신부평부천#2 T/L","154kV 도당분기 지중T/L 건설공사","목적 : 부천지역 계통보강 선종및규격 : 154kV XLPE 2000SQ 회선수및 길이 : 4C * 0.2km 공사구간 : 신부평-부천#2T/L J/B#18 ~ 도당S/S ~ 부천S/S","2018-05-31 08:30","2018-06-29 18:00","2018-05-31 08:30","2018-06-29 18:00","연속",null,null,null,201803150030,"-"]
[89,"인천","직할","신부평중동#3 T/L","154kV 신부평-중동 등 3개T/L 신부평변전소 인출Bay 정비공사","345kV 신부평변전소 154kV 지중T/L 인출Bay 정비(신부평S/S~J/B#1)","2018-05-23 09:00","2018-06-14 18:00","2018-06-10 09:00","2018-07-03 18:00","연속",null,null,null,201803130156,"-"]
[90,"인천","직할","임학S/S 154kV #1 BUS TIE CB","임학S/S 6100 170kV GIS 보통점검","임학S/S 6100 170kV GIS 보통점검","2018-05-02 09:30","2018-05-02 18:00","2018-05-02 09:30","2018-05-02 18:00","당일",null,null,null,201803150051,"-"]
[91,"경기북부","고양","월롱금촌#1 T/L","2018년 상반기 고양전력지사 170kV GIS 정밀점검공사","금촌S/S 월롱-금촌 #1T/L(637) GIS 정밀점검","2018-05-28 09:30","2018-05-30 12:00","2018-05-28 09:30","2018-05-30 12:00","연속",null,null,null,201803070205,"-"]
[92,"경기북부","고양","월롱금촌#2 T/L","2018년 상반기 고양전력지사 170kV GIS 정밀점검공사","금촌S/S 월롱-금촌 #2T/L(647) GIS 정밀점검","2018-05-30 12:00","2018-06-01 18:00","2018-05-30 12:00","2018-06-01 18:00","연속",null,null,null,201803070207,"-"]
[93,"경기북부","고양","문발덕이#1 T/L","2018년 상반기 고양전력지사 170kV GIS 정밀점검공사","문발S/S 문발-덕이 #1T/L(667) GIS 정밀점검","2018-05-04 09:30","2018-05-05 18:00","2018-05-04 09:30","2018-05-05 18:00","연속",null,null,null,201803070209,"-"]
[94,"경기북부","고양","문발덕이#2 T/L","2018년 상반기 고양전력지사 170kV GIS 정밀점검공사","문발S/S 문발-덕이 #2T/L(677) GIS 정밀점검","2018-05-23 09:30","2018-05-24 18:00","2018-05-23 09:30","2018-05-24 18:00","연속",null,null,null,201803070211,"-"]
[95,"경기북부","고양","신파주문발#2 T/L","일진전기제 154kV 구형 PMJ접속함 교체공사(신파주문발#2T/L)","R-type 조립식 접속함 고장 지속발생에 따른 제작사 주관 리콜공사 - 공사주관 : 일진전기 - 교체대상 : 154kV 신파주-문발#2T/L J/B#1,2(총9상) - 작업팀 : 3팀 - 작업일정 : 2018. 5. 14 - 21. 끝.","2018-05-27 08:00","2018-06-03 18:00","2018-05-27 08:00","2018-06-03 18:00","연속",null,null,null,201802120143,"-"]
[96,"경기북부","고양","신파주문발#1 T/L","일진전기제 154kV 구형 PMJ접속함 교체공사(신파주문발#1T/L)","R-type 조립식 접속함 고장 지속발생에 따른 제작사 주관 리콜공사 - 공사주관 : 일진전기 - 교체대상 : 154kV 신파주-문발#1T/L J/B#1,2(총9상) - 작업팀 : 3팀 - 작업일정 : 2018. 5. 6 - 13. 끝.","2018-05-21 09:30","2018-05-27 18:00","2018-05-21 09:30","2018-05-27 18:00","연속",null,null,null,201803070212,"-"]
[97,"경기북부","고양","불광서대문#1 T/L","18년 고양전력지사 변전협력총액공사","170kV GIS 보통점검(불광-서대문#1T/L)","2018-05-09 10:00","2018-05-09 18:00","2018-05-09 10:00","2018-05-09 18:00","당일",null,null,null,201803140117,"-"]
[98,"경기북부","고양","일산S/S 154kV #2 BUS TIE GIS","18년 고양전력지사 변전협력총액공사","170kV GIS 하자점검(#2BUSTIE GIS)","2018-05-15 10:00","2018-05-15 18:00","2018-05-15 10:00","2018-05-15 18:00","당일",null,null,null,201803140129,"-"]
[99,"경기북부","고양","일산S/S 154kV #1 BUS TIE GIS","18년 고양전력지사 변전협력총액공사","170kV GIS 보통점검(#1BUSTIE GIS)","2018-05-14 10:00","2018-05-14 18:00","2018-05-14 10:00","2018-05-14 18:00","당일",null,null,null,201803140127,"-"]
[100,"경기북부","구리","미금화양 T/L","철탑형 기중종단 접속함 부분방전 진단장비 설치공사","- 대상 : 154kV 미금-화양T/L 미금C/H 3상 - 내용 : 철탑형 기중종단 접속함 부분방전 진단장비 설치 시행 - 작업자 : 2017-2018년 지중송전설비 위탁정비 회사[(주)해주전력]","2018-05-10 08:00","2018-05-10 18:00","2018-05-10 08:00","2018-05-10 18:00","당일",null,null,null,201803140004,"-"]
[101,"경기북부","구리","별내도봉 T/L","154kV 별내-도봉T/L 송전선로 정밀점검","별내-도봉T/L No.1~22 철탑 및 충전부 등 정밀점검","2018-05-29 08:00","2018-05-30 18:00","2018-05-29 08:00","2018-05-30 18:00","연속",null,null,null,201801240031,"○"]
[102,"경기북부","구리","서종청평PP#2 T/L","154kV 서종분기T/L 설비개선공사","서종변전소 인출입 철탑 4회선 동시휴전작업 - C/H 철탑 일부 주주재 교체 - No.63 ~ 65 전력선 교체","2018-05-15 07:00","2018-05-22 18:00","취소","취소","연속",null,null,"신뢰도개선",201803150219,"○"]
[103,"경기북부","구리","동서울서종#1 T/L","154kV 서종분기T/L 설비개선공사","서종변전소 인출입 철탑 4회선 동시휴전작업 - C/H 철탑 일부 주주재 교체","2018-05-15 07:00","2018-05-22 18:00","취소","취소","연속",null,null,"신뢰도개선",201803150206,"○"]
[104,"경기북부","구리","동서울서종#2 T/L","154kV 서종분기T/L 설비개선공사","서종변전소 인출입 철탑 4회선 동시휴전작업 - C/H 철탑 일부 주주재 교체","2018-05-15 07:00","2018-05-22 18:00","취소","취소","연속",null,null,"신뢰도개선",201803150211,"○"]
[105,"경기북부","구리","서종청평PP#1 T/L","154kV 서종분기T/L 설비개선공사","서종변전소 인출입 철탑 4회선 동시휴전작업 - C/H 철탑 일부 주주재 교체 - No.63 ~ 65 전력선 교체","2018-05-15 07:00","2018-05-25 18:00","취소","취소","연속",null,null,"신뢰도개선",201803150221,"○"]
[106,"경기북부","구리","신포천백학#1 T/L","신포천S/S 154kV 신포천-백학#1T/L GIS 보통점검","신포천S/S 154kV 신포천-백학#1T/L GIS 보통점검","2018-05-23 09:30","2018-05-23 18:00","2018-05-23 09:30","2018-05-23 18:00","당일",null,null,null,201803140163,"-"]
[107,"경기북부","구리","운천전곡#2 T/L","'18~'19년 직할 가공송전정비 협력회사 총액공사","154kV 운천-전곡#2T/L 불량애자교체","2018-05-29 08:00","2018-06-01 18:00","2018-05-29 08:00","2018-06-01 18:00","연속",null,null,null,201803140092,"○"]
[108,"경기북부","구리","운천전곡#1 T/L","'18~'19년 직할 가공송전정비 협력회사 총액공사","154kV 운천-전곡#1T/L 불량애자교체","2018-05-23 08:00","2018-05-28 18:00","2018-05-23 08:00","2018-05-28 18:00","연속",null,null,null,201803140091,"○"]
[109,"경기북부","구리","포천S/S 포천열병합 T/L CB","포천S/S 154kV GCB 보통점검","포천S/S 154kV GCB 보통점검","2018-05-02 09:30","2018-05-02 18:00","2018-05-02 09:30","2018-05-02 18:00","당일",null,null,null,201803210326,"-"]
[110,"경기북부","직할","신포천덕계#2 T/L","'18-19년 변전협력회사 총액공사(170kv GIS 보통점검)","덕계S/S 신포천-덕계#2T/L 보통점검","2018-05-03 09:00","2018-05-03 18:00","2018-05-03 09:00","2018-05-03 18:00","당일",null,null,null,201803210268,"-"]
[111,"경기북부","직할","신포천덕계#1 T/L","'18-19년 변전협력회사 총액공사(170kv GIS 보통점검)","덕계S/S 신포천-덕계#1T/L 보통점검","2018-05-02 09:00","2018-05-02 18:00","2018-05-02 09:00","2018-05-02 18:00","당일",null,null,null,201803210267,"-"]
[112,"경기북부","직할","신의정부S/S 154kV #3 BUS TIE GIS","18년도 변전협력회사 총액공사","GIS 개폐타임측정","2018-05-15 10:00","2018-05-15 18:00","2018-05-15 10:00","2018-05-15 18:00","당일",null,null,null,201803210222,"-"]
[113,"경기북부","직할","신의정부S/S 154kV #1 BUS TIE GIS","18년도 변전협력회사 총액공사","GIS 개폐타임측정","2018-05-14 09:00","2018-05-14 14:00","2018-05-14 09:00","2018-05-14 14:00","당일",null,null,null,201803210215,"-"]
[114,"경기북부","직할","신의정부S/S 65-66 SEC GIS","18년도 변전협력회사 총액공사","GIS 개폐타임측정","2018-05-10 14:00","2018-05-10 18:00","2018-05-10 14:00","2018-05-10 18:00","당일",null,null,null,201803210195,"-"]
[115,"경기북부","직할","신의정부S/S 66-67 SEC GIS","18년도 변전협력회사 총액공사","GIS 개폐타임측정","2018-05-11 14:00","2018-05-11 18:00","2018-05-11 14:00","2018-05-11 18:00","당일",null,null,null,201803210198,"-"]
[116,"경기북부","직할","신의정부S/S 60-61 SEC GIS","18년도 변전협력회사 총액공사","GIS 개폐타임측정","2018-05-10 09:00","2018-05-10 14:00","2018-05-10 09:00","2018-05-10 14:00","당일",null,null,null,201803210192,"-"]
[117,"경기북부","직할","신의정부금오#2 T/L","18년도 변전협력회사 총액공사","GIS 개폐타임측정","2018-05-04 14:00","2018-05-04 18:00","2018-05-08 14:00","2018-05-08 18:00","당일",null,null,null,201803210274,"-"]
[118,"경기북부","직할","신의정부금오#1 T/L","18년도 변전협력회사 총액공사","GIS 개폐타임측정","2018-05-04 10:00","2018-05-04 14:00","2018-05-08 10:00","2018-05-08 14:00","당일",null,null,null,201803210273,"-"]
[119,"경기북부","직할","신의정부S/S 61-62 SEC GIS","18년도 변전협력회사 총액공사","GIS 개폐타임측정","2018-05-11 09:00","2018-05-11 14:00","2018-05-11 09:00","2018-05-11 14:00","당일",null,null,null,201803210196,"-"]
[120,"경기북부","직할","양주S/S 154kV #61 BUS","'18년 변전협력회사 총액공사","#61 BUS CVT 보통점검","2018-05-10 09:00","2018-05-10 18:00","2018-05-10 09:00","2018-05-10 18:00","당일",null,null,null,201803120045,"-"]
[121,"경기북부","직할","양주S/S 154kV #65 BUS","'18년 변전협력회사 총액공사","#65BUS CVT 보통점검","2018-05-09 14:00","2018-05-09 18:00","2018-05-09 14:00","2018-05-09 18:00","당일",null,null,null,201803120042,"-"]
[122,"경기북부","직할","양주S/S 154kV #60 BUS","'18년 변전협력회사 총액공사","#60 BUS CVT 보통점검","2018-05-09 09:00","2018-05-09 14:00","2018-05-09 09:00","2018-05-09 14:00","당일",null,null,null,201803120039,"-"]
[123,"경기","군포","서서울율전#2 T/L","서서울S/S 154kV 취약설비 GIS화공사","서서울1변전소 서서울율전2TL 2차 GIS 월붓싱+line PT 설치 및 송전선로보호반 이설","2018-05-19 09:00","2018-05-23 18:00","취소","취소","연속",null,null,null,201801040155,"-"]
[124,"경기","군포","서서울율전#1 T/L","서서울S/S 154kV 취약설비 GIS화공사","서서울1변전소 서서울율전1TL 2차 GIS설치 및 송전선로보호반 이설","2018-05-14 09:00","2018-05-18 18:00","취소","취소","연속",null,null,null,201801040156,"-"]
[125,"경기","군포","서안양S/S 삼천리#2T/L GIS","2018년도 군포 170kV GIS 정밀점검공사","서안양S/S 삼천리#2T/L GIS 정밀점검","2018-05-17 08:00","2018-05-19 18:00","2018-05-17 08:00","2018-05-19 18:00","연속",null,null,null,201802090537,"-"]
[126,"경기","군포","서안양S/S 삼천리#1T/L GIS","2018년도 군포 170kV GIS 정밀점검공사","서안양S/S 삼천리#1T/L GIS 정밀점검","2018-05-14 08:00","2018-05-16 18:00","2018-05-14 08:00","2018-05-16 18:00","연속",null,null,null,201802090535,"-"]
[127,"경기","군포","목내안산복합#2 T/L","154kV 목내-안산복합#2T/L 맨홀내 접속함 방식층 보수공사","맨홀내 접속함 방식층 보수","2018-05-04 09:00","2018-05-04 18:00","2018-05-04 09:00","2018-05-04 18:00","당일",null,null,null,201802090276,"-"]
[128,"경기","군포","목내안산복합#1 T/L","154kV 목내-안산복합#1T/L 맨홀내 접속함 방식층 보수공사","맨홀내 접속함 방식층 보수","2018-05-03 09:00","2018-05-03 18:00","2018-05-03 09:00","2018-05-03 18:00","당일",null,null,null,201802090274,"-"]
[129,"경기","군포","안산안산복합#3 T/L","154kV 안산-안산복합#3T/L 맨홀내 접속함 방식층 보수공사","맨홀내 접속함 방식층 보수","2018-05-08 09:00","2018-05-15 18:00","2018-05-08 09:00","2018-05-15 18:00","연속",null,null,null,201802090271,"-"]
[130,"경기","군포","안산C/C 154kV #1 BUS TIE GIS","안산C/C 154kV #1BUS TIE 조작시험","안산C/C #6100 BUS TIE 조작시험","2018-05-16 09:00","2018-05-16 13:00","2018-05-16 09:00","2018-05-16 13:00","당일",null,null,null,201803120688,"-"]
[131,"경기","군포","안산C/C 154kV #2 BUS TIE GIS","안산C/C 154kV #2BUS TIE 조작시험","안산C/C #6200 BUS TIE 조작시험","2018-05-16 14:00","2018-05-16 18:00","2018-05-16 14:00","2018-05-16 18:00","당일",null,null,null,201803120689,"-"]
[132,"경기","군포","안산C/C #60-61 BUS SEC GIS","안산C/C 154kV #60-61 SEC GIS 조작시험","안산C/C #60-61 SEC GIS 조작시험","2018-05-17 09:00","2018-05-17 13:00","2018-05-17 09:00","2018-05-17 13:00","당일",null,null,null,201803120690,"-"]
[133,"경기","군포","안산C/C #65-66 BUS SEC GIS","안산C/C 154kV #65-66 SEC GIS 조작시험","안산C/C #65-66 SEC GIS 조작시험","2018-05-17 14:00","2018-05-17 18:00","2018-05-17 14:00","2018-05-17 18:00","당일",null,null,null,201803120691,"-"]
[134,"경기","군포","안양S/S 산본-안양#1T/L GIS","안양S/S 산본-안양#1T/L GIS 초기점검 공사","안양 : 산본-안양#1T/L GIS 초기점검 산본 : 산본-안양#1T/L GIS 하자점검","2018-05-29 09:00","2018-05-29 18:00","2018-05-29 09:00","2018-05-29 18:00","당일",null,null,null,201803090448,"-"]
[135,"경기","군포","안양S/S 산본-안양#2T/L GIS","안양S/S 산본-안양#2T/L GIS 초기점검 공사","안양 : 산본-안양#2T/L GIS 초기점검 산본 : 산본-안양#2T/L GIS 조작시험","2018-05-30 09:00","2018-05-30 18:00","2018-05-30 09:00","2018-05-30 18:00","당일",null,null,null,201803090451,"-"]
[136,"경기","군포","안양평촌#1 T/L","2018년도 군포 170kV GIS 정밀점검공사","평촌S/S 안양-평촌#1T/L GIS 정밀점검","2018-05-24 08:00","2018-05-26 18:00","2018-05-24 08:00","2018-05-26 18:00","연속",null,null,null,201802090528,"-"]
[137,"경기","동부","왕암가남#1 T/L","154kV 신충주-북충주T/L 건설공사","154kV 신충주- 북충주T/L&154왕암-가남T/L 병가구간 철탑 조립 및 가선 ㅇ 철탑조립 4기, 철거 3기 ㅇ 가선공사 - 왕암-가남T/L : No.49-104 - 신충주-북충주T/L No.23-72","2018-05-12 08:00","2018-09-04 18:00","2018-05-12 08:00","2018-09-04 18:00","연속",null,null,null,201803050224,"-"]
[138,"경기","동부","왕암가남#2 T/L","154kV 신충주-북충주T/L 건설공사","345kV 신충주S/S - 154kV 가남S/S 임시선로 구성 - 철탑조립 1기(왕암-가남T/L No.102 ) - 전력선 및 OPGW 가선(가철탑-왕암-가남T/L No.102 ) - 보호배전반 교체","2018-05-08 08:00","2018-05-11 18:00","2018-05-08 08:00","2018-05-11 18:00","연속",null,null,null,201803050223,"-"]
[139,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2018-05-31 09:30","2018-06-02 18:00","2018-05-31 09:30","2018-06-02 18:00","연속",null,null,null,201803200089,"-"]
[140,"경기","동부","곤지암이천#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2018-05-28 09:30","2018-05-30 18:00","2018-05-28 09:30","2018-05-30 18:00","연속",null,null,null,201803120089,"-"]
[141,"경기","동부","곤지암S/S 154kV #61 BUS","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설 - 증설: #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설: #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2018-05-28 09:30","2018-06-10 17:00","2018-05-28 09:30","2018-06-10 17:00","연속",null,null,null,201803120086,"-"]
[142,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2018-05-24 09:30","2018-05-26 17:00","2018-05-24 09:30","2018-05-26 17:00","연속",null,null,null,201803120081,"-"]
[143,"경기","동부","곤지암S/S 154kV #66 BUS","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설 - 증설: #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설: #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2018-05-21 09:30","2018-05-27 17:00","2018-05-21 09:30","2018-05-27 17:00","연속",null,null,null,201803120076,"-"]
[144,"경기","동부","곤지암S/S 154kV #1 Sh.C CB","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설 - 증설: #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설: #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2018-05-21 09:30","2018-06-29 17:00","2018-05-21 09:30","2018-06-29 17:00","연속",null,null,null,201803120096,"-"]
[145,"경기","동부","곤지암이천#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2018-05-21 09:30","2018-05-23 18:00","2018-05-21 09:30","2018-05-23 18:00","연속",null,null,null,201803120078,"-"]
[146,"경기","동부","곤지암S/S 154kV #2 BUS TIE GIS","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설 - 증설: #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설: #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2018-05-21 09:30","2018-06-24 18:00","2018-05-21 09:30","2018-06-24 18:00","연속",null,null,null,201803200001,"-"]
[147,"경기","동부","곤지암S/S 154kV #2 Sh.C CB","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설 - 증설: #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설: #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2018-05-21 09:30","2018-06-29 17:00","2018-05-21 09:30","2018-06-29 17:00","연속",null,null,null,201803120097,"-"]
[148,"경기","동부","성현산성#1 T/L","154kV 성현-산성#1T/L 규격미달 접지선 교체공사","규격미달 노후 접지선 교체 (150SQ -> 240SQ)","2018-05-09 08:00","2018-05-11 18:00","2018-05-09 08:00","2018-05-11 18:00","연속",null,null,null,201803060137,"-"]
[149,"경기","동부","성현산성#2 T/L","154kV 성현-산성#2T/L 규격미달 접지선 교체공사","규격미달 노후 접지선 교체 (150SQ → 240SQ)","2018-05-14 08:00","2018-05-16 18:00","2018-05-14 08:00","2018-05-16 18:00","연속",null,null,null,201803060139,"-"]
[150,"경기","성남","서안성S/S #1 EM.Tr(ESS) CB","서안성S/S #EM.Tr B상 하자점검","서안성S/S #EM.Tr B상 하자점검 1,2차 GIS 조작시험","2018-05-23 09:00","2018-05-23 18:00","2018-05-23 09:00","2018-05-23 18:00","당일",null,null,null,201803130268,"-"]
[151,"경기","성남","서안성남사#2 T/L","345kV 신안성-신수원 #1T/L 피뢰기 설치(안전이격휴전)","345kV 신안성-신수원 #1T/L 26호 피뢰기 설치(안전이격휴전)","2018-05-07 07:00","2018-05-07 09:00","2018-05-07 07:00","2018-05-07 09:00","당일",null,null,null,201803120317,"-"]
[152,"경기","성남","신수원S/S 154kV #65 BUS","신수원S/S 화성열병합#1T/L 정밀점검","신수원S/S 화성열병합#1T/L 정밀점검","2018-05-24 14:00","2018-05-25 18:00","2018-05-24 14:00","2018-05-25 18:00","연속",null,null,null,201803130232,"-"]
[153,"경기","성남","신수원S/S 154kV #60 BUS","신수원S/S 화성열병합#1T/L 정밀점검","신수원S/S 화성열병합#1T/L 정밀점검","2018-05-23 09:00","2018-05-24 14:00","2018-05-23 09:00","2018-05-24 14:00","연속",null,null,null,201803130231,"-"]
[154,"경기","성남","신수원화성열병#1T/L","신수원S/S 화성열병합#1T/L 정밀점검","신수원S/S 화성열병합#1T/L 정밀점검, 전자변히터","2018-05-23 09:00","2018-05-25 18:00","2018-05-23 09:00","2018-05-25 18:00","연속",null,null,null,201803130230,"-"]
[155,"경기","성남","신수원S/S 154kV #65 BUS","신수원S/S 화성열병합#2T/L 정밀점검","신수원S/S 화성열병합#2T/L 정밀점검","2018-05-17 14:00","2018-05-18 18:00","2018-05-17 14:00","2018-05-18 18:00","연속",null,null,null,201803130246,"-"]
[156,"경기","성남","신수원S/S 154kV #60 BUS","신수원S/S 화성열병합#2T/L 정밀점검","신수원S/S 화성열병합#2T/L 정밀점검","2018-05-16 09:00","2018-05-17 14:00","2018-05-16 09:00","2018-05-17 14:00","연속",null,null,null,201803130245,"-"]
[157,"경기","성남","신수원화성열병#2T/L","신수원S/S 화성열병합#2T/L 정밀점검","신수원S/S 화성열병합#2T/L 정밀점검","2018-05-16 09:00","2018-05-18 18:00","2018-05-16 09:00","2018-05-18 18:00","연속",null,null,null,201803130242,"-"]
[158,"경기","성남","신용인S/S #1 EM.Tr CB","신용인S/S ESS 23kV 모선연결공사","신용인S/S ESS 23kV 모선연결공사 #1EM.Tr 1차, 2차 GIS 조작시험","2018-05-08 09:00","2018-05-18 18:00","2018-05-08 09:00","2018-05-18 18:00","연속",null,null,null,201803130213,"-"]
[159,"경기","성남","신용인S/S 154kV #61 BUS","신용인S/S #2Sh.C 정밀점검(무부하가압)","신용인S/S #2Sh.C 정밀점검(무부하가압)","2018-05-01 09:00","2018-05-02 18:00","취소","취소","연속",null,null,null,201802270207,"-"]
[160,"경기","성남","신용인용인#2 T/L","345kV 신용인-신수원T/L등 2구간 OPGW 시설공사(화성동탄2)","공사장소 : 신용인S/S, 신안성S/S~동측C/H~서측C/H~신수원S/S 시설내역 : OPGW 120/70sq 24/48C 40.58km 비금속광케이블 24/48C 6.987km","2018-05-27 07:00","2018-05-28 18:00","2018-05-27 07:00","2018-05-28 18:00","연속",null,null,null,201803130032,"-"]
[161,"경기","성남","신용인용인#2 T/L","154kV 신용인-용인T/L No.1-2 등 6개 구간 전력선 교체공사","154kV 신용인-용인T/L No.1-2 등 6개구간 전력선 교체공사","2018-05-28 07:00","2018-06-01 18:00","2018-05-28 07:00","2018-06-01 18:00","연속",null,null,null,201803120382,"-"]
[162,"경기","성남","신용인용인#1 T/L","154kV 신용인-용인T/L No.1-2 등 6개 구간 전력선 교체공사","154kV 신용인-용인T/L No.1-2 등 6개구간 전력선 교체공사","2018-05-23 07:00","2018-05-27 18:00","2018-05-23 07:00","2018-05-27 18:00","연속",null,null,null,201803120381,"-"]
[163,"경기","성남","용인남사#1 T/L","345kV 신안성-신수원 #1T/L 피뢰기 설치(안전이격휴전)","345kV 신안성-신수원 #1T/L 26호 피뢰기 설치(안전이격휴전)","2018-05-07 07:00","2018-05-07 09:00","2018-05-07 07:00","2018-05-07 09:00","당일",null,null,null,201803120318,"-"]
[164,"경기","성남","신용인용인#2 T/L","345kV 신안성-신수원 #1T/L 피뢰기 설치(안전이격휴전)","345kV 신안성-신수원 #1T/L 46호 피뢰기 설치(안전이격휴전)","2018-05-07 11:00","2018-05-07 13:00","2018-05-07 11:00","2018-05-07 13:00","당일",null,null,null,201803120324,"-"]
[165,"경기","성남","신용인용인#1 T/L","345kV 신안성-신수원 #1T/L 피뢰기 설치(안전이격휴전)","345kV 신안성-신수원 #1T/L 47-48호 피뢰기 설치(안전이격휴전)","2018-05-07 09:00","2018-05-07 11:00","2018-05-07 09:00","2018-05-07 11:00","당일",null,null,null,201803120322,"-"]
[166,"경기","성남","용인남사#1 T/L","154kV 신용인-용인T/L No.2-4 전력선 교체공사(안전이격확보)","154kV 신용인-용인T/L No.2-4 전력선 교체공사(안전이격확보)","2018-05-26 07:00","2018-05-27 18:00","2018-05-26 07:00","2018-05-27 18:00","매일",null,null,null,201803120384,"-"]
[167,"경기","직할","조암구문천#2 T/L","345kV 아산-화성#1T/L 피뢰기 설치공사(안전확보)","No.124 피뢰기 설치 안전확보(상단 : 아산-화성)","2018-05-28 07:00","2018-05-28 12:00","2018-05-28 07:00","2018-05-28 12:00","당일",null,null,null,201803120568,"-"]
[168,"경기","직할","동수원우만#2 T/L","154kV 동수원S/S 현대화공사","ㅇ154kV 전력케이블 설치, 보호배전반 설치, 전력구 설치","2018-05-28 09:00","2018-07-31 18:00","2018-05-28 09:00","2018-07-31 18:00","연속",null,null,null,201803150032,"-"]
[169,"경기","직할","관양동안양#1 T/L","18년 직할 변전협력회사 총액공사","동안양S/S 관양동안양#1T/L GIS 보통점검","2018-05-18 10:00","2018-05-18 18:00","2018-05-18 10:00","2018-05-18 18:00","당일",null,null,null,201803130011,"-"]
[170,"경기","직할","동안양안양CC#2T/L","18년 직할 변전협력회사 총액공사","동안양S/S 안열#2/L GIS 보통점검, CB 가스누기 보수","2018-05-08 09:00","2018-05-10 18:00","2018-05-08 09:00","2018-05-10 18:00","당일",null,null,null,201803210174,"-"]
[171,"경기","직할","동안양안양CC#1T/L","18년 직할 변전협력회사 총액공사","동안양S/S 안열#1T/L GIS 보통점검","2018-05-03 09:00","2018-05-03 18:00","2018-05-03 09:00","2018-05-03 18:00","당일",null,null,null,201803210173,"-"]
[172,"경기","직할","관양동안양#2 T/L","18년 직할 변전협력회사 총액공사","동안양S/S 관양동안양#2T/L GIS 보통점검","2018-05-21 10:00","2018-05-21 18:00","2018-05-21 10:00","2018-05-21 18:00","당일",null,null,null,201803080504,"-"]
[173,"경기","직할","발안향남#2 T/L","18년 직할 154kV GCB/GIS 정밀점검공사","발안S/S 발안-향남#2T/L GIS 정밀점검공사","2018-05-14 09:00","2018-05-16 18:00","2018-05-14 09:00","2018-05-16 18:00","연속",null,null,null,201803120597,"-"]
[174,"경기","직할","발안향남#1 T/L","18년 직할 154kV GCB/GIS 정밀점검공사","발안S/S 발안-향남#1T/L GIS 정밀점검공사","2018-05-09 09:00","2018-05-11 18:00","2018-05-09 09:00","2018-05-11 18:00","연속",null,null,null,201803120592,"-"]
[175,"경기","직할","화성조암#1 T/L","345kV 아산화성T/L 전력선교체","No.136~138 #2전력선 교체관련 안전거리 확보","2018-05-26 07:00","2018-05-27 18:00","2018-05-26 07:00","2018-05-27 18:00","연속",null,null,null,201803210056,"-"]
[176,"경기","직할","화성S/S 154kV #60 BUS","18년 직할 154kV GCB/GIS 정밀점검공사","화성S/S #61M.Tr 1차 GIS 정밀점검공사(무부하가압)","2018-05-19 09:00","2018-05-19 18:00","2018-05-19 09:00","2018-05-19 18:00","당일",null,null,null,201803120626,"-"]
[177,"경기","직할","화성S/S 154kV #61 BUS","18년 직할 154kV GCB/GIS 정밀점검공사","화성S/S #62M.Tr 1차 GIS 정밀점검공사(무부하가압)","2018-05-25 09:00","2018-05-25 18:00","2018-05-25 09:00","2018-05-25 18:00","당일",null,null,null,201803120628,"-"]
[178,"경기","직할","화성S/S 154kV #67 BUS","18년 직할 154kV GCB/GIS 정밀점검공사","화성S/S #64M.Tr 1차 GIS 정밀점검공사(무부하가압)","2018-05-30 09:00","2018-05-30 18:00","2018-05-30 09:00","2018-05-30 18:00","당일",null,null,null,201803120629,"-"]
[179,"경기","직할","화성S/S 154kV #60 BUS","18년 직할 154kV GCB/GIS 정밀점검공사","화성S/S #61S.C 1차 GIS 정밀점검공사(모선DS작업)","2018-05-31 09:00","2018-06-01 14:00","2018-05-31 09:00","2018-06-01 14:00","연속",null,null,null,201803130025,"-"]
[180,"경기","평택","고덕S/S 고덕-송탄T/L CB","345kV 고덕S/S 건설공사(154kV 고덕-에어T/L 최초가압)","○ 154kV 고덕-에어T/L 최초가압에 따른 휴전 - 154kV 고덕-송탄T/L 6C7 - 154kV #66 BUS - 154kV BUS TIE 6200 CB","2018-05-12 11:00","2018-05-13 11:00","2018-05-12 11:00","2018-05-13 11:00","연속",null,null,null,201803070004,"-"]
[181,"경기","평택","삼죽만승 T/L","'18-19년도 송전정비 협력회사총액공사(항공표시구 설치)","항공표시구 설치 3경간(5EA)","2018-05-12 09:00","2018-05-13 18:00","2018-05-12 09:00","2018-05-13 18:00","매일",null,null,null,201803060061,"-"]
[182,"경기","평택","고덕송탄 T/L","154kV 송탄-오성CC T/L 14호 지장철탑이설공사","ㅁ 구간 : 기설 154㎸ 송탄-오성CC T/L NO.13~15호 ㅁ 지지물 [설치] 154㎸ 송탄-오성CC T/L 2회선-관형지지물 1기 ㅁ 전력선 [설치] 154㎸ 송탄-오성CC T/L 2회선-0.553km","2018-05-25 07:00","2018-05-28 18:00","취소","취소","연속",null,null,null,201803220161,"-"]
[183,"경기","평택","송탄오성CC T/L","154kV 송탄-오성CC T/L 14호 지장철탑이설공사","ㅁ 구간 : 기설 154㎸ 송탄-오성CC T/L NO.13~15호 ㅁ 지지물 [설치] 154㎸ 송탄-오성CC T/L 2회선-관형지지물 1기 ㅁ 전력선 [설치] 154㎸ 송탄-오성CC T/L 2회선-0.553km","2018-05-22 07:00","2018-05-24 18:00","취소","취소","연속",null,null,null,201803220160,"-"]
[184,"경기","평택","고덕송탄 T/L","지제역세권 개발 관련 지중화 본이설공사","154kV 송탄-오성복합T/L No.18~24 지중화 154kV 송탄-안성T/L No.5 이설","2018-05-09 07:00","2018-05-12 18:00","취소","취소","연속",null,null,null,201803220209,"-"]
[185,"경기","평택","송탄오성CC T/L","154kV 송탄-오성CC T/L 14호 지장철탑이설공사","ㅁ 구간 : 기설 154㎸ 송탄-오성CC T/L NO.13~15호 ㅁ 지지물 [설치] 154㎸ 송탄-오성CC T/L 2회선-관형지지물 1기 ㅁ 전력선 [설치] 154㎸ 송탄-오성CC T/L 2회선-0.553km","2018-05-29 07:00","2018-05-31 18:00","취소","취소","연속",null,null,null,201803220166,"-"]
[186,"경기","평택","송탄소사벌 T/L","지제역세권 개발 관련 지중화 본이설공사","154kV 송탄-오성복합T/L No.18~24 지중화 154kV 송탄-안성T/L No.5 이설","2018-05-04 07:00","2018-05-07 18:00","취소","취소","연속",null,null,null,201803220208,"-"]
[187,"경기","평택","송탄안성 T/L","지제역세권 개발 관련 지중화 본이설공사","154kV 송탄-오성복합T/L No.18~24 지중화 154kV 송탄-안성T/L No.5 이설","2018-05-09 07:00","2018-05-11 18:00","취소","취소","연속",null,null,null,201803220210,"-"]
[188,"경기","평택","송탄오성CC T/L","지제역세권 개발 관련 지중화 본이설공사","154kV 송탄-오성복합T/L No.18~24 지중화 154kV 송탄-안성T/L No.5 이설","2018-05-01 07:00","2018-05-08 18:00","취소","취소","연속",null,null,null,201803220206,"-"]
[189,"경기","평택","송탄안성 T/L","지제역세권 개발 관련 지중화 본이설공사","154kV 송탄-오성복합T/L No.18~24 지중화 154kV 송탄-안성T/L No.5 이설","2018-05-01 07:00","2018-05-03 18:00","취소","취소","연속",null,null,null,201803220207,"-"]
[190,"경기","평택","서안성안성#2 T/L","154kV 서운-안성T/L 전력선교체공사(안전확보)","- 공사구간 : No.2~6(4회선구간 상단), 17~21 - 공사내용 : 전선접속개소 전력선교체","2018-05-05 07:00","2018-05-07 18:00","2018-05-05 07:00","2018-05-07 18:00","매일",null,null,null,201803200200,"-"]
[191,"경기","평택","서안성안성#1 T/L","154kV 서운-안성T/L 전력선교체공사(안전확보)","- 공사구간 : No.2~6(4회선구간 상단), 17~21 - 공사내용 : 전선접속개소 전력선교체","2018-05-02 07:00","2018-05-04 18:00","2018-05-02 07:00","2018-05-04 18:00","매일",null,null,null,201803200199,"-"]
[192,"경기","평택","송탄안성 T/L","안성S/S 170kV GIS 용량대체공사","송탄-안성T/L GIS 철거 및 설치","2018-05-01 09:30","2018-05-19 18:00","취소","취소","연속",null,null,null,201803090422,"-"]
[193,"경기","평택","안성S/S 154kV #65 BUS","안성S/S 170kV GIS 용량대체공사","송탄-안성T/L GIS 대체 - #2BUS측 DS 철거","2018-05-01 09:30","2018-05-02 09:30","취소","취소","연속",null,null,null,201803090417,"-"]
[194,"경기","평택","안성S/S 154kV #60 BUS","안성S/S 170kV GIS 용량대체공사","송탄-안성T/L GIS 대체 - #1DS, T/L 철거 및 설치","2018-05-02 09:30","2018-05-11 09:30","취소","취소","연속",null,null,null,201803090425,"-"]
[195,"경기","평택","안성S/S 154kV #65 BUS","안성S/S 170kV GIS 용량대체공사","송탄-안성T/L GIS 대체 - #2BUS 철거 및 설치 - 준공시험","2018-05-11 09:30","2018-05-18 18:00","취소","취소","연속",null,null,null,201803090426,"-"]
[196,"경기","평택","서안성안성#1 T/L","안성S/S 170kV GIS 용량대체공사","송탄-안성T/L GIS 무부하가압","2018-05-18 18:00","2018-05-19 18:00","취소","취소","연속",null,null,null,201803090427,"-"]
[197,"경기","평택","서운안성#1 T/L","안성S/S 170kV GIS 용량대체공사","서운-안성#1T/L GIS 철거 및 설치","2018-05-23 09:30","2018-06-16 18:00","2018-05-23 09:30","2018-06-16 18:00","연속",null,null,null,201803090434,"-"]
[198,"경기","평택","안성S/S 154kV #66 BUS","안성S/S 170kV GIS 용량대체공사","서운-안성#1T/L GIS 대체 - #2BUS측 DS 철거","2018-05-23 09:30","2018-05-24 09:30","2018-05-23 09:30","2018-05-24 09:30","연속",null,null,null,201803090435,"-"]
[199,"경기","평택","안성S/S 154kV #61 BUS","안성S/S 170kV GIS 용량대체공사","서운-안성#1T/L GIS 대체 - #1DS, T/L 철거 및 설치","2018-05-24 09:30","2018-06-04 09:30","2018-05-24 09:30","2018-06-04 09:30","연속",null,null,null,201803090436,"-"]
[200,"경기","평택","오산향남#1 T/L","오산S/S 오산-향남#1T/L GIS CB 조작시험","오산S/S 오산-향남#1T/L GIS CB 조작시험","2018-05-08 10:00","2018-05-08 18:00","2018-05-08 10:00","2018-05-08 18:00","당일",null,null,null,201803130072,"-"]
[201,"경기","평택","평택추팔#1 T/L","추팔S/S 평택-추팔 #1T/L GIS CB 조작시험","추팔S/S 평택-추팔 #1T/L GIS CB 조작시험 / 평택S/S 평택-추팔 #1T/L GIS CB 조작시험","2018-05-06 09:00","2018-05-06 18:00","2018-05-06 09:00","2018-05-06 18:00","당일",null,null,null,201803130080,"-"]
[202,"경기","평택","평택추팔#2 T/L","추팔S/S 평택-추팔 #2T/L GIS CB 조작시험","추팔S/S 평택-추팔 #2T/L GIS CB 조작시험 / 평택S/S 평택-추팔 #2T/L GIS CB 조작시험","2018-05-07 09:00","2018-05-07 18:00","2018-05-07 09:00","2018-05-07 18:00","당일",null,null,null,201803130081,"-"]
[203,"경기","평택","포승평택TP#1 T/L","18년 평택전력지사 170kV GIS 정밀점검공사","18년 평택전력지사 170kV GIS 정밀점검공사 / 평택T/P 포승-평택T/P #1T/L GIS 정밀점검 / 포승S/S 포승-평택T/P #1T/L GIS CB 조작시험","2018-05-25 09:00","2018-05-27 18:00","2018-05-25 09:00","2018-05-27 18:00","연속",null,null,null,201803210039,"-"]
[204,"경기","평택","원정평택T/P#2 T/L","18년 평택전력지사 170kV GIS 정밀점검공사","18년 평택전력지사 170kV GIS 정밀점검공사 / 평택T/P 원정-평택T/P #2T/L GIS 정밀점검 / 원정S/S 원정-평택T/P #2T/L GIS CB 조작시험","2018-05-18 09:00","2018-05-20 18:00","2018-05-18 09:00","2018-05-20 18:00","연속",null,null,null,201803210038,"-"]
[205,"경기","평택","원정평택T/P#1 T/L","18년 평택전력지사 170kV GIS 정밀점검공사","18년 평택전력지사 170kV GIS 정밀점검공사 / 평택T/P 원정-평택T/P #1T/L GIS 정밀점검 / 원정S/S 원정-평택T/P #1T/L GIS CB 조작시험","2018-05-11 09:00","2018-05-13 18:00","2018-05-11 09:00","2018-05-13 18:00","연속",null,null,null,201803210036,"-"]
[206,"경기","평택","평택T/P 154kV #60 BUS","18년 평택전력지사 170kV GIS 정밀점검공사","18년 평택전력지사 170kV GIS 정밀점검공사 / 평택T/P 원정-평택T/P #1T/L GIS 정밀점검 무부하가압","2018-05-12 09:00","2018-05-13 18:00","2018-05-12 09:00","2018-05-13 18:00","연속",null,null,null,201803210041,"-"]
[207,"경기","평택","평택T/P 154kV #60 BUS","18년 평택전력지사 170kV GIS 정밀점검공사","18년 평택전력지사 170kV GIS 정밀점검공사 / 평택T/P 포승-평택T/P #1T/L GIS 정밀점검 무부하가압","2018-05-26 09:00","2018-05-27 18:00","2018-05-26 09:00","2018-05-27 18:00","연속",null,null,null,201803210040,"-"]
[208,"경기","평택","평택T/P 154kV #61 BUS","18년 평택전력지사 170kV GIS 정밀점검공사","18년 평택전력지사 170kV GIS 정밀점검공사 / 평택T/P 원정-평택T/P #2T/L GIS 정밀점검 무부하가압","2018-05-19 09:00","2018-05-20 18:00","2018-05-19 09:00","2018-05-20 18:00","연속",null,null,null,201803210042,"-"]
[209,"경기","평택","포승청북 T/L","154kV 포승-청북T/L 전력선 교체공사","No.32~39 전력선교체(1섹션)","2018-05-14 07:00","2018-05-17 18:00","2018-05-14 07:00","2018-05-17 18:00","연속",null,null,null,201803120557,"-"]
[210,"강원","강릉","영동TP강릉 T/L","154kV 강릉S/S 인출 송전선로 지중화공사","- (신설)No.36~강릉S/S간 송전선로 인출구간 지중화","2018-05-13 08:00","2018-06-14 18:00","2018-05-13 08:00","2018-06-14 18:00","연속",null,null,null,201803210060,"-"]
[211,"강원","강릉","동해강릉T/L","154kV 강릉S/S 인출 송전선로 지중화공사","- (신설)No.36~강릉S/S간 송전선로 인출구간 지중화 : 154kV 영동T/P-강릉#2T/L 지중 케이블 포설시 안전거리 확보","2018-05-17 08:00","2018-05-26 18:00","2018-05-17 08:00","2018-05-26 18:00","매일",null,null,null,201803210035,"-"]
[212,"강원","강릉","강릉북강릉#2 T/L","154kV 강릉S/S 옥내화 잔여공사","송전선로보호반 대체 x 1식 기타부대공사","2018-05-10 09:00","2018-05-31 18:00","2018-05-10 09:00","2018-05-31 18:00","연속",null,null,null,201801120354,"-"]
[213,"강원","동해","동해동영월 T/L","2018~19년도 동해전력지사 송전정비협력회사 총액공사","○ No.151~155 전선접속개소 전선교체공사","2018-05-08 08:00","2018-05-13 18:00","2018-05-08 08:00","2018-05-13 18:00","연속",null,null,"신뢰도개선",201803120136,"-"]
[214,"강원","동해","동해정선 T/L","2018~19년도 동해전력지사 송전정비협력회사 총액공사","○ No.151~155 전선접속개소 전선교체공사","2018-05-14 08:00","2018-05-18 18:00","2018-05-14 08:00","2018-05-18 18:00","연속",null,null,"신뢰도개선",201803120140,"-"]
[215,"강원","동해","북평영동TP#1 T/L","2018년 동해전력지사 154kV GIS 정밀점검공사(북평)","1. 북평S/S 북평-영동TP#1T/L GIS 정밀점검(697)","2018-05-14 09:30","2018-05-16 18:00","2018-05-14 09:30","2018-05-16 18:00","연속",null,null,null,201803060266,"-"]
[216,"강원","동해","북평영동TP#2 T/L","2018년 동해전력지사 154kV GIS 정밀점검공사(북평)","1. 북평S/S 북평-영동TP#2T/L GIS 정밀점검(6A7)","2018-05-17 09:30","2018-05-19 18:00","2018-05-17 09:30","2018-05-19 18:00","연속",null,null,null,201803060267,"-"]
[217,"강원","동해","삼척동해TP T/L","154kV 삼척-동해TPT/L OPGW 교체공사","154kV 삼척-동해TPT/L OPGW교체","2018-05-14 08:00","2018-05-22 18:00","2018-05-14 08:00","2018-05-22 18:00","연속",null,null,null,201803120149,"-"]
[218,"강원","동해","이원태백 T/L","154kV 태원T/L OPGW 교체공사","No.76~82 OPGW교체","2018-05-10 08:00","2018-05-11 18:00","2018-05-10 08:00","2018-05-11 18:00","연속",null,null,null,201803120148,"O"]
[219,"강원","원주","홍천상남#1 T/L","2018년 원주전력 변전협력회사 총액공사","홍천S/S 170kV GIS 초기점검 상남S/S 피뢰기 보통, GIS 절연볼트 교체","2018-05-16 09:00","2018-05-17 17:00","2018-05-16 09:00","2018-05-17 17:00","매일",null,null,null,201803120121,"-"]
[220,"강원","직할","북춘천춘천HP T/L","2018~2019년 강원직할 송전정비 협력회사 총액공사","- 전선접속개소 해소공사 - 피뢰기 설치 - OPGW 교체","2018-05-28 07:30","2018-06-02 18:00","2018-05-28 07:30","2018-06-02 18:00","연속",null,null,null,201803110013,"O"]
[221,"강원","직할","북춘천화천HP T/L","2018~2019년 강원직할 송전정비 협력회사 총액공사","- 전선접속개소 해소공사","2018-05-26 07:30","2018-05-27 18:00","2018-05-26 07:30","2018-05-27 18:00","연속",null,null,null,201803110012,"O"]
[222,"강원","직할","상남인제#1 T/L","2018~2019년 강원직할 송전정비 협력회사 총액공사","- 전선접속개소 해소공사 - 정밀점검","2018-05-02 07:30","2018-05-04 18:00","2018-05-02 07:30","2018-05-04 18:00","연속",null,null,null,201803110005,"-"]
[223,"강원","직할","상남인제#2 T/L","2018~2019년 강원직할 송전정비 협력회사 총액공사","- 전선접속개소 해소공사 - 정밀점검","2018-05-05 07:30","2018-05-10 18:00","2018-05-05 07:30","2018-05-10 18:00","연속",null,null,null,201803110006,"-"]
[224,"강원","직할","남춘천춘천 T/L","2018~2019년 강원직할 송전정비 협력회사 총액공사","- 전선접속개소 해소공사","2018-05-20 07:30","2018-05-22 18:00","2018-05-20 07:30","2018-05-22 18:00","연속",null,null,null,201803110009,"-"]
[225,"강원","직할","춘천소양강HP T/L","2018~2019년 강원직할 송전정비 협력회사 총액공사","- 전선접속개소 해소공사 - 정밀점검","2018-05-23 07:30","2018-05-25 18:00","2018-05-23 07:30","2018-05-25 18:00","연속",null,null,null,201803110011,"-"]
[226,"강원","태백","태백고한 T/L","송전선로 정밀점검","전선 및 금구류 교체작업 및 정밀점검","2018-05-02 09:00","2018-05-05 18:00","2018-05-02 09:00","2018-05-05 18:00","연속",null,null,null,201803090295,"-"]
[227,"강원","태백","고한영월 T/L","송전선로 정밀점검","전선 및 금구류 교체작업 및 정밀점검","2018-05-08 09:00","2018-05-13 18:00","2018-05-08 09:00","2018-05-13 18:00","연속",null,null,null,201803090309,"-"]
[228,"강원","태백","영월_영월CC T/L","170kV GIS 정밀점검","170kV GIS CB 및 DS 정밀점검","2018-05-14 09:00","2018-05-19 18:00","2018-05-14 09:00","2018-05-19 18:00","연속",null,null,null,201803090344,"-"]
[229,"강원","태백","태백영월 T/L","송전선로 정밀점검","전선 및 금구류 교체작업 및 정밀점검","2018-05-14 09:00","2018-05-20 18:00","2018-05-14 09:00","2018-05-20 18:00","연속",null,null,null,201803120312,"-"]
[230,"충북","직할","왕암북충주#2 T/L","154kV 왕암-북충주T/L 전력선교체공사","- 전력선교체 : 13~18 등 9구간 전력선 교체","2018-05-09 07:00","2018-05-25 18:00","2018-05-09 07:00","2018-05-25 18:00","연속",null,null,null,201802080026,"-"]
[231,"충북","직할","왕암북충주#1 T/L","154kV 왕암-북충주T/L 전력선교체공사","- 전력선교체 : 13~18 등 9구간 전력선 교체","2018-05-26 07:00","2018-06-11 18:00","2018-05-26 07:00","2018-06-11 18:00","연속",null,null,null,201802080028,"-"]
[232,"충북","직할","제천영월#2 T/L","154kV 제천-영월T/L No.52 취약철탑 교체공사","2기 철거, 2기 신설 (No.51,52 )","2018-05-26 09:00","2018-05-31 18:00","2018-05-26 09:00","2018-05-31 18:00","연속",null,null,null,201803070244,"-"]
[233,"충북","직할","제천영월#2 T/L","154kV 제천-영월T/L No.52 취약철탑 교체공사","2기 철거, 2기 신설 (No.51,52 )","2018-05-16 09:00","2018-05-18 18:00","2018-05-16 09:00","2018-05-18 18:00","연속",null,null,null,201803070243,"-"]
[234,"충북","직할","제천영월#1 T/L","154kV 제천-영월T/L No.52 취약철탑 교체공사","2기 철거, 2기 신설 (No.51,52 )","2018-05-19 09:00","2018-05-25 18:00","2018-05-19 09:00","2018-05-25 18:00","연속",null,null,null,201803070245,"-"]
[235,"충북","청주","오송북청주#1 T/L","154kV 국사-봉명T/L 지장철탑이설공사","1. 사유 : 청주테크노폴리스 산업단지 조성에 따른 철탑 이설 2. 공사개요 ○ 이설구간 : 154kV 국사­봉명T/L 14~17, 20~23호간 (준공 1994년) ○ 이설개요 : : 4회선 철탑 4기(15,16,21,22), 전력선 4.072C-km 교체 3. 작업내용 : 철탑설치 및 가선","2018-05-28 08:00","2018-05-31 18:00","2018-05-28 08:00","2018-05-31 18:00","연속",null,null,null,201803090083,"-"]
[236,"충북","충주","서운만승 T/L","154kV 서운-만승 등 2개T/L 전력선교체공사","서운-만승T/L No.81~83(진천-만승 #1T/L No.35~37) 전력선교체","2018-05-11 07:00","2018-05-15 18:00","2018-05-11 07:00","2018-05-15 18:00","연속",null,null,null,201803160009,"○"]
[237,"충북","충주","진천S/S 진천-만승#2T/L GIS","2018년도 15kV GIS 정밀점검","2018년도 15kV GIS 정밀점검","2018-05-30 10:00","2018-05-31 18:00","2018-05-30 10:00","2018-05-31 18:00","연속",null,null,null,201803070314,"○"]
[238,"충북","충주","진천만승#1 T/L","154kV 서운-만승 등 2개T/L 전력선교체공사","서운-만승T/L No.81~83(진천-만승 #1T/L No.35~37) 전력선교체","2018-05-11 07:00","2018-05-15 18:00","2018-05-11 07:00","2018-05-15 18:00","연속",null,null,null,201803160010,"○"]
[239,"충북","충주","진천덕산#1T/L","2018년도 15kV GIS 정밀점검","2018년도 15kV GIS 정밀점검","2018-05-08 10:00","2018-05-09 18:00","2018-05-08 10:00","2018-05-09 18:00","연속",null,null,null,201803070317,"○"]
[240,"충북","충주","진천덕산#2T/L","2018년도 15kV GIS 정밀점검","2018년도 15kV GIS 정밀점검","2018-05-18 10:00","2018-05-19 18:00","2018-05-18 10:00","2018-05-19 18:00","연속",null,null,null,201803070319,"○"]
[241,"충북","충주","진천S/S 154kV BUS TIE GIS","2018년도 15kV GIS 정밀점검","2018년도 15kV GIS 정밀점검","2018-05-03 10:00","2018-05-04 18:00","2018-05-03 10:00","2018-05-04 18:00","연속",null,null,null,201803070312,"○"]
[242,"충북","충주","충주풍동 T/L","2018-19년 송전정비 협력회사 총액공사","전력선 교체 (154kV 충주풍동T/L No.58-59)","2018-05-22 08:00","2018-05-24 18:00","2018-05-22 08:00","2018-05-24 18:00","연속",null,null,null,201803050054,"○"]
[243,"대전충남","대전","신옥천남대전#3 T/L","남대전S/S 154kV 신옥천-남대전#3T/L GIS 정밀점검 및 병행","남대전S/S 154kV 신옥천-남대전#3T/L GIS 정밀점검 및 병행작업","2018-05-01 09:00","2018-05-02 18:00","2018-05-01 09:00","2018-05-02 18:00","연속",null,null,null,201803200137,"-"]
[244,"대전충남","대전","신옥천남대전#4 T/L","남대전S/S 154kV 신옥천-남대전#4T/L GIS 정밀점검 및 병행","남대전S/S 154kV 신옥천-남대전#4T/L GIS 정밀점검 및 병행작업","2018-05-03 09:00","2018-05-04 18:00","2018-05-03 09:00","2018-05-04 18:00","연속",null,null,null,201803200139,"-"]
[245,"대전충남","서산","대산석문#1 T/L","154kV 대산-석문#1T/L 전력선 교체공사","154kV 대산-석문#1T/L 2~3호 등 6개 구간전력선 교체공사","2018-05-09 08:00","2018-05-17 18:00","2018-05-09 08:00","2018-05-17 18:00","연속",null,null,null,201803090277,"-"]
[246,"대전충남","서산","대산석문#2 T/L","154kV 대산-석문#2T/L 전력선 교체공사","154kV 대산-석문#2T/L 2~3호 등 6개 구간전력선 교체공사","2018-05-18 08:00","2018-05-23 18:00","2018-05-18 08:00","2018-05-23 18:00","연속",null,null,null,201803090280,"-"]
[247,"대전충남","서산","석문당진화력#2 T/L","154kV 석문-당진화력T/L 전력선 교체공사","21~22호 전력선 교체공사","2018-05-03 09:00","2018-05-04 18:00","2018-05-03 09:00","2018-05-04 18:00","연속",null,null,null,201803090286,"-"]
[248,"대전충남","서산","석문당진화력#1 T/L","154kV 석문-당진화력T/L 전력선 교체공사","21~22호 전력선 교체공사","2018-05-01 09:00","2018-05-02 18:00","2018-05-01 09:00","2018-05-02 18:00","연속",null,null,null,201803160189,"-"]
[249,"대전충남","세종","덕진송강#2 T/L","[변전] 154kV 장기 미동작 차단기 조작시험","○ 장기 미동작 차단기 조작시험","2018-05-03 13:00","2018-05-03 15:00","2018-05-03 13:00","2018-05-03 15:00","당일",null,null,null,201803090416,"-"]
[250,"대전충남","세종","덕진송강#1 T/L","[변전] 154kV 장기 미동작 차단기 조작시험","○ 장기 미동작 차단기 조작시험","2018-05-03 09:00","2018-05-03 12:00","2018-05-03 09:00","2018-05-03 12:00","당일",null,null,null,201803090414,"-"]
[251,"대전충남","세종","세종서세종#2 T/L","[변전] 18년 변전협력업체 총액공사","○ GIS 하자점검 (양단)","2018-05-01 09:00","2018-05-01 18:00","2018-05-01 09:00","2018-05-01 18:00","당일",null,null,null,201803090385,"-"]
[252,"대전충남","세종","월산서세종 T/L","[변전] 18년 변전협력업체 총액공사","○ GIS 하자점검 (양단) ○ Airing Valve 누기 점검(월산)","2018-05-02 09:00","2018-05-02 18:00","2018-05-02 09:00","2018-05-02 18:00","당일",null,null,null,201803090386,"-"]
[253,"대전충남","아산","아산S/S 154kV #66 BUS","아산S/S 154kV #62M.Tr 1차 장기사용 GIS 교체공사","아산S/S 154kV #62M.Tr 1차 장기사용 GIS 교체공사","2018-05-27 09:00","2018-06-01 18:00","2018-05-27 09:00","2018-06-01 18:00","연속",null,null,null,201803120555,"-"]
[254,"대전충남","아산","아산S/S 154kV #61 BUS","아산S/S 154kV #62M.Tr 1차 장기사용 GIS 교체공사","아산S/S 154kV #62M.Tr 1차 장기사용 GIS 교체공사","2018-05-23 09:00","2018-05-26 18:00","2018-05-23 09:00","2018-05-26 18:00","연속",null,null,null,201803120551,"-"]
[255,"대전충남","아산","장재S/S 주공#2T/L CB","장재S/S 154kV 주공#2T/L GIS 점밀점검","○ 장재S/S 154kV 주공#2T/L GIS 점밀점검","2018-05-16 09:00","2018-05-17 18:00","2018-05-16 09:00","2018-05-17 18:00","연속",null,null,null,201803120538,"-"]
[256,"대전충남","아산","풍세장재#2 T/L","풍세,장재S/S 154kV 풍세-장재#2T/L 보호배전반 대체","○ 풍세,장재S/S 154kV 풍세-장재#2T/L 보호배전반 대체","2018-05-14 09:00","2018-05-17 18:00","2018-05-14 09:00","2018-05-17 18:00","연속",null,null,null,201803120566,"-"]
[257,"대전충남","아산","풍세장재#1 T/L","풍세,장재S/S 154kV 풍세-장재#1T/L 보호배전반 교체","○ 풍세,장재S/S 154kV 풍세-장재#1T/L 보호배전반 교체","2018-05-08 09:00","2018-05-11 18:00","2018-05-08 09:00","2018-05-11 18:00","연속",null,null,null,201803120517,"-"]
[258,"대전충남","직할","신탄진대청HP T/L","170kV GIS 정밀점검공사","GCB 정밀점검","2018-05-23 08:00","2018-05-24 18:00","2018-05-23 08:00","2018-05-24 18:00","연속",null,null,null,201803060085,"-"]
[259,"대전충남","청양","관창보령복합 T/L","154kV 보관T/L 전력선 교체공사","○ 교체길이 : 7개 구간 6.343[C-km] ○ 스페이서 교체 : 575개 ○ SB댐퍼 교체 : 322개 ○ 구형부식 애자장치 교체 : 18기 96련 ○ 기타부대공사","2018-05-03 07:00","2018-05-10 18:00","2018-05-03 07:00","2018-05-10 18:00","연속",null,null,null,201802090004,"-"]
[260,"전북","군산","군공S/S 154kV #1 BUS","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 군공-내초#1T/L 차단기 정밀점검(모선단로기 포함)","2018-05-08 09:00","2018-05-09 14:00","2018-05-08 09:00","2018-05-09 14:00","연속",null,null,null,201803200026,"-"]
[261,"전북","군산","군공내초#2 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 군공-내초#2T/L 차단기 정밀점검(모선단로기 포함)","2018-05-14 09:00","2018-05-16 18:00","취소","취소","연속",null,null,null,201803200031,"-"]
[262,"전북","군산","군공S/S 154kV #2 BUS","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 군공-내초#1T/L 차단기 정밀점검(모선단로기 포함)","2018-05-09 14:00","2018-05-10 18:00","2018-05-09 14:00","2018-05-10 18:00","연속",null,null,null,201803200028,"-"]
[263,"전북","군산","군공내초#1 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 군공-내초#1T/L 차단기 정밀점검(모선단로기 포함)","2018-05-08 09:00","2018-05-10 18:00","취소","취소","연속",null,null,null,201803200021,"-"]
[264,"전북","군산","군공S/S 154kV #1 BUS","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 군공-내초#2T/L 차단기 정밀점검(모선단로기 포함)","2018-05-14 09:00","2018-05-15 14:00","2018-05-14 09:00","2018-05-15 14:00","연속",null,null,null,201803200032,"-"]
[265,"전북","군산","군공S/S 154kV #2 BUS","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 군공-내초#2T/L 차단기 정밀점검(모선단로기 포함)","2018-05-15 14:00","2018-05-16 18:00","2018-05-15 14:00","2018-05-16 18:00","연속",null,null,null,201803200033,"-"]
[266,"전북","군산","군공S/S 154kV #2 BUS","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 군공-소룡#2T/L 차단기 정밀점검(모선단로기 포함)","2018-05-03 14:00","2018-05-04 18:00","2018-05-03 14:00","2018-05-04 18:00","연속",null,null,null,201803200020,"-"]
[267,"전북","군산","군공S/S 154kV #1 BUS","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 군공-소룡#2T/L 차단기 정밀점검(모선단로기 포함)","2018-05-02 09:00","2018-05-03 14:00","2018-05-02 09:00","2018-05-03 14:00","연속",null,null,null,201803200019,"-"]
[268,"전북","군산","군공소룡#2 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 군공-소룡#2T/L 차단기 정밀점검(모선단로기 포함)","2018-05-02 09:00","2018-05-04 18:00","2018-05-02 09:00","2018-05-04 18:00","연속",null,null,null,201803200018,"-"]
[269,"전북","군산","군공군산복합#1 T/L","군공-군산복합#1T/L 보호배전반 대체공사","군공-군산복합#1T/L 보호배전반 대체공사","2018-05-28 09:00","2018-06-01 18:00","2018-05-28 09:00","2018-06-01 18:00","연속",null,null,null,201803220009,"-"]
[270,"전북","군산","군공S/S 154kV #2 BUS","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S #4M.Tr 1차 차단기 정밀점검","2018-05-18 16:00","2018-05-18 18:00","2018-05-18 16:00","2018-05-18 18:00","연속",null,null,null,201803200076,"-"]
[271,"전북","군산","군공내초#2 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S #4M.Tr 1차 차단기 정밀점검","2018-05-18 16:00","2018-05-18 18:00","취소","취소","연속",null,null,null,201803200077,"-"]
[272,"전북","군산","동군산군산CC#2 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군산복합S/Y 동군산-군산복합 #2T/L 차단기 정밀점검","2018-05-26 09:00","2018-05-27 18:00","취소","취소","연속",null,null,null,201803200078,"-"]
[273,"전북","군산","군산복합S/Y 동군산-군산복합 #1T/L CB","군산P/O 154kV이상 차단기 조작시험","차단기 조작시험","2018-05-13 09:00","2018-05-13 12:00","취소","취소","당일",null,null,null,201803150045,"-"]
[274,"전북","군산","동군산장항#2 T/L","군산PO 차단기 점검공사","1. 동군산S/S 동군산-장항#2T/L GIS 초기점검(군산PO 이병주) 2. 장항S/S 동군산-장항#2T/L 차단기 조작시험(청양PO 주규철)","2018-05-23 10:00","2018-05-23 14:00","2018-05-23 10:00","2018-05-23 14:00","당일",null,null,null,201803200050,"-"]
[275,"전북","군산","군공소룡#1 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","소룡S/S 군공-소룡 #1T/L 차단기 정밀점검","2018-05-30 09:00","2018-05-31 18:00","2018-05-30 09:00","2018-05-31 18:00","연속",null,null,null,201803200079,"-"]
[276,"전북","군산","군산영등#1 T/L","군산영등T/L 전선접속개소교체공사","○ 전선접속개소 해소공사 - 154kV 군산-영등T/L : No.32~33 (0.279 C-km), No.48~49(0.532 C-km) - 154kV 함열-영등T/L : No.8~9","2018-05-08 07:00","2018-05-10 18:00","취소","취소","연속",null,null,null,201803090270,"-"]
[277,"전북","군산","군산영등#2 T/L","군산영등T/L 전선접속개소교체공사","○ 전선접속개소 해소공사 - 154kV 군산-영등T/L : No.32~33 (0.279 C-km), No.48~49(0.532 C-km) - 154kV 함열-영등T/L : No.8~9","2018-05-11 07:00","2018-05-15 18:00","취소","취소","연속",null,null,null,201803090271,"-"]
[278,"전북","군산","이리백산#2 T/L","군산PO 차단기 점검공사","이리S/S 154kV 이리백산#2T/L 차단기 초기점검(군산전력지사) 백산S/S 154kV 이리백산#2T/L 차단기 조작시험(김제전력지사)","2018-05-09 09:00","2018-05-09 14:00","2018-05-14 09:00","2018-05-14 14:00","당일",null,null,null,201803150086,"-"]
[279,"전북","군산","팔봉영등#1 T/L","팔봉-영등#1T/L 보호배전반 대체공사","팔봉-영등#1T/L 보호배전반 대체공사","2018-05-14 09:00","2018-05-18 18:00","취소","취소","연속",null,null,null,201802200191,"-"]
[280,"전북","군산","팔봉영등#2 T/L","팔봉-영등#2T/L 보호배전반 대체공사","팔봉-영등#2T/L 보호배전반 대체공사","2018-05-08 09:00","2018-05-11 18:00","취소","취소","연속",null,null,null,201802200192,"-"]
[281,"전북","군산","함열영등#1 T/L","함열S/S 170kV 장기사용 GIS 대체공사 (2차)","- 함열-영등#1T/L 대체","2018-05-08 10:00","2018-05-23 18:00","2018-04-26 07:00","2018-05-02 18:00","연속",null,null,null,201803220164,"-"]
[282,"전북","김제","백산김제#1 T/L","154kV 백산-김제T/L 선종교체공사","작업내용 : No.26~30호 전력선교체","2018-05-12 08:00","2018-05-14 18:00","2018-05-12 08:00","2018-05-14 18:00","연속",null,null,null,201803230037,"-"]
[283,"전북","김제","백산김제#2 T/L","154kV 백산-김제T/L 선종교체공사","작업내용 : No.26호~30호 전력선교체","2018-05-08 08:00","2018-05-11 18:00","2018-05-08 08:00","2018-05-11 18:00","연속",null,null,null,201803230036,"-"]
[284,"전북","김제","백산김제#1 T/L","154kV 백산-김제T/L 선종교체공사","작업내용 : No.28호 임시선로 구성","2018-05-07 08:00","2018-05-07 18:00","2018-05-07 08:00","2018-05-07 18:00","연속",null,null,null,201803230081,"-"]
[285,"전북","김제","김제섬진강HP T/L","154kV 백산-김제T/L 선종교체공사","백산-김제T/L 4회선 구간 전력선 교체를 위한 안전확보 휴전","2018-05-08 09:00","2018-05-14 18:00","2018-05-08 09:00","2018-05-14 18:00","연속",null,null,null,201801230085,"-"]
[286,"전북","김제","섬진강H/P 154kV #1 BUS TIE CB","154kV 차단기 보통점검공사","154kV 차단기 보통점검공사","2018-05-08 09:00","2018-05-08 18:00","2018-05-08 09:00","2018-05-08 18:00","당일",null,null,null,201803210290,"○"]
[287,"전북","김제","섬진강H/P #1 M.Tr 1차 CB","154kV 차단기 조작시험","154kV 차단기 조작시험","2018-05-09 09:00","2018-05-09 18:00","2018-05-09 09:00","2018-05-09 18:00","당일",null,null,null,201803210296,"○"]
[288,"전북","김제","섬진강H/P #2 M.Tr 1차 CB","154kV 차단기 보통점검공사","154kV 차단기 보통점검공사","2018-05-10 09:00","2018-05-10 18:00","2018-05-10 09:00","2018-05-10 18:00","당일",null,null,null,201803210294,"○"]
[289,"전북","김제","정공섬진강수력 T/L","154kV 차단기 보통점검공사","154kV 차단기 보통점검공사","2018-05-11 09:00","2018-05-11 18:00","취소","취소","당일",null,null,null,201803210292,"○"]
[290,"전북","김제","신김제동전주#1 T/L","김제PO 154kV GIS 정밀점검공사","김제PO 154kV GIS 정밀점검공사","2018-05-21 09:00","2018-05-23 18:00","2018-05-21 09:00","2018-05-23 18:00","연속",null,null,null,201803130004,"-"]
[291,"전북","김제","신김제S/S 신김제-정공#1T/L CB","2018년도 154kV 차단기 정밀점검","-. 차단부 분해점검 및 이상부품 교체 -. 특성시험 및 경보시험 -. 기타 부대공사 1식","2018-05-19 09:00","2018-05-23 18:00","취소","취소","연속",null,null,null,201801160092,"-"]
[292,"전북","김제","신김제S/S 신김제-전주#1T/L CB","2018년도 154kV 차단기 정밀점검","-. 차단부 분해점검 및 이상부품 교체 -. 특성시험 및 경보시험 -. 기타 부대공사 1식","2018-05-17 09:00","2018-05-19 18:00","취소","취소","연속",null,null,null,201801160093,"-"]
[293,"전북","김제","신김제동전주#2 T/L","김제PO 154kV GIS 정밀점검공사","김제PO 154kV GIS 정밀점검공사","2018-05-31 09:00","2018-06-02 18:00","2018-05-31 09:00","2018-06-02 18:00","연속",null,null,null,201803130006,"-"]
[294,"전북","김제","신김제S/S 신김제-정공#2T/L CB","2018년도 154kV 차단기 정밀점검","-. 차단부 분해점검 및 이상부품 교체 -. 특성시험 및 경보시험 -. 기타 부대공사 1식","2018-05-24 09:00","2018-05-26 18:00","취소","취소","연속",null,null,null,201801160094,"-"]
[295,"전북","김제","정공S/S 154kV #1 BUS TIE CB","2018년도 154kV 차단기 정밀점검","-. 차단부 분해점검 및 이상부품 교체 -. 특성시험 및 경보시험 -. 기타 부대공사 1식","2018-05-17 09:00","2018-05-19 18:00","취소","취소","연속",null,null,null,201801160090,"○"]
[296,"전북","직할","곡성남원#1 T/L","154kV 신남원-남원T/L 건설공사","(휴전)154kV 남원-임실, 곡성-남원 병가선로 이설 관련사업 : 154kV 신남원-남원T/L 건설공사 1.구 간 : 기설 345kV 신남원S/S ~ 기설 154kV 남원S/S 2. 전 력 선 : ACSR 410㎟ × 2B 3. 규 모 : 11.81㎞ / 철탑 : 31기","2018-05-23 08:00","2018-06-02 18:00","2018-05-23 08:00","2018-06-02 18:00","연속",null,null,null,201803150023,"-"]
[297,"전북","직할","북전주진안 T/L","154kV 북전주-진안T/L 송전선로 정밀점검","송전선로 정밀점검 :175기","2018-05-15 09:00","2018-05-29 18:00","2018-05-15 09:00","2018-05-29 18:00","매일",null,null,null,201803160074,"-"]
[298,"전북","직할","무주진안 T/L","154kV 무주-진안T/L 송전선로 정밀점검","송전선로 정밀점검 : 175기","2018-05-08 09:00","2018-05-14 18:00","2018-05-08 09:00","2018-05-14 18:00","매일",null,null,null,201803160070,"-"]
[299,"광주전남","강진","신강진대불#1 T/L","154kV 신강진-대불 등 3개T/L 접속개소해소공사","1. 154kV 강진-장흥 #1,#2 T/L 2. 154kV 대불-남악 #1,#2 T/L 3. 154kV 신강진-대불 #1,#2 T/L","2018-05-17 08:00","2018-05-23 18:00","2018-05-17 08:00","2018-05-23 18:00","연속",null,null,null,201803120338,"-"]
[300,"광주전남","강진","신강진대불#2 T/L","154kV 신강진-대불 등 3개T/L 접속개소해소공사","1. 154kV 강진-장흥 #1,#2 T/L 2. 154kV 대불-남악 #1,#2 T/L 3. 154kV 신강진-대불 #1,#2 T/L","2018-05-24 08:00","2018-05-30 18:00","2018-05-24 08:00","2018-05-30 18:00","연속",null,null,null,201803120339,"-"]
[301,"광주전남","강진","진도S/S 154kV #2 BUS","진도S/S 154kV #2BUS (PT반 대체)","2018~19년 강진전력지사 변전협력회사 총액공사 - 내용 : 154kV PT집합반 대체","2018-05-23 14:00","2018-05-23 18:00","2018-05-23 14:00","2018-05-23 18:00","당일",null,null,null,201803070365,"-"]
[302,"광주전남","강진","해남진도#1 T/L","진도S/S 154kV 해남-진도 #1T/L (GIS 하자점검)","2018~19년 강진전력지사 변전협력회사 총액공사 - 내용 : 170kV GIS 하자점검(진도, 해남)","2018-05-17 09:00","2018-05-17 18:00","2018-05-17 09:00","2018-05-17 18:00","당일",null,null,null,201803070360,"-"]
[303,"광주전남","강진","진도S/S 154kV #2 BUS","진도S/S 154kV #2BUS (PT반 대체)","2018~19년 강진전력지사 변전협력회사 총액공사 - 내용 : 154kV PT집합반 대체","2018-05-24 14:00","2018-05-24 18:00","2018-05-24 14:00","2018-05-24 18:00","당일",null,null,null,201803070366,"-"]
[304,"광주전남","강진","진도S/S 154kV #1 BUS","진도S/S 154kV #1BUS (PT반 대체)","2018~19년 강진전력지사 변전협력회사 총액공사 - 내용 : 154kV PT집합반 대체","2018-05-24 09:00","2018-05-24 14:00","2018-05-24 09:00","2018-05-24 14:00","당일",null,null,null,201803070363,"-"]
[305,"광주전남","강진","진도진도CS#1 T/L","진도S/S 154kV 진도-진도C/S #1T/L (조작불량 ES보수)","2018~19년 강진전력지사 변전협력회사 총액공사 - 내용 : 선로측 ES 조작불량 보수","2018-05-25 09:00","2018-05-25 18:00","2018-05-25 09:00","2018-05-25 18:00","당일",null,null,null,201803120236,"-"]
[306,"광주전남","강진","해남진도#2 T/L","진도S/S 154kV 해남-진도 #2T/L (GIS 하자점검)","2018~19년 강진전력지사 변전협력회사 총액공사 - 내용 : 170kV GIS 하자점검(진도, 해남)","2018-05-18 09:00","2018-05-18 18:00","2018-05-18 09:00","2018-05-18 18:00","당일",null,null,null,201803070361,"-"]
[307,"광주전남","강진","화원진도#2 T/L","진도S/S 154kV 화원-진도 #2T/L (Ari 누기 보수)","2018~19년 강진전력지사 변전협력회사 총액공사 - 내용 : GIS Air 누기 보수","2018-05-21 09:00","2018-05-22 18:00","2018-05-21 09:00","2018-05-22 18:00","당일",null,null,null,201803120237,"-"]
[308,"광주전남","강진","진도S/S 154kV #1 BUS","진도S/S 154kV #1BUS (PT반 대체)","2018~19년 강진전력지사 변전협력회사 총액공사 - 내용 : 154kV PT집합반 대체","2018-05-23 09:00","2018-05-23 14:00","2018-05-23 09:00","2018-05-23 14:00","당일",null,null,null,201803070362,"-"]
[309,"광주전남","강진","진도C/S #1Pole C.Tr","'18~'19년 #2HVDC 변환설비 위탁정비공사","#2HVDC 변환설비 연차점검(#1pole)","2018-05-17 09:00","2018-05-27 18:00","2018-05-17 09:00","2018-05-27 18:00","연속",null,null,null,201803070223,"-"]
[310,"광주전남","강진","진도C/S #2Pole C.Tr","'18~'19년 #2HVDC 변환설비 위탁정비공사","#2HVDC 변환설비 연차점검(#2Pole)","2018-05-21 09:00","2018-05-31 18:00","2018-05-21 09:00","2018-05-31 18:00","연속",null,null,null,201803070218,"-"]
[311,"광주전남","강진","화원진도#1 T/L","화원진도#1 T/L GIS 정밀점검공사","차단부,상부 정밀점검","2018-05-23 09:00","2018-05-24 18:00","2018-05-23 09:00","2018-05-24 18:00","연속",null,null,null,201803120613,"-"]
[312,"광주전남","광주","신광주일곡#2 T/L","신광주S/S 신광주-일곡#2T/L GIS 초기점검","신광주S/S 신광주-일곡#2T/L GIS 초기점검 일곡S/S 신광주-일곡#2T/L GIS 장기미동작 차단기 점검","2018-05-02 09:00","2018-05-02 18:00","2018-05-02 09:00","2018-05-02 18:00","당일",null,null,null,201803120190,"○"]
[313,"광주전남","광주","신광주일곡#1 T/L","신광주S/S 신광주-일곡#1T/L GIS 초기점검","신광주S/S 신광주-일곡#1T/L GIS 초기점검 일곡S/S 신광주-일곡#1T/L GIS 장기미동작 차단기 점검","2018-05-01 09:00","2018-05-01 18:00","2018-05-01 09:00","2018-05-01 18:00","당일",null,null,null,201803120189,"○"]
[314,"광주전남","광주","신광주계림#1 T/L","신광주S/S 신광주-계림#1T/L GIS 초기점검","신광주S/S 신광주-계림#1T/L GIS 초기점검 계림S/S 신광주-계림#1T/L GIS 보통점검","2018-05-03 09:00","2018-05-04 18:00","2018-05-03 09:00","2018-05-04 18:00","매일",null,null,null,201803120191,"○"]
[315,"광주전남","광주","신화순나주#2 T/L","신화순S/S 신화순-나주#2T/L GIS 보통점검","신화순S/S 신화순-나주#2T/L GIS 보통점검","2018-05-11 09:00","2018-05-11 18:00","취소","취소","당일",null,null,null,201803120228,"-"]
[316,"광주전남","목포","고창영광 T/L","154kV 영광S/S 재원태양광T/L 신규수용공사","170kV GIS 재원태양광T/L 신규수용공사 무부하가압 시행","2018-05-05 09:00","2018-05-05 09:00","취소","취소","연속",null,null,null,201803020033,"-"]
[317,"광주전남","목포","장성영광#2 T/L","154kV장성-영광T/L전선접속개소전선교체공사","0 전선 및 금구류 교체 : No.125~160호","2018-05-08 07:00","2018-05-13 18:00","2018-05-05 07:00","2018-05-11 18:00","매일",null,null,null,201803120585,"-"]
[318,"광주전남","목포","장성영광#1 T/L","154kV장성-영광T/L전선접속개소전선교체공사","0 전선 및 금구류 교체 : No.125~160호","2018-05-02 07:00","2018-05-07 18:00","2018-04-29 07:00","2018-05-04 18:00","매일",null,null,null,201803120586,"-"]
[319,"광주전남","목포","고창영광 T/L","154kV 장성-영광T/L전선접속개소전선교체공사","고창-영광T/L 전선교체공사 관련 4회선 구간 안전이격거리 확보차","2018-05-08 07:00","2018-05-13 18:00","2018-05-05 07:00","2018-05-07 18:00","매일",null,null,null,201803120588,"-"]
[320,"광주전남","목포","영광홍농 T/L","154kV 장성-영광T/L전선접속개소전선교체공사","영광-홍농T/L 전선교체공사 관련 4회선 구간 안전이격거리 확보차","2018-05-02 07:00","2018-05-07 18:00","2018-05-11 07:00","2018-05-17 18:00","매일",null,null,null,201803120589,"-"]
[321,"광주전남","순천","광양하동#2 T/L","장기 미동작 차단기 시험","광양-하동#2T/L 장기 미동작 차단기 시험","2018-05-11 13:00","2018-05-11 15:00","2018-05-11 13:00","2018-05-11 15:00","연속",null,null,null,201803120256,"-"]
[322,"광주전남","순천","광양하동#1 T/L","장기 미동작 차단기 시험","광양-하동#1T/L 장기 미동작 차단기 시험","2018-05-11 10:00","2018-05-11 13:00","2018-05-11 10:00","2018-05-11 13:00","연속",null,null,null,201803120252,"-"]
[323,"광주전남","순천","승주S/S 154kV #1 BUS TIE GIS","상반기 170kV GIS 정밀점검공사","6100 정밀점검","2018-05-08 09:00","2018-05-10 18:00","2018-05-08 09:00","2018-05-10 18:00","연속",null,null,null,201802120180,"-"]
[324,"광주전남","순천","승주S/S 154kV #1 BUS","상반기 170kV GIS 정밀점검공사","6100 정밀점검","2018-05-08 09:00","2018-05-09 13:00","2018-05-08 09:00","2018-05-09 13:00","연속",null,null,null,201803120305,"-"]
[325,"광주전남","순천","승주S/S 154kV #2 BUS","상반기 170kV GIS 정밀점검공사","6100 정밀점검","2018-05-09 13:00","2018-05-10 18:00","2018-05-09 13:00","2018-05-10 18:00","연속",null,null,null,201803120306,"-"]
[326,"광주전남","순천","승주서순천 T/L","장기 미동작 차단기 시험","승주-서순천T/L 장기 미동작 차단기 시험","2018-05-15 10:00","2018-05-15 13:00","2018-05-15 10:00","2018-05-15 13:00","연속",null,null,null,201803120267,"-"]
[327,"광주전남","순천","승주주암HP T/L","장기 미동작 차단기 시험","승주-주암HP T/L 장기 미동작 차단기 시험","2018-05-15 13:00","2018-05-15 15:00","2018-05-15 13:00","2018-05-15 15:00","연속",null,null,null,201803120271,"-"]
[328,"광주전남","순천","계림승주#2 T/L","장기 미동작 차단기 시험","계림-승주#2 T/L 장기 미동작 차단기 시험","2018-05-23 13:00","2018-05-23 15:00","2018-05-23 13:00","2018-05-23 15:00","연속",null,null,null,201803120294,"○"]
[329,"광주전남","순천","계림승주#1 T/L","장기 미동작 차단기 시험","계림-승주#1 T/L 장기 미동작 차단기 시험","2018-05-23 10:00","2018-05-23 13:00","2018-05-23 10:00","2018-05-23 13:00","연속",null,null,null,201803120292,"○"]
[330,"광주전남","순천","율촌-여수산단#1 T/L","장기 미동작 차단기 시험","율촌-여수산단#1 T/L 장기 미동작 차단기 시험","2018-05-07 10:00","2018-05-07 13:00","2018-05-07 10:00","2018-05-07 13:00","연속",null,null,null,201803120296,"-"]
[331,"광주전남","순천","율촌-여수산단#2 T/L","장기 미동작 차단기 시험","율촌-여수산단#2 T/L 장기 미동작 차단기 시험","2018-05-07 13:00","2018-05-07 15:00","2018-05-07 13:00","2018-05-07 15:00","연속",null,null,null,201803120297,"-"]
[332,"광주전남","순천","여천여수산단#2 T/L","장기 미동작 차단기 시험","여천-여수산단#2T/L 장기 미동작 차단기 시험","2018-05-18 10:00","2018-05-18 13:00","2018-05-18 10:00","2018-05-18 13:00","연속",null,null,null,201803120234,"-"]
[333,"광주전남","순천","여천호남TP#2 T/L","154kV 여천-호남TP T/L(송전협력회사 총액공사)","노후 애자 교체 - 4~31호, 15기","2018-05-26 07:00","2018-05-28 18:00","2018-05-28 07:00","2018-05-29 18:00","매일",null,null,null,201803090103,"-"]
[334,"광주전남","순천","여천호남TP#1 T/L","154kV 여천-호남TP T/L(송전협력회사 총액공사)","전력선 교체 - 9호~12호, 28~29호","2018-05-22 07:00","2018-05-25 18:00","2018-05-23 07:00","2018-05-25 18:00","연속",null,null,null,201803090100,"-"]
[335,"광주전남","순천","여천여수#1 T/L","154kV 여천-여수T/L(송전협력회사 총액공사)","노후 애자 교체 안전이격확보 - 여천-호남TP T/L 32,38호 2기 4회선 구간","2018-05-27 07:00","2018-05-27 18:00","취소","취소","당일",null,null,null,201803090105,"-"]
[336,"광주전남","순천","용성여수산단#1 T/L","154kV 용성여수산단#1T/L(전선접속개소해소공사)","전력선 교체 - 7호~10호","2018-05-08 07:00","2018-05-14 18:00","2018-05-08 07:00","2018-05-14 18:00","연속",null,null,null,201803090093,"-"]
[337,"광주전남","순천","용성여수산단#2 T/L","154kV 용성여수산단#2T/L(전선접속개소해소공사)","전력선 교체 - 7호~10호, 13~14호","2018-05-15 00:07","2018-05-17 18:00","2018-05-15 00:07","2018-05-17 18:00","연속",null,null,null,201803090095,"-"]
[338,"광주전남","순천","율촌민자#2 T/L","보호배전반 교체(고객 수전설비 점검 및 배전반 대체)","보호배전반 교체(고객 수전설비 점검 및 배전반 대체)","2018-05-04 09:00","2018-05-07 18:00","취소","취소","연속",null,null,null,201803120314,"-"]
[339,"광주전남","순천","율촌민자#1 T/L","보호배전반 교체(고객 수전설비 점검 및 배전반 대체)","보호배전반 교체(고객 수전설비 점검 및 배전반 대체)","2018-05-01 09:00","2018-05-03 18:00","취소","취소","연속",null,null,null,201803120313,"-"]
[340,"광주전남","순천","호남TP여수TP#1 T/L","상반기 170kV GIS 정밀점검공사","호남TP-여수TP#1T/L 정밀점검","2018-05-29 09:00","2018-05-30 18:00","2018-05-31 09:00","2018-06-01 18:00","연속",null,null,null,201802130133,"-"]
[341,"광주전남","순천","여수TP화치#2 T/L","154kV 화치S/S 한화케미칼T/L 신규수용공사","#61BUS측 모선, DS, CB, C/H 챔버 증설구간 여수TP-화치#2T/L을 통한 24시간 무부하가압","2018-05-23 15:00","2018-05-24 15:00","취소","취소","연속",null,null,null,201803120475,"-"]
[342,"광주전남","순천","여수TP화치#2 T/L","154kV 화치S/S 한화케미칼T/L 신규수용공사","#66BUS측 모선 및 DS 증설구간 여수TP-화치#2T/L을 통한 24시간 무부하가압","2018-05-29 15:00","2018-05-30 15:00","취소","취소","연속",null,null,null,201803120477,"-"]
[343,"대구","경산","신경산노변 T/L","노변S/S 신경산-노변T/L 휴전","170kV GIS 정밀점검 Test 선로","2018-05-24 13:00","2018-05-25 18:00","2018-05-24 13:00","2018-05-25 18:00","연속",null,null,null,201803050297,"-"]
[344,"대구","경산","진량노변 T/L","노변S/S 진량-노변T/L 휴전","170kV GIS 정밀점검","2018-05-19 09:00","2018-05-20 18:00","2018-05-19 09:00","2018-05-20 18:00","연속",null,null,null,201803070028,"-"]
[345,"대구","경산","하양봉무#1 T/L","345kV 선산-신포항T/L 전선접속개소 전력선 교체공사","345kV 신포항-북대구T/L No.66~67 선하 154kV 하양-봉무T/L No.43~44 경과선로 안전확보(16,22,23,29일 당일만 휴전, 즉시가압가능)","2018-05-16 08:00","2018-05-29 18:00","2018-05-16 08:00","2018-05-29 18:00","매일",null,null,null,201803160150,"-"]
[346,"대구","경산","하양봉무#2 T/L","345kV 선산-신포항T/L 전선접속개소 전력선 교체공사","345kV 신포항-북대구T/L No.66~67 선하 154kV 하양-봉무T/L No.43~44 경과선로 안전확보(16,22,23,29일 당일만 휴전, 즉시가압가능)","2018-05-16 08:00","2018-05-29 18:00","2018-05-16 08:00","2018-05-29 18:00","매일",null,null,null,201803160151,"-"]
[347,"대구","달성","강창성서#2 T/L","PD집합반 설치공사","154kV 강창성서#2T/L PD집합반 설치 피뢰기 점검 EBA 각 상별 접지선 재설치","2018-05-27 09:00","2018-05-27 18:00","2018-05-27 09:00","2018-05-27 18:00","당일",null,null,null,201803060242,"-"]
[348,"대구","달성","강창성서#1 T/L","PD집합반 설치공사","154kV 강창성서#1T/L PD집합반 설치 피뢰기 점검 EBA 각 상별 접지선 재설치","2018-05-26 09:00","2018-05-26 18:00","2018-05-26 09:00","2018-05-26 18:00","당일",null,null,null,201803060241,"-"]
[349,"대구","달성","대구청도#2 T/L","154kV 청도-밀양T/L 정밀점검 안전확보","154kV 청도-밀양#1T/L 정밀점검 안전확보 : No.2-17","2018-05-02 08:00","2018-05-03 18:00","2018-05-02 08:00","2018-05-03 18:00","매일",null,null,null,201803080389,"-"]
[350,"대구","달성","대구청도#1 T/L","154kV 청도-밀양T/L 정밀점검 안전확보","154kV 청도-밀양#2T/L 정밀점검 안전확보 : No.2-17","2018-05-08 08:00","2018-05-09 18:00","2018-05-08 08:00","2018-05-09 18:00","매일",null,null,null,201803080391,"-"]
[351,"대구","달성","두류봉덕#1 T/L","달성전력지사 GIS 정밀 TEST선로","달성전력지사 GIS 정밀 TEST선로","2018-05-24 13:00","2018-05-25 18:00","2018-05-24 13:00","2018-05-25 18:00","매일",null,null,null,201803080377,"-"]
[352,"대구","달성","두류봉덕#2 T/L","달성전력지사 GIS 정밀점검공사","달성전력지사 GIS 정밀점검공사","2018-05-30 13:00","2018-05-31 18:00","2018-05-30 13:00","2018-05-31 18:00","매일",null,null,null,201803080388,"-"]
[353,"대구","달성","대구봉덕#2 T/L","달성전력지사 GIS 정밀점검공사","달성전력지사 GIS 정밀점검공사","2018-05-02 09:00","2018-05-04 18:00","2018-05-02 09:00","2018-05-05 18:00","연속",null,null,null,201803160049,"-"]
[354,"대구","달성","대구봉덕#1 T/L","달성전력지사 GIS 정밀 TEST선로","달성전력지사 GIS 정밀 TEST선로","2018-05-09 09:00","2018-05-09 18:00","2018-05-09 09:00","2018-05-09 18:00","당일",null,null,null,201803080362,"-"]
[355,"대구","달성","상인봉덕#2 T/L","달성전력지사 GIS 정밀점검공사","달성전력지사 GIS 정밀점검공사","2018-05-03 13:00","2018-05-03 18:00","2018-05-03 13:00","2018-05-03 18:00","당일",null,null,null,201803160053,"-"]
[356,"대구","달성","두류봉덕#1 T/L","달성전력지사 GIS 정밀점검공사","달성전력지사 GIS 정밀점검공사","2018-05-08 09:00","2018-05-09 18:00","2018-05-08 09:00","2018-05-11 18:00","연속",null,null,null,201803080359,"-"]
[357,"대구","달성","두류봉덕#2 T/L","달성전력지사 GIS 정밀점검공사","달성전력지사 GIS 정밀점검공사","2018-05-10 09:00","2018-05-11 18:00","2018-05-14 09:00","2018-05-17 18:00","연속",null,null,null,201803080369,"-"]
[358,"대구","달성","대구봉덕#2 T/L","달성전력지사 GIS 정밀점검공사 TEST 선로","달성전력지사 GIS 정밀점검공사 TEST 선로","2018-05-11 13:00","2018-05-11 18:00","2018-05-15 13:00","2018-05-15 18:00","당일",null,null,null,201803160060,"-"]
[359,"대구","달성","달서팔달#1 T/L","154kV 달서-팔달 등 2개T/L 지장선로 이설공사","○ 목 적 : 대구광역시 매립장증설사업에 지장이 되어 이설 ○ 구 간 : 154kV 달서-팔달T/L No.10~13, 4회선 [하단 : 북대구-팔달T/L] ○ 수 량 : 철탑 이설 2기(가철탑 2기), 전력선교체 4C, 1.051km (A410㎟, HST410㎟)","2018-05-22 09:00","2018-06-16 18:00","취소","취소","연속",null,null,null,201803080481,"-"]
[360,"대구","달성","북대구팔달#1 T/L","154kV 달서-팔달 등 2개T/L 지장선로 이설공사","○ 목 적 : 대구광역시 매립장증설사업에 지장이 되어 이설 ○ 구 간 : 154kV 달서-팔달T/L No.10~13, 4회선 [하단 : 북대구-팔달T/L] ○ 수 량 : 철탑 이설 2기(가철탑 2기), 전력선교체 4C, 1.051km (A410㎟, HST410㎟)","2018-05-22 09:00","2018-06-16 18:00","취소","취소","연속",null,null,null,201803080482,"-"]
[361,"대구","칠곡","관음구암#1 T/L","345kV 선산-신포항T/L 전선접속개소 전력선 교체공사 안전확보","345kV 신포항-북대구T/L No.49~50 선하 154kV 관음-구암T/L No.37~38 경과선로 안전확보(11,15,30,6월3일 당일만 휴전, 즉시가압가능)","2018-05-30 08:00","2018-05-30 18:00","2018-05-30 08:00","2018-05-30 18:00","당일",null,null,null,201803200236,"-"]
[362,"대구","칠곡","관음구암#2 T/L","345kV 선산-신포항T/L 전선접속개소 전력선 교체공사 안전확보","345kV 신포항-북대구T/L No.49~50 선하 154kV 관음-구암T/L No.37~38 경과선로 안전확보(11,15,30,6월3일 당일만 휴전, 즉시가압가능)","2018-05-30 08:00","2018-05-30 18:00","2018-05-30 08:00","2018-05-30 18:00","당일",null,null,null,201803200237,"-"]
[363,"대구","칠곡","관음구암#1 T/L","345kV신포항-북대구 등2개 T/L 지장선로 이설공사","154kV관음-구암T/L No.18-1 철탑 신설","2018-05-14 08:00","2018-05-17 18:00","2018-05-14 08:00","2018-05-17 18:00","연속",null,null,null,201802070181,"-"]
[364,"대구","칠곡","관음구암#2 T/L","345kV신포항-북대구 등2개 T/L 지장선로 이설공사","154kV관음-구암T/L No.18-1 철탑 신설","2018-05-14 08:00","2018-05-14 18:00","2018-05-14 08:00","2018-05-14 18:00","당일",null,null,null,201802070180,"-"]
[365,"대구","칠곡","관음구암#1 T/L","345kV 선산-신포항T/L 전선접속개소 전력선 교체공사 안전확보","345kV 신포항-북대구T/L No.49~50 선하 154kV 관음-구암T/L No.37~38 경과선로 안전확보(11,15,30,6월3일 당일만 휴전, 즉시가압가능)","2018-05-09 08:00","2018-05-09 18:00","2018-05-09 08:00","2018-05-09 18:00","당일",null,null,null,201803160147,"-"]
[366,"대구","칠곡","관음구암#2 T/L","345kV 선산-신포항T/L 전선접속개소 전력선 교체공사 안전확보","345kV 신포항-북대구T/L No.49~50 선하 154kV 관음-구암T/L No.37~38 경과선로 안전확보(11,15,30,6월3일 당일만 휴전, 즉시가압가능)","2018-05-09 08:00","2018-05-09 18:00","2018-05-09 08:00","2018-05-09 18:00","당일",null,null,null,201803160148,"-"]
[367,"대구","칠곡","어모김천#1 T/L","김천 코오롱 인더스트리 공장 증설공사 안전확보 휴전","김천 코오롱 인더스트리 공장 증설공사 안전확보 휴전","2018-05-01 09:00","2018-05-15 18:00","2018-05-01 09:00","2018-05-15 18:00","연속",null,null,null,201803150333,"-"]
[368,"대구","칠곡","북대구관음#1 T/L","154kV북대구-왜관T/L 전력선 교체공사","전력선 교체공사 병가구간 안전확보 154kV북대구-관음T/L No.2~10 (병가)","2018-05-03 08:00","2018-05-11 18:00","2018-05-03 08:00","2018-05-11 18:00","연속",null,null,null,201803080349,"-"]
[369,"대구","칠곡","북대구관음#2 T/L","154kV북대구-왜관T/L 전력선 교체공사","전력선 교체공사 병가구간 안전확보 154kV북대구-관음T/L No.2~10 (병가)","2018-05-10 08:00","2018-05-18 18:00","2018-05-11 08:00","2018-05-18 18:00","연속",null,null,null,201803080102,"-"]
[370,"대구","포항","신포항S/S 154kV #65 BUS","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 상부모선, CB, DS 및 POST, BEAM 철거 등","2018-05-14 08:00","2018-05-15 18:00","취소","취소","연속",null,null,null,201803050018,"-"]
[371,"대구","포항","아화건천#2 T/L","154kV 아화-건천T/L 안전이격 확보공사","No.28-32호 철탑지지물교체(양회선휴전)","2018-05-21 07:00","2018-05-30 18:00","취소","취소","연속",null,null,null,201803160176,"-"]
[372,"대구","포항","아화건천#1 T/L","154kV 아화-건천T/L 안전이격 확보공사","No.28-32호 철탑지지물교체(양회선휴전)","2018-05-21 07:00","2018-05-30 18:00","취소","취소","연속",null,null,null,201803160175,"-"]
[373,"경북","구미","선산산동#1 T/L","선산S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 공사 - 산동#1T/L POST 교체 등","2018-05-07 08:00","2018-05-15 18:00","2018-05-07 08:00","2018-05-15 18:00","연속",null,null,null,201803060001,"-"]
[374,"경북","구미","선산산동#2 T/L","선산S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 공사 - 산동#1T/L POST 교체 등","2018-05-07 08:00","2018-05-15 18:00","2018-05-07 08:00","2018-05-15 18:00","연속",null,null,null,201803060002,"-"]
[375,"경북","구미","선산청리#2 T/L","선산S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 공사","2018-05-16 08:00","2018-05-18 18:00","2018-05-16 08:00","2018-05-18 18:00","연속",null,null,null,201803060004,"-"]
[376,"경북","구미","청리상주#1T/L","2018년도 구미전력지사 변전협력 총액공사","GIS보통점검, LA보통점검","2018-05-04 09:00","2018-05-04 14:00","2018-05-04 09:00","2018-05-04 14:00","당일",null,null,null,201803090116,"-"]
[377,"경북","구미","청리상주#2T/L","2018년도 구미전력지사 변전협력 총액공사","GIS보통점검, LA보통점검","2018-05-04 14:00","2018-05-04 18:00","2018-05-04 14:00","2018-05-04 18:00","당일",null,null,null,201803090117,"-"]
[378,"경북","영주","봉화울진 T/L","2018-19년도 영주전력지사 변전협력업체 총액공사","627 GIS, LA A,B,C상 보통점검","2018-05-08 14:00","2018-05-08 18:00","2018-05-08 14:00","2018-05-08 18:00","당일",null,null,null,201803080307,"-"]
[379,"경북","영주","신영주예천#2 T/L","345kV 신제천-신영주T/L 전선접속개소 전선교체공사","345kV 신제천-신영주T/L 공사관련 하단 안전확보","2018-05-05 09:00","2018-05-07 18:00","2018-05-26 09:00","2018-05-28 18:00","매일",null,null,null,201803060035,"-"]
[380,"경북","영주","신영주예천#2 T/L","345kV 신제천-신영주T/L 전선접속개소 전선교체공사","345kV 신제천-신영주T/L 공사관련 하단 안전확보","2018-05-15 09:00","2018-05-17 18:00","2018-06-05 09:00","2018-06-07 18:00","매일",null,null,null,201803060034,"-"]
[381,"경북","영주","신영주예천#1 T/L","345kV 신제천-신영주T/L 전선접속개소 전선교체공사","345kV 신제천-신영주T/L 공사관련 하단 안전확보","2018-05-05 09:00","2018-05-07 18:00","2018-05-26 09:00","2018-05-28 18:00","매일",null,null,null,201803060032,"-"]
[382,"경북","영주","신영주예천#1 T/L","345kV 신제천-신영주T/L 전선접속개소 전선교체공사","345kV 신제천-신영주T/L 공사관련 하단 안전확보","2018-05-15 09:00","2018-05-17 18:00","2018-06-05 09:00","2018-06-07 18:00","매일",null,null,null,201803060033,"-"]
[383,"경북","직할","안동복합S/Y 154kV #1 BUS TIE GIS","18~19 경북직할 변전협력업체 총액공사","안동복합S/S 6100 GIS 초기점검","2018-05-15 09:00","2018-05-15 18:00","2018-05-15 09:00","2018-05-15 18:00","당일",null,null,null,201803050138,"-"]
[384,"경북","직할","풍산안동CC#1 T/L","18~19 경북직할 변전협력업체 총액공사","풍산S/S 안동CC-풍산#1T/L GIS초기점검 안동복합S/S 안동CC-풍산#1T/L GIS초기점검","2018-05-24 09:00","2018-05-25 18:00","2018-05-24 09:00","2018-05-25 18:00","매일",null,null,null,201803050123,"-"]
[385,"경북","직할","풍산안동CC#2 T/L","18~19 경북직할 변전협력업체 총액공사","풍산S/S 안동CC-풍산#2T/L GIS초기점검 안동복합S/S 안동CC-풍산#2T/L GIS초기점검","2018-05-28 09:00","2018-05-29 18:00","2018-05-28 09:00","2018-05-29 18:00","매일",null,null,null,201803050124,"-"]
[386,"경북","직할","봉화평해 T/L","154kV 울진 현종산 풍력발전단지 송전선로 건설공사","전력선 이설 및 긴선압축, 가선로 구성","2018-05-03 08:00","2018-05-16 18:00","2018-05-03 08:00","2018-05-16 18:00","연속",null,null,null,201803080059,"-"]
[387,"경북","직할","울진평해 T/L","154kV 울진 현종산 풍력발전단지 송전선로 건설공사","울진-현종산, 현종산-평해 선로 분기 및 판넬 이설","2018-05-18 07:00","2018-05-22 18:00","2018-05-18 07:00","2018-05-22 18:00","연속",null,null,null,201803080057,"-"]
[388,"부산울산","동부산","신울산명례#2 T/L","2018년 가공송전 순시점검 위탁공사","154kV 신울산-명례T/L 정밀점검 : 신울산S/S~명례S/S(43기)","2018-05-23 09:00","2018-05-25 18:00","2018-05-23 09:00","2018-05-25 18:00","매일",null,null,null,201803080129,"-"]
[389,"부산울산","동부산","신울산명례#1 T/L","2018년 가공송전 순시점검 위탁공사","154kV 신울산-명례T/L 정밀점검 : 신울산S/S~명례S/S(43기)","2018-05-16 09:00","2018-05-18 18:00","2018-05-16 09:00","2018-05-18 18:00","매일",null,null,null,201803080127,"-"]
[390,"부산울산","동부산","명례정관 T/L","2018년 가공송전 순시점검 위탁공사","154kV 명례-정관T/L 정밀점검 구간 : 명례C/H ~ 4호(4기)","2018-05-15 09:00","2018-05-15 18:00","2018-05-08 09:00","2018-05-10 18:00","당일",null,null,null,201803080123,"-"]
[391,"부산울산","동부산","구서명장#1 T/L","154㎸ 신양산-구서, 구서-명장T/L OPGW 증설공사","154㎸ 신양산-구서, 구서-명장T/L OPGW 증설관련 안전 확보","2018-05-03 07:00","2018-05-04 18:00","2018-05-03 07:00","2018-05-04 18:00","매일",null,null,null,201803090007,"-"]
[392,"부산울산","동부산","구서명장#2 T/L","154㎸ 신양산-구서, 구서-명장T/L OPGW 증설공사","154㎸ 신양산-구서, 구서-명장T/L OPGW 증설관련 안전 확보","2018-05-05 07:00","2018-05-08 18:00","2018-05-05 07:00","2018-05-08 18:00","매일",null,null,null,201803090008,"-"]
[393,"부산울산","동부산","웅촌서창#1 T/L","154kV 웅촌-서창T/L 안전이격거리 확보","국토관리청 시행 국도건설공사 작업기간동안 휴전하여 안전이격거리 확보","2018-05-14 07:00","2018-05-21 19:00","2018-05-14 07:00","2018-05-21 19:00","매일",null,null,"신뢰도개선",201803130226,"-"]
[394,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 154kV M.Tr 1차 GIB 구조개선공사","서창S/S 154kV #1M.Tr 1차 GIB 구조개선관련 시험가압(웅촌-서창#1T/L)","2018-05-02 18:00","2018-05-03 18:00","2018-05-02 18:00","2018-05-03 18:00","연속",null,null,"신뢰도개선",201803110038,"-"]
[395,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 154kV M.Tr 1차 GIB 구조개선공사","서창S/S 154kV #2M.Tr 1차 GIB 구조개선관련 시험가압(웅촌-서창#1T/L)","2018-05-22 18:00","2018-05-23 18:00","2018-05-22 18:00","2018-05-23 18:00","연속",null,null,"신뢰도개선",201803110039,"-"]
[396,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 154kV M.Tr 1차 GIB 구조개선공사","서창S/S 154kV #4M.Tr 1차 GIB 구조개선관련 시험가압(웅촌-서창#1T/L)","2018-05-29 18:00","2018-05-30 18:00","2018-05-29 18:00","2018-05-30 18:00","연속",null,null,"신뢰도개선",201803110040,"-"]
[397,"부산울산","동부산","신양산S/S 154kV #60 BUS","345kV 신양산S/S 현대화 공사","- 154kV 덕트 기초 터파기 - 안전이격확보","2018-05-17 09:00","2018-05-18 18:00","2018-05-17 09:00","2018-05-18 18:00","연속",null,null,null,201803130178,"-"]
[398,"부산울산","동부산","신양산S/S 154kV #65 BUS","345kV 신양산S/S 현대화 공사","- 154kV 덕트 기초 터파기 - 안전이격확보","2018-05-15 09:00","2018-05-16 18:00","2018-05-15 09:00","2018-05-16 18:00","연속",null,null,null,201803130177,"-"]
[399,"부산울산","동부산","정보대연 T/L","정보S/S 170kV GIS 정밀점검공사","정보S/S 170kV 657GIS 정밀점검 및 시험가압","2018-05-10 09:00","2018-05-11 18:00","2018-05-10 09:00","2018-05-11 18:00","연속",null,null,null,201803110037,"-"]
[400,"부산울산","동부산","정보대연 T/L","정보S/S 170kV GIS 정밀점검공사","정보S/S 170kV 6233GIS 정밀점검관련 시험가압(정보-대연T/L)","2018-05-09 17:00","2018-05-09 18:00","2018-05-09 17:00","2018-05-09 18:00","당일",null,null,null,201803110036,"-"]
[401,"부산울산","동부산","정보대연 T/L","정보S/S 170kV GIS 정밀점검공사","정보S/S 170kV 6100GIS 정밀점검관련 시험가압(정보-대연T/L)","2018-05-03 17:00","2018-05-03 18:00","2018-05-03 17:00","2018-05-03 18:00","당일",null,null,null,201803110034,"-"]
[402,"부산울산","북부산","김해어방#2 T/L","김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#2T/L GIS 대체 (677 휴전)","2018-05-21 08:00","2018-06-04 18:00","취소","취소","연속",null,null,null,201803080554,"-"]
[403,"부산울산","북부산","김해S/S 154kV #2 BUS","김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#2T/L GIS 대체 (#2DS 철거)","2018-05-21 08:00","2018-05-22 13:00","취소","취소","연속",null,null,null,201803080555,"-"]
[404,"부산울산","북부산","김해어방#1 T/L","김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 김해-어방#2T/L GIS 대체 - #2BUS 시험가압 2h (647 휴전)","2018-05-22 11:00","2018-05-22 13:00","취소","취소","당일",null,null,null,201803080556,"-"]
[405,"부산울산","북부산","김해S/S 154kV #1 BUS","김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#2T/L GIS 대체(#1DS, CB, 상부BUS 설치)","2018-05-22 13:00","2018-05-28 18:00","취소","취소","연속",null,null,null,201803080557,"-"]
[406,"부산울산","북부산","김해S/S 154kV #2 BUS","김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#2T/L GIS 대체(#2DS 설치)","2018-05-28 08:00","2018-06-04 16:00","취소","취소","연속",null,null,null,201803080560,"-"]
[407,"부산울산","북부산","김해어방#1 T/L","김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 김해-어방#2T/L GIS 대체 - #1BUS 시험가압 48h (647 휴전)","2018-05-26 18:00","2018-05-27 18:00","취소","취소","연속",null,null,null,201803080559,"-"]
[408,"부산울산","북부산","북부산물금 T/L","물금S/S #4M.Tr 증설공사","- #4M.Tr 1차 GIS (6433) 설치 관련 모선감압 안전이격 확보","2018-05-09 09:00","2018-05-09 18:00","2018-05-09 09:00","2018-05-09 18:00","당일",null,null,null,201803090374,"-"]
[409,"부산울산","북부산","북부산물금 T/L","물금S/S #4M.Tr 증설공사","- #4M.Tr 1차 GIS (6433) 설치 관련 모선감압 안전이격 확보","2018-05-14 09:00","2018-05-14 18:00","2018-05-14 09:00","2018-05-14 18:00","당일",null,null,null,201803090376,"-"]
[410,"부산울산","북부산","물금삼랑진PP#2 T/L","2018년 북부산 변전협력회사 총액공사","물금S/S 154kV 물금-삼랑진PP #2T/L (657) GIS 초기점검","2018-05-04 10:00","2018-05-04 18:00","2018-05-08 10:00","2018-05-08 18:00","당일",null,null,null,201803080503,"-"]
[411,"부산울산","북부산","북부산물금 T/L","물금S/S #4M.Tr 증설공사","- #4M.Tr 1차 GIS (6433) 설치관련 #2BUS 시험가압","2018-05-16 18:00","2018-05-17 18:00","2018-05-16 18:00","2018-05-17 18:00","연속",null,null,null,201803090378,"-"]
[412,"부산울산","북부산","북부산물금 T/L","물금S/S #4M.Tr 증설공사","- #4M.Tr 1차 GIS (6433) 설치관련 #1BUS 시험가압","2018-05-12 18:00","2018-05-13 18:00","2018-05-12 18:00","2018-05-13 18:00","연속",null,null,null,201803090377,"-"]
[413,"부산울산","북부산","북부산양산 T/L","154kV 삼랑진양수T/L 전선교체공사","154kV 북부산-양산T/L(주작업) No.1~7, 12~24, 54~62호 전선교체","2018-05-14 07:00","2018-05-27 18:00","2018-05-14 07:00","2018-05-27 18:00","연속",null,null,null,201803050051,"-"]
[414,"부산울산","북부산","북부산삼랑진PP T/L","154kV 삼랑진양수T/L 전선교체공사","154kV 북부산-양산T/L No.12~24, 54~62호 전선교체 안전이격선로","2018-05-18 07:00","2018-05-27 18:00","2018-05-18 07:00","2018-05-27 18:00","매일",null,null,null,201803050052,"○"]
[415,"부산울산","북부산","양산산막#1 T/L","154kV 양산-산막 외1개T/L 인출철탑 정비공사","○ 구 간 : 154㎸ 양산-산막T/L S/T ∼ 2호 ○ 내 용 : 1호 철탑 교체 및 전력선 교체 작업","2018-05-11 08:00","2018-05-13 18:00","취소","취소","연속",null,null,null,201803120286,"-"]
[416,"부산울산","북부산","양산산막#1 T/L","154kV 양산-산막 외1개T/L 인출철탑 정비공사","○ 구 간 : 154㎸ 양산-산막T/L S/T ∼ 2호 ○ 내 용 : 1호 철탑 교체 및 전력선 교체 작업 ※ 안전이격 확보","2018-05-07 08:00","2018-05-07 18:00","취소","취소","당일",null,null,null,201803120279,"-"]
[417,"부산울산","북부산","양산산막#2 T/L","154kV 양산-산막 외1개T/L 인출철탑 정비공사","○ 구 간 : 154㎸ 양산-산막T/L S/T ∼ 2호 ○ 내 용 : 1호 철탑 교체 및 전력선 교체 작업","2018-05-07 08:00","2018-05-10 18:00","취소","취소","연속",null,null,null,201803120282,"-"]
[418,"부산울산","북부산","삼계어방#2 T/L","2018년 북부산 변전협력회사 총액공사","어방S/S 154kV 삼계-어방#2T/L (667) GIS 초기점검","2018-05-03 10:00","2018-05-03 18:00","2018-05-19 10:00","2018-05-19 18:00","당일",null,null,null,201803080501,"-"]
[419,"부산울산","서부산","용원녹공#2 T/L","녹공S/S 154kV 용원-녹공#2T/L(627) GIS 정밀점검","녹공S/S 154kV 용원-녹공#2T/L(627) GIS 정밀점검 (모선DS 점검포함, PMJ선로)","2018-05-12 08:00","2018-05-13 20:00","2018-05-12 08:00","2018-05-13 20:00","연속",null,null,null,201803080094,"-"]
[420,"부산울산","서부산","녹공마천#2 T/L","녹공S/S 154kV #3M.Tr 1차 GIS 정밀점검 시험가압","녹공S/S 154kV #3M.Tr 1차 GIS(6333) 정밀점검 시험가압 (#2BUS 시험가압)","2018-05-11 17:00","2018-05-11 18:00","2018-05-11 17:00","2018-05-11 18:00","당일",null,null,null,201803090024,"-"]
[421,"부산울산","서부산","녹공마천#1 T/L","녹공S/S 154kV #3M.Tr 1차 GIS 정밀점검 시험가압","녹공S/S 154kV #3M.Tr 1차 GIS(6333) 정밀점검 시험가압 (CB, 상부BUS 시험가압)","2018-05-10 17:00","2018-05-10 18:00","2018-05-10 17:00","2018-05-10 18:00","당일",null,null,null,201803090023,"-"]
[422,"부산울산","서부산","용원녹공#1 T/L","녹공S/S 154kV 용원-녹공#1T/L(617) GIS 정밀점검","녹공S/S 154kV 용원-녹공#1T/L(617) GIS 정밀점검 (모선DS 점검포함, PMJ선로)","2018-05-05 08:00","2018-05-06 20:00","2018-05-05 08:00","2018-05-06 20:00","연속",null,null,null,201803080093,"-"]
[423,"부산울산","서부산","서부산신평#2 T/L","345kV 서부산S/S 154kV 인출선로 정비공사","154kV XLPE 2000㎟ 케이블, 2C-0.03km 설치","2018-05-12 08:00","2018-06-04 18:00","2018-05-12 08:00","2018-06-04 18:00","연속",null,null,null,201803080253,"-"]
[424,"부산울산","서부산","서부산S/S #4 S/T GIS","서부산S/S 154kV #4S/T용 M.Tr GIS (6M7) 정밀점검","서부산S/S 154kV #4S/T용 M.Tr GIS (6M7) 정밀점검 (모선DS 점검제외)","2018-05-18 08:00","2018-05-19 18:00","2018-05-18 08:00","2018-05-19 18:00","연속",null,null,null,201803090028,"-"]
[425,"부산울산","서부산","서부산엄궁#2 T/L","서부산S/S 154kV #4S/T용 M.Tr GIS 정밀점검 시험가압","서부산S/S 154kV #4S/T용 M.Tr GIS (6M7) 정밀점검 시험가압 (CB, 상부BUS,C/H 시험가압)","2018-05-19 17:00","2018-05-19 18:00","2018-05-19 17:00","2018-05-19 18:00","당일",null,null,null,201803080084,"-"]
[426,"부산울산","서부산","서부산S/S 154kV #66 BUS","서부산S/S 154kV #4S/T용 M.Tr GIS 정밀점검 시험가압","서부산S/S 154kV #4S/T용 M.Tr GIS (6M7) 정밀점검 시험가압 (#4S/T용 M.Tr (6K7) 시험가압)","2018-05-19 17:00","2018-05-19 18:00","2018-05-19 17:00","2018-05-19 18:00","당일",null,null,null,201803090029,"-"]
[427,"부산울산","울산","동울산방어진 T/L","2018~19년도 울산전력지사 가공송전 협력회사 총액공사","현대#1T/L 전선접속개소 전선교체공사 관련 안격이격거리 확보차","2018-05-06 06:00","2018-05-06 15:00","2018-05-06 06:00","2018-05-06 15:00","당일",null,null,null,201803090175,"-"]
[428,"부산울산","울산","언양산막#1 T/L","154㎸ 신울산-웅촌등 7개 T/L 자기애관 교체공사","지중송전선로용 자기애관(EBA)→폴리머 애관 교체공사","2018-05-28 09:00","2018-05-30 18:00","2018-05-24 09:00","2018-05-27 18:00","연속",null,null,null,201803060068,"-"]
[429,"부산울산","울산","신울산웅촌#2 T/L","154㎸ 신울산-웅촌등 7개 T/L 자기애관 교체공사","지중송전선로용 자기애관(EBA)→폴리머 애관 교체공사","2018-05-31 09:00","2018-06-02 18:00","취소","취소","연속",null,null,null,201803060071,"-"]
[430,"부산울산","울산","신온산온산#3 T/L","2018년 울산P/O 170kV 개폐장치 정밀점검공사","온산S/S 170kV 6231DS 정밀점검관련 시험가압","2018-05-02 17:00","2018-05-02 18:00","취소","취소","당일",null,null,null,201803090118,"-"]
[431,"부산울산","울산","신온산온산#3 T/L","2018년 울산P/O 170kV 개폐장치 정밀점검공사","온산S/S 170kV 6232,6233 정밀점검관련 시험가압","2018-05-04 17:00","2018-05-04 18:00","취소","취소","당일",null,null,null,201803090119,"-"]
[432,"부산울산","울산","신울산울산#2 T/L","2018년 울산P/O 170kV 개폐장치 정밀점검공사","울산S/S 170kV 6332,6333 정밀점검관련 시험가압","2018-05-25 17:00","2018-05-25 18:00","2018-05-23 17:00","2018-05-23 18:00","당일",null,null,null,201803090127,"-"]
[433,"부산울산","울산","신울산울산#2 T/L","2018년 울산P/O 170kV 개폐장치 정밀점검공사","울산S/S 170kV 6132,6133 정밀점검관련 시험가압","2018-05-16 17:00","2018-05-16 18:00","2018-05-14 17:00","2018-05-14 18:00","당일",null,null,null,201803090124,"-"]
[434,"부산울산","울산","신울산울산#1 T/L","2018년 울산P/O 170kV 개폐장치 정밀점검공사","울산S/S 170kV 6131DS 정밀점검관련 시험가압","2018-05-14 17:00","2018-05-14 18:00","2018-05-16 17:00","2018-05-16 18:00","당일",null,null,null,201803090125,"○"]
[435,"부산울산","울산","신울산울산#1 T/L","2018년 울산P/O 170kV 개폐장치 정밀점검공사","울산S/S 170kV 6231DS 정밀점검관련 시험가압","2018-05-09 17:00","2018-05-09 18:00","2018-05-10 17:00","2018-05-10 18:00","당일",null,null,null,201803090122,"○"]
[436,"부산울산","울산","신울산울산#1 T/L","2018년 울산P/O 170kV 개폐장치 정밀점검공사","울산S/S 170kV 6331DS 정밀점검관련 시험가압","2018-05-23 17:00","2018-05-23 18:00","2018-05-25 17:00","2018-05-25 18:00","당일",null,null,null,201803090126,"○"]
[437,"부산울산","울산","신울산울산#2 T/L","2018년 울산P/O 170kV 개폐장치 정밀점검공사","울산S/S 170kV 6232,6233 정밀점검관련 시험가압","2018-05-11 17:00","2018-05-11 18:00","2018-05-08 17:00","2018-05-08 18:00","당일",null,null,null,201803090123,"-"]
[438,"부산울산","울산","용연처용#2 T/L","2018년 처용S/S 170kV 장기사용 GIS 대체공사","처용S/S 170kV 용연-처용#2T/L(617),#1M.Tr 1차 GIS(6133) 대체공사","2018-05-28 08:00","2018-06-12 18:00","취소","취소","연속",null,null,null,201803090128,"-"]
[439,"부산울산","직할","수정범일#1 T/L","154kV 범일 등 3개S/S 지중송전케이블 선종교체공사","154kV 수정-범일T/L 선종교체공사(OF1200 --> XLPE 1200, 0.7km) - 공사구간 : 수정S/S ~ S/J, 범일S/S ~ J/B#7-2","2018-05-30 09:00","2018-07-11 18:00","2018-05-30 09:00","2018-07-11 18:00","연속",null,null,null,201803130237,"-"]
[440,"부산울산","직할","부민부산 T/L","2018년 직할 관내 170kV GIS 정밀점검공사","부민S/S #4M.Tr 1차 GIS(6433) 정밀점검 시험가압선로","2018-05-16 17:00","2018-05-16 18:00","2018-05-16 17:00","2018-05-16 18:00","당일",null,null,null,201803090494,"-"]
[441,"부산울산","직할","서부산부민#2 T/L","345kV 서부산S/S 154kV 인출선로 정비공사","154kV XLPE 2000㎟ 케이블, 2C-0.03km 설치","2018-05-12 08:00","2018-06-04 18:00","2018-05-12 08:00","2018-06-04 18:00","연속",null,null,null,201803080259,"-"]
[442,"경남","직할","삼정천선#2 T/L","삼정S/S GIS화 부지확보 (C/H철탑설치 안전이격 확보)","삼정S/S GIS화 공사 부직확보 작업관련 - 154kV 삼정-천선#1,2T/L용 C/H철탑설치 안전이격 확보 - 154kV 삼정-천선#1,2T/L 동시휴전(5/15~6/7)","2018-05-15 07:30","2018-06-07 17:30","2018-05-15 07:30","2018-06-07 17:30","연속",null,null,null,201803060108,"-"]
[443,"경남","직할","삼정천선#1 T/L","삼정S/S GIS화 부지확보 (154kV 삼정-천선#1T/L 인출변경)","삼정S/S 154kV 삼정-천선#1T/L GIS 인출변경 - 154kV 2회선용 C/H철탑 설치 - C/H철탑 + 임시공급GIS로 인출변경","2018-05-15 07:30","2018-06-07 17:30","2018-05-15 07:30","2018-06-07 17:30","연속",null,null,null,201803060107,"-"]
[444,"경남","직할","신월동읍#1 T/L","154kV 신월-동읍 등 2개T/L OF케이블 교체공사","신월EBG~#1M/H 구간 154kV 신월-동읍#1T/L 케이블 교체(OF1200㎟ → XLPE1200㎟)","2018-05-15 08:00","2018-05-29 18:00","취소","취소","연속",null,null,null,201803020081,"-"]
[445,"경남","직할","신월동읍#2 T/L","154kV 신월-동읍 등 2개T/L OF케이블 교체공사","신월EBG~#1M/H 구간 154kV 신월-동읍#2T/L 케이블 교체(OF1200㎟ → XLPE1200㎟)","2018-05-30 08:00","2018-06-13 18:00","취소","취소","연속",null,null,null,201803020082,"-"]
[446,"경남","직할","차룡창공#1 T/L","차룡S/S 154kV 차룡-창공#1T/L CB보통, LA하자점검","차룡S/S 154kV 차룡-창공#1T/L CB보통, LA하자점검","2018-05-25 09:30","2018-05-25 17:30","2018-05-25 09:30","2018-05-25 17:30","당일",null,null,null,201803040007,"-"]
[447,"경남","진주","동진주진주#2 T/L","2018년도 경남지역본부 지중송전 위탁정비공사","케이블해드 지중송전선로 피뢰기 점검","2018-05-20 09:00","2018-05-20 18:00","2018-05-20 09:00","2018-05-20 18:00","당일",null,null,null,201803050267,"-"]
[448,"경남","진주","동진주진주#1 T/L","2018년도 경남지역본부 지중송전 위탁정비공사","케이블해드 지중송전선로 피뢰기 점검","2018-05-19 09:00","2018-05-19 18:00","2018-05-19 09:00","2018-05-19 18:00","당일",null,null,null,201803050266,"-"]
[449,"경남","진주","가야사봉 T/L","154kV 사봉분기(증)T/L 건설공사","154kV 가야-사봉T/L No.44~50 하단작업, 전선접속, OPGW 교체","2018-05-04 07:00","2018-05-07 19:00","2018-05-11 07:00","2018-05-14 18:00","연속",null,null,null,201803060138,"-"]
[450,"경남","진주","의령동진주#2 T/L","의령S/S 154kV 의령-동진주#2T/L CB(667) 정밀점검","의령S/S 154kV 의령-동진주#2T/L CB(667) 정밀점검","2018-05-05 09:00","2018-05-06 18:30","2018-05-05 09:00","2018-05-06 18:30","연속",null,null,null,201803050300,"-"]
[451,"경남","진주","의령S/S 154kV #1 BUS TIE CB","의령S/S 154kV #1 BUS TIE CB(6100) 정밀점검","의령S/S 154kV #1 BUS TIE CB(6100) 정밀점검 - 황색CB","2018-05-15 09:00","2018-05-16 18:30","2018-05-15 09:00","2018-05-16 18:30","연속",null,null,null,201803050303,"-"]
[452,"경남","진주","하동S/S 154kV #1 BUS TIE CB","하동S/S 154kV BUS TIE(6100) CB 보통점검","하동S/S 154kV BUS TIE(6100) CB 보통점검 - 황색CB","2018-05-25 09:30","2018-05-25 18:30","2018-05-25 09:30","2018-05-25 18:30","당일",null,null,null,201803050306,"-"]
[453,"경남","진주","하동하동화력#1 T/L","154kV 하동-하동화력#1T/L 전선교체 및 피뢰기설치공사(18년)","154kV 하동-하동화력#1T/L 10~12호, 13~14호 전선교체 및 피뢰기 설치(전구간)","2018-05-23 07:00","2018-05-26 18:00","2018-05-23 07:00","2018-05-26 18:00","매일",null,null,null,201803050008,"-"]
[454,"경남","진주","산청함양 T/L","154kV 산청-함양T/L 애자련보강","154kV 산청-함양T/L 애자련보강공사 No.79∼81호 No.94∼95호, No.109∼110호, No.122∼123호","2018-05-26 07:00","2018-05-27 18:00","2018-05-26 07:00","2018-05-27 18:00","당일",null,null,null,201802060217,"-"]
[455,"경남","통영","통영거제#1 T/L","거제S/S 154kV #3Sh.C GIS 정밀점검(시험가압)","1. 거제S/S 154kV #3Sh.C GIS 정밀점검(시험가압)","2018-05-26 17:30","2018-05-26 18:30","2018-05-26 17:30","2018-05-26 18:30","당일",null,null,null,201803060295,"-"]
[456,"경남","통영","통영거제#1 T/L","거제S/S 154kV #1Sh.C MAIN GIS 정밀점검(시험가압)","1. 거제S/S 154kV #1Sh.C MAIN GIS 정밀점검(시험가압)","2018-05-22 17:30","2018-05-22 18:30","2018-05-22 17:30","2018-05-22 18:30","당일",null,null,null,201803060294,"-"]
[457,"경남","통영","고성통영 T/L","154kV 고성-통영T/L YPP 보호계전기 오동작방지대책","1. 고성S/S 154kV 고성-통영T/L YPP 보호계전기 오동작방지 대책시행 2. 통영S/S 154kV 고성-통영T/L YPP 보호계전기 오동작방지 대책시행 - 제작사, 계통 시험파트 입회","2018-05-22 09:30","2018-05-22 17:00","2018-05-22 09:30","2018-05-22 17:00","당일",null,null,null,201803060298,"-"]
[458,"경남","통영","신고성삼천포#1 T/L","삼천포S/S #2M.Tr 1차 GIS 정밀점검(시험가압)","1. 삼천포S/S #2M.Tr 1차 GIS 정밀점검(시험가압)","2018-05-20 17:30","2018-05-20 18:30","2018-05-20 17:30","2018-05-20 18:30","당일",null,null,null,201803060306,"-"]
[459,"경남","통영","삼천포사천#1 T/L","154kV 삼천포-사천T/L 접속개소 전선교체공사","154kV 삼천포-사천#2T/L 접속개소 전선교체공사 공사구간 : 34~39, 51~53, 53~55호","2018-05-08 07:00","2018-05-12 18:30","2018-05-08 07:00","2018-05-12 18:30","연속",null,null,null,201803140155,"-"]
[460,"경남","통영","신고성삼천포#2 T/L","삼천포S/S #2M.Tr 1차 GIS 정밀점검(시험가압)","1. 삼천포S/S #2M.Tr 1차 GIS 정밀점검(시험가압)","2018-05-18 17:30","2018-05-18 18:30","2018-05-18 17:30","2018-05-18 18:30","당일",null,null,null,201803060292,"-"]
[461,"경남","통영","삼천포사천#2 T/L","154kV 삼천포-사천T/L 접속개소 전선교체공사","154kV 삼천포-사천#2T/L 접속개소 전선교체공사 공사구간 : 34~39, 51~53, 53~55호","2018-05-13 07:00","2018-05-17 18:30","2018-05-13 07:00","2018-05-17 18:30","연속",null,null,null,201803060122,"-"]
[462,"경남","통영","신고성삼천포#2 T/L","삼천포S/S 삼천포-사천#2T/L GIS 정밀점검(시험가압)","1. 삼천포S/S 삼천포-사천#2T/L GIS 정밀점검(시험가압)","2018-05-17 17:30","2018-05-17 18:30","2018-05-17 17:30","2018-05-17 18:30","당일",null,null,null,201803060293,"-"]
[463,"경남","통영","신고성거제#2 T/L","154kV 신고성-거제#2T/L 정밀점검","154kV 신고성-거제#2T/L 송전선로 정밀점검 점검구간 : S/T~198호(197기)","2018-05-12 08:00","2018-05-13 18:00","2018-05-12 08:00","2018-05-13 18:00","매일",null,null,null,201803060123,"-"]
[464,"경남","통영","신고성통영 T/L","154kV 신고성-통영T/L 송전선로 정밀점검","154kV 신고성-통영T/L 송전선로 정밀점검 점검구간 : 신고성S/T~149호","2018-05-26 08:00","2018-05-27 17:30","2018-05-26 08:00","2018-05-27 17:30","매일",null,null,null,201803060130,"-"]
[465,"경남","통영","통영거제#1 T/L","통영S/S #3M.Tr 1차 GIS 정밀점검(시험가압)","1. 통영S/S #3M.Tr 1차 GIS 정밀점검(시험가압)","2018-05-05 17:30","2018-05-05 18:30","2018-05-05 17:30","2018-05-05 18:30","당일",null,null,null,201803060285,"-"]
[466,"경남","통영","통영거제#2 T/L","통영S/S #2M.Tr 1차 GIS 정밀점검(시험가압)","1. 통영S/S #2M.Tr 1차 GIS 정밀점검(시험가압)","2018-05-01 17:30","2018-05-01 18:30","2018-05-01 17:30","2018-05-01 18:30","당일",null,null,null,201803060287,"-"]
[467,"경남","함안","가야개양 T/L\n(가야-사봉#2T/L)","154kV 사봉분기(증)T/L 건설공사","차폐각 확보를 위한 GW 이설","2018-05-06 07:00","2018-05-06 11:00","2018-05-13 07:00","2018-05-13 11:00","당일",null,null,null,201803160026,"-"]
[468,"경남","함안","수출월림#2 T/L","수출S/S 수출-월림#2T/L 647 GIS 조작시험","수출S/S 수출-월림#2T/L 647 GIS 조작시험","2018-05-24 13:30","2018-05-24 17:30","2018-05-24 13:30","2018-05-24 17:30","당일",null,null,null,201803060167,"-"]
[469,"경남","함안","수출월림#1 T/L","수출S/S 수출-월림#1T/L 637 GIS 조작시험","수출S/S 수출-월림#1T/L 637 GIS 조작시험","2018-05-24 09:30","2018-05-24 13:30","2018-05-24 09:30","2018-05-24 13:30","당일",null,null,null,201803060166,"-"]
[470,"경남","함안","신마산차룡#2 T/L","154kV 신마산-서마산 등 10개T/L 전선교체 및 정비공사","송전선로용 피뢰기 설치 신마산-차룡 #2T/L (1~5호)","2018-05-02 07:00","2018-05-02 18:00","2018-05-02 07:00","2018-05-02 18:00","당일",null,null,null,201803060088,"-"]
[471,"경남","함안","신마산마산#1 T/L","154kV 신마산-서마산 등 10개T/L 전선교체 및 정비공사","신마산-서마산T/L 전선교체공사 안전이격거리 확보","2018-05-04 06:30","2018-05-07 18:30","2018-05-04 06:30","2018-05-07 18:30","연속",null,null,null,201803050143,"-"]
[472,"경남","함안","신마산마산#2 T/L","154kV 신마산-서마산 등 10개T/L 전선교체 및 정비공사","신마산-서마산T/L 전선교체 및 신마산-마산#1T/L 피뢰기 설치로 인한 신마산-마산#2T/L 안전이격거리 확보","2018-05-06 06:30","2018-05-06 12:00","2018-05-06 06:30","2018-05-06 12:00","당일",null,null,null,201803050148,"-"]
[473,"경남","함안","신마산중리#2 T/L","신마산-중리#2T/L GIS 보통점검 및 조작시험","신마산S/S 647 GIS 보통점검 및 PT,LA 보통 중리S/S 647 GIS 조작시험","2018-05-22 09:30","2018-05-22 17:30","2018-05-22 09:30","2018-05-22 17:30","당일",null,null,null,201803060187,"-"]
[474,"경남","함안","신마산마산#2 T/L","154kV 신마산-서마산 등 10개T/L 전선교체 및 정비공사","신마산-진동T/L 전선교체공사 안전이격거리 확보","2018-05-19 06:30","2018-05-20 18:30","2018-05-19 06:30","2018-05-20 18:30","연속",null,null,null,201803050144,"-"]
[475,"경남","함안","중리가야#2 T/L","중리분기T/L OPGW 증설공사","154kV 중리T/L 26호~가야S/T구간 가공지선 → OPGW 교체(1.6km)","2018-05-26 06:00","2018-05-27 18:00","2018-05-26 06:00","2018-05-27 18:00","연속",null,null,null,201803060112,"-"]
[476,"경남","함안","신마산중리#1 T/L","중리분기T/L OPGW 증설공사","154kV 중리T/L 26호~가야S/T구간 가공지선 → OPGW 교체(1.6km)","2018-05-26 06:00","2018-05-27 18:00","2018-05-26 06:00","2018-05-27 18:00","연속",null,null,null,201803060111,"-"]
[477,"경남","함안","중리가야#1 T/L","중리-가야#1T/L GIS 조작시험","중리-가야#1T/L GIS 조작시험 중리S/S 627 GIS 조작시험 가야S/S 647 GIS 조작시험","2018-05-20 09:30","2018-05-20 17:30","2018-05-20 09:30","2018-05-20 17:30","당일",null,null,null,201803060147,"-"]
[478,"경남","함안","신마산칠서#2 T/L","154kV 칠서-창녕#1T/L 정밀점검 안전이격차","154kV 칠서-창녕#1T/L 1-17호 정밀점검 안전이격차","2018-05-13 09:00","2018-05-13 18:00","2018-05-13 09:00","2018-05-13 18:00","당일",null,null,null,201802260133,"-"]
[479,"경남","함안","신마산칠서#1 T/L","154kV 칠서-창녕#2T/L 정밀점검 안전이격차","154kV 칠서-창녕#2T/L 1-17호 정밀점검 안전이격차","2018-05-12 09:00","2018-05-12 18:00","2018-05-12 09:00","2018-05-12 18:00","당일",null,null,null,201802260128,"-"]
[480,"경북","직할","동안동임하HP T/L","송전선로 점밀점검 및 애자교체","송전선로 점밀점검 및 애자교체","2018-05-08 07:00","2018-05-09 18:00","2018-05-08 07:00","2018-05-09 18:00","연속",{"$nulls":4},"-"]
[481,"부산울산","서부산","서부산S/S 154kV #60 BUS","서부산부민#1T/L 준공선로 시험검사","서부산부민#1T/L 준공선로 시험검사","2018-05-11 11:00","2018-05-11 11:30","2018-05-11 11:00","2018-05-11 11:30","연속",{"$nulls":4},"-"]
[482,"부산울산","서부산","서부산S/S 154kV #61 BUS","서부산신평#1T/L 준공선로 시험검사","서부산신평#1T/L 준공선로 시험검사","2018-05-11 11:00","2018-05-11 11:30","2018-05-11 11:00","2018-05-11 11:30","연속",{"$nulls":4},"-"]

{"sheet":"한수원","index":3,"n_rows":15,"n_cols":20,"rows_kept":15,"cut":false,"hidden":false,"merged":[[0,0,0,6],[4,12,5,12],[4,0,5,0],[4,1,5,1],[4,2,5,2],[4,3,5,3],[4,4,5,4],[4,5,5,5],[4,6,4,7],[4,8,4,9],[4,10,5,10],[4,11,5,11],[4,19,5,19],[4,13,5,13],[4,14,5,14],[4,15,5,15],[4,16,5,16],[4,17,5,17],[4,18,5,18]]}
["2018년도 05월 휴전계획표(한국수력원자력)"]
[]
[]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"고리본부","1발전소","#2 주변압기","고리2호기 29차 O/H 중 주변압기 점검\n* 조작차단기 : CB 7300, 7372","○ 주변압기 및 소내보조변압기 일반점검","2018-05-15T09:00:00","2018-05-25T18:00:00","2018-05-15T09:00:00","2018-05-25T18:00:00","연속","Y"]
[2,"월성본부","1발전소","#2 기동용변압기","월성2호기 17차 O/H 중 소내전원 절체시험\n* 조작차단기 : CB 7400, 7472","○ SST -> UST 소내전원절체시험","2018-05-16T09:00:00","2018-05-17T18:00:00","2018-05-16T09:00:00","2018-05-17T18:00:00","수시\n조작","Y"]
[3,"월성본부","1발전소","#2 주변압기","월성2호기 17차 O/H 중 소내전원 절체시험\n* 조작차단기 : CB 7300, 7372","○ UST -> SST 소내전원절체시험","2018-05-16T09:00:00","2018-05-17T18:00:00","2018-05-16T09:00:00","2018-05-17T18:00:00","수시\n조작","Y"]
[4,"월성본부","1발전소","#2 주변압기","월성2호기 17차 O/H 중 계통연결 대기\n* 조작차단기 : CB 7300, 7372","○ 계통연결전 IPB링크 조립 및 대기\n○ 발전기 성능시험","2018-05-17T18:00:00","2018-05-25T18:00:00","2018-05-17T18:00:00","2018-05-25T18:00:00","연속","Y"]
[5,"월성본부","3발전소","신#1 대기보조변압기","신월성1호기 4차 O/H 중 대기보조변압기 점검\n* 조작차단기 : CB 7300, 7372","○ 대기보조변압기 일반점검","2018-05-08T09:00:00","2018-05-17T18:00:00","2018-05-08T09:00:00","2018-05-17T18:00:00","연속","Y"]
[6,"월성본부","3발전소","신#1 주변압기","신월성1호기 4차 O/H 중 소내전원 절체시험\n* 조작차단기 : CB 7400, 7472","○ 주변압기 모의신호에 의한 차단기 개방","2018-05-24T09:00:00","2018-05-25T18:00:00","2018-05-24T09:00:00","2018-05-25T18:00:00","수시\n조작","Y"]
[7,"한빛본부","2발전소","#3 주변압기","한빛3호기 17차 O/H 중 GIB/GIS 개선\n* 조작차단기 : CB 7700, 7771","○ 주변압기측 GIB/GIS 교체","2018-05-24T10:00:00","2018-08-13T23:00:00","2018-05-24T10:00:00","2018-08-13T23:00:00","연속","Y"]
[8,"한울본부","2발전소","#4 주변압기","한울4호기 13차 O/H 중 주변압기 교체\n* 조작차단기 : CB 7A00, 7A72","○ 주변압기 A,B,C상 교체\n○ 소내보조변압기 01M/N 정밀점검","2018-05-29T13:00:00","2018-07-12T18:00:00","2018-05-29T13:00:00","2018-07-12T18:00:00","연속","Y"]
[9,"한울본부","2발전소","#4 대기보조변압기","한울4호기 13차 O/H 중 대기보조변압기 점검\n* 조작차단기 : CB 7700, 7772,\n                   CB 7800, 7872","○ 대기보조변압기 02M/N 일반점검","2018-05-18T10:00:00","2018-05-29T10:00:00","2018-05-18T10:00:00","2018-05-29T10:00:00","연속","Y"]

{"sheet":"중부","index":4,"n_rows":8,"n_cols":21,"rows_kept":8,"cut":false,"hidden":false,"merged":[[2,14,3,14],[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,15,3,15],[2,16,3,16],[2,17,3,17],[2,18,3,18],[2,19,3,19]]}
["2018년도 5월 휴전계획(한국중부발전)"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"보령발전본부","보령복합","ST#2 주변압기\n(CB 7400, 7472)","계획예방정비관련\n전기설비 점검","주변압기 점검 및 GCB 점검","2018-05-08T09:00:00","2018-06-29T18:00:00","2018-05-08T09:00:00","2018-06-29T18:00:00","연속"]
[2,"인천발전본부","복합1호기","GT #1,2 \n(CB7500, CB7572)","계획예방정비공사(A급)","변압기, GCB(IPB포함) 및 보호계전기 교체","2018-05-09T09:00:00","2018-05-30T18:00:00","2018-05-09T09:00:00","2018-05-30T18:00:00","연속",{"$nulls":9},"Y"]
[3,"인천발전본부","복합1호기","ST #1 \n(CB7600, CB7672)","계획예방정비공사(A급)","변압기, GCB(IPB포함) 및 보호계전기 교체","2018-05-31T09:00:00","2018-06-12T18:00:00","2018-05-31T09:00:00","2018-06-12T18:00:00","연속",{"$nulls":9},"Y"]
[4,"청양변전소","신보령","청양-신보령화력T/L","항공장애표시구 설치","항공장애표시구 설치","2018-05-08 9:00","2018-05-27 17:00","2018-05-08 9:00","2018-05-27 17:00","연속"]