{"text_format":"2","workbook":"xlsx","n_sheets":5,"sheets":["765송부","345송부","154송부","한수원","중부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":10,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":8,"n_cols":16,"rows_kept":8,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"\"2018년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2018년도 6월 휴전계획서"}]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #2 M.Tr A-1","신가평S/S 765kV #2M.Tr 유면계 불량 하자 보수","신가평S/S 765kV #2M.Tr 유면계 불량 하자 보수","2018-06-11 09:00","2018-06-15 18:00","2018-06-11 09:00","2018-06-15 18:00","연속",null,null,null,201804050134]
[2,"경기","성남","신안성S/S 765kV #2 BUS","신안성S/S 765kV 모선보호반 대체","신안성S/S 765kV 모선보호반 대체","2018-06-14 09:00","2018-06-30 18:00","2018-06-18 10:00","2018-06-29 18:00","연속",null,null,null,201804120376]
[3,"경기","성남","신안성신가평 T/L","2018~2019년 성남전력 송전정비 협력회사 총액공사","- 765kV 신안성-신가평T/L 항공장애표시도장(10기)","2018-06-25 07:00","2018-07-15 18:00","2018-06-25 07:00","2018-07-15 18:00","연속",null,null,null,201804130217]
[4,"대전충남","서산","당진T/P 765kV #2 BUS","당진화력 #2BUS 인하선 정비공사","당진화력 #2BUS 인하선 정비공사","2018-06-19 09:00","2018-06-21 18:00","2018-06-19 09:00","2018-06-21 18:00","매일",null,null,null,201804160269]

{"sheet":"345송부","index":1,"n_rows":229,"n_cols":16,"rows_kept":229,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"\"2018년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2018년도 6월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","중부S/S #3 M.Tr A","2018년 중부변전소 362kV GIS 정밀점검공사","#3M.Tr 1차 GIS 정밀점검","2018-06-01 08:00","2018-06-19 18:00","2018-06-01 08:00","2018-06-19 18:00","연속",null,null,null,201804090691]
[2,"서울","중부","중부S/S 345kV #1 BUS","2018년 중부변전소 362kV GIS 정밀점검공사","345kV #1 BUS측 DS/ES 정밀점검","2018-06-25 08:00","2018-06-27 18:00","2018-06-25 08:00","2018-06-27 18:00","연속",null,null,null,201804090697]
[3,"서울","중부","중부S/S 345kV #2 BUS","2018년 중부변전소 362kV GIS 정밀점검공사","345kV #2 BUS측 DS/ES 정밀점검","2018-06-20 08:00","2018-06-22 18:00","2018-06-20 08:00","2018-06-22 18:00","연속",null,null,null,201804090696]
[4,"남서울","강남","신양재S/S #1 M.Tr A","신양재S/S 변전설비 기기점검공사","362,170kV GIS 개폐타임측정 및 조작시험 23kV VCB 및 소내변압기 보통점검","2018-06-05 10:00","2018-06-05 18:00","2018-06-05 10:00","2018-06-05 18:00","당일",null,null,null,201804130345]
[5,"남서울","강남","신양재S/S #2 M.Tr A","신양재S/S 변전설비 기기점검공사","362,170kV GIS 개폐타임측정 및 조작시험 23kV VCB 및 소내변압기 보통점검","2018-06-07 10:00","2018-06-07 18:00","2018-06-07 10:00","2018-06-07 18:00","당일",null,null,null,201804130346]
[6,"남서울","강남","신양재S/S #3 M.Tr A","신양재S/S 변전설비 기기점검공사","362kV GIS 개폐타임측정 및 조작시험 170kV GIS 보통점검","2018-06-08 10:00","2018-06-08 18:00","2018-06-08 10:00","2018-06-08 18:00","당일",null,null,null,201803130163]
[7,"남서울","강남","신양재S/S 345kV #2 BUS","신양재S/S 362kV GIS 모선DS 내부점검","345kV #4Sh.R GIS 모선DS(7452) 내부점검","2018-06-01 10:00","2018-06-02 18:00","취소","취소","연속",null,null,null,201804130343]
[8,"남서울","강남","신양재S/S 345kV #4 Sh.R","신양재S/S 362kV GIS 모선DS 내부점검","345kV #4Sh.R GIS 모선DS(7452) 내부점검","2018-06-01 10:00","2018-06-02 18:00","2018-06-01 10:00","2018-06-02 18:00","연속",null,null,null,201804130344]
[9,"남서울","강남","신양재S/S 신성남-신양재#2T/L CB (7271)","신양재S/S 362kV GIS 개폐타임측정 및 조작시험","362kV GIS(7271) 개폐타임측정 및 조작시험","2018-06-11 10:00","2018-06-11 18:00","2018-06-11 10:00","2018-06-11 18:00","당일",null,null,null,201804130347]
[10,"남서울","동서울","동서울S/S #1 M.Tr A","170kV GCB 교체","170kV GCB 교체, 1,3차 조작시험","2018-06-18 09:00","2018-06-20 18:00","2018-06-18 09:00","2018-06-20 18:00","연속",null,null,null,201804170266]
[11,"남서울","동서울","동서울S/S #2 M.Tr A","차단기 조작시험","1,2,3차 조작시험","2018-06-14 09:00","2018-06-15 18:00","2018-06-14 09:00","2018-06-15 18:00","연속",null,null,null,201804170259]
[12,"남서울","동서울","동서울S/S #3 M.Tr A","170kV GCB 교체","170kV GCB 교체","2018-06-21 09:00","2018-06-23 18:00","2018-06-21 09:00","2018-06-23 18:00","연속",null,null,null,201804170268]
[13,"남서울","동서울","신성남동서울#1 T/L","2018년도 가공송전 순시점검 위탁공사 정밀점검","송전철탑 정밀점검(승탑 후 수목, 부식상태, 전선처짐, 금구류 이상유무, 애자파손 여부, 낙뢰표시기 정동작 여부, 볼트체결 상태 등 점검)","2018-06-07 09:00","2018-06-08 18:00","2018-06-07 09:00","2018-06-08 18:00","연속",null,null,null,201804200092]
[14,"남서울","영등포","신광명S/S #2 M.Tr A","영서S/S 154kV 이하 옥외철구 GIS화 공사","가공-EBA 접속, 보호반 시험","2018-06-11 08:00","2018-06-22 18:00","2018-06-11 08:00","2018-06-22 18:00","연속",null,null,null,201803200049]
[15,"남서울","직할","영등포S/S #1 M.Tr A","(주)새롬프로텍 345kV 변압기 보호반 성능 개선","64V 관련 로직 수정","2018-06-04 14:00","2018-06-04 18:00","2018-06-05 10:00","2018-06-05 13:00","당일",null,null,null,201804090458]
[16,"남서울","직할","영등포S/S #2 M.Tr A","(주)새롬프로텍 345kV 변압기 보호반 성능 개선","64V 관련 로직 수정","2018-06-05 10:00","2018-06-05 14:00","2018-06-05 13:00","2018-06-05 16:00","당일",null,null,null,201804090462]
[17,"남서울","직할","영등포S/S #3 M.Tr A","(주)새롬프로텍 345kV 변압기 보호반 성능 개선","64V 관련 로직 수정","2018-06-05 14:00","2018-06-05 18:00","2018-06-05 16:00","2018-06-05 19:00","당일",null,null,null,201804090463]
[18,"인천","김포","신김포S/S #2 M.Tr A","신김포S/S 345kV #2M.Tr 보통점검","신김포S/S 345kV #2M.Tr 보통점검","2018-06-20 10:00","2018-06-21 18:00","2018-06-20 10:00","2018-06-21 18:00","연속",null,null,null,201804120038]
[19,"인천","김포","가정 345kV #1 Sh.R CB","가정개폐소 345kV #1Sh.R 하자복구공사","- 345kV #1Sh.R 해체 및 반출 - 345kV #1Sh.R 반입 및 조립","2018-06-01 09:00","2018-11-30 18:00","2018-06-01 09:00","2018-11-30 18:00","연속",null,null,null,201804020103]
[20,"인천","김포","신김포S/S 345KV 70-71 SEC CB","신김포S/S 345kV 70-71 BUS-SEC CB 조작시험","신김포S/S 345kV 70-71 BUS-SEC CB 조작시험","2018-06-15 10:00","2018-06-15 13:00","2018-06-15 10:00","2018-06-15 13:00","당일",null,null,null,201804120049]
[21,"인천","김포","신김포S/S 345KV 75-76 SEC CB","신김포S/S 345kV 75-76 BUS-SEC CB 조작시험","신김포S/S 345kV 75-76 BUS-SEC CB 조작시험","2018-06-15 13:00","2018-06-15 16:00","2018-06-15 13:00","2018-06-15 16:00","당일",null,null,null,201804120050]
[22,"인천","김포","신김포S/S 345KV 신김포 -신파주#1T/L TIE CB","신김포S/S 345kV 신김포-신파주#1T/L TIE CB 조작시험","신김포S/S 345kV 신김포-신파주#1T/L TIE 7300 CB 조작시험","2018-06-22 10:00","2018-06-22 15:00","2018-06-22 10:00","2018-06-22 15:00","당일",null,null,null,201804120047]
[23,"인천","김포","신김포신인천CC T/L","신김포-신경서간 광케이블 시설공사","신김포-신경서간 광케이블 시설 OPGW : 13.4Km(가공지선 -&gtOPGW), OFC : 5.3Km 시설","2018-06-01 09:00","2018-06-14 18:00","2018-06-01 09:00","2018-06-14 18:00","연속",null,null,null,201804040079]
[24,"인천","김포","신김포신파주#2 T/L","신김포S/S 345kV 신김포-신파주#2T/L GIS 가스 누기보수","345kV 신김포-신파주#2T/L 7571 GIS 가스 누기보수","2018-06-23 10:00","2018-06-24 18:00","2018-06-23 10:00","2018-06-24 18:00","연속",null,null,null,201804170360]
[25,"인천","시흥","신시흥영흥TP#1 T/L","345kV 신시흥영흥#1T/L 피뢰기 및 항공장애표시구 설치공사","345kV 신시흥영흥#1T/L 피뢰기 및 항공장애표시구 설치공사","2018-06-02 08:00","2018-06-07 18:00","2018-06-01 08:00","2018-06-08 18:00","연속",null,null,null,201803130052]
[26,"인천","시흥","영흥T/P #1G/T 1차 CB (7172)","영흥T/P #1G/T 1차 CB(7172) 동작시험","영흥T/P #1G/T 1차 CB(7172) 동작시험","2018-06-12 10:30","2018-06-12 18:00","2018-06-12 10:30","2018-06-12 18:00","당일",null,null,null,201804130284]
[27,"인천","시흥","영흥T/P #2G/T 1차 CB (7272)","영흥T/P #2G/T 1차 CB(7272) 동작시험","영흥T/P #2G/T 1차 CB(7272) 동작시험","2018-06-05 10:30","2018-06-05 18:00","2018-06-05 10:30","2018-06-05 18:00","당일",null,null,null,201804130270]
[28,"인천","시흥","영흥T/P 영흥TP연락#1T/L-#1 G/T 1차 CB (7100)","영흥TP연락#1T/L-#1 G/T 1차 CB(7100) 동작시험","영흥T/P 영흥TP연락#1T/L-#1 G/T 1차 CB(7100) 동작시험","2018-06-11 10:30","2018-06-11 18:00","2018-06-11 10:30","2018-06-11 18:00","당일",null,null,null,201804130283]
[29,"인천","시흥","영흥T/P 영흥TP연락#2T/L-#2G/T 1차 CB (7200)","영흥T/P 영흥TP연락#2T/L-#2G/T 1차 CB(7200) 동작시험","영흥T/P 영흥TP연락#2T/L-#2G/T 1차 CB(7200) 동작시험","2018-06-04 10:30","2018-06-04 18:00","2018-06-04 10:30","2018-06-04 18:00","당일",null,null,null,201804130269]
[30,"인천","시흥","영흥1TP영흥2TP #2T/L","345kV 영흥연락#2T/L 피뢰기 및 항공장애표시구 설치공사","345kV 영흥연락#2T/L 피뢰기 및 항공장애표시구 설치공사","2018-06-06 08:00","2018-06-07 18:00","2018-06-07 08:00","2018-06-08 18:00","연속",null,null,null,201803130055]
[31,"인천","인천","서인천C/C 345kV #75 BUS","345kV 서인천C/C 용량부족 GIS 대체공사","-#75BUS 모선철거 및 설치(신규분) - 모선일부구간 가스회수 - 75BUS용 모선DS(3조) 교체작업","2018-06-26 10:00","2018-07-10 17:00","2018-06-28 09:00","2018-07-12 17:00","연속",null,null,null,201804020041]
[32,"인천","인천","신가좌S/S #1 M.Tr A","신가좌S/S 345㎸ 용량부족 GIS 대체공사","신가좌S/S 345㎸ 용량부족 GIS 대체공사 - 71Bay 철거 및 설치 (3CB) - 제어케이블 분리 및 결선 - 기타 부대작업","2018-06-18 09:00","2018-06-18 18:00","2018-06-18 09:00","2018-06-18 18:00","연속",null,null,null,201804030070]
[33,"인천","인천","신경서인천CC#2T/L-가정인천CC#1T/L CB (7400)","인천복합S/Y 7400 GIS 조작시험","인천복합S/Y 7400 GIS 조작시험","2018-06-07 09:00","2018-06-07 14:00","2018-06-07 09:00","2018-06-07 14:00","당일",null,null,null,201804100192]
[34,"인천","인천","인천CC S/Y #3S/T CB (7B72)","인천복합S/Y 7B72 GIS 조작시험","인천복합S/Y 7B72 GIS 조작시험","2018-06-04 15:00","2018-06-04 18:00","2018-06-04 15:00","2018-06-04 18:00","당일",null,null,null,201804100191]
[35,"인천","인천","인천CC S/Y #5,6G/T CB (7B71)","인천복합S/Y 7B71 GIS 조작시험","인천복합S/Y 7B71 GIS 조작시험","2018-06-04 09:00","2018-06-04 12:00","2018-06-04 09:00","2018-06-04 12:00","당일",null,null,null,201804100189]
[36,"인천","인천","인천CC S/Y #5,6G/T-#3S/T CB (7B00)","인천복합S/Y 7B00 GIS 조작시험","인천복합S/Y 7B00 GIS 조작시험","2018-06-04 12:00","2018-06-04 15:00","2018-06-04 12:00","2018-06-04 15:00","당일",null,null,null,201804100190]
[37,"인천","인천","인천CC S/Y 가정인천CC#1T/L CB (7472)","인천복합S/Y 7472 GIS 조작시험","인천복합S/Y 7472 GIS 조작시험","2018-06-07 14:00","2018-06-07 18:00","2018-06-07 14:00","2018-06-07 18:00","당일",null,null,null,201804100193]
[38,"인천","인천","인천CC S/Y 신경서-인천CC#1T/L CB (7271)","인천복합S/Y 7271 GIS 조작시험","인천복합S/Y 7271 GIS 조작시험","2018-06-01 09:00","2018-06-01 14:00","2018-06-01 09:00","2018-06-01 14:00","당일",null,null,null,201804100186]
[39,"인천","인천","인천CC S/Y 신경서-인천CC#1T/L-TIE CB (7200)","인천복합S/Y 7200 GIS 조작시험","인천복합S/Y 7200 GIS 조작시험","2018-06-01 14:00","2018-06-01 18:00","2018-06-01 14:00","2018-06-01 18:00","당일",null,null,null,201804100187]
[40,"인천","인천","인천CC S/Y 인천복합 #2 S/T CB (7671)","인천복합S/Y 7671 GIS 조작시험","인천복합S/Y 7671 GIS 조작시험","2018-06-27 14:00","2018-06-27 18:00","2018-06-27 14:00","2018-06-27 18:00","당일",null,null,null,201804100196]
[41,"인천","인천","인천CC S/Y 인천복합 #3,4 G/T CB (7571)","인천복합S/Y 7571 GIS 조작시험","인천복합S/Y 7571 GIS 조작시험","2018-06-27 09:00","2018-06-27 14:00","2018-06-27 09:00","2018-06-27 14:00","당일",null,null,null,201804100195]
[42,"경기북부","고양","신덕은S/S #4 M.Tr A","2018년 상반기 고양전력지사 170kV GIS 정밀점검공사","신덕은S/S #4M.Tr 2차(6444) GIS 정밀점검","2018-06-01 09:30","2018-06-02 18:00","2018-06-11 09:30","2018-06-12 18:00","연속",null,null,null,201803070208]
[43,"경기북부","고양","신파주S/S #1 SVC Tr CB","신파주S/S 345kV SVC 보통점검","신파주S/S 345kV SVC 보통점검","2018-06-18 09:00","2018-06-29 18:00","2018-06-18 09:00","2018-06-29 18:00","연속",null,null,null,201804160006]
[44,"경기북부","고양","신파주S/S 70-71 SEC GIS","18년도 고양전력지사 변전협력회사총액공사(70-71GIS조작시험)","신파주변전소 70-71 GIS 조작시험","2018-06-20 10:00","2018-06-20 12:00","2018-06-20 10:00","2018-06-20 12:00","당일",null,null,null,201804130201]
[45,"경기북부","고양","신파주S/S 75-76 SEC GIS","18년도 고양전력지사 변전협력회사총액공사(75-76GIS조작시험)","신파주변전소 75-76 GIS 조작시험","2018-06-20 13:00","2018-06-20 15:00","2018-06-20 13:00","2018-06-20 15:00","당일",null,null,null,201804130203]
[46,"경기북부","구리","동서울미금#2 T/L","345kV 신의정부-미금T/L 전선접속개소 전선교체공사","345kV 신의정부-미금#1,2T/L 전력선 교체: No.1.2~4,No.29~33 (상단 345kV 신의정부-미금#1,2T/L 작업 안전을 위한 병행하단 휴전)","2018-06-15 09:00","2018-06-17 18:00","취소","취소","연속",null,null,null,201803110017]
[47,"경기북부","구리","동서울미금#2 T/L","345kV 신의정부-미금T/L 전선접속개소 전선교체공사","345kV 신의정부-미금#1,2T/L 전력선 교체: No.1.2~4,No.29~33 (상단 345kV 신의정부-미금#1,2T/L 작업 안전을 위한 병행하단 휴전)","2018-06-23 09:00","2018-06-24 18:00","취소","취소","연속",null,null,null,201803110018]
[48,"경기북부","구리","신가평S/S 345kV #3 Sh.R","2018년 구리전력지사 변전정비회사 총액공사","ㅇ 345kV #3Sh.R 보통점검 ㅇ 345kV #3Sh.R 냉각장치(라디에이터) 세정작업","2018-06-04 08:00","2018-06-05 18:00","2018-06-04 08:00","2018-06-05 18:00","연속",null,null,null,201804180087]
[49,"경기북부","구리","신가평S/S 345kV #4 Sh.R","2018년 구리전력지사 변전정비회사 총액공사","ㅇ 345kV #4Sh.R 보통점검 ㅇ 345kV #4Sh.R 냉각장치(라디에이터) 세정작업","2018-06-07 08:00","2018-06-07 18:00","2018-06-07 08:00","2018-06-07 18:00","당일",null,null,null,201804180088]
[50,"경기북부","구리","신가평미금#1 T/L","2018~19년도 구리전력지사 가공송전정비 협력회사 총액공사","345kV 신가평-미금#1T/L 불량압축인류크램프 교체공사 - 대상 : No.81호","2018-06-28 07:30","2018-06-28 18:00","2018-06-28 07:30","2018-06-28 18:00","당일",null,null,null,201804050309]
[51,"경기북부","직할","신의정부미금#1 T/L","345kV 신의정부-미금T/L 전선접속개소 전선교체공사","345kV 신의정부-미금#1,2T/L 전력선 교체: No.1.2~4,No.29~33","2018-06-15 09:00","2018-06-20 18:00","취소","취소","연속",null,null,null,201803110015]
[52,"경기북부","직할","신의정부미금#1 T/L","345kV 신의정부-미금T/L 전선접속개소 전선교체공사","345kV 신의정부-미금#1,2T/L 전력선 교체: No.1.2~4,No.29~33","2018-06-30 09:00","2018-07-04 18:00","취소","취소","연속",null,null,null,201803150176]
[53,"경기북부","직할","신의정부미금#2 T/L","345kV 신의정부-미금T/L 전선접속개소 전선교체공사","345kV 신의정부-미금#1,2T/L 전력선 교체: No.1.2~4,No.29~33","2018-06-21 09:00","2018-06-29 18:00","취소","취소","연속",null,null,null,201803110016]
[54,"경기북부","직할","신파주양주#1 T/L","18년도 직할 362kV GIS 정밀점검","362kV GIS 정밀점검 - 신파주-양주#1T/L - 신파주-양주#1T/L - TIE","2018-06-03 09:00","2018-06-07 18:00","2018-06-03 09:00","2018-06-07 18:00","연속",null,null,null,201804160021]
[55,"경기북부","직할","양주S/S #1 M.Tr A","양주변전소 옥외철구 GIS화 공사","주변압기 3차측 정비","2018-06-28 09:00","2018-06-30 18:00","2018-06-28 09:00","2018-06-30 18:00","연속",null,null,null,201804170464]
[56,"경기북부","직할","양주S/S #3 M.Tr A","양주변전소 옥외철구 GIS화 공사","주변압기 3차측 정비","2018-06-18 09:00","2018-06-22 18:00","2018-06-18 09:00","2018-06-22 18:00","연속",null,null,null,201804170462]
[57,"경기북부","직할","양주S/S #4 M.Tr A","양주변전소 옥외철구 GIS화 공사","주변압기 3차측 정비","2018-06-25 09:00","2018-06-27 18:00","2018-06-25 09:00","2018-06-27 18:00","연속",null,null,null,201804170463]
[58,"경기북부","직할","양주S/S 345kV #4 Sh.R CB","양주변전소 옥외철구 GIS화 공사","주변압기 3차측 정비","2018-06-18 09:00","2018-06-22 18:00","2018-06-18 09:00","2018-06-22 18:00","연속",null,null,null,201804170465]
[59,"경기","군포","신안산S/S #1 M.Tr A","345kV 신안산S/S 용량부족 GIS 대체 및 SW 증설공사","○ 345kV 신안산S/S 디지털축소형모자익 개조","2018-06-02 09:30","2018-06-03 18:30","2018-06-02 09:30","2018-06-03 18:30","연속",null,null,null,201804110213]
[60,"경기","군포","신안산S/S 345kV #70 BUS","신안산S/S BUS PRO 보호배전반 대체공사","신안산S/S BUS PRO 보호배전반 대체 - 345kV #70BUS","2018-06-18 09:00","2018-06-21 18:00","2018-06-18 09:00","2018-06-21 18:00","연속",null,null,null,201804090728]
[61,"경기","군포","신안산S/S 345kV #75 BUS","신안산S/S BUS PRO 보호배전반 대체공사","신안산S/S BUS PRO 보호배전반 대체 - 345kV #75BUS","2018-06-22 09:00","2018-06-25 18:00","2018-06-22 09:00","2018-06-25 18:00","연속",null,null,null,201804090731]
[62,"경기","군포","화성신안산 T/L","345kV 신안산S/S 용량부족 GIS 대체 및 SW 증설공사","○ 345kV 신안산S/S 디지털축소형모자익 개조공사 - 신안산S/S 건물증축 외벽공사 병행시행(경기건설지사 토건부)","2018-06-02 09:30","2018-06-03 18:30","2018-06-02 09:30","2018-06-03 18:30","연속",null,null,null,201804110212]
[63,"경기","동부","곤지암S/S #3 M.Tr A","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S #61BUS 무부하가압 용 수전변압기","2018-06-09 17:00","2018-06-10 17:00","2018-06-09 17:00","2018-06-10 17:00","연속",null,null,null,201804110007]
[64,"경기","동부","곤지암S/S #3 M.Tr A","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S #66BUS 무부하가압 용 수전변압기","2018-06-16 17:00","2018-06-17 17:00","2018-06-16 17:00","2018-06-17 17:00","연속",null,null,null,201804110015]
[65,"경기","동부","곤지암S/S 345kV #1 BUS","곤지암S/S 362kV GIS 설치공사","곤지암S/S 362kV GIS 설치공사 관련 #1BUS측 설치 - 362kV GIS(63kA, 6300A) 2CB 설치(76Bay)","2018-06-18 09:30","2018-06-24 18:00","2018-06-18 09:30","2018-06-24 18:00","연속",null,null,null,201804110020]
[66,"경기","동부","곤지암S/S 345kV #2 BUS","곤지암S/S 362kV GIS 설치공사","곤지암S/S 362kV GIS 설치공사 관련 #2BUS측 설치 - 362kV GIS(63kA, 6300A) 2CB 설치(76Bay)","2018-06-25 09:30","2018-07-01 18:00","2018-06-25 09:30","2018-07-01 18:00","연속",null,null,null,201804110021]
[67,"경기","동부","곤지암동서울#2 T/L","곤지암S/S 362kV GIS 설치공사","곤지암S/S 362kV GIS 설치공사 관련 #1BUS 무부하가압용 수전선로 - 362kV GIS(63kA, 6300A) 2CB 설치(76Bay)","2018-06-23 18:00","2018-06-24 18:00","2018-06-23 18:00","2018-06-24 18:00","연속",null,null,null,201804110023]
[68,"경기","동부","곤지암동서울#2 T/L","곤지암S/S 362kV GIS 설치공사","곤지암S/S 362kV GIS 설치공사 관련 #1BUS 무부하가압용 수전선로 - 362kV GIS(63kA, 6300A) 2CB 설치(76Bay)","2018-06-30 18:00","2018-07-01 18:00","2018-06-30 18:00","2018-07-01 18:00","연속",null,null,null,201804110025]
[69,"경기","동부","곤지암신충주#1 T/L","2018-2019년 송전정비 협력회사 총액공사(표시구교체)","0 항공장애표시구 교체 : 11-12호 등 31경간 82개 설치","2018-06-18 07:00","2018-06-22 18:00","2018-06-18 07:00","2018-06-22 18:00","연속",null,null,null,201803210152]
[70,"경기","동부","곤지암신충주#2 T/L","345kV 곤지암-신충주#2T/L OPGW 표시구교체","0 항공장애표시구 교체 : 11-12호 등 31경간 51개 설치","2018-06-23 07:00","2018-06-26 18:00","2018-06-23 07:00","2018-06-26 18:00","연속",null,null,null,201803210154]
[71,"경기","성남","서안성S/S 345kV #1 BUS","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ75Bay GIS(7571, 7500) 설치 ㅇ 기타 부대공사 x 1식","2018-06-04 09:00","2018-07-01 09:00","2018-06-04 09:00","2018-07-01 09:00","연속",null,null,null,201804130167]
[72,"경기","성남","신수원S/S #1 M.Tr A","신수원S/S #1M.Tr 2차 LA 하자점검 등","신수원S/S #61M.Tr 2차 LA 하자점검 7172 조작시험, 6144 보통점검","2018-06-26 09:00","2018-06-26 18:00","2018-06-26 09:00","2018-06-26 18:00","당일",null,null,null,201804120371]
[73,"경기","성남","신수원S/S #2 M.Tr A","신수원S/S #2M.Tr 96D 자동복귀형으로 교체","신수원S/S #2M.Tr 96D 자동복귀형으로 교체 7272 조작시험, 6244 보통점검","2018-06-02 10:00","2018-06-02 18:00","2018-06-02 10:00","2018-06-02 18:00","당일",null,null,null,201804120352]
[74,"경기","성남","신수원S/S #3 M.Tr A","신수원S/S 345kV 용량부족 GIS 대체공사","75Bay(#3M.Tr) GIS 철거 및 설치","2018-06-04 10:00","2018-07-31 18:00","2018-06-04 10:00","2018-07-31 18:00","연속",null,null,null,201804050300]
[75,"경기","성남","신수원S/S #4 M.Tr A","신수원S/S #4M.Tr 96D 자동복귀형으로 교체","신수원S/S #4M.Tr 96D 자동복귀형으로 교체","2018-06-03 10:00","2018-06-03 18:00","2018-06-03 10:00","2018-06-03 18:00","당일",null,null,null,201804120351]
[76,"경기","성남","신수원S/S 345kV #1 BUS","신수원S/S 345kV 용량부족 GIS 대체공사","75Bay(#3M.Tr) GIS (#1BUS측) 철거 및 설치","2018-06-04 10:00","2018-07-02 18:00","2018-06-04 10:00","2018-07-02 18:00","연속",null,null,null,201804050301]
[77,"경기","성남","신안성서안성#2 T/L","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ7571, 7500CB 무부하 가압","2018-06-30 09:00","2018-07-01 09:00","2018-06-30 09:00","2018-07-01 09:00","연속",null,null,null,201804130169]
[78,"경기","성남","신안성신성남#1 T/L","345kV 신안성-신성남#1T/L OPGW 표시구교체","0 항공장애표시구 교체 : 1-2호 등 5개소","2018-06-16 07:00","2018-06-16 18:00","2018-06-16 07:00","2018-06-16 18:00","연속",null,null,null,201803210172]
[79,"경기","성남","신안성신성남#2 T/L","2018-2019년 송전정비 협력회사 총액공사(표시구교체)","0 항공장애표시구 교체 : 1-2호 등 5개소","2018-06-14 07:00","2018-06-15 18:00","2018-06-14 07:00","2018-06-15 18:00","연속",null,null,null,201803210170]
[80,"경기","성남","신안성신용인#1 T/L","345kV 신안성-신성남#2T/L 가공지선 표시구교체 안전이격거리 확보","345kV 신안성-신성남#2T/L 가공지선 표시구교체 안전이격거리 확보","2018-06-14 07:00","2018-06-15 18:00","2018-06-14 07:00","2018-06-15 18:00","연속",null,null,null,201803210171]
[81,"경기","성남","신용인삼성 T/L","신수원S/S 345kV 용량부족 GIS 대체공사","75Bay(#3M.Tr) GIS 철거 및 설치 - 안전이격거리 확보","2018-06-05 10:00","2018-06-15 18:00","2018-06-05 10:00","2018-06-15 18:00","연속",null,null,null,201804050308]
[82,"강원","동해","동해S/S #1 M.Tr A","동해S/S STATCOM 설치사업","○ STATCOM 소내전원 공급용 차단기 설치(#1M.Tr 3차)","2018-06-25 09:00","2018-06-26 18:00","2018-06-25 09:00","2018-06-26 18:00","연속",null,null,null,201804020160]
[83,"강원","동해","동해S/S #3 M.Tr A","동해S/S STATCOM 설치사업","STATCOM 소내전원용 차단기 설치(#3M.Tr 3차)","2018-06-27 09:00","2018-06-28 18:00","2018-06-27 09:00","2018-06-28 18:00","연속",null,null,null,201804020161]
[84,"강원","동해","동해삼척GP#2 T/L","345kV 동해-삼척GPT/L 전선접속개소 전선교체공사","No.39~65 전선교체공사","2018-06-12 08:00","2018-06-26 18:00","2018-06-12 08:00","2018-06-26 18:00","연속",null,null,null,201804060244]
[85,"강원","동해","삼척GP #1 M.Tr CB","18년 동해전력지사 변전협력회사 총액공사","1. #1M.Tr 초기점검 2. #1M.Tr 1차 PT 초기점검 3. #1M.Tr 3차 PT 초기점검 4. #1M.Tr 2차 LA 초기점검 5. SFRA 측정 6. #1M.Tr 1차 GIS(7272, 7200) 초기점검 7. #1M.Tr 2, 3차 GIS 초기점검","2018-06-06 09:30","2018-06-08 18:00","2018-06-06 09:30","2018-06-08 18:00","연속",null,null,null,201804050035]
[86,"강원","동해","신제천동해#2 T/L","345kV 동해T/L 전선접속개소 교체공사","No.180~No.226 전선접속개소 교체 7.9c-km","2018-06-07 08:00","2018-06-21 18:00","2018-06-07 08:00","2018-06-21 18:00","연속",null,null,null,201803300059]
[87,"충북","직할","신제천S/S #2 M.Tr A","18년 변전협력회사 총액공사","주변압기, 1-2차 GIS, PT, LA(대체) 초기점검","2018-06-11 09:00","2018-06-12 18:00","2018-06-11 09:00","2018-06-12 18:00","연속",null,null,null,201804080003]
[88,"충북","직할","신제천S/S #4 M.Tr A","18년 변전협력회사 총액공사","주변압기, 3차측 PT, LA(대체) 초기점검","2018-06-14 09:00","2018-06-15 18:00","2018-06-14 09:00","2018-06-15 18:00","연속",null,null,null,201804080004]
[89,"충북","직할","신제천S/S 345kV #1 BUS","신제천S/S SVC 설치용 362kV GIS설치공사","-362kV 63kA 63,000A GIS 2 CB 증설 - 기타부대공사","2018-06-19 08:00","2018-06-28 18:00","2018-06-22 08:00","2018-07-01 18:00","연속",null,null,null,201804090584]
[90,"충북","직할","신충주S/S #3 M.Tr A","18년 변전협력회사 총액공사","주변압기, 1-2차 GIS 기기 하자점검","2018-06-04 09:00","2018-06-05 18:00","2018-06-04 09:00","2018-06-05 18:00","연속",null,null,null,201804080002]
[91,"충북","청주","세종청원#2 T/L","청원S/S 345kV 장기사용 GIS 대체공사","청원S/S 345kV 장기사용 GIS 대체공사 관련 무부하가압 - 72Bay (청원-신진천#2T/L(7271), #1M.Tr(7272), TIE(7200)) 무부하 가압을 위한 휴전","2018-06-09 08:00","2018-06-11 08:00","2018-06-09 08:00","2018-06-11 08:00","연속",null,null,null,201804040129]
[92,"충북","청주","신옥천S/S #1 M.Tr A","신옥천S/S 장기사용 23kV 분로리액터 대체","#1M.Tr 3차측 인출 모선 보강(ACSR 520SQ×2B → ACSR 520SQ×4B)","2018-06-18 10:00","2018-06-22 18:00","2018-06-18 10:00","2018-06-22 18:00","연속",null,null,null,201804130271]
[93,"충북","청주","신옥천S/S #2 M.Tr A","신옥천S/S 장기사용 23kV 분로리액터 대체","#2M.Tr 3차측 인출 모선 보강 - AL Pipe 60Φ → AL Pipe 89Φ - ACSR 520SQ × 2B → ACSR 520SQ × 4B","2018-06-25 10:00","2018-06-29 18:00","2018-06-25 10:00","2018-06-29 18:00","연속",null,null,null,201804130273]
[94,"충북","청주","신옥천북경남 T/L","345kV 신옥천-북경남T/L 전선접속개소 전선교체공사","전선교체 22.661c-km","2018-06-03 08:00","2018-06-12 19:00","취소","취소","연속",null,null,null,201804130113]
[95,"충북","청주","청원S/S 345kV #1 BUS","청원S/S 345kV 장기사용 GIS 대체공사","청원S/S 345kV 장기사용 GIS 대체공사 관련 무부하가압 - 72Bay (청원-신진천#2T/L(7271), #1M.Tr(7272), TIE(7200)) 무부하 가압을 위한 휴전","2018-06-09 08:00","2018-06-10 08:00","2018-06-09 08:00","2018-06-10 08:00","연속",null,null,null,201804040130]
[96,"충북","청주","청원S/S 345kV #2 BUS","청원S/S 345kV 장기사용 GIS 대체공사","청원S/S 345kV 장기사용 GIS 대체공사 관련 무부하가압 - 72Bay (청원-신진천#2T/L(7271), #1M.Tr(7272), TIE(7200)) 무부하 가압을 위한 휴전","2018-06-10 08:00","2018-06-11 08:00","2018-06-10 08:00","2018-06-11 08:00","연속",null,null,null,201804040131]
[97,"충북","충주","신진천S/S 345kV #1 BUS","345kV 신진천S/S 용량부족 GIS 대체공사","-72BAY 3CB 철거 및 63kA 3CB 설치 설치","2018-06-26 14:00","2018-06-27 14:00","2018-06-26 14:00","2018-06-27 14:00","연속",null,null,"신뢰도개선",201804110140]
[98,"충북","충주","신진천S/S 345kV #2 BUS","345kV 신진천S/S 용량부족 GIS 대체공사","-72BAY 3CB 철거 및 63kA 3CB 설치 설치","2018-06-27 14:00","2018-06-28 14:00","2018-06-27 14:00","2018-06-28 14:00","연속",null,null,"신뢰도개선",201804110141]
[99,"대전충남","대전","신계룡S/S #1 M.Tr A","신계룡S/S 345kV #1M.Tr 보호반교체 및 병행작업","신계룡S/S 345kV #1M.Tr 보호반교체 및 병행작업","2018-06-01 09:00","2018-06-12 18:00","2018-06-01 09:00","2018-06-12 18:00","연속",null,null,null,201804090585]
[100,"대전충남","대전","신계룡S/S #3 M.Tr A","신계룡S/S 345kV #3M.Tr 보호계전기 성능개선 및 병행작업","신계룡S/S 345kV #3M.Tr 보호계전기 성능개선 및 1차 부싱 절연유채유","2018-06-18 09:00","2018-06-18 18:00","2018-06-18 09:00","2018-06-18 18:00","당일",null,null,null,201804190035]
[101,"대전충남","서산","당진T/P #72 Tie-Tr 1차 - TIE CB (7300)","18년 서산PO 345/765kV GIS 점검공사","당진화력 345kV #72Tie-Tr 1차-Tie GIS(7300) 정밀점검","2018-06-25 09:00","2018-06-29 18:00","2018-06-25 09:00","2018-06-29 18:00","연속",null,null,null,201804160268]
[102,"대전충남","서산","당진T/P #72 Tie-Tr 1차 CB (7371)","18년 서산PO 345/765kV GIS 점검공사","당진화력 345kV #72Tie-Tr 1차 GIS(7371) 정밀점검","2018-06-11 09:00","2018-06-15 18:00","2018-06-11 09:00","2018-06-15 18:00","연속",null,null,null,201804160266]
[103,"대전충남","서산","신당진S/S 연락#1T/L-#1M.Tr 1차 TIE CB (7400)","18년 서산PO 345/765kV GIS 점검공사","신당진 345kV 연락#1T/L #1M.Tr 1차 Tie GIS(7400) 정밀점검","2018-06-18 09:00","2018-06-22 18:00","2018-06-18 09:00","2018-06-22 18:00","연속",null,null,null,201804160267]
[104,"대전충남","서산","신당진개폐소태안화력#2 T/L","345kV 신서산-태안화력 등 7개 T/L 항공장애구교체공사","345kV 신당진-태안화력T/L 항공장애구교체공사","2018-06-10 08:00","2018-06-10 18:00","2018-06-10 08:00","2018-06-10 18:00","당일",null,null,null,201804090080]
[105,"대전충남","서산","신당진신당진개폐소#1T/L","18년 서산PO 변전정비회사 총액공사","18년 서산PO 변전정비회사 총액공사","2018-06-05 09:00","2018-06-05 18:00","2018-06-05 09:00","2018-06-05 18:00","당일",null,null,null,201804160271]
[106,"대전충남","서산","신서산S/S 345kV #3 Sh.R CB (7571)","18년 서산PO 345/765kV GIS 점검공사","신서산S/S 345kV #3Sh.R GIS(7571) 정밀점검","2018-06-04 09:00","2018-06-08 18:00","2018-06-04 09:00","2018-06-08 18:00","연속",null,null,null,201804160265]
[107,"대전충남","서산","신서산신당진#1 T/L","18년 서산PO 변전정비회사 총액공사","신서산-신당진#1T/L 보호배전반 업그레이드","2018-06-23 09:00","2018-06-24 18:00","2018-06-23 09:00","2018-06-24 18:00","연속",null,null,null,201804160279]
[108,"대전충남","서산","신서산태안화력#2 T/L","18년 서산PO 변전정비회사 총액공사","태안화력 345kV 신서산-태안화력#2T/L GIS(7A71) 하자점검 및 LA,cVT 보통점검","2018-06-09 09:00","2018-06-09 18:00","2018-06-09 09:00","2018-06-09 18:00","당일",null,null,null,201804160273]
[109,"대전충남","서산","태안T/P 10호기 1차 CB (7A72)","18년 서산PO 변전정비회사 총액공사","태안화력 345kV 10호기 1차 GIS(7A72) 하자점검","2018-06-04 09:00","2018-06-04 18:00","2018-06-04 09:00","2018-06-04 18:00","당일",null,null,null,201804160270]
[110,"대전충남","서산","태안T/P 신서산-태안TP#2-10호기 1차 CB (7A00)","18년 서산PO 변전정비회사 총액공사","태안화력 345kV 신서산-태안화력#2T/L-10호기 1차 GIS(7A00) 하자점검","2018-06-07 09:00","2018-06-07 18:00","2018-06-07 09:00","2018-06-07 18:00","당일",null,null,null,201804160272]
[111,"대전충남","아산","아산S/S #1 M.Tr A","아산S/S 170kV 장기사용 GIS 교체공사","아산S/S 170kV 장기사용 GIS 교체공사","2018-06-11 09:00","2018-06-26 18:00","2018-06-11 09:00","2018-06-26 18:00","연속",null,null,null,201804190220]
[112,"대전충남","청양","청양S/S #2 M.Tr A","청양S/S #2M.Tr 보호배전반 성능개선","○ #2M.Tr 보호배전반 성능개선(YPP제)","2018-06-19 09:00","2018-06-19 18:00","2018-06-19 09:00","2018-06-19 18:00","당일",null,null,null,201804100164]
[113,"대전충남","청양","청양신온양#1 T/L","345kV 북당진-신탕정T/L 건설공사(2공구)","345kV 북당진-신탕정T/L 건설공사(2공구) - 기설송전선로 근접개소(345kV 청양-신온양T/L No.145) 철탑 조립, 전선이동 작업 - 345kV 북당진-신탕정T/L 병가구간 가선작업(No.78~150-1)","2018-06-04 07:00","2018-06-15 18:00","2018-06-04 07:00","2018-06-15 18:00","연속",null,null,null,201804020083]
[114,"대전충남","청양","청양신온양#1 T/L","345kV 북당진-신탕정T/L 건설공사(2공구)","345kV 북당진-신탕정T/L 건설공사(2공구) - 345kV 청양-신온양T/L No.145 가선작업 - 345kV 북당진-신탕정T/L 병가구간 가선작업(No.78~150-1)","2018-06-23 07:00","2018-06-28 18:00","2018-06-23 07:00","2018-06-28 18:00","연속",null,null,null,201804020085]
[115,"대전충남","청양","청양신온양#2 T/L","345kV 북당진-신탕정T/L 건설공사(2공구)","345kV 북당진-신탕정T/L 건설공사(2공구) - 기설송전선로 근접개소(345kV 청양-신온양T/L No.145) 철탑 철거, 전선이동 작업 - 345kV 북당진-신탕정T/L 병가구간 가선작업(No.78~150-1)","2018-06-16 07:00","2018-06-22 18:00","2018-06-16 07:00","2018-06-22 18:00","연속",null,null,null,201804020084]
[116,"전북","군산","군산S/S 군산-새만금#2T/L CB (7871)","군산P/O 154kV 이상 차단기 조작시험","차단기 조작시험","2018-06-27 09:00","2018-06-27 15:00","2018-06-27 09:00","2018-06-27 15:00","당일",null,null,null,201804130136]
[117,"전북","군산","군산새만금#1 T/L","군산-새만금T/L 폴리머애자교체공사","폴리머애자교체 : 4, 5호","2018-06-28 07:00","2018-06-30 18:00","2018-06-28 07:00","2018-06-30 18:00","매일",null,null,null,201804180134]
[118,"전북","군산","새만금S/S #2M.Tr 1차 CB (7272)","군산P/O 154kV이상 차단기 조작시험","차단기 조작시험","2018-06-20 09:00","2018-06-20 15:00","2018-06-20 09:00","2018-06-20 15:00","당일",null,null,null,201804120222]
[119,"전북","군산","새만금S/S #3M.Tr 1차 CB (7372)","군산P/O 154kV이상 차단기 조작시험","차단기 조작시험","2018-06-21 09:00","2018-06-21 15:00","2018-06-21 09:00","2018-06-21 15:00","당일",null,null,null,201804120225]
[120,"전북","군산","청양군산#2 T/L","항공장애표시구설치공사","항공구설치","2018-06-18 07:00","2018-06-22 18:00","2018-06-18 07:00","2018-06-22 18:00","매일",null,null,null,201804180135]
[121,"전북","김제","신김제S/S #3 M.Tr A","3차측 계전기 정정 변경","3차측 계전기 정정 변경","2018-06-12 09:30","2018-06-12 14:00","2018-06-12 09:30","2018-06-12 14:00","당일",null,null,null,201804240020]
[122,"전북","김제","신김제S/S #4 M.Tr A","3차측 계전기 정정 변경","3차측 계전기 정정 변경","2018-06-12 14:00","2018-06-12 18:00","2018-06-12 14:00","2018-06-12 18:00","당일",null,null,null,201804240021]
[123,"전북","직할","북경남무주양수 T/L","345kV 신옥천-북경남T/L 전선접속개소 전선교체공사","전선교체 22.661c-km","2018-06-14 08:00","2018-06-19 19:00","취소","취소","연속",null,null,"신뢰도개선",201803090408]
[124,"전북","직할","신남원광양#1 T/L","345kV 신남원-광양T/L 안전이격 확보공사","가. 철탑철거 : 2기 [No.214(T-14), No.216(F-21)] 나. 철탑설치 : 2기 [No.214(C2-26), No.216(SF-36)] 다. 전력선 교체 : 1.790km [ACSR 480㎟ x 2B] , 12가닥 라. 가선로 구성 : 가철탑 1기 (No.216)","2018-06-25 07:00","2018-07-01 18:00","2018-06-28 07:00","2018-07-04 18:00","연속",null,null,null,201804200076]
[125,"전북","직할","신남원의령#1 T/L","345kV 신남원-의령 등 5개T/L 항공장애 표시구 설치공사","- 345kV 신남원-의령T/L : 92개 - 345kV 신옥천-신남원T/L : 146개 - 154kV 신김제-동전주T/L : 56개 - 154kV 동전주-북전주T/L : 29개 - 154kV 진안-장수T/L : 96개","2018-06-21 07:00","2018-06-27 18:00","2018-06-21 07:00","2018-06-27 18:00","매일",null,null,null,201804180084]
[126,"전북","직할","신남원한빛NP#1 T/L","345kV 신남원-한빛#1T/L 전선접속개소 해소공사","○ 전력선교체 : 8.285C-km(ACSR 480㎟*4B) - 대상구간 : No.45~171 (일부구간 제외) ○ 가공지선교체 : 1.924km(ACSR 120㎟*S) ○ 스페이서댐퍼 설치/철거 : 387개/354개 ○ 아마롯드 설치 및 기타 부대공사","2018-06-04 09:00","2018-06-25 18:00","2018-06-04 09:00","2018-06-25 18:00","연속",null,null,null,201804170210]
[127,"전북","직할","신남원한빛NP#2 T/L","신남원-한빛NP#2T/L 장기사용 345kV CVT 대체공사","345kV CVT 3대 교체","2018-06-27 09:30","2018-06-27 18:00","2018-06-27 09:30","2018-06-27 18:00","당일",null,null,null,201804200153]
[128,"전북","직할","신옥천신남원#1 T/L","345kV 신옥천-신남원T/L No.74 안전이격 확보공사","가. 철탑철거 : 2기 [No.73(A-18), No.74(B-14)] 나. 철탑설치 : 1기 [No.74(Ba2-60)] 다. 전력선 교체 : 0.433km [HSTACIR 410㎟ x 2B] , 12가닥 라. 가선로 구성 : 가철탑 1기","2018-06-08 08:00","2018-06-14 18:00","2018-06-15 08:00","2018-06-21 18:00","연속",null,null,null,201804170229]
[129,"전북","직할","신옥천신남원#1 T/L","345kV 신옥천-신남원T/L No.74 안전이격 확보공사","가. 철탑철거 : 2기 [No.73(A-18), No.74(B-14)] 나. 철탑설치 : 1기 [No.74(Ba2-60)] 다. 전력선 교체 : 0.433km [HSTACIR 410㎟ x 2B] , 12가닥 라. 가선로 구성 : 가철탑 1기","2018-06-22 08:00","2018-06-28 18:00","취소","취소","연속",null,null,null,201804170233]
[130,"전북","직할","신옥천신남원#2 T/L","345kV 신옥천-신남원T/L No.74 안전이격 확보공사","가. 철탑철거 : 2기 [No.73(A-18), No.74(B-14)] 나. 철탑설치 : 1기 [No.74(Ba2-60)] 다. 전력선 교체 : 0.433km [HSTACIR 410㎟ x 2B] , 12가닥 라. 가선로 구성 : 가철탑 1기","2018-06-15 08:00","2018-06-21 18:00","취소","취소","연속",null,null,null,201804170230]
[131,"광주전남","강진","신강진S/S 345kV #1 BUS","신강진S/S 345kV 취약설비 GIS화 사업","345kV 옥외철구 → 345kV GIS","2018-06-18 09:00","2018-06-18 18:00","2018-06-17 09:00","2018-06-17 13:00","당일",null,null,"신뢰도개선",201801110143]
[132,"광주전남","강진","신강진S/S 345kV #2 BUS","신강진S/S 345kV 취약설비 GIS화 사업","345kV 옥외철구 → 345kV GIS","2018-06-18 09:00","2018-06-18 18:00","2018-06-17 13:00","2018-06-17 18:00","당일",null,null,"신뢰도개선",201801110144]
[133,"광주전남","강진","신화순신강진#1 T/L","신강진S/S 345kV 이하 취약설비 GIS화 사업","신강진S/S 345kV 옥외철구 - GIS화","2018-06-18 09:00","2018-07-13 18:00","2018-06-18 09:00","2018-07-13 18:00","연속",null,null,null,201804030054]
[134,"광주전남","광주","신화순S/S 345kV #1 BUS","신화순S/S 345kV #1 BUS(변전협력회사 총액공사)","345kV #1BUS PRO 보호반 교체","2018-06-18 09:00","2018-06-22 18:00","2018-06-18 09:00","2018-06-22 18:00","연속",null,null,null,201804060276]
[135,"광주전남","광주","신화순S/S 345kV #2 BUS","신화순S/S 345kV #2 BUS(변전협력회사 총액공사)","345kV #2BUS PRO 보호반 교체","2018-06-25 09:00","2018-06-29 18:00","2018-06-25 09:00","2018-06-29 18:00","연속",null,null,null,201804060277]
[136,"광주전남","목포","신남원한빛NP#1 T/L","신남원한빛NP#1 T/L(362kV GIS 보통점검)","362kV GIS 보통점검","2018-06-21 09:00","2018-06-23 18:00","취소","취소","연속",null,null,null,201804160233]
[137,"광주전남","목포","한빛2N/P 345kV #1 BUS","한빛2N/P 345kV #1 BUS(362kV GIS 보통점검)","362kV GIS 보통점검","2018-06-04 13:00","2018-06-04 18:00","2018-06-04 13:00","2018-06-04 18:00","연속",null,null,null,201804160222]
[138,"광주전남","목포","한빛2N/P 345kV #1 BUS","한빛2N/P 345kV #1 BUS(362kV GIS 보통점검)","362kV GIS 보통점검","2018-06-18 13:00","2018-06-18 18:00","2018-06-18 13:00","2018-06-18 18:00","연속",null,null,null,201804160224]
[139,"광주전남","목포","한빛2N/P 345kV #1 BUS","한빛2N/P 345kV #1 BUS(362kV GIS 보통점검)","362kV GIS 보통점검","2018-06-21 13:00","2018-06-21 18:00","2018-06-21 13:00","2018-06-21 18:00","연속",null,null,null,201804160226]
[140,"광주전남","목포","한빛2N/P 345kV #2 BUS","한빛2N/P 345kV #2 BUS(362kV GIS 보통점검)","362kV GIS 보통점검","2018-06-04 09:00","2018-06-04 13:00","2018-06-04 09:00","2018-06-04 13:00","연속",null,null,null,201804160221]
[141,"광주전남","목포","한빛2N/P 345kV #2 BUS","한빛2N/P 345kV #2 BUS(362kV GIS 보통점검)","362kV GIS 보통점검","2018-06-18 09:00","2018-06-18 13:00","2018-06-18 09:00","2018-06-18 13:00","연속",null,null,null,201804160223]
[142,"광주전남","목포","한빛2N/P 345kV #2 BUS","한빛2N/P 345kV #2 BUS(362kV GIS 보통점검)","362kV GIS 보통점검","2018-06-21 09:00","2018-06-21 13:00","2018-06-21 09:00","2018-06-21 13:00","연속",null,null,null,201804160225]
[143,"광주전남","목포","한빛1NP한빛2NP #1T/L","345kV 한빛연락#1T/L(362kV GIS 보통점검)","362kV GIS 보통점검","2018-06-04 09:00","2018-06-07 18:00","2018-06-04 09:00","2018-06-07 18:00","연속",null,null,null,201804020140]
[144,"광주전남","목포","한빛1NP한빛2NP #2T/L","345kV한빛연락#2T/L(362kV GIS 보통점검)","362kV GIS 보통점검","2018-06-18 09:00","2018-06-20 18:00","2018-06-18 09:00","2018-06-20 18:00","연속",null,null,null,201804020145]
[145,"광주전남","순천","광양S/S #1 M.Tr A","와이피피제 보호계전기 성능개선","와이피피제(L90,D60,F35) 보호계전기 모듈교체","2018-06-26 10:00","2018-06-26 18:00","2018-06-26 10:00","2018-06-26 18:00","당일",null,null,null,201804090175]
[146,"광주전남","순천","광양S/S 345kV #76 BUS","광양S/S 345kV #76 BUS(7A00 차단기 시험가압)","7A00 차단기 내부 균압콘덴서 교체공사 시험가압","2018-06-21 15:00","2018-06-22 18:00","2018-06-21 15:00","2018-06-22 18:00","연속",null,null,null,201804200018]
[147,"광주전남","순천","광양S/S KP복합#2T/L CB (7A72)","광양S/S KP복합#2T/L 7A72CB(7A00 차단기 대체)","7A00 차단기 내부 균압콘덴서 교체공사","2018-06-18 09:00","2018-06-22 18:00","2018-06-18 09:00","2018-06-22 18:00","연속",null,null,null,201804200014]
[148,"광주전남","순천","광양S/S 광양제철#2T/L-KP복합#2T/L CB (7A72)","광양제철#2T/L-KP복합#2T/L CB(7A00 차단기 대체)","7A00 차단기 내부 균압콘덴서 교체공사","2018-06-18 09:00","2018-06-22 18:00","2018-06-18 09:00","2018-06-22 18:00","연속",null,null,null,201804200016]
[149,"광주전남","순천","신강진광양#1 T/L","345kV 신강진-광양#1 T/L(7A00 차단기 시험가압)","7A00 차단기 내부 균압콘덴서 교체공사 시험가압","2018-06-21 15:00","2018-06-22 18:00","2018-06-21 15:00","2018-06-22 18:00","연속",null,null,null,201804200020]
[150,"광주전남","순천","여수T/P #3 Tie-Tr","와이피피제 보호계전기 성능개선","와이피피제(L90,D60,F35) 보호계전기 모듈교체","2018-06-25 10:00","2018-06-25 18:00","2018-06-25 10:00","2018-06-25 18:00","당일",null,null,null,201804090174]
[151,"대구","경산","울주신경산#1 T/L","울주신경산T/L 전력선교체공사","전력선교체(No.95~99,101~106)","2018-06-04 07:00","2018-06-18 18:00","2018-06-04 07:00","2018-06-17 18:00","연속",null,null,null,201804090494]
[152,"대구","경산","울주신경산#2 T/L","울주신경산T/L 전력선교체공사","전력선교체(No.95~99,101~106)","2018-06-19 07:00","2018-07-02 18:00","2018-06-19 07:00","2018-07-02 18:00","연속",null,null,null,201804090497]
[153,"대구","달성","고령S/S 345kV #1 BUS","345kV 고령S/S Sh.R 증설공사","345kV 고령S/S Sh.R 증설공사","2018-06-09 08:00","2018-06-12 18:00","2018-06-09 08:00","2018-06-12 18:00","연속",null,null,null,201804160167]
[154,"대구","칠곡","북경남서대구#2 T/L","서대구S/S 북경남-서대구#2T/L CB,LA,PT 점검","서대구S/S 북경남-서대구#2T/L CB,LA,PT 점검","2018-06-19 09:30","2018-06-19 18:00","2018-06-19 09:30","2018-06-19 18:00","당일",null,null,null,201804050289]
[155,"대구","칠곡","북대구서대구#2 T/L","서대구S/S 북대구-서대구#2T/L CB 및 LA 점검","서대구S/S 북대구-서대구#2T/L CB 및 LA 점검","2018-06-29 09:30","2018-06-29 18:00","2018-06-29 09:30","2018-06-29 18:00","당일",null,null,null,201804050293]
[156,"대구","칠곡","북대구선산 T/L","345kV선산분기T/L 전력선교체공사","345kV선산분기T/L No.54~55 전력선교체","2018-06-04 08:00","2018-06-07 18:00","2018-06-04 08:00","2018-06-07 18:00","연속",null,null,null,201804060258]
[157,"대구","칠곡","서대구S/S #1M.Tr A","서대구S/S #1M.Tr 하자점검","서대구S/S #1M.Tr 하자점검","2018-06-07 09:30","2018-06-08 18:00","2018-06-07 09:30","2018-06-08 18:00","연속",null,null,null,201804050086]
[158,"대구","칠곡","서대구S/S 북경남/서#1/선산#1T/L-TIE CB (7400)","서대구S/S 북경남-서대구#1-서-선#1T/L 7400 GCB 보통점검","서대구S/S 북경남-서대구#1-서-선#1T/L 7400 GCB 보통점검","2018-06-18 14:00","2018-06-18 18:00","2018-06-18 14:00","2018-06-18 18:00","당일",null,null,null,201804050285]
[159,"대구","칠곡","서대구S/S 북경남-서대구#1T/L CB (7471)","서대구S/S 북경남-서대구#1T/L 7471 GCB 보통점검","서대구S/S 북경남-서대구#1T/L 7471 GCB 보통점검","2018-06-18 09:30","2018-06-18 14:00","2018-06-18 09:30","2018-06-18 14:00","당일",null,null,null,201804050282]
[160,"대구","칠곡","서대구고령#1 T/L","서대구S/S 서대구-고령#1T/L GCB , LA 점검","서대구S/S 서대구-고령#1T/L GCB , LA 점검","2018-06-15 09:30","2018-06-15 18:00","2018-06-15 09:30","2018-06-15 18:00","당일",null,null,null,201804050102]
[161,"대구","포항","선산신포항 T/L","345kV 신포항-북대구T/L 지장선로이설공사(본선로 구성)","345kV 신포항-북대구T/L 지장선로이설공사 ○ 지지물 교체 2기, 전선교체 10.1km 345kV 신포항-북대구T/L 안전이격확보 ○ 지지물 교체 4기, 전선교체 5.6km","2018-06-18 08:00","2018-07-03 18:00","2018-06-18 08:00","2018-07-03 18:00","연속",null,null,null,201804090053]
[162,"대구","포항","신포항신영일 T/L","항공장애 주간표지 설치공사","345kV신포항-신영일T/L 항공장애주간표지 설치공사 -작업구간 : No.47-48,65-66","2018-06-15 09:00","2018-06-15 18:00","2018-06-10 09:00","2018-06-10 18:00","당일",null,null,"신뢰도개선",201804060311]
[163,"대구","포항","신포항신월성NP#1 T/L","항공장애주간표지 설치공사","신포항-신월성#1T/L 항공장애표시구 설치 -작업구간 : No.62-63, 64-65","2018-06-04 09:00","2018-06-04 18:00","2018-06-04 09:00","2018-06-04 18:00","당일",null,null,null,201804060308,"○"]
[164,"대구","포항","신포항신월성NP#2 T/L","항공장애 주간표지 설치공사","345kV신포항-신월성#2T/L 항공장애표시구 설치 -작업구간 : No.62-63, 64-65","2018-06-05 09:00","2018-06-05 18:00","2018-06-05 09:00","2018-06-05 18:00","당일",null,null,null,201804060309]
[165,"대구","포항","신포항청송PP T/L","항공장애 주간표지 설치공사","345kV신포항-청송PP T/L 항공장애표시구 설치 -작업구간 : No.331-332, 349-350","2018-06-14 09:00","2018-06-14 18:00","2018-06-03 09:00","2018-06-03 18:00","당일",null,null,"신뢰도개선",201804060310,"○"]
[166,"대구","포항","울주월성NP#1 T/L","2018년 가공송전선로 순시점검 위탁공사","345kV울주-월성T/L 정밀점검 -작업구간 : No.39-89","2018-06-18 09:00","2018-06-22 18:00","2018-06-06 09:00","2018-06-11 18:00","매일",null,null,null,201804060290]
[167,"대구","포항","월성2N/P #3 M.Tr 2차 CB (7572)","2018년 포항전력지사 총액공사 보통점검","월성S/Y 7572 CB 보통점검","2018-06-19 09:00","2018-06-19 18:00","2018-06-29 09:00","2018-06-29 18:00","당일",null,null,null,201804180014]
[168,"경북","구미","선산S/S #1 M.Tr A","선산S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 공사 - RTU D/O 정비공사 관련 시험","2018-06-18 09:00","2018-06-18 11:00","2018-06-18 09:00","2018-06-18 11:00","당일",null,null,null,201804110169]
[169,"경북","구미","선산S/S #2 M.Tr A","선산S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 공사 - RTU D/O 정비공사 관련 시험","2018-06-19 09:00","2018-06-20 18:00","2018-06-19 09:00","2018-06-20 18:00","연속",null,null,null,201804110188]
[170,"경북","구미","선산S/S #3 M.Tr A","선산S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 공사 - RTU D/O 정비공사 관련 시험","2018-06-21 09:00","2018-06-22 18:00","2018-06-21 09:00","2018-06-22 18:00","연속",null,null,null,201804110189]
[171,"경북","구미","선산S/S #4 M.Tr A","선산S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 공사 - 선산-안계#1,2T/L 송전선로 인출변경 - #4M.Tr, 안계#1,2T/L GIS 부하전환","2018-06-08 08:00","2018-06-11 18:00","2018-06-08 08:00","2018-06-11 18:00","연속",null,null,null,201804040095]
[172,"경북","구미","선산S/S #4 M.Tr A","선산S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 공사 - RTU D/O 정비공사 관련 시험","2018-06-25 09:00","2018-06-26 18:00","2018-06-25 09:00","2018-06-26 18:00","연속",null,null,null,201804110190]
[173,"경북","영주","신제천신영주#1 T/L","345kV 신제천-신영주T/L 전선접속개소 전선교체공사","○ 공사구간 : 345kV 신제천-신영주 T/L No.175~181, 191~201 ○ 전력선 교체 : ACSR 480㎟ × 4B 14.560C-km","2018-06-02 07:00","2018-06-11 18:00","2018-06-06 07:00","2018-06-16 18:00","연속",null,null,null,201804030082]
[174,"경북","직할","안동복합S/Y #1M.Tr 1차 GIS","18~19 경북직할 변전협력업체 총액공사","안동복합S/S #1M.Tr 1,2차 차단기 초기점검, #1M.Tr 초기점검","2018-06-18 09:00","2018-06-20 18:00","2018-06-18 09:00","2018-06-20 18:00","당일",null,null,null,201804240001]
[175,"부산울산","동부산","고리N/P S/Y 7077 BUS SEC CB (7077)","고리NP S/Y 362kV GIS 보통점검","고리NP S/Y 362kV 7077GIS 보통점검(#1CLR)","2018-06-07 09:30","2018-06-08 17:00","2018-06-07 09:30","2018-06-08 17:00","연속",null,null,null,201804090816]
[176,"부산울산","동부산","고리N/P S/Y 7177 BUS SEC CB (7177)","고리NP S/Y 362kV GIS 보통점검","고리NP S/Y 362kV 7177GIS 보통점검(#1CLR)","2018-06-07 09:30","2018-06-08 17:00","2018-06-07 09:30","2018-06-08 17:00","연속",null,null,null,201804090817]
[177,"부산울산","동부산","고리N/P S/Y 7577 BUS SEC CB (7577)","고리NP S/Y 362kV GIS 보통점검","고리NP S/Y 362kV 7577GIS 보통점검(#2CLR)","2018-06-11 09:30","2018-06-12 17:00","2018-06-11 09:30","2018-06-12 17:00","연속",null,null,null,201804090818]
[178,"부산울산","동부산","고리N/P S/Y 7677 BUS SEC CB (7677)","고리NP S/Y 362kV GIS 보통점검","고리NP S/Y 362kV 7677GIS 보통점검(#2CLR)","2018-06-11 09:30","2018-06-12 17:00","2018-06-11 09:30","2018-06-12 17:00","연속",null,null,null,201804090819]
[179,"부산울산","동부산","신양산북부산#2 T/L","신양산S/S 362kV GIS 조작시험","1. 신양산S/S 362kV 7371,7300GIS 조작시험(신양산-북부산#2T/L) 2. [병행] 신양산S/S 신양산-북부산#2T/L PT 초기점검","2018-06-04 09:30","2018-06-04 17:00","2018-06-04 09:30","2018-06-04 17:00","당일",null,null,null,201804090815]
[180,"부산울산","북부산","북부산S/S 345kV #70 BUS","345kV 북부산S/S 차단기용량대체공사","모선연결 작업(74-71BAY : 71BAY 증설연결분)","2018-06-07 08:00","2018-06-15 15:00","2018-06-19 15:00","2018-06-20 15:00","연속",null,null,null,201712060084]
[181,"부산울산","북부산","북부산신울산#1 T/L","345kV 북부산S/S 차단기용량대체공사","시험가압선로(71BAY 증설 70BUS 연결분)","2018-06-14 15:00","2018-06-15 15:00","2018-06-19 15:00","2018-06-20 15:00","연속",null,null,null,201801080312]
[182,"부산울산","북부산","북부산신울산#1 T/L","345kV 북부산S/S 차단기용량대체공사","북부산신울산#1 T/L 인출변경","2018-06-26 08:00","2018-07-13 18:00","취소","취소","연속",null,null,null,201801080318]
[183,"부산울산","북부산","신양산북부산#1 T/L","345kV 북부산S/S 차단기용량대체공사","시험가압선로(71BAY 증설 75BUS 연결분)","2018-06-05 15:00","2018-06-06 15:00","취소","취소","연속",null,null,null,201801080315]
[184,"부산울산","북부산","신양산북부산#1 T/L","345kV 북부산S/S 차단기용량대체공사","신양산북부산#1 T/L 인출변경","2018-06-26 08:00","2018-07-13 18:00","취소","취소","연속",null,null,null,201801080320]
[185,"부산울산","서부산","서부산S/S 345kV #1 Sh.R","서부산S/S 345kV #1Sh.R 초기점검","서부산S/S 345kV #1Sh.R 초기점검(#1Sh.R CB(7177) 보통점검 병행)","2018-06-04 10:00","2018-06-05 18:00","2018-06-04 10:00","2018-06-05 18:00","연속",null,null,null,201804050363]
[186,"부산울산","서부산","신녹산S/S #2 M.Tr A","신녹산S/S #2M.Tr 본체 및 OLTC 정밀점검","신녹산S/S #2M.Tr 본체 및 OLTC 정밀점검","2018-06-04 10:00","2018-06-15 18:00","2018-06-04 10:00","2018-06-15 18:00","연속",null,null,null,201804050362]
[187,"부산울산","서부산","신녹산S/S #3 M.Tr A","신녹산S/S #3M.Tr C상 3차측 권선온도계 교체","신녹산S/S #3M.Tr C상 3차측 권선온도계 교체","2018-06-18 10:00","2018-06-18 18:00","2018-06-18 10:00","2018-06-18 18:00","당일",null,null,null,201804050360]
[188,"부산울산","울산","동울산신울산#1 T/L","345kV 동울산-신울산T/L 지장철탑 이설공사 및 전선교체공사","1. 지장이설 구간 : No.50~52(#1 본선로 구성) 2. 전선교체 : No.50~51, 88~99, 107~118)","2018-06-02 07:00","2018-06-15 18:00","2018-06-14 07:00","2018-06-18 18:00","연속",null,null,null,201804090588,"○"]
[189,"부산울산","울산","신온산S/S S-OIL#5T/L CB (7172)","2018-19년 울산전력지사 변전협력회사 총액공사","신온산S/S 345kV 7172 GIS 초기점검","2018-06-01 09:00","2018-06-01 18:00","2018-06-01 09:00","2018-06-01 18:00","당일",null,null,null,201804090504]
[190,"부산울산","울산","신온산S/S S-OIL#6T/L CB (7571)","2018-19년 울산전력지사 변전협력회사 총액공사","신온산S/S 345kV 7571 GIS 초기점검","2018-06-22 09:00","2018-06-22 18:00","2018-06-22 09:00","2018-06-22 18:00","당일",null,null,null,201804090535]
[191,"부산울산","울산","신울산S/S #4 M.Tr A","2018-19년 울산전력지사 변전협력회사 총액공사","1.신울산S/S 345kV #4M.Tr 보통점검 2.신울산S/S 345kV 7600,7672,6464 차단기 동작시험","2018-06-09 09:00","2018-06-10 18:00","2018-06-09 09:00","2018-06-10 18:00","연속",null,null,null,201804090524]
[192,"부산울산","울산","신울산S/S #5 M.Tr A","2018-19년 울산전력지사 변전협력회사 총액공사","1.신울산S/S 345kV #5M.Tr 보통점검 2.신울산S/S 345kV 7700,7772 차단기 동작시험 3.신울산S/S 345kV 6564 GIS 보통점검","2018-06-16 09:00","2018-06-17 18:00","2018-06-16 09:00","2018-06-17 18:00","연속",null,null,null,201804090530]
[193,"부산울산","울산","신울산신온산#1 T/L","345㎸ 신울산-신온산T/L OPGW 증설공사","345㎸ 신울산-신온산#1 T/L OPGW 6.479㎞(120SQ/24C) 증설, S/T↔ICT실간 비금속광케이블 3.364㎞ 등 부대설비 1식","2018-06-14 07:00","2018-06-21 18:00","2018-06-14 07:00","2018-06-21 18:00","연속",null,null,null,201804090473]
[194,"부산울산","울산","울주S/S #3 M.Tr A","2018-19년 울산전력지사 변전협력회사 총액공사","울주S/S 345kV 76Bay B/F PNL 대체","2018-06-16 09:00","2018-06-20 18:00","2018-06-16 09:00","2018-06-20 18:00","연속",null,null,null,201804090511]
[195,"부산울산","울산","울주S/S 울주-신경산#1T/L CB (7871)","2018-19년 울산전력지사 변전협력회사 총액공사","울주S/S 345kV 7871 차단기 동작시험","2018-06-04 09:00","2018-06-04 18:00","2018-06-04 09:00","2018-06-04 18:00","연속",null,null,null,201804090516]
[196,"부산울산","울산","울주S/S 울주-신경산#2T/L CB (7771)","2018-19년 울산전력지사 변전협력회사 총액공사","울주S/S 345kV 7771 차단기 동작시험","2018-06-01 09:00","2018-06-01 18:00","2018-06-01 09:00","2018-06-01 18:00","연속",null,null,null,201804090515]
[197,"부산울산","울산","울주S/S 울주-월성NP#2T/L-TIE CB (7A00)","2018-19년 울산전력지사 변전협력회사 총액공사","울주S/S 345kV 7A00 차단기 동작시험","2018-06-05 09:00","2018-06-05 18:00","2018-06-05 09:00","2018-06-05 18:00","연속",null,null,null,201804090520]
[198,"부산울산","울산","울주고리NP#1 T/L","345kV 울주-고리NPT/L 67~68호 지장철탑이설공사","지장철탑이설 가선로 구성, 구간: 65~68호, 철탑설치: 67-1호 할입","2018-06-08 08:00","2018-06-20 18:00","2018-06-08 08:00","2018-06-20 18:00","연속",null,null,null,201804090375]
[199,"부산울산","울산","울주고리NP#2 T/L","345kV 울주-고리 지장철탑이설공사","지장이설 #2T/L 본선로 구성, 구간: 67~68호, 67-1호 철탑할입","2018-06-21 08:00","2018-07-03 18:00","2018-06-21 08:00","2018-07-03 18:00","연속",null,null,null,201804100133]
[200,"부산울산","직할","신양산신대연#1 T/L","2018년 직할 변전협력회사 총액공사","신대연S/S 신양산-신대연#1T/L PNL 유사고장방지 성능개선","2018-06-18 10:00","2018-06-18 18:00","2018-06-18 10:00","2018-06-18 18:00","당일",null,null,null,201804090341]
[201,"부산울산","직할","신양산신대연#2 T/L","2018년 직할 변전협력회사 총액공사","신대연S/S 신양산-신대연#2T/L PNL 유사고장방지 성능개선","2018-06-19 10:00","2018-06-19 18:00","2018-06-19 10:00","2018-06-19 18:00","당일",null,null,null,201804090342]
[202,"경남","진주","의령S/S 고령-의령#1T/L-TIE CB (7600)","의령S/S 고령-의령#1T/L-TIE CB(7600) 정밀점검","의령S/S 고령-의령#1T/L-TIE CB(7600) 정밀점검","2018-06-07 09:30","2018-06-09 18:30","2018-06-07 09:30","2018-06-09 18:30","연속",null,null,null,201803300114]
[203,"경남","진주","의령S/S 신남원-의령#1T/L CB (7871)","의령S/S 345kV 신남원-의령 #1T/L CB(7871) 조작시험","의령S/S 345kV 신남원-의령 #1T/L CB(7871) 개폐장치 조작시험","2018-06-11 09:30","2018-06-11 14:00","2018-06-11 09:30","2018-06-11 14:00","당일",null,null,null,201803300222]
[204,"경남","진주","의령S/S 신남원-의령#1T/L-#3M.Tr 1차 CB (7800)","의령S/S 345kV 신남원-의령#1T/L #3M.Tr 1차 CB조작시험","의령S/S 345kV 신남원-의령 #1T/L #3M.Tr 1차 CB(7800) 개폐장치 조작시험","2018-06-11 14:00","2018-06-11 18:30","2018-06-11 14:00","2018-06-11 18:30","당일",null,null,null,201803300226]
[205,"경남","진주","의령S/S 신남원-의령#2T/L CB (7771)","의령S/S 345kV 신남원-의령 #2T/L CB(7771) 조작시험","의령S/S 345kV 신남원-의령 #2T/L CB(7771) 개폐장치 조작시험","2018-06-05 09:30","2018-06-05 14:00","2018-06-05 09:30","2018-06-05 14:00","당일",null,null,null,201803300220]
[206,"경남","진주","의령S/S 신남원-의령#2T/L-TIE CB (7700)","의령S/S 345kV 신남원-의령 #2T/L TIE CB 조작시험","의령S/S 345kV 신남원-의령 #2T/L-TIE CB(7700) 개폐장치 조작시험","2018-06-05 14:00","2018-06-05 18:30","2018-06-05 14:00","2018-06-05 18:30","당일",null,null,null,201803300221]
[207,"경남","진주","의령S/S 의령-하동화력#1T/L CB (7171)","의령S/S 의령-하동화력#1T/L CB(7171) 정밀점검","의령S/S 의령-하동화력#1T/L CB(7171) 정밀점검","2018-06-14 09:30","2018-06-16 18:30","2018-06-14 09:30","2018-06-16 18:30","연속",null,null,null,201803300115]
[208,"경남","진주","하동T/P #6 M.Tr 1차 CB (7672)","하동T/P #6M.Tr 1차 CB(7672) 정밀점검","하동T/P #6M.Tr 1차 CB(7672) 정밀점검","2018-06-18 09:30","2018-06-20 18:30","2018-06-18 09:30","2018-06-20 18:30","연속",null,null,null,201803300116]
[209,"경남","진주","하동T/P 70-71-0 SEC CB (70-71-0)","하동T/P BUS SEC CB(70-71-0) 정밀점검","하동T/P BUS SEC CB(70-71-0) 정밀점검","2018-06-26 09:30","2018-06-28 18:30","2018-06-26 09:30","2018-06-28 18:30","연속",null,null,null,201803300117]
[210,"경남","진주","의령S/S #1 M.Tr A","의령S/S 345kV #1M.Tr A상 OFU 히터 교체","의령S/S 345kV #1M.Tr A상 OFU 히터 교체","2018-06-01 09:30","2018-06-01 18:30","2018-06-01 09:30","2018-06-01 18:30","당일",null,null,null,201804270013]
[211,"경남","진주","의령S/S #2 M.Tr A","의령S/S 345kV #2M.Tr 2차 CB(6244) 정밀점검","의령S/S 345kV #2M.Tr 2차 CB(6244) 정밀점검","2018-06-18 09:30","2018-06-19 18:30","2018-06-18 09:30","2018-06-19 18:30","연속",null,null,null,201804270018]
[212,"경남","통영","신고성S/S #3 M.Tr A","신고성S/S 154kV GIS 신규수용공사(시험가압)","1. 신고성S/S 154kV GIS 신규수용공사(시험가압)","2018-06-21 18:30","2018-06-22 18:30","2018-06-21 18:30","2018-06-22 18:30","연속",null,null,null,201804090656]
[213,"경남","통영","신고성S/S #3 M.Tr A","신고성S/S 154kV GIS 신규수용공사(시험가압)","1. 신고성S/S 154kV GIS 신규수용공사(시험가압)","2018-06-28 18:30","2018-06-29 18:30","2018-06-28 18:30","2018-06-29 18:30","연속",null,null,null,201804090657]
[214,"경남","통영","신고성S/S #3 M.Tr A","345kV 삼천포T/P 구내 전력구공사","전력구 구조물 설치 관련 중장비 안전이격 확보","2018-06-11 08:00","2018-06-17 18:00","2018-06-11 08:00","2018-06-17 18:00","연속",null,null,null,201804200069]
[215,"경남","통영","신고성S/S #4M.Tr A","345kV 삼천포T/P 구내 전력구공사","전력구 구조물 설치 관련 중장비 안전이격 확보","2018-06-30 08:00","2018-07-05 18:00","2018-06-30 08:00","2018-07-05 18:00","연속",null,null,null,201804200070]
[216,"경남","함안","북경남S/S #5 Sh.R","북경남S/S 345kV #5Sh.R GIS 보통점검","북경남S/S 7779, 7771, 7700 GIS 보통점검","2018-06-07 09:30","2018-06-08 17:30","2018-06-07 09:30","2018-06-08 17:30","당일",null,null,null,201804100025]
[217,"경남","함안","북경남S/S #6 Sh.R","북경남S/S 345kV #6Sh.R GIS 보통점검","북경남S/S 7979, 7971, 7900 GIS 보통점검","2018-06-11 09:30","2018-06-12 17:30","2018-06-11 09:30","2018-06-12 17:30","당일",null,null,null,201804100029]
[218,"경남","함안","북경남S/S #7 Sh.R","북경남S/S 345kV #7Sh.R GIS 보통점검","북경남S/S 7B79, 7B71, 7B00 GIS 보통점검","2018-06-14 09:30","2018-06-15 17:30","2018-06-14 09:30","2018-06-15 17:30","당일",null,null,null,201804100038]
[219,"경남","함안","북경남S/S 북경남-고령 #1T/L CB (7872)","북경남S/S 북경남-고령#1T/L GIS 보통점검","북경남S/S 북경남-고령#1T/L 7872 GIS 보통점검","2018-06-21 09:30","2018-06-21 17:30","2018-06-21 09:30","2018-06-21 17:30","당일",null,null,null,201804100042]
[220,"경남","함안","북경남S/S 북경남-무주양수 T/L CB (7C72)","북경남S/S 북경남-무주양수T/L GIS 보통점검","북경남S/S 북경남-무주양수T/L 7C72 GIS 보통점검","2018-06-18 09:30","2018-06-18 17:30","2018-06-18 09:30","2018-06-18 17:30","당일",null,null,null,201804100039]
[221,"경남","함안","북경남S/S 신옥천-북경남 T/L CB (7B72)","북경남S/S 신옥천-북경남T/L GIS 보통점검","북경남S/S 신옥천-북경남T/L 7B72 GIS 보통점검","2018-06-22 09:30","2018-06-22 17:30","2018-06-22 09:30","2018-06-22 17:30","당일",null,null,null,201804100043]
[222,"경남","함안","신마산S/S #1 M.Tr A","345kV 신마산S/S 용량부족차단기 대체공사","#1M.Tr측 전력구 시공관련 안전이격거리 확보(가시설설치 및 터파기)","2018-06-01 09:30","2018-06-12 18:00","2018-06-01 09:30","2018-06-12 18:00","연속",null,null,null,201804050239]
[223,"경남","함안","신마산S/S #4 M.Tr A","345kV 신마산S/S 용량부족차단기 대체공사","#4M.Tr측 전력구 시공관련 안전이격거리 확보(가시설 설치 및 터파기)","2018-06-14 09:30","2018-06-23 18:00","2018-06-14 09:30","2018-06-23 18:00","연속",null,null,null,201804050244]
[224,"전북","군산","새만금S/S 345kV #1BUS","새만금S/S 345kV Sh.R 설치공사","새만금S/S 345kV Sh.R 설치공사","2018-06-14 09:00","2018-06-15 18:00","2018-06-14 09:00","2018-06-15 18:00","연속",null,null,null,201804050245]
[225,"전북","군산","군산새만금#1 T/L","새만금S/S 345kV Sh.R 설치공사","새만금S/S 345kV Sh.R 설치공사","2018-06-14 09:00","2018-06-15 18:00","2018-06-14 09:00","2018-06-15 18:00","연속",null,null,null,201804050246]

{"sheet":"154송부","index":2,"n_rows":401,"n_cols":16,"rows_kept":401,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"\"2018년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2018년도 6월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","방학창동#1 T/L","18년 성동P/O 관내 170kV GIS 조작시험","170kV GIS 조작시험 (차단기 개폐타임 측정)","2018-06-12 09:30","2018-06-12 11:30","2018-06-12 09:30","2018-06-12 11:30","당일",null,null,null,201804170396,"-"]
[2,"서울","성동","방학창동#2 T/L","18년 성동P/O 관내 170kV GIS 조작시험","170kV GIS 조작시험 (차단기 개폐타임 측정)","2018-06-12 13:00","2018-06-12 15:00","2018-06-12 13:00","2018-06-12 15:00","당일",null,null,null,201804170397,"-"]
[3,"서울","성동","성동S/S 154kV #60 BUS","변전소 인출선로 재배치 공사","성동S/S 154kV 인출선로 재배치 공사 (성동종로T/L 이설공사)","2018-06-14 09:30","2018-06-22 18:00","2018-06-21 09:30","2018-06-29 18:00","연속",null,null,null,201804130250,"-"]
[4,"서울","성동","성동S/S 154kV #61 BUS","변전소 인출선로 재배치 공사","성동S/S 154kV 인출선로 재배치 공사 (성동종로T/L 이설공사)","2018-06-05 09:30","2018-06-11 18:00","2018-06-14 09:30","2018-06-20 18:00","연속",null,null,null,201804130244,"-"]
[5,"서울","성동","성동S/S 154kV #65 BUS","변전소 인출선로 재배치 공사","성동S/S 154kV 인출선로 재배치 공사 (성동종로T/L 이설공사)","2018-06-25 09:30","2018-07-03 18:00","2018-07-02 09:30","2018-07-10 18:00","연속",null,null,null,201804130252,"-"]
[6,"서울","성동","성동왕십리 T/L","18년 성동P/O 관내 170kV GIS 조작시험","170kV GIS 조작시험 (차단기 개폐타임 측정)","2018-06-07 14:00","2018-06-07 16:00","2018-06-07 14:00","2018-06-07 16:00","당일",null,null,null,201804170408,"-"]
[7,"서울","성동","성수S/S 154kV #1 BUS TIE CB","18년 성동P/O 관내 170kV GIS 조작시험","170kV GIS 조작시험 (차단기 개폐타임 측정)","2018-06-01 10:00","2018-06-01 12:00","취소","취소","당일",null,null,null,201804170413,"-"]
[8,"서울","성동","성수뚝도#1 T/L","18년 성동P/O 관내 170kV GIS 조작시험","170kV GIS 조작시험 (차단기 개폐타임 측정)","2018-06-04 10:00","2018-06-04 17:00","취소","취소","당일",null,null,null,201804170403,"-"]
[9,"서울","성동","성수뚝도#2 T/L","18년 성동P/O 관내 170kV GIS 조작시험","170kV GIS 조작시험 (차단기 개폐타임 측정)","2018-06-05 10:00","2018-06-05 17:00","취소","취소","당일",null,null,null,201804170404,"-"]
[10,"서울","성동","왕십리S/S 154kV BUS TIE CB","18년 성동P/O 관내 170kV GIS 조작시험","170kV GIS 조작시험 (차단기 개폐타임 측정)","2018-06-07 16:00","2018-06-07 18:00","2018-06-07 16:00","2018-06-07 18:00","당일",null,null,null,201804170410,"-"]
[11,"서울","성동","왕십리용두 T/L","18년 성동P/O 관내 170kV GIS 조작시험","170kV GIS 조작시험 (차단기 개폐타임 측정)","2018-06-07 10:00","2018-06-07 12:00","취소","취소","당일",null,null,null,201804170406,"-"]
[12,"서울","성동","창동돈암 T/L","18년 성동P/O 관내 170kV GIS 조작시험","170kV GIS 조작시험 (차단기 개폐타임 측정)","2018-06-12 15:00","2018-06-12 17:00","2018-06-12 15:00","2018-06-12 17:00","당일",null,null,null,201804170398,"-"]
[13,"서울","성동","화양성수 T/L","18년 성동P/O 관내 170kV GIS 조작시험","170kV GIS 조작시험 (차단기 개폐타임 측정)","2018-06-01 13:00","2018-06-01 15:00","2018-06-01 13:00","2018-06-01 15:00","당일",null,null,null,201804170414,"-"]
[14,"서울","중부","세종로옥인#2 T/L","154kV 옥인 및 운니S/S 인출T/L 교체공사","1. 사업목적 : 옥인 및 운니변전소 화재 및 대형 재난사고 예방 2. 사업구간 : 옥인S/S ∼ 옥인인출전력구, 운니S/S 운니인출전력구 3. 사업내용 - 철거 : 154kV OF 2000㎟ 4C, OF 1200㎟ 4C 총길이1.4㎞ - 신설 : 154kV XLPE 2000㎟ 4C, XLPE 1200㎟ 4C 총길이1.4㎞","2018-06-12 09:00","2018-07-13 18:00","2018-06-12 09:00","2018-07-13 18:00","연속",null,null,null,201804120041,"-"]
[15,"서울","중부","옥인운니#2 T/L","154kV 옥인 및 운니S/S 인출T/L 교체공사","- 154kV 옥인운니#2T/L 절연유 교체","2018-06-12 09:00","2018-06-22 18:00","2018-06-12 09:00","2018-06-22 18:00","연속",null,null,null,201804120046,"-"]
[16,"남서울","강남","반포S/S 154kV #1 BUS TIE CB","170kV GIS 개폐타임측정 및 조작시험","170kV GIS 개폐타임측정 및 조작시험","2018-06-18 10:00","2018-06-18 14:00","2018-06-18 10:00","2018-06-18 14:00","당일",null,null,null,201804130338,"-"]
[17,"남서울","동서울","동서울S/S 154kV #1 BUS TIE CB","차단기 조작시험","차단기 조작시험","2018-06-11 10:00","2018-06-11 13:00","2018-06-11 10:00","2018-06-11 13:00","당일",null,null,null,201804170288,"-"]
[18,"남서울","동서울","동서울S/S 154kV #2 BUS TIE CB","차단기 조작시험","차단기 조작시험","2018-06-11 13:00","2018-06-11 16:00","2018-06-11 13:00","2018-06-11 16:00","당일",null,null,null,201804170289,"-"]
[19,"남서울","동서울","산성수서#1 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2018-06-21 09:00","2018-06-21 13:00","2018-06-21 09:00","2018-06-21 13:00","당일",null,null,null,201804170273,"-"]
[20,"남서울","동서울","산성수서#2 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2018-06-21 13:00","2018-06-21 16:00","2018-06-21 13:00","2018-06-21 16:00","당일",null,null,null,201804170274,"-"]
[21,"남서울","영등포","신광명광명#1 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사","가공-GIS 접속, 보호반교체","2018-06-04 08:00","2018-06-08 18:00","2018-06-04 08:00","2018-06-08 18:00","당일",null,null,null,201803200042,"-"]
[22,"남서울","영등포","신광명광명#2 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사","가공-GIS 접속, 보호반교체","2018-06-25 08:00","2018-06-29 18:00","2018-06-25 08:00","2018-06-29 18:00","당일",null,null,null,201803200046,"-"]
[23,"인천","김포","신경서경서#1 T/L","154kV 신경서-경서 등 3개T/L 접지선 교체 및 병행지선 설치공사","○ 접지선 교체 : 접속함 규격 미달개소 보강을 통한 설비신뢰도 향상 - 접속함 : 154kV 신경서-영종T/L J/B #2 등 29 개소 (접지선 150㎟ → 240㎟ ) ○ 병행지선 설치 : 취약개소 병행지선 보강 및 최적 설치로 설비 고장예방 - 병행지선 : 154kV 신경서-경서 #1,2T/L J/B #18~ 경서 EBG 등 4개소","2018-06-01 09:00","2018-06-02 18:00","2018-06-01 09:00","2018-06-02 18:00","연속",null,null,null,201804130139,"-"]
[24,"인천","김포","신경서경서#2 T/L","154kV 신경서-경서 등 3개T/L 접지선 교체 및 병행지선 설치공사","○ 접지선 교체 : 접속함 규격 미달개소 보강을 통한 설비신뢰도 향상 - 접속함 : 154kV 신경서-영종T/L J/B #2 등 29 개소 (접지선 150㎟ → 240㎟ ) ○ 병행지선 설치 : 취약개소 병행지선 보강 및 최적 설치로 설비 고장예방 - 병행지선 : 154kV 신경서-경서 #1,2T/L J/B #18~ 경서 EBG 등 4개소","2018-06-04 09:00","2018-06-05 18:00","2018-06-04 09:00","2018-06-05 18:00","연속",null,null,null,201804130140,"-"]
[25,"인천","김포","영종경서 T/L","154kV 신경서-경서 등 3개T/L 접지선 교체 및 병행지선 설치공사","○ 접지선 교체 : 접속함 규격 미달개소 보강을 통한 설비신뢰도 향상 - 접속함 : 154kV 신경서-영종T/L J/B #2 등 29 개소 (접지선 150㎟ → 240㎟ ) ○ 병행지선 설치 : 취약개소 병행지선 보강 및 최적 설치로 설비 고장예방 - 병행지선 : 154kV 신경서-경서 #1,2T/L J/B #18~ 경서 EBG 등 4개소","2018-06-14 09:00","2018-06-16 18:00","2018-06-14 09:00","2018-06-16 18:00","연속",null,null,null,201804130137,"-"]
[26,"인천","시흥","동시화서시화 T/L","동,서시화S/S 동시화서시화 T/L GIS 보통점검","동,서시화S/S 동시화서시화 T/L GIS 보통점검","2018-06-26 10:00","2018-06-26 18:00","2018-06-12 10:00","2018-06-12 18:00","당일",null,null,null,201804130296,"-"]
[27,"인천","시흥","북시화서시화#3 T/L","북,서시화S/S 북시화서시화#3 T/L 동작시험","북,서시화S/S 북시화서시화#3 T/L 동작시험","2018-06-19 10:00","2018-06-19 18:00","2018-06-05 10:00","2018-06-05 18:00","당일",null,null,null,201804130274,"-"]
[28,"인천","시흥","소래S/S 154kV #2 BUS","소래S/S #4 M.Tr 1차 GIS 정밀점검[무부하용]","소래S/S #4 M.Tr 1차 GIS 정밀점검[무부하용]","2018-06-21 14:00","2018-06-21 18:00","2018-06-21 14:00","2018-06-21 18:00","당일",null,null,null,201804130291,"-"]
[29,"인천","시흥","신시흥#1S/S 154kV #66 BUS","신시흥#1S/S 154kV #62 Sh.C GIS 정밀점검","신시흥#1S/S 154kV #62 Sh.C GIS 정밀점검[무부하용]","2018-06-01 15:00","2018-06-01 18:00","2018-06-01 15:00","2018-06-01 18:00","당일",null,null,null,201803150420,"-"]
[30,"인천","시흥","신시흥#2S/S 154kV #68 BUS","신시흥#2S/S 154kV #67 Sh.C GIS 정밀점검[무부하용]","신시흥#2S/S 154kV #67 Sh.C GIS 정밀점검[무부하용]","2018-06-05 14:00","2018-06-05 18:00","2018-06-05 14:00","2018-06-05 18:00","당일",null,null,null,201804130277,"-"]
[31,"인천","시흥","신시흥#2S/S 154kV #68 BUS","신시흥#2S/S 154kV #68 Sh.C GIS 정밀점검[무부하용]","신시흥#2S/S 154kV #68 Sh.C GIS 정밀점검[무부하용]","2018-06-08 14:00","2018-06-08 18:00","2018-06-08 14:00","2018-06-08 18:00","당일",null,null,null,201804130278,"-"]
[32,"인천","시흥","신시흥남동#1 T/L","신시흥,남동S/S 신시흥남동#1T/L 보통점검","신시흥,남동S/S 신시흥남동#1T/L 보통점검","2018-06-07 10:00","2018-06-07 18:00","2018-06-07 10:00","2018-06-07 18:00","당일",null,null,null,201804130275,"-"]
[33,"인천","시흥","신시흥남동#2 T/L","신시흥,남동S/S 신시흥남동#2 T/L GIS 동작시험","신시흥,남동S/S 신시흥남동#2 T/L GIS 동작시험","2018-06-16 09:00","2018-06-16 18:00","2018-06-16 09:00","2018-06-16 18:00","당일",null,null,null,201804130298,"-"]
[34,"인천","시흥","신시흥오봉 T/L","신시흥,오봉S/S 신시흥오봉T/L GIS 동작시험","신시흥,오봉S/S 신시흥오봉T/L GIS 동작시험","2018-06-23 09:00","2018-06-23 18:00","2018-06-23 09:00","2018-06-23 18:00","당일",null,null,null,201804130300,"-"]
[35,"인천","시흥","연수S/S 154kV #2 BUS","연수S/S #4 M.Tr 1차 GIS 정밀점검[무부하용]","연수S/S #4 M.Tr 1차 GIS 정밀점검[무부하용]","2018-06-19 14:00","2018-06-19 18:00","2018-06-19 14:00","2018-06-19 18:00","당일",null,null,null,201804130290,"-"]
[36,"인천","인천","계양북인천 T/L","2018년 인천전력지사 170kV GIS 정밀점검공사","북인천S/S 계양북인천T/L GIS 정밀점검","2018-06-18 09:00","2018-06-20 18:00","2018-06-04 09:00","2018-06-06 18:00","연속",null,null,null,201804050358,"-"]
[37,"인천","인천","남인천학익#1 T/L","2018년 인천전력지사 170kV GIS 정밀점검공사","학익S/S 남인천학익#1T/L GIS 정밀점검","2018-06-04 09:00","2018-06-06 18:00","2018-07-05 09:00","2018-07-07 18:00","연속",null,null,null,201804050352,"-"]
[38,"인천","인천","남인천학익#2 T/L","2018년 인천전력지사 170kV GIS 정밀점검공사","학익S/S 남인천학익#2T/L GIS 정밀점검","2018-06-11 09:00","2018-06-13 18:00","2018-07-02 09:00","2018-07-04 18:00","연속",null,null,null,201804050354,"-"]
[39,"인천","인천","북인천원창 T/L","2018년 인천전력지사 170kV GIS 정밀점검공사","북인천S/S 북인천원창T/L GIS 정밀점검","2018-06-25 09:00","2018-06-27 18:00","2018-06-18 09:00","2018-06-20 18:00","연속",null,null,null,201804050359,"-"]
[40,"인천","인천","신가좌신현#1 T/L","신현S/S 170kV GIS 대체공사(4차)_#1BUS무부하","○ 신현S/S 170kV GIS 대체공사(#1M.Tr, 신현송현#2T/L)_4차 ☞ #1M.Tr, 신현송현#2T/L 대체","2018-06-23 18:00","2018-06-24 18:00","2018-06-23 18:00","2018-06-24 18:00","연속",null,null,null,201803140025,"-"]
[41,"인천","인천","신가좌신현#1 T/L","신현S/S 170kV GIS 대체공사(4차)_#2BUS무부하","○ 신현S/S 170kV GIS 대체공사(#1M.Tr, 신현송현#2T/L)_4차 ☞ #1M.Tr, 신현송현#2T/L 대체 ☞ 최종 무부하","2018-06-26 18:00","2018-06-27 18:00","2018-06-26 18:00","2018-06-27 18:00","연속",null,null,null,201803140026,"-"]
[42,"인천","인천","신가좌신현#1 T/L","154kV 신가좌-주안 등 2개 T/L 자기애관교체공사","자기애관 교체를 통한 설비 2차 확산피해 방지","2018-06-28 09:00","2018-06-30 18:00","2018-06-28 09:00","2018-06-30 18:00","연속",null,null,null,201803160116,"-"]
[43,"인천","인천","신가좌주안#1 T/L","154kV 신가좌-주안 2개 T/L 자기애관 교체공사","자기애관 교체를 통한 설비 2차 확산피해 방지","2018-06-01 09:00","2018-06-03 18:00","2018-06-01 09:00","2018-06-03 18:00","연속",null,null,null,201803160114,"-"]
[44,"인천","인천","신가좌주안#2 T/L","154kV 신가좌-주안 2개 T/L 자기애관 교체공사","자기애관 교체를 통한 설비 2차 확산피해 방지","2018-06-01 09:00","2018-06-03 18:00","2018-06-01 09:00","2018-06-03 18:00","연속",null,null,null,201803160115,"-"]
[45,"인천","인천","신경서S/S 154kV #61-66 BUS TIE GIS","신경서S/S 6200 GIS 조작시험","신경서S/S 6200 GIS 조작시험","2018-06-11 09:00","2018-06-11 12:00","취소","취소","당일",null,null,null,201804100202,"-"]
[46,"인천","인천","신경서S/S 65-66 SEC GIS","신경서S/S 65-66-0 GIS 보통점검","신경서S/S 65-66-0 GIS 보통점검","2018-06-11 12:00","2018-06-11 18:00","2018-06-11 09:00","2018-06-11 18:00","당일",null,null,null,201804100201,"-"]
[47,"인천","인천","신경서영종 T/L","154kV 신경서-경서 등 3개T/L 접지선 교체 및 병행지선 설치공사","○ 접지선 교체 : 접속함 규격 미달개소 보강을 통한 설비신뢰도 향상 - 접속함 : 154kV 신경서-영종T/L J/B #2 등 29 개소 (접지선 150㎟ → 240㎟ )","2018-06-11 09:00","2018-06-12 18:00","2018-06-11 09:00","2018-06-12 18:00","연속",null,null,null,201804130129,"-"]
[48,"인천","인천","신현S/S 154kV #1 BUS","신현S/S 170kV GIS 대체공사(4차)","○ 신현S/S 170kV GIS 대체공사(#1M.Tr, 신현송현#2T/L_4차 ☞ #1M.Tr, 신현송현#2T/L 대체","2018-06-22 08:00","2018-06-24 18:00","2018-06-22 08:00","2018-06-24 18:00","연속",null,null,null,201803140022,"-"]
[49,"인천","인천","신현S/S 154kV #2 BUS","신현S/S 170kV GIS 대체공사(4차)","○ 신현S/S 170kV GIS 대체공사(#1M.Tr, 신현송현#2T/L_4차 ☞ #1M.Tr, 신현송현#2T/L 대체","2018-06-25 08:00","2018-06-27 18:00","2018-06-25 08:00","2018-06-27 18:00","연속",null,null,null,201803140024,"-"]
[50,"인천","인천","영종중산 T/L","영종,중산S/S 영종중산T/L GIS 초기점검","영종S/S 영종중산T/L GIS 조작시험 중산S/S 영종중산T/L GIS 초기점검","2018-06-29 09:00","2018-06-29 18:00","2018-06-29 09:00","2018-06-29 18:00","당일",null,null,null,201804100209,"-"]
[51,"인천","인천","인천CC S/Y 154kV #1 BUS TIE GIS","인천복합S/Y 6100 GIS 조작시험","인천복합S/Y 6100 GIS 조작시험","2018-06-01 09:00","2018-06-01 18:00","2018-06-01 09:00","2018-06-01 18:00","당일",null,null,null,201804100188,"-"]
[52,"인천","인천","인천CC S/Y 154kV #2 BUS TIE GIS","인천복합S/Y 6200 GIS 조작시험","인천복합S/Y 6200 GIS 조작시험","2018-06-27 09:00","2018-06-27 18:00","취소","취소","당일",null,null,null,201804100197,"-"]
[53,"인천","인천","인천CC S/Y 60-61 SEC GIS","인천복합S/Y 60-61-0 GIS 조작시험","인천복합S/Y 60-61-0 GIS 조작시험","2018-06-07 09:00","2018-06-07 18:00","취소","취소","당일",null,null,null,201804100194,"-"]
[54,"인천","인천","인천CC북인천#1 T/L","인천복합S/Y,북인천S/S 인천CC북인천#1T/L GIS 조작시험","인천복합S/Y 인천CC북인천#1T/L GIS 조작시험 북인천S/S 인천CC북인천#1T/L GIS 조작시험","2018-06-28 09:00","2018-06-28 13:00","2018-06-28 09:00","2018-06-28 13:00","당일",null,null,null,201804100207,"-"]
[55,"인천","인천","인천CC북인천#2 T/L","인천복합S/Y,북인천S/S 인천CC북인천#2T/L GIS 조작시험","인천복합S/Y 인천CC북인천#2T/L GIS 조작시험 북인천S/S 인천CC북인천#2T/L GIS 조작시험","2018-06-28 13:00","2018-06-28 18:00","2018-06-28 13:00","2018-06-28 18:00","당일",null,null,null,201804100208,"-"]
[56,"인천","인천","학익연수#1 T/L","학익연수T/L 병행지선 보강공사","지중송전선로 병행지선 설치","2018-06-29 09:00","2018-06-29 14:00","2018-06-29 09:00","2018-06-29 14:00","당일",null,null,null,201804090203,"-"]
[57,"인천","인천","학익연수#2 T/L","학익연수T/L 병행지선 보강공사","지중송전선로 병행지선 설치","2018-06-29 14:00","2018-06-29 18:00","2018-06-29 14:00","2018-06-29 18:00","당일",null,null,null,201804090207,"-"]
[58,"인천","직할","신부평S/S 154kV #60 BUS","154kV 신부평-중동 등 3개T/L 인출Bay 정비공사 준공시험","154kV 신부평-중동 등 3개T/L 인출Bay 정비공사 무부하가압용","2018-06-08 09:00","2018-06-08 18:00","2018-06-27 09:00","2018-06-27 18:00","당일",null,null,null,201804120080,"-"]
[59,"인천","직할","신부평S/S 154kV #60 BUS","154kV 신부평-중동 등 3개T/L 인출Bay 정비공사 준공시험","154kV 신부평-중동 등 3개T/L 인출Bay 정비공사 무부하가압용","2018-06-30 09:00","2018-06-30 18:00","취소","취소","당일",null,null,null,201804120082,"-"]
[60,"인천","직할","신부평S/S 154kV #66 BUS","154kV 신부평-중동 등 3개T/L 인출Bay 정비공사 준공시험","154kV 신부평-중동 등 3개T/L 인출Bay 정비공사 무부하가압용","2018-06-08 09:00","2018-06-08 18:00","2018-06-27 09:00","2018-06-27 18:00","당일",null,null,null,201804120079,"-"]
[61,"인천","직할","신부평S/S 154kV #66 BUS","154kV 신부평-중동 등 3개T/L 인출Bay 정비공사 준공시험","154kV 신부평-중동 등 3개T/L 인출Bay 정비공사 무부하가압용","2018-06-30 09:00","2018-06-30 18:00","취소","취소","당일",null,null,null,201804120081,"-"]
[62,"인천","직할","신부평임학#2 T/L","154kV 신부평-중동 등 3개T/L 신부평변전소 인출Bay 정비공사","345kV 신부평변전소 154kV 지중T/L 인출Bay 정비(신부평S/S~J/B#1)","2018-06-10 09:00","2018-07-03 18:00","취소","취소","연속",null,null,null,201803130157,"-"]
[63,"인천","직할","신부평중동#3 T/L","154kV 신부평-중동 등 3개T/L 신부평변전소 인출Bay 정비공사","345kV 신부평변전소 154kV 지중T/L 인출Bay 정비(신부평S/S~J/B#1)","2018-06-10 09:00","2018-07-03 18:00","취소","취소","연속",null,null,null,201803130156,"-"]
[64,"경기북부","고양","문발파주열병합#1T/L","18년 고양전력지사 변전협력총액공사","170kV GIS 보통점검","2018-06-01 08:00","2018-06-01 18:00","2018-06-01 08:00","2018-06-01 18:00","당일",null,null,null,201804120315,"-"]
[65,"경기북부","고양","문발파주열병합#2T/L","18년 고양전력지사 변전협력총액공사","170kV GIS 보통점검","2018-06-07 10:00","2018-06-07 18:00","2018-06-07 10:00","2018-06-07 18:00","당일",null,null,null,201804120317,"-"]
[66,"경기북부","고양","능곡상암#1 T/L","2018년 변전정비회사 총액공사(보호PNL 대체)","능곡S/S 능곡-상암#1T/L 보호PNL 대체 상암S/S 능곡-상암#1T/L 보호PNL 대체","2018-06-20 09:00","2018-06-22 18:00","2018-06-20 09:00","2018-06-22 18:00","연속",null,null,null,201804110045,"-"]
[67,"경기북부","고양","덕이호수#1 T/L","154kV 덕이-호수#1T/L일진제 PMJ 불량접속함 리콜공사","일진제 PMJ 불량접속함 6개소(J/B#1, 2, 3, 6, 7, 8) 교체","2018-06-15 08:00","2018-06-28 18:00","2018-06-15 08:00","2018-06-28 18:00","연속",null,null,null,201804130122,"-"]
[68,"경기북부","고양","덕이호수#2 T/L","154kV 덕이-호수#2T/L일진제 PMJ 불량접속함 리콜공사","일진제 PMJ 불량접속함 6개소(J/B#1, 2, 3, 6, 7, 8) 교체","2018-06-29 08:00","2018-07-12 18:00","2018-06-29 08:00","2018-07-12 18:00","연속",null,null,null,201804130127,"-"]
[69,"경기북부","고양","신덕은S/S 60-61 SEC GIS","18년도 고양전력지사 변전협력회사총액공사(60-61GIS조작시험)","신덕은변전소 60-61 GIS 조작시험","2018-06-07 10:00","2018-06-07 12:00","2018-06-07 10:00","2018-06-07 12:00","당일",null,null,null,201804130206,"-"]
[70,"경기북부","고양","신덕은S/S 65-66 SEC GIS","18년도 고양전력지사 변전협력회사총액공사(65-66GIS조작시험)","신덕은변전소 65-66 GIS 조작시험","2018-06-07 13:00","2018-06-07 16:00","2018-06-07 13:00","2018-06-07 16:00","당일",null,null,null,201804130205,"-"]
[71,"경기북부","고양","양주고양#2 T/L","No.26~27 선하지 공사현장 교각 Coping Form 설치","No.26~27 선하지 서울-문산 고속도로 건설공사 현장 교각 Coping Form 설치 시 크레인 사용으로 인한 전력선 안전이격거리 확보","2018-06-01 07:00","2018-06-01 18:00","2018-06-01 07:00","2018-06-01 18:00","당일",null,null,null,201804160064,"○"]
[72,"경기북부","고양","원흥수색#1 T/L","154kV 원흥-수색T/L 지중화 정비공사","ㅁ 임시선로 구성(철탑2기 설치) ㅁ No.4 ~ 5, No.6~8","2018-06-23 07:00","2018-06-24 18:00","2018-06-23 07:00","2018-06-24 18:00","연속",null,null,null,201804160181,"-"]
[73,"경기북부","고양","원흥수색#2 T/L","154kV 원흥-수색T/L 지중화 정비공사","ㅁ 임시선로 구성(철탑2기 설치) ㅁ No.4 ~ 5, No.6~8","2018-06-16 07:00","2018-06-17 18:00","2018-06-16 07:00","2018-06-17 18:00","연속",null,null,null,201804160180,"-"]
[74,"경기북부","고양","일산S/S #6G/T GIS","18년 고양전력지사 변전협력총액공사","170kV GIS 보통점검","2018-06-19 10:00","2018-06-19 18:00","2018-06-19 10:00","2018-06-19 18:00","당일",null,null,null,201804120319,"-"]
[75,"경기북부","고양","일산S/S 154kV #60 BUS","2018년 상반기 고양전력지사 170kV GIS 정밀점검공사","일산S/S 일산-호수 #2T/L(697) GIS 정밀점검","2018-06-10 09:30","2018-06-11 12:00","2018-06-10 09:30","2018-06-11 12:00","연속",null,null,null,201803070200,"-"]
[76,"경기북부","고양","일산S/S 154kV #60 BUS","2018년 상반기 고양전력지사 170kV GIS 정밀점검공사","일산S/S 일산-호수 #1T/L(687) GIS 정밀점검","2018-06-04 09:30","2018-06-05 12:00","2018-06-14 09:30","2018-06-15 12:00","연속",null,null,null,201803070201,"-"]
[77,"경기북부","고양","일산S/S 154kV #65 BUS","2018년 상반기 고양전력지사 170kV GIS 정밀점검공사","일산S/S 일산-호수 #1T/L(687) GIS 정밀점검","2018-06-05 12:00","2018-06-06 18:00","2018-06-15 12:00","2018-06-16 18:00","연속",null,null,null,201803070202,"-"]
[78,"경기북부","고양","일산S/S 154kV #65 BUS","2018년 상반기 고양전력지사 170kV GIS 정밀점검공사","일산S/S 일산-호수 #2T/L(697) GIS 정밀점검","2018-06-11 12:00","2018-06-12 18:00","2018-06-11 12:00","2018-06-12 18:00","연속",null,null,null,201803070203,"-"]
[79,"경기북부","고양","일산호수#1 T/L","2018년 상반기 고양전력지사 170kV GIS 정밀점검공사","일산S/S 일산-호수 #1T/L(687) GIS 정밀점검","2018-06-04 09:30","2018-06-06 18:00","2018-06-14 09:30","2018-06-16 18:00","연속",null,null,null,201803070197,"-"]
[80,"경기북부","고양","일산호수#2 T/L","2018년 상반기 고양전력지사 170kV GIS 정밀점검공사","일산S/S 일산-호수 #2T/L(697) GIS 정밀점검","2018-06-10 09:30","2018-06-12 18:00","2018-06-10 09:30","2018-06-12 18:00","연속",null,null,null,201803070198,"-"]
[81,"경기북부","구리","가평청평HP#1 T/L","가평-청평HP #1T/L 보호반 교체공사","가평-청평HP #1T/L 보호반 교체","2018-06-18 08:00","2018-06-20 18:00","2018-06-20 08:00","2018-06-22 18:00","연속",null,null,null,201803080384,"-"]
[82,"경기북부","구리","가평청평HP#2 T/L","가평-청평H/P #2T/L 보호반 교체공사","가평-청평H/P #2T/L 보호반 교체","2018-06-21 08:00","2018-06-23 18:00","2018-06-25 08:00","2018-06-27 18:00","연속",null,null,null,201803080390,"-"]
[83,"경기북부","구리","덕소진건#1 T/L","345kV 신의정부-미금T/L 전선접속개소 전선교체공사","345kV 신의정부-미금#1,2T/L 전력선 교체: No.1.2~4,No.29~33 (상단 345kV 신의정부-미금#1,2T/L 작업 안전을 위한 병행하단 휴전)","2018-06-28 09:00","2018-07-01 18:00","2018-06-28 09:00","2018-07-01 18:00","연속",null,null,null,201803150177,"○"]
[84,"경기북부","구리","덕소진건#2 T/L","345kV 신의정부-미금T/L 전선접속개소 전선교체공사","345kV 신의정부-미금#1,2T/L 전력선 교체: No.1.2~4,No.29~33 (상단 345kV 신의정부-미금#1,2T/L 작업 안전을 위한 병행하단 휴전)","2018-06-28 09:00","2018-07-01 18:00","2018-06-28 09:00","2018-07-01 18:00","연속",null,null,null,201803150178,"○"]
[85,"경기북부","구리","덕소팔당HP T/L","2017-2018년 지중송전설비 위탁정비공사","- 대상설비 : 154kV 덕소-팔당HPT/L No.38호C/H EB-A 3상 - 작업내용 : 접속개소 점검 및 애관청소, 피뢰기 Doble 점검","2018-06-04 09:00","2018-06-04 18:00","2018-06-04 09:00","2018-06-04 18:00","당일",null,null,null,201804040115,"-"]
[86,"경기북부","구리","덕소팔당HP청평HP T/L","2017-2018년 지중송전설비 위탁정비공사","- 대상설비 : 154kV 덕소-팔당HP-청평HPT/L No.68호C/H EB-A 3상 - 작업내용 : 접속개소 점검 및 애관청소, 피뢰기 Doble 점검","2018-06-05 09:00","2018-06-05 18:00","2018-06-05 09:00","2018-06-05 18:00","당일",null,null,null,201804040125,"-"]
[87,"경기북부","구리","문막용문 T/L","2018~19년도 구리전력지사 가공송전정비 협력회사 총액공사","154kV 문막-용문T/L 애자련보강공사 - 대상 : No.63호","2018-06-26 07:30","2018-06-26 14:00","2018-06-26 07:30","2018-06-26 14:00","당일",null,null,null,201804050306,"-"]
[88,"경기북부","구리","문막지제 T/L","2018~19년도 구리전력지사 가공송전정비 협력회사 총액공사","154kV 문막-지제T/L 애자련보강공사 - 대상 : No.63호","2018-06-26 14:00","2018-06-26 18:00","2018-06-26 14:00","2018-06-26 18:00","당일",null,null,null,201804050307,"-"]
[89,"경기북부","구리","미금S/S 154kV #61 BUS","170kV 미금S/S 장기사용 GIS 교체공사","- 170kV GIS 철거, 설치(미금-광장, 미금-아리수#2T/L, #1Sh.C 1차 GIS) - 기타부대공사 * 상기작업 인접Bay 크레인작업 안전조치 휴전","2018-06-05 09:00","2018-06-19 08:00","2018-06-05 09:00","2018-06-19 08:00","연속",null,null,null,201802190232,"-"]
[90,"경기북부","구리","미금S/S 154kV #66 BUS","170kV 미금S/S 장기사용 GIS 교체공사","* 상기작업 인접Bay 크레인작업 안전조치 휴전 - 170kV GIS 철거, 설치(미금-광장, 미금-아리수#2T/L, #1Sh.C 1차 GIS) - 기타부대공사","2018-06-01 09:00","2018-06-05 08:00","2018-06-01 09:00","2018-06-05 08:00","연속",null,null,null,201802190230,"-"]
[91,"경기북부","구리","미금S/S 154kV #66 BUS","170kV 미금S/S 장기사용 GIS 교체공사","* 상기작업 인접Bay 크레인작업 안전조치 휴전 - 170kV GIS 철거, 설치(미금-광장, 미금-아리수#2T/L, #1Sh.C 1차 GIS) - 기타부대공사","2018-06-19 09:00","2018-06-29 18:00","2018-06-19 09:00","2018-06-29 18:00","연속",null,null,null,201804200042,"-"]
[92,"경기북부","구리","미금S/S 미금-광장T/L GIS","170kV 미금S/S 장기사용 GIS 교체공사","* 상기작업 인접Bay 크레인작업 안전조치 휴전 - 170kV GIS 철거, 설치(미금-광장T/L GIS) - 기타부대공사","2018-06-01 09:00","2018-06-29 18:00","2018-06-01 09:00","2018-06-29 18:00","연속",null,null,null,201802190227,"-"]
[93,"경기북부","구리","별내S/S 별내-열병합#1T/L GIS","18년 구리전력지사 154kV GIS 정밀점검","- 대상 : 별내 열병합 #1T/L (유압, 공기 2일)","2018-06-06 09:00","2018-06-07 18:00","2018-06-06 09:00","2018-06-07 18:00","연속",null,null,null,201804190060,"-"]
[94,"경기북부","구리","별내S/S 별내-열병합#2T/L GIS","18년 구리전력지사 154kV GIS 정밀점검","- 대상 : 별내 열병합 #2T/L (유압, 공기 2일)","2018-06-01 09:00","2018-06-02 18:00","2018-06-01 09:00","2018-06-02 18:00","연속",null,null,null,201804190061,"-"]
[95,"경기북부","구리","별내진접 T/L","345kV 신의정부-미금T/L 전선접속개소 전선교체공사","345kV 신의정부-미금#1,2T/L 전력선 교체: No.1.2~4,No.29~33 (상단 345kV 신의정부-미금#1,2T/L 작업 안전을 위한 병행하단 휴전)","2018-06-18 09:00","2018-06-22 18:00","2018-06-18 09:00","2018-06-22 18:00","연속",null,null,null,201803110021,"-"]
[96,"경기북부","구리","지제용문 T/L","지제S/S 154kV 제지-용문T/L GIS 보통점검","지제S/S 154kV 제지-용문T/L GIS 보통점검","2018-06-11 09:00","2018-06-11 18:00","2018-06-11 09:00","2018-06-11 18:00","당일",null,null,null,201804150002,"-"]
[97,"경기북부","구리","진건별내#1 T/L","진건S/S 154kV 진건-별내#1 T/L GIS 보통점검","진건S/S 154kV 진건-별내#1 T/L GIS 보통점검","2018-06-05 09:00","2018-06-05 14:00","2018-06-05 09:00","2018-06-05 14:00","당일",null,null,null,201804150003,"○"]
[98,"경기북부","구리","진건별내#2 T/L","진건S/S 154kV 진건-별내#2T/L GIS 보통점검","진건S/S 154kV 진건-별내#2T/L GIS 보통점검","2018-06-05 14:00","2018-06-05 18:00","2018-06-05 14:00","2018-06-05 18:00","당일",null,null,null,201804150004,"○"]
[99,"경기북부","구리","진접S/S 154kV #1 BUS TIE CB","진접S/S 모선보호반 교체공사","모선보호반 교체 X 1식","2018-06-04 08:00","2018-06-07 18:00","2018-06-04 08:00","2018-06-07 18:00","연속",null,null,null,201804180104,"-"]
[100,"경기북부","구리","청평HP의암HP T/L","청평H/P 단로기 보통점검","- 651, 6100, 6300 DS 보통점검 - 관련휴전 : 청평의암T/L, #1M.Tr 2차CB, #3M.Tr 2차 CB","2018-06-04 09:00","2018-06-04 18:00","2018-06-04 09:00","2018-06-04 18:00","당일",null,null,null,201804090159,"-"]
[101,"경기북부","구리","청평P/P #1 M.Tr 2차 CB","청평P/P #1BUS 단로기 점검","청평P/P #1BUS 단로기 점검 - #1M.Tr 2차 #1DS(6131), #1S.Tr DS(6335), #2M.Tr 2차 #1DS(6231)","2018-06-28 09:00","2018-06-28 13:00","2018-06-28 09:00","2018-06-28 13:00","당일",null,null,null,201804090229,"-"]
[102,"경기북부","구리","청평P/P #1 M.Tr 2차 CB","청평P/P #2BUS 단로기 점검","청평P/P #2BUS 단로기 점검 - #1M.Tr 2차 #2DS(6132), #1S.Tr DS(6435), #2M.Tr 2차 #2DS(6232)","2018-06-29 09:00","2018-06-29 13:00","2018-06-29 09:00","2018-06-29 13:00","당일",null,null,null,201804090250,"-"]
[103,"경기북부","구리","청평P/P #2 M.Tr 2차 CB","청평P/P #1BUS 단로기 점검","청평P/P #1BUS 단로기 점검 - #1M.Tr 2차 #1DS(6131), #1S.Tr DS(6335), #2M.Tr 2차 #1DS(6231)","2018-06-28 15:00","2018-06-28 17:00","2018-06-28 15:00","2018-06-28 17:00","당일",null,null,null,201804090234,"-"]
[104,"경기북부","구리","청평P/P #2 M.Tr 2차 CB","청평P/P #2BUS 단로기 점검","청평P/P #2BUS 단로기 점검 - #1M.Tr 2차 #2DS(6132), #2S.Tr DS(6435), #2M.Tr 2차 #2DS(6232)","2018-06-29 15:00","2018-06-29 17:00","2018-06-29 15:00","2018-06-29 17:00","당일",null,null,null,201804090260,"-"]
[105,"경기북부","구리","청평P/P 154kV #1 BUS TIE GIS","18년 구리전력지사 154kV GIS 정밀점검","- 대상 : 청평양수 BUS TIE (유압, 공기 2일)","2018-06-14 09:00","2018-06-15 18:00","2018-06-14 09:00","2018-06-15 18:00","연속",null,null,null,201804190064,"-"]
[106,"경기북부","구리","청평H/P #2 M.Tr 2차 CB","청평H/P 단로기 보통점검","- 6300DS 보통점검 DS 양측 CB 개방","2018-06-05 14:00","2018-06-05 18:00","2018-06-05 14:00","2018-06-05 18:00","매일",null,null,null,201804090196,"-"]
[107,"경기북부","구리","청평H/P #3 M.Tr 2차 CB","청평H/P 단로기 보통점검","-6.4(월) : 6100, 6300 DS 점검 -6.5(화) : 6200 DS 점검","2018-06-04 09:00","2018-06-05 18:00","2018-06-04 09:00","2018-06-05 18:00","매일",null,null,null,201804090166,"-"]
[108,"경기북부","구리","청평H/P #1 M.Tr 2차 CB","청평H/P 단로기 보통점검","- 651, 6100, 6300 DS 보통점검 - 관련휴전 : 청평의암T/L, #1M.Tr 2차CB, #3M.Tr 2차 CB","2018-06-04 09:00","2018-06-05 14:00","2018-06-04 09:00","2018-06-05 14:00","매일",null,null,null,201804090162,"-"]
[109,"경기북부","직할","양주S/S 154kV #62 BUS","'18~19 변전협력 총액공사","154kV LA 보통점검","2018-06-14 10:00","2018-06-14 14:00","2018-06-14 10:00","2018-06-14 14:00","당일",null,null,null,201804100012,"-"]
[110,"경기북부","직할","양주S/S 154kV #67 BUS","'18~19 변전협력 총액공사","154kV LA 보통점검","2018-06-14 14:00","2018-06-14 18:00","2018-06-14 14:00","2018-06-14 18:00","당일",null,null,null,201804100013,"-"]
[111,"경기","군포","관양평촌#1 T/L","2018군포 변전총액-평촌S/S 관양평촌#1 T/L하자점검","평촌S/S 154kV 관양평촌#1 T/L하자점검","2018-06-05 09:00","2018-06-05 18:00","2018-06-05 09:00","2018-06-05 18:00","당일",null,null,null,201803120512,"-"]
[112,"경기","군포","관양평촌#2 T/L","2018군포 변전총액-평촌S/S 관양평촌#2 T/L하자점검","평촌S/S 154kV 관양평촌#2 T/L하자점검","2018-06-04 09:00","2018-06-04 18:00","2018-06-04 09:00","2018-06-04 18:00","당일",null,null,null,201803120513,"-"]
[113,"경기","군포","반월시화#1 T/L","반월S/S 154kV 현대화공사","- 154kV CVT 이설","2018-06-07 09:30","2018-06-07 18:00","2018-06-07 09:30","2018-06-07 18:00","연속",null,null,null,201804040153,"-"]
[114,"경기","군포","반월시화#1 T/L","시화변전소 신시흥시화2TL GIS 대체관련 무부하 가압","시화변전소 신시흥시화2TL GIS 대체관련 24H 무부하 가압 시행","2018-06-22 09:00","2018-06-23 18:00","2018-06-22 09:00","2018-06-23 18:00","연속",null,null,null,201804050383,"-"]
[115,"경기","군포","반월시화#2 T/L","반월S/S 154kV 현대화공사","- 154kV CVT 이설","2018-06-08 09:30","2018-06-08 18:00","2018-06-08 09:30","2018-06-08 18:00","연속",null,null,null,201804040154,"-"]
[116,"경기","군포","서서울#2일동#1 T/L","154kV 일동S/S 서서울-일동#1T/L 하자점검","154kV 일동S/S 서서울-일동#1T/L 하자점검 피뢰기 하자점검","2018-06-19 09:00","2018-06-19 18:00","2018-06-19 09:00","2018-06-19 18:00","당일",null,null,null,201804110287,"-"]
[117,"경기","군포","서서울#2일동#2 T/L","154kV 일동S/S 서서울-일동#2T/L 하자점검","154kV 일동S/S 서서울-일동#2T/L 하자점검 피뢰기 하자점검","2018-06-20 09:00","2018-06-20 18:00","2018-06-20 09:00","2018-06-20 18:00","당일",null,null,null,201804110293,"-"]
[118,"경기","군포","신시흥시화#2 T/L","시화변전소 신시흥시화2TL GIS 대체공사","시화변전소 신시흥시화2TL 노후 GIS 대체작업","2018-06-14 09:00","2018-07-01 18:00","2018-06-14 09:00","2018-07-01 18:00","연속",null,null,null,201804050379,"-"]
[119,"경기","군포","신안산남안산#1 T/L","남안산 축소형 디지털모자익반 설치공사","남안산 축모반 설치공사 신안산SS- 677CB 조작시험(개폐타임 등) 남안산SS-신안산-남안산#1T/L 조작시험","2018-06-14 09:00","2018-06-16 18:00","2018-06-14 09:00","2018-06-16 18:00","연속",null,null,null,201804050373,"-"]
[120,"경기","군포","신안산남안산#2 T/L","남안산 축소형 디지털모자익반 설치공사","남안산 축모반 설치공사 신안산- 687CB 조작시험(개폐타임 등) 남안산- 신안산-남안산#2T/L 보조계전기 교체 및 조작시험","2018-06-18 09:00","2018-06-20 18:00","2018-06-18 09:00","2018-06-20 18:00","연속",null,null,null,201804050374,"-"]
[121,"경기","군포","안양평촌#2 T/L","2018군포 변전총액-평촌S/S 안양평촌#2 T/L조작시험","평촌S/S 154kV 안양양평촌#2 T/L조작시험","2018-06-07 09:00","2018-06-07 18:00","2018-06-07 09:00","2018-06-07 18:00","당일",null,null,null,201803120521,"-"]
[122,"경기","동부","곤지암S/S 154kV #66 BUS","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설 - 증설: #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설: #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2018-06-11 09:30","2018-06-17 17:00","2018-06-11 09:30","2018-06-17 17:00","연속",null,null,null,201804110008,"-"]
[123,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2018-06-07 09:30","2018-06-09 17:00","2018-06-07 09:30","2018-06-09 17:00","연속",null,null,null,201804110005,"-"]
[124,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2018-06-11 09:30","2018-06-12 18:00","2018-06-11 09:30","2018-06-12 18:00","연속",null,null,null,201804110010,"-"]
[125,"경기","동부","곤지암이천#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2018-06-03 09:30","2018-06-06 18:00","2018-06-03 09:30","2018-06-06 18:00","연속",null,null,null,201804110002,"-"]
[126,"경기","동부","곤지암이천#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2018-06-13 09:30","2018-06-16 17:00","2018-06-13 09:30","2018-06-16 17:00","연속",null,null,null,201804110012,"-"]
[127,"경기","동부","산성S/S 154kV #1 BUS TIE GIS","18년 동부변전 협력회사 총액공사","산성 154 #1BUSTIE GIS 보통점검","2018-06-15 09:30","2018-06-15 18:00","2018-06-15 09:30","2018-06-15 18:00","당일",null,null,null,201804110044,"○"]
[128,"경기","성남","남사진위#2 T/L","154kV 동탄S/S 건설공사","- 남사진위T/L 분기, 보호반대체 및 무부하가압","2018-06-01 09:00","2018-06-29 18:00","2018-05-25 09:00","2018-06-15 18:00","연속",null,null,null,201804130082,"-"]
[129,"경기","성남","신성남서판교 #1 T/L","신성남-서판교#1T/L 보통점검, 조작시험","신성남S/S 신성남-서판교#1T/L 조작시험 서판교S/S 신성남-서판교#1T/L 보통점검","2018-06-27 09:00","2018-06-27 18:00","2018-06-27 09:00","2018-06-27 18:00","당일",null,null,null,201804130050,"-"]
[130,"경기","성남","신성남서판교 #2 T/L","신성남-서판교#2T/L 보통점검, 조작시험","신성남S/S 신성남-서판교#2T/L 조작시험 서판교S/S 신성남-서판교#2T/L 보통점검","2018-06-01 10:00","2018-06-01 18:00","2018-06-01 10:00","2018-06-01 18:00","당일",null,null,null,201804120353,"-"]
[131,"경기","성남","신성남정자#1 T/L","신성남-정자#1T/L 보통점검, 조작시험","신성남S/S 신성남-정자#1T/L 조작시험 정자S/S 신성남-정자#1T/L 보통점검","2018-06-15 09:00","2018-06-15 18:00","2018-06-15 09:00","2018-06-15 18:00","당일",null,null,null,201804130041,"-"]
[132,"경기","성남","신성남정자#2 T/L","신성남-정자#2T/L 보통점검, 조작시험","신성남S/S 신성남-정자#2T/L 조작시험 정자S/S 신성남-정자#2T/L 보통점검","2018-06-18 09:00","2018-06-18 18:00","2018-06-18 09:00","2018-06-18 18:00","당일",null,null,null,201804120368,"-"]
[133,"경기","성남","신수원북동탄#1 T/L","신수원-북동탄#1T/L 하자점검 및 조작시험","신수원S/S 신수원-북동탄#1T/L 조작시험 북동탄S/S 신수원-북동탄#1T/L 하자점검","2018-06-05 09:00","2018-06-05 18:00","2018-06-05 09:00","2018-06-05 18:00","당일",null,null,null,201804120360,"-"]
[134,"경기","성남","신수원북동탄#2 T/L","신수원-북동탄#2T/L 하자점검 및 조작시험","신수원S/S 신수원-북동탄#2T/L 조작시험 북동탄S/S 신수원-북동탄#2T/L 하자점검","2018-06-12 09:00","2018-06-12 18:00","2018-06-12 09:00","2018-06-12 18:00","당일",null,null,null,201804120361,"-"]
[135,"경기","성남","신용인S/S 154kV #3 BUS-TIE(6300) GIS","신용인S/S 6300 BUS TIE 보통점검","신용인S/S 6300 BUS TIE 보통점검","2018-06-07 09:00","2018-06-07 18:00","2018-06-07 09:00","2018-06-07 18:00","당일",null,null,null,201804120365,"-"]
[136,"경기","성남","신용인S/S 60-61 SEC960-61-0) GIS","신용인S/S 60-61 BUS SEC 정밀점검","신용인S/S 60-61 BUS SEC 정밀점검","2018-06-14 09:00","2018-06-16 18:00","2018-06-14 09:00","2018-06-16 18:00","당일",null,null,null,201804230089,"-"]
[137,"경기","성남","신용인S/S 61-62 SEC(61-62-0) GIS","신용인S/S 61-62, 66-67 보통점검","신용인S/S 61-62, 66-67 보통점검","2018-06-25 09:00","2018-06-25 14:00","2018-06-25 09:00","2018-06-25 14:00","당일",null,null,null,201804120372,"-"]
[138,"경기","성남","신용인S/S 66-67 SEC(66-67-0) GIS","신용인S/S 61-62, 66-67 보통점검","신용인S/S 61-62, 66-67 보통점검","2018-06-25 14:00","2018-06-25 18:00","2018-06-25 14:00","2018-06-25 18:00","당일",null,null,null,201804120373,"-"]
[139,"경기","성남","신갈수원열병합T/L CB","신갈S/S 통열T/L 보통점검","신갈S/S 통열T/L 보통점검","2018-06-21 09:00","2018-06-21 18:00","2018-06-21 09:00","2018-06-21 18:00","당일",null,null,null,201804130056,"-"]
[140,"경기","직할","동수원우만#1 T/L","154kV 동수원S/S 현대화공사","154kV 신설전력구 설치관련 안전이격","2018-06-01 09:00","2018-06-05 18:00","2018-06-01 09:00","2018-06-05 18:00","연속",null,null,null,201804120304,"-"]
[141,"경기","직할","발안향남#1 T/L","154kV 발안-향남T/L No.7-9 전선교체공사","154kV 발안-향남T/L No.7-9 전선교체공사","2018-06-06 07:00","2018-06-07 18:00","2018-06-06 07:00","2018-06-07 18:00","연속",null,null,null,201804100128,"-"]
[142,"경기","직할","발안향남#2 T/L","154kV 발안-향남T/L No.7-9 전선교체공사","154kV 발안-향남T/L No.7-9 전선교체공사","2018-06-10 07:00","2018-06-11 18:00","2018-06-10 07:00","2018-06-11 18:00","연속",null,null,null,201804100129,"-"]
[143,"경기","직할","서서울#2남수원 #1T/L","남수원S/S 154kV 장기사용 GIS 교체공사","남수원S/S 154kV 장기사용 GIS 교체공사(서서울남수원#1T/L,#4M.Tr)","2018-06-18 09:00","2018-07-15 18:00","2018-06-18 09:00","2018-07-15 18:00","연속",null,null,null,201804110296,"-"]
[144,"경기","직할","화성S/S 154kV #62 BUS","18년 직할 154kV GCB/GIS 정밀점검공사","화성S/S #69Sh.C GIS 정밀점검공사(무부하가압)","2018-06-06 09:00","2018-06-06 18:00","2018-06-06 09:00","2018-06-06 18:00","당일",null,null,null,201804110289,"-"]
[145,"경기","직할","화성S/S 154kV #65 BUS","18년 직할 154kV GCB/GIS 정밀점검공사","화성S/S #61Sh.C GIS 정밀점검공사(모선DS작업)","2018-06-01 14:00","2018-06-02 18:00","2018-06-01 14:00","2018-06-02 18:00","연속",null,null,null,201804110286,"-"]
[146,"경기","직할","화성S/S 154kV #67 BUS","18년 직할 154kV GCB/GIS 정밀점검공사","화성S/S #6ASh.C GIS 정밀점검공사(무부하가압)","2018-06-13 09:00","2018-06-14 18:00","2018-06-13 09:00","2018-06-14 18:00","연속",null,null,null,201804110294,"-"]
[147,"경기","직할","화성조암#1 T/L","345kV 아산화성T/L 전력선교체(안전확보)","No.136~138 #1전력선 교체관련 안전거리 확보","2018-06-02 07:00","2018-06-03 18:00","2018-06-02 07:00","2018-06-03 18:00","연속",null,null,null,201803210057,"-"]
[148,"경기","평택","고덕송탄 T/L","지제역세권 개발 관련 지중화 본이설공사","154kV 송탄-오성복합T/L No.18~24 지중화 154kV 송탄-안성T/L No.5 이설","2018-06-14 07:00","2018-06-17 18:00","2018-06-14 07:00","2018-06-17 18:00","연속",null,null,null,201804110074,"-"]
[149,"경기","평택","서운S/S 154kV #1 BUS-TIE(6100) GIS","서운S/S 154kV #1BUS TIE CB 조작시험","서운S/S 154kV #1BUS TIE CB 조작시험","2018-06-04 10:00","2018-06-04 18:00","2018-06-04 10:00","2018-06-04 18:00","당일",null,null,null,201804110325,"○"]
[150,"경기","평택","서운안성#2 T/L","안성S/S 170kV GIS 용량대체공사","서운-안성#2T/L GIS 철거 및 설치","2018-06-15 09:30","2018-07-16 18:00","2018-06-15 09:30","2018-07-16 18:00","연속",null,null,null,201804020093,"○"]
[151,"경기","평택","송탄S/S 154kV #1 BUS TIE(6100) GIS","송탄S/S 154kV #1BUS TIE GIS 하자점검","송탄S/S 154kV #1BUS TIE GIS 하자점검","2018-06-05 10:00","2018-06-05 18:00","2018-06-05 10:00","2018-06-05 18:00","당일",null,null,null,201804110326,"○"]
[152,"경기","평택","송탄소사벌 T/L","지제역세권 개발 관련 지중화 본이설공사","154kV 송탄-오성복합T/L No.18~24 지중화 154kV 송탄-안성T/L No.5 이설","2018-06-09 07:00","2018-06-12 18:00","2018-06-09 07:00","2018-06-12 18:00","연속",null,null,null,201804110072,"○"]
[153,"경기","평택","송탄안성 T/L","지제역세권 개발 관련 지중화 본이설공사","154kV 송탄-오성복합T/L No.18~24 지중화 154kV 송탄-안성T/L No.5 이설","2018-06-06 07:00","2018-06-08 18:00","2018-06-06 07:00","2018-06-08 18:00","연속",null,null,null,201804110071,"○"]
[154,"경기","평택","송탄안성 T/L","지제역세권 개발 관련 지중화 본이설공사","154kV 송탄-오성복합T/L No.18~24 지중화 154kV 송탄-안성T/L No.5 이설","2018-06-14 07:00","2018-06-16 18:00","2018-06-14 07:00","2018-06-16 18:00","연속",null,null,null,201804110076,"○"]
[155,"경기","평택","송탄오성CC T/L","지제역세권 개발 관련 지중화 본이설공사","154kV 송탄-오성복합T/L No.18~24 지중화 154kV 송탄-안성T/L No.5 이설","2018-06-06 07:00","2018-06-13 18:00","2018-06-06 07:00","2018-06-13 18:00","연속",null,null,null,201804110070,"○"]
[156,"경기","평택","송탄진위#1 T/L","154kV 고덕분기 지중T/L 건설공사","ㅇ 공사구간 : 345kV 고덕S/S ~ 154kV 송탄진위T/L 분기점 ㅇ 선종 및 긍장 : 154kV XLPE 2,500SQ,. 4C - 4.0km","2018-06-30 08:00","2018-08-19 18:00","2018-06-30 08:00","2018-08-19 18:00","연속",null,null,null,201804050311,"-"]
[157,"경기","평택","송탄진위#2 T/L","154kV 고덕분기 지중T/L 건설공사","ㅇ 공사구간 : 345kV 고덕S/S ~ 154kV 송탄진위T/L 분기점 ㅇ 선종 및 긍장 : 154kV XLPE 2,500SQ,. 4C - 4.0km","2018-06-18 08:00","2018-08-19 18:00","2018-06-18 08:00","2018-08-19 18:00","연속",null,null,null,201804050310,"-"]
[158,"경기","평택","안성S/S 154kV #61 BUS","안성S/S 170kV GIS 용량대체공사","서운-안성#2T/L, #5M.Tr, #1Sh.C용 GIS 대체 - #1DS, T/L 철거 및 설치","2018-06-17 09:30","2018-06-30 09:30","2018-06-17 09:30","2018-06-30 09:30","연속",null,null,null,201804020107,"-"]
[159,"경기","평택","안성S/S 154kV #66 BUS","안성S/S 170kV GIS 용량대체공사","서운-안성#1T/L GIS 대체 - #2BUS 철거 및 설치 - 준공시험","2018-06-04 09:30","2018-06-15 18:00","2018-06-04 09:30","2018-06-15 18:00","연속",null,null,null,201803090437,"-"]
[160,"경기","평택","안성S/S 154kV #66 BUS","안성S/S 170kV GIS 용량대체공사","서운-안성#2T/L,#5M.Tr, #1Sh.C용 GIS 대체 - #2BUS 철거 및 설치","2018-06-15 09:30","2018-06-17 09:30","2018-06-15 09:30","2018-06-17 09:30","연속",null,null,null,201804020102,"-"]
[161,"경기","평택","안성S/S 154kV #66 BUS","안성S/S 170kV GIS 용량대체공사","서운-안성#2T/L, #5M.Tr, #1ShC용 GIS 대체 - #2BUS 철거 및 설치 - 준공시험","2018-06-30 09:30","2018-07-15 18:00","2018-06-30 09:30","2018-07-15 18:00","연속",null,null,null,201804020108,"-"]
[162,"경기","평택","오산평택#2 T/L","154kV 평택S/S SW증설공사(고덕-평택TL)","○ 154kV 고덕-평택#1,2T/L 무부하가압용","2018-06-04 10:00","2018-06-05 15:00","2018-06-04 10:00","2018-06-05 15:00","연속",null,null,null,201804130057,"-"]
[163,"경기","평택","평택T/P 154kV #1 BUS TIE GIS","평택T/P 154kV #1BUS TIE GIS 보통점검","평택T/P 154kV #1BUS TIE GIS 보통점검","2018-06-26 09:00","2018-06-26 18:00","2018-06-26 09:00","2018-06-26 18:00","당일",null,null,null,201804110341,"-"]
[164,"경기","평택","평택T/P 154kV #2 BUS TIE GIS","평택T/P 154kV #2BUS TIE GIS 보통점검","평택T/P 154kV #2BUS TIE GIS 보통점검","2018-06-27 09:00","2018-06-27 18:00","2018-06-27 09:00","2018-06-27 18:00","당일",null,null,null,201804110342,"-"]
[165,"경기","평택","평택T/P 154kV #61 BUS","18년 평택전력지사 170kV GIS 정밀점검공사","18년 평택전력지사 170kV GIS 정밀점검공사 / 평택T/P 포승-평택T/P #2T/L GIS 정밀점검 무부하가압","2018-06-02 09:00","2018-06-03 18:00","2018-06-02 09:00","2018-06-03 18:00","연속",null,null,null,201804110314,"-"]
[166,"경기","평택","평택T/P 154kV 60-61 BUS SEC GIS","평택T/P 154kV 60-61 SEC GIS 보통점검","평택T/P 154kV 60-61 SEC GIS 보통점검","2018-06-21 09:00","2018-06-21 18:00","2018-06-21 09:00","2018-06-21 18:00","당일",null,null,null,201804110339,"-"]
[167,"경기","평택","평택T/P 154kV 65-66 BUS SEC GIS","평택T/P 154kV 65-66 SEC GIS 보통점검","평택T/P 154kV 65-66 SEC GIS 보통점검","2018-06-22 09:00","2018-06-22 18:00","2018-06-22 09:00","2018-06-22 18:00","당일",null,null,null,201804110340,"-"]
[168,"경기","평택","평택TP평택CC#1T/L","평택T/P 154kV 평택복합 #1T/L GIS 보통점검","평택T/P 154kV 평택복합 #1T/L GIS 보통점검","2018-06-23 09:00","2018-06-23 18:00","2018-06-23 09:00","2018-06-23 18:00","당일",null,null,null,201804110337,"-"]
[169,"경기","평택","평택TP평택CC#2T/L","평택T/P 154kV 평택복합 #2T/L GIS 보통점검","평택T/P 154kV 평택복합 #2T/L GIS 보통점검","2018-06-24 09:00","2018-06-24 18:00","2018-06-24 09:00","2018-06-24 18:00","당일",null,null,null,201804110338,"-"]
[170,"경기","평택","포승평택TP#2 T/L","18년 평택전력지사 170kV GIS 정밀점검공사","18년 평택전력지사 170kV GIS 정밀점검공사 / 평택T/P 포승-평택T/P #2T/L GIS 정밀점검","2018-06-01 09:00","2018-06-03 18:00","2018-06-01 09:00","2018-06-03 18:00","연속",null,null,null,201804110313,"-"]
[171,"강원","강릉","강릉북강릉#2 T/L","154kV 강릉S/S 옥내화 잔여공사","170kV GIS CHC[강릉-북강릉#2T/L) 해체 및 조립 (옥외)강릉S/S -(SA)강릉S/S #2임시모선 인하선 철거 1식","2018-06-13 09:00","2018-07-21 18:00",{"$f":"G175","v":"2018-06-13 09:00"},{"$f":"H175","v":"2018-07-21 18:00"},"연속",null,null,null,201801120351,"-"]
[172,"강원","강릉","강릉북강릉#1 T/L","154kV 강릉S/S 인출 송전선로 지중화공사","- (신설)No.2~강릉S/S간 송전선로 인출구간 지중화","2018-06-09 09:00","2018-06-12 18:00",{"$f":"G176","v":"2018-06-09 09:00"},"2018-06-12 18:00","연속",null,null,null,201803300010,"-"]
[173,"강원","강릉","강릉횡계#2 T/L","154kV 강릉S/S 옥내화 잔여공사","송전선로보호반 대체 x 1식 기타 부대공사","2018-06-14 09:00","2018-07-14 18:00","2018-06-14 09:00","2018-07-14 18:00","연속",null,null,null,201801120356,"-"]
[174,"강원","강릉","속초S/S #1 EM.Tr A CB","속초S/S ESS 정밀점검","ESS 종합정밀점검","2018-06-18 09:00","2018-06-29 18:00","2018-06-18 09:00","2018-06-29 18:00","연속",null,null,null,201804050245,"-"]
[175,"강원","강릉","속초간성#1 T/L","2018~19년 송전정비협력회사 총액공사","○ 전선접속개소 전선교체공사(속초-간성 #1T/L No.15~94 일부구간, 3,420M)","2018-06-04 09:00","2018-06-14 18:00","2018-06-04 09:00","2018-06-14 18:00","연속",null,null,null,201804060058,"-"]
[176,"강원","강릉","속초간성#2 T/L","2018~19년 송전정비협력회사 총액공사","○ 전선접속개소 전선교체공사(속초-간성 #2T/L No.15~94 일부구간, 3,420M)","2018-06-15 09:00","2018-06-24 18:00","2018-06-15 09:00","2018-06-24 18:00","연속",null,null,null,201804060063,"-"]
[177,"강원","원주","홍천소양강HP T/L","2018년 가공송전선로 순시점검 위탁공사 등 2건","정밀점검 및 항공장애표시구 설치","2018-06-07 08:30","2018-06-08 18:00","취소","취소","연속",null,null,"신뢰도개선",201804050138,"-"]
[178,"강원","직할","가평춘천HP T/L","2018~2019년 강원직할 송전정비회사 총액공사","항공장애표시구 설치 4경간 12개","2018-06-14 08:30","2018-06-14 18:00",{"$f":"G182","v":"2018-06-14 08:30"},"2018-06-14 18:00","당일",null,null,null,201804050136,"-"]
[179,"강원","직할","남춘천춘천 T/L","2018년 가공송전선로 순시점검 위탁공사","정밀점검","2018-06-11 08:30","2018-06-12 18:00","2018-06-11 08:30","2018-06-12 18:00","매일",null,null,null,201804050141,"-"]
[180,"강원","직할","상남인제#1 T/L","2018년 가공송전선로 순시점검 위탁공사","정밀점검","2018-06-18 08:30","2018-06-20 18:00","2018-06-18 08:30","2018-06-20 18:00","매일",null,null,null,201804050145,"-"]
[181,"강원","직할","상남인제#2 T/L","2018년 가공송전선로 순시점검 위탁공사","정밀점검","2018-06-25 08:30","2018-06-27 18:00","2018-06-25 08:30","2018-06-27 18:00","매일",null,null,null,201804050147,"-"]
[182,"강원","직할","운천철원#1 T/L","'18-'19 강원본부 직할 변전정비 총액공사","○ 154kV 철원S/S 운천-철원 #1 T/L GIS 하자점검 - 차단기 개폐타임 측정, 가스 수분측정 등 - 보호배전반 PNL 초기점검","2018-06-27 10:00","2018-06-27 14:00","2018-06-27 10:00","2018-06-27 14:00","당일",null,null,null,201804180121,"-"]
[183,"강원","직할","운천철원#2 T/L","'18-'19 강원본부 직할 변전정비 총액공사","○ 154kV 철원S/S 운천-철원 #2 T/L GIS 하자점검 - 차단기 개폐타임 측정, 가스 수분측정 등 - 보호배전반 PNL 초기점검","2018-06-27 14:00","2018-06-27 18:00","2018-06-27 14:00","2018-06-27 18:00","당일",null,null,null,201804180123,"-"]
[184,"강원","직할","철원화천#1 T/L","'18-'19 강원본부 직할 변전정비 총액공사","○ 154kV 철원S/S 철원-화천 #1 T/L GIS 하자점검 - 차단기 개폐타임 측정, 가스 수분측정 등 - 보호배전반 PNL 초기점검","2018-06-07 07:30","2018-06-07 18:00","2018-06-07 07:30","2018-06-07 18:00","당일",null,null,null,201804180124,"-"]
[185,"강원","직할","철원화천#2 T/L","'18-'19 강원본부 직할 변전정비 총액공사","○ 154kV 철원S/S 철원-화천 #2 T/L GIS 하자점검 - 차단기 개폐타임 측정, 가스 수분측정 등 - 보호배전반 PNL 초기점검","2018-06-08 07:30","2018-06-08 18:00","2018-06-08 07:30","2018-06-08 18:00","당일",null,null,null,201804180125,"-"]
[186,"강원","직할","청평HP의암HP T/L","2018~2019년 강원직할 송전정비회사 총액공사","항공장애표시구 설치 12경간 36개","2018-06-04 08:30","2018-06-05 18:00","2018-06-04 08:30","2018-06-05 18:00","연속",null,null,null,201804050135,"-"]
[188,"강원","태백","도계태백 T/L","태백전력지사 변전정비회사 총액공사","차단기 조작시험","2018-06-19 10:00","2018-06-19 14:00","2018-06-19 10:00","2018-06-19 14:00","당일",null,null,null,201804060087,"-"]
[189,"강원","태백","동영월영월CC T/L","태백전력지사 170 GIS 정밀점검","동영월S/S 동영월-영월CC T/L GIS 정밀점검","2018-06-04 10:00","2018-06-06 14:00","2018-06-04 10:00","2018-06-06 14:00","연속",null,null,null,201804060064,"-"]
[190,"강원","태백","동해동영월 T/L","태백전력지사 170kV GIS 정밀점검","동영월S/S 동해-동영월 T/L GIS 정밀점검","2018-06-18 10:00","2018-06-20 14:00","2018-06-18 10:00","2018-06-20 14:00","연속",null,null,null,201804060206,"-"]
[192,"충북","직할","감곡여주#1 T/L","감곡S/S 154kV 감곡-여주#1T/L LA 초기점검","감곡S/S 154kV 감곡-여주#1T/L LA 초기점검","2018-06-08 10:10","2018-06-08 13:00","2018-06-08 10:10","2018-06-08 13:00","당일",null,null,null,201804040160,"-"]
[193,"충북","직할","단양영월CC#2 T/L","단양S/S 154kV 단양-영월CC #2T/L PT 보통점검","단양S/S 154kV 단양-영월CC #2T/L PT 보통점검","2018-06-14 10:00","2018-06-14 18:00","2018-06-14 10:00","2018-06-14 18:00","당일",null,null,null,201804040162,"-"]
[194,"충북","직할","신제천남원주#2 T/L","신제천S/S 신제천-남원주#2T/L GIS 초기점검","-170kV GIS 초기점검","2018-06-04 13:00","2018-06-04 18:00","2018-06-04 13:00","2018-06-04 18:00","당일",null,null,null,201804040167,"-"]
[195,"충북","직할","신제천영월CC#2 T/L","신제천S/S 신제천-영월CC#2T/L GIS 초기점검","170kV GIS 초기점검","2018-06-04 09:00","2018-06-04 13:00","2018-06-04 09:00","2018-06-04 13:00","당일",null,null,null,201804040163,"-"]
[196,"충북","직할","신제천주진#1 T/L","345kV 신제천-신영주T/L 접속개소 전선교체공사","345kV 신제천-신영주 선로횡단개소 안전확보를 위해 154kV 신제천-주진T/L 선로 휴전","2018-06-03 10:00","2018-06-03 18:00","2018-06-03 10:00","2018-06-03 18:00","당일",null,null,null,201804120175,"-"]
[197,"충북","직할","신충주감곡#2 T/L","감곡S/S 154kV 신충주-감곡#2T/L LA 초기점검","감곡S/S 154kV 신충주-감곡#2T/L LA 초기점검","2018-06-08 13:00","2018-06-08 18:00",{"$f":"G199","v":"2018-06-08 13:00"},"2018-06-08 18:00","당일",null,null,null,201804040161,"-"]
[198,"충북","직할","음성금왕#2 T/L","음성S/S 음성-금왕#2T/L LA 대체","음성S/S 음성-금왕#2T/L LA 대체","2018-06-07 10:00","2018-06-07 18:00","2018-06-07 10:00","2018-06-07 18:00","당일",null,null,null,201803200015,"○"]
[199,"충북","직할","점촌단양 T/L","단양S/S 점촌-단양T/L PT대체","단양S/S 점촌-단양T/L PT대체","2018-06-01 10:00","2018-06-01 18:00","2018-06-01 10:00","2018-06-01 18:00","당일",null,null,null,201803150031,"-"]
[200,"충북","청주","부강대청HP T/L","2018년 청주전력지사 170kV GIS 정밀점검공사","부강-대청HP T/L GIS 정밀점검","2018-06-14 08:30","2018-06-15 18:00","2018-06-14 08:30","2018-06-15 18:00","연속",null,null,null,201804130130,"○"]
[201,"충북","청주","사직북청주#1 T/L","2018년 청주전력지사 170kV GIS 정밀점검공사","사직-북청주#1T/L GIS 정밀점검","2018-06-18 08:30","2018-06-19 18:00","2018-06-18 08:30","2018-06-19 18:00","연속",null,null,null,201804130132,"-"]
[202,"충북","청주","서청주사직#2 T/L","2018년 청주전력지사 170kV GIS 정밀점검공사","서청주-사직#2T/L GIS 정밀점검","2018-06-16 08:30","2018-06-17 18:00","2018-06-16 08:30","2018-06-17 18:00","연속",null,null,null,201804130131,"-"]
[203,"충북","청주","신진천오창#1 T/L","2018년 청주전력지사 170kV GIS 정밀점검공사","신진천오창#1T/L GIS 정밀점검","2018-06-09 08:30","2018-06-10 18:00",{"$f":"G205","v":"2018-06-09 08:30"},{"$f":"H205","v":"2018-06-10 18:00"},"연속",null,null,null,201804130104,"-"]
[204,"충북","청주","오송북청주#2 T/L","154kV 국사-봉명T/L 지장철탑이설공사","1. 사유 : 청주테크노폴리스 산업단지 조성에 따른 철탑 이설 2. 공사개요 ○ 이설구간 : 154kV 국사­봉명T/L 14~17, 20~23호간 (준공 1994년) ○ 이설개요 : : 4회선 철탑 4기(15,16,21,22), 전력선 4.072C-km 교체 3. 작업내용 : 철탑설치 및 가선","2018-06-01 08:00","2018-06-04 18:00",{"$f":"G206","v":"2018-06-01 08:00"},{"$f":"H206","v":"2018-06-04 18:00"},"연속",null,null,null,201803090088,"-"]
[205,"충북","청주","죽림청주열병합 T/L CB","2018년 청주전력지사 170kV GIS 정밀점검공사","청주난방T/L GIS 정밀점검","2018-06-22 08:30","2018-06-23 18:00",{"$f":"G207","v":"2018-06-22 08:30"},"2018-06-23 18:00","연속",null,null,null,201804130134,"-"]
[206,"충북","충주","신진천S/S 154kV #61 BUS","2018년 충주전력지사 154kV GIS 정밀점검","2018년 충주전력지사 154kV GIS 정밀점검","2018-06-26 10:00","2018-06-26 18:00","2018-06-26 10:00","2018-06-26 18:00","연속",null,null,null,201803260288,"-"]
[207,"충북","충주","신진천S/S 60-61 SEC GIS","2018년도 154kV GIS 정밀점검","2018년도 154kV GIS 정밀점검","2018-06-25 10:00","2018-06-26 18:00","2018-06-25 10:00","2018-06-26 18:00","연속",null,null,null,201803070371,"-"]
[208,"충북","충주","신진천S/S 신진천-오창#2T/L GIS","2018년도 154kV GIS 정밀점검 및 보호반 대체","2018년도 154kV GIS 정밀점검 및 보호반 대체","2018-06-22 10:00","2018-06-26 18:00","2018-06-22 10:00","2018-06-26 18:00","연속",null,null,null,201803070369,"-"]
[206,"충북","충주","신진천S/S 154kV #61 BUS","2018년 충주전력지사 154kV GIS 정밀점검","2018년 충주전력지사 154kV GIS 정밀점검","2018-06-26 10:00","2018-06-26 18:00","2018-06-26 10:00","2018-06-26 18:00","연속",null,null,null,201803260288,"-"]
[207,"충북","충주","신진천S/S 60-61 SEC GIS","2018년도 154kV GIS 정밀점검","2018년도 154kV GIS 정밀점검","2018-06-25 10:00","2018-06-26 18:00","2018-06-25 10:00","2018-06-26 18:00","연속",null,null,null,201803070371,"-"]
[208,"충북","충주","신진천S/S 신진천-오창#2T/L GIS","2018년도 154kV GIS 정밀점검 및 보호반 대체","2018년도 154kV GIS 정밀점검 및 보호반 대체","2018-06-22 10:00","2018-06-26 18:00","2018-06-22 10:00","2018-06-26 18:00","연속",null,null,null,201803070369,"-"]
[209,"대전충남","대전","신계룡S/S #1EM.Tr A CB","신계룡S/S ESS PCS, BAT 정밀점검 및 병행작업","신계룡S/S ESS PCS, BAT 정밀점검, #1EM.Tr 하자점검 및 병행작업","2018-06-18 09:00","2018-06-29 18:00","2018-06-18 09:00","2018-06-29 18:00","연속",null,null,null,201804090623,"-"]
[210,"대전충남","대전","신계룡가수원#1 T/L","신계룡S/S 154kV 신계룡-가수원#1T/L GIS 보통점검 및 병행","신계룡S/S 154kV 신계룡-가수원#1T/L GIS 보통점검 및 병행작업","2018-06-15 09:00","2018-06-15 18:00","2018-06-15 09:00","2018-06-15 18:00","당일",null,null,null,201804090617,"-"]
[211,"대전충남","대전","신옥천남대전#1 T/L","남대전S/S 154kV 신옥천-남대전#1T/L GIS 정밀점검","남대전S/S 154kV 신옥천-남대전#1T/L GIS 정밀점검","2018-06-11 09:00","2018-06-12 18:00","2018-06-11 09:00","2018-06-12 18:00","연속",null,null,null,201804090587,"-"]
[212,"대전충남","대전","신옥천남대전#2 T/L","남대전S/S 154kV 신옥천-남대전#2T/L GIS 정밀점검","남대전S/S 154kV 신옥천-남대전#2T/L GIS 정밀점검","2018-06-14 09:00","2018-06-15 18:00","2018-06-14 09:00","2018-06-15 18:00","연속",null,null,null,201804090590,"-"]
[213,"대전충남","서산","당진송악#1 T/L","18년 서산PO 변전정비회사 총액공사","송악S/S 당진-송악#1T/L GIS 보통점검","2018-06-16 09:00","2018-06-16 18:00","2018-06-16 09:00","2018-06-16 18:00","당일",null,null,null,201804160275,"-"]
[214,"대전충남","서산","당진송악#2 T/L","18년 서산PO 변전정비회사 총액공사","송악S/S 당진-송악#2T/L GIS 보통점검","2018-06-17 09:00","2018-06-17 18:00","2018-06-17 09:00","2018-06-17 18:00","당일",null,null,null,201804160276,"-"]
[215,"대전충남","서산","서산태안 T/L","154kV 대산T/L 전력선 교체공사","154Kv 대산T/L 7~8,9~10","2018-06-18 07:00","2018-06-20 18:00","2018-06-18 07:00","2018-06-20 18:00","연속",null,null,null,201804230006,"-"]
[216,"대전충남","서산","서산태안화력 T/L","154kV 대산T/L 전력선 교체공사","154Kv 대산T/L 7~8,9~10","2018-06-21 07:00","2018-06-23 18:00","2018-06-21 07:00","2018-06-23 18:00","연속",null,null,null,201804230001,"-"]
[217,"대전충남","서산","신당진당진#1 T/L","18년 서산PO 변전정비회사 총액공사","당진S/S 154kV 신당진-당진#1T/L GCB 보통점검 신당진S/S 154kV 신당진-당진#1T/L GIS 보통점검","2018-06-02 09:00","2018-06-02 18:00","2018-06-02 09:00","2018-06-02 18:00","당일",null,null,null,201804160264,"-"]
[218,"대전충남","서산","태안T/P 154kV #1 BUS","태안화력 154kV 장기사용 GIS 대체공사","태안화력 154kV 장기사용 GIS(6383) 대체공사","2018-06-04 09:00","2018-06-06 15:00","2018-06-04 09:00","2018-06-06 15:00","연속",null,null,null,201804160258,"-"]
[219,"대전충남","서산","태안T/P 154kV #1 BUS","태안화력 154kV 장기사용 GIS 대체공사","태안화력 154kV 장기사용 GIS(6383) 대체공사","2018-06-15 15:00","2018-06-22 18:00","2018-06-15 15:00","2018-06-22 18:00","연속",null,null,null,201804160260,"-"]
[220,"대전충남","서산","태안T/P 154kV #1 BUS","태안화력 154kV 장기사용 GIS 대체공사","태안화력 154kV 장기사용 GIS(6483) 대체공사","2018-06-25 09:00","2018-06-27 15:00","2018-06-25 09:00","2018-06-27 15:00","연속",null,null,null,201804160261,"-"]
[221,"대전충남","서산","태안T/P 154kV #2 BUS","태안화력 154kV 장기사용 GIS 대체공사","태안화력 154kV 장기사용 GIS(6383) 대체공사","2018-06-06 15:00","2018-06-15 15:00","2018-06-06 15:00","2018-06-15 15:00","연속",null,null,null,201804160259,"-"]
[222,"대전충남","서산","태안T/P 154kV #2 BUS","태안화력 154kV 장기사용 GIS 대체공사","태안화력 154kV 장기사용 GIS(6483) 대체공사","2018-06-27 15:00","2018-07-06 15:00","2018-06-27 15:00","2018-07-06 15:00","연속",null,null,null,201804160262,"-"]
[223,"대전충남","세종","천안전의#1 T/L","[송전] 154kV 천안-전의T/L 지장송전선로 이설공사","- 154kV 천안-전의T/L No.5~7 지장송전선로 이설공사","2018-06-22 08:00","2018-06-25 18:00","2018-06-22 08:00","2018-06-25 18:00","연속",null,null,null,201804110206,"-"]
[224,"대전충남","세종","천안전의#2 T/L","[송전] 154kV 천안-전의T/L 지장송전선로 이설공사","- 154kV 천안-전의T/L No.5~7 지장송전선로 이설공사","2018-06-26 08:00","2018-06-29 18:00","2018-06-26 08:00","2018-06-29 18:00","연속",null,null,null,201804110207,"-"]
[225,"대전충남","아산","신온양석곡#1 T/L","신온양,석곡S/S 154kV 신온양-석곡#1T/L CB 개폐타임 측정","○신온양,석곡S/S 154kV 신온양-석곡#1T/L CB 개폐타임 측정 ○병행) 신온양,석곡S/S 보호계전기 성능개선","2018-06-18 09:00","2018-06-18 18:00","2018-06-18 09:00","2018-06-18 18:00","당일",null,null,null,201804120342,"-"]
[226,"대전충남","아산","신온양석곡#2 T/L","[송전]154kV 신온양-석곡등 10개T/L 피뢰기 설치공사","154kV 신온양-석곡#2T/L","2018-06-10 07:00","2018-06-15 18:00","2018-06-10 07:00","2018-06-15 18:00","매일",null,null,null,201804120271,"-"]
[227,"대전충남","아산","신온양한샘#2 T/L","154kV 신온양-한샘T/L 건설공사","2회선 가수전을 위한 전선 탑상이설","2018-06-19 08:00","2018-06-20 19:00","2018-06-19 08:00","2018-06-20 19:00","당일",null,null,null,201804300207,"-"]
[228,"대전충남","아산","신온양한샘#1 T/L","154kV 신온양-한샘T/L 건설공사","2회선 가수전을 위한 전선 탑상이설","2018-06-21 08:00","2018-06-22 19:00","2018-06-21 08:00","2018-06-22 19:00","매일",null,null,null,201804300208,"-"]
[229,"대전충남","아산","아산S/S 154kV #60 BUS","아산S/S 170kV 장기사용 GIS 교체공사","아산S/S 170kV 장기사용 GIS 교체공사","2018-06-11 09:00","2018-06-14 18:00","2018-06-11 09:00","2018-06-14 18:00","연속",null,null,null,201804190217,"-"]
[230,"대전충남","아산","아산S/S 154kV #60 BUS","아산S/S 170kV 장기사용 GIS 교체공사","아산S/S 170kV 장기사용 GIS 교체공사","2018-06-20 09:00","2018-06-26 18:00","2018-06-20 09:00","2018-06-26 18:00","연속",null,null,null,201804190219,"-"]
[231,"대전충남","아산","아산S/S 154kV #65 BUS","아산S/S 170kV 장기사용 GIS 교체공사","아산S/S 170kV 장기사용 GIS 교체공사","2018-06-15 09:00","2018-06-19 18:00","2018-06-15 09:00","2018-06-19 18:00","연속",null,null,null,201804190218,"-"]
[232,"대전충남","청양","대천서천화력#1 T/L","154kV 옥산-서천화력T/L 전선교체공사(안격이격거리확보)","가. 전력선 교체 : 22개 구간 28.405 [c-km] (ACSR 410㎟ × 2B) 나. 현수애자련 교체 : 6기 36 [련] 다. 스페이서 교체 : 2,176 [개] 라.상간스페이서 철거,설치 : 49 [개] 마. 피뢰기 철거 설치 : 6기 18[조] 바. 기타부대공사 1식","2018-06-08 07:00","2018-06-22 18:00","2018-06-08 07:00","2018-06-22 18:00","연속",null,null,null,201804170455,"-"]
[233,"대전충남","청양","대천서천화력#2 T/L","154kV 옥산-서천화력T/L 전선교체공사(안격이격거리확보)","가. 전력선 교체 : 22개 구간 28.405 [c-km] (ACSR 410㎟ × 2B) 나. 현수애자련 교체 : 6기 36 [련] 다. 스페이서 교체 : 2,176 [개] 라.상간스페이서 철거,설치 : 49 [개] 마. 피뢰기 철거 설치 : 6기 18[조] 바. 기타부대공사 1식","2018-06-01 07:00","2018-06-12 18:00","2018-06-01 07:00","2018-06-12 18:00","연속",null,null,null,201804170453,"-"]
[234,"대전충남","청양","옥산서천화력#1 T/L","154kV 옥산-서천화력T/L 전선교체공사","가. 전력선 교체 : 22개 구간 28.405 [c-km] (ACSR 410㎟ × 2B) 나. 현수애자련 교체 : 6기 36 [련] 다. 스페이서 교체 : 2,176 [개] 라.상간스페이서 철거,설치 : 49 [개] 마. 피뢰기 철거 설치 : 6기 18[조] 바. 기타부대공사 1식","2018-06-08 07:00","2018-07-07 18:00","2018-06-08 07:00","2018-07-07 18:00","연속",null,null,null,201804170448,"-"]
[235,"전북","군산","군공군산복합#2 T/L","군공-군산복합#2T/L 보호배전반 대체공사","군공-군산복합#2T/L 보호배전반 대체공사","2018-06-19 09:00","2018-06-25 18:00","2018-06-19 09:00","2018-06-25 18:00","연속",null,null,null,201804190162,"-"]
[236,"전북","군산","군공소룡#2 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","소룡S/S 군공-소룡 #2T/L 차단기 정밀점검","2018-06-01 09:00","2018-06-02 18:00","2018-06-01 09:00","2018-06-02 18:00","연속",null,null,null,201803200080,"-"]
[237,"전북","군산","군산동군산#1 T/L","항공장애표시구 설치공사","항공자애표시구 설치","2018-06-27 07:00","2018-06-27 18:00","2018-06-27 07:00","2018-06-27 18:00","당일",null,null,null,201804180136,"-"]
[238,"전북","군산","은진함열#2 T/L","함열S/S 170kV 장기사용 GIS 대체공사 (3차)","- 은진-함열T/L 등 170kV GIS 8CCT 대체 - 기초보강 및 기타부대공사 1식","2018-06-14 09:00","2018-07-17 18:00","2018-06-14 09:00","2018-07-17 18:00","연속",null,null,null,201804150009,"-"]
[239,"전북","군산","군산영등#2 T/L","항공장애표시구 설치공사","항공장애표시구 설치공사","2018-06-26 07:00","2018-06-27 18:00","2018-06-26 07:00","2018-06-27 18:00","매일",null,null,null,201804300007,"-"]
[240,"전북","군산","군산이리#2 T/L","항공장애표시구 설치공사","항공장애표시구 설치공사","2018-06-26 07:00","2018-06-27 18:00","2018-06-26 07:00","2018-06-27 18:00","매일",null,null,null,201804300008,"-"]
[241,"전북","군산","군공군산복합#1 T/L","군공-군산복합#1T/L 보호배전반 대체공사","군공-군산복합#1T/L 보호배전반 대체공사","2018-06-14 09:00","2018-06-18 18:00","2018-06-14 09:00","2018-06-18 18:00","연속",{"$nulls":4},"-"]
[242,"전북","김제","고창영광 T/L","345kV 신남원-한빛#1T/L 전선접속개소 해소공사","345kV 신남원-한빛#1T/L 전선접속개소 해소공사 4회선구간 안전이격확보","2018-06-04 09:00","2018-06-12 18:00","취소","취소","매일",null,null,null,201804170223,"-"]
[243,"전북","김제","고창홍농 T/L","김제P/O 차단기 정밀점검공사","고창-홍농T/L 차단기 정밀점검","2018-06-14 09:00","2018-06-15 18:00","2018-06-14 09:00","2018-06-15 18:00","연속",null,null,null,201804120120,"-"]
[244,"전북","김제","신김제S/S 154kV #3 BUS TIE CB","신김제S/S #62-67 모선보호반 교체공사","신김제S/S #62-67 모선보호반 교체공사","2018-06-04 09:00","2018-06-07 18:00","취소","취소","당일",null,null,null,201804100070,"-"]
[245,"전북","김제","신김제S/S 61-62-0 SEC CB","신김제S/S #62-67 모선보호반 교체공사","신김제S/S #62-67 모선보호반 교체공사","2018-06-04 09:00","2018-06-07 18:00","취소","취소","연속",null,null,null,201804100067,"-"]
[246,"전북","김제","신김제S/S 66-67-0 SEC CB","신김제S/S #62-67 모선보호반 교체공사","신김제S/S #62-67 모선보호반 교체공사","2018-06-04 09:00","2018-06-07 18:00","취소","취소","연속",null,null,null,201804100068,"-"]
[247,"전북","김제","신김제정공#2 T/L","김제PO 154kV GIS 정밀점검","정공S/S 6100 시험가압","2018-06-02 09:00","2018-06-02 18:00","2018-06-02 09:00","2018-06-02 18:00","연속",null,null,null,201803130010,"-"]
[248,"전북","김제","신김제남전주#2 T/L","차단기 조작시험","차단기 조작시험","2018-06-19 09:00","2018-06-19 18:00","취소","취소","당일",null,null,null,201802120039,"-"]
[249,"전북","김제","정주고창#1 T/L","김제p/o 170kv GIS정밀점검공사","고창S/S BUS TIE CB 정밀점검 시험가압","2018-06-12 16:00","2018-06-12 18:00","취소","취소","당일",null,null,null,201804160194,"-"]
[250,"전북","직할","곡성남원#2 T/L","154kV 신남원-남원T/L 건설공사","(휴전)154kV 남원-임실, 곡성-남원 병가선로 이설 관련사업 : 154kV 신남원-남원T/L 건설공사 1.구 간 : 기설 345kV 신남원S/S ~ 기설 154kV 남원S/S 2. 전 력 선 : ACSR 410㎟ × 2B 3. 규 모 : 11.81㎞ / 철탑 : 31기","2018-06-04 08:00","2018-06-12 18:00","2018-06-04 08:00","2018-06-12 18:00","연속",null,null,null,201803150024,"-"]
[251,"전북","직할","북전주봉동#1 T/L","2018년 전북직할 154kV 차단기 정밀점검공사","- 차단부 정밀점검","2018-06-18 09:30","2018-06-19 17:30","취소","취소","연속",null,null,null,201803070085,"-"]
[252,"전북","직할","북전주봉동#2 T/L","2018년 전북직할 154kV 차단기 정밀점검공사","- 차단부 정밀점검","2018-06-20 09:30","2018-06-21 17:30","취소","취소","연속",null,null,null,201803070087,"-"]
[253,"전북","직할","신김제동전주#1 T/L","2018년 전북직할 154kV 차단기 정밀점검공사","- 차단부 정밀점검","2018-06-04 09:30","2018-06-06 17:30","2018-06-04 09:30","2018-06-06 17:30","연속",null,null,null,201803070053,"-"]
[254,"전북","직할","신김제동전주#2 T/L","345kV 신남원-의령 등 5개T/L 항공장애 표시구 설치공사","- 345kV 신남원-의령T/L : 92개 - 345kV 신옥천-신남원T/L : 146개 - 154kV 신김제-동전주T/L : 56개 - 154kV 동전주-북전주T/L : 29개 - 154kV 진안-장수T/L : 96개","2018-06-07 07:00","2018-06-08 18:00","2018-06-07 07:00","2018-06-08 18:00","매일",null,null,null,201804180117,"-"]
[255,"전북","직할","팔봉봉동#1 T/L","2018년 전북직할 154kV 차단기 정밀점검공사","- 차단부 정밀점검","2018-06-15 14:00","2018-06-15 16:00","취소","취소","연속",null,null,null,201803070078,"-"]
[256,"전북","직할","팔봉봉동#1 T/L","2018년 전북직할 154kV 차단기 정밀점검공사","- 차단부 정밀점검","2018-06-25 09:30","2018-06-26 17:30","취소","취소","연속",null,null,null,201803070091,"-"]
[257,"전북","직할","팔봉봉동#2 T/L","2018년 전북직할 154kV 차단기 정밀점검공사","- 차단부 정밀점검","2018-06-27 09:30","2018-06-28 17:30","취소","취소","연속",null,null,null,201803070094,"-"]
[258,"광주전남","강진","강진남창#1 T/L","남창S/S 강진-남창 #1T/L (DS 결상보수)","2018~19년 강진전력지사 변전협력회사 총액공사 - 내용 : DS 결상보수, 선로측 P.G 클램프 교체 (강진측 작업 병행)","2018-06-10 09:00","2018-06-10 18:00","2018-06-10 09:00","2018-06-10 18:00","당일",null,null,null,201803300090,"-"]
[259,"광주전남","강진","강진남창#2 T/L","남창S/S 강진-남창 #2T/L (클램프 교체)","2018~19년 강진전력지사 변전협력회사 총액공사 - 내용 : 선로측 P.G 클램프 교체","2018-06-17 09:00","2018-06-17 18:00","2018-06-17 09:00","2018-06-17 18:00","당일",null,null,null,201803300091,"-"]
[260,"광주전남","강진","남창해남CS#2 T/L","154kV 해남C/S #4M.Tr 증설공사","○ #4M.Tr 변압기 증설관련 무부하 가압","2018-06-01 10:00","2018-06-02 12:00","2018-06-01 10:00","2018-06-02 12:00","연속",null,null,null,201804110073,"-"]
[261,"광주전남","강진","신강진대불#1 T/L","154kV 대불-남악 등 2개T/L 지장송전선로 이설공사","보성~임성리간 철도 신설에 따른 154kV 신강진-대불T/L 지장이설 - (No. 61호) 철탑1기 신설","2018-06-18 07:00","2018-06-22 18:00","2018-06-23 07:00","2018-06-23 18:00","연속",null,null,null,201804260023,"-"]
[262,"광주전남","강진","신강진대불#2 T/L","154kV 대불-남악 등 2개T/L 지장송전선로 이설공사","보성~임성리간 철도 신설에 따른 154kV 신강진-대불T/L 지장이설 - (No. 61호) 철탑1기 신설","2018-06-23 07:00","2018-06-27 18:00","2018-06-18 07:00","2018-06-22 18:00","연속",null,null,null,201804260024,"-"]
[263,"광주전남","강진","해남C/S #1 C.Tr 1차 CB","154kV 해남C/S #4M.Tr 증설공사","○ #4M.Tr 변압기 증설관련 무부하 가압","2018-06-01 10:00","2018-06-01 12:00","2018-06-01 10:00","2018-06-01 12:00","당일",null,null,null,201804110001,"-"]
[264,"광주전남","강진","해남C/S #2 C.Tr 1차 CB","154kV 해남C/S #4M.Tr 증설공사","○ #4M.Tr 변압기 증설관련 무부하 가압","2018-06-01 10:00","2018-06-01 12:00","2018-06-01 10:00","2018-06-01 12:00","당일",null,null,null,201804110004,"-"]
[265,"광주전남","강진","해남C/S 154kV #1 BUS","154kV 해남C/S #4M.Tr 증설공사","○ #4M.Tr 변압기 증설관련 무부하 가압","2018-06-01 10:00","2018-06-01 12:00","2018-06-01 10:00","2018-06-01 12:00","연속",null,null,null,201804110067,"-"]
[266,"광주전남","강진","해남C/S 154kV #2 BUS","154kV 해남C/S #4M.Tr 증설공사","○ #4M.Tr 변압기 증설관련 무부하 가압","2018-06-01 12:00","2018-06-02 12:00","2018-06-01 12:00","2018-06-02 12:00","연속",null,null,null,201804110075,"-"]
[267,"광주전남","강진","화원진도#2 T/L","154kV 화원-진도 등 3개T/L 피뢰기 설치공사","154kV 화원-진도#2T/L 피뢰기 설치공사 ○ 송전용 피뢰기 설치 : 39기, 117set","2018-06-20 08:00","2018-06-22 18:00","2018-06-20 08:00","2018-06-22 18:00","연속",null,null,null,201804090186,"-"]
[268,"광주전남","광주","신광주장성#2 T/L","18년 광주변전 총액공사(신광주-장성#2)","신광주S/S 신광주-장성#2 GIS 초기점검","2018-06-04 09:00","2018-06-04 18:00","2018-06-04 09:00","2018-06-04 18:00","당일",null,null,null,201804130024,"-"]
[269,"광주전남","광주","신화순평동 T/L","18년 광주전력지사 변전협력회사 총액공사(신화순나주#1T/L)","154kV LA 교체, 장기미동작 CB 점검","2018-06-12 09:00","2018-06-12 18:00","2018-06-12 09:00","2018-06-12 18:00","당일",null,null,null,201804030165,"-"]
[270,"광주전남","목포","나주엄다#1 T/L","154kV나주-엄다T/L 안전이격확보공사","보조암설치 2기","2018-06-01 06:30","2018-06-01 12:30","2018-06-01 06:30","2018-06-01 12:30","당일",null,null,null,201804040100,"-"]
[271,"광주전남","목포","나주엄다#1 T/L","154kV나주-엄다T/L 안전이격확보공사","○철탑조립 및 철거 : 4기(No.59,60,63,64) ○전력선 공중이동 및 긴선","2018-06-02 09:00","2018-06-05 18:00","2018-06-02 09:00","2018-06-05 18:00","매일",null,null,null,201804040106,"-"]
[272,"광주전남","목포","나주엄다#2 T/L","154kV나주-엄다T/L 안전이격확보공사","○철탑조립 및 철거 : 4기(No.59,60,63,64) ○전력선 공중이동 및 긴선","2018-06-01 12:30","2018-06-01 18:30","2018-06-01 12:30","2018-06-01 18:30","매일",null,null,null,201804040104,"-"]
[273,"광주전남","목포","나주엄다#2 T/L","154kV나주-엄다T/L 안전이격확보공사","보조암설치 2기","2018-06-06 09:00","2018-06-09 18:00","2018-06-06 09:00","2018-06-09 18:00","당일",null,null,null,201804230081,"-"]
[274,"광주전남","순천","순천승주#1 T/L","154kV 순천-승주 등 2개T/L OPGW용 항공구 시설공사","154kV 순천-승주T/L No.150-151, 159-160호 OPGW용 항공구 26식 설치","2018-06-25 07:00","2018-06-26 18:00","취소","취소","연속",null,null,null,201804090578,"-"]
[275,"광주전남","순천","순천율촌#1 T/L","154kV 순천-율촌T/L C/H철탑 설치공사","가. 공사구간 : 154kV 순천-율촌T/L No.68 ∼ 72호(C/H)간 나. 작업내용 ○ 지지물 : 본선로 CH2-20 1기(관형지지물), 가철탑 1기(Bbus2-30) ○ 전력선 : ACSR 520㎟ × S, L = 0.113km(68호∼69호간)","2018-06-15 08:00","2018-06-16 18:00","취소","취소","연속",null,null,null,201804020201,"-"]
[276,"광주전남","순천","순천율촌#2 T/L","154kV 순천-율촌T/L C/H철탑 설치공사","가. 공사구간 : 154kV 순천-율촌T/L No.68 ∼ 72호(C/H)간 나. 작업내용 ○ 지지물 : 본선로 CH2-20 1기(관형지지물), 가철탑 1기(Bbus2-30) ○ 전력선 : ACSR 520㎟ × S, L = 0.113km(68호∼69호간)","2018-06-17 08:00","2018-06-18 18:00","취소","취소","연속",null,null,null,201804020202,"-"]
[277,"광주전남","순천","승주서순천 T/L","154kV 순천-승주 등 2개 T/L OPGW용 항공구 시설공사","154kV 승주-서순천T/L No.47-48, 50-52, 83-86호 OPGW용 항공구 38식 설치","2018-06-27 07:00","2018-06-28 18:00","취소","취소","연속",null,null,null,201804090580,"-"]
[278,"광주전남","순천","여수TP여천#1 T/L","장기 미동작 차단기 시험","여수TP-여천#1/L 장기 미동작 차단기 시험","2018-06-07 10:00","2018-06-07 13:00","2018-06-07 10:00","2018-06-07 13:00","당일",null,null,null,201803120275,"-"]
[279,"광주전남","순천","여수TP여천#2 T/L","장기 미동작 차단기 시험","여수TP-여천#2L 장기 미동작 차단기 시험","2018-06-07 13:00","2018-06-07 15:00","2018-06-07 13:00","2018-06-07 15:00","당일",null,null,null,201803120276,"-"]
[280,"광주전남","순천","여수TP용성#1 T/L","장기 미동작 차단기 시험","여수TP-용성#1/L 장기 미동작 차단기 시험","2018-06-14 10:00","2018-06-14 13:00","취소","취소","당일",null,null,null,201803120287,"-"]
[281,"광주전남","순천","여수TP용성#2 T/L","장기 미동작 차단기 시험","여수TP-용성#2L 장기 미동작 차단기 시험","2018-06-14 13:00","2018-06-14 15:00","취소","취소","당일",null,null,null,201803120289,"-"]
[282,"광주전남","순천","여수TP화치#1 T/L","장기 미동작 차단기 시험","여수TP-화치#1 T/L 장기 미동작 차단기 시험","2018-06-19 10:00","2018-06-19 13:00","2018-06-19 10:00","2018-06-19 13:00","당일",null,null,null,201803120298,"-"]
[283,"광주전남","순천","여수TP화치#2 T/L","장기 미동작 차단기 시험","여수TP-화치#2 T/L 장기 미동작 차단기 시험","2018-06-19 13:00","2018-06-19 15:00","2018-06-19 13:00","2018-06-19 15:00","당일",null,null,null,201803120299,"-"]
[284,"광주전남","순천","여수TP화치#2 T/L","154kV 화치S/S 한화케미칼T/L 신규수용공사","#61BUS측 모선, DS, CB, C/H 챔버 증설구간 여수TP-화치#2T/L을 통한 24시간 무부하가압","2018-06-21 15:00","2018-06-22 15:00","2018-06-21 15:00","2018-06-22 15:00","연속",null,null,null,201804050251,"-"]
[285,"광주전남","순천","여수TP화치#2 T/L","154kV 화치S/S 한화케미칼T/L 신규수용공사","#66BUS측 모선 및 DS 증설구간 여수TP-화치#2T/L을 통한 24시간 무부하가압","2018-06-27 15:00","2018-06-28 15:00","2018-06-27 15:00","2018-06-28 15:00","연속",null,null,null,201804050252,"-"]
[286,"광주전남","직할","남광주S/S 남광주-금천#2T/L GIS","18-19년도 직할 변전협력회사 총액공사","- 장기미동작 차단기 점검","2018-06-04 09:00","2018-06-04 18:00","취소","취소","당일",null,null,null,201804040070,"-"]
[287,"광주전남","직할","남광주S/S 남광주-화순#1T/L GIS","18-19년도 직할 변전협력회사 총액공사","- 장기미동작 차단기 점검","2018-06-05 09:00","2018-06-05 13:00","취소","취소","당일",null,null,null,201804040071,"-"]
[288,"광주전남","직할","남광주S/S 남광주-화순#2T/L GIS","18-19년도 직할 변전협력회사 총액공사","- 장기미동작 차단기 점검","2018-06-05 13:00","2018-06-05 18:00","취소","취소","당일",null,null,null,201804040072,"-"]
[289,"광주전남","직할","농성S/S 농성-화정#1T/L GIS","18-19년도 직할 변전협력회사 총액공사","- 장기미동작 차단기 점검","2018-06-07 09:00","2018-06-07 18:00","2018-06-07 09:00","2018-06-07 18:00","당일",null,null,null,201804040074,"-"]
[290,"광주전남","직할","농성S/S 농성-화정#2T/L GIS","18-19년도 직할 변전협력회사 총액공사","- 장기미동작 차단기 점검","2018-06-14 09:00","2018-06-14 18:00","2018-06-14 09:00","2018-06-14 18:00","당일",null,null,null,201804040075,"-"]
[291,"광주전남","직할","매월S/S 매월-화정#1T/L GIS","18-19년도 직할 변전협력회사 총액공사","- 장기미동작 차단기 점검","2018-06-11 09:00","2018-06-11 18:00","취소","취소","당일",null,null,null,201804040076,"-"]
[292,"광주전남","직할","매월S/S 매월-화정#2T/L GIS","18-19년도 직할 변전협력회사 총액공사","- 장기미동작 차단기 점검","2018-06-12 09:00","2018-06-12 18:00","취소","취소","당일",null,null,null,201804040077,"-"]
[293,"광주전남","직할","신화순나주#2 T/L","154kV 나주옥내화 건설공사","○154kV 나주옥내화 건설공사 - M.Tr : 154kV 60MVA 4Bank - GIS : 154kV 50kA 19CCT(11T/L), 22.9kV 25kA 41CCT(25D/L) - 기타부대공사","2018-06-29 09:00","2018-07-01 18:00","2018-06-29 09:00","2018-07-01 18:00","연속",null,null,null,201804200131,"-"]
[294,"광주전남","직할","일곡비아#2 T/L","[변전] 비아S/S 170kV 장기사용GIS 대체공사","○ 비아S/S 현대화사업 및 170kV 장기사용GIS 대체공사","2018-06-18 09:00","2018-07-06 18:00","취소","취소","연속",null,null,null,201804020088,"-"]
[295,"대구","경산","신경산노변 T/L","신경산S/S 신경산-노변T/L 휴전","GIS 초기점검","2018-06-18 09:00","2018-06-18 14:00",{"$f":"G300","v":"2018-06-18 09:00"},{"$f":"H300","v":"2018-06-18 14:00"},"당일",null,null,null,201804090723,"-"]
[296,"대구","달성","고령논공#1 T/L","달성전력지사 변전총액공사","달성전력지사 변전총액공사","2018-06-21 09:00","2018-06-21 18:00","2018-06-23 09:00","2018-06-23 18:00","당일",null,null,"신뢰도개선",201804090333,"-"]
[297,"대구","달성","고령다산#1 T/L","달성전력지사 변전총액공사","달성전력지사 변전총액공사","2018-06-22 09:00","2018-06-22 18:00",{"$f":"G302","v":"2018-06-22 09:00"},"2018-06-22 18:00","당일",null,null,null,201804090334,"-"]
[298,"대구","달성","고령다산#2 T/L","달성전력지사 변전총액공사","달성전력지사 변전총액공사","2018-06-25 09:00","2018-06-25 18:00","2018-06-25 09:00","2018-06-25 18:00","당일",null,null,null,201804090335,"-"]
[299,"대구","달성","고령쌍림#1 T/L","달성전력지사 변전총액공사","달성전력지사 변전총액공사","2018-06-26 09:00","2018-06-26 18:00","2018-06-26 09:00","2018-06-26 18:00","당일",null,null,null,201804090336,"-"]
[300,"대구","달성","논공S/S #1 EM.Tr A CB","달성전력지사 변전총액공사","달성전력지사 변전총액공사","2018-06-18 09:00","2018-06-29 18:00",{"$f":"G305","v":"2018-06-18 09:00"},{"$f":"H305","v":"2018-06-29 18:00"},"연속",null,null,null,201804090321,"-"]
[301,"대구","달성","논공달성#1 T/L","154kv 논공-달성T/L 안전이격확보 및 전선교체공사","논공-달성T/L 30호 철탑 교체 18~25,25~35,36~S/T 전선접속개소 전선교체","2018-06-25 09:00","2018-07-09 18:00",{"$f":"G306","v":"2018-06-25 09:00"},{"$f":"H306","v":"2018-07-09 18:00"},"연속",null,null,null,201804040029,"-"]
[303,"대구","달성","달서팔달#1 T/L","154kV 달서-팔달 등 2개T/L 지장선로 이설공사","○ 목 적 : 대구광역시 매립장증설사업에 지장이 되어 이설 ○ 구 간 : 154kV 달서-팔달T/L No.10~13, 4회선 [하단 : 북대구-팔달T/L] ○ 수 량 : 철탑 이설 2기(가철탑 2기), 전력선교체 4C, 1.051km (A410㎟, HST410㎟)","2018-06-07 08:00","2018-06-29 18:00",{"$f":"G307","v":"2018-06-07 08:00"},"2018-06-29 18:00","연속",null,null,null,201804120106,"-"]
[304,"대구","달성","대구봉덕#1 T/L","PD집합반 설치공사","EBA 하부 PD 측정센서 설치 및 철탑하부 집합반 단자함 설치","2018-06-07 09:00","2018-06-07 18:00","2018-06-07 09:00","2018-06-07 18:00","당일",null,null,null,201804060235,"-"]
[305,"대구","달성","대구봉덕#2 T/L","PD집합반 설치공사","EBA 하부 PD 측정센서 설치 및 철탑하부 집합반 단자함 설치","2018-06-08 09:00","2018-06-08 18:00","2018-06-08 09:00","2018-06-08 18:00","당일",null,null,null,201804060236,"-"]
[306,"대구","달성","북대구팔달#1 T/L","154kV 달서-팔달 등 2개T/L 지장선로 이설공사","○ 목 적 : 대구광역시 매립장증설사업에 지장이 되어 이설 ○ 구 간 : 154kV 달서-팔달T/L No.10~13, 4회선 [하단 : 북대구-팔달T/L] ○ 수 량 : 철탑 이설 2기(가철탑 2기), 전력선교체 4C, 1.051km (A410㎟, HST410㎟)","2018-06-07 08:00","2018-06-29 18:00","2018-06-07 08:00","2018-06-29 18:00","연속",null,null,null,201804120105,"-"]
[307,"대구","달성","상인봉덕#1 T/L","PD집합반 설치공사","EBA 하부 PD 측정센서 설치 및 철탑하부 집합반 단자함 설치","2018-06-20 09:00","2018-06-20 18:00","2018-06-20 09:00","2018-06-20 18:00","당일",null,null,null,201804060240,"-"]
[308,"대구","달성","상인봉덕#2 T/L","PD집합반 설치공사","EBA 하부 PD 측정센서 설치 및 철탑하부 집합반 단자함 설치","2018-06-21 09:00","2018-06-21 18:00","2018-06-21 09:00","2018-06-21 18:00","당일",null,null,null,201804060242,"-"]
[309,"대구","칠곡","관음구암#1 T/L","345kV 선산-신포항T/L 전선접속개소 전력선 교체공사 안전확보","345kV 신포항-북대구T/L No.49~50 선하 154kV 관음-구암T/L No.37~38 경과선로 안전확보(6월3일 당일만 휴전, 즉시가압가능)","2018-06-03 08:00","2018-06-03 18:00","2018-06-03 08:00","2018-06-03 18:00","당일",null,null,null,201804090064,"-"]
[310,"대구","칠곡","관음구암#2 T/L","345kV 선산-신포항T/L 전선접속개소 전력선 교체공사 안전확보","345kV 신포항-북대구T/L No.49~50 선하 154kV 관음-구암T/L No.37~38 경과선로 안전확보(6월3일 당일만 휴전, 즉시가압가능)","2018-06-03 08:00","2018-06-03 18:00","2018-06-03 08:00","2018-06-03 18:00","당일",null,null,null,201804090066,"-"]
[311,"대구","칠곡","북대구관음#1 T/L","154kV북대구S/S 지중송전선로 인출변경공사","북대구왜관, 북대구관음T/L 지중인출BAY 변경공사","2018-06-23 09:00","2018-07-10 18:00","2018-06-23 09:00","2018-07-10 18:00","연속",null,null,null,201804090278,"-"]
[312,"대구","칠곡","북대구관음#2 T/L","154kV북대구S/S 지중송전선로 인출변경공사","북대구왜관, 북대구관음T/L 지중인출BAY 변경공사","2018-06-04 09:00","2018-06-22 18:00","2018-06-04 09:00","2018-06-22 18:00","연속",null,null,null,201804090273,"-"]
[313,"대구","칠곡","북대구왜관#1 T/L","154kV북대구S/S 지중송전선로 인출변경공사","북대구왜관, 북대구관음T/L 지중인출BAY 변경공사","2018-06-23 09:00","2018-07-02 18:00","2018-06-23 09:00","2018-07-02 18:00","연속",null,null,null,201804090281,"-"]
[314,"대구","칠곡","북대구왜관#2 T/L","154kV북대구S/S 지중송전선로 인출변경공사","북대구왜관, 북대구관음T/L 지중인출BAY 변경공사","2018-06-04 09:00","2018-06-14 18:00","2018-06-04 09:00","2018-06-14 18:00","연속",null,null,null,201804090269,"-"]
[315,"대구","포항","아화건천#1 T/L","154kV 아화-건천T/L 안전이격확보 철탑교체공사","No.27-34 양회선 휴전 철탑교체공사","2018-06-23 07:00","2018-07-02 18:00","2018-06-23 07:00","2018-07-02 18:00","연속",null,null,null,201804130052,"-"]
[316,"대구","포항","아화건천#2 T/L","154kV 아화-건천T/L 안전이격확보 철탑교체공사","No.27-34 양회선 휴전 철탑교체공사","2018-06-23 07:00","2018-07-02 18:00","2018-06-23 07:00","2018-07-02 18:00","연속",null,null,null,201804130053,"-"]
[317,"경북","구미","선산고아#2 T/L","선산S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 공사 - 선산-안계#1,2T/L 송전선로 인출변경 안전이격 확보","2018-06-04 08:00","2018-06-09 18:00","2018-06-04 08:00","2018-06-09 18:00","연속",null,null,null,201804040099,"-"]
[318,"경북","구미","선산고아#1 T/L","선산S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 공사 - 선산-안계#1,2T/L 송전선로 인출변경 안전이격 확보","2018-06-04 08:00","2018-06-09 18:00","2018-06-04 08:00","2018-06-09 18:00","연속",null,null,null,201804040096,"-"]
[319,"경북","구미","선산청리#1 T/L","선산S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 공사 - RTU D/O 정비공사 관련 시험","2018-06-20 09:00","2018-06-20 14:00","2018-06-20 09:00","2018-06-20 14:00","당일",null,null,null,201804110177,"-"]
[320,"경북","구미","선산청리#2 T/L","선산S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 공사 - RTU D/O 정비공사 관련 시험","2018-06-20 09:00","2018-06-20 14:00","2018-06-20 09:00","2018-06-20 14:00","당일",null,null,null,201804110178,"-"]
[321,"경북","구미","청리S/S 청리-상주#1T/L GIS","2018년도 구미전력지사 변전협력 총액공사","GIS보통점검, LA보통점검","2018-06-11 09:00","2018-06-11 14:00","2018-06-11 09:00","2018-06-11 14:00","당일",null,null,null,201804120255,"-"]
[322,"경북","구미","청리S/S 청리-상주#2T/L GIS","2018년도 구미전력지사 변전협력 총액공사","GIS보통점검, LA보통점검","2018-06-11 14:00","2018-06-11 18:00","2018-06-11 14:00","2018-06-11 18:00","당일",null,null,null,201804120258,"-"]
[323,"경북","영주","봉화울진 T/L","2018-19년도 영주전력지사 변전협력업체 총액공사","봉화S/S 170kV 627 GIS, LA A,B,C상 보통점검","2018-06-12 10:00","2018-06-12 15:00","취소","취소","당일",null,null,"신뢰도개선",201804040038,"-"]
[324,"경북","영주","신영주예천#1 T/L","345kV 신제천-신영주T/L 전선접속개소 전선교체공사","345kV 신제천-신영주T/L 공사관련 하단 안전확보","2018-06-05 09:00","2018-06-07 18:00",{"$f":"G328","v":"2018-06-05 09:00"},"2018-06-07 18:00","매일",null,null,null,201803060033,"-"]
[325,"경북","영주","신영주예천#2 T/L","345kV 신제천-신영주T/L 전선접속개소 전선교체공사","345kV 신제천-신영주T/L 공사관련 하단 안전확보","2018-06-05 09:00","2018-06-07 18:00","2018-06-05 09:00","2018-06-07 18:00","매일",null,null,null,201803060034,"-"]
[326,"경북","영주","점촌단양 T/L","공기압축 조작방식 차단기 동작특성시험","공기압축 조작방식 차단기 동작특성시험","2018-06-01 09:00","2018-06-01 14:00","2018-06-01 09:00","2018-06-01 14:00","당일",null,null,null,201804160236,"-"]
[327,"경북","직할","진보영양풍력 T/L CB","2018년 경북본부 직할 170kV GIS 정밀점검","영양풍력T/L GIS 정밀점검","2018-06-18 09:00","2018-06-21 18:00","2018-06-18 09:00","2018-06-21 18:00","연속",null,null,null,201804130014,"-"]
[328,"부산울산","동부산","신양산S/S 154kV #60 BUS","345kV 신양산S/S 현대화 공사","- 154kV 덕트 기초 터파기 - 안전이격확보","2018-06-08 09:00","2018-06-08 18:00","2018-06-08 09:00","2018-06-08 18:00","당일",null,null,null,201804160203,"-"]
[329,"부산울산","동부산","신양산S/S 154kV #65 BUS","345kV 신양산S/S 현대화 공사","- 154kV 덕트 기초 터파기 - 안전이격확보","2018-06-07 09:00","2018-06-07 18:00","2018-06-07 09:00","2018-06-07 18:00","당일",null,null,null,201804160202,"-"]
[330,"부산울산","동부산","신양산S/S 60-61-0 SEC CB","신양산S/S 170kV GIS 조작시험","신양산S/S 170kV GIS 조작시험(60-61-0)","2018-06-01 09:30","2018-06-01 11:30","2018-06-01 09:30","2018-06-01 11:30","당일",null,null,null,201804090811,"-"]
[331,"부산울산","동부산","신양산S/S 61-62-0 SEC CB","신양산S/S 170kV GIS 조작시험","신양산S/S 170kV GIS 조작시험(61-62-0)","2018-06-01 11:30","2018-06-01 15:00","2018-06-01 11:30","2018-06-01 15:00","당일",null,null,null,201804090812,"-"]
[332,"부산울산","동부산","신양산S/S 66-67-0 SEC CB","신양산S/S 170kV GIS 조작시험","신양산S/S 170kV GIS 조작시험(66-67-0)","2018-06-01 15:00","2018-06-01 17:00","2018-06-01 15:00","2018-06-01 17:00","당일",null,null,null,201804090813,"-"]
[333,"부산울산","동부산","웅촌서창#1 T/L","154kV 웅촌-서창T/L 20호 지장철탑이설공사","작업구간 : 18~21호, 철탑교체 : 20호","2018-06-18 08:00","2018-06-21 18:00","2018-06-18 08:00","2018-06-21 18:00","연속",null,null,null,201804030089,"-"]
[334,"부산울산","동부산","웅촌서창#2 T/L","154kV 웅촌-서창T/L 20호 지장철탑이설공사","작업구간 : 18~21호, 철탑교체 : 20호","2018-06-22 08:00","2018-06-25 18:00","2018-06-22 08:00","2018-06-25 18:00","연속",null,null,null,201804030091,"-"]
[335,"부산울산","북부산","김해S/S 154kV #1 BUS","(1차)김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#2T/L GIS 대체(#1DS 시험가압)","2018-06-24 16:00","2018-06-24 18:00","2018-06-24 16:00","2018-06-24 18:00","당일",null,null,null,201804030109,"-"]
[336,"부산울산","북부산","김해S/S 154kV #1 BUS","(2차)김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#1T/L GIS 대체(#1DS, CB, 상부BUS 설치)","2018-06-26 13:00","2018-07-01 18:00","2018-06-26 13:00","2018-07-01 18:00","연속",null,null,null,201804030112,"-"]
[337,"부산울산","북부산","김해S/S 154kV #1 BUS","(1차)김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#2T/L GIS 대체(#1DS, CB, 상부BUS 설치)","2018-06-10 13:00","2018-06-16 18:00","2018-06-10 13:00","2018-06-16 18:00","연속",null,null,null,201804170019,"-"]
[338,"부산울산","북부산","김해S/S 154kV #2 BUS","(2차)김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#1T/L GIS 대체(#2DS 철거)","2018-06-25 08:00","2018-06-26 13:00","2018-06-25 08:00","2018-06-26 13:00","연속",null,null,null,201804030113,"-"]
[339,"부산울산","북부산","김해S/S 154kV #2 BUS","(1차)김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#2T/L GIS 대체 (#2DS 철거)","2018-06-09 08:00","2018-06-10 13:00","2018-06-09 08:00","2018-06-10 13:00","연속",null,null,null,201804170017,"-"]
[340,"부산울산","북부산","김해S/S 154kV #2 BUS","(1차)김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#2T/L GIS 대체(#2DS 설치)","2018-06-17 08:00","2018-06-24 16:00",{"$f":"G344","v":"2018-06-17 08:00"},"2018-06-24 16:00","연속",null,null,null,201804170021,"-"]
[341,"부산울산","북부산","김해어방#1 T/L","(2차)김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#1T/L GIS 대체","2018-06-25 08:00","2018-07-09 18:00","2018-06-25 08:00","2018-07-09 18:00","연속",null,null,null,201804030116,"-"]
[342,"부산울산","북부산","김해어방#2 T/L","(2차)김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#1T/L GIS 대체(Wall Bushing 철거 안전이격)","2018-06-25 13:00","2018-06-25 15:00","2018-06-25 13:00","2018-06-25 15:00","당일",null,null,null,201804090482,"-"]
[343,"부산울산","북부산","김해어방#2 T/L","(1차)김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#2T/L GIS 대체 (677 휴전)","2018-06-09 08:00","2018-06-24 18:00","2018-06-09 08:00","2018-06-24 18:00","연속",null,null,null,201804170016,"-"]
[344,"부산울산","북부산","매리김해#1 T/L","(2차)김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#1T/L GIS 대체(#1BUS 시험가압)","2018-06-30 18:00","2018-07-01 18:00","2018-06-30 18:00","2018-07-01 18:00","연속",null,null,null,201804030118,"-"]
[345,"부산울산","북부산","매리김해#1 T/L","(1차)김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 김해-어방#2T/L GIS 대체 - #1BUS 시험가압 24h (647 휴전)","2018-06-15 18:00","2018-06-16 18:00","2018-06-15 18:00","2018-06-16 18:00","연속",null,null,null,201804170020,"-"]
[346,"부산울산","북부산","매리김해#2 T/L","(1차)김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#2T/L GIS 대체(#2DS, #2BUS, CB, 상부BUS 시험가압 / #1DS 시험가압)","2018-06-23 16:00","2018-06-24 18:00","2018-06-23 16:00","2018-06-24 18:00","연속",null,null,null,201804030111,"-"]
[347,"부산울산","북부산","매리김해#2 T/L","(2차)김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#1T/L GIS 대체(#2BUS 시험가압)","2018-06-26 11:00","2018-06-26 13:00","2018-06-26 11:00","2018-06-26 13:00","당일",null,null,null,201804030117,"-"]
[348,"부산울산","북부산","매리김해#2 T/L","(1차)김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 김해-어방#2T/L GIS 대체 - #2BUS 시험가압 2h (647 휴전)","2018-06-10 11:00","2018-06-10 13:00","2018-06-10 11:00","2018-06-10 13:00","당일",null,null,null,201804170018,"-"]
[349,"부산울산","북부산","북부산물금 T/L","154kV 물금S/S #4M.Tr 증설공사","#4M.Tr 최초가압 선로","2018-06-19 17:00","2018-06-20 18:00","2018-06-19 17:00","2018-06-20 18:00","연속",null,null,null,201804060246,"-"]
[350,"부산울산","북부산","양산산막#1 T/L","154kV 양산-산막 외1개T/L 인출철탑 정비공사","○ 구 간 : 154㎸ 양산-산막T/L S/T ∼ 2호 ○ 내 용 : 1호 철탑 교체 및 전력선 교체 작업 ※ 안전이격 확보","2018-06-10 08:00","2018-06-10 18:00","2018-06-10 08:00","2018-06-10 18:00","당일",null,null,null,201804100108,"-"]
[351,"부산울산","북부산","양산산막#1 T/L","154kV 양산-산막 외1개T/L 인출철탑 정비공사","○ 구 간 : 154㎸ 양산-산막T/L S/T ∼ 2호 ○ 내 용 : 1호 철탑 교체 및 전력선 교체 작업","2018-06-15 08:00","2018-06-17 18:00","2018-06-15 08:00","2018-06-17 18:00","연속",null,null,null,201804100110,"-"]
[352,"부산울산","북부산","양산산막#2 T/L","154kV 양산-산막 외1개T/L 인출철탑 정비공사","○ 구 간 : 154㎸ 양산-산막T/L S/T ∼ 2호 ○ 내 용 : 1호 철탑 교체 및 전력선 교체 작업","2018-06-10 08:00","2018-06-14 18:00","2018-06-10 08:00","2018-06-14 18:00","연속",null,null,null,201804100109,"-"]
[353,"부산울산","북부산","주촌삼계#1 T/L","2018년 북부산 변전협력회사 총액공사","삼계S/S 154kV 주촌-삼계#1T/L GIS 미동작 점검","2018-06-12 10:00","2018-06-12 18:00","2018-06-12 10:00","2018-06-12 18:00","당일",null,null,null,201804030123,"-"]
[354,"부산울산","북부산","호포물금 T/L","154㎸ 신울산-웅촌등 7개 T/L 자기애관 교체공사","지중송전선로용 자기애관(EBA)→폴리머 애관 교체공사","2018-06-05 09:00","2018-06-08 18:00","2018-06-05 09:00","2018-06-08 18:00","연속",null,null,null,201804020195,"-"]
[355,"부산울산","서부산","녹공마천#1 T/L","녹공S/S 154kV #1Sh.C Main Gis 정밀점검","녹공S/S 154kV #1Sh.C Main Gis(6179) GIS 정밀점검 (CB, 상부BUS 시험가압)","2018-06-01 17:00","2018-06-01 18:00","2018-06-01 17:00","2018-06-01 18:00","당일",null,null,null,201804050296,"-"]
[356,"부산울산","서부산","서부산S/S 154kV #60 BUS","서부산S/S 154kV 인출 지중송전선로 정비공사","송전선로 정비공사 완료(무부하시험) 후 앵글체크","2018-06-04 11:00","2018-06-04 11:30",{"$f":"G360","v":"2018-06-04 11:00"},"2018-06-04 11:30","당일",null,null,null,201804190073,"-"]
[357,"부산울산","서부산","서부산S/S 154kV #61 BUS","서부산S/S 154kV #61M.Tr 1차 GIS(6133) 시험가압","서부산S/S 154kV #61M.Tr 1차 GIS(6133) 정밀점검 시험가압 (CB, 상부BUS 시험가압)","2018-06-19 17:00","2018-06-19 18:00","2018-06-19 17:00","2018-06-19 18:00","당일",null,null,null,201804040087,"-"]
[358,"부산울산","서부산","서부산S/S 154kV #61 BUS","서부산S/S 154kV 인출 지중송전선로 정비공사","송전선로 정비공사 완료(무부하시험) 후 앵글체크","2018-06-04 11:00","2018-06-04 11:30","2018-06-04 11:00","2018-06-04 11:30","당일",null,null,null,201804190074,"-"]
[359,"부산울산","서부산","서부산S/S 154kV #66 BUS","서부산S/S 154kV #62M.Tr 1차 GIS(6233) 시험가압","서부산S/S 154kV #62M.Tr 1차 GIS(6233) 정밀점검 시험가압 (CB, 상부BUS)","2018-06-21 17:00","2018-06-21 18:00","2018-06-21 17:00","2018-06-21 18:00","당일",null,null,null,201804040092,"-"]
[360,"부산울산","서부산","서부산부산 T/L","서부산S/S 154kV 서부산-부산T/L GIS (6K7) 정밀점검","서부산S/S 154kV 서부산-부산T/L GIS (6K7) 정밀점검 (모선DS 점검제외)","2018-06-22 08:00","2018-06-23 18:00","2018-06-22 08:00","2018-06-23 18:00","연속",null,null,null,201804040086,"-"]
[361,"부산울산","서부산","서부산엄궁#1 T/L","서부산S/S 154kV #62M.Tr 1차(6233) GIS 시험가압","서부산S/S 154kV #62M.Tr 1차(6233) GIS 정밀점검 시험가압 (CB, 상부BUS 시험가압)","2018-06-21 17:00","2018-06-21 18:00","2018-06-21 17:00","2018-06-21 18:00","당일",null,null,null,201804040097,"○"]
[362,"부산울산","서부산","서부산엄궁#2 T/L","서부산S/S 154kV #61M.Tr 1차(6133) GIS 시험가압","서부산S/S 154kV #61M.Tr 1차(6133) GIS 정밀점검 시험가압 (CB, 상부BUS 시험가압)","2018-06-19 17:00","2018-06-19 18:00","2018-06-19 17:00","2018-06-19 18:00","당일",null,null,null,201804040088,"-"]
[363,"부산울산","울산","동울산방어진 T/L","2018-19년 울산전력지사 변전협력회사 총액공사","1. 동울산S/S 154kV 6A7 GIS 차단기 동작시험 2. 방어진S/S 154kV 617 GIS 차단기 동작시험","2018-06-30 09:00","2018-06-30 18:00","2018-06-30 09:00","2018-06-30 18:00","당일",null,null,null,201804090735,"-"]
[364,"부산울산","울산","신울산언양#1 T/L","154kV 신울산-언양 등 3개T/L 지장철탑이설공사","○ 64호 신설철탑 설치 및 63호 상부재 교체 ○ 작업구간 : 59호~65호","2018-06-05 08:00","2018-06-08 18:00","취소","취소","연속",null,null,"신뢰도개선",201804030085,"-"]
[365,"부산울산","울산","신울산언양#2 T/L","154kV 신울산-언양 등 3개T/L 지장철탑이설공사","○ 64호 신설철탑 설치 및 63호 상부재 교체 ○ 작업구간 : 59호~65호","2018-06-05 08:00","2018-06-08 18:00","취소","취소","연속",null,null,"신뢰도개선",201804030086,"-"]
[366,"부산울산","울산","언양산막#2 T/L","154kV 신울산-웅촌 등 7개 T/L 자기애관 교체공사","지중송전선로용 자기애관(EBA)→폴리머 애관 교체공사","2018-06-01 09:00","2018-06-04 18:00",{"$f":"G370","v":"2018-06-01 09:00"},"2018-06-04 18:00","연속",null,null,null,201804090601,"-"]
[367,"부산울산","울산","옥동외동#2 T/L","2018~2019년 울산전력지사 송전정비 협력회사 총액공사","외동-옥동#2T/L 46~47호, 57~58호 회전스페이서 설치","2018-06-04 09:00","2018-06-05 18:00",{"$f":"G371","v":"2018-06-04 09:00"},{"$f":"H371","v":"2018-06-05 18:00"},"매일",null,null,null,201804030088,"-"]
[368,"부산울산","울산","용연처용#2 T/L","2018년 처용S/S 170kV 장기사용 GIS 대체공사","처용S/S 170kV 용연-처용#2T/L(617),#1M.Tr 1차 GIS(6133) 대체공사","2018-06-04 08:00","2018-06-22 18:00","2018-06-04 08:00","2018-06-22 18:00","연속",null,null,null,201804170158,"-"]
[369,"부산울산","직할","명장연산#1 T/L","154kV 연산S/S #3M.Tr 증설공사","※154kV 연산S/S #3M.Tr 증설공사(154KV GIS설치) - 연산S/S #1BUS 시험가압 24hr(#1DS 투입X)","2018-06-01 16:00","2018-06-02 16:00","2018-06-01 16:00","2018-06-02 16:00","연속",null,null,null,201804090367,"-"]
[370,"부산울산","직할","명장연산#2 T/L","154kV 연산S/S #3M.Tr 증설공사","※154kV 연산S/S #3M.Tr 증설공사(154KV GIS설치) - 연산S/S #2BUS 시험가압 24hr(6332DS투입)","2018-06-08 16:00","2018-06-09 16:00","2018-06-08 16:00","2018-06-09 16:00","연속",null,null,null,201804090364,"-"]
[371,"부산울산","직할","부민부산 T/L","2018년 직할 관내 170kV GIS 정밀점검공사","부민S/S #4M.Tr 1차 GIS(6433) 정밀점검 시험가압선로","2018-06-07 17:00","2018-06-07 18:00","2018-06-07 17:00","2018-06-07 18:00","당일",null,null,null,201804160215,"-"]
[372,"경남","직할","신월동읍#2 T/L","154kV 신월-동읍 등 2개T/L OF케이블 교체공사","신월EBG~#1M/H 구간 154kV 신월-동읍#2T/L 케이블 교체(OF1200㎟ → XLPE1200㎟)","2018-06-09 08:00","2018-07-03 18:00","2018-06-09 08:00","2018-07-03 18:00","연속",null,null,null,201804100111,"-"]
[373,"경남","직할","천선개폐소 154kV #60 BUS","삼정S/S 154kV 삼정-천선#1,2T/L 인출변경 공사 시험가압","삼정S/S 옥외철구설비 GIS화 사업의 부지확보 작업 154kV 삼정-천선#1,2T/L 인출변경 후 송전선로 시험가압 및 상체크","2018-06-05 09:30","2018-06-07 17:30","2018-06-05 09:30","2018-06-07 17:30","연속",null,null,null,201804060114,"-"]
[374,"경남","진주","삼천포사천#2 T/L","사천S/S 154kV #1Sh.C CB(6179) 정밀점검 시험가압","사천S/S 154kV #1Sh.C CB(6179) 정밀점검 시험가압","2018-06-08 18:00","2018-06-08 18:30","2018-06-08 18:00","2018-06-08 18:30","연속",null,null,null,201804090197,"-"]
[375,"경남","진주","의령S/S 154kV #1 BUS TIE CB","의령S/S 154kV BUS SEC 정밀점검 시험가압 - 황색차단기","의령S/S 154kV BUS SEC CB(65-66-0) 정밀점검 시험가압 - 황색차단기","2018-06-27 18:00","2018-06-27 18:30","2018-06-27 18:00","2018-06-27 18:30","당일",null,null,null,201804050255,"○"]
[376,"경남","진주","의령S/S 154kV #1 BUS TIE CB","의령S/S 154kV 의령-함양T/L 정밀점검 시험가압 - 황색차단기","의령S/S 154kV 의령-함양T/L CB(637) 정밀점검 시험가압 - 황색차단기","2018-06-03 18:00","2018-06-03 18:30","2018-06-03 18:00","2018-06-03 18:30","당일",null,null,null,201804170197,"○"]
[377,"경남","진주","의령함양 T/L","의령S/S 154kV 의령-함양T/L CB(637) 정밀점검","의령S/S 154kV 의령-함양T/L CB(637) 정밀점검 병행 : 함양S/S 154kV 의령-함양T/L PT,LA(A,B,C) 보통점검 함양S/S 의령-함양#1T/L CB(667) 개폐장치 조작시험 의령S/S 의령-함양T/L LA(A,B,C) 보통점검","2018-06-02 09:30","2018-06-03 18:30","2018-06-02 09:30","2018-06-03 18:30","연속",null,null,null,201804170195,"-"]
[378,"경남","진주","진주개양#1 T/L","154kV 하동-남해 등 2개T/L 안전이격확보 및 송전설비보강공사","154kV 진주-개양T/L 6~9호 이도조정","2018-06-16 06:00","2018-06-16 20:00","2018-06-16 06:00","2018-06-16 20:00","당일",null,null,null,201804010014,"-"]
[379,"경남","통영","삼천포사천#1 T/L","154kV 삼천포S/S #2M.Tr 증설공사(최초가압)","1. 154kV삼천포변전소 #2변압기 증설공사 - 154/229KV 45/60MVA 1BANK - #2M.Tr 최초가압 선로","2018-06-20 10:00","2018-06-21 10:00","2018-06-20 10:00","2018-06-21 10:00","연속",null,null,null,201804170182,"-"]
[380,"경남","통영","신고성통영 T/L","154kV 신고성-통영T/L 송전선로 정밀점검","154kV 신고성-통영T/L 송전선로 정밀점검(1~149호, 148기)","2018-06-02 09:00","2018-06-03 18:00","2018-06-02 09:00","2018-06-03 18:00","매일",null,null,null,201804090312,"-"]
[381,"경남","통영","신고성통영 T/L","154kV 신고성-통영T/L 송전선로 정밀점검","154kV 신고성-통영T/L 송전선로 정밀점검(1~149호, 148기)","2018-06-09 09:00","2018-06-10 18:00","2018-06-09 09:00","2018-06-10 18:00","매일",null,null,null,201804090314,"-"]
[382,"경남","통영","통영거제#1 T/L","154kV 신고성-통영T/L 송전선로 정밀점검 병가구간 안전확보","154kV 신고성-통영T/L 송전선로 정밀점검(1~149호, 148기) 병가구간 작업자 안전확보","2018-06-03 09:00","2018-06-03 18:00","2018-06-03 09:00","2018-06-03 18:00","당일",null,null,null,201804090323,"-"]
[383,"경남","통영","통영거제#1 T/L","거제S/S 154kV BUS-TIE GIS 정밀점검(시험가압)","1. 거제S/S 154kV BUS-TIE GIS 정밀점검(시험가압)","2018-06-02 18:00","2018-06-02 19:00","2018-06-02 18:00","2018-06-02 19:00","당일",null,null,null,201804160005,"-"]
[384,"경남","함안","신김해진영#1 T/L","진영S/S 신김해-진영#1T/L GIS 조작시험","진영S/S 신김해-진영#1T/L GIS 조작시험","2018-06-24 09:30","2018-06-24 13:30","취소","취소","당일",null,null,null,201804100016,"-"]
[385,"경남","함안","신김해진영#2 T/L","진영S/S 신김해-진영#2T/L GIS 조작시험","진영S/S 신김해-진영#2T/L GIS 조작시험","2018-06-24 13:30","2018-06-24 17:30","취소","취소","당일",null,null,null,201804100018,"-"]
[386,"경남","함안","신마산마산#2 T/L","154kV 신마산-진동T/L 접속개소 전선교체공사","○ 공사개요 - 154kV 신마산-진동T/L 안전거리확보","2018-06-16 06:30","2018-06-17 19:00","2018-06-16 06:30","2018-06-17 19:00","연속",null,null,null,201804130013,"-"]
[387,"경남","함안","진영초동#1 T/L","154kV 수산S/S 건설공사","-진영-초동#1T/L 파이분기 →진영-수산#1T/L, 초동-수산#1T/L","2018-06-14 09:00","2018-06-22 18:00","2018-06-14 09:00","2018-06-22 18:00","연속",null,null,null,201804110157,"-"]
[388,"경남","함안","진영초동#2 T/L","154kV 수산S/S 건설공사","-진영-초동#2T/L 파이분기 →진영-수산#2T/L, 초동-수산#2T/L","2018-06-23 09:00","2018-06-28 18:00","2018-06-23 09:00","2018-06-28 18:00","연속",null,null,null,201804110158,"-"]
[389,"경남","함안","진영한림정#1 T/L","한림정S/S 진영-한림정#1T/L GIS 제작사 메커니즘 보수","한림정S/S 진영-한림정#1T/L 6C7 GIS 제작사 메커니즘 보수","2018-06-02 09:30","2018-06-03 17:30","2018-06-02 09:30","2018-06-03 17:30","당일",null,null,null,201804100044,"-"]
[390,"경남","함안","진영한림정#1 T/L","(시험가압)한림정S/S 한림정-삼계#1T/L GIS 제작사 메커니즘 보수","(시험가압)한림정S/S 한림정-삼계#1T/L 617 GIS 제작사 메커니즘 보수","2018-06-17 14:00","2018-06-17 17:30","2018-06-17 14:00","2018-06-17 17:30","당일",null,null,null,201804100052,"-"]
[391,"경남","함안","진영한림정#2 T/L","한림정S/S 진영-한림정#2T/L GIS 제작사 메커니즘 보수","한림정S/S 진영-한림정#2T/L 677 GIS 제작사 메커니즘 보수","2018-06-09 09:30","2018-06-10 17:30","2018-06-09 09:30","2018-06-10 17:30","당일",null,null,null,201804100048,"-"]
[392,"경남","함안","한림정삼계#1 T/L","(시험가압)한림정S/S 진영-한림정#1T/L GIS 제작사 메커니즘 보수","(시험가압)한림정S/S 진영-한림정#1T/L 6C7 GIS 제작사 메커니즘 보수","2018-06-03 14:00","2018-06-03 17:30","취소","취소","당일",null,null,null,201804100045,"-"]
[393,"경남","함안","한림정삼계#1 T/L","한림정S/S 한림정-삼계#1T/L GIS 제작사 메커니즘 보수","한림정S/S 한림정-삼계#1T/L 617 GIS 제작사 메커니즘 보수","2018-06-16 09:30","2018-06-17 17:30","2018-06-16 09:30","2018-06-17 17:30","당일",null,null,null,201804100051,"-"]
[394,"경남","함안","한림정삼계#1 T/L","(시험가압)한림정S/S #1M.Tr 1차 GIS 제작사 메커니즘 보수","(시험가압)한림정S/S #1M.Tr 1차 6133 GIS 제작사 메커니즘 보수","2018-06-23 14:00","2018-06-23 17:30","2018-06-23 14:00","2018-06-23 17:30","당일",null,null,null,201804100055,"-"]
[395,"경남","함안","한림정삼계#1 T/L","(시험가압)한림정S/S #1BUS TIE GIS 제작사 메커니즘 보수","(시험가압)한림정S/S #1BUS TIE 6100 GIS 제작사 메커니즘 보수","2018-06-06 14:00","2018-06-06 17:30","2018-06-06 14:00","2018-06-06 17:30","당일",null,null,null,201804100058,"-"]
[396,"경남","함안","한림정삼계#2 T/L","(시험가압)한림정S/S 진영-한림정#2T/L GIS 제작사 메커니즘 보수","(시험가압)한림정S/S 진영-한림정#2T/L 677 GIS 제작사 메커니즘 보수","2018-06-10 14:00","2018-06-10 17:30","취소","취소","당일",null,null,"한전 요청",201804100050,"-"]
[397,"경남","함안","한림정삼계#2 T/L","(시험가압)한림정S/S #2M.Tr 1차 GIS 제작사 메커니즘 보수","(시험가압)한림정S/S #2M.Tr 1차 6233 GIS 제작사 메커니즘 보수","2018-06-30 14:00","2018-06-30 17:30","2018-06-30 14:00","2018-06-30 17:30","당일",null,null,null,201804100056,"-"]

{"sheet":"한수원","index":3,"n_rows":7,"n_cols":20,"rows_kept":7,"cut":false,"hidden":false,"merged":[[0,0,0,6],[2,12,3,12],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,19,3,19],[2,13,3,13],[2,14,3,14],[2,15,3,15],[2,16,3,16],[2,17,3,17],[2,18,3,18]]}
["2018년도 06월 휴전계획표(한국수력원자력)"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"한빛본부","2발전소","#3 기동변압기(03XN)","한빛3호기 17차 O/H 중 기동변압기\n(03XN) 점검\n* 조작차단기 : CB 7600, 7671","○ 기동변압기(03XN) 일반점검\n○ 보호계전기 개체 및 연동시험","2018-06-01T10:00:00","2018-06-12T18:00:00","2018-06-01T10:00:00","2018-06-12T18:00:00","연속","Y"]
[2,"한빛본부","2발전소","#3 기동변압기(04XN)","한빛3호기 17차 O/H 중 기동변압기\n(04XN) 점검\n* 조작차단기 : CB 7500, 7571","○ 기동변압기(04XN) 일반점검\n○ 보호계전기 개체 및 연동시험","2018-06-18T10:00:00","2018-06-29T22:00:00","2018-06-18T10:00:00","2018-06-29T22:00:00","연속","Y"]
[3,"월성본부","2발전소","#3 주변압기","월성3호기 16차 O/H 중 주변압기\n점검\n* 조작차단기 : CB 7500, 7572","○ 주변압기 및 소내용변압기 점검","2018-06-11T09:00:00","2018-07-06T19:00:00","2018-06-11T09:00:00","2018-07-06T19:00:00","연속","Y"]

{"sheet":"중부","index":4,"n_rows":5,"n_cols":21,"rows_kept":5,"cut":false,"hidden":false,"merged":[[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,20,3,20],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,14,3,14],[2,15,3,15],[2,16,3,16],[2,17,3,17],[2,18,3,18],[2,19,3,19]]}
["2017년도 06월휴전계획표(추가)"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전소\n연계","사업소\n간","사업소\n내","발전소 정지\n계획(OH) 연계"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"인천발전본부","복합2호기","GT #3,4 \n(CB7500, CB7571)","계획예방정비공사(B급)","변압기, GCB 및 IPB 점검,정기검사","2018-06-22T09:00:00","2018-07-13T18:00:00","2018-06-22T09:00:00","2018-07-13T18:00:00","연속",{"$nulls":9},"Y"]