{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["765송부","345송부","154송부","한수원"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":10,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":7,"n_cols":16,"rows_kept":7,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"\"2018년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2018년도 7월 휴전계획서"}]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"강원","태백","신태백S/S 765kV #2 BUS","신태백 S/S 800GIS 정밀점검 공사","8552DS 정밀점검","2018-07-16 10:00","2018-07-20 18:00","2018-07-02 10:00","2018-07-06 18:00","당일",null,null,null,201805040214]
[2,"강원","태백","신태백S/S 765kV #1 BUS","신태백 S/S 800GIS 정밀점검 공사","8551DS 정밀점검","2018-07-23 10:00","2018-07-27 18:00","취소","취소","당일",null,null,null,201805040215]
[3,"대전충남","서산","신서산S/S 765kV #2 BUS","신서산 345kV 7952 DS 가스누기 발생 관련 점검","신서산 345kV 7952 DS 가스누기 발생 관련 점검","2018-07-02 09:00","2018-07-04 18:00","취소","취소","연속",null,null,null,201805170046]

{"sheet":"345송부","index":1,"n_rows":90,"n_cols":16,"rows_kept":90,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"\"2018년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2018년도 7월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","영등포","신광명S/S #4 M.Tr A","영서S/S 154kV 이하 옥외철구 GIS화 공사","가공-EBA 접속, 보호반 시험 등","2018-07-09 08:00","2018-07-27 18:00","2018-07-02 08:00","2018-07-15 18:00","연속",null,null,null,201803200058]
[2,"인천","시흥","영흥#2T/P 신시흥영흥TP#1T/L - TIE CB (7800)","영흥#2T/P 신시흥영흥TP#1T/L-TIE CB(7800)GIS점검","영흥#2T/P 신시흥영흥TP#1T/L - TIE CB(7800) GIS 보통점검","2018-07-03 10:30","2018-07-03 18:00","2018-07-03 10:30","2018-07-03 18:00","당일",null,null,null,201805140166]
[3,"인천","시흥","영흥#2T/P 신시흥영흥TP#1T/L CB (7871)","영흥#2T/P 신시흥영흥TP#1T/L CB(7871)GIS 보통점검","영흥#2T/P 신시흥영흥TP#1T/L CB(7871)GIS 보통점검","2018-07-04 10:30","2018-07-04 18:00","2018-07-04 10:30","2018-07-04 18:00","당일",null,null,null,201805140167]
[4,"인천","인천","서인천C/C 345kV #4 Sh.R","서인천복합S/Y #4Sh.R 물청소 및 GIS 조작시험","서인천복합S/Y #4Sh.R 방열기 물청소 서인천복합S/Y 7A79 GIS 조작시험","2018-07-11 09:00","2018-07-11 18:00","2018-07-11 09:00","2018-07-11 18:00","당일",null,null,null,201805090368]
[5,"인천","인천","서인천C/C 345kV #3 Sh.R","서인천복합S/Y #3Sh.R 보통점검 및 물청소, GIS 조작시험","서인천복합S/Y #3Sh.R 보통점검 서인천복합S/Y #3Sh.R 방열기 물청소 서인천복합S/Y 7B79 GIS 조작시험","2018-07-12 09:00","2018-07-12 18:00","2018-07-12 09:00","2018-07-12 18:00","당일",null,null,null,201805090369]
[6,"인천","인천","서인천C/C 신부평#2T/L #1Sh.R(신) CB","서인천복합S/Y #1Sh.R 초기점검 및 물청소, GIS 조작시험","서인천복합S/Y #1Sh.R 초기점검 서인천복합S/Y #1Sh.R 물청소 서인천복합S/Y 7379 GIS 조작시험","2018-07-10 09:00","2018-07-10 18:00","2018-07-10 09:00","2018-07-10 18:00","당일",null,null,null,201805090366]
[7,"인천","인천","서인천C/C 신부평#3T/L Sh.R(#2 Sh.R) CB","서인천복합S/Y #2Sh.R 물청소 및 GIS 조작시험","서인천복합S/Y #2Sh.R 방열기 물청소 서인천복합S/Y 7479 GIS 조작시험","2018-07-09 09:00","2018-07-09 18:00","2018-07-09 09:00","2018-07-09 18:00","당일",null,null,null,201805090367]
[8,"인천","인천","인천CC S/Y 345kV #75 BUS","345KV 인천CC Sh.R 증설공사","- 345KV Sh.R(200MVAR) X 2Bank 설치 - 345kV GIS (50KA,4000A) X 5CB 설치 - 기타 부대설비 X 1식","2018-07-02 08:00","2018-07-04 18:00","취소","취소","연속",null,null,null,201805150003]
[9,"인천","인천","인천CC S/Y 345kV #76 BUS","345KV 인천CC Sh.R 증설공사","- 345KV Sh.R(200MVAR) X 2Bank 설치 - 345kV GIS (50KA,4000A) X 5CB 설치 - 기타 부대설비 X 1식","2018-07-12 08:00","2018-07-18 18:00","취소","취소","연속",null,null,null,201805150005]
[10,"인천","인천","인천CC S/Y 345kV #71 BUS","345KV 인천CC Sh.R 증설공사","- 345KV Sh.R(200MVAR) X 2Bank 설치 - 345kV GIS (50KA,4000A) X 5CB 설치 - 기타 부대설비 X 1식","2018-07-05 08:00","2018-07-11 18:00","취소","취소","연속",null,null,null,201805150004]
[11,"인천","직할","서인천CC신부평#3 T/L","345kV 서인천CC-신부평#3T/L 절연유 채취","345kV 서인천CC-신부평#3T/L 절연유 채취","2018-07-01 09:00","2018-07-02 18:00","2018-07-01 09:00","2018-07-02 18:00","연속",null,null,null,201805160074]
[12,"경기북부","직할","양주S/S #2 M.Tr A","양주변전소 옥외철구 GIS화 공사","주변압기 3차측 정비","2018-07-02 09:00","2018-07-06 18:00","2018-07-02 09:00","2018-07-06 18:00","연속",null,null,null,201804170466]
[13,"경기","군포","신안산S/S #3 M.Tr A","18년 군포P/O 변전정비회사총액공사","- 1차 차단기(7271,7200) 조작시험 - 2차 차단기(6344) 조작시험 - 3차 차단기(4379) 조작시험","2018-07-03 09:00","2018-07-03 18:00","2018-07-03 09:00","2018-07-03 18:00","당일",null,null,null,201805100116]
[14,"경기","성남","신안성서안성#2 T/L","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ7551DS 전단까지 무부하 가압","2018-07-21 09:00","2018-07-22 09:00","2018-07-21 09:00","2018-07-22 09:00","연속",null,null,null,201805180165]
[15,"경기","성남","서안성신진천#2 T/L","345kV 신안성-서안성T/L OPGW 증설공사","No.93~서안성S/S OPGW 증설(7기)","2018-07-05 07:00","2018-07-06 18:00","2018-07-05 07:00","2018-07-06 18:00","연속",null,null,null,201805110082]
[16,"경기","성남","신성남신양재#1 T/L","345kV 신성남-신양재T/L 접속개소 전선교체공사","345kV 신성남-신양재T/L 접속개소 전선교체공사","2018-07-02 07:00","2018-07-05 18:00","2018-07-02 07:00","2018-07-05 18:00","연속",null,null,null,201805100146]
[17,"경기","성남","신성남신양재#2 T/L","345kV 신성남-신양재T/L 접속개소 전선교체공사","345kV 신성남-신양재T/L 접속개소 전선교체공사","2018-07-06 07:00","2018-07-09 18:00","2018-07-06 07:00","2018-07-09 18:00","연속",null,null,null,201805100156]
[18,"경기","성남","신성남S/S #5 M.Tr A","신성남S/S #5M.Tr, 7600, 7672 보통점검 등","신성남S/S #5M.Tr, 7600, 7672 보통점검, 1차LA 대체, 2차LA, CVT 보통점검, 3차LA 하자점검, 6544 조작시험, M.Tr 누유점검","2018-07-09 09:00","2018-07-10 18:00","2018-07-09 09:00","2018-07-10 18:00","연속",null,null,null,201805110289]
[19,"경기","성남","신수원삼성#1T/L","신수원S/S 345kV 용량부족 GIS 대체공사","75Bay(#3M.Tr) GIS 무부하 가압","2018-07-30 10:00","2018-07-31 18:00","취소","취소","연속",null,null,null,201804130084]
[20,"경기","성남","신수원S/S #3 M.Tr A","신수원S/S 345kV 용량부족 GIS 대체공사","75Bay(#3M.Tr) GIS 무부하 및 실부하 가압","2018-07-30 10:00","2018-07-31 18:00","취소","취소","연속",null,null,null,201804120103]
[21,"경기","성남","신안성신수원#1 T/L","신수원S/S 345kV 용량부족 GIS 대체공사","75Bay(#3M.Tr) GIS 철거 및 설치(무부하가압)","2018-07-02 10:00","2018-07-03 18:00","취소","취소","연속",null,null,null,201804050303]
[22,"경기","성남","신안성신수원#2 T/L","신수원S/S 345kV 용량부족 GIS 대체공사","75Bay(#3M.Tr) GIS 무부하 가압","2018-07-30 10:00","2018-07-31 18:00","취소","취소","연속",null,null,null,201804130112]
[23,"경기","성남","신안성서안성#2 T/L","(안전이격휴전)345kV 신안성신수원T/L 피뢰기 설치(No.2~11)","(안전이격휴전) 345kV 신안성신수원T/L 피뢰기 설치공사(No.2~11) 시 No.2~11 병가선로 안전이격확보","2018-07-08 07:00","2018-07-08 18:00","2018-07-08 07:00","2018-07-08 18:00","당일",null,null,null,201805140078]
[24,"경기","성남","신안성신수원#1 T/L","345kV 신안성신수원T/L 피뢰기 설치(No.2~11)","345kV 신안성신수원T/L 피뢰기 설치공사(No.2~11)","2018-07-08 07:00","2018-07-08 18:00","2018-07-08 07:00","2018-07-08 18:00","당일",null,null,null,201805140079]
[25,"경기","성남","신용인S/S #3 M.Tr A","신용인S/S 7500,7572 하자점검, 6344 조작시험","신용인S/S 7500,7572 하자점검, 6344 조작시험","2018-07-05 09:00","2018-07-05 18:00","취소","취소","당일",null,null,null,201805110287]
[26,"경기","성남","신안성신용인#1 T/L","신용인S/S 신안성-신용인#1T/L 7471,7400 하자점검","신용인S/S 신안성-신용인#1T/L LA 대체, 7471,7400 하자점검","2018-07-10 09:00","2018-07-10 18:00","2018-07-10 09:00","2018-07-10 18:00","당일",null,null,null,201805110291]
[27,"경기","성남","신용인S/S #2 M.Tr A","신용인S/S #2M.Tr, 1,3차 LA, CVT 보통점검 등","신용인S/S #2M.Tr, 1,3차 LA, CVT 보통점검, 7472 하자점검, 6244 조작시험","2018-07-12 09:00","2018-07-12 18:00","취소","취소","당일",null,null,null,201805110294]
[28,"경기","직할","화성S/S #1M.Tr A","18년 직할 변전협력회사 총액공사","화성S/S #1M.Tr 7172조작, 2차 GIS 조작, 1차 LA 교체","2018-07-10 10:00","2018-07-11 18:00","2018-07-10 10:00","2018-07-11 18:00","연속",null,null,null,201805140118]
[29,"경기","직할","화성신안산 T/L","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 75-76 SEC GIS 대체관련 #76모선 무부하가압","2018-07-14 10:00","2018-07-15 18:00","2018-07-14 10:00","2018-07-15 18:00","연속",null,null,null,201805170211]
[30,"경기","직할","화성S/S 345kV #76 BUS","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 #76모선 분리","2018-07-01 09:00","2018-07-15 18:00","2018-07-01 09:00","2018-07-15 18:00","연속",null,null,null,201805020010]
[31,"대전충남","서산","신서산S/S 신서산-아산#1T/L CB (7972)","신서산 345kV 7152 DS 가스누기 발생 관련 점검","신서산 345kV 7152 DS 가스누기 발생 관련 점검","2018-07-02 09:00","2018-07-04 18:00","취소","취소","당일",null,null,null,201805170045]
[32,"대전충남","서산","태안T/P 75-76-0 SEC CB (75-76-0)","18년 서산PO 변전협력회사 총액공사","태안화력 345kV 75-76-0 SEC GIS 초기점검","2018-07-03 09:00","2018-07-03 18:00","2018-07-03 09:00","2018-07-03 18:00","당일",null,null,null,201805140147]
[33,"대전충남","서산","태안T/P 70-71-0 SEC CB (70-71-0)","18년 서산PO 변전협력회사 총액공사","태안화력 345kV 70-71-0 SEC GIS 초기점검","2018-07-02 09:00","2018-07-02 18:00","2018-07-02 09:00","2018-07-02 18:00","당일",null,null,null,201805140145]
[34,"전북","군산","새만금S/S 군산-새만금#1 T/L GIS","새만금S/S 345kV #1Sh.R 설치 공사","- Sh.R(345kV 200MVAR) * 1BANK - GIS(362kV 4000A) * 2CB - 기타부대공사 * 1식","2018-07-13 09:00","2018-07-14 18:00","2018-07-13 09:00","2018-07-14 18:00","연속",null,null,null,201805160111]
[35,"전북","군산","새만금S/S 345kV #1BUS","새만금S/S 345kV Sh.R 설치공사","- Sh.R(345kV 200MVAR) * 1BANK - GIS(362kV 4000A) * 2CB - 기타 부대 공사 * 1식","2018-07-13 09:00","2018-07-14 18:00","2018-07-13 09:00","2018-07-14 18:00","연속",null,null,null,201805160112]
[36,"전북","직할","북경남무주양수 T/L","154kV북대구-관음 등 11개T/L 항공장애표지 설치공사","345kV북경남-무주양수T/L No.136~137 등 16경간 항공장애구 설치","2018-07-09 09:00","2018-07-12 18:00","2018-07-09 09:00","2018-07-12 18:00","연속",null,null,null,201805090126]
[37,"전북","직할","신남원광양#2 T/L","345kV 신남원-광양T/L 안전이격 확보공사","가. 철탑철거 : 2기 [No.214(T-14), No.216(F-21)] 나. 철탑설치 : 2기 [No.214(C2-26), No.216(SF-36)] 다. 전력선 교체 : 1.790km [ACSR 480㎟ x 2B] , 12가닥 라. 가선로 구성 : 가철탑 1기 (No.216)","2018-07-05 07:00","2018-07-14 18:00","2018-07-05 07:00","2018-07-14 18:00","연속",null,null,null,201804200079]
[38,"광주전남","목포","신남원한빛NP#1 T/L","345kV 신김제-한빛NP 등 4개T/L 지장송전선로 이설공사","345kV 신남원-한빛NP T/L 12호 철탑이설 및 11-16호 전력선 교체","2018-07-08 09:00","2018-07-21 18:00","취소","취소","연속",null,null,null,201805040197]
[39,"광주전남","목포","신남원한빛NP#2 T/L","345kV 신김제-한빛NP 등 4개T/L 지장송전선로 이설공사","345kV 신남원-한빛NP T/L 12호 철탑이설 및 11-16호 전력선 교체","2018-07-22 09:00","2018-07-30 18:00","취소","취소","연속",null,null,null,201805040201]
[40,"광주전남","목포","신남원한빛NP#2 T/L","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","○ 362kV GIS(4000A,40kA) X 9CCT 철거 ○ 362kV GIS(6300A,63kA) X 9CCT 설치 ○ 기타부대공사 X 1식","2018-07-30 09:00","2018-09-21 18:00","취소","취소","연속",null,null,null,201805170162]
[41,"광주전남","목포","한빛2NP한빛3NP #4T/L","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","○ 362kV GIS(4000A,40kA) X 9CCT 철거 ○ 362kV GIS(6300A,63kA) X 9CCT 설치 ○ 기타부대공사 X 1식","2018-07-30 09:00","2018-09-21 18:00","취소","취소","연속",null,null,null,201805170159]
[42,"광주전남","목포","한빛1NP한빛2NP #2T/L","345kV한빛연락#2T/L(362kV GIS 보통점검)","362kV GIS 보통점검","2018-07-16 09:00","2018-07-18 18:00","취소","취소","연속",null,null,"신뢰도개선",201804020145]
[43,"광주전남","목포","신남원한빛NP#2 T/L","345kV 신김제-한빛NP 등 4개T/L 지장송전선로 이설공사","345kV 신남원-한빛NP T/L 12호 철탑이설 및 11-16호 전력선 교체","2018-07-01 09:00","2018-07-07 18:00","취소","취소","연속",null,null,null,201805040195]
[44,"대구","경산","신경산S/S #2 M.Tr A","신경산S/S #2M.Tr 휴전","170kV GIS 초기점검 NGK부싱 절연유 가스분석","2018-07-04 09:00","2018-07-04 18:00","2018-07-04 09:00","2018-07-04 18:00","당일",null,null,null,201805090391]
[45,"대구","경산","신경산S/S #3 M.Tr A","신경산S/S #3M.Tr 휴전","170kV GIS 초기점검 NGK부싱 절연유 가스분석","2018-07-05 09:00","2018-07-05 18:00","2018-07-05 09:00","2018-07-05 18:00","당일",null,null,null,201805090392]
[46,"대구","경산","신경산S/S #1 M.Tr A","신경산S/S #1M.Tr 휴전","NGK부싱 절연유 가스분석","2018-07-06 09:00","2018-07-06 13:00","2018-07-06 09:00","2018-07-06 13:00","당일",null,null,null,201805090389]
[47,"대구","경산","신경산S/S #4 M.Tr A","신경산S/S #4M.Tr 휴전","NGK부싱 절연유 가스분석","2018-07-06 13:00","2018-07-06 18:00","2018-07-06 13:00","2018-07-06 18:00","당일",null,null,null,201805090390]
[48,"대구","달성","고령S/S 345kV #1 BUS","345kV 고령S/S Sh.R 설치공사","345kV 고령S/S Sh.R 설치공사","2018-07-07 09:00","2018-07-10 18:00","취소","취소","연속",null,null,null,201805210055]
[49,"대구","달성","고령S/S #4 M.Tr A","달성전력지사 변전총액공사","1,2,3차 차단기 동작시험, 3차LA교체,PT보통점검","2018-07-13 09:00","2018-07-13 18:00","2018-07-13 09:00","2018-07-13 18:00","당일",null,null,null,201805150178]
[50,"대구","칠곡","북대구S/S 신포항북대구T/L CB (7172)","북대구S/S 신포항북대구T/L CB CB 7172 장기미동작점검","북대구S/S 신포항북대구T/L CB CB 7172 장기미동작점검","2018-07-09 09:30","2018-07-09 13:00","2018-07-09 09:30","2018-07-09 13:00","당일",null,null,null,201805090274]
[51,"대구","칠곡","북대구S/S #2 M.Tr A","북대구S/S #2M.Tr 휴전작업","북대구S/S #2M.Tr 휴전작업","2018-07-12 09:30","2018-07-12 18:00","2018-07-12 09:30","2018-07-12 18:00","당일",null,null,null,201805090278]
[52,"대구","칠곡","북대구S/S #1 M.Tr A","북대구S/S #1M.Tr 휴전작업","북대구S/S #1M.Tr 휴전작업","2018-07-11 09:30","2018-07-11 18:00","2018-07-11 09:30","2018-07-11 18:00","당일",null,null,null,201805090277]
[53,"대구","칠곡","북대구S/S 북대구-선산T/L CB (7272)","북대구S/S 북대구선산T/L CB 7272 장기미동작점검","북대구S/S 북대구선산T/L CB 7272 장기미동작점검","2018-07-09 13:00","2018-07-09 15:30","2018-07-09 13:00","2018-07-09 15:30","당일",null,null,null,201805090283]
[54,"대구","칠곡","서대구S/S 서대구-고령#2T/L CB (7271)","서대구S/S 서대구고령#2T/L 7271 GCB 장기미동작점검","서대구S/S 서대구고령#2T/L 7271 GCB 장기미동작점검","2018-07-03 09:30","2018-07-03 14:00","2018-07-03 09:30","2018-07-03 14:00","당일",null,null,null,201805090265]
[55,"대구","칠곡","서대구S/S 345kV #2 BUS","서대구S/S 345kV #2 BUS 휴전","서대구S/S 345kV #2 BUS 휴전","2018-07-20 09:30","2018-07-20 18:00","취소","취소","당일",null,null,"신뢰도개선",201805090281]
[56,"대구","칠곡","서대구S/S 345kV #1 BUS","서대구S/S 345kV #1 BUS 휴전","서대구S/S 345kV #1 BUS 휴전","2018-07-19 09:30","2018-07-19 18:00","취소","취소","당일",null,null,"신뢰도개선",201805090280]
[57,"대구","칠곡","서대구S/S 서대구-고령#2T/L-TIE CB (7200)","서대구S/S 서대구-고령#2T/L-TIE 7200 CB 장기미동작점검","서대구S/S 서대구-고령#2T/L-TIE 7200 CB 장기미동작점검","2018-07-03 14:00","2018-07-03 18:00","2018-07-03 14:00","2018-07-03 18:00","당일",null,null,null,201805090266]
[58,"대구","포항","신포항S/S #4 M.Tr A","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 8DS, T-BUS 철거 등","2018-07-25 08:00","2018-07-26 18:00","2018-07-25 08:00","2018-07-26 18:00","연속",null,null,null,201804050027]
[59,"대구","포항","신포항S/S #3 M.Tr A","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 8DS, T-BUS 철거 등","2018-07-23 08:00","2018-07-24 18:00","2018-07-23 08:00","2018-07-24 18:00","연속",null,null,null,201804050026]
[60,"대구","포항","신포항S/S #2 M.Tr A","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 8DS, T-BUS 철거 등","2018-07-16 08:00","2018-07-17 18:00","2018-07-16 08:00","2018-07-17 18:00","연속",null,null,null,201804050025]
[61,"대구","포항","신포항S/S #1 M.Tr A","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 8DS, T-BUS 철거 등","2018-07-11 08:00","2018-07-12 18:00","2018-07-11 08:00","2018-07-12 18:00","연속",null,null,null,201804050024]
[62,"대구","포항","신포항북대구 T/L","345kV 신포항-북대구T/L 지장선로이설공사","지장송전선로 이설 - 지지물 : 125,126호 - 구 간 : 118~132호 - 임시선로 구성 후 본선로 구성","2018-07-04 07:00","2018-07-16 18:00","2018-07-04 07:00","2018-07-16 18:00","연속",null,null,null,201805180020]
[63,"대구","포항","울주월성NP#1 T/L","2018년 포항전력지사 보통점검","울주월성NP#1 T/L PT A,B,C상 보통점검 7571, 7500 CB 보통점검","2018-07-02 09:30","2018-07-03 18:00","2018-07-02 09:30","2018-07-03 18:00","연속",null,null,null,201805090062]
[64,"대구","포항","월성2N/P 70-71-0 SEC CB (70-71-0)","2018년 포항전력지사 보통점검","월성2N/P 70-71-0 SEC CB 보통점검","2018-07-04 09:30","2018-07-04 18:00","취소","취소","당일",null,null,null,201805090063]
[65,"대구","포항","월성2N/P#1SS Tr 1차-#3SS Tr 1차 CB (7600)","2018년 포항전력지사 보통점검","월성2N/P#1SS Tr 1차-#3SS Tr 1차(7600) CB 보통점검","2018-07-11 09:30","2018-07-11 18:00","2018-07-09 09:30","2018-07-09 18:00","당일",null,null,null,201805090073]
[66,"대구","포항","월성2N/P #3 SS Tr 1차 CB (7672)","2018년 포항전력지사 보통점검","월성2N/P #3 SS Tr 1차(7672) CB 보통점검","2018-07-12 09:30","2018-07-12 18:00","2018-07-09 09:30","2018-07-09 18:00","당일",null,null,null,201805090074]
[67,"대구","포항","월성2N/P 75-76-0 SEC CB (75-76-0)","2018년 포항전력지사 보통점검","월성2N/P 75-76-0 SEC CB 보통점검","2018-07-05 09:30","2018-07-05 18:00","취소","취소","당일",null,null,null,201805090064]
[68,"경북","구미","선산S/S #3 M.Tr A","선산S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 공사 - M.Tr 2차 상부모선 이설작업","2018-07-09 08:00","2018-07-12 18:00","2018-07-09 08:00","2018-07-12 18:00","연속",null,null,null,201805150115]
[69,"경북","구미","선산S/S #2 M.Tr A","선산S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 공사 - M.Tr 2차 상부모선 이설작업","2018-07-02 08:00","2018-07-05 18:00","2018-07-02 08:00","2018-07-05 18:00","연속",null,null,null,201805150109]
[70,"경북","영주","한울2N/P #3-1 SS.Tr 1차 CB (7572)","한울2발S/Y 362kV GIS 기기점검","한울2발S/Y 362kV 7572 GIS 하자점검","2018-07-03 09:30","2018-07-03 14:00","2018-07-03 09:30","2018-07-03 14:00","당일",null,null,null,201805090303]
[71,"경북","영주","한울2N/P #3-2 SS.Tr 1차 CB (7672)","한울2발S/Y 362kV GIS 기기점검","한울2발S/Y 362kV 7672 GIS 하자점검","2018-07-03 14:00","2018-07-03 18:00","2018-07-03 14:00","2018-07-03 18:00","당일",null,null,null,201805090305]
[72,"부산울산","동부산","신양산S/S #2 M.Tr A","신양산S/S 362kV GIS 조작시험","1. 신양산S/S 362kV 7372GIS 조작시험 2. [병행] 154kV 6244GCB 조작시험","2018-07-04 09:30","2018-07-04 14:00","2018-07-04 09:30","2018-07-04 14:00","당일",null,null,null,201805140004]
[73,"부산울산","동부산","신양산S/S #1 M.Tr A","신양산S/S 362kV GIS 보통점검","1. 신양산S/S 362kV 7172GIS 보통점검(#1M.Tr) 2. [병행] 154kV 6144GCB 조작시험 3. [병행] 23kV VCB 조작시험 4. [병행] #1-1,2Sh.R 초기점검","2018-07-03 09:30","2018-07-03 18:00","2018-07-03 09:30","2018-07-03 18:00","당일",null,null,null,201805140003]
[74,"부산울산","북부산","신양산북부산#1 T/L","345kV 북부산S/S 차단기용량대체공사","시험가압선로(71BAY 증설 75BUS 연결분)","2018-07-01 18:00","2018-07-02 18:00","2018-07-01 18:00","2018-07-02 18:00","연속",null,null,null,201805140083]
[75,"부산울산","북부산","북부산신울산#1 T/L","345kV 북부산S/S 차단기용량대체공사","시험가압선로(71BAY 증설 70BUS 연결분)","2018-07-10 18:00","2018-07-11 18:00","2018-07-10 18:00","2018-07-11 18:00","연속",null,null,null,201805140084]
[76,"부산울산","북부산","북부산S/S 345kV #70 BUS","345kV 북부산S/S 차단기용량대체공사","1. 모선연결 작업(74-71BAY : 71BAY 증설연결분) , 2. 71BAY C/H 연결 GIB 조립","2018-07-03 08:00","2018-07-11 18:00","2018-07-03 08:00","2018-07-11 18:00","연속",null,null,null,201801080324]
[77,"부산울산","울산","북부산울산TP T/L","345kV 신울산복합-북부산T/L 건설공사","○ 345kV 신울산복합-북부산T/L 건설 가선로 구성관련 안전이격확보 - 구간 : 기설 No.3 ~ 5구간","2018-07-11 07:00","2018-07-12 19:00","2018-07-07 07:00","2018-07-09 19:00","매일",null,null,null,201805110192]
[78,"부산울산","울산","울주고리NP#1 T/L","345kV 울주-고리NPT/L 67~68호 지장철탑이설공사","지장철탑이설 본선로 구성, 구간: 65~68호, 철탑설치: 67-1호 할입","2018-07-04 08:00","2018-07-08 18:00","2018-07-18 08:00","2018-07-22 18:00","연속",null,null,null,201805080191]
[79,"경남","진주","하동T/P TIE-#4 M.Tr 1차 CB (7400)","하동T/P TIE-#4M.Tr 1차 CB(7400) 개폐장치 조작시험","하동T/P TIE-#4M.Tr 1차 CB(7400) 개폐장치 조작시험 -하동T/P 4호기 정지기간 : 05.08 ~ 07.18","2018-07-03 09:30","2018-07-03 14:00","2018-07-03 09:30","2018-07-03 14:00","당일",null,null,null,201805030118]
[80,"경남","진주","하동T/P #4 M.Tr 1차 CB (7472)","하동T/P #4M.Tr 1차 CB(7472) 개폐장치 조작시험","하동T/P #4M.Tr 1차 CB(7472) 개폐장치 조작시험 -하동T/P 4호기 정지기간 : 05.08 ~ 07.18","2018-07-03 14:00","2018-07-03 18:30","2018-07-03 14:00","2018-07-03 18:30","당일",null,null,null,201805030119]
[81,"경남","함안","신마산신김해#2 T/L","345kV 신마산-신김해 #2T/L 피뢰기 설치공사","송전선로용 피뢰기 설치 : 신마산-신김해 #2T/L 62호 (1기)","2018-07-02 09:00","2018-07-02 13:00","2018-07-02 09:00","2018-07-02 13:00","당일",null,null,null,201805080019]
[82,"경남","함안","신마산신김해#1 T/L","345kV 신마산S/S 용량부족차단기 대체공사","#2BUS 임시모선 연결 후 시험가압 6Hr","2018-07-15 12:00","2018-07-15 18:00","2018-07-15 12:00","2018-07-15 18:00","당일",null,null,null,201805140105]
[83,"경남","함안","신마산S/S 345kV #2 BUS","345kV 신마산S/S 용량부족차단기 대체공사","#2BUS 임시모선 설치","2018-07-14 09:00","2018-07-15 18:00","2018-07-14 09:00","2018-07-15 18:00","연속",null,null,null,201805140097]
[84,"경남","함안","신마산S/S #1 M.Tr A","345kV 신마산S/S 용량부족차단기 대체공사","#1M.Tr측 전력구 시공관련 안전이격거리 확보(가시설설치 1차 해체)","2018-07-12 09:30","2018-07-13 18:00","2018-07-12 09:30","2018-07-13 18:00","연속",null,null,null,201805140100]
[85,"경남","함안","신마산신김해#2 T/L","345kV 신마산S/S 용량부족차단기 대체공사","#1BUS 임시모선 연결 후 시험가압 6Hr","2018-07-08 12:00","2018-07-08 18:00","2018-07-08 12:00","2018-07-08 18:00","당일",null,null,null,201805140104]
[86,"경남","함안","신마산S/S 345kV #1 BUS","345kV 신마산S/S 용량부족차단기 대체공사","#1BUS 임시모선 설치","2018-07-07 09:00","2018-07-08 18:00","2018-07-07 09:00","2018-07-08 18:00","연속",null,null,null,201805140094]

{"sheet":"154송부","index":2,"n_rows":127,"n_cols":16,"rows_kept":127,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"\"2018년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2018년도 7월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","동서울","동서울S/S 66-67-0 SEC CB","170kV GCB 정밀점검","170kV GCB 정밀점검","2018-07-04 09:00","2018-07-05 18:00","2018-07-04 09:00","2018-07-05 18:00","연속",null,null,null,201805110148]
[2,"남서울","동서울","동서울가락#2 T/L","170kV GCB 정밀점검","170kV GCB 정밀점검","2018-07-02 09:00","2018-07-03 18:00","2018-07-02 09:00","2018-07-03 18:00","연속",null,null,null,201805110147]
[3,"남서울","동서울","가락수서#2 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2018-07-04 14:00","2018-07-04 18:00","취소","취소","당일",null,null,null,201805110144]
[4,"남서울","동서울","가락수서#1 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2018-07-04 09:00","2018-07-04 14:00","취소","취소","당일",null,null,null,201805110142]
[5,"남서울","영등포","신광명소래 T/L","영서S/S 154kV 이하 옥외철구 GIS화 공사","가공-GIS 접속, 보호반이설","2018-07-09 08:00","2018-07-13 18:00","2018-07-02 08:00","2018-07-06 18:00","연속",null,null,null,201803200057]
[6,"인천","김포","경서양촌#2 T/L","경서S/S 154kV 경서-양촌#2T/L GIS 보통점검","경서S/S 154kV 경서-양촌#2T/L GIS 보통점검","2018-07-03 09:00","2018-07-03 18:00","2018-07-03 09:00","2018-07-03 18:00","당일",null,null,null,201805150066]
[7,"인천","시흥","신시흥북시화#1 T/L","154kV 신시흥-북시화#1T/L 애자교체공사","154kV 신시흥-북시화#1T/L 애자교체공사","2018-07-16 08:00","2018-07-16 18:00","2018-07-20 08:00","2018-07-20 18:00","당일",null,null,null,201805180118]
[8,"인천","인천","관교만수 T/L","관교만수T/L 병행지선 보강 공사","지중선로 병행지선 설치","2018-07-08 09:00","2018-07-08 14:00","2018-07-08 09:00","2018-07-08 14:00","당일",null,null,null,201804090157]
[9,"인천","인천","신가좌신현#2 T/L","154kV 신가좌-주안 등 2개 T/L 자기애관교체공사","자기애관 교체를 통한 설비 2차 확산피해 방지","2018-07-01 09:00","2018-07-03 18:00","2018-07-01 09:00","2018-07-03 18:00","연속",null,null,null,201803160117]
[10,"인천","인천","학익연수#2 T/L","2018년 인천전력지사 170kV GIS 정밀점검공사","학익S/S 학익연수#2T/L GIS 정밀점검","2018-07-23 09:00","2018-07-25 18:00","2018-07-23 09:00","2018-07-25 18:00","연속",null,null,null,201805090372]
[11,"인천","인천","학익연수#1 T/L","2018년 인천전력지사 170kV GIS 정밀점검공사","학익S/S 학익연수#1T/L GIS 정밀점검","2018-07-16 09:00","2018-07-18 18:00","2018-07-16 09:00","2018-07-18 18:00","연속",null,null,null,201805090373]
[12,"인천","인천","학익S/S 154kV #1 BUS TIE GIS","2018년 인천전력지사 170kV GIS 정밀점검공사","학익S/S #1BUS TIE(6100) GIS 정밀점검","2018-07-09 09:00","2018-07-11 18:00","2018-07-09 09:00","2018-07-11 18:00","연속",null,null,null,201805090371]
[13,"경기북부","고양","양주고양#2 T/L","No.26~27 선하지 공사현장 교각 Coping Form 철거","No.26~27 선하지 서울-문산 고속도로 건설공사 현장 교각 Coping Form 철거 시 크레인 사용으로 인한 전력선 안전이격거리 확보","2018-07-02 07:00","2018-07-02 18:00","2018-07-02 07:00","2018-07-02 18:00","당일",null,null,null,201805110266]
[14,"경기북부","구리","덕소팔당HP청평HP T/L","청평수력S/Y #5M.Tr 철거공사","○#5M.Tr 철거 ○23kV VCB 및 DS 철거 ○154kV GCB 및 DS철거 ○23kV 옥외철구 철거 ○기타 부속자재 철거","2018-07-02 09:00","2018-07-04 18:00","2018-07-16 09:00","2018-07-20 18:00","연속",null,null,null,201805110007]
[15,"경기북부","구리","청평H/P 154kV #2 BUS","청평수력S/Y #5M.Tr 철거공사","○#5M.Tr 철거 ○23kV VCB 및 DS 철거 ○154kV GCB 및 DS철거 ○23kV 옥외철구 철거 ○기타 부속자재 철거ㅓ","2018-07-02 09:00","2018-07-04 18:00","2018-07-16 09:00","2018-07-20 18:00","연속",null,null,null,201805110008]
[16,"경기북부","구리","청평H/P 154kV #1 BUS TIE CB","청평수력S/Y #5M.Tr 철거공사","○#5M.Tr 철거 ○23kV VCB 및 DS 철거 ○154kV GCB 및 DS철거 ○23kV 옥외철구 철거 ○기타 부속자재 철거","2018-07-02 09:00","2018-07-04 18:00","2018-07-16 09:00","2018-07-20 18:00","연속",null,null,null,201805110006]
[17,"경기북부","직할","신포천동두천#1 T/L","'18년 170kV GIS 정밀점검","GIS 정밀점검","2018-07-02 09:00","2018-07-03 18:00","2018-07-02 09:00","2018-07-03 18:00","연속",null,null,null,201804160019]
[18,"경기북부","직할","신포천동두천#2 T/L","'18년 170kV GIS 정밀점검","GIS 정밀점검","2018-07-04 09:00","2018-07-05 18:00","2018-07-04 09:00","2018-07-05 18:00","연속",null,null,null,201804160020]
[19,"경기","군포","반월시화#2 T/L","반월S/S 154kV 현대화공사","- 154kV CVT 이설","2018-07-26 09:30","2018-07-26 18:00","2018-07-26 09:30","2018-07-26 18:00","당일",null,null,null,201805110240]
[20,"경기","군포","반월시화#1 T/L","반월S/S 154kV 현대화공사","- 154kV CVT 이설","2018-07-25 09:30","2018-07-25 18:00","2018-07-25 09:30","2018-07-25 18:00","당일",null,null,null,201805110239]
[21,"경기","군포","신시흥시화#1 T/L","시화변전소 신시흥시화1TL GIS 대체공사","시화변전소 신시흥시화1TL 노후 GIS 대체작업","2018-07-02 09:00","2018-07-19 18:00","2018-07-02 09:00","2018-07-19 18:00","연속",null,null,null,201804050387]
[22,"경기","군포","반월시화#1 T/L","시화변전소 신시흥시화1TL GIS 대체관련 무부하 가압","시화변전소 신시흥시화1TL GIS 대체관련 24H 무부하 가압 시행","2018-07-10 09:00","2018-07-11 18:00","2018-07-10 09:00","2018-07-11 18:00","연속",null,null,null,201804050390]
[23,"경기","군포","반월시화#2 T/L","154kV 신시흥-시화#1T/L 애자교체공사(병가선로)","154kV 신시흥-시화#1T/L 애자교체공사(병가선로) -반월시화#2(상),신시흥시화#1(하)","2018-07-17 08:00","2018-07-17 18:00","2018-07-17 08:00","2018-07-17 18:00","당일",null,null,null,201805180119]
[24,"경기","성남","신성남서판교 #3 T/L","신성남-서판교#3T/L 보호반 성능개선","신성남-서판교#3T/L 세니온제 154kV 단거리송전선로 보호반 성능개선차","2018-07-02 09:00","2018-07-02 18:00","2018-07-02 09:00","2018-07-02 18:00","당일",null,null,null,201805020012]
[25,"경기","성남","신봉수지#1 T/L","154kV 신봉-수지#1T/L 조립식접속함 교체공사","유사고장예방 R-Type PMJ 교체 - 대상선로 : 154kV 신봉-수지#1T/L 36상","2018-07-13 08:00","2018-07-27 18:00","2018-07-13 08:00","2018-07-27 18:00","연속",null,null,null,201805140174]
[26,"경기","성남","신수원S/S 154kV #62 BUS","신수원S/S 345kV 용량부족 GIS 대체공사","75Bay(#3M.Tr) GIS 무부하 가압","2018-07-29 10:00","2018-07-31 18:00","취소","취소","매일",null,null,null,201804130088]
[27,"경기","직할","화성S/S 154kV #2 BUS TIE GIS","18년 직할 변전협력회사 총액공사","화성S/S 6200 GIS 보통","2018-07-04 10:00","2018-07-04 18:00","2018-07-04 10:00","2018-07-04 18:00","당일",null,null,null,201805140114]
[28,"경기","직할","화성S/S 60-61 SEC GIS","18년 직할 변전협력회사 총액공사","화성S/S 60-61 GIS 보통","2018-07-05 10:00","2018-07-05 18:00","2018-07-05 10:00","2018-07-05 18:00","당일",null,null,null,201805140116]
[29,"경기","직할","화성남양#1 T/L","18년 직할 변전협력회사 총액공사","화성S/S 화성남양#1T/L GIS, PT, LA 보통점검","2018-07-07 09:00","2018-07-07 18:00","2018-07-07 09:00","2018-07-07 18:00","당일",null,null,null,201805140133]
[30,"경기","직할","화성S/S 154kV #67 BUS","18년 직할 154kV GCB/GIS 정밀점검공사","화성S/S #64M.Tr 1차 GIS 정밀점검공사(무부하가압)","2018-07-11 09:00","2018-07-11 18:00","2018-07-11 09:00","2018-07-11 18:00","당일",null,null,null,201805140098]
[31,"경기","직할","화성S/S 154kV #60 BUS","18년 직할 154kV GCB/GIS 정밀점검공사","화성S/S #61S.C 1차 GIS 정밀점검공사(모선DS작업)","2018-07-12 09:00","2018-07-13 14:00","2018-07-12 09:00","2018-07-13 14:00","매일",null,null,null,201805140096]
[32,"경기","직할","화성S/S 154kV #1 BUS TIE GIS","18년 직할 변전협력회사 총액공사","화성S/S 6100 GIS 보통","2018-07-03 10:00","2018-07-03 18:00","2018-07-03 10:00","2018-07-03 18:00","당일",null,null,null,201805140113]
[33,"경기","직할","화성S/S 154kV #65 BUS","18년 직할 154kV GCB/GIS 정밀점검공사","화성S/S #61Sh.C GIS 정밀점검공사(모선DS작업)","2018-07-13 14:00","2018-07-14 18:00","2018-07-13 14:00","2018-07-14 18:00","당일",null,null,null,201805140092]
[34,"경기","직할","화성남양#2 T/L","18년 직할 변전협력회사 총액공사","화성S/S 화성남양#2T/L GIS, PT, LA 보통점검","2018-07-14 09:00","2018-07-14 18:00","2018-07-14 09:00","2018-07-14 18:00","당일",null,null,null,201805140135]
[35,"경기","직할","화성S/S 65-66 SEC GIS","18년 직할 변전협력회사 총액공사","화성S/S 65-66 GIS 보통","2018-07-06 10:00","2018-07-06 18:00","2018-07-06 10:00","2018-07-06 18:00","당일",null,null,null,201805140117]
[36,"경기","평택","고덕송탄 T/L","154kV 고덕분기 지중T/L 건설공사","ㅇ 공사구간 : 345kV 고덕S/S ~ 154kV 송탄진위T/L 분기점 ㅇ 선종 및 긍장 : 154kV XLPE 2,500SQ,. 4C - 4.0km","2018-07-10 08:00","2018-08-19 18:00","2018-07-10 08:00","2018-08-19 18:00","연속",null,null,null,201805140106]
[37,"경기","평택","서운안성#1 T/L","154kV 서운-안성T/L 전력선 교체공사","- 공사구간 : No.2-6 - 공사규모 : 전력선 14가닥 교체(1.059km)","2018-07-06 07:00","2018-07-08 18:00","2018-07-06 07:00","2018-07-08 18:00","연속",null,null,null,201805170186]
[38,"경기","평택","서운안성#2 T/L","안성S/S 170kV GIS 용량대체공사","#5M.Tr 및 #1Sh.C 무부하 가압 용","2018-07-02 10:00","2018-07-03 18:00","2018-07-02 10:00","2018-07-03 18:00","매일",null,null,null,201805080096]
[39,"경기","평택","서안성안성#1 T/L","154kV 서운-안성T/L 전력선 교체공사(안전확보)","- 공사구간 : No.2-6 (서안성-안성 병가) - 공사규모 : 전력선 14가닥 교체(1.059km)","2018-07-06 07:00","2018-07-08 18:00","2018-07-06 07:00","2018-07-08 18:00","연속",null,null,null,201805170187]
[40,"경기","평택","오성C/C 154kV #2 BUS TIE GIS","오성복합S/Y 154kV #2BUS TIE GIS 보통점검","오성복합S/Y 154kV #2BUS TIE GIS 보통점검","2018-07-06 10:00","2018-07-06 18:00","2018-07-06 10:00","2018-07-06 18:00","당일",null,null,null,201805100279]
[41,"경기","평택","오성C/C #60-61 BUS SEC GIS","오성복합S/Y 154kV 60-61 SEC GIS 보통점검","오성복합S/Y 154kV 60-61 SEC GIS 보통점검","2018-07-12 10:00","2018-07-12 18:00","2018-07-12 10:00","2018-07-12 18:00","당일",null,null,null,201805100280]
[42,"경기","평택","오성C/C #65-66 BUS SEC GIS","오성복합S/Y 154kV 65-66 SEC GIS 보통점검","오성복합S/Y 154kV 65-66 SEC GIS 보통점검","2018-07-13 10:00","2018-07-13 18:00","2018-07-13 10:00","2018-07-13 18:00","당일",null,null,null,201805100281]
[43,"경기","평택","오성C/C 154kV #1 BUS TIE GIS","오성복합S/Y 154kV #1BUS TIE GIS 보통점검","오성복합S/Y 154kV #1BUS TIE GIS 보통점검","2018-07-05 10:00","2018-07-05 18:00","2018-07-05 10:00","2018-07-05 18:00","당일",null,null,null,201805100278]
[44,"강원","강릉","강릉북강릉#1 T/L","154kV 강릉S/S 인출 송전선로 지중화공사","- (신설)No.2~강릉S/S간 송전선로 인출구간 지중화","2018-07-23 09:00","2018-08-27 18:00","2018-07-28 09:00","2018-08-27 18:00","연속",null,null,null,201805080028]
[45,"강원","원주","홍천상남#1 T/L","2018년 원주전력 변전협력회사 총액공사","상남S/S 피뢰기 보통, GIS 절연볼트 교체","2018-07-04 10:00","2018-07-04 17:00","2018-07-04 10:00","2018-07-04 17:00","당일",null,null,null,201805090158]
[46,"강원","원주","홍천상남#2 T/L","2018년 원주전력 변전협력회사 총액공사","상남S/S 피뢰기 보통, GIS 절연볼트 교체","2018-07-05 10:00","2018-07-05 17:00","2018-07-05 10:00","2018-07-05 17:00","당일",null,null,null,201805090159]
[47,"강원","태백","태백고한 T/L","태백전력지사 변전정비회사 총액공사","고한S/S 태백-고한T/L GIS, 피뢰기 보통점검 태백S/S 태백-고한T/L GIS 조작시험","2018-07-02 10:00","2018-07-02 18:00","2018-07-02 10:00","2018-07-02 18:00","당일",null,null,null,201805040196]
[48,"강원","태백","제천영월#2 T/L","태백전력지사 변전정비회사 총액공사","영월S/S 제천-영월 #2T/L GIS 조작시험","2018-07-04 14:00","2018-07-04 18:00","2018-07-04 14:00","2018-07-04 18:00","당일",null,null,null,201805040205]
[49,"강원","태백","제천영월#1 T/L","태백전력지사 변전정비회사 총액공사","영월S/S 제천-영월 #1T/L GIS 조작시험","2018-07-04 10:00","2018-07-04 14:00","2018-07-04 10:00","2018-07-04 14:00","당일",null,null,null,201805040203]
[50,"강원","태백","정암풍력 T/L CB","태백전력지사 변전정비회사 총액공사","태백S/S 154kV 정암풍력 #1T/L GIS 하자점검","2018-07-03 10:00","2018-07-03 14:00","2018-07-03 10:00","2018-07-03 14:00","당일",null,null,null,201805040200]
[51,"강원","태백","태백삼척GP#1 T/L","태백전력지사 변전정비회사 총액공사","태백S/S 154kV 태백-삼척GP #1T/L GIS 석포제련 고객요청","2018-07-05 09:00","2018-07-07 18:00","2018-07-05 09:00","2018-07-07 18:00","매일",null,null,null,201805040208]
[52,"강원","태백","태백삼척GP#2 T/L","태백전력지사 변전정비회사 총액공사","태백S/S 154kV 태백-삼척 GP #1T/L GIS 석포제련 고객요청","2018-07-08 09:00","2018-07-15 18:00","2018-07-08 09:00","2018-07-15 18:00","매일",null,null,null,201805210018]
[53,"강원","태백","태백삼척GP#2 T/L","66kV 백산전철T/L 노후취약 지지물 교체 공사","66kV 백산전철T/L 노후취약 지지물 교체 공사 안전이격확보차 ","2018-07-26 08:00","2018-07-26 18:00","2018-07-26 08:00","2018-07-26 18:00","당일"]
[54,"강원","태백","도계태백 T/L","66kV 백산전철T/L 노후취약 지지물 교체 공사","66kV 백산전철T/L 노후취약 지지물 교체 공사 안전이격확보차 ","2018-07-26 08:00","2018-07-26 18:00","2018-07-26 08:00","2018-07-26 18:00","당일"]
[55,"대전충남","서산","태안T/P 154kV #1 BUS","태안화력 154kV 장기사용 GIS 대체공사","태안화력 154kV 장기사용 GIS(6483) 대체공사","2018-07-06 15:00","2018-07-13 18:00","2018-07-06 15:00","2018-07-13 18:00","매일",null,null,null,201804160263]
[56,"대전충남","아산","신온양한샘#2 T/L","154kV 신온양-한샘T/L 건설공사","가선로 구성(기설17~가철탑) #2T/L 가압","2018-07-26 07:00","2018-07-27 19:00","2018-07-26 07:00","2018-07-27 19:00","연속",null,null,null,201805110076]
[57,"대전충남","아산","신온양한샘#1 T/L","154kV 신온양-한샘T/L 건설공사","가선로 구성(기설17~가철탑~기설18)","2018-07-24 07:00","2018-07-25 19:00","2018-07-24 07:00","2018-07-25 19:00","연속",null,null,null,201805110068]
[58,"대전충남","아산","신온양한샘#1 T/L","154kV 신온양-한샘T/L 건설공사","가선로 구성(기설17~가철탑) #1T/L 가압","2018-07-28 07:00","2018-07-29 19:00","2018-07-28 07:00","2018-07-29 19:00","연속",null,null,null,201805110067]
[59,"전북","군산","동군산군산CC#2 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군산복합S/Y 동군산-군산복합 #2T/L 차단기 정밀점검","2018-07-07 09:00","2018-07-08 18:00","2018-07-07 09:00","2018-07-08 18:00","연속",null,null,null,201805160079]
[60,"전북","군산","군산이리#2 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 군산-이리 #2T/L 차단기 정밀점검","2018-07-16 09:00","2018-07-17 18:00","2018-07-16 09:00","2018-07-17 18:00","연속",null,null,null,201803200107]
[61,"전북","군산","군산영등#1 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 군산-영등 #1T/L 차단기 정밀점검","2018-07-18 09:00","2018-07-19 18:00","2018-07-18 09:00","2018-07-19 18:00","연속",null,null,null,201803200108]
[62,"전북","군산","군산영등#2 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 군산-영등 #2T/L 차단기 정밀점검","2018-07-23 09:00","2018-07-24 18:00","2018-07-23 09:00","2018-07-24 18:00","연속",null,null,null,201803200109]
[63,"전북","군산","군산S/S 154kV #61 BUS","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 61-62-0 BUS SEC 차단기 정밀점검(모선단로기 포함)","2018-07-25 09:00","2018-07-26 14:00","2018-07-25 09:00","2018-07-26 14:00","연속",null,null,null,201803200111]
[64,"전북","군산","군산S/S 61-62-0 SEC CB","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 61-62-0 BUS SEC 차단기 정밀점검(모선단로기 포함)","2018-07-25 09:00","2018-07-27 18:00","2018-07-25 09:00","2018-07-27 18:00","연속",null,null,null,201803200110]
[65,"전북","군산","군산동군산#1 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 61-62-0 BUS SEC 차단기 정밀점검(모선단로기 포함)","2018-07-26 12:00","2018-07-26 14:00","2018-07-26 12:00","2018-07-26 14:00","당일",null,null,null,201803200112]
[66,"전북","군산","군산S/S 154kV #62 BUS","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 61-62-0 BUS SEC 차단기 정밀점검(모선단로기 포함)","2018-07-26 14:00","2018-07-27 18:00","2018-07-26 14:00","2018-07-27 18:00","연속",null,null,null,201803200113]
[67,"전북","군산","군산동군산#2 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 61-62-0 BUS SEC 차단기 정밀점검(모선단로기 포함)","2018-07-27 16:00","2018-07-27 18:00","2018-07-27 16:00","2018-07-27 18:00","당일",null,null,null,201803200114]
[68,"전북","군산","군산S/S 66-67-0 SEC CB","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 66-67-0 BUS SEC 차단기 정밀점검(모선단로기 포함)","2018-07-30 09:00","2018-08-01 18:00","2018-07-30 09:00","2018-08-01 18:00","연속",null,null,null,201803200115]
[69,"전북","군산","군산S/S 154kV #66 BUS","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 66-67-0 BUS SEC 차단기 정밀점검(모선단로기 포함)","2018-07-30 09:00","2018-07-31 14:00","2018-07-30 09:00","2018-07-31 14:00","연속",null,null,null,201803200116]
[70,"전북","군산","군산동군산#1 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 66-67-0 BUS SEC 차단기 정밀점검(모선단로기 포함)","2018-07-31 12:00","2018-07-31 14:00","2018-07-31 12:00","2018-07-31 14:00","당일",null,null,null,201803200117]
[71,"전북","군산","군산S/S 154kV #67 BUS","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 66-67-0 BUS SEC 차단기 정밀점검(모선단로기 포함)","2018-07-31 14:00","2018-08-01 18:00","2018-07-31 14:00","2018-08-01 18:00","연속",null,null,null,201803200118]
[72,"전북","군산","군산이리#1 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 군산-이리 #1T/L 차단기 정밀점검","2018-07-12 09:00","2018-07-13 18:00","2018-07-12 09:00","2018-07-13 18:00","연속",null,null,null,201803200106]
[73,"전북","군산","군공소룡#1 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","소룡S/S 군공-소룡 #1T/L 차단기 정밀점검","2018-07-02 09:00","2018-07-03 18:00","2018-07-02 09:00","2018-07-03 18:00","연속",null,null,null,201803200079]
[74,"전북","군산","군공소룡#2 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","소룡S/S 군공-소룡 #2T/L 차단기 정밀점검","2018-07-04 09:00","2018-07-05 18:00","2018-07-04 09:00","2018-07-05 18:00","연속",null,null,null,201803200080]
[75,"전북","군산","팔봉봉동#1 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 팔봉-봉동 #1T/L 차단기 정밀점검","2018-07-02 09:00","2018-07-03 18:00","취소","취소","연속",null,null,null,201803200095]
[76,"전북","군산","팔봉봉동#2 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군공S/S 154kV 팔봉-봉동 #2T/L 차단기 정밀점검","2018-07-04 09:00","2018-07-05 18:00","취소","취소","연속",null,null,null,201803200096]
[77,"전북","김제","정주고창#2 T/L","154kV 정주-고창#2T/L 항공장애표시구설치공사","No.80~81, 81~82, 82~83, 85~86, 86~87, 87~88호 28EA","2018-07-02 08:00","2018-07-03 18:00","2018-07-02 08:00","2018-07-03 18:00","매일",null,null,null,201804300170]
[78,"전북","김제","고창홍농 T/L","154kV 고창-홍농T/L 항공장애표시구 교체","154kV 정주-고창#2T/L과 154kV 고창-홍농T/L 항공장애표시구 교체공사 시 병행선로로 안전거리 확보를위해 휴전","2018-07-02 08:00","2018-07-03 18:00","2018-07-02 08:00","2018-07-03 18:00","매일",null,null,null,201805090335]
[79,"전북","김제","신김제전주#1 T/L","154kV 신김제-전주#1T/L 항공장애표시구설치공사","No.35~36, 36~37호 11EA","2018-07-06 08:00","2018-07-07 18:00","2018-07-06 08:00","2018-07-07 18:00","매일",null,null,null,201804300173]
[80,"전북","김제","신김제정공#2 T/L","154kV 신김제-정공#2T/L 항공장애표시구설치공사","No.22~23, 27~28, 28~29, 37~38, 38~39호 29EA","2018-07-04 08:00","2018-07-05 18:00","2018-07-04 08:00","2018-07-05 18:00","매일",null,null,null,201804300172]
[81,"광주전남","강진","남창해남CS#2 T/L","남창S/S 154kV 남창-해남C/S #2T/L (DS 결상 보수)","2018~19년 강진전력지사 변전정비회사 총액공사 - 내용 : DS 결상 예방 관련 보수","2018-07-10 09:00","2018-07-10 18:00","2018-07-10 09:00","2018-07-10 18:00","당일",null,null,null,201805080215]
[82,"광주전남","강진","남창해남CS#1 T/L","남창S/S 154kV 남창-해남C/S #1T/L (DS 결상 보수)","2018~19년 강진전력지사 변전정비회사 총액공사 - 내용 : DS 결상 예방 관련 보수","2018-07-09 09:00","2018-07-09 18:00","2018-07-09 09:00","2018-07-09 18:00","당일",null,null,null,201805080213]
[83,"광주전남","강진","강진남창#1 T/L","남창S/S 154kV 강진-남창 #1T/L (DS 결상 보수)","2018~19년 강진전력지사 변전정비회사 총액공사 - 내용 : LA 인하선 측 노후 P.G 클램프 교체 강진, 남창측 양단 DS 결상 및 불량개소 보수","2018-07-03 09:00","2018-07-03 18:00","2018-07-03 09:00","2018-07-03 18:00","당일",null,null,null,201804300160]
[84,"광주전남","강진","강진남창#2 T/L","남창S/S 154kV 강진-남창 #2T/L (P.G 클램프 교체)","2018~19년 강진전력지사 변전정비회사 총액공사 - 내용 : LA 인하선 측 노후 P.G 클램프 교체","2018-07-02 09:00","2018-07-02 18:00","2018-07-02 09:00","2018-07-02 18:00","당일",null,null,null,201804300159]
[85,"광주전남","광주","신화순S/S #1EM.Tr A CB","신화순S/S F/R용 ESS설비 연차점검","- F/R용 ESS설비 정밀점검 및 성능평가 - #61 M.Tr, ESS용 S.Tr(3-2,4S.Tr), 154kV 및 23kV GIS 하자점검","2018-07-02 09:00","2018-07-13 18:00","2018-07-02 09:00","2018-07-13 18:00","연속",null,null,null,201805030058]
[86,"광주전남","순천","여수TP화치#2 T/L","154kV 화치S/S 한화케미칼T/L 신규수용공사","한화케미칼T/L 신설분 24시간 무부하가압 - DS, CB, 상부BUS, 챔버 무부하가압","2018-07-04 10:00","2018-07-05 10:00","2018-07-04 10:00","2018-07-05 10:00","연속",null,null,null,201805080129]
[87,"광주전남","직할","신화순나주#2 T/L","154kV 나주옥내화 건설공사","○154kV 나주옥내화 건설공사 - M.Tr : 154kV 60MVA 4Bank - GIS : 154kV 50kA 19CCT(11T/L), 22.9kV 25kA 41CCT(25D/L) - 기타부대공사","2018-07-11 09:00","2018-07-13 18:00","2018-07-11 09:00","2018-07-13 18:00","연속",null,null,null,201804200131]
[88,"광주전남","직할","비아S/S 154kV #1 BUS","[변전] 비아S/S 170kV 장기사용GIS 대체공사","○ 비아S/S 170kV 장기사용 대체공사","2018-07-18 15:00","2018-07-28 09:00","취소","취소","연속",null,null,null,201805290102]
[89,"광주전남","직할","비아S/S 154kV #1 BUS TIE GIS","[변전] 비아S/S 170kV 장기사용GIS 대체공사","○ 비아S/S 170kV 장기사용 대체공사","2018-07-16 09:00","2018-08-03 18:00","취소","취소","연속",null,null,null,201805290101]
[90,"광주전남","직할","일곡비아#1 T/L","[변전] 비아S/S 170kV 장기사용GIS 대체공사","○ 비아S/S 170kV 장기사용 대체공사","2018-07-13 09:00","2018-07-14 09:00","2018-07-13 09:00","2018-07-14 09:00","연속",null,null,null,201805290100]
[91,"광주전남","직할","일곡비아#1 T/L","[변전] 비아S/S 170kV 장기사용GIS 대체공사","○ 비아S/S 170kV 장기사용 대체공사","2018-07-10 15:00","2018-07-11 09:00","2018-07-10 15:00","2018-07-11 09:00","연속",null,null,null,201805290099]
[92,"광주전남","직할","일곡비아#1 T/L","[변전] 비아S/S 170kV 장기사용GIS 대체공사","○ 비아S/S 170kV 장기사용 대체공사","2018-07-05 15:00","2018-07-06 09:00","2018-07-05 15:00","2018-07-06 09:00","연속",null,null,null,201805290098]
[93,"대구","달성","논공달성#2 T/L","154kV 논공-달성T/L 안전이격확보 및 전선교체공사","논공-달성T/L 30호 철탑교체, 18~25,25~35,36~S/T 전선교체","2018-07-10 08:00","2018-07-24 18:00","취소","취소","연속",null,null,null,201805090012]
[94,"대구","포항","건천천북#1 T/L","2018년 가공송전선로 순시점검 위탁공사","건천-천북#1 T/L No.86, 91 지지애자 절연저항 측정","2018-07-04 09:00","2018-07-04 18:00","취소","취소","당일",null,null,null,201805090118]
[95,"대구","포항","신포항상정#1 T/L","2018-19년도 가공송전정비 협력회사 가공지선 정비공사","가공지선 1조 추가설치 및 피뢰기 설치","2018-07-09 08:00","2018-07-09 18:00","2018-07-09 08:00","2018-07-09 18:00","당일",null,null,null,201805150155]
[96,"대구","포항","신포항상정#2 T/L","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- CVT 이설 및 8DS, T-BUS 철거 등","2018-07-09 08:00","2018-07-10 18:00","2018-07-09 08:00","2018-07-10 18:00","연속",null,null,null,201803050001]
[97,"대구","포항","신포항S/S 154kV #65 BUS","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 상부모선, CB, DS 및 POST, BEAM 철거 등","2018-07-09 08:00","2018-07-10 18:00","2018-07-09 08:00","2018-07-10 18:00","연속",null,null,null,201804050023]
[98,"대구","포항","옥동외동#1 T/L","2018년 포항전력지사 조작시험","외동옥동#1 T/L 687 CB 조작시험, LA A,B,C 보통점검","2018-07-09 10:00","2018-07-09 18:00","2018-07-09 10:00","2018-07-09 18:00","당일",null,null,null,201805090069]
[99,"경북","구미","선산청리#1 T/L","선산S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 공사 - 피뢰기 Lead선 보강작업","2018-07-04 13:00","2018-07-04 18:00","2018-07-04 13:00","2018-07-04 18:00","당일",null,null,null,201805150111]
[100,"경북","직할","안동동안동#1 T/L","2018년 경북본부 직할 170kV GIS 정밀점검 공사","동안동S/S 6100GIS 정밀점검 무부하가압","2018-07-03 13:00","2018-07-03 18:00","2018-07-03 13:00","2018-07-03 18:00","당일",null,null,null,201805020042]
[101,"부산울산","동부산","명례S/S 154KV #1 BUS TIE CB","명례S/S 170kV GIS 조작시험","명례S/S 170kV GIS 조작시험(6100)","2018-07-06 09:30","2018-07-06 14:00","2018-07-06 09:30","2018-07-06 14:00","당일",null,null,null,201805140005]
[102,"부산울산","동부산","정관S/S 154KV#1 BUS TIE CB","정관S/S 170kV GIS 조작시험","정관S/S 170kV GIS 조작시험(6100)","2018-07-06 14:00","2018-07-06 18:00","2018-07-06 14:00","2018-07-06 18:00","당일",null,null,null,201805140006]
[103,"부산울산","북부산","김해어방#2 T/L","(2차)김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#1T/L GIS 대체(#2DS, #2BUS, CB, 상부BUS 시험가압)","2018-07-08 16:00","2018-07-09 18:00","2018-07-08 16:00","2018-07-09 18:00","연속",null,null,null,201804030119]
[104,"부산울산","북부산","김해S/S 154kV #1 BUS","(2차)김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#1T/L GIS 대체(#1DS 시험가압)","2018-07-09 16:00","2018-07-09 18:00","2018-07-09 16:00","2018-07-09 18:00","당일",null,null,null,201804030114]
[105,"부산울산","북부산","김해어방#2 T/L","(2차)김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#1T/L GIS 대체(Wall Bushing 설치 안전이격)","2018-07-05 13:00","2018-07-05 17:00","2018-07-05 13:00","2018-07-05 17:00","당일",null,null,null,201804090484]
[106,"부산울산","북부산","김해S/S 154kV #2 BUS","(2차)김해S/S 154kV 장기사용 GIS 대체공사","김해S/S 154kV 김해-어방#1T/L GIS 대체(#2DS 설치)","2018-07-02 08:00","2018-07-09 16:00","2018-07-02 08:00","2018-07-09 16:00","연속",null,null,null,201804030115]
[107,"부산울산","북부산","서창산막#2 T/L","18년 가공송전 협력업체 총액공사","3, 4, 5호 상,중,하단 아킹혼 설치공사","2018-07-08 07:00","2018-07-08 18:00","2018-07-08 07:00","2018-07-08 18:00","당일",null,null,null,201805100059]
[108,"부산울산","북부산","서창산막#1 T/L","18년 가공송전 협력업체 총액공사","3, 4, 5호 상,중,하단 아킹혼 설치공사","2018-07-07 07:00","2018-07-07 18:00","2018-07-07 07:00","2018-07-07 18:00","당일",null,null,null,201805100058]
[109,"부산울산","울산","신울산언양#2 T/L","154kV 신울산-언양 등 3개T/L 지장철탑이설공사","○ 철탑 3기 교체(65, 66, 66-1호) ○ 작업구간 : 64~67호","2018-07-08 08:00","2018-07-10 18:00","2018-07-08 08:00","2018-07-10 18:00","연속",null,null,null,201805100204]
[110,"부산울산","울산","신울산언양#1 T/L","154kV 신울산-언양 등 3개T/L 지장철탑이설공사","○ 철탑 3기 교체(65, 66, 66-1호) ○ 작업구간 : 64~67호","2018-07-03 08:00","2018-07-07 18:00","2018-07-03 08:00","2018-07-07 18:00","연속",null,null,null,201805100199]
[111,"부산울산","울산","신울산언양#2 T/L","154kV 신울산-언양 등 3개T/L 지장철탑이설공사","○ 철탑 3기 교체(65, 66, 66-1호) ○ 작업구간 : 64~67호","2018-07-01 08:00","2018-07-02 18:00","2018-07-01 08:00","2018-07-02 18:00","연속",null,null,null,201805100193]
[112,"부산울산","울산","옥동외동#1 T/L","2018년 가공송전 순시점검 위탁공사","이도조정 및 상간스페이서 설치","2018-07-02 08:00","2018-07-04 18:00","2018-07-02 08:00","2018-07-04 18:00","연속",null,null,null,201805100112]
[113,"부산울산","울산","신온산온산#3 T/L","2018-19년 울산전력지사 변전협력회사 총액공사","온산S/S 170kV 신온산-온산#3T/L GIS 차단기 동작시험","2018-07-03 09:00","2018-07-03 18:00","2018-07-03 09:00","2018-07-03 18:00","당일",null,null,null,201805100128]
[114,"부산울산","울산","용연울산TP#3 T/L","345kV 신울산복합-북부산T/L 건설공사","○ 345kV 신울산복합-북부산T/L 건설관련 가선로 구성 - 구간 : 기설 No.3 ~ 5구간","2018-07-07 07:00","2018-07-09 19:00","2018-07-07 07:00","2018-07-09 19:00","연속",null,null,null,201805110188]
[115,"부산울산","울산","울산울산TP#1 T/L","345kV 신울산복합-북부산T/L 건설공사","○ 345kV 신울산복합-북부산T/L 건설관련 가선로 구성 - 구간 : 기설 No.2 ~ 6구간","2018-07-05 07:00","2018-07-06 19:00","2018-07-05 07:00","2018-07-06 19:00","연속",null,null,null,201805110187]
[116,"부산울산","울산","울산울산TP#2 T/L","345kV 신울산복합-북부산T/L 건설공사","○ 345kV 신울산복합-북부산T/L 건설관련 가선로 구성 - 구간 : 기설 No.2 ~ 6구간","2018-07-01 07:00","2018-07-04 19:00","2018-07-01 07:00","2018-07-04 19:00","연속",null,null,null,201805110186]
[117,"부산울산","울산","온산처용#1 T/L","2018-19년 울산전력지사 변전협력회사 총액공사","1.처용S/S 축소형모자익대체관련 제어케이블 철거 및 설치작업 2.처용S/S 170kV 온산-처용#1T/L GIS 공기압압력계 불량점검 및 조치","2018-07-09 09:00","2018-07-10 18:00","2018-07-10 09:00","2018-07-11 18:00","연속",null,null,null,201805170086]
[118,"부산울산","직할","수정범일#2 T/L","154kV 범일 등 3개S/S 지중송전케이블 선종교체공사","154kV 수정-범일T/L 선종교체공사(OF1200 --&gtXLPE 1200, 0.7km) - 공사구간 : 수정S/S ~ S/J, 범일S/S ~ J/B#7-2","2018-07-12 09:00","2018-08-23 18:00","2018-07-12 09:00","2018-08-23 18:00","연속",null,null,null,201805110136]
[119,"경남","직할","천선개폐소 154kV #65 BUS","삼정S/S GIS화 부지확보 삼정-천선#2T/L 인출변경 시험가압","삼정-천선#2T/L 인출변경시 시험가압시 상대단 변전소 모선조정","2018-07-11 09:30","2018-07-13 17:30","2018-07-11 09:30","2018-07-13 17:30","연속",null,null,null,201805090147]
[120,"경남","진주","의령S/S #1 EM.Tr A CB","의령S/S ESS 정기 성능점검 및 설비점검","의령S/S ESS 정기 성능점검 및 설비점검","2018-07-16 09:30","2018-07-25 18:30","2018-07-16 09:30","2018-07-25 18:30","연속",null,null,null,201805030045]
[121,"경남","진주","하동개양#2 T/L","154kV 하동-개양T/L 30~33호 안전이격거리확보","30~33호 임시선로 구성","2018-07-14 06:00","2018-07-15 20:00","취소","취소","연속",null,null,null,201805020181]
[122,"경남","진주","하동개양#1 T/L","154kV 하동-개양T/L 30~33호 안전이격거리확보","30~33호 임시선로 구성","2018-07-14 06:00","2018-07-15 20:00","취소","취소","연속",null,null,null,201805020178]
[123,"경남","통영","통영거제#1 T/L","154kV 통영-거제#1T/L YPP 보호계전기 오동작방지대책","1. 통영S/S 154kV 통영-거제#1T/L YPP 보호계전기(87Ry) 오동작방지 대책시행 2. 거제S/S 154kV 통영-거제#1T/L YPP 보호계전기(87Ry) 오동작방지 3. 삼성중공업 내 154kV 통영-거제#1T/L YPP 보호계전기(87Ry) 오동작방지 대책시행 - 제작사, 계통 시험파트 입회","2018-07-01 09:30","2018-07-01 18:30","2018-07-01 09:30","2018-07-01 18:30","당일",null,null,null,201805300171]

{"sheet":"한수원","index":3,"n_rows":13,"n_cols":20,"rows_kept":13,"cut":false,"hidden":false,"merged":[[2,19,3,19],[2,13,3,13],[2,14,3,14],[2,15,3,15],[2,16,3,16],[2,17,3,17],[2,18,3,18],[0,0,0,6],[2,12,3,12],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11]]}
["2018년도 07월 휴전계획표(한국수력원자력)"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"한빛본부","1발전소","#2 주변압기","한빛2호기 23차 O/H 중 주변압기 점검\n* 조작차단기 : CB 7400, 7471","○ 주변압기 및 소내보조변압기 점검","2018-07-16T10:00:00","2018-10-06T16:00:00","2018-07-16T10:00:00","2018-10-06T16:00:00","연속","Y"]
[2,"한빛본부","1발전소","#2 기동변압기(X01)","한빛2호기 23차 O/H 중 기동변압기\n(X01) 점검\n* 조작차단기 : CB 7300, 7371","○ 기동변압기(X01) 일반점검","2018-07-21T13:00:00","2018-08-24T13:00:00","2018-07-21T13:00:00","2018-08-24T13:00:00","연속","Y"]
[3,"한빛본부","2발전소","#4 기동변압기(04XN)","한빛4호기 16차 O/H 중 GIB/GIS 개선\n* 조작차단기 : CB 7800, 7871","○ 기동변압기측(04XN) GIB/CV케이블 교체\n○ 기동변압기측(04XN) GIS 교체","2018-07-02T10:00:00","2018-08-26T18:00:00","2018-07-02T10:00:00","2018-08-26T18:00:00","연속","Y"]
[4,"한빛본부","2발전소","#4 기동변압기(03XN)","한빛4호기 16차 O/H 중 GIB/GIS 개선\n* 조작차단기 : CB 7900, 7971","○ 기동변압기측(03XN) GIB/CV케이블 교체\n○ 기동변압기측(03XN) GIS 교체","2018-07-29T10:00:00","2018-09-11T18:00:00","2018-07-29T10:00:00","2018-09-11T18:00:00","연속","Y"]
[5,"월성본부","2발전소","#3 기동용변압기","월성3호기 16차 O/H 중 기동변압기 점검\n* 조작차단기 : CB 7600, 7672","○ 기동용변압기 점검","2018-07-10T09:00:00","2018-07-24T19:00:00","2018-07-10T09:00:00","2018-07-24T19:00:00","연속","Y"]
[6,"월성본부","2발전소","#3 주변압기","월성3호기 16차 O/H 중 소내모선 \n정전작업 및 전원절체시험\n* 조작차단기 : CB 7500, 7572","○ 소내모선 정전작업\n○ 소내전원절체시험","2018-07-25T09:00:00","2018-07-26T23:00:00","2018-07-25T09:00:00","2018-07-26T23:00:00","수시\n조작","Y"]
[7,"월성본부","2발전소","#3 기동용변압기","월성3호기 16차 O/H 중 소내전원\n절체시험\n* 조작차단기 : CB 7600, 7672","○ 소내전원절체시험","2018-07-25T09:00:00","2018-07-26T23:00:00","2018-07-25T09:00:00","2018-07-26T23:00:00","수시\n조작","Y"]
[8,"월성본부","2발전소","#3 주변압기","월성3호기 16차 O/H 중 계통연결 대기\n* 조작차단기 : CB 7500, 7572","○ 계통연결전 발전기 링크 조립 및 대기","2018-07-26T23:00:00","2018-08-05T16:00:00","2018-07-26T23:00:00","2018-08-05T16:00:00","연속","Y"]
[9,"한울본부","2발전소","#4 주변압기","한울4호기 13차 O/H 중 소내전원\n절체시험\n* 조작차단기 : CB 7600, 7672","○ 소내전원 절체시험\n  - 절체시험 후 개방차단기 재투입","2018-07-24T14:00:00","2018-07-24T17:00:00","2018-07-24T14:00:00","2018-07-24T17:00:00","수시\n조작","Y"]