{"text_format":"2","workbook":"xlsx","n_sheets":5,"sheets":["765송부","345송부","154송부","한수원","중부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":9,"n_cols":16,"rows_kept":9,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,14,3,14],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2018년도 \"&#REF!&\"월 휴전계획서\"","v":{"$error":"#REF!"}}]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신안성신가평 T/L","신가평S/S 765kV Trench제 부싱단자 교체","신가평S/S 765kV Trench제 부싱단자 교체","2018-09-20 09:00","2018-09-20 18:00","2018-09-20 09:00","2018-09-20 18:00","당일",null,null,null,201807110216,"-"]
[2,"경기북부","구리","신태백신가평#2 T/L","신가평S/S 765kV Trench제 부싱단자 교체","신가평S/S 765kV Trench제 부싱단자 교체","2018-09-21 09:00","2018-09-21 18:00","2018-09-21 09:00","2018-09-21 18:00","당일",null,null,null,201807110217,"-"]
[3,"경기북부","구리","신태백신가평#1 T/L","신가평S/S 765kV Trench제 부싱단자 교체","신가평S/S 765kV Trench제 부싱단자 교체","2018-09-18 09:00","2018-09-19 09:00","2018-09-18 09:00","2018-09-19 18:00","연속",null,null,null,201807300092,"-"]
[4,"경기","성남","신서산신안성#1 T/L","765kV 신서산-신안성#1T/L 송전선로 정밀점검","765kV 신서산-신안성#1T/L 211~259호 송전선로 정밀점검","2018-09-27 08:00","2018-10-02 18:00","취소","취소","연속",null,null,null,201807040130,"-"]
[5,"대전충남","서산","신서산S/S #3 M.Tr A-2","765kV M.Tr 2차측 장경간 구조개선 공사","765kV M.Tr 2차측 장경간 구조개선 공사","2018-09-17 09:00","2018-10-26 18:00","2018-09-17 09:00","2018-10-26 18:00","연속",null,null,null,201807120007,"-"]

{"sheet":"345송부","index":1,"n_rows":234,"n_cols":16,"rows_kept":234,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,14,3,14],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2018년도 \"&#REF!&\"월 휴전계획서\"","v":{"$error":"#REF!"}}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #2 M.Tr A","18년 성동P/O 변전협력회사 총액공사","- 주변압기 보통점검(성동S/S #2M.Tr)","2018-09-19 09:30","2018-09-20 17:00","2018-09-19 09:30","2018-09-20 17:00","연속",null,null,null,201807130104,{"$f":"IF(ISERROR(VLOOKUP(D5,#REF!,13,0)),\"-\",VLOOKUP(D5,#REF!,13,0))","v":"-"}]
[2,"남서울","영등포","신광명S/S #1 M.Tr A","영서S/S 154kV 이하 옥외철구 GIS화 공사","상부 가공지선 정비 이격거리 확보","2018-09-11 09:00","2018-09-11 18:00","2018-09-11 09:00","2018-09-11 18:00","당일",null,null,null,201807190050,{"$f":"IF(ISERROR(VLOOKUP(D6,#REF!,13,0)),\"-\",VLOOKUP(D6,#REF!,13,0))","v":"-"}]
[3,"남서울","영등포","신광명S/S #4 M.Tr A","영서S/S 154kV 이하 옥외철구 GIS화 공사","상부 가공지선 정비 이격거리 확보","2018-09-14 09:00","2018-09-14 18:00","2018-09-14 09:00","2018-09-14 18:00","당일",null,null,null,201807190053,{"$f":"IF(ISERROR(VLOOKUP(D7,#REF!,13,0)),\"-\",VLOOKUP(D7,#REF!,13,0))","v":"-"}]
[4,"남서울","영등포","신광명S/S #3 M.Tr A","영서S/S 154kV 이하 옥외철구 GIS화 공사","상부 가공지선 정비 이격거리 확보","2018-09-13 09:00","2018-09-13 18:00","2018-09-13 09:00","2018-09-13 18:00","당일",null,null,null,201807190052,{"$f":"IF(ISERROR(VLOOKUP(D8,#REF!,13,0)),\"-\",VLOOKUP(D8,#REF!,13,0))","v":"-"}]
[5,"남서울","영등포","신광명S/S #2 M.Tr A","영서S/S 154kV 이하 옥외철구 GIS화 공사","상부 가공지선 정비 이격거리 확보","2018-09-12 09:00","2018-09-12 18:00","2018-09-12 09:00","2018-09-12 18:00","당일",null,null,null,201807190051,{"$f":"IF(ISERROR(VLOOKUP(D9,#REF!,13,0)),\"-\",VLOOKUP(D9,#REF!,13,0))","v":"-"}]
[6,"남서울","영등포","신광명영등포#2 T/L","345kV 신광명-영등포#2T/L EBG 해체점검","345kV 신광명-영등포#2T/L EBG 해체점검 - 신광명EBG (2개소), 영등포EBG (3개소)","2018-09-21 18:00","2018-09-28 18:00","2018-09-21 18:00","2018-09-28 18:00","연속",null,null,null,201807060129,{"$f":"IF(ISERROR(VLOOKUP(D10,#REF!,13,0)),\"-\",VLOOKUP(D10,#REF!,13,0))","v":"-"}]
[7,"남서울","직할","신광명영등포#1 T/L","345kV T/L 보호반 교체","신광명-영등포#1T/L 보호반 교체","2018-09-28 18:00","2018-10-03 18:00","2018-09-28 18:00","2018-10-03 18:00","연속",null,null,null,201807090291,{"$f":"IF(ISERROR(VLOOKUP(D11,#REF!,13,0)),\"-\",VLOOKUP(D11,#REF!,13,0))","v":"-"}]
[8,"남서울","직할","영등포S/S #3 M.Tr A","(주)새롬프로텍 345kV 변압기 보호반 성능 개선","64V 관련 로직 수정","2018-09-04 16:00","2018-09-04 19:00","2018-09-04 16:00","2018-09-04 19:00","당일",null,null,null,201807240072,{"$f":"IF(ISERROR(VLOOKUP(D12,#REF!,13,0)),\"-\",VLOOKUP(D12,#REF!,13,0))","v":"-"}]
[9,"남서울","직할","영등포S/S #2 M.Tr A","(주)새롬프로텍 345kV 변압기 보호반 성능 개선","64V 관련 로직 수정","2018-09-04 13:00","2018-09-04 16:00","2018-09-04 13:00","2018-09-04 16:00","당일",null,null,null,201807240071,{"$f":"IF(ISERROR(VLOOKUP(D13,#REF!,13,0)),\"-\",VLOOKUP(D13,#REF!,13,0))","v":"-"}]
[10,"남서울","직할","영등포S/S #1 M.Tr A","(주)새롬프로텍 345kV 변압기 보호반 성능 개선","64V 관련 로직 수정","2018-09-04 09:00","2018-09-04 13:00","2018-09-04 09:00","2018-09-04 13:00","당일",null,null,null,201807240068,{"$f":"IF(ISERROR(VLOOKUP(D14,#REF!,13,0)),\"-\",VLOOKUP(D14,#REF!,13,0))","v":"-"}]
[11,"인천","직할","서인천CC신부평#1 T/L","345kV 서인천CC-신부평#1T/L OF케이블 절연유 채취밸브 설치공사","J/B#30 등 3개소 절연유 채취밸브 설치","2018-09-17 09:00","2018-09-18 18:00","취소","취소","연속",null,null,null,201807230010,{"$f":"IF(ISERROR(VLOOKUP(D15,#REF!,13,0)),\"-\",VLOOKUP(D15,#REF!,13,0))","v":"-"}]
[12,"인천","직할","서인천CC신부평#2 T/L","345kV 서인천CC-신부평#2T/L OF케이블 절연유 채취밸브 설치공사","J/B#24 등 9개소 절연유 채취밸브 설치","2018-09-19 09:00","2018-09-20 18:00","취소","취소","연속",null,null,null,201807230012,{"$f":"IF(ISERROR(VLOOKUP(D16,#REF!,13,0)),\"-\",VLOOKUP(D16,#REF!,13,0))","v":"-"}]
[13,"인천","직할","서인천CC신부평#3 T/L","345kV 서인천CC-신부평#3T/L OF케이블 절연유 채취밸브 설치공사","J/B#24 등 9개소 절연유 채취밸브 설치","2018-09-27 09:00","2018-09-28 18:00","취소","취소","연속",null,null,null,201807230013,{"$f":"IF(ISERROR(VLOOKUP(D17,#REF!,13,0)),\"-\",VLOOKUP(D17,#REF!,13,0))","v":"-"}]
[14,"인천","인천","신가좌S/S #1 M.Tr A","신가좌S/S 345㎸ 용량부족 GIS 대체공사","신가좌S/S 345㎸ 용량부족 GIS 대체공사 - 71Bay 철거 및 설치 (3CB) - 제어케이블 분리 및 결선 - 기타 부대작업","2018-09-03 09:00","2018-12-21 18:00","2018-09-15 08:00","2018-11-25 18:00","연속",null,null,null,201807020051,{"$f":"IF(ISERROR(VLOOKUP(D18,#REF!,13,0)),\"-\",VLOOKUP(D18,#REF!,13,0))","v":"-"}]
[15,"인천","인천","신가좌S/S 345kV #1 BUS","신가좌S/S 345㎸ 용량부족 GIS 대체공사","신가좌S/S 345㎸ 용량부족 GIS 대체공사 - 실부하 가압 관련 앵글 측정","2018-09-14 13:00","2018-09-14 16:00","2018-09-27 08:00","2018-10-10 18:00","연속",null,null,null,201804030076,{"$f":"IF(ISERROR(VLOOKUP(D19,#REF!,13,0)),\"-\",VLOOKUP(D19,#REF!,13,0))","v":"-"}]
[16,"인천","인천","신가좌S/S 345kV #2 BUS","신가좌S/S 345㎸ 용량부족 GIS 대체공사","신가좌S/S 345㎸ 용량부족 GIS 대체공사 - 실부하 가압 관련 앵글 측정","2018-09-14 16:00","2018-09-14 18:00","취소","취소","당일",null,null,null,201804030077,{"$f":"IF(ISERROR(VLOOKUP(D20,#REF!,13,0)),\"-\",VLOOKUP(D20,#REF!,13,0))","v":"-"}]
[17,"인천","인천","신가좌S/S 신가좌신시흥#2T/L GIS","2018년 인천전력지사 362㎸ GIS 정밀점검","신가좌S/S 7471 GIS 정밀점검","2018-09-14 09:00","2018-09-16 18:00","취소","취소","연속",null,null,null,201807060108,{"$f":"IF(ISERROR(VLOOKUP(D21,#REF!,13,0)),\"-\",VLOOKUP(D21,#REF!,13,0))","v":"-"}]
[18,"인천","인천","신가좌가정#2 T/L","신가좌S/S 345㎸ 용량부족 GIS 대체공사","신가좌S/S 345㎸ 용량부족 GIS 대체공사 - 71Bay 철거 및 설치 (3CB) - 제어케이블 분리 및 결선 - 기타 부대작업","2018-09-03 09:00","2018-12-21 18:00","2018-09-15 08:00","2018-11-25 18:00","연속",null,null,null,201807020050,{"$f":"IF(ISERROR(VLOOKUP(D22,#REF!,13,0)),\"-\",VLOOKUP(D22,#REF!,13,0))","v":"-"}]
[19,"인천","시흥","신가좌신시흥#1 T/L","345kV 신가좌-신시흥(신시흥-신광명)T/L 지장송전선로 이설공사","■ 휴전일정(임시선로 구성) ○ 1차 휴전(5일간) - (상단) 345kV 신시흥-신광명 #2T/L No.34~38 - (하단) 345kV 신가좌-신시흥 #2T/L No.57~61 ○ 2차 휴전(5일간) - (상단) 345kV 신시흥-신광명 #1T/L No.34~38 - (하단) 345kV 신가좌-신시흥 #1T/L No.57~61","2018-09-16 06:00","2018-09-20 18:00","취소","취소","연속",null,null,null,201807120162,{"$f":"IF(ISERROR(VLOOKUP(D23,#REF!,13,0)),\"-\",VLOOKUP(D23,#REF!,13,0))","v":"-"}]
[20,"인천","시흥","신가좌신시흥#2 T/L","345kV 신가좌-신시흥(신시흥-신광명)T/L 지장송전선로 이설공사","■ 휴전일정(임시선로 구성) ○ 1차 휴전(5일간) - (상단) 345kV 신시흥-신광명 #2T/L No.34~38 - (하단) 345kV 신가좌-신시흥 #2T/L No.57~61 ○ 2차 휴전(5일간) - (상단) 345kV 신시흥-신광명 #1T/L No.34~38 - (하단) 345kV 신가좌-신시흥 #1T/L No.57~61","2018-09-11 06:00","2018-09-15 18:00","취소","취소","연속",null,null,null,201807120160,{"$f":"IF(ISERROR(VLOOKUP(D24,#REF!,13,0)),\"-\",VLOOKUP(D24,#REF!,13,0))","v":"-"}]
[21,"인천","인천","신가좌신시흥#2T/L-#3 M.Tr 1차 GIS","2018년 인천전력지사 362㎸ GIS 정밀점검","신가좌S/S 7400 GIS 정밀점검","2018-09-11 09:00","2018-09-13 18:00","취소","취소","연속",null,null,null,201807060107,{"$f":"IF(ISERROR(VLOOKUP(D25,#REF!,13,0)),\"-\",VLOOKUP(D25,#REF!,13,0))","v":"-"}]
[22,"인천","인천","신경서S/S 345kV #1 BUS","2018년 인천전력지사 362㎸ GIS 정밀점검","신경서S/S 7171 GIS 정밀점검 - 7171 CB, 7151 DS 정밀점검","2018-09-18 09:00","2018-09-21 18:00","2018-09-18 09:00","2018-09-21 18:00","연속",null,null,null,201807060109,{"$f":"IF(ISERROR(VLOOKUP(D26,#REF!,13,0)),\"-\",VLOOKUP(D26,#REF!,13,0))","v":"-"}]
[23,"인천","인천","신경서S/S 신경서신인천CCT/L GIS","2018년 인천전력지사 362㎸ GIS 정밀점검","신경서S/S 7171 GIS 정밀점검","2018-09-18 09:00","2018-09-21 18:00","2018-09-18 09:00","2018-09-21 18:00","연속",null,null,null,201807060110,{"$f":"IF(ISERROR(VLOOKUP(D27,#REF!,13,0)),\"-\",VLOOKUP(D27,#REF!,13,0))","v":"-"}]
[24,"인천","김포","신김포S/S 345kV #3Sh.R","신김포S/S 345kV #3Sh.R 보통점검","신김포S/S 345kV #3Sh.R 보통점검","2018-09-11 09:00","2018-09-11 18:00","2018-09-11 09:00","2018-09-11 18:00","당일",null,null,null,201807030163,{"$f":"IF(ISERROR(VLOOKUP(D28,#REF!,13,0)),\"-\",VLOOKUP(D28,#REF!,13,0))","v":"-"}]
[25,"인천","직할","신부평S/S 345kV #1 Sh.R","신부평S/S 345kV #1Sh.R 보통점검","신부평S/S 345kV #1Sh.R 보통점검","2018-09-20 09:00","2018-09-21 18:00","2018-09-20 09:00","2018-09-21 18:00","연속",null,null,null,201807120061,{"$f":"IF(ISERROR(VLOOKUP(D29,#REF!,13,0)),\"-\",VLOOKUP(D29,#REF!,13,0))","v":"-"}]
[26,"인천","시흥","신시흥#1S/S #3 M.Tr A","신시흥#1S/S #3 M.Tr 2차GIS 정밀점검","신시흥#1S/S #3 M.Tr 2차GIS 정밀점검","2018-09-12 08:00","2018-09-14 18:00","2018-09-15 08:00","2018-09-16 18:00","연속",null,null,null,201807120032,{"$f":"IF(ISERROR(VLOOKUP(D30,#REF!,13,0)),\"-\",VLOOKUP(D30,#REF!,13,0))","v":"-"}]
[27,"인천","시흥","신시흥#2S/S #4 M.Tr A","신시흥#1S/S #4 M.Tr 2차GIS 정밀점검","신시흥#1S/S #4 M.Tr 2차GIS 정밀점검","2018-09-17 08:00","2018-09-20 18:00","2018-09-17 08:00","2018-09-20 18:00","연속",null,null,null,201807120034,{"$f":"IF(ISERROR(VLOOKUP(D31,#REF!,13,0)),\"-\",VLOOKUP(D31,#REF!,13,0))","v":"-"}]
[28,"인천","시흥","신시흥#2S/S #5M.Tr A","신시흥S/S 2-1,2 COMP 대체 관련 이격거리 확보용","신시흥S/S 2-1,2 COMP 대체 관련 이격거리 확보용","2018-09-28 09:00","2018-09-28 18:00","2018-09-28 09:00","2018-09-28 18:00","당일",null,null,null,201807120042,{"$f":"IF(ISERROR(VLOOKUP(D32,#REF!,13,0)),\"-\",VLOOKUP(D32,#REF!,13,0))","v":"-"}]
[29,"인천","시흥","신시흥신광명#1 T/L","345kV 신가좌-신시흥(신시흥-신광명)T/L 지장송전선로 이설공사","■ 휴전일정(임시선로 구성) ○ 1차 휴전(5일간) - (상단) 345kV 신시흥-신광명 #2T/L No.34~38 - (하단) 345kV 신가좌-신시흥 #2T/L No.57~61 ○ 2차 휴전(5일간) - (상단) 345kV 신시흥-신광명 #1T/L No.34~38 - (하단) 345kV 신가좌-신시흥 #1T/L No.57~61","2018-09-16 06:00","2018-09-20 18:00","취소","취소","연속",null,null,null,201807120163,{"$f":"IF(ISERROR(VLOOKUP(D33,#REF!,13,0)),\"-\",VLOOKUP(D33,#REF!,13,0))","v":"-"}]
[30,"인천","시흥","신시흥신광명#2 T/L","345kV 신가좌-신시흥(신시흥-신광명)T/L 지장송전선로 이설공사","■ 휴전일정(임시선로 구성) ○ 1차 휴전(5일간) - (상단) 345kV 신시흥-신광명 #2T/L No.34~38 - (하단) 345kV 신가좌-신시흥 #2T/L No.57~61 ○ 2차 휴전(5일간) - (상단) 345kV 신시흥-신광명 #1T/L No.34~38 - (하단) 345kV 신가좌-신시흥 #12T/L No.57~61","2018-09-11 06:00","2018-09-15 18:00","취소","취소","연속",null,null,null,201807120161,{"$f":"IF(ISERROR(VLOOKUP(D34,#REF!,13,0)),\"-\",VLOOKUP(D34,#REF!,13,0))","v":"-"}]
[31,"인천","시흥","영흥T/P #1 TIE Tr 1차 CB (7371)","영흥T/P #1 TIE Tr 1차 CB (7371) 동작점검","영흥T/P #1 TIE Tr 1차 CB (7371) 동작점검","2018-09-03 10:30","2018-09-03 18:00","2018-09-03 10:30","2018-09-03 18:00","당일",null,null,null,201807250027,{"$f":"IF(ISERROR(VLOOKUP(D35,#REF!,13,0)),\"-\",VLOOKUP(D35,#REF!,13,0))","v":"-"}]
[32,"인천","인천","인천CC S/Y 345KV #1Sh.R CB","345KV 인천CC Sh.R 설치공사","7272 보호게전기 연동시험 및 Sh.R 초기가압","2018-09-17 10:00","2018-09-18 10:00","2018-09-17 10:00","2018-09-18 10:00","연속",null,null,null,201807110004,{"$f":"IF(ISERROR(VLOOKUP(D36,#REF!,13,0)),\"-\",VLOOKUP(D36,#REF!,13,0))","v":"-"}]
[33,"인천","인천","인천CC S/Y 345kV #71 BUS","인천CC Sh.R 설치 공사","7351 DS 연결","2018-09-03 10:00","2018-09-10 18:00","2018-09-03 10:00","2018-09-10 10:00","연속",null,null,null,201807160124,{"$f":"IF(ISERROR(VLOOKUP(D37,#REF!,13,0)),\"-\",VLOOKUP(D37,#REF!,13,0))","v":"-"}]
[34,"인천","인천","인천CC S/Y 345kV #76 BUS","인천CC Sh.R 설치 공사","7352 DS 연결","2018-09-10 10:00","2018-09-17 10:00","2018-09-10 10:00","2018-09-17 10:00","연속",null,null,null,201807160125,{"$f":"IF(ISERROR(VLOOKUP(D38,#REF!,13,0)),\"-\",VLOOKUP(D38,#REF!,13,0))","v":"-"}]
[35,"인천","인천","인천CC S/Y 345KV#2Sh.R CB","345KV 인천CC Sh.R 설치공사","Sh.R 초기가압","2018-09-18 10:00","2018-09-19 10:00","2018-09-18 10:00","2018-09-19 10:00","연속",null,null,null,201807110005,{"$f":"IF(ISERROR(VLOOKUP(D39,#REF!,13,0)),\"-\",VLOOKUP(D39,#REF!,13,0))","v":"-"}]
[36,"경기북부","고양","신파주신덕은#1 T/L","신덕은변전소 내진보강 공사","○ 라디에이터실 철골 브레이싱 추가 및 보강 : 14.3ton ○ 녹막이 페인트칠 : 287M2 ○ 쌍줄비계설치 : 783M2","2018-09-17 09:00","2018-09-21 18:00","2018-09-17 09:00","2018-09-21 18:00","연속",null,null,null,201807170025,{"$f":"IF(ISERROR(VLOOKUP(D40,#REF!,13,0)),\"-\",VLOOKUP(D40,#REF!,13,0))","v":"-"}]
[37,"경기북부","고양","신덕은S/S #1 M.Tr A","주변압기 보통점검 및 디지털압력감시장치 시범적용차","주변압기 보통점검 및 디지털압력감시장치 시범적용차","2018-09-18 09:00","2018-09-19 18:00","2018-09-18 09:00","2018-09-19 18:00","연속",null,null,null,201807130144,{"$f":"IF(ISERROR(VLOOKUP(D41,#REF!,13,0)),\"-\",VLOOKUP(D41,#REF!,13,0))","v":"-"}]
[38,"경기북부","고양","신파주S/S #1SVC Tr CB","18년 신파주S/S SVC 보통점검","18년 신파주S/S 345kV SVC 보통점검","2018-09-03 09:00","2018-09-14 18:00","2018-09-03 09:00","2018-09-14 18:00","연속",null,null,null,201807040150,{"$f":"IF(ISERROR(VLOOKUP(D42,#REF!,13,0)),\"-\",VLOOKUP(D42,#REF!,13,0))","v":"-"}]
[39,"경기북부","고양","파주문산C/C 파주-발전단#3T/L-신덕은-파주 CB(7300)","발전단 변압기 점검 - 파주에너지서비스","발전단 변압기 점검 - 파주에너지서비스 - #3G/T 변압기 점검","2018-09-29 00:00","2018-10-11 00:00","2018-09-29 00:00","2018-10-11 00:00","연속",null,null,null,201807160096,{"$f":"IF(ISERROR(VLOOKUP(D43,#REF!,13,0)),\"-\",VLOOKUP(D43,#REF!,13,0))","v":"-"}]
[40,"경기북부","고양","파주문산C/C 파주문산-발전단#3T/L CB (7372)","발전단 변압기 점검 - 파주에너지서비스","발전단 변압기 점검 - 파주에너지서비스 - #3G/T 변압기 점검","2018-09-29 00:00","2018-10-11 00:00","2018-09-29 00:00","2018-10-11 00:00","연속",null,null,null,201807160097,{"$f":"IF(ISERROR(VLOOKUP(D44,#REF!,13,0)),\"-\",VLOOKUP(D44,#REF!,13,0))","v":"-"}]
[41,"경기북부","고양","파주문산C/C 파주-발전단#4T/L-신덕은-파주 CB(7400)","발전단 변압기 점검 - 파주에너지서비스","발전단 변압기 점검 - 파주에너지서비스 - #4G/T 변압기 점검","2018-09-28 00:00","2018-10-08 00:00","2018-09-28 00:00","2018-10-08 00:00","연속",null,null,null,201807160094,{"$f":"IF(ISERROR(VLOOKUP(D45,#REF!,13,0)),\"-\",VLOOKUP(D45,#REF!,13,0))","v":"-"}]
[42,"경기북부","고양","파주문산C/C 파주문산-발전단#4T/L CB (7472)","발전단 변압기 점검 - 파주에너지서비스","발전단 변압기 점검 - 파주에너지서비스 - #4G/T 변압기 점검","2018-09-28 00:00","2018-10-08 00:00","2018-09-28 00:00","2018-10-08 00:00","연속",null,null,null,201807160095,{"$f":"IF(ISERROR(VLOOKUP(D46,#REF!,13,0)),\"-\",VLOOKUP(D46,#REF!,13,0))","v":"-"}]
[43,"경기북부","고양","파주문산C/C 파주문산-발전단#2T/L CB (7272)","발전단 변압기 점검 - 파주에너지서비스","발전단 변압기 점검 - 파주에너지서비스 - #2G/T 변압기 점검","2018-09-15 00:00","2018-09-27 00:00","2018-09-15 00:00","2018-09-27 00:00","연속",null,null,null,201807160093,{"$f":"IF(ISERROR(VLOOKUP(D47,#REF!,13,0)),\"-\",VLOOKUP(D47,#REF!,13,0))","v":"-"}]
[44,"경기북부","고양","파주문산C/C 파주문산-발전단#2T/L-TIE CB (7200)","발전단 변압기 점검 - 파주에너지서비스","발전단 변압기 점검 - 파주에너지서비스 - #2G/T 변압기 점검","2018-09-15 00:00","2018-09-27 00:00","2018-09-15 00:00","2018-09-27 00:00","연속",null,null,null,201807160092,{"$f":"IF(ISERROR(VLOOKUP(D48,#REF!,13,0)),\"-\",VLOOKUP(D48,#REF!,13,0))","v":"-"}]
[45,"경기북부","고양","파주문산C/C 파주문산-발전단#1T/L-TIE CB (7100)","발전단 변압기 점검 - 파주에너지서비스","발전단 변압기 점검 - 파주에너지서비스 - #1G/T 변압기 점검","2018-09-14 00:00","2018-09-24 00:00","2018-09-14 00:00","2018-09-24 00:00","연속",null,null,null,201807160088,{"$f":"IF(ISERROR(VLOOKUP(D49,#REF!,13,0)),\"-\",VLOOKUP(D49,#REF!,13,0))","v":"-"}]
[46,"경기북부","고양","파주문산C/C 파주문산-발전단#1T/L CB (7172)","발전단 변압기 점검 - 파주에너지서비스","발전단 변압기 점검 - 파주에너지서비스 - #1G/T 변압기 점검","2018-09-14 00:00","2018-09-24 00:00","2018-09-14 00:00","2018-09-24 00:00","연속",null,null,null,201807160089,{"$f":"IF(ISERROR(VLOOKUP(D50,#REF!,13,0)),\"-\",VLOOKUP(D50,#REF!,13,0))","v":"-"}]
[47,"경기북부","고양","신덕은파주문산CC#1 T/L","파주문산CC 345kV GIS 개폐써지 측정","파주문산CC 345kV GIS 개폐써지 측정","2018-09-17 11:00","2018-09-18 18:00","2018-09-17 11:00","2018-09-18 18:00","당일",null,null,null,201807170028,{"$f":"IF(ISERROR(VLOOKUP(D51,#REF!,13,0)),\"-\",VLOOKUP(D51,#REF!,13,0))","v":"-"}]
[48,"경기북부","구리","신가평미금#1 T/L","미금변전소 감시제어설비 교체공사","기존 모자이크반 철거 및 신규 SA혼용시스템 설치 (병행 : 보호계전기 회로보완-재폐로 로직변경)","2018-09-27 09:00","2018-09-29 18:00","2018-09-27 09:00","2018-09-29 18:00","연속",null,null,null,201805290035,{"$f":"IF(ISERROR(VLOOKUP(D52,#REF!,13,0)),\"-\",VLOOKUP(D52,#REF!,13,0))","v":"-"}]
[49,"경기북부","구리","미금S/S #2 M.Tr A","미금S/S 345kV #2M.Tr 정밀점검공사","미금S/S 345kV #2M.Tr 정밀점검공사","2018-09-05 08:00","2018-09-14 18:00","취소","취소","연속",null,null,null,201807110218,{"$f":"IF(ISERROR(VLOOKUP(D53,#REF!,13,0)),\"-\",VLOOKUP(D53,#REF!,13,0))","v":"-"}]
[50,"경기북부","구리","미금S/S #2 M.Tr A","170kV 미금S/S 장기사용 GIS 교체공사(2차분)","73BAY B/F반 교체공사 - 170kV GIS 철거, 설치(크레인 안전이격 확보)","2018-09-15 08:00","2018-09-19 18:00","취소","취소","연속",null,null,null,201807120068,{"$f":"IF(ISERROR(VLOOKUP(D54,#REF!,13,0)),\"-\",VLOOKUP(D54,#REF!,13,0))","v":"-"}]
[51,"경기북부","구리","미금성동#1 T/L","미금S/S 362kV 장기사용 GIS 교체공사","안전이격거리 관련 매일 휴전","2018-09-30 08:00","2018-10-05 18:00","취소","취소","매일",null,null,null,201807200125,{"$f":"IF(ISERROR(VLOOKUP(D55,#REF!,13,0)),\"-\",VLOOKUP(D55,#REF!,13,0))","v":"-"}]
[52,"경기북부","구리","미금S/S #2 M.Tr A","170kV 미금S/S 장기사용 GIS 교체공사(2차분)","- 170kV GIS 철거, 설치(크레인 안전이격 확보) - 기타부대공사","2018-09-01 08:00","2018-09-04 18:00","취소","취소","매일",null,null,null,201807120064,{"$f":"IF(ISERROR(VLOOKUP(D56,#REF!,13,0)),\"-\",VLOOKUP(D56,#REF!,13,0))","v":"-"}]
[53,"경기북부","구리","동서울미금#1 T/L","미금S/S 73BAY B/F반 교체공사","미금S/S 73BAY B/F반 교체공사 7371, 7300 GIS 가스누기점검","2018-09-15 08:00","2018-09-19 18:00","취소","취소","연속",null,null,null,201802200239,{"$f":"IF(ISERROR(VLOOKUP(D57,#REF!,13,0)),\"-\",VLOOKUP(D57,#REF!,13,0))","v":"-"}]
[54,"경기북부","구리","동서울미금#2 T/L","74Bay B/F반 교체공사","74Bay B/F반 교체공사","2018-09-11 08:00","2018-09-14 18:00","취소","취소","연속",null,null,null,201807200119,{"$f":"IF(ISERROR(VLOOKUP(D58,#REF!,13,0)),\"-\",VLOOKUP(D58,#REF!,13,0))","v":"-"}]
[55,"경기북부","구리","미금S/S 345kV #1 Sh.R","미금S/S 362kV 장기사용 GIS 교체공사","미금S/S 362kV #1Sh.R GIS 교체공사 - #1Sh.R - 모선 분리작업 - 보호반 교체작업","2018-09-30 08:00","2018-10-21 18:00","2018-09-30 08:00","2018-10-21 18:00","연속",null,null,null,201807200124,{"$f":"IF(ISERROR(VLOOKUP(D59,#REF!,13,0)),\"-\",VLOOKUP(D59,#REF!,13,0))","v":"-"}]
[56,"경기북부","구리","미금S/S 345kV #1 BUS Sh.R MAIN GIS","미금S/S 362kV 장기사용 GIS 교체공사","미금S/S 362kV #1,5Sh.R GIS 교체공사 - #1Sh.R - 모선 분리작업 - 보호반 교체작업","2018-09-30 08:00","2018-10-05 18:00","2018-09-30 08:00","2018-10-05 18:00","연속",null,null,null,201807130045,{"$f":"IF(ISERROR(VLOOKUP(D60,#REF!,13,0)),\"-\",VLOOKUP(D60,#REF!,13,0))","v":"-"}]
[57,"경기북부","직할","신의정부S/S #3 M.Tr A","18년 변전정비 총액공사","장기사용 부싱 절연유 가스분석 및 절연열화 진단","2018-09-19 10:00","2018-09-20 09:30","2018-09-19 10:00","2018-09-20 09:30","연속",null,null,null,201806260004,{"$f":"IF(ISERROR(VLOOKUP(D61,#REF!,13,0)),\"-\",VLOOKUP(D61,#REF!,13,0))","v":"-"}]
[58,"경기북부","직할","신의정부S/S #4 M.Tr A","18년 변전정비 총액공사","장기사용 부싱 절연유 가스분석 및 절연열화 진단","2018-09-20 10:00","2018-09-21 09:30","2018-09-20 10:00","2018-09-21 09:30","연속",null,null,null,201806260005,{"$f":"IF(ISERROR(VLOOKUP(D62,#REF!,13,0)),\"-\",VLOOKUP(D62,#REF!,13,0))","v":"-"}]
[59,"경기북부","직할","양주S/S 345kV #4 Sh.R","양주변전소 옥외철구 GIS화 공사","345kV M.Tr 3차측 정비","2018-09-03 09:00","2018-09-04 18:00","2018-09-03 09:00","2018-09-04 18:00","연속",null,null,null,201807110161,{"$f":"IF(ISERROR(VLOOKUP(D63,#REF!,13,0)),\"-\",VLOOKUP(D63,#REF!,13,0))","v":"-"}]
[60,"경기북부","직할","양주S/S #1 M.Tr A","양주변전소 옥외철구 GIS화 공사","345kV M.Tr 3차측 GIS 기초 설치","2018-09-17 09:00","2018-09-30 18:00","2018-09-17 09:00","2018-09-30 18:00","연속",null,null,null,201807110160,{"$f":"IF(ISERROR(VLOOKUP(D64,#REF!,13,0)),\"-\",VLOOKUP(D64,#REF!,13,0))","v":"-"}]
[61,"경기북부","직할","양주S/S SVC M.Tr 1차 GIS","362kV GIS 개페타임측정","SVC M.Tr 1차 GIS(7771)개폐타임 측정","2018-09-18 10:00","2018-09-18 13:00","2018-09-18 10:00","2018-09-18 13:00","당일",null,null,null,201807170161,{"$f":"IF(ISERROR(VLOOKUP(D65,#REF!,13,0)),\"-\",VLOOKUP(D65,#REF!,13,0))","v":"-"}]
[62,"경기북부","직할","양주S/S 345kV #5 Sh.R GIS","362kV GIS 개페타임측정","#5 Sh.R GIS(7569)개폐타임 측정","2018-09-18 13:00","2018-09-18 18:00","2018-09-18 13:00","2018-09-18 18:00","당일",null,null,null,201807170162,{"$f":"IF(ISERROR(VLOOKUP(D66,#REF!,13,0)),\"-\",VLOOKUP(D66,#REF!,13,0))","v":"-"}]
[63,"경기북부","직할","양주S/S #3 M.Tr A","양주변전소 옥외철구 GIS화 공사","345kV M.Tr 3차측 GIS 기초 설치","2018-09-03 09:00","2018-09-15 18:00","2018-09-03 09:00","2018-09-15 18:00","연속",null,null,null,201807110159,{"$f":"IF(ISERROR(VLOOKUP(D67,#REF!,13,0)),\"-\",VLOOKUP(D67,#REF!,13,0))","v":"-"}]
[64,"경기","군포","서서울#2S/S 345kV 7D BAY TIE CB (7D00)","서서울#2S/S 362kV GIS DS 조작불량관련 하자보수","○ DS 조작부측 상부 베어링 교체","2018-09-03 09:00","2018-09-04 14:00","2018-09-03 09:00","2018-09-04 14:00","연속",null,null,null,201806280112,{"$f":"IF(ISERROR(VLOOKUP(D68,#REF!,13,0)),\"-\",VLOOKUP(D68,#REF!,13,0))","v":"-"}]
[65,"경기","군포","서서울#2S/S 345kV 서서울2-화성#2T/L CB (7D71)","서서울#2S/S 362kV GIS DS 조작불량관련 하자보수","○ DS 조작부측 상부 베어링 교체","2018-09-03 09:00","2018-09-04 14:00","2018-09-03 09:00","2018-09-04 14:00","연속",null,null,null,201806280111,{"$f":"IF(ISERROR(VLOOKUP(D69,#REF!,13,0)),\"-\",VLOOKUP(D69,#REF!,13,0))","v":"-"}]
[66,"경기","군포","서서울#2S/S 345kV 7C BAY TIE CB (7C00)","서서울#2S/S 362kV GIS DS 조작불량관련 하자보수","○ DS 조작부측 상부 베어링 교체","2018-09-04 09:00","2018-09-05 18:00","2018-09-04 09:00","2018-09-05 18:00","연속",null,null,null,201806280114,{"$f":"IF(ISERROR(VLOOKUP(D70,#REF!,13,0)),\"-\",VLOOKUP(D70,#REF!,13,0))","v":"-"}]
[67,"경기","군포","서서울#2S/S 345kV 서서울2-화성#1T/L CB (7C71)","서서울#2S/S 362kV GIS DS 조작불량관련 하자보수","○ DS 조작부측 상부 베어링 교체","2018-09-04 09:00","2018-09-05 18:00","2018-09-04 09:00","2018-09-05 18:00","연속",null,null,null,201806280113,{"$f":"IF(ISERROR(VLOOKUP(D71,#REF!,13,0)),\"-\",VLOOKUP(D71,#REF!,13,0))","v":"-"}]
[68,"경기","군포","서서울#2신성남 #1T/L","서서울#2S/S 362kV GIS DS 조작불량관련 하자보수","○ DS 조작부측 상부 베어링 교체","2018-09-06 09:00","2018-09-07 18:00","2018-09-06 09:00","2018-09-07 18:00","연속",null,null,null,201806280115,{"$f":"IF(ISERROR(VLOOKUP(D72,#REF!,13,0)),\"-\",VLOOKUP(D72,#REF!,13,0))","v":"-"}]
[69,"경기","군포","서서울2S/S 345kV #71 BUS GIS","서서울#2S/S 362kV GIS DS 조작불량관련 하자보수","○ DS 조작부측 상부 베어링 교체","2018-09-12 09:00","2018-09-14 18:00","2018-09-12 09:00","2018-09-14 18:00","연속",null,null,null,201806280118,{"$f":"IF(ISERROR(VLOOKUP(D73,#REF!,13,0)),\"-\",VLOOKUP(D73,#REF!,13,0))","v":"-"}]
[70,"경기","군포","서서울S/S #1 M.Tr A","서서울S/S #1변압기 B상 1차 붓싱 누유보수 작업","서서울S/S #1변압기 B상 1차 붓싱 누유보수 작업 - 하자보수","2018-09-10 09:00","2018-09-14 18:00","2018-09-10 09:00","2018-09-14 18:00","연속",null,null,null,201804300203,{"$f":"IF(ISERROR(VLOOKUP(D74,#REF!,13,0)),\"-\",VLOOKUP(D74,#REF!,13,0))","v":"-"}]
[71,"경기","군포","서서울S/S #3 M.Tr A","서서울S/S 345kV 3M.Tr A상 1차 불량 부싱 교체공사","서서울S/S 345kV 3M.Tr A상 1차 불량 부싱 교체 및 3차측 S.Tr, 차단기 점검","2018-09-03 09:00","2018-09-07 18:00","2018-09-03 09:00","2018-09-07 18:00","연속",null,null,null,201804300176,{"$f":"IF(ISERROR(VLOOKUP(D75,#REF!,13,0)),\"-\",VLOOKUP(D75,#REF!,13,0))","v":"-"}]
[72,"경기","동부","곤지암신충주#1 T/L","345kV 곤지암-신충주T/L 접속개소 전선교체공사","345kV 곤지암-신충주T/L 접속개소 전선교체공사","2018-09-27 07:30","2018-10-11 18:00","2018-09-27 07:30","2018-10-11 18:00","연속",null,null,null,201807030146,{"$f":"IF(ISERROR(VLOOKUP(D76,#REF!,13,0)),\"-\",VLOOKUP(D76,#REF!,13,0))","v":"-"}]
[73,"경기","동부","곤지암동서울#1 T/L","2018년 가공송전 순시점검 위탁공사(송전선로 정밀점검)","345kV 곤지암-동서울T/L 1~41호 송전선로 정밀점검","2018-09-03 09:00","2018-09-05 14:00","취소","취소","연속",null,null,null,201807110191,{"$f":"IF(ISERROR(VLOOKUP(D77,#REF!,13,0)),\"-\",VLOOKUP(D77,#REF!,13,0))","v":"-"}]
[74,"경기","동부","곤지암동서울#2 T/L","2018년 가공송전 순시점검 위탁공사(송전선로 정밀점검)","345kV 곤지암-동서울T/L 1~41호 송전선로 정밀점검","2018-09-05 14:00","2018-09-08 14:00","2018-09-05 14:00","2018-09-08 14:00","연속",null,null,null,201807110193,{"$f":"IF(ISERROR(VLOOKUP(D78,#REF!,13,0)),\"-\",VLOOKUP(D78,#REF!,13,0))","v":"-"}]
[75,"경기","동부","곤지암S/S #3 M.Tr A","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 #66BUS 무부하가압용 주변압기","2018-09-29 16:00","2018-09-30 16:00","취소","취소","연속",null,null,null,201807090101,{"$f":"IF(ISERROR(VLOOKUP(D79,#REF!,13,0)),\"-\",VLOOKUP(D79,#REF!,13,0))","v":"-"}]
[76,"경기","성남","신안성서안성#2 T/L","345kV 신안성-서안성T/L OPGW 증설","No.14~서안성S/S OPGW 증설(7기), No.11~19 항공구 48개 설치(9기)","2018-09-01 12:00","2018-09-02 18:00","2018-09-01 12:00","2018-09-02 18:00","연속",null,null,null,201807090203,{"$f":"IF(ISERROR(VLOOKUP(D80,#REF!,13,0)),\"-\",VLOOKUP(D80,#REF!,13,0))","v":"-"}]
[77,"경기","성남","신안성서안성#1 T/L","345kV 신안성-서안성T/L OPGW 증설","No.13~14 OPGW 증설(2기), 항공구 3개 시설","2018-09-01 07:00","2018-09-01 12:00","2018-09-01 07:00","2018-09-01 12:00","연속",null,null,null,201807090195,{"$f":"IF(ISERROR(VLOOKUP(D81,#REF!,13,0)),\"-\",VLOOKUP(D81,#REF!,13,0))","v":"-"}]
[78,"경기","성남","서안성신진천#1 T/L","345kV 신안성-서안성T/L OPGW 증설공사","No.93~서안성S/S OPGW 증설(7기)","2018-09-01 07:00","2018-09-02 18:00","2018-09-01 07:00","2018-09-02 18:00","연속",null,null,null,201807090186,{"$f":"IF(ISERROR(VLOOKUP(D82,#REF!,13,0)),\"-\",VLOOKUP(D82,#REF!,13,0))","v":"-"}]
[79,"경기","성남","신안성서안성#2 T/L","345kV 신안성-서안성T/L OPGW 증설","No.14~서안성S/S OPGW 증설(7기), No.11~19 항공구 48개 설치(9기)","2018-09-08 07:00","2018-09-08 18:00","2018-09-08 07:00","2018-09-08 18:00","연속",null,null,null,201807090222,{"$f":"IF(ISERROR(VLOOKUP(D83,#REF!,13,0)),\"-\",VLOOKUP(D83,#REF!,13,0))","v":"-"}]
[80,"경기","성남","서안성신진천#2 T/L","345kV 신안성-서안성T/L OPGW 증설","No.93~98 항공구 32개 설치(6기)","2018-09-09 07:00","2018-09-09 18:00","2018-09-09 07:00","2018-09-09 18:00","연속",null,null,null,201807090208,{"$f":"IF(ISERROR(VLOOKUP(D84,#REF!,13,0)),\"-\",VLOOKUP(D84,#REF!,13,0))","v":"-"}]
[81,"경기","성남","신안성서안성#1 T/L","345kV 신안성-서안성T/L OPGW 증설","No.13~19 항공구 32개 설치(7기)","2018-09-09 07:00","2018-09-09 18:00","2018-09-09 07:00","2018-09-09 18:00","연속",null,null,null,201807090214,{"$f":"IF(ISERROR(VLOOKUP(D85,#REF!,13,0)),\"-\",VLOOKUP(D85,#REF!,13,0))","v":"-"}]
[82,"경기","성남","서안성신진천#1 T/L","345kV 신안성-서안성T/L OPGW 증설공사","No.93~서안성S/S OPGW 증설(7기), 항공구 48개 시설","2018-09-08 07:00","2018-09-08 18:00","2018-09-08 07:00","2018-09-08 18:00","연속",null,null,null,201807090220,{"$f":"IF(ISERROR(VLOOKUP(D86,#REF!,13,0)),\"-\",VLOOKUP(D86,#REF!,13,0))","v":"-"}]
[83,"경기","성남","서서울#2신성남 #2T/L","345kV 서서울2-신성남#2T/L 송전선로 정밀점검","345kV 서서울2-신성남#2T/L 1~39호 송전선로 정밀점검","2018-09-10 08:00","2018-09-13 18:00","2018-09-10 08:00","2018-09-13 18:00","연속",null,null,null,201807040131,{"$f":"IF(ISERROR(VLOOKUP(D87,#REF!,13,0)),\"-\",VLOOKUP(D87,#REF!,13,0))","v":"-"}]
[84,"경기","성남","신성남S/S #2 M.Tr A","신성남S/S #2M.Tr 2차 GIS 대체","신성남S/S #2M.Tr 2차 GIS 대체, #2M.Tr 보통점검, 2차 LA, NGR보통점검, 3차 LA 하자점검, 7272 보통점검, 누유보수, 전자변히터, 붓싱절연유채유","2018-09-06 09:00","2018-09-21 18:00","2018-09-06 09:00","2018-09-21 18:00","연속",null,null,null,201807090384,{"$f":"IF(ISERROR(VLOOKUP(D88,#REF!,13,0)),\"-\",VLOOKUP(D88,#REF!,13,0))","v":"-"}]
[85,"경기","성남","신안성신수원#2 T/L","신수원S/S 345kV 용량부족 GIS 대체공사","74,755Bay(#1BUS) GIB 설치 안전 이격","2018-09-30 08:00","2018-10-02 18:00","취소","취소","연속",null,null,null,201807050046,{"$f":"IF(ISERROR(VLOOKUP(D89,#REF!,13,0)),\"-\",VLOOKUP(D89,#REF!,13,0))","v":"-"}]
[86,"경기","성남","신수원S/S 345kV #1 BUS","신수원S/S 345kV 용량부족 GIS 대체공사","74,75Bay GIS (#1BUS측) 모선연결","2018-09-28 08:00","2018-10-02 18:00","취소","취소","연속",null,null,null,201807050037,{"$f":"IF(ISERROR(VLOOKUP(D90,#REF!,13,0)),\"-\",VLOOKUP(D90,#REF!,13,0))","v":"-"}]
[87,"경기","성남","신수원S/S #4 M.Tr A","신수원S/S 345kV 용량부족 GIS 대체공사","74Bay(#4M.Tr) GIS 철거 및 설치","2018-09-06 08:00","2018-10-06 18:00","취소","취소","연속",null,null,null,201807050042,{"$f":"IF(ISERROR(VLOOKUP(D91,#REF!,13,0)),\"-\",VLOOKUP(D91,#REF!,13,0))","v":"-"}]
[88,"경기","성남","신안성신수원#2 T/L","신수원S/S 345kV 용량부족 GIS 대체공사","74,755Bay(#1BUS) GIS 철거 안전 이격","2018-09-03 08:00","2018-09-11 18:00","취소","취소","연속",null,null,null,201807050045,{"$f":"IF(ISERROR(VLOOKUP(D92,#REF!,13,0)),\"-\",VLOOKUP(D92,#REF!,13,0))","v":"-"}]
[89,"경기","성남","신수원S/S #3 M.Tr - TIE CB (7500)","신수원S/S 345kV GIS 용량대체공사","345kV GIS #1BUS 교체 및 #3M.Tr용 CB교체","2018-09-01 09:00","2018-11-13 18:00","취소","취소","연속",null,null,null,201807090140,{"$f":"IF(ISERROR(VLOOKUP(D93,#REF!,13,0)),\"-\",VLOOKUP(D93,#REF!,13,0))","v":"-"}]
[90,"경기","성남","신수원S/S #2 M.Tr A","신수원S/S #2M.Tr 2차 보통점검, 붓싱 절연유 채유","신수원S/S #2M.Tr 2차 보통점검, 붓싱 절연유 채유","2018-09-15 09:00","2018-09-15 18:00","취소","취소","당일",null,null,null,201807090426,{"$f":"IF(ISERROR(VLOOKUP(D94,#REF!,13,0)),\"-\",VLOOKUP(D94,#REF!,13,0))","v":"-"}]
[91,"경기","성남","신수원S/S 345kV #1 BUS","신수원S/S 345kV 용량부족 GIS 대체공사","75Bay(#3M.Tr) GIS (#1BUS측) 철거 및 설치","2018-09-01 08:00","2018-09-05 18:00","취소","취소","연속",null,null,null,201807050032,{"$f":"IF(ISERROR(VLOOKUP(D95,#REF!,13,0)),\"-\",VLOOKUP(D95,#REF!,13,0))","v":"-"}]
[92,"경기","성남","신용인삼성 T/L","신수원S/S 345kV 용량부족 GIS 대체공사","74,5Bay(#1BUS) GIB 철거 및 설치 - 안전이격거리 확보","2018-09-12 08:00","2018-09-16 18:00","취소","취소","연속",null,null,null,201807050053,{"$f":"IF(ISERROR(VLOOKUP(D96,#REF!,13,0)),\"-\",VLOOKUP(D96,#REF!,13,0))","v":"-"}]
[93,"경기","직할","화성S/S #4M.Tr A","18년 직할 154kV GCB/GIS 정밀점검공사","화성S/S #4M.Tr 2차 GIS 정밀점검공사","2018-09-20 09:00","2018-09-21 18:00","2018-09-20 09:00","2018-09-21 18:00","연속",null,null,null,201807060239,{"$f":"IF(ISERROR(VLOOKUP(D97,#REF!,13,0)),\"-\",VLOOKUP(D97,#REF!,13,0))","v":"-"}]
[94,"경기","평택","평택T/P #1 M.Tr 1차 CB (7472)","평택화력S/Y 7472CB GIS 보통점검","평택화력S/Y 7472CB GIS 보통점검","2018-09-21 10:00","2018-09-21 18:00","2018-09-21 10:00","2018-09-21 18:00","당일",null,null,null,201807090212,{"$f":"IF(ISERROR(VLOOKUP(D98,#REF!,13,0)),\"-\",VLOOKUP(D98,#REF!,13,0))","v":"-"}]
[95,"경기","평택","평택T/P 화성평택#1T/L CB (7671)","평택화력S/Y 7671CB GIS 보통점검","평택화력S/Y 7671CB GIS 보통점검","2018-09-20 09:00","2018-09-20 18:00","2018-09-20 09:00","2018-09-20 18:00","당일",null,null,null,201807090213,{"$f":"IF(ISERROR(VLOOKUP(D99,#REF!,13,0)),\"-\",VLOOKUP(D99,#REF!,13,0))","v":"-"}]
[96,"경기","평택","평택T/P #1,2 SU Tr 1차-화성평택#2T/L CB (7500)","평택화력S/Y 7500CB GIS 보통점검","평택화력S/Y 7500CB GIS 보통점검","2018-09-14 10:00","2018-09-14 18:00","2018-09-14 10:00","2018-09-14 18:00","당일",null,null,null,201807090210,{"$f":"IF(ISERROR(VLOOKUP(D100,#REF!,13,0)),\"-\",VLOOKUP(D100,#REF!,13,0))","v":"-"}]
[97,"경기","평택","평택T/P 화성평택#2T/L CB (7571)","평택화력S/Y 7571CB GIS 보통점검","평택화력S/Y 7571CB GIS 보통점검","2018-09-13 10:00","2018-09-13 18:00","2018-09-13 10:00","2018-09-13 18:00","당일",null,null,null,201807090209,{"$f":"IF(ISERROR(VLOOKUP(D101,#REF!,13,0)),\"-\",VLOOKUP(D101,#REF!,13,0))","v":"-"}]
[98,"경기","평택","평택T/P #1,2 SU Tr 1차 CB (7572)","평택화력S/Y 7572CB GIS 보통점검","평택화력S/Y 7572CB GIS 보통점검","2018-09-12 10:00","2018-09-12 18:00","2018-09-12 10:00","2018-09-12 18:00","당일",null,null,null,201807090211,{"$f":"IF(ISERROR(VLOOKUP(D102,#REF!,13,0)),\"-\",VLOOKUP(D102,#REF!,13,0))","v":"-"}]
[99,"경기","평택","평택T/P #3,4 SU Tr 1차-#4 M.Tr 1차 CB (7200)","평택화력S/Y 7200CB GIS 보통점검","평택화력S/Y 7200CB GIS 보통점검","2018-09-07 10:00","2018-09-07 18:00","2018-09-07 10:00","2018-09-07 18:00","당일",null,null,null,201807090206,{"$f":"IF(ISERROR(VLOOKUP(D103,#REF!,13,0)),\"-\",VLOOKUP(D103,#REF!,13,0))","v":"-"}]
[100,"경기","평택","평택T/P #4 M.Tr 1차 CB (7271)","평택화력S/Y 7271CB GIS 보통점검","평택화력S/Y 7271CB GIS 보통점검","2018-09-06 10:00","2018-09-06 18:00","2018-09-06 10:00","2018-09-06 18:00","당일",null,null,null,201807090205,{"$f":"IF(ISERROR(VLOOKUP(D104,#REF!,13,0)),\"-\",VLOOKUP(D104,#REF!,13,0))","v":"-"}]
[101,"경기","평택","평택T/P #3,4 SU Tr 1차 CB (7272)","평택화력S/Y 7272CB GIS 보통점검","평택화력S/Y 7272CB GIS 보통점검","2018-09-05 10:00","2018-09-05 18:00","2018-09-05 10:00","2018-09-05 18:00","당일",null,null,null,201807090207,{"$f":"IF(ISERROR(VLOOKUP(D105,#REF!,13,0)),\"-\",VLOOKUP(D105,#REF!,13,0))","v":"-"}]
[102,"강원","강릉","신양양S/S 신양양-양수TL-#1 M.Tr 1차 CB (7100)","2018년 장기 미동작 차단기 조작시험","신양양S/S 장기미동작차단기(7100) 조작시험","2018-09-03 10:00","2018-09-03 14:00","2018-09-03 10:00","2018-09-03 14:00","당일",null,null,null,201807100144,{"$f":"IF(ISERROR(VLOOKUP(D106,#REF!,13,0)),\"-\",VLOOKUP(D106,#REF!,13,0))","v":"-"}]
[103,"강원","강릉","신양양S/S #2 M.Tr 1차-TIE CB (7300)","2018년 장기 미동작 차단기 조작시험","신양양S/S 장기미동작차단기(7300) 조작시험","2018-09-03 14:00","2018-09-03 18:00","2018-09-03 14:00","2018-09-03 18:00","당일",null,null,null,201807100146,{"$f":"IF(ISERROR(VLOOKUP(D107,#REF!,13,0)),\"-\",VLOOKUP(D107,#REF!,13,0))","v":"-"}]
[104,"강원","강릉","신양양S/S 동해-신양양T/L-TIE CB (7200)","2018년 장기 미동작 차단기 조작시험","신양양S/S 장기미동작차단기(7200) 조작시험","2018-09-04 14:00","2018-09-04 18:00","2018-09-04 14:00","2018-09-04 18:00","당일",null,null,null,201807100150,{"$f":"IF(ISERROR(VLOOKUP(D108,#REF!,13,0)),\"-\",VLOOKUP(D108,#REF!,13,0))","v":"-"}]
[105,"강원","강릉","신양양S/S 동해-신양양T/L CB (7271)","2018년 장기 미동작 차단기 조작시험","신양양S/S 장기미동작차단기(7271) 조작시험","2018-09-04 10:00","2018-09-04 14:00","2018-09-04 10:00","2018-09-04 14:00","당일",null,null,null,201807100148,{"$f":"IF(ISERROR(VLOOKUP(D109,#REF!,13,0)),\"-\",VLOOKUP(D109,#REF!,13,0))","v":"-"}]
[106,"강원","동해","동해S/S 345kV #1 BUS","동해S/S STATCOM용 GIS 설치공사","○ 362kV 6300A 63kA GIS × 2CB ○ 기타부대공사 1식","2018-09-13 09:00","2018-09-21 18:00","2018-09-13 09:00","2018-09-21 18:00","연속",null,null,null,201807090163,{"$f":"IF(ISERROR(VLOOKUP(D110,#REF!,13,0)),\"-\",VLOOKUP(D110,#REF!,13,0))","v":"-"}]
[107,"강원","동해","동해S/S #3 M.Tr A","2018년 동해전력지사 변전협력회사 총액공사","1. #3M.Tr 주변압기 보통점검 & 붓싱유 채유 2. 2차 GIS 초기점검(6344) 3. 1, 3차 PT 하자(보통)점검 4. 1, 2, 3차 LA 보통점검","2018-09-05 09:30","2018-09-07 18:00","2018-09-05 09:30","2018-09-07 18:00","매일",null,null,null,201807110201,{"$f":"IF(ISERROR(VLOOKUP(D111,#REF!,13,0)),\"-\",VLOOKUP(D111,#REF!,13,0))","v":"-"}]
[108,"강원","동해","동해S/S #1 M.Tr A","동해S/S 345kV #1M.Tr 대체공사","- 345kV M.Tr 철거/설치 - 기타 부대공사","2018-09-12 09:00","2018-11-02 18:00","취소","취소","연속",null,null,null,201807090110,{"$f":"IF(ISERROR(VLOOKUP(D112,#REF!,13,0)),\"-\",VLOOKUP(D112,#REF!,13,0))","v":"-"}]
[109,"강원","동해","동해삼척GP#2 T/L","345kV 동해-삼척GPT/L 전선접속개소 전선교체공사","No.39~65 전선접속개소 전선교체공사","2018-09-27 08:00","2018-10-10 18:00","2018-09-27 08:00","2018-10-10 18:00","연속",null,null,null,201807130079,{"$f":"IF(ISERROR(VLOOKUP(D113,#REF!,13,0)),\"-\",VLOOKUP(D113,#REF!,13,0))","v":"-"}]
[110,"강원","동해","동해삼척GP#1 T/L","345kV 동해-삼척GPT/L 전선접속개소 전선교체공사","No.39~65 전선접속개소 전선교체공사","2018-09-10 08:00","2018-09-23 18:00","2018-09-10 08:00","2018-09-23 18:00","연속",null,null,null,201807130078,{"$f":"IF(ISERROR(VLOOKUP(D114,#REF!,13,0)),\"-\",VLOOKUP(D114,#REF!,13,0))","v":"-"}]
[111,"강원","태백","신태백S/S #3 M.Tr 2차 CB (7671)","18~19년 태백전력지사 변전정비 총액공사","신태백S/S 345kV 7671CB 보통점검","2018-09-07 10:00","2018-09-07 18:00","2018-09-07 10:00","2018-09-07 18:00","당일",null,null,null,201807090263,{"$f":"IF(ISERROR(VLOOKUP(D115,#REF!,13,0)),\"-\",VLOOKUP(D115,#REF!,13,0))","v":"-"}]
[112,"강원","태백","신태백S/S #2M.Tr 2차-TIE CB (7300)","18~19년 태백전력지사 변전정비 총액공사","신태백S/S 345kV 7300CB 보통점검","2018-09-06 10:00","2018-09-06 18:00","2018-09-06 10:00","2018-09-06 18:00","당일",null,null,null,201807090260,{"$f":"IF(ISERROR(VLOOKUP(D116,#REF!,13,0)),\"-\",VLOOKUP(D116,#REF!,13,0))","v":"-"}]
[113,"강원","태백","신태백S/S #2 M.Tr 2차 CB (7371)","18~19년 태백전력지사 변전정비 총액공사","신태백S/S 345kV 7371CB 보통점검","2018-09-05 10:00","2018-09-05 18:00","2018-09-05 10:00","2018-09-05 18:00","당일",null,null,null,201807090256,{"$f":"IF(ISERROR(VLOOKUP(D117,#REF!,13,0)),\"-\",VLOOKUP(D117,#REF!,13,0))","v":"-"}]
[114,"충북","직할","신제천S/S #2 M.Tr A","신제천 #2M.Tr 주변압기, GIS, 기타설비 점검 및 DS 하자대체","- 345kV 주변압기 보통점검 - 1,2차 GIS 초기점검 - 1,3차 LA 대체 및 2차 LA 점검 - 3차 PT 초기점검","2018-09-11 09:00","2018-09-15 18:00","2018-09-11 09:00","2018-09-15 18:00","연속",null,null,null,201807040090,{"$f":"IF(ISERROR(VLOOKUP(D118,#REF!,13,0)),\"-\",VLOOKUP(D118,#REF!,13,0))","v":"-"}]
[115,"충북","직할","신제천S/S #3 M.Tr A","충북 직할 변전협력회사 총액공사","#3M.Tr 3차측 23kV VCB 대체(4대), 23kV #11 Sh.R 대체","2018-09-03 09:00","2018-09-09 18:00","2018-09-03 09:00","2018-09-09 18:00","연속",null,null,null,201807060019,{"$f":"IF(ISERROR(VLOOKUP(D119,#REF!,13,0)),\"-\",VLOOKUP(D119,#REF!,13,0))","v":"-"}]
[116,"충북","직할","신제천신충주#2 T/L","신제천S/S 신제천신충주#2T/L DS 하자대체 및 GIS 초기점검","- 7361,7301 DS 설비개선품 대체 - 362kV GIS(7371,7300) 초기점검","2018-09-11 09:00","2018-09-14 18:00","2018-09-11 09:00","2018-09-14 18:00","연속",null,null,null,201806200112,{"$f":"IF(ISERROR(VLOOKUP(D120,#REF!,13,0)),\"-\",VLOOKUP(D120,#REF!,13,0))","v":"-"}]
[117,"충북","직할","신제천S/S 345kV #2 BUS","345kV 신제천 SVC용 GIS 설치공사","345kV 63kA 6300A 설치 2CB 기타부대공사 1식","2018-09-11 09:00","2018-09-18 18:00","2018-09-11 09:00","2018-09-18 18:00","연속",null,null,null,201807030193,{"$f":"IF(ISERROR(VLOOKUP(D121,#REF!,13,0)),\"-\",VLOOKUP(D121,#REF!,13,0))","v":"-"}]
[118,"충북","직할","신제천신영주#1 T/L","신제천S/S 신제천신영주#1T/L DS 하자대체 및 GIS 초기점검","- 7661,7601 DS 설비개선품 대체 - 362kV GIS(7671,7600) 초기점검","2018-09-19 09:00","2018-09-21 18:00","2018-09-19 09:00","2018-09-21 18:00","연속",null,null,null,201806200111,{"$f":"IF(ISERROR(VLOOKUP(D122,#REF!,13,0)),\"-\",VLOOKUP(D122,#REF!,13,0))","v":"-"}]
[119,"충북","청주","신옥천S/S #3 M.Tr A","18~19년 청주전력 변전협력회사 총액공사","345kV #3M.Tr 하자점검 및 1차 GIS 초기점검","2018-09-27 09:30","2018-09-28 18:00","2018-09-27 09:30","2018-09-28 18:00","연속",null,null,null,201807120099,{"$f":"IF(ISERROR(VLOOKUP(D123,#REF!,13,0)),\"-\",VLOOKUP(D123,#REF!,13,0))","v":"-"}]
[120,"충북","청주","청원S/S #2 M.Tr A","청원S/S 345kV 장기사용 GIS 대체공사(전문)","○ 345kV GIS(가스절연개폐장치) 철거, 설치 × 1식 - GIS(40kA 4000A) 철거 × 6CB - GIS(50kA 4000A) 설치 × 6CB ○ 설치 GIS 기초 보강공사 × 1식 ○ 제어케이블 철거, 설치 및 기타 부대공사 × 1식","2018-09-03 09:00","2018-11-30 18:00","2018-09-03 09:00","2018-11-30 18:00","연속",null,null,null,201807030140,{"$f":"IF(ISERROR(VLOOKUP(D124,#REF!,13,0)),\"-\",VLOOKUP(D124,#REF!,13,0))","v":"-"}]
[121,"충북","청주","세종청원#1 T/L","청원S/S 345kV 장기사용 GIS 대체공사(전문)","○ 345kV GIS(가스절연개폐장치) 철거, 설치 × 1식 - GIS(40kA 4000A) 철거 × 6CB - GIS(50kA 4000A) 설치 × 6CB ○ 설치 GIS 기초 보강공사 × 1식 ○ 제어케이블 철거, 설치 및 기타 부대공사 × 1식","2018-09-03 09:00","2018-11-30 18:00","2018-09-03 09:00","2018-11-30 18:00","연속",null,null,null,201807030142,{"$f":"IF(ISERROR(VLOOKUP(D125,#REF!,13,0)),\"-\",VLOOKUP(D125,#REF!,13,0))","v":"-"}]
[122,"대전충남","대전","신계룡청양 T/L","[송전] 345kV 신옥천-청양T/L 전선교체공사","[송전] 345kV 신계룡-청양T/L 전선접속개소 전선교체","2018-09-16 07:00","2018-10-03 18:00","취소","취소","연속",null,null,null,201807030234,{"$f":"IF(ISERROR(VLOOKUP(D126,#REF!,13,0)),\"-\",VLOOKUP(D126,#REF!,13,0))","v":"-"}]
[123,"대전충남","대전","신계룡S/S #2 M.Tr A","신계룡S/S 345kV #2M.Tr보호반,74BAY B/F반교체 및 병행","신계룡S/S 345kV #2M.Tr보호반,74BAY B/F반교체 및 병행작업","2018-09-12 09:00","2018-09-20 18:00","2018-09-12 09:00","2018-09-20 18:00","연속",null,null,null,201807050202,{"$f":"IF(ISERROR(VLOOKUP(D127,#REF!,13,0)),\"-\",VLOOKUP(D127,#REF!,13,0))","v":"-"}]
[124,"대전충남","서산","북당진S/S GSEPS #4-1호기 -TIE CB (7700)","18년 변전협력회사 총액공사","345kV GIS 초기점검","2018-09-07 09:00","2018-09-07 18:00","2018-09-07 09:00","2018-09-07 18:00","당일",null,null,null,201807100143,{"$f":"IF(ISERROR(VLOOKUP(D128,#REF!,13,0)),\"-\",VLOOKUP(D128,#REF!,13,0))","v":"-"}]
[125,"대전충남","서산","북당진S/S GSEPS #4-2호기 CB (7872)","18년 변전협력회사 총액공사","345kV GIS 초기점검","2018-09-04 09:00","2018-09-04 18:00","2018-09-04 09:00","2018-09-04 18:00","당일",null,null,null,201807100139,{"$f":"IF(ISERROR(VLOOKUP(D129,#REF!,13,0)),\"-\",VLOOKUP(D129,#REF!,13,0))","v":"-"}]
[126,"대전충남","서산","북당진S/S GSEPS #4-2호기 -TIE CB (7800)","18년 변전협력회사 총액공사","345kV GIS 초기점검","2018-09-05 09:00","2018-09-05 18:00","2018-09-05 09:00","2018-09-05 18:00","당일",null,null,null,201807100140,{"$f":"IF(ISERROR(VLOOKUP(D130,#REF!,13,0)),\"-\",VLOOKUP(D130,#REF!,13,0))","v":"-"}]
[127,"대전충남","서산","북당진S/S GSEPS #4-1호기 CB (7772)","18년 변전협력회사 총액공사","345kV GIS 초기점검","2018-09-06 09:00","2018-09-06 18:00","2018-09-06 09:00","2018-09-06 18:00","당일",null,null,null,201807100142,{"$f":"IF(ISERROR(VLOOKUP(D131,#REF!,13,0)),\"-\",VLOOKUP(D131,#REF!,13,0))","v":"-"}]
[128,"대전충남","서산","신당진개폐소 태안TP#1-연락#1T/L TIE CB (7A00)","18년 변전협력회사 총액공사","345kV GIS 하자점검","2018-09-20 09:00","2018-09-20 18:00","2018-09-20 09:00","2018-09-20 18:00","당일",null,null,null,201807100159,{"$f":"IF(ISERROR(VLOOKUP(D132,#REF!,13,0)),\"-\",VLOOKUP(D132,#REF!,13,0))","v":"-"}]
[129,"대전충남","서산","신당진개폐소 태안TP#1T/L CB (7A71)","18년 변전협력회사 총액공사","345kV GIS 하자점검","2018-09-19 09:00","2018-09-19 18:00","2018-09-19 09:00","2018-09-19 18:00","당일",null,null,null,201807100158,{"$f":"IF(ISERROR(VLOOKUP(D133,#REF!,13,0)),\"-\",VLOOKUP(D133,#REF!,13,0))","v":"-"}]
[130,"대전충남","서산","신당진개폐소 신당진연락#1T/L CB (7A72)","18년 변전협력회사 총액공사","345kV GIS 하자점검","2018-09-21 09:00","2018-09-21 18:00","2018-09-21 09:00","2018-09-21 18:00","당일",null,null,null,201807100160,{"$f":"IF(ISERROR(VLOOKUP(D134,#REF!,13,0)),\"-\",VLOOKUP(D134,#REF!,13,0))","v":"-"}]
[131,"대전충남","서산","신당진S/S 75-76 BUS SECTION CB (75-76-0)","서산PO 735/345kV GIS 점검","서산PO 735/345 GIS 점검","2018-09-10 09:00","2018-09-14 18:00","2018-09-10 09:00","2018-09-14 18:00","연속",null,null,null,201807100162,{"$f":"IF(ISERROR(VLOOKUP(D135,#REF!,13,0)),\"-\",VLOOKUP(D135,#REF!,13,0))","v":"-"}]
[132,"대전충남","서산","신당진S/S 70-71 BUS SECTION CB (70-71-0)","서산PO 735/345kV GIS 점검","서산PO 735/345 GIS 점검","2018-09-03 09:00","2018-09-07 18:00","2018-09-03 09:00","2018-09-07 18:00","연속",null,null,null,201807100161,{"$f":"IF(ISERROR(VLOOKUP(D136,#REF!,13,0)),\"-\",VLOOKUP(D136,#REF!,13,0))","v":"-"}]
[133,"대전충남","서산","신서산S/S 345kV #5 Sh.R","18년 변전협력회사 총액공사","345kv Sh.R 보통점검","2018-09-19 09:00","2018-09-19 18:00","2018-09-19 09:00","2018-09-19 18:00","당일",null,null,null,201807100152,{"$f":"IF(ISERROR(VLOOKUP(D137,#REF!,13,0)),\"-\",VLOOKUP(D137,#REF!,13,0))","v":"-"}]
[134,"대전충남","서산","신서산S/S 345kV #3 Sh.R CB (7571)","서산 PO 345/765kV GIS 점검공사","신서산 345kV 7571 GIS 정밀점검","2018-09-17 09:00","2018-09-21 18:00","2018-09-17 09:00","2018-09-21 18:00","연속",null,null,null,201807120006,{"$f":"IF(ISERROR(VLOOKUP(D138,#REF!,13,0)),\"-\",VLOOKUP(D138,#REF!,13,0))","v":"-"}]
[135,"대전충남","서산","신서산S/S 신서산-신당진#1T/L CB (7872)","18년 변전협력회사 총액공사","345kv GIS 보통점검","2018-09-21 09:00","2018-09-21 18:00","2018-09-21 09:00","2018-09-21 18:00","당일",null,null,null,201807100154,{"$f":"IF(ISERROR(VLOOKUP(D139,#REF!,13,0)),\"-\",VLOOKUP(D139,#REF!,13,0))","v":"-"}]
[136,"대전충남","서산","신서산S/S #4M.Tr2차-신서산신당진#1T/L CB (7800)","18년 변전협력회사 총액공사","신서산 345kV 7800 CB 보통점검","2018-09-20 09:00","2018-09-20 18:00","2018-09-20 09:00","2018-09-20 18:00","당일",null,null,null,201807180008,{"$f":"IF(ISERROR(VLOOKUP(D140,#REF!,13,0)),\"-\",VLOOKUP(D140,#REF!,13,0))","v":"-"}]
[137,"대전충남","서산","태안T/P TIE-3호기 1차 CB (7300)","18년 변전협력회사 총액공사","345kV GIS 하자점검","2018-09-18 09:00","2018-09-18 18:00","2018-09-18 09:00","2018-09-18 18:00","당일",null,null,null,201807100149,{"$f":"IF(ISERROR(VLOOKUP(D141,#REF!,13,0)),\"-\",VLOOKUP(D141,#REF!,13,0))","v":"-"}]
[138,"대전충남","서산","태안T/P TIE-1호기 1차CB(신) (7100)","18년 변전협력회사 총액공사","345kV GIS 하자점검","2018-09-11 09:00","2018-09-11 18:00","2018-09-11 09:00","2018-09-11 18:00","당일",null,null,null,201807100145,{"$f":"IF(ISERROR(VLOOKUP(D142,#REF!,13,0)),\"-\",VLOOKUP(D142,#REF!,13,0))","v":"-"}]
[139,"대전충남","서산","태안T/P 75-76-0 SEC CB (75-76-0)","18년 변전협력회사 총액공사","345kV GIS 초기점검","2018-09-04 09:00","2018-09-04 18:00","2018-09-20 09:00","2018-09-20 18:00","당일",null,null,null,201807100138,{"$f":"IF(ISERROR(VLOOKUP(D143,#REF!,13,0)),\"-\",VLOOKUP(D143,#REF!,13,0))","v":"-"}]
[140,"대전충남","서산","태안T/P 70-71-0 SEC CB (70-71-0)","18년 변전협력회사 총액공사","345kV GIS 초기점검","2018-09-03 09:00","2018-09-03 18:00","2018-09-19 09:00","2018-09-19 18:00","당일",null,null,null,201807100137,{"$f":"IF(ISERROR(VLOOKUP(D144,#REF!,13,0)),\"-\",VLOOKUP(D144,#REF!,13,0))","v":"-"}]
[141,"대전충남","서산","태안T/P 3호기 1차 CB (7372)","18년 변전협력회사 총액공사","345kV GIS 하자점검","2018-09-17 09:00","2018-09-17 18:00","2018-09-17 09:00","2018-09-17 18:00","당일",null,null,null,201807100147,{"$f":"IF(ISERROR(VLOOKUP(D145,#REF!,13,0)),\"-\",VLOOKUP(D145,#REF!,13,0))","v":"-"}]
[142,"대전충남","아산","신온양S/S 신온양-서서울 #2 T/L - #4 M.Tr 1차 CB (7700)","신온양S/S 7500,7700,7800 GIS 에어체크밸브 교체","신온양S/S 7500,7700,7800 GIS 에어체크밸브 교체","2018-09-19 12:00","2018-09-19 15:00","2018-09-19 12:00","2018-09-19 15:00","당일",null,null,null,201807090354,{"$f":"IF(ISERROR(VLOOKUP(D146,#REF!,13,0)),\"-\",VLOOKUP(D146,#REF!,13,0))","v":"-"}]
[143,"대전충남","아산","신온양S/S 신온양서서울#1T/L-신온양신탕정#2T/L CB (7800)","신온양S/S 7500,7700,7800 GIS 에어체크밸브 교체","신온양S/S 7500,7700,7800 GIS 에어체크밸브 교체","2018-09-19 15:00","2018-09-19 18:00","2018-09-19 15:00","2018-09-19 18:00","당일",null,null,null,201807090357,{"$f":"IF(ISERROR(VLOOKUP(D147,#REF!,13,0)),\"-\",VLOOKUP(D147,#REF!,13,0))","v":"-"}]
[144,"대전충남","아산","신온양S/S 청양-신온양 #1 T/L - #3 M.Tr 1차 CB (7500)","신온양S/S 7500,7700,7800 GIS 에어체크밸브 교체","신온양S/S 7500,7700,7800 GIS 에어체크밸브 교체","2018-09-19 09:00","2018-09-19 12:00","2018-09-19 09:00","2018-09-19 12:00","당일",null,null,null,201807090347,{"$f":"IF(ISERROR(VLOOKUP(D148,#REF!,13,0)),\"-\",VLOOKUP(D148,#REF!,13,0))","v":"-"}]
[145,"대전충남","아산","신탕정S/S #3 M.Tr A","신탕정S/S #3M.Tr실 상부풍도실 환기팬 교체","신탕정S/S #3M.Tr실 상부풍도실 환기팬 2대 교체","2018-09-20 09:00","2018-09-20 18:00","2018-09-20 09:00","2018-09-20 18:00","당일",null,null,null,201807100112,{"$f":"IF(ISERROR(VLOOKUP(D149,#REF!,13,0)),\"-\",VLOOKUP(D149,#REF!,13,0))","v":"-"}]
[146,"대전충남","청양","보령T/P 345kV #76 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7371 GIS 교체 ○ 보령화력 345kV 7300 GIS 교체 ○ 보령화력 345kV 7372 GIS 교체","2018-09-02 09:00","2018-09-02 18:00","2018-09-02 09:00","2018-09-02 18:00","당일",null,null,null,201806080017,{"$f":"IF(ISERROR(VLOOKUP(D150,#REF!,13,0)),\"-\",VLOOKUP(D150,#REF!,13,0))","v":"-"}]
[147,"대전충남","청양","청양S/S 청양-보령화력#2T/L CB (7672)","청양S/S 362kV GIS 전자변 러버히터 설치","청양S/S 362kV GIS 전자변 러버히터 설치(7672CB)","2018-09-03 09:00","2018-09-03 18:00","2018-09-18 09:00","2018-09-18 18:00","당일",null,null,null,201807060207,{"$f":"IF(ISERROR(VLOOKUP(D151,#REF!,13,0)),\"-\",VLOOKUP(D151,#REF!,13,0))","v":"-"}]
[148,"대전충남","청양","청양S/S 청양-보령화력#1T/L CB (7172)","청양S/S 362kV GIS 전자변 러버히터 설치","청양S/S 362kV GIS 전자변 러버히터 설치(7172CB)","2018-09-05 09:00","2018-09-05 18:00","2018-09-05 09:00","2018-09-05 18:00","당일",null,null,null,201807060210,{"$f":"IF(ISERROR(VLOOKUP(D152,#REF!,13,0)),\"-\",VLOOKUP(D152,#REF!,13,0))","v":"-"}]
[149,"대전충남","청양","청양S/S 청양-신보령T/L CB (7271)","청양S/S 362kV GIS 전자변 러버히터 설치","청양S/S 362kV GIS 전자변 러버히터 설치(7271CB)","2018-09-11 09:00","2018-09-11 18:00","2018-09-19 09:00","2018-09-19 18:00","당일",null,null,null,201807050141,{"$f":"IF(ISERROR(VLOOKUP(D153,#REF!,13,0)),\"-\",VLOOKUP(D153,#REF!,13,0))","v":"-"}]
[150,"대전충남","청양","청양S/S 청양-신보령T/L-청양보령복합TL CB (7200)","청양S/S 362kV GIS 전자변 러버히터 설치","청양S/S 362kV GIS 전자변 러버히터 설치(7200CB)","2018-09-12 09:00","2018-09-12 18:00","2018-09-12 09:00","2018-09-12 18:00","당일",null,null,null,201807050142,{"$f":"IF(ISERROR(VLOOKUP(D154,#REF!,13,0)),\"-\",VLOOKUP(D154,#REF!,13,0))","v":"-"}]
[151,"대전충남","청양","청양S/S 청양-보령복합T/L CB (7272)","청양S/S 362kV GIS 전자변 러버히터 설치","청양S/S 362kV GIS 전자변 러버히터 설치(7272CB)","2018-09-13 09:00","2018-09-13 18:00","2018-10-11 09:00","2018-10-11 18:00","당일",null,null,null,201807050249,{"$f":"IF(ISERROR(VLOOKUP(D155,#REF!,13,0)),\"-\",VLOOKUP(D155,#REF!,13,0))","v":"-"}]
[152,"대전충남","청양","청양S/S 70-71-0 SEC CB (70-71-0)","청양S/S 362kV GIS 전자변 러버히터 설치","청양S/S 362kV GIS 전자변 러버히터 설치(70-71-0 SEC CB)","2018-09-14 09:00","2018-09-14 18:00","2018-09-14 09:00","2018-09-14 18:00","당일",null,null,null,201807050254,{"$f":"IF(ISERROR(VLOOKUP(D156,#REF!,13,0)),\"-\",VLOOKUP(D156,#REF!,13,0))","v":"-"}]
[153,"대전충남","청양","청양S/S 75-76-0 SEC CB (75-76-0)","청양S/S 362kV GIS 전자변 러버히터 설치","청양S/S 362kV GIS 전자변 러버히터 설치(75-76-0 SEC CB)","2018-09-17 09:00","2018-09-17 18:00","2018-09-17 09:00","2018-09-17 18:00","당일",null,null,null,201807050251,{"$f":"IF(ISERROR(VLOOKUP(D157,#REF!,13,0)),\"-\",VLOOKUP(D157,#REF!,13,0))","v":"-"}]
[154,"대전충남","청양","청양신온양#1 T/L","345kV 북당진-신탕정T/L 건설공사(2공구)","345kV 북당진-신탕정T/L 건설공사(2공구) - 345kV 청양-신온양#1T/L 신설 No.145 긴선 - 345kV 청양-신온양#1T/L 기설 No.150 긴선","2018-09-18 07:00","2018-09-21 18:00","2018-09-18 07:00","2018-09-21 18:00","연속",null,null,null,201807190049,{"$f":"IF(ISERROR(VLOOKUP(D158,#REF!,13,0)),\"-\",VLOOKUP(D158,#REF!,13,0))","v":"-"}]
[155,"전북","군산","군산S/S #3 M.Tr A","군산PO 345kV 주변압기 정밀점검공사","345V M.Tr 정밀점검 × 단상3대 (1Bank)","2018-09-03 09:00","2018-09-06 18:00","2018-09-03 09:00","2018-09-06 18:00","연속",null,null,null,201807030052,{"$f":"IF(ISERROR(VLOOKUP(D159,#REF!,13,0)),\"-\",VLOOKUP(D159,#REF!,13,0))","v":"-"}]
[156,"전북","군산","군산S/S #3 M.Tr A","2018년 군산P/O 170kV GIS 정밀점검공사","군산S/S 345kV #3M.tr 2차 GIS 차단기 정밀점검","2018-09-13 09:00","2018-09-14 18:00","2018-09-13 09:00","2018-09-14 18:00","연속",null,null,null,201807190027,{"$f":"IF(ISERROR(VLOOKUP(D160,#REF!,13,0)),\"-\",VLOOKUP(D160,#REF!,13,0))","v":"-"}]
[157,"전북","군산","청양군산#2 T/L","항공장애표시구설치공사","항공구설치","2018-09-06 07:00","2018-09-08 18:00","2018-09-06 07:00","2018-09-08 18:00","매일",null,null,null,201805300259,{"$f":"IF(ISERROR(VLOOKUP(D161,#REF!,13,0)),\"-\",VLOOKUP(D161,#REF!,13,0))","v":"-"}]
[158,"전북","김제","군산신김제#2 T/L","모자익배전반 교체공사(조작시험)","장기사용 모자익배전반교체 -> 디축모, 집감반구성","2018-09-13 09:00","2018-09-14 18:00","2018-09-13 09:00","2018-09-14 18:00","연속",null,null,null,201807180007,{"$f":"IF(ISERROR(VLOOKUP(D162,#REF!,13,0)),\"-\",VLOOKUP(D162,#REF!,13,0))","v":"-"}]
[159,"전북","김제","신김제S/S #1 M.Tr A","모자익배전반 교체공사(조작시험)","장기사용 모자익배전반교체 -> 디축모, 집감반구성","2018-09-10 09:00","2018-09-14 18:00","2018-09-10 09:00","2018-09-14 18:00","연속",null,null,null,201807180005,{"$f":"IF(ISERROR(VLOOKUP(D163,#REF!,13,0)),\"-\",VLOOKUP(D163,#REF!,13,0))","v":"-"}]
[160,"전북","김제","신김제한빛NP#1 T/L","모자익배전반 교체공사(조작시험)","장기사용 모자익배전반교체 -> 디축모, 집감반구성후 조작시험","2018-09-20 09:00","2018-09-21 18:00","취소","취소","연속",null,null,null,201807180011,{"$f":"IF(ISERROR(VLOOKUP(D164,#REF!,13,0)),\"-\",VLOOKUP(D164,#REF!,13,0))","v":"-"}]
[161,"전북","김제","신김제한빛NP#1 T/L","345kV 신김제-한빛#1T/L 전력선 교체공사","전력선교체 : No.49~202호 중 10개 내장-내장 구간 13.897C-km 가공지선 교체 : No.49~200호 중 7개 내장-내장 구간 11.293km 스페이서댐퍼, 항공구교체 등 부대공사","2018-09-28 07:00","2018-10-24 18:00","2018-09-28 07:00","2018-10-24 18:00","연속",null,null,null,201807120005,{"$f":"IF(ISERROR(VLOOKUP(D165,#REF!,13,0)),\"-\",VLOOKUP(D165,#REF!,13,0))","v":"-"}]
[162,"전북","김제","신김제S/S #4 M.Tr A","345kV 신김제S/S 154kV #61, #62M.Tr 증설","154kV #61,#62M.Tr 기기기초 설치 안전이격확보 154kV #61,#62M.Tr용 GIS 기기기초 설치 안전이격확보","2018-09-01 07:00","2018-09-07 18:00","2018-09-01 07:00","2018-09-07 18:00","연속",null,null,null,201806060006,{"$f":"IF(ISERROR(VLOOKUP(D166,#REF!,13,0)),\"-\",VLOOKUP(D166,#REF!,13,0))","v":"-"}]
[163,"전북","김제","신김제S/S #2 M.Tr A","모자익배전반 교체공사(조작시험)","장기사용 모자익배전반교체 -> 디축모, 집감반구성후 조작시험","2018-09-17 09:00","2018-09-21 18:00","2018-09-17 09:00","2018-09-21 18:00","연속",null,null,null,201807180010,{"$f":"IF(ISERROR(VLOOKUP(D167,#REF!,13,0)),\"-\",VLOOKUP(D167,#REF!,13,0))","v":"-"}]
[164,"전북","김제","군산신김제#1 T/L","모자익배전반 교체공사(조작시험)","장기사용 모자익배전반교체 -> 디축모, 집감반구성","2018-09-15 09:00","2018-09-16 18:00","2018-09-15 09:00","2018-09-16 18:00","연속",null,null,null,201807180009,{"$f":"IF(ISERROR(VLOOKUP(D168,#REF!,13,0)),\"-\",VLOOKUP(D168,#REF!,13,0))","v":"-"}]
[165,"전북","직할","북경남무주양수 T/L","345kV 북경남-무주양수T/L 애자 절연저항 측정","345kV 북경남-무주양수T/L 애자 절연저항 측정","2018-09-17 08:00","2018-09-18 18:00","2018-09-17 08:00","2018-09-18 18:00","연속",null,null,null,201807050039,{"$f":"IF(ISERROR(VLOOKUP(D169,#REF!,13,0)),\"-\",VLOOKUP(D169,#REF!,13,0))","v":"-"}]
[166,"전북","직할","무주P/P #1M.Tr 1차 CB (7172)","무주P/P #1M.Tr 1차측 CB(7172) 누유개소 보수","무주P/P #1M.Tr 1차 CB(7172) B상 유압 S/W Block 교체 : 1식","2018-09-28 10:00","2018-09-28 18:00","2018-09-28 10:00","2018-09-28 18:00","당일",null,null,null,201807160134,{"$f":"IF(ISERROR(VLOOKUP(D170,#REF!,13,0)),\"-\",VLOOKUP(D170,#REF!,13,0))","v":"-"}]
[167,"전북","직할","신남원광양#2 T/L","345kV 신남원-광양T/L 안전이격 확보공사","가. 철탑철거 : 2기 [No.214(T-14), No.216(F-21)] 나. 철탑설치 : 2기 [No.214(C2-26), No.216(SF-36)] 다. 전력선 교체 : 1.790km [ACSR 480㎟ x 2B] , 12가닥 라. 가선로 구성 : 가철탑 1기 (No.216)","2018-09-17 09:00","2018-09-23 18:00","2018-09-17 09:00","2018-09-23 18:00","연속",null,null,null,201807170103,{"$f":"IF(ISERROR(VLOOKUP(D171,#REF!,13,0)),\"-\",VLOOKUP(D171,#REF!,13,0))","v":"-"}]
[168,"전북","직할","신남원광양#1 T/L","345kV 신남원-광양T/L 안전이격 확보공사","가. 철탑철거 : 2기 [No.214(T-14), No.216(F-21)] 나. 철탑설치 : 2기 [No.214(C2-26), No.216(SF-36)] 다. 전력선 교체 : 1.790km [ACSR 480㎟ x 2B] , 12가닥 라. 가선로 구성 : 가철탑 1기 (No.216)","2018-09-10 09:00","2018-09-16 18:00","취소","취소","연속",null,null,null,201807170102,{"$f":"IF(ISERROR(VLOOKUP(D172,#REF!,13,0)),\"-\",VLOOKUP(D172,#REF!,13,0))","v":"-"}]
[169,"전북","직할","신남원의령#2 T/L","신남원S/S 362kV GIS CB(7400) A상 가스누기 점검공사 외","○ 362kV GIS CB(7400) A상 가스누기 보수작업 ○ 362kV DS 단자대 교체(9EA)","2018-09-04 10:00","2018-09-06 18:00","2018-09-04 10:00","2018-09-06 18:00","연속",null,null,null,201807060066,{"$f":"IF(ISERROR(VLOOKUP(D173,#REF!,13,0)),\"-\",VLOOKUP(D173,#REF!,13,0))","v":"-"}]
[170,"전북","직할","신남원한빛NP#1 T/L","신남원S/S 362kV DS 조작함 단자대 교체공사(7272)","○ 362kV 7272 Bay 양단, 선로인출 DS 단자대 교체(8EA)","2018-09-21 09:00","2018-09-21 18:00","취소","취소","연속",null,null,null,201807100050,{"$f":"IF(ISERROR(VLOOKUP(D174,#REF!,13,0)),\"-\",VLOOKUP(D174,#REF!,13,0))","v":"-"}]
[171,"전북","직할","신남원의령#1 T/L","신남원S/S 362kV DS 조작함 단자대 교체공사(7300,7371)","○ 362kV 7300 Bay 양단 DS 단자대 교체(5EA) ○ 362kV 7371 Bay 양단, 선로인출 DS 단자대 교체(6EA)","2018-09-19 07:00","2018-09-19 18:00","2018-09-14 07:00","2018-09-14 18:00","당일",null,null,null,201807100051,{"$f":"IF(ISERROR(VLOOKUP(D175,#REF!,13,0)),\"-\",VLOOKUP(D175,#REF!,13,0))","v":"-"}]
[172,"전북","직할","신남원S/S 신남원-신광주#2 - TIE GIS","신남원S/S 362kV DS 조작함 단자대 교체공사(7800)","○ 362kV 7800 Bay 양단 DS 단자대 교체(6EA)","2018-09-18 09:00","2018-09-18 18:00","2018-09-18 09:00","2018-09-18 18:00","당일",null,null,null,201807100049,{"$f":"IF(ISERROR(VLOOKUP(D176,#REF!,13,0)),\"-\",VLOOKUP(D176,#REF!,13,0))","v":"-"}]
[173,"전북","직할","신남원신광주#2 T/L","신남원S/S 362kV DS 조작함 단자대 교체공사(7871)","○ 362kV 7871 Bay 양단, 선로인출 DS 단자대 교체(9EA)","2018-09-17 13:00","2018-09-17 19:00","2018-09-17 13:00","2018-09-17 19:00","당일",null,null,null,201807100048,{"$f":"IF(ISERROR(VLOOKUP(D177,#REF!,13,0)),\"-\",VLOOKUP(D177,#REF!,13,0))","v":"-"}]
[174,"전북","직할","신남원S/S #1 M.Tr 1차 GIS","신남원S/S 362kV DS 조작함 단자대 교체공사(7772)","○ 362kV 7772 Bay 7752 DS 단자대 교체(3EA)","2018-09-17 09:00","2018-09-17 13:00","2018-09-17 09:00","2018-09-17 13:00","당일",null,null,null,201807100047,{"$f":"IF(ISERROR(VLOOKUP(D178,#REF!,13,0)),\"-\",VLOOKUP(D178,#REF!,13,0))","v":"-"}]
[175,"전북","직할","신남원신광주#1 T/L","신남원S/S 362kV DS 조작함 단자대 교체공사(7700,7771)","○ 362kV 7700 Bay 양단 DS 단자대 교체(2EA) ○ 362kV 7771 Bay 양단, 선로인출 DS 단자대 교체(7EA)","2018-09-14 09:00","2018-09-14 18:00","2018-09-14 09:00","2018-09-14 18:00","당일",null,null,null,201807100046,{"$f":"IF(ISERROR(VLOOKUP(D179,#REF!,13,0)),\"-\",VLOOKUP(D179,#REF!,13,0))","v":"-"}]
[176,"전북","직할","신옥천신남원#1 T/L","신남원S/S 362kV DS 조작함 단자대 교체공사(7200,7271)","○ 362kV 7200 Bay 양단 DS 단자대 교체(5EA) ○ 362kV 7271 Bay 양단, 선로인출 DS 단자대 교체(5EA)","2018-09-11 09:00","2018-09-11 18:00","2018-09-11 09:00","2018-09-11 18:00","당일",null,null,null,201807100038,{"$f":"IF(ISERROR(VLOOKUP(D180,#REF!,13,0)),\"-\",VLOOKUP(D180,#REF!,13,0))","v":"-"}]
[177,"전북","직할","신옥천신남원#2 T/L","신남원S/S 362kV DS 조작함 단자대 교체공사(7100,7171)","○ 362kV 7100 Bay 양단 DS 단자대 교체(5EA) ○ 362kV 7171 Bay 양단, 선로인출 DS 단자대 교체(4EA)","2018-09-07 09:00","2018-09-07 18:00","2018-09-07 09:00","2018-09-07 18:00","당일",null,null,null,201807100037,{"$f":"IF(ISERROR(VLOOKUP(D181,#REF!,13,0)),\"-\",VLOOKUP(D181,#REF!,13,0))","v":"-"}]
[178,"전북","직할","신남원한빛NP#2 T/L","신남원S/S 362kV DS 조작함 단자대 교체공사(7172)","○ 362kV 7172 Bay 양단, 선로인출 DS 단자대 교체(7EA)","2018-09-10 09:00","2018-09-10 18:00","취소","취소","연속",null,null,null,201807100052,{"$f":"IF(ISERROR(VLOOKUP(D182,#REF!,13,0)),\"-\",VLOOKUP(D182,#REF!,13,0))","v":"-"}]
[179,"광주전남","광주","신광주S/S #1 M.Tr A","신광주S/S #1 M.Tr(#1M.Tr 교체공사)","신광주S/S #1 M.Tr 교체","2018-09-17 09:00","2018-11-09 18:00","취소","취소","연속",null,null,null,201806110049,{"$f":"IF(ISERROR(VLOOKUP(D183,#REF!,13,0)),\"-\",VLOOKUP(D183,#REF!,13,0))","v":"-"}]
[180,"광주전남","광주","신광주S/S #4 M.Tr A","신광주S/S #4 M.Tr (변전협력회사총액공사)","#4 M.Tr 부싱절연열화측정, 7800,7872 CB 전자변 교체","2018-09-06 09:00","2018-09-07 18:00","취소","취소","연속",null,null,null,201806110026,{"$f":"IF(ISERROR(VLOOKUP(D184,#REF!,13,0)),\"-\",VLOOKUP(D184,#REF!,13,0))","v":"-"}]
[181,"광주전남","광주","신광주S/S #3 M.Tr A","신광주S/S #3 M.Tr (변전협력회사총액공사)","#3 M.Tr 부싱절연열화측정","2018-09-10 13:00","2018-09-10 18:00","취소","취소","연속",null,null,null,201806110035,{"$f":"IF(ISERROR(VLOOKUP(D185,#REF!,13,0)),\"-\",VLOOKUP(D185,#REF!,13,0))","v":"-"}]
[182,"광주전남","광주","신광주S/S #2 M.Tr A","신광주S/S #2 M.Tr (변전협력회사총액공사)","#2 M.Tr 부싱절연열화측정","2018-09-10 09:00","2018-09-10 13:00","취소","취소","연속",null,null,null,201806110033,{"$f":"IF(ISERROR(VLOOKUP(D186,#REF!,13,0)),\"-\",VLOOKUP(D186,#REF!,13,0))","v":"-"}]
[183,"광주전남","광주","신화순S/S #1 M.Tr A","신화순S/S #1 M.Tr(변전협력회사총액공사)","7972 CB 보통점검, M.Tr 부싱절연유 채취, S.Tr 초기점검, 1,2차 LA 초기점검,DS조작함 리미트 스위치 교체","2018-09-03 09:00","2018-09-05 18:00","2018-09-03 09:00","2018-09-05 18:00","연속",null,null,null,201806110023,{"$f":"IF(ISERROR(VLOOKUP(D187,#REF!,13,0)),\"-\",VLOOKUP(D187,#REF!,13,0))","v":"-"}]
[184,"광주전남","목포","신김제한빛NP#1 T/L","345kV 신김제-한빛NP 등 4개T/L 지장송전선로 이설공사","345kV 신김제-한빛NP T/L 10 - 13호 전력선 교체 345kV 신남원-한빛NP T/L 12호 철탑이설 및 11-16호 전력선 교체 345kV 신광주-한빛NP T/L 12,13,14호 철탑이설 및 11-16호 전력선 교체 154kV 홍농분기 T/L 51,52호 철탑이설 및 46-52호 전력선 교체","2018-09-28 09:00","2018-10-03 18:00","2018-09-28 09:00","2018-10-03 18:00","연속",null,null,null,201807090139,{"$f":"IF(ISERROR(VLOOKUP(D188,#REF!,13,0)),\"-\",VLOOKUP(D188,#REF!,13,0))","v":"-"}]
[185,"광주전남","순천","신강진광양#1 T/L","광양S/S 362kV GIS 용량대체 공사","362kV 78BAY GIS 용량대체(7871,7700CB)","2018-09-03 09:00","2018-12-19 18:00","취소","취소","연속",null,null,null,201807130131,{"$f":"IF(ISERROR(VLOOKUP(D189,#REF!,13,0)),\"-\",VLOOKUP(D189,#REF!,13,0))","v":"-"}]
[186,"광주전남","순천","광양여수TP T/L","‘18-19년도 순천전력지사 변전협력회사 총액공사","불량애자 교체","2018-09-03 14:00","2018-09-03 18:00","취소","취소","연속",null,null,null,201807190044,{"$f":"IF(ISERROR(VLOOKUP(D190,#REF!,13,0)),\"-\",VLOOKUP(D190,#REF!,13,0))","v":"-"}]
[187,"광주전남","순천","광양S/S #3 M.Tr A","‘18-19년도 순천전력지사 변전협력회사 총액공사","불량애자 교체","2018-09-03 09:00","2018-09-03 14:00","2018-09-03 09:00","2018-09-03 14:00","당일",null,null,null,201807090150,{"$f":"IF(ISERROR(VLOOKUP(D191,#REF!,13,0)),\"-\",VLOOKUP(D191,#REF!,13,0))","v":"-"}]
[188,"광주전남","순천","광양S/S #3 M.Tr A","광양S/S 362kV GIS 용량대체 공사","362kV 77BAY GIS 용량대체(7771,7700,7772)","2018-09-03 09:00","2018-12-19 18:00","2018-09-03 09:00","2018-12-19 18:00","연속",null,null,null,201807050187,{"$f":"IF(ISERROR(VLOOKUP(D192,#REF!,13,0)),\"-\",VLOOKUP(D192,#REF!,13,0))","v":"-"}]
[189,"광주전남","순천","신강진광양#2 T/L","광양S/S 362kV GIS 용량대체 공사","362kV 77BAY GIS 용량대체(7771,7700,7772)","2018-09-03 09:00","2018-12-19 18:00","2018-09-03 09:00","2018-12-19 18:00","연속",null,null,null,201807050190,{"$f":"IF(ISERROR(VLOOKUP(D193,#REF!,13,0)),\"-\",VLOOKUP(D193,#REF!,13,0))","v":"-"}]
[190,"대구","경산","울주신경산#2 T/L","신경산S/S 7361DS 구동축 기어 교체관련 휴전","신경산S/S 7361DS 구동축 기어 교체(A,B,C 및 단로기 내부점검병행)","2018-09-12 09:00","2018-09-14 18:00","2018-09-12 09:00","2018-09-14 18:00","연속",null,null,null,201807050128,{"$f":"IF(ISERROR(VLOOKUP(D194,#REF!,13,0)),\"-\",VLOOKUP(D194,#REF!,13,0))","v":"-"}]
[191,"대구","경산","신경산대구#1 T/L","345kV 신경산-대구T/L 전력선교체공사","전력선교체(No.39~51)","2018-09-01 07:00","2018-09-11 18:00","2018-09-29 07:00","2018-10-10 18:00","연속",null,null,null,201807030107,{"$f":"IF(ISERROR(VLOOKUP(D195,#REF!,13,0)),\"-\",VLOOKUP(D195,#REF!,13,0))","v":"-"}]
[192,"대구","경산","신경산대구#2 T/L","345kV 신경산-대구T/L 전력선교체공사","전력선교체(No.39~51)","2018-09-12 07:00","2018-09-22 18:00","취소","취소","연속",null,null,null,201807030108,{"$f":"IF(ISERROR(VLOOKUP(D196,#REF!,13,0)),\"-\",VLOOKUP(D196,#REF!,13,0))","v":"-"}]
[193,"대구","달성","고령S/S #4 M.Tr A","345kV 고령S/S Sh.R 설치공사","Sh.R(200MVar)*1Bank 설치관련 #2S.Tr 이설(#2S.Tr 위치에 방화벽 시공)","2018-09-29 09:00","2018-09-30 18:00","2018-09-29 09:00","2018-09-30 18:00","연속",null,null,null,201807130127,{"$f":"IF(ISERROR(VLOOKUP(D197,#REF!,13,0)),\"-\",VLOOKUP(D197,#REF!,13,0))","v":"-"}]
[194,"대구","칠곡","북대구S/S #2 M.Tr A","북대구S/S #2M.Tr 누유보수","북대구S/S #2M.Tr 누유보수","2018-09-18 09:30","2018-09-18 18:00","취소","취소","연속",null,null,null,201807040152,{"$f":"IF(ISERROR(VLOOKUP(D198,#REF!,13,0)),\"-\",VLOOKUP(D198,#REF!,13,0))","v":"-"}]
[195,"대구","칠곡","북경남서대구#2 T/L","서대구S/S 북경남서대구#2T/L GCB 및 LA,PT 점검","서대구S/S 북경남서대구#2T/L GCB 장기미동작점검 및 LA,PT 보통점검","2018-09-20 09:30","2018-09-20 18:00","2018-09-20 09:30","2018-09-20 18:00","당일",null,null,null,201807160172,{"$f":"IF(ISERROR(VLOOKUP(D199,#REF!,13,0)),\"-\",VLOOKUP(D199,#REF!,13,0))","v":"-"}]
[196,"대구","포항","신포항신월성NP#1 T/L","2018년 신포항S/S 75Bay B/F 보호반 대체작업","2018년 신포항S/S 75Bay B/F 보호반 대체작업","2018-09-03 09:00","2018-09-06 18:00","취소","취소","연속",null,null,null,201807050099,{"$f":"IF(ISERROR(VLOOKUP(D200,#REF!,13,0)),\"-\",VLOOKUP(D200,#REF!,13,0))","v":"-"}]
[197,"대구","포항","신포항북대구 T/L","보호배전반 회로개선","보호배전반 회로개선","2018-09-17 09:00","2018-09-17 18:00","2018-09-17 09:00","2018-09-17 18:00","당일",null,null,null,201807100053,{"$f":"IF(ISERROR(VLOOKUP(D201,#REF!,13,0)),\"-\",VLOOKUP(D201,#REF!,13,0))","v":"-"}]
[198,"대구","포항","신포항S/S #2 M.Tr A","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- GIS 기초보강(파일시공) 관련 상부 전력선분리 등","2018-09-13 08:00","2018-09-20 18:00","취소","취소","연속",null,null,null,201807110105,{"$f":"IF(ISERROR(VLOOKUP(D202,#REF!,13,0)),\"-\",VLOOKUP(D202,#REF!,13,0))","v":"-"}]
[199,"대구","포항","울주월성NP#1 T/L","2018년 가공송전선로 순시점검 위탁공사","154kV영일-입실T/L 정밀점검 안전확보차","2018-09-19 08:00","2018-09-19 18:00","취소","취소","연속",null,null,null,201807040186,{"$f":"IF(ISERROR(VLOOKUP(D203,#REF!,13,0)),\"-\",VLOOKUP(D203,#REF!,13,0))","v":"-"}]
[200,"대구","경산","신경산S/S #2 M.Tr A","신경산S/S 345kV #2M.Tr 휴전","#2M.Tr C상 1차 부싱 절연유 GAS 분석 불량 보수","2018-09-01 00:00","2018-12-31 18:00","2018-09-01 00:00","2018-12-31 18:00","연속",null,null,null,201807270072,{"$f":"IF(ISERROR(VLOOKUP(D204,#REF!,13,0)),\"-\",VLOOKUP(D204,#REF!,13,0))","v":"-"}]
[201,"경북","영주","신한울한울#1 T/L","18-19년도 가공송전정비회사 총액공사","345kV 신한울-한울연락#1,2T/L No.1-4 스페이서댐퍼 교체공사","2018-09-10 08:00","2018-09-11 18:00","취소","취소","연속",null,null,null,201807060017,{"$f":"IF(ISERROR(VLOOKUP(D205,#REF!,13,0)),\"-\",VLOOKUP(D205,#REF!,13,0))","v":"-"}]
[202,"경북","영주","신한울한울#2 T/L","18-19년도 가공송전정비회사 총액공사","345kV 신한울-한울연락#1,2T/L No.1-4 스페이서댐퍼 교체공사","2018-09-12 08:00","2018-09-13 18:00","취소","취소","연속",null,null,null,201807060018,{"$f":"IF(ISERROR(VLOOKUP(D206,#REF!,13,0)),\"-\",VLOOKUP(D206,#REF!,13,0))","v":"-"}]
[203,"경북","영주","한울1NP한울2NP#2 T/L","18-19년도 가공송전정비회사 총액공사","345kV 한울연락#1,2T/L No.1-4 스페이서댐퍼 교체공사","2018-09-14 08:00","2018-09-18 20:00","2018-09-17 08:00","2018-09-22 20:00","연속",null,null,null,201807060014,{"$f":"IF(ISERROR(VLOOKUP(D207,#REF!,13,0)),\"-\",VLOOKUP(D207,#REF!,13,0))","v":"-"}]
[204,"경북","영주","한울1NP한울2NP#1 T/L","2018년 영주전력지사 362kV GIS 정밀점검 공사","한울1발S/Y 362kV 7271, 7200 GIS 절연로드 교체","2018-09-04 08:00","2018-09-09 20:00","취소","취소","연속",null,null,null,201807050260,{"$f":"IF(ISERROR(VLOOKUP(D208,#REF!,13,0)),\"-\",VLOOKUP(D208,#REF!,13,0))","v":"-"}]
[205,"부산울산","동부산","고리N/P S/Y 7677 BUS SEC CB (7677)","고리NP S/Y 362kV #2CLR GIS 보통점검","고리NP S/Y 362kV #2CLR GIS 보통점검(7677)","2018-09-18 09:30","2018-09-19 17:00","2018-09-18 09:30","2018-09-19 17:00","연속",null,null,null,201807160035,{"$f":"IF(ISERROR(VLOOKUP(D209,#REF!,13,0)),\"-\",VLOOKUP(D209,#REF!,13,0))","v":"-"}]
[206,"부산울산","동부산","고리N/P S/Y 고리 G1 CB (7272)","고리NP S/Y 362kV GIS 조작시험","고리NP S/Y 362kV GIS 조작시험(7272)","2018-09-20 09:30","2018-09-20 14:00","2018-09-20 09:30","2018-09-20 14:00","당일",null,null,null,201807090342,{"$f":"IF(ISERROR(VLOOKUP(D210,#REF!,13,0)),\"-\",VLOOKUP(D210,#REF!,13,0))","v":"-"}]
[207,"부산울산","동부산","고리N/P S/Y 7577 BUS SEC CB (7577)","고리NP S/Y 362kV #2CLR GIS 보통점검","고리NP S/Y 362kV #2CLR GIS 보통점검(7577)","2018-09-18 09:30","2018-09-19 17:00","2018-09-18 09:30","2018-09-19 17:00","연속",null,null,null,201807160034,{"$f":"IF(ISERROR(VLOOKUP(D211,#REF!,13,0)),\"-\",VLOOKUP(D211,#REF!,13,0))","v":"-"}]
[208,"부산울산","북부산","북부산신온산 T/L","345kV 북부산-울산화력 등 4개T/L 전선접속개소 전선교체공사","345kV 북부산-신온산T/L No.35~145호 전선교체","2018-09-27 07:00","2018-10-14 18:00","2018-09-27 07:00","2018-10-14 18:00","연속",null,null,null,201807110188,{"$f":"IF(ISERROR(VLOOKUP(D212,#REF!,13,0)),\"-\",VLOOKUP(D212,#REF!,13,0))","v":"-"}]
[209,"부산울산","북부산","북부산S/S 345kV #70 BUS","345kV 북부산S/S 차단기용량대체공사","71bay 설치분 시험가압 및 PT ANGLE 측정","2018-09-18 16:00","2018-09-19 16:00","2018-09-18 16:00","2018-09-19 16:00","연속",null,null,null,201806050046,{"$f":"IF(ISERROR(VLOOKUP(D213,#REF!,13,0)),\"-\",VLOOKUP(D213,#REF!,13,0))","v":"-"}]
[210,"부산울산","북부산","신양산북부산#1 T/L","345kV 북부산S/S 차단기용량대체공사","신양산북부산#1 T/L 인출변경","2018-09-09 08:00","2018-09-21 18:00","2018-09-09 08:00","2018-09-21 18:00","연속",null,null,null,201805240063,{"$f":"IF(ISERROR(VLOOKUP(D214,#REF!,13,0)),\"-\",VLOOKUP(D214,#REF!,13,0))","v":"-"}]
[211,"부산울산","북부산","북부산신울산#1 T/L","345kV 북부산S/S 차단기용량대체공사","북부산신울산#1 T/L 인출변경","2018-09-09 08:00","2018-09-21 18:00","2018-09-09 08:00","2018-09-21 18:00","연속",null,null,null,201805240062,{"$f":"IF(ISERROR(VLOOKUP(D215,#REF!,13,0)),\"-\",VLOOKUP(D215,#REF!,13,0))","v":"-"}]
[212,"부산울산","북부산","북부산S/S 345kV #75 BUS","345kV 북부산S/S 차단기용량대체공사","북부산S/S 신울산#1, 신양산#1T/L C/H 조립 관련 안전이격거리 확보","2018-09-08 09:00","2018-09-09 08:00","2018-09-08 09:00","2018-09-09 08:00","연속",null,null,null,201807030190,{"$f":"IF(ISERROR(VLOOKUP(D216,#REF!,13,0)),\"-\",VLOOKUP(D216,#REF!,13,0))","v":"-"}]
[213,"부산울산","북부산","북부산S/S 345kV #75 BUS","345kV 북부산S/S 차단기용량대체공사","1. 기설GIS (GIS-옥외모선 연결구간) 철거, 2. 신설GIS-B/S 연결작업","2018-09-27 08:00","2018-10-12 18:00","2018-09-27 08:00","2018-10-12 18:00","연속",null,null,null,201806050052,{"$f":"IF(ISERROR(VLOOKUP(D217,#REF!,13,0)),\"-\",VLOOKUP(D217,#REF!,13,0))","v":"-"}]
[214,"부산울산","울산","신울산고리NP#2 T/L","345kV 신울산-고리NPT/L 송전용량증대전선교체공사","송전용량증대전선교체, 구간: 고리~2호, 0.646C-km, 12가닥","2018-09-15 08:00","2018-09-21 18:00","2018-09-15 08:00","2018-09-21 18:00","연속",null,null,null,201807040138,{"$f":"IF(ISERROR(VLOOKUP(D218,#REF!,13,0)),\"-\",VLOOKUP(D218,#REF!,13,0))","v":"-"}]
[215,"부산울산","울산","신울산S/S #1 M.Tr A","2018-19년 울산전력지사 변전협력회사 총액공사","신울산S/S 345kV #1M.Tr 하자점검","2018-09-27 09:00","2018-09-28 18:00","2018-09-27 09:00","2018-09-28 18:00","연속",null,null,null,201807090430,{"$f":"IF(ISERROR(VLOOKUP(D219,#REF!,13,0)),\"-\",VLOOKUP(D219,#REF!,13,0))","v":"-"}]
[216,"부산울산","울산","신울산고리NP#1 T/L","345kV 신울산-고리NPT/L 송전용량증대전선교체공사","송전용량증대전선교체, 구간: 고리~2호, 0.646C-km, 12가닥","2018-09-15 08:00","2018-09-21 18:00","2018-09-15 08:00","2018-09-21 18:00","연속",null,null,null,201807040137,{"$f":"IF(ISERROR(VLOOKUP(D220,#REF!,13,0)),\"-\",VLOOKUP(D220,#REF!,13,0))","v":"-"}]
[217,"부산울산","울산","북부산울산TP T/L","2018-19년 울산전력지사 변전협력회사 총액공사","울산복합 345kV 75Bay B/F PNL 대체(발전기 정지관련 병행작업)","2018-09-07 09:00","2018-09-15 18:00","취소","취소","연속",null,null,null,201807090267,{"$f":"IF(ISERROR(VLOOKUP(D221,#REF!,13,0)),\"-\",VLOOKUP(D221,#REF!,13,0))","v":"-"}]
[218,"부산울산","직할","신대연S/S #2M.Tr A","신대연S/S #2M.Tr 제작사 하자보수점검","신대연S/S #2M.Tr 제작사 하자보수점검","2018-09-20 10:00","2018-09-21 18:00","2018-09-20 10:00","2018-09-21 18:00","연속",null,null,null,201807110018,{"$f":"IF(ISERROR(VLOOKUP(D222,#REF!,13,0)),\"-\",VLOOKUP(D222,#REF!,13,0))","v":"-"}]
[219,"부산울산","직할","신대연S/S #1M.Tr A","신대연S/S #1M.Tr 제작사 하자보수점검","신대연S/S #1M.Tr 제작사 하자보수점검","2018-09-18 10:00","2018-09-19 18:00","2018-09-18 10:00","2018-09-19 18:00","연속",null,null,null,201807110017,{"$f":"IF(ISERROR(VLOOKUP(D223,#REF!,13,0)),\"-\",VLOOKUP(D223,#REF!,13,0))","v":"-"}]
[220,"경남","진주","신남원의령#1 T/L","345kV 신남원-의령#1T/L 106호 불량애자 교체","345kV 신남원-의령#1T/L 106호 불량애자 교체","2018-09-14 09:00","2018-09-14 18:00","2018-09-14 09:00","2018-09-14 18:00","당일",null,null,null,201806260157,{"$f":"IF(ISERROR(VLOOKUP(D224,#REF!,13,0)),\"-\",VLOOKUP(D224,#REF!,13,0))","v":"-"}]
[221,"경남","진주","의령S/S #2 M.Tr 1차 CB (7572)","의령S/S 345kV #2M.Tr 1차 CB(7572) 보통점검","의령S/S 345kV #2M.Tr 1차 CB(7572) 보통점검","2018-09-20 09:30","2018-09-20 18:30","2018-09-20 09:30","2018-09-20 18:30","당일",null,null,null,201807020207,{"$f":"IF(ISERROR(VLOOKUP(D225,#REF!,13,0)),\"-\",VLOOKUP(D225,#REF!,13,0))","v":"-"}]
[222,"경남","진주","의령S/S 의령-산청양수#2T/L CB (7371)","의령S/S 345kV 의령-산청양수#2T/L CB(7371) 보통점검","의령S/S 345kV 의령-산청양수#2T/L CB(7371) 보통점검","2018-09-14 09:30","2018-09-14 18:30","2018-09-14 09:30","2018-09-14 18:30","당일",null,null,null,201807020206,{"$f":"IF(ISERROR(VLOOKUP(D226,#REF!,13,0)),\"-\",VLOOKUP(D226,#REF!,13,0))","v":"-"}]
[223,"경남","진주","하동T/P 의령-하동TP#1T/L CB (7171)","하동T/P 345kV 의령-하동T/P#1T/L CB 조작시험","하동T/P 345kV 의령-하동T/P #1T/L CB(7171) 개폐장치 조작시험","2018-09-13 14:00","2018-09-13 18:30","2018-09-13 14:00","2018-09-13 18:30","당일",null,null,null,201806270105,{"$f":"IF(ISERROR(VLOOKUP(D227,#REF!,13,0)),\"-\",VLOOKUP(D227,#REF!,13,0))","v":"-"}]
[224,"경남","진주","하동T/P 의령-하동TP#1T/L-#1M.Tr 1차 CB (7100)","하동T/P 345kV 의령-하동T/P#1T/L-#1M.Tr1차CB조작시험","하동T/P 345kV 의령-하동T/P #1T/L-#1M.Tr 1차 CB(7100) 개폐장치 조작시험","2018-09-13 09:30","2018-09-13 14:00","2018-09-13 09:30","2018-09-13 14:00","당일",null,null,null,201806270104,{"$f":"IF(ISERROR(VLOOKUP(D228,#REF!,13,0)),\"-\",VLOOKUP(D228,#REF!,13,0))","v":"-"}]
[225,"경남","함안","북경남S/S 북경남-서대구 #2T/L CB (7972)","북경남S/S 345kV 북경남-서대구#2T/L 7972 GIS 보통점검","북경남S/S 345kV 북경남-서대구#2T/L 7972 GIS 보통점검","2018-09-27 09:30","2018-09-27 17:30","2018-09-27 09:30","2018-09-27 17:30","당일",null,null,null,201807060148,{"$f":"IF(ISERROR(VLOOKUP(D229,#REF!,13,0)),\"-\",VLOOKUP(D229,#REF!,13,0))","v":"-"}]
[226,"경남","함안","신마산S/S #4 M.Tr A","345kV 신마산S/S 용량부족 차단기 대체공사(#4M.Tr)","#4M.Tr 1차측 전력구 시공관련 안전이격거리 확보차","2018-09-10 09:30","2018-09-11 18:00","2018-09-10 09:30","2018-09-11 18:00","연속",null,null,null,201807090454,{"$f":"IF(ISERROR(VLOOKUP(D230,#REF!,13,0)),\"-\",VLOOKUP(D230,#REF!,13,0))","v":"-"}]
[227,"경남","함안","신마산S/S #4 M.Tr A","345kV 신마산S/S 용량부족 차단기 대체공사(#4M.Tr)","#4M.Tr 1차측 전력구 시공관련 안전이격거리 확보차","2018-09-03 09:30","2018-09-04 18:00","2018-09-03 09:30","2018-09-04 18:00","연속",null,null,null,201807090452,{"$f":"IF(ISERROR(VLOOKUP(D231,#REF!,13,0)),\"-\",VLOOKUP(D231,#REF!,13,0))","v":"-"}]
[228,"경남","함안","신마산S/S #1 M.Tr A","345kV 신마산S/S 용량부족 차단기 대체공사(#1M.Tr)","#1M.Tr 1차측 전력구 시공관련 안전이격거리 확보차","2018-09-05 09:30","2018-09-07 18:00","2018-09-05 09:30","2018-09-07 18:00","연속",null,null,null,201807090453,{"$f":"IF(ISERROR(VLOOKUP(D232,#REF!,13,0)),\"-\",VLOOKUP(D232,#REF!,13,0))","v":"-"}]
[229,"경남","함안","신마산신김해#1 T/L","345kV 신마산S/S 용량부족차단기 대체공사","용량부족차단기 대체공사 관련 기존 #1BUS 시험가압","2018-09-28 09:00","2018-09-30 18:00","2018-09-28 09:00","2018-09-30 18:00","연속",null,null,null,201807310015,{"$f":"IF(ISERROR(VLOOKUP(D233,#REF!,13,0)),\"-\",VLOOKUP(D233,#REF!,13,0))","v":"-"}]
[230,"경남","함안","신마산S/S 345kV #1 BUS","345kV 신마산S/S 용량부족차단기 대체공사","용량부족차단기 대체공사 관련 기존 #1BUS, 신설#1BUS 도킹작업","2018-09-28 09:00","2018-09-30 18:00","2018-09-28 09:00","2018-09-30 18:00","연속",null,null,null,201807310019,{"$f":"IF(ISERROR(VLOOKUP(D234,#REF!,13,0)),\"-\",VLOOKUP(D234,#REF!,13,0))","v":"-"}]

{"sheet":"154송부","index":2,"n_rows":421,"n_cols":16,"rows_kept":421,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,14,3,14],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2018년도 \"&#REF!&\"월 휴전계획서\"","v":{"$error":"#REF!"}}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동군자#2 T/L","18년 군자S/S 장기사용 170kV GIS 교체공사(성동군자#2T/L)","2018년 군자S/S 장기사용 170kV GIS 교체공사(성동군자#2T/L)","2018-09-28 09:00","2018-10-15 18:00","2018-09-28 09:00","2018-10-15 18:00","연속"," ",null,null,201807160150,{"$f":"IF(ISERROR(VLOOKUP(D5,#REF!,13,0)),\"-\",VLOOKUP(D5,#REF!,13,0))","v":"-"}]
[2,"서울","성동","미금화양 T/L","18년 성동P/O 170KV GIS 조작시험","차단기 개폐타임 측정","2018-09-18 11:00","2018-09-18 12:00","2018-09-18 11:00","2018-09-18 12:00","당일",null,null,null,201807160192,{"$f":"IF(ISERROR(VLOOKUP(D6,#REF!,13,0)),\"-\",VLOOKUP(D6,#REF!,13,0))","v":"-"}]
[3,"서울","중부","중부당인리#1 T/L","2018년 중부P/O 170kV GIS 정밀점검공사","#1 BUS-TIE GIS(6100) 정밀점검 (시험가압)","2018-09-15 17:00","2018-09-15 18:00","2018-09-15 17:00","2018-09-15 18:00","당일",null,null,null,201807170136,{"$f":"IF(ISERROR(VLOOKUP(D7,#REF!,13,0)),\"-\",VLOOKUP(D7,#REF!,13,0))","v":"-"}]
[4,"서울","중부","중부당인리#1 T/L","2018년 중부P/O 170kV GIS 정밀점검공사","#3 M.Tr GIS(6333) 정밀점검 (시험가압)","2018-09-13 17:00","2018-09-13 18:00","2018-09-13 17:00","2018-09-13 18:00","당일",null,null,null,201807170132,{"$f":"IF(ISERROR(VLOOKUP(D8,#REF!,13,0)),\"-\",VLOOKUP(D8,#REF!,13,0))","v":"-"}]
[5,"서울","중부","중부당인리#2 T/L","2018년 중부P/O 170kV GIS 정밀점검공사","65-66BUS-SECTION 정밀점검 (시험가압)","2018-09-21 17:00","2018-09-21 18:00","2018-09-21 17:00","2018-09-21 18:00","당일",null,null,null,201807170147,{"$f":"IF(ISERROR(VLOOKUP(D9,#REF!,13,0)),\"-\",VLOOKUP(D9,#REF!,13,0))","v":"-"}]
[6,"서울","중부","당인리S/S 154kV #65 BUS","2018년 중부P/O 170kV GIS 정밀점검공사","65-66BUS-SECTION GIS 정밀점검 (시험가압)","2018-09-21 17:00","2018-09-21 18:00","2018-09-21 17:00","2018-09-21 18:00","당일",null,null,null,201807170144,{"$f":"IF(ISERROR(VLOOKUP(D10,#REF!,13,0)),\"-\",VLOOKUP(D10,#REF!,13,0))","v":"-"}]
[7,"서울","중부","중부당인리#1 T/L","2018년 중부P/O 170kV GIS 정밀점검공사","60-61BUS-SECTION GIS 정밀점검 (시험가압)","2018-09-17 17:00","2018-09-17 18:00","2018-09-17 17:00","2018-09-17 18:00","당일",null,null,null,201807170137,{"$f":"IF(ISERROR(VLOOKUP(D11,#REF!,13,0)),\"-\",VLOOKUP(D11,#REF!,13,0))","v":"-"}]
[8,"서울","중부","당인리S/S 60-61-0 SEC CB","2018년 중부P/O 170kV GIS 정밀점검공사","60-61 BUS-SECTION GIS 정밀점검","2018-09-16 08:00","2018-09-17 18:00","2018-09-16 08:00","2018-09-17 18:00","연속",null,null,null,201807170141,{"$f":"IF(ISERROR(VLOOKUP(D12,#REF!,13,0)),\"-\",VLOOKUP(D12,#REF!,13,0))","v":"-"}]
[9,"서울","중부","당인리S/S 154kV #60 BUS","2018년 중부P/O 170kV GIS 정밀점검공사","#3 M.Tr GIS(6333) 정밀점검 (시험가압)","2018-09-13 17:00","2018-09-13 18:00","2018-09-13 17:00","2018-09-13 18:00","당일",null,null,null,201807170133,{"$f":"IF(ISERROR(VLOOKUP(D13,#REF!,13,0)),\"-\",VLOOKUP(D13,#REF!,13,0))","v":"-"}]
[10,"서울","중부","당인리S/S 154kV #2 BUS TIE CB","2018년 중부P/O 170kV GIS 정밀점검공사","#2 BUS-TIE GIS(6200) GIS 정밀점검","2018-09-18 08:00","2018-09-19 18:00","2018-09-18 08:00","2018-09-19 18:00","연속",null,null,null,201807170142,{"$f":"IF(ISERROR(VLOOKUP(D14,#REF!,13,0)),\"-\",VLOOKUP(D14,#REF!,13,0))","v":"-"}]
[11,"서울","중부","당인리S/S 154kV #60 BUS","2018년 중부P/O 170kV GIS 정밀점검공사","#1 BUS-TIE GIS(6100) 정밀점검 (시험가압)","2018-09-15 17:00","2018-09-15 18:00","2018-09-15 17:00","2018-09-15 18:00","당일",null,null,null,201807170134,{"$f":"IF(ISERROR(VLOOKUP(D15,#REF!,13,0)),\"-\",VLOOKUP(D15,#REF!,13,0))","v":"-"}]
[12,"서울","중부","당인리S/S 154kV #1 BUS TIE CB","2018년 중부P/O 170kV GIS 정밀점검공사","#1 BUS-TIE GIS(6100) 정밀점검","2018-09-14 08:00","2018-09-15 18:00","2018-09-14 08:00","2018-09-15 18:00","연속",null,null,null,201807170139,{"$f":"IF(ISERROR(VLOOKUP(D16,#REF!,13,0)),\"-\",VLOOKUP(D16,#REF!,13,0))","v":"-"}]
[13,"서울","중부","당인리S/S 65-66-0 SEC CB","2018년 중부P/O 170kV GIS 정밀점검공사","65-66BUS-SECTION GIS 정밀점검","2018-09-20 08:00","2018-09-21 18:00","2018-09-20 08:00","2018-09-21 18:00","연속",null,null,null,201807170145,{"$f":"IF(ISERROR(VLOOKUP(D17,#REF!,13,0)),\"-\",VLOOKUP(D17,#REF!,13,0))","v":"-"}]
[14,"서울","중부","당인리S/S 154kV #60 BUS","2018년 중부P/O 170kV GIS 정밀점검공사","60-61BUS-SECTION GIS 정밀점검 (시험가압)","2018-09-17 17:00","2018-09-17 18:00","2018-09-17 17:00","2018-09-17 18:00","당일",null,null,null,201807170135,{"$f":"IF(ISERROR(VLOOKUP(D18,#REF!,13,0)),\"-\",VLOOKUP(D18,#REF!,13,0))","v":"-"}]
[15,"서울","중부","당인리S/S 154kV #66 BUS","2018년 중부P/O 170kV GIS 정밀점검공사","#2 BUS-TIE GIS(6200) 정밀점검 (시험가압)","2018-09-19 17:00","2018-09-19 18:00","2018-09-19 17:00","2018-09-19 18:00","당일",null,null,null,201807170143,{"$f":"IF(ISERROR(VLOOKUP(D19,#REF!,13,0)),\"-\",VLOOKUP(D19,#REF!,13,0))","v":"-"}]
[16,"서울","중부","용산동빙고 T/L","154kV 동빙고S/S 인출T/L 선종교체공사","동빙고S/S ~ 첫번째 관로 맨홀 OF-&gtXLPE 선종교체공사","2018-09-10 09:00","2018-10-16 18:00","2018-09-10 09:00","2018-10-16 18:00","연속",null,null,null,201807120109,{"$f":"IF(ISERROR(VLOOKUP(D20,#REF!,13,0)),\"-\",VLOOKUP(D20,#REF!,13,0))","v":"-"}]
[17,"서울","중부","세종로옥인#1 T/L","154kV 옥인 및 운니S/S 인출T/L 교체공사","1. 사업목적 : 옥인 및 운니변전소 화재 및 대형 재난사고 예방 2. 사업구간 : 옥인S/S ∼ 옥인인출전력구, 운니S/S 운니인출전력구 3. 사업내용 - 철거 : 154kV OF 2000㎟ 4C, OF 1200㎟ 4C 총길이1.4㎞ - 신설 : 154kV XLPE 2000㎟ 4C, XLPE 1200㎟ 4C 총길이1.4㎞","2018-09-03 09:00","2018-10-15 18:00","2018-09-03 09:00","2018-10-15 18:00","연속",null,null,null,201807170127,{"$f":"IF(ISERROR(VLOOKUP(D21,#REF!,13,0)),\"-\",VLOOKUP(D21,#REF!,13,0))","v":"-"}]
[18,"남서울","강남","대치논현#1 T/L","대치S/S 장기사용GIS 대체공사","장기사용GIS 대체공사 #1BUS 설치","2018-09-09 10:00","2018-09-10 18:00","2018-09-09 10:00","2018-09-10 18:00","연속",null,null,null,201807200117,{"$f":"IF(ISERROR(VLOOKUP(D22,#REF!,13,0)),\"-\",VLOOKUP(D22,#REF!,13,0))","v":"-"}]
[19,"남서울","강남","대치논현#1 T/L","대치S/S 장기사용GIS 대체공사","대치S/S #2BUS 무부하가압","2018-09-15 16:00","2018-09-15 18:00","2018-09-15 16:00","2018-09-15 18:00","당일",null,null,null,201807180117,{"$f":"IF(ISERROR(VLOOKUP(D23,#REF!,13,0)),\"-\",VLOOKUP(D23,#REF!,13,0))","v":"-"}]
[20,"남서울","강남","대치S/S 154kV #2 BUS","대치S/S 장기사용GIS 대체공사","논현-대치#2T/L, #3M.Tr 1차 GIS 대체 무부하가압","2018-09-30 18:00","2018-10-01 18:00","2018-09-30 18:00","2018-10-01 18:00","연속",null,null,null,201807200068,{"$f":"IF(ISERROR(VLOOKUP(D24,#REF!,13,0)),\"-\",VLOOKUP(D24,#REF!,13,0))","v":"-"}]
[21,"남서울","강남","대치S/S 154kV #1 BUS","대치S/S 장기사용GIS 대체공사","170kV GIS 대체 : 논현-대치#2T/L, #3M.Tr 1차 GIS 23kV GIS 대체 : #3Bank(14CCT)","2018-09-06 10:00","2018-09-12 18:00","2018-09-06 10:00","2018-09-12 18:00","연속",null,null,null,201807180026,{"$f":"IF(ISERROR(VLOOKUP(D25,#REF!,13,0)),\"-\",VLOOKUP(D25,#REF!,13,0))","v":"-"}]
[22,"남서울","강남","대치논현#1 T/L","대치S/S 장기사용GIS 대체공사","대치S/S #2BUS 무부하가압","2018-09-05 16:00","2018-09-05 18:00","2018-09-05 16:00","2018-09-05 18:00","당일",null,null,null,201807180115,{"$f":"IF(ISERROR(VLOOKUP(D26,#REF!,13,0)),\"-\",VLOOKUP(D26,#REF!,13,0))","v":"-"}]
[23,"남서울","강남","대치논현#1 T/L","대치S/S 장기사용GIS 대체공사","대치S/S #1BUS 무부하가압","2018-09-12 16:00","2018-09-12 18:00","2018-09-12 16:00","2018-09-12 18:00","당일",null,null,null,201807180116,{"$f":"IF(ISERROR(VLOOKUP(D27,#REF!,13,0)),\"-\",VLOOKUP(D27,#REF!,13,0))","v":"-"}]
[24,"남서울","강남","대치S/S 154kV #2 BUS","대치S/S 장기사용GIS 대체공사","170kV GIS 대체 : 논현-대치#2T/L, #3M.Tr 1차 GIS 23kV GIS 대체 : #3Bank(14CCT)","2018-09-03 10:00","2018-09-05 18:00","2018-09-03 10:00","2018-09-05 18:00","연속",null,null,null,201807180023,{"$f":"IF(ISERROR(VLOOKUP(D28,#REF!,13,0)),\"-\",VLOOKUP(D28,#REF!,13,0))","v":"-"}]
[25,"남서울","강남","대치논현#1 T/L","대치S/S 장기사용GIS 대체공사","논현-대치#2T/L, #3M.Tr 1차 GIS 대체 무부하가압","2018-09-30 18:00","2018-10-01 18:00","2018-09-30 18:00","2018-10-01 18:00","연속",null,null,null,201807200070,{"$f":"IF(ISERROR(VLOOKUP(D29,#REF!,13,0)),\"-\",VLOOKUP(D29,#REF!,13,0))","v":"-"}]
[26,"남서울","강남","대치S/S 154kV #2 BUS","대치S/S 장기사용GIS 대체공사","170kV GIS 대체 : 논현-대치#2T/L, #3M.Tr 1차 GIS 23kV GIS 대체 : #3Bank(14CCT)","2018-09-13 10:00","2018-09-15 18:00","2018-09-13 10:00","2018-09-15 18:00","연속",null,null,null,201807180027,{"$f":"IF(ISERROR(VLOOKUP(D30,#REF!,13,0)),\"-\",VLOOKUP(D30,#REF!,13,0))","v":"-"}]
[27,"남서울","강남","대치논현#1 T/L","대치S/S 장기사용GIS 대체공사","장기사용GIS 대체공사 #2BUS 설치","2018-09-13 10:00","2018-09-14 18:00","2018-09-13 10:00","2018-09-14 18:00","연속",null,null,null,201807200118,{"$f":"IF(ISERROR(VLOOKUP(D31,#REF!,13,0)),\"-\",VLOOKUP(D31,#REF!,13,0))","v":"-"}]
[28,"남서울","강남","대치논현#2 T/L","대치S/S 장기사용GIS 대체공사","170kV GIS 대체 : 논현-대치#2T/L, #3M.Tr 1차 GIS 23kV GIS 대체 : #3Bank(14CCT)","2018-09-03 10:00","2018-10-02 18:00","2018-09-03 10:00","2018-10-02 18:00","연속",null,null,null,201807180021,{"$f":"IF(ISERROR(VLOOKUP(D32,#REF!,13,0)),\"-\",VLOOKUP(D32,#REF!,13,0))","v":"-"}]
[29,"남서울","강남","사당신림 T/L","사당S/S 170kV GIS 개폐타임측정 및 조작시험","사당-신림T/L GIS 개폐타임측정 및 조작시험","2018-09-18 10:00","2018-09-18 14:00","취소","취소","당일",null,null,null,201807180035,{"$f":"IF(ISERROR(VLOOKUP(D33,#REF!,13,0)),\"-\",VLOOKUP(D33,#REF!,13,0))","v":"-"}]
[30,"남서울","강남","사당봉천#1 T/L","사당S/S 170kV GIS 개폐타임측정 및 조작시험","사당-봉천#1T/L GIS 개폐타임측정 및 조작시험","2018-09-19 10:00","2018-09-19 14:00","취소","취소","당일",null,null,null,201807180051,{"$f":"IF(ISERROR(VLOOKUP(D34,#REF!,13,0)),\"-\",VLOOKUP(D34,#REF!,13,0))","v":"-"}]
[31,"남서울","강남","사당봉천#2 T/L","사당S/S 170kV GIS 개폐타임측정 및 조작시험","사당-봉천#2T/L GIS 개폐타임측정 및 조작시험","2018-09-19 14:00","2018-09-19 18:00","취소","취소","당일",null,null,null,201807180053,{"$f":"IF(ISERROR(VLOOKUP(D35,#REF!,13,0)),\"-\",VLOOKUP(D35,#REF!,13,0))","v":"-"}]
[32,"남서울","동서울","가락수서#2 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2018-09-10 15:00","2018-09-10 18:00","2018-09-10 15:00","2018-09-10 18:00","당일",null,null,null,201807200093,{"$f":"IF(ISERROR(VLOOKUP(D36,#REF!,13,0)),\"-\",VLOOKUP(D36,#REF!,13,0))","v":"-"}]
[33,"남서울","동서울","가락수서#1 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2018-09-10 09:00","2018-09-10 15:00","2018-09-10 09:00","2018-09-10 15:00","당일",null,null,null,201807200092,{"$f":"IF(ISERROR(VLOOKUP(D37,#REF!,13,0)),\"-\",VLOOKUP(D37,#REF!,13,0))","v":"-"}]
[34,"남서울","동서울","풍납석촌#2 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2018-09-19 14:00","2018-09-21 18:00","2018-09-19 14:00","2018-09-21 18:00","연속",null,null,null,201807200091,{"$f":"IF(ISERROR(VLOOKUP(D38,#REF!,13,0)),\"-\",VLOOKUP(D38,#REF!,13,0))","v":"-"}]
[35,"남서울","동서울","풍납석촌#1 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2018-09-17 09:00","2018-09-19 14:00","2018-09-17 09:00","2018-09-19 14:00","연속",null,null,null,201807200090,{"$f":"IF(ISERROR(VLOOKUP(D39,#REF!,13,0)),\"-\",VLOOKUP(D39,#REF!,13,0))","v":"-"}]
[36,"남서울","영등포","신광명광명#2 T/L","2018~2019 영등포전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2018-09-04 09:00","2018-09-04 18:00","취소","취소","당일",null,null,null,201807200034,{"$f":"IF(ISERROR(VLOOKUP(D40,#REF!,13,0)),\"-\",VLOOKUP(D40,#REF!,13,0))","v":"-"}]
[37,"남서울","영등포","광명구공#2 T/L","2018~2019 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험 - 개폐타임측정","2018-09-06 14:00","2018-09-06 18:00","취소","취소","당일",null,null,null,201807200039,{"$f":"IF(ISERROR(VLOOKUP(D41,#REF!,13,0)),\"-\",VLOOKUP(D41,#REF!,13,0))","v":"-"}]
[38,"남서울","영등포","광명구공#1 T/L","2018~2019 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험 - 개폐타임측정","2018-09-06 09:00","2018-09-06 14:00","취소","취소","당일",null,null,null,201807200038,{"$f":"IF(ISERROR(VLOOKUP(D42,#REF!,13,0)),\"-\",VLOOKUP(D42,#REF!,13,0))","v":"-"}]
[39,"남서울","영등포","대방신길#2 T/L","2018~2019 영등포전력지사 변전협력회사 총액공사","170kV GIS 차단기 조작시험 - 개폐타임 측정","2018-09-03 14:00","2018-09-03 18:00","2018-09-03 14:00","2018-09-03 18:00","당일",null,null,null,201807200016,{"$f":"IF(ISERROR(VLOOKUP(D43,#REF!,13,0)),\"-\",VLOOKUP(D43,#REF!,13,0))","v":"-"}]
[40,"남서울","영등포","독산대방#1 T/L","2018~2019 영등포전력지사 변전협력회사 총액공사","170kV GIS 차단기 조작시험 - 개폐타임 측정","2018-09-05 09:00","2018-09-05 14:00","2018-09-05 09:00","2018-09-05 14:00","당일",null,null,null,201807200017,{"$f":"IF(ISERROR(VLOOKUP(D44,#REF!,13,0)),\"-\",VLOOKUP(D44,#REF!,13,0))","v":"-"}]
[41,"남서울","영등포","독산대방#2 T/L","2018~2019 영등포전력지사 변전협력회사 총액공사","170kV GIS 차단기 조작시험 - 개폐타임 측정","2018-09-05 14:00","2018-09-05 18:00","2018-09-05 14:00","2018-09-05 18:00","당일",null,null,null,201807200018,{"$f":"IF(ISERROR(VLOOKUP(D45,#REF!,13,0)),\"-\",VLOOKUP(D45,#REF!,13,0))","v":"-"}]
[42,"남서울","영등포","대방신길#1 T/L","2018~2019 영등포전력지사 변전협력회사 총액공사","170kV GIS 차단기 조작시험 - 개폐타임 측정","2018-09-03 09:00","2018-09-03 14:00","2018-09-03 09:00","2018-09-03 14:00","당일",null,null,null,201807200015,{"$f":"IF(ISERROR(VLOOKUP(D46,#REF!,13,0)),\"-\",VLOOKUP(D46,#REF!,13,0))","v":"-"}]
[43,"남서울","영등포","시흥독산#2 T/L","2018~2019 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험 - 개폐타임 측정","2018-09-07 14:00","2018-09-07 18:00","취소","취소","당일",null,null,null,201807200032,{"$f":"IF(ISERROR(VLOOKUP(D47,#REF!,13,0)),\"-\",VLOOKUP(D47,#REF!,13,0))","v":"-"}]
[44,"남서울","영등포","시흥독산#1 T/L","2018~2019 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험 - 개폐타임 측정","2018-09-07 09:00","2018-09-07 14:00","취소","취소","당일",null,null,null,201807200030,{"$f":"IF(ISERROR(VLOOKUP(D48,#REF!,13,0)),\"-\",VLOOKUP(D48,#REF!,13,0))","v":"-"}]
[45,"남서울","영등포","화곡마곡#1 T/L","2018~2019 영등포전력지사 변전협력회사 총액공사","170kV GIS 초기점검","2018-09-06 09:00","2018-09-06 14:00","취소","취소","당일",null,null,null,201807200021,{"$f":"IF(ISERROR(VLOOKUP(D49,#REF!,13,0)),\"-\",VLOOKUP(D49,#REF!,13,0))","v":"-"}]
[46,"남서울","영등포","화곡마곡#2 T/L","2018~2019 영등포전력지사 변전협력회사 총액공사","170kV GIS 초기점검","2018-09-06 14:00","2018-09-06 18:00","취소","취소","당일",null,null,null,201807200022,{"$f":"IF(ISERROR(VLOOKUP(D50,#REF!,13,0)),\"-\",VLOOKUP(D50,#REF!,13,0))","v":"-"}]
[47,"남서울","영등포","신정목동#1 T/L","2018~2019 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험 - 개폐타임 측정","2018-09-12 09:00","2018-09-12 18:00","2018-09-13 09:00","2018-09-13 18:00","당일",null,null,null,201807200028,{"$f":"IF(ISERROR(VLOOKUP(D51,#REF!,13,0)),\"-\",VLOOKUP(D51,#REF!,13,0))","v":"-"}]
[48,"남서울","영등포","신광명시흥#1 T/L","2018~2019 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험 - 개폐타임측정","2018-09-05 09:00","2018-09-05 18:00","취소","취소","당일",null,null,null,201807200036,{"$f":"IF(ISERROR(VLOOKUP(D52,#REF!,13,0)),\"-\",VLOOKUP(D52,#REF!,13,0))","v":"-"}]
[49,"남서울","영등포","고강화곡#1 T/L","2018~2019 영등포전력지사 변전협력회사 총액공사","170kV GIS 초기점검","2018-09-10 09:00","2018-09-10 14:00","취소","취소","당일",null,null,null,201807200024,{"$f":"IF(ISERROR(VLOOKUP(D53,#REF!,13,0)),\"-\",VLOOKUP(D53,#REF!,13,0))","v":"-"}]
[50,"남서울","영등포","고강화곡#2 T/L","2018~2019 영등포전력지사 변전협력회사 총액공사","170kV GIS 초기점검","2018-09-10 14:00","2018-09-10 18:00","취소","취소","당일",null,null,null,201807200026,{"$f":"IF(ISERROR(VLOOKUP(D54,#REF!,13,0)),\"-\",VLOOKUP(D54,#REF!,13,0))","v":"-"}]
[51,"남서울","직할","봉천신길#2 T/L","154kV 신길인출전력구 OF케이블 선종교체공사","1. 공사명 : 154kV 신길인출전력구 OF케이블 선종교체공사 2. 공사구간 : 신길S/S ~ 신길-대방관로 M/H#23-2 3. 규모 : XLPE 1,200SQ 1.03km 4. 주요공정 - 케이블포설 : 12구간, - 케이블 접속 : 중간접속 3개소, 종단접속 1개소","2018-09-10 09:00","2018-11-07 18:00","2018-09-10 09:00","2018-11-07 18:00","연속",null,null,null,201807020126,{"$f":"IF(ISERROR(VLOOKUP(D55,#REF!,13,0)),\"-\",VLOOKUP(D55,#REF!,13,0))","v":"-"}]
[52,"남서울","직할","영등포양평#1 T/L","154kV 차단기 보통점검","영등포-양평#1T/L 차단기 보통점검","2018-09-10 10:00","2018-09-10 18:00","2018-09-10 10:00","2018-09-10 18:00","당일",null,null,null,201807090324,{"$f":"IF(ISERROR(VLOOKUP(D56,#REF!,13,0)),\"-\",VLOOKUP(D56,#REF!,13,0))","v":"-"}]
[53,"남서울","직할","영등포양평#2 T/L","154kV 차단기 보통점검","영등포-양평#2T/L 차단기 보통점검","2018-09-11 10:00","2018-09-11 18:00","2018-09-11 10:00","2018-09-11 18:00","당일",null,null,null,201807090326,{"$f":"IF(ISERROR(VLOOKUP(D57,#REF!,13,0)),\"-\",VLOOKUP(D57,#REF!,13,0))","v":"-"}]
["추가","남서울","동서울","동남위례#2 T/L","154kV 동남S/S #3M.Tr 증설공사","  170kV GIS 증설 1CCT 증설\n- 모선GAS 감압관련 마지막 BAY 휴전 ","2018-09-01 09:00","2018-09-02 18:00","2018-09-01 09:00","2018-09-02 18:00","연속"]
["추가","남서울","동서울","동남위례#2 T/L","154kV 동남S/S #3M.Tr 증설공사","  170kV GIS 증설 1CCT 증설\n- #1 BUS 무부하가압 + 모선GAS 감압관련 휴전","2018-09-04 14:00","2018-09-06 18:00","2018-09-04 14:00","2018-09-06 18:00","연속"]
["추가","남서울","동서울","동남위례#2 T/L","154kV 동남S/S #3M.Tr 증설공사","  170kV GIS 증설 1CCT 증설\n- #2 BUS 무부하가압","2018-09-08 17:00","2018-09-09 17:00","2018-09-08 17:00","2018-09-09 17:00","연속"]
[54,"인천","인천","계양북인천 T/L","2018년 인천전력지사 170kV GIS 정밀점검공사","북인천S/S 계양북인천T/L GIS 정밀점검","2018-09-27 09:00","2018-09-29 18:00","2018-09-27 09:00","2018-09-29 18:00","연속",null,null,null,201807050079,{"$f":"IF(ISERROR(VLOOKUP(D61,#REF!,13,0)),\"-\",VLOOKUP(D61,#REF!,13,0))","v":"-"}]
[55,"인천","직할","부개S/S 154kV #1 BUS","부개S/S #1M.Tr 1차 170kV GIS 정밀점검","부개S/S #1M.Tr 1차 170kV GIS 정밀점검(1BUS휴전, 무부하용)","2018-09-28 14:00","2018-09-28 18:00","취소","취소","연속",null,null,null,201807120058,{"$f":"IF(ISERROR(VLOOKUP(D62,#REF!,13,0)),\"-\",VLOOKUP(D62,#REF!,13,0))","v":"-"}]
[56,"인천","직할","부천S/S 154kV #1 BUS","부천S/S 동부하이텍T/L 170kV GIS 정밀점검(1BUS 휴전)","부천S/S 동부하이텍T/L 170kV GIS 정밀점검(1BUS 휴전)","2018-09-18 10:00","2018-09-19 10:00","2018-09-18 10:00","2018-09-19 10:00","연속",null,null,null,201807120056,{"$f":"IF(ISERROR(VLOOKUP(D63,#REF!,13,0)),\"-\",VLOOKUP(D63,#REF!,13,0))","v":"-"}]
[57,"인천","직할","부천S/S 154kV #2 BUS","부천S/S 동부하이텍T/L 170kV GIS 정밀점검(2BUS 휴전)","부천S/S 동부하이텍T/L 170kV GIS 정밀점검(2BUS 휴전)","2018-09-19 10:00","2018-09-20 10:00","2018-09-19 10:00","2018-09-20 10:00","연속",null,null,null,201807120057,{"$f":"IF(ISERROR(VLOOKUP(D64,#REF!,13,0)),\"-\",VLOOKUP(D64,#REF!,13,0))","v":"-"}]
[58,"인천","시흥","서서울#2소래 T/L","154kV 서서울2소래T/L EBA 자기애관 교체공사","154kV 서서울2소래T/L EBA 자기애관 교체공사","2018-09-10 08:00","2018-09-11 18:00","2018-09-10 08:00","2018-09-11 18:00","연속",null,null,null,201807130038,{"$f":"IF(ISERROR(VLOOKUP(D65,#REF!,13,0)),\"-\",VLOOKUP(D65,#REF!,13,0))","v":"-"}]
[59,"인천","시흥","서안양소래 T/L","154kV 서안양소래T/L EBA 자기애관 교체공사","154kV 서안양소래T/L EBA 자기애관 교체공사","2018-09-08 08:00","2018-09-09 18:00","2018-09-08 08:00","2018-09-09 18:00","연속",null,null,null,201807130036,{"$f":"IF(ISERROR(VLOOKUP(D66,#REF!,13,0)),\"-\",VLOOKUP(D66,#REF!,13,0))","v":"-"}]
[60,"인천","인천","신가좌S/S 154kV #60 BUS","2018년 인천전력지사 170kV GIS 정밀점검공사","신가좌S/S 신가좌주안#1T/L GIS 정밀점검 후 무부하가압","2018-09-19 14:00","2018-09-19 18:00","취소","취소","당일",null,null,null,201807180089,{"$f":"IF(ISERROR(VLOOKUP(D67,#REF!,13,0)),\"-\",VLOOKUP(D67,#REF!,13,0))","v":"-"}]
[61,"인천","인천","신가좌S/S 154kV #60 BUS","2018년 인천전력지사 170kV GIS 정밀점검공사","신가좌S/S 신가좌주안#2T/L GIS 정밀점검 후 무부하가압","2018-09-22 14:00","2018-09-22 18:00","취소","취소","당일",null,null,null,201807180090,{"$f":"IF(ISERROR(VLOOKUP(D68,#REF!,13,0)),\"-\",VLOOKUP(D68,#REF!,13,0))","v":"-"}]
[62,"인천","인천","신가좌부개#1 T/L","154kV 신가좌-부개#1T/L OF케이블 절연유 채취밸브 설치 공사","신가좌SJ 등 6개소","2018-09-27 09:00","2018-09-28 18:00","취소","취소","연속",null,null,null,201807230039,{"$f":"IF(ISERROR(VLOOKUP(D69,#REF!,13,0)),\"-\",VLOOKUP(D69,#REF!,13,0))","v":"-"}]
[63,"인천","인천","신가좌부개#2 T/L","154kV 신가좌-부개#2T/L OF케이블 절연유 채취밸브 설치 공사","신가좌SJ 등 6개소","2018-09-27 09:00","2018-09-28 18:00","취소","취소","연속",null,null,null,201807230040,{"$f":"IF(ISERROR(VLOOKUP(D70,#REF!,13,0)),\"-\",VLOOKUP(D70,#REF!,13,0))","v":"-"}]
[64,"인천","인천","신가좌주안#1 T/L","2018년 인천전력지사 170kV GIS 정밀점검공사","신가좌S/S 신가좌주안#1T/L GIS 정밀점검","2018-09-17 09:00","2018-09-19 18:00","취소","취소","연속",null,null,null,201807050094,{"$f":"IF(ISERROR(VLOOKUP(D71,#REF!,13,0)),\"-\",VLOOKUP(D71,#REF!,13,0))","v":"-"}]
[65,"인천","인천","신가좌주안#2 T/L","2018년 인천전력지사 170kV GIS 정밀점검공사","신가좌S/S 신가좌주안#1T/L GIS 정밀점검","2018-09-20 09:00","2018-09-22 18:00","취소","취소","연속",null,null,null,201807050096,{"$f":"IF(ISERROR(VLOOKUP(D72,#REF!,13,0)),\"-\",VLOOKUP(D72,#REF!,13,0))","v":"-"}]
[66,"인천","시흥","신광명소래 T/L","154kV 서서울2소래T/L EBA 자기애관 교체공사","154kV 서서울2소래T/L EBA 자기애관 교체공사관련 안전 이격 휴전","2018-09-10 08:00","2018-09-11 18:00","2018-09-10 08:00","2018-09-11 18:00","연속",null,null,null,201807130039,{"$f":"IF(ISERROR(VLOOKUP(D73,#REF!,13,0)),\"-\",VLOOKUP(D73,#REF!,13,0))","v":"-"}]
[67,"인천","직할","신부평임학#2 T/L","154kV 신부평-중동 등 3개T/L 신부평변전소 인출Bay 정비공사","○ 345kV 신부평변전소 154kV 지중T/L 인출Bay 정비(신부평S/S~J/B#1) - 목적 : 양모선 고장시 대규모 정전 방지를 위한 계통 취약개소 안정성 향상","2018-09-14 09:00","2018-10-24 18:00","2018-09-14 09:00","2018-10-24 18:00","연속",null,null,null,201807110132,{"$f":"IF(ISERROR(VLOOKUP(D74,#REF!,13,0)),\"-\",VLOOKUP(D74,#REF!,13,0))","v":"-"}]
[68,"인천","직할","신부평중동#2 T/L","중동S/S 154kV GIS 설치공사","- 154kV GIS × 22CCT 설치 - 신규GIS와 기설GIS 모선 연결 (#2 BUS 시험가압)","2018-09-12 10:00","2018-09-13 10:00","2018-09-12 10:00","2018-09-13 10:00","연속",null,null,null,201807040101,{"$f":"IF(ISERROR(VLOOKUP(D75,#REF!,13,0)),\"-\",VLOOKUP(D75,#REF!,13,0))","v":"-"}]
[69,"인천","직할","신부평중동#2 T/L","중동S/S 154kV GIS 설치공사","- 154kV GIS × 22CCT 설치 - 신규GIS와 기설GIS 모선 연결 (#1 BUS 시험가압)","2018-09-07 10:00","2018-09-08 10:00","2018-09-07 10:00","2018-09-08 10:00","연속",null,null,null,201807040100,{"$f":"IF(ISERROR(VLOOKUP(D76,#REF!,13,0)),\"-\",VLOOKUP(D76,#REF!,13,0))","v":"-"}]
[70,"인천","직할","신부평중동#3 T/L","154kV 신부평-중동 등 3개T/L 신부평변전소 인출Bay 정비공사","○ 345kV 신부평변전소 154kV 지중T/L 인출Bay 정비(신부평S/S~J/B#1) - 목적 : 양모선 고장시 대규모 정전 방지를 위한 계통 취약개소 안정성 향상","2018-09-14 09:00","2018-10-24 18:00","2018-09-14 09:00","2018-10-24 18:00","연속",null,null,null,201807110142,{"$f":"IF(ISERROR(VLOOKUP(D77,#REF!,13,0)),\"-\",VLOOKUP(D77,#REF!,13,0))","v":"-"}]
[71,"인천","시흥","신시흥#2S/S 154kV #67 BUS","신시흥S/S 신시흥시화#2 T/L GIS 대체공사","신시흥S/S 신시흥시화#2 T/L GIS 대체공사","2018-09-30 08:00","2018-10-02 08:00","2018-09-30 08:00","2018-10-02 08:00","연속",null,null,null,201807120041,{"$f":"IF(ISERROR(VLOOKUP(D78,#REF!,13,0)),\"-\",VLOOKUP(D78,#REF!,13,0))","v":"-"}]
[72,"인천","시흥","신시흥북시화#1 T/L","북시화S/S 신시흥북시화#1 T/L GIS 초기점검","북시화S/S 신시흥북시화#1 T/L GIS 초기점검","2018-09-28 10:00","2018-09-28 18:00","2018-09-28 10:00","2018-09-28 18:00","당일",null,null,null,201807120036,{"$f":"IF(ISERROR(VLOOKUP(D79,#REF!,13,0)),\"-\",VLOOKUP(D79,#REF!,13,0))","v":"-"}]
[73,"인천","시흥","신시흥북시화#2 T/L","154kV 신시흥-북시화#2T/L 피뢰기 설치공사","154kV 신시흥-북시화#2T/L 피뢰기 설치공사 -평일 휴전불가로 10/3 작업예정(별도신청)","2018-09-30 08:00","2018-09-30 18:00","2018-09-30 08:00","2018-09-30 18:00","당일",null,null,null,201807060137,{"$f":"IF(ISERROR(VLOOKUP(D80,#REF!,13,0)),\"-\",VLOOKUP(D80,#REF!,13,0))","v":"-"}]
[74,"인천","시흥","신시흥시화#2 T/L","신시흥S/S 신시흥시화#2 T/L GIS 대체공사","신시흥S/S 신시흥시화#2 T/L GIS 대체공사","2018-09-30 08:00","2018-10-09 18:00","2018-09-30 08:00","2018-10-09 18:00","연속",null,null,null,201807120039,{"$f":"IF(ISERROR(VLOOKUP(D81,#REF!,13,0)),\"-\",VLOOKUP(D81,#REF!,13,0))","v":"-"}]
[75,"인천","김포","영종경서 T/L","154kV 영종-경서T/L 접지선 교체공사","○ 접지선 교체 : 접속함 규격 미달개소 보강을 통한 설비신뢰도 향상 - 접속함 : 154kV 영종-경서T/L M/H #38 (접지선 150㎟ → 240㎟)","2018-09-03 09:00","2018-09-03 18:00","2018-09-03 09:00","2018-09-03 18:00","당일",null,null,null,201807120012,{"$f":"IF(ISERROR(VLOOKUP(D82,#REF!,13,0)),\"-\",VLOOKUP(D82,#REF!,13,0))","v":"-"}]
[76,"인천","시흥","온수소래 T/L","154kV 서안양소래T/L EBA 자기애관 교체공사","154kV 서안양소래T/L EBA 자기애관 교체공사관련 안전 이격 휴전","2018-09-08 08:00","2018-09-09 18:00","2018-09-08 08:00","2018-09-09 18:00","연속",null,null,null,201807130037,{"$f":"IF(ISERROR(VLOOKUP(D83,#REF!,13,0)),\"-\",VLOOKUP(D83,#REF!,13,0))","v":"-"}]
[77,"인천","인천","인천남인천#1 T/L","인천,남인천S/S 인천남인천#1T/L 보호반 대체공사","인천,남인천S/S 인천남인천#1T/L 보호반 대체공사","2018-09-10 09:00","2018-09-14 18:00","2018-09-10 09:00","2018-09-14 18:00","연속",null,null,null,201807090455,{"$f":"IF(ISERROR(VLOOKUP(D84,#REF!,13,0)),\"-\",VLOOKUP(D84,#REF!,13,0))","v":"-"}]
[78,"인천","인천","인천남인천#2 T/L","인천,남인천S/S 인천남인천#2T/L 보호반 대체공사","인천,남인천S/S 인천남인천#2T/L 보호반 대체공사","2018-09-17 09:00","2018-09-21 18:00","2018-09-17 09:00","2018-09-21 18:00","연속",null,null,null,201807090456,{"$f":"IF(ISERROR(VLOOKUP(D85,#REF!,13,0)),\"-\",VLOOKUP(D85,#REF!,13,0))","v":"-"}]
[79,"인천","직할","중동S/S 154kV #1 BUS","중동S/S 154kV GIS 대체공사","중동S/S 154kV GIS 대체공사 중동-화곡#2T/L, #1M.Tr 1차 GIS","2018-09-14 09:00","2018-09-15 09:00","취소","취소","연속",null,null,null,201807110156,{"$f":"IF(ISERROR(VLOOKUP(D86,#REF!,13,0)),\"-\",VLOOKUP(D86,#REF!,13,0))","v":"-"}]
[80,"인천","직할","중동S/S 154kV #1 BUS","중동S/S 154kV GIS 대체공사","중동S/S 154kV GIS 대체공사 중동-화곡#2T/L 인출GIB 무부하 가압","2018-09-18 16:00","2018-09-19 16:00","취소","취소","연속",null,null,null,201807110164,{"$f":"IF(ISERROR(VLOOKUP(D87,#REF!,13,0)),\"-\",VLOOKUP(D87,#REF!,13,0))","v":"-"}]
[81,"인천","직할","중동S/S 154kV #1 BUS","중동S/S 154kV GIS 대체공사","중동S/S 154kV GIS 대체공사 중동-화곡#1T/L,#2M.Tr 1차 GIS 대체 공사","2018-09-28 08:00","2018-09-29 09:00","취소","취소","연속",null,null,null,201807110206,{"$f":"IF(ISERROR(VLOOKUP(D88,#REF!,13,0)),\"-\",VLOOKUP(D88,#REF!,13,0))","v":"-"}]
[82,"인천","직할","중동S/S 154kV #1 BUS","중동S/S 154kV GIS 설치공사","- 154kV GIS × 22CCT 설치 - 신규GIS와 기설GIS 모선 연결","2018-09-03 09:30","2018-09-08 10:00","취소","취소","연속",null,null,null,201807040093,{"$f":"IF(ISERROR(VLOOKUP(D89,#REF!,13,0)),\"-\",VLOOKUP(D89,#REF!,13,0))","v":"-"}]
[83,"인천","직할","중동S/S 154kV #2 BUS","중동S/S 154kV GIS 대체공사","중동S/S 154kV GIS 대체공사 중동-화곡#2T/L, #1M.Tr 1차 GIS","2018-09-13 08:00","2018-09-14 09:00","취소","취소","연속",null,null,null,201807110152,{"$f":"IF(ISERROR(VLOOKUP(D90,#REF!,13,0)),\"-\",VLOOKUP(D90,#REF!,13,0))","v":"-"}]
[84,"인천","직할","중동S/S 154kV #2 BUS","중동S/S 154kV GIS 대체공사","중동S/S 154kV GIS 대체공사 중동-화곡#1T/L,#2M.Tr 1차 GIS 대체 공사","2018-09-27 08:00","2018-09-28 09:00","취소","취소","연속",null,null,null,201807110205,{"$f":"IF(ISERROR(VLOOKUP(D91,#REF!,13,0)),\"-\",VLOOKUP(D91,#REF!,13,0))","v":"-"}]
[85,"인천","직할","중동S/S 154kV #2 BUS","중동S/S 154kV GIS 설치공사","- 154kV GIS × 22CCT 설치 - 신규GIS와 기설GIS 모선 연결","2018-09-08 10:00","2018-09-13 10:00","취소","취소","연속",null,null,null,201807040099,{"$f":"IF(ISERROR(VLOOKUP(D92,#REF!,13,0)),\"-\",VLOOKUP(D92,#REF!,13,0))","v":"-"}]
[86,"인천","직할","중동화곡#1 T/L","중동S/S 154kV GIS 대체공사","중동S/S 154kV GIS 대체공사 중동-화곡#1T/L,#2M.Tr 1차 GIS 대체 공사","2018-09-27 08:00","2018-10-03 18:00","취소","취소","연속",null,null,null,201807110207,{"$f":"IF(ISERROR(VLOOKUP(D93,#REF!,13,0)),\"-\",VLOOKUP(D93,#REF!,13,0))","v":"-"}]
[87,"인천","직할","중동화곡#2 T/L","중동S/S 154kV GIS 대체공사","중동S/S 154kV GIS 대체공사 중동-화곡#2T/L, #1M.Tr 1차 GIS","2018-09-13 08:00","2018-09-19 18:00","취소","취소","연속",null,null,null,201807110157,{"$f":"IF(ISERROR(VLOOKUP(D94,#REF!,13,0)),\"-\",VLOOKUP(D94,#REF!,13,0))","v":"-"}]
[88,"인천","직할","신부평부흥#1 T/L","345kV 신부평#2S/S 토건공사 ","154kV 신부평 -부흥 T/L 지중 연결을 위한 전력구공사 시행 ㅇ 기설 전력구 벽체 철거 ","2018-09-03 09:00","2018-09-12 18:00","취소","취소","매일",null,null,null,201807240064,{"$f":"IF(ISERROR(VLOOKUP(D95,#REF!,13,0)),\"-\",VLOOKUP(D95,#REF!,13,0))","v":"-"}]
[89,"인천","직할","신부평부흥#2 T/L","345kV 신부평#2S/S 토건공사 ","154kV 신부평 -부흥 T/L 지중 연결을 위한 전력구공사 시행 ㅇ 기설 전력구 벽체 철거 ","2018-09-03 09:00","2018-09-12 18:00","취소","취소","매일",null,null,null,201807240063,{"$f":"IF(ISERROR(VLOOKUP(D96,#REF!,13,0)),\"-\",VLOOKUP(D96,#REF!,13,0))","v":"-"}]
[90,"인천","인천","신가좌인천#1 T/L","2018년 인천전력지사 170kV GIS 정밀점검공사","신가좌S/S 신가좌주안#1T/L GIS 정밀점검 후 무부하가압","2018-09-19 14:00","2018-09-19 18:00","2018-09-19 14:00","2018-09-19 18:00","당일",null,null,null,201807300060,{"$f":"IF(ISERROR(VLOOKUP(D97,#REF!,13,0)),\"-\",VLOOKUP(D97,#REF!,13,0))","v":"-"}]
[91,"인천","인천","신가좌인천#1 T/L","2018년 인천전력지사 170kV GIS 정밀점검공사","신가좌S/S 신가좌주안#2T/L GIS 정밀점검 후 무부하가압","2018-09-22 14:00","2018-09-22 18:00","2018-09-22 14:00","2018-09-22 18:00","당일",null,null,null,201807300061,{"$f":"IF(ISERROR(VLOOKUP(D98,#REF!,13,0)),\"-\",VLOOKUP(D98,#REF!,13,0))","v":"-"}]
[92,"인천","인천","경서북인천#1 T/L","2018년 인천전력지사 170kV GIS 정밀점검공사","북인천S/S 계양북인천T/L GIS 정밀점검 후 무부하가압","2018-09-29 14:00","2018-09-29 18:00","2018-09-29 14:00","2018-09-29 18:00","당일",null,null,null,201807300062,{"$f":"IF(ISERROR(VLOOKUP(D99,#REF!,13,0)),\"-\",VLOOKUP(D99,#REF!,13,0))","v":"-"}]
[93,"인천","인천","북인천S/S 154kV #1 BUS","2018년 인천전력지사 170kV GIS 정밀점검공사","북인천S/S 계양북인천T/L GIS 정밀점검 후 무부하가압","2018-09-29 14:00","2018-09-29 18:00","2018-09-29 14:00","2018-09-29 18:00","당일",null,null,null,201807180085,{"$f":"IF(ISERROR(VLOOKUP(D100,#REF!,13,0)),\"-\",VLOOKUP(D100,#REF!,13,0))","v":"-"}]
[94,"인천","직할","부천도당#1T/L","부천S/S 동부하이텍T/L 170kV GIS 정밀점검 ","부천S/S 동부하이텍T/L 170kV GIS 정밀점검 1BUS 무부하가압용 도당부천#1T/L 휴전 ","2018-09-19 10:00","2018-09-19 14:00","2018-09-19 10:00","2018-09-19 14:00","당일",null,null,null,201807300073,{"$f":"IF(ISERROR(VLOOKUP(D101,#REF!,13,0)),\"-\",VLOOKUP(D101,#REF!,13,0))","v":"-"}]
[95,"인천","직할","부천도당#1T/L","부천S/S 동부하이텍T/L 170kV GIS 정밀점검 ","부천S/S 동부하이텍T/L 170kV GIS 정밀점검 1BUS 무부하가압용 도당부천#1T/L 휴전 ","2018-09-20 10:00","2018-09-20 14:00","2018-09-20 10:00","2018-09-20 14:00","당일",null,null,null,201807300074,{"$f":"IF(ISERROR(VLOOKUP(D102,#REF!,13,0)),\"-\",VLOOKUP(D102,#REF!,13,0))","v":"-"}]
[96,"경기북부","고양","능곡상암#2 T/L","2018년 변전정비회사 총액공사(보호PNL 대체)","능곡S/S 능곡-상암#2T/L 보호PNL 대체 상암S/S 능곡-상암#2T/L 보호PNL 대체","2018-09-18 09:00","2018-09-20 18:00","2018-09-18 09:00","2018-09-20 18:00","연속",null,null,null,201806190034,{"$f":"IF(ISERROR(VLOOKUP(D103,#REF!,13,0)),\"-\",VLOOKUP(D103,#REF!,13,0))","v":"-"}]
[97,"경기북부","고양","문산월롱#2 T/L","서울문산고속도로 건설 지장송전선로 이설공사","서울문산고속도로 건설 지장이설구간 이설 - 154kV 문산-월롱T/L No.9~12(154kV 신덕은-문산T/L 4회선 구간) - 철탑 2기 신설, 3기 철거","2018-09-20 07:00","2018-09-29 18:00","2018-09-20 07:00","2018-09-29 18:00","연속",null,null,null,201807160075,{"$f":"IF(ISERROR(VLOOKUP(D104,#REF!,13,0)),\"-\",VLOOKUP(D104,#REF!,13,0))","v":"-"}]
[98,"경기북부","고양","신덕은문산#1 T/L","서울문산고속도로 건설 지장송전선로 이설공사","서울문산고속도로 건설 지장이설구간 이설 - 154kV 문산-월롱T/L No.9~12(154kV 신덕은-문산T/L 4회선 구간) - 철탑 2기 신설, 3기 철거","2018-09-15 07:00","2018-09-19 18:00","취소","취소","연속",null,null,null,201807160071,{"$f":"IF(ISERROR(VLOOKUP(D105,#REF!,13,0)),\"-\",VLOOKUP(D105,#REF!,13,0))","v":"-"}]
[99,"경기북부","고양","신덕은문산#2 T/L","서울문산고속도로 건설 지장송전선로 이설공사","서울문산고속도로 건설 지장이설구간 이설 - 154kV 문산-월롱T/L No.9~12(154kV 신덕은-문산T/L 4회선 구간) - 철탑 2기 신설, 3기 철거","2018-09-20 07:00","2018-09-29 18:00","취소","취소","연속",null,null,null,201807160074,{"$f":"IF(ISERROR(VLOOKUP(D106,#REF!,13,0)),\"-\",VLOOKUP(D106,#REF!,13,0))","v":"-"}]
[100,"경기북부","고양","신덕은문산#1 T/L","서울문산고속도로 건설 지장송전선로 이설공사","서울문산고속도로 건설 지장이설구간 이설 - 154kV 문산-월롱T/L No.9~12(154kV 신덕은-문산T/L 4회선 구간) - 철탑 2기 신설, 3기 철거","2018-09-30 07:00","2018-10-05 18:00","취소","취소","연속",null,null,null,201807160073,{"$f":"IF(ISERROR(VLOOKUP(D107,#REF!,13,0)),\"-\",VLOOKUP(D107,#REF!,13,0))","v":"-"}]
[101,"경기북부","고양","문산월롱#1 T/L","서울문산고속도로 건설 지장송전선로 이설공사","서울문산고속도로 건설 지장이설구간 이설 - 154kV 문산-월롱T/L No.9~12(154kV 신덕은-문산T/L 4회선 구간) - 철탑 2기 신설, 3기 철거","2018-09-30 07:00","2018-10-05 18:00","2018-09-30 07:00","2018-10-05 18:00","연속",null,null,null,201807160077,{"$f":"IF(ISERROR(VLOOKUP(D108,#REF!,13,0)),\"-\",VLOOKUP(D108,#REF!,13,0))","v":"-"}]
[102,"경기북부","고양","문산월롱#1 T/L","서울문산고속도로 건설 지장송전선로 이설공사","서울문산고속도로 건설 지장이설구간 이설 - 154kV 문산-월롱T/L No.9~12(154kV 신덕은-문산T/L 4회선 구간) - 철탑 2기 신설, 3기 철거","2018-09-15 07:00","2018-09-19 18:00","2018-09-15 07:00","2018-09-19 18:00","연속",null,null,null,201807160076,{"$f":"IF(ISERROR(VLOOKUP(D109,#REF!,13,0)),\"-\",VLOOKUP(D109,#REF!,13,0))","v":"-"}]
[103,"경기북부","구리","가평청평HP#1 T/L","154kV 가평-청평HP#1 T/L 피뢰기 설치공사","ㅇ 피뢰기 설치 - No.1~43호","2018-09-16 07:30","2018-09-19 18:00","취소","취소","연속",null,null,null,201807120015,{"$f":"IF(ISERROR(VLOOKUP(D110,#REF!,13,0)),\"-\",VLOOKUP(D110,#REF!,13,0))","v":"-"}]
[104,"경기북부","구리","가평춘천HP T/L","154kV 가평-춘천HP T/L 피뢰기 설치공사","ㅇ 피뢰기 설치 - No.70~135호","2018-09-11 07:30","2018-09-16 18:00","2018-09-11 07:30","2018-09-16 18:00","연속",null,null,null,201807120013,{"$f":"IF(ISERROR(VLOOKUP(D111,#REF!,13,0)),\"-\",VLOOKUP(D111,#REF!,13,0))","v":"-"}]
[105,"경기북부","구리","마석청평HP#1 T/L","154kV 마석-청평HP#1T/L 정밀점검 불량적출개소 정비공사","ㅇ 정밀점검 불량적출개소 정비공사 - 노후취약금구 교체 : No.3,6,8,9,10,24호 - 불량애자 교체 : No.12 - SB댐퍼 설치 : No.7,8,18,19,20,22,23","2018-09-03 07:30","2018-09-05 18:00","2018-09-03 07:30","2018-09-05 18:00","연속",null,null,null,201806140038,{"$f":"IF(ISERROR(VLOOKUP(D112,#REF!,13,0)),\"-\",VLOOKUP(D112,#REF!,13,0))","v":"-"}]
[106,"경기북부","구리","미금화양 T/L","170kV 미금S/S 장기사용 GIS 교체공사(2차분)","- 170kV GIS 철거, 설치 - 기타부대공사","2018-09-01 08:00","2018-10-06 18:00","취소","취소","연속",null,null,null,201807120043,{"$f":"IF(ISERROR(VLOOKUP(D113,#REF!,13,0)),\"-\",VLOOKUP(D113,#REF!,13,0))","v":"-"}]
[107,"경기북부","구리","미금광장 T/L","170kV 미금S/S 장기사용 GIS 교체공사(2차분)","- 170kV GIS 철거, 설치(시험가압 선로) - 기타부대공사 - 병행공사 : 송전선로 피뢰기 설치(No.1~5호) / 감독 : 송전부 조태현","2018-09-13 07:00","2018-09-14 08:00","취소","취소","연속",null,null,null,201807120070,{"$f":"IF(ISERROR(VLOOKUP(D114,#REF!,13,0)),\"-\",VLOOKUP(D114,#REF!,13,0))","v":"-"}]
[108,"경기북부","구리","미금덕소#1 T/L","ㅇ 154kV 미금-덕소#1T/L 피뢰기 설치공사","ㅇ 피뢰기 설치 : No.1~5호","2018-09-10 07:30","2018-09-10 14:00","2018-09-10 07:30","2018-09-10 14:00","당일",null,null,null,201807170107,{"$f":"IF(ISERROR(VLOOKUP(D115,#REF!,13,0)),\"-\",VLOOKUP(D115,#REF!,13,0))","v":"-"}]
[109,"경기북부","구리","미금S/S 154kV #67 BUS","170kV 미금S/S 장기사용 GIS 교체공사(2차분)","- 170kV GIS 철거, 설치 - 기타부대공사","2018-09-01 08:00","2018-09-03 08:00","2018-09-01 08:00","2018-09-03 08:00","연속",null,null,null,201807120046,{"$f":"IF(ISERROR(VLOOKUP(D116,#REF!,13,0)),\"-\",VLOOKUP(D116,#REF!,13,0))","v":"-"}]
[110,"경기북부","구리","미금S/S 154kV #66 BUS","170kV 미금S/S 장기사용 GIS 교체공사(2차분)","- 170kV GIS 철거, 설치 - 기타부대공사","2018-09-01 08:00","2018-09-03 08:00","2018-09-01 08:00","2018-09-03 08:00","연속",null,null,null,201807120045,{"$f":"IF(ISERROR(VLOOKUP(D117,#REF!,13,0)),\"-\",VLOOKUP(D117,#REF!,13,0))","v":"-"}]
[111,"경기북부","구리","미금광장 T/L","170kV 미금S/S 장기사용 GIS 교체공사(2차분)","- 170kV GIS 철거, 설치(시험가압 선로) - 기타부대공사","2018-09-02 14:00","2018-09-03 08:00","취소","취소","연속",null,null,null,201807120069,{"$f":"IF(ISERROR(VLOOKUP(D118,#REF!,13,0)),\"-\",VLOOKUP(D118,#REF!,13,0))","v":"-"}]
[112,"경기북부","구리","미금S/S 154kV #66 BUS","170kV 미금S/S 장기사용 GIS 교체공사(2차분)","- 170kV GIS 철거, 설치 - 기타부대공사","2018-09-14 08:00","2018-10-06 10:00","2018-09-14 08:00","2018-10-06 10:00","연속",null,null,null,201807120049,{"$f":"IF(ISERROR(VLOOKUP(D119,#REF!,13,0)),\"-\",VLOOKUP(D119,#REF!,13,0))","v":"-"}]
[113,"경기북부","구리","미금S/S 154kV #67 BUS","170kV 미금S/S 장기사용 GIS 교체공사(2차분)","- 170kV GIS 철거, 설치 - 기타부대공사","2018-09-14 08:00","2018-10-06 10:00","2018-09-14 08:00","2018-10-06 10:00","연속",null,null,null,201807120050,{"$f":"IF(ISERROR(VLOOKUP(D120,#REF!,13,0)),\"-\",VLOOKUP(D120,#REF!,13,0))","v":"-"}]
[114,"경기북부","구리","미금S/S 154kV #61 BUS","170kV 미금S/S 장기사용 GIS 교체공사(2차분)","- 170kV GIS 철거, 설치 - 기타부대공사","2018-09-03 08:00","2018-09-14 08:00","2018-09-03 08:00","2018-09-14 08:00","연속",null,null,null,201807120047,{"$f":"IF(ISERROR(VLOOKUP(D121,#REF!,13,0)),\"-\",VLOOKUP(D121,#REF!,13,0))","v":"-"}]
[115,"경기북부","구리","미금S/S 154kV #62 BUS","170kV 미금S/S 장기사용 GIS 교체공사(2차분)","- 170kV GIS 철거, 설치 - 기타부대공사","2018-09-03 08:00","2018-09-14 08:00","2018-09-03 08:00","2018-09-14 08:00","연속",null,null,null,201807120048,{"$f":"IF(ISERROR(VLOOKUP(D122,#REF!,13,0)),\"-\",VLOOKUP(D122,#REF!,13,0))","v":"-"}]
[116,"경기북부","구리","진건별내#2 T/L","154kV 별내S/S #3M.Tr 증설공사","154kV GIS * 1CCT 증설(154kV #2BUS 증설 시험가압)","2018-09-18 18:00","2018-09-19 18:00","2018-09-18 18:00","2018-09-19 18:00","연속",null,null,null,201807170050,{"$f":"IF(ISERROR(VLOOKUP(D123,#REF!,13,0)),\"-\",VLOOKUP(D123,#REF!,13,0))","v":"-"}]
[117,"경기북부","구리","진건별내#1 T/L","154kV 별내S/S #3M.Tr 증설공사","#3M.Tr 무부하가압","2018-09-20 09:00","2018-09-21 13:00","2018-09-20 09:00","2018-09-21 13:00","연속",null,null,null,201807170041,{"$f":"IF(ISERROR(VLOOKUP(D124,#REF!,13,0)),\"-\",VLOOKUP(D124,#REF!,13,0))","v":"-"}]
[118,"경기북부","구리","진건별내#1 T/L","154kV 별내S/S #3M.Tr 증설공사","154kV GIS * 1CCT 증설(154kV #1BUS 증설 시험가압)","2018-09-06 18:00","2018-09-07 18:00","2018-09-06 18:00","2018-09-07 18:00","연속",null,null,null,201807170047,{"$f":"IF(ISERROR(VLOOKUP(D125,#REF!,13,0)),\"-\",VLOOKUP(D125,#REF!,13,0))","v":"-"}]
[119,"경기북부","구리","신포천덕계#1 T/L","'18~'19년 경기북부직할 가공송전정비 협력회사 총액공사","피뢰기 설치 및 불량애자교체","2018-09-17 08:00","2018-09-17 18:00","2018-09-17 08:00","2018-09-17 18:00","당일",null,null,null,201807120136,{"$f":"IF(ISERROR(VLOOKUP(D126,#REF!,13,0)),\"-\",VLOOKUP(D126,#REF!,13,0))","v":"-"}]
[120,"경기북부","구리","신포천전곡#1 T/L","'18~'19년 경기북부직할 가공송전정비 협력회사 총액공사","불량애자교체 154kV 운천-전곡#2T/L 하단병가선로","2018-09-19 12:00","2018-09-19 18:00","2018-09-19 12:00","2018-09-19 18:00","당일",null,null,null,201807160104,{"$f":"IF(ISERROR(VLOOKUP(D127,#REF!,13,0)),\"-\",VLOOKUP(D127,#REF!,13,0))","v":"-"}]
[121,"경기북부","구리","신포천전곡#2 T/L","'18~'19년 경기북부직할 가공송전정비 협력회사 총액공사","피뢰기 설치 및 불량애자교체","2018-09-17 08:00","2018-09-18 14:00","2018-09-17 08:00","2018-09-18 14:00","연속",null,null,null,201807120135,{"$f":"IF(ISERROR(VLOOKUP(D128,#REF!,13,0)),\"-\",VLOOKUP(D128,#REF!,13,0))","v":"-"}]
[122,"경기북부","구리","운천전곡#2 T/L","'18~'19년 경기북부직할 가공송전정비 협력회사 총액공사","불량애자교체","2018-09-19 08:00","2018-09-19 18:00","2018-09-19 08:00","2018-09-19 18:00","당일",null,null,null,201807160101,{"$f":"IF(ISERROR(VLOOKUP(D129,#REF!,13,0)),\"-\",VLOOKUP(D129,#REF!,13,0))","v":"-"}]
[123,"경기북부","구리","운천철원#1 T/L","18년 154kV GIS 정밀점검공사","18년 154kV GIS 정밀점검공사 - CB, 1DS, 2DS, 6DS","2018-09-09 08:30","2018-09-11 18:00","2018-09-09 08:30","2018-09-11 18:00","연속",null,null,null,201807130059,{"$f":"IF(ISERROR(VLOOKUP(D130,#REF!,13,0)),\"-\",VLOOKUP(D130,#REF!,13,0))","v":"-"}]
[124,"경기북부","구리","운천철원#2 T/L","구리전력 154kV GIS 보통점검","구리전력 154kV GIS 보통점검 -차단기 개폐타임 -주/보조회로 절연저항,접촉저항 측정 -공압식 차단기 메커니즘 분해점검 -기타 부대설비 점검","2018-09-27 08:00","2018-09-27 18:00","2018-09-27 08:00","2018-09-27 18:00","당일",null,null,null,201807130130,{"$f":"IF(ISERROR(VLOOKUP(D131,#REF!,13,0)),\"-\",VLOOKUP(D131,#REF!,13,0))","v":"-"}]
[125,"경기북부","구리","운천전곡#1 T/L","'18~'19년 경기북부직할 가공송전정비 협력회사 총액공사","불량애자교체","2018-09-18 08:00","2018-09-18 18:00","2018-09-18 08:00","2018-09-18 18:00","당일",null,null,null,201807120139,{"$f":"IF(ISERROR(VLOOKUP(D132,#REF!,13,0)),\"-\",VLOOKUP(D132,#REF!,13,0))","v":"-"}]
[126,"경기북부","구리","지제S/S 154kV #1 BUS TIE CB","구리전력 상반기 장기무동작 차단기 점검","구리전력 상반기 장기무동작 차단기 점검 -차단기 개폐타임 측정 -구리스 고착 점검 -기타 부대설비 점검","2018-09-19 09:00","2018-09-19 18:00","2018-09-19 09:00","2018-09-19 18:00","당일",null,null,null,201807110221,{"$f":"IF(ISERROR(VLOOKUP(D133,#REF!,13,0)),\"-\",VLOOKUP(D133,#REF!,13,0))","v":"-"}]
[127,"경기북부","구리","별내진접 T/L","18년 154kV GIS 정밀점검공사","18년 154kV GIS 정밀점검공사 - 정밀점검 후 시험가압","2018-09-14 17:00","2018-09-14 18:00","2018-09-14 17:00","2018-09-14 18:00","당일",null,null,null,201807130134,{"$f":"IF(ISERROR(VLOOKUP(D134,#REF!,13,0)),\"-\",VLOOKUP(D134,#REF!,13,0))","v":"-"}]
[128,"경기북부","구리","서홍천청평PP T/L","구리전력 서홍천-청평PP 636 DS 조작회로 불량","구리전력 서홍천-청평PP 636 DS 조작회로 불량 - 인터록회로 불량 점검 - 회로 연결잭 단자 발청 점검","2018-09-28 14:00","2018-09-28 18:00","2018-09-28 14:00","2018-09-28 18:00","당일",null,null,null,201807160163,{"$f":"IF(ISERROR(VLOOKUP(D135,#REF!,13,0)),\"-\",VLOOKUP(D135,#REF!,13,0))","v":"-"}]
[129,"경기북부","구리","포천운천#1 T/L","'18~'19년 경기북부직할 가공송전정비 협력회사 총액공사","불량애자교체 154kV 운천-전곡#2T/L 상단병가선로","2018-09-19 08:00","2018-09-19 12:00","2018-09-19 08:00","2018-09-19 12:00","당일",null,null,null,201807160105,{"$f":"IF(ISERROR(VLOOKUP(D136,#REF!,13,0)),\"-\",VLOOKUP(D136,#REF!,13,0))","v":"-"}]
[130,"경기북부","구리","신포천포천#2 T/L","포천S/S 154kV 신포천-포천#2T/L GCB 노후대체","포천S/S 154kV 신포천-포천#2T/L GCB 노후대체","2018-09-30 09:00","2018-10-06 18:00","2018-09-30 09:00","2018-10-06 18:00","연속",null,null,null,201807130051,{"$f":"IF(ISERROR(VLOOKUP(D137,#REF!,13,0)),\"-\",VLOOKUP(D137,#REF!,13,0))","v":"-"}]
[131,"경기북부","구리","포천운천#2 T/L","'18~'19년 경기북부직할 가공송전정비 협력회사 총액공사","불량애자교체 154kV 운천-전곡#1T/L 상단병가선로","2018-09-18 14:00","2018-09-18 18:00","2018-09-18 14:00","2018-09-18 18:00","당일",null,null,null,201807120140,{"$f":"IF(ISERROR(VLOOKUP(D138,#REF!,13,0)),\"-\",VLOOKUP(D138,#REF!,13,0))","v":"-"}]
[132,"경기북부","직할","금오상계#2 T/L","2018년 가공송전 순시점검 위탁공사","불량애자 절연저항측정","2018-09-12 09:00","2018-09-13 18:00","2018-09-12 09:00","2018-09-13 18:00","연속",null,null,null,201807240004,{"$f":"IF(ISERROR(VLOOKUP(D139,#REF!,13,0)),\"-\",VLOOKUP(D139,#REF!,13,0))","v":"-"}]
[133,"경기북부","직할","금오상계#1 T/L","2018년 가공송전 순시점검 위탁공사","불량애자 절연저항측정","2018-09-10 09:00","2018-09-11 18:00","2018-09-10 09:00","2018-09-11 18:00","연속",null,null,null,201807240003,{"$f":"IF(ISERROR(VLOOKUP(D140,#REF!,13,0)),\"-\",VLOOKUP(D140,#REF!,13,0))","v":"-"}]
[134,"경기북부","직할","남면백석#2 T/L","'18년 변전협력회사 총액공사","170kV GIS 초기점검","2018-09-06 09:00","2018-09-06 18:00","2018-09-06 09:00","2018-09-06 18:00","당일",null,null,null,201807100026,{"$f":"IF(ISERROR(VLOOKUP(D141,#REF!,13,0)),\"-\",VLOOKUP(D141,#REF!,13,0))","v":"-"}]
[135,"경기북부","직할","양주고양#2 T/L","'18년 변전협력회사 총액공사","170kV GIS 개폐타임 측정","2018-09-07 09:00","2018-09-07 14:00","2018-09-07 09:00","2018-09-07 14:00","당일",null,null,null,201807100027,{"$f":"IF(ISERROR(VLOOKUP(D142,#REF!,13,0)),\"-\",VLOOKUP(D142,#REF!,13,0))","v":"-"}]
[136,"경기북부","직할","양주S/S 65-66-0 SEC CB","'18년 변전협력회사 총액공사","170kV GIS 개폐타임 측정","2018-09-07 14:00","2018-09-07 18:00","2018-09-07 14:00","2018-09-07 18:00","당일",null,null,null,201807100030,{"$f":"IF(ISERROR(VLOOKUP(D143,#REF!,13,0)),\"-\",VLOOKUP(D143,#REF!,13,0))","v":"-"}]
[137,"경기북부","직할","신의정부용현#1 T/L","'18년 변전협력회사 총액공사","170kV GIS 하자점검","2018-09-04 09:00","2018-09-04 18:00","취소","취소","당일",null,null,null,201807100023,{"$f":"IF(ISERROR(VLOOKUP(D144,#REF!,13,0)),\"-\",VLOOKUP(D144,#REF!,13,0))","v":"-"}]
[138,"경기북부","직할","신의정부용현#2 T/L","'18년 변전협력회사 총액공사","170kV GIS 하자점검","2018-09-05 09:00","2018-09-05 18:00","취소","취소","당일",null,null,null,201807100024,{"$f":"IF(ISERROR(VLOOKUP(D145,#REF!,13,0)),\"-\",VLOOKUP(D145,#REF!,13,0))","v":"-"}]
[139,"경기","군포","산본안양#1 T/L","산본변전소 #3M.Tr 1차 GIS 대체공사","산본변전소 #3M.Tr 1차 GIS 대체작업 1BUS 무부하 가압","2018-09-12 08:00","2018-09-13 18:00","2018-09-12 08:00","2018-09-13 18:00","연속",null,null,null,201807030132,{"$f":"IF(ISERROR(VLOOKUP(D146,#REF!,13,0)),\"-\",VLOOKUP(D146,#REF!,13,0))","v":"-"}]
[140,"경기","군포","서서울#2남수원 #1T/L","서서울#2S/S 170kV GIS 초기점검","서서울#2S/S 170kV GIS 초기점검 - 6D7","2018-09-27 13:00","2018-09-27 18:00","2018-09-27 13:00","2018-09-27 18:00","당일",null,null,null,201804300192,{"$f":"IF(ISERROR(VLOOKUP(D147,#REF!,13,0)),\"-\",VLOOKUP(D147,#REF!,13,0))","v":"-"}]
[141,"경기","군포","서서울#2일동 #2T/L","서서울#2S/S 170kV GIS 초기점검","서서울#2S/S 170kV GIS 초기점검 - 6A7","2018-09-12 09:00","2018-09-12 13:00","2018-09-12 09:00","2018-09-12 13:00","당일",null,null,null,201804300190,{"$f":"IF(ISERROR(VLOOKUP(D148,#REF!,13,0)),\"-\",VLOOKUP(D148,#REF!,13,0))","v":"-"}]
[142,"경기","군포","서서울#2일동 #1T/L","서서울#2S/S 170kV GIS 초기점검","서서울#2S/S 170kV GIS 초기점검 - 6B7","2018-09-12 13:00","2018-09-12 18:00","2018-09-12 13:00","2018-09-12 18:00","당일",null,null,null,201804300191,{"$f":"IF(ISERROR(VLOOKUP(D149,#REF!,13,0)),\"-\",VLOOKUP(D149,#REF!,13,0))","v":"-"}]
[143,"경기","군포","서서울#2남수원 #2T/L","서서울#2S/S 170kV GIS 초기점검","서서울#2S/S 170kV GIS 초기점검 - 6C7","2018-09-27 09:00","2018-09-27 13:00","2018-09-27 09:00","2018-09-27 13:00","당일",null,null,null,201804300193,{"$f":"IF(ISERROR(VLOOKUP(D150,#REF!,13,0)),\"-\",VLOOKUP(D150,#REF!,13,0))","v":"-"}]
[144,"경기","군포","서서울율전#1 T/L","서서울S/S 154kV 취약설비 GIS화 공사-인출철탑보강","서서울S/S 154kV 취약설비 GIS화 공사-율전#1T/L 인출철탑보강","2018-09-18 09:00","2018-09-18 12:00","2018-09-18 09:00","2018-09-18 12:00","당일",null,null,null,201807030120,{"$f":"IF(ISERROR(VLOOKUP(D151,#REF!,13,0)),\"-\",VLOOKUP(D151,#REF!,13,0))","v":"-"}]
[145,"경기","군포","목내안산복합#1 T/L","154kV 목내-안산복합#1T/L 맨홀내 접속함 방식층 보수공사","맨홀내 접속함 방식층 보수","2018-09-07 09:00","2018-09-08 18:00","2018-09-07 09:00","2018-09-08 18:00","연속",null,null,null,201807030082,{"$f":"IF(ISERROR(VLOOKUP(D152,#REF!,13,0)),\"-\",VLOOKUP(D152,#REF!,13,0))","v":"-"}]
[146,"경기","군포","목내안산복합#2 T/L","154kV 목내-안산복합#2T/L 맨홀내 접속함 방식층 보수공사","맨홀내 접속함 방식층 보수","2018-09-09 09:00","2018-09-10 18:00","2018-09-09 09:00","2018-09-10 18:00","연속",null,null,null,201807030083,{"$f":"IF(ISERROR(VLOOKUP(D153,#REF!,13,0)),\"-\",VLOOKUP(D153,#REF!,13,0))","v":"-"}]
[147,"경기","군포","화성조암#1 T/L","조암S/S 화성조암#1T/L GIS 보조계전기 교체작업","화성조암#1T/L GIS 노후 보조계전기 교체","2018-09-04 10:00","2018-09-04 18:00","2018-09-04 10:00","2018-09-04 18:00","당일",null,null,null,201804300202,{"$f":"IF(ISERROR(VLOOKUP(D154,#REF!,13,0)),\"-\",VLOOKUP(D154,#REF!,13,0))","v":"-"}]
[148,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2018-09-27 08:30","2018-09-29 16:00","취소","취소","연속",null,null,null,201807090100,{"$f":"IF(ISERROR(VLOOKUP(D155,#REF!,13,0)),\"-\",VLOOKUP(D155,#REF!,13,0))","v":"-"}]
[149,"경기","동부","곤지암S/S 154kV #2 Sh.C CB","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설 - 증설(4CCT): #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설(4CCT): #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2018-09-12 08:30","2018-11-02 17:30","취소","취소","연속",null,null,null,201807090081,{"$f":"IF(ISERROR(VLOOKUP(D156,#REF!,13,0)),\"-\",VLOOKUP(D156,#REF!,13,0))","v":"-"}]
[150,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2018-09-20 08:30","2018-09-22 17:30","취소","취소","연속",null,null,null,201807090095,{"$f":"IF(ISERROR(VLOOKUP(D157,#REF!,13,0)),\"-\",VLOOKUP(D157,#REF!,13,0))","v":"-"}]
[151,"경기","동부","곤지암S/S 154kV #66 BUS","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설 - 증설(4CCT): #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설(4CCT): #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2018-09-17 08:30","2018-09-30 17:30","취소","취소","연속",null,null,null,201807090089,{"$f":"IF(ISERROR(VLOOKUP(D158,#REF!,13,0)),\"-\",VLOOKUP(D158,#REF!,13,0))","v":"-"}]
[152,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2018-09-12 08:30","2018-09-14 17:30","취소","취소","연속",null,null,null,201807090090,{"$f":"IF(ISERROR(VLOOKUP(D159,#REF!,13,0)),\"-\",VLOOKUP(D159,#REF!,13,0))","v":"-"}]
[153,"경기","동부","곤지암S/S 154kV #1 Sh.C CB","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설 - 증설(4CCT): #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설(4CCT): #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2018-09-12 08:30","2018-11-02 17:30","취소","취소","연속",null,null,null,201807090078,{"$f":"IF(ISERROR(VLOOKUP(D160,#REF!,13,0)),\"-\",VLOOKUP(D160,#REF!,13,0))","v":"-"}]
[154,"경기","동부","곤지암이천#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2018-09-17 08:30","2018-09-19 17:30","취소","취소","연속",null,null,null,201807090092,{"$f":"IF(ISERROR(VLOOKUP(D161,#REF!,13,0)),\"-\",VLOOKUP(D161,#REF!,13,0))","v":"-"}]
[155,"경기","동부","이천S/S 이천-가남#1T/L GIS","이천-가남#1T/L #1DS 구동함교체","이천-가남#1T/L #1DS 구동함교체","2018-09-10 09:00","2018-09-11 18:00","2018-09-10 09:00","2018-09-11 18:00","연속",null,null,null,201807120133,{"$f":"IF(ISERROR(VLOOKUP(D162,#REF!,13,0)),\"-\",VLOOKUP(D162,#REF!,13,0))","v":"-"}]
[156,"경기","성남","남사진위#1 T/L","154kV 동탄S/S GIS 및 SIS 설치공사","- 남사-동탄#1T/L, 동탄-진위#1T/L 건설(병행작업) - 동탄S/S GIS C/H Chamber 조립 - 진위S/S 동탄-진위#1T/L Line PT 설치","2018-09-01 09:00","2018-09-30 18:00","2018-09-01 09:00","2018-09-30 18:00","연속",null,null,null,201806280020,{"$f":"IF(ISERROR(VLOOKUP(D163,#REF!,13,0)),\"-\",VLOOKUP(D163,#REF!,13,0))","v":"-"}]
[157,"경기","성남","모현용인#2 T/L","154kV 모현-용인#2T/L OPGW 표시구교체","0 항공장애표시구 교체 : 3-4호 등 13개소","2018-09-20 07:00","2018-09-22 18:00","2018-09-20 07:00","2018-09-22 18:00","연속",null,null,null,201803210169,{"$f":"IF(ISERROR(VLOOKUP(D164,#REF!,13,0)),\"-\",VLOOKUP(D164,#REF!,13,0))","v":"-"}]
[158,"경기","성남","오포모현#1 T/L","2018-2019년 송전정비 협력회사 총액공사(표시구설치)","0 항공장애표시구 설치 : 5-6호","2018-09-19 12:00","2018-09-19 18:00","2018-09-19 12:00","2018-09-19 18:00","당일",null,null,null,201807040077,{"$f":"IF(ISERROR(VLOOKUP(D165,#REF!,13,0)),\"-\",VLOOKUP(D165,#REF!,13,0))","v":"-"}]
[159,"경기","성남","모현용인#1 T/L","2018-2019년 송전정비 협력회사 총액공사(표시구설치)","0 항공장애표시구 설치 : 3-4호 등 14개소 39개","2018-09-15 07:00","2018-09-19 18:00","2018-09-15 07:00","2018-09-19 18:00","연속",null,null,null,201807040076,{"$f":"IF(ISERROR(VLOOKUP(D166,#REF!,13,0)),\"-\",VLOOKUP(D166,#REF!,13,0))","v":"-"}]
[160,"경기","성남","신봉수지#2 T/L","154kV 신봉-수지#2T/L 일진제 R-Type PMJ 교체공사","유사고장예방 일진제 구형 접속함 교체(Recall) - 공사대상 : JB#1~6, 총 36상","2018-09-06 08:00","2018-09-20 18:00","2018-09-06 08:00","2018-09-20 18:00","연속",null,null,null,201806270134,{"$f":"IF(ISERROR(VLOOKUP(D167,#REF!,13,0)),\"-\",VLOOKUP(D167,#REF!,13,0))","v":"-"}]
[161,"경기","성남","신성남S/S 154kV #4 Sh.C","신성남S/S #2M.Tr 2차 GIS 대체(안전이격)","신성남S/S #2M.Tr 2차 GIS 대체(안전이격)","2018-09-06 09:00","2018-09-21 18:00","2018-09-06 09:00","2018-09-21 18:00","연속",null,null,null,201807090392,{"$f":"IF(ISERROR(VLOOKUP(D168,#REF!,13,0)),\"-\",VLOOKUP(D168,#REF!,13,0))","v":"-"}]
[162,"경기","성남","신성남정자#1 T/L","정자S/S 신성남-정자#1T/L 가스 누기보수","정자S/S 신성남-정자#1T/L 가스 누기보수","2018-09-05 09:00","2018-09-06 18:00","2018-09-05 09:00","2018-09-06 18:00","연속",null,null,null,201807090395,{"$f":"IF(ISERROR(VLOOKUP(D169,#REF!,13,0)),\"-\",VLOOKUP(D169,#REF!,13,0))","v":"-"}]
[163,"경기","직할","서서울#2남수원 #1T/L","남수원S/S 154kV 장기사용 GIS 교체공사","남수원S/S 154kV 장기사용 GIS 교체공사(남수원발안2T/L,#3M.Tr) 무부하","2018-09-15 09:00","2018-09-17 09:00","2018-09-15 09:00","2018-09-17 09:00","연속",null,null,null,201807040018,{"$f":"IF(ISERROR(VLOOKUP(D170,#REF!,13,0)),\"-\",VLOOKUP(D170,#REF!,13,0))","v":"-"}]
[164,"경기","직할","남수원발안#2 T/L","남수원S/S 154kV 장기사용 GIS 교체공사","남수원S/S 154kV 장기사용 GIS 교체공사(남수원발안2T/L,#3M.Tr)","2018-08-27 09:00","2018-09-23 18:00","2018-08-27 09:00","2018-09-23 18:00","연속",null,null,null,201807030088,{"$f":"IF(ISERROR(VLOOKUP(D171,#REF!,13,0)),\"-\",VLOOKUP(D171,#REF!,13,0))","v":"-"}]
[165,"경기","직할","동수원우만#1 T/L","154kV 동수원변전소 현대화공사","154kV 전력케이블 인출변경, 보호반 대체","2018-09-03 09:00","2018-10-10 18:00","2018-09-03 09:00","2018-10-10 18:00","연속",null,null,null,201807030188,{"$f":"IF(ISERROR(VLOOKUP(D172,#REF!,13,0)),\"-\",VLOOKUP(D172,#REF!,13,0))","v":"-"}]
[166,"경기","직할","동안양안양CC#2 T/L","154kV 동안양-안양열병합#2T/L OF절연유 채유","OF절연유 채유작업","2018-09-13 09:00","2018-09-14 18:00","2018-09-13 09:00","2018-09-14 18:00","연속",null,null,null,201807030099,{"$f":"IF(ISERROR(VLOOKUP(D173,#REF!,13,0)),\"-\",VLOOKUP(D173,#REF!,13,0))","v":"-"}]
[167,"경기","직할","의왕동안양#2 T/L","154kV 의왕-동안양T/L 지장송전선로 지중화공사","임시선로 송전선로 구성 - 154kV 의왕-동안양T/L No.32,33,34,34-134-2(5기)","2018-09-06 07:00","2018-09-08 18:00","2018-09-06 07:00","2018-09-08 18:00","연속",null,null,null,201807040054,{"$f":"IF(ISERROR(VLOOKUP(D174,#REF!,13,0)),\"-\",VLOOKUP(D174,#REF!,13,0))","v":"-"}]
[168,"경기","직할","의왕동안양#1 T/L","154kV 의왕-동안양T/L 지장송전선로 지중화공사","임시선로 송전선로 구성 - 154kV 의왕-동안양T/L No.32,33,34,34-134-2(5기)","2018-09-03 07:00","2018-09-05 18:00","2018-09-03 07:00","2018-09-05 18:00","연속",null,null,null,201807040053,{"$f":"IF(ISERROR(VLOOKUP(D175,#REF!,13,0)),\"-\",VLOOKUP(D175,#REF!,13,0))","v":"-"}]
[169,"경기","직할","관양동안양#2 T/L","18년 직할 변전협력회사 총액공사","동안양S/S 관양동안양#2T/L GIS 보통점검","2018-09-27 10:00","2018-09-27 18:00","2018-09-27 10:00","2018-09-27 18:00","연속",null,null,null,201807090055,{"$f":"IF(ISERROR(VLOOKUP(D176,#REF!,13,0)),\"-\",VLOOKUP(D176,#REF!,13,0))","v":"-"}]
[170,"경기","직할","동안양안양CC#1 T/L","154kV 동안양-안양열병합#1T/L OF절연유 채유","OF절연유 채유작업","2018-09-11 09:00","2018-09-12 18:00","2018-09-11 09:00","2018-09-12 18:00","연속",null,null,null,201807030098,{"$f":"IF(ISERROR(VLOOKUP(D177,#REF!,13,0)),\"-\",VLOOKUP(D177,#REF!,13,0))","v":"-"}]
[171,"경기","직할","서서울율전#1 T/L","18년 직할 변전협력회사 총액공사","율전S/S 서서울율전#1T/L GIS 보통점검","2018-09-17 10:00","2018-09-17 18:00","2018-09-17 10:00","2018-09-17 18:00","당일",null,null,null,201807090039,{"$f":"IF(ISERROR(VLOOKUP(D178,#REF!,13,0)),\"-\",VLOOKUP(D178,#REF!,13,0))","v":"-"}]
[172,"경기","직할","발안향남#2 T/L","154kV 발안-향남T/L No.7-9 전선교체공사","154kV 발안-향남T/L No.7-9 전선교체공사","2018-09-15 07:00","2018-09-16 18:00","2018-09-15 07:00","2018-09-16 18:00","연속",null,null,null,201807050151,{"$f":"IF(ISERROR(VLOOKUP(D179,#REF!,13,0)),\"-\",VLOOKUP(D179,#REF!,13,0))","v":"-"}]
[173,"경기","직할","화성S/S 61-62 SEC GIS","18년 직할 154kV GCB/GIS 정밀점검공사","화성S/S 61-62-0 GIS 정밀점검공사","2018-09-10 09:00","2018-09-11 18:00","2018-09-10 09:00","2018-09-11 18:00","연속",null,null,null,201807060227,{"$f":"IF(ISERROR(VLOOKUP(D180,#REF!,13,0)),\"-\",VLOOKUP(D180,#REF!,13,0))","v":"-"}]
[174,"경기","직할","화성남양#1 T/L","18년 직할 변전협력회사 총액공사","화성S/S 화성남양#1T/L GIS,PT,LA보통","2018-09-08 09:00","2018-09-08 18:00","2018-09-08 09:00","2018-09-08 18:00","당일",null,null,null,201807090045,{"$f":"IF(ISERROR(VLOOKUP(D181,#REF!,13,0)),\"-\",VLOOKUP(D181,#REF!,13,0))","v":"-"}]
[175,"경기","직할","화성S/S 154kV #66 BUS","18년 직할 154kV GCB/GIS 정밀점검공사","화성S/S #4M.Tr 2차 GIS 정밀점검공사(무부하가압)","2018-09-21 09:00","2018-09-21 18:00","2018-09-21 09:00","2018-09-21 18:00","당일",null,null,null,201807060256,{"$f":"IF(ISERROR(VLOOKUP(D182,#REF!,13,0)),\"-\",VLOOKUP(D182,#REF!,13,0))","v":"-"}]
[176,"경기","직할","화성S/S 154kV #62 BUS","18년 직할 154kV GCB/GIS 정밀점검공사","화성S/S 6300 GIS 정밀점검공사(무부하가압)","2018-09-18 09:00","2018-09-18 18:00","2018-09-18 09:00","2018-09-18 18:00","당일",null,null,null,201807060253,{"$f":"IF(ISERROR(VLOOKUP(D183,#REF!,13,0)),\"-\",VLOOKUP(D183,#REF!,13,0))","v":"-"}]
[177,"경기","직할","화성S/S 154kV # 3BUS TIE GIS","18년 직할 154kV GCB/GIS 정밀점검공사","화성S/S 6300 GIS 정밀점검공사","2018-09-17 09:00","2018-09-18 18:00","2018-09-17 09:00","2018-09-18 18:00","연속",null,null,null,201807060232,{"$f":"IF(ISERROR(VLOOKUP(D184,#REF!,13,0)),\"-\",VLOOKUP(D184,#REF!,13,0))","v":"-"}]
[178,"경기","직할","화성남양#2 T/L","18년 직할 변전협력회사 총액공사","화성S/S 화성남양#2T/L GIS,PT,LA보통","2018-09-15 09:00","2018-09-15 18:00","2018-09-15 09:00","2018-09-15 18:00","당일",null,null,null,201807090108,{"$f":"IF(ISERROR(VLOOKUP(D185,#REF!,13,0)),\"-\",VLOOKUP(D185,#REF!,13,0))","v":"-"}]
[179,"경기","직할","화성S/S 154kV #66 BUS","18년 직할 154kV GCB/GIS 정밀점검공사","화성S/S 66-67-0 GIS 정밀점검공사(무부하가압)","2018-09-14 09:00","2018-09-14 18:00","2018-09-14 09:00","2018-09-14 18:00","당일",null,null,null,201807060252,{"$f":"IF(ISERROR(VLOOKUP(D186,#REF!,13,0)),\"-\",VLOOKUP(D186,#REF!,13,0))","v":"-"}]
[180,"경기","직할","화성S/S 66-67 SEC GIS","18년 직할 154kV GCB/GIS 정밀점검공사","화성S/S 66-67-0 GIS 정밀점검공사","2018-09-13 09:00","2018-09-14 18:00","2018-09-13 09:00","2018-09-14 18:00","연속",null,null,null,201807060231,{"$f":"IF(ISERROR(VLOOKUP(D187,#REF!,13,0)),\"-\",VLOOKUP(D187,#REF!,13,0))","v":"-"}]
[181,"경기","직할","화성S/S 154kV #61 BUS","18년 직할 154kV GCB/GIS 정밀점검공사","화성S/S 61-62-0 GIS 정밀점검공사(무부하가압)","2018-09-11 09:00","2018-09-11 18:00","2018-09-11 09:00","2018-09-11 18:00","당일",null,null,null,201807060250,{"$f":"IF(ISERROR(VLOOKUP(D188,#REF!,13,0)),\"-\",VLOOKUP(D188,#REF!,13,0))","v":"-"}]
[182,"경기","평택","송탄S/S 154kV #1 BUS TIE(6100) GIS","송탄S/S 154kV #1BUS TIE GIS 하자점검","송탄S/S 154kV #1BUS TIE GIS 하자점검","2018-09-03 10:00","2018-09-03 18:00","2018-09-03 10:00","2018-09-03 18:00","당일",null,null,null,201807090188,{"$f":"IF(ISERROR(VLOOKUP(D189,#REF!,13,0)),\"-\",VLOOKUP(D189,#REF!,13,0))","v":"-"}]
[183,"경기","평택","서안성안성#1 T/L","안성S/S 170kV GIS 용량대체공사","서안성-안성#1T/L GIS 철거 및 설치 6100B/T GIS 철거 및 설치 #2M.Tr GIS 철거 및 설치","2018-09-01 08:00","2018-09-21 18:00","2018-09-01 08:00","2018-09-21 18:00","연속",null,null,null,201806300008,{"$f":"IF(ISERROR(VLOOKUP(D190,#REF!,13,0)),\"-\",VLOOKUP(D190,#REF!,13,0))","v":"-"}]
[184,"경기","평택","서안성안성#1 T/L","154kV 서운-안성T/L 전력선 교체공사(안전확보)","- 공사구간 : No.2-6 (서안성-안성 병가) - 공사규모 : 전력선 14가닥 교체(1.059km)","2018-09-28 08:00","2018-09-30 18:00","2018-09-28 08:00","2018-09-30 18:00","매일",null,null,null,201807090079,{"$f":"IF(ISERROR(VLOOKUP(D191,#REF!,13,0)),\"-\",VLOOKUP(D191,#REF!,13,0))","v":"-"}]
[185,"경기","평택","안성S/S 154kV #1 BUS TIE CB","안성S/S 170kV GIS 용량대체공사","서안성-안성#1T/L GIS 철거 및 설치 6100B/T GIS 철거 및 설치 #2M.Tr GIS 철거 및 설치","2018-09-01 08:00","2018-09-21 18:00","2018-09-01 08:00","2018-09-21 18:00","연속",null,null,null,201806300010,{"$f":"IF(ISERROR(VLOOKUP(D192,#REF!,13,0)),\"-\",VLOOKUP(D192,#REF!,13,0))","v":"-"}]
[186,"경기","평택","서운안성#1 T/L","154kV 서운-안성T/L 전력선 교체공사","- 공사구간 : No.2-6 - 공사규모 : 전력선 14가닥 교체(1.059km)","2018-09-28 08:00","2018-09-30 18:00","2018-09-29 08:00","2018-09-30 18:00","연속",null,null,null,201807090074,{"$f":"IF(ISERROR(VLOOKUP(D193,#REF!,13,0)),\"-\",VLOOKUP(D193,#REF!,13,0))","v":"-"}]
[187,"경기","평택","오산향남#2 T/L","154kV 오산-향남T/L OPGW 증설공사","* No.16(C/H) ~ 오산S/S C/H OP-S-L48 교체 1.62km * 향남S/S G/T ~ 오산S/S C/H OP-S-L48 증설 5.75km * 오산S/S C/H ~ ICT실 FOFC-S-48 교체 0.206km 및 시설 0.206km * 향남S/S ICT실 ~ G/T FOFC-S-48 시설 0.048km * No.15(C/H) ~ N","2018-09-10 07:00","2018-09-30 18:00","2018-09-10 07:00","2018-09-30 18:00","연속",null,null,null,201807090175,{"$f":"IF(ISERROR(VLOOKUP(D194,#REF!,13,0)),\"-\",VLOOKUP(D194,#REF!,13,0))","v":"-"}]
[188,"경기","평택","오산향남#1 T/L","154kV 오산-향남T/L OPGW 증설공사","* No.16(C/H) ~ 오산S/S C/H OP-S-L48 교체 1.62km * 향남S/S G/T ~ 오산S/S C/H OP-S-L48 증설 5.75km * 오산S/S C/H ~ ICT실 FOFC-S-48 교체 0.206km 및 시설 0.206km * 향남S/S ICT실 ~ G/T FOFC-S-48 시설 0.048km * No.15(C/H) ~ N","2018-09-18 07:00","2018-09-19 18:00","2018-09-18 07:00","2018-09-19 18:00","연속",null,null,null,201807090176,{"$f":"IF(ISERROR(VLOOKUP(D195,#REF!,13,0)),\"-\",VLOOKUP(D195,#REF!,13,0))","v":"-"}]
[189,"경기","평택","오산평택#1 T/L","154kV 오산-향남T/L OPGW 증설공사","* No.16(C/H) ~ 오산S/S C/H OP-S-L48 교체 1.62km * 향남S/S G/T ~ 오산S/S C/H OP-S-L48 증설 5.75km * 오산S/S C/H ~ ICT실 FOFC-S-48 교체 0.206km 및 시설 0.206km * 향남S/S ICT실 ~ G/T FOFC-S-48 시설 0.048km * No.15(C/H) ~ N","2018-09-18 07:00","2018-09-19 18:00","2018-09-18 07:00","2018-09-19 18:00","연속",null,null,null,201807090181,{"$f":"IF(ISERROR(VLOOKUP(D196,#REF!,13,0)),\"-\",VLOOKUP(D196,#REF!,13,0))","v":"-"}]
[190,"경기","평택","오산평택#2 T/L","154kV 오산-향남T/L OPGW 증설공사","* No.16(C/H) ~ 오산S/S C/H OP-S-L48 교체 1.62km * 향남S/S G/T ~ 오산S/S C/H OP-S-L48 증설 5.75km * 오산S/S C/H ~ ICT실 FOFC-S-48 교체 0.206km 및 시설 0.206km * 향남S/S ICT실 ~ G/T FOFC-S-48 시설 0.048km * No.15(C/H) ~","2018-09-10 07:00","2018-09-17 18:00","2018-09-10 07:00","2018-09-17 18:00","연속",null,null,null,201807090180,{"$f":"IF(ISERROR(VLOOKUP(D197,#REF!,13,0)),\"-\",VLOOKUP(D197,#REF!,13,0))","v":"-"}]
["추가","경기","동부","곤지암율현#1T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 #66BUS 무부하가압용 주변압기","2018-09-29 16:00","2018-09-30 16:00","2018-09-29 16:00","2018-09-30 16:00","연속",{"$nulls":4},{"$f":"IF(ISERROR(VLOOKUP(D198,#REF!,13,0)),\"-\",VLOOKUP(D198,#REF!,13,0))","v":"-"}]
[191,"강원","강릉","간성인제#2 T/L","154kV 간성S/S #3M.Tr 증설공사","154/23kV 15/20MVA X 3대(1Bank ) 설치 170kV GIS 50kA 1250A 1CCT 설치 25.8kV GIS 25KA 2000A 4CCT 설치 0 증설 170kV GIS 모선 건전성 확인 전원","2018-09-10 18:00","2018-09-11 18:00","취소","취소","연속",null,null,null,201807090003,{"$f":"IF(ISERROR(VLOOKUP(D199,#REF!,13,0)),\"-\",VLOOKUP(D199,#REF!,13,0))","v":"-"}]
[192,"강원","강릉","간성인제#1 T/L","154kV 간성S/S #3M.Tr 증설공사","154/23kV 15/20MVA x3대(1Bank) 설치 170kV GIS 50kA 1250A x 1CCT 설치 25.8kV GIS 25kA 2000A X 4CCT 설치 0 170kV GIS 1CCT(모선 포함) 건전성 확인 전원","2018-09-19 18:00","2018-09-20 18:00","취소","취소","연속",null,null,null,201807090009,{"$f":"IF(ISERROR(VLOOKUP(D200,#REF!,13,0)),\"-\",VLOOKUP(D200,#REF!,13,0))","v":"-"}]
[193,"강원","강릉","영동TP강릉 T/L","2018~19년도 송전정비 협력회사 총액공사","○ 국산애자교체 - 154kV 강릉T/L No.14","2018-09-06 12:00","2018-09-08 18:00","2018-09-27 12:00","2018-09-29 18:00","매일",null,null,null,201807090391,{"$f":"IF(ISERROR(VLOOKUP(D201,#REF!,13,0)),\"-\",VLOOKUP(D201,#REF!,13,0))","v":"-"}]
[194,"강원","강릉","동해강릉 T/L","2018~19년도 송전정비 협력회사 총액공사","○ 국산애자교체 - 154kV 동해분기T/L No.2, 17, 46, 53-1 - 154kV 강릉T/L No.12-1","2018-09-03 07:00","2018-09-03 18:00","2018-09-02 07:00","2018-09-02 18:00","당일",null,null,null,201807090382,{"$f":"IF(ISERROR(VLOOKUP(D202,#REF!,13,0)),\"-\",VLOOKUP(D202,#REF!,13,0))","v":"-"}]
[195,"강원","강릉","강릉(SA)-횡계#1TL T/L","2018~19년도 송전정비 협력회사 총액공사","○ 국산애자교체 - 154kV 강릉수력#1T/L No.9, 10","2018-09-10 07:00","2018-09-10 18:00","2018-09-10 07:00","2018-09-12 18:00","당일",null,null,null,201807090396,{"$f":"IF(ISERROR(VLOOKUP(D203,#REF!,13,0)),\"-\",VLOOKUP(D203,#REF!,13,0))","v":"-"}]
[196,"강원","강릉","강릉(SA)횡계#2 T/L","2018~19년도 송전정비 협력회사 총액공사","○ 국산애자교체 - 154kV 강릉수력#2T/L No.9, 10, 33","2018-09-11 07:00","2018-09-11 18:00","2018-09-13 07:00","2018-09-15 18:00","당일",null,null,null,201807090398,{"$f":"IF(ISERROR(VLOOKUP(D204,#REF!,13,0)),\"-\",VLOOKUP(D204,#REF!,13,0))","v":"-"}]
[197,"강원","강릉","동해영동TP T/L","2018~19년도 송전정비 협력회사 총액공사","○ 국산애자교체 - 154kV 동해분기T/L No.16, 17, 32, 34, 36, 38, 46, 53, 53-1 - 154kV 강릉T/L ST, No.1, 7-1","2018-09-04 07:00","2018-09-06 12:00","2018-09-04 07:00","2018-09-06 12:00","매일",null,null,null,201807090389,{"$f":"IF(ISERROR(VLOOKUP(D205,#REF!,13,0)),\"-\",VLOOKUP(D205,#REF!,13,0))","v":"-"}]
[198,"강원","동해","도계태백 T/L","2018~19년도 동해전력지사 송전정비협력회사 총액공사","154kV 도계-태백T/L No.1 피뢰기설치공사","2018-09-05 08:00","2018-09-05 18:00","2018-09-05 08:00","2018-09-05 18:00","당일",null,null,null,201807100064,{"$f":"IF(ISERROR(VLOOKUP(D206,#REF!,13,0)),\"-\",VLOOKUP(D206,#REF!,13,0))","v":"-"}]
[199,"강원","동해","동해이원#2 T/L","2018~19년도 동해전력지사 송전정비협력회사 총액공사","154kV 동해-이원#2T/L No.1~5 피뢰기설치공사","2018-09-04 08:00","2018-09-04 18:00","2018-09-04 08:00","2018-09-04 18:00","당일",null,null,null,201807100062,{"$f":"IF(ISERROR(VLOOKUP(D207,#REF!,13,0)),\"-\",VLOOKUP(D207,#REF!,13,0))","v":"-"}]
[200,"강원","동해","울진삼척GP#2 T/L","(주)세니온 154kV 송전선로 보호반(IED 포함) 성능개선 시행","보호배전반 성능개선, 정정확인, 연동시험, 실부하가압","2018-09-14 10:00","2018-09-14 18:00","2018-09-14 10:00","2018-09-14 18:00","당일",null,null,null,201807090026,{"$f":"IF(ISERROR(VLOOKUP(D208,#REF!,13,0)),\"-\",VLOOKUP(D208,#REF!,13,0))","v":"-"}]
[201,"강원","동해","울진삼척GP#1 T/L","(주)세니온 154kV 송전선로 보호반(IED 포함) 성능개선 시행","보호배전반 성능개선, 정정확인, 연동시험, 실부하가압","2018-09-13 10:00","2018-09-13 18:00","2018-09-13 10:00","2018-09-13 18:00","당일",null,null,null,201807090025,{"$f":"IF(ISERROR(VLOOKUP(D209,#REF!,13,0)),\"-\",VLOOKUP(D209,#REF!,13,0))","v":"-"}]
[202,"강원","동해","동해정선 T/L","2018년 동해전력지사 변전협력회사 총액공사","○ 붓싱 인출 케이블 교체","2018-09-03 10:00","2018-09-03 18:00","2018-09-03 10:00","2018-09-03 18:00","당일",null,null,null,201807110002,{"$f":"IF(ISERROR(VLOOKUP(D210,#REF!,13,0)),\"-\",VLOOKUP(D210,#REF!,13,0))","v":"-"}]
[203,"강원","원주","홍천상남#1 T/L","2018년 원주전력 변전협력회사 총액공사","상남S/S 피뢰기 보통, GIS 절연볼트 교체","2018-09-05 10:00","2018-09-05 18:00","2018-09-05 10:00","2018-09-05 18:00","당일",null,null,null,201807060092,{"$f":"IF(ISERROR(VLOOKUP(D211,#REF!,13,0)),\"-\",VLOOKUP(D211,#REF!,13,0))","v":"-"}]
[204,"강원","원주","홍천상남#2 T/L","2018년 원주전력 변전협력회사 총액공사","상남S/S 피뢰기 보통, GIS 절연볼트 교체","2018-09-06 10:00","2018-09-06 18:00","2018-09-06 10:00","2018-09-06 18:00","당일",null,null,null,201807060093,{"$f":"IF(ISERROR(VLOOKUP(D212,#REF!,13,0)),\"-\",VLOOKUP(D212,#REF!,13,0))","v":"-"}]
[205,"강원","원주","남원주원주#1 T/L","154kV 원주변전소 디지털화 공사","1. 피뢰기 이설 2. OPGW 인출변경","2018-09-03 09:00","2018-09-03 18:00","2018-09-01 09:00","2018-09-01 18:00","당일",null,null,null,201807040107,{"$f":"IF(ISERROR(VLOOKUP(D213,#REF!,13,0)),\"-\",VLOOKUP(D213,#REF!,13,0))","v":"-"}]
[206,"강원","원주","남원주원주#2 T/L","154kV 원주변전소 디지털화 공사","1. 피뢰기 이설 2. OPGW 인출변경","2018-09-04 09:00","2018-09-04 18:00","2018-09-02 09:00","2018-09-02 18:00","당일",null,null,null,201807040108,{"$f":"IF(ISERROR(VLOOKUP(D214,#REF!,13,0)),\"-\",VLOOKUP(D214,#REF!,13,0))","v":"-"}]
[207,"강원","원주","횡성홍천#2 T/L","2018년도 남원주 등 7개 변전소 내진보강공사","횡성변전소 배면부 드라이비트 철거 후 섬유보강공사","2018-09-11 08:00","2018-09-20 18:00","2018-09-11 08:00","2018-09-20 18:00","매일",null,null,null,201807160141,{"$f":"IF(ISERROR(VLOOKUP(D215,#REF!,13,0)),\"-\",VLOOKUP(D215,#REF!,13,0))","v":"-"}]
[208,"강원","원주","횡성홍천#1 T/L","2018년도 남원주 등 7개 변전소 내진보강공사","횡성변전소 배면부 드라이비트 철거 후 섬유 붙임","2018-09-01 08:00","2018-09-10 18:00","2018-09-01 08:00","2018-09-10 18:00","매일",null,null,null,201807160140,{"$f":"IF(ISERROR(VLOOKUP(D216,#REF!,13,0)),\"-\",VLOOKUP(D216,#REF!,13,0))","v":"-"}]
[209,"강원","원주","북원주횡성#2 T/L","2018년도 남원주 등 7개 변전소 내진보강공사","횡성변전소 배면부 드라이비트 철거 후 섬유보강공사","2018-09-21 08:00","2018-09-30 18:00","2018-09-22 08:00","2018-09-30 18:00","매일",null,null,null,201807160142,{"$f":"IF(ISERROR(VLOOKUP(D217,#REF!,13,0)),\"-\",VLOOKUP(D217,#REF!,13,0))","v":"-"}]
[210,"강원","직할","홍천남춘천 T/L","2018~2019년도 직할 변전정비 총액공사","○ 장기사용 기타노후설비 대체공사 : 홍천-남춘천/L LA A,B,C 교체","2018-09-13 10:00","2018-09-13 18:00","2018-09-13 10:00","2018-09-13 18:00","당일",null,null,null,201807030054,{"$f":"IF(ISERROR(VLOOKUP(D218,#REF!,13,0)),\"-\",VLOOKUP(D218,#REF!,13,0))","v":"-"}]
[211,"강원","직할","청평HP의암HP T/L","154kV 청평HP의암HPT/L 안전이격 확보공사","철탑철거5 / 철탑신설 4기 철타교체 및 전력선, 가공지선교체, 항공표시구 설치 등","2018-09-14 07:00","2018-09-20 18:00","2018-09-14 07:00","2018-09-20 18:00","연속",null,null,null,201807090322,{"$f":"IF(ISERROR(VLOOKUP(D219,#REF!,13,0)),\"-\",VLOOKUP(D219,#REF!,13,0))","v":"-"}]
[212,"강원","직할","청평HP의암HP T/L","154kV 청평HP의암HPT/L 안전이격 확보공사","철탑철거5 / 철탑신설 4기 가선로 구성","2018-09-04 09:00","2018-09-05 18:00","2018-09-04 09:00","2018-09-05 18:00","연속",null,null,null,201807090320,{"$f":"IF(ISERROR(VLOOKUP(D220,#REF!,13,0)),\"-\",VLOOKUP(D220,#REF!,13,0))","v":"-"}]
[213,"강원","직할","상남인제#1 T/L","2018년 가공송전선로 순시점검 위탁공사","정밀점검","2018-09-10 09:00","2018-09-18 18:00","2018-09-10 09:00","2018-09-18 18:00","매일",null,null,null,201807090253,{"$f":"IF(ISERROR(VLOOKUP(D221,#REF!,13,0)),\"-\",VLOOKUP(D221,#REF!,13,0))","v":"-"}]
[214,"강원","직할","춘천북춘천#1 T/L","송전선로용 피뢰기 설치공사","송전선로용 피뢰기 설치 16기","2018-09-07 07:00","2018-09-08 18:00","취소","취소","매일",null,null,null,201807090249,{"$f":"IF(ISERROR(VLOOKUP(D222,#REF!,13,0)),\"-\",VLOOKUP(D222,#REF!,13,0))","v":"-"}]
[215,"강원","직할","가평화천HP T/L","2018년~2019년 강원지역본부 직할 변전정비 총액공사","화천H/P 154kV 가평-화천H/P T/L 보통점검 - GCB, LA, DS, PT, PNL","2018-09-06 10:00","2018-09-07 18:00","2018-09-06 10:00","2018-09-07 18:00","연속",null,null,null,201807090168,{"$f":"IF(ISERROR(VLOOKUP(D223,#REF!,13,0)),\"-\",VLOOKUP(D223,#REF!,13,0))","v":"-"}]
[216,"강원","태백","동해동영월 T/L","154kV 영월화력T/L 안전이격확보 공사","154kV 영월화력T/L 안전이격확보 공사","2018-09-03 08:00","2018-09-09 18:00","2018-09-14 08:00","2018-09-22 18:00","연속",null,null,null,201807090274,{"$f":"IF(ISERROR(VLOOKUP(D224,#REF!,13,0)),\"-\",VLOOKUP(D224,#REF!,13,0))","v":"-"}]
[217,"강원","태백","정선영월CC T/L","154kV 영월화력T/L 안전이격확보 공사","154kV 영월화력T/L 안전이격확보 공사","2018-09-10 08:00","2018-09-16 18:00","2018-09-04 10:00","2018-09-13 18:00","연속",null,null,null,201807090283,{"$f":"IF(ISERROR(VLOOKUP(D225,#REF!,13,0)),\"-\",VLOOKUP(D225,#REF!,13,0))","v":"-"}]
[218,"충북","직할","제천영월#2 T/L","154kV 제천-영월T/L No.52 취약철탑 교체공사","전력연구원 안정성 검토결과에 따른 취약철탑 교체공사","2018-09-01 08:00","2018-09-02 12:00","2018-09-01 08:00","2018-09-02 12:00","연속",null,null,null,201807230032,{"$f":"IF(ISERROR(VLOOKUP(D226,#REF!,13,0)),\"-\",VLOOKUP(D226,#REF!,13,0))","v":"-"}]
[219,"충북","직할","제천영월#1 T/L","154kV 제천-영월T/L No.52 취약철탑 교체공사","전력연구원 안정성 검토결과에 따른 취약철탑 교체공사","2018-09-02 13:00","2018-09-08 18:00","2018-09-02 13:00","2018-09-08 18:00","연속",null,null,null,201807090185,{"$f":"IF(ISERROR(VLOOKUP(D227,#REF!,13,0)),\"-\",VLOOKUP(D227,#REF!,13,0))","v":"-"}]
[220,"충북","청주","오송북청주#1 T/L","2018년 청주 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 오송-북청주#1T/L No.20~48 정밀점검 - 9/3 ~ 9/5 (매일)","2018-09-03 09:00","2018-09-05 18:00","취소","취소","매일",null,null,null,201807130128,{"$f":"IF(ISERROR(VLOOKUP(D228,#REF!,13,0)),\"-\",VLOOKUP(D228,#REF!,13,0))","v":"-"}]
[222,"충북","직할","제천영월#2 T/L","154kV 제천-영월T/L No.52 취약철탑 교체공사","전력연구원 안정성 검토결과에 따른 취약철탑 교체공사","2018-09-09 08:00","2018-09-10 18:00","2018-09-09 08:00","2018-09-10 18:00","연속",null,null,null,201807090184,{"$f":"IF(ISERROR(VLOOKUP(D229,#REF!,13,0)),\"-\",VLOOKUP(D229,#REF!,13,0))","v":"-"}]
[223,"충북","청주","부강대청HP T/L","2018년 청주전력지사 170kV GIS 정밀점검공사","부강-대청HP T/L GIS 정밀점검","2018-09-10 09:00","2018-09-11 18:00","2018-09-10 09:00","2018-09-11 18:00","연속",null,null,null,201807130073,{"$f":"IF(ISERROR(VLOOKUP(D230,#REF!,13,0)),\"-\",VLOOKUP(D230,#REF!,13,0))","v":"-"}]
[224,"충북","청주","오송북청주#2 T/L","2018년 청주 가공송전선로 순시점검 위탁공사(정밀점검)","154kV오송-북청주#2T/L No.20~48 정밀점검 - 9/10 ~ 9/12 (매일)","2018-09-10 09:00","2018-09-12 18:00","취소","취소","매일",null,null,null,201807130146,{"$f":"IF(ISERROR(VLOOKUP(D231,#REF!,13,0)),\"-\",VLOOKUP(D231,#REF!,13,0))","v":"-"}]
[225,"충북","충주","진천만승#2 T/L","만승S/S 170kV 장기사용 GIS 대체공사","170kV T/L GIS * 3CCT 170kV T/R GIS * 1CCT 170kV BUS PT&ES GIS * 1CCT","2018-09-10 14:00","2018-09-11 18:00","2018-09-10 14:00","2018-09-11 18:00","연속",null,null,null,201807170159,{"$f":"IF(ISERROR(VLOOKUP(D232,#REF!,13,0)),\"-\",VLOOKUP(D232,#REF!,13,0))","v":"-"}]
[226,"충북","직할","제천영월#2 T/L","2018년 가공송전선로 순시점검 위탁공사","154kV 신제천-영월CCT/L 점밀점검 안전조치","2018-09-15 08:00","2018-09-15 18:00","취소","취소","당일",null,null,null,201807170100,{"$f":"IF(ISERROR(VLOOKUP(D233,#REF!,13,0)),\"-\",VLOOKUP(D233,#REF!,13,0))","v":"-"}]
[227,"충북","청주","서청주사직#2 T/L","2018년 청주전력지사 170kV GIS 정밀점검공사","서청주-사직#2T/L GIS 정밀점검","2018-09-15 09:00","2018-09-16 18:00","취소","취소","연속",null,null,null,201807130071,{"$f":"IF(ISERROR(VLOOKUP(D234,#REF!,13,0)),\"-\",VLOOKUP(D234,#REF!,13,0))","v":"-"}]
[228,"충북","충주","진천만승#2 T/L","만승S/S 170kV 장기사용 GIS 대체공사","170kV T/L GIS * 3CCT 170kV T/R GIS * 1CCT 170kV BUS PT&ES GIS * 1CCT","2018-09-17 08:00","2018-09-20 18:00","2018-09-17 08:00","2018-09-20 18:00","연속",null,null,null,201807170160,{"$f":"IF(ISERROR(VLOOKUP(D235,#REF!,13,0)),\"-\",VLOOKUP(D235,#REF!,13,0))","v":"-"}]
[229,"충북","직할","점촌단양 T/L","단양S/S 154kV 점촌단양T/L PT 대체","단양S/S 154kV 점촌단양T/L PT 대체","2018-09-17 10:00","2018-09-17 18:00","2018-09-17 10:00","2018-09-17 18:00","매일",null,null,null,201807120009,{"$f":"IF(ISERROR(VLOOKUP(D236,#REF!,13,0)),\"-\",VLOOKUP(D236,#REF!,13,0))","v":"-"}]
[230,"충북","직할","신제천남원주#2 T/L","신제천S/S 신제천남원주#2T/L GIS 초기점검","- 170kV GIS 초기점검","2018-09-18 13:00","2018-09-18 18:00","취소","취소","당일",null,null,null,201806200122,{"$f":"IF(ISERROR(VLOOKUP(D237,#REF!,13,0)),\"-\",VLOOKUP(D237,#REF!,13,0))","v":"-"}]
[231,"충북","직할","신제천주진#1 T/L","신제천S/S 신제천주진#1T/L GIS 및 LA 점검","- 170kV GIS 초기점검 - 170kV LA 보통점검","2018-09-19 09:00","2018-09-19 18:00","2018-09-19 09:00","2018-09-19 18:00","당일",null,null,null,201806200120,{"$f":"IF(ISERROR(VLOOKUP(D238,#REF!,13,0)),\"-\",VLOOKUP(D238,#REF!,13,0))","v":"-"}]
[232,"충북","직할","제천영월#1 T/L","2018년 가공송전선로 순시점검 위탁공사","154kV 신제천-영월CCT/L 점밀점검 안전조치","2018-09-22 08:00","2018-09-22 18:00","2018-09-22 08:00","2018-09-22 18:00","당일",null,null,null,201807170101,{"$f":"IF(ISERROR(VLOOKUP(D239,#REF!,13,0)),\"-\",VLOOKUP(D239,#REF!,13,0))","v":"-"}]
[233,"충북","충주","서운만승 T/L","154kV 서운-만승 등 2개T/L 전력선교체공사","154kV 서운-만승T/L No.81~83 전력선교체(중하단4선)","2018-09-28 07:00","2018-10-01 18:00","2018-09-28 07:00","2018-10-01 18:00","연속",null,null,null,201807170125,{"$f":"IF(ISERROR(VLOOKUP(D240,#REF!,13,0)),\"-\",VLOOKUP(D240,#REF!,13,0))","v":"-"}]
[234,"충북","충주","진천만승#1 T/L","154kV 서운-만승 등 2개T/L 전력선교체공사","154kV 진천-만승#1T/L No.35~37 전력선교체(상하단 4선)","2018-09-28 07:00","2018-10-01 18:00","2018-09-28 07:00","2018-10-01 18:00","연속",null,null,null,201807170126,{"$f":"IF(ISERROR(VLOOKUP(D241,#REF!,13,0)),\"-\",VLOOKUP(D241,#REF!,13,0))","v":"-"}]
[235,"충북","청주","신진천오창#1 T/L","2018년 청주전력지사 170kV GIS 정밀점검공사","신진천오창#1T/L GIS 정밀점검","2018-09-29 09:00","2018-09-30 18:00","취소","취소","연속",null,null,null,201807130070,{"$f":"IF(ISERROR(VLOOKUP(D242,#REF!,13,0)),\"-\",VLOOKUP(D242,#REF!,13,0))","v":"-"}]
["추가","충북","직할","신제천영월CC#1 T/L"," 2018년 가공송전선로 순시점검 위탁공사","- 정밀점검 : No.1~78","2018-09-11 08:00","2018-09-16 18:00","2018-09-11 08:00","2018-09-16 18:00","매일",{"$nulls":4},"-"]
["추가","충북","직할","신제천영월CC#2 T/L"," 2018년 가공송전선로 순시점검 위탁공사","- 정밀점검 : No.1~78","2018-09-17 08:00","2018-09-22 18:00","2018-09-17 08:00","2018-09-22 18:00","매일",{"$nulls":4},"-"]
[236,"대전충남","대전","논산은진#2 T/L","은진S/S 논산은진#2T/L 모선GIB화, 1차 GIS이설 및 병행작업","은진S/S 논산은진#2T/L 모선GIB화, 1차 GIS이설 및 병행작업 -병행작업(송전선로 인출변경, 리드선연장(철탑이설))","2018-09-04 09:00","2018-09-20 18:00","2018-09-04 09:00","2018-09-20 18:00","연속",null,null,null,201807020042,{"$f":"IF(ISERROR(VLOOKUP(D245,#REF!,13,0)),\"-\",VLOOKUP(D245,#REF!,13,0))","v":"-"}]
[237,"대전충남","대전","논산은진#1 T/L","은진S/S 논산은진#1T/L 모선GIB화, 1차 GIS이설 및 병행작업","은진S/S 논산은진#1T/L 모선GIB화, 1차 GIS이설 및 병행작업 -병행작업(인출방향개조, 지지애자 및 가공모선 철거)","2018-09-15 09:00","2018-10-02 18:00","2018-09-15 09:00","2018-10-02 18:00","연속",null,null,null,201807020043,{"$f":"IF(ISERROR(VLOOKUP(D246,#REF!,13,0)),\"-\",VLOOKUP(D246,#REF!,13,0))","v":"-"}]
[238,"대전충남","서산","신당진당진#2 T/L","서산PO 154kV GIS 정밀점검 공사","서산PO 154kV GIS 정밀점검 공사 당진 GCB 보통점검","2018-09-29 09:00","2018-09-30 18:00","취소","취소","연속",null,null,null,201807100163,{"$f":"IF(ISERROR(VLOOKUP(D247,#REF!,13,0)),\"-\",VLOOKUP(D247,#REF!,13,0))","v":"-"}]
[239,"대전충남","세종","천안전의#2 T/L","[송전] 154kV 천안-전의T/L 안전거리 확보공사","[송전] 철탑교체 : 3기(No.30,32,35), 전선교체 : 2.141km(No.29~36)","2018-09-03 07:00","2018-09-09 18:00","취소","취소","연속",null,null,null,201807120156,{"$f":"IF(ISERROR(VLOOKUP(D248,#REF!,13,0)),\"-\",VLOOKUP(D248,#REF!,13,0))","v":"-"}]
[240,"대전충남","세종","천안전의#1 T/L","[송전] 154kV 천안-전의T/L 안전거리 확보공사","[송전] 철탑교체 : 3기(No.30,32,35), 전선교체 : 2.141km(No.29~36)","2018-09-10 07:00","2018-10-21 18:00","취소","취소","연속",null,null,null,201807120158,{"$f":"IF(ISERROR(VLOOKUP(D249,#REF!,13,0)),\"-\",VLOOKUP(D249,#REF!,13,0))","v":"-"}]
[241,"대전충남","세종","조치원월산 T/L","[변전] '18년 세종P/O 170kV GIS 정밀점검공사","○ GIS 정밀점검(모선DS포함)","2018-09-10 09:00","2018-09-11 18:00","취소","취소","연속",null,null,null,201807120169,{"$f":"IF(ISERROR(VLOOKUP(D250,#REF!,13,0)),\"-\",VLOOKUP(D250,#REF!,13,0))","v":"-"}]
[242,"대전충남","세종","조치원전의#1 T/L","[변전] '18년 세종P/O 170kV GIS 정밀점검공사","○ GIS 정밀점검(모선DS포함)","2018-09-12 09:00","2018-09-13 18:00","2018-09-12 09:00","2018-09-13 18:00","연속",null,null,null,201807120167,{"$f":"IF(ISERROR(VLOOKUP(D251,#REF!,13,0)),\"-\",VLOOKUP(D251,#REF!,13,0))","v":"-"}]
[243,"대전충남","세종","조치원전의#2 T/L","[변전] '18년 세종P/O 170kV GIS 정밀점검공사","○ GIS 정밀점검(모선DS포함)","2018-09-17 09:00","2018-09-18 18:00","2018-10-04 09:00","2018-10-05 18:00","연속",null,null,null,201807120168,{"$f":"IF(ISERROR(VLOOKUP(D252,#REF!,13,0)),\"-\",VLOOKUP(D252,#REF!,13,0))","v":"-"}]
[244,"대전충남","아산","신온양한샘#2 T/L","154kV 신온양-한샘T/L 건설공사","신설 선로 가압을 위한 전력선 공사(긴선, 기설 전선 철거, 점펴선 연결 등)","2018-09-30 07:00","2018-10-02 19:00","2018-09-30 07:00","2018-10-02 19:00","연속",null,null,null,201807060116,{"$f":"IF(ISERROR(VLOOKUP(D253,#REF!,13,0)),\"-\",VLOOKUP(D253,#REF!,13,0))","v":"-"}]
[245,"대전충남","아산","신온양한샘#1 T/L","154kV 신온양-한샘T/L 건설공사","신설 선로 가압을 위한 전력선 공사(긴선, 기설 전선 철거, 점펴선 연결 등)","2018-09-01 07:00","2018-09-02 19:00","2018-09-01 07:00","2018-09-02 19:00","연속",null,null,null,201807060121,{"$f":"IF(ISERROR(VLOOKUP(D254,#REF!,13,0)),\"-\",VLOOKUP(D254,#REF!,13,0))","v":"-"}]
[246,"대전충남","아산","한샘둔포#1 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기설치공사","154kV 한샘-둔포 #1T/L 피뢰기설치공사(24기분)","2018-09-10 07:00","2018-09-14 18:00","2018-09-10 07:00","2018-09-14 18:00","매일",null,null,null,201807060091,{"$f":"IF(ISERROR(VLOOKUP(D255,#REF!,13,0)),\"-\",VLOOKUP(D255,#REF!,13,0))","v":"-"}]
[247,"대전충남","청양","관창보령복합 T/L","154kV 보관T/L 현수애자련 보강공사","[송전] 애자련보강 및 이도조정 - 애자련보강 : No.4, 5호(1점지지 - 2점지지) - 이도조정 : No.4 ~ 5호","2018-09-05 07:00","2018-09-06 18:00","2018-09-05 07:00","2018-09-06 18:00","연속",null,null,null,201807240048,{"$f":"IF(ISERROR(VLOOKUP(D256,#REF!,13,0)),\"-\",VLOOKUP(D256,#REF!,13,0))","v":"-"}]
[248,"대전충남","청양","관창보령화력 T/L","154kV 보관T/L 현수애자련 보강공사","[송전] 애자련보강 및 이도조정 - 애자련보강 : No.4, 5호(1점지지 - 2점지지) - 이도조정 : No.4 ~ 5호","2018-09-03 07:00","2018-09-04 18:00","2018-09-03 07:00","2018-09-04 18:00","연속",null,null,null,201807240047,{"$f":"IF(ISERROR(VLOOKUP(D257,#REF!,13,0)),\"-\",VLOOKUP(D257,#REF!,13,0))","v":"-"}]
[249,"전북","군산","동군산군산CC#2 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군산CC 154kV 동군산-군산복합 #2T/L 차단기 정밀점검","2018-09-15 09:00","2018-09-16 18:00","2018-09-15 09:00","2018-09-16 18:00","연속",null,null,null,201807190014,{"$f":"IF(ISERROR(VLOOKUP(D258,#REF!,13,0)),\"-\",VLOOKUP(D258,#REF!,13,0))","v":"-"}]
[250,"전북","군산","군산동군산#2 T/L","항공장애표시구 설치공사","항공자애표시구 설치","2018-09-03 07:00","2018-09-03 18:00","2018-09-03 07:00","2018-09-03 18:00","당일",null,null,null,201805300261,{"$f":"IF(ISERROR(VLOOKUP(D259,#REF!,13,0)),\"-\",VLOOKUP(D259,#REF!,13,0))","v":"-"}]
[251,"전북","군산","군산영등#1 T/L","항공장애표시구 설치공사","항공자애표시구 설치","2018-09-04 07:00","2018-09-04 18:00","2018-09-04 07:00","2018-09-04 18:00","당일",null,null,null,201805300263,{"$f":"IF(ISERROR(VLOOKUP(D260,#REF!,13,0)),\"-\",VLOOKUP(D260,#REF!,13,0))","v":"-"}]
[252,"전북","군산","군산이리#1 T/L","항공장애표시구 설치공사","항공자애표시구 설치 안전이격거리확보","2018-09-04 07:00","2018-09-04 18:00","2018-09-04 07:00","2018-09-04 18:00","당일",null,null,null,201805300262,{"$f":"IF(ISERROR(VLOOKUP(D261,#REF!,13,0)),\"-\",VLOOKUP(D261,#REF!,13,0))","v":"-"}]
[253,"전북","군산","군산이리#2 T/L","항공장애표시구 설치공사","항공자애표시구 설치 안전이격거리확보","2018-09-06 07:00","2018-09-06 18:00","2018-09-06 07:00","2018-09-06 18:00","당일",null,null,null,201807110143,{"$f":"IF(ISERROR(VLOOKUP(D262,#REF!,13,0)),\"-\",VLOOKUP(D262,#REF!,13,0))","v":"-"}]
[254,"전북","군산","군산영등#2 T/L","항공장애표시구 설치공사","항공자애표시구 설치","2018-09-06 07:00","2018-09-06 18:00","2018-09-06 07:00","2018-09-06 18:00","당일",null,null,null,201807110145,{"$f":"IF(ISERROR(VLOOKUP(D263,#REF!,13,0)),\"-\",VLOOKUP(D263,#REF!,13,0))","v":"-"}]
[255,"전북","군산","군산S/S 154kV #67 BUS","2018년 군산P/O 154kV 차단기 정밀점검","- 군산S/S #3 M.Tr 2차 GIS 정밀점검공사","2018-09-14 14:00","2018-09-14 18:00","2018-09-14 14:00","2018-09-14 18:00","연속",null,null,null,201807190016,{"$f":"IF(ISERROR(VLOOKUP(D264,#REF!,13,0)),\"-\",VLOOKUP(D264,#REF!,13,0))","v":"-"}]
[256,"전북","군산","군산동군산#2 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군산S/S 345kV #3M.tr 2차 GIS 차단기 정밀점검","2018-09-14 14:00","2018-09-14 18:00","2018-09-14 14:00","2018-09-14 18:00","연속",null,null,null,201807190017,{"$f":"IF(ISERROR(VLOOKUP(D265,#REF!,13,0)),\"-\",VLOOKUP(D265,#REF!,13,0))","v":"-"}]
[257,"전북","군산","팔봉영등#2 T/L","군산PO 노후배전반 대체공사","팔봉-영등#2TL 보호배전반 대체","2018-09-10 09:00","2018-09-14 18:00","취소","취소","연속",null,null,null,201807040095,{"$f":"IF(ISERROR(VLOOKUP(D266,#REF!,13,0)),\"-\",VLOOKUP(D266,#REF!,13,0))","v":"-"}]
[258,"전북","군산","팔봉봉동#1 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","팔봉S/S 팔봉-봉동#1T/L GIS 정밀점검","2018-09-07 07:00","2018-09-08 18:00","취소","취소","연속",null,null,null,201807190008,{"$f":"IF(ISERROR(VLOOKUP(D267,#REF!,13,0)),\"-\",VLOOKUP(D267,#REF!,13,0))","v":"-"}]
[259,"전북","군산","팔봉봉동#2 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","팔봉S/S 팔봉-봉동#2T/L GIS 정밀점검","2018-09-05 07:00","2018-09-06 18:00","취소","취소","연속",null,null,null,201807190009,{"$f":"IF(ISERROR(VLOOKUP(D268,#REF!,13,0)),\"-\",VLOOKUP(D268,#REF!,13,0))","v":"-"}]
[260,"전북","군산","팔봉영등#1 T/L","군산PO 노후배전반 대체공사","팔봉-영등#1TL 보호배전반 대체","2018-09-17 09:00","2018-09-21 18:00","취소","취소","연속",null,null,null,201807040096,{"$f":"IF(ISERROR(VLOOKUP(D269,#REF!,13,0)),\"-\",VLOOKUP(D269,#REF!,13,0))","v":"-"}]
[261,"전북","김제","정주고창#1 T/L","154kV 정주-고창 안전이격확보공사","정주-고창#1T/L 철탑 이설 및 전력선 교체 철탑교체 : No.66,69,70,72호 전력선 교체 : No.65~74호","2018-09-03 07:00","2018-09-04 18:00","2018-09-03 07:00","2018-09-04 18:00","연속",null,null,null,201807030239,{"$f":"IF(ISERROR(VLOOKUP(D270,#REF!,13,0)),\"-\",VLOOKUP(D270,#REF!,13,0))","v":"-"}]
[262,"전북","김제","고창S/S 고창-홍농T/L GIS","김제P/O 2018년 170KV GIS 정밀점검공사","고창-홍농 T/L 차단기 정밀점공사","2018-09-06 09:00","2018-09-08 18:00","취소","취소","연속",null,null,null,201807110167,{"$f":"IF(ISERROR(VLOOKUP(D271,#REF!,13,0)),\"-\",VLOOKUP(D271,#REF!,13,0))","v":"-"}]
[263,"전북","김제","고창S/S 고창-영광T/L GIS","김제P/O 2018년 170KV GIS 정밀점검공사","고창-영광 T/L 차단기 정밀점공사","2018-09-03 09:00","2018-09-05 18:00","취소","취소","연속",null,null,null,201807110166,{"$f":"IF(ISERROR(VLOOKUP(D272,#REF!,13,0)),\"-\",VLOOKUP(D272,#REF!,13,0))","v":"-"}]
[264,"전북","김제","정주고창#1 T/L","154kV 정주-고창 안전이격확보공사","정주-고창#1T/L 철탑 이설 및 전력선 교체 철탑교체 : No.66,69,70,72호 전력선 교체 : No.65~74호","2018-09-10 07:00","2018-09-14 18:00","2018-09-10 07:00","2018-09-14 18:00","연속",null,null,null,201807030241,{"$f":"IF(ISERROR(VLOOKUP(D273,#REF!,13,0)),\"-\",VLOOKUP(D273,#REF!,13,0))","v":"-"}]
[265,"전북","김제","정주고창#2 T/L","154kV 정주-고창 안전이격확보공사","정주-고창#1T/L 철탑 이설 및 전력선 교체 철탑교체 : No.66,69,70,72호 전력선 교체 : No.65~74호","2018-09-05 07:00","2018-09-09 18:00","2018-09-05 07:00","2018-09-09 18:00","연속",null,null,null,201807030240,{"$f":"IF(ISERROR(VLOOKUP(D274,#REF!,13,0)),\"-\",VLOOKUP(D274,#REF!,13,0))","v":"-"}]
[266,"전북","김제","김제섬진강HP T/L","154kV 고창-홍농 등7개T/L 피뢰기 설치공사","154kV 김제-섬진강T/L 82기, 피뢰기 246Set 설치","2018-09-01 08:00","2018-09-14 18:00","2018-09-01 08:00","2018-09-14 18:00","매일",null,null,null,201806290058,{"$f":"IF(ISERROR(VLOOKUP(D275,#REF!,13,0)),\"-\",VLOOKUP(D275,#REF!,13,0))","v":"-"}]
[267,"전북","김제","신김제S/S 61-62-0 SEC CB","모선보호반 교체공사","모선보호반 교체공사","2018-09-17 09:00","2018-09-21 18:00","2018-09-17 09:00","2018-09-21 18:00","연속",null,null,null,201807160084,{"$f":"IF(ISERROR(VLOOKUP(D276,#REF!,13,0)),\"-\",VLOOKUP(D276,#REF!,13,0))","v":"-"}]
[268,"전북","김제","신김제정공#1 T/L","김제P/O 2018년 170KV GIS 정밀점검공사","154KV 신김제- 정공#1T/L 차단기 정밀점검","2018-09-13 09:00","2018-09-15 18:00","2018-09-13 09:00","2018-09-15 18:00","연속",null,null,null,201807110197,{"$f":"IF(ISERROR(VLOOKUP(D277,#REF!,13,0)),\"-\",VLOOKUP(D277,#REF!,13,0))","v":"-"}]
[269,"전북","김제","신김제남전주#1 T/L","154kV 고창-홍농 등7개T/L 피뢰기 설치공사","154kV 신김제-남전주#1T/L 5기, 피뢰기 15Set 설치","2018-09-27 08:00","2018-09-27 18:00","2018-09-27 08:00","2018-09-27 18:00","매일",null,null,null,201807020097,{"$f":"IF(ISERROR(VLOOKUP(D278,#REF!,13,0)),\"-\",VLOOKUP(D278,#REF!,13,0))","v":"-"}]
[270,"전북","김제","신김제S/S 154kV #3 BUS TIE CB","모선보호반 교체공사","모선보호반 교체공사","2018-09-17 09:00","2018-09-21 18:00","2018-09-17 09:00","2018-09-21 18:00","연속",null,null,null,201807160083,{"$f":"IF(ISERROR(VLOOKUP(D279,#REF!,13,0)),\"-\",VLOOKUP(D279,#REF!,13,0))","v":"-"}]
[271,"전북","김제","신김제S/S 66-67-0 SEC CB","모선보호반 교체공사","모선보호반 교체공사","2018-09-17 09:00","2018-09-21 18:00","2018-09-17 09:00","2018-09-21 18:00","연속",null,null,null,201807160085,{"$f":"IF(ISERROR(VLOOKUP(D280,#REF!,13,0)),\"-\",VLOOKUP(D280,#REF!,13,0))","v":"-"}]
[272,"전북","김제","신김제정공#1 T/L","154kV 고창-홍농 등7개T/L 피뢰기 설치공사","154kV 신김제-정공#1T/L 5기, 피뢰기 15Set 설치","2018-09-28 09:00","2018-09-28 18:00","2018-09-28 09:00","2018-09-28 18:00","매일",null,null,null,201807020099,{"$f":"IF(ISERROR(VLOOKUP(D281,#REF!,13,0)),\"-\",VLOOKUP(D281,#REF!,13,0))","v":"-"}]
[273,"전북","김제","정공S/S 154kV #1 BUS TIE GIS","김제P/O 2018년 170KV GIS 정밀점검공사","154KV BUS TIE 차단기 정밀점공사","2018-09-10 09:00","2018-09-12 18:00","2018-09-10 09:00","2018-09-12 18:00","연속",null,null,null,201807110181,{"$f":"IF(ISERROR(VLOOKUP(D282,#REF!,13,0)),\"-\",VLOOKUP(D282,#REF!,13,0))","v":"-"}]
[274,"전북","김제","정공섬진강수력 T/L","154kV 고창-홍농 등7개T/L 피뢰기 설치공사","154kV 정공-섬진강T/L 53기, 피뢰기 159Set 설치","2018-09-15 08:00","2018-09-23 18:00","2018-09-15 08:00","2018-09-23 18:00","매일",null,null,null,201806290059,{"$f":"IF(ISERROR(VLOOKUP(D283,#REF!,13,0)),\"-\",VLOOKUP(D283,#REF!,13,0))","v":"-"}]
[275,"전북","김제","신김제정공#1 T/L","김제P/O 2018년 170KV GIS 정밀점검공사","154KV BUS TIE 차단기 시험가압","2018-09-11 16:00","2018-09-11 18:00","2018-09-11 16:00","2018-09-11 18:00","연속",null,null,null,201807110186,{"$f":"IF(ISERROR(VLOOKUP(D284,#REF!,13,0)),\"-\",VLOOKUP(D284,#REF!,13,0))","v":"-"}]
[276,"전북","직할","북전주봉동#2 T/L","2018년 전북직할 154kV 차단기 정밀점검공사","- 차단부 정밀점검","2018-09-12 09:30","2018-09-13 17:00","취소","취소","연속",null,null,null,201807200079,{"$f":"IF(ISERROR(VLOOKUP(D285,#REF!,13,0)),\"-\",VLOOKUP(D285,#REF!,13,0))","v":"-"}]
[277,"전북","직할","북전주봉동#1 T/L","2018년 전북직할 154kV 차단기 정밀점검공사","- 차단부 정밀점검","2018-09-10 09:30","2018-09-11 17:00","취소","취소","연속",null,null,null,201807200078,{"$f":"IF(ISERROR(VLOOKUP(D286,#REF!,13,0)),\"-\",VLOOKUP(D286,#REF!,13,0))","v":"-"}]
[278,"전북","직할","북전주진안 T/L","북전주-진안T/L 보호배전반 대체공사","북전주-진안T/L 보호배전반 대체공사","2018-09-03 09:30","2018-09-07 18:00","2018-09-03 09:30","2018-09-07 18:00","연속",null,null,null,201807110098,{"$f":"IF(ISERROR(VLOOKUP(D287,#REF!,13,0)),\"-\",VLOOKUP(D287,#REF!,13,0))","v":"-"}]
[279,"전북","직할","북전주용담수력 T/L","북전주-용담수력T/L 보호배전반 대체공사","북전주-용담수력T/L 보호배전반 대체공사","2018-09-17 09:30","2018-09-21 18:00","2018-09-17 09:30","2018-09-21 18:00","연속",null,null,null,201807110100,{"$f":"IF(ISERROR(VLOOKUP(D288,#REF!,13,0)),\"-\",VLOOKUP(D288,#REF!,13,0))","v":"-"}]
[280,"전북","군산","군산서군산#1 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군산S/S 154kV 군산-서군산 #1T/L 차단기 정밀점검","2018-09-19 09:00","2018-09-20 18:00","2018-09-19 09:00","2018-09-20 18:00","연속",null,null,null,201803200122,{"$f":"IF(ISERROR(VLOOKUP(D289,#REF!,13,0)),\"-\",VLOOKUP(D289,#REF!,13,0))","v":"-"}]
[281,"전북","군산","군산서군산#2 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군산S/S 154kV 군산-서군산 #2T/L 차단기 정밀점검","2018-09-17 09:00","2018-09-18 18:00","2018-09-17 09:00","2018-09-18 18:00","연속",null,null,null,201803200123,{"$f":"IF(ISERROR(VLOOKUP(D290,#REF!,13,0)),\"-\",VLOOKUP(D290,#REF!,13,0))","v":"-"}]
[282,"전북","군산","군산동군산#2 T/L","2018년 군산P/O 170kV GIS 정밀점검공사","군산S/S 154kV 군산-동군산 #2T/L 차단기 정밀점검","2018-09-27 09:00","2018-09-28 18:00","2018-09-27 09:00","2018-09-28 18:00","연속",null,null,null,201803200121,{"$f":"IF(ISERROR(VLOOKUP(D291,#REF!,13,0)),\"-\",VLOOKUP(D291,#REF!,13,0))","v":"-"}]
[283,"전북","김제","백산김제#1 T/L","항공장애표시구 설치공사","항공장애표시구 설치","2018-09-01 08:00","2018-09-01 18:00","2018-09-01 08:00","2018-09-01 18:00","당일",null,null,null,201806190071,{"$f":"IF(ISERROR(VLOOKUP(D292,#REF!,13,0)),\"-\",VLOOKUP(D292,#REF!,13,0))","v":"-"}]
[284,"광주전남","강진","강진남창#2 T/L","남창S/S 154kV 강진-남창 #2T/L (인출 P.G클램프 교체)","2018~19년 강진전력지사 변전정비회사 총액공사 - 내용 : 남창S/S 강진-남창 #2T/L 인출 P.G클램프 교체","2018-09-19 09:00","2018-09-19 18:00","2018-09-19 09:00","2018-09-19 18:00","당일",null,null,null,201807100167,{"$f":"IF(ISERROR(VLOOKUP(D293,#REF!,13,0)),\"-\",VLOOKUP(D293,#REF!,13,0))","v":"-"}]
[285,"광주전남","강진","강진남창#1 T/L","남창S/S 154kV 강진-남창 #1T/L (DS 결상 예방작업)","2018~19년 강진전력지사 변전정비회사 총액공사 - 내용 : 남창S/S 강진-남창 #1T/L DS 결상 예방작업","2018-09-20 09:00","2018-09-20 18:00","2018-09-20 09:00","2018-09-20 18:00","당일",null,null,null,201807100166,{"$f":"IF(ISERROR(VLOOKUP(D294,#REF!,13,0)),\"-\",VLOOKUP(D294,#REF!,13,0))","v":"-"}]
[286,"광주전남","강진","화원진도#1 T/L","154kV 진도S/S #1M.Tr 용량변경공사","1. 154kV #1M.Tr 무부하가압","2018-09-14 09:00","2018-09-15 18:00","취소","취소","연속",null,null,null,201807060258,{"$f":"IF(ISERROR(VLOOKUP(D295,#REF!,13,0)),\"-\",VLOOKUP(D295,#REF!,13,0))","v":"-"}]
[287,"광주전남","강진","진도S/S 154kV #1 BUS","154kV 진도S/S #1M.Tr 용량변경공사","1. 154kV #1M.Tr 무부하가압","2018-09-14 09:00","2018-09-15 18:00","취소","취소","연속",null,null,null,201807060266,{"$f":"IF(ISERROR(VLOOKUP(D296,#REF!,13,0)),\"-\",VLOOKUP(D296,#REF!,13,0))","v":"-"}]
[288,"광주전남","강진","해남C/S #2 C.Tr 1차 CB(신규)","#1HVDC 노후변환설비 교체사업","밸브, 냉각설비, 제어기, 관련 제어케이블 교체 및 시운전 C.Tr, 필터, VBE 등 PNL 교체","2018-09-17 09:00","2019-02-28 18:00","취소","취소","연속",null,null,null,201807050240,{"$f":"IF(ISERROR(VLOOKUP(D297,#REF!,13,0)),\"-\",VLOOKUP(D297,#REF!,13,0))","v":"-"}]
[289,"광주전남","강진","해남C/S 154kV #2 DTF CB(신규)","#1HVDC 노후변환설비 교체사업","밸브, 냉각설비, 제어기, 관련 제어케이블 교체 및 시운전 C.Tr, 필터, VBE 등 PNL 교체","2018-09-17 09:00","2019-02-28 18:00","취소","취소","연속",null,null,null,201807050244,{"$f":"IF(ISERROR(VLOOKUP(D298,#REF!,13,0)),\"-\",VLOOKUP(D298,#REF!,13,0))","v":"-"}]
[290,"광주전남","강진","해남C/S 154kV #1 Sh.C CB","#1HVDC 노후변환설비 교체사업","밸브, 냉각설비, 제어기, 관련 제어케이블 교체 및 시운전 C.Tr, 필터, VBE 등 PNL 교체","2018-09-17 09:00","2019-02-28 18:00","취소","취소","연속",null,null,null,201807050243,{"$f":"IF(ISERROR(VLOOKUP(D299,#REF!,13,0)),\"-\",VLOOKUP(D299,#REF!,13,0))","v":"-"}]
[291,"광주전남","강진","해남C/S 154kV #2 HPF CB(신규)","#1HVDC 노후변환설비 교체사업","밸브, 냉각설비, 제어기, 관련 제어케이블 교체 및 시운전 C.Tr, 필터, VBE 등 PNL 교체","2018-09-17 09:00","2019-02-28 18:00","취소","취소","연속",null,null,null,201807050245,{"$f":"IF(ISERROR(VLOOKUP(D300,#REF!,13,0)),\"-\",VLOOKUP(D300,#REF!,13,0))","v":"-"}]
[292,"광주전남","강진","해남C/S 154kV #1 DTF CB","#1HVDC 노후변환설비 교체사업","밸브, 냉각설비, 제어기, 관련 제어케이블 교체 및 시운전 C.Tr, 필터, VBE 등 PNL 교체","2018-09-17 09:00","2019-02-28 18:00","취소","취소","연속",null,null,null,201807050241,{"$f":"IF(ISERROR(VLOOKUP(D301,#REF!,13,0)),\"-\",VLOOKUP(D301,#REF!,13,0))","v":"-"}]
[293,"광주전남","강진","해남C/S 154kV #1 BUS TIE GIS(신규)","해남C/S 154kV 6100 GIS (GIS 하자점검)","2018~19년 강진전력지사 변전정비회사 총액공사 - 내용 : GIS 하자점검","2018-09-17 09:00","2018-09-17 18:00","취소","취소","당일",null,null,null,201804300158,{"$f":"IF(ISERROR(VLOOKUP(D302,#REF!,13,0)),\"-\",VLOOKUP(D302,#REF!,13,0))","v":"-"}]
[294,"광주전남","강진","해남C/S 154kV #1 HPF CB","#1HVDC 노후변환설비 교체사업","밸브, 냉각설비, 제어기, 관련 제어케이블 교체 및 시운전 C.Tr, 필터, VBE 등 PNL 교체","2018-09-17 09:00","2019-02-28 18:00","취소","취소","연속",null,null,null,201807050242,{"$f":"IF(ISERROR(VLOOKUP(D303,#REF!,13,0)),\"-\",VLOOKUP(D303,#REF!,13,0))","v":"-"}]
[295,"광주전남","강진","해남C/S #1 C.Tr 1차 CB","#1HVDC 노후변환설비 교체사업","밸브, 냉각설비, 제어기, 관련 제어케이블 교체 및 시운전 C.Tr, 필터, VBE 등 PNL 교체","2018-09-17 09:00","2019-02-28 18:00","취소","취소","연속",null,null,null,201807050239,{"$f":"IF(ISERROR(VLOOKUP(D304,#REF!,13,0)),\"-\",VLOOKUP(D304,#REF!,13,0))","v":"-"}]
[296,"광주전남","강진","해남C/S 154kV #2 Sh.C CB(신규)","#1HVDC 노후변환설비 교체사업","밸브, 냉각설비, 제어기, 관련 제어케이블 교체 및 시운전 C.Tr, 필터, VBE 등 PNL 교체","2018-09-17 09:00","2019-02-28 18:00","취소","취소","연속",null,null,null,201807050247,{"$f":"IF(ISERROR(VLOOKUP(D305,#REF!,13,0)),\"-\",VLOOKUP(D305,#REF!,13,0))","v":"-"}]
[297,"광주전남","광주","계림충장#1 T/L","18년 광주 변전정비회사 총액공사 (계림-충장#1T/L)","계림-충장#1T/L 양단 보호반 교체, 장기미동작 CB점검","2018-09-10 09:00","2018-09-12 18:00","취소","취소","연속",null,null,null,201807030002,{"$f":"IF(ISERROR(VLOOKUP(D306,#REF!,13,0)),\"-\",VLOOKUP(D306,#REF!,13,0))","v":"-"}]
[298,"광주전남","광주","계림충장#2 T/L","18년 광주 변전정비회사 총액공사 (계림-충장2T/L)","계림-충장#2T/L 양단 보호반 교체, 장기미동작 CB점검","2018-09-17 09:00","2018-09-19 18:00","취소","취소","연속",null,null,null,201807030004,{"$f":"IF(ISERROR(VLOOKUP(D307,#REF!,13,0)),\"-\",VLOOKUP(D307,#REF!,13,0))","v":"-"}]
[299,"광주전남","광주","정공담양 T/L","18년 광주변전총액공사","담양S/S 정공-담양T/L GIS 보통점검","2018-09-21 09:00","2018-09-21 18:00","취소","취소","당일",null,null,null,201807040112,{"$f":"IF(ISERROR(VLOOKUP(D308,#REF!,13,0)),\"-\",VLOOKUP(D308,#REF!,13,0))","v":"-"}]
[300,"광주전남","광주","담양김제 T/L","18년 광주변전총액공사","담양S/S 담양-김제T/L GIS 보통점검","2018-09-10 09:00","2018-09-10 18:00","취소","취소","당일",null,null,null,201807040113,{"$f":"IF(ISERROR(VLOOKUP(D309,#REF!,13,0)),\"-\",VLOOKUP(D309,#REF!,13,0))","v":"-"}]
[301,"광주전남","광주","담양일곡#1 T/L","154kV 담양-일곡등 6개T/L 피뢰기 설치공사","담양일곡#1T/L No.2~15호간 피뢰기 설치","2018-09-17 08:30","2018-09-19 18:00","2018-09-17 08:30","2018-09-19 18:00","매일",null,null,null,201807040151,{"$f":"IF(ISERROR(VLOOKUP(D310,#REF!,13,0)),\"-\",VLOOKUP(D310,#REF!,13,0))","v":"-"}]
[302,"광주전남","광주","신광주곡성#2 T/L","154kV 담양-일곡등 6개T/L 피뢰기 설치공사","신광주곡성#2 T/L No.1~5호간 피뢰기 설치","2018-09-20 08:30","2018-09-20 18:00","2018-09-20 08:30","2018-09-20 18:00","당일",null,null,null,201807040153,{"$f":"IF(ISERROR(VLOOKUP(D311,#REF!,13,0)),\"-\",VLOOKUP(D311,#REF!,13,0))","v":"-"}]
[303,"광주전남","광주","북광주일곡#1 T/L","18년 광주변전총액공사","북광주 북광주-일곡#1T/L GIS 보통점검","2018-09-13 09:00","2018-09-13 18:00","2018-09-13 09:00","2018-09-13 18:00","당일",null,null,null,201807040115,{"$f":"IF(ISERROR(VLOOKUP(D312,#REF!,13,0)),\"-\",VLOOKUP(D312,#REF!,13,0))","v":"-"}]
[304,"광주전남","광주","남광주화순#1 T/L","18년 광주 변전정비회사 총액공사 (남광주-화순1T/L)","남광주-화순#1T/L LA점검","2018-09-21 09:00","2018-09-21 18:00","2018-09-21 09:00","2018-09-21 18:00","당일",null,null,null,201807030005,{"$f":"IF(ISERROR(VLOOKUP(D313,#REF!,13,0)),\"-\",VLOOKUP(D313,#REF!,13,0))","v":"-"}]
[305,"광주전남","목포","장성영광#2 T/L","154kV 영광S/S #4M.Tr 증설공사","#4M.Tr 증설","2018-09-08 16:00","2018-09-09 16:00","2018-09-08 16:00","2018-09-09 16:00","연속",null,null,null,201805220005,{"$f":"IF(ISERROR(VLOOKUP(D314,#REF!,13,0)),\"-\",VLOOKUP(D314,#REF!,13,0))","v":"-"}]
[306,"광주전남","목포","장성영광#2 T/L","154kV 영광S/S #4M.Tr 증설공사","#4M.Tr 증설","2018-09-13 16:00","2018-09-14 16:00","2018-09-13 16:00","2018-09-14 16:00","연속",null,null,null,201805220006,{"$f":"IF(ISERROR(VLOOKUP(D315,#REF!,13,0)),\"-\",VLOOKUP(D315,#REF!,13,0))","v":"-"}]
[307,"광주전남","목포","장성영광#2 T/L","154kV 영광S/S #4M.Tr 증설공사","#4M.Tr 증설","2018-09-27 13:00","2018-09-28 13:00","2018-09-27 13:00","2018-09-28 13:00","연속",null,null,null,201805070002,{"$f":"IF(ISERROR(VLOOKUP(D316,#REF!,13,0)),\"-\",VLOOKUP(D316,#REF!,13,0))","v":"-"}]
[308,"광주전남","목포","엄다운남#2 T/L","운남S/S 170kV 장기사용 GIS 대체공사","170kV GIS 7BAY 대체(PT&ES BAY포함)","2018-09-27 09:00","2018-10-16 18:00","취소","취소","연속",null,null,null,201807100008,{"$f":"IF(ISERROR(VLOOKUP(D317,#REF!,13,0)),\"-\",VLOOKUP(D317,#REF!,13,0))","v":"-"}]
[309,"광주전남","순천","서순천벌교#1 T/L","154kV 서순천-벌교#1 T/L GIS 대체","벌교S/S 170kV 장기사용 GIS 대체공사","2018-09-03 09:00","2018-09-21 18:00","2018-09-03 09:00","2018-09-21 18:00","연속",null,null,null,201807030035,{"$f":"IF(ISERROR(VLOOKUP(D318,#REF!,13,0)),\"-\",VLOOKUP(D318,#REF!,13,0))","v":"-"}]
[310,"광주전남","순천","서순천벌교#2 T/L","154kV 서순천-벌교#1T/L Wall 부싱 철거","벌교S/S 170kV 장기사용 GIS 대체공사 - 서순천-벌교#1T/L Wall 부싱 철거(이격거리 확보 휴전)","2018-09-06 09:00","2018-09-06 18:00","2018-09-09 09:00","2018-09-09 18:00","당일",null,null,null,201807030058,{"$f":"IF(ISERROR(VLOOKUP(D319,#REF!,13,0)),\"-\",VLOOKUP(D319,#REF!,13,0))","v":"-"}]
[311,"광주전남","순천","서순천벌교#2 T/L","154kV 서순천-벌교#1T/L Wall 부싱 설치","벌교S/S 170kV 장기사용 GIS 대체공사 - 서순천-벌교#1T/L Wall 부싱 설치(이격거리 확보 휴전)","2018-09-12 09:00","2018-09-12 18:00","2018-09-16 09:00","2018-09-16 18:00","당일",null,null,null,201807030063,{"$f":"IF(ISERROR(VLOOKUP(D320,#REF!,13,0)),\"-\",VLOOKUP(D320,#REF!,13,0))","v":"-"}]
[312,"광주전남","순천","승주서순천 T/L","345kV 광양-율촌CC등 12개T/L 피뢰기 설치공사","154kV 승주-서순천T/L 피뢰기 설치 - 피뢰기 설치 (1~96호, 96기)","2018-09-27 07:00","2018-10-02 18:00","2018-09-27 07:00","2018-10-02 18:00","매일",null,null,null,201807090196,{"$f":"IF(ISERROR(VLOOKUP(D321,#REF!,13,0)),\"-\",VLOOKUP(D321,#REF!,13,0))","v":"-"}]
[313,"광주전남","순천","여수TP화치#1 T/L","장기 미동작 차단기 시험","장기 미동작 차단기 시험","2018-09-11 10:00","2018-09-11 13:00","2018-09-11 10:00","2018-09-11 13:00","당일",null,null,null,201807060122,{"$f":"IF(ISERROR(VLOOKUP(D322,#REF!,13,0)),\"-\",VLOOKUP(D322,#REF!,13,0))","v":"-"}]
[314,"광주전남","순천","여수TP용성#1 T/L","장기 미동작 차단기 시험","장기 미동작 차단기 시험","2018-09-21 10:00","2018-09-21 13:00","취소","취소","당일",null,null,null,201807060125,{"$f":"IF(ISERROR(VLOOKUP(D323,#REF!,13,0)),\"-\",VLOOKUP(D323,#REF!,13,0))","v":"-"}]
[315,"광주전남","순천","여수TP용성#2 T/L","장기 미동작 차단기 시험","장기 미동작 차단기 시험","2018-09-21 13:00","2018-09-21 15:00","취소","취소","당일",null,null,null,201807060124,{"$f":"IF(ISERROR(VLOOKUP(D324,#REF!,13,0)),\"-\",VLOOKUP(D324,#REF!,13,0))","v":"-"}]
[316,"광주전남","순천","여수TP화치#2 T/L","장기 미동작 차단기 시험","장기 미동작 차단기 시험","2018-09-11 13:00","2018-09-11 15:00","2018-09-11 13:00","2018-09-11 15:00","당일",null,null,null,201807060123,{"$f":"IF(ISERROR(VLOOKUP(D325,#REF!,13,0)),\"-\",VLOOKUP(D325,#REF!,13,0))","v":"-"}]
[317,"광주전남","직할","나주엄다#1 T/L","154kV 나주-엄다#1T/L(나주S/S 6A6 DS 과열보수)","나주S/S 나주-엄다#1T/L 6A6 DS 과열발생(6월 25일, 상간 온도차 10℃)","2018-09-03 09:00","2018-09-03 18:00","취소","취소","당일",null,null,null,201806260076,{"$f":"IF(ISERROR(VLOOKUP(D326,#REF!,13,0)),\"-\",VLOOKUP(D326,#REF!,13,0))","v":"-"}]
[318,"광주전남","직할","일곡비아#1 T/L","[변전] 비아S/S 장기사용GIS 대체공사","○ 비아-하남#2T/L 대체 후 무부하가압","2018-09-21 18:00","2018-09-22 18:00","2018-09-21 18:00","2018-09-22 18:00","연속",null,null,null,201807100031,{"$f":"IF(ISERROR(VLOOKUP(D327,#REF!,13,0)),\"-\",VLOOKUP(D327,#REF!,13,0))","v":"-"}]
[319,"광주전남","직할","일곡비아#1 T/L","[변전] 비아S/S 장기사용GIS 대체공사","○ #2BUS 가스주입 후 무부하가압용","2018-09-18 18:00","2018-09-19 18:00","2018-09-18 18:00","2018-09-19 18:00","연속",null,null,null,201807100029,{"$f":"IF(ISERROR(VLOOKUP(D328,#REF!,13,0)),\"-\",VLOOKUP(D328,#REF!,13,0))","v":"-"}]
[320,"광주전남","직할","일곡비아#1 T/L","[변전] 비아S/S 장기사용GIS 대체공사","○ #1BUS 가스주입 후 무부하가압용","2018-09-14 18:00","2018-09-15 18:00","2018-09-14 18:00","2018-09-15 18:00","연속",null,null,null,201807100028,{"$f":"IF(ISERROR(VLOOKUP(D329,#REF!,13,0)),\"-\",VLOOKUP(D329,#REF!,13,0))","v":"-"}]
[321,"광주전남","직할","비아하남#2 T/L","[변전] 비아S/S 장기사용GIS 대체공사","○ 장기사용GIS 대체(공사분)","2018-09-10 08:00","2018-09-22 18:00","2018-09-10 08:00","2018-09-22 18:00","연속",null,null,null,201807100025,{"$f":"IF(ISERROR(VLOOKUP(D330,#REF!,13,0)),\"-\",VLOOKUP(D330,#REF!,13,0))","v":"-"}]
[322,"광주전남","직할","일곡비아#2 T/L","154kV 일곡-비아T/L 지중화공사","연제동 힐스테이트 아파트 신축관련 지중화공사(요청자시행) 요청자 : (주)웰메이드씨앤디 시공사 : (주)한백 대상구간 : NO.12~14","2018-09-05 09:00","2018-09-07 18:00","2018-09-05 09:00","2018-09-07 18:00","연속",null,null,null,201807200094,{"$f":"IF(ISERROR(VLOOKUP(D331,#REF!,13,0)),\"-\",VLOOKUP(D331,#REF!,13,0))","v":"-"}]
[323,"대구","경산","진량노변 T/L","PD집합반 설치공사","PD집합반 설치공사","2018-09-20 09:00","2018-09-20 14:00","취소","취소","당일",null,null,null,201806080131,{"$f":"IF(ISERROR(VLOOKUP(D332,#REF!,13,0)),\"-\",VLOOKUP(D332,#REF!,13,0))","v":"-"}]
[324,"대구","경산","신경산노변 T/L","PD집합반 설치 및 접지선교체공사","PD집합반 설치 및 접지선 교체공사","2018-09-20 14:00","2018-09-21 18:00","취소","취소","매일",null,null,null,201806080132,{"$f":"IF(ISERROR(VLOOKUP(D333,#REF!,13,0)),\"-\",VLOOKUP(D333,#REF!,13,0))","v":"-"}]
[325,"대구","경산","노변효목#2 T/L","PD집합반 설치공사","PD집합반 설치공사","2018-09-19 14:00","2018-09-19 20:00","취소","취소","당일",null,null,null,201806080130,{"$f":"IF(ISERROR(VLOOKUP(D334,#REF!,13,0)),\"-\",VLOOKUP(D334,#REF!,13,0))","v":"-"}]
[326,"대구","경산","노변효목#1 T/L","PD집합반 설치공사","PD집합반 설치공사","2018-09-19 09:00","2018-09-19 14:00","취소","취소","당일",null,null,null,201806080129,{"$f":"IF(ISERROR(VLOOKUP(D335,#REF!,13,0)),\"-\",VLOOKUP(D335,#REF!,13,0))","v":"-"}]
[327,"대구","경산","신경산청통#2 T/L","2018년 경산전력 가공송전 협력회사 총액공사","NO.13~14, 32~33 항공구 설치 안전확보","2018-09-17 07:00","2018-09-17 18:00","취소","취소","당일",null,null,null,201807160030,{"$f":"IF(ISERROR(VLOOKUP(D336,#REF!,13,0)),\"-\",VLOOKUP(D336,#REF!,13,0))","v":"-"}]
[328,"대구","경산","신경산청통#1 T/L","2018년 경산전력 가공송전 협력회사 총액공사","NO.13~14, 32~33 항공구 설치 안전확보","2018-09-17 07:00","2018-09-17 18:00","취소","취소","당일",null,null,null,201807160029,{"$f":"IF(ISERROR(VLOOKUP(D337,#REF!,13,0)),\"-\",VLOOKUP(D337,#REF!,13,0))","v":"-"}]
[329,"대구","경산","대구청도#2 T/L","청도S/S 대구-청도#2T/L 휴전","154kV 모선보호반 교체 준공시험","2018-09-20 13:30","2018-09-20 14:00","2018-09-20 13:30","2018-09-20 14:00","당일",null,null,null,201807050154,{"$f":"IF(ISERROR(VLOOKUP(D338,#REF!,13,0)),\"-\",VLOOKUP(D338,#REF!,13,0))","v":"-"}]
[330,"대구","경산","대구청도#1 T/L","청도S/S 대구-청도#1T/L 휴전","154kV 모선보호반 교체 준공시험","2018-09-20 14:00","2018-09-20 14:30","2018-09-20 14:00","2018-09-20 14:30","당일",null,null,null,201807050155,{"$f":"IF(ISERROR(VLOOKUP(D339,#REF!,13,0)),\"-\",VLOOKUP(D339,#REF!,13,0))","v":"-"}]
[331,"대구","달성","다산강창#1 T/L","달성전력 변전총액(차단기 동작특성시험)","달성전력 변전총액(차단기 동작특성시험)","2018-09-14 09:00","2018-09-14 12:00","2018-09-14 09:00","2018-09-14 12:00","당일",null,null,null,201807060198,{"$f":"IF(ISERROR(VLOOKUP(D340,#REF!,13,0)),\"-\",VLOOKUP(D340,#REF!,13,0))","v":"-"}]
[332,"대구","달성","다산강창#2 T/L","달성전력 변전총액(차단기 동작특성시험)","달성전력 변전총액(차단기 동작특성시험)","2018-09-14 12:00","2018-09-14 15:00","2018-09-14 12:00","2018-09-14 15:00","당일",null,null,null,201807060199,{"$f":"IF(ISERROR(VLOOKUP(D341,#REF!,13,0)),\"-\",VLOOKUP(D341,#REF!,13,0))","v":"-"}]
[333,"대구","칠곡","칠곡인동#1 T/L","칠곡S/S #3M.Tr 1차 GIS 대체관련 안전이격 거리 확보","칠곡S/S #3M.Tr 1차 GIS 대체 안전이격 거리 확보","2018-09-03 09:30","2018-09-14 18:00","2018-09-03 09:30","2018-09-14 18:00","연속",null,null,null,201807160146,{"$f":"IF(ISERROR(VLOOKUP(D342,#REF!,13,0)),\"-\",VLOOKUP(D342,#REF!,13,0))","v":"-"}]
[334,"대구","포항","흥해북포항#1 T/L","북포항S/S 170kV 장기사용 GIS 대체공사(1차)","북포항S/S 170kV 장기사용 GIS 대체공사(1차)","2018-09-11 09:00","2018-09-11 13:00","2018-09-12 09:00","2018-09-12 13:00","당일",null,null,null,201807030157,{"$f":"IF(ISERROR(VLOOKUP(D343,#REF!,13,0)),\"-\",VLOOKUP(D343,#REF!,13,0))","v":"-"}]
[335,"대구","포항","흥해북포항#2 T/L","북포항S/S 170kV 장기사용 GIS 대체공사(1차)","북포항S/S 170kV 장기사용 GIS 대체공사(1차)","2018-09-03 09:00","2018-09-19 18:00","2018-09-03 09:00","2018-09-19 18:00","연속",null,null,null,201807030148,{"$f":"IF(ISERROR(VLOOKUP(D344,#REF!,13,0)),\"-\",VLOOKUP(D344,#REF!,13,0))","v":"-"}]
[336,"대구","포항","흥해북포항#1 T/L","북포항S/S 170kV 장기사용 GIS 대체공사(1차)","북포항S/S 170kV 장기사용 GIS 대체공사(1차)","2018-09-07 09:00","2018-09-07 13:00","2018-09-07 09:00","2018-09-07 13:00","당일",null,null,null,201807030156,{"$f":"IF(ISERROR(VLOOKUP(D345,#REF!,13,0)),\"-\",VLOOKUP(D345,#REF!,13,0))","v":"-"}]
[337,"경북","구미","구미광평#1 T/L","154kV 구미-광평T/L 조립식접속함(PMJ) 교체공사","154kV 구미-광평T/L 일진제 R-Type 조립식접속함 21개 교체(7개소)","2018-09-27 09:00","2018-10-10 18:00","2018-09-27 09:00","2018-10-10 18:00","연속",null,null,null,201807110162,{"$f":"IF(ISERROR(VLOOKUP(D346,#REF!,13,0)),\"-\",VLOOKUP(D346,#REF!,13,0))","v":"-"}]
[338,"경북","구미","상주S/S #1 M.Tr A CB","상주S/S RTU교체에 따른 SCADA 정비공사","상주S/S RTU교체에 따른 SCADA 정비공사","2018-09-17 09:00","2018-09-17 15:00","2018-09-17 09:00","2018-09-17 15:00","당일",null,null,null,201807030134,{"$f":"IF(ISERROR(VLOOKUP(D347,#REF!,13,0)),\"-\",VLOOKUP(D347,#REF!,13,0))","v":"-"}]
[339,"경북","구미","상주영동 T/L","2018년 가공송전 순시점검 위탁공사","154kV 상주T/L 초기점검 - No.127~133, 157~159","2018-09-21 09:00","2018-09-21 18:00","취소","취소","당일",null,null,null,201807130077,{"$f":"IF(ISERROR(VLOOKUP(D348,#REF!,13,0)),\"-\",VLOOKUP(D348,#REF!,13,0))","v":"-"}]
[340,"경북","구미","상주보은 T/L","2018년 가공송전 순시점검 위탁공사","154kV 상주T/L 초기점검 - No.127~133, 157~159","2018-09-20 09:00","2018-09-20 18:00","취소","취소","당일",null,null,null,201807130076,{"$f":"IF(ISERROR(VLOOKUP(D349,#REF!,13,0)),\"-\",VLOOKUP(D349,#REF!,13,0))","v":"-"}]
[341,"경북","구미","상주S/S #3 M.Tr A CB","상주S/S RTU교체에 따른 SCADA 정비공사","상주S/S RTU교체에 따른 SCADA 정비공사","2018-09-19 09:00","2018-09-19 15:00","2018-09-19 09:00","2018-09-19 15:00","당일",null,null,null,201807030207,{"$f":"IF(ISERROR(VLOOKUP(D350,#REF!,13,0)),\"-\",VLOOKUP(D350,#REF!,13,0))","v":"-"}]
[342,"경북","구미","상주S/S #2 M.Tr A CB","상주S/S RTU교체에 따른 SCADA 정비공사","상주S/S RTU교체에 따른 SCADA 정비공사","2018-09-18 09:00","2018-09-18 15:00","2018-09-18 09:00","2018-09-18 15:00","당일",null,null,null,201807030137,{"$f":"IF(ISERROR(VLOOKUP(D351,#REF!,13,0)),\"-\",VLOOKUP(D351,#REF!,13,0))","v":"-"}]
[343,"경북","구미","선산청리#2 T/L","선산S/S 154kV 옥외철구 설비 GIS화 공사","PD 발생개소 제작사 보수","2018-09-10 09:00","2018-09-11 18:00","2018-09-10 09:00","2018-09-11 18:00","연속",null,null,null,201807110001,{"$f":"IF(ISERROR(VLOOKUP(D352,#REF!,13,0)),\"-\",VLOOKUP(D352,#REF!,13,0))","v":"-"}]
[344,"경북","영주","봉화울진 T/L","2018-19년도 영주전력지사 변전협력업체 총액공사","- 627 GIS, LA 보통점검","2018-09-14 07:00","2018-09-14 18:00","2018-09-14 07:00","2018-09-14 18:00","당일",null,null,null,201807040075,{"$f":"IF(ISERROR(VLOOKUP(D353,#REF!,13,0)),\"-\",VLOOKUP(D353,#REF!,13,0))","v":"-"}]
[345,"경북","영주","점촌문경 T/L","2018-19년도 영주전력지사 변전협력업체 총액공사","점촌S/S 점촌-문경T/L 차단기 개폐타임측정","2018-09-21 09:00","2018-09-21 14:00","2018-09-21 09:00","2018-09-21 14:00","당일",null,null,null,201807040079,{"$f":"IF(ISERROR(VLOOKUP(D354,#REF!,13,0)),\"-\",VLOOKUP(D354,#REF!,13,0))","v":"-"}]
[346,"경북","직할","신영주안동#2 T/L","안동S/S 23kV 옥외철구 GIS화 공사","가. 23kV 옥외철구 설비 ⇒ 25.8kV 친환경개폐장치 대체 × 28Bay[전문업체분] 나. 제어 및 전력케이블 철거․설치 × 1식 다. 철구 및 기기기초 철거․설치 × 1식 라. 접지 및 기타 부대작업 × 1식","2018-09-27 08:00","2018-09-29 18:00","2018-09-27 08:00","2018-09-29 18:00","연속",null,null,null,201807090069,{"$f":"IF(ISERROR(VLOOKUP(D355,#REF!,13,0)),\"-\",VLOOKUP(D355,#REF!,13,0))","v":"-"}]
[347,"경북","직할","안동S/S #3 M.Tr A CB","안동S/S 23kV 옥외철구 GIS화 공사","가. 23kV 옥외철구 설비 ⇒ 25.8kV 친환경개폐장치 대체 × 28Bay[전문업체분] 나. 제어 및 전력케이블 철거․설치 × 1식 다. 철구 및 기기기초 철거․설치 × 1식 라. 접지 및 기타 부대작업 × 1식","2018-09-01 08:00","2018-09-04 18:00","2018-09-01 08:00","2018-09-04 18:00","연속",null,null,null,201807090058,{"$f":"IF(ISERROR(VLOOKUP(D356,#REF!,13,0)),\"-\",VLOOKUP(D356,#REF!,13,0))","v":"-"}]
[348,"경북","직할","안동동안동#2 T/L","안동S/S 23kV 옥외철구 GIS화 공사","가. 23kV 옥외철구 설비 ⇒ 25.8kV 친환경개폐장치 대체 × 28Bay[전문업체분] 나. 제어 및 전력케이블 철거․설치 × 1식 다. 철구 및 기기기초 철거․설치 × 1식 라. 접지 및 기타 부대작업 × 1식","2018-09-16 08:00","2018-09-18 18:00","2018-09-16 08:00","2018-09-18 18:00","연속",null,null,null,201807090067,{"$f":"IF(ISERROR(VLOOKUP(D357,#REF!,13,0)),\"-\",VLOOKUP(D357,#REF!,13,0))","v":"-"}]
[349,"경북","직할","안동S/S #2 M.Tr A CB","안동S/S 23kV 옥외철구 GIS화 공사","가. 23kV 옥외철구 설비 ⇒ 25.8kV 친환경개폐장치 대체 × 28Bay[전문업체분] 나. 제어 및 전력케이블 철거․설치 × 1식 다. 철구 및 기기기초 철거․설치 × 1식 라. 접지 및 기타 부대작업 × 1식","2018-09-05 08:00","2018-09-08 18:00","2018-09-05 08:00","2018-09-08 18:00","연속",null,null,null,201807090060,{"$f":"IF(ISERROR(VLOOKUP(D358,#REF!,13,0)),\"-\",VLOOKUP(D358,#REF!,13,0))","v":"-"}]
[350,"경북","직할","안동S/S #1 M.Tr A CB","안동S/S 23kV 옥외철구 GIS화 공사","가. 23kV 옥외철구 설비 ⇒ 25.8kV 친환경개폐장치 대체 × 28Bay[전문업체분] 나. 제어 및 전력케이블 철거․설치 × 1식 다. 철구 및 기기기초 철거․설치 × 1식 라. 접지 및 기타 부대작업 × 1식","2018-09-09 08:00","2018-09-12 18:00","2018-09-09 08:00","2018-09-12 18:00","연속",null,null,null,201807090062,{"$f":"IF(ISERROR(VLOOKUP(D359,#REF!,13,0)),\"-\",VLOOKUP(D359,#REF!,13,0))","v":"-"}]
[351,"경북","직할","안동동안동#1 T/L","안동S/S 23kV 옥외철구 GIS화 공사","가. 23kV 옥외철구 설비 ⇒ 25.8kV 친환경개폐장치 대체 × 28Bay[전문업체분] 나. 제어 및 전력케이블 철거․설치 × 1식 다. 철구 및 기기기초 철거․설치 × 1식 라. 접지 및 기타 부대작업 × 1식","2018-09-13 08:00","2018-09-15 18:00","2018-09-13 08:00","2018-09-15 18:00","연속",null,null,null,201807090065,{"$f":"IF(ISERROR(VLOOKUP(D360,#REF!,13,0)),\"-\",VLOOKUP(D360,#REF!,13,0))","v":"-"}]
[352,"경북","직할","안동풍산 T/L","안동S/S 23kV 옥외철구 GIS화 공사","가. 23kV 옥외철구 설비 ⇒ 25.8kV 친환경개폐장치 대체 × 28Bay[전문업체분] 나. 제어 및 전력케이블 철거․설치 × 1식 다. 철구 및 기기기초 철거․설치 × 1식 라. 접지 및 기타 부대작업 × 1식","2018-09-19 08:00","2018-09-21 18:00","2018-09-19 08:00","2018-09-21 18:00","연속",null,null,null,201807090068,{"$f":"IF(ISERROR(VLOOKUP(D361,#REF!,13,0)),\"-\",VLOOKUP(D361,#REF!,13,0))","v":"-"}]
[353,"경북","직할","영덕평해#2 T/L","154kV 평해S/S 현대화 공사","-영덕평해#1T/L GCB 이설관련 안전이격 확보","2018-09-17 09:00","2018-09-17 18:00","취소","취소","연속",null,null,null,201807160015,{"$f":"IF(ISERROR(VLOOKUP(D362,#REF!,13,0)),\"-\",VLOOKUP(D362,#REF!,13,0))","v":"-"}]
[354,"경북","직할","영덕평해#1 T/L","154kV 평해S/S 현대화 공사","-영덕평해#2T/L GCB 이설관련 안전이격 확보차","2018-09-10 09:00","2018-09-10 18:00","취소","취소","당일",null,null,null,201807160010,{"$f":"IF(ISERROR(VLOOKUP(D363,#REF!,13,0)),\"-\",VLOOKUP(D363,#REF!,13,0))","v":"-"}]
[355,"경북","직할","울진평해 T/L","154kV 울진 현종산 풍력발전단지 송전선로 건설공사","No.14 전력선이동, 긴선(하단→상단) 및 평해 변전소 보호계전기 철거,신설,TEST","2018-09-15 07:00","2018-09-21 18:00","취소","취소","연속",null,null,null,201807040114,{"$f":"IF(ISERROR(VLOOKUP(D364,#REF!,13,0)),\"-\",VLOOKUP(D364,#REF!,13,0))","v":"-"}]
[356,"경북","직할","영덕평해#1 T/L","154kV 평해S/S 현대화 공사","-영덕평해#1T/L GCB 이설","2018-09-17 09:00","2018-09-21 18:00","취소","취소","연속",null,null,null,201807160006,{"$f":"IF(ISERROR(VLOOKUP(D365,#REF!,13,0)),\"-\",VLOOKUP(D365,#REF!,13,0))","v":"-"}]
[357,"경북","직할","영덕평해#2 T/L","154kV 평해S/S 현대화 공사","-영덕평해#2T/L GCB 이설","2018-09-10 09:00","2018-09-14 18:00","취소","취소","연속",null,null,null,201807160004,{"$f":"IF(ISERROR(VLOOKUP(D366,#REF!,13,0)),\"-\",VLOOKUP(D366,#REF!,13,0))","v":"-"}]
[358,"부산울산","동부산","구서노포#2 T/L","154kV 노포-정관 등 10개T/L 송전용 피뢰기 설치공사","1. 작업내용 : 154kV 구서-노포#2T/L 피뢰기 설치 2. 설치수량 : 18기, 54set","2018-09-17 09:00","2018-09-19 18:00","2018-09-17 09:00","2018-09-19 18:00","연속",null,null,null,201807050034,{"$f":"IF(ISERROR(VLOOKUP(D367,#REF!,13,0)),\"-\",VLOOKUP(D367,#REF!,13,0))","v":"-"}]
[359,"부산울산","동부산","구서명장#1 T/L","구서S/S 154kV 657GIS Air 누기 불량조치","구서S/S 154kV 657GIS(659-1ES) Air누기 불량조치","2018-09-20 09:30","2018-09-20 17:00","2018-09-21 09:30","2018-09-21 17:00","당일",null,null,null,201807160038,{"$f":"IF(ISERROR(VLOOKUP(D368,#REF!,13,0)),\"-\",VLOOKUP(D368,#REF!,13,0))","v":"-"}]
[360,"부산울산","동부산","노포정관#1 T/L","154kV 노포-정관 등 10개T/L 송전용 피뢰기 설치공사","1. 작업내용 : 154kV 구서-노포#2T/L 피뢰기 설치관련 안전이격확보","2018-09-17 09:00","2018-09-17 18:00","2018-09-17 09:00","2018-09-17 18:00","당일",null,null,null,201807060098,{"$f":"IF(ISERROR(VLOOKUP(D369,#REF!,13,0)),\"-\",VLOOKUP(D369,#REF!,13,0))","v":"-"}]
[361,"부산울산","동부산","명례정관 T/L","154kV 노포-정관 등 10개T/L 송전용 피뢰기설치공사","1. 작업내용 : 154kV 명례-정관T/L 피뢰기 설치 2. 설치수량 : 3기, 9set","2018-09-20 09:00","2018-09-20 18:00","2018-09-20 09:00","2018-09-20 18:00","당일",null,null,null,201807050033,{"$f":"IF(ISERROR(VLOOKUP(D370,#REF!,13,0)),\"-\",VLOOKUP(D370,#REF!,13,0))","v":"-"}]
[362,"부산울산","북부산","북부산S/S 65-66-0 SEC CB","2018년 북부산 변전협력회사 총액공사","북부산S/S 154kV 65-66 Bus-Section GIS 초기점검","2018-09-28 10:00","2018-09-28 18:00","2018-09-28 10:00","2018-09-28 18:00","당일",null,null,null,201807090030,{"$f":"IF(ISERROR(VLOOKUP(D371,#REF!,13,0)),\"-\",VLOOKUP(D371,#REF!,13,0))","v":"-"}]
[363,"부산울산","북부산","북부산S/S 154kV #3 BUS TIE CB","2018년 북부산 변전협력회사 총액공사","북부산S/S 154kV 6300 Bus-Tie 초기점검","2018-09-19 10:00","2018-09-19 18:00","2018-09-19 10:00","2018-09-19 18:00","당일",null,null,null,201807060136,{"$f":"IF(ISERROR(VLOOKUP(D372,#REF!,13,0)),\"-\",VLOOKUP(D372,#REF!,13,0))","v":"-"}]
[364,"부산울산","북부산","북부산S/S 60-61-0 SEC CB","2018년 북부산 변전협력회사 총액공사","북부산S/S 154kV 60-61 Bus-Section GIS 초기점검","2018-09-20 10:00","2018-09-20 18:00","2018-09-20 10:00","2018-09-20 18:00","당일",null,null,null,201807090027,{"$f":"IF(ISERROR(VLOOKUP(D373,#REF!,13,0)),\"-\",VLOOKUP(D373,#REF!,13,0))","v":"-"}]
[365,"부산울산","북부산","북부산S/S 154kV #1 BUS TIE CB","2018년 북부산 변전협력회사 총액공사","북부산S/S 154kV 6100 Bus-Tie 초기점검","2018-09-17 10:00","2018-09-17 18:00","2018-09-17 10:00","2018-09-17 18:00","당일",null,null,null,201807060133,{"$f":"IF(ISERROR(VLOOKUP(D374,#REF!,13,0)),\"-\",VLOOKUP(D374,#REF!,13,0))","v":"-"}]
[366,"부산울산","북부산","북부산S/S 61-62-0 SEC CB","2018년 북부산 변전협력회사 총액공사","북부산S/S 154kV 61-62 Bus-Section GIS 초기점검","2018-09-27 10:00","2018-09-27 18:00","2018-09-27 10:00","2018-09-27 18:00","당일",null,null,null,201807090029,{"$f":"IF(ISERROR(VLOOKUP(D375,#REF!,13,0)),\"-\",VLOOKUP(D375,#REF!,13,0))","v":"-"}]
[367,"부산울산","북부산","북부산S/S 154kV #2 BUS TIE CB","2018년 북부산 변전협력회사 총액공사","북부산S/S 154kV 6200 Bus-Tie 초기점검","2018-09-18 10:00","2018-09-18 18:00","2018-09-18 10:00","2018-09-18 18:00","당일",null,null,null,201807060135,{"$f":"IF(ISERROR(VLOOKUP(D376,#REF!,13,0)),\"-\",VLOOKUP(D376,#REF!,13,0))","v":"-"}]
[368,"부산울산","북부산","언양산막#1 T/L","154kV 신울산-언양 등 3개T/L 지장철탑이설공사","154kV 언양-산막T/L 가선로 구성작업 ○ 가철탑 2기 (2, 3호) 설치 및 기설철탑 2기(2, 3호) 철거 ○ 작업구간 : 1~4호(154kV 직동-언양T/L 50~47호)","2018-09-17 08:00","2018-09-21 18:00","2018-09-17 08:00","2018-09-21 18:00","연속",null,null,null,201807040104,{"$f":"IF(ISERROR(VLOOKUP(D377,#REF!,13,0)),\"-\",VLOOKUP(D377,#REF!,13,0))","v":"-"}]
[369,"부산울산","북부산","언양산막#2 T/L","154kV 신울산-언양 등 3개T/L 지장철탑이설공사","154kV 언양-산막T/L 가선로 구성작업 ○ 가철탑 2기 (2, 3호) 설치 및 기설철탑 2기(2, 3호) 철거 ○ 작업구간 : 1~4호(154kV 직동-언양T/L 50~47호)","2018-09-11 08:00","2018-09-15 18:00","2018-09-11 08:00","2018-09-15 18:00","연속",null,null,null,201807040098,{"$f":"IF(ISERROR(VLOOKUP(D378,#REF!,13,0)),\"-\",VLOOKUP(D378,#REF!,13,0))","v":"-"}]
[370,"부산울산","북부산","물금삼랑진PP#2 T/L","154kV 삼랑진양수 스위치야드 현대화 사업","- 삼랑진양수 발전소 현대화(18.9.~20.9.)에 따른 발전기 전면정지로 스위치야드 셧다운에 따라 삼랑진양수 옥외철구에서 옥외 GIS 대체 시행 - 현대화 사업기간(18.8.~19.9.) 내 안정적 계통운영을 위하여 양산삼랑진T/L과 물금삼랑진#2T/L 간 Jumper 시행(소요기간 5일 예정)","2018-09-10 08:00","2018-09-15 18:00","취소","취소","연속",null,null,null,201807110015,{"$f":"IF(ISERROR(VLOOKUP(D379,#REF!,13,0)),\"-\",VLOOKUP(D379,#REF!,13,0))","v":"-"}]
[371,"부산울산","북부산","물금삼랑진PP#1 T/L","154kV 삼랑진양수 스위치야드 현대화 사업","- 삼랑진양수 발전소 현대화(18.9.~20.9.)에 따른 발전기 전면정지로 스위치야드 셧다운에 따라 삼랑진양수 옥외철구에서 옥외 GIS 대체 시행 - 현대화 사업기간(18.9.~19.9.)에 맞추어 해당설비 장기휴전계획","2018-09-10 08:00","2019-09-09 18:00","취소","취소","연속",null,null,null,201807110010,{"$f":"IF(ISERROR(VLOOKUP(D380,#REF!,13,0)),\"-\",VLOOKUP(D380,#REF!,13,0))","v":"-"}]
[372,"부산울산","북부산","양산삼랑진PP T/L","154kV 삼랑진양수 스위치야드 현대화 사업","- 삼랑진양수 발전소 현대화(18.9.~20.9.)에 따른 발전기 전면정지로 스위치야드 셧다운에 따라 삼랑진양수 옥외철구에서 옥외 GIS 대체 시행 - 현대화 사업기간(18.8.~19.9.) 내 안정적 계통운영을 위하여 양산삼랑진T/L과 물금삼랑진#2T/L 간 Jumper 시행(소요기간 5일 예정)","2018-09-10 08:00","2018-09-15 18:00","취소","취소","연속",null,null,null,201807110014,{"$f":"IF(ISERROR(VLOOKUP(D381,#REF!,13,0)),\"-\",VLOOKUP(D381,#REF!,13,0))","v":"-"}]
[373,"부산울산","북부산","북부산삼랑진PP T/L","154kV 삼랑진양수 스위치야드 현대화 사업","- 삼랑진양수 발전소 현대화(18.9.~20.9.)에 따른 발전기 전면정지로 스위치야드 셧다운에 따라 삼랑진양수 옥외철구에서 옥외 GIS 대체 시행 - 현대화 사업기간(18.9.~19.9.)에 맞추어 해당설비 장기휴전계획","2018-09-10 08:00","2019-09-09 18:00","취소","취소","연속",null,null,null,201807110013,{"$f":"IF(ISERROR(VLOOKUP(D382,#REF!,13,0)),\"-\",VLOOKUP(D382,#REF!,13,0))","v":"-"}]
[374,"부산울산","울산","신울산영남TP#2 T/L","154kV 신울산-울산#2T/L 송전선로용 피뢰기 설치공사(이격거리확보)","ㅁ 154kV 신울산-울산#2T/L 피뢰기 설치 관련 이격거리 확보(병가구간 : No.2~4)","2018-09-27 07:00","2018-09-27 18:00","2018-09-27 07:00","2018-09-27 18:00","당일",null,null,null,201807060074,{"$f":"IF(ISERROR(VLOOKUP(D383,#REF!,13,0)),\"-\",VLOOKUP(D383,#REF!,13,0))","v":"-"}]
[375,"부산울산","울산","신울산울산#1 T/L","2018-19년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV 신울산-울산#1T/L 6M1DS 접촉자 과열보수","2018-09-17 09:00","2018-09-17 18:00","취소","취소","당일",null,null,null,201807090277,{"$f":"IF(ISERROR(VLOOKUP(D384,#REF!,13,0)),\"-\",VLOOKUP(D384,#REF!,13,0))","v":"-"}]
[376,"부산울산","울산","신울산S/S 154kV #62 BUS","신울산S/S 154kV 신울산-영남T/P#1T/L 6K1 과열개소 보수","신울산S/S 154kV 신울산-영남T/P#1T/L 6K1 과열개소 보수","2018-09-20 09:00","2018-09-20 18:00","2018-09-20 09:00","2018-09-20 18:00","당일",null,null,null,201807240025,{"$f":"IF(ISERROR(VLOOKUP(D385,#REF!,13,0)),\"-\",VLOOKUP(D385,#REF!,13,0))","v":"-"}]
[377,"부산울산","울산","신울산영남TP#1 T/L","신울산S/S 154kV 신울산-영남T/P#1T/L 6K1 과열개소 보수","신울산S/S 154kV 신울산-영남T/P#1T/L 6K1 과열개소 보수","2018-09-20 09:00","2018-09-20 18:00","2018-09-20 09:00","2018-09-20 18:00","당일",null,null,null,201807240023,{"$f":"IF(ISERROR(VLOOKUP(D386,#REF!,13,0)),\"-\",VLOOKUP(D386,#REF!,13,0))","v":"-"}]
[378,"부산울산","울산","신울산울산#2 T/L","154kV 신울산-울산#2T/L 송전선로용 피뢰기 설치공사","1. 선로명 : 154kV 신울산-울산#2T/L 2. 공사개요 : 송전선로용 피뢰기 설치 ㅇ 구간 : No.1~11, 15, 16(14기)","2018-09-27 07:00","2018-09-28 18:00","취소","취소","연속",null,null,null,201807060031,{"$f":"IF(ISERROR(VLOOKUP(D387,#REF!,13,0)),\"-\",VLOOKUP(D387,#REF!,13,0))","v":"-"}]
[379,"부산울산","울산","온산처용#1 T/L","2018년 처용S/S 170kV 장기사용 GIS 대체공사","처용S/S 170kV 용연-처용#1T/L(627),#2M.Tr 1차 GIS(6233) GIS 대체관련 #1BUS시험가압","2018-09-10 18:00","2018-09-11 18:00","2018-09-10 18:00","2018-09-11 18:00","연속",null,null,null,201807090276,{"$f":"IF(ISERROR(VLOOKUP(D388,#REF!,13,0)),\"-\",VLOOKUP(D388,#REF!,13,0))","v":"-"}]
[380,"부산울산","직할","범일서면#2 T/L","154kV 범일 등 3개S/S 지중송전케이블 선종교체공사","154kV 범일-서면T/L 선종교체공사(OF 1200 ----> XLPE 1200) - 공사구간 : 범일S/S ~ J/B#7-1, 서면S/S ~ S/J","2018-09-27 09:00","2018-11-08 18:00","2018-09-27 09:00","2018-11-08 18:00","연속",null,null,null,201807090325,{"$f":"IF(ISERROR(VLOOKUP(D389,#REF!,13,0)),\"-\",VLOOKUP(D389,#REF!,13,0))","v":"-"}]
[381,"부산울산","직할","부산수정#2 T/L","2018년 직할 변전협력회사 총액공사","- 부산S/S 부산-수정#2T/L PNL 대체 - 수정S/S 부산-수정#2T/L PNL 대체 - 수정S/S 부산-수정#2T/L GIS 보통점검 (9/20 10:00~16:00) - 부산S/S 부산-수정#2T/L GIS 미동작점검 (9/20 10:00~16:00)","2018-09-19 14:00","2018-09-21 18:00","2018-09-19 14:00","2018-09-21 18:00","연속",null,null,null,201807100003,{"$f":"IF(ISERROR(VLOOKUP(D390,#REF!,13,0)),\"-\",VLOOKUP(D390,#REF!,13,0))","v":"-"}]
[382,"부산울산","직할","부산영도#2 T/L","154kV 부산-영도T/L 선종 교체 공사","□ 선종교체 : OF 케이블 → XLPE 케이블 ○ 154kV OF 케이블 1200㎟, 2회선-1.2km 철거 ○ 154kV XLPE 케이블 1200㎟, 2회선-1.2km 설치.","2018-09-27 09:00","2018-11-25 18:00","2018-09-27 09:00","2018-11-25 18:00","연속",null,null,null,201807060083,{"$f":"IF(ISERROR(VLOOKUP(D391,#REF!,13,0)),\"-\",VLOOKUP(D391,#REF!,13,0))","v":"-"}]
[383,"부산울산","직할","부산수정#1 T/L","2018년 직할 변전협력회사 총액공사","- 부산S/S 부산-수정#1T/L PNL 대체 - 수정S/S 부산-수정#1T/L PNL 대체 - 수정S/S 부산-수정#1T/L GIS 보통점검 (9/17 10:00~16:00) - 부산S/S 부산-수정#1T/L GIS 미동작점검 (9/17 10:00~16:00)","2018-09-17 10:00","2018-09-19 14:00","2018-09-17 10:00","2018-09-19 14:00","연속",null,null,null,201807100002,{"$f":"IF(ISERROR(VLOOKUP(D392,#REF!,13,0)),\"-\",VLOOKUP(D392,#REF!,13,0))","v":"-"}]
[384,"부산울산","직할","수정S/S 154kV #1 BUS TIE CB","2018년 직할 변전협력회사 총액공사","6100BT GIS 보통점검","2018-09-15 10:00","2018-09-15 16:00","2018-09-15 10:00","2018-09-15 16:00","당일",null,null,null,201807100004,{"$f":"IF(ISERROR(VLOOKUP(D393,#REF!,13,0)),\"-\",VLOOKUP(D393,#REF!,13,0))","v":"-"}]
[385,"경남","직할","신월동읍#2 T/L","154kV 녹공-마천 등 17개 T/L 피뢰기 설치공사","신월-삼정#2T/L 피뢰기 설치공사 작업 안전이격 확보","2018-09-15 09:00","2018-09-15 18:00","2018-09-15 09:00","2018-09-15 18:00","당일",null,null,null,201807090305,{"$f":"IF(ISERROR(VLOOKUP(D394,#REF!,13,0)),\"-\",VLOOKUP(D394,#REF!,13,0))","v":"-"}]
[386,"경남","직할","창공월림#2 T/L","154kV 창원-창공T/L 전력선교체공사","154kV 창원-창공T/L 전력선교체공사 * 전력선교체공사관련 안전거리 확보","2018-09-15 07:00","2018-09-29 18:00","2018-09-15 07:00","2018-09-29 18:00","연속",null,null,null,201807180075,{"$f":"IF(ISERROR(VLOOKUP(D395,#REF!,13,0)),\"-\",VLOOKUP(D395,#REF!,13,0))","v":"-"}]
[387,"경남","직할","창원창공#1 T/L","154kV 창원-창공T/L 전력선교체공사","154kV 창원-창공T/L 전력선교체공사 창공S/T~6호","2018-09-15 07:00","2018-09-29 18:00","2018-09-15 07:00","2018-09-29 18:00","연속",null,null,null,201807180074,{"$f":"IF(ISERROR(VLOOKUP(D396,#REF!,13,0)),\"-\",VLOOKUP(D396,#REF!,13,0))","v":"-"}]
[388,"경남","진주","사봉개양#1 T/L","154kV 사봉분기(증)T/L 건설공사","사봉분기(증) 건설공사 부분 인계인수검사 관련 부적합사항 조치 - 154kV 사봉-개양#1T/L No.2 3상 점퍼선 교체","2018-09-10 08:00","2018-09-10 15:00","2018-09-10 08:00","2018-09-10 15:00","당일",null,null,null,201807090228,{"$f":"IF(ISERROR(VLOOKUP(D397,#REF!,13,0)),\"-\",VLOOKUP(D397,#REF!,13,0))","v":"-"}]
[389,"경남","진주","가야사봉#2 T/L","154kV 사봉분기(증)T/L 건설공사","사봉분기(증) 건설공사 부분 인계인수검사 관련 부적합사항 조치 - 154kV 사봉-개양#1T/L No.2 3상 점퍼선 교체 - 안전이격거리 확보","2018-09-10 08:00","2018-09-10 15:00","2018-09-10 08:00","2018-09-10 15:00","당일",null,null,null,201807090232,{"$f":"IF(ISERROR(VLOOKUP(D398,#REF!,13,0)),\"-\",VLOOKUP(D398,#REF!,13,0))","v":"-"}]
[390,"경남","진주","의령함양 T/L","154kV 의령-함양T/L 93호 과열개소 정비","154kV 의령-함양T/L 93호 과열개소 정비","2018-09-01 13:00","2018-09-01 18:00","2018-09-01 13:00","2018-09-01 18:00","당일",null,null,null,201806260156,{"$f":"IF(ISERROR(VLOOKUP(D399,#REF!,13,0)),\"-\",VLOOKUP(D399,#REF!,13,0))","v":"-"}]
[391,"경남","진주","동진주진주#2 T/L","진주S/S 154kV 동진주-진주#2T/L CB(637) 조작시험","진주S/S 154kV 동진주-진주#2T/L CB(637) 개폐장치 조작시험 병행 : 진주S/S 154kV 동진주-진주#2T/L LA 보통점검","2018-09-02 09:00","2018-09-02 14:00","2018-09-02 09:00","2018-09-02 14:00","당일",null,null,null,201806270097,{"$f":"IF(ISERROR(VLOOKUP(D400,#REF!,13,0)),\"-\",VLOOKUP(D400,#REF!,13,0))","v":"-"}]
[392,"경남","진주","하동개양#1 T/L","154kV 하동-개양T/L 30~33호 안전이격거리확보 및 피뢰기설치","154kV 하동-개양#1T/L 30~33호 안전이격거리확보 임시선로 구성","2018-09-22 07:00","2018-09-23 20:00","2018-09-22 07:00","2018-09-23 20:00","연속",null,null,null,201807020057,{"$f":"IF(ISERROR(VLOOKUP(D401,#REF!,13,0)),\"-\",VLOOKUP(D401,#REF!,13,0))","v":"-"}]
[393,"경남","진주","광양하동#2 T/L","하동S/S 154kV 광양-하동#2T/L CB(687) 보통점검","하동S/S 154kV 광양-하동#2T/L CB(687) 보통점검 병행 : 광양-하동#2T/L LA,PT 보통점검 (변전부 우종택)","2018-09-19 14:00","2018-09-19 18:30","2018-09-19 14:00","2018-09-19 18:30","당일",null,null,null,201806270103,{"$f":"IF(ISERROR(VLOOKUP(D402,#REF!,13,0)),\"-\",VLOOKUP(D402,#REF!,13,0))","v":"-"}]
[394,"경남","진주","광양하동#1 T/L","하동S/S 154kV 광양-하동#1T/L CB(677) 보통점검","하동S/S 154kV 광양-하동#1T/L CB(677) 보통점검 병행 : 광양-하동#1T/L LA,PT 보통점검 (변전부 우종택)","2018-09-19 09:30","2018-09-19 14:00","2018-09-19 09:30","2018-09-19 14:00","당일",null,null,null,201806270102,{"$f":"IF(ISERROR(VLOOKUP(D403,#REF!,13,0)),\"-\",VLOOKUP(D403,#REF!,13,0))","v":"-"}]
[395,"경남","진주","하동개양#1 T/L","154kV 하동-개양T/L 30~33호 안전이격거리확보 및 피뢰기설치","#2T/L 88~108호 구간 피뢰기설치 안전거리확보","2018-09-29 07:00","2018-09-30 20:00","2018-09-29 07:00","2018-09-30 20:00","매일",null,null,null,201807130021,{"$f":"IF(ISERROR(VLOOKUP(D404,#REF!,13,0)),\"-\",VLOOKUP(D404,#REF!,13,0))","v":"-"}]
[396,"경남","진주","하동개양#2 T/L","154kV 하동-개양T/L 30~33호 안전이격거리확보 및 피뢰기설치","154kV 하동-개양T/L 30~33호 안전이격거리확보 임시선로 구성","2018-09-29 07:00","2018-09-30 20:00","2018-09-29 07:00","2018-09-30 20:00","연속",null,null,null,201807020058,{"$f":"IF(ISERROR(VLOOKUP(D405,#REF!,13,0)),\"-\",VLOOKUP(D405,#REF!,13,0))","v":"-"}]
[397,"경남","진주","산청함양 T/L","함양S/S 154kV 산청-함양T/L CB(657) 개폐장치 조작시험","함양S/S 154kV 산청-함양T/L CB(657) 개폐장치 조작시험","2018-09-01 10:00","2018-09-01 13:00","2018-09-01 10:00","2018-09-01 13:00","당일",null,null,null,201806270111,{"$f":"IF(ISERROR(VLOOKUP(D406,#REF!,13,0)),\"-\",VLOOKUP(D406,#REF!,13,0))","v":"-"}]
[398,"경남","진주","함양거창#2 T/L","함양S/S 154kV 함양-거창#2T/L CB(687) 개폐장치 조작시험","함양S/S 154kV 함양-거창#2T/L CB(687) 개폐장치 조작시험 병행 : 거창S/S 154kV 함양-거창#2T/L CB(647) 개폐장치 조작시험(변전부 배기원)","2018-09-15 10:00","2018-09-15 18:00","2018-09-15 10:00","2018-09-15 18:00","당일",null,null,null,201806270109,{"$f":"IF(ISERROR(VLOOKUP(D407,#REF!,13,0)),\"-\",VLOOKUP(D407,#REF!,13,0))","v":"-"}]
[399,"경남","진주","함양거창#1 T/L","함양S/S 154kV 함양-거창#1T/L CB(677) 개폐장치 조작시험","함양S/S 154kV 함양-거창#1T/L CB(677) 개폐장치 조작시험 병행 : 거창S/S 154kV 함양-거창#1T/L CB(637) 개폐장치 조작시험(변전부 배기원)","2018-09-08 10:00","2018-09-08 18:00","2018-09-08 10:00","2018-09-08 18:00","당일",null,null,null,201806270106,{"$f":"IF(ISERROR(VLOOKUP(D408,#REF!,13,0)),\"-\",VLOOKUP(D408,#REF!,13,0))","v":"-"}]
[400,"경남","통영","삼천포사천#2 T/L","154kV 삼천포-사천T/L 전선교체공사","154kV 삼천포-사천T/L 전선교체공사 20~21, 22~25호 구간","2018-09-16 07:00","2018-09-20 18:00","2018-09-16 07:00","2018-09-20 18:00","연속",null,null,null,201807050184,{"$f":"IF(ISERROR(VLOOKUP(D409,#REF!,13,0)),\"-\",VLOOKUP(D409,#REF!,13,0))","v":"-"}]
[401,"경남","통영","삼천포사천#1 T/L","154kV 삼천포-사천T/L 전선교체공사","154kV 삼천포-사천T/L 전선교체공사 20~21, 22~25호 구간","2018-09-11 07:00","2018-09-15 18:00","2018-09-11 07:00","2018-09-15 18:00","연속",null,null,null,201807050182,{"$f":"IF(ISERROR(VLOOKUP(D410,#REF!,13,0)),\"-\",VLOOKUP(D410,#REF!,13,0))","v":"-"}]
[402,"경남","통영","신고성거제#1 T/L","154kV 진동-안정T/L 피뢰기 설치공사 병가구간 안전확보","154kV 진동-안정T/L 피뢰기 설치공사 병가구간 안전확보","2018-09-15 07:00","2018-09-16 18:00","2018-09-15 07:00","2018-09-16 18:00","매일",null,null,null,201807050196,{"$f":"IF(ISERROR(VLOOKUP(D411,#REF!,13,0)),\"-\",VLOOKUP(D411,#REF!,13,0))","v":"-"}]
[403,"경남","통영","신마산진동 T/L","진동S/S 154kV 신마산-진동T/L GIS 대체공사","1. 진동S/S 154kV 신마산-진동T/L GIS 대체공사","2018-09-27 08:30","2018-10-09 19:00","2018-09-27 08:30","2018-10-09 19:00","연속",null,null,null,201807070001,{"$f":"IF(ISERROR(VLOOKUP(D412,#REF!,13,0)),\"-\",VLOOKUP(D412,#REF!,13,0))","v":"-"}]
[404,"경남","함안","가야사봉#1 T/L","가야S/S 제강T/L 대체공사(#2BUS 시험가압)","가야S/S 제강T/L 대체공사 - #2BUS 및 2DS, CB 부 시험가압","2018-09-13 14:00","2018-09-14 17:30","2018-09-13 14:00","2018-09-14 17:30","연속",null,null,null,201807100042,{"$f":"IF(ISERROR(VLOOKUP(D413,#REF!,13,0)),\"-\",VLOOKUP(D413,#REF!,13,0))","v":"-"}]
[405,"경남","함안","가야사봉#1 T/L","가야S/S 제강T/L 대체공사(#1BUS 시험가압)","가야S/S 제강T/L 대체공사 - #1BUS 시험가압","2018-09-07 14:00","2018-09-08 14:00","2018-09-07 14:00","2018-09-08 14:00","연속",null,null,null,201807100041,{"$f":"IF(ISERROR(VLOOKUP(D414,#REF!,13,0)),\"-\",VLOOKUP(D414,#REF!,13,0))","v":"-"}]
[406,"경남","함안","가야사봉#1 T/L","가야S/S 제강T/L 대체공사(안전이격확보)","가야S/S 제강T/L 대체공사 - 인출용 철구 설치(안전이격확보)","2018-09-15 09:30","2018-09-15 17:30","2018-09-15 09:30","2018-09-15 17:30","당일",null,null,null,201807240028,{"$f":"IF(ISERROR(VLOOKUP(D415,#REF!,13,0)),\"-\",VLOOKUP(D415,#REF!,13,0))","v":"-"}]
[407,"경남","함안","가야사봉#1 T/L","가야S/S 제강T/L 대체공사(안전이격확보)","가야S/S 제강T/L 대체공사 - 전선연결 및 철구조립에 따른 안전이격확보","2018-09-24 09:30","2018-09-25 17:30","2018-09-24 09:30","2018-09-25 17:30","연속",null,null,null,201807100043,{"$f":"IF(ISERROR(VLOOKUP(D416,#REF!,13,0)),\"-\",VLOOKUP(D416,#REF!,13,0))","v":"-"}]
[408,"경남","함안","신마산차룡#2 T/L","154kV 신마산-차룡#2T/L 피뢰기 설치공사","ㅇ1~5호 피뢰기 설치","2018-09-27 07:30","2018-09-27 18:00","2018-09-27 07:30","2018-09-27 18:00","당일",null,null,null,201807050168,{"$f":"IF(ISERROR(VLOOKUP(D417,#REF!,13,0)),\"-\",VLOOKUP(D417,#REF!,13,0))","v":"-"}]
[409,"경남","함안","진영한림정#1 T/L","한림정S/S 6133 GIS 제작사 메커니즘 보수 시험가압","한림정S/S 6133 GIS 제작사 메커니즘 보수 시험가압 관련 진영-한림정#1T/L 휴전","2018-09-01 14:00","2018-09-01 17:30","2018-09-01 14:00","2018-09-01 17:30","당일",null,null,null,201807060180,{"$f":"IF(ISERROR(VLOOKUP(D418,#REF!,13,0)),\"-\",VLOOKUP(D418,#REF!,13,0))","v":"-"}]
[410,"경남","함안","한림정삼계#2 T/L","한림정S/S 한림정-삼계#2T/L 647 GIS 조작시험","한림정S/S 한림정-삼계#2T/L 647 GIS 조작시험","2018-09-29 16:00","2018-09-29 17:30","2018-09-29 16:00","2018-09-29 17:30","당일",null,null,null,201807060153,{"$f":"IF(ISERROR(VLOOKUP(D419,#REF!,13,0)),\"-\",VLOOKUP(D419,#REF!,13,0))","v":"-"}]
[411,"경남","함안","진영한림정#2 T/L","한림정S/S 6233 GIS 제작사 메커니즘 보수 시험가압","한림정S/S 6233 GIS 제작사 메커니즘 보수 시험가압 관련 진영-한림정#2T/L 휴전","2018-09-29 14:00","2018-09-29 16:00","2018-09-29 14:00","2018-09-29 16:00","당일",null,null,null,201807060181,{"$f":"IF(ISERROR(VLOOKUP(D420,#REF!,13,0)),\"-\",VLOOKUP(D420,#REF!,13,0))","v":"-"}]
[412,"경남","함안","진영한림정#1 T/L","한림정S/S 6100 GIS 제작사 메커니즘 보수 시험가압","한림정S/S 6100 GIS 제작사 메커니즘 보수 시험가압 관련 진영-한림정#1T/L 휴전","2018-09-08 14:00","2018-09-08 17:30","2018-09-08 14:00","2018-09-08 17:30","당일",null,null,null,201807060175,{"$f":"IF(ISERROR(VLOOKUP(D421,#REF!,13,0)),\"-\",VLOOKUP(D421,#REF!,13,0))","v":"-"}]

{"sheet":"한수원","index":3,"n_rows":5,"n_cols":13,"rows_kept":5,"cut":false,"hidden":false,"merged":[[1,11,2,11],[1,12,2,12],[1,0,2,0],[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,4,2,4],[1,5,2,5],[1,6,1,7],[1,8,1,9],[1,10,2,10]]}
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","처리결과\n(Y/N)","처리사유"]
[{"$nulls":6},"시작","종료","시작","종료"]
[3,"한빛본부","3발전소","#5 주변압기","한빛5호기 12차 O/H 중 주변압기\n점검\n* 조작차단기 : CB 7D00, 7D71","○ 주변압기 일반점검\n○ 소내보조변압기 일반점검\n○ 갑종보호계전기 삼중화 개선 및 준공시험","2018-09-28\n10:00","2018-10-24\n16:00","2018-09-27\n09:00","2018-10-20\n18:00","연속"]
[4,"한울본부","1발전소","#1 비상보조변압기","한울1호기 22차 O/H 중 비상보조\n변압기 교체\n* 조작차단기 : CB 7300, 7372","○ 비상보조변압기 교체","2018-09-18\n10:00","2018-10-08\n18:00","2018-09-18\n10:00","2018-10-08\n18:00","연속"]

{"sheet":"중부","index":4,"n_rows":7,"n_cols":13,"rows_kept":7,"cut":false,"hidden":false,"merged":[[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7]]}
["2018년도 09월휴전계획표(한국중부발전)"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","처리결과\n(Y/N)","처리사유"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"인천발전본부","복합3호기","인천CC#5,6GT 주변압기(7B00,7B71)","계획예방정비공사(A급)","변압기, GCB 및 IPB 점검,정기검사","2018-09-03 09:00","2018-10-26 18:00","2018-09-03 09:00","2018-10-26 18:00","연속"]
[2,"인천발전본부","복합3호기","인천CC#3ST 주변압기(7B00,7B72)","계획예방정비공사(A급)","변압기, GCB 및 IPB 점검,정기검사","2018-10-27 09:00","2018-11-23 18:00","2018-10-27 09:00","2018-11-23 18:00","연속"]
[3,"보령본부","보령3발","345kV 보령-보령복합(연락) #2 T/L\n(CB 7772, 7872, 7800, 7871, 7200, 7271)","7,8호기 GIS 78Bay \n보통점검","갑종보호계전기 시험 및\nGIS 78Bay 보통점검","2018-10-29 09:00","2018-11-09 17:00","2018-10-29 09:00","2018-11-09 17:00","연속"]