{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["집중심의","765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":14,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"집중심의","index":0,"n_rows":39,"n_cols":11,"rows_kept":39,"cut":false,"hidden":true,"merged":[[0,1,0,10],[2,6,2,7],[2,8,2,9]]}
[null,"'18년 12월 주요휴전 집중심의 대상"]
[]
["번호","전압","본부","설 비 명","공     사    개    요","심의사유","신청일시(일수)",null,"심의일시(일수)",null,"비  고"]
[1,345,"경기","화성S/S 70-71-0 SEC CB(70-71-0)"," 화성S/S 용량부족 차단기대체 및 SW증설 공사","장기휴전","18-12-01 09:00 ~ 19-04-30 18:00",151]
[2,345,"경기","화성S/S 345kV #1LCR 71BUS CB(7177)"," 화성S/S 용량부족 차단기대체 및 SW증설 공사","장기휴전","18-12-01 09:00 ~ 19-04-30 18:00",151]
[3,345,"경기","화성S/S 345kV #1LCR 70BUS CB(7077)"," 화성S/S 용량부족 차단기대체 및 SW증설 공사","장기휴전","18-12-01 09:00 ~ 19-04-30 18:00",151]
[4,345,"경기","화성S/S 345kV #70 BUS"," 화성S/S 용량부족 차단기대체 및 SW증설 공사","장기휴전","18-12-01 09:00 ~ 19-04-30 18:00",151]
[5,345,"경기","화성S/S 345kV #2LCR 75BUS GIS CB(7577)"," 화성S/S 용량부족 차단기대체 및 SW증설 공사","동시휴전","12-03 09:00 ~ \n12-07 18:00",5]
[6,345,"경기","화성S/S 345kV #2LCR 76BUS GIS CB(7677)"," 화성S/S 용량부족 차단기대체 및 SW증설 공사","동시휴전","12-03 09:00 ~\n12-07 18:00",5]
[7,345,"경기","화성S/S 345kV #71 BUS"," 화성S/S 용량부족 차단기대체 및 SW증설 공사","장기휴전","12-11 09:00 ~\n12-25 18:00",15]
[8,154,"전북","신김제S/S #61 EM.Tr","신김제 ESS 정밀점검","장기휴전\n(ESS 정지)","12-01 09:00 ~\n12-12 18:00",12,null,null,"ESS 정지"]
[9,154,"광주전남","나주변전소 T/L","나주옥내화 관련 154kV 송전선로 이설공사","장기휴전","19-03~19-05","3개월","19-03~19-05","3개월","19년 중요휴전 사전협의"]
[10,154,"광주전남","장성영광#1T/L","154kV 장성-영광#1T/L 비표준 EB-A 자기애관 교체공사\n○ EB-A 교체 #1T/L A,B상\n○ 케이블 포설 #1T/L A,B상 114m\n○ 무접지 PMNJ #1T/L A,B상\n○ 기타 부대공사 2식 ","계통안정","11-19 09:00 ~ 11-26 18:00",8,"11-19 09:00 ~\n11-26 18:00",8]
[11,154,"광주전남","장성영광#2T/L"," 154kV 장성-영광#1T/L 비표준 EB-A 자기애관 교체공사\n○ EB-A 부분방전 진단 UWB센서 설치(#2T/L) ","계통안정","11-27 09:00 ~ 11-27 15:00",1,"11-27 09:00 ~\n11-27 15:00",1]
[12,154,"대구","논공S/S #1EM.Tr","23kV GIS - ESS GIS 모선연계","ESS 설비","12-17 09:00 ~ 12-20 18:00",4]
[13,345,"부산울산","신김해북부산#1,2 T/L","북부산S/S 구내 가공지선 철거\n(신김해-북부산#1,2 T/L 횡단개소)","동시휴전","12-04 09:00 ~ 12-04 18:00",1]
[14,345,"부산울산","울산C/C #3 M.Tr A","울산C/C 345kV #3M.Tr 보통점검 및 2차 차단기 동작시험","발전소 연계선로","12-10 09:00 ~ 12-11 18:00",2]
[15,345,"부산울산","신온산S/S #1 M.Tr A","신온산S/S 345kV #1M.Tr 보통점검 신온산S/S 345kV 7200,7272 차단기 동작시험 신온산S/S 154kV 6144 GIS, 23kV 6484 CB 보통점검","발전소 연계선로","12-06 09:00 ~ 12-07 18:00",2]
[16,345,"부산울산","서창산막#1 T/L","양산사송 공공주택지구 내 지장철탑 이설","계통안정","12-07 07:00 ~ 12-09 18:00",3]
[17,345,"부산울산","신양산북부산#2 T/L","345kV 신양산-북부산 T/L : 41-43호 154kV 노포-정관T/L : 8-12호 신설철탑 : 1기, 가철탑 : 1기","장기휴전","12-09 08:00 ~ 12-11 18:00",3]
[18,345,"부산울산","신양산북부산#1 T/L","345kV 신양산-북부산 T/L : 41-43호 154kV 노포-정관T/L : 8-12호 신설철탑 : 1기, 가철탑 : 1기","장기휴전","12-12 08:00 ~ 12-19 18:00",8]
[19,345,"부산울산","신양산북부산#2 T/L","345kV 신양산-북부산 T/L : 41-43호 154kV 노포-정관T/L : 8-12호 신설철탑 : 1기, 가철탑 : 1기","장기휴전","12-20 08:00 ~ 12-24 18:00",5]
[20,154,"부산울산","노포정관#2 T/L","345kV 신양산-북부산 T/L : 41-43호 154kV 노포-정관T/L : 8-12호 신설철탑 : 1기, 가철탑 : 1기","장기휴전","12-12 08:00 ~ 12-24 18:00",13]
[21,154,"부산울산","노포정관#1 T/L","345kV 신양산-북부산 T/L : 41-43호 154kV 노포-정관T/L : 8-12호 신설철탑 : 1기, 가철탑 : 1기","장기휴전","12-25 08:00 ~ 12-28 18:00",4]
[22,154,"부산울산","서부산-부민#1 T/L","154kV 서부산-신평,YK T/L 지중화사업 ","발전소 연계선로","12-18 12:00 ~ 12-18 13:00",1]
[23,154,"부산울산","서부산S/S #65BUS","154kV 서부산-신평,YK T/L 지중화사업 ","발전소 연계선로","12-18 12:00 ~ 12-18 13:00",1]
[24,345,"경남","신마산-삼천포T/P #2 T/L"," 345kV 신마산S/S 용량부족 차단기 대체공사","계통안정","12-01 07:00 ~ 12-04 19:00",4]
[25,154,"경남","신마산S/S 154kV #61 BUS"," 345kV 신마산S/S 용량부족 차단기 대체공사","계통안정","12-05 15:00 ~ 12-05 18:00",1]
[26,345,"경남","의령-신마산 #1 T/L"," 345kV 신마산S/S 용량부족 차단기 대체공사","계통안정","12-05 06:30 ~ 12-11 18:00",7]
[27,345,"경남","의령-신마산 #2 T/L"," 345kV 신마산S/S 용량부족 차단기 대체공사","계통안정","12-12 06:30 ~ 12-18 18:00",7]
[28,345,"경남","신마산-삼천포T/P #2 T/L"," 345kV 신마산S/S 용량부족 차단기 대체공사","계통안정","12-19 06:30 ~ 12-24 18:00",7]
[29,345,"경남","신마산-삼천포T/P #1 T/L"," 345kV 신마산S/S 용량부족 차단기 대체공사","계통안정","12-25 06:30 ~ 12-30 18:00",7]
[30,154,"경남","신마산-칠서 #1 T/L"," 345kV 신마산S/S 용량부족 차단기 대체공사","계통안정","12-22 07:00 ~ 12-22 19:00",1]
[31,154,"경남","신마산-칠서 #2 T/L"," 345kV 신마산S/S 용량부족 차단기 대체공사","계통안정","12-22 07:00 ~ 12-22 19:00",1]
[32,154,"경남","신마산S/S 154kV #60 BUS"," 345kV 신마산S/S 용량부족 차단기 대체공사","계통안정","12-22 15:00 ~ 12-22 18:00",1]
[33,345,"경남","신마산S/S #5 M.Tr"," 345kV 신마산S/S 용량부족 차단기 대체공사","계통안정","12-23 07:00 ~ 01-08 18:00",17]
[34,154,"경남","신마산-칠서 #1 T/L"," 345kV 신마산S/S 용량부족 차단기 대체공사","계통안정","12-29 07:00 ~ 12-29 19:00",1]
[35,154,"경남","신마산-칠서 #2 T/L"," 345kV 신마산S/S 용량부족 차단기 대체공사","계통안정","12-29 07:00 ~ 12-29 19:00",1]
[36,154,"경남","의령S/S #1EM.Tr ","#1EM.Tr 하자점검","ESS휴전","12-05 09:00 ~ 12-05 18:30",1]

{"sheet":"765송부","index":1,"n_rows":4,"n_cols":16,"rows_kept":4,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,14,3,14],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
["2019년도 1월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]

{"sheet":"345송부","index":2,"n_rows":44,"n_cols":12,"rows_kept":44,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2],[2,11,3,11]]}
["2019년도 1월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"인천","김포","가정개폐소 345KV #1Sh.R - TIE CB (7600)","7372 CB 무부하 가압","○가정S/S 7372 CB 설치 ○가정S/S 7272, 7472 LINE PT 설치 ○기타부대작업","2019-01-24 18:00","2019-01-25 18:00","취소","취소","연속"]
[2,"인천","김포","345kV 가정개폐소 #1 Sh.R 1차 CB (7671)","7372 CB 무부하 가압","○가정S/S 7372 CB 설치 ○가정S/S 7272, 7472 LINE PT 설치 ○기타부대작업","2019-01-24 18:00","2019-01-25 18:00","취소","취소","연속"]
[3,"인천","김포","가정개폐소 345kV #76BUS","7372 CB 무부하 가압","○가정S/S 7372 CB 설치 ○가정S/S 7272, 7472 LINE PT 설치 ○기타부대작업","2019-01-24 18:00","2019-01-25 18:00","취소","취소","연속"]
[4,"인천","김포","345kV신가좌 - 가정 #2T/L CB (7371)","73BAY BF 시험","○가정S/S 7372 CB 설치 ○가정S/S 7272, 7472 LINE PT 설치 ○기타부대작업","2019-01-24 09:00","2019-01-24 18:00","취소","취소","연속"]
[5,"인천","김포","가정개폐소 345kV #75BUS","7372 모선보호반 시험 및 무부하 가압","○가정S/S 7372 CB 설치 ○가정S/S 7272, 7472 LINE PT 설치 ○기타부대작업","2019-01-21 09:00","2019-01-25 18:00","취소","취소","연속"]
[6,"인천","김포","신가좌 -가정#2 TIE CB (7300)","신부평#2S/S 362kV GIS 설치공사","○가정S/S 7372 CB 설치 ○가정S/S 7272, 7472 LINE PT 설치 ○기타부대작업","2019-01-10 09:00","2019-01-25 18:00","취소","취소","연속"]
[7,"인천","시흥","영흥T/P #3 M.Tr(G.T) 1차 CB (7472)","영흥T/P #3 M.Tr(G.T) 1차 CB[7472] GIS 구조개선","영흥T/P #3 M.Tr(G.T) 1차 CB[7472] GIS 구조개선","2019-01-14 09:30","2019-01-18 18:00","취소","취소","연속"]
[8,"강원","동해","동해S/S 345kV #2 BUS","동해S/S STATCOM용 GIS 설치공사","○ 362kV 6300A 63kA GIS × 2CB ○ 기타부대공사 1식","2019-01-09 14:00","2019-01-10 18:00","취소","취소","연속"]
[9,"강원","동해","동해S/S 345kV #1 BUS","동해S/S STATCOM용 GIS 설치공사","○ 362kV 6300A 63kA GIS × 2CB ○ 기타부대공사 1식","2019-01-09 09:00","2019-01-09 13:30","취소","취소","당일"]
[10,"강원","동해","동해S/S 345kV #2 BUS","동해S/S STATCOM용 GIS 설치공사","○ 362kV 6300A 63kA GIS × 2CB ○ 기타부대공사 1식","2019-01-09 14:00","2019-01-10 18:00","취소","취소","연속"]
[11,"강원","동해","동해S/S 345kV #1 BUS","동해S/S STATCOM용 GIS 설치공사","○ 362kV 6300A 63kA GIS × 2CB ○ 기타부대공사 1식","2019-01-09 09:00","2019-01-09 13:30","취소","취소","당일"]
[12,"충북","직할","신제천S/S 345kV #2 BUS","345kV 신제천S/S SVC 설치공사","345kV SVC 설치 345kV M.Tr 1Bank 설치 362kV GIS 2CB 설치","2019-01-07 10:00","2019-01-08 18:00","2019-01-07 10:00","2019-01-08 18:00","당일"]
[13,"충북","직할","신제천S/S 345kV #2 BUS","345kV 신제천S/S SVC 설치공사","345kV SVC 설치 345kV M.Tr 1Bank 설치 362kV GIS 2CB 설치","2019-01-03 12:00","2019-01-04 18:00","2019-01-03 12:00","2019-01-04 18:00","연속"]
[14,"충북","직할","신제천S/S 345kV #1 BUS","345kV 신제천S/S SVC 설치공사","345kV SVC 설치 345kV M.Tr 1Bank 설치 362kV GIS 2CB 설치","2019-01-03 09:00","2019-01-03 12:00","2019-01-03 09:00","2019-01-03 12:00","연속"]
[15,"대전충남","청양","청양S/S 345kV #75 BUS","청양S/S 345kV PT집합반 설치공사","청양S/S 345kV PT집합반 설치공사(#75BUS)","2019-01-07 14:00","2019-01-07 18:00","취소","취소","당일"]
[16,"대전충남","청양","청양S/S 345kV #76 BUS","청양S/S 345kV PT집합반 설치공사","청양S/S 345kV PT집합반 설치공사(#76BUS)","2019-01-08 14:00","2019-01-08 18:00","취소","취소","당일"]
[17,"대전충남","청양","청양S/S 345kV #71 BUS","청양S/S 345kV PT집합반 설치공사","청양S/S 345kV PT집합반 설치공사(#71BUS)","2019-01-08 08:00","2019-01-08 13:00","취소","취소","당일"]
[18,"대전충남","청양","청양S/S 345kV #70 BUS","청양S/S 345kV PT집합반 설치공사","청양S/S 345kV PT집합반 설치공사(#70BUS)","2019-01-07 08:00","2019-01-07 13:00","취소","취소","당일"]
[19,"전북","군산","군산S/S #1 M.Tr A","군산S/S #1 M.Tr A","군산S/S 345kV 모자익 대체공사","2019-01-07 09:00","2019-01-11 18:00","취소","취소","연속"]
[20,"전북","군산","군산S/S #3 M.Tr A","군산S/S #3 M.Tr A","군산S/S 345kV 모자익 대체공사","2019-01-21 09:00","2019-01-25 18:00","취소","취소","연속"]
[21,"전북","군산","군산S/S #2 M.Tr A","군산S/S #2 M.Tr A","군산S/S 345kV 모자익 대체공사","2019-01-14 09:00","2019-01-18 18:00","취소","취소","연속"]
[22,"전북","군산","군산S/S #4 M.Tr A","군산S/S #4 M.Tr A","군산S/S 345kV 모자익 대체공사","2019-01-28 09:00","2019-02-01 18:00","취소","취소","연속"]
[23,"광주전남","순천","광양S/S #1 M.Tr A","변압기 부싱 절연유 채유","광양S/S #1M.Tr 1,2차 부싱 절연유 채유","2019-01-22 09:00","2019-01-22 17:00","2019-01-22 09:00","2019-01-22 17:00","당일"]
[24,"광주전남","순천","광양S/S #2 M.Tr A","변압기 부싱 절연유 채유","광양S/S #2M.Tr 1,2차 부싱 절연유 채유","2019-01-23 09:00","2019-01-23 17:00","2019-01-23 09:00","2019-01-23 17:00","당일"]
[25,"대구","달성","서대구고령#2 T/L","345kV 고령S/S #1Sh.R 설치공사","ㅇ 345kV Sh.R 1Bank 설치 ㅇ 362kV GIS 3Cb 설치 ㅇ 기타부대공사","2019-01-10 16:00","2019-01-11 16:00","2019-01-20 16:00","2019-01-21 16:00","연속"]
[26,"대구","달성","서대구고령#2 T/L","345kV 고령S/S #1Sh.R 설치공사","ㅇ 345kV Sh.R 1Bank 설치 ㅇ 362kV GIS 3Cb 설치 ㅇ 기타부대공사","2019-01-22 16:00","2019-01-23 16:00","2019-01-28 16:00","2019-01-29 16:00","연속"]
[27,"대구","달성","고령S/S 345kV #2 BUS","345kV 고령S/S #1Sh.R 설치공사","ㅇ 345kV Sh.R 1Bank 설치 ㅇ 362kV GIS 3Cb 설치 ㅇ 기타부대공사","2019-01-14 09:00","2019-01-23 18:00","2019-01-22 09:00","2019-01-29 18:00","연속"]
[28,"대구","달성","고령S/S 345kV #1 BUS","345kV 고령S/S #1Sh.R 설치공사","ㅇ 345kV Sh.R 1Bank 설치 ㅇ 362kV GIS 3Cb 설치 ㅇ 기타부대공사","2019-01-02 09:00","2019-01-11 18:00","2019-01-14 09:00","2019-01-21 18:00","연속"]
[29,"경북","구미","서대구선산#1 T/L","2018-19년도 구미전력지사 가공송전 협력회사 총액공사","ㅇ 항공장애표시구 설치","2019-01-07 07:00","2019-01-09 18:00","취소","취소","매일"]
[30,"경북","구미","선산S/S #1 M.Tr A","선산S/S #1M.Tr OFU 누유개소 하자 보수공사","-#1M.Tr A,B,C 상 OFU 누유개소 하자보수","2019-01-10 09:00","2019-01-11 18:00","2019-01-10 09:00","2019-01-11 18:00","당일"]
[31,"경북","구미","서대구선산#2 T/L","2018-19년도 구미전력지사 가공송전 협력회사 총액공사","ㅇ 항공장애표시구 설치","2019-01-10 07:00","2019-01-12 18:00","취소","취소","매일"]
[32,"경북","영주","한울2NP한울3NP #3T/L","2018-19년도 영주전력지사 변전협력업체 총액공사","한울3발S/Y 7B71, 7B00 CB 보통점검","2019-01-08 09:00","2019-01-08 18:00","2019-01-08 09:00","2019-01-08 18:00","당일"]
[33,"부산울산","동부산","신양산S/S #2 M.Tr A","345kV 신양산S/S 현대화 공사","154kV GIS 붓싱설치 및 기태부대작업(안전이격)","2019-01-10 09:00","2019-01-10 18:00","2019-01-10 09:00","2019-01-10 18:00","당일"]
[34,"부산울산","동부산","신양산S/S #4 M.Tr A","345kV 신양산S/S 현대화 공사","154kV GIS 붓싱설치 및 기태부대작업(안전이격)","2019-01-11 09:00","2019-01-11 18:00","2019-01-11 09:00","2019-01-11 18:00","당일"]
[35,"부산울산","동부산","신양산S/S #1 M.Tr A","345kV 신양산S/S 현대화 공사","154kV GIS 붓싱설치 및 기태부대작업(안전이격)","2019-01-09 09:00","2019-01-09 18:00","2019-01-09 09:00","2019-01-09 18:00","당일"]
[36,"경남","함안","신마산S/S #5M.Tr A","345kV 신마산S/S 용량부족 차단기 대체공사","345kV 신마산S/S 용량부족 차단기 대체공사 인출변경 - #5M.Tr 1차 인출변경 작업","2019-01-08 07:00","2019-01-24 18:00","2019-01-08 07:00","2019-01-24 18:00","연속"]
[37,"경남","함안","신마산삼천포화력#2 T/L","345kV 신마산S/S 용량부족 차단기 대체공사","345kV 신마산S/S 용량부족 차단기 대체공사 - 분리된 신설#1BUS 시험가압 선로","2019-01-11 07:00","2019-01-13 18:00","2019-01-11 07:00","2019-01-13 18:00","연속"]
[38,"경남","함안","신마산삼천포화력#1 T/L","345kV 신마산S/S 용량부족 차단기 대체공사","345kV 신마산S/S 용량부족 차단기 대체공사 - 분리된 신설#2BUS 시험가압 선로","2019-01-19 18:00","2019-01-20 18:00","2019-01-19 18:00","2019-01-20 18:00","연속"]
[39,"경남","함안","신마산S/S 345kV #2 BUS (신설GIS)","345kV 신마산S/S 용량부족 차단기 대체공사","345kV 신마산S/S 용량부족 차단기 대체공사 - 신설#2BUS ~ 기존옥외#2BUS 분리작업","2019-01-18 07:00","2019-01-20 18:00","2019-01-18 07:00","2019-01-20 18:00","연속"]
[40,"경남","함안","신마산S/S 345kV #1 BUS (신설GIS)","345kV 신마산S/S 용량부족 차단기 대체공사","345kV 신마산S/S 용량부족 차단기 대체공사 - 신설#1BUS ~ 기존옥외#1BUS 분리작업","2019-01-11 07:00","2019-01-13 18:00","2019-01-11 07:00","2019-01-13 18:00","연속"]

{"sheet":"154송부","index":3,"n_rows":38,"n_cols":12,"rows_kept":38,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2],[2,11,3,11]]}
["2019년도 1월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","강남","대치S/S 154kV #1 BUS","대치S/S 장기사용GIS 대체공사","154kV 대치-강남#1T/L, #1M.Tr 1차, 6100 BUS TIE GIS 무부하가압","2019-01-18 18:00","2019-01-19 18:00","2019-01-18 18:00","2019-01-19 18:00","연속"]
[2,"남서울","강남","강남대치#2 T/L","대치S/S 장기사용GIS 대체공사","대치S/S 장기사용GIS 대체관련 BUS 절체","2019-01-04 09:00","2019-01-04 10:00","2019-01-19 18:00","2019-01-20 18:00","당일"]
[3,"남서울","강남","강남대치#2 T/L","대치S/S 장기사용GIS 대체공사","154kV #2BUS 무부하가압","2019-01-07 16:00","2019-01-07 18:00","2019-01-21 09:00","2019-01-21 10:00","당일"]
[4,"남서울","강남","강남대치#2 T/L","대치S/S 장기사용GIS 대체공사","대치S/S 장기사용GIS 대체관련 BUS 절체","2019-01-08 09:00","2019-01-08 10:00","2019-01-21 18:00","2019-01-22 18:00","당일"]
[5,"남서울","강남","대치S/S 154kV #1 BUS","대치S/S 장기사용GIS 대체공사","154kV 대치-강남#1T/L, #1M.Tr 1차, 6100 BUS TIE GIS #1DS 설치","2019-01-08 10:00","2019-01-10 18:00","2019-01-08 10:00","2019-01-10 18:00","연속"]
[6,"남서울","강남","강남대치#2 T/L","대치S/S 장기사용GIS 대체공사","154kV #1BUS 무부하가압","2019-01-10 16:00","2019-01-10 18:00","2019-01-25 18:00","2019-01-26 18:00","당일"]
[7,"남서울","강남","대치S/S 154kV #2 BUS","대치S/S 장기사용GIS 대체공사","154kV 대치-강남#1T/L, #1M.Tr 1차, 6100 BUS TIE GIS 무부하가압","2019-01-17 18:00","2019-01-18 18:00","2019-01-25 18:00","2019-01-26 18:00","연속"]
[8,"남서울","강남","대치S/S 154kV #2 BUS","대치S/S 장기사용GIS 대체공사","154kV 대치-강남#1T/L, #1M.Tr 1차, 6100 BUS TIE GIS #2DS 설치","2019-01-04 10:00","2019-01-07 18:00","2019-01-21 10:00","2019-01-22 18:00","연속"]
[9,"남서울","영등포","마곡S/S 154kV #1 BUS","154kV 마곡S/S #4M.Tr 증설공사","154kV M.Tr x 1 bank 170kV GIS x 1 cct 25.8kV SIS x 3 cct","2019-01-14 09:00","2019-01-18 18:00","취소","취소","연속"]
[10,"남서울","영등포","화곡마곡#2 T/L","154kV 마곡S/S #4M.Tr 증설공사","170kV GIS 1CCT 증설 - 무부하가압(24H)","2019-01-24 13:00","2019-01-25 18:00","취소","취소","연속"]
[11,"남서울","영등포","마곡S/S 154kV #2 BUS","154kV 마곡S/S #4M.Tr 증설공사","154kV M.Tr x 1 bank 170kV GIS x 1 cct 25.8kV SIS x 3 cct","2019-01-21 09:00","2019-01-25 18:00","취소","취소","연속"]
[12,"남서울","영등포","화곡마곡#2 T/L","154kV 마곡S/S #4M.Tr 증설공사","170kV GIS 1CCT 증설 - 무부하가압(24H)","2019-01-17 13:00","2019-01-18 18:00","취소","취소","연속"]
[13,"인천","직할","신부평S/S 154kV #65 BUS","신부평-청천S/S SW증설","신부평S/S측 1CCT 증설","2019-01-20 09:00","2019-01-24 18:00","2019-01-20 09:00","2019-01-24 18:00","연속"]
[14,"인천","직할","신부평S/S 154kV #60 BUS","신부평-청천S/S SW증설","신부평S/S측 1CCT 증설","2019-01-15 09:00","2019-01-19 18:00","2019-01-15 09:00","2019-01-19 18:00","연속"]
[15,"경기","평택","고덕S/S 고덕-평택#1T/L CB(697)"," 345kV 고덕E/C 154kV S.W 증설","○ 170kV FIS 4000A 2CCT 설치","2019-01-10 09:00","2019-01-11 18:00","취소","취소","연속"]
[16,"경기","평택","고덕S/S 고덕-평택#2T/L CB(6A7)"," 345kV 고덕E/C 154kV S.W 증설","○ 170kV FIS 4000A 2CCT 설치","2019-01-17 09:00","2019-01-18 18:00","취소","취소","연속"]
[17,"강원","원주","홍천소양강HP T/L","154kV 소양T/L No.84~89간 안전이격 확보공사","- 철탑 철거 4기, 3기 신설","2019-01-21 09:00","2019-01-23 18:00","2019-01-21 09:00","2019-01-23 18:00","연속"]
[18,"강원","직할","홍천남춘천 T/L","154kV 소양T/L No.84~89간 안전이격 확보공사","- 철탑 철거 4기, 3기 신설","2019-01-24 09:00","2019-01-26 18:00","2019-01-24 09:00","2019-01-26 18:00","연속"]
[19,"충북","직할","음성금왕#2 T/L","금왕S/S #5M.Tr 증설공사","#5M.Tr 증설분 무부하 가압","2019-01-15 11:00","2019-01-15 11:00","2019-01-06 10:00","2019-01-06 17:00","연속"]
[20,"전북","김제","정주고창#1 T/L","정주S/S 170kV GIS 설치공사","정주S/S 정주-고창#1T/L 차단기 이설 고창S/S 송전선로 보호배전반 교체","2019-01-21 09:00","2019-01-27 18:00","2019-01-21 09:00","2019-01-27 18:00","연속"]
[21,"광주전남","목포","엄다운남#1 T/L","운남S/S 170kV 장기사용 GIS 대체공사","엄다운남#2T/L GIS 및 BUS-TIE GIS 대체","2019-01-07 09:00","2019-01-24 18:00","2019-01-07 09:00","2019-01-24 18:00","연속"]
[22,"광주전남","목포","운남S/S 154kV #1 BUS TIE CB","운남S/S 170kV 장기사용 GIS 대체공사","엄다운남#2T/L GIS 및 BUS-TIE GIS 대체","2019-01-07 08:00","2019-01-24 18:00","2019-01-07 08:00","2019-01-24 18:00","연속"]
[23,"광주전남","직할","신화순나주#2 T/L","나주S/S 옥내화 관련 인출정비 C/H 설치공사","C/H 6기, LA/LP 11기 설치","2019-01-10 08:00","2019-01-10 18:00","2019-01-12 08:00","2019-01-12 18:00","당일"]
[24,"광주전남","직할","신화순나주#2 T/L","나주S/S 옥내화 관련 인출정비 C/H 설치공사","C/H 6기, LA/LP 11기 설치","2019-01-15 08:00","2019-01-15 18:00","2019-01-19 08:00","2019-01-19 18:00","당일"]
[25,"대구","달성","상인봉덕#1 T/L","달성전력지사 차단기동작특성시험","달성전력지사 차단기동작특성시험","2019-01-07 09:00","2019-01-07 18:00","취소","취소","당일"]
[26,"경북","구미","상주점촌#1 T/L","154kV 상주-점촌T/L 안전이격확보공사","1. 공사목적 설비 노후화(1937년 건설, 81년 경과)로 저지상고에 의한 산불, 안전사고 및 설비고장 예방을 위한 지지물교체를 통한 안전이격 확보 2. 사업지역 : 경북 상주시 함창읍 오동리, 오사리 일원 3. 사업구간 : 18 - 27호간 4. 사업내용 : 철탑교체 8기, 전력선 교체 2.5km","2019-01-24 07:00","2019-01-25 18:00","2019-01-26 07:00","2019-01-27 18:00","연속"]
[27,"경북","구미","상주점촌#2 T/L","154kV 상주-점촌T/L 안전이격확보공사","1. 공사목적 설비 노후화(1937년 건설, 81년 경과)로 저지상고에 의한 산불, 안전사고 및 설비고장 예방을 위한 지지물교체를 통한 안전이격 확보 2. 사업지역 : 경북 상주시 함창읍 오동리, 오사리 일원 3. 사업구간 : 18 - 27호간 4. 사업내용 : 철탑교체 8기, 전력선 교체 2.5km","2019-01-22 07:00","2019-01-23 18:00","2019-01-19 07:00","2019-01-20 18:00","연속"]
[28,"경북","구미","선산청리#1 T/L","2019년도 구미전력지사 변전협력업체 총액공사","- LA보통점검","2019-01-28 09:00","2019-01-28 18:00","2019-01-28 09:00","2019-01-28 18:00","당일"]
[29,"경북","직할","현종산풍력평해#2 T/L","154kV 평해S/S 옥외철구설비 현대화 공사","154kV M.Tr GCB 이설관련 모선정비 - 현종산-평해#2 T/L 및 #6233 GCB Lead Common 작업","2019-01-29 08:00","2019-01-31 18:00","2019-01-29 08:00","2019-01-31 18:00","연속"]
[30,"부산울산","북부산","양산산막#1 T/L","154kV 양산-산막 외1개T/L 인출철탑 정비공사","○ 구 간 : 154㎸ 양산-산막T/L S/T ∼ 2호 ○ 내 용 : 관형지지물(CH) 1호 신설 및 전력선 교체 작업 ※ 안전이격 확보를 위한 양회선 휴전","2019-01-05 07:00","2019-01-11 18:00","2019-01-05 07:00","2019-01-11 18:00","연속"]
[31,"부산울산","북부산","양산산막#2 T/L","154kV 양산-산막 외1개T/L 인출철탑 정비공사","○ 구 간 : 154㎸ 양산-산막T/L S/T ∼ 2호 ○ 내 용 : 관형지지물(CH) 1호 신설 및 전력선 교체 작업 ※ 안전이격 확보를 위한 양회선 휴전","2019-01-05 07:00","2019-01-11 18:00","2019-01-05 07:00","2019-01-11 18:00","연속"]
[32,"경남","함안","신마산칠서#1 T/L","345kV 신마산S/S 차단기 대체관련 가공송전선로 인출변경공사","○ 345kV 신마산-삼천포화력T/L 175~176호 전력선 가선을 위한 안전이격확보","2019-01-01 07:00","2019-01-01 19:00","2019-01-01 07:00","2019-01-01 19:00","당일"]
[33,"경남","함안","신마산S/S 154kV #60 BUS","345kV 신마산S/S 용량부족 차단기 대체공사","345kV 신마산 용량부족 차단기 대체공사 M.Tr 상체크 시행 - #5M.Tr 인출변경에 따른 상체크 시행모선","2019-01-24 15:00","2019-01-24 18:00","2019-01-24 15:00","2019-01-24 18:00","당일"]
[34,"경남","함안","신마산칠서#2 T/L","345kV 신마산S/S 차단기 대체관련 가공송전선로 인출변경공사","○ 345kV 신마산-삼천포화력T/L 175~176호 전력선 가선을 위한 안전이격확보","2019-01-01 07:00","2019-01-01 19:00","2019-01-01 07:00","2019-01-01 19:00","당일"]