{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["종합","765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":13,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"종합","index":0,"n_rows":37,"n_cols":33,"rows_kept":37,"cut":false,"hidden":true,"merged":[[14,14,14,15],[10,1,10,2],[11,1,11,2],[14,9,14,13],[9,1,9,2],[14,2,14,6],[11,3,11,6],[10,3,10,6],[9,3,9,6],[0,0,0,15],[7,14,7,15],[7,1,7,2],[8,1,8,2],[7,9,7,13],[7,3,7,6],[8,3,8,6]]}
[{"$f":"\"'19년 \"&R15&\"월 휴전심의 결과\"","v":"'19년 8월 휴전심의 결과"}]
[]
[]
[]
[]
[]
["◎ 전체 심의결과"]
["전   압","신 청",null,"채 택",null,null,null,"일정\n조정","불채택","(병행/취소/연기)",{"$nulls":4},"연간계획반영(%)"]
["765kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B9-I9","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J9,L9,N9)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O9/B9)","v":{"$error":"#REF!"}}]
["345kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B10-I10","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J10,L10,N10)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O10/B10)","v":{"$error":"#REF!"}}]
["154kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B11-I11","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J11,L11,N11)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O11/B11)","v":{"$error":"#REF!"}}]
["계",{"$f":"SUM(B9:B11)","v":{"$error":"#REF!"}},null,{"$f":"SUM(D9:D11)","v":{"$error":"#REF!"}},null,null,null,{"$f":"SUM(H9:H11)","v":{"$error":"#REF!"}},{"$f":"SUM(J12,L12,N12)","v":{"$error":"#REF!"}},{"$f":"SUM(J9:J11)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(L9:L11)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(N9:N11)","v":{"$error":"#REF!"}},{"$f":"SUM(O9:O11)","v":{"$error":"#REF!"}},{"$f":"(O12/B12)","v":{"$error":"#REF!"}}]
[]
["◎ 본부별 심의결과",{"$nulls":16},"월"]
["사업소","신 청","(765/345/154)",{"$nulls":4},"채 택","불채택","(병행/취소/연기)",{"$nulls":4},"연간계획반영(%)",null,null,8]
["서   울",{"$f":"SUM(C16:G16)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},{"$f":"B16-I16","v":{"$error":"#REF!"}},{"$f":"SUM(J16,L16,N16)","v":{"$error":"#REF!"}},{"$f":"SUM(S16:U16)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(W16:Y16)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA16:AC16)","v":{"$error":"#REF!"}},{"$f":"SUM(AE16:AG16)","v":{"$error":"#REF!"}},{"$f":"(O16/B16)","v":{"$error":"#REF!"}},null,"서울",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}}]
["남서울",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$f":"SUM(J17,L17,N17)","v":{"$error":"#REF!"}},{"$f":"SUM(S17:U17)","v":{"$error":"#REF!"}},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"남서울",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}}]
["인   천",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"인천",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}}]
["경기북부",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경기북부",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}}]
["경   기",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경기",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}}]
["강   원",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"강원",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}}]
["충   북",{"$f":"SUM(C22:G22)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"충북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}}]
["대전충남",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"대전충남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}}]
["전   북",{"$f":"SUM(C24:G24)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"전북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}}]
["광주전남",{"$f":"SUM(C25:G25)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"광주전남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}}]
["대구",{"$f":"SUM(C26:G26)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},{"$f":"B26-I26","v":{"$error":"#REF!"}},{"$f":"SUM(J26,L26,N26)","v":{"$error":"#REF!"}},{"$f":"SUM(S26:U26)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(W26:Y26)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA26:AC26)","v":{"$error":"#REF!"}},{"$f":"SUM(AE26:AG26)","v":{"$error":"#REF!"}},{"$f":"(O26/B26)","v":{"$error":"#REF!"}},null,"대구",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}}]
["경북",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}}]
["부산울산",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"부산울산",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}}]
["경   남",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$f":"SUM(W29:Y29)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA29:AC29)","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},null,"경남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}}]
["제   주",{"$f":"SUM(C30:G30)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$f":"(O30/B30)","v":{"$error":"#REF!"}},null,"제주",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}}]
[]
[" 붙임 :  1. 집중심의내역 1부"]
[" 붙임 :  전압별 검토서 1부. 끝."]
[]
[null,{"$f":"SUM(B16:B30)","v":{"$error":"#REF!"}},{"$f":"SUM(C16:C30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(E16:E30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(G16:G30)","v":{"$error":"#REF!"}},{"$f":"SUM(H16:H30)","v":{"$error":"#REF!"}},{"$f":"SUM(I16:I30)","v":{"$error":"#REF!"}},{"$f":"SUM(J16:J30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(L16:L30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(N16:N30)","v":{"$error":"#REF!"}},{"$f":"SUM(O16:O30)","v":{"$error":"#REF!"}}]
[{"$f":"COUNTIF(B36:N36,\"NO\")","v":0},{"$f":"IF(B35=B12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(C35=B9,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(E35=B10,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(G35=B11,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(H35=D12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(I35=I12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(J35=J12,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(L35=L12,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(N35=N12,\"\",\"NO\")","v":{"$error":"#REF!"}}]
[{"$f":"IF(A36>=1,\"틀린곳\",\"\")","v":""},{"$f":"IF(B36=\"NO\",\"총계\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C36=\"NO\",\"765\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(D36=\"NO\",\"총계\",\"\")","v":""},{"$f":"IF(E36=\"NO\",\"345\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(G36=\"NO\",\"154\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(H36=\"NO\",\"채택\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(I36=\"NO\",\"불채택\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(J36=\"NO\",\"병행\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(L36=\"NO\",\"취소\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(N36=\"NO\",\"연기\",\"\")","v":{"$error":"#REF!"}}]

{"sheet":"765송부","index":1,"n_rows":8,"n_cols":17,"rows_kept":8,"cut":false,"hidden":false,"merged":[[2,16,3,16],[2,15,3,15],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,14,3,14],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 8월 휴전계획서"}]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부","계통안정 사유"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"대전충남","서산","신서산당진TP#1 T/L","신서산S/S 765kV 효성제 HSGS 조작불량 점검","- 신서산S/S 765kV 신서산-당진화력1TL HSGS 조작불량 점검","2019-08-19 09:00","2019-08-19 18:00","취소","취소","당일"]
[2,"대전충남","서산","신서산당진TP#2 T/L","신서산S/S 765kV 효성제 HSGS 조작불량 점검","- 신서산S/S 765kV 신서산-당진화력2TL HSGS 조작불량 점검","2019-08-20 09:00","2019-08-20 18:00","취소","취소","당일"]
[3,"부산울산","동부산","신고리S/S #3 Tie-Tr A-1","고리NP S/Y 362kV GIS 정밀점검관련 시험가압","고리NP S/Y 362kV 7600,7672GIS 정밀점검관련 시험가압(#3M.Tr)","2019-08-30 18:00","2019-08-31 18:00","2019-08-30 18:00","2019-08-31 18:00","연속"]
[4,"부산울산",null,"고리1호기 주변압기 CB(8400,8472)","1호기 5차 계획예방정비\n*조작차단기 : PCB 8400, 8472","○ 소내 전원절체(UAT -> SAT) 시험 후 차단기 재투입","2019-08-09 09:00","2019-08-09 18:00","2019-08-09 09:00","2019-08-09 18:00","연속"]

{"sheet":"345송부","index":2,"n_rows":50,"n_cols":17,"rows_kept":50,"cut":false,"hidden":false,"merged":[[2,16,3,16],[2,15,3,15],[2,14,3,14],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 8월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부","계통안정 사유"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","미금S/S 345kV #2 Sh.R","미금S/S 345kV Sh.R 보호반 교체공사","미금S/S 345kV Sh.R 보호반 교체공사","2019-08-12 09:00","2019-08-16 18:00","취소","취소","연속"]
[2,"경기북부","구리","미금S/S 345kV #1 Sh.R","미금S/S 345kV Sh.R 보호반 교체공사","미금S/S 345kV Sh.R 보호반 교체공사","2019-08-12 09:00","2019-08-16 18:00","취소","취소","연속"]
[3,"경기북부","구리","미금S/S 345kV #6 Sh.R","미금S/S 345kV 72Bay B/F반 교체공사","미금S/S 345kV 72Bay B/F반 교체공사","2019-08-05 09:00","2019-08-09 18:00","취소","취소","연속"]
[4,"경기북부","구리","미금성동#2 T/L","미금S/S 345kV 72Bay B/F반 교체공사","미금S/S 345kV 72Bay B/F반 교체공사","2019-08-05 09:00","2019-08-09 18:00","취소","취소","연속"]
[5,"경기북부","구리","미금S/S 345kV #3 Sh.R","미금S/S 345kV 72Bay B/F반 교체공사","미금S/S 345kV 72Bay B/F반 교체공사","2019-08-05 09:00","2019-08-09 18:00","취소","취소","연속"]
[6,"경기북부","구리","미금S/S 345kV #4 Sh.R","미금S/S 345kV 72Bay B/F반 교체공사","미금S/S 345kV 72Bay B/F반 교체공사","2019-08-05 09:00","2019-08-09 18:00","취소","취소","연속"]
[7,"경기북부","구리","미금S/S 345kV #1 BUS Sh.R MAIN GIS","미금S/S 345kV Sh.R 보호반 교체공사","미금S/S 345kV Sh.R 보호반 교체공사","2019-08-12 09:00","2019-08-16 18:00","취소","취소","연속"]
[8,"경기북부","구리","미금S/S 345kV #5 Sh.R","미금S/S 345kV Sh.R 보호반 교체공사","미금S/S 345kV Sh.R 보호반 교체공사","2019-08-12 09:00","2019-08-16 18:00","취소","취소","연속"]
[9,"전북","군산","군산S/S #2 M.Tr","군산P/O 170kV GIS 정밀점검공사","군산S/S 170kV #2M.Tr 2차 GIS 정밀점검공사","2019-08-28 09:00","2019-08-29 18:00","2019-08-28 09:00","2019-08-29 18:00","연속"]
[10,"전북","군산","군산S/S #1 M.Tr","군산P/O 170kV GIS 정밀점검공사","군산S/S 170kV #1M.TR 2차 GIS 정밀점검공사","2019-08-26 09:00","2019-08-27 18:00","2019-08-26 09:00","2019-08-27 18:00","연속"]
[11,"전북","직할","신옥천신남원#1 T/L","보호배전반 통신이상관련 광케이블 교체공사","1. 345kV 신옥천-신남원T/L 보호배전반 4면 광케이블로 교체","2019-08-01 10:00","2019-08-01 18:00","2019-08-01 10:00","2019-08-01 18:00","당일"]
[12,"전북","직할","신옥천신남원#2 T/L","보호배전반 통신이상관련 광케이블 교체공사","1. 345kV 신옥천-신남원T/L 보호배전반 4면 광케이블로 교체","2019-08-02 10:00","2019-08-02 18:00","2019-08-02 10:00","2019-08-02 18:00","당일"]
[13,"대구","달성","고령S/S #3 M.Tr","고령S/S 76B/F 대체작업","고령S/S 76B/F 대체작업","2019-08-26 09:00","2019-08-30 18:00","취소","취소","연속"]
[14,"대구","달성","서대구고령#1 T/L","고령S/S 76B/F 대체작업","고령S/S 76B/F 대체작업","2019-08-26 09:00","2019-08-30 18:00","취소","취소","연속"]
[15,"대구","포항","신월성N/P 345kV #2 SA.TR 1차 CB A (7272-A)","신월성 7272 GIS 보통점검","신월성 7272 GIS 보통점검","2019-08-06 09:30","2019-08-06 18:00","2019-08-06 09:30","2019-08-06 18:00","당일"]
[16,"대구","포항","월성연락#2 T/L","월성-연락#2T/L 휴전","신월성 7200,7271 GIS 보통점검 월성 7871 조작시험 LCR, DS 보통점검","2019-08-07 09:30","2019-08-08 18:00","2019-08-07 09:30","2019-08-08 18:00","연속"]
[17,"경북","구미","서대구선산#2 T/L","2019년 가공송전 순시점검 위탁공사","345kV 서대구-선산#1,2T/L 북대구-선산 및 선산-신포항T/L - 현수애자 절연성능진단 시행결과 현수애자 불량의심개소 발견 - 휴전 후 절연저항 측정 후 애자 교체작업 시행 - 345kV 서대구-선산#1T/L : 10장, 서대구-선산#2T/L : 10장 - 345kV 북대구-선산T/L : 2장, 선산-신포항T/L : 1장","2019-08-22 09:00","2019-08-26 18:00","취소","취소","매일"]
[18,"경북","구미","서대구선산#1 T/L","2019년 가공송전 순시점검 위탁공사","345kV 서대구-선산#1,2T/L 북대구-선산 및 선산-신포항T/L - 현수애자 절연성능진단 시행결과 현수애자 불량의심개소 발견 - 휴전 후 절연저항 측정 후 애자 교체작업 시행 - 345kV 서대구-선산#1T/L : 10장, 서대구-선산#2T/L : 10장 - 345kV 북대구-선산T/L : 2장, 선산-신포항T/L : 1장","2019-08-19 09:00","2019-08-21 18:00","취소","취소","매일"]
[19,"경북","구미","북대구선산 T/L","2019년 가공송전 순시점검 위탁공사","345kV 서대구-선산#1,2T/L 북대구-선산 및 선산-신포항T/L - 현수애자 절연성능진단 시행결과 현수애자 불량의심개소 발견 - 휴전 후 절연저항 측정 후 애자 교체작업 시행 - 345kV 서대구-선산#1T/L : 10장, 서대구-선산#2T/L : 10장 - 345kV 북대구-선산T/L : 2장, 선산-신포항T/L : 1장","2019-08-21 09:00","2019-08-21 18:00","취소","취소","당일"]
[20,"경북","구미","선산신포항 T/L","2019년 가공송전 순시점검 위탁공사","345kV 서대구-선산#1,2T/L 북대구-선산 및 선산-신포항T/L - 현수애자 절연성능진단 시행결과 현수애자 불량의심개소 발견 - 휴전 후 절연저항 측정 후 애자 교체작업 시행 - 345kV 서대구-선산#1T/L : 10장, 서대구-선산#2T/L : 10장 - 345kV 북대구-선산T/L : 2장, 선산-신포항T/L : 1장","2019-08-26 09:00","2019-08-26 18:00","취소","취소","당일"]
[21,"경북","영주","신영주한울NP2#2 T/L","345kV 신영주S/S TCSC 설치공사","- TCSC 555.28MVar × 2조 설치 - 신영주S/S 신영주-한울NP2 #2T/L 송전선로보호반 개조 × 1식 - 신영주S/S 신영주-한울NP2 #2T/L GIB용 보호반 설치","2019-08-12 10:00","2019-08-16 15:00","취소","취소","연속"]
[22,"경북","영주","신영주한울NP2#1 T/L","345kV 신영주S/S TCSC 설치공사","- TCSC 555.28MVar × 2조 설치 - 신영주S/S 신영주-한울NP2 #1T/L 송전선로보호반 개조 × 1식 - 신영주S/S 신영주-한울NP2 #1T/L GIB용 보호반 설치","2019-08-05 10:00","2019-08-09 15:00","취소","취소","연속"]
[23,"경북","영주","한울#3N/P 신한울연락#2T/L-#5 SA.Tr 2차 TIE CB (7E00)","2018-19년도 영주전력지사 변전협력업체 총액공사","한울3발S/Y 7E00CB 하자점검","2019-08-29 14:00","2019-08-29 18:00","2019-08-29 14:00","2019-08-29 18:00","당일"]
[24,"경북","영주","한울#3N/P 신한울연락#2T/L CB (7E71)","2018-19년도 영주전력지사 변전협력업체 총액공사","한울3발S/Y 7E71CB 하자점검","2019-08-29 09:00","2019-08-29 14:00","2019-08-29 09:00","2019-08-29 14:00","당일"]
[25,"경북","영주","한울#3N/P #5 SA.Tr 2차 CB (7E72)","2018-19년도 영주전력지사 변전협력업체 총액공사","한울3발S/Y 7E72CB 하자점검","2019-08-30 09:00","2019-08-30 15:00","2019-08-30 09:00","2019-08-30 15:00","당일"]
[26,"부산울산","동부산","고리2N/P 345kV #76 BUS","고리NP S/Y 362kV GIS 정밀점검관련 시험가압","고리NP S/Y 362kV 7600,7672GIS 정밀점검관련 시험가압(#76BUS)","2019-08-30 18:00","2019-08-31 18:00","2019-08-30 18:00","2019-08-31 18:00","연속"]
[27,"경남","통영","고성하이S/Y 고성하이-삼천포화력#2T/L CB (7171)","345kV 고성하이S/Y 건설공사 가압","무부하가압 : 8.22. 14:00 ~ 8.23. 14:00 사용전검사 : 8.26 ~ 8.30 실부하가압 : 8.29 14:00 ~ 18:00","2019-08-22 14:00","2019-08-29 18:00","취소","취소","연속"]
[28,"경남","통영","고성하이S/Y 고성하이-삼천포화력#1T/L CB (7271)","345kV 고성하이S/Y 건설공사 가압","무부하가압 : 8.22. 14:00 ~ 8.23. 14:00 사용전검사 : 8.26 ~ 8.30 실부하가압 : 8.29 14:00 ~ 18:00","2019-08-22 14:00","2019-08-29 18:00","취소","취소","연속"]
[29,"경남","통영","고성하이S/Y G1호기 1차 CB (7172)","345kV 고성하이S/Y 건설공사 가압","무부하가압 : 8.22. 14:00 ~ 8.23. 14:00 사용전검사 : 8.26 ~ 8.30 실부하가압 : 8.29 14:00 ~ 18:00","2019-08-22 14:00","2019-08-29 18:00","취소","취소","연속"]
[30,"경남","통영","고성하이S/Y 삼천포화력#2T/L-G1호기 CB (7100)","345kV 고성하이S/Y 건설공사 가압","무부하가압 : 8.22. 14:00 ~ 8.23. 14:00 사용전검사 : 8.26 ~ 8.30 실부하가압 : 8.29 14:00 ~ 18:00","2019-08-22 14:00","2019-08-29 18:00","취소","취소","연속"]
[31,"경남","통영","고성하이S/Y 삼천포화력#1T/L-G2호기 CB (7200)","345kV 고성하이S/Y 건설공사 가압","무부하가압 : 8.22. 14:00 ~ 8.23. 14:00 사용전검사 : 8.26 ~ 8.30 실부하가압 : 8.29 14:00 ~ 18:00","2019-08-22 14:00","2019-08-29 18:00","취소","취소","연속"]
[32,"경남","통영","고성하이S/Y 345kV #75 BUS CB","345kV 고성하이S/Y 건설공사 가압","무부하가압 : 8.22. 14:00 ~ 8.23. 14:00 사용전검사 : 8.26 ~ 8.30 실부하가압 : 8.29 14:00 ~ 18:00","2019-08-22 14:00","2019-08-29 18:00","취소","취소","연속"]
[33,"경남","통영","고성하이S/Y G2호기 1차 CB (7272)","345kV 고성하이S/Y 건설공사 가압","무부하가압 : 8.22. 14:00 ~ 8.23. 14:00 사용전검사 : 8.26 ~ 8.30 실부하가압 : 8.29 14:00 ~ 18:00","2019-08-22 14:00","2019-08-29 18:00","취소","취소","연속"]
[34,"경남","통영","고성하이S/Y 345kV #70 BUS CB","345kV 고성하이S/Y 건설공사 가압","무부하가압 : 8.22. 14:00 ~ 8.23. 14:00 사용전검사 : 8.26 ~ 8.30 실부하가압 : 8.29 14:00 ~ 18:00","2019-08-22 14:00","2019-08-29 18:00","취소","취소","연속"]
[35,"경남","통영","고성하이T/P삼천포TP#1 T/L CB","삼천포,신고성S/S 용량부족차단기 대체공사","-모선보호 구간 확장 작업 복귀 -고성하이T/L 보호계전기 정정 및 연동시험 -고성하이S/Y 무부하시험 가압 및 본가압","2019-08-05 09:00","2019-08-29 18:00","2019-08-05 09:00","2019-08-29 18:00","연속"]
[36,"경남","통영","고성하이T/P삼천포TP#2 T/L CB","삼천포,신고성S/S 용량부족차단기 대체공사","-모선보호 구간 확장 작업 복귀 -고성하이T/L 보호계전기 정정 및 연동시험 -고성하이S/Y 무부하시험 가압 및 본가압","2019-08-05 09:00","2019-08-29 18:00","2019-08-05 09:00","2019-08-29 18:00","연속"]
[37,"경남","통영","삼천포T/P 삼천포-TIE#1T/L CB (7272)","삼천포,신고성S/S 용량부족차단기 대체공사","고성하이화력S/Y 무부하시험 가압","2019-08-22 14:00","2019-08-23 14:00","2019-08-22 14:00","2019-08-23 14:00","연속"]
[38,"경남","통영","삼천포T/P TIE#1T/L-#2 G.Tr TIE CB(7200)","삼천포,신고성S/S 용량부족차단기 대체공사","고성하이화력S/Y 무부하시험가압","2019-08-22 14:00","2019-08-23 14:00","2019-08-22 14:00","2019-08-23 14:00","연속"]
[39,"경남","통영","삼천포T/P 삼천포-TIE#1T/L CB (7272)","삼천포,신고성S/S 용량부족차단기 대체공사","고성하이화력S/Y 실부하 위상측정","2019-08-29 14:00","2019-08-29 18:00","2019-08-29 14:00","2019-08-29 18:00","당일"]
[40,"경남","통영","삼천포T/P TIE#1T/L-#2 G.Tr TIE CB(7200)","삼천포,신고성S/S 용량부족차단기 대체공사","고성하이화력S/Y 실부하 위상측정","2019-08-29 14:00","2019-08-29 18:00","2019-08-29 14:00","2019-08-29 18:00","당일"]
[41,"경남","통영","(신)신고성S/S 삼천포-TIE#1T/L CB (7A72)","삼천포,신고성S/S 용량부족차단기 대체공사","고성하이화력S/Y 무부하시험 가압","2019-08-22 14:00","2019-08-23 14:00","2019-08-22 14:00","2019-08-23 14:00","연속"]
[42,"경남","통영","(신)신고성S/S 삼천포-TIE#1T/L CB (7A72)","삼천포,신고성S/S 용량부족차단기 대체공사","고성하이화력S/Y 실부하 위상측정","2019-08-29 14:00","2019-08-29 18:00","2019-08-29 14:00","2019-08-29 18:00","당일"]
[43,"경남","통영","(신)신고성S/S 삼천포#1T/L-고성하이 CB(7A00)","삼천포,신고성S/S 용량부족차단기 대체공사","고성하이화력S/Y 실부하 위상체크","2019-08-29 14:00","2019-08-29 18:00","2019-08-29 14:00","2019-08-29 18:00","당일"]
[44,"경남","통영","(신)신고성S/S 삼천포#1T/L-고성하이 CB(7A00)","삼천포,신고성S/S 용량부족차단기 대체공사","고성하이화력S/Y 무부하시험가압","2019-08-22 14:00","2019-08-23 14:00","2019-08-22 14:00","2019-08-23 14:00","연속"]
[45,"대구",null,"신월성2호기 대기보조변압기 CB(7200,7272)","신월성2호기 3차 계획예방정비\n#2 대기보조변압기(SAT) 점검\n* 조작차단기 : CB 7200, 7272","○ SAT 일반점검 등","2019-08-06 09:00","2019-08-22 18:00","2019-08-06 09:00","2019-08-22 18:00","연속"]
[46,"대구",null,"신월성2호기 주변압기 CB(7100,7172)","신월성 2호기 3차 계획예방정비\n# 소내전원절체시험 \n* 조작차단기 : CB 7100, 7172","○ 소내전원절체시험시 주변압기 \n   모의 보호신호에 의한 PCB개방","2019-08-23 09:00","2019-08-24 18:00","2019-08-23 09:00","2019-08-24 18:00","연속"]

{"sheet":"154송부","index":3,"n_rows":36,"n_cols":17,"rows_kept":36,"cut":false,"hidden":false,"merged":[[2,16,3,16],[2,15,3,15],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,14,3,14],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 8월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부","계통안정 사유"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","고양","신파주문발#2 T/L","파주운정3지구 지장송전선로 지중화공사","- 공사구간 : 154kV 신파주-문발#1,2T/L J/B#1∼#6 2.012km - 선종 및 선로길이 : XLPE 2500㎟×2C 0.801km / XLPE 2000㎟(D)×2C 1.211km","2019-08-23 08:00","2019-10-01 18:00","2019-08-23 08:00","2019-10-01 18:00","연속"]
[2,"경기북부","구리","신장덕소#2 T/L","154㎸ 덕소S/S 옥내화관련 지중T/L 건설공사","154kV 덕소S/S 옥내화공사 시행에 따른 관련 지중T/L 정비사업, 154kV 신장-덕소#2T/L 휴전작업으로 신설 덕소S/S 계통병입 및 부하절체","2019-08-09 09:00","2019-09-07 18:00","2019-08-09 09:00","2019-09-07 18:00","연속"]
[3,"경기북부","직할","양주불광#1 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주불광#1 T/L 인출측 전력구공사","2019-08-31 09:00","2019-08-31 18:00","2019-08-31 09:00","2019-08-31 18:00","연속"]
[4,"경기북부","직할","양주은평#1 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주은평#1 T/L 인출측 전력구공사","2019-08-29 09:00","2019-08-30 18:00","2019-08-29 09:00","2019-08-30 18:00","연속"]
[5,"경기북부","직할","양주은평#2 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주은평#2 T/L 인출측 전력구공사","2019-08-27 09:00","2019-08-28 18:00","2019-08-27 09:00","2019-08-28 18:00","연속"]
[6,"경기북부","직할","양주고양#1 T/L","양주S/S옥외철구 GIS화 전력구공사","양주고양#1 T/L 인출측 전력구공사","2019-08-24 09:00","2019-08-24 18:00","2019-08-24 09:00","2019-08-24 18:00","연속"]
[7,"경기북부","직할","양주불광#2 T/L","양주S/S 옥외철구 GIS화 전력구공사(양주S/S현대화)","양주불광#2 T/L 인출측 전력구공사","2019-08-25 09:00","2019-08-25 18:00","2019-08-25 09:00","2019-08-25 18:00","연속"]
[8,"경기","평택","고덕진위#2 T/L","154kV 고덕-삼성 #3,4T/L 증설","154kV GIS 2CCT 증설 무부하 가압","2019-08-26 14:00","2019-08-27 14:00","2019-08-26 14:00","2019-08-27 14:00","연속"]
[9,"경기","평택","고덕진위#2 T/L","154kV 고덕-진위 30호 지장철탑 이설공사","남사나들목 개설 관련 30호 지장이설 2기 신설, 1기 철거","2019-08-18 07:00","2019-08-21 18:00","2019-08-18 07:00","2019-08-21 18:00","연속"]
[10,"경기","평택","고덕진위#1 T/L","154kV 고덕-진위 30호 지장철탑 이설공사","남사나들목 개설 관련 30호 지장이설 2기 신설, 1기 철거","2019-08-22 07:00","2019-08-25 18:00","2019-08-22 07:00","2019-08-25 18:00","연속"]
[11,"강원","강릉","동해영동TP T/L","154kV 강릉T/L No.7~7.1간 지장송전선로 지중화공사","154kV 강릉T/L No.7~7.1간 본선로 구성 - CH철탑 설치 2기, 지중케이블 포설 및 접속(No.7~7.1간)","2019-08-01 09:00","2019-08-05 18:00","2019-08-01 09:00","2019-08-05 18:00","연속"]
[12,"강원","강릉","강릉영동TP T/L","154kV 강릉T/L No.7~7.1간 지장송전선로 지중화공사","154kV 강릉T/L No.7~7.1간 본선로 구성 - CH철탑 설치 2기, 지중케이블 포설 및 접속(No.7~7.1간)","2019-08-01 09:00","2019-08-05 18:00","2019-08-01 09:00","2019-08-05 18:00","연속"]
[13,"강원","직할","가평춘천HP T/L","154kV 화천T/L No.65~69 안전이격확보공사","No.65~69 철탑교체(5기), 전력선 2.132km 교체","2019-08-26 09:00","2019-09-08 18:00","취소","취소","연속"]
[14,"강원","직할","가평화천HP T/L","154kV 화천T/L No.65~69 안전이격확보공사","No.65~69 철탑교체(5기), 전력선 2.132km 교체","2019-08-26 09:00","2019-09-08 18:00","취소","취소","연속"]
[15,"강원","직할","양구화천HP#1 T/L","유압조작부 누유관련 제작사 하자보수","유압력계 교체 및 부대공사","2019-08-20 10:00","2019-08-20 14:00","2019-08-20 10:00","2019-08-20 14:00","당일"]
[16,"강원","직할","양구화천HP#2 T/L","유압조작부 누유관련 제작사 하자보수","유압력계 교체 및 부대공사","2019-08-20 14:00","2019-08-20 18:00","2019-08-20 14:00","2019-08-20 18:00","당일"]
[17,"전북","군산","군산S/S 154kV #66 BUS","군산P/O 170kV GIS 정밀점검공사","군산S/S 170kV #2M.Tr 2차 GIS 정밀점검공사 (군산-동군산#1T/L 활용 무부하 가압)","2019-08-29 15:00","2019-08-29 17:00","2019-08-29 15:00","2019-08-29 17:00","연속"]
[18,"전북","군산","군산S/S 154kV #60 BUS","군산P/O 170kV GIS 정밀점검공사","군산S/S 170kV #1M.TR 2차 GIS 정밀점검공사 (군산-이리#1T/L 활용 무부하 가압)","2019-08-27 15:00","2019-08-27 17:00","2019-08-27 15:00","2019-08-27 17:00","당일"]
[19,"전북","군산","군산S/S 154kV 군산-동군산#1T/L GIS","군산P/O 170kV GIS 정밀점검공사","군산S/S 170kV #2M.Tr 2차 GIS 정밀점검공사 (군산-동군산#1T/L 활용 무부하 가압)","2019-08-29 15:00","2019-08-29 17:00","2019-08-29 15:00","2019-08-29 17:00","연속"]
[20,"전북","군산","군산S/S 154kV 군산-이리#1T/L GIS","군산P/O 170kV GIS 정밀점검공사","군산S/S 170kV #1M.TR 2차 GIS 정밀점검공사 (군산-이리#1T/L 활용 무부하 가압)","2019-08-27 15:00","2019-08-27 17:00","2019-08-27 15:00","2019-08-27 17:00","당일"]
[21,"전북","군산","군산서군산#1 T/L","서군산S/S 현대화관련 부지확보공사","서군산S/S 현대화관련 부지확보공사(무부하가압용)","2019-08-31 09:00","2019-09-01 18:00","2019-08-31 09:00","2019-09-01 18:00","연속"]
[22,"광주전남","강진","신강진대불#1 T/L","154kV 인출선로 모선재배열공사(신강진S/S)","가. 공사장소 : 신강진S/S 154kV 인출선로 나. 휴전선로 : 154kV 신강진-강진#2T/L, 신강진-대불#1T/L 다. 작업내용 - 인출선로 모선 재배열을 위한 선로 재배열공사 - 선종/길이 : 신강진-대불#1T/L(XLPE 2000SQ X 1C(D) X 0.12km) 신강진-강진#2T/L(XLPE","2019-08-18 09:00","2019-08-18 18:00","2019-08-18 09:00","2019-08-18 18:00","당일"]
[23,"광주전남","강진","신강진대불#1 T/L","154kV 인출선로 모선 재배열공사(신강진)","가. 공사장소 : 신강진S/S 154kV 인출선로 나. 휴전선로 : 154kV 신강진-강진#2T/L, 신강진-대불#1T/L 다. 작업내용 - 인출선로 모선 재배열을 위한 선로 재배열공사 - 선종/길이 : 신강진-대불#1T/L(XLPE 2000SQ X 1C(D) X 0.12km) 신강진-강진#2T/L(XLPE","2019-08-31 09:00","2019-08-31 12:00","2019-08-31 09:00","2019-08-31 12:00","연속"]
[24,"광주전남","강진","신강진대불#1 T/L","154kV 인출선로 모선 재배열공사(신강진)","가. 공사장소 : 신강진S/S 154kV 인출선로 나. 휴전선로 : 154kV 신강진-강진#2T/L, 신강진-대불#1T/L 다. 작업내용 - 인출선로 모선 재배열을 위한 선로 재배열공사 - 선종/길이 : 신강진-대불#1T/L(XLPE 2000SQ X 1C(D) X 0.12km) 신강진-강진#2T/L(XLPE 2000SQ X 1C(D) X 0.12km) - 접속 : EB-G 4개소, EB-A 4개소","2019-08-03 09:00","2019-08-06 18:00","2019-08-03 09:00","2019-08-06 18:00","연속"]
[25,"광주전남","광주","신광주곡성#1 T/L","154kV 인출선로 모선 재배열공사(신광주)","○ (345kV)신광주S/S 154kV 인출선로 모선 재배열공사 - Sec(60-65)→Sec(61-66) 변경 : 154kV 신광주-장성#2 T/L (XLPE 2000㎟ × 1C(D) × 0.06km) - Sec(61-66)→Sec(60-65) 변경 : 154kV 신광주-곡성#1 T/L (XLPE 2000㎟ × 1C × 0.06km)","2019-08-19 09:00","2019-09-25 18:00","취소","취소","연속"]
[26,"광주전남","목포","영광백수풍력#1 T/L CB","`19년 변전정비회사 총액공사(영광SS 백수풍력T/L 보통점검)","`19년 변전정비회사 총액공사(영광SS 백수풍력T/L 보통점검)","2019-08-20 10:00","2019-08-20 18:00","2019-08-20 10:00","2019-08-20 18:00","당일"]
[27,"대구","달성","대구봉덕#2 T/L","대구S/S 대구-봉덕#2T/L 보호반대체","대구S/S 대구-봉덕#2T/L 보호반대체","2019-08-29 09:00","2019-08-30 18:00","2019-08-29 09:00","2019-08-30 18:00","연속"]
[28,"경남","직할","완암안민#2 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-08-10 07:00","2019-08-14 18:00","취소","취소","연속"]
[29,"경남","직할","창원완암#2 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-08-07 07:00","2019-08-09 18:00","취소","취소","연속"]
[30,"경남","직할","창원완암#1 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-08-07 07:00","2019-08-12 18:00","취소","취소","연속"]
[31,"경남","직할","완암안민#1 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-08-10 07:00","2019-08-12 18:00","취소","취소","연속"]
[32,"경남","직할","창원완암#2 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-08-13 07:00","2019-08-14 18:00","취소","취소","연속"]