{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["종합","765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":13,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"종합","index":0,"n_rows":37,"n_cols":33,"rows_kept":37,"cut":false,"hidden":true,"merged":[[0,0,0,15],[7,14,7,15],[7,1,7,2],[8,1,8,2],[7,9,7,13],[7,3,7,6],[8,3,8,6],[14,14,14,15],[10,1,10,2],[11,1,11,2],[14,9,14,13],[9,1,9,2],[14,2,14,6],[11,3,11,6],[10,3,10,6],[9,3,9,6]]}
[{"$f":"\"'19년 \"&R15&\"월 휴전심의 결과\"","v":"'19년 10월 휴전심의 결과"}]
[]
[]
[]
[]
[]
["◎ 전체 심의결과"]
["전   압","신 청",null,"채 택",null,null,null,"일정\n조정","불채택","(병행/취소/연기)",{"$nulls":4},"연간계획반영(%)"]
["765kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B9-I9","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J9,L9,N9)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O9/B9)","v":{"$error":"#REF!"}}]
["345kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B10-I10","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J10,L10,N10)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O10/B10)","v":{"$error":"#REF!"}}]
["154kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B11-I11","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J11,L11,N11)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O11/B11)","v":{"$error":"#REF!"}}]
["계",{"$f":"SUM(B9:B11)","v":{"$error":"#REF!"}},null,{"$f":"SUM(D9:D11)","v":{"$error":"#REF!"}},null,null,null,{"$f":"SUM(H9:H11)","v":{"$error":"#REF!"}},{"$f":"SUM(J12,L12,N12)","v":{"$error":"#REF!"}},{"$f":"SUM(J9:J11)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(L9:L11)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(N9:N11)","v":{"$error":"#REF!"}},{"$f":"SUM(O9:O11)","v":{"$error":"#REF!"}},{"$f":"(O12/B12)","v":{"$error":"#REF!"}}]
[]
["◎ 본부별 심의결과",{"$nulls":16},"월"]
["사업소","신 청","(765/345/154)",{"$nulls":4},"채 택","불채택","(병행/취소/연기)",{"$nulls":4},"연간계획반영(%)",null,null,10]
["서   울",{"$f":"SUM(C16:G16)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},{"$f":"B16-I16","v":{"$error":"#REF!"}},{"$f":"SUM(J16,L16,N16)","v":{"$error":"#REF!"}},{"$f":"SUM(S16:U16)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(W16:Y16)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA16:AC16)","v":{"$error":"#REF!"}},{"$f":"SUM(AE16:AG16)","v":{"$error":"#REF!"}},{"$f":"(O16/B16)","v":{"$error":"#REF!"}},null,"서울",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}}]
["남서울",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$f":"SUM(J17,L17,N17)","v":{"$error":"#REF!"}},{"$f":"SUM(S17:U17)","v":{"$error":"#REF!"}},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"남서울",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}}]
["인   천",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"인천",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}}]
["경기북부",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경기북부",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}}]
["경   기",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경기",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}}]
["강   원",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"강원",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}}]
["충   북",{"$f":"SUM(C22:G22)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"충북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}}]
["대전충남",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"대전충남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}}]
["전   북",{"$f":"SUM(C24:G24)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"전북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}}]
["광주전남",{"$f":"SUM(C25:G25)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"광주전남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}}]
["대구",{"$f":"SUM(C26:G26)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},{"$f":"B26-I26","v":{"$error":"#REF!"}},{"$f":"SUM(J26,L26,N26)","v":{"$error":"#REF!"}},{"$f":"SUM(S26:U26)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(W26:Y26)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA26:AC26)","v":{"$error":"#REF!"}},{"$f":"SUM(AE26:AG26)","v":{"$error":"#REF!"}},{"$f":"(O26/B26)","v":{"$error":"#REF!"}},null,"대구",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}}]
["경북",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}}]
["부산울산",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"부산울산",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}}]
["경   남",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$f":"SUM(W29:Y29)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA29:AC29)","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},null,"경남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}}]
["제   주",{"$f":"SUM(C30:G30)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$f":"(O30/B30)","v":{"$error":"#REF!"}},null,"제주",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}}]
[]
[" 붙임 :  1. 집중심의내역 1부"]
[" 붙임 :  전압별 검토서 1부. 끝."]
[]
[null,{"$f":"SUM(B16:B30)","v":{"$error":"#REF!"}},{"$f":"SUM(C16:C30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(E16:E30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(G16:G30)","v":{"$error":"#REF!"}},{"$f":"SUM(H16:H30)","v":{"$error":"#REF!"}},{"$f":"SUM(I16:I30)","v":{"$error":"#REF!"}},{"$f":"SUM(J16:J30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(L16:L30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(N16:N30)","v":{"$error":"#REF!"}},{"$f":"SUM(O16:O30)","v":{"$error":"#REF!"}}]
[{"$f":"COUNTIF(B36:N36,\"NO\")","v":0},{"$f":"IF(B35=B12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(C35=B9,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(E35=B10,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(G35=B11,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(H35=D12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(I35=I12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(J35=J12,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(L35=L12,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(N35=N12,\"\",\"NO\")","v":{"$error":"#REF!"}}]
[{"$f":"IF(A36>=1,\"틀린곳\",\"\")","v":""},{"$f":"IF(B36=\"NO\",\"총계\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C36=\"NO\",\"765\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(D36=\"NO\",\"총계\",\"\")","v":""},{"$f":"IF(E36=\"NO\",\"345\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(G36=\"NO\",\"154\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(H36=\"NO\",\"채택\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(I36=\"NO\",\"불채택\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(J36=\"NO\",\"병행\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(L36=\"NO\",\"취소\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(N36=\"NO\",\"연기\",\"\")","v":{"$error":"#REF!"}}]

{"sheet":"765송부","index":1,"n_rows":14,"n_cols":13,"rows_kept":14,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 10월 휴전계획서"}]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #3 M.Tr A-1","신가평S/S #77Bay B/F 보호반 교체공사","신가평S/S #77Bay B/F 보호반 교체공사","2019-10-28 09:00","2019-11-01 18:00","2019-10-14 09:00","2019-10-18 18:00","연속"]
[2,"경기","성남","신안성신가평 T/L","2018-2019년 성남전력지사 송전정비회사 총액공사","- 765kV 신안성-신가평T/L 항공장애표시도장(16기)","2019-10-07 07:00","2019-10-28 18:00","2019-10-21 07:00","2019-11-07 18:00","연속"]
[3,"강원","태백","신태백S/S #4 M.Tr A-1","19년 태백전력지사 765kV 주변압기 정밀점검 공사","신태백변전소 #4M.Tr 정밀점검 공사 / [병행] 9/23(월) 8500CB조작시험 / [병행] 9/23(월) 7771CB 보통점검","2019-10-07 10:00","2019-12-09 18:00","2019-10-07 10:00","2019-12-09 18:00","연속"]
[4,"강원","태백","신태백신가평#2 T/L","345kV 신영주, 신제천TCSC 설치사업","신영주, 신제천S/S TCSC 설치공사 - TCSC 제어용 신호 구성을 위한 SPS 설치(신태백, 신제천, 신영주S/S) - 접점 및 보호계전기 동작 관련 연동시험","2019-10-01 09:00","2019-10-02 18:00","2019-10-01 09:00","2019-10-02 18:00","연속"]
[5,"경북","영주","신한울S/S #1 M.Tr A-1","신한울S/S 벨로우즈 교체 공사","신한울S/S 벨로우즈 교체 공사","2019-10-28 09:00","2019-11-01 18:00","2019-10-28 09:00","2019-11-01 18:00","연속"]
[6,"부산울산","동부산","신고리S/S #2 Tie-Tr A-1","고리NP S/Y 362kV GIS 구조개선관련 시험가압","고리NP S/Y 362kV 7D00,7D72GIS 구조개선관련 시험가압(#3M.Tr)","2019-10-12 09:30","2019-10-13 09:30","2019-10-18 18:00","2019-10-19 18:00","연속"]
[7,"부산울산","동부산","북경남신고리NP#2 T/L","2018-2019년 동부산전력지사 송전정비 협력회사 총액공사","항공표시구 제거 ㅇ 구간 : 31~34호","2019-10-10 08:00","2019-10-11 18:00","취소","취소","연속"]
[8,"부산울산","동부산","북경남신고리NP#1 T/L","2018-2019년 동부산전력지사 송전정비 협력회사 총액공사","항공표시구 제거 ㅇ 구간 : 31~34호","2019-10-07 08:00","2019-10-08 18:00","취소","취소","연속"]
[9,"경남","함안","북경남신고리NP#1 T/L","765kV 북경남-신고리NP #1 T/L 착설방지링 설치","765kV 북경남-신고리NP #1 T/L 착설방지링 설치","2019-10-10 08:30","2019-10-15 18:00","2019-10-10 08:30","2019-10-15 18:00","매일"]
[10,"부산울산",null,"신고리S/S #3 Tie-Tr A-1","GIS 구조개선 관련 시험가압","GIS 구조개선 관련 시험가압","2019-10-01 13:00","2019-10-02 13:00","2019-10-01 13:00","2019-10-02 13:00","연속"]

{"sheet":"345송부","index":2,"n_rows":356,"n_cols":13,"rows_kept":356,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 10월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #1 M.Tr","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-10-07 07:30","2019-10-08 17:30","2019-10-07 07:30","2019-10-08 17:30","연속"]
[2,"서울","성동","성동S/S #2 M.Tr","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-10-14 07:30","2019-10-15 17:30","2019-10-14 07:30","2019-10-15 17:30","연속"]
[3,"서울","중부","중부S/S 345kV #75 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 345kV #2BUS PT 보통점검","2019-10-10 14:00","2019-10-10 18:00","2019-10-10 14:00","2019-10-10 18:00","당일"]
[4,"서울","중부","중부S/S 345kV #70 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 345kV #1BUS PT 보통점검","2019-10-10 09:00","2019-10-10 14:00","2019-10-10 09:00","2019-10-10 14:00","당일"]
[5,"서울","중부","양주중부#1 T/L","접속함 과열관련 유사고장 사전 예방점검","접속함 과열 재발방지 위한 접속함 점검","2019-10-29 09:00","2019-10-30 18:00","취소","취소","연속"]
[6,"서울","중부","중부S/S #3 M.Tr","19년 중부P/O 345kV GIS 정밀점검 공사","ㅇ345kV #3M.Tr 1차, 2차 GIS 정밀점검","2019-10-28 10:00","2019-11-08 18:00","2019-10-28 10:00","2019-11-08 18:00","연속"]
[7,"남서울","강남","신양재S/S 345kV #70 PT GIS","345kV #1BUS PT 보통점검","345kV #1BUS PT 보통점검","2019-10-14 09:00","2019-10-14 14:00","2019-10-14 09:00","2019-10-14 14:00","당일"]
[8,"남서울","강남","신양재S/S 345kV #70 BUS","345kV #1BUS PT 보통점검","345kV #1BUS PT 보통점검","2019-10-14 09:00","2019-10-14 14:00","2019-10-14 09:00","2019-10-14 14:00","당일"]
[9,"남서울","강남","신양재S/S #2 M.Tr","345kV #2M.Tr 1차 보통점검,2차 보통점검 및 전자변 교체","345kV #2M.Tr 1차 보통점검,2차 보통점검 및 전자변 교체","2019-10-17 09:00","2019-10-18 18:00","2019-10-17 09:00","2019-10-18 18:00","연속"]
[10,"남서울","강남","신양재S/S 345kV #75 BUS","345kV #2BUS PT 보통점검","345kV #2BUS PT 보통점검","2019-10-14 14:00","2019-10-14 18:00","2019-10-14 14:00","2019-10-14 18:00","당일"]
[11,"남서울","강남","신양재S/S #1 M.Tr","345kV #1M.Tr 1차 보통점검,2차 보통점검 및 전자변 교체","345kV #1M.Tr 1차 보통점검,2차 보통점검 및 전자변 교체","2019-10-15 09:00","2019-10-16 18:00","2019-10-15 09:00","2019-10-16 18:00","연속"]
[12,"남서울","강남","신양재S/S 345kV #75 PT GIS","345kV #2BUS PT 보통점검","345kV #2BUS PT 보통점검","2019-10-14 14:00","2019-10-14 18:00","2019-10-14 14:00","2019-10-14 18:00","당일"]
[13,"남서울","동서울","동서울S/S 345kV SVC 1차 CB(7771)","7771 GIS 정밀점검","7771 GIS 정밀점검","2019-10-14 10:00","2019-10-18 18:00","2019-10-14 10:00","2019-10-18 18:00","연속"]
[14,"남서울","동서울","동서울S/S 345kV SVC 1차-TIE CB(7700)","7700 GIS 정밀점검","7700 GIS 정밀점검","2019-10-21 10:00","2019-10-21 18:00","2019-10-21 10:00","2019-10-21 18:00","연속"]
[15,"남서울","동서울","동서울S/S #3 M.Tr A","#3M.Tr bushing 절연유 채유","#3M.Tr bushing 절연유 채유","2019-10-30 10:00","2019-10-30 14:00","취소","취소","당일"]
[16,"남서울","동서울","동서울S/S #4 M.Tr","동서울S/S 154kV 현대화 공사","○ T-BUS DS 철거 및 인출Lead 직결 ○ LA 및 CVT 이설","2019-10-14 08:30","2019-10-16 17:00","2019-10-14 08:30","2019-10-16 17:00","연속"]
[17,"남서울","동서울","동서울S/S #3 M.Tr","동서울S/S 154kV 현대화 공사","○ T-BUS DS 철거 및 인출Lead 직결 ○ LA 및 CVT 이설","2019-10-23 08:30","2019-10-25 17:00","2019-10-23 08:30","2019-10-25 17:00","연속"]
[18,"남서울","동서울","동서울S/S #4 M.Tr","#4M.Tr bushing 절연유 채유","#4M.Tr bushing 절연유 채유","2019-10-30 14:00","2019-10-30 18:00","취소","취소","당일"]
[19,"남서울","영등포","신광명S/S #1 M.Tr","#1M.Tr 1차 CVT 보통점검 및 2차 GIS 하자보수","-1,2차 부싱절연유 채유 및 절연열화 측정 -1,2,3차 LA 보통점검 2차 하자보수 효성시행","2019-10-07 09:00","2019-10-08 18:00","2019-10-07 09:00","2019-10-08 18:00","연속"]
[20,"남서울","영등포","신광명S/S #2 M.Tr","#2M.Tr 1차 CVT 보통점검 및 2차 GIS 하자보수","-1,2차 부싱절연유 채유 및 절연열화 측정 -1,2,3차 LA 보통점검 2차 하자보수 효성시행","2019-10-10 09:00","2019-10-11 18:00","2019-10-10 09:00","2019-10-11 18:00","연속"]
[21,"남서울","영등포","신광명S/S #3 M.Tr","#3M.Tr 1차 CVT 보통점검 및 2차 GIS 하자보수","-1,2차 부싱절연유 채유 및 절연열화 측정 -1,2,3차 LA 보통점검 2차 하자보수 효성시행","2019-10-14 09:00","2019-10-15 18:00","2019-10-14 09:00","2019-10-15 18:00","연속"]
[22,"남서울","영등포","신광명S/S #4 M.Tr","#4M.Tr 1차 CVT 보통점검 및 2차 GIS 하자보수","-1,2차 부싱절연유 채유 및 절연열화 측정 -1,2,3차 LA 보통점검 2차 하자보수 효성시행","2019-10-16 09:00","2019-10-17 18:00","2019-10-16 09:00","2019-10-17 18:00","연속"]
[23,"남서울","영등포","신시흥신광명#1 T/L","신광명S/S 345kV GCB 보통점검(7172)","345kV GCB 보통점검","2019-10-18 09:00","2019-10-18 18:00","2019-10-18 09:00","2019-10-18 18:00","당일"]
[24,"남서울","직할","영등포S/S #2 M.Tr","직할 170kV GIS 정밀점검","직할 170kV GIS 정밀점검 (무부하) 7272","2019-10-07 09:00","2019-10-09 14:00","2019-10-07 09:00","2019-10-09 14:00","연속"]
[25,"남서울","직할","영등포S/S #3 M.Tr","직할 170kV GIS 정밀점검","직할 170kV GIS 정밀점검 (무부하) 7372","2019-10-09 14:00","2019-10-11 18:00","2019-10-09 14:00","2019-10-11 18:00","연속"]
[26,"남서울","직할","영등포S/S #1 M.Tr","직할 170kV GIS 정밀점검","직할 170kV GIS 정밀점검 (무부하) 7172","2019-10-02 14:00","2019-10-04 18:00","2019-10-02 14:00","2019-10-04 18:00","연속"]
[27,"인천","김포","가정개폐소 345kV 신가좌-가정#2T/L CB(7371)","신부평#2S/S 362kV GIS 설치공사","7372 CB 무부하 가압","2019-10-20 18:00","2019-10-21 18:00","2019-10-20 18:00","2019-10-21 18:00","연속"]
[28,"인천","김포","가정개폐소 345kV #75 BUS","신부평#2S/S 362kV GIS 설치공사","7272, 7372, 7472 CB 사용전검사","2019-10-21 18:00","2019-10-23 18:00","2019-10-21 18:00","2019-10-23 18:00","연속"]
[29,"인천","김포","가정개폐소 345kV #76 BUS","신부평#2S/S 362kV GIS 설치공사","7272, 7372, 7472 CB 사용전검사","2019-10-21 18:00","2019-10-23 18:00","2019-10-21 18:00","2019-10-23 18:00","연속"]
[30,"인천","김포","가정개폐소 345kV #75 BUS","신부평#2S/S 362kV GIS 설치공사","가정개폐소 7372 CB 설치 7272, 7472 LINE PT 설치 7372 모선보호반 시험 및 무부하 가압","2019-10-17 09:00","2019-10-21 18:00","2019-10-17 09:00","2019-10-21 18:00","연속"]
[31,"인천","김포","가정개폐소 345kV #1 Sh.R 1차 CB(7671)","신부평#2S/S 362kV GIS 설치공사","7372 CB 무부하 가압","2019-10-20 18:00","2019-10-21 18:00","2019-10-20 18:00","2019-10-21 18:00","연속"]
[32,"인천","김포","신가좌가정#2 T/L","신부평#2S/S 362kV GIS 설치공사","7372 CB 설치 73BAY BF시험 및 무부하가압","2019-10-20 09:00","2019-10-21 18:00","2019-10-20 09:00","2019-10-21 18:00","연속"]
[33,"인천","김포","가정개폐소 345kV #1 Sh.R TIE CB(7600)","신부평#2S/S 362kV GIS 설치공사","7372 CB 무부하 가압","2019-10-20 18:00","2019-10-21 18:00","2019-10-20 18:00","2019-10-21 18:00","연속"]
[34,"인천","김포","가정개폐소 345kV #76 BUS","신부평#2S/S 362kV GIS 설치공사","7372 무부하 가압","2019-10-20 18:00","2019-10-21 18:00","2019-10-20 18:00","2019-10-21 18:00","연속"]
[35,"인천","김포","신김포신인천CC T/L","345kV 신김포-신인천CC T/L 보호계전기 성능개선","(주)선도전기 87 PCM 통신회로 Loop시 오동작방지 관련 펌웨어 업그레이드","2019-10-10 10:00","2019-10-10 18:00","2019-10-10 10:00","2019-10-10 18:00","당일"]
[36,"인천","부평","신가좌신시흥#1 T/L","345kV신가좌-신시흥#1T/L 이도조정공사","345kV신가좌-신시흥T/L No.9~10 이도조정","2019-10-14 08:00","2019-10-14 18:00","2019-10-14 08:00","2019-10-14 18:00","당일"]
[37,"인천","부평","신경서S/S #2 M.Tr","신경서S/S #2M.Tr 휴전작업","신경서S/S #2M.Tr 휴전작업 - #2M.Tr 휴전(소내반 대체 사전작업), 부싱절연유 채유 - 6244 GIS 보통 - 4289 VCB 조작","2019-10-07 09:00","2019-10-08 18:00","2019-10-07 09:00","2019-10-08 18:00","연속"]
[38,"인천","부평","신경서서인천CC T/L","345kV 신경서-서인천CC T/L 보호계전기 성능개선","(주)선도전기 87 PCM 통신회로 Loop시 오동작방지 관련 펌웨어 업그레이드","2019-10-14 10:00","2019-10-14 18:00","2019-10-14 10:00","2019-10-14 18:00","당일"]
[39,"인천","부평","신경서인천CC#1 T/L","345kV 신경서-인천CC#1 T/L 보호계전기 성능개선","(주)선도전기 87 PCM 통신회로 Loop시 오동작방지 관련 펌웨어 업그레이드","2019-10-15 10:00","2019-10-15 18:00","2019-10-15 10:00","2019-10-15 18:00","당일"]
[40,"인천","부평","신경서신인천CC T/L","345kV 신경서-신인천CC T/L 보호계전기 성능개선","(주)선도전기 87 PCM 통신회로 Loop시 오동작방지 관련 펌웨어 업그레이드","2019-10-11 10:00","2019-10-11 18:00","2019-10-11 10:00","2019-10-11 18:00","당일"]
[41,"인천","부평","인천CC S/Y #2 Tie-Tr","인천복합S/Y #2Tie-Tr 휴전작업","- #2TIE-TR 보통점검 - 부싱절연유 채유(NGK) - 6244 GIS 조작시험","2019-10-10 10:00","2019-10-11 18:00","2019-10-10 10:00","2019-10-11 18:00","연속"]
[42,"인천","부평","인천CC포스코CC#1 T/L","DTS 보수공사","DTS 단선개소 보수공사","2019-10-01 09:00","2019-10-01 13:00","2019-10-01 09:00","2019-10-01 13:00","당일"]
[43,"인천","부평","신경서포스코CC#1 T/L","DTS 보수공사","DTS 단선개소 보수공사","2019-10-01 13:30","2019-10-01 18:00","2019-10-01 13:30","2019-10-01 18:00","당일"]
[44,"인천","시흥","신시흥#1S/S 345kV 신시흥-영흥TP#3T/L CB A (7771)","신시흥S/S 345kV 신시흥-영흥TP#3T/L(7771) CB 정밀점검","신시흥S/S 345kV 신시흥-영흥TP#3T/L(7771) CB 정밀점검 및 7761DS C상 가스누기보수","2019-10-28 09:00","2019-10-31 18:00","2019-10-28 09:00","2019-10-31 18:00","연속"]
[45,"인천","시흥","영흥1TP영흥2TP#2 T/L","영흥S/Y 영흥TP연락#2T/L CB (7271) 정밀점검 무부하용","영흥S/Y 영흥TP연락#2T/L CB (7271) 정밀점검 무부하용","2019-10-04 09:00","2019-10-04 18:00","2019-10-04 09:00","2019-10-04 18:00","당일"]
[46,"인천","시흥","영흥T/P 345kV #1T.Tr 1차 CB(7371)","영흥T/P 345kV #1T.Tr 1차 CB(7371) 정밀점검","영흥T/P 345kV #1T.Tr 1차 CB(7371) 정밀점검","2019-10-07 09:00","2019-10-10 18:00","2019-10-07 09:00","2019-10-10 18:00","연속"]
[47,"인천","시흥","영흥1TP영흥2TP#1 T/L","영흥T/P 345kV #1T.Tr 1차 CB(7371) 정밀점검 무부하용","영흥T/P 345kV #1T.Tr 1차 CB(7371) 정밀점검 무부하용","2019-10-10 09:00","2019-10-10 18:00","2019-10-10 09:00","2019-10-10 18:00","당일"]
[48,"인천","시흥","영흥T/P 345kV #70 BUS","영흥T/P 345kV #1T.Tr 1차 CB(7371) 정밀점검 무부하용","영흥T/P 345kV #1T.Tr 1차 CB(7371) 정밀점검 무부하용","2019-10-10 09:00","2019-10-10 18:00","2019-10-10 09:00","2019-10-10 18:00","당일"]
[49,"인천","시흥","영흥T/P 345kV 신시흥-영흥TP#2T/L CB(7471)","영흥T/P 345kV 신시흥-영흥TP#2T/L CB(7471) 정밀점검","영흥T/P 345kV 신시흥-영흥TP#2T/L CB(7471) 정밀점검","2019-10-14 09:00","2019-10-17 18:00","2019-10-14 09:00","2019-10-17 18:00","연속"]
[50,"인천","시흥","영흥1TP영흥2TP#1 T/L","영흥T/P 신시흥-영흥TP#2T/L CB(7471) 정밀점검 무부하용","영흥T/P 신시흥-영흥TP#2T/L CB(7471) 정밀점검 무부하용","2019-10-17 09:00","2019-10-17 18:00","2019-10-17 09:00","2019-10-17 18:00","당일"]
[51,"인천","시흥","영흥T/P 345kV #70 BUS","영흥T/P 신시흥-영흥TP#2T/L CB(7471) 정밀점검 무부하용","영흥T/P 신시흥-영흥TP#2T/L CB(7471) 정밀점검 무부하용","2019-10-17 09:00","2019-10-17 18:00","2019-10-17 09:00","2019-10-17 18:00","당일"]
[52,"인천","시흥","영흥T/P 345kV 신시흥-영흥TP#4T/L CB(7571)","영흥T/P 345kV 신시흥-영흥TP#4T/L CB(7571) 정밀점검","영흥T/P 345kV 신시흥-영흥TP#4T/L CB(7571) 정밀점검","2019-10-21 09:00","2019-10-24 18:00","2019-10-21 09:00","2019-10-24 18:00","연속"]
[53,"인천","시흥","영흥1TP영흥2TP#1 T/L","영흥T/P 신시흥-영흥TP#4T/L CB(7571) 정밀점검 무부하용","영흥T/P 신시흥-영흥TP#4T/L CB(7571) 정밀점검 무부하용","2019-10-24 09:00","2019-10-24 18:00","2019-10-24 09:00","2019-10-24 18:00","당일"]
[54,"인천","시흥","영흥T/P 345kV #70 BUS","영흥T/P 신시흥-영흥TP#4T/L CB(7571) 정밀점검 무부하용","영흥T/P 신시흥-영흥TP#4T/L CB(7571) 정밀점검 무부하용","2019-10-24 09:00","2019-10-24 18:00","2019-10-24 09:00","2019-10-24 18:00","당일"]
[55,"인천","직할","신부평S/S #4 M.Tr","신부평S/S 345kV #4M.Tr 1,2차 조작시험","신부평S/S 345kV #4M.Tr 1,2차 조작시험","2019-10-31 09:30","2019-10-31 18:00","2019-10-31 09:30","2019-10-31 18:00","당일"]
[56,"인천","직할","신부평S/S 345kV #4 Sh.R","신부평S/S 362kV #4Sh.R 7479 GIS 조작시험","신부평S/S 362kV #4Sh.R 7479 GIS 조작시험","2019-10-10 14:00","2019-10-10 18:00","2019-10-10 14:00","2019-10-10 18:00","당일"]
[57,"인천","직할","서인천CC신부평#4 T/L","신부평S/S 362kV 서인천신부평#4T/L 7471 GIS 보통점검","신부평S/S 362kV 서인천신부평#4T/L 7471 GIS 보통점검","2019-10-11 09:30","2019-10-11 18:00","2019-10-11 09:30","2019-10-11 18:00","당일"]
[58,"인천","직할","신부평S/S #1 M.Tr","신부평S/S 345kV #1M.Tr 1,2차 조작시험","신부평S/S 345kV #1M.Tr 1,2차 조작시험","2019-10-28 09:30","2019-10-28 18:00","2019-10-28 09:30","2019-10-28 18:00","당일"]
[59,"인천","직할","신부평S/S #2 M.Tr","신부평S/S 345kV #2M.Tr 1,2차 조작시험","신부평S/S 345kV #2M.Tr 1,2차 조작시험","2019-10-29 09:30","2019-10-29 18:00","2019-10-29 09:30","2019-10-29 18:00","당일"]
[60,"인천","직할","신부평S/S 345kV #3 Sh.R","신부평S/S 362kV #3Sh.R 7379 GIS 보통점검","신부평S/S 362kV #3Sh.R 7379 GIS 보통점검","2019-10-10 09:30","2019-10-10 14:00","2019-10-10 09:30","2019-10-10 14:00","당일"]
[61,"인천","직할","신부평S/S #3 M.Tr","신부평S/S 345kV #3M.Tr 1,2차 조작시험","신부평S/S 345kV #3M.Tr 1,2차 조작시험","2019-10-30 09:30","2019-10-30 18:00","2019-10-30 09:30","2019-10-30 18:00","당일"]
[62,"경기북부","고양","신파주신덕은#1 T/L","신덕은변전소 내진보강 3차 잔여공사","철골 브레이스 1개소 설치(3.33ton)","2019-10-21 09:00","2019-10-25 18:00","2019-10-21 09:00","2019-10-25 18:00","연속"]
[63,"경기북부","고양","신덕은S/S 신덕은-LG디스플레이 #1T/L GIS","선도전기 송전선로 보호계전기 성능개선","보호계전기 펌웨어 업그레이드","2019-10-21 09:00","2019-10-21 18:00","2019-10-21 09:00","2019-10-21 18:00","당일"]
[64,"경기북부","고양","신덕은S/S 신덕은-LG디스플레이#2T/L GIS","선도전기 송전선로 보호계전기 성능개선","보호계전기 펌웨어 업그레이드","2019-10-22 09:00","2019-10-22 18:00","2019-10-22 09:00","2019-10-22 18:00","당일"]
[65,"경기북부","고양","파주문산C/C 345kV #4G/T 1차 CB (7472)","변전총액공사-7472 GIS 하자점검","7472 GIS 하자점검","2019-10-14 09:00","2019-10-14 18:00","2019-10-14 09:00","2019-10-14 18:00","당일"]
[66,"경기북부","고양","파주문산C/C 345kV #4TIE-#4G/T 1차 CB (7400)","제작사 설비보수-유압펌프 누유보수","파주문산CC 7400 CB 유압펌프 누유보수","2019-10-30 09:00","2019-10-30 18:00","2019-10-30 09:00","2019-10-30 18:00","당일"]
[67,"경기북부","고양","파주문산C/C 345kV 신덕은-파주문산CC#1T/L CB (7471)","제작사 설비보수-유압펌프 누유보수","파주문산CC 77471 CB 유압펌프 누유보수","2019-10-29 09:00","2019-10-29 18:00","2019-10-29 09:00","2019-10-29 18:00","당일"]
[68,"경기북부","고양","파주문산C/C 345kV #3TIE-#3G/T 1차 CB (7300)","제작사 설비보수-유압펌프 누유보수","파주문산CC 7300 CB 유압펌프 누유보수","2019-10-28 09:00","2019-10-28 18:00","2019-10-28 09:00","2019-10-28 18:00","당일"]
[69,"경기북부","고양","파주문산C/C 345kV #4G/T 1차 CB (7472)","변전총액공사-345kV GIS 하자점검","파주문산CC 7472 GIS 하자점검","2019-10-23 09:00","2019-10-23 18:00","2019-10-23 09:00","2019-10-23 18:00","당일"]
[70,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용GIS 교체공사(7차분)","- 170kV GIS 철거, 설치(안전이격확보) - 기타 부대공사","2019-10-21 08:00","2019-10-29 18:00","취소","취소","매일"]
[71,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용GIS 교체공사(6차분)","- 170kV GIS 철거, 설치(시험가압) - 기타 부대공사","2019-10-18 15:00","2019-10-19 16:00","취소","취소","연속"]
[72,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용GIS 교체공사(7차분)","- 170kV GIS 철거, 설치(시험가압) - 기타 부대공사","2019-10-29 15:00","2019-10-30 16:00","취소","취소","연속"]
[73,"경기북부","구리","미금성동#4 T/L","미금S/S 345kV #77BAY B/F반 교체공사","미금S/S 345kV #77BAY B/F반 교체공사 - 미금-성동#4T/L, 신가평-미금#1T/L","2019-10-28 09:00","2019-11-01 18:00","2019-10-14 09:00","2019-10-18 18:00","연속"]
[74,"경기북부","구리","신가평미금#1 T/L","미금S/S 345kV #77BAY B/F반 교체공사","미금S/S 345kV #77BAY B/F반 교체공사 - 미금-성동#4T/L, 신가평-미금#1T/L","2019-10-28 09:00","2019-11-01 18:00","2019-10-14 09:00","2019-10-18 18:00","연속"]
[75,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용GIS 교체공사(7차분)","- 170kV GIS 철거, 설치(시험가압) - 기타 부대공사","2019-10-21 16:00","2019-10-22 08:00","취소","취소","연속"]
[76,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용GIS 교체공사(6차분)","- 170kV GIS 철거, 설치(시험가압) - 기타 부대공사","2019-10-06 16:00","2019-10-07 08:00","취소","취소","연속"]
[77,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용GIS 교체공사(7차분)","- 170kV GIS 철거, 설치(시험가압) - 기타 부대공사","2019-10-24 16:00","2019-10-25 08:00","취소","취소","연속"]
[78,"경기북부","구리","신포천포천CC#1 T/L","345kV T/L보호반(유호) 성능개선 시행","345kV T/L보호반(유호) 성능개선 시행","2019-10-07 09:00","2019-10-07 18:00","2019-10-07 09:00","2019-10-07 18:00","당일"]
[79,"경기북부","구리","신포천포천CC#2 T/L","345kV T/L보호반(유호) 성능개선 시행","345kV T/L보호반(유호) 성능개선 시행","2019-10-08 09:00","2019-10-08 18:00","2019-10-08 09:00","2019-10-08 18:00","당일"]
[80,"경기북부","구리","신포천포천LNGCC#2 T/L","신포천S/S 345kV #1BUS 가스누기보수공사","신포천S/S 345kV #1BUS 가스누기보수공사 - #1BUS 휴전(연속) - 신포천-포천LNGC/C #1,2T/L (매일)","2019-10-02 09:00","2019-10-04 18:00","2019-10-02 09:00","2019-10-04 18:00","매일"]
[81,"경기북부","구리","신포천포천LNGCC#1 T/L","신포천S/S 345kV #1BUS 가스누기보수공사","신포천S/S 345kV #1BUS 가스누기보수공사 - #1BUS 휴전(연속) - 신포천-포천LNGC/C #1,2T/L (매일)","2019-10-02 09:00","2019-10-04 18:00","2019-10-02 09:00","2019-10-04 18:00","매일"]
[82,"경기북부","구리","신포천동두천CC#2 T/L","직할 관내 OPGW 항공장애표시구 설치 공사","직할 관내 OPGW 항공장애표시구 설치 공사 - 신포천동두천CC#2T/L 항공장애표시구 4개 설치","2019-10-15 06:00","2019-10-15 18:00","2019-10-15 06:00","2019-10-15 18:00","당일"]
[83,"경기북부","구리","신포천동두천CC#1 T/L","직할 관내 OPGW 항공장애표시구 설치 공사","직할 관내 OPGW 항공장애표시구 설치 공사 - 신포천동두천CC#1T/L 항공장애표시구 3개 설치","2019-10-14 06:00","2019-10-14 18:00","2019-10-14 06:00","2019-10-14 18:00","당일"]
[84,"경기북부","직할","신의정부S/S #2 M.Tr","345kV M.Tr 본체 및 OLTC 정밀점검","#2M.Tr C상 본체 및 OLTC 정밀점검","2019-10-07 09:00","2019-10-11 18:00","2019-10-07 09:00","2019-10-11 18:00","연속"]
[85,"경기북부","직할","양주S/S 345kV #70 BUS","'19년 345kV GIS 정밀점검(양주-중부#1T/L)","양주-중부#1T/L (7571,7500) 정밀점검","2019-10-14 07:00","2019-10-16 13:00","취소","취소","연속"]
[86,"경기북부","직할","신파주양주#2 T/L","'19년 345kV GIS 정밀점검","신파주-양주#2T/L (7471,7400)","2019-10-07 07:00","2019-10-11 17:00","2019-10-07 07:00","2019-10-11 17:00","연속"]
[87,"경기북부","직할","양주S/S 345kV #70 BUS","'19년 345kV GIS 정밀점검(신파주-양주#2T/L)","신파주-양주#2T/L (7471,7400) 정밀점검","2019-10-07 07:00","2019-10-09 13:00","취소","취소","연속"]
[88,"경기북부","직할","양주S/S #2 M.Tr","345kV GIS 정밀점검(병행설비)","7402DS점검을 위한 휴전","2019-10-07 07:00","2019-10-11 17:00","2019-10-07 07:00","2019-10-11 17:00","연속"]
[89,"경기북부","직할","양주S/S 345kV #75 BUS","'19년 345kV GIS 정밀점검(신파주-양주#2T/L)","신파주-양주#2T/L (7471,7400) 정밀점검","2019-10-09 13:00","2019-10-11 17:00","취소","취소","연속"]
[90,"경기북부","직할","양주S/S 345kV #5 Sh.R","'19년 345kV GIS 정밀점검(양주-중부#1T/L)","양주-중부#1T/L (7571,7500) 정밀점검","2019-10-14 07:00","2019-10-18 17:00","2019-10-14 07:00","2019-10-18 17:00","연속"]
[91,"경기북부","직할","양주S/S 345kV #75 BUS","'19년 345kV GIS 정밀점검(양주-중부#2T/L)","양주-중부#2T/L (7671,7600) 정밀점검","2019-10-23 13:00","2019-10-25 17:00","취소","취소","연속"]
[92,"경기북부","직할","양주S/S 345kV #4 Sh.R","'19년 345kV GIS 정밀점검(양주-중부#2T/L)","양주-중부#2T/L (7671,7600) 정밀점검","2019-10-21 07:00","2019-10-25 17:00","2019-10-21 07:00","2019-10-25 17:00","연속"]
[93,"경기북부","직할","양주중부#2 T/L","'19년 345kV GIS 정밀점검(양주-중부#2T/L)","양주-중부#2T/L (7671,7600) 정밀점검","2019-10-21 07:00","2019-10-25 17:00","2019-10-21 07:00","2019-10-25 17:00","연속"]
[94,"경기북부","직할","양주S/S 345kV #6 Sh.R","'19년 345kV GIS 정밀점검(양주-중부#2T/L)","양주-중부#2T/L (7671,7600) 정밀점검","2019-10-21 07:00","2019-10-25 17:00","2019-10-21 07:00","2019-10-25 17:00","연속"]
[95,"경기북부","직할","양주S/S 345kV #70 BUS","'19년 345kV GIS 정밀점검(양주-중부#2T/L)","양주-중부#2T/L (7671,7600) 정밀점검","2019-10-21 07:00","2019-10-23 13:00","취소","취소","연속"]
[96,"경기북부","직할","양주중부#1 T/L","'19년 345kV GIS 정밀점검(양주-중부#1T/L)","양주-중부#1T/L (7571,7500) 정밀점검","2019-10-14 07:00","2019-10-18 17:00","2019-10-14 07:00","2019-10-18 17:00","연속"]
[97,"경기북부","직할","양주S/S 345kV #75 BUS","'19년 345kV GIS 정밀점검(양주-중부#1T/L)","양주-중부#1T/L (7571,7500) 정밀점검","2019-10-16 13:00","2019-10-18 17:00","취소","취소","연속"]
[98,"경기","군포","서서울S/S #4 M.Tr","2019년 군포P/O 변전정비회사 총액공사","서서울S/S 345kV #4M.Tr 1, 2차 부싱절연유 채유(A,B,C상)","2019-10-17 13:00","2019-10-17 18:00","2019-10-17 13:00","2019-10-17 18:00","당일"]
[99,"경기","군포","화성서서울#1 T/L","345kV 화성-서서울T/L 소도체 불량개소 정비","- 25~26호간 소도체불량개소 정비","2019-10-28 08:00","2019-10-29 18:00","2019-10-28 08:00","2019-10-29 18:00","연속"]
[100,"경기","군포","서서울S/S #3 M.Tr","2019년 군포P/O 변전정비회사 총액공사","서서울S/S 345kV #3M.Tr 1, 2차 부싱절연유 채유(A,B,C상)","2019-10-17 09:00","2019-10-17 13:00","2019-10-17 09:00","2019-10-17 13:00","당일"]
[101,"경기","군포","신안산S/S 345kV #75 BUS","345kV 신안산S/S 용량부족 GIS 대체공사","345kV 신안산S/S 용량부족 GIS 대체공사 - #71BAY(#1M.Tr) 용량대체 #75BUS 모선연결","2019-10-17 09:00","2019-10-25 18:00","2019-10-17 09:00","2019-10-25 18:00","연속"]
[102,"경기","군포","신시흥신안산 T/L","345kV 신안산S/S 용량부족 GIS 대체공사","345kV 신안산S/S 용량부족 GIS 대체공사 - #71BAY(#1M.Tr) 용량대체 #70BUS 무부하가압용","2019-10-15 09:00","2019-10-16 18:00","2019-10-15 09:00","2019-10-16 18:00","연속"]
[103,"경기","군포","신안산S/S 345kV #70 BUS","345kV 신안산S/S 용량부족 GIS 대체공사","345kV 신안산S/S 용량부족 GIS 대체공사 - #71BAY(#1M.Tr) 용량대체 #70BUS 모선연결","2019-10-08 09:00","2019-10-16 18:00","2019-10-08 09:00","2019-10-16 18:00","연속"]
[104,"경기","군포","화성신안산 T/L","345kV 신안산S/S 용량부족 GIS 대체공사","345kV 신안산S/S 용량부족 GIS 대체공사 - #71BAY(#1M.Tr) 용량대체 #75BUS 무부하가압용","2019-10-26 09:00","2019-10-27 18:00","취소","취소","연속"]
[105,"경기","군포","신안산S/S #3 M.Tr","345kV 신안산S/S 용량부족 GIS 대체공사","- 345kV #72Bay측 40kA GIS 철거 - 345kV #72Bay측 63kA GIS 설치","2019-10-31 09:00","2019-12-31 18:00","2019-10-31 09:00","2019-12-15 18:00","연속"]
[106,"경기","동부","곤지암동서울#2 T/L","19년 동부변전협력회사 총액공사","곤지암:곤지암-동서울#2T/L 휴전(계통요청 보호반 ABB 성능개선) 7471.7400 GIS (개폐타임)","2019-10-08 09:30","2019-10-08 18:00","2019-10-08 09:30","2019-10-08 18:00","당일"]
[107,"경기","동부","곤지암동서울#1 T/L","19년 동부변전협력회사 총액공사","곤지암:곤지암-동서울#1T/L 휴전(계통요청 보호반 ABB 성능개선) 7371.7300 GIS (개폐타임)","2019-10-07 09:30","2019-10-07 18:00","2019-10-07 09:30","2019-10-07 18:00","당일"]
[108,"경기","동부","곤지암S/S 345kV #3 M.Tr 1차-TIE CB A (7500-A)","19년 동부변전협력회사 총액공사","곤지암:7572,7500 GIS (개폐타임)","2019-10-04 09:30","2019-10-04 18:00","2019-10-04 09:30","2019-10-04 18:00","당일"]
[109,"경기","동부","곤지암S/S 345kV #1 M.Tr 1차 CB A (7172-A)","19년 동부변전협력회사 총액공사","곤지암: 7172,7372 GIS (개폐타임)","2019-10-02 09:30","2019-10-02 18:00","2019-10-02 09:30","2019-10-02 18:00","당일"]
[110,"경기","동부","곤지암S/S 345kV #2 M.Tr 1차 CB A (7372-A)","19년 동부변전협력회사 총액공사","곤지암: 7172,7372 GIS (개폐타임)","2019-10-02 09:30","2019-10-02 18:00","2019-10-02 09:30","2019-10-02 18:00","당일"]
[111,"경기","동부","곤지암S/S 345kV #3 M.Tr 1차 CB A (7572-A)","19년 동부변전협력회사 총액공사","곤지암:7572,7500 GIS (개폐타임)","2019-10-04 09:30","2019-10-04 18:00","2019-10-04 09:30","2019-10-04 18:00","당일"]
[112,"경기","성남","서안성S/S 345kV #75 BUS","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ74Bay GIS 용량대체 ㅇ 기타 부대공사 x 1식","2019-10-01 09:00","2019-10-17 09:00","2019-10-01 09:00","2019-10-17 09:00","연속"]
[113,"경기","성남","서안성신진천#1 T/L","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ74Bay 용량대체공사관련 무부하 가압","2019-10-16 09:00","2019-10-17 09:00","2019-10-16 09:00","2019-10-17 09:00","연속"]
[114,"경기","성남","서안성S/S #4 M.Tr","M.Tr, 1차 GIS 제작사 하자처리","- A상 96G 연결부누유 -7672,7600 CB ES 코일불량 -7672,7600CB 히터불량, 단자대 열화 -7600CB 유압계 누유 -7672,7600CB CT 명판 불일치","2019-10-21 09:00","2019-10-21 18:00","2019-10-21 09:00","2019-10-21 18:00","당일"]
[115,"경기","성남","신성남신양재#2 T/L","2019년 가공송전 순시점검 위탁공사(성남)","345kV 신성남-신양재#2T/L 1,2호 점퍼지지애자 교체","2019-10-18 09:00","2019-10-18 18:00","2019-10-18 09:00","2019-10-18 18:00","당일"]
[116,"경기","성남","신안성신성남#1 T/L","가보제 345T/L 로직개선(계통)","가보제 345T/L 로직개선(계통)","2019-10-10 09:00","2019-10-10 18:00","2019-10-10 09:00","2019-10-10 18:00","당일"]
[117,"경기","성남","신수원S/S #4 M.Tr","M.Tr 보통점검","M.Tr 보통점검","2019-10-14 09:00","2019-10-14 18:00","2019-10-14 09:00","2019-10-14 18:00","당일"]
[118,"경기","성남","신안성S/S 345kV 신안성-서안성#1T/L GIS","7C52DS 보조계전기 교체(차단기 단독휴전)","7C52DS 보조계전기 교체(차단기 단독휴전)","2019-10-15 09:00","2019-10-15 18:00","2019-10-15 09:00","2019-10-15 18:00","당일"]
[119,"경기","성남","신안성S/S 345kV 신안성-서안성#2T/L GIS","7B62,7B52DS 보조계전기 교체(차단기 단독휴전)","7B62,7B52DS 보조계전기 교체(차단기 단독휴전)","2019-10-15 09:00","2019-10-15 18:00","2019-10-15 09:00","2019-10-15 18:00","당일"]
[120,"경기","성남","신용인삼성 T/L","345kV신용인-신수원,신용인-삼성T/L 전선교체공사","선종교체공사 1~13호 5.224km(ACSR 480→HSTACIR 410)","2019-10-08 09:00","2019-10-27 18:00","2019-10-08 09:00","2019-10-27 18:00","연속"]
[121,"경기","성남","신용인신수원 T/L","345kV신용인-신수원,신용인-삼성T/L 전선교체공사","선종교체공사 1~13호 5.224km(ACSR 480→HSTACIR 410)","2019-10-28 09:00","2019-11-09 18:00","2019-10-28 09:00","2019-11-09 18:00","연속"]
[122,"경기","성남","신용인신수원 T/L","345kV신용인-신수원,신용인-삼성T/L 전선교체공사","선종교체공사 1~13호 5.224km(ACSR 480→HSTACIR 410)","2019-10-01 09:00","2019-10-07 18:00","2019-10-01 09:00","2019-10-07 18:00","연속"]
[123,"경기","직할","화성신시흥 T/L","345kV 신안산S/S 용량부족 GIS 대체공사","- 신시흥S/S 화성-신시흥T/L 보호배전반 대체 - 화성-신시흥T/L #56-1호 보조 Arm 설치","2019-10-21 09:00","2019-10-30 18:00","2019-10-21 09:00","2019-10-30 18:00","연속"]
[124,"경기","직할","화성S/S #4 M.Tr","19년 직할 변전협력회사 총액공사","화성S/S #4M.Tr 1차 GIS 보통, 부싱절연유 채유","2019-10-14 09:00","2019-10-14 18:00","2019-10-14 09:00","2019-10-14 18:00","당일"]
[125,"경기","직할","화성S/S 345kV #76 BUS","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV GIS(40/50kA -&gt63kA) 교체공사 O. 화성-신안산#1T/L 이용 #76BUS 무부하가압","2019-10-08 16:00","2019-10-10 11:00","2019-10-08 16:00","2019-10-10 11:00","연속"]
[126,"경기","직할","화성신안산 T/L","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV GIS(40/50kA -&gt63kA) 교체공사 O. 화성-신안산#1T/L 이용 #76BUS 무부하가압","2019-10-08 16:00","2019-10-10 11:00","2019-10-08 16:00","2019-10-10 11:00","연속"]
[127,"경기","직할","화성신안산 T/L","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV GIS(40/50kA -&gt63kA) 교체공사 O. 화성-신안산#1T/L 이용 #71BUS 무부하가압","2019-10-07 16:00","2019-10-08 16:00","2019-10-07 16:00","2019-10-08 16:00","연속"]
[128,"경기","직할","화성평택T/P#2 T/L","345kV 화성-평택TP T/L 전선접속개소 전선교체공사","전선접속개소 전력선(ACSR 480㎟ × 4B : 1.790C-km) 교체","2019-10-14 07:00","2019-10-21 18:00","2019-10-14 07:00","2019-10-21 18:00","연속"]
[129,"경기","직할","화성S/S 345kV #2 CLR 76BUS GIS","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV GIS(40/50kA -&gt63kA) 교체공사 O. #2CLR 불량 기둥 재설치","2019-10-01 10:00","2019-10-31 18:00","2019-10-01 10:00","2019-10-31 18:00","연속"]
[130,"경기","직할","화성S/S 345kV #71 BUS","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV GIS(40/50kA -&gt63kA) 교체공사 O. 화성-신안산#1T/L 이용 #71BUS 무부하가압","2019-10-07 16:00","2019-10-08 16:00","2019-10-07 16:00","2019-10-08 16:00","연속"]
[131,"경기","직할","화성S/S 345kV #2 CLR 75BUS GIS(7577)","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV GIS(40/50kA -&gt63kA) 교체공사 O. #2CLR 불량 기둥 재설치","2019-10-01 10:00","2019-10-31 18:00","2019-10-01 10:00","2019-10-31 18:00","연속"]
[133,"경기","성남","서서울#2신성남 #1T/L","345kV 서서울2-신성남T/L 안전이격 확보공사","345kV 서서울2-신성남T/L 안전이격 확보공사","2019-10-01 07:00","2019-10-05 18:00","2019-10-01 07:00","2019-10-05 18:00","연속"]
[134,"경기","성남","서서울#2신성남 #1T/L","345kV 서서울2-신성남T/L 안전이격 확보공사","345kV 서서울2-신성남T/L 안전이격 확보공사","2019-10-01 07:00","2019-10-05 18:00","취소","취소","연속"]
[135,"경기","성남","서서울#2신성남 #1T/L","345kV 서서울2-신성남T/L 안전이격 확보공사","345kV 서서울2-신성남T/L 안전이격 확보공사","2019-10-01 07:00","2019-10-05 18:00","취소","취소","연속"]
[136,"경기","성남","서서울#2신성남 #1T/L","345kV 서서울2-신성남T/L 안전이격 확보공사","345kV 서서울2-신성남T/L 안전이격 확보공사","2019-10-01 07:00","2019-10-05 18:00","취소","취소","연속"]
[137,"강원","강릉","신양양양양PP T/L","가공송전선로 순시점검 위탁공사","○ 불량애자 검출 - 345kV 신양양-양양PPT/L 신양양변전소 인출 지지애자 불량애자 검출","2019-10-11 08:00","2019-10-11 18:00","2019-10-11 08:00","2019-10-11 18:00","당일"]
[138,"강원","강릉","신양양S/S #2 M.Tr","2019 변전협력회사 총액공사","신양양 362kV #2M.Tr 1차 GIS 보통점검 신양양 362kV #2M.Tr 1차 - TIE GIS 보통점검 신양양 154kV #2M.Tr 2차 GIS 보통점검","2019-10-07 10:00","2019-10-10 18:00","2019-10-07 10:00","2019-10-10 18:00","당일"]
[139,"강원","강릉","동해양양PP T/L","2018-19년도 강릉전력지사 송전정비 협력회사 총액공사","○ 아킹혼 철거 - 154kV 신양양인제#1T/L No.7, 9 - 345kV 동해양양PPT/L 병가구간(작업자 안전을 위한 병가회선 휴전)","2019-10-01 07:00","2019-10-01 18:00","2019-10-01 07:00","2019-10-01 18:00","당일"]
[140,"강원","동해","동해신양양 T/L","2019년 동해전력지사 변전협력회사 총액공사","1. 송전선로 보호반 대체","2019-10-28 09:30","2019-11-01 18:00","2019-10-28 09:30","2019-11-01 18:00","연속"]
[141,"강원","동해","신제천동해#2 T/L","2018~2019년도 송전정비 협력회사 총액공사","○작 업 명 : 345kV 신제천-동해T/L 전선 접속개소 해소 ○공사구간 : No.293~297","2019-10-24 07:00","2019-10-26 18:00","취소","취소","연속"]
[142,"강원","동해","동해S/S #1 M.Tr","2019년 동해전력지사 변전협력회사 총액공사","1. #71 Bay B/F PNL 대체 2. M.Tr 초기점검 3. M.Tr 부싱절연유 채취 4. #1S.Tr 보통점검 5. 장기미동작 차단기 조작시험","2019-10-21 09:30","2019-10-25 18:00","2019-10-21 09:30","2019-10-25 18:00","연속"]
[143,"강원","동해","신제천동해#1 T/L","2018~2019년도 송전정비 협력회사 총액공사","○작 업 명 : 345kV 신제천-동해T/L 전선 접속개소 해소 ○공사구간 : No.293~297","2019-10-21 07:00","2019-10-23 18:00","취소","취소","연속"]
[144,"강원","동해","동해S/S #3 M.Tr","2019년 동해전력지사 변전협력회사 총액공사","1. #76 Bay B/F PNL 대체 2. 장기미동작 차단기 조작시험","2019-10-18 09:30","2019-10-22 18:00","취소","취소","연속"]
[145,"강원","동해","동해삼척GP#2 T/L","345kV 동해-삼척GPT/L 전선접속개소 전선교체공사","공사개요 ○ 전력선 접속개소 해소 : No.5 ∼ 6 등 8개소 15.448C-km ○ 가공지선 접속개소 해소 : No.12 ∼ 17 등 3개소 5.944C-km","2019-10-18 08:00","2019-11-01 18:00","취소","취소","연속"]
[146,"강원","동해","동해삼척GP#1 T/L","345kV 동해-삼척GPT/L 전선접속개소 전선교체공사","공사개요 ○ 전력선 접속개소 해소 : No.5 ∼ 6 등 8개소 15.448C-km ○ 가공지선 접속개소 해소 : No.12 ∼ 17 등 3개소 5.944C-km","2019-10-03 08:00","2019-10-17 18:00","2019-10-21 08:00","2019-11-04 18:00","연속"]
[147,"충북","직할","신중부신진천#2 T/L","345kV 신중부-신진천T/L 안전이격거리 확보공사","철탑설치 5기, 철탑철거 5기(가철탑 4기 설치), 전선가선(6.6km)","2019-10-25 07:30","2019-11-18 19:00","2019-10-25 07:30","2019-11-18 19:00","연속"]
[148,"충북","직할","신중부신진천#1 T/L","345kV 신중부-신진천T/L 안전이격거리 확보공사","철탑설치 5기, 철탑철거 5기(가철탑 4기 설치), 전선가선(6.6km)","2019-10-21 07:30","2019-10-24 19:00","2019-10-21 07:30","2019-10-24 19:00","연속"]
[149,"충북","직할","신진천S/S 345kV #70 BUS","신진천S/S 345kV 모선보호반 대체 및 CT집합반 대체","신진천S/S 345kV 모선보호반 대체 및 CT집합반 대체","2019-10-19 10:00","2019-10-20 18:00","2019-10-19 10:00","2019-10-20 18:00","연속"]
[150,"충북","직할","서안성신진천#2 T/L","2018~19년 충주전력지사 송전정비회사 총액공사","스페이서교체(17~18),조류퇴치장치설치(2~16,27~30,32~35)","2019-10-02 07:00","2019-10-04 18:00","2019-10-04 07:00","2019-10-04 18:00","매일"]
[151,"충북","직할","신진천S/S 345kV #75 BUS","신진천S/S 345kV 모선보호반 대체 및 CT집합반 대체","신진천S/S 345kV 모선보호반 대체 및 CT집합반 대체","2019-10-26 10:00","2019-10-27 18:00","2019-10-12 10:00","2019-10-13 18:00","연속"]
[152,"충북","직할","신진천S/S #1 M.Tr","'19년 직할 154kV GIS 정밀점검 공사","신진천S/S 345kV #1M.Tr 2차 GIS 보통점검+조작부 정밀점검","2019-10-09 10:00","2019-10-09 18:00","2019-10-09 10:00","2019-10-09 18:00","당일"]
[153,"충북","직할","신진천S/S #3 M.Tr","신진천S/S 345kV #3M.Tr 1차,TIE GIS 하자점검","신진천S/S 345kV #3M.Tr 1차 GIS 및 TIE GIS 하자점검","2019-10-05 10:00","2019-10-06 18:00","2019-10-05 10:00","2019-10-06 18:00","연속"]
[154,"충북","직할","신진천S/S #2 M.Tr","'19년 직할 154kV GIS 정밀점검 공사","신진천S/S 345kV #2M.Tr 2차 GIS 보통점검+조작부 정밀점검","2019-10-03 10:00","2019-10-03 18:00","2019-10-03 10:00","2019-10-03 18:00","당일"]
[155,"충북","청주","신옥천S/S #2 M.Tr","신옥천S/S 154kV GIS화 공사","154kV GIS 26CCT 설치 옥외철구→GIS 부하절체","2019-10-10 09:00","2019-10-15 18:00","2019-10-10 09:00","2019-10-15 18:00","연속"]
[156,"충북","청주","신옥천북경남 T/L","345kV 신옥천-북경남T/L 전력선 교체공사","345kV 신옥천-북경남T/L 전력선 교체공사 구 간 : 신옥천-북경남 No.253~255 등 5경간(4.5km) 작업내용 : 전선접속개소 전력선 교체공사","2019-10-08 08:00","2019-10-17 18:00","2019-10-08 08:00","2019-10-17 18:00","연속"]
[157,"충북","충주","신제천신영주#1 T/L","신제천S/S 345kV #70BUS부 DS 제작사(LS) 하자대체","- 345kV 수평 EDS 조작불량 관련 제작사(LS) 하자대체 관련 무부하가압 - 작업대상 : 7351,7451,7651,7751,7951,7A51 6개소","2019-10-04 13:00","2019-10-04 18:00","2019-10-04 13:00","2019-10-04 18:00","당일"]
[158,"충북","충주","신제천신영주#1 T/L","신제천S/S 345kV #75BUS부 DS 제작사(LS) 하자대체","- 345kV 수평 EDS 조작불량 관련 제작사(LS) 하자대체 관련 무부하가압. - 작업대상 :7352, 7452, 7952 3개소.","2019-10-19 13:00","2019-10-19 18:00","2019-10-19 13:00","2019-10-19 18:00","당일"]
[159,"충북","충주","신제천S/S 345KV #75 BUS","신제천S/S 345kV #75BUS부 DS 제작사(LS) 하자대체","- 345kV 수평 EDS 조작불량 관련 제작사(LS) 하자대체. - 대상 : 7352, 7452, 7952 3개소.","2019-10-14 09:00","2019-10-19 18:00","2019-10-14 09:00","2019-10-19 18:00","연속"]
[160,"충북","충주","곤지암신충주#1 T/L","2018-2019년 송전정비회사 총액공사","345kV피뢰기 설치 (No.163-224)","2019-10-05 08:00","2019-10-13 18:00","2019-10-05 08:00","2019-10-13 18:00","매일"]
[161,"충북","충주","신제천신충주#2 T/L","2018-2019년 송전정비회사 총액공사","피뢰기 설치 (No.163-224)","2019-10-05 08:00","2019-10-13 18:00","2019-10-05 08:00","2019-10-13 18:00","매일"]
[162,"대전충남","대전","신계룡S/S 345kV 신계룡-청양T/L TIE CB(7100)","신계룡S/S 345kV ES 구속핀 교체","신계룡S/S 345kV ES 구속핀 교체(7109-6)","2019-10-01 10:00","2019-10-01 11:00","2019-10-01 10:00","2019-10-01 11:00","당일"]
[163,"대전충남","대전","신계룡S/S 345kV 신계룡-청양T/L CB(7171)","신계룡S/S 345kV ES 구속핀 교체","신계룡S/S 345kV ES 구속핀 교체(7109-1)","2019-10-01 09:00","2019-10-01 10:00","2019-10-01 09:00","2019-10-01 10:00","당일"]
[164,"대전충남","대전","신계룡S/S 345kV 신옥천-신계룡T/L CB(7271)","신계룡S/S 345kV ES 구속핀 교체","신계룡S/S 345kV ES 구속핀 교체(7209-1)","2019-10-01 11:00","2019-10-01 12:00","2019-10-01 11:00","2019-10-01 12:00","당일"]
[165,"대전충남","대전","신계룡S/S 345kV #1 M.Tr 1차 CB(7272)","신계룡S/S 345kV ES 구속핀 교체","신계룡S/S 345kV ES 구속핀 교체(7209-6)","2019-10-01 13:00","2019-10-01 14:00","2019-10-01 13:00","2019-10-01 14:00","당일"]
[166,"대전충남","대전","신계룡S/S 345kV #2 M.Tr 1차 TIE CB(7400)","신계룡S/S 345kV ES 구속핀 교체","신계룡S/S 345kV ES 구속핀 교체(7409-1)","2019-10-01 14:00","2019-10-01 15:00","2019-10-01 14:00","2019-10-01 15:00","당일"]
[167,"대전충남","대전","신계룡S/S 345kV #2 M.Tr 1차 CB(7472)","신계룡S/S 345kV ES 구속핀 교체","신계룡S/S 345kV ES 구속핀 교체(7409-6)","2019-10-01 15:00","2019-10-01 16:00","2019-10-01 15:00","2019-10-01 16:00","당일"]
[168,"대전충남","서산","당진화력S/Y 345kV 1호기 1차 CB(7172)","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험 - 당진T/P 1호기 1차 (7172)CB","2019-10-23 10:00","2019-10-23 14:00","2019-10-23 10:00","2019-10-23 14:00","당일"]
[169,"대전충남","서산","당진T/P #71 Tie-Tr","당진화력S/S 345kV #71 TIE TR 2차 자기애자 교체공사","당진화력S/S 345kV #71 TIE TR 2차 자기애자 교체공사","2019-10-07 09:00","2019-10-11 18:00","2019-10-07 09:00","2019-10-11 18:00","연속"]
[170,"대전충남","서산","당진화력S/Y 2호기 1차 CB(7272)","19년도 변전협력회사 총액공사","당진화력S/Y 345kV 2호기 1차 GIS(7272) 및 LA 보통점검","2019-10-11 09:00","2019-10-11 18:00","2019-10-11 09:00","2019-10-11 18:00","당일"]
[171,"대전충남","서산","북당진S/S #4-2 M.Tr CB(7872)","19년도 변전협력회사 총액공사","북당진S/S 345kV #4-2 M.Tr GIS(7772) 하자점검","2019-10-16 09:00","2019-10-16 18:00","2019-10-16 09:00","2019-10-16 18:00","당일"]
[172,"대전충남","서산","북당진S/S 345kV #75 BUS","345kV 북당진E/C #1M.Tr용 362kV GIS 설치공사","362kV GIS 3CB 설치","2019-10-10 09:00","2019-10-19 18:00","2019-10-25 09:00","2019-10-30 18:00","연속"]
[173,"대전충남","서산","북당진S/S #4-1 M.Tr TIE CB(7700)","19년도 변전협력회사 총액공사","북당진S/S 345kV #4-1 M.Tr TIE GIS(7800) 하자점검","2019-10-17 09:00","2019-10-17 18:00","2019-10-17 09:00","2019-10-17 18:00","당일"]
[174,"대전충남","서산","신당진S/S 신당진연락#2T/L CB(7771)","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험 -신당진S/S 신당진-태안화력#2T/L (7771)CB","2019-10-17 14:00","2019-10-17 18:00","2019-10-17 14:00","2019-10-17 18:00","당일"]
[175,"대전충남","서산","신당진S/S #70-#71 SEC CB(70-71-0)","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험 -신당진S/S 70-71 BUS SECTION CB","2019-10-02 10:00","2019-10-02 14:00","2019-10-02 10:00","2019-10-02 14:00","당일"]
[176,"대전충남","서산","신서산신당진#1 T/L","19년도 변전협력회사 총액공사","신당진S/S 신서산신당진#1 T/L CVT 대체 신서산신당진#1 T/L 보호계전기 성능개선작업","2019-10-10 09:00","2019-10-11 18:00","2019-10-10 09:00","2019-10-11 18:00","연속"]
[177,"대전충남","서산","신당진S/S 신당진연락#1T/L-#1 M.Tr 1차 TIE CB(7400)","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험 -신당진S/S 345kV 신당진연락#1T/L-#1 M.Tr 1차 TIE CB (7400)CB","2019-10-16 10:00","2019-10-16 14:00","2019-10-15 14:00","2019-10-15 18:00","당일"]
[178,"대전충남","서산","신당진S/S 신당진연락#2-신서산신당진#2T/L TIE CB(7700)","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험 - 신당진S/S 345kV 신당진연락#2-신서산신당진#2T/L TIE (7700)CB","2019-10-16 14:00","2019-10-16 18:00","2019-10-16 14:00","2019-10-16 18:00","당일"]
[179,"대전충남","서산","신서산S/S #4 Sh.R CB(7779)","서산P/O 19년도 변전협력회사 총액공사","신서산S/S 345kV #4 Sh.R GIS(7779) 보통점검","2019-10-23 09:00","2019-10-23 18:00","2019-10-23 09:00","2019-10-23 18:00","당일"]
[180,"대전충남","서산","태안T/P #3 GEN 1차 TIE CB(7300)","서산P/O 19년도 변전협력회사 총액공사","태안T/P 345kV #3 GEN 1차 TIE GIS(7300) 보통점검","2019-10-22 09:00","2019-10-22 18:00","2019-10-22 09:00","2019-10-22 18:00","당일"]
[181,"대전충남","서산","태안T/P #2 GEN 1차 CB(7272)","서산P/O 19년도 변전협력회사 총액공사","태안T/P 345kV #2 GEN 1차 GIS(7272) 하자점검","2019-10-21 09:00","2019-10-21 18:00","2019-10-21 09:00","2019-10-21 18:00","당일"]
[182,"대전충남","서산","태안T/P #71-#72 SEC CB(71-72-0)","서산P/O 19년도 변전협력회사 총액공사","태안T/P 345kV 71-72-0 SEC GIS 보통점검","2019-10-24 09:00","2019-10-24 18:00","2019-10-24 09:00","2019-10-24 18:00","당일"]
[183,"대전충남","서산","태안T/P #2 M.Tr 1차 CB(7771)","태안T/P 345kV #2 M.Tr 1차 CB 하자보수 작업","차단기 동작 매카니즘 점검 및 교체","2019-10-07 13:00","2019-10-11 18:00","2019-10-07 13:00","2019-10-11 18:00","연속"]
[184,"대전충남","서산","태안T/P #2 GEN 1차 TIE CB(7200)","서산P/O 19년도 변전협력회사 총액공사","태안T/P 345kV #2 GEN 1차 TIE GIS(7200) 하자점검","2019-10-18 09:00","2019-10-18 18:00","2019-10-18 09:00","2019-10-18 18:00","당일"]
[185,"대전충남","서산","태안T/P #76-#77 SEC CB (76-77-0)","서산P/O 19년도 변전협력회사 총액공사","태안T/P 345kV 76-77-0 SEC GIS 하자점검","2019-10-25 09:00","2019-10-25 18:00","2019-10-25 09:00","2019-10-25 18:00","당일"]
[186,"대전충남","서산","태안T/P #3 GEN 1차 CB(7372)","서산P/O 19년도 변전협력회사 총액공사","태안T/P 345kV #3 GEN 1차 GIS(7372) 보통점검","2019-10-23 09:00","2019-10-23 18:00","2019-10-23 09:00","2019-10-23 18:00","당일"]
[187,"대전충남","세종","세종남청주#2 T/L","345kV 보호배전반 성능개선_세종변전소","345kV 보호배전반 성능개선_세종변전소 - 345kV 보호계전기 성능개선 4면","2019-10-02 09:00","2019-10-02 18:00","2019-10-02 09:00","2019-10-02 18:00","당일"]
[188,"대전충남","세종","세종남청주#1 T/L","345kV 보호배전반 성능개선_세종변전소","345kV 보호배전반 성능개선_세종변전소 - 345kV 보호계전기 성능개선 4면","2019-10-01 09:00","2019-10-01 18:00","2019-10-01 09:00","2019-10-01 18:00","당일"]
[189,"대전충남","세종","신옥천세종#2 T/L","345kV 보호배전반 성능개선_세종변전소","345kV 보호배전반 성능개선_세종변전소 - 345kV 보호계전기 성능개선 4면","2019-10-04 09:00","2019-10-04 18:00","2019-10-04 09:00","2019-10-04 18:00","당일"]
[190,"대전충남","아산","신서산아산#1 T/L","[송전]345kV 신서산-아산T/L 전선교체공사","ㅇ 접속개소 전선교체 : No.35~36 24가닥 교체","2019-10-19 07:00","2019-10-20 18:00","2019-10-19 07:00","2019-10-20 18:00","연속"]
[191,"대전충남","아산","신서산아산#1 T/L","[송전]345kV 신서산-아산 등 2개T/L 지장송전선로 이설공사","가. 철탑 설치 및 철거 : 2기 [No.83(B4-28 → Bb4-36), No.84(F4-29 → F4-39)] 나. 전력선교체 - ACSR 480㎟ x 4B x 2C × 1.778km [No.82~83 1선 교체, No.83~88 24선 교체] - ACSR 410㎟ x 2B x 2C × 1.778km [No.83~88 24선 교체]","2019-10-14 07:00","2019-10-24 18:00","취소","취소","연속"]
[192,"대전충남","아산","아산S/S #4 M.Tr","아산S/S 345kV #4M.Tr 부싱절연유 채유","아산S/S 345kV #4M.Tr 부싱절연유 채유","2019-10-14 09:00","2019-10-15 18:00","2019-10-14 09:00","2019-10-15 18:00","연속"]
[193,"대전충남","아산","신서산아산#2 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기 설치공사","[안전이격거리] 154kV 합덕-송악 #2T/L 피뢰기 설치 (27기, 81set) [병행] 345kV 신서산-아산T/L 전선교체공사","2019-10-12 07:00","2019-10-13 18:00","2019-10-12 07:00","2019-10-13 18:00","연속"]
[194,"대전충남","아산","신서산아산#1 T/L","[송전]345kV 신서산-아산T/L 전선교체공사","ㅇ 접속개소 전선교체 : No.35~36 24가닥 교체","2019-10-26 07:00","2019-10-27 18:00","2019-10-26 07:00","2019-10-27 18:00","연속"]
[195,"대전충남","아산","신서산아산#2 T/L","[송전]345kV 신서산-아산 등 2개T/L 지장송전선로 이설공사","가. 철탑 설치 및 철거 : 2기 [No.83(B4-28 → Bb4-36), No.84(F4-29 → F4-39)] 나. 전력선교체 - ACSR 480㎟ x 4B x 2C × 1.778km [No.82~83 1선 교체, No.83~88 24선 교체] - ACSR 410㎟ x 2B x 2C × 1.778km [No.83~88 24선 교체]","2019-10-25 07:00","2019-11-04 18:00","취소","취소","연속"]
[196,"대전충남","아산","신서산아산#2 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기 설치공사","[안전이격거리] 154kV 아산-합덕 #2T/L 피뢰기 설치 (16기, 44set)","2019-10-05 07:00","2019-10-06 18:00","2019-10-05 07:00","2019-10-06 18:00","연속"]
[197,"대전충남","청양","보령C/C 345kV #75-#76 SEC CB(75-76-0)","보령C/C 362kV 차단기 부동작 예방 조작시험","보령C/C 362kV 차단기 부동작 예방 조작시험 - 대상 : 75-76-0","2019-10-11 14:00","2019-10-11 18:00","2019-10-11 14:00","2019-10-11 18:00","당일"]
[198,"대전충남","청양","보령C/C 345kV #70-#71 SEC CB(70-71-0)","보령C/C 362kV 차단기 부동작 예방 조작시험","보령C/C 362kV 차단기 부동작 예방 조작시험 - 대상 : 70-71-0","2019-10-11 09:00","2019-10-11 13:00","2019-10-11 09:00","2019-10-11 13:00","당일"]
[199,"대전충남",6950,"보령C/C 보령연락#1T/L-#1 M.Tr 1차 CB(7100)","보령C/C 362kV GIS 보통점검","보령C/C 362kV GIS 보통점검(7100)","2019-10-08 09:00","2019-10-08 18:00","2019-10-08 09:00","2019-10-08 18:00","당일"]
[200,"대전충남","청양","보령C/C 보령연락#2T/L CB(7271)","보령C/C 362kV 차단기 부동작 예방 조작시험","보령C/C 362kV 차단기 부동작 예방 조작시험 - 대상 : 보령C/C(7271)","2019-10-28 09:00","2019-10-28 13:00","2019-10-28 09:00","2019-10-28 13:00","당일"]
[201,"대전충남","청양","보령C/C  #4 M.Tr 1차 CB(7472)","보령C/C 362kV 차단기 보통점검","보령C/C 362kV 차단기 보통점검 - 대상 : 보령C/C 7472","2019-10-25 09:00","2019-10-25 18:00","2019-10-25 09:00","2019-10-25 18:00","당일"]
[202,"대전충남","청양","보령C/C #1 M.Tr 1차 CB(7172)","보령C/C 362kV GIS 보통점검","보령C/C 362kV GIS 보통점검(7172)","2019-10-10 09:00","2019-10-10 18:00","2019-10-10 09:00","2019-10-10 18:00","당일"]
[203,"대전충남","청양","청양보령복합 T/L","송전선로 보호배전반 성능개선 등","송전선로 보호배전반 성능개선 - 대상 : 청양-보령복합T/L(양단) - 병행 : 청양S/S 측 LA, CVT 초기점검","2019-10-22 09:00","2019-10-22 18:00","2019-10-22 09:00","2019-10-22 18:00","당일"]
[204,"대전충남","청양","보령T/P 아산보령화력#2T/L-#5M.Tr1차 CB(7500)","보령T/P 362kV GIS 초기점검","보령T/P 362kV GIS 초기점검 - 대상 : 보령T/P(7500)","2019-10-24 09:00","2019-10-24 18:00","2019-10-24 09:00","2019-10-24 18:00","연속"]
[205,"대전충남","청양","보령T/P #5,6 SU TR 1차-#4 M.Tr 1차 CB(7400)","보령T/P 362kV GIS 초기점검","보령T/P 362kV GIS 초기점검 - 대상 : 보령T/P 7400","2019-10-30 09:00","2019-10-30 18:00","2019-10-30 09:00","2019-10-30 18:00","당일"]
[206,"대전충남","청양","보령T/P 345kV 아산-보령화력#2T/L CB(7571)","보령T/P 362kV GIS 초기점검","보령T/P 362kV GIS 초기점검 - 대상 : 보령T/P(7571)","2019-10-23 09:00","2019-10-23 18:00","2019-10-23 09:00","2019-10-23 18:00","연속"]
[207,"대전충남","청양","보령T/P #5,6 SU TR 1차 CB(7471)","보령T/P 362kV GIS 초기점검","보령T/P 362kV GIS 초기점검 - 대상 : 보령T/P 7471","2019-10-29 09:00","2019-10-29 18:00","2019-10-29 09:00","2019-10-29 18:00","당일"]
[208,"대전충남","청양","청양S/S #1 M.Tr","청양S/S #1M.Tr 과열개소 보수","청양S/S #1M.Tr 과열개소 보수 - A상 3차측 부싱 단자측 과열","2019-10-31 09:00","2019-10-31 18:00","2019-10-31 09:00","2019-10-31 18:00","당일"]
[209,"전북","군산","군산S/S #2 M.Tr","군산P/O 170kV GIS 정밀점검공사","군산S/S 170kV #2M.Tr 2차 GIS 정밀점검공사","2019-10-03 09:00","2019-10-04 18:00","취소","취소","연속"]
[210,"전북","군산","군산S/S #1 M.Tr","군산P/O 170kV GIS 정밀점검공사","군산S/S 170kV #1M.TR 2차 GIS 정밀점검공사","2019-10-01 09:00","2019-10-02 18:00","취소","취소","연속"]
[211,"전북","군산","군산S/S #3 M.Tr","유호전기 345kV 변압기 보호배전반 성능개선","Line DS 접점 철거 및 STUB 정정 OFF","2019-10-08 10:00","2019-10-08 18:00","2019-10-08 10:00","2019-10-08 18:00","당일"]
[212,"전북","군산","군산새만금#1 T/L","345kV 군산-새만금T/L 초기점검","초기점검 : 1~88호, 88기","2019-10-14 08:00","2019-10-18 18:00","2019-10-14 08:00","2019-10-18 18:00","매일"]
[213,"전북","군산","군산새만금#2 T/L","345kV 군산-새만금T/L 초기점검","초기점검 : 1~88호, 88기","2019-10-21 08:00","2019-10-25 18:00","2019-10-21 08:00","2019-10-25 18:00","매일"]
[214,"전북","김제","군산신김제#1 T/L","2019년 345kV GIS 정밀점검공사","- 차단기 내부 분해점검 - 기타부태공사 1식","2019-10-28 09:00","2019-11-09 18:00","2019-10-28 09:00","2019-11-09 18:00","연속"]
[215,"전북","김제","군산신김제#2 T/L","2019년 345kV GIS 정밀점검공사","- 차단기 내부 분해점검 - 기타부태공사 1식","2019-10-14 09:00","2019-10-26 18:00","2019-10-14 09:00","2019-10-26 18:00","연속"]
[216,"전북","김제","신김제S/S #2 M.Tr","김제P/O 345kV 변압기 정밀점검공사","신김제S/S 345kV #2M.Tr 정밀점검 기타부대공사","2019-10-28 09:30","2019-11-09 18:00","2019-10-28 09:30","2019-11-09 18:00","연속"]
[217,"전북","김제","신김제S/S #1 M.Tr","김제P/O 345kV 변압기 정밀점검공사","신김제S/S 345kV #1M.Tr 정밀점검 기타부대공사","2019-10-14 09:30","2019-10-26 18:00","2019-10-14 09:30","2019-10-26 18:00","연속"]
[218,"전북","직할","북경남무주양수 T/L","345kV 신옥천-북경남T/L 전력선 교체공사","345kV 신옥천-북경남T/L 전력선 교체공사 구 간 : 신옥천-북경남 No.253~255 등 5경간(4.5km) 작업내용 : 전선접속개소 전력선 교체공사","2019-10-01 08:00","2019-10-07 18:00","2019-10-01 08:00","2019-10-07 18:00","연속"]
[219,"전북","직할","북경남무주양수 T/L","345kV 북경남2분기 항공장애구 설치공사","졀연저항 측정 및 항공장애표시구 설치","2019-10-16 08:30","2019-10-18 18:00","취소","취소","연속"]
[220,"전북","직할","신남원S/S #1 M.Tr","신남원S/S 345kV #1M.Tr 절연보강 및 3차측 PT교체작업","1. 신남원S/S 3차측 절연보강 및 PT 교체","2019-10-15 09:00","2019-10-17 18:00","2019-10-15 09:00","2019-10-17 18:00","연속"]
[221,"전북","직할","신남원S/S 345kV #70 BUS","신남원S/S 345kV GIS CB/DS GAS 누기 보수공사","신남원S/S 345kV GIS CB/DS SF6 GAS 누기에 따른 보수공사","2019-10-21 09:30","2019-11-08 17:00","2019-10-21 09:30","2019-11-08 17:00","연속"]
[222,"전북","직할","신남원신광주#2 T/L","신남원S/S 345kV GIS CB/DS GAS 누기 보수공사","신남원S/S 345kV GIS CB/DS SF6 GAS 누기에 따른 보수공사","2019-10-21 09:30","2019-11-08 17:00","2019-10-21 09:30","2019-11-08 17:00","연속"]
[223,"광주전남","강진","신강진S/S 345kV #2 BUS (GIS)","345kV 신강진E/C #4M.Tr 증설공사","O 345kV M.Tr(500MAV) 설치 * 1Bank O 362kV GIS(50kA 4000A) 설치 * 1Bay O 170kV GIS(50kA 2000A) 설치 *1CCT O 기타 부대공사 *1식","2019-10-24 14:00","2019-10-30 14:00","취소","취소","연속"]
[224,"광주전남","강진","신강진S/S 345kV #2 BUS (GIS)","신강진S/S 345kV 취약설비 GIS화 ","345kV 옥외 철구 345kV GIS 화 (75BAY) ","2019-10-14 09:00","2019-10-22 18:00","2019-10-14 09:00","2019-10-22 18:00","연속"]
[225,"광주전남","강진","신화순신강진#1 T/L","345kV 신강진E/C #4M.Tr 증설공사","O 345kV M.Tr(500MAV) 설치 * 1Bank O 362kV GIS(50kA 4000A) 설치 * 1Bay O 170kV GIS(50kA 2000A) 설치 *1CCT O 기타 부대공사 *1식","2019-10-24 14:00","2019-10-30 14:00","취소","취소","연속"]
[226,"광주전남","광주","신광주한빛NP#2 T/L","신광주S/S 345kV 신광주-한빛NP#2T/L LA 초기점검","신광주S/S 345kV 신광주-한빛NP#2T/L LA 초기점검","2019-10-08 09:00","2019-10-08 18:00","2019-10-08 09:00","2019-10-08 18:00","당일"]
[227,"광주전남","광주","신광주한빛NP#1 T/L","신광주S/S 345kV 신광주-한빛NP#1T/L LA 초기점검","신광주S/S 345kV 신광주-한빛NP#1T/L LA 초기점검","2019-10-09 09:00","2019-10-09 18:00","2019-10-09 09:00","2019-10-09 18:00","당일"]
[228,"광주전남","광주","신광주신화순#2 T/L","신화순S/S 신광주-신화순#2T/L (변전협력회사공사)","신화순S/S 신광주-신화순#2T/L 1ST, 2ND PNL 교체,78BAY BF PNL 교체 신광주S/S 신광주-신화순#2T/L 1ST, 2ND PNL 교체","2019-10-17 09:00","2019-10-31 18:00","2019-10-07 09:00","2019-10-11 18:00","연속"]
[229,"광주전남","순천","광양하동화력#1 T/L","345kV 광양하동화력#1T/L 정밀점검","19년 가공송전 순시위탁공사 - 345kV 광양하동화력#1T/L 정밀점검","2019-10-01 08:00","2019-10-04 18:00","2019-10-29 08:00","2019-10-31 18:00","매일"]
[230,"광주전남","순천","여수T/P #1 Tie-Tr","19년 변전정비회사 총액공사(애자련교체)","여수화력S/Y #1M.Tr 불량 현수애자(12련) 교체","2019-10-25 10:00","2019-10-25 18:00","2019-10-25 10:00","2019-10-25 18:00","당일"]
[231,"대구","경산","신경산S/S 345kV #70 BUS","신경산S/S 362kV GIS 대체공사","모선ES~DS간 인터록 시험 모선DS 조작시험, 자체인터록 시험 무부하 가압(송전선로~7171CB~#1BUS)","2019-10-30 09:00","2019-11-01 09:00","2019-10-30 09:00","2019-11-01 09:00","연속"]
[232,"대구","경산","울주신경산#1 T/L","345kV 울주-신경산 등 5개T/L 지장송전선로 이설공사","○ 345kV 울주-신경산 No.118~120 - No.119 가철탑 활용 임시선로 구성","2019-10-12 09:00","2019-10-15 18:00","취소","취소","연속"]
[233,"대구","경산","울주신경산#2 T/L","345kV 울주-신경산 등 5개T/L 지장송전선로 이설공사","○ 345kV 울주-신경산 No.118~120 - No.119 가철탑 활용 임시선로 구성","2019-10-08 09:00","2019-10-11 18:00","취소","취소","연속"]
[234,"대구","경산","신경산대구#2 T/L","신경산S/S 362kV GIS 대체공사","#1BUS 접속 건전성확인 무부하가압용 선로","2019-10-02 18:00","2019-10-03 09:00","2019-10-02 18:00","2019-10-03 09:00","연속"]
[235,"대구","달성","고령S/S 고령-의령#2T/L CB(7471)","고령S/S 고령-의령#2T/L 7471 GIS 보통점검","고령S/S 고령-의령#2T/L 7471 GIS 보통점검","2019-10-21 09:00","2019-10-21 18:00","2019-10-21 09:00","2019-10-21 18:00","당일"]
[236,"대구","달성","고령S/S #2 M.Tr","고령S/S 154kV 고령-서구지T/L S/W 증설공사","고령S/S 154kV 고령-서구지T/L S/W 증설공사","2019-10-14 09:00","2019-10-18 18:00","2019-10-16 09:00","2019-10-20 18:00","연속"]
[237,"대구","달성","고령S/S #3 M.Tr","고령S/S 76B/F 대체작업 및 기타작업","고령S/S 76B/F 대체,차단기동작특성시험, 지지애자 교체작업","2019-10-07 09:00","2019-10-11 18:00","2019-10-07 09:00","2019-10-15 18:00","연속"]
[238,"대구","달성","서대구고령#1 T/L","고령S/S 76B/F 대체작업 및 기타작업","고령S/S 76B/F 대체,차단기동작특성시험, 지지애자 교체작업","2019-10-07 09:00","2019-10-11 18:00","2019-10-07 09:00","2019-10-15 18:00","연속"]
[239,"대구","달성","고령S/S #2 M.Tr","고령S/S 154kV 고령-서구지T/L S/W 증설공사","고령S/S 154kV 고령-서구지T/L S/W 증설공사","2019-10-21 09:00","2019-10-24 18:00","2019-10-24 09:00","2019-10-27 18:00","연속"]
[240,"대구","달성","고령S/S 고령-의령#2T/L-TIE CB(7400)","고령S/S 고령-의령#2T/L 7400 GIS 보통점검","고령S/S 고령-의령#2T/L 7400 GIS 보통점검","2019-10-22 09:00","2019-10-22 18:00","2019-10-22 09:00","2019-10-22 18:00","당일"]
[241,"대구","달성","북경남고령#1 T/L","고령S/S 78B/F 대체작업 및 기타작업","고령S/S 78/F 대체,GIS 보통점검, 지지애자 교체작업","2019-10-28 09:00","2019-11-05 18:00","2019-10-28 09:00","2019-10-30 18:00","연속"]
[242,"대구","달성","북경남고령#2 T/L","345kV 북경남1분기T/L 항공장애표시구 설치공사","1.항공장애표시구 설치(No.20~24, 26~30) ※관련 근거 : 공항시설법 기준","2019-10-16 08:30","2019-10-18 18:00","2019-10-22 08:30","2019-10-24 18:00","연속"]
[243,"대구","달성","고령S/S #4 M.Tr","고령S/S 78B/F 대체작업 및 기타작업","고령S/S 78/F 대체,GIS 보통점검, 지지애자 교체작업","2019-10-28 09:00","2019-11-05 18:00","취소","취소","연속"]
[244,"대구","달성","북경남대구#2 T/L","345kV 북경남1분기T/L 항공장애표시구 설치공사","1.항공장애표시구 설치(No.20~24, 26~30) ※관련근거 : 공항시설법 기준","2019-10-16 08:30","2019-10-18 18:00","2019-10-22 08:30","2019-10-24 18:00","연속"]
[245,"대구","달성","대구S/S #1 M.Tr","대구S/S #1M.Tr 보통점검 및 GIS 보통점검","대구S/S #1M.Tr 보통점검 및 GIS 보통점검","2019-10-23 09:00","2019-10-24 18:00","2019-10-23 09:00","2019-10-24 18:00","연속"]
[246,"대구","달성","북경남대구#1 T/L","345kV 북경남1분기T/L 항공장애표시구 설치공사","1.항공장애표시구 설치(No.20~24, 26~30) ※관련근거 : 공항시설법 기준","2019-10-28 08:30","2019-10-30 18:00","2019-10-28 08:30","2019-10-30 18:00","연속"]
[247,"대구","칠곡","북대구S/S 신포항-북대구T/L CB(7172)","북대구S/S 신포항-북대구T/L 7172 GIS 보통점검","북대구S/S 신포항-북대구T/L 7172 GIS 보통점검","2019-10-07 14:00","2019-10-07 18:00","2019-10-07 14:00","2019-10-07 18:00","당일"]
[248,"대구","칠곡","북대구S/S TIE-신포항-북대구T/L CB(7100)","북대구S/S 신포항-북대구T/L TIE GIS 보통점검","북대구S/S 신포항-북대구T/L TIE GIS 보통점검","2019-10-07 09:30","2019-10-07 14:00","2019-10-07 09:30","2019-10-07 14:00","당일"]
[249,"대구","칠곡","북대구S/S #3 M.Tr","북대구S/S #3M.Tr 부싱 절연유 채유","북대구S/S #3M.Tr 부싱 절연유 채유","2019-10-16 09:30","2019-10-16 18:00","2019-10-16 09:30","2019-10-16 18:00","당일"]
[250,"대구","칠곡","북대구서대구#2 T/L","2018~19년도 칠곡 송전정비회사 총액공사","(안전확보)인출 선로명 표시찰 교체(서대구S/S)","2019-10-14 12:00","2019-10-14 18:00","2019-10-21 12:00","2019-10-21 18:00","당일"]
[251,"대구","칠곡","북대구선산 T/L","2018~19년도 칠곡 송전정비회사 총액공사","(안전확보)인출 선로명 표시찰 교체(북대구S/S)","2019-10-14 12:00","2019-10-14 18:00","2019-10-21 12:00","2019-10-21 18:00","당일"]
[252,"대구","칠곡","신포항북대구 T/L","2018~19년도 칠곡 송전정비회사 총액공사","(안전확보)인출 선로명 표시찰 교체(북대구S/S)","2019-10-14 08:00","2019-10-14 12:00","2019-10-21 08:00","2019-10-21 12:00","당일"]
[253,"대구","칠곡","북대구서대구#1 T/L","2018~19년도 칠곡 송전정비회사 총액공사","(안전확보)인출 선로명 표시찰 교체(서대구S/S)","2019-10-14 08:00","2019-10-14 12:00","2019-10-21 08:00","2019-10-21 12:00","당일"]
[254,"대구","칠곡","북대구S/S TIE-북대구-선산T/L CB(7200)","북대구S/S 북대구-선산T/L TIE GIS 7200 보통점검","북대구S/S 북대구-선산T/L TIE GIS 7200 보통점검","2019-10-11 09:30","2019-10-11 14:00","2019-10-11 09:30","2019-10-11 14:00","당일"]
[255,"대구","칠곡","서대구S/S #3 M.Tr 1차 TIE CB(7600)","서대구S/S #3M.Tr 1차 TIE CB 7600 장기미동작점검","서대구S/S #3M.Tr 1차 TIE CB 7600 장기미동작점검","2019-10-07 13:00","2019-10-07 16:00","2019-10-07 13:00","2019-10-07 16:00","당일"]
[256,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","T-BUS, 8DS 철거 및 LEAD 연결","2019-10-22 09:00","2019-10-22 18:00","취소","취소","연속"]
[257,"대구","칠곡","서대구S/S #2 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","T-BUS, 8DS 철거 및 LEAD 연결","2019-10-23 09:00","2019-10-23 18:00","취소","취소","연속"]
[258,"대구","칠곡","서대구S/S #3 M.Tr 1차 CB(7671)","서대구S/S 345kV #3M.Tr 1차 CB 7671 장기미동작점검","서대구S/S 345kV #3M.Tr 1차 CB 7671 장기미동작점검","2019-10-07 09:30","2019-10-07 13:00","2019-10-07 09:30","2019-10-07 13:00","당일"]
[259,"대구","칠곡","북경남서대구#1 T/L","2019년 가공송전순시점검 위탁공사","항공장애표시구설치공사, 불량애자검출 절연저항 측정(1,21,72)","2019-10-01 08:30","2019-10-03 18:00","2019-10-01 08:30","2019-10-03 18:00","연속"]
[260,"대구","칠곡","북경남서대구#2 T/L","2019년도 가공송전 순시점검 위탁공사","항공장애표시구 설치공사, 불량애자검출 절연저항측정(ST,1,21)","2019-10-14 08:30","2019-10-15 18:00","2019-10-16 08:30","2019-10-17 18:00","연속"]
[261,"대구","칠곡","서대구S/S #3 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","T-BUS, 8DS 철거 및 LEAD 연결","2019-10-24 09:00","2019-10-24 18:00","취소","취소","연속"]
[262,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","T-BUS, 8DS 철거 및 LEAD 연결","2019-10-25 09:00","2019-10-25 18:00","취소","취소","연속"]
[263,"대구","포항","신포항S/S #4 M.Tr","신포항 #4M.Tr 부싱 절연유 채유 및 절연열화 측정","신포항 #4M.Tr 부싱 절연유 채유 및 절연열화 측정,7772 보통점검,6444조작시험","2019-10-07 09:00","2019-10-07 18:00","2019-10-07 09:00","2019-10-07 18:00","당일"]
[264,"대구","포항","신포항S/S #1 M.Tr 1차 CB(7571)","신포항 345kV GCB 7571 보통점검","신포항 345kV GCB 7571 보통점검","2019-10-08 09:00","2019-10-08 18:00","2019-10-08 09:00","2019-10-08 18:00","당일"]
[265,"대구","포항","월성2N/P #3 SS TR 1차 CB(7672)","월성S/S 7600,7672 GIS 보통점검","월성S/S 7600,7672 GIS 보통점검","2019-10-01 09:30","2019-10-01 18:00","2019-10-01 09:30","2019-10-01 18:00","당일"]
[266,"대구","포항","월성2N/P #1 SS TR 1차-#3 SS TR 1차 CB(7600)","월성S/S 7600,7672 GIS 보통점검","월성S/S 7600,7672 GIS 보통점검","2019-10-01 09:30","2019-10-01 18:00","2019-10-01 09:30","2019-10-01 18:00","당일"]
[267,"경북","영주","신영주한울NP2#1 T/L","345kV 신영주S/S TCSC 설치공사","- TCSC 555.28MVar × 2조 설치 - 신영주S/S 신영주-한울NP2 #1T/L 송전선로보호반 개조 × 1식 - 신영주S/S 신영주-한울NP2 #1T/L GIB용 보호반 설치","2019-10-07 10:00","2019-10-12 15:00","2019-10-06 10:00","2019-10-11 15:00","연속"]
[268,"경북","구미","선산S/S #4 M.Tr","2019년도 구미전력지사 변전정비업체 총액공사","- 1,2차 부싱 절연유 채유","2019-10-16 09:00","2019-10-16 18:00","2019-10-11 09:00","2019-10-11 18:00","당일"]
[269,"경북","구미","선산S/S #2 M.Tr","2019년도 구미전력지사 변전정비업체 총액공사","- 1,2차 부싱 절연유 채유","2019-10-15 09:00","2019-10-15 18:00","2019-10-10 09:00","2019-10-10 18:00","당일"]
[270,"경북","구미","선산S/S 345kV 예비 M.Tr CB","2019년도 구미전력지사 변전정비업체 총액공사","-M.Tr 보통점검 - 1차 부싱교체 - 2차 부싱 절연유 채유","2019-10-17 09:00","2019-10-18 18:00","취소","취소","연속"]
[271,"경북","영주","신영주한울NP2#1 T/L","345kV 신영주-한울NP2T/L 전선접속개소 전력선 교체공사","345kV 신영주-한울NP2 전선접속개소 전력선 교체공사(14~19호,95~99호)","2019-10-21 07:00","2019-10-28 18:00","2019-10-21 07:00","2019-10-28 18:00","연속"]
[272,"경북","영주","신영주한울NP2#2 T/L","345kV 신영주-한울NP2T/L 전선접속개소 전력선 교체공사","345kV 신영주-한울NP2 전선접속개소 전력선 교체공사(14~19호,95~99호)","2019-10-29 07:00","2019-11-05 18:00","2019-10-29 07:00","2019-11-05 18:00","연속"]
[273,"경북","직할","안동복합S/S UNIT #1 M.Tr 2차 GIS(7372)","18~19년 경북본부 직할 변전정비회사 총액공사","ES조작함 불량관련 점검","2019-10-15 09:00","2019-10-15 15:00","2019-10-15 09:00","2019-10-15 15:00","당일"]
[274,"경북","직할","안동복합S/S 345kV 신영일-안동CCT/L-TIE GIS(7300)","18~19년 경북본부 직할 변전정비회사 총액공사","ES조작함 불량관련 점검","2019-10-15 15:00","2019-10-15 19:00","2019-10-15 15:00","2019-10-15 19:00","당일"]
[275,"부산울산","동부산","고리2N/P 345kV #77 BUS","고리NP S/Y 362kV GIS 구조개선관련 시험가압","고리NP S/Y 현대제 362kV 7D00,7D72GIS 구조개선관련 시험가압(#77BUS)","2019-10-12 09:30","2019-10-13 09:30","2019-10-18 18:00","2019-10-19 18:00","연속"]
[276,"부산울산","동부산","신양산고리NP#2 T/L","신양산E/C 345kV 인출측 CVT 교체","신양산E/C 345kV 인출측 CVT 교체(신양산-고리#2T/L)","2019-10-29 09:30","2019-10-30 18:00","2019-10-29 09:30","2019-10-30 18:00","연속"]
[277,"부산울산","동부산","신양산S/S #1 M.Tr","신양산E/C 345kV M.Tr 보호PNL 대체","신양산E/C 345kV M.Tr 보호PNL 대체(#1M.Tr)","2019-10-14 09:30","2019-10-18 18:00","취소","취소","연속"]
[278,"부산울산","동부산","신양산신대연#2 T/L","2018-2019년 동부산전력지사 송전정비 협력회사 총액공사","불량압축인류크램프 정비","2019-10-31 08:00","2019-11-01 18:00","2019-10-31 08:00","2019-11-01 18:00","매일"]
[279,"부산울산","동부산","신양산S/S #4 M.TR","신양산E/C 345kV M.Tr 보호PNL 대체","신양산E/C 345kV M.Tr 보호PNL 대체(#4M.Tr)","2019-10-07 09:30","2019-10-11 18:00","취소","취소","연속"]
[280,"부산울산","동부산","신양산고리NP#1 T/L","345㎸ 신양산-고리NP T/L OPGW 증설공사","345㎸ 신양산-고리NP#1T/L OPGW 23.05㎞(120SQ/48C) 증설, S/T↔ICT실간 비금속광케이블 0.305㎞ 등 부대설비 1식","2019-10-21 07:00","2019-10-27 18:00","2019-10-21 07:00","2019-10-27 18:00","연속"]
[281,"부산울산","북부산","북부산S/S #2 M.Tr","2019년 북부산 변전협력회사 총액공사","북부산E/C 345kV 북부산-신온산T/L 보호반대체 관련 PT 결선 변경 및 시험","2019-10-28 09:00","2019-11-01 18:00","2019-10-28 09:00","2019-11-01 18:00","연속"]
[282,"부산울산","북부산","서부산북부산#1 T/L","2019년 북부산 변전협력회사 총액공사","북부산E/C 345kV 서부산-북부산#1T/L 7600,7671GIS 초기점검","2019-10-07 09:00","2019-10-08 18:00","2019-10-07 09:00","2019-10-08 18:00","연속"]
[283,"부산울산","북부산","북부산신울산#1 T/L","2019년 북부산 변전협력회사 총액공사","북부산E/C 345kV북부산-신울산#1T/L 7171,7100 GIS 초기점검","2019-10-23 10:00","2019-10-25 18:00","2019-10-23 10:00","2019-10-25 18:00","연속"]
[284,"부산울산","북부산","북부산신온산 T/L","2019년 북부산 변전협력회사 총액공사","북부산E/C 345kV 북부산-신온산T/L 보호반대체","2019-10-28 09:00","2019-11-01 18:00","2019-10-28 09:00","2019-11-01 18:00","연속"]
[285,"부산울산","북부산","북부산신울산#2 T/L","18-19년도 송전정비 협력회사 총액공사","항공도장시행(345kV 북부산-신울산#1,2T/L 82호)","2019-10-22 10:00","2019-10-22 18:00","2019-10-22 10:00","2019-10-22 18:00","당일"]
[286,"부산울산","서부산","서부산S/S #3 M.Tr","서부산E/C 345kV #3M.Tr 변압기 보호반 내부 회로개선","서부산E/C 345kV #3M.Tr 변압기 보호반 내부 회로개선","2019-10-25 10:00","2019-10-25 18:00","취소","취소","당일"]
[287,"부산울산","서부산","신김해신녹산#1 T/L","2019년 가공송전위탁정비공사 (정밀점검)","345kV 신김해-신녹산T/L 23~52호 정밀점검","2019-10-14 08:00","2019-10-18 17:00","2019-10-14 08:00","2019-10-18 17:00","연속"]
[288,"부산울산","서부산","신김해신녹산#2 T/L","2019년 가공송전위탁정비공사 (정밀점검)","345kV 신김해-신녹산T/L 23~52호 정밀점검","2019-10-21 08:00","2019-10-25 17:00","2019-10-21 08:00","2019-10-25 17:00","연속"]
[289,"부산울산","울산","동울산S/S #2 M.Tr","유호전기 345kV 변압기 보호반 성능개선작업","- 유호전기 동울산S/S 345kV #2M.Tr 변압기 보호반 성능개선작업","2019-10-30 14:00","2019-10-30 18:00","2019-10-30 14:00","2019-10-30 18:00","당일"]
[290,"부산울산","울산","동울산S/S #1 M.Tr","유호전기 345kV 변압기 보호반 성능개선작업","- 유호전기 동울산S/S 345kV #1 M.Tr 변압기 보호반 성능개선작업","2019-10-30 09:00","2019-10-30 14:00","2019-10-30 09:00","2019-10-30 14:00","당일"]
[291,"부산울산","울산","동울산신울산#1 T/L","345kV 동울산분기T/L 항공장애표지 설치공사","□ 공사내용 : 345kV 동울산분기T/L 항공장애표지구 설치(안전이격) □ 공사구간 - 345kV 동울산-월성NP#2T/L No.39-66(상단) - 345kV 동울산-신울산T/L#1(하단) □ 공사기간 : 2019.10.25 ~ 2019.10.28","2019-10-25 08:00","2019-10-28 18:00","2019-10-25 08:00","2019-10-28 18:00","매일"]
[292,"부산울산","울산","동울산월성NP#2 T/L","345kV 동울산분기T/L 항공장애표지 설치공사","□ 공사내용 : 345kV 동울산분기T/L 항공장애표지구 설치(안전이격) □ 공사구간 - 345kV 동울산-월성NP#2T/L No.39-66(상단) - 345kV 동울산-신울산T/L#1(하단) □ 공사기간 : 2019.10.25 ~ 2019.10.28","2019-10-25 08:00","2019-10-28 18:00","2019-10-25 08:00","2019-10-28 18:00","매일"]
[293,"부산울산","울산","동울산월성NP#1 T/L","345kV 동울산분기T/L 항공장애표지 설치공사","□ 공사내용 : 345kV 동울산분기T/L 항공장애표지구 설치(안전이격) □ 공사구간 - 345kV 동울산-월성NP#1T/L No.39-66(상단) - 345kV 동울산-신울산T/L#2(하단) □ 공사기간 : 2019.10.21 ~ 2019.10.24","2019-10-21 08:00","2019-10-24 18:00","2019-10-21 08:00","2019-10-24 18:00","매일"]
[294,"부산울산","울산","동울산신울산#2 T/L","345kV 동울산분기T/L 항공장애표지 설치공사","□ 공사내용 : 345kV 동울산분기T/L 항공장애표지구 설치(안전이격) □ 공사구간 - 345kV 동울산-월성NP#1T/L No.39-66(상단) - 345kV 동울산-신울산T/L#2(하단) □ 공사기간 : 2019.10.21 ~ 2019.10.24","2019-10-21 08:00","2019-10-24 18:00","2019-10-21 08:00","2019-10-24 18:00","매일"]
[295,"부산울산","울산","동울산S/S #3 M.Tr","18~19년 변전협력 총액공사","- 동울산S/S 345kV #3M.Tr 2차 차단기 보통점검","2019-10-18 09:00","2019-10-18 18:00","2019-10-18 09:00","2019-10-18 18:00","당일"]
[296,"부산울산","울산","신온산S/S #2 M.Tr 1차 CB(7472)","18~19년 변전협력 총액공사","- 신온산S/S 345kV #2M.Tr 1차 7472GIS차단기 동작 시험","2019-10-16 13:00","2019-10-16 18:00","2019-10-16 13:00","2019-10-16 18:00","당일"]
[297,"부산울산","울산","신온산S/S 신온산T/L-TIE CB(7300)","18~19년 변전협력 총액공사","- 신온산S/S 345kV 신온산-울산TP-#2M.Tr 1차 TIE 7400GIS차단기 동작 시험","2019-10-16 09:00","2019-10-16 13:00","2019-10-16 09:00","2019-10-16 13:00","당일"]
[298,"부산울산","울산","신온산신울산#2 T/L","송전선로 철탑 주간표지 항공도장 공사","□ 공사내용 : 345kV 신울산-신온산 T/L 철탑(No.22) 항공도장 □ 공사기간 : 2019.10.10 ~ 2019.10.11 ※ 양회선 휴전불가시, 1회선 휴전 시행","2019-10-11 07:00","2019-10-11 18:00","2019-10-11 07:00","2019-10-11 18:00","당일"]
[299,"부산울산","울산","신울산S/S #5 M.Tr","18~19년 변전협력 총액공사","- 345kV #5M.Tr 2차 차단기 동작시험","2019-10-30 13:00","2019-10-30 18:00","2019-10-30 13:00","2019-10-30 18:00","당일"]
[300,"부산울산","울산","신울산고리NP#1 T/L","345kV YPP제 송전선로 보호반 성능개선 작업","- 345kV 신울산-고리NP#1T/L YPP제 송전선로 보호반 성능개선 작업","2019-10-15 09:00","2019-10-16 18:00","2019-10-15 09:00","2019-10-16 18:00","연속"]
[301,"부산울산","울산","신온산신울산#1 T/L","송전선로 철탑 주간표지 항공도장 공사","□ 공사내용 : 345kV 신울산-신온산 T/L 철탑(No.22) 항공도장 □ 공사기간 : 2019.10.10 ~ 2019.10.11 ※ 양회선 휴전불가시, 1회선 휴전 시행","2019-10-10 07:00","2019-10-10 18:00","2019-10-10 07:00","2019-10-10 18:00","당일"]
[302,"부산울산","울산","신울산고리NP#2 T/L","345kV YPP제 송전선로 보호반 성능개선 작업","- 345kV 신울산-고리NP#2T/L YPP제 송전선로 보호반 성능개선 작업","2019-10-17 09:00","2019-10-18 18:00","2019-10-17 09:00","2019-10-18 18:00","연속"]
[303,"부산울산","울산","신울산S/S #4 M.Tr","18~19년 변전협력 총액공사","- 345kV #4M.Tr 2차 차단기 동작시험","2019-10-30 09:00","2019-10-30 13:00","2019-10-08 09:00","2019-10-08 18:00","당일"]
[304,"부산울산","울산","신울산S/S #1 M.Tr","18~19년 변전협력 총액공사","- 신울산S/S 345kV #1M.Tr A상 1,2차 부싱 절연유 채유","2019-10-24 09:00","2019-10-24 18:00","2019-10-02 09:00","2019-10-02 18:00","당일"]
[305,"부산울산","울산","울산C/C #3 Tie-Tr","18~19년 변전협력 총액공사","- 울산복합 345kV #3M.Tr A상 1,2차 부싱 절연유 채유","2019-10-23 09:00","2019-10-23 18:00","2019-11-22 09:00","2019-11-22 18:00","당일"]
[306,"부산울산","울산","울산C/C #1 Tie-Tr","18~19년 변전협력 총액공사","- 울산복합 345kV #1M.Tr A상 1,2차 부싱 절연유 채유","2019-10-21 09:00","2019-10-21 18:00","2019-11-19 09:00","2019-11-19 18:00","당일"]
[307,"부산울산","울산","울산C/C #2 Tie-Tr","18~19년 변전협력 총액공사","- 울산복합 345kV #2M.Tr A상 1,2차 부싱 절연유 채유","2019-10-22 09:00","2019-10-22 18:00","2019-11-21 09:00","2019-11-21 18:00","당일"]
[308,"부산울산","울산","울산C/C 신온산-울산TPT/L CB(7671)","18~19년 변전협력 총액공사","- 울산복합 345kV 신온산-울산TPT/L 7671차단기 보통점검","2019-10-22 09:00","2019-10-22 18:00","2019-10-22 09:00","2019-10-22 18:00","당일"]
[309,"부산울산","울산","북부산울산TP T/L","345kV 신울산복합-북부산T/L 건설공사","○ 공사목적 : 345kV 신울산복합-북부산T/L 울산화력ST~No.12 가선공사 - 공사내용 : NO.3~5호 가공지선 연긴선 시행","2019-10-26 09:00","2019-10-27 18:00","2019-10-26 09:00","2019-10-27 18:00","매일"]
[310,"부산울산","울산","울주고리NP#1 T/L","유호전기 345kV 송전선로 보호반 성능개선작업","- 유호전기 울주S/S 345kV 울주-고리TP#1T/L 송전선로 보호반 성능개선작업","2019-10-04 09:00","2019-10-04 18:00","2019-10-04 09:00","2019-10-04 18:00","당일"]
[311,"부산울산","울산","울주월성NP#2 T/L","새롬프로텍 345kV 송전선로 보호반 성능개선작업","- 새롬프로텍 345kV 울주-월성NP#2 T/L 송전선로 보호반 성능개선작업","2019-10-24 09:00","2019-10-24 13:00","2019-10-24 09:00","2019-10-24 13:00","당일"]
[312,"부산울산","울산","울주고리NP#1 T/L","고리NP S/Y 362kV GIS 구조개선관련 시험가압","고리NP S/Y 362kV 7B00,7B72GIS 구조개선관련 시험가압(울주-고리#1T/L)","2019-10-25 18:00","2019-10-26 18:00","취소","취소","연속"]
[313,"부산울산","울산","울주S/S #2 M.Tr","유호전기 345kV 변압기 보호반 성능개선작업","- 유호전기 울주S/S 345kV #2M.Tr 변압기 보호반 성능개선작업","2019-10-31 09:00","2019-10-31 14:00","2019-10-31 09:00","2019-10-31 14:00","당일"]
[314,"부산울산","직할","신대연S/S #2 M.Tr","2019년 직할 변전협력회사 총액공사","- 345kV #2M.Tr 1,2차 GIS(7200,6244) 차단기 동작시험 - 345kV #2M.Tr 3차 GIS(4289) 보통점검 - #2S.Tr GIS 보통점검","2019-10-23 10:00","2019-10-23 18:00","2019-10-23 10:00","2019-10-23 18:00","당일"]
[315,"부산울산","직할","신대연S/S #1 M.Tr","2019년 직할 변전협력회사 총액공사","- 345kV #1M.Tr 1,2차 GIS(7100,6144) 차단기 동작시험 - 345kV #1M.Tr 3차 GIS(4189) 보통점검 - #1S.Tr GIS 보통점검","2019-10-22 10:00","2019-10-22 18:00","2019-10-22 10:00","2019-10-22 18:00","당일"]
[316,"경남","직할","신김해S/S #3 M.Tr","19년도 직할 170kV GIS 정밀점검","신김해S/S #2-1 Sh.C GCB 정밀점검 시험가압선로 : #3M.Tr , #62BUS","2019-10-01 16:30","2019-10-01 18:00","2019-10-01 16:30","2019-10-01 18:00","당일"]
[317,"경남","직할","신김해북부산#1 T/L","345kV 신김해-북부산T/L 78호 지장송전선로 이설공사","345kV 신김해-북부산T/L 77~81호 간 지장이설공사[본탑 1기, 계탑 1기]","2019-10-05 07:00","2019-10-16 18:00","취소","취소","연속"]
[318,"경남","직할","신김해S/S #3 M.Tr","19년도 직할 170kV GIS 정밀점검","신김해S/S #2-2 Sh.C GCB 정밀점검 시험가압선로 : #3M.Tr , #62BUS","2019-10-05 16:30","2019-10-05 18:00","2019-10-05 16:30","2019-10-05 18:00","당일"]
[319,"경남","직할","신김해S/S #1 M.Tr","신김해S/S #73Bay B/F PNL 대체작업","신김해S/S #73Bay B/F PNL 대체작업 [병행] 7300,7372 CB 조작시험 점검","2019-10-07 09:00","2019-10-11 18:00","2019-10-07 09:00","2019-10-11 18:00","연속"]
[320,"경남","직할","창원삼천포TP#2 T/L","345kV 창원-삼천포화력T/L 102-105호 등 5개구간 전력선 교체","전선접속개소(직선슬리브 제거) 전력선 교체 및 노후금구류(스페이서댐퍼)교체","2019-10-13 07:00","2019-10-31 18:00","2019-10-13 07:00","2019-10-31 18:00","연속"]
[321,"경남","진주","신남원의령#2 T/L","의령S/S 신남원-의령#2T/L-TIE 77 Bay B/F PNL 대체","의령S/S 신남원-의령#2T/L-TIE 77 Bay B/F PNL 대체","2019-10-28 09:00","2019-11-01 18:00","2019-10-28 09:00","2019-11-01 18:00","연속"]
[322,"경남","진주","의령신마산#2 T/L","의령S/S 의령-신마산#2T/L-TIE 7A Bay B/F PNL 대체","의령S/S 의령-신마산#2T/L-TIE 7A Bay B/F PNL 대체","2019-10-21 09:00","2019-10-25 18:00","2019-10-21 09:00","2019-10-25 18:00","연속"]
[323,"경남","진주","고령의령#2 T/L","의령S/S 345kV 75Bay B/F 보호반 대체","의령S/S 345kV 75Bay B/F 보호반 대체","2019-10-07 09:00","2019-10-11 18:00","2019-10-07 09:00","2019-10-11 18:00","연속"]
[324,"경남","진주","의령S/S #2 M.Tr","의령S/S #2M.Tr 정밀점검","의령S/S #2M.Tr 정밀점검","2019-10-07 09:00","2019-10-17 18:00","2019-10-07 09:00","2019-10-17 18:00","연속"]
[325,"경남","진주","하동T/P 광양-하동TP#2T/L-#6 M.Tr 1차 CB(7600)","하동T/P 광양-하동TP#2T/L-#6M.Tr CB(7600) 조작시험","하동T/P 광양-하동TP#2T/L-#6M.Tr CB(7600) 조작시험","2019-10-14 10:00","2019-10-14 14:00","2019-10-14 10:00","2019-10-14 14:00","당일"]
[326,"경남","진주","하동T/P 광양-하동TP#1T/L-#3 M.Tr 1차 CB(7300)","하동T/P 광양-하동TP#1T/L-#3M.Tr CB(7300) 조작시험","하동T/P 광양-하동TP#1T/L-#3M.Tr CB(7300) 조작시험","2019-10-11 10:00","2019-10-11 14:00","2019-10-11 10:00","2019-10-11 14:00","당일"]
[327,"경남","진주","하동T/P #3 M.Tr 1차 CB(7372)","하동T/P 3M.Tr 1차 CB(7372) 조작시험","하동T/P 3M.Tr 1차 CB(7372) 조작시험","2019-10-11 14:00","2019-10-11 17:00","2019-10-11 14:00","2019-10-11 17:00","당일"]
[328,"경남","진주","하동T/P #6 M.Tr 1차 CB(7672)","하동T/P #6M.Tr 1차 CB(7672) 조작시험","하동T/P #6M.Tr 1차 CB(7672) 조작시험","2019-10-14 14:00","2019-10-14 17:00","2019-10-14 14:00","2019-10-14 17:00","당일"]
[329,"경남","통영","삼천포T/P 창원#1T/L-TIE#2T/L TIE CB(7500)","삼천포,신고성S/S 용량부족차단기 대체공사","창원-삼천포화력#2T/L 인출철구 조립을 위한 안전이격거리 확보","2019-10-19 09:00","2019-10-20 18:00","2019-10-19 09:00","2019-10-20 18:00","연속"]
[330,"경남","통영","삼천포T/P 삼천포-TIE#2T/L CB(7571)","삼천포,신고성S/S 용량부족차단기 대체공사","창원-삼천포화력#2T/L 인출철구 설치를 위한 안전거리 이격확보","2019-10-19 09:00","2019-10-20 18:00","2019-10-19 09:00","2019-10-20 18:00","연속"]
[331,"경남","통영","(신)삼천포T/P 고성하이화력#1T/L CB(7A71)","(신)신고성S/S 345kV CB(7A71) 개폐장치 조작시험","(신)신고성S/S 345kV CB(7A71) 개폐장치 조작시험","2019-10-07 09:30","2019-10-07 11:30","2019-10-07 09:30","2019-10-07 11:30","당일"]
[332,"경남","통영","(신)삼천포T/P 삼천포#1T/L-고성하이#1T/L TIE CB(7A00)","(신)신고성S/S 345kV CB(7A00) 개폐장치 조작시험","(신)신고성S/S 345kV CB(7A00) 개폐장치 조작시험","2019-10-07 13:00","2019-10-07 15:30","2019-10-07 13:00","2019-10-07 15:30","당일"]
[333,"경남","통영","신고성S/S #2 M.Tr","삼천포,신고성S/S 용량부족차단기 대체공사","변압기 1차 피뢰기 이설","2019-10-24 09:00","2019-10-24 18:00","2019-10-24 09:00","2019-10-24 18:00","당일"]
[334,"경남","통영","(신)삼천포T/P 신마산-삼천포화력#1T/L CB(7A72)","(신)신고성S/S 345kV CB(7A72) 개폐장치 조작시험","(신)신고성S/S 345kV CB(7A72) 개폐장치 조작시험","2019-10-07 15:30","2019-10-07 18:00","2019-10-07 15:30","2019-10-07 18:00","당일"]
[335,"경남","통영","신고성S/S #1 M.Tr","신고성S/S 345kV #1 M.Tr 2차 GIS 조작시험 등 3건","신고성S/S 345kV #1 M.Tr 2차 GIS 조작시험 등 3건","2019-10-21 09:30","2019-10-21 18:00","2019-10-21 09:30","2019-10-22 18:00","연속"]
[336,"경남","통영","(신)신고성S/S TIE#2T/L-G4호기 TIE CB(7400)","삼천포,신고성S/S 용량부족차단기 대체공사","창원-삼천포화력#2T/L 인출철구 조립을 위한 안전이격거리 확보","2019-10-19 09:00","2019-10-20 18:00","2019-10-19 09:00","2019-10-20 18:00","연속"]
[337,"경남","통영","(신)신고성S/S 삼천포-TIE#2T/L CB(7472)","삼천포,신고성S/S 용량부족차단기 대체공사","창원-삼천포화력#2T/L 인출철구 조립을 위한 안전이격거리 확보","2019-10-19 09:00","2019-10-20 18:00","2019-10-19 09:00","2019-10-20 18:00","연속"]
[338,"경남","통영","(신)신고성S/S #4 G.Tr 1차 CB(7471)","(신)신고성S/S 345kV CB(7471) 개폐장치 조작시험","(신)신고성S/S 345kV CB(7471) 개폐장치 조작시험","2019-10-10 09:30","2019-10-10 13:00","2019-10-10 09:30","2019-10-10 18:00","당일"]
[339,"경남","통영","(신)신고성S/S SEC CB((신)75-76-0)","(신)신고성S/S 345kV CB(75-76) 개폐장치 조작시험","(신)신고성S/S 345kV CB(75-76) 개폐장치 조작시험","2019-10-08 13:00","2019-10-08 15:00","2019-10-08 13:00","2019-10-08 15:00","당일"]
[340,"경남","통영","(신)신고성S/S SEC CB((신)70-71-0)","(신)신고성S/S 345kV CB(70-71) 개폐장치 조작시험","(신)신고성S/S 345kV CB(70-71) 개폐장치 조작시험","2019-10-08 09:30","2019-10-08 11:30","2019-10-18 09:30","2019-10-18 14:00","당일"]
[341,"경남","통영","(신)신고성S/S 삼천포-TIE#2T/L CB(7472)","(신)신고성S/S 345kV CB(7472) GIS 초기점검","(신)신고성S/S 345kV CB(7472) GIS 초기점검","2019-10-04 14:00","2019-10-04 18:00","취소","취소","당일"]
[342,"경남","통영","(신)신고성S/S TIE#2T/L-G4호기 TIE CB(7400)","(신)신고성S/S 345kV CB(7400) GIS 초기점검","(신)신고성S/S 345kV CB(7400) GIS 초기점검","2019-10-04 09:30","2019-10-04 14:00","2019-10-16 09:30","2019-10-16 18:00","당일"]
[343,"경남","통영","신고성S/S #3 M.Tr","신고성S/S 345kV #3 M.Tr 3차 VCB 조작시험 등 3건","신고성S/S 345kV #3 M.Tr 3차 VCB 조작시험 등 3건","2019-10-22 09:30","2019-10-22 18:00","2019-10-24 09:30","2019-10-24 18:00","당일"]
[344,"경남","함안","신마산S/S #1 M.Tr 1차 CB(7172)","신마산S/S 345kV #1M.Tr 1차 GIS 7172 초기점검","신마산S/S 345kV #1M.Tr 1차 GIS 7172 초기점검","2019-10-16 09:30","2019-10-16 17:30","2019-10-16 09:30","2019-10-16 17:30","당일"]
[345,"경남","함안","신마산S/S 의령#1T/L-#3 M.Tr 1차 TIE CB(7300)","신마산S/S 의령#1T/L-#3M.Tr 1차 TIE 7300 초기점검","신마산S/S 의령#1T/L-#3M.Tr 1차 TIE 7300 초기점검","2019-10-18 09:30","2019-10-18 17:30","2019-10-18 09:30","2019-10-18 17:30","당일"]
[346,"경남","함안","신마산S/S #2 M.Tr 1차 CB(7272)","신마산S/S 345kV #2M.Tr 1차 GIS 7272 초기점검","신마산S/S 345kV #2M.Tr 1차 GIS 7272 초기점검","2019-10-21 09:30","2019-10-21 17:30","2019-10-21 09:30","2019-10-21 17:30","당일"]
[347,"경남","함안","신마산S/S 의령-신마산#1T/L CB(7371)","신마산S/S 345kV 의령-신마산#1T/L GIS 7371 초기점검","신마산S/S 345kV 의령-신마산#1T/L GIS 7371 초기점검","2019-10-17 09:30","2019-10-17 17:30","2019-10-17 09:30","2019-10-17 17:30","당일"]
[348,"경남","함안","신마산S/S #3 M.Tr 1차 CB(7372)","신마산S/S 345kV #3M.Tr 1차 GIS 7372 초기점검","신마산S/S 345kV #3M.Tr 1차 GIS 7372 초기점검","2019-10-24 09:30","2019-10-24 17:30","2019-10-24 09:30","2019-10-24 17:30","당일"]
[349,"경남","함안","신마산S/S #4 M.Tr 1차 CB A (7472)","신마산S/S 345kV #4M.Tr 1차 GIS 7472 초기점검","신마산S/S 345kV #4M.Tr 1차 GIS 7472 초기점검","2019-10-29 09:30","2019-10-29 17:30","2019-10-29 09:30","2019-10-29 17:30","당일"]
[350,"광주전남",null,"광양#2CC 주변압기(7100,7172,7200,7272)","계획예방정비 공사","계획예방정비 공사","2019-10-03 09:00","2019-10-09 18:00","2019-10-03 09:00","2019-10-09 18:00","연속"]
[351,"부산울산",null,"고리NP S/Y 345kV #76 BUS","GIS 구조개선 관련 시험가압","GIS 구조개선 관련 시험가압","2019-10-01 13:00","2019-10-02 13:00","2019-10-01 13:00","2019-10-02 13:00","연속"]
[352,"강원",null,"양양양수#1,2,3,4M.Tr CB(7100,7172,7200,7271,7272,7300,7372)","자체기동발전기 자체시험","자체기동발전기 자체시험","2019-10-10 10:00","2019-10-10 12:00","2019-10-10 10:00","2019-10-10 12:00","연속"]
[353,"경북",null,"예천양수1호기 주변압기(7100,7172)","A급 계획예방정비 공사","A급 계획예방정비 공사","2019-10-03 08:00","2021-01-05 20:00","2019-10-03 08:00","2021-01-05 20:00","연속"]

{"sheet":"154송부","index":3,"n_rows":530,"n_cols":13,"rows_kept":530,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 10월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","도봉방학#2 T/L","2019-20년 성동 지중송전 위탁정비공사 C/H 및 피뢰기 점검","가. 작업내용 : 피뢰기 절연열화 측정, 누설전류 및 절연저항 측정 피뢰기, EBA 애관청소 및 단자조임 EBA 절연저항 및 절연유 누유여부 점검 나. 작업장소 : 도봉S/S 스위치야드","2019-10-25 09:00","2019-10-25 18:00","2019-10-25 09:00","2019-10-25 18:00","당일"]
[2,"서울","성동","도봉방학#1 T/L","2019-20년 성동 지중송전 위탁정비공사 C/H 및 피뢰기 점검","가. 작업내용 : 피뢰기 절연열화 측정, 누설전류 및 절연저항 측정 피뢰기, EBA 애관청소 및 단자조임 EBA 절연저항 및 절연유 누유여부 점검 나. 작업장소 : 도봉S/S 스위치야드 다. 시행업체 : 대한전선(성동 지중송전 위탁회사)","2019-10-24 09:00","2019-10-24 18:00","2019-10-24 09:00","2019-10-24 18:00","당일"]
[3,"서울","성동","성동S/S 154kV #61 BUS","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-10-15 15:30","2019-10-15 17:30","2019-10-15 15:30","2019-10-15 17:30","당일"]
[4,"서울","성동","성동S/S 154kV #65-#66 SEC GIS","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-10-01 08:00","2019-10-02 17:30","2019-10-01 08:00","2019-10-02 17:30","연속"]
[5,"서울","성동","성동S/S 154kV #65 BUS","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-10-02 15:30","2019-10-02 17:30","2019-10-02 15:30","2019-10-02 17:30","당일"]
[6,"서울","성동","성동S/S 154kV #60 BUS","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-10-08 15:30","2019-10-08 17:30","2019-10-08 15:30","2019-10-08 17:30","당일"]
[7,"서울","성동","군자성수 T/L","154kV 성수S/S #3M.Tr 증설공사","154kV GIS 모선 증설분 시험가압","2019-10-11 09:00","2019-10-12 18:00","2019-10-11 09:00","2019-10-12 18:00","연속"]
[8,"서울","성동","군자성수 T/L","154kV 성수S/S #3M.Tr 증설공사","154kV GIS 모선 증설분 시험가압","2019-10-08 09:00","2019-10-09 18:00","2019-10-08 09:00","2019-10-09 18:00","연속"]
[9,"서울","성동","양주쌍문#2 T/L","2019-20년 성동 지중송전 위탁정비공사 C/H 및 피뢰기 점검","가. 작업내용 : 피뢰기 절연열화 측정, 누설전류 및 절연저항 측정 피뢰기, EBA 애관청소 및 단자조임 EBA 절연저항 및 절연유 누유여부 점검 나. 작업장소 : 쌍문C/H 다. 시행업체 : 대한전선(성동 지중송전 위탁회사)","2019-10-29 09:00","2019-10-29 18:00","2019-10-29 09:00","2019-10-29 18:00","당일"]
[10,"서울","성동","양주쌍문#1 T/L","2019-20년 성동 지중송전 위탁정비공사 C/H 및 피뢰기 점검","가. 작업내용 : 피뢰기 절연열화 측정, 누설전류 및 절연저항 측정 피뢰기, EBA 애관청소 및 단자조임 EBA 절연저항 및 절연유 누유여부 점검 나. 작업장소 : 쌍문C/H 다. 시행업체 : 대한전선(성동 지중송전 위탁회사)","2019-10-28 09:00","2019-10-28 18:00","2019-10-28 09:00","2019-10-28 18:00","당일"]
[11,"서울","성동","창동쌍문#2 T/L","19년 성동P/O 장기사용 노후배전반 교체공사","창동, 쌍문S/S 창동쌍문#2T/L 보호배전반 노후대체","2019-10-21 10:00","2019-10-24 17:00","2019-10-21 10:00","2019-10-24 17:00","연속"]
[12,"서울","성동","창동쌍문#1 T/L","19년 성동P/O 장기사용 노후배전반 교체공사","창동, 쌍문S/S 창동쌍문#1T/L 보호배전반 노후대체","2019-10-28 10:00","2019-10-31 17:00","2019-10-28 10:00","2019-10-31 17:00","연속"]
[13,"서울","성동","미금화양 T/L","19년 성동P/O 장기사용 노후배전반 교체공사","화양S/S 미금화양T/L 보호배전반 노후대체","2019-10-14 10:00","2019-10-16 17:00","2019-10-14 10:00","2019-10-16 17:00","연속"]
[14,"서울","중부","동빙고반포#1 T/L","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사","2019-10-14 09:00","2019-10-15 18:00","2019-10-14 09:00","2019-10-15 18:00","연속"]
[15,"서울","중부","동빙고S/S 154kV #60 BUS","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사","2019-10-15 17:00","2019-10-15 18:00","2019-10-15 17:00","2019-10-15 18:00","당일"]
[16,"서울","중부","수색상암#1 T/L","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사","2019-10-24 09:00","2019-10-26 18:00","2019-10-24 09:00","2019-10-26 18:00","연속"]
[17,"서울","중부","수색S/S 154kV #65 BUS","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사","2019-10-26 17:00","2019-10-26 18:00","2019-10-26 17:00","2019-10-26 18:00","연속"]
[18,"서울","중부","수색S/S 154kV #60 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 수색S/S 154kV 수색상암#1T/L #1, 2DS 및 Line DS 보통점검","2019-10-26 10:00","2019-10-26 14:00","2019-10-26 10:00","2019-10-26 14:00","당일"]
[19,"서울","중부","수색S/S 154kV #65 BUS","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사","2019-10-19 17:00","2019-10-19 18:00","2019-10-19 17:00","2019-10-19 18:00","연속"]
[20,"서울","중부","수색S/S 154kV #65 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 수색S/S 154kV 수색상암#1T/L #1, 2DS 및 Line DS 보통점검","2019-10-26 14:00","2019-10-26 18:00","2019-10-26 14:00","2019-10-26 18:00","당일"]
[21,"서울","중부","중부용산#2 T/L","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사","2019-10-08 17:00","2019-10-08 18:00","2019-10-08 17:00","2019-10-08 18:00","당일"]
[22,"서울","중부","중부용산#1 T/L","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사","2019-10-11 17:00","2019-10-11 18:00","2019-10-11 17:00","2019-10-11 18:00","당일"]
[23,"서울","중부","중부용산#2 T/L","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사","2019-10-04 17:00","2019-10-04 18:00","2019-10-04 17:00","2019-10-04 18:00","당일"]
[24,"서울","중부","은평S/S 154kV #60 BUS","은평S/S 170kV GIS 대체공사(2차분)","은평S/S 170kV GIS 대체공사(2차분) - 수색은평#2T/L, #4M.Tr 1차 GIS","2019-10-28 09:00","2019-11-06 13:00","2019-10-28 09:00","2019-11-06 13:00","연속"]
[25,"서울","중부","은평S/S 154kV #60 BUS","은평S/S 170kV GIS 대체공사(1차분)","은평S/S 170kV GIS 대체공사(1차분) - 은평녹번T/L, 은평세종로T/L GIS","2019-10-02 09:00","2019-10-11 13:00","2019-10-02 09:00","2019-10-11 13:00","연속"]
[26,"서울","중부","은평S/S 154kV #65 BUS","은평S/S 170kV GIS 대체공사(1차분)","은평S/S 170kV GIS 대체공사(1차분) - 은평녹번T/L, 은평세종로T/L GIS","2019-10-11 13:00","2019-10-23 17:00","2019-10-11 13:00","2019-10-23 17:00","연속"]
[27,"서울","중부","중부S/S 154kV #66 BUS","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사","2019-10-01 17:00","2019-10-01 18:00","2019-10-01 17:00","2019-10-01 18:00","당일"]
[28,"서울","직할","종로서소문 T/L","19년 직할 변전소 170kV GIS 정밀점검공사","GIS 정밀점검","2019-10-21 09:00","2019-10-23 18:00","2019-10-21 09:00","2019-10-23 18:00","연속"]
[29,"남서울","강남","논일역삼#1 T/L","논일-역삼#1T/L GIS 설비점검","논일S/S : 논일-역삼#1T/L GIS 하자점검 역삼S/S : 논일-역삼#1T/L GIS 개폐타임측정","2019-10-30 09:00","2019-10-30 18:00","2019-10-30 09:00","2019-10-30 18:00","당일"]
[30,"남서울","강남","논현논일#2 T/L","논현,논일S/S 논현-논일#2T/L GIS 보통점검","논현,논일S/S 논현-논일#2T/L GIS 보통점검","2019-10-29 09:00","2019-10-29 18:00","2019-10-27 09:00","2019-10-27 18:00","당일"]
[31,"남서울","강남","논현논일#1 T/L","논현,논일S/S 논현-논일#1T/L GIS 보통점검","논현,논일S/S 논현-논일#1T/L GIS 보통점검","2019-10-28 09:00","2019-10-28 18:00","2019-10-26 09:00","2019-10-26 18:00","당일"]
[32,"남서울","강남","동빙고반포#2 T/L","동빙고-반포#2T/L 170kV GIS 정밀점검","동빙고-반포#2T/L 170kV GIS 정밀점검","2019-10-17 09:00","2019-10-19 18:00","2019-10-21 09:00","2019-10-23 18:00","연속"]
[33,"남서울","강남","동빙고반포#1 T/L","동빙고-반포#1T/L 170kV GIS 정밀점검","동빙고-반포#1T/L 170kV GIS 정밀점검","2019-10-14 09:00","2019-10-16 18:00","2019-10-16 09:00","2019-10-18 18:00","연속"]
[34,"남서울","강남","신사S/S 154kV #60-#65 BUS TIE GIS","신사S/S 154kV Bustie GIS 개폐타임측정, 전자변 교체","신사S/S 154kV Bustie GIS 개폐타임측정, 전자변 교체","2019-10-23 09:00","2019-10-23 18:00","2019-10-24 09:00","2019-10-24 18:00","당일"]
[35,"남서울","강남","신양재신사#2 T/L","신양재-신사#2T/L GIS 개폐타임측정,전자변 교체","신사S/S 신양재-신사#2T/L GIS 개폐타임측정,전자변 교체 신양재S/S 신양재-신사#2T/L GIS 개폐타임측정,전자변 교체","2019-10-11 14:00","2019-10-11 18:00","2019-10-11 14:00","2019-10-11 18:00","당일"]
[36,"남서울","강남","신양재신사#1 T/L","신양재-신사#1T/L GIS 개폐타임측정,전자변 교체","신사S/S 신양재-신사#1T/L GIS 개폐타임측정,전자변 교체 신양재S/S 신양재-신사#1T/L GIS 개폐타임측정,전자변 교체","2019-10-11 09:00","2019-10-11 14:00","2019-10-11 09:00","2019-10-11 14:00","당일"]
[37,"남서울","강남","신양재역삼#1 T/L","신양재-역삼#1T/L 170kV GIS 정밀점검","신양재-역삼#1T/L 170kV GIS 정밀점검","2019-10-07 09:00","2019-10-09 18:00","2019-10-07 09:00","2019-10-09 18:00","연속"]
[38,"남서울","강남","신양재역삼#2 T/L","신양재-역삼#2T/L 170kV GIS 정밀점검","신양재-역삼#2T/L 170kV GIS 정밀점검","2019-10-10 09:00","2019-10-12 18:00","2019-10-10 09:00","2019-10-12 18:00","연속"]
[39,"남서울","동서울","동서울송파#2 T/L","동서울S/S 154kV 현대화 공사","○ T-BUS DS 철거 및 인출Lead 직결 ○ LA 및 CVT 이설","2019-10-21 08:30","2019-10-22 17:00","2019-10-21 08:30","2019-10-22 17:00","연속"]
[40,"남서울","동서울","동서울가락#2 T/L","동서울S/S 154kV 현대화 공사","○ T-BUS DS 철거 및 인출Lead 직결 ○ LA 및 CVT 이설","2019-10-14 08:30","2019-10-16 17:00","2019-10-14 08:30","2019-10-16 17:00","연속"]
[41,"남서울","동서울","동서울가락#1 T/L","동서울S/S 154kV 현대화 공사","○ T-BUS DS 철거 및 인출Lead 직결 ○ LA 및 CVT 이설","2019-10-17 08:30","2019-10-18 17:00","2019-10-17 08:30","2019-10-18 17:00","연속"]
[42,"남서울","동서울","동서울송파#1 T/L","동서울S/S 154kV 현대화 공사","○ T-BUS DS 철거 및 인출Lead 직결 ○ LA 및 CVT 이설","2019-10-23 08:30","2019-10-25 17:00","2019-10-23 08:30","2019-10-25 17:00","연속"]
[43,"남서울","동서울","동서울강동#2 T/L","동서울S/S 154kV 현대화 공사","○ T-BUS DS 철거 및 인출Lead 직결 ○ LA 및 CVT 이설","2019-10-28 08:30","2019-10-29 17:00","2019-10-28 08:30","2019-10-29 17:00","연속"]
[44,"남서울","동서울","동서울신장#2 T/L","동서울S/S 154kV 현대화 공사","○ T-BUS DS 철거 및 인출Lead 직결 ○ LA 및 CVT 이설","2019-10-30 08:30","2019-10-31 17:00","2019-10-30 08:30","2019-10-31 17:00","연속"]
[45,"남서울","동서울","동서울강동#1 T/L","동서울S/S 154kV 현대화 공사","○ T-BUS DS 철거 및 인출Lead 직결 ○ LA 및 CVT 이설","2019-10-30 08:30","2019-10-31 17:00","2019-10-30 08:30","2019-10-31 17:00","연속"]
[46,"남서울","동서울","동서울신장#1 T/L","동서울S/S 154kV 현대화 공사","○ T-BUS DS 철거 및 인출Lead 직결 ○ LA 및 CVT 이설","2019-10-21 10:00","2019-10-22 13:00","취소","취소","연속"]
[47,"남서울","동서울","동서울서종#2 T/L","동서울S/S 154kV 현대화 공사","○ T-BUS DS 철거 및 인출Lead 직결 ○ LA 및 CVT 이설","2019-10-21 10:00","2019-10-22 13:00","취소","취소","연속"]
[48,"남서울","동서울","동서울서종#1 T/L","동서울S/S 154kV 현대화 공사","○ T-BUS DS 철거 및 인출Lead 직결 ○ LA 및 CVT 이설","2019-10-22 13:00","2019-10-23 17:00","취소","취소","연속"]
[49,"남서울","동서울","강동풍납#1 T/L","154kV 강동-풍납T/L 풍납S/S 인출구간 선종교체공사","풍납S/S 인출구간내 OF케이블을 XLPE케이블로 교체설치","2019-10-01 09:00","2019-11-15 18:00","취소","취소","연속"]
[50,"남서울","영등포","신광명광명#2 T/L","신광명S/S 170kV GIS 하자보수(접합부 크랙)","-효성 제작사 하자보수","2019-10-02 13:00","2019-10-02 15:00","취소","취소","당일"]
[51,"남서울","영등포","신광명시흥#1 T/L","신광명S/S 170kV GIS 하자보수(접합부 크랙)","-효성 제작사 하자보수","2019-10-01 10:00","2019-10-01 12:00","취소","취소","당일"]
[52,"남서울","영등포","신광명광명#1 T/L","신광명S/S 170kV GIS 하자보수(접합부 크랙)","-효성 제작사 하자보수","2019-10-02 10:00","2019-10-02 12:00","취소","취소","당일"]
[53,"남서울","영등포","신광명소래 T/L","신광명S/S 170kV GIS 하자보수(접합부 크랙)","-효성 제작사 하자보수","2019-10-01 15:00","2019-10-01 17:00","2019-10-01 15:00","2019-10-01 17:00","당일"]
[54,"남서울","영등포","신광명시흥#2 T/L","신광명S/S 170kV GIS 하자보수(접합부 크랙)","-효성 제작사 하자보수","2019-10-01 13:00","2019-10-01 15:00","취소","취소","당일"]
[55,"남서울","영등포","온수소래 T/L","154kV 온수-소래T/L 정밀점검","점검대상 : 154kV 신광명-소래T/L(No.1~22) 휴전회선명 : 온수-소래T/L(병가선로 서안양-소래T/L)","2019-10-16 07:00","2019-10-17 18:00","2019-10-19 07:00","2019-10-20 18:00","연속"]
[56,"남서울","영등포","중동화곡#2 T/L","154kV 송전선로보호반 대체(양단)","중동S/S, 화곡S/S 중동-화곡#2T/L 송전선로보호반 대체","2019-10-21 09:00","2019-10-25 18:00","취소","취소","연속"]
[57,"남서울","직할","신길S/S 154kV #65 BUS","직할 170kV GIS 정밀점검(무부하)","직할 170kV GIS #3M.Tr (정밀점검 무부하선로)","2019-10-29 18:00","2019-10-30 14:00","2019-10-29 18:00","2019-10-30 14:00","연속"]
[58,"남서울","직할","신길S/S 154kV #65 BUS","직할 170kV GIS 정밀점검(무부하)","직할 170kV GIS #4M.Tr (정밀점검 무부하선로)","2019-10-31 18:00","2019-11-01 18:00","2019-10-31 18:00","2019-11-01 18:00","연속"]
[59,"남서울","직할","봉천신길#2 T/L","직할 170kV GIS 정밀점검(무부하)","직할 170kV GIS #3M.Tr (정밀점검 무부하선로)","2019-10-29 18:00","2019-10-30 14:00","2019-10-29 18:00","2019-10-30 14:00","연속"]
[60,"남서울","직할","봉천신길#2 T/L","직할 170kV GIS 정밀점검(무부하)","직할 170kV GIS #4M.Tr (정밀점검 무부하선로)","2019-10-31 18:00","2019-11-01 18:00","2019-10-31 18:00","2019-11-01 18:00","연속"]
[61,"남서울","직할","영등포S/S 154kV #66 BUS","직할 170kV GIS 정밀점검","직할 170kV GIS 정밀점검(6200 BUS TIE, 65-66 BUS SEC) 및 66BUS LA 점검","2019-10-14 09:00","2019-10-18 18:00","2019-10-14 09:00","2019-10-18 18:00","연속"]
[62,"남서울","직할","영등포S/S 154kV #60 BUS","직할 170kV GIS 정밀점검(무부하)","직할 170kV GIS 60-65 BUS TIE(정밀점검 무부하선로)","2019-10-22 18:00","2019-10-23 14:00","2019-10-22 18:00","2019-10-23 14:00","연속"]
[63,"남서울","직할","영등포S/S 154kV #60-#61 SEC CB","직할 170kV GIS 정밀점검","직할 170kV GIS 정밀점검","2019-10-23 14:00","2019-10-25 18:00","2019-10-23 14:00","2019-10-25 18:00","연속"]
[64,"남서울","직할","영등포영오 T/L","직할 170kV GIS 정밀점검(무부하)","직할 170kV GIS (60-61 SEC 정밀점검 무부하)","2019-10-24 18:00","2019-10-25 18:00","2019-10-24 18:00","2019-10-25 18:00","연속"]
[65,"남서울","직할","영등포S/S 154kV #61 BUS","직할 170kV GIS 정밀점검(무부하)","직할 170kV GIS (60-61 SEC 정밀점검 무부하)","2019-10-24 18:00","2019-10-25 18:00","2019-10-24 18:00","2019-10-25 18:00","연속"]
[66,"남서울","직할","영등포S/S 154kV #60-#65 BUS TIE CB","직할 170kV GIS 정밀점검","직할 170kV GIS 정밀점검","2019-10-21 09:00","2019-10-23 14:00","2019-10-21 09:00","2019-10-23 14:00","연속"]
[67,"남서울","직할","영등포영오 T/L","직할 170kV GIS 정밀점검(무부하)","직할 170kV GIS 60-65 BUS TIE(정밀점검 무부하선로)","2019-10-22 18:00","2019-10-23 14:00","2019-10-22 18:00","2019-10-23 14:00","연속"]
[68,"인천","김포","경서양촌#1 T/L","경서S/S 170kV GIS 개조공사","○ 경서S/S 170kV GIS 개조공사(무부하 시행) - #3M.Tr, #4M.Tr 1차 GIS 철거 - #3M.Tr, #4M.Tr 1차 GIS 개조 및 설치 - 기타부대공사 1식","2019-10-22 15:00","2019-10-23 15:00","2019-10-22 15:00","2019-10-23 15:00","연속"]
[69,"인천","김포","경서S/S 154kV #60 BUS","경서S/S 170kV GIS 개조공사","○ 경서S/S 170kV GIS 개조공사 - #3M.Tr, #4M.Tr 1차 GIS 철거 - #3M.Tr, #4M.Tr 1차 GIS 개조 및 설치 - 기타부대공사 1식","2019-10-16 08:00","2019-10-23 15:00","2019-10-16 08:00","2019-10-23 15:00","연속"]
[70,"인천","김포","경서S/S 154kV #65 BUS","경서S/S 170kV GIS 개조공사","○ 경서S/S 170kV GIS 개조공사 - #3M.Tr, #4M.Tr 1차 GIS 철거 - #3M.Tr, #4M.Tr 1차 GIS 개조 및 설치 - 기타부대공사 1식","2019-10-14 08:00","2019-10-15 18:00","2019-10-14 08:00","2019-10-15 18:00","연속"]
[71,"인천","김포","경서S/S 154kV #65 BUS","경서S/S 170kV GIS 개조공사","○ 경서S/S 170kV GIS 개조공사 - #3M.Tr, #4M.Tr 1차 GIS 철거 - #3M.Tr, #4M.Tr 1차 GIS 개조 및 설치 - 기타부대공사 1식","2019-10-23 15:00","2019-11-02 18:00","2019-10-23 15:00","2019-11-02 18:00","연속"]
[72,"인천","김포","신김포장기#1 T/L","신김포S/S 154kV 신김포-장기#1T/L 보호반 대체공사","1. 신김포S/S 154kV 신김포-장기#1T/L 보호반 대체공사 2. 장기S/S 154kV 신김포-장기#1T/L 보호반 대체공사","2019-10-14 09:00","2019-10-18 18:00","2019-10-14 09:00","2019-10-18 18:00","연속"]
[73,"인천","김포","신김포양곡#1 T/L","345kV 신김포S/S #63D.Tr 증설공사","345kV 신김포S/S #63D.Tr 증설공사 - #60BUS 무부하가압","2019-10-24 09:00","2019-10-25 18:00","2019-10-24 09:00","2019-10-25 18:00","연속"]
[74,"인천","김포","신김포S/S 154kV #60 BUS","345kV 신김포S/S #63D.Tr 증설공사","345kV 신김포S/S #63D.Tr 증설공사 - 170kV GIS 4CCT","2019-10-21 09:00","2019-10-25 18:00","2019-10-21 09:00","2019-10-25 18:00","연속"]
[75,"인천","김포","신김포S/S 154kV #65 BUS","345kV 신김포S/S #63D.Tr 증설공사","345kV 신김포S/S #63D.Tr 증설공사 - 170kV GIS 4CCT","2019-10-28 09:00","2019-11-01 18:00","2019-10-28 09:00","2019-11-01 18:00","연속"]
[76,"인천","김포","신김포양곡#1 T/L","345kV 신김포S/S #63D.Tr 증설공사","345kV 신김포S/S #63D.Tr 증설공사 - #65BUS 무부하가압","2019-10-31 09:00","2019-11-01 18:00","2019-10-31 09:00","2019-11-01 18:00","연속"]
[77,"인천","부평","주안관교#2 T/L","154kV 만수분기(증) 지중T/L 건설공사","○ 구 간 : 154㎸ 만수변전소 ~ M/H#19 ○ 선종/회선길이 : 154㎸ XLPE 1,200㎟, 2회선-3.0㎞ ○ 공 사 기 간 : 2018. 12 ~ 2019. 07 ○ 준 공 목 표 : 2019년 07월","2019-10-14 10:00","2019-11-10 18:00","2019-10-17 10:00","2019-11-13 18:00","연속"]
[78,"인천","부평","관교만수 T/L","154kV 만수S/S S.W 증설공사","- 154kV GIS(5CCT) 설치","2019-10-18 17:30","2019-10-18 18:00","2019-10-18 17:30","2019-10-18 18:00","당일"]
[79,"인천","부평","관교만수 T/L","154kV 만수S/S S.W 증설공사","- 154kV GIS(5CCT) 설치","2019-10-03 13:00","2019-10-03 13:30","2019-10-03 13:00","2019-10-03 13:30","당일"]
[80,"인천","부평","신가좌부개#1 T/L","부개S/S 신가좌부개#1T/L 장기미동작차단기 조작시험","부개S/S 신가좌부개#1T/L 장기미동작차단기 조작시험","2019-10-15 09:30","2019-10-15 13:00","취소","취소","연속"]
[81,"인천","부평","부흥부개#1 T/L","부개S/S 부흥부개#1T/L 장기미동작차단기 조작시험","부개S/S 부흥부개#1T/L 장기미동작차단기 조작시험","2019-10-17 09:30","2019-10-17 13:00","2019-10-17 09:30","2019-10-17 13:00","연속"]
[82,"인천","부평","신가좌부개#2 T/L","부개S/S 신가좌부개#2T/L 장기미동작차단기 조작시험","부개S/S 신가좌부개#2T/L 장기미동작차단기 조작시험","2019-10-15 13:00","2019-10-15 18:00","취소","취소","연속"]
[83,"인천","부평","부흥부개#2 T/L","부개S/S 부흥부개#2T/L 장기미동작차단기 조작시험","부개S/S 부흥부개#2T/L 장기미동작차단기 조작시험","2019-10-17 13:00","2019-10-17 18:00","2019-10-17 13:00","2019-10-17 18:00","연속"]
[84,"인천","부평","서인천C/C 154kV #66 BUS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","서인천복합S/Y #8G.Tr GIS(6833) 정밀점검 관련 무부하가압용","2019-10-17 13:00","2019-10-17 18:00","2019-10-17 13:00","2019-10-17 18:00","당일"]
[85,"인천","부평","서인천C/C 154kV #60-#61 SEC GIS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","서인천복합S/Y 60-61 BUS SEC GIS 정밀점검 1) 170㎸ GIS 정밀점검 × 1식 2) 기타 부대작업 × 1식","2019-10-30 09:00","2019-11-01 18:00","2019-10-30 09:00","2019-11-01 18:00","연속"]
[86,"인천","부평","서인천C/C 154kV #66 BUS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","서인천복합S/Y #7G.Tr GIS(6733) 정밀점검 관련 무부하가압용","2019-10-24 13:00","2019-10-24 18:00","2019-10-24 13:00","2019-10-24 18:00","당일"]
[87,"인천","부평","서인천C/C 154kV #61-#66 BUS TIE GIS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","서인천복합S/Y #8G.Tr GIS(6833) 정밀점검 관련 무부하가압용","2019-10-17 13:00","2019-10-17 18:00","2019-10-17 13:00","2019-10-17 18:00","당일"]
[88,"인천","부평","서인천C/C 154kV #7 G.Tr 1차 GIS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","서인천복합S/Y #7G.Tr GIS(6733) 정밀점검 1) 170㎸ GIS 정밀점검 × 1식 2) 기타 부대작업 × 1식","2019-10-22 09:00","2019-10-24 18:00","2019-10-22 09:00","2019-10-24 18:00","연속"]
[89,"인천","부평","서인천C/C 154kV #8 G.Tr 1차 GIS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","서인천복합S/Y #8G.Tr GIS(6833) 정밀점검 1) 170㎸ GIS 정밀점검 × 1식 2) 기타 부대작업 × 1식","2019-10-10 09:00","2019-10-17 18:00","2019-10-10 09:00","2019-10-17 18:00","연속"]
[90,"인천","부평","서인천C/C 154kV #61-#66 BUS TIE GIS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","서인천복합S/Y #7G.Tr GIS(6733) 정밀점검 관련 무부하가압용","2019-10-24 13:00","2019-10-24 18:00","2019-10-24 13:00","2019-10-24 18:00","당일"]
[91,"인천","부평","신가좌주안#1 T/L","신가좌주안#1 T/L 보호계전기 성능개선","㈜선도전기 송전선로 보호계전기 통신회로 loop시 오동작 방지","2019-10-08 09:00","2019-10-08 13:00","취소","취소","당일"]
[92,"인천","부평","신가좌주안#2 T/L","신가좌주안#2 T/L 보호계전기 성능개선","㈜선도전기 송전선로 보호계전기 통신회로 loop시 오동작 방지","2019-10-08 13:00","2019-10-08 18:00","취소","취소","당일"]
[93,"인천","부평","신현포스코CC#2 T/L","신현-포스코CC 선로정수 측정 및 보호계전기 정정값 반영","지중송전선로 병행지선 설치보강 후 선로정수 변동분 반영으로 계전기 오동작 방지[계통운영부 시험파트에서 반영 시행]","2019-10-29 13:30","2019-10-29 18:00","2019-10-29 13:30","2019-10-29 18:00","당일"]
[94,"인천","부평","신현포스코CC#1 T/L","신현-포스코CC 선로정수 측정 및 보호계전기 정정값 반영","지중송전선로 병행지선 설치보강 후 선로정수 변동분 반영으로 계전기 오동작 방지[계통운영부 시험파트에서 반영 시행]","2019-10-29 09:00","2019-10-29 13:00","2019-10-29 09:00","2019-10-29 13:00","당일"]
[95,"인천","부평","신현송현#2 T/L","신현-송현 선로정수 측정 및 보호계전기 정정값 반영","지중송전선로 병행지선 설치보강 후 선로정수 변동분 반영으로 계전기 오동작 방지[계통운영부 시험파트에서 반영 시행]","2019-10-28 13:30","2019-10-28 18:00","2019-10-28 13:30","2019-10-28 18:00","당일"]
[96,"인천","부평","신현송현#1 T/L","신현-송현 선로정수 측정 및 보호계전기 정정값 반영","지중송전선로 병행지선 설치보강 후 선로정수 변동분 반영으로 계전기 오동작 방지[계통운영부 시험파트에서 반영 시행]","2019-10-28 09:00","2019-10-28 13:00","2019-10-28 09:00","2019-10-28 13:00","당일"]
[97,"인천","부평","원창포스코CC#2 T/L","원창-포스코CC 선로정수 측정 및 보호계전기 정정값 반영","지중송전선로 병행지선 설치보강 후 선로정수 변동분 반영으로 계전기 오동작 방지[계통운영부 시험파트에서 반영 시행]","2019-10-04 13:30","2019-10-04 18:00","2019-10-04 13:30","2019-10-04 18:00","당일"]
[98,"인천","부평","원창포스코CC#1 T/L","원창-포스코CC 선로정수 측정 및 보호계전기 정정값 반영","지중송전선로 병행지선 설치보강 후 선로정수 변동분 반영으로 계전기 오동작 방지[계통운영부 시험파트에서 반영 시행]","2019-10-04 09:00","2019-10-04 13:00","2019-10-04 09:00","2019-10-04 13:00","당일"]
[99,"인천","부평","인천CC북인천#1 T/L","인천CC 154kV S/W 증설공사","- GIS(170kV 50KA 2000A) X 1CCT 설치","2019-10-24 10:00","2019-10-25 17:00","2019-10-24 10:00","2019-10-25 17:00","연속"]
[100,"인천","부평","인천T/P 154kV #66 BUS","인천CC 154kV S/W 증설공사","- GIS(170kV 50KA 2000A) X 1CCT 설치","2019-10-24 10:00","2019-10-25 17:00","2019-10-24 10:00","2019-10-25 17:00","연속"]
[101,"인천","부평","인천CC북인천#1 T/L","북인천S/S,인천CC 인천CC북인천#1T/L 보호반 대체공사","-북인천S/S 인천CC북인천#1T/L 보호반 대체공사 -인천CC 인천CC북인천#1T/L 보호반 대체공사","2019-10-28 09:00","2019-11-01 18:00","2019-10-28 09:00","2019-11-01 18:00","연속"]
[102,"인천","시흥","신시흥남동#2 T/L","154kV 신시흥-남동#2T/L 절연유 채유","154kV 신시흥-남동#2T/L 절연유 채유","2019-10-14 09:00","2019-10-16 18:00","2019-10-14 09:00","2019-10-16 18:00","매일"]
[103,"인천","시흥","도림오봉#2 T/L","154kV 도림오봉#2T/L 선로정수 측정","154kV 도림오봉#2T/L 병행지선 설치관련 선로정수 측정","2019-10-01 10:00","2019-10-01 13:00","2019-10-01 10:00","2019-10-01 13:00","당일"]
[104,"인천","시흥","시화동시화#1 T/L","154kV 시화-동시화#1T/L 선로정수 측정","154kV 시화-동시화1T/L 병행지선 설치관련 선로정수 측정","2019-10-08 10:00","2019-10-08 13:00","2019-10-20 10:00","2019-10-20 13:00","당일"]
[105,"인천","시흥","시화동시화#2 T/L","154kV 시화-동시화#2T/L 선로정수 측정","154kV 시화-동시화#2T/L 병행지선 설치관련 선로정수 측정","2019-10-08 13:00","2019-10-08 16:00","2019-10-20 13:00","2019-10-20 16:00","당일"]
[106,"인천","시흥","북시화서시화#1 T/L","북시화서시화#1 T/L 보호계전기 성능개선","㈜선도전기 송전선로 보호계전기 통신회로 loop시 오동작 방지","2019-10-07 09:00","2019-10-07 13:00","2019-10-07 09:00","2019-10-07 13:00","당일"]
[107,"인천","시흥","북시화서시화#2 T/L","북시화서시화#2 T/L 보호계전기 성능개선","㈜선도전기 송전선로 보호계전기 통신회로 loop시 오동작 방지","2019-10-07 14:00","2019-10-07 18:00","2019-10-07 14:00","2019-10-07 18:00","당일"]
[108,"인천","시흥","서안양소래 T/L","154kV 온수-소래T/L 정밀점검","점검대상 : 154kV 신광명-소래T/L(No.1~22) 휴전회선명 : 서안양소래T/L 휴전사유 : 온수-소래T/L과 병가","2019-10-16 07:00","2019-10-17 18:00","2019-10-19 07:00","2019-10-20 18:00","연속"]
[109,"인천","시흥","서안양소래 T/L","154kV 서서울소래T/L OPGW 항공장애표시구 시설공사","154kV 서서울소래T/L(OPGW) 항공장애표시구 설치공사 - 설치구간 OPGW 1조 이므로 양회선 동시휴전 필요 - 서서울2소래(좌)-서서울2서안양(우), 서서울2소래(좌)-서안양소래(우)","2019-10-15 14:00","2019-10-15 18:00","2019-10-15 14:00","2019-10-15 18:00","당일"]
[110,"인천","시흥","서서울#2소래 T/L","154kV 서서울소래T/L OPGW 항공장애표시구 시설공사","154kV 서서울소래T/L(OPGW) 항공장애표시구 설치공사 - 설치구간 OPGW 1조 이므로 양회선 동시휴전 필요 - 서서울2소래(좌)-서서울2서안양(우), 서서울2소래(좌)-서안양소래(우)","2019-10-15 08:00","2019-10-15 18:00","2019-10-15 08:00","2019-10-15 18:00","당일"]
[111,"인천","시흥","신시흥도림#2 T/L","154kV 신시흥도림#2T/L 선로정수 측정","154kV 신시흥도림#2T/L 병행지선 설치관련 선로정수 측정","2019-10-01 13:00","2019-10-01 16:00","2019-10-01 13:00","2019-10-01 16:00","당일"]
[112,"인천","직할","신부평임학#2 T/L","신부평,임학S/S 170kV 신부평임학#2T/L 차단기 조작시험","신부평,임학S/S 170kV 신부평임학#2T/L 차단기 조작시험","2019-10-25 09:30","2019-10-25 18:00","2019-10-25 09:30","2019-10-25 18:00","당일"]
[113,"인천","직할","신부평중동#2 T/L","신부평S/S 170kV 신부평중동#2T/L 장기미동작 차단기 조작시험","신부평S/S 170kV 신부평중동#2T/L 장기미동작 차단기 조작시험","2019-10-29 13:00","2019-10-29 18:00","2019-10-29 13:00","2019-10-29 18:00","당일"]
[114,"인천","직할","신부평중동#1 T/L","신부평S/S 170kV 신부평중동#1T/L 장기미동작 차단기 조작시험","신부평S/S 170kV 신부평중동#1T/L 장기미동작 차단기 조작시험","2019-10-29 09:30","2019-10-29 13:00","2019-10-29 09:30","2019-10-29 13:00","당일"]
[115,"인천","직할","신부평고강#2 T/L","전자파 저감기술 현장시범 적용공사","신부평#2-영서 건설공사 특고압민원 관련 전자파 저감 실증시험 결과의 현장시범적용을 통한 효과검증 및 인천 및 부천지역 민원해소를 위한 전자파 저감기술 현장 시범적용 공사","2019-10-26 09:30","2019-10-26 12:30","2019-10-26 09:30","2019-10-26 12:30","당일"]
[116,"인천","직할","신부평중동#3 T/L","신부평S/S 170kV 신부평중동#3T/L 장기미동작 차단기 조작시험","신부평S/S 170kV 신부평중동#3T/L 장기미동작 차단기 조작시험","2019-10-30 09:30","2019-10-30 18:00","2019-10-30 09:30","2019-10-30 18:00","당일"]
[117,"인천","직할","신부평임학#1 T/L","신부평,임학S/S 170kV 신부평임학#1T/L 차단기 조작시험","신부평,임학S/S 170kV 신부평임학#1T/L 차단기 조작시험","2019-10-24 09:30","2019-10-24 18:00","2019-10-24 09:30","2019-10-24 18:00","당일"]
[118,"인천","직할","중동화곡#2 T/L","154kV중동-화곡#2T/L 정밀점검","154kV중동-화곡#2T/L 정밀점검","2019-10-21 08:00","2019-10-23 18:00","취소","취소","연속"]
[119,"인천","직할","중동화곡#1 T/L","154kV중동-화곡#1T/L 정밀점검","154kV중동-화곡#1T/L 정밀점검","2019-10-16 08:00","2019-10-18 18:00","2019-10-16 08:00","2019-10-18 18:00","연속"]
[120,"경기북부","고양","양주금촌#2 T/L","변전총액공사 - 금촌S/S 차단기 조작시험","송전선로 차단기 조작시험","2019-10-01 13:00","2019-10-01 15:00","2019-10-01 13:00","2019-10-01 15:00","당일"]
[121,"경기북부","고양","양주금촌#1 T/L","변전총액공사 - 금촌S/S 차단기 조작시험","송전선로 차단기 조작시험","2019-10-01 10:00","2019-10-01 12:00","2019-10-01 10:00","2019-10-01 12:00","당일"]
[122,"경기북부","고양","지도능곡#2 T/L","변전총액공사 - 능곡S/S 차단기 조작시험","송전선로 차단기 조작시험","2019-10-08 10:00","2019-10-08 12:00","2019-10-08 10:00","2019-10-08 12:00","당일"]
[123,"경기북부","고양","지도능곡#1 T/L","변전총액공사 - 능곡S/S 차단기 조작시험","송전선로 차단기 조작시험","2019-10-07 10:00","2019-10-07 12:00","2019-10-07 10:00","2019-10-07 12:00","당일"]
[124,"경기북부","고양","문발S/S 154KV #65 BUS","파주운정3지구 지장송전선로 지중화공사","- 공사구간 : 154kV 신파주-문발#1,2T/L J/B#1∼#6 2.012km - 선종 및 선로길이 : XLPE 2500㎟×2C 0.801km / XLPE 2000㎟(D)×2C 1.211km","2019-10-01 10:00","2019-10-02 18:00","2019-10-01 10:00","2019-10-02 18:00","연속"]
[125,"경기북부","고양","문발덕이#2 T/L","파주운정3지구 지장송전선로 지중화공사","- 공사구간 : 154kV 신파주-문발#1,2T/L J/B#1∼#6 2.012km - 선종 및 선로길이 : XLPE 2500㎟×2C 0.801km / XLPE 2000㎟(D)×2C 1.211km","2019-10-01 10:00","2019-10-02 18:00","2019-10-01 10:00","2019-10-02 18:00","연속"]
[126,"경기북부","고양","문발S/S 154kV #60-#65 BUS TIE CB","2019년 고양P/O 변전정비회사 총액공사","문발S/S 154kV #60-#65 BUS PRO PNL 교체공사","2019-10-15 09:00","2019-10-17 18:00","2019-10-15 09:00","2019-10-17 18:00","연속"]
[127,"경기북부","고양","신파주S/S 154kV 신파주-송포#2T/L GIS","2019 고양P/O 변전정비회사 총액공사(신파주-송포#2T/L)","170kV GIS 보통점검","2019-10-04 09:30","2019-10-04 18:00","2019-10-04 09:30","2019-10-04 18:00","당일"]
[128,"경기북부","고양","신파주S/S 154kV #61-#66 BUS TIE GIS","2019 고양P/O 변전정비회사 총액공사(신파주 #6200 BUSTIE)","170kV GIS 보통점검","2019-10-10 09:30","2019-10-10 18:00","2019-10-10 09:30","2019-10-10 18:00","당일"]
[129,"경기북부","고양","신파주금촌#1 T/L","19-20년 지중송전설비 위탁정비공사","케이블헤드 및 피뢰기 점검 - 신파주 C/H","2019-10-30 09:00","2019-10-30 18:00","취소","취소","연속"]
[130,"경기북부","고양","신파주금촌#2 T/L","19-20년 지중송전설비 위탁정비공사","케이블헤드 및 피뢰기 점검 - 신파주 C/H","2019-10-31 09:00","2019-10-31 18:00","취소","취소","연속"]
[131,"경기북부","고양","신파주S/S 154kV 신파주-송포#1T/L GIS","2019 고양P/O 변전정비회사 총액공사(신파주-송포 #1T/L)","170kV GIS 보통점검","2019-10-02 09:30","2019-10-02 18:00","2019-10-02 09:30","2019-10-02 18:00","당일"]
[132,"경기북부","고양","신덕은원흥#2 T/L","154kV 신덕은-원흥T/L 송전용량증대 전력선교체공사","ㅇ 전력선교체 : 12.03km - 구간 : No.10~13, No.17~30, No.39~46, NO.48~60 ㅇ 계탑 및 애자련변경 - No.10(계탑), No.11(애자련변경)","2019-10-03 07:00","2019-10-06 18:00","취소","취소","연속"]
[133,"경기북부","고양","신덕은원흥#2 T/L","154kV 신덕은-원흥T/L 송전용량증대 전력선교체공사","ㅇ 전력선교체 : 12.03km - 구간 : No.10~13, No.17~30, No.39~46, NO.48~60 ㅇ 계탑 및 애자련변경 - No.10(계탑), No.11(애자련변경)","2019-10-20 07:00","2019-11-09 18:00","취소","취소","연속"]
[134,"경기북부","고양","원흥수색#2 T/L","19-20년 지중송전설비 위탁정비공사","케이블헤드 및 피뢰기 점검 - 16호 C/H","2019-10-28 09:00","2019-10-29 18:00","취소","취소","연속"]
[135,"경기북부","고양","원흥수색#1 T/L","19-20년 지중송전설비 위탁정비공사","케이블헤드 및 피뢰기 점검 - 16호 C/H","2019-10-24 09:00","2019-10-25 18:00","취소","취소","연속"]
[136,"경기북부","고양","월롱S/S 154kV 문산-월롱#2T/L GIS","2019 고양P/O 변전정비회사 총액공사(문산-월롱#2T/L)","170kV GIS 보통점검","2019-10-08 09:30","2019-10-08 18:00","취소","취소","당일"]
[137,"경기북부","고양","월롱S/S 154kV 문산-월롱#1T/L GIS","2019 고양P/O 변전정비회사 총액공사(문산-월롱#1T/L)","170kV GIS 보통점검","2019-10-07 09:30","2019-10-07 18:00","취소","취소","당일"]
[138,"경기북부","고양","고양일산#2 T/L","2019년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(3CCT + PT Bay) 1. 154kV 일산S/S 일산-송포#1,2T/L 2. 154kV 일산S/S #6G/T 3. 154kV #60-#65 BUS PT Bay","2019-10-14 09:00","2019-11-08 18:00","2019-10-07 09:00","2019-11-01 18:00","연속"]
[139,"경기북부","고양","일산송포#1 T/L","2019년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(3CCT + PT Bay) 1. 154kV 일산S/S 일산-송포#1,2T/L 2. 154kV 일산S/S #6G/T 3. 154kV #60-#65 BUS PT Bay","2019-10-14 09:00","2019-11-08 18:00","2019-10-07 09:00","2019-11-01 18:00","연속"]
[140,"경기북부","고양","일산송포#2 T/L","2019년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(3CCT + PT Bay) 1. 154kV 일산S/S 일산-송포#1,2T/L 2. 154kV 일산S/S #6G/T 3.154kV #60-#65 BUS PT Bay","2019-10-14 09:00","2019-11-08 18:00","2019-10-07 09:00","2019-11-01 18:00","연속"]
[141,"경기북부","고양","일산S/S 154kV #6G/T CB","2019년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(3CCT + PT Bay) 1. 154kV 일산S/S 일산-송포#1,2T/L 2. 154kV 일산S/S #6G/T 3. 154kV #60-#65 BUS PT Bay","2019-10-14 09:00","2019-11-08 18:00","2019-10-07 09:00","2019-11-01 18:00","연속"]
[142,"경기북부","고양","일산S/S 154KV #66 BUS","2019년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(3CCT + PT Bay) 1. 154kV 일산S/S 일산-송포#1,2T/L 2. 154kV 일산S/S #6G/T 3. 154kV #60-#65 BUS PT Bay","2019-10-14 09:00","2019-10-17 09:00","2019-10-07 09:00","2019-10-10 09:00","연속"]
[143,"경기북부","고양","일산S/S 154kV #61 BUS","2019년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(3CCT + PT Bay) 1. 154kV 일산S/S 일산-송포#1,2T/L 2. 154kV 일산S/S #6G/T 3. 154kV #60-#65 BUS PT Bay","2019-10-17 09:00","2019-10-28 09:00","2019-10-10 09:00","2019-10-21 09:00","연속"]
[144,"경기북부","고양","일산지도#2 T/L","기중종단접속함(EB-A) 자기애관 교체공사","기설 자기애관 → 폴리머애관 교체","2019-10-21 09:00","2019-10-24 18:00","취소","취소","연속"]
[145,"경기북부","고양","일산지도#1 T/L","기중종단접속함(EB-A) 자기애관 교체공사","기설 자기애관 → 폴리머애관 교체","2019-10-14 09:00","2019-10-18 18:00","취소","취소","연속"]
[146,"경기북부","구리","가평청평HP#1 T/L","가평s/S 가평청평HP#1 T/L CVT 점검","가평S/S 가평청평HP#1 T/L CVT 점검","2019-10-14 09:00","2019-10-14 14:00","2019-10-14 09:00","2019-10-14 14:00","당일"]
[147,"경기북부","구리","가평청평HP#2 T/L","154kV 화천T/L 항공장애시설물 정비공사","ㅇ 항공장애표시구 설치 - No.133~134","2019-10-29 07:00","2019-10-29 18:00","2019-10-29 07:00","2019-10-29 18:00","연속"]
[148,"경기북부","구리","가평화천HP T/L","154kV 화천T/L 항공장애시설물 정비공사","ㅇ 항공장애표시구 설치 - No.133~134","2019-10-29 07:00","2019-10-29 18:00","2019-10-29 07:00","2019-10-29 18:00","연속"]
[149,"경기북부","구리","덕소팔당HP청평HP T/L","154㎸ 덕소S/S 옥내화관련 지중T/L 건설공사","154kV 덕소S/S 옥내화공사 시행에 따른 관련 지중T/L 정비사업 154kV 덕소-팔당-청평T/L 휴전작업으로 신설 덕소S/S 계통병입","2019-10-07 09:00","2019-10-31 18:00","2019-10-07 09:00","2019-10-31 18:00","연속"]
[150,"경기북부","구리","미금S/S 154kV #60 BUS","미금S/S 170kV 장기사용GIS 교체공사(6차분)","- 170kV GIS 철거, 설치 - 기타 부대공사","2019-10-01 08:00","2019-10-07 08:00","취소","취소","연속"]
[151,"경기북부","구리","미금S/S 154kV #60 BUS","미금S/S 170kV 장기사용GIS 교체공사(7차분)","- 170kV GIS 철거, 설치 - 기타 부대공사","2019-10-30 10:00","2019-10-30 15:00","취소","취소","연속"]
[152,"경기북부","구리","미금S/S 154kV #60 BUS","미금S/S 170kV 장기사용GIS 교체공사(7차분)","- 170kV GIS 철거, 설치 - 기타 부대공사","2019-10-22 08:00","2019-10-25 08:00","취소","취소","연속"]
[153,"경기북부","구리","미금S/S 154kV #65 BUS","미금S/S 170kV 장기사용GIS 교체공사(6차분)","- 170kV GIS 철거, 설치 - 기타 부대공사","2019-10-07 08:00","2019-10-19 16:00","취소","취소","연속"]
[154,"경기북부","구리","미금화양 T/L","미금S/S 154kV 미금-화양T/L보호반 교체공사","미금S/S 154kV 미금-화양T/L보호반 교체","2019-10-14 09:00","2019-10-16 18:00","2019-10-14 09:00","2019-10-16 18:00","연속"]
[155,"경기북부","구리","미금S/S 154kV #60 BUS","미금S/S 170kV 장기사용GIS 교체공사(6차분)","- 170kV GIS 철거, 설치 - 기타 부대공사","2019-10-19 10:00","2019-10-19 15:00","취소","취소","연속"]
[156,"경기북부","구리","미금덕소#1 T/L","미금S/S 170kV 장기사용GIS 교체공사(7차분)","- 170kV GIS 철거, 설치(안전이격확보) - 기타 부대공사","2019-10-21 08:00","2019-10-29 18:00","취소","취소","매일"]
[157,"경기북부","구리","미금S/S 154kV #65 BUS","미금S/S 170kV 장기사용GIS 교체공사(7차분)","- 170kV GIS 철거, 설치 - 기타 부대공사","2019-10-25 08:00","2019-10-30 16:00","취소","취소","연속"]
[158,"경기북부","구리","미금S/S 154kV #65 BUS","미금S/S 170kV 장기사용GIS 교체공사(7차분)","- 170kV GIS 철거, 설치 - 기타 부대공사","2019-10-21 08:00","2019-10-22 18:00","취소","취소","연속"]
[159,"경기북부","구리","미금구리#1 T/L","미금S/S 170kV 장기사용GIS 교체공사(7차분)","- 170kV GIS 철거, 설치 - 기타 부대공사","2019-10-21 08:00","2019-10-30 18:00","취소","취소","연속"]
[160,"경기북부","구리","별내도봉 T/L","154kV 별내-도봉T/L PMJ 교체공사","○ 대상 : J/B#1~#3 구간 3개소 9상 ○ 내용 : 일진제 조립식 중간접속함 형태 변경(R→Flat Type)","2019-10-01 08:00","2019-10-07 18:00","취소","취소","연속"]
[161,"경기북부","구리","신포천전곡#1 T/L","OPGW 항공장애표시구 소음 민원 관련 항공장애표시구 교체","OPGW 항공장애표시구 소음 민원 관련 항공장애표시구 교체 - 구간 : 154kV 신포천전곡#1T/L No.42~44 2경간 - 한단 : 154kV 운천전곡#2T/L 안전이격거리 확보로 동시 휴전","2019-10-16 07:00","2019-10-16 18:00","2019-10-16 07:00","2019-10-16 18:00","당일"]
[162,"경기북부","구리","신포천전곡#2 T/L","2018~2019년 직할 가공송전 정비회사 총액공사(항공구 교체)","항공구 소음 민원 관련 항공구 교체 - 구 간 : 154kV 신포천전곡#2T/L No.42~44호 2경간 - 하단 154kV 운천전곡#1T/L 안전이격거리 확보로 동시휴전","2019-10-14 08:00","2019-10-14 18:00","2019-10-14 08:00","2019-10-14 18:00","당일"]
[163,"경기북부","구리","운천전곡#1 T/L","2018~2019년 직할 가공송전 정비회사 총액공사(항공구 교체_병가)","항공구 소음 민원 관련 항공구 교체 - 구 간 : 154kV 신포천전곡#2T/L No.42~44호 2경간 - 하단 154kV 운천전곡#1T/L 안전이격거리 확보로 동시휴전","2019-10-14 08:00","2019-10-14 18:00","2019-10-14 08:00","2019-10-14 18:00","당일"]
[164,"경기북부","구리","운천전곡#2 T/L","OPGW 항공장애표시구 소음 민원 관련 항공장애표시구 교체","OPGW 항공장애표시구 소음 민원 관련 항공장애표시구 교체 - 구간 : 154kV 신포천전곡#1T/L No.42~44 2경간 - 한단 : 154kV 운천전곡#2T/L 안전이격거리 확보로 동시 휴전","2019-10-16 07:00","2019-10-16 18:00","2019-10-16 07:00","2019-10-16 18:00","당일"]
[165,"경기북부","구리","청평HP의암HP T/L","2018~19년도 구리전력지사 가공송전정비 협력회사 총액공사","ㅇ 애자련보강공사 - 대상 : No.37,38","2019-10-25 09:00","2019-10-25 18:00","2019-10-25 09:00","2019-10-25 18:00","당일"]
[166,"경기북부","구리","청평H/P 154kV #2 M.TR 2차 CB","6200 원방조작 불가조치","6200 원방조작 불가조치","2019-10-01 10:00","2019-10-01 18:00","2019-10-01 10:00","2019-10-01 18:00","당일"]
[167,"경기북부","구리","청평H/P 154kV #2 M.TR 2차 DS(연락) CB","6200 원방조작 불량 조치","6200 원방조작 불량 조치","2019-10-01 10:00","2019-10-01 18:00","2019-10-01 10:00","2019-10-01 18:00","당일"]
[168,"경기북부","구리","청평H/P 154kV #3 M.TR 2차 CB","6200DS 원방조작 불가 조치","6200DS 원방조작 불가 조치","2019-10-01 10:00","2019-10-01 18:00","2019-10-01 10:00","2019-10-01 18:00","당일"]
[169,"경기북부","구리","청평P/P 154kV #1 S.Tr CB","청평양수 #60BUS CVT 보통점검","청평양수 #60BUS CVT 보통점검","2019-10-15 09:30","2019-10-15 18:00","2019-10-15 09:30","2019-10-15 18:00","당일"]
[170,"경기북부","구리","청평P/P 154kV #60 BUS","청평양수 #60BUS CVT 보통점검","청평양수 #60BUS CVT 보통점검","2019-10-15 09:30","2019-10-15 18:00","2019-10-15 09:30","2019-10-15 18:00","당일"]
[171,"경기북부","구리","청평P/P 154kV #2 S.Tr CB","청평양수 #65BUS CVT 점검","청평양수 #65BUS CVT 점검","2019-10-16 09:30","2019-10-16 18:00","2019-10-16 09:30","2019-10-16 18:00","당일"]
[172,"경기북부","구리","청평P/P 154kV #1 M.Tr 2차 CB","'18~19 구리전력 변전협력 총액공사","청평P/P 154kV #1M.Tr 2차 CB 보통점검공사","2019-10-28 09:00","2019-10-28 18:00","2019-10-28 09:00","2019-10-28 18:00","당일"]
[173,"경기북부","구리","청평P/P 154kV #65 BUS","청평양수 #65BUS CVT 점검","청평양수 #65BUS CVT 점검","2019-10-16 09:30","2019-10-16 18:00","2019-10-16 09:30","2019-10-16 18:00","당일"]
[174,"경기북부","구리","팔당H/P 154kV #2 M.Tr 1차 CB","‘18∼19년 구리전력지사 변전협력 총액공사","팔당H/P 154kV #2M.Tr 1차 GIS 보통점검공사","2019-10-15 09:00","2019-10-15 18:00","2019-10-15 09:00","2019-10-15 18:00","당일"]
[175,"경기북부","직할","신포천동두천#1 T/L","동두천E/C 154kV Sh.C 증설공사","ㅇ 154kV Sh.C 1Bank 설치 ㅇ 154kV Sh.C용 GIS 1CCT 설치","2019-10-14 09:00","2019-10-26 18:00","2019-10-14 09:00","2019-10-26 18:00","연속"]
[176,"경기북부","직할","신의정부송우#1 T/L","2019년 가공송전선로 순시점검 위탁공사","정밀점검 (No.5~50)","2019-10-22 08:00","2019-10-24 18:00","2019-10-22 08:00","2019-10-24 18:00","연속"]
[177,"경기북부","직할","신의정부송우#2 T/L","2019년 가공송전선로 순시점검 위탁공사","정밀점검 (No.5~50)","2019-10-15 08:00","2019-10-17 18:00","2019-10-15 08:00","2019-10-17 18:00","연속"]
[178,"경기북부","직할","양주은평#1 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주은평#1T/L 인출측 전력구공사","2019-10-21 09:00","2019-10-22 18:00","2019-10-21 09:00","2019-10-22 18:00","연속"]
[179,"경기북부","직할","양주쌍문#1 T/L","154kV 문산-월롱 등 11개T/L 피뢰기 설치공사","154kV 양주-쌍문#1T/L 피뢰기 설치","2019-10-22 07:00","2019-10-23 18:00","2019-10-22 07:00","2019-10-23 18:00","연속"]
[180,"경기북부","직할","양주은평#2 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주은평#2T/L 인출측 전력구공사","2019-10-23 09:00","2019-10-24 18:00","2019-10-23 09:00","2019-10-24 18:00","연속"]
[181,"경기북부","직할","양주지축#1 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주지축#1T/L 인출측 전력구공사","2019-10-16 09:00","2019-10-17 18:00","취소","취소","연속"]
[182,"경기북부","직할","양주녹양#1 T/L","18~19년 직할 변전정비회사 총액공사","□ 양주-녹양 #1T/L LA, CVT 보통점검 □ 양주측, 녹양측 모두 점검있음 → 양주S/S 점검 후 녹양S/S 점검 시행","2019-10-24 09:00","2019-10-24 18:00","2019-10-24 09:00","2019-10-24 18:00","당일"]
[183,"경기북부","직할","양주녹양#2 T/L","154kV 문산-월롱 등 11개T/L 피뢰기 설치공사","154kV 양주-녹양#2T/L 피뢰기 설치","2019-10-21 07:00","2019-10-22 18:00","2019-10-21 07:00","2019-10-22 18:00","연속"]
[184,"경기북부","직할","옥정동두천#1 T/L","2018~2019년 경기북부직할 가공송전 정비회사 총액공사","압축클램프 교체 (No.1)","2019-10-08 08:00","2019-10-08 18:00","2019-10-08 08:00","2019-10-08 18:00","당일"]
[185,"경기북부","직할","옥정송우#1 T/L","2018~2019년 경기북부직할 가공송전 정비회사 총액공사","압축클램프 교체 (No.1)","2019-10-07 08:00","2019-10-07 18:00","2019-10-07 08:00","2019-10-07 18:00","당일"]
[186,"경기북부","직할","옥정동두천#2 T/L","2018~2019년 경기북부직할 가공송전 정비회사 총액공사","피뢰기설치 (No.1) 압축클램프 교체 (No.1)","2019-10-07 08:00","2019-10-07 18:00","2019-10-07 08:00","2019-10-07 18:00","당일"]
[187,"경기북부","직할","옥정송우#2 T/L","2018~2019년 경기북부직할 가공송전 정비회사 총액공사","압축클램프 교체 (No.1) 피뢰기 설치 (No.1)","2019-10-08 08:00","2019-10-08 18:00","2019-10-08 08:00","2019-10-08 18:00","당일"]
[188,"경기","군포","화성남양#1 T/L","345kV 신안산분기T/L OPGW시설공사","공사장소 : 화성S/S-No.2~No.56~신안산S/S 시설내역: OPGW 120㎟ 24C SM 17.566km, 48C SM 4.113㎞ 시설","2019-10-27 09:00","2019-10-27 18:00","2019-10-27 09:00","2019-10-27 18:00","연속"]
[189,"경기","군포","시화동시화#2 T/L","군포P/O 변전정비회사 총액공사","시화S/S 시화-동시화#2T/L 조작시험","2019-10-11 14:00","2019-10-11 18:00","2019-10-11 14:00","2019-10-11 18:00","당일"]
[190,"경기","군포","시화동시화#1 T/L","군포P/O 변전정비회사 총액공사","시화S/S 시화-동시화#1T/L 조작시험","2019-10-11 09:00","2019-10-11 13:00","2019-10-11 09:00","2019-10-11 13:00","당일"]
[191,"경기","군포","평촌안양2CC #1T/L","군포P/O 변전정비회사 총액공사","안양C/C, 평촌S/S 평촌-안양2CC #1T/L 초기점검(17년가압)","2019-10-01 09:00","2019-10-01 13:00","취소","취소","당일"]
[192,"경기","군포","평촌안양2CC #3T/L","군포P/O 변전정비회사 총액공사","안양C/C,평촌S/S 평촌-안양2CC #3T/L 초기점검(17년가압)","2019-10-01 14:00","2019-10-01 18:00","취소","취소","당일"]
[193,"경기","군포","평촌안양2CC #2T/L","군포P/O 변전정비회사 총액공사","안양C/C, 평촌S/S 평촌-안양2CC #2/L 초기점검(17년가압)","2019-10-02 09:00","2019-10-02 13:00","취소","취소","당일"]
[194,"경기","군포","안양2C/C 154kV #60-#65 BUS TIE GIS","군포P/O 변전정비회사 총액공사","안양C/C #6100 BUS-TIE GIS 초기점검(17년가압)","2019-10-02 14:00","2019-10-02 18:00","취소","취소","당일"]
[195,"경기","군포","안양S/S 154kV 산본-안양#2T/L GIS","안양S/S 산본-안양#2T/L 하자점검","안양S/S 산본-안양#2T/L 하자점검 산본S/S 산본-안양#2T/L 하자점검","2019-10-16 09:00","2019-10-16 18:00","2019-10-16 09:00","2019-10-16 18:00","당일"]
[196,"경기","군포","안양S/S 154kV 산본-안양#1T/L GIS","안양S/S 산본-안양#1T/L 하자점검","안양S/S 산본-안양#1T/L 하자점검 산본S/S 산본-안양#1T/L 조작시험","2019-10-15 09:00","2019-10-15 18:00","2019-10-15 09:00","2019-10-15 18:00","당일"]
[197,"경기","동부","가남S/S 154kV 왕암-가남#2T/L GIS","불량 OPGW 교체 공사","왕암-가남#2T/L 192호∼199호간(1/5Km) 불량 OPGW 교체 공사 - 192∼199호간 OPGW(100Sq,48C 약1.5Km 연긴선, 접속 및 시험) 교체 (~8)","2019-10-07 09:30","2019-10-08 18:00","2019-10-07 09:30","2019-10-08 18:00","연속"]
[198,"경기","동부","곤지암초월#2 T/L","154kV 곤지암-초월#2T/L R-Type PMJ 교체공사","유사고장예방 R-Type PMJ 교체(6EA)","2019-10-14 08:00","2019-10-27 18:00","2019-10-14 08:00","2019-10-27 18:00","연속"]
[199,"경기","동부","곤지암S/S 154kV 곤지암-초월#1T/L GIS","19년 동부변전협력회사 총액공사","곤지암 : 곤지암-초월#1T/L 보호반대체(~30) 초월 : 곤지암-초월#1T/L 보호반대체(~30) 초월:곤지암-초월#1T/L (보통) 43L/R 회로보완 확인 및 Remote 회로분리 시행","2019-10-28 09:30","2019-10-30 18:00","2019-10-28 09:30","2019-10-30 18:00","연속"]
[200,"경기","동부","성현S/S 154kV 산성-성현#2T/L GIS","19년 동부변전협력회사 총액공사","산성:산성-성현#2T/L (개폐타임),Remote 회로분리 시행 성현:산성-성현#2T/L (개폐타임) 43L/R 회로보완 확인 및 Remote 회로분리 시행","2019-10-24 09:30","2019-10-24 18:00","2019-10-24 09:30","2019-10-24 18:00","당일"]
[201,"경기","동부","성현S/S 154kV 성현-분당#2T/L GIS","19년 동부변전협력회사 총액공사","성현 : 성현-분당#2T/L 보호반대체(~18) 분당 : 성현-분당#2T/LL 보호반대체(~18) 분당:성현-분당#2T/L (초기)","2019-10-10 09:30","2019-10-12 18:00","2019-10-10 09:30","2019-10-12 18:00","연속"]
[202,"경기","동부","성현S/S 154kV 성현-분당#1T/L GIS","19년 동부변전협력회사 총액공사","성현 : 성현-분당#1T/L 보호반대체 분당 : 성현-분당#1T/LL 보호반대체(~16) 성현:성현-분당#1 T/L GIS(보통) LA대체,43L/R 회로보완 확인 및 Remote 회로분리 시행","2019-10-07 09:30","2019-10-09 18:00","2019-10-07 09:30","2019-10-09 18:00","연속"]
[203,"경기","동부","성현S/S 154kV 산성-성현#1T/L GIS","19년 동부변전협력회사 총액공사","산성:산성-성현#1T/L (개폐타임),Remote 회로분리 시행 성현:산성-성현#1T/L (보통) 43L/R 회로보완 확인 및 Remote 회로분리 시행","2019-10-23 09:30","2019-10-23 18:00","2019-10-23 09:30","2019-10-23 18:00","당일"]
[204,"경기","동부","성현S/S 154kV 산성-성현#3T/L GIS","19년 동부변전협력회사 총액공사","산성:산성-성현#3T/L (보통) 43L/R 회로보완 확인 및 Remote 회로분리 시행 성현:산성-성현#3T/L (정밀예정) 43L/R 회로보완 확인 및 Remote 회로분리 시행","2019-10-25 09:30","2019-10-25 18:00","2019-10-25 09:30","2019-10-25 18:00","당일"]
[205,"경기","동부","이천율현#1 T/L","154kV 이천-율현#1T/L 송전선로 정밀점검","송전선로 정밀점검","2019-10-21 08:00","2019-10-22 18:00","2019-10-19 08:00","2019-10-20 18:00","연속"]
[206,"경기","동부","이천가남#1 T/L","154kV 이천-가남#1T/L C/H 및 피뢰기 점검","No.13,14CH 피뢰기 점검","2019-10-17 09:30","2019-10-17 18:00","2019-10-17 09:30","2019-10-17 18:00","당일"]
[207,"경기","동부","이천가남#2 T/L","154kV 이천-가남#2T/L C/H 및 피뢰기 점검","No.13,14CH 피뢰기 점검","2019-10-18 09:30","2019-10-18 18:00","2019-10-18 09:30","2019-10-18 18:00","당일"]
[208,"경기","동부","이천율현#2 T/L","154kV 이천-율현#2T/L 송전선로 정밀점검","송전선로 정밀점검","2019-10-23 08:00","2019-10-24 18:00","2019-10-26 08:00","2019-10-27 18:00","연속"]
[209,"경기","성남","서안성안성#2 T/L","(안전이격휴전) 154kV 서안성-남사T/L 피뢰기 설치공사","- (안전이격휴전) 154kV 서안성-남사T/L 피뢰기 설치 시 154kV 서안성-남사 No.1 병가","2019-10-18 07:00","2019-10-18 09:00","2019-10-18 07:00","2019-10-18 09:00","당일"]
[210,"경기","성남","서안성남사#1 T/L","154kV 서안성-남사T/L 피뢰기 설치 및 전선접속개소 교체공사","- 154kV 서안성-남사T/L 피뢰기 설치 및 전선교체공사 (No.1-20, 60 SET 및 No.10-11 전선교체공사)","2019-10-17 07:00","2019-10-19 18:00","2019-10-17 07:00","2019-10-19 18:00","연속"]
[211,"경기","성남","서안성S/S 154kV #61-#62 SEC GIS","GIS 제작사 하자처리","61-62-91,92ES 코일불량","2019-10-22 09:00","2019-10-22 18:00","2019-10-22 09:00","2019-10-22 18:00","당일"]
[212,"경기","성남","서안성남사#2 T/L","154kV 서안성-남사T/L 전선접속개소 교체공사","- 154kV 서안성-남사T/L 전선교체공사 (No.10-11 전선교체공사)","2019-10-16 07:00","2019-10-16 18:00","2019-10-16 07:00","2019-10-16 18:00","당일"]
[213,"경기","성남","신수원S/S 154kV #65 BUS","PT PNL 보조Ry 교체","PT PNL 보조Ry 교체","2019-10-14 14:00","2019-10-14 18:00","2019-10-23 14:00","2019-10-23 18:00","당일"]
[214,"경기","성남","신수원S/S 154kV #62 BUS","PT PNL 보조Ry 교체","PT PNL 보조Ry 교체","2019-10-16 09:00","2019-10-16 14:00","취소","취소","당일"]
[215,"경기","성남","신수원S/S 154kV #67 BUS","PT PNL 보조Ry 교체","PT PNL 보조Ry 교체","2019-10-16 14:00","2019-10-16 18:00","취소","취소","당일"]
[216,"경기","성남","신수원S/S 154kV #61-#62 SEC GIS","GIS 조작시험","GIS 조작시험","2019-10-02 09:00","2019-10-02 18:00","2019-10-02 09:00","2019-10-02 18:00","당일"]
[217,"경기","성남","신수원S/S 154kV #60 BUS","PT PNL 보조Ry 교체","PT PNL 보조Ry 교체","2019-10-14 09:00","2019-10-14 14:00","2019-10-23 09:00","2019-10-23 14:00","당일"]
[218,"경기","성남","신수원S/S 154kV #61 BUS","PT PNL 보조Ry 교체","PT PNL 보조Ry 교체","2019-10-12 09:00","2019-10-12 14:00","2019-10-12 09:00","2019-10-12 14:00","당일"]
[219,"경기","성남","신수원S/S 154kV #66 BUS","PT PNL 보조Ry 교체","PT PNL 보조Ry 교체","2019-10-12 14:00","2019-10-12 18:00","2019-10-12 14:00","2019-10-12 18:00","당일"]
[220,"경기","성남","신용인S/S 154kV #62 BUS","PT PNL 보조Ry교체","PT PNL 보조Ry교체","2019-10-29 09:00","2019-10-29 14:00","2019-10-29 09:00","2019-10-29 14:00","당일"]
[221,"경기","성남","신용인S/S 154kV #66 BUS","PT 보조Ry 교체","PT 보조Ry 교체","2019-10-28 14:00","2019-10-28 18:00","2019-10-28 14:00","2019-10-28 18:00","당일"]
[222,"경기","성남","신용인S/S 154kV #61 BUS","PT 보조Ry 교체","PT 보조Ry 교체","2019-10-28 09:00","2019-10-28 14:00","2019-10-28 09:00","2019-10-28 14:00","당일"]
[223,"경기","성남","신용인용인#1 T/L","345kV신용인-신수원,신용인-삼성T/L 전선교체공사(안전이격)","안전이격확보","2019-10-01 09:00","2019-10-14 18:00","2019-10-01 09:00","2019-10-14 18:00","연속"]
[224,"경기","성남","신용인기흥#2 T/L","345kV신용인-신수원,신용인-삼성T/L 전선교체공사(안전이격)","안전이격확보","2019-10-01 09:00","2019-10-21 18:00","2019-10-01 09:00","2019-10-21 18:00","연속"]
[225,"경기","성남","신용인용인#2 T/L","345kV신용인-신수원,신용인-삼성T/L 전선교체공사(안전이격)","안전이격확보","2019-10-01 09:00","2019-10-14 18:00","2019-10-01 09:00","2019-10-14 18:00","연속"]
[226,"경기","성남","신용인S/S 154kV #65 BUS","PT PNL 보조Ry교체","PT PNL 보조Ry교체","2019-10-27 14:00","2019-10-27 18:00","2019-10-27 14:00","2019-10-27 18:00","당일"]
[227,"경기","성남","신용인기흥#2 T/L","345kV신용인-신수원,신용인-삼성T/L 전선교체공사(안전이격)","안전이격확보","2019-10-28 09:00","2019-11-04 18:00","2019-10-28 09:00","2019-11-04 18:00","연속"]
[228,"경기","성남","신용인기흥#1 T/L","345kV신용인-신수원,신용인-삼성T/L 전선교체공사(안전이격)","안전이격확보","2019-10-01 09:00","2019-10-21 18:00","2019-10-01 09:00","2019-10-21 18:00","연속"]
[229,"경기","성남","신용인S/S 154kV #60 BUS","PT PNL 보조Ry교체","PT PNL 보조Ry교체","2019-10-27 09:00","2019-10-27 14:00","2019-10-27 09:00","2019-10-27 14:00","당일"]
[230,"경기","성남","신용인기흥#1 T/L","345kV신용인-신수원,신용인-삼성T/L 전선교체공사(안전이격)","안전이격확보","2019-10-28 09:00","2019-11-04 18:00","2019-10-28 09:00","2019-11-04 18:00","연속"]
[231,"경기","직할","서서울#2남수원 #2T/L","남수원S/S 154kV 장기사용 GIS 교체공사","서서울2남수원#2T/L 및 #1M.Tr 1차 GIS 교체","2019-10-10 09:00","2019-11-12 18:00","취소","취소","연속"]
[232,"경기","직할","남수원S/S 154kV #2 BUS","남수원S/S 154kV 장기사용 GIS 교체공사","서서울2남수원#2T/L 및 #1M.Tr 1차 GIS 교체","2019-10-31 14:00","2019-11-12 09:00","2019-10-31 14:00","2019-11-12 09:00","연속"]
[233,"경기","직할","서서울#2남수원 #1T/L","남수원S/S 154kV 장기사용 GIS 교체공사","서서울2남수원#2T/L 및 #1M.Tr 1차 GIS 교체","2019-10-29 14:00","2019-10-30 14:00","취소","취소","연속"]
[234,"경기","직할","남수원S/S 154kV #1 BUS","남수원S/S 154kV 장기사용 GIS 교체공사","서서울2남수원#2T/L 및 #1M.Tr 1차 GIS 교체","2019-10-17 09:00","2019-10-30 18:00","2019-10-17 09:00","2019-10-30 18:00","연속"]
[235,"경기","직할","의왕동안양#1 T/L","19년 직할 변전협력회사 총액공사","의왕S/S 의왕-동안양#1T/L GIS 조작, LA하자 동안양S/S 의왕-동안양#1T/L GCB 조작시험","2019-10-29 09:00","2019-10-29 14:00","2019-10-29 09:00","2019-10-29 14:00","당일"]
[236,"경기","직할","의왕동안양#2 T/L","19년 직할 변전협력회사 총액공사","의왕S/S 의왕-동안양#2T/L LA하자 동안양S/S 의왕-동안양#2T/L GCB 조작시험","2019-10-29 14:00","2019-10-29 18:00","2019-10-29 14:00","2019-10-29 18:00","당일"]
[237,"경기","직할","서서울서수원#2 T/L","19년 직할 변전협력회사 총액공사","서수원S/S 서서울-서수원#2T/L LA 하자점검","2019-10-24 09:00","2019-10-24 18:00","2019-10-24 09:00","2019-10-24 18:00","당일"]
[238,"경기","직할","서수원율전#2 T/L","154kV 서수원-율전#2T/L PD진단센서 및 집합반 설치공사","철탑형C/H EBA PD센서 및 집합반 설치","2019-10-07 09:00","2019-10-07 18:00","2019-10-07 09:00","2019-10-07 18:00","당일"]
[239,"경기","직할","서서울율전#2 T/L","19년 직할 변전협력회사 총액공사","율전S/S 서서울-율전#1,2T/L GIS 조작시험","2019-10-08 14:00","2019-10-08 18:00","2019-10-08 14:00","2019-10-08 18:00","당일"]
[240,"경기","직할","서서울율전#1 T/L","19년 직할 변전협력회사 총액공사","율전S/S 서서울-율전#1,2T/L GIS 조작시험","2019-10-08 09:00","2019-10-08 14:00","2019-10-08 09:00","2019-10-08 14:00","당일"]
[241,"경기","직할","율전의왕#2 T/L","19년 직할 변전협력회사 총액공사","의왕S/S 율전-의왕#2T/L GIS초기, LA하자 율전S/S 율전-의왕#2T/L GIS조작","2019-10-25 09:00","2019-10-25 18:00","2019-10-25 09:00","2019-10-25 18:00","당일"]
[242,"경기","직할","의왕동안양#1 T/L","의왕S/S 154kV 장기사용 GIS 대체공사","의왕S/S 군포전철#2T/L(647) GIS 대체(#2BUS 무부하가압용)","2019-10-06 09:00","2019-10-07 09:00","2019-10-11 15:00","2019-10-14 18:00","연속"]
[243,"경기","평택","평택오성CC#2 T/L","154kV 평택오성CC T/L 철탑교체공사 (구간 오성ST~2호)","고객소유선로(오성복합) 철탑교체 154kV 평택오성CC #2T/L 철탑교체공사 (구간 ST~2호, No.1교체)","2019-10-15 08:00","2019-10-19 18:00","2019-10-15 08:00","2019-10-19 18:00","연속"]
[244,"경기","평택","송탄오성CC #2T/L","154kV 송탄오성CC T/L 철탑교체공사 (구간 오성ST~2호)","고객소유선로(오성복합) 철탑교체 154kV 송탄오성CC T/L 철탑교체공사 (구간 ST~2호, No.1교체)","2019-10-10 08:00","2019-10-19 18:00","2019-10-10 08:00","2019-10-19 18:00","연속"]
[245,"경기","평택","평택오성CC#1 T/L","154kV 평택오성CC T/L 철탑교체공사 (구간 오성ST~2호)","고객소유선로(오성복합) 철탑교체 154kV 평택오성CC #1T/L 철탑교체공사 (구간 ST~2호, No.1교체)","2019-10-10 08:00","2019-10-14 18:00","2019-10-10 08:00","2019-10-14 18:00","연속"]
[246,"경기","평택","송탄오성CC #1T/L","154kV 송탄오성CC T/L 철탑교체공사 (구간 오성ST~2호)","고객소유선로(오성복합) 철탑교체 154kV 송탄오성CC #1T/L 철탑교체공사 (구간 ST~2호, No.1교체)","2019-10-15 08:00","2019-10-19 18:00","2019-10-15 08:00","2019-10-19 18:00","연속"]
[247,"경기","평택","청북평택#1 T/L","2018-2019 송전정비회사 총액공사","소도체 이도조정 No.14-21(상단)","2019-10-11 08:00","2019-10-11 18:00","2019-10-11 08:00","2019-10-11 18:00","당일"]
[248,"경기","평택","평택TP평택CC#1T/L","평택C/C 154kV 평택복합#1 T/L GIS 조작시험","평택C/C 154kV 평택복합#1 T/L GIS 조작시험 및 전자변 교체","2019-10-25 10:00","2019-10-25 18:00","2019-10-25 10:00","2019-10-25 18:00","당일"]
[249,"경기","평택","평택TP평택CC#2T/L","평택C/C 154kV 평택복합#2 T/L GIS 조작시험","평택C/C 154kV 평택복합#2 T/L GIS 조작시험 및 전자변 교체","2019-10-28 10:00","2019-10-28 18:00","2019-10-28 10:00","2019-10-28 18:00","당일"]
[250,"경기","직할","남수원발안#1 T/L","154kV 발안-향남T/L OPGW 증설공사","발안S/S~향남S/S간 OPGW 6.288km 증설(24C→48C)","2019-10-01 07:00","2019-10-07 18:00","취소","취소","연속"]
[251,"경기","직할","남수원발안#2 T/L","154kV 발안-향남T/L OPGW 증설공사","발안S/S~향남S/S간 OPGW 6.288km 증설(24C→48C)","2019-10-01 07:00","2019-10-06 18:00","취소","취소","연속"]
[252,"경기","직할","발안향남#2 T/L","154kV 발안-향남T/L OPGW 증설공사","발안S/S~향남S/S간 OPGW 6.288km 증설(24C→48C)","2019-10-07 07:00","2019-10-07 18:00","취소","취소","연속"]
[253,"강원","강릉","강릉북강릉#1 T/L","154kV 강릉-북강릉-주문진-양양간 OPGW교체공사","- OPGW 13.733km 교체 - 항공장애표시구 32개 철거 - 항공장애표시구 38개 설치","2019-10-04 08:00","2019-10-05 18:00","2019-10-04 08:00","2019-10-05 18:00","연속"]
[254,"강원","강릉","북강릉주문진#2 T/L","154kV 강릉-북강릉-주문진-양양간 OPGW 교체공사","- OPGW 13.733km 교체 - 항공장애표시구 32개 철거 - 항공장애표시구 38개 설치","2019-10-04 08:00","2019-10-14 18:00","2019-10-04 08:00","2019-10-14 18:00","연속"]
[255,"강원","강릉","북강릉주문진#1 T/L","154kV 강릉-북강릉-주문진-양양간 OPGW교체공사","- OPGW 26.364km 교체 - 항공장애표시구 55개 철거 - 항공장애표시구 55개 설치","2019-10-18 08:00","2019-10-20 18:00","2019-10-18 08:00","2019-10-20 18:00","연속"]
[256,"강원","강릉","주문진양양#1 T/L","154kV 강릉-북강릉-주문진-양양간 OPGW교체공사","- OPGW 13.733km 교체 - 항공장애표시구 32개 철거 - 항공장애표시구 38개 설치","2019-10-12 08:00","2019-10-14 18:00","2019-10-12 08:00","2019-10-14 18:00","연속"]
[257,"강원","강릉","주문진양양#2 T/L","154kV 강릉-북강릉-주문진-양양간 OPGW교체공사","- OPGW 26.364km 교체 - 항공장애표시구 55개 철거 - 항공장애표시구 55개 설치","2019-10-18 08:00","2019-11-04 18:00","2019-10-18 08:00","2019-11-04 18:00","연속"]
[258,"강원","강릉","횡계평창 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2019-10-14 10:00","2019-10-18 18:00","2019-10-14 10:00","2019-10-18 18:00","연속"]
[259,"강원","동해","동해영동TP T/L","2018~2019년도 동해전력지사 송전정비협력회사 총액공사","154kV 동해분기T/L 인출정비공사 철탑 4기 철거, 2기 신설","2019-10-18 08:00","2019-10-20 18:00","취소","취소","연속"]
[260,"강원","동해","동해강릉 T/L","2018~2019년도 동해전력지사 송전정비협력회사 총액공사","154kV 동해분기T/L 인출정비공사 철탑 4기 철거, 2기 신설","2019-10-14 08:00","2019-10-16 18:00","취소","취소","연속"]
[261,"강원","동해","북평영동TP#1 T/L","2018~2019년도 동해전력지사 송전정비협력회사 총액공사","154kV 동해분기T/L 인출정비공사 철탑 4기 철거, 2기 신설","2019-10-14 08:00","2019-10-16 18:00","취소","취소","연속"]
[262,"강원","동해","북평영동TP#1 T/L","2018~2019년도 동해전력지사 송전정비협력회사 총액공사","154kV 동해분기T/L 인출정비공사 철탑 4기 철거, 2기 신설","2019-10-18 08:00","2019-10-20 18:00","취소","취소","연속"]
[263,"강원","동해","북평영동TP#2 T/L","2018~2019년도 동해전력지사 송전정비협력회사 총액공사","154kV 동해분기T/L 인출정비공사 철탑 4기 철거, 2기 신설","2019-10-18 08:00","2019-10-20 18:00","취소","취소","연속"]
[264,"강원","동해","태백삼척GP#2 T/L","2019년 동해전력지사 장기미동작 차단기 조작시험","1. 장기미동작 차단기 조작시험","2019-10-08 10:00","2019-10-08 13:00","2019-10-08 10:00","2019-10-08 13:00","당일"]
[265,"강원","동해","삼척G/PS/S 154kV 기동#1T/L CB","2019년 동해전력지사 장기미동작 차단기 조작시험","1. 장기미동작 차단기 조작시험","2019-10-11 10:00","2019-10-11 13:00","2019-10-11 10:00","2019-10-11 13:00","당일"]
[266,"강원","동해","삼척G/PS/S 154kV 기동#2T/L CB","2019년 동해전력지사 장기미동작 차단기 조작시험","1. 장기미동작 차단기 조작시험","2019-10-11 13:00","2019-10-11 18:00","2019-10-11 13:00","2019-10-11 18:00","당일"]
[267,"강원","동해","울진삼척GP#2 T/L","2019년 동해전력지사 장기미동작 차단기 조작시험","1. 장기미동작 차단기 조작시험","2019-10-10 10:00","2019-10-10 13:00","2019-10-10 10:00","2019-10-10 13:00","당일"]
[268,"강원","동해","동해정선 T/L","2019년 동해전력지사 변전협력회사 총액공사","1. LA 초기점검","2019-10-07 10:00","2019-10-07 15:00","2019-10-07 10:00","2019-10-07 15:00","당일"]
[269,"강원","원주","홍천상남#2 T/L","2018~2019년도 송전정비 협력회사 총액공사","○ 작업명 : 항공장애표시구 정비 ○ 작업구간 : No.64~65등 10개소 38개 교체","2019-10-14 07:00","2019-10-17 18:00","2019-10-14 07:00","2019-10-17 18:00","매일"]
[270,"강원","원주","홍천상남#1 T/L","2018~2019년도 송전정비 협력회사 총액공사","○ 작업명 : 항공장애표시구 정비 ○ 작업구간 : No.64~65등 10개소 38개 교체","2019-10-07 07:00","2019-10-11 18:00","2019-10-07 07:00","2019-10-11 18:00","매일"]
[271,"강원","직할","남춘천춘천열병합#2 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 남춘천-춘천열병합T/L 초기점검","2019-10-21 09:00","2019-10-23 18:00","2019-10-28  9:00","2019-10-30  18:00","매일"]
["272","강원","직할","남춘천춘천열병합#1 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 남춘천-춘천열병합T/L 초기점검","2019-10-16 09:00","2019-10-18 18:00","2019-10-21  9:00","2019-10-23  18:00","매일"]
[273,"강원","직할","상남인제#2 T/L","18~19 강원직할 송전정비회사 총액공사","상남-인제#2T/L No.34 중단 섬락애자 교체","2019-10-02 09:00","2019-10-02 17:00","2019-10-02 09:00","2019-10-02 17:00","당일"]
["274","강원","직할","춘천북춘천#2 T/L","154kV 인제-양구 등 12개T/L PD집합반 설치공사","춘천북춘천#2T/L EBA PD진단센서 및 집합반 설치공사","2019-10-08 09:00","2019-10-08 18:00","2019-10-15 9:00","2019-10-15  18:00","당일"]
["275","강원","직할","춘천소양강HP T/L","154kV 인제-양구 등 12개T/L PD집합반 설치공사","춘천소양강HP T/L EBA PD진단센서 및 집합반 설치공사","2019-10-08 09:00","2019-10-08 18:00","2019-10-15 9:00","2019-10-15  18:00","당일"]
["276","강원","직할","춘천북춘천#1 T/L","154kV 인제-양구 등 12개T/L PD집합반 설치공사","춘천북춘천#1T/L EBA PD진단센서 및 집합반 설치공사","2019-10-07 09:00","2019-10-07 18:00","2019-10-14 9:00","2019-10-14  18:00","당일"]
["277","강원","직할","남춘천춘천 T/L","154kV 인제-양구 등 12개T/L PD집합반 설치공사","남춘천춘천T/L EBA PD진단센서 및 집합반 설치공사","2019-10-07 09:00","2019-10-07 18:00","2019-10-14 9:00","2019-10-14  18:00","당일"]
["278","강원","직할","북춘천춘천HP T/L","19년 장기사용 노후배전반 교체공사","보호배전반 2면 교체 및 기타부대공사","2019-10-15 10:00","2019-10-17 18:00","2019-10-16 9:00","2019-10-18 18:00","연속"]
[279,"강원","직할","가평춘천HP T/L","154kV 화천T/L No.65~69 안전이격확보공사","No.65~69 철탑교체(5기), 전력선 2.132km 교체","2019-10-03 08:00","2019-10-10 18:00","2019-10-03 08:00","2019-10-10 18:00","연속"]
[280,"강원","직할","서홍천춘천열병합 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 남춘천-춘천열병합T/L 초기점검","2019-10-21 09:00","2019-10-23 18:00","2019-10-28 9:00","2019-10-30\n18:00","매일"]
[281,"강원","직할","청평PP춘천열병합 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 남춘천-춘천열병합T/L 초기점검","2019-10-16 09:00","2019-10-18 18:00","2019-10-21  9:00","2019-10-23  18:00","매일"]
[282,"강원","직할","북춘천화천HP T/L","차단기 접속단자 과열관련 설비 보강공사","차단기 1차측 단자 교체 및 부대공사","2019-10-01 10:00","2019-10-01 18:00","2019-10-11 10:00","2019-10-11  18:00","당일"]
[283,"강원","태백","영월C/C 154kV 영월G/T#3T/L CB","영월발전본부 계획예방정비공사 및 정기검사","영월발전본부 GT#3 주변압기 법정검사","2019-10-25 10:00","2019-10-25 15:00","2019-10-25 10:00","2019-10-25 15:00","당일"]
[284,"충북","직할","진천광혜원#2 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","CVT 1EA, LA 3EA 이설","2019-10-03 09:00","2019-10-03 18:00","2019-10-17 09:00","2019-10-18 18:00","연속"]
[285,"충북","직할","진천광혜원#1 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","안전거리 이격(기기기초 터파기)","2019-10-13 09:00","2019-10-15 18:00","2019-10-26 09:00","2019-10-26 18:00","매일"]
[286,"충북","직할","진천광혜원#2 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","안전거리 이격(기기기초 터파기)","2019-10-10 09:00","2019-10-12 18:00","2019-10-25 09:00","2019-10-25 18:00","매일"]
[287,"충북","직할","서운광혜원 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","안전거리 이격(기기기초 터파기)","2019-10-06 09:00","2019-10-09 18:00","2019-10-21 09:00","2019-10-23 18:00","매일"]
[288,"충북","직할","진천광혜원#1 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","CVT 1EA 이설, LA 3EA 철거","2019-10-02 09:00","2019-10-02 18:00","2019-10-15 09:00","2019-10-16 18:00","연속"]
[289,"충북","직할","신진천진천#1 T/L","154kV 신진천-진천T/L OPGW 증설공사","154kV 신진천-진천T/L 가공지선 철거 및 OPGW 10km 시설","2019-10-20 09:00","2019-10-20 18:00","취소","취소","당일"]
[290,"충북","직할","신진천진천#2 T/L","154kV 신진천-진천T/L OPGW 증설공사","154kV 신진천-진천T/L 가공지선 철거 및 OPGW 10km 시설","2019-10-19 09:00","2019-10-19 18:00","취소","취소","당일"]
[291,"충북","직할","신진천오창#2 T/L","154kV 신진천-진천T/L OPGW 증설공사","154kV 신진천-진천T/L 가공지선 철거 및 OPGW 10km 시설","2019-10-19 09:00","2019-10-20 18:00","2019-10-19 09:00","2019-10-20 18:00","연속"]
[292,"충북","직할","진천덕산#1 T/L","2018~19년 직할 송전정비회사 총액공사","No.26 불량애자교체","2019-10-17 08:00","2019-10-17 18:00","2019-10-20 08:00","2019-10-20 14:00","당일"]
[293,"충북","청주","남청주청주#3 T/L","154kV 청원-청주T/L 계통정비공사","17호 철탑 교체(1기), 18호 철탑 철거(2기), 전력선교체(4.104C-km)","2019-10-18 08:00","2019-10-23 18:00","2019-10-31 08:00","2019-11-05 18:00","연속"]
[294,"충북","청주","남청주오송#2 T/L","18-19년 청주전력 변전협력회사 총액공사","남청주S/S 남청주오송#2T/L 154kV GIS 보통점검, CVT, LA 대체","2019-10-12 09:30","2019-10-13 18:00","2019-10-12 09:30","2019-10-13 18:00","연속"]
[295,"충북","청주","남청주청주#1 T/L","154kV 청원-청주T/L 계통정비공사","17호 철탑 교체(1기), 18호 철탑 철거(2기), 전력선교체(4.104C-km)","2019-10-01 08:00","2019-10-05 18:00","2019-10-14 08:00","2019-10-18 18:00","연속"]
[296,"충북","청주","남청주청주#3 T/L","154kV 청원-청주T/L 계통정비공사","17호 철탑 교체(1기), 18호 철탑 철거(2기), 전력선교체(4.104C-km)","2019-10-01 08:00","2019-10-05 18:00","2019-10-14 08:00","2019-10-18 18:00","연속"]
[297,"충북","청주","남청주청주#2 T/L","154kV 청원-청주T/L 계통정비공사","17호 철탑 교체(1기), 18호 철탑 철거(2기), 전력선교체(4.104C-km)","2019-10-06 08:00","2019-10-17 18:00","2019-10-19 08:00","2019-10-30 18:00","연속"]
[298,"충북","청주","남청주죽림#2 T/L","18-19년 청주전력 변전협력회사 총액공사","남청주S/S,죽림S/S 남청주죽림#2T/L 154kV GIS 보통점검 죽림S/S 남청주죽림#2T/L 144kV 피뢰기 대체","2019-10-26 10:00","2019-10-27 18:00","2019-10-26 10:00","2019-10-27 18:00","연속"]
[299,"충북","청주","남청주청주#2 T/L","154kV 청원-청주T/L 계통정비공사","17호 철탑 교체(1기), 18호 철탑 철거(2기), 전력선교체(4.104C-km)","2019-10-24 08:00","2019-10-28 18:00","취소","취소","연속"]
[300,"충북","청주","남청주청주#1 T/L","154kV 청원-청주T/L 계통정비공사","17호 철탑 교체(1기), 18호 철탑 철거(2기), 전력선교체(4.104C-km)","2019-10-18 08:00","2019-10-23 18:00","2019-10-31 08:00","2019-11-05 18:00","연속"]
[301,"충북","청주","상주보은 T/L","154kV 상주T/L 안전이격거리 확보공사","154kV 상주T/L 안전이격 확보공사 - 철탑 1기 교체 - 전선교체 : No.86 ~ 88","2019-10-16 08:00","2019-10-17 18:00","2019-10-16 08:00","2019-10-17 18:00","연속"]
[302,"충북","청주","상주보은 T/L","154kV 상주T/L 안전이격거리 확보공사","154kV 상주T/L 안전이격 확보공사 - 철탑 1기 교체 - 전선교체 : No.86 ~ 88","2019-10-18 08:00","2019-10-19 18:00","2019-10-18 08:00","2019-10-19 18:00","연속"]
[303,"충북","청주","신옥천남대전#2 T/L","신옥천S/S 154kV GIS화 공사","154kV GIS 26CCT 설치 옥외철구→GIS 부하절체","2019-10-10 09:00","2019-10-15 18:00","2019-10-10 09:00","2019-10-15 18:00","연속"]
[304,"충북","청주","신옥천용운#2 T/L","신옥천S/S 154kV GIS화 공사","154kV GIS 26CCT 설치 옥외철구→GIS 부하절체","2019-10-07 09:00","2019-10-09 18:00","2019-10-07 09:00","2019-10-09 18:00","연속"]
[305,"충북","청주","신옥천추부#1 T/L","신옥천S/S 154kV GIS화 공사","154kV GIS 26CCT 설치 옥외철구→GIS 부하절체","2019-10-24 09:00","2019-10-26 18:00","2019-10-24 09:00","2019-10-26 18:00","연속"]
[306,"충북","청주","신옥천남대전#3 T/L","신옥천S/S 154kV GIS화 공사","154kV GIS 26CCT 설치 옥외철구→GIS 부하절체","2019-10-28 09:00","2019-10-30 18:00","2019-10-28 09:00","2019-10-30 18:00","연속"]
[307,"충북","청주","신옥천남대전#4 T/L","신옥천S/S 154kV GIS화 공사","154kV GIS 26CCT 설치 옥외철구→GIS 부하절체","2019-10-31 09:00","2019-11-02 18:00","2019-10-31 09:00","2019-11-02 18:00","연속"]
[308,"충북","청주","상주영동 T/L","154kV 상주T/L 안전이격거리 확보공사","154kV 상주T/L 안전이격 확보공사 - 철탑 1기 교체 - 전선교체 : No.86 ~ 88","2019-10-18 08:00","2019-10-19 18:00","2019-10-18 08:00","2019-10-19 18:00","연속"]
[309,"충북","청주","상주영동 T/L","154kV 상주T/L 안전이격거리 확보공사","154kV 상주T/L 안전이격 확보공사 - 철탑 1기 교체 - 전선교체 : No.86 ~ 88","2019-10-16 08:00","2019-10-17 18:00","2019-10-16 08:00","2019-10-17 18:00","연속"]
[310,"충북","청주","오송북청주#1 T/L","18-19년 청주전력 변전협력회사 총액공사","오송S/S,북청주S/S 오송북청주#1T/L 154kV GIS 보통점검","2019-10-03 10:00","2019-10-03 18:00","2019-10-03 10:00","2019-10-03 18:00","당일"]
[311,"충북","충주","금왕남음성#1 T/L","2018~19년 직할 송전정비회사 총액공사","No.2~16 조류퇴치방지장치설치","2019-10-11 09:00","2019-10-11 18:00","2019-10-11 09:00","2019-10-11 18:00","당일"]
[312,"충북","충주","음성금왕#2 T/L","2018~19년 직할 송전정비회사 총액공사","154kV 금왕-남음성#1T/L 안전이격확보","2019-10-11 09:00","2019-10-11 18:00","2019-10-11 09:00","2019-10-11 18:00","당일"]
[313,"충북","충주","음성금왕#1 T/L","2018~19년 직할 송전정비회사 총액공사","154kV 금왕-남음성#2T/L 안전이격확보","2019-10-12 09:00","2019-10-12 18:00","2019-10-12 09:00","2019-10-12 18:00","당일"]
[314,"충북","충주","금왕남음성#2 T/L","2018~19년 직할 송전정비회사 총액공사","No.2~16 조류퇴치방지장치설치","2019-10-12 09:00","2019-10-12 18:00","2019-10-12 09:00","2019-10-12 18:00","당일"]
[315,"충북","충주","문경단양 T/L","18-19년 직할 변전정비 총액공사","단양S/S 154kV 문경단양T/L GIS 보통점검. 공기조작부 정밀점검.","2019-10-07 09:00","2019-10-07 18:00","2019-10-07 09:00","2019-10-07 18:00","당일"]
[316,"충북","충주","신제천S/S 154KV #62-#67 BUS TIE GIS","'18-19년 직할 변전정비 총액공사","154kV GIS 보통점검","2019-10-25 09:00","2019-10-25 18:00","2019-10-25 09:00","2019-10-25 18:00","당일"]
[317,"충북","충주","신제천제천#1 T/L","2018-2019년 송전정비회사 총액공사","154kV 피뢰기 설치 (No.1-5)","2019-10-24 08:00","2019-10-25 18:00","2019-10-24 08:00","2019-10-25 18:00","매일"]
[318,"충북","충주","신제천주진#2 T/L","'18-19년 직할 변전정비 총액공사","신제천S/S 154kV 신제천-주진#2T/L GIS 보통점검","2019-10-10 09:00","2019-10-10 18:00","2019-10-10 09:00","2019-10-10 18:00","당일"]
[319,"충북","충주","신제천S/S 154KV #65-#66 SEC GIS","'18-19년 직할 변전정비 총액공사","154kV GIS 보통점검","2019-10-18 09:00","2019-10-18 14:00","2019-10-18 09:00","2019-10-18 14:00","당일"]
[320,"충북","충주","신제천왕암#1 T/L","2018-2019년 송전정비회사 총액공사","154kV 피뢰기 설치 (No.1-5)","2019-10-24 08:00","2019-10-25 18:00","2019-10-24 08:00","2019-10-25 18:00","매일"]
[321,"충북","충주","신제천S/S 154KV #61-#66 BUS TIE GIS","'18-19년 직할 변전정비 총액공사","154kV GIS 보통점검","2019-10-18 14:00","2019-10-18 18:00","2019-10-18 14:00","2019-10-18 18:00","당일"]
[322,"충북","충주","신제천제천#1 T/L","신제천S/S 신제천제천#1T/L 보호반 제작사 점검","보호배전반 제작사(세니온) 하자점검(43PDA 교체 등)","2019-10-15 10:00","2019-10-15 16:00","2019-10-15 10:00","2019-10-15 16:00","당일"]
[323,"충북","충주","충주충주HP#1 T/L","충주 H/P 송전선 보호계전기 시험","충주 H/P 송전선 보호계전기 시험","2019-10-21 13:00","2019-10-21 18:00","2019-10-21 13:00","2019-10-21 18:00","당일"]
[324,"충북","충주","충주충주HP#2 T/L","충주 H/P 송전선 보호계전기 시험","충주 H/P 송전선 보호계전기 시험","2019-10-23 09:00","2019-10-23 18:00","2019-10-23 09:00","2019-10-23 18:00","당일"]
[325,"충북","충주","충주충주HP#1 T/L","충주 H/P 송전선 보호계전기 시험","충주 H/P 송전선 보호계전기 시험","2019-10-22 09:00","2019-10-22 18:00","2019-10-22 09:00","2019-10-22 18:00","당일"]
[326,"충북","충주","충주충주HP#2 T/L","충주 H/P 송전선 보호계전기 시험","충주 H/P 송전선 보호계전기 시험","2019-10-24 09:00","2019-10-24 18:00","2019-10-24 09:00","2019-10-24 18:00","당일"]
[327,"대전충남","대전","가수원S/S 154kV LH열병합T/L GIS","[고객요청] 가수원S/S 154kV LH열병합 T/L 점검 및 병행작업","[고객요청] 가수원S/S 154kV LH열병합 T/L 점검 및 병행작업","2019-10-07 09:00","2019-10-18 18:00","2019-10-07 09:00","2019-10-18 18:00","연속"]
[328,"대전충남","서산","신당진당진#2 T/L","당진S/S 154kV측 취약설비 GIS화","154kV 옥외철구형 설비 GIS화 - 옥외설비 철거(GCB, DS, GIDS, LA, CVT 등) - 옥외철구 전력선 교체(CU-&gtAL) 디지털 혼용운영시스템 이설 신설GIS 무부하 가압(24H)","2019-10-14 08:00","2019-10-18 18:00","2019-10-14 08:00","2019-10-18 18:00","연속"]
[329,"대전충남","서산","당진송악#1 T/L","당진S/S 154kV측 취약설비 GIS화","154kV 옥외철구형 설비 GIS화 - 옥외설비 철거(GCB, DS, GIDS, LA, CVT 등) - 옥외철구 전력선 교체(CU-&gtAL) 디지털 혼용운영시스템 이설","2019-10-14 08:00","2019-10-18 18:00","2019-10-14 08:00","2019-10-18 18:00","연속"]
[330,"대전충남","서산","당진S/S 154kV #1 SC","당진S/S 154kV측 취약설비 GIS화","#1SH.C용 전력케이블 활용 신설 및 기설 모선 연결 - 기설 GCB와 Sh.C 간 결선분리 - 기설 GCB와 EBA 간 연결 - 기타부대작업","2019-10-07 09:00","2019-10-18 18:00","2019-10-07 09:00","2019-10-18 18:00","연속"]
[331,"대전충남","서산","석문당진화력#1 T/L","서산P/O 170kV GIS 정밀점검공사","석문S/S 석문당진화력#1 T/L GIS(617) 정밀점검 당진화력S/S 석문당진화력#1 T/L GIS(627) 보통점검","2019-10-30 14:00","2019-11-01 18:00","2019-10-30 14:00","2019-11-01 18:00","연속"]
[332,"대전충남","서산","대산석문#1 T/L","서산P/O 170kV 정밀점검공사","석문S/S 대산석문#1 T/L GIS(657) 정밀점검 대산S/S 대산석문#1 T/L GIS(6D7) 보통점검","2019-10-23 09:00","2019-10-25 18:00","2019-10-23 09:00","2019-10-25 18:00","연속"]
[333,"대전충남","서산","대산석문#2 T/L","서산P/O 170kV 정밀점검공사","석문S/S 대산석문#2 T/L GIS(647) 정밀점검 대산S/S 대산석문#2 T/L GIS(697) 보통점검","2019-10-28 09:00","2019-10-30 14:00","2019-10-28 09:00","2019-10-30 14:00","연속"]
[334,"대전충남","서산","합덕송악#2 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기 설치공사","154kV 합덕-송악 #2T/L 피뢰기 설치 (27기, 81set) [안전이격거리 확보] 345kV 신서산-아산#2T/L [병행] 345kV 신서산-아산T/L 전선교체공사","2019-10-12 07:00","2019-10-13 18:00","2019-10-12 07:00","2019-10-13 18:00","매일"]
[335,"대전충남","서산","합덕송악#1 T/L","154kV 합덕-송악T/L 항공장애표시구 교체","154kV 합덕-송악T/L No.47~48 항공장애표시구 교체","2019-10-09 09:00","2019-10-09 18:00","2019-10-09 09:00","2019-10-09 18:00","당일"]
[336,"대전충남","세종","덕진송강#2 T/L","154kV 세종-송강, 덕진-대화 연결 지중T/L 건설공사","1. 설치 가. 세종-송강 : 신설C/H~M/H#4 나. 덕진-대화 : 덕진E/C~신설C/H 2. 철거 : 덕진-송강T/L(덕진E/C~M/H#4)","2019-10-10 09:30","2019-10-23 17:00","2019-10-10 09:30","2019-10-23 17:00","연속"]
[337,"대전충남","세종","월산서세종 T/L","[송전]154kV 월산-서세종T/L EBA 절연유 채유작업","154kV 월산-서세종T/L EBA 절연유 채유로 열화진단","2019-10-10 08:00","2019-10-10 18:00","2019-10-10 08:00","2019-10-10 18:00","당일"]
[338,"대전충남","아산","한샘둔포#2 T/L","둔포S/S 154kV 한샘-둔포#2T/L GIS 전자변 교체","둔포S/S 154kV 한샘-둔포#2T/L GIS 전자변 교체","2019-10-22 09:00","2019-10-22 18:00","2019-10-22 09:00","2019-10-22 18:00","당일"]
[339,"대전충남","아산","장재불당#1 T/L","불당S/S 154kV 장재-불당#1TL 전자변 교체","불당S/S 154kV 장재-불당#1TL 전자변 교체","2019-10-15 09:00","2019-10-15 13:00","취소","취소","당일"]
[340,"대전충남","아산","서천안탕정#1 T/L","154kV 장재-천안 등 4개T/L 일진제 PMJ 교체공사","일진제 R-type 조립식접속함(PMJ) 교체","2019-10-28 08:00","2019-11-03 18:00","취소","취소","연속"]
[341,"대전충남","아산","아산합덕#2 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기 설치공사","154kV 아산-합덕 #2T/L 피뢰기 설치 (16기, 44set) [안전이격거리 확보] 345kV 신서산-아산#2T/L","2019-10-05 07:00","2019-10-06 18:00","2019-10-05 07:00","2019-10-06 18:00","매일"]
[342,"대전충남","아산","아산합덕#1 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기 설치공사","[안전이격거리] 154kV 아산-인주 #1T/L 피뢰기 설치 (10기, 30set)","2019-10-19 07:00","2019-10-20 18:00","2019-10-19 07:00","2019-10-20 18:00","매일"]
[343,"대전충남","아산","아산인주#1 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기 설치공사","154kV 아산-인주 #1T/L 피뢰기 설치 (10기, 30set) [안전이격거리확보] 154kV 아산-합덕 #1T/L","2019-10-19 07:00","2019-10-20 18:00","2019-10-19 07:00","2019-10-20 18:00","매일"]
[344,"대전충남","아산","아산합덕#1 T/L","[송전]345kV 신서산-아산 등 2개T/L 지장송전선로 이설공사","가. 철탑 설치 및 철거 : 2기 [No.83(B4-28 → Bb4-36), No.84(F4-29 → F4-39)] 나. 전력선교체 - ACSR 480㎟ x 4B x 2C × 1.778km [No.82~83 1선 교체, No.83~88 24선 교체] - ACSR 410㎟ x 2B x 2C × 1.778km [No.83~88 24선 교체]","2019-10-14 07:00","2019-10-24 18:00","취소","취소","연속"]
[345,"대전충남","아산","아산합덕#2 T/L","[송전]345kV 신서산-아산 등 2개T/L 지장송전선로 이설공사","가. 철탑 설치 및 철거 : 2기 [No.83(B4-28 → Bb4-36), No.84(F4-29 → F4-39)] 나. 전력선교체 - ACSR 480㎟ x 4B x 2C × 1.778km [No.82~83 1선 교체, No.83~88 24선 교체] - ACSR 410㎟ x 2B x 2C × 1.778km [No.83~88 24선 교체]","2019-10-25 07:00","2019-11-04 18:00","취소","취소","연속"]
[346,"대전충남","아산","아산인주#2 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기 설치공사","154kV 아산-인주 #2T/L (9기 - 27set)","2019-10-05 07:00","2019-10-05 18:00","2019-10-05 07:00","2019-10-05 18:00","당일"]
[347,"대전충남","아산","온양풍세#1 T/L","온양S/S 154kV 온양-풍세#1TL 전자변 교체공사","온양S/S 154kV 온양-풍세#1TL 전자변 교체공사","2019-10-16 09:00","2019-10-16 13:00","2019-10-20 09:00","2019-10-20 13:00","당일"]
[348,"대전충남","아산","풍세장재#1 T/L","154kV 장재-천안 등 4개T/L 일진제 PMJ 교체공사","일진제 R-type 조립식접속함(PMJ) 교체","2019-10-14 08:00","2019-10-20 18:00","취소","취소","연속"]
[349,"대전충남","아산","풍세장재#2 T/L","154kV 장재-천안 등 4개T/L 일진제 PMJ 교체공사","일진제 R-type 조립식접속함(PMJ) 교체","2019-10-21 08:00","2019-10-27 18:00","취소","취소","연속"]
[350,"대전충남","청양","관창보령복합 T/L","154kV 관창-보령화력 등 3개T/L 자기애관 교체공사","154kV 관창-보령복합T/L C/H#1 자기애관 6상 → 폴리머애관 교체","2019-10-01 09:00","2019-10-04 18:00","2019-10-01 09:00","2019-10-04 18:00","연속"]
[351,"대전충남","서산","신당진S/S 154kV #60 BUS","19년도 서산P/O 154kV GIS 정밀점검공사","- 신당진S/S 154kV 신당진-당진#2T/L #1DS 정밀점검","2019-10-15 09:00","2019-10-15 18:00","2019-10-15 09:00","2019-10-15 18:00","당일"]
[352,"대전충남","서산","신당진S/S 154kV #65 BUS","19년도 서산P/O 154kV GIS 정밀점검공사","- 신당진S/S 154kV 신당진-당진#2T/L #2DS 정밀점검","2019-10-16 09:00","2019-10-16 18:00","2019-10-16 09:00","2019-10-16 18:00","당일"]
[353,"전북","군산","군산S/S 154kV 군산-동군산#1T/L GIS","군산P/O 170kV GIS 정밀점검공사","군산S/S 170kV #2M.Tr 2차 GIS 정밀점검공사 (군산-동군산#1T/L 활용 무부하 가압)","2019-10-04 15:00","2019-10-04 17:00","2019-10-04 15:00","2019-10-04 17:00","연속"]
[354,"전북","군산","군산동군산#2 T/L","군산P/O 차단기 조작시험","군산-동군산#2T/L 차단기 조작시험","2019-10-07 09:00","2019-10-07 18:00","2019-10-07 09:00","2019-10-07 18:00","당일"]
[355,"전북","군산","군산S/S 154kV #66 BUS","군산P/O 170kV GIS 정밀점검공사","군산S/S 170kV #2M.Tr 2차 GIS 정밀점검공사 (군산-동군산#1T/L 활용 무부하 가압)","2019-10-04 15:00","2019-10-04 17:00","2019-10-04 15:00","2019-10-04 17:00","연속"]
[356,"전북","군산","군산S/S 154kV #60 BUS","군산P/O 170kV GIS 정밀점검공사","군산S/S 170kV #1M.TR 2차 GIS 정밀점검공사 (군산-이리#1T/L 활용 무부하 가압)","2019-10-02 15:00","2019-10-02 17:00","2019-10-02 15:00","2019-10-02 17:00","당일"]
[357,"전북","군산","군산S/S 154kV 군산-이리#1T/L GIS","군산P/O 170kV GIS 정밀점검공사","군산S/S 170kV #1M.TR 2차 GIS 정밀점검공사 (군산-이리#1T/L 활용 무부하 가압)","2019-10-02 15:00","2019-10-02 17:00","2019-10-02 15:00","2019-10-02 17:00","당일"]
[358,"전북","군산","군산서군산#2 T/L","서군산S/S 현대화관련 부지확보공사","서군산S/S 현대화관련 부지확보공사","2019-10-29 09:00","2019-11-06 18:00","2019-10-29 09:00","2019-11-06 18:00","연속"]
[359,"전북","군산","이리전주#2 T/L","154kV 이리-전주T/L 일부지중화관련 철탑교체공사","- 철탑교체 4기 : 49, 50, 51, 52호 - 전선교체 : 47~50, 51~53호 - 가선로 구성 및 기타 부대공사","2019-10-22 09:00","2019-10-31 18:00","2019-10-22 09:00","2019-10-31 18:00","연속"]
[360,"전북","김제","정주고창#2 T/L","154kV 정주-고창 안전이격거리 확보공사","철탑 교체 : No.39, 40 전력선 교체 : No.37~41","2019-10-22 08:00","2019-10-28 18:00","2019-10-22 08:00","2019-10-28 18:00","연속"]
[361,"전북","김제","정주고창#1 T/L","154kV 정주-고창 안전이격거리 확보공사","철탑 교체 : No.39, 40 전력선 교체 : No.37~41","2019-10-21 08:00","2019-10-21 18:00","2019-10-21 08:00","2019-10-21 18:00","당일"]
[362,"전북","김제","정주고창#1 T/L","154kV 정주-고창 안전이격거리 확보공사","철탑 교체 : No.39, 40 전력선 교체 : No.37~41","2019-10-29 09:00","2019-11-04 18:00","2019-10-29 09:00","2019-11-04 18:00","연속"]
[363,"전북","김제","김제칠보HP T/L","칠보S/Y 김제-칠보T/L 가스누기 보수공사","칠보S/Y 김제-칠보T/L 가스누기 보수공사","2019-10-14 09:00","2019-10-18 18:00","2019-10-14 09:00","2019-10-18 18:00","연속"]
[364,"전북","김제","칠보H/P 154kV #1 M.Tr 1차 GIS","칠보S/Y 김제-칠보T/L 가스누기 보수공사","칠보S/Y 김제-칠보T/L 가스누기 보수공사","2019-10-14 09:00","2019-10-18 18:00","2019-10-14 09:00","2019-10-18 18:00","연속"]
[365,"전북","김제","칠보H/P 154kV #60 BUS","칠보S/Y 김제-칠보T/L 가스누기 보수공사","칠보S/Y 김제-칠보T/L 가스누기 보수공사","2019-10-14 09:00","2019-10-18 18:00","2019-10-14 09:00","2019-10-18 18:00","연속"]
[366,"전북","김제","임실남전주#2 T/L","154kV 남전주-임실T/L OPGW 증설공사","가공지선 철거후 OPGW 교체(38km) 및 항공구 정비","2019-10-01 09:00","2019-11-09 18:00","2019-10-01 09:00","2019-11-09 18:00","연속"]
[367,"전북","김제","정공S/S 154kV #60-#65 BUS TIE CB","154kV 정공E/C #5M.Tr 및 KCFT T/L 증설 공사","- 154kV M.Tr(15/20MVA *3대) * 1BANK 설치 - 170kV GIS(1250A) * 2CCT 설치 - 22.9kV GIS(2000A, 600A) * 4CCT 설치","2019-10-02 08:00","2019-10-10 18:00","2019-10-02 08:00","2019-10-10 18:00","연속"]
[368,"전북","김제","정공칠보HP T/L","154kV 정공-정주T/L 정밀점검","No.1~31호 정밀점검 4회선 구간 안전거리 확보","2019-10-21 08:00","2019-10-21 18:00","2019-10-21 08:00","2019-10-21 18:00","당일"]
[369,"전북","김제","정공정주#1 T/L","154kV 정공-정주T/L 정밀점검","No.1~31호 정밀점검","2019-10-21 08:00","2019-10-22 18:00","2019-10-21 08:00","2019-10-22 18:00","매일"]
[370,"전북","김제","정공담양 T/L","154kV 정공-정주T/L 정밀점검","No.1~31호 정밀점검 4회선 구간 안전거리 확보","2019-10-23 08:00","2019-10-23 18:00","2019-10-23 08:00","2019-10-23 18:00","당일"]
[371,"전북","김제","정공정주#2 T/L","154kV 정공-정주T/L 정밀점검","No.1~31호 정밀점검","2019-10-23 08:00","2019-10-24 18:00","2019-10-23 08:00","2019-10-24 18:00","매일"]
[372,"전북","김제","신김제정공#1 T/L","154kV 신김제-정공T/L 정밀점검","No.1~11호 신김제-정공T/L 정밀점검","2019-10-29 08:00","2019-10-29 18:00","2019-10-29 08:00","2019-10-29 18:00","당일"]
[373,"전북","김제","정공S/S 154kV #60-#65 BUS TIE CB","154kV 정공E/C #5M.Tr 및 KCFT T/L 증설 공사","- 154kV M.Tr(15/20MVA *3대) * 1BANK 설치 - 170kV GIS(1250A) * 2CCT 설치 - 22.9kV GIS(2000A, 600A) * 4CCT 설치","2019-10-24 09:00","2019-10-25 09:00","2019-10-24 09:00","2019-10-25 09:00","연속"]
[374,"전북","김제","정공S/S 154kV #60 BUS","154kV 정공E/C #5M.Tr 및 KCFT T/L 증설 공사","- 154kV M.Tr(15/20MVA *3대) * 1BANK 설치 - 170kV GIS(1250A) * 2CCT 설치 - 22.9kV GIS(2000A, 600A) * 4CCT 설치","2019-10-24 09:00","2019-10-25 09:00","2019-10-24 09:00","2019-10-25 09:00","연속"]
[375,"전북","김제","신김제정공#1 T/L","154kV 정공E/C #5M.Tr 및 KCFT T/L 증설 공사","- 154kV M.Tr(15/20MVA *3대) * 1BANK 설치 - 170kV GIS(1250A) * 2CCT 설치 - 22.9kV GIS(2000A, 600A) * 4CCT 설치","2019-10-24 09:00","2019-10-25 09:00","2019-10-24 09:00","2019-10-25 09:00","연속"]
[376,"전북","김제","신김제정공#1 T/L","154kV 정공E/C #5M.Tr 및 KCFT T/L 증설 공사","- 154kV M.Tr(15/20MVA *3대) * 1BANK 설치 - 170kV GIS(1250A) * 2CCT 설치 - 22.9kV GIS(2000A, 600A) * 4CCT 설치","2019-10-02 08:00","2019-10-10 18:00","2019-10-02 08:00","2019-10-10 18:00","연속"]
[377,"전북","김제","정공S/S 154kV #65 BUS","154kV 정공E/C #5M.Tr 및 KCFT T/L 증설 공사","- 154kV M.Tr(15/20MVA *3대) * 1BANK 설치 - 170kV GIS(1250A) * 2CCT 설치 - 22.9kV GIS(2000A, 600A) * 4CCT 설치","2019-10-02 08:00","2019-10-10 18:00","2019-10-02 08:00","2019-10-10 18:00","연속"]
[378,"전북","김제","신김제정공#2 T/L","154kV 신김제-정공T/L 정밀점검","No.1~11호 신김제-정공T/L 정밀점검","2019-10-31 08:00","2019-10-31 18:00","2019-10-31 08:00","2019-10-31 18:00","당일"]
[379,"전북","직할","신김제동전주#1 T/L","154kV 남전주-임실T/L OPGW 증설공사","가공지선 철거후 OPGW 교체(38km) 및 항공구 정비","2019-10-29 09:00","2019-10-30 18:00","2019-10-29 09:00","2019-10-30 18:00","연속"]
[380,"전북","직할","신김제동전주#2 T/L","154kV 남전주-임실T/L OPGW 증설공사","가공지선 철거후 OPGW 교체(38km) 및 항공구 정비","2019-10-31 09:00","2019-11-01 18:00","2019-10-31 09:00","2019-11-01 18:00","연속"]
[381,"전북","직할","무주용담수력 T/L","관내S/S 노후배전반 대체공사","1. 154kV 무주-용담수력T/L 보호배전반 대체","2019-10-14 10:00","2019-10-23 18:00","2019-10-14 10:00","2019-10-23 18:00","연속"]
[382,"전북","직할","북전주용담수력 T/L","154kV 북전주-용담수력T/L 압축인류 클램프 교체공사","압축인류 클램프 교체 - No.26 상단 부하측","2019-10-07 09:00","2019-10-07 18:00","2019-10-07 09:00","2019-10-07 18:00","당일"]
[383,"광주전남","강진","신강진강진#1 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","신강진보호배전반 대체, 시험, LA, CVT 이설 송전선로 철거 및 가선, 선로접속, 모선철구 철거","2019-10-06 09:00","2019-10-17 18:00","취소","취소","연속"]
[384,"광주전남","강진","남창S/S 154kV 강진-남창#2T/L CB A","강진S/S 154kV 이하 취약설비 GIS화 사업","송전선로 가선, 선로접속, LA, CVT이설 강진-남창#2T/L, 신강진-강진#2T/L 직결해제","2019-10-18 09:00","2019-10-31 18:00","취소","취소","연속"]
[385,"광주전남","강진","신강진S/S 154kV 신강진-강진#2T/L CB","강진S/S 154kV이하 취약설비 GIS화 사업","송전선로 가선, 선로접속, LA,CVT 이설 강진-남창#2T/L, 신강진-강진#2T/L 직결해제","2019-10-18 09:00","2019-10-31 18:00","취소","취소","연속"]
[386,"광주전남","강진","해남진도#1 T/L","154kV 해남-진도T/L (불량U볼트 교체공사)","2018~2019 송전정비회사 총액공사 154kV 해남-진도T/L (불량U볼트 교체공사)","2019-10-01 08:00","2019-10-02 17:00","2019-10-01 08:00","2019-10-02 17:00","매일"]
[387,"광주전남","강진","해남진도#2 T/L","154kV 해남-진도T/L (불량U볼트 교체공사)","2018~2019 송전정비회사 총액공사 154kV 해남-진도T/L (불량U볼트 교체공사)","2019-10-03 08:00","2019-10-04 17:00","2019-10-03 08:00","2019-10-04 17:00","매일"]
[388,"광주전남","광주","계림승주#1 T/L","신광주-계림T/L OPGW 증설공사","신광주-계림T/L 광코어 부족 해소를 위한 OPGW 교체(24C→48C)","2019-10-15 08:00","2019-10-15 18:00","취소","취소","당일"]
[389,"광주전남","광주","신광주장성#2 T/L","154kV 인출선로 모선 재배열공사","가. 공사장소 : 신광주S/S 154kV 인출선로 나. 휴전선로 : 154kV 신광주-곡성#1T/L 다. 작업내용 - 인출선로 모선 재배열을 위한 선로 재배열공사 - 선종/길이 : 신광주-곡성#1T/L(XLPE 2000SQ X 1C(D) X 0.07km) 신광주-장성#2T/L(XLPE 2000SQ X 1C(D","2019-10-16 09:00","2019-10-19 18:00","2019-10-16 09:00","2019-10-19 18:00","연속"]
[390,"광주전남","광주","신광주장성#2 T/L","154kV 인출선로 모선 재배열공사","가. 공사장소 : 신광주S/S 154kV 인출선로 나. 휴전선로 : 154kV 신광주-곡성#1T/L 다. 작업내용 - 인출선로 모선 재배열을 위한 선로 재배열공사 - 선종/길이 : 신광주-곡성#1T/L(XLPE 2000SQ X 1C(D) X 0.07km) 신광주-장성#2T/L(XLPE 2000SQ X 1C(D","2019-10-10 09:00","2019-10-10 18:00","2019-10-08 09:00","2019-10-08 18:00","연속"]
[391,"광주전남","광주","신광주계림#1 T/L","신광주-계림T/L OPGW 증설공사","신광주-계림T/L 광코어 부족 해소를 위한 OPGW 교체(24C→48C)","2019-10-14 08:00","2019-10-18 18:00","취소","취소","연속"]
[392,"광주전남","광주","신광주계림#2 T/L","신광주-계림T/L OPGW 증설공사","신광주-계림T/L 광코어 부족 해소를 위한 OPGW 교체(24C→48C)","2019-10-15 08:00","2019-10-15 18:00","취소","취소","당일"]
[393,"광주전남","광주","신광주장성#1 T/L","19년 광주변전총액(장기미동작차단기 점검)","장성S/S 신광주-장성#1T/L 장기미동작차단기 점검","2019-10-11 09:00","2019-10-11 14:00","2019-10-11 09:00","2019-10-11 14:00","당일"]
[394,"광주전남","순천","서순천주암HP T/L","154kV 서순천-주암HPT/L 등 4개선로 자기애관 교체공사","자기애관 교체 : 4개소 대상선로 : 서순천-주암HP, 서순천-승주, 벌교-고흥#1,2","2019-10-23 09:00","2019-10-24 12:00","2019-10-23 09:00","2019-10-24 12:00","연속"]
[395,"광주전남","순천","순천승주#2 T/L","154kV 순천-승주#2 T/L 불량애자교체 및 상간스페이서 설치","18~19년도 순천전력 협력회사 총액공사 - 순천-승주#2 T/L 불량애자교체 : No.2호(1기) - 순천-승주#2 T/L 상간스페이서 설치 : No.109-110호간","2019-10-11 07:00","2019-10-11 18:00","2019-10-11 07:00","2019-10-11 18:00","당일"]
[396,"광주전남","순천","승주서순천 T/L","154kV 서순천-주암HPT/L 등 4개선로 자기애관 교체공사","자기애관 교체 : 4개소 대상선로 : 서순천-주암HP, 서순천-승주, 벌교-고흥#1,2","2019-10-24 13:00","2019-10-25 20:00","2019-10-24 13:00","2019-10-25 20:00","연속"]
[397,"광주전남","순천","계림승주#1 T/L","19년 송전정비회사 총액공사","18~19년도 순천정비회사 총액공사 - 순천-승주#2 T/L 불량애자교체 및 상간스페이서 설치관련 4회선구간 병가선로 안전이격거리확보","2019-10-11 07:00","2019-10-11 18:00","2019-10-11 07:00","2019-10-11 18:00","당일"]
[398,"광주전남","순천","승주주암HP T/L","19년 변전정비회사 총액공사","승주S/S 승주-주암HPT/L 1DS 댐퍼교체","2019-10-23 10:00","2019-10-23 16:00","2019-10-23 10:00","2019-10-23 16:00","당일"]
[399,"광주전남","순천","여수소라#2 T/L","19년 변전정비회사 총액공사","여수S/S : 여수-소라#2T/L GIS 보조계전기 교체, CB타임측정 소라S/S : 여수-소라#2T/L GIS CB 타임측정","2019-10-30 10:00","2019-10-30 18:00","2019-10-27 10:00","2019-10-27 18:00","당일"]
[400,"광주전남","순천","여수소라#1 T/L","19년 변전정비회사 총액공사","여수S/S : 여수-소라#1T/L GIS 보조계전기 교체, CB타임측정 소라S/S : 여수-소라#1T/L GIS CB 타임측정","2019-10-29 10:00","2019-10-29 18:00","2019-10-26 10:00","2019-10-26 18:00","당일"]
[401,"광주전남","순천","여천호남TP#2 T/L","19년 변전정비회사 총액공사(애자련교체)","여천S/S 여천-호남TP#2T/L 불량 현수애자(12련) 교체","2019-10-17 10:00","2019-10-17 18:00","2019-10-17 10:00","2019-10-17 18:00","당일"]
[402,"광주전남","순천","여천호남TP#1 T/L","19년 변전정비회사 총액공사(애자련교체)","여천S/S 여천-호남TP#1T/L 불량 현수애자(5련) 교체","2019-10-16 10:00","2019-10-16 18:00","2019-10-16 10:00","2019-10-16 18:00","당일"]
[403,"광주전남","순천","여천여수#2 T/L","19년 변전정비회사 총액공사(애자련교체)","여천S/S 여천-여수#2T/L 불량 현수애자(6련) 교체","2019-10-15 10:00","2019-10-15 18:00","2019-10-15 10:00","2019-10-15 18:00","당일"]
[404,"광주전남","순천","여천여수#1 T/L","19년 순천 변전협력회사 총액공사","[여천] 여천-여수#1T/L GIS 보통점검 [여수] 여천-여수#1T/L GIS CB 타임측정","2019-10-18 10:00","2019-10-18 18:00","2019-10-18 10:00","2019-10-18 18:00","당일"]
[405,"광주전남","순천","율촌여수산단#1 T/L","19년 순천 변전협력회사 총액공사","[율촌] 율촌-여수산단#1T/L GIS 보통점검","2019-10-04 10:00","2019-10-04 18:00","2019-10-04 10:00","2019-10-04 18:00","당일"]
[406,"광주전남","순천","율촌여수산단#2 T/L","19년 변전정비회사 총액공사","율촌S/S 율촌-여수산단#2T/L GIS 보통점검","2019-10-21 10:00","2019-10-21 18:00","2019-10-21 10:00","2019-10-21 18:00","당일"]
[407,"광주전남","직할","나주평동#2 T/L","154kV 왕곡E/C 인출구간 지중C/H 건설공사","154kV 나주-평동T/L No.19 - 20호간 선하지 C/H 2기 신설 - C/H(관형지지물) 2기 신설(No.19-1, 19-2) - 전력선 연,긴선 250m - C/H 인하선 연결","2019-10-25 09:00","2019-10-29 18:00","2019-10-25 09:00","2019-10-29 18:00","연속"]
[408,"광주전남","직할","나주평동#1 T/L","154kV 왕곡E/C 인출구간 지중C/H 건설공사","154kV 나주-평동T/L No.19 - 20호간 선하지 C/H 2기 신설 - C/H(관형지지물) 2기 신설(No.19-1, 19-2) - 전력선 연,긴선 250m - C/H 인하선 연결","2019-10-25 09:00","2019-10-29 18:00","2019-10-25 09:00","2019-10-29 18:00","연속"]
[409,"광주전남","직할","하남장성#1 T/L","2019년도 직할 가공송전선로 순시점검 위탁공사","○ 154kV 하남-장성#1T/L 정밀점검 - 하남S/S ~ 장성S/S, 37기","2019-10-21 08:00","2019-10-25 18:00","2019-10-21 08:00","2019-10-25 18:00","매일"]
[410,"광주전남","직할","하남장성#2 T/L","2019년도 직할 가공송전선로 순시점검 위탁공사","○ 154kV 하남-장성#2T/L 정밀점검 - 하남S/S ~ 장성S/S, 37기","2019-10-28 08:00","2019-11-01 18:00","취소","취소","매일"]
[411,"대구","경산","범물남대구#2 T/L","2018~19년 경산변전협력 총액공사","-장기미동작타임측정","2019-10-24 11:00","2019-10-24 14:00","2019-10-24 11:00","2019-10-24 14:00","당일"]
[412,"대구","경산","범물남대구#1 T/L","2018~19년 경산변전협력 총액공사","-장기미동작타임측정","2019-10-24 09:30","2019-10-24 11:00","2019-10-24 09:30","2019-10-24 11:00","당일"]
[413,"대구","경산","안심대구그린파워#2 T/L","2018~19년 경산변전협력 총액공사","-모선보호반교체공사","2019-10-17 16:00","2019-10-17 16:30","2019-10-17 16:00","2019-10-17 16:30","당일"]
[414,"대구","경산","안심대구그린파워#1 T/L","2018~19년 경산변전협력 총액공사","-모선보호반교체공사","2019-10-17 15:00","2019-10-17 16:00","2019-10-17 15:00","2019-10-17 16:00","당일"]
[415,"대구","달성","강창성서#2 T/L","강창S/S 강창성서2T/L 차단기동작특성시험","강창S/S 강창성서2T/L 차단기동작특성시험","2019-10-30 13:00","2019-10-30 18:00","2019-10-30 13:00","2019-10-30 18:00","당일"]
[416,"대구","달성","강창성서#1 T/L","강창S/S 강창성서1T/L 차단기동작특성시험","강창S/S 강창성서1T/L 차단기동작특성시험","2019-10-30 09:00","2019-10-30 13:00","2019-10-30 09:00","2019-10-30 13:00","당일"]
[417,"대구","달성","고령쌍림#2 T/L","고령S/S 154kV 고령-서구지T/L S/W 증설공사","고령S/S 154kV 고령-서구지T/L S/W 증설공사","2019-10-24 18:00","2019-10-25 18:00","2019-10-27 12:00","2019-10-28 12:00","연속"]
[418,"대구","달성","고령쌍림#2 T/L","고령S/S 154kV 고령-서구지T/L S/W 증설공사","고령S/S 154kV 고령-서구지T/L S/W 증설공사","2019-10-23 15:00","2019-10-24 15:00","2019-10-26 09:00","2019-10-27 09:00","연속"]
[419,"대구","달성","고령쌍림#2 T/L","고령S/S 154kV 고령-서구지T/L S/W 증설공사","고령S/S 154kV 고령-서구지T/L S/W 증설공사","2019-10-17 15:00","2019-10-18 15:00","2019-10-19 15:00","2019-10-20 15:00","연속"]
[420,"대구","달성","성서달성#1 T/L","달성,성서S/S 성서달성#1T/L 차단기동작특성시험","달성,성서S/S 성서달성#1T/L 차단기동작특성시험","2019-10-18 09:00","2019-10-18 13:00","2019-10-18 09:00","2019-10-18 13:00","당일"]
[421,"대구","달성","성서달성#2 T/L","달성,성서S/S 성서달성#2T/L 차단기동작특성시험","달성,성서S/S 성서달성#2T/L 차단기동작특성시험","2019-10-18 13:00","2019-10-18 18:00","2019-10-18 13:00","2019-10-18 18:00","당일"]
[422,"대구","달성","대구봉덕#1 T/L","EBA 절연유 채취","대구봉덕 C/H EBA 절연유 채취","2019-10-17 09:30","2019-10-17 18:00","2019-10-17 09:30","2019-10-17 18:00","당일"]
[423,"대구","달성","두류봉덕#1 T/L","봉덕S/S 두류봉덕1T/L 차단기동작특성시험","봉덕S/S 두류봉덕1T/L 차단기동작특성시험","2019-10-25 09:00","2019-10-25 13:00","2019-10-25 09:00","2019-10-25 13:00","당일"]
[424,"대구","달성","두류봉덕#2 T/L","봉덕S/S 두류봉덕2T/L 차단기동작특성시험","봉덕S/S 두류봉덕2T/L 차단기동작특성시험","2019-10-25 13:00","2019-10-25 18:00","2019-10-25 13:00","2019-10-25 18:00","당일"]
[425,"대구","달성","쌍림합천#2 T/L","쌍림S/S 쌍림합천#2 보호반대체작업","쌍림S/S 쌍림합천#2 보호반대체작업","2019-10-16 09:00","2019-10-17 18:00","2019-10-19 09:00","2019-10-20 18:00","연속"]
[426,"대구","달성","쌍림합천#1 T/L","쌍림S/S 쌍림합천1T/L 차단기동작특성시험","쌍림S/S 쌍림합천1T/L 차단기동작특성시험","2019-10-25 09:00","2019-10-25 18:00","2019-10-03 09:00","2019-10-03 18:00","당일"]
[427,"대구","포항","건천천북#1 T/L","154kV 건천-천북#1T/L SB댐퍼 설치공사","154kV 건천-천북#1T/L SB댐퍼 설치공사 - No.84,85,86,87,88(5기)","2019-10-14 08:00","2019-10-15 18:00","2019-10-14 08:00","2019-10-15 18:00","연속"]
[428,"경북","구미","남인동인동#1 T/L","19년 구미전력지사 변전정비업체 총액공사","- GIS 보통점검","2019-10-04 09:00","2019-10-04 14:00","2019-10-04 09:00","2019-10-04 14:00","당일"]
[429,"경북","구미","남인동인동#2 T/L","19년 구미전력지사 변전정비업체 총액공사","- GIS 보통점검","2019-10-04 14:00","2019-10-04 18:00","2019-10-04 14:00","2019-10-04 18:00","당일"]
[430,"경북","직할","안동동안동#2 T/L","18~19년 경북본부 직할 변전정비회사 총액공사","652DS 내부소음관련 점검","2019-10-14 09:00","2019-10-15 18:00","2019-10-14 09:00","2019-10-15 18:00","연속"]
[431,"경북","직할","봉화울진 T/L","18~19년 경북본부 직할 변전정비회사 총액공사","보통점검","2019-10-02 09:00","2019-10-02 17:00","2019-10-02 09:00","2019-10-02 17:00","당일"]
[432,"경북","직할","울진현종산풍력 T/L","18~19년 경북본부 직할 변전정비회사 총액공사","초기점검","2019-10-21 09:00","2019-10-21 18:00","2019-10-21 09:00","2019-10-21 18:00","당일"]
[433,"부산울산","동부산","구서명장#2 T/L","2018-2019년 동부산전력지사 송전정비 협력회사","안전이격거리확보(154kV 신양산-구서#2T/L 휴전관련)","2019-10-16 08:00","2019-10-17 18:00","2019-10-16 08:00","2019-10-17 18:00","연속"]
[434,"부산울산","동부산","신울산명례#2 T/L","명례E/C 170kV GIS 차단기 동작시험","명례E/C 170kV 627GIS 차단기 동작시험(신울산-명례#2T/L)","2019-10-10 14:00","2019-10-10 18:00","2019-10-10 14:00","2019-10-10 18:00","당일"]
[435,"부산울산","동부산","신울산명례#1 T/L","명례E/C 170kV GIS 차단기 동작시험","명례E/C 170kV 617GIS 차단기 동작시험(신울산-명례#1T/L)","2019-10-10 09:30","2019-10-10 14:00","2019-10-10 09:30","2019-10-10 14:00","당일"]
[436,"부산울산","동부산","명례정관 T/L","명례E/C 170kV GIS 차단기 동작시험","1.명례E/C 170kV 647GIS 차단기 동작시험(명례-정관T/L) 2. 정관E/C 667GIS 차단기 동작시험","2019-10-08 09:30","2019-10-08 18:00","2019-10-08 09:30","2019-10-08 18:00","당일"]
[437,"부산울산","동부산","명례고리NP T/L","명례E/C 170kV GIS 차단기 동작시험","명례E/C 170kV 637GIS 차단기 동작시험(명례-고리T/L)","2019-10-11 09:30","2019-10-11 14:00","2019-10-11 09:30","2019-10-11 14:00","당일"]
[438,"부산울산","동부산","웅촌서창#1 T/L","서창E/C 170kV GIS 보통점검","서창E/C 170kV 647GIS 보통점검(웅촌-서창#1T/L)","2019-10-10 09:30","2019-10-10 18:00","2019-10-10 09:30","2019-10-10 18:00","당일"]
[439,"부산울산","동부산","정보대연 T/L","154kV 정보-대연T/L OF케이블 보수작업","154kV 정보-대연T/L OF케이블 보수작업","2019-10-28 09:00","2019-10-31 18:00","2019-10-28 09:00","2019-10-31 18:00","연속"]
[440,"부산울산","북부산","김해어방#2 T/L","2019 북부산전력지사 가공순시점검위탁공사","154kV 김해-어방#1T/L 정밀점검 관련 작업자 안전확보","2019-10-05 09:00","2019-10-05 14:00","2019-10-12 09:00","2019-10-12 14:00","당일"]
[441,"부산울산","북부산","김해어방#1 T/L","2019 북부산전력지사 가공순시점검위탁공사","154kV 김해-어방#1T/L 정밀점검(1~3호) 3기","2019-10-05 09:00","2019-10-05 14:00","2019-10-12 09:00","2019-10-12 14:00","당일"]
[442,"부산울산","북부산","김해어방#1 T/L","2019 북부산전력지사 가공순시점검위탁공사","154kV 김해-어방#2T/L 정밀점검 관련 작업자 안전확보","2019-10-05 14:00","2019-10-05 18:00","2019-10-12 14:00","2019-10-12 18:00","당일"]
[443,"부산울산","북부산","김해어방#2 T/L","2019 북부산전력지사 가공순시점검위탁공사","154kV 김해-어방#2T/L 정밀점검(1~3호) 3기","2019-10-05 14:00","2019-10-05 18:00","2019-10-12 14:00","2019-10-12 18:00","당일"]
[444,"부산울산","북부산","북부산물금 T/L","2019년 북부산 154kV GIS 정밀점검 공사","물금E/C 154kV Bus-Tie GIS 정밀점검(1DS,CB 시험가압1h)","2019-10-19 12:00","2019-10-19 13:00","2019-10-19 12:00","2019-10-19 13:00","당일"]
[445,"부산울산","북부산","북부산물금 T/L","2019년 북부산 154kV GIS 정밀점검 공사","물금E/C 154kV Bus-Tie GIS 정밀점검(2DS부 시험가압1h)","2019-10-20 17:00","2019-10-20 18:00","2019-10-20 17:00","2019-10-20 18:00","당일"]
[446,"부산울산","북부산","북부산물금 T/L","2019년 북부산 154kV GIS 정밀점검 공사","물금E/C 154kV #2M.Tr 1차 GIS 정밀점검(1DS,CB,상부부스 시험가압1h)","2019-10-10 12:00","2019-10-10 13:00","2019-10-10 12:00","2019-10-10 13:00","당일"]
[447,"부산울산","북부산","북부산물금 T/L","2019년 북부산 154kV GIS 정밀점검 공사","물금E/C 154kV #2M.Tr 1차 GIS 정밀점검(2DS부 시험가압1h)","2019-10-11 17:00","2019-10-11 18:00","2019-10-11 17:00","2019-10-11 18:00","당일"]
[448,"부산울산","북부산","북부산물금 T/L","2019년 북부산 154kV GIS 정밀점검 공사","물금E/C 154kV #1M.Tr 1차 GIS 정밀점검(1DS,CB,상부부스 시험가압1h)","2019-10-16 12:00","2019-10-16 13:00","2019-10-16 12:00","2019-10-16 13:00","당일"]
[449,"부산울산","북부산","북부산물금 T/L","2019년 북부산 154kV GIS 정밀점검 공사","물금E/C 154kV #1M.Tr 1차 GIS 정밀점검(2DS부 시험가압1h)","2019-10-17 17:00","2019-10-17 18:00","2019-10-17 17:00","2019-10-17 18:00","당일"]
[450,"부산울산","북부산","물금S/S 154kV #60 BUS","물금E/C 154kV GIS 모선분리공사","물금E/C 154kV #60BUS GIB철거 및 60-61Bus-section 설치","2019-10-22 09:00","2019-10-31 15:00","2019-10-22 09:00","2019-10-31 15:00","연속"]
[451,"부산울산","북부산","북부산물금 T/L","물금E/C 154kV GIS 모선분리공사","물금E/C 154kV GIS 모선분리공사(시험가압 24h)","2019-10-30 15:00","2019-10-31 15:00","2019-10-30 15:00","2019-10-31 15:00","연속"]
[452,"부산울산","북부산","물금S/S 154kV #65 BUS","물금E/C 154kV GIS 모선분리공사","물금E/C 154kV #65BUS GIB철거 및 65-66Bus-section 설치","2019-10-31 15:00","2019-11-10 15:00","2019-10-31 15:00","2019-11-10 15:00","연속"]
[453,"부산울산","북부산","북부산S/S 154kV #66-#67 SEC CB","2019년 북부산 변전협력회사 총액공사","북부산E/C 154kV 66-67-0 GIS 차단기조작시험","2019-10-15 14:00","2019-10-15 16:00","2019-10-15 14:00","2019-10-15 16:00","당일"]
[454,"부산울산","북부산","북부산S/S 154kV #61-#62 SEC CB","2019년 북부산 변전협력회사 총액공사","북부산E/C 154kV 61-62-0 GIS 차단기조작시험","2019-10-15 12:00","2019-10-15 14:00","2019-10-15 12:00","2019-10-15 14:00","당일"]
[455,"부산울산","북부산","북부산S/S 154kV #65-#66 SEC CB","2019년 북부산 변전협력회사 총액공사","북부산E/C 154kV 65-66-0 GIS 차단기조작시험","2019-10-15 10:00","2019-10-15 12:00","2019-10-15 10:00","2019-10-15 12:00","당일"]
[456,"부산울산","북부산","서창산막#1 T/L","2019년 북부산 변전협력회사 총액공사","산막E/C 154kV서창-산막#1T/L GIS 차단기 조작시험","2019-10-13 10:00","2019-10-13 14:00","취소","취소","당일"]
[457,"부산울산","북부산","서창산막#2 T/L","2019년 북부산 변전협력회사 총액공사","산막E/C 154kV서창-산막#2T/L GIS 차단기 조작시험","2019-10-13 14:00","2019-10-13 18:00","취소","취소","당일"]
[458,"부산울산","북부산","양산산막#1 T/L","양산S/S 현대화공사","154kV 양산-산막#2T/L 시험가압 선로","2019-10-01 10:00","2019-10-02 10:00","2019-10-01 10:00","2019-10-02 10:00","연속"]
[459,"부산울산","북부산","양산산막#2 T/L","양산S/S 현대화공사","154kV 양산(SA)-산막#2T/L 시험가압 (24H)","2019-10-01 10:00","2019-10-02 10:00","2019-10-01 10:00","2019-10-02 10:00","연속"]
[460,"부산울산","북부산","양산산막#1 T/L","양산S/S 현대화공사","154kV #1Sh.C 시험가압 선로","2019-10-31 10:00","2019-11-01 10:00","2019-10-31 10:00","2019-11-01 10:00","연속"]
[461,"부산울산","서부산","서부산다대#2 T/L","154kV 서부산-다대T/L 지장이설 및 선종교체공사","선로명 : 154kV 서부산-다대T/L 구 간 : J/B#2 ~ J/B#5 (1.09km) 작업내용 : 을숙도대교-장림고개간 지하차도건설공사에 따른 지장이설 및 케이블 선종교체","2019-10-02 09:00","2019-12-20 18:00","2019-10-02 09:00","2019-12-20 18:00","연속"]
[462,"부산울산","서부산","신녹산용원#2 T/L","일진전기 R-Type 조립식접속함 교체작업","○ 작업 내용 : 일진제 R-Type PMJ 교체 ○ 교체 수량 : 3상 1개소","2019-10-21 09:00","2019-10-27 18:00","2019-10-21 09:00","2019-10-27 18:00","연속"]
[463,"부산울산","서부산","신녹산용원#1 T/L","일진전기 R-Type 조립식접속함 교체작업","○ 작업 내용 : 일진제 R-Type PMJ 교체 ○ 교체 수량 : 3상 1개소","2019-10-14 09:00","2019-10-20 18:00","2019-10-14 09:00","2019-10-20 18:00","연속"]
[464,"부산울산","울산","성암S/S 154kV #61 BUS","성암E/C 154kV S.W 증설공사","성암E/C 170kV GIS*5Bay 신규설치 - 남울산-성암#1,2T/L - 성암-울산T/P#1,2T/L -SK에너지No2FCC#1T/L(신규수용)","2019-10-07 09:00","2019-10-18 18:00","2019-10-07 09:00","2019-10-18 18:00","연속"]
[465,"부산울산","울산","신온산온산#3 T/L","신온산E/C 154kV #1Sh.C 6179GIS 가스누기보수작업","- 신온산E/C 154kV #1Sh.C MAIN 6179GIS #1,2DS 가스누기관련 인접BAY 휴전 및 시험가압 1H(단로기 별 1시간 요망)","2019-10-21 09:00","2019-10-24 18:00","2019-10-21 09:00","2019-10-24 18:00","연속"]
[466,"부산울산","울산","신울산S/S 154kV #66-#67 SEC CB","18~19년 변전협력 총액공사","- 154kV #66-67BUS SEC CB AUX 접점뭉치 불량교체","2019-10-11 13:00","2019-10-11 18:00","2019-10-11 13:00","2019-10-11 18:00","당일"]
[467,"부산울산","울산","신울산S/S 154kV #61-#62 SEC CB","18~19년 변전협력 총액공사","- 154kV #61-62BUS SEC CB AUX 접점뭉치 불량교체","2019-10-11 09:00","2019-10-11 13:00","취소","취소","당일"]
[468,"부산울산","울산","신울산두왕#2 T/L","송전선로 철탑 주간표지 항공도장 공사(안전이격확보)","□ 공사내용 : 154kV 신울산-울산 T/L 철탑(No.3) 항공도장 안전이격확보 □ 공사기간 : 2019.10.21 ~ 2019.10.22 ※ 양회선 휴전불가시, 1회선 휴전 시행","2019-10-22 08:00","2019-10-22 12:00","2019-10-22 08:00","2019-10-22 12:00","매일"]
[469,"부산울산","울산","신울산두왕#2 T/L","2019년도 가공송전 순시점검 위탁공사","1) 정밀점검 ○ 154kV 신울산-두왕#2T/L No.2~6(5기) ○ 병가선로 휴전 - 공사명 : 154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사 - 휴전설비 : 154kV 신울산-울산#2T/L (10/25~29)","2019-10-25 08:00","2019-10-25 18:00","2019-10-25 08:00","2019-10-25 18:00","당일"]
[470,"부산울산","울산","신울산두왕#1 T/L","송전선로 철탑 주간표지 항공도장 공사(안전이격확보)","□ 공사내용 : 154kV 신울산-울산 T/L 철탑(No.3) 항공도장 안전이격확보 □ 공사기간 : 2019.10.21 ~ 2019.10.22 ※ 양회선 휴전불가시, 1회선 휴전 시행","2019-10-21 08:00","2019-10-21 12:00","2019-10-21 08:00","2019-10-21 12:00","당일"]
[471,"부산울산","울산","영남T/P 154kV #60-#65 BUS TIE CB","18~19년 변전협력 총액공사","- 영남화력 154kV #1BUS TIE GIS 보통점검","2019-10-04 09:00","2019-10-04 18:00","2019-10-04 09:00","2019-10-04 18:00","당일"]
[472,"부산울산","울산","용연울산TP#1 T/L","2019년 울산전력지사 170kV 장기사용GIS 대체공사","- 154kV 롯데케미칼T/L #1DS, CB철거 후 #1BUS 시험가압 24H","2019-10-31 17:00","2019-11-01 17:00","2019-10-31 17:00","2019-11-01 17:00","연속"]
[473,"부산울산","울산","용연울산TP#3 T/L","2019년 울산화력 170kV 장기사용GIS 대체공사","- 용연S/S 154kV 롯데케미칼T/L #2BUS 철거관련 시험가압 1H","2019-10-28 17:00","2019-10-28 18:00","2019-10-28 17:00","2019-10-28 18:00","당일"]
[474,"부산울산","울산","용연울산TP#3 T/L","345kV 신울산복합-북부산T/L 건설사업","○ 공사목적 : 345kV 신울산복합-북부산T/L 울산화력ST~No.12 가선공사 - 공사내용 : 345kV 신울산복합-북부산T/L 울산화력ST~No.9 연선 및No.3,4,5 긴선","2019-10-29 09:00","2019-10-30 18:00","2019-10-29 09:00","2019-10-30 18:00","연속"]
[475,"부산울산","울산","용연울산TP#1 T/L","345kV 신울산복합-북부산T/L 건설사업","○ 공사목적 : 345kV 신울산복합-북부산T/L 울산화력ST~No.12 가선공사 - 용연-울산TP T/L 및 SK에너지 선로 횡단구간 발받침철탑 설치 및 보호망 설치","2019-10-25 09:00","2019-10-25 18:00","취소","취소","연속"]
[476,"부산울산","울산","용연울산TP#3 T/L","2019년 170kV GIS 하반기 정밀점검공사","- 울산화력 154kV #4,5,6ST-UP TR #2 (677)GIS CB,#1DS, 상부모선 정밀점검 후 시험가압(1H)","2019-10-18 17:00","2019-10-18 18:00","2019-10-18 17:00","2019-10-18 18:00","당일"]
[477,"부산울산","울산","용연울산TP#2 T/L","2019년 170kV GIS 하반기 정밀점검공사","- 울산화력 154kV #4,5,6ST-UP TR #2 (677)GIS #2DS 정밀점검 후 시험가압(1H)","2019-10-14 17:00","2019-10-14 18:00","2019-10-14 17:00","2019-10-14 18:00","당일"]
[478,"부산울산","울산","울산T/P 154kV #66 BUS","2019년 170kV GIS 하반기 정밀점검공사","- 울산화력 154kV #4,5,6ST-UP TR #2 (677)GIS #2DS 정밀점검 및 시험가압(1H)","2019-10-14 09:00","2019-10-14 18:00","2019-10-14 09:00","2019-10-14 18:00","당일"]
[479,"부산울산","울산","울산T/P 154kV #65 BUS","2019년 울산화력 170kV 장기사용GIS 대체공사","- 154kV #1S/T GIS #2BUS 철거 및 #2BUS, CB, 상부모선 설치","2019-10-07 09:00","2019-10-12 18:00","2019-10-07 09:00","2019-10-12 18:00","연속"]
[480,"부산울산","울산","용연울산TP#2 T/L","345kV 신울산복합-북부산T/L 건설사업","○ 공사목적 : 345kV 신울산복합-북부산T/L 울산화력ST~No.12 가선공사 - 용연-울산TP T/L 및 SK에너지 선로 횡단구간 발받침철탑 설치 및 보호망 설치","2019-10-25 09:00","2019-10-25 18:00","취소","취소","연속"]
[481,"부산울산","울산","울산울산TP#1 T/L","154kV 울산-영남T/P 전력구공사","터널 483M 관로 1,576M","2019-10-24 09:00","2019-10-29 18:00","취소","취소","매일"]
[482,"부산울산","울산","울산울산TP#2 T/L","345kV 신울산복합-북부산T/L 건설사업","○ 공사목적 : 154kV 울산-울산TP T/L 임시선로 구성 (345kV 신울산복합-북부산T/L 건설관련)","2019-10-22 09:00","2019-10-23 18:00","2019-10-23 07:00","2019-10-24 18:00","연속"]
[483,"부산울산","울산","울산울산TP#1 T/L","345kV 신울산복합-북부산T/L 건설사업","○ 공사목적 : 154kV 울산-울산TP T/L 임시선로 구성 (345kV 신울산복합-북부산T/L 건설관련)","2019-10-18 09:00","2019-10-21 18:00","2019-10-19 09:00","2019-10-22 18:00","연속"]
[484,"부산울산","울산","울산울산TP#2 T/L","345kV 신울산복합-북부산T/L 건설공사","○ 공사목적 : 154kV 울산-울산TP T/L 임시선로 구성 (345kV 신울산복합-북부산T/L 건설관련)","2019-10-14 09:00","2019-10-17 18:00","2019-10-15 07:00","2019-10-17 18:00","연속"]
[485,"부산울산","울산","울산T/P 154kV 4,5,6 SU TR #2 1차 CB","2019년 울산전력지사 170kV 하반기 정밀점검공사","- 울산화력 154kV 4,5,6 SU TR #2 1차 차단기 정밀점검","2019-10-14 09:00","2019-10-18 18:00","2019-10-14 09:00","2019-10-18 18:00","연속"]
[486,"부산울산","울산","울산T/P 154kV #60 BUS","2019년 울산화력 170kV 장기사용GIS 대체공사","- 154kV #1S/T 6533GIS #1DS 투입 후 시험가압 1H","2019-10-12 17:00","2019-10-12 18:00","2019-10-12 17:00","2019-10-12 18:00","당일"]
[487,"부산울산","울산","울산울산TP#1 T/L","2019년 울산화력 170kV 장기사용GIS 대체공사","- 154kV #1S/T 6533GIS #2BUS, #2DS, CB, 상부모선 시험가압 24H","2019-10-11 17:00","2019-10-12 17:00","2019-10-11 17:00","2019-10-12 17:00","연속"]
[488,"부산울산","울산","울산T/P 154kV 4,5,6 SU TR #1 1차 CB","2019년 울산전력지사 170kV 하반기 정밀점검공사","- 울산화력 154kV 4,5,6 SU TR #1 1차 차단기 정밀점검","2019-10-07 09:00","2019-10-11 18:00","2019-10-07 09:00","2019-10-11 18:00","연속"]
[489,"부산울산","울산","울산울산TP#2 T/L","154kV 울산-영남T/P 전력구공사","터널 483M 관로 1,576M","2019-10-30 09:00","2019-11-08 18:00","2019-10-13 09:00","2019-10-13 18:00","매일"]
[490,"부산울산","울산","울산울산TP#1 T/L","2019년 울산화력 170kV 장기사용GIS 대체공사","- 154kV #1S/T 6433 GIS 철거관련 #1BUS 시험가압24H","2019-10-03 17:00","2019-10-04 17:00","2019-10-03 17:00","2019-10-04 17:00","연속"]
[491,"부산울산","울산","울산T/P 154kV #61 BUS","2019년 170kV GIS 하반기 정밀점검공사","- 울산화력 154kV #4,5,6ST-UP TR #2 (677)GIS #1DS 정밀점검 및 시험가압(1H)","2019-10-15 09:00","2019-10-18 18:00","2019-10-15 09:00","2019-10-18 18:00","연속"]
[492,"부산울산","울산","울주외동#2 T/L","송전선로 철탑 주간표지 항공도장 공사","□ 공사내용 : 154kV 울주-외동 T/L 철탑(No.15) 항공도장 □ 공사기간 : 2019.10.28~ 2019.10.29 ※ 양회선 휴전불가시, 1회선 휴전 시행","2019-10-29 08:00","2019-10-29 18:00","2019-10-29 08:00","2019-10-29 18:00","당일"]
[493,"부산울산","울산","울주외동#1 T/L","송전선로 철탑 주간표지 항공도장 공사","□ 공사내용 : 154kV 울주-외동 T/L 철탑(No.15) 항공도장 □ 공사기간 : 2019.10.28 ~ 2019.10.29 ※ 양회선 휴전불가시, 1회선 휴전 시행","2019-10-28 08:00","2019-10-28 18:00","2019-10-28 08:00","2019-10-28 18:00","당일"]
[494,"부산울산","울산","웅촌서창#2 T/L","19년 가공송전 순시점검 위탁공사(동부산)","초기점검 ㅇ 점검대상 : 9,10,11호","2019-10-22 09:00","2019-10-22 18:00","2019-10-22 09:00","2019-10-22 18:00","당일"]
[495,"경남","직할","신김해진영#2 T/L","신김해S/S 신김해-진영#2T/L CB 조작시험 점검","신김해S/S 신김해-진영#2T/L CB 조작시험 점검","2019-10-16 09:30","2019-10-16 17:30","2019-10-16 09:30","2019-10-16 17:30","당일"]
[496,"경남","직할","신월삼정#2 T/L","154kV 신월-삼정#2T/L 지중송전선로용 피뢰기 점검","154kV 신월-삼정#2T/L 지중송전선로용 피뢰기 점검(열화진단)","2019-10-10 09:30","2019-10-10 17:00","2019-10-10 09:30","2019-10-10 17:00","당일"]
[497,"경남","직할","안민천선#2 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-10-01 07:00","2019-10-02 18:00","취소","취소","연속"]
[498,"경남","직할","완암안민#1 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-10-01 07:00","2019-10-02 18:00","취소","취소","연속"]
[499,"경남","직할","완암안민#2 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-10-05 07:00","2019-10-09 18:00","2019-10-09 07:00","2019-10-09 18:00","연속"]
[500,"경남","직할","창원완암#1 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-10-05 07:00","2019-10-07 18:00","2019-10-09 07:00","2019-10-09 18:00","연속"]
[501,"경남","직할","완암안민#1 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-10-05 07:00","2019-10-07 18:00","취소","취소","연속"]
[502,"경남","직할","창원완암#2 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-10-08 07:00","2019-10-09 18:00","2019-10-09 07:00","2019-10-09 18:00","연속"]
[503,"경남","직할","주촌삼계#1 T/L","154kV 주촌E/C #4M.Tr 증설공사","주촌E/C #4M.Tr 증설관련 #60 BUS 시험가압 선로","2019-10-08 17:00","2019-10-09 17:00","2019-10-08 17:00","2019-10-09 17:00","연속"]
[504,"경남","직할","주촌삼계#2 T/L","154kV 주촌E/C #4M.Tr 증설공사","주촌E/C #4M.Tr 증설관련 #65 BUS 시험가압 선로","2019-10-15 17:00","2019-10-16 17:00","2019-10-15 17:00","2019-10-16 17:00","연속"]
[505,"경남","직할","신마산차룡#1 T/L","차룡S/S 신마산-차룡 #1T/L CB 조작시험 점검","차룡S/S 신마산-차룡 #1T/L CB 조작시험 점검","2019-10-23 09:30","2019-10-23 17:30","2019-10-23 09:30","2019-10-23 17:30","당일"]
[506,"경남","직할","신마산차룡#2 T/L","차룡S/S 신마산-차룡 #2T/L CB 조작시험 점검","차룡S/S 신마산-차룡 #2T/L CB 조작시험 점검","2019-10-24 09:30","2019-10-24 17:30","2019-10-24 09:30","2019-10-24 17:30","당일"]
[507,"경남","진주","의령동진주#1 T/L","154kV 의령-동진주#1T/L EBA 절연유 분석","154kV 의령-동진주#1T/L 기중종단접속함(EBA) 절연유 분석을 위한 채유작업","2019-10-05 08:30","2019-10-05 18:30","2019-10-05 08:30","2019-10-05 18:30","당일"]
[508,"경남","진주","의령동진주#2 T/L","154kV 의령-동진주#2T/L EBA 절연유 분석","154kV 의령-동진주#2T/L 기중종단접속함(EBA) 절연유 분석을 위한 채유작업","2019-10-06 08:30","2019-10-06 18:30","2019-10-06 08:30","2019-10-06 18:30","당일"]
[509,"경남","진주","동진주진주#2 T/L","154kV 동진주-진주#2T/L EBA 절연유 분석","154kV 동진주-진주#2T/L 기중종단접속함(EBA) 절연유 분석을 위한 채유작업","2019-10-12 08:30","2019-10-12 18:30","2019-10-12 08:30","2019-10-12 18:30","당일"]
[510,"경남","진주","진주개양#1 T/L","154kV 진주-개양#1T/L EBA 절연유 분석","154kV 진주-개양#1T/L 기중종단접속함(EBA) 절연유 분석을 위한 채유작업","2019-10-07 08:00","2019-10-07 19:00","2019-10-05 08:00","2019-10-05 19:00","당일"]
[511,"경남","진주","진주개양#2 T/L","154kV 진주-개양#2T/L EBA 절연유 분석","154kV 진주-개양#2T/L 기중종단접속함(EBA) 절연유 분석을 위한 채유작업","2019-10-08 08:00","2019-10-08 19:00","2019-10-06 08:00","2019-10-06 19:00","당일"]
[512,"경남","진주","동진주진주#1 T/L","154kV 동진주-진주#1T/L EBA 절연유 분석","154kV 동진주-진주#1T/L 기중종단접속함(EBA) 절연유 분석을 위한 채유작업","2019-10-09 08:30","2019-10-09 18:30","2019-10-09 08:30","2019-10-09 18:30","당일"]
[513,"경남","통영","신고성거제#1 T/L","거제,신고성S/S 신고성-거제#1T/L 송전선로 PNL 대체공사","거제,신고성S/S 신고성-거제#1T/L 송전선로 PNL 대체공사","2019-10-12 09:30","2019-10-13 18:00","2019-10-12 09:30","2019-10-13 18:00","연속"]
[514,"경남","통영","신고성거제#2 T/L","154kV 신고성-거제#2T/L 정밀점검","154kV 신고성-거제#2T/L 정밀점검","2019-10-05 09:00","2019-10-06 18:00","2019-10-05 09:00","2019-10-06 18:00","매일"]
[515,"경남","통영","신고성S/S 154kV 신고성-삼천포#1T/L CB","신고성S/S 154kV 신고성-삼천포#1T/L 조작시험","신고성S/S 154kV 신고성-삼천포#1T/L 조작시험","2019-10-23 09:30","2019-10-23 11:30","2019-10-23 09:30","2019-10-23 11:30","당일"]
[516,"경남","통영","신고성S/S 154kV 신고성-삼천포#2T/L CB","신고성S/S 154kV 신고성-삼천포#2T/L 개폐장치 조작시험","신고성S/S 154kV 신고성-삼천포#2T/L 개폐장치 조작시험","2019-10-23 13:00","2019-10-23 18:00","2019-10-23 13:00","2019-10-23 18:00","당일"]
[517,"경남","통영","진동S/S 154kV #65 BUS","진동S/S 170kV 모선보강공사","170kV GIS 4CCT(B/T,B/S*2,PT&ES) 증설공사","2019-10-14 09:00","2019-10-25 18:00","2019-10-14 09:00","2019-10-25 18:00","연속"]
[518,"경남","통영","통영거제#2 T/L","154kV 통영-거제#2T/L 암정판 볼트교체","154kV 통영-거제#2T/L 27, 43호 암정판 볼트교체(볼트 노후화 및 규격상이)","2019-10-26 09:00","2019-10-27 18:00","2019-10-26 09:00","2019-10-27 18:00","매일"]
[519,"경남","통영","신고성통영 T/L","154kV 신고성-통영T/L 정밀점검","154kV 신고성-통영T/L 송전선로 정밀점검","2019-10-19 09:00","2019-10-20 18:00","2019-10-19 09:00","2019-10-20 18:00","매일"]
[520,"남서울","동서울","신장덕소#1T/L","신장S/S 신장-덕소#1T/L GIS 하자점검","신장S/S 신장-덕소#1T/L GIS 하자점검 - 케이블헤드 외관 변형으로 내부점검","2019-10-01 09:00","2019-10-02 18:00","2019-10-01 09:00","2019-10-02 18:00","연속"]
[521,"남서울","동서울","잠실강남#1T/L","차단기 보통점검 및 하자점검","잠실 : 보통점검 강남 : 하자점검","2019-10-17 10:00","2019-10-17 18:00","2019-10-17 10:00","2019-10-17 18:00","당일"]
[522,"남서울","동서울","잠실강남#2T/L","차단기 보통점검 및 하자점검","잠실 : 보통점검 강남 : 하자점검","2019-10-18 10:00","2019-10-18 18:00","2019-10-18 10:00","2019-10-18 18:00","당일"]
[523,"남서울","동서울","강남선릉#1T/L","차단기 보통점검 및 하자점검","강남 : 차단기 하자점검 선릉 : 차단기 조작시험","2019-10-30 10:00","2019-10-30 18:00","2019-10-30 10:00","2019-10-30 18:00","당일"]
[524,"남서울","동서울","강남선릉#2T/L","차단기 보통점검 및 하자점검","강남 : 차단기 하자점검 선릉 : 차단기 조작시험","2019-10-31 10:00","2019-10-31 18:00","2019-10-31 10:00","2019-10-31 18:00","당일"]
[525,"대전충남","서산","신당진S/S 154kV\n60-61-0 SEC CB","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험 -신당진S/S 60-61-0 SEC CB","2019-10-15 10:00","2019-10-15 14:00","2019-10-15 10:00","2019-10-15 14:00","당일"]
[526,"대전충남","서산","신당진S/S 154kV\n65-66-0 SEC CB","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험 -신당진S/S 65-66-0 SEC CB","2019-10-16 10:00","2019-10-16 14:00","2019-10-16 10:00","2019-10-16 14:00","당일"]