{"text_format":"2","workbook":"xlsx","n_sheets":5,"sheets":["종합","765송부","345송부","154송부","시송전설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":16,"comments":2,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"종합","index":0,"n_rows":37,"n_cols":33,"rows_kept":37,"cut":false,"hidden":true,"merged":[[0,0,0,15],[7,14,7,15],[7,1,7,2],[8,1,8,2],[7,9,7,13],[7,3,7,6],[8,3,8,6],[14,14,14,15],[10,1,10,2],[11,1,11,2],[14,9,14,13],[9,1,9,2],[14,2,14,6],[11,3,11,6],[10,3,10,6],[9,3,9,6]]}
[{"$f":"\"'20년 \"&R15&\"월 휴전심의 결과\"","v":"'20년 3월 휴전심의 결과"}]
[]
[]
[]
[]
[]
["◎ 전체 심의결과"]
["전   압","신 청",null,"채 택",null,null,null,"일정\n조정","불채택","(병행/취소/연기)",{"$nulls":4},"연간계획반영(%)"]
["765kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B9-I9","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J9,L9,N9)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O9/B9)","v":{"$error":"#REF!"}}]
["345kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B10-I10","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J10,L10,N10)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O10/B10)","v":{"$error":"#REF!"}}]
["154kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B11-I11","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J11,L11,N11)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O11/B11)","v":{"$error":"#REF!"}}]
["계",{"$f":"SUM(B9:B11)","v":{"$error":"#REF!"}},null,{"$f":"SUM(D9:D11)","v":{"$error":"#REF!"}},null,null,null,{"$f":"SUM(H9:H11)","v":{"$error":"#REF!"}},{"$f":"SUM(J12,L12,N12)","v":{"$error":"#REF!"}},{"$f":"SUM(J9:J11)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(L9:L11)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(N9:N11)","v":{"$error":"#REF!"}},{"$f":"SUM(O9:O11)","v":{"$error":"#REF!"}},{"$f":"(O12/B12)","v":{"$error":"#REF!"}}]
[]
["◎ 본부별 심의결과",{"$nulls":16},"월"]
["사업소","신 청","(765/345/154)",{"$nulls":4},"채 택","불채택","(병행/취소/연기)",{"$nulls":4},"연간계획반영(%)",null,null,3]
["서   울",{"$f":"SUM(C16:G16)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},{"$f":"B16-I16","v":{"$error":"#REF!"}},{"$f":"SUM(J16,L16,N16)","v":{"$error":"#REF!"}},{"$f":"SUM(S16:U16)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(W16:Y16)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA16:AC16)","v":{"$error":"#REF!"}},{"$f":"SUM(AE16:AG16)","v":{"$error":"#REF!"}},{"$f":"(O16/B16)","v":{"$error":"#REF!"}},null,"서울",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}}]
["남서울",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$f":"SUM(J17,L17,N17)","v":{"$error":"#REF!"}},{"$f":"SUM(S17:U17)","v":{"$error":"#REF!"}},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"남서울",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}}]
["인   천",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"인천",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}}]
["경기북부",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경기북부",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}}]
["경   기",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경기",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}}]
["강   원",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"강원",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}}]
["충   북",{"$f":"SUM(C22:G22)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"충북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}}]
["대전충남",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"대전충남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}}]
["전   북",{"$f":"SUM(C24:G24)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"전북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}}]
["광주전남",{"$f":"SUM(C25:G25)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"광주전남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}}]
["대구",{"$f":"SUM(C26:G26)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},{"$f":"B26-I26","v":{"$error":"#REF!"}},{"$f":"SUM(J26,L26,N26)","v":{"$error":"#REF!"}},{"$f":"SUM(S26:U26)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(W26:Y26)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA26:AC26)","v":{"$error":"#REF!"}},{"$f":"SUM(AE26:AG26)","v":{"$error":"#REF!"}},{"$f":"(O26/B26)","v":{"$error":"#REF!"}},null,"대구",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}}]
["경북",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}}]
["부산울산",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"부산울산",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}}]
["경   남",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$f":"SUM(W29:Y29)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA29:AC29)","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},null,"경남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}}]
["제   주",{"$f":"SUM(C30:G30)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$f":"(O30/B30)","v":{"$error":"#REF!"}},null,"제주",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}}]
[]
[" 붙임 :  1. 집중심의내역 1부"]
[" 붙임 :  전압별 검토서 1부. 끝."]
[]
[null,{"$f":"SUM(B16:B30)","v":{"$error":"#REF!"}},{"$f":"SUM(C16:C30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(E16:E30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(G16:G30)","v":{"$error":"#REF!"}},{"$f":"SUM(H16:H30)","v":{"$error":"#REF!"}},{"$f":"SUM(I16:I30)","v":{"$error":"#REF!"}},{"$f":"SUM(J16:J30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(L16:L30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(N16:N30)","v":{"$error":"#REF!"}},{"$f":"SUM(O16:O30)","v":{"$error":"#REF!"}}]
[{"$f":"COUNTIF(B36:N36,\"NO\")","v":0},{"$f":"IF(B35=B12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(C35=B9,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(E35=B10,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(G35=B11,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(H35=D12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(I35=I12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(J35=J12,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(L35=L12,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(N35=N12,\"\",\"NO\")","v":{"$error":"#REF!"}}]
[{"$f":"IF(A36>=1,\"틀린곳\",\"\")","v":""},{"$f":"IF(B36=\"NO\",\"총계\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C36=\"NO\",\"765\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(D36=\"NO\",\"총계\",\"\")","v":""},{"$f":"IF(E36=\"NO\",\"345\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(G36=\"NO\",\"154\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(H36=\"NO\",\"채택\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(I36=\"NO\",\"불채택\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(J36=\"NO\",\"병행\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(L36=\"NO\",\"취소\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(N36=\"NO\",\"연기\",\"\")","v":{"$error":"#REF!"}}]

{"sheet":"765송부","index":1,"n_rows":15,"n_cols":13,"rows_kept":15,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2020년도 \"&종합!R15&\"월 휴전계획서\"","v":"2020년도 3월 휴전계획서"}]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #1 M.Tr","신가평S/S 765kV #1M.Tr 철공진 방지공사","신가평S/S 765kV #1M.Tr 철공진 방지공사 - 72BAY 측 캐패시터 설치","2020-03-16 09:00","2020-03-25 18:00","2020-03-16 09:00","2020-03-25 18:00","연속"]
[2,"경기","성남","신안성S/S 765kV #85 BUS","20년 성남전력 변전정비회사 총액공사","#85BUS 모선보호반 대체","2020-03-04 09:00","2020-03-13 18:00","2020-03-04 09:00","2020-03-13 18:00","연속"]
[3,"경기","성남","신안성S/S 765kV #80 BUS","20년 성남전력 변전정비회사 총액공사","#80BUS 모선보호반 CT케이블 철거 및 포설","2020-03-02 09:00","2020-03-03 18:00","2020-03-02 09:00","2020-03-03 18:00","연속"]
[4,"강원","태백","신태백S/S #4 M.Tr","신태백S/S 345kV 용량부족 차단기 대체공사","1. 345kV 77BAY 대체(가덕산풍력 1CB증설 포함) 2. 765kV 8572 CB 유압장치 교체","2020-03-21 09:00","2020-06-18 18:00","2020-03-21 09:00","2020-06-18 18:00","연속"]
[5,"충북","직할","신중부E/C #5 M.Tr","765kV 신중부S/S 초기점검공사","765kV 신중부S/S 초기점검공사 345kV GIS PD발생 관련 절연로드PIN교체작업(7B61,7B01)","2020-03-21 09:00","2020-03-22 18:00","2020-03-21 09:00","2020-03-22 18:00","연속"]
[6,"충북","직할","신중부E/C #4 M.Tr","765kV 신중부S/S 초기점검공사","765kV 신중부S/S 초기점검공사 345kV GIS PD발생 관련 절연로드PIN교체작업(7961,7901)","2020-03-14 09:00","2020-03-15 18:00","2020-03-14 09:00","2020-03-15 18:00","연속"]
[7,"부산울산","동부산","신고리N/P #2 Tie-Tr","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(신고리S/S #2M.Tr)","2020-03-27 18:00","2020-03-28 18:00","2020-04-03 18:00","2020-04-04 18:00","연속"]
[8,"부산울산","동부산","신고리N/P #3 Tie-Tr","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(신고리S/S #3M.Tr)","2020-03-20 18:00","2020-03-21 18:00","2020-03-27 18:00","2020-03-28 18:00","연속"]
[9,"경남","함안","북경남S/S #5 M.Tr","765kV 북경남SS #5M.Tr 보통점검","765kV 북경남SS #5M.Tr(6대) 보통점검 시행","2020-03-30 09:00","2020-04-03 18:00","2020-03-16 09:00","2020-03-20 18:00","연속"]
[10,"경남","함안","북경남S/S #3 M.Tr","765kV 북경남SS #3M.Tr 보통점검","765kV 북경남SS #3M.Tr(6대) 보통점검 시행","2020-03-16 09:00","2020-03-20 18:00","2020-03-30 09:00","2020-04-03 18:00","연속"]
[11,"경남","함안","북경남S/S #4 M.Tr","765kV 북경남SS #4M.Tr 보통점검","765kV 북경남SS #4M.Tr(6대) 보통점검 시행","2020-03-23 09:00","2020-03-27 18:00","2020-03-23 09:00","2020-03-27 18:00","연속"]

{"sheet":"345송부","index":2,"n_rows":259,"n_cols":13,"rows_kept":259,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2020년도 \"&종합!R15&\"월 휴전계획서\"","v":"2020년도 3월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","중부S/S 345kV #1 Sh.R","20년 중부전력지사 변전정비회사 총액공사","ㅇ 중부S/S #1Sh.R GIS 하자점검","2020-03-02 09:00","2020-03-02 18:00","2020-03-02 09:00","2020-03-02 18:00","연속"]
[2,"남서울","동서울","곤지암동서울#1 T/L","345kV 곤지암-동서울#1T/L 7171, 7100 GIS 조작시험","345kV 곤지암-동서울#1T/L 7171, 7100 GIS 조작시험","2020-03-10 09:00","2020-03-10 18:00","2020-03-10 09:00","2020-03-10 18:00","연속"]
[3,"남서울","동서울","동서울미금#1 T/L","'20년도 동서울P/O 가공송전 순시점검 위탁공사","345kV 동서울-미금T/L 신규 건설구간 초기점검","2020-03-02 08:00","2020-03-02 18:00","취소","취소","연속"]
[4,"남서울","동서울","동서울미금#2 T/L","'20년도 동서울P/O 가공송전 순시점검 위탁공사","345kV 동서울-미금T/L 신규 건설구간 초기점검","2020-03-03 08:00","2020-03-03 18:00","2020-03-03 08:00","2020-03-03 18:00","연속"]
[5,"남서울","동서울","곤지암동서울#2 T/L","345kV 곤지암-동서울#2T/L 7271, 7200 GIS 보통점검","345kV 곤지암-동서울#2T/L 7271, 7200 GIS 보통점검","2020-03-11 09:00","2020-03-11 18:00","2020-03-11 09:00","2020-03-11 18:00","연속"]
[6,"남서울","동서울","신용인동서울#1 T/L","345kV 신용인-동서울#1T/L 7371, 7300 GIS 조작시험","345kV 신용인-동서울#1T/L 7371, 7300 GIS 조작시험","2020-03-12 09:00","2020-03-12 18:00","2020-03-12 09:00","2020-03-12 18:00","연속"]
[7,"남서울","동서울","신용인동서울#2 T/L","345kV 신용인-동서울#2T/L 7671, 7600 GIS 조작시험","345kV 신용인-동서울#2T/L 7671, 7600 GIS 조작시험","2020-03-13 09:00","2020-03-13 18:00","2020-03-13 09:00","2020-03-13 18:00","연속"]
[8,"남서울","동서울","신성남동서울#1 T/L","345kV 신성남-동서울#1T/L 7571, 7500 GIS 보통점검","345kV 신성남-동서울#1T/L 7571, 7500 GIS 보통점검","2020-03-16 09:00","2020-03-16 18:00","2020-03-16 09:00","2020-03-16 18:00","연속"]
[9,"남서울","영등포","신광명S/S 신시흥#1-서서울#1T/L TIE CB(7100)","신광명S/S #71Bay TIE CB 전자변 교체","공압식 차단기 지연동작 방지대책 전자변 교체","2020-03-11 09:00","2020-03-11 18:00","2020-03-11 09:00","2020-03-11 18:00","연속"]
[10,"남서울","영등포","신광명S/S 서서울-신광명#1T/L CB(7171)","신광명S/S 서서울-신광명#1T/L CB 전자변 교체","공압식 차단기 지연동작 방지대책 전자변 교체","2020-03-16 09:00","2020-03-16 18:00","2020-03-16 09:00","2020-03-16 18:00","연속"]
[11,"남서울","영등포","신광명S/S 서서울-신광명#2T/L CB(7272)","신광명S/S 서서울-신광명#2T/L CB 전자변 교체","공압식 차단기 지연동작 방지대책 전자변 교체","2020-03-17 09:00","2020-03-17 18:00","2020-03-17 09:00","2020-03-17 18:00","연속"]
[12,"남서울","영등포","신광명S/S #70-#71 SEC CB","신광명S/S #70-#71 SEC CB 전자변 교체","공압식 차단기 지연동작 방지대책 전자변 교체","2020-03-12 09:00","2020-03-12 18:00","2020-03-12 09:00","2020-03-12 18:00","연속"]
[13,"남서울","영등포","신광명S/S #75-#76 SEC CB","신광명S/S #75-#76 SEC CB 전자변 교체","공압식 차단기 지연동작 방지대책 전자변 교체","2020-03-13 09:00","2020-03-13 18:00","2020-03-13 09:00","2020-03-13 18:00","연속"]
[14,"남서울","직할","영등포S/S 345kV #70 BUS","영등포E/C #4M.Tr 증설","362kV GIS x 3CB 345kV M.Tr x 1 Bank 170kV GIS x 1CCT","2020-03-16 09:00","2020-03-23 09:00","취소","취소","연속"]
[15,"남서울","직할","영등포S/S 345kV #75 BUS","영등포E/C #4M.Tr 증설","362kV GIS x 3CB 345kV M.Tr x 1 Bank 170kV GIS x 1CCT","2020-03-23 09:00","2020-03-29 18:00","취소","취소","연속"]
[16,"인천","부평","신인천C/C 신경서신인천C/CT/L CB (7871(구))","신인천복합S/Y 7871 GIS 하자점검","신인천복합S/Y 7871 GIS 하자점검","2020-03-31 09:00","2020-03-31 18:00","2020-03-31 09:00","2020-03-31 18:00","연속"]
[17,"인천","부평","신인천C/C 신경서신인천T/L-4MT201 TIE CB(7800)","신인천복합S/Y 7800 GIS 하자점검","신인천복합S/Y 7800 GIS 하자점검","2020-03-30 09:00","2020-03-30 18:00","2020-03-30 09:00","2020-03-30 18:00","연속"]
[18,"인천","부평","신인천C/C 4MT001 TIE CB(7900)","신인천복합S/Y 7900 GIS 조작시험","신인천복합S/Y 7900 GIS 조작시험","2020-03-27 13:00","2020-03-27 18:00","2020-03-27 13:00","2020-03-27 18:00","연속"]
[19,"인천","부평","신인천C/C 4MT101 CB(7772)","신인천복합S/Y 7772 GIS 조작시험","신인천복합S/Y 7772 GIS 조작시험","2020-03-27 09:00","2020-03-27 13:00","2020-03-27 09:00","2020-03-27 13:00","연속"]
[20,"인천","부평","신인천C/C 4MT001 CB(7972)","신인천복합S/Y 7972 GIS 조작시험","신인천복합S/Y 7972 GIS 조작시험","2020-03-26 13:00","2020-03-26 18:00","2020-03-26 13:00","2020-03-26 18:00","연속"]
[21,"인천","부평","신인천C/C 4MT201 CB(7872)","신인천복합S/Y 7872 GIS 조작시험","신인천복합S/Y 7872 GIS 조작시험","2020-03-26 09:00","2020-03-26 13:00","2020-03-26 09:00","2020-03-26 13:00","연속"]
[22,"인천","부평","신인천C/C #76-#77 SEC CB","신인천복합S/Y 76-77 SEC GIS 조작시험","신인천복합S/Y 76-77 SEC GIS 조작시험","2020-03-25 13:00","2020-03-25 18:00","2020-03-25 13:00","2020-03-25 18:00","연속"]
[23,"인천","부평","신인천C/C #71-#72 SEC CB","신인천복합S/Y 71-72 SEC GIS 조작시험","신인천복합S/Y 71-72 SEC GIS 조작시험","2020-03-25 09:00","2020-03-25 13:00","2020-03-25 09:00","2020-03-25 13:00","연속"]
[24,"인천","부평","신인천C/C #75-#76 SEC CB","신인천복합S/Y 75-76 SEC GIS 조작시험","신인천복합S/Y 75-76 SEC GIS 조작시험","2020-03-24 13:00","2020-03-24 18:00","2020-03-24 13:00","2020-03-24 18:00","연속"]
[25,"인천","부평","신인천C/C #70-#71 SEC CB","신인천복합S/Y 70-71 SEC GIS 조작시험","신인천복합S/Y 70-71 SEC GIS 조작시험","2020-03-24 09:00","2020-03-24 13:00","2020-03-24 09:00","2020-03-24 13:00","연속"]
[26,"인천","부평","인천CC S/Y #2 TIE Tr 1차 CB(7C72)","인천화력S/Y 7C72GIS 조작시험","인천화력S/Y 7C72GIS 조작시험","2020-03-23 13:00","2020-03-23 18:00","2020-03-23 13:00","2020-03-23 18:00","연속"]
[27,"인천","시흥","신시흥신광명#1 T/L","신시흥S/S 345kV 신시흥신광명#1T/L LA대체","신시흥S/S 345kV 신시흥신광명#1T/L LA대체","2020-03-23 10:00","2020-03-24 18:00","2020-03-23 10:00","2020-03-24 18:00","연속"]
[28,"인천","부평","인천CC S/Y 가정인천CC#2T/L-#2 TIE Tr 1차 TIE CB(7C00)","인천화력S/Y 7C00GIS 조작시험","인천화력S/Y 7C00GIS 조작시험","2020-03-23 09:00","2020-03-23 13:00","2020-03-23 09:00","2020-03-23 13:00","연속"]
[29,"인천","부평","인천CC S/Y 가정-인천CC#2T/L CB(7C71)","인천화력S/Y 7C71GIS 조작시험","인천화력S/Y 7C71GIS 조작시험","2020-03-20 13:00","2020-03-20 18:00","2020-03-20 13:00","2020-03-20 18:00","연속"]
[30,"인천","부평","인천CC S/Y 인천복합 #5,6G/T CB(7B71)","인천화력S/Y 7B71GIS 조작시험","인천화력S/Y 7B71GIS 조작시험","2020-03-20 09:00","2020-03-20 13:00","2020-03-20 09:00","2020-03-20 13:00","연속"]
[31,"인천","부평","인천CC S/Y 인천복합 #3S/T CB(7B72)","인천화력S/Y 7B72GIS 조작시험","인천화력S/Y 7B72GIS 조작시험","2020-03-19 13:00","2020-03-19 18:00","2020-03-19 13:00","2020-03-19 18:00","연속"]
[32,"인천","부평","인천CC S/Y 포스코S/Y-인천CC#2T/L CB(7A72)","인천화력S/Y 7A72GIS 조작시험","인천화력S/Y 7A72GIS 조작시험","2020-03-19 09:00","2020-03-19 13:00","2020-03-19 09:00","2020-03-19 13:00","연속"]
[33,"인천","부평","인천CC S/Y 인천복합#5,6G/T-인천복합#3S/T TIE CB(7B00)","인천화력S/Y 7B00GIS 조작시험","인천화력S/Y 7B00GIS 조작시험","2020-03-18 13:00","2020-03-18 18:00","2020-03-18 13:00","2020-03-18 18:00","연속"]
[34,"인천","부평","인천CC S/Y 포스코S/Y인천CC#1-#2T/L TIE CB(7A00)","인천화력S/Y 7A00GIS 조작시험","인천화력S/Y 7A00GIS 조작시험","2020-03-18 09:00","2020-03-18 13:00","2020-03-18 09:00","2020-03-18 13:00","연속"]
[35,"인천","부평","인천CC S/Y #75-#76 SEC CB","인천화력S/Y 75-76 SEC GIS 조작시험","인천화력S/Y 75-76 SEC GIS 조작시험","2020-03-17 13:00","2020-03-17 18:00","2020-03-17 13:00","2020-03-17 18:00","연속"]
[36,"인천","부평","신경서서인천CC T/L","선도제 345kV 송전선로 보호배전반 성능개선","87 PCM 통신회로 Loop시 오동작방지 관련 펌웨어 업그레이드","2020-03-17 10:00","2020-03-17 16:00","2020-03-17 10:00","2020-03-17 16:00","연속"]
[37,"인천","부평","인천CC S/Y #70-#71 SEC CB","인천화력S/Y 70-71 SEC GIS 조작시험","인천화력S/Y 70-71 SEC GIS 조작시험","2020-03-17 09:00","2020-03-17 13:00","2020-03-17 09:00","2020-03-17 13:00","연속"]
[38,"인천","부평","인천CC S/Y 포스코S/Y-인천CC#1T/L CB(7A71)","인천화력S/Y 7A71GIS 조작시험","인천화력S/Y 7A71GIS 조작시험","2020-03-16 13:00","2020-03-16 18:00","2020-03-16 13:00","2020-03-16 18:00","연속"]
[39,"인천","부평","신김포신인천CC T/L","선도제 345kV 송전선로 보호배전반 성능개선","87 PCM 통신회로 Loop시 오동작방지 관련 펌웨어 업그레이드","2020-03-16 10:00","2020-03-16 16:00","2020-03-16 10:00","2020-03-16 16:00","연속"]
[40,"인천","부평","인천CC S/Y 신경서-인천CC#2T/L CB(7471)","인천화력S/Y 7471GIS 조작시험","인천화력S/Y 7471GIS 조작시험","2020-03-16 09:00","2020-03-16 13:00","2020-03-16 09:00","2020-03-16 13:00","연속"]
[41,"인천","부평","인천CC S/Y 신경서-인천CC#1T/L CB(7271)","인천화력S/Y 7271GIS 조작시험","인천화력S/Y 7271GIS 조작시험","2020-03-13 13:00","2020-03-13 18:00","2020-03-13 13:00","2020-03-13 18:00","연속"]
[42,"인천","부평","인천CC S/Y #1 TIE Tr 1차 CB(7171)","인천화력S/Y 7171GIS 조작시험","인천화력S/Y 7171GIS 조작시험","2020-03-13 09:00","2020-03-13 13:00","2020-03-13 09:00","2020-03-13 13:00","연속"]
[43,"인천","부평","인천CC S/Y 신경서인천CC#1T/L TIE CB(7200)","인천화력S/Y 7200GIS 조작시험","인천화력S/Y 7200GIS 조작시험","2020-03-12 13:00","2020-03-12 18:00","2020-03-12 13:00","2020-03-12 18:00","연속"]
[44,"인천","부평","인천CC S/Y #1 TIE Tr 1차 TIE CB(7100)","인천화력S/Y 7100GIS 조작시험","인천화력S/Y 7100GIS 조작시험","2020-03-12 09:00","2020-03-12 13:00","2020-03-12 09:00","2020-03-12 13:00","연속"]
[45,"인천","시흥","영흥#2T/P 신시흥-영흥TP#1T/L TIE GIS","영흥#2SY 345kV 신시흥영흥#1 CB(7800) B상 누유보수","영흥#2SY 345kV 신시흥영흥#1 CB(7800) B상 누유보수","2020-03-09 10:00","2020-03-09 18:00","2020-03-09 10:00","2020-03-09 18:00","연속"]
[46,"인천","부평","신경서포스코CC#2 T/L","345kV 신경서-포스코T/L 접속함 교체공사","PD발생에 따른 접속함 교체(8EA) (#1T/L-J/B#4(A,B상), J/B#7(A,B,C상), #2T/L-J/B#8(A,B,C상)","2020-03-09 09:00","2020-03-15 18:00","2020-03-09 09:00","2020-03-15 18:00","연속"]
[47,"인천","직할","신부평S/S #3 M.Tr","신부평S/S #3M.Tr 2차 170kV GIS 정밀점검","신부평S/S #3M.Tr 2차 170kV GIS 정밀점검","2020-03-09 09:00","2020-03-11 18:00","취소","취소","연속"]
[48,"인천","시흥","영흥#2T/P 신시흥-영흥TP#3T/L-#6G.Tr 1차 TIE GIS","영흥#2SY 345kV 신시흥영흥#3 CB(7700) A,B상 누유보수","영흥#2SY 345kV 신시흥영흥#3 CB(7700) A,B상 누유보수","2020-03-06 10:00","2020-03-06 18:00","2020-03-06 10:00","2020-03-06 18:00","연속"]
[49,"인천","시흥","영흥#2T/P 영흥TP연락#1T/L GIS","영흥#2S/Y 345kV영흥TP연락#1TL CB(7671) A상 누유보수","영흥#2S/Y 345kV영흥TP연락#1TL CB(7671) A상 누유보수","2020-03-05 10:00","2020-03-05 18:00","2020-03-05 10:00","2020-03-05 18:00","연속"]
[50,"인천","직할","신부평S/S #2 M.Tr","신부평S/S #2M.Tr 2차 170kV GIS 정밀점검","신부평S/S #2M.Tr 2차 170kV GIS 정밀점검","2020-03-05 09:00","2020-03-07 18:00","취소","취소","연속"]
[51,"인천","부평","신가좌S/S 신가좌-신시흥#2T/L CB(7471)","신가좌S/S 7471GIS 조작시험","신가좌S/S 7471GIS 조작시험","2020-03-04 13:00","2020-03-04 18:00","2020-03-04 13:00","2020-03-04 18:00","연속"]
[52,"인천","부평","신가좌S/S 신가좌-신시흥#1T/L CB(7272)","신가좌S/S 7272GIS 조작시험","신가좌S/S 7272GIS 조작시험","2020-03-04 09:00","2020-03-04 13:00","2020-03-04 09:00","2020-03-04 13:00","연속"]
[53,"인천","부평","신가좌S/S 신가좌신시흥#2T/L-#3 M.Tr 1차 TIE CB(7400)","신가좌S/S 7400GIS 조작시험","신가좌S/S 7400GIS 조작시험","2020-03-03 13:00","2020-03-03 18:00","2020-03-03 13:00","2020-03-03 18:00","연속"]
[54,"인천","부평","신가좌S/S #2 M.Tr 1차 TIE CB A (7300)","신가좌S/S 7300GIS 조작시험","신가좌S/S 7300GIS 조작시험","2020-03-03 09:00","2020-03-03 13:00","2020-03-03 09:00","2020-03-03 13:00","연속"]
[55,"인천","부평","신가좌S/S #3 M.Tr 1차 CB(7472)","신가좌S/S 7472GIS 조작시험","신가좌S/S 7472GIS 조작시험","2020-03-02 13:00","2020-03-02 18:00","2020-03-02 13:00","2020-03-02 18:00","연속"]
[56,"인천","김포","가정개폐소 가정-갈산#1T/L CB(7472)","345kV 가정-갈산 지중T/L 건설공사","목적 : 서부지역 전력계통보강 선종 및 규격 : 345kV XLPE 2500SQ 회선수 및 길이 : 3회선, 7Km 금회휴전 : 가정-갈산#1T/L 관련 차단기( 7400, 7472 ) 작업내용 : GIS챔버분리, 케이블입상, 접속, AC내전압, GIS챔버 조립","2020-03-02 09:30","2020-04-07 18:00","2020-03-02 09:30","2020-04-07 18:00","연속"]
[57,"인천","김포","가정개폐소 가정-갈산#1T/L TIE CB(7400)","345kV 가정-갈산 지중T/L 건설공사","목적 : 서부지역 전력계통보강 선종 및 규격 : 345kV XLPE 2500SQ 회선수 및 길이 : 3회선, 7Km 금회휴전 : 가정-갈산#1T/L 관련 차단기( 7400, 7472 ) 작업내용 : GIS챔버분리, 케이블입상, 접속, AC내전압, GIS챔버 조립","2020-03-02 09:30","2020-04-07 18:00","2020-03-02 09:30","2020-04-07 18:00","연속"]
[58,"인천","김포","가정개폐소 신가좌-가정#2T/L TIE CB(7300)","345kV 가정-갈산 지중T/L 건설공사","목적 : 서부지역 전력계통보강 선종 및 규격 : 345kV XLPE 2500SQ 회선수 및 길이 : 3회선, 7Km 금회휴전 : 가정-갈산#2T/L 관련 차단기( 7300, 7372(신규) ) 작업내용 : GIS챔버분리, 케이블입상, 접속, AC내전압, GIS챔버 조립","2020-03-02 09:30","2020-04-07 18:00","2020-03-02 09:30","2020-04-07 18:00","연속"]
[59,"인천","김포","가정개폐소 가정-갈산#2T/L CB(7372)","345kV 가정-갈산 지중T/L 건설공사","목적 : 서부지역 전력계통보강 선종 및 규격 : 345kV XLPE 2500SQ 회선수 및 길이 : 3회선, 7Km 금회휴전 : 가정-갈산#2T/L 관련 차단기( 7300, 7372(신규) ) 작업내용 : GIS챔버분리, 케이블입상, 접속, AC내전압, GIS챔버 조립","2020-03-02 09:30","2020-04-07 18:00","2020-03-02 09:30","2020-04-07 18:00","연속"]
[60,"인천","부평","신가좌S/S 신가좌-가정#1T/L CB(7271)","신가좌S/S 7271GIS 조작시험","신가좌S/S 7271GIS 조작시험","2020-03-02 09:00","2020-03-02 13:00","2020-03-02 09:00","2020-03-02 13:00","연속"]
[61,"인천","부평","신경서포스코CC#1 T/L","345kV 신경서-포스코T/L 접속함 교체공사","PD발생에 따른 접속함 교체(8EA) (#1T/L-J/B#4(A,B상), J/B#7(A,B,C상), #2T/L-J/B#8(A,B,C상)","2020-03-02 09:00","2020-03-08 18:00","2020-03-02 09:00","2020-03-08 18:00","연속"]
[62,"인천","직할","신부평S/S #1 M.Tr","신부평S/S #1M.Tr 2차 170kV GIS 정밀점검","신부평S/S #1M.Tr 2차 170kV GIS 정밀점검","2020-03-02 09:00","2020-03-04 18:00","취소","취소","연속"]
[63,"경기북부","고양","신덕은S/S #1 M.Tr","신덕은S/S 345kV #1M.Tr 보호반 교체공사","신덕은S/S 345kV #1M.Tr 보호반 신규 보호반으로 교체","2020-03-09 10:00","2020-03-13 18:00","2020-03-09 10:00","2020-03-13 18:00","연속"]
[64,"경기북부","고양","신김포신파주#2 T/L","345kV 신파주-양주 등 11개T/L 항공시설물 정비공사","항공구 설치공사 시행 - 구간 : 345kV 신김포-신파주T/L No.13-14호 등 5경간","2020-03-16 07:00","2020-03-16 18:00","2020-03-17 07:00","2020-03-17 18:00","연속"]
[65,"경기북부","고양","신김포신파주#1 T/L","고양전력지사 관내 T/L OPGW 항공장애표시구 시설공사","345kV 신김포-신파주#1T/L OPGW용 항공장애 표시구 설치","2020-03-17 07:00","2020-03-17 18:00","2020-03-18 07:00","2020-03-18 18:00","연속"]
[66,"경기북부","고양","파주문산C/C 신덕은-파주문산CC#1T/L CB(7471)","제작사 설비보수-유압블록 누유보수","제작사 - 파주문산CC 7471 CB 유압펌프 누유보수 변전정비회사 - 차단기 개폐타임 측정","2020-03-26 09:00","2020-03-26 18:00","2020-03-26 09:00","2020-03-26 18:00","연속"]
[67,"경기북부","고양","파주문산C/C #4TIE-#4G/T 1차 CB(7400)","제작사 설비보수-유압블록 누유보수","제작사 - 파주문산CC 7471 CB 유압펌프 누유보수","2020-03-27 10:00","2020-03-27 18:00","2020-03-27 10:00","2020-03-27 18:00","연속"]
[68,"경기북부","구리","동서울미금#1 T/L","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 미금S/S 교체 73Bay 차단기 3대 감시제어계측 포인트이관 (→SA) - 73Bay LCP 및 배전반 모자익반 제어케이블 철거 및 재결선","2020-03-02 09:00","2020-03-06 18:00","2020-03-02 09:00","2020-03-06 18:00","연속"]
[69,"경기북부","구리","신가평미금#1 T/L","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 미금S/S 교체 77Bay 차단기 3대 감시제어계측 포인트이관 (→SA) - 77Bay LCP 및 배전반 모자익반 제어케이블 철거 및 재결선","2020-03-09 09:00","2020-03-17 18:00","2020-03-09 09:00","2020-03-17 18:00","연속"]
[70,"경기북부","구리","미금S/S #2 M.Tr","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 미금S/S 교체 73Bay 차단기 3대 감시제어계측 포인트이관 (→SA) - 73Bay LCP 및 배전반 모자익반 제어케이블 철거 및 재결선","2020-03-02 09:00","2020-03-06 18:00","취소","취소","연속"]
[71,"경기북부","구리","신가평미금#2 T/L","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 미금S/S 교체 77Bay 차단기 3대 감시제어계측 포인트이관 (→SA) - 78Bay LCP 및 배전반 모자익반 제어케이블 철거 및 재결선","2020-03-19 09:00","2020-03-27 18:00","2020-03-19 09:00","2020-03-27 18:00","연속"]
[72,"경기북부","구리","신가평포천LNGCC#1 T/L","345kV 신가평-포천LNGCC T/L 항공장애시설물 정비공사","ㅇ 항공장애표시구 설치 - No.1~2호 등 48경간","2020-03-02 07:00","2020-03-13 18:00","취소","취소","연속"]
[73,"경기북부","구리","신가평S/S 345kV #75 BUS","19년 345kV GIS 정밀점검","19년 345kV GIS 정밀점검(7472GIS 정밀점검)","2020-03-02 09:00","2020-03-03 18:00","취소","취소","연속"]
[74,"경기북부","구리","신가평신의정부#2 T/L","345kV 신가평-신의정부T/L 항공장애시설물 정비공사","ㅇ 항공장애표시구 설치 - S/T ~ No.1호","2020-03-16 07:00","2020-03-16 18:00","2020-03-02 07:00","2020-03-02 18:00","연속"]
[75,"경기북부","직할","양주S/S #3 M.Tr 1차 GIS CB(7772)","'20-21년 경기북부 직할 변전협력회사 총액공사","보통점검","2020-03-23 09:00","2020-03-26 18:00","2020-03-23 09:00","2020-03-26 18:00","연속"]
[76,"경기북부","직할","양주S/S SVC M.Tr-#3 M.Tr 1차 TIE GIS CB(7700)","'20-21년 경기북부 직할 변전협력회사 총액공사","보통점검","2020-03-23 09:00","2020-03-26 18:00","2020-03-23 09:00","2020-03-26 18:00","연속"]
[77,"경기북부","직할","양주S/S #3 M.Tr","양주S/S 옥외철구 GIS화 전력구공사","#3M.Tr 인출측 전력구공사","2020-03-18 09:00","2020-03-19 18:00","2020-03-18 09:00","2020-03-19 18:00","연속"]
[78,"경기북부","직할","양주S/S #2 M.Tr","양주S/S 옥외철구 GIS화 전력구공사","#2M.Tr 인출측 전력구공사","2020-03-16 09:00","2020-03-17 18:00","2020-03-16 09:00","2020-03-17 18:00","연속"]
[79,"경기북부","직할","양주S/S #1 M.Tr","양주S/S 옥외철구 GIS화 전력구공사","#1M.Tr 인출측 전력구공사","2020-03-11 09:00","2020-03-12 18:00","2020-03-11 09:00","2020-03-12 18:00","연속"]
[80,"경기북부","직할","양주S/S #4 M.Tr","양주S/S 옥외철구 GIS화 전력구공사","#4M.Tr 인출측 전력구공사","2020-03-09 09:00","2020-03-10 18:00","2020-03-09 09:00","2020-03-10 18:00","연속"]
[81,"경기북부","직할","양주S/S 345kV #4 Sh.R","'20-21년 경기북부 직할 변전협력회사 총액공사","차단기 보통점검","2020-03-06 09:00","2020-03-06 18:00","2020-03-06 09:00","2020-03-06 18:00","연속"]
[82,"경기북부","직할","양주S/S 345kV #6 Sh.R","'20-21년 경기북부 직할 변전협력회사 총액공사","개폐타임 측정","2020-03-03 09:00","2020-03-03 18:00","2020-03-03 09:00","2020-03-03 18:00","연속"]
[83,"경기북부","직할","양주S/S 345kV #5 Sh.R","'20-21년 경기북부 직할 변전협력회사 총액공사","차단기 보통점검","2020-03-05 09:00","2020-03-05 18:00","2020-03-05 09:00","2020-03-05 18:00","연속"]
[84,"경기북부","직할","신파주양주#1 T/L","고양전력지사 관내 T/L OPGW 항공장애표시구 시설공사","345kV 양주-중부#2T/L OPGW용 항공장애 표시구 설치","2020-03-09 07:00","2020-03-10 18:00","취소","취소","연속"]
[85,"경기북부","직할","신파주양주#2 T/L","'19년 경기북부직할 362kV GIS정밀점검(미시행분)","정밀점검","2020-03-09 07:30","2020-03-15 18:00","취소","취소","연속"]
[86,"경기","군포","신안산S/S #4 M.Tr","345kV 신안산S/S 용량부족 GIS 대체공사","345kV 신안산S/S 용량부족 GIS 대체공사 - #73BAY(#4M.Tr) 용량대체 - 345kV 40kA 3CB 철거, 345kV 63kA 3CB 설치","2020-03-23 09:00","2020-06-26 18:00","2020-03-10 09:00","2020-06-19 18:00","연속"]
[87,"경기","군포","신안산S/S 345kV #70 BUS","345kV 신안산S/S 용량부족 GIS 대체공사","345kV 신안산S/S 용량부족 GIS 대체공사 - #70BUS 용량대체(71, 72, 73Bay, 40kA → 63kA)","2020-03-02 09:00","2020-03-19 18:00","2020-03-02 09:00","2020-03-20 18:00","연속"]
[88,"경기","군포","신시흥신안산#1 T/L","345kV 신안산S/S 용량부족 GIS 대체공사","345kV 신안산S/S 용량부족 GIS 대체공사 - #73BAY(#4M.Tr, 신시흥-신안산T/L) 용량대체 - 345kV 40kA 3CB 철거, 345kV 63kA 3CB 설치","2020-03-23 09:00","2020-06-26 18:00","2020-03-10 09:00","2020-06-19 18:00","연속"]
[89,"경기","성남","신성남S/S STATCOM CB","20년 성남전력 변전정비회사 총액공사","신성남S/S 345kV STATCOM 냉각설비점검 - M.Tr(보통) - 1차 GIS(보통) - 1,2차 LA(보통) - 1차 N LA(보통)","2020-03-04 09:00","2020-03-06 18:00","2020-03-04 09:00","2020-03-06 18:00","연속"]
[90,"경기","성남","신성남동서울#2 T/L","신성남-동서울TL OPGW시설공사(대장지구)","신성남동서울T/L 불곡산C/H~동서울 구간 OPGW 증설","2020-03-02 07:00","2020-03-13 18:00","2020-03-02 07:00","2020-03-13 18:00","연속"]
[91,"경기","성남","신수원S/S 신수원-삼성#2T/L TIE GIS CB(7400)","20년 성남전력 변전정비회사 총액공사","신수원S/S 345kV 신수원-삼성#2T/L TIE GIS 초기점검","2020-03-26 09:00","2020-03-26 18:00","2020-03-26 09:00","2020-03-26 18:00","연속"]
[92,"경기","성남","신수원S/S 신수원-삼성#2T/L GIS CB(7472)","20년 성남전력 변전정비회사 총액공사","신수원S/S 345kV 신수원-삼성#2T/L GIS 초기점검","2020-03-27 09:00","2020-03-27 18:00","2020-03-27 09:00","2020-03-27 18:00","연속"]
[93,"경기","성남","신수원S/S #4 M.Tr 1차 GIS CB(7471)","20년 성남전력 변전정비회사 총액공사","신수원S/S 345kV #4 M.Tr 1차 GIS 초기점검","2020-03-25 09:00","2020-03-25 18:00","2020-03-25 09:00","2020-03-25 18:00","연속"]
[94,"경기","성남","신안성S/S #6 Sh.R FEEDER GIS CB(7979)","20년 성남전력 변전정비회사 총액공사","신안성S/S 345kV #6 Sh.R FEEDER GIS 조작시험 - 전자변히터설치","2020-03-24 14:00","2020-03-24 18:00","2020-03-24 14:00","2020-03-24 18:00","연속"]
[95,"경기","성남","신안성S/S #5 Sh.R FEEDER GIS CB(7779)","20년 성남전력 변전정비회사 총액공사","신안성S/S 345kV #5 Sh.R FEEDER GIS 조작시험 - 전자변히터설치","2020-03-24 09:00","2020-03-24 14:00","2020-03-24 09:00","2020-03-24 14:00","연속"]
[96,"경기","성남","신용인동서울#1 T/L","신성남-동서울TL OPGW시설공사(대장지구)","신성남동서울T/L 불곡산C/H~동서울 구간 OPGW 증설","2020-03-12 07:00","2020-03-12 18:00","취소","취소","연속"]
[97,"경기","성남","신용인S/S #4 M.Tr","20년 성남전력 변전정비회사 총액공사","신용인S/S 345kV #4 M.Tr 초기점검 - 1,2차 GIS(초기) - 1,2,3차 LA(초기)","2020-03-02 09:00","2020-03-03 18:00","2020-03-02 09:00","2020-03-03 18:00","연속"]
[98,"경기","직할","화성S/S 345kV #76 BUS","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV (40/50kA -> 63kA) GIS 30대 교체 O. 화성-평택T/P #1T/L 7BBAY -> 77BAY 이설","2020-03-18 11:00","2020-03-19 11:00","2020-03-18 11:00","2020-03-19 11:00","연속"]
[99,"경기","직할","화성평택T/P#2 T/L","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV (40/50kA -> 63kA) GIS 30대 교체 O. 화성-평택T/P #2T/L 78_BAY -> 7B_BAY 이설","2020-03-23 10:00","2020-04-10 17:00","2020-03-23 10:00","2020-04-10 17:00","연속"]
[100,"경기","직할","화성평택T/P#1 T/L","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV (40/50kA -> 63kA) GIS 30대 교체 O. 화성-평택T/P #1T/L 7BBAY -> 77BAY 이설","2020-03-02 10:00","2020-03-20 17:00","2020-03-02 10:00","2020-03-20 17:00","연속"]
[101,"경기","직할","화성신안산#1 T/L","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV (40/50kA -> 63kA) GIS 30대 교체 O. 화성-평택T/P #1T/L 7BBAY -> 77BAY 이설","2020-03-17 11:00","2020-03-19 11:00","2020-03-17 11:00","2020-03-20 11:00","연속"]
[102,"경기","직할","화성S/S 345kV #71 BUS","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV (40/50kA -> 63kA) GIS 30대 교체 O. 화성-평택T/P #1T/L 7BBAY -> 77BAY 이설","2020-03-17 11:00","2020-03-18 11:00","2020-03-17 11:00","2020-03-18 11:00","연속"]
[103,"경기","직할","아산화성#1 T/L","345kV 신온양서서울외 2개T/L 지장이설","지장이설 임시선로 구성","2020-03-02 07:00","2020-03-06 18:00","2020-03-02 07:00","2020-03-06 18:00","연속"]
[104,"경기","직할","아산화성#2 T/L","345kV 신온양서서울외 2개T/L 지장이설","지장이설 임시선로 구성","2020-03-07 07:00","2020-03-10 18:00","2020-03-07 07:00","2020-03-10 18:00","연속"]
[105,"경기","직할","화성S/S #1 CLR 71BUS GIS(2019)","20-21년 경기본부 직할 변전정비회사 총액공사","화성S/S #1CLR 71BUS GIS 초기점검","2020-03-11 10:00","2020-03-11 18:00","2020-03-11 10:00","2020-03-11 18:00","연속"]
[106,"경기","직할","화성S/S #1 CLR 70BUS GIS(2019)","20-21년 경기본부 직할 변전정비회사 총액공사","화성S/S #1CLR 70BUS GIS 초기점검","2020-03-12 10:00","2020-03-12 18:00","2020-03-12 10:00","2020-03-12 18:00","연속"]
[107,"강원","강릉","신양양S/S #3 M.Tr","신양양S/S 러버히터 설치","○ 신양양S/S 러버히터 설치 - 7472CB, 7400 CB","2020-03-10 10:00","2020-03-10 18:00","2020-03-10 10:00","2020-03-10 18:00","연속"]
[108,"강원","강릉","동해양양PP T/L","양양PP 컨트롤블록 교체","○ 양양PP 컨트롤블록 교체 - 7371CB, 7300 CB","2020-03-02 10:00","2020-03-07 18:00","2020-03-02 10:00","2020-03-07 18:00","연속"]
[109,"강원","강릉","신양양양양PP T/L","양양PP 컨트롤블록 교체","○ 양양PP 컨트롤블록 교체 - 7171CB, 7100 CB","2020-03-23 10:00","2020-03-28 18:00","2020-03-23 10:00","2020-03-28 18:00","연속"]
[110,"강원","동해","동해S/S #2 M.Tr","2020년 동해전력지사 변전정비 협력회사 총액공사","1. 74Bay B/F PNL 대체공사 2. M.Tr 보통점검 3. M.Tr 1차 GIS(7472) 보통점검 4. M.Tr 1, 2, 3차 LA 보통점검 5. M.Tr 1, 3차 PT 보통점검 6. M.Tr 2차 차단기 조작시험","2020-03-02 09:30","2020-03-06 18:00","2020-03-02 09:30","2020-03-06 18:00","연속"]
[111,"강원","동해","신제천동해#1 T/L","2020년 동해전력지사 변전정비 협력회사 총액공사","1. 71Bay B/F PNL 대체 2. GIS 보통점검(7171, 7100) 3. LA 보통점검 4. PT 보통점검 5. 송전선로 보호반 초기점검","2020-03-09 09:30","2020-03-13 18:00","2020-03-09 09:30","2020-03-13 18:00","연속"]
[112,"강원","동해","동해S/S #1 M.Tr","2020년 동해전력지사 변전정비 협력회사 총액공사","1. 71Bay B/F PNL 대체공사 2. M.Tr 1차 GIS(7172) 보통점검 3. M.Tr 1, 2, 3차 LA 보통점검 4. M.Tr 1, 3차 PT 보통점검 5. M.Tr 2차 차단기 조작시험","2020-03-09 09:30","2020-03-13 18:00","2020-03-09 09:30","2020-03-13 18:00","연속"]
[113,"강원","동해","동해양양PP T/L","2020년 동해전력지사 변전정비 협력회사 총액공사","1. 74Bay B/F PNL 대체 2. GIS 보통점검(7471, 7400) 3. LA 보통점검 4. PT 보통점검 5. 송전선로 보호반 보통점검","2020-03-02 09:30","2020-03-06 18:00","취소","취소","연속"]
[114,"강원","동해","삼척GP한울NP#1 T/L","2020년 동해전력 변전정비 협력회사 총액공사","1. GIS 보통점검(7571, 7500) 2. PT 보통점검 3. 송전선로보호반 보통점검","2020-03-20 09:30","2020-03-20 18:00","2020-03-20 09:30","2020-03-20 18:00","연속"]
[115,"강원","동해","삼척T/P #1 Tie-Tr","2020년 동해전력 변전정비 협력회사 총액공사","1. M.Tr 하자점검 2. 1, 2, 3차 GIS 하자점검","2020-03-16 09:30","2020-03-18 18:00","2020-03-16 09:30","2020-03-18 18:00","연속"]
[116,"강원","동해","삼척GP한울NP#2 T/L","2020년 동해전력 변전정비 협력회사 총액공사","1. GIS 보통점검(7471, 7400) 2. PT 보통점검 3. 송전선로보호반 보통점검","2020-03-19 09:30","2020-03-19 18:00","2020-03-19 09:30","2020-03-19 18:00","연속"]
[117,"충북","직할","신중부신진천#1 T/L","345kV 신중부-신진천T/L 안전이격거리 확보공사","철탑 2기 교체, 전선이동","2020-03-09 07:00","2020-03-11 18:00","2020-03-04 07:00","2020-03-05 18:00","연속"]
[118,"충북","직할","신중부신진천#1 T/L","345kV 신중부-신진천T/L 안전이격거리 확보공사","철탑 2기 교체, 전선이동","2020-03-20 07:00","2020-03-22 18:00","2020-03-14 07:00","2020-03-16 18:00","연속"]
[119,"충북","직할","신중부S/S 345kV #6 Sh.R CB","765kV 신중부S/S 초기점검공사","765kV 신중부S/S 초기점검공사 345kV GIS PD발생 관련 절연로드PIN교체작업(7C61,7C01)","2020-03-16 09:00","2020-03-17 18:00","취소","취소","연속"]
[120,"충북","직할","신중부남청주#1 T/L","765kV 신중부S/S 초기점검공사","765kV 신중부S/S 초기점검공사 345kV GIS PD발생 관련 절연로드PIN교체작업(7C02,7C62)","2020-03-18 09:00","2020-03-19 18:00","2020-03-28 09:00","2020-03-29 18:00","연속"]
[121,"충북","직할","신중부남청주#2 T/L","765kV 신중부S/S 초기점검공사","765kV 신중부S/S 초기점검공사 345kV GIS PD발생 관련 절연로드PIN교체작업(7B02,7B62)","2020-03-23 09:00","2020-03-24 18:00","취소","취소","연속"]
[122,"충북","직할","신중부신진천#2 T/L","345kV 신중부-신진천T/L 안전이격거리 확보공사","철탑 2기 교체, 전선이동","2020-03-12 07:00","2020-03-19 18:00","2020-03-06 07:00","2020-03-13 18:00","연속"]
[123,"충북","직할","신중부E/C 345kV #75 BUS","765kV 신중부S/S 초기점검공사","765kV 신중부S/S 초기점검공사 345kV GIS PD발생 관련 절연로드PIN교체작업(7952,7A52,7B52,7C52)","2020-03-30 09:00","2020-04-01 18:00","취소","취소","연속"]
[124,"충북","직할","신중부E/C 345kV #70 BUS","765kV 신중부S/S 초기점검공사","765kV 신중부S/S 초기점검공사 345kV GIS PD발생 관련 절연로드PIN교체작업(7951,7A51,7B51,7C51)","2020-03-25 09:00","2020-03-27 18:00","취소","취소","연속"]
[125,"충북","직할","신진천S/S #2 M.Tr","신진천S/S 362KV 63KA GIS 용량대체공사-74bay","345kV 차단기 용량대체 3대","2020-03-16 08:00","2020-06-29 18:00","2020-03-17 08:00","2020-06-29 18:00","연속"]
[126,"충북","직할","서안성신진천#1 T/L","신진천S/S 362KV 63KA GIS 용량대체공사-74bay","345kV 차단기 용량대체 3대","2020-03-16 08:00","2020-06-29 18:00","2020-03-17 08:00","2020-06-29 18:00","연속"]
[127,"충북","직할","신진천S/S #4 M.Tr","2020년 충북본부 직할 주변압기 정밀점검공사","신진천S/S 345kV #4M.Tr 정밀점검","2020-03-21 09:30","2020-03-26 18:00","취소","취소","연속"]
[128,"충북","청주","남청주S/S #4 M.Tr","20-21년 청주전력 변전협력회사 총액공사","남청주S/S 345kV #4M.Tr 보통점검 및 362kV GIS 보통점검 등","2020-03-24 09:30","2020-03-26 18:00","2020-03-25 09:30","2020-03-27 18:00","연속"]
[129,"충북","청주","세종남청주#1 T/L","20-21년 청주전력 변전협력회사 총액공사","남청주S/S 345kV 세종남청주#1T/L GIS 초기점검 등","2020-03-09 09:30","2020-03-09 18:00","2020-03-09 09:30","2020-03-09 18:00","연속"]
[130,"충북","청주","신옥천S/S 345KV #75 BUS","20년 청주전력 변전 협력회사 총액공사","신옥천S/S 345kV 모선보호반 교체공사","2020-03-09 09:30","2020-03-12 18:00","2020-03-09 09:30","2020-03-12 18:00","연속"]
[131,"충북","청주","신옥천세종#1 T/L","20-21년 청주전력 변전협력회사 총액공사","신옥천S/S 345kV 71BAY B/F반 대체","2020-03-16 09:30","2020-03-19 18:00","취소","취소","연속"]
[132,"충북","청주","신옥천S/S #1 M.Tr","20-21년 청주전력 변전협력회사 총액공사","신옥천S/S 345kV 71BAY B/F반 대체","2020-03-16 09:30","2020-03-19 18:00","2020-04-01 09:30","2020-04-04 18:00","연속"]
[133,"충북","청주","신옥천북경남 T/L","345kV 신옥천-북경남T/L 전력선 교체공사","345kV 신옥천-북경남T/L 전력선 교체공사 작업내용 - 전력선 교체 No.258~259, No.260~261, No.265~267 - 가공지선 교체 : No.261~263, No.248~253, No,237~238","2020-03-20 08:00","2020-03-26 18:00","2020-03-20 08:00","2020-03-26 18:00","연속"]
[134,"충북","청주","신옥천세종#2 T/L","20-21년 청주전력 변전협력회사 총액공사","신옥천S/S 345kV 72BAY B/F반 대체","2020-03-23 09:30","2020-03-26 18:00","취소","취소","연속"]
[135,"충북","청주","신옥천무주양수 T/L","20-21년 청주전력 변전협력회사 총액공사","신옥천S/S 345kV 73BAY B/F반 대체","2020-03-30 09:30","2020-04-01 18:00","2020-03-27 09:30","2020-03-30 18:00","연속"]
[136,"충북","청주","신옥천S/S 345KV #70 BUS","20년 청주전력 변전 협력회사 총액공사","신옥천S/S 345kV 모선보호반 교체공사","2020-03-02 09:30","2020-03-05 18:00","2020-03-02 09:30","2020-03-05 18:00","연속"]
[137,"충북","충주","곤지암신충주#2 T/L","345kV 곤지암-신충주 등 4개T/L 전력선교체공사","전선접속개소 해소를 위한 전력선교체 - 대상선로 : 345kV 곤지암-신충주 #2T/L - 작업내용 : 전력선 연선, 긴선","2020-03-17 08:00","2020-03-31 18:00","취소","취소","연속"]
[138,"충북","충주","곤지암신충주#1 T/L","345kV 곤지암-신충주 등 4개T/L 전력선교체공사","전선접속개소 해소를 위한 전력선교체 - 대상선로 : 345kV 곤지암-신충주 #1T/L - 작업내용 : 전력선 연선, 긴선","2020-03-02 08:00","2020-03-16 18:00","취소","취소","연속"]
[139,"충북","충주","STATCOM M.Tr 1차 GIS","신충주S/S STATCOM Pump 모터 교체","신충주S/S STATCOM #2Cooling System #APump 모터 신품 교체 - #APump 베어링 교체 임시조치(19.11.06) 후 신품모터 확보 완료","2020-03-02 10:00","2020-03-02 18:00","2020-03-02 10:00","2020-03-02 18:00","연속"]
[140,"대전충남","서산","북당진현대제철T/L","345kV 신송산분기T/L 건설공사","- 해당구간 : No.71 ~ No.69 구간내 No.70 선로 - 공사내용 : No.70 선로 가철탑 이설 전력선 공중이동 ACSR/AW 480SQ x 4B x 2C (0.793km)","2020-03-09 07:00","2020-03-12 18:00","취소","취소","연속"]
[141,"대전충남","서산","신당진개폐소현대제철 T/L","345kV 신송산분기T/L 건설공사","- 해당구간 : No.71 ~ No.69 구간내 No.70 선로 - 공사내용 : No.70 선로 가철탑 이설 전력선 공중이동 ACSR/AW 480SQ x 4B x 2C (0.793km)","2020-03-13 07:00","2020-03-16 18:00","취소","취소","연속"]
[142,"대전충남","서산","신서산S/S 345kV #5 Sh.R","20년 변전정비회사 총액공사","신서산S/S 345kV 79BAY B/F보호반 대체","2020-03-09 09:00","2020-03-13 18:00","2020-03-09 09:00","2020-03-13 18:00","연속"]
[143,"대전충남","서산","신서산신당진#1 T/L","민원구간 OPGW 항공장애표시구 교체공사","항공장애표시구 28개 교체","2020-03-21 09:00","2020-03-22 18:00","취소","취소","매일"]
[144,"대전충남","서산","신당진개폐소태안TP#1 T/L","태안화력 345kV 75B/F반 대체 및 7571 GIS 보통점검","태안화력 345kV 75B/F 및 7571 GIS,LA,CVT 보통점검","2020-03-31 09:00","2020-04-06 18:00","2020-03-31 09:00","2020-04-06 18:00","연속"]
[145,"대전충남","아산","아산S/S #1 M.Tr","아산S/S 345kV 73Bay B/F반 교체","아산S/S 345kV 73Bay B/F반 교체(신서산-아산#2T/L 동시휴전)","2020-03-20 09:00","2020-03-30 18:00","2020-03-20 09:00","2020-03-30 18:00","연속"]
[146,"대전충남","아산","신서산아산#2 T/L","[송전]345kV 신서산-아산 등 2개T/L 지장송전선로 이설공사","가. 철탑 설치 및 철거 : 2기 [No.83(B4-28 → Bb4-36), No.84(F4-29 → F4-39)] 나. 전력선교체 - ACSR 480㎟ x 4B x 2C × 1.778km [No.82~83 1선 교체, No.83~88 24선 교체] - ACSR 410㎟ x 2B x 2C × 1.778km [No.83~88 24선 교체]","2020-03-20 07:00","2020-03-30 18:00","2020-03-20 07:00","2020-03-30 18:00","연속"]
[147,"대전충남","아산","신서산아산#1 T/L","[송전]345kV 신서산-아산 등 2개T/L 지장송전선로 이설공사","가. 철탑 설치 및 철거 : 2기 [No.83(B4-28 → Bb4-36), No.84(F4-29 → F4-39)] 나. 전력선교체 - ACSR 480㎟ x 4B x 2C × 1.778km [No.82~83 1선 교체, No.83~88 24선 교체] - ACSR 410㎟ x 2B x 2C × 1.778km [No.83~88 24선 교체]","2020-03-09 07:00","2020-03-19 18:00","2020-03-09 07:00","2020-03-19 18:00","연속"]
[148,"대전충남","청양","보령C/C 보령연락#1T/L-#1 M.Tr 1차 CB(7100)","보령C/C 345kV 차단기 부동작 예방 조작시험","보령C/C 345kV 차단기 부동작 예방 조작시험 - 보령연락#1T/L-GT1,GT2 CB(7100) 조작시험","2020-03-20 13:00","2020-03-20 18:00","2020-03-20 13:00","2020-03-20 18:00","연속"]
[149,"대전충남","청양","보령C/C #2 M.Tr 1차 CB(7272)","보령C/C 362kV GIS 보통점검","보령C/C 362kV GIS 보통점검 - #2M.Tr(ST1) 1차측 GIS(7272) 보통점검","2020-03-23 09:00","2020-03-23 18:00","2020-03-23 09:00","2020-03-23 18:00","연속"]
[150,"대전충남","청양","신보령TP보령CC T/L","보령복합 345kV신보령연락T/L 보호반 성능개선","보령복합 345kV신보령연락T/L 보호반 성능개선 - 보호반 성능개선(보령복합 측)","2020-03-09 09:00","2020-03-09 18:00","취소","취소","연속"]
[151,"대전충남","청양","보령C/C #1 M.Tr 1차 CB(7172)","보령C/C 345kV 차단기 부동작 예방 조작시험","보령C/C 345kV 차단기 부동작 예방 조작시험 - GT1&GT2 1차측 CB(7172) 조작시험","2020-03-20 09:00","2020-03-20 12:00","2020-03-20 09:00","2020-03-20 12:00","연속"]
[152,"대전충남","청양","청양보령CC T/L","[송전]345kV 청양-보령복합T/L 정밀점검","345kV 청양-보령복합T/L No.1~86 정밀점검","2020-03-16 09:00","2020-03-20 18:00","2020-03-16 09:00","2020-03-20 18:00","매일"]
[153,"대전충남","청양","보령TP보령CC#2 T/L","보령복합 345kV보령연락#2T/L 보호반 성능개선","보령복합 345kV보령연락#2T/L 보호반 성능개선 - 보령복합 7200(보통) - 보호반 성능개선","2020-03-10 09:00","2020-03-10 18:00","취소","취소","연속"]
[154,"대전충남","청양","보령T/P #5 M.Tr 1차 CB(7572)","보령T/P 362kV GIS 초기점검","보령T/P 362kV GIS 초기점검 - #5M.Tr 1차측(7572) 초기점검","2020-03-25 09:00","2020-03-25 18:00","2020-03-25 09:00","2020-03-25 18:00","연속"]
[155,"전북","군산","군산S/S #4 M.Tr","군산P/O 차단기 점검공사","1. 1차 차단기 보통점검, 2. 2차 차단기 조작시험 3. 1, 2차 LA 보통점검","2020-03-12 09:00","2020-03-12 18:00","2020-03-12 09:00","2020-03-12 18:00","연속"]
[156,"전북","군산","군산S/S #3 M.Tr","군산P/O 차단기 점검공사","1. 1, 2차 차단기 조작시험 2. 1차 B상 부싱유채유 3. 2차 LA 보통점검 4. 3차 PT점검","2020-03-13 09:00","2020-03-13 18:00","2020-03-13 09:00","2020-03-13 18:00","연속"]
[157,"전북","군산","군산S/S #2 M.Tr","군산P/O 차단기 점검공사","1. 7472 보통점검 2. 2,3차 차단기 조작시험 3. 1, 2차 A, B, C상 부싱유채유 4. 2차 LA 보통점검 5. 3차 PT점검","2020-03-09 09:00","2020-03-11 18:00","2020-03-09 09:00","2020-03-11 18:00","연속"]
[158,"전북","군산","군산S/S #1 M.Tr","군산P/O 차단기 점검공사","1. 7272 보통점검 2. 2,3차 차단기 조작시험 3. 2차 A, B상 부싱유채유 4. 2차 LA 보통점검 5. 3차 PT점검","2020-03-06 09:00","2020-03-06 18:00","2020-03-06 09:00","2020-03-06 18:00","연속"]
[159,"전북","직할","북경남무주양수 T/L","345kV 신옥천-북경남T/L 전력선 교체공사","345kV 신옥천-북경남T/L 전력선 교체공사 - 전력선교체공사 : No.258~259","2020-03-18 08:00","2020-03-19 18:00","2020-03-18 08:00","2020-03-19 18:00","연속"]
[160,"전북","직할","신남원S/S 345kV #70 BUS","신남원S/S 345kV GIS GAS 누기 보수공사(2차)","- 345kV GIS GAS 누기 관련 보수공사 * 345kV #70BUS GAS 감압","2020-03-31 09:30","2020-04-09 17:00","2020-03-31 09:30","2020-04-09 17:00","연속"]
[161,"전북","직할","신남원의령#1 T/L","신남원S/S 345kV GIS GAS 누기 보수공사(2차)","- 345kV GIS GAS 누기 관련 보수공사(7371) * 차단부 해체/보수/조립","2020-03-31 09:30","2020-04-03 17:00","2020-03-31 09:30","2020-04-03 17:00","연속"]
[162,"전북","직할","신옥천신남원#1 T/L","신남원S/S 345kV GIS GAS 누기 보수공사(2차)","- 345kV GIS GAS 누기 관련 보수공사(7271, 7200) * 차단부 해체/보수/조립","2020-03-09 09:30","2020-03-30 17:00","2020-03-09 09:30","2020-03-30 17:00","연속"]
[163,"전북","직할","신남원S/S 345kV #70 BUS","신남원S/S 345kV GIS GAS 누기 보수공사(2차)","- 345kV GIS GAS 누기 관련 보수공사 * 345kV #70BUS GAS 감압","2020-03-09 09:30","2020-03-30 17:00","2020-03-09 09:30","2020-03-30 17:00","연속"]
[164,"광주전남","강진","신강진광양#2 T/L","신화순-광양#2T/L GIS 초기점검","신화순-광양#2T/L GIS 초기점검 - 신화순-광양#2T/L 인출 LA 설비 개선","2020-03-24 09:00","2020-03-24 18:00","취소","취소","연속"]
[165,"광주전남","강진","신강진광양#1 T/L","신화순-광양#1T/L GIS 초기점검","신화순-광양#1T/L GIS 초기점검 - 신화순-광양#1T/L 인출 LA 설비 개선","2020-03-23 09:00","2020-03-23 18:00","취소","취소","연속"]
[166,"광주전남","강진","신강진S/S #3 M.Tr","신강진S/S 345kV #3M.Tr 1차 GIS 보통점검","신강진S/S 345kV #3M.Tr 1차 GIS 보통점검 - #3M.Tr 및 1, 2, 초기점검 - #3M.Tr 1차 GIS LA Flash Over 현상 설비 개선","2020-03-16 09:00","2020-03-18 18:00","2020-03-04 09:00","2020-03-06 18:00","연속"]
[167,"광주전남","강진","신강진S/S #2M.Tr","신강진S/S 345kV #2M.Tr 1차 GIS 보통점검","신강진S/S 345kV #2M.Tr 1차 GIS 보통점검 - #2M.Tr 1차 GIS LA Flash Over 현상 설비 개선","2020-03-13 09:00","2020-03-13 18:00","2020-03-12 09:00","2020-03-12 18:00","연속"]
[168,"광주전남","강진","신화순신강진#2 T/L","신화순-신강진#2T/L 정밀점검","2020년 가공송전 순시점검 위탁공사 - 345kV 신화순-신강진#2T/L 송전선로 정밀점검","2020-03-12 09:00","2020-03-20 18:00","2020-03-03 09:00","2020-03-03 18:00","연속"]
[169,"광주전남","강진","신강진S/S #1M.Tr","신강진S/S 345kV #1M.Tr 1차 GIS 보통점검","신강진S/S 345kV #1M.Tr 1차 GIS 보통점검 - #1M.Tr 1차 GIS LA Flash Over 현상 설비 개선","2020-03-12 09:00","2020-03-12 18:00","2020-03-09 09:00","2020-03-09 18:00","연속"]
[170,"광주전남","강진","신강진S/S #4 M.Tr","신강진S/S 345kV #4M.Tr 1차 GIS 보통점검","신강진S/S 345kV #4M.Tr 1차 GIS 초기점검 - #4M.Tr 1차 GIS LA Flash Over 현상 설비 개선 - #4M.Tr 2차 GIS, LA, 3차 PT 초기점검","2020-03-10 09:00","2020-03-11 18:00","2020-03-10 09:00","2020-03-11 18:00","연속"]
[171,"광주전남","강진","신화순신강진#1 T/L","신화순-신강진#1T/L 정밀점검","2020년 가공송전 순시점검 위탁공사 - 345kV 신화순-신강진#1T/L 송전선로 정밀점검","2020-03-02 09:00","2020-03-10 18:00","2020-03-02 09:00","2020-03-02 18:00","연속"]
[172,"광주전남","순천","광양여수TP T/L","20~21년 순천전력지사 총액공사(GIS 초기점검)","광양S/S 345kV 광양-여수TPT/L 7471 GIS, LA,CVT 보통점검 여수T/P 345kV 광양-여수TPT/L 7171,7100 GIS 타임 및 절연열화 측정, CVT 초기점검","2020-03-18 09:00","2020-03-19 18:00","취소","취소","연속"]
[173,"광주전남","순천","광양S/S #75-#76 SEC CB","광양S/S 362kV GIS 차단기 용량대체","광양S/S 362kV GIS 차단기 용량대체 -#75-#76 SEC-CB 대체(50kA - 63kA)","2020-03-04 09:00","2020-04-21 18:00","2020-03-04 09:00","2020-04-21 18:00","연속"]
[174,"광주전남","순천","광양S/S #2 M.Tr","20~21년 순천전력지사 총액공사(GIS 초기점검)","광양S/S #2M.Tr 1차 GIS 7272 초기점검","2020-03-17 09:00","2020-03-17 18:00","취소","취소","연속"]
[175,"광주전남","순천","광양율촌CC T/L","20~21년 순천전력지사 변전총액공사(GIS 하자점검)","광양S/S 광양-율촌CCT/L 7371,7300 GIS, LA(A,B,C)상 하자점검 율촌CC 광양-율촌CCT/L 7171, 7100 GIS 타임및 절연열화 측정","2020-03-10 09:00","2020-03-12 18:00","취소","취소","연속"]
[176,"광주전남","순천","광양S/S 345kV #75 BUS","광양S/S 362kV GIS 차단기 용량대체","광양S/S 362kV GIS 차단기 용량대체 -#75BUS 모선대체(50kA - 63kA)","2020-03-04 09:00","2020-04-21 18:00","2020-03-04 09:00","2020-04-21 18:00","연속"]
[177,"광주전남","순천","광양S/S 345kV #76 BUS","광양S/S 362kV GIS 차단기 용량대체","광양S/S 362kV GIS 차단기 용량대체 -#76BUS 모선대체(50kA - 63kA)","2020-03-04 09:00","2020-04-21 18:00","2020-03-04 09:00","2020-04-21 18:00","연속"]
[178,"광주전남","순천","광양S/S #3 M.Tr","광양S/S 362kV GIS 차단기 용량대체","광양S/S 362kV GIS 차단기 용량대체 -#75-#76 SEC-CB 대체(50kA - 63kA)작업구간 근접휴전","2020-03-02 09:00","2020-04-23 18:00","2020-03-02 09:00","2020-04-23 18:00","연속"]
[179,"광주전남","순천","율촌CC 여수TP T/L","345kV 율촌CC-여수TP T/L 정밀점검","20년 가공송전 순시점검 위탁공사 정밀점검","2020-03-02 08:00","2020-03-02 18:00","2020-03-02 08:00","2020-03-02 18:00","연속"]
[180,"대구","달성","북경남대구#1 T/L","대구S/S 북경남-대구#1T/L관련 GIS 보통점검","대구S/S 북경남-대구#1T/L, 북경남-대구#1T/L TIE GIS 보통점검","2020-03-25 09:00","2020-03-25 18:00","취소","취소"]
[181,"대구","칠곡","북대구S/S 북대구-서대구#2T/L CB(7371)","북대구S/S 345kV 북대구-서대구#2T/L GIS 보통점검","북대구S/S 345kV 북대구-서대구#2T/L GIS 보통점검","2020-03-12 09:00","2020-03-12 18:00","취소","취소"]
[182,"대구","칠곡","북대구S/S 345kV #1 Sh.R","북대구S/S 345kV #1Sh.R 1차 7671,7679GIS 하자점검","북대구S/S 345kV #1Sh.R 1차 7671,7679GIS 하자점검","2020-03-13 09:00","2020-03-13 18:00","취소","취소"]
[183,"대구","칠곡","북대구S/S TIE-북대구-선산T/L CB(7200)","북대구S/S 345kV 7200GIS 장기미동작 점검","북대구S/S 345kV 7200GIS 장기미동작 점검","2020-03-31 15:00","2020-03-31 18:00","취소","취소"]
[184,"대구","칠곡","북대구S/S #3 M.Tr","북대구S/S 345kV 7600,7672 GIS 하자점검","북대구S/S 345kV 7600,7672 GIS 하자점검","2020-03-05 09:00","2020-03-05 18:00","2020-03-05 09:00","2020-03-05 18:00","연속"]
[185,"대구","칠곡","북대구S/S 북대구-선산T/L CB(7272)","북대구S/S 345kV 북대구-선산T/L 7272GIS 장기미동작 점검","북대구S/S 345kV 북대구-선산T/L 7272GIS 장기미동작 점검","2020-03-19 09:00","2020-03-19 14:00","2020-03-19 09:00","2020-03-19 14:00","연속"]
[186,"대구","칠곡","북대구S/S 북대구-서대구#1T/L CB(7471)","북대구S/S 345kV 북대구-서대구#1T/L 7471GIS 장기미동작","북대구S/S 345kV 북대구-서대구#1T/L 7471GIS 장기미동작","2020-03-19 14:00","2020-03-19 18:00","2020-03-19 14:00","2020-03-19 18:00","연속"]
[187,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","T-BUS 및 8DS 철거","2020-03-10 09:00","2020-03-10 18:00","취소","취소"]
[188,"대구","칠곡","서대구S/S #2 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","T-BUS 및 8DS 철거","2020-03-11 09:00","2020-03-11 18:00","취소","취소"]
[189,"대구","칠곡","서대구S/S #3 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","T-BUS 및 8DS 철거","2020-03-12 09:00","2020-03-12 18:00","2020-03-30 08:00","2020-03-30 18:00","연속"]
[190,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","T-BUS 및 8DS 철거","2020-03-13 09:00","2020-03-13 18:00","2020-03-23 08:00","2020-03-24 18:00","연속"]
[191,"대구","포항","신포항신영일 T/L","신포항-신영일TL 송전선로 보호반 대체작업","신포항-신영일TL 송전선로 보호반 대체작업","2020-03-16 09:00","2020-03-20 18:00","2020-03-16 09:00","2020-03-20 18:00","연속"]
[192,"대구","포항","신포항S/S #2 M.Tr","신포항 #2M.Tr 보통점검","신포항 #2M.Tr , 2,3차 LA , 4279 VCB, #2S.Tr 보통점검 7671,7672, 6244 조작시험 접지개소 : #2M.Tr 1,2,3차 LA, 7671,7672,6244,4279 차단기 양단","2020-03-23 09:00","2020-03-24 18:00","2020-03-23 09:00","2020-03-24 18:00","연속"]
[193,"대구","포항","신포항북대구 T/L","345kV 신포항-북대구T/L 전력선교체공사","345kV 신포항-북대구T/L 전력선교체공사 공사구간 : 345kV 신포항-북대구T/L No.202~205, 208~219, 265~272 전력선교체 : ACSR 480㎟*4B*2C, 14.645C_km 가공지선교체 : ACSR 120㎟ 7.623C_km","2020-03-23 08:00","2020-04-06 18:00","취소","취소","연속"]
[194,"대구","포항","울주월성NP#2 T/L","'20-21 포항전력지사 가공송전 정비회사 총액공사","345kV울주-월성NP#2 T/L 전력선 소도체 이도조정","2020-03-23 08:00","2020-03-27 18:00","2020-03-23 08:00","2020-03-27 18:00","연속"]
[195,"경북","영주","신제천신영주#1 T/L","345kV 신제천-신영주T/L 전선접속개소 전선교체공사","○ 공사구간 : 345kV 신제천-신영주T/L No. 167-172, 181-191 ○ 전력선교체 : ACSR 480mm² ×4B 11.564C-km","2020-03-30 09:00","2020-04-07 18:00","취소","취소","연속"]
[196,"경북","직할","안동C/C #2 Tie-Tr","20~21년 경북본부 직할 변전정비회사 총액공사","하자점검, 2차 GIS, 3차 SIS 하자점검","2020-03-26 09:00","2020-03-27 18:00","2020-03-26 09:00","2020-03-27 18:00","연속"]
[197,"경북","직할","안동복합S/S 신영주-안동CC T/L-#2 M.Tr 1차 TIE GIS(7200)","20~21년 경북본부 직할 변전정비회사 총액공사","하자점검","2020-03-25 14:00","2020-03-25 19:00","2020-03-25 14:00","2020-03-25 19:00","연속"]
[198,"경북","직할","안동복합S/S #2 M.Tr 1차 GIS(7272)","20~21년 경북본부 직할 변전정비회사 총액공사","하자점검","2020-03-25 08:00","2020-03-25 14:00","2020-03-25 08:00","2020-03-25 14:00","연속"]
[199,"경북","직할","청송P/P 신영주-청송PP T/L-#1 M.Tr 2차 TIE GIS(7100)","20~21년 경북본부 직할 변전정비회사 총액공사","보통점검","2020-03-24 09:00","2020-03-24 18:00","2020-03-24 09:00","2020-03-24 18:00","연속"]
[200,"경북","직할","청송P/P 신영주-청송PP T/L GIS(7171)","20~21년 경북본부 직할 변전정비회사 총액공사","보통점검","2020-03-23 09:00","2020-03-23 18:00","2020-03-23 09:00","2020-03-23 18:00","연속"]
[201,"경북","직할","신영주청송PP T/L","345kV 영포T/L 전선접속개소 전선교체공사","ㅇ전력선교체:ACSR480*4B*2C 철거 및 설치(7.449C-km) ㅇ가공지선교체:ACSR120 철거 및 설치(5.221C-km)","2020-03-21 09:00","2020-03-29 18:00","2020-03-23 09:00","2020-03-31 18:00","연속"]
[202,"부산울산","동부산","고리NP S/Y 신양산-고리#2T/L CB(7A71)","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선공사(7A71)","2020-03-02 09:30","2020-03-07 18:00","취소","취소","연속"]
[203,"부산울산","동부산","고리NP S/Y 신고리-고리#2T/L-TIE CB(7F00)","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선공사(7F00)","2020-03-30 09:30","2020-04-04 18:00","2020-04-06 09:30","2020-04-11 18:00","연속"]
[204,"부산울산","동부산","고리NP S/Y 신고리-고리#2T/L CB(7F71)","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선공사(7F71)","2020-03-23 09:30","2020-03-28 18:00","2020-03-30 09:30","2020-04-04 18:00","연속"]
[205,"부산울산","동부산","고리NP S/Y 신고리-고리#3T/L CB(7A72)","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선공사(7A72)","2020-03-16 09:30","2020-03-21 18:00","2020-03-23 09:30","2020-03-28 18:00","연속"]
[206,"부산울산","동부산","고리NP S/Y 신양산-고리#2T/L-신고리-고리#3T/L TIE CB(7A00)","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선공사(7A00)","2020-03-09 09:30","2020-03-14 18:00","취소","취소","연속"]
[207,"부산울산","동부산","신양산신대연#1 T/L","'20-21년 송전정비회사 총액공사","154kV 신양산-기장#2T/L 애자교체관련 안전이격확보","2020-03-24 08:00","2020-03-24 18:00","2020-03-24 08:00","2020-03-24 18:00","연속"]
[208,"부산울산","동부산","신양산고리NP#2 T/L","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(7A00)","2020-03-13 18:00","2020-03-14 18:00","취소","취소","연속"]
[209,"부산울산","동부산","신양산신대연#2 T/L","[3차] 345kV 신양산S/S 현대화공사","1. 내용 - 신양산-신대연#2T/L 제어케이블 이설 - 345kV #1M.Tr 및 1,2,3차 제어케이블 이설 - 345kV #1M.Tr 2차 인출변경 - 154kV #61M.Tr 1차 인출변경 2. 배전선로 이설 - 8개D/L 이설","2020-03-30 09:00","2020-04-13 18:00","2020-04-16 09:00","2020-04-29 18:00","연속"]
[210,"부산울산","동부산","신양산고리NP#2 T/L","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(7A71)","2020-03-06 18:00","2020-03-07 18:00","취소","취소","연속"]
[211,"부산울산","동부산","신양산S/S #1 M.Tr","[3차] 345kV 신양산S/S 현대화공사","1. 내용 - 신양산-신대연#2T/L 제어케이블 이설 - 345kV #1M.Tr 및 1,2,3차 제어케이블 이설 - 345kV #1M.Tr 2차 인출변경 - 154kV #61M.Tr 1차 인출변경 2. 배전선로 이설 - 8개D/L 이설","2020-03-30 09:00","2020-04-13 18:00","2020-04-16 09:00","2020-04-29 18:00","연속"]
[212,"부산울산","북부산","북부산S/S #3 M.Tr","북부산S/S 345kV #3M.Tr 누유 보수 공사","북부산S/S 345kV #3M.Tr 누유 보수 공사","2020-03-02 10:00","2020-03-02 18:00","2020-03-02 10:00","2020-03-02 18:00","연속"]
[213,"부산울산","북부산","북부산S/S #4 M.Tr","2020년 북부산 변전협력회사 총액공사","북부산S/S 345kV 1차측 7800,7872 GIS 하자점검","2020-03-18 10:00","2020-03-19 18:00","2020-03-18 10:00","2020-03-19 18:00","연속"]
[214,"부산울산","북부산","북부산S/S 서부산-북부산#3T/L CB((신)7871)","2020년 북부산 변전협력회사 총액공사","북부산S/S 345kV 서부산-북부산#3/TL 7871 단독 GIS 하자점검","2020-03-20 10:00","2020-03-20 18:00","2020-03-20 10:00","2020-03-20 18:00","연속"]
[215,"부산울산","북부산","북부산S/S 345kV #4 Sh.R","2020년 북부산 변전협력회사 총액공사","북부산S/S 345kV 4Sh.R 1차 7900,7972,7A77GIS 하자점검","2020-03-24 10:00","2020-03-25 18:00","취소","취소","연속"]
[216,"부산울산","북부산","북부산S/S #4 Sh.R 1차 선로측 CB(7A77)","2020년 북부산 변전협력회사 총액공사","북부산S/S 345kV 4Sh.R 1차 7900,7972,7A77GIS 하자점검","2020-03-24 10:00","2020-03-25 18:00","취소","취소","연속"]
[217,"부산울산","북부산","북부산S/S #4 Sh.R 1차 CB((신)7972)","2020년 북부산 변전협력회사 총액공사","북부산S/S 345kV 4Sh.R 1차 7900,7972,7A77GIS 하자점검","2020-03-24 10:00","2020-03-25 18:00","취소","취소","연속"]
[218,"부산울산","서부산","서부산S/S 345kV #1 Sh.R","서부산S/S 345kV #1Sh.R 수냉각 PNL 대체","서부산S/S 345kV #1Sh.R 수냉각 PNL 대체","2020-03-23 10:00","2020-03-29 18:00","취소","취소","연속"]
[219,"부산울산","울산","동울산신울산#1 T/L","345kV 동울산-신울산T/L 철탑보강공사","ㅇ대상철탑 : 78,79,80,81,97,98","2020-03-09 07:00","2020-03-10 18:00","취소","취소","연속"]
[220,"부산울산","울산","동울산신울산#2 T/L","345kV 동울산-신울산T/L 철탑보강공사","ㅇ대상철탑 : 78,79,80,81,97,98","2020-03-11 07:00","2020-03-12 18:00","취소","취소","연속"]
[221,"부산울산","울산","신온산S/S S-OIL#5T/L CB(7172)","20~21년 변전협력 총액공사","- 신온산S/S 345kV S-OIL#5T/L 7172GIS 하자점검","2020-03-06 09:00","2020-03-06 18:00","2020-03-06 09:00","2020-03-06 18:00","연속"]
[222,"부산울산","울산","신온산S/S S-OIL#6T/L-#3 M.Tr 1차 TIE CB(7500)","20~21년 변전협력 총액공사","- 신온산S/S 345kV #3M.Tr-S-OIL#6T/L TIE 7500차단기 보통점검","2020-03-23 09:00","2020-03-23 18:00","2020-03-23 09:00","2020-03-23 18:00","연속"]
[223,"부산울산","울산","신온산S/S 신온산T/L-TIE CB(7300)","20~21년 변전협력 총액공사","- 신온산S/S 345kV 신온산T/L-TIE 7300 차단기 보통점검","2020-03-24 09:00","2020-03-24 18:00","2020-03-24 09:00","2020-03-24 18:00","연속"]
[224,"부산울산","울산","신온산S/S #2 M.Tr 1차 CB(7472)","20~21년 변전협력 총액공사","- 신온산S/S 345kV #2M.Tr 1차 7472차단기 보통점검","2020-03-17 09:00","2020-03-17 18:00","2020-03-17 09:00","2020-03-17 18:00","연속"]
[225,"부산울산","울산","신온산S/S #1 M.Tr 1차 CB(7272)","20~21년 변전협력 총액공사","- 신온산S/S 345kV #1M.Tr 1차 7272차단기 보통점검","2020-03-19 09:00","2020-03-19 18:00","2020-03-19 09:00","2020-03-19 18:00","연속"]
[226,"부산울산","울산","신온산S/S 북부산-신온산T/L CB(7371)","20~21년 변전협력 총액공사","- 신온산S/S 345kV 북부산-신온산T/L 7371 차단기 보통점검","2020-03-26 09:00","2020-03-26 18:00","2020-03-26 09:00","2020-03-26 18:00","연속"]
[227,"부산울산","울산","신온산S/S 신울산#1T/L-#1 M.Tr 1차 TIE CB(7200)","20~21년 변전협력 총액공사","- 신온산S/S 345kV 신울산#1T/L-#1 M.Tr 1차 TIE 7200 차단기 보통점검","2020-03-27 09:00","2020-03-27 18:00","2020-03-27 09:00","2020-03-27 18:00","연속"]
[228,"부산울산","울산","신온산S/S 신온산-울산TPT/L CB(7471)","20~21년 변전협력 총액공사","- 신온산S/S 345kV 신온산-울산TPT/L 7471 차단기 보통점검","2020-03-25 09:00","2020-03-25 18:00","2020-03-25 09:00","2020-03-25 18:00","연속"]
[229,"부산울산","울산","신온산S/S S-OIL#6T/L CB(7571)","20~21년 변전협력 총액공사","- 신온산S/S 345kV S-OIL#6T/L 7571GIS 하자점검","2020-03-04 09:00","2020-03-04 18:00","2020-03-04 09:00","2020-03-04 18:00","연속"]
[230,"부산울산","울산","울주S/S #2 M.Tr","20~21년 변전협력 총액공사","- M.Tr 하자점검 - M.Tr 1차 차단기(7472, 7400)GIS 하자점검 - M.Tr 2차 차단기(6244)GIS 하자점검 - 1, 2차 피뢰기 보통점검","2020-03-16 09:00","2020-03-17 18:00","2020-03-16 09:00","2020-03-17 18:00","연속"]
[231,"경남","직할","신김해S/S #1 M.Tr","신김해S/S 345kV #1M.Tr 보통점검","신김해S/S 345kV #1M.Tr 보통점검 신김해S/S 345kV #1M.Tr 1차 CB(7372) 보통점검 신김해S/S 345kV #73BAY TIE CB(7300) 보통점검 신김해S/S 345kV #1M.Tr 1, 2, 3차 LA 보통점검","2020-03-09 09:30","2020-03-11 17:30","2020-03-09 09:30","2020-03-11 17:30","연속"]
[232,"경남","직할","창원삼천포TP#1 T/L","2020년도 가공송전 순시점검 위탁공사","송전선로 정밀점검(345kV 창원-삼천포화력#1T/L 103~189호)","2020-03-16 08:00","2020-03-20 18:00","2020-03-16 08:00","2020-03-20 18:00","매일"]
[233,"경남","직할","신김해창원#1 T/L","2020년도 가공송전 순시점검 위탁공사","송전선로 정밀점검(345kV 신김해-창원#1T/L 1~53호)","2020-03-21 08:00","2020-03-23 18:00","2020-03-21 08:00","2020-03-23 18:00","매일"]
[234,"경남","직할","창원삼천포TP#2 T/L","2020년도 가공송전 순시점검 위탁공사","송전선로 정밀점검(345kV 창원-삼천포화력#2T/L 103~189호)","2020-03-23 08:00","2020-03-29 18:00","2020-03-23 08:00","2020-03-29 18:00","매일"]
[235,"경남","직할","신김해창원#2 T/L","2020년도 가공송전 순시점검 위탁공사","송전선로 정밀점검(345kV 신김해-창원#2T/L 1~53호)","2020-03-12 08:00","2020-03-16 18:00","2020-03-12 08:00","2020-03-16 18:00","매일"]
[236,"경남","직할","창원S/S #3 M.Tr","창원S/S 345kV #3M.Tr 1차 CB(7372) 하자점검","창원S/S 345kV #3M.Tr 1차 CB(7372) 하자점검 창원S/S 345kV #3M.Tr 2차 CB(6344) 하자점검 창원S/S 345kV #73BAY TIE CB(7300) 조작시험","2020-03-05 09:30","2020-03-05 17:30","2020-03-05 09:30","2020-03-05 17:30","연속"]
[237,"경남","진주","의령S/S #70-#71 SEC CB","의령S/S 345kV SEC B/F PNL 대체공사","의령S/S 345kV SEC B/F PNL 대체공사","2020-03-23 09:00","2020-03-27 18:00","2020-03-09 09:00","2020-03-13 18:00","연속"]
[238,"경남","진주","의령S/S #75-#76 SEC CB","의령S/S 345kV SEC B/F PNL 대체공사","의령S/S 345kV SEC B/F PNL 대체공사","2020-03-23 09:00","2020-03-27 18:00","2020-03-09 09:00","2020-03-13 18:00","연속"]
[239,"경남","진주","의령S/S 예비 M.Tr CB","의령S/S 345kV 예비 M.Tr 보통점검","의령S/S 345kV 예비 M.Tr 보통점검","2020-03-16 10:00","2020-03-16 17:00","취소","취소","연속"]
[240,"경남","진주","하동T/P #70-#71 SEC CB","하동T/P 345kV 70-71-0 SEC CB 조작시험","하동T/P 345kV 70-71-0 SEC CB 조작시험","2020-03-20 10:00","2020-03-20 14:00","2020-03-20 10:00","2020-03-20 14:00","연속"]
[241,"경남","진주","하동T/P #75-#76 SEC CB","하동T/P 345kV 75-76-0 SEC CB 조작시험","하동T/P 345kV 75-76-0 SEC CB 조작시험","2020-03-20 14:00","2020-03-20 17:00","2020-03-20 14:00","2020-03-20 17:00","연속"]
[242,"경남","진주","하동T/P #8 M.Tr 1차 TIE CB(7800)","하동T/P 345kV TIE-#8M.Tr 1차 CB(7800) 보통점검","하동T/P 345kV TIE-#8M.Tr 1차 CB(7800) 보통점검","2020-03-26 10:00","2020-03-26 17:00","2020-03-26 10:00","2020-03-26 17:00","연속"]
[243,"경남","진주","하동T/P #8 M.Tr 1차 CB(7872)","하동T/P 345kV #8M.Tr 1차 CB(7872) 보통점검","하동T/P 345kV #8M.Tr 1차 CB(7872) 보통점검","2020-03-27 10:00","2020-03-27 17:00","2020-03-27 10:00","2020-03-27 17:00","연속"]
[244,"경남","진주","하동T/P #7 M.Tr 1차 CB(7772)","하동T/P 345kV #7M.Tr 1차 CB(7772) 보통점검","하동T/P 345kV #7M.Tr 1차 CB(7772) 보통점검","2020-03-10 10:00","2020-03-10 17:00","2020-03-25 10:00","2020-03-25 17:00","연속"]
[245,"경남","진주","하동T/P #7 M.Tr 1차 TIE CB(7700)","하동T/P 345kV TIE-#7M.Tr 1차 CB(7700) 보통점검","하동T/P 345kV TIE-#7M.Tr 1차 CB(7700) 보통점검","2020-03-09 10:00","2020-03-09 17:00","2020-03-18 10:00","2020-03-18 17:00","연속"]
[246,"경남","통영","(신)삼천포T/P #1 G.Tr 1차 CB((신)7171)","신고성S/S 345kV #1GEN 1차 차단기 하자점검","신고성S/S 345kV #1GEN 1차 차단기 하자점검","2020-03-16 09:30","2020-03-18 18:00","2020-03-16 09:30","2020-03-18 18:00","연속"]
[247,"경남","통영","(신)신고성S/S 345kV #6 G.Tr 1차 CB(7671)","신신고성S/S 7671 GIS 초기점검","신신고성S/S 7671 GIS 초기점검","2020-03-16 09:30","2020-03-18 18:00","2020-03-16 09:30","2020-03-18 18:00","연속"]
[248,"경남","통영","(신)삼천포T/P 345kV #4 M.Tr 1차-#6 G.Tr 1차 TIE CB(7600)","신신고성S/S 7600 GIS 초기점검","신신고성S/S 7600 GIS 초기점검","2020-03-11 09:30","2020-03-12 18:00","2020-03-11 09:30","2020-03-12 18:00","연속"]
[249,"경남","통영","신고성S/S #1 M.Tr","신고성S/S 345kV #3M.Tr 1차 차단기 하자점검","신고성S/S 345kV #3M.Tr 1차 차단기 하자점검","2020-03-09 09:30","2020-03-11 18:00","2020-03-09 09:30","2020-03-11 18:00","연속"]
[250,"경남","통영","(신)삼천포T/P 345kV #3 G.Tr 1차-#5 G.Tr 1차 TIE CB(7500)","신신고성S/S 7500 GIS 초기점검","신신고성S/S 7500 GIS 초기점검","2020-03-09 09:30","2020-03-10 18:00","2020-03-09 09:30","2020-03-10 18:00","연속"]
[251,"경남","통영","(신)신고성S/S 345kV #5 G.Tr 1차 CB(7571)","신신고성S/S 7571 GIS 초기점검","신신고성S/S 7571 GIS 초기점검","2020-03-09 09:30","2020-03-10 18:00","2020-03-09 09:30","2020-03-10 18:00","연속"]
[252,"광주전남",null,"한빛5호기 주변압기 CB(7D00,7D71)","주변압기 및 소내보조변압기 일반점검 등","주변압기 및 소내보조변압기 일반점검 등","2020-03-27 09:00","2020-04-22 18:00","2020-03-27 09:00","2020-04-22 18:00","연속"]
[253,"부산울산",null,"고리2호기 주변압기 CB(7300,7372)","주변압기 일반점검 등","주변압기 일반점검 등","2020-03-31 09:00","2020-04-13 18:00","2020-03-31 09:00","2020-04-13 18:00","연속"]
[254,"대전충남",null,"2호기 주변압기","2호기 주변압기 점검","2호기 주변압기 점검","2020-03-06","2020-05-15T18:00:00","2020-03-06","2020-05-15T18:00:00","연속"]
[255,"대전충남",null,"청양-신보령화력T/L","신보령 GIS 보통점검","신보령 GIS 보통점검 실시","2020-03-09T09:00:00","2020-03-13T18:00:00","2020-03-09T09:00:00","2020-03-13T18:00:00","연속"]

{"sheet":"154송부","index":3,"n_rows":436,"n_cols":13,"rows_kept":436,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2020년도 \"&종합!R15&\"월 휴전계획서\"","v":"2020년도 3월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","수색상암#1 T/L","2020년 중부P/O 170kV GIS 정밀점검(19년 이월분)","상암S/S #3M.Tr 시험가압용","2020-03-26 17:00","2020-03-26 18:00","2020-03-11 17:00","2020-03-11 18:00","연속"]
[2,"서울","중부","수색상암#1 T/L","2020년 중부P/O 170kV GIS 정밀점검(19년 이월분)","수색S/S 수색상암#1T/L GCB 정밀점검","2020-03-30 09:00","2020-04-01 18:00","취소","취소","연속"]
[3,"서울","중부","중부당인리#2 T/L","20년 중부전력지사 변전정비회사 총액공사","ㅇ 중부S/S 중부당인리#2T/L GIS 보통점검","2020-03-27 09:00","2020-03-27 18:00","2020-03-27 09:00","2020-03-27 18:00","연속"]
[4,"서울","중부","중부용산#1 T/L","20년 중부전력지사 변전정비회사 총액공사","ㅇ 중부S/S 중부용산#1T/L GIS 보통점검","2020-03-23 09:00","2020-03-23 18:00","2020-03-23 09:00","2020-03-23 18:00","연속"]
[5,"서울","중부","중부용산#2 T/L","20년 중부전력지사 변전정비회사 총액공사","ㅇ 중부S/S 중부용산#2T/L GIS 보통점검","2020-03-24 09:00","2020-03-24 18:00","2020-03-24 09:00","2020-03-24 18:00","연속"]
[6,"서울","중부","중부아현 T/L","20년 중부전력지사 변전정비회사 총액공사","ㅇ 중부S/S 중부아현T/L GIS 보통점검","2020-03-25 09:00","2020-03-25 18:00","2020-03-25 09:00","2020-03-25 18:00","연속"]
[7,"서울","중부","중부당인리#1 T/L","20년 중부전력지사 변전정비회사 총액공사","ㅇ 중부S/S 중부당인리#1T/L GIS 보통점검","2020-03-26 09:00","2020-03-26 18:00","2020-03-26 09:00","2020-03-26 18:00","연속"]
[8,"서울","직할","서소문S/S 154kV #60-#65 BUS TIE CB","20-21년 직할 변전정비회사 총액공사","GIS조작시험","2020-03-05 10:00","2020-03-05 18:00","2020-03-05 10:00","2020-03-05 18:00","연속"]
[9,"서울","직할","신촌순화 T/L","20-21년 직할 변전정비회사 총액공사","GIS조작시험","2020-03-06 10:00","2020-03-06 18:00","2020-03-06 10:00","2020-03-06 18:00","연속"]
[10,"서울","직할","운니원남#1 T/L","20-21년 직할 변전정비회사 총액공사","GIS조작시험,전자변교체","2020-03-12 10:00","2020-03-13 18:00","2020-03-12 10:00","2020-03-13 18:00","연속"]
[11,"서울","직할","옥인운니#1 T/L","20-21년 직할 변전정비회사 총액공사","GIS조작시험,전자변교체","2020-03-11 10:00","2020-03-11 18:00","2020-03-11 10:00","2020-03-11 18:00","연속"]
[12,"서울","직할","옥인운니#2 T/L","20-21년 직할 변전정비회사 총액공사","GIS조작시험","2020-03-11 10:00","2020-03-11 18:00","2020-03-11 10:00","2020-03-11 18:00","연속"]
[13,"서울","직할","운니원남#2 T/L","20-21년 직할 변전정비회사 총액공사","GIS조작시험,전자변교체","2020-03-12 10:00","2020-03-13 18:00","2020-03-12 10:00","2020-03-13 18:00","연속"]
[14,"남서울","강남","논일S/S 154kV #65 BUS","154kV 논일E/C #3M.Tr용 GIS 설치공사","154kV GIS 1CCT 설치","2020-03-30 10:00","2020-04-03 18:00","취소","취소","연속"]
[15,"남서울","강남","신양재S/S 154kV 신양재-신사#2T/L GIS","170kV GIS 개폐타임측정-변전협력","신양재S/S 신양재-신사#2T/L GIS 개폐타임측정, 누기보수 신사S/S 신양재-신사#2T/L GIS 개폐타임측정","2020-03-04 09:00","2020-03-04 18:00","2020-03-04 09:00","2020-03-04 18:00","연속"]
[16,"남서울","강남","신양재S/S 154kV 신양재-역삼#3T/L GIS","170kV GIS 개폐타임측정-변전협력","170kV 신양재-역삼#3T/L GIS 개폐타임측정(신양재S/S)","2020-03-10 09:00","2020-03-10 14:00","2020-03-10 09:00","2020-03-10 14:00","연속"]
[17,"남서울","강남","신양재S/S 154kV 신양재-역삼#2T/L GIS","170kV GIS 개폐타임측정-변전협력","170kV 신양재-역삼#2T/L GIS 개폐타임측정(신양재S/S)","2020-03-09 14:00","2020-03-09 18:00","2020-03-09 14:00","2020-03-09 18:00","연속"]
[18,"남서울","강남","신양재S/S 154kV 신양재-역삼#1T/L GIS","170kV GIS 개폐타임측정-변전협력","170kV 신양재-역삼#1T/L GIS 개폐타임측정(신양재S/S)","2020-03-09 09:00","2020-03-09 14:00","2020-03-09 09:00","2020-03-09 14:00","연속"]
[19,"남서울","동서울","잠실강남#1 T/L","170kV GIS 경보회로 로직변경","170kV GIS 경보회로 로직변경","2020-03-19 09:00","2020-03-19 14:00","2020-03-19 09:00","2020-03-19 14:00","연속"]
[20,"남서울","동서울","강남선릉#2 T/L","170kV GIS 보통점검, 전자변교체 및 경보회로 로직변경","강남 : 경보회로 로직변경 선릉 : 보통점검 및 전자변교체","2020-03-18 09:00","2020-03-18 18:00","2020-03-18 09:00","2020-03-18 18:00","연속"]
[21,"남서울","동서울","강남선릉#1 T/L","170kV GIS 보통점검, 전자변교체 및 경보회로 로직변경","강남 : 경보회로 로직변경 선릉 : 보통점검 및 전자변교체","2020-03-17 09:00","2020-03-17 18:00","2020-03-17 09:00","2020-03-17 18:00","연속"]
[22,"남서울","동서울","잠실강남#2 T/L","170kV GIS 경보회로 로직변경","170kV GIS 경보회로 로직변경","2020-03-19 14:00","2020-03-19 18:00","2020-03-19 14:00","2020-03-19 18:00","연속"]
[23,"남서울","동서울","강동천호#2 T/L","170kV GIS 보통점검 및 전자변교체","170kV GIS 보통점검 및 전자변교체","2020-03-04 09:00","2020-03-04 18:00","취소","취소","연속"]
[24,"남서울","동서울","강동천호#1 T/L","170kV GIS 보통점검 및 전자변교체","170kV GIS 보통점검 및 전자변교체","2020-03-03 09:00","2020-03-03 18:00","취소","취소","연속"]
[25,"남서울","동서울","강동풍납#2 T/L","170kV GIS 하자점검","170kV GIS 하자점검","2020-03-02 14:00","2020-03-02 18:00","2020-03-02 14:00","2020-03-02 18:00","연속"]
[26,"남서울","동서울","강동풍납#1 T/L","170kV GIS 하자점검","170kV GIS 하자점검","2020-03-02 09:00","2020-03-02 14:00","2020-03-02 09:00","2020-03-02 14:00","연속"]
[27,"남서울","동서울","염곡개포#2 T/L","154kv염곡-개포T/L 지장이설","염곡-개포T/L 지장이설 1. 구 간 및 선종 : M/H#4~#5 약 450m (OF2000) 2회선 2. 공사기간 (케이블) 20년 03월 ~ 20년 06월 3. 이설 비용 : 서초구청 4. 시공업체 : LS전선 5. 특이사항 : 기존 관로경과지에 전력구 신설","2020-03-23 09:00","2020-05-08 18:00","2020-03-23 09:00","2020-05-08 18:00","연속"]
[28,"남서울","동서울","산성수서#2 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2020-03-05 14:00","2020-03-05 18:00","2020-03-05 14:00","2020-03-05 18:00","연속"]
[29,"남서울","동서울","가락수서#1 T/L","170kV GIS 보통점검 및 전자변교체","170kV GIS 보통점검 및 전자변교체","2020-03-06 09:00","2020-03-06 18:00","2020-03-06 09:00","2020-03-06 18:00","연속"]
[30,"남서울","동서울","가락수서#2 T/L","170kV GIS 보통점검 및 전자변교체","170kV GIS 보통점검 및 전자변교체","2020-03-09 09:00","2020-03-09 18:00","2020-03-09 09:00","2020-03-09 18:00","연속"]
[31,"남서울","동서울","산성수서#1 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2020-03-05 09:00","2020-03-05 14:00","2020-03-05 09:00","2020-03-05 14:00","연속"]
[32,"남서울","영등포","목동S/S 154kV 오류-목동T/L CB","목동S/S 오류-목동T/L 전자변 교체","공압식 차단기 지연동작 방지대책 전자변 교체","2020-03-20 09:00","2020-03-20 18:00","2020-03-20 09:00","2020-03-20 18:00","연속"]
[33,"남서울","영등포","목동S/S 154kV 영등포-목동#1T/L CB","목동S/S 영등포-목동#1T/L 전자변 교체","공압식 차단기 지연동작 방지대책 전자변 교체","2020-03-20 09:00","2020-03-20 18:00","2020-03-20 09:00","2020-03-20 18:00","연속"]
[34,"남서울","영등포","신광명시흥#2 T/L","신광명S/S 신광명-시흥#2T/L 하자점검","SO2 및 수분 측정 차단기 동작시간 측정 경보시험 및 조작시험","2020-03-19 09:00","2020-03-19 18:00","2020-03-21 14:00","2020-03-21 18:00","연속"]
[35,"남서울","영등포","신광명시흥#1 T/L","신광명S/S 신광명-시흥#1T/L 하자점검","SO2 및 수분 측정 차단기 동작시간 측정 경보시험 및 조작시험","2020-03-18 09:00","2020-03-18 18:00","2020-03-21 09:00","2020-03-21 14:00","연속"]
[36,"남서울","영등포","신광명광명#1 T/L","신광명S/S 신광명-광명#1T/L 하자점검","SO2 및 수분 측정 차단기 동작시간 측정 경보시험 및 조작시험","2020-03-20 09:00","2020-03-20 18:00","2020-03-14 09:00","2020-03-14 14:00","연속"]
[37,"남서울","영등포","신광명광명#2 T/L","신광명S/S 신광명-광명#2T/L 하자점검","SO2 및 수분 측정 차단기 동작시간 측정 경보시험 및 조작시험","2020-03-23 09:00","2020-03-23 18:00","2020-03-14 14:00","2020-03-14 18:00","연속"]
[38,"남서울","영등포","신광명소래 T/L","신광명S/S 신광명-소래T/L 하자점검","SO2 및 수분 측정 차단기 동작시간 측정 경보시험 및 조작시험","2020-03-27 09:00","2020-03-27 18:00","2020-03-27 09:00","2020-03-27 18:00","연속"]
[39,"남서울","영등포","신정S/S 154kV #60-#65 BUS TIE CB","신정S/S 154kV모선보호반 교체공사","-모선보호반 교체 -김우현,최종수","2020-03-16 09:00","2020-03-20 18:00","2020-03-16 09:00","2020-03-20 18:00","연속"]
[40,"남서울","영등포","양평양천#1 T/L","154㎸ 양평-양천T/L 선종교체공사","1. 154kV OF 케이블 철거 - 154kV 양평-양천#1,2T/L 철거 : 2.522km 2. 154kV XLPE 케이블 포설 및 접속 - 케이블포설 : 154kV 양평-양천#1,2T/L 포설 : 2.522km(구간 : 7구간 * 2회선) - 케이블접속 : 종단접속(2개소*2회선), 절연접속(4개소 *2회선), 보통접속(2개소 * 2회선)","2020-03-12 09:00","2020-07-30 18:00","취소","취소","연속"]
[41,"남서울","영등포","천왕오류#2 T/L","2019-2020년 영등포전력지사 지중송전설비 위탁정비공사","OF케이블 절연유 채유","2020-03-14 09:00","2020-03-14 18:00","취소","취소","연속"]
[42,"남서울","영등포","천왕오류#1 T/L","2019-2020년 영등포전력지사 지중송전설비 위탁정비공사","OF케이블 절연유 채유","2020-03-07 09:00","2020-03-07 18:00","취소","취소","연속"]
[43,"남서울","영등포","오류목동 T/L","2019-2020년 영등포전력지사 지중송전설비 위탁정비공사","OF케이블 절연유 채유","2020-03-11 09:00","2020-03-11 18:00","2020-03-11 09:00","2020-03-11 18:00","연속"]
[44,"남서울","직할","사당봉천#2 T/L","장기사용 보호배전반 교체공사","장기사용 송전선로 보호배전반 교체공사","2020-03-09 09:00","2020-03-11 18:00","취소","취소","연속"]
[45,"남서울","직할","대방신길#2 T/L","장기사용 보호배전반 교체공사","장기사용 송전선로 보호배전반 교체공사","2020-03-02 09:00","2020-03-04 14:00","2020-03-02 09:00","2020-03-04 14:00","연속"]
[46,"남서울","직할","영등포S/S 154kV 영등포-영오#2T/L GIS","영등포E/C #4M.Tr 증설","362kV GIS x 3CB 345kV M.Tr x 1 Bank 170kV GIS x 1CCT","2020-03-02 09:00","2020-03-15 18:00","2020-03-23 09:00","2020-04-05 18:00","연속"]
[47,"남서울","직할","영등포S/S 154kV #66 BUS","영등포E/C #4M.Tr 증설","362kV GIS x 3CB 345kV M.Tr x 1 Bank 170kV GIS x 1CCT","2020-03-09 09:00","2020-03-15 18:00","2020-03-29 18:00","2020-04-05 18:00","연속"]
[48,"남서울","직할","영등포S/S 154kV #61 BUS","영등포E/C #4M.Tr 증설","362kV GIS x 3CB 345kV M.Tr x 1 Bank 170kV GIS x 1CCT","2020-03-02 09:00","2020-03-09 09:00","2020-03-23 09:00","2020-03-29 18:00","연속"]
[49,"남서울","직할","영등포S/S 154kV 영등포-노량진T/L GIS","영등포E/C #4M.Tr 증설","362kV GIS x 3CB 345kV M.Tr x 1 Bank 170kV GIS x 1CCT","2020-03-02 09:00","2020-03-15 18:00","2020-03-23 09:00","2020-04-05 18:00","연속"]
[50,"인천","김포","신경서경서#3 T/L","김포전력지사 170kV GIS 정밀점검","경서S/S 170kV 신경서-경서#3T/L GIS 정밀점검공사","2020-03-23 09:00","2020-03-25 18:00","2020-03-23 09:00","2020-03-25 18:00","연속"]
[51,"인천","김포","신김포장기#1 T/L","신김포S/S #63D.Tr 증설공사","- #63D.Tr 최초 무부하가압용","2020-03-09 09:00","2020-03-10 18:00","2020-03-09 09:00","2020-03-10 18:00","연속"]
[52,"인천","김포","신김포S/S 154kV #60 BUS","신김포S/S #63D.Tr 증설공사","- #63D.Tr 무부하가압","2020-03-09 09:00","2020-03-10 18:00","2020-03-09 09:00","2020-03-10 18:00","연속"]
[53,"인천","김포","신김포장기#1 T/L","345kV 신김포S/S #63D.Tr 증설공사","345kV 신김포S/S #63D.Tr 증설공사(무부하가압) - 170kV GIS 4CCT","2020-03-03 09:00","2020-03-04 09:00","2020-03-03 09:00","2020-03-04 09:00","연속"]
[54,"인천","김포","신김포S/S 154kV #65 BUS","345kV 신김포S/S #63D.Tr 증설공사","345kV 신김포S/S #63D.Tr 증설공사 - 170kV GIS 4CCT","2020-03-04 09:00","2020-03-07 18:00","2020-03-04 09:00","2020-03-07 18:00","연속"]
[55,"인천","김포","신김포S/S 154kV #60 BUS","345kV 신김포S/S #63D.Tr 증설공사","345kV 신김포S/S #63D.Tr 증설공사 - 170kV GIS 4CCT","2020-03-02 09:00","2020-03-04 09:00","2020-03-02 09:00","2020-03-04 09:00","연속"]
[56,"인천","김포","신김포장기#1 T/L","345kV 신김포S/S #63D.Tr 증설공사","345kV 신김포S/S #63D.Tr 증설공사(무부하가압) - 170kV GIS 4CCT","2020-03-06 09:00","2020-03-07 18:00","2020-03-06 09:00","2020-03-07 18:00","연속"]
[57,"인천","김포","경서양촌#1 T/L","김포전력지사 170kV GIS 정밀점검","양촌S/S 170kV 경서-양촌#1T/L GIS 정밀점검공사","2020-03-16 09:00","2020-03-18 18:00","2020-03-16 09:00","2020-03-18 18:00","연속"]
[58,"인천","부평","남동관교#1 T/L","154kV남동관교#1T/L 정밀점검","154kV남동-관교#1T/L 정밀점검","2020-03-23 09:00","2020-03-24 18:00","2020-03-23 09:00","2020-03-24 18:00","연속"]
[59,"인천","부평","남동관교#2 T/L","154kV남동-관교#2T/L 정밀점검","154kV남동-관교#2T/L 정밀점검","2020-03-25 09:00","2020-03-26 18:00","2020-03-25 09:00","2020-03-26 18:00","연속"]
[60,"인천","부평","남인천학익#1 T/L","남인천,학익S/S 남인천학익#1T/L GIS 조작시험","남인천,학익S/S 남인천학익#1T/L GIS 조작시험","2020-03-05 09:00","2020-03-05 18:00","2020-03-05 09:00","2020-03-05 18:00","연속"]
[61,"인천","부평","인천남인천#2 T/L","남인천S/S 인천남인천#2T/L GIS 조작시험","남인천S/S 인천남인천#2T/L GIS 조작시험","2020-03-11 09:00","2020-03-11 18:00","2020-03-11 09:00","2020-03-11 18:00","연속"]
[62,"인천","부평","부개원미#2 T/L","부개S/S 부개원미#2T/L GIS 조작시험","부개S/S 부개원미#2T/L GIS 조작시험","2020-03-06 13:00","2020-03-06 18:00","2020-03-06 13:00","2020-03-06 18:00","연속"]
[63,"인천","부평","부개원미#1 T/L","부개S/S 부개원미#1T/L GIS 조작시험","부개S/S 부개원미#1T/L GIS 조작시험","2020-03-06 09:00","2020-03-06 13:00","2020-03-06 09:00","2020-03-06 13:00","연속"]
[64,"인천","부평","신가좌인천#3 T/L","신가좌S/S 신가좌인천#3T/L GIS 조작시험","신가좌S/S 신가좌인천#3T/L GIS 조작시험","2020-03-17 09:00","2020-03-17 18:00","2020-03-17 09:00","2020-03-17 18:00","연속"]
[65,"인천","부평","인천CC북인천#2 T/L","인천복합S/Y 인천CC북인천#2T/L GIS AIR 누기 보수","인천복합S/Y 인천CC북인천#2T/L GIS AIR 누기 보수 - GIS AIR 배기밸브 누기 보수","2020-03-09 09:00","2020-03-09 18:00","2020-03-09 09:00","2020-03-09 18:00","연속"]
[66,"인천","부평","주안만수 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2020-03-03 09:00","2020-03-04 18:00","2020-03-03 09:00","2020-03-04 18:00","연속"]
[67,"인천","부평","신가좌주안#2 T/L","송전선로 보호배전반 성능개선 및 선로정수 측정","- 87 PCM 통신회로 Loop시 오동작방지 관련 펌웨어 업그레이드 - 지중선로 병행지선 설치 관련 선로정수 측정","2020-03-02 13:00","2020-03-02 17:00","취소","취소","연속"]
[68,"인천","부평","신가좌주안#1 T/L","송전선로 보호배전반 성능개선 및 선로정수 측정","- 87 PCM 통신회로 Loop시 오동작방지 관련 펌웨어 업그레이드 - 지중선로 병행지선 설치 관련 선로정수 측정","2020-03-02 10:00","2020-03-02 13:00","취소","취소","연속"]
[69,"인천","부평","주안S/S 154kV #60 BUS","주안S/S #1M.Tr 교체공사(무부하 가압)","1. 변압기 1BANK 철거 및 설치 2. 기타 부대공사 1식","2020-03-24 15:00","2020-03-25 15:00","2020-03-24 15:00","2020-03-25 15:00","연속"]
[70,"인천","부평","영종중산 T/L","중산S/S 영종중산T/L GIS 하자점검","- 중산S/S 영종중산T/L GIS 하자점검 - 세니온제 IED 성능개선 및 보드교체","2020-03-03 09:00","2020-03-03 18:00","2020-03-03 09:00","2020-03-03 18:00","연속"]
[71,"인천","부평","신경서중산 T/L","중산S/S 신경서중산T/L GIS 하자점검","- 중산S/S 신경서중산T/L GIS 하자점검 - 세니온제 IED 성능개선 및 보드교체","2020-03-02 09:00","2020-03-02 18:00","2020-03-02 09:00","2020-03-02 18:00","연속"]
[72,"인천","부평","남인천학익#2 T/L","학익S/S 남인천학익#2T/L GIS 조작시험","학익S/S 남인천학익#2T/L GIS 조작시험","2020-03-19 09:00","2020-03-19 18:00","2020-03-19 09:00","2020-03-19 18:00","연속"]
[73,"인천","부평","학익연수#1 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2020-03-09 09:00","2020-03-10 18:00","2020-03-09 09:00","2020-03-10 18:00","연속"]
[74,"인천","부평","학익연수#2 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2020-03-11 09:00","2020-03-12 18:00","2020-03-11 09:00","2020-03-12 18:00","연속"]
[75,"인천","시흥","신시흥도림#1 T/L","도림S/S 154kV 신시흥도림#1T/L GIS초기점검","도림S/S 154kV 신시흥도림#1T/L GIS초기점검","2020-03-16 10:00","2020-03-16 18:00","취소","취소","연속"]
[76,"인천","시흥","도림오봉#1 T/L","도림S/S 154kV 도림오봉#1T/L GIS초기점검","도림S/S 154kV 도림오봉#1T/L GIS초기점검","2020-03-13 10:00","2020-03-13 18:00","취소","취소","연속"]
[77,"인천","시흥","동시화서시화 T/L","동시화S/S 154kV 동시화서시화T/L GIS누유보수","동시화S/S 154kV 동시화서시화T/L GIS누유보수","2020-03-04 10:00","2020-03-04 18:00","취소","취소","연속"]
[78,"인천","시흥","신시흥북시화#1 T/L","북시화S/S 154kV 신시흥북시화#1T/L GIS하자점검","북시화S/S 154kV 신시흥북시화#1T/L GIS하자점검","2020-03-20 10:00","2020-03-20 18:00","취소","취소","연속"]
[79,"인천","시흥","북시화서시화#3 T/L","154kV 북시화-서시화#3 T/L 구형 SVL 교체공사","154kV 북시화-서시화#3 T/L 구형 SVL 교체공사","2020-03-30 09:00","2020-03-31 18:00","2020-03-30 09:00","2020-03-31 18:00","연속"]
[80,"인천","시흥","북시화서시화#2 T/L","154kV 북시화-서시화#2 T/L 구형 SVL 교체공사","154kV 북시화-서시화#2 T/L 구형 SVL 교체공사","2020-03-26 09:00","2020-03-27 18:00","2020-03-26 09:00","2020-03-27 18:00","연속"]
[81,"인천","시흥","북시화서시화#1 T/L","154kV 북시화-서시화#1 T/L 구형 SVL 교체공사","154kV 북시화-서시화#1 T/L 구형 SVL 교체공사","2020-03-24 09:00","2020-03-25 18:00","2020-03-24 09:00","2020-03-25 18:00","연속"]
[82,"인천","시흥","신시흥#1S/S 154kV #61-#62 SEC GIS","신시흥S/S 154kV 61-62 SEC GIS조작시험","신시흥S/S 154kV 61-62 SEC GIS조작시험","2020-03-19 10:00","2020-03-19 14:00","2020-03-19 10:00","2020-03-19 14:00","연속"]
[83,"인천","시흥","신시흥#1S/S 154kV #66-#67 SEC GIS","신시흥S/S 154kV 66-67 SEC GIS조작시험","신시흥S/S 154kV 66-67 SEC GIS조작시험","2020-03-19 14:00","2020-03-19 18:00","2020-03-19 14:00","2020-03-19 18:00","연속"]
[84,"인천","시흥","신시흥#2S/S 154kV #67-#68 SEC GIS(2019)","신시흥S/S 154kV 67-68 SEC GIS초기점검","신시흥S/S 154kV 67-68 SEC GIS초기점검","2020-03-25 14:00","2020-03-25 18:00","2020-03-25 14:00","2020-03-25 18:00","연속"]
[85,"인천","시흥","신시흥#2S/S 154kV #63-#68 BUS TIE GIS","신시흥S/S 154kV 6400 BUS-TIE GIS조작시험","신시흥S/S 154kV 6400 BUS-TIE GIS조작시험","2020-03-12 14:00","2020-03-12 18:00","2020-03-12 14:00","2020-03-12 18:00","연속"]
[86,"인천","시흥","신시흥시화#1 T/L","신시흥S/S 154kV 신시흥시화#1T/L GIS보통점검","신시흥S/S 154kV 신시흥시화#1T/L GIS보통점검","2020-03-23 10:00","2020-03-23 18:00","2020-03-23 10:00","2020-03-23 18:00","연속"]
[87,"인천","시흥","신시흥#2S/S 154kV #62-#63 SEC GIS(2019)","신시흥S/S 154kV 62-63 SEC GIS초기점검","신시흥S/S 154kV 62-63 SEC GIS초기점검","2020-03-25 10:00","2020-03-25 14:00","2020-03-25 10:00","2020-03-25 14:00","연속"]
[88,"인천","시흥","신시흥#2S/S 154kV #62-#67 BUS TIE GIS","신시흥S/S 154kV 6300 BUS-TIE GIS조작시험","신시흥S/S 154kV 6300 BUS-TIE GIS조작시험","2020-03-12 10:00","2020-03-12 14:00","2020-03-12 10:00","2020-03-12 14:00","연속"]
[89,"인천","시흥","도림오봉#2 T/L","오봉S/S 154kV 도림오봉#2T/L GIS보통점검","오봉S/S 154kV 도림오봉#2T/L GIS보통점검","2020-03-17 10:00","2020-03-17 18:00","취소","취소","연속"]
[90,"인천","직할","계양원창 T/L","임학계양#1T/L 광케이블 시설공사","임학-계양S/S 광케이블 시설(OPGW 7,097km, OFC 1.764km)","2020-03-09 09:00","2020-03-13 18:00","2020-03-09 09:00","2020-03-13 18:00","연속"]
[91,"인천","직할","임학계양#1 T/L","임학계양#1T/L 광케이블 시설공사","임학-계양S/S 광케이블 시설(OPGW 7,097km, OFC 1.764km)","2020-03-09 09:00","2020-03-13 18:00","2020-03-09 09:00","2020-03-13 18:00","연속"]
[92,"인천","직할","부천도당#1 T/L","도당,부천S/S 도당부천#1T/L 170kV GIS 초기점검,조작시험","도당,부천S/S 도당부천#1T/L 170kV GIS 초기점검,조작시험 도당(초기), 부천(조작)","2020-03-23 09:30","2020-03-23 18:00","2020-03-23 09:30","2020-03-23 18:00","연속"]
[93,"인천","직할","신부평도당#2 T/L","신부평,도당S/S 신부평,도당#2T/L 170kV GIS 보통,초기점검","신부평,도당S/S 신부평,도당#2T/L 170kV GIS 보통,초기점검 신부평(보통),도당(초기)","2020-03-20 09:30","2020-03-20 18:00","2020-03-20 09:30","2020-03-20 18:00","연속"]
[94,"인천","직할","신부평도당#1 T/L","신부평,도당S/S 신부평,도당#1T/L 170kV GIS 보통,초기점검","신부평,도당S/S 신부평,도당#1T/L 170kV GIS 보통,초기점검 신부평(보통),도당(초기)","2020-03-19 09:30","2020-03-19 18:00","2020-03-19 09:30","2020-03-19 18:00","연속"]
[95,"인천","직할","부천도당#2 T/L","도당,부천S/S 도당부천#2T/L 170kV GIS 초기점검,조작시험","도당,부천S/S 도당부천#2T/L 170kV GIS 초기점검,조작시험 도당(초기), 부천(조작)","2020-03-24 09:30","2020-03-24 18:00","2020-03-24 09:30","2020-03-24 18:00","연속"]
[96,"인천","직할","부흥부개#1 T/L","부흥S/S #3M.Tr 1차 170kV GIS 정밀 무부하가압용","부흥S/S #3M.Tr 1차 170kV GIS 정밀 무부하가압용","2020-03-18 14:00","2020-03-18 18:00","2020-03-18 14:00","2020-03-18 18:00","연속"]
[97,"인천","직할","부흥부개#1 T/L","부흥S/S #4M.Tr 1차 170kV GIS 정밀 무부하가압용","부흥S/S #4M.Tr 1차170kV GIS 정밀 #1BUS 무부하가압용","2020-03-20 10:00","2020-03-20 12:00","2020-03-20 10:00","2020-03-20 12:00","연속"]
[98,"인천","직할","부흥부개#2 T/L","부흥S/S #4M.Tr 1차 170kV GIS 정밀 무부하가압용","부흥S/S #4M.Tr 1차170kV GIS 정밀 #2BUS 무부하가압용","2020-03-21 15:00","2020-03-21 17:00","2020-03-21 15:00","2020-03-21 17:00","연속"]
[99,"인천","직할","경서북인천#2 T/L","북인천S/S 경서북인천#2T/L 170kV GIS 조작시험","북인천S/S 경서북인천#2T/L 170kV GIS 조작시험","2020-03-04 14:00","2020-03-04 18:00","2020-03-04 14:00","2020-03-04 18:00","연속"]
[100,"인천","직할","경서북인천#1 T/L","북인천S/S 경서북인천#1T/L 170kV GIS 조작시험","북인천S/S 북인천원창T/L 170kV GIS 조작시험","2020-03-04 09:30","2020-03-04 14:00","2020-03-04 09:30","2020-03-04 14:00","연속"]
[101,"인천","직할","북인천원창 T/L","북인천S/S 북인천원창T/L 170kV GIS 조작시험","북인천S/S 북인천원창T/L 170kV GIS 조작시험","2020-03-03 09:30","2020-03-03 18:00","2020-03-03 09:30","2020-03-03 18:00","연속"]
[102,"인천","직할","계양북인천 T/L","계양,북인천S/S 계양북인천T/L 170kV GIS 조작시험(양단)","계양,북인천S/S 계양북인천T/L 170kV GIS 조작시험(양단)","2020-03-16 09:30","2020-03-16 18:00","2020-03-16 09:30","2020-03-16 18:00","연속"]
[103,"인천","직할","인천CC북인천#1 T/L","북인천S/S 인천CC북인천#1T/L 170kV GIS 조작시험","북인천S/S 인천CC북인천#1T/L 170kV GIS 조작시험","2020-03-05 09:30","2020-03-05 14:00","2020-03-05 09:30","2020-03-05 14:00","연속"]
[104,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S #61D.Tr 1차 170kV GIS 정밀 무부하가압용","신부평S/S #61D.Tr 1차 170kV GIS 정밀 무부하가압용","2020-03-14 14:00","2020-03-14 18:00","2020-03-14 14:00","2020-03-14 18:00","연속"]
[105,"인천","직할","신부평부흥#1 T/L","154kV 갈산-부흥 지중T/L 인출정비공사","○ 154kV XLPE 2,000㎟, 2C×0.2㎞(갈산-부흥)설치 및 기설선로 철거","2020-03-25 08:00","2020-04-24 18:00","2020-03-25 08:00","2020-04-24 18:00","연속"]
[106,"경기북부","고양","양주고양#2 T/L","고양전력지사 관내 T/L OPGW 항공장애표시구 시설공사","154kV 양주-고양#2T/L OPGW용 항공장애 표시구 설치","2020-03-11 07:00","2020-03-11 18:00","2020-03-11 07:00","2020-03-11 18:00","연속"]
[107,"경기북부","고양","양주고양#1 T/L","고양전력지사 관내 T/L OPGW 항공장애표시구 시설공사","154kV 양주-고양#1T/L OPGW용 항공장애 표시구 설치","2020-03-12 07:00","2020-03-12 18:00","2020-03-12 07:00","2020-03-12 18:00","연속"]
[108,"경기북부","고양","양주금촌#1 T/L","345kV 신파주-양주 등 11개T/L 항공시설물 정비공사","항공구 설치공사 - 154kV 양주-금촌 #1T/L No.22-23 등 7경간","2020-03-12 07:00","2020-03-13 18:00","2020-03-12 07:00","2020-03-13 18:00","연속"]
[109,"경기북부","고양","양주금촌#2 T/L","고양전력지사 관내 T/L OPGW 항공장애표시구 시설공사","154kV 양주-금촌#2T/L OPGW용 항공장애 표시구 설치","2020-03-09 07:00","2020-03-11 18:00","2020-03-09 07:00","2020-03-11 18:00","연속"]
[110,"경기북부","고양","지도능곡#2 T/L","2020년 변전정비회사 총액공사","170kV GIS 보통점검","2020-03-11 09:30","2020-03-11 18:00","2020-03-11 09:30","2020-03-11 18:00","연속"]
[111,"경기북부","고양","일산S/S 154KV #60 BUS","2020년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(1CCT + PT Bay) 1. 154kV 일산S/S #2G/T 2. 154kV #60-#65 BUS PT Bay","2020-03-21 09:00","2020-03-27 17:00","2020-03-21 09:00","2020-03-27 17:00","연속"]
[112,"경기북부","고양","일산호수#2 T/L","2020년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(1CCT + PT Bay) 1. 154kV 일산S/S #2G/T 2. 154kV #60-#65 BUS PT Bay","2020-03-27 17:00","2020-03-28 09:00","2020-03-27 17:00","2020-03-28 09:00","연속"]
[113,"경기북부","고양","일산S/S 154KV #65 BUS","2020년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(1CCT + PT Bay) 1. 154kV 일산S/S #2G/T 2. 154kV #60-#65 BUS PT Bay","2020-03-28 09:00","2020-04-06 13:00","2020-03-28 09:00","2020-04-06 13:00","연속"]
[114,"경기북부","고양","일산S/S 154kV #2G/T CB","2020년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(1CCT + PT Bay) 1. 154kV 일산S/S #2G/T 2. 154kV #60-#65 BUS PT Bay","2020-03-18 09:00","2020-04-07 18:00","2020-03-18 09:00","2020-04-07 18:00","연속"]
[115,"경기북부","고양","일산S/S 154KV #65 BUS","2020년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(1CCT + PT Bay) 1. 154kV 일산S/S #2G/T 2. 154kV #60-#65 BUS PT Bay","2020-03-18 09:00","2020-03-20 17:00","2020-03-18 09:00","2020-03-20 17:00","연속"]
[116,"경기북부","고양","일산지도#2 T/L","2020년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(1CCT + PT Bay) 1. 154kV 일산S/S #2G/T 2. 154kV #60-#65 BUS PT Bay","2020-03-18 09:00","2020-04-07 18:00","2020-03-18 09:00","2020-04-07 18:00","연속"]
[117,"경기북부","고양","일산호수#2 T/L","2020년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(1CCT + PT Bay) 1. 154kV 일산S/S #2G/T 2. 154kV #60-#65 BUS PT Bay","2020-03-20 17:00","2020-03-21 09:00","2020-03-20 17:00","2020-03-21 09:00","연속"]
[118,"경기북부","고양","일산지도#1 T/L","2020년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(1CCT + PT Bay) 1. 154kV 일산S/S #2G/T 2. 154kV #60-#65 BUS PT Bay","2020-03-18 09:00","2020-04-07 18:00","2020-03-18 09:00","2020-04-07 18:00","연속"]
[119,"경기북부","구리","가평춘천HP T/L","2020~21년도 구리전력지사 송전정비회사 총액공사","ㅇ 불량애자 교체 - No.78,79,102","2020-03-20 07:00","2020-03-20 18:00","2020-03-20 07:00","2020-03-20 18:00","연속"]
[120,"경기북부","구리","가평청평HP#2 T/L","765kV 신안성-신가평 등 13개T/L 항공장애시설물 정비공사","ㅇ 항공장애표시구 설치 - No.가평-청평HP#2T/L No.3~4","2020-03-17 07:00","2020-03-17 18:00","2020-03-17 07:00","2020-03-17 18:00","연속"]
[121,"경기북부","구리","가평화천HP T/L","765kV 신안성-신가평 등 13개T/L 항공장애시설물 정비공사","ㅇ 항공장애표시구 설치 - 154kV 가평-화천HP T/L No.133~134","2020-03-17 07:00","2020-03-17 18:00","2020-03-17 07:00","2020-03-17 18:00","연속"]
[122,"경기북부","구리","구리신내#2 T/L","'20~21 구리전력 변전정비 총액공사","구리S/S 154kV 구리-신내#2T/L GIS 조작시험","2020-03-23 09:00","2020-03-23 18:00","2020-03-23 09:00","2020-03-23 18:00","연속"]
[123,"경기북부","구리","덕소마석#2 T/L","'20∼21 구리전력 변전정비 총액공사","덕소S/S 덕소-마석#2T/L GIS 초기점검공사","2020-03-10 09:00","2020-03-10 18:00","2020-03-10 09:00","2020-03-10 18:00","연속"]
[124,"경기북부","구리","덕소진건#2 T/L","'20~21 구리전력 변전정비 총액공사","덕소S/S 덕소-진건#2T/L GIS 초기점검공사","2020-03-05 09:00","2020-03-05 18:00","2020-03-05 09:00","2020-03-05 18:00","연속"]
[125,"경기북부","구리","덕소진건#1 T/L","'20~21 구리전력 변전정비 총액공사","덕소S/S 덕소-진건#1T/L GIS 초기점검공사","2020-03-03 09:00","2020-03-03 18:00","2020-03-03 09:00","2020-03-03 18:00","연속"]
[126,"경기북부","구리","덕소마석#1 T/L","'20~21년 구리전력 변전협력 총액공사","덕소S/S 154kV 덕소-마석#1T/L GIS 초기점검공사","2020-03-11 09:00","2020-03-11 18:00","2020-03-11 09:00","2020-03-11 18:00","연속"]
[127,"경기북부","구리","마석청평HP#1 T/L","2020~21년도 구리전력지사 송전정비회사 총액공사","ㅇ SB댐퍼 교체 - No.25","2020-03-13 07:00","2020-03-13 10:00","2020-03-13 07:00","2020-03-13 10:00","연속"]
[128,"경기북부","구리","마석청평HP#2 T/L","2020~21년도 구리전력지사 송전정비회사 총액공사","ㅇ SB댐퍼 교체 - No.25","2020-03-13 10:00","2020-03-13 12:00","2020-03-13 10:00","2020-03-13 12:00","연속"]
[129,"경기북부","구리","운천전곡#1 T/L","'20~21 구리전력 변전정비 총액공사","운천S/S 154kV 운천-전곡#1T/L GIS 조작시험","2020-03-26 09:00","2020-03-26 18:00","2020-03-26 09:00","2020-03-26 18:00","연속"]
[130,"경기북부","구리","포천GS포천열병합 T/L CB","'20~21 구리전력 변전정비 총액공사","포천S/S 포천열병합T/l GIS 하자점검공사","2020-03-16 09:00","2020-03-16 18:00","2020-03-16 09:00","2020-03-16 18:00","연속"]
[131,"경기북부","직할","금오상계#2 T/L","2020~2021년 직할 가공송전 정비회사 총액공사","불량애자교체 및 압축인류클램프 교체","2020-03-23 08:00","2020-03-27 18:00","2020-03-23 08:00","2020-03-27 18:00","연속"]
[132,"경기북부","직할","금오상계#1 T/L","2020~2021년 직할 가공송전 정비회사 총액공사","불량애자교체 및 압축인류클램프 교체","2020-03-16 08:00","2020-03-20 18:00","2020-03-16 08:00","2020-03-20 18:00","연속"]
[133,"경기북부","직할","도봉방학#2 T/L","20년도 직할 변전정비회사 총액공사","621DS 과열개소 보수","2020-03-30 09:00","2020-03-30 18:00","2020-03-30 09:00","2020-03-30 18:00","연속"]
[134,"경기북부","직할","백석덕계#1 T/L","20년도 직할 변전정비회사 총액공사","백석S/S 백석-덕계 #1T/L 보통점검","2020-03-05 10:00","2020-03-05 18:00","2020-03-05 10:00","2020-03-05 18:00","연속"]
[135,"경기북부","직할","녹양백석#1 T/L","20년도 직할 변전정비회사 총액공사","백석S/S 녹양-백석 #1 T/L 보통점검 녹양S/S 녹양-백석 #1 T/L 개폐타임 측정","2020-03-10 10:00","2020-03-10 18:00","2020-03-10 10:00","2020-03-10 18:00","연속"]
[136,"경기북부","직할","남면백석#2 T/L","20년도 직할 변전정비회사 총액공사","백석S/S 남면-백석 #2 T/L 하자점검","2020-03-11 10:00","2020-03-11 18:00","2020-03-11 10:00","2020-03-11 18:00","연속"]
[137,"경기북부","직할","녹양백석#2 T/L","20년도 직할 변전정비회사 총액공사","녹양S/S 녹양-백석 #2T/L 개폐타임 측정 및 전자변 러버히터 설치","2020-03-12 10:00","2020-03-12 14:00","2020-03-12 10:00","2020-03-12 14:00","연속"]
[138,"경기북부","직할","옥정송우#2 T/L","'20~21 구리전력 변전정비 총액공사","송우S/S 154kV 옥정-송우#2T/L GIS 보통점검공사","2020-03-19 09:00","2020-03-19 18:00","2020-03-19 09:00","2020-03-19 18:00","연속"]
[139,"경기북부","직할","양주S/S SVC M.Tr 1차 GIS","'20-21년 경기북부 직할 변전협력회사 총액공사","보통점검","2020-03-23 09:00","2020-03-26 18:00","취소","취소","연속"]
[140,"경기북부","직할","용현도봉#2 T/L","2020~2021년 직할 가공송전 정비회사 총액공사","불량애자교체 및 압축인류클램프 교체","2020-03-16 08:00","2020-03-20 18:00","2020-03-16 08:00","2020-03-20 18:00","연속"]
[141,"경기북부","직할","용현도봉#1 T/L","2020~2021년 직할 가공송전 정비회사 총액공사","불량애자교체 및 압축인류클램프 교체","2020-03-23 08:00","2020-03-27 18:00","2020-03-23 08:00","2020-03-27 18:00","연속"]
[142,"경기북부","고양","신덕은문산#1 T/L","2020년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S GIS 교체공사 관련 SPS 사전 작업","2020-03-18 09:00","2020-03-18 10:00","2020-03-17 13:00","2020-03-17 14:00","연속"]
[143,"경기북부","고양","신덕은문산#2 T/L","2020년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S GIS 교체공사 관련 SPS 사전 작업","2020-03-18 10:00","2020-03-18 11:00","2020-03-17 14:00","2020-03-17 15:00","연속"]
[144,"경기북부","고양","신덕은원흥#1 T/L","2020년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S GIS 교체공사 관련 SPS 사전 작업","2020-03-18 11:00","2020-03-18 12:00","2020-03-17 15:00","2020-03-17 16:00","연속"]
[145,"경기북부","고양","신덕은원흥#2 T/L","2020년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S GIS 교체공사 관련 SPS 사전 작업","2020-03-18 12:00","2020-03-18 13:00","2020-03-17 16:00","2020-03-17 17:00","연속"]
[146,"경기","군포","서서울#2서안양 T/L","154kV 서안양S/S #4M.Tr 증설공사","154kV 서안양S/S #4M.Tr 증설공사 ○ 154㎸ M.Tr 60MVA × 1Bank ○ 154㎸ GIS × 1CCT, 23㎸ GIS × 3CCT","2020-03-06 09:00","2020-03-07 18:00","2020-03-06 09:00","2020-03-07 18:00","연속"]
[147,"경기","군포","서서울#2서안양 T/L","154kV 서안양S/S #4M.Tr 증설공사","154kV 서안양S/S #4M.Tr 증설공사 ○ 154㎸ M.Tr 60MVA × 1Bank ○ 154㎸ GIS × 1CCT, 23㎸ GIS × 3CCT","2020-03-03 09:00","2020-03-04 18:00","2020-03-03 09:00","2020-03-04 18:00","연속"]
[148,"경기","군포","서서울#2서안양 T/L","154kV 서안양S/S #4M.Tr 증설공사","154kV 서안양S/S #4M.Tr 증설공사 ○ 154㎸ M.Tr 60MVA × 1Bank ○ 154㎸ GIS × 1CCT, 23㎸ GIS × 3CCT","2020-03-25 09:00","2020-03-26 18:00","2020-03-25 09:00","2020-03-26 18:00","연속"]
[149,"경기","군포","산본안양#1 T/L","산본-안양#1T/L GIS 조작시험(양단)","산본SS 산본안양#1TL GIS 조작시험, 안양SS 산본안양#1TL GIS조작시험","2020-03-23 09:00","2020-03-23 14:00","2020-03-23 09:00","2020-03-23 14:00","연속"]
[150,"경기","군포","산본안양#2 T/L","산본-안양#2T/L GIS 조작시험(양단)","산본SS 산본안양#2TL GIS 조작시험, 안양SS 산본안양#2TL GIS 조작시험","2020-03-23 14:00","2020-03-23 18:00","2020-03-23 14:00","2020-03-23 18:00","연속"]
[151,"경기","군포","장덕마도 T/L","장덕변전소 외벽 누수공사","창호 코킹 및 유리 교체","2020-03-11 09:00","2020-03-11 18:00","2020-03-13 09:00","2020-03-13 18:00","연속"]
[152,"경기","군포","화성장덕 T/L","장덕변전소 외부 누수공사","창호 코킹 및 유리 교체","2020-03-12 09:00","2020-03-12 18:00","2020-03-14 09:00","2020-03-14 18:00","연속"]
[153,"경기","동부","곤지암율현#2 T/L","154kV 곤지암-율현 #2T/L 송전선로 정밀점검","송전선로 정밀점검","2020-03-16 09:00","2020-03-20 18:00","2020-03-16 09:00","2020-03-20 18:00","매일"]
[154,"경기","동부","곤지암율현#1 T/L","154kV 곤지암-율현 #1T/L 송전선로 정밀점검","송전선로 정밀점검","2020-03-09 09:00","2020-03-12 18:00","2020-03-09 09:00","2020-03-12 18:00","매일"]
[155,"경기","동부","곤지암이천#1 T/L","154kV 곤지암-이천 #1T/L 송전선로 정밀점검","송전선로 정밀점검","2020-03-25 09:00","2020-03-27 18:00","2020-03-25 09:00","2020-03-27 18:00","매일"]
[156,"경기","동부","곤지암율현#1 T/L","154kV 곤지암-이천 #1T/L 송전선로 정밀점검","안전상 휴전 (4회선 구간)","2020-03-25 09:00","2020-03-26 18:00","2020-03-25 09:00","2020-03-26 18:00","매일"]
[157,"경기","동부","곤지암이천#2 T/L","154kV 곤지암-이천 #2T/L 송전선로 정밀점검","송전선로 정밀점검","2020-03-23 09:00","2020-03-24 18:00","2020-03-23 09:00","2020-03-24 18:00","매일"]
[158,"경기","동부","곤지암율현#2 T/L","154kV 곤지암-이천 #2T/L 송전선로 정밀점검","안전상 휴전 (4회선 구간)","2020-03-23 09:00","2020-03-23 18:00","2020-03-23 09:00","2020-03-23 18:00","연속"]
[159,"경기","동부","곤지암이천#2 T/L","154kV 곤지암-이천 #2T/L 송전선로 정밀점검","송전선로 정밀점검","2020-03-20 09:00","2020-03-20 18:00","2020-03-20 09:00","2020-03-20 18:00","연속"]
[160,"경기","동부","분당오포#1 T/L","154kV 성현-분당 #2T/L 과열개소 정비","안전상 휴전 (4회선 구간)","2020-03-02 09:00","2020-03-02 12:00","2020-03-02 09:00","2020-03-02 12:00","연속"]
[161,"경기","동부","분당오포#2 T/L","154kV 성현-분당 #1T/L 과열개소 정비","안전상 휴전 (4회선 구간)","2020-03-02 12:00","2020-03-02 15:00","2020-03-02 12:00","2020-03-02 15:00","연속"]
[162,"경기","동부","성현분당#2 T/L","154kV 성현-분당 #2T/L 과열개소 정비","과열개소 정비","2020-03-02 09:00","2020-03-02 12:00","2020-03-02 09:00","2020-03-02 12:00","연속"]
[163,"경기","동부","성현분당#1 T/L","154kV 성현-분당 #1T/L 과열개소 정비","과열개소 정비","2020-03-02 12:00","2020-03-02 15:00","2020-03-02 12:00","2020-03-02 15:00","연속"]
[164,"경기","동부","성현산성#3 T/L","20년 동부 변전정비회사 총액공사","산성:산성-성현#3T/L(조작) 43L/R 회로보완 확인 및 Remote 회로분리 시행 성현:산성-성현#3T/L(조작) 43L/R 회로보완 확인 및 Remote 회로분리 시행","2020-03-26 09:30","2020-03-26 18:00","2020-03-26 09:30","2020-03-26 18:00","연속"]
[165,"경기","동부","이천율현#2 T/L","20년 동부 변전정비회사 총액공사","이천:이천-율현#2T/L(보통), 43L/R 회로보완 확인 및 Remote 회로분리 시행, LA(초기) 율현:이천-율현#2T/L(보통), 43L/R 회로보완 확인 및 Remote 회로분리 시행","2020-03-31 09:30","2020-03-31 18:00","2020-03-31 09:30","2020-03-31 18:00","연속"]
[166,"경기","동부","이천가남#1 T/L","20년 동부 변전정비회사 총액공사","이천:이천-가남#1T/L(보통), 43L/R 회로보완 확인 및 Remote 회로분리 시행, LA(초기) 가남:이천-가남#1T/L(보통), 43L/R 회로보완 확인 및 Remote 회로분리 시행","2020-03-06 09:30","2020-03-06 18:00","2020-03-06 09:30","2020-03-06 18:00","연속"]
[167,"경기","동부","이천가남#2 T/L","20년 동부 변전정비회사 총액공사","이천:이천-가남#2T/L(보통)LA(초기)","2020-03-03 09:30","2020-03-03 18:00","2020-03-03 09:30","2020-03-03 18:00","연속"]
[168,"경기","성남","농서신갈#2 T/L","신갈S/S 154kV GIS 대체","GIS 대체(농서#2T/L)","2020-03-23 09:00","2020-04-10 18:00","2020-03-23 09:00","2020-04-10 18:00","연속"]
[169,"경기","성남","농서신갈#1 T/L","신갈S/S 154kV GIS 대체","GIS 대체","2020-03-02 09:00","2020-03-20 18:00","2020-03-02 09:00","2020-03-20 18:00","연속"]
[170,"경기","성남","신용인S/S 154kV #1 EM.Tr CB","20년 성남전력 변전정비회사 총액공사","신용인:#1EM.Tr(보통)(~13) - 1차 LA(보통), 1차 N LA(보통) - 1차 GIS(보통) - 2차 EGIS(보통), 1,2 ES.Tr EGIS(보통) - E6100 EGIS(보통), #1,2,3,4,5,6 ESS EGIS(보통)","2020-03-09 09:00","2020-03-13 18:00","2020-03-09 09:00","2020-03-13 18:00","연속"]
[171,"경기","성남","신용인S/S 154kV #60-#61 SEC GIS","20년 성남전력 변전정비회사 총액공사","신용인S/S 154kV #60-#61 SEC GIS 조작시험","2020-03-27 09:00","2020-03-27 14:00","2020-03-27 09:00","2020-03-27 14:00","연속"]
[172,"경기","성남","신용인S/S 154kV #65-#66 SEC GIS","20년 성남전력 변전정비회사 총액공사","신용인S/S 154kV #65-#66 SEC GIS 조작시험","2020-03-27 14:00","2020-03-27 18:00","2020-03-27 14:00","2020-03-27 18:00","연속"]
[173,"경기","성남","용인남사#1 T/L","154kV 용인-남사#1T/L 송전선로 정밀점검","154kV 용인-남사#1T/L(No.1~54) 송전선로 정밀점검","2020-03-30 09:00","2020-04-03 18:00","2020-03-30 09:00","2020-04-03 18:00","매일"]
[174,"경기","성남","신성남정자 #3 T/L","154kV 정자S/S #4M.Tr 증설공사","154kV 정자S/S #4M.Tr 증설공사","2020-03-19 14:00","2020-03-20 18:00","취소","취소","연속"]
[175,"경기","직할","서서울#2남수원 #1T/L","봉담-송산고속도로 지장철탑이설공사(3공구)","봉담-송산고속도로 지장철탑이설공사(3공구) (154kV 서서울-남수원T/L No.43~48)","2020-03-29 07:00","2020-04-03 18:00","2020-03-29 07:00","2020-04-03 18:00","연속"]
[176,"경기","직할","서서울#2남수원 #2T/L","봉담-송산고속도로 지장철탑이설공사(3공구)","봉담-송산고속도로 지장철탑이설공사(3공구) (154kV 서서울-남수원T/L No.43~48)","2020-03-28 07:00","2020-03-28 18:00","2020-03-28 07:00","2020-03-28 18:00","연속"]
[177,"경기","직할","의왕동안양#2 T/L","20-21년 경기본부 직할 변전정비회사 총액공사","동안양S/S, 의왕S/S 의왕-동안양#2T/L 조작시험","2020-03-11 10:00","2020-03-11 18:00","2020-03-11 10:00","2020-03-11 18:00","연속"]
[178,"경기","직할","관양동안양#1 T/L","20-21년 경기본부 직할 변전정비회사 총액공사","동안양S/S 관양-동안양#1T/L 조작시험","2020-03-10 10:00","2020-03-10 14:00","2020-03-10 10:00","2020-03-10 14:00","연속"]
[179,"경기","직할","관양동안양#2 T/L","20-21년 경기본부 직할 변전정비회사 총액공사","동안양S/S 관양-동안양#1T/L 조작시험","2020-03-10 14:00","2020-03-10 18:00","2020-03-10 14:00","2020-03-10 18:00","연속"]
[180,"경기","직할","발안S/S 154kV #60 BUS","발안S/S #5M.Tr용 GIS 설치","-GIS 설치 * 1CCT","2020-03-09 09:00","2020-03-14 18:00","취소","취소","연속"]
[181,"경기","직할","발안S/S 154kV #65 BUS","발안S/S #5M.Tr용 GIS 설치","-GIS 설치 * 1CCT","2020-03-16 09:00","2020-03-24 18:00","취소","취소","연속"]
[182,"경기","직할","발안구문천#1 T/L","발안S/S #5M.Tr용 GIS 설치","-GIS 설치 * 1CCT","2020-03-23 18:00","2020-03-24 18:00","2020-03-23 18:00","2020-03-24 18:00","연속"]
[183,"경기","직할","발안구문천#1 T/L","발안S/S #5M.Tr용 GIS 설치","-GIS 설치 * 1CCT","2020-03-13 18:00","2020-03-14 18:00","2020-03-13 18:00","2020-03-14 18:00","연속"]
[184,"경기","직할","발안S/S 154kV #60 BUS","발안S/S #5M.Tr용 GIS 설치","-GIS 설치 * 1CCT","2020-03-25 09:00","2020-04-01 18:00","취소","취소","연속"]
[185,"경기","직할","남수원발안#1 T/L","발안S/S #5M.Tr용 GIS 설치","-GIS 설치 * 1CCT","2020-03-09 09:00","2020-04-01 18:00","취소","취소","연속"]
[186,"경기","직할","율전의왕#1 T/L","20-21년 경기본부 직할 변전정비회사 총액공사","율전S/S 율전-의왕#1T/L GIS 조작시험 / 의왕S/S 율전-의왕#1T/L GIS 초기점검","2020-03-25 10:00","2020-03-25 18:00","2020-03-25 10:00","2020-03-25 18:00","연속"]
[187,"경기","직할","서서울율전#2 T/L","20-21년 경기본부 직할 변전정비회사 총액공사","율전S/S 서서울-율전#2T/L GIS 조작시험","2020-03-24 14:00","2020-03-24 18:00","2020-03-24 14:00","2020-03-24 18:00","연속"]
[188,"경기","직할","서서울율전#1 T/L","20-21년 경기본부 직할 변전정비회사 총액공사","율전S/S 서서울-율전#1T/L GIS 조작시험","2020-03-24 10:00","2020-03-24 14:00","2020-03-24 10:00","2020-03-24 14:00","연속"]
[189,"경기","직할","율전의왕#2 T/L","20-21년 경기본부 직할 변전정비회사 총액공사","율전S/S 율전-의왕#2T/L GIS 조작시험","2020-03-17 10:00","2020-03-17 18:00","2020-03-17 10:00","2020-03-17 18:00","연속"]
[190,"경기","직할","서수원율전#1 T/L","20-21년 경기본부 직할 변전정비회사 총액공사","서수원S/S 서수원-율전#1T/L 조작시험","2020-03-12 10:00","2020-03-12 14:00","2020-03-12 10:00","2020-03-12 14:00","연속"]
[191,"경기","직할","서수원율전#2 T/L","20-21년 경기본부 직할 변전정비회사 총액공사","서수원S/S 서수원-율전#2T/L 조작시험","2020-03-12 14:00","2020-03-12 18:00","2020-03-12 14:00","2020-03-12 18:00","연속"]
[192,"경기","직할","발안향남#1 T/L","20-21년 경기본부 직할 변전정비회사 총액공사","향남S/S 발안-향남#1T/L GIS 보통점검 / 발안S/S 발안-향남#1T/L LA 하자점검","2020-03-20 10:00","2020-03-20 18:00","2020-03-20 10:00","2020-03-20 18:00","연속"]
[193,"경기","직할","오산향남#2 T/L","20-21년 경기본부 직할 변전정비회사 총액공사","향남S/S 오산-향남#2T/L GIS 보통점검","2020-03-21 14:00","2020-03-21 18:00","2020-03-21 14:00","2020-03-21 18:00","연속"]
[194,"경기","직할","오산향남#1 T/L","20-21년 경기본부 직할 변전정비회사 총액공사","향남S/S 오산-향남#1T/L GIS 보통점검","2020-03-21 09:00","2020-03-21 14:00","2020-03-21 09:00","2020-03-21 14:00","연속"]
[195,"경기","직할","발안향남#2 T/L","20-21년 경기본부 직할 변전정비회사 총액공사","향남S/S 발안-향남#2T/L GIS 보통점검 / 발안S/S 발안-향남#2T/L LA 하자점검","2020-03-19 10:00","2020-03-19 18:00","2020-03-19 10:00","2020-03-19 18:00","연속"]
[196,"경기","평택","고덕평택#2 T/L","고덕,평택S/S 154kV 고덕-평택#2T/L GIS 하자점검","고덕,평택S/S 154kV 고덕-평택#2T/L GIS 하자점검","2020-03-24 10:00","2020-03-24 18:00","2020-03-24 10:00","2020-03-24 18:00","연속"]
[197,"경기","평택","고덕평택#1 T/L","고덕,평택S/S 154kV 고덕-평택#1T/L GIS 하자점검","고덕,평택S/S 154kV 고덕-평택#1T/L GIS 하자점검","2020-03-23 10:00","2020-03-23 18:00","2020-03-23 10:00","2020-03-23 18:00","연속"]
[198,"경기","평택","고덕송탄#1 T/L","고덕S/S 154kV 고덕-송탄#1T/L GIS 하자점검","고덕S/S 154kV 고덕-송탄#1T/L GIS 하자점검","2020-03-25 10:00","2020-03-25 18:00","2020-03-25 10:00","2020-03-25 18:00","연속"]
[199,"경기","평택","고덕송탄#2 T/L","고덕S/S 154kV 고덕-송탄#2T/L GIS 하자점검","고덕S/S 154kV 고덕-송탄#2T/L GIS 하자점검","2020-03-26 10:00","2020-03-26 18:00","2020-03-26 10:00","2020-03-26 18:00","연속"]
[200,"경기","평택","서운삼죽 T/L","서운S/S 154kV 서운-삼죽T/L GIS 보통점검","서운S/S 154kV 서운-삼죽T/L GIS 보통점검","2020-03-31 10:00","2020-03-31 18:00","2020-03-31 10:00","2020-03-31 18:00","연속"]
[201,"경기","평택","서운안성#2 T/L","서운S/S 154kV 서운-안성#2T/L GIS 보통점검","서운S/S 154kV 서운-안성#2T/L GIS 보통점검","2020-03-30 10:00","2020-03-30 18:00","2020-03-30 10:00","2020-03-30 18:00","연속"]
[202,"경기","평택","서운안성#1 T/L","서운S/S 154kV 서운-안성#1T/L GIS 보통점검","서운S/S 154kV 서운-안성#1T/L GIS 보통점검","2020-03-27 10:00","2020-03-27 18:00","2020-03-27 10:00","2020-03-27 18:00","연속"]
[203,"경기","평택","서운광혜원 T/L","서운S/S 154kV 서운-광혜원T/L GIS 보통점검","서운S/S 154kV 서운-광혜원T/L GIS 보통점검","2020-03-20 10:00","2020-03-20 18:00","2020-03-20 10:00","2020-03-20 18:00","연속"]
[204,"경기","평택","오산평택#1 T/L","오산S/S 154kV 오산-평택#1T/L 보호배전반 대체","오산S/S 154kV 오산-평택#1 T/L 보호배전반 대체 및 GIS 보통점검","2020-03-09 10:00","2020-03-11 18:00","2020-03-09 10:00","2020-03-11 18:00","연속"]
[205,"경기","평택","만호청북#1 T/L","345kV 신온양서서울외 2개T/L 지장이설","지장이설 임시선로 구성","2020-03-17 07:00","2020-03-19 18:00","2020-03-17 07:00","2020-03-19 18:00","연속"]
[206,"경기","평택","평택추팔#1 T/L","2020-2021 송전정비회사 총액공사","지지물 보강공사(인클로징 1기, 계탑 2기, 가철주 2기) - 임시선로(가철주) 구성","2020-03-23 07:00","2020-03-24 18:00","취소","취소","연속"]
[207,"경기","평택","평택추팔#2 T/L","2020-2021 송전정비회사 총액공사","지지물 보강공사(인클로징 1기, 계탑 2기, 가철주 2기)","2020-03-25 07:00","2020-03-31 18:00","취소","취소","연속"]
[208,"경기","평택","포승청북 T/L","345kV 신온양서서울외 2개T/L 지장이설","지장이설 임시선로 구성","2020-03-13 07:00","2020-03-16 18:00","2020-03-13 07:00","2020-03-16 18:00","연속"]
[209,"강원","강릉","주진평창#2 T/L","2020년 변전협력총액공사 170kV GIS 보통점검","○ 2020년 변전협력총액공사 - 170kV GIS 보통점검, 기타기기 점검(피뢰기)","2020-03-06 10:00","2020-03-06 18:00","2020-03-06 10:00","2020-03-06 18:00","연속"]
[210,"강원","강릉","신제천주진#1 T/L","2020년 변전협력총액공사 170kV GIS 보통점검","○ 2020년 변전협력총액공사 - 170kV GIS 보통점검, 기타기기 점검(피뢰기)","2020-03-03 10:00","2020-03-03 18:00","2020-03-03 10:00","2020-03-03 18:00","연속"]
[211,"강원","강릉","신제천주진#2 T/L","2020년 변전협력총액공사 170kV GIS 보통점검","○ 2020년 변전협력총액공사 - 170kV GIS 보통점검, 기타기기 점검(피뢰기)","2020-03-04 10:00","2020-03-04 18:00","2020-03-04 10:00","2020-03-04 18:00","연속"]
[212,"강원","강릉","주진평창#1 T/L","2020년 변전협력총액공사 170kV GIS 보통점검","○ 2020년 변전협력총액공사 - 170kV GIS 보통점검, 기타기기 점검(피뢰기)","2020-03-05 10:00","2020-03-05 18:00","2020-03-05 10:00","2020-03-05 18:00","연속"]
[213,"강원","강릉","평창올림픽 T/L","2020년 가공송전선로 순시점검 위탁공사","○ 초기점검 (154kV 올림픽분기T/L) - 올림픽S/S, No.1, 횡계평창No.7(전원측)","2020-03-24 09:00","2020-03-24 18:00","2020-03-24 09:00","2020-03-24 18:00","연속"]
[214,"강원","강릉","횡계올림픽 T/L","2020년 가공송전선로 순시점검 위탁공사","○ 초기점검 (154kV 올림픽분기T/L) - 올림픽S/S, No.1, 횡계평창No.5(부하측)","2020-03-23 09:00","2020-03-23 18:00","2020-03-23 09:00","2020-03-23 18:00","연속"]
[215,"강원","동해","이원도계 T/L","2020년 동해전력지사 170kV GIS 정밀점검","1. GIS 정밀점검 2. LA 보통점검","2020-03-30 09:30","2020-04-01 14:00","2020-03-30 09:30","2020-04-01 14:00","연속"]
[216,"강원","동해","동해이원#1 T/L","2020년 동해전력 변전정비 협력회사 총액공사","1. LA 보통점검 2. 차단기조작시험[양측]","2020-03-12 09:30","2020-03-12 18:00","2020-03-12 09:30","2020-03-12 18:00","연속"]
[217,"강원","동해","동해이원#2 T/L","2020년 동해전력 변전정비 협력회사 총액공사","1. LA 보통점검 2. 차단기조작시험[양측]","2020-03-13 09:30","2020-03-13 18:00","2020-03-13 09:30","2020-03-13 18:00","연속"]
[218,"강원","동해","이원동해TP T/L","154kV 동해화력T/L 자기애관 교체공사","기중종단접속(EBA) 자기애관을 폴리머애관으로 교체(6기)","2020-03-02 09:00","2020-03-06 18:00","2020-03-02 09:00","2020-03-06 18:00","연속"]
[219,"강원","동해","삼척동해TP T/L","154kV 동해화력T/L 자기애관 교체공사","기중종단접속(EBA) 자기애관을 폴리머애관으로 교체(6기)","2020-03-09 09:00","2020-03-13 18:00","2020-03-09 09:00","2020-03-13 18:00","연속"]
[220,"강원","동해","이원삼척 T/L","2020년 동해전력지사 170kV GIS 정밀점검","1. GIS 정밀점검 2. LA 보통점검","2020-03-16 09:30","2020-03-18 14:00","2020-03-16 09:30","2020-03-18 14:00","연속"]
[221,"강원","동해","동해정선 T/L","154kV 정선S/S 외장재 교체공사","산불 화재 확산 방지를 위한 노후 드라이비트 철거 및 메탈패널 교체","2020-03-03 13:00","2020-03-04 18:00","2020-03-03 13:00","2020-03-04 18:00","연속"]
[222,"강원","동해","정선영월CC T/L","154kV 정선S/S 외장재 교체공사","산불 화재 확산 방지를 위한 노후 드라이비트 철거 및 메탈패널 교체","2020-03-09 09:00","2020-03-11 13:00","2020-03-09 09:00","2020-03-11 13:00","연속"]
[223,"강원","동해","동해정선 T/L","154kV 정선S/S 외장재 교체공사","산불 화재 확산 방지를 위한 노후 드라이비트 철거 및 메탈패널 교체","2020-03-11 13:00","2020-03-13 18:00","2020-03-11 13:00","2020-03-13 18:00","연속"]
[224,"강원","동해","정선영월CC T/L","154kV 정선S/S 외장재 교체공사","산불 화재 확산 방지를 위한 노후 드라이비트 철거 및 메탈패널 교체","2020-03-02 09:00","2020-03-03 13:00","2020-03-02 09:00","2020-03-03 13:00","연속"]
[225,"강원","직할","남춘천춘천열병합#1 T/L","2020~2021년 강원직할 송전정비회사 총액공사","불량애자 교체 15기 29련","2020-03-24 08:00","2020-03-28 19:00","2020-03-24 08:00","2020-03-28 19:00","연속"]
[226,"강원","직할","남춘천춘천열병합#2 T/L","2020~2021년 강원직할 송전정비회사 총액공사","불량애자 교체 13기 30련","2020-03-29 08:00","2020-04-01 19:00","2020-03-29 08:00","2020-04-01 19:00","연속"]
[227,"강원","직할","북춘천춘천HP T/L","2020~2021년 강원지역본부 직할 변전정비 총액공사","GCB, LA, PT 보통점검","2020-03-24 09:00","2020-03-24 18:00","2020-03-24 09:00","2020-03-24 18:00","연속"]
[228,"강원","직할","가평춘천HP T/L","2020~2021년 강원지역본부 직할 변전정비 총액공사","GCB, LA, PT 보통점검","2020-03-23 09:00","2020-03-23 18:00","취소","취소","연속"]
[229,"강원","직할","춘천열병합S/Y 154kV #60 BUS","2020-2021 변전협력회사 총액공사","춘천열병합S/Y #1, #2 BUS PT GIS 하자점검 ㅇPT FUSE 단선 및 단자조임 등","2020-03-17 10:00","2020-03-17 14:00","2020-03-17 10:00","2020-03-17 14:00","연속"]
[230,"강원","직할","춘천열병합S/Y 154kV #65 BUS","2020-2021 변전협력회사 총액공사","춘천열병합S/Y #1, #2 BUS PT GIS 하자점검 ㅇPT FUSE 단선 및 단자조임 등","2020-03-17 14:00","2020-03-17 18:00","2020-03-17 14:00","2020-03-17 18:00","연속"]
[231,"강원","직할","화천화천HP#1 T/L","20~21 강원본부 직할 변전정비 총액공사","○ 화천-화천H/P #1T/L GCB 보통점검 ○ 화천-화천H/P #1T/L DS, LA, PT 보통점검","2020-03-18 10:00","2020-03-19 18:00","2020-03-18 10:00","2020-03-19 18:00","연속"]
[232,"강원","직할","화천H/P 154kV #60-#65 BUS TIE GIS","20~21 강원본부 직할 변전정비 총액공사","○ 154kV #1BUS-TIE GIS 하자점검","2020-03-20 10:00","2020-03-20 18:00","2020-03-23 10:00","2020-03-23 18:00","연속"]
[233,"충북","직할","신진천오창#1 T/L","20~21년도 직할 변전정비회사 총액공사","신진천-오창#1T/L 장기사용 배전반 대체","2020-03-21 09:00","2020-03-22 18:00","2020-03-21 09:00","2020-03-22 18:00","연속"]
[234,"충북","직할","신진천진천#1 T/L","154kV 신진천-진천T/L OPGW 증설공사","154kV 신진천-진천T/L 가공지선 철거 및 OPGW 10km 시설","2020-03-14 09:00","2020-03-14 18:00","2020-03-07 09:00","2020-03-07 18:00","연속"]
[235,"충북","직할","신진천진천#2 T/L","154kV 신진천-진천T/L OPGW 증설공사","154kV 신진천-진천T/L 가공지선 철거 및 OPGW 10km 시설","2020-03-15 09:00","2020-03-15 18:00","2020-03-08 09:00","2020-03-08 18:00","연속"]
[236,"충북","직할","신진천오창#2 T/L","20~21년도 직할 변전정비회사 총액공사","신진천-오창#2T/L 장기사용 배전반 대체","2020-03-14 09:00","2020-03-15 18:00","2020-03-07 09:00","2020-03-08 18:00","연속"]
[237,"충북","직할","진천덕산#2 T/L","20~21년도 직할 변전정비회사 총액공사","진천-덕산#2T/L 장기사용 배전반 대체","2020-03-17 10:00","2020-03-20 18:00","2020-03-17 10:00","2020-03-20 18:00","연속"]
[238,"충북","직할","진천덕산#1 T/L","20~21년도 직할 변전정비회사 총액공사","진천-덕산#1T/L 장기사용 배전반 대체","2020-03-10 10:00","2020-03-13 18:00","2020-03-10 10:00","2020-03-13 18:00","연속"]
[239,"충북","청주","옥천보은 T/L","154kV 신옥천-옥천T/L, 상주T/L 정밀점검","154kV 상주T/L 정밀점검(No.14~59) 3월 9일 연속 154kV 신옥천-옥천#2T/L과 병가구간(No.24~36) 작업시행 3월 10일~12일 매일 상주T/L No.14~59 정밀점검 시행","2020-03-09 08:00","2020-03-12 18:00","2020-03-09 08:00","2020-03-12 18:00","매일"]
[240,"충북","청주","옥천영동 T/L","154kV 신옥천-옥천T/L 정밀점검(병가선로)","154kV 신옥천-옥천T/L 정밀점검(병가선로, No.24~36)","2020-03-04 08:00","2020-03-04 18:00","2020-03-04 08:00","2020-03-04 18:00","연속"]
[241,"충북","청주","옥천영동 T/L","154kV 상주T/L 정밀점검","154kV 상주T/L 정밀점검(No.14~59)","2020-03-18 08:00","2020-03-20 18:00","2020-03-25 08:00","2020-03-27 18:00","연속"]
[242,"충북","충주","신제천왕암#1 T/L","2020년 가공송전선로 순시점검 위탁공사","애자 제원 확인 (No. 7, 14)","2020-03-04 09:00","2020-03-04 12:00","취소","취소","연속"]
[243,"충북","충주","신제천남원주#2 T/L","2020년 가공송전선로 순시점검 위탁공사","애자 제원 확인 (No. ST, 12, 13)","2020-03-03 13:00","2020-03-03 18:00","2020-03-01 13:00","2020-03-01 18:00","연속"]
[244,"충북","충주","신제천왕암#2 T/L","2020년 가공송전선로 순시점검 위탁공사","애자 제원 확인 (No.7, 14)","2020-03-04 13:00","2020-03-04 18:00","취소","취소","연속"]
[245,"충북","충주","신제천남원주#1 T/L","2020년 가공송전선로 순시점검 위탁공사","애자 제원 확인 (No. ST, 12, 13)","2020-03-03 09:00","2020-03-03 12:00","2020-03-01 09:00","2020-03-01 12:00","연속"]
[246,"충북","충주","왕암가남#1 T/L","왕암S/S 154kV SW 증설공사(봉양전철#1T/L)","기설 GIS (#5M.Tr Bay ) x 1CCT 철거 GIS x 1CCT 신설 최초 가압(무부하 가압)","2020-03-19 10:00","2020-03-20 10:00","2020-03-25 10:00","2020-03-26 10:00","연속"]
[247,"충북","충주","왕암가남#1 T/L","왕암S/S 154kV SW 증설공사(봉양전철#1T/L)","기설 GIS(#5M.Tr Bay) x 1CCT 철거 GIS x 1CCT 신설 무부하 가압 전원","2020-03-13 10:00","2020-03-14 10:00","2020-03-13 10:00","2020-03-13 13:00","연속"]
[248,"충북","충주","풍동음성#1 T/L","154kV 풍동-음성T/L No.13~51 전선접속개소 전선교체공사","154kV 풍동-음성T/L No.13~51 (14경간, 6구간)","2020-03-23 07:00","2020-04-03 18:00","2020-03-23 07:00","2020-04-03 18:00","연속"]
[249,"대전충남","대전","은진함열#2 T/L","[송전] 154kV 은진-함열T/L 취약철탑 교체공사","[송전] 154kV 은진-함열T/L 취약철탑 교체 ○ 구간 : 154kV 은진-함열T/L No.48~52 ○ 철탑 설치/철거 : 1기[No.51] ○ 전선교체 : 0.4km[ACSR410㎟×2B×2회선] ○ 가공지선 : 0.4km[ACSR97㎟×1조] ○ 기타부대공사","2020-03-02 07:00","2020-04-05 18:00","2020-03-02 07:00","2020-04-05 18:00","연속"]
[250,"대전충남","대전","은진함열#1 T/L","[송전] 154kV 은진-함열T/L 취약철탑 교체공사","[송전] 154kV 은진-함열T/L 취약철탑 교체 ○ 구간 : 154kV 은진-함열T/L No.48~52 ○ 철탑 설치/철거 : 1기[No.51] ○ 전선교체 : 0.4km[ACSR410㎟×2B×2회선] ○ 가공지선 : 0.4km[ACSR97㎟×1조] ○ 기타부대공사","2020-03-02 07:00","2020-04-05 18:00","2020-03-02 07:00","2020-04-05 18:00","연속"]
[251,"대전충남","서산","당진송악#1 T/L","서산P/O OPGW 항공장애표시구 시설공사","항공구 26개 설치","2020-03-07 09:00","2020-03-08 18:00","2020-03-07 09:00","2020-03-08 18:00","매일"]
[252,"대전충남","서산","신당진당진#1 T/L","서산P/O OPGW 항공장애표시구 시설공사","항공구 5 개 설치","2020-03-15 09:00","2020-03-15 18:00","2020-03-15 09:00","2020-03-15 18:00","연속"]
[253,"대전충남","서산","합덕송악#1 T/L","서산P/O OPGW 항공장애표시구 시설공사","항공장애표시구 5개 설치","2020-03-15 09:00","2020-03-15 18:00","2020-03-15 09:00","2020-03-15 18:00","연속"]
[254,"대전충남","서산","태안태안화력 T/L","서산P/O OPGW 항공장애표시구 시설공사","항공장애표시구 31 개 설치","2020-03-28 09:00","2020-03-29 18:00","2020-03-28 09:00","2020-03-29 18:00","매일"]
[255,"대전충남","서산","서산태안화력 T/L","20년도 차단기 부동작 예방시험","20년도 차단기 부동작 예방시험 - 태안T/P 서산-태안T/P T/L (617)CB 부동작 예방시험","2020-03-23 10:00","2020-03-23 14:00","2020-03-23 10:00","2020-03-23 14:00","연속"]
[256,"대전충남","서산","합덕송악#2 T/L","서산P/O OPGW 항공장애표시구 시설공사","항공구 26개 설치","2020-03-07 09:00","2020-03-08 18:00","2020-03-07 09:00","2020-03-08 18:00","매일"]
[257,"대전충남","세종","신풍공주#2 T/L","[송전]154kV 신풍-공주T/L 접속개소전선교체공사","[송전]154kV 신충-공주#2T/L 접속개소전선교체공사 -#2T/L: No.7~12(상,중,하단 6선), No.13~14(중단 2선)","2020-03-30 07:00","2020-04-04 18:00","2020-03-30 07:00","2020-04-04 18:00","연속"]
[258,"대전충남","세종","신풍공주#1 T/L","[송전]154kV 신풍-공주T/L 접속개소전선교체공사","[송전]154kV 신충-공주#1T/L 접속개소전선교체공사 -#1T/L: No.7~12(상,중,하단 6선), No.13~14(중단 2선)","2020-03-23 07:00","2020-03-28 18:00","2020-03-23 07:00","2020-03-28 18:00","연속"]
[259,"대전충남","세종","세종송강#2 T/L","[송전] 154kV 세종-송강T/L 안전이격확보공사","ㅇ 공사구간 : 154kV 세종-송강T/L No.17~19 ㅇ 철탑 : No.18호 1기 설치, 가철주 1기 ㅇ 전력선 : HSTACIR/AW 330 x S x 2C (0.25km) 교체(No.18~19)","2020-03-28 07:00","2020-03-31 18:00","취소","취소","연속"]
[260,"대전충남","아산","신온양석곡#2 T/L","신온양S/S 신온양-석곡#2T/L GIS 보통점검","신온양S/S 신온양-석곡#2T/L GIS 보통점검","2020-03-11 09:00","2020-03-11 18:00","2020-03-11 09:00","2020-03-11 18:00","연속"]
[261,"대전충남","아산","신온양한샘#2 T/L","[송전]154kV신온양-한샘#2T/L 정밀점검","[병행]154kV서천안-탕정#1T/L 휴전으로 인한 모선로 휴전","2020-03-14 08:00","2020-03-14 18:00","2020-03-14 08:00","2020-03-14 18:00","연속"]
[262,"대전충남","아산","신온양한샘#1 T/L","[송전]154kV신온양-한샘#1T/L 정밀점검","[병행]154kV서천안-탕정#2T/L 휴전으로 인한 모선로 휴전","2020-03-21 08:00","2020-03-21 18:00","2020-03-21 08:00","2020-03-21 18:00","연속"]
[263,"대전충남","아산","신온양석곡#1 T/L","신온양S/S 신온양-석곡#1T/L GIS 보통점검","신온양S/S 신온양-석곡#1T/L GIS 보통점검","2020-03-10 09:00","2020-03-10 18:00","2020-03-10 09:00","2020-03-10 18:00","연속"]
[264,"대전충남","아산","아산인주#1 T/L","[송전]154kV아산-인주#1T/L 정밀점검","[병행]154kV인주탕정#2T/L 휴전으로 인한 모선로 휴전 (3/14일) [병행]154kV아산합덕#1T/L 휴전으로 인한 자선로 휴전 (3/15일)","2020-03-14 08:00","2020-03-15 18:00","취소","취소","매일"]
[265,"대전충남","아산","아산인주#2 T/L","[송전]154kV아산-인주#2T/L 정밀점검","[병행]154kV아산-합덕#2T/L 휴전으로 인한 자선로 휴전","2020-03-28 08:00","2020-03-28 18:00","취소","취소","연속"]
[266,"대전충남","아산","아산인주#2 T/L","[송전]154kV아산-인주#2T/L 정밀점검","[병행]154kV인주탕정#1T/L 휴전으로 인한 모선로 휴전","2020-03-21 08:00","2020-03-21 18:00","취소","취소","연속"]
[267,"대전충남","아산","아산합덕#2 T/L","[송전]345kV 신서산-아산 등 2개T/L 지장송전선로 이설공사","가. 철탑 설치 및 철거 : 2기 [No.83(B4-28 → Bb4-36), No.84(F4-29 → F4-39)] 나. 전력선교체 - ACSR 480㎟ x 4B x 2C × 1.778km [No.82~83 1선 교체, No.83~88 24선 교체] - ACSR 410㎟ x 2B x 2C × 1.778km [No.83~88 24선 교체]","2020-03-20 07:00","2020-03-30 18:00","2020-03-20 07:00","2020-03-30 18:00","연속"]
[268,"대전충남","아산","아산합덕#1 T/L","[송전]345kV 신서산-아산 등 2개T/L 지장송전선로 이설공사","가. 철탑 설치 및 철거 : 2기 [No.83(B4-28 → Bb4-36), No.84(F4-29 → F4-39)] 나. 전력선교체 - ACSR 480㎟ x 4B x 2C × 1.778km [No.82~83 1선 교체, No.83~88 24선 교체] - ACSR 410㎟ x 2B x 2C × 1.778km [No.83~88 24선 교체]","2020-03-09 07:00","2020-03-19 18:00","2020-03-09 07:00","2020-03-19 18:00","연속"]
[269,"대전충남","아산","온양풍세#2 T/L","온양,풍세S/S 온양-풍세#2T/L GIS 보호배전반 교체","온양,풍세S/S 온양-풍세#2T/L GIS 보호배전반 교체","2020-03-09 09:00","2020-03-13 18:00","취소","취소","연속"]
[270,"대전충남","아산","온양풍세#1 T/L","온양,풍세S/S 온양-풍세#1T/L GIS 보호배전반 교체","온양,풍세S/S 온양-풍세#1T/L GIS 보호배전반 교체","2020-03-02 09:00","2020-03-06 18:00","취소","취소","연속"]
[271,"대전충남","아산","인주탕정#2 T/L","345kV 북당진-신탕정T/L OPGW시설공사(2구간)","북당진-신탕정T/L 신설관련 OPGW 교체작업","2020-03-07 07:00","2020-03-08 18:00","2020-03-07 07:00","2020-03-08 18:00","연속"]
[272,"대전충남","아산","인주탕정#1 T/L","154kV 인주-불당T/L C/H 건설공사","154kV 인주-불당T/L C/H 건설공사 - 본선로 작업을 위한 임시선로 구성(가철탑) 및 가선","2020-03-18 07:00","2020-03-24 18:00","2020-03-18 07:00","2020-03-24 18:00","연속"]
[273,"대전충남","아산","서천안탕정#2 T/L","154kV 인주-불당T/L C/H 건설공사","154kV 인주-불당T/L C/H 건설공사 - 본선로 작업을 위한 임시선로 구성(가철탑) 및 가선","2020-03-18 07:00","2020-03-24 18:00","2020-03-18 07:00","2020-03-24 18:00","연속"]
[274,"대전충남","아산","서천안탕정#1 T/L","154kV 인주-불당T/L C/H 건설공사","154kV 인주-불당T/L C/H 건설공사 - 본선로 작업을 위한 임시선로 구성(가철탑) 및 가선","2020-03-11 07:00","2020-03-17 18:00","2020-03-11 07:00","2020-03-17 18:00","연속"]
[275,"대전충남","아산","인주탕정#2 T/L","154kV 인주-불당T/L C/H 건설공사","154kV 인주-불당T/L C/H 건설공사 - 본선로 작업을 위한 임시선로 구성(가철탑) 및 가선","2020-03-11 07:00","2020-03-17 18:00","2020-03-11 07:00","2020-03-17 18:00","연속"]
[276,"대전충남","직할","세종송강#1 T/L","[송전]국제과학비즈니스벨트 지장송전선로 지중화공사(요청자시행)","ㅇ 요청자(한국토지주택공사) 직접시행 지장이설 및 지중화공사 ㅇ 공사구간 : 154kV 세종-송강T/L No.82~83 ㅇ 철탑 : C/H 1기 설치, 가철탑 1기 ㅇ 전력선 : HSTACIR/AW 330 x S x 2C (1.041km) ㅇ CH 1기 설치, 가철탑 1기 설치철거 외 기타 부대공사 시행","2020-03-10 07:00","2020-03-27 18:00","취소","취소","연속"]
[277,"대전충남","직할","세종송강#1 T/L","[송전]국제과학비즈니스벨트 지장송전선로 지중화공사(요청자시행)","ㅇ 요청자(한국토지주택공사) 직접시행 지장이설 및 지중화공사 ㅇ 공사구간 : 154kV 세종-송강T/L No.82~83 ㅇ 철탑 : C/H 1기 설치, 가철탑 1기 ㅇ 전력선 : HSTACIR/AW 330 x S x 2C (1.041km) ㅇ CH 1기 설치, 가철탑 1기 설치철거 외 기타 부대공사 시행","2020-03-02 07:00","2020-03-03 18:00","취소","취소","연속"]
[278,"대전충남","직할","세종송강#2 T/L","[송전]국제과학비즈니스벨트 지장송전선로 지중화공사(요청자시행)","ㅇ 요청자(한국토지주택공사) 직접시행 지장이설 및 지중화공사 ㅇ 공사구간 : 154kV 세종-송강T/L No.82~83 ㅇ 철탑 : C/H 1기 설치, 가철탑 1기 ㅇ 전력선 : HSTACIR/AW 330 x S x 2C (1.041km) ㅇ CH 1기 설치, 가철탑 1기 설치철거 외 기타 부대공사 시행","2020-03-04 07:00","2020-03-09 18:00","취소","취소","연속"]
[279,"대전충남","직할","신탄진대청HP T/L","170kV GIS 전자변 교체","○직할 관내 170kV GIS 전자변 교체 (총 12대)","2020-03-18 09:00","2020-03-18 18:00","2020-03-18 09:00","2020-03-18 18:00","연속"]
[280,"대전충남","서산","서산태안 T/L","태안S/S ~ 태안화력 OPGW 증설공사","태안S/S ~ 서산-태안T/L No.52 OPGW 증설 및 가공지선 철거","2020-03-24 07:00","2020-03-27 18:00","2020-03-24 07:00","2020-03-27 18:00","연속"]
[281,"전북","군산","군공소룡#2 T/L","군산P/O 차단기 점검공사","군공-소룡#2T/L 차단기 보통점검","2020-03-06 09:30","2020-03-06 18:00","2020-03-11 09:30","2020-03-11 18:00","연속"]
[282,"전북","군산","군공소룡#1 T/L","군산P/O 차단기 점검공사","군공-소룡#1T/L 차단기 보통점검","2020-03-05 09:30","2020-03-05 18:00","2020-03-10 09:30","2020-03-10 18:00","연속"]
[283,"전북","군산","군산동군산#1 T/L","군산동군산T/L 안전이격거리확보공사","- 철탑신설 2기 : 24, 26호 - 철탑철거 3기 : 24, 25, 26호 - 전선교체 : 20~26호","2020-03-21 07:00","2020-03-28 18:00","2020-03-21 07:00","2020-03-28 18:00","연속"]
[284,"전북","군산","군산동군산#2 T/L","군산동군산T/L 안전이격거리확보공사","- 철탑신설 2기 : 24, 26호 - 철탑철거 3기 : 24, 25, 26호 - 전선교체 : 20~26호","2020-03-12 07:00","2020-03-20 18:00","2020-03-12 07:00","2020-03-20 18:00","연속"]
[285,"전북","군산","내초군장#1 T/L","군산P/O 차단기 조작시험","1. 군장 627 차단기 조작시험 2. 내초 665 차단기 조작시험","2020-03-04 09:30","2020-03-04 13:00","2020-03-31 09:00","2020-03-31 12:00","연속"]
[286,"전북","군산","내초군장#2 T/L","군산P/O 차단기 조작시험","1. 군장 637 차단기 조작시험 2. 내초 667 차단기 조작시험","2020-03-04 13:00","2020-03-04 18:00","2020-03-31 13:00","2020-03-31 16:00","연속"]
[287,"전북","군산","군공내초#2 T/L","군산P/O 차단기 조작시험","군공-내초#2T/L 차단기 조작시험","2020-03-03 13:00","2020-03-03 16:00","2020-03-30 13:00","2020-03-30 16:00","연속"]
[288,"전북","군산","군공내초#1 T/L","군산P/O 차단기 조작시험","군공-내초#1T/L 차단기 조작시험","2020-03-03 09:00","2020-03-03 12:00","2020-03-30 09:00","2020-03-30 12:00","연속"]
[289,"전북","군산","이리전주#1 T/L","154kV 이리-전주T/L 일부지중화관련 철탑교체공사","- 철탑교체 4기 : 49, 50, 51, 52호 - 전선교체 : 47~50, 51~53호 - 가선로 구성 및 기타 부대공사 - C/H 50, 51호 옹벽 및 콘크리트 설치","2020-03-09 07:00","2020-03-10 18:00","2020-03-09 07:00","2020-03-10 18:00","연속"]
[290,"전북","군산","이리전주#1 T/L","154kV 이리-전주T/L 일부지중화관련 철탑교체공사","- 철탑교체 4기 : 49, 50, 51, 52호 - 전선교체 : 47~50, 51~53호 - 가선로 구성 및 기타 부대공사 - C/H 50, 51호 옹벽 및 콘크리트 설치","2020-03-15 07:00","2020-03-16 18:00","2020-03-15 07:00","2020-03-16 18:00","연속"]
[291,"전북","군산","이리전주#2 T/L","154kV 이리-전주T/L 일부지중화관련 철탑교체공사","- 철탑교체 4기 : 49, 50, 51, 52호 - 전선교체 : 47~50, 51~53호 - 가선로 구성 및 기타 부대공사 - C/H 50, 51호 옹벽 및 콘크리트 설치","2020-03-11 07:00","2020-03-14 18:00","2020-03-11 07:00","2020-03-14 18:00","연속"]
[292,"전북","김제","정주고창#2 T/L","154kV 정주-고창 안전이격거리 확보공사","철탑 교체 : No.39, 40 전력선 교체 : No.37~41","2020-03-03 08:00","2020-03-08 18:00","취소","취소","연속"]
[293,"전북","김제","고창영광 T/L","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2020-03-04 16:00","2020-03-04 17:00","2020-03-04 16:00","2020-03-04 17:00","연속"]
[294,"전북","김제","정주고창#1 T/L","154kV 정주-고창 안전이격거리 확보공사","철탑 교체 : No.39, 40 전력선 교체 : No.37~41","2020-03-09 08:00","2020-03-15 18:00","취소","취소","연속"]
[295,"전북","김제","정주고창#1 T/L","154kV 정주-고창 안전이격거리 확보공사","철탑 교체 : No.39, 40 전력선 교체 : No.37~41","2020-03-02 08:00","2020-03-02 18:00","취소","취소","연속"]
[296,"전북","김제","고창홍농 T/L","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2020-03-04 17:00","2020-03-04 18:00","2020-03-04 17:00","2020-03-04 18:00","연속"]
[297,"전북","김제","김제S/S 154kV 백산-김제#1T/L GIS","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2020-03-06 10:00","2020-03-06 13:00","2020-03-06 10:00","2020-03-06 13:00","연속"]
[298,"전북","김제","김제S/S 154kV 백산-김제#2T/L GIS","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2020-03-06 13:00","2020-03-06 16:00","2020-03-06 13:00","2020-03-06 16:00","연속"]
[299,"전북","김제","김제S/S 154kV 김제-칠보수력T/L GIS","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2020-03-25 10:00","2020-03-25 13:00","2020-03-25 10:00","2020-03-25 13:00","연속"]
[300,"전북","김제","김제S/S 154kV 담양-김제T/L GIS","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2020-03-25 13:00","2020-03-25 14:00","2020-03-25 13:00","2020-03-25 14:00","연속"]
[301,"전북","김제","김제S/S 154kV 김제-부안#2T/L GIS","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2020-03-05 13:00","2020-03-05 16:00","2020-03-05 13:00","2020-03-05 16:00","연속"]
[302,"전북","김제","김제S/S 154kV 김제-부안#1T/L GIS","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2020-03-05 10:00","2020-03-05 13:00","2020-03-05 10:00","2020-03-05 13:00","연속"]
[303,"전북","김제","남전주임실#2 T/L","154kV 남전주-임실T/L OPGW 증설공사","가공지선 철거후 OPGW 교체(38km) 및 항공구 정비","2020-03-16 09:00","2020-04-24 18:00","2020-03-16 09:00","2020-04-24 18:00","연속"]
[304,"전북","김제","백산S/S 154kV 이리-백산#2T/L GIS","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2020-03-09 11:00","2020-03-09 12:00","2020-03-09 11:00","2020-03-09 12:00","연속"]
[305,"전북","김제","백산S/S 154kV 이리-백산#1T/L GIS","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2020-03-09 10:00","2020-03-09 11:00","2020-03-09 10:00","2020-03-09 11:00","연속"]
[306,"전북","김제","신김제전주#2 T/L","154kV 신김제-남전주#1T/L 정밀점검","154kV 신김제-남전주T/L 정밀점검(4회선구간 병가선로 신김제-정주#2 휴전필요)","2020-03-23 08:00","2020-03-26 17:00","2020-03-23 08:00","2020-03-26 17:00","매일"]
[307,"전북","김제","신김제남전주#1 T/L","154kV 신김제-남전주T/L 정밀점검","154kV 신김제-남전주T/L 정밀점검","2020-03-23 08:00","2020-03-26 17:00","2020-03-23 08:00","2020-03-26 17:00","매일"]
[308,"전북","김제","신김제전주#1 T/L","154kV 신김제-남전주#2T/L 정밀점검","154kV 신김제-남전주#2T/L 정밀점검(신김제-정주#1 병가선로 휴전)","2020-03-30 08:00","2020-04-02 17:00","2020-03-30 08:00","2020-04-02 17:00","매일"]
[309,"전북","김제","신김제남전주#2 T/L","154kV 신김제-남전주#2T/L 정밀점검","154kV 신김제-남전주#2T/L 정밀점검","2020-03-30 08:00","2020-04-02 17:00","2020-03-30 08:00","2020-04-02 17:00","매일"]
[310,"전북","김제","정공S/S 154kV #60-#65 BUS TIE GIS","정공S/S 6100 BUS TIE GIS 에어누기 보수공사","정공S/S 6100 BUS TIE GIS 에어누기 보수공사","2020-03-02 10:00","2020-03-02 18:00","2020-03-02 10:00","2020-03-02 18:00","연속"]
[311,"전북","직할","신김제동전주#2 T/L","154kV 동전주-북전주 등 2개T/L 전력선 교체공사","전력선 교체 ○ 154kV 신김제-동전주#2T/L No.65~66 중,하단 4가닥","2020-03-02 07:00","2020-03-03 18:00","2020-03-02 07:00","2020-03-03 18:00","연속"]
[312,"전북","직할","팔봉봉동#2 T/L","관내 154kV 이상 차단기 점검공사","봉동SS 팔봉-봉동#2T/L 차단기 조작시험","2020-03-23 14:00","2020-03-23 18:00","취소","취소","연속"]
[313,"전북","직할","북전주봉동#1 T/L","관내 154kV 이상 차단기 점검공사","봉동SS 북전주-봉동#1T/L 차단기 조작시험 북전주SS 북전주-봉동#1T/L 차단기 조작시험/ 전자변교체","2020-03-24 10:00","2020-03-24 18:00","취소","취소","연속"]
[314,"전북","직할","북전주봉동#2 T/L","관내 154kV 이상 차단기 점검공사","봉동SS 북전주-봉동#2T/L 차단기 조작시험 북전주SS 북전주-봉동#2T/L 차단기 보통점검","2020-03-25 10:00","2020-03-25 18:00","취소","취소","연속"]
[315,"전북","직할","팔봉봉동#1 T/L","관내 154kV 이상 차단기 점검공사","봉동SS 팔봉-봉동#1T/L 차단기 조작시험","2020-03-23 10:00","2020-03-23 14:00","취소","취소","연속"]
[316,"전북","군산","새만금비응#2 T/L","154kV 61-66 모선보호반 CPU 교체공사","154kV 61-66 모선보호반 CPU 교체공사","2020-03-12 10:00","2020-03-13 18:00","2020-03-12 10:00","2020-03-13 18:00","연속"]
[317,"전북","군산","비응군장#2 T/L","154kV 61-66 모선보호반 CPU 교체공사","154kV 61-66 모선보호반 CPU 교체공사","2020-03-12 10:00","2020-03-13 18:00","2020-03-12 10:00","2020-03-13 18:00","연속"]
[318,"광주전남","강진","삼호화원#2 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치 (C/H No.1)","2020-03-12 14:00","2020-03-12 18:00","취소","취소","연속"]
[319,"광주전남","강진","삼호화원#1 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치 (C/H No.1)","2020-03-12 09:00","2020-03-12 14:00","취소","취소","연속"]
[320,"광주전남","광주","남광주금천#2 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치 (3. 2 : 남광주-금천#7C/H, 3. 3 : 나주-금천#1C/H)","2020-03-02 14:00","2020-03-03 18:00","취소","취소","매일"]
[321,"광주전남","광주","남광주금천#1 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치 (3. 2 : 남광주-금천#7C/H, 3. 3 : 나주-금천#1C/H)","2020-03-02 09:00","2020-03-03 14:00","취소","취소","매일"]
[322,"광주전남","광주","담양일곡#1 T/L","154kV 담양-일곡T/L 190-192호 지장송전선로 지중화 공사","가. 공 사 명 : 담양첨단문화복합단지 지장송전선로 지중화 공사 나. 공사시행 : 요청자 직접시행(담양대숲마루 주식회사) 다. 대상설비 : 154kV 담양-일곡 #1,2T/L 189 ∼ 192호 라. 공사내용 ○ 가공분야 : C/H 철탑2기 신설 및 케이블 접속 ○ 지중분야 : 관로 785m(XLPE 1,200㎟*S*2C)","2020-03-20 08:00","2020-03-22 18:00","취소","취소","연속"]
[323,"광주전남","광주","담양일곡#2 T/L","154kV 담양-일곡T/L 190-192호 지장송전선로 지중화 공사","가. 공 사 명 : 담양첨단문화복합단지 지장송전선로 지중화 공사 나. 공사시행 : 요청자 직접시행(담양대숲마루 주식회사) 다. 대상설비 : 154kV 담양-일곡 #1,2T/L 189 ∼ 192호 라. 공사내용 ○ 가공분야 : C/H 철탑2기 신설 및 케이블 접속 ○ 지중분야 : 관로 785m(XLPE 1,200㎟*S*2C)","2020-03-23 08:00","2020-03-25 18:00","취소","취소","연속"]
[324,"광주전남","광주","신광주일곡#2 T/L","신광주S/S 신광주-일곡#2T/L 송전선로 보호반 이동","신광주,일곡S/S 신광주-일곡#2T/L 송전선로 보호반 교체 전 사전 작업(신광주 측 보호반 이동)","2020-03-31 09:00","2020-03-31 18:00","2020-03-31 09:00","2020-03-31 18:00","연속"]
[325,"광주전남","목포","나주엄다#2 T/L","[20~21년 송전정비회사]154kV나주-엄다#2T/L 아킹혼 설치공사","154kV나주-엄다#2T/L 아킹혼 설치공사","2020-03-02 08:00","2020-03-05 18:00","취소","취소","매일"]
[326,"광주전남","목포","영광홍농 T/L","`20년 목포전력지사 변전정비회사 총액공사","영광S/S 영광-홍농T/L 차단기 조작시험, LA 하자점검, PT 하자점검 홍농S/S 영광-홍농T/L GIS 하자점검","2020-03-24 09:00","2020-03-24 18:00","2020-03-24 09:00","2020-03-24 18:00","연속"]
[327,"광주전남","목포","장성영광#2 T/L","`20년 목포전력지사 변전정비회사 총액공사","영광S/S 장성-영광#2T/L 차단기 조작시험, LA 하자점검","2020-03-18 10:00","2020-03-18 14:00","2020-03-18 10:00","2020-03-18 14:00","연속"]
[328,"광주전남","목포","장성영광#1 T/L","[20~21년 송전정비회사]154kV 장성-영광#1T/L 아킹혼 설치공사","154kV 장성-영광#1T/L 아킹혼 설치공사","2020-03-06 08:00","2020-03-06 18:00","2020-03-06 08:00","2020-03-06 18:00","연속"]
[329,"광주전남","순천","순천율촌#1 T/L","154kV 순천-율촌#1 T/L 정밀점검","20년 가공송전 순시점검 위탁공사 정밀점검","2020-03-02 08:00","2020-03-03 18:00","취소","취소","매일"]
[330,"광주전남","순천","광양순천#1 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치 (C/H No.178)","2020-03-19 09:00","2020-03-19 14:00","취소","취소","연속"]
[331,"광주전남","순천","광양순천#2 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치 (C/H No.178)","2020-03-19 14:00","2020-03-19 18:00","취소","취소","연속"]
[332,"광주전남","순천","순천승주#1 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치 (C/H No.173)","2020-03-23 09:00","2020-03-23 14:00","취소","취소","연속"]
[333,"광주전남","순천","순천승주#2 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치 (C/H No.173)","2020-03-23 14:00","2020-03-23 18:00","취소","취소","연속"]
[334,"광주전남","순천","순천율촌#2 T/L","154kV 순천-율촌#2 T/L 정밀점검","20년 가공송전 순시점검 위탁공사 정밀점검","2020-03-04 08:00","2020-03-05 18:00","취소","취소","매일"]
[335,"광주전남","순천","율촌여수산단#1 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치 (C/H No.1)","2020-03-24 09:00","2020-03-24 14:00","취소","취소","연속"]
[336,"광주전남","순천","율촌여수산단#2 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치 (C/H No.1)","2020-03-24 14:00","2020-03-24 18:00","취소","취소","연속"]
[337,"광주전남","순천","용성여수산단#1 T/L","용성S/S LG 화학 GIS 설치공사","154kV GIS 5CCT 설치","2020-03-18 09:00","2020-03-20 18:00","2020-04-02 15:00","2020-04-03 15:00","연속"]
[338,"광주전남","순천","용성S/S 154kV #60 BUS","용성S/S LG 화학 GIS 설치공사","154kV GIS 5CCT 설치","2020-03-23 09:00","2020-03-27 18:00","취소","취소","연속"]
[339,"광주전남","순천","용성여수산단#1 T/L","용성S/S LG 화학 GIS 설치공사","154kV GIS 5CCT 설치","2020-03-25 09:00","2020-03-27 18:00","취소","취소","연속"]
[340,"광주전남","순천","용성S/S 154kV #65 BUS","용성S/S LG 화학 GIS 설치공사","154kV GIS 5CCT 설치","2020-03-02 09:00","2020-03-20 18:00","취소","취소","연속"]
[341,"광주전남","순천","여천호남TP#1 T/L","154kV 여천-호남T/P#1T/L EB-A 절연유채유","호남T/P 154kV 여천-호남T/P#1T/L EB-A 3상 절연유 채유","2020-03-27 09:00","2020-03-27 18:00","2020-03-27 09:00","2020-03-27 18:00","연속"]
[342,"광주전남","직할","나주금천#1 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치 (C/H No.1)","2020-03-04 09:00","2020-03-04 14:00","취소","취소","연속"]
[343,"광주전남","직할","나주금천#2 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치 (C/H No.1)","2020-03-04 14:00","2020-03-04 18:00","취소","취소","연속"]
[344,"대구","경산","노변효목#1 T/L","154kV 시지분기 지중T/L 건설공사","노변효목T/L M/H#3,4 ~ 시지E/C구간 2파이 분기,XLPE2,000 *4C*0.24km","2020-03-16 09:00","2020-04-08 18:00","2020-03-16 09:00","2020-04-08 18:00","연속"]
[345,"대구","경산","하양반야월#2 T/L","154kV 신서분기 지중T/L 건설공사","신서E/C~154kV 하양-반야월T/L 분기맨홀(2파이 분기) 154kV XLPE1200*2C(D) 0.5km, 154kV XLPE2500*2C 0.5km","2020-03-04 09:00","2020-03-24 18:00","취소","취소","연속"]
[346,"대구","경산","하양반야월#1 T/L","154kV 신서분기 지중T/L 건설공사","신서E/C~154kV 하양-반야월T/L 분기맨홀(2파이 분기) 154kV XLPE1200*2C(D) 0.5km, 154kV XLPE2500*2C 0.5km","2020-03-25 09:00","2020-04-14 18:00","취소","취소","연속"]
[347,"대구","경산","신경산진량 T/L","2020~21년 경산변전 정밀점검공사","경산변전 정밀점검공사(무부하가압)","2020-03-17 17:00","2020-03-17 18:00","2020-03-17 17:00","2020-03-17 18:00","연속"]
[348,"대구","경산","청도밀양#1 T/L","20~21년 달성 송전정비회사 총액공사","항공장애표시구 설치공사(안전 이격)","2020-03-03 14:00","2020-03-03 18:00","2020-03-07 14:00","2020-03-07 18:00","연속"]
[349,"대구","경산","청도밀양#2 T/L","20~21년 달성 송전정비회사 총액공사","항공장애표시구 설치공사(안전 이격)","2020-03-03 07:30","2020-03-03 14:00","2020-03-07 07:30","2020-03-07 14:00","연속"]
[350,"대구","달성","고령쌍림#2 T/L","고령-쌍림#2T/L 정밀점검","고령-쌍림#2T/L 정밀점검","2020-03-24 08:00","2020-03-25 18:00","2020-03-26 08:00","2020-03-28 18:00","연속"]
[351,"대구","달성","고령다산#2 T/L","고령-다산#2T/L 정밀점검","고령-다산#2T/L 정밀점검","2020-03-26 08:00","2020-03-27 18:00","취소","취소","연속"]
[352,"대구","달성","고령S/S 154kV #66 BUS","고령-다산#2T/L 정밀점검","고령-다산#2T/L 정밀점검","2020-03-27 17:00","2020-03-27 18:00","취소","취소","연속"]
[353,"대구","달성","고령쌍림#1 T/L","고령-쌍림#1T/L 정밀점검","고령-쌍림#1T/L 정밀점검","2020-03-19 08:00","2020-03-20 18:00","2020-03-31 08:00","2020-04-01 18:00","연속"]
[354,"대구","달성","고령다산#1 T/L","고령-다산#1T/L 정밀점검","고령-다산#1T/L 정밀점검","2020-03-30 08:00","2020-03-31 18:00","취소","취소","연속"]
[355,"대구","달성","대구봉덕#1 T/L","C/H 피뢰기 점검","154kV 대구-봉덕#1T/L 대구봉덕C/H","2020-03-23 09:00","2020-03-23 14:00","취소","취소","연속"]
[356,"대구","달성","대구봉덕#2 T/L","C/H 피뢰기 점검","154kV 대구-봉덕#2T/L 대구봉덕C/H","2020-03-23 14:00","2020-03-23 18:00","취소","취소","연속"]
[357,"대구","달성","대구청도#2 T/L","20~21년 달성 송전정비회사 총액공사","항공장애표시구 설치공사(안전 이격)","2020-03-03 14:00","2020-03-03 18:00","2020-03-07 14:00","2020-03-07 18:00","연속"]
[358,"대구","달성","대구청도#1 T/L","20~21년 달성 송전정비회사 총액공사","항공장애표시구 설치공사(안전 이격)","2020-03-03 07:30","2020-03-03 14:00","2020-03-07 07:30","2020-03-07 14:00","연속"]
[359,"대구","포항","상정양북 T/L","154kV 영일-입실T/L 안전이격거리확보공사","154kV 영일-입실T/L 안전이격거리확보공사 철탑 철거 : 154kV 영일-입실T/L No.42 ~ 47(6기) 철탑 설치 : 154kV 영일-입실T/L No.42, 44, 46, 47 전선 및 가공지선 교체 : 154kV 영일-입실T/L No.40~47호 간","2020-03-02 08:00","2020-03-16 18:00","2020-02-29 08:00","2020-03-15 18:00","연속"]
[360,"대구","포항","영일입실 T/L","154kV 영일-입실T/L 안전이격거리확보공사","154kV 영일-입실T/L 안전이격거리확보공사 철탑 철거 : 154kV 영일-입실T/L No.42 ~ 47(6기) 철탑 설치 : 154kV 영일-입실T/L No.42, 44, 46, 47 전선 및 가공지선 교체 : 154kV 영일-입실T/L No.40~47호 간","2020-03-02 08:00","2020-03-16 18:00","2020-02-29 08:00","2020-03-15 18:00","연속"]
[361,"대구","포항","울주입실#2 T/L","20-21 포항전력지사 가공송전 정비회사 총액공사","345kV울주-월성NP#2 T/L 전력선 소도체 이도조정 안전확보","2020-03-24 08:00","2020-03-25 18:00","2020-03-24 08:00","2020-03-25 18:00","연속"]
[362,"경북","구미","구미광평#1 T/L","2020-21년 구미전력지사 변전정비업체 총액공사","- 154kV 모선보호반 대체공사","2020-03-19 13:00","2020-03-19 13:30","2020-03-19 13:00","2020-03-19 13:30","연속"]
[363,"경북","구미","구미광평#2 T/L","2020-21년 구미전력지사 변전정비업체 총액공사","- 154kV 모선보호반 대체공사","2020-03-19 13:30","2020-03-19 14:00","2020-03-19 13:30","2020-03-19 14:00","연속"]
[364,"경북","직할","안동동안동#1 T/L","2020년 가공송전 위탁공사(154kV 안동-동안동T/L 정밀점검)","No.1-20","2020-03-09 08:00","2020-03-10 18:00","2020-03-09 08:00","2020-03-10 18:00","연속"]
[365,"경북","직할","안동동안동#2 T/L","2020년 가공송전 위탁공사(154kV 안동-동안동T/L 정밀점검)","No.1-20","2020-03-11 08:00","2020-03-12 18:00","2020-03-11 08:00","2020-03-12 18:00","연속"]
[366,"경북","직할","동안동임하HP T/L","2020년 가공송전 위탁공사(154kV 동안동-임하HPT/L 정밀점검)","No.1-29","2020-03-16 09:00","2020-03-18 18:00","2020-03-16 09:00","2020-03-18 18:00","연속"]
[367,"경북","직할","현종산풍력평해#2 T/L","154kV 평해S/S 옥외철구설비 현대화 공사","○현종산풍력-평해#2T/L GIS로 전환 - 인출모선 조정, 보호반 이설, 전력선 교체, OPGW 이설, 준공시험","2020-03-24 09:00","2020-04-01 18:00","2020-03-24 09:00","2020-04-01 18:00","연속"]
[368,"경북","직할","현종산풍력평해#1 T/L","20~21년 경북본부 직할 변전정비회사 총액공사","초기점검","2020-03-18 10:00","2020-03-18 18:00","2020-03-18 10:00","2020-03-18 18:00","연속"]
[369,"부산울산","동부산","구서노포#2 T/L","'20-21년 송전정비회사 총액공사","애자교체 : 1호","2020-03-27 08:00","2020-03-27 18:00","2020-03-27 08:00","2020-03-27 18:00","연속"]
[370,"부산울산","동부산","구서명장#1 T/L","'20-21년 송전정비회사 총액공사","애자교체 : 14, 18, 20호","2020-03-25 08:00","2020-03-25 18:00","2020-03-25 08:00","2020-03-25 18:00","연속"]
[371,"부산울산","동부산","구서명장#2 T/L","'20-21년 송전정비회사 총액공사","애자교체 : 26호","2020-03-26 08:00","2020-03-26 18:00","2020-03-26 08:00","2020-03-26 18:00","연속"]
[372,"부산울산","동부산","수영정보#2 T/L","수영S/S 170kV GIS 차단기 동작시험","1. 수영S/S 170kV 657GIS 차단기 동작시험(수영-정보#2T/L) 2. (병행)정보S/S 170kV 637GIS 차단기 동작시험","2020-03-24 09:30","2020-03-24 14:00","취소","취소","연속"]
[373,"부산울산","동부산","신양산구서#1 T/L","[2차] 345kV 신양산S/S 현대화공사","1. 내용 - 154kV 신양산-구서#1T/L 인출변경 - 154kV #62M.Tr 1차 인출변경 2. 배전선로 이설 - 8개D/L 이설","2020-03-11 09:00","2020-03-20 18:00","2020-03-11 09:00","2020-03-20 18:00","연속"]
[374,"부산울산","동부산","정관고리NP T/L","'20-21년 송전정비회사 총액공사","애자교체 : 3호","2020-03-20 08:00","2020-03-20 18:00","2020-03-20 08:00","2020-03-20 18:00","연속"]
[375,"부산울산","북부산","매리김해#1 T/L","2020년도 북부산 가공송전 순시점검 위탁공사","154kV 호포-매리#1T/L 송전선로 정밀점검(1~25호, 22기) 병가구간 작업자 안전확보","2020-03-22 09:00","2020-03-22 18:00","2020-03-22 09:00","2020-03-22 18:00","매일"]
[376,"부산울산","북부산","북부산삼랑진PP T/L","북부산S/S 154kV 송전선로 인출Bay 조정 공사","북부산S/S 154kV 송전선로 인출Bay 조정 공사 1차(#62BUS 시험가압 2H)","2020-03-27 12:00","2020-03-27 14:00","2020-03-27 12:00","2020-03-27 14:00","연속"]
[377,"부산울산","북부산","북부산삼랑진PP T/L","북부산S/S 154kV 송전선로 인출Bay 조정 공사","북부산S/S 154kV 송전선로 인출Bay 조정 공사 1차 (6G1 철거 안전이격)","2020-03-25 12:00","2020-03-26 18:00","2020-03-25 12:00","2020-03-26 18:00","연속"]
[378,"부산울산","북부산","북부산S/S 154kV #62 BUS","북부산S/S 154kV 송전선로 인출Bay 조정 공사","북부산S/S 154kV 송전선로 인출Bay 조정 공사 1차 (시험가압2h &6G1 DS 철거)","2020-03-25 12:00","2020-03-27 14:00","2020-03-25 12:00","2020-03-27 14:00","연속"]
[379,"부산울산","북부산","북부산양산 T/L","북부산S/S 154kV 송전선로 인출Bay 조정 공사","북부산S/S 154kV 송전선로 인출Bay 조정 공사 1차(6G7 개조이설)","2020-03-24 08:00","2020-04-24 18:00","2020-03-24 08:00","2020-04-24 18:00","연속"]
[380,"부산울산","북부산","북부산삼랑진PP T/L","북부산S/S 154kV 송전선로 인출Bay 조정 공사","북부산S/S 154kV 송전선로 인출Bay 조정 공사 1차 (6G2 철거 안전이격)","2020-03-24 08:00","2020-03-24 18:00","2020-03-24 08:00","2020-03-24 18:00","연속"]
[381,"부산울산","북부산","북부산S/S 154kV #67 BUS","북부산S/S 154kV 송전선로 인출Bay 조정 공사","북부산S/S 154kV 송전선로 인출Bay 조정 공사 1차 (6G2 DS 철거)","2020-03-24 08:00","2020-03-25 14:00","2020-03-24 08:00","2020-03-25 14:00","연속"]
[382,"부산울산","북부산","북부산S/S 154kV #61 BUS","북부산S/S 154kV 송전선로 인출Bay 조정 공사","북부산S/S 154kV 송전선로 인출Bay 조정 공사 1차 (신 6D7,6D1 설치)","2020-03-30 08:00","2020-04-03 18:00","2020-03-30 08:00","2020-04-03 18:00","연속"]
[383,"부산울산","북부산","언양산막#2 T/L","20-21년도 북부산전력지사 가공송전정비협력 총액공사","154kV 언양-산막#2T/L 회전스페이서 교체","2020-03-02 13:00","2020-03-02 18:00","2020-03-02 13:00","2020-03-02 18:00","연속"]
[384,"부산울산","북부산","언양산막#1 T/L","20-21년도 북부산전력지사 가공송전정비협력 총액공사","154kV 언양-산막#1T/L 회전스페이서 교체","2020-03-02 09:00","2020-03-02 13:00","2020-03-02 09:00","2020-03-02 13:00","연속"]
[385,"부산울산","북부산","서창산막#1 T/L","154kV 서창-산막T/L 56~59호 지장철탑이설(요청자)","ㅇ 공사개요 : 154kV 서창-산막T/L 56~59호 ㅇ 공사내용 : 신설2기, 철거 2기, 전선교체 0.675km","2020-03-07 07:00","2020-03-08 18:00","2020-03-07 07:00","2020-03-08 18:00","연속"]
[386,"부산울산","북부산","서창산막#2 T/L","154kV 서창-산막T/L 56~59호 지장철탑이설(요청자)","ㅇ 공사개요 : 154kV 서창-산막T/L 56~59호 ㅇ 공사내용 : 신설2기, 철거 2기, 전선교체 0.675km","2020-03-14 07:00","2020-03-15 18:00","2020-03-14 07:00","2020-03-15 18:00","연속"]
[387,"부산울산","북부산","주촌삼계#2 T/L","2020년도 북부산 가공송전 순시점검 위탁공사","154kV 주촌-삼계#2T/L 송전선로 정밀점검(31~38호, 8기)","2020-03-19 09:00","2020-03-19 18:00","2020-03-19 09:00","2020-03-19 18:00","연속"]
[388,"부산울산","북부산","주촌삼계#1 T/L","2020년도 북부산 가공송전 순시점검 위탁공사","154kV 주촌-삼계#1T/L 송전선로 정밀점검(31~38호, 8기)","2020-03-18 09:00","2020-03-18 18:00","2020-03-18 09:00","2020-03-18 18:00","연속"]
[389,"부산울산","북부산","김해어방#2 T/L","2020년 북부산 변전협력회사 총액공사","김해S/S 154kV 김해-어방#2T/L GIS 하자점검","2020-03-31 10:00","2020-03-31 18:00","2020-03-31 10:00","2020-03-31 18:00","연속"]
[390,"부산울산","북부산","호포매리#1 T/L","2020년도 북부산 가공송전 순시점검 위탁공사","154kV 호포-매리#1T/L 송전선로 정밀점검(1~25호, 22기)","2020-03-21 09:00","2020-03-22 18:00","2020-03-21 09:00","2020-03-22 18:00","매일"]
[391,"부산울산","서부산","서부산다대#1 T/L","154kV 서부산-다대T/L 지장이설 및 선종교체공사","선로명 : 154kV 서부산-다대#1T/L 구 간 : J/B#2 ~ J/B#5 (1.01km) 작업내용 : 을숙도대교-장림고개간 지하차도건설공사에 따른 지장이설 및 케이블 선종교체","2020-03-02 09:00","2020-05-04 18:00","2020-03-02 09:00","2020-05-04 18:00","연속"]
[392,"부산울산","울산","동울산방어진 T/L","2020년 가공송전선로 순시점검 위탁공사","ㅁ 154kV 동울산-방어진T/L, 동울산-효문#3T/L 정밀점검 - 대상기수 : 31기","2020-03-23 08:30","2020-03-26 18:00","2020-03-23 08:30","2020-03-26 18:00","연속"]
[393,"부산울산","울산","두왕영남TP#1 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2020-03-16 07:00","2020-03-20 18:00","2020-03-16 07:00","2020-03-20 18:00","연속"]
[394,"부산울산","울산","두왕영남TP#1 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2020-03-24 07:00","2020-03-24 18:00","2020-03-24 07:00","2020-03-24 18:00","연속"]
[395,"부산울산","울산","두왕영남TP#2 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2020-03-21 07:00","2020-03-23 18:00","2020-03-21 07:00","2020-03-23 18:00","연속"]
[396,"부산울산","울산","신울산명례#1 T/L","2020년 154kV 개폐장치 정밀점검공사","- 신울산S/S 154kV #67-68BUS SEC GIS 정밀점검관련 시험가압 1H","2020-03-20 17:00","2020-03-20 18:00","2020-03-20 17:00","2020-03-20 18:00","연속"]
[397,"부산울산","울산","신울산S/S 154kV #63 BUS","2020년 154kV 개폐장치 정밀점검공사","- 신울산S/S 154kV #62-63BUS SEC GIS 정밀점검관련 시험가압 1H","2020-03-17 17:00","2020-03-17 18:00","2020-03-17 17:00","2020-03-17 18:00","연속"]
[398,"부산울산","울산","신울산명례#1 T/L","2020년 154kV 개폐장치 정밀점검공사","- 신울산S/S 154kV #62-63BUS SEC GIS 정밀점검관련 시험가압 1H","2020-03-17 17:00","2020-03-17 18:00","2020-03-17 17:00","2020-03-17 18:00","연속"]
[399,"부산울산","울산","신울산S/S 154kV #62-#63 SEC CB","2020년 154kV 개폐장치 정밀점검공사","- 신울산S/S 154kV #62-63BUS SEC GIS 정밀점검","2020-03-16 09:00","2020-03-17 18:00","2020-03-16 09:00","2020-03-17 18:00","연속"]
[400,"부산울산","울산","신울산두왕#1 T/L","2020년 가공송전선로 순시점검 위탁공사","ㅁ (안전이격) 154kV 신울산-울산#1T/L 정밀점검관련 안전이격확보","2020-03-11 08:30","2020-03-11 18:00","2020-03-11 08:30","2020-03-11 18:00","연속"]
[401,"부산울산","울산","신울산울산#2 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2020-03-11 07:00","2020-03-12 18:00","2020-03-11 07:00","2020-03-12 18:00","연속"]
[402,"부산울산","울산","신울산S/S 154kV #68 BUS","2020년 154kV 개폐장치 정밀점검공사","- 신울산S/S 154kV #67-68BUS SEC GIS 정밀점검관련 시험가압 1H","2020-03-20 17:00","2020-03-20 18:00","2020-03-20 17:00","2020-03-20 18:00","연속"]
[403,"부산울산","울산","신울산울산#1 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2020-03-09 07:00","2020-03-10 18:00","2020-03-09 07:00","2020-03-10 18:00","연속"]
[404,"부산울산","울산","신울산S/S 154kV #67-#68 SEC CB","2020년 154kV 개폐장치 정밀점검공사","- 신울산S/S 154kV #67-68BUS SEC GIS 정밀점검","2020-03-19 17:00","2020-03-20 18:00","2020-03-19 17:00","2020-03-20 18:00","연속"]
[405,"부산울산","울산","온산처용#2 T/L","20~21년 변전협력 총액공사","- 양단 송전선로 보호반 교체 - 온산측 154kV 온산-처용#2T/L 667GIS 정밀점검","2020-03-23 09:00","2020-03-25 18:00","2020-03-23 09:00","2020-03-25 18:00","연속"]
[406,"부산울산","울산","용연처용#2 T/L","20~21년 변전협력 총액공사","- 용연S/S 154kV 용연-처용#2T/L GIS 하자점검 및 피뢰기 보통점검","2020-03-13 09:00","2020-03-13 18:00","2020-03-13 09:00","2020-03-13 18:00","연속"]
[407,"부산울산","울산","용연처용#1 T/L","20~21년 변전협력 총액공사","- 용연S/S 154kV 용연-처용#1T/L GIS 하자점검 및 피뢰기 보통점검","2020-03-12 09:00","2020-03-12 18:00","2020-03-12 09:00","2020-03-12 18:00","연속"]
[408,"부산울산","울산","용연울산TP#1 T/L","2020년 154kV 상반기 개폐장치 정밀점검공사","- 용연S/S 154kV #1M.Tr 1차 정밀점검 후 시험가압 1H","2020-03-27 09:00","2020-03-27 18:00","2020-03-27 09:00","2020-03-27 18:00","연속"]
[409,"부산울산","울산","울산울산TP#2 T/L","2020년 154kV 개폐장치 정밀점검공사","- 울산S/S 154kV 울산-울산TP#2T/L 687GIS 정밀점검","2020-03-04 09:00","2020-03-06 18:00","2020-03-04 09:00","2020-03-06 18:00","연속"]
[410,"부산울산","직할","개금범천#1 T/L","범천S/S 154kV 장기사용 GIS 대체공사","범천S/S 154kV 장기사용 GIS 대체공사 - 154kV GIS * 7CCT 철거 및 대체","2020-03-23 09:00","2020-04-14 18:00","취소","취소","연속"]
[411,"부산울산","직할","양정범천 T/L","범천S/S 154kV 장기사용 GIS 대체공사","범천S/S 154kV 장기사용 GIS 대체공사 시험가압","2020-03-25 17:00","2020-03-25 19:00","취소","취소","연속"]
[412,"경남","직할","신김해진영#2 T/L","2020년도 가공송전 순시점검 위탁공사","송전선로 정밀점검(345kV 신김해-창원#2T/L 53호)을 위한 안전거리 확보휴전","2020-03-14 08:00","2020-03-14 18:00","2020-03-14 08:00","2020-03-14 18:00","연속"]
[413,"경남","직할","신김해진영#1 T/L","2020년도 가공송전 순시점검 위탁공사","송전선로 정밀점검(345kV 신김해-창원#1T/L 53호)을 위한 안전거리 확보 휴전","2020-03-21 08:00","2020-03-21 18:00","2020-03-21 08:00","2020-03-21 18:00","연속"]
[414,"경남","진주","의령S/S 154kV #60-#65 BUS TIE CB","의령S/S 154kV #1 BUS TIE CB(6100) 조작시험","의령S/S 154kV #1 BUS TIE CB(6100) 조작시험","2020-03-06 10:00","2020-03-06 14:00","2020-03-06 10:00","2020-03-06 14:00","연속"]
[415,"경남","진주","하동개양#1 T/L","154kV 하동-개양T/L 송전선로 정밀점검 및 안전이격거리확보","154kV 하동-개양T/L 송전선로 정밀점검 및 안전이격거리확보","2020-03-22 08:30","2020-03-22 17:00","취소","취소","연속"]
[416,"경남","진주","하동개양#2 T/L","154kV 하동-개양T/L 송전선로 정밀점검 및 안전이격거리확보","154kV 하동-개양T/L 송전선로 정밀점검 및 안전이격거리확보","2020-03-22 08:30","2020-03-22 17:00","취소","취소","연속"]
[417,"경남","진주","하동하동화력#1 T/L","하동S/S 154kV 하동-하동TP#1T/L CB(637) 조작시험","하동S/S 154kV 하동-하동TP#1T/L CB(637) 조작시험","2020-03-25 10:00","2020-03-25 14:00","2020-03-25 10:00","2020-03-25 14:00","연속"]
[418,"경남","진주","하동개양#2 T/L","154kV 하동-개양T/L 송전선로 정밀점검 및 안전이격거리확보","154kV 하동-개양T/L 송전선로 정밀점검 및 안전이격거리확보","2020-03-29 08:30","2020-03-29 17:00","취소","취소","연속"]
[419,"경남","진주","하동하동화력#2 T/L","하동S/S 154kV 하동-하동TP#2T/L CB(647) 조작시험","하동S/S 154kV 하동-하동TP#2T/L CB(647) 조작시험","2020-03-25 14:00","2020-03-25 17:00","2020-03-25 14:00","2020-03-25 17:00","연속"]
[420,"경남","진주","하동개양#1 T/L","154kV 하동-개양T/L 송전선로 정밀점검 및 안전이격거리확보","154kV 하동-개양T/L 송전선로 정밀점검 및 안전이격거리확보","2020-03-29 08:30","2020-03-29 17:00","취소","취소","연속"]
[421,"경남","진주","쌍림합천#2 T/L","합천S/S 154kV 쌍림-합천#2T/L CB(657) 보통점검","합천S/S 154kV 쌍림-합천#2T/L CB(657) 보통점검","2020-03-30 14:00","2020-03-30 17:00","2020-03-30 14:00","2020-03-30 17:00","연속"]
[422,"경남","진주","합천수력#1 T/L","합천S/S 154kV 합천수력#1T/L CB(637) 조작시험","합천S/S 154kV 합천수력#1T/L CB(637) 조작시험","2020-03-12 10:00","2020-03-12 14:00","2020-03-12 10:00","2020-03-12 14:00","연속"]
[423,"경남","진주","합천수력#2 T/L","합천S/S 154kV 합천수력#2T/L CB(647) 조작시험","합천S/S 154kV 합천수력#2T/L CB(647) 조작시험","2020-03-12 14:00","2020-03-12 17:00","2020-03-12 14:00","2020-03-12 17:00","연속"]
[424,"경남","진주","쌍림합천#1 T/L","합천S/S 154kV 쌍림-합천#1T/L CB(667) 보통점검","합천S/S 154kV 쌍림-합천#1T/L CB(667) 보통점검","2020-03-30 10:00","2020-03-30 14:00","2020-03-30 10:00","2020-03-30 14:00","연속"]
[425,"경남","통영","통영거제#2 T/L","거제S/S #4M.Tr 1차 GIS 정밀점검 시험가압","거제S/S #4M.Tr 1차 GIS 정밀점검 시험가압","2020-03-27 07:00","2020-03-27 08:00","2020-03-27 07:00","2020-03-27 08:00","연속"]
[426,"경남","통영","통영거제#2 T/L","거제S/S #3M.Tr 1차 GIS 정밀점검 시험가압","거제S/S #3M.Tr 1차 GIS 정밀점검 시험가압","2020-03-25 07:00","2020-03-25 08:00","2020-03-25 07:00","2020-03-25 08:00","연속"]
[427,"경남","통영","삼천포사천#1 T/L","154kV 삼천포-사천#1T/L 송전선로 정밀점검","154kV 삼천포-사천#1T/L 송전선로 정밀점검 및 안전거리확보","2020-03-09 09:00","2020-03-15 18:00","2020-03-09 09:00","2020-03-15 18:00","매일"]
[428,"경남","통영","삼천포사천#2 T/L","154kV 삼천포-사천#2T/L 송전선로 정밀점검","154kV 삼천포-사천#2T/L 송전선로 정밀점검 및 안전거리확보","2020-03-14 09:00","2020-03-20 18:00","2020-03-14 09:00","2020-03-20 18:00","매일"]
[429,"경남","함안","마산S/S 154kV 마산-수출#2T/L GIS","마산S/S 154kV 마산-수출#2T/L GIS 보통점검","마산S/S 154kV 마산-수출#2T/L GIS 보통점검","2020-03-06 09:30","2020-03-06 17:30","2020-03-06 09:30","2020-03-06 17:30","연속"]
[430,"경남","함안","마산S/S 154kV 마산-수출#1T/L GIS","마산S/S 154kV 마산-수출#1T/L GIS 보통점검","마산S/S 154kV 마산-수출#1T/L GIS 보통점검","2020-03-05 09:30","2020-03-05 17:30","2020-03-05 09:30","2020-03-05 17:30","연속"]
[431,"경남","함안","초동밀양#2 T/L","154kV 초동-밀양#1T/L 애자 발취(초동-밀양#2 T/L 안전이격)","154kV 초동-밀양#1T/L 11,12,16호 자기애자 발취 및 교체 작업 안전이격 확보를 위한 154kV 초동-밀양#2T/L 휴전","2020-03-21 08:30","2020-03-21 18:00","2020-03-21 08:30","2020-03-21 18:00","연속"]
[432,"경남","함안","초동밀양#1 T/L","154kV 초동-밀양#1T/L 장기사용 자기애자 발취","154kV 초동-밀양#1T/L 11,12,16호 자기애자 발취 및 교체","2020-03-21 08:30","2020-03-21 18:00","2020-03-21 08:30","2020-03-21 18:00","연속"]

{"sheet":"시송전설비","index":4,"n_rows":1,"n_cols":17,"rows_kept":1,"cut":false,"hidden":true,"merged":[[0,16,0,21]]}
["1차\n사업소","2차\n사업소","설비명",{"$nulls":8},"연간\n반영","비고","Key-point","시송전설비 여부","찾는함수","=IF(ISERROR(VLOOKUP(D5,시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D5,시송전설비!$C$2:$O$130,13,0))"]