{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":20,"n_cols":13,"rows_kept":20,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2020년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2020년도 5월 휴전계획서"}]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기","성남","신안성S/S #4 M.Tr A-1","20년 성남전력 765kV M.Tr 보통점검","신안성S/S 765kV #4M.Tr 보통점검","2020-05-11 09:00","2020-05-22 18:00","2020-05-11 09:00","2020-05-22 18:00","연속"]
[2,"경기","성남","신안성신가평 T/L","2020-2021년 성남전력지사 가공송전정비회사 총액공사","- 765kV 신안성-신가평T/L 항공장애표시도장(22기)","2020-05-06 07:00","2020-05-29 18:00","취소","취소","연속"]
[3,"충북","직할","신중부-신안성#2T/L-#5 M.Tr 1차 TIE CB A","765kV 신중부S/S 초기점검공사","신중부S/S 765kV GIS 초기점검","2020-05-13 09:00","2020-05-14 18:00","2020-05-13 09:00","2020-05-14 18:00","연속"]
[4,"충북","직할","신중부S/S 765kV #5 M.Tr 1차 CB A","765kV 신중부S/S 초기점검공사","신중부S/S 765kV GIS 초기점검","2020-05-11 09:00","2020-05-12 18:00","2020-05-11 09:00","2020-05-12 18:00","연속"]
[5,"충북","직할","신중부S/S 765kV #4 M.Tr 1차 CB A","765kV 신중부S/S 초기점검공사","신중부S/S 765kV GIS 초기점검","2020-05-06 09:00","2020-05-07 18:00","2020-05-06 09:00","2020-05-07 18:00","연속"]
[6,"대전충남","서산","당진화력S/Y 765kV 6호기 1차 CB A","20년 서산P/O 765kV GIS 정밀점검공사","당진화력S/S 765kV 8571 GIS 정밀점검","2020-05-18 09:00","2020-05-29 18:00","2020-05-18 09:00","2020-05-29 18:00","연속"]
[7,"대전충남","서산","신서산S/S 765kV 신서산-신중부#2T/L CB A","20년 서산P/O 765kV GIS 정밀점검공사","신서산S/S 765kV 8671 GIS 정밀점검","2020-05-04 09:00","2020-05-15 18:00","2020-05-04 09:00","2020-05-15 18:00","연속"]
[8,"부산울산","동부산","신고리N/P #2 Tie-Tr","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(71-72-0 - 4시간)","2020-05-23 09:00","2020-05-23 13:00","2020-05-29 16:00","2020-05-29 18:00","연속"]
[9,"부산울산","동부산","신고리N/P #3 Tie-Tr","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(7677 - 2시간)","2020-05-23 09:00","2020-05-23 11:00","취소","취소","연속"]
[10,"부산울산","동부산","신고리N/P #2 Tie-Tr","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(76-77-0 - 2시간)","2020-05-30 09:00","2020-05-30 11:00","취소","취소","연속"]
[11,"부산울산","동부산","신고리N/P #2 Tie-Tr","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(7D71 - 4시간)","2020-05-16 09:00","2020-05-16 13:00","2020-05-22 16:00","2020-05-22 18:00","연속"]
[12,"부산울산","동부산","신고리N/P #2 Tie-Tr","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(7B71 - 4시간)","2020-05-09 09:00","2020-05-09 13:00","2020-05-15 16:00","2020-05-15 18:00","연속"]
[13,"경남","함안","북경남S/S 765kV #4 M.Tr 1차 CB","765kV 북경남SS GIS(8672CB) 보통점검","765kV 북경남SS GIS(8672CB) 보통점검","2020-05-11 09:00","2020-05-12 18:00","2020-05-11 09:00","2020-05-12 18:00","연속"]
[14,"경남","함안","북경남S/S 765kV #5 M.Tr 1차 CB","765kV 북경남SS GIS(8772CB) 보통점검","765kV 북경남SS GIS(8772CB) 보통점검","2020-05-08 09:00","2020-05-09 18:00","2020-05-08 09:00","2020-05-09 18:00","연속"]
[15,"경남","함안","북경남S/S 765kV #3 M.Tr 1차 CB","765kV 북경남SS GIS(8572CB) 보통점검","765kV 북경남SS GIS(8572CB) 보통점검","2020-05-13 09:00","2020-05-14 18:00","2020-05-13 09:00","2020-05-14 18:00","연속"]
[16,"경남","함안","북경남S/S #1 BUS-#5M.Tr 1차 TIE CB","765kV 북경남SS GIS(8700CB) 보통점검","765kV 북경남SS GIS(8700CB) 보통점검","2020-05-06 09:00","2020-05-07 18:00","2020-05-06 09:00","2020-05-07 18:00","연속"]

{"sheet":"345송부","index":1,"n_rows":301,"n_cols":13,"rows_kept":301,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2020년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2020년도 5월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","강남","신양재S/S 345kV #2 Sh.R","362kV GIS 초기점검 - 변전협력","362kV #2Sh.R GIS 초기점검","2020-05-08 10:00","2020-05-08 18:00","2020-05-08 10:00","2020-05-08 18:00","연속"]
[2,"남서울","강남","신양재S/S 345kV #1 Sh.R","362kV GIS 초기점검 - 변전협력","362kV #1Sh.R GIS 초기점검","2020-05-07 10:00","2020-05-07 18:00","2020-05-07 10:00","2020-05-07 18:00","연속"]
[3,"남서울","동서울","동서울S/S #4 M.Tr","서울 동남권지역 전기공급시설 전력구공사(동서울#2-강남5차)","H-Pile 인발 및 해체","2020-05-20 09:00","2020-05-20 18:00","2020-05-20 09:00","2020-05-20 18:00","연속"]
[4,"남서울","동서울","동서울S/S 345kV #2 Sh.R 1차 CB A (7A72A)","345kV GIS 초기점검","345kV 7A72, 7079 GIS 초기점검","2020-05-12 09:00","2020-05-12 18:00","취소","취소","연속"]
[5,"남서울","동서울","동서울S/S 345kV #75-#76 SEC CB A (75-76-0A)","345kV GIS 보통점검","345kV GIS 보통점검","2020-05-12 09:00","2020-05-12 18:00","취소","취소","연속"]
[6,"남서울","동서울","동서울S/S 345kV #70-#71 SEC CB A (70-71-0A)","345kV GIS 보통점검","345kV GIS 보통점검","2020-05-11 09:00","2020-05-11 18:00","취소","취소","연속"]
[7,"남서울","영등포","신광명S/S 345kV #70-#71 SEC CB (70-71-0)","신광명S/S 345kV #70-71 SEC 동작불량 정비","- GCB 결상트립 관련 점검","2020-05-18 09:00","2020-05-19 18:00","2020-05-18 09:00","2020-05-19 18:00","연속"]
[8,"남서울","영등포","서서울신광명#1 T/L","345kV 신광명S/S GIS 용량대체 및 SW 증설공사","- GIS(63kA 6,300A) 24CB 설치 - GIS(40kA 4,000A) 2CB 철거 - 기기기초 및 기타부대공사 1식","2020-05-28 10:00","2020-05-30 18:00","취소","취소","연속"]
[9,"남서울","영등포","신광명S/S 345kV 영등포#2T/L TIE CB A (7600A)","신광명S/S 345kV GCB 보통점검(7600)","- 차단기 동작시험 - GIS 조작시험 - 코일저항, 절연저항 측정 - 주도체저항 측정","2020-05-14 09:00","2020-05-14 18:00","2020-05-14 09:00","2020-05-14 18:00","연속"]
[10,"남서울","영등포","서서울신광명#2 T/L","345kV 신광명S/S GIS 용량대체 및 SW 증설공사","- GIS(63kA 6,300A) 24CB 설치 - GIS(40kA 4,000A) 2CB 철거 - 기기기초 및 기타부대공사 1식","2020-05-25 10:00","2020-05-27 18:00","취소","취소","연속"]
[11,"남서울","영등포","신시흥신광명#1 T/L","345kV 신광명S/S GIS 용량대체 및 SW 증설공사","- GIS(63kA 6,300A) 24CB 설치 - GIS(40kA 4,000A) 2CB 철거 - 기기기초 및 기타부대공사 1식","2020-05-21 10:00","2020-05-23 18:00","취소","취소","연속"]
[12,"남서울","영등포","신시흥신광명#2 T/L","345kV 신광명S/S GIS 용량대체 및 SW 증설공사","- GIS(63kA 6,300A) 24CB 설치 - GIS(40kA 4,000A) 2CB 철거 - 기기기초 및 기타부대공사 1식","2020-05-18 10:00","2020-05-20 18:00","취소","취소","연속"]
[13,"남서울","영등포","신광명S/S 345kV #75 BUS","신광명S/S 345kV #75-#76 SEC 불량사항 정비","○ 75-76-1DS A상 개방 중 과전류 발생하여 계전기 동작으로 개방 불가 ○ #75 BUS 휴전을 통하여 옥외철구 상단 DS 구동메커니즘 상태 확인 및 내부 점검 ○ 고착에 의한 과부하 발생으로 추정하여, 내부 이물질 제거 등 시행 예정","2020-05-16 09:00","2020-05-17 18:00","취소","취소","연속"]
[14,"남서울","직할","영등포S/S 345kV #2 Sh.R","영등포S/S 345kV GIS 정밀점검공사","영등포S/S 345kV GIS 정밀점검공사 다빈도 차단기 정밀점검","2020-05-18 09:00","2020-05-21 18:00","취소","취소","연속"]
[15,"남서울","직할","영등포S/S 345kV #1 Sh.R","영등포S/S 345kV GIS 정밀점검공사","영등포S/S 345kV GIS 정밀점검공사 다빈도 차단기 정밀점검","2020-05-11 09:00","2020-05-14 18:00","2020-05-25 09:00","2020-05-28 18:00","연속"]
[16,"인천","김포","신김포S/S 345kV #1Sh.R-TIE GIS","신김포S/S 345kV 7100 GIS CB 발췌점검","신김포S/S 345kV #1Sh.R-TIE GIS(7100) 발췌점검","2020-05-11 09:00","2020-05-14 18:00","2020-05-11 09:00","2020-05-14 18:00","연속"]
[17,"인천","김포","신김포서인천CC T/L","345kV 신김포-서인천CCT/L 자기애관 교체공사","○ 대상설비 : 345kV 아라뱃길C/H EBA 6상 ○ 공사내용 : 자기애관 대체 폴리머애관 교체공사","2020-05-11 09:00","2020-05-24 20:00","2020-05-11 09:00","2020-05-24 20:00","연속"]
[18,"인천","김포","신김포S/S 345kV 신김포-신인천CC T/L GIS","신김포S/S 345kV 7471 GIS CB 정밀점검","신김포S/S 345kV 신김포-신인천CC T/L GIS(7471) 정밀점검","2020-05-25 09:00","2020-05-28 18:00","2020-05-25 09:00","2020-05-28 18:00","연속"]
[19,"인천","김포","신김포S/S 345kV #2Sh.R 1차 GIS","신김포S/S 345kV 7271 GIS CB 발췌점검","신김포S/S 345kV #2Sh.R 1차 GIS(7271) 발췌점검","2020-05-18 09:00","2020-05-21 18:00","2020-05-18 09:00","2020-05-21 18:00","연속"]
[20,"인천","부평","서인천C/C 345kV 서인천CC-신부평#4T/L CB A (7A72_A)","서인천복합S/Y 7A72 GIS 하자점검","서인천복합S/Y 7A72 GIS 하자점검","2020-05-27 09:00","2020-05-27 18:00","2020-05-27 09:00","2020-05-27 18:00","연속"]
[21,"인천","부평","서인천C/C 345kV 서인천CC신부평#1-#4T/L TIE CB A (7A00_A)","서인천복합S/Y 7A00 GIS 하자점검","서인천복합S/Y 7A00 GIS 하자점검","2020-05-25 09:00","2020-05-25 18:00","2020-05-25 09:00","2020-05-25 18:00","연속"]
[22,"인천","부평","서인천C/C 345kV 서인천CC-신부평#4T/L CB A (7A72_A)","서인천복합S/Y 7A72GIS 하자점검","서인천복합S/Y 7A72GIS 하자점검","2020-05-11 09:00","2020-05-11 18:00","취소","취소","연속"]
[23,"인천","부평","서인천C/C 345kV #1 M.Tr 1차 CB A (7172_A)","서인천C/C 345kV 7172 GIS 보통점검","서인천C/C 345kV 7172 GIS 보통점검","2020-05-29 09:00","2020-05-29 18:00","2020-05-29 09:00","2020-05-29 18:00","연속"]
[24,"인천","부평","신가좌S/S #2 M.Tr","신가좌S/S 345kV #2 M.Tr 2차 GIS 정밀점검 공사","신가좌S/S 345kV #2 M.Tr 2차 GIS 정밀점검 공사","2020-05-19 09:00","2020-05-21 18:00","2020-05-19 09:00","2020-05-21 18:00","연속"]
[25,"인천","부평","신가좌S/S #3 M.Tr","신가좌S/S 345kV #3 M.Tr 보호반 대체","- 신가좌S/S 345kV #3 M.Tr 보호반 대체 - 신가좌S/S 345kV #3 M.Tr 보통점검","2020-05-11 09:00","2020-05-15 18:00","2020-05-11 09:00","2020-05-15 18:00","연속"]
[26,"인천","부평","신가좌신시흥#2 T/L","345kV 신가좌-신시흥#2T/L 스페이서 간격조정","345kV 신가좌-신시흥#2T/L 스페이서 간격조정","2020-05-25 08:00","2020-05-29 18:00","취소","취소","연속"]
[27,"인천","부평","신경서포스코CC#1 T/L","345kV 신경서-포스코T/L 접속함 교체공사","중간접속함 리콜자재(에폭시유니트 불량)로 교체 시행(18set) J/B#1, 2, 3, 5, 6, 9(개소당 3set)","2020-05-11 09:00","2020-06-14 18:00","2020-05-11 09:00","2020-06-14 18:00","연속"]
[28,"인천","부평","신인천C/C 345kV 신김포신인천T/L-4MT101 TIE CB A (7700_A)","서인천C/C 345kV 7700 GIS 보통점검","서인천C/C 345kV 7700 GIS 보통점검","2020-05-20 09:00","2020-05-20 18:00","2020-05-20 09:00","2020-05-20 18:00","연속"]
[29,"인천","부평","신인천C/C 345kV 3MT201 CB A (7672_A)","서인천C/C 345kV 7672 GIS 보통점검","서인천C/C 345kV 7672 GIS 보통점검","2020-05-19 09:00","2020-05-19 18:00","2020-05-19 09:00","2020-05-19 18:00","연속"]
[30,"인천","부평","신인천C/C 345kV 3MT001-3MT201 TIE CB A (7600_A)","서인천C/C 345kV 7600 GIS 보통점검","서인천C/C 345kV 7600 GIS 보통점검","2020-05-18 09:00","2020-05-18 18:00","2020-05-18 09:00","2020-05-18 18:00","연속"]
[31,"인천","부평","신인천C/C 345kV 3MT101 CB A (7572_A)","서인천C/C 345kV 7572 GIS 보통점검","서인천C/C 345kV 7572 GIS 보통점검","2020-05-15 09:00","2020-05-15 18:00","2020-05-15 09:00","2020-05-15 18:00","연속"]
[32,"인천","부평","신인천C/C 345kV 3MT101 TIE CB A (7500_A)","서인천C/C 345kV 7500 GIS 보통점검","서인천C/C 345kV 7500 GIS 보통점검","2020-05-14 09:00","2020-05-14 18:00","2020-05-14 09:00","2020-05-14 18:00","연속"]
[33,"인천","부평","신인천C/C 345kV 신김포-신인천C/C T/L CB A (7771_A)","서인천C/C 345kV 7771 GIS 보통점검","서인천C/C 345kV 7771 GIS 보통점검","2020-05-21 09:00","2020-05-21 18:00","2020-05-21 09:00","2020-05-21 18:00","연속"]
[34,"인천","부평","인천CC S/Y 345kV 인천CC#3,4G/T-인천CC#1,2G/T TIE CB A (7500_A)","인천C/C 345kV 7500 GIS 보통점검","인천C/C 345kV 7500 GIS 보통점검","2020-05-27 09:00","2020-05-27 18:00","2020-05-27 09:00","2020-05-27 18:00","연속"]
[35,"인천","부평","인천CC S/Y 345kV 인천복합 #3,4 G/T CB A (7571_A)","인천C/C 345kV 7571 GIS 보통점검","인천C/C 345kV 7571 GIS 보통점검","2020-05-28 09:00","2020-05-28 18:00","2020-05-28 09:00","2020-05-28 18:00","연속"]
[36,"인천","부평","인천CC S/Y 345kV 인천복합 #1,2 G/T CB A (7572_A)","인천C/C 345kV 7572 GIS 보통점검","인천C/C 345kV 7572 GIS 보통점검","2020-05-29 09:00","2020-05-29 18:00","2020-05-29 09:00","2020-05-29 18:00","연속"]
[37,"인천","부평","인천CC S/Y 345kV 가정-인천CC#1T/L CB A (7472_A)","인천C/C 345kV 7472 GIS 보통점검","인천C/C 345kV 7472 GIS 보통점검","2020-05-26 09:00","2020-05-26 18:00","2020-05-26 09:00","2020-05-26 18:00","연속"]
[38,"인천","부평","인천CC S/Y 345kV 신경서인천CC#2-가정인천CC#1T/L TIE CB A (7400_A)","인천C/C 345kV 7400 GIS 보통점검","인천C/C 345kV 7400 GIS 보통점검","2020-05-25 09:00","2020-05-25 18:00","2020-05-25 09:00","2020-05-25 18:00","연속"]
[39,"인천","부평","포스코S/Y 345kV #1 STEP-UP-TR T/L CB A (7172)","포스코S/Y 7172 GIS 보통점검","포스코S/Y 7172 GIS 보통점검","2020-05-04 09:00","2020-05-04 18:00","2020-05-04 09:00","2020-05-04 18:00","연속"]
[40,"인천","부평","포스코S/Y 345kV #2 STEP-UP-TR T/L CB A (7272)","포스코S/Y 7272 GIS 보통점검","포스코S/Y 7272 GIS 보통점검","2020-05-06 09:00","2020-05-06 18:00","2020-05-06 09:00","2020-05-06 18:00","연속"]
[41,"인천","부평","포스코S/Y 345kV #3 STEP-UP-TR T/L CB A (7372)","포스코S/Y 7372 GIS 보통점검","포스코S/Y 7372 GIS 보통점검","2020-05-07 09:00","2020-05-07 18:00","2020-05-07 09:00","2020-05-07 18:00","연속"]
[42,"인천","부평","포스코S/Y 345kV #4 STEP-UP-TR T/L CB A (7472)","포스코S/Y 7472 GIS 보통점검 공사","포스코S/Y 7472 GIS 보통점검 공사","2020-05-08 09:00","2020-05-08 18:00","2020-05-08 09:00","2020-05-08 18:00","연속"]
[43,"인천","시흥","신시흥#1S/S #1 M.Tr","신시흥S/S 345kV #1M.Tr휴전(PL-LD6분전반대체)","신시흥S/S 345kV #1M.Tr휴전(PL-LD6분전반대체)","2020-05-06 10:00","2020-05-06 18:00","2020-05-06 10:00","2020-05-06 18:00","연속"]
[44,"인천","시흥","신시흥#1S/S 345kV 신시흥-신광명#1T/L TIE GIS","신시흥S/S 345kV 7900 GIS정밀점검","신시흥S/S 345kV 7900 GIS정밀점검","2020-05-21 10:00","2020-05-23 18:00","2020-05-21 10:00","2020-05-23 18:00","연속"]
[45,"인천","시흥","신가좌신시흥#1 T/L","345kV 신가좌-신시흥(신시흥-신광명)T/L 지장송전선로 이설공사","공사구간 : (하단) 345kV 신가좌-신시흥 #1T/L No.58~59 (상단) 345kV 신시흥-신광명 #1T/L No.35~36 선로길이 : 345kV 신시흥-신광명T/L - 0.4777km 345kV 신가좌-신시흥T/L - 0.4777km","2020-05-02 07:00","2020-05-08 18:00","2020-05-02 07:00","2020-05-08 18:00","연속"]
[46,"인천","시흥","신시흥신광명#1 T/L","345kV 신가좌-신시흥(신시흥-신광명)T/L 지장송전선로 이설공사","공사구간 : (상단) 345kV 신시흥-신광명 #1T/L No.35~36 (하단) 345kV 신가좌-신시흥 #1T/L No.58~59 선로길이 : 345kV 신시흥-신광명T/L - 0.4777km 345kV 신가좌-신시흥T/L - 0.4777km","2020-05-02 07:00","2020-05-06 18:00","2020-05-02 07:00","2020-05-06 18:00","연속"]
[47,"인천","시흥","신시흥#1S/S 345kV 신시흥-신광명#2T/L-2M.Tr 1차 TIE GIS","신시흥S/S 345kV 7A00 GIS정밀점검","신시흥S/S 345kV 7A00 GIS정밀점검","2020-05-14 10:00","2020-05-16 18:00","2020-05-14 10:00","2020-05-16 18:00","연속"]
[48,"인천","시흥","신시흥#1S/S 345kV 신시흥-영흥TP#3T/L TIE GIS","신시흥S/S 345kV 7700 GIS정밀점검","신시흥S/S 345kV 7700 GIS정밀점검","2020-05-11 10:00","2020-05-13 18:00","2020-05-11 10:00","2020-05-13 18:00","연속"]
[49,"인천","시흥","신시흥#1S/S 345kV 신시흥-영흥TP#4T/L GIS","신시흥S/S 345kV 7871 GIS정밀점검","신시흥S/S 345kV 7871 GIS정밀점검","2020-05-18 10:00","2020-05-20 18:00","2020-05-18 10:00","2020-05-20 18:00","연속"]
[50,"인천","시흥","신시흥#2S/S 345kV 신시흥-영흥TP#2T/L GIS","신시흥S/S 345kV 7271 GIS정밀점검","신시흥S/S 345kV 7271 GIS정밀점검","2020-05-25 10:00","2020-05-27 18:00","2020-05-25 10:00","2020-05-27 18:00","연속"]
[51,"인천","시흥","신시흥#2S/S #4 M.Tr","신시흥S/S 345kV #4M.Tr 보통점검","신시흥S/S 345kV #4M.Tr 보통점검","2020-05-11 10:00","2020-05-13 18:00","2020-05-11 10:00","2020-05-13 18:00","연속"]
[52,"인천","시흥","영흥T/P 345kV 신시흥-영흥TP#2T/L GIS","영흥#1S/Y 345kV 신시흥영흥#2T/L(7471) ANN보수","영흥#1S/Y 345kV 신시흥영흥#2T/L(7471) ANN보수","2020-05-18 10:00","2020-05-18 18:00","2020-05-18 10:00","2020-05-18 18:00","연속"]
[53,"인천","시흥","영흥T/P 345kV #1T.Tr 1차-#2T.Tr 1차 TIE GIS","영흥#1S/Y 345kV 7300 GIS정밀점검","영흥#1S/Y 345kV 7300 GIS정밀점검","2020-05-04 10:00","2020-05-07 18:00","2020-05-04 10:00","2020-05-07 18:00","연속"]
[54,"인천","시흥","영흥T/P 345kV #75 BUS","영흥#1S/Y 345kV 7300 GIS정밀 무부하가압(75BUS휴전)","영흥#1S/Y 345kV 7300 GIS정밀 무부하가압(75BUS휴전)","2020-05-07 14:00","2020-05-07 15:00","2020-05-07 14:00","2020-05-07 15:00","연속"]
[55,"인천","시흥","영흥1TP영흥2TP#1 T/L","영흥#1S/Y 345kV 7300 GIS정밀 무부하(영흥연락#1TL휴전)","영흥#1S/Y 345kV 7300 GIS정밀 무부하(영흥연락#1TL휴전)","2020-05-07 14:00","2020-05-07 15:00","2020-05-07 14:00","2020-05-07 15:00","연속"]
[56,"인천","직할","서인천CC신부평#4 T/L","345kV 서인천CC-신부평#4T/L 절연유 보충","345kV 서인천CC-신부평#4T/L 절연유 보충","2020-05-11 09:00","2020-05-11 18:00","취소","취소","연속"]
[57,"인천","직할","신부평S/S 345kV 서인천CC-신부평#2T/L-#2 M.Tr 1차 TIE CB C (7200_C)","신부평S/S 7200CB 강화조작시험","신부평S/S 7200CB 강화조작시험","2020-05-15 09:30","2020-05-15 14:00","2020-05-15 09:30","2020-05-15 14:00","연속"]
[58,"인천","직할","신부평S/S 345kV 서인천CC-신부평#4T/L CB A (7471_A)","신부평S/S 7400CB 강화조작시험","신부평S/S 7400CB 강화조작시험","2020-05-15 14:00","2020-05-15 18:00","2020-05-15 14:00","2020-05-15 18:00","연속"]
[59,"인천","직할","신부평S/S 345kV #1 Sh.R CB A (7179_A)","신부평S/S 7179CB 362kV GIS 보통점검","신부평S/S 7179CB 362kV GIS 보통점검","2020-05-21 09:30","2020-05-21 18:00","2020-05-21 09:30","2020-05-21 18:00","연속"]
[60,"인천","직할","신부평S/S 345kV #2 Sh.R CB A (7279_A)","신부평S/S 7279CB 362kV GIS 보통점검","신부평S/S 7279CB 362kV GIS 보통점검","2020-05-22 09:30","2020-05-22 18:00","2020-05-22 09:30","2020-05-22 18:00","연속"]
[61,"인천","직할","신부평S/S 345kV 서인천CC-신부평#1T/L CB A (7171_A)","신부평S/S 7171CB 362kV GIS 보통점검","신부평S/S 7171CB 362kV GIS 보통점검","2020-05-28 09:30","2020-05-28 18:00","2020-05-28 09:30","2020-05-28 18:00","연속"]
[62,"인천","직할","신부평S/S 345kV 서인천CC-신부평#1T/L-#1M.Tr 1차 TIE CB B (7100_B)","신부평S/S 7100CB 362kV GIS 보통점검","신부평S/S 7100CB 362kV GIS 보통점검","2020-05-29 09:30","2020-05-29 18:00","2020-05-29 09:30","2020-05-29 18:00","연속"]
[63,"인천","직할","신부평S/S #2 M.Tr","신부평S/S #2M.Tr 2차 170kV GIS 정밀점검","신부평S/S #2M.Tr 2차 170kV GIS 정밀점검","2020-05-06 09:00","2020-05-08 18:00","2020-05-18 09:00","2020-05-20 18:00","연속"]
[64,"경기북부","고양","신덕은S/S #2 M.Tr","'20~'21년 고양전력지사 변전정비회사 총액공사","변압기 보호배전반 교체공사","2020-05-11 09:00","2020-05-15 18:00","2020-05-11 09:00","2020-05-15 18:00","연속"]
[65,"경기북부","고양","신덕은S/S #4 M.Tr","신덕은S/S #4M.Tr 3차 GPT 교체작업","삼능제 PT 구조개선 관련 GPT 교체","2020-05-28 09:00","2020-05-28 18:00","2020-05-28 09:00","2020-05-28 18:00","연속"]
[66,"경기북부","고양","신파주양주#2 T/L","345kV 신파주-양주T/L No.12 안전이격거리 확보공사","ㅇ 철탑 신설 2기(신설No.12, 임시No.12) 철거 2기(기설No.12, 임시No.12)","2020-05-28 07:00","2020-06-07 18:00","2020-05-28 07:00","2020-06-07 18:00","연속"]
[67,"경기북부","고양","신김포신파주#1 T/L","신파주변전소 외부 천장재 교체공사","가. 시스템비계 설치 : 1,523.89㎡ 나. 샌드위치판넬 지붕 상부 보양 : 186.51㎡ 다. 기존 천장재 철거 : 689.99㎡ 라. 기존 천장 철골틀 철거 : 736.55㎡ 마. 내풍압용 천장틀 및 천장재 설치 : 736.55㎡","2020-05-02 09:00","2020-05-06 18:00","취소","취소","연속"]
[68,"경기북부","고양","신파주신덕은#2 T/L","2020년 가공송전선로 순시점검 위탁공사","ㅇ 정밀점검","2020-05-17 07:00","2020-05-17 18:00","2020-05-17 07:00","2020-05-17 18:00","연속"]
[69,"경기북부","고양","신파주신덕은#1 T/L","2020년 가공송전선로 순시점검 위탁공사","ㅇ 정밀점검","2020-05-18 07:00","2020-05-20 18:00","2020-05-18 07:00","2020-05-20 18:00","연속"]
[70,"경기북부","고양","신김포신파주#2 T/L","2020_신파주양주 OPGW #2TL 증설","- 신파주양주 #2TL ACSR 120SQ 철거 및 OPGW시설(경간 16.122km) - 2020_신파주양주 OPGW #2TL 증설에 따른 병가구간 휴전","2020-05-25 09:00","2020-05-28 20:00","2020-05-25 09:00","2020-05-28 20:00","연속"]
[71,"경기북부","고양","신파주양주#1 T/L","345kV 신파주-양주T/L No.12 안전이격거리 확보공사","ㅇ 철탑 신설 2기(신설No.12, 임시No.12) 철거 2기(기설No.12, 임시No.12)","2020-05-25 07:00","2020-05-27 18:00","2020-05-25 07:00","2020-05-27 18:00","연속"]
[72,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용 GIS대체공사(6차분)-안전이격거리확보","- 미금덕소#1T/L 철거, 설치 - 미금구리#2T/L 철거, 설치 - 시험가압(5.18~19), (5.24~25), (6.5~6)","2020-05-19 08:00","2020-05-24 16:00","2020-05-19 08:00","2020-05-24 16:00","매일"]
[73,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용 GIS대체공사(6차분)-시험가압","- 미금덕소#1T/L 철거, 설치 - 미금구리#2T/L 철거, 설치 - 시험가압(5.18~19), (5.23~25), (6.5~6)","2020-05-18 18:00","2020-05-19 08:00","2020-05-18 18:00","2020-05-19 08:00","연속"]
[74,"경기북부","구리","미금S/S 345kV #2 Sh.R","미금 #2Sh.R 7279 차단기 하자점검","차단기 하자점검","2020-05-11 09:00","2020-05-11 18:00","2020-05-11 09:00","2020-05-11 18:00","연속"]
[75,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용 GIS대체공사(5차분)-안전이격거리확보","- 6100 BUS TIE 철거, 설치 - 60BUS PT, 65BUS PT 철거, 설치 - 안전이격거리확보","2020-05-04 09:00","2020-05-09 18:00","2020-05-04 09:00","2020-05-09 18:00","매일"]
[76,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 미금S/S 교체 71Bay 차단기 3대 감시제어계측 포인트이관 (→SA) - 71Bay LCP 및 배전반 모자익반 제어케이블 철거 및 재결선","2020-05-10 09:00","2020-05-16 18:00","2020-05-10 09:00","2020-05-16 18:00","연속"]
[77,"경기북부","구리","미금성동#1 T/L","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 미금S/S 교체 71Bay 차단기 3대 감시제어계측 포인트이관 (→SA) - 71Bay LCP 및 배전반 모자익반 제어케이블 철거 및 재결선","2020-05-10 09:00","2020-05-16 13:00","2020-05-10 09:00","2020-05-16 13:00","연속"]
[78,"경기북부","구리","미금S/S 345kV STATCOM M.Tr 1차 TIE CB A (7900A)","미금 STATCOM 1차 TIE(7900) 차단기 보통점검","차단기 보통점검 및 전자변 교체","2020-05-07 13:00","2020-05-08 18:00","2020-05-07 13:00","2020-05-08 18:00","연속"]
[79,"경기북부","구리","미금S/S STATCOM M.Tr 1차 CB A (7972A)","미금S/S STATCOM 1차(7972) 차단기 보통점검","차단기 보통점검, 전자변 교체","2020-05-06 09:00","2020-05-07 13:00","2020-05-06 09:00","2020-05-07 13:00","연속"]
[80,"경기북부","구리","미금성동#2 T/L","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 미금S/S 교체 72Bay 차단기 1대 감시제어계측 포인트이관 (→SA) - 72Bay LCP 및 배전반 모자익반 제어케이블 철거 및 재결선 - #3,4Sh.R LCP 및 배전반 모자익반 제어케이블 철거 및 재결선","2020-05-25 09:00","2020-05-29 13:00","취소","취소","연속"]
[81,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용 GIS대체공사(6차분)-안전이격거리확보","- 미금덕소#1T/L 철거, 설치 - 미금구리#2T/L 철거, 설치 - 시험가압(5.18~19), (5.24~25), (6.5~6)","2020-05-25 08:00","2020-06-05 17:00","2020-05-25 08:00","2020-06-05 17:00","매일"]
[82,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용 GIS대체공사(6차분)-시험가압","- 미금덕소#1T/L 철거, 설치 - 미금구리#2T/L 철거, 설치 - 시험가압(5.18~19), (5.23~25), (6.5~6)","2020-05-24 16:00","2020-05-25 08:00","2020-05-24 16:00","2020-05-25 08:00","연속"]
[83,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용 GIS대체공사(6차분)-안전이격거리확보","- 미금덕소#1T/L 철거, 설치 - 미금구리#2T/L 철거, 설치 - 시험가압(5.18~19), (5.24~25), (6.5~6)","2020-05-18 08:00","2020-05-18 18:00","2020-05-18 08:00","2020-05-18 18:00","연속"]
[84,"경기북부","구리","신의정부미금#2 T/L","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 미금S/S 교체 75Bay 차단기 2대 감시제어계측 포인트이관 (→SA) - 75Bay LCP 및 배전반 모자익반 제어케이블 철거 및 재결선","2020-05-04 09:00","2020-05-08 13:00","2020-05-04 09:00","2020-05-08 13:00","연속"]
[85,"경기북부","구리","포천LNGC/C 345kV #2 G/T TR 2차 CB A (7272A)","345kV GIS 하자점검","345kV GIS 하자점검","2020-05-21 09:00","2020-05-21 18:00","2020-05-21 09:00","2020-05-21 18:00","연속"]
[86,"경기북부","구리","포천LNGC/C 345kV 신포천#2T/L-#2 G/T TR 2차 TIE CB A (7200A)","345kV GIS 하자점검","345kV GIS 하자점검","2020-05-20 09:00","2020-05-20 18:00","2020-05-20 09:00","2020-05-20 18:00","연속"]
[87,"경기북부","구리","포천LNGC/C 345kV 신포천-포천LNGC/C #2T/L CB A (7271A)","345kV GIS 하자점검","345kV GIS 하자점검","2020-05-19 09:00","2020-05-19 18:00","2020-05-19 09:00","2020-05-19 18:00","연속"]
[88,"경기북부","구리","포천LNGC/C 345kV #1 G/T TR 2차 CB A (7172A)","구리전력지사 345kV GIS 하자점검","구리전력지사 345kV GIS 하자점검","2020-05-14 09:00","2020-05-14 18:00","2020-05-14 09:00","2020-05-14 18:00","연속"]
[89,"경기북부","구리","포천LNGC/C 345kV 신포천-포천LNGC/C #1T/L CB A (7171A)","345kV GIS 하자점검","345kV GIS 하자점검","2020-05-12 09:00","2020-05-12 18:00","2020-05-12 09:00","2020-05-12 18:00","연속"]
[90,"경기북부","구리","포천LNGC/C 345kV 신포천#1T/L-#1 G/T TR 2차 TIE CB A (7100A)","345kV GIS 하자점검","345kV GIS 하자점검","2020-05-13 09:00","2020-05-13 18:00","2020-05-13 09:00","2020-05-13 18:00","연속"]
[91,"경기북부","구리","포천LNGC/C 345kV 신가평-포천LNGC/C #2T/L CB A (7371A)","345kV GIS 하자점검","345kV GIS 하자점검","2020-05-26 09:00","2020-05-26 18:00","2020-05-26 09:00","2020-05-26 18:00","연속"]
[92,"경기북부","구리","포천LNGC/C 신가평#2T/L-#1 S/T TR 2차 TIE CB A (7300A)","345kV GIS 하자점검","345kV GIS 하자점검","2020-05-27 09:00","2020-05-27 18:00","2020-05-27 09:00","2020-05-27 18:00","연속"]
[93,"경기북부","구리","포천LNGC/C 345kV #1 S/T TR 2차 CB A (7372A)","345kV GIS 하자점검","345kV GIS 하자점검","2020-05-28 09:00","2020-05-28 18:00","2020-05-28 09:00","2020-05-28 18:00","연속"]
[94,"경기북부","직할","신의정부S/S #4 M.Tr","신의정부S/S DS 발청 하자보수공사","신의정부S/S 345kV #4 M.Tr 2차 GIS측 모선 DS부 발청제거","2020-05-26 09:00","2020-05-29 18:00","2020-05-26 09:00","2020-05-29 18:00","연속"]
[95,"경기북부","직할","신의정부미금#1 T/L","20~21년 경기북부 직할 가공송전정비회사 총액공사","압축인류크램프 및 점퍼선교체","2020-05-13 12:00","2020-05-13 18:00","취소","취소","연속"]
[96,"경기북부","직할","신가평신의정부#2 T/L","20~21년 경기북부 직할 가공송전정비회사 총액공사","점퍼선교체","2020-05-13 08:00","2020-05-13 12:00","취소","취소","연속"]
[97,"경기북부","직할","양주중부#2 T/L","345kV 신파주-양주 등 11개T/L 항공시설물 보강공사","ㅇ 항공시설물 보강공사","2020-05-21 07:00","2020-05-22 18:00","취소","취소","연속"]
[98,"경기북부","직할","양주중부#1 T/L","345kV 신파주-양주 등 11개T/L 항공시설물 보강공사","ㅇ 항공시설물 보강공사","2020-05-19 07:00","2020-05-20 18:00","취소","취소","연속"]
[99,"경기북부","직할","양주S/S #4 M.Tr","양주변전소 옥외철구 GIS화 공사","345kV M.Tr 2차 전력케이블 설치","2020-05-14 09:00","2020-05-25 18:00","2020-05-14 09:00","2020-05-25 18:00","연속"]
[100,"경기북부","직할","양주S/S #1 M.Tr","양주변전소 옥외철구 GIS화 공사","345kV M.Tr 2차 전력케이블 설치","2020-05-06 09:00","2020-05-08 18:00","2020-05-06 09:00","2020-05-08 18:00","연속"]
[101,"경기북부","직할","양주S/S #2 M.Tr","양주변전소 옥외철구 GIS화 공사","345kV M.Tr 2차 전력케이블 기초설치","2020-05-11 09:00","2020-05-13 18:00","2020-05-11 09:00","2020-05-13 18:00","연속"]
[102,"경기북부","직할","양주S/S #3 M.Tr","양주변전소 옥외철구 GIS화 공사","345kV M.Tr 2차 전력케이블 기초설치","2020-05-26 09:00","2020-05-28 18:00","2020-05-26 09:00","2020-05-28 18:00","연속"]
[103,"경기","직할","화성S/S #3 M.Tr","345kV 화성S/S GIS 용량대체공사 ","78 Bay GIS 용량대체 장비반입 관련 이격거리 확보 ","2020-05-04 09:00","2020-05-08 18:00","2020-05-04 09:00","2020-05-08 18:00","연속"]
[104,"경기","군포","신온양서서울#2 T/L","345kV 신온양서서울외 2개T/L 지장철탑이설공사","철탑교체 2기, 전력선교체 59 ~ 65","2020-05-26 07:00","2020-06-06 18:00","취소","취소","연속"]
[105,"경기","군포","서서울S/S 345kV 서서울-신광명#1T/L GIS","서서울S/S 서서울-신광명#1T/L 7571 GIS 조작시험","서서울S/S 서서울-신광명#1T/L 7571 GIS 조작시험","2020-05-12 09:00","2020-05-12 14:00","2020-05-12 09:00","2020-05-12 14:00","연속"]
[106,"경기","군포","서서울S/S 345kV 서서울-신광명#2T/L GIS","서서울S/S 서서울-신광명#2T/L 7671 GIS 조작시험","서서울S/S 서서울-신광명#2T/L 7671 GIS 조작시험","2020-05-11 14:00","2020-05-11 18:00","2020-05-11 14:00","2020-05-11 18:00","연속"]
[107,"경기","군포","서서울S/S 345kV 신온양-서서울#2T/L GIS","서서울S/S 신온양-서서울#2T/L 7772 GIS 조작시험","서서울S/S 신온양-서서울#2T/L 7772 GIS 조작시험","2020-05-11 09:00","2020-05-11 14:00","2020-05-11 09:00","2020-05-11 14:00","연속"]
[108,"경기","군포","신온양서서울#1 T/L","345kV 신온양서서울외 2개T/L 지장철탑이설공사","철탑교체 2기, 전력선교체 59 ~ 65","2020-05-20 07:00","2020-05-25 18:00","취소","취소","연속"]
[109,"경기","군포","신안산S/S 345kV #75 BUS","345kV 신안산S/S 용량부족 GIS 대체공사","345kV 신안산S/S 용량부족 GIS 대체공사 - #75BUS 용량대체(71, 72, 73Bay, 40kA → 63kA)","2020-05-04 09:00","2020-05-23 18:00","2020-05-04 09:00","2020-05-23 18:00","연속"]
[110,"경기","군포","화성신안산#2 T/L","345kV 신안산S/S 용량부족 GIS 대체공사","345kV 신안산S/S 용량부족 GIS 대체공사 - 75BUS GIS 대체공사후 무부하가압","2020-05-22 09:00","2020-05-23 18:00","취소","취소","연속"]
[111,"경기","동부","곤지암S/S #1 M.Tr","20년 동부 변전정비회사 총액공사","곤지암:345kV #1M.Tr(보통)(~13) 부싱절연유채유 7172,7100(보통)6144(보통)(~13)7172(A,B,C)전자변교체7100(B상)전자변 실리콘히터설치 3차 #1S.Tr(4189) GIS(보통)","2020-05-12 09:30","2020-05-13 18:00","2020-05-12 09:30","2020-05-13 18:00","연속"]
[112,"경기","동부","곤지암신충주#1 T/L","20년 동부 변전정비회사 총액공사","곤지암:7200,7271 GIS(보통), 7200(B,C), 7271(A,B,C) 전자변교체 43L/R 회로보완 확인 및 Remote 회로분리 시행","2020-05-06 09:30","2020-05-06 18:00","취소","취소","연속"]
[113,"경기","동부","곤지암S/S #2 M.Tr","20년 동부 변전정비회사 총액공사","곤지암:345kV #2M.Tr(보통)(~20) 부싱절연유채유,B상 OFU필터교체,7372,7300(보통)6244(보통)(~20),7372(B,C),7300(A,B,C)전자변교체,3차 #2S.Tr(4289) GIS(보통)","2020-05-19 09:30","2020-05-20 18:00","2020-05-19 09:30","2020-05-20 18:00","연속"]
[114,"경기","성남","신안성신성남#2 T/L","신성남-동서울TL OPGW시설공사(대장지구)","신성남동서울T/L No.83~머내C/H구간 OPGW 증설","2020-05-25 09:00","2020-05-27 18:00","2020-05-25 09:00","2020-05-27 18:00","연속"]
[115,"경기","성남","신성남동서울#2 T/L","345kV 신성남-동서울T/L 성남 판교대장 도시개발지구 지중화공사","○ 지 지 물 - 신 설 : 산형강 4각철탑 4기(임시철탑 3기 포함), C/H철탑 1기 - 보 강 : 산형강 4각철탑 4기(인클로징 2기 포함) - 철 거 : 산형강 4각철탑 6기(임시철탑 3기 포함) ○ 전 력 선 - 신 설 : ACSR 480 × 2B × 2C, 1.315km - 철 거 :","2020-05-26 09:00","2020-06-05 18:00","2020-05-26 09:00","2020-06-05 18:00","연속"]
[116,"경기","성남","서서울#2신성남#1 T/L","신성남-동서울TL OPGW시설공사(대장지구)","신성남동서울T/L 머내C/H~신성남 구간 OPGW 증설","2020-05-24 09:00","2020-05-25 18:00","2020-05-24 09:00","2020-05-25 18:00","연속"]
[117,"경기","성남","서서울#2신성남#1 T/L","20년 성남전력 변전정비회사 총액공사","서서울2-신성남 #1T/L - LA(보통),CVT(초기) - 유호배전반성능개선 - 전자변교체","2020-05-26 09:00","2020-05-26 18:00","2020-05-26 09:00","2020-05-26 18:00","연속"]
[118,"경기","성남","신안성신성남#1 T/L","2020-21 가공송전정비 총액공사(애자련 교체)","345kV 신성남-동서울#1T/L 성능저하 국산애자 교체 작업자 안전이격 확보, 확보작업개소 - No.76,79(2기)","2020-05-08 07:00","2020-05-08 18:00","2020-05-08 07:00","2020-05-08 18:00","연속"]
[119,"경기","성남","신성남동서울#1 T/L","345kV 신성남-동서울T/L 성남 판교대장 도시개발지구 지중화공사","○ 지 지 물 - 신 설 : 산형강 4각철탑 4기(임시철탑 3기 포함), C/H철탑 1기 - 보 강 : 산형강 4각철탑 4기(인클로징 2기 포함) - 철 거 : 산형강 4각철탑 6기(임시철탑 3기 포함) ○ 전 력 선 - 신 설 : ACSR 480 × 2B × 2C, 1.315km - 철 거 : ACSR 480 × 2B × 2C, 2.184km","2020-05-11 09:00","2020-05-25 18:00","2020-05-11 09:00","2020-05-25 18:00","연속"]
[120,"경기","성남","신성남신양재#1 T/L","20년 성남전력 변전정비회사 총액공사","신성남신양재#1 T/L - 1차 GIS 보통점검, 전자변교체 - LA 보통점검 - 7800 A,B,C 대쉬포트누유확인 - 7871 B 대쉬포트 누유확인","2020-05-19 09:00","2020-05-20 18:00","2020-05-19 09:00","2020-05-20 18:00","연속"]
[121,"경기","성남","신성남신양재#2 T/L","20년 성남전력 변전정비회사 총액공사","신성남신양재#2 T/L - 1차 GIS(보통),전자변교체 - LA(보통), - 7771B상, 7700A상 대쉬포트누유","2020-05-21 09:00","2020-05-22 18:00","2020-05-21 09:00","2020-05-22 18:00","연속"]
[122,"경기","성남","신수원S/S #4 M.Tr","20년 성남전력 345kV M.Tr 정밀점검","신수원S/S 345kV #4M.Tr 정밀점검","2020-05-25 09:00","2020-06-05 18:00","2020-05-25 09:00","2020-06-05 18:00","연속"]
[123,"경기","성남","신안성서안성#1 T/L","20년 성남전력 변전정비회사 총액공사","신안성서안성#1 T/L 7C72 A상 투입결상","2020-05-12 09:00","2020-05-12 18:00","2020-05-12 09:00","2020-05-12 18:00","연속"]
[124,"경기","성남","신용인S/S #1 M.Tr","20년 성남전력 변전정비회사 총액공사","신용인S/S 345kV #1 M.Tr - LA 1차,2차(보통) - LA 3차(초기) - PT 3차(보통) - 붓싱절연유채유,전자변교체","2020-05-20 09:00","2020-05-21 18:00","2020-05-20 09:00","2020-05-21 18:00","연속"]
[125,"경기","직할","화성S/S 345kV #70-#71 SEC GIS(2019)","20년 직할 변전정비회사 총액공사","화성S/S #70-71SEC GIS 초기점검","2020-05-07 09:00","2020-05-07 18:00","2020-05-07 09:00","2020-05-07 18:00","연속"]
[126,"경기","직할","화성신안산#1 T/L","봉담-송산간 도로개설 관련 지장이설 2공구","가철탑 3기 설치","2020-05-02 07:00","2020-05-15 18:00","2020-05-02 07:00","2020-05-15 18:00","연속"]
[127,"경기","직할","화성신평택CC#1 T/L","20년 직할 변전정비회사 총액공사","화성S/S 화성-신평택CC #1T/L, TIE GIS 하자점검","2020-05-25 09:00","2020-05-25 18:00","2020-05-25 09:00","2020-05-25 18:00","연속"]
[128,"경기","직할","화성S/S #3 M.Tr","20년 경기직할 154kV GIS 정밀점검공사","화성S/S #3M.Tr 2차 GIS 정밀점검","2020-05-18 09:00","2020-05-20 18:00","2020-05-18 09:00","2020-05-20 18:00","연속"]
[129,"경기","직할","화성S/S 345kV #1 CLR 70BUS GIS(2019)","20년 직할 변전정비회사 총액공사","화성S/S #1CLR 70BUS GIS 초기점검","2020-05-28 09:00","2020-05-28 18:00","2020-05-28 09:00","2020-05-28 18:00","연속"]
[130,"경기","직할","화성S/S 345kV #1 CLR 71BUS GIS(2019)","20년 직할 변전정비회사 총액공사","화성S/S #1CLR 71BUS GIS 초기점검","2020-05-29 09:00","2020-05-29 18:00","2020-05-29 09:00","2020-05-29 18:00","연속"]
[131,"경기","직할","화성신안산#2 T/L","봉담-송산간 도로개설 관련 지장이설 2공구","가철탑 3기 설치","2020-05-16 07:00","2020-05-21 18:00","2020-05-16 07:00","2020-05-21 18:00","연속"]
[132,"경기","직할","화성신평택CC#2 T/L","20년 직할 변전정비회사 총액공사","화성S/S 화성-신평택CC #2T/L, TIE GIS, 상부 GIS 하자(~27)","2020-05-26 09:00","2020-05-27 18:00","2020-05-26 09:00","2020-05-27 18:00","연속"]
[133,"경기","평택","서안성S/S 345kV 신안성-서안성#1T/L GIS","345kV 서안성S/S GIS 용량대체공사","345kV GIS 11CB 철거 및 설치","2020-05-27 09:00","2020-05-29 09:00","2020-05-27 09:00","2020-05-29 09:00","연속"]
[134,"경기","평택","서안성S/S 345kV #70 BUS","345kV 서안성S/S GIS 용량대체공사","345kV GIS 11CB 철거 및 설치","2020-05-04 09:00","2020-05-29 09:00","2020-05-04 09:00","2020-05-29 09:00","연속"]
[135,"경기","평택","서안성S/S 345kV #75 BUS","345kV 서안성S/S GIS 용량대체공사","345kV GIS 11CB 철거 및 설치","2020-05-29 09:00","2020-06-19 09:00","2020-05-29 09:00","2020-06-19 09:00","연속"]
[136,"강원","강릉","동해신양양 T/L","20-21년도 송전정비회사 총액공사","○ 상간스페이서 설치 - 345kV 양양양수T/L No.162-163","2020-05-22 08:00","2020-05-22 18:00","2020-05-22 08:00","2020-05-22 18:00","연속"]
[137,"강원","강릉","신양양S/S #1 M.Tr","신양양S/S 부싱절연유 채유","○ 신양양S/S 부싱절연유 채유","2020-05-06 10:00","2020-05-06 18:00","2020-05-07 10:00","2020-05-07 18:00","연속"]
[138,"강원","강릉","신양양S/S #2 M.Tr","신양양S/S 부싱절연유 채유","○ 신양양S/S 부싱절연유 채유","2020-05-07 10:00","2020-05-07 18:00","2020-05-08 10:00","2020-05-08 18:00","연속"]
[139,"강원","강릉","동해양양PP T/L","20-21년도 송전정비회사 총액공사","○ 상간스페이서 설치 - 345kV 양양양수T/L No.162~163","2020-05-21 08:00","2020-05-21 18:00","취소","취소","연속"]
[140,"강원","강릉","양양P/P 345kV #4 M.Tr 1차 CB (7372)","변전협력총액공사","○ 양양PP 345kV GIS 보통점검 - 7372CB","2020-05-04 10:00","2020-05-04 18:00","2020-05-06 10:00","2020-05-06 18:00","연속"]
[141,"강원","강릉","동해양양PP T/L","양양PP 송전선로 보호반 교체","○ 양양PP 송전선로 보호반 교체 ○ 컨트롤블록 교체 ○ 송변전광단말장치 설치","2020-05-25 10:00","2020-05-30 18:00","2020-05-25 10:00","2020-05-30 18:00","연속"]
[142,"강원","동해","동해S/S #3 M.Tr","2020년 동해전력지사 변전정비 협력회사 총액공사","1. 76 Bay B/F PNL 대체 2. 2차 차단기 조작시험","2020-05-11 09:30","2020-05-15 18:00","2020-05-11 09:30","2020-05-15 18:00","연속"]
[143,"강원","동해","동해삼척GP#2 T/L","345kV 동해-삼척GPT/L 전선접속개소 전선교체공사","전선접속개소 전선교체공사","2020-05-09 08:00","2020-05-20 18:00","2020-05-09 08:00","2020-05-20 18:00","연속"]
[144,"충북","청주","신옥천세종#2 T/L","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 345kV 72BAY B/F반 교체 공사","2020-05-25 10:00","2020-05-28 18:00","취소","취소","연속"]
[145,"충북","청주","신옥천북경남 T/L","345kV 신옥천-북경남T/L 전력선 교체공사","- 전력선 교체 No.258~259, No.260~261, No.265~267 - 가공지선 교체 : No.261~263, No.248~253, No,237~238","2020-05-23 07:00","2020-05-30 18:00","2020-05-23 07:00","2020-05-30 18:00","연속"]
[146,"충북","청주","신옥천S/S 345kV #75 BUS","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 345kV 75BUS 모선보호반 교체 공사","2020-05-18 10:00","2020-05-21 18:00","2020-05-18 10:00","2020-05-21 18:00","연속"]
[147,"충북","청주","신옥천신남원#1 T/L","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 345kV 74BAY B/F반 교체 공사","2020-05-11 10:00","2020-05-14 18:00","2020-05-11 10:00","2020-05-14 18:00","연속"]
[148,"충북","청주","신옥천S/S #2 M.Tr","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 345kV 74BAY B/F반 교체 공사","2020-05-11 10:00","2020-05-14 18:00","2020-05-11 10:00","2020-05-14 18:00","연속"]
[149,"충북","충주","신제천신충주#2 T/L","345kV 곤지암-신충주 등 4개T/L 전력선교체공사","전선접소개소 해소 전력선교체공사","2020-05-06 08:00","2020-05-09 18:00","2020-05-06 08:00","2020-05-09 18:00","연속"]
[150,"충북","충주","신제천신충주#1 T/L","345kV 곤지암-신충주 등 4개T/L 전력선교체공사","전선접소개소 해소 전력선교체공사","2020-05-02 08:00","2020-05-05 18:00","2020-05-02 08:00","2020-05-05 18:00","연속"]
[151,"대전충남","서산","당진T/P #72 Tie-Tr","20년 서산P/O 345kV M.Tr 정밀점검공사","당진화력S/S 345kV #72Tie-Tr 정밀점검","2020-05-04 09:00","2020-05-21 18:00","2020-05-04 09:00","2020-05-21 18:00","연속"]
[152,"대전충남","서산","태안T/P 345kV 개폐소-태안화력#2T/L CB A (7971A)","20년 서산P/O 345kV GIS정밀점검 및 조작로드교체 공사","태안화력S/S 7971 GIS 정밀점검 및 조작로드 교체 (#72BUS휴전-8일)","2020-05-04 09:00","2020-05-08 18:00","2020-05-04 09:00","2020-05-08 18:00","연속"]
[153,"대전충남","청양","아산보령TP#2 T/L","[송전]345kV 청양-보령 등 9개TL 항공장애표시구 정비공사","345kV 아산-보령화력#2T/L 항공장애표시구 설치 - No.4~5, 27~28, 28~29, 31~32, 55~56, 58~59, 64~65, 76~77,86~87 (9경간)","2020-05-06 07:00","2020-05-08 18:00","취소","취소","매일"]
[154,"대전충남","청양","보령C/C 345kV 보령연락#1T/L CB A (7171(A))","보령C/C 7171CB 조작시험","보령C/C 7171CB 조작시험","2020-05-06 09:00","2020-05-06 18:00","2020-05-06 09:00","2020-05-06 18:00","연속"]
[155,"대전충남","서산","당진화력S/Y 345kV 2호기 1차 CB A (7272A)","20년도 장기 미동작 차단기 조작시험","당진T/P 345kV 2호기 1차 7272 CB 조작시험","2020-05-06 10:00","2020-05-06 14:00","2020-05-06 10:00","2020-05-06 14:00","연속"]
[156,"대전충남","서산","345kV #1 TIE TR-2호기 1차 CB B (7200B)","20년도 장기 미동작 차단기 조작시험","당진T/P 345kV TIE Tr 1차-2호기 1차 7200 CB 조작시험","2020-05-07 10:00","2020-05-07 14:00","2020-05-07 10:00","2020-05-07 14:00","연속"]
[157,"대전충남","서산","태안T/P 345kV #72 BUS","20년 서산P/O 345kV GIS정밀점검 및 조작로드교체 공사","태안화력S/S 7971 GIS 조작로드 교체 무부하가압","2020-05-08 09:00","2020-05-08 18:00","2020-05-08 09:00","2020-05-08 18:00","연속"]
[158,"대전충남","서산","태안T/P 345kV #71-#72 SEC CB (71-72-0C)","20년 서산P/O 345kV GIS정밀점검 및 조작로드교체 공사","태안화력S/S 7971 GIS 조작로드 교체 무부하가압","2020-05-08 09:00","2020-05-08 18:00","2020-05-08 09:00","2020-05-08 18:00","연속"]
[159,"대전충남","서산","북당진현대제철 T/L","345kV 신송산분기T/L 건설사업","해당구간 : No.71 ~ No.69 구간내 No.70 선로 - 공사내용 : No.70 선로 가철탑 이설 전력선 공중이동 ACSR/AW 480SQ x 4B x 2C (0.793km)","2020-05-11 07:00","2020-05-14 18:00","취소","취소","연속"]
[160,"대전충남","청양","청양보령TP#1 T/L","청양S/S #71BAY B/F반 교체","청양S/S #71BAY B/F반 교체","2020-05-11 09:00","2020-05-15 18:00","취소","취소","연속"]
[161,"대전충남","청양","신계룡청양 T/L","청양S/S #71BAY B/F반 교체","청양S/S #71BAY B/F반 교체","2020-05-11 09:00","2020-05-15 18:00","2020-05-11 09:00","2020-05-15 18:00","연속"]
[162,"대전충남","아산","신온양S/S #3 M.Tr","신온양S/S 345kV #3M.Tr 장기사용 보호배전반 교체","○신온양S/S 345kV #3M.Tr 보호배전반 교체 ○신온양S/S 345kV #3M.Tr 3차측 GIS PD발생 관련 점검","2020-05-11 10:00","2020-05-15 18:00","2020-05-11 10:00","2020-05-15 18:00","연속"]
[163,"대전충남","서산","산서산S/S 345kV 신서산--신당진#2T/L CB A (7772A)","20년 서산P/O 변전정비 총액공사","신서산S/S 신서산-신당진#2T/L GIS (7772) 보통점검","2020-05-14 09:00","2020-05-14 18:00","2020-05-14 09:00","2020-05-14 18:00","연속"]
[164,"대전충남","서산","신당진개폐소현대제철 T/L","345kV 신송산분기T/L 건설사업","해당구간 : No.71 ~ No.69 구간내 No.70 선로 - 공사내용 : No.70 선로 가철탑 이설 전력선 공중이동 ACSR/AW 480SQ x 4B x 2C (0.793km)","2020-05-15 07:00","2020-05-18 18:00","취소","취소","연속"]
[165,"대전충남","서산","태안T/P 345kV #76-#77 SEC CB (76-77-0C)","20년 서산P/O 345kV GIS정밀점검 및 조작로드교체 공사","태안화력S/S 7900 GIS 조작로드 교체 무부하가압","2020-05-15 09:00","2020-05-15 18:00","2020-05-15 09:00","2020-05-15 18:00","연속"]
[166,"대전충남","서산","태안T/P 345kV #77 BUS","20년 서산P/O 345kV GIS정밀점검 및 조작로드교체 공사","태안화력S/S 7900 GIS 조작로드 교체 무부하가압","2020-05-15 09:00","2020-05-15 18:00","2020-05-15 09:00","2020-05-15 18:00","연속"]
[167,"대전충남","서산","태안T/P 345kV #9 GEN 1차 CB A (7972A)","20년 서산P/O 345kV GIS정밀점검 및 조작로드교체 공사","태안화력S/S 7972 GIS 정밀점검 및 조작로드 교체 (#77BUS휴전-22일)","2020-05-18 09:00","2020-05-22 18:00","2020-05-18 09:00","2020-05-22 18:00","연속"]
[168,"대전충남","아산","신온양S/S #4 M.Tr","신온양S/S 345kV #4M.Tr 장기사용 보호배전반 교체","○신온양S/S 345kV #4M.Tr 보호배전반 교체","2020-05-18 09:00","2020-05-22 18:00","2020-05-18 09:00","2020-05-22 18:00","연속"]
[169,"대전충남","청양","신옥천청양 T/L","청양S/S #74BAY B/F반 교체","청양S/S #74BAY B/F반 교체","2020-05-18 09:00","2020-05-22 18:00","2020-05-18 09:00","2020-05-22 18:00","연속"]
[170,"대전충남","청양","청양군산#1 T/L","청양S/S #74BAY B/F반 교체","청양S/S #74BAY B/F반 교체","2020-05-18 09:00","2020-05-22 18:00","2020-05-18 09:00","2020-05-22 18:00","연속"]
[171,"대전충남","서산","북당진S/S 345kV 7671T/L-#1M.Tr 1차 CB A (7600_A)","345kV 북당진S/S #1M.Tr 증설공사","#1M.Tr 실부하가압","2020-05-19 08:00","2020-05-19 18:00","2020-05-19 08:00","2020-05-19 18:00","연속"]
[172,"대전충남","서산","북당진S/S #1 M.Tr","345kV 북당진S/S #1M.Tr 증설공사","M.TR 실부하 가압","2020-05-19 08:00","2020-05-19 18:00","2020-05-19 08:00","2020-05-19 18:00","연속"]
[173,"대전충남","서산","당진T/P #71 Tie-Tr","당진화력S/Y 154kV 장기사용 GIS 대체공사","당진화력S/Y 154kV 장기사용 GIS 대체공사","2020-05-22 09:00","2020-06-08 18:00","2020-05-22 09:00","2020-06-08 18:00","연속"]
[174,"대전충남","서산","태안T/P 345kV #77 BUS","20년 서산P/O 345kV GIS정밀점검 및 조작로드교체 공사","태안화력S/S 7972 GIS 조작로드 교체 무부하가압","2020-05-22 09:00","2020-05-22 18:00","2020-05-22 09:00","2020-05-22 18:00","연속"]
[175,"대전충남","서산","태안T/P 345kV #76-#77 SEC CB (76-77-0C)","20년 서산P/O 345kV GIS정밀점검 및 조작로드교체 공사","태안화력S/S 7972 GIS 조작로드 교체 무부하가압","2020-05-22 09:00","2020-05-22 18:00","2020-05-22 09:00","2020-05-22 18:00","연속"]
[176,"대전충남","대전","신옥천신계룡 T/L","[송전]345kV 신옥천-신계룡T/L 스페이서댐퍼교체 및 정밀점검","[송전]345kV 신옥천-신계룡T/L 스페이서댐퍼교체 및 정밀점검 ○ 스페이서댐퍼교체 : No.20~23, 65~77 ○ 정밀점검 : No.72~신계룡S/S","2020-05-25 07:00","2020-05-28 18:00","2020-05-25 07:00","2020-05-28 18:00","매일"]
[177,"대전충남","서산","태안T/P 345kV #71-#72 SEC CB (71-72-0C)","20년 서산P/O 345kV GIS정밀점검 및 조작로드교체 공사","태안화력S/S 71-72-0 SEC-GIS 조작로드 교체 (#71,72BUS휴전-29일)","2020-05-25 09:00","2020-05-29 18:00","2020-05-25 09:00","2020-05-29 18:00","연속"]
[178,"대전충남","서산","당진화력S/Y 765kV #1 TIE TR 2차 CB A (7271A)","20년도 장기 미동작 차단기 조작시험","당진T/P 345kV TIE Tr 2차 7271 CB 조작시험","2020-05-26 14:00","2020-05-26 18:00","2020-05-26 14:00","2020-05-26 18:00","연속"]
[179,"대전충남","서산","신당진S/S 345kV 신당진연락#2T/L-#3 M.Tr 1차 TIE CB A (7800A)","20년도 장기 미동작 차단기 조작시험","신당진S/S 345kV #3M.Tr TIE 7800 CB 조작시험","2020-05-28 10:00","2020-05-28 14:00","2020-05-28 10:00","2020-05-28 14:00","연속"]
[180,"대전충남","서산","신당진S/S 345kV #3 M.Tr 1차 CB A (7872A)","20년도 장기 미동작 차단기 조작시험","신당진S/S 345kV #3M.Tr 1차 7872 CB 조작시험","2020-05-28 14:00","2020-05-28 18:00","2020-05-28 14:00","2020-05-28 18:00","연속"]
[181,"대전충남","서산","태안T/P 345kV #72 BUS","20년 서산P/O 345kV GIS정밀점검 및 조작로드교체 공사","태안화력S/S 71-72-0 SEC-GIS 조작로드 교체 (#71,72BUS휴전-29일)","2020-05-29 09:00","2020-05-29 18:00","2020-05-29 09:00","2020-05-29 18:00","연속"]
[182,"대전충남","서산","태안T/P 345kV #71 BUS","20년 서산P/O 345kV GIS정밀점검 및 조작로드교체 공사","태안화력S/S 71-72-0 SEC-GIS 조작로드 교체 (#71,72BUS휴전-29일)","2020-05-29 09:00","2020-05-29 18:00","취소","취소","연속"]
[183,"전북","군산","군산새만금#1 T/L","군산P/O 차단기 점검공사(군산-새만금#1T/L 조작시험)","군산S/S CB 7871 조작시험 새만금S/S 7271, 7200 조작시험","2020-05-12 09:00","2020-05-12 18:00","2020-05-12 09:00","2020-05-12 18:00","연속"]
[184,"전북","군산","청양군산#2 T/L","군산P/O 차단기 점검공사(청양-군산#2T/L CB 보통점검)","CB 7471 보통점검","2020-05-08 09:00","2020-05-08 18:00","2020-05-08 09:00","2020-05-08 18:00","연속"]
[185,"전북","군산","군산새만금#2 T/L","군산P/O 차단기 점검공사(군산-새만금#2T/L 조작시험)","군산S/S CB 7771 조작시험 새만금S/S 7371, 7300 조작시험","2020-05-11 09:00","2020-05-11 18:00","2020-05-11 09:00","2020-05-11 18:00","연속"]
[186,"전북","군산","청양군산#1 T/L","군산P/O 차단기 점검공사(청양-군산#1T/L CB 보통점검)","CB 7371, 7300 보통점검","2020-05-07 09:00","2020-05-07 18:00","2020-05-07 09:00","2020-05-07 18:00","연속"]
[187,"전북","군산","군산신김제#2 T/L","군산P/O 차단기 점검공사(군산-신김제#2T/L 보통점검)","CB 7171, 7100 보통점검 인출 LA, CVT 보통점검","2020-05-04 09:00","2020-05-04 18:00","2020-05-04 09:00","2020-05-04 18:00","연속"]
[188,"전북","군산","군산신김제#1 T/L","군산P/O 차단기 점검공사(군산-신김제#1T/L 보통점검)","CB 7271 보통점검","2020-05-06 09:00","2020-05-06 18:00","2020-05-06 09:00","2020-05-06 18:00","연속"]
[189,"전북","군산","새만금S/S 345kV #2M.Tr 1차 CB A (7272/A)","군산P/O 차단기 점검공사(새만금#2M.Tr 1차 CB 조작시험)","새만금S/S CB 7272 조작시험","2020-05-13 09:00","2020-05-13 11:00","2020-05-13 09:00","2020-05-13 11:00","연속"]
[190,"전북","군산","새만금S/S 345kV #3M.Tr 1차 CB A (7372/A)","군산P/O 차단기 점검공사(새만금#3M.Tr 1차 CB 조작시험)","새만금S/S CB 7372 조작시험","2020-05-13 13:00","2020-05-13 15:00","2020-05-13 13:00","2020-05-13 15:00","연속"]
[191,"전북","군산","새만금S/S 345kV #1 Sh.R","군산P/O 차단기 점검공사(새만금#1Sh.R CB 조작시험)","새만금S/S CB 7400, 7472 조작시험","2020-05-14 09:00","2020-05-14 13:00","2020-05-14 09:00","2020-05-14 13:00","연속"]
[192,"전북","김제","신김제한빛NP#1 T/L","345kV 신김제-한빛#1T/L 전력선 교체공사","가. 전력선 교체 : 2.973C-km (No.135〜143호) 나. 스페이서댐퍼 설치 / 철거 : 138개 / 126개 다. 점퍼선 교체 : 1기 (No.143호) 라. 기타 부대공사","2020-05-25 08:00","2020-06-07 18:00","취소","취소","연속"]
[193,"전북","김제","신김제S/S #3 M.Tr","154kV #1,2,3Sh.C 차단부 제작사 정밀점검","- 6179 차단부 철거 중 안전이격 확보","2020-05-01 09:00","2020-05-04 18:00","2020-05-06 09:00","2020-05-06 18:00","연속"]
[194,"전북","직할","북경남무주양수 T/L","345kV 신옥천-북경남T/L 전력선 교체공사","345kV 신옥천-북경남T/L 전력선 교체공사 - 전력선교체공사 : No.258~259","2020-05-21 07:00","2020-05-22 18:00","2020-05-21 07:00","2020-05-22 18:00","연속"]
[195,"전북","직할","신남원의령#2 T/L","신남원S/S GAS 누기보수공사(7452/7471)","신남원S/S GAS 누기보수공사 [휴전개소 : 신남원-의령#2T/L, #75BUS(~05/25), #70BUS(~05/29)] [작업개소 : 7452DS(A/B/C,~05/25), 7471(B,~05/29)]","2020-05-25 10:00","2020-05-28 18:00","2020-05-25 10:00","2020-05-28 18:00","연속"]
[196,"전북","직할","신남원S/S 345kV #70 BUS","신남원S/S GAS 누기보수공사(#70BUS)","신남원S/S GAS 누기보수공사 [휴전개소 : #70BUS] [작업개소] - 7271/7200(04/07~04/27) - 7471(05/26~05/29) - 7371(05/30~06/02) - 7671/7661(06/15~06/28)","2020-05-25 10:00","2020-05-28 18:00","2020-05-25 10:00","2020-05-28 18:00","연속"]
[197,"전북","직할","신남원의령#1 T/L","신남원S/S GAS 누기보수공사(7371)","신남원S/S GAS 누기보수공사 [휴전개소 : 신남원-의령#1T/L, #70BUS] [작업개소 : 7371(A)]","2020-05-29 10:00","2020-05-30 18:00","2020-05-29 10:00","2020-05-30 18:00","연속"]
[198,"전북","직할","신남원S/S 345kV #75 BUS","신남원S/S GAS 누기보수공사(#75BUS)","신남원S/S GAS 누기보수공사 [휴전개소 : #75BUS] [작업개소] - 7600(04/28~05/21) - 7272(05/02~05/13) - 7352/7452(05/14~05/25) - 7500(06/03~06/14)","2020-05-29 10:00","2020-06-16 18:00","2020-05-29 10:00","2020-06-16 18:00","연속"]
[199,"광주전남","순천","광양S/S #2 M.Tr","20~21년 순천전력지사 변전정비회사 총액공사","#2M.Tr 부싱 도블, 절연유 채유, 1차 GIS 초기점검","2020-05-04 09:00","2020-05-04 18:00","취소","취소","연속"]
[200,"광주전남","순천","신강진광양#2 T/L","광양S/S 362kV GIS 용량 대체공사","○ 광양S/S 362kV GIS 용량 대체 안전이격 확보 - #70-#71Sec CB대체(50kA→63kA) - 7751DS 및 #71BUS(77Bay) M-BUS 대체","2020-05-06 09:00","2020-05-19 13:00","2020-05-06 09:00","2020-05-19 13:00","연속"]
[201,"광주전남","순천","광양S/S 345kV #71 BUS","광양S/S 362kV GIS 용량 대체공사","○ 광양S/S 362kV GIS 용량 대체 - #70-#71Sec CB대체(50kA→63kA)","2020-05-06 09:00","2020-07-02 18:00","2020-05-06 09:00","2020-07-02 18:00","연속"]
[202,"광주전남","순천","광양S/S 345kV #70 BUS","광양S/S 362kV GIS 용량 대체공사","○ 광양S/S 362kV GIS 용량 대체 - #70-#71Sec CB대체(50kA→63kA)","2020-05-06 09:00","2020-07-02 18:00","2020-05-06 09:00","2020-07-02 18:00","연속"]
[203,"광주전남","순천","광양S/S 345kV #70-#71 SEC CB (70-71-0)","광양S/S 362kV GIS 용량대체공사","○ 광양S/S 362kV GIS 용량대체공사 - #70-#71Sec CB 대체(50kA → 63kA)","2020-05-06 09:00","2020-07-02 18:00","2020-05-06 09:00","2020-07-02 18:00","연속"]
[204,"광주전남","광주","신남원신광주#2 T/L","20년 광주변전총액공사(신남원-신광주#2 CVT 점검)","-345kV 신남원-신광주#2T/L CVT 보통점검","2020-05-08 09:00","2020-05-08 18:00","2020-05-08 09:00","2020-05-08 18:00","연속"]
[205,"광주전남","목포","한빛2NP한빛3NP#4 T/L","목포전력지사 362kV GIS 정밀점검공사","7B72 GIS 정밀점검","2020-05-18 10:00","2020-05-21 18:00","2020-05-18 10:00","2020-05-21 18:00","연속"]
[206,"광주전남","광주","신광주S/S #3 M.Tr","20년 광주변전총액공사(신광주#3M.Tr)","신광주S/S #3M.Tr 보통점검","2020-05-13 09:30","2020-05-15 18:00","2020-05-13 09:30","2020-05-15 18:00","연속"]
[207,"광주전남","순천","여수T/P #3  Tie-Tr","20년 상반기 순천전력지사 345kV GIS 정밀점검공사","여수화력 7300,7372 GIS 정밀점검 ( 7302 , 7362, 7322 DS 포함)","2020-05-18 09:00","2020-05-22 18:00","2020-05-18 09:00","2020-05-22 18:00","연속"]
[208,"광주전남","광주","신광주S/S #4 M.Tr","20년 광주변전총액공사(신광주#4M.Tr)","신광주S/S #4M.Tr B/F 보호판넬 교체","2020-05-18 09:30","2020-05-22 18:00","2020-05-18 09:30","2020-05-22 18:00","연속"]
[209,"광주전남","순천","신강진광양#1 T/L","광양S/S 362kV GIS 용량 대체공사","○ 광양S/S 362kV GIS 용량 대체 안전이격 확보 - #70-#71Sec CB대체(50kA→63kA) - 7851DS 및 #71BUS(78Bay) M-BUS 대체","2020-05-19 14:00","2020-06-04 18:00","2020-05-19 14:00","2020-06-04 18:00","연속"]
[210,"광주전남","광주","신화순S/S #1 M.Tr","20년 광주변전총액공사(신화순#1M.Tr)","신화순S/S #1M.Tr 보통점검, 4185DS 보통점검, #1S.Tr 하자점검, 1,2,3차 LA 하자점검, 3차 PT 보통점검","2020-05-20 09:30","2020-05-22 18:00","2020-05-20 09:30","2020-05-22 18:00","연속"]
[211,"광주전남","순천","여수T/P #2 Tie-Tr","20년 상반기 순천전력지사 345kV GIS 정밀점검공사","여수화력 7200,7272 GIS 정밀점검","2020-05-25 09:00","2020-05-29 18:00","2020-05-25 09:00","2020-05-29 18:00","연속"]
[212,"광주전남","광주","신화순S/S #2 M.Tr","20년 광주변전총액공사(신화순#2M.Tr)","신화순S/S #2M.Tr 보통점검, 1,2,3차 LA 및 3차 PT 보통점검","2020-05-25 09:30","2020-05-27 18:00","2020-05-25 09:30","2020-05-27 18:00","연속"]
[213,"광주전남","광주","신광주S/S #2 M.Tr","20년 광주변전총액공사(신광주 #2M.Tr)","-345kV 신광주 #2M.Tr LA 초기점검","2020-05-29 09:00","2020-05-29 18:00","2020-05-29 09:00","2020-05-29 18:00","연속"]
[214,"광주전남","광주","신화순S/S #3 M.Tr","2020년 광주전력지사 170kV GIS 정밀점검공사","2020년 광주전력지사 170kV GIS 정밀점검공사","2020-05-28 09:00","2020-05-29 18:00","2020-05-28 09:00","2020-05-29 18:00","연속"]
[215,"대구","경산","신경산S/S #1 M.Tr","20년 상반기 경산P/O 170kV GIS 정밀점검 공사","- GIS정밀점검, 전자변 교체 (6144 GIS)","2020-05-11 09:00","2020-05-12 18:00","2020-05-11 09:00","2020-05-12 18:00","연속"]
[216,"대구","경산","신경산대구#1 T/L","2020년 가공송전 순시점검 위탁공사 정밀점검","345kV 신경산-대구#1T/L 정밀점검 시행","2020-05-07 09:00","2020-05-21 18:00","2020-05-07 09:00","2020-05-19 18:00","연속"]
[217,"대구","경산","신경산S/S #4 M.Tr","20년 상반기 경산P/O 170kV GIS 정밀점검 공사","- 6444 차단부 정밀점검","2020-05-05 09:00","2020-05-06 18:00","취소","취소","연속"]
[218,"대구","달성","고령S/S #1 M.Tr","고령S/S #1M.Tr 및 1,2차 초기점검","고령S/S #1M.Tr 및 1,2차 초기점검","2020-05-28 09:00","2020-05-28 18:00","2020-05-28 09:00","2020-05-28 18:00","연속"]
[219,"대구","달성","대구S/S #2 M.Tr","대구S/S #2M.Tr 및 1,2차 보통점검","대구S/S #2M.Tr 및 1,2차 보통점검","2020-05-25 09:00","2020-05-26 18:00","2020-05-25 09:00","2020-05-26 18:00","연속"]
[220,"대구","칠곡","북대구S/S 345kV #2 M.Tr 1차 CB A (7472)","북대구S/S #2 M.Tr 1차 GIS Control block 교체","북대구S/S 345kV #2 M.Tr 1차 GIS Control block 교체","2020-05-13 09:30","2020-05-15 18:00","2020-05-13 09:30","2020-05-15 18:00","연속"]
[221,"대구","칠곡","북대구S/S 345kV #1 M.Tr 1차 CB A (7372)","부대구S/S #1 M.Tr CB Control Block 교체","북대구S/S#1 M.Tr CB Control Block 교체작업","2020-05-20 14:00","2020-05-22 18:00","2020-05-20 14:00","2020-05-22 18:00","연속"]
[222,"대구","칠곡","북대구S/S 345kV 서대구#1T/L-#2 M.Tr 1차 TIE CB A (7400)","서대구#1T/L-#2M.Tr 1차TIE CB ControlBlock 교체","부대구S/S 서대구#1T/L-#2 M.Tr 1차 TIE CB Control Block 교체","2020-05-27 14:00","2020-05-29 18:00","2020-05-27 14:00","2020-05-29 18:00","연속"]
[223,"대구","칠곡","북대구S/S 345kV 북대구-서대구#1T/L CB A (7471)","북대구S/S 북대구-서대구#1T/L CB Control Block 교체","부대구S/S 북대구-서대구#1T/L CB Control Block 교체","2020-05-25 09:30","2020-05-27 14:00","2020-05-25 09:30","2020-05-27 14:00","연속"]
[224,"대구","칠곡","북대구S/S 345kV 서대구#2T/L-#1 M.Tr 1차 TIE CB A (7300)","서대구#2T/L-#1 M.Tr CB ControlBlock 교체","북대구S/S 서대구#2T/L-#1 M.Tr CB Control Block 교체작업","2020-05-18 09:30","2020-05-20 14:00","2020-05-18 09:30","2020-05-20 14:00","연속"]
[225,"대구","칠곡","서대구S/S 345kV 서대구-고령#2T/L-TIE CB A (7200)","서대구S/S 345kV GCB 공기조작부 정밀점검","서대구S/S 345kV GCB 공기조작부 정밀점검","2020-05-20 09:00","2020-05-21 18:00","2020-05-20 09:00","2020-05-21 18:00","연속"]
[226,"대구","칠곡","서대구S/S 345kV 서대구-고령#2T/L CB A (7271)","서대구S/S 345kV GCB 공기조작부 정밀점검","서대구S/S 345kV GCB 공기조작부 정밀점검","2020-05-18 09:00","2020-05-19 18:00","2020-05-18 09:00","2020-05-19 18:00","연속"]
[227,"대구","칠곡","서대구S/S 345kV 서대구-선산#2T/L CB A (7872)","서대구S/S 345kV GCB 공기조작부 정밀점검","서대구S/S 345kV GCB 공기조작부 정밀점검","2020-05-25 09:00","2020-05-26 18:00","2020-05-25 09:00","2020-05-26 18:00","연속"]
[228,"대구","포항","신월성N/P 345kV 신포항-신월성NP#4T/L CB A (7171-A)","신월성S/Y 7171,7271 GIS 조작시험","신월성S/Y 7171,7271 GIS 조작시험","2020-05-22 09:30","2020-05-22 14:00","2020-05-22 09:30","2020-05-22 14:00","연속"]
[229,"대구","포항","신월성N/P 345kV 월성연락#2T/L CB A (7271-A)","신월성S/Y 7171,7271 GIS 조작시험","신월성S/Y 7171,7271 GIS 조작시험","2020-05-22 14:00","2020-05-22 18:00","2020-05-22 14:00","2020-05-22 18:00","연속"]
[230,"대구","포항","신월성NP#4-#2 M.Tr 2차 TIE CB A (7100-A)","신월성S/Y 7100, 7172 GIS 조작시험","신월성S/Y 7100, 7172 GIS 조작시험","2020-05-25 09:30","2020-05-25 14:00","2020-05-25 09:30","2020-05-25 14:00","연속"]
[231,"대구","포항","신월성N/P 345kV #2 M.Tr 1차 CB A (7172-A)","신월성S/Y 7100, 7172 GIS 조작시험","신월성S/Y 7100, 7172 GIS 조작시험","2020-05-25 14:00","2020-05-25 18:00","2020-05-25 14:00","2020-05-25 18:00","연속"]
[232,"대구","포항","신포항북대구 T/L","345kV 신포항-북대구T/L 전력선교체공사","345kV 신포항-북대구T/L 전력선교체공사 공사구간 : 345kV 신포항-북대구T/L No.202~205, 208~219, 265~272 전력선교체 : ACSR 480㎟*4B*2C, 14.645C_km 가공지선교체 : ACSR 120㎟ 7.623C_km","2020-05-07 07:00","2020-05-22 18:00","2020-05-07 07:00","2020-05-22 18:00","연속"]
[233,"대구","포항","월성2N/P 345kV 울주-월성#1T/L-#3 M.Tr 2차 CB A (7500-A)","월성S/Y 7571, 7500 CB 조작시험","월성S/Y 7571, 7500 CB 조작시험","2020-05-28 14:00","2020-05-28 18:00","2020-05-28 14:00","2020-05-28 18:00","연속"]
[234,"대구","포항","월성2N/P 345kV 울주-월성N/P #1T/L CB A (7571-A)","월성S/Y 7571, 7500 CB 조작시험","월성S/Y 7571, 7500 CB 조작시험","2020-05-28 09:30","2020-05-28 14:00","2020-05-28 09:30","2020-05-28 14:00","연속"]
[235,"대구","포항","울주월성NP#2 T/L","'20-21년도 포항전력지사 가공송전 정비회사 총액공사","345kV울주-월성NP#2 T/L 소도체 이도조정","2020-05-25 08:00","2020-05-29 18:00","2020-05-25 08:00","2020-05-29 18:00","연속"]
[236,"대구","경산","신경산대구#2 T/L","2020년 가공송전 순시점검 위탁공사 정밀점검","2020년 가공송전 순시점검 위탁공사 정밀점검","2020-05-22 09:00","2020-06-01 18:00","2020-05-20 09:00","2020-06-01 18:00","연속"]
[237,"경북","구미","북대구선산 T/L","2020-21년도 구미전력지사 변전정비업체 총액공사","-7371,7300 GIS보통점검","2020-05-14 09:00","2020-05-14 18:00","취소","취소","연속"]
[238,"경북","구미","선산S/S #4 M.Tr","2020-21년도 구미전력지사 변전정비업체 총액공사","-96P 누유보수 -7700,7772GIS조작시험 -1차PT 보통점검, 3차 GPT보통점검 -1,2,3차 LA하자점검 -1,2차 부싱절연유 채유","2020-05-07 09:00","2020-05-08 18:00","2020-05-07 09:00","2020-05-08 18:00","연속"]
[239,"경북","영주","신영주S/S #3 M.Tr","2020-21년 영주전력지사 변전정비회사 총액공사","- #3M.Tr 보통점검 - 6344 차단기 보통점검 - 2,3차 LA 보통점검 - 3차 PT 보통점검 - 부싱절연유 채유","2020-05-06 09:00","2020-05-07 18:00","취소","취소","연속"]
[240,"경북","직할","안동C/C #1 Tie-Tr","20~21년 경북본부 직할 변전정비회사 총액공사","7100 GIS 하자점검","2020-05-13 14:00","2020-05-13 18:00","2020-05-13 14:00","2020-05-13 18:00","연속"]
[241,"경북","직할","안동C/C #1 Tie-Tr","20~21년 경북본부 직할 변전정비회사 총액공사","#1 M.Tr, 6144, 4189 하자점검","2020-05-14 09:00","2020-05-15 18:00","2020-05-14 09:00","2020-05-15 18:00","연속"]
[242,"경북","직할","안동복합S/S 345kV #1 M.Tr 1차 GIS","20~21년 경북본부 직할 변전정비회사 총액공사","7171 GIS 하자점검","2020-05-13 09:00","2020-05-13 14:00","2020-05-13 09:00","2020-05-13 14:00","연속"]
[243,"부산울산","동부산","고리2N/P 345kV #72 BUS","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(7D71 - 4시간)","2020-05-16 09:00","2020-05-16 13:00","2020-05-22 16:00","2020-05-22 18:00","연속"]
[244,"부산울산","동부산","고리NP#1고리NP#2 #1 T/L","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선공사(7677)","2020-05-18 09:00","2020-05-23 11:00","취소","취소","연속"]
[245,"부산울산","동부산","고리2N/P 345kV #76 BUS","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(7677 - 2시간)","2020-05-23 09:00","2020-05-23 11:00","취소","취소","연속"]
[246,"부산울산","동부산","고리2N/P 345kV #72 BUS","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(71-72-0 - 4시간)","2020-05-23 09:00","2020-05-23 13:00","2020-05-29 16:00","2020-05-29 18:00","연속"]
[247,"부산울산","동부산","고리NP S/Y 345kV 신고리 #3, 4 SAT CB A (7D71_A)","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선공사(7D71)","2020-05-11 09:00","2020-05-16 13:00","2020-05-18 09:00","2020-05-22 18:00","연속"]
[248,"부산울산","동부산","고리NP S/Y 345kV #76-#77 SEC CB (76-77-0)","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선공사(76-77-0)","2020-05-25 09:00","2020-05-30 11:00","취소","취소","연속"]
[249,"부산울산","동부산","고리NP S/Y 345kV #71-#72 SEC CB (71-72-0)","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선공사(71-72-0)","2020-05-18 09:00","2020-05-23 13:00","2020-05-25 09:00","2020-05-29 18:00","연속"]
[250,"부산울산","동부산","고리2N/P 345kV #72 BUS","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(7B71 - 4시간)","2020-05-09 09:00","2020-05-09 13:00","2020-05-15 16:00","2020-05-15 18:00","연속"]
[251,"부산울산","동부산","고리2N/P 345kV #77 BUS","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(76-77-0 - 2시간)","2020-05-30 09:00","2020-05-30 11:00","취소","취소","연속"]
[252,"부산울산","동부산","고리NP S/Y 345kV 울주-고리#1T/L CB A (7B71_A)","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선공사(7B71)","2020-05-04 09:00","2020-05-09 13:00","2020-05-11 09:00","2020-05-15 18:00","연속"]
[253,"부산울산","동부산","신양산S/S #4 M.TR","[7차] 345kV 신양산S/S 현대화공사","1. 내용 - 신양산-고리NP#1T/L 제어케이블 이설 - 345kV #4M.Tr 및 1,2,3차 제어케이블 이설 - 345kV #4M.Tr 2차 인출변경 - 154kV 신양산-기장#1T/L 인출변경","2020-05-20 09:00","2020-06-02 18:00","2020-05-20 09:00","2020-06-02 18:00","연속"]
[254,"부산울산","동부산","신양산고리NP#1 T/L","[7차] 345kV 신양산S/S 현대화공사","1. 내용 - 신양산-고리NP#1T/L 제어케이블 이설 - 345kV #4M.Tr 및 1,2,3차 제어케이블 이설 - 345kV #4M.Tr 2차 인출변경 - 154kV 신양산-기장#1T/L 인출변경","2020-05-20 09:00","2020-06-02 18:00","취소","취소","연속"]
[255,"부산울산","동부산","신양산신대연#1 T/L","[6차] 345kV 신양산S/S 현대화공사","1. 내용 - 신양산-신대연#1/L 제어케이블 이설","2020-05-12 09:00","2020-05-19 18:00","2020-05-12 09:00","2020-05-19 18:00","연속"]
[256,"부산울산","동부산","신양산북부산#1 T/L","[5차] 345kV 신양산S/S 현대화공사","1. 내용 - 신양산-북부산#1/L 제어케이블 이설","2020-05-07 09:00","2020-05-11 18:00","2020-05-07 09:00","2020-05-11 18:00","연속"]
[257,"부산울산","북부산","북부산S/S 서부산북부산#3T/L Sh.R","20-21 북부산전력지사 변전총액공사","북부산S/S 345kV 서부산-북부산#3T/L 7877 GIS 하자점검","2020-05-22 10:00","2020-05-22 18:00","2020-05-22 10:00","2020-05-22 18:00","연속"]
[258,"부산울산","북부산","북부산S/S 345kV 서부산-북부산#3T/L Sh.R CB A ((신)7877_A)","20-21 북부산전력지사 변전총액공사","북부산S/S 345kV 서부산-북부산#3T/L 7877 GIS 하자점검","2020-05-22 10:00","2020-05-22 18:00","2020-05-22 10:00","2020-05-22 18:00","연속"]
[259,"부산울산","북부산","북부산S/S 345kV #4 Sh.R 1차 선로측 CB A (7A77_A)","20-21 북부산전력지사 변전총액공사","북부산S/S 345kV #4Sh.R 하자점검 및 345kV #4Sh.R 1차 7900, 7972, 7A77 GIS 하자점검","2020-05-12 10:00","2020-05-13 18:00","2020-05-12 10:00","2020-05-13 18:00","연속"]
[260,"부산울산","북부산","북부산S/S 345kV 서부산#2-#4 Sh.R 1차 TIE CB A ((신)7900_A)","20-21 북부산전력지사 변전총액공사","북부산S/S 345kV #4Sh.R 하자점검 및 345kV #4Sh.R 1차 7900, 7972, 7A77 GIS 하자점검","2020-05-12 10:00","2020-05-13 18:00","2020-05-12 10:00","2020-05-13 18:00","연속"]
[261,"부산울산","북부산","신김해북부산#1 T/L","345kV 북부산-울산TP 등 4개 T/L 전선접속개소 전선교체공사","신김해-북부산 #1T/L : 4~8, 8~9. 9~10, 17~19호간 전선교체, 17호 피뢰기설치","2020-05-25 07:00","2020-06-03 18:00","2020-05-25 07:00","2020-06-03 18:00","연속"]
[262,"부산울산","북부산","신김해북부산#2 T/L","345kV 북부산-울산TP 등 4개 T/L 전선접속개소 전선교체공사","신김해-북부산 #2T/L : 4~8, 8~9. 9~10호간 전선교체","2020-05-18 07:00","2020-05-24 18:00","2020-05-18 07:00","2020-05-24 18:00","연속"]
[263,"부산울산","북부산","북부산S/S 345kV #76 BUS","2020 북부산전력지사 345kV GIS 정밀점검","북부산S/S 345kV #76BUS GIS 정밀점검 (7352DS, 7252DS)","2020-05-20 10:00","2020-05-21 18:00","2020-05-20 10:00","2020-05-21 18:00","연속"]
[264,"부산울산","북부산","북부산S/S 345kV #71 BUS","2020 북부산전력지사 345kV GIS 정밀점검","북부산S/S 345kV #71BUS GIS 정밀점검 (7351DS, 7251DS)","2020-05-18 10:00","2020-05-19 18:00","2020-05-18 10:00","2020-05-19 18:00","연속"]
[265,"부산울산","북부산","북부산S/S 345kV #4 Sh.R 1차 CB A ((신)7972_A)","20-21 북부산전력지사 변전총액공사","북부산S/S 345kV #4Sh.R 하자점검 및 345kV #4Sh.R 1차 7900, 7972, 7A77 GIS 하자점검","2020-05-12 10:00","2020-05-13 18:00","2020-05-12 10:00","2020-05-13 18:00","연속"]
[266,"부산울산","북부산","북부산S/S 345kV #4 Sh.R","20-21 북부산전력지사 변전총액공사","북부산S/S 345kV #4Sh.R 하자점검 및 345kV #4Sh.R 1차 7900, 7972, 7A77 GIS 하자점검","2020-05-12 10:00","2020-05-13 18:00","2020-05-12 10:00","2020-05-13 18:00","연속"]
[267,"부산울산","울산","신울산고리NP#2 T/L","345㎸ 신울산-고리NP T/L OPGW 시설공사","345㎸ 신울산-고리NP#2T/L OPGW 25.23㎞(70SQ/48C) 시설, S/T↔ICT실간 비금속광케이블 0.7㎞ 등 부대설비 1식","2020-05-18 07:00","2020-05-31 18:00","취소","취소","연속"]
[268,"부산울산","울산","신울산고리NP#1 T/L","345kV 신울산-고리NPT/L 송전용량증대전선교체공사","공사명 : 송전용량증대 전선교체공사 구간 : 42 ~ 51호, 6.662C-km 선종 : ACSR480*2B*2C => HSTACIR/AW410*2B*2C","2020-05-07 07:00","2020-05-15 18:00","취소","취소","연속"]
[269,"부산울산","울산","울주고리NP#2 T/L","2020년 345kV 개폐장치 정밀점검공사","시험가압 1h","2020-05-08 17:00","2020-05-08 18:00","2020-05-08 17:00","2020-05-08 18:00","연속"]
[270,"부산울산","울산","울주고리NP#2 T/L","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(7D71 - 4시간)","2020-05-16 09:00","2020-05-16 13:00","2020-05-22 16:00","2020-05-22 18:00","연속"]
[271,"부산울산","울산","울주고리NP#2 T/L","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(71-72-0 - 4시간)","2020-05-23 09:00","2020-05-23 13:00","2020-05-29 16:00","2020-05-29 18:00","연속"]
[272,"부산울산","울산","울주고리NP#1 T/L","2020년 345kV 개폐장치 정밀점검공사","7671 시험가압1H","2020-05-13 17:00","2020-05-13 18:00","2020-05-13 17:00","2020-05-13 18:00","연속"]
[273,"부산울산","울산","울주S/S 345kV 울주-고리NP#1T/L CB A (7671-A)","2020년 345kV 개폐장치 정밀점검공사","7671 GIS 정밀점검","2020-05-11 09:00","2020-05-13 18:00","2020-05-11 09:00","2020-05-13 18:00","연속"]
[274,"부산울산","울산","울주S/S 345kV 울주-신경산#2T/L TIE CB A (7700-A)","2020년 345kV 개폐장치 정밀점검공사","7771 GIS 정밀점검","2020-05-25 09:00","2020-05-27 18:00","2020-05-25 09:00","2020-05-27 18:00","연속"]
[275,"부산울산","울산","울주고리NP#2 T/L","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(7B71 - 4시간)","2020-05-09 09:00","2020-05-09 13:00","2020-05-15 16:00","2020-05-15 18:00","연속"]
[276,"부산울산","울산","울주S/S 345kV 울주-고리NP#2T/L TIE CB A (7500-A)","2020년 345kV 개폐장치 정밀점검공사","- 7500 GIS 정밀점검","2020-05-06 09:00","2020-05-08 18:00","2020-05-06 09:00","2020-05-08 18:00","연속"]
[277,"부산울산","울산","울주신경산#2 T/L","2020년 345kV 개폐장치 정밀점검공사","7771 GIS 정밀점검 후 시험가압 1H","2020-05-27 17:00","2020-05-27 18:00","2020-05-27 17:00","2020-05-27 18:00","연속"]
[278,"부산울산","울산","울주S/S 345kV 울주-고리NP#1T/L TIE CB A (7600-A)","2020년 345kV 개폐장치 정밀점검공사","7600 GIS 정밀점검","2020-05-18 09:00","2020-05-20 18:00","2020-05-18 09:00","2020-05-20 18:00","연속"]
[279,"부산울산","울산","울주고리NP#1 T/L","2020년 345kV 개폐장치 정밀점검공사","7600 GIS 정밀점검 후 시험가압1H","2020-05-20 17:00","2020-05-20 18:00","2020-05-20 17:00","2020-05-20 18:00","연속"]
[280,"부산울산","직할","신대연S/S #2 M.Tr","2020년 상반기 직할 170kV GIS 정밀점검공사","신대연S/S 345kV #2M.Tr 2차 (6244) GIS 정밀점검 -차단부 및 상부BUS, Cable Head부 정밀점검 -모선DS부 점검 제외","2020-05-20 09:00","2020-05-21 18:00","2020-05-20 09:00","2020-05-21 18:00","연속"]
[281,"부산울산","직할","신대연S/S 345kV #1 Sh.R","2020년 직할 변전정비회사 총액공사","#1Sh.R 7079GIS 차단기 동작시험","2020-05-27 10:00","2020-05-27 18:00","2020-05-27 13:00","2020-05-27 18:00","연속"]
[282,"부산울산","직할","신대연S/S #1 M.Tr","2020년 상반기 직할 170kV GIS 정밀점검공사","신대연S/S 345kV #1M.Tr 2차 (6144) GIS 정밀점검 -차단부 및 상부BUS, Cable Head부 정밀점검 -모선DS부 점검 제외","2020-05-06 09:00","2020-05-07 18:00","2020-05-06 09:00","2020-05-07 18:00","연속"]
[283,"부산울산","직할","신대연S/S 345kV #2 Sh.R","2020년 직할 변전정비회사 총액공사","#2Sh.R 7579GIS 차단기 동작시험","2020-05-26 10:00","2020-05-26 18:00","2020-05-26 13:00","2020-05-26 18:00","연속"]
[284,"경남","직할","신김해S/S #5 M.Tr","신김해S/S 345kV #76BAY TIE GIS 정밀점검","신김해S/S 345kV #76BAY TIE GIS 정밀점검 신김해S/S 345kV #5M.Tr 1, 2차 CB(7672, 6544)조작시험","2020-05-04 09:30","2020-05-08 17:30","2020-05-04 09:30","2020-05-08 17:30","연속"]
[285,"경남","직할","신김해신녹산#2 T/L","신김해S/S 345kV 신김해-신녹산#2T/L GIS 정밀점검","신김해S/S 345kV 신김해-신녹산#2T/L GIS(7871) 정밀점검 신김해S/S 345kV 신김해-신녹산#2T/L GIS(7800) 보통점검","2020-05-25 09:30","2020-05-29 17:30","2020-05-25 09:30","2020-05-29 17:30","연속"]
[286,"경남","진주","산청P/P 345kV 의령-산청PP#2T/L-#2 M.Tr 1차 CB A (7200_A)","산청P/P 의령-산청PP#2T/L-#2M.Tr 1차(7200) 정밀점검","산청P/P 의령-산청PP#2T/L-#2M.Tr 1차(7200) 정밀점검","2020-05-11 09:00","2020-05-17 18:00","2020-05-11 09:00","2020-05-17 18:00","연속"]
[287,"경남","진주","의령S/S 345kV 의령-하동화력#2T/L CB A (7271(A))","의령S/S 의령-하동화력#2T/L CB(7271) 정밀점검","의령S/S 의령-하동화력#2T/L CB(7271) 정밀점검","2020-05-18 09:00","2020-05-24 18:00","2020-05-18 09:00","2020-05-24 18:00","연속"]
[288,"경남","진주","의령S/S 345kV 의령-하동화력#2T/L TIE CB A (7200(A))","의령S/S 의령-하동화력#2T/L TIE CB(7200) 정밀점검","의령S/S 의령-하동화력#2T/L TIE CB(7200) 정밀점검","2020-05-25 09:00","2020-05-31 18:00","2020-05-25 09:00","2020-05-31 18:00","연속"]
[289,"경남","통영","창원삼천포TP#2 T/L","345kV 창원-삼천포화력T/L 전선접속개소 교체공사","345kV 창원-삼천포화력#2T/L 전선접속개소 교체공사(86~87호 등 5개구간)","2020-05-11 08:00","2020-05-24 18:00","2020-05-11 08:00","2020-05-24 18:00","연속"]
[290,"경남","통영","삼천포T/P 345kV 삼천포-TIE#1T/L CB (72272_A)","삼천포,신고성 차단기 용량대체공사","인출철구교체","2020-05-25 09:00","2020-06-05 18:00","2020-05-25 09:00","2020-06-05 18:00","연속"]
[291,"경남","통영","삼천포T/P 345kV 신마산-삼천포화력#2T/L CB B (72272_B)","삼천포,신고성 차단기 용량대체공사","인출철구교체","2020-05-25 09:00","2020-06-05 18:00","2020-05-25 09:00","2020-06-05 18:00","연속"]
[292,"경남","통영","신고성S/S #3 M.Tr","신고성S/S #3M.Tr 보통점검 및 OLTC 정밀점검 등 4건","1. 신고성S/S #3M.Tr 보통점검 및 OLTC 정밀점검 2. 신고성S/S #3M.Tr PNL 대체 3. (신)신고성 7572 GIS 하자점검 4. #6S.Tr 하자 점검, #3 S.Tr VCB 조작시험, #3M.Tr 1차 LA 하자점검","2020-05-18 10:00","2020-05-24 18:00","2020-05-18 10:00","2020-05-24 18:00","연속"]
[293,"경남","통영","신고성S/S #4 M.Tr","신고성S/S #4M.Tr 및 OLTC 정밀점검 등 4건","1. 신고성S/S #4M.Tr 및 OLTC 정밀점검 2. 신고성S/S 23kV #4-1,2,3 Sh.R, 3차 Main VCB 및 447-1,2,3 하자점검 3. (신)신고성 7672 GIS 하자점검 및 #4M.Tr 2차 GIS 보통점검 4. #4M.Tr 1,2,3차 LA 보통점검","2020-05-11 10:00","2020-05-17 18:00","2020-05-11 10:00","2020-05-17 18:00","연속"]
[294,"광주전남",null,"한빛N/P #5 대기보조변압기 CB (7B00, 7B71)","대기보조변압기 일반점검 등","대기보조변압기 일반점검 등","2020-05-14 09:00","2020-06-02 18:00","2020-05-14 09:00","2020-06-02 18:00","연속"]
[295,"전북","군산","새만금S/S 345kV #1 Sh.R CB(7472)","군산P/O 차단기 점검공사(새만금#1Sh.R CB 조작시험)","새만금S/S CB 7400, 7472 조작시험","2020-05-14 13:00","2020-05-14 18:00","2020-05-14 13:00","2020-05-14 18:00","연속"]
[296,"부산울산","울산","울주S/S 345kV #2 BUS","2020년 345kV 개폐장치 정밀점검공사","시험가압 1h","2020-05-08 17:00","2020-05-08 18:00","2020-05-08 17:00","2020-05-08 18:00","연속"]
[297,"부산울산","울산","울주S/S 345kV #1 BUS","2020년 345kV 개폐장치 정밀점검공사","7671 시험가압1H","2020-05-13 17:00","2020-05-13 18:00","2020-05-13 17:00","2020-05-13 18:00","연속"]

{"sheet":"154송부","index":2,"n_rows":614,"n_cols":13,"rows_kept":614,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2020년도 \"&[1]종합!R15&\"월 휴전계획서\"","v":"2020년도 5월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","군자화양#1 T/L","'20년 성동P/O 노후 보호배전반 교체공사","군자, 화양S/S 154kV 군자화양#1T/L 보호배전반 노후대체","2020-05-04 10:00","2020-05-08 17:00","2020-05-04 10:00","2020-05-08 17:00","연속"]
[2,"서울","성동","군자성수 T/L","'20년 성동P/O 노후 보호배전반 교체공사","군자, 성수S/S 154kV 군자성수T/L 보호배전반 노후대체","2020-05-11 10:00","2020-05-14 17:00","2020-05-11 10:00","2020-05-14 17:00","연속"]
[3,"서울","성동","군자화양#2 T/L","'20년 성동P/O 노후 보호배전반 교체공사","군자, 화양S/S 154kV 군자화양#2T/L 보호배전반 노후대체","2020-05-25 10:00","2020-05-28 17:00","2020-05-25 10:00","2020-05-28 17:00","연속"]
[4,"서울","성동","노원종암 T/L","장위4구역 전력구 지장전력설비 이설공사","○ 154kV 노원종암T/L M/H#7~10 구간 임시이설(20년) 및 본이설(21년) ○ 154kV 안암노원#1,2T/L M/H#7~10 구간 임시이설(20년) 및 본이설(21년)","2020-05-11 09:00","2020-05-28 18:00","2020-05-18 09:00","2020-06-04 18:00","연속"]
[5,"서울","성동","노원종암 T/L","2020년 성동 변전정비회사 총액공사","170kV GIS 보통점검","2020-05-25 10:00","2020-05-25 18:00","취소","취소","연속"]
[6,"서울","성동","성동S/S 154kV #61 BUS","2020년 성동P/O 154kV GIS 정밀점검공사","성동S/S 성동휘경#1T/L GIS 정밀점검 시험가압","2020-05-12 15:30","2020-05-12 17:30","2020-05-12 15:30","2020-05-12 17:30","연속"]
[7,"서울","성동","성동휘경#1 T/L","2020년 성동P/O 154kV GIS 정밀점검공사","성동S/S 성동휘경#1T/L GIS 정밀점검","2020-05-11 09:30","2020-05-12 17:30","취소","취소","연속"]
[8,"서울","성동","성동S/S 154kV #60 BUS","2020년 성동P/O 154kV GIS 정밀점검공사","성동S/S 성동군자#1T/L GIS 정밀점검 시험가압","2020-05-08 15:30","2020-05-08 17:30","2020-05-08 15:30","2020-05-08 17:30","연속"]
[9,"서울","성동","쌍문미아#1 T/L","154kV 수유분기 지중T/L 건설공사","- 구간 : 수유S/S~쌍문미아T/L 분기점 - 선종/회선수 : XLPE 1200SQ/ 2회선-0.3km","2020-05-11 09:00","2020-06-27 18:00","취소","취소","연속"]
[10,"서울","성동","왕십리용두 T/L","2020년 성동P/O 154kV GIS 정밀점검공사","왕십리S/S 왕십리용두T/L GIS 정밀점검","2020-05-13 09:30","2020-05-15 17:30","2020-05-25 09:30","2020-05-26 17:30","연속"]
[11,"서울","중부","수색상암#2 T/L","원흥수색-수색상암#2TL 직결공사","원흥수색-수색상암#2TL 직결공사","2020-05-01 08:00","2020-06-05 18:00","2020-05-08 08:00","2020-06-21 18:00","연속"]
[12,"서울","중부","수색S/S 154kV #65 BUS","원흥수색-수색상암#2TL 직결공사","원흥수색-수색상암#2TL 직결공사","2020-05-03 08:00","2020-05-03 18:00","2020-05-10 08:00","2020-05-10 18:00","연속"]
[13,"서울","중부","수색S/S 154kV #60 BUS","원흥수색-수색상암#2TL 직결공사","원흥수색-수색상암#2TL 직결공사","2020-05-16 08:00","2020-05-16 13:00","2020-05-16 08:00","2020-05-16 13:00","연속"]
[14,"서울","중부","원흥수색#1 T/L","원흥수색-수색상암#2TL 직결공사","원흥수색-수색상암#2TL 직결공사","2020-05-16 08:00","2020-05-24 18:00","2020-05-16 08:00","2020-05-24 18:00","연속"]
[15,"서울","중부","수색S/S 154kV #65 BUS","원흥수색-수색상암#2TL 직결공사","원흥수색-수색상암#2TL 직결공사","2020-05-16 13:00","2020-05-16 18:00","2020-05-16 13:00","2020-05-16 18:00","연속"]
[16,"서울","중부","수색S/S 154kV #60 BUS","원흥수색-수색상암#2TL 직결공사","원흥수색-수색상암#2TL 직결공사","2020-05-23 08:00","2020-05-23 18:00","2020-05-23 08:00","2020-05-23 18:00","연속"]
[17,"서울","중부","수색S/S 154kV #65 BUS","원흥수색-수색상암#2TL 직결공사","원흥수색-수색상암#2TL 직결공사","2020-05-24 08:00","2020-05-24 18:00","2020-05-24 08:00","2020-05-24 18:00","연속"]
[18,"서울","중부","원흥수색#2 T/L","원흥수색-수색상암#2TL 직결공사","원흥수색-수색상암#2TL 직결공사","2020-05-27 08:00","2020-06-05 18:00","2020-05-27 08:00","2020-06-21 18:00","연속"]
[19,"서울","중부","수색S/S 154kV #60 BUS","원흥수색-수색상암#2TL 직결공사","원흥수색-수색상암#2TL 직결공사","2020-05-30 08:00","2020-05-30 13:00","2020-05-30 08:00","2020-05-30 13:00","연속"]
[20,"서울","중부","수색S/S 154kV #60 BUS","원흥수색-수색상암#2TL 직결공사","원흥수색-수색상암#2TL 직결공사","2020-05-02 08:00","2020-05-02 18:00","2020-05-09 08:00","2020-05-09 18:00","연속"]
[21,"서울","직할","지축서대문#2 T/L","154kV 현저분기 지중T/L 건설공사","○선종 및 규격 : 154kV XLPE 2,000㎟ ○회선수 및 길이 : 4회선, 0.462km ○케이블포설 : 2구간, 철거 2구간(OF케이블 1구간, XLPE케이블 1구간) ○케이블접속 : 8개소(종단접속 4개소, 중간접속 4개소) ○기타사항 - 현저변전소 최초가압 사용전검사(변전) : 3일 소요","2020-05-06 09:30","2020-06-19 18:00","2020-05-06 09:30","2020-06-19 18:00","연속"]
[22,"서울","직할","원남미아#2 T/L","20년 직할 변전협력 총액공사","GIS 조작시험","2020-05-04 10:00","2020-05-04 18:00","2020-05-04 10:00","2020-05-04 18:00","연속"]
[23,"남서울","강남","논일S/S 154kV #60 BUS","154kV 논일S/S #3M.Tr용 GIS 설치공사","신규모선 상확인 및 초기가압","2020-05-11 15:00","2020-05-12 18:00","2020-05-09 15:00","2020-05-10 18:00","연속"]
[24,"남서울","강남","신사논일#1 T/L","154kV 논일S/S #3M.Tr용 GIS 설치공사","연동시험 및 무부하가압","2020-05-11 14:00","2020-05-12 18:00","2020-05-11 14:00","2020-05-12 18:00","연속"]
[25,"남서울","강남","논일S/S 154kV #65 BUS","154kV 논일S/S #3M.Tr용 GIS 설치공사","신규모선 상확인 및 초기가압","2020-05-11 09:00","2020-05-11 15:00","2020-05-09 09:00","2020-05-09 15:00","연속"]
[26,"남서울","동서울","유통단지#2 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2020-05-19 09:00","2020-05-19 18:00","2020-05-19 09:00","2020-05-19 18:00","연속"]
[27,"남서울","동서울","유통단지#1 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2020-05-18 09:00","2020-05-18 18:00","2020-05-18 09:00","2020-05-18 18:00","연속"]
[28,"남서울","동서울","강남대치#2 T/L","170kV GIS 경보회로 로직변경","170kV GIS 경보회로 로직변경","2020-05-06 14:00","2020-05-06 18:00","2020-05-06 14:00","2020-05-06 18:00","연속"]
[29,"남서울","동서울","강남대치#1 T/L","170kV GIS 경보회로 로직변경","170kV GIS 경보회로 로직변경","2020-05-06 09:00","2020-05-06 14:00","2020-05-06 09:00","2020-05-06 14:00","연속"]
[30,"남서울","동서울","강동상일#2 T/L","170kV GIS 보통점검 및 전자변교체","170kV GIS 보통점검 및 전자변교체","2020-05-22 09:00","2020-05-22 18:00","2020-05-21 14:00","2020-05-21 18:00","연속"]
[31,"남서울","동서울","강동상일#1 T/L","170kV GIS 보통점검 및 전자변교체","170kV GIS 보통점검 및 전자변교체","2020-05-21 09:00","2020-05-21 18:00","2020-05-21 09:00","2020-05-21 14:00","연속"]
[32,"남서울","동서울","동서울S/S 154kV #60-#61 SEC CB","170kV GCB 보통점검","170kV GCB 보통점검","2020-05-26 09:00","2020-05-26 18:00","2020-05-26 09:00","2020-05-26 18:00","연속"]
[33,"남서울","동서울","동서울S/S 154kV #61-#62 SEC CB","170kV GCB 보통점검","170kV GCB 보통점검","2020-05-25 09:00","2020-05-25 18:00","2020-05-25 09:00","2020-05-25 18:00","연속"]
[34,"남서울","동서울","동서울S/S 154kV #60-#65 BUS TIE CB","170kV GCB 보통점검","170kV GCB 보통점검","2020-05-21 09:00","2020-05-21 18:00","2020-05-21 09:00","2020-05-21 18:00","연속"]
[35,"남서울","동서울","동서울S/S 154kV #65-#66 SEC CB","170kV GCB 보통점검","170kV GCB 보통점검","2020-05-28 09:00","2020-05-28 18:00","2020-05-28 09:00","2020-05-28 18:00","연속"]
[36,"남서울","동서울","동서울S/S 154kV #66-#67 SEC CB","170kV GCB 보통점검","170kV GCB 보통점검","2020-05-29 09:00","2020-05-29 18:00","2020-05-29 09:00","2020-05-29 18:00","연속"]
[37,"남서울","동서울","동서울S/S 154kV #62-#67 BUS TIE CB","170kV GCB 보통점검","170kV GCB 보통점검","2020-05-22 09:00","2020-05-22 18:00","2020-05-22 09:00","2020-05-22 18:00","연속"]
[38,"남서울","동서울","논현선릉#1 T/L","세니온 보호배전반 성능개선","170kV GIS 보통점검 보호배전반 성능개선","2020-05-20 10:00","2020-05-20 18:00","2020-05-20 10:00","2020-05-20 18:00","연속"]
[39,"남서울","동서울","동서울송파#1 T/L","170kV GIS 정밀점검","송파S/S 170kV GIS 정밀점검","2020-05-25 09:00","2020-05-27 14:00","2020-05-25 09:00","2020-05-27 14:00","연속"]
[40,"남서울","동서울","동서울송파#2 T/L","170kV GIS 정밀점검","송파S/S 170kV GIS 정밀점검","2020-05-27 14:00","2020-05-29 18:00","2020-05-27 14:00","2020-05-29 18:00","연속"]
[41,"남서울","동서울","수서S/S 154kV #1 BUS TIE CB","170kV GIS 보통점검","170kV GIS 보통점검","2020-05-20 09:00","2020-05-20 18:00","2020-05-20 09:00","2020-05-20 18:00","연속"]
[42,"남서울","영등포","가양등촌#1 T/L","가양S/S 170kV GIS 조작시험(가양-등촌#1,2T/L)","- 차단기 동작시험 - GIS 조작시험","2020-05-27 09:00","2020-05-27 14:00","2020-05-04 09:00","2020-05-04 14:00","연속"]
[43,"남서울","영등포","가양등촌#1 T/L","154kV 가양S/S 인출전력구 케이블 선종교체공사","가양S/S 인출전력구 케이블 선종교체공사(2회선 0.31km)","2020-05-11 09:00","2020-07-21 18:00","취소","취소","연속"]
[44,"남서울","영등포","가양등촌#2 T/L","154kV 가양S/S 인출전력구 케이블 선종교체공사","가양S/S 인출전력구 케이블 선종교체공사(2회선 0.31km)","2020-05-11 09:00","2020-07-21 18:00","취소","취소","연속"]
[45,"남서울","영등포","마곡가양#1 T/L","가양S/S 170kV GIS 보통점검(마곡-가양#1T/L)","- 차단기 개폐타임 측정 - GIS 조작시험 - SF6가스 수분 및 SO2 측정 - 코일저항, 절연저항 측정 - 주도체저항 측정","2020-05-18 09:00","2020-05-18 18:00","취소","취소","연속"]
[46,"남서울","영등포","가양등촌#2 T/L","가양S/S 170kV GIS 조작시험(가양-등촌#1,2T/L)","- 차단기 동작시험 - GIS 조작시험","2020-05-27 14:00","2020-05-27 18:00","2020-05-04 14:00","2020-05-04 18:00","연속"]
[47,"남서울","영등포","가양등촌#1 T/L","154kV 가양-등촌T/L 일부구간 지장 이설공사","○ 지중송전 : 154kV OF 1200 x 2C x 0.320km 신설 및 철거 ○ 비금속광케이블(OFC) 신설 및 철거 ○ 관로 320m 신설 및 철거(요청자 시행)","2020-05-25 09:00","2020-07-01 18:00","취소","취소","연속"]
[48,"남서울","영등포","마곡가양#2 T/L","가양S/S 170kV GIS 보통점검(마곡-가양#2T/L)","- 차단기 개폐타임 측정 - GIS 조작시험 - SF6 가스 수분 및 SO2 측정 - 코일저항, 절연저항 측정 - 주도체저항 측정","2020-05-19 09:00","2020-05-19 18:00","취소","취소","연속"]
[49,"남서울","영등포","신정목동#2 T/L","목동S/S 170kV GIS 조작시험(신정-목동#1,2TL)","- 차단기 개폐타임 측정 - GIS 조작시험","2020-05-08 14:00","2020-05-08 18:00","2020-05-11 14:00","2020-05-11 18:00","연속"]
[50,"남서울","영등포","신정목동#1 T/L","목동S/S 170kV GIS 조작시험(신정-목동#1,2TL)","- 전자변 교체 - 차단기 개폐타임 측정 - GIS 조작시험","2020-05-08 09:00","2020-05-08 14:00","2020-05-11 09:00","2020-05-11 14:00","연속"]
[51,"남서울","영등포","양평양천#1 T/L","154kV양평-양천T/L선종교체공사","○ 구 간 : 양평S/S ∼양천S/S ○ 케이블 철거 : 154㎸ OF 1200㎟ × 1회선(D), 2.542㎞ ○ 주요공종 - 케이블 철거구간 : OF 1200㎟(D) × 10구간× 2C(2.54km) - 케이블 포설구간 : XLPE 1200㎟(D) × 5구간×2C(1.46km),","2020-05-25 09:00","2020-10-22 18:00","2020-05-25 09:00","2020-10-22 18:00","연속"]
[52,"남서울","영등포","천왕오류#1 T/L","천왕,오류S/S 천왕-구로#2T/L GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-05-25 15:00","2020-05-29 18:00","취소","취소","연속"]
[53,"남서울","영등포","천왕구로#2 T/L","천왕S/S 천왕-구로#2T/L GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-05-20 15:00","2020-05-22 18:00","2020-05-20 15:00","2020-05-22 18:00","연속"]
[54,"남서울","영등포","화곡S/S 154kV #60 BUS","154kV 화곡S/S 공항#2T/L GIS 정밀점검공사","- GIS(170kV 50kA 2000A) x 1CCT 정밀점검 - 기타부대공사","2020-05-16 09:00","2020-05-17 14:00","2020-05-01 08:00","2020-05-01 20:00","연속"]
[55,"남서울","영등포","고강화곡#1 T/L","화곡S/S 170kV GIS 조작시험(고강-화곡#1T/L)","- 차단기 동작시험 - GIS 조작시험","2020-05-20 09:00","2020-05-20 14:00","2020-05-20 09:00","2020-05-20 14:00","연속"]
[56,"남서울","영등포","고강화곡#2 T/L","화곡S/S 170kV GIS 조작시험(고강-화곡#2T/L)","- 차단기 동작시험 - GIS 조작시험","2020-05-20 14:00","2020-05-20 18:00","2020-05-20 14:00","2020-05-20 18:00","연속"]
[57,"남서울","영등포","화곡마곡#1 T/L","화곡S/S 170kV GIS 조작시험(화곡-마곡#1,2T/L)","- 차단기 동작시험 - GIS 조작시험","2020-05-22 09:00","2020-05-22 14:00","2020-05-01 18:00","2020-05-01 20:00","연속"]
[58,"남서울","영등포","화곡마곡#2 T/L","화곡S/S 170kV GIS 조작시험(화곡-마곡#1,2T/L)","- 차단기 동작시험 - GIS 조작시험","2020-05-22 14:00","2020-05-22 18:00","2020-05-05 18:00","2020-05-05 20:00","연속"]
[59,"남서울","영등포","화곡S/S 154kV #65 BUS","154kV 화곡S/S 공항#2T/L GIS 정밀점검공사","- GIS(170kV 50kA 2000A) x 1CCT 정밀점검 - 기타부대공사","2020-05-23 09:00","2020-05-24 14:00","2020-05-05 08:00","2020-05-05 20:00","연속"]
[60,"남서울","직할","대방신길#1 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2020-05-06 10:00","2020-05-06 14:00","2020-05-20 10:00","2020-05-20 14:00","연속"]
[61,"남서울","직할","봉천신길#2 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2020-05-19 14:00","2020-05-19 18:00","2020-05-14 14:00","2020-05-14 18:00","연속"]
[62,"남서울","직할","봉천신길#1 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2020-05-19 10:00","2020-05-19 14:00","2020-05-14 10:00","2020-05-14 14:00","연속"]
[63,"남서울","직할 ","신길S/S 154kV #60-#65 BUS TIE CB","주변압기 정밀점검 관련 계통 통합","신길S/S #1,2,3,4M.Tr 정밀점검 및 OLTC Diverter 교체 관련 계통 통합","2020-05-18 09:00","2020-06-08 18:00","2020-05-18 09:00","2020-06-08 18:00","연속"]
[64,"인천","김포","양촌양곡#1 T/L","154kV 왕길-양촌 등 4개 T/L PD진단용 센서 및 집합반 설치공사","○ UWB센서 설치 : 3상 ○ PD진단용 집합반 설치 : 양촌C/H","2020-05-18 09:00","2020-05-22 18:00","2020-05-18 09:00","2020-05-22 18:00","연속"]
[65,"인천","김포","양촌양곡#2 T/L","154kV 왕길-양촌 등 4개 T/L PD진단용 센서 및 집합반 설치공사","○ UWB센서 설치 :3상 ○ PD진단용 집합반 설치 양촌C/H","2020-05-25 09:00","2020-05-29 18:00","2020-05-25 09:00","2020-05-29 18:00","연속"]
[66,"인천","김포","김포장기#2 T/L","장기S/S 154kV 김포-장기#2T/L GIS 보통점검","장기S/S 154kV 김포-장기#2T/L GIS 보통점검","2020-05-12 10:00","2020-05-12 18:00","2020-05-12 10:00","2020-05-12 18:00","연속"]
[67,"인천","김포","김포장기#1 T/L","장기S/S 154kV 김포-장기#1T/L GIS 보통점검","장기S/S 154kV 김포-장기#1T/L GIS 보통점검","2020-05-11 10:00","2020-05-11 18:00","2020-05-11 10:00","2020-05-11 18:00","연속"]
[68,"인천","부평","주안관교#1 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2020-05-19 09:00","2020-05-21 18:00","2020-05-19 09:00","2020-05-21 18:00","연속"]
[69,"인천","부평","관교만수#2 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2020-05-28 09:00","2020-05-28 18:00","2020-05-28 09:00","2020-05-28 18:00","연속"]
[70,"인천","부평","관교만수#1 T/L","관교S/S 관교만수#1T/L GIS 보통점검","관교S/S 관교만수#1T/L GIS 보통점검","2020-05-11 09:00","2020-05-11 18:00","2020-05-11 09:00","2020-05-11 18:00","연속"]
[71,"인천","부평","인천남인천#1 T/L","변전소 인출구간 OF케이블 선종교체공사","1. 보강대상 : 154kV 옥내 GIS형 변전소 케이블처리실내 SJ(유지접속)설치개소 2. EBG ∼ J/B#1 케이블 선종교체(OF→XLPE), 편단급유 가능 대상 교체 시행","2020-05-27 09:00","2020-06-30 18:00","2020-05-27 09:00","2020-06-30 18:00","연속"]
[72,"인천","부평","주안만수#1 T/L","만수S/S 주안만수#1T/L GIS 보통점검","만수S/S 주안만수#1T/L GIS 보통점검","2020-05-20 09:00","2020-05-20 18:00","2020-05-20 09:00","2020-05-20 18:00","연속"]
[73,"인천","부평","신경서경서#2 T/L","신경서S/S 신경서경서#2 T/L 보호반 대체공사","신경서S/S 신경서경서#2 T/L 보호반 대체공사","2020-05-25 09:00","2020-05-29 18:00","2020-05-25 09:00","2020-05-29 18:00","연속"]
[74,"인천","부평","신경서경서#1 T/L","신경서S/S 신경서경서#1 T/L 보호반 대체공사","신경서S/S 신경서경서#1 T/L 보호반 대체공사","2020-05-18 09:00","2020-05-22 18:00","2020-05-18 09:00","2020-05-22 18:00","연속"]
[75,"인천","부평","신가좌신현#1 T/L","154kV신가좌-신현#1T/L 피뢰기 설치공사","154kV신가좌-신현#1T/L 피뢰기 설치공사","2020-05-01 09:00","2020-05-01 13:00","2020-05-01 09:00","2020-05-01 13:00","연속"]
[76,"인천","부평","인천CC북인천#2 T/L","인천복합S/Y 인천CC북인천#2T/L 보호배전반 대체공사","인천복합S/Y 인천CC북인천#2T/L 보호배전반 대체공사 - 북인천S/S 인천CC북인천#2T/L 보호배전반 대체공사(직할 병행) - 인천CC북인천#2T/L 170㎸ GIS 정밀점검(병행)","2020-05-04 09:00","2020-05-08 18:00","2020-05-04 09:00","2020-05-08 18:00","연속"]
[77,"인천","부평","신가좌주안#2 T/L","신가좌주안#2 T/L 보호계전기 성능개선 등","-㈜선도전기 송전선로 보호계전기 통신회로 loop시 오동작 방지 -병행지선 설치관련 선로정수 측정","2020-05-10 13:00","2020-05-10 16:00","2020-05-10 13:00","2020-05-10 16:00","연속"]
[78,"인천","부평","신가좌주안#1 T/L","신가좌주안#1 T/L 보호계전기 성능개선 등","-㈜선도전기 송전선로 보호계전기 통신회로 loop시 오동작 방지 -병행지선 설치관련 선로정수 측정","2020-05-10 09:00","2020-05-10 12:00","2020-05-10 09:00","2020-05-10 12:00","연속"]
[79,"인천","부평","주안만수#2 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2020-05-26 09:00","2020-05-27 18:00","2020-05-26 09:00","2020-05-27 18:00","연속"]
[80,"인천","시흥","신시흥도림#1 T/L","도림S/S 154kV 신시흥도림#1TL GIS초기점검","도림S/S 154kV 신시흥도림#1TL GIS초기점검","2020-05-21 10:00","2020-05-21 18:00","2020-05-21 10:00","2020-05-21 18:00","연속"]
[81,"인천","시흥","동시화서시화 T/L","동시화S/S 154kV 동시화서시화TL 보호반대체","동시화S/S 154kV 동시화서시화TL 보호반대체","2020-05-18 10:00","2020-05-22 18:00","2020-05-18 10:00","2020-05-22 18:00","연속"]
[82,"인천","시흥","북시화서시화#1 T/L","154kV 북시화-서시화#1T/L 구형 SVL 교체공사","154kV 북시화-서시화#1T/L 구형 SVL 교체공사","2020-05-13 09:00","2020-05-15 18:00","2020-05-13 09:00","2020-05-15 18:00","연속"]
[83,"인천","시흥","북시화서시화#2 T/L","154kV 북시화-서시화#2T/L 구형 SVL 교체공사","154kV 북시화-서시화#2T/L 구형 SVL 교체공사","2020-05-20 09:00","2020-05-22 18:00","2020-05-20 09:00","2020-05-22 18:00","연속"]
[84,"인천","시흥","북시화서시화#3 T/L","154kV 북시화-서시화#3T/L 구형 SVL 교체공사","154kV 북시화-서시화#3T/L 구형 SVL 교체공사","2020-05-27 09:00","2020-05-29 18:00","2020-05-27 09:00","2020-05-29 18:00","연속"]
[85,"인천","시흥","신시흥북시화#1 T/L","북시화S/S 154kV 신시흥북시화#1T/L PT누유보수","북시화S/S 154kV 신시흥북시화#1T/L PT누유보수","2020-05-04 10:00","2020-05-04 18:00","2020-05-04 10:00","2020-05-04 18:00","연속"]
[86,"인천","시흥","서안양소래 T/L","소래S/S 154kV 서안양소래TL GIS보통점검","소래S/S 154kV 서안양소래TL GIS보통점검","2020-05-08 10:00","2020-05-08 18:00","2020-05-08 10:00","2020-05-08 18:00","연속"]
[87,"인천","시흥","도림오봉#2 T/L","오봉S/S 154kV 도림오봉#2TL GIS보통점검","오봉S/S 154kV 도림오봉#2TL GIS보통점검","2020-05-15 10:00","2020-05-15 18:00","2020-05-15 10:00","2020-05-15 18:00","연속"]
[88,"인천","시흥","도림오봉#1 T/L","오봉S/S 154kV 도림오봉#1TL GIS보통점검","오봉S/S 154kV 도림오봉#1TL GIS보통점검","2020-05-14 10:00","2020-05-14 18:00","2020-05-14 10:00","2020-05-14 18:00","연속"]
[89,"인천","직할","임학계양#1 T/L","임학,계양S/S 임학-계양#1T/L 보호반 대체(양단)","임학,계양S/S 임학-계양#1T/L 보호반 대체(양단)","2020-05-11 09:30","2020-05-15 18:00","2020-05-11 09:30","2020-05-15 18:00","연속"]
[90,"인천","직할","신부평도당#2 T/L","154kV 갈산-도당 지중T/L 인출정비공사","○ 154kV XLPE 2,000㎟, 2C×0.4km(갈산-도당)설치 및 기설선로 철거","2020-05-25 10:00","2020-06-30 16:00","취소","취소","연속"]
[91,"인천","직할","신부평도당#1 T/L","154kV 갈산-도당 지중T/L 인출정비공사","○ 154kV XLPE 2,000㎟, 2C×0.4km(갈산-도당)설치 및 기설선로 철거","2020-05-25 10:00","2020-06-30 16:00","취소","취소","연속"]
[92,"인천","직할","신부평고강#2 T/L","154kV신부평-고강#2T/L 피뢰기 설치공사","154kV신부평-고강#2T/L 피뢰기 설치공사","2020-05-01 09:00","2020-05-01 15:00","취소","취소","연속"]
[93,"경기북부","고양","고양S/S 154kV #60 BUS","154kV 고양S/S #3M.Tr 증설 공사(170kV)","- 170kV 1CCT 설치(Main) - 기타 부대공사 1식","2020-05-19 09:00","2020-05-25 09:00","2020-05-19 09:00","2020-05-25 09:00","연속"]
[94,"경기북부","고양","양주고양#2 T/L","154kV 고양S/S #3M.Tr 증설 공사(170kV)","- 170kV 1CCT 설치(Main) - 기타 부대공사 1식","2020-05-23 18:00","2020-05-25 09:00","2020-05-23 18:00","2020-05-25 09:00","연속"]
[95,"경기북부","고양","고양S/S 154kV #65 BUS","154kV 고양S/S #3M.Tr 증설 공사(170kV)","- 170kV 1CCT 설치(Main) - 기타 부대공사 1식","2020-05-25 09:00","2020-05-29 18:00","2020-05-25 09:00","2020-05-29 18:00","연속"]
[96,"경기북부","고양","양주고양#2 T/L","154kV 고양S/S #3M.Tr 증설 공사(170kV)","- 170kV 1CCT 설치(Main) - 기타 부대공사 1식","2020-05-28 18:00","2020-05-29 18:00","2020-05-28 18:00","2020-05-29 18:00","연속"]
[97,"경기북부","고양","월롱금촌#2 T/L","154kV 월롱-금촌T/L 자기애관 교체공사","금촌C/H 자기애관 →폴리머애관 교체","2020-05-18 09:00","2020-05-22 18:00","2020-05-18 09:00","2020-05-22 18:00","연속"]
[98,"경기북부","고양","월롱금촌#1 T/L","154kV 월롱-금촌T/L 자기애관 교체공사","금촌C/H 자기애관 →폴리머애관 교체","2020-05-11 09:00","2020-05-15 18:00","2020-05-11 09:00","2020-05-15 18:00","연속"]
[99,"경기북부","고양","남면백석#2 T/L","345kV 신파주-양주 등 11개T/L 항공시설물 보강공사","ㅇ 항공시설물 보강공사","2020-05-25 07:00","2020-05-25 18:00","2020-05-25 07:00","2020-05-25 18:00","연속"]
[100,"경기북부","고양","능곡상암#2 T/L","170kV GIS 조작시험 - 총액","능곡S/S 능곡-상암#2T/L 조작시험","2020-05-07 10:00","2020-05-07 13:00","2020-05-07 10:00","2020-05-07 13:00","연속"]
[101,"경기북부","고양","능곡상암#1 T/L","170kV GIS 조작시험 - 총액","능곡S/S 능곡-상암#1T/L 조작시험","2020-05-06 10:00","2020-05-06 18:00","2020-05-06 10:00","2020-05-06 18:00","연속"]
[102,"경기북부","고양","신파주송포#1 T/L","154kV 신파주-송포#1T/L OF케이블 선종교체공사","송포EBG-#1S/J 구간 OF 2,000sq → XLPE 2,000sq 선종교체공사","2020-05-11 09:00","2020-06-19 18:00","2020-05-11 09:00","2020-06-19 18:00","연속"]
[103,"경기북부","고양","신파주문발#1 T/L","2020년 상반기 고양P/O 170kV GIS 정밀점검공사","2020년 상반기 고양P/O 170kV GIS 정밀점검공사(신파주-문발#1T/L)","2020-05-06 10:00","2020-05-07 18:00","2020-05-06 10:00","2020-05-07 18:00","연속"]
[104,"경기북부","고양","문산월롱#1 T/L","'19-'20년 지중송전설비 위탁정비공사","문산-월롱T/L 월롱C/H 케이블헤드 및 피뢰기 점검","2020-05-18 09:00","2020-05-20 18:00","2020-05-25 09:00","2020-05-27 18:00","연속"]
[105,"경기북부","고양","문산월롱#2 T/L","'19-'20년 지중송전설비 위탁정비공사","문산-월롱T/L 월롱C/H 케이블헤드 및 피뢰기 점검","2020-05-21 09:00","2020-05-22 18:00","2020-05-28 09:00","2020-05-29 18:00","연속"]
[106,"경기북부","고양","덕이호수#2 T/L","2020년 상반기 고양P/O 170kV GIS 정밀점검공사","2020년 상반기 고양P/O 170kV GIS 정밀점검공사(덕이-호수#2T/L)","2020-05-27 10:00","2020-05-28 18:00","2020-05-27 10:00","2020-05-28 18:00","연속"]
[107,"경기북부","고양","덕이호수#1 T/L","2020년 상반기 고양P/O 170kV GIS 정밀점검공사","2020년 상반기 고양P/O 170kV GIS 정밀점검공사(덕이-호수#1T/L)","2020-05-25 10:00","2020-05-26 18:00","2020-05-25 10:00","2020-05-26 18:00","연속"]
[108,"경기북부","구리","가평청평HP#1 T/L","2020년 가공송전 순시점검 위탁공사","154kV 가평-청평HPT/L 정밀점검","2020-05-25 08:00","2020-05-28 18:00","취소","취소","연속"]
[109,"경기북부","구리","덕소S/S 154KV #60-#65 BUS TIE GIS","`20~21년 구리전력 변전정비 총액공사","덕소S/S 154kV #1BUS-TIE GIS 초기점검","2020-05-14 09:00","2020-05-14 14:00","2020-05-14 09:00","2020-05-14 14:00","연속"]
[110,"경기북부","구리","덕소S/S 154KV #60-#61 SEC GIS","`20~21 구리전력 변전정비 총액공사","덕소S/S #60-61 SEC GIS 초기점검","2020-05-18 09:00","2020-05-18 14:00","2020-05-18 09:00","2020-05-18 14:00","연속"]
[111,"경기북부","구리","덕소S/S 154KV #61-#66 BUS TIE GIS","`20~21년 구리전력 변전정비 총액공사","덕소S/S 154kV #2BUS-TIE GIS 초기점검","2020-05-14 14:00","2020-05-14 18:00","2020-05-14 14:00","2020-05-14 18:00","연속"]
[112,"경기북부","구리","덕소S/S 154KV #65-#66 SEC GIS","`20~21 구리전력 변전정비 총액공사","덕소S/S #65-66 SEC GIS 초기점검","2020-05-18 14:00","2020-05-18 18:00","2020-05-18 14:00","2020-05-18 18:00","연속"]
[113,"경기북부","구리","신장덕소#1 T/L","2020년 가공송전 순시점검 위탁공사","154kV 신장-덕소 #1,2T/L 정밀점검","2020-05-07 08:00","2020-05-07 13:00","2020-05-21 08:00","2020-05-21 13:00","연속"]
[114,"경기북부","구리","신장덕소#2 T/L","2020년 가공송전 순시점검 위탁공사","154kV 신장-덕소 #1,2T/L 정밀점검","2020-05-07 13:00","2020-05-07 18:00","2020-05-21 13:00","2020-05-21 18:00","연속"]
[115,"경기북부","구리","미금덕소#1 T/L","미금S/S 170kV 장기사용 GIS대체공사(6차분)","- 미금덕소#1T/L 철거, 설치 - 미금구리#2T/L 철거, 설치","2020-05-18 08:00","2020-06-06 18:00","2020-05-18 08:00","2020-06-06 18:00","연속"]
[116,"경기북부","구리","미금구리#2 T/L","미금S/S 170kV 장기사용 GIS대체공사(6차분)","- 미금덕소#1T/L 철거, 설치 - 미금구리#2T/L 철거, 설치","2020-05-18 08:00","2020-06-06 18:00","2020-05-18 08:00","2020-06-06 18:00","연속"]
[117,"경기북부","구리","미금덕소#2 T/L","미금S/S 170kV 장기사용 GIS대체공사(5차분)-안전이격거리확보","- 6100 BUS TIE 철거, 설치 - 60BUS PT, 65BUS PT 철거, 설치 - 안전이격거리 확보 - 미금덕소#2T/L 시험가압(5.4~5), (5.8~9), (5.15~16)","2020-05-05 08:00","2020-05-08 18:00","2020-05-05 08:00","2020-05-08 18:00","매일"]
[118,"경기북부","구리","미금S/S 154kV #60 BUS","미금S/S 170kV 장기사용 GIS대체공사(5차분)","- 6100 BUS TIE 철거, 설치 - 60BUS PT, 65BUS PT 철거, 설치","2020-05-05 08:00","2020-05-09 08:00","2020-05-05 08:00","2020-05-09 08:00","연속"]
[119,"경기북부","구리","미금덕소#2 T/L","미금S/S 170kV 장기사용 GIS대체공사(5차분)-안전이격거리확보","- 6100 BUS TIE 철거, 설치 - 60BUS PT, 65BUS PT 철거, 설치 - 안전이격거리 확보 - 미금덕소#2T/L 시험가압(5.4~5), (5.8~9), (5.15~16)","2020-05-09 08:00","2020-05-15 17:00","2020-05-09 08:00","2020-05-15 17:00","매일"]
[120,"경기북부","구리","미금덕소#2 T/L","미금S/S 170kV 장기사용 GIS대체공사(5차분)-시험가압","- 6100 BUS TIE 철거, 설치 - 60BUS PT, 65BUS PT 철거, 설치 - 미금덕소#2T/L 시험가압(5.4~5), (5.9~10), (5.15~16)","2020-05-15 18:00","2020-05-16 18:00","2020-05-15 18:00","2020-05-16 18:00","연속"]
[121,"경기북부","구리","미금덕소#2 T/L","미금S/S 170kV 장기사용 GIS대체공사(5차분)-시험가압","- 6100 BUS TIE 철거, 설치 - 60BUS PT, 65BUS PT 철거, 설치 - 미금덕소#2T/L 시험가압(5.4~5), (5.9~10), (5.15~16)","2020-05-04 08:00","2020-05-05 08:00","2020-05-04 08:00","2020-05-05 08:00","연속"]
[122,"경기북부","구리","미금덕소#1 T/L","미금S/S 170kV 장기사용 GIS대체공사(5차분)-안전이격거리확보","- 6100 BUS TIE 철거, 설치 - 60BUS PT, 65BUS PT 철거, 설치 - 안전이격거리확보","2020-05-04 09:00","2020-05-15 18:00","2020-05-04 09:00","2020-05-15 18:00","매일"]
[123,"경기북부","구리","미금S/S 154kV #65 BUS","미금S/S 170kV 장기사용 GIS대체공사(5차분)","- 6100 BUS TIE 철거, 설치 - 60BUS PT, 65BUS PT 철거, 설치","2020-05-04 08:00","2020-05-05 08:00","2020-05-04 08:00","2020-05-05 08:00","연속"]
[124,"경기북부","구리","미금S/S 154kV #65 BUS","미금S/S 170kV 장기사용 GIS대체공사(6차분)","- 미금덕소#1T/L 철거, 설치 - 미금구리#2T/L 철거, 설치","2020-05-25 08:00","2020-06-06 18:00","2020-05-25 08:00","2020-06-06 18:00","연속"]
[125,"경기북부","구리","미금S/S 154kV #60-#65 BUS TIE CB","미금S/S 170kV 장기사용 GIS대체공사(5차분)","- 6100 BUS TIE 철거, 설치 - 60BUS PT, 65BUS PT 철거, 설치","2020-05-04 08:00","2020-05-16 18:00","2020-05-04 08:00","2020-05-16 18:00","연속"]
[126,"경기북부","구리","미금덕소#2 T/L","미금S/S 170kV 장기사용 GIS대체공사(5차분)-시험가압","- 6100 BUS TIE 철거, 설치 - 60BUS PT, 65BUS PT 철거, 설치 - 미금덕소#2T/L 시험가압(5.4~5), (5.8~9), (5.15~16)","2020-05-08 18:00","2020-05-09 08:00","2020-05-08 18:00","2020-05-09 08:00","연속"]
[127,"경기북부","구리","미금S/S 154kV #65 BUS","미금S/S 170kV 장기사용 GIS대체공사(5차분)","- 6100 BUS TIE 철거, 설치 - 60BUS PT, 65BUS PT 철거, 설치","2020-05-09 08:00","2020-05-16 18:00","2020-05-09 08:00","2020-05-16 18:00","연속"]
[128,"경기북부","구리","미금S/S 154kV #60 BUS","미금S/S 170kV 장기사용 GIS대체공사(6차분)","- 미금덕소#1T/L 철거, 설치 - 미금구리#2T/L 철거, 설치","2020-05-19 08:00","2020-05-25 08:00","2020-05-19 08:00","2020-05-25 08:00","연속"]
[129,"경기북부","구리","미금S/S 154kV #60 BUS","미금S/S 170kV 장기사용 GIS대체공사(5차분)","- 6100 BUS TIE 철거, 설치 - 60BUS PT, 65BUS PT 철거, 설치","2020-05-16 10:00","2020-05-16 15:00","2020-05-16 10:00","2020-05-16 15:00","연속"]
[130,"경기북부","구리","미금S/S 154kV #65 BUS","미금S/S 170kV 장기사용 GIS대체공사(6차분)","- 미금덕소#1T/L 철거, 설치 - 미금구리#2T/L 철거, 설치","2020-05-18 08:00","2020-05-19 08:00","2020-05-18 08:00","2020-05-19 08:00","연속"]
[131,"경기북부","구리","별내도봉 T/L","154kV 별내-도봉T/L 중간접속함 교체공사","일진전기제 리콜대상 조립식 중간접속함(PMJ) 교체 ○ 대상 : 154kV 별내-도봉T/L J/B#1~3 ○ 내용 : 고무슬리브 형태 변경 3개소(9상)","2020-05-18 08:00","2020-05-24 18:00","2020-05-18 08:00","2020-05-24 18:00","연속"]
[132,"경기북부","구리","동서울서종#1 T/L","2020년 가공송전 순시점검 위탁공사","154kV 신장-덕소 #1,2T/L 정밀점검 (병가철탑)","2020-05-07 13:00","2020-05-07 18:00","2020-05-21 13:00","2020-05-21 18:00","연속"]
[133,"경기북부","구리","동서울서종#2 T/L","2020년 가공송전 순시점검 위탁공사","154kV 신장-덕소 #1,2T/L 정밀점검 (병가철탑)","2020-05-07 08:00","2020-05-07 13:00","2020-05-21 08:00","2020-05-21 13:00","연속"]
[134,"경기북부","구리","운천철원#1 T/L","2020~2021년 직할 가공송전 정비회사 총액공사","압축인류크램프 및 점퍼선 교체","2020-05-25 08:00","2020-05-25 18:00","2020-05-26 08:00","2020-05-26 18:00","연속"]
[135,"경기북부","구리","청평H/P 154kV #3 M.TR 2차 CB","`20~21 구리전력 변전정비 총액공사","청평HP #3M.Tr 2차 CB 조작시험","2020-05-20 09:00","2020-05-20 18:00","2020-05-20 09:00","2020-05-20 18:00","연속"]
[136,"경기북부","직할","녹양백석#1 T/L","양주S/S GIS화관련 154kV 인출T/L 지중화공사","154kV 양주-녹양#2, 쌍문#1T/L 시험 가압","2020-05-23 09:00","2020-05-24 18:00","2020-05-23 09:00","2020-05-24 18:00","연속"]
[137,"경기북부","직할","도봉방학#1 T/L","20~21 직할 변전정비회사 총액공사","□ 도봉S/S 도봉-방학 #1 T/L GCB 개폐타임 측정","2020-05-25 09:00","2020-05-25 18:00","2020-05-25 09:00","2020-05-25 18:00","연속"]
[138,"경기북부","직할","백석덕계#1 T/L","2020~2021년 직할 가공송전 정비회사 총액공사","점퍼선교체","2020-05-12 08:00","2020-05-12 18:00","2020-05-26 08:00","2020-05-26 18:00","연속"]
[139,"경기북부","직할","옥정송우#2 T/L","154kV 신의정부-송우T/L No.49 안전이격거리확보공사","신의정부송우T/L No.49 안전이격확보공사를 위한 하단 병가회선 휴전","2020-05-11 08:00","2020-05-11 18:00","2020-05-11 08:00","2020-05-11 18:00","연속"]
[140,"경기북부","직할","옥정송우#1 T/L","154kV 신의정부-송우T/L No.49 안전이격거리확보공사","신의정부송우T/L No.49 안전이격확보공사를 위한 하단 병가회선 휴전","2020-05-13 08:00","2020-05-13 18:00","2020-05-13 08:00","2020-05-13 18:00","연속"]
[141,"경기북부","직할","옥정송우#2 T/L","154kV 신의정부-송우T/L No.49 안전이격거리확보공사","신의정부송우T/L No.49 안전이격확보공사를 위한 하단 병가회선 휴전","2020-05-16 08:00","2020-05-16 18:00","2020-05-16 08:00","2020-05-16 18:00","연속"]
[142,"경기북부","직할","신의정부송우#2 T/L","154kV 신의정부-송우T/L No.49 안전이격거리확보공사","신설 : 1기(No.49) 철거 :2기(No.49,No.49-1) 가철탑 1기 설치 및 철거","2020-05-11 08:00","2020-05-12 18:00","2020-05-11 08:00","2020-05-12 18:00","연속"]
[143,"경기북부","직할","신의정부송우#1 T/L","154kV 신의정부-송우T/L No.49 안전이격거리확보공사","신설 : 1기(No.49) 철거 :2기(No.49,No.49-1) 가철탑 1기 설치 및 철거","2020-05-13 08:00","2020-05-15 18:00","2020-05-13 08:00","2020-05-15 18:00","연속"]
[144,"경기북부","직할","신의정부송우#2 T/L","154kV 신의정부-송우T/L No.49 안전이격거리확보공사","신설 : 1기(No.49) 철거 :2기(No.49,No.49-1) 가철탑 1기 설치 및 철거","2020-05-16 08:00","2020-05-17 18:00","2020-05-16 08:00","2020-05-17 18:00","연속"]
[145,"경기북부","직할","신의정부S/S 154kV #61 BUS","신의정부S/S DS부 발청 하자보수공사","신의정부S/S 345kV #4 M.Tr 2차 GIS 모선 DS부 발청제거","2020-05-26 09:00","2020-05-27 18:00","취소","취소","연속"]
[146,"경기북부","직할","신의정부S/S 154kV #66 BUS","신의정부S/S DS부 발청 하자보수공사","신의정부S/S 345kV #4 M.Tr 2차 GIS 모선 DS부 발청제거","2020-05-28 09:00","2020-05-29 18:00","취소","취소","연속"]
[147,"경기북부","직할","양주쌍문#2 T/L","양주S/S GIS화관련 154kV 인출T/L 지중화공사","○ 대상 : 154kV 양주-쌍문#2T/L ○ 내용 : 신설EBA~신설EBG 구간 케이블 접속","2020-05-26 08:00","2020-06-14 18:00","2020-05-26 08:00","2020-06-14 18:00","연속"]
[148,"경기북부","직할","양주녹양#1 T/L","양주S/S GIS화관련 154kV 인출T/L 지중화공사","○ 대상 : 154kV 양주-녹양#1T/L ○ 내용 : 신설EBA~신설EBG 구간 케이블 접속","2020-05-25 08:00","2020-06-14 18:00","2020-05-25 08:00","2020-06-14 18:00","연속"]
[149,"경기북부","직할","양주쌍문#1 T/L","양주S/S GIS화관련 154kV 인출T/L 지중화공사","○ 대상 : 154kV 양주-쌍문#1T/L ○ 내용 : 신설EBA~신설EBG 구간 케이블 접속","2020-05-05 08:00","2020-05-24 18:00","2020-05-05 08:00","2020-05-24 18:00","연속"]
[150,"경기북부","직할","양주녹양#2 T/L","양주S/S GIS화관련 154kV 인출T/L 지중화공사","○ 대상 : 154kV 양주-녹양#2T/L ○ 내용 : 신설EBA~신설EBG 구간 케이블 접속","2020-05-04 08:00","2020-05-24 18:00","2020-05-04 08:00","2020-05-24 18:00","연속"]
[151,"경기북부","직할","옥정동두천#1 T/L","20년 직할 170kV GIS 정밀점검","- 옥정S/S 옥정-동두천 #1 T/L GIS 정밀점검 - 동두천S/S 옥정-동두천 #1 T/L GIS 정밀점검","2020-05-04 09:00","2020-05-08 18:00","2020-05-04 09:00","2020-05-08 18:00","연속"]
[152,"경기북부","직할","옥정동두천#2 T/L","20년 직할 170kV GIS 정밀점검","- 옥정S/S 옥정-동두천 #2 T/L GIS 정밀점검 - 동두천S/S 옥정-동두천 #2 T/L GIS 정밀점검","2020-05-18 09:00","2020-05-22 18:00","2020-05-18 09:00","2020-05-22 18:00","연속"]
[153,"경기북부","직할","별내진접 T/L","`20~21 구리전력 변전정비 총액공사","진접S/S 별내-진접T/L GIS 조작시험","2020-05-28 09:00","2020-05-28 14:00","2020-05-28 09:00","2020-05-28 14:00","연속"]
[154,"경기","직할","남수원발안#1 T/L","154kV 남수원-발안T/L OPGW 증설공사","154kV 남수원-발안T/L OPGW 증설공사","2020-05-20 08:00","2020-05-29 18::00","2020-05-20 08:00","2020-05-29 18::00","연속"]
[155,"경기","직할","남수원발안#2 T/L","154kV 남수원-발안T/L OPGW 증설공사","154kV 남수원-발안T/L OPGW 증설공사","2020-05-30 08:00","2020-05-31 18:00","2020-05-30 08:00","2020-05-31 18:00","연속"]
[156,"경기","직할","발안향남#2 T/L","154kV 남수원-발안T/L OPGW 증설공사","154kV 남수원-발안T/L OPGW 증설공사","2020-05-30 08:00","2020-05-31 18:00","2020-05-30 08:00","2020-05-31 18:00","연속"]
[157,"경기","직할","관양평촌#1 T/L","2019년 평촌S/S 23kV 장기사용 GIS 대체공사 ","SA 혼용반 케이블 이설 공사 ","2020-05-06 09:00","2020-05-06 18:00","2020-05-06 09:00","2020-05-06 18:00","연속"]
[158,"경기","군포","마도사강#1 T/L","마도S/S 마도-사강#1T/L GIS 하자점검, 사강S/S 조작시험","마도S/S 마도-사강#1T/L GIS 하자점검, 사강S/S 마도-사강#1T/L GIS조작시험","2020-05-20 09:00","2020-05-20 14:00","2020-05-20 09:00","2020-05-20 14:00","연속"]
[159,"경기","군포","마도사강#2 T/L","마도S/S 마도-사강#2T/L GIS 하자점검, 사강S/S 조작시험","마도S/S 마도-사강#2T/L GIS 하자점검, 사강S/S 마도-사강#2T/L GIS 조작시험","2020-05-20 14:00","2020-05-20 18:00","2020-05-20 14:00","2020-05-20 18:00","연속"]
[160,"경기","군포","서서울#2서안양 T/L","154kV 서안양S/S #4M.Tr 증설공사","#4M.Tr 1차 인출 GIB 및 #4M.Tr 시험가압","2020-05-26 18:00","2020-05-27 18:00","2020-05-26 18:00","2020-05-27 18:00","연속"]
[161,"경기","군포","서서울#2서안양 T/L","20년 군포PO 170kV GIS 정밀점검-서안양SS 서서울2서안양TL","서안양SS 서서울2서안양TL GIS 정밀점검공사","2020-05-21 09:00","2020-05-23 18:00","2020-05-21 09:00","2020-05-23 18:00","연속"]
[162,"경기","군포","서서울#2일동#1 T/L","2020-2021년도 송전정비회사 총액공사","154kV 일동-원곡#1T/L 휴전작업 관련 안전이격거리확보","2020-05-16 08:00","2020-05-16 12:00","2020-05-16 08:00","2020-05-16 12:00","연속"]
[163,"경기","군포","화성장덕 T/L","2020년 군포PO 170kV GIS 정밀점검공사-장덕SS 화성장덕TL","장덕SS 화성장덕TL GIS 정밀점검공사","2020-05-01 09:00","2020-05-03 18:00","2020-05-01 09:00","2020-05-03 18:00","연속"]
[164,"경기","군포","장덕마도 T/L","2020년 군포PO 170kV GIS 정밀점검공사-장덕SS 6100","장덕SS 6100 GIS 정밀점검공사 무부하가압용","2020-05-07 09:00","2020-05-08 18:00","2020-05-07 09:00","2020-05-08 18:00","연속"]
[165,"경기","군포","장덕마도 T/L","2020년 군포PO 170kV GIS 정밀점검공사-장덕SS 6100","장덕SS 6100 GIS 정밀점검공사 무부하가압용","2020-05-07 09:00","2020-05-08 18:00","취소","취소","연속"]
[166,"경기","군포","화성장덕 T/L","2020년 군포PO 170kV GIS 정밀점검공사-장덕SS 화성장덕TL","장덕SS 화성장덕TL GIS 정밀점검공사","2020-05-01 09:00","2020-05-03 18:00","취소","취소","연속"]
[167,"경기","동부","곤지암초월#1 T/L","20년 동부 변전정비회사 총액공사","곤지암:곤지암-초월#1T/L GIS(보통), 43L/R 회로보완 확인 및 Remote 회로분리 시행 초월:곤지암-초월#1T/L GIS(조작), GIS전자변교체,전자변 실리콘히터 설치, 43L/R 회로보완 확인 및 Remote 회로분리 시행","2020-05-04 09:30","2020-05-04 18:00","2020-05-04 09:30","2020-05-04 18:00","연속"]
[168,"경기","동부","곤지암율현#1 T/L","154kV 곤지암-율현#1T/L 불량애자교체","불량애자 교체작업(6호)","2020-05-09 08:00","2020-05-09 11:00","2020-05-09 08:00","2020-05-09 11:00","연속"]
[169,"경기","동부","곤지암이천#1 T/L","154kV 곤지암-율현#1T/L 불량애자교체(안전상 휴전)","불량애자 교체작업(6호)(안전상 휴전)","2020-05-09 08:00","2020-05-09 11:00","2020-05-09 08:00","2020-05-09 11:00","연속"]
[170,"경기","동부","곤지암이천#2 T/L","154kV 곤지암-율현#2T/L 불량애자교체,피뢰기 설치(안전상 휴전)","불량애자 교체작업(6호)(안전상 휴전) 피뢰기 설치작업(1~5호)(안전상 휴전)","2020-05-09 11:00","2020-05-09 19:00","2020-05-09 11:00","2020-05-09 19:00","연속"]
[171,"경기","동부","곤지암이천#2 T/L","154kV 곤지암-율현#2T/L 피뢰기 설치(안전상 휴전)","피뢰기 설치작업(1~5호)(안전상 휴전)","2020-05-10 08:00","2020-05-10 12:00","2020-05-10 08:00","2020-05-10 12:00","연속"]
[172,"경기","동부","곤지암율현#2 T/L","154kV 곤지암-율현#2T/L 불량애자교체 및 피뢰기 설치","불량애자 교체작업(6호) 피뢰기 설치작업(1~5호)","2020-05-09 11:00","2020-05-09 19:00","2020-05-09 11:00","2020-05-09 19:00","연속"]
[173,"경기","동부","곤지암율현#2 T/L","154kV 곤지암-율현#2T/L 피뢰기 설치","피뢰기 설치작업(1~5호)","2020-05-10 08:00","2020-05-10 12:00","2020-05-10 08:00","2020-05-10 12:00","연속"]
[174,"경기","동부","곤지암이천#2 T/L","154kV 곤지암-이천#2T/L 피뢰기 설치","피뢰기 설치작업(1~5호)","2020-05-10 12:00","2020-05-10 19:00","2020-05-10 12:00","2020-05-10 19:00","연속"]
[175,"경기","동부","곤지암율현#2 T/L","154kV 곤지암-이천#2T/L 피뢰기 설치(안전상 휴전)","피뢰기 설치작업(1~5호)(안전상 휴전)","2020-05-10 12:00","2020-05-10 19:00","2020-05-10 12:00","2020-05-10 19:00","연속"]
[176,"경기","동부","곤지암초월#1 T/L","20년 동부 변전정비회사 총액공사","곤지암:곤지암-초월#1T/L GIS(보통), 43L/R 회로보완 확인 및 Remote 회로분리 시행 초월:곤지암-초월#1T/L GIS(조작), GIS전자변교체,전자변 실리콘히터 설치, 43L/R 회로보완 확인 및 Remote 회로분리 시행","2020-05-04 09:30","2020-05-04 18:00","취소","취소","연속"]
[177,"경기","동부","곤지암율현#1 T/L","154kV 곤지암-율현#1T/L 불량애자교체","불량애자 교체작업(6호)","2020-05-09 08:00","2020-05-09 11:00","취소","취소","연속"]
[178,"경기","동부","곤지암이천#1 T/L","154kV 곤지암-율현#1T/L 불량애자교체(안전상 휴전)","불량애자 교체작업(6호)(안전상 휴전)","2020-05-09 08:00","2020-05-09 11:00","취소","취소","연속"]
[179,"경기","동부","곤지암이천#2 T/L","154kV 곤지암-율현#2T/L 불량애자교체,피뢰기 설치(안전상 휴전)","불량애자 교체작업(6호)(안전상 휴전) 피뢰기 설치작업(1~5호)(안전상 휴전)","2020-05-09 11:00","2020-05-09 19:00","취소","취소","연속"]
[180,"경기","동부","곤지암율현#2 T/L","154kV 곤지암-이천#2T/L 피뢰기 설치(안전상 휴전)","피뢰기 설치작업(1~5호)(안전상 휴전)","2020-05-10 12:00","2020-05-10 19:00","취소","취소","연속"]
[181,"경기","동부","곤지암이천#2 T/L","154kV 곤지암-이천#2T/L 피뢰기 설치","피뢰기 설치작업(1~5호)","2020-05-10 12:00","2020-05-10 19:00","취소","취소","연속"]
[182,"경기","동부","곤지암율현#2 T/L","154kV 곤지암-율현#2T/L 피뢰기 설치","피뢰기 설치작업(1~5호)","2020-05-10 08:00","2020-05-10 12:00","취소","취소","연속"]
[183,"경기","동부","곤지암이천#2 T/L","154kV 곤지암-율현#2T/L 피뢰기 설치(안전상 휴전)","피뢰기 설치작업(1~5호)(안전상 휴전)","2020-05-10 08:00","2020-05-10 12:00","취소","취소","연속"]
[184,"경기","동부","곤지암율현#2 T/L","154kV 곤지암-율현#2T/L 불량애자교체 및 피뢰기 설치","불량애자 교체작업(6호) 피뢰기 설치작업(1~5호)","2020-05-09 11:00","2020-05-09 19:00","취소","취소","연속"]
[185,"경기","동부","모현용인#1 T/L","154kV 모현S/S SW 신규수용공사","○ 170kV GIS(50kA, 2000A) × 1CCT 설치- 무부하가압","2020-05-14 09:00","2020-05-15 18:00","2020-05-14 09:00","2020-05-15 18:00","연속"]
[186,"경기","동부","모현용인#1 T/L","154kV 모현S/S SW 신규수용공사","○ 170kV GIS(50kA, 2000A) × 1CCT 설치- 무부하가압","2020-05-21 09:00","2020-05-22 18:00","2020-05-21 09:00","2020-05-22 18:00","연속"]
[187,"경기","동부","모현용인#1 T/L","154kV 모현S/S SW 신규수용공사","○ 170kV GIS(50kA, 2000A) × 1CCT 설치- 무부하가압","2020-05-14 09:00","2020-05-15 18:00","취소","취소","연속"]
[188,"경기","동부","성현분당#1 T/L","20년 동부 변전정비회사 총액공사","성현:성현-분당#1T/L(조작),GIS전자변교체,43L/R 회로보완 확인 및 Remote 회로분리 시행, LA(초기) 성현-분당#2T/L(조작),GIS전자변교체,43L/R 회로보완 확인 및 Remote 회로분리 시행","2020-05-20 09:30","2020-05-20 14:00","2020-05-20 09:30","2020-05-20 14:00","연속"]
[189,"경기","동부","성현분당#2 T/L","20년 동부 변전정비회사 총액공사","성현:성현-분당#1T/L(조작),GIS전자변교체,43L/R 회로보완 확인 및 Remote 회로분리 시행, LA(초기) 성현-분당#2T/L(조작),GIS전자변교체,43L/R 회로보완 확인 및 Remote 회로분리 시행","2020-05-20 14:00","2020-05-20 18:00","2020-05-20 14:00","2020-05-20 18:00","연속"]
[190,"경기","동부","곤지암이천#1 T/L","20년 동부 변전정비회사 총액공사","이천:곤지암-이천#1T/L(보통), 43L/R 회로보완 확인 및 Remote 회로분리 시행, LA(초기)","2020-05-07 09:30","2020-05-07 18:00","취소","취소","연속"]
[191,"경기","동부","곤지암이천#1 T/L","20년 동부 변전정비회사 총액공사","이천:곤지암-이천#1T/L(보통), 43L/R 회로보완 확인 및 Remote 회로분리 시행, LA(초기)","2020-05-07 09:30","2020-05-07 18:00","취소","취소","연속"]
[192,"경기","동부","초월성현#1 T/L","154kV 초월-성현#1T/L 송전선로 정밀점검","송전선로 정밀점검 - 1~59호 전구간","2020-05-25 08:00","2020-05-29 18:00","2020-05-25 08:00","2020-05-29 18:00","매일"]
[193,"경기","동부","곤지암초월#1 T/L","154kV 초월-성현#1T/L 송전선로 정밀점검(안전상 휴전)","송전선로 정밀점검 - 1~59호 전구간","2020-05-27 08:00","2020-05-29 18:00","2020-05-27 08:00","2020-05-29 18:00","매일"]
[194,"경기","성남","신수원S/S 154kV #61-#62 SEC GIS","20년 성남전력 154kV GIS 정밀점검","신수원S/S 154kV #61-62 SEC GIS 정밀점검","2020-05-11 09:00","2020-05-13 14:00","2020-05-11 09:00","2020-05-13 14:00","연속"]
[195,"경기","성남","신수원S/S 154kV #61 BUS","20년 성남전력 154kV GIS 정밀점검","신수원S/S 154kV #61-62 SEC GIS 무부하","2020-05-13 09:00","2020-05-13 14:00","2020-05-13 09:00","2020-05-13 14:00","연속"]
[196,"경기","성남","신수원S/S 154kV #61 BUS","20년 성남전력 154kV GIS 정밀점검","신수원S/S 154kV #61-62 SEC GIS 무부하","2020-05-13 09:00","2020-05-13 14:00","취소","취소","연속"]
[197,"경기","성남","신수원S/S 154kV #66 BUS","20년 성남전력 154kV GIS 정밀점검","신수원S/S 154kV #66-67 SEC GIS 무부하","2020-05-15 09:00","2020-05-15 18:00","2020-05-15 09:00","2020-05-15 18:00","연속"]
[198,"경기","성남","신수원S/S 154kV #66-#67 SEC GIS","20년 성남전력 154kV GIS 정밀점검","신수원S/S 154kV #66-67 SEC GIS 정밀점검","2020-05-13 14:00","2020-05-15 18:00","2020-05-13 14:00","2020-05-15 18:00","연속"]
[199,"경기","성남","신용인기흥#2 T/L","20년 성남전력 변전정비회사 총액공사","신용인S/S 기흥#2T/L 조작시험 양단 T/L보호반 교체","2020-05-11 09:00","2020-05-15 18:00","2020-05-11 09:00","2020-05-15 18:00","연속"]
[200,"경기","성남","모현용인#2 T/L","2020-21 가공송전정비 총액공사(애자련 교체)","154kV 모현-용인#2T/L 성능저하 국산애자 교체 - 용인S/S,42,48(3기)","2020-05-13 07:00","2020-05-13 18:00","2020-05-13 07:00","2020-05-13 18:00","연속"]
[201,"경기","성남","오천용인#1 T/L","2020-21 가공송전정비 총액공사(애자련 교체)","154kV 용인-오천#1T/L 성능저하 국산애자 교체 - 용인S/S,No.74(2기)","2020-05-18 07:00","2020-05-18 18:00","2020-05-18 07:00","2020-05-18 18:00","연속"]
[202,"경기","성남","모현용인#2 T/L","2020-21 가공송전정비 총액공사(애자련 교체)","154kV 모현-용인#2T/L 성능저하 국산애자 교체 - 용인S/S,42,48(3기)","2020-05-13 07:00","2020-05-13 18:00","취소","취소","연속"]
[203,"경기","성남","모현용인#1 T/L","2020-21 가공송전정비 총액공사(애자련 교체)","154kV 모현-용인#1T/L 성능저하 국산애자 교체 - 용인S/S,41,43,48,50(5기)","2020-05-11 07:00","2020-05-12 18:00","2020-05-11 07:00","2020-05-12 18:00","매일"]
[204,"경기","성남","모현용인#1 T/L","2020-21 가공송전정비 총액공사(애자련 교체)","154kV 모현-용인#1T/L 성능저하 국산애자 교체 - 용인S/S,41,43,48,50(5기)","2020-05-11 07:00","2020-05-12 18:00","취소","취소","매일"]
[205,"경기","직할","과천동안양#1 T/L","154kV 동안양S/S 옥내화 공사","ㅇ 과천-동안양#1T/L 철거 후 이설","2020-05-20 10:00","2022-06-30 18:00","2020-05-20 10:00","2022-06-30 18:00","연속"]
[206,"경기","직할","남수원발안#1 T/L","20년 직할 변전정비회사 총액공사","발안S/S 남수원-발안#1T/L LA 하자점검","2020-05-26 09:00","2020-05-26 14:00","2020-05-26 09:00","2020-05-26 14:00","연속"]
[207,"경기","직할","남수원발안#2 T/L","20년 직할 변전정비회사 총액공사","발안S/S 남수원-발안#2T/L LA 하자점검","2020-05-26 14:00","2020-05-26 18:00","2020-05-26 14:00","2020-05-26 18:00","연속"]
[208,"경기","직할","서서울#2봉담#1 T/L","세니온 송전선로 보호 IED 성능개선 시행","봉담S/S 서서울2-봉담T/L 세니온 송전선로 보호 IED 성능개선 시행","2020-05-18 09:00","2020-05-18 18:00","2020-05-18 09:00","2020-05-18 18:00","연속"]
[209,"경기","직할","서서울#2봉담#2 T/L","세니온 송전선로 보호 IED 성능개선 시행","봉담S/S 서서울2-봉담T/L 세니온 송전선로 보호 IED 성능개선 시행","2020-05-19 09:00","2020-05-19 18:00","2020-05-19 09:00","2020-05-19 18:00","연속"]
[210,"경기","직할","서서울#2봉담#1 T/L","세니온 송전선로 보호 IED 성능개선 시행","봉담S/S 서서울2-봉담T/L 세니온 송전선로 보호 IED 성능개선 시행","2020-05-18 09:00","2020-05-18 18:00","취소","취소","연속"]
[211,"경기","직할","서수원호매실#1 T/L","서수원S/S 23kV 현대화공사","154kV 서수원-호매실#1T/L 보호배전반 교체","2020-05-04 09:00","2020-05-08 18:00","취소","취소","연속"]
[212,"경기","직할","서서울서수원#1 T/L","20년 직할 변전정비회사 총액공사","서수원S/S 서서울-서수원#1T/L GIS 조작","2020-05-18 09:00","2020-05-18 14:00","2020-05-18 09:00","2020-05-18 14:00","연속"]
[213,"경기","직할","서서울서수원#2 T/L","20년 직할 변전정비회사 총액공사","서수원S/S 서서울-서수원#2T/L GIS 조작","2020-05-18 14:00","2020-05-18 18:00","2020-05-18 14:00","2020-05-18 18:00","연속"]
[214,"경기","직할","서수원율전#2 T/L","서수원S/S 23kV 현대화공사","154kV 서수원-율전#2T/L 보호배전반 교체","2020-05-25 09:00","2020-05-29 18:00","취소","취소","연속"]
[215,"경기","직할","서서울서수원#2 T/L","20년 직할 변전정비회사 총액공사","서수원S/S 서서울-서수원#2T/L GIS 조작","2020-05-18 14:00","2020-05-18 18:00","취소","취소","연속"]
[216,"경기","직할","서서울서수원#1 T/L","20년 직할 변전정비회사 총액공사","서수원S/S 서서울-서수원#1T/L GIS 조작","2020-05-18 09:00","2020-05-18 14:00","취소","취소","연속"]
[217,"경기","직할","서수원호매실#2 T/L","서수원S/S 23kV 현대화공사","154kV 서수원-호매실#2T/L 보호배전반 교체","2020-05-11 09:00","2020-05-15 18:00","취소","취소","연속"]
[218,"경기","직할","서수원율전#1 T/L","서수원S/S 23kV 현대화공사","154kV 서수원-율전#1T/L 보호배전반 교체","2020-05-19 09:00","2020-05-23 18:00","취소","취소","연속"]
[219,"경기","직할","서수원호매실#1 T/L","서수원S/S 23kV 현대화공사","154kV 서수원-호매실#1T/L 보호배전반 교체","2020-05-04 09:00","2020-05-08 18:00","취소","취소","연속"]
[220,"경기","직할","서수원호매실#2 T/L","서수원S/S 23kV 현대화공사","154kV 서수원-호매실#2T/L 보호배전반 교체","2020-05-11 09:00","2020-05-15 18:00","취소","취소","연속"]
[221,"경기","직할","화성S/S 154kV #62 BUS","20년 경기직할 154kV GIS 정밀점검공사","화성S/S #3M.Tr 2차 GIS 정밀점검","2020-05-18 09:00","2020-05-19 13:00","2020-05-18 09:00","2020-05-19 13:00","연속"]
[222,"경기","직할","화성마도 T/L","20년 경기직할 154kV GIS 정밀점검공사","화성S/S 화성-마도T/L GIS 정밀점검","2020-05-23 09:00","2020-05-24 18:00","취소","취소","연속"]
[223,"경기","직할","화성S/S 154kV #61 BUS","20년 경기직할 154kV GIS 정밀점검공사","화성S/S #63Sh.C GIS 정밀점검","2020-05-28 09:00","2020-05-28 18:00","2020-05-28 09:00","2020-05-28 18:00","연속"]
[224,"경기","직할","화성S/S 154kV #61 BUS","20년 경기직할 154kV GIS 정밀점검공사","화성S/S #64Sh.C GIS 정밀점검","2020-05-31 09:00","2020-05-31 18:00","2020-05-31 09:00","2020-05-31 18:00","연속"]
[225,"경기","평택","고덕평택#1 T/L","154kV 동평택S/S 건설사업","154kV 동평택S/S 변전설비 최초가압","2020-05-28 13:00","2020-05-29 13:00","2020-05-28 13:00","2020-05-29 13:00","연속"]
[226,"경기","평택","서운삼죽 T/L","2020~21년 직할 송전정비회사 총액공사","불량애자교체, 아킹혼설치","2020-05-14 08:00","2020-05-15 18:00","2020-05-14 08:00","2020-05-15 18:00","매일"]
[227,"경기","평택","소사벌안성 T/L","154kV 소사벌안성T/L EBA 절연유 채취작업","1소사벌안성T/L 소사벌C/H EBA 절연유 채취(3상)","2020-05-06 09:00","2020-05-06 16:00","2020-05-06 09:00","2020-05-06 16:00","연속"]
[228,"경기","평택","소사벌안성 T/L","154kV 소사벌안성T/L EBA 절연유 채취작업","1소사벌안성T/L 소사벌C/H EBA 절연유 채취(3상)","2020-05-06 09:00","2020-05-06 16:00","취소","취소","연속"]
[229,"경기","평택","송탄오성CC#1 T/L","154kV 송탄-오성CCT/L 14호 지장철탑 이설공사","고덕산단진입도로 개설관련 지장철탑 이설공사 1기신철, 1기철거, 1기임시, 0.553km","2020-05-09 07:00","2020-05-12 18:00","2020-05-24 07:00","2020-05-27 18:00","연속"]
[230,"경기","평택","송탄오성CC#2 T/L","154kV 송탄-오성CCT/L 14호 지장철탑 이설공사","고덕산단진입도로 개설관련 지장철탑 이설공사 1기신철, 1기철거, 1기임시, 0.553km","2020-05-04 07:00","2020-05-08 18:00","2020-05-19 07:00","2020-05-23 18:00","연속"]
[231,"경기","평택","송탄오성CC#1 T/L","154kV 송탄-오성CCT/L 14호 지장철탑 이설공사","고덕산단진입도로 개설관련 지장철탑 이설공사 1기신철, 1기철거, 1기임시, 0.553km","2020-05-09 07:00","2020-05-12 18:00","취소","취소","연속"]
[232,"경기","평택","송탄오성CC#2 T/L","154kV 송탄-오성CCT/L 14호 지장철탑 이설공사","고덕산단진입도로 개설관련 지장철탑 이설공사 1기신철, 1기철거, 1기임시, 0.553km","2020-05-04 07:00","2020-05-08 18:00","취소","취소","연속"]
[233,"경기","평택","원정만호#2 T/L","20-21 송전정비회사총액공사(피뢰기설치)","20-21 송전정비회사총액공사(피뢰기설치)","2020-05-21 07:00","2020-05-22 18:00","2020-05-21 07:00","2020-05-22 18:00","연속"]
[234,"경기","평택","청북평택#1 T/L","20-21 송전정비회사총액공사(피뢰기설치)","20-21 송전정비회사총액공사(피뢰기설치)","2020-05-25 07:00","2020-05-27 19:00","2020-05-25 07:00","2020-05-27 19:00","연속"]
[235,"경기","평택","둔포추팔#2 T/L","20-21 송전정비회사총액공사(피뢰기설치)","20-21 송전정비회사총액공사(피뢰기설치)","2020-05-18 08:00","2020-05-20 19:00","2020-05-18 08:00","2020-05-20 19:00","연속"]
[236,"경기","평택","둔포추팔#1 T/L","20-21 송전정비회사총액공사(피뢰기설치) _안전이격확보","둔포-추팔 #2 T/L 안전이격확보차 휴전신청","2020-05-18 08:00","2020-05-18 11:00","2020-05-18 08:00","2020-05-18 11:00","연속"]
[237,"경기","평택","평택추팔#1 T/L","20-21년 평택전력지사 송전정비회사 총액공사","상단선로 전력선 교체에 따른 안전거리확보","2020-05-06 07:00","2020-05-06 18:00","2020-05-06 07:00","2020-05-06 18:00","연속"]
[238,"경기","평택","평택추팔#1 T/L","20-21년 평택전력지사 송전정비회사 총액공사","상단선로 전력선 교체에 따른 안전거리확보","2020-05-06 07:00","2020-05-06 18:00","취소","취소","연속"]
[239,"경기","평택","평택S/S 154kV 오산-평택#1T/L CB","평택S/S 154kV 오산-평택#1T/L GCB 정밀점검","평택S/S 154kV 오산-평택#1T/L GCB 정밀점검 / 오산S/S 154kV 오산-평택#1T/L GIS 보통점검","2020-05-13 09:00","2020-05-15 18:00","2020-05-13 09:00","2020-05-15 18:00","연속"]
[240,"경기","평택","평택S/S 154kV 오산-평택#2T/L CB","평택S/S 154kV 오산-평택#2T/L GCB 정밀점검","평택S/S 154kV 오산-평택#2T/L GCB 정밀점검 / 오산S/S 154kV 오산-평택#2T/L GIS 보통점검","2020-05-18 09:00","2020-05-20 18:00","2020-05-18 09:00","2020-05-20 18:00","연속"]
[241,"경기","평택","포승청북 T/L","20-21 송전정비회사총액공사(피뢰기설치) _안전이격확보","청북-평택#1T/L 안전이격확보차","2020-05-27 07:00","2020-05-27 19:00","2020-05-27 07:00","2020-05-27 19:00","연속"]
[242,"강원","강릉","속초간성#1 T/L","간성#4M.Tr 최초가압","간성#4M.Tr 최초가압으로 인한 휴전","2020-05-06 09:00","2020-05-08 18:00","2020-05-06 09:00","2020-05-08 18:00","연속"]
[243,"강원","동해","동해정선 T/L","2020년 동해전력지사 가공송전선로 순시점검 위탁공사","지장수목벌채작업시행","2020-05-14 09:00","2020-05-15 18:00","2020-05-14 09:00","2020-05-15 18:00","매일"]
[244,"강원","동해","동해동영월 T/L","2020년 동해전력지사 가공송전선로 순시점검 위탁공사","지장수목벌채작업시행","2020-05-11 09:00","2020-05-13 18:00","2020-05-11 09:00","2020-05-13 18:00","매일"]
[245,"강원","동해","북평영동TP#2 T/L","'19~20년 강원본부 지중송전설비 위탁공사","154kV 북평-영동화력#2 T/L PD집합반 설치공사","2020-05-08 12:30","2020-05-08 18:00","2020-05-08 12:30","2020-05-08 18:00","연속"]
[246,"강원","동해","북평영동TP#1 T/L","'19~20년 강원본부 지중송전설비 위탁공사","154kV 북평-영동화력#1 T/L PD집합반 설치공사","2020-05-08 09:00","2020-05-08 12:30","2020-05-08 09:00","2020-05-08 12:30","연속"]
[247,"강원","원주","신제천남원주#1 T/L","2020년 가공송전선로 순시점검 위탁공사","○ 154kV 신제천남원주#1T/L 측방 지장수목 벌채 -약 64본 벌채예정","2020-05-29 09:00","2020-05-29 18:00","취소","취소","연속"]
[248,"강원","원주","홍천소양강HP T/L","2020~2021년 강원직할 송전정비회사 총액공사","접속개소해소공사","2020-05-12 07:30","2020-05-14 19:00","2020-05-12 07:30","2020-05-14 19:00","연속"]
[249,"강원","원주","홍천S/S 154kV #60-#65 BUS TIE CB","2020년 원주전력 변전정비 총액공사","170kV GIS 하자점검","2020-05-28 10:00","2020-05-28 18:00","2020-05-28 10:00","2020-05-28 18:00","연속"]
[250,"강원","직할","북춘천화천HP T/L","2020년 강원본부직할 154kV GIS, GCB 정밀점검공사","ㅇ 북춘천S/S 북춘천-화천HP T/L GIS 정밀점검","2020-05-21 09:00","2020-05-23 18:00","2020-05-21 09:00","2020-05-23 18:00","연속"]
[251,"강원","직할","춘천북춘천#1 T/L","2020년 강원본부직할 154kV GIS, GCB 정밀점검공사","ㅇ 북춘천S/S 춘천-북춘천 #1 T/L GIS 정밀점검","2020-05-14 09:00","2020-05-16 18:00","2020-05-14 09:00","2020-05-16 18:00","연속"]
[252,"강원","직할","춘천북춘천#2 T/L","2020년 강원본부직할 154kV GIS, GCB 정밀점검공사","ㅇ 북춘천S/S 춘천-북춘천 #2 T/L GIS 정밀점검","2020-05-11 09:00","2020-05-13 18:00","2020-05-11 09:00","2020-05-13 18:00","연속"]
[253,"강원","직할","북춘천춘천HP T/L","2020년 강원본부직할 154kV GIS, GCB 정밀점검공사","ㅇ 북춘천S/S 북춘천-춘천HP T/L GIS 정밀점검","2020-05-18 09:00","2020-05-20 18:00","2020-05-18 09:00","2020-05-20 18:00","연속"]
[254,"강원","직할","상남인제#1 T/L","2020~2021년 강원직할 송전정비회사 총액공사","접속개소해소공사","2020-05-15 07:30","2020-05-15 19:00","2020-05-15 07:30","2020-05-16 18:00","연속"]
[255,"강원","직할","상남인제#2 T/L","2020~2021년 강원직할 송전정비회사 총액공사","접속개소해소공사","2020-05-16 07:30","2020-05-19 19:00","2020-05-17 07:30","2020-05-20 19:00","연속"]
[256,"강원","직할","운천철원#2 T/L","20~21 강원본부 직할 변전정비 총액공사","○ 운천-철원 #2T/L LA A, B, C 보통점검","2020-05-26 14:00","2020-05-26 18:00","2020-05-26 14:00","2020-05-26 18:00","연속"]
[257,"강원","직할","철원화천#1 T/L","2020~2021년 경기북부 직할 가공송전 정비회사 총액공사","ㅇ 154kV 운천-철원#1T/L 병가선로 - 압축인류크램프 및 점퍼선 교체","2020-05-25 08:00","2020-05-25 18:00","2020-05-25 08:00","2020-05-25 18:00","연속"]
[258,"강원","태백","정선영월CC T/L","'19~20년 강원본부 지중송전설비 위탁공사","154kV 정선-영월CC T/L PD집합반 설치공사","2020-05-06 09:00","2020-05-06 18:00","2020-05-06 09:00","2020-05-06 18:00","연속"]
[259,"강원","태백","동영월영월CC T/L","'19~20년 강원본부 지중송전설비 위탁공사","154kV 동영월-영월CC T/L PD집합반 설치공사","2020-05-07 09:00","2020-05-07 18:00","2020-05-07 09:00","2020-05-07 18:00","연속"]
[260,"강원","태백","신제천영월CC#2 T/L","'19~20년 강원본부 지중송전설비 위탁공사","154kV 신제천-영월CC#2 T/L PD집합반 설치공사","2020-05-07 09:00","2020-05-07 18:00","2020-05-07 09:00","2020-05-07 18:00","연속"]
[261,"강원","태백","신제천영월CC#1 T/L","'19~20년 강원본부 지중송전설비 위탁공사","154kV 신제천-영월CC#1 T/L PD집합반 설치공사","2020-05-06 09:00","2020-05-06 18:00","2020-05-06 09:00","2020-05-06 18:00","연속"]
[262,"강원","태백","제천영월#2 T/L","태백전력지사 170kV GIS 정밀점검 공사","170kV 제천영월 #2T/L GIS 정밀점검 공사","2020-05-18 10:00","2020-05-20 18:00","2020-05-18 10:00","2020-05-20 18:00","연속"]
[263,"강원","태백","태백영월 T/L","태백전력지사 170kV GIS 정밀점검 공사","170kV 태백영월T/L GIS 정밀점검 공사","2020-05-21 10:00","2020-05-23 18:00","2020-05-21 10:00","2020-05-23 18:00","연속"]
[264,"강원","태백","영월S/S 154kV #60-#65 BUS TIE GIS","'20년 태백전력지사 170kV GIS 정밀점검 공사","영월S/S #1 BUS-TIE GIS 정밀점검","2020-05-25 10:00","2020-05-27 18:00","2020-05-25 10:00","2020-05-27 18:00","연속"]
[265,"강원","태백","제천영월#1 T/L","태백전력지사 170kV GIS 정밀점검 공사","170kV 제천영월 #1T/L GIS 정밀점검 공사","2020-05-14 10:00","2020-05-16 18:00","2020-05-14 10:00","2020-05-16 18:00","연속"]
[266,"충북","직할","진천광혜원#2 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","#1M.Tr 부싱조립 안전이격 및 신규 GIS 가압","2020-05-01 09:00","2020-05-02 18:00","2020-05-01 09:00","2020-05-03 18:00","연속"]
[267,"충북","직할","진천광혜원#1 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","신규 GIS 가압(무부하가압 포함)","2020-05-03 16:00","2020-05-04 18:00","2020-05-05 09:00","2020-05-06 18:00","연속"]
[268,"충북","직할","서운광혜원 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","#2M.Tr 부싱 조립 안전이격거리 확보 및 신규 GIS 가압","2020-05-09 09:00","2020-05-10 18:00","2020-05-08 09:00","2020-05-10 18:00","연속"]
[269,"충북","청주","국사봉명#2 T/L","154kV 국사-봉명T/L 안전이격확보공사","24호 철탑교체 1기","2020-05-24 07:00","2020-05-31 18:00","취소","취소","연속"]
[270,"충북","청주","오창국사#1 T/L","2020-2021년 청주전력지사 송전정비회사 총액공사","사다리 설치 : No.18","2020-05-27 09:00","2020-05-27 18:00","취소","취소","연속"]
[271,"충북","청주","국사봉명#1 T/L","154kV 국사-봉명T/L 안전이격확보공사","154kV 국사-봉명#1TL 충전부 방호조치","2020-05-23 07:00","2020-05-23 18:00","취소","취소","연속"]
[272,"충북","청주","남청주청주#3 T/L","20-21년 청주전력 변전정비회사 총액공사","남청주,청주S/S 154kV 남청주청주#3T/L GIS 보통점검","2020-05-07 09:00","2020-05-07 18:00","2020-05-07 09:00","2020-05-07 18:00","연속"]
[273,"충북","청주","남청주죽림#1 T/L","154kV 남청주-죽림T/L 정밀점검","154kV 남청주-죽림#1T/L (22기) 정밀점검","2020-05-09 08:00","2020-05-09 18:00","취소","취소","연속"]
[274,"충북","청주","북청주봉명#1 T/L","2020년 청주전력지사 170kV GIS 정밀점검","2020년 청주전력지사 170kV GIS 정밀점검","2020-05-16 09:00","2020-05-17 18:00","2020-05-16 09:00","2020-05-17 18:00","연속"]
[275,"충북","청주","사직북청주#2 T/L","2020년 청주전력지사 170kV GIS 정밀점검","2020년 청주전력지사 170kV GIS 정밀점검 (누기개소 보수)","2020-05-02 09:00","2020-05-03 18:00","취소","취소","연속"]
[276,"충북","청주","오송북청주#2 T/L","154kV 국사-봉명T/L 안전이격확보공사","154kV 오송-북청주#2TL 충전부 방호조치","2020-05-23 07:00","2020-05-23 18:00","취소","취소","연속"]
[277,"충북","청주","오송북청주#1 T/L","154kV 국사-봉명T/L 안전이격확보공사","24호 철탑교체 1기","2020-05-24 07:00","2020-05-31 18:00","취소","취소","연속"]
[278,"충북","청주","남청주오송#1 T/L","154kV 남청주-오송T/L EBA PD 집합반 설치공사","오송 C/H 내 154kV 남청주-오송#1 T/L EBA PD 집합반 설치 및 피뢰기 열화진단","2020-05-30 09:00","2020-05-30 18:00","취소","취소","연속"]
[279,"충북","청주","남청주오송#2 T/L","154kV 남청주-오송T/L EBA PD 집합반 설치공사","오송C/H 내 154kV 남청주-오송#2 T/L EBA PD 집합반 설치","2020-05-31 09:00","2020-05-31 18:00","취소","취소","연속"]
[280,"충북","청주","오송북청주#1 T/L","154kV 오송S/S #1M.Tr용 GIS 설치공사","#1BUS 증설분(#1M.Tr Bay) 무부하가압","2020-05-14 09:00","2020-05-15 18:00","2020-05-14 09:00","2020-05-15 18:00","연속"]
[281,"충북","청주","오송북청주#1 T/L","154kV 오송S/S #1M.Tr용 GIS 설치공사","#2BUS 증설분(#1M.Tr Bay) 무부하가압","2020-05-21 09:00","2020-05-22 18:00","2020-05-21 09:00","2020-05-22 18:00","연속"]
[282,"충북","청주","남청주청주#2 T/L","20-21년 청주전력 변전정비회사 총액공사","청주S/S 154kV 남청주청주#2T/L GIS 초기점검","2020-05-08 09:30","2020-05-08 18:00","2020-05-08 09:30","2020-05-08 18:00","연속"]
[283,"충북","충주","신제천영월CC#2 T/L","20-21년 충주전력 변전정비회사 총액공사","신제천S/S 154kV 신제천-영월CC#2T/L GIS 하자점검","2020-05-15 09:00","2020-05-15 18:00","2020-05-15 09:00","2020-05-15 18:00","연속"]
[284,"충북","충주","신제천주진#1 T/L","20-21년 충주전력 변전정비회사 총액공사","신제천S/S 154kV 신제천-주진#1T/L GIS 하자점검","2020-05-07 09:00","2020-05-07 18:00","2020-05-07 09:00","2020-05-07 18:00","연속"]
[285,"충북","충주","왕암충주 T/L","345kV 곤지암-신충주 등 4개T/L 전력선교체공사","전선접속개소 해소 전력선교체공사","2020-05-19 08:30","2020-05-22 18:00","2020-05-26 09:00","2020-05-28 18:00","연속"]
[286,"충북","충주","왕암가남#1 T/L","154kV 신충주-북충주T/L 하자처리","154kV 신충주-북충주#1,2T/L, 왕암-가남T/L 이도조정, 금구류 취부 부대공사 1식","2020-05-19 08:00","2020-05-19 18:00","2020-05-19 08:00","2020-05-19 18:00","연속"]
[287,"충북","충주","왕암가남#2 T/L","154kV 신충주-북충주T/L 하자처리","154kV 신충주-북충주#1,2T/L, 왕암-가남T/L 이도조정, 금구류 취부 부대공사 1식","2020-05-21 08:00","2020-05-21 18:00","2020-05-21 08:00","2020-05-21 18:00","연속"]
[288,"충북","충주","음성괴산 T/L","154kV 풍동-음성T/L 지장철탑 이설공사","○ 공사구간 : 154kV 풍동-음성 No.73~76 (4회선 구간) ○ 공사개요 : 4회선 철탑신설 2기, 철거 2기, 전선교체 3.6C-km","2020-05-18 07:00","2020-05-28 18:00","2020-05-18 07:00","2020-05-28 18:00","연속"]
[289,"충북","충주","음성사리 T/L","154kV 풍동-음성T/L 지장철탑 이설공사","○ 공사구간 : 154kV 풍동-음성 No.73~76 (4회선 구간) ○ 공사개요 : 4회선 철탑신설 2기, 철거 2기, 전선교체 3.6C-km","2020-05-29 07:00","2020-06-30 18:00","2020-05-29 07:00","2020-06-30 18:00","연속"]
[290,"충북","충주","북충주충주 T/L","345kV 곤지암-신충주 등 4개T/L 전력선교체공사","전선접속개소 해소 전력선교체공사","2020-05-15 08:30","2020-05-18 18:00","2020-05-29 09:00","2020-05-31 18:00","연속"]
[291,"충북","충주","충주충주HP#1 T/L","345kV 곤지암-신충주 등 4개T/L 전력선교체공사","전선접속개소 해소 전력선교체공사(4회선 작업을 위한 병행휴전)","2020-05-19 09:00","2020-05-22 18:00","2020-05-19 09:00","2020-05-22 18:00","연속"]
[292,"충북","충주","충주충주HP#2 T/L","345kV 곤지암-신충주 등 4개T/L 전력선교체공사","전선접속개소 해소 전력선교체공사(4회선 작업을 위한 병행휴전)","2020-05-15 09:00","2020-05-18 18:00","2020-05-15 09:00","2020-05-18 18:00","연속"]
[293,"충북","충주","풍동음성#1 T/L","154kV 풍동-음성T/L 지장철탑 이설공사","○ 공사구간 : 154kV 풍동-음성 No.73~76 (4회선 구간) ○ 공사개요 : 4회선 철탑신설 2기, 철거 2기, 전선교체 3.6C-km","2020-05-18 07:00","2020-05-28 18:00","2020-05-18 07:00","2020-05-28 18:00","연속"]
[294,"충북","충주","풍동음성#2 T/L","154kV 풍동-음성T/L 지장철탑 이설공사","○ 공사구간 : 154kV 풍동-음성 No.73~76 (4회선 구간) ○ 공사개요 : 4회선 철탑신설 2기, 철거 2기, 전선교체 3.6C-km","2020-05-29 07:00","2020-06-30 18:00","2020-05-29 07:00","2020-06-30 18:00","연속"]
[295,"대전충남","직할","세종송강#1 T/L","[송전]국제과학비즈니스벨트 지장송전선로 지중화공사(요청자시행)","ㅇ 요청자(한국토지주택공사) 직접시행 지장이설 및 지중화공사 ㅇ 공사구간 : 154kV 세종-송강T/L No.16~17 ㅇ 철탑 : C/H 1기 설치, 가철탑 1기 ㅇ 전력선 : HSTACIR/AW 330 x S x 2C (1.041km) ㅇ CH 1기 설치, 가철탑 1기 설치철거 외 기타 부대공사 시행","2020-05-01 07:00","2020-05-02 18:00","취소","취소","연속"]
[296,"대전충남","직할","대화둔산#1 T/L","[송전]154kV 대화-둔산 등 2개T/L 선종교체 공사","○ 공사구간 : 154kV 대화-둔산 #1T/L 전구간 ○ 선종교체 : 154kV OF 2000㎟ → 154kV XLPE 2000㎟ (6.26km)","2020-05-01 09:00","2020-12-31 18:00","취소","취소","연속"]
[297,"대전충남","직할","동대전대화#1 T/L","[송전]154kV 대화-둔산 등 2개T/L 선종교체 공사","○ 공사구간 : 154kV 동대전-대화#1T/L 전구간 ○ 선종교체 : 154kV OF 2000㎟ → 154kV XLPE 2000㎟ (4.42km)","2020-05-01 09:00","2020-12-31 18:00","취소","취소","연속"]
[298,"대전충남","서산","태안태안화력 T/L","서산P/O OPGW 항공장애표시구 시설공사","항공장애표시구 31 개 설치","2020-05-02 09:00","2020-05-03 18:00","2020-05-02 09:00","2020-05-03 18:00","매일"]
[299,"대전충남","직할","세종송강#2 T/L","[송전]국제과학비즈니스벨트 지장송전선로 지중화공사(요청자시행)","ㅇ 요청자(한국토지주택공사) 직접시행 지장이설 및 지중화공사 ㅇ 공사구간 : 154kV 세종-송강T/L No.16~17 ㅇ 철탑 : C/H 1기 설치, 가철탑 1기 ㅇ 전력선 : HSTACIR/AW 330 x S x 2C (1.041km) ㅇ CH 1기 설치, 가철탑 1기 설치철거 외 기타 부대공사 시행","2020-05-03 07:00","2020-05-08 18:00","2020-05-16 07:00","2020-05-17 18:00","연속"]
[300,"대전충남","서산","신당진S/S 154kV #61-#66 BUS TIE CB","20년 서산P/O 변전정비 총액공사","신당진S/S 154kV #1BUS-TIE GIS(6200) 보통점검","2020-05-04 09:00","2020-05-04 18:00","2020-05-04 09:00","2020-05-04 18:00","연속"]
[301,"대전충남","세종","덕진공주#1 T/L","[변전]세종PO 변전정비회사 총액공사","세종전력지사 변전정비회사 총액공사 - 덕진S/S덕진-공주#1T/L 미동작차단기 조작시험 및 피뢰기 보통점검 - 공주S/S덕진-공주#1T/L 미동작차단기 조작시험 및 피뢰기 보통점검","2020-05-06 09:00","2020-05-07 18:00","2020-05-06 09:00","2020-05-07 18:00","연속"]
[302,"대전충남","서산","당진송악#2 T/L","20년 서산P/O 변전정비 총액공사","당진S/S 당진-송악#2T/L GIS (637) 초기점검","2020-05-07 09:00","2020-05-07 18:00","2020-05-07 09:00","2020-05-07 18:00","연속"]
[303,"대전충남","아산","아산예산#1 T/L","예산S/S 아산-예산#1T/L GIS 보통점검 등","예산S/S 아산-예산#1T/L GIS 보통점검 등","2020-05-07 09:00","2020-05-07 18:00","2020-05-07 09:00","2020-05-07 18:00","연속"]
[304,"대전충남","아산","신온양한샘#1 T/L","한샘S/S 신온양-한샘#1T/L GIS 보통점검 및 LA 보통점검","한샘S/S 신온양-한샘#1T/L GIS 보통점검 및 LA 보통점검","2020-05-07 09:00","2020-05-07 18:00","2020-05-07 09:00","2020-05-07 18:00","연속"]
[305,"대전충남","청양","청양신풍#1 T/L","청양S/S 청양-신풍#1T/L 전자변 교체","청양S/S 청양-신풍#1T/L 전자변 교체 및 LA 보통점검","2020-05-07 09:00","2020-05-07 18:00","취소","취소","연속"]
[306,"대전충남","세종","덕진대화#1 T/L","[변전]세종PO 변전정비회사 총액공사","세종전력지사 변전정비회사 총액공사 - 덕진S/S덕진-대화#1T/L 장기미동작차단기 조작시험","2020-05-29 09:00","2020-05-29 18:00","2020-05-29 09:00","2020-05-29 18:00","연속"]
[307,"대전충남","아산","아산예산#2 T/L","예산S/S 아산-예산#2T/L GIS 보통점검 등","예산S/S 아산-예산#2T/L GIS 보통점검 등","2020-05-08 09:00","2020-05-08 18:00","2020-05-08 09:00","2020-05-08 18:00","연속"]
[308,"대전충남","아산","신온양한샘#2 T/L","한샘S/S 신온양-한샘#2T/L GIS 보통점검 및 LA 보통점검","한샘S/S 신온양-한샘#2T/L GIS 보통점검 및 LA 보통점검","2020-05-08 09:00","2020-05-08 18:00","2020-05-08 09:00","2020-05-08 18:00","연속"]
[309,"대전충남","청양","청양신풍#2 T/L","청양S/S 청양-신풍#2T/L 전자변 교체","청양S/S 청양-신풍#2T/L 전자변 교체 및 LA 보통점검","2020-05-08 09:00","2020-05-08 18:00","취소","취소","연속"]
[310,"대전충남","직할","세종송강#1 T/L","[송전]국제과학비즈니스벨트 지장송전선로 지중화공사(요청자시행)","ㅇ 요청자(한국토지주택공사) 직접시행 지장이설 및 지중화공사 ㅇ 공사구간 : 154kV 세종-송강T/L No.16~17 ㅇ 철탑 : C/H 1기 설치, 가철탑 1기 ㅇ 전력선 : HSTACIR/AW 330 x S x 2C (1.041km) ㅇ CH 1기 설치, 가철탑 1기 설치철거 외 기타 부대공사 시행","2020-05-09 07:00","2020-05-26 18:00","2020-05-18 07:00","2020-05-26 18:00","연속"]
[311,"대전충남","아산","둔포석곡#1 T/L","석곡S/S 154kV #4M.Tr 증설공사(무부하가압)","석곡S/S 154kV #4M.Tr 증설공사(무부하가압)","2020-05-09 10:00","2020-05-11 10:00","2020-05-09 10:00","2020-05-11 10:00","연속"]
[312,"대전충남","아산","인주탕정#1 T/L","154kV 인주-불당T/L C/H 건설사업","154kV 인주-불당T/L C/H 건설공사 - C/H 접속을 위한 병가철탑 상하단 교체공사 시행","2020-05-11 07:00","2020-05-18 18:00","취소","취소","연속"]
[313,"대전충남","아산","서천안탕정#2 T/L","154kV 인주-불당T/L C/H 건설사업","154kV 인주-불당T/L C/H 건설공사 - C/H 접속을 위한 병가철탑 상하단 교체공사 시행","2020-05-11 07:00","2020-05-18 18:00","2020-05-11 07:00","2020-05-18 18:00","연속"]
[314,"대전충남","서산","석문당진화력#1 T/L","당진화력S/Y 154kV 장기사용 GIS 대체공사","당진화력S/Y 154kV 장기사용 GIS 대체공사","2020-05-11 09:00","2020-05-20 18:00","2020-05-11 09:00","2020-05-20 18:00","연속"]
[315,"대전충남","서산","당진T/P 154kV #1 BUS","당진화력S/Y 154kV 장기사용 GIS 대체공사","당진화력S/Y 154kV 장기사용 GIS 대체공사","2020-05-11 09:00","2020-05-15 18:00","2020-05-11 09:00","2020-05-15 18:00","연속"]
[316,"대전충남","서산","대산석문#2 T/L","154kV 일진제 인출DS 개선","석문S/S 154kV 대산-석문#2 DS개선 (병행) 대산S/S 154kV 대산-석문#2T/L LA 보통점검","2020-05-11 09:00","2020-05-13 18:00","2020-05-11 09:00","2020-05-13 18:00","연속"]
[317,"대전충남","세종","덕진공주#2 T/L","[변전]세종PO 변전정비회사 총액공사","세종전력지사 변전정비회사 총액공사 - 덕진S/S덕진-공주#2T/L 미동작차단기 조작시험 및 피뢰기 보통점검 - 공주S/S덕진-공주#2T/L 미동작차단기 조작시험 및 피뢰기 보통점검","2020-05-11 09:00","2020-05-12 18:00","2020-05-11 09:00","2020-05-12 18:00","연속"]
[318,"대전충남","대전","팔봉두마#2 T/L","154kV 신계룡-두마T/L OPGW 증설공사","신계룡S/S ~ 두마S/S 간 가공지선(ACSR 97SQ)를 OPGW/100SQ로 변경","2020-05-13 07:00","2020-05-16 18:00","2020-05-13 07:00","2020-05-16 18:00","연속"]
[319,"대전충남","세종","덕진대화#2 T/L","[변전]세종PO 변전정비회사 총액공사","세종전력지사 변전정비회사 총액공사 - 덕진S/S덕진-대화#2T/L 장기미동작차단기 조작시험","2020-05-30 09:00","2020-05-30 18:00","2020-05-30 09:00","2020-05-30 18:00","연속"]
[320,"대전충남","서산","태안T/P 154kV #60-#65 BUS TIE CB","20년도 장기 미동작 차단기 조작시험","태안T/P 154kV #1 Bus-Tie 6100 CB 조작시험","2020-05-13 10:00","2020-05-13 14:00","2020-05-13 10:00","2020-05-13 14:00","연속"]
[321,"대전충남","세종","부강월산#1 T/L","[변전]세종PO 변전정비회사 총액공사","세종전력지사 변전정비회사 총액공사 - 부강S/S부강-월산#1T/L 피뢰기 보통점검 및 장기미동작차단기조작 - 부강S/S부강-월산#2T/L 피뢰기 보통점검 및 장기미동작차단기조작 - 월산S/S부강-월산#1T/L GIS 보통점검 및 피뢰기 보통점검 - 월산S/S부강-월산#2T/L GIS 보통점검 및 피뢰기 보통점검","2020-05-14 09:00","2020-05-15 18:00","2020-05-14 09:00","2020-05-15 18:00","연속"]
[322,"대전충남","서산","GSEPS#1 T/L","20년 서산P/O 154kV GIS 정밀점검","송악S/S 154kV GSEPS #1T/L GIS 정밀점검","2020-05-15 09:00","2020-05-17 18:00","2020-05-15 09:00","2020-05-17 18:00","연속"]
[323,"대전충남","아산","둔포석곡#1 T/L","석곡S/S 154kV #4M.Tr 증설공사(무부하가압)","석곡S/S 154kV #4M.Tr 증설공사(무부하가압)","2020-05-15 10:00","2020-05-16 10:00","2020-05-15 10:00","2020-05-16 10:00","연속"]
[324,"대전충남","서산","당진T/P 154kV #2 BUS","당진화력S/Y 154kV 장기사용 GIS 대체공사","당진화력S/Y 154kV 장기사용 GIS 대체공사","2020-05-16 09:00","2020-05-20 18:00","2020-05-16 09:00","2020-05-20 18:00","연속"]
[325,"대전충남","서산","대산석문#1 T/L","154kV 일진제 인출DS 개선","석문S/S 154kV 대산-석문#1 DS개선 (병행)대산S/S 154kV 대산-석문#1T/L LA,CVT 보통점검","2020-05-18 09:00","2020-05-20 18:00","2020-05-18 09:00","2020-05-20 18:00","연속"]
[326,"대전충남","세종","천안전의#1 T/L","[변전]세종PO 변전정비회사 총액공사","세종전력지사 변전정비회사 총액공사 - 전의S/S천안-전의#1T/L 피뢰기 하자점검","2020-05-18 09:00","2020-05-18 18:00","취소","취소","연속"]
[327,"대전충남","아산","풍세장재#1 T/L","154kV 풍세-장재T/L 일진제 PMJ 교체공사","일진제 R-type 조립식접속함(PMJ) 교체","2020-05-18 09:00","2020-05-24 18:00","2020-05-18 09:00","2020-05-24 18:00","연속"]
[328,"대전충남","아산","인주탕정#2 T/L","154kV 인주-불당T/L C/H 건설사업","154kV 인주-불당T/L C/H 건설공사 - C/H 접속을 위한 병가철탑 상하단 교체공사 시행","2020-05-19 07:00","2020-05-26 18:00","취소","취소","연속"]
[329,"대전충남","아산","서천안탕정#1 T/L","154kV 인주-불당T/L C/H 건설사업","154kV 인주-불당T/L C/H 건설공사 - C/H 접속을 위한 병가철탑 상하단 교체공사 시행","2020-05-19 07:00","2020-05-26 18:00","2020-05-19 07:00","2020-05-26 18:00","연속"]
[330,"대전충남","서산","북당진S/S 154kV #60-65BUS TIE CB","345kV 북당진S/S #1M.Tr 증설공사","M.TR 실부하 가압","2020-05-19 08:00","2020-05-19 18:00","2020-05-19 08:00","2020-05-19 18:00","연속"]
[331,"대전충남","서산","북당진S/S 154kV 바이오매스#2T/L CB","345kV 북당진S/S #1M.Tr 증설공사","M.TR 실부하 가압","2020-05-19 08:00","2020-05-19 18:00","2020-05-19 08:00","2020-05-19 18:00","연속"]
[332,"대전충남","세종","천안전의#2 T/L","[변전]세종PO 변전정비회사 총액공사","세종전력지사 변전정비회사 총액공사 - 전의S/S천안-전의#2T/L 피뢰기 하자점검","2020-05-19 09:00","2020-05-19 18:00","취소","취소","연속"]
[333,"대전충남","세종","세종서세종#1 T/L","[변전]세종PO 변전정비회사 총액공사","세종전력지사 변전정비회사 총액공사 - 세종S/S세종-서세종#1T/L 장기미동작차단기 조작시험","2020-05-20 09:00","2020-05-20 18:00","2020-05-20 09:00","2020-05-20 18:00","연속"]
[334,"대전충남","세종","세종서세종#2 T/L","[변전]세종PO 변전정비회사 총액공사","세종전력지사 변전정비회사 총액공사 - 세종S/S세종-서세종#2T/L 장기미동작차단기 조작시험","2020-05-21 09:00","2020-05-21 18:00","2020-05-21 09:00","2020-05-21 18:00","연속"]
[335,"대전충남","서산","당진화력S/Y 154kV #1 BUS TIE CB","당진화력S/Y 154kV 장기사용 GIS 대체공사","당진화력S/Y 154kV 장기사용 GIS 대체공사(BUS TIE GIS 대체)","2020-05-22 09:00","2020-06-08 18:00","2020-05-22 09:00","2020-06-08 18:00","연속"]
[336,"대전충남","서산","석문당진화력#2 T/L","당진화력S/Y 154kV 장기사용 GIS 대체공사","당진화력S/Y 154kV 장기사용 GIS 대체공사","2020-05-22 09:00","2020-06-08 18:00","2020-05-22 09:00","2020-06-08 18:00","연속"]
[337,"대전충남","서산","당진T/P 154kV #1 BUS","당진화력S/Y 154kV 장기사용 GIS 대체공사","당진화력S/Y 154kV 장기사용 GIS 대체공사","2020-05-22 09:00","2020-05-31 18:00","2020-05-22 09:00","2020-05-31 18:00","연속"]
[338,"대전충남","서산","송악GSEPS#2 T/L","20년 서산P/O 154kV GIS 정밀점검","송악S/S 154kV GSEPS #2T/L GIS 정밀점검","2020-05-22 09:00","2020-05-24 18:00","2020-05-22 09:00","2020-05-24 18:00","연속"]
[339,"대전충남","아산","불당서천안#1 T/L","154kV 불당S/S SW 증설공사(#1BUS 무부하가압)","154kV 불당S/S SW 증설공사(#1BUS 무부하가압)","2020-05-22 10:30","2020-05-23 10:30","취소","취소","연속"]
[340,"대전충남","서산","서산태안화력 T/L","`20-21년 송전정비회사 총액공사","154kV 서산-태안화력T/L 이도조정 및 애자교체 공사 ○ 이도조정 : No.14-15 하단 등 7개소 ○ 애자교체 : No.36등 2기","2020-05-25 08:00","2020-05-26 18:00","2020-05-25 08:00","2020-05-26 18:00","매일"]
[341,"대전충남","세종","조치원전의#1 T/L","[변전]세종PO 변전정비회사 총액공사","세종전력지사 변전정비회사 총액공사 - 전의S/S조치원-전의#1T/L GIS보통점검 및 피뢰기 하자점검 - 조치원S/S조치원-전의#1T/L GIS 장기미동작차단기 조작시험","2020-05-25 09:00","2020-05-26 18:00","2020-05-25 09:00","2020-05-26 18:00","연속"]
[342,"대전충남","아산","풍세장재#2 T/L","154kV 풍세-장재T/L 일진제 PMJ 교체공사","일진제 R-type 조립식접속함(PMJ) 교체","2020-05-25 09:00","2020-05-31 18:00","2020-05-25 09:00","2020-05-31 18:00","연속"]
[343,"대전충남","청양","신서천옥산#1 T/L","옥산-서천#1T/L 관련기기 점검","옥산S/S 보통점검, 전자변 교체 및 LA 보통점검 서천S/S 초기점검","2020-05-25 09:00","2020-05-25 18:00","2020-05-25 09:00","2020-05-25 18:00","연속"]
[344,"대전충남","서산","태안안면#1 T/L","20년도 장기 미동작 차단기 조작시험","태안S/S 154kV 태안-안면#1T/L 617 CB 조작시험","2020-05-25 10:00","2020-05-25 14:00","2020-05-25 10:00","2020-05-25 14:00","연속"]
[345,"대전충남","청양","신서천대천#1 T/L","서천S/S 대천-서천#1T/L 초기점검","서천S/S 대천-서천#1T/L 초기점검","2020-05-26 09:00","2020-05-26 18:00","2020-05-26 09:00","2020-05-26 18:00","연속"]
[346,"대전충남","세종","세종송강#2 T/L","154kV 둔곡S/S 및 관련T/L 건설공사","154kV 세종-둔곡T/L, 154kV 둔곡-송강 지중T/L #2T/L 본선로 구성 및 154kV 둔곡S/S #2T/L 가압","2020-05-27 07:00","2020-05-30 18:00","2020-05-27 07:00","2020-06-03 18:00","연속"]
[347,"대전충남","아산","서천안탕정#1 T/L","154kV 인주-불당T/L C/H 건설사업","154kV 인주-불당T/L C/H 건설공사 - C/H 접속을 위한 병가철탑 상하단 교체공사 시행","2020-05-27 07:00","2020-06-29 18:00","2020-05-27 07:00","2020-06-29 18:00","연속"]
[348,"대전충남","아산","인주탕정#1 T/L","154kV 인주-불당T/L C/H 건설사업","154kV 인주-불당T/L C/H 건설공사 - C/H 접속을 위한 병가철탑 상하단 교체공사 시행","2020-05-27 07:00","2020-06-22 18:00","취소","취소","연속"]
[349,"대전충남","서산","신당진S/S 154kV #60-#65 BUS TIE GIS","20년 서산P/O 154kV GIS 정밀점검","신당진 154kV #1BUS-TIE GIS 정밀점검","2020-05-27 09:00","2020-05-29 18:00","2020-05-27 09:00","2020-05-29 18:00","연속"]
[350,"대전충남","세종","조치원전의#2 T/L","[변전]세종PO 변전정비회사 총액공사","세종전력지사 변전정비회사 총액공사 - 전의S/S조치원-전의#2T/L GIS보통점검 및 피뢰기 하자점검 - 조치원S/S조치원-전의#2T/L GIS 장기미동작차단기 조작시험","2020-05-27 09:00","2020-05-28 18:00","2020-05-27 09:00","2020-05-28 18:00","연속"]
[351,"대전충남","서산","태안안면#2 T/L","20년도 장기 미동작 차단기 조작시험","태안S/S 154kV 태안-안면#2T/L 627 CB 조작시험","2020-05-27 10:00","2020-05-27 14:00","2020-05-27 10:00","2020-05-27 14:00","연속"]
[352,"대전충남","아산","불당서천안#2 T/L","154kV 불당S/S SW 증설공사(#2BUS 무부하가압)","154kV 불당S/S SW 증설공사(#2BUS 무부하가압)","2020-05-28 10:30","2020-05-29 10:30","취소","취소","연속"]
[353,"대전충남","세종","부강월산#2 T/L","[변전]세종PO 변전정비회사 총액공사","세종전력지사 변전정비회사 총액공사 - 부강S/S부강-월산#1T/L 피뢰기 보통점검 및 장기미동작차단기조작 - 부강S/S부강-월산#2T/L 피뢰기 보통점검 및 장기미동작차단기조작 - 월산S/S부강-월산#1T/L GIS 보통점검 및 피뢰기 보통점검 - 월산S/S부강-월산#2T/L GIS 보통점검 및 피뢰기 보통점검","2020-05-08 09:00","2020-05-08 18:00","2020-05-08 09:00","2020-05-08 18:00","연속"]
[354,"대전충남","청양","동군산장항#2 T/L","[송전]154kV 옥산-장항T/L 불량애자교체공사(병가)","[송전]154kV 옥산-장항T/L 불량애자교체공사(병가) - No.3~70 (19기, 1,096장)","2020-05-29 09:00","2020-05-29 18:00","2020-05-29 09:00","2020-05-29 18:00","연속"]
[355,"대전충남","세종","부강월산#2 T/L","[변전]세종PO 변전정비회사 총액공사","세종전력지사 변전정비회사 총액공사 - 부강S/S부강-월산#1T/L 피뢰기 보통점검 및 장기미동작차단기조작 - 부강S/S부강-월산#2T/L 피뢰기 보통점검 및 장기미동작차단기조작 - 월산S/S부강-월산#1T/L GIS 보통점검 및 피뢰기 보통점검 - 월산S/S부강-월산#2T/L GIS 보통점검 및 피뢰기 보통점검","2020-05-13 09:00","2020-05-13 18:00","2020-05-13 09:00","2020-05-13 18:00","연속"]
[356,"전북","군산","군산S/S 154kV #60-#65 BUS TIE CB","군산P/O 154kV 이상 차단기 조작시험(6100)","6100 개폐타임측정","2020-05-25 09:00","2020-05-25 10:30","2020-05-25 09:00","2020-05-25 10:30","연속"]
[357,"전북","군산","군산S/S 154kV #62-#67 BUS TIE CB","군산P/O 154kV 이상 차단기 보통점검(6300)","6300 CB 보통점검","2020-05-25 10:30","2020-05-25 18:00","2020-05-25 10:30","2020-05-25 18:00","연속"]
[358,"전북","군산","군산S/S 154kV #61-#62 SEC CB","군산P/O 154kV 이상 차단기 조작시험(61-62-0)","61-62-0 CB 조작시험","2020-05-26 09:00","2020-05-26 10:30","2020-05-26 09:00","2020-05-26 10:30","연속"]
[359,"전북","군산","군산S/S 154kV #60-#61 SEC CB","군산P/O 154kV 이상 차단기 점검공사(60-61-0)","60-61-0 CB 보통점검","2020-05-26 10:30","2020-05-26 18:00","2020-05-26 10:30","2020-05-26 18:00","연속"]
[360,"전북","군산","군산S/S 154kV #66-#67 SEC CB","군산P/O 154kV 이상 차단기 조작시험(66-67-0)","66-67-0 CB 조작시험","2020-05-27 09:00","2020-05-27 10:30","2020-05-27 09:00","2020-05-27 10:30","연속"]
[361,"전북","군산","군산S/S 154kV #65-#66 SEC CB","군산P/O 154kV 이상 차단기 점검공사(65-66-0)","65-66-0 CB 보통점검","2020-05-27 10:30","2020-05-27 18:00","2020-05-27 10:30","2020-05-27 18:00","연속"]
[362,"전북","군산","영등팔봉#2 T/L","군산P/O 154kV이상 차단기 조작시험공사","영등,팔봉S/S 영등-팔봉#2T/L 차단기 조작시험","2020-05-08 13:00","2020-05-08 16:00","2020-05-08 13:00","2020-05-08 16:00","연속"]
[363,"전북","군산","군산영등#1 T/L","군산P/O 154kV이상 차단기 조작시험공사","영등,군산S/S 군산-영등#1T/L 차단기 조작시험","2020-05-07 09:30","2020-05-07 12:00","2020-05-07 09:30","2020-05-07 12:00","연속"]
[364,"전북","군산","군산영등#2 T/L","군산P/O 154kV이상 차단기 조작시험공사","영등,군산S/S 군산-영등#2T/L 차단기 조작시험","2020-05-07 13:00","2020-05-07 16:00","2020-05-07 13:00","2020-05-07 16:00","연속"]
[365,"전북","군산","영등팔봉#1 T/L","군산P/O 154kV이상 차단기 조작시험공사","영등,팔봉S/S 영등-팔봉#1T/L 차단기 조작시험","2020-05-08 09:30","2020-05-08 12:00","2020-05-08 09:30","2020-05-08 12:00","연속"]
[366,"전북","김제","김제칠보HP T/L","154kV 정공, 칠보, 김제 분기T/L OPGW 증설공사","가공지선 철거 후 OPGW 교체 및 항공구 정비","2020-05-06 07:00","2020-05-08 18:00","2020-05-06 07:00","2020-05-08 18:00","연속"]
[367,"전북","김제","백산김제#1 T/L","154kV 정공, 칠보, 김제 분기 T/L OPGW 증설공사","가공지선 철거 후 OPGW 교체 및 항공구 정비","2020-05-06 07:00","2020-05-08 18:00","2020-05-06 07:00","2020-05-08 18:00","연속"]
[368,"전북","김제","신김제남전주#1 T/L","김제P/O 170kV GIS 정밀점검공사","154kV GIS 내부점검 전자변 교체 등","2020-05-25 09:30","2020-05-27 18:00","2020-05-25 09:30","2020-05-27 18:00","연속"]
[369,"전북","김제","신김제남전주#2 T/L","김제P/O 170kV GIS 정밀점검공사","154kV GIS 내부점검 전자변 교체 등","2020-05-28 09:30","2020-05-30 18:00","2020-05-28 09:30","2020-05-30 18:00","연속"]
[370,"전북","김제","신김제동전주#1 T/L","154kV 남전주-임실T/L OPGW 증설공사","가공지선 철거후 OPGW 교체(38km) 및 항공구 정비","2020-05-08 09:00","2020-05-09 18:00","취소","취소","연속"]
[371,"전북","김제","신김제동전주#2 T/L","154kV 남전주-임실T/L OPGW 증설공사","가공지선 철거후 OPGW 교체(38km) 및 항공구 정비","2020-05-06 09:00","2020-05-07 18:00","취소","취소","연속"]
[372,"전북","김제","정공칠보HP T/L","154kV 정공, 칠보, 김제 분기 T/L OPGW 증설공사","가공지선 철거 후 OPGW 교체 및 항공구 정비","2020-05-11 07:00","2020-05-28 18:00","2020-05-12 07:00","2020-05-29 18:00","연속"]
[373,"전북","김제","정공정주#1 T/L","154kV 정공, 칠보, 김제 분기 T/L OPGW 증설공사","가공지선 철거 후 OPGW 교체 및 항공구 정비","2020-05-25 07:00","2020-05-28 18:00","2020-05-19 07:00","2020-05-22 18:00","연속"]
[374,"전북","김제","정주부안#2 T/L","345kV 신김제-한빛#1T/L 전력선 교체공사","신김제-한빛#1T/L No.141~142 철탑횡단개소로 안전이격거리 확보차 양회선 휴전","2020-05-30 08:00","2020-06-02 18:00","취소","취소","매일"]
[375,"전북","김제","정주부안#1 T/L","345kV 신김제-한빛#1T/L 전력선 교체공사","신김제-한빛#1T/L No.141~142 철탑횡단개소로 안전이격거리 확보차 양회선 휴전","2020-05-30 08:00","2020-06-02 18:00","취소","취소","매일"]
[376,"전북","직할","무주용담수력 T/L","`20~`21년 전북본부 직할 변전정비회사 총액공사","[무주S/S] 154kV 무주-용담수력T/L 차단기 조작시험, LA점검","2020-05-15 10:00","2020-05-15 18:00","2020-05-15 10:00","2020-05-15 18:00","연속"]
[377,"전북","직할","팔봉봉동#1 T/L","관내 154kV 이상 차단기 점검공사","봉동SS 팔봉-봉동#1T/L 차단기 조작시험","2020-05-11 10:00","2020-05-11 14:00","2020-05-04 10:00","2020-05-04 14:00","연속"]
[378,"전북","직할","팔봉봉동#2 T/L","관내 154kV 이상 차단기 점검공사","봉동SS 팔봉-봉동#2T/L 차단기 조작시험","2020-05-11 14:00","2020-05-11 18:00","2020-05-04 14:00","2020-05-04 18:00","연속"]
[379,"전북","직할","북전주봉동#1 T/L","관내 154kV 이상 차단기 점검공사","봉동SS 북전주-봉동#1T/L 차단기 조작시험 북전주SS 북전주-봉동#1T/L 차단기 조작시험/ 전자변교체","2020-05-12 10:00","2020-05-12 18:00","2020-05-12 10:00","2020-05-12 18:00","연속"]
[380,"전북","직할","북전주진안 T/L","`20~`21년 전북본부 직할 변전정비회사 총액공사","[북전주S/S] 154kV 북전주-진안T/L 차단기 조작시험, CVT점검 [진안S/S] 154kV 북전주-진안T/L 차단기 조작시험, LA점검","2020-05-14 10:00","2020-05-14 18:00","2020-05-14 10:00","2020-05-14 18:00","연속"]
[381,"전북","직할","북전주용담수력 T/L","`20~`21년 전북본부 직할 변전정비회사 총액공사","[북전주S/S] 북전주-용담수력T/L 차단기 조작시험, 히터설치","2020-05-13 10:00","2020-05-13 18:00","2020-05-13 10:00","2020-05-13 18:00","연속"]
[382,"전북","직할","이리전주#2 T/L","154kV 탄소분기 지중T/L 건설공사","- 기설 이리-전주#2T/L 케이블 절단 후 이리-탄소#2T/L 접속","2020-05-23 10:00","2020-06-26 18:00","2020-05-25 10:00","2020-06-12 18:00","연속"]
[383,"광주전남","직할","왕곡나주#2 T/L","154kV 왕곡E/C 토건공사","변전소 내 C/H부지 포장","2020-05-01 08:00","2020-05-05 18:00","2020-05-01 08:00","2020-05-05 18:00","연속"]
[384,"광주전남","직할","평동왕곡#2 T/L","154kV 왕곡E/C 토건공사","변전소 내 C/H부지 포장","2020-05-01 09:00","2020-05-05 18:00","2020-05-01 09:00","2020-05-05 18:00","연속"]
[385,"광주전남","순천","율촌여수산단#2 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치 (C/H No.1)","2020-05-04 09:00","2020-05-04 18:00","2020-05-04 09:00","2020-05-04 18:00","연속"]
[386,"광주전남","강진","삼호S/S 154kV 대불-삼호#1T/L GIS","강진전력지사 170kV GIS 정밀점검 공사","- 삼호S/S 대불-삼호#1T/L GIS 정밀점검","2020-05-06 09:00","2020-05-08 18:00","2020-05-06 09:00","2020-05-08 18:00","연속"]
[387,"광주전남","순천","율촌여수산단#1 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치 (C/H No.1)","2020-05-06 09:00","2020-05-06 18:00","2020-05-06 09:00","2020-05-06 18:00","연속"]
[388,"광주전남","직할","왕곡나주#1 T/L","왕곡 변전기자재 실증시험장 신축공사","○시스템 비계 해체, 정리, 반출작업","2020-05-06 09:00","2020-05-20 18:00","2020-05-07 09:00","2020-05-21 18:00","연속"]
[389,"광주전남","직할","평동왕곡#1 T/L","왕곡 변전기자재 실증시험장 신축공사","○시스템비계 해체, 정리, 반출작업","2020-05-06 09:00","2020-05-20 18:00","2020-05-07 09:00","2020-05-21 18:00","연속"]
[390,"광주전남","광주","신광주계림#1 T/L","20년 광주변전총액공사(신광주계림#1T/L)","계림S/S 신광주계림#1T/L GIS장기미동작 차단기 점검, 신광주S/S 신광주계림#1T/L LA 초기점검","2020-05-11 09:30","2020-05-11 18:00","2020-05-11 09:30","2020-05-11 13:00","연속"]
[391,"광주전남","광주","신광주계림#2 T/L","20년 광주변전총액공사(신광주계림#2T/L)","계림S/S 신광주계림#2T/L GIS장기미동작 차단기 점검, 신광주S/S 신광주계림#2T/L LA 초기점검","2020-05-07 09:30","2020-05-07 13:00","2020-05-11 13:00","2020-05-11 18:00","연속"]
[392,"광주전남","순천","호남TP여수TP#2 T/L","20-21년 순천전력지사 송전정비회사 총액공사","154kV 호남TP-여수TP#2T/L 애자교체 - 애자교체 1기(6호)","2020-05-07 08:00","2020-05-07 18:00","2020-05-13 08:00","2020-05-13 18:00","연속"]
[393,"광주전남","광주","북광주계림#1 T/L","20년 광주변전총액공사(북광주계림#1T/L)","계림S/S 북광주계림#1T/L GIS장기미동작 차단기 점검","2020-05-12 09:30","2020-05-12 18:00","2020-05-12 09:30","2020-05-12 13:00","연속"]
[394,"광주전남","광주","북광주계림#2 T/L","20년 광주변전총액공사(북광주계림#2T/L)","계림S/S 북광주계림#2T/L GIS장기미동작 차단기 점검","2020-05-07 13:00","2020-05-07 18:00","2020-05-12 13:00","2020-05-12 18:00","연속"]
[395,"광주전남","순천","서순천주암HP T/L","20-21년 순천전력지사 송전정비회사 총액공사","154kV 서순천-주암HP T/L 전선접속개소해소 -전력선 교체(12~13호간 하단)","2020-05-08 09:00","2020-05-08 18:00","2020-05-06 09:00","2020-05-06 18:00","연속"]
[396,"광주전남","순천","여천호남TP#2 T/L","345kV 광양CC-신여수T/L 건설공사","154kV 여천-호남TP T/L 가선로 구성공사 - 공 사 명 : 345kV 광양CC-신여수T/L 건설공사 - 공사개요 : 철탑 1기 신설 및 철거(No.7) - 전선이동 : 2기 - 시공사/감리사 : 세종텔레콤/한국코아엔지니어링","2020-05-11 07:00","2020-05-13 18:00","2020-05-25 07:00","2020-05-27 18:00","연속"]
[397,"광주전남","광주","일곡비아#1 T/L","2020년 가공송전 순시점검 위탁공사","154kV 일곡-비아T/L 13호 C/H 초기점검","2020-05-11 09:00","2020-05-11 18:00","2020-05-06 11:00","2020-05-06 16:00","연속"]
[398,"광주전남","강진","삼호S/S 154kV 대불-삼호#2T/L GIS","강진전력지사 170kV GIS 정밀점검 공사","- 삼호S/S 대불-삼호#2T/L GIS 정밀점검","2020-05-13 13:00","2020-05-15 18:00","2020-05-13 13:00","2020-05-15 18:00","연속"]
[399,"광주전남","순천","여천호남TP#1 T/L","345kV 광양CC-신여수T/L 건설공사","154kV 여천-호남TP T/L 가선로 구성공사 - 공 사 명 : 345kV 광양CC-신여수T/L 건설공사 - 공사개요 : 철탑 1기 신설 및 철거(No.7) - 전선이동 : 2기 - 시공사/감리사 : 세종텔레콤/한국코아엔지니어링","2020-05-14 07:00","2020-05-16 18:00","2020-05-28 07:00","2020-05-30 18:00","연속"]
[400,"광주전남","순천","용성여수산단#1 T/L","일진제 170kV GIS 유사고장 조치공사 및 정밀점검","용성S/S #60BUS 무부하가압 선로","2020-05-14 15:00","2020-05-15 15:00","2020-05-14 15:00","2020-05-15 15:00","연속"]
[401,"광주전남","강진","신화순나주#1 T/L","20-21년 강진전력지사 변전정비회사 총액공사","나주S/S 신화순-나주#1,2T/L GIS 초기점검","2020-05-15 10:00","2020-05-15 14:00","2020-05-15 10:00","2020-05-15 14:00","연속"]
[402,"광주전남","강진","신화순나주#2 T/L","20-21년 강진전력지사 변전정비회사 총액공사","나주S/S 신화순-나주#1,2T/L GIS 초기점검","2020-05-15 14:00","2020-05-15 18:00","2020-05-15 14:00","2020-05-15 18:00","연속"]
[403,"광주전남","순천","여수소라#1 T/L","154kV 여수소라#1 T/L 정밀점검","20년 가공송전 순시점검 위탁공사","2020-05-18 08:00","2020-05-19 18:00","2020-05-18 08:00","2020-05-19 18:00","매일"]
[404,"광주전남","강진","삼호S/S 154kV 삼호-화원#1T/L GIS","강진전력지사 170kV GIS 정밀점검 공사","- 삼호S/S 삼호-화원#1T/L GIS 정밀점검","2020-05-18 09:00","2020-05-20 12:00","2020-05-18 09:00","2020-05-20 12:00","연속"]
[405,"광주전남","순천","여수소라#2 T/L","154kV 여수소라#2 T/L 정밀점검","20년 가공송전 순시점검 위탁공사","2020-05-20 08:00","2020-05-21 18:00","2020-05-20 08:00","2020-05-21 18:00","매일"]
[406,"광주전남","강진","삼호S/S 154kV 삼호-화원#2T/L GIS","강진전력지사 170kV GIS 정밀점검 공사","- 삼호S/S 삼호-화원#2T/L GIS 정밀점검","2020-05-20 13:00","2020-05-22 18:00","2020-05-20 13:00","2020-05-22 18:00","연속"]
[407,"광주전남","강진","신강진대불#1 T/L","20-21년 강진전력지사 변전정비회사 총액공사","신강진S/S 신강진-대불#1,2T/L GIS, LA 하자점검","2020-05-21 10:00","2020-05-21 14:00","2020-05-21 10:00","2020-05-21 14:00","연속"]
[408,"광주전남","강진","신강진대불#2 T/L","20-21년 강진전력지사 변전정비회사 총액공사","신강진S/S 신강진-대불#1,2T/L GIS, LA 하자점검","2020-05-21 14:00","2020-05-21 18:00","2020-05-21 14:00","2020-05-21 18:00","연속"]
[409,"광주전남","순천","용성여수산단#1 T/L","일진제 170kV GIS 유사고장 조치공사 및 정밀점검","용성S/S #65BUS 무부하가압 선로","2020-05-21 15:00","2020-05-22 15:00","2020-05-21 15:00","2020-05-22 15:00","연속"]
[410,"광주전남","직할","하남평동#2 T/L","154kV 덕림분기T/L 건설공사","가) 공사구간 : 154kV 하남-평동T/L 기설No.7 ~ 덕림분기No.1(기설No.8)~기설No.11 나) 휴전작업 공사구간 154kV 하남-평동T/L 기설No.7 ~ 덕림분기No.1[하단](기설No.8)~기설 No.11 다) 전력선종 : ACSR 410㎟ * 2B * 2C 라) 선로길이 : 1.152km","2020-05-23 08:00","2020-05-25 18:00","2020-05-23 08:00","2020-05-25 18:00","연속"]
[411,"광주전남","직할","하남평동#1 T/L","154kV 덕림분기 T/L 건설공사","가) 공사구간 : 154kV 하남-평동T/L 기설No.7 ~ 덕림분기No.1(기설No.8)~기설No.11 나) 휴전작업 공사구간 154kV 하남-평동T/L 기설No.7 ~ 덕림분기No.1[하단](기설No.8)~기설 No.11 다) 전력선종 : ACSR 410㎟ * 2B * 2C 라) 선로길이 : 1.152km","2020-05-23 08:00","2020-05-28 18:00","2020-05-23 08:00","2020-05-28 18:00","연속"]
[412,"광주전남","순천","승주S/S 154kV 순천-승주#1T/L GIS","20년 상반기 순천전력지사 170kV GIS 정밀점검공사","순천-승주#1T/L 정밀점검","2020-05-25 09:00","2020-05-26 18:00","2020-05-07 09:00","2020-05-08 18:00","연속"]
[413,"광주전남","순천","고흥S/S 154kV 고흥솔라파크 T/L GIS","20-21년 순천전력지사 변전정비회사 총액공사","솔라파크T/L GIS 보통점검","2020-05-27 09:00","2020-05-27 18:00","2020-05-27 09:00","2020-05-27 18:00","연속"]
[414,"광주전남","광주","신화순S/S #1EM.Tr CB","20년 광주전력지사 170kV GIS 정밀점검공사(ESS소내전원공급목적)","신화순S/S #3M.Tr 휴전관련 → ESS 소내전원 확보용 : #1ES.Tr 가압 용도","2020-05-28 09:00","2020-05-29 18:00","2020-05-28 09:00","2020-05-29 18:00","연속"]
[415,"광주전남","순천","승주S/S 154kV 순천-승주#2T/L GIS","20년 상반기 순천전력지사 170kV GIS 정밀점검공사","순천-승주#2T/L 정밀점검","2020-05-28 09:00","2020-05-29 18:00","2020-05-11 09:00","2020-05-12 18:00","연속"]
[416,"대구","경산","신경산노변 T/L","시지S/S 건설공사","- 15/20 MVAR * 3대 * 2BANK 설치 - 170kV 10CCT 설치 - 25.8kV 11CCT 설치 - 기타 부대공사","2020-05-27 09:00","2020-05-29 18:00","2020-05-27 09:00","2020-05-29 18:00","연속"]
[417,"대구","경산","진량노변 T/L","시지S/S 건설공사","- 15/20 MVAR * 3대 * 2BANK 설치 - 170kV 10CCT 설치 - 25.8kV 11CCT 설치 - 기타 부대공사","2020-05-07 09:00","2020-05-13 18:00","2020-05-07 09:00","2020-05-13 18:00","연속"]
[418,"대구","경산","청도밀양#1 T/L","20~21년 달성 송전정비회사 총액공사","항공장애표시구 설치공사(안전 이격)","2020-05-30 14:00","2020-05-30 18:00","2020-05-30 14:00","2020-05-30 18:00","연속"]
[419,"대구","경산","청도밀양#2 T/L","20~21년 달성 송전정비회사 총액공사","항공장애표시구 설치공사(안전 이격)","2020-05-30 07:30","2020-05-30 14:00","2020-05-30 07:30","2020-05-30 14:00","연속"]
[420,"대구","경산","청통와촌#2 T/L","20년 상반기 경산P/O 170kV GIS 정밀점검","- 6333 GIS 무부하가압용 테스트선로","2020-05-02 17:00","2020-05-02 18:00","취소","취소","연속"]
[421,"대구","경산","청통S/S 154kV #2 BUS","20년 상반기 경산P/O 170kV GIS 정밀점검","- 6333 GIS 무부하가압용","2020-05-02 17:00","2020-05-02 18:00","취소","취소","연속"]
[422,"대구","경산","청통와촌#2 T/L","20년 상반기 경산P/O 170kV GIS 정밀점검","- 667 GIS 전자변교체","2020-05-25 09:00","2020-05-25 18:00","취소","취소","연속"]
[423,"대구","경산","청통와촌#1 T/L","20년 상반기 경산P/O 170kV GIS 정밀점검","- 677 GIS 전자변교체","2020-05-22 09:00","2020-05-22 18:00","취소","취소","연속"]
[424,"대구","경산","청통S/S 154kV #2 BUS","20년 상반기 경산P/O 170kV GIS 정밀점검","- 6333 GIS 무부하가압용","2020-05-02 17:00","2020-05-02 18:00","취소","취소","연속"]
[425,"대구","달성","고령쌍림#1 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-05-11 09:00","2020-05-11 11:00","취소","취소","연속"]
[426,"대구","달성","고령논공#2 T/L","고령S/S 고령-논공#2T/L GIS 정밀점검[DS포함]","고령S/S 고령-논공#2T/L GIS 정밀점검[DS포함]","2020-05-01 09:00","2020-05-03 18:00","2020-05-01 09:00","2020-05-03 18:00","연속"]
[427,"대구","달성","고령다산#1 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-05-11 14:00","2020-05-11 17:00","취소","취소","연속"]
[428,"대구","달성","고령다산#2 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-05-12 08:00","2020-05-16 18:00","취소","취소","연속"]
[429,"대구","달성","고령쌍림#2 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-05-12 08:00","2020-05-17 18:00","취소","취소","연속"]
[430,"대구","달성","고령S/S 154kV #66 BUS","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-05-15 17:00","2020-05-15 18:00","취소","취소","연속"]
[431,"대구","달성","고령S/S 154kV #65 BUS","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-05-15 18:00","2020-05-16 18:00","취소","취소","연속"]
[432,"대구","달성","고령쌍림#1 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-05-17 08:00","2020-05-21 18:00","취소","취소","연속"]
[433,"대구","달성","고령다산#1 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-05-17 08:00","2020-05-21 18:00","취소","취소","연속"]
[434,"대구","달성","고령S/S 154kV #61 BUS","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-05-20 17:00","2020-05-20 18:00","취소","취소","연속"]
[435,"대구","달성","고령S/S 154kV #60 BUS","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-05-20 18:00","2020-05-21 18:00","취소","취소","연속"]
[436,"대구","달성","고령쌍림#2 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-05-11 11:00","2020-05-11 14:00","취소","취소","연속"]
[437,"대구","달성","논공달성#1 T/L","달성S/S 논공-달성#1T/L 보통점검","달성S/S 논공-달성#1T/L 보통점검","2020-05-29 09:00","2020-05-29 14:00","2020-05-29 09:00","2020-05-29 14:00","연속"]
[438,"대구","달성","논공달성#2 T/L","달성S/S 논공-달성#2T/L 보통점검","달성S/S 논공-달성#2T/L 보통점검","2020-05-29 14:00","2020-05-29 18:00","2020-05-29 14:00","2020-05-29 18:00","연속"]
[439,"대구","달성","대구청도#2 T/L","20~21년 달성 송전정비회사 총액공사","항공장애표시구 설치공사(안전 이격)","2020-05-30 14:00","2020-05-30 18:00","2020-05-30 14:00","2020-05-30 18:00","연속"]
[440,"대구","달성","대구범물#1 T/L","2020년 가공송전선로 순시점검 위탁공사","154kV 대구-범물#1T/L 아킹혼 간격조정","2020-05-21 08:00","2020-05-21 18:00","2020-05-21 08:00","2020-05-21 18:00","연속"]
[441,"대구","달성","대구청도#1 T/L","20~21년 달성 송전정비회사 총액공사","항공장애표시구 설치공사(안전 이격)","2020-05-30 07:30","2020-05-30 14:00","2020-05-30 07:30","2020-05-30 14:00","연속"]
[442,"대구","달성","상인봉덕#1 T/L","봉덕S/S 상인-봉덕#1T/L 전자변교체","봉덕S/S 상인-봉덕#1T/L 전자변교체","2020-05-14 09:00","2020-05-14 18:00","2020-05-14 09:00","2020-05-14 18:00","연속"]
[443,"대구","달성","서구지E/C 154kV #60-61 BUS SEC GIS","서구지S/S #60-#61 BUS SEC 초기점검","서구지S/S #60-#61 BUS SEC 초기점검","2020-05-14 09:00","2020-05-14 13:00","취소","취소","연속"]
[444,"대구","달성","서구지E/C 154kV #65-66 BUS SEC GIS","서구지S/S #65-#66 BUS SEC 초기점검","서구지S/S #65-#66 BUS SEC 초기점검","2020-05-14 13:00","2020-05-14 18:00","취소","취소","연속"]
[445,"대구","달성","쌍림합천#2 T/L","쌍림S/S 쌍림-합천#2T/L 정밀점검[DS포함]","쌍림S/S 쌍림-합천#2T/L 정밀점검[DS포함]","2020-05-18 09:00","2020-05-20 18:00","2020-05-18 09:00","2020-05-20 18:00","연속"]
[446,"대구","달성","고령쌍림#1 T/L","쌍림S/S #60-#65 BUS TIE 정밀점검[TEST 선로]","쌍림S/S #60-#65 BUS TIE 정밀점검[TEST 선로]","2020-05-15 13:00","2020-05-16 18:00","2020-05-15 13:00","2020-05-16 18:00","매일"]
[447,"대구","달성","고령쌍림#2 T/L","쌍림S/S 고령-쌍림#2T/L 정밀점검[DS포함]","쌍림S/S 고령-쌍림#2T/L 정밀점검[DS포함]","2020-05-11 09:00","2020-05-13 18:00","2020-05-11 09:00","2020-05-13 18:00","연속"]
[448,"대구","직할","공평서침산 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2020-05-20 09:00","2020-05-21 18:00","2020-05-20 09:00","2020-05-21 18:00","연속"]
[449,"대구","직할","효목안심#2 T/L","시지S/S 건설공사","- 15/20 MVAR * 3대 * 2BANK 설치 - 170kV 10CCT 설치 - 25.8kV 11CCT 설치 - 기타 부대공사","2020-05-27 09:00","2020-05-27 18:00","취소","취소","연속"]
[450,"대구","직할","효목안심#1 T/L","시지S/S 건설공사","- 15/20 MVAR * 3대 * 2BANK 설치 - 170kV 10CCT 설치 - 25.8kV 11CCT 설치 - 기타 부대공사","2020-05-07 09:00","2020-05-07 18:00","취소","취소","연속"]
[451,"대구","칠곡","TAK 1공장 T/L GIS","광평S/S TAK 1공장 T/L 170GIS 보통점검","광평S/S TAK 1공장 T/L 170GIS 보통점검","2020-03-28 09:00","2020-03-28 17:00","취소","취소","연속"]
[452,"대구","칠곡","남구미광평#2 T/L","광평S/S 6233GIS 차단부 정밀점검 무부하가압","광평S/S 6233GIS 차단부 정밀점검 무부하가압","2020-05-07 13:00","2020-05-07 18:00","2020-05-07 13:00","2020-05-07 18:00","연속"]
[453,"대구","칠곡","광평S/S 154kV #2 BUS","광평S/S 6233GIS 차단부 정밀점검 무부하가압","광평S/S 6233GIS 차단부 정밀점검 무부하가압","2020-05-07 13:00","2020-05-07 18:00","취소","취소","연속"]
[454,"대구","칠곡","TAK 1공장 T/L GIS","광평S/S TAK 1공장 T/L 170GIS 보통점검","광평S/S TAK 1공장 T/L 170GIS 보통점검","2020-05-16 09:00","2020-05-16 17:00","취소","취소","연속"]
[455,"대구","칠곡","북대구구암#1 T/L","154kV 관음-구암T/L 지장송전선로 이설공사","관음-구암T/L 31~34호 철거/설치관련 안전확보(하단횡단)","2020-05-25 07:30","2020-05-29 18:30","2020-05-25 07:30","2020-05-29 18:30","매일"]
[456,"대구","칠곡","북대구구암#2 T/L","154kV 관음-구암T/L 지장송전선로 이설공사","관음-구암T/L 31~34호 철거/설치관련 안전확보(하단 횡단)","2020-05-25 07:30","2020-05-29 18:30","2020-05-25 07:30","2020-05-29 18:30","매일"]
[457,"대구","포항","신영일천북#2 T/L","345kV 신포항-북대구T/L 전력선교체공사(안전확보)","345kV 신포항-북대구T/L 전력선교체공사 공사구간 : 345kV 신포항-북대구T/L No.202~205, 208~219, 265~272 전력선교체 : ACSR 480㎟*4B*2C, 14.645C_km 가공지선교체 : ACSR 120㎟ 7.623C_km","2020-05-14 07:00","2020-05-20 18:00","2020-05-14 07:00","2020-05-20 18:00","매일"]
[458,"대구","포항","신영일천북#1 T/L","345kV 신포항-북대구T/L 전력선교체공사(안전확보)","345kV 신포항-북대구T/L 전력선교체공사 공사구간 : 345kV 신포항-북대구T/L No.202~205, 208~219, 265~272 전력선교체 : ACSR 480㎟*4B*2C, 14.645C_km 가공지선교체 : ACSR 120㎟ 7.623C_km","2020-05-14 07:00","2020-05-20 18:00","2020-05-14 07:00","2020-05-20 18:00","매일"]
[459,"대구","포항","상정영일 T/L","345kV 신포항-북대구T/L 전력선교체공사(안전확보)","345kV 신포항-북대구T/L 전력선교체공사 공사구간 : 345kV 신포항-북대구T/L No.202~205, 208~219, 265~272 전력선교체 : ACSR 480㎟*4B*2C, 14.645C_km 가공지선교체 : ACSR 120㎟ 7.623C_km","2020-05-07 07:00","2020-05-13 18:00","2020-05-07 07:00","2020-05-13 18:00","매일"]
[460,"대구","포항","영일입실 T/L","345kV 신포항-북대구T/L 전력선교체공사(안전확보)","345kV 신포항-북대구T/L 전력선교체공사 공사구간 : 345kV 신포항-북대구T/L No.202~205, 208~219, 265~272 전력선교체 : ACSR 480㎟*4B*2C, 14.645C_km 가공지선교체 : ACSR 120㎟ 7.623C_km","2020-05-07 07:00","2020-05-13 18:00","2020-05-07 07:00","2020-05-13 18:00","매일"]
[461,"대구","포항","청하영덕#2 T/L","154kV 청하-영덕T/L 접속개소 전력선교체공사","154kV 청하-영덕T/L 접속개소 전력선교체공사 ○ 공사구간 : 154kV 청하-영덕 T/L 80∼96호, 116∼128호 ○ 공사내용 : 전력선 교체 ACSR 410㎟*2B*2C, 10.786C_km","2020-05-26 07:00","2020-06-09 18:00","2020-05-26 07:00","2020-06-09 18:00","연속"]
[462,"대구","포항","청하영덕#1 T/L","154kV 청하-영덕T/L 접속개소 전력선교체공사","154kV 청하-영덕T/L 접속개소 전력선교체공사 ○ 공사구간 : 154kV 청하-영덕 T/L 80∼96호, 116∼128호 ○ 공사내용 : 전력선 교체 ACSR 410㎟*2B*2C, 10.786C_km","2020-05-11 07:00","2020-05-25 18:00","2020-05-11 07:00","2020-05-25 18:00","연속"]
[463,"경북","구미","구미광평#2 T/L","2020-21년 구미전력지사 변전정비업체 총액공사","- 154kV 모선보호반 대체공사","2020-05-21 13:30","2020-05-21 14:00","2020-05-21 13:30","2020-05-21 14:00","연속"]
[464,"경북","구미","구미광평#1 T/L","2020-21년 구미전력지사 변전정비업체 총액공사","- 154kV 모선보호반 대체공사","2020-05-21 13:00","2020-05-21 13:30","2020-05-21 13:00","2020-05-21 13:30","연속"]
[465,"경북","구미","동상주개폐소 154kV 동상주-점촌#1T/L GIS","2020-21년 구미전력지사 변전정비업체 총액공사","GIS초기점검, 세니온제 송전선로 보호IED 성능개선","2020-05-15 09:00","2020-05-15 14:00","2020-05-15 09:00","2020-05-15 14:00","연속"]
[466,"경북","구미","동상주개폐소 154kV 동상주-점촌#2T/L GIS","2020-21년 구미전력지사 변전정비업체 총액공사","GIS초기점검, 세니온제 송전선로 보호IED 성능개선","2020-05-15 14:00","2020-05-15 18:00","2020-05-15 14:00","2020-05-15 18:00","연속"]
[467,"경북","구미","선산청리#1 T/L","154kV 선산-청리분기-상주 T/L OPGW 교체공사","154kV 선산변전소-선산청리분기, 선산청리분기-상주No.49까지 OPGW 교체(약 34km)","2020-05-19 09:00","2020-05-26 18:00","2020-05-19 09:00","2020-05-26 18:00","연속"]
[468,"경북","구미","선산청리#2 T/L","154kV 선산-청리분기-상주 T/L OPGW 교체공사","154kV 선산변전소-선산청리분기, 선산청리분기-상주No.49까지 OPGW 교체(약 34km)","2020-05-07 09:00","2020-05-14 18:00","2020-05-07 09:00","2020-05-14 18:00","연속"]
[469,"경북","구미","청리상주#2 T/L","154kV 선산-청리분기-상주 T/L OPGW 교체공사","154kV 선산변전소-선산청리분기, 선산청리분기-상주No.49까지 OPGW 교체(약 34km)","2020-05-23 09:00","2020-05-24 18:00","2020-05-23 09:00","2020-05-24 18:00","연속"]
[470,"경북","직할","영덕진보#1 T/L","154kV 영덕-진보#1T/L 전선교체공사","154kV 영덕-진보#1T/L 전선교체공사","2020-05-06 09:00","2020-05-14 18:00","취소","취소","연속"]
[471,"경북","직할","영덕진보#2 T/L","154kV 영덕-진보#2T/L 전선교체공사","154kV 영덕-진보#2T/L 전선교체공사","2020-05-18 09:00","2020-05-26 18:00","취소","취소","연속"]
[472,"경북","직할","현종산풍력평해#2 T/L","154kV 평해S/S 옥외철구설비 현대화 공사","○현종산풍력-평해#2T/L 휴전 - 154kV 모선재 재단 및 설치, 철구 철거 등","2020-05-20 09:00","2020-05-20 18:00","2020-05-20 09:00","2020-05-20 18:00","연속"]
[473,"부산울산","동부산","구서명장#2 T/L","압축인류크램프 정비","154kV 신양산-구서#2T/L 작업관련 안전이격확보용 휴전","2020-05-01 08:00","2020-05-04 18:00","2020-05-01 08:00","2020-05-04 18:00","연속"]
[474,"부산울산","동부산","구서노포#1 T/L","구서S/S 154kV GIS 차단기 동작시험","구서S/S 154kV GIS 차단기 동작시험(구서-노포#1T/L)","2020-05-13 09:30","2020-05-13 14:00","2020-05-13 09:30","2020-05-13 14:00","연속"]
[475,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 154kV GIS 정밀점검공사","서창S/S 154kV 6133 GIS 정밀점검 관련 시험가압","2020-05-26 17:00","2020-05-26 18:00","취소","취소","연속"]
[476,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 154kV GIS 정밀점검공사","서창S/S 154kV 637 GIS 정밀점검 관련 시험가압","2020-05-28 09:00","2020-05-30 18:00","2020-05-28 09:00","2020-05-30 18:00","연속"]
[477,"부산울산","동부산","서창산막#1 T/L","서창S/S 154kV GIS 정밀점검공사","서창S/S 154kV GIS 정밀점검공사(서창-산막#1T/L)","2020-05-05 09:00","2020-05-05 18:00","2020-05-05 09:00","2020-05-05 18:00","연속"]
[478,"부산울산","동부산","웅촌서창#2 T/L","서창S/S 154kV GIS 정밀점검공사","서창S/S 154kV 6233 GIS 정밀점검 관련 시험가압","2020-05-20 17:00","2020-05-20 18:00","취소","취소","연속"]
[479,"부산울산","동부산","웅촌서창#2 T/L","서창S/S 154kV GIS 정밀점검공사","서창S/S 154kV 6133 GIS 정밀점검 관련 시험가압","2020-05-27 17:00","2020-05-27 18:00","취소","취소","연속"]
[480,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 154kV GIS 정밀점검공사","서창S/S 154kV 6233 GIS 정밀점검 관련 시험가압","2020-05-19 17:00","2020-05-19 18:00","취소","취소","연속"]
[481,"부산울산","동부산","신양산기장#1 T/L","[7차] 345kV 신양산S/S 현대화공사","1. 내용 - 신양산-고리NP#1T/L 제어케이블 이설 - 345kV #4M.Tr 및 1,2,3차 제어케이블 이설 - 345kV #4M.Tr 2차 인출변경 - 154kV 신양산-기장#1T/L 인출변경","2020-05-20 09:00","2020-06-02 18:00","2020-05-20 09:00","2020-06-02 18:00","연속"]
[482,"부산울산","동부산","신양산구서#2 T/L","[4차] 345kV 신양산S/S 현대화공사","1. 내용 - 154kV 신양산-구서#2T/L 인출변경","2020-05-01 09:00","2020-05-06 18:00","2020-05-01 09:00","2020-05-06 18:00","연속"]
[483,"부산울산","동부산","수영우동 T/L","우동S/S 154kV GIS 보통점검","우동S/S 154kV GIS 보통점검(수영-우동T/L)","2020-05-14 09:30","2020-05-14 17:00","2020-05-14 09:30","2020-05-14 17:00","연속"]
[484,"부산울산","북부산","김해S/S 154kV #60-#65 BUS TIE CB","20-21 북부산전력지사 변전총액공사","김해S/S 154kV BUS-TIE(6100) GIS 차단기 동작시험","2020-05-21 10:00","2020-05-21 14:00","2020-05-21 10:00","2020-05-21 14:00","연속"]
[485,"부산울산","북부산","매리김해#1 T/L","2020 북부산전력지사 154kV GIS 정밀점검","김해S/S 154kV #2M.Tr 1차(6233)GIS 정밀점검 ( 2DS부 시험가압(1h) : 154kV 매리-김해#1T/L)","2020-05-20 17:00","2020-05-20 18:00","2020-05-20 17:00","2020-05-20 18:00","연속"]
[486,"부산울산","북부산","김해S/S 154kV #65 BUS","2020 북부산전력지사 154kV GIS 정밀점검","김해S/S 154kV #2M.Tr 1차(6233)GIS 정밀점검 (#2BUS 휴전)","2020-05-19 14:00","2020-05-20 17:00","2020-05-19 14:00","2020-05-20 17:00","연속"]
[487,"부산울산","북부산","매리김해#1 T/L","2020 북부산전력지사 154kV GIS 정밀점검","김해S/S 154kV #2M.Tr 1차(6233)GIS 정밀점검 ( 1DS부 시험가압(1h) : 154kV 매리-김해#1T/L)","2020-05-19 13:00","2020-05-19 14:00","2020-05-19 13:00","2020-05-19 14:00","연속"]
[488,"부산울산","북부산","김해S/S 154kV #60 BUS","2020 북부산전력지사 154kV GIS 정밀점검","김해S/S 154kV #2M.Tr 1차(6233)GIS 정밀점검 ( #1BUS 휴전)","2020-05-18 09:00","2020-05-19 13:00","2020-05-18 09:00","2020-05-19 13:00","연속"]
[489,"부산울산","북부산","미남덕포#2 T/L","19-20년 북부산전력지사 지중송전 위탁정비공사","미남-덕포T/L 케이블헤드 점검(덕포C/H)","2020-05-20 13:00","2020-05-20 18:00","2020-05-20 13:00","2020-05-20 18:00","연속"]
[490,"부산울산","북부산","미남덕포#1 T/L","19-20년 북부산전력지사 지중송전 위탁정비공사","미남-덕포T/L 케이블헤드 점검(덕포C/H)","2020-05-20 09:00","2020-05-20 13:00","2020-05-20 09:00","2020-05-20 13:00","연속"]
[491,"부산울산","북부산","호포매리#1 T/L","154kV 호포-매리T/L 24호 변위철탑 정비공사","#2T/L 임시선로 설치(4회선철탑, 매리-김해#1 포함)","2020-05-23 07:00","2020-05-24 18:00","취소","취소","연속"]
[492,"부산울산","북부산","매리김해#1 T/L","154kV 호포-매리T/L 24호 변위철탑 정비공사","#2T/L 임시선로 설치(4회선철탑, 호포-매리#1 포함)","2020-05-23 07:00","2020-05-24 18:00","취소","취소","연속"]
[493,"부산울산","북부산","매리김해#2 T/L","154kV 호포-매리T/L 24호 변위철탑 정비공사","#2T/L 임시선로 설치(4회선철탑, 호포-매리#2 포함)","2020-05-16 07:00","2020-05-17 18:00","취소","취소","연속"]
[494,"부산울산","북부산","호포매리#2 T/L","154kV 호포-매리T/L 24호 변위철탑 정비공사","#2T/L 임시선로 설치(4회선철탑, 매리-김해#2 포함)","2020-05-16 07:00","2020-05-17 18:00","취소","취소","연속"]
[495,"부산울산","북부산","구포모라#1 T/L","20-21 북부산전력지사 변전총액공사","모라S/S 154kV 구포-모라#1T/L GIS 보통점검 및 전자변교체","2020-05-26 10:00","2020-05-26 18:00","2020-05-26 10:00","2020-05-26 18:00","연속"]
[496,"부산울산","북부산","물금삼랑진PP#1 T/L","20-21 북부산전력지사 변전총액공사","물금S/S 154kV 물금-삼랑진#1T/L GIS 보통점검","2020-05-14 10:00","2020-05-14 18:00","2020-05-14 10:00","2020-05-14 18:00","연속"]
[497,"부산울산","북부산","북부산양산 T/L","북부산S/S 154kV 송전선로 인출Bay 조정공사","북부산S/S 154kV 북부산-삼랑진PP T/L 인출Bay 조정공사(2차) (안전이격 확보)","2020-05-07 14:00","2020-05-08 18:00","2020-05-09 08:00","2020-05-09 18:00","연속"]
[498,"부산울산","북부산","북부산S/S 154kV #62-#67 BUS TIE CB","20-21 북부산전력지사 변전총액공사","북부산S/S 154kV #62-#67BUS-TIE (6300) 하자점검","2020-05-04 10:00","2020-05-04 18:00","2020-05-04 10:00","2020-05-04 18:00","연속"]
[499,"부산울산","북부산","북부산S/S 154kV #66 BUS","북부산S/S 154kV 송전선로 인출Bay 조정공사","북부산S/S 154kV 북부산-삼랑진PP T/L 인출Bay 조정공사(2차) - 154kV #66BUS 휴전 (2DS부 설치 시험가압(24h))","2020-05-18 08:00","2020-05-23 16:00","2020-05-18 08:00","2020-05-23 16:00","연속"]
[500,"부산울산","북부산","북부산물금 T/L","북부산S/S 154kV 송전선로 인출Bay 조정공사","북부산S/S 154kV 북부산-삼랑진PP T/L 인출Bay 조정공사(2차) - 154kV #67BUS 시험가압(2h)","2020-05-07 12:00","2020-05-07 14:00","2020-05-08 16:00","2020-05-08 18:00","연속"]
[501,"부산울산","북부산","북부산S/S 154kV #62 BUS","북부산S/S 154kV 송전선로 인출Bay 조정공사","북부산S/S 154kV 북부산-삼랑진PP T/L 인출Bay 조정공사(2차) - (북부산-삼랑진PP T/L 2차 DS 분리)","2020-05-07 14:00","2020-05-09 14:00","2020-05-09 08:00","2020-05-11 18:00","연속"]
[502,"부산울산","북부산","북부산S/S 154kV #61 BUS","북부산S/S 154kV 송전선로 인출Bay 조정공사","북부산S/S 154kV 북부산-삼랑진PP T/L 인출Bay 조정공사(2차) - 154kV #61BUS 휴전 (1DS부 설치)","2020-05-11 08:00","2020-05-15 18:00","2020-05-12 08:00","2020-05-16 18:00","연속"]
[503,"부산울산","북부산","북부산물금 T/L","북부산S/S 154kV 송전선로 인출Bay 조정공사","북부산S/S 154kV 북부산-삼랑진PP T/L 인출Bay 조정공사(2차) - 154kV #62BUS 시험가압(2h)","2020-05-09 12:00","2020-05-09 14:00","2020-05-11 16:00","2020-05-11 18:00","연속"]
[504,"부산울산","북부산","북부산S/S 154kV #61 BUS","북부산S/S 154kV 송전선로 인출Bay 조정공사","북부산S/S 154kV 북부산-삼랑진PP T/L 인출Bay 조정공사(2차) - 154kV #61BUS 휴전 (1DS부 시험가압(2h))","2020-05-23 16:00","2020-05-23 18:00","2020-05-23 16:00","2020-05-23 18:00","연속"]
[505,"부산울산","북부산","북부산양산 T/L","북부산S/S 154kV 송전선로 인출Bay 조정공사","북부산S/S 154kV 북부산-삼랑진PP T/L 인출Bay 조정공사(2차) (안전이격 확보)","2020-05-06 08:00","2020-05-06 18:00","2020-05-06 08:00","2020-05-07 18:00","연속"]
[506,"부산울산","북부산","북부산S/S 154kV #67 BUS","북부산S/S 154kV 송전선로 인출Bay 조정공사","북부산S/S 154kV 북부산-삼랑진PP T/L 인출Bay 조정공사(2차) #67BUS 휴전 - (북부산-삼랑진PP T/L 2DS측 분리)","2020-05-06 08:00","2020-05-07 14:00","2020-05-06 08:00","2020-05-08 18:00","연속"]
[507,"부산울산","북부산","북부산삼랑진PP T/L","북부산S/S 154kV 송전선로 인출Bay 조정공사","북부산S/S 154kV 북부산-삼랑진PP T/L 인출Bay 조정공사(2차)","2020-05-06 08:00","2020-06-05 18:00","2020-05-06 08:00","2020-06-05 18:00","연속"]
[508,"부산울산","북부산","서창산막#1 T/L","154kV 서창-산막T/L 13호 지장철탑 이설공사","- 5/9 ~ 10 : #1T/L 가선로 철거 및 본선로 구성","2020-05-02 07:00","2020-05-03 18:00","2020-05-02 07:00","2020-05-03 18:00","연속"]
[509,"부산울산","북부산","주촌삼계#1 T/L","2020 북부산전력지사 154kV GIS정밀점검","삼계S/S 154kV #3M.Tr 1차(6333) GIS 정밀점검 - 2DS부 시험가압 : 삼계-주촌#1T/L(1h)","2020-05-13 17:00","2020-05-13 18:00","2020-05-13 17:00","2020-05-13 18:00","연속"]
[510,"부산울산","북부산","한림정삼계#2 T/L","2020년도 북부산 가공송전 순시점검 위탁공사","154kV 삼계-어방#1T/L 송전선로 정밀점검(1~51호) 안전확보 휴전","2020-05-22 08:00","2020-05-22 18:00","2020-05-22 08:00","2020-05-22 18:00","연속"]
[511,"부산울산","북부산","주촌삼계#2 T/L","2020년도 북부산 가공송전 순시점검 위탁공사","154kV 삼계-어방#1T/L 송전선로 정밀점검(1~51호) 안전확보 휴전","2020-05-22 08:00","2020-05-22 18:00","2020-05-22 08:00","2020-05-22 18:00","연속"]
[512,"부산울산","북부산","한림정삼계#1 T/L","2020년도 북부산 가공송전 순시점검 위탁공사","154kV 삼계-어방#2T/L 송전선로 정밀점검(1~51호) 안전확보 휴전","2020-05-09 08:00","2020-05-09 18:00","2020-05-09 08:00","2020-05-09 18:00","연속"]
[513,"부산울산","북부산","주촌삼계#1 T/L","2020년도 북부산 가공송전 순시점검 위탁공사","154kV 삼계-어방#2T/L 송전선로 정밀점검(1~51호) 안전확보 휴전","2020-05-09 08:00","2020-05-09 18:00","2020-05-09 08:00","2020-05-09 18:00","연속"]
[514,"부산울산","북부산","삼계어방#2 T/L","2020년도 북부산 가공송전 순시점검 위탁공사","154kV 삼계-어방#2T/L 송전선로 정밀점검(1~51호)","2020-05-09 08:00","2020-05-10 18:00","2020-05-09 08:00","2020-05-10 18:00","매일"]
[515,"부산울산","북부산","주촌삼계#1 T/L","2020 북부산전력지사 154kV GIS정밀점검","삼계S/S 154kV #3M.Tr 1차(6333) GIS 정밀점검 - 1DS부 시험가압 : 삼계-주촌#1T/L(1h)","2020-05-12 13:00","2020-05-12 14:00","취소","취소","연속"]
[516,"부산울산","북부산","삼계S/S 154kV #65 BUS","2020 북부산전력지사 154kV GIS 정밀점검","삼계S/S 154kV #3M.Tr 1차(6333)GIS 정밀점검 - #2BUS 휴전","2020-05-12 14:00","2020-05-13 17:00","2020-05-13 17:00","2020-05-13 18:00","연속"]
[517,"부산울산","북부산","삼계S/S 154kV #60 BUS","2020 북부산전력지사 154kV GIS 정밀점검","삼계S/S 154kV BUS-TIE(6100)GIS 정밀점검 - #1BUS 휴전","2020-05-06 09:00","2020-05-07 13:00","취소","취소","연속"]
[518,"부산울산","북부산","주촌삼계#1 T/L","2020 북부산전력지사 154kV GIS 정밀점검","삼계S/S 154kV BUS-TIE(6100)GIS 정밀점검 (BUS-TIE 6100 1DS측 시험가압)","2020-05-07 13:00","2020-05-07 14:00","취소","취소","연속"]
[519,"부산울산","북부산","삼계S/S 154kV #65 BUS","2020 북부산전력지사 154kV GIS 정밀점검","삼계S/S 154kV BUS-TIE(6100)GIS 정밀점검 (#2BUS 휴전)","2020-05-07 14:00","2020-05-08 17:00","2020-05-06 09:00","2020-05-08 18:00","연속"]
[520,"부산울산","북부산","주촌삼계#1 T/L","2020 북부산전력지사 154kV GIS 정밀점검","삼계S/S 154kV BUS-TIE(6100)GIS 정밀점검 (BUS-TIE 6100 2DS측 시험가압)","2020-05-08 17:00","2020-05-08 18:00","2020-05-08 17:00","2020-05-08 18:00","연속"]
[521,"부산울산","북부산","삼계S/S 154kV #60 BUS","2020 북부산전력지사 154kV GIS 정밀점검","삼계S/S 154kV #3M.Tr 1차(6333)GIS 정밀점검 - #1BUS 휴전","2020-05-11 09:00","2020-05-12 13:00","취소","취소","연속"]
[522,"부산울산","북부산","어방S/S 154kV #65 BUS","2020 북부산전력지사 154kV GIS 정밀점검","어방S/S 154kV BUS-TIE(6100) GIS 정밀점검 (154kV #65BUS 휴전 : 2DS측 작업)","2020-05-29 14:00","2020-05-30 17:00","2020-05-29 14:00","2020-05-30 17:00","연속"]
[523,"부산울산","북부산","김해어방#1 T/L","2020 북부산전력지사 154kV GIS 정밀점검","어방S/S 154kV BUS-TIE(6100) GIS 정밀점검 2DS 측 시험가압 (시험가압선로 : 김해-어방#1T/L)","2020-05-30 17:00","2020-05-30 18:00","2020-05-30 17:00","2020-05-30 18:00","연속"]
[524,"부산울산","북부산","삼계어방#1 T/L","2020년 북부산전력지사 154kV GIS 정밀점검","어방S/S 154kV 삼계-어방#1T/L(627) GIS 정밀점검","2020-05-22 09:00","2020-05-24 18:00","2020-05-22 09:00","2020-05-24 18:00","연속"]
[525,"부산울산","북부산","어방S/S 154kV #60 BUS","2020년 북부산전력지사 154kV GIS 정밀점검","어방S/S 154kV 삼계-어방#1T/L(627) GIS 정밀점검 (#1BUS 휴전 : 1DS 점검)","2020-05-22 09:00","2020-05-23 13:00","2020-05-22 09:00","2020-05-23 13:00","연속"]
[526,"부산울산","북부산","어방S/S 154kV #65 BUS","2020년 북부산전력지사 154kV GIS 정밀점검","어방S/S 154kV 삼계-어방#1T/L(627) GIS 정밀점검 (#2BUS 휴전 : 2DS 점검)","2020-05-23 14:00","2020-05-24 17:00","2020-05-23 14:00","2020-05-24 17:00","연속"]
[527,"부산울산","북부산","김해어방#1 T/L","2020 북부산전력지사 154kV GIS 정밀점검","어방S/S 154kV BUS-TIE(6100) GIS 정밀점검 1DS 측 시험가압 (시험가압선로 : 김해-어방#1T/L)","2020-05-29 13:00","2020-05-29 14:00","2020-05-29 13:00","2020-05-29 14:00","연속"]
[528,"부산울산","북부산","김해어방#1 T/L","2020 북부산전력지사 154kV GIS 정밀점검","어방S/S 154kV 김해-어방#1T/L(617) GIS 정밀점검","2020-05-25 09:00","2020-05-27 18:00","2020-05-25 09:00","2020-05-27 18:00","연속"]
[529,"부산울산","북부산","어방S/S 154kV #65 BUS","2020 북부산전력지사 154kV GIS 정밀점검","어방S/S 154kV 김해-어방#1T/L(617) GIS 정밀점검 (154kV #62BUS 휴전 : 2DS측 작업)","2020-05-26 14:00","2020-05-27 17:00","2020-05-26 14:00","2020-05-27 17:00","연속"]
[530,"부산울산","북부산","어방S/S 154kV #60-#65 BUS TIE CB","2020 북부산전력지사 154kV GIS 정밀점검","어방S/S 154kV BUS-TIE(6100) GIS 정밀점검","2020-05-28 09:00","2020-05-30 18:00","2020-05-28 09:00","2020-05-30 18:00","연속"]
[531,"부산울산","북부산","어방S/S 154kV #60 BUS","2020 북부산전력지사 154kV GIS 정밀점검","어방S/S 154kV BUS-TIE(6100) GIS 정밀점검 (154kV #61BUS 휴전 : 1DS측 작업)","2020-05-28 09:00","2020-05-29 13:00","2020-05-28 09:00","2020-05-29 13:00","연속"]
[532,"부산울산","북부산","어방S/S 154kV #60 BUS","2020 북부산전력지사 154kV GIS 정밀점검","어방S/S 154kV 김해-어방#1T/L(617) GIS 정밀점검 (154kV #61BUS 휴전 : 1DS측 작업)","2020-05-25 09:00","2020-05-26 13:00","2020-05-25 09:00","2020-05-26 13:00","연속"]
[533,"부산울산","서부산","녹공S/S 154kV 용원-녹공#1T/L GIS","녹공S/S 154kV 용원-녹공#1T/L 차단기동작시험","녹공S/S 154kV 용원-녹공#1T/L 차단기동작시험","2020-05-12 10:00","2020-05-12 14:00","2020-05-12 10:00","2020-05-12 14:00","연속"]
[534,"부산울산","서부산","녹공S/S 154kV 용원-녹공#2T/L GIS","녹공S/S 154kV 용원-녹공#2T/L 차단기동작시험","녹공S/S 154kV 용원-녹공#2T/L 차단기동작시험","2020-05-12 14:00","2020-05-12 18:00","2020-05-12 14:00","2020-05-12 18:00","연속"]
[535,"부산울산","서부산","녹산S/S 154kV 신녹산-녹산#1T/L GIS","녹산S/S 154kV 신녹산-녹산#1T/L GIS 보통점검","녹산S/S 154kV 신녹산-녹산#1T/L GIS 보통점검","2020-05-13 10:00","2020-05-13 18:00","2020-05-13 10:00","2020-05-13 18:00","연속"]
[536,"부산울산","서부산","녹산S/S 154kV 신녹산-녹산#2T/L GIS","녹산S/S 154kV 신녹산-녹산#2T/L GIS 보통점검","녹산S/S 154kV 신녹산-녹산#2T/L GIS 보통점검","2020-05-14 10:00","2020-05-14 18:00","2020-05-14 10:00","2020-05-14 18:00","연속"]
[537,"부산울산","서부산","서부산S/S 154kV 서부산-다대#2T/L GIS","서부산S/S 154kV 서부산-다대#2T/L GIS 보통점검","서부산S/S 154kV 서부산-다대#2T/L GIS 보통점검","2020-05-28 10:00","2020-05-28 18:00","2020-05-28 10:00","2020-05-28 18:00","연속"]
[538,"부산울산","서부산","서부산S/S 154kV 서부산-다대#1T/L GIS","서부산S/S 154kV 서부산-다대#1T/L GIS 보통점검","서부산S/S 154kV 서부산-다대#1T/L GIS 보통점검","2020-05-27 10:00","2020-05-27 18:00","2020-05-27 10:00","2020-05-27 18:00","연속"]
[539,"부산울산","서부산","서부산S/S 154kV #2 S/T GIS","서부산S/S 154kV #2S/T T/L 차단기동작시험","서부산S/S 154kV #2S/T T/L 차단기동작시험","2020-05-04 10:00","2020-05-04 18:00","2020-05-04 10:00","2020-05-04 18:00","연속"]
[540,"부산울산","울산","신울산매암#2 T/L","20~21년 변전협력 총액공사","차단기 동작시험 및 전자변 교체","2020-05-04 09:00","2020-05-04 18:00","2020-05-15 09:00","2020-05-15 18:00","연속"]
[541,"부산울산","울산","신울산매암#3 T/L","20~21년 변전협력 총액공사","- 신울산)차단기 동작시험 및 전자변 교체 - 매암)GIS 보통점검","2020-05-01 09:00","2020-05-01 18:00","2020-05-14 09:00","2020-05-14 18:00","연속"]
[542,"부산울산","울산","신온산성암#2 T/L","345kV 신울산복합-북부산T/L 건설공사","-공사내용 : 154kV 신온산-성암T/L 임시선로 구성(전선이동) -공사목적 : 345kV 신울산복합-북부산T/L 철탑설치","2020-05-11 07:00","2020-05-23 18:00","2020-05-11 07:00","2020-05-23 18:00","연속"]
[543,"부산울산","울산","신울산명례#2 T/L","20~21년 변전협력 총액공사","차단기 동작시험","2020-05-21 09:00","2020-05-21 18:00","2020-05-21 09:00","2020-05-21 18:00","연속"]
[544,"부산울산","울산","신울산S/S 154kV T BUS TIE CB","20~21년 변전협력 총액공사","GCB 보통점검","2020-05-19 09:00","2020-05-19 18:00","2020-05-19 09:00","2020-05-19 18:00","연속"]
[545,"부산울산","울산","온산처용#1 T/L","20~21년 변전협력 총액공사","- 차단기 동작시험(온산,처용)","2020-05-15 09:00","2020-05-15 18:00","2020-05-14 09:00","2020-05-14 18:00","연속"]
[546,"부산울산","울산","신온산온산#3 T/L","20~21년 변전협력 총액공사","- 신온산)GIS 보통점검 -온산) 차단기 동작시험","2020-05-08 09:00","2020-05-08 18:00","2020-05-08 09:00","2020-05-08 18:00","연속"]
[547,"부산울산","울산","신온산온산#1 T/L","20~21년 변전협력 총액공사","차단기 동작시험","2020-05-06 09:00","2020-05-06 18:00","2020-05-06 09:00","2020-05-06 18:00","연속"]
[548,"부산울산","울산","신온산온산#2 T/L","20~21년 변전협력 총액공사","차단기 동작시험","2020-05-07 09:00","2020-05-07 18:00","2020-05-07 09:00","2020-05-07 18:00","연속"]
[549,"부산울산","울산","용연처용#1 T/L","345kV 신울산복합-북부산T/L 건설공사","- 공사내용 : 신울산복합-북부산T/L 11호~12호 보호망 설치(안전이격) -공사목적 : 154kV 용연-처용T/L 직상 345kV 전력선 가선을 위한 보호망","2020-05-01 07:00","2020-05-01 18:00","2020-05-01 07:00","2020-05-01 18:00","연속"]
[550,"부산울산","울산","용연처용#1 T/L","345kV 신울산복합-북부산T/L 건설공사","-공사내용 : 345kV 본선로 및 154kV 용연-처용 병가 신설선로 가선공사(전선이동) -공사목적 : 345kV 및 154kV 신설 병가구간(13호~15호) 전력선 가선공사","2020-05-11 07:00","2020-05-23 18:00","2020-05-11 07:00","2020-05-23 18:00","연속"]
[551,"부산울산","울산","용연울산TP#1 T/L","2020년 용연S/S 154kV 장기사용 GIS 교체공사","○ 170kV 50kA 2,000A GIS(CHD, 지중) × 1CCT 철거,설치 ○ 기타 부대공사 × 1식","2020-05-29 18:00","2020-05-30 18:00","2020-05-29 18:00","2020-05-30 18:00","연속"]
[552,"부산울산","울산","용연울산TP#1 T/L","2020년 용연S/S 154kV 장기사용 GIS 교체공사","○ 170kV 50kA 2,000A GIS(CHD, 지중) × 1CCT 철거,설치 ○ 기타 부대공사 × 1식","2020-05-24 18:00","2020-05-24 19:00","2020-05-25 18:00","2020-05-25 19:00","연속"]
[553,"부산울산","울산","용연처용#2 T/L","345kV 신울산복합-북부산T/L 건설공사","- 공사내용 : 신울산복합-북부산T/L 11호~12호 보호망 설치(안전이격) -공사목적 : 154kV 용연-처용T/L 직상 345kV 전력선 가선을 위한 보호망","2020-05-01 07:00","2020-05-01 18:00","2020-05-01 07:00","2020-05-01 18:00","연속"]
[554,"부산울산","울산","울산T/P 154kV #60 BUS","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","○ 170kV 50kA 2,000A GIS(T/L) × 2CCT 철거,설치 ○ 170kV 50kA 4,000A GIS(B/S) × 2CCT 철거,설치 ○ 170kV 50kA 2,000A GIS(CHD, 지중) × 1CCT 철거,설치 ○ 기타 부대공사 × 1식","2020-05-24 17:00","2020-05-24 18:00","2020-05-24 17:00","2020-05-24 18:00","연속"]
[555,"부산울산","울산","용연울산TP#1 T/L","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","○ 170kV 50kA 2,000A GIS(T/L) × 2CCT 철거,설치 ○ 170kV 50kA 4,000A GIS(B/S) × 2CCT 철거,설치 ○ 170kV 50kA 2,000A GIS(CHD, 지중) × 1CCT 철거,설치 ○ 기타 부대공사 × 1식","2020-05-23 17:00","2020-05-24 17:00","2020-05-23 17:00","2020-05-24 17:00","연속"]
[556,"부산울산","울산","울산T/P 154kV #61 BUS","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","○ 170kV 50kA 2,000A GIS(T/L) × 2CCT 철거,설치 ○ 170kV 50kA 4,000A GIS(B/S) × 2CCT 철거,설치 ○ 170kV 50kA 2,000A GIS(CHD, 지중) × 1CCT 철거,설치 ○ 기타 부대공사 × 1식","2020-05-21 09:00","2020-05-24 18:00","2020-05-21 09:00","2020-05-24 18:00","연속"]
[557,"부산울산","울산","울산울산TP#1 T/L","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","○ 170kV 50kA 2,000A GIS(T/L) × 2CCT 철거,설치 ○ 170kV 50kA 4,000A GIS(B/S) × 2CCT 철거,설치 ○ 170kV 50kA 2,000A GIS(CHD, 지중) × 1CCT 철거,설치 ○ 기타 부대공사 × 1식","2020-05-19 18:00","2020-05-20 18:00","2020-05-19 18:00","2020-05-20 18:00","연속"]
[558,"부산울산","울산","울산T/P 154kV #60 BUS","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","○ 170kV 50kA 2,000A GIS(T/L) × 2CCT 철거,설치 ○ 170kV 50kA 4,000A GIS(B/S) × 2CCT 철거,설치 ○ 170kV 50kA 2,000A GIS(CHD, 지중) × 1CCT 철거,설치 ○ 기타 부대공사 × 1식","2020-05-11 09:00","2020-05-20 18:00","2020-05-11 09:00","2020-05-20 18:00","연속"]
[559,"부산울산","울산","울산울산TP#1 T/L","345kV 신울산복합-북부산T/L 건설공사","- 공사내용 : 신울산복합-북부산T/L 11호~12호 보호망 설치 및 전선가선(안전이격) -공사목적 : 154kV 용연-처용T/L 직상 보호망 설치 및 전력선 가선","2020-05-01 07:00","2020-05-07 18:00","2020-05-01 07:00","2020-05-07 18:00","연속"]
[560,"부산울산","울산","울산T/P 154kV #61 BUS","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","○ 170kV 50kA 2,000A GIS(T/L) × 2CCT 철거,설치 ○ 170kV 50kA 4,000A GIS(B/S) × 2CCT 철거,설치 ○ 170kV 50kA 2,000A GIS(CHD, 지중) × 1CCT 철거,설치 ○ 기타 부대공사 × 1식","2020-05-09 09:00","2020-05-10 18:00","2020-05-09 09:00","2020-05-10 18:00","연속"]
[561,"부산울산","울산","울산울산TP#1 T/L","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","○ 170kV 50kA 2,000A GIS(T/L) × 2CCT 철거,설치 ○ 170kV 50kA 4,000A GIS(B/S) × 2CCT 철거,설치 ○ 170kV 50kA 2,000A GIS(CHD, 지중) × 1CCT 철거,설치 ○ 기타 부대공사 × 1식","2020-05-08 18:00","2020-05-08 19:00","2020-05-08 18:00","2020-05-08 19:00","연속"]
[562,"부산울산","울산","울산T/P 154kV #65 BUS","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","○ 170kV 50kA 2,000A GIS(T/L) × 2CCT 철거,설치 ○ 170kV 50kA 4,000A GIS(B/S) × 2CCT 철거,설치 ○ 170kV 50kA 2,000A GIS(CHD, 지중) × 1CCT 철거,설치 ○ 기타 부대공사 × 1식","2020-05-08 09:00","2020-05-08 18:00","2020-05-08 09:00","2020-05-08 18:00","연속"]
[563,"부산울산","울산","용연울산TP#1 T/L","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","○ 170kV 50kA 2,000A GIS(T/L) × 2CCT 철거,설치 ○ 170kV 50kA 4,000A GIS(B/S) × 2CCT 철거,설치 ○ 170kV 50kA 2,000A GIS(CHD, 지중) × 1CCT 철거,설치 ○ 기타 부대공사 × 1식","2020-05-10 17:00","2020-05-10 18:00","2020-05-10 17:00","2020-05-10 18:00","연속"]
[564,"부산울산","울산","울산울산TP#1 T/L","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","○ 170kV 50kA 2,000A GIS(T/L) × 2CCT 철거,설치 ○ 170kV 50kA 4,000A GIS(B/S) × 2CCT 철거,설치 ○ 170kV 50kA 2,000A GIS(CHD, 지중) × 1CCT 철거,설치 ○ 기타 부대공사 × 1식","2020-05-24 17:00","2020-05-24 18:00","2020-05-24 17:00","2020-05-24 18:00","연속"]
[565,"부산울산","울산","웅촌서창#1 T/L","20~21년 변전협력 총액공사","GIS 보통점검","2020-05-04 09:00","2020-05-04 18:00","2020-05-15 09:00","2020-05-15 18:00","연속"]
[566,"부산울산","직할","범천S/S 154kV #60 BUS","범천S/S 154kV 장기사용 GIS 대체공사(1차)","1.170kV 50kA 2,000A GIS(T/L) × 4CCT 대체 2.170kV 50kA 1,250A GIS(T/R) × 2CCT 대체 3.170kV 50kA 2,000A GIS(B/T) × 1CCT 대체 4.170kV 50kA PT&ES × 1CCT 대체 5.기타 부대공사 × 1식","2020-05-11 09:00","2020-05-20 18:00","2020-05-11 09:00","2020-05-20 18:00","연속"]
[567,"부산울산","직할","양정범천 T/L","범천S/S 154kV 장기사용 GIS 대체공사","#2BUS 시험가압 선로(1H)","2020-05-08 17:00","2020-05-08 18:00","2020-05-08 17:00","2020-05-08 18:00","연속"]
[568,"부산울산","직할","개금범천#2 T/L","범천S/S 154kV 장기사용 GIS 대체공사","1.170kV 50kA 2,000A GIS(T/L) × 4CCT 대체 2.170kV 50kA 1,250A GIS(T/R) × 2CCT 대체 3.170kV 50kA 2,000A GIS(B/T) × 1CCT 대체 4.170kV 50kA PT&ES × 1CCT 대체 5.기타 부대공사 × 1식","2020-05-07 09:00","2020-05-29 18:00","2020-05-07 09:00","2020-05-29 18:00","연속"]
[569,"부산울산","직할","양정범천 T/L","범천S/S 154kV 장기사용 GIS 대체공사","#1BUS 시험가압 선로(24H)","2020-05-19 18:00","2020-05-20 18:00","2020-05-19 18:00","2020-05-20 18:00","연속"]
[570,"부산울산","직할","신대연S/S 154kV #60 BUS","2020년 상반기 직할 170kV GIS 정밀점검공사","신대연S/S 154kV BUS-TIE (6100) GIS 시험가압관련 -CB부 시험가압(2시간)","2020-05-19 18:00","2020-05-19 20:00","2020-05-19 18:00","2020-05-19 20:00","연속"]
[571,"부산울산","직할","신대연S/S 154kV #65 BUS","2020년 상반기 직할 170kV GIS 정밀점검공사","신대연S/S 345kV #2M.Tr 2차 (6244) GIS 시험가압관련 -CB부 및 상부모선, C/H 시험가압(2시간)","2020-05-21 18:00","2020-05-21 20:00","2020-05-21 18:00","2020-05-21 20:00","연속"]
[572,"부산울산","직할","신대연S/S 154kV #60 BUS","2020년 상반기 직할 170kV GIS 정밀점검공사","신대연S/S 345kV #1M.Tr 2차 (6144) GIS 시험가압관련 -CB부 및 상부모선, C/H 시험가압(2시간)","2020-05-07 18:00","2020-05-07 20:00","2020-05-07 18:00","2020-05-07 20:00","연속"]
[573,"부산울산","울산TP#1","울산T/P 154kV #60-#61 SEC GIS","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","○ 170kV 50kA 2,000A GIS(T/L) × 2CCT 철거,설치 ○ 170kV 50kA 4,000A GIS(B/S) × 2CCT 철거,설치 ○ 170kV 50kA 2,000A GIS(CHD, 지중) × 1CCT 철거,설치 ○ 기타 부대공사 × 1식","2020-05-09 09:00","2020-05-24 18:00","2020-05-09 09:00","2020-05-24 18:00","연속"]
[574,"부산울산","울산","용연처용#2 T/L","345kV 신울산복합-북부산T/L 건설공사",null,"2020-05-27 07:00","2020-06-07 18:00","2020-05-27 07:00","2020-06-07 18:00","연속"]
[575,"경남","직할","신월삼정#2 T/L","삼정S/S 154kV 신월-삼정#2T/L 인출변경작업","삼정S/S GIS화 사업 : 154kV 신월-삼정#2T/L 인출변경작업 - 구)변전소 => 신)변전소로 인출변경","2020-05-06 07:00","2020-05-27 18:30","2020-05-06 07:00","2020-05-27 18:30","연속"]
[576,"경남","직할","삼정천선#1 T/L","삼정S/S 154kV 삼정-천선#1T/L 인출변경","삼정S/S GIS화 사업 : 삼정-천선#1T/L 인출변경 작업 - 구)변전소 => 신)변전소 인출변경","2020-05-18 07:00","2020-06-04 18:30","2020-05-18 07:00","2020-06-04 18:30","연속"]
[577,"경남","직할","신김해장유#1 T/L","154kv 장유-마천T/L OPGW 시설공사","장유-마천T/L OPGW 시설 : 22km","2020-05-13 07:00","2020-05-15 18:00","2020-05-13 07:00","2020-05-15 18:00","연속"]
[578,"경남","직할","신김해장유#2 T/L","154kv 장유-마천T/L OPGW 시설공사","장유-마천T/L OPGW 시설 : 22km","2020-05-10 07:00","2020-05-12 18:00","2020-05-10 07:00","2020-05-12 18:00","연속"]
[579,"경남","직할","신김해지사#2 T/L","154kv 장유-마천T/L OPGW 시설공사","장유-마천T/L OPGW 시설 : 22km","2020-05-10 07:00","2020-05-12 18:00","2020-05-10 07:00","2020-05-12 18:00","연속"]
[580,"경남","직할","신김해진영#2 T/L","신김해S/S 154kV 신김해-진영#2T/L GIS 보통점검","신김해S/S 154kV 신김해-진영#2T/L GIS 보통점검 및 전자변교체","2020-05-29 09:30","2020-05-29 17:30","2020-05-29 09:30","2020-05-29 17:30","연속"]
[581,"경남","직할","신김해진영#1 T/L","신김해S/S 154kV 신김해-진영#1T/L GIS 보통점검","신김해S/S 154kV 신김해-진영#1T/L GIS 보통점검 및 전자변교체","2020-05-28 09:30","2020-05-28 17:30","2020-05-28 09:30","2020-05-28 17:30","연속"]
[582,"경남","직할","신김해지사#1 T/L","154kv 장유-마천T/L OPGW 시설공사","장유-마천T/L OPGW 시설 : 22km","2020-05-13 07:00","2020-05-23 18:00","2020-05-13 07:00","2020-05-23 18:00","연속"]
[583,"경남","직할","장유마천#1 T/L","154kv 장유-마천T/L OPGW 시설공사","장유-마천T/L OPGW 시설 : 22km","2020-05-01 07:00","2020-05-25 18:00","2020-05-01 07:00","2020-05-25 18:00","연속"]
[584,"경남","직할","천선진해#2 T/L","154kV 천선-진해#2T/L 초기점검","154kV 천선-진해#2T/L 초기점검(16, 17호)","2020-05-29 08:00","2020-05-29 13:00","2020-05-29 08:00","2020-05-29 13:00","연속"]
[585,"경남","직할","천선진해#1 T/L","154kV 천선-진해#1T/L 초기점검","154kV 천선-진해#1T/L 초기점검(16, 17호)","2020-05-29 08:00","2020-05-29 18:00","2020-05-29 08:00","2020-05-29 18:00","연속"]
[586,"경남","직할","의창차룡#1 T/L GIS","154kV 의창분기 지중T/L 건설공사","XLPE 2,000/4회선(0.7km) 154kV 신마산-의창 #1T/L 154kV 의창-차룡 #1T/L 무부하 가압(24H)","2020-05-18 10:00","2020-05-19 10:00","취소","취소","연속"]
[587,"경남","진주","진주개양#1 T/L","개양S/S 진주-개양#1T/L CB(617) 보통점검","개양S/S 진주-개양#1T/L CB(617) 보통점검 - 병행 : 진주S/S 진주-개양#1T/L CB(617) 조작시험","2020-05-23 10:00","2020-05-23 13:00","2020-05-23 10:00","2020-05-23 13:00","연속"]
[588,"경남","진주","개양S/S 154kV #60-#65 BUS TIE CB","개양S/S 154kV BUS PRO PNL 대체공사","개양S/S 154kV BUS PRO PNL 대체공사","2020-05-25 09:00","2020-05-28 18:00","2020-05-25 09:00","2020-05-28 18:00","연속"]
[589,"경남","진주","진주개양#2 T/L","개양S/S 진주-개양#2T/L CB(627) 보통점검","개양S/S 진주-개양#2T/L CB(627) 보통점검 - 병행 : 진주S/S 진주-개양#1T/L CB(627) 조작시험","2020-05-23 13:00","2020-05-23 17:00","2020-05-23 13:00","2020-05-23 17:00","연속"]
[590,"경남","진주","삼천포사천#1 T/L","사천S/S 삼천포-사천#1T/L CB(617) 보통점검","사천S/S 삼천포-사천#1T/L CB(617) 보통점검","2020-05-15 10:00","2020-05-15 13:00","2020-05-15 10:00","2020-05-15 13:00","연속"]
[591,"경남","진주","삼천포사천#2 T/L","사천S/S 삼천포-사천#2T/L CB(627) 보통점검","사천S/S 삼천포-사천#2T/L CB(627) 보통점검","2020-05-15 13:00","2020-05-15 17:00","2020-05-15 13:00","2020-05-15 17:00","연속"]
[592,"경남","진주","삼천포사천#1 T/L","사천S/S 사천-사남#1T/L 정밀점검 시험가압","사천S/S 사천-사남#1T/L 정밀점검 시험가압","2020-05-17 10:00","2020-05-17 18:00","2020-05-17 10:00","2020-05-17 18:00","연속"]
[593,"경남","진주","삼천포사천#2 T/L","사천S/S 사천-사남#2T/L 정밀점검 시험가압","사천S/S 사천-사남#2T/L 정밀점검 시험가압","2020-05-24 10:00","2020-05-24 18:00","2020-05-24 10:00","2020-05-24 18:00","연속"]
[594,"경남","진주","의령동진주#1 T/L","의령S/S 154kV 의령-동진주#1T/L CB(657) 조작시험","의령S/S 154kV 의령-동진주#1T/L CB(657) 조작시험 - 병행 : 동진주S/S 154kV 의령-동진주#1T/L CB(617) 보통점검","2020-05-30 10:00","2020-05-30 13:00","2020-05-30 10:00","2020-05-30 13:00","연속"]
[595,"경남","진주","의령동진주#2 T/L","의령S/S 154kV 의령-동진주#2T/L CB(667) 조작시험","의령S/S 154kV 의령-동진주#1T/L CB(667) 조작시험 - 병행 : 동진주S/S 154kV 의령-동진주#1T/L CB(627) 보통점검","2020-05-30 13:00","2020-05-30 17:00","2020-05-30 13:00","2020-05-30 17:00","연속"]
[596,"경남","진주","하동개양#1 T/L","154kV 하동-개양T/L 송전선로 정밀점검 및 안전거리확보","154kV 하동-개양T/L 송전선로 정밀점검 및 안전거리확보","2020-05-09 08:30","2020-05-10 17:00","2020-05-09 08:30","2020-05-10 17:00","매일"]
[597,"경남","진주","하동개양#2 T/L","154kV 하동-개양T/L 송전선로 정밀점검 및 안전거리확보","154kV 하동-개양T/L 송전선로 정밀점검 및 안전거리확보","2020-05-09 08:30","2020-05-10 17:00","2020-05-09 08:30","2020-05-10 17:00","매일"]
[598,"경남","진주","하동개양#2 T/L","154kV 하동-개양T/L 송전선로 정밀점검 및 안전거리확보","154kV 하동-개양T/L 송전선로 정밀점검 및 안전거리확보","2020-05-16 08:30","2020-05-17 17:00","2020-05-16 08:30","2020-05-17 17:00","매일"]
[599,"경남","진주","하동개양#1 T/L","154kV 하동-개양T/L 송전선로 정밀점검 및 안전거리확보","154kV 하동-개양T/L 송전선로 정밀점검 및 안전거리확보","2020-05-16 08:30","2020-05-17 17:00","2020-05-16 08:30","2020-05-17 17:00","매일"]
[600,"경남","함안","신마산동읍#2 T/L","154kV 신마산-차룡#1 T/L 1~2호, 7~11호 전선교체","154kV 신마산-차룡#1 T/L 1~2호, 7~11호 전선교체공사 안전이격 확보차","2020-05-01 06:30","2020-05-05 18:00","2020-05-01 06:30","2020-05-05 18:00","연속"]
[601,"경남","함안","신마산동읍#1 T/L","154kV 신마산-차룡#1T/L 1~2호 전선교체공사","154kV 신마산-차룡#1T/L 1~2호 전선교체공사 안전이격 확보차","2020-05-05 07:00","2020-05-05 18:00","2020-05-05 07:00","2020-05-05 18:00","매일"]
[602,"경남","함안","신마산1의창#1 T/L GIS","154kV 의창분기 지중T/L 건설공사","XLPE 2,000/4회선(0.7km) 154kV 신마산-의창 #1T/L 154kV 의창-차룡 #1T/L 무부하 가압(24H)","2020-05-18 10:00","2020-05-19 10:00","취소","취소","연속"]
[603,"경남","함안","신마산차룡#1 T/L","154kV 의창변전소 건설공사","154kV 의창분기T/L 접속작업 및 154kV 의창변전소 최초가압","2020-05-01 09:00","2020-05-27 18:00","2020-05-01 09:00","2020-05-27 18:00","연속"]
[604,"경남","함안","진영S/S 154kV 진영-수산#1T/L GIS","진영S/S 154kV 진영-수산#1T/L GIS 정밀점검","진영S/S 154kV 진영-수산#1T/L GIS 정밀점검","2020-05-01 08:30","2020-05-02 17:30","2020-05-01 08:30","2020-05-02 17:30","연속"]
[605,"경남","함안","칠서S/S 154kV #2 BUS","칠서SS 6100,60-65PT,617,6133 GIS 대체","칠서S/S 154kV 6100, 60-65PT, 신마산-칠서#2T/L, #2M.Tr 1차 GIS 대체 (장기사용 GIS 대체)","2020-05-20 13:30","2020-05-29 17:30","2020-05-20 13:30","2020-05-29 17:30","연속"]
[606,"경남","함안","칠서S/S 154kV #1 BUS","칠서SS 6100,60-65PT,617,6133 GIS 대체","칠서S/S 154kV 6100, 60-65PT, 신마산-칠서#2T/L, #2M.Tr 1차 GIS 대체 (장기사용 GIS 대체)","2020-05-09 09:00","2020-05-20 13:30","2020-05-09 09:00","2020-05-20 13:30","연속"]
[607,"경남","함안","칠서S/S 154kV #60-#65 BUS TIE GIS","칠서SS 6100,60-65PT,617,6133 GIS 대체","칠서S/S 154kV 6100, 60-65PT, 신마산-칠서#2T/L, #1M.Tr 1차 GIS 대체 (장기사용 GIS 대체)","2020-05-06 09:00","2020-05-29 17:30","2020-05-06 09:00","2020-05-29 17:30","연속"]
[608,"경남","함안","신마산칠서#2 T/L","칠서SS 6100,60-65PT,617,6133 GIS 대체","칠서S/S 154kV 6100, 60-65PT, 신마산-칠서#2T/L, #1M.Tr 1차 GIS 대체 (장기사용 GIS 대체)","2020-05-06 09:00","2020-05-29 17:30","2020-05-06 09:00","2020-05-29 17:30","연속"]
[609,"경남",null,"합천합천수력#1 T/L","옥외변전소 애자청소 및 금구류 조임 공사","옥외변전소 애자청소 및 금구류 조임 공사","2020-05-19 09:00","2020-05-21 18:00","2020-05-19 09:00","2020-05-21 18:00","연속"]
[610,"경남",null,"합천합천수력#2 T/L","옥외변전소 애자청소 및 금구류 조임 공사","옥외변전소 애자청소 및 금구류 조임 공사","2020-05-19 09:00","2020-05-21 18:00","2020-05-19 09:00","2020-05-21 18:00","연속"]