{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":14,"n_cols":13,"rows_kept":14,"cut":false,"hidden":false,"merged":[[2,12,3,12],[2,2,3,2],[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2020년도 6월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기","성남","신안성신가평 T/L","2020-2021년 성남전력지사 가공송전정비회사 총액공사","- 765kV 신안성-신가평T/L 항공장애표시도장(22기)","2020-06-01 07:00","2020-06-30 18:00","취소","취소","연속"]
[2,"충북","직할","신중부S/S 765kV CB 8600","신중부S/S 765kV GIS 초기점검 공사","신중부S/S 765kV GIS 초기점검 공사 (8600CB)","2020-06-02 09:00","2020-06-02 18:00","2020-06-02 09:00","2020-06-02 18:00","연속"]
[3,"충북","직할","신중부S/S 765kV CB 8671","신중부S/S 765kV GIS 초기점검 공사","신중부S/S 765kV GIS 초기점검 공사 (8671CB)","2020-06-01 09:00","2020-06-01 18:00","2020-06-01 09:00","2020-06-01 18:00","연속"]
[4,"충북","직할","신중부S/S 765kV CB 8571","신중부S/S 765kV GIS 초기점검 공사","신중부S/S 765kV GIS 초기점검 공사 (8571CB)","2020-06-03 09:00","2020-06-03 13:00","2020-06-03 09:00","2020-06-03 13:00","연속"]
[5,"충북","직할","신서산신중부#1 T/L","765kV 신서산-신중부T/L HSES 개방회로 개선공사","765kV 신서산-신중부#1T/L HSES 개방회로 개선공사","2020-06-01 09:00","2020-06-01 18:00","2020-05-22 09:00","2020-05-22 18:00","연속"]
[6,"충북","직할","신중부S/S 765kV CB 8500","신중부S/S 765kV GIS 초기점검 공사","신중부S/S 765kV GIS 초기점검 공사 (8500CB)","2020-06-03 13:00","2020-06-03 18:00","2020-06-03 13:00","2020-06-03 18:00","연속"]
[7,"충북","직할","신서산신중부#2 T/L","765kV 신서산-신중부T/L HSES 개방회로 개선공사","765kV 신서산-신중부#2T/L HSES 개방회로 개선공사","2020-06-03 09:00","2020-06-03 18:00","2020-05-25 09:00","2020-05-25 18:00","연속"]
[8,"부산울산","동부산","신고리N/P #2 Tie-Tr","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(76-77-0 - 2시간)","2020-06-05 16:00","2020-06-05 18:00","2020-06-05 16:00","2020-06-05 18:00","연속"]
[9,"부산울산","동부산","신고리N/P #3 Tie-Tr","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(7677 - 2시간)","2020-06-12 16:00","2020-06-12 18:00","2020-06-12 16:00","2020-06-12 18:00","연속"]
[10,"경남","함안","북경남S/S 765kV #1BUS","북경남S/S 765kV 8651DS C상 고장조치","북경남S/S 765kV 8651DS C상 고장조치 - 8609-1ES 소손부품(구동자 및 고정자 쉴드) 교체 및 내부점검","2020-06-22 09:00","2020-06-26 18:00","2020-06-22 09:00","2020-06-26 18:00","연속"]

{"sheet":"345송부","index":1,"n_rows":273,"n_cols":13,"rows_kept":273,"cut":false,"hidden":false,"merged":[[2,12,3,12],[2,2,3,2],[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2020년도 6월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #1 M.Tr","2020년 성동P/O 345kV M.Tr 및 OLTC 정밀점검공사","2020년 성동P/O 345kV M.Tr 및 OLTC 정밀점검공사","2020-06-24 08:00","2020-07-09 18:00","2020-06-24 08:00","2020-07-09 18:00","연속"]
[2,"서울","성동","성동S/S #3 M.Tr","2020년 성동PO 변전정비회사 총액공사","주변압기 2차170kV GIS 보통점검","2020-06-08 10:00","2020-06-08 18:00","취소","취소","연속"]
[3,"서울","중부","중부S/S #1 M.Tr","`20 중부P/O 변전정비회사 총액공사","중부S/S #1M.Tr 초기점검","2020-06-02 10:00","2020-06-04 18:00","2020-06-02 10:00","2020-06-04 18:00","연속"]
[4,"남서울","동서울","동서울S/S 345kV CB 7A00","345kV GIS 초기점검","345kV 7A72, 7079 GIS 초기점검","2020-06-22 09:00","2020-06-23 18:00","2020-06-22 09:00","2020-06-23 18:00","연속"]
[5,"남서울","동서울","동서울S/S #4 M.Tr","서울 동남권지역 전기공급시설 전력구공사(동서울#2-강남5차)","가시설 인발(H-Pile)을 위한 휴전작업","2020-06-08 09:00","2020-06-08 18:00","2020-06-08 09:00","2020-06-08 18:00","연속"]
[6,"남서울","동서울","동서울S/S 345kV SVC CB","SVC 옥외설비 및 열교환기 정기점검","SVC 옥외설비 및 열교환기 정기점검","2020-06-15 09:00","2020-06-19 18:00","2020-06-15 09:00","2020-06-19 18:00","연속"]
[7,"남서울","동서울","동서울S/S 345kV CB 7A72","345kV GIS 초기점검","345kV 7A72, 7079 GIS 초기점검","2020-06-22 09:00","2020-06-23 18:00","2020-06-22 09:00","2020-06-23 18:00","연속"]
[8,"남서울","동서울","동서울S/S 345kV #2 Sh.R","345kV #2Sh.R 초기 및 GIS 초기점검","345kV #2Sh.R 초기점검 345kV 7A72, 7079 GIS 초기점검","2020-06-22 09:00","2020-06-23 18:00","2020-06-22 09:00","2020-06-23 18:00","연속"]
[9,"남서울","영등포","신광명S/S 345kV #75 BUS","신광명S/S 345kV 75-76 SEC 동작불량 정비","- 75-75-1DS 동작불량 관련 정비 시행","2020-06-27 09:00","2020-06-28 18:00","2020-06-27 09:00","2020-06-28 18:00","연속"]
[10,"남서울","직할","영등포S/S 345kV #2 Sh.R","영등포S/S 345kV GIS 정밀점검공사","영등포S/S 345kV GIS 정밀점검공사 다빈도 차단기 정밀점검","2020-06-01 09:00","2020-06-04 18:00","2020-06-01 09:00","2020-06-04 18:00","연속"]
[11,"남서울","직할","영등포S/S 345kV #75 BUS","345kV 영등포S/S #4M.Tr 설치공사","○ 345kV M.Tr 설치 ○ 362kV GIS 3CB 설치 ○ 170kV GIS 1Bay 설치 - 설치완료 후 최종 무부하가압","2020-06-05 18:00","2020-06-06 18:00","2020-06-05 18:00","2020-06-06 18:00","연속"]
[12,"남서울","직할","신광명영등포#2 T/L","345kV 영등포S/S #4M.Tr 증설공사","-무부하 가압 용 ○ 345kV 변압기 증설 ○ 362kV GIS 3CB 증설 ○ 170kV GIS 1CCT 증설","2020-06-05 18:00","2020-06-06 18:00","취소","취소","연속"]
[13,"인천","김포","신김포S/S 345kV CB 7400","신김포S/S 345kV 7400 GIS CB 정밀점검","신김포S/S 345kV 신김포신인천CC T/L-#2 M.Tr 1차 TIE(7400) 정밀점검","2020-06-01 09:00","2020-06-04 18:00","2020-06-01 09:00","2020-06-04 18:00","연속"]
[14,"인천","부평","신가좌가정#2 T/L","신가좌S/S #71BAY B/F 보호반 대체공사","신가좌S/S #71BAY B/F 보호반 대체공사","2020-06-01 09:00","2020-06-05 18:00","2020-06-22 09:00","2020-06-29 18:00","연속"]
[15,"인천","부평","신가좌S/S #1 M.Tr","신가좌S/S #71BAY B/F 보호반 대체공사","신가좌S/S #71BAY B/F 보호반 대체공사","2020-06-01 09:00","2020-06-05 18:00","2020-06-22 09:00","2020-06-29 18:00","연속"]
[16,"인천","부평","신가좌가정#1 T/L","지중송전 위탁정비공사 피뢰기 열화진단","345kV 가정C/H 점검","2020-06-15 09:00","2020-06-16 18:00","취소","취소","연속"]
[17,"인천","부평","신가좌S/S #3 M.Tr","신가좌S/S #3M.Tr 보호반 대체공사","- 신가좌S/S #3M.Tr 보호반 대체공사 - 관련 변전설비 병행 휴전작업","2020-06-29 09:00","2020-07-03 18:00","2020-06-29 09:00","2020-07-03 18:00","연속"]
[18,"인천","부평","신가좌신시흥#1 T/L","345kV 신가좌-신시흥#1T/L 스페이서 간격조정","345kV 신가좌-신시흥#1T/L 스페이서 간격조정","2020-06-08 08:00","2020-06-12 18:00","취소","취소","연속"]
[19,"인천","부평","신경서인천CC#1 T/L","신경서S/S #72BAY B/F 보호반 대체공사","신경서S/S #72BAY B/F 보호반 대체공사","2020-06-22 09:00","2020-06-26 18:00","2020-06-01 09:00","2020-06-05 18:00","연속"]
[20,"인천","부평","신경서S/S #2 M.Tr","신경서S/S #72BAY B/F 보호반 대체공사","신경서S/S #72BAY B/F 보호반 대체공사","2020-06-22 09:00","2020-06-26 18:00","2020-06-01 09:00","2020-06-05 18:00","연속"]
[21,"인천","부평","신경서S/S #1 M.Tr","신경서S/S #71BAY B/F 보호반 대체공사","신경서S/S #71BAY B/F 보호반 대체공사","2020-06-15 09:00","2020-06-19 18:00","2020-06-08 09:00","2020-06-12 18:00","연속"]
[22,"인천","부평","신경서신인천CC T/L","신경서S/S #71BAY B/F 보호반 대체공사","신경서S/S #71BAY B/F 보호반 대체공사","2020-06-15 09:00","2020-06-19 18:00","2020-06-08 09:00","2020-06-12 18:00","연속"]
[23,"인천","부평","인천C/C 345kV #2 Sh.R","인천CC S/Y 345kV #2 Sh.R 초기점검","- 인천CC S/Y 345kV #2 Sh.R 초기점검 - 관련 변전설비 병행 휴전작업","2020-06-17 09:00","2020-06-18 18:00","2020-06-17 09:00","2020-06-18 18:00","연속"]
[24,"인천","부평","인천C/C 345kV CB 7672","인천CC S/Y 345kV 7672 GIS 보통점검","- 인천CC S/Y 345kV 7672 GIS 보통점검","2020-06-23 09:00","2020-06-23 18:00","2020-06-23 09:00","2020-06-23 18:00","연속"]
[25,"인천","부평","인천C/C 345kV CB 7600","인천CC S/Y 345kV 7600 GIS 보통점검","- 인천CC S/Y 345kV 7600 GIS 보통점검","2020-06-22 09:00","2020-06-22 18:00","2020-06-22 09:00","2020-06-22 18:00","연속"]
[26,"인천","부평","인천C/C 345kV CB 7671","인천CC S/Y 345kV 7671 GIS 보통점검","- 인천CC S/Y 345kV 7671 GIS 보통점검","2020-06-19 09:00","2020-06-19 18:00","2020-06-19 09:00","2020-06-19 18:00","연속"]
[27,"인천","부평","인천C/C 345kV #1 Sh.R","인천CC S/Y 345kV #1 Sh.R 초기점검","- 인천CC S/Y 345kV #1 Sh.R 초기점검 - 관련 변전설비 병행 휴전작업","2020-06-15 09:00","2020-06-16 18:00","2020-06-15 09:00","2020-06-16 18:00","연속"]
[28,"인천","시흥","신시흥신광명#2 T/L","신시흥S/S 345kV 신시흥신광명#2T/L 피뢰기대체공사","신시흥S/S 345kV 신시흥신광명#2T/L 피뢰기대체공사","2020-06-09 09:00","2020-06-12 18:00","취소","취소","연속"]
[29,"인천","시흥","신시흥영흥TP#1 T/L","345kV 신시흥영흥#1T/L 사선 현수애자 절연성능 진단","345kV 신시흥영흥#1T/L 사선 현수애자 절연성능 진단","2020-06-09 08:00","2020-06-10 18:00","취소","취소","매일"]
[30,"인천","시흥","신시흥영흥TP#2 T/L","345kV 신시흥영흥#2T/L 사선 현수애자 절연성능 진단","345kV 신시흥영흥#2T/L 사선 현수애자 절연성능 진단","2020-06-11 08:00","2020-06-12 18:00","2020-06-11 08:00","2020-06-12 18:00","매일"]
[31,"인천","시흥","신시흥#2S/S #6 M.Tr","신시흥S/S 345kV #6M.Tr보통점검","신시흥S/S 345kV #6M.Tr보통점검","2020-06-22 09:00","2020-06-24 18:00","2020-06-22 09:00","2020-06-24 18:00","연속"]
[32,"인천","시흥","신시흥#2S/S #5 M.Tr","신시흥S/S 345kV #5M.Tr보통점검","신시흥S/S 345kV #5M.Tr보통점검","2020-06-15 09:00","2020-06-17 18:00","2020-06-15 09:00","2020-06-17 18:00","연속"]
[33,"인천","직할","신부평S/S #4 M.Tr","신부평S/S #4M.Tr 7472, 6444 GIS 강화조작시험","신부평S/S #4M.Tr 7472, 6444 GIS 강화조작시험","2020-06-04 09:30","2020-06-04 18:00","2020-06-04 09:30","2020-06-04 18:00","연속"]
[34,"인천","직할","신부평S/S 345kV CB 7271","신부평S/S 서인천CC신부평#2T/L 7271CB 조작시험","신부평S/S 서인천CC신부평#2T/L 7271CB 조작시험","2020-06-16 09:30","2020-06-16 18:00","2020-06-16 09:30","2020-06-16 18:00","연속"]
[35,"인천","직할","서인천CC신부평#4 T/L","345kV 서인천CC-신부평#4T/L 절연유 및 가스보충","345kV 서인천CC-신부평#4T/L 절연유(8급유) 및 가스(6급유)보충","2020-06-14 10:00","2020-06-14 15:00","2020-06-14 10:00","2020-06-14 15:00","연속"]
[36,"인천","직할","서인천CC신부평#3 T/L","유호제 345kV 송전선로 보호배전반 성능개선","보호배전반 인출 DS 상태 감시회로 회로개선","2020-06-08 10:00","2020-06-08 18:00","2020-06-08 10:00","2020-06-08 18:00","연속"]
[37,"경기북부","고양","신덕은S/S 345kV CB 7071","362kV GIS 하자점검 - 총액공사","신덕은S/S 7071 GIS 하자점검","2020-06-09 09:00","2020-06-10 18:00","2020-06-09 09:00","2020-06-10 18:00","연속"]
[38,"경기북부","고양","신덕은S/S 345kV CB 7072","362kV GIS 하자점검 - 총액공사","신덕은S/S 7072 GIS 하자점검","2020-06-11 09:00","2020-06-12 18:00","2020-06-11 09:00","2020-06-12 18:00","연속"]
[39,"경기북부","고양","신덕은S/S #2 M.Tr","'20~'21년 고양전력지사 변전정비회사 총액공사","변압기 보호배전반 교체공사","2020-06-08 09:00","2020-06-12 18:00","취소","취소","연속"]
[40,"경기북부","고양","신덕은S/S 345kV CB 7000","362kV GIS 하자점검 - 총액공사","신덕은S/S 7000 GIS 하자점검","2020-06-08 09:00","2020-06-12 18:00","2020-06-08 09:00","2020-06-12 18:00","연속"]
[41,"경기북부","고양","신파주양주#1 T/L","345kV 신파주-양주T/L No.12 안전이격거리 확보공사","ㅇ 철탑 신설 2기(신설No.12, 임시No.12) 철거 2기(기설No.12, 임시No.12)","2020-06-08 07:00","2020-06-10 18:00","2020-06-08 07:00","2020-06-10 18:00","연속"]
[42,"경기북부","고양","신파주S/S #1 M.Tr","20년 고양P/O 변전정비 총액공사","신파주S/S #1M.Tr A상 OFU 필터교체 작업","2020-06-01 10:00","2020-06-01 18:00","2020-06-01 10:00","2020-06-01 18:00","연속"]
[43,"경기북부","고양","신김포신파주#1 T/L","345kV 신파주변전소 외부 천장재 교체공사","가. 시스템비계 설치 : 1,523.89㎡ 나. 샌드위치판넬 지붕 상부 보양 : 186.51㎡ 다. 기존 천장재 철거 : 689.99㎡ 라. 기존 천장 철골틀 철거 : 736.55㎡ 마. 내풍압용 천장틀 및 천장재 설치 : 736.55㎡","2020-06-01 09:00","2020-06-05 18:00","2020-06-01 09:00","2020-06-05 18:00","연속"]
[44,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용 GIS대체공사(7차분)-시험가압","- 미금구리#1T/L 철거, 설치 - 시험가압(6.8~9), (6.11~12), (6.16~17)","2020-06-08 08:00","2020-06-09 08:00","2020-06-08 08:00","2020-06-09 08:00","연속"]
[45,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용 GIS대체공사(7차분)-시험가압","- 미금구리#1T/L 철거, 설치 - 시험가압(6.8~9), (6.11~12), (6.16~17)","2020-06-16 17:00","2020-06-17 17:00","2020-06-16 17:00","2020-06-17 17:00","연속"]
[46,"경기북부","구리","미금S/S 345kV #1 Sh.R","`20~21 구리전력 변전정비 총액공사","미금S/S 345kV #1 Sh.R GIS 개폐타임측정","2020-06-15 09:30","2020-06-15 18:00","2020-06-15 09:30","2020-06-15 18:00","연속"]
[47,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용 GIS대체공사(6차분)-시험가압","- 미금덕소#1T/L 철거, 설치 - 미금구리#2T/L 철거, 설치 - 시험가압(5.18~19), (5.23~25), (6.5~6)","2020-06-05 17:00","2020-06-06 17:00","2020-06-05 17:00","2020-06-06 17:00","연속"]
[48,"경기북부","구리","미금성동#4 T/L","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 미금S/S 교체 77Bay 차단기 1대 감시제어계측 포인트이관 (→SA) - 77Bay LCP 및 배전반 모자익반 제어케이블 철거 및 재결선","2020-06-01 10:00","2020-06-05 13:00","2020-06-01 10:00","2020-06-05 13:00","연속"]
[49,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용 GIS대체공사(7차분)-안전이격거리확보","- 미금구리#1T/L 철거, 설치 - 시험가압(6.8~9), (6.11~12), (6.16~17)","2020-06-12 08:00","2020-06-16 17:00","2020-06-12 08:00","2020-06-16 17:00","매일"]
[50,"경기북부","구리","미금S/S #2 M.Tr","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 미금S/S 교체 345kV #2M.Tr 관련 감시제어계측 포인트이관 (→SA) - 변압기관련 GIS LCP 및 배전반 모자익반 제어케이블 철거 및 재결선","2020-06-22 10:00","2020-06-26 13:00","2020-06-22 10:00","2020-06-26 13:00","연속"]
[51,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용 GIS대체공사(7차분)-시험가압","- 미금구리#1T/L 철거, 설치 - 시험가압(6.8~9), (6.11~12), (6.16~17)","2020-06-11 17:00","2020-06-12 08:00","2020-06-11 17:00","2020-06-12 08:00","연속"]
[52,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용 GIS대체공사(7차분)-안전이격거리확보","- 미금구리#1T/L 철거, 설치 - 시험가압(6.8~9), (6.11~12), (6.16~17)","2020-06-09 08:00","2020-06-11 17:00","2020-06-09 08:00","2020-06-11 17:00","매일"]
[53,"경기북부","구리","신가평신의정부#1 T/L","345kV 신가평-신의정부 T/L 항공장애시설물 정비공사","ㅇ 항공장애표시구 설치 - S/T~1호","2020-06-23 07:00","2020-06-23 18:00","2020-06-23 07:00","2020-06-23 18:00","연속"]
[54,"경기북부","구리","신가평신의정부#2 T/L","345kV 신가평-신의정부#2T/L 정밀점검","- No.45~48, 96,97 정밀점검","2020-06-04 08:30","2020-06-04 18:00","2020-06-04 08:30","2020-06-04 18:00","연속"]
[55,"경기북부","구리","포천LNGC/C 345kV CB 7400","20년도 구리전력지사 345kV GIS 하자점검공사","20년도 구리전력지사 345kV GIS 하자점검공사","2020-06-10 09:00","2020-06-10 18:00","2020-06-10 09:00","2020-06-10 18:00","연속"]
[56,"경기북부","구리","포천LNGC/C 345kV CB 7471","20년도 구리전력지사 345kV GIS 하자점검공사","20년도 구리전력지사 345kV GIS 하자점검공사","2020-06-09 09:00","2020-06-09 18:00","2020-06-09 09:00","2020-06-09 18:00","연속"]
[57,"경기북부","직할","신덕은동두천CC#2 T/L","20년도 경기북부 직할 362kV GIS 정밀점검공사","동두천CC 신덕은-동두천CC #2 T/L 정밀점검(7171, 7100)","2020-06-12 09:00","2020-06-19 18:00","2020-06-12 09:00","2020-06-19 18:00","연속"]
[58,"경기북부","직할","신포천동두천CC#2 T/L","2020년 가공송전선로 순시점검 위탁공사","가공송전선로 정밀점검","2020-06-22 08:00","2020-06-24 18:00","2020-06-22 08:00","2020-06-24 18:00","연속"]
[59,"경기북부","직할","신덕은동두천CC#1 T/L","20년도 경기북부 직할 362kV GIS 정밀점검공사","동두천CC 신덕은-동두천CC #1 T/L 정밀점검(7271, 7200)","2020-06-22 09:00","2020-06-26 18:00","2020-06-22 09:00","2020-06-26 18:00","연속"]
[60,"경기북부","직할","신포천동두천CC#1 T/L","20년도 경기북부 직할 362kV GIS 정밀점검공사","동두천CC 신포천-동두천CC #1 T/L 정밀점검(7571)","2020-06-08 09:00","2020-06-16 18:00","2020-06-08 09:00","2020-06-16 18:00","연속"]
[61,"경기북부","직할","신의정부S/S #2 M.Tr","신의정부S/S 154kV DS부 발청 하자보수","신의정부 #2 M.Tr 2차측 DS 발청제거","2020-06-30 13:00","2020-07-03 18:00","2020-06-30 13:00","2020-07-03 18:00","연속"]
[62,"경기북부","직할","신의정부S/S #3 M.Tr","신의정부S/S 종합예방진단시스템 설치공사","신의정부S/S 종합예방진단시스템 설치공사 주변압기 붓싱 시험탭. OLTC 센서 설치부 실측","2020-06-29 09:00","2020-06-29 18:00","2020-06-29 09:00","2020-06-29 18:00","연속"]
[63,"경기북부","직할","신의정부S/S #1 M.Tr","신의정부S/S 종합예방진단시스템 설치공사","신의정부S/S 종합예방진단시스템 설치공사 주변압기 붓싱 시험탭. OLTC 센서 설치부 실측","2020-06-26 09:00","2020-06-26 18:00","2020-06-26 09:00","2020-06-26 18:00","연속"]
[64,"경기북부","직할","신의정부S/S 345kV #2 Sh.R","2020~2021년 경기북부 직할 변전정비회사 총액공사","신의정부S/S 345kV #2Sh.R 하자점검","2020-06-02 09:00","2020-06-02 18:00","2020-06-02 09:00","2020-06-02 18:00","연속"]
[65,"경기","군포","서서울#2S/S 345kV CB 7C71","서서울#2S/S 7C71 GIS 조작시험","서서울#2S/S 7C71 GIS 조작시험","2020-06-04 12:00","2020-06-04 14:00","2020-06-04 12:00","2020-06-04 14:00","연속"]
[66,"경기","군포","서서울#2S/S #5 M.Tr","서서울#2S/S #5 M.Tr 1차 7A72, 2차 GIS 조작시험","서서울#2S/S #5 M.Tr 1차 7A72, 2차 GIS 조작시험","2020-06-08 09:00","2020-06-08 18:00","2020-06-15 09:00","2020-06-17 18:00","연속"]
[67,"경기","군포","서서울#2S/S 345kV CB 7C00","서서울#2S/S 7C00 GIS 조작시험","서서울#2S/S 7C00 GIS 조작시험","2020-06-04 09:00","2020-06-04 12:00","2020-06-04 09:00","2020-06-04 12:00","연속"]
[68,"경기","군포","서서울#2S/S 345kV CB 7D72","서서울#2S/S 7D72 GIS 조작시험","서서울#2S/S 7D72 GIS 조작시험","2020-06-05 14:00","2020-06-05 18:00","2020-06-05 14:00","2020-06-05 18:00","연속"]
[69,"경기","군포","서서울#2S/S #6 M.Tr","서서울#2S/S #6 M.Tr 1차 7B72, 2차 GIS 조작시험","서서울#2S/S #6 M.Tr 1차 7B72, 2차 GIS 조작시험, 3차 GPT 초기점검","2020-06-24 09:00","2020-06-24 18:00","2020-06-24 09:00","2020-06-26 18:00","연속"]
[70,"경기","군포","서서울#2S/S 345kV CB 7C72","서서울#2S/S 7C72 GIS 조작시험","서서울#2S/S 7C72 GIS 조작시험","2020-06-04 14:00","2020-06-04 18:00","2020-06-04 14:00","2020-06-04 18:00","연속"]
[71,"경기","군포","서서울#2S/S 345kV CB 7D71","서서울#2S/S 7D71 GIS 조작시험","서서울#2S/S 7D71 GIS 조작시험","2020-06-05 09:00","2020-06-05 12:00","2020-06-05 09:00","2020-06-05 12:00","연속"]
[72,"경기","군포","서서울#2S/S 345kV CB 7D00","서서울#2S/S 7D00 GIS 조작시험","서서울#2S/S 7D00 GIS 조작시험","2020-06-05 12:00","2020-06-05 14:00","2020-06-05 12:00","2020-06-05 14:00","연속"]
[73,"경기","군포","신온양서서울#1 T/L","345kV 신온양서서울외 2개T/L 지장철탑이설공사","철탑교체 2기, 전력선교체 59 ~ 65","2020-06-16 07:00","2020-06-21 18:00","2020-05-26 07:00","2020-05-31 18:00","연속"]
[74,"경기","군포","서서울S/S #3 M.Tr","서서울S/S #3 M.Tr PNL 대체공사 등","서서울S/S #3 M.Tr PNL 대체 / 7600,7672 GIS 조작 / 6344 GIS 하자 / 4399, 4379, 437-1,2 VCB 보통점검","2020-06-22 09:00","2020-06-26 18:00","2020-06-22 09:00","2020-06-26 18:00","연속"]
[75,"경기","군포","신안산S/S 345kV #75 BUS","345kV 신안산S/S 용량부족 GIS 대체공사","345kV 신안산S/S 용량부족 GIS 대체공사(73bay) - 73bay 무부하 가압","2020-06-16 13:00","2020-06-17 13:00","2020-06-16 13:00","2020-06-17 13:00","연속"]
[76,"경기","군포","신안산S/S #3 M.Tr","345kV 신안산S/S 용량부족 GIS 대체공사","345kV 신안산S/S 용량부족 GIS 대체공사 - 345kV #3M.Tr CVT 설치","2020-06-22 09:00","2020-06-30 18:00","2020-06-24 09:00","2020-07-03 18:00","연속"]
[77,"경기","군포","신시흥신안산#2 T/L","신안산S/S 신시흥-신안산#2T/L IED 성능개선","신안산S/S 신시흥-신안산#2T/L IED 성능개선(영인기술)","2020-06-24 09:00","2020-06-24 18:00","2020-06-24 09:00","2020-06-24 18:00","연속"]
[78,"경기","군포","신안산S/S 345kV #70 BUS","345kV 신안산S/S 용량부족 GIS 대체공사","345kV 신안산S/S 용량부족 GIS 대체공사(73bay) - 73bay 무부하 가압","2020-06-15 13:00","2020-06-16 13:00","2020-06-15 13:00","2020-06-16 13:00","연속"]
[79,"경기","동부","곤지암S/S #3 M.Tr","20년 동부 변전정비회사 총액공사","곤지암:345kV #3M.Tr(보통)(~16) 부싱절연유채유,C상 OFU필터교체,7572,7500(보통)6344(보통)(~16)7572(A,B,C),7500(A,B,C)전자변교체,1차,2차 LA(보통)","2020-06-15 09:30","2020-06-16 18:00","2020-06-15 09:30","2020-06-16 18:00","연속"]
[80,"경기","동부","곤지암S/S #4 M.Tr","20년 동부 변전정비회사 총액공사","곤지암:345kV #4M.Tr(초기)(~18) 7672,7600(초기)6444(초기)(~18) 1차,2차 LA(초기)","2020-06-17 09:30","2020-06-18 18:00","2020-06-17 09:30","2020-06-18 18:00","연속"]
[81,"경기","성남","신성남동서울#2 T/L","20년 성남전력 변전정비회사 총액공사","전자변교체 - LA 보통점검 - CVT 보통점검 - 가보제 재페로성능개선 - B상 GIS 대쉬포트 누유 보수","2020-06-08 09:00","2020-06-08 18:00","취소","취소","연속"]
[82,"경기","성남","신성남신양재#1 T/L","'20~'21년 송전정비회사 총액공사","154kV 신성남-신봉#1 송전선로 피뢰기 설치공사 (1~5호) - 4회선 병가구간 안전이격거리 확보","2020-06-12 08:00","2020-06-12 13:00","2020-06-12 08:00","2020-06-12 13:00","연속"]
[83,"경기","성남","신수원S/S #3 M.Tr","20년 성남전력 154kV GIS 정밀점검","신수원S/S #3M.Tr 2차측 GIS 정밀점검","2020-06-08 09:00","2020-06-10 14:00","2020-06-08 09:00","2020-06-10 14:00","연속"]
[84,"경기","성남","신안성신성남#2 T/L","345kV 신용인-동서울T/L 불량애자 점검 및 교체(안전이격 확보)","345kV 신용인-동서울T/L 불량애자 점검 및 교체(안전이격 확보)","2020-06-22 08:00","2020-06-26 18:00","취소","취소","연속"]
[85,"경기","성남","신안성신성남#1 T/L","345kV 신용인-동서울T/L 불량애자 점검 및 교체(안전이격 확보)","345kV 신용인-동서울T/L 불량애자 점검 및 교체(안전이격 확보)","2020-06-15 08:00","2020-06-19 18:00","취소","취소","연속"]
[86,"경기","성남","신안성S/S 345kV #5 Sh.R FEEDER GIS","20년 성남전력 변전정비회사 총액공사","신안성S/S 345kV #5 Sh.R FEEDER GIS 조작시험 - 전자변히터설치","2020-06-10 09:00","2020-06-10 18:00","2020-06-10 09:00","2020-06-10 18:00","연속"]
[87,"경기","성남","신용인동서울#2 T/L","345kV 신용인-동서울T/L 불량애자 점검 및 교체","345kV 신용인-동서울T/L 불량애자 점검 및 교체","2020-06-22 08:00","2020-06-26 18:00","취소","취소","연속"]
[88,"경기","성남","신용인동서울#1 T/L","345kV 신용인-동서울T/L 불량애자 점검 및 교체","345kV 신용인-동서울T/L 불량애자 점검 및 교체","2020-06-15 08:00","2020-06-19 18:00","취소","취소","연속"]
[89,"경기","직할","화성서서울#1 T/L","봉담-송산간 2공구 도로개설 관련 지장이설공사","345kV 화성-서서울T/L 18~23호 임시 4기","2020-06-01 07:00","2020-06-10 18:00","취소","취소","연속"]
[90,"경기","직할","화성S/S #1 M.Tr","20년 직할 변전정비회사 총액공사","화성S/S #1M.Tr 보통(~11), 1차 GIS, 3차 Main CB 보통, 1차 LA 하자, 3차 LA, PT 보통(TM-OLTC 탭), #1S.Tr VCB, #1S.Tr #1-1Sh.R, #1-2Sh.R 보통, #1M.Tr 1차, 2차 부싱절연유 채유(A,B,C상)","2020-06-24 09:00","2020-06-25 18:00","2020-06-24 09:00","2020-06-25 18:00","연속"]
[91,"경기","직할","화성평택T/P#2 T/L","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV (40/50kA -> 63kA) GIS 30대 교체 O. 화성-평택T/P #2T/L 7BBAY -> 78BAY 원복이설","2020-06-15 08:00","2020-06-29 18:00","2020-06-15 08:00","2020-06-29 18:00","연속"]
[92,"경기","직할","화성S/S 345kV #71 BUS","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV (40/50kA -> 63kA) GIS 30대 교체 O. 화성-평택T/P #2T/L 7BBAY -> 78BAY 환원이설","2020-06-26 11:00","2020-06-27 11:00","2020-06-26 11:00","2020-06-27 11:00","연속"]
[93,"경기","직할","화성S/S 345kV #76 BUS","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV (40/50kA -> 63kA) GIS 30대 교체 O. 화성-평택T/P #2T/L 7BBAY -> 78BAY 환원이설","2020-06-25 11:00","2020-06-26 11:00","2020-06-25 11:00","2020-06-26 11:00","연속"]
[94,"경기","직할","화성신안산#1 T/L","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV (40/50kA -> 63kA) GIS 30대 교체 O. 화성-신안산 #1T/L 79BAY -> 7B BAY 임시이설","2020-06-30 08:00","2020-07-15 18:00","2020-06-30 08:00","2020-07-15 18:00","연속"]
[95,"경기","직할","화성서서울#2 T/L","봉담-송산간 2공구 도로개설 관련 지장이설공사","345kV 화성-서서울T/L 18~23호 임시 4기","2020-06-11 07:00","2020-06-14 18:00","2020-06-09 07:00","2020-06-14 18:00","연속"]
[96,"경기","평택","서안성S/S 345kV 신안성-서안성#1T/L GIS","345kV 서안성S/S GIS 용량대체공사","345kV GIS 11CB 철거 및 설치","2020-06-11 09:00","2020-06-12 09:00","2020-06-11 09:00","2020-06-12 09:00","연속"]
[97,"경기","군포","신온양서서울#2 T/L"," 345kV 신온양서서울외 2개T/L 지장철탑이설공사 "," 345kV 신온양서서울외 2개T/L 지장철탑이설공사 ","2020-06-22 07:00","2020-07-03 18:00","2020-06-01 07:00","2020-06-12 18:00","연속"]
[98,"경기","성남","신안성신성남#2 T/L "," 345kV 신안성-신성남#2T/L 송전선로 정밀점검 "," 345kV 신안성-신성남#2T/L 송전선로 정밀점검 ","2020-06-15 09:00","2020-07-03 18:00","2020-06-15 09:00","2020-07-03 18:00","연속"]
[99,"경기","성남","신안성신용인#2 T/L "," 345kV 신안성-신용인#2T/L 송전선로 정밀점검 "," 345kV 신안성-신용인#2T/L 송전선로 정밀점검 ","2020-06-15 09:00","2020-07-03 18:00","2020-06-15 09:00","2020-07-03 18:00","연속"]
[100,"강원","강릉","신양양양양PP T/L","가보전기제 보호배전반 성능개선","- 보호계전기 성능개선 시행 - 보호계전기 동작시험 및 연동시험","2020-06-24 10:00","2020-06-24 18:00","2020-06-24 10:00","2020-06-24 18:00","연속"]
[101,"강원","강릉","신양양S/S #3 M.Tr","신양양S/S 154kV GIS 하자점검","○ 신양양S/S 154kV GIS 하자점검 - 7472CB, 7400 CB","2020-06-03 10:00","2020-06-03 18:00","2020-06-03 10:00","2020-06-03 18:00","연속"]
[102,"강원","강릉","양양P/P 345kV CB 7100","양양PP 컨트롤블록 교체","○ 양양PP 컨트롤블록 교체 - 7100 CB","2020-06-01 10:00","2020-06-03 18:00","2020-06-01 10:00","2020-06-03 18:00","연속"]
[103,"충북","직할","신중부남청주#1 T/L","345kV GIS PD발생 관련 절연로드PIN교체작업","345kV GIS PD발생 관련 절연로드PIN교체작업(7C02,7C62)","2020-06-24 09:00","2020-06-25 18:00","2020-06-24 09:00","2020-06-25 18:00","연속"]
[104,"충북","직할","신중부S/S 345kV #6 Sh.R","765kV 신중부S/S 초기점검공사","765kV 신중부S/S 초기점검공사(#6Sh.R, 7C79, 7C71, 7C00) 345kV GIS PD발생 관련 절연로드PIN교체작업(7C61,7C01)","2020-06-22 09:00","2020-06-26 18:00","2020-06-22 09:00","2020-06-26 18:00","연속"]
[105,"충북","직할","신중부S/S 345kV #5 Sh.R","765kV 신중부S/S 초기점검공사","765kV 신중부S/S 초기점검공사(#5Sh.R, 7A79, 7A71, 7A00) 345kV GIS PD발생 관련 절연로드PIN교체작업(7A61,7A01)","2020-06-15 09:00","2020-06-19 18:00","2020-06-15 09:00","2020-06-19 18:00","연속"]
[106,"충북","직할","신중부S/S 345kV CB 7B00","765kV 신중부S/S 초기점검공사","765kV 신중부S/S 초기점검공사(7B00CB)","2020-06-11 09:00","2020-06-11 18:00","2020-06-11 09:00","2020-06-11 18:00","연속"]
[107,"충북","직할","신중부S/S 345kV CB 7B71","765kV 신중부S/S 초기점검공사","765kV 신중부S/S 초기점검공사(7B71)","2020-06-10 09:00","2020-06-10 18:00","2020-06-10 09:00","2020-06-10 18:00","연속"]
[108,"충북","직할","신중부남청주#2 T/L","345kV GIS PD발생 관련 절연로드PIN교체작업","345kV GIS PD발생 관련 절연로드PIN교체작업(7B02, 7B62)","2020-06-17 09:00","2020-06-18 18:00","2020-06-17 09:00","2020-06-18 18:00","연속"]
[109,"충북","청주","신옥천신남원#2 T/L","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 345kV 75BAY B/F반 교체공사","2020-06-01 10:00","2020-06-04 18:00","2020-06-01 10:00","2020-06-04 18:00","연속"]
[110,"충북","청주","신옥천청양 T/L","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 345kV 76BAY B/F반 교체공사","2020-06-08 10:00","2020-06-11 18:00","2020-06-08 10:00","2020-06-11 18:00","연속"]
[111,"충북","청주","신옥천S/S #3 M.Tr","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 345kV 76BAY B/F반 교체공사","2020-06-08 10:00","2020-06-11 18:00","2020-06-08 10:00","2020-06-11 18:00","연속"]
[112,"충북","청주","신옥천신계룡 T/L","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 345kV 77BAY B/F반 교체 공사","2020-06-15 10:00","2020-06-18 18:00","2020-06-15 10:00","2020-06-18 18:00","연속"]
[113,"충북","청주","신옥천북경남 T/L","345kV 신옥천-북경남T/L 전력선 교체공사","- 전력선 교체 No.258~259, No.260~261, No.265~267 - 가공지선 교체 : No.261~263, No.248~253, No,237~238","2020-06-24 07:00","2020-06-30 18:00","취소","취소","연속"]
[114,"충북","청주","신옥천S/S #1 M.Tr","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 345kV 71BAY B/F반 교체 공사","2020-06-29 10:00","2020-07-02 18:00","취소","취소","연속"]
[115,"충북","청주","신옥천세종#1 T/L","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 345kV 71BAY B/F반 교체공사","2020-06-29 10:00","2020-07-02 18:00","취소","취소","연속"]
[116,"충북","청주","신옥천세종#2 T/L","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 345kV 72BAY B/F반 교체 공사","2020-06-24 10:00","2020-06-27 18:00","취소","취소","연속"]
[117,"충북","충주","신제천신영주#1 T/L","345kV 곤지암-신충주 등 4개T/L 전력선교체공사","전선접소개소 해소 전력선교체공사","2020-06-07 08:00","2020-06-11 18:00","2020-06-06 08:00","2020-06-10 18:00","연속"]
[118,"충북","충주","신제천신영주#2 T/L","345kV 곤지암-신충주 등 4개T/L 전력선교체공사","전선접소개소 해소 전력선교체공사","2020-06-12 08:00","2020-06-16 18:00","취소","취소","연속"]
[119,"충북","충주","신제천S/S #2 M.Tr","20-21년 충주전력 변전정비회사 총액공사","신제천S/S #2M.Tr 1,2차 GIS 하자점검. 3차 VCB 초기점검 3대.","2020-06-17 09:00","2020-06-18 18:00","2020-06-17 09:00","2020-06-18 18:00","연속"]
[120,"충북","충주","신제천동해#1 T/L","20-21년 충주전력 변전정비회사 총액공사","신제천S/S 7971, 7900 GIS 하자점검","2020-06-16 09:00","2020-06-16 18:00","2020-06-05 08:00","2020-06-05 18:00","연속"]
[121,"충북","충주","신충주S/S STATCOM M.Tr 1차 GIS","신충주S/S","STATCOM 냉각설비 초기점검. STACOM 345kV GIS(7071,7000) 하자점검. STACOM 345kV 변압기(A,B,C,예비) 하자점검. 23kV GIS(4479,4579) 및 #4.5S.Tr 하자점검.","2020-06-22 09:30","2020-06-26 18:00","2020-06-22 09:30","2020-06-26 18:00","연속"]
[122,"충북","충주","신충주S/S STATCOM M.Tr 1차 TIE GIS","신충주S/S","STATCOM 냉각설비 초기점검. STACOM 345kV GIS(7071,7000) 하자점검. STACOM 345kV 변압기(A,B,C,예비) 하자점검. 23kV GIS(4479,4579) 및 #4.5S.Tr 하자점검.","2020-06-22 09:30","2020-06-26 18:00","2020-06-22 09:30","2020-06-26 18:00","연속"]
[123,"충북","충주","곤지암신충주#1 T/L","345kV 곤지암-신충주 등 4개T/L 전력선교체공사","전선접소개소 해소 전력선교체공사","2020-06-18 08:00","2020-07-02 18:00","2020-06-20 08:00","2020-07-04 18:00","연속"]
[124,"충북","충주","신제천신충주#2 T/L","345kV 곤지암-신충주 등 4개T/L 전력선교체공사","전선접소개소 해소 전력선교체공사","2020-06-04 08:00","2020-06-06 18:00","2020-06-12 08:00","2020-06-14 18:00","연속"]
[125,"충북","충주","신제천신충주#1 T/L","345kV 곤지암-신충주 등 4개T/L 전력선교체공사","전선접소개소 해소 전력선교체공사","2020-06-01 08:00","2020-06-03 18:00","2020-06-15 08:00","2020-06-17 18:00","연속"]
[126,"대전충남","서산","태안T/P 345kV SEC CB 76770","20년 서산P/O 345kV GIS정밀점검 및 조작로드교체 공사","태안화력S/S 76-77-0 SEC-GIS 조작로드 교체","2020-06-01 09:00","2020-06-05 18:00","2020-06-01 09:00","2020-06-05 18:00","연속"]
[127,"대전충남","청양","보령C/C 345kV CB 7372","계획예방정비공사(발전소 요청)","계획예방정비공사(발전소 요청)","2020-06-01 09:00","2020-06-10 18:00","취소","취소","연속"]
[128,"대전충남","청양","보령C/C 345kV CB 7472","계획예방정비공사(발전소 요청)","계획예방정비공사(발전소 요청)","2020-06-01 09:00","2020-06-10 18:00","취소","취소","연속"]
[129,"대전충남","청양","보령C/C 345kV CB 7400","계획예방정비공사(발전소 요청)","계획예방정비공사(발전소 요청)","2020-06-01 09:00","2020-06-10 18:00","취소","취소","연속"]
[130,"대전충남","청양","보령C/C 345kV CB 7300","계획예방정비공사(발전소 요청)","계획예방정비공사(발전소 요청)","2020-06-01 09:00","2020-06-10 18:00","취소","취소","연속"]
[131,"대전충남","서산","신당진S/S 345kV SEC CB 70710","20년도 장기 미동작 차단기 조작시험","신당진S/S 70-71-0 CB 조작시험","2020-06-01 10:00","2020-06-01 14:00","2020-06-01 10:00","2020-06-01 14:00","연속"]
[132,"대전충남","서산","신당진S/S 345kV SEC CB 75760","20년도 장기 미동작 차단기 조작시험","신당진S/S 75-76-0 CB 조작시험","2020-06-01 14:00","2020-06-01 18:00","2020-06-01 14:00","2020-06-01 18:00","연속"]
[133,"대전충남","아산","아산S/S 345kV CB 7200","아산S/S 345kV 7200, 7271 GIS 보통점검","아산S/S 345kV 7200, 7271 GIS 보통점검","2020-06-02 09:00","2020-06-02 13:00","2020-06-02 09:00","2020-06-02 13:00","연속"]
[134,"대전충남","아산","아산S/S 345kV CB 7271","아산S/S 345kV 7200, 7271 GIS 보통점검","아산S/S 345kV 7200, 7271 GIS 보통점검","2020-06-02 13:00","2020-06-02 18:00","2020-06-02 13:00","2020-06-02 18:00","연속"]
[135,"대전충남","아산","아산S/S 345kV CB 7172","아산S/S 345kV 7172 GIS 보통점검","아산S/S 345kV 7172 GIS 보통점검","2020-06-03 09:00","2020-06-03 18:00","2020-06-03 09:00","2020-06-03 18:00","연속"]
[136,"대전충남","서산","신서산S/S 345kV #3 Sh.R 1차 CB A (7571A)","20년도 장기 미동작 차단기 조작시험","신서산S/S #3Sh.R 7579 CB 조작시험","2020-06-03 10:00","2020-06-03 14:00","2020-06-03 10:00","2020-06-03 14:00","연속"]
[137,"대전충남","서산","신서산S/S 345kV #4 Sh.R 7779CB A (7779A)","20년도 장기 미동작 차단기 조작시험","신서산S/S #4Sh.R 7779 CB 조작시험","2020-06-03 14:00","2020-06-03 18:00","2020-06-03 14:00","2020-06-03 18:00","연속"]
[138,"대전충남","서산","태안T/P 345kV #76 BUS","20년 서산P/O 345kV GIS정밀점검 및 조작로드교체 공사","태안화력S/S 76-77-0 SEC-GIS 조작로드 교체(무부하가압)","2020-06-05 09:00","2020-06-05 18:00","2020-06-05 09:00","2020-06-05 18:00","연속"]
[139,"대전충남","서산","태안T/P 345kV #77 BUS","20년 서산P/O 345kV GIS정밀점검 및 조작로드교체 공사","태안화력S/S 76-77-0 SEC-GIS 조작로드 교체(무부하가압)","2020-06-05 09:00","2020-06-05 18:00","2020-06-05 09:00","2020-06-05 18:00","연속"]
[140,"대전충남","서산","북당진현대제철 T/L","345kV 신송산분기T/L 건설사업","- 해당구간 : No.71 ~ No.69 구간내 No.70 선로 - 공사내용 : No.70 선로 가철탑 이설 전력선 공중이동 ACSR/AW 480SQ x 4B x 2C (0.793km)","2020-06-08 07:00","2020-06-11 18:00","취소","취소","연속"]
[141,"대전충남","아산","아산S/S #2 M.Tr","아산S/S 345kV #2M.Tr 부싱절연유 채유, 병행작업","아산S/S 345kV #2M.Tr 부싱절연유 채유, 병행작업","2020-06-10 09:00","2020-06-12 18:00","2020-06-03 09:00","2020-06-05 18:00","연속"]
[142,"대전충남","서산","태안T/P 345kV SEC CB 75760","20년도 장기 미동작 차단기 조작시험","태안T/P 75-76-0 CB 조작시험","2020-06-10 10:00","2020-06-10 14:00","2020-06-10 10:00","2020-06-10 14:00","연속"]
[143,"대전충남","서산","신당진개폐소현대제철 T/L","345kV 신송산분기T/L 건설사업","- 해당구간 : No.71 ~ No.69 구간내 No.70 선로 - 공사내용 : No.70 선로 가철탑 이설 전력선 공중이동 ACSR/AW 480SQ x 4B x 2C (0.793km)","2020-06-12 07:00","2020-06-15 18:00","취소","취소","연속"]
[144,"대전충남","서산","신당진S/S #1 M.Tr","20년 서산P/O 154kV GIS 정밀점검공사","신당진 345kV #1M.Tr 2차 GIS(6144) 정밀점검 및 DS(6141,6142) 정밀점검","2020-06-15 09:00","2020-06-19 18:00","2020-06-01 09:00","2020-06-05 18:00","연속"]
[145,"대전충남","청양","청양S/S 345kV SEC CB 70710","청양S/S 362kV GIS 전자변교체 및 메커니즘점검","청양S/S 70-71 SEC-CB 전자변교체 및 메커니즘점검","2020-06-15 09:00","2020-06-15 18:00","2020-06-15 09:00","2020-06-15 18:00","연속"]
[146,"대전충남","서산","당진T/P 345kV CB 7171","20년도 장기 미동작 차단기 조작시험","댱잔T/P #71Tie-Tr 1차 7171 CB 조작시험","2020-06-15 10:00","2020-06-15 14:00","2020-06-15 10:00","2020-06-15 14:00","연속"]
[147,"대전충남","청양","청양S/S 345kV SEC CB 75760","청양S/S 362kV GIS 전자변교체 및 메커니즘점검","청양S/S 76-77 SEC-CB 전자변교체 및 메커니즘점검","2020-06-16 09:00","2020-06-16 18:00","2020-06-16 09:00","2020-06-16 18:00","연속"]
[148,"대전충남","서산","신당진S/S 345kV CB 7100","20년 서산P/O 변전정비 총액공사","신당진S/S 345kV 71Bay TIE- GIS(7100) 보통점검","2020-06-17 09:00","2020-06-17 18:00","2020-06-01 09:00","2020-06-01 18:00","연속"]
[149,"대전충남","서산","신당진S/S 345kV CB 7471","20년 서산P/O 변전정비 총액공사","신당진S/S 345kV 신당진연락#1 T/L GIS(7471) 보통점검","2020-06-18 09:00","2020-06-18 18:00","2020-05-29 09:00","2020-05-29 18:00","연속"]
[150,"대전충남","서산","신당진S/S 345kV CB 7771","20년 서산P/O 변전정비 총액공사","신당진S/S 345kV 신당진연락#2 T/L GIS(7771) 보통점검","2020-06-19 09:00","2020-06-19 18:00","2020-06-03 09:00","2020-06-03 18:00","연속"]
[151,"대전충남","서산","신당진S/S 345kV CB 7700","20년 서산P/O 변전정비 총액공사","신당진S/S 345kV 신당진연락#2 T/L -TIE GIS(7700) 보통점검","2020-06-22 09:00","2020-06-22 18:00","2020-06-04 09:00","2020-06-04 18:00","연속"]
[152,"대전충남","청양","보령C/C 345kV #70 BUS","보령C/C 345kV 모선PT 전압비 시험 및 점검","보령C/C 345kV 모선PT 전압비 시험 및 점검","2020-06-22 09:00","2020-06-22 11:00","2020-06-22 09:00","2020-06-22 11:00","연속"]
[153,"대전충남","청양","보령C/C 345kV #71 BUS","보령C/C 345kV 모선PT 전압비 시험 및 점검","보령C/C 345kV 모선PT 전압비 시험 및 점검","2020-06-22 11:00","2020-06-22 13:00","2020-06-22 11:00","2020-06-22 13:00","연속"]
[154,"대전충남","청양","보령C/C 345kV #75 BUS","보령C/C 345kV 모선PT 전압비 시험 및 점검","보령C/C 345kV 모선PT 전압비 시험 및 점검","2020-06-22 13:00","2020-06-22 15:00","2020-06-22 13:00","2020-06-22 15:00","연속"]
[155,"대전충남","청양","보령C/C 345kV #76 BUS","보령C/C 345kV 모선PT 전압비 시험 및 점검","보령C/C 345kV 모선PT 전압비 시험 및 점검","2020-06-22 15:00","2020-06-22 17:00","2020-06-22 15:00","2020-06-22 17:00","연속"]
[156,"대전충남","서산","신당진개폐소 345kV CB 7C71","20년 서산P/O 변전정비 총액공사","신당진S/S 345kV 개폐소-태안화력#2T/L GIS(7C71) 보통점검","2020-06-23 09:00","2020-06-23 18:00","2020-06-23 09:00","2020-06-23 18:00","연속"]
[157,"대전충남","서산","신서산S/S 345kV CB 7671","20년 서산P/O 변전정비 총액공사","신서산S/S 765kV #3M.Tr 2차 GIS(7671) 보통점검","2020-06-24 09:00","2020-06-24 18:00","2020-06-05 09:00","2020-06-05 18:00","연속"]
[158,"대전충남","서산","신서산S/S 345kV CB 7871","20년 서산P/O 변전정비 총액공사","신서산S/S 765kV #4M.Tr 2차 GIS(7871) 보통점검","2020-06-25 09:00","2020-06-25 18:00","2020-06-25 09:00","2020-06-25 18:00","연속"]
[159,"대전충남","청양","청양S/S #2M.Tr","345kV #2M.Tr 1,2차 차단기 조작시험","7772, 7700 및 6244 조작시험","2020-06-26 09:00","2020-06-26 18:00","취소","취소","연속"]
[160,"대전충남","서산","태안T/P 345kV #7M.Tr 1차 CB C","20년 서산P/O 345kV GIS정밀점검 및 조작로드교체 공사","태안화력S/S 76-77-0 SEC-GIS 조작로드 교체(무부하가압)","2020-06-05 09:00","2020-06-05 18:00","2020-06-05 09:00","2020-06-05 18:00","연속"]
[161,"전북","김제","신김제S/S #3 M.Tr","154kV #1,2,3 Sh.C 차단부 제작사 정밀점검","- 6179 차단부 설치중 안전이격 - 6179, 6279, 6379 설치후 환원전 무부하 시험가압(24H)","2020-06-22 09:00","2020-06-30 18:00","2020-06-22 09:00","2020-06-30 18:00","연속"]
[162,"전북","김제","신김제한빛NP#1 T/L","345kV 신김제-한빛#1T/L 전력선 교체공사","가. 전력선 교체 : 2.973C-km (No.135~143호) 나. 스페이서댐퍼 설치 / 철거 : 138개 / 126개 다. 점퍼선 교체 : 1기 (No.143호) 라. 기타 부대공사","2020-06-17 08:00","2020-06-30 18:00","취소","취소","연속"]
[163,"전북","직할","북경남무주양수 T/L","345kV 신옥천-북경남T/L 전력선 교체공사","345kV 신옥천-북경남T/L 전력선 교체공사 - 전력선교체공사 : No.258~259","2020-06-22 07:00","2020-06-23 18:00","2020-06-22 07:00","2020-06-23 18:00","연속"]
[164,"전북","직할","신남원광양#1 T/L","신남원S/S GAS 누기보수공사(7500)","신남원S/S GAS 누기보수공사 [휴전개소 : 신남원-광양#1T/L, #75BUS] [작업개소 : 7500(A/B/C)]","2020-06-01 10:00","2020-06-12 18:00","2020-06-14 10:00","2020-06-25 18:00","연속"]
[165,"전북","직할","신남원광양#2 T/L","신남원S/S GAS 누기보수공사(7671/7661)","신남원S/S GAS 누기보수공사 [휴전개소 : 신남원-광양#2T/L, #70BUS] [작업개소 : 7671(A/B/C), 7661(B)]","2020-06-13 10:00","2020-06-30 18:00","2020-06-26 10:00","2020-07-13 18:00","연속"]
[166,"전북","직할","신남원S/S 345kV #70 BUS","신남원S/S GAS 누기보수공사(#70BUS)","신남원S/S GAS 누기보수공사 [휴전개소 : #70BUS] [작업개소] - 7271/7200(04/07~04/27) - 7471(05/26~05/29) - 7371(05/30~06/02) - 7671/7661(06/15~06/28)","2020-06-17 10:00","2020-06-30 18:00","2020-06-30 10:00","2020-07-13 18:00","연속"]
[167,"광주전남","강진","신강진S/S #1M.Tr","신강진S/S 345kV #1M.Tr 하자보수 공사","345kV #1M.Tr B상 컨서베이터 판상유면계 교체 345kV #1M.Tr B상 유온도계 교체","2020-06-08 09:00","2020-06-09 18:00","2020-06-08 09:00","2020-06-09 18:00","연속"]
[168,"광주전남","강진","신강진S/S 345kV CB 7271","신화순-신강진#1T/L GIS CB(7271) 결상계전기 교체","신화순-신강진#1T/L GIS CB(7271) 결상계전기(47T1) 교체","2020-06-15 09:00","2020-06-15 18:00","2020-06-15 09:00","2020-06-15 18:00","연속"]
[169,"광주전남","강진","신강진S/S 345kV CB 7300","신화순-신강진#2/L GIS TIE CB(7300) B상 유압실린더 교체","신화순-신강진#2/L GIS TIE CB(7300) B상 유압실린더 교체","2020-06-16 09:00","2020-06-16 18:00","2020-06-16 09:00","2020-06-16 18:00","연속"]
[170,"광주전남","강진","신강진S/S #4 M.Tr","신강진S/S 345kV #4M.Tr 누유개소 정비공사","#4M.Tr 방압변(A, B, C상) 교체 #4M.Tr C상 절연유 여과 기타 누유개소 정비","2020-06-22 09:00","2020-06-24 18:00","2020-06-22 09:00","2020-06-24 18:00","연속"]
[171,"광주전남","광주","신광주S/S 345kV CB 7872","20년 광주변전총액(345kV 7872 장기미동작차단기점검)","신광주S/S 345kV 7872 장기미동작차단기점검","2020-06-12 13:00","2020-06-12 15:00","2020-06-12 13:00","2020-06-12 15:00","연속"]
[172,"광주전남","광주","신광주S/S 345kV CB 7471","20년 광주변전총액(345kV 7471 장기미동작차단기점검)","신광주S/S 345kV 7471 장기미동작차단기점검, Dashpot A상 점검","2020-06-17 12:00","2020-06-17 18:00","2020-06-17 12:00","2020-06-17 18:00","연속"]
[173,"광주전남","광주","신광주S/S 345kV CB 7800","20년 광주변전총액(345kV 7800 장기미동작차단기점검)","신광주S/S 345kV 7800 장기미동작차단기점검","2020-06-12 10:00","2020-06-12 12:00","2020-06-12 10:00","2020-06-12 12:00","연속"]
[174,"광주전남","광주","신광주S/S 345kV CB 7400","20년 광주변전총액(345kV 7400 장기미동작차단기점검)","신광주S/S 345kV 7400 장기미동작차단기점검, Dashpot A,C상 점검","2020-06-18 09:00","2020-06-18 18:00","2020-06-18 09:00","2020-06-18 18:00","연속"]
[175,"광주전남","광주","신광주신화순#1 T/L","20년 광주변전총액공사(신광주-신화순#1T/L LA)","-345kV 신광주-신화순#1T/L LA 대체","2020-06-15 09:00","2020-06-16 18:00","2020-06-15 09:00","2020-06-16 18:00","연속"]
[176,"광주전남","광주","신광주S/S 345kV CB 7200","20년 광주변전총액(345kV 7200 장기미동작차단기점검)","신광주S/S 345kV 7200 장기미동작차단기점검","2020-06-17 09:00","2020-06-17 12:00","2020-06-17 09:00","2020-06-17 12:00","연속"]
[177,"광주전남","광주","신광주신화순#2 T/L","신광주S/S 345kV #1Sh.R 설치공사(75BAY B/F반 대체)","362kV GIS 설치 및 75BAY B/F반 대체","2020-06-01 09:00","2020-06-12 18:00","2020-06-01 09:00","2020-06-12 18:00","연속"]
[178,"광주전남","광주","신화순S/S 345kV 예비 M.Tr CB","20년 광주변전총액공사(신화순S/S 예비M.Tr)","신화순S/S 예비M.Tr 보통점검","2020-06-03 09:30","2020-06-03 18:00","취소","취소","연속"]
[179,"광주전남","목포","한빛1NP한빛2NP#1 T/L","2020년 목포전력지사 362kV GIS 정밀점검공사","한빛연락#1T/L 7372 차단부 정밀점검","2020-06-15 10:00","2020-06-18 18:00","2020-06-15 10:00","2020-06-18 18:00","연속"]
[180,"광주전남","목포","한빛1NP한빛2NP#2 T/L","2020년 목포전력지사 362kV GIS 정밀점검공사","한빛연락#2T/L 7472 차단부 정밀점검","2020-06-29 10:00","2020-07-02 18:00","2020-06-29 10:00","2020-07-02 18:00","연속"]
[181,"광주전남","목포","한빛N/P 345kV CB 7371","2020년 목포전력지사 362kV GIS 정밀점검","#2-1S/U TR 1차 GIS 7371 차단부 정밀점검","2020-06-22 10:00","2020-06-25 18:00","2020-06-10 10:00","2020-06-13 18:00","연속"]
[182,"광주전남","목포","신김제한빛NP#2 T/L","2020년 직할 가공송전 순시점검 위탁공사","345kV 신김제-한빛NP#2T/L No.1~25호 정밀점검","2020-06-22 09:00","2020-06-25 18:00","2020-06-22 09:00","2020-06-25 18:00","매일"]
[183,"광주전남","순천","신강진광양#2 T/L","광양S/S 362kV GIS 용량 대체공사","○ 광양S/S 362kV GIS 용량 대체 안전이격 확보 - #70-#71Sec CB대체(50kA→63kA) - 7751DS 및 #71BUS(77Bay) M-BUS 대체","2020-06-09 09:00","2020-06-29 18:00","2020-06-01 09:00","2020-06-26 18:00","연속"]
[184,"광주전남","순천","여수T/P 345kV CB 7271","20년 상반기 순천전력지사 345kV GIS 정밀점검공사","여수화력 7271 GIS 정밀점검","2020-06-01 09:00","2020-06-05 18:00","2020-06-01 09:00","2020-06-05 18:00","연속"]
[185,"대구","경산","신경산S/S #4 M.Tr","20년 상반기 경산P/O 170kV GIS 정밀점검 공사","- 6444 차단부 정밀점검","2020-06-12 09:00","2020-06-13 18:00","2020-06-12 09:00","2020-06-13 18:00","연속"]
[186,"대구","달성","고령S/S 345kV #1 Sh.R","고령S/S #1Sh.R 초기점검","고령S/S #1Sh.R 초기점검","2020-06-22 09:00","2020-06-22 18:00","2020-06-22 09:00","2020-06-23 18:00","연속"]
[187,"대구","달성","북경남대구#1 T/L","대구S/S 북경남-대구#1T/L 보통점검 및 보조Ry 교체","대구S/S 북경남-대구#1T/L 보통점검 및 보조Ry 교체","2020-06-15 09:00","2020-06-16 18:00","2020-06-15 09:00","2020-06-16 18:00","연속"]
[188,"대구","칠곡","북대구S/S 345kV CB 7272","북대구S/S 북대구-선산T/L CB Control Block 교체","북대구S/S 북대구-선산T/L CB Control Block 교체작업","2020-06-03 09:30","2020-06-05 14:00","2020-06-01 09:30","2020-06-03 14:00","연속"]
[189,"대구","칠곡","북대구S/S 345kV CB 7200","북대구S/S 북대구-선산T/L TIE CB Control Block 교체","북대구S/S 북대구-선산T/L TIE CB Control Block 교체작업","2020-06-01 09:30","2020-06-03 18:00","2020-06-03 15:00","2020-06-05 14:00","연속"]
[190,"대구","칠곡","북대구서대구#2 T/L","북대구S/S 345kV GIS 보통점검","북대구S/S 345kV GIS 보통점검","2020-06-15 09:30","2020-06-15 18:00","2020-06-15 09:30","2020-06-15 18:00","연속"]
[191,"대구","칠곡","북대구S/S 345kV 예비 M.Tr CB","북대구S/S 345kV 예비M.Tr 보통점검","북대구S/S 345kV 예비M.Tr 보통점검","2020-06-23 09:30","2020-06-23 18:00","취소","취소","연속"]
[192,"대구","칠곡","서대구S/S #3 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사(토목)","전력구 안전조치(강관항타시공)관련 안전이격확보","2020-06-18 08:00","2020-06-19 18:00","취소","취소","연속"]
[193,"대구","칠곡","북경남서대구#2 T/L","서대구S/S 345kV GCB 장기미동작점검","서대구S/S 345kV GCB 장기미동작점검","2020-06-17 09:30","2020-06-17 18:00","2020-06-17 09:30","2020-06-17 18:00","연속"]
[194,"대구","칠곡","서대구고령#1 T/L","서대구S/S 345kV GCB 장기미동작점검","서대구S/S 345kV GCB 장기미동작점검","2020-06-09 09:30","2020-06-09 18:00","2020-06-09 09:30","2020-06-09 18:00","연속"]
[195,"대구","칠곡","북경남서대구#1 T/L","서대구S/S 345kV GCB 장기미동작점검","서대구S/S 345kV GCB 장기미동작점검","2020-06-24 09:30","2020-06-24 18:00","2020-06-24 09:30","2020-06-24 18:00","연속"]
[196,"대구","칠곡","서대구S/S #2 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사(토목)","전력구 안전조치(강관항타시공)관련 안전이격확보","2020-06-29 08:00","2020-06-30 18:00","취소","취소","연속"]
[197,"대구","포항","신월성N/P 345kV CB 7500","신월성S/Y 7571, 7500 GIS 조작시험","신월성S/Y 7571, 7500 GIS 조작시험","2020-06-17 14:00","2020-06-17 18:00","2020-06-17 14:00","2020-06-17 18:00","연속"]
[198,"대구","포항","신월성N/P 345kV CB 7371","신월성S/Y 7371, 7471 GIS 조작시험","신월성S/Y 7371, 7471 GIS 조작시험","2020-06-05 09:30","2020-06-05 14:00","2020-06-05 09:30","2020-06-05 14:00","연속"]
[199,"대구","포항","신월성N/P 345kV CB 7471","신월성S/Y 7371, 7471 GIS 조작시험","신월성S/Y 7371, 7471 GIS 조작시험","2020-06-05 14:00","2020-06-05 18:00","2020-06-05 14:00","2020-06-05 18:00","연속"]
[200,"대구","포항","신월성N/P 345kV CB 7571","신월성S/Y 7571, 7500 GIS 조작시험","신월성S/Y 7571, 7500 GIS 조작시험","2020-06-17 09:00","2020-06-17 14:00","2020-06-17 09:00","2020-06-17 14:00","연속"]
[201,"대구","포항","신포항S/S #3 M.Tr","신포항S/S #3M.Tr 누유개소 보수작업","신포항S/S #3M.Tr 누유개소 보수작업","2020-06-10 09:00","2020-06-11 18:00","2020-06-10 09:00","2020-06-11 18:00","연속"]
[202,"대구","포항","월성N/P 345kV SEC CB 75760","월성S/Y 70-71-0, 75-76-0 GIS 조작시험차","월성S/Y 70-71-0, 75-76-0 GIS 조작시험차","2020-06-30 14:00","2020-06-30 18:00","2020-06-30 14:00","2020-06-30 18:00","연속"]
[203,"대구","포항","월성N/P 345kV SEC CB 70710","월성S/Y 70-71-0, 75-76-0 GIS 조작시험차","월성S/Y 70-71-0, 75-76-0 GIS 조작시험차","2020-06-30 09:30","2020-06-30 14:00","2020-06-30 09:30","2020-06-30 14:00","연속"]
[204,"경북","구미","선산S/S #2 M.Tr","2020-21년도 구미전력지사 변전정비업체 총액공사","-M.Tr 보통점검 -7172 GIS조작시험 -1,2차 부싱절연유 채유","2020-06-22 09:00","2020-06-23 18:00","2020-06-22 09:00","2020-06-23 18:00","연속"]
[205,"경북","구미","선산S/S 345kV CB 7000","Control Block 교체","제작사 입회 하 Control Block 교체","2020-06-03 09:00","2020-06-04 18:00","2020-06-03 09:00","2020-06-04 18:00","연속"]
[206,"경북","구미","서대구선산#1 T/L","20-21년 가공송전 정비공사 총액공사","345kV 서대구-선산T/L 스페이서 댐퍼 정비공사 o 스페이서 댐퍼 부족수량 추가 설치 및 간격재조정 o 구간 : No.2 ~ 27","2020-06-15 07:00","2020-06-17 18:00","2020-06-15 07:00","2020-06-17 18:00","매일"]
[207,"경북","구미","서대구선산#2 T/L","20-21년 가공송전 정비공사 총액공사","345kV 서대구-선산T/L 스페이서 댐퍼 정비공사 o 스페이서 댐퍼 부족수량 추가 설치 및 간격재조정 o 구간 : No.2 ~ 27","2020-06-18 07:00","2020-06-20 18:00","2020-06-18 07:00","2020-06-20 18:00","매일"]
[208,"경북","구미","선산S/S #3 M.Tr","2020-21년도 구미전력지사 변전정비업체 총액공사","-7472 GIS조작시험 -1,2차 부싱절연유 채유","2020-06-24 09:00","2020-06-24 18:00","2020-06-24 09:00","2020-06-24 18:00","연속"]
[209,"경북","영주","신영주S/S #1 M.Tr","신영주S/S 154kV 옥외철구설비 현대화공사","전력구 및 기기기초 설치 관련 파일시공 - 상부모선 및 임시철거 - 170kV GIS 부지 마이크로파일 시공(토목)","2020-06-08 09:00","2020-06-08 18:00","2020-06-08 09:00","2020-06-08 18:00","연속"]
[210,"경북","영주","신영주S/S #2 M.Tr","신영주S/S 154kV 옥외철구설비 현대화공사","전력구 및 기기기초 설치 관련 파일시공 - 상부모선 및 임시철거 - 170kV GIS 부지 마이크로파일 시공(토목)","2020-06-15 09:00","2020-06-15 18:00","2020-06-15 09:00","2020-06-15 18:00","연속"]
[211,"경북","영주","신영주S/S 345kV STATCOM GIS","STATCOM 냉각설비 유사고장 재발방지 대책 시행","-. STATCOM 냉각설비 경보시험 -. Valve Room 내 냉각배관 누수 개소 확인 및 조치 -. 냉각시스템 초기점검 시행","2020-06-29 09:00","2020-07-03 18:00","2020-06-29 09:00","2020-07-03 18:00","연속"]
[212,"경북","영주","신영주S/S 345kV STATCOM TIE GIS","STATCOM 냉각설비 유사고장 재발방지 대책 시행","-. STATCOM 냉각설비 경보시험 -. Valve Room 내 냉각배관 누수 개소 확인 및 조치 -. 냉각시스템 초기점검 시행","2020-06-29 09:00","2020-07-03 18:00","2020-06-29 09:00","2020-07-03 18:00","연속"]
[213,"경북","직할","신포항청송PP T/L","20~21년 경북본부 직할 변전정비회사 총액공사","신포항-청송PP T/L 보호반 교체","2020-06-11 09:00","2020-06-19 18:00","2020-06-11 09:00","2020-06-19 18:00","연속"]
[214,"경북","직할","청송P/P #2 M.Tr","20~21년 경북본부 직할 변전정비회사 총액공사","청송양수S/Y 72BAY B/F PNL 교체","2020-06-11 09:00","2020-06-19 18:00","2020-06-11 09:00","2020-06-19 18:00","연속"]
[215,"부산울산","동부산","고리2N/P 345kV #71 BUS","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(7177 - 2시간)","2020-06-19 16:00","2020-06-19 18:00","취소","취소","연속"]
[216,"부산울산","동부산","고리N/P 345kV #1 CLR CB","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선공사(7177)","2020-06-15 09:00","2020-06-19 18:00","취소","취소","연속"]
[217,"부산울산","동부산","고리N/P 345kV CB 7271","고리NP S/Y 345kV GIS 보통점검","1. 고리NP S/Y 345kV GIS 보통점검(7271) 2. 고리NP S/Y 345kV GIS 전자변 교체(7271)","2020-06-26 09:30","2020-06-26 17:00","2020-06-26 09:30","2020-06-26 17:00","연속"]
[218,"부산울산","동부산","고리N/P 345kV CB 7272","고리NP S/Y 345kV GIS 보통점검","1. 고리NP S/Y 345kV GIS 보통점검(7272) 2. 고리NP S/Y 345kV GIS 전자변 교체(7272)","2020-06-30 09:30","2020-06-30 17:00","2020-06-30 09:30","2020-06-30 17:00","연속"]
[219,"부산울산","동부산","고리N/P 345kV CB 7200","고리NP S/Y 345kV GIS 보통점검","1. 고리NP S/Y 345kV GIS 보통점검(7200) 2. 고리NP S/Y 345kV GIS 전자변 교체(7200)","2020-06-29 09:30","2020-06-29 17:00","2020-06-29 09:30","2020-06-29 17:00","연속"]
[220,"부산울산","동부산","고리N/P 345kV CB 7A71","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선공사(7A71)","2020-06-08 09:00","2020-06-12 18:00","취소","취소","연속"]
[221,"부산울산","동부산","신양산S/S 345kV #1 BUS","[11차] 345kV 신양산S/S 현대화공사","1.내용 - 345kV 70BUS 모선보호반 대체","2020-06-29 09:00","2020-07-01 18:00","취소","취소","연속"]
[222,"부산울산","동부산","신양산고리NP#2 T/L","[10차] 345kV 신양산S/S 현대화공사","1.내용 - 154kV 신양산-시랑#1, #2M.Tr 2차 인출변경 및 보호반 대체 - 신양산-고리NP#2T/L 보호배전반 이설","2020-06-13 09:00","2020-06-27 18:00","취소","취소","연속"]
[223,"부산울산","동부산","신양산S/S #3 M.TR","[10차] 345kV 신양산S/S 현대화공사","1.내용 - 154kV 신양산-시랑#1, #2M.Tr 2차 인출변경 및 보호반 대체 - 신양산-고리NP#2T/L 보호배전반 이설","2020-06-13 09:00","2020-06-27 18:00","2020-06-13 09:00","2020-06-27 18:00","연속"]
[224,"부산울산","동부산","신양산북부산#2 T/L","345㎸ 신양산-북부산T/L OPGW 증설공사","345㎸ 신양산-북부산#2T/L OPGW 21.950㎞(120SQ/48C) 시설, S/T↔ICT실간 비금속광케이블 0.83㎞ 등 부대설비 1식","2020-06-27 07:00","2020-07-10 18:00","2020-06-29 07:00","2020-07-12 18:00","연속"]
[225,"부산울산","동부산","신양산고리NP#2 T/L","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(7177 - 2시간)","2020-06-19 16:00","2020-06-19 18:00","취소","취소","연속"]
[226,"부산울산","동부산","신양산고리NP#2 T/L","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(7A71 - 2시간)","2020-06-12 16:00","2020-06-12 18:00","취소","취소","연속"]
[227,"부산울산","동부산","신양산S/S 345kV CB 7671","신양산S/S 345kV GIS 보통점검","1. 신양산S/S 345kV GIS 보통점검(7671) 2. 신양산S/S 345kV GIS 전자변 교체(7671)","2020-06-09 09:30","2020-06-09 17:00","2020-06-09 09:30","2020-06-09 17:00","연속"]
[228,"부산울산","동부산","신양산S/S 345kV CB 7571","신양산S/S 345kV GIS 보통점검","1. 신양산S/S 345kV GIS 보통점검(7571) 2. 신양산S/S 345kV GIS 전자변 교체(7571)","2020-06-08 09:30","2020-06-08 17:00","2020-06-08 09:30","2020-06-08 17:00","연속"]
[229,"부산울산","북부산","북부산신울산#2 T/L","2020년 북부산전력지사 345kV GIS 정밀점검공사","2020년 북부산전력지사 345kV GIS 정밀점검공사 (7172, 7200CB 정밀점검)","2020-06-01 09:00","2020-06-05 18:00","2020-06-01 09:00","2020-06-05 18:00","연속"]
[230,"부산울산","북부산","서부산북부산#1 T/L","2019-2020년 북부산전력지사 지중송전 위탁정비공사","345kV 서부산-북부산T/L OF케이블 절연유 채취","2020-06-01 09:00","2020-06-01 18:00","2020-06-01 09:00","2020-06-01 18:00","연속"]
[231,"부산울산","북부산","북부산신온산 T/L","345kV 북부산-울산TP 등 4개 T/L 전선접속개소 전선교체공사","북부산-신온산 : No.30~35, 55~57, 57~61호간 (9경간)","2020-06-06 07:00","2020-06-09 18:00","2020-06-06 07:00","2020-06-09 18:00","연속"]
[232,"부산울산","북부산","북부산신울산#1 T/L","345㎸ 북부산-신울산T/L OPGW 증설공사","345㎸ 북부산-신울산#1T/L OPGW 43.864㎞(70SQ/48C) 시설, S/T↔ICT실간 비금속광케이블 0.797㎞ 등 부대설비 1식","2020-06-19 07:00","2020-06-28 18:00","2020-06-19 07:00","2020-06-28 18:00","연속"]
[233,"부산울산","북부산","북부산울산TP T/L","345kV 북부산-울산TP 등 4개 T/L 전선접속개소 전선교체공사","북부산-울산TP : No.30~35, 55~57, 57~61, 124~128호간 (17경간)","2020-06-10 07:00","2020-06-18 18:00","2020-06-10 07:00","2020-06-18 18:00","연속"]
[234,"부산울산","북부산","서부산북부산#2 T/L","2019-2020년 북부산전력지사 지중송전 위탁정비공사","345kV 서부산-북부산T/L OF케이블 절연유 채취","2020-06-02 09:00","2020-06-02 18:00","2020-06-02 09:00","2020-06-02 18:00","연속"]
[235,"부산울산","서부산","서부산S/S 345kV #1 Sh.R","서부산S/S 345kV #1Sh.R 수냉각 PNL 대체공사","서부산S/S 345kV #1Sh.R 수냉각 PNL 대체공사","2020-06-08 10:00","2020-06-12 18:00","2020-06-08 10:00","2020-06-12 18:00","연속"]
[236,"부산울산","서부산","서부산S/S 345kV #2 Sh.R","서부산S/S 345kV #2Sh.R 수냉각 PNL 대체공사","서부산S/S 345kV #2Sh.R 수냉각 PNL 대체공사","2020-06-15 10:00","2020-06-19 18:00","2020-06-15 10:00","2020-06-19 18:00","연속"]
[237,"부산울산","울산","신온산S/S #4 M.Tr","20-21년 변전정비회사 총액공사","C상 M.Tr 보통점검 부싱절연유 채유","2020-06-02 09:00","2020-06-02 18:00","2020-06-02 09:00","2020-06-02 18:00","연속"]
[238,"부산울산","울산","신온산신울산#1 T/L","2019-2020년 북부산전력지사 지중송전 위탁정비공사","345kV 신울산-신온산T/L(B) 케이블헤드 점검(청량C/H)","2020-06-23 09:00","2020-06-23 13:00","취소","취소","연속"]
[239,"부산울산","울산","신온산신울산#2 T/L","2019-2020년 북부산전력지사 지중송전 위탁정비공사","345kV 신울산-신온산T/L(B) 케이블헤드 점검(청량C/H)","2020-06-23 13:00","2020-06-23 18:00","취소","취소","연속"]
[240,"부산울산","울산","신울산월성NP#2 T/L","345kV동울산-신울산T/L 계통변경공사","철탑부지변위에 따른 철탑붕괴 대비 및 계통변경공사","2020-06-10 07:00","2020-06-18 18:00","2020-06-10 07:00","2020-06-18 18:00","연속"]
[241,"부산울산","울산","울주신경산#1 T/L","20년 상반기 345kV GIS 정밀점검 공사","7871 CB 정밀점검 시험가압1H","2020-06-03 17:00","2020-06-03 18:00","2020-06-03 17:00","2020-06-03 18:00","연속"]
[242,"부산울산","울산","울주S/S 345kV CB 7871","20년 상반기 345kV GIS 정밀점검 공사","7871 CB 정밀점검","2020-06-01 09:00","2020-06-03 18:00","2020-06-01 09:00","2020-06-03 18:00","연속"]
[243,"부산울산","동부산","고리N/P 345kV SEC CB 76770","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선공사(76-77-0)","2020-06-01 09:00","2020-06-05 18:00","2020-06-01 09:00","2020-06-05 18:00","연속"]
[244,"부산울산","동부산","고리2N/P 345kV #77 BUS","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(76-77-0 - 2시간)","2020-06-05 16:00","2020-06-05 18:00","2020-06-05 16:00","2020-06-05 18:00","연속"]
[245,"부산울산","동부산","고리NP#1고리NP#2 #2 T/L","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선공사(7677)","2020-06-08 09:00","2020-06-12 18:00","2020-06-08 09:00","2020-06-12 18:00","연속"]
[246,"부산울산","동부산","고리2N/P 345kV #76 BUS","고리NP S/Y 현대제 362kV GIS 구조개선공사","고리NP S/Y 현대제 362kV GIS 구조개선 관련 시험가압(7677 - 2시간)","2020-06-12 16:00","2020-06-12 18:00","2020-06-12 16:00","2020-06-12 18:00","연속"]
[247,"경남","직할","신김해S/S #4 M.Tr","신김해S/S 345kV #4M.Tr관련 변전설비 점검","신김해S/S 345kV #4M.Tr 1,2차 GIS 점검, 2차 CB 전자변 교체, 부싱점검, 3차 CB, PT 보통점검","2020-06-15 09:30","2020-06-16 17:30","2020-06-15 09:30","2020-06-16 17:30","연속"]
[248,"경남","직할","신김해S/S #5 M.Tr","신김해S/S 345kV 76BAY TIE CB(7600) 정밀점검","신김해S/S 345kV 76BAY TIE CB(7600) 정밀점검 병행 : CB(7672), CB(6544) 조작시험","2020-06-01 09:00","2020-06-05 18:00","2020-06-01 09:00","2020-06-05 18:00","연속"]
[249,"경남","직할","신김해창원#1 T/L","신김해, 창원S/S 345kV 신김해-창원#1T/L GIS 보통점검","신김해, 창원S/S 345kV 신김해-창원#1T/L GIS 보통점검, 신김해S/S PT, LA보통점검","2020-06-22 09:30","2020-06-23 17:30","2020-06-22 09:30","2020-06-23 17:30","연속"]
[250,"경남","직할","신김해창원#2 T/L","345신김해-창원 송전선로 초기점검","345신김해-창원 송전선로 초기점검","2020-06-08 08:00","2020-06-09 17:00","2020-06-08 08:00","2020-06-09 17:00","매일"]
[251,"경남","진주","산청P/P 345kV CB 7200","산청PP 의령-산청#2T/L-#2M.Tr 1차 CB(7200) 정밀점검","산청PP 의령-산청#2T/L - #2M.Tr 1차 CB(7200) 정밀점검","2020-06-01 09:00","2020-06-01 18:00","취소","취소","연속"]
[252,"경남","통영","창원삼천포TP#1 T/L","345kV 창원-삼천포화력T/L 전선접속개소 교체공사","345kV 창원-삼천포화력#1T/L 전선접속개소 교체공사(86~87호 등 5개구간)","2020-06-08 08:00","2020-06-21 18:00","2020-06-08 08:00","2020-06-21 18:00","연속"]
[253,"경남","통영","삼천포T/P 345kV 삼천포-TIE#2T/L CB A","삼천포,신고성 차단기 용량대체공사","인출철구 설치","2020-06-08 09:00","2020-06-22 18:00","2020-06-08 09:00","2020-06-22 18:00","연속"]
[254,"경남","통영","(신)신고성S/S 345kV CB 7300","(신)신고성 7300 GIS 하자점검","1.(신)신고성 7300 GIS 하자점검","2020-06-04 10:00","2020-06-04 15:00","2020-06-04 10:00","2020-06-04 15:00","연속"]
[255,"경남","통영","(신)신고성S/S 345kV CB 7371","(신)신고성 7371 GIS 하자점검","1.(신)신고성 7371 GIS 하자점검","2020-06-03 10:00","2020-06-03 18:00","2020-06-03 10:00","2020-06-03 18:00","연속"]
[256,"경남","통영","(신)신고성S/S 345kV CB 7B71","(신)신고성 7B71 GIS 하자점검","1. (신)신고성 7B71 GIS 하자점검","2020-06-02 10:00","2020-06-02 18:00","2020-06-02 10:00","2020-06-02 18:00","연속"]
[257,"경남","통영","신고성S/S #1 M.Tr","신고성S/S #1M.Tr 2차 GIS 보통점검 등 3건","1. 신고성S/S #1M.Tr 2차 GIS 보통점검 2. 신고성S/S #1M.Tr 2차 GIS 전자변 교체 3. 신고성S/S 7100, 7172, 7171 GIS 조작시험","2020-06-25 10:00","2020-06-25 18:00","2020-06-25 10:00","2020-06-25 18:00","연속"]
[258,"경남","통영","(신)신고성S/S 345kV CB 7271","(신)신고성 7271 GIS 하자점검","1. (신)신고성 7271 GIS 하자점검","2020-06-12 10:00","2020-06-12 18:00","2020-06-12 10:00","2020-06-12 18:00","연속"]
[259,"경남","통영","(신)신고성S/S 345kV CB 7372","(신)신고성 7372 GIS 하자점검","1.(신)신고성 7372 GIS 하자점검","2020-06-05 10:00","2020-06-05 18:00","2020-06-05 10:00","2020-06-05 18:00","연속"]
[260,"경남","통영","(신)신고성S/S 345kV CB 7471","(신)신고성 7471 GIS 개폐장치 조작시험","1. (신)신고성 7471 GIS 개폐장치 조작시험","2020-06-04 15:00","2020-06-04 18:00","2020-06-04 15:00","2020-06-04 18:00","연속"]
[261,"경기","군포","신온양서서울#1 T/L"," 345kV 신온양서서울외 2개T/L 지장철탑이설공사 "," 345kV 신온양서서울외 2개T/L 지장철탑이설공사 ","2020-06-13 07:00","2020-06-18 18:00","2020-06-13 07:00","2020-06-18 18:00","연속"]
[262,"광주전남",null,"한빛2호기 주변압기(7400,7471)","주변압기 일반점검","주변압기 일반점검","2020-06-03 10:00","2020-08-13 11:00","2020-06-03 10:00","2020-08-13 11:00","연속"]
[263,"광주전남",null,"한빛2호기 기동변압기1(7300,7371)","기동변압기 일반점검","기동변압기 일반점검","2020-06-09 14:00","2020-06-24 08:00","2020-06-09 14:00","2020-06-24 08:00","연속"]
[264,"광주전남",null,"한빛2호기 기동변압기2(7F00,7F71)","기동변압기 일반점검","기동변압기 일반점검","2020-06-30 14:00","2020-07-30 13:00","2020-06-30 14:00","2020-07-30 13:00","연속"]
[265,"경북",null,"예천양수1,2호기 주변압기 CB(7200,7271, 7100,7172)","비상발전기 정밀점검","비상발전기 정밀점검","2020-06-04 13:00","2020-06-04 18:00","2020-06-04 13:00","2020-06-04 18:00","연속"]
[266,"경북",null,"예천양수1,2호기 주변압기 CB(7200,7271, 7100,7172)","자체기동발전기 자체시험","자체기동발전기 자체시험","2020-06-05 14:00","2020-06-05 16:00","2020-06-05 14:00","2020-06-05 16:00","연속"]
[267,"전북",null,"무주양수1,2호기 주변압기 CB(7100,7200)","자체기동발전기 정기시험","자체기동발전기 정기시험","2020-06-05 10:30","2020-06-05 12:30","2020-06-05 10:30","2020-06-05 12:30","연속"]
[268,"경북",null,"예천양수1호기 주변압기 CB(7100,7172)","주변압기 누유부 점검","주변압기 누유부 점검","2020-06-10 09:00","2020-06-10 18:00","2020-06-10 09:00","2020-06-10 18:00","연속"]
[269,"경북",null,"예천양수1,2호기 주변압기 CB(7200,7271, 7100,7172)","자체기동발전기 정기시험","자체기동발전기 정기시험","2020-06-12 10:30","2020-06-12 12:30","2020-06-12 10:30","2020-06-12 12:30","연속"]

{"sheet":"154송부","index":2,"n_rows":649,"n_cols":13,"rows_kept":649,"cut":false,"hidden":false,"merged":[[2,12,3,12],[2,2,3,2],[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2020년도 6월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","창동쌍문#1 T/L","'20년 성동P/O 노후 보호배전반 교체공사","군자, 화양S/S 154kV 군자화양#1T/L 보호배전반 노후대체","2020-05-04 10:00","2020-05-08 17:00","취소","취소","연속"]
[2,"서울","성동","구의광장#1 T/L","20년 성동 변전정비회사 총액공사","장기미동작 GIS 조작시험","2020-06-01 10:00","2020-06-01 18:00","2020-06-01 10:00","2020-06-01 18:00","연속"]
[3,"서울","성동","구의광장#2 T/L","20년 성동 변전정비회사 총액공사","장기미동작 GIS 조작시험","2020-06-02 10:00","2020-06-02 18:00","2020-06-02 10:00","2020-06-02 18:00","연속"]
[4,"서울","성동","구의광장#1 T/L","2020년 성동P/O 변전정비회사 총액공사","2020년 성동P/O 변전정비회사 총액공사 -조작시험, GIS 전자변 교체","2020-06-08 09:30","2020-06-08 14:30","2020-06-08 09:30","2020-06-08 14:30","연속"]
[5,"서울","성동","구의광장#2 T/L","2020년 성동P/O 변전정비회사 총액공사","2020년 성동P/O 변전정비회사 총액공사 -조작시험, GIS 전자변 교체","2020-06-08 14:30","2020-06-08 18:00","2020-06-08 14:30","2020-06-08 18:00","연속"]
[6,"서울","성동","천호구의#2 T/L","2020년 성동P/O 변전정비회사 총액공사","2020년 성동P/O 변전정비회사 총액공사 -조작시험, GIS 전자변 교체","2020-06-09 09:30","2020-06-09 18:00","2020-06-09 09:30","2020-06-09 18:00","연속"]
[7,"서울","성동","노원종암 T/L","장위4구역 전력구 지장전력설비 이설공사","○ 154kV 노원종암T/L M/H#7~10 구간 임시이설(20년) 및 본이설(21년) ○ 154kV 안암노원#1,2T/L M/H#7~10 구간 임시이설(20년) 및 본이설(21년)","2020-06-08 09:00","2020-06-25 18:00","2020-06-08 09:00","2020-06-25 18:00","연속"]
[8,"서울","성동","마장용두 T/L","2020년 성동P/O 변전정비회사 총액공사","2020년 성동P/O 변전정비회사 총액공사 -조작시험, GIS 전자변 교체","2020-06-15 10:00","2020-06-15 18:00","2020-06-15 10:00","2020-06-15 18:00","연속"]
[9,"서울","성동","성동S/S 154kV #60 BUS","2020년 성동P/O 154kV GIS 정밀점검공사","성동S/S 성동군자#1T/L GIS 정밀점검 시험가압","2020-06-18 15:30","2020-06-18 17:30","2020-06-18 15:30","2020-06-18 17:30","연속"]
[10,"서울","성동","성동휘경#1 T/L","2020년 성동P/O 154kV GIS 정밀점검공사","성동S/S 성동휘경#1T/L GIS 정밀점검","2020-06-19 09:30","2020-06-20 17:30","2020-06-19 09:30","2020-06-20 17:30","연속"]
[11,"서울","성동","성동S/S 154kV #61 BUS","2020년 성동P/O 154kV GIS 정밀점검공사","성동S/S 성동휘경#1T/L GIS 정밀점검 시험가압","2020-06-20 15:30","2020-06-20 17:30","2020-06-20 15:30","2020-06-20 17:30","연속"]
[12,"서울","성동","성수뚝도#2 T/L","'20년 성동P/O 노후 보호배전반 교체공사","성수, 뚝도S/S 154kV 성수뚝도#2T/L 보호배전반 노후대체","2020-06-08 10:00","2020-06-11 17:00","취소","취소","연속"]
[13,"서울","성동","성수뚝도#1 T/L","'20년 성동P/O 노후 보호배전반 교체공사","성수, 뚝도S/S 154kV 성수뚝도#1T/L 보호배전반 노후대체","2020-06-01 10:00","2020-06-04 17:00","취소","취소","연속"]
[14,"서울","성동","양주쌍문#2 T/L","2020년 성동PO 변전정비회사 총액공사","170kV GIS 보통점검","2020-06-01 10:00","2020-06-01 18:00","취소","취소","연속"]
[15,"서울","성동","창동돈암 T/L","2020년 성동P/O 변전정비회사 총액공사","2020년 성동P/O 변전정비회사 총액공사 -조작시험, GIS 전자변 교체","2020-06-02 10:30","2020-06-02 15:00","취소","취소","연속"]
[16,"서울","성동","방학창동#2 T/L","2020년 성동P/O 변전정비회사 총액공사","2020년 성동P/O 변전정비회사 총액공사 -조작시험, GIS 전자변 교체","2020-06-02 14:30","2020-06-02 18:00","취소","취소","연속"]
[17,"서울","성동","방학창동#1 T/L","2020년 성동P/O 변전정비회사 총액공사","2020년 성동P/O 변전정비회사 총액공사 -조작시험, GIS 전자변 교체","2020-06-02 10:00","2020-06-02 14:30","취소","취소","연속"]
[18,"서울","중부","순화동빙고 T/L","20년 중부전력지사 170kV GIS 정밀점검공사","ㅇ 동빙고S/S #3M.Tr 1차 GIS 정밀점검(시험가압)","2020-06-10 17:00","2020-06-10 18:00","2020-06-10 17:00","2020-06-10 18:00","연속"]
[19,"서울","중부","동빙고S/S 154kV #60 BUS","20년 중부전력지사 170kV GIS 정밀점검공사","ㅇ 동빙고S/S #3M.Tr 1차 GIS 정밀점검(#60BUS DS 점검 및 시험가압)","2020-06-09 14:00","2020-06-10 18:00","2020-06-09 14:00","2020-06-10 18:00","연속"]
[20,"서울","중부","동빙고S/S 154kV #65 BUS","20년 중부전력지사 170kV GIS 정밀점검공사","ㅇ 동빙고S/S #4M.Tr 1차 GIS 정밀점검(#65BUS DS 점검 및 시험가압)","2020-06-04 14:00","2020-06-05 18:00","2020-06-04 14:00","2020-06-05 18:00","연속"]
[21,"서울","중부","순화동빙고 T/L","20년 중부전력지사 170kV GIS 정밀점검공사","ㅇ 동빙고S/S #4M.Tr 1차 GIS 정밀점검(시험가압)","2020-06-05 17:00","2020-06-05 18:00","2020-06-05 17:00","2020-06-05 18:00","연속"]
[22,"서울","중부","동빙고S/S 154kV #65 BUS","20년 중부전력지사 170kV GIS 정밀점검공사","ㅇ 동빙고S/S #3M.Tr 1차 GIS 정밀점검(#65BUS DS 점검)","2020-06-08 10:00","2020-06-09 14:00","2020-06-08 10:00","2020-06-09 14:00","연속"]
[23,"서울","중부","동빙고S/S 154kV #60 BUS","20년 중부전력지사 170kV GIS 정밀점검공사","ㅇ 동빙고S/S #4M.Tr 1차 GIS 정밀점검(#60BUS DS점검)","2020-06-03 10:00","2020-06-04 14:00","2020-06-03 10:00","2020-06-04 14:00","연속"]
[24,"서울","직할","지축서대문#1 T/L","154kV 현저분기 지중T/L 건설공사","○선종 및 규격 : 154kV XLPE 2,000㎟ ○회선수 및 길이 : 4회선, 0.462km ○케이블포설 : 2구간, 철거 2구간(OF케이블 1구간, XLPE케이블 1구간) ○케이블접속 : 8개소(종단접속 4개소, 중간접속 4개소) ○기타사항 - 현저변전소 최초가압 사용전검사(변전) : 1일 소요","2020-06-22 09:00","2020-07-27 18:00","2020-06-22 09:00","2020-07-27 18:00","연속"]
[25,"서울","직할","운니S/S 154kV #2 BUS","154kV 운니S/S 170kV GIS 설치공사","GIS(170kV 50kA) × 1CCT 기타 부대작업 × 1식","2020-06-01 09:00","2020-06-06 18:00","2020-06-01 09:00","2020-06-06 18:00","연속"]
[26,"서울","직할","운니원남#2 T/L","154kV 운니S/S 170kV GIS 설치공사","GIS(170kV 50kA) × 1CCT 기타 부대작업 × 1식","2020-06-05 15:00","2020-06-06 18:00","2020-06-05 15:00","2020-06-06 18:00","연속"]
[27,"서울","직할","운니S/S 154kV #1 BUS","154kV 운니S/S 170kV GIS 설치공사","GIS(170kV 50kA) × 1CCT 기타 부대작업 × 1식","2020-06-08 09:00","2020-06-12 18:00","2020-06-08 09:00","2020-06-12 18:00","연속"]
[28,"서울","직할","운니원남#1 T/L","154kV 운니S/S 170kV GIS 설치공사","GIS(170kV 50kA) × 1CCT 기타 부대작업 × 1식","2020-06-11 15:00","2020-06-12 18:00","2020-06-11 15:00","2020-06-12 18:00","연속"]
[29,"서울","직할","종로서소문 T/L","20년 직할 170kV GIS 정밀점검공사","종로S/S 170kV 종로서소문T/L GIS 정밀점검공사","2020-06-15 10:00","2020-06-17 18:00","2020-06-22 10:00","2020-06-24 18:00","연속"]
[30,"남서울","강남","논현선릉#2 T/L","2020년 강남전력지사 170kV GIS 정밀점검","2020년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : #2M.Tr 1차 GIS - 무부하대상 :#65BUS, 논현-선릉#2T/L","2020-06-08 15:00","2020-06-08 18:00","2020-06-06 15:00","2020-06-06 18:00","연속"]
[31,"남서울","강남","논현S/S 154kV #65 BUS","2020년 강남전력지사 170kV GIS 정밀점검","2020년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : #2M.Tr 1차 GIS - 무부하대상 :#65BUS, 논현-선릉#2T/L","2020-06-08 15:00","2020-06-08 18:00","2020-06-06 15:00","2020-06-06 18:00","연속"]
[32,"남서울","강남","논현선릉#1 T/L","2020년 강남전력지사 170kV GIS 정밀점검","2020년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 논현-선릉#1T/L GIS","2020-06-12 10:00","2020-06-16 18:00","2020-06-01 09:00","2020-06-03 18:00","연속"]
[33,"남서울","강남","논현S/S 154kV #60 BUS","2020년 강남전력지사 170kV GIS 정밀점검","2020년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : #1M.Tr 1차 GIS - 무부하대상 :#60BUS, 논현-선릉#1T/L","2020-06-03 15:00","2020-06-03 18:00","2020-06-13 15:00","2020-06-13 18:00","연속"]
[34,"남서울","강남","논현선릉#1 T/L","2020년 강남전력지사 170kV GIS 정밀점검","2020년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : #1M.Tr 1차 GIS - 무부하대상 :#60BUS, 논현-선릉#1T/L","2020-06-03 15:00","2020-06-03 18:00","2020-06-13 15:00","2020-06-13 18:00","연속"]
[35,"남서울","강남","대치논현#1 T/L","2020년 강남전력지사 170kV GIS 정밀점검","2020년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 논현-대치#1T/L GIS","2020-06-09 10:00","2020-06-11 18:00","2020-06-08 10:00","2020-06-10 18:00","연속"]
[36,"남서울","강남","역삼S/S 154kV #1 BUS","2020년 강남전력지사 170kV GIS 정밀점검","2020년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 역삼S/S #3M.Tr 1차 GIS - 무부하대상 :#60BUS, 신양재-역삼#1T/L","2020-06-19 15:00","2020-06-19 18:00","2020-06-17 15:00","2020-06-17 18:00","연속"]
[37,"남서울","강남","신양재역삼#1 T/L","2020년 강남전력지사 170kV GIS 정밀점검","2020년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 역삼S/S #3M.Tr 1차 GIS - 무부하대상 :#60BUS, 신양재-역삼#1T/L","2020-06-19 15:00","2020-06-19 18:00","2020-06-17 15:00","2020-06-17 18:00","연속"]
[38,"남서울","강남","역삼S/S 154kV #2 BUS","2020년 강남전력지사 170kV GIS 정밀점검","2020년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 역삼S/S #4M.Tr 1차 GIS - 무부하대상 :#65BUS, 신양재-역삼#2T/L","2020-06-24 15:00","2020-06-24 18:00","2020-06-22 15:00","2020-06-22 18:00","연속"]
[39,"남서울","강남","신양재역삼#2 T/L","2020년 강남전력지사 170kV GIS 정밀점검","2020년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 역삼S/S #4M.Tr 1차 GIS - 무부하대상 :#65BUS, 신양재-역삼#2T/L","2020-06-24 15:00","2020-06-24 18:00","2020-06-22 15:00","2020-06-22 18:00","연속"]
[40,"남서울","동서울","강동풍납#1 T/L","170kV GIS 하자점검","170kV GIS 하자점검","2020-06-11 09:00","2020-06-11 14:00","2020-06-29 09:00","2020-06-29 14:00","연속"]
[41,"남서울","동서울","강동풍납#2 T/L","170kV GIS 하자점검","170kV GIS 하자점검","2020-06-11 14:00","2020-06-11 18:00","2020-06-29 14:00","2020-06-29 18:00","연속"]
[42,"남서울","동서울","동서울송파#2 T/L","154kV 동서울-송파,가락T/L 지중화공사","신설 전력구 시공에 따른 기설 케이블 이동","2020-06-22 08:00","2020-06-26 18:00","2020-06-22 08:00","2020-06-26 18:00","연속"]
[43,"남서울","동서울","동서울가락#2 T/L","154kV 동서울-송파,가락T/L 지중화공사","신설 전력구 시공에 따른 기설 케이블 이동","2020-06-18 08:00","2020-06-20 18:00","2020-06-18 08:00","2020-06-20 18:00","연속"]
[44,"남서울","동서울","상일S/S 154kV #1 BUS","154kV 상일S/S #4M.Tr 증설공사","170kV GIS 1CCT 설치","2020-06-09 09:00","2020-06-13 18:00","2020-06-05 09:00","2020-06-09 18:00","연속"]
[45,"남서울","동서울","강동상일#1 T/L","154kV 상일S/S #4M.Tr 증설공사","170kV GIS 1CCT 설치","2020-06-12 16:00","2020-06-13 18:00","2020-06-08 16:00","2020-06-09 18:00","연속"]
[46,"남서울","동서울","강동상일#1 T/L","154kV 상일S/S #4M.Tr 증설공사","170kV GIS 1CCT 설치","2020-06-17 16:00","2020-06-18 18:00","2020-06-13 16:00","2020-06-14 18:00","연속"]
[47,"남서울","동서울","상일S/S 154kV #2 BUS","154kV 상일S/S #4M.Tr 증설공사","170kV GIS 1CCT 설치","2020-06-14 09:00","2020-06-18 18:00","2020-06-10 09:00","2020-06-14 18:00","연속"]
[48,"남서울","동서울","풍납석촌#1 T/L","송전선로 보호반 교체공사","송전선로 보호반 교체공사","2020-06-08 09:00","2020-06-10 18:00","취소","취소","연속"]
[49,"남서울","동서울","풍납석촌#2 T/L","송전선로 보호반 교체공사","송전선로 보호반 교체공사","2020-06-15 09:00","2020-06-17 18:00","취소","취소","연속"]
[50,"남서울","영등포","마곡가양#2 T/L","가양S/S 170kV GIS 보통점검(마곡-가양#2T/L)","- 차단기 개폐타임 측정 - GIS 조작시험 - 내부 메커니즘 점검 - SF6 수분, SO2 측정","2020-06-12 09:00","2020-06-12 18:00","취소","취소","연속"]
[51,"남서울","영등포","가양등촌#2 T/L","가양S/S 170kV GIS 조작시험(가양-등촌#1,2T/L)","- 차단기 개폐타임 측정 - GIS 조작시험","2020-06-15 14:00","2020-06-15 18:00","취소","취소","연속"]
[52,"남서울","영등포","마곡가양#1 T/L","가양S/S 170kV GIS 보통점검(마곡-가양#1T/L)","- 차단기 개폐타임 측정 - GIS 조작시험 - 내부 메커니즘 점검 - SF6 수분, SO2 측정","2020-06-11 09:00","2020-06-11 18:00","취소","취소","연속"]
[53,"남서울","영등포","가양등촌#1 T/L","가양S/S 170kV GIS 조작시험(가양-등촌#1,2T/L)","- 차단기 개폐타임 측정 - GIS 조작시험","2020-06-15 09:00","2020-06-15 14:00","취소","취소","연속"]
[54,"남서울","영등포","구공S/S 154kV #61 BUS","154kV 신광명-가산SS SW 증설공사","154kV 신광명-가산SS SW 증설공사","2020-06-16 09:00","2020-06-20 15:30","2020-06-16 09:00","2020-06-20 15:30","연속"]
[55,"남서울","영등포","구공S/S 154kV #60 BUS","154kV 신광명-가산SS SW 증설공사","154kV 신광명-가산SS SW 증설공사","2020-06-29 09:00","2020-07-03 15:30","2020-06-29 09:00","2020-07-03 15:30","연속"]
[56,"남서울","영등포","구공S/S 154kV #66 BUS","154kV 신광명-가산SS SW 증설공사","154kV 신광명-가산SS SW 증설공사","2020-06-22 09:00","2020-06-26 15:30","2020-06-22 09:00","2020-06-26 15:30","연속"]
[57,"남서울","영등포","독산대방#1 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-06-09 09:00","2020-06-10 18:00","2020-06-13 09:00","2020-06-14 18:00","연속"]
[58,"남서울","영등포","대방신길#2 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-06-10 15:00","2020-06-12 18:00","2020-06-03 15:00","2020-06-05 18:00","연속"]
[59,"남서울","영등포","대방신길#1 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-06-01 09:00","2020-06-03 18:00","2020-06-01 09:00","2020-06-03 18:00","연속"]
[60,"남서울","영등포","독산대방#2 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-06-11 09:00","2020-06-12 18:00","취소","취소","연속"]
[61,"남서울","영등포","시흥독산#2 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-06-22 09:00","2020-06-26 18:00","취소","취소","연속"]
[62,"남서울","영등포","시흥독산#1 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-06-15 09:00","2020-06-19 18:00","취소","취소","연속"]
[63,"남서울","영등포","양평양천#1 T/L","154kV양평-양천T/L 선종교체공사","○ 위 치 : 양평, 양천S/S 및 목동공동구, 맨홀·전력구 ○ 구 간 : 양평S/S ∼양천S/S ○ 케이블 철거 : 154㎸ OF 1200㎟ × 1회선(B), 2.46㎞ ○ 주요공종 - 케이블 포설구간 : XLPE 1200㎟ × 5구간 ×1C(B)×1.474km XLPE 2000㎟(S) × 3구간 ×1C(S)×1km - 케이블 접속 : 14개소","2020-06-08 09:00","2020-10-20 18:00","2020-06-08 09:00","2020-10-20 18:00","연속"]
[64,"남서울","영등포","오류S/S 154kV #1 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","오류S/S #3M.Tr 1차 GIS 무부하 가압용","2020-06-09 15:00","2020-06-09 16:00","2020-06-17 09:00","2020-06-17 13:00","연속"]
[65,"남서울","영등포","오류목동 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-06-15 09:00","2020-06-16 18:00","2020-06-22 09:00","2020-06-24 18:00","연속"]
[66,"남서울","영등포","오류목동 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","#1BUSTIE 무부하가압용","2020-06-12 15:00","2020-06-12 16:00","2020-06-19 15:00","2020-06-19 17:00","연속"]
[67,"남서울","영등포","오류목동 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","오류S/S #3M.Tr 1차 GIS 무부하 가압용","2020-06-09 15:00","2020-06-09 16:00","2020-06-17 09:00","2020-06-17 13:00","연속"]
[68,"남서울","영등포","오류S/S 154kV CB 6100","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-06-11 09:00","2020-06-12 18:00","2020-06-17 13:00","2020-06-19 18:00","연속"]
[69,"남서울","영등포","오류S/S 154kV #1 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","#1BUSTIE 무부하가압용","2020-06-11 09:00","2020-06-12 18:00","2020-06-17 13:00","2020-06-19 18:00","연속"]
[70,"남서울","영등포","천왕오류#2 T/L","천왕,오류S/S 천왕-오류#2T/L GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-06-01 15:00","2020-06-05 18:00","취소","취소","연속"]
[71,"남서울","영등포","화곡마곡#2 T/L","화곡S/S 170kV GIS 조작시험(화곡-마곡#1,2T/L)","- 차단기 개폐타임 측정 - GIS 조작시험","2020-06-10 14:00","2020-06-10 18:00","취소","취소","연속"]
[72,"남서울","영등포","화곡마곡#1 T/L","화곡S/S 170kV GIS 조작시험(화곡-마곡#1,2T/L)","- 차단기 개폐타임 측정 - GIS 조작시험","2020-06-10 09:00","2020-06-10 14:00","취소","취소","연속"]
[73,"남서울","영등포","고강화곡#2 T/L","화곡S/S 170kV GIS 조작시험(고강-화곡#2T/L)","- 차단기 개폐타임 측정 - GIS 조작시험","2020-06-09 14:00","2020-06-09 18:00","취소","취소","연속"]
[74,"남서울","영등포","고강화곡#1 T/L","화곡S/S 170kV GIS 조작시험(고강-화곡#1T/L)","- 차단기 개폐타임 측정 - GIS 조작시험","2020-06-09 09:00","2020-06-09 14:00","취소","취소","연속"]
[75,"남서울","영등포","중동화곡#2 T/L","화곡S/S 170kV GIS 조작시험","- 차단기 개폐타임 측정 - GIS 조작시험","2020-06-08 14:00","2020-06-08 18:00","취소","취소","연속"]
[76,"남서울","영등포","중동화곡#1 T/L","화곡S/S 170kV GIS 조작시험","- 차단기 개폐타임 측정 -GIS 조작시험","2020-06-08 09:00","2020-06-08 14:00","취소","취소","연속"]
[77,"남서울","직할","노들노량진 T/L","170kV GIS 보통점검","노들S/S 170kV GIS 보통점검 노량진S/S 170kV GIS 조작시험","2020-06-05 10:00","2020-06-05 18:00","2020-06-05 10:00","2020-06-05 18:00","연속"]
[78,"인천","김포","경서양촌#1 T/L","기중종단접속함(EBA) PD진단센서 및 집합반 설치공사","기중종단접속함(EBA) PD진단센서 및 집합반 설치공사 - 대상 : 경서-양촌#1T/L(D) 경서C/H 12상 - 내용 : PD센서 설치 및 케이블 포설, 집합반 설치","2020-06-01 09:00","2020-06-03 18:00","2020-06-01 09:00","2020-06-03 18:00","연속"]
[79,"인천","김포","경서양촌#2 T/L","기중종단접속함(EBA) PD진단센서 및 집합반 설치공사","기중종단접속함(EBA) PD진단센서 및 집합반 설치공사 - 대상 : 경서-양촌#2T/L(D) 경서C/H 12상 - 내용 : PD센서 설치 및 케이블 포설, 집합반 설치","2020-06-04 09:00","2020-06-06 18:00","2020-06-04 09:00","2020-06-06 18:00","연속"]
[80,"인천","김포","김포장기#2 T/L","154kV 신경서-영종 등 2개T/L 병행지선 설치공사","154kV 신경서-영종, 김포-장기T/L 병행지선 설치","2020-06-24 09:00","2020-06-25 18:00","2020-06-24 09:00","2020-06-25 18:00","연속"]
[81,"인천","김포","김포장기#1 T/L","154kV 신경서-영종 등 2개T/L 병행지선 설치공사","154kV 신경서-영종, 김포-장기T/L 병행지선 설치","2020-06-22 09:00","2020-06-23 18:00","2020-06-22 09:00","2020-06-23 18:00","연속"]
[82,"인천","김포","신김포S/S 154kV SEC CB 65660","신김포S/S #64M.Tr 증설공사 관련 170kV GIS 설치공사","신김포S/S #64M.Tr 증설공사 관련 170kV GIS 설치공사 - 모선연결작업 - 무부하가압","2020-06-29 09:00","2020-07-03 18:00","2020-06-29 09:00","2020-07-03 18:00","연속"]
[83,"인천","김포","신김포장기#1T/L","신김포S/S #64M.Tr 증설공사 관련 170kV GIS 설치공사","신김포S/S #64M.Tr 증설공사 관련 170kV GIS 설치공사 - #64M.Tr 1차 GIS 무부하가압용","2020-06-30 09:00","2020-07-01 18:00","2020-06-30 09:00","2020-07-01 18:00","연속"]
[84,"인천","김포","신김포양곡#1 T/L","양곡S/S 154kV 신김포-양곡#1T/L GIS 조작시험","양곡S/S 154kV 신김포-양곡#1T/L GIS 조작시험(전자변 교체 병행)","2020-06-08 10:00","2020-06-08 18:00","2020-06-08 10:00","2020-06-08 18:00","연속"]
[85,"인천","김포","신김포양곡#2 T/L","양곡S/S 154kV 신김포-양곡#2T/L GIS 조작시험","양곡S/S 154kV 신김포-양곡#2T/L GIS 조작시험(전자변 교체 병행)","2020-06-09 10:00","2020-06-09 18:00","2020-06-09 10:00","2020-06-09 18:00","연속"]
[86,"인천","김포","양곡S/S 154kV CB 6100","양곡S/S 154kV #60-#65 BUS TIE GIS 조작시험","양곡S/S 154kV #60-#65 BUS TIE GIS 조작시험","2020-06-05 10:00","2020-06-05 18:00","2020-06-05 10:00","2020-06-05 18:00","연속"]
[87,"인천","김포","신경서왕길#1 T/L","기중종단접속함(EBA) PD진단센서 및 집합반 설치공사","기중종단접속함(EBA) PD진단센서 및 집합반 설치공사 - 대상 : 신경서-왕길#1T/L 왕길#1, #2C/H 6상 - 내용 : PD센서 설치 및 케이블 포설, 집합반 설치","2020-06-08 09:00","2020-06-12 18:00","2020-06-08 09:00","2020-06-12 18:00","연속"]
[88,"인천","김포","신경서왕길#2 T/L","기중종단접속함(EBA) PD진단센서 및 집합반 설치공사","기중종단접속함(EBA) PD진단센서 및 집합반 설치공사 - 대상 : 신경서-왕길#2T/L 왕길#1, #2C/H 6상 - 내용 : PD센서 설치 및 케이블 포설, 집합반 설치","2020-06-15 09:00","2020-06-19 18:00","2020-06-15 09:00","2020-06-19 18:00","연속"]
[89,"인천","부평","관교S/S 154kV CB 6100","관교S/S 154kV 6100 BUS TIE GIS 보통점검","관교S/S 154kV 6100 BUS TIE GIS 보통점검","2020-06-30 09:00","2020-06-30 18:00","2020-06-30 09:00","2020-06-30 18:00","연속"]
[90,"인천","부평","신경서서인천CC T/L","서인천C/C 154kV 서인천CC-신경서T/L GIS 보통점검","서인천C/C 154kV 서인천CC-신경서T/L GIS 보통점검","2020-06-29 09:00","2020-06-29 18:00","2020-06-26 09:00","2020-06-26 18:00","연속"]
[91,"인천","부평","신현송현#1 T/L","송현S/S 신현-송현#1T/L GIS 보통점검","- 송현S/S 신현-송현#1T/L GIS 보통점검","2020-06-08 09:00","2020-06-08 18:00","2020-06-08 09:00","2020-06-08 18:00","연속"]
[92,"인천","부평","신현송현#2 T/L","송현S/S 신현-송현#2T/L GIS 보통점검","- 송현S/S 신현-송현#2T/L GIS 보통점검","2020-06-09 09:00","2020-06-09 18:00","2020-06-09 09:00","2020-06-09 18:00","연속"]
[93,"인천","부평","신가좌신현#1 T/L","신가좌S/S 154kV 신가좌-신현#1T/L GIS 보통점검","- 신가좌S/S 154kV 신가좌-신현#1T/L GIS 보통점검","2020-06-10 09:00","2020-06-10 18:00","2020-06-10 09:00","2020-06-10 18:00","연속"]
[94,"인천","부평","신가좌신현#2 T/L","신가좌S/S 154kV 신가좌-신현#2T/L GIS 보통점검","- 신가좌S/S 154kV 신가좌-신현#2T/L GIS 보통점검","2020-06-11 09:00","2020-06-11 18:00","2020-06-11 09:00","2020-06-11 18:00","연속"]
[95,"인천","부평","신가좌주안#2 T/L","신가좌S/S 154kV 신가좌-주안#2T/L GIS 조작시험","신가좌S/S 154kV 신가좌-주안#2T/L GIS 조작시험","2020-06-30 09:00","2020-06-30 18:00","2020-06-30 09:00","2020-06-30 18:00","연속"]
[96,"인천","부평","신가좌주안#1 T/L","신가좌S/S 154kV 신가좌-주안#1T/L GIS 조작시험","신가좌S/S 154kV 신가좌-주안#1T/L GIS 조작시험","2020-06-18 14:00","2020-06-18 18:00","2020-06-18 14:00","2020-06-18 18:00","연속"]
[97,"인천","부평","신가좌인천#1 T/L","신가좌S/S 154kV 신가좌-인천#1T/L GIS 조작시험","- 신가좌S/S 154kV 신가좌-인천#1T/L GIS 조작시험","2020-06-18 09:00","2020-06-18 14:00","2020-06-18 09:00","2020-06-18 14:00","연속"]
[98,"인천","부평","신경서경서#3 T/L","신경서S/S 154kV 신경서-경서#3T/L GIS 보통점검","신경서S/S 154kV 신경서-경서#3T/L GIS 보통점검","2020-06-19 09:00","2020-06-19 18:00","2020-06-19 09:00","2020-06-19 18:00","연속"]
[99,"인천","부평","신경서영종 T/L","154kV 신경서-영종 등 2개T/L 병행지선 설치공사","영종전력구 병행지선 설치(813m)","2020-06-29 09:00","2020-06-30 18:00","2020-06-29 09:00","2020-06-30 18:00","연속"]
[100,"인천","부평","북인천원창 T/L","154㎸ 북인천-원창 등 2개 T/L 병행지선 보강 공사","154㎸ 북인천-원창 등 2개 T/L 병행지선 보강 공사 북인천-원창T/L : #JB 3~5 인천CC-북인천T/L : #JB 6~7","2020-06-29 08:00","2020-06-29 18:00","2020-06-29 08:00","2020-06-29 18:00","연속"]
[101,"인천","부평","신가좌인천#2 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2020-06-01 09:00","2020-06-02 18:00","2020-06-01 09:00","2020-06-02 18:00","연속"]
[102,"인천","부평","신가좌인천#3 T/L","154kV 신가좌-인천#3T/L SVL 설치공사","구형 SVL 교체","2020-06-23 09:00","2020-06-25 18:00","2020-06-23 09:00","2020-06-25 18:00","연속"]
[103,"인천","부평","인천S/S 154kV CB 6100","인천S/S 154kV 6100 BUS TIE GIS 보통점검","인천S/S 154kV 6100 BUS TIE GIS 보통점검","2020-06-24 09:00","2020-06-24 18:00","2020-06-24 09:00","2020-06-24 18:00","연속"]
[104,"인천","부평","인천C/C 154kV SEC CB 60610","인천CC S/Y 154kV #60-#61 SEC GIS 보통점검","인천CC S/Y 154kV #60-#61 SEC GIS 보통점검","2020-06-22 09:00","2020-06-22 18:00","2020-06-22 09:00","2020-06-22 18:00","연속"]
[105,"인천","부평","인천C/C 154kV SEC CB 65660","인천CC S/Y 154kV #65-#66 SEC GIS 보통점검","인천CC S/Y 154kV #65-#66 SEC GIS 보통점검","2020-06-23 09:00","2020-06-23 18:00","2020-06-23 09:00","2020-06-23 18:00","연속"]
[106,"인천","부평","인천CC북인천#2 T/L","154㎸ 북인천-원창 등 2개 T/L 병행지선 보강 공사","154㎸ 북인천-원창 등 2개 T/L 병행지선 보강 공사 북인천-원창T/L : #JB 3~5 인천CC-북인천T/L : #JB 6~7","2020-06-30 08:00","2020-06-30 18:00","2020-06-30 08:00","2020-06-30 18:00","연속"]
[107,"인천","부평","학익연수#2 T/L","학익S/S 154kV 학익-연수#2T/L 보호반 대체 공사","학익S/S 154kV 학익-연수#2T/L 보호반 대체 공사","2020-06-08 09:00","2020-06-12 18:00","2020-06-15 09:00","2020-06-19 18:00","연속"]
[108,"인천","시흥","남동동춘 T/L","남동,동춘S/S 154kV 남동동춘TL GIS보통점검","남동,동춘S/S 154kV 남동동춘TL GIS보통점검","2020-06-01 10:00","2020-06-01 18:00","2020-06-01 10:00","2020-06-01 18:00","연속"]
[109,"인천","시흥","신시흥남동#1 T/L","154kV 신시흥-남동#1T/L SVL 교체공사","154kV 신시흥-남동#1T/L SVL 교체공사","2020-06-02 09:00","2020-06-04 18:00","2020-06-02 09:00","2020-06-04 18:00","연속"]
[110,"인천","시흥","오봉남동#1 T/L","남동S/S 154kV 오봉남동#1TL GIS보통점검","남동S/S 154kV 오봉남동#1TL GIS보통점검","2020-06-02 10:00","2020-06-02 18:00","2020-06-02 10:00","2020-06-02 18:00","연속"]
[111,"인천","시흥","신시흥남동#2 T/L","154kV 신시흥-남동#2T/L SVL 교체공사","154kV 신시흥-남동#2T/L SVL 교체공사","2020-06-09 09:00","2020-06-11 18:00","2020-06-09 09:00","2020-06-11 18:00","연속"]
[112,"인천","시흥","동시화서시화 T/L","동시화,서시화S/S 154kV 동시화서시화TL 보호반대체","동시화,서시화S/S 154kV 동시화서시화TL 보호반대체","2020-06-01 10:00","2020-06-05 18:00","2020-06-01 10:00","2020-06-05 18:00","연속"]
[113,"인천","시흥","신광명소래 T/L","소래S/S 154kV 신광명소래TL GIS보통점검","소래S/S 154kV 신광명소래TL GIS보통점검","2020-06-04 10:00","2020-06-04 18:00","2020-06-04 10:00","2020-06-04 18:00","연속"]
[114,"인천","시흥","서서울#2소래 T/L","소래S/S 154kV 서서울2소래 GIS조작시험","소래S/S 154kV 서서울2소래 GIS조작시험","2020-06-08 10:00","2020-06-08 18:00","2020-06-08 10:00","2020-06-08 18:00","연속"]
[115,"인천","시흥","신시흥도림#2 T/L","154kV 신시흥-남동T/L 지장송전선로 이설공사","○ 구간 : 154kV 신시흥-남동T/L No.16~18(하단:신시흥-도림T/L) ○ 내용 : 임시철탑 설치(No.17)","2020-06-23 07:00","2020-06-24 18:00","취소","취소","연속"]
[116,"인천","시흥","신시흥도림#1 T/L","154kV 신시흥-남동T/L 지장송전선로 이설공사","○ 구간 : 154kV 신시흥-남동T/L No.16~18(하단:신시흥-도림T/L) ○ 내용 : 임시철탑 설치(No.17)","2020-06-25 07:00","2020-06-26 18:00","취소","취소","연속"]
[117,"인천","시흥","신시흥남동#1 T/L","154kV 신시흥-남동T/L 지장송전선로 이설공사","○ 구간 : 154kV 신시흥-남동T/L No.16~18(하단:신시흥-도림T/L) ○ 내용 : 임시철탑 설치(No.17)","2020-06-25 07:00","2020-06-26 18:00","취소","취소","연속"]
[118,"인천","시흥","신시흥남동#2 T/L","154kV 신시흥-남동T/L 지장송전선로 이설공사","○ 구간 : 154kV 신시흥-남동T/L No.16~18(하단:신시흥-도림T/L) ○ 내용 : 임시철탑 설치(No.17)","2020-06-23 07:00","2020-06-24 18:00","취소","취소","연속"]
[119,"인천","직할","계양김포#1 T/L","계양김포#1T/L 광케이블 시설공사","계양S/S-김포S/S 광케이블 시설(OPGW 3.575km, OFC 3.181km)","2020-06-15 09:00","2020-06-19 18:00","2020-06-15 09:00","2020-06-19 18:00","연속"]
[120,"인천","직할","고강S/S 154kV CB 6100","고강S/S 6100 BUS TIE 170kV GIS 강화조작시험","고강S/S 6100 BUS TIE 170kV GIS 강화조작시험","2020-06-05 09:30","2020-06-05 18:00","2020-06-05 09:30","2020-06-05 18:00","연속"]
[121,"인천","직할","고강화곡#1 T/L","154kV 고강S/S SW 증설공사(#2BUS 무부하)","고강S/S 154kV SW 증설공사(고강화곡#1T/L 이용 무부하가압) - 154kV GIS 1CCT 설치 - 기타부대공사","2020-06-13 18:00","2020-06-14 18:00","2020-06-13 18:00","2020-06-14 18:00","연속"]
[122,"인천","직할","고강화곡#1 T/L","154kV 고강S/S SW 증설공사(#1BUS 무부하)","고강S/S 154kV SW 증설공사(고강화곡#1T/L 이용 무부하가압) - 154kV GIS 1CCT 설치 - 기타부대공사","2020-06-06 18:00","2020-06-07 18:00","2020-06-06 18:00","2020-06-07 18:00","연속"]
[123,"인천","직할","신부평도당#2 T/L","신부평,도당S/S 신부평도당#2T/L 보통점검(양단)","신부평,도당S/S 신부평도당#2T/L 신부평(보통), 도당(초기)","2020-06-03 09:30","2020-06-03 18:00","2020-06-03 09:30","2020-06-03 18:00","연속"]
[124,"인천","직할","신부평도당#1 T/L","신부평,도당S/S 신부평도당#1T/L 보통점검(양단)","신부평,도당S/S 신부평도당#1T/L 신부평(보통), 도당(초기)","2020-06-02 09:30","2020-06-02 18:00","2020-06-02 09:30","2020-06-02 18:00","연속"]
[125,"인천","직할","신부평중동#3 T/L","신부평,중동S/S 신부평중동#3T/L 보통점검(양단)","신부평,중동S/S 신부평중동#3T/L 신부평(강화조작), 중동(초기)","2020-06-10 09:30","2020-06-10 18:00","2020-06-10 09:30","2020-06-10 18:00","연속"]
[126,"인천","직할","신부평중동#2 T/L","신부평,중동S/S 신부평중동#2T/L 보통점검(양단)","신부평,중동S/S 신부평중동#2T/L 신부평(강화조작), 중동(초기)","2020-06-09 09:30","2020-06-09 18:00","2020-06-09 09:30","2020-06-09 18:00","연속"]
[127,"인천","직할","신부평중동#1 T/L","신부평,중동S/S 신부평중동#1T/L 보통점검(양단)","신부평,중동S/S 신부평중동#1T/L 신부평(보통), 중동(초기)","2020-06-08 09:30","2020-06-08 18:00","2020-06-08 09:30","2020-06-08 18:00","연속"]
[128,"인천","직할","신부평S/S 154kV SEC CB 65660","신부평S/S 65-66-0 BUS SEC 보통점검","신부평S/S 65-66-0 BUS SEC 보통점검","2020-06-05 14:00","2020-06-05 18:00","2020-06-05 14:00","2020-06-05 18:00","연속"]
[129,"인천","직할","신부평S/S 154kV SEC CB 60610","신부평S/S 60-61-0 BUS SEC 보통점검","신부평S/S 60-61-0 BUS SEC 보통점검","2020-06-05 09:30","2020-06-05 14:00","2020-06-05 09:30","2020-06-05 14:00","연속"]
[130,"인천","직할","신부평고강#2 T/L","신부평,고강S/S 신부평고강#2T/L 강화조작시험(양단)","신부평,고강S/S 신부평고강#2T/L 강화조작시험(양단)","2020-06-20 14:00","2020-06-20 18:00","취소","취소","연속"]
[131,"인천","직할","신부평고강#1 T/L","신부평,고강S/S 신부평고강#1T/L 강화조작시험(양단)","신부평,고강S/S 신부평고강#1T/L 강화조작시험(양단)","2020-06-20 09:30","2020-06-20 14:00","취소","취소","연속"]
[132,"인천","직할","신부평고강#2 T/L","20~21년 부평전력지사 가공송전 정비회사 총액공사","20~21년 부평전력지사 가공송전 정비회사 총액공사 활선애자청소","2020-06-02 08:00","2020-06-03 18:00","취소","취소","매일"]
[133,"인천","직할","신부평고강#1 T/L","20~21년 부평전력지사 가공송전 정비회사 총액공사","20~21년 부평전력지사 가공송전 정비회사 총액공사 활선애자청소","2020-06-02 08:00","2020-06-03 18:00","취소","취소","매일"]
[134,"인천","직할","신부평임학#2 T/L","신부평,임학S/S 170kV 신부평임학#2T/L 송전선로 보호반 대체","신부평,임학S/S 170kV 신부평임학#2T/L 송전선로 보호반 대체 신부평(강화조작), 임학(조작)","2020-06-29 09:30","2020-07-03 18:00","2020-06-29 09:30","2020-07-03 18:00","연속"]
[135,"인천","직할","신부평임학#1 T/L","신부평,임학S/S 170kV 신부평임학#1T/L 송전선로 보호반 대체","신부평,임학S/S 170kV 신부평임학#1T/L 송전선로 보호반 대체 신부평(강화조작), 임학(조작)","2020-06-22 09:30","2020-06-26 18:00","2020-06-22 09:30","2020-06-26 18:00","연속"]
[136,"인천","직할","신부평S/S 154kV CB 6100","신부평S/S 60-65 BUS TIE 보통점검","신부평S/S 60-65 BUS TIE 보통점검","2020-06-15 09:30","2020-06-15 18:00","2020-06-15 09:30","2020-06-15 18:00","연속"]
[137,"경기북부","고양","남면백석#2 T/L","345kV 신파주-양주 등 11개T/L 항공시설물 정비공사","345kV 신덕은-동두천CC#2T/L 가공지선 항공구 설치공사 안전이격거리 확보 휴전","2020-06-16 07:00","2020-06-16 18:00","2020-06-16 07:00","2020-06-16 18:00","연속"]
[138,"경기북부","고양","남면백석#1 T/L","고양전력지사 관내 T/L OPGW 항공장애표시구 시설공","345kV 신덕은-동두천CC#1T/L OPGW용 항공장애 표시구 설치 안전이격거리 확보 휴전","2020-06-22 07:00","2020-06-24 18:00","2020-06-22 07:00","2020-06-24 18:00","연속"]
[139,"경기북부","고양","문발덕이#2 T/L","2020년 상반기 고양P/O 170kV GIS 정밀점검공사","2020년 상반기 고양P/O 170kV GIS 정밀점검공사(문발-덕이#2T/L)","2020-06-03 09:30","2020-06-04 18:00","2020-06-03 09:30","2020-06-04 18:00","연속"]
[140,"경기북부","고양","문발덕이#1 T/L","2020년 상반기 고양P/O 170kV GIS 정밀점검공사","2020년 상반기 고양P/O 170kV GIS 정밀점검공사(문발-덕이#1T/L)","2020-06-01 09:30","2020-06-02 18:00","2020-06-01 09:30","2020-06-02 18:00","연속"]
[141,"경기북부","고양","신덕은문산#1T/L","2020~2021 고양전력지사 변전정비회사 총액공사","송전선로 보호반 교체공사","2020-06-08 09:00","2020-06-11 18:00","2020-06-23 09:00","2020-06-26 18:00","연속"]
[142,"경기북부","고양","신덕은문산#2T/L","2020~2021 고양전력지사 변전정비회사 총액공사","송전선로 보호반 교체공사","2020-06-15 09:00","2020-06-18 18:00","2020-06-30 09:00","2020-07-03 18:00","연속"]
[143,"경기북부","고양","문산월롱#1 T/L","고양전력지사 관내 T/L OPGW 항공장애표시구 시설공","154kV 신덕은-문산#1T/L OPGW용 항공장애 표시구 설치 안전이격거리 확보 휴전","2020-06-08 07:00","2020-06-08 18:00","취소","취소","연속"]
[144,"경기북부","고양","일산송포#2T/L","2020 고양P/O 변전정비회사 총액공사(일산-송포#2T/L)","170kV GIS 하자점검","2020-06-17 09:30","2020-06-18 18:00","2020-06-17 09:30","2020-06-18 18:00","연속"]
[145,"경기북부","고양","신파주송포#2 T/L","154kV 신파주-송포 #2T/L OF케이블 선종교체공사","OF 케이블 2,000sq → XLPE 2,000sq 선종교체공사","2020-06-22 09:00","2020-07-31 18:00","2020-06-22 09:00","2020-07-31 18:00","연속"]
[146,"경기북부","고양","일산송포#1 T/L","2020 고양P/O 변전정비회사 총액공사(일산-송포#1T/L)","170kV GIS 하자점검","2020-06-15 09:30","2020-06-16 18:00","2020-06-15 09:30","2020-06-16 18:00","연속"]
[147,"경기북부","고양","신덕은S/S 154kV SEC CB 65660","2020 고양P/O 변전정비회사 총액공사(신덕은 #65-66BUSSEC)","170kV GIS 보통점검","2020-06-24 10:00","2020-06-24 18:00","2020-06-24 10:00","2020-06-24 18:00","연속"]
[148,"경기북부","고양","신덕은S/S 154kV SEC CB 60610","2020 고양P/O 변전정비회사 총액공사(신덕은 #60-61BUSSEC)","170kV GIS 보통점검","2020-06-23 10:00","2020-06-23 18:00","2020-06-23 10:00","2020-06-23 18:00","연속"]
[149,"경기북부","고양","신덕은S/S 154kV CB 6200","2020 고양P/O 변전정비회사 총액공사(신덕은 #6200BUSTIE)","170kV GIS 보통점검","2020-06-05 10:00","2020-06-05 18:00","2020-06-05 10:00","2020-06-05 18:00","연속"]
[150,"경기북부","고양","신덕은S/S 154kV CB 6100","2020 고양P/O 변전정비회사 총액공사(신덕은 #6100BUSTIE)","170kV GIS 보통점검","2020-06-03 10:00","2020-06-03 18:00","2020-06-03 10:00","2020-06-03 18:00","연속"]
[151,"경기북부","고양","신덕은금촌#1 T/L","2020년 가공송전선로 순시점검 위탁공사","ㅇ 345kV 신파주-신덕은T/L 정밀점검 안전이격거리 확보 휴전","2020-06-10 07:00","2020-06-10 18:00","취소","취소","연속"]
[152,"경기북부","고양","신덕은금촌#2 T/L","2020년 가공송전선로 순시점검 위탁공사","ㅇ 345kV 신파주-신덕은T/L 정밀점검 안전이격거리 확보 휴전","2020-06-09 07:00","2020-06-09 18:00","취소","취소","연속"]
[153,"경기북부","고양","월롱금촌#1 T/L","345kV 신파주-양주 등 11개T/L 항공시설물 정비공사","345kV 신덕은-동두천CC#2T/L 가공지선 항공구 설치공사 안전이격거리 확보 휴전","2020-06-18 07:00","2020-06-18 18:00","2020-06-18 07:00","2020-06-18 18:00","연속"]
[154,"경기북부","고양","일산호수#1 T/L","'20~'21년 고양전력지사 변전정비회사 총액공사","송전선로 보호배전반 교체공사","2020-06-02 09:00","2020-06-05 18:00","취소","취소","연속"]
[155,"경기북부","고양","양주지축#1 T/L","2020년 가공송전선로 순시점검 위탁공사","ㅇ 정밀점검","2020-06-11 07:00","2020-06-12 18:00","2020-06-04 07:00","2020-06-05 18:00","연속"]
[156,"경기북부","고양","양주지축#2 T/L","2020년 가공송전선로 순시점검 위탁공사","ㅇ 정밀점검","2020-06-09 07:00","2020-06-10 18:00","2020-06-02 07:00","2020-06-03 18:00","연속"]
[157,"경기북부","구리","가평화천HP T/L","765kV 신안성-신가평 등 13개T/L 항공장애시설물 정비공사","ㅇ 항공장애표시구 설치 - 154kV 가평-화천HP T/L No.133~134","2020-06-23 09:00","2020-06-23 18:00","2020-06-23 09:00","2020-06-23 18:00","연속"]
[158,"경기북부","구리","가평청평HP#2 T/L","2020년 가공송전 순시점검 위탁공사","154kV 가평-청평HPT/L 정밀점검","2020-06-22 08:00","2020-06-26 18:00","2020-06-22 08:00","2020-06-26 18:00","연속"]
[159,"경기북부","구리","덕소팔당HP T/L","`20~21 구리전력 변전정비 총액공사","덕소S/S 154kV 덕소-팔당HP T/L GIS 초기점검공사","2020-06-08 09:30","2020-06-08 14:00","2020-06-08 09:30","2020-06-08 14:00","연속"]
[160,"경기북부","구리","덕소팔당HP청평HP T/L","`20~21년 구리전력 변전정비 총액공사","덕소S/S 덕소-팔당-청평HP T/L GIS 초기점검공사 청평H/P 덕소-팔당-청평HP T/L GCB 조작시험","2020-06-10 09:00","2020-06-10 18:00","2020-06-10 09:00","2020-06-10 18:00","연속"]
[161,"경기북부","구리","미금S/S 154kV #60 BUS","미금S/S 170kV 장기사용 GIS대체공사(7차분)","- 미금구리#1T/L 철거, 설치","2020-06-17 09:00","2020-06-17 15:00","2020-06-17 15:00","2020-06-17 16:00","연속"]
[162,"경기북부","구리","미금S/S 154kV #65 BUS","미금S/S 170kV 장기사용 GIS대체공사(7차분)","- 미금구리#1T/L 철거, 설치","2020-06-12 08:00","2020-06-17 18:00","2020-06-12 08:00","2020-06-17 15:00","연속"]
[163,"경기북부","구리","미금S/S 154kV #60 BUS","미금S/S 170kV 장기사용 GIS대체공사(7차분)","- 미금구리#1T/L 철거, 설치","2020-06-09 08:00","2020-06-12 08:00","2020-06-09 08:00","2020-06-12 08:00","연속"]
[164,"경기북부","구리","미금덕소#1 T/L","미금S/S 170kV 장기사용 GIS대체공사(7차분)-안전이격거리확보","- 미금구리#1T/L 철거, 설치","2020-06-08 08:00","2020-06-16 18:00","2020-06-08 08:00","2020-06-16 18:00","매일"]
[165,"경기북부","구리","미금구리#1 T/L","미금S/S 170kV 장기사용 GIS대체공사(7차분)","- 미금구리#1T/L 철거, 설치","2020-06-08 08:00","2020-06-17 18:00","2020-06-08 08:00","2020-06-17 18:00","연속"]
[166,"경기북부","구리","미금S/S 154kV #65 BUS","미금S/S 170kV 장기사용 GIS대체공사(7차분)","- 미금구리#1T/L 철거, 설치","2020-06-08 08:00","2020-06-09 08:00","2020-06-08 08:00","2020-06-09 08:00","연속"]
[167,"경기북부","구리","미금S/S 154kV #60 BUS","미금S/S 170kV 장기사용 GIS대체공사(6차분)","- 미금덕소#1T/L 철거, 설치 - 미금구리#2T/L 철거, 설치","2020-06-06 09:00","2020-06-06 18:00","2020-06-06 09:00","2020-06-06 18:00","연속"]
[168,"경기북부","구리","서종청평PP#1 T/L","2020년 가공송전 순시점검 위탁공사","154kV 서종-청평PPT/L 정밀점검","2020-06-08 08:00","2020-06-12 18:00","취소","취소","연속"]
[169,"경기북부","구리","서종청평PP#2 T/L","2020년 가공송전 순시점검 위탁공사","154kV 서종-청평PPT/L 정밀점검","2020-06-15 08:00","2020-06-19 18:00","취소","취소","연속"]
[170,"경기북부","구리","신포천백학#1 T/L","20~21년 경기북부 직할 가공송전정비회사 총액공사","ㅇ 345kV 신덕은-동두천CC#2T/L 병가선로 - 불량애자교체","2020-06-15 08:00","2020-06-15 18:00","2020-06-15 08:00","2020-06-15 18:00","연속"]
[171,"경기북부","구리","신포천백학#2 T/L","20~21년 경기북부 직할 가공송전정비회사 총액공사","ㅇ 345kV 신덕은-동두천CC#1T/L 병가선로 - 압축인류크램프 및 점퍼선교체","2020-06-22 08:00","2020-06-22 18:00","2020-06-22 08:00","2020-06-22 18:00","연속"]
[172,"경기북부","구리","운천S/S 154kV CB 6100","`20~21년 구리전력 변전정비 총액공사","운천S/S 154kV BUS-TIE GIS 조작시험 및 전자변교체","2020-06-16 09:30","2020-06-16 18:00","2020-06-16 09:30","2020-06-16 18:00","연속"]
[173,"경기북부","구리","청평P/P 154kV CB 6133","`20~21년 구리전력 변전정비 총액공사","청평P/P 154kV #1M.Tr 2차 GCB 조작시험 및 전자변 교체","2020-06-05 09:00","2020-06-05 18:00","취소","취소","연속"]
[174,"경기북부","구리","청평P/P 154kV CB 6233","`20~21 구리전력 변전정비 총액공사","청평P/P 154kV #2M.Tr 차단기 (6233) 조작시험, 전자변 교체","2020-06-02 09:00","2020-06-02 18:00","2020-06-11 09:00","2020-06-11 18:00","연속"]
[175,"경기북부","직할","녹양백석#2 T/L","양주S/S GIS화관련 154kV 인출T/L 지중화공사","154kV 양주-녹양#1, 쌍문#2T/L 시험 가압","2020-06-12 18:00","2020-06-14 18:00","2020-06-15 09:00","2020-06-16 18:00","연속"]
[176,"경기북부","직할","도봉S/S 154kV CB 6100","20~21 직할 변전정비회사 총액공사","□ 도봉S/S 154kV BUS-TIE GCB 개폐타임 측정","2020-06-23 09:00","2020-06-23 18:00","2020-06-23 09:00","2020-06-23 18:00","연속"]
[177,"경기북부","직할","신의정부S/S 154kV #60 BUS","신의정부S/S 154kV DS부 발청 하자보수","신의정부 #2 M.Tr 2차 DS부 발청제거","2020-06-30 09:00","2020-07-01 18:00","2020-06-30 09:00","2020-07-01 18:00","연속"]
[178,"경기북부","직할","신의정부S/S 154kV #66 BUS","신의정부S/S 154kV DS부 발청 하자보수","신의정부-금오 #1 T/L DS 발청제거 신의정부-금오 #2 T/L DS 발청제거 66BUS PT 발청제거","2020-06-01 09:00","2020-06-04 18:00","2020-06-01 09:00","2020-06-02 18:00","연속"]
[179,"경기북부","직할","양주은평#2 T/L","2020년 가공송전선로 순시점검 위탁공사","ㅇ 154kV 양주-지축#1T/L 정밀점검 안전이격거리 확보 휴전","2020-06-11 07:00","2020-06-12 18:00","2020-06-04 07:00","2020-06-05 18:00","연속"]
[180,"경기북부","직할","양주은평#1 T/L","2020년 가공송전선로 순시점검 위탁공사","ㅇ 154kV 양주-지축#2T/L 정밀점검 안전이격거리 확보 휴전","2020-06-09 07:00","2020-06-10 18:00","2020-06-02 07:00","2020-06-03 18:00","연속"]
[181,"경기북부","직할","양주S/S 154kV #65 BUS","양주S/S GIS화관련 154kV 인출T/L 지중화공사","154kV 양주-녹양#1, 쌍문#2T/L 시험 가압","2020-06-13 18:00","2020-06-14 18:00","2020-06-16 00:00","2020-06-16 18:00","연속"]
[182,"경기북부","직할","양주S/S 154kV #60 BUS","양주S/S GIS화관련 154kV 인출T/L 지중화공사","154kV 양주-녹양#1, 쌍문#2T/L 시험 가압","2020-06-12 18:00","2020-06-13 18:00","2020-06-15 09:00","2020-06-16 00:00","연속"]
[183,"경기북부","직할","운천전곡#1 T/L","전곡S/S 운천-전곡 #1 T/L A상 노즐 교체공사","전곡S/S 운천-전곡 #1 T/L A상 노즐 교체공사","2020-06-29 08:00","2020-07-02 18:00","2020-06-30 08:00","2020-07-03 18:00","연속"]
[184,"경기","군포","남군포산본#2 T/L","남군포S/S 남군포-산본#2T/L GIS 초기점검","남군포S/S 남군포-산본#2T/L GIS 초기점검, 산본S/S 남군포-산본#2T/L GIS 초기점검","2020-06-26 14:00","2020-06-26 18:00","2020-06-26 14:00","2020-06-26 18:00","연속"]
[185,"경기","군포","남군포산본#1 T/L","남군포S/S 남군포-산본#1T/L GIS 초기점검","남군포S/S 남군포-산본#1T/L GIS 초기점검, 산본S/S 남군포-산본#1T/L GIS 초기점검","2020-06-26 09:00","2020-06-26 14:00","2020-06-26 09:00","2020-06-26 14:00","연속"]
[186,"경기","군포","반월시화#2 T/L","반월S/S 반월-시화#2T/L 보호반대체 및 GIS 하자점검","반월S/S 반월-시화#2T/L 보호반대체 및 GIS 하자점검, 시화S/S 반월-시화#2T/L 보호반대체 및 GIS 보통점검","2020-06-30 09:00","2020-07-02 18:00","2020-06-30 09:00","2020-07-02 18:00","연속"]
[187,"경기","군포","서서울#2일동#1 T/L","서서울#2S/S 서서울2-일동#1T/L GIS 조작시험","서서울#2S/S 서서울2-일동#1T/L GIS 조작시험, 일동S/S 서서울2-일동#1T/L GIS 조작시험","2020-06-09 09:00","2020-06-09 14:00","2020-06-09 09:00","2020-06-09 14:00","연속"]
[188,"경기","군포","서서울#2봉담#2 T/L","서서울#2S/S 서서울2-봉담#2T/L GIS 조작시험","서서울#2S/S 서서울2-봉담#2T/L GIS 조작시험","2020-06-01 14:00","2020-06-01 18:00","2020-06-01 14:00","2020-06-01 18:00","연속"]
[189,"경기","군포","서서울#2소래 T/L","서서울#2S/S 서서울2-소래 T/L GIS 조작시험","서서울#2S/S 서서울2-소래 T/L GIS 조작시험","2020-06-10 14:00","2020-06-10 18:00","2020-06-10 14:00","2020-06-10 18:00","연속"]
[190,"경기","군포","서서울#2일동#2 T/L","서서울#2S/S 서서울2-일동#2T/L GIS 조작시험","서서울#2S/S 서서울2-일동#2T/L GIS 조작시험, 일동S/S 서서울2-일동#2T/L GIS 조작시험","2020-06-09 14:00","2020-06-09 18:00","2020-06-09 14:00","2020-06-09 18:00","연속"]
[191,"경기","군포","서안양소래 T/L","서안양S/S 서안양-소래T/L GIS 조작시험","서안양S/S 서안양-소래T/L GIS 조작시험","2020-06-29 09:00","2020-06-29 18:00","2020-06-29 09:00","2020-06-29 18:00","연속"]
[192,"경기","군포","서서울#2서안양 T/L","154kV 서안양S/S #4M.Tr 증설공사","#4M.Tr 무부하가압","2020-06-01 18:00","2020-06-02 18:00","2020-06-01 18:00","2020-06-02 18:00","연속"]
[193,"경기","군포","서서울#2서안양 T/L","20년 군포PO 170kV GIS 정밀점검-서안양SS 서서울2서안양TL","서안양SS 서서울2-서안양T/L GIS 정밀점검공사, 서서울#2S/S 서서울2-서안양T/L GIS 조작시험","2020-06-03 09:00","2020-06-05 18:00","2020-06-03 09:00","2020-06-05 18:00","연속"]
[194,"경기","군포","반월시화#1 T/L","시화S/S 반월-시화#1T/L 누기개소 보수 및 보통점검","시화S/S 반월-시화#1T/L 누기개소 보수(인출 상부측)","2020-06-01 09:00","2020-06-02 18:00","취소","취소","연속"]
[195,"경기","군포","신시흥시화#2 T/L","시화S/S 신시흥-시화#2T/L GIS 조작시험","시화S/S 신시흥-시화#2T/L GIS 조작시험","2020-06-09 14:00","2020-06-09 18:00","2020-06-09 14:00","2020-06-09 18:00","연속"]
[196,"경기","군포","시화동시화#2 T/L","시화S/S 시화-동시화#2T/L GIS 보통점검","시화S/S 시화-동시화#2T/L GIS 보통점검","2020-06-15 14:00","2020-06-15 18:00","취소","취소","연속"]
[197,"경기","군포","시화중시화 T/L","시화S/S 시화-중시화T/L 보호반대체 및 GIS 조작시험","시화S/S 시화-중시화T/L GIS 조작시험, 중시화S/S 시화-중시화T/L GIS 보통점검, 양단 보호반 대체","2020-06-23 09:00","2020-06-25 18:00","2020-06-23 09:00","2020-06-25 18:00","연속"]
[198,"경기","군포","신시흥시화#1 T/L","시화S/S 신시흥-시화#1T/L GIS 조작시험","시화S/S 신시흥-시화#1T/L GIS 조작시험","2020-06-09 09:00","2020-06-09 14:00","2020-06-09 09:00","2020-06-09 14:00","연속"]
[199,"경기","군포","시화동시화#1 T/L","시화S/S 시화-동시화#1T/L GIS 조작시험","시화S/S 시화-동시화#1T/L GIS 조작시험","2020-06-15 09:00","2020-06-15 14:00","취소","취소","연속"]
[200,"경기","동부","곤지암초월#2 T/L","20년 동부 변전정비회사 총액공사","곤지암:곤지암-초월#2T/L GIS(보통), 43L/R 회로보완 확인 및 Remote 회로분리 시행 초월:곤지암-초월#2T/L GIS(보통),전자변 실리콘히터 설치, 43L/R 회로보완 확인 및 Remote 회로분리 시행","2020-06-11 09:30","2020-06-11 18:00","2020-06-11 09:30","2020-06-11 18:00","연속"]
[201,"경기","동부","동판교야탑 T/L","20년 동부 변전정비회사 총액공사","동판교:동판교-야탑T/L GIS(보통), 43L/R 회로보완 확인 및 Remote 회로분리 시행 야탑:동판교-야탑T/L GIS(조작),GIS전자변교체(H),전자변 실리콘히터 설치,43L/R 회로보완 확인 및 Remote 회로분리 시행","2020-06-30 09:30","2020-06-30 18:00","2020-06-30 09:30","2020-06-30 18:00","연속"]
[202,"경기","동부","모현용인#1 T/L","154kV 모현S/S SW 신규수용공사","○ 모현-에버랜드#2T/L- 최초가압","2020-06-09 09:00","2020-06-10 18:00","2020-06-09 09:00","2020-06-10 18:00","연속"]
[203,"경기","동부","산성수서#1 T/L","20년 동부 변전정비회사 총액공사","산성:산성-수서#1T/L(조작),GIS전자변교체,43L/R 회로보완 확인 및 Remote 회로분리 시행 산성-수서#2T/L(조작),GIS전자변교체,43L/R 회로보완 확인 및 Remote 회로분리 시행","2020-06-03 09:30","2020-06-03 14:00","2020-06-03 09:30","2020-06-03 14:00","연속"]
[204,"경기","동부","산성수서#2 T/L","20년 동부 변전정비회사 총액공사","산성:산성-수서#1T/L(조작),GIS전자변교체,43L/R 회로보완 확인 및 Remote 회로분리 시행 산성-수서#2T/L(조작),GIS전자변교체,43L/R 회로보완 확인 및 Remote 회로분리 시행","2020-06-03 14:00","2020-06-03 18:00","2020-06-03 14:00","2020-06-03 18:00","연속"]
[205,"경기","동부","성현산성#1 T/L","20년 동부 변전정비회사 총액공사","성현:산성-성현#1T/L(조작),GIS전자변교체,43L/R 회로보완 확인 및 Remote 회로분리 시행 산성-성현#2T/L(조작),GIS전자변교체,전자변 실리콘히터 설치,43L/R 회로보완 확인 및 Remote 회로분리 시행","2020-06-08 09:30","2020-06-08 14:00","2020-06-08 09:30","2020-06-08 14:00","연속"]
[206,"경기","동부","성현산성#2 T/L","20년 동부 변전정비회사 총액공사","성현:산성-성현#1T/L(조작),GIS전자변교체,43L/R 회로보완 확인 및 Remote 회로분리 시행 산성-성현#2T/L(조작),GIS전자변교체,전자변 실리콘히터 설치,43L/R 회로보완 확인 및 Remote 회로분리 시행","2020-06-08 14:00","2020-06-08 18:00","2020-06-08 14:00","2020-06-08 18:00","연속"]
[207,"경기","동부","중원야탑 T/L","20년 동부 변전정비회사 총액공사","야탑:중원-야탑T/L(조작),GIS전자변교체(H),전자변 실리콘히터 설치, 43L/R 회로보완 확인 및 Remote 회로분리 시행,중원,야탑S/S 중원-야탑T/L 세니온 성능개선","2020-06-12 09:30","2020-06-12 18:00","2020-06-12 09:30","2020-06-12 18:00","연속"]
[208,"경기","동부","초월성현#2 T/L","154kV 초월-성현#2T/L 송전선로 정밀점검","송전선로 정밀점검 - 1~59호 전구간","2020-06-01 08:00","2020-06-05 18:00","2020-06-01 08:00","2020-06-05 18:00","매일"]
[209,"경기","동부","곤지암초월#2 T/L","154kV 초월-성현#2T/L 송전선로 정밀점검(안전상 휴전)","송전선로 정밀점검 - 1~59호 전구간","2020-06-03 08:00","2020-06-05 18:00","2020-06-03 08:00","2020-06-05 18:00","매일"]
[210,"경기","성남","신갈수원열병합 T/L","신갈S/S 154kV GIS 대체","GIS 대체(통열T/L)","2020-06-01 09:00","2020-06-19 18:00","2020-06-01 09:00","2020-06-19 18:00","연속"]
[211,"경기","성남","신성남서판교#1 T/L","20년 성남전력 변전정비회사 총액공사","보통점검 및 전자변교체","2020-06-18 09:00","2020-06-18 18:00","2020-06-18 09:00","2020-06-18 18:00","연속"]
[212,"경기","성남","신수원S/S 154kV CB 6300","20년 성남전력 154kV GIS 정밀점검","신수원S/S 154kV #62-#67 BUS-TIE GIS 정밀점검","2020-06-10 14:00","2020-06-13 18:00","2020-06-10 14:00","2020-06-13 18:00","연속"]
[213,"경기","성남","신수원북동탄#1 T/L","20년 성남전력 154kV GIS 정밀점검","신수원S/S #62-67 BUS-TIE GIS 무부하가압","2020-06-12 09:00","2020-06-12 18:00","2020-06-12 09:00","2020-06-12 18:00","연속"]
[214,"경기","성남","신수원북동탄#1 T/L","20년 성남전력 154kV GIS 정밀점검","신수원S/S #3M.Tr 2차측 GIS 무부하가압","2020-06-10 09:00","2020-06-10 14:00","2020-06-10 09:00","2020-06-10 14:00","연속"]
[215,"경기","성남","신수원S/S 154kV #62 BUS","20년 성남전력 154kV GIS 정밀점검","신수원S/S 154kV 북동탄#2T/L #1DS 점검 및 무부하가압","2020-06-04 14:00","2020-06-06 18:00","취소","취소","연속"]
[216,"경기","성남","신수원북동탄#2 T/L","20년 성남전력 154kV GIS 정밀점검","정밀점검","2020-06-03 14:00","2020-06-06 18:00","2020-06-03 14:00","2020-06-06 18:00","연속"]
[217,"경기","성남","신수원S/S 154kV #67 BUS","20년 성남전력 154kV GIS 정밀점검","신수원S/S 154kV 북동탄#1T/L #2DS 점검 및 무부하가압 신수원S/S 154kV 북동탄#2T/L #2DS 점검 및 무부하가압","2020-06-02 14:00","2020-06-04 14:00","취소","취소","연속"]
[218,"경기","성남","신수원S/S 154kV #62 BUS","20년 성남전력 154kV GIS 정밀점검","신수원S/S 154kV 북동탄#1T/L #1DS 점검 및 무부하가압","2020-06-01 09:00","2020-06-02 14:00","취소","취소","연속"]
[219,"경기","성남","신수원북동탄#1 T/L","20년 성남전력 154kV GIS 정밀점검","정밀점검","2020-06-01 09:00","2020-06-03 14:00","2020-06-01 09:00","2020-06-03 14:00","연속"]
[220,"경기","성남","신용인S/S 154kV #1 EM.Tr CB","20년 성남전력 변전정비회사 총액공사","신용인:#1EM.Tr(보통) - 1차 LA(보통), 1차 N LA(보통) - 1차 GIS(보통) - 2차 EGIS(보통), 1,2 ES.Tr EGIS(보통) - E6100 EGIS(보통), #1,2,3,4,5,6 ESS EGIS(보통)","2020-06-01 09:00","2020-06-05 18:00","2020-06-01 09:00","2020-06-05 18:00","연속"]
[221,"경기","성남","신용인용인#1 T/L","'20~'21년 송전정비회사 총액공사","154kV 신용인-동백#2 송전선로 피뢰기 설치공사 (1~5호) - 4회선 병가구간 안전이격거리 확보","2020-06-11 08:00","2020-06-11 12:00","2020-06-09 08:00","2020-06-09 18:00","연속"]
[222,"경기","성남","신용인동백#2 T/L","'20~'21년 송전정비회사 총액공사","345kV S/S 인출 154kV 송전선로 피뢰기 설치공사 (1~5호)","2020-06-11 08:00","2020-06-11 18:00","2020-06-11 08:00","2020-06-11 18:00","연속"]
[223,"경기","성남","신용인용인#2 T/L","'20~'21년 송전정비회사 총액공사","345kV S/S 인출 154kV 송전선로 피뢰기 설치공사 (23~27호)","2020-06-09 08:00","2020-06-10 18:00","2020-06-10 08:00","2020-06-11 18:00","매일"]
[224,"경기","성남","신용인동백#1 T/L","'20~'21년 송전정비회사 총액공사","154kV 신용인-용인#2 송전선로 피뢰기 설치공사 (23~27호) -4회선 병가구간 안전 이격거리 확보","2020-06-09 08:00","2020-06-09 12:00","취소","취소","연속"]
[225,"경기","성남","신용인S/S 154kV SEC CB 65660","20년 성남전력 변전정비회사 총액공사","신용인S/S 154kV #65-#66 SEC GIS 조작시험","2020-06-04 14:00","2020-06-04 18:00","2020-06-04 14:00","2020-06-04 18:00","연속"]
[226,"경기","성남","신용인S/S 154kV SEC CB 60610","20년 성남전력 변전정비회사 총액공사","신용인S/S 154kV #60-#61 SEC GIS 조작시험","2020-06-04 09:00","2020-06-04 14:00","2020-06-04 09:00","2020-06-04 14:00","연속"]
[227,"경기","성남","오천용인#2 T/L","효성제 토크불량개소 보수","효성제 토크불량개소 보수","2020-06-23 14:00","2020-06-23 18:00","2020-06-23 14:00","2020-06-23 18:00","연속"]
[228,"경기","성남","용인남사#2 T/L","효성제 토크불량개소 보수","효성제 토크불량개소 보수","2020-06-08 14:00","2020-06-08 18:00","2020-06-08 14:00","2020-06-08 18:00","연속"]
[229,"경기","성남","용인남사#1 T/L","효성제 토크불량개소 보수","효성제 토크불량개소 보수","2020-06-08 09:00","2020-06-08 14:00","2020-06-08 09:00","2020-06-08 14:00","연속"]
[230,"경기","성남","모현용인#1 T/L","효성제 토크불량개소 보수","효성제 토크불량개소 보수","2020-06-22 09:00","2020-06-22 14:00","2020-06-22 09:00","2020-06-22 14:00","연속"]
[231,"경기","성남","오천용인#1 T/L","효성제 토크불량개소 보수","효성제 토크불량개소 보수","2020-06-23 09:00","2020-06-23 14:00","2020-06-23 09:00","2020-06-23 14:00","연속"]
[232,"경기","성남","모현용인#2 T/L","효성제 토크불량개소 보수","효성제 토크불량개소 보수","2020-06-22 14:00","2020-06-22 18:00","2020-06-22 14:00","2020-06-22 18:00","연속"]
[233,"경기","직할","조암구문천#2 T/L","20년 직할 변전정비회사 총액공사","구문천S/S 조암-구문천 #2T/L 보통","2020-06-30 09:00","2020-06-30 18:00","2020-06-30 09:00","2020-06-30 18:00","연속"]
[234,"경기","직할","조암구문천#1 T/L","20년 직할 변전정비회사 총액공사","구문천S/S 조암-구문천 #1T/L 보통","2020-06-29 09:00","2020-06-29 18:00","2020-06-29 09:00","2020-06-29 18:00","연속"]
[235,"경기","직할","봉담남수원#2 T/L","봉담-송산간 3공구 도로개설 관련 지장이설공사","154kV 봉담-남수원T/L 43~48호 3기 신설","2020-06-18 07:00","2020-06-22 18:00","2020-06-18 07:00","2020-06-22 18:00","연속"]
[236,"경기","직할","봉담남수원#1 T/L","봉담-송산간 3공구 도로개설 관련 지장이설공사","154kV 봉담-남수원T/L 43~48호 3기 신설","2020-06-23 07:00","2020-06-27 18:00","2020-06-23 07:00","2020-06-27 18:00","연속"]
[237,"경기","직할","과천동안양#2 T/L","2020년 직할 변전정비회사 총액공사","ㅇ154kV 차단기 공기압 조작방식 전자변 교체","2020-06-11 10:00","2020-06-11 18:00","2020-06-11 10:00","2020-06-11 18:00","연속"]
[238,"경기","직할","과천동안양#1 T/L","154kV 동안양S/S 옥내화 공사","ㅇ 과천-동안양#1T/L 철거 후 옥내화 이설","2020-06-22 10:00","2022-06-30 18:00","2020-06-22 10:00","2022-06-30 18:00","연속"]
[239,"경기","직할","의왕동안양#2 T/L","154kV 동안양S/S 옥내화 공사","ㅇ 의왕-동안양#2T/L 이설","2020-06-22 10:00","2020-06-26 18:00","2020-06-22 10:00","2020-06-26 18:00","연속"]
[240,"경기","직할","관양동안양#1 T/L","2020년 직할 변전정비회사 총액공사","ㅇ154kV 차단기 공기압 조작방식 전자변 교체","2020-06-29 09:00","2020-06-29 14:00","2020-06-29 09:00","2020-06-29 14:00","연속"]
[241,"경기","직할","동안양안양CC#1 T/L","20년 직할 변전정비회사 총액공사","동안양S/S 안열#1T/L GIS 조작 안양복합S/S 동안양-안열#1T/L GIS 초기","2020-06-12 09:00","2020-06-12 18:00","2020-06-12 09:00","2020-06-12 18:00","연속"]
[242,"경기","직할","동안양안양CC#2 T/L","20년 직할 변전정비회사 총액공사","동안양S/S 안열 #2T/L 조작 안양복합S/S 동안양-안열 #2T/L 초기","2020-06-17 09:00","2020-06-17 18:00","2020-06-17 09:00","2020-06-17 18:00","연속"]
[243,"경기","직할","화성발안#1 T/L","154kV 화성-발안#1T/L 송전선로 정밀점검","154kV 화성-발안#1T/L(No.1~18) 송전선로 정밀점검, 피뢰기 설치(1~5호)","2020-06-16 09:00","2020-06-16 18:00","2020-06-16 09:00","2020-06-16 18:00","연속"]
[244,"경기","직할","발안S/S 154kV #65 BUS","2020년 직할 154kV GIS 정밀점검공사","발안-향남#2T/L #2DS 정밀점검","2020-06-11 13:00","2020-06-12 18:00","2020-06-11 13:00","2020-06-12 18:00","연속"]
[245,"경기","직할","발안S/S 154kV #60 BUS","2020년 직할 154kV GIS 정밀점검공사","발안-향남#2T/L #1DS 정밀점검","2020-06-10 09:00","2020-06-11 13:00","2020-06-10 09:00","2020-06-11 13:00","연속"]
[246,"경기","직할","발안S/S 154kV #65 BUS","2020년 직할 154kV GIS 정밀점검공사","발안-향남#1T/L #2DS 정밀점검","2020-06-08 13:00","2020-06-09 18:00","2020-06-08 13:00","2020-06-09 18:00","연속"]
[247,"경기","직할","발안S/S 154kV #60 BUS","2020년 직할 154kV GIS 정밀점검공사","발안-향남#1T/L #1DS 정밀점검","2020-06-07 09:00","2020-06-08 13:00","2020-06-07 09:00","2020-06-08 13:00","연속"]
[248,"경기","직할","화성발안#2 T/L","154kV 화성-발안#2T/L 송전선로 정밀점검","154kV 화성-발안#2T/L(No.1~18) 송전선로 정밀점검","2020-06-17 09:00","2020-06-17 18:00","2020-06-17 09:00","2020-06-17 18:00","연속"]
[249,"경기","직할","서서울#2봉담#1 T/L","20년 직할 변전정비회사 총액공사","봉담S/S 서서울2-봉담#1T/L 초기","2020-06-02 09:00","2020-06-02 18:00","2020-06-02 09:00","2020-06-02 18:00","연속"]
[250,"경기","직할","서서울서수원#2 T/L","서수원변전소 23kV 현대화공사","154kV 서서울-서수원#2T/L 보호배전반 이설","2020-06-11 09:00","2020-06-13 18:00","2020-06-11 09:00","2020-06-13 18:00","연속"]
[251,"경기","직할","서서울서수원#1 T/L","서수원변전소 23kV 현대화공사","154kV 서서울-서수원#1T/L 보호배전반 이설","2020-06-08 09:00","2020-06-10 18:00","2020-06-08 09:00","2020-06-10 18:00","연속"]
[252,"경기","직할","서수원율전#1 T/L","서수원변전소 23kV 현대화공사","154kV 서수원-율전#1T/L 보호배전반 교체","2020-06-15 09:00","2020-06-17 18:00","2020-06-15 09:00","2020-06-17 18:00","연속"]
[253,"경기","직할","서수원율전#2 T/L","서수원변전소 23kV 현대화공사","154kV 서수원-율전#2T/L 보호배전반 교체","2020-06-18 09:00","2020-06-20 18:00","2020-06-18 09:00","2020-06-20 18:00","연속"]
[254,"경기","직할","서수원호매실#2 T/L","서수원변전소 23kV 현대화공사","154kV 서수원-호매실#2T/L 보호배전반 이설","2020-06-04 09:00","2020-06-06 18:00","취소","취소","연속"]
[255,"경기","직할","서수원호매실#1 T/L","서수원변전소 23kV 현대화공사","154kV 서수원-호매실#1T/L 보호배전반 이설","2020-06-01 09:00","2020-06-03 18:00","취소","취소","연속"]
[256,"경기","직할","서서울서수원#1 T/L","서수원E/C 현대화관련 OPGW 및 인입 광케이블 이설공사","* No.2 ~ No.3 OP-S-L24→48 교체 0.312km * 서수원S/S ICT실 ~ No.2 FOFC-S-24→48 교체 0.200km * 접속, 최종시험 및 기타 부대공사 1식","2020-06-18 09:00","2020-06-18 18:00","2020-06-18 09:00","2020-06-18 18:00","연속"]
[257,"경기","직할","서서울율전#1 T/L","2020년 직할 변전정비회사 총액공사","ㅇ154kV 차단기 공기압 조작방식 전자변 교체","2020-06-30 09:00","2020-06-30 14:00","2020-06-30 09:00","2020-06-30 14:00","연속"]
[258,"경기","직할","서서울율전#2 T/L","2020년 직할 변전정비회사 총액공사","ㅇ154kV 차단기 공기압 조작방식 전자변 교체","2020-06-30 14:00","2020-06-30 18:00","2020-06-30 14:00","2020-06-30 18:00","연속"]
[259,"경기","직할","안양평촌#2 T/L","2020년 직할 변전정비회사 총액공사","ㅇ154kV 차단기 공기압 조작방식 전자변 교체","2020-06-29 14:00","2020-06-29 18:00","2020-06-29 14:00","2020-06-29 18:00","연속"]
[260,"경기","직할","발안향남#1 T/L","20년 직할 변전정비회사 총액공사","발안S/S 발안-향남#1T/L GIS 정밀점검공사 향남S/S 발안-향남#1T/L GIS 보통 (TM-IED Cap 연결선 단선) 발안S/S 발안-향남#1T/L LA 하자","2020-06-07 09:00","2020-06-09 18:00","2020-06-07 09:00","2020-06-09 18:00","연속"]
[261,"경기","직할","오산향남#2 T/L","20년 직할 변전정비회사 총액공사","향남S/S 오산-향남#2T/L GIS 보통","2020-06-05 09:00","2020-06-05 18:00","2020-06-05 09:00","2020-06-05 18:00","연속"]
[262,"경기","직할","발안향남#2 T/L","20년 직할 변전정비회사 총액공사","발안S/S 발안-향남#2T/L GIS 정밀점검공사 향남S/S 발안-향남#2T/L GIS 보통 발안S/S 발안-향남#2T/L LA 하자","2020-06-10 09:00","2020-06-12 18:00","2020-06-10 09:00","2020-06-12 18:00","연속"]
[263,"경기","직할","오산향남#1 T/L","20년 직할 변전정비회사 총액공사","향남S/S 오산-향남#1T/L GIS 보통","2020-06-04 09:00","2020-06-04 18:00","2020-06-04 09:00","2020-06-04 18:00","연속"]
[264,"경기","직할","화성S/S 154kV #60 BUS","2020년 직할 154kV GIS 정밀점검공사","화성-마도T/L 정밀점검공사","2020-06-14 09:00","2020-06-14 18:00","2020-06-14 09:00","2020-06-14 18:00","연속"]
[265,"경기","직할","화성마도 T/L","2020년 직할 154kV GIS 정밀점검공사","화성-마도T/L 정밀점검공사","2020-06-13 09:00","2020-06-14 18:00","2020-06-13 09:00","2020-06-14 18:00","연속"]
[266,"경기","직할","화성남양#2 T/L","2020년 직할 변전정비회사 총액공사","ㅇ154kV 차단기 공기압 조작방식 전자변 교체","2020-06-20 14:00","2020-06-20 18:00","2020-06-20 14:00","2020-06-20 18:00","연속"]
[267,"경기","직할","화성남양#1 T/L","2020년 직할 변전정비회사 총액공사","ㅇ154kV 차단기 공기압 조작방식 전자변 교체","2020-06-20 09:00","2020-06-20 14:00","2020-06-20 09:00","2020-06-20 14:00","연속"]
[268,"경기","평택","고덕평택#1 T/L","154kV 동평택S/S 건설사업","154kV 동평택S/S 변전설비 최초가압","2020-06-29 13:00","2020-06-30 13:00","2020-06-29 13:00","2020-06-30 13:00","연속"]
[269,"경기","평택","고덕송탄#1 T/L","고덕S/S 154kV 고덕-송탄#1T/L GIS 하자점검","고덕S/S 154kV 고덕-송탄#1T/L GIS 하자점검","2020-06-09 10:00","2020-06-09 18:00","2020-06-09 10:00","2020-06-09 18:00","연속"]
[270,"경기","평택","고덕송탄#2 T/L","고덕S/S 154kV 고덕-송탄#2T/L GIS 하자점검","고덕S/S 154kV 고덕-송탄#2T/L GIS 하자점검","2020-06-10 10:00","2020-06-10 18:00","2020-06-10 10:00","2020-06-10 18:00","연속"]
[271,"경기","평택","고덕평택#2 T/L","고덕,평택S/S 154kV 고덕-평택#2T/L GIS 하자점검","고덕,평택S/S 154kV 고덕-평택#2T/L GIS 하자점검","2020-06-03 10:00","2020-06-03 18:00","2020-06-03 10:00","2020-06-03 18:00","연속"]
[272,"경기","평택","고덕평택#1 T/L","고덕,평택S/S 154kV 고덕-평택#1T/L GIS 하자점검","고덕,평택S/S 154kV 고덕-평택#1T/L GIS 하자점검","2020-06-02 10:00","2020-06-02 18:00","2020-06-02 10:00","2020-06-02 18:00","연속"]
[273,"경기","평택","원정만호#1 T/L","2020년 평택전력지사 170kV GIS 정밀점검공사","2020년 평택전력지사 170kV GIS 정밀점검공사 / 원정,만호S/S 원정-만호#1T/L GIS 정밀점검공사","2020-06-22 09:00","2020-06-27 18:00","2020-06-22 09:00","2020-06-27 18:00","연속"]
[274,"경기","평택","서안성남사#1 T/L","'20~'21년 송전정비회사 총액공사","송전용 피뢰기 설치공사 (1~20호)","2020-06-15 08:00","2020-06-19 18:00","취소","취소","매일"]
[275,"경기","평택","서안성S/S 154kV #1 EM.Tr CB","서안성S/S 154kV #1 EM.Tr A 변압기 보통점검","서안성S/S 154kV #1 EM.Tr A 변압기 보통점검 / 보호반 성능 개선 / 1차,2차 GIS 보통점검","2020-06-10 10:00","2020-06-12 18:00","2020-06-10 10:00","2020-06-12 18:00","연속"]
[276,"경기","평택","서안성안성#2 T/L","'20~'21년 송전정비회사 총액공사","154kV 서안성-남사#1T/L 송전용 피뢰기 설치공사 (1~20호) - 4회선 병가구간 안전이격거리 확보","2020-06-15 08:00","2020-06-15 18:00","취소","취소","연속"]
[277,"경기","평택","서안성안성#1 T/L","'20~'21년 송전정비회사 총액공사","345kV S/S 인출 154kV 송전선로 피뢰기 설치공사 (30~34호)","2020-06-22 08:00","2020-06-23 18:00","취소","취소","매일"]
[278,"경기","평택","서안성남사#2 T/L","'20~'21년 송전정비회사 총액공사","345kV S/S 인출 154kV 송전선로 피뢰기 설치공사 (1~5호)","2020-06-22 08:00","2020-06-22 18:00","취소","취소","매일"]
[279,"경기","평택","서운안성#2 T/L","154kV 서운-안성T/L 정밀점검","154kV 서운-안성T/L 정밀점검 - #1T/L : 안성S/S~No.28 - #2T/L : 안성S/S~No.42","2020-06-27 09:00","2020-06-27 18:00","2020-06-27 09:00","2020-06-27 18:00","연속"]
[280,"경기","평택","서운안성#1 T/L","154kV 서운-안성T/L 정밀점검","154kV 서운-안성T/L 정밀점검 - #1T/L : 안성S/S~No.28 - #2T/L : 안성S/S~No.42","2020-06-13 09:00","2020-06-14 18:00","2020-06-13 09:00","2020-06-14 18:00","매일"]
[281,"경기","평택","서운안성#2 T/L","154kV 서운-안성T/L 정밀점검","154kV 서운-안성T/L 정밀점검 - #1T/L : 안성S/S~No.28 - #2T/L : 안성S/S~No.42","2020-06-20 09:00","2020-06-21 18:00","2020-06-20 09:00","2020-06-21 18:00","매일"]
[282,"경기","평택","진위동탄#2 T/L","154kV 진위S/S #4M.Tr 증설공사","#65BUS 무부하가압","2020-06-04 18:00","2020-06-05 18:00","2020-06-04 18:00","2020-06-05 18:00","연속"]
[283,"경기","평택","진위동탄#2 T/L","154kV 진위S/S #4M.Tr 증설공사","#60BUS 무부하가압","2020-06-11 18:00","2020-06-12 18:00","2020-06-11 18:00","2020-06-12 18:00","연속"]
[284,"경기","평택","만호청북#1 T/L","청북S/S 154kV 만호-청북T/L GIS 보통점검","청북S/S 154kV 만호-청북T/L GIS 보통점검","2020-06-26 10:00","2020-06-26 18:00","2020-06-26 10:00","2020-06-26 18:00","연속"]
[285,"경기","평택","평택TP평택CC#2 T/L","평택C/C 154kV LNG#2T/L 전자변 교체 및 GIS 보통점검","평택C/C 154kV LNG#2T/L 전자변 교체 및 GIS 보통점검","2020-06-25 10:00","2020-06-25 18:00","2020-06-25 10:00","2020-06-25 18:00","연속"]
[286,"경기","평택","포승청북 T/L","2020년 평택전력지사 170kV GIS 정밀점검공사","2020년 평택전력지사 170kV GIS 정밀점검공사 / 포승S/S 포승-청북T/L GIS 정밀점검공사","2020-06-08 09:00","2020-06-10 18:00","2020-06-08 09:00","2020-06-10 18:00","연속"]
[287,"경기","평택","포승만호 T/L","2020년 평택전력지사 170kV GIS 정밀점검공사","2020년 평택전력지사 170kV GIS 정밀점검공사 / 포승S/S 만호-포승T/L GIS 정밀점검공사","2020-06-11 09:00","2020-06-13 18:00","2020-06-11 09:00","2020-06-13 18:00","연속"]
[288,"강원","강릉","강릉횡계#2 T/L","20-21년도 송전정비회사 총액공사","○ 수평 추락방지시설 설치 - 154kV 횡계분기T/L No.47","2020-06-02 12:00","2020-06-02 18:00","2020-06-02 12:00","2020-06-02 18:00","연속"]
[289,"강원","강릉","강릉횡계#1 T/L","2020년 변전협력총액공사 170kV GIS 보통점검","○ 2020년 변전협력총액공사 - 170kV GIS 보통점검, 전자변 교체","취  소","취  소","취소","취소","연속"]
[290,"강원","강릉","강릉횡계#1 T/L","20-21년도 송전정비회사 총액공사","○ 수평 추락방지시설 설치 - 154kV 횡계분기T/L No.47","2020-06-02 08:00","2020-06-02 12:00","2020-06-02 08:00","2020-06-02 12:00","연속"]
[291,"강원","강릉","신양양양양#1 T/L","20-21년도 송전정비회사 총액공사","○ 수평 추락방지 시설 설치 - 154kV 신양양양양T/L No.40","취  소","취  소","취소","취소","연속"]
[292,"강원","강릉","신양양양양#2 T/L","20-21년도 송전정비회사 총액공사","○ 수평 추락방지시설 설치 - 154kV 신양양양양T/L No.40","취  소","취  소","취소","취소","연속"]
[293,"강원","강릉","신양양양양#1 T/L","2020년 변전협력총액공사 170kV GIS 보통점검","○ 2020년 변전협력총액공사 - 170kV GIS 보통점검, 전자변 교체","2020-06-04 10:00","2020-06-04 18:00","2020-06-04 10:00","2020-06-04 18:00","연속"]
[294,"강원","강릉","신양양양양#2 T/L","2020년 변전협력총액공사 170kV GIS 보통점검","○ 2020년 변전협력총액공사 - 170kV GIS 보통점검, 전자변 교체","2020-06-05 10:00","2020-06-05 18:00","2020-06-05 10:00","2020-06-05 18:00","연속"]
[295,"강원","강릉","주진평창#1 T/L","횡성, 주진변전소 외장재 교체공사","○ 노후 외장재 철거 : 외벽 드라이비트 철거 등 ○ 외장재 설치 : 외벽 폴리메탈판넬, 샌드위치판넬, AL시트패널 설치 등 ○ 도장공사 : 고탄성아크릴도장, 수성페인트 칠 등 ○ 기타공사 : 폐기물처리 60.612 TON","2020-06-08 09:00","2020-06-15 18:00","취소","취소","매일"]
[296,"강원","강릉","신제천주진#2 T/L","횡성, 주진변전소 외장재 교체공사","○ 노후 외장재 철거 : 외벽 드라이비트 철거 등 ○ 외장재 설치 : 외벽 폴리메탈판넬, 샌드위치판넬, AL시트패널 설치 등 ○ 도장공사 : 고탄성아크릴도장, 수성페인트 칠 등 ○ 기타공사 : 폐기물처리 60.612 TON","2020-06-16 09:00","2020-06-23 18:00","2020-06-16 09:00","2020-06-23 18:00","매일"]
[297,"강원","강릉","신제천주진#1 T/L","횡성, 주진변전소 외장재 교체공사","○ 노후 외장재 철거 : 외벽 드라이비트 철거 등 ○ 외장재 설치 : 외벽 폴리메탈판넬, 샌드위치판넬, AL시트패널 설치 등 ○ 도장공사 : 고탄성아크릴도장, 수성페인트 칠 등 ○ 기타공사 : 폐기물처리 60.612 TON","2020-06-19 09:00","2020-06-26 18:00","2020-06-19 09:00","2020-06-26 18:00","매일"]
[298,"강원","강릉","주진평창#2 T/L","횡성, 주진변전소 외장재 교체공사","○ 노후 외장재 철거 : 외벽 드라이비트 철거 등 ○ 외장재 설치 : 외벽 폴리메탈판넬, 샌드위치판넬, AL시트패널 설치 등 ○ 도장공사 : 고탄성아크릴도장, 수성페인트 칠 등 ○ 기타공사 : 폐기물처리 60.612 TON","2020-06-11 09:00","2020-06-18 18:00","취소","취소","매일"]
[299,"강원","동해","동해영동TP T/L","154kV 동해분기T/L No.15~19호간 지장철탑 이설공사","지장송전선로 이설 철탑 설치 : 4기(가철탑 1기 포함) 전력선 교체 : 2C-1.52km","2020-06-30 09:00","2020-07-05 18:00","2020-06-30 09:00","2020-07-05 18:00","연속"]
[300,"강원","동해","동해영동TP T/L","154kV 동해분기T/L No.15~19호간 지장철탑 이설공사","지장송전선로 이설 철탑 설치 : 4기(가철탑 1기 포함) 전력선 교체 : 2C-1.52km","2020-06-16 09:00","2020-06-19 18:00","2020-06-16 09:00","2020-06-19 18:00","연속"]
[301,"강원","동해","동해강릉 T/L","154kV 동해분기T/L No.15~19호간 지장철탑 이설공사","지장송전선로 이설 철탑 설치 : 4기(가철탑 1기 포함) 전력선 교체 : 2C-1.52km","2020-06-20 09:00","2020-06-29 18:00","2020-06-20 09:00","2020-06-29 18:00","연속"]
[302,"강원","동해","울진삼척GP#2 T/L","세니온제 보호배전반 성능개선","보호배전반 성능개선 시행 보호계전기 동작시험 및 연동시험","2020-06-03 10:00","2020-06-03 18:00","2020-06-12 10:00","2020-06-12 19:00","연속"]
[303,"강원","동해","울진삼척GP#1 T/L","세니온제 보호배전반 성능개선","보호배전반 성능개선 시행 보호계전기 동작시험 및 연동시험","2020-06-02 10:00","2020-06-02 18:00","2020-06-11 10:00","2020-06-11 19:00","연속"]
[304,"강원","원주","남원주원주#1 T/L","원주S/S 154kV GIS실 신축공사","전력구공사 이격거리 확보","2020-06-02 13:00","2020-06-02 18:00","2020-06-02 13:00","2020-06-02 18:00","연속"]
[305,"강원","원주","원주서원주#1 T/L","원주S/S 154kV GIS실 신축공사","전력구공사 이격거리 확보","2020-06-01 13:00","2020-06-01 18:00","2020-06-01 13:00","2020-06-01 18:00","연속"]
[306,"강원","원주","남원주원주#2 T/L","원주S/S 154kV GIS실 신축공사","전력구공사 이격거리 확보","2020-06-01 09:00","2020-06-02 13:00","2020-06-01 09:00","2020-06-02 13:00","매일"]
[307,"강원","원주","횡성홍천#2 T/L","횡성, 주진변전소 외장재 교체공사","○ 노후 외장재 철거 : 외벽 드라이비트 철거 등 ○ 외장재 설치 : 외벽 폴리메탈판넬, 샌드위치판넬, AL시트패널 설치 등 ○ 도장공사 : 고탄성아크릴도장, 수성페인트 칠 등 ○ 기타공사 : 폐기물처리 60.612 TON","2020-06-11 09:00","2020-06-18 18:00","2020-06-11 09:00","2020-06-18 18:00","매일"]
[308,"강원","원주","횡성홍천#1 T/L","횡성, 주진변전소 외장재 교체공사","○ 노후 외장재 철거 : 외벽 드라이비트 철거 등 ○ 외장재 설치 : 외벽 폴리메탈판넬, 샌드위치판넬, AL시트패널 설치 등 ○ 도장공사 : 고탄성아크릴도장, 수성페인트 칠 등 ○ 기타공사 : 폐기물처리 60.612 TON","2020-06-08 09:00","2020-06-15 18:00","2020-06-08 09:00","2020-06-15 18:00","매일"]
[309,"강원","원주","북원주횡성#2 T/L","횡성, 주진변전소 외장재 교체공사","○ 노후 외장재 철거 : 외벽 드라이비트 철거 등 ○ 외장재 설치 : 외벽 폴리메탈판넬, 샌드위치판넬, AL시트패널 설치 등 ○ 도장공사 : 고탄성아크릴도장, 수성페인트 칠 등 ○ 기타공사 : 폐기물처리 60.612 TON","2020-06-16 09:00","2020-06-23 18:00","2020-06-16 09:00","2020-06-23 18:00","매일"]
[310,"강원","원주","북원주횡성#1 T/L","횡성, 주진변전소 외장재 교체공사","○ 노후 외장재 철거 : 외벽 드라이비트 철거 등 ○ 외장재 설치 : 외벽 폴리메탈판넬, 샌드위치판넬, AL시트패널 설치 등 ○ 도장공사 : 고탄성아크릴도장, 수성페인트 칠 등 ○ 기타공사 : 폐기물처리 60.612 TON","2020-06-19 09:00","2020-06-26 18:00","2020-06-19 09:00","2020-06-26 18:00","매일"]
[311,"강원","직할","화천화천HP#1 T/L","20~21 강원본부 직할 변전정비 총액공사","○ 화천-화천H/P #1T/L #1, 2 DS 보통점검","2020-06-09 10:00","2020-06-09 18:00","취소","취소","연속"]
[312,"강원","직할","화천H/P 154kV #60 BUS","20~21 강원본부 직할 변전정비 총액공사","○ 화천-화천H/P #1T/L #1DS 보통점검 ○ #1BUS CVT 보통점검","2020-06-09 10:00","2020-06-09 14:00","2020-06-09 10:00","2020-06-09 14:00","연속"]
[313,"강원","직할","화천화천HP#2 T/L","2020~2021년 강원직할 송전정비회사 총액공사","불량애자 교체 및 항공장애표시구 교체","2020-06-08 07:00","2020-06-08 19:00","취소","취소","연속"]
[314,"강원","직할","가평화천HP T/L","2020년 직할 장기미동작 차단기 조작시험","○ 가평-화천H/P T/L 장기미동작 차단기 조작시험","2020-06-10 10:00","2020-06-10 14:00","2020-06-10 10:00","2020-06-10 14:00","연속"]
[315,"강원","직할","화천H/P 154kV #65 BUS","20~21 강원본부 직할 변전정비 총액공사","○ 화천-화천H/P #1T/L #2DS 보통점검 ○ #2BUS CVT 보통점검","2020-06-09 14:00","2020-06-09 18:00","2020-06-09 14:00","2020-06-09 18:00","연속"]
[316,"강원","태백","동해동영월 T/L","20-21 태백전력지사 변전정비회사 총액공사","동영월S/S 154kV 동해-동영월 T/L GIS 조작시험","2020-06-30 10:00","2020-06-30 14:00","2020-06-30 10:00","2020-06-30 14:00","연속"]
[317,"강원","태백","단양영월CC#2 T/L","20-21 태백전력지사 변전정비회사 총액공사","영월C/C 154kV 단양-영월CC #2 T/L GIS 조작시험","2020-06-24 14:00","2020-06-24 18:00","2020-06-24 14:00","2020-06-24 18:00","연속"]
[318,"강원","태백","단양영월CC#1 T/L","20-21 태백전력지사 변전정비회사 총액공사","영월C/C 154kV 단양-영월CC #1 T/L GIS 조작시험","2020-06-24 10:00","2020-06-24 14:00","2020-06-24 10:00","2020-06-24 14:00","연속"]
[319,"강원","태백","고한영월 T/L","20년 태백전력지사 170kV GIS 정밀점검 공사","영월S/S 154kV 고한-영월T/L GIS 정밀점검","2020-06-04 10:00","2020-06-06 18:00","2020-06-04 10:00","2020-06-06 18:00","연속"]
[320,"강원","태백","영월_영월CC T/L","20-21 태백전력지사 변전정비회사 총액공사","영월S/S 154kV 영월-영월CC T/L GIS 조작시험","2020-06-23 10:00","2020-06-23 18:00","2020-06-23 10:00","2020-06-23 18:00","연속"]
[321,"강원","태백","태백삼척GP#2 T/L","20-21 태백전력지사 변전정비회사 총액공사","태백S/S 154kV 태백-삼척GP #2T/L GIS 조작시험","2020-06-10 14:00","2020-06-10 18:00","2020-06-10 14:00","2020-06-10 18:00","연속"]
[322,"강원","태백","태백고한 T/L","20-21 태백전력지사 변전정비회사 총액공사","태백S/S 154kV 태백-고한 T/L GIS 조작시험","2020-06-18 10:00","2020-06-18 18:00","2020-06-18 10:00","2020-06-18 18:00","연속"]
[323,"강원","태백","태백삼척GP#1 T/L","20-21 태백전력지사 변전정비회사 총액공사","태백S/S 154kV 태백-삼척GP #1T/L GIS 조작시험","2020-06-10 10:00","2020-06-10 14:00","2020-06-10 10:00","2020-06-10 14:00","연속"]
[324,"충북","직할","서운광혜원 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","안전거리 이격","2020-06-05 09:00","2020-06-06 18:00","취소","취소","매일"]
[325,"충북","직할","삼죽광혜원 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","안전거리 이격","2020-06-03 09:00","2020-06-04 18:00","취소","취소","매일"]
[326,"충북","직할","서운광혜원 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","안전거리 이격","2020-06-01 09:00","2020-06-02 18:00","취소","취소","매일"]
[327,"충북","직할","신진천오창#1 T/L","2020~21년 직할 송전정비회사 총액공사","154kV 신진천-진천T/L 안전이격확보","2020-06-22 08:00","2020-06-22 18:00","취소","취소","매일"]
[328,"충북","직할","신진천S/S 154kV SEC CB 60610","20~21년도 직할 변전정비회사 총액공사","신진천S/S 154kV #60-65 모선보호반 대체","2020-06-23 10:00","2020-06-26 18:00","취소","취소","연속"]
[329,"충북","직할","신진천S/S 154kV CB 6100","20~21년도 직할 변전정비회사 총액공사","신진천S/S 154kV #60-65 모선보호반 대체","2020-06-23 10:00","2020-06-26 18:00","취소","취소","연속"]
[330,"충북","직할","신진천S/S 154kV CB 6200","20~21년도 직할 변전정비회사 총액공사","신진천S/S 154kV #61-66 모선보호반 대체","2020-06-30 10:00","2020-07-03 18:00","취소","취소","연속"]
[331,"충북","직할","신진천S/S 154kV SEC CB 65660","20~21년도 직할 변전정비회사 총액공사","신진천S/S 154kV #61-66 모선보호반 대체","2020-06-30 10:00","2020-07-03 18:00","취소","취소","연속"]
[332,"충북","직할","신진천진천#2 T/L","2020~21년 직할 송전정비회사 총액공사","아킹혼설치(no.1~31), 불량애자교체(6기), 조류착지방지장치(15기)","2020-06-22 08:00","2020-06-26 18:00","취소","취소","매일"]
[333,"충북","직할","신진천S/S 154kV SEC CB 60610","20~21년도 직할 변전정비회사 총액공사","신진천S/S 154kV #61-66 모선보호반 대체","2020-06-30 10:00","2020-07-03 18:00","취소","취소","연속"]
[334,"충북","직할","신진천S/S 154kV SEC CB 61620","20~21년도 직할 변전정비회사 총액공사","신진천S/S 154kV #61-66 모선보호반 대체","2020-06-30 10:00","2020-07-03 18:00","취소","취소","연속"]
[335,"충북","직할","신진천S/S 154kV SEC CB 66670","20~21년도 직할 변전정비회사 총액공사","신진천S/S 154kV #61-66 모선보호반 대체","2020-06-30 10:00","2020-07-03 18:00","취소","취소","연속"]
[336,"충북","직할","신진천S/S 154kV SEC CB 65660","20~21년도 직할 변전정비회사 총액공사","신진천S/S 154kV #60-65 모선보호반 대체","2020-06-23 10:00","2020-06-26 18:00","취소","취소","연속"]
[337,"충북","청주","국사봉명#1 T/L","154kV 국사-봉명T/L 안전이격확보공사","24호 철탑교체 1기","2020-06-01 07:00","2020-06-06 18:00","취소","취소","연속"]
[338,"충북","청주","옥천보은 T/L","20-21년 청주전력 변전정비회사 총액공사","보은S/S 154kV 옥천보은T/L GIS 보통점검","2020-06-05 10:00","2020-06-05 18:00","2020-06-05 10:00","2020-06-05 18:00","연속"]
[339,"충북","청주","서청주사직#2 T/L","20-21년 청주전력 변전정비회사 총액공사","서청주,사직S/S 154kV 서청주사직#2T/L 보호반 교체 공사","2020-06-06 09:00","2020-06-07 18:00","취소","취소","연속"]
[340,"충북","청주","오송북청주#1 T/L","154kV 오송S/S #1M.Tr 증설공사 최초가압","#1M.Tr 증설분 최초가압","2020-06-22 09:00","2020-06-23 18:00","2020-06-22 09:00","2020-06-23 18:00","연속"]
[341,"충북","청주","오송북청주#2 T/L","154kV 국사-봉명T/L 안전이격확보공사","24호 철탑교체 1기","2020-06-01 07:00","2020-06-06 18:00","취소","취소","연속"]
[342,"충북","청주","남청주청주#1 T/L","20-21년 청주전력 변전정비회사 총액공사","청주S/S 154kV 남청주청주#1T/L GIS 초기점검","2020-06-03 09:30","2020-06-03 18:00","2020-06-03 09:30","2020-06-03 18:00","연속"]
[343,"충북","청주","남청주청주#4 T/L","20-21년 청주전력 변전정비회사 총액공사","청주S/S 154kV 남청주청주#4T/L GIS 초기점검","2020-06-02 09:30","2020-06-02 18:00","2020-06-02 09:30","2020-06-02 18:00","연속"]
[344,"충북","충주","금왕남음성#2 T/L","2020~21년 직할 송전정비회사 총액공사","불량애자교체(No.6), 조류착지방지방치(No.2~26)","2020-06-04 08:00","2020-06-05 18:00","취소","취소","매일"]
[345,"충북","충주","금왕남음성#1 T/L","2020~21년 직할 송전정비회사 총액공사","아킹혼설치(No.1~35), 조류착지방지방치(No.2~26)","2020-06-12 08:00","2020-06-17 18:00","취소","취소","매일"]
[346,"충북","충주","문경단양 T/L","단양S/S 154kV GIS 장기사용 대체공사(단양전철#2T/L)","기설 GIS(단양전철#2T/L) 철거 x 1CCT 신규 GIS(단양전철#2T/L) 설치 x 1CCT ※ 단양전철 #2T/L 작업시 안전이격확보용 휴전","2020-06-02 10:00","2020-06-02 18:00","2020-06-02 10:00","2020-06-02 18:00","연속"]
[347,"충북","충주","단양영월CC#1 T/L","단양S/S 154kV GIS 장기사용 대체공사(단양전철#2T/L)","기설 GIS(단양전철#2T/L) 철거 x 1CCT 신규 GIS(단양전철#2T/L) 설치 x 1CCT ※ 단양전철#2T/L 무부하가압 전원","2020-06-08 10:00","2020-06-09 13:00","2020-06-08 10:00","2020-06-09 13:00","연속"]
[348,"충북","충주","문경단양 T/L","단양S/S 154kV GIS 장기사용 대체공사(단양전철#2T/L)","기설 GIS(단양전철#2T/L) 철거 x 1CCT 신규 GIS(단양전철#2T/L) 설치 x 1CCT ※ 단양전철 #2T/L 작업시 안전이격확보용 휴전","2020-06-11 10:00","2020-06-12 18:00","2020-06-11 10:00","2020-06-12 18:00","매일"]
[349,"충북","충주","단양영월CC#1 T/L","단양S/S 154kV GIS 장기사용 대체공사(단양전철#2T/L)","기설 GIS(단양전철#2T/L) 철거 x 1CCT 신규 GIS(단양전철#2T/L) 설치 x 1CCT ※ 단양전철#2T/L 무부하가압 전원","2020-06-17 10:00","2020-06-18 13:00","2020-06-17 10:00","2020-06-18 13:00","연속"]
[350,"충북","충주","신충주음성#2 T/L","2020~21년 직할 송전정비회사 총액공사","불량애자교체(No.66,70,71)","2020-06-08 08:00","2020-06-08 18:00","취소","취소","매일"]
[351,"충북","충주","음성금왕#1 T/L","2020~21년 직할 송전정비회사 총액공사","No.36.3~38 전력선교체","2020-06-01 08:00","2020-06-05 18:00","취소","취소","연속"]
[352,"충북","충주","음성금왕#2 T/L","2020~21년 직할 송전정비회사 총액공사","No.36.3~38 전력선교체, 아킹혼설치(51기), 불량애자교체(3기)","2020-06-08 08:00","2020-06-17 18:00","취소","취소","연속"]
[353,"충북","충주","신제천제천#2 T/L","'20-21년 충주전력지사 변전정비 총액공사","제천S/S 신제천-제천#2T/L GIS 보통점검","2020-06-15 10:00","2020-06-15 18:00","취소","취소","연속"]
[354,"대전충남","서산","당진T/P 154kV #2 BUS","당진화력S/Y 154kV 장기사용 GIS 대체공사","당진화력S/Y 154kV 장기사용 GIS 대체공사","2020-06-02 09:00","2020-06-08 18:00","2020-06-02 09:00","2020-06-08 18:00","연속"]
[355,"대전충남","서산","신당진S/S 154kV SEC CB 60610","20년 서산P/O 154kV GIS 정밀점검공사","신당진 154kV #60-61 GIS 정밀점검","2020-06-01 09:00","2020-06-03 14:00","2020-06-15 09:00","2020-06-17 14:00","연속"]
[356,"대전충남","아산","온양풍세#1 T/L","온양,풍세S/S 온양-풍세#1T/L 보호배전반 교체공사","온양,풍세S/S 온양-풍세#1T/L 보호배전반 교체공사","2020-06-01 09:00","2020-06-05 18:00","취소","취소","연속"]
[357,"대전충남","아산","인주탕정#1 T/L","154kV 인주-불당T/L C/H 건설사업","154kV 인주-불당T/L C/H 건설공사 - C/H 접속을 위한 병가철탑 상하단 교체공사 시행","2020-06-01 09:00","2020-06-08 18:00","2020-06-01 09:00","2020-06-08 18:00","연속"]
[358,"대전충남","아산","서천안탕정#2 T/L","154kV 인주-불당T/L C/H 건설사업","154kV 인주-불당T/L C/H 건설공사 - C/H 접속을 위한 병가철탑 상하단 교체공사 시행","2020-06-01 09:00","2020-06-08 18:00","2020-06-01 09:00","2020-06-08 18:00","연속"]
[359,"대전충남","청양","보령T/P 154kV CB 6100","2020년 청양P/O 170kV GIS 정밀점검공사","2020년 청양P/O 170kV GIS 정밀점검공사","2020-06-01 09:00","2020-06-03 14:00","2020-06-01 09:00","2020-06-03 14:00","연속"]
[360,"대전충남","청양","동군산장항#1 T/L","[송전]154kV 옥산-장항T/L 불량애자교체공사(병가)","[송전]154kV 옥산-장항T/L 불량애자교체공사(병가) - No.3~70 (19기, 1,096장)","2020-06-01 09:00","2020-06-01 18:00","2020-06-01 09:00","2020-06-01 18:00","연속"]
[361,"대전충남","서산","신당진S/S 154kV SEC CB 65660","20년 서산P/O 154kV GIS 정밀점검공사","신당진 154kV #65-66 GIS 정밀점검","2020-06-03 14:00","2020-06-05 18:00","2020-06-17 14:00","2020-06-19 18:00","연속"]
[362,"대전충남","아산","아산S/S 154kV CB 6200","아산S/S 154kV 6200 GIS 보통점검","아산S/S 154kV 6200 GIS 보통점검","2020-06-04 09:00","2020-06-04 18:00","2020-06-04 09:00","2020-06-04 18:00","연속"]
[363,"대전충남","서산","태안T/P 154kV 태안IGCC CB 6133","20년도 장기 미동작 차단기 조작시험","태안T/P ST/GT(IGCC) 6133 CB 조작시험","2020-06-04 10:00","2020-06-04 14:00","2020-06-04 10:00","2020-06-04 14:00","연속"]
[364,"대전충남","직할","부강신탄진 T/L","154kV 부강-신탄진T/L 보호배전반 성능개선","○ 154kV 부강-신탄진T/L 보호배전반 성능개선 - 87, 21 보호계전기 교체","2020-06-05 09:00","2020-06-05 18:00","2020-06-05 09:00","2020-06-05 18:00","연속"]
[365,"대전충남","세종","덕진공주#1 T/L","[송전]국제과학비즈니스벨트 지장송전선로 지중화공사(요청자시행)","ㅇ 요청자(한국토지주택공사) 직접시행 지장이설 및 지중화공사 ㅇ 공사구간 : 154kV 덕진-공주(덕진-유성)T/L No.13~15 ㅇ 철탑 : C/H 2기 설치, 가철탑 2기 ㅇ 전력선 : ACSR 410 x S x 4C ㅇ CH 2기 설치, 가철탑 2기 설치철거 외 기타 부대공사 시행","2020-06-08 07:00","2020-06-14 18:00","2020-06-08 07:00","2020-06-14 18:00","연속"]
[366,"대전충남","청양","청양신풍#1 T/L","[송전]154kV 청양-은하 등 2개TL 접속개소제거 전선교체공사","[송전]154kV 청양-신풍TL 접속개소제거 전선교체공사 - No.32~34(4W) 상단 2가닥, No.40~42(4W) 하단 2가닥","2020-06-08 07:00","2020-06-10 18:00","2020-06-08 07:00","2020-06-10 18:00","연속"]
[367,"대전충남","대전","신옥천서대전 T/L","[송전]154kV 신옥천-서대전T/L 정밀점검 및 OPGW 교체","[송전]154kV 신옥천-서대전T/L 정밀점검 및 OPGW 교체","2020-06-08 08:00","2020-06-17 18:00","2020-06-08 08:00","2020-06-17 18:00","연속"]
[368,"대전충남","대전","신옥천유천 T/L","[송전]154kV 신옥천-서대전T/L 정밀점검 및 OPGW 교체","[송전]154kV 신옥천-유천T/L 정밀점검 및 OPGW 교체","2020-06-08 08:00","2020-06-18 18:00","2020-06-08 08:00","2020-06-18 18:00","연속"]
[369,"대전충남","아산","신탕정탕정#1 T/L","신탕정,탕정S/S 신탕정-탕정#1T/L GIS 보통점검","신탕정,탕정S/S 신탕정-탕정#1T/L GIS 보통점검","2020-06-08 09:00","2020-06-08 18:00","2020-06-08 09:00","2020-06-08 18:00","연속"]
[370,"대전충남","아산","온양풍세#2 T/L","온양,풍세S/S 온양-풍세#2T/L 보호배전반 교체공사","온양,풍세S/S 온양-풍세#2T/L 보호배전반 교체공사","2020-06-08 09:00","2020-06-12 18:00","취소","취소","연속"]
[371,"대전충남","직할","덕진대화#1 T/L","20년 직할 170kV GIS 정밀점검공사","○20년 직할 170kV GIS 정밀점검공사 - 대상 : 동대전(2), 대화(3), 신탄진(2)","2020-06-08 09:00","2020-06-09 18:00","2020-06-08 09:00","2020-06-09 18:00","연속"]
[372,"대전충남","청양","동군산장항#2 T/L","2020년 청양P/O 170kV GIS 정밀점검공사","2020년 청양P/O 170kV GIS 정밀점검공사","2020-06-08 09:00","2020-06-10 14:00","2020-06-08 09:00","2020-06-10 14:00","연속"]
[373,"대전충남","서산","서산홍성 T/L","`20-21년 송전정비회사 총액공사","154kV 서산-홍성T/L 이도조정 ○ 이도조정 : No.83-85 상단 등 4 section","2020-06-09 08:00","2020-06-10 18:00","2020-06-09 08:00","2020-06-10 18:00","매일"]
[374,"대전충남","서산","신당진서산#1 T/L","`20-21년 송전정비회사 총액공사","154kV 서산-홍성T/L 이도조정 (병가구간) ○ 이도조정 : No.83-85 상단 등 4 section","2020-06-09 08:00","2020-06-10 18:00","2020-06-09 08:00","2020-06-10 18:00","매일"]
[375,"대전충남","아산","신탕정탕정#2 T/L","신탕정,탕정S/S 신탕정-탕정#2T/L GIS 보통점검","신탕정,탕정S/S 신탕정-탕정#2T/L GIS 보통점검","2020-06-09 09:00","2020-06-09 18:00","2020-06-09 09:00","2020-06-09 18:00","연속"]
[376,"대전충남","아산","서천안탕정#1 T/L","154kV 인주-불당T/L C/H 건설사업","154kV 인주-불당T/L C/H 건설공사 - C/H 접속을 위한 병가철탑 상하단 교체공사 시행","2020-06-09 09:00","2020-06-16 18:00","2020-06-09 09:00","2020-06-16 18:00","연속"]
[377,"대전충남","아산","인주탕정#2 T/L","154kV 인주-불당T/L C/H 건설사업","154kV 인주-불당T/L C/H 건설공사 - C/H 접속을 위한 병가철탑 상하단 교체공사 시행","2020-06-09 09:00","2020-06-16 18:00","2020-06-09 09:00","2020-06-16 18:00","연속"]
[378,"대전충남","서산","서산해미 T/L","`20-21년 송전정비회사 총액공사","154kV 서산-해미T/L 이도조정 ○ 이도조정 : No.83-85 상단","2020-06-10 08:00","2020-06-10 18:00","2020-06-10 08:00","2020-06-10 18:00","연속"]
[379,"대전충남","아산","불당서천안#1 T/L","불당S/S 불당-서천안#1T/L GIS 전자변 교체","불당S/S 불당-서천안#1T/L GIS 전자변 교체","2020-06-10 09:00","2020-06-10 18:00","취소","취소","연속"]
[380,"대전충남","청양","청양신풍#2 T/L","[송전]154kV 청양-은하 등 2개TL 접속개소제거 전선교체공사","[송전]154kV 청양-신풍TL 접속개소제거 전선교체공사 - No.32~34(4W) 상단 2가닥, No.40~42(4W) 하단 2가닥","2020-06-11 07:00","2020-06-12 18:00","2020-06-11 07:00","2020-06-12 18:00","연속"]
[381,"대전충남","아산","불당서천안#2 T/L","불당S/S 불당-서천안#2T/L GIS 전자변 교체","불당S/S 불당-서천안#2T/L GIS 전자변 교체","2020-06-11 09:00","2020-06-11 18:00","취소","취소","연속"]
[382,"대전충남","직할","덕진대화#2 T/L","20년 직할 170kV GIS 정밀점검공사","○20년 직할 170kV GIS 정밀점검공사 - 대상 : 동대전(2), 대화(3), 신탄진(2)","2020-06-11 09:00","2020-06-12 18:00","2020-06-11 09:00","2020-06-12 18:00","연속"]
[383,"대전충남","서산","태안T/P 154kV 태양광소수력 CB 6233","20년도 장기 미동작 차단기 조작시험","태안T/P 태양광소수력 6233 CB 조작시험","2020-06-11 10:00","2020-06-11 14:00","2020-06-11 10:00","2020-06-11 14:00","연속"]
[384,"대전충남","세종","덕진공주#2 T/L","[송전]국제과학비즈니스벨트 지장송전선로 지중화공사(요청자시행)","ㅇ 요청자(한국토지주택공사) 직접시행 지장이설 및 지중화공사 ㅇ 공사구간 : 154kV 덕진-공주(덕진-유성)T/L No.13~15 ㅇ 철탑 : C/H 2기 설치, 가철탑 2기 ㅇ 전력선 : ACSR 410 x S x 4C ㅇ CH 2기 설치, 가철탑 2기 설치철거 외 기타 부대공사 시행","2020-06-15 07:00","2020-06-23 18:00","2020-06-15 07:00","2020-06-23 18:00","연속"]
[385,"대전충남","서산","신당진S/S 154kV #60 BUS","20년 서산P/O 154kV GIS 정밀점검공사","신당진 345kV #1M.Tr 2차 GIS(6144) 정밀점검 및 DS(6141,6142) 정밀점검","2020-06-15 09:00","2020-06-16 14:00","2020-06-01 09:00","2020-06-02 14:00","연속"]
[386,"대전충남","세종","서세종조치원 T/L","[변전]2020년 세종PO 170kV GIS 정밀점검공사","- 170kV GIS 정밀점검공사","2020-06-15 09:00","2020-06-16 18:00","2020-06-15 09:00","2020-06-16 18:00","연속"]
[387,"대전충남","아산","아산인주#1 T/L","아산,인주S/S 아산-인주#1T/L GIS 보통점검","아산,인주S/S 아산-인주#1T/L GIS 보통점검","2020-06-15 09:00","2020-06-15 18:00","취소","취소","연속"]
[388,"대전충남","직할","대화둔산#1 T/L","[송전]154kV 대화-둔산 등 2개T/L 선종교체 공사","○ 공사구간 : 154kV 대화-둔산 #1T/L 전구간 ○ 선종교체 : 154kV OF 2000㎟ → 154kV XLPE 2000㎟ (6.26km)","2020-06-15 09:00","2021-01-31 18:00","2020-06-15 09:00","2021-01-31 18:00","연속"]
[389,"대전충남","직할","동대전대화#1 T/L","[송전]154kV 대화-둔산 등 2개T/L 선종교체 공사","○ 공사구간 : 154kV 동대전-대화#1T/L 전구간 ○ 선종교체 : 154kV OF 2000㎟ → 154kV XLPE 2000㎟ (4.42km)","2020-06-15 09:00","2021-01-31 18:00","2020-06-15 09:00","2021-01-31 18:00","연속"]
[390,"대전충남","직할","동대전신탄진#1 T/L","20년 직할 170kV GIS 정밀점검공사","○20년 직할 170kV GIS 정밀점검공사 - 대상 : 동대전(2), 대화(3), 신탄진(2)","2020-06-15 09:00","2020-06-16 18:00","2020-06-15 09:00","2020-06-16 18:00","연속"]
[391,"대전충남","서산","신당진당진#2 T/L","20년 서산P/O 변전정비 총액공사","당진S/S 154kV 신당진-당진#2T/L (657) 초기점검 (병행) 신당진S/S 154kV 신당진-당진#2T/L 637 CB 조작시험","2020-06-16 09:00","2020-06-16 18:00","2020-06-16 09:00","2020-06-16 18:00","연속"]
[392,"대전충남","서산","신당진S/S 154kV #65 BUS","20년 서산P/O 154kV GIS 정밀점검공사","신당진 345kV #1M.Tr 2차 GIS(6144) 정밀점검 및 DS(6141,6142) 정밀점검","2020-06-16 14:00","2020-06-17 18:00","2020-06-02 14:00","2020-06-03 18:00","연속"]
[393,"대전충남","아산","인주탕정#1 T/L","154kV 인주-불당T/L C/H 건설사업","154kV 인주-불당T/L C/H 건설공사 - C/H 접속을 위한 병가철탑 상하단 교체공사 시행","2020-06-17 09:00","2020-07-13 18:00","2020-06-17 09:00","2020-07-13 18:00","연속"]
[394,"대전충남","아산","서천안탕정#1 T/L","154kV 인주-불당T/L C/H 건설사업","154kV 인주-불당T/L C/H 건설공사 - C/H 접속을 위한 병가철탑 상하단 교체공사 시행","2020-06-17 09:00","2020-07-20 18:00","2020-06-17 09:00","2020-07-20 18:00","연속"]
[395,"대전충남","세종","월산서세종 T/L","[변전]2020년 세종PO 170kV GIS 정밀점검공사","- 170kV GIS 정밀점검공사","2020-06-18 09:00","2020-06-19 18:00","2020-06-18 09:00","2020-06-19 18:00","연속"]
[396,"대전충남","직할","동대전신탄진#2 T/L","20년 직할 170kV GIS 정밀점검공사","○20년 직할 170kV GIS 정밀점검공사 - 대상 : 동대전(2), 대화(3), 신탄진(2)","2020-06-18 09:00","2020-06-19 18:00","2020-06-18 09:00","2020-06-19 18:00","연속"]
[397,"대전충남","서산","당진T/P 154kV 1,2호기 S/U TR 1차 GIS","당진화력S/Y 154kV 장기사용 GIS 대체공사","당진화력S/Y 154kV 장기사용 GIS 대체공사","2020-06-20 09:00","2020-06-28 18:00","2020-06-20 09:00","2020-06-28 18:00","연속"]
[398,"대전충남","서산","당진T/P 154kV #1 BUS","당진화력S/Y 154kV 장기사용 GIS 대체공사","당진화력S/Y 154kV 장기사용 GIS 대체공사","2020-06-17 09:00","2020-06-21 18:00","2020-06-17 09:00","2020-06-21 18:00","연속"]
[399,"대전충남","직할","동대전신탄진#1 T/L","[송전]154kV 동대전-신탄진T/L 안전이격거리 확보공사","○ 철탑 3기 설치 및 3기 철거, 1기 장주변경 - 신설/철거 : No.7,8,13 - 장주변경 : No.14 ○ 전력선 교체 : ACSR 240㎟ x S x 2C, 1.646km - No.6~9, 12~14","2020-06-20 09:00","2020-06-30 18:00","2020-06-20 09:00","2020-06-30 18:00","연속"]
[400,"대전충남","직할","동대전신탄진#2 T/L","[송전]154kV 동대전-신탄진T/L 안전이격거리 확보공사","○ 철탑 3기 설치 및 3기 철거, 1기 장주변경 - 신설/철거 : No.7,8,13 - 장주변경 : No.14 ○ 전력선 교체 : ACSR 240㎟ x S x 2C, 1.646km - No.6~9, 12~14","2020-06-20 09:00","2020-06-30 18:00","2020-06-20 09:00","2020-06-30 18:00","연속"]
[401,"대전충남","세종","조치원월산 T/L","[변전]2020년 세종PO 170kV GIS 정밀점검공사","- 170kV GIS 정밀점검공사","2020-06-22 09:00","2020-06-23 18:00","2020-06-22 09:00","2020-06-23 18:00","연속"]
[402,"대전충남","아산","둔포석곡#1 T/L","석곡S/S 154kV #4M.Tr 증설공사(무부하가압)","석곡S/S 154kV #4M.Tr 증설공사(무부하가압)","2020-06-23 14:00","2020-06-25 18:00","2020-06-23 14:00","2020-06-25 18:00","연속"]
[403,"대전충남","세종","덕진공주#1 T/L","[송전]국제과학비즈니스벨트 지장송전선로 지중화공사(요청자시행)","ㅇ 요청자(한국토지주택공사) 직접시행 지장이설 및 지중화공사 ㅇ 공사구간 : 154kV 덕진-공주(덕진-유성)T/L No.13~15 ㅇ 철탑 : C/H 2기 설치, 가철탑 2기 ㅇ 전력선 : ACSR 410 x S x 4C ㅇ CH 2기 설치, 가철탑 2기 설치철거 외 기타 부대공사 시행","2020-06-24 07:00","2020-06-30 18:00","2020-06-24 07:00","2020-06-30 18:00","연속"]
[404,"대전충남","서산","당진T/P 154kV #2 BUS","당진화력S/Y 154kV 장기사용 GIS 대체공사","당진화력S/Y 154kV 장기사용 GIS 대체공사","2020-06-16 09:00","2020-06-16 18:00","2020-06-16 09:00","2020-06-16 18:00","연속"]
[405,"대전충남","직할","송강신일#1 T/L","신일S/S 154kV 송강-신일#1T/L GIS 차단기 하자점검","신일S/S 154kV 송강-신일#1T/L GIS 차단기 하자점검","2020-06-29 09:00","2020-06-29 18:00","2020-06-29 09:00","2020-06-29 18:00","연속"]
[406,"대전충남","서산","당진T/P 154kV 3,4호기 S/U TR 1차 GIS","당진화력S/Y 154kV 장기사용 GIS 대체공사","당진화력S/Y 154kV 장기사용 GIS 대체공사","2020-06-30 09:00","2020-07-05 18:00","2020-06-30 09:00","2020-07-05 18:00","연속"]
[407,"대전충남","대전","팔봉두마#2 T/L","154kV 신계룡-두마T/L OPGW증설공사","신계룡S/S ~ 두마S/S간 가공지선(ACSR 97SQ)를 OPGW/100SQ로 변경","2020-06-01 07:00","2020-06-04 18:00","2020-06-01 07:00","2020-06-05 18:00","연속"]
[408,"대전충남","서산","당진T/P 154kV #2 BUS","당진화력S/Y 154kV 장기사용 GIS 대체공사","당진화력S/Y 154kV 장기사용 GIS 대체공사","2020-06-22 09:00","2020-06-25 18:00","2020-06-22 09:00","2020-06-25 18:00","연속"]
[409,"대전충남","서산","당진T/P 154kV #2 BUS","당진화력S/Y 154kV 장기사용 GIS 대체공사","당진화력S/Y 154kV 장기사용 GIS 대체공사","2020-06-30 09:00","2020-06-30 18:00","2020-06-30 09:00","2020-06-30 18:00","연속"]
[410,"전북","군산","군공군산CC#1 T/L","군산복합S/Y 인출 EDS 불완전 개방 하자점검공사","1. 군산복합S/Y 군공-군산CC#1T/L 인출 EDS 내부점검 2. 군공, 군산복합 차단기 조작시험","2020-06-17 09:00","2020-06-18 18:00","2020-06-17 09:00","2020-06-18 18:00","연속"]
[411,"전북","군산","군산이리#1 T/L","154kV 군산-이리T/L 안전이격확보공사","18,19호 가철탑 조립 및 공중이동","2020-06-15 07:00","2020-06-19 18:00","2020-06-15 07:00","2020-06-19 18:00","연속"]
[412,"전북","군산","군산이리#2 T/L","154kV 군산-이리T/L 안전이격확보공사","18,19호 가철탑 조립 및 공중이동","2020-06-20 07:00","2020-06-22 18:00","2020-06-20 07:00","2020-06-22 18:00","연속"]
[413,"전북","군산","동군산장항#1 T/L","154kV 동군산-장항T/L 용량증대 전선교체공사","No.22~25 용량증대 전선교체","2020-06-01 07:00","2020-06-03 18:00","2020-06-01 07:00","2020-06-03 18:00","연속"]
[414,"전북","군산","동군산장항#2 T/L","154kV 동군산-장항T/L 용량증대 전선교체공사","No.22~25 용량증대 전선교체","2020-06-04 07:00","2020-06-06 18:00","2020-06-04 07:00","2020-06-06 18:00","연속"]
[415,"전북","군산","서군산소룡#2 T/L","2020년 군산P/O 차단기 점검공사(서군산-소룡#1T/L)","○ 서군산 : 차단기(637,4244) 초기/보통점검(#2M.Tr 휴전병행, 공용 Bay), 단로기(6231) 보통점검, ○ 소룡 : 차단기(637) 보통점검, GIS GAS 시각화","2020-06-01 09:00","2020-06-01 18:00","2020-06-01 09:00","2020-06-01 18:00","연속"]
[416,"전북","군산","군산서군산#1 T/L","군산P/O 차단기 점검공사(군산-서군산#1T/L)","○ 군산 : 차단기(6C7) 조작시험 ○ 서군산 : 차단기(627) 조작시험","2020-06-03 09:00","2020-06-03 13:00","2020-06-03 09:00","2020-06-03 13:00","연속"]
[417,"전북","군산","서군산소룡#1 T/L","2020년 군산P/O 차단기 점검공사(서군산-소룡#1T/L)","○ 서군산 : 차단기(637) 초기점검(#3M.Tr 휴전병행, 공용 Bay), 단로기(6331) 보통점검, 보호배전반 점검 ○ 소룡 : 차단기(637) 보통점검, GIS GAS 시각화","2020-06-02 09:00","2020-06-02 18:00","2020-06-02 09:00","2020-06-02 18:00","연속"]
[418,"전북","군산","군산서군산#2 T/L","군산P/O 차단기 점검공사(군산-서군산#2T/L)","○ 군산 : 차단기(6D7) 조작시험 ○ 서군산 : 차단기(617) 조작시험","2020-06-03 13:00","2020-06-03 18:00","2020-06-03 13:00","2020-06-03 18:00","연속"]
[419,"전북","군산","팔봉두마#2 T/L","2020년 군산P/O 차단기 보통점검공사(팔봉-두마#2T/L)","팔봉S/S : 154kV 팔봉-두마#2T/L 차단기(617) 조작시험","2020-06-04 09:00","2020-06-04 11:00","2020-06-05 09:00","2020-06-05 11:00","연속"]
[420,"전북","군산","팔봉두마#1 T/L","2020년 군산P/O 차단기 보통점검공사(팔봉-두마#1T/L)","팔봉S/S : 154kV 팔봉-두마#1T/L 차단기(637) 조작시험","2020-06-04 11:00","2020-06-04 13:00","2020-06-05 11:00","2020-06-05 13:00","연속"]
[421,"전북","김제","백산김제#2 T/L","154kV 정공,칠보,김제분기T/L OPGW 증설공사","- 항공장애표시구 19개 시설","2020-06-05 07:00","2020-06-05 18:00","2020-06-08 07:00","2020-06-08 18:00","연속"]
[422,"전북","김제","담양김제 T/L","154kV 정공,칠보,김제분기T/L OPGW 증설공사","_ 항공구 19개 시설","2020-06-05 07:00","2020-06-05 18:00","2020-06-05 07:00","2020-06-08 18:00","연속"]
[423,"전북","김제","신김제남전주#1 T/L","154kV 남전주-임실T/L OPGW 증설공사","이도 점검","2020-06-08 07:00","2020-06-08 18:00","취소","취소","연속"]
[424,"전북","김제","정공담양 T/L","154kV 정공,칠보,김제분기T/L OPGW 증설공사","- 항공장애표시구 28개 시설","2020-06-10 07:00","2020-06-10 18:00","2020-06-10 07:00","2020-06-10 18:00","연속"]
[425,"전북","김제","정공정주#2 T/L","154kV 정공,칠보,김제분기T/L OPGW 증설공사","- 항공장애표시구 28개 시설","2020-06-10 07:00","2020-06-10 18:00","2020-06-10 07:00","2020-06-10 18:00","연속"]
[426,"전북","김제","정공S/S 154kV #65 BUS","김제PO 170kV GIS 정밀점검공사","무부하시험가압","2020-06-13 09:30","2020-06-13 18:00","2020-06-13 09:30","2020-06-13 18:00","연속"]
[427,"전북","김제","신김제정공#2 T/L","김제PO 170kV GIS 정밀점검공사","무부하시험가압","2020-06-13 09:30","2020-06-13 18:00","2020-06-13 09:30","2020-06-13 18:00","연속"]
[428,"전북","김제","신김제정공#1 T/L","154kV 차단기 조작시험","154kV 차단기 조작시험","2020-06-03 10:00","2020-06-03 14:00","2020-06-03 10:00","2020-06-03 14:00","연속"]
[429,"전북","김제","신김제정공#2 T/L","154kV 차단기 조작시험","154kV 차단기 조작시험","2020-06-03 14:00","2020-06-03 18:00","2020-06-03 14:00","2020-06-03 18:00","연속"]
[430,"전북","김제","정주부안#1 T/L","345kV 신김제-한빛#1T/L 전력선 교체공사","신김제-한빛#1T/L No.141~142 철탑횡단개소로 안전이격거리 확보차 양회선 휴전","2020-06-27 08:00","2020-06-30 18:00","취소","취소","매일"]
[431,"전북","김제","정주부안#2 T/L","345kV 신김제-한빛#1T/L 전력선 교체공사","신김제-한빛#1T/L No.141~142 철탑횡단개소로 안전이격거리 확보차 양회선 휴전","2020-06-27 08:00","2020-06-30 18:00","취소","취소","매일"]
[432,"전북","직할","이리전주#2 T/L","154kV 탄소분기 지중T/L 건설공사","- 기설 이리-전주#2T/L 케이블 절단 후 이리-탄소#2T/L 접속","2020-06-08 07:00","2020-07-01 18:00","2020-06-15 07:00","2020-07-10 18:00","연속"]
[433,"광주전남","광주","정공담양 T/L","20년 광주변전총액공사(정공담양T/L)","담양S/S 정공담양T/L 장기미동작 CB점검, CVT 초기점검","2020-06-10 09:30","2020-06-10 13:30","취소","취소","연속"]
[434,"광주전남","광주","담양김제 T/L","20년 광주변전총액공사(담양김제T/L)","담양S/S 담양김제T/L 장기미동작 CB점검, CVT 초기점검","2020-06-10 13:30","2020-06-10 18:00","취소","취소","연속"]
[435,"광주전남","광주","장성영광#2 T/L","154kV장성-영광T/L 국산불량애자교체공사","불양애자교체 970개","2020-06-15 06:00","2020-06-19 18:00","2020-06-15 10:00","2020-06-15 15:00","매일"]
[436,"광주전남","광주","하남장성#1 T/L","154kV장성-영광T/L 국산불량애자교체공사(작업 안전확보)","154kV장성-영광#2T/L 안전거리확보","2020-06-15 06:00","2020-06-19 18:00","2020-06-23 11:00","2020-06-23 16:00","매일"]
[437,"광주전남","목포","나주엄다#1 T/L","154kV 엄다-목포 T/L 안전이격확보공사(안전거리확보)","154kV 엄다-목포 No.94,95","2020-06-26 07:00","2020-06-30 18:00","취소","취소","매일"]
[438,"광주전남","목포","나주엄다#1 T/L","154kV 엄다-목포 T/L 안전이격확보공사(안전거리확보)","154kV 엄다-목포 No.94,95","2020-06-15 07:00","2020-06-17 18:00","취소","취소","매일"]
[439,"광주전남","목포","나주엄다#2 T/L","154kV 엄다-목포 T/L 안전이격확보공사(안전거리확보)","154kV 엄다-목포 No.144,145,149","2020-06-18 07:00","2020-06-25 18:00","취소","취소","매일"]
[440,"광주전남","목포","고창영광 T/L","`20년 목포전력지사 변전정비회사 총액공사","차단기 조작시험, LA 하자점검","2020-06-01 14:00","2020-06-01 18:00","2020-06-01 14:00","2020-06-01 18:00","연속"]
[441,"광주전남","목포","영광홍농 T/L","영광-홍농T/L No.7-17, 35-41호 OPGW 교체공사","가. 영광-홍농T/L No.7-17호, 35-41호 OPGW(100SQ/24C) 4.965km 교체 나. 기타 부대공사 1식.","2020-06-02 07:00","2020-06-05 18:00","2020-06-16 07:00","2020-06-19 18:00","연속"]
[442,"광주전남","목포","장성영광#1 T/L","영광-홍농T/L No.7-17, 35-41호 OPGW 교체공사","가. 영광-홍농T/L No.7-17호, 35-41호 OPGW(100SQ/24C) 4.965km 교체 나. 기타 부대공사 1식.","2020-06-02 07:00","2020-06-05 18:00","2020-06-16 07:00","2020-06-19 18:00","연속"]
[443,"광주전남","목포","고창홍농 T/L","`20년 목포전력지사 변전정비회사 총액공사","차단기 조작시험","2020-06-01 10:00","2020-06-01 14:00","2020-06-01 10:00","2020-06-01 14:00","연속"]
[444,"광주전남","순천","소라서순천#1 T/L","154kV 소라-서순천T/L 안전이격확보공사","○ 대상선로: 154kV 소라-서순천T/L No.55 ~ 60, 65 ~ 69, 72 ~ 80호 ○ 공사물량 - 철탑상향 : 6기(No.59, 67, 68, 76, 77, 78호) - 전선교체 : ACSR 410㎟×S, 1.17C-km - 관련 부대공사 : 1식","2020-06-05 09:00","2020-06-16 18:00","2020-06-12 07:00","2020-06-23 18:00","연속"]
[445,"광주전남","순천","여천여수산단#2 T/L","20년 상반기 순천전력지사 154kV GIS 정밀점검공사","여수산단 여천-여수산단#2T/L GIS 정밀점검공사","2020-06-11 09:00","2020-06-12 18:00","2020-06-11 09:00","2020-06-12 18:00","연속"]
[446,"광주전남","순천","여수T/P 154kV CB 6100","20-21년 순천전력지사 변전정비회사 총액공사(모선 보호반 대체)","여수TP 154kV #60-65 모선보호반 대체","2020-06-15 09:00","2020-06-18 18:00","2020-06-15 09:00","2020-06-18 18:00","연속"]
[447,"광주전남","순천","여수T/P 154kV SEC CB 60610","20-21년 순천전력지사 변전정비회사 총액공사(모선 보호반 대체)","여수TP 154kV #60-65 모선보호반 대체","2020-06-15 09:00","2020-06-18 18:00","2020-06-15 09:00","2020-06-18 18:00","연속"]
[448,"광주전남","순천","여수T/P 154kV SEC CB 65660","20-21년 순천전력지사 변전정비회사 총액공사(모선 보호반 대체)","여수TP 154kV #60-65 모선보호반 대체","2020-06-15 09:00","2020-06-18 18:00","2020-06-15 09:00","2020-06-18 18:00","연속"]
[449,"광주전남","순천","여수TP화치#2 T/L","345kV 광양CC-신여수T/L 건설사업","154kV 여수TP-화치#2 T/L 가선로 구성공사 - 공 사 명 : 345kV 광양CC-신여수T/L 건설공사 - 공사개요 : 철탑 1기 신설 및 철거(No.3), OPGW 시공 - 전선이동 : 1기 - 시공사/감리사 : 세종텔레콤/한국코아엔지니어링","2020-06-19 07:00","2020-06-21 18:00","2020-06-19 07:00","2020-06-21 18:00","연속"]
[450,"광주전남","순천","여수TP화치#1 T/L","345kV 광양CC-신여수T/L 건설사업","154kV 여수TP-화치#1 T/L 가선로 구성공사 - 공 사 명 : 345kV 광양CC-신여수T/L 건설공사 - 공사개요 : 철탑 1기 신설 및 철거(No.3), OPGW 시공 - 전선이동 : 1기 - 시공사/감리사 : 세종텔레콤/한국코아엔지니어링","2020-06-22 07:00","2020-06-24 18:00","2020-06-22 07:00","2020-06-24 18:00","연속"]
[451,"광주전남","순천","호남TP여수TP#1 T/L","345kV 광양CC-신여수T/L 건설사업","154kV 호남TP-여수TP#1 T/L 가선로 구성공사 - 공 사 명 : 345kV 광양CC-신여수T/L 건설공사 - 공사개요 : 철탑 1기 신설 및 철거(No.14), - 전선이동 : 1기 - 시공사/감리사 : 세종텔레콤/한국코아엔지니어링","2020-06-01 07:00","2020-06-03 18:00","2020-06-27 07:00","2020-06-29 18:00","연속"]
[452,"광주전남","순천","여천여수#2 T/L","20~21년 순천전력지사 변전총액공사(애자련교체)","여천S/S #2M.Tr 불량 현수애자 (1련) 교체관련 안전 이격거리 확보","2020-06-03 09:00","2020-06-03 14:00","2020-06-03 09:00","2020-06-03 14:00","연속"]
[453,"광주전남","순천","용성S/S 154kV #60 BUS","154kV 용성S/S LG화학 신규수용공사","○ 170kV GIS x 5CCT 설치 ○ 송전선로 보호반 x 2면 설치 ○ 모선보호반 x 1식 ○ AC,DC 소내반 각 1면 설치 ○ PT집합반 x 1면 설치 ○ 기초 및 기타 부대공사 x 1식","2020-04-27 10:00","2020-04-30 14:00","취소","취소","연속"]
[454,"광주전남","순천","용성S/S 154kV #60 BUS","일진제 170kV GIS 유사고장 조치공사 및 정밀점검","용성S/S 여수TP-용성#2T/L GIS 유사고장 조치 및 정밀점검","2020-04-20 09:00","2020-04-21 14:00","취소","취소","연속"]
[455,"광주전남","순천","용성S/S 154kV #65 BUS","일진제 170kV GIS 유사고장 조치공사 및 정밀점검","용성S/S 여수TP-용성#2T/L GIS 유사고장 조치 및 정밀점검","2020-04-21 14:00","2020-04-23 18:00","취소","취소","연속"]
[456,"광주전남","순천","용성여수산단#1 T/L","154kV 용성S/S LG화학 신규수용공사","170kV GIS SEC DS 전단 모선부분 가압","2020-04-02 15:00","2020-04-03 15:00","취소","취소","연속"]
[457,"광주전남","순천","여수TP용성#1 T/L","일진제 170kV GIS 유사고장 조치공사 및 정밀점검","용성S/S 여수TP-용성#1T/L GIS 유사고장 조치 및 정밀점검","2020-04-20 09:00","2020-04-24 18:00","취소","취소","연속"]
[458,"광주전남","순천","율촌화치#1 T/L","20-21년 순천전력지사 변전정비회사 총액공사","율촌S/S 율촌-화치#1T/L GIS LA A상 보통, LA(B.C) 하자점검 및 화치S/S 타임측정","2020-06-03 09:00","2020-06-03 18:00","2020-06-03 09:00","2020-06-03 18:00","연속"]
[459,"광주전남","순천","율촌화치#2 T/L","20-21년 순천전력지사 변전정비회사 총액공사","율촌S/S 율촌-화치#2T/L GIS 보통점검, LA(A,B,C) 하자점검 및 화치S/S 타임측정","2020-06-04 09:00","2020-06-04 18:00","2020-06-04 09:00","2020-06-04 18:00","연속"]
[460,"광주전남","직할","남광주금천#1 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치","2020-06-11 08:00","2020-06-12 18:00","취소","취소","매일"]
[461,"광주전남","직할","나주금천#1 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치","2020-06-11 08:00","2020-06-11 18:00","취소","취소","연속"]
[462,"광주전남","직할","나주금천#2 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치","2020-06-15 08:00","2020-06-15 18:00","취소","취소","연속"]
[463,"광주전남","직할","남광주금천#2 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치","2020-06-15 08:00","2020-06-16 18:00","취소","취소","매일"]
[464,"광주전남","직할","농성화정#1 T/L","2020~21년 직할 변전정비회사 총액공사","○ 효성제 170kV GIS 전자변 교체 ○ 170kV GIS 보통점검","2020-06-29 09:00","2020-06-29 14:00","2020-06-29 09:00","2020-06-29 14:00","연속"]
[465,"광주전남","직할","농성화정#1 T/L","농성E/C 154kV 이하 장기사용 GIS(Digital화) 교체 공사","충장-농성#2T/L, #2M.Tr 1차, PT & ES GIS 교체 무부하 가압 선로","2020-06-26 18:00","2020-06-27 18:00","2020-06-26 18:00","2020-06-27 18:00","연속"]
[466,"광주전남","직할","농성화정#1 T/L","농성E/C 154kV 이하 장기사용 GIS(Digital화) 교체 공사","충장-농성#2T/L, #2M.Tr 1차, PT & ES GIS 교체 무부하 가압 선로","2020-06-17 18:00","2020-06-18 09:00","2020-06-17 18:00","2020-06-18 09:00","연속"]
[467,"광주전남","직할","농성화정#1 T/L","농성E/C 154kV 이하 장기사용 GIS(Digital화) 교체 공사","충장-농성#2T/L, #2M.Tr 1차, PT & ES GIS 교체 무부하 가압 선로","2020-06-03 18:00","2020-06-04 09:00","2020-06-03 18:00","2020-06-04 09:00","연속"]
[468,"광주전남","직할","충장농성#2 T/L","농성E/C 154kV 이하 장기사용 GIS(Digital화) 교체 공사","충장-농성#2T/L, #2M.Tr 1차, PT & ES GIS 교체","2020-06-01 09:00","2020-06-27 18:00","2020-06-01 09:00","2020-06-27 18:00","연속"]
[469,"광주전남","직할","농성화정#2 T/L","2020~21년 직할 변전정비회사 총액공사","○ 효성제 170kV GIS 전자변 교체 ○ 170kV GIS 보통점검","2020-06-29 14:00","2020-06-29 18:00","2020-06-29 14:00","2020-06-29 18:00","연속"]
[470,"광주전남","직할","평동왕곡#1 T/L","왕곡 변전기자재 실증시험장 신축공사","○실증시험장 방화댐퍼 설치","2020-06-15 09:00","2020-06-23 18:00","2020-06-08 09:00","2020-06-15 18:00","연속"]
[471,"광주전남","직할","왕곡나주#1 T/L","왕곡 변전기자재 실증시험장 신축공사","○실증시험장 방화댐퍼 설치","2020-06-15 09:00","2020-06-23 18:00","2020-06-08 09:00","2020-06-15 18:00","연속"]
[472,"광주전남","직할","비아하남#2 T/L","2020~21년 직할 변전정비회사 총액공사","○ 효성제 170kV GIS 전자변 교체","2020-06-23 10:00","2020-06-23 16:00","2020-06-24 09:00","2020-06-25 18:00","연속"]
[473,"광주전남","직할","하남장성#2 T/L","2020~21년 직할 변전정비회사 총액공사","○ 효성제 170kV GIS 전자변 교체","2020-06-22 11:00","2020-06-22 16:00","2020-06-22 11:00","2020-06-22 16:00","연속"]
[474,"대구","경산","노변효목#2 T/L","154kV 시지분기 지중T/L 건설공사","노변효목T/L M/H#3,4 ~ 시지E/C구간 2π 분기,XLPE2,000 *4C*0.24km","2020-06-06 09:00","2020-06-25 18:00","2020-06-26 09:00","2020-07-08 18:00","연속"]
[475,"대구","경산","신경산노변 T/L","20년 상반기 경산P/O 170kV GIS 정밀점검","- 627 차단부 정밀점검","2020-06-08 09:00","2020-06-09 18:00","2020-06-08 09:00","2020-06-09 18:00","연속"]
[476,"대구","경산","노변효목#1 T/L","20년 상반기 경산P/O 170kV GIS 정밀점검","- 6100 무부하 가압용 테스트 선로","2020-06-02 17:00","2020-06-02 18:00","취소","취소","연속"]
[477,"대구","경산","노변효목#1 T/L","20년 상반기 경산P/O 170kV GIS 정밀점검","- 6133 무부하 가압용 테스트 선로","2020-06-04 17:00","2020-06-04 18:00","취소","취소","연속"]
[478,"대구","경산","하양반야월#2 T/L","154kV 신서분기 지중T/L 건설공사","신서E/C~154kV 하양-반야월T/L 분기맨홀(2파이 분기) 154kV XLPE1200*2C(D) 0.5km, 154kV XLPE2500*2C 0.5km","2020-06-25 09:00","2020-07-15 18:00","취소","취소","연속"]
[479,"대구","경산","신경산진량 T/L","20년 상반기 경산P/O 170kV GIS 정밀점검","- 6100 무부하 가압용 테스트선로","2020-06-11 17:00","2020-06-11 18:00","2020-06-11 17:00","2020-06-11 18:00","연속"]
[480,"대구","달성","강창성서#2 T/L","강창,성서S/S 강창-성서#2T/L 보통점검","강창,성서S/S 강창-성서#2T/L 보통점검","2020-06-07 14:00","2020-06-07 18:00","2020-06-21 09:00","2020-06-21 18:00","연속"]
[481,"대구","달성","강창성서#1 T/L","강창,성서S/S 강창-성서#1T/L 보통점검","강창,성서S/S 강창-성서#1T/L 보통점검","2020-06-07 09:00","2020-06-07 14:00","2020-06-20 09:00","2020-06-20 18:00","연속"]
[482,"대구","달성","고령S/S 154kV #62 BUS","고령S/S #62-#67 BUS TIE #1DS 정밀점검","고령S/S #62-#67 BUS TIE #1DS 정밀점검","2020-06-12 09:00","2020-06-13 14:00","2020-06-12 09:00","2020-06-13 14:00","연속"]
[483,"대구","달성","고령논공#1 T/L","고령S/S #62-#67 BUS TIE 정밀점검[TEST 선로]","고령S/S #62-#67 BUS TIE 정밀점검[TEST 선로]","2020-06-13 14:00","2020-06-14 18:00","2020-06-13 14:00","2020-06-14 18:00","매일"]
[484,"대구","달성","고령쌍림#1 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-06-22 09:00","2020-06-22 11:00","취소","취소","연속"]
[485,"대구","달성","고령쌍림#2 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-06-22 11:00","2020-06-22 14:00","취소","취소","연속"]
[486,"대구","달성","고령다산#1 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-06-22 14:00","2020-06-22 17:00","취소","취소","연속"]
[487,"대구","달성","고령쌍림#2 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-06-23 08:00","2020-06-28 18:00","취소","취소","연속"]
[488,"대구","달성","고령다산#2 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-06-23 08:00","2020-06-27 18:00","취소","취소","연속"]
[489,"대구","달성","고령S/S 154kV #66 BUS","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-06-26 17:00","2020-06-26 18:00","취소","취소","연속"]
[490,"대구","달성","고령S/S 154kV #65 BUS","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-06-26 18:00","2020-06-27 18:00","취소","취소","연속"]
[491,"대구","달성","고령다산#1 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-06-28 08:00","2020-07-02 18:00","취소","취소","연속"]
[492,"대구","달성","고령쌍림#1 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-06-28 08:00","2020-07-01 18:00","취소","취소","연속"]
[493,"대구","달성","고령논공#1 T/L","고령S/S #3Sh.C GIS 정밀점검[TEST 선로]","고령S/S #3Sh.C GIS 정밀점검[TEST 선로]","2020-06-06 14:00","2020-06-07 18:00","2020-06-06 14:00","2020-06-07 18:00","매일"]
[494,"대구","달성","고령S/S 154kV CB 6300","고령S/S #62-#67 BUS TIE 정밀점검(DS포함)","고령S/S #62-#67 BUS TIE 정밀점검(DS포함)","2020-06-12 09:00","2020-06-14 18:00","2020-06-12 09:00","2020-06-14 18:00","연속"]
[495,"대구","직할","동인내당#2 T/L","지중송전 OF케이블 절연유 채유","지중송전 OF케이블 절연유 채유","2020-06-10 10:00","2020-06-10 18:00","2020-06-10 10:00","2020-06-10 18:00","연속"]
[496,"대구","직할","동인내당#1 T/L","지중송전 OF케이블 절연유 채유","지중송전 OF케이블 절연유 채유","2020-06-11 10:00","2020-06-11 18:00","2020-06-11 10:00","2020-06-11 18:00","연속"]
[497,"대구","직할","동인공평#1 T/L","동인S/S 동인-공평#1 차단기 동작시간 측정","차단기 동작시간 측정","2020-06-09 09:30","2020-06-09 14:00","취소","취소","연속"]
[498,"대구","직할","동인공평#2 T/L","동인S/S 동인-공평#2 차단기 동작시간 측정","차단기 동작시간 측정","2020-06-09 14:00","2020-06-09 18:00","취소","취소","연속"]
[499,"대구","칠곡","남구미농소#1 T/L","154kV남구미-농소T/L 안전이격 확보공사","154kV남구미-농소T/L 안전이격 확보공사","2020-06-11 07:30","2020-06-30 18:00","2020-06-11 07:00","2020-06-30 18:00","연속"]
[500,"대구","칠곡","북대구구암#2 T/L","154kV 관음-구암T/L 지장송전선로 이설공사","관음-구암T/L 31~34호 철거/설치관련 안전확보(하단횡단)","2020-06-02 07:30","2020-06-06 18:30","2020-06-02 07:30","2020-06-06 18:30","매일"]
[501,"대구","칠곡","북대구왜관#2 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사(토목)","전력구 안전조치(강관항타시공)관련 안전이격확보","2020-06-24 08:00","2020-06-25 14:00","취소","취소","연속"]
[502,"대구","칠곡","북대구왜관#1 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사(토목)","전력구 안전조치(강관항타시공)관련 안전이격확보","2020-06-25 14:00","2020-06-26 18:00","취소","취소","연속"]
[503,"대구","칠곡","북대구구암#1 T/L","154kV 관음-구암T/L 지장송전선로 이설공사","관음-구암T/L 31~34호 철거/설치관련 안전확보(하단횡단)","2020-06-02 07:30","2020-06-06 18:30","2020-06-02 07:30","2020-06-06 18:30","매일"]
[504,"대구","칠곡","북대구관음#2 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사(토목)","전력구 안전조치(강관항타시공)관련 안전이격확보","2020-06-30 08:00","2020-07-01 18:00","취소","취소","연속"]
[505,"대구","칠곡","북대구연락#1 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사(토목)","전력구 안전조치(강관항타시공)관련 안전이격확보","2020-06-23 08:00","2020-06-24 18:00","취소","취소","연속"]
[506,"대구","칠곡","북대구연락#2 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사(토목)","전력구 안전조치(강관항타시공)관련 안전이격확보","2020-06-22 08:00","2020-06-23 18:00","취소","취소","연속"]
[507,"대구","칠곡","서대구남인동#2 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사(토목)","전력구 안전조치(강관항타시공)관련 안전이격확보","2020-06-16 08:00","2020-06-17 14:00","취소","취소","연속"]
[508,"대구","칠곡","서대구남구미#1 T/L","154kV남구미-농소T/L 안전이격 확보공사","154kV남구미-농소T/L 안전이격 확보공사","2020-06-11 07:30","2020-06-30 18:00","2020-06-11 07:00","2020-06-30 18:00","연속"]
[509,"대구","칠곡","서대구남인동#1 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사(토목)","전력구 안전조치(강관항타시공)관련 안전이격확보","2020-06-17 14:00","2020-06-18 18:00","취소","취소","연속"]
[510,"대구","포항","신포항S/S 154kV CB 6100","신포항S/S 6100 CB 조작시험","신포항S/S 6100 CB 조작시험","2020-06-25 09:00","2020-06-25 18:00","2020-06-25 09:00","2020-06-25 18:00","연속"]
[511,"대구","포항","아화건천#2 T/L","154kV 아화-건천T/L 안전이격거리 확보공사","-작업구간 : no17~22 - 철탑 2기 철거 및 설치 (no20,21) - 양회선 동시휴전","2020-06-01 08:00","2020-06-07 18:00","2020-06-08 08:00","2020-06-14 18:00","연속"]
[512,"대구","포항","아화건천#1 T/L","154kV 아화-건천T/L 안전이격거리 확보공사","- 작업구간 : No.17-22 - 철탑 2기 철거 및 설치(no20,21) - 양회선 동시휴전","2020-06-01 08:00","2020-06-07 18:00","2020-06-08 08:00","2020-06-14 18:00","연속"]
[513,"대구","포항","아화영천#2 T/L","아화S/S 6100 GIS 정밀점검 공사(TEST)","아화S/S 6102 DS 정밀점검 무부하가압","2020-06-03 17:00","2020-06-03 18:00","취소","취소","연속"]
[514,"대구","포항","아화S/S 154kV #2 BUS","아화S/S 6100 GIS 정밀점검 공사","아화S/S 6102 DS 정밀점검","2020-06-02 14:00","2020-06-03 18:00","취소","취소","연속"]
[515,"대구","포항","아화S/S 154kV CB 6100","아화S/S 6100 GIS 정밀점검 공사","아화S/S 6100 GIS 정밀점검","2020-06-01 09:00","2020-06-03 18:00","취소","취소","연속"]
[516,"대구","포항","아화S/S 154kV #1 BUS","아화S/S 6100 GIS 정밀점검 공사","아화S/S 6101 DS 정밀점검","2020-06-01 09:00","2020-06-02 14:00","취소","취소","연속"]
[517,"경북","구미","남인동인동#1 T/L","2020-21년 구미전력지사 변전정비업체 총액공사","-남인동S/S : LA 보통점검, 인동S/S: GIS조작시험","2020-06-18 09:00","2020-06-18 14:00","2020-06-18 09:00","2020-06-18 14:00","연속"]
[518,"경북","구미","남인동인동#2 T/L","2020-21년 구미전력지사 변전정비업체 총액공사","-남인동S/S : LA 보통점검, 인동S/S: GIS조작시험","2020-06-18 14:00","2020-06-18 18:00","2020-06-18 14:00","2020-06-18 18:00","연속"]
[519,"경북","구미","청리상주#1 T/L","2020-21년 구미전력지사 변전정비업체 총액공사","- LA 초기점검","2020-06-05 09:00","2020-06-05 14:00","2020-06-05 09:00","2020-06-05 14:00","연속"]
[520,"경북","영주","신영주안동#1 T/L","신영주S/S 154kV 옥외철구설비 현대화공사","전력구 및 기기기초 설치 관련 파일시공 - 상부모선 및 임시철거 - 170kV GIS 부지 마이크로파일 시공(토목)","2020-06-04 09:00","2020-06-04 18:00","2020-06-04 09:00","2020-06-04 18:00","연속"]
[521,"경북","영주","신영주안동#2 T/L","신영주S/S 154kV 옥외철구설비 현대화공사","전력구 및 기기기초 설치 관련 파일시공 - 상부모선 임시철거 - 170kV GIS 부지 마이크로파일 시공(토목)","2020-06-05 09:00","2020-06-05 18:00","2020-06-05 09:00","2020-06-05 18:00","연속"]
[522,"경북","영주","점촌문경 T/L","2020-21년 영주전력지사 변전정비회사 총액공사","-. 점촌S/S : 657 CB 보통점검/차단기 전자변 교체 -. 문경S/S : 617 CB 보통점검","2020-06-13 09:00","2020-06-13 18:00","2020-06-13 09:00","2020-06-13 18:00","연속"]
[523,"경북","직할","영덕진보#2 T/L","154kV 영덕-진보#2T/L 전선교체공사","154kV 영덕-진보#2T/L 전선교체공사","2020-06-11 08:00","2020-06-19 18:00","2020-06-17 08:00","2020-06-25 18:00","연속"]
[524,"경북","직할","영덕진보#1 T/L","154kV 영덕-진보#1T/L 전선교체공사","154kV 영덕-진보#1T/L 전선교체공사","2020-06-02 08:00","2020-06-10 18:00","2020-06-08 08:00","2020-06-16 18:00","연속"]
[525,"경북","직할","현종산풍력평해#1 T/L","154kV 평해S/S 옥외철구설비 현대화 공사","○현종산풍력-평해#1T/L 휴전 - 인출모선 조정, 보호반 이설, 전력선 교체, 준공시험","2020-06-29 09:00","2020-07-02 18:00","취소","취소","연속"]
[526,"경북","직할","현종산풍력평해#2 T/L","154kV 평해S/S 옥외철구설비 현대화 공사","○현종산풍력-평해#2T/L 휴전 - #3M.Tr 상부모선 설치(안전이격거리 확보휴전)","2020-06-22 09:00","2020-06-22 18:00","2020-06-22 09:00","2020-06-22 18:00","연속"]
[527,"경북","직할","풍산안동CC#1 T/L","20~21년 경북본부 직할 변전정비회사 총액공사","안동복합,풍산S/S 안동CC-풍산 #1 T/L GIS 조작시험","2020-06-24 09:00","2020-06-24 18:00","2020-06-24 09:00","2020-06-24 18:00","연속"]
[528,"경북","직할","풍산안동CC#2 T/L","20~21년 경북본부 직할 변전정비회사 총액공사","안동복합,풍산S/S 안동CC-풍산 #2 T/L GIS 조작시험","2020-06-25 09:00","2020-06-25 18:00","2020-06-25 09:00","2020-06-25 18:00","연속"]
[529,"경북","직할","안동풍산 T/L","20~21년 경북본부 직할 변전정비회사 총액공사","풍산S/S 안동-풍산T/L GIS 조작시험","2020-06-23 09:00","2020-06-23 18:00","2020-06-23 09:00","2020-06-23 18:00","연속"]
[530,"부산울산","동부산","구서노포#2 T/L","'20-21년 송전정비회사 총액공사","애자교체 : 1호","2020-06-23 08:00","2020-06-23 18:00","2020-06-23 08:00","2020-06-23 18:00","연속"]
[531,"부산울산","동부산","구서명장#1 T/L","동부산전력지사 가공송전 취약설비 정비공사","압축인류크램프 정비 구간 : 3호, 20호","2020-06-25 08:00","2020-06-26 18:00","2020-06-25 08:00","2020-06-26 18:00","연속"]
[532,"부산울산","동부산","신양산구서#1 T/L","동부산전력지사 가공송전 취약설비 정비공사","154kV 구서-명장#1T/L 안전이격확보용","2020-06-25 08:00","2020-06-26 18:00","2020-06-25 08:00","2020-06-26 18:00","연속"]
[533,"부산울산","동부산","구서명장#2 T/L","동부산전력지사 가공송전 취약설비 정비공사","압축인류크램프 정비 구간 : 1,2,3,14호","2020-06-30 08:00","2020-07-02 18:00","2020-06-30 08:00","2020-07-02 18:00","연속"]
[534,"부산울산","동부산","신양산구서#2 T/L","동부산전력지사 가공송전 취약설비 정비공사","154kV 구서-명장#2T/L 안전이격확보용","2020-06-30 08:00","2020-07-02 18:00","2020-06-30 08:00","2020-07-02 18:00","연속"]
[535,"부산울산","동부산","구서노포#2 T/L","구서S/S 154kV GIS 정밀점검공사 시험가압","구서S/S 154kV GIS 정밀점검공사 시험가압(6433)","2020-06-10 17:00","2020-06-10 18:00","2020-06-10 17:00","2020-06-10 18:00","연속"]
[536,"부산울산","동부산","명례정관 T/L","20년도 가공송전 순시점검 위탁공사(수목전지)","154kV 명례-정관T/L 선하지 수목전지 작업 ○작업구간 : 22호~24호","2020-06-18 09:00","2020-06-18 18:00","2020-06-18 09:00","2020-06-18 18:00","연속"]
[537,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 154kV GIS 정밀점검공사 시험가압","서창S/S 154kV GIS 정밀점검공사 시험가압(6133)","2020-06-02 17:00","2020-06-02 18:00","2020-06-02 17:00","2020-06-02 18:00","연속"]
[538,"부산울산","동부산","웅촌서창#2 T/L","서창S/S 154kV GIS 정밀점검공사 시험가압","서창S/S 154kV GIS 정밀점검공사 시험가압(6133)","2020-06-03 17:00","2020-06-03 18:00","2020-06-03 17:00","2020-06-03 18:00","연속"]
[539,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 154kV GIS 정밀점검공사 시험가압","서창S/S 154kV GIS 정밀점검공사 시험가압(6233)","2020-06-05 17:00","2020-06-05 18:00","2020-06-05 17:00","2020-06-05 18:00","연속"]
[540,"부산울산","동부산","웅촌서창#2 T/L","서창S/S 154kV GIS 정밀점검공사 시험가압","서창S/S 154kV GIS 정밀점검공사 시험가압(6233)","2020-06-06 17:00","2020-06-06 18:00","2020-06-06 17:00","2020-06-06 18:00","연속"]
[541,"부산울산","동부산","신양산시랑#1 T/L","[10차] 345kV 신양산S/S 현대화공사","1.내용 - 154kV 신양산-시랑#1, #2M.Tr 2차 인출변경 및 보호반 대체 - 신양산-고리NP#2T/L 보호배전반 이설","2020-06-13 09:00","2020-06-27 18:00","2020-06-13 09:00","2020-06-27 18:00","연속"]
[542,"부산울산","동부산","수영우동 T/L","우동S/S 154kV GIS 전자변교체","우동S/S 154kV GIS 전자변교체(수영-우동T/L)","2020-06-27 09:30","2020-06-27 17:00","2020-06-27 09:30","2020-06-27 17:00","연속"]
[543,"부산울산","동부산","정관고리NP T/L","'20-21년 송전정비회사 총액공사","애자교체 : 3호","2020-06-25 08:00","2020-06-25 18:00","2020-06-25 08:00","2020-06-25 18:00","연속"]
[544,"부산울산","북부산","매리김해#1 T/L","154kV 호포-매리T/L 24호 변위철탑 정비공사","#1T/L 임시선로 설치(4회선철탑, 호포-매리#1 포함)","2020-06-13 07:00","2020-06-14 18:00","2020-06-13 07:00","2020-06-14 18:00","연속"]
[545,"부산울산","북부산","호포매리#2 T/L","154kV 호포-매리T/L 24호 변위철탑 정비공사","#2T/L 임시선로 설치(4회선철탑, 매리-김해#2 포함)","2020-06-06 07:00","2020-06-07 18:00","2020-06-06 07:00","2020-06-07 18:00","연속"]
[546,"부산울산","북부산","매리김해#2 T/L","154kV 호포-매리T/L 24호 변위철탑 정비공사","#2T/L 임시선로 설치(4회선철탑, 호포-매리#2 포함)","2020-06-06 07:00","2020-06-07 18:00","2020-06-06 07:00","2020-06-07 18:00","연속"]
[547,"부산울산","북부산","호포매리#1 T/L","154kV 호포-매리T/L 24호 변위철탑 정비공사","#1T/L 임시선로 설치(4회선철탑, 매리-김해#1 포함)","2020-06-13 07:00","2020-06-14 18:00","2020-06-13 07:00","2020-06-14 18:00","연속"]
[548,"부산울산","북부산","물금삼랑진PP#1 T/L","154kV 물금-삼랑진#1T/L 노후 금구류 및 전선교체공사","154kV 물금-삼랑진#1T/L 노후 금구류 및 전선교체공사(1~58호, 금구류교체 44호, 전선교체 12.405C-km)","2020-06-10 07:30","2020-06-20 18:00","2020-06-10 07:30","2020-06-20 18:00","연속"]
[549,"부산울산","북부산","북부산미남#2 T/L","20-21년 북부산전력지사 변전총액공사","북부산S/S 154kV 북부산-미남#2T/L GIS 하자점검","2020-06-16 10:00","2020-06-16 18:00","2020-06-16 10:00","2020-06-16 18:00","연속"]
[550,"부산울산","북부산","북부산S/S 154kV CB 6200","20-21년 북부산전력지사 변전총액공사","북부산S/S 154kV #2 BUS-TIE(6200) 하자점검","2020-06-09 10:00","2020-06-09 18:00","2020-06-09 10:00","2020-06-09 18:00","연속"]
[551,"부산울산","북부산","북부산S/S 154kV CB 6100","20-21년 북부산전력지사 변전총액공사","북부산S/S 154kV #1BUS-TIE(6100) 하자점검","2020-06-29 10:00","2020-06-29 18:00","2020-06-29 10:00","2020-06-29 18:00","연속"]
[552,"부산울산","북부산","북부산S/S 154kV SEC CB 61620","20-21년 북부산전력지사 변전총액공사","북부산S/S 154kV #61-#62 BUS-SEC GIS 하자점검","2020-06-19 10:00","2020-06-19 18:00","2020-06-19 10:00","2020-06-19 18:00","연속"]
[553,"부산울산","북부산","북부산구포#1 T/L","20-21년 북부산전력지사 변전총액공사","북부산S/S 154kV 북부산-구포#1T/L GIS 하자점검","2020-06-22 10:00","2020-06-22 18:00","2020-06-22 10:00","2020-06-22 18:00","연속"]
[554,"부산울산","북부산","북부산S/S 154kV SEC CB 60610","20-21년 북부산전력지사 변전총액공사","북부산S/S 154kV #60-#61 BUS-SEC GIS 하자점검","2020-06-23 10:00","2020-06-23 18:00","2020-06-23 10:00","2020-06-23 18:00","연속"]
[555,"부산울산","북부산","북부산S/S 154kV SEC CB 66670","20-21년 북부산전력지사 변전총액공사","북부산S/S 154kV #66-#67 BUS-SEC GIS 하자점검","2020-06-26 10:00","2020-06-26 18:00","2020-06-26 10:00","2020-06-26 18:00","연속"]
[556,"부산울산","북부산","북부산S/S 154kV SEC CB 65660","20-21년 북부산전력지사 변전총액공사","북부산S/S 154kV #65-#66 BUS-SEC GIS 하자점검","2020-06-30 10:00","2020-06-30 18:00","2020-06-30 10:00","2020-06-30 18:00","연속"]
[557,"부산울산","북부산","북부산미남#1 T/L","20-21년 북부산전력지사 변전총액공사","북부산S/S 154kV 북부산-미남#1T/L GIS 하자점검","2020-06-15 10:00","2020-06-15 18:00","2020-06-15 10:00","2020-06-15 18:00","연속"]
[558,"부산울산","북부산","양산산막#2 T/L","20-21년 북부산전력지사 변전총액공사","양산S/S 154kV 양산-산막#2T/L GIS 초기점검","2020-06-12 10:00","2020-06-12 18:00","2020-06-12 10:00","2020-06-12 18:00","연속"]
[559,"부산울산","북부산","양산산막#1 T/L","20-21년 북부산전력지사 변전총액공사","양산S/S 154kV 양산-산막#1T/L GIS 초기점검","2020-06-11 10:00","2020-06-11 18:00","2020-06-11 10:00","2020-06-11 18:00","연속"]
[560,"부산울산","북부산","삼랑진PP양산(SA)#1 T/L","20-21년 북부산전력지사 변전총액공사","양산S/S 154kV 양산-삼랑진PPT/L GIS 초기점검","2020-06-02 10:00","2020-06-02 18:00","2020-06-02 10:00","2020-06-02 18:00","연속"]
[561,"부산울산","북부산","엄궁학장#1 T/L","20-21 북부산전력지사 변전총액공사","엄궁,학장S/S 154kV 엄궁-학장#1T/L 송전선로보호반 대체공사","2020-06-17 10:00","2020-06-19 18:00","2020-06-17 10:00","2020-06-19 18:00","연속"]
[562,"부산울산","북부산","엄궁S/S 154kV #65 BUS","2020 북부산전력지사 154kV GIS 정밀점검","엄궁S/S 154kV #1M.Tr 1차 GIS(6133) 정밀점검 (#2BUS 휴전 및 시험가압)","2020-06-07 18:00","2020-06-07 19:00","2020-06-07 18:00","2020-06-07 19:00","연속"]
[563,"부산울산","북부산","엄궁S/S 154kV #65 BUS","2020 북부산전력지사 154kV GIS 정밀점검","엄궁S/S 154kV #2M.Tr 1차 GIS(6233) 정밀점검 (#2BUS 휴전 및 시험가압)","2020-06-14 17:00","2020-06-14 18:00","2020-06-14 17:00","2020-06-14 18:00","연속"]
[564,"부산울산","북부산","모라엄궁#1 T/L","2020 북부산전력지사 154kV GIS 정밀점검","엄궁S/S 154kV 모라-엄궁#1T/L GIS(667) 정밀점검","2020-06-08 09:00","2020-06-10 18:00","2020-06-08 09:00","2020-06-10 18:00","연속"]
[565,"부산울산","북부산","엄궁S/S 154kV #65 BUS","2020 북부산전력지사 154kV GIS 정밀점검","엄궁S/S 154kV 모라-엄궁#1T/L GIS(667) 정밀점검 (#2BUS 휴전)","2020-06-09 14:00","2020-06-10 18:00","2020-06-09 14:00","2020-06-10 18:00","연속"]
[566,"부산울산","북부산","엄궁S/S 154kV #60 BUS","2020 북부산전력지사 154kV GIS 정밀점검","엄궁S/S 154kV 모라-엄궁#1T/L GIS(667) 정밀점검 (#1BUS 휴전)","2020-06-08 09:00","2020-06-09 14:00","2020-06-08 09:00","2020-06-09 14:00","연속"]
[567,"부산울산","북부산","엄궁학장#2 T/L","20-21 북부산전력지사 변전총액공사","엄궁,학장S/S 154kV 엄궁-학장#2T/L 송전선로보호반 대체공사","2020-06-24 10:00","2020-06-26 18:00","2020-06-24 10:00","2020-06-26 18:00","연속"]
[568,"부산울산","북부산","호포S/S 154kV #65 BUS","2020 북부산전력지사 154kV GIS 정밀점검","호포S/S 154kV #1M.Tr 1차 GIS(6133) 정밀점검 (#2BUS 휴전)","2020-06-30 14:00","2020-07-01 18:00","2020-06-30 14:00","2020-07-01 18:00","연속"]
[569,"부산울산","북부산","호포S/S 154kV #60 BUS","2020 북부산전력지사 154kV GIS 정밀점검","호포S/S 154kV #1M.Tr 1차 GIS(6133) 정밀점검 (#1BUS 휴전)","2020-06-29 09:00","2020-06-30 14:00","2020-06-29 09:00","2020-06-30 14:00","연속"]
[570,"부산울산","북부산","호포물금 T/L","2020 북부산전력지사 154kV GIS 정밀점검","호포S/S 154kV #1M.Tr 1차 GIS(6133) 정밀점검 (#1DS 측 시험가압 )","2020-06-30 13:00","2020-06-30 14:00","2020-06-30 13:00","2020-06-30 14:00","연속"]
[571,"부산울산","서부산","서부산다대#2 T/L","154kV 서부산-다대T/L 지장이설 및 선종교체공사","1. 선로명 : 154kV 서부산-다대#2T/L 2. 구 간 : J/B#2 ~ J/B#5(1.01km) 3. 작업내용 : 을숙도대교-장림고개간 지하차도 건설공사에 따른 지장이설(선종교체 병행)","2020-06-08 09:00","2020-08-14 18:00","2020-06-08 09:00","2020-08-14 18:00","연속"]
[572,"부산울산","서부산","서부산S/S 154kV #65 BUS","서부산S/S 154kV #3ST GIS 정밀점검","서부산S/S 154kV #3ST GIS 정밀점검 [2DS 점검]","2020-06-06 09:00","2020-06-06 18:00","2020-06-06 09:00","2020-06-06 18:00","연속"]
[573,"부산울산","서부산","서부산다대#2 T/L","서부산S/S 154kV #3ST GIS 정밀점검","서부산S/S 154kV #3ST GIS 정밀점검 [2DS 점검 시험가압]","2020-06-06 16:00","2020-06-06 18:00","2020-06-06 16:00","2020-06-06 18:00","연속"]
[574,"부산울산","서부산","서부산S/S 154kV #60 BUS","서부산S/S 154kV #3ST GIS 정밀점검","서부산S/S 154kV #3ST GIS 정밀점검 [1DS+CB 점검]","2020-06-04 09:00","2020-06-05 18:00","2020-06-04 09:00","2020-06-05 18:00","연속"]
[575,"부산울산","서부산","서부산S/S 154kV CB 657","서부산S/S 154kV #3ST GIS 정밀점검","서부산S/S 154kV #3ST GIS 정밀점검","2020-06-04 09:00","2020-06-06 18:00","2020-06-04 09:00","2020-06-06 18:00","연속"]
[576,"부산울산","서부산","서부산S/S 154kV #60 BUS","154kV 서부산-다대T/L 지장이설 및 선종교체공사","1. 선로명 : 154kV 서부산-다대#2T/L 2. 구 간 : J/B#2 ~ J/B#5(1.01km) 3. 작업내용 : 을숙도대교-장림고개간 지하차도 건설공사에 따른 지장이설(선종교체 병행) ] 4. 휴전요청 사유 : 시험가압 후 앵글체크 시 서부산S/S측 모선절체(#60->#65)","2020-06-01 09:00","2020-06-01 18:00","2020-06-01 09:00","2020-06-01 18:00","연속"]
[577,"부산울산","서부산","서부산다대#2 T/L","서부산S/S 154kV #3ST GIS 정밀점검","서부산S/S 154kV #3ST GIS 정밀점검 [1DS+CB 점검 시험가압]","2020-06-05 16:00","2020-06-05 18:00","2020-06-05 16:00","2020-06-05 18:00","연속"]
[578,"부산울산","서부산","신녹산녹산#2 T/L","신녹산S/S 154kV #1Sh.C 차단기 내부점검","신녹산S/S 154kV #1Sh.C 차단기 내부점검 차단기교체공사 시험가압 24H 시험가압선로","2020-06-04 18:00","2020-06-05 18:00","2020-06-04 18:00","2020-06-05 18:00","연속"]
[579,"부산울산","서부산","신녹산용원#1 T/L","신녹산S/S 154kV 신녹산-용원#1T/L 차단기동작시험","신녹산S/S 154kV 신녹산-용원#1T/L 차단기동작시험 용원S/S 154kV 신녹산-용원#1T/L 차단기동작시험","2020-06-22 10:00","2020-06-22 18:00","2020-06-22 10:00","2020-06-22 18:00","연속"]
[580,"부산울산","서부산","신녹산용원#2 T/L","신녹산S/S 154kV 신녹산-용원#2T/L 차단기동작시험","신녹산S/S 154kV 신녹산-용원#2T/L 차단기동작시험 용원S/S 154kV 신녹산-용원#2T/L 차단기동작시험","2020-06-23 10:00","2020-06-23 18:00","2020-06-23 10:00","2020-06-23 18:00","연속"]
[581,"부산울산","서부산","다대신평 T/L","154kV 다대-신평T/L 등 3개T/L 지장이설공사","[을숙도대교~장림고개 간 지하차도 건설공사] 지장 지중송전설비 이설 - 케이블 포설 : 4구간, 접속 : IJ(9상), NJ(12상)","2020-06-17 09:00","2020-06-30 18:00","2020-06-17 09:00","2020-06-30 18:00","연속"]
[582,"부산울산","울산","두왕영남TP#1 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2020-06-29 07:00","2020-06-29 18:00","2020-06-29 07:00","2020-06-29 18:00","연속"]
[583,"부산울산","울산","두왕영남TP#2 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2020-06-26 07:00","2020-06-28 18:00","2020-06-25 07:00","2020-06-26 18:00","연속"]
[584,"부산울산","울산","두왕영남TP#1 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2020-06-21 07:00","2020-06-25 18:00","2020-06-21 07:00","2020-06-24 18:00","연속"]
[585,"부산울산","울산","두왕영남TP#2 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2020-06-19 07:00","2020-06-20 18:00","2020-06-19 07:00","2020-06-20 18:00","연속"]
[586,"부산울산","울산","신울산두왕#2 T/L","2020년도 가공송전선로 순시점검 위탁공사","154kV 신울산-두왕#2T/L 정밀점검 - No.2~5(5기)","2020-06-30 08:30","2020-06-30 18:00","2020-06-30 08:30","2020-06-30 18:00","연속"]
[587,"부산울산","울산","신온산성암#2 T/L","345kV 신울산복합-북부산T/L 건설공사","154kV 신온산-성암T/L 임시선로 구성 -구간:기설21호~기설27호","2020-06-26 07:00","2020-07-05 18:00","2020-06-26 07:00","2020-07-05 18:00","연속"]
[588,"부산울산","울산","신울산S/S 154kV #66 BUS","20-21년 변전정비회사 총액공사","DS 접촉자 불량 보수 #66BUS LA 보통점검","2020-06-24 09:00","2020-06-24 18:00","2020-06-24 09:00","2020-06-24 18:00","연속"]
[589,"부산울산","울산","신울산울산#2 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2020-06-29 07:00","2020-06-30 18:00","2020-06-23 07:00","2020-06-24 18:00","연속"]
[590,"부산울산","울산","신울산울산#1 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2020-06-11 07:00","2020-06-12 18:00","2020-06-15 07:00","2020-06-16 18:00","연속"]
[591,"부산울산","울산","신울산울산#2 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2020-06-14 07:00","2020-06-15 18:00","2020-06-17 07:00","2020-06-18 18:00","연속"]
[592,"부산울산","울산","언양산막#2 T/L","20-21년 변전정비회사 총액공사","GIS 디지털 압력계 교체","2020-06-03 09:00","2020-06-03 18:00","2020-06-03 09:00","2020-06-03 18:00","연속"]
[593,"부산울산","울산","신울산언양#1 T/L","20-21년 변전정비회사 총액공사","GIS 보통점검, 디지털 압력계 교체","2020-06-22 09:00","2020-06-22 18:00","2020-06-22 09:00","2020-06-22 18:00","연속"]
[594,"부산울산","울산","신울산언양#2 T/L","20-21년 변전정비회사 총액공사","GIS 보통점검, 디지털 압력계 교체","2020-06-23 09:00","2020-06-23 18:00","2020-06-23 09:00","2020-06-23 18:00","연속"]
[595,"부산울산","울산","언양산막#1 T/L","20-21년 변전정비회사 총액공사","GIS 디지털 압력계 교체","2020-06-02 09:00","2020-06-02 18:00","2020-06-02 09:00","2020-06-02 18:00","연속"]
[596,"부산울산","울산","용연울산TP#2 T/L","20-21년 변전정비회사 총액공사","GIS 하자점검","2020-06-03 09:00","2020-06-03 18:00","2020-06-03 09:00","2020-06-03 18:00","연속"]
[597,"부산울산","울산","용연울산TP#1 T/L","2020년 용연S/S 154kV 장기사용 GIS 교체공사","○ 154kV SK에너지 FCC #1T/L #2BUS, #2DS, CB, 상부BUS, 챔버까지 시험가압(24Hr)","2020-06-04 18:00","2020-06-05 18:00","2020-06-04 18:00","2020-06-05 18:00","연속"]
[598,"부산울산","울산","용연처용#1 T/L","345kV 신울산복합-북부산T/L 건설공사","1. 345kV 2회선 가선공사(신설13호~15호) 2. 154kV 용연-처용T/L 기설선로 철거 및 신설선로 가선공사/전선이동 (기설7호~12호)","2020-06-11 07:00","2020-06-22 18:00","2020-06-11 07:00","2020-06-22 18:00","연속"]
[599,"부산울산","울산","용연처용#2 T/L","20-21년 변전정비회사 총액공사","GIS 하자점검,LA보통점검","2020-06-24 09:00","2020-06-24 18:00","2020-06-24 09:00","2020-06-24 18:00","연속"]
[600,"부산울산","울산","용연울산TP#1 T/L","20-21년 변전정비회사 총액공사","GIS 하자점검","2020-06-02 09:00","2020-06-02 18:00","2020-06-02 09:00","2020-06-02 18:00","연속"]
[601,"부산울산","울산","울산울산TP#1 T/L","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","1. 울산-울산T/P #1T/L 송전선 이설 2. 시험가압일정 / 대상/가압경로 ㅇ 07.03 17:00~(1h) / 울산-울산TP#1T/L / #60BUS, 자체선로 1DS(투입)","2020-06-29 09:00","2020-07-03 18:00","2020-06-21 08:30","2020-06-26 18:00","연속"]
[602,"부산울산","울산","울산T/P 154kV #65 BUS","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","1. 65-66 SEC-GIS 대체 2. 시험가압일정 / 대상/가압경로 ㅇ 6.27 17:00~(1h) 65BUS, 65-66-1(투입) / 울산-울산TP #1","2020-06-27 17:00","2020-06-27 18:00","2020-06-20 17:00","2020-06-20 18:00","연속"]
[603,"부산울산","울산","울산울산TP#1 T/L","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","1. 65-66 SEC-GIS 대체 2. 시험가압일정 / 대상/가압경로 ㅇ 6.27 17:00~(1h) 65BUS, 65-66-1(투입) / 울산-울산TP #1","2020-06-27 17:00","2020-06-27 18:00","2020-06-20 17:00","2020-06-20 18:00","연속"]
[604,"부산울산","울산","용연울산TP#1 T/L","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","1. 65-66 SEC-GIS 대체 ㅇ 66 BUS GIB 설치 2. 신)울산-울산TP#1, 울산피피TL 2DS 설치(울산-울산TP#1 송전선 이설 포함) 3. 시험가압일정 / 대상/가압경로 ㅇ 6.26 17:00~(24h) 66BUS, 65-66-0,-2 / 용연-울산TP #1","2020-06-26 17:00","2020-06-27 17:00","2020-06-19 17:00","2020-06-20 17:00","연속"]
[605,"부산울산","울산","울산T/P 154kV #66 BUS","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","1. 65-66 SEC-GIS 대체 ㅇ 66BUS GIB 철거 및 END 커버 설치 2. 시험가압일정 / 대상/가압경로 ㅇ 6.15 17:00~(1h) 66BUS / 용연-울산TP #1","2020-06-15 09:00","2020-06-16 18:00","2020-06-08 10:00","2020-06-09 18:00","연속"]
[606,"부산울산","울산","울산T/P 154kV SEC CB 65660","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","1. 65-66 SEC-GIS 대체 2. 신)울산-울산TP#1, 울산피피TL 2DS 설치(울산-울산TP#1 송전선 이설 포함) 3. 시험가압일정 / 대상/가압경로 ㅇ 6.15 17:00~(1h) 66BUS / 용연-울산TP #1 ㅇ 6.23 18:00~(24h) 65BUS, 65-66-1DS / 울산-울산TP #1 ㅇ 6.26 17:00~(24h) 66BUS, 65-66-0,-2 / 용연-울산TP #1 ㅇ 6.27 17:00~(1h) 65BUS, 65-66-1 / 울산-울산TP #1","2020-06-15 09:00","2020-07-02 18:00","2020-06-08 10:00","2020-06-26 18:00","연속"]
[607,"부산울산","울산","용연울산TP#1 T/L","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","1. 65-66 SEC-GIS 대체 ㅇ 66BUS GIB 철거 및 END 커버 설치 2. 시험가압일정 / 대상/가압경로 ㅇ 6.15 17:00~(1h) 66BUS / 용연-울산TP #1","2020-06-16 17:00","2020-06-16 18:00","2020-06-09 17:00","2020-06-09 18:00","연속"]
[608,"부산울산","울산","울산T/P 154kV #65 BUS","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","1. 65-66 SEC-GIS 대체 ㅇ 65-66 SEC GIS 철거 및 설치 2. 신)울산-울산TP#1, 울산피피TL 2DS 설치(울산-울산TP#1 송전선 이설 포함) 3. 시험가압일정 / 대상/가압경로 ㅇ 6.23 18:00~(24h) 65BUS, 65-66-1DS(개방) / 울산-울산TP #1","2020-06-17 09:00","2020-06-24 18:00","2020-06-10 08:30","2020-06-17 18:00","연속"]
[609,"부산울산","울산","울산울산TP#1 T/L","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","1. 65-66 SEC-GIS 대체 ㅇ 65-66 SEC GIS 철거 및 설치 2. 신)울산-울산TP#1, 울산피피TL 2DS 설치(울산-울산TP#1 송전선 이설 포함) 3. 시험가압일정 / 대상/가압경로 ㅇ 6.23 18:00~(24h) 65BUS, 65-66-1DS(개방) / 울산-울산TP #1","2020-06-23 18:00","2020-06-24 18:00","2020-06-16 18:00","2020-06-17 18:00","연속"]
[610,"부산울산","울산","울산T/P 154kV #66 BUS","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","1. 65-66 SEC-GIS 대체 ㅇ 66 BUS GIB 설치 2. 신)울산-울산TP#1, 울산피피TL 2DS 설치(울산-울산TP#1 송전선 이설 포함) 3. 시험가압일정 / 대상/가압경로 ㅇ 6.26 17:00~(24h) 66BUS, 65-66-0,-2 / 용연-울산TP #1","2020-06-25 09:00","2020-06-27 18:00","2020-06-18 08:30","2020-06-20 18:00","연속"]
[611,"부산울산","울산","울산울산TP#1 T/L","154kV 울산S/S SW증설공사","○ 울산S/S #1BUS 시험가압 선로(24Hr)","2020-06-05 18:00","2020-06-06 18:00","2020-06-05 18:00","2020-06-06 18:00","연속"]
[612,"부산울산","울산","울산울산TP#1 T/L","154kV 울산S/S SW증설공사","○ 울산S/S #2BUS 시험가압 선로(24Hr)","2020-06-12 18:00","2020-06-13 18:00","2020-06-12 18:00","2020-06-13 18:00","연속"]
[613,"부산울산","울산","울주직동#2 T/L","20년 상반기 개폐장치 정밀점검 공사","GIS 정밀점검","2020-06-03 09:00","2020-06-04 18:00","2020-06-03 09:00","2020-06-04 18:00","연속"]
[614,"부산울산","울산","울주직동#1 T/L","20년 상반기 개폐장치 정밀점검 공사","GIS 정밀점검","2020-06-01 09:00","2020-06-02 18:00","2020-06-01 09:00","2020-06-02 18:00","연속"]
[615,"부산울산","직할","범천S/S 154kV #60 BUS","범천S/S 154kV 장기사용 GIS 대체공사(2차공정)","1.170kV 50kA 2,000A GIS(T/L) × 4CCT 대체 2.170kV 50kA 1,250A GIS(T/R) × 2CCT 대체 3.170kV 50kA 2,000A GIS(B/T) × 1CCT 대체 4.170kV 50kA PT&ES × 1CCT 대체 5.기타 부대공사 × 1식","2020-06-10 09:00","2020-06-21 18:00","2020-06-10 09:00","2020-06-21 18:00","연속"]
[616,"부산울산","직할","양정범천 T/L","범천S/S 154kV 장기사용 GIS 대체공사(2차공정)","#2BUS 시험가압 선로(1H)","2020-06-09 17:00","2020-06-09 18:00","2020-06-09 17:00","2020-06-09 18:00","연속"]
[617,"부산울산","직할","양정범천 T/L","범천S/S 154kV 장기사용 GIS 대체공사(2차공정)","#1BUS 시험가압 선로(24H)","2020-06-20 18:00","2020-06-21 18:00","2020-06-20 18:00","2020-06-21 18:00","연속"]
[618,"부산울산","직할","범천S/S 154kV #65 BUS","범천S/S 154kV 장기사용 GIS 대체공사(2차공정)","1.170kV 50kA 2,000A GIS(T/L) × 4CCT 대체 2.170kV 50kA 1,250A GIS(T/R) × 2CCT 대체 3.170kV 50kA 2,000A GIS(B/T) × 1CCT 대체 4.170kV 50kA PT&ES × 1CCT 대체 5.기타 부대공사 × 1식","2020-06-22 09:00","2020-07-03 16:00","2020-06-22 09:00","2020-07-03 16:00","연속"]
[619,"부산울산","직할","개금범천#1 T/L","범천S/S 154kV 장기사용 GIS 대체공사(2차공정)","1.170kV 50kA 2,000A GIS(T/L) × 4CCT 대체 2.170kV 50kA 1,250A GIS(T/R) × 2CCT 대체 3.170kV 50kA 2,000A GIS(B/T) × 1CCT 대체 4.170kV 50kA PT&ES × 1CCT 대체 5.기타 부대공사 × 1식","2020-06-08 09:00","2020-07-03 18:00","2020-06-08 09:00","2020-07-03 18:00","연속"]
[620,"부산울산","직할","신대연양정#2 T/L","2020년 상반기 직할 170kV GIS 정밀점검공사","신대연S/S 154kV 신대연-양정 #2/L(647) GIS 정밀점검 -차단부 및 상부BUS, Cable Head부 정밀점검 -모선DS부 점검 제외","2020-06-03 09:00","2020-06-04 18:00","2020-06-03 09:00","2020-06-04 18:00","연속"]
[621,"부산울산","직할","신대연양정#1 T/L","2020년 상반기 직할 170kV GIS 정밀점검공사","신대연S/S 154kV 신대연-양정 #1/L(637) GIS 정밀점검 -차단부 및 상부BUS, Cable Head부 정밀점검 -모선DS부 점검 제외","2020-06-01 09:00","2020-06-02 18:00","2020-06-01 09:00","2020-06-02 18:00","연속"]
[622,"경남","직할","신월삼정#2 T/L","삼정S/S 154kV 신김해-삼정#2T/L 인출변경관련 안전이격확보","삼정S/S GIS화 사업 154kV 신김해-삼정#2T/L 인출변경관련 안전이격확보 - 신김해-삼정#2T/L 하단선로 안전이격확보","2020-06-20 08:00","2020-06-21 17:30","2020-06-20 08:00","2020-06-21 17:30","연속"]
[623,"경남","직할","신월삼정#1 T/L","삼정S/S 154kV 신김해-삼정#2T/L 인출변경관련 안전이격확보","삼정S/S GIS화 사업 154kV 신김해-삼정#2T/L 인출변경관련 안전이격확보 - 신김해-삼정#2T/L 하단선로 안전이격확보","2020-06-20 08:00","2020-06-21 17:30","2020-06-20 08:00","2020-06-21 17:30","연속"]
[624,"경남","직할","신김해삼정#2 T/L","삼정S/S GIS화 사업 154kV 신김해-삼정#2T/L 인출변경","삼정S/S GIS화 사업 154kV 신김해-삼정#2T/L 인출변경 - 가공선로 인출변경 : 옥외철구 => C/H철탑","2020-06-20 08:00","2020-06-24 17:30","2020-06-20 08:00","2020-06-24 17:30","연속"]
[625,"경남","진주","함양거창#1 T/L","거창S/S 함양-거창#1T/L GIS(637) 정밀점검","거창S/S 함양-거창#1T/L GIS(637) 정밀점검 병행 : 함양S/S 함양-거창#1T/L GCB(687) 조작시험 등","2020-06-02 09:00","2020-06-03 18:00","2020-06-09 09:00","2020-06-10 18:00","연속"]
[626,"경남","진주","함양거창#2 T/L","거창S/S 함양-거창#2T/L GIS(647) 정밀점검","거창S/S 함양-거창#2T/L GIS(647) 정밀점검 병행 : 함양S/S 함양-거창#2T/L GCB(677) 조작시험 등","2020-06-04 09:00","2020-06-05 18:00","2020-06-11 09:00","2020-06-12 18:00","연속"]
[627,"경남","진주","동진주진주#2 T/L","동진주S/S 154kV 동진주-진주#2T/L GIS(647) 보통점검","동진주S/S 154kV 동진주-진주#1T/L GIS(647) 보통점검 병행 : 진주S/S 154kV 동진주-진주#1T/L GIS(637) 보통점검","2020-06-27 14:00","2020-06-27 18:00","2020-06-27 14:00","2020-06-27 18:00","연속"]
[628,"경남","진주","동진주진주#1 T/L","동진주S/S 154kV 동진주-진주#1T/L GIS(637) 보통점검","동진주S/S 154kV 동진주-진주#1T/L GIS(637) 보통점검 병행 : 진주S/S 154kV 동진주-진주#1T/L GIS(647) 보통점검","2020-06-27 09:00","2020-06-27 14:00","2020-06-27 09:00","2020-06-27 14:00","연속"]
[629,"경남","진주","동진주S/S 154kV CB 6100","동진주S/S 154kV #60-#65 BUS TIE GIS 보통점검","동진주S/S 154kV #60-#65 BUS TIE GIS 보통점검","2020-06-12 14:00","2020-06-12 18:00","2020-06-12 14:00","2020-06-12 18:00","연속"]
[630,"경남","통영","삼천포사천#1 T/L","삼천포S/S 디지털화공사","삼천포-사천#1T/L PNL 성능개선 및 케이블 이설(RTU-> 154kV LID)","2020-06-08 10:00","2020-06-08 18:00","2020-06-08 10:00","2020-06-08 18:00","연속"]
[631,"경남","통영","삼천포사천#2 T/L","삼천포S/S 디지털화공사","삼천포-사천#2T/L PNL 케이블 이설(RTU-> 154kV LID)","2020-06-09 10:00","2020-06-09 18:00","2020-06-09 10:00","2020-06-09 18:00","연속"]
[632,"경남","통영","신고성삼천포#1 T/L","삼천포S/S 디지털화공사","1. 신고성-삼천포#1T/L GIS 케이블 이설(RTU-> 154kV LID) 2. 신고성-삼천포#1T/L PNL 성능개선 및 광케이블 결선","2020-06-15 10:00","2020-06-15 18:00","2020-06-15 10:00","2020-06-15 18:00","연속"]
[633,"경남","통영","신고성삼천포#2 T/L","154kV 신고성-삼천포#2T/L PNL 대체공사","1. 154kV 신고성-삼천포#2T/L PNL 대체공사 2. 삼천포S/S 신고성-삼천포#2T/L GIS 케이블 이설(RTU-> 154kV LID) 3. 삼천포S/S 신고성-삼천포#2T/L PNL 성능개선 및 광케이블 결선","2020-06-22 10:00","2020-06-24 18:00","2020-06-22 10:00","2020-06-24 18:00","연속"]
[634,"경남","통영","신고성통영 T/L","154kV 통영-거제#1T/L 과열개소 보수","154kV 통영-거제#1T/L 과열개소 보수관련 안전이격거리 확보차","2020-06-20 09:00","2020-06-20 14:00","2020-06-20 09:00","2020-06-20 14:00","연속"]
[635,"경남","통영","통영거제#1 T/L","154kV 통영-거제#1T/L 과열개소 보수","154kV 통영-거제#1T/L 과열개소 보수(3호)","2020-06-20 09:00","2020-06-20 18:00","2020-06-20 09:00","2020-06-20 18:00","연속"]
[636,"경남","함안","가야사봉#1 T/L","가야S/S 154kV 가야-사봉#1T/L GIS 조작시험","가야S/S 154kV 가야-사봉#1T/L GIS 조작시험","2020-06-20 09:30","2020-06-20 13:30","2020-06-20 09:30","2020-06-20 13:30","연속"]
[637,"경남","함안","중리가야#2 T/L","가야S/S 154kV 중리-가야#2T/L GIS 조작시험","가야S/S 154kV 중리-가야#2T/L GIS 조작시험","2020-06-20 13:30","2020-06-20 17:30","2020-06-20 13:30","2020-06-20 17:30","연속"]
[638,"경남","함안","신월동읍#2 T/L","동읍S/S 154kV 신월-동읍#2T/L GIS 정밀점검","동읍S/S 154kV 신월-동읍#2T/L GIS 정밀점검","2020-06-16 08:30","2020-06-19 17:30","2020-06-16 08:30","2020-06-19 17:30","연속"]
[639,"경남","함안","신마산차룡#2 T/L","154kV 의창S/S 건설공사","신마산-의창#2T/L, 의창-차룡#2T/L 지중케이블 접속작업 및 무부하시험가압(실부하가압 6/30)","2020-06-01 09:00","2020-06-30 18:00","2020-06-01 09:00","2020-06-30 18:00","연속"]
[640,"경남","함안","신마산중리#2 T/L","신마산S/S 154kV 신마산-중리#2T/L CB 조작시험","신마산S/S 154kV 신마산-중리#2T/L CB 조작시험","2020-06-13 09:30","2020-06-13 17:30","2020-06-13 09:30","2020-06-13 17:30","연속"]
[641,"경남","함안","신마산중리#1 T/L","신마산S/S 154kV 신마산-중리#1T/L CB 조작시험","신마산S/S 154kV 신마산-중리#1T/L CB 조작시험","2020-06-06 09:30","2020-06-06 17:30","2020-06-06 09:30","2020-06-06 17:30","연속"]
[642,"경남","함안","진영한림정#1 T/L","진영S/S 154kV 진영-한림정#1T/L GIS 보통점검","진영S/S 154kV 진영-한림정#1T/L GIS 보통점검","2020-06-27 09:30","2020-06-27 17:30","2020-06-27 09:30","2020-06-27 17:30","연속"]
[643,"경남","함안","칠서창녕#2 T/L","칠서SS 6100,60-65PT,617,6133 GIS 대체 시험가압","칠서SS 6100,60-65PT,617,6133 GIS 대체 관련 시험가압","2020-06-04 17:00","2020-06-05 17:00","2020-06-04 17:00","2020-06-05 17:00","연속"]
[644,"경남","함안","한림정삼계#1 T/L","한림정S/S 154kV 한림정-삼계#1T/L GIS 보통점검","한림정S/S 154kV 한림정-삼계#1T/L GIS 보통점검","2020-06-10 09:30","2020-06-10 17:30","2020-06-10 09:30","2020-06-10 17:30","연속"]
[645,"경남","함안","한림정삼계#2 T/L","한림정S/S 154kV 한림정-삼계#2T/L GIS 보통점검","한림정S/S 154kV 한림정-삼계#2T/L GIS 보통점검","2020-06-11 09:30","2020-06-11 17:30","2020-06-11 09:30","2020-06-11 17:30","연속"]