{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":4,"n_cols":13,"rows_kept":4,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
["2020년도 7월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]

{"sheet":"345송부","index":1,"n_rows":77,"n_cols":13,"rows_kept":77,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
["2020년도 7월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","영등포","신광명S/S 345kV CB 7672","신광명S/S 362kV GIS 보통점검(7672)","- 차단기 동작특성 시험 - GIS 조작시험 - SF6 수분 및 SO2 측정 - 차단기 메커니즘 점검","2020-07-04 14:00","2020-07-04 18:00","취소","취소","연속"]
[2,"남서울","영등포","신광명S/S 345kV CB 7572","신광명S/S 362kV GIS 보통점검(7572)","-차단기 개폐타임 측정 - GIS 조작시험 - SF6 수분 및 SO2 측정 - 차단기 메커니즘 점검","2020-07-04 09:00","2020-07-04 14:00","취소","취소","연속"]
[3,"남서울","동서울","동서울S/S #4 M.Tr","서울 동남권지역 전기공급시설 전력구공사(동서울#2-강남5차) ","  전력구 가시설(H-Pile) 인발 작업 ","2020-07-10 09:00","2020-07-10 18:00","2020-07-05 09:00","2020-07-05 18:00","연속"]
[4,"남서울","신광명","신광명S/S #4 M.Tr","신광명S/S #4M.Tr 과열개소 보수 ","신광명S/S #4M.Tr 과열개소 보수 ","2020-07-01 09:00","2020-07-05 18:00","2020-07-01 09:00","2020-07-05 18:00","연속"]
[5,"인천","직할","신부평S/S 345kV #3 Sh.R","신부평S/S 7379CB 조작시험","신부평S/S 7379CB 조작시험","2020-07-07 09:30","2020-07-07 18:00","2020-07-07 09:30","2020-07-07 18:00","연속"]
[6,"인천","직할","신부평S/S 345kV CB 7371","신부평S/S 서인천CC신부평#3T/L 7371CB 조작시험","신부평S/S 서인천CC신부평#3T/L 7371CB 조작시험","2020-07-06 09:30","2020-07-06 14:00","2020-07-06 09:30","2020-07-06 14:00","연속"]
[7,"인천","직할","신부평S/S 345kV CB 7471","신부평S/S 서인천CC신부평#4T/L 7471CB 조작시험","신부평S/S 서인천CC신부평#4T/L 7471CB 조작시험","2020-07-06 14:00","2020-07-06 18:00","2020-07-06 14:00","2020-07-06 18:00","연속"]
[8,"경기북부","구리","미금성동#2 T/L","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 미금S/S 72Bay 관련 차단기 3대 감시제어계측 포인트이관 (→SA) - 72Bay LCP 및 배전반 모자익반 제어케이블 철거 및 재결선 - #3,4Sh.R LCP 및 배전반 모자익반 제어케이블 철거 및 재결선","2020-07-13 09:00","2020-07-17 18:00","취소","취소","연속"]
[9,"경기북부","구리","미금S/S #3 M.Tr","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - #3M.Tr 2,3차측 차단기 및 단로기 감시제어계측 포인트이관 (→SA) - #3M.Tr 2,3차측 차단기 LCP 및 모자익반 제어케이블 철거 및 재결선","2020-07-06 09:00","2020-07-10 18:00","2020-07-06 09:00","2020-07-10 18:00","연속"]
[10,"경기북부","구리","신가평포천LNGCC#1 T/L","345kV 신가평-포천LNGCC T/L 항공장애시설물 정비공사","ㅇ 항공장애표시구 설치 - No.1~2호 등 48경간","2020-07-01 07:00","2020-07-17 18:00","2020-07-04 07:00","2020-07-17 18:00","연속"]
[11,"경기북부","직할","신의정부S/S #4 M.Tr","신의정부S/S 종합예방진단시스템 설치공사","신의정부S/S 종합예방진단시스템 설치공사 주변압기 붓싱 시험탭. OLTC 센서 설치부 실측","2020-07-06 09:00","2020-07-06 18:00","2020-07-06 09:00","2020-07-06 18:00","연속"]
[12,"경기","군포","서서울#2S/S 345kV CB 7A71","서서울2S/S 서서울2-신성남#1T/L 7A71 GIS 조작시험","서서울2S/S 서서울2-신성남#1T/L 7A71 GIS 조작시험","2020-07-03 09:00","2020-07-03 18:00","2020-07-03 09:00","2020-07-03 18:00","연속"]
[13,"경기","성남","신수원S/S #1 M.Tr","20년 성남전력 변전정비회사 총액공사","신수원S/S 345kV #1 M.Tr - 2차측 GIS(조작),전자변교체 - 3차측 GIS(조작) - 1S.Tr(대체) - #1M.Tr 2차 부싱 상간온도차 보수","2020-07-02 09:00","2020-07-03 18:00","취소","취소","연속"]
[14,"경기","성남","신안성S/S 345kV #7 Sh.R","20년 성남전력 변전정비회사 총액공사","신안성S/S 345kV #7 Sh.R FEEDER GIS 보통점검 - 전자변 및 전자변 히터 설치","2020-07-06 09:00","2020-07-06 18:00","2020-07-06 09:00","2020-07-06 18:00","연속"]
[15,"강원","동해","동해S/S 345kV CB 7271","2020년 동해전력지사 변전정비 총액공사","동해S/S 345kV 신제천-동해#2T/L GIS CB 전자변 교체","2020-07-06 09:00","2020-07-06 18:00","2020-07-06 09:00","2020-07-06 18:00","연속"]
[16,"강원","동해","동해S/S 345kV CB 7200","2020년 동해전력지사 변전정비 총액공사","동해S/S 345kV 7200 GIS CB 전자변 교체","2020-07-07 09:00","2020-07-07 18:00","2020-07-07 09:00","2020-07-07 18:00","연속"]
[17,"강원","동해","동해S/S 345kV CB 7100","2020년 동해전력지사 변전정비 총액공사","동해S/S 345kV 7100 BUS TIE CB 전자변 교체","2020-07-09 09:00","2020-07-09 18:00","2020-07-09 09:00","2020-07-09 18:00","연속"]
[18,"강원","동해","동해S/S 345kV CB 7172","2020년 동해전력지사 변전정비 총액공사","동해S/S 345kV #1 M.TR 1차 GIS CB 전자변 교체","2020-07-10 09:00","2020-07-10 18:00","취소","취소","연속"]
[19,"강원","동해","동해S/S 345kV CB 7171","2020년 동해전력지사 변전정비 총액공사","동해S/S 345kV 신제천-동해#1T/L CB 전자변 교체","2020-07-08 09:00","2020-07-08 18:00","2020-07-08 09:00","2020-07-08 18:00","연속"]
[20,"강원","동해","동해S/S 345kV CB 7400","2020년 동해전력지사 변전정비 총액공사","동해S/S 345kV 7400 GIS CB 전자변 교체","2020-07-14 09:00","2020-07-14 18:00","취소","취소","연속"]
[21,"강원","동해","동해S/S 345kV CB 7472","2020년 동해전력지사 변전정비 총액공사","동해S/S 345kV #2 M.Tr 1차 GIS CB 전자변 교체","2020-07-15 09:00","2020-07-15 18:00","취소","취소","연속"]
[22,"강원","동해","동해S/S 345kV CB 7471","2020년 동해전력지사 변전정비 총액공사","동해S/S 345kV 동해-양양P/PT/L GIS CB 전자변 교체","2020-07-13 09:00","2020-07-13 18:00","취소","취소","연속"]
[23,"강원","동해","삼척GP한울NP#1 T/L","2020년 동해전력지사 가공송전선로 순시점검 위탁공사","송전선로 정밀점검","2020-07-20 09:00","2020-07-24 18:00","2020-07-20 09:00","2020-07-24 18:00","매일"]
[24,"강원","동해","삼척GP한울NP#2 T/L","2020년 동해전력지사 가공송전선로 순시점검 위탁공사","송전선로 정밀점검","2020-07-27 09:00","2020-07-31 18:00","2020-07-27 09:00","2020-07-31 18:00","매일"]
[25,"충북","청주","남청주S/S #3 M.Tr","#3M.Tr 영상전압 발생개소 점검","#3M.Tr 영상전압 발생개소 점검","2020-07-01 09:00","2020-07-03 18:00","2020-07-01 09:00","2020-07-03 18:00","연속"]
[26,"충북","충주","신제천신충주#1 T/L","345kV 곤지암-신충주 등 4개T/L 전력선교체공사","- 전선교체 휴전작업 관련 4회선구간 병행휴전 - 본작업개소 345kV 곤지암-신충주T/L No.157~163","2020-07-01 08:00","2020-07-08 18:00","취소","취소","연속"]
[27,"충북","충주","신제천S/S #4 M.Tr","20-21년 충주전력 변전정비회사 총액공사","신제천변전소 #4M.Tr 3차측 절연보강. 3차 VCB(4479. 4289. 4589) 초기점검.","2020-07-09 09:00","2020-07-10 18:00","2020-07-09 09:00","2020-07-10 18:00","연속"]
[28,"충북","충주","곤지암신충주#2 T/L","345kV 곤지암-신충주 등 4개T/L 전력선교체공사","전선접소개소 해소 전력선교체공사","2020-07-03 08:00","2020-07-17 18:00","취소","취소","연속"]
[29,"충북","충주","곤지암신충주#2 T/L","345kV 곤지암-신충주 등 4개T/L 전력선교체공사","전선접소개소 해소 전력선교체공사","2020-07-05 08:00","2020-07-19 18:00","취소","취소","연속"]
[30,"대전충남","서산","북당진현대제철 T/L","345kV 신송산분기T/L 건설사업","- 해당구간 : No.71 ~ No.69 구간내 No.70 선로 - 공사내용 : No.70 선로 가철탑 이설 전력선 공중이동 ACSR/AW 480SQ x 4B x 2C (0.793km)","2020-07-06 07:00","2020-07-09 18:00","취소","취소","연속"]
[31,"대전충남","서산","신당진개폐소현대제철 T/L","345kV 신송산분기T/L 건설사업","- 해당구간 : No.71 ~ No.69 구간내 No.70 선로 - 공사내용 : No.70 선로 가철탑 이설 전력선 공중이동 ACSR/AW 480SQ x 4B x 2C (0.793km)","2020-07-10 07:00","2020-07-13 18:00","취소","취소","연속"]
[32,"전북","군산","군산신김제#2 T/L","군산신김제T/L 추락방지설비 시설공사","-추락방지설비 설치 : 64,65,82호","2020-07-09 07:00","2020-07-09 13:00","2020-07-09 07:00","2020-07-09 13:00","연속"]
[33,"전북","군산","군산신김제#1 T/L","군산신김제T/L 추락방지설비 시설공사","-추락방지설비 설치 : 64,65,82호","2020-07-08 07:00","2020-07-08 13:00","2020-07-08 07:00","2020-07-08 13:00","연속"]
[34,"전북","김제","신김제S/S 345kV CB 7471","신김제S/S 345kV 7471 CB 조작시험","신김제S/S 345kV 7471 CB 조작시험(선로 활선, 7471 단일기기 휴전)","2020-07-01 10:00","2020-07-01 14:00","2020-07-01 10:00","2020-07-01 14:00","연속"]
[35,"전북","직할","신남원S/S 345kV #70 BUS","신남원S/S GAS 누기보수공사(#70BUS)","신남원S/S GAS 누기보수공사 [휴전개소 : #70BUS] [작업개소] - 7271/7200(04/07~04/27) - 7471(05/26~05/29) - 7371(05/30~06/02) - 7671/7661(06/15~06/28)","2020-07-14 10:00","2020-07-17 18:00","취소","취소","연속"]
[36,"전북","직할","신남원의령#1 T/L","신남원S/S GAS 누기보수공사(7371)","신남원S/S GAS 누기보수공사 [휴전개소 : 신남원-의령#1T/L, #70BUS] [작업개소 : 7371(A)]","2020-07-18 10:00","2020-07-19 18:00","취소","취소","연속"]
[37,"전북","직할","신남원의령#2 T/L","신남원S/S GAS 누기보수공사(7452/7471)","신남원S/S GAS 누기보수공사 [휴전개소 : 신남원-의령#2T/L, #70BUS)] [작업개소 : 7452DS(A/B/C), 7471(B)]","2020-07-14 10:00","2020-07-17 18:00","취소","취소","연속"]
[38,"전북","직할","신남원S/S 345kV #1 M.Tr 1차 GIS","`20~`21년 전북 직할 변전정비회사 총액공사","[신남원S/S] 345kV #1M.Tr 하자점검 / 1,2차 GIS 하자점검 / TIE GIS보통점검","2020-07-01 09:00","2020-07-03 18:00","취소","취소","연속"]
[39,"전북","직할","신남원S/S 345kV 신남원신광주#1T/L-#1 M.Tr 1차 TIE GIS","`20~`21년 전북 직할 변전정비회사 총액공사","[신남원S/S] 345kV #1M.Tr 하자점검 / 1,2차 GIS 하자점검 / TIE GIS보통점검","2020-07-01 09:00","2020-07-03 18:00","취소","취소","연속"]
[40,"전북","직할","신남원S/S 345kV #75 BUS","신남원S/S GAS 누기보수공사(#75BUS)","신남원S/S GAS 누기보수공사 [휴전개소 : #75BUS] [작업개소] - 7600(04/28~05/21) - 7272(05/02~05/13) - 7352/7452(05/14~05/25) - 7500(06/03~06/14)","2020-07-18 10:00","2020-07-19 18:00","취소","취소","연속"]
[41,"광주전남","광주","신광주S/S 345kV #2 BUS","345kV 신광주S/S 345kV #1Sh.R 증설공사 실부하가압","345kV 신광주S/S 345kV #1Sh.R 증설공사 실부하가압(Angle 측정)","2020-07-27 09:00","2020-07-28 18:00","2020-07-27 09:00","2020-07-28 18:00","연속"]
[42,"광주전남","광주","신광주신화순#2 T/L","345kV 신광주S/S 345kV #1Sh.R 증설공사 무부하가압","345kV 신광주S/S 345kV #1Sh.R 증설공사 내전압시험 및 무부하가압","2020-07-27 09:00","2020-07-28 18:00","2020-07-27 09:00","2020-07-28 18:00","연속"]
[43,"광주전남","광주","신광주신화순#2 T/L","345kV 신광주S/S 345kV #1Sh.R 증설공사 실부하가압","345kV 신광주S/S 345kV #1Sh.R 증설공사 실부하가압(Angle 측정)","2020-07-29 13:00","2020-07-30 18:00","2020-07-29 13:00","2020-07-30 18:00","연속"]
[44,"광주전남","광주","신화순신강진#1 T/L","20년 송전정비총액공사(신화순-신강진#1T/L)","신화순S/S 옥외모선 현수애자 교체","2020-07-06 09:00","2020-07-07 18:00","2020-07-06 09:00","2020-07-07 18:00","연속"]
[45,"광주전남","광주","신화순신강진#2 T/L","20년 송전정비총액공사(신화순-신강진#2T/L)","신화순S/S 옥외모선 현수애자 교체","2020-07-08 09:00","2020-07-09 18:00","2020-07-08 09:00","2020-07-09 18:00","연속"]
[46,"대구","칠곡","북대구S/S 345kV CB 7471","북대구S/S 북대구-서대구#1T/L CB Control Block 교체","부대구S/S 북대구-서대구#1T/L CB Control Block 교체","2020-07-13 09:30","2020-07-15 14:00","2020-07-13 09:30","2020-07-15 14:00","연속"]
[47,"대구","칠곡","북대구S/S 345kV CB 7371","북대구-서대구#2T/L CB Control block 교체","북대구-서대구#2T/L CB Control block 교체","2020-07-20 09:30","2020-07-22 18:00","취소","취소","연속"]
[48,"대구","칠곡","북대구S/S 345kV CB 7400","서대구#1T/L-#2M.Tr 1차TIE CB ControlBlock 교체","부대구S/S 서대구#1T/L-#2 M.Tr 1차 TIE CB Control Block 교체","2020-07-15 14:00","2020-07-17 18:00","2020-07-15 14:00","2020-07-17 18:00","연속"]
[49,"대구","칠곡","북대구S/S 345kV CB 7372","부대구S/S #1 M.Tr CB Control Block 교체","북대구S/S#1 M.Tr CB Control Block 교체작업","2020-07-08 14:00","2020-07-10 18:00","2020-07-08 14:00","2020-07-10 18:00","연속"]
[50,"대구","칠곡","북대구S/S 345kV CB 7300","서대구#2T/L-#1 M.Tr CB ControlBlock 교체","북대구S/S 서대구#2T/L-#1 M.Tr CB Control Block 교체작업","2020-07-01 09:30","2020-07-03 18:00","2020-07-01 09:30","2020-07-03 18:00","연속"]
[51,"대구","칠곡","북대구S/S #2 M.Tr","북대구S/S 4289GIS 무부하가압","북대구S/S 4289GIS 무부하가압","2020-07-03 09:30","2020-07-03 18:00","2020-07-01 09:30","2020-07-03 18:00","연속"]
[52,"대구","칠곡","북대구S/S 345kV CB 7472","북대구S/S #2 M.Tr 1차 GIS Control block 교체","북대구S/S 345kV #2 M.Tr 1차 GIS Control block 교체","2020-07-06 09:30","2020-07-08 14:00","2020-07-06 09:30","2020-07-08 14:00","연속"]
[53,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사(토목)","전력구 관련 H파일 항타 안전이격 확보","2020-07-27 08:00","2020-07-27 18:00","2020-07-27 08:00","2020-07-27 18:00","연속"]
[54,"대구","칠곡","서대구S/S #3 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사(토목)","전력구 관련 H파일 항타 안전이격 확보","2020-07-20 08:00","2020-07-20 18:00","2020-07-20 08:00","2020-07-20 18:00","연속"]
[55,"대구","칠곡","서대구S/S #2 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사(토목)","전력구 관련 H파일 항타 안전이격 확보","2020-07-30 08:00","2020-07-30 18:00","2020-07-30 08:00","2020-07-30 18:00","연속"]
[56,"대구","포항","신포항S/S 345kV CB 7500","신포항S/S 7571,7500CB 조작시험","신포항S/S 7571,7500CB 조작시험","2020-07-09 14:00","2020-07-09 18:00","취소","취소","연속"]
[57,"대구","포항","신포항S/S 345kV CB 7571","신포항S/S 7571, 7500 CB 조작시험","신포항S/S 7571, 7500 CB 조작시험","2020-07-09 09:00","2020-07-09 14:00","취소","취소","연속"]
[58,"대구","포항","월성N/P 345kV CB 7371","월성S/Y 7271 보통점검, 7371 조작시험","월성S/Y 7271 보통점검, 7371 조작시험","2020-07-16 14:00","2020-07-16 18:00","2020-07-16 14:00","2020-07-16 18:00","연속"]
[59,"대구","포항","월성N/P 345kV CB 7271","월성S/Y 7271 보통점검, 7371 조작시험","월성S/Y 7271 보통점검, 7371 조작시험","2020-07-16 09:30","2020-07-16 14:00","취소","취소","연속"]
[60,"경북","구미","선산S/S 345kV CB 7000","Control Block 교체","제작사 입회 하 Control Block 교체","2020-07-21 09:00","2020-07-21 18:00","2020-07-21 09:00","2020-07-21 18:00","연속"]
[61,"경북","직할","청송P/P 345kV #2 BUS","청송양수S/Y 345kV #1,2 모선보호반 교체공사","345kV #1,2 모선보호반 교체","2020-07-08 14:00","2020-07-10 18:00","2020-07-08 14:00","2020-07-10 18:00","연속"]
[62,"경북","직할","청송P/P 345kV #1 BUS","청송양수S/Y 345kV #1,2 모선보호반 교체공사","345kV #1,2 모선보호반 교체","2020-07-06 09:00","2020-07-08 13:00","2020-07-06 09:00","2020-07-08 13:00","연속"]
[63,"부산울산","동부산","신양산S/S 345kV #2 BUS","[12차] 345kV 신양산S/S 현대화공사","신양산S/S 345kV 75BUS 모선보호반 대체","2020-07-02 09:00","2020-07-04 18:00","취소","취소","연속"]
[64,"부산울산","북부산","신김해북부산#1 T/L","345kV 북부산-울산TP 등 4개 T/L 전선접속개소 전선교체공사","신김해-북부산 #1T/L : 4~8, 8~9. 9~10","2020-07-11 07:00","2020-07-16 18:00","2020-06-27 17:00","2020-06-27 18:00","연속"]
[65,"부산울산","울산","신온산S/S #3 M.Tr","20-21년 변전정비회사 총액공사","AC,DC PNL 대체 관련 안전이격(매일)","2020-07-01 09:00","2020-07-02 18:00","2020-07-01 09:00","2020-07-02 18:00","매일"]
[66,"부산울산","울산","북부산신온산 T/L","345kV 신울산복합-북부산T/L 건설공사","-작업내용 : 154kV 신온산-성암T/L #1 신설 병가선로 구성 및 345kV 북부산-신온산T/L 임시선로 구성 - 154kV 신온산-성암 #1 : 3일 전선 공중이동, 9일 안전이격(345 가선작업) - 345kV 북부산-신온산T/L : 전선 공중이동","2020-07-22 09:00","2020-08-02 18:00","2020-07-22 09:00","2020-08-02 18:00","연속"]
[67,"부산울산","울산","신울산S/S 345kV CB 7372","20-21년 변전정비회사 총액공사","7352 B상 DS 불량관련 교체 및 7372 GCB 보통점검 - #75BUS PT 보통점검","2020-07-06 09:00","2020-07-07 18:00","2020-07-06 09:00","2020-07-07 18:00","연속"]
[68,"부산울산","울산","신울산S/S 345kV #75 BUS","20-21년 변전정비회사 총액공사","7352 B상 DS 불량관련 교체 및 7371 GCB 보통점검 - #75BUS PT 보통점검","2020-07-01 09:00","2020-07-02 18:00","2020-07-01 09:00","2020-07-02 18:00","연속"]
[69,"대구",null,"월성N/P #4호기 주변압기 CB","월성4호기 17차 O/H 중 주변압기 점검\n * 조작차단기 : CB 7700, 7772","○ 주변압기 점검","2020-07-22 11:00","2020-08-07 19:00","2020-07-22 11:00","2020-08-07 19:00","연속"]
[70,"광주전남",null,"한빛N/P #5호기 주변압기 CB","5호기 13차 계획예방정비\n- 조작차단기 : PCB 7D00, 7D71","○ 소내전원절체시험 수행\n○ 대기보조변압기 실부하 위상각 측정","2020-07-28 09:00","2020-07-28 18:00","2020-07-28 09:00","2020-07-28 18:00","연속"]
[71,"경북",null,"한울N/P #1호기 주변압기 CB","1호기 23차 계획예방정비\n* 조작차단기 : CB 7100, 7172","○ 주/소내보조/여자변압기 일반점검 ","2020-07-30 15:00","2020-08-27 15:00","2020-07-30 15:00","2020-08-27 15:00","연속"]
[72,"전북",null,"신남원S/S #1 M.Tr","`20~`21년 전북 직할 변전정비회사 총액공사","[신남원S/S] 345kV #1M.Tr 하자점검 / 1,2차 GIS 하자점검 / TIE GIS보통점검","2020-07-01 09:00","2020-07-03 18:00","2020-07-06 09:00","2020-07-10 18:00","연속"]
[73,"부산울산",null,"부산복합1,2GT용 주변압기(7400,7471)","계획예방정비 공사","계획예방정비 공사","2020-07-27 09:00","2020-09-29 18:00","2020-07-27 09:00","2020-09-29 18:00","연속"]

{"sheet":"154송부","index":2,"n_rows":129,"n_cols":13,"rows_kept":129,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
["2020년도 7월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","광장뚝도#2 T/L","2020년 성동P/O 변전정비회사 총액공사","2020년 성동P/O 변전정비회사 총액공사","2020-07-03 13:00","2020-07-03 18:00","취소","취소","연속"]
[2,"서울","성동","광장뚝도#1 T/L","2020년 성동P/O 변전정비회사 총액공사","2020년 성동P/O 변전정비회사 총액공사","2020-07-03 09:00","2020-07-03 13:30","취소","취소","연속"]
[3,"서울","성동","천호구의#1 T/L","2020년 성동P/O 변전정비회사 총액공사","2020년 성동P/O 변전정비회사 총액공사 -장기미동작 조작시험","2020-07-02 09:30","2020-07-02 18:00","취소","취소","연속"]
[4,"서울","성동","안암노원#2 T/L","장위재개발4구역 전력구 지장전력설비 이설공사","○ 154kV 노원종암T/L M/H#7~10 구간 임시이설(20년) 및 본이설(21년) ○ 154kV 안암노원#1,2T/L M/H#7~10 구간 임시이설(20년) 및 본이설(21년)","2020-07-01 09:00","2020-07-27 18:00","취소","취소","연속"]
[5,"서울","성동","안암노원#1 T/L","장위재개발4구역 전력구 지장전력설비 이설공사","○ 154kV 노원종암T/L M/H#7~10 구간 임시이설(20년) 및 본이설(21년) ○ 154kV 안암노원#1,2T/L M/H#7~10 구간 임시이설(20년) 및 본이설(21년)","2020-07-01 09:00","2020-07-27 18:00","2020-07-04 09:00","2020-07-17 18:00","연속"]
[6,"남서울","강남","대치논현#2 T/L","154㎸ 신양재-개포 등 7개T/L 병행지선 설치공사","154㎸ 신양재-개포 등 7개T/L 병행지선 설치공사","2020-07-01 09:00","2020-07-01 18:00","취소","취소","연속"]
[7,"남서울","강남","강남대치#1 T/L","154㎸ 신양재-개포 등 7개T/L 병행지선 설치공사","154㎸ 신양재-개포 등 7개T/L 병행지선 설치공사","2020-07-02 09:00","2020-07-02 18:00","취소","취소","연속"]
[8,"남서울","강남","강남대치#2 T/L","154㎸ 신양재-개포 등 7개T/L 병행지선 설치공사","154㎸ 신양재-개포 등 7개T/L 병행지선 설치공사","2020-07-03 09:00","2020-07-03 18:00","취소","취소","연속"]
[9,"남서울","동서울","논현선릉#1 T/L","170kV GIS 보통점검 및 세니온 보호배전반 성능개선","170kV GIS 보통점검 및 전자변교체 보호배전반 성능개선","2020-07-07 09:00","2020-07-07 14:00","2020-07-07 09:00","2020-07-07 14:00","연속"]
[10,"남서울","동서울","논현선릉#2 T/L","170kV GIS 보통점검및 세니온 보호배전반 성능개선","170kV GIS 보통점검 및 전자변 교체 보호배전반 성능개선","2020-07-07 14:00","2020-07-07 18:00","2020-07-07 14:00","2020-07-07 18:00","연속"]
[11,"남서울","영등포","구공S/S 154kV #65 BUS","154kV 신광명-가산SS SW 증설공사","154kV 신광명-가산SS SW 증설공사","2020-07-06 09:00","2020-07-10 15:30","2020-06-29 09:00","2020-07-02 15:30","연속"]
[12,"남서울","영등포","영등포구로#1 T/L","구로S/S 170kV 조작시험(영등포-구로#1,2)","- 차단기 동작특성 시험 - GIS 조작시험","2020-07-01 09:00","2020-07-01 14:00","취소","취소","연속"]
[13,"남서울","영등포","영등포구로#2 T/L","구로S/S 170kV GIS 조작시험(영등포-구로#1,2)","- 차단기 동작특성 시험 - GIS 조작시험","2020-07-01 14:00","2020-07-01 18:00","취소","취소","연속"]
[14,"인천","김포","신김포장기#1 T/L","신김포S/S #64M.Tr 증설공사 관련 170kV GIS 설치공사","신김포S/S #64M.Tr 증설공사 관련 170kV GIS 설치공사 - #64M.Tr 1차 GIS 무부하가압용","2020-07-02 09:00","2020-07-03 18:00","2020-07-02 09:00","2020-07-03 18:00","연속"]
[15,"인천","부평","남인천S/S 154kV #2 BUS","남인천S/S #3M.Tr 1차 GIS 모선 #2DS 정밀점검 공사용","남인천S/S #3M.Tr 1차 GIS 모선 #2DS 정밀점검 공사용","2020-07-01 10:00","2020-07-02 10:00","2020-07-01 10:00","2020-07-02 10:00","연속"]
[16,"인천","부평","남인천S/S 154kV #1 BUS","남인천S/S #3M.Tr 1차 GIS 정밀점검 후 무부하 가압 확인용","남인천S/S #3M.Tr 1차 GIS 정밀점검 후 무부하 가압 확인용","2020-07-03 13:00","2020-07-03 15:00","2020-07-03 13:00","2020-07-03 15:00","연속"]
[17,"인천","부평","남인천S/S 154kV #2 BUS","남인천S/S #3M.Tr 1차 GIS 정밀점검 후 무부하 가압 확인용","남인천S/S #3M.Tr 1차 GIS 정밀점검 후 무부하 가압 확인용","2020-07-03 15:00","2020-07-03 18:00","2020-07-03 15:00","2020-07-03 18:00","연속"]
[18,"경기북부","구리","미금S/S 154kV CB 6300","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 154kV 6300 Bus-Tie GIS 감시제어계측 포인트이관 (→SA) - 154kV 6300 Bus-Tie GIS LCP 및 모자익반 제어케이블 철거 및 재결선","2020-07-27 09:00","2020-07-31 18:00","2020-07-06 09:00","2020-07-10 18:00","연속"]
[19,"경기북부","구리","미금S/S 154kV SEC CB 61620","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 154kV #61-62-0 Bus-Sec GIS 감시제어계측 포인트이관 (→SA) - 154kV #61-62-0 Bus-Sec GIS LCP 및 모자익반 제어케이블 철거 및 재결선","2020-07-27 09:00","2020-07-31 18:00","2020-07-06 09:00","2020-07-10 18:00","연속"]
[20,"경기북부","구리","미금S/S 154kV #5 Sh.C CB","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 154kV #5 SC용 GIS 감시제어계측 포인트이관 (→SA) - 154kV #5 SC용 GIS LCP 및 모자익반 제어케이블 철거 및 재결선","2020-07-27 09:00","2020-07-31 18:00","취소","취소","연속"]
[21,"경기북부","구리","미금S/S 154kV #3 Sh.C CB","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 154kV #3 SC용 GIS 감시제어계측 포인트이관 (→SA) - 154kV #3 SC용 GIS LCP 및 모자익반 제어케이블 철거 및 재결선","2020-07-20 09:00","2020-07-24 18:00","취소","취소","연속"]
[22,"경기북부","구리","미금S/S 154kV #1 Sh.C CB","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 154kV #1 SC용 GIS 감시제어계측 포인트이관 (→SA) - 154kV #1 SC용 GIS LCP 및 모자익반 제어케이블 철거 및 재결선","2020-07-20 09:00","2020-07-24 18:00","취소","취소","연속"]
[23,"경기북부","구리","미금S/S 154kV #2 Sh.C CB","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 154kV #2 SC용 GIS 감시제어계측 포인트이관 (→SA) - 154kV #2 SC용 GIS LCP 및 모자익반 제어케이블 철거 및 재결선","2020-07-20 09:00","2020-07-24 18:00","취소","취소","연속"]
[24,"경기북부","구리","미금S/S 154kV #6 Sh.C CB","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 154kV #6 SC용 GIS 감시제어계측 포인트이관 (→SA) - 154kV #6 SC용 GIS LCP 및 모자익반 제어케이블 철거 및 재결선","2020-07-27 09:00","2020-07-31 18:00","취소","취소","연속"]
[25,"경기북부","구리","미금S/S 154kV #4 Sh.C CB","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 154kV #4 SC용 GIS 감시제어계측 포인트이관 (→SA) - 154kV #4 SC용 GIS LCP 및 모자익반 제어케이블 철거 및 재결선","2020-07-27 09:00","2020-07-31 18:00","취소","취소","연속"]
[26,"경기북부","구리","미금S/S 154kV SEC CB 66670","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 154kV #66-67-0 Bus-Sec GIS 감시제어계측 포인트이관 (→SA) - 154kV #66-67-0 Bus-Sec GIS LCP 및 모자익반 제어케이블 철거 및 재결선","2020-07-27 09:00","2020-07-31 18:00","2020-07-06 09:00","2020-07-10 18:00","연속"]
[27,"경기북부","구리","서홍천청평PP T/L","345kV 신가평-포천LNGCC T/L 항공장애시설물 정비공사(병가구간)","ㅇ 항공장애표시구 설치 - No.1~2호 등 48경간 - 병가구간(하단선로 : 서홍천-청평PP) 휴전","2020-07-02 07:00","2020-07-02 18:00","2020-07-02 07:00","2020-07-02 18:00","연속"]
[28,"경기북부","직할","신의정부S/S 154kV #65 BUS","신의정부S/S 하자보수공사","신의정부S/S #2 M.Tr 2차 GIS DS 발청보수","2020-07-02 09:00","2020-07-03 18:00","2020-07-02 09:00","2020-07-03 18:00","연속"]
[29,"경기북부","직할","운천전곡#1 T/L","전곡S/S 운천-전곡 #1 T/L 노즐 교체공사","전곡S/S 운천-전곡 #1 T/L 노즐 교체공사","2020-07-01 08:00","2020-07-03 18:00","취소","취소","연속"]
[30,"경기북부","직할","운천전곡#2 T/L","전곡S/S 운천-전곡T/L 노즐, 접촉자 교체공사","□ 전곡S/S 운천-전곡 #2T/L 노즐, 접촉자 교체 및 시험","2020-07-07 08:00","2020-07-09 18:00","2020-07-02 08:00","2020-07-04 18:00","연속"]
[31,"경기","군포","서서울#2일동#2 T/L"," 154kV 북안산분기T/L OPGW시설공사","가. 공사장소 : 일동S/S~북안산S/S~원곡S/S 나. 시설내역 - OPGW 100㎟ 48C 14.534㎞ 시설 - 비금속광케이블(FOFC) 48C 0.468㎞ 시설","2020-07-01 07:00","2020-07-07 18:00","2020-07-01 07:00","2020-07-07 18:00","연속"]
[32,"경기","군포","안양평촌#1 T/L"," 안양S/S 안양-평촌#1T/L GIS 조작시험"," 안양S/S 안양-평촌#1T/L GIS 조작시험","2020-07-02 09:00","2020-07-02 14:00","2020-07-02 09:00","2020-07-02 14:00","연속"]
[33,"경기","군포","안양평촌#2 T/L"," 안양S/S 안양-평촌#2T/L GIS 조작시험"," 안양S/S 안양-평촌#2T/L GIS 조작시험","2020-07-02 14:00","2020-07-02 18:00","2020-07-02 14:00","2020-07-02 18:00","연속"]
[34,"경기","동부","곤지암율현#1 T/L"," 154kV 곤지암-율현#1T/L 불량애자교체","불량애자 교체작업(6호)","2020-07-04 08:00","2020-07-04 11:00","2020-07-04 08:00","2020-07-04 11:00","연속"]
[35,"경기","동부","곤지암이천#1 T/L"," 154kV 곤지암-율현#1T/L 불량애자교체(안전상 휴전)","불량애자 교체작업(6호)(안전상 휴전)","2020-07-04 08:00","2020-07-04 11:00","2020-07-04 08:00","2020-07-04 11:00","연속"]
[36,"경기","동부","곤지암이천#1 T/L"," 20년 동부 변전정비회사 총액공사","곤지암:곤지암-이천#1T/L(보통) LA(보통), 이천:곤지암-이천#1T/L(보통), 43L/R 회로보완 확인 및 Remote 회로분리 시행, LA(초기)-유압탱크 측면 볼트측 누유흔적제거 요망","2020-07-09 09:30","2020-07-09 18:00","취소","취소","연속"]
[37,"경기","동부","곤지암율현#2 T/L"," 154kV 곤지암-율현#2T/L 불량애자교체 및 피뢰기 설치","불량애자 교체작업(6호) 피뢰기 설치작업(1~5호)","2020-07-04 11:00","2020-07-04 19:00","2020-07-04 11:00","2020-07-04 19:00","연속"]
[38,"경기","동부","곤지암이천#2 T/L"," 154kV 곤지암-율현#2T/L 불량애자교체,피뢰기 설치(안전상 휴전)","불량애자 교체작업(6호)(안전상 휴전) 피뢰기 설치작업(1~5호)(안전상 휴전)","2020-07-04 11:00","2020-07-04 19:00","2020-07-04 11:00","2020-07-04 19:00","연속"]
[39,"경기","동부","곤지암율현#2 T/L"," 154kV 곤지암-율현#2T/L 피뢰기 설치","피뢰기 설치작업(1~5호)","2020-07-05 08:00","2020-07-05 12:00","2020-07-05 08:00","2020-07-05 12:00","연속"]
[40,"경기","동부","곤지암이천#2 T/L"," 154kV 곤지암-율현#2T/L 피뢰기 설치(안전상 휴전)","피뢰기 설치작업(1~5호)(안전상 휴전)","2020-07-05 08:00","2020-07-05 12:00","2020-07-05 08:00","2020-07-05 12:00","연속"]
[41,"경기","동부","곤지암이천#2 T/L"," 154kV 곤지암-이천#2T/L 피뢰기 설치","피뢰기 설치작업(1~5호)","2020-07-05 12:00","2020-07-05 19:00","2020-07-05 12:00","2020-07-05 19:00","연속"]
[42,"경기","동부","곤지암율현#2 T/L"," 154kV 곤지암-이천#2T/L 피뢰기 설치(안전상 휴전)","피뢰기 설치작업(1~5호)(안전상 휴전)","2020-07-05 12:00","2020-07-05 19:00","2020-07-05 12:00","2020-07-05 19:00","연속"]
[43,"경기","동부","오천용인#2 T/L"," 154kV 오천S/S #1M.Tr 증설공사","#1M.Tr 증설공사","2020-07-06 09:00","2020-07-10 18:00","취소","취소","연속"]
[44,"경기","성남","신성남정자#1 T/L"," 20년 성남전력 변전정비회사 총액공사","- 보통점검 및 전자변교체 - 세니온ied 성능개선 - 6J9-3 원격투개방불량조치","2020-07-07 09:00","2020-07-07 18:00","2020-07-07 09:00","2020-07-07 18:00","연속"]
[45,"경기","성남","신성남정자#2 T/L"," 20년 성남전력 변전정비회사 총액공사","- 보통점검 및 전자변교체 - 6DS원격 투입불가 조치","2020-07-08 09:00","2020-07-08 18:00","2020-07-08 09:00","2020-07-08 18:00","연속"]
[46,"경기","직할","발안향남#1 T/L"," 향남S/S 옥상 방수 공사 (이격거리확보)","향남S/S 옥상 방수 공사 (이격거리확보)","2020-07-01 09:00","2020-07-12 18:00","2020-06-25 09:00","2020-07-04 18:00","매일"]
[47,"경기","직할","발안향남#2 T/L"," 향남S/S 옥상 방수 공사 (이격거리확보)","향남S/S 옥상 방수 공사 (이격거리확보)","2020-07-01 09:00","2020-07-12 18:00","2020-06-25 09:00","2020-07-04 18:00","매일"]
[48,"경기","직할","율전의왕#1 T/L"," 20년 직할 변전정비회사 총액공사","율전S/S 율전-의왕#1T/L GIS 전자변 교체","2020-07-03 09:00","2020-07-03 14:00","2020-07-03 09:00","2020-07-03 14:00","연속"]
[49,"경기","직할","율전의왕#2 T/L"," 20년 직할 변전정비회사 총액공사","율전S/S 율전-의왕#2T/L GIS 전자변 교체","2020-07-03 14:00","2020-07-03 18:00","2020-07-03 14:00","2020-07-03 18:00","연속"]
[50,"경기","평택","송탄오성CC#2 T/L"," 20-21 송전정비회사총액공사(피뢰기설치)_안전이격확보","20-21 송전정비회사총액공사(피뢰기설치)_안전이격확보","2020-07-09 08:00","2020-07-09 11:00","취소","취소","연속"]
[51,"경기","평택","원정만호#2 T/L"," 20-21 송전정비회사총액공사(피뢰기설치)","20-21 송전정비회사총액공사(피뢰기설치)","2020-07-01 07:00","2020-07-02 18:00","2020-07-01 07:00","2020-07-02 18:00","연속"]
[52,"경기","평택","진위동탄#1 T/L","  진위S/S 154kV #60-#65 BUS TIE GIS 무부하가압","진위S/S 154kV #60-#65 BUS TIE GIS 정밀점검공사 무부하가압","2020-07-03 09:00","2020-07-03 18:00","2020-07-03 09:00","2020-07-03 18:00","연속"]
[53,"경기","평택","진위동탄#1 T/L"," 진위S/S 154kV #60-#65 BUS TIE GIS 무부하가압","진위S/S 154kV #60-#65 BUS TIE GIS 정밀점검공사 무부하가압","2020-07-06 16:00","2020-07-07 10:00","2020-07-06 16:00","2020-07-07 10:00","연속"]
[54,"경기","평택","진위동탄#2 T/L"," 진위S/S 154kV #4M.Tr 증설 관련 최초가압 및 무부하가압","진위S/S 154kV #4M.Tr 증설 관련 최초가압 및 무부하가압","2020-07-27 09:00","2020-07-28 18:00","2020-07-27 09:00","2020-07-28 18:00","연속"]
[55,"경기","평택","청북평택#1 T/L"," 20-21 송전정비회사총액공사(피뢰기설치)","20-21 송전정비회사총액공사(피뢰기설치)","2020-07-03 07:00","2020-07-05 19:00","2020-07-03 07:00","2020-07-05 19:00","연속"]
[56,"경기","평택","둔포추팔#2 T/L"," 20-21 송전정비회사총액공사(피뢰기설치)","20-21 송전정비회사총액공사(피뢰기설치)","2020-07-06 08:00","2020-07-08 19:00","취소","취소","연속"]
[57,"경기","평택","둔포추팔#1 T/L"," 20-21 송전정비회사총액공사(피뢰기설치) _안전이격확보","둔포-추팔 #2 T/L 안전이격확보차 휴전신청","2020-07-06 08:00","2020-07-06 11:00","취소","취소","연속"]
[58,"경기","평택","오산평택#2 T/L"," 평택전력지사 170kV GCB 정밀점검","평택S/S 154kV 오산-평택#2T/L GCB 정밀점검 / 오산S/S 154kV 오산-평택#2T/L GIS 보통점검","2020-07-06 09:00","2020-07-08 18:00","취소","취소","연속"]
[59,"경기","평택","평택추팔#1 T/L"," 20-21 송전정비회사총액공사(피뢰기설치)","20-21 송전정비회사총액공사(피뢰기설치)","2020-07-09 08:00","2020-07-12 19:00","2020-07-09 08:00","2020-07-12 19:00","연속"]
[60,"경기","평택","포승청북 T/L"," 20-21 송전정비회사총액공사(피뢰기설치) _안전이격확보","청북-평택#1T/L 안전이격확보차","2020-07-04 07:00","2020-07-04 19:00","2020-07-04 07:00","2020-07-04 19:00","연속"]
[61,"강원","원주","원주서원주#2 T/L","세니온제 보호배전반 성능개선 및 보호배전반 초기점검","- 보호계전기 성능개선 시행 - 보호배전반 초기점검","2020-07-21 10:00","2020-07-21 18:00","취소","취소","연속"]
[62,"강원","원주","원주서원주#1 T/L","154kV 원주S/S 디지털화 공사","154kV 원주-서원주#1T/L 인출변경","2020-07-17 08:00","2020-07-20 18:00","취소","취소","연속"]
[63,"강원","원주","남원주원주#2 T/L","154kV 원주S/S 디지털화 공사","154kV 원주-남원주#2T/L 인출변경","2020-07-17 08:00","2020-07-20 18:00","취소","취소","연속"]
[64,"강원","원주","남원주원주#1 T/L","154kV 원주S/S 디지털화 공사","154kV 원주-남원주#1T/L 인출변경","2020-07-14 08:00","2020-07-16 18:00","취소","취소","연속"]
[65,"강원","원주","횡성홍천#1 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","ㅇ 횡성홍천#2T/L 월부싱 설치 안전이격확보","2020-07-15 09:00","2020-07-15 18:00","취소","취소","연속"]
[66,"강원","원주","횡성홍천#2 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","ㅇ 170kV 장기사용 GIS 철거/설치 ㅇ 디지털화공사 케이블 철거 및 광케이블 포설 ㅇ SA 운영장치 시험","2020-07-06 09:00","2020-07-24 18:00","취소","취소","연속"]
[67,"강원","원주","횡성홍천#1 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","ㅇ 170kV 장기사용 GIS 철거/설치 ㅇ 안전이격확보","2020-07-08 09:00","2020-07-08 18:00","취소","취소","연속"]
[68,"강원","직할","남춘천춘천 T/L","2020년 직할 154kV GIS 정밀점검공사","ㅇ직할 남춘천변전소 5Bay GIS 정밀점검 시행 ㅇ공압식 GIS 전자변 교체 병행 시행","2020-07-06 09:00","2020-07-08 18:00","취소","취소","연속"]
[69,"강원","직할","남춘천춘천열병합#2 T/L","2020년 직할 154kV GIS 정밀점검공사","ㅇ직할 남춘천변전소 5Bay GIS 정밀점검 시행 ㅇ공압식 GIS 전자변 교체 병행 시행","2020-07-01 09:00","2020-07-03 18:00","2020-07-01 09:00","2020-07-03 18:00","연속"]
[70,"강원","태백","영월C/C 154kV CB 6100G","20-21 태백전력지사 변전정비회사 총액공사","영월C/C 154kV BUS-TIE GIS 조작시험","2020-07-01 10:00","2020-07-01 18:00","2020-07-01 10:00","2020-07-01 18:00","연속"]
[71,"충북","청주","북청주봉명#2 T/L","봉명S/S 23kV 장기사용 개폐장치 대체공사","북청주-봉명#2T/L 제어감시 케이블 이설 (RTU → SA시스템 현장정보처리반)","2020-07-10 09:00","2020-07-10 18:00","2020-07-10 09:00","2020-07-10 18:00","연속"]
[72,"충북","청주","국사봉명#1 T/L","봉명S/S 23kV 장기사용 개폐장치 대체공사","국사-봉명#1T/L 제어감시 케이블 이설 (RTU → SA시스템 현장정보처리반)","2020-07-08 09:00","2020-07-08 18:00","2020-07-08 09:00","2020-07-08 18:00","연속"]
[73,"충북","청주","국사봉명#2 T/L","봉명S/S 23kV 장기사용 개폐장치 대체공사","국사-봉명#2T/L 제어감시 케이블 이설 (RTU → SA시스템 현장정보처리반)","2020-07-09 09:00","2020-07-09 18:00","2020-07-09 09:00","2020-07-09 18:00","연속"]
[74,"충북","충주","단양영월CC#1 T/L","단양S/S 154kV GIS 장기사용 대체공사(단양전철#2T/L)","기설 GIS(단양전철#2T/L) 철거 x 1CCT 신규 GIS(단양전철#2T/L) 설치 x 1CCT ※ 단양전철#2T/L 무부하가압 전원","2020-07-01 10:00","2020-07-02 10:00","2020-07-01 10:00","2020-07-02 10:00","연속"]
[75,"충북","충주","음성괴산 T/L","154kV 풍동-음성T/L 지장철탑 이설공사","○ 공사구간 : 154kV 풍동-음성 No.73~76 (4회선 구간) ○ 공사개요 : 4회선 철탑신설 2기, 철거 2기, 전선교체 3.6C-km","2020-07-03 07:00","2020-07-10 18:00","2020-07-03 07:00","2020-07-10 18:00","연속"]
[76,"충북","충주","풍동음성#1 T/L","154kV 풍동-음성T/L 지장철탑 이설공사","○ 공사구간 : 154kV 풍동-음성 No.73~76 (4회선 구간) ○ 공사개요 : 4회선 철탑신설 2기, 철거 2기, 전선교체 3.6C-km","2020-07-05 07:00","2020-07-10 18:00","2020-07-05 07:00","2020-07-10 18:00","연속"]
[77,"대전충남","서산","당진T/P 154kV #2 BUS","당진화력S/Y 154kV 장기사용 GIS 교체공사","당진화력S/Y 154kV 장기사용 GIS 교체공사","2020-07-06 09:00","2020-07-09 18:00","2020-07-06 09:00","2020-07-09 18:00","연속"]
[78,"대전충남","아산","인주탕정#1 T/L","154kV 인주-불당T/L C/H 건설사업","154kV 인주-불당T/L C/H 건설공사 - C/H 접속을 위한 병가철탑 상하단 교체공사 시행","2020-07-21 07:00","2020-07-27 18:00","2020-07-04 07:00","2020-07-07 18:00","연속"]
[79,"대전충남","아산","서천안탕정#2 T/L","154kV 인주-불당T/L C/H 건설사업","154kV 인주-불당T/L C/H 건설공사 - C/H 접속을 위한 병가철탑 상하단 교체공사 시행","2020-07-21 07:00","2020-07-27 18:00","2020-07-04 07:00","2020-07-07 18:00","연속"]
[80,"대전충남","아산","인주탕정#2 T/L","154kV 인주-불당T/L C/H 건설사업","154kV 인주-불당T/L C/H 건설공사 - C/H 접속을 위한 병가철탑 상하단 교체공사 시행","2020-07-14 07:00","2020-07-20 18:00","취소","취소","연속"]
[81,"전북","군산","군산이리#2 T/L","154kV 군산-이리T/L 안전이격확보공사","18,19호 가철탑 조립 및 공중이동","2020-07-06 07:00","2020-07-09 18:00","취소","취소","연속"]
[82,"전북","군산","군산이리#1 T/L","154kV 군산-이리T/L 안전이격확보공사","18,19호 가철탑 조립 및 공중이동","2020-07-01 07:00","2020-07-05 18:00","취소","취소","연속"]
[83,"전북","군산","동군산장항#2 T/L","동군산장항T/L 추락방지설비 시설공사","-추락방지설비 설치 : 23,24호","2020-07-09 13:00","2020-07-09 18:00","2020-07-09 13:00","2020-07-09 18:00","연속"]
[84,"전북","군산","동군산장항#1 T/L","동군산장항T/L 추락방지설비 시설공사","-추락방지설비 설치 : 23,24호","2020-07-08 13:00","2020-07-08 18:00","2020-07-08 13:00","2020-07-08 18:00","연속"]
[85,"전북","군산","새만금소룡#2 T/L","군산P/O 차단기 조작시험","군산P/O 차단기 조작시험 가스 시각화","2020-07-02 09:00","2020-07-02 18:00","2020-07-02 09:00","2020-07-02 18:00","연속"]
[86,"전북","군산","새만금소룡#1 T/L","군산P/O 차단기 조작시험","군산P/O 차단기 조작시험 가스 시각화","2020-07-01 09:00","2020-07-01 18:00","2020-07-01 09:00","2020-07-01 18:00","연속"]
[87,"전북","군산","영등팔봉#2 T/L","군산P/O 장기사용 LA 교체공사","- 영등-팔봉#2T/L A, B, C상 LA교체","2020-07-07 09:00","2020-07-09 18:00","취소","취소","연속"]
[88,"전북","직할","무주진안 T/L","무주변전소 외벽보수 및 기타공사","무주변전소 외벽보수 및 기타공사","2020-07-06 08:00","2020-07-10 17:00","2020-07-01 08:00","2020-07-10 17:00","매일"]
[89,"광주전남","강진","나주엄다#2 T/L","20-21년 강진전력지사 변전정비회사 총액공사","154kV 나주-엄다 #1,2T/L GIS 초기점검","2020-07-23 14:00","2020-07-23 18:00","2020-07-03 14:00","2020-07-03 18:00","연속"]
[90,"광주전남","강진","나주엄다#1 T/L","20-21년 강진전력지사 변전정비회사 총액공사","154kV 나주-엄다 #1,2T/L GIS 초기점검","2020-07-23 10:00","2020-07-23 14:00","2020-07-03 10:00","2020-07-03 14:00","연속"]
[91,"광주전남","직할","남광주금천#1 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치","2020-07-06 08:00","2020-07-07 18:00","2020-06-29 08:00","2020-06-30 18:00","매일"]
[92,"광주전남","직할","나주금천#1 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치","2020-07-06 08:00","2020-07-06 18:00","2020-06-29 08:00","2020-06-29 18:00","연속"]
[93,"광주전남","직할","나주금천#2 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치","2020-07-01 08:00","2020-07-01 18:00","2020-07-01 08:00","2020-07-01 18:00","연속"]
[94,"광주전남","직할","남광주금천#2 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치","2020-07-01 08:00","2020-07-02 18:00","2020-07-01 08:00","2020-07-02 18:00","매일"]
[95,"대구","경산","하양반야월#2 T/L","154kV 신서분기 지중T/L 건설공사","신서E/C~154kV 하양-반야월T/L 분기맨홀(2파이 분기) 154kV XLPE1200*2C(D) 0.5km, 154kV XLPE2500*2C 0.5km","2020-07-14 09:30","2020-08-04 18:00","2020-07-14 09:30","2020-08-04 18:00","연속"]
[96,"대구","직할","검단산격#1 T/L","변전소 인출구간 OF 선종교체 공사","OF 선종교체 공사","2020-07-13 09:00","2020-08-07 18:00","2020-07-13 09:00","2020-08-07 18:00","연속"]
[97,"경북","구미","점촌동상주개폐소#2 T/L","154kV 동상주-점촌T/L No.7-9 임시선로 점검","- 154kV 동상주-점촌T/L 지장이설공사 관련 임시선로 장기운영으로 인한 점검(No.7-9)","2020-07-04 13:00","2020-07-04 16:00","2020-07-04 13:00","2020-07-04 16:00","연속"]
[98,"경북","구미","점촌동상주개폐소#1 T/L","154kV 동상주-점촌T/L No.7-9 임시선로 점검","- 154kV 동상주-점촌T/L 지장이설공사 관련 임시선로 장기운영으로 인한 점검(No.7-9)","2020-07-04 09:00","2020-07-04 12:00","2020-07-04 09:00","2020-07-04 12:00","연속"]
[99,"경북","구미","상주S/S 154kV CB 6100","2020-21년 구미전력지사 변전정비업체 총액공사","- 154kV 모선보호반 대체공사","2020-07-06 09:00","2020-07-09 18:30","2020-07-06 09:00","2020-07-09 18:30","연속"]
[100,"경북","직할","진보S/S 154kV GS영양풍력#2T/L GIS","20~21년 경북본부 직할 변전정비회사 총액공사","진보S/S GS영양풍력#2 T/L GIS 하자점검 및 고객측 송전선로 스페이서 설치 작업","2020-07-15 09:00","2020-07-17 18:00","2020-07-15 09:00","2020-07-17 18:00","연속"]
[101,"경북","직할","현종산풍력평해#1 T/L","154kV 평해S/S 옥외철구설비 현대화 공사","○현종산풍력-평해#1T/L 휴전 - 인출모선 조정, 보호반 이설, 전력선 교체, 준공시험","2020-07-06 09:00","2020-07-09 18:00","2020-07-06 09:00","2020-07-09 18:00","연속"]
[102,"부산울산","북부산","서창산막#1 T/L","154kV 서창-산막T/L 52~64호 지중화","가선로구성작업(연긴선)","2020-07-04 07:00","2020-07-05 18:00","2020-07-04 07:00","2020-07-05 18:00","연속"]
[103,"부산울산","북부산","주촌삼계#1 T/L","20-21 북부산전력지사 변전 총액공사","삼계S/S 154kV 주촌-삼계#1T/L 차단기 동작시험","2020-07-09 10:00","2020-07-09 14:00","2020-07-09 10:00","2020-07-09 14:00","연속"]
[104,"부산울산","북부산","주촌삼계#2 T/L","20-21 북부산전력지사 변전 총액공사","삼계S/S 154kV 주촌-삼계#2T/L 차단기 동작시험","2020-07-09 14:00","2020-07-09 18:00","2020-07-09 14:00","2020-07-09 18:00","연속"]
[105,"부산울산","북부산","주촌삼계#1 T/L","2020 북부산전력지사 154kV GIS 정밀점검","삼계S/S 154kV BUS-TIE(6100) GIS 정밀점검 (차단기 시험가압 - 시험가압선로 : 주촌-삼계#1T/L)","2020-07-05 17:00","2020-07-05 18:00","2020-07-05 17:00","2020-07-05 18:00","연속"]
[106,"부산울산","북부산","삼계S/S 154kV #65 BUS","2020 북부산전력지사 154kV GIS 정밀점검","삼계S/S 154kV BUS-TIE(6100) GIS 정밀점검 (#2BUS 휴전)","2020-07-04 09:00","2020-07-05 18:00","2020-07-04 09:00","2020-07-05 18:00","연속"]
[107,"부산울산","북부산","주촌삼계#1 T/L","2020 북부산전력지사 154kV GIS 정밀점검","삼계S/S #3M.Tr 1차 6333GIS 정밀점검 (차단기 시험가압 - 시험가압선로 : 주촌-삼계#1T/L)","2020-07-03 17:00","2020-07-03 18:00","2020-07-03 17:00","2020-07-03 18:00","연속"]
[108,"부산울산","북부산","삼계S/S 154kV #65 BUS","2020 북부산전력지사 154kV GIS 정밀점검","삼계S/S #3M.Tr 1차 6333GIS 정밀점검 (#2BUS 휴전-차단기 시험가압)","2020-07-03 17:00","2020-07-03 18:00","2020-07-03 17:00","2020-07-03 18:00","연속"]
[109,"부산울산","북부산","호포물금 T/L","2020 북부산전력지사 154kV GIS 정밀점검","호포S/S 154kV #1M.Tr 1차 GIS(6133) 정밀점검 (#2DS 측 시험가압 )","2020-07-01 17:00","2020-07-01 18:00","2020-07-01 17:00","2020-07-01 18:00","연속"]
[110,"부산울산","서부산","다대신평 T/L","154kV 다대-신평T/L 등 3개T/L 지장이설공사","[을숙도대교~장림고개 간 지하차도 건설공사] 지장 지중송전설비 이설 - 케이블 포설 : 4구간, 접속 : IJ(9상), NJ(12상)","2020-07-01 09:00","2020-07-17 18:00","2020-07-01 09:00","2020-07-17 18:00","연속"]
[111,"부산울산","서부산","다대장림 T/L","154kV 다대-신평T/L 등 3개T/L 지장이설공사","[을숙도대교~장림고개 간 지하차도 건설공사] 지장 지중송전설비 이설 - 케이블 포설 : 4구간, 접속 : IJ(9상), NJ(12상)","2020-07-20 09:00","2020-08-04 18:00","취소","취소","연속"]
[112,"부산울산","서부산","신김해지사#2 T/L","보호IED ~ SCADA 원격소장치 연계시스템 시설공사","선로명 : 154kV 신김해-지사#2 T/L 작업내용 : 연계시스템 시설관련 보호계전기 IED 설정","2020-07-02 09:00","2020-07-02 18:00","2020-07-02 09:00","2020-07-02 18:00","연속"]
[113,"부산울산","서부산","신김해지사#1 T/L","보호IED ~ SCADA 원격소장치 연계시스템 시설공사","선로명 : 154kV 신김해-지사#1 T/L 작업내용 : 연계시스템 시설관련 보호계전기 IED 설정","2020-07-01 09:00","2020-07-01 18:00","2020-07-01 09:00","2020-07-01 18:00","연속"]
[114,"부산울산","울산","신울산울산#1 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2020-07-01 07:00","2020-07-03 18:00","2020-07-01 07:00","2020-07-03 18:00","연속"]
[115,"부산울산","울산","울산울산TP#2 T/L","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","- 송전선 이설(627-&gt617) - 울산T/P 154kV (신)울산-울산TP#2T/L GIS(627) #65BUS 및 GIS 전체 시험가압 선로(24H이상)","2020-07-16 09:00","2020-07-22 18:00","취소","취소","연속"]
[116,"부산울산","울산","울산울산TP#2 T/L","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","- 울산T/P 154kV (구)울산-울산TP#1T/L GIS(617) #2DS철거 및 고깔 설치 후 #65BUS 시험가압 선로(1H)","2020-07-06 17:00","2020-07-06 18:00","취소","취소","연속"]
[117,"부산울산","울산","울산T/P 154kV #60 BUS","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","- 울산T/P 154kV (구)울산-울산TP#1T/L GIS(617) #1DS, CB, 부싱, GIB 철거 - 울산T/P 154kV (신)울산-울산TP#2T/L GIS(627) #1DS, CB, 부싱, GIB 설치","2020-07-07 09:00","2020-07-13 09:00","취소","취소","연속"]
[118,"부산울산","울산","울산T/P 154kV #65 BUS","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","- 울산T/P 154kV (구)울산-울산TP#1T/L GIS(617) #2DS 고깔, 상부BUS, GIB 철거 - 울산T/P 154kV (신)울산-울산TP#2T/L GIS(627) #2DS, 상부BUS, GIB 설치","2020-07-13 09:00","2020-07-22 18:00","취소","취소","연속"]
[119,"부산울산","울산","울산T/P 154kV #60 BUS","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","1. 울산-울산T/P #1T/L 송전선 이설 2. 시험가압일정 / 대상/가압경로 ㅇ 07.03 17:00~(1h) / 울산-울산TP#1T/L / #60BUS, 자체선로 1DS(투입)","2020-07-03 17:00","2020-07-03 18:00","2020-07-03 17:00","2020-07-03 18:00","연속"]
[120,"부산울산","울산","울산T/P 154kV #65 BUS","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","- 울산T/P 154kV (구)울산-울산TP#1T/L GIS(617) #2DS철거 및 고깔 설치","2020-06-26 17:00","2020-06-26 18:00","2020-06-26 17:00","2020-06-26 18:00","연속"]
[121,"부산울산","울산","울산울산TP#2 T/L","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","- 울산T/P 154kV (신)울산-울산TP#2T/L GIS(627) #60BUS 시험가압 선로(24H이상)","2020-07-11 18:00","2020-07-13 09:00","취소","취소","연속"]
[122,"부산울산","울산","울산T/P 154kV #60 BUS","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","- 울산T/P 154kV (신)울산-울산TP#2T/L GIS(627) #1DS(#60BUS) 시험가압","2020-07-22 17:00","2020-07-22 18:00","취소","취소","연속"]
[123,"경남",null,"합천합천수력#1 T/L","옥외변전소 점검보수","옥외변전소 점검보수","2020-07-21 09:00","2020-07-23 18:00","취소","취소","연속"]
[124,"경남",null,"합천합천수력#2 T/L","옥외변전소 점검보수","옥외변전소 점검보수","2020-07-21 09:00","2020-07-23 18:00","취소","취소","연속"]
[125,"대구","달성","달성상인#2 T/L","154kV 달성상인#2 T/L 보호반 대체공사","송전선로 보호반 대체 공사","2020-07-16 09:00","2020-07-17 18:00","2020-07-16 09:00","2020-07-17 18:00","연속"]