{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":9,"n_cols":11,"rows_kept":9,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2020년도 8월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"강원","태백","신태백신한울#1 T/L","2020년 신태백S/S 800kV GIS 보통점검 공사","CB(8471), HSGS(84H1), DS(8461, 8401, 8421), VT(84Bay T/L) 보통점검","2020-08-24 09:00","2020-08-28 18:00","2020-08-24 09:00","2020-08-28 18:00","연속"]
[2,"강원","태백","신태백S/S #2 M.Tr","2020년 신태백S/S 800kV GIS 보통점검 공사","CB (8300, 8372), DS (8302, 8362, 8322), VT(#2M.Tr 1차) 보통점검, #2M.Tr 1, 2차측 도체분리·접속","2020-08-10 09:00","2020-08-21 18:00","2020-08-10 09:00","2020-08-21 18:00","연속"]
[3,"강원","태백","신태백S/S 765kV #1 BUS","2020년 신태백S/S 800kV GIS 보통점검 공사","DS(8351, 8451, 8551, 8651), ES+VT(#1BUS) 보통점검","2020-08-04 09:00","2020-08-05 18:00","취소","취소","연속"]
[4,"강원","태백","신태백S/S 765kV #2 BUS","2020년 신태백S/S 800kV GIS 보통점검 공사","DS(8352, 8452, 8652), ES+VT(#2BUS) 보통점검","2020-08-06 09:00","2020-08-07 18:00","취소","취소","연속"]
[5,"강원","태백","신태백신한울#2 T/L","2020년 신태백S/S 800kV GIS 보통점검 공사","CB(8371), HSGS(83H1), DS(8361, 8301, 8321), VT(83Bay T/L) 보통점검","2020-08-17 09:00","2020-08-21 18:00","2020-08-17 09:00","2020-08-21 18:00","연속"]

{"sheet":"345송부","index":1,"n_rows":36,"n_cols":11,"rows_kept":36,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2020년도 8월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","동서울","동서울S/S 345kV CB 7A72","345kV GIS 초기점검","345kV 7A72, 7079 GIS 초기점검","2020-08-03 09:00","2020-08-04 18:00","2020-08-03 09:00","2020-08-04 18:00","연속"]
[2,"남서울","동서울","동서울S/S 345kV #2 Sh.R","345kV #2Sh.R 초기 및 GIS 초기점검","345kV #2Sh.R 초기점검 345kV 7A72, 7079 GIS 초기점검","2020-08-03 09:00","2020-08-04 18:00","2020-08-03 09:00","2020-08-04 18:00","연속"]
[3,"남서울","동서울","동서울S/S 345kV CB 7A00","345kV GIS 초기점검","345kV 7A72, 7079 GIS 초기점검","2020-08-03 09:00","2020-08-04 18:00","2020-08-03 09:00","2020-08-04 18:00","연속"]
[4,"인천","부평","신경서포스코CC#2 T/L","345kV 신경서-포스코T/L 접속함 교체공사","중간접속함 리콜자재(에폭시유니트 불량)로 교체시행 (23set)","2020-08-24T09:00:00","2020-09-27T18:00:00","2020-08-24T09:00:00","2020-09-27T18:00:00","연속"]
[5,"경기북부","고양","신파주S/S SVC CB","20년 신파주S/S SVC 보통점검","20년 신파주S/S 345kV SVC 보통점검","2020-08-03 09:00","2020-08-14 18:00","2020-08-03 09:00","2020-08-14 18:00","연속"]
[6,"경기북부","구리","신가평S/S 345kV #3 Sh.R","'20-21년 구리전력지사 변전정비회사 총액공사","장기사용 배전반 대체 - 신가평S/S 345kV #3Sh.R보호반 대체","2020-08-24 09:00","2020-08-28 18:00","2020-08-24 09:00","2020-08-28 18:00","연속"]
[7,"경기북부","구리","신가평S/S 345kV #4 Sh.R","'20-21년 구리전력지사 변전정비회사 총액공사","장기사용 배전반 대체 - 신가평S/S 345kV #4Sh.R보호반 대체","2020-08-31 09:00","2020-09-04 18:00","2020-08-31 09:00","2020-09-04 18:00","연속"]
[8,"경기북부","직할","신의정부S/S 345kV #1 Sh.R","2020~2021년 경기북부 직할 변전정비회사 총액공사","Sh.R 냉각설비 청소 및 점검","2020-08-05 09:00","2020-08-05 12:00","2020-08-05 09:00","2020-08-05 12:00","연속"]
[9,"강원","동해","동해신양양 T/L","세니온제 보호계전기 성능개선","345kV 동해-신양양T/L 보호계전기 성능개선(양단)","2020-08-11 10:30","2020-08-11 18:00","2020-08-11 10:30","2020-08-11 18:00","연속"]
[10,"강원","태백","신태백S/S 345kV #3 Sh.R","765kV 신태백S/S 345kV 용량부족차단기 대체 및 SW증설공사","345kV 75Bay 용량부족 GIS 3CB 대체(7571, 7500, 7579 휴전, 7572 휴전은 임시로 진행 예정)","2020-08-13 09:00","2020-11-10 18:00","2020-08-13 09:00","2020-11-10 18:00","연속"]
[11,"강원","태백","신태백S/S 345kV CB 7400","765kV 신태백S/S 345kV 용량부족차단기 대체 및 SW증설공사","345kV 신태백한울NP2 #1T/L 송전선로 인출변경 (75Bay → 74Bay 이설)","2020-08-03 09:00","2020-08-13 18:00","2020-08-03 09:00","2020-08-13 18:00","연속"]
[12,"강원","태백","신태백S/S 345kV CB 7472","765kV 신태백S/S 345kV 용량부족차단기 대체 및 SW증설공사","345kV 신태백한울NP2 #1T/L 송전선로 인출변경 (75Bay → 74Bay 이설)","2020-08-03 09:00","2020-08-13 18:00","2020-08-03 09:00","2020-08-13 18:00","연속"]
[13,"강원","태백","신태백한울NP#1 T/L","765kV 신태백S/S 345kV 용량부족차단기 대체 및 SW증설공사","345kV 신태백한울NP2 #1T/L 송전선로 인출변경 (75Bay → 74Bay 이설)","2020-08-03 09:00","2020-08-13 18:00","2020-08-03 09:00","2020-08-13 18:00","연속"]
[14,"충북","충주","곤지암신충주#1 T/L","345kV 곤지암-신충주 등 4개T/L 전력선교체공사","전선접소개소 해소 전력선교체공사","2020-08-24 07:00","2020-09-07 18:00","2020-08-24 07:00","2020-09-07 18:00","연속"]
[15,"충북","충주","신제천신충주#2 T/L","345kV 곤지암-신충주 등 4개T/L 전력선교체공사","전선접소개소 해소 전력선교체공사","2020-08-19 07:00","2020-08-21 18:00","2020-08-19 07:00","2020-08-21 18:00","연속"]
[16,"충북","충주","신제천신충주#1 T/L","345kV 곤지암-신충주 등 4개T/L 전력선교체공사","전선접소개소 해소 전력선교체공사","2020-08-16 07:00","2020-08-18 18:00","2020-08-16 07:00","2020-08-18 18:00","연속"]
[17,"전북","김제","신김제S/S #3 M.Tr","154kV Sh.C GIS 개조공사","154kV #1,#2Sh.C GIS 개조공사 - 안전이격 확보 휴전(긴급시 30분내 투입가능)","2020-08-10 09:00","2020-08-10 18:00","2020-08-10 09:00","2020-08-10 18:00","연속"]
[18,"광주전남","목포","한빛3N/P 345kV #1BUS","한빛N/P #3S/Y 7D51DS 부분방전 해소공사","한빛N/P #3S/Y 7D51DS B상 부분방전 해소공사","2020-08-05 09:00","2020-08-07 18:00","2020-08-05 09:00","2020-08-07 18:00","연속"]
[19,"대구","달성","고령S/S #4 M.Tr","고령S/S 345kV #4M.Tr 96P,96D 회로보완","고령S/S 345kV #4M.Tr 96P,96D 회로보완","2020-08-03 09:00","2020-08-03 18:00","2020-08-03 09:00","2020-08-03 18:00","연속"]
[20,"대구","칠곡","북대구S/S 345kV CB 7172","신포항-북대구T/L 7172CB Control Block 교체공사","신포항-북대구T/L 7172CB Control Block 교체공사","2020-08-24 09:30","2020-08-26 14:00","2020-08-24 09:30","2020-08-26 14:00","연속"]
[21,"대구","칠곡","북대구S/S #3 M.Tr","북대구S/S 345kV M.Tr 기계적보호장치 회로보완","북대구S/S 345kV M.Tr 기계적보호장치 회로보완","2020-08-07 09:00","2020-08-07 18:00","2020-08-07 09:00","2020-08-07 18:00","연속"]
[22,"대구","칠곡","북대구S/S #2 M.Tr","북대구S/S 345kV M.Tr 기계적보호장치 회로보완","북대구S/S 345kV M.Tr 기계적보호장치 회로보완","2020-08-06 09:00","2020-08-06 18:00","2020-08-06 09:00","2020-08-06 18:00","연속"]
[23,"대구","칠곡","북대구S/S #1 M.Tr","북대구S/S 345kV M.Tr 기계적보호장치 회로보완","북대구S/S 345kV M.Tr 기계적보호장치 회로보완","2020-08-05 09:00","2020-08-05 18:00","2020-08-05 09:00","2020-08-05 18:00","연속"]
[24,"대구","칠곡","북대구S/S 345kV CB 7100","신포항-북대구T/L TIE 7100CB Control Block 교체공사","신포항-북대구T/L TIE 7100CB Control Block 교체공사","2020-08-26 14:00","2020-08-28 18:00","2020-08-26 14:00","2020-08-28 18:00","연속"]
[25,"대구","포항","신포항S/S #4 M.Tr","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 상부모선 및 금구류 철거 - 모선배선 및 리드선 연결 - CB, DS, CVT, 기기가대, 제어케이블 철거 등","2020-08-10 08:00","2020-08-12 18:00","2020-08-10 08:00","2020-08-12 18:00","연속"]
[26,"대구","포항","신포항S/S #3 M.Tr","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 상부모선 및 금구류 철거 - 모선배선 및 리드선 연결 - CB, DS, 기기가대, 제어케이블 철거 등","2020-08-03 08:00","2020-08-06 18:00","2020-08-03 08:00","2020-08-06 18:00","연속"]
[27,"경북","영주","한울1NP한울2NP#2 T/L","2020-21년 영주전력지사 변전정비회사 총액공사","- YPP 계전기 성능개선 - 7100,7172 CB 보통점검","2020-08-21 09:00","2020-08-21 18:00","취소","취소","연속"]
[28,"대전충남","서산","북당진현대제철 T/L","345kV 신송산분기T/L 건설공사","- 해당구간 : No.71 ~ No.69 구간내 No.70 선로 - 공사내용 : No.70 선로 가 철탑 이설 전력선 공중이동 ACSR/AW 480SQ x 4B x 2C (0.793km)","2020-08-03 07:00","2020-08-06 18:00","취소","취소","연속"]
[29,"대전충남","서산","신당진개폐소현대제철 T/L","345kV 신송산분기T/L 건설공사","- 해당구간 : No.71 ~ No.69 구간내 No.70 선로 - 공사내용 : No.70 선로 가 철탑 이설 전력선 공중이동 ACSR/AW 480SQ x 4B x 2C (0.793km)","2020-08-07 07:00","2020-08-10 18:00","취소","취소","연속"]
[30,"광주전남",null,"한빛N/P #3호기 주변압기 CB","3호기 17차 OH - 조작차단기 7700, 7771","계통 연결 조작(시험 및 계통 병입)","2020-08-28 22:00","2020-08-29 01:00","2020-08-28 22:00","2020-08-29 01:00","연속"]
[31,"경북",null,"한울N/P #6호기 주변압기 CB","6호기 11차 계획예방정비 * 조작차단기 : CB 7C00, 7C72","○ 주변압기 B상 교체 ○ 주변압기 A상 정밀점검 ○ 주/소내보조/여자변압기 일반점검 ○ 소내전원 절체(UAT→SAT)시험","2020-08-04 15:00","2020-09-14 15:00","2020-08-04 15:00","2020-09-14 15:00","연속"]
[32,"경북",null,"한울1호기 기동변압기(7300,7372)","비상보조변압기 일반점검","비상보조변압기 일반점검","2020-08-24 15:00","2020-08-31 15:00","2020-08-24 15:00","2020-08-31 15:00","연속"]

{"sheet":"154송부","index":2,"n_rows":35,"n_cols":11,"rows_kept":35,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2020년도 8월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","Q(MVAr)","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","광장뚝도#2 T/L","2020년 성동P/O 변전정비회사 총액공사","2020년 성동P/O 변전정비회사 총액공사","2020-07-03 13:00","2020-07-03 18:00","취소","취소","연속"]
[2,"남서울","동서울","염곡개포#2 T/L","154kv염곡-개포T/L 지장이설","염곡-개포T/L 지장이설 1. 구 간 및 선종 : M/H#4~#5 약 450m (OF2000) 2회선 2. 공사기간 (케이블) 20년 08월 ~ 20년 12월 3. 이설 비용 : 서초구청 4. 시공업체 : LS전선 5. 특이사항 : 기존 관로경과지에 전력구 신설","2020-08-31 09:00","2020-10-23 18:00","2020-08-31 09:00","2020-10-23 18:00","연속"]
[3,"경기북부","구리","미금아리수#1 T/L CB","미금S/S 감시제어설비 교체공사","- 노후 모자익반 및 현장조작반간 제어케이블 교체 (아날로그 → 디지털SA)","2020-08-24 09:00","2020-08-28 18:00","취소","취소","연속"]
[4,"경기","동부","야탑성현#1 T/L","154kV 성현S/S #5M.Tr 증설공사","154kV 성현S/S #5M.Tr 증설공사 -170kV 전력케이블 설치위한 관로 구성시 안전이격거리 확보","2020-08-10 09:00","2020-08-31 18:00","2020-08-10 09:00","2020-08-31 18:00","연속"]
[5,"경기","동부","야탑성현#2 T/L","154kV 성현S/S #5M.Tr 증설공사","154kV 성현S/S #5M.Tr 증설공사 -170kV 전력케이블 설치위한 관로 구성시 안전이격거리 확보","2020-08-10 09:00","2020-08-31 18:00","2020-08-10 09:00","2020-08-31 18:00","연속"]
[6,"경기","평택","진위동탄#2 T/L","진위S/S 154kV #4M.Tr 증설 관련 최초가압 및 무부하가압","진위S/S 154kV #4M.Tr 증설 관련 최초가압 및 무부하가압","2020-08-10 09:00","2020-08-11 18:00","2020-08-10 09:00","2020-08-11 18:00","연속"]
[7,"강원","강릉","주진평창#1 T/L","2020년 변전협력총액공사 170kV GIS 보통점검","○ 2020년 변전협력총액공사 - 기타기기 점검(피뢰기) - 평창S/S 주진평창#1T/L 장기미동작 차단기 동작시험","2020-08-03 10:00","2020-08-03 18:00","2020-08-03 10:00","2020-08-03 18:00","연속"]
[8,"강원","원주","홍천S/S 154kV CB 6100","홍천S/S 154kV 6100 BUS-TIE GIS 불량카운터 조치","홍천S/S 154kV 6100 BUS-TIE GIS 불량카운터 조치 (제작사 : 현대)","2020-08-25 10:00","2020-08-25 18:00","2020-08-25 10:00","2020-08-25 18:00","연속"]
[9,"충북","충주","감곡여주#2 T/L","154kV 감곡-여주T/L No.4~12호간 지장이설공사(요청자시행)","154kV 감곡-여주T/L 4~12호 철탑이설공사 - 이설시행자 : 하나은행(요청자 직접시행) - 철탑이설 : 7기(5~11호) - 이설목적 : 감곡골프장 조성에 지장이 되는 철탑의 이설","2020-08-08 08:00","2020-08-19 18:00","2020-08-08 08:00","2020-08-19 18:00","연속"]
[10,"전북","군산","군산영등#1 T/L","성능저하 국산 점퍼지지애자 교체공사","-점퍼지지애자교체 : S/T, 44, 55호","2020-08-11 07:00","2020-08-11 18:00","취소","취소","연속"]
[11,"전북","군산","군산영등#2 T/L","성능저하 국산 점퍼지지애자 교체공사","-점퍼지지애자교체 : S/T, 44, 55호","2020-08-10 07:00","2020-08-10 18:00","취소","취소","연속"]
[12,"전북","군산","내초군장#2 T/L","내초S/S #3M.Tr 부분방전 해소공사 무부하 가압","- 내초S/S #3M.Tr 부분방전 해소 내부점검 후 무부하 가압","2020-08-06 09:00","2020-08-06 18:00","2020-08-08 09:00","2020-08-08 18:00","연속"]
[13,"전북","군산","비응군장#1 T/L","비응S/S 170kV GIS 제작사 부분방전 하자보수공사","GIS 이음발생 하자보수 2DS 이음개소 하자보수","2020-08-24 09:00","2020-08-28 18:00","취소","취소","연속"]
[14,"전북","군산","비응군장#2 T/L","비응S/S 154kV GIS 제작사 부분방전 관련 하자보수공사","차단부 부분방전 하자보수 2DS 이음개소 하자보수","2020-08-17 09:00","2020-08-21 18:00","취소","취소","연속"]
[15,"전북","군산","새만금비응#2 T/L","비응S/S 154kV GIS 제작사 부분방전 관련 하자보수공사","차단부 부분방전 하자보수 2DS 이음개소 하자보수","2020-08-17 09:00","2020-08-21 18:00","취소","취소","연속"]
[16,"전북","군산","새만금비응#1 T/L","비응S/S 170kV GIS 제작사 부분방전 하자보수공사","GIS 이음발생 하자보수 2DS 이음개소 하자보수","2020-08-24 09:00","2020-08-28 18:00","취소","취소","연속"]
[17,"전북","군산","팔봉두마#1 T/L","성능저하 국산 점퍼지지애자 교체공사","-점퍼지지애자교체 : 7호","2020-08-11 07:00","2020-08-11 18:00","취소","취소","연속"]
[18,"광주전남","목포","안좌신안그린발전#1 T/L CB","`20년 목포전력지사 변전정비회사 총액공사","차단기 조작시험","2020-08-17 10:00","2020-08-17 18:00","2020-08-17 10:00","2020-08-17 18:00","연속"]
[19,"광주전남","목포","영광백수풍력#1 T/L CB","`20년 목포전력지사 변전정비회사 총액공사","차단기 조작시험","2020-08-24 10:00","2020-08-24 18:00","2020-08-24 10:00","2020-08-24 18:00","연속"]
[20,"대구","경산","하양반야월#1 T/L","154kV 신서분기 지중T/L 건설공사","신서E/C~154kV 하양-반야월T/L 분기맨홀(2파이 분기) 154kV XLPE1200*2C(D) 0.5km, 154kV XLPE2500*2C 0.5km","2020-08-10 09:30","2020-09-03 18:00","2020-08-10 09:30","2020-09-03 18:00","연속"]
[21,"대구","달성","논공S/S 154kV #1 EM.Tr CB","논공S/S 154kV EM.Tr 96P, 96D 회로보완","논공S/S 154kV EM.Tr 96P, 96D 회로보완","2020-08-04 09:00","2020-08-04 18:00","2020-08-04 09:00","2020-08-04 18:00","연속"]
[22,"대구","직할","검단산격#2 T/L","변전소 인출구간 OF 선종교체 공사","변전소 인출구간 OF 선종교체","2020-08-10 09:00","2020-09-04 18:00","2020-08-10 09:00","2020-09-04 18:00","연속"]
[23,"대구","포항","신포항영일#1 T/L","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 상부모선 및 금구류 철거 - 모선배선 및 리드선 연결 - CB, DS, CVT, 기기가대, 제어케이블 철거 등","2020-08-10 08:00","2020-08-12 18:00","2020-08-10 08:00","2020-08-12 18:00","연속"]
[24,"대구","포항","신포항영일#2 T/L","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 상부모선 및 금구류 철거 - 모선배선 및 리드선 연결 - CB, DS, CVT, 기기가대, 제어케이블 철거 등","2020-08-03 08:00","2020-08-06 18:00","2020-08-03 08:00","2020-08-06 18:00","연속"]
[25,"부산울산","북부산","김해어방#2 T/L","2020-2021년 북부산전력지사 가공송전협력회사 총액공사","불량애자련 교체","2020-08-03 12:00","2020-08-03 18:00","2020-08-03 12:00","2020-08-03 18:00","연속"]
[26,"부산울산","북부산","김해어방#1 T/L","2020-2021년 북부산전력지사 가공송전협력회사 총액공사","불량애자련 교체","2020-08-03 08:00","2020-08-03 12:00","2020-08-03 08:00","2020-08-03 12:00","연속"]
[27,"부산울산","북부산","북부산미남#2 T/L","2020-2021년 북부산전력지사 가공송전협력회사 총액공사","불량애자련 교체","2020-08-04 12:00","2020-08-04 18:00","2020-08-04 12:00","2020-08-04 18:00","연속"]
[28,"부산울산","북부산","북부산미남#1 T/L","2020-2021년 북부산전력지사 가공송전협력회사 총액공사","불량애자련 교체","2020-08-04 08:00","2020-08-04 12:00","2020-08-04 08:00","2020-08-04 12:00","연속"]
[29,"부산울산","서부산","다대장림 T/L","154kV 다대-신평T/L 등 3개T/L 지장이설공사","[을숙도대교~장림고개 간 지하차도 건설공사] 지장 지중송전설비 이설 - 케이블 포설 : 4구간, 접속 : IJ(9상), NJ(12상)","2020-08-21 09:00","2020-09-03 18:00","취소","취소","연속"]
[30,"부산울산","서부산","서부산S/S 154kV #65 BUS","154kV 서부산-다대T/L 지장이설 및 선종교체공사","1. 선로명 : 154kV 서부산-다대#2T/L 2. 구 간 : J/B#2 ~ J/B#5(1.01km) 3. 작업내용 : 을숙도대교-장림고개간 지하차도 건설공사에 따른 지장이설(선종교체 병행) ] 4. 휴전요청 사유 : 시험가압 후 앵글체크 시 서부산S/S측 모선절체(#65->#60)","2020-08-28 09:00","2020-08-28 18:00","취소","취소","연속"]
[31,"부산울산","서부산","다대신평 T/L","154kV 다대-신평T/L 등 3개T/L 지장이설공사","[을숙도대교~장림고개 간 지하차도 건설공사] 지장 지중송전설비 이설 - 케이블 포설 : 4구간, 접속 : IJ(9상), NJ(12상)","2020-08-03 09:00","2020-08-20 18:00","2020-08-03 09:00","2020-08-20 18:00","연속"]