{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":15,"n_cols":11,"rows_kept":15,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2020년도 11월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신안성신가평 T/L","765kV 신안성-신가평T/L 항공시설물 정비공사","- 765kV 신안성-신가평T/L 항공장애표시도장(19기)","2020-11-02 07:00","2020-11-30 18:00","취소","취소","연속"]
[2,"경기북부","구리","신가평S/S #3 M.Tr","신가평S/S 765kV #3M.Tr OLTC 불량 보수","신가평S/S 765kV #3M.Tr A-L상 OLTC 불량 보수","2020-11-03 10:00","2020-11-05 18:00","2020-11-03 10:00","2020-11-05 18:00","연속"]
[3,"강원","태백","신태백S/S #3 M.Tr","765kV 신태백S/S 345kV 용량부족차단기 대체 및 SW증설공사","- 345kV 76Bay GIS 대체(40kA 4000A→ 63kA 6300A)","2020-11-16 09:00","2021-03-10 18:00","2020-11-16 09:00","2021-03-10 18:00","연속"]
[4,"강원","태백","신태백S/S 765kV CB 8671","2020년 태백전력지사 800kV GIS 보통점검 공사","신태백변전소 8671CB 보통점검","2020-11-02 09:00","2020-11-03 18:00","2020-11-02 09:00","2020-11-03 18:00","연속"]
[5,"강원","태백","신태백S/S 765kV CB 8600","2020년 태백전력지사 800kV GIS 보통점검 공사","신태백변전소 8600CB 보통점검","2020-11-04 09:00","2020-11-05 18:00","2020-11-04 09:00","2020-11-05 18:00","연속"]
[6,"강원","태백","신태백S/S 765kV CB 8500","2020년 태백전력지사 800kV GIS 보통점검 공사","신태백변전소 8500CB 보통점검","2020-11-06 09:00","2020-11-06 18:00","2020-11-06 09:00","2020-11-06 18:00","연속"]
[7,"강원","태백","신태백S/S 765kV CB 8571","2020년 태백전력지사 800kV GIS 보통점검 공사","신태백변전소 8571CB 보통점검","2020-11-09 09:00","2020-11-10 18:00","2020-11-09 09:00","2020-11-10 18:00","연속"]
[8,"충북","직할","신중부S/S 765kV #2 BUS","신중부S/S 765kV GIS 설치공사","- 765kV GIS 설치 * 1CB(8572) - 기타 부대공사 12식","2020-11-02 09:00","2020-11-23 18:00","2020-11-02 09:00","2020-11-18 18:00","연속"]
[9,"충북","직할","신중부S/S 765kV CB 8500","신중부S/S 765kV GIS 설치공사","- 765kV GIS 설치 * 1CB(8572) - 기타 부대공사 12식","2020-11-02 09:00","2020-11-23 18:00","2020-11-02 09:00","2020-12-30 18:00","연속"]
[10,"부산울산","동부산","북경남신고리NP#1 T/L","765kV GIS HSES 개방회로 개선","북경남신고리NP#1T/L HSES 개방회로(단상 개방방식으로 변경) 개선","2020-11-19 09:30","2020-11-19 18:00","2020-11-19 09:30","2020-11-19 18:00","연속"]
[11,"부산울산","동부산","북경남신고리NP#2 T/L","765kV GIS HSES 개방회로 개선","북경남신고리NP#2T/L HSES 개방회로(단상 개방방식으로 변경) 개선","2020-11-18 09:30","2020-11-18 18:00","2020-11-18 09:30","2020-11-18 18:00","연속"]

{"sheet":"345송부","index":1,"n_rows":355,"n_cols":11,"rows_kept":355,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2020년도 11월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #1 M.Tr","2020년 성동P/O 345kV M.Tr 및 OLTC 정밀점검공사","2020년 성동P/O 345kV M.Tr 및 OLTC 정밀점검공사","2020-11-09 09:30","2020-11-18 18:00","2020-11-09 09:30","2020-11-18 18:00","연속"]
[2,"서울","성동","성동S/S #4 M.Tr","2020년 성동P/O 345kV M.Tr 및 OLTC 정밀점검공사","2020년 성동P/O 345kV M.Tr 및 OLTC 정밀점검공사","2020-11-19 09:30","2020-11-27 18:00","2020-11-19 09:30","2020-11-27 18:00","연속"]
[3,"서울","중부","중부S/S #3 M.Tr","중부S/S 345kV 주변압기 및 OLTC 정밀점검공사","중부S/S 345kV 주변압기 및 OLTC 정밀점검공사","2020-11-26 10:00","2020-12-06 18:00","취소","취소","연속"]
[4,"서울","중부","중부S/S 345kV CB 7371","345kV 중부S/S #4M.Tr 증설공사","○ 345kV M.Tr(단상 166.7MVA×3대, 송유풍냉식) × 1Bank 설치 ○ 345kV GIS(362kV, 50kA, 4000A) × 1CB 설치 (GIB 포함) ○ 154kV GIS(170kV, 50kA, 2000A, TR) × 1CCT 설치 ○ 25.8kV 친환경개폐장치(25.8kV, 단모선) × 1식 설치","2020-11-08 09:00","2020-11-08 18:00","2020-11-08 09:00","2020-11-08 18:00","연속"]
[5,"서울","중부","중부S/S 345kV CB 7300","345kV 중부S/S #4M.Tr 증설공사","○ 345kV M.Tr(단상 166.7MVA×3대, 송유풍냉식) × 1Bank 설치 ○ 345kV GIS(362kV, 50kA, 4000A) × 1CB 설치 (GIB 포함) ○ 154kV GIS(170kV, 50kA, 2000A, TR) × 1CCT 설치 ○ 25.8kV 친환경개폐장치(25.8kV, 단모선) × 1식 설치","2020-11-08 09:00","2020-11-25 18:00","2020-11-08 09:00","2020-11-25 18:00","연속"]
[6,"서울","중부","중부S/S #1 M.Tr","`20 중부PO 변전정비회사 총액공사","#1M.Tr 초기점검, 누기보수, 누유보수","2020-11-30 10:00","2020-12-02 18:00","취소","취소","연속"]
[7,"서울","중부","중부S/S 345kV #1 Sh.R","`20 중부PO 변전정비회사 총액공사","GIS 누기보수","2020-11-30 10:00","2020-12-02 18:00","2020-11-30 10:00","2020-12-02 18:00","연속"]
[8,"남서울","강남","신양재S/S 345kV CB 7171","신양재S/S 362kV GIS Control block 교체","신양재S/S 362kV GIS Control block 교체 - 단독 차단기(7171) 휴전","2020-11-30 09:00","2020-12-08 18:00","2020-11-30 09:00","2020-12-08 18:00","연속"]
[9,"남서울","강남","신양재S/S 345kV #4 Sh.R","신양재S/S 362kV GIS 정밀점검","신양재S/S 362kV GIS 정밀점검","2020-11-13 09:00","2020-11-27 18:00","2020-11-13 09:00","2020-11-27 18:00","연속"]
[10,"남서울","강남","신양재S/S 345kV #3 Sh.R","신양재S/S 362kV GIS Control block 교체","신양재S/S 362kV GIS Control block 교체","2020-11-02 09:00","2020-11-12 18:00","2020-11-02 09:00","2020-11-12 18:00","연속"]
[11,"남서울","강남","신양재S/S #2 M.Tr","2020년 강남P/O 345kV 주변압기 정밀점검","- 신양재S/S #2M.Tr 정밀점검","2020-11-02 09:00","2020-11-20 18:00","2020-11-02 09:00","2020-11-20 18:00","연속"]
[12,"남서울","동서울","신성남동서울#2 T/L","20~21년 동서울전력지사 가공송전정비회사 총액공사","철탑 추락방지시설 설치공사","2020-11-29 08:00","2020-11-29 18:00","2020-11-29 08:00","2020-11-29 18:00","연속"]
[13,"남서울","동서울","신성남동서울#1 T/L","20~21년 동서울전력지사 가공송전정비회사 총액공사","철탑 추락방지시설 설치공사","2020-11-28 08:00","2020-11-28 18:00","취소","취소","연속"]
[14,"남서울","동서울","곤지암동서울#1 T/L","세종-포천고속도로건설 지장송전선로 지중화(이설)공사","345kV 곤지암-동서울T/L No.66 이설","2020-11-11 09:00","2020-11-16 18:00","2020-11-11 09:00","2020-11-16 18:00","연속"]
[15,"남서울","동서울","동서울S/S #2 M.Tr","동서울S/S 345kV 노후 주변압기 교체공사","○ 345kV M.Tr 7대 교체 ○ 기타 부대작업 1식","2020-11-02 09:00","2020-11-27 18:00","2020-11-07 14:00","2020-12-02 14:00","연속"]
[16,"남서울","동서울","곤지암동서울#2 T/L","세종-포천고속도로건설 지장송전선로 지중화(이설)공사","345kV 곤지암-동서울T/L No.66 이설","2020-11-02 09:00","2020-11-10 18:00","2020-11-02 09:00","2020-11-10 18:00","연속"]
[17,"남서울","동서울","동서울S/S #3 M.Tr","#3M.Tr 누유개소 점검 및 보수","#3M.Tr 누유개소 보수 및 bushing 절연유 채유","2020-11-01 09:00","2020-11-01 18:00","2020-11-06 09:00","2020-11-06 18:00","연속"]
[18,"남서울","동서울","동서울미금#2 T/L","세종-포천 고속도로건설 지장송전선로 지중화(이설)공사","임시철탑 No.1~5(5기) 건설","2020-11-19 09:00","2020-12-08 18:00","2020-11-19 09:00","2020-12-08 18:00","연속"]
[19,"남서울","동서울","동서울S/S 345kV #76 BUS","동서울S/S 345kV 노후 주변압기 교체공사","○ 345kV M.Tr 7대 교체 ○ 기타 부대작업 1식","2020-11-24 13:00","2020-11-25 13:00","2020-11-27 13:00","2020-11-28 13:00","연속"]
[20,"남서울","동서울","신성남동서울#2 T/L","동서울S/S 345kV 노후 주변압기 교체공사","○ 345kV M.Tr 7대 교체 ○ 기타 부대작업 1식","2020-11-24 13:00","2020-11-25 13:00","2020-11-27 13:00","2020-11-28 13:00","연속"]
[21,"남서울","동서울","동서울미금#1 T/L","세종-포천 고속도로건설 지장송전선로 지중화(이설)공사","임시철탑 No.1~5(5기) 건설","2020-11-19 09:00","2020-12-08 18:00","2020-11-19 09:00","2020-12-08 18:00","연속"]
[22,"남서울","동서울","동서울S/S #4 M.Tr","동서울S/S 345kV 노후 주변압기 교체공사","○ 345kV M.Tr 7대 교체 ○ 기타 부대작업 1식","2020-11-30 09:00","2020-12-18 18:00","취소","취소","연속"]
[23,"남서울","영등포","신시흥신광명#1 T/L","추락방지시설 설치공사","추락방지시설 설치공사 345kV 신시흥-신광명T/L No.5,11,12,13호 수직, 수평 추락방지시설 설치","2020-11-09 08:00","2020-11-09 18:00","2020-11-23 08:00","2020-11-23 18:00","연속"]
[24,"남서울","영등포","신광명S/S 345kV CB 7672","신광명S/S 362kV GIS 보통점검(신광명-영등포#2)","- 차단기 개폐타임 측정 - 차단기 메커니즘 점검 - SF6 가스 수분 및 SO2 측정. 등.","2020-11-07 14:00","2020-11-07 18:00","2020-11-07 14:00","2020-11-07 18:00","연속"]
[25,"남서울","영등포","신광명S/S 345kV CB 7572","신광명S/S 362kV GIS 보통점검(신광명-영등포#1)","- 차단기 개폐타임 측정 - 차단기 메커니즘 점검 - SF6가스 수분 및 SO2 측정 등.","2020-11-07 09:00","2020-11-07 14:00","2020-11-07 09:00","2020-11-07 14:00","연속"]
[26,"남서울","영등포","서서울신광명#2 T/L","추락방지시설 설치공사","추락방지시설 설치공사 345kV 서서울-신광명T/L 3, 14.1, 30호 수직, 수평 추락방지시설 설치","2020-11-06 08:00","2020-11-06 18:00","취소","취소","연속"]
[27,"남서울","영등포","신시흥신광명#2 T/L","추락방지시설 설치공사","추락방지시설 설치공사 345kV 신시흥-신광명T/L No.5,11,12,13호 수직, 수평 추락방지시설 설치","2020-11-10 08:00","2020-11-10 18:00","2020-11-24 08:00","2020-11-24 18:00","연속"]
[28,"남서울","영등포","신광명S/S 345kV #70 BUS","345kV 신광명S/S GIS 용량대체 및 S/W 증설","- 신광명 345kV GIS 24CCT 설치(63kA)","2020-11-25 10:00","2020-11-28 10:00","취소","취소","연속"]
[29,"남서울","영등포","서서울신광명#1 T/L","345kV 신광명S/S GIS 용량대체 및 S/W 증설","- 신광명 345kV GIS 24CCT 설치(63kA)","2020-11-28 10:00","2020-11-29 10:00","취소","취소","연속"]
[30,"남서울","영등포","신광명S/S 345kV #75 BUS","345kV 신광명S/S GIS 용량대체 및 S/W 증설","- 신광명 345kV GIS 24CCT 설치(63kA)","2020-11-29 10:00","2020-12-02 10:00","취소","취소","연속"]
[31,"남서울","영등포","서서울신광명#1 T/L","추락방지시설 설치공사","추락방지시설 설치공사 345kV 서서울-신광명T/L 3, 14.1, 30호 수직, 수평 추락방지시설 설치","2020-11-05 08:00","2020-11-05 18:00","취소","취소","연속"]
[32,"인천","김포","신김포신인천CC T/L","345kV 신김포-신인천CC T/L 잔여 접속함 해체점검","공사대상 : (1B) J/B#1,3,4-1,7 / (2B) J/B#1,2,4-1,7 공사내용 : 접속함 해체점검","2020-11-26 08:00","2020-11-28 20:00","2020-11-26 08:00","2020-11-28 20:00","연속"]
[33,"인천","김포","신김포S/S 345kV CB 7171","신김포S/S 345kV 7171 GIS CB 성능개선 공사","신김포S/S 345kV 7171 GIS CB 성능개선 공사(Main & Inner Nozzle 재질변경)","2020-11-02 09:00","2020-11-04 14:00","2020-11-02 09:00","2020-11-04 14:00","연속"]
[34,"인천","김포","신김포S/S 345kV CB 7100","신김포S/S 345kV 7100 GIS CB 성능개선 공사","신김포S/S 345kV 7100 GIS CB 성능개선 공사(Main & Inner Nozzle 재질변경)","2020-11-04 14:00","2020-11-06 18:00","2020-11-04 14:00","2020-11-06 18:00","연속"]
[35,"인천","김포","신김포S/S 345kV CB 7271","신김포S/S 345kV 7271 GIS CB 성능개선 공사","신김포S/S 345kV 7271 GIS CB 성능개선 공사(Main & Inner Nozzle 재질변경)","2020-11-09 09:00","2020-11-11 14:00","2020-11-09 09:00","2020-11-11 14:00","연속"]
[36,"인천","김포","신김포S/S 345kV CB 7600","신김포S/S 345kV 7600 GIS CB 성능개선 공사","신김포S/S 345kV 7600 GIS CB 성능개선 공사(Main & Inner Nozzle 재질변경)","2020-11-23 09:00","2020-11-25 14:00","2020-11-23 09:00","2020-11-25 14:00","연속"]
[37,"인천","김포","신김포S/S #2 M.Tr","신김포S/S 345kV #2M.Tr 3차측 GIS 보통점검","○ 신김포S/S 345kV #2M.Tr 3차측 GIS 보통점검 ○ 신김포S/S 23kV #2S.Tr 보통점검","2020-11-10 10:00","2020-11-10 18:00","2020-11-10 10:00","2020-11-10 18:00","연속"]
[38,"인천","김포","신김포S/S 345kV CB 7200","신김포S/S 345kV 7200 GIS CB 성능개선 공사","신김포S/S 345kV 7200 GIS CB 성능개선 공사(Main & Inner Nozzle 재질변경)","2020-11-11 14:00","2020-11-13 18:00","2020-11-11 14:00","2020-11-13 18:00","연속"]
[39,"인천","김포","신김포S/S 345kV CB 7272","신김포S/S 345kV 7272 GIS CB 성능개선 공사","신김포S/S 345kV 7272 GIS CB 성능개선 공사(Main & Inner Nozzle 재질변경)","2020-11-16 09:00","2020-11-18 14:00","2020-11-16 09:00","2020-11-18 14:00","연속"]
[40,"인천","김포","신김포S/S 345kV CB 7671","신김포S/S 345kV 7671 GIS CB 성능개선 공사","신김포S/S 345kV 7671 GIS CB 성능개선 공사(Main & Inner Nozzle 재질변경)","2020-11-18 14:00","2020-11-20 18:00","2020-11-18 14:00","2020-11-20 18:00","연속"]
[41,"인천","김포","신김포S/S #1 M.Tr","신김포S/S 345kV #1M.Tr 3차측 GIS 보통점검","○ 신김포S/S 345kV #1M.Tr 3차측 GIS 보통점검 ○ 신김포S/S 23kV #1S.Tr 보통점검","2020-11-09 10:00","2020-11-09 18:00","2020-11-09 10:00","2020-11-09 18:00","연속"]
[42,"인천","부평","서인천C/C #4 Tie-Tr","서인천복합S/Y 345kV #4M.Tr 보통점검 공사","서인천복합S/Y 345kV #4M.Tr 보통점검 공사","2020-11-09 09:00","2020-11-10 18:00","2020-11-09 09:00","2020-11-10 18:00","연속"]
[43,"인천","부평","신가좌S/S 154kV #61 BUS","신가좌S/S 362kV 용량부족 GIS 교체공사","-신가좌S/S 362kV 용량부족 GIS 교체공사 -실부하가압 관련 앵글 측정","2020-11-25 16:00","2020-11-25 18:00","취소","취소","연속"]
[44,"인천","부평","신가좌S/S 345kV CB 7600","신가좌S/S 362kV 용량부족 GIS 교체공사","-신가좌S/S 362kV 용량부족 GIS 교체공사 -345㎸ #75BUS 무부하 가압용 (24H)","2020-11-08 10:00","2020-11-09 10:00","2020-11-08 10:00","2020-11-09 10:00","연속"]
[45,"인천","부평","신가좌S/S 345kV #1 BUS","신가좌S/S 362kV 용량부족 GIS 교체공사","-신가좌S/S 362kV 용량부족 GIS 교체공사 -실부하가압 관련 앵글 측정","2020-11-20 14:00","2020-11-20 16:00","2020-11-20 14:00","2020-11-20 16:00","연속"]
[46,"인천","부평","신가좌S/S 345kV #2 BUS","신가좌S/S 362kV 용량부족 GIS 교체공사","-신가좌S/S 362kV 용량부족 GIS 교체공사 -실부하가압 관련 앵글 측정","2020-11-25 16:00","2020-11-25 18:00","2020-11-25 16:00","2020-11-25 18:00","연속"]
[47,"인천","부평","신가좌S/S 345kV CB 7600","신가좌S/S 362kV 용량부족 GIS 교체공사","-신가좌S/S 362kV 용량부족 GIS 교체공사 -345㎸ #75BUS 무부하 가압용 (24H)","2020-10-31 10:00","2020-11-01 10:00","2020-10-31 10:00","2020-11-01 10:00","연속"]
[48,"인천","부평","인천C/C 345kV #75 BUS","인천복합S/Y #75BUS 모선보호반 교체 공사","인천복합S/Y #75BUS 모선보호반 교체 공사","2020-11-16 09:00","2020-11-20 18:00","2020-11-16 09:00","2020-11-20 18:00","연속"]
[49,"인천","부평","인천C/C 345kV #70 BUS","인천복합S/Y #70BUS 모선보호반 교체 공사","인천복합S/Y #70BUS 모선보호반 교체 공사","2020-11-09 09:00","2020-11-13 18:00","2020-11-26 09:00","2020-12-02 18:00","연속"]
[50,"인천","부평","인천C/C #2 Tie-Tr","인천복합S/Y #2S.Tr GIS 누기보수 공사","인천복합S/Y #2S.Tr GIS 누기보수 공사","2020-11-02 09:00","2020-11-03 18:00","2020-11-02 09:00","2020-11-03 18:00","연속"]
[51,"인천","시흥","신시흥신광명#1 T/L","345kV 신시흥-신광명 #1T/L 과열개소 정비","345kV 신시흥-신광명 #1T/L 과열개소 정비 No.52.99","2020-11-10 08:00","2020-11-10 18:00","취소","취소","연속"]
[52,"인천","직할","갈산S/S 345kV #75 BUS","345kV 갈산S/S Sh.R 증설","345kV 3CB 증설","2020-11-23 09:00","2020-11-27 18:00","2020-11-23 09:00","2020-11-27 18:00","연속"]
[53,"인천","직할","갈산S/S 345kV #70 BUS","345kV 갈산S/S Sh.R 증설","345kV 3CB 증설","2020-11-16 09:00","2020-11-20 18:00","2020-11-16 09:00","2020-11-20 18:00","연속"]
[54,"인천","직할","서인천CC신부평#3 T/L","345kV 서인천CC-신부평 등 2개T/L 절연유 채취밸브 설치공사","[345kV 서인천CC-신부평 등 2개T/L 절연유 채취밸브 설치공사] - 대상선로 : 서인천CC-신부평#1,2,3,4T/L, 신가좌-부개#1,2T/L","2020-11-02 09:00","2020-11-11 18:00","2020-11-02 09:00","2020-11-11 18:00","연속"]
[55,"인천","직할","서인천CC신부평#4 T/L","345kV 서인천CC-신부평 등 2개T/L 절연유 채취밸브 설치공사","[345kV 서인천CC-신부평 등 2개T/L 절연유 채취밸브 설치공사] - 대상선로 : 서인천CC-신부평#1,2,3,4T/L, 신가좌-부개#1,2T/L","2020-11-28 09:00","2020-11-29 18:00","취소","취소","연속"]
[56,"인천","직할","서인천CC신부평#2 T/L","345kV 서인천CC-신부평 등 2개T/L 절연유 채취밸브 설치공사","[345kV 서인천CC-신부평 등 2개T/L 절연유 채취밸브 설치공사] - 대상선로 : 서인천CC-신부평#1,2,3,4T/L, 신가좌-부개#1,2T/L","2020-11-13 09:00","2020-11-22 18:00","2020-11-13 09:00","2020-11-22 18:00","연속"]
[57,"경기북부","고양","신덕은S/S #1 M.Tr","345kV 신덕은S/S 종합 예방진단시스템 설치공사","○ DGA 설치 ○ OLTC UHF 센서 설치 ○ OLTC 진단장치 설치","2020-11-10 09:00","2020-11-13 18:00","2020-11-10 09:00","2020-11-13 18:00","연속"]
[58,"경기북부","고양","신파주신덕은#1 T/L","'20~'21년 고양전력지사 변전정비회사 총액공사","71BAY B/F 반 교체공사","2020-11-10 09:00","2020-11-13 18:00","2020-11-10 09:00","2020-11-13 18:00","연속"]
[59,"경기북부","고양","신덕은S/S #4 M.Tr","345kV 신덕은S/S 종합 예방진단시스템 설치공사","○ DGA 설치 ○ OLTC UHF 센서 설치 ○ OLTC 진단장치 설치","2020-11-25 09:00","2020-11-26 18:00","2020-11-25 09:00","2020-11-26 18:00","연속"]
[60,"경기북부","고양","신덕은S/S #2 M.Tr","345kV 신덕은S/S 종합 예방진단시스템 설치공사","○ DGA 설치 ○ OLTC UHF 센서 설치 ○ OLTC 진단장치 설치","2020-11-17 09:00","2020-11-20 18:00","2020-11-17 09:00","2020-11-20 18:00","연속"]
[61,"경기북부","고양","신파주신덕은#2 T/L","'20~'21년 고양전력지사 변전정비회사 총액공사","72BAY B/F 반 교체공사","2020-11-17 09:00","2020-11-20 18:00","2020-11-17 09:00","2020-11-20 18:00","연속"]
[62,"경기북부","고양","신덕은S/S #3 M.Tr","345kV 신덕은S/S 종합 예방진단시스템 설치공사","○ DGA 설치 ○ OLTC UHF 센서 설치 ○ OLTC 진단장치 설치","2020-11-23 09:00","2020-11-24 18:00","2020-11-23 09:00","2020-11-24 18:00","연속"]
[63,"경기북부","고양","신파주S/S 345kV SEC CB 70710","362kV GIS 보통점검-변전총액공사","70-71 GIS 보통점검","2020-11-26 09:00","2020-11-26 18:00","2020-11-26 09:00","2020-11-26 18:00","연속"]
[64,"경기북부","고양","신파주S/S 345kV SEC CB 75760","362kV GIS 보통점검-변전총액공사","75-76 GIS 보통점검","2020-11-27 09:00","2020-11-27 18:00","2020-11-27 09:00","2020-11-27 18:00","연속"]
[65,"경기북부","구리","미금S/S #3 M.Tr","'20~21 구리전력 변전정비 총액공사","미금S/S 345kV #3M.Tr 1,2차 GIS 조작시험, 전자변교체 피뢰기 보통점검","2020-11-19 09:00","2020-11-20 18:00","2020-11-09 09:00","2020-11-10 18:00","연속"]
[66,"경기북부","구리","미금S/S STATCOM CB","미금S/S STATCOM 냉각설비 점검공사","미금S/S STATCOM 냉각설비 점검공사 HMI 교체공사","2020-11-30 09:00","2020-12-07 18:00","2020-11-30 09:00","2020-12-07 18:00","연속"]
[67,"경기북부","구리","미금S/S 345kV #6 Sh.R","'20~21년 구리전력 변전정비 총액공사","미금S/S 345kV #6Sh.R GIS 조작시험","2020-11-11 09:00","2020-11-11 18:00","2020-11-11 09:00","2020-11-11 18:00","연속"]
[68,"경기북부","구리","미금S/S 345kV #5 Sh.R","'20~21년 구리전력 변전정비 총액공사","미금S/S 345kV #5Sh.R GIS 조작시험","2020-11-10 09:00","2020-11-10 18:00","2020-11-10 09:00","2020-11-10 18:00","연속"]
[69,"경기북부","구리","미금S/S 345kV #1 Sh.R","'20~21년 구리전력 변전정비 총액공사","미금S/S 345kV #1Sh.R GIS 조작시험","2020-11-09 09:00","2020-11-09 18:00","2020-11-09 09:00","2020-11-09 18:00","연속"]
[70,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 362kV GIS PT 대체공사","- 미금-성동#1T/L 인출PT 대체 - #1M.Tr 인출PT 대체 - 기타 부대공사 1식","2020-11-09 09:00","2020-11-18 18:00","취소","취소","연속"]
[71,"경기북부","구리","미금성동#1 T/L","미금S/S 362kV GIS PT 대체공사","- 미금-성동#1T/L 인출PT 대체 - #1M.Tr 인출PT 대체 - 기타 부대공사 1식","2020-11-09 09:00","2020-11-18 18:00","취소","취소","연속"]
[72,"경기북부","구리","신의정부미금#2 T/L","2020년 가공송전선로 순시점검 위탁공사","현수애자 절연저항측정 상단병가선로","2020-11-02 08:00","2020-11-02 12:00","2020-11-02 08:00","2020-11-02 12:00","연속"]
[73,"경기북부","구리","신의정부미금#1 T/L","2020년 가공송전선로 순시점검 위탁공사","현수애자 절연저항측정 상단병가선로","2020-11-02 12:00","2020-11-02 17:00","2020-11-02 12:00","2020-11-02 17:00","연속"]
[74,"경기북부","구리","신가평신의정부#2 T/L","2020년 가공송전선로 순시점검 위탁공사","현수애자 절연저항측정","2020-11-02 12:00","2020-11-02 17:00","2020-11-02 12:00","2020-11-02 17:00","연속"]
[75,"경기북부","구리","신가평신의정부#1 T/L","2020년 가공송전선로 순시점검 위탁공사","현수애자 절연저항측정","2020-11-02 08:00","2020-11-02 12:00","2020-11-02 08:00","2020-11-02 12:00","연속"]
[76,"경기북부","구리","신가평미금#1 T/L","20-21년 구리전력지사 변전정비회사 총액공사","○ 장기사용 배전반 교체공사 - 345kV 신가평-미금#1T/L보호반 교체","2020-11-04 09:00","2020-11-13 18:00","2020-11-04 09:00","2020-11-13 18:00","연속"]
[77,"경기북부","구리","신가평포천LNGCC#1 T/L","20-21년 구리전력지사 변전정비회사 총액공사","○ 장기사용 배전반 교체공사 - 신가평S/S 345kV #74BAY B/F보호반 교체","2020-11-16 09:00","2020-11-20 18:00","2020-11-16 09:00","2020-11-20 18:00","연속"]
[78,"경기북부","구리","신가평S/S 345kV #3 Sh.R","20-21년 구리전력지사 변전정비회사 총액공사","○ 장기사용 배전반 교체공사 - 신가평S/S 345kV #74BAY B/F보호반 교체","2020-11-16 09:00","2020-11-20 18:00","2020-11-16 09:00","2020-11-20 18:00","연속"]
[79,"경기북부","구리","신가평S/S 345kV #4 Sh.R","20-21년 구리전력지사 변전정비회사 총액공사","○ 장기사용 배전반 교체공사 - 신가평S/S 345kV #76BAY B/F보호반 교체","2020-11-23 09:00","2020-11-27 18:00","2020-11-23 09:00","2020-11-27 18:00","연속"]
[80,"경기북부","구리","신가평신의정부#1 T/L","20-21년 구리전력지사 변전정비회사 총액공사","○ 장기사용 배전반 교체공사 - 신가평S/S 345kV #76BAY B/F보호반 교체","2020-11-23 09:00","2020-11-27 18:00","2020-11-23 09:00","2020-11-27 18:00","연속"]
[81,"경기북부","구리","신포천S/S #3 M.Tr","신포천SS #2M.Tr 부싱절연유 채유","신포천SS #2M.Tr 부싱절연유 채유","2020-11-16 14:00","2020-11-16 18:00","취소","취소","연속"]
[82,"경기북부","구리","신포천S/S #2 M.Tr","신포천SS #2M.Tr 부싱절연유 채유","신포천SS #2M.Tr 부싱절연유 채유","2020-11-16 09:00","2020-11-16 14:00","취소","취소","연속"]
[83,"경기북부","구리","신가평포천LNGCC#2 T/L","구리전력지사 345kV GIS 보통점검","구리전력지사 345kV GIS 보통점검","2020-11-04 09:00","2020-11-04 18:00","취소","취소","연속"]
[84,"경기북부","직할","신포천동두천CC#2 T/L","가보제 송전선로 보호반 성능개선 공사","- 재폐로 진행중 고장 재발시 3상 최종 Trip - 최종 Trip 신호 발생시 재폐로 신호 Reset","2020-11-10 09:00","2020-11-10 18:00","2020-11-10 09:00","2020-11-10 18:00","연속"]
[85,"경기북부","직할","신덕은동두천CC#1 T/L","2020년 가공송전선로 순시점검 위탁공사","피뢰기 특별점검 상단병가선로","2020-11-13 08:00","2020-11-20 18:00","2020-11-13 08:00","2020-11-20 18:00","매일"]
[86,"경기북부","직할","신의정부S/S 345kV #2 Sh.R","20~21년도 경기북부 직할 변전정비회사 총액공사","신의정부S/S #2 Sh.R 보호배전반 교체공사","2020-11-23 09:00","2020-11-27 18:00","2020-11-23 09:00","2020-11-27 18:00","연속"]
[87,"경기북부","직할","신의정부S/S #2 M.Tr","신의정부S/S 효성제 GIS 하자보수공사","#2 M.Tr 2차측 발청보수","2020-11-06 09:00","2020-11-10 18:00","2020-11-06 09:00","2020-11-10 18:00","연속"]
[88,"경기북부","직할","신의정부S/S 345kV #1 Sh.R","신의정부S/S 효성제 GIS 하자보수공사","#1 Sh.R 측 DS, ES 제어케이블 경로변경","2020-11-13 09:00","2020-11-13 18:00","2020-11-13 09:00","2020-11-13 18:00","연속"]
[89,"경기북부","직할","양주S/S #1 M.Tr","양주변전소 옥외철구 GIS화 공사","감시제어 시스템 이설(모자이크→SA)","2020-11-02 09:00","2020-11-08 18:00","2020-11-04 09:00","2020-11-11 18:00","연속"]
[90,"경기북부","직할","양주중부#1 T/L","20-21년도 가공송전 정비회사 총액공사","ㅇ 96년도 상반기 이전 고려애자 교체","2020-11-12 07:00","2020-11-12 18:00","취소","취소","연속"]
[91,"경기북부","직할","양주S/S #1 M.Tr","양주S/S 154kV 인출T/L 지중화공사","상시험 및 무부하가압용","2020-11-14 09:00","2020-11-15 18:00","2020-11-14 09:00","2020-11-15 18:00","연속"]
[92,"경기북부","직할","신의정부양주#1 T/L","양주변전소 옥외철구 GIS화 공사","감시제어 시스템 이설(모자이크→SA)","2020-11-09 09:00","2020-11-16 18:00","2020-11-09 09:00","2020-11-16 18:00","연속"]
[93,"경기북부","직할","신의정부양주#2 T/L","양주변전소 옥외철구 GIS화 공사","감시제어 시스템 이설(모자이크→SA)","2020-11-02 09:00","2020-11-08 18:00","2020-11-02 09:00","2020-11-08 18:00","연속"]
[94,"경기북부","직할","양주S/S #4 M.Tr","양주변전소 옥외철구 GIS화 공사","감시제어 시스템 이설(모자이크→SA)","2020-11-09 09:00","2020-11-16 18:00","2020-11-09 09:00","2020-11-15 18:00","연속"]
[95,"경기북부","구리","동서울미금#1 T/L","20-21년 구리전력지사 변전정비회사 총액공사","장기사용 배전반 교체공사 - 345kV #73BAY B/F반 교체 ","2020-11-02 09:00","2020-11-06 18:00","취소","취소","연속"]
[96,"경기","군포","서서울#2S/S #6 M.Tr","서서울#2S/S #6 M.Tr 1차측 CVT설치","서서울#2S/S #6 M.Tr 1차측 CVT설치","2020-11-21 09:00","2020-11-22 18:00","2020-11-21 09:00","2020-11-22 18:00","연속"]
[97,"경기","군포","서서울#2S/S #5 M.Tr","서서울#2S/S #5 M.Tr 1차측 CVT설치","서서울#2S/S #5 M.Tr 1차측 CVT설치","2020-11-14 09:00","2020-11-15 18:00","2020-11-14 09:00","2020-11-15 18:00","연속"]
[98,"경기","군포","서서울신광명#1 T/L","서서울-신광명#1T/L 보호반 대체 공사","서서울-신광명#1T/L 보호반 대체 공사","2020-11-09 09:00","2020-11-13 18:00","2020-11-09 09:00","2020-11-13 18:00","연속"]
[99,"경기","군포","서서울신광명#2 T/L","서서울-신광명#2T/L 보호반 대체 공사","서서울-신광명#2T/L 보호반 대체 공사","2020-11-16 09:00","2020-11-20 18:00","2020-11-16 09:00","2020-11-20 18:00","연속"]
[100,"경기","군포","신안산S/S #3 M.Tr","신안산S/S #3M.Tr 보호배전반 대체공사","신안산S/S #3M.Tr 보호배전반 대체공사, 7271, 7200 GIS 초기점검","2020-11-30 09:00","2020-12-04 18:00","2020-11-30 09:00","2020-12-04 18:00","연속"]
[101,"경기","동부","곤지암신충주#1 T/L","2020~2021년 성남전력지사 송전정비회사 총액공사","- 345kV 곤지암-신충주T/L 압축인류크램프 보수","2020-11-05 08:00","2020-11-05 18:00","2020-11-05 08:00","2020-11-05 18:00","연속"]
[102,"경기","성남","신성남S/S #5 M.Tr","20년 성남전력 변전정비회사 총액공사","- 7672(조작), 전자변교체 - 2차측 GIS (조작), 전자변교체 - 3차측 GIS (대체)","2020-11-05 09:00","2020-11-06 18:00","2020-11-05 09:00","2020-11-06 18:00","연속"]
[103,"경기","성남","서서울#2신성남#2 T/L","서서울2-신성남 스페이서 간격조정","서서울2-신성남 스페이서 간격조정 - 1806개, 38경간","2020-11-05 08:00","2020-11-07 18:00","2020-11-05 08:00","2020-11-07 18:00","연속"]
[104,"경기","성남","신성남S/S STATCOM CB","STATCOM 보통점검","STATCOM 보통점검","2020-11-09 09:00","2020-11-20 18:00","2020-11-09 09:00","2020-11-20 18:00","연속"]
[105,"경기","성남","신성남동서울#1 T/L","20년 성남전력지사 변전정비회사 총액공사","- 7471,7400(보통),전자변교체 - LA(보통 - 가보제 재페로성능개선","2020-11-16 09:00","2020-11-17 18:00","2020-11-16 09:00","2020-11-17 18:00","연속"]
[106,"경기","성남","신성남S/S 345kV CB 7371","20년 성남전력지사 변전정비회사 총액공사","B상 단독 전자변교체","2020-11-19 09:00","2020-11-19 18:00","2020-11-19 09:00","2020-11-19 18:00","연속"]
[107,"경기","성남","서서울#2신성남#1 T/L","서서울2-신성남 스페이서 간격조정","서서울2-신성남 스페이서 간격조정 - 1806개, 38경간","2020-11-02 08:00","2020-11-04 18:00","2020-11-02 08:00","2020-11-04 18:00","연속"]
[108,"경기","성남","신수원S/S #3 M.Tr","20년 성남전력 변전정비회사 총액공사","보호반대체","2020-11-02 09:00","2020-11-06 18:00","2020-11-02 09:00","2020-11-02 18:00","연속"]
[109,"경기","성남","신용인신수원 T/L","20년 성남전력지사 변전정비회사 총액공사","영인기술제 성능개선","2020-11-25 09:00","2020-11-25 18:00","2020-11-25 09:00","2020-11-25 18:00","연속"]
[110,"경기","성남","신안성신수원#1 T/L","20년 성남전력지사 변전정비회사 총액공사","영인기술제 성능개선","2020-11-26 09:00","2020-11-26 18:00","2020-11-26 09:00","2020-11-26 18:00","연속"]
[111,"경기","성남","신수원S/S 345kV #2 BUS","신수원S/S 345kV 용량부족GIS 대체","- GIS 대체 * 3대","2020-11-28 10:00","2020-11-29 10:00","2020-11-28 10:00","2020-11-29 10:00","연속"]
[112,"경기","성남","신안성신수원#2 T/L","신수원S/S 345kV 용량부족GIS 대체","- GIS 대체 * 3대","2020-11-28 10:00","2020-11-29 10:00","2020-11-28 10:00","2020-11-29 10:00","연속"]
[113,"경기","성남","신안성신성남#1 T/L","345kV 신안성-신용인#1T/L OPGW 항공장애표시구 정비공사","신안성-신용인#1T/L OPGW 항공장애표시구 정비공사 관련 안전이격 확보","2020-11-09 09:00","2020-11-13 18:00","2020-11-09 09:00","2020-11-13 18:00","연속"]
[114,"경기","성남","신안성S/S 345kV #7 Sh.R","20년 성남전력지사 변전정비회사 총액공사","FEEDER GIS 전자변교체 보호반대체","2020-11-09 14:00","2020-11-09 18:00","2020-11-09 14:00","2020-11-09 18:00","연속"]
[115,"경기","성남","신안성신성남#2 T/L","345kV 신용인-동서울T/L 지장철탑 이설공사(서울세종)","345kV 신용인-동서울T/L 7-1호 지장철탑 이설(요청자 시행 공사) - 교체구간 : 0.7km, 4회선 1기 본선로, 1기 임시선로 - 345kV 신안성-신성남T/L 64-1호 병가구간","2020-11-25 09:00","2020-12-08 18:00","2020-11-25 09:00","2020-12-08 18:00","연속"]
[116,"경기","성남","신안성신용인#1 T/L","345kV 신안성-신용인#1T/L OPGW 항공장애표시구 정비공사","항공장애표시구 풍소음 민원해소용 항공장애표시구 정비 - 철거 25개, 설치 39개","2020-11-09 09:00","2020-11-13 18:00","2020-11-09 09:00","2020-11-13 18:00","연속"]
[117,"경기","성남","신용인동서울#2 T/L","345kV 신용인-동서울T/L 지장철탑 이설공사(서울세종)","345kV 신용인-동서울T/L 7-1호 지장철탑 이설(요청자 시행 공사) - 교체구간 : 0.7km, 4회선 1기 본선로, 1기 임시선로 - 345kV 신안성-신성남T/L 64-1호 병가구간","2020-11-25 09:00","2020-12-08 18:00","2020-11-25 09:00","2020-12-08 18:00","연속"]
[118,"경기","성남","신용인S/S #2 M.Tr","20년 성남전력 변전정비회사 총액공사","96D 회로보완","2020-11-12 09:00","2020-11-12 18:00","2020-11-12 09:00","2020-11-12 18:00","연속"]
[119,"경기","직할","화성서서울#1 T/L","봉담-송산간 2공구 도로개설 관련 지장이설공사","345kV 화성-서서울T/L 18~23호 본철탑 2기 설치","2020-11-30 07:00","2020-12-08 18:00","2020-11-30 07:00","2020-12-08 18:00","연속"]
[120,"경기","직할","화성서서울#2 T/L","봉담-송산간 2공구 도로개설 관련 지장이설공사","345kV 화성-서서울T/L 18~23호 본철탑 2기 설치","2020-11-19 07:00","2020-11-29 18:00","2020-11-19 07:00","2020-11-29 18:00","연속"]
[121,"경기","직할","화성S/S #3 M.Tr","20년 직할 345kV 주변압기 정밀점검공사","화성S/S 345kV #3M.Tr 정밀점검 시행","2020-11-09 09:00","2020-11-18 18:00","2020-11-09 09:00","2020-11-18 18:00","연속"]
[122,"경기","직할","화성신안산#1 T/L","봉담-송산간 2공구 도로개설 관련 지장이설공사","345kV 화성-신안산T/L 16호~20호 본철탑 2기","2020-11-08 07:00","2020-11-17 18:00","2020-11-08 07:00","2020-11-17 18:00","연속"]
[123,"경기","평택","고덕S/S 345kV CB 7300","고덕S/S 345kV #1 M.Tr 1차 TIE CB C상 유압펌프 보수","고덕S/S 345kV #1 M.Tr 1차 TIE CB C상 유압펌프 보수","2020-11-04 10:00","2020-11-04 18:00","2020-11-04 10:00","2020-11-04 18:00","연속"]
[124,"경기","평택","서안성S/S #4 M.Tr","서안성S/S 63kA GIS 외장형 CVT 설치","- 외장형 CVT 설치 × 4조(#1,2,3,4M.Tr)","2020-11-23 09:00","2020-11-25 09:00","2020-11-23 09:00","2020-11-25 09:00","연속"]
[125,"경기","평택","서안성S/S #3 M.Tr","서안성S/S 345kV #3M.Tr 변압기 보통점검","서안성S/S 345kV #3M.Tr 변압기 보통점검 / 1,2차 붓싱절연유 채유","2020-11-16 10:00","2020-11-18 18:00","2020-11-16 10:00","2020-11-18 18:00","연속"]
[126,"경기","평택","서안성S/S #1 M.Tr","서안성S/S 345kV #1 M.Tr 변압기 보통점검","서안성S/S 345kV #1 M.Tr 변압기 보통점검 / 1,2차 붓싱절연유 채유","2020-11-09 10:00","2020-11-11 18:00","2020-11-09 10:00","2020-11-11 18:00","연속"]
[127,"강원","강릉","신양양양양PP T/L","2020 변전협력회사 총액공사","○ 전위변성기, 피뢰기 보통점검","2020-11-10 10:00","2020-11-10 18:00","2020-11-10 10:00","2020-11-10 18:00","연속"]
[128,"강원","강릉","동해양양PP T/L","20-21년도 강릉전력지사 송전정비회사 총액공사","○ 점퍼선 교체공사 : 345kV 양양양수T/L No.19~175(16기)","2020-11-19 08:00","2020-11-30 18:00","2020-11-19 08:00","2020-11-30 18:00","매일"]
[129,"강원","동해","동해S/S 345kV CB 7572","2020년 동해전력 변전정비협력회사 총액공사","장기미동작 차단기 조작시험","2020-11-18 09:00","2020-11-18 18:00","2020-11-18 09:00","2020-11-18 18:00","연속"]
[130,"강원","동해","동해S/S 345kV CB 7471","2020년 동해전력 변전정비협력회사 총액공사","전자변 교체","2020-11-17 09:00","2020-11-17 18:00","취소","취소","연속"]
[131,"강원","동해","동해S/S 345kV CB 7372","2020년 동해전력 변전정비협력회사 총액공사","장기미동작 차단기 조작시험","2020-11-16 09:00","2020-11-16 18:00","2020-11-16 09:00","2020-11-16 18:00","연속"]
[132,"강원","동해","동해S/S 345kV CB 7300","2020년 동해전력 변전정비협력회사 총액공사","장기미동작 차단기 조작시험","2020-11-10 09:00","2020-11-10 18:00","2020-11-10 09:00","2020-11-10 18:00","연속"]
[133,"강원","동해","동해S/S 345kV CB 7172","2020년 동해전력 변전정비협력회사 총액공사","전자변 교체","2020-11-09 09:00","2020-11-09 18:00","2020-11-09 09:00","2020-11-09 18:00","연속"]
[134,"강원","동해","신제천동해#2 T/L","2020년 동해전력 변전정비협력회사 총액공사","1.LA 보통점검 2. PT 보통점검","2020-11-18 09:00","2020-11-18 18:00","취소","취소","연속"]
[135,"강원","동해","동해S/S 345kV CB 7400","2020년 동해전력 변전정비협력회사 총액공사","전자변 교체","2020-11-19 09:00","2020-11-19 18:00","취소","취소","연속"]
[136,"강원","동해","동해S/S 345kV CB 7472","2020년 동해전력 변전정비협력회사 총액공사","전자변 교체","2020-11-20 09:00","2020-11-20 18:00","2020-11-17 09:00","2020-11-17 18:00","연속"]
[137,"강원","동해","동해S/S STATCOM CB","동해S/S 345kV STATCOM 냉각설비 초기점검","1. STATCOM 냉각설비 초기점검 2. M.Tr 초기점검 3. M.Tr 1차 LA 초기점검 4. M.Tr 보호반 보통점검 5. GIS 초기검검[77BAY TIE 포함] 6. S.Tr 초기점검 7. S.Tr CB 초기점검, 8. S.Tr DS 초기점검","2020-11-02 09:00","2020-11-06 18:00","2020-11-02 09:00","2020-11-06 18:00","연속"]
[138,"강원","동해","북평T/P 345kV CB 7200","2020년 동해전력 변전정비협력회사 총액공사","GIS 보통점검","2020-11-12 09:00","2020-11-12 18:00","2020-11-12 09:00","2020-11-12 18:00","연속"]
[139,"강원","동해","북평T/P 345kV CB 7172","2020년 동해전력 변전정비협력회사 총액공사","장기미동작 차단기 조작시험","2020-11-06 10:00","2020-11-06 12:00","2020-11-06 10:00","2020-11-06 12:00","연속"]
[140,"강원","동해","북평T/P 345kV CB 7300","2020년 동해전력 변전정비협력회사 총액공사","GIS 보통점검","2020-11-13 13:00","2020-11-13 18:00","2020-11-13 13:00","2020-11-13 18:00","연속"]
[141,"강원","동해","북평T/P 345kV CB 7371","2020년 동해전력 변전정비협력회사 총액공사","GIS 보통점검","2020-11-13 09:00","2020-11-13 12:00","2020-11-13 09:00","2020-11-13 12:00","연속"]
[142,"강원","동해","북평T/P 345kV CB 7271","2020년 동해전력 변전정비협력회사 총액공사","GIS 보통점검","2020-11-12 09:00","2020-11-12 12:00","2020-11-12 09:00","2020-11-12 12:00","연속"]
[143,"강원","동해","북평T/P 345kV CB 7100","2020년 동해전력 변전정비협력회사 총액공사","GIS 보통점검","2020-11-11 13:00","2020-11-11 18:00","2020-11-11 13:00","2020-11-11 18:00","연속"]
[144,"강원","동해","북평T/P 345kV CB 7171","2020년 동해전력 변전정비협력회사 총액공사","GIS 보통점검","2020-11-11 09:00","2020-11-11 12:00","2020-11-11 09:00","2020-11-11 12:00","연속"]
[145,"강원","동해","북평T/P 345kV CB 7222","2020년 동해전력 변전정비협력회사 총액공사","장기미동작 차단기 조작시험","2020-11-06 13:00","2020-11-06 15:00","2020-11-06 13:00","2020-11-06 15:00","연속"]
[146,"강원","동해","삼척G/P 345kV CB 7572","2020년 동해전력 변전정비협력회사 총액공사","장기미동작 차단기 조작시험","2020-11-23 09:00","2020-11-23 18:00","2020-11-23 09:00","2020-11-23 18:00","연속"]
[147,"강원","태백","신태백한울NP#2 T/L","765kV 신태백S/S 345kV 용량부족차단기 대체 및 SW증설공사","- 345kV 신태백-한울NP2#2T/L 인출변경 - 345kV 신태백-한울NP2#2T/L 보호배전반 이설 - 345kV 76Bay GIS 대체","2020-11-09 09:00","2020-11-20 18:00","2020-11-10 09:00","2020-11-20 18:00","연속"]
[148,"충북","직할","신중부S/S 345kV #6 Sh.R","'20~21년 직할 변전정비회사 총액공사","765kV 신중부S/S 초기점검공사(#6Sh.R, 7C79, 7C71, 7C00)","2020-11-11 09:00","2020-11-13 18:00","2020-11-11 09:00","2020-11-13 18:00","연속"]
[149,"충북","직할","신진천S/S #3 M.Tr","'20~21년 직할 변전정비회사 총액공사","#3M.Tr 보통점검, 2차 GIS 보통점검, 부싱 절연유 채유, 1차 CVT 설치, 옥외 등기구 설치, 3차측 절연보강","2020-11-21 10:00","2020-11-22 18:00","2020-11-21 10:00","2020-11-22 18:00","연속"]
[150,"충북","청주","신중부남청주#2 T/L","345kV 신중부-남청주T/L No.60,61 안전이격확보공사","철탑 2기교체(가철탑 2기 신설,철거) / 전력선교체: 1.842km - #2T/L 기설철탑에서 본선로 이동","2020-11-16 07:00","2020-11-18 18:00","취소","취소","연속"]
[151,"충북","청주","남청주S/S #3 M.Tr","20-21년 청주전력 변전정비 총액공사","#3M.Tr 1차 GIS 보통점검","2020-11-07 09:00","2020-11-07 18:00","취소","취소","연속"]
[152,"충북","청주","남청주S/S #1 M.Tr","20-21년 청주전력 변전정비 총액공사","#1M.Tr 2차 GIS 보통점검","2020-11-08 09:00","2020-11-08 18:00","2020-11-14 09:00","2020-11-15 18:00","연속"]
[153,"충북","청주","신중부남청주#2 T/L","2020-2021년 청주전력지사 송전정비회사 총액공사","추락방지시설 설치 - No.35, 36","2020-11-08 08:00","2020-11-08 18:00","취소","취소","연속"]
[154,"충북","청주","세종남청주#2 T/L","2020-2021년 청주전력지사 송전정비회사 총액공사","항공도장 신옥천-세종#1 : 44, 49, 64, 68, 73호 (병가) 세종-남청주#2 : 9, 30호 애자교체 세종-남청주#2: 32, 46, 54, 55호","2020-11-05 08:00","2020-11-07 18:00","2020-11-16 08:00","2020-11-18 18:00","매일"]
[155,"충북","청주","신중부남청주#1 T/L","2020-2021년 청주전력지사 송전정비회사 총액공사","추락방지시설 설치 - No.35, 36","2020-11-07 08:00","2020-11-07 18:00","취소","취소","연속"]
[156,"충북","청주","세종남청주#1 T/L","2020-2021년 청주전력지사 송전정비회사 총액공사","- 항공도장 : No.9, 30, 45","2020-11-02 08:00","2020-11-04 18:00","2020-11-19 08:00","2020-11-21 18:00","매일"]
[157,"충북","청주","신중부남청주#1 T/L","345kV 신중부-남청주T/L No.60,61 안전이격확보공사","철탑 2기교체(가철탑 2기 신설,철거) / 전력선교체: 1.842km - 기설철탑 2기 철거, 신설철탑 2기 신설 - #1T/L 전력선 교체","2020-11-19 07:00","2020-12-13 18:00","취소","취소","연속"]
[158,"충북","청주","신옥천세종#1 T/L","2020-2021년 청주전력지사 송전정비회사 총액공사","항공도장 - No.44, 49, 64, 68, 73 불량애자 교체 - No.25, 61","2020-11-05 08:00","2020-11-07 18:00","2020-11-16 08:00","2020-11-18 18:00","매일"]
[159,"충북","청주","신옥천세종#2 T/L","2020-2021년 청주전력지사 송전정비회사 총액공사","항공도장 - No.49, 54, 73 불량애자 교체 - No.27, 29-1","2020-11-02 08:00","2020-11-04 18:00","2020-11-19 08:00","2020-11-21 18:00","매일"]
[160,"충북","충주","신제천S/S #2 M.Tr","20-21년 충주전력지사 변전정비 총액공사","신제천S/S #2M.Tr 1차 LA 교체 및 조류방지장치 설치","2020-11-19 10:00","2020-11-20 18:00","2020-11-19 10:00","2020-11-20 18:00","연속"]
[161,"충북","충주","신제천신영주#1 T/L","2020-2021년 송전정비회사 총액공사","추락방지장치 시범설치 (No.36,37,39,40)","2020-11-05 07:00","2020-11-06 18:00","2020-11-05 07:00","2020-11-06 18:00","매일"]
[162,"충북","충주","신제천S/S #3 M.Tr","20-21년 충주전력지사 변전정비 총액공사","주변압기 보통점검 및 1,2차 부싱절연유 채유 등","2020-11-09 09:30","2020-11-11 18:00","2020-11-09 09:30","2020-11-11 18:00","연속"]
[163,"충북","충주","신제천신영주#2 T/L","2020-2021년 송전정비회사 총액공사","추락방지장치 시범설치 (No.36,37,39,40) 철탑도장 (No.39,40)","2020-11-09 07:00","2020-11-09 18:00","2020-11-09 07:00","2020-11-09 18:00","매일"]
[164,"대전충남","대전","신옥천신계룡 T/L","신계룡S/S 345kV 72B/F PNL 교체 및 병행작업","신계룡S/S 345kV 72B/F PNL 교체 및 병행작업","2020-11-16 09:00","2020-11-20 18:00","2020-11-16 09:00","2020-11-20 18:00","연속"]
[165,"대전충남","대전","신계룡S/S #2 M.Tr","신계룡S/S #2M.Tr 부싱절연유(1차,2차) 채유 및 병행작업","신계룡S/S #2M.Tr 부싱절연유(1차,2차) 채유 및 병행작업","2020-11-20 09:00","2020-11-20 18:00","2020-11-20 09:00","2020-11-20 18:00","연속"]
[166,"대전충남","대전","신계룡S/S #1 M.Tr","신계룡S/S 345kV 72B/F PNL 교체 및 병행작업","신계룡S/S 345kV 72B/F PNL 교체 및 병행작업","2020-11-16 09:00","2020-11-20 18:00","2020-11-16 09:00","2020-11-20 18:00","연속"]
[167,"대전충남","대전","신계룡청양 T/L","154kV 신계룡-두마T/L OPGW 증설공사","신계룡S/S ~ 두마S/S 간 가공지선(ACSR 97SQ)를 OPGW/100SQ로 변경","2020-11-16 07:00","2020-11-19 18:00","2020-11-16 07:00","2020-11-19 18:00","연속"]
[168,"대전충남","서산","신당진개폐소태안TP#2 T/L","20년 서산P/O 변전정비 총액공사","태안화력S/S 개폐소-태안TP#2 T/L CVT 보통점검 신당진S/S 개폐소-태안TP#2 T/L CVT 보통점검","2020-11-11 10:00","2020-11-11 18:00","2020-11-11 10:00","2020-11-11 18:00","연속"]
[169,"대전충남","서산","신서산S/S 345kV CB 7A00","20년 서산P/O 345kV GIS정밀점검공사","신서산S/S 345kV 신서산-아산#2T/L TIE (7A00) GIS 정밀점검","2020-11-02 10:00","2020-11-06 18:00","2020-11-02 10:00","2020-11-06 18:00","연속"]
[170,"대전충남","서산","신서산S/S 345kV CB 7A72","20년 서산P/O 345kV GIS정밀점검공사","신서산S/S 345kV 신서산-아산#2T/L 1차 (7A72) GIS 정밀점검","2020-11-09 10:00","2020-11-13 18:00","2020-11-09 10:00","2020-11-13 18:00","연속"]
[171,"대전충남","서산","신서산S/S 345kV CB 7571","20년 서산P/O 변전정비회사 총액공사","신서산S/S 345kV 7579 CB 전자변교체","2020-11-05 10:00","2020-11-06 18:00","2020-11-05 10:00","2020-11-06 18:00","연속"]
[172,"대전충남","서산","태안T/P #2 M.Tr","20년 서산P/O 변전정비 총액공사","태안화력S/S 345kV #2M.Tr 초기점검(1차,2차 LA, 1차(7771),2차(6244),3차(4279) GIS, #2S.Tr)","2020-11-02 10:00","2020-11-06 18:00","2020-11-02 10:00","2020-11-06 18:00","연속"]
[173,"대전충남","세종","세종S/S #2 M.Tr","[변전]세종PO 변전정비회사 총액공사","장기미동작 차단기 동작시험","2020-11-03 09:00","2020-11-03 18:00","2020-11-03 09:00","2020-11-03 18:00","연속"]
[174,"대전충남","세종","세종S/S #3 M.Tr","[변전]세종PO 변전정비회사 총액공사","장기미동작 차단기 동작시험","2020-11-04 09:00","2020-11-04 18:00","2020-11-04 09:00","2020-11-04 18:00","연속"]
[175,"대전충남","아산","청양신온양#2 T/L","[송전]345kV청양-신온양#2T/L 정밀점검","345kV청양-신온양#2T/L 84~116, 122~144, 145~149호 정밀점검","2020-11-05 08:00","2020-11-07 18:00","2020-11-05 08:00","2020-11-07 18:00","매일"]
[176,"대전충남","아산","신온양S/S #4 M.Tr","신온양S/S 345kV #4M.Tr 2차 GIS 보통점검","신온양S/S 345kV #4M.Tr 2차 GIS 보통점검","2020-11-17 09:00","2020-11-17 18:00","2020-11-17 09:00","2020-11-17 18:00","연속"]
[177,"대전충남","아산","청양신온양#2 T/L","345kV 북당진-신탕정T/L OPGW 시설공사(2구간)","345kV 청양-신온양 #2T/L No.146~147 항공구 5식 교체","2020-11-15 07:00","2020-11-15 18:00","2020-11-15 07:00","2020-11-15 18:00","연속"]
[178,"대전충남","아산","신온양S/S #3 M.Tr","신온양S/S 345kV #3M.Tr 2차 GIS 보통점검","신온양S/S 345kV #3M.Tr 2차 GIS 보통점검","2020-11-16 09:00","2020-11-16 18:00","2020-11-16 09:00","2020-11-16 18:00","연속"]
[179,"대전충남","아산","신탕정S/S 345kV CB 7171","신탕정S/S 345kV 7171, 7271 GIS 하자점검","신탕정S/S 345kV 7171, 7271 GIS 하자점검","2020-11-09 09:00","2020-11-09 13:00","2020-11-09 09:00","2020-11-09 13:00","연속"]
[180,"대전충남","아산","신탕정S/S 345kV CB 7271","신탕정S/S 345kV 7171, 7271 GIS 하자점검","신탕정S/S 345kV 7171, 7271 GIS 하자점검","2020-11-09 13:00","2020-11-09 18:00","2020-11-09 13:00","2020-11-09 18:00","연속"]
[181,"대전충남","아산","신탕정S/S 345kV CB 7571","신탕정S/S 345kV 7571, 7500 GIS 하자점검","신탕정S/S 345kV 7571, 7500 GIS 하자점검","2020-11-10 09:00","2020-11-10 13:00","2020-11-10 09:00","2020-11-10 13:00","연속"]
[182,"대전충남","아산","신탕정S/S 345kV CB 7471","신탕정S/S 345kV 7471 GIS 하자점검","신탕정S/S 345kV 7471 GIS 하자점검","2020-11-11 09:00","2020-11-11 18:00","2020-11-11 09:00","2020-11-11 18:00","연속"]
[183,"대전충남","아산","신탕정S/S 345kV CB 7500","신탕정S/S 345kV 7571, 7500 GIS 하자점검","신탕정S/S 345kV 7571, 7500 GIS 하자점검","2020-11-10 13:00","2020-11-10 18:00","2020-11-10 13:00","2020-11-10 18:00","연속"]
[184,"대전충남","아산","아산S/S 345kV CB 7371","아산S/S 345KV 현대제 GIS 공기조작부 성능개선공사","- 공기조작부 컨트롤블럭 철거 공장점검입고 - 점검완료분 설치 - 차단기 개폐타임","2020-11-11 09:00","2020-11-13 18:00","2020-11-11 09:00","2020-11-13 18:00","연속"]
[185,"대전충남","아산","아산S/S 345kV CB 7572","아산S/S 345KV 현대제 GIS 공기조작부 성능개선공사","- 공기조작부 컨트롤블럭 철거 공장점검입고 - 점검완료분 설치 - 차단기 개폐타임","2020-11-30 09:00","2020-12-02 18:00","2020-11-30 09:00","2020-12-02 18:00","연속"]
[186,"대전충남","아산","아산S/S 345kV CB 7500","아산S/S 345KV 현대제 GIS 공기조작부 성능개선공사","- 공기조작부 컨트롤블럭 철거 공장점검입고 - 점검완료분 설치 - 차단기 개폐타임","2020-11-26 09:00","2020-11-28 18:00","2020-11-26 09:00","2020-11-28 18:00","연속"]
[187,"대전충남","아산","아산S/S #3 M.Tr","아산S/S 345kV #3M.Tr 부싱절연유 채유","아산S/S 345kV #3M.Tr 부싱절연유 채유","2020-11-20 09:00","2020-11-20 18:00","2020-11-20 09:00","2020-11-20 18:00","연속"]
[188,"대전충남","아산","아산S/S 345kV CB 7872","아산S/S 345KV 현대제 GIS 공기조작부 성능개선공사","- 공기조작부 컨트롤블럭 철거 공장점검입고 - 점검완료분 설치 - 차단기 개폐타임","2020-11-09 09:00","2020-11-11 18:00","2020-11-09 09:00","2020-11-11 18:00","연속"]
[189,"대전충남","아산","아산S/S #1 M.Tr","아산S/S 345kV #1M.Tr 부싱절연유 채유","아산S/S 345kV #1M.Tr 부싱절연유 채유","2020-11-19 09:00","2020-11-19 18:00","2020-11-19 09:00","2020-11-19 18:00","연속"]
[190,"대전충남","청양","보령TP보령CC#2 T/L","보령C/C 362kV GIS 스페이서 교체","보령C/C 345kV 보령연락#2T/L ES Terminal 스페이서 교체(7209-2 ES)","2020-11-04 09:00","2020-11-05 18:00","2020-11-04 09:00","2020-11-05 18:00","연속"]
[191,"대전충남","청양","신보령TP보령CC T/L","보령C/C 345kV 신보령연락T/L GIS 과열개소 점검","보령C/C 345kV 신보령연락T/L GIS 과열개소 점검","2020-11-14 09:00","2020-11-14 13:00","2020-11-14 09:00","2020-11-14 13:00","연속"]
[192,"대전충남","청양","청양보령CC T/L","보령C/C 345kV 청양-보령복합T/L GIS 과열개소 점검","보령C/C 345kV 청양-보령복합T/L GIS 과열개소 점검","2020-11-14 13:00","2020-11-14 18:00","2020-11-14 13:00","2020-11-14 18:00","연속"]
[193,"대전충남","청양","보령TP보령CC#1 T/L","보령C/C 362kV GIS 스페이서 교체","보령C/C 345kV 보령연락#1T/L ES Terminal 스페이서 교체(7109-2,4 ES)","2020-11-02 09:00","2020-11-03 18:00","2020-11-02 09:00","2020-11-03 18:00","연속"]
[194,"대전충남","청양","보령T/P 345kV CB 7672","보령T/P 362kV GIS(7672) 초기점검","보령T/P 362kV GIS(7672) 초기점검","2020-11-18 09:00","2020-11-18 18:00","2020-11-18 09:00","2020-11-18 18:00","연속"]
[195,"대전충남","청양","보령T/P 345kV CB 7600","보령T/P 362kV GIS(7600) 초기점검","보령T/P 362kV GIS(7600) 초기점검","2020-11-17 09:00","2020-11-17 18:00","2020-11-17 09:00","2020-11-17 18:00","연속"]
[196,"대전충남","청양","보령T/P 345kV CB 7472","보령T/P 362kV GIS(7472) 초기점검","보령T/P 362kV GIS(7472) 초기점검","2020-11-12 09:00","2020-11-12 18:00","2020-11-12 09:00","2020-11-12 18:00","연속"]
[197,"대전충남","청양","보령T/P 345kV CB 7400","보령T/P 362kV GIS(7400) 초기점검","보령T/P 362kV GIS(7400) 초기점검","2020-11-13 09:00","2020-11-13 18:00","2020-11-13 09:00","2020-11-13 18:00","연속"]
[198,"대전충남","청양","보령T/P 345kV CB 7671","보령T/P 362kV GIS(7671) 초기점검","보령T/P 362kV GIS(7671) 초기점검","2020-11-16 09:00","2020-11-16 18:00","2020-11-16 09:00","2020-11-16 18:00","연속"]
[199,"대전충남","청양","신옥천청양 T/L","154kV 신계룡-두마T/L OPGW 증설공","신계룡S/S ~ 두마S/S 간 가공지선(ACSR 97SQ)를 OPGW/100SQ로 변경","2020-11-23 07:00","2020-11-26 18:00","2020-11-23 07:00","2020-11-26 18:00","연속"]
[200,"대전충남","청양","청양신탕정 T/L","청양S/S #73BAY B/F PNL 대체","청양S/S #73BAY B/F PNL 대체","2020-11-09 09:00","2020-11-13 18:00","취소","취소","연속"]
[201,"대전충남","청양","청양군산#2 T/L","청양S/S #73BAY B/F PNL 대체","청양S/S #73BAY B/F PNL 대체","2020-11-09 09:00","2020-11-13 18:00","취소","취소","연속"]
[202,"대전충남","청양","청양S/S 345kV CB 7772","청양S/S 345kV 7772CB 부동작예방 조작시험","청양S/S 362kV GIS(7772) 초기점검","2020-11-23 09:00","2020-11-23 13:00","2020-11-23 09:00","2020-11-23 13:00","연속"]
[203,"대전충남","청양","청양군산#1 T/L","[송전]345kV 청양-보령 등 9개TL 항공장애표시구 정비공사","345kV 청양-군산#1T/L 항공장애표시구 설치 - No.72~73, 73~74, 105~106, 113~114, 118~119, 126~127, 128~129, 131~132, 143~144, 144~145, 157~158, 158~159, 159~160, 165`166(14경간)","2020-11-02 07:00","2020-11-06 18:00","취소","취소","매일"]
[204,"대전충남","청양","청양S/S 345kV CB 7200","청양S/S 345kV 7200CB 메커니즘점검","청양S/S 345kV 7200CB 메커니즘점검","2020-11-26 09:00","2020-11-26 18:00","2020-11-26 09:00","2020-11-26 18:00","연속"]
[205,"대전충남","청양","청양S/S 345kV CB 7271","청양S/S 345kV 7271CB 메커니즘점검","청양S/S 345kV 7271CB 메커니즘점검","2020-11-25 09:00","2020-11-25 18:00","2020-11-25 09:00","2020-11-25 18:00","연속"]
[206,"대전충남","청양","청양S/S 345kV CB 7172","청양S/S 362kV GIS(7172) 보통점검 및 전자변교체","청양S/S 362kV GIS(7172) 보통점검, 전자변교체 및 메커니즘점검","2020-11-24 09:00","2020-11-24 18:00","2020-11-24 09:00","2020-11-24 18:00","연속"]
[207,"대전충남","청양","청양S/S 345kV CB 7700","청양S/S 345kV 7700CB 부동작예방 조작시험","청양S/S 362kV GIS(7700) 초기점검","2020-11-23 14:00","2020-11-23 18:00","2020-11-23 14:00","2020-11-23 18:00","연속"]
[208,"전북","군산","군산새만금#2 T/L","345kV 군산S/S Sh.R 설치공사","345kV 군산S/S Sh.R 설치공사 [휴전개소 : #70BUS] [작업개소 : 76BAY]","2020-11-25 18:00","2020-11-26 18:00","2020-11-25 18:00","2020-11-26 18:00","연속"]
[209,"전북","군산","군산S/S 345kV #1 BUS","345kV 군산S/S Sh.R 설치공사","345kV 군산S/S Sh.R 설치공사 [휴전개소 : #70BUS] [작업개소 : 76BAY]","2020-11-25 18:00","2020-11-26 18:00","2020-11-25 18:00","2020-11-26 18:00","연속"]
[210,"전북","군산","군산새만금#2 T/L","345kV 군산S/S Sh.R 설치공사","345kV 군산S/S Sh.R 설치공사 [휴전개소 : #75BUS] [작업개소 : 76BAY]","2020-11-24 18:00","2020-11-25 18:00","2020-11-24 18:00","2020-11-25 18:00","연속"]
[211,"전북","군산","군산S/S 345kV #2 BUS","345kV 군산S/S Sh.R 설치공사","345kV 군산S/S Sh.R 설치공사 [휴전개소 : #75BUS] [작업개소 : 76BAY]","2020-11-24 18:00","2020-11-25 18:00","2020-11-24 18:00","2020-11-25 18:00","연속"]
[212,"전북","군산","군산S/S #3 M.Tr","345kV 군산S/S Sh.R 설치공사","345kV 군산S/S Sh.R 설치공사 [휴전개소 : #75BUS] [작업개소 : 76BAY]","2020-11-24 18:00","2020-11-25 18:00","2020-11-24 18:00","2020-11-25 18:00","연속"]
[213,"전북","군산","청양군산#2 T/L","군산P/O 공압식 차단기 전자변 교체공사","-군산S/S 345kV 청양-군산#2 T/L 전자변 교체공사","2020-11-19 09:00","2020-11-19 18:00","취소","취소","연속"]
[214,"전북","군산","군산새만금#2 T/L","군산P/O 공압식 차단기 전자변 교체공사","-군산S/S 345kV 군산-새만금 #2 T/L 전자변 교체공사","2020-11-12 09:00","2020-11-12 18:00","2020-11-12 09:00","2020-11-12 18:00","연속"]
[215,"전북","군산","군산새만금#1 T/L","군산P/O 공압식 차단기 전자변 교체공사","-군산S/S 345kV 군산-새만금 #1 T/L 전자변 교체공사","2020-11-11 09:00","2020-11-11 18:00","2020-11-11 09:00","2020-11-11 18:00","연속"]
[216,"전북","군산","새만금S/S #3 M.Tr","'20년 군산P/O 170kV GIS 정밀점검 공사","새만금S/S 345kV #3M.Tr 2차 GIS 정밀점검","2020-11-25 09:00","2020-11-26 18:00","2020-11-25 09:00","2020-11-26 18:00","연속"]
[217,"전북","군산","새만금S/S #2 M.Tr","'20년 군산P/O 170kV GIS 정밀점검공사","새만금S/S 345kV #2M.Tr 2차 GIS 정밀점검공사","2020-11-23 09:00","2020-11-24 18:00","2020-11-23 09:00","2020-11-24 18:00","연속"]
[218,"전북","김제","신김제S/S #4 M.Tr","신김제S/S #4M.Tr 및 78BAY B/F PNL 대체","신김제S/S #4M.Tr 및 78BAY B/F PNL 대체","2020-11-16 09:00","2020-11-27 18:00","2020-11-23 09:00","2020-12-04 18:00","연속"]
[219,"전북","김제","신김제S/S #3 M.Tr","154kV #1,2,3Sh.C 차단부 제작사 정밀점검 (안전이격)","- 차단부 철거 후 제작사 입고 - 제작사 정밀점검 후 설치","2020-11-02 09:00","2020-11-10 18:00","2020-11-09 09:00","2020-11-20 18:00","연속"]
[220,"전북","직할","신남원S/S 345kV #1BUS","신남원S/S 362kV GIS GAS 누기 보수공사","- 7471CB B상 누기보수, #70BUS 휴전병행","2020-11-02 09:00","2020-11-05 18:00","2020-11-23 09:00","2020-11-26 18:00","연속"]
[221,"전북","직할","신남원의령#1 T/L","신남원S/S 362kV GIS GAS 누기 보수공사","- 7352DS B상 누기보수, #75BUS 휴전병행","2020-11-06 09:00","2020-11-07 18:00","2020-11-30 09:00","2020-12-01 18:00","연속"]
[222,"전북","직할","신남원광양#1 T/L","신남원S/S 362kV GIS GAS 누기 보수공사","- 7500CB A,B,C상 누기보수, #75BUS 휴전병행","2020-11-09 09:00","2020-11-21 18:00","2020-12-02 09:00","2020-12-15 18:00","연속"]
[223,"전북","직할","신남원광양#2 T/L","신남원S/S 362kV GIS GAS 누기 보수공사","- 7600CB C상 누기보수, #75BUS 휴전병행 - 7671CB A,B,C상 누기보수, #70BUS 휴전병행 - 7661DS B상 누기보수, #70BUS 휴전병행","2020-11-23 09:00","2020-12-15 18:00","취소","취소","연속"]
[224,"전북","직할","신남원S/S 345kV #1BUS","신남원S/S 362kV GIS GAS 누기 보수공사","- 7671CB A, B, C상 누기보수, #70BUS 휴전병행 - 7661DS B상 누기보수, #70BUS 휴전병행","2020-11-27 09:00","2020-12-15 18:00","취소","취소","연속"]
[225,"전북","직할","신남원의령#2 T/L","신남원S/S 362kV GIS GAS 누기 보수공사","- 7471CB B상 누기보수, #70BUS 휴전병행","2020-11-02 09:00","2020-11-05 18:00","2020-11-23 09:00","2020-11-26 18:00","연속"]
[226,"전북","직할","신남원신광주#2 T/L","`20~`21년 전북 직할 변전정비회사 총액공사","신남원S/S 7871, 7800GIS 보통점검 및 노후 단자대 교체","2020-11-02 09:00","2020-11-03 18:00","2020-11-02 09:00","2020-11-03 18:00","연속"]
[227,"전북","직할","신남원S/S 345kV #2BUS","신남원S/S 362kV GIS GAS 누기 보수공사","- 7352DS B상 누기보수, #75BUS 휴전병행 - 7500CB A, B, C상 누기보수, #75BUS 휴전병행 - 7600CB C상 누기보수, #75BUS 휴전병행","2020-11-06 09:00","2020-11-26 18:00","2020-11-30 09:00","2020-12-15 18:00","연속"]
[228,"광주전남","강진","신강진S/S #4 M.Tr","'20-21년 강진전력지사 변전정비회사 총액공사","신강진S/S #4M.Tr 1차 부싱 절연열화 측정","2020-11-03 10:00","2020-11-04 17:00","2020-11-03 10:00","2020-11-04 17:00","연속"]
[229,"광주전남","광주","신광주S/S 345kV #1 BUS","2020∼21년 광주전력지사 변전정비회사 총액공사","345kV #70BUS 모선보호반 교체","2020-11-16 09:00","2020-11-20 18:00","취소","취소","연속"]
[230,"광주전남","광주","신광주신화순#2 T/L","345kV신광주-신화순T/L 전선접속개소전선교체공사","전선교체 1.995 C-km","2020-11-24 07:00","2020-11-29 18:00","2020-11-30 07:00","2020-12-05 18:00","연속"]
[231,"광주전남","광주","신광주신화순#1 T/L","345kV신광주-신화순T/L 전선접속개소전선교체공사","전선교체 1.995 C-km","2020-11-30 07:00","2020-12-05 18:00","2020-11-24 07:00","2020-11-29 18:00","연속"]
[232,"광주전남","광주","신광주S/S 345kV #2 BUS","2020∼21년 광주전력지사 변전정비회사 총액공사","345kV #75BUS 모선보호반 교체","2020-11-23 09:00","2020-11-27 18:00","취소","취소","연속"]
[233,"광주전남","광주","신화순S/S 345kV #2 BUS","신화순S/S 345kV #75BUS(변전협력회사 총액공사)","345kV PT 반 교체","2020-11-11 13:00","2020-11-12 18:00","2020-11-11 13:00","2020-11-12 18:00","연속"]
[234,"광주전남","광주","신화순S/S #1 M.Tr","20년 광주변전총액(신화순 #1M.Tr)","신화순S/S 345kV #1M.Tr 보통점검, 4185DS 보통점검, #1S.Tr 하자점검, 1,2,3차 LA 하자점검, 3차 PT 보통점검, 7972CB 장기미동작 차단기 점검","2020-11-04 09:30","2020-11-06 18:00","2020-11-04 09:30","2020-11-06 18:00","연속"]
[235,"광주전남","광주","신화순S/S #2 M.Tr","20년 광주변전총액(신화순 #2M.Tr)","신화순S/S 345kV FR 교체관련 345kV #2M.Tr CT 결선 이설","2020-11-09 09:00","2020-11-09 13:00","2020-11-09 09:00","2020-11-09 13:00","연속"]
[236,"광주전남","광주","신화순S/S #3 M.Tr","20년 광주변전총액(신화순 #3M.Tr)","신화순S/S 345kV FR 교체관련 345kV #3M.Tr CT 결선 이설","2020-11-09 13:00","2020-11-09 18:00","2020-11-09 13:00","2020-11-09 18:00","연속"]
[237,"광주전남","광주","신화순S/S 345kV #1 BUS","신화순S/S 345kV #70 BUS(변전협력회사 총액공사)","345kV PT 반 교체","2020-11-10 09:00","2020-11-11 13:00","2020-11-10 09:00","2020-11-11 13:00","연속"]
[238,"광주전남","광주","신화순S/S 345kV #1 BUS","신화순S/S 345kV #70BUS(변전협력회사 총액공사)","345kV PT 반 교체","2020-11-13 09:00","2020-11-13 18:00","2020-11-13 09:00","2020-11-13 18:00","연속"]
[239,"광주전남","광주","신화순S/S #1 M.Tr","20년 광주변전총액(신화순 #1M.Tr)","신화순S/S 345kV FR 교체관련 345kV #1M.Tr CT 결선 이설","2020-11-16 09:00","2020-11-16 11:00","2020-11-16 09:00","2020-11-16 11:00","연속"]
[240,"광주전남","광주","신화순S/S #2 M.Tr","20년 광주변전총액(신화순 #2M.Tr)","신화순S/S 345kV FR 교체관련 345kV #2M.Tr CT 결선 이설","2020-11-16 13:00","2020-11-16 15:00","2020-11-16 13:00","2020-11-16 15:00","연속"]
[241,"광주전남","광주","신화순S/S #3 M.Tr","20년 광주변전총액(신화순 #3M.Tr)","신화순S/S 345kV FR 교체관련 345kV #3M.Tr CT 결선 이설","2020-11-16 15:00","2020-11-16 18:00","2020-11-16 15:00","2020-11-16 18:00","연속"]
[242,"광주전남","목포","한빛2NP한빛3NP#3 T/L","2020년 목포전력지사 변전정비회사 총액공사","한빛#3S/Y 한빛연락#3T/L CVT 하자점검 한빛 제2개폐소 한빛연락#3T/L 한류리액터 보통점검, LA 보통점검","2020-11-16 10:00","2020-11-17 18:00","2020-11-16 10:00","2020-11-17 18:00","연속"]
[243,"광주전남","순천","광양여수TP T/L","여수화력S/Y #4M.Tr 및 SW증설 공사","1. 362kV GIS 6CB 설치 2. 345kV #4M.Tr 증설 3. 기타부대공사","2020-12-01 10:00","2020-12-09 18:00","취소","취소","연속"]
[244,"광주전남","순천","여수T/P 345kV #1 BUS","여수화력S/Y #4M.Tr 및 SW증설 공사","1. 362kV GIS 6CB 설치 2. 345kV #4M.Tr 증설 3. 기타부대공사","2020-12-01 10:00","2021-01-15 18:00","취소","취소","연속"]
[245,"광주전남","순천","여수T/P #1 Tie-Tr","여수화력S/Y #4M.Tr 및 SW증설공사","- 362kV GIS 6CB설치 - 345kV #4M.Tr 증설 - 기타 부대공사","2020-11-02 10:00","2020-11-11 18:00","2020-11-16 10:00","2020-11-18 18:00","연속"]
[246,"광주전남","순천","광양여수TP T/L","여수화력S/Y #4M.Tr 및 SW증설공사","345kV #75-76BUS 증설 무부하가압","2020-11-30 10:00","2020-12-01 10:00","2020-11-16 10:00","2020-11-18 18:00","연속"]
[247,"광주전남","순천","여수T/P #1 Tie-Tr","여수화력S/Y #4M.Tr 및 SW증설공사","345kV #75-76BUS 증설 무부하가압","2020-11-30 10:00","2020-12-01 10:00","취소","취소","연속"]
[248,"광주전남","순천","여수T/P 345kV #2 BUS","여수화력S/Y #4M.Tr 및 SW증설공사","- 362kV GIS 6CB설치 - 345kV #4M.Tr 증설 - 기타 부대공사","2020-11-02 10:00","2020-11-27 18:00","취소","취소","연속"]
[249,"광주전남","순천","여수T/P #2 Tie-Tr","여수화력S/Y #4M.Tr 및 SW증설공사","- 362kV GIS 6CB설치 - 345kV #4M.Tr 증설 - 기타 부대공사","2020-11-12 10:00","2020-11-18 18:00","취소","취소","연속"]
[250,"대구","달성","고령의령#2 T/L","고령S/S 7471, 7400 차단기동작시험","고령S/S 7471, 7400 차단기동작시험","2020-11-20 09:00","2020-11-20 18:00","취소","취소","연속"]
[251,"대구","달성","고령S/S #3 M.Tr","고령S/S #3M.Tr 휴전","#3M.Tr 보통, GIS 보통점검, LA , CVT점검","2020-11-04 09:00","2020-11-06 18:00","2020-11-04 09:00","2020-11-06 18:00","연속"]
[252,"대구","달성","고령S/S #1 M.Tr","고령S/S #1M.Tr 냉각팬불량 현장확인 및 보수작업","고령S/S #1M.Tr 냉각팬불량 현장확인 및 보수작업","2020-11-02 09:00","2020-11-02 18:00","2020-11-02 09:00","2020-11-02 18:00","연속"]
[253,"대구","달성","고령S/S 345kV #1 BUS","고령S/S 154kV PT집합반 대체작업","고령S/S 154kV PT집합반 대체작업","2020-11-03 11:00","2020-11-03 12:00","2020-11-03 11:00","2020-11-03 12:00","연속"]
[254,"대구","달성","고령S/S 345kV #2 BUS","고령S/S 154kV PT집합반 대체작업","고령S/S 154kV PT집합반 대체작업","2020-11-03 13:00","2020-11-03 14:00","2020-11-03 13:00","2020-11-03 14:00","연속"]
[255,"대구","달성","고령S/S #1 M.Tr","고령S/S 154kV PT집합반 대체작업","고령S/S 154kV PT집합반 대체작업","2020-11-03 14:00","2020-11-03 15:00","2020-11-03 14:00","2020-11-03 15:00","연속"]
[256,"대구","달성","고령S/S 345kV #1 BUS","고령S/S 154kV PT집합반 대체작업","고령S/S 154kV PT집합반 대체작업","2020-11-03 17:00","2020-11-03 18:00","2020-11-03 17:00","2020-11-03 18:00","연속"]
[257,"대구","달성","고령S/S #4 M.Tr","고령S/S 154kV PT집합반 대체작업","고령S/S 154kV PT집합반 대체작업","2020-11-03 17:00","2020-11-03 18:00","2020-11-03 17:00","2020-11-03 18:00","연속"]
[258,"대구","달성","고령S/S #3 M.Tr","고령S/S 154kV PT집합반 대체작업","고령S/S 154kV PT집합반 대체작업","2020-11-03 16:00","2020-11-03 17:00","2020-11-03 16:00","2020-11-03 17:00","연속"]
[259,"대구","달성","고령S/S #2 M.Tr","고령S/S 154kV PT집합반 대체작업","고령S/S 154kV PT집합반 대체작업","2020-11-03 15:00","2020-11-03 16:00","2020-11-03 15:00","2020-11-03 16:00","연속"]
[260,"대구","달성","북경남대구#1 T/L","154kV 대구-청도T/L 송전용량증대 전선교체공사 관련 안전확보","송전용량증대 전선교체공사 관련 (4호) 병가구간작업 안전확보","2020-11-08 07:00","2020-11-08 18:00","2020-11-06 07:00","2020-11-06 18:00","연속"]
[261,"대구","달성","북경남대구#2 T/L","154kV 대구-청도T/L 송전용량증대 전선교체공사 관련 안전확보","송전용량증대 전선교체공사 관련 (4호) 병가구간작업 안전확보","2020-11-08 07:00","2020-11-08 18:00","2020-11-07 07:00","2020-11-07 18:00","연속"]
[262,"대구","달성","북경남대구#1 T/L","154kV 대구-청도T/L 송전용량증대 전선교체공사 관련 안전확보","송전용량증대 전선교체공사 관련 (4호) 병가구간작업 안전확보","2020-11-15 07:00","2020-11-15 18:00","2020-11-13 07:00","2020-11-13 18:00","연속"]
[263,"대구","달성","북경남대구#2 T/L","154kV 대구-청도T/L 송전용량증대 전선교체공사 관련 안전확보","송전용량증대 전선교체공사 관련 (4호) 병가구간작업 안전확보","2020-11-15 07:00","2020-11-15 18:00","2020-11-14 07:00","2020-11-14 18:00","연속"]
[264,"대구","달성","북경남대구#1 T/L","20-21년 가공송전 정비회사 총액공사","애자련 교체공사(No.49)","2020-11-02 08:00","2020-11-02 18:00","취소","취소","연속"]
[265,"대구","칠곡","북대구S/S #2 M.Tr","북대구S/S 154kV #2 BUS-PRO PNL 대체공사","북대구S/S 154kV #2 BUS-PRO PNL 대체공사","2020-11-20 10:00","2020-11-20 10:30","2020-11-20 10:00","2020-11-20 10:30","연속"]
[266,"대구","칠곡","북대구선산 T/L","북대구S/S #4M.Tr 증설공사","주변압기 기초공사 지반보강(파일시공)관련 안전확보","2020-11-19 09:00","2020-11-19 18:00","2020-11-19 09:00","2020-11-19 18:00","매일"]
[267,"대구","칠곡","북대구S/S #3 M.Tr","북대구S/S 154kV #2 BUS-PRO PNL 대체공사","북대구S/S 154kV #2 BUS-PRO PNL 대체공사","2020-11-20 15:00","2020-11-20 15:30","2020-11-20 15:00","2020-11-20 15:30","연속"]
[268,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사(토목)","전력구 토류판 시공관련 H파일 철거","2020-11-26 09:00","2020-11-26 18:00","2020-11-26 09:00","2020-11-26 18:00","연속"]
[269,"대구","칠곡","서대구S/S #2 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사(토목)","전력구 토류판 시공관련 H파일 철거","2020-11-24 09:00","2020-11-24 18:00","2020-11-24 09:00","2020-11-24 18:00","연속"]
[270,"대구","칠곡","서대구고령#2 T/L","서대구S/S 345kV T/L LA,PT 하자 및 보통점검","서대구S/S 345kV T/L LA,PT 하자 및 보통점검","2020-11-13 09:30","2020-11-13 18:00","2020-11-13 09:30","2020-11-13 18:00","연속"]
[271,"대구","칠곡","서대구S/S #3 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사(토목)","전력구 토류판 시공관련 H파일 철거","2020-11-23 09:00","2020-11-23 18:00","2020-11-23 09:00","2020-11-23 18:00","연속"]
[272,"대구","포항","신영일안동CC T/L","신영일S/S 76BAY B/F PNL 대체 작업","신영일S/S 76BAY B/F PNL 대체 작업","2020-11-23 09:00","2020-11-27 18:00","2020-11-23 09:00","2020-11-27 18:00","연속"]
[273,"대구","포항","신포항신월성NP#1 T/L","2020-21년 포항전력지사 가공송전 정비회사 총액공사","BC링크 설치 : No.26~29","2020-11-16 08:00","2020-11-19 18:00","2020-11-16 08:00","2020-11-19 18:00","연속"]
[274,"대구","포항","월성NP신월성NP#2 T/L","2020-21년 포항전력지사 가공송전 정비회사 총액공사","고정형 폴리머점퍼지지애자 설치 : No.7","2020-11-23 08:00","2020-11-23 18:00","2020-11-23 08:00","2020-11-23 18:00","연속"]
[275,"대구","포항","신포항신월성NP#4 T/L","2020-21년 포항전력지사 가공송전 정비회사 총액공사","고정형 폴리머점퍼지지애자 설치 : No.8","2020-11-25 08:00","2020-11-25 18:00","2020-11-25 08:00","2020-11-25 18:00","연속"]
[276,"대구","포항","신포항신월성NP#2 T/L","2020-21년 포항전력지사 가공송전 정비회사 총액공사","고정형 폴리머점퍼지지애자 설치 : No.4","2020-11-24 08:00","2020-11-24 18:00","2020-11-24 08:00","2020-11-24 18:00","연속"]
[277,"대구","포항","신포항S/S 345kV CB 7472","신포항S/S 7472, 7400 CB 조작시험","신포항S/S 7472, 7400 CB 조작시험","2020-11-25 09:30","2020-11-25 14:00","2020-11-25 09:30","2020-11-25 14:00","연속"]
[278,"대구","포항","신포항S/S 345kV CB 7400","신포항S/S 7472, 7400 GIS 조작시험","신포항S/S 7472, 7400 GIS 조작시험","2020-11-25 14:00","2020-11-25 18:00","2020-11-25 14:00","2020-11-25 18:00","연속"]
[279,"대구","포항","신포항S/S 345kV CB 7571","신포항S/S 7571, 7500 CB 조작시험","신포항S/S 7571, 7500 CB 조작시험","2020-11-24 09:30","2020-11-24 14:00","2020-11-24 09:30","2020-11-24 14:00","연속"]
[280,"대구","포항","신포항북대구 T/L","345kV 신포항-북대구T/L 지장송전선로 이설공사","도남지구 공공택지 조성관련 지장이설공사 45~47호 철거/설치","2020-11-13 08:00","2020-11-24 18:00","2020-11-13 08:00","2020-11-24 18:00","연속"]
[281,"대구","포항","선산신포항 T/L","345kV 신포항-북대구T/L 지장송전선로 이설공사","도남지구 공공택지 조성관련 지장이설공사 45~47호 철거/설치","2020-11-01 08:00","2020-11-12 18:00","2020-11-01 08:00","2020-11-12 18:00","연속"]
[282,"대구","포항","신포항S/S 345kV CB 7500","신포항S/S 7571, 7500 CB 조작시험","신포항S/S 7571, 7500 CB 조작시험","2020-11-24 14:00","2020-11-24 18:00","2020-11-24 14:00","2020-11-24 18:00","연속"]
[283,"대구","포항","신포항S/S 345kV CB 7300","신포항S/S 7371, 7300 GIS 조작시험","신포항S/S 7371, 7300 GIS 조작시험","2020-11-27 14:00","2020-11-27 18:00","2020-11-27 14:00","2020-11-27 18:00","연속"]
[284,"대구","포항","신포항S/S 345kV CB 7371","신포항S/S 7371, 7300 GIS 조작시험","신포항S/S 7371, 7300 GIS 조작시험","2020-11-27 09:30","2020-11-27 14:00","2020-11-27 09:30","2020-11-27 14:00","연속"]
[285,"대구","포항","신포항S/S 345kV CB 7700","신포항S/S 7771, 7700 GIS 조작시험","신포항S/S 7771, 7700 GIS 조작시험","2020-11-26 14:00","2020-11-26 18:00","2020-11-26 14:00","2020-11-26 18:00","연속"]
[286,"대구","포항","신포항S/S 345kV CB 7771","신포항S/S 7771, 7700 GIS 조작시험","신포항S/S 7771, 7700 GIS 조작시험","2020-11-26 09:30","2020-11-26 14:00","2020-11-26 09:30","2020-11-26 14:00","연속"]
[287,"대구","포항","월성N/P 345kV CB 7372","월성S/Y 345kV 75BUS 모선보호반 대체작업","월성S/Y 345kV 75BUS 모선보호반 대체작업","2020-11-02 09:00","2020-11-06 18:00","2020-11-02 09:00","2020-11-06 18:00","연속"]
[288,"대구","포항","월성N/P 345kV #75 BUS","월성S/Y 345kV 75BUS 모선보호반 대체작업","월성S/Y 345kV 75BUS 모선보호반 대체작업","2020-11-02 09:00","2020-11-06 18:00","2020-11-02 09:00","2020-11-06 18:00","연속"]
[289,"대구","포항","월성N/P 345kV SEC CB 75760","월성S/Y 345kV 75BUS 모선보호반 대체작업","월성S/Y 345kV 75BUS 모선보호반 대체작업","2020-11-02 09:00","2020-11-06 18:00","2020-11-02 09:00","2020-11-06 18:00","연속"]
[290,"대구","포항","월성N/P 345kV CB 7472","월성S/Y 345kV 75BUS 모선보호반 대체작업","월성S/Y 345kV 75BUS 모선보호반 대체작업","2020-11-02 09:00","2020-11-06 18:00","2020-11-02 09:00","2020-11-06 18:00","연속"]
[291,"대구","포항","월성N/P 345kV CB 7272","월성S/Y 345kV 75BUS 모선보호반 대체작업","월성S/Y 345kV 75BUS 모선보호반 대체작업","2020-11-02 09:00","2020-11-06 18:00","2020-11-02 09:00","2020-11-06 18:00","연속"]
[292,"대구","포항","울주월성NP#2 T/L","2020-21년 포항전력지사 가공송전 정비회사 총액공사","고정형 폴리머점퍼지지애자 설치 : No.65, 73","2020-11-25 08:00","2020-11-27 18:00","2020-11-25 08:00","2020-11-27 18:00","연속"]
[293,"경북","영주","신영주S/S #2 M.Tr","2020-21년 영주전력지사 변전정비회사 총액공사","- 신영주S/S #2M.Tr 2차 CB(6244) 조작시험 - 345kV 보호반 3차측 지락요소 정정","2020-11-24 09:00","2020-11-24 18:00","2020-11-17 09:00","2020-11-17 12:00","연속"]
[294,"경북","영주","신영주S/S STATCOM CB","신영주S/S STATCOM 소방설비 성능 개선공사","- 신영주S/S STATCOM 소방설비 성능 개선공사","2020-11-11 09:00","2020-11-13 18:00","취소","취소","연속"]
[295,"경북","영주","신영주S/S #3 M.Tr","신영주S/S 154kV 현대화 전력구공사","전력구 설치 관련 기 시공 가시설 철거","2020-11-25 08:00","2020-11-26 18:00","2020-11-25 08:00","2020-11-26 18:00","연속"]
[296,"경북","영주","신영주S/S #1 M.Tr","2020-21년 영주전력지사 변전정비회사 총액공사","- 신영주S/S #1M.Tr 2차 CB(6144) 조작시험 - 345kV 보호반 3차측 지락요소 정정","2020-11-23 09:00","2020-11-23 18:00","2020-11-17 12:00","2020-11-17 18:00","연속"]
[297,"부산울산","동부산","고리N/P 345kV #75 BUS","345kV 고리N/P SW증설공사","10월 기 휴전신청분 취소시 반영요청","2020-11-18 09:00","2020-12-04 18:00","2020-11-18 09:00","2020-12-04 18:00","연속"]
[298,"부산울산","동부산","고리N/P 345kV #70 BUS","345kV 고리N/P SW증설공사","10월 기 휴전신청분 취소시 반영요청","2020-11-03 09:00","2020-11-17 18:00","2020-11-03 09:00","2020-11-17 18:00","연속"]
[299,"부산울산","동부산","신고리고리NP#3 T/L","울산 울주지역 전기공급시설 전력구공사(신고리-고리)","[신고리] 개착식 전력구 L=834m, 접속맨홀 1개소 / [고 리] 개착식 전력구 L=274m, C/H부지 1개소","2020-11-10 09:00","2020-11-12 18:00","2020-11-10 09:00","2020-11-12 18:00","매일"]
[300,"부산울산","동부산","신양산S/S #4 M.Tr","[철거4차] 345kV 신양산S/S 현대화 일반공사","#4M.Tr 2차측 옥외철구 설비 철거","2020-11-02 08:00","2020-11-06 18:00","2020-11-09 08:00","2020-11-13 18:00","연속"]
[301,"부산울산","동부산","신양산신대연#1 T/L","동부산전력지사 가공송전 취약설비 정비공사","압축인류크램프 정비 ㅇ 구간 : 3, 4호","2020-11-13 08:00","2020-11-13 18:00","2020-11-13 08:00","2020-11-13 18:00","연속"]
[302,"부산울산","동부산","신양산S/S #4 M.Tr","[철거4차] 345kV 신양산S/S 현대화 일반공사","#4M.Tr 2차측 옥외철구 설비 철거","2020-11-02 08:00","2020-11-06 18:00","취소","취소","연속"]
[303,"부산울산","동부산","신양산북부산#1 T/L","20년도 가공송전 순시점검 위탁공사(정밀점검)","345kV 신양산-북부산#1T/L 정밀점검 ㅇ정밀점검 구간 : 신양산S/S ~ 북부산S/S","2020-11-14 09:00","2020-11-18 18:00","2020-11-14 09:00","2020-11-18 18:00","연속"]
[304,"부산울산","동부산","신양산신대연#2 T/L","동부산전력지사 가공송전 취약설비 정비공사","ㅇ송전용 피뢰기 설치 : 1~7호, 9~11호, 14, 15, 22호","2020-11-09 08:00","2020-11-12 18:00","2020-11-09 08:00","2020-11-12 18:00","연속"]
[305,"부산울산","북부산","북부산S/S 345kV SEC CB 75760","20-21 북부산전력지사 변전총액공사","북부산S/S 345kV 75-76-0 GIS 차단기 전자변 교체 (L Type)","2020-11-25 09:00","2020-11-26 18:00","취소","취소","연속"]
[306,"부산울산","북부산","북부산신울산#2 T/L","345kV 북부산-신울산#2T/L 노후 금구류 및 전선교체공사","345kV 북부산-신울산#2T/L 노후 금구류 및 전선교체공사(1~89호, 21경간 9.188C-km)","2020-11-18 09:00","2020-12-08 18:00","2020-11-24 09:00","2020-12-14 18:00","연속"]
[307,"부산울산","북부산","북부산S/S #3 M.Tr","20-21 북부산전력지사 변전총액공사","북부산S/S 345kV #3M.Tr 1차GIS (7700,7772) 전자변 교체(L Type)","2020-11-09 09:00","2020-11-11 18:00","2020-11-09 09:00","2020-11-11 18:00","연속"]
[308,"부산울산","북부산","북부산S/S 345kV CB 7771","20-21 북부산전력지사 변전총액공사","북부산S/S 345kV 신양산-북부산#2T/L GIS 7771(단독차단기) 전자변교체(L Type)","2020-11-23 09:00","2020-11-24 18:00","2020-11-23 09:00","2020-11-24 18:00","연속"]
[309,"부산울산","서부산","서부산S/S #3 M.Tr","서부산S/S #73Bay B/F PNL 대체","서부산S/S #73Bay B/F PNL 대체 (#3M.Tr, 서부산-북부산#3T/L 휴전)","2020-11-23 09:00","2020-11-27 18:00","2020-11-23 09:00","2020-11-27 18:00","연속"]
[310,"부산울산","서부산","서부산S/S 345kV CB 7500","서부산S/S 345kV 7500 GIS 차단기동작시험","서부산S/S 345kV 7500 GIS 차단기동작시험","2020-11-13 10:00","2020-11-13 18:00","2020-11-13 10:00","2020-11-13 18:00","연속"]
[311,"부산울산","서부산","서부산북부산#3 T/L","서부산S/S #73Bay B/F PNL 대체","서부산S/S #73Bay B/F PNL 대체 (#3M.Tr, 서부산-북부산#3T/L 휴전)","2020-11-23 09:00","2020-11-27 18:00","2020-11-23 09:00","2020-11-27 18:00","연속"]
[312,"부산울산","서부산","서부산S/S 345kV CB 7400","서부산S/S 345kV 7400 GIS 차단기동작시험","서부산S/S 345kV 7400 GIS 차단기동작시험","2020-11-10 10:00","2020-11-10 18:00","2020-11-10 10:00","2020-11-10 18:00","연속"]
[313,"부산울산","서부산","서부산S/S 345kV CB 7471","서부산S/S 345kV 7471 GIS 차단기동작시험","서부산S/S 345kV 7471 GIS 차단기동작시험","2020-11-11 10:00","2020-11-11 18:00","2020-11-11 10:00","2020-11-11 18:00","연속"]
[314,"부산울산","서부산","서부산S/S 345kV CB 7571","서부산S/S 345kV 7571 GIS 차단기동작시험","서부산S/S 345kV 7571 GIS 차단기동작시험","2020-11-16 10:00","2020-11-16 18:00","2020-11-16 10:00","2020-11-16 18:00","연속"]
[315,"부산울산","서부산","서부산S/S 345kV CB 7572","서부산S/S 345kV 7572 GIS 차단기동작시험","서부산S/S 345kV 7572 GIS 차단기동작시험","2020-11-17 10:00","2020-11-17 18:00","2020-11-17 10:00","2020-11-17 18:00","연속"]
[316,"부산울산","서부산","서부산S/S 345kV CB 7472","서부산S/S 345kV 7472 GIS 차단기동작시험","서부산S/S 345kV 7472 GIS 차단기동작시험","2020-11-12 10:00","2020-11-12 18:00","2020-11-12 10:00","2020-11-12 18:00","연속"]
[317,"부산울산","서부산","신녹산S/S 345kV CB 7372","신녹산S/S 345kV 7372 GIS 차단기동작시험","신녹산S/S 345kV 7372 GIS 차단기동작시험","2020-11-18 10:00","2020-11-18 18:00","2020-11-18 10:00","2020-11-18 18:00","연속"]
[318,"부산울산","울산","신울산S/S 345kV CB 7572","20~21년 변전협력 총액공사","- 차단기 동작시험","2020-11-17 09:00","2020-11-17 18:00","2020-11-17 09:00","2020-11-17 18:00","연속"]
[319,"부산울산","울산","신울산S/S #4 M.Tr","20~21년 변전협력 총액공사","- 2차 GIS 보통점검 및 전자변교체","2020-11-18 09:00","2020-11-18 18:00","2020-11-18 09:00","2020-11-18 18:00","연속"]
[320,"부산울산","울산","울산C/C #3 Tie-Tr","울산복합S/Y 345kV SW증설공사","- 345kV 울산복합-북부산#1,2T/L(7A71, 7171)용 GIS 설치 후 시험가압 24H","2020-11-01 17:00","2020-11-02 17:00","2020-11-01 17:00","2020-11-02 17:00","연속"]
[321,"부산울산","울산","북부산울산TP T/L","345kV 신울산복합-북부산T/L 건설공사","154kV 신온산-성암 #1,#2 14호~27호 본선로 구성 345kV 신울산복합-북부산T/L 17호~28호 본선로 구성 (345kV 신울산복합-북부산T/L #2 최초가압)","2020-11-20 07:00","2020-11-30 18:00","2020-11-20 07:00","2020-11-30 18:00","연속"]
[322,"부산울산","울산","울산C/C #2 Tie-Tr","154kV 변전설비 자기애관 교체공사","345kV #2M.Tr 2차측 EBA 자기애관(6상)을 폴리머애관으로 교체","2020-11-24 09:00","2020-11-29 18:00","2020-11-24 09:00","2020-11-29 18:00","연속"]
[323,"부산울산","울산","울산C/C #1 Tie-Tr","154kV 변전설비 자기애관 교체공사","345kV #1M.Tr 2차측 EBA 자기애관(6상)을 폴리머애관으로 교체","2020-11-17 09:00","2020-11-22 18:00","2020-11-17 09:00","2020-11-22 18:00","연속"]
[324,"부산울산","울산","울주고리NP#2 T/L","`20~21년도 가공송전 정비회사 총액공사(동부산전력지사)","345kV 울주-고리NP#2 T/L 스페이서 간격조정 75호~90호","2020-11-03 08:00","2020-11-06 18:00","2020-11-03 08:00","2020-11-06 18:00","연속"]
[325,"부산울산","울산","울주S/S #3 M.Tr","20년 울산전력지사 345kV M.Tr 보통점검 공사","- M.Tr 보통점검(정밀-&gt보통으로 변경) - 7672 차단기 동작시험 - 부싱절연유 채유","2020-11-02 09:00","2020-11-03 18:00","2020-11-02 09:00","2020-11-03 18:00","연속"]
[326,"부산울산","울산","울주S/S #4 M.Tr","2020년 345kV 개폐장치 정밀점검공사","- 7872 GIS 정밀점검","2020-11-16 09:00","2020-11-18 18:00","2020-11-16 09:00","2020-11-18 18:00","연속"]
[327,"부산울산","울산","울주S/S 345kV #2 BUS","2020년 345kV 개폐장치 정밀점검공사","- 7A00 GIS 정밀점검관련 시험가압1H","2020-11-11 17:00","2020-11-11 18:00","2020-11-11 17:00","2020-11-11 18:00","연속"]
[328,"부산울산","울산","울주신경산#2 T/L","2020년 345kV 개폐장치 정밀점검공사","- 7A00 GIS 정밀점검관련 시험가압1H","2020-11-11 17:00","2020-11-11 18:00","2020-11-11 17:00","2020-11-11 18:00","연속"]
[329,"부산울산","울산","울주S/S 345kV CB 7A00","2020년 345kV 개폐장치 정밀점검공사","- 7A00 GIS 정밀점검","2020-11-09 09:00","2020-11-11 18:00","2020-11-09 09:00","2020-11-11 18:00","연속"]
[330,"부산울산","직할","신대연S/S 345kV #2 Sh.R","345kV 신대연S/S #2Sh.R 7579 GIS 긴급점검","345kV 신대연S/S #2Sh.R GIS 제작사 점검 (7579 GIS 결상TRIP에 따른 점검)","2020-11-16 09:30","2020-11-20 18:00","2020-11-16 09:30","2020-11-20 18:00","연속"]
[331,"경남","직할","신김해북부산#1 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 철탑설치 및 철거 : 각 2기 ○ 전력선 및 가공지선 교체 : 1.4km (93-97호) ○ 스페이서 댐퍼 교체","2020-11-13 07:00","2020-11-16 18:00","2020-11-27 07:00","2020-11-30 18:00","연속"]
[332,"경남","직할","신김해S/S #2 M.Tr","신김해S/S 154kV 장기사용GIS 교체공사(3차) 안전이격,시험가압","신김해S/S 154kV 장기사용GIS 교체공사(3차) 안전이격,시험가압 휴전 - 대상 : 신김해-장유#2T/L, #2BUS TIE, #2BUS PT, ES","2020-11-09 08:00","2020-11-15 18:00","2020-11-15 08:00","2020-11-19 18:00","연속"]
[333,"경남","직할","신김해S/S #2 M.Tr","신김해S/S 154kV 장기사용GIS 교체공사(3차) 안전이격,시험가압","신김해S/S 154kV 장기사용GIS 교체공사(3차) 안전이격,시험가압 휴전 - 대상 : 신김해-장유#2T/L, #2BUS TIE, #2BUS PT, ES","2020-11-02 08:00","2020-11-08 18:00","2020-11-06 08:00","2020-11-14 18:00","연속"]
[334,"경남","직할","신김해북부산#2 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 철탑설치 및 철거 : 각 2기 ○ 전력선 및 가공지선 교체 : 1.4km (93-97호) ○ 스페이서 댐퍼 교체","2020-11-06 07:00","2020-11-09 18:00","2020-11-20 07:00","2020-11-23 18:00","연속"]
[335,"경남","직할","신김해S/S #2 M.Tr","신김해S/S 154kV 장기사용GIS 교체공사(4차)","신김해S/S 154kV 장기사용GIS 교체공사(4차) - 대상 : 신김해-장유#1T/L, #2M.Tr 2차 GIS","2020-11-18 08:00","2020-12-08 18:00","2020-11-24 08:00","2020-12-14 18:00","연속"]
[336,"경남","진주","의령S/S #2 M.Tr","의령S/S #2M.Tr 2차 GIS 및 3차 VCB(4279) 조작시험","의령S/S #2M.Tr 2차 GIS(6233) 및 VCB(4279) 조작시험","2020-11-02 09:00","2020-11-02 18:00","2020-11-02 09:00","2020-11-02 18:00","연속"]
[337,"경남","진주","의령S/S 345kV CB 7100","의령S/S 의령-하동T/P#1T/L - TIE CB(7100) 보통점검","의령S/S 의령-하동T/P#1T/L - TIE CB(7100) 보통점검","2020-11-10 10:00","2020-11-10 14:00","2020-11-10 10:00","2020-11-10 14:00","연속"]
[338,"경남","진주","신남원의령#1 T/L","345kV 신남원-의령T/L No.78~86 안전이격거리 확보공사","No.78 철탑 기초 마이크로 파일 시공 관련 안전이격거리 확보차","2020-11-16 07:00","2020-11-19 18:00","취소","취소","매일"]
[339,"경남","진주","신남원의령#2 T/L","345kV 신남원-의령T/L No.78~86 안전이격거리 확보공사","No.78 철탑 기초 마이크로 파일 시공 관련 안전이격거리 확보차","2020-11-20 07:00","2020-11-23 18:00","취소","취소","매일"]
[340,"경남","진주","의령S/S #3 M.Tr","의령S/S #3M.Tr 2차 GIS(6344) 조작시험","의령S/S #3M.Tr 2차 GIS(6344) 조작시험","2020-11-09 10:00","2020-11-09 14:00","2020-11-09 10:00","2020-11-09 14:00","연속"]
[341,"경남","진주","하동T/P 345kV CB 7672","하동T/P #6M.Tr 1차 CB 조작시험","하동T/P #6M.Tr 1차 CB 조작시험","2020-11-12 10:00","2020-11-12 16:00","2020-11-12 10:00","2020-11-12 16:00","연속"]
[342,"경남","통영","고성하이T/P 345kV CB 7100","345kV 고성하이S/Y 건설공사","G1호기 계통병입관련 종합연동시험","2020-11-02 09:00","2020-11-02 18:00","2020-11-02 09:00","2020-11-02 18:00","연속"]
[343,"경남","통영","고성하이T/P 345kV CB 7172","345kV 고성하이S/Y 건설공사","G1호기 계통병입관련 종합연동시험","2020-11-02 09:00","2020-11-02 18:00","2020-11-02 09:00","2020-11-02 18:00","연속"]
[344,"경남","함안","신마산S/S #5 M.Tr","신마산S/S 345kV #5 M.Tr 정밀점검","신마산S/S 345kV #5 M.Tr 정밀점검","2020-11-09 09:30","2020-11-20 18:00","2020-11-09 09:30","2020-11-20 18:00","연속"]
[345,"부산울산","고리","고리N/P #1호기 주변압기 CB (7200, 7272)","고리1호기 제1차 영구정지 정기검사 관련 345kV 스위치야드, A,B계열 설비점검 * 조작차단기 : CB-7200,7272","○ 주변압기 / UAT A,B 일반점검 ○ 주변압기 / UAT A,B 관련 보호계전기 교정, 정주기시험","2020-11-04 17:00","2020-11-11 15:00","2020-11-04 17:00","2020-11-11 15:00","연속"]
[346,"부산울산","고리","고리N/P #1 Tie-Tr CB (7671, 7600)","강압변압기 #1 정밀점검 및 방열기 교체공사","신고리 345kV 변전소내 강압변압기 No.1 정밀점검 및 방열기 교체공사","2020-11-03 13:00","2020-11-18 18:00","2020-11-03 13:00","2020-11-18 18:00","연속"]
[347,"대구","월성","월성N/P #2호기 주변압기 CB (7372, 7300)","월성 2호기 제19차 계획예방정비 관련 짝수모선 휴전작업 *조작차단기 : CB7372,7300","- 짝수모선 휴전작업 - 짝수모선 삼중화 작업으로 인한 변압기 휴전","2020-11-11 09:00","2020-11-12 18:00","2020-11-10 09:00","2020-11-11 18:00","연속"]
[348,"대구","월성","월성N/P #2 기동용변압기 CB (7472, 7400)","월성 2호기 제19차 계획예방정비 관련 홀수모선 휴전작업 *조작차단기 : CB7472,7400","- 홀수모선 휴전작업 - 홀수모선 삼중화 작업으로 인한 변압기 휴전","2020-11-18 19:00","2020-11-20 18:00","2020-11-15 09:00","2020-11-16 18:00","연속"]
[349,"경기북부","직할","양주S/S #2 M.Tr","양주변전소 옥외철구 GIS화 공사","감시제어 시스템 이설(모자이크→SA)","2020-11-16 09:00","2020-11-23 18:00","2020-11-16 09:00","2020-11-23 18:00","연속"]
[350,"대구","월성","월성N/P #2호기 주변압기 CB (7372, 7300)","월성 2호기 제19차 계획예방정비 관련 전원절체시험 *조작차단기 : CB7372,7300","- SST → UST 소내전원절체시험","2020-11-26 09:00","2020-11-28 18:00","2020-11-26 09:00","2020-11-28 18:00","연속"]
[351,"대구","월성","월성N/P #2 기동용변압기 CB (7472, 7400)","월성 2호기 제19차 계획예방정비 관련 전원절체시험 *조작차단기 : CB7472,7400","- UST → SST 소내전원절체시험","2020-11-26 09:00","2020-11-28 18:00","2020-11-26 09:00","2020-11-28 18:00","연속"]

{"sheet":"154송부","index":2,"n_rows":692,"n_cols":11,"rows_kept":692,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2020년도 11월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","은평세종로 T/L","154kV 녹번분기 지중T/L 건설공사","154kV 은평-세종로T/L 1π분기 - 공사후 : 154kV 은평-녹번#2T/L, 154kV 녹번-세종로T/L","2020-11-11 09:00","2021-01-31 18:00","취소","취소","연속"]
[2,"서울","직할","중앙서소문 T/L","20년 직할 170kV GIS 정밀점검공사","GIS 정밀점검","2020-11-23 10:00","2020-11-25 18:00","취소","취소","연속"]
[3,"서울","직할","현저서대문#2 T/L","20년 직할 170kV GIS 정밀점검공사","GIS 정밀점검","2020-11-26 09:00","2020-11-27 18:00","2020-11-23 09:00","2020-11-24 18:00","연속"]
[4,"서울","성동","구의광장#2 T/L","20년 성동 변전정비회사 총액공사","GIS 인출 DS 구동링크 불량보수","2020-11-05 10:00","2020-11-05 18:00","2020-11-05 10:00","2020-11-05 18:00","연속"]
[5,"서울","성동","창동쌍문#1 T/L","쌍문S/S 변전종합예방진단시스템 설치","차단기 동작특성장치 센서 설치 관련 연동시험","2020-11-23 09:30","2020-11-23 14:00","2020-11-23 09:30","2020-11-23 14:00","연속"]
[6,"서울","성동","쌍문미아#2 T/L","쌍문S/S 변전종합예방진단시스템 설치","차단기 동작특성장치 센서 설치","2020-11-17 14:00","2020-11-17 18:00","2020-11-17 14:00","2020-11-17 18:00","연속"]
[7,"서울","성동","양주쌍문#2 T/L","쌍문S/S 변전종합예방진단시스템 설치","차단기 동작특성장치 센서 설치 관련 연동시험","2020-11-16 14:00","2020-11-16 18:00","2020-11-16 14:00","2020-11-16 18:00","연속"]
[8,"서울","성동","창동쌍문#2 T/L","쌍문S/S 변전종합예방진단시스템 설치","차단기 동작특성장치 센서 설치 관련 연동시험","2020-11-23 14:00","2020-11-23 18:00","2020-11-23 14:00","2020-11-23 18:00","연속"]
[9,"서울","성동","양주쌍문#1 T/L","쌍문S/S 변전종합예방진단시스템 설치","차단기 동작특성장치 센서 설치 관련 연동시험","2020-11-16 09:30","2020-11-16 14:00","2020-11-16 09:30","2020-11-16 14:00","연속"]
[10,"서울","성동","창동쌍문#2 T/L","154kV 수유S/S 건설공사","154kV 수유S/S 무부하가압","2020-11-16 09:00","2020-11-21 18:00","2020-11-16 09:00","2020-11-21 18:00","연속"]
[11,"서울","성동","창동돈암 T/L","20년 성동PO 변전정비회사 총액공사","장기미동작 차단기 동작시험","2020-11-10 10:00","2020-11-10 14:00","2020-11-10 10:00","2020-11-10 14:00","연속"]
[12,"서울","성동","창동S/S 154kV CB 6100","20년 성동PO 변전정비회사 총액공사","장기미동작 차단기 동작시험","2020-11-10 14:00","2020-11-10 17:00","2020-11-10 14:00","2020-11-10 17:00","연속"]
[13,"서울","성동","군자화양#2 T/L","20년 성동PO 변전정비회사 총액공사","장기미동작 차단기 동작시험","2020-11-05 10:00","2020-11-05 17:00","2020-11-05 10:00","2020-11-05 17:00","연속"]
[14,"서울","중부","원흥상암 T/L","2020~2021 서울본부 가공송전정비회사 총액공사","불량애자 교체 : 2호","2020-11-03 13:00","2020-11-03 18:00","2020-11-03 13:00","2020-11-03 18:00","연속"]
[15,"서울","중부","수색S/S 154kV #60 BUS","2020년 중부전력지사 170kV GIS 정밀점검(이월분)","수색S/S 수색상암#1T/L GCB 정밀점검 시험가압용","2020-11-25 17:00","2020-11-25 18:00","2020-12-02 17:00","2020-12-02 18:00","연속"]
[16,"서울","중부","수색S/S 154kV CB 6100","2020년 중부전력지사 170kV GIS 정밀점검(이월분)","수색S/S 154kV BUS TIE GCB 정밀점검","2020-11-26 09:00","2020-11-28 18:00","2020-11-26 09:00","2020-11-28 18:00","연속"]
[17,"서울","중부","수색중부#1 T/L","2020년 중부전력지사 170kV GIS 정밀점검(이월분)","수색S/S 154kV BUS TIE GCB 정밀점검 시험가압용","2020-11-28 17:00","2020-11-28 18:00","2020-11-28 17:00","2020-11-28 18:00","연속"]
[18,"서울","중부","수색S/S 154kV #1 BUS","`20 중부PO 변전정비회사 총액공사","수색중부#1TL 모선LS 점검","2020-11-30 08:00","2020-11-30 13:00","취소","취소","연속"]
[19,"서울","중부","수색S/S 154kV #2 BUS","`20 중부PO 변전정비회사 총액공사","수색중부#1TL 모선LS 점검","2020-11-30 13:00","2020-11-30 18:00","취소","취소","연속"]
[20,"서울","중부","원흥수색#1 T/L","2020~2021 서울본부 가공송전정비회사 총액공사","불량애자 교체 : 2호","2020-11-03 08:00","2020-11-03 13:00","2020-11-03 08:00","2020-11-03 13:00","연속"]
[21,"서울","중부","수색상암#1 T/L","2020년 중부전력지사 170kV GIS 정밀점검(이월분)","수색S/S 수색상암#1T/L GCB 정밀점검","2020-11-23 09:00","2020-11-25 18:00","2020-11-30 09:00","2020-12-02 18:00","연속"]
[22,"서울","중부","은평세종로 T/L","154kV 녹번분기 지중T/L 건설공사","154kV 은평-세종로T/L 1π분기 - 공사후 : 154kV 은평-녹번#2T/L, 154kV 녹번-세종로T/L","2020-11-23 09:00","2021-02-12 18:00","2020-11-23 09:00","2021-02-12 18:00","연속"]
[23,"서울","중부","중부S/S 154kV #60 BUS","`20 중부PO 변전정비회사 총액공사","60BUS PT 보통점검","2020-11-02 10:00","2020-11-02 14:00","2020-11-02 10:00","2020-11-02 14:00","연속"]
[24,"서울","중부","중부S/S 154kV SEC CB 60610","`20 중부PO 변전정비회사 총액공사","60-61GIS 조작시험","2020-11-02 10:00","2020-11-02 14:00","2020-11-02 10:00","2020-11-02 14:00","연속"]
[25,"서울","중부","중부S/S 154kV SEC CB 65660","`20 중부PO 변전정비회사 총액공사","65-66GIS 조작시험","2020-11-02 14:00","2020-11-02 18:00","2020-11-02 14:00","2020-11-02 18:00","연속"]
[26,"서울","중부","중부S/S 154kV #65 BUS","`20 중부PO 변전정비회사 총액공사","65BUS PT 보통점검","2020-11-02 14:00","2020-11-02 18:00","2020-11-02 14:00","2020-11-02 18:00","연속"]
[27,"서울","중부","중부S/S 154kV #61 BUS","`20 중부PO 변전정비회사 총액공사","61BUS PT 보통점검","2020-11-03 10:00","2020-11-03 14:00","2020-11-03 10:00","2020-11-03 14:00","연속"]
[28,"서울","중부","중부S/S 154kV #66 BUS","`20 중부PO 변전정비회사 총액공사","66BUS PT 보통점검","2020-11-03 14:00","2020-11-03 18:00","2020-11-03 14:00","2020-11-03 18:00","연속"]
[29,"서울","중부","중부S/S 154kV #65 BUS","345kV 중부S/S #4M.Tr 증설공사","○ 345kV M.Tr(단상 166.7MVA×3대, 송유풍냉식) × 1Bank 설치 ○ 345kV GIS(362kV, 50kA, 4000A) × 1CB 설치 (GIB 포함) ○ 154kV GIS(170kV, 50kA, 2000A, TR) × 1CCT 설치 ○ 25.8kV 친환경개폐장치(25.8kV, 단모선) × 1식 설치","2020-11-23 09:00","2020-11-27 18:00","2020-11-23 09:00","2020-11-27 18:00","연속"]
[30,"서울","중부","중부S/S 154kV #60 BUS","345kV 중부S/S #4M.Tr 증설공사","○ 345kV M.Tr(단상 166.7MVA×3대, 송유풍냉식) × 1Bank 설치 ○ 345kV GIS(362kV, 50kA, 4000A) × 1CB 설치 (GIB 포함) ○ 154kV GIS(170kV, 50kA, 2000A, TR) × 1CCT 설치 ○ 25.8kV 친환경개폐장치(25.8kV, 단모선) × 1식 설치","2020-11-30 09:00","2020-12-05 18:00","2020-11-30 09:00","2020-12-05 18:00","연속"]
[31,"서울","중부","중부S/S 154kV CB 6100","20~21년 중부전력지사 변전정비회사 총액공사","6101, 6109-1 전자변 O-Ring 교체","2020-11-02 14:00","2020-11-05 18:00","2020-11-02 14:00","2020-11-05 18:00","연속"]
[32,"서울","직할","원남미아#1 T/L","20년 직할 변전협력 총액공사","GIS조작시험,전자변교체","2020-11-23 10:00","2020-11-23 18:00","취소","취소","연속"]
[33,"남서울","동서울","강남선릉#2 T/L","170kV GIS 경보회로 로직변경","170kV GIS 경보회로 로직변경","2020-11-04 14:00","2020-11-04 18:00","2020-11-04 14:00","2020-11-04 18:00","연속"]
[34,"남서울","동서울","잠실강남#1 T/L","170kV GIS 경보회로 로직변경","170kV GIS 경보회로 로직변경 접속함 접지선교체(송전부)","2020-11-03 09:00","2020-11-03 13:00","2020-11-03 09:00","2020-11-03 13:00","연속"]
[35,"남서울","동서울","잠실강남#2 T/L","170kV GIS 경보회로 로직변경","170kV GIS 경보회로 로직변경 접속함 접지선교체(송전부)","2020-11-03 13:00","2020-11-03 18:00","2020-11-03 13:00","2020-11-03 18:00","연속"]
[36,"남서울","동서울","강남선릉#1 T/L","170kV GIS 경보회로 로직변경","170kV GIS 경보회로 로직변경","2020-11-04 09:00","2020-11-04 14:00","2020-11-04 09:00","2020-11-04 14:00","연속"]
[37,"남서울","동서울","염곡개포#1 T/L","154kv염곡-개포T/L 지장이설","염곡-개포T/L 지장이설 1. 구 간 및 선종 : M/H#4~#5 약 450m (OF2000) 2회선 2. 공사기간 (케이블) 20년 08월 ~ 20년 12월 3. 이설 비용 : 서초구청 4. 시공업체 : LS전선 5. 특이사항 : 기존 관로경과지에 전력구 신설","2020-11-30 09:00","2021-01-22 18:00","2020-11-30 09:00","2021-01-22 18:00","연속"]
[38,"남서울","동서울","동서울신장#2 T/L","세종-포천고속도로건설 지장송전선로 지중화(이설)공사","지중화공사를 위한 가철탑건설 공사 시행","2020-11-02 09:00","2020-11-08 18:00","2020-11-02 09:00","2020-11-08 18:00","연속"]
[39,"남서울","동서울","동서울S/S 154kV #61 BUS","동서울S/S 345kV 노후 주변압기 교체공사","○ 345kV M.Tr 7대 교체 ○ 기타 부대작업 1식","2020-11-24 13:00","2020-11-24 16:00","2020-11-27 13:00","2020-11-27 16:00","연속"]
[40,"남서울","동서울","동서울신장#1 T/L","EBA 부분방전 진단센서 설치공사","PD센서 12개 설치 및 Test Box 설치","2020-11-19 09:00","2020-11-20 18:00","2020-11-19 09:00","2020-11-20 18:00","연속"]
[41,"남서울","동서울","동서울가락#1 T/L","170kV GCB 조작시험","170kV GCB 조작시험","2020-11-05 09:00","2020-11-05 18:00","2020-11-05 09:00","2020-11-05 18:00","연속"]
[42,"남서울","동서울","강동상일#1 T/L","154kV 상일S/S #4M.Tr 증설공사","*154kV #4M.Tr 증설관련 무부하가압* - 170kV GIS * 1CCT - 154kV M.Tr * 1BANK - 25.8kV GIS * 4CCT","2020-11-07 09:00","2020-11-08 18:00","2020-11-07 09:00","2020-11-08 18:00","연속"]
[43,"남서울","동서울","상일S/S 154kV #1 BUS","154kV 상일S/S #4M.Tr 증설공사","*154kV #4M.Tr 증설관련 무부하가압* - 170kV GIS * 1CCT - 154kV M.Tr * 1BANK - 25.8kV GIS * 4CCT","2020-11-07 09:00","2020-11-08 18:00","2020-11-07 09:00","2020-11-08 18:00","연속"]
[44,"남서울","동서울","산성수서#2 T/L","EBA 부분방전 진단센서 설치공사","PD센서 18개 및 Test Box 3개소 설치","2020-11-16 09:00","2020-11-18 18:00","2020-11-16 09:00","2020-11-18 18:00","연속"]
[45,"남서울","동서울","산성수서#1 T/L","EBA 부분방전 진단센서 설치공사","PD센서 18개 및 Test Box 3개소 설치","2020-11-09 09:00","2020-11-13 18:00","2020-11-09 09:00","2020-11-13 18:00","연속"]
[46,"남서울","동서울","신장덕소#1 T/L","EBA 부분방전 진단센서 설치공사","PD센서 12개 및 Test Box 설치","2020-11-23 09:00","2020-11-24 18:00","2020-11-23 09:00","2020-11-24 18:00","연속"]
[47,"남서울","동서울","신장덕소#2 T/L","EBA 부분방전 진단센서 설치공사","PD센서 12개 및 Test Box 설치","2020-11-25 09:00","2020-11-26 18:00","2020-11-25 09:00","2020-11-26 18:00","연속"]
[48,"남서울","동서울","잠실수서#1 T/L","EBA 부분방전 진단센서 설치공사","PD센서 6개 및 Test Box 설치","2020-11-30 09:00","2020-12-01 18:00","2020-11-30 09:00","2020-12-01 18:00","연속"]
[49,"남서울","영등포","가양등촌#1 T/L","154kV 가양-등촌T/L 일부구간 지장이설공사","○ 지중송전 : 154kV OF 1200 x 2C x 0.320km 신설 및 철거 ○ 비금속광케이블(OFC) 신설 및 철거 ○ 관로 320m 신설 및 철거(요청자 시행)","2020-11-09 09:00","2020-12-16 18:00","취소","취소","연속"]
[50,"남서울","영등포","천왕구로#1 T/L","154kV 천왕∼구로, 오류 송전선로 이설공사","154kV 천왕∼구로, 오류 송전선로 이설공사","2020-11-10 09:00","2020-12-10 18:00","2020-11-10 09:00","2020-12-10 18:00","연속"]
[51,"남서울","영등포","천왕구로#2 T/L","154kV 천왕∼구로, 오류 송전선로 이설공사","154kV 천왕∼구로, 오류 송전선로 이설공사","2020-11-10 09:00","2020-12-10 18:00","2020-11-10 09:00","2020-12-10 18:00","연속"]
[52,"남서울","영등포","독산대방#2 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-11-29 09:00","2020-11-30 18:00","2020-10-31 09:00","2020-11-01 18:00","연속"]
[53,"남서울","영등포","대방신길#2 T/L","154kV 대방인출전력구 OF케이블 선종교체공사","대방 인출전력구 내 154kV 대방-신길#2T/L 선종교체 공사 - 구간 : 대방S/S~J/B#38 - 교체전 : OF 1200, 교체후 : XLPE 1200","2020-11-16 09:00","2020-12-27 18:00","취소","취소","연속"]
[54,"남서울","영등포","시흥독산#1 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-11-01 09:00","2020-11-06 18:00","2020-11-02 09:00","2020-11-07 18:00","연속"]
[55,"남서울","영등포","시흥독산#2 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-11-09 09:00","2020-11-14 18:00","2020-11-09 09:00","2020-11-14 18:00","연속"]
[56,"남서울","영등포","시흥S/S 154kV #2 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-11-27 14:00","2020-11-28 14:00","2020-11-27 14:00","2020-11-28 14:00","연속"]
[57,"남서울","영등포","시흥S/S 154kV #1 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-11-04 09:00","2020-11-05 14:00","2020-11-04 09:00","2020-11-05 14:00","연속"]
[58,"남서울","영등포","시흥S/S 154kV #2 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-11-05 14:00","2020-11-06 14:00","2020-11-05 14:00","2020-11-06 14:00","연속"]
[59,"남서울","영등포","시흥S/S 154kV #1 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-11-12 09:00","2020-11-13 14:00","2020-11-12 09:00","2020-11-13 14:00","연속"]
[60,"남서울","영등포","시흥S/S 154kV #2 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-11-13 14:00","2020-11-14 14:00","2020-11-13 14:00","2020-11-14 14:00","연속"]
[61,"남서울","영등포","시흥S/S 154kV #1 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-11-16 09:00","2020-11-17 14:00","2020-11-16 09:00","2020-11-17 14:00","연속"]
[62,"남서울","영등포","시흥S/S 154kV #2 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-11-17 14:00","2020-11-18 14:00","2020-11-17 14:00","2020-11-18 14:00","연속"]
[63,"남서울","영등포","시흥독산#1 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","#1M.Tr 1차 무부하가압용","2020-11-17 14:00","2020-11-17 15:00","2020-11-17 14:00","2020-11-17 15:00","연속"]
[64,"남서울","영등포","시흥독산#1 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","#1M.Tr 1차 무부하가압용","2020-11-18 14:00","2020-11-18 15:00","2020-11-18 14:00","2020-11-18 15:00","연속"]
[65,"남서울","영등포","시흥독산#2 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","#4M.Tr 1차 무부하가압용","2020-11-28 14:00","2020-11-28 15:00","2020-11-28 14:00","2020-11-28 15:00","연속"]
[66,"남서울","영등포","시흥독산#2 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","#4M.Tr 1차 무부하가압용","2020-11-27 14:00","2020-11-27 15:00","2020-11-27 14:00","2020-11-27 15:00","연속"]
[67,"남서울","영등포","시흥S/S 154kV #1 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-11-26 09:00","2020-11-27 14:00","2020-11-26 09:00","2020-11-27 14:00","연속"]
[68,"남서울","영등포","시흥독산#1 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","#3M.Tr 1차 무부하가압용","2020-11-25 14:00","2020-11-25 15:00","2020-11-25 14:00","2020-11-25 15:00","연속"]
[69,"남서울","영등포","시흥독산#1 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","#3M.Tr 1차 무부하가압용","2020-11-24 14:00","2020-11-24 15:00","2020-11-24 14:00","2020-11-24 15:00","연속"]
[70,"남서울","영등포","시흥S/S 154kV #2 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-11-24 14:00","2020-11-25 14:00","2020-11-24 14:00","2020-11-25 14:00","연속"]
[71,"남서울","영등포","시흥S/S 154kV #1 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-11-23 09:00","2020-11-24 14:00","2020-11-23 09:00","2020-11-24 14:00","연속"]
[72,"남서울","영등포","시흥독산#2 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","#2M.Tr 1차 무부하가압용","2020-11-21 14:00","2020-11-21 15:00","2020-11-21 14:00","2020-11-21 15:00","연속"]
[73,"남서울","영등포","시흥S/S 154kV #2 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-11-20 14:00","2020-11-21 14:00","2020-11-20 14:00","2020-11-21 14:00","연속"]
[74,"남서울","영등포","시흥독산#2 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","#2M.Tr 1차 무부하가압용","2020-11-20 14:00","2020-11-20 15:00","2020-11-20 14:00","2020-11-20 15:00","연속"]
[75,"남서울","영등포","시흥S/S 154kV #1 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-11-19 09:00","2020-11-20 14:00","2020-11-19 09:00","2020-11-20 14:00","연속"]
[76,"남서울","영등포","양평양천#2 T/L","154kV양평-양천T/L 선종교체공사","○ 위 치 : 양평, 양천S/S 및 목동공동구, 맨홀·전력구 ○ 구 간 : 양평S/S ∼양천S/S ○ 케이블 철거 : 154㎸ OF 1200㎟ × 1회선(D), 2.542㎞ ○ 주요공종 - 포설구간 : XLPE 1200㎟(D) × 5구간×2C(1.46km), XLPE 2000㎟(S) × 3구간 ×2C(1.1km) - 케이블 접속 : 14개소","2020-11-02 09:00","2021-03-26 18:00","취소","취소","연속"]
[77,"남서울","영등포","천왕오류#2 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2020-11-07 09:00","2020-11-08 18:00","2020-11-07 09:00","2020-11-08 18:00","연속"]
[78,"남서울","영등포","중동화곡#1 T/L","화곡S/S 170kV GIS 조작시험(중동-화곡#1,2)","- 차단기 개폐타임 측정 - GIS 조작 - 러버히터 설","2020-11-02 09:00","2020-11-02 14:00","2020-11-21 09:00","2020-11-21 14:00","연속"]
[79,"남서울","영등포","고강화곡#2 T/L","화곡S/S 170kV GIS 조작시험(고강-화곡#2)","- 차단기 개폐타임 측정 - GIS 조작 - 러버히터 설치","2020-11-03 09:00","2020-11-03 18:00","2020-11-14 09:00","2020-11-14 18:00","연속"]
[80,"남서울","영등포","중동화곡#2 T/L","화곡S/S 170kV GIS 조작시험(중동-화곡#1,2)","- 차단기 개폐타임 측정 - GIS 조작 - 러버히터 설치","2020-11-02 14:00","2020-11-02 18:00","2020-11-21 14:00","2020-11-21 18:00","연속"]
[81,"남서울","영등포","화곡마곡#2 T/L","화곡S/S 170kV GIS 조작시험(화곡-마곡#2)","- 차단기 개폐타임 측정 - GIS 조작","2020-11-10 09:00","2020-11-10 18:00","취소","취소","연속"]
[82,"남서울","직할","영등포영오#2 T/L","170kV GIS 정밀점검공사","영오S/S 영등포-영오#2T/L GIS CB(627) 정밀점검(전자변교체 포함) (무부하:상대단 변전소)","2020-11-04 14:00","2020-11-06 18:00","2020-11-04 14:00","2020-11-06 18:00","연속"]
[83,"남서울","직할","영오S/S 154kV CB 6100","170kV GIS 정밀점검공사","영오S/S #60-#65 BUS TIE GIS(6100) 정밀점검(전자변교체 포함)","2020-11-23 09:00","2020-11-25 14:00","2020-11-23 09:00","2020-11-25 14:00","연속"]
[84,"남서울","직할","영오S/S 154kV #1 BUS","170kV GIS 정밀점검공사(TIE 점검시 BUS절체불가)","TIE 정밀점검시 BUS 절체불가[영오S/S #60-#65 BUS TIE GIS(6100) 정밀점검 관련]","2020-11-23 09:00","2020-11-25 14:00","2020-11-23 09:00","2020-11-25 14:00","연속"]
[85,"남서울","직할","영등포영오#1 T/L","170kV GIS 정밀점검공사","영오S/S 영등포-영오#1T/L GIS CB(617) 정밀점검(전자변교체 포함) (무부하:상대단 변전소)","2020-11-02 09:00","2020-11-04 14:00","2020-11-02 09:00","2020-11-04 14:00","연속"]
[86,"남서울","직할","영오S/S 154kV #1 BUS","170kV GIS 정밀점검공사(무부하용)","무부하 가압용[영오S/S #1M.Tr GIS(6133) 정밀점검 관련]","2020-11-18 09:00","2020-11-18 14:00","2020-11-18 09:00","2020-11-18 14:00","연속"]
[87,"남서울","직할","영오S/S 154kV #2 BUS","170kV GIS 정밀점검공사(무부하용)","무부하 가압용[영오S/S #2M.Tr GIS(6233) 정밀점검 관련]","2020-11-20 09:00","2020-11-20 19:00","2020-11-20 09:00","2020-11-20 19:00","연속"]
[88,"남서울","영등포","화곡S/S 154kV #1 BUS","154kV 고강-화곡(증) 지중T/L 건설공사","XLPE 2000/1200㎟ 1C-2.4km","2020-11-07 14:00","2020-11-07 15:00","2020-11-07 14:00","2020-11-07 15:00","연속"]
[89,"남서울","영등포","중동화곡#1 T/L","154kV 고강-화곡(증) 지중T/L 건설공사","XLPE 2000/1200㎟ 1C-2.4km","2020-11-07 14:00","2020-11-08 15:00","2020-11-07 14:00","2020-11-08 15:00","연속"]
[90,"남서울","영등포","화곡S/S 154kV #2 BUS","154kV 고강-화곡(증) 지중T/L 건설공사","XLPE 2000/1200㎟ 1C-2.4km","2020-11-07 15:00","2020-11-08 15:00","2020-11-07 15:00","2020-11-08 15:00","연속"]
[91,"인천","부평","서인천C/C 154kV CB 6833","서인천복합S/Y 170kV #8G.Tr(6833) GIS 조작시험 공사","서인천복합S/Y 170kV #8G.Tr(6833) GIS 조작시험 공사","2020-11-10 14:00","2020-11-10 18:00","2020-11-10 14:00","2020-11-10 18:00","연속"]
[92,"인천","부평","서인천C/C 154kV CB 6733","서인천복합S/Y 170kV #7G.Tr(6733) GIS 조작시험 공사","서인천복합S/Y 170kV #7G.Tr(6733) GIS 조작시험 공사","2020-11-10 09:00","2020-11-10 14:00","2020-11-10 09:00","2020-11-10 14:00","연속"]
[93,"인천","부평","송현포스코CC#2 T/L","송현S/S 송현포스코CC#2T/L GIS 보통점검 공사","송현S/S 송현포스코CC#2T/L GIS 보통점검 공사","2020-11-12 09:00","2020-11-12 18:00","2020-11-12 09:00","2020-11-12 18:00","연속"]
[94,"인천","부평","송현포스코CC#1 T/L","송현S/S 송현포스코CC#1T/L GIS 보통점검 공사","송현S/S 송현포스코CC#1T/L GIS 보통점검 공사","2020-11-11 09:00","2020-11-11 18:00","2020-11-11 09:00","2020-11-11 18:00","연속"]
[95,"인천","부평","신가좌S/S 154kV SEC CB 60610","신가좌S/S 154kV #60-#61 SEC GIS 보통점검 공사","신가좌S/S 154kV #60-#61 SEC GIS 보통점검 공사","2020-11-16 09:00","2020-11-16 18:00","2020-11-16 09:00","2020-11-16 18:00","연속"]
[96,"인천","부평","신가좌인천#1 T/L","신가좌S/S 신가좌인천#1T/L 보호반 교체 공사","신가좌S/S 신가좌인천#1T/L 보호반 교체 공사","2020-11-02 09:00","2020-11-06 18:00","2020-11-02 09:00","2020-11-06 18:00","연속"]
[97,"인천","부평","신가좌S/S 154kV SEC CB 61620","신가좌S/S 154kV #61-#62 SEC GIS 보통점검 공사","신가좌S/S 154kV #61-#62 SEC GIS 보통점검 공사","2020-11-17 09:00","2020-11-17 18:00","2020-11-17 09:00","2020-11-17 18:00","연속"]
[98,"인천","부평","신가좌S/S 154kV SEC CB 65660","신가좌S/S 154kV #65-#66 SEC GIS 보통점검 공사","신가좌S/S 154kV #65-#66 SEC GIS 보통점검 공사","2020-11-18 09:00","2020-11-18 18:00","2020-11-18 09:00","2020-11-18 18:00","연속"]
[99,"인천","부평","신가좌S/S 154kV SEC CB 66670","신가좌S/S 154kV #66-#67 SEC GIS 보통점검 공사","신가좌S/S 154kV #66-#67 SEC GIS 보통점검 공사","2020-11-19 09:00","2020-11-19 18:00","2020-11-19 09:00","2020-11-19 18:00","연속"]
[100,"인천","부평","신가좌S/S 154kV CB 6100","신가좌S/S 6100 GIS 보통점검 공사","신가좌S/S 6100 GIS 보통점검 공사","2020-11-25 09:00","2020-11-25 18:00","2020-11-25 09:00","2020-11-25 18:00","연속"]
[101,"인천","부평","신가좌S/S 154kV CB 6300","신가좌S/S 6300 GIS 보통점검 공사","신가좌S/S 6300 GIS 보통점검 공사","2020-11-26 09:00","2020-11-26 18:00","2020-11-26 09:00","2020-11-26 18:00","연속"]
[102,"인천","부평","신가좌부개#1 T/L","신가좌S/S 신가좌부개#1T/L GIS 보통점검 공사","신가좌S/S 신가좌부개#1T/L GIS 보통점검 공사","2020-11-30 09:00","2020-11-30 18:00","2020-11-30 09:00","2020-11-30 18:00","연속"]
[103,"인천","부평","신가좌부개#2 T/L","신가좌S/S 신가좌부개#2T/L GIS 보통점검 공사","신가좌S/S 신가좌부개#2T/L GIS 보통점검 공사","2020-11-30 09:00","2020-11-30 18:00","2020-11-30 09:00","2020-11-30 18:00","연속"]
[104,"인천","부평","원창포스코CC#2 T/L","원창S/S 원창포스코#2T/L GIS 보통점검 공사","원창S/S 원창포스코#2T/L GIS 보통점검 공사","2020-11-27 09:00","2020-11-27 18:00","2020-11-27 09:00","2020-11-27 18:00","연속"]
[105,"인천","부평","원창포스코CC#1 T/L","원창S/S 원창포스코#1T/L GIS 보통점검 공사","원창S/S 원창포스코#1T/L GIS 보통점검 공사","2020-11-26 09:00","2020-11-26 18:00","2020-11-26 09:00","2020-11-26 18:00","연속"]
[106,"인천","부평","인천CC포스코CC#2 T/L","인천복합S/Y 인천CC포스코CC#2T/L GIS 정밀점검 공사","인천복합S/Y 인천CC포스코CC#2T/L GIS 정밀점검 공사","2020-11-05 09:00","2020-11-07 18:00","2020-11-05 09:00","2020-11-07 18:00","연속"]
[107,"인천","부평","인천CC북인천#1 T/L","인천복합S/Y 인천CC포스코CC#1T/L GIS 정밀점검 무부하 가압용","인천복합S/Y 인천CC포스코CC#1T/L GIS 정밀점검 무부하 가압용","2020-11-04 13:00","2020-11-04 18:00","2020-11-04 13:00","2020-11-04 18:00","연속"]
[108,"인천","부평","인천CC북인천#2 T/L","인천복합S/Y 인천CC포스코CC#2T/L GIS 무부하가압용","인천복합S/Y 인천CC포스코CC#2T/L GIS 무부하가압용","2020-11-07 13:00","2020-11-07 18:00","2020-11-07 13:00","2020-11-07 18:00","연속"]
[109,"인천","부평","인천C/C 154kV #61 BUS","인천복합S/Y 인천CC포스코CC#1T/L GIS 정밀점검 무부하 가압용","인천복합S/Y 인천CC포스코CC#1T/L GIS 정밀점검 무부하 가압용","2020-11-04 13:00","2020-11-04 18:00","2020-11-04 13:00","2020-11-04 18:00","연속"]
[110,"인천","부평","인천CC포스코CC#1 T/L","인천복합S/Y 인천CC포스코CC#1 T/L GIS 정밀점검 공사","인천복합S/Y 인천CC포스코CC#1 T/L GIS 정밀점검 공사","2020-11-02 09:00","2020-11-04 18:00","2020-11-02 09:00","2020-11-04 18:00","연속"]
[111,"인천","부평","인천C/C 154kV #65 BUS","인천복합S/Y 인천CC포스코CC#2T/L GIS 무부하가압용","인천복합S/Y 인천CC포스코CC#2T/L GIS 무부하가압용","2020-11-07 13:00","2020-11-07 18:00","2020-11-07 13:00","2020-11-07 18:00","연속"]
[112,"인천","시흥","남동연수#2 T/L","154kV 남동-연수#2T/L 절연유 열화진단","154kV 남동-연수#2T/L 절연유 열화진단","2020-11-04 09:00","2020-11-05 18:00","2020-11-04 09:00","2020-11-05 18:00","연속"]
[113,"인천","시흥","남동연수#1 T/L","154kV 남동-연수#1T/L 절연유 열화진단","154kV 남동-연수#1T/L 절연유 열화진단","2020-11-02 09:00","2020-11-03 18:00","2020-11-02 09:00","2020-11-03 18:00","연속"]
[114,"인천","시흥","시화동시화#1 T/L","154kV 동시화S/S GIS 설치공사","154kV GIS 2CCT 증설관련 무부하 가압 (TR BAY, BUS TIE)","2020-11-20 18:00","2020-11-21 18:00","2020-11-20 18:00","2020-11-21 18:00","연속"]
[115,"인천","시흥","동시화남시화 T/L","154kV 동시화S/S GIS 설치공사","154kV GIS 2CCT 증설 (TR BAY, BUS TIE)","2020-11-02 09:30","2020-11-04 18:00","2020-11-02 09:30","2020-11-04 18:00","연속"]
[116,"인천","시흥","시화동시화#1 T/L","154kV 동시화S/S GIS 설치공사","154kV GIS 2CCT 증설관련 무부하 가압 (TR BAY, BUS TIE)","2020-11-10 18:00","2020-11-11 18:00","2020-11-10 18:00","2020-11-11 18:00","연속"]
[117,"인천","시흥","동시화남시화 T/L","154kV 동시화S/S GIS 설치공사","154kV GIS 2CCT 증설 (TR BAY, BUS TIE)","2020-11-12 09:30","2020-11-14 18:00","2020-11-12 09:30","2020-11-14 18:00","연속"]
[118,"인천","시흥","동시화서시화 T/L","154kV 동시화S/S GIS 설치공사","154kV GIS BUS SEC 증설","2020-11-23 09:30","2020-11-26 18:00","2020-11-23 09:30","2020-11-26 18:00","연속"]
[119,"인천","시흥","북시화서시화#3 T/L","북시화SA혼용화공사(북시화서시화#3T/L휴전)","북시화SA혼용화공사(북시화서시화#3T/L휴전)","2020-11-06 10:00","2020-11-06 18:00","2020-11-06 10:00","2020-11-06 18:00","연속"]
[120,"인천","시흥","신시흥북시화#1 T/L","북시화SA혼용화공사(신시흥북시화#1T/L휴전)","북시화SA혼용화공사(신시흥북시화#1T/L휴전)","2020-11-02 10:00","2020-11-02 18:00","2020-11-02 10:00","2020-11-02 18:00","연속"]
[121,"인천","시흥","북시화서시화#1 T/L","북시화SA혼용화공사(북시화서시화#1T/L휴전)","북시화SA혼용화공사(북시화서시화#1T/L휴전)","2020-11-04 10:00","2020-11-04 18:00","2020-11-04 10:00","2020-11-04 18:00","연속"]
[122,"인천","시흥","신시흥북시화#2 T/L","북시화SA혼용화공사(신시흥북시화#2T/L휴전)","북시화SA혼용화공사(신시흥북시화#2T/L휴전)","2020-11-03 10:00","2020-11-03 18:00","2020-11-03 10:00","2020-11-03 18:00","연속"]
[123,"인천","시흥","북시화서시화#2 T/L","북시화SA혼용화공사(북시화서시화#2T/L휴전)","북시화SA혼용화공사(북시화서시화#2T/L휴전)","2020-11-05 10:00","2020-11-05 18:00","2020-11-05 10:00","2020-11-05 18:00","연속"]
[124,"인천","시흥","서서울#2소래 T/L","154kV 서서울-소래T/L 현수애자 절연성능진단","154kV 서서울-소래T/L 현수애자 절연성능진단(불량애자검출) - 강관/관형주 철탑 사선상태 휴전작업 - 작업대상 : No.47,60,62,73(4기)","2020-11-10 13:00","2020-11-10 18:00","2020-11-10 13:00","2020-11-10 18:00","연속"]
[125,"인천","시흥","서안양소래 T/L","154kV 서서울-소래T/L 현수애자 절연성능진단","154kV 서서울-소래T/L 현수애자 절연성능진단(불량애자검출) - 강관/관형주 철탑 사선상태 휴전작업 - 작업대상 : No.60,62,73(3기)","2020-11-10 08:00","2020-11-10 13:00","2020-11-10 08:00","2020-11-10 13:00","연속"]
[126,"인천","시흥","신시흥시화#2 T/L","154kV 신시흥-시화T/L 추락방지시설 설치공사","154kV 신시흥-시화T/L 추락방지시설 설치공사(No.12,13)","2020-11-09 13:00","2020-11-09 18:00","2020-11-09 13:00","2020-11-09 18:00","연속"]
[127,"인천","시흥","신시흥시화#1 T/L","154kV 신시흥-시화T/L 추락방지시설 설치공사","154kV 신시흥-시화T/L 추락방지시설 설치공사(No.12,13)","2020-11-09 08:00","2020-11-09 13:00","2020-11-09 08:00","2020-11-09 13:00","연속"]
[128,"인천","시흥","도림오봉#1 T/L","오봉S/S 154kV 도림오봉#1T/L GIS보통점검","오봉S/S 154kV 도림오봉#1T/L GIS보통점검","2020-11-07 09:00","2020-11-07 18:00","2020-11-07 09:00","2020-11-07 18:00","연속"]
[129,"인천","시흥","도림오봉#2 T/L","오봉S/S 154kV 도림오봉#2T/L GIS보통점검","오봉S/S 154kV 도림오봉#2T/L GIS보통점검","2020-11-14 09:00","2020-11-14 18:00","2020-11-14 09:00","2020-11-14 18:00","연속"]
[130,"인천","직할","계양원창 T/L","345kV신가좌-가정#2T/L 정밀점검","345kV신가좌-가정#2T/L 정밀점검 시행을 위한 병가선로 휴전","2020-11-23 09:30","2020-11-23 13:00","2020-11-23 09:30","2020-11-23 13:00","연속"]
[131,"인천","직할","신부평고강#2 T/L","154kV 신부평-고강T/L 케이블헤드 및 피뢰기 점검","154kV 신부평-고강T/L 케이블헤드 및 피뢰기 점검(원종C/H)","2020-11-14 14:00","2020-11-14 18:00","취소","취소","연속"]
[132,"인천","직할","신부평고강#1 T/L","154kV 신부평-고강T/L 케이블헤드 및 피뢰기 점검","154kV 신부평-고강T/L 케이블헤드 및 피뢰기 점검(원종C/H)","2020-11-14 09:00","2020-11-14 14:00","취소","취소","연속"]
[133,"인천","직할","부천도당#1 T/L","도당,부천S/S 도당부천#1T/L 170kV GIS 초기점검,강화조작시험","도당,부천S/S 도당부천#1T/L 170kV GIS 초기점검,강화조작시험 도당(초기), 부천(강화조작)","2020-11-09 09:30","2020-11-09 18:00","취소","취소","연속"]
[134,"인천","직할","부천도당#2 T/L","도당,부천S/S 도당부천#2T/L 170kV GIS 초기점검,강화조작시험","도당,부천S/S 도당부천#2T/L 170kV GIS 초기점검,강화조작시험 도당(초기), 부천(강화조작)","2020-11-10 09:30","2020-11-10 18:00","취소","취소","연속"]
[135,"경기북부","고양","능곡상암#1 T/L","세니온제 송전선로 보호반 성능개선 공사","IED 펌웨어 업데이트 : 43PDA, 거리계전기 오동작 방지, 검 출 전류 기준값 변경등","2020-11-19 09:00","2020-11-19 18:00","취소","취소","연속"]
[136,"경기북부","고양","신덕은문산#1 T/L","'20~'21년 고양전력지사 변전정비회사 총액공사","송전선로 보호배전반 교체공사","2020-11-24 09:00","2020-11-26 18:00","취소","취소","연속"]
[137,"경기북부","고양","문산월롱#2 T/L","2020년도 가공송전 순시점검 위탁공사","송전설비 초기점검","2020-11-04 08:00","2020-11-04 18:00","2020-11-04 08:00","2020-11-04 18:00","연속"]
[138,"경기북부","고양","문산월롱#1 T/L","2020년도 가공송전 순시점검 위탁공사","송전설비 초기점검","2020-11-25 08:00","2020-11-25 18:00","2020-11-25 08:00","2020-11-25 18:00","연속"]
[139,"경기북부","고양","백학남면#2 T/L","2020년 가공송전선로 순시점검 위탁공사","피뢰기 특별점검","2020-11-18 08:00","2020-11-20 18:00","2020-11-18 08:00","2020-11-20 18:00","연속"]
[140,"경기북부","고양","신덕은문산#2 T/L","154kV 신덕은-문산#2T/L 발열개소 방식층 재조립","154kV 신덕은-문산#2T/L 발열개소 방식층 재조립","2020-11-03 09:00","2020-11-05 18:00","취소","취소","연속"]
[141,"경기북부","고양","신덕은금촌#1 T/L","2020년 고양P/O 변전정비 총액공사","2020년 170kV GIS 조작시험","2020-11-06 14:00","2020-11-06 16:00","2020-11-06 14:00","2020-11-06 16:00","연속"]
[142,"경기북부","고양","신파주문발#2 T/L","2020년 고양P/O 변전정비 총액공사","2020년 170kV GIS 조작시험","2020-11-06 10:00","2020-11-06 12:00","2020-11-06 10:00","2020-11-06 12:00","연속"]
[143,"경기북부","고양","신파주원흥#1 T/L","2020년 고양P/O 변전정비 총액공사","2020년 170kV GIS 조작시험","2020-11-23 10:00","2020-11-23 12:00","2020-11-23 10:00","2020-11-23 12:00","연속"]
[144,"경기북부","고양","신파주원흥#2 T/L","2020년 고양P/O 변전정비 총액공사","2020년 170kV GIS 조작시험","2020-11-23 13:00","2020-11-23 15:00","2020-11-23 13:00","2020-11-23 15:00","연속"]
[145,"경기북부","고양","일산지도#1 T/L","2020년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사 - 60-65 BUS PT Bay 시험가압(65BUS측)","2020-11-18 17:00","2020-11-19 17:00","2020-11-16 17:00","2020-11-17 09:00","연속"]
[146,"경기북부","고양","일산S/S 154KV #65 BUS","2020년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(60-65 PT Bay)","2020-11-14 09:00","2020-11-19 17:00","2020-11-13 09:00","2020-11-17 10:00","연속"]
[147,"경기북부","고양","일산호수#2 T/L","2020년 고양P/O 변전정비 총액공사","2020년 170kV GIS 조작시험","2020-11-12 10:00","2020-11-12 12:00","2020-11-05 10:00","2020-11-05 18:00","연속"]
[148,"경기북부","고양","일산송포#2 T/L","지중송전설비 위탁정비공사","154kV 일산-송포#2T/L OF케이블 절연유 열화진단","2020-11-25 09:00","2020-11-25 18:00","2020-11-25 09:00","2020-11-25 18:00","연속"]
[149,"경기북부","고양","일산S/S 154kV SEC CB 60610","170kV GIS 조작시험-변전총액공사","일산S/S 60-61 SEC 차단기 개폐타임 측정 및 조작시험","2020-11-11 10:00","2020-11-11 18:00","2020-11-11 10:00","2020-11-11 18:00","연속"]
[150,"경기북부","고양","일산S/S 154KV #65 BUS","2020년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(60-65 PT Bay)","2020-11-09 09:00","2020-11-10 13:00","2020-11-09 09:00","2020-11-10 09:00","연속"]
[151,"경기북부","고양","일산S/S 154KV #60 BUS","2020년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(60-65 PT Bay)","2020-11-10 13:00","2020-11-14 09:00","2020-11-10 09:00","2020-11-13 09:00","연속"]
[152,"경기북부","고양","일산지도#1 T/L","2020년 고양전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사 - 60-65 BUS PT Bay 시험가압(60BUS측)","2020-11-13 17:00","2020-11-14 09:00","2020-11-12 17:00","2020-11-13 09:00","연속"]
[153,"경기북부","고양","일산송포#1 T/L","지중송전설비 위탁정비공사","154kV 일산-송포#1T/L OF케이블 절연유 열화진단","2020-11-24 09:00","2020-11-24 18:00","2020-11-24 09:00","2020-11-24 18:00","연속"]
[154,"경기북부","고양","지도능곡#2 T/L","지중송전설비 위탁정비공사","154kV 지도-능곡#2T/L OF케이블 절연유 열화진단","2020-11-03 09:00","2020-11-03 18:00","2020-11-03 10:00","2020-11-03 14:00","연속"]
[155,"경기북부","고양","지도능곡#1 T/L","154kV 지도-능곡#1T/L OF케이블 선종교체공사","지도S/S, 능곡S/S EBG구간 OF케이블 → XLPE케이블 선종교체공사","2020-11-04 09:00","2020-12-16 18:00","2020-11-03 14:00","2020-11-03 18:00","연속"]
[156,"경기북부","구리","덕소진건#2 T/L","19-20년도 경기북부 직할 지중송전설비 위탁정비공사","피뢰기, C/H 점검(Doble Test)","2020-11-20 09:00","2020-11-20 18:00","2020-11-20 09:00","2020-11-20 18:00","연속"]
[157,"경기북부","구리","덕소진건#1 T/L","19-20년도 경기북부 직할 지중송전설비 위탁정비공사","피뢰기, C/H 점검(Doble Test)","2020-11-19 09:00","2020-11-19 18:00","2020-11-19 09:00","2020-11-19 18:00","연속"]
[158,"경기북부","구리","마석S/S 154kV #1 BUS","'20-21년 구리전력지사 변전정비회사 총액공사","장기사용 배전반 교체공사 - 마석S/S CPD반 교체","2020-11-23 09:00","2020-11-23 18:00","2020-11-23 09:00","2020-11-23 18:00","연속"]
[159,"경기북부","구리","마석S/S 154kV #2 BUS","'20-21년 구리전력지사 변전정비회사 총액공사","장기사용 배전반 교체공사 - 마석S/S CPD반 교체","2020-11-24 09:00","2020-11-24 18:00","2020-11-24 09:00","2020-11-24 18:00","연속"]
[160,"경기북부","구리","미금S/S 154kV CB 6300","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - #62-67 BUS TIe GIS 관련 감시제어계측 포인트이관 (→SA) - #62-67 BUS TIe GIS LCP 및 모자익반 제어케이블 철거 및 재결선","2020-11-02 09:00","2020-11-06 18:00","취소","취소","연속"]
[161,"경기북부","구리","미금S/S 154kV SEC CB 66670","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - #66-67 BUS SEC GIS 관련 감시제어계측 포인트이관 (→SA) - #66-67 BUS SEC GIS LCP 및 모자익반 제어케이블 철거 및 재결선","2020-11-02 09:00","2020-11-06 18:00","취소","취소","연속"]
[162,"경기북부","구리","미금S/S 154kV SEC CB 65660","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - #65-66 BUS SEC GIS 관련 감시제어계측 포인트이관 (→SA) - #65-66 BUS SEC GIS LCP 및 모자익반 제어케이블 철거 및 재결선","2020-11-09 09:00","2020-11-13 18:00","취소","취소","연속"]
[163,"경기북부","구리","미금S/S 154kV SEC CB 61620","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - #61-62 BUS SEC GIS 관련 감시제어계측 포인트이관 (→SA) - #61-62 BUS SEC GIS LCP 및 모자익반 제어케이블 철거 및 재결선","2020-11-02 09:00","2020-11-06 18:00","2020-11-02 09:00","2020-11-06 18:00","연속"]
[164,"경기북부","구리","미금S/S 154kV CB 6200","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - #61-66 BUS TIe GIS 관련 감시제어계측 포인트이관 (→SA) - #61-66 BUS TIe GIS LCP 및 모자익반 제어케이블 철거 및 재결선","2020-11-09 09:00","2020-11-13 18:00","취소","취소","연속"]
[165,"경기북부","구리","미금S/S 154kV SEC CB 60610","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - #60-61 BUS SEC GIS 관련 감시제어계측 포인트이관 (→SA) - #60-61 BUS SEC GIS LCP 및 모자익반 제어케이블 철거 및 재결선","2020-11-09 09:00","2020-11-13 18:00","2020-11-09 09:00","2020-11-13 18:00","연속"]
[166,"경기북부","구리","동서울서종#2 T/L","154kV 동서울-서종#2T/L 불량애자교체공사","No.39호 하단부하측 불량애자교체공사","2020-11-04 07:00","2020-11-04 18:00","취소","취소","연속"]
[167,"경기북부","구리","동서울서종#1 T/L","154kV 동서울-서종#1T/L 불량애자교체공사","No.38호 상단전원측 불량애자교체공사","2020-11-03 07:00","2020-11-03 18:00","취소","취소","연속"]
[168,"경기북부","구리","신포천백학#2 T/L","2020년 가공송전선로 순시점검 위탁공사","피뢰기 특별점검","2020-11-13 08:00","2020-11-17 18:00","2020-11-13 08:00","2020-11-17 18:00","연속"]
[169,"경기북부","구리","운천S/S 154kV #2 BUS","'20-21년 구리전력지사 변전정비회사 총액공사","장기사용 배전반 교체공사 - 운천S/S CPD반 교체","2020-11-10 09:00","2020-11-10 18:00","2020-11-10 09:00","2020-11-10 18:00","연속"]
[170,"경기북부","구리","운천S/S 154kV #1 BUS","'20-21년 구리전력지사 변전정비회사 총액공사","장기사용 배전반 교체공사 - 운천S/S CPD반 교체","2020-11-09 09:00","2020-11-09 18:00","2020-11-09 09:00","2020-11-09 18:00","연속"]
[171,"경기북부","구리","지제용문#1 T/L","세니온제 송전선로 보호반 성능개선 공사","IED 펌웨어 업데이트 : 43PDA, 거리계전기 오동작 방지, 검 출 전류 기준값 변경등","2020-11-18 09:00","2020-11-18 18:00","취소","취소","연속"]
[172,"경기북부","구리","진건별내#2 T/L","세니온제 송전선로 보호반 성능개선 공사","IED 펌웨어 업데이트 : 43PDA, 거리계전기 오동작 방지, 검 출 전류 기준값 변경등","2020-11-17 09:00","2020-11-17 18:00","2020-11-17 09:00","2020-11-17 18:00","연속"]
[173,"경기북부","구리","진건별내#1 T/L","세니온제 송전선로 보호반 성능개선 공사","IED 펌웨어 업데이트 : 43PDA, 거리계전기 오동작 방지, 검 출 전류 기준값 변경등","2020-11-16 09:00","2020-11-16 18:00","2020-11-16 09:00","2020-11-16 18:00","연속"]
[174,"경기북부","구리","포천S/S 154kV CB 6100","'20~21 구리전력 변전정비 총액공사","포천S/S 154kV BUS-TIE GCB 조작시험, 전자변교체","2020-11-04 09:00","2020-11-04 18:00","2020-11-04 09:00","2020-11-04 18:00","연속"]
[175,"경기북부","직할","금오상계#2 T/L","2020년 가공송전선로 순시점검 위탁공사","피뢰기 특별점검","2020-11-26 08:00","2020-11-30 18:00","2020-11-26 08:00","2020-11-30 18:00","연속"]
[176,"경기북부","직할","금오상계#1 T/L","2020년 가공송전선로 순시점검 위탁공사","피뢰기 특별점검","2020-11-23 08:00","2020-11-25 18:00","취소","취소","연속"]
[177,"경기북부","직할","신의정부S/S 154kV CB 6300","20~21 직할 변전정비회사 총액공사","□ 신의정부S/S #62-#67 BUS-TIE GIS 조작시험 및 가스분석","2020-11-11 09:00","2020-11-11 18:00","취소","취소","연속"]
[178,"경기북부","직할","신의정부용현#1 T/L","신의정부S/S 효성제 GIS 하자보수공사","신의정부-용현 #1 T/L DS 발청보수","2020-11-02 09:00","2020-11-03 18:00","2020-11-02 09:00","2020-11-03 18:00","연속"]
[179,"경기북부","직할","신의정부S/S 154kV #65 BUS","신의정부S/S 효성제 GIS 하자보수공사","신의정부-용현 #1, 2 T/L, #2 M.Tr 2차측 발청보수","2020-11-02 09:00","2020-11-07 18:00","2020-11-02 09:00","2020-11-07 18:00","연속"]
[180,"경기북부","직할","신의정부S/S 154kV #60 BUS","신의정부S/S 효성제 GIS 하자보수공사","신의정부-용현 #1, 2 T/L, #2 M.Tr 2차측 발청보수","2020-11-09 09:00","2020-11-10 18:00","2020-11-09 09:00","2020-11-10 18:00","연속"]
[181,"경기북부","직할","신의정부용현#2 T/L","신의정부S/S 효성제 GIS 하자보수공사","신의정부-용현 #2 T/L DS 발청보수","2020-11-04 09:00","2020-11-05 18:00","2020-11-04 09:00","2020-11-05 18:00","연속"]
[182,"경기북부","직할","양주은평#2 T/L","양주S/S 154kV 인출T/L 지중화공사","154kV 양주-은평#2 T/L 구내 지중화 ○ 구간 : 신설 EBA~신설 EBG ○ 내용 : 케이블 포설 및 접속","2020-11-16 08:00","2020-12-04 18:00","2020-11-16 08:00","2020-12-04 18:00","연속"]
[183,"경기북부","직할","양주지축#2 T/L","양주S/S 154kV 인출T/L 지중화공사","154kV 양주-지축#2 T/L 구내 지중화 ○ 구간 : 신설 EBA~신설 EBG ○ 내용 : 케이블 포설 및 접속","2020-11-16 08:00","2020-12-04 18:00","2020-11-16 08:00","2020-12-04 18:00","연속"]
[184,"경기북부","직할","양주S/S 154kV #60 BUS","양주S/S 154kV 인출T/L 지중화공사","상시험 및 무부하가압용","2020-11-14 09:00","2020-11-15 18:00","2020-11-14 09:00","2020-11-15 18:00","연속"]
[185,"경기북부","직할","양주S/S 154kV #61 BUS","양주S/S 154kV 인출T/L 지중화공사","상시험 및 무부하가압용","2020-11-14 09:00","2020-11-15 18:00","2020-11-14 09:00","2020-11-15 18:00","연속"]
[186,"경기북부","직할","양주지축#1 T/L","양주S/S 154kV 인출T/L 지중화공사","154kV 양주-지축#1 T/L 구내 지중화 ○ 구간 : 신설 EBA~신설 EBG ○ 내용 : 케이블 포설 및 접속","2020-11-04 08:00","2020-11-15 18:00","2020-11-04 08:00","2020-11-15 18:00","연속"]
[187,"경기북부","직할","양주은평#1 T/L","양주S/S 154kV 인출T/L 지중화공사","154kV 양주-은평#1 T/L 구내 지중화 ○ 구간 : 신설 EBA~신설 EBG ○ 내용 : 케이블 포설 및 접속","2020-11-04 08:00","2020-11-15 18:00","2020-11-04 08:00","2020-11-15 18:00","연속"]
[188,"경기북부","직할","옥정송우#2 T/L","세니온제 송전선로 보호반 성능개선 공사","IED 펌웨어 업데이트 : 43PDA, 거리계전기 오동작 방지, 검 출 전류 기준값 변경등","2020-11-12 09:00","2020-11-12 18:00","2020-11-12 09:00","2020-11-12 18:00","연속"]
[189,"경기북부","직할","용현도봉#1 T/L","2020년 가공송전선로 순시점검 위탁공사","피뢰기 특별점검","2020-11-26 08:00","2020-11-30 18:00","2020-11-26 08:00","2020-11-30 18:00","연속"]
[190,"경기북부","직할","용현도봉#2 T/L","2020년 가공송전선로 순시점검 위탁공사","피뢰기 특별점검","2020-11-23 08:00","2020-11-25 18:00","취소","취소","연속"]
[191,"경기","군포","서서울#2서안양 T/L","154kV 서서울-소래T/L 현수애자 절연성능진단","154kV 서서울-소래T/L 현수애자 절연성능진단(불량애자검출) - 강관/관형주 철탑 사선상태 휴전작업 - 작업대상 : No.47(1기)","2020-11-09 08:00","2020-11-09 13:00","2020-11-09 08:00","2020-11-09 13:00","연속"]
[192,"경기","군포","서서울율전#1 T/L","154kV 서서울-율전T/L 5,6호 안전이격확보공사","- 철탑 교체 : 2기 / 전선교체 : 4~6호간","2020-11-29 08:00","2020-12-05 18:00","2020-11-29 08:00","2020-12-04 18:00","연속"]
[193,"경기","군포","서서울율전#2 T/L","154kV 서서울-율전T/L 5,6호 안전이격확보공사","- 철탑 교체 : 2기 / 전선교체 : 4~6호간","2020-11-28 08:00","2020-11-28 18:00","2020-11-28 08:00","2020-11-28 18:00","연속"]
[194,"경기","군포","성곡중시화 T/L","성곡-중시화T/L 보호반 대체공사","성곡-중시화T/L 보호반 대체공사","2020-11-02 08:00","2020-11-05 18:00","2020-11-02 08:00","2020-11-05 18:00","연속"]
[195,"경기","군포","신안산남안산#2 T/L","신안산S/S 신안산-남안산#2T/L 거리계전기 재정정","신안산S/S 신안산-남안산#2T/L 거리계전기 재정정","2020-11-12 14:00","2020-11-12 18:00","2020-11-12 14:00","2020-11-12 18:00","연속"]
[196,"경기","군포","신안산남안산#1 T/L","신안산S/S 신안산-남안산#1T/L 거리계전기 재정정","신안산S/S 신안산-남안산#1T/L 거리계전기 재정정","2020-11-12 09:00","2020-11-12 14:00","2020-11-12 09:00","2020-11-12 14:00","연속"]
[197,"경기","동부","곤지암율현#1 T/L","154kV 오천-율현T/L 송전선로 정밀점검(안전이격거리 확보)","154kV 오천-율현#2T/L 송전선로 정밀점검 안전이격거리 확보","2020-11-01 09:00","2020-11-01 18:00","취소","취소","연속"]
[198,"경기","동부","모현용인#1 T/L","20년 동부 변전정비회사 총액공사","모현:오포-모현#1,오포-모현#2,모현-용인#1,모현-에버랜드#1제어모듈교체","2020-11-23 09:30","2020-11-23 18:00","2020-11-23 09:30","2020-11-23 18:00","연속"]
[199,"경기","동부","분당오포#1 T/L","성현분당#2T/L OPGW 낙뢰소산장치 철거 및 항공구설치 안전이격확보","성현분당#2T/L 안전이격확보","2020-11-07 07:00","2020-11-11 18:00","2020-11-07 07:00","2020-11-11 18:00","매일"]
[200,"경기","동부","성현분당#2 T/L","OPGW 낙뢰소산장치 철거 및 항공장애표시구 설치","낙뢰소산장치 2~18호 철거 및 항공장애표시구 35개","2020-11-07 07:00","2020-11-11 18:00","2020-11-07 07:00","2020-11-11 18:00","매일"]
[201,"경기","동부","분당오포#2 T/L","OPGW 낙뢰소산장치 철거 및 항공구설치","낙뢰소산장치 1~28호 철거 및 항공장애표시구 설치","2020-11-14 07:00","2020-11-18 18:00","2020-11-14 07:00","2020-11-18 18:00","매일"]
[202,"경기","동부","성현분당#1 T/L","분당오포#2T/L OPGW 낙뢰소산장치 철거 및 항공장애표시구 설치","병가구간 안전이격확보","2020-11-14 07:00","2020-11-18 18:00","2020-11-14 07:00","2020-11-18 18:00","매일"]
[203,"경기","동부","성현산성#1 T/L","20년 동부 변전정비회사 총액공사","산성:산성-성현#1,2T/L GIS(보통)","2020-11-02 09:30","2020-11-02 14:00","2020-11-02 09:30","2020-11-02 14:00","연속"]
[204,"경기","동부","성현산성#2 T/L","20년 동부 변전정비회사 총액공사","산성:산성-성현#1,2T/L GIS(보통)","2020-11-02 14:00","2020-11-02 18:00","2020-11-02 14:00","2020-11-02 18:00","연속"]
[205,"경기","동부","오천율현#2 T/L","154kV 오천-율현T/L 송전선로 정밀점검","154kV 오천-율현#2T/L 1~25호 송전선로 정밀점검(25기)","2020-11-01 09:00","2020-11-02 18:00","취소","취소","연속"]
[206,"경기","동부","오포모현#2 T/L","2020-2021년 성남전력지사 가공송전정비회사 총액공사","- 154kV 오포-모현T/L 추락방지시설 설치(1기)","2020-11-03 08:00","2020-11-03 18:00","2020-11-03 08:00","2020-11-03 18:00","연속"]
[207,"경기","동부","오포모현#1 T/L","2020-2021년 성남전력지사 가공송전정비회사 총액공사","- 154kV 오포-모현T/L 추락방지시설 설치(1기)","2020-11-02 08:00","2020-11-02 18:00","2020-11-02 08:00","2020-11-02 18:00","연속"]
[208,"경기","성남","서판교중원#1 T/L","20년 성남전력지사 변전정비회사 총액공사","보호반대체, 거리계전기성능개선","2020-11-23 09:00","2020-11-26 18:00","2020-11-23 09:00","2020-11-26 18:00","연속"]
[209,"경기","성남","신성남서판교 #1 T/L","20년 성남전력지사 변전정비회사 총액공사","보통점검, 전자변교체","2020-11-20 09:00","2020-11-20 18:00","2020-11-20 09:00","2020-11-20 18:00","연속"]
[210,"경기","성남","신성남정자 #3 T/L","20년 성남전력지사 변전정비회사 총액공사","거리계전기 개선","2020-11-19 09:00","2020-11-19 18:00","2020-11-19 09:00","2020-11-19 18:00","연속"]
[211,"경기","성남","신성남정자#1 T/L","20년 성남전력지사 변전정비회사 총액공사","거리계전기 개선","2020-11-18 09:00","2020-11-18 18:00","2020-11-18 09:00","2020-11-18 18:00","연속"]
[212,"경기","성남","신수원S/S 154kV SEC CB 65660","20년 성남전력지사 변전정비회사 총액공사","전자변교체","2020-11-04 16:00","2020-11-04 18:00","2020-11-04 16:00","2020-11-04 18:00","연속"]
[213,"경기","성남","신수원S/S 154kV CB 6200","20년 성남전력지사 변전정비회사 총액공사","전자변교체","2020-11-04 11:00","2020-11-04 14:00","2020-11-04 11:00","2020-11-04 14:00","연속"]
[214,"경기","성남","신수원S/S 154kV CB 6100","20년 성남전력지사 변전정비회사 총액공사","전자변교체","2020-11-04 09:00","2020-11-04 11:00","2020-11-04 09:00","2020-11-04 11:00","연속"]
[215,"경기","성남","신수원북동탄#1 T/L","154kV 신수원-북동탄 등 2개소 인출변경공사","○ 154kV 신수원-북동탄#1T/L 인출변경 - 선종 : 154kV XLPE 2,000㎟ 1C(D) - 내용 : EB-G 1개소 철거 및 신설 (기설 신수원-북동탄#1에서 예비(프렉스T/L)로 인출변경)","2020-11-09 09:00","2020-12-04 18:00","취소","취소","연속"]
[216,"경기","성남","신수원S/S 154kV SEC CB 60610","20년 성남전력지사 변전정비회사 총액공사","전자변교체","2020-11-04 14:00","2020-11-04 16:00","2020-11-04 14:00","2020-11-04 16:00","연속"]
[217,"경기","성남","신용인용인#2 T/L","20년 직할 송전정비회사 총액공사","신용인용인#2TL 불량애자교체 2,7,9,20호","2020-11-13 07:00","2020-11-13 18:00","취소","취소","연속"]
[218,"경기","성남","신용인용인#2 T/L","20년 직할 송전정비회사 총액공사","신용인기흥#1TL 불량애자교체, 안전이격거리확보","2020-11-04 07:00","2020-11-04 18:00","취소","취소","연속"]
[219,"경기","성남","신용인용인#1 T/L","20년 직할 송전정비회사 총액공사","신용인기흥#2TL 불량애자교체, 안전이격거리확보","2020-11-05 07:00","2020-11-05 18:00","취소","취소","연속"]
[220,"경기","성남","신용인동백#1 T/L","20년 성남전력지사 변전정비회사 총액공사","보호반대체","2020-11-30 09:00","2020-12-04 18:00","2020-11-30 09:00","2020-12-04 18:00","연속"]
[221,"경기","성남","신용인용인#1 T/L","20년 직할 송전정비회사 총액공사","신용인용인#1TL 불량애자교체 3,7,20호","2020-11-12 07:00","2020-11-12 18:00","취소","취소","연속"]
[222,"경기","성남","신용인S/S 154kV CB 6100","20년 성남전력지사 변전정비회사 총액공사","전자변교체","2020-11-12 09:00","2020-11-12 14:00","2020-11-12 09:00","2020-11-12 14:00","연속"]
[223,"경기","성남","신용인S/S 154kV SEC CB 61620","20년 성남전력지사 변전정비회사 총액공사","전자변교체","2020-11-12 14:00","2020-11-12 18:00","2020-11-12 14:00","2020-11-12 18:00","연속"]
[224,"경기","직할","관양동안양#1 T/L","20년 직할 변전정비회사 총액공사","동안양 : 관양-동안양 #1T/L GIS 보통","2020-11-04 09:00","2020-11-04 18:00","2020-11-04 09:00","2020-11-04 18:00","연속"]
[225,"경기","직할","관양동안양#2 T/L","20년 직할 변전정비회사 총액공사","동안양 : 관양-동안양 #2T/L GIS 보통","2020-11-23 09:00","2020-11-23 18:00","2020-11-23 09:00","2020-11-23 18:00","연속"]
[226,"경기","직할","발안S/S 154kV #1 BUS","발안S/S #5M.Tr 증설","GIS * 1CCT설치, 모선PT 이설","2020-11-02 09:00","2020-11-11 18:00","2020-11-02 09:00","2020-11-11 18:00","연속"]
[227,"경기","직할","율전의왕#1 T/L","20년 직할 변전정비회사 총액공사","율전S/S 율전-의왕 #1T/L GIS 전자변 교체","2020-11-02 09:00","2020-11-02 18:00","2020-11-02 09:00","2020-11-02 18:00","연속"]
[228,"경기","직할","율전의왕#2 T/L","20년 직할 변전정비회사 총액공사","율전S/S 율전-의왕 #2T/L GIS 전자변 교체","2020-11-03 09:00","2020-11-03 18:00","2020-11-03 09:00","2020-11-03 18:00","연속"]
[229,"경기","직할","율전동수원#1 T/L","154kV 서수원-율전-동수원T/L OPGW 증설공사","*율전CH ~ No.3(15)간 OP-S-L24 신설 0.710km","2020-11-09 07:00","2020-11-11 18:00","2020-11-09 07:00","2020-11-11 18:00","연속"]
[230,"경기","직할","서수원율전#2 T/L","154kV 서수원-율전-동수원T/L OPGW 증설공사","*율전CH ~ No.3(15)간 OP-S-L24 신설 0.710km","2020-11-09 07:00","2020-11-11 18:00","2020-11-09 07:00","2020-11-11 18:00","연속"]
[231,"경기","직할","율전동수원#2 T/L","154kV 서수원-율전-동수원T/L OPGW 증설공사","*율전CH ~ No.3(15)간 OP-S-L24 신설 0.710km","2020-11-09 07:00","2020-11-11 18:00","2020-11-09 07:00","2020-11-11 18:00","연속"]
[232,"경기","직할","신봉이의#1 T/L","20년 직할 변전정비회사 총액공사","이의 : 신봉-이의 #1,2T/L 보통","2020-11-09 09:00","2020-11-09 18:00","2020-11-09 09:00","2020-11-09 18:00","연속"]
[233,"경기","직할","신봉이의#2 T/L","20년 직할 송전정비회사 총액공사","율전동수원#1TL 불량애자교체 안전이격거리 확보","2020-11-09 09:00","2020-11-09 13:00","2020-11-09 09:00","2020-11-09 13:00","연속"]
[234,"경기","직할","화성수촌#1 T/L","154kV 화성-발안#1T/L 송전선로 정밀점검","154kV 화성-발안#1T/L(No.1~18) 송전선로 정밀점검 [안전이격거리 확보]","2020-11-16 08:00","2020-11-17 17:00","2020-11-16 08:00","2020-11-17 17:00","매일"]
[235,"경기","직할","화성수촌#2 T/L","154kV 화성-발안#2T/L 송전선로 정밀점검","154kV 화성-발안#2T/L(No.1~18) 송전선로 정밀점검 [안전이격거리 확보]","2020-11-12 09:00","2020-11-13 18:00","2020-11-12 09:00","2020-11-13 18:00","매일"]
[236,"경기","직할","화성발안#2 T/L","154kV 화성-발안#2T/L 송전선로 정밀점검","154kV 화성-발안#2T/L(No.1~18) 송전선로 정밀점검","2020-11-12 09:00","2020-11-13 18:00","2020-11-12 09:00","2020-11-13 18:00","매일"]
[237,"경기","직할","화성발안#1 T/L","154kV 화성-발안#1T/L 송전선로 정밀점검","154kV 화성-발안#1T/L(No.1~18) 송전선로 정밀점검","2020-11-16 08:00","2020-11-17 17:00","2020-11-16 08:00","2020-11-17 17:00","매일"]
[238,"경기","평택","서안성안성#1 T/L","20년 직할 송전정비회사 총액공사","서안성안성#1TL 피뢰기설치공사 5기","2020-11-16 07:00","2020-11-17 18:00","취소","취소","매일"]
[239,"경기","평택","서안성남사#1 T/L","20년 직할 송전정비회사 총액공사","피뢰기설치공사 20기, 추락방지장치 설치 3기, 불량애자교체 20EA","2020-11-09 07:00","2020-11-13 18:00","취소","취소","매일"]
[240,"경기","평택","서안성안성#2 T/L","20년 직할 송전정비회사 총액공사","서안성남사#1TL 피뢰기설치공사 안전이격거리 확보","2020-11-09 07:00","2020-11-09 18:00","취소","취소","연속"]
[241,"경기","평택","서안성남사#2 T/L","20년 직할 송전정비회사 총액공사","서안성남사#2TL 피뢰기설치 5기, 추락방지장치설치 3기, 애자교체 20EA","2020-11-16 07:00","2020-11-16 18:00","취소","취소","연속"]
[242,"경기","평택","서운안성#2 T/L","서운S/S 154kV 서운-안성#2T/L GIS 보통점검","서운S/S 154kV 서운-안성#2T/L GIS 보통점검","2020-11-07 09:00","2020-11-07 18:00","2020-11-07 09:00","2020-11-07 18:00","연속"]
[243,"경기","평택","오산평택#2 T/L","화성정남 전력구 운영시스템 설치공사","CCTV 및 PD진단 단자집합반 설치공사","2020-11-20 09:00","2020-11-21 18:00","2020-11-20 09:00","2020-11-21 18:00","매일"]
[244,"경기","평택","오산향남#2 T/L","화성정남 전력구 운영시스템 설치공사","CCTV 및 PD진단 단자집합반 설치공사","2020-11-20 09:00","2020-11-21 18:00","2020-11-20 09:00","2020-11-21 18:00","매일"]
[245,"경기","평택","오산평택#1 T/L","화성정남 전력구 운영시스템 설치공사","CCTV 및 PD진단 단자집합반 설치공사","2020-11-18 09:00","2020-11-19 18:00","2020-11-18 09:00","2020-11-19 18:00","매일"]
[246,"경기","평택","오산향남#1 T/L","화성정남 전력구 운영시스템 설치공사","CCTV 및 PD진단 단자집합반 설치공사","2020-11-18 09:00","2020-11-19 18:00","2020-11-18 09:00","2020-11-19 18:00","매일"]
[247,"경기","평택","진위동탄#2 T/L","20-2년도 평택전력지사 송전정비회사 총액공사","추락방지장치 설치","2020-11-12 10:00","2020-11-12 12:00","2020-11-12 10:00","2020-11-12 12:00","연속"]
[248,"경기","평택","진위동탄#1 T/L","20-2년도 평택전력지사 송전정비회사 총액공사","추락방지장치 설치","2020-11-12 08:00","2020-11-12 10:00","2020-11-12 08:00","2020-11-12 10:00","연속"]
[249,"경기","평택","포승청북 T/L","345kV 신온양-서서울 외 2개T/L 지장이설","지장이설 본선로 구성 No.43, 44, 43-46 전력선 교체","2020-11-01 07:00","2020-11-02 18:00","2020-11-01 07:00","2020-11-02 18:00","연속"]
[250,"경기","평택","평택추팔#2 T/L","20-21 송전정비회사총액공사(지지물보강)","평택-추팔T/L 지지물보강 인클로징 1(43호), 계탑 2(22호, 44호), 가철주 2기(계탑공사용)","2020-11-20 08:00","2020-11-27 18:00","2020-11-20 08:00","2020-11-27 18:00","연속"]
[251,"경기","평택","평택추팔#1 T/L","154kV 오산-평택 등 3개T/L 지중화 임시이설공사","- 154kV 오산-평택 No.71 ～ 평택S/S (신설 5기, 철거 5기) - 154kV 평택-추팔 평택S/S ～ No.13 (신설 7기 철거 7기) - 154kV 청북-평택 No.23 ～ 평택S/S (신설 2기, 철거 2기)","2020-11-18 07:00","2020-11-22 18:00","2020-11-18 07:00","2020-11-22 18:00","연속"]
[252,"경기","평택","평택추팔#2 T/L","154kV 오산-평택 등 3개T/L 지중화 임시이설공사","- 154kV 오산-평택 No.71 ～ 평택S/S (신설 5기, 철거 5기) - 154kV 평택-추팔 평택S/S ～ No.13 (신설 7기 철거 7기) - 154kV 청북-평택 No.23 ～ 평택S/S (신설 2기, 철거 2기)","2020-11-18 07:00","2020-11-22 18:00","2020-11-18 07:00","2020-11-22 18:00","연속"]
[253,"경기","평택","청북평택#1 T/L","154kV 오산-평택 등 3개T/L 지중화 임시이설공사","- 154kV 오산-평택 No.71 ～ 평택S/S (신설 5기, 철거 5기) - 154kV 평택-추팔 평택S/S ～ No.13 (신설 7기 철거 7기) - 154kV 청북-평택 No.23 ～ 평택S/S (신설 2기, 철거 2기)","2020-11-15 07:00","2020-11-17 18:00","2020-11-15 07:00","2020-11-17 18:00","연속"]
[254,"경기","평택","청북평택#2 T/L","154kV 오산-평택 등 3개T/L 지중화 임시이설공사","- 154kV 오산-평택 No.71 ～ 평택S/S (신설 5기, 철거 5기) - 154kV 평택-추팔 평택S/S ～ No.13 (신설 7기 철거 7기) - 154kV 청북-평택 No.23 ～ 평택S/S (신설 2기, 철거 2기)","2020-11-12 07:00","2020-11-14 18:00","2020-11-12 07:00","2020-11-14 18:00","연속"]
[255,"경기","평택","평택추팔#1 T/L","20-21 송전정비회사총액공사(지지물보강)","평택-추팔T/L 지지물보강 인클로징 1(43호), 계탑 2(22호, 44호), 가철주 2기(계탑공사용)","2020-11-16 08:00","2020-11-19 18:00","2020-11-16 08:00","2020-11-19 18:00","연속"]
[256,"경기","평택","오산평택#1 T/L","154kV 오산-평택 등 3개T/L 지중화 임시이설공사","- 154kV 오산-평택 No.71 ～ 평택S/S (신설 5기, 철거 5기) - 154kV 평택-추팔 평택S/S ～ No.13 (신설 7기 철거 7기) - 154kV 청북-평택 No.23 ～ 평택S/S (신설 2기, 철거 2기)","2020-11-29 07:00","2020-12-01 18:00","2020-11-29 07:00","2020-12-01 18:00","연속"]
[257,"경기","평택","평택추팔#1 T/L","20-21 송전정비회사총액공사(지지물보강)","평택-추팔T/L 지지물보강 인클로징 1(43호), 계탑 2(22호, 44호), 가철주 2기(계탑공사용)","2020-11-28 08:00","2020-12-01 18:00","2020-11-28 08:00","2020-12-01 18:00","연속"]
[258,"경기","평택","오산평택#2 T/L","154kV 오산-평택 등 3개T/L 지중화 임시이설공사","- 154kV 오산-평택 No.71 ～ 평택S/S (신설 5기, 철거 5기) - 154kV 평택-추팔 평택S/S ～ No.13 (신설 7기 철거 7기) - 154kV 청북-평택 No.23 ～ 평택S/S (신설 2기, 철거 2기)","2020-11-26 07:00","2020-11-28 18:00","2020-11-26 07:00","2020-11-28 18:00","연속"]
[259,"경기","평택","오산평택#1 T/L","154kV 오산-평택 등 3개T/L 지중화 임시이설공사","- 154kV 오산-평택 No.71 ～ 평택S/S (신설 5기, 철거 5기) - 154kV 평택-추팔 평택S/S ～ No.13 (신설 7기 철거 7기) - 154kV 청북-평택 No.23 ～ 평택S/S (신설 2기, 철거 2기)","2020-11-23 07:00","2020-11-25 18:00","2020-11-23 07:00","2020-11-25 18:00","연속"]
[260,"경기","평택","포승평택TP#1 T/L","안전이격확보_20-21평택전력지사 송전정비회사 총액공사","피뢰기 설치","2020-11-01 07:00","2020-11-02 18:00","2020-11-01 07:00","2020-11-02 18:00","연속"]
[261,"경기","직할","화성수촌#2 T/L","수촌S/S #1M.Tr 증설공사","수촌S/S 154kV #1M.Tr 무부하가압","2020-11-14 07:00","2020-11-15 18:00","2020-11-14 07:00","2020-11-15 18:00","연속"]
[262,"강원","강릉","속초간성#2 T/L","신양양분기등 OPGW 불량금구류 교체공사","○ 현수크램프 18개 교체, SB댐퍼 4개교체등 불량금구류 교체공사","2020-11-23 08:30","2020-11-23 18:00","2020-11-23 08:30","2020-11-23 18:00","연속"]
[263,"강원","강릉","속초간성#1 T/L","신양양분기등 OPGW 불량금구류 교체공사","○ 현수크램프 18개 교체, SB댐퍼 4개교체등 불량금구류 교체공사","2020-11-16 08:30","2020-11-20 18:00","2020-11-16 08:30","2020-11-20 18:00","매일"]
[264,"강원","강릉","신양양속초#2 T/L","신양양분기등 OPGW 불량금구류 교체공사","○ 현수크램프 18개 교체, SB댐퍼 4개교체등 불량금구류 교체공사","2020-11-24 08:30","2020-11-26 18:00","2020-11-24 08:30","2020-11-26 18:00","매일"]
[265,"강원","강릉","신양양양양#1 T/L","신양양분기등 OPGW 불량금구류 교체공사","○ 현수크램프 18개 교체, SB댐퍼 4개교체등 불량금구류 교체공사","2020-11-24 08:30","2020-11-26 18:00","2020-11-24 08:30","2020-11-26 18:00","매일"]
[266,"강원","강릉","신양양양양#2 T/L","신양양분기등 OPGW 불량금구류 교체공사","○ 현수크램프 18개 교체, SB댐퍼 4개교체등 불량금구류 교체공사","2020-11-27 08:30","2020-11-27 18:00","2020-11-27 08:30","2020-11-27 18:00","연속"]
[267,"강원","강릉","신양양속초#1 T/L","신양양분기등 OPGW 불량금구류 교체공사","○ 현수크램프 18개 교체, SB댐퍼 4개교체등 불량금구류 교체공사","2020-11-27 08:30","2020-11-27 18:00","2020-11-27 08:30","2020-11-27 18:00","연속"]
[268,"강원","강릉","동해영동TP T/L","154kV 강릉 등 8개T/L 피뢰기 설치공사","○ 피뢰기 설치 : 154kV 강릉T/L No.1~8-1","2020-11-02 08:00","2020-11-03 18:00","2020-11-02 08:00","2020-11-03 18:00","매일"]
[269,"강원","강릉","강릉영동TP T/L","20-21년도 강릉전력지사 송전정비회사 총액공사","○ SB댐퍼 교체 및 설치 : 154kV 강릉T/L No.1~65","2020-11-04 08:00","2020-11-18 18:00","2020-11-04 08:00","2020-11-18 18:00","매일"]
[270,"강원","동해","동해T/P 154kV #2 BUS","동해화력S/Y 장기사용 170kV GIS 대체공사","- 동해화력S/Y 장기사용 170kV GIS 6CCT대체 - 동해화력S/Y 부분디지털화 공사","2020-11-04 09:00","2020-11-09 18:00","2020-11-04 09:00","2020-11-09 18:00","연속"]
[271,"강원","동해","동해T/P 154kV #2 BUS","동해화력S/Y 장기사용 170kV GIS 대체공사","- 동해화력S/Y 장기사용 170kV GIS 6CCT대체 - 동해화력S/Y 부분디지털화 공사","2020-11-18 09:00","2020-11-25 18:00","2020-11-18 09:00","2020-11-25 18:00","연속"]
[272,"강원","동해","동해T/P 154kV #1 BUS","동해화력S/Y 장기사용 170kV GIS 대체공사","- 동해화력S/Y 장기사용 170kV GIS 6CCT대체 - 동해화력S/Y 부분디지털화 공사","2020-11-10 09:00","2020-11-17 18:00","2020-11-10 09:00","2020-11-17 18:00","연속"]
[273,"강원","동해","동해T/P 154kV #2 BUS","동해화력S/Y 장기사용 170kV GIS 대체공사","- 동해화력S/Y 장기사용 170kV GIS 6CCT대체 - 동해화력S/Y 부분디지털화 공사","2020-11-30 09:00","2020-12-05 18:00","2020-11-30 09:00","2020-12-05 18:00","연속"]
[274,"강원","동해","동해정선 T/L","영월-동영월-정선간 OPGW 교체공사","- OPGW(OP-S-L48)7.875km 교체 - 항공장애표시구 46개 철거 및 설치","2020-11-16 08:00","2020-11-22 18:00","2020-11-16 08:00","2020-11-22 18:00","연속"]
[275,"강원","원주","남원주원주#1 T/L","2020~2021년 원주전력지사 송전정비회사 총액공사","애자련 보강(1련 → 2련)","2020-11-09 08:00","2020-11-09 18:00","취소","취소","연속"]
[276,"강원","원주","남원주원주#2 T/L","2020~2021년 원주전력지사 송전정비회사 총액공사","애자련 보강(1련 → 2련)","2020-11-10 08:00","2020-11-10 18:00","취소","취소","연속"]
[277,"강원","원주","북원주횡성#2 T/L","2020~2021년 원주전력지사 송전정비 협력회사 총액공사","국산 지지애자 교체","2020-11-12 08:00","2020-11-12 18:00","취소","취소","연속"]
[278,"강원","원주","북원주횡성#1 T/L","2020~2021년 원주전력지사 송전정비 협력회사 총액공사","국산 지지애자 교체","2020-11-11 08:00","2020-11-11 18:00","취소","취소","연속"]
[279,"강원","원주","상남인제#2 T/L","2020년 원주전력지사 170kV GIS 정밀점검 공사","2020년 원주전력지사 170kV GIS 정밀점검 공사","2020-11-05 10:00","2020-11-07 18:00","2020-11-05 10:00","2020-11-07 18:00","연속"]
[280,"강원","원주","상남인제#1 T/L","2020년 원주전력지사 170kV GIS 정밀점검 공사","2020년 원주전력지사 170kV GIS 정밀점검 공사","2020-11-02 10:00","2020-11-04 18:00","2020-11-02 10:00","2020-11-04 18:00","연속"]
[281,"강원","원주","홍천상남#2 T/L","2020년 원주전력지사 170kV GIS 정밀점검 공사","2020년 원주전력지사 170kV GIS 정밀점검 공사","2020-11-12 10:00","2020-11-14 18:00","2020-11-12 10:00","2020-11-14 18:00","연속"]
[282,"강원","원주","홍천상남#1 T/L","2020년 원주전력지사 170kV GIS 정밀점검 공사","2020년 원주전력지사 170kV GIS 정밀점검 공사","2020-11-09 10:00","2020-11-11 18:00","2020-11-09 10:00","2020-11-11 18:00","연속"]
[283,"강원","원주","홍천S/S 154kV CB 6100","홍천S/S 6100 BUS-TIE 유압모터 제작사 보수(현대)","홍천S/S 6100 BUS-TIE 유압모터 제작사 보수(현대)","2020-11-03 10:00","2020-11-03 18:00","2020-11-03 10:00","2020-11-03 18:00","연속"]
[284,"강원","원주","횡성홍천#1 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","ㅇ 170kV 장기사용 GIS 철거/설치 ㅇ 디지털화공사 케이블 철거 및 광케이블 포설 ㅇ SA 운영장치 시험","2020-11-23 09:00","2020-12-18 18:00","2020-11-23 09:00","2020-12-18 18:00","연속"]
[285,"강원","원주","횡성홍천#2 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","ㅇ 170kV GIS 월부싱교체 안전이격확보","2020-11-24 08:00","2020-11-24 18:00","2020-11-24 08:00","2020-11-24 18:00","연속"]
[286,"강원","직할","인제양구#1 T/L","2020년 하반기 장기 미동작 차단기 조작시험","양구S/S 154kV 인제-양구 #1T/L 차단기 조작시험","2020-11-18 10:00","2020-11-18 14:00","2020-11-18 10:00","2020-11-18 14:00","연속"]
[287,"강원","직할","인제양구#2 T/L","2020년 하반기 장기 미동작 차단기 조작시험","양구S/S 154kV 인제-양구 #2T/L 차단기 조작시험","2020-11-18 14:00","2020-11-18 18:00","2020-11-18 14:00","2020-11-18 18:00","연속"]
[288,"강원","직할","청평HP의암HP T/L","154kV 의암T/L 전선접속개소 해소공사","전력선 교체 No.10~31-1(8.523km)","2020-11-01 08:30","2020-11-07 18:00","2020-11-01 08:30","2020-11-07 18:00","연속"]
[289,"강원","직할","춘천소양강HP T/L","2020년 하반기 장기 미동작 차단기 조작시험","춘천S/S 154kV 춘천-소양강HP T/L 차단기 조작시험","2020-11-17 10:00","2020-11-17 14:00","2020-11-17 10:00","2020-11-17 14:00","연속"]
[290,"강원","직할","가평춘천HP T/L","154kV 화천T/L 안전이격 확보공사","철탑 교체 및 전력선교체 , 기타 부대공사","2020-11-23 08:30","2020-11-27 18:00","취소","취소","연속"]
[291,"강원","직할","철원화천#1 T/L","2020년 하반기 강원본부 직할 154kV GIS 정밀점검공사","화천S/S 154kV 철원-화천 #1 T/L GIS 정밀점검","2020-11-02 09:00","2020-11-04 18:00","2020-11-02 09:00","2020-11-04 18:00","연속"]
[292,"강원","직할","철원화천#2 T/L","2020년 하반기 강원본부 직할 154kV GIS 정밀점검공사","화천S/S 154kV 철원-화천 #2 T/L GIS 정밀점검","2020-11-05 09:00","2020-11-07 18:00","2020-11-05 09:00","2020-11-07 18:00","연속"]
[293,"강원","직할","북춘천화천HP T/L","화천HP 보호배전반 이설 및 교체공사","화천HP 현대화에 따른 보호배전반 이설 및 교체공사","2020-11-26 09:00","2020-11-28 18:00","2020-11-26 09:00","2020-11-28 18:00","연속"]
[294,"강원","직할","양구화천HP#1 T/L","화천HP 보호배전반 이설 및 교체공사","화천HP 현대화에 따른 보호배전반 이설 및 교체공사","2020-11-23 09:00","2020-11-25 18:00","2020-11-23 09:00","2020-11-25 18:00","연속"]
[295,"강원","직할","가평화천HP T/L","화천HP 보호배전반 이설 및 교체공사","화천HP 현대화에 따른 보호배전반 이설 및 교체공사","2020-11-30 09:00","2020-12-02 18:00","2020-11-30 09:00","2020-12-02 18:00","연속"]
[296,"강원","직할","양구화천HP#2 T/L","화천HP 보호배전반 이설 및 교체공사","화천HP 현대화에 따른 보호배전반 이설 및 교체공사","2020-11-19 09:00","2020-11-21 18:00","2020-11-19 09:00","2020-11-21 18:00","연속"]
[297,"강원","태백","태백영월 T/L","20~21년 태백전력지사 송전정비회사 총액공사","애자교체","2020-11-03 09:00","2020-11-05 18:00","2020-11-03 09:00","2020-11-05 18:00","매일"]
[298,"강원","직할","화천H/P 154kV #1 BUS","화천HP 보호배전반 이설 및 교체공사","화천HP 현대화에 따른 보호배전반 이설 및 교체공사","2020-11-16 09:00","2020-11-18 18:00","2020-11-16 09:00","2020-11-18 18:00","연속"]
[299,"강원","직할","화천H/P 154KV CB 6100","화천HP 보호배전반 이설 및 교체공사","화천HP 현대화에 따른 보호배전반 이설 및 교체공사","2020-11-16 09:00","2020-12-10 18:00","2020-11-16 09:00","2020-12-10 18:00","연속"]
[300,"강원","직할","화천H/P 154kV #2 BUS","화천HP 보호배전반 이설 및 교체공사","화천HP 현대화에 따른 보호배전반 이설 및 교체공사","2020-11-16 09:00","2020-11-18 18:00","2020-11-16 09:00","2020-11-18 18:00","연속"]
[301,"강원","강릉","북평영동TP#1 T/L","2020년 170kV GIS 정밀점검","○ 2020년 170kV GIS 정밀점검","2020-11-16 09:00","2020-11-18 18:00","2020-11-16 09:00","2020-11-18 18:00","연속"]
[302,"강원","강릉","북평영동TP#2 T/L","2020년 170kV GIS 정밀점검","○ 2020년 170kV GIS 정밀점검","2020-11-19 09:00","2020-11-21 18:00","2020-11-19 09:00","2020-11-21 18:00","연속"]
[303,"충북","직할","신진천S/S 154kV SEC CB 65660","장기 미동작 차단기 점검","동작특성 시험 기타부대작업","2020-11-19 10:00","2020-11-19 14:00","2020-11-19 10:00","2020-11-19 14:00","연속"]
[304,"충북","직할","신진천S/S 154kV CB 6100","20~21년도 직할 변전정비회사 총액공사","신진천S/S 154kV #60-65 BUS-TIE GIS 보통점검","2020-11-30 10:00","2020-11-30 18:00","2020-11-30 10:00","2020-11-30 18:00","연속"]
[305,"충북","직할","신진천S/S 154kV SEC CB 66670","장기 미동작 차단기 점검","동작특성 시험 기타부대작업","2020-11-19 14:00","2020-11-19 18:00","2020-11-19 14:00","2020-11-19 18:00","연속"]
[306,"충북","청주","국사봉명#1 T/L","20년 하반기 청주전력지사 170kV GIS 정밀점검공사","국사봉명#1T/L CB 정밀점검","2020-11-21 09:00","2020-11-22 18:00","2020-11-21 09:00","2020-11-22 18:00","연속"]
[307,"충북","청주","오창국사#2 T/L","20년 하반기 청주전력지사 170kV GIS 정밀점검공사","#6100 BUS-TIE CB 정밀점검","2020-11-10 17:00","2020-11-10 18:00","2020-11-10 17:00","2020-11-10 18:00","연속"]
[308,"충북","청주","국사봉명#1 T/L","154kV 오창-봉명구간 OPGW 시설공사","○ 공사구간 : 오창S/S ∼ 국사S/S ∼ 국사-봉명 11호(오송-북청주 32호) ○ 공사내용 : 가공지선 ACSR 97㎟ 철거 및 OPGW 100㎟ 시설 ○ 시 공 사 : 한전KDN, 시공관리책임자 : 백승갑 (H.P:010-4141-1352)","2020-11-01 07:00","2020-11-01 18:00","2020-11-01 07:00","2020-11-01 18:00","연속"]
[309,"충북","청주","국사봉명#2 T/L","20년 하반기 청주전력지사 170kV GIS 정밀점검공사","국사봉명#2T/L CB 정밀점검","2020-11-14 09:00","2020-11-15 18:00","2020-11-14 09:00","2020-11-15 18:00","연속"]
[310,"충북","청주","남청주청주#4 T/L","20년 하반기 청주전력지사 170kV GIS 정밀점검공사","#66-65 BUS-SEC GIS CB 정밀점검","2020-11-24 17:00","2020-11-24 18:00","2020-11-24 17:00","2020-11-24 18:00","연속"]
[311,"충북","청주","남청주죽림#2 T/L","20-21년 청주전력 변전정비 총액","남청주죽림#2TL 에어 누기보수","2020-11-08 09:00","2020-11-08 18:00","취소","취소","연속"]
[312,"충북","청주","상주보은 T/L","154kV 상주T/L No.93-1 안전이격 확보공사","154kV 상주T/L No.93-1 기설설탑 철거 및 신설철탑 건설 지상고 부족에 따른 안전이격 확보공사 시행(F2-17m -> Ba2-28m)","2020-11-18 07:00","2020-11-18 18:00","취소","취소","연속"]
[313,"충북","청주","상주보은 T/L","154kV 상주T/L No.93-1 안전이격 확보공사","154kV 상주T/L No.93-1 기설설탑 철거 및 신설철탑 건설 지상고 부족에 따른 안전이격 확보공사 시행(F2-17m -> Ba2-28m)","2020-11-22 07:00","2020-11-23 18:00","취소","취소","매일"]
[314,"충북","청주","서청주사직#2 T/L","20-21년 청주전력 변전정비 총액공사","서청주-사직#2T/L GIS 보통점검","2020-11-28 09:00","2020-11-28 18:00","취소","취소","연속"]
[315,"충북","청주","상주영동 T/L","154kV 상주T/L No.93-1 안전이격 확보공사","154kV 상주T/L No.93-1 기설설탑 철거 및 신설철탑 건설 지상고 부족에 따른 안전이격 확보공사 시행(F2-17m -> Ba2-28m)","2020-11-19 07:00","2020-11-21 18:00","취소","취소","매일"]
[316,"충북","청주","남청주오송#1 T/L","154kV 오송-북청주 등 2개T/L EBA PD진단용 집합반 설치공사","오송, 북청주C/H EBA PD센서 및 집합반 설치","2020-11-21 09:00","2020-11-21 18:00","취소","취소","연속"]
[317,"충북","청주","남청주오송#2 T/L","154kV 오송-북청주 등 2개T/L EBA PD진단용 집합반 설치공사","오송, 북청주C/H EBA PD센서 및 집합반 설치","2020-11-22 09:00","2020-11-22 18:00","취소","취소","연속"]
[318,"충북","청주","오창국사#1 T/L","154kV 오창-봉명구간 OPGW 시설공사","○ 공사구간 : 오창S/S ∼ 국사S/S ∼ 국사-봉명 11호(오송-북청주 32호) ○ 공사내용 : 가공지선 ACSR 97㎟ 철거 및 OPGW 100㎟ 시설 ○ 시 공 사 : 한전KDN, 시공관리책임자 : 백승갑 (H.P:010-4141-1352)","2020-11-21 07:00","2020-11-22 18:00","2020-11-21 07:00","2020-11-22 18:00","연속"]
[319,"충북","청주","오창국사#1 T/L","154kV 오창-봉명구간 OPGW 시설공사","○ 공사구간 : 오창S/S ∼ 국사S/S ∼ 국사-봉명 11호(오송-북청주 32호) ○ 공사내용 : 가공지선 ACSR 97㎟ 철거 및 OPGW 100㎟ 시설 ○ 시 공 사 : 한전KDN, 시공관리책임자 : 백승갑 (H.P:010-4141-1352)","2020-11-01 07:00","2020-11-01 18:00","2020-11-01 07:00","2020-11-01 18:00","연속"]
[320,"충북","청주","신진천오창#1 T/L","20-21년 청주전력 변전정비 총액공사","피뢰기 대체","2020-11-29 09:00","2020-11-29 18:00","취소","취소","연속"]
[321,"충북","청주","옥천보은 T/L","154kV 상주T/L 정밀점검","2020 가공송전 순시점검 위탁공사 154kV 상주T/L No.1~110 정밀점검","2020-11-12 09:00","2020-11-14 18:00","취소","취소","매일"]
[322,"충북","청주","옥천영동 T/L","154kV 상주T/L 정밀점검","2020 가공송전 순시점검 위탁공사 154kV 상주T/L No.1~110 정밀점검","2020-11-15 09:00","2020-11-17 18:00","취소","취소","매일"]
[323,"충북","청주","남청주죽림#1 T/L","154kV 남청주-죽림 T/L 정밀점검","2020년 가공송전 순시점검 위탁공사 154kV 남청주-죽림T/L No.1~22 정밀점검","2020-11-07 09:00","2020-11-07 18:00","2020-11-07 09:00","2020-11-07 18:00","매일"]
[324,"충북","청주","사리초정#2 T/L","20년 하반기 청주전력지사 170kV GIS 정밀점검공사","사리초정#2T/L CB 정밀점검","2020-11-25 09:00","2020-11-26 18:00","2020-11-25 09:00","2020-11-26 18:00","연속"]
[325,"충북","충주","남음성덕산#1 T/L","남음성S/S #1M.Tr 증설공사","무부하 가압","2020-11-24 15:00","2020-11-25 18:00","2020-11-24 15:00","2020-11-25 18:00","연속"]
[326,"충북","충주","단양영월CC#2 T/L","2020-2021년 송전정비회사 총액공사","애자교체 (No.74)","2020-11-19 13:00","2020-11-19 18:00","2020-11-19 13:00","2020-11-19 18:00","연속"]
[327,"충북","충주","단양영월CC#1 T/L","2020-2021년 송전정비회사 총액공사","애자교체 (No.59,65)","2020-11-19 07:00","2020-11-19 12:00","2020-11-19 07:00","2020-11-19 12:00","연속"]
[328,"충북","충주","북충주충주 T/L","2020-2021년 송전정비회사 총액공사","압축인류클램프 교체 No.68,84,87,96,98,100,105,106,108,109,111,112 (12기)","2020-11-09 07:00","2020-11-17 18:00","2020-11-09 07:00","2020-11-17 18:00","매일"]
[329,"충북","충주","신제천영월CC#2 T/L","신제천S/S #5Sh.C GIS 정밀점검(차단부 자재교체)","신제천S/S 154kV #5 Sh.C GIS CB 부속품 교체, 정밀점검 후 무부하가압","2020-11-10 17:00","2020-11-11 16:00","2020-11-14 09:00","2020-11-14 18:00","연속"]
[330,"충북","충주","신제천영월CC#1 T/L","2020-2021년 송전정비회사 총액공사","추락방지장치 설치 (No.5,6)","2020-11-27 13:00","2020-11-27 18:00","2020-11-27 13:00","2020-11-27 18:00","연속"]
[331,"충북","충주","신제천영월CC#2 T/L","2020-2021년 송전정비회사 총액공사","추락방지장치 시범설치 (No.5,6)","2020-11-30 07:00","2020-11-30 18:00","2020-11-30 07:00","2020-11-30 18:00","연속"]
[332,"충북","충주","신제천S/S 154kV #67 BUS","신제천S/S #4Sh.C GIS 정밀점검(차단부 자재교체)","신제천S/S 154kV #4 Sh.C GIS 차단부교체, 정밀점검 후 무부하 가압 (모선통합 요청에 따른 거래소승인분 신청)","2020-11-03 17:00","2020-11-04 16:00","2020-11-07 09:00","2020-11-07 18:00","연속"]
[333,"충북","충주","신제천영월CC#2 T/L","신제천S/S #4Sh.C GIS 정밀점검(차단부 자재교체)","신제천S/S 154kV #4 Sh.C GIS 차단부교체, 정밀점검 후 무부하 가압","2020-11-03 17:00","2020-11-04 16:00","2020-11-07 09:00","2020-11-07 18:00","연속"]
[334,"충북","충주","신제천왕암#1 T/L","2020-2021년 송전정비회사 총액공사","애자교체 (No.7,14) 철탑도장 (No.14,21,25)","2020-11-10 07:00","2020-11-12 18:00","2020-11-02 07:00","2020-11-04 18:00","매일"]
[335,"충북","충주","신제천제천#2 T/L","2020-2021년 송전정비회사 총액공사","※안전이격거리 확보 애자교체 :154kV 신제천-왕암T/L No.7,14 철탑도장 :154kV 신제천-왕암T/L No.14,21,25","2020-11-13 07:00","2020-11-14 18:00","2020-11-05 07:00","2020-11-06 18:00","매일"]
[336,"충북","충주","신제천왕암#2 T/L","2020-2021년 송전정비회사 총액공사","애자교체 (No.7,14) 철탑도장 (No.14,21,25)","2020-11-13 07:00","2020-11-14 18:00","2020-11-05 07:00","2020-11-06 18:00","매일"]
[337,"충북","충주","신제천남원주#2 T/L","2020-2021년 송전정비회사 총액공사","애자 교체 (No.S/T,12,13,31,33-1,37)","2020-11-25 07:00","2020-11-26 18:00","취소","취소","매일"]
[338,"충북","충주","신제천남원주#1 T/L","2020-2021년 송전정비회사 총액공사","애자 교체 (No.S/T, 12,13)","2020-11-24 07:00","2020-11-24 18:00","취소","취소","연속"]
[339,"충북","충주","신제천S/S 154kV #67 BUS","신제천S/S #5Sh.C GIS 정밀점검(차단부 자재교체)","신제천S/S 154kV #5 Sh.C GIS CB 부속품 교체, 정밀점검 후 무부하가압 (모선통합 요청에 따른 거래소승인분 신청)","2020-11-10 17:00","2020-11-11 16:00","2020-11-14 09:00","2020-11-14 18:00","연속"]
[340,"충북","충주","신제천제천#1 T/L","2020-2021년 송전정비회사 총액공사","애자교체 (No.10,16)","2020-11-10 07:00","2020-11-12 18:00","2020-11-02 07:00","2020-11-04 18:00","매일"]
[341,"충북","충주","왕암가남#2 T/L","154kV 감곡S/S 인출 송전선로 계통정비공사","설치 4기(2회선 1, 4회선 3), 철거 4기, 선로길이 4.761C-km 154㎸ 감곡-여주T/L(신충주-감곡T/L 병가) №2～5간(№3,4 교체) 154㎸ 왕암-가남T/L №135～138간(№136,137 교체)","2020-11-01 07:00","2020-12-01 18:00","2020-11-08 07:00","2020-12-07 18:00","연속"]
[342,"충북","충주","왕암충주 T/L","2020-2021년 송전정비회사 총액공사","압축인류클램프 교체(No.80,82,84,87,92,98,100,105,106,108,109,111,112(13기) 애자교체 No.44","2020-11-02 07:00","2020-11-08 18:00","2020-11-02 07:00","2020-11-08 18:00","매일"]
[343,"충북","충주","왕암가남#1 T/L","154kV 감곡S/S 인출 송전선로 계통정비공사","설치 4기(2회선 1, 4회선 3), 철거 4기, 선로길이 4.761C-km 154㎸ 감곡-여주T/L(신충주-감곡T/L 병가) №2～5간(№3,4 교체) 154㎸ 왕암-가남T/L №135～138간(№136,137 교체)","2020-11-11 07:00","2020-11-22 18:00","2020-11-16 07:00","2020-11-30 18:00","연속"]
[344,"충북","충주","음성사리 T/L","2020년 직할 가공송전선로 순시점검 위탁공사","154kV 풍동-음성#2T/L 현수애자 절연저항측정에 따른 안전이격 확보","2020-11-25 09:00","2020-11-26 18:00","2020-11-25 09:00","2020-11-26 18:00","매일"]
[345,"충북","충주","제천영월#2 T/L","2020-2021년 송전정비회사 총액공사","애자 교체 (No.44-1,49)","2020-11-18 13:00","2020-11-18 18:00","2020-11-14 13:00","2020-11-14 18:00","연속"]
[346,"충북","충주","제천영월#1 T/L","2020-2021년 송전정비회사 총액공사","애자교체 (No.44-1)","2020-11-18 07:00","2020-11-18 12:00","2020-11-14 07:00","2020-11-14 12:00","연속"]
[347,"충북","충주","충주풍동 T/L","2020년 직할 가공송전선로 순시점검 위탁공사","154kV 풍동-음성#2T/L 현수애자 절연저항측정에 따른 안전이격 확보","2020-11-23 09:00","2020-11-23 18:00","2020-11-23 09:00","2020-11-23 18:00","매일"]
[348,"충북","충주","충주S/S 154kV SEC CB 60610","2020년 충주전력지사 170kV GIS 정밀점검","충주S/S #60-#61BUS SEC GIS 정밀점검","2020-11-04 09:00","2020-11-05 18:00","2020-11-04 09:00","2020-11-05 18:00","연속"]
[349,"충북","충주","충주충주HP#2 T/L","2020-2021년 송전정비회사 총액공사","※안전이격거리 확보 압축인류클램프 교체 북충주-충주T/L No.68,84,87,96,98,100,105,106,108,109,111,112 (12기)","2020-11-09 07:00","2020-11-13 18:00","2020-11-09 07:00","2020-11-13 18:00","매일"]
[350,"충북","충주","충주충주HP#1 T/L","2020-2021년 송전정비회사 총액공사","※안전거리 확보 압축인류클램프 교체(왕암충주T/L No.80,82,84,87,92,98,100,105,106,108,109,111,112(13기)","2020-11-02 07:00","2020-11-06 18:00","2020-11-02 07:00","2020-11-06 18:00","매일"]
[351,"충북","충주","풍동음성#2 T/L","2020년 직할 가공송전선로 순시점검 위탁공사","현수애자 절연저항측정 (11기)","2020-11-23 09:00","2020-11-26 18:00","2020-11-23 09:00","2020-11-26 18:00","매일"]
[352,"충북","충주","풍동음성#1 T/L","2020~21년 직할 송전정비회사 총액공사","아킹혼설치 및 불량애자교체, 항공장애표시등철거 등","2020-11-02 08:00","2020-11-10 18:00","2020-11-02 08:00","2020-11-10 18:00","매일"]
[353,"대전충남","대전","금산무주#1 T/L","[송전] 154kV 금산-무주#1T/L 정밀점검","[송전] 154kV 금산-무주#1T/L 정밀점검","2020-11-05 07:30","2020-11-06 18:00","2020-11-05 07:30","2020-11-06 18:00","매일"]
[354,"대전충남","대전","금산무주#2 T/L","[송전] 154kV 금산-무주#2T/L 정밀점검","[송전] 154kV 금산-무주#2T/L 정밀점검","2020-11-09 07:30","2020-11-13 18:00","2020-11-09 07:30","2020-11-13 18:00","매일"]
[355,"대전충남","대전","신옥천남대전#1 T/L","남대전S/S 154kV 신옥천-남대전#1TL 차단기 부동작 예방조작 시험","남대전S/S 154kV 신옥천-남대전#1T/L 차단기 부동작 예방조작 시험","2020-11-23 09:00","2020-11-23 13:00","2020-11-23 09:00","2020-11-23 13:00","연속"]
[356,"대전충남","대전","신옥천남대전#2 T/L","남대전S/S 154kV 신옥천-남대전#2TL 차단기 부동작 예방조작 시험","남대전S/S 154kV 신옥천-남대전#2T/L 차단기 부동작 예방조작 시험","2020-11-23 14:00","2020-11-23 18:00","2020-11-23 14:00","2020-11-23 18:00","연속"]
[357,"대전충남","대전","신옥천남대전#4 T/L","[송전]154kV 신옥천-서대전 등 18개T/L 주수애자청소","[송전]154kV 신옥천-남대전#4T/L 사선애자청소","2020-11-17 10:00","2020-11-17 18:00","2020-11-06 10:00","2020-11-06 18:00","매일"]
[358,"대전충남","대전","신옥천남대전#3 T/L","남대전S/S 154kV 신옥천-남대전#3TL 차단기 부동작 예방조작 시험","남대전S/S 154kV 신옥천-남대전#3T/L 차단기 부동작 예방조작 시험","2020-11-24 09:00","2020-11-24 13:00","취소","취소","연속"]
[359,"대전충남","대전","신옥천남대전#4 T/L","남대전S/S 154kV 신옥천-남대전#4TL 차단기 부동작 예방조작 시험","남대전S/S 154kV 신옥천-남대전#4T/L 차단기 부동작 예방조작 시험","2020-11-24 14:00","2020-11-24 18:00","취소","취소","연속"]
[360,"대전충남","대전","신옥천남대전#3 T/L","[송전]154kV 신옥천-서대전 등 18개T/L 주수애자청소","[송전]154kV 신옥천-남대전#3T/L 사선애자청소","2020-11-16 07:00","2020-11-17 10:00","2020-11-05 07:00","2020-11-06 10:00","매일"]
[361,"대전충남","대전","팔봉두마#2 T/L","[송전]154kV 신옥천-서대전 등 18개T/L 주수애자청소","[송전]154kV 팔봉-두마#2T/L 사선애자청소","2020-11-09 07:00","2020-11-09 18:00","2020-11-09 07:00","2020-11-09 18:00","연속"]
[362,"대전충남","대전","신옥천용운#1 T/L","[제어] 154kV 신옥천-용운T/L OPGW 교체공사(S/T~No.5)","※OPGW 소손에 따른 OPGW 교체(S/T~No.5 1.4km) ○ 공사구간 : 신옥천S/S S/T~No.5 ○ 공사내역 : OPGW 1.4km 교체 및 부대공사 ○ 공사일정 : '20.11.09~11.12","2020-11-16 08:00","2020-11-19 18:00","취소","취소","연속"]
[363,"대전충남","대전","신옥천용운#2 T/L","[제어] 154kV 신옥천-용운T/L OPGW 교체공사(S/T~No.5)","※OPGW 소손에 따른 OPGW 교체(S/T~No.5 1.4km) ○ 공사구간 : 신옥천S/T~No.5 ○ 공사내역 : OPGW 1.4km 교체 및 부대공사 ○ 공사일정 : '20.11.09~11.12","2020-11-16 08:00","2020-11-19 18:00","취소","취소","연속"]
[364,"대전충남","서산","대산석문#1 T/L","대산S/S 154kV 현대케미칼#1,2T/L GIS 설치공사","안전이격 확보","2020-11-03 08:00","2020-11-04 18:00","취소","취소","매일"]
[365,"대전충남","서산","서산대산#4 T/L","서산S/S 154kV 모선구분GIS 설치공사","서산S/S 154kV 모선구분GIS 설치공사","2020-11-02 09:00","2020-11-12 18:00","2020-11-02 09:00","2020-11-12 18:00","연속"]
[366,"대전충남","서산","서산S/S 154kV #2 BUS","서산S/S 154kV 모선구분GIS 설치공사","서산S/S 154kV 모선구분GIS 설치공사","2020-11-02 09:00","2020-11-12 18:00","2020-11-02 09:00","2020-11-12 18:00","연속"]
[367,"대전충남","서산","신당진서산#2 T/L","154kV 서산S/S DS 이음관련 보수","154kV 서산S/S DS 이음관련 보수","2020-11-17 10:00","2020-11-18 18:00","2020-11-17 10:00","2020-11-18 18:00","연속"]
[368,"대전충남","세종","덕진S/S 154kV #1 BUS","덕진S/S 154kV 모선구분GIS 설치공사","덕진S/S 154kV 모선구분GIS 설치공사","2020-11-09 10:00","2020-11-19 14:00","2020-11-09 10:00","2020-11-19 14:00","연속"]
[369,"대전충남","세종","덕진공주#1 T/L","[송전]국제과학비즈니스벨트 지장송전선로 지중화공사(요청자시행)","ㅇ 요청자(한국토지주택공사) 직접시행 지장이설 및 지중화공사 ㅇ 공사구간 : 154kV 덕진-공주(덕진-유성)T/L No.13~15 ㅇ 철탑 : C/H 2기 설치, 가철탑 2기 ㅇ 전력선 : ACSR 410 x S x 4C ㅇ 본선로 구성","2020-11-06 07:00","2020-11-10 18:00","2020-11-06 07:00","2020-11-10 18:00","연속"]
[370,"대전충남","세종","덕진공주#2 T/L","[송전]국제과학비즈니스벨트 지장송전선로 지중화공사(요청자시행)","ㅇ 요청자(한국토지주택공사) 직접시행 지장이설 및 지중화공사 ㅇ 공사구간 : 154kV 덕진-공주(덕진-유성)T/L No.13~15 ㅇ 철탑 : C/H 2기 설치, 가철탑 2기 ㅇ 전력선 : ACSR 410 x S x 4C ㅇ 본선로 구성","2020-11-11 07:00","2020-11-15 18:00","2020-11-11 07:00","2020-11-15 18:00","연속"]
[371,"대전충남","세종","덕진S/S 154kV CB 6100","덕진S/S 154kV 모선구분GIS 설치공사","덕진S/S 154kV 모선구분GIS 설치공사 (6100 임시 운휴)","2020-11-02 14:00","2020-12-01 18:00","2020-11-02 14:00","2020-12-01 18:00","연속"]
[372,"대전충남","세종","덕진S/S 154kV #2 BUS","덕진S/S 154kV 모선구분GIS 설치공사","덕진S/S 154kV 모선구분GIS 설치공사","2020-11-19 14:00","2020-11-30 10:00","2020-11-19 14:00","2020-11-30 10:00","연속"]
[373,"대전충남","세종","덕진공주#1 T/L","[송전]국제과학비즈니스벨트 지장송전선로 지중화공사(요청자시행)","ㅇ 요청자(한국토지주택공사) 직접시행 지장이설 및 지중화공사 ㅇ 공사구간 : 154kV 덕진-공주(덕진-유성)T/L No.13~15 ㅇ 철탑 : C/H 2기 설치, 가철탑 2기 ㅇ 전력선 : ACSR 410 x S x 4C ㅇ 본선로 구성","2020-11-16 07:00","2020-11-20 18:00","2020-11-16 07:00","2020-11-20 18:00","연속"]
[374,"대전충남","세종","덕진대화#1 T/L","[송전] 송전철탑 추락방지시설 설치공사","○ 154kV 용운-대화T/L No.26 C/H 추락방지시설 설치 (병가휴전) ○ 154kV 대덕-덕진T/L No.15 C/H 추락방지시설 설치","2020-11-23 08:00","2020-11-23 18:00","2020-11-23 08:00","2020-11-23 18:00","연속"]
[375,"대전충남","세종","부강신탄진 T/L","[변전]세종PO 변전정비회사 총액공사","부강S/S 부강-신탄진 피뢰기 교체공사","2020-11-05 09:00","2020-11-05 18:00","2020-11-05 09:00","2020-11-05 18:00","연속"]
[376,"대전충남","세종","부강월산#1 T/L","154kV 부강-월산T/L 현수애자교체 및 보강공사","[송전] 부강-월산#1T/L 현수애자 교체 및 애자련보강 - No.8,13호(지지애자교체)","2020-11-02 07:00","2020-11-02 18:00","2020-11-02 07:00","2020-11-02 18:00","연속"]
[377,"대전충남","세종","부강월산#2 T/L","154kV 부강-월산T/L 현수애자교체 및 보강공사","[송전] 부강-월산#2T/L 현수애자 교체 및 애자련보강 - No.26호(지지애자교체)","2020-11-03 07:00","2020-11-03 18:00","2020-11-03 07:00","2020-11-03 18:00","연속"]
[378,"대전충남","세종","조치원전의#2 T/L","154kV 조치원-전의T/L 현수애자교체 및 보강공사","[송전] 조치원-전의#2T/L 현수애자 교체 및 애자련보강 - No.13,27,36,52,조치원S/T(현수애자교체)","2020-11-18 07:00","2020-11-19 18:00","2020-11-18 07:00","2020-11-19 18:00","연속"]
[379,"대전충남","세종","조치원전의#1 T/L","154kV 조치원-전의T/L 현수애자교체 및 보강공사","[송전] 조치원-전의#1T/L 현수애자 교체 및 애자련보강 - No13,36,37,조치원S/T(현수애자교체)","2020-11-16 07:00","2020-11-17 18:00","2020-11-16 07:00","2020-11-17 18:00","연속"]
[380,"대전충남","아산","불당서천안#1 T/L","불당S/S 154kV 불당-서천안#1T/L GIS 전자변 교체","불당S/S 154kV 불당-서천안#1T/L GIS 전자변 교체","2020-11-12 09:00","2020-11-12 18:00","취소","취소","연속"]
[381,"대전충남","아산","불당서천안#2 T/L","불당S/S 154kV 불당-서천안#2T/L GIS 전자변 교체","불당S/S 154kV 불당-서천안#2T/L GIS 전자변 교체","2020-11-13 09:00","2020-11-13 18:00","취소","취소","연속"]
[382,"대전충남","아산","서천안탕정#1 T/L","[송전]성능저하 점퍼지지애자 교체공사","154kV 서천안-탕정 등 6개T/L 성능저하 점퍼지지애자 교체공사","2020-11-11 08:00","2020-11-11 11:00","취소","취소","연속"]
[383,"대전충남","아산","서천안탕정#2 T/L","[송전]성능저하 점퍼지지애자 교체공사","154kV 서천안-탕정 등 6개T/L 성능저하 점퍼지지애자 교체공사","2020-11-11 11:00","2020-11-11 18:00","취소","취소","연속"]
[384,"대전충남","아산","아산예산#2 T/L","[송전]성능저하 점퍼지지애자 교체공사","154kV 서천안-탕정 등 6개T/L 성능저하 점퍼지지애자 교체공사","2020-11-12 14:00","2020-11-12 18:00","취소","취소","연속"]
[385,"대전충남","아산","아산예산#1 T/L","[송전]성능저하 점퍼지지애자 교체공사","154kV 서천안-탕정 등 6개T/L 성능저하 점퍼지지애자 교체공사","2020-11-12 08:00","2020-11-12 14:00","취소","취소","연속"]
[386,"대전충남","아산","아산인주#1 T/L","아산S/S 아산-인주#1T/L GIS 보통점검","아산S/S 아산-인주#1T/L GIS 보통점검","2020-11-21 09:00","2020-11-21 18:00","2020-11-21 09:00","2020-11-21 18:00","연속"]
[387,"대전충남","아산","아산인주#1 T/L","345kV북당진-신탕정T/L 건설공사","No.47 ~ 48 가선공사 - 아산인주#1,#2T/L 횡단을 위한 보호망 설치(양회선 휴전 3시간)","2020-11-28 08:00","2020-11-28 11:00","2020-11-28 08:00","2020-11-28 11:00","연속"]
[388,"대전충남","아산","아산인주#2 T/L","345kV북당진-신탕정T/L 건설공사","No.47 ~ 48 가선공사 - 아산인주#1,#2T/L 횡단을 위한 보호망 설치(양회선 휴전 3시간)","2020-11-28 08:00","2020-11-28 11:00","2020-11-28 08:00","2020-11-28 11:00","연속"]
[389,"대전충남","아산","인주탕정#1 T/L","345kV북당진-신탕정T/L 건설공사","No.47 ~ 48 가선공사 - 인주탕정#1,#2T/L 횡단을 위한 보호망 설치(양회선 휴전 3시간)","2020-11-28 14:00","2020-11-28 17:00","2020-11-28 14:00","2020-11-28 17:00","연속"]
[390,"대전충남","아산","인주탕정#2 T/L","345kV북당진-신탕정T/L 건설공사","No.47 ~ 48 가선공사 - 인주탕정#1,#2T/L 횡단을 위한 보호망 설치(양회선 휴전 3시간)","2020-11-28 14:00","2020-11-28 17:00","2020-11-28 14:00","2020-11-28 17:00","연속"]
[391,"대전충남","아산","인주탕정#2 T/L","[송전]성능저하 점퍼지지애자 교체공사","154kV 서천안-탕정 등 6개T/L 성능저하 점퍼지지애자 교체공사","2020-11-20 09:00","2020-11-20 18:00","취소","취소","연속"]
[392,"대전충남","아산","장재천안#1 T/L","[송전]154kV 장재-천안T/L No.24~25 청당지구 지중화공사","천안시 일부구간 지중화사업 요청에 의한 154kV 장재-천안T/L No.24~25 지중화 시행 - 선종 및 길이 : XLPE 2,000㎟(D)×2C, 0.577km","2020-11-12 08:00","2020-12-06 18:00","2020-11-12 08:00","2020-12-06 18:00","연속"]
[393,"대전충남","아산","신탕정탕정#1 T/L","신탕정,탕정S/S GIS 보통점검 및 PNL 성능개선","신탕정,탕정S/S GIS 보통점검 및 PNL 성능개선","2020-11-16 09:00","2020-11-16 18:00","취소","취소","연속"]
[394,"대전충남","아산","신탕정탕정#2 T/L","신탕정,탕정S/S GIS 보통점검 및 PNL 성능개선","신탕정,탕정S/S GIS 보통점검 및 PNL 성능개선","2020-11-17 09:00","2020-11-17 18:00","취소","취소","연속"]
[395,"대전충남","아산","온양풍세#1 T/L","[송전]성능저하 점퍼지지애자 교체공사","154kV 서천안-탕정 등 6개T/L 성능저하 점퍼지지애자 교체공사","2020-11-18 08:00","2020-11-18 18:00","취소","취소","연속"]
[396,"대전충남","아산","온양풍세#2 T/L","[송전]성능저하 점퍼지지애자 교체공사","154kV 서천안-탕정 등 6개T/L 성능저하 점퍼지지애자 교체공사","2020-11-19 08:00","2020-11-19 18:00","취소","취소","연속"]
[397,"대전충남","아산","한샘둔포#2 T/L","154kV 직산S/S 및 직산분기T/L 건설공사","ㅇ 구간 : 154kV 한샘-둔포T/L 16호 ~ 신설 직산S/S ㅇ 선로길이 : 4C-4.283km ㅇ 지지물수 : 관형지지물 12기","2020-11-30 07:00","2020-12-06 18:00","2020-11-30 07:00","2020-12-06 18:00","연속"]
[398,"대전충남","아산","한샘둔포#1 T/L","154kV 직산S/S 및 직산분기T/L 건설공사","ㅇ 구간 : 154kV 한샘-둔포T/L 16호 ~ 신설 직산S/S ㅇ 선로길이 : 4C-4.283km ㅇ 지지물수 : 관형지지물 12기","2020-11-23 07:00","2020-11-29 18:00","2020-11-23 07:00","2020-11-29 18:00","연속"]
[399,"대전충남","아산","한샘서천안#1 T/L","154kV 직산S/S 및 분기 송전선로 건설공사","O 154kV 직산S/S 및 분기 송전선로 무부하 가압 - 154kV 직산S/S 무부하 가압 - 154kV 한샘-직산, 직산-둔포 #1T/L","2020-11-26 09:00","2020-11-27 09:00","2020-11-26 09:00","2020-11-27 09:00","연속"]
[400,"대전충남","직할","대덕둔지 T/L","직할 세니온제 154kV 송전선로보호반 성능개선","□직할 세니온제 154kV 송전선로보호반 성능개선 ○ 대덕,둔지S/S 154lV 대덕둔지T/L □ 154kV GIS 보통점검 ○ 둔지S/S 154lV 대덕둔지T/L","2020-11-10 09:00","2020-11-10 18:00","2020-11-10 09:00","2020-11-10 18:00","연속"]
[401,"대전충남","직할","덕진대화#2 T/L","[송전]154kV 옥산-부여 등 3개T/L 자기애관 교체공사","○ 비표준형 및 표준형 EBA 자기애관 → 폴리머애관 30상 교체","2020-11-02 08:00","2020-11-12 18:00","2020-11-02 08:00","2020-11-12 18:00","연속"]
[402,"대전충남","직할","대화둔산#2 T/L","직할 세니온제 154kV 송전선로보호반 성능개선","□직할 세니온제 154kV 송전선로보호반 성능개선 ○ 대화,둔산S/S 154lV 대화둔산#2T/L □ 154kV GIS 보통점검 ○ 둔산S/S 154lV 대화둔산#2T/L □ 154kV GIS 차단기 동작시험 ○ 대화S/S 154lV 대화둔산#2T/L","2020-11-12 09:00","2020-11-12 18:00","취소","취소","연속"]
[403,"대전충남","직할","송강신일#2 T/L","신일S/S 154kV 송강-신일#2T/L GIS 차단기 하자점검","신일S/S 154kV 송강-신일#2T/L GIS 차단기 하자점검","2020-11-25 09:00","2020-11-25 18:00","2020-11-25 09:00","2020-11-25 18:00","연속"]
[404,"대전충남","청양","장항S/S 154kV #1 BUS","154kV 장항S/S #4M.Tr 증설공사","#4M.Tr 및 1,2차 GIS 무부하가압","2020-11-24 09:00","2020-11-24 14:00","취소","취소","연속"]
[405,"대전충남","청양","장항S/S 154kV #2 BUS","154kV 장항S/S #4M.Tr 증설공사","#4M.Tr 및 1,2차 GIS 무부하가압","2020-11-24 14:00","2020-11-25 14:00","취소","취소","연속"]
[406,"전북","군산","내초S/S 154kV 내초SE열병합#1 T/L CB","군산P/O 154kV이상 차단기 점검공사","-SE열병합S/Y 내초-SE열병합#1T/L 차단기 점검","2020-11-03 09:00","2020-11-03 18:00","취소","취소","연속"]
[407,"전북","군산","내초S/S 154kV 내초SE열병합#2 T/L CB","군산P/O 154kV이상 차단기 점검공사","-SE열병합S/Y 내초-SE열병합#2T/L 차단기 점검","2020-11-04 09:00","2020-11-04 18:00","취소","취소","연속"]
[408,"전북","군산","군산S/S 154kV CB 6300","'20년 군산P/O 공압식차단기 전자변 교체공사","- 군산S/S 154kV #62-#67 BUS TIE GIS 전자변 교체","2020-11-18 09:00","2020-11-18 14:00","2020-11-18 09:00","2020-11-18 14:00","연속"]
[409,"전북","군산","군산S/S 154kV SEC CB 60610","'20년 군산P/O 공압식차단기 전자변 교체공사","- 군산S/S 154kV #60-#61 SEC GIS 전자변 교체","2020-11-17 09:00","2020-11-17 14:00","2020-11-17 09:00","2020-11-17 14:00","연속"]
[410,"전북","군산","군산S/S 154kV SEC CB 65660","'20년 군산P/O 공압식차단기 전자변 교체공사","- 군산S/S 154kV #65-#66 SEC GIS 전자변 교체","2020-11-17 14:00","2020-11-17 18:00","2020-11-17 14:00","2020-11-17 18:00","연속"]
[411,"전북","군산","내초군장#1 T/L","154kV 군장S/S SMG에너지T/L 신규수용공사(무부하가압)","170kV GIS X 1CCT","2020-11-23 10:00","2020-11-23 14:00","취소","취소","연속"]
[412,"전북","군산","비응군장#1 T/L","'20년 군산P/O 170kV GIS 정밀점검공사","군장S/S 154kV 비응-군장#1T/L GIS 정밀점검","2020-11-16 09:00","2020-11-17 18:00","2020-11-09 09:00","2020-11-10 18:00","연속"]
[413,"전북","군산","비응군장#2 T/L","154kV 군장S/S SMG에너지T/L 신규수용공사(안전이격)","170kV GIS X 1CCT","2020-11-04 10:00","2020-11-13 16:00","2020-11-18 10:00","2020-11-27 16:00","연속"]
[414,"전북","군산","내초군장#1 T/L","154kV SMG에너지T/L 신규수용공사(시험가압)","170kV GIS X 1CCT","2020-11-12 16:00","2020-11-13 16:00","2020-11-26 16:00","2020-11-27 16:00","연속"]
[415,"전북","군산","내초군장#2 T/L","154kV 군장S/S SMG에너지T/L 신규수용공사(무부하가압)","170kV GIS X 1CCT","2020-11-23 14:00","2020-11-24 14:00","취소","취소","연속"]
[416,"전북","군산","내초군장#2 T/L","154kV 군장S/S SMG에너지T/L 신규수용공사(시험가압)","170kV GIS X 1CCT","2020-11-09 10:00","2020-11-10 10:00","2020-11-23 10:00","2020-11-24 10:00","연속"]
[417,"전북","군산","비응군장#2 T/L","'20년 군산P/O 170kV GIS 정밀점검공사","군장S/S 154kV 비응-군장#2T/L GIS 정밀점검","2020-11-18 09:00","2020-11-19 18:00","2020-11-11 09:00","2020-11-12 18:00","연속"]
[418,"전북","군산","새만금소룡#2 T/L","'20년 군산P/O 170kV GIS 정밀점검공사(시험가압)","새만금S/S 154kV #62-#67 BUS-TIE GIS 정밀점검 무부하가압","2020-11-26 14:00","2020-11-26 16:00","2020-11-26 14:00","2020-11-26 16:00","연속"]
[419,"전북","군산","새만금소룡#2 T/L","'20년 군산P/O 170kV GIS 정밀점검공사(시험가압)","새만금S/S #3M.Tr 2차 GIS 정밀점검 무부하가압","2020-11-05 14:00","2020-11-05 16:00","2020-11-05 14:00","2020-11-05 16:00","연속"]
[420,"전북","군산","새만금소룡#1 T/L","'20년 군산P/O 170kV GIS 정밀점검공사","새만금S/S 154kV 새만금-소룡#1T/L GIS 정밀점검","2020-11-02 09:00","2020-11-03 18:00","2020-11-02 09:00","2020-11-03 18:00","연속"]
[421,"전북","군산","새만금소룡#1 T/L","'20년 군산P/O 170kV GIS 정밀점검공사(시험가압)","새만금S/S 345kV #2M.Tr 2차 GIS 정밀점검 무부하가압용","2020-11-24 14:00","2020-11-24 16:00","2020-11-24 14:00","2020-11-24 16:00","연속"]
[422,"전북","군산","군산서군산#2 T/L","군산P/O 154kV이상 차단기 점검공사","-서군산S/S 군산-서군산#2T/L 차단기 조작시험","2020-11-09 09:00","2020-11-10 18:00","2020-11-16 09:00","2020-11-17 18:00","연속"]
[423,"전북","군산","서군산소룡#1 T/L","군산P/O 154kV이상 차단기 점검공사","-서군산S/S 서군산-소룡#1T/L 차단기 점검","2020-11-12 09:00","2020-11-13 18:00","2020-11-19 09:00","2020-11-20 18:00","연속"]
[424,"전북","군산","군산서군산#1 T/L","군산P/O 기타변전설비 점검공사","-서군산S/S 군산-서군산#1T/L #1,2DS 점검","2020-11-11 09:00","2020-11-11 18:00","2020-11-18 09:00","2020-11-18 18:00","연속"]
[425,"전북","군산","군산이리#1 T/L","154kV 군산-이리T/L 안전이격확보공사","18,19호 신설철탑 조립 및 공중이동","2020-11-23 09:00","2020-11-27 18:00","2020-11-21 07:00","2020-11-22 18:00","연속"]
[426,"전북","군산","군산이리#2 T/L","154kV 군산-이리T/L 안전이격확보공사","18,19호 신설철탑 조립 및 공중이동","2020-11-16 09:00","2020-11-22 18:00","2020-11-14 07:00","2020-11-15 18:00","연속"]
[427,"전북","김제","김제부안#2 T/L","가스누기 보수공사 시험가압","김제S/S #1M.Tr 1차 GIS 가스누기 보수공사 시험가압","2020-11-04 09:00","2020-11-04 18:00","2020-11-04 09:00","2020-11-04 18:00","연속"]
[428,"전북","김제","칠보H/P 154kV CB 6100","154kV 차단기 보통점검","154kV 차단기 보통점검","2020-11-24 14:00","2020-11-24 18:00","2020-11-24 14:00","2020-11-24 18:00","연속"]
[429,"전북","김제","신김제S/S 154kV CB 6200","신김제S/S 노후 170GIS 교체공사","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-11 09:00","2020-11-13 18:00","2020-11-23 09:00","2020-12-24 18:00","연속"]
[430,"전북","김제","신김제S/S 154kV SEC CB 65660","신김제S/S 노후 170GIS 교체공사","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-11 09:00","2020-11-13 18:00","2020-11-23 09:00","2020-11-25 12:00","연속"]
[431,"전북","김제","신김제전주#2 T/L","신김제S/S 노후 170GIS 교체공사","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-11 09:00","2020-12-10 18:00","2020-11-23 09:00","2020-12-24 18:00","연속"]
[432,"전북","김제","신김제S/S 154kV #67 BUS","신김제S/S 인출송전 재배열 공사(시험가압)","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-09 09:00","2020-11-10 18:00","2020-11-18 09:00","2020-11-19 09:00","연속"]
[433,"전북","김제","신김제S/S 154kV CB 6300","신김제S/S 인출송전 재배열 공사(시험가압)","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-09 09:00","2020-11-10 18:00","2020-11-09 09:00","2020-11-20 09:00","연속"]
[434,"전북","김제","신김제남전주#2 T/L","신김제S/S 인출송전 재배열 공사 (6279 CB로 이동)","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 (Sh.C 철거 후 6279 CB로 이동) - 기타 부대공사 1식","2020-11-02 09:00","2020-11-10 18:00","2020-11-09 09:00","2020-11-20 18:00","연속"]
[435,"전북","김제","신김제전주#1 T/L","신김제S/S 인출송전 재배열 공사 (6179 CB로 이동)","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 (Sh.C 철거 후 6179 CB로 이동) - 기타 부대공사 1식","2020-11-03 09:00","2020-11-10 18:00","2020-11-10 13:00","2020-11-20 18:00","연속"]
[436,"전북","김제","신김제S/S 154kV #61 BUS","신김제S/S 노후 170GIS 교체공사","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-11 09:00","2020-11-13 18:00","2020-11-25 13:00","2020-12-02 09:00","연속"]
[437,"전북","김제","신김제S/S 154kV SEC CB 66670","신김제S/S 노후 170GIS 교체공사","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-11 09:00","2020-11-13 18:00","2020-11-23 09:00","2020-11-25 12:00","연속"]
[438,"전북","김제","신김제S/S 154kV #66 BUS","신김제S/S 노후 170GIS 교체공사","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-11 09:00","2020-11-13 18:00","2020-11-23 09:00","2020-11-25 12:00","연속"]
[439,"전북","김제","신김제S/S 154kV CB 6300","신김제S/S 노후 170GIS 교체공사(시험가압)","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-13 09:00","2020-11-14 18:00","취소","취소","연속"]
[440,"전북","김제","신김제남전주#2 T/L","신김제S/S 노후 170GIS 교체공사(시험가압)","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-13 09:00","2020-11-14 18:00","취소","취소","연속"]
[441,"전북","김제","신김제S/S 154kV #67 BUS","신김제S/S 노후 170GIS 교체공사(시험가압)","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-13 09:00","2020-11-14 18:00","취소","취소","연속"]
[442,"전북","김제","신김제S/S 154kV SEC CB 60610","신김제S/S 노후 170GIS 교체공사","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-13 18:00","2020-11-24 18:00","2020-11-25 13:00","2020-12-02 09:00","연속"]
[443,"전북","김제","신김제S/S 154kV CB 6200","신김제S/S 노후 170GIS 교체공사","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-13 18:00","2020-11-24 18:00","취소","취소","연속"]
[444,"전북","김제","신김제S/S 154kV #61 BUS","신김제S/S 노후 170GIS 교체공사","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-13 18:00","2020-11-24 18:00","취소","취소","연속"]
[445,"전북","김제","신김제S/S 154kV SEC CB 61620","신김제S/S 노후 170GIS 교체공사","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-13 18:00","2020-11-24 18:00","2020-11-25 13:00","2020-12-02 09:00","연속"]
[446,"전북","김제","신김제S/S 154kV SEC CB 66670","신김제S/S 노후 170GIS 교체공사","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-25 09:00","2020-12-08 18:00","취소","취소","연속"]
[447,"전북","김제","신김제S/S 154kV SEC CB 65660","신김제S/S 노후 170GIS 교체공사","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-25 09:00","2020-12-08 18:00","취소","취소","연속"]
[448,"전북","김제","신김제전주#2 T/L","신김제S/S 노후 170GIS 교체공사(안전이격)","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-02 09:00","2020-11-02 18:00","2020-11-10 08:00","2020-11-10 12:00","연속"]
[449,"전북","김제","신김제S/S 154kV SEC CB 66670","신김제S/S 노후 170GIS 교체공사","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-07 09:00","2020-11-09 18:00","2020-11-18 09:00","2020-11-19 09:00","연속"]
[450,"전북","김제","신김제남전주#1 T/L","신김제S/S 노후 170GIS 교체공사(재배치)","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-25 09:00","2020-12-08 18:00","2020-11-25 09:00","2020-11-25 12:00","연속"]
[451,"전북","김제","신김제S/S 154kV CB 6100","신김제S/S 노후 170GIS 교체공사","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-25 09:00","2020-12-08 18:00","취소","취소","연속"]
[452,"전북","김제","신김제S/S 154kV SEC CB 66670","신김제S/S 노후 170GIS 교체공사","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-11-11 09:00","2020-11-13 18:00","취소","취소","연속"]
[453,"전북","김제","정공S/S 154kV #1 BUS","정공S/S 170kV GIS 교체공사","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2020-11-16 09:30","2020-11-21 13:00","2020-11-16 09:30","2020-11-21 13:00","연속"]
[454,"전북","김제","정공S/S 154kV #2 BUS","정공S/S 170kV GIS 교체공사","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2020-11-22 09:30","2020-11-28 13:00","2020-11-22 09:30","2020-11-28 13:00","연속"]
[455,"전북","김제","정공S/S 154kV CB 6100","정공S/S 60-65 B/P PNL 설치, 61-66 B/P 회로개선","정공S/S 60-65 BUSPRO PNL 설치 및 61-66 BUSPRO 회로개선","2020-11-02 09:00","2020-11-06 18:00","2020-11-02 09:00","2020-11-06 18:00","연속"]
[456,"전북","김제","신김제정공#1 T/L","정공S/S 170kV GIS 교체공사 무부하가압","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2020-11-04 11:00","2020-11-04 13:00","2020-11-04 11:00","2020-11-04 13:00","연속"]
[457,"전북","김제","신김제정공#1 T/L","정공S/S 170kV GIS 교체공사 무부하가압","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2020-11-07 13:00","2020-11-08 13:00","2020-11-07 13:00","2020-11-08 13:00","연속"]
[458,"전북","김제","신김제정공#1 T/L","정공S/S 170kV GIS 교체공사 무부하 가압","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2020-11-12 13:00","2020-11-13 13:00","2020-11-12 13:00","2020-11-13 13:00","연속"]
[459,"전북","김제","정공칠보HP T/L","정공S/S 170kV GIS 교체공사 이격거리 확보","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2020-11-16 09:30","2020-11-18 13:00","2020-11-16 09:30","2020-11-18 13:00","매일"]
[460,"전북","김제","신김제정공#1 T/L","정공S/S 170kV GIS 교체공사 무부하가압","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2020-11-20 13:00","2020-11-21 13:00","2020-11-20 13:00","2020-11-21 13:00","연속"]
[461,"전북","김제","정공칠보HP T/L","정공S/S 170kV GIS 교체공사 이격거리확보","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2020-11-22 09:30","2020-11-27 13:00","2020-11-22 09:30","2020-11-27 13:00","매일"]
[462,"전북","김제","신김제정공#1 T/L","정공S/S 170kV GIS 교체공사 무부하가압","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2020-11-27 13:00","2020-11-28 13:00","2020-11-27 13:00","2020-11-28 13:00","연속"]
[463,"전북","김제","정공S/S 154kV #2 BUS","정공S/S 170kV GIS 교체공사","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2020-11-02 09:30","2020-11-04 13:00","2020-11-02 09:30","2020-11-04 13:00","연속"]
[464,"전북","김제","정공S/S 154kV #1 BUS","정공S/S 170kV GIS 교체공사","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2020-11-04 13:00","2020-11-08 13:00","2020-11-04 13:00","2020-11-08 13:00","연속"]
[465,"전북","김제","정공S/S 154kV #2 BUS","정공S/S 170kV GIS 교체공사","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2020-11-08 13:00","2020-11-13 13:00","2020-11-08 13:00","2020-11-13 13:00","연속"]
[466,"전북","직할","남원임실#1 T/L","154kV 남원S/S 옥외철구설비 GIS화 공사","○ 154kV 남원-임실#1T/L 인출구간 변경 및 GIS설비로 이전","2020-11-09 08:00","2020-11-18 18:00","2020-11-09 08:00","2020-11-18 18:00","연속"]
[467,"전북","직할","곡성남원#1 T/L","154kV 남원S/S 옥외철구설비 GIS화 공사","○ 154kV 곡성-남원#1T/L 인출구간 변경 및 GIS설비로 이전","2020-11-09 08:00","2020-11-18 18:00","2020-11-09 08:00","2020-11-18 18:00","연속"]
[468,"전북","직할","신김제동전주#2 T/L","154kV 신김제-동전주 등 3개T/L 아킹혼 설치공사","아킹혼 설치공사 ○ 154kV 신김제-동전주#2T/L No.32~83(일부구간, 35기)","2020-11-02 08:00","2020-11-04 18:00","2020-11-02 08:00","2020-11-04 18:00","매일"]
[469,"전북","직할","무주S/S 154kV #2 BUS","무주S/S 154kV GIS 교체공사(전문)","- 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2020-11-18 09:00","2020-11-30 18:00","취소","취소","연속"]
[470,"전북","직할","금산무주#1 T/L","무주S/S 154kV GIS 교체공사(Main 교체)","- 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2020-11-15 09:00","2020-12-23 18:00","취소","취소","연속"]
[471,"전북","직할","무주S/S 154kV CB 6100","무주S/S 154kV GIS 교체공사(Main 교체)","- 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2020-11-18 09:00","2020-12-23 18:00","취소","취소","연속"]
[472,"전북","직할","무주용담HP T/L","무주S/S 154kV GIS 교체공사(전문) (무부하가압)","*** 154kV #60BUS 무부하 가압 선로 - 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2020-11-30 09:00","2020-12-01 18:00","취소","취소","연속"]
[473,"전북","직할","무주용담HP T/L","무주S/S 154kV GIS 교체공사(전문) (무부하가압)","*** 154kV #60BUS 무부하 가압 선로 - 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2020-11-16 09:00","2020-11-17 18:00","2020-11-26 10:00","2020-11-27 10:00","연속"]
[474,"전북","직할","무주용담HP T/L","무주S/S 154kV GIS 교체공사(전문) (무부하가압)","*** 154kV #60BUS 무부하 가압 선로 - 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2020-11-05 09:00","2020-11-06 18:00","2020-11-16 10:00","2020-11-17 10:00","연속"]
[475,"전북","직할","무주진안 T/L","무주S/S 154kV GIS 교체공사(전문)(시험가압)","*** 무부하 가압용 선로 - 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2020-11-30 09:00","2020-12-01 18:00","취소","취소","연속"]
[476,"전북","직할","무주S/S 154kV #2 BUS","무주S/S 154kV GIS 교체공사(전문)","- 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2020-11-06 09:00","2020-11-17 18:00","2020-11-17 10:00","2020-11-27 10:00","연속"]
[477,"전북","직할","무주용담HP T/L","[송전] 154kV 금산-무주#1T/L 정밀점검","[송전] 154kV 무주-용담수력T/L(병가) 정밀점검","2020-11-11 07:30","2020-11-13 18:00","취소","취소","매일"]
[478,"전북","직할","무주진안 T/L","[송전] 154kV 금산-무주#1T/L 정밀점검","[송전] 154kV 무주-진안T/L(병가) 정밀점검","2020-11-07 07:30","2020-11-07 18:00","2020-11-07 07:30","2020-11-07 18:00","연속"]
[479,"전북","직할","무주진안 T/L","무주S/S 154kV GIS 교체공사(전문) (무부하가압)","*** 154kV #60BUS 무부하 가압 선로 - 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2020-11-16 10:00","2020-11-17 10:00","취소","취소","연속"]
[480,"전북","직할","무주진안 T/L","무주S/S 154kV GIS 교체공사(전문) (무부하가압)","*** 154kV #60BUS 무부하 가압 선로 - 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2020-11-05 10:00","2020-11-06 10:00","취소","취소","연속"]
[481,"전북","직할","북전주봉동#2 T/L","관내 154kV 이상 차단기 점검공사","154kV 차단기 조작시험 및 히터설치","2020-11-09 09:00","2020-11-09 14:00","2020-11-21 09:00","2020-11-21 14:00","연속"]
[482,"전북","직할","전주탄소#2 T/L","관내 154kV 이상 차단기 점검공사","154kV 차단기 보통점검","2020-11-09 14:00","2020-11-09 18:00","2020-11-09 14:00","2020-11-09 18:00","연속"]
[483,"전북","군산","동군산장항#1 T/L","154kV 동군산-장항T/L 용량증대 전선교체공사","장경간개소 용량증대 공사","2020-11-09 09:00","2020-11-12 18:00","2020-11-09 09:00","2020-11-12 18:00","연속"]
[484,"전북","군산","동군산장항#2 T/L","154kV 동군산-장항T/L 용량증대 전선교체공사","장경간개소 용량증대 공사","2020-11-09 09:00","2020-11-12 18:00","2020-11-13 09:00","2020-11-15 18:00","연속"]
[485,"전북","김제","정공담양 T/L","정공S/S 170kV GIS 교체공사 이격거리 확보","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2020-11-16 09:30","2020-11-18 13:00","2020-11-16 09:30","2020-11-18 13:00","매일"]
[486,"전북","김제","정공담양 T/L","정공S/S 170kV GIS 교체공사 이격거리확보","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2020-11-22 09:30","2020-11-27 13:00","2020-11-22 09:30","2020-11-27 13:00","매일"]
[487,"광주전남","강진","강진남창#1 T/L","'20~21년도 송전정비회사 총액공사","구 간 : 154kV강진-남창#1T/L No.43-103, 5경간 작업내용 : 가공지선 항공장애표시구 설치","2020-11-02 07:00","2020-11-04 18:00","2020-11-10 07:00","2020-11-12 18:00","연속"]
[488,"광주전남","강진","신강진대불#1 T/L","20-21년 강진전력지사 변전정비회사 총액공사","신강진,대불S/S 신강진-대불#1T/L 보호반 대체","2020-11-16 08:00","2020-11-18 14:00","2020-11-16 08:00","2020-11-18 14:00","연속"]
[489,"광주전남","강진","신강진대불#2 T/L","20-21년 강진전력지사 변전정비회사 총액공사","신강진, 대불S/S 신강진-대불#2T/L 보호반 대체","2020-11-18 14:00","2020-11-20 18:00","2020-11-18 14:00","2020-11-20 18:00","연속"]
[490,"광주전남","강진","장흥벌교 T/L","장흥S/S 장기사용 GIS 대체공사","장흥S/S 154kV #2BUS 무부하 가압 장흥S/S 154kV #1BUS 무부하 가압","2020-11-02 18:00","2020-11-15 18:00","2020-11-02 18:00","2020-11-15 18:00","연속"]
[491,"광주전남","강진","강진장흥#1 T/L","장흥S/S 장기사용 GIS 대체공사","강진-장흥#1T/L GIS 대체 #2M.Tr 1차 GIS 대체","2020-11-02 09:00","2020-11-15 18:00","2020-11-02 09:00","2020-11-15 18:00","연속"]
[492,"광주전남","강진","해남진도#1 T/L","'20~21년도 송전정비회사 총액공사","구 간 : 154kV해남-진도#1T/L No.88-91, 2경간 작업내용 : 가공지선 항공장애표시구 설치","2020-11-05 07:00","2020-11-05 18:00","2020-11-05 07:00","2020-11-05 18:00","연속"]
[493,"광주전남","광주","담양일곡#2 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치","2020-11-13 09:00","2020-11-13 18:00","2020-11-13 09:00","2020-11-13 18:00","연속"]
[494,"광주전남","광주","담양일곡#1 T/L","EB-A 부분방전 진단센서 설치공사","UWB센서 및 PD집합반 설치","2020-11-12 09:00","2020-11-12 18:00","2020-11-12 09:00","2020-11-12 18:00","연속"]
[495,"광주전남","광주","북광주일곡#2 T/L","154kV 일곡S/S #4M.Tr 증설공사","154kV 일곡S/S #4M.Tr 증설공사 무부하 가압","2020-11-05 09:00","2020-11-06 18:00","2020-11-11 09:00","2020-11-12 18:00","연속"]
[496,"광주전남","광주","신광주일곡#2 T/L","2020년 광주전력지사 170kV GIS 정밀점검공사","2020년 광주전력지사 170kV GIS 정밀점검공사","2020-11-04 09:00","2020-11-05 18:00","취소","취소","연속"]
[497,"광주전남","광주","신광주일곡#1 T/L","2020년 광주전력지사 170kV GIS 정밀점검공사","2020년 광주전력지사 170kV GIS 정밀점검공사 - 일곡S/S : GIS CB, 상부BUS 정밀점검 - 신광주S/S : LS산전제 DS Shaft축 마모관련 621DS 정밀점검","2020-11-02 09:00","2020-11-03 18:00","취소","취소","연속"]
[498,"광주전남","광주","북광주일곡#2 T/L","154kV 일곡S/S #4M.Tr 증설공사","154kV 일곡S/S #4M.Tr 증설공사 사용전검사","2020-11-09 09:00","2020-11-10 18:00","2020-11-30 09:00","2020-11-30 18:00","연속"]
[499,"광주전남","광주","하남장성#2 T/L","2020년 광주전력지사 170kV GIS 정밀점검공사","2020년 광주전력지사 170kV GIS 정밀점검공사","2020-11-16 09:00","2020-11-18 18:00","2020-11-23 09:00","2020-11-24 18:00","연속"]
[500,"광주전남","광주","신광주장성#1 T/L","2020년 광주전력지사 170kV GIS 정밀점검공사","2020년 광주전력지사 170kV GIS 정밀점검공사","2020-11-02 09:00","2020-11-04 18:00","2020-11-11 09:00","2020-11-13 18:00","연속"]
[501,"광주전남","광주","하남장성#1 T/L","2020년 광주전력지사 170kV GIS 정밀점검공사","2020년 광주전력지사 170kV GIS 정밀점검공사","2020-11-09 09:00","2020-11-11 18:00","2020-11-18 09:00","2020-11-20 18:00","연속"]
[502,"광주전남","순천","광양순천#2 T/L","20(하)170kV GIS 정밀점검공사","광양S/S 광양-순천#1T/L GIS 정밀점검(CB,상부모선)","2020-11-12 09:00","2020-11-13 18:00","2020-11-12 09:00","2020-11-13 18:00","연속"]
[503,"광주전남","순천","광양순천#1 T/L","20(하)170kV GIS 정밀점검공사","광양S/S 광양-순천#1T/L GIS 정밀점검(CB,상부모선)","2020-11-10 09:00","2020-11-11 18:00","2020-11-10 09:00","2020-11-11 18:00","연속"]
[504,"광주전남","순천","승주서순천 T/L","20-21년 변전정비회사 총액공사","서순천 승주-서순천T/L GIS 타임측정","2020-11-13 09:00","2020-11-13 18:00","2020-11-13 09:00","2020-11-13 18:00","연속"]
[505,"광주전남","순천","여수T/P 154kV CB 6200","20-21년 변전정비회사 총액공사","여수화력 6200BUS-TIE GIS 보통점검","2020-11-10 09:00","2020-11-10 18:00","2020-11-10 09:00","2020-11-10 18:00","연속"]
[506,"광주전남","순천","여천여수#1 T/L","154kV 여천여수#1 T/L 4회선 병가구간 휴전","20년 가공송전 순시점검 위탁공사-여천-호남T/P#2 정밀점검","2020-11-11 09:00","2020-11-11 18:00","2020-11-11 09:00","2020-11-11 18:00","연속"]
[507,"광주전남","순천","여천여수#2 T/L","154kV 여천여수#2 T/L 4회선 병가구간 휴전","20년 가공송전 순시점검 위탁공사-여천-호남T/P#1 정밀점검","2020-11-04 09:00","2020-11-04 18:00","2020-11-04 09:00","2020-11-04 18:00","연속"]
[508,"광주전남","순천","여천호남TP#1 T/L","154kV 여천호남TP#1 T/L 정밀점검","20년 가공송전 순시점검 위탁공사","2020-11-02 09:00","2020-11-04 18:00","2020-11-02 09:00","2020-11-04 18:00","매일"]
[509,"광주전남","순천","호남TP여수TP#1 T/L","154kV 호남TP여수TP#1 T/L 정밀점검","20년 가공송전 순시점검 위탁공사","2020-11-02 09:00","2020-11-02 18:00","2020-11-02 09:00","2020-11-02 18:00","연속"]
[510,"광주전남","순천","호남TP여수TP#2 T/L","154kV 호남TP여수TP#2 T/L 정밀점검","20년 가공송전 순시점검 위탁공사","2020-11-09 09:00","2020-11-09 18:00","2020-11-09 09:00","2020-11-09 18:00","연속"]
[511,"광주전남","순천","여천호남TP#2 T/L","154kV 여천호남TP#2 T/L 정밀점검","20년 가공송전 순시점검 위탁공사","2020-11-09 09:00","2020-11-11 18:00","2020-11-09 09:00","2020-11-11 18:00","매일"]
[512,"광주전남","직할","농성화정#2 T/L","농성S/S 154kV 농성-화정 #2T/L (PNL 교체)","2020~2021 광주전남본부 직할 변전정비회사 총액공사","2020-11-11 09:00","2020-11-13 18:00","2020-11-11 09:00","2020-11-13 18:00","연속"]
[513,"광주전남","직할","매월화정#1 T/L","'20~21년 직할 변전정비회사 총액공사(PNL 교체)","ㅇ 매월-화정#1T/L 보호반 교체","2020-11-16 09:00","2020-11-18 18:00","2020-11-30 09:00","2020-12-02 18:00","연속"]
[514,"광주전남","직할","일곡비아#1 T/L","20~21년 직할 변전정비회사 총액공사","170kV GIS 초기점검","2020-11-03 09:00","2020-11-03 13:00","2020-11-09 09:00","2020-11-09 13:00","연속"]
[515,"광주전남","순천","순천승주#2 T/L","보호배전반 유사고장관련 성능개선 공사","보호배전반 유사고장관련 성능개선","2020-11-03 09:00","2020-11-03 18:00","2020-11-24 09:00","2020-11-24 18:00","연속"]
[516,"광주전남","강진","강진남창#1 T/L","'20~21년도 송전정비회사 총액공사","구 간 : 154kV강진-남창#1T/L No.43-103, 5경간 작업내용 : 가공지선 항공장애표시구 설치","2020-10-28 09:00","2020-11-11 18:00","취소","취소","연속"]
[517,"광주전남","순천","여천여수산단#1 T/L","20~21년 직할 변전정비회사 총액공사","여수산단 여천여수산단#2T/L 1DS 가스누기 조치","2020-11-02 09:00","2020-11-03 18:00","2020-11-19 09:00","2020-11-20 18:00","연속"]
[518,"광주전남","순천","여천여수산단#2 T/L","20~21년 직할 변전정비회사 총액공사","여수산단 여천여수산단#2T/L 1DS 가스누기 조치","2020-11-02 09:00","2020-11-03 18:00","2020-11-19 09:00","2020-11-20 18:00","연속"]
[519,"대구","경산","노변시지#1 T/L","20년 하반기 경산P/O 170kV GIS 정밀점검","- 657GIS 차단부 정밀점검 및 공기조작부(전자변) 교체","2020-11-05 09:00","2020-11-06 18:00","2020-11-05 09:00","2020-11-06 18:00","연속"]
[520,"대구","경산","신경산노변 T/L","20년 하반기 경산P/O 170kV GIS 정밀점검","- 노변 6100GIS 정밀점검무부하가압선로","2020-11-20 17:00","2020-11-20 18:00","2020-11-20 17:00","2020-11-20 18:00","연속"]
[521,"대구","경산","노변시지#2 T/L","경산P/O 하반기 정밀점검공사","- 687GIS 차단부 정밀점검 및 공기조작부(전자변) 교체","2020-11-09 09:00","2020-11-10 18:00","2020-11-09 09:00","2020-11-10 18:00","연속"]
[522,"대구","경산","신경산노변 T/L","20년 하반기 경산P/O 170kV GIS 정밀점검","- 노변 6133GIS 정밀점검무부하가압선로","2020-11-13 17:00","2020-11-13 18:00","2020-11-13 17:00","2020-11-13 18:00","연속"]
[523,"대구","경산","신경산노변 T/L","20년 하반기 경산P/O 170kV GIS 정밀점검","- 노변 6233GIS 정밀점검무부하가압선로","2020-11-17 17:00","2020-11-17 18:00","2020-11-17 17:00","2020-11-17 18:00","연속"]
[524,"대구","경산","신경산진량 T/L","20년 하반기 경산P/O 170kV GIS 정밀점검","- 진량 6433GIS 정밀점검무부하가압선로","2020-11-03 17:00","2020-11-03 18:00","2020-11-03 17:00","2020-11-03 18:00","연속"]
[525,"대구","경산","청도밀양#1 T/L","154kV 대구-청도T/L OPGW 광코아 용량증설 공사","ㅇ 대구-청도 No.33~40호 OPGW 교체작업 : No.40호 병가철탑 안전확보","2020-11-12 08:00","2020-11-12 18:00","2020-11-12 08:00","2020-11-12 18:00","연속"]
[526,"대구","달성","강창성서#1 T/L","20-21년 가공송전정비회사 총액공사","애자련 교체공사(ST)","2020-11-07 08:00","2020-11-07 14:00","2020-11-07 08:00","2020-11-07 14:00","연속"]
[527,"대구","달성","강창성서#2 T/L","20-21년 가공송전정비회사 총액공사","애자련 교체공사(ST)","2020-11-07 14:00","2020-11-07 18:00","2020-11-07 14:00","2020-11-07 18:00","연속"]
[528,"대구","달성","다산강창#2 T/L","20-21년 가공송전정비회사 총액공사","애자련 교체공사(No.19 등 11기)","2020-11-24 08:00","2020-11-27 18:00","2020-11-24 08:00","2020-11-27 18:00","연속"]
[529,"대구","달성","다산강창#1 T/L","20-21년 가공송전정비회사 총액공사","애자련 교체공사(No.19 등 11기)","2020-11-17 08:00","2020-11-20 18:00","2020-11-17 08:00","2020-11-20 18:00","연속"]
[530,"대구","달성","창녕구지#1 T/L","20-21년 가공송전정비회사 총액공사","회전형 스페이서 설치(No.99~100)","2020-11-10 08:00","2020-11-10 18:00","2020-11-10 08:00","2020-11-10 18:00","연속"]
[531,"대구","달성","달성S/S 154kV CB 6100","달성S/S 6100 전자변 교체작업","달성S/S 6100 전자변 교체작업","2020-11-23 09:00","2020-11-23 18:00","2020-11-23 09:00","2020-11-23 18:00","연속"]
[532,"대구","달성","대구청도#2 T/L","154kV 대구-청도T/L 송전용량증대 전선교체공사","대구S/T ~ 대구-청도T/L 15호, 대구-청도T/L 22~39호 송전용량증대 전선교체공사","2020-11-12 07:00","2020-11-20 18:00","2020-11-12 07:00","2020-11-20 18:00","연속"]
[533,"대구","달성","대구청도#1 T/L","154kV 대구-청도T/L 송전용량증대 전선교체공사","대구S/T ~ 대구-청도T/L 15호, 대구-청도T/L 22~39호 송전용량증대 전선교체공사","2020-11-03 07:00","2020-11-11 18:00","2020-11-02 07:00","2020-11-10 18:00","연속"]
[534,"대구","달성","두류봉덕#1 T/L","두류,봉덕S/S 두류-봉덕#1T/L 보호반 대체작업","두류,봉덕S/S 두류-봉덕#1T/L 보호반 대체작업","2020-11-10 09:00","2020-11-11 18:00","2020-11-10 09:00","2020-11-11 18:00","연속"]
[535,"대구","달성","대구봉덕#2 T/L","봉덕S/S 대구-봉덕#1,2T/L 차단기동작시험","봉덕S/S 대구-봉덕#1,2T/L 차단기동작시험","2020-11-23 14:00","2020-11-23 18:00","2020-11-23 14:00","2020-11-23 18:00","연속"]
[536,"대구","달성","대구봉덕#1 T/L","봉덕S/S 대구-봉덕#1,2T/L 차단기동작시험","봉덕S/S 대구-봉덕#1,2T/L 차단기동작시험","2020-11-23 09:00","2020-11-23 14:00","2020-11-23 09:00","2020-11-23 14:00","연속"]
[537,"대구","달성","상인봉덕#2 T/L","상인,봉덕S/S 상인-봉덕#2T/L 보호반대체작업","상인,봉덕S/S 상인-봉덕#2T/L 보호반대체작업","2020-11-12 09:00","2020-11-13 18:00","2020-11-12 09:00","2020-11-13 18:00","연속"]
[538,"대구","달성","성서달성#1 T/L","성서,달성S/S 성서-달성#1T/L 보호반 대체작업","성서,달성S/S 성서-달성#1T/L 보호반 대체작업","2020-11-21 09:00","2020-11-22 18:00","2020-11-21 09:00","2020-11-22 18:00","연속"]
[539,"대구","달성","성서달성#2 T/L","성서,달성S/S 성서-달성#2T/L 보호반 대체작업","성서,달성S/S 성서-달성#2T/L 보호반 대체작업","2020-11-28 09:00","2020-11-29 18:00","2020-11-28 09:00","2020-11-29 18:00","연속"]
[540,"대구","달성","고령쌍림#2 T/L","쌍림S/S 154kV 모선보호반 대체작업(TEST선로)","쌍림S/S 154kV 모선보호반 대체작업(TEST선로)","2020-11-26 16:30","2020-11-26 17:00","2020-11-26 16:30","2020-11-26 17:00","연속"]
[541,"대구","달성","고령쌍림#1 T/L","쌍림S/S 154kV 모선보호반 대체작업(TEST선로)","쌍림S/S 154kV 모선보호반 대체작업(TEST선로)","2020-11-26 16:00","2020-11-26 16:30","2020-11-26 16:00","2020-11-26 16:30","연속"]
[542,"대구","달성","쌍림합천#1 T/L","쌍림S/S 154kV 모선보호반 대체작업(TEST선로)","쌍림S/S 154kV 모선보호반 대체작업(TEST선로)","2020-11-26 15:00","2020-11-26 15:30","2020-11-26 15:00","2020-11-26 15:30","연속"]
[543,"대구","달성","쌍림합천#2 T/L","쌍림S/S 154kV 모선보호반 대체작업(TEST선로)","쌍림S/S 154kV 모선보호반 대체작업(TEST선로)","2020-11-26 14:00","2020-11-26 14:30","2020-11-26 14:00","2020-11-26 14:30","연속"]
[544,"대구","직할","공평서침산 T/L","변전소 인출구간 OF 선종교체 공사","변전소 인출구간 OF 선로 철거, XLPE 케이블 포설","2020-11-16 09:00","2020-12-18 18:00","2020-11-16 09:00","2020-12-18 18:00","연속"]
[545,"대구","직할","남대구동인#1 T/L","남대구 전자변교체, GIS 보통점검","남대구 전자변교체, GIS 보통점검","2020-11-11 09:30","2020-11-13 18:00","2020-11-11 09:30","2020-11-13 18:00","연속"]
[546,"대구","직할","남대구동인#2 T/L","남대구 전자변교체, GIS 보통점검","남대구 전자변교체, GIS 보통점검","2020-11-18 09:30","2020-11-20 18:00","2020-11-18 09:30","2020-11-20 18:00","연속"]
[547,"대구","직할","공평서침산 T/L","모선보호반 교체(TEST)","모선보호반 교체(TEST)","2020-11-15 09:30","2020-11-15 10:00","2020-11-15 09:30","2020-11-15 10:00","연속"]
[548,"대구","칠곡","구미광평#2 T/L","광평S/S 154kV 모선보호반 대체","광평S/S 154kV 모선보호반 대체","2020-11-12 11:30","2020-11-12 12:00","2020-11-12 11:30","2020-11-12 12:00","연속"]
[549,"대구","칠곡","구미광평#1 T/L","구미-광평#1T/L 송전선로 보호반 대체작업","구미-광평#1T/L 송전선로 보호반 대체작업","2020-11-18 09:00","2020-11-19 18:00","2020-11-18 09:00","2020-11-19 18:00","연속"]
[550,"대구","칠곡","구미광평#2 T/L","구미-광평#2T/L 송전선로 보호반 대체작업","구미-광평#2T/L 송전선로 보호반 대체작업","2020-11-30 09:00","2020-12-01 18:00","2020-11-30 09:00","2020-12-01 18:00","연속"]
[551,"대구","칠곡","구미광평#1 T/L","광평S/S 154kV 모선보호반 대체","광평S/S 154kV 모선보호반 대체","2020-11-12 11:00","2020-11-12 11:30","2020-11-12 11:00","2020-11-12 11:30","연속"]
[552,"대구","칠곡","북대구구암#2 T/L","345kV 신포항-북대구T/L 지장송전선로 이설공사","도남지구 공공택지 조성관련 지장이설공사 45~47호 철거/설치 관련 선로 하단 안전확보","2020-11-01 08:00","2020-11-24 18:00","2020-11-01 08:00","2020-11-24 18:00","매일"]
[553,"대구","칠곡","북대구구암#1 T/L","345kV 신포항-북대구T/L 지장송전선로 이설공사","도남지구 공공택지 조성관련 지장이설공사 45~47호 철거/설치 관련 선로 하단 안전확보","2020-11-01 08:00","2020-11-24 18:00","2020-11-01 08:00","2020-11-24 18:00","매일"]
[554,"대구","포항","건천천북#2 T/L","154kV 건천-천북T/L 지장송전선로 지중화 공사 임시선로 구성","154kV 건천-천북T/L No.5,7,8 임시철탑 신설","2020-11-10 08:00","2020-11-15 18:00","취소","취소","연속"]
[555,"대구","포항","아화건천#2 T/L","154kV 아화-건천T/L OPGW 교체작업","154kV 건천-천북T/L ST~No.4 GW 긴선철거","2020-11-07 08:00","2020-11-07 18:00","2020-11-07 08:00","2020-11-07 18:00","연속"]
[556,"대구","포항","건천천북#1 T/L","154kV 건천-천북T/L 지장송전선로 지중화 공사 임시선로 구성","154kV 건천-천북T/L No.5,7,8 임시철탑 신설","2020-11-06 08:00","2020-11-09 18:00","취소","취소","연속"]
[557,"대구","포항","포항경주 T/L","154kV 경주S/S 옥내화공사","신설 경주SA 변전소 최초가압","2020-11-02 09:00","2020-11-15 18:00","2020-11-02 09:00","2020-11-15 18:00","연속"]
[558,"대구","포항","아화건천#1 T/L","154kV 아화-건천T/L 안전이격거리 확보공사","- 작업구간 : No.34-42 - 철탑 5기 철거 및 설치 - 양회선 동시휴전","2020-11-26 07:00","2020-12-04 18:00","2020-11-26 07:00","2020-12-04 18:00","연속"]
[559,"대구","포항","아화건천#2 T/L","154kV 아화-건천T/L 안전이격거리 확보공사","- 작업구간 : No.34-42 - 철탑 5기 철거 및 설치 - 양회선 동시휴전","2020-11-26 07:00","2020-12-04 18:00","2020-11-26 07:00","2020-12-04 18:00","연속"]
[560,"대구","포항","울주외동#2 T/L","외동S/S 울주-외동#1,2T/L GIS 조작시험","외동S/S 울주-외동#1,2T/L GIS 조작시험","2020-11-19 14:00","2020-11-19 18:00","2020-11-19 14:00","2020-11-19 18:00","연속"]
[561,"대구","포항","울주입실#2 T/L","2020-21년 포항전력지사 가공송전 정비회사 총액공사","345kV울주-월성NP#2 T/L 고정형 폴리머점퍼지지애자 설치(안전확보)","2020-11-30 08:00","2020-11-30 18:00","2020-11-30 08:00","2020-11-30 18:00","연속"]
[562,"대구","포항","영일포항#1 T/L","154kV 영일-포항T/L 안전이격거리확보공사 [2회선 동시휴전]","- 지지물 설치 : (신설) No.14 (1기) - 지지물 철거 : (기설) No.14 (1기) - 지지물 보강 : (기설) No.14 (1기) - 전력선 교체 : 2.295C-km (HSTACIR 410)","2020-11-16 08:00","2020-11-22 18:00","2020-11-16 08:00","2020-11-22 18:00","연속"]
[563,"대구","포항","영일포항#2 T/L","154kV 영일-포항T/L 안전이격거리확보공사 [2회선 동시휴전]","- 지지물 설치 : (신설) No.14 (1기) - 지지물 철거 : (기설) No.14 (1기) - 지지물 보강 : (기설) No.14 (1기) - 전력선 교체 : 2.295C-km (HSTACIR 410)","2020-11-16 08:00","2020-11-22 18:00","2020-11-16 08:00","2020-11-22 18:00","연속"]
[564,"경북","구미","남인동인동#1 T/L","남인동S/S 170kV GIS교체공사[3차수]","- 남인동-인동#1(687), #1M.Tr(6133) GIS교체","2020-11-02 09:00","2020-11-23 09:00","2020-11-02 09:00","2020-11-23 09:00","연속"]
[565,"경북","구미","서대구남인동#1 T/L","남인동S/S 170kV GIS교체공사[4차수]","- 서대구-남인동#1T/L(617) GIS교체 - 에스아이엘T/L(627) GIS철거","2020-11-24 09:00","2020-12-14 09:00","2020-11-24 09:00","2020-12-14 09:00","연속"]
[566,"경북","구미","남인동인동#2 T/L","남인동S/S 170kV GIS교체공사[4차수]","- 서대구-남인동#1T/L(617) GIS교체 - 에스아이엘T/L(627) GIS철거 - 무부하가압용 선로(즉시가압 가능)","2020-11-25 18:00","2020-11-26 09:00","2020-11-25 18:00","2020-11-26 09:00","연속"]
[567,"경북","구미","남인동S/S 154kV #1 BUS","남인동S/S 170kV GIS교체공사[4차수]","- 서대구-남인동#1T/L(617) GIS교체 - 에스아이엘T/L(627) GIS철거","2020-11-26 09:00","2020-12-07 09:00","2020-11-26 09:00","2020-12-07 09:00","연속"]
[568,"경북","구미","점촌동상주개폐소#2 T/L","구미전력지사 관내 `96년 이전 불량애자 교체공사","154kV 동상주-점촌 등 10개T/L o 교체대상 : 96년 상반기 이전 현수애자 o 애자종류 : 25000LBS 및 36000LBS","2020-11-03 07:00","2020-11-03 18:00","2020-11-03 07:00","2020-11-03 18:00","연속"]
[569,"경북","구미","점촌동상주개폐소#1 T/L","구미전력지사 관내 `96년 이전 불량애자 교체공사","154kV 동상주-점촌 등 10개T/L o 교체대상 : 96년 상반기 이전 현수애자 o 애자종류 : 25000LBS 및 36000LBS","2020-11-02 07:00","2020-11-02 18:00","2020-11-02 07:00","2020-11-02 18:00","연속"]
[570,"경북","구미","상주영동 T/L","구미전력지사 관내 `96년 이전 불량애자 교체공사","154kV 동상주-점촌 등 10개T/L(안전확보) o 교체대상 : 96년 상반기 이전 현수애자 o 애자종류 : 25000LBS 및 36000LBS","2020-11-07 07:00","2020-11-07 18:00","2020-11-07 07:00","2020-11-07 18:00","연속"]
[571,"경북","구미","선산청리#1 T/L","구미전력지사 관내 `96년 이전 불량애자 교체공사","154kV 동상주-점촌 등 10개T/L(안전확보) o 교체대상 : 96년 상반기 이전 현수애자 o 애자종류 : 25000LBS 및 36000LBS","2020-11-10 07:00","2020-11-12 18:00","2020-11-10 07:00","2020-11-12 18:00","매일"]
[572,"경북","구미","선산청리#2 T/L","구미전력지사 관내 `96년 이전 불량애자 교체공사","154kV 동상주-점촌 등 10개T/L(안전확보) o 교체대상 : 96년 상반기 이전 현수애자 o 애자종류 : 25000LBS 및 36000LBS","2020-11-14 07:00","2020-11-16 18:00","2020-11-14 07:00","2020-11-16 18:00","매일"]
[573,"경북","구미","청리상주#2 T/L","구미전력지사 관내 `96년 이전 불량애자 교체공사","154kV 동상주-점촌 등 10개T/L(안전확보) o 교체대상 : 96년 상반기 이전 현수애자 o 애자종류 : 25000LBS 및 36000LBS","2020-11-11 07:00","2020-11-12 18:00","2020-11-11 07:00","2020-11-12 18:00","매일"]
[574,"경북","영주","문경단양 T/L","2020년 영주전력지사 170kV GIS 정밀점검","- 627CB 정밀점검 - LA 보통점검","2020-11-20 09:00","2020-11-22 18:00","2020-11-20 09:00","2020-11-22 18:00","연속"]
[575,"경북","영주","예천점촌#1 T/L","20-21년 가공송전 정비회사 총액공사","154kV 신영주-안동 등 7개T/L 불량애자 교체공사","2020-11-08 07:00","2020-11-10 18:00","2020-11-07 07:00","2020-11-08 18:00","연속"]
[576,"경북","영주","점촌단양 T/L","20-21년 가공송전 정비회사 총액공사","154kV 신영주-안동 등 7개T/L 불량애자 교체공사","2020-11-11 07:00","2020-11-12 18:00","취소","취소","연속"]
[577,"경북","영주","점촌문경 T/L","20-21년 가공송전 정비회사 총액공사","154kV 신영주-안동 등 7개T/L 불량애자 교체공사","2020-11-15 07:00","2020-11-15 18:00","취소","취소","연속"]
[578,"경북","영주","예천점촌#2 T/L","20-21년 가공송전 정비회사 총액공사","154kV 신영주-안동 등 7개T/L 불량애자 교체공사","2020-11-14 07:00","2020-11-16 18:00","2020-11-14 07:00","2020-11-15 18:00","연속"]
[579,"경북","직할","동안동임하HP T/L","'20-21년 경북직할 가공송전 정비회사 총액공사","154kV 동상주-풍산 등 7개T/L 불량애자교체공사 ○ 154kV 동상주-풍산T/L 4기, 동안동-임하HPT/L 2기, 신영주-안동T/L 5기, 안동-동안동T/L 8기, 영덕-진보T/L 1기, 울진-현종산풍력T/L 8기, 현종산-평해T/L 7기 154kV 영덕-평해 등 5개T/L 점퍼지지애자 교체공사 ○ 154kV 영덕-평해T/L 11기, 동안동-임하HPT/L 3기, 신영주-안동T/L 1기, 영덕-진보T/L 6기, 안동-동안동T/L 6기","2020-11-20 13:00","2020-11-27 18:00","2020-11-24 09:00","2020-11-25 18:00","연속"]
[580,"경북","직할","신영주안동#1 T/L","'20-21년 경북직할 가공송전 정비회사 총액공사","154kV 동상주-풍산 등 7개T/L 불량애자교체공사 ○ 154kV 동상주-풍산T/L 4기, 동안동-임하HPT/L 2기, 신영주-안동T/L 5기, 안동-동안동T/L 8기, 영덕-진보T/L 1기, 울진-현종산풍력T/L 8기, 현종산-평해T/L 7기 154kV 영덕-평해 등 5개T/L 점퍼지지애자 교체공사 ○ 154kV 영덕-평해T/L 11기, 동안동-임하HPT/L 3기, 신영주-안동T/L 1기, 영덕-진보T/L 6기, 안동-동안동T/L 6기","2020-11-09 09:00","2020-11-13 18:00","2020-11-13 09:00","2020-11-13 18:00","연속"]
[581,"경북","직할","신영주안동#2 T/L","'20-21년 경북직할 가공송전 정비회사 총액공사","154kV 동상주-풍산 등 7개T/L 불량애자교체공사 ○ 154kV 동상주-풍산T/L 4기, 동안동-임하HPT/L 2기, 신영주-안동T/L 5기, 안동-동안동T/L 8기, 영덕-진보T/L 1기, 울진-현종산풍력T/L 8기, 현종산-평해T/L 7기 154kV 영덕-평해 등 5개T/L 점퍼지지애자 교체공사 ○ 154kV 영덕-평해T/L 11기, 동안동-임하HPT/L 3기, 신영주-안동T/L 1기, 영덕-진보T/L 6기, 안동-동안동T/L 6기","2020-11-02 09:00","2020-11-06 18:00","2020-11-16 09:00","2020-11-17 18:00","연속"]
[582,"경북","직할","안동동안동#2 T/L","'20-21년 경북직할 가공송전 정비회사 총액공사","154kV 동상주-풍산 등 7개T/L 불량애자교체공사 ○ 154kV 동상주-풍산T/L 4기, 동안동-임하HPT/L 2기, 신영주-안동T/L 5기, 안동-동안동T/L 8기, 영덕-진보T/L 1기, 울진-현종산풍력T/L 8기, 현종산-평해T/L 7기 154kV 영덕-평해 등 5개T/L 점퍼지지애자 교체공사 ○ 154kV 영덕-평해T/L 11기, 동안동-임하HPT/L 3기, 신영주-안동T/L 1기, 영덕-진보T/L 6기, 안동-동안동T/L 6기","2020-11-19 09:00","2020-11-20 18:00","2020-11-19 09:00","2020-11-20 18:00","연속"]
[583,"경북","직할","안동동안동#1 T/L","'20-21년 경북직할 가공송전 정비회사 총액공사","154kV 동상주-풍산 등 7개T/L 불량애자교체공사 ○ 154kV 동상주-풍산T/L 4기, 동안동-임하HPT/L 2기, 신영주-안동T/L 5기, 안동-동안동T/L 8기, 영덕-진보T/L 1기, 울진-현종산풍력T/L 8기, 현종산-평해T/L 7기 154kV 영덕-평해 등 5개T/L 점퍼지지애자 교체공사 ○ 154kV 영덕-평해T/L 11기, 동안동-임하HPT/L 3기, 신영주-안동T/L 1기, 영덕-진보T/L 6기, 안동-동안동T/L 6기","2020-11-23 09:00","2020-11-25 18:00","2020-11-23 09:00","2020-11-25 18:00","연속"]
[584,"경북","직할","영덕진보#1 T/L","'20-21년 경북직할 가공송전 정비회사 총액공사","154kV 동상주-풍산 등 7개T/L 불량애자교체공사 ○ 154kV 동상주-풍산T/L 4기, 동안동-임하HPT/L 2기, 신영주-안동T/L 5기, 안동-동안동T/L 8기, 영덕-진보T/L 1기, 울진-현종산풍력T/L 8기, 현종산-평해T/L 7기 154kV 영덕-평해 등 5개T/L 점퍼지지애자 교체공사 ○ 154kV 영덕-평해T/L 11기, 동안동-임하HPT/L 3기, 신영주-안동T/L 1기, 영덕-진보T/L 6기, 안동-동안동T/L 6기","2020-11-11 09:00","2020-11-11 18:00","2020-11-12 09:00","2020-11-12 18:00","연속"]
[585,"경북","직할","영덕진보#2 T/L","'20-21년 경북직할 가공송전 정비회사 총액공사","154kV 동상주-풍산 등 7개T/L 불량애자교체공사 ○ 154kV 동상주-풍산T/L 4기, 동안동-임하HPT/L 2기, 신영주-안동T/L 5기, 안동-동안동T/L 8기, 영덕-진보T/L 1기, 울진-현종산풍력T/L 8기, 현종산-평해T/L 7기 154kV 영덕-평해 등 5개T/L 점퍼지지애자 교체공사 ○ 154kV 영덕-평해T/L 11기, 동안동-임하HPT/L 3기, 신영주-안동T/L 1기, 영덕-진보T/L 6기, 안동-동안동T/L 6기","2020-11-12 09:00","2020-11-12 18:00","취소","취소","연속"]
[586,"경북","직할","울진삼척GP#1 T/L","20~21년 경북본부 직할 변전정비회사 총액공사","GIS 보통점검, CVT 초기점검","2020-11-12 09:00","2020-11-12 18:00","2020-11-12 09:00","2020-11-12 18:00","연속"]
[587,"경북","직할","봉화울진 T/L","'20-21년 경북직할 가공송전 정비회사 총액공사","154kV 동상주-풍산 등 7개T/L 불량애자교체공사 ○ 154kV 동상주-풍산T/L 4기, 동안동-임하HPT/L 2기, 신영주-안동T/L 5기, 안동-동안동T/L 8기, 영덕-진보T/L 1기, 울진-현종산풍력T/L 8기, 현종산-평해T/L 7기","2020-11-02 09:00","2020-11-02 18:00","2020-11-02 09:00","2020-11-02 18:00","연속"]
[588,"경북","직할","울진삼척GP#2 T/L","20~21년 경북본부 직할 변전정비회사 총액공사","GIS 보통점검, CVT 초기점검","2020-11-13 09:00","2020-11-13 18:00","2020-11-13 09:00","2020-11-13 18:00","연속"]
[589,"경북","직할","안동풍산 T/L","154kV 안동-풍산 등 2개T/L 지장선로 임시이설공사","○ 공사구간 : 154kV 안동-풍산T/L No.59~64 ○ 지지물 설치 3기, 철거 4기 ○ 전력선 HSTACIR/AW 240㎟ × S, ACSR 410㎟ × S, 0.971km","2020-11-15 07:00","2020-11-20 18:00","취소","취소","연속"]
[590,"경북","직할","현종산풍력평해#1 T/L","'20-21년 경북직할 가공송전 정비회사 총액공사","154kV 동상주-풍산 등 4개T/L 철탑보강공사 ○ 154kV 동상주-풍산 No.65, 동안동-임하HPT/L No.10, 울진-현종산풍력T/L No.79, 현종산풍력-평해T/L No.73 154kV 동상주-풍산 등 7개T/L 불량애자교체공사 ○ 154kV 동상주-풍산T/L 4기, 동안동-임하HPT/L 2기, 신영주-안동T/L 5기, 안동-동안동T/L 8기, 영덕-진보T/L 1기, 울진-현종산풍력T/L 8기, 현종산-평해T/L 7기","2020-11-04 09:00","2020-11-05 18:00","2020-11-10 09:00","2020-11-11 18:00","연속"]
[591,"경북","직할","현종산풍력평해#2 T/L","'20-21년 경북직할 가공송전 정비회사 총액공사","154kV 동상주-풍산 등 4개T/L 철탑보강공사 ○ 154kV 동상주-풍산 No.65, 동안동-임하HPT/L No.10, 울진-현종산풍력T/L No.79, 현종산풍력-평해T/L No.73","2020-11-03 09:00","2020-11-03 18:00","2020-11-09 09:00","2020-11-09 18:00","연속"]
[592,"부산울산","동부산","신양산구서#1 T/L","동부산전력지사 관내 OPGW 항공장애표시구 설치공사","154kV 신양산-수영#2T/L 안전이격확보용 휴전","2020-11-04 08:00","2020-11-04 18:00","취소","취소","연속"]
[593,"부산울산","동부산","신양산구서#2 T/L","동부산전력지사 관내 OPGW 항공장애표시구 설치공사","154kV 신양산-수영#1T/L 안전이격확보용 휴전","2020-11-03 08:00","2020-11-03 18:00","취소","취소","연속"]
[594,"부산울산","동부산","노포정관#2 T/L","노포S/S 154kV GIS 차단기 동작시험","1.노포S/S 154kV GIS 차단기 동작시험(노포-정관#2T/L) 2.정관S/S 154kV GIS 차단기 동작시험","2020-11-06 09:30","2020-11-06 17:00","2020-11-06 09:30","2020-11-06 17:00","연속"]
[595,"부산울산","동부산","노포정관#1 T/L","노포S/S 154kV GIS 차단기 동작시험","1.노포S/S 154kV GIS 차단기 동작시험(노포-정관#1T/L) 2.정관S/S 154kV GIS 차단기 동작시험","2020-11-05 09:30","2020-11-05 17:00","2020-11-05 09:30","2020-11-05 17:00","연속"]
[596,"부산울산","동부산","구서명장#1 T/L","명장S/S 송전선로보호반 성능개선","명장S/S 송전선로보호반 성능개선","2020-11-10 09:30","2020-11-10 17:00","2020-11-10 09:30","2020-11-10 17:00","연속"]
[597,"부산울산","동부산","수영정보#2 T/L","수영S/S 154kV GIS 차단기 동작시험","1.수영S/S 154kV GIS 차단기 동작시험(수영-정보#2T/L) 2.정보S/S 154kV GIS 차단기 동작시험","2020-11-22 09:30","2020-11-22 17:00","2020-11-22 09:30","2020-11-22 17:00","연속"]
[598,"부산울산","동부산","수영정보#1 T/L","수영S/S 154kV GIS 차단기 동작시험","1.수영S/S 154kV GIS 차단기 동작시험(수영-정보#1T/L) 2.정보S/S 154kV GIS 차단기 동작시험","2020-11-21 09:30","2020-11-21 17:00","2020-11-21 09:30","2020-11-21 17:00","연속"]
[599,"부산울산","동부산","수영우동 T/L","OF케이블 고정형 절연유 채취밸브 설치공사","OF케이블 고정형 절연유 채취밸브 설치 및 절연유 시료 채취","2020-11-17 09:00","2020-11-19 18:00","취소","취소","연속"]
[600,"부산울산","북부산","김해어방#2 T/L","20-21년 북부산전력지사 가공송전정비 총액공사","김해어방#2 김해S/S S/T, 1호(2기) 국산애자 교체공사","2020-11-24 09:00","2020-11-24 18:00","2020-11-24 09:00","2020-11-24 18:00","연속"]
[601,"부산울산","북부산","김해어방#1 T/L","20-21년 북부산전력지사 가공송전정비 총액공사","김해어방#1 김해S/S S/T, 1호(2기) 국산애자 교체공사","2020-11-24 09:00","2020-11-24 18:00","2020-11-24 09:00","2020-11-24 18:00","연속"]
[602,"부산울산","북부산","호포매리#2 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","○ #2T/L 임시선로 구성(4회선, 매리-김해#2 포함) ○ 가철탑 24-1, 1-1호 설치","2020-11-07 07:00","2020-11-08 18:00","2020-11-07 07:00","2020-11-08 18:00","연속"]
[603,"부산울산","북부산","매리김해#2 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","○ #2T/L 임시선로 구성(4회선, 호포-매리#2 포함) ○ 가철탑 24-1, 1-1호 설치","2020-11-07 07:00","2020-11-08 18:00","2020-11-07 07:00","2020-11-08 18:00","연속"]
[604,"부산울산","북부산","호포매리#1 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","○ #1T/L 임시선로 구성(4회선, 매리-김해#1 포함) ○ 가철탑 24-1, 1-1호 설치","2020-11-14 07:00","2020-11-15 18:00","2020-11-14 07:00","2020-11-15 18:00","연속"]
[605,"부산울산","북부산","매리김해#1 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","○ #1T/L 임시선로 구성(4회선, 호포-매리#1 포함) ○ 가철탑 24-1, 1-1호 설치","2020-11-14 07:00","2020-11-15 18:00","2020-11-14 07:00","2020-11-15 18:00","연속"]
[606,"부산울산","북부산","서창산막#2 T/L","20-21년 북부산전력지사 가공송전정비 총액공사","서창산막#2 2,53호(2기) 국산애자 교체공사","2020-11-29 09:00","2020-11-29 18:00","2020-11-28 09:00","2020-11-28 18:00","연속"]
[607,"부산울산","북부산","서창산막#1 T/L","20-21년 북부산전력지사 가공송전정비 총액공사","서창산막#1 2,53호(2기) 국산애자 교체공사","2020-11-28 09:00","2020-11-28 18:00","2020-11-28 09:00","2020-11-28 18:00","연속"]
[608,"부산울산","북부산","양산산막#2 T/L","20-21년 북부산전력지사 가공송전정비 총액공사","양산산막#2 4호(1기) 국산애자교체공사","2020-11-06 12:00","2020-11-06 18:00","2020-11-25 12:00","2020-11-25 18:00","연속"]
[609,"부산울산","북부산","양산산막#1 T/L","20-21년 북부산전력지사 가공송전정비 총액공사","양산산막#1 4호(1기) 국산애자교체공사","2020-11-06 09:00","2020-11-06 12:00","2020-11-25 09:00","2020-11-25 12:00","연속"]
[610,"부산울산","북부산","삼계어방#1 T/L","20-21년 북부산전력지사 가공송전정비 총액공사","삼계어방#1 9,13,17,18,19,20,23호(7기) 국산애자 교체공사","2020-11-16 09:00","2020-11-20 18:00","2020-11-16 09:00","2020-11-20 18:00","연속"]
[611,"부산울산","북부산","한림정삼계#2 T/L","20-21년 북부산전력지사 가공송전정비 총액공사","한림정삼계#2 17-29호(9기) 국산애자 교체공사","2020-11-16 09:00","2020-11-20 18:00","2020-11-16 09:00","2020-11-20 18:00","연속"]
[612,"부산울산","북부산","한림정삼계#1 T/L","20-21년 북부산전력지사 가공송전정비 총액공사","한림정삼계#1 17-29호(9기) 국산애자 교체공사","2020-11-10 09:00","2020-11-13 18:00","2020-11-10 09:00","2020-11-13 18:00","연속"]
[613,"부산울산","북부산","삼계어방#1 T/L","20-21년 북부산전력지사 가공송전정비회사 총액공사","삼계어방#2 26호 애자교체를 위한 안전이격휴전선로","2020-11-14 09:00","2020-11-14 18:00","2020-11-14 09:00","2020-11-14 18:00","연속"]
[614,"부산울산","북부산","삼계어방#2 T/L","20-21년 북부산전력지사 가공송전정비 총액공사","삼계어방#2 8,17,19.26호(4기) 국산애자 교체공사","2020-11-10 09:00","2020-11-14 18:00","2020-11-10 09:00","2020-11-14 18:00","연속"]
[615,"부산울산","북부산","어방S/S 154kV CB 6100","20-21 북부산전력지사 변전총액공사","어방S/S 154kV 모선보호반 대체공사 (6100 BUS-TIE 휴전)","2020-11-02 09:00","2020-11-06 18:00","2020-11-02 09:00","2020-11-06 18:00","연속"]
[616,"부산울산","울산","두왕영남TP#1 T/L","울산S/S 154kV SW 증설공사","○ 두왕-울산#1T/L 송전선로 인출변경(남부건설본부 송전건설부) ○ 두왕-울산#1T/L, 울산-영남T/P #1T/L 보호반 이설(설비보강부) ○ 두왕-울산#1T/L, 울산-영남T/P #1T/L 최초가압 및 실부하가압(설비보강부)","2020-11-15 07:00","2020-12-03 18:00","2020-11-15 07:00","2020-12-03 18:00","연속"]
[617,"부산울산","울산","방어진영남TP#2 T/L","154kV 방어진-영남TP#2T/L 전선교체 공사","154kV 방어진-영남TP#2T/L 태풍 마이삭 관련 소손개소 전선교체 - 구간 : No.1~5","2020-11-02 07:00","2020-11-04 18:00","2020-11-02 07:00","2020-11-04 18:00","연속"]
[618,"부산울산","울산","방어진영남TP#1 T/L","19-20년 지중송전 위탁정비공사","방어진, 영남화력 케이블헤드 및 피뢰기 점검","2020-11-10 10:00","2020-11-10 18:00","2020-11-10 10:00","2020-11-10 18:00","연속"]
[619,"부산울산","울산","신온산온산#3 T/L","20-21년 변전정비회사 총액공사","- 송전선로 보호반 대체","2020-11-03 09:00","2020-11-05 18:00","2020-11-03 09:00","2020-11-05 18:00","연속"]
[620,"부산울산","울산","신울산S/S 154kV SEC CB 61620","20~21년 변전협력 총액공사","- 차단기 동작시험","2020-11-10 09:00","2020-11-10 14:00","2020-11-10 09:00","2020-11-10 14:00","연속"]
[621,"부산울산","울산","신울산S/S 154kV #68 BUS","신울산S/S 154kV 덕하전철 신규수용공사","신규고객선로 GCB 2CB(6R7,6S7 신설분) 24시간 시험가압","2020-11-18 09:00","2020-11-19 18:00","2020-11-18 09:00","2020-11-19 18:00","연속"]
[622,"부산울산","울산","신울산S/S 154kV CB 6100","20~21년 변전협력 총액공사","- GIS 보통점검 및 전자변교체","2020-11-12 09:00","2020-11-12 18:00","2020-11-12 09:00","2020-11-12 18:00","연속"]
[623,"부산울산","울산","신울산S/S 154kV CB 6200","20~21년 변전협력 총액공사","- GIS 보통점검 및 전자변교체","2020-11-13 09:00","2020-11-13 18:00","2020-11-13 09:00","2020-11-13 18:00","연속"]
[624,"부산울산","울산","신울산S/S 154kV SEC CB 66670","20~21년 변전협력 총액공사","- 차단기 동작시험","2020-11-10 14:00","2020-11-10 18:00","2020-11-10 14:00","2020-11-10 18:00","연속"]
[625,"부산울산","울산","신울산언양#1 T/L","20~21년 변전협력 총액공사","- GIS 보통점검 및 전자변교체","2020-11-05 09:00","2020-11-05 18:00","2020-11-05 09:00","2020-11-05 18:00","연속"]
[626,"부산울산","울산","신울산언양#2 T/L","20~21년 변전협력 총액공사","- GIS 보통점검 및 전자변교체","2020-11-06 09:00","2020-11-06 18:00","2020-11-06 09:00","2020-11-06 18:00","연속"]
[627,"부산울산","울산","신울산명례#2 T/L","신울산S/S 154kV 덕하전철 신규수용공사","신규고객선로 GCB 2CB(6R7,6S7 신설분) 24시간 시험가압","2020-11-18 09:00","2020-11-19 18:00","2020-11-18 09:00","2020-11-19 18:00","연속"]
[628,"부산울산","울산","신온산온산#3 T/L","20년 하반기 울산전력지사 154kV 개폐장치 정밀점검 공사","온산S/S 무림P&P T/L 정밀점검 관련 시험가압1H","2020-11-13 17:00","2020-11-13 18:00","2020-11-13 17:00","2020-11-13 18:00","연속"]
[629,"부산울산","울산","용연울산TP#3 T/L","20년 하반기 울산전력지사 154kV 개폐장치 정밀점검 공사","용연S/S #4M.Tr 정밀점검 관련 시험가압1H","2020-11-16 17:00","2020-11-16 18:00","2020-11-16 17:00","2020-11-16 18:00","연속"]
[630,"부산울산","울산","울산울산TP#1 T/L","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","- 울산T/P 154kV SKC화학T/L GIS #2DS(682)부 철거 및 고깔 설치 후 시험가압선로","2020-11-02 15:00","2020-11-02 16:00","2020-11-02 15:00","2020-11-02 16:00","연속"]
[631,"부산울산","울산","울산울산TP#1 T/L","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","- 울산T/P 154kV SKC화학T/L GIS #60BUS 시험가압선로(모선만)","2020-11-06 14:00","2020-11-07 14:00","2020-11-06 14:00","2020-11-07 14:00","연속"]
[632,"부산울산","울산","울산T/P 154kV #65 BUS","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","- 울산T/P 154kV SKC화학T/L GIS #2DS(682)부 철거 및 고깔 설치","2020-11-02 07:00","2020-11-02 16:00","2020-11-02 07:00","2020-11-02 16:00","연속"]
[633,"부산울산","울산","울산T/P 154kV #65 BUS","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","- 울산T/P 154kV SKC화학T/L GIS #2DS, 상부BUS, 챔버 설치","2020-11-07 14:00","2020-11-13 18:00","2020-11-07 14:00","2020-11-13 18:00","연속"]
[634,"부산울산","울산","울산울산TP#1 T/L","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","- 울산T/P 154kV SKC화학T/L GIS #2DS, CB, #6DS 투입 후 시험가압선로","2020-11-12 17:00","2020-11-13 18:00","2020-11-12 17:00","2020-11-13 18:00","연속"]
[635,"부산울산","울산","울산울산TP#2 T/L","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","- 울산T/P 154kV SKC화학T/L 점퍼선 분리 후 울산-울산TP#2T/L과 임시선로 구성 후 자기선로로 시험가압","2020-11-03 07:00","2020-11-04 15:00","2020-11-03 07:00","2020-11-04 15:00","연속"]
[636,"부산울산","울산","울산T/P 154kV #60 BUS","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","- 울산T/P 154kV SKC화학T/L GIS #1BUS, #1DS, CB, 상부 철거 및 설치","2020-11-02 16:00","2020-11-07 14:00","2020-11-02 16:00","2020-11-07 14:00","연속"]
[637,"부산울산","울산","울산울산TP#2 T/L","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","- 울산T/P 154kV SKC화학T/L과 울산-울산TP#2T/L 임시선로 구성 원복 후 시험가압 후 실부하가압","2020-11-14 07:00","2020-11-14 18:00","2020-11-14 07:00","2020-11-14 18:00","연속"]
[638,"부산울산","울산","울산T/P 154kV #60 BUS","2020년 울산화력S/Y 154kV 장기사용 GIS 교체공사","- 울산T/P 154kV SKC화학T/L GIS #1DS(681) 투입 후 60BUS로 시험가압","2020-11-13 17:00","2020-11-13 18:00","2020-11-13 17:00","2020-11-13 18:00","연속"]
[639,"부산울산","울산","울산울산TP#1 T/L","울산S/S 154kV SW 증설공사","○ 울산-영남T/P #1T/L 전력케이블 포설 및 접속(남부건설본부 지중건설부) ○ 두왕-울산#1T/L, 울산-영남T/P #1T/L 보호반 이설(설비보강부) ○ 울산-울산T/P #1T/L 전력케이블 선종교체(설비보강부) ○ 두왕-울산#1T/L, 울산-영남T/P #1T/L 최초가압 및 실부하가압(설비보강부)","2020-11-15 07:00","2020-12-03 18:00","2020-11-15 07:00","2020-12-03 18:00","연속"]
[640,"부산울산","울산","울주외동#1 T/L","20년 하반기 울산전력지사 154kV 개폐장치 정밀점검 공사","GIS 정밀점검","2020-11-05 09:00","2020-11-06 18:00","2020-11-05 09:00","2020-11-06 18:00","연속"]
[641,"부산울산","울산","울주외동#2 T/L","20년 하반기 울산전력지사 154kV 개폐장치 정밀점검 공사","GIS 정밀점검","2020-11-03 09:00","2020-11-04 18:00","2020-11-03 09:00","2020-11-04 18:00","연속"]
[642,"부산울산","울산","웅촌서창#1 T/L","20-21년 변전정비회사 총액공사","- 송전선로 보호반 대체 -웅촌측 차단기 동작시험","2020-11-02 09:00","2020-11-04 18:00","2020-11-02 09:00","2020-11-04 18:00","연속"]
[643,"부산울산","울산","웅촌서창#2 T/L","20~21년 변전협력 총액공사","차단기 동작시험","2020-11-25 09:00","2020-11-25 18:00","2020-11-25 09:00","2020-11-25 18:00","연속"]
[644,"부산울산","울산","울주직동#1 T/L","20~21년 변전협력 총액공사","- 차단기 동작시험","2020-11-12 09:00","2020-11-12 14:00","2020-11-12 09:00","2020-11-12 14:00","연속"]
[645,"부산울산","울산","울주직동#2 T/L","20~21년 변전협력 총액공사","- 차단기 동작시험","2020-11-12 14:00","2020-11-12 18:00","2020-11-12 14:00","2020-11-12 18:00","연속"]
[646,"부산울산","울산","온산처용#2 T/L","처용S/S 23kV #2BANK 대체공사","처용S/S 23kV #2BANK 대체공사 관련 시험가압 1H","2020-11-25 17:00","2020-11-25 18:00","2020-11-25 17:00","2020-11-25 18:00","연속"]
[647,"부산울산","직할","정보대연 T/L","20-21년 직할 변전정비회사 총액공사","대연S/S 정보-대연T/L PNL 대체공사","2020-11-14 09:30","2020-11-16 18:00","취소","취소","연속"]
[648,"부산울산","직할","범일S/S 154kV CB 6100","20-21년 직할 변전정비회사 총액공사","범일S/S 6100 GIS 차단기 조작시험","2020-11-25 09:30","2020-11-25 18:00","2020-11-25 09:30","2020-11-25 18:00","연속"]
[649,"부산울산","직할","범일서면#1 T/L","OF케이블 고정형 절연유 채취밸브 설치공사","OF케이블 고정형 절연유 채취밸브 설치 및 절연유 시료 채취","2020-11-09 09:00","2020-11-11 09:00","2020-11-09 09:00","2020-11-11 09:00","연속"]
[650,"부산울산","직할","범일서면#2 T/L","OF케이블 고정형 절연유 채취밸브 설치공사","OF케이블 고정형 절연유 채취밸브 설치 및 절연유 시료 채취","2020-11-11 09:00","2020-11-13 09:00","2020-11-11 09:00","2020-11-13 09:00","연속"]
[651,"경남","직할","신월삼정#2 T/L","삼정S/S GIS화 154kV 신김해-삼정#1T/L 인출변경 및 시험가압","삼정S/S GIS화 154kV 신김해-삼정#1T/L 인출변경 및 OPGW 교체 시 하단선로 안전이격 및 시험가압","2020-11-18 08:00","2020-11-27 17:30","2020-11-18 08:00","2020-11-27 17:30","연속"]
[652,"경남","직할","삼정천선#2 T/L","삼정S/S GIS화 154kV 삼정-천선#2T/L 인출변경","삼정S/S GIS화 154kV 삼정-천선#2T/L 인출변경 (구)삼정변전소에서 (신)삼정SA변전소로","2020-11-18 08:00","2020-12-08 17:30","2020-11-18 08:00","2020-12-08 17:30","연속"]
[653,"경남","직할","신김해삼정#1 T/L","삼정S/S GIS화 154kV 신김해-삼정#1T/L 인출변경","삼정S/S GIS화 154kV 신김해-삼정#1T/L 인출변경 ((구)삼정S/S에서 (신)삼정SA변전)소 및 OPGW 교체작업","2020-11-18 08:00","2020-11-27 17:30","2020-11-18 08:00","2020-11-27 17:30","연속"]
[654,"경남","직할","신김해주촌#1 T/L","신김해S/S 154kV 장기사용GIS 교체공사(3차) 안전이격 휴전","신김해S/S 154kV 장기사용GIS 교체공사(3차) 안전이격 휴전 - 대상 : 신김해-장유#2T/L, #2BUS TIE, #2BUS PT, ES","2020-11-02 08:00","2020-11-06 18:00","2020-11-06 08:00","2020-11-13 18:00","매일"]
[655,"경남","직할","신김해주촌#1 T/L","신김해S/S 154kV 장기사용GIS 교체공사(3차) 안전이격 휴전","신김해S/S 154kV 장기사용GIS 교체공사(3차) 안전이격 휴전 - 대상 : 신김해-장유#2T/L, #2BUS TIE, #2BUS PT, ES","2020-11-09 08:00","2020-11-13 18:00","2020-11-15 08:00","2020-11-19 18:00","매일"]
[656,"경남","직할","신김해장유#1 T/L","신김해S/S 154kV 장기사용GIS 교체공사(4차)","신김해S/S 154kV 장기사용GIS 교체공사(4차) - 대상 : 신김해-장유#1T/L, #2M.Tr 2차 GIS","2020-11-18 08:00","2020-12-08 18:00","2020-11-24 08:00","2020-12-14 18:00","연속"]
[657,"경남","직할","신김해지사#2 T/L","신김해S/S 154kV 장기사용GIS 교체공사(4차) 시험가압","신김해S/S 154kV 장기사용GIS 교체공사(4차) 시험가압 - 대상 : 신김해-장유#1T/L, #2M.Tr 2차 GIS","2020-11-21 12:00","2020-11-21 18:00","2020-11-26 12:00","2020-11-26 18:00","연속"]
[658,"경남","직할","신김해지사#2 T/L","신김해S/S 154kV 장기사용GIS 교체공사(4차) 안전이격,시험가압","신김해S/S 154kV 장기사용GIS 교체공사(4차) 안전이격,시험가압 - 대상 : 신김해-장유#1T/L, #2M.Tr 2차 GIS","2020-11-23 08:00","2020-11-29 18:00","2020-11-27 08:00","2020-12-05 18:00","연속"]
[659,"경남","진주","사천개양#2 T/L","154kV 사천-개양T/L No.30∼35 안전이격거리 확보공사","사천-개양T/L No. 30∼35(전선교체 구간: No. 29∼35호)","2020-11-22 09:00","2020-11-24 18:00","2020-11-22 09:00","2020-11-24 18:00","연속"]
[660,"경남","진주","사천개양#1 T/L","154kV 사천-개양T/L No.30∼35 안전이격거리 확보공사","사천-개양T/L No. 30∼35(전선교체 구간: No. 29∼35호)","2020-11-15 09:00","2020-11-21 18:00","2020-11-15 09:00","2020-11-21 18:00","연속"]
[661,"경남","진주","의령함양 T/L","함양S/S 옥외철구 현대화 공사","함양S/S 옥외철구 현대화 - (신)함양으로 이설 1. 의령-함양T/L EBA 연결 2. 보호계전기 이설","2020-11-21 08:00","2020-11-22 19:00","2020-11-21 08:00","2020-11-22 19:00","연속"]
[662,"경남","진주","함양거창#2 T/L","함양S/S 옥외철구 현대화 공사","함양S/S 옥외철구 현대화 - (신)함양으로 이설 1. 함양-거창#2T/L C/H 연결 2. 함양-거창#2T/L 거창측 보호배전반 교체","2020-11-21 07:30","2020-11-24 19:00","2020-11-21 07:30","2020-11-24 19:00","연속"]
[663,"경남","통영","고성통영 T/L","154kV 고성-통영T/L 추락방지시설 설치","154kV 고성-통영T/L 추락방지시설 설치(146, 149호)","2020-11-22 08:00","2020-11-22 18:00","2020-11-22 08:00","2020-11-22 18:00","연속"]
[664,"경남","통영","신고성삼천포#1 T/L","삼천포S/S 170kV GIS 대체공사 3차공정 시험가압","삼천포S/S 170kV GIS 대체공사 3차공정 #1BUS 시험가압 -#2M.Tr 1차 GIS, 삼천포-사천#2T/L GIS 대체","2020-11-04 13:00","2020-11-05 09:00","2020-11-04 13:00","2020-11-05 09:00","연속"]
[665,"경남","통영","신고성삼천포#2 T/L","삼천포S/S 170kV GIS 대체공사 3차공정 시험가압","삼천포S/S 170kV GIS 대체공사 3차공정 #2BUS 시험가압 -#2M.Tr 1차 GIS, 삼천포-사천#2T/L GIS 대체","2020-11-13 13:00","2020-11-14 13:00","2020-11-13 13:00","2020-11-14 13:00","연속"]
[666,"경남","통영","삼천포S/S 154kV #2 BUS","삼천포S/S 170kV GIS 대체공사 3차공정","삼천포S/S 170kV GIS 대체공사 3차공정 - #2M.Tr 1차 GIS, 삼천포-사천#2T/L GIS 대체공사","2020-11-05 09:00","2020-11-14 18:00","2020-11-05 09:00","2020-11-14 18:00","연속"]
[667,"경남","통영","신고성통영 T/L","154kV 신고성-통영T/L 추락방지시설 설치","154kV 신고성-통영T/L 추락방지시설 설치(146, 149호)","2020-11-21 08:00","2020-11-21 18:00","2020-11-21 08:00","2020-11-21 18:00","연속"]
[668,"경남","통영","신고성거제#1 T/L","154kV 신고성-거제#1T/L 추락방지시설 설치","154kV 신고성-거제#1T/L 추락방지시설 설치(145호)","2020-11-14 08:00","2020-11-15 18:00","2020-11-14 08:00","2020-11-15 18:00","매일"]
[669,"경남","통영","신고성고성 T/L","154kV 신고성-고성T/L 보통점검 등 2건","1. 154kV 신고성-고성T/L 보통점검 및 전자변 교체 2. 154kV 신고성-고성T/L CVT, LA 보통점검","2020-11-07 10:00","2020-11-07 18:00","2020-11-07 10:00","2020-11-07 18:00","연속"]
[670,"경남","함안","가야사봉#2 T/L","가야S/S 154kV 가야-사봉#2T/L GIS 정밀점검","가야S/S 154kV 가야-사봉#2T/L GIS 정밀점검","2020-11-07 09:00","2020-11-08 18:00","2020-11-07 09:00","2020-11-08 18:00","연속"]
[671,"경남","함안","신마산S/S 154kV CB 6200","신마산S/S 154kV #61-#66 BUS TIE CB 조작시험","신마산S/S 154kV #61-#66 BUS TIE CB 조작시험","2020-11-26 09:00","2020-11-26 13:00","2020-11-26 09:00","2020-11-26 13:00","연속"]
[672,"경남","함안","신마산칠서#1 T/L","154kV 신마산-칠서T/L 지장송전선로 이설공사(요청자시행)","- 40~45호 구간 이설(기설-&gt신설)","2020-11-04 09:00","2020-11-10 17:00","2020-11-12 09:00","2020-11-18 17:00","연속"]
[673,"경남","함안","신마산칠서#2 T/L","154kV 신마산-칠서T/L 지장송전선로 이설공사(요청자시행)","- 40~45호 구간 이설(기설-&gt신설)","2020-11-18 09:00","2020-11-23 18:00","2020-11-21 09:00","2020-11-27 18:00","연속"]
[674,"경남","함안","신마산S/S 154kV CB 6100","신마산S/S 154kV #60-#65 BUS TIE CB 조작시험","신마산S/S 154kV #60-#65 BUS TIE CB 조작시험","2020-11-25 09:00","2020-11-25 13:00","2020-11-25 09:00","2020-11-25 13:00","연속"]
[675,"경남","함안","중리가야#1 T/L","154kV 중리-가야T/L 20,21,38호 안전이격확보공사","철탑교체(3기) 및 전력선 교체(19~23, 37~39호간)","2020-11-25 07:00","2020-11-29 18:00","2020-11-25 07:00","2020-11-29 18:00","연속"]
[676,"경남","함안","중리가야#2 T/L","154kV 중리-가야T/L 20,21,38호 안전이격확보공사","철탑교체(3기) 및 전력선교체(19~23,37~39호간)","2020-11-30 07:00","2020-12-02 18:00","2020-11-30 07:00","2020-12-02 18:00","연속"]
[677,"경남","함안","진영한림정#1 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 345k신김해-북부산T/L 95-96호 횡단구간 안전확보","2020-11-07 07:00","2020-11-08 18:00","2020-11-21 07:00","2020-11-22 18:00","연속"]
[678,"경남","함안","진영한림정#2 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 345k신김해-북부산T/L 95-96호 횡단구간 안전확보","2020-11-14 07:00","2020-11-15 18:00","2020-11-28 07:00","2020-11-29 18:00","연속"]
[679,"경남","함안","진영한림정#1 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 345k신김해-북부산T/L 95-96호 횡단구간 안전확보","2020-11-14 07:00","2020-11-15 18:00","2020-11-28 07:00","2020-11-29 18:00","연속"]
[680,"경남","함안","진영한림정#2 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 345k신김해-북부산T/L 95-96호 횡단구간 안전확보","2020-11-07 07:00","2020-11-08 18:00","2020-11-21 07:00","2020-11-22 18:00","연속"]
[681,"경남","함안","창녕구지#2 T/L","창녕S/S 154kV 창녕-구지#2T/L CB 전자변 교체 외","창녕S/S 154kV 창녕-구지#2T/L CB 전자변 교체 외","2020-11-21 09:00","2020-11-21 18:00","2020-11-21 09:00","2020-11-21 18:00","연속"]
[682,"경남","함안","신마산칠서#1 T/L","칠서S/S 154kV 장기사용 GIS 대체공사","칠서S/S 154kV 장기사용 GIS 대체공사","2020-11-11 17:00","2020-11-12 17:00","2020-11-11 09:00","2020-11-12 09:00","연속"]
[683,"경남","함안","칠서창녕#1 T/L","칠서S/S 154kV 장기사용 GIS 대체공사","칠서S/S 154kV 장기사용 GIS 대체공사","2020-11-16 09:00","2020-12-03 17:00","2020-11-19 09:00","2020-12-07 17:00","연속"]
[684,"경남","함안","신마산칠서#2 T/L","칠서S/S 154kV 장기사용 GIS 대체공사","칠서S/S 154kV 장기사용 GIS 대체공사","2020-11-17 18:00","2020-11-18 09:00","2020-11-20 18:00","2020-11-21 09:00","연속"]
[685,"경남","함안","신마산칠서#1 T/L","칠서S/S 154kV 장기사용 GIS 대체공사","칠서S/S 154kV 장기사용 GIS 대체공사","2020-11-23 18:00","2020-11-25 09:00","2020-11-27 18:00","2020-11-29 09:00","연속"]
[686,"경남","함안","신마산칠서#2 T/L","칠서S/S 154kV 장기사용 GIS 대체공사","칠서S/S 154kV 장기사용 GIS 대체공사","2020-11-10 17:00","2020-11-11 17:00","2020-11-10 09:00","2020-11-11 09:00","연속"]
[687,"경남","함안","신마산칠서#1 T/L","칠서S/S 154kV 장기사용 GIS 대체공사","칠서S/S 154kV 장기사용 GIS 대체공사","2020-11-02 18:00","2020-11-04 09:00","2020-11-02 18:00","2020-11-04 09:00","연속"]
[688,"인천","부평","신가좌S/S 154kV #61 BUS","신가좌S/S 362kV 용량부족 GIS 교체공사","-신가좌S/S 362kV 용량부족 GIS 교체공사 -실부하가압 관련 앵글 측정","2020-11-25 16:00","2020-11-25 18:00","2020-11-25 16:00","2020-11-25 18:00","연속"]