{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":9,"n_cols":11,"rows_kept":9,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2020년도 12월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"강원","태백","신태백신가평#1 T/L","신한울 1호기 상업운전 관련 SPS 설치","신한울 1호기 상업운전 관련 SPS 설치","2020-12-28 09:00","2020-12-28 18:00","취소","취소","연속"]
[2,"강원","태백","신태백신가평#2 T/L","신한울 1호기 상업운전 관련 SPS 설치","신한울 1호기 상업운전 관련 SPS 설치","2020-12-29 09:00","2020-12-29 18:00","취소","취소","연속"]
[3,"경북","영주","신태백신한울#1 T/L","신한울 1호기 상업운전 관련 SPS 설치","신한울 1호기 상업운전 관련 SPS 설치","2020-12-21 09:00","2020-12-22 18:00","취소","취소","연속"]
[4,"경북","영주","신태백신한울#2 T/L","신한울 1호기 상업운전 관련 SPS 설치","신한울 1호기 상업운전 관련 SPS 설치","2020-12-28 09:00","2020-12-29 18:00","취소","취소","연속"]
[5,"경남","함안","북경남S/S #5 M.Tr","북경남S/S 765kV #5 M.Tr 2차 GIB 접지본드 과열 해소","북경남S/S 765kV #5 M.Tr 2차 GIB 접지본드 과열 해소","2020-12-10 09:00","2020-12-10 18:00","2020-12-10 09:00","2020-12-10 18:00","연속"]

{"sheet":"345송부","index":1,"n_rows":155,"n_cols":11,"rows_kept":155,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2020년도 12월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #1 M.Tr","2020년 성동P/O 345kV M.Tr 및 OLTC 정밀점검공사","2020년 성동P/O 345kV M.Tr 및 OLTC 정밀점검공사","2020-12-04 09:30","2020-12-14 18:00","취소","취소","연속"]
[2,"서울","성동","성동S/S #2 M.Tr","2020년 성동PO 변전정비회사 총액공사","주변압기 2차 154kV GIS 조작시험","2020-12-02 10:00","2020-12-02 17:00","취소","취소","연속"]
[3,"서울","중부","중부S/S #2 M.Tr","`20 중부S/S 345kV M.Tr 정밀점검공사","345kV M.Tr 정밀점검","2020-12-16 10:00","2020-12-24 18:00","취소","취소","연속"]
[4,"서울","중부","중부S/S #1 M.Tr","`20 중부PO 변전정비회사 총액공사","#1M.Tr 초기점검","2020-12-29 10:00","2020-12-31 18:00","취소","취소","연속"]
[5,"서울","중부","중부S/S 345kV #1 Sh.R","`20 중부PO 변전정비회사 총액공사","#1Sh.R 누기보수","2020-12-29 10:00","2020-12-31 18:00","취소","취소","연속"]
[6,"서울","중부","양주중부#1 T/L","`20 중부PO 변전정비회사 총액공사","PT보통점검, 전자변 교체","2020-12-27 10:00","2020-12-27 18:00","취소","취소","연속"]
[7,"서울","중부","양주중부#2 T/L","`20 중부PO 변전정비회사 총액공사","PT보통점검, 전자변 교체","2020-12-28 10:00","2020-12-28 18:00","취소","취소","연속"]
[8,"서울","중부","중부S/S #3 M.Tr","`20 중부S/S 345kV M.Tr 정밀점검공사","345kV M.Tr 정밀점검","2020-12-06 10:00","2020-12-15 18:00","취소","취소","연속"]
[9,"남서울","강남","신양재S/S 345kV #3 Sh.R","신양재S/S 362kV GIS Control block 교체","신양재S/S 362kV GIS Control block 교체","2020-12-07 09:00","2020-12-17 18:00","2020-12-14 09:00","2020-12-14 18:00","연속"]
[10,"남서울","강남","신양재S/S 345kV #4 Sh.R","신양재S/S 362kV GIS 정밀점검","신양재S/S 362kV GIS 정밀점검","2020-12-18 09:00","2020-12-31 18:00","취소","취소","연속"]
[11,"남서울","영등포","신광명영등포#2 T/L","신광명S/S 362kV GIS 보통점검(신광명-영등포#1,2)","- 차단기 개폐타임 측정 - GIS 조작시험 - SF5가스 수분 및 SO2 측정 - 차단기 메커니즘 점검","2020-12-05 14:00","2020-12-05 18:00","취소","취소","연속"]
[12,"남서울","영등포","신광명영등포#1 T/L","신광명S/S 345kV GIS 보통점검(신광명-영등포#1,2)","- 차단기 개폐타임 측정 - GIS 조작시험 - SF6가스 수분 및 SO2 측정 - 메커니즘 점검","2020-12-05 09:00","2020-12-05 14:00","취소","취소","연속"]
[13,"남서울","영등포","신광명S/S #4 M.Tr","신광명S/S #4 M.Tr 3차측 절연보강 공사","- #4M.Tr 3차측 절연 보강","2020-12-10 09:00","2020-12-11 18:00","취소","취소","연속"]
[14,"남서울","강남","신성남신양재 #1 T/L ","345kV 신성남-신양재T/L 피뢰기 열화진단 ","345kV 신성남-신양재T/L 피뢰기 열화진단 ","2020-12-01 09:00","2020-12-01 18:00","2020-12-01 09:00","2020-12-01 18:00","연속"]
[15,"남서울","강남","신성남신양재 #2 T/L ","345kV 신성남-신양재T/L 피뢰기 열화진단 ","345kV 신성남-신양재T/L 피뢰기 열화진단 ","2020-12-02 09:00","2020-12-02 18:00","2020-12-02 09:00","2020-12-02 18:00","연속"]
[16,"남서울","영등포","신광명S/S #1 M.Tr","신광명S/S 345kV 주변압기 부싱점검 ","신광명S/S #1M.Tr 345kV 주변압기 부싱점검 ","2020-12-07 09:00","2020-12-09 18:00","2020-11-26 09:00","2020-11-30 18:00","연속"]
[17,"남서울","동서울","동서울S/S 345kV #76 BUS ","  동서울S/S 345kV 노후 주변압기 교체공사 ","  ○ 345kV M.Tr 100/166.7MVA * 7대 교체\n○ 기타 부대공사 1식 ","2020-12-21 13:00","2020-12-22 13:00","2020-12-21 13:00","2020-12-22 13:00","연속"]
[18,"남서울","동서울","신성남동서울#2 T/L ","  동서울S/S 345kV 노후 주변압기 교체공사 ","  ○ 345kV M.Tr 100/166.7MVA * 7대 교체\n○ 기타 부대공사 1식 ","2020-12-21 13:00","2020-12-22 13:00","2020-12-21 13:00","2020-12-22 13:00","연속"]
[19,"인천","부평","신가좌신시흥#2 T/L","신가좌S/S 신가좌신시흥#2 T/L PT 보통점검","신가좌S/S 신가좌신시흥#2 T/L PT 보통점검","2020-12-01 09:00","2020-12-01 18:00","취소","취소","연속"]
[20,"인천","부평","신경서S/S 345kV #1 Sh.R","신경서S/S 7179 GIS 하자점검","신경서S/S 7179 GIS 하자점검","2020-12-02 09:00","2020-12-02 18:00","2020-12-02 09:00","2020-12-02 18:00","연속"]
[21,"인천","부평","신가좌가정#2 T/L","345kV신가좌-가정#2T/L 정밀점검","345kV신가좌-가정#2T/L 가공 송전선로 정밀점검","2020-12-03 09:30","2020-12-04 18:00","취소","취소","연속"]
[22,"인천","부평","신인천C/C 345kV CB 7572","서인천복합S/Y 7572 GIS 보통점검 공사","서인천복합S/Y 7572 GIS 보통점검 공사","2020-12-04 09:00","2020-12-04 18:00","2020-12-04 09:00","2020-12-04 18:00","연속"]
[23,"인천","부평","신가좌S/S 154kV #66 BUS","신가좌S/S 6200 GIS 정밀점검 관련 무부하 가압용","신가좌S/S 6200 GIS 정밀점검 관련 무부하 가압용","2020-12-05 09:00","2020-12-05 18:00","취소","취소","연속"]
[24,"인천","부평","신가좌S/S #1 M.Tr","신가좌S/S #1,4M.Tr 345㎸ CVT 설치 관련 기초공사","신가좌S/S #1,4M.Tr 345㎸ CVT 설치 관련 기초공사","2020-12-07 09:00","2020-12-07 18:00","2020-12-07 09:00","2020-12-07 18:00","연속"]
[25,"인천","부평","신가좌S/S #4 M.Tr","신가좌S/S #1,4M.Tr 345㎸ CVT 설치 관련 기초공사","신가좌S/S #1,4M.Tr 345㎸ CVT 설치 관련 기초공사","2020-12-08 09:00","2020-12-08 18:00","2020-12-08 09:00","2020-12-08 18:00","연속"]
[26,"인천","직할","가정갈산#2 T/L","345kV 갈산S/S Sh.R 증설","Sh.R 초기가압","2020-12-30 10:00","2020-12-31 13:00","2020-12-30 10:00","2020-12-31 13:00","연속"]
[27,"인천","직할","갈산S/S 345kV #70 BUS","345kV 갈산S/S Sh.R 증설공사","345kV 3CB 증설","2020-12-30 10:00","2020-12-30 13:00","2020-12-30 10:00","2020-12-30 13:00","연속"]
[28,"인천","직할","갈산S/S 345kV #75 BUS","345kV 갈산S/S Sh.R 증설공사","345kV 3CB 증설","2020-12-30 13:00","2020-12-31 13:00","2020-12-30 13:00","2020-12-31 13:00","연속"]
[29,"경기북부","고양","신파주S/S 345kV CB 7771","362kV GIS 조작시험","7771,7700 GIS 조작시험 및 SF6 측정","2020-12-08 09:00","2020-12-08 13:00","2020-12-08 09:00","2020-12-08 13:00","연속"]
[30,"경기북부","고양","신파주S/S 345kV CB 7700","362kV GIS 조작시험","7771,7700 GIS 조작시험 및 SF6 측정","2020-12-08 13:00","2020-12-08 18:00","2020-12-08 13:00","2020-12-08 18:00","연속"]
[31,"경기북부","구리","미금S/S 345kV CB 7772","`20~21 구리전력 변전정비 총액공사","미금S/S 345kV 7772 차단기 개폐타임 측정","2020-12-07 09:00","2020-12-07 14:00","2020-12-07 09:00","2020-12-07 14:00","연속"]
[32,"경기북부","구리","미금S/S 345kV CB 7700","`20~21 구리전력 변전정비 총액공사","미금S/S 345kV 7700 차단기 개폐타임 측정","2020-12-07 14:00","2020-12-07 18:00","2020-12-07 14:00","2020-12-07 18:00","연속"]
[33,"경기북부","구리","미금S/S 345kV CB 7079","`20~21 구리전력 변전정비 총액공사","미금S/S #1 BUS Sh.R Main 차단기 개폐타임측정","2020-12-01 09:00","2020-12-01 18:00","취소","취소","연속"]
[34,"경기북부","구리","미금S/S 345kV #5 Sh.R","미금S/S 감시제어설비 교체공사","#5Sh.R 관련 감시제어케이블 교체 및 조작,경보 시험","2020-12-21 09:00","2020-12-22 18:00","취소","취소","연속"]
[35,"경기북부","구리","미금S/S 345kV #2 Sh.R","미금S/S 감시제어설비 교체공사","#2Sh.R 관련 감시제어케이블 교체 및 조작,경보 시험","2020-12-16 09:00","2020-12-17 18:00","취소","취소","연속"]
[36,"경기북부","구리","미금S/S 345kV #1 Sh.R","미금S/S 감시제어설비 교체공사","#1Sh.R 관련 감시제어케이블 교체 및 조작,경보 시험","2020-12-14 09:00","2020-12-15 18:00","취소","취소","연속"]
[37,"경기북부","구리","미금S/S 345kV CB 7200","`20~21 구리전력 변전정비 총액공사","미금S/S 345kV 7200 차단기 개폐타임 측정","2020-12-08 14:00","2020-12-08 18:00","2020-12-08 14:00","2020-12-08 18:00","연속"]
[38,"경기북부","구리","미금S/S 345kV CB 7271","`20~21 구리전력 변전정비 총액공사","미금S/S 345kV 7271 차단기 개폐타임 측정","2020-12-08 09:00","2020-12-08 14:00","2020-12-08 09:00","2020-12-08 14:00","연속"]
[39,"경기북부","구리","신가평S/S 345kV #2 Sh.R","구리전력지사 7379CB 하자점검","구리전력지사 7379CB 하자점검","2020-12-01 09:00","2020-12-01 18:00","2020-12-01 09:00","2020-12-01 18:00","연속"]
[40,"경기북부","직할","양주S/S SVC CB","양주변전소 옥외철구 GIS화 공사","감시제어 시스템 이설(모자이크→SA)","2020-12-07 09:00","2020-12-13 18:00","2020-12-07 09:00","2020-12-13 18:00","연속"]
[41,"경기북부","직할","양주S/S #1 M.Tr","양주S/S 154kV 인출T/L 지중화공사","상시험 및 무부하가압용","2020-12-07 09:00","2020-12-08 18:00","2020-12-07 09:00","2020-12-08 18:00","연속"]
[42,"경기","군포","서서울#2S/S #6 M.Tr","서서울#2S/S #6 M.Tr 1차측 CVT설치","서서울#2S/S #6 M.Tr 1차측 CVT설치","2020-12-07 09:00","2020-12-10 18:00","취소","취소","연속"]
[43,"경기","군포","서서울#2S/S #5 M.Tr","서서울#2S/S #5 M.Tr 1차측 CVT설치","서서울#2S/S #5 M.Tr 1차측 CVT설치","2020-12-01 09:00","2020-12-04 18:00","취소","취소","연속"]
[44,"경기","군포","신온양서서울#1 T/L","154kV 화성-발안T/L OPGW 증설공사(96C_시범사업)","* 화성S/T ~ No.10(10)간 OP-S-L48→96 교체 2.467km * No.10(10) ~ CH.18간 OP-S-L24→48 교체 2.125km * 화성S/S ICT실 ~ 화성S/T FOFC 교체(48→96C) 0.390km * 발안S/S ICT실 ~ CH.18 FOFC 증설(24→48C) 3.193km * 접속, 최종시험 및 기타 부","2020-12-07 07:00","2020-12-08 18:00","취소","취소","매일"]
[45,"경기","군포","신시흥신안산#1 T/L","'20년 OPGW 금구류 및 항공장애표시구 정비공사","345kV 신시흥-신안산#1T/L No.65-72 항공구 정비","2020-12-07 09:00","2020-12-07 18:00","2020-12-07 09:00","2020-12-07 18:00","연속"]
[46,"경기","동부","곤지암신충주#1 T/L","2020~2021년 성남전력지사 송전정비회사 총액공사","- 345kV 곤지암-신충주#1T/L 압축인류크램프 보수","2020-12-01 08:00","2020-12-01 18:00","취소","취소","연속"]
[47,"경기","동부","곤지암S/S 345kV #1 Sh.R","20년 동부변전정비회사 총액공사","곤지암:#1Sh.R GIS(조작), 7179(A,B,C)GIS전자변교체,전자변실리콘히터 설치(A,B,C) 43L/R 회로보완 확인 및 Remote 회로분리 시행","2020-12-02 09:00","2020-12-02 18:00","2020-12-02 09:00","2020-12-02 18:00","연속"]
[48,"경기","성남","신수원삼성#2 T/L","20년 성남전력 변전정비회사 총액공사","보통점검, 유호제계전기성능개선","2020-12-04 09:00","2020-12-04 18:00","2020-12-04 09:00","2020-12-04 18:00","연속"]
[49,"경기","성남","신안성신성남#1 T/L","345kV 신용인-동서울T/L 지장철탑 이설공사(이천오산)","345kV 신용인-동서울T/L 7-1호 지장철탑 이설(요청자 시행 공사) - 교체구간 : 0.7km, 4회선 1기 본선로, 1기 임시선로 - 345kV 신안성-신성남T/L 64-1호 병가구간","2020-12-09 09:00","2020-12-22 18:00","취소","취소","연속"]
[50,"경기","성남","신용인동서울#1 T/L","345kV 신용인-동서울T/L 지장철탑 이설공사(이천오산)","345kV 신용인-동서울T/L 7-1호 지장철탑 이설(요청자 시행 공사) - 교체구간 : 0.7km, 4회선 1기 본선로, 1기 임시선로 - 345kV 신안성-신성남T/L 64-1호 병가구간","2020-12-09 09:00","2020-12-22 18:00","취소","취소","연속"]
[51,"경기","성남","신용인삼성 T/L","20년 성남전력 변전정비회사 총액공사","보호계전기 성능개선(유호) LA초기점검","2020-12-02 09:00","2020-12-02 18:00","2020-12-02 09:00","2020-12-02 18:00","연속"]
[52,"경기","직할","화성S/S #4 M.Tr","20년 직할 변전정비회사 총액공사","화성 : #4M.Tr 1차, 2차 GIS 조작, 1, 2차 부싱절연유 채유(A,B,C상)","2020-12-01 09:00","2020-12-01 18:00","2020-12-01 09:00","2020-12-01 18:00","연속"]
[53,"강원","동해","동해삼척GP#2 T/L","동해S/S 362kV GIS DS 투입불량 보수 작업","동해S/S 362kV GIS DS 투입불량 보수 작업","2020-12-01 09:00","2020-12-02 18:00","2020-12-01 09:00","2020-12-02 18:00","매일"]
[54,"강원","강릉","신양양S/S #2 M.Tr","신양양S/S 장기미동작 차단기 동작시험","신양양S/S 장기미동작 차단기 동작시험 #2M.Tr 1차, #2M.Tr 1차-TIE,#2M.Tr 2차 CB","2020-12-01 10:00","2020-12-01 18:00","2020-12-01 10:00","2020-12-01 18:00","연속"]
[55,"강원","강릉","신양양S/S #1 M.Tr","신양양S/S 장기미동작 차단기 동작시험","신양양S/S 장기미동작 차단기 동작시험 #1M.Tr 1차, 신양양-양양PP T/L - #1M.Tr 1차 TIE,#1M.Tr 2차, #1M.Tr 3차 CB","2020-12-02 10:00","2020-12-02 18:00","2020-12-02 10:00","2020-12-02 18:00","연속"]
[56,"강원","동해","동해삼척GP#1 T/L","동해S/S 362kV GIS DS 투입불량 보수 작업","동해S/S 362kV GIS DS 투입불량 보수 작업","2020-12-03 09:00","2020-12-04 18:00","2020-12-03 09:00","2020-12-04 18:00","매일"]
[57,"강원","동해","동해S/S #3 M.Tr","동해S/S 362kV GIS DS 투입불량 보수 작업","동해S/S 362kV GIS DS 투입불량 보수 작업","2020-12-05 09:00","2020-12-06 18:00","2020-12-05 09:00","2020-12-06 18:00","매일"]
[58,"강원","동해","동해북평TP#3 T/L","동해S/S 362kV GIS DS 투입불량 보수 작업","동해S/S 362kV GIS DS 투입불량 보수 작업","2020-12-07 09:00","2020-12-08 18:00","2020-12-07 09:00","2020-12-08 18:00","연속"]
[59,"강원","동해","동해S/S 345kV CB 7171","동해S/S 362kV GIS DS 투입불량 보수 작업","동해S/S 362kV GIS DS 투입불량 보수 작업","2020-12-11 09:00","2020-12-11 18:00","2020-12-11 09:00","2020-12-11 18:00","연속"]
[60,"강원","동해","동해S/S 345kV CB 7471","동해S/S 362kV GIS DS 투입불량 보수 작업","동해S/S 362kV GIS DS 투입불량 보수 작업","2020-12-14 09:00","2020-12-14 18:00","2020-12-14 09:00","2020-12-14 18:00","연속"]
[61,"강원","동해","동해S/S 345kV CB 7400","동해S/S 362kV GIS DS 투입불량 보수 작업","동해S/S 362kV GIS DS 투입불량 보수 작업","2020-12-15 09:00","2020-12-15 18:00","2020-12-15 09:00","2020-12-15 18:00","연속"]
[62,"강원","강릉","양양P/P 345kV CB 7200","2020년 345kV GIS 보통점검","○ 2020년 345kV GIS 보통점검 ○ 7200CB 컨트롤블록 교체","2020-12-21 10:00","2020-12-23 18:00","취소","취소","연속"]
[63,"강원","강릉","양양P/P 345kV CB 7272","2020년 345kV GIS 보통점검","○ 2020년 345kV GIS 보통점검 ○ 7272CB 컨트롤블록 교체","2020-12-21 10:00","2020-12-23 18:00","취소","취소","연속"]
[64,"충북","직할","신진천S/S #2 M.Tr","20~21년도 직할 변전정비회사 총액공사","신진천S/S 345kV #2M.Tr 1,2차 LA 하자점검, 1차 CVT 설치, 부싱 절연유 채유, 옥외등기구 교체","2020-12-12 10:00","2020-12-12 18:00","2020-12-12 10:00","2020-12-12 18:00","연속"]
[65,"충북","직할","서안성신진천#1 T/L","2020년 직할 가공송전선로 순시점검 위탁공사","현수애자 절연저항측정 (중각도 철탑 3기)","2020-12-03 09:00","2020-12-04 18:00","취소","취소","매일"]
[66,"충북","직할","신진천S/S #1 M.Tr","20~21년도 직할 변전정비회사 총액공사","신진천S/S 345kV #2M.Tr 1차 CVT 설치, 부싱 절연유 채유, 옥외등기구 교체","2020-12-13 10:00","2020-12-13 18:00","2020-12-13 10:00","2020-12-13 18:00","연속"]
[67,"충북","직할","신진천S/S #4 M.Tr","20~21년도 직할 변전정비회사 총액공사","신진천S/S 345kV #4M.Tr 보통점검, 부싱 절연유 채유, 1차 CVT 설치, 옥외등기구 교체","2020-12-05 10:00","2020-12-06 18:00","2020-12-05 10:00","2020-12-06 18:00","연속"]
[68,"충북","청주","남청주S/S 345kV CB 7100","20-21년 청주전력 변전정비 총액","6년 이상 사용 노후 전자변 교체","2020-12-02 09:00","2020-12-02 18:00","2020-12-08 09:00","2020-12-08 18:00","연속"]
[69,"충북","청주","남청주S/S 345kV CB 7171","20-21년 청주전력 변전정비 총액","6년 이상 사용 노후 전자변 교체","2020-12-01 09:00","2020-12-01 18:00","2020-12-07 09:00","2020-12-07 18:00","연속"]
[70,"충북","청주","신중부남청주#2 T/L","345kV 신중부-남청주T/L No.60,61 안전이격확보공사","철탑 2기교체(가철탑 2기 신설,철거) / 전력선교체: 1.842km - #2T/L : 가선로에서 본선로 이동 및 전력선교체(No.57~62)","2020-12-14 07:00","2020-12-18 18:00","취소","취소","연속"]
[71,"충북","청주","신옥천S/S #3 M.Tr","미동작 차단기 조작 시험 및 케이블 추가 포설","미동작 차단기 조작 시험 및 케이블 추가 포설","2020-12-03 10:00","2020-12-03 18:00","2020-12-03 10:00","2020-12-03 18:00","연속"]
[72,"충북","청주","신옥천S/S 345kV CB 7272","20-21년 청주전력 변전정비 총액","GIS보통점검","2020-12-04 09:00","2020-12-04 18:00","2020-12-04 09:00","2020-12-04 18:00","연속"]
[73,"충북","청주","신옥천S/S 345kV CB 7200","20-21년 청주전력 변전정비 총액","GIS보통점검","2020-12-03 09:00","2020-12-03 18:00","2020-12-02 09:00","2020-12-02 18:00","연속"]
[74,"충북","청주","신옥천S/S #2 M.Tr","미동작 차단기 조작 시험 및 케이블 추가 포설","미동작 차단기 조작 시험 및 케이블 추가 포설","2020-12-02 10:00","2020-12-02 18:00","2020-12-02 10:00","2020-12-02 18:00","연속"]
[75,"충북","청주","신옥천S/S #1 M.Tr","미동작 차단기 조작 시험 및 케이블 추가 포설","미동작 차단기 조작 시험 및 케이블 추가 포설","2020-12-01 10:00","2020-12-01 18:00","2020-12-01 10:00","2020-12-01 18:00","연속"]
[76,"충북","충주","신제천신충주#2 T/L","20-21년 충주전력지사 변전정비 총액공사","신제천-신충주#2T/L 7371 GIS 및 피뢰기 보통점검","2020-12-01 10:00","2020-12-01 18:00","2020-12-01 10:00","2020-12-01 18:00","연속"]
[77,"충북","충주","신충주S/S #1 M.Tr","신충주S/S #1M.Tr 345kV 주변압기 정밀점검","신충주S/S #1M.Tr 345kV 주변압기 정밀점검","2020-12-01 09:00","2020-12-14 18:00","2020-12-01 09:00","2020-12-14 18:00","연속"]
[78,"대전충남","서산","신당진개폐소북당진 T/L","서산P/O OPGW 항공장애표시구 시설공사","OPGW 항공장애표시구 6개 설치","2020-12-06 08:00","2020-12-06 18:00","취소","취소","연속"]
[79,"대전충남","서산","신서산신당진#2 T/L","20년 서산P/O 변전정비 총액공사","신당진S/S 345kV 신서산-신당진#2 CVT 보통점검","2020-12-09 10:00","2020-12-09 18:00","2020-11-26 10:00","2020-11-26 18:00","연속"]
[80,"대전충남","서산","신서산신당진#1 T/L","20년 서산P/O 변전정비 총액공사","신당진S/S 345kV 신서산-신당진#1 CVT 보통점검","2020-12-08 10:00","2020-12-08 18:00","취소","취소","연속"]
[81,"대전충남","서산","신서산신당진#1 T/L","서산P/O OPGW 항공장애표시구 시설공사","항공장애표시구 22개 설치","2020-12-05 08:00","2020-12-05 18:00","2020-11-25 10:00","2020-11-25 18:00","연속"]
[82,"대전충남","서산","신서산아산#2 T/L","서산P/O OPGW 항공장애표시구 시설공사","OPGW항공장애표시구 22개 설치","2020-12-05 08:00","2020-12-05 18:00","2020-11-25 10:00","2020-11-25 18:00","연속"]
[83,"대전충남","서산","신당진개폐소태안TP#2 T/L","20년 서산P/O 변전정비 총액공사","태안화력S/S 개폐소-태안TP#2 T/L CVT 보통점검 신당진S/S 개폐소-태안TP#2 T/L CVT 보통점검","2020-12-02 09:00","2020-12-03 18:00","취소","취소","매일"]
[84,"대전충남","아산","신온양S/S #2 M.Tr","신온양S/S 345kV #2M.Tr 부싱절연유 채유","신온양S/S 345kV #2M.Tr 부싱절연유 채유","2020-12-07 09:00","2020-12-07 18:00","2020-12-07 09:00","2020-12-07 18:00","연속"]
[85,"대전충남","아산","신탕정S/S #3 M.Tr","신탕정S/S 345kV #3M.Tr GIS 내장형 콘덴서 설치","신탕정S/S 345kV #3M.Tr GIS 내장형 콘덴서 설치(GIS 이상전압 발생으로 시행)","2020-12-21 09:00","2020-12-27 18:00","2020-12-21 09:00","2020-12-27 18:00","연속"]
[86,"대전충남","아산","신탕정S/S #2 M.Tr","신탕정S/S 345kV #2M.Tr GIS 내장형 콘덴서 설치","신탕정S/S 345kV #2M.Tr GIS 내장형 콘덴서 설치(GIS 이상전압 발생으로 시행)","2020-12-14 09:00","2020-12-18 18:00","2020-12-14 09:00","2020-12-18 18:00","연속"]
[87,"대전충남","아산","신탕정S/S #1 M.Tr","신탕정S/S 345kV #1M.Tr GIS 내장형 콘덴서 설치","신탕정S/S 345kV #1M.Tr GIS 내장형 콘덴서 설치(GIS 이상전압 발생으로 시행)","2020-12-07 09:00","2020-12-11 18:00","2020-12-07 09:00","2020-12-11 18:00","연속"]
[88,"대전충남","아산","아산S/S 345kV CB 7800","아산S/S 345KV 현대제 GIS 공기조작부 성능개선공사","- 공기조작부 컨트롤블럭 철거 공장점검입고 - 점검완료분 설치 - 차단기 개폐타임","2020-12-07 09:00","2020-12-09 18:00","2020-12-07 09:00","2020-12-09 18:00","연속"]
[89,"대전충남","아산","아산화성#2 T/L","[송전]345kV아산-화성T/L 초기점검","345kV아산-화성#2T/L18~31호 초기점검","2020-12-02 08:00","2020-12-02 18:00","2020-12-12 08:00","2020-12-12 18:00","연속"]
[90,"대전충남","아산","아산화성#1 T/L","[송전]345kV아산-화성T/L 초기점검","345kV아산-화성#1T/L18~31호 초기점검","2020-12-01 08:00","2020-12-01 18:00","2020-12-05 08:00","2020-12-05 18:00","연속"]
[91,"대전충남","청양","보령C/C 345kV SEC CB 70710","보령C/C 345kV CB(70-71-0) 부동작예방 조작시험","보령C/C 345kV CB(70-71-0) 부동작예방 조작시험","2020-12-01 09:00","2020-12-01 13:00","2020-12-01 09:00","2020-12-01 13:00","연속"]
[92,"대전충남","청양","보령C/C 345kV SEC CB 75760","보령C/C 345kV CB(75-76-0) 부동작예방 조작시험","보령C/C 345kV CB(75-76-0) 부동작예방 조작시험","2020-12-01 14:00","2020-12-01 18:00","2020-12-01 14:00","2020-12-01 18:00","연속"]
[93,"대전충남","청양","청양S/S 345kV CB 7371","청양S/S 362kV GIS(7371) 보통점검 및 전자변교체","청양S/S 362kV GIS(7371) 보통점검 및 전자변교체, 메커니즘점검","2020-12-02 09:00","2020-12-02 18:00","2020-12-02 09:00","2020-12-02 18:00","연속"]
[94,"전북","군산","군산S/S #4 M.Tr","군산S/S 주변압기 인출단자 변경공사","- 압축식 단자변경","2020-12-07 10:00","2020-12-07 18:00","2020-12-07 10:00","2020-12-07 18:00","연속"]
[95,"전북","군산","군산S/S #2 M.Tr","군산S/S 주변압기 인출단자 변경공사","- 압축식 단자변경","2020-12-02 10:00","2020-12-02 18:00","2020-12-02 10:00","2020-12-02 18:00","연속"]
[96,"전북","군산","군산S/S #1 M.Tr","군산S/S 주변압기 인출단자 변경공사","- 압축식 단자변경","2020-12-01 10:00","2020-12-01 18:00","2020-12-01 10:00","2020-12-01 18:00","연속"]
[97,"전북","군산","군산S/S 345kV CB 7100","'20년 군산S/S 공압식차단기(7100 CB) 전자변 교체공사","- 군산S/S 345kV 군산-신김제#2 T/L 7100 TIE CB 전자변 교체","2020-12-17 09:00","2020-12-17 18:00","2020-12-17 09:00","2020-12-17 18:00","연속"]
[98,"전북","군산","군산S/S 345kV CB 7171","'20년 군산S/S 공압식차단기(7171 CB) 전자변 교체공사","- 군산S/S 345kV 군산-신김제#2 T/L 7171 CB 전자변 교체","2020-12-16 09:00","2020-12-16 18:00","2020-12-16 09:00","2020-12-16 18:00","연속"]
[99,"전북","군산","군산S/S #3 M.Tr","군산S/S 주변압기 인출단자 변경공사","- 압축식 단자변경","2020-12-04 10:00","2020-12-04 18:00","2020-12-04 10:00","2020-12-04 18:00","연속"]
[100,"전북","직할","신남원광양#1 T/L","신남원S/S 362kV GIS GAS 누기 보수공사","- 7500CB A,B,C상 누기보수, #75BUS 휴전병행","2020-12-02 09:00","2020-12-15 18:00","취소","취소","연속"]
[101,"전북","직할","신남원한빛NP#1 T/L","`20~`21년 전북 직할 변전정비회사 총액공사","신남원S/S 신남원-한빛NP#1T/L A,B,C상 피뢰기점검","2020-12-15 09:00","2020-12-16 18:00","취소","취소","연속"]
[102,"전북","직할","신남원S/S 345kV #70BUS","신남원S/S GAS 누기 보수공사(2차)-#70BUS","- 12/21 ~ 01/08 : 신남원-광양#2T/L 휴전병행","2020-12-21 09:00","2021-01-08 18:00","취소","취소","연속"]
[103,"전북","직할","신남원광양#2 T/L","신남원S/S GAS 누기 보수공사(2차)-7600","- 12/16~19 : 7600CB C상 GAS 누기보수, #75BUS 휴전병행 - 12/20~01/06 : 7671CB A, B, C상 GAS 누기보수, #70BUS 휴전병행 - 01/07~08 : 7661DS B GAS 누기보수, #70BUS 휴전병행","2020-12-16 09:00","2021-01-08 18:00","취소","취소","연속"]
[104,"전북","직할","신남원한빛NP#2 T/L","신남원-한빛NP#2T/L OPGW 항공구 시설공사","신남원-한빛NP#2T/L 미설치 항공구 시설","2020-12-07 09:00","2020-12-10 18:00","취소","취소","연속"]
[105,"전북","직할","신남원S/S 345kV CB 7371","2020년 전북 직할 362kV GIS 정밀점검 공사 (7371 CB)","신남원S/S 345kV 신남원-의령#1T/L 정밀점검","2020-12-21 09:00","2020-12-24 18:00","2020-12-21 09:00","2020-12-24 18:00","연속"]
[106,"전북","직할","신남원S/S 345kV CB 7100","2020년 전북 직할 362kV GIS 정밀점검 공사 (7100 CB)","신남원S/S 345kV 신옥천신남원#2-신남원한빛#2 CB 정밀점검","2020-12-16 09:00","2020-12-19 18:00","2020-12-16 09:00","2020-12-19 18:00","연속"]
[107,"전북","직할","신남원신광주#1 T/L","345kV 신남원-신광주 등 5개T/L 추락방지시설 설치공서","1. 345kV 신남원-신광주 #2T/L 추락방지시설 설치공사 가. 대상철탑 : 345kV 신남원-신광주T/L No. 3, 6(4회선 병가구간)","2020-12-01 08:00","2020-12-02 17:00","2020-12-16 08:00","2020-12-17 17:00","매일"]
[108,"전북","직할","신남원S/S 345kV CB 7571","2020년 전북 직할 362kV GIS 정밀점검 공사 (7571 CB)","신남원S/S 345kV 신남원-광양#1 T/L 정밀점검","2020-12-02 09:00","2020-12-15 18:00","2020-12-02 09:00","2020-12-15 18:00","연속"]
[109,"광주전남","강진","신강진S/S #1 M.Tr","'20-21년 강진전력지사 변전정비회사 총액공사","O 신강진S/S #1M.Tr 3차 종합 VCB 대체 O 신강진S/S #1S.Tr VCB 대체 O 신강진S/S #1M.Tr 3차측 절연화 시공","2020-12-15 09:00","2020-12-16 18:00","2020-12-15 09:00","2020-12-16 18:00","연속"]
[110,"광주전남","강진","신강진S/S #2 M.Tr","'20-21년 강진전력지사 변전정비회사 총액공사","O 신강진S/S #2S.Tr VCB 대체 O 신강진S/S #2M.Tr 3차측 절연화 시공","2020-12-17 09:00","2020-12-18 18:00","2020-12-17 09:00","2020-12-18 18:00","연속"]
[111,"광주전남","순천","신남원광양#2 T/L","345kV신남원-광양T/L 안전이격확보공사","철탑조립 3기 전력선교체 2.281KM","2020-12-16 07:00","2020-12-23 18:00","취소","취소","연속"]
[112,"대구","포항","신포항S/S 345kV CB 7372","신포항S/S 7471, 7372 CB 조작시험","신포항S/S 7471, 7372 CB 조작시험","2020-12-08 14:00","2020-12-08 18:00","2020-12-08 14:00","2020-12-08 18:00","연속"]
[113,"대구","포항","신포항S/S 345kV CB 7471","신포항S/S 7471, 7372 CB 조작시험","신포항S/S 7471, 7372 CB 조작시험","2020-12-08 09:30","2020-12-08 14:00","2020-12-08 09:30","2020-12-08 14:00","연속"]
[114,"대구","포항","신포항S/S 345kV CB 7272","신포항S/S 7272, 7572 CB 조작시험","신포항S/S 7272, 7572 CB 조작시험","2020-12-09 09:30","2020-12-09 14:00","2020-12-09 09:30","2020-12-09 14:00","연속"]
[115,"대구","포항","신포항S/S 345kV CB 7572","신포항S/S 7272, 7572 CB 조작시험","신포항S/S 7272, 7572 CB 조작시험","2020-12-09 14:00","2020-12-09 18:00","2020-12-09 14:00","2020-12-09 18:00","연속"]
[116,"대구","포항","신포항S/S 345kV CB 7772","신포항S/S 7772 CB 조작시험","신포항S/S 7772 CB 조작시험","2020-12-10 09:30","2020-12-10 14:00","2020-12-10 09:30","2020-12-10 14:00","연속"]
[117,"부산울산","동부산","고리N/P 345kV CB 7371","고리NP S/Y 345kV GIS 차단기 동작시험","고리NP S/Y 7371GIS 차단기 동작시험","2020-12-01 09:30","2020-12-01 17:00","2020-12-01 09:30","2020-12-01 17:00","연속"]
[118,"부산울산","동부산","고리N/P 345kV #75 BUS","345kV 고리N/P S/W 증설공사","1. 765kV 신고리S/S #4M.Tr 증설관련 345kV 2차측 GIS 증설 : #75BUS측 2. 시험가압 : #76BUS→#75BUS→7452DS→7472CB→7400CB(76BUS측 기기조작 없음)","2020-12-23 09:00","2021-01-06 18:00","2020-12-23 09:00","2021-01-06 18:00","연속"]
[119,"부산울산","동부산","고리N/P 345kV #70 BUS","345kV 고리N/P S/W 증설공사","1. 765kV 신고리S/S #4M.Tr 증설관련 345kV 2차측 GIS 증설 : #70BUS 2. 시험가압 : #71BUS→#70BUS→7451DS(#71BUS측 기기조작 없음)","2020-12-08 09:00","2020-12-22 18:00","2020-12-08 09:00","2020-12-22 18:00","연속"]
[120,"부산울산","북부산","북부산S/S 345kV CB 7478","20-21 북부산전력지사 변전 총액공사","북부산S/S 345kV 신김해-북부산#2T/L 7478 BY-PASS차단기 동작시험","2020-12-04 10:00","2020-12-04 13:00","2020-12-04 10:00","2020-12-04 13:00","연속"]
[121,"부산울산","북부산","북부산S/S 345kV SEC CB 70710","20-21 북부산전력지사 변전 총액공사","북부산S/S 345kV 70-71-0 BUS-SECTION 차단기 전자변 교체","2020-12-10 10:00","2020-12-11 18:00","2020-12-10 10:00","2020-12-11 18:00","연속"]
[122,"부산울산","북부산","북부산S/S #1 M.Tr","20-21 북부산전력지사 변전 총액공사","북부산S/S 345kV #1M.Tr 2차 GIS(6144) 하자점검","2020-12-15 10:00","2020-12-16 18:00","2020-12-15 10:00","2020-12-16 18:00","연속"]
[123,"부산울산","북부산","북부산S/S 345kV SEC CB 75760","20-21 북부산전력지사 변전 총액공사","북부산S/S 345kV 75-76-0 BUS-SECTION 차단기 전자변 교체","2020-12-17 10:00","2020-12-18 18:00","2020-12-17 10:00","2020-12-18 18:00","연속"]
[124,"부산울산","서부산","서부산S/S #3 M.Tr","서부산S/S #3M.Tr 보통점검","서부산S/S #3M.Tr 보통점검","2020-12-14 10:00","2020-12-16 18:00","2020-12-14 10:00","2020-12-16 18:00","연속"]
[125,"부산울산","서부산","서부산S/S #1 M.Tr","서부산S/S #1M.Tr 2차 GIS 보통점검 및 전자변교체","서부산S/S #1M.Tr 2차 GIS 보통점검 및 전자변교체","2020-12-08 10:00","2020-12-08 18:00","2020-12-08 10:00","2020-12-08 18:00","연속"]
[126,"부산울산","서부산","신녹산S/S #3 M.Tr","신녹산S/S #3M.Tr 2차 GIS 차단기동작시험","신녹산S/S #3M.Tr 2차 GIS 차단기동작시험","2020-12-11 10:00","2020-12-11 18:00","2020-12-11 10:00","2020-12-11 18:00","연속"]
[127,"부산울산","서부산","신녹산S/S #2 M.Tr","신녹산S/S #2M.Tr 2차 GIS 차단기동작시험","신녹산S/S #2M.Tr 2차 GIS 차단기동작시험","2020-12-10 10:00","2020-12-10 18:00","2020-12-10 10:00","2020-12-10 18:00","연속"]
[128,"부산울산","울산","동울산신울산#2 T/L","2020년도 가공송전 순시점검 위탁공사","항공점검 과열개소 정비 - 대상구간 : (기)동울산월성NPT/L 41호((신)동울산-신울산 측)","2020-12-02 09:00","2020-12-02 18:00","2020-12-02 09:00","2020-12-02 18:00","연속"]
[129,"부산울산","울산","동울산월성NP#2 T/L","2020년도 가공송전 순시점검 위탁공사","○ 항공점검 관련 과열개소 정비 - 대상구간 : 26호, 31호","2020-12-01 09:00","2020-12-01 18:00","2020-12-01 09:00","2020-12-01 18:00","연속"]
[130,"부산울산","울산","북부산신온산 T/L","345kV 신울산복합-북부산T/L 건설공사","남울산S/S 계통구성 및 신울산복합-북부산T/L #1 최초가압","2020-12-07 07:00","2020-12-16 18:00","취소","취소","연속"]
[131,"부산울산","울산","신온산울산TP T/L","345kV 신울산복합-북부산T/L 건설공사","남울산S/S 계통구성","2020-12-17 07:00","2020-12-24 18:00","취소","취소","연속"]
[132,"부산울산","울산","신울산S/S #3 M.Tr","신울산S/S 154kV GIS현대화공사","- 154kV TR-BUS 철거관련 345kV #3M.Tr 6368DS철거","2020-12-01 09:00","2020-12-02 18:00","2020-12-01 09:00","2020-12-02 18:00","연속"]
[133,"부산울산","울산","신울산S/S #2 M.Tr","신울산S/S 154kV GIS현대화공사","- 154kV TR-BUS 철거관련 345kV #2M.Tr #6268DS철거","2020-12-25 09:00","2020-12-26 18:00","2020-12-25 09:00","2020-12-26 18:00","연속"]
[134,"부산울산","울산","북부산울산TP T/L","345kV 신울산복합-북부산T/L 건설공사","남울산S/S 계통구성","2020-12-25 07:00","2020-12-29 18:00","취소","취소","연속"]
[135,"경남","직할","신김해북부산#1 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 철탑설치 및 철거 : 각 2기 ○ 전력선 및 가공지선 교체 : 1.4km (93-97호) ○ 스페이서 댐퍼 교체","2020-12-24 07:00","2020-12-30 18:00","취소","취소","연속"]
[136,"경남","직할","신김해S/S #1 M.Tr","신김해S/S 345kV #1M.Tr 3차 PT점검","신김해S/S 345kV #1M.Tr 3차 PT점검","2020-12-16 09:30","2020-12-16 17:30","2020-12-16 09:30","2020-12-16 17:30","연속"]
[137,"경남","직할","신김해S/S #3 M.Tr","신김해S/S 345kV #3M.Tr 1차 LA 교체","신김해S/S 345kV #3M.Tr 1차 LA 교체","2020-12-15 09:30","2020-12-15 17:30","2020-12-15 09:30","2020-12-15 17:30","연속"]
[138,"경남","직할","신김해북부산#2 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 철탑설치 및 철거 : 각 2기 ○ 전력선 및 가공지선 교체 : 1.4km (93-97호) ○ 스페이서 댐퍼 교체","2020-12-31 07:00","2021-01-06 18:00","취소","취소","연속"]
[139,"경남","직할","신김해창원#1 T/L","2020-21 경남본부 직할 송전정비회사 총액공사","추락방지시설(와이어)설치","2020-12-01 07:00","2020-12-01 18:00","2020-12-02 07:00","2020-12-02 18:00","연속"]
[140,"경남","직할","신김해창원#2 T/L","2020-21 경남본부 직할 송전정비회사 총액공사","추락방지시설(와이어)설치","2020-12-02 07:00","2020-12-02 18:00","2020-12-01 07:00","2020-12-01 18:00","연속"]
[141,"경남","직할","창원S/S #2 M.Tr","창원S/S 345kV #2M.Tr 1,2,3차 GIS 조작시험","창원S/S 345kV #2M.Tr 1,2,3차 GIS 조작시험","2020-12-14 09:30","2020-12-14 17:30","2020-12-14 09:30","2020-12-14 17:30","연속"]
[142,"경남","진주","하동T/P 345kV #76 BUS","하동T/P #76BUS 모선보호반 대체","하동T/P #76BUS 모선보호반 대체","2020-12-14 10:00","2020-12-18 18:00","취소","취소","연속"]
[143,"경남","진주","하동T/P 345kV #71 BUS","하동T/P #71BUS 모선보호반 대체","하동T/P #71BUS 모선보호반 대체","2020-12-21 10:00","2020-12-25 18:00","취소","취소","연속"]
[144,"경남","진주","하동T/P 345kV CB 7672","하동T/P 345kV #6M.Tr 1차 TIE CB(7672) 보통점검","하동T/P 345kV #6M.Tr 1차 TIE CB(7672) 보통점검","2020-12-02 10:00","2020-12-02 16:00","취소","취소","연속"]
[145,"경남","통영","신고성S/S 345kV CB 7472G","신고성S/S 7472 GIS 조작시험","1. 신고성S/S 7472 GIS 조작시험","2020-12-01 10:00","2020-12-01 14:00","2020-12-01 10:00","2020-12-01 14:00","연속"]
[146,"경남","통영","신고성S/S #3 M.Tr","신고성S/S #3M.Tr 보호반 대체","1. 신고성S/S #3M.Tr 보호반 대체","2020-12-07 10:00","2020-12-11 18:00","2020-12-07 10:00","2020-12-11 18:00","연속"]
[147,"경남","통영","신고성S/S 345kV CB 7400G","신고성S/S 7400 GIS 조작시험","1. 신고성S/S 7400 GIS 조작시험","2020-12-01 14:00","2020-12-01 18:00","2020-12-01 14:00","2020-12-01 18:00","연속"]
[148,"대전충남","서산","신서산S/S 345kV #3 Sh.R","7579CB 전자변 교체(A,B,C상)","7579CB 전자변 교체(A,B,C상)","2020-12-10 10:00","2020-12-11 18:00","2020-12-10 10:00","2020-12-11 18:00","연속"]
[149,"경북","청송","청송양수1호기 주변압기 CB(7100,7172)","동기차단기 내전압 시험","동기차단기 내전압 시험","2020-12-04 16:00","2020-12-08 13:00","2020-12-04 16:00","2020-12-08 13:00","연속"]
[150,"경북","청송","청송양수2호기 주변압기 CB(7200,7272)","동기차단기 내전압 시험","동기차단기 내전압 시험","2020-12-08 13:00","2020-12-11 16:00","2020-12-08 13:00","2020-12-11 16:00","연속"]
[151,"대구","포항","월성N/P #2호기 주변압기 CB(7300, 7372)","월성 2호기 제19차 계획예방정비관련 계통병입전 대기(CB7300, CB7372)","계통병입전 IPB링크 조립 및 계통병입 대기 등","2020-11-27 18:00","2020-12-04 07:00","2020-11-27 18:00","2020-12-04 07:00","연속"]

{"sheet":"154송부","index":2,"n_rows":322,"n_cols":11,"rows_kept":322,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2020년도 12월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성수뚝도#2 T/L","'20년 성동P/O 노후 보호배전반 교체공사","성수, 뚝도S/S 154kV 성수뚝도#2T/L 보호배전반 노후대체","2020-10-19 10:00","2020-10-22 17:00","취소","취소","연속"]
[2,"서울","성동","성수뚝도#2 T/L","'20년 성동P/O 노후 보호배전반 교체공사","성수, 뚝도S/S 154kV 성수뚝도#2T/L 보호배전반 노후대체","2020-12-07 10:00","2020-12-10 17:00","취소","취소","연속"]
[3,"서울","중부","상암등촌#1 T/L","2020~2021 서울본부 가공송전정비회사 총액공사","불량애자 및 지지애자교체 : 1,4,7 추락방지시설 설치 : 1,2,4,5,6","2020-12-14 08:00","2020-12-15 18:00","2020-12-14 08:00","2020-12-15 18:00","연속"]
[4,"서울","중부","원흥상암 T/L","`20 중부PO 변전정비회사 총액공사","원흥상암TL GIS 보통점검","2020-12-07 10:00","2020-12-07 18:00","2020-12-07 10:00","2020-12-07 18:00","연속"]
[5,"서울","중부","상암등촌#2 T/L","2020~2021 서울본부 가공송전정비회사 총액공사","불량애자 및 지지애자교체 : 1,7 추락방지시설 설치 : 1,2,4,5,6","2020-12-16 08:00","2020-12-17 18:00","2020-12-16 08:00","2020-12-17 18:00","연속"]
[6,"서울","중부","수색S/S 154kV #1 BUS","`20 중부PO 변전정비회사 총액공사","수색중부#2TL, #3M.Tr LS 모선 LS점검","2020-12-01 10:00","2020-12-01 14:00","취소","취소","연속"]
[7,"서울","중부","수색S/S 154kV #2 BUS","`20 중부PO 변전정비회사 총액공사","수색중부#2TL, #3M.Tr LS 모선 LS점검","2020-12-01 14:00","2020-12-01 18:00","취소","취소","연속"]
[8,"서울","중부","원흥수색#1 T/L","`20 중부PO 변전 정비회사 총액공사","원흥수색TL 모선LS 점검","2020-12-02 09:00","2020-12-02 18:00","2020-12-05 10:00","2020-12-05 18:00","연속"]
[9,"서울","중부","수색S/S 154kV #1 BUS","`20 중부PO 변전정비회사 총액공사","원흥수색#1TL LS 보통점검","2020-12-02 10:00","2020-12-02 14:00","취소","취소","연속"]
[10,"서울","중부","수색S/S 154kV #2 BUS","`20 중부PO 변전정비회사 총액공사","원흥수색#1TL LS 보통점검","2020-12-02 14:00","2020-12-02 18:00","취소","취소","연속"]
[11,"서울","중부","수색S/S 154kV #1 BUS","`20 중부PO 변전정비회사 총액공사","수색은평#1TL LS 보통점검","2020-12-04 10:00","2020-12-04 14:00","2020-12-05 10:00","2020-12-05 14:00","연속"]
[12,"서울","중부","수색S/S 154kV #2 BUS","`20 중부PO 변전정비회사 총액공사","수색은평#1TL LS 보통점검","2020-12-04 14:00","2020-12-04 18:00","2020-12-05 14:00","2020-12-05 18:00","연속"]
[13,"서울","중부","수색S/S 154kV #1 BUS","`20 중부PO 변전정비회사 총액공사","수색중부#1TL 모선LS 점검","2020-12-05 08:00","2020-12-05 13:00","2020-12-06 08:00","2020-12-06 13:00","연속"]
[14,"서울","중부","수색S/S 154kV #2 BUS","`20 중부PO 변전정비회사 총액공사","수색중부#1TL 모선LS 점검","2020-12-05 13:00","2020-12-05 18:00","2020-12-06 13:00","2020-12-06 18:00","연속"]
[15,"서울","중부","수색S/S 154kV #1 BUS","2020년 중부전력지사 170kV GIS 정밀점검(이월분)","수색S/S 수색상암#1T/L GCB 정밀점검 시험가압용","2020-12-02 17:00","2020-12-02 18:00","취소","취소","연속"]
[16,"서울","직할","서소문S/S 154kV #1 BUS","20년 서울직할 170kV GIS 정밀점검공사","서소문S/S #3M.Tr 1차 GIS 시험가압","2020-12-22 17:00","2020-12-22 18:00","2020-12-24 17:00","2020-12-24 18:00","연속"]
[17,"서울","직할","원남미아#1 T/L","20년 서울직할 170kV GIS 정밀점검공사","원남S/S #3M.Tr 1차 GIS 시험가압","2020-12-16 17:00","2020-12-16 18:00","2020-12-16 17:00","2020-12-16 18:00","연속"]
[18,"서울","직할","원남미아#1 T/L","20년 직할 변전협력 총액공사","GIS조작시험,전자변교체","2020-12-10 10:00","2020-12-10 18:00","2020-12-10 10:00","2020-12-10 18:00","연속"]
[19,"서울","직할","중앙서소문 T/L","20년 직할 170kV GIS 정밀점검공사","GIS 정밀점검","2020-12-07 10:00","2020-12-09 18:00","2020-12-09 10:00","2020-12-11 18:00","연속"]
[20,"남서울","동서울","동서울서종#1 T/L","세종-포천고속도로 건설사업 지장송전선로 이설공사","154kV 동서울-서종T/L 임시철탑 건설 및 가선공사(No.92~94)","2020-12-16 09:00","2020-12-24 18:00","2020-11-23 09:00","2020-12-01 18:00","연속"]
[21,"남서울","동서울","동서울서종#2 T/L","세종-포천고속도로 건설사업 지장송전선로 이설공사","154kV 동서울-서종T/L 임시철탑 건설 및 가선공사(No.92~94)","2020-12-25 09:00","2020-12-30 18:00","2020-12-02 09:00","2020-12-07 18:00","연속"]
[22,"남서울","동서울","잠실수서#2 T/L","EBA 부분방전 진단센서 설치공사","PD센서 6개 및 Test Box 설치","2020-12-02 09:00","2020-12-03 18:00","2020-12-02 09:00","2020-12-03 18:00","연속"]
[23,"남서울","영등포","가양S/S 154kV CB 6100","가양S/S 170kV GIS 조작시험(6100)","- 차단기 개폐타임 측정 - GIS 조작시험","2020-12-11 09:00","2020-12-11 18:00","2020-12-11 09:00","2020-12-11 18:00","연속"]
[24,"남서울","영등포","구공S/S 154kV #61 BUS","154kV 신광명-구공 지중T/L 건설공사","구간 : 154kV 신광명S/S ~ 구공S/S 선종및긍장 : 154kV XLPE 2000SQ 2C 5.3km","2020-12-16 14:00","2020-12-16 17:00","2020-12-13 09:00","2020-12-13 12:00","연속"]
[25,"남서울","영등포","구공S/S 154kV #60 BUS","154kV 신광명-구공 지중T/L 건설공사","구간 : 154kV 신광명S/S ~ 구공S/S 선종및긍장 : 154kV XLPE 2000SQ 2C 5.3km","2020-12-15 09:00","2020-12-15 14:00","2020-12-12 09:00","2020-12-12 12:00","연속"]
[26,"남서울","영등포","구공대림#2 T/L","154kV 신광명-구공 지중T/L 건설공사","구간 : 154kV 신광명S/S ~ 구공S/S 선종및긍장 : 154kV XLPE 2000SQ 2C 5.3km","2020-12-15 09:00","2020-12-16 14:00","2020-12-12 09:00","2020-12-13 09:00","연속"]
[27,"남서울","영등포","구공S/S 154kV #65 BUS","154kV 신광명-구공 지중T/L 건설공사","구간 : 154kV 신광명S/S ~ 구공S/S 선종및긍장 : 154kV XLPE 2000SQ 2C 5.3km","2020-12-15 14:00","2020-12-16 14:00","2020-12-12 12:00","2020-12-13 09:00","연속"]
[28,"남서울","영등포","구공대림#1 T/L","154kV 신광명-구공 지중T/L 건설공사","구간 : 154kV 신광명S/S ~ 구공S/S 선종및긍장 : 154kV XLPE 2000SQ 2C 5.3km","2020-12-16 14:00","2020-12-17 17:00","2020-12-13 09:00","2020-12-14 09:00","연속"]
[29,"남서울","영등포","구공대림#1 T/L","구공S/S 154kV 가산메트로#1,2T/L 증설","구공S/S 154kV 가산메트로#1,2T/L GIS 설치 무부하가압용 선로","2020-12-30 18:00","2020-12-31 18:00","2020-12-30 18:00","2020-12-31 18:00","연속"]
[30,"남서울","영등포","구공S/S 154kV #66 BUS","154kV 신광명-구공 지중T/L 건설공사","구간 : 154kV 신광명S/S ~ 구공S/S 선종및긍장 : 154kV XLPE 2000SQ 2C 5.3km","2020-12-16 17:00","2020-12-17 17:00","2020-12-13 12:00","2020-12-14 09:00","연속"]
[31,"남서울","영등포","구공S/S 154kV #60 BUS","구공S/S 154kV 가산메트로#1,2T/L 증설","구공S/S 154kV 가산메트로#1,2T/L GIS 설치","2020-12-18 09:00","2020-12-21 18:00","2020-12-18 09:00","2020-12-21 18:00","연속"]
[32,"남서울","영등포","구공대림#2 T/L","구공S/S 154kV 가산메트로#1,2T/L 증설","구공S/S 154kV 가산메트로#1,2T/L GIS 설치 무부하가압용 선로","2020-12-20 18:00","2020-12-21 18:00","2020-12-20 18:00","2020-12-21 18:00","연속"]
[33,"남서울","영등포","구공S/S 154kV #65 BUS","구공S/S 154kV 가산메트로#1,2T/L 증설","구공S/S 154kV 가산메트로#1,2T/L GIS 설치","2020-12-22 09:00","2020-12-24 18:00","2020-12-22 09:00","2020-12-24 18:00","연속"]
[34,"남서울","영등포","구공대림#2 T/L","구공S/S 154kV 가산메트로#1,2T/L 증설","구공S/S 154kV 가산메트로#1,2T/L GIS 설치 무부하가압용 선로","2020-12-23 18:00","2020-12-24 18:00","2020-12-23 18:00","2020-12-24 18:00","연속"]
[35,"남서울","영등포","구공S/S 154kV #61 BUS","구공S/S 154kV 가산메트로#1,2T/L 증설","구공S/S 154kV 가산메트로#1,2T/L GIS 설치","2020-12-25 09:00","2020-12-28 18:00","2020-12-25 09:00","2020-12-28 18:00","연속"]
[36,"남서울","영등포","구공대림#1 T/L","구공S/S 154kV 가산메트로#1,2T/L 증설","구공S/S 154kV 가산메트로#1,2T/L GIS 설치 무부하가압용 선로","2020-12-27 18:00","2020-12-28 18:00","2020-12-27 18:00","2020-12-28 18:00","연속"]
[37,"남서울","영등포","구공S/S 154kV #66 BUS","구공S/S 154kV 가산메트로#1,2T/L 증설","구공S/S 154kV 가산메트로#1,2T/L GIS 설치","2020-12-29 09:00","2020-12-31 18:00","2020-12-29 09:00","2020-12-31 18:00","연속"]
[38,"남서울","영등포","구로S/S 154kV #2 BUS","154kV 천왕-구로,오류T/L 지장송전선로이설공사","○ 위 치 : 광명시 광명동 776-16일원 ○ 선 로 명 : 154kV 천왕-구로#1,2T/L ○ 구 간 : 천왕S/S S/J M/H#1 ∼M/H#3호 구간중 121m ○ 휴전 모선명 : 154kV 구로S/S 170kV GIS #65 BUS ○ 휴전 사유 : 상시험 ○ 주요공종 - 케이블철거,포설, 접속 등 준공시험","2020-12-10 10:00","2020-12-10 10:15","2020-12-10 10:00","2020-12-10 10:30","연속"]
[39,"남서울","영등포","등촌S/S 154kV #1 BUS","등촌S/S 170kV GIS 접지 인터록 점검","- 등촌SS 170kV GIS 접지 인터록 점검","2020-12-05 09:00","2020-12-05 14:00","2020-12-05 09:00","2020-12-05 14:00","연속"]
[40,"남서울","영등포","등촌S/S 154kV #2 BUS","등촌S/S 170kV GIS 접지 인터록 점검","- 170kV GIS 접지 인터록 점검","2020-12-05 14:00","2020-12-05 18:00","2020-12-05 14:00","2020-12-05 18:00","연속"]
[41,"남서울","영등포","마곡S/S 154kV CB 6100","마곡S/S 170kV GIS 조작시험(6100)","- 차단기 개폐타임 측정 - GIS 조작시험","2020-12-03 14:00","2020-12-03 18:00","2020-12-03 14:00","2020-12-03 18:00","연속"]
[42,"남서울","영등포","신광명S/S 154kV #65 BUS","154kV 신광명-구공 지중T/L 건설공사","구간 : 154kV 신광명S/S ~ 구공S/S 선종및긍장 : 154kV XLPE 2000SQ 2C 5.3km","2020-12-15 14:00","2020-12-16 14:00","2020-12-12 12:00","2020-12-13 09:00","연속"]
[43,"남서울","영등포","신광명S/S 154kV #61 BUS","154kV 신광명-구공 지중T/L 건설공사","구간 : 154kV 신광명S/S ~ 구공S/S 선종및긍장 : 154kV XLPE 2000SQ 2C 5.3km","2020-12-16 14:00","2020-12-16 17:00","2020-12-13 09:00","2020-12-13 12:00","연속"]
[44,"남서울","영등포","신광명S/S 154kV #66 BUS","154kV 신광명-구공 지중T/L 건설공사","구간 : 154kV 신광명S/S ~ 구공S/S 선종및긍장 : 154kV XLPE 2000SQ 2C 5.3km","2020-12-16 17:00","2020-12-17 17:00","2020-12-13 12:00","2020-12-14 09:00","연속"]
[45,"남서울","영등포","신광명S/S 154kV #60 BUS","154kV 신광명-구공 지중T/L 건설공사","구간 : 154kV 신광명S/S ~ 구공S/S 선종및긍장 : 154kV XLPE 2000SQ 2C 5.3km","2020-12-15 09:00","2020-12-15 14:00","2020-12-12 09:00","2020-12-12 12:00","연속"]
[46,"남서울","영등포","천왕오류#2 T/L","154kV 천왕-구로, 오류T/L 지장송전선로이설공사","○ 위 치 : 광명시 광명동 776-16일원 ○ 선 로 명 : 154kV 천왕-오류#2T/L ○ 구 간 : 천왕S/S S/J M/H#1 ∼M/H#3호 구간중 121m ○케이블철거 및 포설 ○케이블접속 : 2개소, 2회선","2020-12-11 09:00","2021-01-14 18:00","2020-12-11 09:00","2021-01-14 18:00","연속"]
[47,"남서울","영등포","화곡S/S 154kV CB 6100","화곡S/S 170kV GIS 조작시험(6100)","- 차단기 개폐타임 측정 - GIS 조작시험","2020-12-03 09:00","2020-12-03 14:00","2020-12-03 09:00","2020-12-03 14:00","연속"]
[48,"남서울","직할","양평양천#2 T/L","154kV 양평-양천T/L 선종교체공사","○ 위 치 : 양평, 양천S/S 및 목동공동구, 맨홀·전력구 ○ 구 간 : 양평S/S ∼양천S/S ○ 케이블 철거 : 154㎸ OF 1200㎟ × 1회선(D), 2.542㎞ ○ 주요공종 - 케이블 철거구간 : OF 1200㎟(D) × 10구간× 2C - 케이블 포설구간 : 8구간 - 케이블 접속 : 14개소","2020-12-01 09:00","2021-04-19 18:00","2020-12-01 15:00","2021-04-19 18:00","연속"]
[49,"남서울","강남","신양재신사#3 T/L","154kV 신양재-신사#3T/L 절연유 열화진단","154kV 신양재-신사#3T/L 절연유 열화진단","2020-12-03 09:00","2020-12-03 18:00","2020-12-04 09:00","2020-12-04 18:00","연속"]
[50,"남서울","동서울","동서울S/S 154kV #61 BUS ","동서울S/S 345kV 노후 주변압기 교체공사 ","○ 345kV M.Tr 100/166.7MVA * 7대 교체\n○ 기타 부대공사 1식 ","2020-12-21 13:00","2020-12-22 13:00","2020-12-21 13:00","2020-12-22 13:00","연속"]
[51,"인천","김포","양촌양곡#1 T/L","20년도 가공송전순시점검 위탁공사(초기점검)","154kV 양촌_양곡T/L 초기점검 대상 : No.1,2,3,8,9,10,12,13,14","2020-12-01 09:00","2020-12-01 18:00","취소","취소","연속"]
[52,"인천","부평","신가좌신현#2 T/L","신가좌S/S #2M.Tr 2차 GIS 정밀점검 공사 관련 휴전 선로","신가좌S/S #2M.Tr 2차 GIS 정밀점검 공사 관련 휴전 선로","2020-12-01 09:00","2020-12-02 18:00","취소","취소","연속"]
[53,"인천","김포","신김포장기#1 T/L","신김포S/S #64M.Tr 무부하가압","신김포S/S #64M.Tr 무부하가압 - 신김포 장기#1T/L 이용 무부하가압","2020-12-01 13:00","2020-12-02 13:00","취소","취소","연속"]
[54,"인천","시흥","시화동시화#1 T/L","154kV 동시화S/S GIS 설치공사","154kV GIS BUS SEC 증설관련 무부하 가압","2020-12-01 18:00","2020-12-02 18:00","2020-12-01 18:00","2020-12-02 18:00","연속"]
[55,"인천","김포","양촌양곡#2 T/L","20년도 가공송전순시점검 위탁공사(초기점검)","154kV 양촌_양곡T/L 초기점검 대상 : No.1,2,3,8,9,10,12,13,14","2020-12-02 09:00","2020-12-02 18:00","취소","취소","연속"]
[56,"인천","부평","인천C/C 154kV CB 6100","인천복합S/Y #6100 GIS 조작시험","인천복합S/Y #6100 GIS 조작시험","2020-12-02 09:00","2020-12-02 11:00","2020-12-02 09:00","2020-12-02 11:00","연속"]
[57,"인천","부평","인천C/C 154kV SEC CB 60610","인천복합S/Y #60-61 SEC GIS 조작시험","인천복합S/Y #60-61 SEC GIS 조작시험","2020-12-02 11:00","2020-12-02 15:00","2020-12-02 11:00","2020-12-02 15:00","연속"]
[58,"인천","부평","인천C/C 154kV SEC CB 65660","인천복합S/Y #65-66 SEC GIS 조작시험","인천복합S/Y #65-66 SEC GIS 조작시험","2020-12-02 15:00","2020-12-02 18:00","2020-12-02 15:00","2020-12-02 18:00","연속"]
[59,"인천","부평","신가좌S/S 154kV CB 6200","신가좌S/S #6200 GIS 정밀점검 공사","신가좌S/S #6200 GIS 정밀점검 공사","2020-12-03 09:00","2020-12-05 18:00","취소","취소","연속"]
[60,"인천","시흥","동시화서시화 T/L","154kV 동시화S/S GIS 설치공사","154kV GIS BUS SEC 증설","2020-12-03 09:30","2020-12-05 18:00","취소","취소","연속"]
[61,"인천","직할","계양원창 T/L","345kV신가좌-가정#2T/L 정밀점검","345kV신가좌-가정#2T/L 및 154kV계양-원창T/L 병가 구간(No.2,3) 작업을 위한 휴전 신청","2020-12-03 09:30","2020-12-03 13:00","취소","취소","연속"]
[62,"인천","부평","신가좌신현#2 T/L","신가좌S/S #6200 GIS 정밀점검 관련 무부하 선로","신가좌S/S #6200 GIS 정밀점검 관련 무부하 선로","2020-12-05 13:00","2020-12-05 18:00","취소","취소","연속"]
[63,"인천","부평","원창포스코CC#1 T/L","원창S/S 원창포스코CC#1 T/L GIS 보통점검 공사","원창S/S 원창포스코CC#1 T/L GIS 보통점검 공사","2020-12-07 00:09","2020-12-07 18:00","2020-12-07 00:09","2020-12-07 18:00","연속"]
[64,"인천","부평","원창포스코CC#2 T/L","원창S/S 원창포스코CC#2 T/L GIS 보통점검 공사","원창S/S 원창포스코CC#2 T/L GIS 보통점검 공사","2020-12-08 00:09","2020-12-08 18:00","2020-12-08 00:09","2020-12-08 18:00","연속"]
[65,"인천","시흥","시화동시화#1 T/L","154kV 동시화S/S GIS 설치공사","154kV GIS BUS SEC 증설관련 무부하 가압","2020-12-11 18:00","2020-12-12 18:00","2020-12-11 18:00","2020-12-12 18:00","연속"]
[66,"인천","시흥","동시화남시화 T/L","154kV 동시화S/S GIS 설치공사","154kV GIS BUS SEC 증설관련 보호회로 이설","2020-12-13 09:30","2020-12-13 16:00","취소","취소","연속"]
[67,"인천","시흥","동시화서시화 T/L","154kV 동시화S/S GIS 설치공사","154kV GIS BUS SEC 증설관련 보호회로 이설","2020-12-13 09:30","2020-12-13 16:00","취소","취소","연속"]
[68,"인천","시흥","동시화서시화 T/L","154kV 동시화S/S GIS 설치공사","#5M.Tr 초기가압","2020-12-22 14:00","2020-12-23 16:00","취소","취소","연속"]
[69,"경기북부","구리","동서울서종#1 T/L","세니온제 송전선로 보호반 성능개선 공사","IED 펌웨어 업데이트 : 43PDA, 거리계전기 오동작 방지, 검 출 전류 기준값 변경등","2020-12-01 13:00","2020-12-01 15:00","취소","취소","연속"]
[70,"경기북부","구리","운천전곡#2 T/L","`20~21 구리전력 변전정비 총액공사","운천S/S 운천-전곡#2T/L GIS 조작시험, 전자변 교체","2020-12-04 09:00","2020-12-04 18:00","2020-12-04 09:00","2020-12-04 18:00","연속"]
[71,"경기북부","구리","신포천포천#2 T/L","`20~21 구리전력 변전정비 총액공사","포천S/S 신포천-포천#2T/L GCB 개폐타임측정","2020-12-02 09:00","2020-12-02 18:00","2020-12-02 09:00","2020-12-02 18:00","연속"]
[72,"경기북부","구리","포천S/S 154kV #1 BUS","포천S/S BUS-TIE 이설공사","이설 BUS-TIE GIS #1BUS 연결 및 CVT 이설","2020-12-10 09:00","2020-12-11 18:00","2020-12-10 09:00","2020-12-11 18:00","연속"]
[73,"경기북부","구리","포천S/S 154kV #2 BUS","포천S/S BUS-TIE 이설공사","이설 GIS #2BUS 연결 및 CVT 이설","2020-12-07 09:00","2020-12-08 18:00","2020-12-07 09:00","2020-12-08 18:00","연속"]
[74,"경기북부","직할","양주녹양#2 T/L","20-21년 가공송전 정비회사 총액공사","ㅇ 수평수직구명줄 설치","2020-12-04 07:00","2020-12-05 18:00","2020-12-04 07:00","2020-12-05 18:00","연속"]
[75,"경기북부","직할","양주녹양#1 T/L","20-21년 가공송전 정비회사 총액공사","ㅇ 수평수직구명줄 설치","2020-12-01 07:00","2020-12-02 18:00","2020-12-01 07:00","2020-12-02 18:00","연속"]
[76,"경기북부","직할","양주S/S 154kV #60 BUS","양주S/S 154kV 인출T/L 지중화공사","상시험 및 무부하가압용","2020-12-07 09:00","2020-12-08 18:00","2020-12-07 09:00","2020-12-08 18:00","연속"]
[77,"경기북부","직할","양주S/S 154kV #61 BUS","양주S/S 154kV 인출T/L 지중화공사","상시험 및 무부하가압용","2020-12-07 09:00","2020-12-08 18:00","2020-12-07 09:00","2020-12-08 18:00","연속"]
[78,"경기","군포","서서울율전#2 T/L","154kV 서서울-율전T/L 5,6호 안전이격확보공사","- 철탑 교체 : 2기 / 전선교체 : 4~6호간","2020-12-05 08:00","2020-12-07 18:00","2020-12-05 08:00","2020-12-07 18:00","연속"]
[79,"경기","군포","서서울#2일동#1 T/L","154kV 북안산분기T/L OPGW 시설공사","가. 공사장소 : 일동S/S~북안산S/S~원곡S/S 나. 시설내역 - OPGW 100㎟ 48C 14.534㎞ 시설 - 비금속광케이블(FOFC) 48C 0.468㎞ 시설","2020-12-04 00:07","2020-12-05 18:00","2020-12-13 07:00","2020-12-13 18:00","연속"]
[80,"경기","군포","수촌조암#2 T/L","'20년 OPGW 금구류 및 항공장애표시구 정비공사","154kV 수촌-조암#2T/L No.31-32 항공구 정비","2020-12-10 09:00","2020-12-10 18:00","취소","취소","연속"]
[81,"경기","동부","곤지암이천#2 T/L","20년 동부변전정비회사 총액공사","곤지암:곤지암-이천#2T/L(보통) LA(보통) 이천:곤지암-이천#2T/L(보통) LA(초기)","2020-12-05 09:00","2020-12-05 18:00","취소","취소","연속"]
[82,"경기","동부","오포모현#1 T/L","20년 동부변전정비회사 총액공사","오포:오포-모현#1T/L보호반대체(~7) 모현:오포-모현#1T/L보호반대체(~7) 제어모듈교체","2020-12-05 09:00","2020-12-07 18:00","2020-12-05 09:00","2020-12-07 18:00","연속"]
[83,"경기","동부","곤지암초월#1 T/L","20년 동부변전정비회사 총액공사","초월:곤지암-초월#1T/L GIS전자변교체(H)","2020-12-01 09:00","2020-12-01 18:00","2020-12-01 09:00","2020-12-01 18:00","연속"]
[84,"경기","성남","용인남사#1 T/L","20-21년 직할 송전정비회사 총액공사","국산불량애자교체 14호 60ea","2020-12-04 09:00","2020-12-04 12:00","2020-12-05 07:00","2020-12-05 10:00","연속"]
[85,"경기","성남","용인남사#2 T/L","20-21년 직할 송전정비회사 총액공사","국산불량애자교체 14호 20ea","2020-12-04 12:00","2020-12-04 18:00","2020-12-05 10:00","2020-12-05 12:00","연속"]
[86,"경기","직할","발안구문천#2 T/L","20년 직할 변전정비회사 총액공사","구문천 : 발안-구문천 #2T/L 보통 발안 : 발안-구문천 #2T/L 보통","2020-12-02 09:00","2020-12-02 18:00","취소","취소","연속"]
[87,"경기","직할","발안구문천#1 T/L","20년 직할 변전정비회사 총액공사","구문천 : 발안-구문천 #1T/L 보통 발안 : 발안-구문천 #1T/L 보통","2020-12-01 09:00","2020-12-01 18:00","취소","취소","연속"]
[88,"경기","직할","남수원발안#1 T/L","154kV 발안S/S #5M.Tr 증설공사","154kV 발안S/S #5M.Tr 무부하 가압","2020-12-14 09:00","2020-12-15 18:00","2020-12-14 09:00","2020-12-15 18:00","연속"]
[89,"경기","직할","서수원율전#2 T/L","20-21년 직할 송전정비회사 총액공사","국산불량애자교체 3호 20ea","2020-12-05 12:00","2020-12-05 18:00","2020-12-05 15:00","2020-12-05 18:00","연속"]
[90,"경기","직할","서서울서수원#1 T/L","20-21년 직할 송전정비회사 총액공사","서수원율전TL 국산불량애자교체공사 안전이격거리확보","2020-12-05 12:00","2020-12-05 18:00","2020-12-05 13:00","2020-12-05 15:00","연속"]
[91,"경기","직할","서수원율전#1 T/L","20-21년 직할 송전정비회사 총액공사","국산불량애자교체 1호 20ea","2020-12-05 09:00","2020-12-05 12:00","2020-12-05 15:00","2020-12-05 18:00","연속"]
[92,"경기","직할","화성수촌#2 T/L","154kV 화성-발안T/L OPGW 증설공사(96C_시범사업)","* 화성S/T ~ No.10(10)간 OP-S-L48→96 교체 2.467km * No.10(10) ~ CH.18간 OP-S-L24→48 교체 2.125km * 화성S/S ICT실 ~ 화성S/T FOFC 교체(48→96C) 0.390km * 발안S/S ICT실 ~ CH.18 FOFC 증설(24→48C) 3.193km * 접속, 최종시험 및 기타 부","2020-12-04 07:00","2020-12-08 18:00","취소","취소","연속"]
[93,"경기","직할","화성발안#2 T/L","154kV 화성-발안T/L OPGW 증설공사(96C_시범사업)","* 화성S/T ~ No.10(10)간 OP-S-L48→96 교체 2.467km * No.10(10) ~ CH.18간 OP-S-L24→48 교체 2.125km * 화성S/S ICT실 ~ 화성S/T FOFC 교체(48→96C) 0.390km * 발안S/S ICT실 ~ CH.18 FOFC 증설(24→48C) 3.193km * 접속, 최종시험 및 기타 부","2020-12-04 07:00","2020-12-09 18:00","취소","취소","연속"]
[94,"경기","평택","서안성남사#2 T/L","20-21년 직할 송전정비회사 총액공사","용인남사TL 국산불량애자교체공사 안전이격거리확보","2020-12-04 12:00","2020-12-04 18:00","2020-12-05 07:00","2020-12-05 12:00","연속"]
[95,"경기","평택","서안성남사#1 T/L","20-21년 직할 송전정비회사 총액공사","용인남사TL 국산불량애자교체공사 안전이격거리확보","2020-12-04 09:00","2020-12-04 12:00","취소","취소","연속"]
[96,"경기","평택","서운삼죽 T/L","2020년 직할 가공송전선로 순시점검 위탁공사","현수애자 절연저항측정 (중각도 철탑 2기)","2020-12-03 09:00","2020-12-04 18:00","2020-12-03 09:00","2020-12-04 18:00","매일"]
[97,"경기","평택","소사벌안성 T/L","154kV 소사벌안성T/L EBA 해체점검","소사벌C/H 소사벌안성T/L EBA 해체점검 - 해체점검사유 : 절연유 분석결과 C2H2검출","2020-12-04 09:00","2020-12-07 18:00","취소","취소","연속"]
[98,"경기","평택","원정평택T/P#1 T/L","가공송전 순시점검 위탁공사","154kV 원정-평택화력T/L 운휴선로 정비공사 관련 초기점검 시행 - 작업구간 : S/T~No.7","2020-12-02 10:00","2020-12-02 13:00","취소","취소","연속"]
[99,"경기","평택","원정평택T/P#2 T/L","가공송전 순시점검 위탁공사","154kV 원정-평택화력T/L 운휴선로 정비공사 관련 초기점검 시행 - 작업구간 : S/T~No.7","2020-12-02 13:00","2020-12-02 16:00","취소","취소","연속"]
[100,"경기","평택","포승청북 T/L","20-2년도 평택전력지사 송전정비회사 총액공사","추락방지장치 설치","2020-12-04 08:00","2020-12-04 10:00","취소","취소","연속"]
[101,"경기","평택","만호청북#1 T/L","20-2년도 평택전력지사 송전정비회사 총액공사","추락방지장치 설치","2020-12-04 10:00","2020-12-04 17:00","취소","취소","연속"]
[102,"경기","평택","평택TP평택CC#2 T/L","평택C/C 154kV 평택복합#2T/L GIS Air 누기보수","평택C/C 154kV 평택복합#2T/L GIS Air 누기보수","2020-12-01 10:00","2020-12-01 18:00","2020-12-01 10:00","2020-12-01 18:00","연속"]
[103,"경기","동부","가남여주 T/L","154kV 감곡S/S 인출 송전선로 계통정비공사","154kV 감곡S/S 인출 송전선로 계통정비공사","2020-12-02 07:00","2020-12-09 18:00","2020-12-02 07:00","2020-12-09 18:00","연속"]
[104,"강원","동해","울진삼척GP#1 T/L","삼척GP 스페이서 누기 관련 보수공사","삼척GP 스페이서 누기 관련 보수공사","2020-12-01 09:00","2020-12-08 18:00","취소","취소","연속"]
[105,"강원","직할","화천화천HP#1 T/L","2020~2021년 강원직할 송전정비회사 총액공사","불량애자 교체 7기","2020-12-01 09:00","2020-12-02 18:00","취소","취소","연속"]
[106,"강원","직할","양구화천HP#1 T/L","화천HP 보호배전반 이설 및 교체공사","화천HP 현대화에 따른 보호배전반 이설 및 교체공사","2020-12-02 09:00","2020-12-04 18:00","2020-12-02 09:00","2020-12-04 18:00","연속"]
[107,"강원","강릉","영동T/P 154kV #1 BUS","2020년 변전협력회사 총액공사","영동TP FGD #1BUS 전위변성기 보통점검","2020-12-02 10:00","2020-12-02 18:00","2020-12-02 10:00","2020-12-02 18:00","연속"]
[108,"강원","직할","화천화천HP#2 T/L","2020~2021년 강원직할 송전정비회사 총액공사","불량애자 교체 7기","2020-12-03 09:00","2020-12-04 18:00","2020-12-03 09:00","2020-12-04 18:00","연속"]
[109,"강원","직할","홍천남춘천 T/L","2020년 하반기 장기 미동작 차단기 조작시험","남춘천S/S 154kV 홍천-남춘천 T/L 차단기 조작시험","2020-12-03 10:00","2020-12-03 14:00","취소","취소","연속"]
[110,"강원","직할","양구화천HP#2 T/L","화천HP 보호배전반 이설 및 교체공사","화천HP 현대화에 따른 보호배전반 이설 및 교체공사","2020-12-06 09:00","2020-12-08 18:00","2020-12-06 09:00","2020-12-08 18:00","연속"]
[111,"강원","직할","화천화천HP#1 T/L","화천HP 보호배전반 이설 및 교체공사","화천HP 현대화에 따른 보호배전반 이설 및 교체공사","2020-12-07 09:00","2020-12-09 18:00","취소","취소","연속"]
[112,"강원","직할","화천화천HP#2 T/L","화천HP 보호배전반 이설 및 교체공사","화천HP 현대화에 따른 보호배전반 이설 및 교체공사","2020-12-09 09:00","2020-12-11 18:00","2020-12-09 09:00","2020-12-11 18:00","연속"]
[113,"강원","동해","동해T/P 154kV #1 BUS","동해화력S/Y 장기사용 170kV GIS 대체공사","- 동해화력S/Y 장기사용 170kV GIS 6CCT대체 - 동해화력S/Y 부분디지털화 공사","2020-12-07 09:00","2020-12-12 18:00","2020-12-08 18:00","2020-12-14 17:00","연속"]
[114,"강원","원주","횡성홍천#2 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","ㅇ 횡성홍천#1T/L 월부싱교체 안전이격확보","2020-12-08 08:00","2020-12-09 18:00","2020-12-08 08:00","2020-12-09 18:00","연속"]
[115,"강원","동해","태백삼척GP#2 T/L","삼척GP 스페이서 누기 관련 보수공사","삼척GP 스페이서 누기 관련 보수공사","2020-12-09 09:00","2020-12-16 18:00","2020-12-09 09:00","2020-12-16 18:00","연속"]
[116,"강원","강릉","강릉횡계#1 T/L","2020년 170kV GIS 하자점검","○ 2020년 170kV GIS 하자점검 : 강릉S/S 강릉-횡계#1T/L ○ 2020년 장기미동작 차단기 조작시험 : 횡계S/S 강릉횡계#1T/L","2020-12-10 10:00","2020-12-10 18:00","2020-12-10 10:00","2020-12-10 18:00","연속"]
[117,"강원","직할","북춘천화천HP T/L","화천HP 보호배전반 이설 및 교체공사","화천HP 현대화에 따른 보호배전반 이설 및 교체공사","2020-12-16 09:00","2020-12-18 18:00","취소","취소","연속"]
[118,"강원","직할","가평화천HP T/L","화천HP 보호배전반 이설 및 교체공사","화천HP 현대화에 따른 보호배전반 이설 및 교체공사","2020-12-20 09:00","2020-12-22 18:00","2020-12-20 09:00","2020-12-22 18:00","연속"]
[119,"강원","원주","북원주횡성#1 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","ㅇ 170kV 장기사용 GIS 철거/설치 ㅇ 디지털화공사 케이블 철거 및 광케이블 포설 ㅇ SA 운영장치 시험","2020-12-21 08:00","2021-01-08 18:00","취소","취소","연속"]
[120,"강원","원주","북원주횡성#2 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","ㅇ 북원주-횡성#1T/L 월부싱철거/설치 안전이격 확보","2020-12-22 08:00","2020-12-22 18:00","취소","취소","연속"]
[121,"강원","직할","화천H/P 154kV #1 BUS","화천HP 보호배전반 이설 및 교체공사","화천HP 현대화에 따른 보호배전반 이설 및 교체공사","2020-12-23 09:00","2020-12-24 09:00","2020-12-23 09:00","2020-12-24 09:00","연속"]
[122,"강원","직할","화천H/P 154kV #2 BUS","화천HP 보호배전반 이설 및 교체공사","화천HP 현대화에 따른 보호배전반 이설 및 교체공사","2020-12-24 09:00","2020-12-24 18:00","2020-12-24 09:00","2020-12-24 18:00","연속"]
[123,"충북","직할","서운광혜원 T/L","2020년 직할 가공송전선로 순시점검 위탁공사","현수애자 절연저항측정 (중각도 철탑 2기)","2020-12-01 09:00","2020-12-01 18:00","취소","취소","매일"]
[124,"충북","직할","진천광혜원#2 T/L","2020년 직할 가공송전선로 순시점검 위탁공사","현수애자 절연저항측정 (중각도 철탑 1기)","2020-12-02 09:00","2020-12-02 18:00","취소","취소","매일"]
[125,"충북","직할","신진천진천#2 T/L","20~21년도 직할 변전정비회사 총액공사","신진천S/S 신진천-진천#2T/L GIS 보통점검 및 LA 하자점검 진천S/S 신진천-진천#2T/L LA 보통점검","2020-12-01 10:00","2020-12-01 18:00","취소","취소","연속"]
[126,"충북","청주","옥천보은 T/L","154kV 보은S/S #4M.Tr 대체공사","154/22.9kV 15/20MVA * 3상 설치","2020-12-21 09:00","2020-12-22 09:00","취소","취소","연속"]
[127,"충북","청주","북청주봉명#2 T/L","20년 하반기 청주전력지사 170kV GIS 정밀점검공사","북청주봉명#2T/L GIS 정밀점검","2020-12-05 09:00","2020-12-06 18:00","취소","취소","연속"]
[128,"충북","청주","남청주오송#2 T/L","154kV 오송-북청주 등 2개T/L EBA PD단자 집합반 설치공사","EBA PD단자 집합반 설치","2020-12-06 09:00","2020-12-06 18:00","2020-12-06 09:00","2020-12-06 18:00","연속"]
[129,"충북","청주","남청주오송#1 T/L","154kV 오송-북청주 등 2개T/L EBA PD단자 집합반 설치공사","EBA PD단자 집합반 설치","2020-12-05 09:00","2020-12-05 18:00","2020-12-05 09:00","2020-12-05 18:00","연속"]
[130,"충북","충주","왕암여주#2 T/L","154kV 왕암-가남T/L 안전이격확보공사","본탑(No.112,113,114)조립 및 전력선 가선(#2T/L측)","2020-12-21 08:00","2020-12-26 18:00","취소","취소","연속"]
[131,"충북","충주","왕암여주#1 T/L","154kV 왕암-가남T/L 안전이격확보공사","본탑(No.112,113,114)조립 및 전력선 가선(#1T/L측)","2020-12-13 08:00","2020-12-20 18:00","취소","취소","연속"]
[132,"충북","충주","왕암여주#1 T/L","154kV 감곡S/S 인출 송전선로 계통정비공사","설치 4기(2회선 1, 4회선 3), 철거 4기, 선로길이 4.761C-km 154㎸ 감곡-여주T/L(신충주-감곡T/L 병가) №2～5간(№3,4 교체) 154㎸ 왕암-가남T/L №135～138간(№136,137 교체)","2020-12-10 07:00","2020-12-12 18:00","2020-12-12 07:00","2020-12-14 18:00","연속"]
[133,"충북","충주","신충주감곡#1 T/L","154kV 감곡S/S 인출 송전선로 계통정비공사","설치 4기(2회선 1, 4회선 3), 철거 4기, 선로길이 4.761C-km 154㎸ 감곡-여주T/L(신충주-감곡T/L 병가) №2～5간(№3,4 교체) 154㎸ 왕암-가남T/L №135～138간(№136,137 교체)","2020-12-10 07:00","2020-12-12 18:00","2020-12-12 07:00","2020-12-14 18:00","연속"]
[134,"충북","충주","신충주감곡#2 T/L","154kV 감곡S/S 인출 송전선로 계통정비공사","설치 4기(2회선 1, 4회선 3), 철거 4기, 선로길이 4.761C-km 154㎸ 감곡-여주T/L(신충주-감곡T/L 병가) №2～5간(№3,4 교체) 154㎸ 왕암-가남T/L №135～138간(№136,137 교체)","2020-12-02 07:00","2020-12-09 18:00","2020-12-04 07:00","2020-12-11 18:00","연속"]
[135,"대전충남","서산","대산석문#1 T/L","대산S/S 154kV 현대케미칼#1,2T/L GIS 설치공사","대산S/S 154kV 현대케미칼#1,2T/L GIS 설치공사(안전이격확보)","2020-12-11 08:00","2020-12-12 18:00","취소","취소","매일"]
[136,"대전충남","서산","대산석문#1 T/L","대산S/S 154kV 현대케미칼#1,2T/L GIS 설치공사","대산S/S 154kV 현대케미칼#1,2T/L GIS 설치공사(안전이격확보)","2020-12-05 08:00","2020-12-06 18:00","취소","취소","매일"]
[137,"대전충남","아산","신온양한샘#2 T/L","신온양,한샘S/S 신온양-한샘#2T/L 보호배전반 교체","신온양,한샘S/S 신온양-한샘#2T/L 보호배전반 교체","2020-12-01 09:00","2020-12-04 18:00","취소","취소","연속"]
[138,"대전충남","아산","아산인주#1 T/L","345kV북당진-신탕정T/L 건설공사","No.47 ~ 48 가선공사 - 아산인주#1,#2T/L 횡단을 위한 보호망 설치(양회선 휴전 3시간)","2020-12-25 08:00","2020-12-25 11:00","취소","취소","연속"]
[139,"대전충남","아산","아산인주#2 T/L","345kV북당진-신탕정T/L 건설공사","No.47 ~ 48 가선공사 - 아산인주#1,#2T/L 횡단을 위한 보호망 설치(양회선 휴전 3시간)","2020-12-25 08:00","2020-12-25 11:00","취소","취소","연속"]
[140,"대전충남","아산","인주탕정#1 T/L","345kV북당진-신탕정T/L 건설공사","No.47 ~ 48 가선공사 - 아산인주#1,#2T/L 횡단을 위한 보호망 설치(양회선 휴전 3시간)","2020-12-25 14:00","2020-12-25 17:00","취소","취소","연속"]
[141,"대전충남","아산","인주탕정#2 T/L","345kV북당진-신탕정T/L 건설공사","No.47 ~ 48 가선공사 - 아산인주#1,#2T/L 횡단을 위한 보호망 설치(양회선 휴전 3시간)","2020-12-25 14:00","2020-12-25 17:00","취소","취소","연속"]
[142,"대전충남","아산","서천안탕정#2 T/L","154kV 인주-불당T/L C/H 건설공사","154kV 인주-불당T/L C/H 건설공사 - 임시선로 철거 및 본선로 구성","2020-12-18 07:00","2020-12-24 18:00","2020-12-18 07:00","2020-12-24 18:00","연속"]
[143,"대전충남","아산","인주탕정#1 T/L","154kV 인주-불당T/L C/H 건설공사","154kV 인주-불당T/L C/H 건설공사 - 임시선로 철거 및 본선로 구성","2020-12-18 07:00","2020-12-24 18:00","취소","취소","연속"]
[144,"대전충남","아산","인주탕정#2 T/L","154kV 인주-불당T/L C/H 건설공사","154kV 인주-불당T/L C/H 건설공사 - 임시선로 철거 및 본선로 구성","2020-12-25 07:00","2020-12-31 18:00","취소","취소","연속"]
[145,"대전충남","아산","서천안탕정#1 T/L","154kV 인주-불당T/L C/H 건설공사","154kV 인주-불당T/L C/H 건설공사 - 임시선로 철거 및 본선로 구성","2020-12-25 07:00","2020-12-31 18:00","2020-12-25 07:00","2020-12-31 18:00","연속"]
[146,"대전충남","아산","한샘둔포#1 T/L","154kV 직산분기T/L 건설공사","154kV 한샘-둔포T/L 15,17호 ~ 신설 직산S/S (직산S/S 관련 가철탑 설치)","2020-12-11 07:00","2020-12-17 18:00","2020-12-11 07:00","2020-12-17 18:00","연속"]
[147,"대전충남","아산","한샘둔포#2 T/L","154kV 직산분기T/L 건설공사","154kV 한샘-둔포T/L 15,17호 ~ 신설 직산S/S (직산S/S 관련 가철탑 설치)","2020-12-18 07:00","2020-12-24 18:00","2020-12-18 07:00","2020-12-24 18:00","연속"]
[148,"대전충남","직할","부강신탄진 T/L","154kV 부강-신탄진T/L 송전전로보호반 성능개선","154kV 부강-신탄진T/L 송전전로보호반 성능개선","2020-12-10 09:00","2020-12-10 18:00","취소","취소","연속"]
[149,"대전충남","서산","신당진서산#2 T/L","154kV 서산S/S DS 이음관련 보수","154kV 서산S/S DS 이음관련 보수","2020-12-08 10:00","2020-12-09 18:00","취소","취소","연속"]
[150,"전북","군산","군산S/S 154kV CB 6300","'20년 군산P/O 공압식차단기 전자변 교체공사","- 군산S/S 154kV #62-#67 BUS TIE GIS 전자변 교체","2020-12-18 09:00","2020-12-18 14:00","2020-12-18 09:00","2020-12-18 14:00","연속"]
[151,"전북","군산","군산서군산#2 T/L","154kV군산-서군산T/L 전선정비 공사","154kV군산-서군산T/L 전선 오염제거","2020-12-02 09:00","2020-12-02 18:00","취소","취소","연속"]
[152,"전북","군산","군산서군산#1 T/L","154kV군산-서군산T/L 전선정비 공사","154kV군산-서군산T/L 전선 오염제거","2020-12-01 09:00","2020-12-01 18:00","취소","취소","연속"]
[153,"전북","군산","내초군장#2 T/L","154kV 군장S/S SMG에너지T/L 신규수용공사(무부하가압)","170kV GIS X 1CCT","2020-12-07 14:00","2020-12-08 14:00","2020-12-10 14:00","2020-12-11 14:00","연속"]
[154,"전북","군산","내초군장#1 T/L","154kV 군장S/S SMG에너지T/L 신규수용공사(무부하가압)","170kV GIS X 1CCT","2020-12-07 10:00","2020-12-07 14:00","2020-12-10 10:00","2020-12-10 14:00","연속"]
[155,"전북","군산","내초군장#2 T/L","내초S/S #3M.Tr 부분방전 해소공사 무부하 가압","- 내초S/S #3M.Tr 부분방전 해소 내부점검 후 무부하 가압","2020-12-12 09:00","2020-12-12 18:00","2020-12-12 09:00","2020-12-12 18:00","연속"]
[156,"전북","군산","새만금소룡#1 T/L","154kV 새만금-소룡T/L 리콜 접속함 교체공사","리콜(하자) R타입 PMJ 접속함 23상 교체공사","2020-12-14 09:00","2020-12-30 18:00","취소","취소","연속"]
[157,"전북","군산","새만금소룡#2 T/L","154kV 새만금-소룡T/L 리콜 접속함 교체공사","리콜(하자) R타입 PMJ 접속함 23상 교체공사","2020-12-31 09:00","2021-01-15 18:00","취소","취소","연속"]
[158,"전북","군산","새만금소룡#2 T/L","154kV 새만금-소룡T/L 리콜 접속함 교체공사(양회선 동시휴전용)","리콜(하자) R타입 PMJ 접속함 23상 교체공사(토목작업)","2020-12-14 09:00","2020-12-18 18:00","취소","취소","연속"]
[159,"전북","군산","서군산소룡#2 T/L","군산P/O 기타변전설비 점검공사","- 6232 DS 점검","2020-12-01 10:00","2020-12-01 18:00","2020-12-04 10:00","2020-12-04 18:00","연속"]
[160,"전북","김제","백산김제#2 T/L","추락방지 시설장치 설치공사","추락방지시설 백산-김제 24호 설치공사","2020-12-04 09:00","2020-12-04 18:00","취소","취소","연속"]
[161,"전북","김제","백산김제#1 T/L","추락방지 시설장치 설치공사","추락방지시설 백산-김제 24호 설치공사","2020-12-03 09:00","2020-12-03 18:00","취소","취소","연속"]
[162,"전북","김제","신김제S/S 154kV SEC CB 65660","신김제S/S 노후 170GIS 교체 및 인출송전 재배열 공사","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-12-02 09:00","2020-12-23 18:00","2020-12-09 09:00","2020-12-23 18:00","연속"]
[163,"전북","김제","신김제S/S 154kV #60 BUS","신김제S/S 노후 170GIS 교체 (신김제동전주#1 무부하가압시 필요)","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-12-01 09:00","2020-12-02 09:00","2020-12-08 09:00","2020-12-09 09:00","연속"]
[164,"전북","김제","신김제S/S 154kV CB 6100","신김제S/S 노후 170GIS 교체 (신김제동전주#1 무부하가압시 필요)","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-12-01 09:00","2020-12-02 09:00","2020-12-08 09:00","2020-12-09 09:00","연속"]
[165,"전북","김제","신김제동전주#1 T/L","신김제S/S 노후 170GIS 교체공사  (무부하가압)","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-12-01 09:00","2020-12-02 09:00","2020-12-08 09:00","2020-12-09 09:00","연속"]
[166,"전북","김제","신김제S/S 154kV SEC CB 60610","신김제S/S 노후 170GIS 교체 (신김제동전주#1 무부하가압시 필요)","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-12-01 09:00","2020-12-02 09:00","2020-12-08 09:00","2020-12-09 09:00","연속"]
[167,"전북","김제","신김제남전주#1 T/L","신김제S/S 노후 170GIS 교체공사 (선로이설 인출변경) ","송전선로 인출 BAY 조정( 657 CB 남전주#1 =>687 CB로 이동)","2020-12-14 18:00","2020-12-24 18:00","취소","취소","연속"]
[168,"전북","김제","신김제S/S 154kV CB 6100","신김제S/S 노후 170GIS 교체 및 인출송전 재배열 공사  (무부하가압)","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-12-24 12:00","2020-12-24 18:00","2020-12-24 12:00","2020-12-24 18:00","연속"]
[169,"전북","김제","신김제S/S 154kV #60 BUS","신김제S/S 노후 170GIS 교체 및 인출송전 재배열 공사  (무부하가압)","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-12-24 12:00","2020-12-24 18:00","2020-12-24 12:00","2020-12-24 18:00","연속"]
[170,"전북","김제","신김제S/S 154kV #66 BUS","신김제S/S 노후 170GIS 교체 및 인출송전 재배열 공사","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-12-02 09:00","2020-12-23 18:00","2020-12-09 09:00","2020-12-23 18:00","연속"]
[171,"전북","김제","신김제S/S 154kV SEC CB 61620","신김제S/S 노후 170GIS 교체 및 인출송전 재배열 공사 (무부하가압)","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-12-24 09:00","2020-12-24 12:00","2020-12-24 09:00","2020-12-24 12:00","연속"]
[172,"전북","김제","신김제S/S 154kV SEC CB 60610","신김제S/S 노후 170GIS 교체 및 인출송전 재배열 공사  (무부하가압)","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-12-24 09:00","2020-12-24 18:00","2020-12-24 09:00","2020-12-24 18:00","연속"]
[173,"전북","김제","신김제S/S 154kV #61 BUS","신김제S/S 노후 170GIS 교체 및 인출송전 재배열 공사  (무부하가압)","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-12-24 09:00","2020-12-24 12:00","2020-12-24 09:00","2020-12-24 12:00","연속"]
[174,"전북","김제","신김제남전주#1 T/L","신김제S/S 노후 170GIS 교체공사 (무부하가압)","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-12-01 09:00","2020-12-02 09:00","취소","취소","연속"]
[175,"전북","김제","신김제S/S 154kV SEC CB 66670","신김제S/S 노후 170GIS 교체 및 인출송전 재배열 공사","- 장기사용 노후 170GIS 교체공사 - 송전선로 인출 BAY 조정 - 기타 부대공사 1식","2020-12-02 09:00","2020-12-23 18:00","2020-12-09 09:00","2020-12-23 18:00","연속"]
[176,"전북","김제","정공칠보HP T/L","정공S/S SA혼용시스템 설치공사","정공S/S SA혼용시스템 설치공사 (케이블 이설)","2020-12-07 09:00","2020-12-08 18:00","2020-12-07 09:00","2020-12-08 18:00","연속"]
[177,"전북","김제","정공담양 T/L","정공S/S SA혼용시스템 설치공사","정공S/S SA혼용시스템 설치공사 (케이블 이설)","2020-12-01 09:00","2020-12-02 18:00","2020-12-01 09:00","2020-12-02 18:00","연속"]
[178,"전북","김제","정주부안#2 T/L","송전철탑 추락방지시설 설치공사","정주-고창 4호 추락방지시설장치 설치","2020-12-02 09:00","2020-12-02 18:00","2020-12-02 09:00","2020-12-02 18:00","연속"]
[179,"전북","김제","정주고창#2 T/L","송전철탑 추락방지시설 설치공사","정주-고창 4호 추락방지시설장치 설치","2020-12-02 09:00","2020-12-02 18:00","2020-12-02 09:00","2020-12-02 18:00","연속"]
[180,"전북","김제","정주부안#1 T/L","송전철탑 추락방지시설 설치공사","정주-고창 4호 추락방지시설장치 설치","2020-12-01 09:00","2020-12-01 18:00","2020-12-01 09:00","2020-12-01 18:00","연속"]
[181,"전북","김제","정주고창#1 T/L","송전철탑 추락방지시설 설치공사","정주-고창 4호 추락방지시설장치 설치","2020-12-01 09:00","2020-12-01 18:00","2020-12-01 09:00","2020-12-01 18:00","연속"]
[182,"전북","직할","남원임실#2 T/L","154kV 남원S/S 옥외철구설비 GIS화 공사","○ 154kV 남원-임실#2T/L 인출구간 변경 및 GIS설비로 이전","2020-12-28 08:00","2021-01-16 18:00","2020-12-28 08:00","2021-01-16 18:00","연속"]
[183,"전북","직할","신남원남원#1 T/L","154kV 남원S/S 옥외철구설비 GIS화 공사","○ 154kV 신남원-남원#1T/L 인출구간 변경 및 GIS설비로 이전","2020-12-28 08:00","2021-01-16 18:00","2020-12-28 08:00","2021-01-16 18:00","연속"]
[184,"전북","직할","금산무주#1 T/L","무주S/S 154kV GIS 교체공사(Main 교체)","- 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2020-12-08 10:00","2021-01-27 15:00","취소","취소","연속"]
[185,"전북","직할","무주S/S 154kV #1 BUS","무주S/S 170kV 장기사용 GIS 교체공사","무주S/S 170kV 장기사용 GIS 교체공사 (#1 BUS)","2020-12-24 15:00","2021-01-14 15:00","취소","취소","연속"]
[186,"전북","직할","무주S/S 154kV #2 BUS","무주S/S 154kV GIS 교체공사(전문)"," 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT) (#2 BUS)","2020-12-08 10:00","2020-12-24 15:00","취소","취소","연속"]
[187,"전북","직할","무주용담수력 T/L","무주S/S 154kV GIS 교체공사(전문) (무부하가압)","*** 154kV #60BUS 무부하 가압 선로 - 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2020-12-01 15:00","2020-12-02 15:00","2020-12-01 15:00","2020-12-02 15:00","연속"]
[188,"전북","직할","무주S/S 154kV CB 6100","무주S/S 154kV GIS 교체공사(Main 교체)","- 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2020-12-08 10:00","2021-01-27 15:00","취소","취소","연속"]
[189,"전북","직할","무주용담수력 T/L","무주S/S 154kV GIS 교체공사(전문) (무부하가압)","*** 154kV #60BUS 무부하 가압 선로 - 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2020-12-23 15:00","2020-12-24 15:00","취소","취소","연속"]
[190,"전북","직할","북전주진안 T/L","OPGW 항공구 시설공사","북전주-진안T/L 미설치 항공구 시설공사","2020-12-11 08:00","2020-12-11 17:00","2020-12-11 08:00","2020-12-11 17:00","연속"]
[191,"전북","직할","무주진안 T/L","OPGW 항공구 시설공사","무주-진안T/L 미설치 항공구 시설공사","2020-12-10 08:00","2020-12-10 17:00","2020-12-10 08:00","2020-12-10 17:00","연속"]
[192,"전북","군산","군공군산CC#1 T/L","지중 송전선로 절연유 채유공사","지중 송전선로 절연유 채유공사","2020-12-07 09:00","2020-12-08 18:00","취소","취소","연속"]
[193,"전북","군산","군공군산CC#2 T/L","지중 송전선로 절연유 채유공사","지중 송전선로 절연유 채유공사","2020-12-09 09:00","2020-12-10 18:00","취소","취소","연속"]
[194,"전북","군산","군공내초#1 T/L","지중 송전선로 절연유 채유공사","지중 송전선로 절연유 채유공사","2020-12-05 09:00","2020-12-05 18:00","취소","취소","연속"]
[195,"전북","군산","군공내초#2 T/L","지중 송전선로 절연유 채유공사","지중 송전선로 절연유 채유공사","2020-12-12 09:00","2020-12-12 18:00","취소","취소","연속"]
[196,"광주전남","강진","신강진대불#2 T/L","20-21년 강진전력지사 변전정비회사 총액공사","신강진, 대불S/S 신강진-대불#2T/L 보호반 대체","2020-12-02 09:00","2020-12-04 18:00","취소","취소","연속"]
[197,"광주전남","광주","신광주곡성#2 T/L","154kV 순창분기T/L 건설공사","구 간 : (기설) 154kV 신광주-곡성TL No.75,77 ~ (신설) C/H - 본선로 구성 : 가철탑 철거 및 전선 이동, 1호 설치, 1-2호 연선 및 긴선 등","2020-12-07 08:00","2020-12-30 18:00","취소","취소","연속"]
[198,"광주전남","광주","충장농성#2 T/L","OF케이블 절연유 채유","충장-농성#2 T/L OF케이블 절연유 채유","2020-12-08 09:00","2020-12-08 18:00","취소","취소","연속"]
[199,"광주전남","광주","충장농성#1 T/L","OF케이블 절연유 채유","충장-농성#1 T/L OF케이블 절연유 채유","2020-12-07 09:00","2020-12-07 18:00","취소","취소","연속"]
[200,"광주전남","목포","나주엄다#2 T/L","154kV 엄다-목포 T/L 아킹혼설치공사 4회선구간 안전이격확보","엄다-목포 T/L 아킹혼설치공사 4회선 구간 안전이격 확보 차 휴전","2020-12-10 08:00","2020-12-11 18:00","2020-12-10 08:00","2020-12-11 18:00","매일"]
[201,"광주전남","목포","장성영광#2 T/L","154kV 장성-영광T/L 안전이격확보공사","인크로징 2기, 철거 및 설치 1기","2020-12-21 08:00","2020-12-24 18:00","취소","취소","연속"]
[202,"광주전남","목포","장성영광#1 T/L","154kV 장성-영광T/L 안전이격확보공사","인크로징 2기, 철거 및 설치 1기","2020-12-15 08:00","2020-12-18 18:00","취소","취소","연속"]
[203,"광주전남","목포","영광홍농 T/L","공압식 차단기 조작시험(직영작업)","영광S/S 영광-홍농T/L 차단기 조작시험","2020-12-15 13:00","2020-12-15 15:00","2020-12-15 10:00","2020-12-15 18:00","연속"]
[204,"광주전남","순천","여수T/P 154kV SEC CB 60610","20-21년 변전정비회사 총액공사","여수화력 60-61, 65-66BUS-SEC GIS 보통점검","2020-12-04 09:00","2020-12-04 14:00","취소","취소","연속"]
[205,"광주전남","순천","여수T/P 154kV SEC CB 65660","20-21년 변전정비회사 총액공사","여수화력 60-61, 65-66BUS-SEC GIS 보통점검","2020-12-04 14:00","2020-12-04 18:00","취소","취소","연속"]
[206,"광주전남","순천","여수TP용성#1 T/L","20-21년 변전정비회사 총액공사","여화 여수TP-용성#1T/L GIS #2DS 댐퍼 교체","2020-12-21 09:00","2020-12-21 18:00","취소","취소","연속"]
[207,"광주전남","순천","여수T/P 154kV CB 6100","20-21년 변전정비회사 총액공사","여수화력 6100BUS-TIE GIS 보통점검","2020-12-03 09:00","2020-12-03 18:00","2020-12-01 09:00","2020-12-01 18:00","연속"]
[208,"광주전남","직할","남광주금천#1 T/L","금천S/S 154kV 남광주-금천 #1T/L(유사고장)","세니온제 154kV 송전선로 보호 IED 성능개선 시행 - 보호 IED 성능개선, 내부부품(콘덴서) 교체","2020-12-17 09:00","2020-12-17 14:00","2020-12-15 09:00","2020-12-15 14:00","연속"]
[209,"광주전남","직할","남광주금천#2 T/L","금천S/S 154kV 남광주-금천 #2T/L(유사고장)","세니온제 154kV 송전선로 보호 IED 성능개선 시행 - 보호 IED 성능개선, 내부부품(콘덴서) 교체","2020-12-17 14:00","2020-12-17 18:00","2020-12-15 14:00","2020-12-15 18:00","연속"]
[210,"광주전남","직할","나주금천#2 T/L","금천S/S 154kV 나주-금천 #2T/L(유사고장)","세니온제 154kV 송전선로 보호 IED 성능개선 시행 - 보호 IED 성능개선, 내부부품(콘덴서) 교체","2020-12-14 14:00","2020-12-14 18:00","2020-12-14 14:00","2020-12-14 18:00","연속"]
[211,"광주전남","직할","나주금천#1 T/L","금천S/S 154kV 나주-금천 #1T/L(유사고장)","세니온제 154kV 송전선로 보호 IED 성능개선 시행 - 보호 IED 성능개선, 내부부품(콘덴서) 교체","2020-12-14 09:00","2020-12-14 14:00","2020-12-14 09:00","2020-12-14 14:00","연속"]
[212,"광주전남","직할","매월화정#1 T/L","'20~21년 직할 변전정비회사 총액공사(PNL 교체)","ㅇ 매월-화정#1T/L 보호반 교체","2020-12-14 09:00","2020-12-16 18:00","취소","취소","연속"]
[213,"광주전남","직할","수완흑석#1 T/L","수완S/S 154kV 수완-흑석 #1T/L(유사고장)","지중 송전선로 거리계전기 Zone1 오버리치 동작 우려 선로 로직 수정 - 제작사 입회 보호계전기 로직 수정 및 이면배선(회로보완)","2020-12-18 09:00","2020-12-18 14:00","2020-12-18 09:00","2020-12-18 14:00","연속"]
[214,"광주전남","직할","수완흑석#2 T/L","수완S/S 154kV 수완-흑석 #2T/L(유사고장)","지중 송전선로 거리계전기 Zone1 오버리치 동작 우려 선로 로직 수정 - 제작사 입회 보호계전기 로직 수정 및 이면배선(회로보완)","2020-12-18 14:00","2020-12-18 18:00","2020-12-18 14:00","2020-12-18 18:00","연속"]
[215,"광주전남","직할","왕곡나주#2 T/L","왕곡S/S 154kV 왕곡-나주 #2T/L(유사고장)","세니온제 154kV 송전선로 보호 IED 성능개선 시행 - 보호 IED 성능개선, 내부부품(콘덴서) 교체","2020-12-10 14:00","2020-12-10 18:00","2020-12-10 14:00","2020-12-10 18:00","연속"]
[216,"광주전남","직할","왕곡나주#1 T/L","왕곡S/S 154kV 왕곡-나주 #1T/L(유사고장)","세니온제 154kV 송전선로 보호 IED 성능개선 시행 - 보호 IED 성능개선, 내부부품(콘덴서) 교체","2020-12-10 09:00","2020-12-10 14:00","2020-12-10 09:00","2020-12-10 14:00","연속"]
[217,"광주전남","직할","평동왕곡#2 T/L","평동S/S 장기사용 GIS교체공사","보호배전반 IED 개조공사","2020-12-02 13:00","2020-12-03 18:00","2020-12-15 13:00","2020-12-16 18:00","연속"]
[218,"광주전남","직할","평동왕곡#1 T/L","평동S/S 장기사용 GIS교체공사","보호배전반 IED개조 공사","2020-12-01 09:00","2020-12-02 13:00","2020-12-14 09:00","2020-12-15 13:00","연속"]
[219,"광주전남","직할","하남장성#1 T/L","하남S/S 154kV 하남-장성 #1T/L(유사고장)","세니온제 154kV 송전선로 보호 IED 성능개선 시행 - 보호 IED 성능개선, 내부부품(콘덴서) 교체","2020-12-21 09:00","2020-12-21 14:00","취소","취소","연속"]
[220,"광주전남","직할","하남장성#2 T/L","하남S/S 154kV 하남-장성 #2T/L(유사고장)","세니온제 154kV 송전선로 보호 IED 성능개선 시행 - 보호 IED 성능개선, 내부부품(콘덴서) 교체","2020-12-15 14:00","2020-12-15 18:00","취소","취소","연속"]
[221,"대구","경산","대구범물#2 T/L","범물S/S 154kV GIS 디지털화 및 Sh.C 교체공사","송전선로 보호반 이설","2020-12-01 09:30","2020-12-02 18:00","취소","취소","연속"]
[222,"대구","경산","대구범물#1 T/L","범물S/S 154kV GIS 디지털화 및 Sh.C 교체공사","송전선로 보호반 이설","2020-12-07 09:30","2020-12-08 18:00","취소","취소","연속"]
[223,"대구","달성","고령S/S 154kV #65 BUS","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-12-19 18:00","2020-12-20 18:00","취소","취소","연속"]
[224,"대구","달성","고령S/S 154kV #66 BUS","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-12-19 17:00","2020-12-19 18:00","취소","취소","연속"]
[225,"대구","달성","고령S/S 154kV #61 BUS","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-12-25 17:00","2020-12-25 18:00","취소","취소","연속"]
[226,"대구","달성","고령쌍림#2 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-12-15 08:00","2020-12-21 18:00","취소","취소","연속"]
[227,"대구","달성","고령다산#2 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-12-15 08:00","2020-12-20 18:00","취소","취소","연속"]
[228,"대구","달성","고령다산#1 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-12-21 08:00","2020-12-26 18:00","취소","취소","연속"]
[229,"대구","달성","고령쌍림#1 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-12-21 08:00","2020-12-25 18:00","취소","취소","연속"]
[230,"대구","달성","고령S/S 154kV #60 BUS","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2020-12-25 18:00","2020-12-26 18:00","취소","취소","연속"]
[231,"대구","달성","달성상인#1 T/L","달성,상인S/S 달성-상인#1T/L GIS 보통점검","달성,상인S/S 달성-상인#1T/L GIS 보통점검","2020-12-04 09:00","2020-12-04 18:00","2020-12-04 09:00","2020-12-04 18:00","연속"]
[232,"대구","달성","고령쌍림#2 T/L","쌍림S/S 154kV 모선보호반 대체작업(TEST선로)","쌍림S/S 154kV 모선보호반 대체작업(TEST선로)","2020-12-11 16:00","2020-12-11 16:30","2020-12-11 16:00","2020-12-11 16:30","연속"]
[233,"대구","달성","쌍림합천#2 T/L","쌍림S/S 154kV 모선보호반 대체작업(TEST선로)","쌍림S/S 154kV 모선보호반 대체작업(TEST선로)","2020-12-11 14:00","2020-12-11 14:30","2020-12-11 14:00","2020-12-11 14:30","연속"]
[234,"대구","달성","쌍림합천#1 T/L","쌍림S/S 154kV 모선보호반 대체작업(TEST선로)","쌍림S/S 154kV 모선보호반 대체작업(TEST선로)","2020-12-11 14:30","2020-12-11 15:00","2020-12-11 14:30","2020-12-11 15:00","연속"]
[235,"대구","달성","고령쌍림#1 T/L","쌍림S/S 154kV 모선보호반 대체작업(TEST선로)","쌍림S/S 154kV 모선보호반 대체작업(TEST선로)","2020-12-11 15:00","2020-12-11 15:30","2020-12-11 15:00","2020-12-11 15:30","연속"]
[236,"대구","직할","동인내당#2 T/L","동인S/S 차단기 동작시간 측정","동인S/S 차단기 동작시간 측정","2020-12-31 14:00","2020-12-31 18:00","취소","취소","연속"]
[237,"대구","직할","동인내당#1 T/L","동인S/S 차단기 동작시간 측정","동인S/S 차단기 동작시간 측정","2020-12-31 09:30","2020-12-31 14:00","취소","취소","연속"]
[238,"대구","포항","포항경주 T/L","154kV 경주S/S 옥내화공사 최초가압","154kV 경주S/S 옥내화공사 최초가압","2020-12-07 09:00","2020-12-18 18:00","2020-12-07 09:00","2020-12-18 18:00","연속"]
[239,"대구","포항","천북경주인수 T/L","154kV 경주S/S 옥내화공사","154kV 경주S/S 옥내화공사 최초가압","2020-12-21 09:00","2020-12-29 18:00","2020-12-21 09:00","2020-12-29 18:00","연속"]
[240,"대구","포항","아화영천#2 T/L","아화-영천#1TL, 아화-영천#2TL(아화변전소 외장재 교체공사)","아화-영천#1TL, 아화-영천#2TL(아화변전소 외장재 교체공사)","2020-12-07 09:00","2020-12-12 18:00","2020-12-07 09:00","2020-12-12 18:00","매일"]
[241,"대구","포항","아화영천#1 T/L","아화-영천#1TL, 아화-영천#2TL(아화변전소 외장재 교체공사)","아화-영천#1TL, 아화-영천#2TL(아화변전소 외장재 교체공사)","2020-12-10 09:00","2020-12-15 18:00","2020-12-10 09:00","2020-12-15 18:00","매일"]
[242,"경북","구미","남인동인동#2 T/L","남인동S/S 170kV GIS교체공사[4차수]","- 서대구-남인동#1T/L(617) GIS교체 - 에스아이엘T/L(627) GIS철거 - 무부하가압용 선로(즉시가압 가능)","2020-12-04 18:00","2020-12-07 09:00","2020-12-04 18:00","2020-12-07 09:00","연속"]
[243,"경북","직할","안동풍산 T/L","154kV 안동-풍산등 2개T/L 지장송전선로 임시이설공사","○ 공사구간 : 154kV 안동-풍산T/L No.59~64 ○ 지지물 설치 3기, 철거 4기 ○ 전력선 HSTACIR/AW 240㎟ × S, ACSR 410㎟ × S, 0.971km","2020-12-07 07:00","2020-12-12 18:00","2020-12-07 07:00","2020-12-12 18:00","연속"]
[244,"부산울산","동부산","신양산구서#2 T/L","`20~21년도 가공송전 정비회사 총액공사(동부산)","○애자교체 공사 - 2, 4, 10, 22, 37호 ○ 추락방지장치 설치공사 - 21, 22, 40호","2020-12-07 08:00","2020-12-09 18:00","취소","취소","연속"]
[245,"부산울산","동부산","신양산구서#2 T/L","구서S/S 154kV 646GIS 전자변 누기조치","구서S/S 154kV 646GIS 전자변 누기조치(신양산-구서#2T/L)","2020-12-11 09:30","2020-12-11 17:00","취소","취소","연속"]
[246,"부산울산","동부산","구서명장#2 T/L","`20~21년도 가공송전 정비회사 총액공사(동부산)","○애자교체 공사(154kV 신양산-구서#2T/L 작업 안전이격확보용) - 37호 ○ 추락방지장치 설치공사(154kV 신양산-구서#2T/L 작업 안전이격확보용) - 40호","2020-12-07 08:00","2020-12-09 18:00","취소","취소","연속"]
[247,"부산울산","동부산","신양산구서#1 T/L","`20~21년도 가공송전 정비회사 총액공사(동부산)","○애자교체 공사 - 21, 36, 40호 ○ 추락방지장치 설치공사 - 21, 22, 40호","2020-12-01 08:00","2020-12-04 18:00","취소","취소","연속"]
[248,"부산울산","동부산","구서명장#1 T/L","`20~21년도 가공송전 정비회사 총액공사(동부산)","○애자교체 공사(154kV 신양산-구서#1T/L 안전이격확보용) - 21, 36, 40호 ○ 추락방지장치 설치공사(154kV 신양산-구서#1T/L 안전이격확보용) - 21, 22, 40호","2020-12-01 08:00","2020-12-04 18:00","취소","취소","연속"]
[249,"부산울산","동부산","노포정관#1 T/L","노포S/S 154kV GIS 차단기 동작시험","노포,정관S/S 154kV GIS 차단기 동작시험(노포-정관#1T/L)","2020-12-07 09:30","2020-12-07 17:00","취소","취소","연속"]
[250,"부산울산","동부산","명례S/S 154kV CB 6100","명례S/S 154kV GIS 보통점검","명례S/S 6100GIS 보통점검","2020-12-02 09:30","2020-12-02 17:00","2020-12-02 09:30","2020-12-02 17:00","연속"]
[251,"부산울산","동부산","정관S/S 154kV CB 6100","정관S/S 154kV GIS 차단기 동작시험","정관S/S 6100GIS 차단기 동작시험","2020-12-04 09:30","2020-12-04 14:00","2020-12-04 09:30","2020-12-04 14:00","연속"]
[252,"부산울산","북부산","호포매리#1 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","○ #1T/L 임시선로 구성(4회선, 매리-김해#1 포함) ○ 가철탑 24-1, 1-1호 설치","2020-12-12 07:00","2020-12-13 18:00","취소","취소","연속"]
[253,"부산울산","북부산","매리김해#2 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","○ #2T/L 임시선로 구성(4회선, 호포-매리#2 포함) ○ 가철탑 24-1, 1-1호 설치","2020-12-04 07:00","2020-12-06 18:00","취소","취소","연속"]
[254,"부산울산","북부산","호포매리#2 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","○ #2T/L 임시선로 구성(4회선, 매리-김해#2 포함) ○ 가철탑 24-1, 1-1호 설치","2020-12-04 07:00","2020-12-06 18:00","취소","취소","연속"]
[255,"부산울산","북부산","매리김해#1 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","○ #1T/L 임시선로 구성(4회선, 호포-매리#1 포함) ○ 가철탑 24-1, 1-1호 설치","2020-12-12 07:00","2020-12-13 18:00","취소","취소","연속"]
[256,"부산울산","북부산","물금삼랑진PP#1 T/L","154kV 물금-삼랑진#1T/L 피뢰기설치, 전선교체공사","154kV 물금-삼랑진#1T/L 피뢰기설치, 전선교체공사(39~58호간 전선교체)","2020-12-09 07:00","2020-12-17 18:00","2020-12-09 07:00","2020-12-17 18:00","연속"]
[257,"부산울산","북부산","북부산호포 T/L","20-21 북부산전력지사 변전 총액공사","북부산,호포S/S 154kV 북부산-호포T/L 송전선로 보호반 대체","2020-12-08 10:00","2020-12-10 18:00","취소","취소","연속"]
[258,"부산울산","북부산","양산산막#2 T/L","20-21년 북부산 가공송전정비회사 총액공사","154kV 언양산막#1 작업 안전이격을 위한 휴전","2020-12-07 08:00","2020-12-08 17:00","2020-12-07 08:00","2020-12-08 17:00","매일"]
[259,"부산울산","북부산","서창산막#2 T/L","20-21년 북부산 가공송전정비회사 총액공사","154kV 언양산막#2 작업 안전이격을 위한 휴전","2020-12-01 08:00","2020-12-02 17:00","취소","취소","매일"]
[260,"부산울산","북부산","언양산막#2 T/L","20-21년 북부산 가공송전정비회사 총액공사","154kV 언양산막#2 96년 상반기 이전 성능저하 국산애자교체공사","2020-12-01 08:00","2020-12-05 17:00","취소","취소","연속"]
[261,"부산울산","북부산","언양산막#1 T/L","20-21년 북부산 가공송전정비회사 총액공사","154kV 언양산막#1 96년 상반기 이전 성능저하 국산애자교체공사","2020-12-07 08:00","2020-12-11 17:00","취소","취소","연속"]
[262,"부산울산","서부산","서부산S/S 154kV CB 6100","서부산S/S #6100 TIE GIS 전자변교체","서부산S/S #6100 TIE GIS 전자변교체","2020-12-01 10:00","2020-12-01 18:00","2020-12-01 10:00","2020-12-01 18:00","연속"]
[263,"부산울산","서부산","서부산S/S 154kV SEC CB 60610","서부산S/S #60-61 SEC GIS 전자변교체","서부산S/S #60-61 SEC GIS 전자변교체","2020-12-02 10:00","2020-12-02 18:00","2020-12-11 10:00","2020-12-11 18:00","연속"]
[264,"부산울산","서부산","서부산S/S 154kV SEC CB 65660","서부산S/S #65-65 SEC GIS 전자변교체","서부산S/S #65-65 SEC GIS 전자변교체","2020-12-04 10:00","2020-12-04 18:00","2020-12-04 10:00","2020-12-04 18:00","연속"]
[265,"부산울산","서부산","서부산다대#1 T/L","서부산S/S 서부산-다대#1T/L 전자변교체","서부산S/S 서부산-다대#1T/L 전자변교체","2020-12-07 10:00","2020-12-07 18:00","2020-12-07 10:00","2020-12-07 18:00","연속"]
[266,"부산울산","서부산","서부산엄궁#1 T/L","서부산S/S 서부산-엄궁#1T/L GIS 전자변교체","서부산S/S 서부산-엄궁#1T/L GIS 전자변교체","2020-12-16 10:00","2020-12-16 18:00","취소","취소","연속"]
[267,"부산울산","서부산","신녹산녹산#2 T/L","신녹산,녹산S/S 신녹산-녹산#2T/L PNL 성능개선","신녹산,녹산S/S 신녹산-녹산#2T/L PNL 성능개선(YPP)","2020-12-15 10:00","2020-12-15 18:00","2020-12-15 10:00","2020-12-15 18:00","연속"]
[268,"부산울산","서부산","신녹산녹산#1 T/L","신녹산,녹산S/S 신녹산-녹산#1T/L PNL 성능개선","신녹산,녹산S/S 신녹산-녹산#1T/L PNL 성능개선(YPP)","2020-12-09 10:00","2020-12-09 18:00","2020-12-09 10:00","2020-12-09 18:00","연속"]
[269,"부산울산","울산","두왕영남TP#2 T/L","울산S/S 154kV SW증설공사","○ 두왕-울산#2T/L, 울산-영남T/P #2T/L 보호반 이설(설비보강부) ○ 두왕-영남T/P #2T/L 선로분기(송전건설부) ○ 두왕-울산#2T/L, 울산-영남T/P #2T/L 최초가압 및 실부하가압(설비보강부)","2020-12-14 07:00","2020-12-29 18:00","2020-12-07 07:00","2020-12-11 18:00","연속"]
[270,"부산울산","울산","방어진영남TP#1 T/L","154㎸ 방어진-영남TP#1T/L OPGW 교체공사","154㎸ 방어진-영남TP#1T/L OPGW 5.686㎞(120SQ/24C) 시설, C/H↔ICT실간 비금속광케이블 0.79㎞ 등 부대설비 1식","2020-12-05 08:00","2020-12-06 18:00","취소","취소","연속"]
[271,"부산울산","울산","방어진영남TP#2 T/L","154㎸ 방어진-영남TP#1T/L OPGW 교체공사","OPGW 단선에 따른 교체작업시 안전확보","2020-12-05 07:00","2020-12-06 18:00","취소","취소","매일"]
[272,"부산울산","울산","성암울산TP#1 T/L","성암S/S 170kV 신설GIS 시험가압(성암-울산T/P #1T/L)","성암S/S 신설GIS[성암-울산T/P #1T/L(697)] 시험가압 -울산울산TP--&gt성암울산TP로 계통변경","2020-12-05 10:00","2020-12-06 10:00","2020-12-05 10:00","2020-12-06 10:00","연속"]
[273,"부산울산","울산","성암울산TP#2 T/L","성암S/S 170kV 신설GIS 시험가압(성암-울산T/P #1T/L)","성암S/S 신설GIS[성암-울산T/P #2T/L(657)] 시험가압 -울산울산TP--&gt성암울산TP로 계통변경","2020-12-09 10:00","2020-12-10 10:00","2020-12-09 10:00","2020-12-10 10:00","연속"]
[274,"부산울산","울산","신온산온산#1 T/L","20년 하반기 울산전력지사 154kV 개폐장치 정밀점검 공사","- GIS 정밀점검 - 세니온 단거리 송전선로 보호반 성능개선 - 시험팀,보호제어과, 제작사 입회 필요 - 온산측 차단기 동작시험","2020-12-07 09:00","2020-12-08 18:00","2020-12-07 09:00","2020-12-08 18:00","연속"]
[275,"부산울산","울산","신울산S/S 154kV CB 6400","신울산S/S 154kV GIS현대화공사","- 154kV TR-BUS 철거관련 154kV T-BUS TIE 6408DS철거","2020-12-04 09:00","2020-12-05 18:00","취소","취소","연속"]
[276,"부산울산","울산","신울산명례#2 T/L","신울산S/S 154kV GIS현대화공사","- 154kV TR-BUS 철거관련 154kV 신울산-명례#2T/L 6Q8DS철거","2020-12-07 09:00","2020-12-08 18:00","취소","취소","연속"]
[277,"부산울산","울산","신울산명례#1 T/L","신울산S/S 154kV GIS현대화공사","- 154kV TR-BUS 철거관련 154kV 신울산-명례#1T/L 6P8DS철거","2020-12-09 09:00","2020-12-10 18:00","취소","취소","연속"]
[278,"부산울산","울산","신울산S/S 154kV #68 BUS","신울산S/S 154kV 덕하전철 신규수용공사","고객선로(지중케이블) 24시간 시험가압(6R,6S Bay)","2020-12-08 09:00","2020-12-09 18:00","취소","취소","연속"]
[279,"부산울산","울산","신울산명례#2 T/L","신울산S/S 154kV 덕하전철 신규수용공사","고객선로(지중케이블) 24시간 시험가압(6R,6S Bay)","2020-12-08 09:00","2020-12-09 18:00","취소","취소","연속"]
[280,"부산울산","울산","신울산매암#3 T/L","신울산S/S 154kV GIS현대화공사","- 154kV TR-BUS 철거관련 154kV 신울산-매암#3T/L #6H6DS철거","2020-12-28 09:00","2020-12-29 18:00","취소","취소","연속"]
[281,"부산울산","울산","온산처용#2 T/L","20-21년 변전정비회사 총액공사","- 송전선로 보호반 대체","2020-12-09 09:00","2020-12-11 18:00","2020-12-09 09:00","2020-12-11 18:00","연속"]
[282,"부산울산","울산","용연울산TP#3 T/L","20년 하반기 울산전력지사 154kV 개폐장치 정밀점검 공사","용연S/S #4M.Tr 정밀점검 관련 시험가압1H","2020-12-30 17:00","2020-12-30 18:00","2020-12-30 17:00","2020-12-30 18:00","연속"]
[283,"부산울산","울산","울산T/P 154kV #65 BUS","성암S/S 170kV 신설GIS 시험가압(성암-울산T/P #2T/L)","성암S/S 신설GIS[성암-울산T/P #2T/L(657)] 시험가압 -울산울산TP--&gt성암울산TP로 계통변경","2020-12-09 10:00","2020-12-10 10:00","2020-12-09 10:00","2020-12-10 10:00","연속"]
[284,"부산울산","울산","울산T/P 154kV #65 BUS","성암S/S 170kV 신설GIS 시험가압(성암-울산T/P #1T/L)","성암S/S 신설GIS[성암-울산T/P #1T/L(697)] 시험가압 -울산울산TP--&gt성암울산TP로 계통변경","2020-12-05 10:00","2020-12-06 10:00","2020-12-05 10:00","2020-12-06 10:00","연속"]
[285,"부산울산","울산","울산울산TP#1 T/L","성암S/S 170kV 신설GIS 시험가압(성암-울산T/P #1T/L)","성암S/S 신설GIS[성암-울산T/P #1T/L(697)] 시험가압 -울산울산TP--&gt성암울산TP로 계통변경","2020-12-05 10:00","2020-12-06 10:00","취소","취소","연속"]
[286,"부산울산","울산","울산울산TP#2 T/L","성암S/S 170kV 신설GIS 시험가압(성암-울산T/P #2T/L)","성암S/S 신설GIS[성암-울산T/P #2T/L(657)] 시험가압 -울산울산TP--&gt성암울산TP로 계통변경","2020-12-09 10:00","2020-12-10 10:00","2020-12-09 10:00","2020-12-10 10:00","연속"]
[287,"부산울산","울산","용연울산TP#3 T/L","345kV 신울산복합-북부산T/L 건설공사","345kV 신울산복합-북부산T/L No.3~No.4 아킹혼 설치 및 항공구 설치(안전이격)","2020-12-12 07:00","2020-12-12 18:00","취소","취소","연속"]
[288,"부산울산","울산","울산울산TP#2 T/L","20년 하반기 울산전력지사 154kV 개폐장치 정밀점검 공사","울산S/S #4M.Tr 정밀점검 관련 시험가압1H","2020-12-02 17:00","2020-12-02 18:00","취소","취소","연속"]
[289,"부산울산","울산","울산울산TP#2 T/L","울산S/S 154kV SW증설공사","○ 울산-영남T/P #2T/L 전력케이블 포설 및 접속(남부건설본부 지중건설부) ○ 울산-울산T/P #2T/L 전력케이블 선종교체(설비보강부) ○ 두왕-울산#2T/L, 울산-영남T/P #2T/L 보호반 이설(설비보강부) ○ 두왕-울산#2T/L, 울산-영남T/P #2T/L 최초가압 및 실부하가압(설비보강부)","2020-12-04 09:30","2020-12-29 18:00","취소","취소","연속"]
[290,"부산울산","울산","울산영남TP#2 T/L","울산S/S 154kV SW 증설공사","○ 울산-영남TP #2T/L 무부하 시험가압(1Hr)","2020-12-28 17:00","2020-12-28 18:00","취소","취소","연속"]
[291,"부산울산","울산","울산영남TP#1 T/L","울산S/S 154kV SW 증설공사","○ 울산-영남TP #1T/L 무부하 시험가압(1Hr)","2020-12-01 17:00","2020-12-01 18:00","취소","취소","연속"]
[292,"부산울산","직할","부산수정#2 T/L","19-20년도 서부산 지중송전설비 위탁정비공사","[OF케이블 절연유 채취밸브 설치공사] 절연유 채취밸브 설치(30개소)","2020-12-21 09:00","2020-12-24 18:00","2020-12-21 09:00","2020-12-24 18:00","연속"]
[293,"부산울산","직할","부산수정#1 T/L","19-20년도 서부산 지중송전설비 위탁정비공사","[OF케이블 절연유 채취밸브 설치공사] 절연유 채취밸브 설치(30개소)","2020-12-07 09:00","2020-12-11 18:00","2020-12-07 09:00","2020-12-11 18:00","연속"]
[294,"경남","직할","신김해삼정#2 T/L","삼정S/S GIS화 154kV 삼정-천선#2T/L 인출변경 시험가압","삼정S/S GIS화 154kV 삼정-천선#2T/L 인출변경 시험가압","2020-12-07 09:30","2020-12-08 17:30","2020-12-07 09:30","2020-12-08 17:30","연속"]
[295,"경남","직할","신월삼정#2 T/L","삼정S/S GIS화 #3M.Tr 이설공사 시험가압","삼정S/S GIS화 #3M.Tr 이설공사 시험가압","2020-12-03 09:30","2020-12-04 17:30","2020-12-03 09:30","2020-12-04 17:30","연속"]
[296,"경남","직할","신김해지사#2 T/L","신김해S/S 154kV 장기사용GIS 교체공사(4차) 안전이격,시험가압","신김해S/S 154kV 장기사용GIS 교체공사(4차) 안전이격,시험가압 - 대상 : 신김해-장유#1T/L, #2M.Tr 2차 GIS","2020-12-06 08:00","2020-12-10 18:00","2020-12-06 08:00","2020-12-10 18:00","연속"]
[297,"경남","직할","주촌삼계#1 T/L","주촌S/S 주촌-삼계 #1T/L GIS 보통점검","주촌S/S 주촌-삼계 #1T/L GIS 보통점검","2020-12-02 09:30","2020-12-02 17:30","2020-12-02 09:30","2020-12-02 17:30","연속"]
[298,"경남","직할","주촌삼계#2 T/L","주촌S/S 주촌-삼계 #2T/L GIS 보통점검","주촌S/S 주촌-삼계 #2T/L GIS 보통점검","2020-12-03 09:30","2020-12-03 17:30","2020-12-03 09:30","2020-12-03 17:30","연속"]
[299,"경남","직할","천선진해#1 T/L","154kV 천선분기T/L 지장송전선로 이설공사","신설철탑조립, 천선-진해 기설~신설 1호 전력선교체 및 긴선, 기설철탑철거","2020-12-14 07:00","2020-12-25 18:00","2020-12-14 07:00","2020-12-25 18:00","연속"]
[300,"경남","직할","삼정천선#1 T/L","154kV 천선분기T/L 지장송전선로 이설공사","신설철탑조립, 6호 기설~신설 전력선교체 및 긴선, 기설철탑철거","2020-12-14 07:00","2020-12-25 18:00","2020-12-14 07:00","2020-12-25 18:00","연속"]
[301,"경남","진주","사봉개양#1 T/L","개양S/S 154kV 사봉-개양#1T/L GIS 보통점검","개양S/S 154kV 사봉-개양#1T/L GIS 보통점검","2020-12-12 10:00","2020-12-12 14:00","2020-12-12 10:00","2020-12-12 14:00","연속"]
[302,"경남","진주","사봉개양#2 T/L","개양S/S 154kV 사봉-개양#2T/L GIS 보통점검","개양S/S 154kV 사봉-개양#2T/L GIS 보통점검","2020-12-12 14:00","2020-12-12 18:00","2020-12-12 14:00","2020-12-12 18:00","연속"]
[303,"경남","진주","개양S/S 154kV CB 6100","개양S/S 고장파급장치반 대체공사","개양S/S 고장파급장치반 대체공사","2020-12-03 10:00","2020-12-06 18:00","2020-12-03 10:00","2020-12-06 18:00","연속"]
[304,"경남","진주","하동S/S 154kV CB 6100","하동S/S 154kV #1BUS TIE GIS 메커니즘 정밀점검","하동S/S 154kV #1BUS TIE GIS 메커니즘 정밀점검","2020-12-09 10:00","2020-12-09 17:00","2020-12-09 10:00","2020-12-09 17:00","연속"]
[305,"경남","통영","신고성삼천포#2 T/L","신고성-삼천포#2T/L 보호반 대체","1. 신고성S/S 신고성-삼천포#2T/L 보호반 대체 2. 삼천포S/S 신고성-삼천포#2T/L 보호반 대체","2020-12-14 10:00","2020-12-18 18:00","2020-12-14 10:00","2020-12-18 18:00","연속"]
[306,"경남","통영","신고성거제#2 T/L","154kV 신고성-거제#2T/L 폴리머애자 교체","154kV 신고성-거제#2T/L 폴리머애자 교체(161~183호)","2020-12-12 08:00","2020-12-13 18:00","2020-12-12 08:00","2020-12-13 18:00","매일"]
[307,"경남","통영","신고성거제#2 T/L","154kV 신고성-거제#2T/L 폴리머애자 교체","154kV 신고성-거제#2T/L 폴리머애자 교체(161~183호)","2020-12-05 08:00","2020-12-06 18:00","2020-12-05 08:00","2020-12-06 18:00","매일"]
[308,"경남","함안","진영한림정#1 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 345k신김해-북부산T/L 95-96호 횡단구간 안전확보","2020-12-26 07:00","2020-12-27 18:00","2021-01-30 07:00","2021-01-31 18:00","연속"]
[309,"경남","함안","진영수산#1 T/L","154kV 진영-수산T/L 7, 29호 추락방지장치 설치","154kV 진영-수산T/L 29호 추락방지장치 설치 154kV 진영-수산T/L 7호(동읍-진영 34호에 병가) 추락방지장치 설치 154kV 동읍-진영T/L 34호(모철탑) 추락방지장치 설치 안전확보차","2020-12-07 08:00","2020-12-07 18:00","2020-12-07 08:00","2020-12-07 18:00","연속"]
[310,"경남","함안","진영수산#2 T/L","154kV 진영-수산T/L 7, 29호 추락방지장치 설치","154kV 진영-수산T/L 29호 추락방지장치 설치 154kV 진영-수산T/L 7호(동읍-진영 34호에 병가) 추락방지장치 설치 154kV 동읍-진영T/L 34호(모철탑) 추락방지장치 설치 안전확보차","2020-12-08 08:00","2020-12-08 18:00","2020-12-08 08:00","2020-12-08 18:00","연속"]
[311,"경남","함안","진영한림정#2 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 345k신김해-북부산T/L 95-96호 횡단구간 안전확보","2020-12-26 07:00","2020-12-27 18:00","2021-01-30 07:00","2021-01-31 18:00","연속"]
[312,"경남","함안","창녕초동#2 T/L","창녕S/S 154kV 창녕-초동#2T/L CB 보통점검","창녕S/S 154kV 창녕-초동#2T/L CB 보통점검 외","2020-12-10 09:00","2020-12-10 18:00","2020-12-10 09:00","2020-12-10 18:00","연속"]
[313,"경남","함안","창녕초동#1 T/L","창녕S/S 154kV 창녕-초동#1T/L CB 보통점검","창녕S/S 154kV 창녕-초동#1T/L CB 보통점검 외","2020-12-09 09:00","2020-12-09 18:00","2020-12-09 09:00","2020-12-09 18:00","연속"]
[314,"경남","함안","창녕구지#1 T/L","창녕S/S 154kV 창녕-구지#1T/L CB 조작시험","창녕S/S 154kV 창녕-구지#1T/L CB 조작시험 외","2020-12-07 09:00","2020-12-07 18:00","2020-12-07 09:00","2020-12-07 18:00","연속"]
[315,"경남","함안","창녕구지#2 T/L","창녕S/S 154kV 창녕-구지#2T/L CB 조작시험","창녕S/S 154kV 창녕-구지#2T/L CB 조작시험 외","2020-12-05 09:00","2020-12-05 18:00","2020-12-05 09:00","2020-12-05 18:00","연속"]
[316,"경남","함안","신마산칠서#1 T/L","칠서S/S 154kV 장기사용 GIS 대체공사","칠서S/S 154kV 장기사용 GIS 대체공사","2020-12-05 17:00","2020-12-06 17:00","2020-12-05 17:00","2020-12-06 17:00","연속"]
[317,"경남","함안","신마산칠서#2 T/L","칠서S/S 154kV 장기사용 GIS 대체공사","칠서S/S 154kV 장기사용 GIS 대체공사","2020-12-04 17:00","2020-12-05 17:00","2020-12-04 17:00","2020-12-05 17:00","연속"]
[318,"인천","부평","신가좌S/S 154kV #66 BUS","신가좌S/S 6200 GIS 정밀점검 관련 무부하 가압용","신가좌S/S 6200 GIS 정밀점검 관련 무부하 가압용","2020-12-05 09:00","2020-12-05 18:00","취소","취소","연속"]