{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":6,"n_cols":11,"rows_kept":6,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2021년도 1월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경북","영주","신태백신한울#1 T/L","신한울1호기 상업운전 관련 SPS 설치공사","신한울1호기 상업운전 관련 SPS 설치공사","2021-01-11 09:00","2021-01-12 18:00","2021-01-11 09:00","2021-01-12 18:00","당일"]
[2,"경북","영주","신태백신한울#2 T/L","신한울1호기 상업운전 관련 SPS 설치공사","신한울1호기 상업운전 관련 SPS 설치공사","2021-01-18 09:00","2021-01-19 18:00","2021-01-18 09:00","2021-01-19 18:00","당일"]

{"sheet":"345송부","index":1,"n_rows":44,"n_cols":11,"rows_kept":44,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2021년도 1월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","중부S/S #2 M.Tr","중부S/S 345kV M.Tr 및 OLTC 정밀점검공사","#2M.Tr 및 OLTC 정밀점검","2021-01-22 09:00","2021-01-31 18:00","취소","취소","연속"]
[2,"서울","중부","중부S/S #3 M.Tr","중부S/S 345kV M.Tr 및 OLTC 정밀점검공사","#3M.Tr 및 OLTC 정밀점검, 부싱교체","2021-01-11 09:00","2021-01-21 18:00","취소","취소","연속"]
[3,"인천","직할","갈산S/S 345kV #70 BUS","345kV 갈산S/S Sh.R 증설","Sh.R 초기가압","2021-01-12 09:00","2021-01-13 13:00","2021-01-12 09:00","2021-01-13 13:00","연속"]
[4,"인천","직할","갈산S/S #1 M.Tr","345kV 갈산S/S Sh.R 증설","#2Sh.R 증설","2021-01-12 09:00","2021-01-13 18:00","2021-01-12 09:00","2021-01-13 18:00","연속"]
[5,"인천","직할","갈산S/S 345kV #75 BUS","345kV 갈산S/S Sh.R 증설","Sh.R 초기가압","2021-01-12 13:00","2021-01-13 18:00","2021-01-12 13:00","2021-01-13 18:00","연속"]
[6,"경기북부","직할","신의정부S/S #4 M.Tr","'20~21 변전정비 총액공사","신의정부S/S #4M.Tr 가스분석 이상 부싱 절연유 채유 (C2H2 1ppm 검출, 추적관리 대상 : 1차 C / 2차 A,B)","2021-01-12 09:00","2021-01-12 18:00","2021-01-12 09:00","2021-01-12 18:00","연속"]
[7,"경기북부","직할","신의정부S/S #3 M.Tr","'20~21 변전정비 총액공사","신의정부S/S #3M.Tr 가스분석 이상 부싱 절연유 채유 (C2H2 1ppm 검출, 추적관리 대상 : 1차 B,C / 2차 A,B,C)","2021-01-11 09:00","2021-01-11 18:00","2021-01-11 09:00","2021-01-11 18:00","연속"]
[8,"경기북부","직할","양주S/S #4 M.Tr","양주S/S 154kV 옥외철구 철거(#4M.Tr 2차 옥외철구)","양주S/S 154kV 옥외철구 철거(#4M.Tr 2차 옥외철구)","2021-01-16 09:00","2021-01-16 18:00","2021-01-16 09:00","2021-01-16 18:00","연속"]
[9,"경기북부","직할","양주S/S #1 M.Tr","'20~21 변전정비 총액공사","양주S/S #1(구)M.Tr 2차 A, B상 가스이상 부싱 절연유 채유 C2H2 1ppm 검출, 추적관리 대상","2021-01-09 09:00","2021-01-09 18:00","2021-01-09 09:00","2021-01-09 18:00","연속"]
[10,"경기북부","직할","신의정부양주#2 T/L","신의정부S/S 효성제 GIS 하자보수공사","신의정부-양주 #2 T/L GIS 케이블플러그 교체 및 전선관 경로변경(U→I)","2021-01-12 09:00","2021-01-13 18:00","취소","취소","연속"]
[11,"경기북부","직할","신의정부양주#1 T/L","신의정부S/S 효성제 GIS 하자보수공사","신의정부-양주 #1 T/L GIS DS, ES 전선관 경로변경(U→I)","2021-01-14 09:00","2021-01-14 18:00","취소","취소","연속"]
[12,"경기","성남","신성남S/S STATCOM CB","STATCOM 보통점검",2,"2021-01-18 09:00","2021-01-29 18:00","2021-01-18 09:00","2021-01-29 18:00","연속"]
[13,"전북","군산","군산새만금#1 T/L","345kV 군산-신김제 등 3개T/L 피뢰기 설치공사","345kV 군산-신김제, 군산-새만금, 청양-군산T/L 송전선로용 피뢰기 1회선 설치","2021-01-18 09:00","2021-01-29 18:00","2021-01-18 09:00","2021-01-29 18:00","연속"]
[14,"전북","직할","신남원S/S 345kV #2BUS","신남원S/S GAS 누기 보수공사(2차)-#75BUS","- 1/4 ~ 1/26 : 신남원-광양#2T/L 휴전병행","2021-01-04 09:00","2021-01-07 18:00","취소","취소","연속"]
[15,"전북","직할","신남원광양#2 T/L","신남원S/S GAS 누기 보수공사(2차)-7671,7600","- 1/4~1/7 : 7600CB C상 GAS 누기보수, #75BUS 휴전병행 - 1/11~1/24 : 7671CB A, B, C상 GAS 누기보수, #70BUS 휴전병행 - 1/25~1/26 : 7661DS B GAS 누기보수, #70BUS 휴전병행","2021-01-04 09:00","2021-01-26 18:00","취소","취소","연속"]
[16,"전북","직할","신남원S/S 345kV #1BUS","신남원S/S GAS 누기 보수공사(2차)-#70BUS","- 1/11 ~ 1/26 : 신남원-광양#2T/L 휴전병행","2021-01-11 09:00","2021-01-26 18:00","취소","취소","연속"]
[17,"광주전남","목포","신김제한빛NP#2 T/L","한빛NP #3S/Y 362kV 장기사용 GIS 교체공사","한빛NP #3S/Y 362kV 장기사용 GIS 교체공사(7EBAY)","2021-01-11 09:00","2021-03-10 18:00","2021-01-11 09:00","2021-03-10 18:00","연속"]
[18,"광주전남","목포","한빛N/P 345kV CB 7E72","한빛NP #3S/Y 362kV 장기사용 GIS 교체공사","한빛NP #3S/Y 362kV 장기사용 GIS 교체공사(7EBAY)","2021-01-11 09:00","2021-03-10 18:00","취소","취소","연속"]
[19,"광주전남","목포","한빛N/P 345kV CB 7E00","한빛NP #3S/Y 362kV 장기사용 GIS 교체공사","한빛NP #3S/Y 362kV 장기사용 GIS 교체공사(7EBAY)","2021-01-11 09:00","2021-03-10 18:00","취소","취소","연속"]
[20,"광주전남","목포","한빛N/P 345kV CB 7E71","한빛NP #3S/Y 362kV 장기사용 GIS 교체공사","한빛NP #3S/Y 362kV 장기사용 GIS 교체공사(7EBAY)","2021-01-11 09:00","2021-03-10 18:00","2021-01-11 09:00","2021-03-10 18:00","연속"]
[21,"광주전남","순천","율촌CC여수TP T/L","345kV 광양CC-신여수T/L 건설사업","- 공사개요 : 345kV 광양-여수TP T/L No.가2 전선이동 - 시공사/감리사 : 세종텔레콤/한국코아엔지니어링","2021-01-22 07:00","2021-01-25 18:00","취소","취소","연속"]
[22,"광주전남","순천","광양여수TP T/L","345kV 광양CC-신여수T/L 건설사업","- 공사개요 : 345kV 광양-여수TP T/L No.가2 철탑 조립 - 시공사/감리사 : 세종텔레콤/한국코아엔지니어링","2021-01-18 07:00","2021-01-21 18:00","취소","취소","연속"]
[23,"대구","포항","신월성N/P 345kV CB 7172","신월성S/Y 7100, 7172 GIS 보통점검","신월성S/Y 7100, 7172 GIS 보통점검","2021-01-19 09:30","2021-01-19 18:00","취소","취소","연속"]
[24,"대구","포항","신월성N/P 345kV CB 7100","신월성S/Y 7100, 7172 GIS 보통점검","신월성S/Y 7100, 7172 GIS 보통점검","2021-01-19 09:00","2021-01-19 18:00","취소","취소","연속"]
[25,"부산울산","울산","신울산S/S #4 M.Tr","신울산S/S 154kV GIS현대화공사","- TR-BUS용 6468DS 철거관련 휴전","2021-01-20 09:00","2021-01-21 18:00","취소","취소","연속"]
[26,"부산울산","울산","신울산S/S #2 M.Tr","신울산S/S 154kV GIS현대화공사","- TR-BUS용 6268DS 철거관련 휴전","2021-01-15 09:00","2021-01-16 18:00","취소","취소","연속"]
[27,"부산울산","울산","신대연S/S #2 Sh.R CB","345kV 신대연S/S #2Sh.R 7579 GIS 하자점검","345kV 신대연S/S #2Sh.R GIS 하자점검","2021-01-11 09:30","2021-01-14 18:00","2021-01-11 09:30","2021-01-14 18:00","연속"]
[28,"부산울산","울산","신대연S/S #1 Sh.R CB","345kV 신대연S/S #1Sh.R 유펌프점검","345kV 신대연S/S #1Sh.R 유펌프점검","2021-01-15 09:30","2021-01-15 18:00","2021-01-15 09:30","2021-01-15 18:00","연속"]
[29,"부산울산","울산","신울산S/S #1 M.Tr","신울산S/S 154kV GIS현대화공사","- TR-BUS용 6168DS 철거관련 휴전","2021-01-18 09:00","2021-01-19 18:00","취소","취소","연속"]
[30,"부산울산","울산","신울산S/S #3 M.Tr","신울산S/S 154kV GIS현대화공사","- TR-BUS용 6368DS 철거관련 휴전","2021-01-04 09:00","2021-01-05 18:00","취소","취소","연속"]
[31,"경남","직할","신김해북부산#2 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 철탑설치 및 철거 : 각 2기 ○ 전력선 및 가공지선 교체 : 1.4km (93-97호) ○ 스페이서 댐퍼 교체","2021-01-28 07:00","2021-02-03 18:00","취소","취소","연속"]
[32,"경남","직할","신김해북부산#1 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 철탑설치 및 철거 : 각 2기 ○ 전력선 및 가공지선 교체 : 1.4km (93-97호) ○ 스페이서 댐퍼 교체","2021-01-01 07:00","2021-01-03 18:00","취소","취소","연속"]
[33,"경남","직할","신김해북부산#1 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 철탑설치 및 철거 : 각 2기 ○ 전력선 및 가공지선 교체 : 1.4km (93-97호) ○ 스페이서 댐퍼 교체","2021-01-21 07:00","2021-01-27 18:00","취소","취소","연속"]
[34,"대구","월성","신월성N/P #2호기 주변압기 CB (7100, 7172)","신월성 2호기 4차 계획예방정비, #2 MTR/UAT/EXTR 점검 *조작차단기 : PCB 7100, 7172","○ MTR/UAT/EXTR 일반 점검 등","2021-01-09 09:00","2021-01-30 18:00","2021-01-09 09:00","2021-01-30 18:00","연속"]
[35,"대구","월성","신월성N/P #2 대기보조변압기 CB (7200, 7272)","신월성 2호기 4차  계획예방정비, #2 대기보조변압기(SAT) 점검 *조작차단기 : PCB 7200, 7272","○ 대기보조변압기 일반점검 등","2021-01-31 09:00","2021-02-10 18:00","2021-01-31 09:00","2021-02-10 18:00","연속"]
[36,"광주전남","영광","한빛N/P #1호기 주변압기 CB (7100, 7171)","한빛1호기 25차 O/H 중 주변압기 점검 * 조작차단기 : CB 7100, 7171","○ 주변압기 일반점검","2021-01-27 10:00","2021-04-15 11:00","2021-01-27 10:00","2021-04-15 11:00","연속"]
[37,"광주전남","영광","한빛N/P #1 기동변압기 CB (7200, 7271)","한빛1호기 25차 O/H 중 기동변압기(X01) 공사 * 조작차단기 : CB 7200, 7271","○ 기동변압기(X01) 공사","2021-01-28 20:00","2021-02-22 20:00","2021-01-28 20:00","2021-02-22 20:00","연속"]
[38,"광주전남","영광","한빛N/P #6호기 주변압기 CB (7E00, 7E71)","6호기 13차 계획예방정비 - 조작차단기 : PCB 7E00, 7E71, 7E72","○ 주변압기 및 소내보조변압기 일반점검 ○ 보호계전기 개체/연동시험 등 ○ 스위치야드 차단기(GIS) 교체공사 ○ 가스절연모선(GIB) 교체공사","2021-01-11 09:00","2021-03-05 18:00","2021-01-11 09:00","2021-03-05 18:00","연속"]
[39,"인천","직할","갈산S/S #1 M.Tr","345kV 갈산S/S Sh.R 증설","#2Sh.R 증설","2021-01-04 09:00","2021-01-05 18:00","2021-01-04 09:00","2021-01-05 18:00","연속"]
[40,"경기북부","구리","신포천S/S 345kV CB 7379","7392-1,2 ES 구조개선 공사","7392-1,2 ES 구조개선 공사","2021-01-07 09:00","2021-01-08 18:00","2021-01-07 09:00","2021-01-08 18:00","매일"]

{"sheet":"154송부","index":2,"n_rows":57,"n_cols":11,"rows_kept":57,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2021년도 1월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","구의S/S 154kV #1 BUS","○ 154kV 구의S/S 가스변압기 교체공사(2차분 무부하가압)","○ 154kV 구의S/S 가스변압기 교체공사(2차분 무부하가압) - 154kV 구의S/S #1M.Tr A,B,C상 철거(유입) - 154kV 구의S/S #1M.Tr A,B,C상 설치(가스절연)","2021-01-22 15:00","2021-01-25 10:00","2021-01-22 15:00","2021-01-25 10:00","연속"]
[2,"서울","성동","구의광장#1 T/L","○ 154kV 구의S/S 가스변압기 교체공사(2차분 무부하가압)","○ 154kV 구의S/S 가스변압기 교체공사(2차분 무부하가압) - 154kV 구의S/S #1M.Tr A,B,C상 철거(유입) - 154kV 구의S/S #1M.Tr A,B,C상 설치(가스절연)","2021-01-22 15:00","2021-01-25 10:00","2021-01-22 15:00","2021-01-25 10:00","연속"]
[3,"서울","중부","동빙고반포#1 T/L","154kV 동빙고S/S #3M.Tr 증설공사","154kV 동빙고S/S #3M.Tr 증설공사(최초 가압)","2021-01-09 09:00","2021-01-10 10:00","2021-01-09 09:00","2021-01-10 10:00","연속"]
[4,"남서울","영등포","오류S/S 154kV #2 BUS","154kV 천왕-구로,오류T/L 지장송전선로이설공사","○ 위 치 : 광명시 광명동 776-16일원 ○ 선 로 명 : 154kV 천왕-오류#2T/L ○ 구 간 : 천왕S/S S/J M/H#0 ∼M/H#3호 구간중 144m ○ 주요공종 - 케이블 철거,포설,접속,준공시험","2021-01-13 10:00","2021-01-13 10:20","2021-01-13 10:00","2021-01-13 10:20","연속"]
[5,"남서울","영등포","천왕오류#1 T/L","154kV 천왕-구로, 오류T/L 지장송전선로 이설공사","○ 구 간 : 154㎸ 천왕S/S S/J#0 ∼ 신설 M/H#1 ○ 공사기간 : 2020. 6. 26 ∼ 2021. 4. 25 ○ 선종 및 회선길이 : 154kV OF 1,200㎟ × 2C × 0.144km, OF 600㎟ × 2C × 0.144km ○ 케이블 접속 : 8개소","2021-01-15 09:00","2021-02-18 18:00","2021-01-15 09:00","2021-02-18 18:00","연속"]
[6,"강원","직할","상남인제#1 T/L","2020-2021 강원본부 직할 변전정비 총액공사","154kV 공압식 차단기 전자변 교체 및 개폐타임 측정 시행","2021-01-04 10:00","2021-01-04 18:00","2021-01-04 10:00","2021-01-04 18:00","연속"]
[7,"강원","직할","남춘천춘천열병합#2 T/L","장기 미동작 차단기 동작시험","차단기 개폐타임 측정 및 비상트립 시험 시행","2021-01-05 10:00","2021-01-05 12:00","2021-01-05 10:00","2021-01-05 12:00","연속"]
[8,"대전충남","대전","논산은진#2 T/L","은진S/S 154kV 옥외철구 철거작업","은진S/S 154kV 옥외철구 철거작업(작업구간 확보)","2021-01-05 10:00","2021-01-05 11:00","취소","취소","연속"]
[9,"대전충남","대전","논산은진#1 T/L","은진S/S 154kV 옥외철구 철거작업","은진S/S 154kV 옥외철구 철거작업(작업구간 확보)","2021-01-05 10:00","2021-01-05 11:00","취소","취소","연속"]
[10,"대전충남","아산","풍세장재#1 T/L","풍세,장재S/S 풍세,장재#1T/L 보호배전반 성능개선","풍세,장재S/S 풍세,장재#1T/L 보호배전반 성능개선","2021-01-19 09:00","2021-01-19 18:00","취소","취소","연속"]
[11,"대전충남","아산","인주탕정#1 T/L","154kV 인주-불당T/L C/H 건설공사","154kV 인주-불당T/L C/H 건설공사 - 임시선로 철거 및 본선로 구성","2021-01-04 09:00","2021-01-10 18:00","취소","취소","연속"]
[12,"대전충남","아산","서천안탕정#2 T/L","154kV 인주-불당T/L C/H 건설공사","154kV 인주-불당T/L C/H 건설공사 - 임시선로 철거 및 본선로 구성","2021-01-04 09:00","2021-01-10 18:00","2021-01-04 09:00","2021-01-10 18:00","연속"]
[13,"대전충남","아산","서천안탕정#1 T/L","154kV 인주-불당T/L C/H 건설공사","154kV 인주-불당T/L C/H 건설공사 - 임시선로 철거 및 본선로 구성","2021-01-11 09:00","2021-01-17 18:00","2021-01-11 09:00","2021-01-17 18:00","연속"]
[14,"대전충남","아산","인주탕정#2 T/L","154kV 인주-불당T/L C/H 건설공사","154kV 인주-불당T/L C/H 건설공사 - 임시선로 철거 및 본선로 구성","2021-01-11 09:00","2021-01-17 18:00","취소","취소","연속"]
[15,"대전충남","청양","서산홍성 T/L","홍성S/S 서산-홍성T/L GIS CT케이블 교체","홍성S/S 서산-홍성T/L GIS CT케이블 교체","2021-01-28 09:00","2021-01-28 18:00","취소","취소","연속"]
[16,"대전충남","아산","신탕정S/S #1M.Tr","신탕정S/S 345kV #1M.Tr GIS 내장형 콘덴서 설치","신탕정S/S 345kV #1M.Tr GIS 내장형 콘덴서 설치","2021-01-04 09:00","2021-01-08 18:00","취소","취소","연속"]
[17,"대전충남","아산","아산인주#1T/L","345kV 북당진-신탕정T/L 건설공사","No.47~48 가선공사 - 아산인주#1,2T/L 횡단을 위한 보호망 설치(양회선 휴전 3시간)","2021-01-23 08:00","2021-01-23 11:00","취소","취소","연속"]
[18,"대전충남","아산","아산인주#2T/L","345kV 북당진-신탕정T/L 건설공사","No.47~48 가선공사 - 아산인주#1,2T/L 횡단을 위한 보호망 설치(양회선 휴전 3시간)","2021-01-23 08:00","2021-01-23 11:00","취소","취소","연속"]
[19,"대전충남","아산","인주탕정#1T/L","345kV 북당진-신탕정T/L 건설공사","No.47~48 가선공사 - 아산인주#1,2T/L 횡단을 위한 보호망 설치(양회선 휴전 3시간)","2021-01-23 14:00","2021-01-23 17:00","취소","취소","연속"]
[20,"대전충남","아산","인주탕정#2T/L","345kV 북당진-신탕정T/L 건설공사","No.47~48 가선공사 - 아산인주#1,2T/L 횡단을 위한 보호망 설치(양회선 휴전 3시간)","2021-01-23 14:00","2021-01-23 17:00","취소","취소","연속"]
[21,"전북","군산","내초군장#1 T/L","154kV 군장S/S SMG에너지T/L 신규수용공사(시험가압)","170kV GIS X 1CCT","2021-01-12 10:00","2021-01-13 10:00","2021-01-12 10:00","2021-01-13 10:00","연속"]
[22,"전북","직할","신남원남원#2 T/L","154kV 남원S/S 옥외철구설비 GIS화 공사","○ 154kV 신남원-남원#2T/L 인출구간 변경 및 GIS설비로 이전","2021-01-28 08:00","2021-02-19 18:00","취소","취소","연속"]
[23,"전북","직할","신남원남원#1 T/L","남원S/S 옥외철구설비 GIS화 공사","○ 154kV 신남원-남원#1T/L 선로변경(가공→지중) ○ 154kV GIS 가압 ○ 신남원, 남원S/S 보호배전반 대체 등","2021-01-04 08:00","2021-01-27 18:00","취소","취소","연속"]
[24,"전북","직할","곡성남원#2 T/L","154kV 남원S/S 옥외철구설비 GIS화 공사","○ 154kV 곡성-남원#2T/L 인출구간 변경 및 GIS설비로 이전","2021-01-28 08:00","2021-02-19 18:00","취소","취소","연속"]
[25,"전북","직할","남원임실#2 T/L","154kV 남원S/S 옥외철구설비 GIS화 공사","○ 154kV 남원-임실#2T/L 인출구간 변경 및 GIS설비로 이전","2021-01-04 08:00","2021-01-27 18:00","취소","취소","연속"]
[26,"광주전남","광주","계림승주#1 T/L","154kV 계림-승주#1 T/L 애자교체","2020년 송전협력회사 총액공사 154kV 계림-승주#1 T/L 애자교체(2, 71, 89호)","2021-01-13 09:00","2021-01-14 18:00","2021-01-13 09:00","2021-01-14 18:00","매일"]
[27,"광주전남","순천","여수TP화치#1 T/L","345kV 광양CC-신여수T/L 건설사업","- 공사개요 : 345kV 광양-여수TP T/L No.2, 3 철탑 조립 - 시공사/감리사 : 세종텔레콤/한국코아엔지니어링","2021-01-11 07:00","2021-01-13 18:00","2021-01-11 07:00","2021-01-13 18:00","연속"]
[28,"광주전남","직할","평동왕곡#1 T/L","154kV 왕곡S/S #1,4M.Tr 증설공사 무부하가압","154kV 왕곡S/S #1,4M.Tr 증설공사","2021-01-14 10:00","2021-01-15 10:00","2021-01-14 10:00","2021-01-15 10:00","연속"]
[29,"광주전남","직할","왕곡나주#1 T/L","154kV 왕곡S/S #1,4M.Tr 증설공사 무부하가압","154kV 왕곡S/S #1,4M.Tr 증설공사","2021-01-21 10:00","2021-01-22 10:00","2021-01-21 10:00","2021-01-22 10:00","연속"]
[30,"광주전남","직할","왕곡나주#2 T/L","154kV 왕곡S/S #1,4M.Tr 증설공사(#4M.Tr 측)","154kV 왕곡S/S #1,4M.Tr 증설공사","2021-01-25 10:00","2021-02-03 18:00","취소","취소","연속"]
[31,"광주전남","직할","왕곡나주#2 T/L","154kV 왕곡S/S #1,4M.Tr 증설공사 무부하가압","154kV 왕곡S/S #1,4M.Tr 증설공사","2021-01-28 10:00","2021-01-29 10:00","취소","취소","연속"]
[32,"광주전남","직할","평동왕곡#2 T/L","154kV 왕곡S/S #1,4M.Tr 증설공사(#4M.Tr 측)","154kV 왕곡S/S #1,4M.Tr 증설공사","2021-01-25 10:00","2021-02-03 18:00","취소","취소","연속"]
[33,"대구","달성","월배S/S 154kV #2 BUS","월배S/S 달성-월배T/L SW 증설작업","월배S/S 달성-월배T/L SW 증설작업","2021-01-11 09:00","2021-01-17 18:00","취소","취소","연속"]
[34,"부산울산","울산","신울산명례#2 T/L","신울산S/S 154kV GIS현대화공사","- TR-BUS용 6Q8DS 철거관련 휴전","2021-01-06 09:00","2021-01-07 18:00","2021-01-06 09:00","2021-01-07 18:00","연속"]
[35,"부산울산","울산","신울산울산#2 T/L","신울산S/S 154kV GIS현대화공사","- TR-BUS용 6N8DS 철거관련 휴전","2021-01-11 09:00","2021-01-12 18:00","취소","취소","연속"]
[36,"부산울산","울산","신울산울산#1 T/L","신울산S/S 154kV GIS현대화공사","- TR-BUS용 6M8DS 철거관련 휴전","2021-01-13 09:00","2021-01-14 18:00","취소","취소","연속"]
[37,"부산울산","울산","신울산명례#1 T/L","신울산S/S 154kV GIS현대화공사","- TR-BUS용 6P8DS 철거관련 휴전","2021-01-08 09:00","2021-01-09 18:00","2021-01-08 09:00","2021-01-09 18:00","연속"]
[38,"부산울산","울산","용연울산TP#2 T/L","2020-21년 울산전력지사 변전협력회사 총액공사","- 가스배관 구조 변경(#1,2모선휴전필요함) - GIS 하자점검 - LA 보통점검 - 최원재 과장님 PITR 정기시험 병행","2021-01-04 09:00","2021-01-07 18:00","취소","취소","연속"]
[39,"부산울산","울산","울산T/P 154kV #66 BUS","2020-21년 울산전력지사 변전협력회사 총액공사","RY PT 케이블 교체(1심X4조-&gt4심X1조)","2021-01-26 14:00","2021-01-26 18:00","취소","취소","연속"]
[40,"부산울산","울산","울산T/P 154kV #61 BUS","2020-21년 울산전력지사 변전협력회사 총액공사","RY PT 케이블 교체(1심X4조-&gt4심X1조)","2021-01-26 09:00","2021-01-26 14:00","취소","취소","연속"]
[41,"경남","직할","창원천선#1 T/L","154kV 천선분기T/L 지장송전선로 이설공사","154kV 안민-천선 #2T/L 전선교체에 따른 안전이격확보","2021-01-19 07:00","2021-01-22 18:00","2021-01-19 07:00","2021-01-22 18:00","연속"]
[42,"경남","직할","창원천선#2 T/L","154kV 천선분기T/L 지장송전선로 이설공사","154kV 안민-천선 #2T/L 전선교체에 따른 안전이격확보","2021-01-19 07:00","2021-01-22 18:00","2021-01-19 07:00","2021-01-22 18:00","연속"]
[43,"경남","직할","안민천선#1 T/L","154kV 천선분기T/L 지장송전선로 이설공사","154kV 창원-천선 #1T/L 전선교체에 따른 안전이격확보","2021-01-15 07:00","2021-01-18 18:00","2021-01-15 07:00","2021-01-18 13:00","연속"]
[44,"경남","직할","안민천선#2 T/L","154kV 천선분기T/L 지장송전선로 이설공사","154kV 창원-천선 #1T/L 전선교체에 따른 안전이격확보","2021-01-15 07:00","2021-01-18 18:00","2021-01-15 07:00","2021-01-18 13:00","연속"]
[45,"경남","함안","진영한림정#1 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 345k신김해-북부산T/L 95-96호 횡단구간 안전확보","2021-01-30 07:00","2021-01-31 18:00","2021-01-30 07:00","2021-01-31 18:00","연속"]
[46,"경남","함안","진영한림정#1 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 345k신김해-북부산T/L 95-96호 횡단구간 안전확보","2021-01-02 07:00","2021-01-03 18:00","2021-01-02 07:00","2021-01-03 18:00","연속"]
[47,"경남","함안","진영한림정#1 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 345k신김해-북부산T/L 95-96호 횡단구간 안전확보","2021-01-23 07:00","2021-01-24 18:00","2021-01-23 07:00","2021-01-24 18:00","연속"]
[48,"경남","함안","진영한림정#2 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 345k신김해-북부산T/L 95-96호 횡단구간 안전확보","2021-01-02 07:00","2021-01-03 18:00","2021-01-02 07:00","2021-01-03 18:00","연속"]
[49,"경남","함안","진영한림정#1 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 345k신김해-북부산T/L 95-96호 횡단구간 안전확보","2021-01-02 07:00","2021-01-03 18:00","취소","취소","연속"]
[50,"경남","함안","진영한림정#2 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 345k신김해-북부산T/L 95-96호 횡단구간 안전확보","2021-01-23 07:00","2021-01-24 18:00","2021-01-23 07:00","2021-01-24 18:00","연속"]
[51,"경남","함안","진영한림정#2 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 345k신김해-북부산T/L 95-96호 횡단구간 안전확보","2021-01-02 07:00","2021-01-03 18:00","취소","취소","연속"]
[52,"경남","함안","진영한림정#2 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 345k신김해-북부산T/L 95-96호 횡단구간 안전확보","2021-01-30 07:00","2021-01-31 18:00","2021-01-30 07:00","2021-01-31 18:00","연속"]
[53,"광주전남","순천","호남TP여수TP#2 T/L"," 20-21년 순천전력지사 변전정비회사 총액공사","호남화력S/Y 호남T/P-여수T/P #2T/L GIS #1DS부 가스누기 조치공사","2021-01-14 09:00","2021-01-15 18:00","2021-01-14 09:00","2021-01-15 18:00","연속"]