{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":4,"n_cols":11,"rows_kept":4,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2021년도 2월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]

{"sheet":"345송부","index":1,"n_rows":55,"n_cols":11,"rows_kept":55,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2021년도 2월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","중부S/S 345kV CB 7300","345kV 중부S/S #4M.Tr 증설공사","○ 345kV M.Tr(단상 166.7MVA×3대, 송유풍냉식) × 1Bank 설치 ○ 345kV GIS(362kV, 50kA, 4000A) × 1CB 설치 (GIB 포함) ○ 154kV GIS(170kV, 50kA, 2000A, TR) × 1CCT 설치 ○ 25.8kV 친환경개폐장치(25.8kV, 단모선) × 1식 설치","2021-02-22 09:00","2021-02-26 18:00","2021-02-22 09:00","2021-02-26 18:00","연속"]
[2,"서울","중부","중부S/S 345kV #2 BUS","345kV 중부S/S #4M.Tr 증설공사","○ 345kV M.Tr(단상 166.7MVA×3대, 송유풍냉식) × 1Bank 설치 ○ 345kV GIS(362kV, 50kA, 4000A) × 1CB 설치 (GIB 포함) ○ 154kV GIS(170kV, 50kA, 2000A, TR) × 1CCT 설치 ○ 25.8kV 친환경개폐장치(25.8kV, 단모선) × 1식 설치","2021-02-25 09:00","2021-02-26 18:00","2021-02-25 09:00","2021-02-26 18:00","연속"]
[3,"서울","중부","중부S/S 345kV CB 7372","345kV 중부S/S #4M.Tr 증설공사","○ 345kV M.Tr(단상 166.7MVA×3대, 송유풍냉식) × 1Bank 설치 ○ 345kV GIS(362kV, 50kA, 4000A) × 1CB 설치 (GIB 포함) ○ 154kV GIS(170kV, 50kA, 2000A, TR) × 1CCT 설치 ○ 25.8kV 친환경개폐장치(25.8kV, 단모선) × 1식 설치","2021-02-22 09:00","2021-02-26 18:00","2021-02-22 09:00","2021-02-26 18:00","연속"]
[4,"남서울","영등포","신광명S/S 345kV CB 7172","신광명S/S 345kV GCB 조작시험(7172)","- 차단기 개폐타임 측정 - GCB 조작시험 - 에어링밸브 누기 보수","2021-02-23 09:00","2021-02-23 18:00","2021-02-23 09:00","2021-02-23 18:00","연속"]
[5,"남서울","영등포","신광명S/S 345kV CB 7171","신광명S/S 345kV GCB 조작시험(7171)","- 차단기 개폐타임 측정 - GCB 조작시험 - 에어링밸브 누기 보수","2021-02-22 09:00","2021-02-22 18:00","2021-02-22 09:00","2021-02-22 18:00","연속"]
[6,"남서울","영등포","신광명S/S #3 M.Tr","신광명S/S #3M.Tr 과열개소 및 기타 보수","- 3차측 과열개소 보수 - #1,2차 조작시험 - 부싱 절연유 및 절연열화 측정","2021-02-24 09:00","2021-02-26 18:00","2021-02-24 09:00","2021-02-26 18:00","연속"]
[7,"경기북부","구리","미금S/S 345kV #5 Sh.R","미금S/S 감시제어설비 교체공사","#5Sh.R 관련 감시제어케이블 교체 및 조작,경보 시험","2021-02-17 12:00","2021-02-19 18:00","2021-01-20 12:00","2021-01-22 18:00","연속"]
[8,"경기북부","구리","미금S/S 345kV #2 Sh.R","미금S/S 감시제어설비 교체공사","#2Sh.R 관련 감시제어케이블 교체 및 조작,경보 시험","2021-02-15 09:00","2021-02-17 12:00","2021-01-18 09:00","2021-01-20 12:00","연속"]
[9,"경기북부","구리","미금S/S STATCOM CB","미금S/S STATCOM HMI 교체공사","미금S/S STATCOM HMI 교체공사","2021-02-22 09:00","2021-03-03 18:00","2021-02-22 09:00","2021-03-03 18:00","연속"]
[10,"경기북부","직할","신의정부양주#2 T/L","신의정부S/S 효성제 GIS 하자보수공사","신의정부-양주 #2 T/L GIS 케이블플러그 교체 및 전선관 경로변경(U→I)","2021-02-08 09:00","2021-02-09 18:00","2021-02-08 09:00","2021-02-09 18:00","연속"]
[11,"경기북부","직할","신의정부양주#1 T/L","양주변전소 옥외철구 GIS화 공사","배전반 및 감시제어시스템 이설(모자이크 → SA)","2021-02-15 09:00","2021-02-28 18:00","2021-02-15 09:00","2021-02-28 18:00","연속"]
[12,"경기북부","직할","양주S/S #1 M.Tr","양주변전소 옥외철구 GIS화 공사","배전반 및 감시제어시스템 이설(모자이크 → SA)","2021-02-15 09:00","2021-02-28 18:00","2021-02-15 09:00","2021-02-28 18:00","연속"]
[13,"경기","성남","신안성신성남#2 T/L","345kV 신용인-동서울T/L 지장철탑 이설공사(이천오산)","345kV 신용인-동서울T/L 7-1호 지장철탑 이설(요청자 시행 공사) - 교체구간 : 0.7km, 4회선 1기 본선로, 1기 임시선로 - 345kV 신안성-신성남T/L 64-1호 병가구간","2021-02-17 08:00","2021-03-02 18:00","2021-02-17 08:00","2021-03-02 18:00","연속"]
[14,"경기","성남","신용인동서울#2 T/L","345kV 신용인-동서울T/L 지장철탑 이설공사(이천오산)","345kV 신용인-동서울T/L 7-1호 지장철탑 이설(요청자 시행 공사) - 교체구간 : 0.7km, 4회선 1기 본선로, 1기 임시선로 - 345kV 신안성-신성남T/L 64-1호 병가구간","2021-02-17 08:00","2021-03-02 18:00","2021-02-17 08:00","2021-03-02 18:00","연속"]
[15,"충북","청주","신중부남청주#2 T/L","345kV 신중부-남청주T/L 안전이격 확보공사","- 철탑 2기교체(No.60, 61) - 가철탑 2기 신설(기설선로-&gt가선로 구성)","2021-02-11 08:00","2021-02-14 18:00","2021-02-11 08:00","2021-02-14 18:00","연속"]
[16,"충북","청주","신중부남청주#1 T/L","345kV 신중부-남청주T/L 안전이격 확보공사","- 철탑 2기교체(No.60, 61) - 가철탑 2기 신설(기설선로-&gt가선로 구성)","2021-02-27 07:00","2021-03-01 18:00","2021-02-27 07:00","2021-03-01 18:00","연속"]
[17,"대전충남","청양","보령T/P 345kV #70 BUS","보령T/P 345kV #70 BUS PT 철공진방지회로 설치","○보령T/P 345kV #70 BUS PT 철공진방지회로 설치 - A,B,C 3상 철공진방지회로 설치 및 시험","2021-02-15 09:00","2021-02-19 18:00","2021-02-15 09:00","2021-02-19 18:00","연속"]
[18,"대전충남","청양","아산보령TP#2 T/L","345kV 아산-보령화력#2T/L 누기개소 정비","345kV 아산-보령화력#2T/L 누기개소 정비 - A상 인출부싱 누기개소 정비","2021-02-16 09:00","2021-02-18 18:00","2021-02-22 09:00","2021-02-25 18:00","연속"]
[19,"대전충남","청양","보령T/P 345kV #75 BUS","보령T/P 345kV #75 BUS PT 철공진방지회로 교체","○ 보령T/P 345kV #75 BUS PT 철공진방지회로 교체 - A,B,C 3상 철공진방진회로 교체 설치 및 시험","2021-02-22 09:00","2021-02-26 18:00","2021-02-22 09:00","2021-02-26 18:00","연속"]
[20,"전북","군산","군산새만금#1 T/L","345kV 군산-신김제 등 3개T/L 피뢰기 설치공사","345kV 군산-신김제, 군산-새만금, 청양-군산T/L 송전선로용 피뢰기 1회선 설치","2021-02-15 09:00","2021-02-26 18:00","2021-02-15 09:00","2021-02-26 18:00","연속"]
[21,"전북","김제","신김제S/S #2 M.Tr","신김제S/S 154kV GIS 교체 및 인출송전 재배열공사 (안전이격)","신김제S/S 154kV GIS 교체 안전이격 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","2021-02-16 09:00","2021-03-12 18:00","2021-02-16 09:00","2021-03-12 18:00","연속"]
[22,"전북","직할","신남원광양#2 T/L","신남원S/S GAS 누기 보수공사(2차)-7671,7600","신남원S/S GAS 누기 보수공사 2/15~3/3 : 7671CB A, B, C상 GAS 누기보수, #70BUS 휴전병행 - 3/4~3/5 : 7661DS B GAS 누기보수, #70BUS 휴전병행 - 3/8~3/11 : 7600CB C상 GAS 누기보수, #75BUS 휴전병행","2021-02-15 09:00","2021-03-11 18:00","2021-02-15 09:00","2021-03-11 18:00","연속"]
[23,"전북","직할","신남원S/S 345kV #1BUS","신남원S/S GAS 누기 보수공사(2차)-#70BUS","신남원S/S GAS 누기 보수공사 02/15 ~ 03/11 : 신남원-광양#2T/L 휴전병행","2021-02-15 09:00","2021-03-05 18:00","2021-02-15 09:00","2021-03-05 18:00","연속"]
[24,"광주전남","광주","신광주한빛NP#1 T/L","345kV 신광주-한빛NP#1 T/L 정밀점검","2021년 가공송전 순시점검 위탁공사 345kV 신광주-한빛NP#1 T/L 정밀점검","2021-02-16 09:00","2021-02-23 18:00","2021-02-16 09:00","2021-02-23 18:00","연속"]
[25,"광주전남","광주","신광주한빛NP#2 T/L","345kV 신광주-한빛NP#2 T/L 정밀점검","2021년 가공송전 순시점검 위탁공사 345kV 신광주-한빛NP#2 T/L 정밀점검","2021-02-01 09:00","2021-02-08 18:00","2021-02-01 09:00","2021-02-08 18:00","연속"]
[26,"광주전남","순천","여수T/P 345kV #2 BUS","여수화력S/Y #4M.Tr 및 SW증설 공사","ㅇ362kV #75,76BUS 차단기 설치","2021-02-22 10:00","2021-03-30 18:00","2021-02-22 10:00","2021-03-30 18:00","연속"]
[27,"광주전남","순천","여수T/P #1 Tie-Tr","여수화력S/Y #4M.Tr 및 SW증설 공사","ㅇ345kV #4M.Tr 설치 ㅇ362kV GIS 6CB 설치 등","2021-02-22 10:00","2021-03-03 18:00","2021-02-22 10:00","2021-03-03 18:00","연속"]
[28,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사(건축)","345kV 현장제어동 외벽 설치작업 관련 안전이격 확보","2021-02-01 08:00","2021-02-05 18:00","2021-02-01 08:00","2021-02-05 18:00","연속"]
[29,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사(건축)","345kV 현장제어동 외벽 설치작업 관련 안전이격 확보","2021-02-22 08:00","2021-02-24 18:00","2021-02-22 08:00","2021-02-24 18:00","연속"]
[30,"대구","포항","신월성N/P 345kV CB 7200","신월성S/Y 7200, 7272 GIS 보통점검","신월성S/Y 7200, 7272 GIS 보통점검","2021-02-03 09:30","2021-02-03 18:00","2021-02-03 09:30","2021-02-03 18:00","연속"]
[31,"대구","포항","신월성N/P 345kV CB 7272","신월성 7200,7272 GIS 보통점검","신월성 7200,7272 GIS 보통점검","2021-02-03 09:30","2021-02-03 18:00","2021-02-03 09:30","2021-02-03 18:00","연속"]
[32,"대구","포항","월성N/P 345kV CB 7671","월성S/Y 7671 CB 보통점검","월성S/Y 7671 CB 보통점검","2021-02-25 09:30","2021-02-25 18:00","2021-02-25 09:30","2021-02-25 18:00","연속"]
[33,"대구","포항","월성N/P 345kV CB 7600","월성S/Y 7600 CB 차단기 보통점검","월성S/Y 7600 CB 차단기 보통점검","2021-02-25 09:30","2021-02-25 18:00","2021-02-25 09:30","2021-02-25 18:00","연속"]
[34,"대구","포항","월성N/P 345kV CB 7200","월성S/Y 7200, 7272 GIS 보통점검","월성S/Y 7200, 7272 GIS 보통점검","2021-02-24 09:30","2021-02-24 18:00","2021-02-24 09:30","2021-02-24 18:00","연속"]
[35,"대구","포항","월성N/P 345kV CB 7272","월성S/Y 7200, 7272 GIS 보통점검","월성S/Y 7200, 7272 GIS 보통점검","2021-02-24 09:30","2021-02-24 18:00","2021-02-24 09:30","2021-02-24 18:00","연속"]
[36,"경북","영주","신영주S/S #1 M.Tr","신영주S/S 154kV 옥외철구설비 현대화공사","MOSAIC PNL 개조공사 관련 설비제어 케이블 이설","2021-02-07 08:00","2021-02-07 13:00","2021-02-07 08:00","2021-02-07 13:00","연속"]
[37,"경북","영주","신영주S/S #3 M.Tr","신영주S/S 154kV 옥외철구설비 현대화공사","MOSAIC PNL 개조공사 관련 설비제어 케이블 이설","2021-02-01 13:00","2021-02-01 18:00","2021-02-01 13:00","2021-02-01 18:00","연속"]
[38,"경북","영주","신영주S/S #2 M.Tr","신영주S/S 154kV 옥외철구설비 현대화공사","MOSAIC PNL 개조공사 관련 설비제어 케이블 이설","2021-02-04 13:00","2021-02-04 18:00","2021-02-04 13:00","2021-02-04 18:00","연속"]
[39,"부산울산","울산","신온산신울산#2 T/L","신온산S/S 345kV 용량부족 차단기대체공사","-기설 모선GIB 대체(40/50kA 철거, 60kA 설치) -기설 GIS(CB,DS,ES) 대체 -LCP, GCP 대체","2021-02-16 09:00","2021-03-18 18:00","취소","취소","연속"]
[40,"부산울산","울산","신온산S/S 345kV 신온산S-OIL#5 T/L CB (7100, 7172)","신온산S/S 345kV 용량부족 차단기대체공사","-기설 모선GIB 대체(40/50kA 철거, 60kA 설치) -기설 GIS(CB,DS,ES) 대체 - LCP, GCP 대체","2021-02-16 09:00","2021-03-18 18:00","취소","취소","연속"]
[41,"부산울산","울산","신온산S/S 345kV #1 BUS","신온산S/S 345kV 용량부족 차단기대체공사","-기설 모선GIB 대체(40/50kA 철거, 60kA 설치) -모선 PT 대체 - LCP 대체","2021-02-16 09:00","2021-03-18 18:00","취소","취소","연속"]
[42,"부산울산","울산","신울산S/S #3 M.Tr","20-21년 변전정비회사 총액공사","- 51T CT 인출변경","2021-02-21 09:00","2021-02-21 18:00","2021-02-21 09:00","2021-02-21 18:00","연속"]
[43,"부산울산","울산","북부산울산TP T/L","345kV 신울산복합-북부산T/L 건설공사","345kV 신울산복합-북부산T/L #2 전력선 연결작업 154kV 신온산-성암T/L 신설철탑 전선이동","2021-02-15 07:00","2021-03-03 18:00","취소","취소","연속"]
[44,"경남","직할","신김해북부산#1 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 철탑설치 및 철거 : 각 2기 ○ 전력선 및 가공지선 교체 : 1.4km (93-97호) ○ 스페이서 댐퍼 교체","2021-02-18 07:00","2021-02-24 18:00","2021-02-18 07:00","2021-02-24 18:00","연속"]
[45,"경남","직할","신김해북부산#2 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 철탑설치 및 철거 : 각 2기 ○ 전력선 및 가공지선 교체 : 1.4km (93-97호) ○ 스페이서 댐퍼 교체","2021-02-25 07:00","2021-03-03 18:00","2021-02-25 07:00","2021-03-03 18:00","연속"]
[46,"대구","월성","신월성N/P #2호기 주변압기 CB (7100, 7172)","신월성 2호기 4차 계획예방정비, #2 소내전원절체시험, *조작차단기 : PCB 7100, 7172","○ 소내전원절체시험시 주변압기 모의 신호에 의한 PCB 개방","2021-02-11 09:00","2021-02-11 18:00","2021-02-11 09:00","2021-02-11 18:00","연속"]
[47,"서울","성동","성동S/S #3 M.Tr","성동S/S 345kV #2Sh.R 및 7279 CB 무부하가압용","성동S/S 345kV #2Sh.R 및 7279 CB 무부하가압용","2021-02-08 10:00","2021-02-10 18:00","2021-02-08 10:00","2021-02-10 18:00","연속"]
[48,"서울","성동","미금성동#4 T/L","성동S/S 345kV #2Sh.R 및 7279 CB 무부하가압용","성동S/S 345kV #2Sh.R 및 7279 CB 무부하가압용","2021-02-08 10:00","2021-02-10 18:00","2021-02-08 10:00","2021-02-10 18:00","연속"]
[49,"서울","성동","성동S/S 345kV #2 BUS","성동S/S 345kV #2Sh.R 및 7279 CB 무부하가압용","성동S/S 345kV #2Sh.R 및 7279 CB 무부하가압용","2021-02-08 10:00","2021-02-10 18:00","2021-02-08 10:00","2021-02-10 18:00","연속"]
[50,"광주전남","한빛","한빛3호기 기동변압기 CB(7800,7871)","NSPB 설비개선 및 78 BAY SYNC 회로 점검","NSPB 설비개선 및 78 BAY SYNC 회로 점검","2021-02-23 09:00","2021-02-24 18:00","2021-02-23 09:00","2021-02-24 18:00","연속"]
[51,"경남","하동","하동8호기 주변압기 CB(7800,7872)","전력용변압기 법정 정기검사","전력용변압기 법정 정기검사","2021-02-08 14:00","2021-03-22 13:30","2021-02-08 14:00","2021-03-22 13:30","연속"]

{"sheet":"154송부","index":2,"n_rows":120,"n_cols":11,"rows_kept":120,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2021년도 2월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동휘경#1 T/L","154kV GIS 에어누기 보수","에어누기 보수, 차단기 조작시험","2021-02-16 09:30","2021-02-16 18:00","2021-02-16 09:30","2021-02-16 18:00","연속"]
[2,"서울","중부","중부S/S 154kV #65 BUS","345kV 중부S/S #4M.Tr 증설공사","○ 345kV M.Tr(단상 166.7MVA×3대, 송유풍냉식) × 1Bank 설치 ○ 345kV GIS(362kV, 50kA, 4000A) × 1CB 설치 (GIB 포함) ○ 154kV GIS(170kV, 50kA, 2000A, TR) × 1CCT 설치 ○ 25.8kV 친환경개폐장치(25.8kV, 단모선) × 1식 설치","2021-02-25 15:00","2021-02-26 18:00","2021-02-25 15:00","2021-02-26 18:00","연속"]
[3,"서울","중부","중부S/S 154kV #60 BUS","345kV 중부S/S #4M.Tr 증설공사","○ 345kV M.Tr(단상 166.7MVA×3대, 송유풍냉식) × 1Bank 설치 ○ 345kV GIS(362kV, 50kA, 4000A) × 1CB 설치 (GIB 포함) ○ 154kV GIS(170kV, 50kA, 2000A, TR) × 1CCT 설치 ○ 25.8kV 친환경개폐장치(25.8kV, 단모선) × 1식 설치","2021-02-25 09:00","2021-02-25 14:00","2021-02-25 09:00","2021-02-25 14:00","연속"]
[4,"남서울","동서울","동서울강동#2 T/L","세종-포천 고속도로건설 지장송전선로 지중화(이설)공사","임시철탑 건설 및 기설철탑과 임시철탑간 전력선 이설","2021-02-26 09:00","2021-03-03 18:00","2021-02-26 09:00","2021-03-03 18:00","매일"]
[5,"남서울","영등포","가양등촌#1 T/L","154kV 가양-등촌T/L 일부구간 지장이설공사","○ 지중송전 : 154kV OF 1200 x 2C x 0.320km 신설 및 철거 ○ 비금속광케이블(OFC) 신설 및 철거 ○ 관로 320m 신설 및 철거(요청자 시행)","2021-02-23 09:00","2021-04-19 18:00","2021-02-23 09:00","2021-04-19 18:00","연속"]
[6,"남서울","영등포","구공대림#1 T/L","154kV 구공S/S 가산메트로#1, 2T/L 증설공사","154kV 구공S/S 가산메트로#1, 2T/L 증설공사(#2T/L 설치)","2021-02-19 17:00","2021-02-20 17:00","2021-02-19 17:00","2021-02-20 17:00","연속"]
[7,"남서울","영등포","구공대림#2 T/L","154kV 구공S/S 가산메트로#1, 2T/L 증설공사","154kV 구공S/S 가산메트로#1T/L 설치","2021-02-04 17:00","2021-02-05 17:00","2021-02-04 17:00","2021-02-05 17:00","연속"]
[8,"남서울","영등포","구공대림#1 T/L","154kV 구공S/S 가산메트로#1, 2T/L 증설공사","154kV 구공S/S 가산메트로#1, 2T/L 증설공사(#2T/L 설치)","2021-02-25 17:00","2021-02-26 17:00","2021-02-25 17:00","2021-02-26 17:00","연속"]
[9,"남서울","영등포","구공S/S 154kV #66 BUS","154kV 구공S/S 가산메트로#1, 2T/L 증설공사","154kV 구공S/S 가산메트로#1, 2T/L 증설공사(#2T/L 설치)","2021-02-22 09:00","2021-02-26 18:00","2021-02-22 09:00","2021-02-26 18:00","연속"]
[10,"남서울","영등포","구공S/S 154kV #60 BUS","154kV 구공S/S 가산메트로#1, 2T/L 증설공사","154kV 구공S/S 가산메트로#1T/L 설치","2021-02-01 09:00","2021-02-05 18:00","2021-02-01 09:00","2021-02-05 18:00","연속"]
[11,"남서울","영등포","구공S/S 154kV #61 BUS","154kV 구공S/S 가산메트로#1, 2T/L 증설공사","154kV 구공S/S 가산메트로#1, 2T/L 증설공사(#2T/L 설치)","2021-02-15 09:00","2021-02-21 18:00","2021-02-15 09:00","2021-02-21 18:00","연속"]
[12,"남서울","영등포","구공대림#2 T/L","154kV 구공S/S 가산메트로#1, 2T/L 증설공사","154kV 구공S/S 가산메트로#1T/L 설치","2021-02-09 17:00","2021-02-10 17:00","2021-02-09 17:00","2021-02-10 17:00","연속"]
[13,"남서울","영등포","구공S/S 154kV #65 BUS","154kV 구공S/S 가산메트로#1, 2T/L 증설공사","154kV 구공S/S 가산메트로#1T/L 설치","2021-02-06 09:00","2021-02-10 18:00","2021-02-06 09:00","2021-02-10 18:00","연속"]
[14,"남서울","영등포","대방신길#2 T/L","154kV 대방인출전력구 OF케이블 선종교체공사","대방 인출전력구 내 154kV 대방-신길#2T/L 선종교체 공사 - 구간 : 대방S/S~J/B#38 - 교체전 : OF 1200, 교체후 : XLPE 1200","2021-02-15 09:00","2021-03-26 18:00","2021-02-15 09:00","2021-03-26 18:00","연속"]
[15,"남서울","영등포","오류S/S 154kV #1 BUS","154kV 천왕-구로,오류T/L 지장송전선로이설공사","구 간 : 154㎸ 천왕S/S S/J#0 ∼ 신설 M/H#1 공사기간 : 2020. 10. 26 ~ 2021. 4. 25 선종 및 회선길이 : 154kV OF 1,200㎟ × 2C × 0.144km, 154kV OF 600㎟ × 2C × 0.144km 케이블 철거 규격 및 긍장 : OF 1200㎟ × 1구간× 2C × 0.144km, OF 600㎟ × 1구간× 2C × 0.144km","2021-02-08 10:00","2021-02-08 10:15","2021-02-08 10:00","2021-02-08 10:15","연속"]
[16,"남서울","영등포","영등포목동#2 T/L","목동S/S 170kV GIS 차단기 동작시험","전자변 교체, 러버히터 설치","2021-02-01 09:00","2021-02-01 18:00","2021-02-01 09:00","2021-02-01 18:00","연속"]
[17,"남서울","영등포","신정목동#2 T/L","목동S/S 170kV GIS 차단기 동작시험","전자변 교체, 러버히터 설치","2021-02-02 09:00","2021-02-02 18:00","취소","취소","연속"]
[18,"남서울","영등포","목동양천#1 T/L","목동S/S 170kV GIS 차단기 동작시험","전자변 교체, 러버히터 설치","2021-02-03 09:00","2021-02-03 18:00","취소","취소","연속"]
[19,"경기북부","구리","운천S/S 154kV CB 6100","`20~21 구리전력 변전정비 총액공사","운천S/S 154kV BUS-TIE GIS 개폐타임측정","2021-02-24 09:00","2021-02-24 18:00","2021-02-24 09:00","2021-02-24 18:00","연속"]
[20,"경기","군포","서서울율전#2 T/L","154kV 서서울-율전T/L 5,6호 안전이격확보공사","철탑교체 2기, 전선교체 0.542km(12가닥), 기타(현수애자, 금구류 교체 등)","2021-02-20 08:00","2021-02-20 19:00","2021-02-20 08:00","2021-02-20 19:00","연속"]
[21,"경기","군포","서서울율전#1 T/L","154kV 서서울-율전T/L 5,6호 안전이격확보공사","철탑교체 2기, 전선교체 0.542km(12가닥), 기타(현수애자, 금구류 교체 등)","2021-02-21 08:00","2021-02-27 19:00","2021-02-21 08:00","2021-02-27 19:00","연속"]
[22,"경기","군포","서서울율전#2 T/L","154kV 서서울-율전T/L 5,6호 안전이격확보공사","철탑교체 2기, 전선교체 0.542km(12가닥), 기타(현수애자, 금구류 교체 등)","2021-02-28 08:00","2021-03-04 19:00","2021-02-28 08:00","2021-03-04 19:00","연속"]
[23,"경기","평택","포승청북 T/L","345kV 신온양-서서울외 2개T/L 지장철탑이설공사(본선로)","지지물(관형주) 2기 신설, 임시선로 1기 철거 전력선교체 No.42~46","2021-02-22 08:00","2021-02-26 18:00","2021-02-22 08:00","2021-02-26 18:00","연속"]
[24,"경기","평택","만호청북#1 T/L","345kV 신온양-서서울외 2개T/L 지장철탑이설공사(본선로)","지지물(관형주) 2기 신설, 임시선로 1기 철거 전력선교체 No.42~46","2021-02-16 08:00","2021-02-21 18:00","2021-02-16 08:00","2021-02-21 18:00","연속"]
[25,"강원","동해","동해T/P 154kV #2 BUS","동해화력S/Y 장기사용 170kV GIS 대체공사","- 170kV GIS 7CCT 대체 - 동해화력S/Y 변전소 SA화","2021-02-17 11:00","2021-02-21 18:00","2021-02-17 11:00","2021-02-21 18:00","연속"]
[26,"강원","동해","이원동해TP T/L","동해화력S/Y 장기사용 170kV GIS 대체공사","- 170kV GIS 7CCT 대체 - 동해화력S/Y 변전소 SA화","2021-02-15 10:00","2021-03-19 18:00","2021-02-15 10:00","2021-03-19 18:00","연속"]
[27,"강원","동해","동해T/P 154kV #1 BUS","동해화력S/Y 장기사용 170kV GIS 대체공사","- 신설 BUS TIE #1BUS 무부하 가압","2021-02-15 11:00","2021-02-16 11:00","2021-02-15 11:00","2021-02-16 11:00","연속"]
[28,"강원","동해","동해T/P 154kV #2 BUS","동해화력S/Y 장기사용 170kV GIS 대체공사","- 신설 BUS TIE #2BUS 무부하 가압","2021-02-16 11:00","2021-02-17 11:00","2021-02-16 11:00","2021-02-17 11:00","연속"]
[29,"강원","동해","동해T/P 154kV #1 BUS","동해화력S/Y 장기사용 170kV GIS 대체공사","- 170kV GIS 7CCT 대체 - 동해화력S/Y 변전소 SA화","2021-02-21 18:00","2021-03-03 18:00","2021-02-21 18:00","2021-03-03 18:00","연속"]
[30,"강원","동해","이원도계 T/L","154kV 이원-도계 T/L COM Fail Alarm 동작관련 원인규명","ㅇ 제작사(YPP) 합동 원인규명 점검","2021-02-02 10:30","2021-02-02 18:00","2021-02-02 10:30","2021-02-02 18:00","연속"]
[31,"강원","원주","남원주원주#2 T/L","2021년 원주전력지사 변전정비회사 총액공사","#1,2,6DS 누기보수","2021-02-03 10:00","2021-02-03 18:00","2021-02-03 10:00","2021-02-03 18:00","연속"]
[32,"강원","원주","남원주원주#1 T/L","2021년 원주전력지사 변전정비회사 총액공사","임시 SPS 철거 및 차단기 매커니즘 누기보수","2021-02-02 10:00","2021-02-02 18:00","2021-02-02 10:00","2021-02-02 18:00","연속"]
[33,"대전충남","아산","둔포직산#1 T/L","154kV 직산분기T/L 건설공사","ㅇ 피뢰기 설치 : 4회선 12기","2021-02-16 09:00","2021-02-19 18:00","취소","취소","연속"]
[34,"대전충남","아산","둔포직산#2 T/L","154kV 직산분기T/L 건설공사","ㅇ 피뢰기 설치 : 4회선 12기","2021-02-20 08:00","2021-02-23 17:00","취소","취소","연속"]
[35,"대전충남","아산","한샘직산#1 T/L","154kV 직산분기T/L 건설공사","ㅇ 피뢰기 설치 : 4회선 12기","2021-02-20 08:00","2021-02-23 17:00","취소","취소","연속"]
[36,"대전충남","아산","한샘직산#2 T/L","154kV 직산분기T/L 건설공사","ㅇ 피뢰기 설치 : 4회선 12기","2021-02-16 08:00","2021-02-19 17:00","취소","취소","연속"]
[37,"대전충남","아산","서천안탕정#2 T/L","154kV 인주-불당T/L C/H 건설공사","154kV 인주-불당T/L C/H 건설공사 - 임시선로 철거 및 본선로 구성","2021-02-08 09:00","2021-02-14 18:00","취소","취소","연속"]
[38,"대전충남","아산","인주탕정#1 T/L","154kV 인주-불당T/L C/H 건설공사","154kV 인주-불당T/L C/H 건설공사 - 임시선로 철거 및 본선로 구성","2021-02-08 09:00","2021-02-14 18:00","취소","취소","연속"]
[39,"대전충남","아산","인주탕정#2 T/L","154kV 인주-불당T/L C/H 건설공사","154kV 인주-불당T/L C/H 건설공사 - 임시선로 철거 및 본선로 구성","2021-02-15 09:00","2021-02-21 18:00","취소","취소","연속"]
[40,"대전충남","아산","서천안탕정#1 T/L","154kV 인주-불당T/L C/H 건설공사","154kV 인주-불당T/L C/H 건설공사 - 임시선로 철거 및 본선로 구성","2021-02-15 09:00","2021-02-21 18:00","취소","취소","연속"]
[41,"대전충남","청양","신서천대천#2 T/L","대천-서천#2T/L 송전선로 보호반 시험(SPS 시험)","대천-서천#2T/L SPS설치관련 송전선로 보호반 시험","2021-02-02 13:00","2021-02-02 18:00","2021-02-02 13:00","2021-02-02 18:00","연속"]
[42,"대전충남","청양","신서천대천#1 T/L","대천-서천#1T/L 송전선로 보호반 시험(SPS 시험)","대천-서천#1T/L SPS 설치 관련 송전선로 보호반 시험","2021-02-02 09:00","2021-02-02 13:00","2021-02-02 09:00","2021-02-02 13:00","연속"]
[43,"대전충남","청양","신서천옥산#2 T/L","옥산-서천#2T/L 송전선로 보호반 시험(SPS 시험)","옥산-서천#2T/L SPS 설치 관련 송전선로 보호반 시험","2021-02-01 13:00","2021-02-01 18:00","2021-02-01 13:00","2021-02-01 18:00","연속"]
[44,"대전충남","청양","신서천옥산#1 T/L","옥산-서천#1T/L 송전선로 보호반 시험(SPS 시험)","옥산-서천#1T/L SPS 설치 관련 송전선로 보호반 시험","2021-02-01 09:00","2021-02-01 13:00","2021-02-01 09:00","2021-02-01 13:00","연속"]
[45,"대전충남","대전","팔봉두마#2 T/L","두마S/S 154kV GIS DS부 정밀점검","두마S/S 154kV GIS DS부 정밀점검 - 627, 6233BAY","2021-02-08 09:00","2021-02-10 18:00","2021-02-08 09:00","2021-02-10 18:00","연속"]
[46,"대전충남","대전","팔봉두마#1 T/L","두마S/S 154kV GIS DS부 정밀점검","두마S/S 154kV GIS DS부 정밀점검 - 617, 6133BAY","2021-02-02 09:00","2021-02-04 18:00","2021-02-02 09:00","2021-02-04 18:00","연속"]
[47,"대전충남","대전","신계룡두마#1 T/L","154kV 신계룡-두마T/L OPGW 증설공사","신계룡S/S ~ 두마S/S 간 가공지선(ACSR 97SQ)를 OPGW/100SQ로 변경","2021-02-23 08:00","2021-02-25 18:00","취소","취소","매일"]
[48,"대전충남","대전","신계룡두마#2 T/L","154kV 신계룡-두마T/L OPGW 증설공사","신계룡S/S ~ 두마S/S 간 가공지선(ACSR 97SQ)를 OPGW/100SQ로 변경","2021-02-23 08:00","2021-02-25 18:00","취소","취소","매일"]
[49,"전북","군산","내초군장#1 T/L","154kV 군장S/S SMG에너지T/L 신규수용공사(시험가압)","170kV GIS X 1CCT","2021-02-17 10:00","2021-02-18 10:00","2021-02-17 10:00","2021-02-18 10:00","연속"]
[50,"전북","군산","함열영등#2 T/L","154KV 낭산 분기T/L 건설공사","○ 위치 : 154kV 영등-함열T/L 56-57호 ~ 신설 154kV 낭산S/S ○ 규모 : ACSR 410×2B×4C×2.065km, 철탑 7기 ○ 금회작업 내용 : 본선로 구성(신설 1호 ~ 신설 낭산S/S)","2021-02-15 07:00","2021-03-18 18:00","2021-02-15 07:00","2021-03-18 18:00","연속"]
[51,"전북","김제","신김제S/S 154kV #65 BUS","신김제S/S 154kV GIS 교체 및 인출송전 재배열공사(시험가압)","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","2021-02-18 09:00","2021-02-18 18:00","2021-02-18 09:00","2021-02-18 18:00","연속"]
[52,"전북","김제","신김제S/S 154kV SEC CB 65660","신김제S/S 154kV GIS 교체 및 인출송전 재배열공사","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","2021-02-16 09:00","2021-02-18 18:00","2021-02-16 09:00","2021-02-18 09:00","연속"]
[53,"전북","김제","신김제S/S 154kV #66 BUS","신김제S/S 154kV GIS 교체 및 인출송전 재배열공사","- 154kV GIS 14CCT, PT 2BAY 교체 - 재배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","2021-02-16 09:00","2021-02-18 18:00","2021-02-16 09:00","2021-02-18 18:00","연속"]
[54,"전북","김제","신김제S/S 154kV SEC CB 66670","신김제S/S 154kV GIS 교체 및 인출송전 재배열공사","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","2021-02-16 09:00","2021-02-18 18:00","2021-02-16 09:00","2021-02-18 18:00","연속"]
[55,"전북","김제","신김제S/S 154kV CB 6200","신김제S/S 154kV GIS 교체 및 인출송전 재배열공사","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","2021-02-16 09:00","2021-03-12 18:00","2021-02-16 09:00","2021-03-12 18:00","연속"]
[56,"전북","김제","신김제정공#1 T/L","신김제S/S 154kV GIS 교체 및 인출송전 재배열공사 (시험가압)","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","2021-02-18 09:00","2021-02-18 18:00","2021-02-18 09:00","2021-02-18 18:00","연속"]
[57,"전북","김제","신김제S/S 154kV SEC CB 60610","신김제S/S 154kV GIS 교체 및 인출송전 재배열공사","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","2021-02-18 18:00","2021-02-27 18:00","2021-02-18 18:00","2021-02-27 18:00","연속"]
[58,"전북","김제","신김제S/S 154kV #61 BUS","신김제S/S 154kV GIS 교체 및 인출송전 재배열공사","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","2021-02-18 18:00","2021-02-27 18:00","2021-02-18 18:00","2021-02-27 18:00","연속"]
[59,"전북","김제","신김제S/S 154kV SEC CB 61620","신김제S/S 154kV GIS 교체 및 인출송전 재배열공사","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","2021-02-18 18:00","2021-02-27 18:00","2021-02-18 18:00","2021-02-27 18:00","연속"]
[60,"전북","김제","신김제남전주#1 T/L","신김제S/S 154kV GIS 교체 및 인출송전 재배열공사 (안전이격)","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","2021-02-17 10:00","2021-02-17 12:00","2021-02-17 10:00","2021-02-17 12:00","연속"]
[61,"전북","김제","신김제S/S 154kV CB 6100","신김제S/S 154kV GIS 교체 및 인출송전 재배열공사(시험가압)","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","2021-02-26 09:00","2021-02-27 18:00","2021-02-26 09:00","2021-02-27 18:00","연속"]
[62,"전북","김제","신김제S/S 154kV #60 BUS","신김제S/S 154kV GIS 교체 및 인출송전 재배열공사(시험가압)","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","2021-02-26 09:00","2021-02-27 18:00","2021-02-26 09:00","2021-02-27 18:00","연속"]
[63,"전북","김제","신김제정공#1 T/L","신김제S/S 154kV GIS 교체 및 인출송전 재배열공사(시험가압)","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","2021-02-26 09:00","2021-02-27 18:00","2021-02-26 09:00","2021-02-27 18:00","연속"]
[64,"전북","김제","신김제S/S 154kV CB 6100","정공S/S 170kV GIS 교체공사","170kV GIS 7BAY 철거 및 설치 (6200 신설) 170kV GIS 3BAY 설치 기타부대공사","2021-02-22 09:30","2021-03-05 18:00","2021-02-22 09:30","2021-03-05 18:00","연속"]
[65,"전북","김제","정공S/S 154kV #2 BUS","정공S/S 170kV GIS 교체공사","170kV GIS 7BAY 철거 및 설치  (6200 신설) 170kV GIS 3BAY 설치 기타부대공사","2021-02-22 09:30","2021-02-25 13:00","2021-02-22 09:30","2021-02-25 13:00","연속"]
[66,"전북","김제","신김제정공#1 T/L","정공S/S 170kV GIS 교체공사 무부하가압","170kV GIS 7BAY 철거 및 설치  (6200 신설) 170kV GIS 3BAY 설치 기타부대공사","2021-02-24 13:00","2021-02-25 13:00","2021-02-24 13:00","2021-02-25 13:00","연속"]
[67,"전북","김제","정공S/S 154kV #1 BUS","정공S/S 170kV GIS 교체공사","170kV GIS 7BAY 철거 및 설치  (6200 신설) 170kV GIS 3BAY 설치 기타부대공사","2021-02-25 13:00","2021-02-28 13:00","2021-02-25 13:00","2021-02-28 13:00","연속"]
[68,"전북","김제","신김제정공#1 T/L","정공S/S 170kV GIS 교체공사 무부하가압","170kV GIS 7BAY 철거 및 설치  (6200 신설) 170kV GIS 3BAY 설치 기타부대공사","2021-02-27 13:00","2021-02-28 13:00","2021-02-27 13:00","2021-02-28 13:00","연속"]
[69,"전북","김제","정공S/S 154kV #2 BUS","정공S/S 170kV GIS 교체공사","170kV GIS 7BAY 철거 및 설치  (6200 신설) 170kV GIS 3BAY 설치 기타부대공사","2021-02-28 13:00","2021-03-05 13:00","2021-02-28 13:00","2021-03-05 13:00","연속"]
[70,"전북","직할","신남원남원#1 T/L","154kV 남원S/S 옥외철구설비 GIS화 공사","○ 154kV 신남원-남원#1T/L 인출구간 변경 및 GIS설비로 이전","2021-02-22 08:00","2021-03-11 18:00","취소","취소","연속"]
[71,"전북","직할","남원임실#2 T/L","154kV 남원S/S 옥외철구설비 GIS화 공사","○ 154kV 남원-임실#2T/L 인출구간 변경 및 GIS설비로 이전","2021-02-22 08:00","2021-03-11 18:00","취소","취소","연속"]
[72,"전북","직할","북전주봉동#2 T/L","2020~2021년 전북 직할 변전정비회사 총액공사","○ 관내 154kV 이상 차단기 점검공사 - 북전주S/S 154kV 북전주-봉동#2/TL 전자변교체(조작시험포함)","2021-02-25 09:00","2021-02-25 18:00","취소","취소","연속"]
[73,"광주전남","강진","진도서제주HVDC #1 Pole CB","'20~'21년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) #1 MonoPole 연차점검","2021-02-27 09:00","2021-03-13 18:00","2021-02-27 09:00","2021-03-13 18:00","연속"]
[74,"광주전남","광주","신광주계림#1 T/L","20년 광주변전정비회사 총액공사","2DS 모선순간 순간압력게이지 불량 조치","2021-02-03 09:00","2021-02-03 18:00","취소","취소","연속"]
[75,"광주전남","광주","신광주일곡#2 T/L","154kV 신광주-일곡T/L 지중화 전력구공사","수직구 세미실드 장비반입에 따른 선로인근 대형장비(크레인) 작업","2021-02-24 07:00","2021-02-26 18:00","취소","취소","매일"]
[76,"광주전남","광주","신화순나주#2 T/L","2020~21년 직할 송전정비회사 총액공사","154kV 신화순-매월#2T/L 피뢰기 설치공사 관련 안전이격거리 확보차","2021-02-15 08:00","2021-02-15 18:00","2021-02-15 08:00","2021-02-15 18:00","연속"]
[77,"광주전남","광주","신광주일곡#2 T/L","2020~21년 직할 송전정비회사 총액공사","154kV 일곡-비아#2T/L 피뢰기 설치공사 관련 안전이격거리 확보차","2021-02-08 08:00","2021-02-08 13:00","취소","취소","연속"]
[78,"광주전남","광주","장성영광#1 T/L","2020~21년 직할 송전정비회사 총액공사","154kV 하남-장성#2T/L 피뢰기 설치공사 관련 안전이격거리 확보차","2021-02-04 08:00","2021-02-05 18:00","취소","취소","연속"]
[79,"광주전남","광주","신광주장성#1 T/L","154kV 신광주-장성#1T/L 피뢰기 설치공사","154kV 신광주-장성#1T/L 피뢰기 설치공사 - 피뢰기 설치 67기(No.6~72호)","2021-02-22 09:00","2021-02-23 18:00","취소","취소","매일"]
[80,"광주전남","순천","광양순천#1 T/L","세니온 송전선로 보호IED성능개선","세니온 송전선로 보호IED성능개선","2021-02-01 09:00","2021-02-01 18:00","취소","취소","연속"]
[81,"광주전남","순천","순천율촌#1 T/L","세니온 송전선로 보호IED성능개선","세니온 송전선로 보호IED성능개선","2021-02-03 10:00","2021-02-03 18:00","취소","취소","연속"]
[82,"광주전남","순천","순천승주#2 T/L","YPPP제 송전선로 계전기 성능개선","YPPP제 송전선로 계전기 성능개선","2021-02-16 10:00","2021-02-16 18:00","취소","취소","연속"]
[83,"광주전남","순천","순천승주#1 T/L","세니온 송전선로 보호IED성능개선","세니온 송전선로 보호IED성능개선","2021-02-09 10:00","2021-02-09 18:00","취소","취소","연속"]
[84,"광주전남","순천","순천율촌#2 T/L","세니온 송전선로 보호IED성능개선","세니온 송전선로 보호IED성능개선","2021-02-04 10:00","2021-02-04 18:00","취소","취소","연속"]
[85,"광주전남","순천","광양순천#2 T/L","세니온 송전선로 보호IED성능개선","세니온 송전선로 보호IED성능개선","2021-02-02 09:00","2021-02-02 18:00","취소","취소","연속"]
[86,"광주전남","직할","매월화정#1 T/L","154kV 매월-화정 #1T/L (보호배전반 교체)","2020~2021년 광주전남본부 직할 변전정비회사 총액공사 - 내용 : 보호배전반 교체","2021-02-15 09:00","2021-02-17 18:00","취소","취소","연속"]
[87,"광주전남","직할","일곡비아#2 T/L","2020~21년 직할 송전정비회사 총액공사","154kV 일곡-비아#2T/L 피뢰기 설치공사 (12기)","2021-02-08 08:00","2021-02-09 18:00","취소","취소","연속"]
[88,"광주전남","직할","하남장성#2 T/L","2020~21년 직할 송전정비회사 총액공사","154kV 비아-하남#2T/L 피뢰기 설치공사 관련 4회선 구간 안전이격거리 확보(18기) 및 154kV 하남-장성#2T/L 피뢰기 설치공사 (35기)","2021-02-01 08:00","2021-02-05 18:00","취소","취소","연속"]
[89,"광주전남","직할","평동왕곡#2 T/L","154kV 왕곡S/S #1,4M.Tr 증설공사(#4M.Tr 측)","154kV 왕곡S/S #1,4M.Tr 증설공사","2021-02-26 10:00","2021-03-09 18:00","2021-02-26 10:00","2021-03-09 18:00","연속"]
[90,"광주전남","직할","왕곡나주#2 T/L","154kV 왕곡S/S #1,4M.Tr 증설공사(#4M.Tr 측)","154kV 왕곡S/S #1,4M.Tr 증설공사","2021-02-26 10:00","2021-03-09 18:00","2021-02-26 10:00","2021-03-09 18:00","연속"]
[91,"광주전남","목포","장성영광#2 T/L","154kV 장성-영광T/L 안전이격확보공사","인크로징 2기 철거 및 1기 설치","2021-02-15 08:00","2021-02-15 18:00","2021-02-15 08:00","2021-02-15 18:00","연속"]
[92,"광주전남","목포","장성영광#1 T/L","154kV 장성-영광T/L 안전이격확보공사","인크로징 2기 철거 및 1기 설치","2021-02-16 08:00","2021-02-19 18:00","2021-02-16 08:00","2021-02-19 18:00","연속"]
[93,"광주전남","목포","장성영광#2 T/L","154kV 장성-영광T/L 안전이격확보공사","인크로징 2기 철거 및 1기 설치","2021-02-22 08:00","2021-02-25 18:00","2021-02-22 08:00","2021-02-25 18:00","연속"]
[94,"대구","달성","고령다산#1 T/L","고령변전소 154kV 송전선로 인출변경공사","고령변전소 154kV 송전선로 인출변경공사","2021-02-28 08:00","2021-03-05 18:00","취소","취소","연속"]
[95,"대구","달성","고령쌍림#2 T/L","고령변전소 154kV 송전선로 인출변경공사","고령변전소 154kV 송전선로 인출변경공사","2021-02-22 08:00","2021-02-28 18:00","취소","취소","연속"]
[96,"대구","달성","고령S/S 154kV #65 BUS","고령변전소 154kV 송전선로 인출변경공사","고령변전소 154kV 송전선로 인출변경공사","2021-02-26 18:00","2021-02-27 18:00","취소","취소","연속"]
[97,"대구","달성","고령S/S 154kV #66 BUS","고령변전소 154kV 송전선로 인출변경공사","고령변전소 154kV 송전선로 인출변경공사","2021-02-26 17:00","2021-02-26 18:00","취소","취소","연속"]
[98,"대구","달성","고령쌍림#1 T/L","고령변전소 154kV 송전선로 인출변경공사","고령변전소 154kV 송전선로 인출변경공사","2021-02-28 08:00","2021-03-04 18:00","취소","취소","연속"]
[99,"대구","달성","고령다산#2 T/L","고령변전소 154kV 송전선로 인출변경공사","고령변전소 154kV 송전선로 인출변경공사","2021-02-22 08:00","2021-02-27 18:00","취소","취소","연속"]
[100,"대구","달성","달성상인#1 T/L","달성S/S 달성-월배T/L SW 증설(TEST선로)","달성S/S 달성-월배T/L SW 증설(TEST선로)","2021-02-27 09:00","2021-02-28 18:00","2021-02-27 09:00","2021-02-28 18:00","연속"]
[101,"대구","달성","달성S/S 154kV #1 BUS","달성S/S 달성-월배T/L SW 증설","달성S/S 달성-월배T/L SW 증설","2021-02-23 09:00","2021-02-28 18:00","2021-02-23 09:00","2021-02-28 18:00","연속"]
[102,"부산울산","울산","두왕영남TP#1 T/L","울산S/S 154kV SW 증설공사","○ 울산-영남T/P #1T/L 전력케이블 포설 및 접속(남부건설본부 지중건설부) ○ 두왕-울산#1T/L, 울산-영남T/P #1T/L 보호반 이설(설비보강부) ○ 울산-울산T/P #1T/L 전력케이블 선종교체(설비보강부) ○ 두왕-울산#1T/L, 울산-영남T/P #1T/L 최초가압 및 실부하가압(설비보강부)","2021-02-15 07:00","2021-03-12 18:00","취소","취소","연속"]
[103,"부산울산","울산","신울산언양#2 T/L","철탑 추락방지장치 설치공사","추락방지장치 와이어형(수직,수평) 시범설치공사 - 구간 : 154kV 신울산-언양T/L No.66,66-1","2021-02-05 07:00","2021-02-05 18:00","2021-02-05 07:00","2021-02-05 18:00","연속"]
[104,"부산울산","울산","신울산언양#1 T/L","철탑 추락방지장치 설치공사","추락방지장치 와이어형(수직,수평) 시범설치공사 - 구간 : 154kV 신울산-언양T/L No.66,66-1","2021-02-04 07:00","2021-02-04 18:00","2021-02-04 07:00","2021-02-04 18:00","연속"]
[105,"부산울산","울산","울산울산TP#1 T/L","울산S/S 154kV SW 증설공사","○ 울산-영남T/P #1T/L 전력케이블 포설 및 접속(남부건설본부 지중건설부) ○ 두왕-울산#1T/L, 울산-영남T/P #1T/L 보호반 이설(설비보강부) ○ 울산-울산T/P #1T/L 전력케이블 선종교체(설비보강부) ○ 두왕-울산#1T/L, 울산-영남T/P #1T/L 최초가압 및 실부하가압(설비보강부)","2021-02-15 07:00","2021-03-12 18:00","취소","취소","연속"]
[106,"부산울산","울산","울주외동#1 T/L","철탑 추락방지장치 설치공사","추락방지장치 와이어형(수직,수평) 시범설치공사 - 구간 : 154kV 울주-외동T/L No.7,9","2021-02-08 07:00","2021-02-08 18:00","2021-02-08 07:00","2021-02-08 18:00","연속"]
[107,"부산울산","울산","울주외동#2 T/L","철탑 추락방지장치 설치공사","추락방지장치 와이어형(수직,수평) 시범설치공사 - 구간 : 154kV 울주-외동T/L No.7,9","2021-02-09 07:00","2021-02-09 18:00","2021-02-09 07:00","2021-02-09 18:00","연속"]
[108,"부산울산","직할","부산수정#1 T/L","20-21년 직할 변전정비회사 총액공사","부산-수정#1T/L 43CA OFF 오경보 조치 및 PITR 업데이트","2021-02-01 09:30","2021-02-01 18:00","취소","취소","연속"]
[109,"부산울산","직할","부산수정#2 T/L","20-21년 직할 변전정비회사 총액공사","부산-수정#2T/L 43CA OFF 오경보 조치 및 PITR 업데이트","2021-02-02 09:30","2021-02-02 18:00","취소","취소","연속"]
[110,"경남","진주","삼천포사천#1 T/L","사천S/S 154kV #2Sh.C GIS CB(6279) 제작사 점검","사천S/S 154kV #2Sh.C GIS CB(6279) 제작사 점검 시험가압용T/L","2021-02-25 17:00","2021-02-25 18:00","2021-02-25 17:00","2021-02-25 18:00","연속"]
[111,"경남","통영","신고성고성 T/L","154kV 신고성-고성/L 피뢰기설치공사","154kV 신고성-통영T/L 95호, 154kV 고성분기T/L 1~8호","2021-02-24 08:00","2021-02-24 18:00","2021-02-28 08:00","2021-02-28 18:00","연속"]
[112,"경남","통영","신고성삼천포#1 T/L","154kV 신고성-삼천포T/L 피뢰기설치공사","154kV 신고성-삼천포#1T/L 피뢰기설치공사(6~22호)","2021-02-22 08:00","2021-02-23 18:00","취소","취소","매일"]
[113,"경남","함안","진영한림정#2 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 345k신김해-북부산T/L 95-96호 횡단구간 안전확보","2021-02-27 07:00","2021-02-28 18:00","2021-02-27 07:00","2021-02-28 18:00","연속"]
[114,"경남","함안","진영한림정#2 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 345k신김해-북부산T/L 95-96호 횡단구간 안전확보","2021-02-20 07:00","2021-02-21 18:00","2021-02-20 07:00","2021-02-21 18:00","연속"]
[115,"경남","함안","진영한림정#1 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 345k신김해-북부산T/L 95-96호 횡단구간 안전확보","2021-02-20 07:00","2021-02-21 18:00","2021-02-20 07:00","2021-02-21 18:00","연속"]
[116,"경남","함안","진영한림정#1 T/L","345kV 신김해-북부산T/L 94호 안전이격 확보공사","○ 345k신김해-북부산T/L 95-96호 횡단구간 안전확보","2021-02-27 07:00","2021-02-28 18:00","2021-02-27 07:00","2021-02-28 18:00","연속"]