{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":22,"n_cols":11,"rows_kept":22,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2021년도 3월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신안성신가평 T/L","765kV 신안성-신가평T/L 항공시설물 정비공사","- 765kV 신안성-신가평T/L 항공장애표시도장(19기)","2021-03-03 07:00","2021-03-31 18:00","취소","취소","연속"]
[2,"경기북부","구리","신가평S/S #4 M.Tr","20~21년 구리전력지사 변전정비회사 총액공사","장기사용 배전반 교체공사 - 신가평S/S 765kV #85BAY B/F보호반 교체","2021-03-18 09:00","2021-03-31 18:00","취소","취소","연속"]
[3,"경기북부","구리","신가평S/S #2 M.Tr","'20~21년 구리전력 변전정비회사 총액공사","신가평S/S #2M.Tr A-L상 OFU 누유 보수","2021-03-02 09:00","2021-03-02 18:00","2021-03-02 09:00","2021-03-02 18:00","연속"]
[4,"경기","성남","신안성S/S #5 M.Tr A-1","신안성S/S 765kV #5 M.Tr 1차측 GIS 메커니즘점검","신안성S/S 765kV #5 M.Tr 1차측 GIS 메커니즘점검","2021-03-02 09:00","2021-03-05 18:00","취소","취소","연속"]
[5,"경기","성남","신안성S/S #4 M.Tr A-1","21년 성남전력 변전정비회사 총액공사","M.Tr 보호반대체","2021-03-08 09:00","2021-04-16 18:00","취소","취소","연속"]
[6,"경기","성남","신중부신안성#2 T/L","21년 성남전력 변전정비회사 총액공사","87BAY B/F반 대체","2021-03-08 09:00","2021-03-19 18:00","취소","취소","연속"]
[7,"강원","태백","신태백신가평#1 T/L","신한울1호기 상업운전 관련 SPS 설치공사","신한울1호기 상업운전 관련 SPS 설치공사","2021-03-17 09:00","2021-03-17 18:00","취소","취소","연속"]
[8,"강원","태백","신태백신가평#2 T/L","신한울1호기 상업운전 관련 SPS 설치공사","신한울1호기 상업운전 관련 SPS 설치공사","2021-03-18 09:00","2021-03-18 18:00","취소","취소","연속"]
[9,"충북","직할","신중부E/C #5 M.Tr","765kV 신중부S/S #3M.Tr 증설공사","- #5M.Tr 3차 전력케이블 철거 - 3차 GIS 제어케이블 분리. - 기타 부대작업.","2021-03-04 08:00","2021-03-04 18:00","2021-03-04 08:00","2021-03-04 18:00","연속"]
[10,"대전충남","서산","신서산당진TP#1 T/L","21년 서산P/O 변전정비 총액공사","신서산S/S 765kV 신서산-당진화력#1T/L 보호반 대체(T/L, BF) (병행)신서산S/S 765kV 신서산-당진화력#1T/L(8471정밀점검)","2021-03-29 09:00","2021-04-09 18:00","취소","취소","연속"]
[11,"대전충남","서산","신서산S/S #3 M.Tr","21년 서산P/O 765kV M.Tr 정밀점검","신서산S/S 765kV #3M.Tr 정밀점검 (병행) 신서산S/S 765kV 8300, 8372 보통점검","2021-03-22 10:00","2021-05-14 18:00","2021-03-22 10:00","2021-05-14 18:00","연속"]
[12,"경북","영주","신태백신한울#2 T/L","신한울1호기 상업운전 관련 SPS 설치공사","신한울1호기 상업운전 관련 SPS 설치공사","2021-03-16 09:00","2021-03-16 18:00","취소","취소","연속"]
[13,"경북","영주","신태백신한울#1 T/L","신한울1호기 상업운전 관련 SPS 설치공사","신한울1호기 상업운전 관련 SPS 설치공사","2021-03-15 09:00","2021-03-15 18:00","취소","취소","연속"]
[14,"부산울산","동부산","북경남신고리NP#2 T/L","신고리S/S 765kV 인출부싱 가스주입구 설치","신고리S/S 765kV 인출부싱 가스주입구 설치(북경남-신고리#2T/L)","2021-03-09 09:30","2021-03-09 17:00","2021-03-09 09:30","2021-03-09 17:00","연속"]
[15,"부산울산","동부산","북경남신고리NP#1 T/L","신고리S/S 765kV 인출부싱 가스주입구 설치","신고리S/S 765kV 인출부싱 가스주입구 설치(북경남-신고리#1T/L)","2021-03-08 09:30","2021-03-08 17:00","2021-03-08 09:30","2021-03-08 17:00","연속"]
[16,"부산울산","동부산","신고리N/P #1 Tie-Tr","신고리S/S 765kV M.Tr 누유개소 조치","신고리S/S 765kV M.Tr 누유개소 조치(#1M.Tr C-1)","2021-03-15 09:00","2021-03-31 18:00","2021-03-15 09:00","2021-03-31 18:00","연속"]
[17,"강원","태백","신태백S/S #2 M.Tr","765kV 신태백S/S 345kV 용량부족차단기 대체 및 SW증설공사","1. 345kV 73Bay GIS 3CB 대체 2. 보호배전반 이설 3. 제어케이블 분리, 포설, 결선 1식","2021-03-19 09:00","2021-06-30 18:00","2021-03-19 09:00","2021-06-30 18:00","연속"]
[18,"부산울산","고리","신고리N/P #1호기 주변압기 CB(8471, 8400)","신고리 1호기 6차 계획예방정비","전력용변압기 일반점검 및 구내 선로 점검, 보호계전기 시험 등","2021-03-03 09:00","2021-03-24 18:00","2021-03-03 09:00","2021-03-24 18:00","연속"]

{"sheet":"345설비","index":1,"n_rows":228,"n_cols":11,"rows_kept":228,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2021년도 3월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S 345kV #2 BUS","성동S/S 345kV #2Sh.R 고장복구공사(시험가압)","#2 Sh.R 및 7279 CB 시험가압용","2021-03-05 10:00","2021-03-07 18:00","2021-03-05 10:00","2021-03-08 18:00","연속"]
[2,"서울","성동","성동S/S #3 M.Tr","성동S/S 345kV #2Sh.R 고장복구공사(시험가압)","#2 Sh.R 및 7279 CB 시험가압용","2021-03-05 10:00","2021-03-07 18:00","2021-03-05 10:00","2021-03-08 18:00","연속"]
[3,"서울","성동","미금성동#4 T/L","성동S/S 345kV #2Sh.R 고장복구공사(시험가압)","#2 Sh.R 및 7279 CB 시험가압용","2021-03-05 10:00","2021-03-07 18:00","2021-03-05 10:00","2021-03-08 18:00","연속"]
[4,"서울","중부","중부S/S #2 M.Tr","중부S/S 345kV 주변압기 정밀점검공사","345kV M.Tr 정밀점검","2021-03-19 09:00","2021-03-28 18:00","2021-03-19 09:00","2021-03-28 18:00","연속"]
[5,"서울","중부","중부S/S #1 M.Tr","`21 중부PO 변전정비회사 총액공사","345kV M.Tr 초기점검","2021-03-29 09:00","2021-03-31 18:00","2021-03-29 09:00","2021-03-31 18:00","연속"]
[6,"서울","중부","중부S/S #3 M.Tr","중부S/S 345kV 주변압기 정밀점검공사","345kV M.Tr 정밀점검","2021-03-08 09:00","2021-03-18 18:00","2021-03-08 09:00","2021-03-18 18:00","연속"]
[7,"남서울","강남","신양재S/S #2 M.Tr","신양재S/S #1,2S.Tr 1차 CB 교체공사","신양재S/S #1,2S.Tr 1차 CB 교체공사","2021-03-08 09:00","2021-03-12 18:00","2021-03-08 09:00","2021-03-12 18:00","연속"]
[8,"남서울","강남","신양재S/S #1 M.Tr","신양재S/S #1,2S.Tr 1차 CB 교체공사","신양재S/S #1,2S.Tr 1차 CB 교체공사","2021-03-01 09:00","2021-03-05 18:00","2021-03-01 09:00","2021-03-05 18:00","연속"]
[9,"남서울","동서울","동서울S/S #1 M.Tr","동서울S/S #1M.Tr 부싱절연유 시료 채유","부싱절연유 가스 분석 이상에 따른 3개월 추적분석 시료채유 1차 GIS 조작시험 및 2차 GCB 조작시험","2021-03-04 09:00","2021-03-04 18:00","2021-03-03 09:00","2021-03-03 18:00","연속"]
[10,"남서울","동서울","동서울S/S SVC CB","SVC M.Tr 정밀점검 및 SVC 설비 보통점검","SVC M.Tr 정밀점검 및 SVC 설비 보통점검","2021-03-02 09:00","2021-03-16 18:00","2021-03-02 09:00","2021-03-16 18:00","연속"]
[11,"남서울","동서울","동서울S/S 345kV #71 BUS","장기사용 보호배전반 교체공사","345kV #71-76 모선보호반 교체공사","2021-03-02 09:00","2021-03-06 18:00","2021-03-02 09:00","2021-03-06 18:00","연속"]
[12,"남서울","동서울","동서울S/S 345kV #76 BUS","장기사용 보호배전반 교체공사","345kV #71-76 모선보호반 교체공사","2021-03-08 09:00","2021-03-12 18:00","2021-03-08 09:00","2021-03-12 18:00","연속"]
[13,"남서울","영등포","신광명영등포#1 T/L","신광명S/S 362kV GIS 보통점검(신광명-영등포#1,2)","- 362kV GIS 보통점검 - 계전기 불량사항 정비(계통시험파트 입회)","2021-02-27 09:00","2021-02-27 18:00","2021-02-27 09:00","2021-02-27 18:00","연속"]
[14,"남서울","영등포","신광명S/S 345kV #75 BUS","신광명S/S 345kV DS 과열개소 보수","- 7152 DS 과열개소 보수","2021-02-27 09:00","2021-02-27 18:00","2021-02-27 09:00","2021-02-27 18:00","연속"]
[15,"남서울","영등포","신광명S/S 345kV CB 7172","신광명S/S 345kV DS 과열개소 보수","- 7152 DS 과열개소 보수","2021-02-27 09:00","2021-02-27 18:00","2021-02-27 09:00","2021-02-27 18:00","연속"]
[16,"남서울","영등포","서서울신광명#2 T/L","신광명S/S 345kV 서서울-신광명#2T/L 보호반 교체","- 345kV 서서울-신광명#2T/L 보호반 교체","2021-03-22 09:00","2021-03-26 18:00","2021-03-22 09:00","2021-03-26 18:00","연속"]
[17,"남서울","영등포","신광명영등포#2 T/L","신광명S/S 362kV GIS 보통점검(신광명-영등포#1,2)","- 362kV GIS 보통점검","2021-02-28 09:00","2021-02-28 18:00","2021-02-28 09:00","2021-02-28 18:00","연속"]
[18,"인천","김포","신김포신인천CC T/L","345kV 신김포-신인천CC T/L 잔여 접속함 해체점검","공사대상 : (1B) J/B#1,3,4-1,7 / (2B) J/B#1,2,4-1,7 공사내용 : 접속함 해체점검","2021-03-08 08:00","2021-03-10 20:00","2021-03-08 08:00","2021-03-10 20:00","연속"]
[19,"인천","부평","신가좌S/S #1 M.Tr","신가좌S/S #1M.TR 휴전작업","신가좌S/S #1M.TR 휴전작업","2021-03-08 09:00","2021-03-10 18:00","2021-03-08 09:00","2021-03-10 18:00","연속"]
[20,"인천","부평","신가좌가정#2 T/L","345kV 신가좌-가정T/L No.9 가공지선 암 교체","345kV 신가좌-가정T/L No.9 가공지선 암 교체","2021-03-04 08:00","2021-03-05 18:00","2021-03-22 08:00","2021-03-23 18:00","연속"]
[21,"인천","부평","신가좌가정#1 T/L","345kV 신가좌-가정T/L No.9 가공지선 암 교체","345kV 신가좌-가정T/L No.9 가공지선 암 교체","2021-03-02 08:00","2021-03-03 18:00","2021-03-24 08:00","2021-03-25 18:00","연속"]
[22,"인천","부평","신가좌S/S #4 M.Tr","신가좌S/S #4M.TR 휴전작업","신가좌S/S #4M.TR 휴전작업","2021-03-15 09:00","2021-03-17 18:00","2021-03-15 09:00","2021-03-17 18:00","연속"]
[23,"인천","부평","인천C/C 345kV #70 BUS","인천CC S/Y 345kV #70 BUS 모선보호반 교체 공사","인천CC S/Y 345kV #70 BUS 모선보호반 교체 공사","2021-03-15 09:00","2021-03-19 18:00","2021-03-15 09:00","2021-03-19 18:00","연속"]
[24,"인천","부평","인천C/C 345kV #75 BUS","인천CC S/Y 345kV #75 BUS 모선보호반 교체 공사","인천CC S/Y 345kV #75 BUS 모선보호반 교체 공사","2021-03-22 09:00","2021-03-26 18:00","2021-03-22 09:00","2021-03-26 18:00","연속"]
[25,"인천","시흥","신시흥#1S/S #2 M.Tr","신시흥#1S/S 345kV #2M.Tr 2차 GIS대체공사","신시흥#1S/S 345kV #2M.Tr 2차 GIS대체공사","2021-03-23 08:00","2021-04-05 18:00","취소","취소","연속"]
[26,"인천","시흥","신시흥#1S/S #3 M.Tr","신시흥#1S/S 154kV 신시흥남동#2T/L GIS대체(#3M.Tr)","신시흥#1S/S 154kV 신시흥남동#2T/L GIS대체(#3M.Tr)","2021-03-14 18:00","2021-03-15 18:00","취소","취소","연속"]
[27,"인천","시흥","신시흥#1S/S #3 M.Tr","신시흥#1S/S 154kV 신시흥남동#2T/L GIS대체(#3M.Tr)","신시흥#1S/S 154kV 신시흥남동#2T/L GIS대체(#3M.Tr)","2021-03-10 17:00","2021-03-10 18:00","취소","취소","연속"]
[28,"인천","시흥","신시흥#1S/S #1 M.Tr","신시흥#1S/S 345kV #1M.Tr 부싱유 채유","신시흥#1S/S 345kV #1M.Tr 부싱유 채유","2021-03-09 10:00","2021-03-09 18:00","취소","취소","연속"]
[29,"인천","시흥","신시흥영흥TP#3 T/L","2020-2021년 송전정비회사 총액공사","345kV 서서울2-신시흥#2T/L 휴전작업 관련 안전이격거리확보","2021-03-27 08:00","2021-03-27 12:00","2021-03-27 08:00","2021-03-27 12:00","연속"]
[30,"인천","시흥","영흥#2T/P 345kV CB 7672","영흥#2S/Y 345kV 7672 GIS누유보수","영흥#2S/Y 345kV 7672 GIS누유보수","2021-03-04 14:00","2021-03-04 18:00","2021-03-04 14:00","2021-03-04 18:00","연속"]
[31,"인천","시흥","영흥#2T/P 345kV CB 7900","영흥#2S/Y 345kV 7900 GIS누유보수","영흥#2S/Y 345kV 7900 GIS누유보수","2021-03-03 10:00","2021-03-03 14:00","2021-03-03 10:00","2021-03-03 14:00","연속"]
[32,"인천","시흥","영흥#2T/P 345kV CB 7971","영흥#2S/Y 345kV 7971 GIS누유보수","영흥#2S/Y 345kV 7971 GIS누유보수","2021-03-03 14:00","2021-03-03 18:00","2021-03-03 14:00","2021-03-03 18:00","연속"]
[33,"인천","시흥","영흥#2T/P 345kV CB 7600","영흥#2S/Y 345kV 7600 GIS누유보수","영흥#2S/Y 345kV 7600 GIS누유보수","2021-03-04 10:00","2021-03-04 14:00","2021-03-04 10:00","2021-03-04 14:00","연속"]
[34,"인천","시흥","영흥#2T/P 345kV CB 7772","영흥#2S/Y 345kV 7772 GIS누유보수","영흥#2S/Y 345kV 7772 GIS누유보수","2021-03-05 10:00","2021-03-05 18:00","2021-03-05 10:00","2021-03-05 18:00","연속"]
[35,"경기북부","고양","신덕은동두천CC#1 T/L","362kV GIS 하자점검-변전총액공사","7571,7500 GIS 하자점검","2021-03-15 09:00","2021-03-16 18:00","취소","취소","연속"]
[36,"경기북부","고양","신파주S/S #2 M.Tr","21년 고양P/O 변전정비회사 총액공사","유펌프 관련 회로보완작업","2021-03-17 09:30","2021-03-17 18:00","2021-03-17 09:30","2021-03-17 18:00","연속"]
[37,"경기북부","고양","신파주S/S #1 M.Tr","21년 고양P/O 변전정비회사 총액공사","유펌프 관련 회로보완작업","2021-03-16 09:30","2021-03-16 18:00","2021-03-16 09:30","2021-03-16 18:00","연속"]
[38,"경기북부","고양","신파주S/S #3 M.Tr","21년 고양P/O 변전정비회사 총액공사","PD발생 개소 측정(설비진단처) 및 #3M.Tr 누유개소 보수","2021-03-18 09:30","2021-03-19 18:00","2021-03-18 09:30","2021-03-19 18:00","연속"]
[39,"경기북부","구리","미금S/S 345kV #2 BUS","미금성동#3TL 7552DS 가스누기 보수","미금성동#3TL 7552DS 가스누기 보수","2021-03-08 09:00","2021-03-12 18:00","취소","취소","연속"]
[40,"경기북부","구리","미금S/S 345kV CB 7771","`20~21 구리전력 변전정비 총액공사","미금S/S 신가평-미금#1T/L GIS 7771 CB 개폐타임 측정","2021-03-24 09:00","2021-03-24 14:00","2021-03-24 09:00","2021-03-24 14:00","연속"]
[41,"경기북부","구리","미금S/S 345kV CB 7400","`20~21 구리전력 변전정비 총액공사","미금S/S 동서울-미금#2T/L TIE GIS 7400 CB 개폐타임 측정","2021-03-24 14:00","2021-03-24 18:00","2021-03-24 14:00","2021-03-24 18:00","연속"]
[42,"경기북부","구리","신가평포천LNGCC#2 T/L","345kV GIS 보통점검","345kV GIS 보통점검","2021-03-02 09:00","2021-03-02 18:00","취소","취소","연속"]
[43,"경기북부","직할","양주S/S #3 M.Tr","양주변전소 옥외철구 GIS화 공사","배전반 및 감시제어시스템 이설(모자이크 → SA)","2021-03-12 09:00","2021-03-21 18:00","2021-03-12 09:00","2021-03-21 18:00","연속"]
[44,"경기북부","직할","양주S/S #4 M.Tr","양주변전소 옥외철구 GIS화 공사","배전반 및 감시제어시스템 이설(모자이크 → SA)","2021-03-22 09:00","2021-03-31 18:00","2021-03-22 09:00","2021-03-31 18:00","연속"]
[45,"경기북부","직할","신의정부양주#2 T/L","양주변전소 옥외철구 GIS화 공사","배전반 및 감시제어시스템 이설(모자이크 → SA)","2021-03-02 09:00","2021-03-11 18:00","2021-03-02 09:00","2021-03-11 18:00","연속"]
[46,"경기북부","직할","양주S/S #2 M.Tr","양주변전소 옥외철구 GIS화 공사","배전반 및 감시제어시스템 이설(모자이크 → SA)","2021-03-02 09:00","2021-03-11 18:00","2021-03-02 09:00","2021-03-11 18:00","연속"]
[47,"경기북부","직할","양주S/S 345kV CB 7771","양주변전소 옥외철구 GIS화 공사","배전반 및 감시제어시스템 이설(모자이크 → SA)","2021-03-22 09:00","2021-03-31 18:00","2021-03-22 09:00","2021-03-31 18:00","연속"]
[48,"경기북부","직할","신파주양주#2 T/L","양주변전소 옥외철구 GIS화 공사","배전반 및 감시제어시스템 이설(모자이크 → SA)","2021-03-12 09:00","2021-03-21 18:00","2021-03-12 09:00","2021-03-21 18:00","연속"]
[49,"경기","군포","서서울#2신시흥#1 T/L","2020-2021년 송전정비회사 총액공사","- 점퍼지지애자 교체 3련","2021-03-29 08:00","2021-03-29 18:00","2021-03-29 08:00","2021-03-29 18:00","연속"]
[50,"경기","군포","서서울#2신시흥#2 T/L","2020-2021년 송전정비회사 총액공사","- 스페이서간격 조정 1335개 - 점퍼지지애자 교체 3련","2021-03-24 08:00","2021-03-28 18:00","2021-03-24 08:00","2021-03-28 18:00","연속"]
[51,"경기","군포","신시흥신안산#2 T/L","2020-2021년 송전정비회사 총액공사","345kV 서서울2-신시흥#2T/L 휴전작업 관련 안전이격거리확보","2021-03-24 08:00","2021-03-27 18:00","2021-03-24 08:00","2021-03-25 18:00","매일"]
[52,"경기","동부","곤지암S/S 345kV CB 7372","21년 동부 변전정비회사 총액공사","곤지암:7300,7372 차단기(조작)","2021-03-23 09:30","2021-03-23 14:00","취소","취소","연속"]
[53,"경기","동부","곤지암S/S 345kV CB 7172","21년 동부 변전정비회사 총액공사","곤지암:7172,7100 차단기(조작)","2021-03-22 09:30","2021-03-22 13:00","2021-03-22 09:30","2021-03-22 13:00","연속"]
[54,"경기","동부","곤지암S/S 345kV CB 7100","21년 동부 변전정비회사 총액공사","곤지암:7172,7100 차단기(조작)","2021-03-22 13:00","2021-03-22 18:00","2021-03-22 13:00","2021-03-22 18:00","연속"]
[55,"경기","동부","곤지암S/S 345kV CB 7300","21년 동부 변전정비회사 총액공사","곤지암:7300,7372 차단기(조작)","2021-03-23 14:00","2021-03-23 18:00","취소","취소","연속"]
[56,"경기","동부","곤지암S/S 345kV CB 7400","21년 동부 변전정비회사 총액공사","곤지암:7400,7471 차단기(조작)","2021-03-24 09:30","2021-03-24 14:00","2021-03-24 09:30","2021-03-24 14:00","연속"]
[57,"경기","동부","곤지암S/S 345kV CB 7471","21년 동부 변전정비회사 총액공사","곤지암:7400,7471 차단기(조작)","2021-03-24 14:00","2021-03-24 18:00","2021-03-24 14:00","2021-03-24 18:00","연속"]
[58,"경기","동부","곤지암S/S 345kV CB 7500","21년 동부 변전정비회사 총액공사","곤지암:7500,7572 차단기(조작)","2021-03-25 09:30","2021-03-25 14:00","2021-03-25 09:30","2021-03-25 14:00","연속"]
[59,"경기","동부","곤지암S/S 345kV CB 7572","21년 동부 변전정비회사 총액공사","곤지암:7500,7572 차단기(조작)","2021-03-25 14:00","2021-03-25 18:00","2021-03-25 14:00","2021-03-25 18:00","연속"]
[60,"경기","성남","신안성신성남#1 T/L","345kV 신용인-동서울T/L 지장철탑 이설공사(이천오산)","345kV 신용인-동서울T/L 7-1호 지장철탑 이설(요청자 시행 공사) - 교체구간 : 0.7km, 4회선 1기 본선로, 1기 임시선로 - 345kV 신안성-신성남T/L 64-1호 병가구간","2021-03-03 08:00","2021-03-16 18:00","2021-03-03 08:00","2021-03-16 18:00","연속"]
[61,"경기","성남","신안성신용인#1 T/L","345kV 신안성-신용인#1T/L 스페이서댐퍼 점검 및 교체공사","345kV 신안성-신용인#1T/L 불량 스페이서댐퍼 점검 및 교체","2021-03-16 09:00","2021-03-16 18:00","2021-03-16 09:00","2021-03-16 18:00","연속"]
[62,"경기","성남","신용인S/S #1 M.Tr","21년 성남전력지사 변전정비회사 총액공사","2차 GIS 6142 전자변 에어누기 점검,2차 GIS 조작시험","2021-03-29 09:00","2021-03-29 18:00","2021-03-29 09:00","2021-03-29 18:00","연속"]
[63,"경기","성남","신용인S/S #3 M.Tr","21년 성남전력지사 변전정비회사 총액공사","- OFU FILTER 교체 - 7500,7572 보통점검 - 6344 조작시험 - 2차 LA대체 - 부싱절연유채유","2021-03-09 09:00","2021-03-10 18:00","2021-03-09 09:00","2021-03-10 18:00","연속"]
[64,"경기","성남","신용인동서울#1 T/L","345kV 신용인-동서울T/L 지장철탑 이설공사(이천오산)","345kV 신용인-동서울T/L 7-1호 지장철탑 이설(요청자 시행 공사) - 교체구간 : 0.7km, 4회선 1기 본선로, 1기 임시선로 - 345kV 신안성-신성남T/L 64-1호 병가구간","2021-03-03 08:00","2021-03-15 18:00","2021-03-03 08:00","2021-03-15 18:00","연속"]
[65,"경기","직할","화성S/S 345kV SEC CB 70710","21년 경기 직할 변전정비회사 총액공사","화성 : 70-71SEC GIS 하자점검","2021-03-22 09:00","2021-03-22 18:00","2021-03-22 09:00","2021-03-22 18:00","연속"]
[66,"경기","직할","아산화성#2 T/L","345kV 신온양-서서울외 2개T/L 지장철탑이설공사(본선로)","지지물(관형주) 1기 신설, 임시선로 1기 철거 전력선교체 No.84~91","2021-03-15 08:00","2021-03-23 18:00","2021-03-15 08:00","2021-03-23 18:00","연속"]
[67,"경기","직할","아산화성#1 T/L","345kV 신온양-서서울외 2개T/L 지장철탑이설공사(본선로)","지지물(관형주) 1기 신설, 임시선로 1기 철거 전력선교체 No.84~91","2021-03-24 08:00","2021-03-31 18:00","2021-03-24 08:00","2021-03-31 18:00","연속"]
[68,"경기","직할","화성신안산#2 T/L","화성S/S 345kV GIS 용량대체공사","7B -> 7A 화성신안산#2T/L 환원 및 #71BUS 용량대체","2021-03-17 13:00","2021-04-02 18:00","2021-03-17 13:00","2021-04-02 18:00","연속"]
[69,"경기","직할","화성신안산#1 T/L","화성S/S 345kV GIS 용량대체공사","안전이격거리 확보 (#71BUS GIS 용량대체 79 Bay)","2021-03-15 09:00","2021-03-17 13:00","2021-03-15 09:00","2021-03-17 13:00","연속"]
[70,"경기","직할","화성S/S #1 M.Tr","화성S/S 154kV 장기사용 GIS 대체공사","화성S/S 154kV 장기사용 GIS 대체 X 14BAY","2021-03-24 09:00","2021-04-30 18:00","취소","취소","연속"]
[71,"경기","직할","화성평택T/P#2 T/L","화성S/S 345kV GIS 용량대체공사","안전이격거리 확보 (#71BUS GIS 용량대체 78 Bay)","2021-03-10 13:00","2021-03-12 18:00","2021-03-10 13:00","2021-03-12 18:00","연속"]
[72,"경기","직할","화성S/S 345kV #71 BUS","화성S/S 345kV GIS 용량대체공사","#71BUS GIS 용량대체","2021-03-02 09:00","2021-03-31 18:00","2021-03-02 09:00","2021-03-31 18:00","연속"]
[73,"경기","직할","화성평택T/P#1 T/L","화성S/S 345kV GIS 용량대체공사","안전이격거리 확보 (#71BUS GIS 용량대체 77 Bay)","2021-03-08 09:00","2021-03-10 13:00","2021-03-08 09:00","2021-03-10 13:00","연속"]
[74,"경기","평택","고덕S/S #1 M.Tr","고덕S/S 345kV #1 M.Tr 누유 보수공사","고덕S/S 345kV #1 M.Tr 누유 보수공사 / A상 OFU / B상 OLTC Head Cover","2021-03-04 10:00","2021-03-05 18:00","2021-03-04 10:00","2021-03-05 18:00","연속"]
[75,"경기","평택","고덕S/S STATCOM CB","고덕S/S 345kV STATCOM 제어기 개선작업","STATCOM 제어기 개선 및 제작사 점검","2021-03-10 10:00","2021-03-11 18:00","2021-03-10 10:00","2021-03-11 18:00","연속"]
[76,"경기","평택","서안성S/S 345kV CB 7472","서안성S/S 345kV #3 M.Tr 1차 GIS(7472) 하자점검","서안성S/S 345kV #3 M.Tr 1차 GIS(7472) 하자점검","2021-03-19 10:00","2021-03-19 18:00","2021-03-19 10:00","2021-03-19 18:00","연속"]
[77,"경기","평택","서안성S/S 345kV CB 7400","서안성S/S신안성서안성#2TL-#3 MTr TIE(7400) 하자점검","서안성S/S신안성서안성#2TL-#3 MTr TIE GIS(7400) 하자점검","2021-03-18 10:00","2021-03-18 18:00","2021-03-18 10:00","2021-03-18 18:00","연속"]
[78,"경기","평택","서안성S/S 345kV CB 7372","서안성S/S 345kV #2 M.Tr 1차 GIS(7372) 하자점검","서안성S/S 345kV #2 M.Tr 1차 GIS(7372) 하자점검","2021-03-17 10:00","2021-03-17 18:00","2021-03-17 10:00","2021-03-17 18:00","연속"]
[79,"경기","평택","서안성S/S 345kV CB 7300","서안성S/S신안성서안성#1TL-#2M.Tr TIE(7300) 하자점검","서안성S/S신안성서안성#1TL-#2M.Tr TIE GIS(7300) 하자점검","2021-03-16 10:00","2021-03-16 18:00","2021-03-16 10:00","2021-03-16 18:00","연속"]
[80,"경기","평택","서안성S/S 345kV CB 7172","서안성S/S 345kV #1 M.Tr 1차 GIS(7172) 하자점검","서안성S/S 345kV #1 M.Tr 1차 GIS(7172) 하자점검","2021-03-15 10:00","2021-03-15 18:00","2021-03-15 10:00","2021-03-15 18:00","연속"]
[81,"경기","평택","서안성신진천#1 T/L","345kV 서안성S/S 용량부족 GIS 대체공사","1. #70BUS 하자보수(무부하가압용) - 72BAY 측 모선부 진공도 기준 미달","2021-03-08 09:00","2021-03-08 14:00","취소","취소","연속"]
[82,"경기","평택","서안성S/S 345kV #1 BUS","345kV 서안성S/S 용량부족 GIS 대체공사","1. #70BUS 하자보수 - 72BAY 측 모선부 진공도 기준 미달","2021-03-02 09:00","2021-03-08 14:00","2021-03-02 09:00","2021-03-08 14:00","연속"]
[83,"경기","평택","평택T/P 345kV CB 7972","평택T/P 345kV 신평택 #1G/T 1차 GIS(7972) 하자점검","평택T/P 345kV 신평택 #1G/T 1차 GIS(7972) 하자점검","2021-03-31 10:00","2021-03-31 18:00","2021-03-31 10:00","2021-03-31 18:00","연속"]
[84,"경기","평택","평택T/P 345kV CB 7900","평택T/P 345kV 신평택#1-화성신평#2T/L(7900) 하자점검","평택T/P 345kV 신평택#1-화성신평#2T/L GIS(7900) 하자점검","2021-03-30 10:00","2021-03-30 18:00","2021-03-30 10:00","2021-03-30 18:00","연속"]
[85,"경기","평택","평택T/P 345kV CB 7971","평택T/P 345kV 화성-신평택CC#2T/L GIS(7971) 하자점검","평택T/P 345kV 화성-신평택CC#2T/L GIS(7971) 하자점검","2021-03-29 10:00","2021-03-29 18:00","2021-03-29 10:00","2021-03-29 18:00","연속"]
[86,"강원","강릉","동해신양양 T/L","345kV 강릉안인화력 1,2호기 접속공사","345kV 양양양수 -강릉안인개패소간 ∏분기 접속","2021-03-01 09:00","2021-03-08 18:00","2021-03-01 09:00","2021-03-11 18:00","연속"]
[87,"강원","강릉","동해양양PP T/L","345kV 강릉안인화력 1,2호기 접속공사","345kV 양양양수 -강릉안인개패소간 ∏분기 접속","2021-03-09 09:00","2021-03-15 18:00","2021-03-18 09:00","2021-03-25 18:00","연속"]
[88,"강원","동해","삼척T/P #2 Tie-Tr","동해전력지사 2021년 170kV GIS 정밀점검","1. GIS 정밀점검 2. 가스 누기 관련 스페이서 점검","2021-03-29 09:00","2021-04-04 18:00","2021-03-29 09:00","2021-04-04 18:00","연속"]
[89,"강원","태백","신태백한울NP#2 T/L","765kV 신태백S/S 345kV 용량부족차단기 대체 및 SW증설공사","1. 345kV 신태백한울NP2 #2T/L 보호배전반 이설 2. 345kV 신태백한울NP2 #2T/L 송전선로 인출변경 (75Bay → 76Bay 이설)","2021-03-02 09:00","2021-03-10 18:00","2021-03-02 09:00","2021-03-10 18:00","연속"]
[90,"강원","태백","신태백S/S 345kV CB 7600, 7672","765kV 신태백S/S 345kV 용량부족차단기 대체 및 SW증설공사","345kV 신태백한울NP2 #2T/L 송전선로 인출변경 (75Bay → 76Bay 이설)","2021-03-02 09:00","2021-03-10 18:00","2021-03-02 09:00","2021-03-10 18:00","연속"]
[91,"강원","태백","신태백한울NP#1 T/L","765kV 신태백S/S 345kV 용량부족차단기 대체 및 SW증설공사","1. 345kV 신태백한울NP2 #1T/L 보호배전반 이설 2. 345kV 신태백한울NP2 #1T/L 송전선로 인출변경 (74Bay → 75Bay 이설)","2021-03-11 09:00","2021-03-18 18:00","2021-03-11 09:00","2021-03-18 18:00","연속"]
[92,"강원","태백","신태백S/S 345kV CB 7500, 7572","765kV 신태백S/S 345kV 용량부족차단기 대체 및 SW증설공사","345kV 신태백한울NP2 #1T/L 송전선로 인출변경 (74Bay → 75Bay 이설)","2021-03-11 09:00","2021-03-18 18:00","2021-03-11 09:00","2021-03-18 18:00","연속"]
[93,"강원","태백","신태백S/S #2 Sh.R CB","765kV 신태백S/S 345kV 용량부족차단기 대체 및 SW증설공사","1. 345kV 74Bay GIS 3CB 대체 2. 보호배전반 이설 설치 3. 제어케이블 분리, 포설, 결선 1식","취 소 ","취 소","취소","취소","연속"]
[94,"강원","태백","신태백S/S #2 M.Tr","765kV 신태백S/S 345kV 용량부족차단기 대체 및 SW증설공사","1. 345kV 73Bay GIS 3CB 대체 2. 보호배전반 이설 3. 제어케이블 분리, 포설, 결선 1식","2021-03-19 09:00","2021-06-30 18:00","취소","취소","연속"]
[95,"충북","직할","신중부신진천#1 T/L","765kV 신중부S/S #3M.Tr 증설공사","- 345kV #75 BUS 연결관련 안전이격거리 확보 - 기타 부대작업.","2021-03-15 08:00","2021-03-15 18:00","2021-03-15 08:00","2021-03-15 18:00","연속"]
[96,"충북","직할","신중부S/S 345kV #2 BUS","765kV 신중부S/S #3M.Tr 증설공사","- 345kV #75 BUS 연결 - 기타 부대작업.","2021-03-15 08:00","2021-03-19 18:00","2021-03-15 08:00","2021-03-19 18:00","연속"]
[97,"충북","직할","신중부S/S 345kV #1 BUS","765kV 신중부S/S #3M.Tr 증설공사","- 345kV #70 BUS 연결 - 기타 부대작업.","2021-03-08 08:00","2021-03-12 18:00","2021-03-08 08:00","2021-03-12 18:00","연속"]
[98,"충북","직할","서안성신진천#2 T/L","2020~21년 직할 송전정비회사 총액공사","불량애자교체(No.6,31,32,34)","2021-03-09 07:30","2021-03-10 18:00","2021-03-09 07:30","2021-03-10 18:00","연속"]
[99,"충북","직할","신진천S/S 345kV #70 BUS","345kV 신진천S/S 용량부족 GIS 대체공사 (#70BUS)","345kV GIS #70BUS 및 (#71~74BAY)51DS 대체(8차분)","2021-03-22 08:00","2021-04-21 18:00","2021-03-22 08:00","2021-04-21 18:00","연속"]
[100,"충북","직할","서안성신진천#1 T/L","2020~21년 직할 송전정비회사 총액공사","피뢰기설치(No.2,9,11), 불량애자교체(No.32)","2021-03-11 07:30","2021-03-12 18:00","2021-03-11 07:30","2021-03-12 18:00","연속"]
[101,"충북","청주","남청주S/S #3 M.Tr","21년 청주전력 상반기 170kV GIS 정밀점검 공사","남청주S/S #3M.Tr 2차 GIS 정밀점검","2021-03-06 09:00","2021-03-07 18:00","취소","취소","연속"]
[102,"충북","청주","세종남청주#2 T/L","남청주S/S 345kV 장기사용 GIS 대체공사","○ 기설 GIS(362kV, 40kA, 4000A) × 2CB 철거 ○ 신규 GIS(362kV, 50kA, 4000A) × 2CB 설치 ○ 기기기초 및 부대공사 × 1식","2021-03-22 08:00","2021-06-15 18:00","취소","취소","연속"]
[103,"충북","청주","신옥천S/S #2 M.Tr","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 345kV #2M.Tr 보통점검","2021-03-16 09:30","2021-03-17 18:00","2021-03-16 09:30","2021-03-17 18:00","연속"]
[104,"충북","청주","신옥천S/S #3 M.Tr","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 345kV #3M.Tr 보통점검","2021-03-23 09:30","2021-03-24 18:00","2021-03-23 09:30","2021-03-24 18:00","연속"]
[105,"충북","충주","신제천동해#2 T/L","20-21년 충주전력지사 변전정비 총액공사","신제천S/S 신제천-동해#2T/L LA점검","취 소 ","취 소","취소","취소","연속"]
[106,"충북","충주","신제천S/S #2 M.Tr","20-21년 충주전력지사 변전정비팀 총액공사","신제천S/S 345kV #2M.Tr 1차 LA 초기점검","2021-03-10 10:00","2021-03-10 18:00","2021-03-10 10:00","2021-03-10 18:00","연속"]
[107,"대전충남","서산","신당진개폐소태안TP#1 T/L","154kV 태안-태안화력T/L 피뢰기 설치공사","154kV 태안-태안화력T/L 피뢰기 설치 - No.2~27(26기) - 4회선 병가철탑 안전이격확보","2021-03-08 08:00","2021-03-10 18:00","2021-03-08 08:00","2021-03-10 18:00","매일"]
[108,"대전충남","서산","신당진S/S 345kV CB 7771","'21년 장기 미동작 차단기 조작시험","신당진S/S 345kV 신당진연락#2T/L 7771 CB 조작시험","2021-03-16 10:00","2021-03-16 14:00","2021-03-16 10:00","2021-03-16 14:00","연속"]
[109,"대전충남","서산","신당진S/S 345kV CB 7700","'21년 장기 미동작 차단기 조작시험","신당진S/S 345kV 신당진연락#2-신서산#2T/L TIE 7700 CB 조작시험","2021-03-16 14:00","2021-03-16 18:00","2021-03-16 14:00","2021-03-16 18:00","연속"]
[110,"대전충남","서산","신당진S/S 345kV CB 7872","'21년 장기 미동작 차단기 조작시험","신당진S/S 345kV #3 M.Tr 1차 7872 CB 조작시험","2021-03-18 14:00","2021-03-18 18:00","2021-03-18 14:00","2021-03-18 18:00","연속"]
[111,"대전충남","서산","신당진S/S 345kV CB 7800","'21년 장기 미동작 차단기 조작시험","신당진S/S 345kV #3 M.Tr 1차-TIE 7800 CB 조작시험","2021-03-18 10:00","2021-03-18 14:00","2021-03-18 10:00","2021-03-18 14:00","연속"]
[112,"대전충남","서산","신서산아산#1 T/L","154kV 합덕-송악T/L 피뢰기 설치공사","154kV 합덕-송악T/L 피뢰기 설치 - No.2~28(27기) - 4회선 병가철탑 안전이격확보","2021-03-15 08:00","2021-03-17 18:00","2021-03-15 08:00","2021-03-17 18:00","매일"]
[113,"대전충남","서산","태안T/P 345kV CB 7600","21년 서산P/O 345kV GIS 정밀점검","태안화력S/S 345kV 6호기TIE(7600) 정밀점검","2021-03-29 10:00","2021-04-02 18:00","2021-03-29 10:00","2021-04-02 18:00","연속"]
[114,"대전충남","세종","신옥천세종#1 T/L","[변전]세종PO변전정비총액공사","362kV GIS 보통점검(7371,7300)","2021-03-04 09:00","2021-03-05 18:00","2021-03-04 09:00","2021-03-05 18:00","연속"]
[115,"대전충남","세종","세종남청주#2 T/L","[변전]세종PO변전정비총액공사","362kV GIS 보통점검(7271,7200)","2021-03-08 09:00","2021-03-09 18:00","2021-03-08 09:00","2021-03-09 18:00","연속"]
[116,"대전충남","세종","신옥천세종#2 T/L","[변전]세종PO변전정비총액공사","362kV GIS 보통점검(7471,7400)","2021-03-02 09:00","2021-03-03 18:00","2021-03-02 09:00","2021-03-03 18:00","연속"]
[117,"대전충남","세종","세종남청주#1 T/L","[변전]세종PO변전정비총액공사","362kV GIS 보통점검(7571,7500)","2021-03-10 09:00","2021-03-11 18:00","2021-03-10 09:00","2021-03-11 18:00","연속"]
[118,"대전충남","세종","세종S/S #2 M.Tr","[변전]세종PO변전정비총액공사","345kV 주변압기 1,2,3차 GIS 보통점검","2021-03-15 09:00","2021-03-18 18:00","2021-03-15 09:00","2021-03-17 18:00","연속"]
[119,"대전충남","세종","세종S/S #3 M.Tr","[변전]세종PO변전정비총액공사","345kV 주변압기 1,2,3차 GIS 보통점검","2021-03-22 09:00","2021-03-25 18:00","2021-03-18 09:00","2021-03-20 18:00","연속"]
[120,"대전충남","아산","신탕정S/S #1 M.Tr","신탕정S/S 345kV #1M.Tr GIS 내장형 콘덴서 설치","신탕정S/S 345kV #1M.Tr GIS 내장형 콘덴서 설치","2021-03-08 09:00","2021-03-13 18:00","2021-03-08 09:00","2021-03-13 18:00","연속"]
[121,"대전충남","아산","신탕정S/S #2 M.Tr","신탕정S/S 345kV #2M.Tr GIS 내장형 콘덴서 설치","신탕정S/S 345kV #2M.Tr GIS 내장형 콘덴서 설치","2021-03-15 09:00","2021-03-19 18:00","2021-03-15 09:00","2021-03-19 18:00","연속"]
[122,"대전충남","아산","신탕정S/S #3 M.Tr","신탕정S/S 345kV #3M.Tr GIS 내장형 콘덴서 설치","신탕정S/S 345kV #3M.Tr GIS 내장형 콘덴서 설치","2021-03-22 09:00","2021-03-28 18:00","2021-03-22 09:00","2021-03-28 18:00","연속"]
[123,"대전충남","아산","아산S/S #1 M.Tr","아산S/S #1M.Tr 부싱절연유 채유","아산S/S #1M.Tr 부싱절연유 채유","2021-03-10 09:00","2021-03-10 18:00","2021-03-10 09:00","2021-03-10 18:00","연속"]
[124,"대전충남","청양","보령C/C 345kV SEC CB 75760","보령C/C 345kV 차단기 부동작예방 조작시험","보령C/C 345kV 차단기 부동작예방 조작시험(75-76-0) - 자체시행","2021-03-11 15:00","2021-03-11 18:00","2021-03-11 15:00","2021-03-11 18:00","연속"]
[125,"대전충남","청양","보령C/C 345kV CB 7171","보령C/C 345kV 차단기 부동작예방 조작시험","보령C/C 345kV 차단기 부동작예방 조작시험(7171) - 자체시행","2021-03-10 09:00","2021-03-10 12:00","2021-03-10 09:00","2021-03-10 12:00","연속"]
[126,"대전충남","청양","보령C/C 345kV CB 7371","보령C/C 345kV 차단기 부동작예방 조작시험","보령C/C 345kV 차단기 부동작예방 조작시험(7371)","2021-03-09 15:00","2021-03-09 18:00","2021-03-09 15:00","2021-03-09 18:00","연속"]
[127,"대전충남","청양","보령C/C 345kV CB 7200","보령C/C 345kV 차단기 부동작예방 조작시험","보령C/C 345kV 차단기 부동작예방 조작시험(7200)","2021-03-09 12:00","2021-03-09 15:00","2021-03-09 12:00","2021-03-09 15:00","연속"]
[128,"대전충남","청양","보령C/C 345kV CB 7272","보령C/C 345kV 차단기 부동작예방 조작시험","보령C/C 345kV 차단기 부동작예방 조작시험(7272)","2021-03-09 09:00","2021-03-09 12:00","2021-03-09 09:00","2021-03-09 12:00","연속"]
[129,"대전충남","청양","보령C/C 345kV CB 7100","보령C/C 345kV 차단기 부동작예방 조작시험","보령C/C 345kV 차단기 부동작예방 조작시험(7100)","2021-03-08 14:00","2021-03-08 18:00","2021-03-08 14:00","2021-03-08 18:00","연속"]
[130,"대전충남","청양","보령C/C 345kV CB 7300","보령C/C 345kV 차단기 부동작예방 조작시험","보령C/C 345kV 차단기 부동작예방 조작시험(7300) - 자체시행","2021-03-11 12:00","2021-03-11 15:00","2021-03-11 12:00","2021-03-11 15:00","연속"]
[131,"대전충남","청양","보령C/C 345kV CB 7372","보령C/C 345kV 차단기 부동작예방 조작시험","보령C/C 345kV 차단기 부동작예방 조작시험(7372) - 자체시행","2021-03-11 09:00","2021-03-11 12:00","2021-03-11 09:00","2021-03-11 12:00","연속"]
[132,"대전충남","청양","보령C/C 345kV CB 7172","보령C/C 345kV 차단기 부동작예방 조작시험","보령C/C 345kV 차단기 부동작예방 조작시험(7172)","2021-03-08 09:00","2021-03-08 13:00","2021-03-08 09:00","2021-03-08 13:00","연속"]
[133,"대전충남","청양","보령C/C 345kV CB 7271","보령C/C 345kV 차단기 부동작예방 조작시험","보령C/C 345kV 차단기 부동작예방 조작시험(7271) - 자체시행","2021-03-10 12:00","2021-03-10 15:00","2021-03-10 12:00","2021-03-10 15:00","연속"]
[134,"대전충남","청양","보령C/C 345kV SEC CB 70710","보령C/C 345kV 차단기 부동작예방 조작시험","보령C/C 345kV 차단기 부동작예방 조작시험(70-71-0) - 자체시행","2021-03-10 15:00","2021-03-10 18:00","2021-03-10 15:00","2021-03-10 18:00","연속"]
[135,"대전충남","청양","보령T/P 345kV #75 BUS","보령T/P #75BUS PT 철공진방지회로 설치","보령T/P #75BUS PT 철공진방지회로 설치","2021-03-22 09:00","2021-03-26 18:00","2021-03-22 09:00","2021-03-26 18:00","연속"]
[136,"대전충남","청양","보령T/P 345kV #70 BUS","보령T/P #70BUS PT 철공진방지회로 설치","보령T/P #70BUS PT 철공진방지회로 설치","2021-03-15 09:00","2021-03-19 18:00","2021-03-15 09:00","2021-03-19 18:00","연속"]
[137,"대전충남","청양","청양신탕정 T/L","[송전]345kV 청양-신온양 등 5개 T/L 피뢰기 설치공사","345kV 청양-신탕정T/L 피뢰기 설치공사 No.1~56 호 철탑 송전용 피뢰기 설치","2021-03-02 08:00","2021-03-08 18:00","취소","취소","매일"]
[138,"대전충남","청양","청양신보령TP T/L","청양-신보령화력T/L LA, CVT 보통점검 및 차단기 조작시험","- 청양-신보령화력T/L LA, CVT 보통점검 - 7271, 7200차단기 부동작예방 조작시험","2021-03-12 09:00","2021-03-12 18:00","취소","취소","연속"]
[139,"전북","군산","군산신김제#1 T/L","345kV 군산-신김제 등 3개T/L 피뢰기 설치공사","345kV 군산-신김제, 군산-새만금, 청양-군산T/L 송전선로용 피뢰기 1회선 설치","2021-03-10 09:00","2021-03-24 18:00","2021-03-02 09:00","2021-03-24 18:00","매일"]
[140,"전북","군산","군산S/S 345kV CB 7871","'21년 군산S/S 공압식차단기(7871 CB) 전자변 교체공사","- 군산S/S 345kV 7871 CB 전자변 교체공사","2021-03-23 09:00","2021-03-23 18:00","2021-03-23 09:00","2021-03-23 18:00","연속"]
[141,"전북","군산","군산S/S 345kV CB 7800","'21년 군산S/S 공압식차단기(7800 CB) 전자변 교체공사","- 군산S/S 345kV 7800 CB 전자변 교체공사","2021-03-24 09:00","2021-03-24 18:00","2021-03-24 09:00","2021-03-24 18:00","연속"]
[142,"전북","군산","군산S/S #4 M.Tr","'21년 군산S/S 공압식차단기(7872 CB) 전자변 교체공사","- 군산S/S 345kV 7872 CB 전자변 교체공사","2021-03-25 09:00","2021-03-25 18:00","2021-03-25 09:00","2021-03-25 18:00","연속"]
[143,"전북","군산","청양군산#1 T/L","345kV 군산-신김제 등 3개T/L 피뢰기 설치공사","345kV 군산-신김제, 군산-새만금, 청양-군산T/L 송전선로용 피뢰기 1회선 설치","2021-03-02 09:00","2021-03-09 18:00","2021-03-22 09:00","2021-04-02 18:00","매일"]
[144,"전북","김제","신김제S/S #2 M.Tr","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분)","- 6244, (구)남전주#1, 65-66-0 SEC GIS 교체 - 인출변경에 따른 케이블 이설 1식 - 기타 부대공사 1식","2021-03-15 09:00","2021-04-30 18:00","2021-03-15 09:00","2021-04-30 18:00","연속"]
[145,"전북","김제","신김제S/S #1 M.Tr","신김제S/S 345kV #1M.Tr C상 96G 점검","신김제S/S 345kV #1M.Tr C상 96G 점검","2021-03-13 09:00","2021-03-13 18:00","2021-03-13 09:00","2021-03-13 18:00","연속"]
[146,"전북","직할","신남원S/S 345kV #1BUS","신남원S/S GAS 누기 보수공사(2차)-#70BUS","- 03/08 ~ 03/25 : 신남원-광양#2T/L 휴전병행 - 03/26 ~ 03/31 : 신남원-의령#1T/L 휴전병행","2021-03-19 08:00","2021-03-24 18:00","2021-03-19 08:00","2021-03-24 18:00","연속"]
[147,"전북","직할","신옥천신남원#2 T/L","345kV 신옥천-신남원#2T/L 피뢰기 설치공사","□ 345kV 신옥천-신남원#2T/L 피뢰기 설치공사 ○ No.1~178 구간 송전선로용 피뢰기 설치 및 아킹혼 철거","2021-03-15 09:00","2021-03-30 18:00","2021-03-12 09:00","2021-03-15 18:00","연속"]
[148,"전북","직할","신남원S/S 345kV #2BUS","신남원S/S GAS 누기 보수공사(2차)-#75BUS","- 2/15 ~ 3/11 : 신남원-광양#2T/L 휴전병행","2021-03-08 09:00","2021-03-11 18:00","2021-03-08 09:00","2021-03-11 18:00","연속"]
[149,"전북","직할","신남원한빛NP#2 T/L","신남원-한빛#2T/L 송전선로 정밀점검","No.21~171 정밀점검","2021-03-02 08:00","2021-03-18 18:00","2021-03-09 08:00","2021-03-26 18:00","연속"]
[150,"전북","직할","신남원의령#1 T/L","신남원S/S GAS 누기 보수공사(2차)-7371","- 3/26~3/31 : 7371CB A상 GAS 누기보수, #70BUS 휴전병행","2021-03-19 08:00","2021-03-24 18:00","취소","취소","연속"]
[151,"광주전남","강진","신강진S/S #1 M.Tr","'20-21년 강진전력지사 변전정비회사 총액공사","신강진S/S #1M.Tr 1, 2차 부싱 절연유 채유 신강진S/S #1M.Tr 1차 부싱 절연열화 측정 신강진S/S #1M.Tr 3차측 절연화 시공","2021-03-29 09:00","2021-03-29 18:00","2021-03-29 09:00","2021-03-29 18:00","연속"]
[152,"광주전남","강진","신강진S/S #2 M.Tr","'20-21년 강진전력지사 변전정비회사 총액공사","신강진S/S #2M.Tr 1, 2차 부싱 절연유 채유 신강진S/S #2M.Tr 1차 부싱 절연열화 측정 신강진S/S #2M.Tr 3차측 절연화 시공","2021-03-30 09:00","2021-03-31 18:00","2021-03-30 09:00","2021-03-31 18:00","연속"]
[153,"광주전남","광주","신광주신화순#2 T/L","345kV 신광주-신화순등5개T/L 피뢰기설치공사","345kV 신광주-신화순등5개T/L 피뢰기설치공사 -345kV 신광주-신화순#2T/L (121기)","2021-03-02 07:00","2021-03-08 18:00","2021-03-02 07:00","2021-03-08 18:00","매일"]
[154,"광주전남","광주","신광주S/S 345kV #1 BUS","21년 광주변전총액(1BUS 모선보호반 교체)","345kV #1BUS PRO 보호반 교체","2021-03-15 09:00","2021-03-19 18:00","취소","취소","연속"]
[155,"광주전남","광주","신광주S/S 345kV #2 BUS","21년 광주변전총액(2BUS 모선보호반 교체)","345kV #2BUS PRO 보호반 교체","2021-03-22 09:00","2021-03-26 18:00","취소","취소","연속"]
[156,"광주전남","목포","한빛2NP한빛3NP#3 T/L","한빛NP #3S/Y 362kV 장기사용 GIS 교체공사","한빛NP #3S/Y 362kV 장기사용 GIS 교체공사(C BAY)","2021-03-15 09:00","2021-05-07 18:00","2021-03-15 09:00","2021-05-07 18:00","연속"]
[157,"광주전남","목포","한빛#3N/P 345kV CB 7C71","한빛NP #3S/Y 362kV 장기사용 GIS 교체공사","한빛NP #3S/Y 362kV 장기사용 GIS 교체공사(7CBAY)","2021-03-15 09:00","2021-05-07 18:00","2021-03-15 09:00","2021-05-07 18:00","연속"]
[158,"광주전남","순천","신남원광양#1 T/L","345kV 광양S/S 용량부족GIS 대체공사(#70BUS) 사용전검사","345kV 광양S/S 용량부족GIS 대체공사(#70BUS) 관련 사용전검사","2021-03-30 10:00","2021-03-31 16:00","2021-03-31 10:00","2021-04-02 18:00","연속"]
[159,"광주전남","순천","신남원광양#1 T/L","345kV 광양S/S 용량부족GIS 대체공사(#70BUS) 무부하가압","345kV 광양S/S 용량부족GIS 대체공사(#70BUS) 관련 무부하가압","2021-03-29 10:00","2021-03-30 10:00","취소","취소","연속"]
[160,"광주전남","순천","광양여수TP T/L","345kV 광양-여수TP T/L 절연저항측정","21년 가공송전 순시점검 위탁공사- 00년 이전 국산애자 절연저항 측정 No. 42~125호, 5기","2021-03-24 08:00","2021-03-25 18:00","2021-03-24 08:00","2021-03-25 18:00","매일"]
[161,"광주전남","순천","신남원광양#1 T/L","345kV 광양S/S 용량부족GIS 대체공사(#70BUS)","345kV 광양S/S 용량부족GIS 대체공사(#70BUS) 관련 안전이격거리 확보","2021-03-10 10:00","2021-03-17 09:00","2021-03-12 10:00","2021-03-19 09:00","연속"]
[162,"광주전남","순천","광양S/S 345kV #70 BUS","345kV 광양S/S 용량부족GIS 대체공사(#70BUS)","345kV 광양S/S 용량부족GIS 대체공사(#70BUS)","2021-03-02 10:00","2021-03-31 15:00","2021-03-02 10:00","2021-04-02 18:00","연속"]
[163,"광주전남","순천","광양율촌CC T/L","345kV 광양S/S 용량부족GIS 대체공사(#70BUS)","345kV 광양S/S 용량부족GIS 대체공사(#70BUS) 관련 안전이격거리 확보","2021-03-04 09:00","2021-03-10 09:00","2021-03-04 09:00","2021-03-10 09:00","연속"]
[164,"광주전남","순천","신남원광양#2 T/L","345kV 광양S/S 용량부족GIS 대체공사(#70BUS)","345kV 광양S/S 용량부족GIS 대체공사(#70BUS) 관련 안전이격거리 확보","2021-03-17 10:00","2021-03-23 18:00","2021-03-19 10:00","2021-03-25 18:00","연속"]
[165,"대구","칠곡","북대구S/S #1 M.Tr","북대구S/S 154kV #60-65 모선보호반 교체작업","북대구S/S 154kV #60-65 모선보호반 교체작업","2021-03-05 13:30","2021-03-05 14:00","2021-03-05 13:30","2021-03-05 14:00","연속"]
[166,"대구","칠곡","북대구서대구#2 T/L","345kV 북대구S/S #4M.Tr 증설공사","345kV POST 설치관련 안전확보","2021-03-30 09:00","2021-03-30 18:00","2021-03-30 09:00","2021-03-30 18:00","연속"]
[167,"대구","칠곡","서대구S/S #4 M.Tr","345kV 북대구S/S #4M.Tr 증설공사","345kV POST 설치관련 안전확보","2021-03-31 09:00","2021-03-31 18:00","2021-03-31 09:00","2021-03-31 18:00","연속"]
[168,"대구","포항","신영일S/S 345kV CB 7572","신영일S/S 7500, 7572 GIS 보통점검","신영일S/S 7500, 7572 GIS 보통점검","2021-03-18 09:30","2021-03-18 18:00","2021-03-18 09:30","2021-03-18 18:00","연속"]
[169,"대구","포항","신영일S/S 345kV CB 7500","신영일S/S 7500, 7572 GIS 보통점검","신영일S/S 7500, 7572 GIS 보통점검","2021-03-18 14:00","2021-03-18 18:00","2021-03-18 14:00","2021-03-18 18:00","연속"]
[170,"대구","포항","신영일S/S 345kV CB 7700","신영일S/S 7700 GIS 보통점검","신영일S/S 7700 GIS 보통점검","2021-03-25 09:30","2021-03-25 14:00","2021-03-25 09:30","2021-03-25 14:00","연속"]
[171,"대구","포항","신포항S/S #4 M.Tr","신포항S/S #4M.Tr 보통점검","신포항S/S #4M.Tr 보통점검","2021-03-09 09:00","2021-03-10 18:00","2021-03-09 09:00","2021-03-10 18:00","연속"]
[172,"경북","구미","선산S/S #2 M.Tr","2020-21년 구미전력지사 변전정비업체 총액공사","-6244 GIS 하자점검, 1,2,3차 LA 보통점검, 23kV #2M.Tr PT 보통점검, 30F2 경보 발생관련 점검","2021-03-03 09:00","2021-03-04 18:00","2021-03-03 09:00","2021-03-04 18:00","연속"]
[173,"경북","영주","신제천신영주#1 T/L","345kV 신제천-신영주#1T/L 피뢰기 설치공사","345kV 신제천-신영주#1T/L 피뢰기 설치공사","2021-03-15 07:00","2021-03-20 18:00","2021-03-15 07:00","2021-03-20 18:00","매일"]
[174,"경북","영주","신제천신영주#2 T/L","유호전기제 345kV 송전선로 보호반 성능개선","- 유호전기제 345kV 송전선로 보호반 성능개선","2021-03-12 14:00","2021-03-12 18:00","2021-03-12 14:00","2021-03-12 18:00","연속"]
[175,"경북","영주","신영주청송PP T/L","유호전기제 345kV 송전선로 보호반 성능개선","- 유호전기제 345kV 송전선로 보호반 성능개선","2021-03-11 09:00","2021-03-11 18:00","2021-03-11 09:00","2021-03-11 18:00","연속"]
[176,"경북","직할","신영일안동CC T/L","345kV 영포T/L 전선접속개소 전선교체공사","345kV 영포T/L 전선접속개소 전선교체공사 No.182~194","2021-03-31 08:00","2021-04-08 18:00","2021-03-31 08:00","2021-04-08 18:00","연속"]
[177,"경북","직할","신포항청송PP T/L","345kV 영포T/L 전선접속개소 전선교체공사","345kV 영포T/L 전선접속개소 전선교체공사 No.182~194","2021-03-22 08:00","2021-03-30 18:00","2021-03-22 08:00","2021-03-30 18:00","연속"]
[178,"부산울산","동부산","신양산신대연#1 T/L","신양산S/S 345kV GIS 차단기 동작시험","신양산S/S 345kV GIS 차단기 동작시험(신양산-신대연#1T/L)","2021-03-31 09:30","2021-03-31 17:00","2021-03-31 09:30","2021-03-31 17:00","연속"]
[179,"부산울산","동부산","신양산신대연#2 T/L","신양산S/S 345kV GIS 차단기 동작시험","신양산S/S 345kV GIS 차단기 동작시험(신양산-신대연#2T/L)","2021-03-30 09:30","2021-03-30 17:00","2021-03-30 09:30","2021-03-30 17:00","연속"]
[180,"부산울산","북부산","신김해북부산#2 T/L","345kV 신김해-북부산T/L 35~36호간 지장송전선로 이설공사","임시철탑 설치, #2T/L 임시선로 구성 * 요청자부담시행공사 *","2021-03-02 07:00","2021-03-03 18:00","취소","취소","연속"]
[181,"부산울산","북부산","신김해북부산#1 T/L","345kV 북부산-울산TP 등 4개 T/L 전선접속개소 전선교체공사","신김해-북부산 #1T/L 4~10호간 추락방지시설 설치 4~8, 8~9. 9~10호간 전선교체","2021-03-04 07:00","2021-03-12 18:00","취소","취소","연속"]
[182,"부산울산","북부산","신김해북부산#2 T/L","345kV 신김해-북부산T/L 35~36호간 지장송전선로 이설공사","임시철탑 철거, #2T/L 임시선로 철거 및 본선로 구성 * 요청자부담시행공사 *","2021-03-13 07:00","2021-03-14 18:00","취소","취소","연속"]
[183,"부산울산","서부산","서부산S/S #1 Sh.R CB","서부산S/S 345kV 차단기 용량부족 대체공사","서부산S/S 71BAY(서부산-북부산#1T/L, #1Sh.R, #2M.Tr) 차단기 용량부족 대체 ○ 345kV GIS 40kA 4,000A×3CB 철거 ○ 345kV GIS 63kA 6,300A×3CB 설치","2021-03-22 09:00","2021-06-25 18:00","2021-03-22 09:00","2021-06-25 18:00","연속"]
[184,"부산울산","서부산","서부산S/S #2 M.Tr","서부산S/S 345kV 차단기 용량부족 대체공사","서부산S/S 71BAY(서부산-북부산#1T/L, #1Sh.R, #2M.Tr) 차단기 용량부족 대체 ○ 345kV GIS 40kA 4,000A×3CB 철거 ○ 345kV GIS 63kA 6,300A×3CB 설치","2021-03-22 09:00","2021-06-25 18:00","2021-03-22 09:00","2021-06-25 18:00","연속"]
[185,"부산울산","서부산","서부산북부산#1 T/L","서부산S/S 345kV 차단기 용량부족 대체공사","서부산S/S 71BAY(서부산-북부산#1T/L, #1Sh.R, #2M.Tr) 차단기 용량부족 대체 ○ 345kV GIS 40kA 4,000A×3CB 철거 ○ 345kV GIS 63kA 6,300A×3CB 설치","2021-03-22 09:00","2021-06-25 18:00","2021-03-22 09:00","2021-06-25 18:00","연속"]
[186,"부산울산","서부산","신녹산S/S #2 M.Tr","신녹산S/S 345kV #2M.Tr 보통점검","신녹산S/S 345kV #2M.Tr 보통점검 및 2차 차단기동작시험","2021-03-09 09:00","2021-03-11 18:00","2021-03-09 09:00","2021-03-11 18:00","연속"]
[187,"부산울산","울산","동울산S/S 345kV CB 7172","20-21년 변전정비회사 총액공사","동울산S/S 7172 CB차단기 동작시험","2021-03-17 14:00","2021-03-17 18:00","2021-03-17 14:00","2021-03-17 18:00","연속"]
[188,"부산울산","울산","동울산S/S 345kV CB 7272","20-21년 변전정비회사 총액공사","동울산S/S 7272 CB차단기 동작시험","2021-03-17 09:00","2021-03-17 14:00","2021-03-17 09:00","2021-03-17 14:00","연속"]
[189,"부산울산","울산","신온산S/S #2 M.Tr","20~21년 변전협력 총액공사","- 74BAY B/F PNL 대체 -#2M.Tr 3차 PT 점검, 부싱절연유 채유","2021-03-08 09:00","2021-03-12 18:00","취소","취소","연속"]
[190,"부산울산","울산","신온산울산TP T/L","20~21년 변전협력 총액공사","- 74BAY B/F PNL 대체 -#2M.Tr 3차 PT 점검, 부싱절연유 채유","2021-03-08 09:00","2021-03-12 18:00","취소","취소","연속"]
[191,"부산울산","울산","신울산S/S #1 M.Tr","20-21년 변전정비회사 총액공사","- M.Tr 하자점검 - 2차 GIS 동작시험 및 전자변교체","2021-03-24 09:00","2021-03-25 18:00","취소","취소","연속"]
[192,"부산울산","울산","신울산S/S #3 M.Tr","20-21년 변전정비회사 총액공사","- 51T CT 인출변경","2021-03-10 09:00","2021-03-10 18:00","취소","취소","연속"]
[193,"부산울산","울산","신울산S/S #2 M.Tr","신울산S/S 154kV 현대화공사","TR-BUS DS(6268) 철거","2021-03-29 09:30","2021-03-30 17:00","2021-03-29 09:30","2021-03-30 17:00","연속"]
[194,"부산울산","울산","신울산S/S #3 M.Tr","신울산S/S 154kV 현대화공사","TR-BUS DS(6368) 철거","2021-03-04 09:30","2021-03-05 17:00","2021-03-04 09:30","2021-03-05 17:00","연속"]
[195,"부산울산","울산","울산C/C 345kV CB 7A71, 7A00","울산복합S/Y 345kV SW증설공사","- 345kV 울산복합-북부산#2T/L 송전선로 계통연결 후 본가압","2021-03-31 09:00","2021-04-01 18:00","2021-03-31 09:00","2021-04-01 18:00","연속"]
[196,"부산울산","울산","북부산울산TP T/L","345kV 신울산복합-북부산T/L 건설공사","- 작업내용 : 345kV 신울산복합-북부산 #2 T/L 전력선가선(전선이동)","2021-03-15 07:00","2021-04-16 18:00","2021-03-15 07:00","2021-04-16 18:00","연속"]
[197,"부산울산","울산","울산C/C #2 Tie-Tr","20-21년 변전정비회사 총액공사","- 51T관련 3차측 CT 점검(보호제어과) - 2차 GIS 차단기 동작시험","2021-03-05 09:00","2021-03-05 18:00","취소","취소","연속"]
[198,"부산울산","울산","울주고리NP#2 T/L","21년도 가공송전 순시점검 위탁공사","345kV 울주-고리NP#2T/L 정밀점검","2021-03-22 09:00","2021-04-02 18:00","2021-03-22 09:00","2021-04-02 18:00","연속"]
[199,"부산울산","울산","울주월성NP#1 T/L","20-21년 변전정비회사 총액공사","- LA 대체 - 7900, 7971 차단기 동작시험","2021-03-23 09:00","2021-03-23 18:00","2021-03-23 09:00","2021-03-23 18:00","연속"]
[200,"부산울산","울산","울주고리NP#1 T/L","21년도 가공송전 순시점검 위탁공사","345kV 울주-고리NP#1T/L 정밀점검","2021-03-08 09:00","2021-03-19 18:00","2021-03-08 09:00","2021-03-19 18:00","연속"]
[201,"경남","직할","신김해S/S #4 M.Tr","신김해S/S 345kV #4M.Tr 보통점검","신김해S/S 345kV #4M.Tr 보통점검 (병행) 1차 CB(7872) 보통점검,TIE CB(7800) 조작시험, 2차 CB 전자변 교체,1,2,3차 LA 보통, 3차 PT 보통,절연유채유","2021-03-29 09:30","2021-04-01 17:30","2021-03-29 09:30","2021-04-01 17:30","연속"]
[202,"경남","진주","신남원의령#2 T/L","345kV 신남원-의령T/L No.78~86 철탑 지상고 확보공사","○ 345kV 신남원-의령#2T/L No.78~86 철탑 지상고 확보공사 휴전작업 - 철탑 인클로징 철탑 조립 6기(No.78~83) - 전력선 교체 : No.78~86(ACSR480MM2 X 4B X 2.619C-km) - 가공지선 교체 : No.83~86(ACSR120MM2 X S X 1.029km) ※ 통영-대전 고속도로 횡단개소 포함","2021-03-30 07:00","2021-04-13 18:00","2021-03-30 07:00","2021-04-13 18:00","연속"]
[203,"경남","진주","신남원의령#1 T/L","345kV 신남원-의령T/L No.78~86 철탑 지상고 확보공사","○ 345kV 신남원-의령#1T/L No.78~86 철탑 지상고 확보공사 휴전작업 - 철탑 인클로징 철탑 조립 6기(No.78~83) - 전력선 교체 : No.78~86(ACSR480MM2 X 4B X 2.619C-km) - 가공지선 교체 : No.83~86(ACSR120MM2 X S X 1.029km) ※ 통영-대전 고속도로 횡단개소","2021-03-15 07:00","2021-03-29 18:00","2021-03-15 07:00","2021-03-29 18:00","연속"]
[204,"경남","진주","하동T/P 345kV CB 7872","20-21년 진주전력지사 변전정비팀 총액공사","하동T/P 345kV #8M.Tr 1차 CB(7872) 조작시험","2021-03-19 10:00","2021-03-19 13:00","2021-03-19 10:00","2021-03-19 13:00","연속"]
[205,"경남","진주","하동T/P 345kV CB 7800","20-21년 진주전력지사 변전정비팀 총액공사","하동T/P 345kV TIE-#8M.Tr 1차 CB(7800) 조작시험","2021-03-19 13:00","2021-03-19 15:00","2021-03-19 13:00","2021-03-19 15:00","연속"]
[206,"경남","통영","신고성S/S #3 M.Tr","신고성S/S #3M.Tr 보호반 대체","신고성S/S #3M.Tr 보호반 대체","2021-03-08 09:00","2021-03-12 18:00","2021-03-08 09:00","2021-03-12 18:00","연속"]
[207,"대전충남","신보령","신보령T/P #1호기 주변압기 CB(7100, 7172)","1호기 계획예방정비공사","1호기 주변압기 점검","2021-03-08 09:00","2021-04-23 18:00","2021-03-08 09:00","2021-04-23 18:00","연속"]
[208,"광주전남","한빛","한빛#6 대기보조변압기 CB(7C71, 7C00)","6호기 13차 계획예방정비 - 조작차단기 : PCB 7C00, 7C71, 7C72","○ 대기보조변압기 일반점검 ○ 보호계전기 개체/연동시험 등 ○ 스위치야드 차단기(GIS) 교체공사(47일)","2020-03-15 09:00","2021-04-30 18:00","2021-03-15 09:00","2021-04-30 18:00","연속"]
[209,"광주전남","한빛","한빛#1N/P 기동변압기X02 CB(7F00, 7F72)","한빛1호기 25차 O/H 중 기동변압기 (X02) 공사 * 조작차단기 : CB 7F00, 7F72","○ 기동변압기(X01) 공사","2021-03-02 09:00","2021-03-31 14:00","2021-03-02 09:00","2021-03-31 14:00","연속"]
[210,"대구","월성","월성N/P #1 기동용변압기 CB(7671, 7600)","월성 1호기 제1차 영구정지 안전유지설비 점검 *조작차단기 : CB7671,7600","ㅇ기둉용변압기 일반점검 ㅇ기동용변압기 보호계전기 정기시험(차단기 연동시험 포함)","2021-03-16 09:00","2021-03-22 18:00","2021-03-16 09:00","2021-03-22 18:00","연속"]
[211,"경기북부","고양","신덕은S/S #4 M.Tr","2021 고양P/O 변전정비회사 총액공사(#4M.Tr 2차 GIS)","170kV GIS 보통점검","2021-03-11 10:00","2021-03-11 18:00","2021-03-11 10:00","2021-03-11 18:00","연속"]
[212,"경기","성남","신용인S/S #1 Sh.R CB","초기점검 및 모선변경(동대→케이블)","초기점검 및 모선변경(동대→케이블)","2021-03-22 09:00","2021-03-22 18:00","2021-03-22 09:00","2021-03-22 18:00","연속"]
[213,"경기","평택","서안성신진천#2 T/L","345kV 서안성S/S 용량부족 GIS 대체공사","1. #70BUS 하자보수(무부하가압용) - 72BAY 측 모선부 진공도 기준 미달","2021-03-08 09:00","2021-03-08 14:00","2021-03-06 14:00","2021-03-07 14:00","연속"]
[214,"대전충남","서산","태안T/P #10호기 주변압기 CB 7A00, 7A72","계획예방정비 - 갑종보호계전기 시험 등","계획예방정비 - 갑종보호계전기 시험 등","2021-03-04 10:00","2021-04-22 13:00","2021-03-04 10:00","2021-04-22 13:00","연속"]
[215,"대전충남","서산","태안T/P CB 7500, 7572","태안T/P 5,6호기 공용 MEB 교체공사에 따른 연동시험 진행","태안T/P 5,6호기 공용 MEB 교체공사에 따른 연동시험 진행","2021-03-04 09:00","2021-03-04 12:00","2021-03-04 09:00","2021-03-04 12:00","연속"]
[216,"대전충남","서산","태안T/P CB 7600, 7672","태안T/P 5,6호기 공용 MEB 교체공사에 따른 연동시험 진행","태안T/P 5,6호기 공용 MEB 교체공사에 따른 연동시험 진행","2021-03-04 09:00","2021-03-04 12:00","2021-03-04 09:00","2021-03-04 12:00","연속"]
[217,"대전충남","서산","신서산태안TP#1 T/L","태안T/P 5,6호기 공용 MEB 교체공사에 따른 연동시험 진행","태안T/P 5,6호기 공용 MEB 교체공사에 따른 연동시험 진행","2021-03-04 13:00","2021-03-04 18:00","2021-03-04 13:00","2021-03-04 18:00","연속"]
[218,"대전충남","서산","태안T/P SEC CB 70710","태안T/P 5,6호기 공용 MEB 교체공사에 따른 연동시험 진행","태안T/P 5,6호기 공용 MEB 교체공사에 따른 연동시험 진행","2021-03-05 13:00","2021-03-05 15:00","2021-03-05 13:00","2021-03-05 15:00","연속"]
[219,"대전충남","서산","태안T/P SEC CB 75760","태안T/P 5,6호기 공용 MEB 교체공사에 따른 연동시험 진행","태안T/P 5,6호기 공용 MEB 교체공사에 따른 연동시험 진행","2021-03-05 15:00","2021-03-05 18:00","2021-03-05 15:00","2021-03-05 18:00","연속"]
[220,"전북","직할","신옥천신남원#2 T/L","345kV 신옥천-신남원#2T/L 피뢰기 설치공사","□ 345kV 신옥천-신남원#2T/L 피뢰기 설치공사 ○ No.1~178 구간 송전선로용 피뢰기 설치 및 아킹혼 철거","2021-03-25 09:00","2021-04-10 18:00","2021-03-25 09:00","2021-04-10 18:00","연속"]
[221,"강원",null,"양양양수2호기 주변압기 CB(7200,7271)","주기기 및 보조기기 분해점검","주기기 및 보조기기 분해점검","2021-03-02 10:00","2021-10-08 18:00","2021-03-02 10:00","2021-10-08 18:00","연속"]
[222,"경남",null,"고성하이2호기 주변압기 CB(7200, 7272)","상분리모선 연결작업 및 시험 등","상분리모선 연결작업 및 시험 등","2021-03-08 14:00","2021-03-29 14:00","2021-03-08 14:00","2021-03-29 14:00","연속"]
[223,"전북",null,"무주양수1,2호기 주변압기 CB(7100,7200)","자체기동발전기 예비시험","자체기동발전기 예비시험","2021-03-16 12:00","2021-03-16 14:00","2021-03-16 12:00","2021-03-16 14:00","연속"]
[224,"전북",null,"무주양수1,2호기 주변압기 CB(7100,7200)","자체기동발전기 정기시험","자체기동발전기 정기시험","2021-03-24 14:00","2021-03-24 16:00","2021-03-24 14:00","2021-03-24 16:00","연속"]

{"sheet":"154설비","index":2,"n_rows":639,"n_cols":11,"rows_kept":639,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2021년도 3월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","화양광장 T/L","2021년도 가공송전 순시점검 위탁공사(서울본부)","송전선로 정밀점검 : 광장분기 No.1∼11(11기)","2021-03-17 09:00","2021-03-18 18:00","2021-03-17 09:00","2021-03-18 18:00","연속"]
[2,"서울","성동","성수뚝도#2 T/L","'21년 성동P/O 노후 보호배전반 교체공사","성수, 뚝도S/S 154kV 성수뚝도#2T/L 보호배전반 노후대체","2021-03-08 10:00","2021-03-11 18:00","2021-03-08 10:00","2021-03-11 18:00","연속"]
[3,"서울","성동","창동쌍문#1 T/L","쌍문S/S 종합예방진단시스템 설치","차단기 동작특성분석장치 결선 및 개폐타임 측정","2021-03-08 09:30","2021-03-08 14:00","2021-03-12 09:30","2021-03-12 14:00","연속"]
[4,"서울","성동","창동쌍문#2 T/L","쌍문S/S 종합예방진단시스템 설치","차단기 동작특성분석장치 결선 및 개폐타임 측정","2021-03-08 14:00","2021-03-08 18:00","2021-03-12 14:00","2021-03-12 18:00","연속"]
[5,"서울","중부","당인리S/S 154kV CB 6200","`21 중부PO 변전정비회사 총액공사","170kV GIS 보통점검","2021-03-05 10:00","2021-03-05 18:00","2021-03-05 10:00","2021-03-05 18:00","연속"]
[6,"서울","중부","당인리S/S 154kV SEC CB 60610","`21 중부PO 변전정비회사 총액공사","170kV GIS 보통점검","2021-03-02 10:00","2021-03-02 18:00","2021-03-02 10:00","2021-03-02 18:00","연속"]
[7,"서울","중부","당인리S/S 154kV SEC CB 65660","`21 중부PO 변전정비회사 총액공사","170kV GIS 보통점검","2021-03-03 10:00","2021-03-03 18:00","2021-03-03 10:00","2021-03-03 18:00","연속"]
[8,"서울","중부","당인리S/S 154kV CB 6100","`21 중부PO 변전정비회사 총액공사","170kV GIS 보통점검","2021-03-04 10:00","2021-03-04 18:00","2021-03-04 10:00","2021-03-04 18:00","연속"]
[9,"서울","중부","원흥상암 T/L","2020~2021 가공송전 정비회사 총액공사","불량애자교체 및 점퍼지지애자 교체","2021-03-08 07:30","2021-03-08 18:00","2021-04-09 07:30","2021-04-09 18:00","연속"]
[10,"서울","중부","수색S/S 154kV #1 BUS","수색S/S 154kV BUSTIE 이설관련 기초공사","BUSTIE 이설관련 기초 공사 - GCB 기초, DS 기초, LA 기초 공사","2021-03-16 09:00","2021-03-19 18:00","2021-03-16 09:00","2021-03-19 18:00","연속"]
[11,"서울","중부","수색S/S 154kV #2 BUS","수색S/S 154kV BUSTIE 이설관련 기초공사","BUSTIE 이설관련 기초 공사 - GCB 기초, DS 기초, LA 기초 공사","2021-03-22 09:00","2021-03-26 18:00","2021-03-22 09:00","2021-03-26 18:00","연속"]
[12,"서울","중부","양주은평#1 T/L","`21 중부PO 변전정비회사 총액공사","170kV GIS 조작시험","2021-03-10 10:00","2021-03-10 14:00","취소","취소","연속"]
[13,"서울","중부","양주은평#2 T/L","`21 중부PO 변전정비회사 총액공사","170kV GIS 조작시험","2021-03-11 10:00","2021-03-11 14:00","취소","취소","연속"]
[14,"서울","중부","중부아현 T/L","`21 중부PO 변전정비회사 총액공사","170kV GIS 조작시험","2021-03-16 10:00","2021-03-16 14:00","2021-03-16 10:00","2021-03-16 14:00","연속"]
[15,"서울","중부","중부용산#1 T/L","`21 중부PO 변전정비회사 총액공사","170kV GIS 조작시험","2021-03-12 10:00","2021-03-12 14:00","2021-03-12 10:00","2021-03-12 14:00","연속"]
[16,"서울","중부","중부용산#2 T/L","`21 중부PO 변전정비회사 총액공사","170kV GIS 조작시험","2021-03-15 10:00","2021-03-15 14:00","2021-03-15 10:00","2021-03-15 14:00","연속"]
[17,"서울","중부","지축현저#1 T/L","2020~2021 가공송전 정비회사 총액공사","수색은평#2 No.4 4회선 철탑 피뢰기 설치에 따른 병가선로 휴전","2021-03-09 07:30","2021-03-09 18:00","2021-04-10 07:30","2021-04-10 18:00","연속"]
[18,"서울","중부","지축현저#2 T/L","2020~2021 가공송전 정비회사 총액공사","지축현저#2 No.4 피뢰기 설치","2021-03-10 07:30","2021-03-10 18:00","2021-04-11 07:30","2021-04-11 18:00","연속"]
[19,"서울","직할","종로서소문 T/L","21년 직할 변전협력 총액공사","GIS 조작시험","2021-03-23 10:00","2021-03-23 12:00","2021-03-23 10:00","2021-03-23 12:00","연속"]
[20,"서울","직할","중앙서소문 T/L","21년 직할 변전협력 총액공사","GIS 조작시험","2021-03-23 13:00","2021-03-23 18:00","2021-03-23 13:00","2021-03-23 18:00","연속"]
[21,"서울","직할","순화동빙고 T/L","21년 직할 변전협력 총액공사","GIS보통점검","2021-03-05 10:00","2021-03-05 18:00","2021-03-05 10:00","2021-03-05 18:00","연속"]
[22,"서울","직할","신촌순화 T/L","21년 직할 변전협력 총액공사","GIS보통점검","2021-03-04 10:00","2021-03-04 18:00","2021-03-04 10:00","2021-03-04 18:00","연속"]
[23,"서울","직할","옥인운니#1 T/L","21년 직할 변전협력 총액공사","GIS 조작시험","2021-03-17 10:00","2021-03-17 18:00","2021-03-17 10:00","2021-03-17 18:00","연속"]
[24,"서울","직할","운니S/S 154kV CB 6100","21년 직할 변전협력 총액공사","GIS 조작시험","2021-03-16 10:00","2021-03-16 18:00","2021-03-16 10:00","2021-03-16 18:00","연속"]
[25,"서울","직할","옥인운니#2 T/L","21년 직할 변전협력 총액공사","GIS 조작시험","2021-03-18 10:00","2021-03-18 18:00","2021-03-18 10:00","2021-03-18 18:00","연속"]
[26,"서울","직할","원남미아#1 T/L","21년 직할 변전협력 총액공사","GIS조작시험,전자변교체","2021-03-03 10:00","2021-03-03 18:00","2021-03-03 10:00","2021-03-03 18:00","연속"]
[27,"남서울","동서울","강남선릉#2 T/L","170kV GIS 경보회로 로직변경","170kV GIS 경보회로 로직변경 선릉S/S 170kV GIS 조작시험","2021-03-05 14:00","2021-03-05 18:00","2021-03-05 14:00","2021-03-05 18:00","연속"]
[28,"남서울","동서울","강남선릉#1 T/L","170kV GIS 경보회로 로직변경","170kV GIS 경보회로 로직변경 선릉S/S 170kV GIS 조작시험","2021-03-05 09:00","2021-03-05 14:00","2021-03-05 09:00","2021-03-05 14:00","연속"]
[29,"남서울","동서울","잠실강남#2 T/L","170kV GIS 경보회로 로직변경","170kV GIS 경보회로 로직변경 잠실S/S 170kV GIS 조작시험","2021-03-04 14:00","2021-03-04 18:00","2021-03-04 14:00","2021-03-04 18:00","연속"]
[30,"남서울","동서울","잠실강남#1 T/L","170kV GIS 경보회로 로직변경","170kV GIS 경보회로 로직변경 잠실S/S 170kV GIS 조작시험","2021-03-04 09:00","2021-03-04 14:00","2021-03-04 09:00","2021-03-04 14:00","연속"]
[31,"남서울","동서울","동서울강동#1 T/L","세종-포천 고속도로건설 지장송전선로 지중화(이설)공사","임시철탑 건설 및 기설철탑과 임시철탑간 전력선 이설","2021-03-04 09:00","2021-03-08 18:00","2021-03-04 09:00","2021-03-08 18:00","연속"]
[32,"남서울","동서울","논현선릉#2 T/L","170kV GIS 정기점검","170kV GIS 조작시험","2021-03-09 14:00","2021-03-09 18:00","2021-03-09 14:00","2021-03-09 18:00","연속"]
[33,"남서울","동서울","논현선릉#1 T/L","170kV GIS 정기점검","170kV GIS 조작시험","2021-03-09 09:00","2021-03-09 14:00","2021-03-09 09:00","2021-03-09 14:00","연속"]
[34,"남서울","동서울","산성수서#2 T/L","170kV GIS 정기점검","170kV GIS 조작시험","2021-03-29 14:00","2021-03-29 18:00","2021-03-29 14:00","2021-03-29 18:00","연속"]
[35,"남서울","동서울","산성수서#1 T/L","170kV GIS 정기점검","170kV GIS 조작시험","2021-03-29 09:00","2021-03-29 14:00","2021-03-29 09:00","2021-03-29 14:00","연속"]
[36,"남서울","동서울","신장덕소#2 T/L","170kV GIS 초기점검","170kV GIS 초기점검","2021-03-03 10:00","2021-03-03 18:00","2021-03-03 10:00","2021-03-03 18:00","연속"]
[37,"남서울","동서울","신장덕소#1 T/L","170kV GIS 초기점검","170kV GIS 초기점검","2021-03-02 10:00","2021-03-02 18:00","2021-03-02 10:00","2021-03-02 18:00","연속"]
[38,"남서울","동서울","송파잠실#4 T/L","170kV GIS 정기점검","170kV GIS 조작시험","2021-03-25 09:00","2021-03-25 18:00","2021-03-25 09:00","2021-03-25 18:00","연속"]
[39,"남서울","동서울","송파잠실#3 T/L","170kV GIS 정기점검","잠실 : 170kV GIS 조작시험, 전자변교체 송파 : 170kV GIS 조작시험","2021-03-24 09:00","2021-03-24 18:00","2021-03-24 09:00","2021-03-24 18:00","연속"]
[40,"남서울","동서울","송파잠실#2 T/L","170kV GIS 정기점검","170kV GIS 조작시험","2021-03-23 09:00","2021-03-23 18:00","2021-03-23 09:00","2021-03-23 18:00","연속"]
[41,"남서울","동서울","송파잠실#1 T/L","170kV GIS 정기점검","170kV GIS 조작시험","2021-03-22 09:00","2021-03-22 18:00","2021-03-22 09:00","2021-03-22 18:00","연속"]
[42,"남서울","영등포","가양등촌#1 T/L","154kV 가양-등촌T/L 일부구간 지장이설공사","○ 지중송전 : 154kV OF 1200 x 2C x 0.320km 신설 및 철거 ○ 비금속광케이블(OFC) 신설 및 철거 ○ 관로 320m 신설 및 철거(요청자 시행) ○ 병행휴전 : 154kV 가양-등촌T/L 선종교체공사","2021-03-03 09:00","2021-05-17 18:00","취소","취소","연속"]
[43,"남서울","영등포","신광명광명#1 T/L","광명S/S 신광명-광명#2T/L GIS 2DS 보수","#2DS부 가동자 및 고동자 교체","2021-03-27 09:00","2021-03-28 18:00","2021-03-27 09:00","2021-03-28 18:00","연속"]
[44,"남서울","영등포","광명S/S 154kV #2 BUS","광명S/S 신광명-광명#2T/L GIS 2DS 보수","#2DS부 가동자 및 고동자 교체","2021-03-27 09:00","2021-03-28 18:00","2021-03-27 09:00","2021-03-28 18:00","연속"]
[45,"남서울","영등포","광명S/S 154kV CB 6100","광명S/S 154kV 6100 B/T CT 점검","- 모선보호반 전류치 C상 상이 원인 파악(A,B:0.38A, C:0.19A)","2021-03-05 09:00","2021-03-05 18:00","2021-03-05 09:00","2021-03-05 18:00","연속"]
[46,"남서울","영등포","신광명광명#2 T/L","광명S/S 신광명-광명#2T/L GIS 2DS 보수","#2DS부 가동자 및 고동자 교체","2021-03-27 09:00","2021-03-28 18:00","2021-03-27 09:00","2021-03-28 18:00","연속"]
[47,"남서울","영등포","광명구공#1 T/L","20~21년 영등포전력지사 변전정비회사 총액공사","구공SS 170kV GIS 차단기 조작기구부 교체 및 점검 광명SS 170kV GIS 보통점검","2021-03-02 09:00","2021-03-02 18:00","2021-03-16 09:00","2021-03-16 18:00","연속"]
[48,"남서울","영등포","구공대림#2 T/L","154kV 구공S/S 가산메트로#1, 2T/L 증설공사","154kV 구공S/S 가산메트로#1T/L 무부하가압","2021-03-04 17:00","2021-03-05 17:00","2021-03-04 17:00","2021-03-05 17:00","연속"]
[49,"남서울","영등포","구공S/S 154kV #60 BUS","154kV 구공S/S 가산메트로#1, 2T/L 증설공사","154kV 구공S/S 가산메트로#1T/L 무부하가압","2021-03-04 17:00","2021-03-05 17:00","2021-03-04 17:00","2021-03-05 17:00","연속"]
[50,"남서울","영등포","구공대림#1 T/L","154kV 구공S/S 가산메트로#1, 2T/L 증설공사","154kV 구공S/S 가산메트로#2T/L 무부하가압","2021-03-12 17:00","2021-03-13 17:00","2021-03-12 17:00","2021-03-13 17:00","연속"]
[51,"남서울","영등포","구공S/S 154kV #61 BUS","154kV 구공S/S 가산메트로#1, 2T/L 증설공사","154kV 구공S/S 가산메트로#2T/L 무부하가압","2021-03-12 17:00","2021-03-13 17:00","2021-03-12 17:00","2021-03-13 17:00","연속"]
[52,"남서울","영등포","구공S/S 154kV CB 6100","20~21년 영등포전력지사 변전정비회사 총액공사","구공SS 170kV GIS 하자점검 - 하자기한 만료전 점검시행","2021-03-15 09:00","2021-03-15 18:00","2021-03-15 09:00","2021-03-15 18:00","연속"]
[53,"남서울","영등포","광명구공#2 T/L","20~21년 영등포전력지사 변전정비회사 총액공사","구공SS 170kV GIS 조작기구부 교체 및 점검 광명S/S 170kV GIS 보통점검","2021-03-03 09:00","2021-03-03 18:00","2021-03-17 09:00","2021-03-17 18:00","연속"]
[54,"남서울","영등포","대방S/S 154kV #1 BUS","154kV 대방인출전력구 OF케이블 선종교체공사","154kV 대방인출전력구 내 154kV 대방-신길#2T/L 선종교체공사 가압 전 상시험 확인","2021-03-26 09:00","2021-03-26 18:00","2021-03-26 09:00","2021-03-26 18:00","연속"]
[55,"남서울","영등포","독산대방#2 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2021-03-31 09:00","2021-04-01 18:00","취소","취소","연속"]
[56,"남서울","영등포","목동양천#1 T/L","목동S/S 170kV GIS 전자변 고착관련 점검","- 전자변 고착 관련 차단부 점검","2021-03-04 09:00","2021-03-04 18:00","2021-03-04 09:00","2021-03-04 18:00","연속"]
[57,"남서울","영등포","신정목동#2 T/L","20~21년 영등포전력지사 변전정비회사 총액공사","목동SS 170kV GIS 조작기구부 교체 및 점검","2021-03-05 09:00","2021-03-05 18:00","2021-03-06 09:00","2021-03-06 18:00","연속"]
[58,"남서울","영등포","시흥S/S 154kV #1 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2021-03-22 09:00","2021-03-23 13:00","2021-03-22 09:00","2021-03-23 13:00","연속"]
[59,"남서울","영등포","시흥S/S 154kV #2 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","부분방전 시스템 센서 설치","2021-03-08 09:00","2021-03-08 18:00","2021-03-08 09:00","2021-03-08 18:00","연속"]
[60,"남서울","영등포","시흥독산#1 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2021-03-08 09:00","2021-03-10 18:00","2021-03-08 09:00","2021-03-10 18:00","연속"]
[61,"남서울","영등포","시흥독산#2 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2021-03-11 09:00","2021-03-17 18:00","2021-03-11 09:00","2021-03-17 18:00","연속"]
[62,"남서울","영등포","시흥S/S 154kV #1 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2021-03-15 09:00","2021-03-16 13:00","2021-03-15 09:00","2021-03-16 13:00","연속"]
[63,"남서울","영등포","시흥S/S 154kV #2 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2021-03-16 14:00","2021-03-17 18:00","2021-03-16 14:00","2021-03-17 18:00","연속"]
[64,"남서울","영등포","시흥S/S 154kV #1 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2021-03-18 09:00","2021-03-19 13:00","2021-03-18 09:00","2021-03-19 13:00","연속"]
[65,"남서울","영등포","시흥독산#2 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","BUSTIE 2BUS 무부하가압용","2021-03-27 14:00","2021-03-27 15:00","2021-03-27 14:00","2021-03-27 15:00","연속"]
[66,"남서울","영등포","시흥S/S 154kV #2 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2021-03-26 14:00","2021-03-27 18:00","2021-03-26 14:00","2021-03-27 18:00","연속"]
[67,"남서울","영등포","시흥독산#1 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","BUSTIE 1BUS, CB 무부하가압용","2021-03-26 13:00","2021-03-26 14:00","2021-03-26 13:00","2021-03-26 14:00","연속"]
[68,"남서울","영등포","시흥S/S 154kV #1 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2021-03-25 09:00","2021-03-26 13:00","2021-03-25 09:00","2021-03-26 13:00","연속"]
[69,"남서울","영등포","시흥S/S 154kV CB 6100","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2021-03-25 09:00","2021-03-27 18:00","2021-03-25 09:00","2021-03-27 18:00","연속"]
[70,"남서울","영등포","시흥S/S 154kV #2 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2021-03-23 14:00","2021-03-24 14:00","2021-03-23 14:00","2021-03-24 14:00","연속"]
[71,"남서울","영등포","신광명시흥#2 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2021-03-22 09:00","2021-03-24 18:00","2021-03-22 09:00","2021-03-24 18:00","연속"]
[72,"남서울","영등포","시흥S/S 154kV #2 BUS","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2021-03-19 14:00","2021-03-20 18:00","2021-03-19 14:00","2021-03-20 18:00","연속"]
[73,"남서울","영등포","신광명시흥#1 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2021-03-18 09:00","2021-03-20 18:00","2021-03-18 09:00","2021-03-20 18:00","연속"]
[74,"남서울","영등포","천왕오류#2 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 수분 및 SO2 측정 GIS 내부점검 오링 및 흡습제 교체 경보 및 조작시험","2021-03-02 09:00","2021-03-03 18:00","2021-03-03 09:00","2021-03-04 18:00","연속"]
[75,"남서울","영등포","중동화곡#2 T/L","화곡S/S 170kV GIS 전자변 교체, 조작시험(중동-화곡#2)","- 공압식 차단기 지연트립 발생 관련 전자변 교체 시행 - 차단기 조작시험","2021-03-13 14:00","2021-03-13 18:00","취소","취소","연속"]
[76,"남서울","영등포","중동화곡#1 T/L","화곡S/S 170kV GIS 전자변 교체, 조작시험(중동-화곡#1)","- 공압식 차단기 지연트립 발생 관련 전자변 교체 시행 - 차단기 조작시험","2021-03-13 09:00","2021-03-13 14:00","취소","취소","연속"]
[77,"남서울","영등포","화곡S/S 154kV CB 6100","화곡S/S 170kV GIS 전자변 교체, 조작시험","- 공압식 차단기 지연트립 발생 관련 전자변 교체 시행 - 차단기 조작시험","2021-03-29 09:00","2021-03-29 18:00","2021-03-29 09:00","2021-03-29 18:00","연속"]
[78,"남서울","영등포","고강화곡#2 T/L","화곡S/S 170kV GIS 전자변 교체, 조작시험(고강-화곡#2)","- 공압식 차단기 지연트립 발생 관련 전자변 교체 시행 - 차단기 조작시험","2021-03-22 09:00","2021-03-22 18:00","2021-03-19 14:00","2021-03-19 18:00","연속"]
[79,"남서울","영등포","고강화곡#1 T/L","화곡S/S 170kV GIS 전자변 교체, 조작시험(고강-화곡#1)","- 공압식 차단기 지연트립 발생 관련 전자변 교체 시행 - 차단기 조작시험","2021-03-19 09:00","2021-03-19 18:00","2021-03-19 09:00","2021-03-19 14:00","연속"]
[80,"남서울","직할","사당신림 T/L","170kV GIS 정밀점검공사","170kV GIS 정밀점검공사","2021-03-29 09:00","2021-03-31 14:00","2021-03-29 09:00","2021-03-31 14:00","연속"]
[81,"인천","김포","신경서경서#1 T/L","경서S/S 154kV 신경서-경서#1T/L GIS 조작시험","경서S/S 154kV 신경서-경서#1T/L GIS 조작시험","2021-03-08 10:00","2021-03-08 14:00","2021-03-08 10:00","2021-03-08 14:00","연속"]
[82,"인천","김포","신경서경서#2 T/L","경서S/S 154kV 신경서-경서#2T/L GIS 조작시험","경서S/S 154kV 신경서-경서#2T/L GIS 조작시험","2021-03-08 14:00","2021-03-08 18:00","2021-03-08 14:00","2021-03-08 18:00","연속"]
[83,"인천","김포","신경서경서#3 T/L","경서S/S 154kV 신경서-경서#3T/L GIS 조작시험","경서S/S 154kV 신경서-경서#3T/L GIS 조작시험","2021-03-09 10:00","2021-03-09 14:00","2021-03-09 10:00","2021-03-09 14:00","연속"]
[84,"인천","김포","경서북인천#2 T/L","경서S/S 154kV 경서-북인천#2T/L GIS 조작시험","경서S/S 154kV 경서-북인천#2T/L GIS 조작시험","2021-03-09 14:00","2021-03-09 18:00","2021-03-09 14:00","2021-03-09 18:00","연속"]
[85,"인천","김포","계양김포#1 T/L","김포S/S 154kV 계양-김포#1T/L GIS 보통점검","김포S/S 154kV 계양-김포#1T/L GIS 보통점검","2021-03-16 10:00","2021-03-16 18:00","2021-03-16 10:00","2021-03-16 18:00","연속"]
[86,"인천","김포","김포장기#2 T/L","김포S/S 154kV 김포-장기#2T/L GIS 보통점검","김포S/S 154kV 김포-장기#2T/L GIS 보통점검","2021-03-19 10:00","2021-03-19 18:00","2021-03-19 10:00","2021-03-19 18:00","연속"]
[87,"인천","김포","계양김포#2 T/L","김포S/S 154kV 계양-김포#2T/L GIS 보통점검","김포S/S 154kV 계양-김포#2T/L GIS 보통점검","2021-03-17 10:00","2021-03-17 18:00","2021-03-17 10:00","2021-03-17 18:00","연속"]
[88,"인천","김포","김포장기#1 T/L","김포S/S 154kV 김포-장기#1T/L GIS 보통점검","김포S/S 154kV 김포-장기#1T/L GIS 보통점검","2021-03-18 10:00","2021-03-18 18:00","2021-03-18 10:00","2021-03-18 18:00","연속"]
[89,"인천","김포","신김포장기#1 T/L","신김포S/S 154kV 신김포-장기#1T/L GIS 보통점검","신김포S/S 154kV 신김포-장기#1T/L GIS 보통점검","2021-03-11 10:00","2021-03-11 18:00","2021-03-11 10:00","2021-03-11 18:00","연속"]
[90,"인천","김포","신김포S/S 154kV CB 6100","신김포S/S 154kV #60-#65 BUS TIE GIS 보통점검","신김포S/S 154kV #60-#65 BUS TIE GIS 보통점검","2021-03-10 10:00","2021-03-10 18:00","취소","취소","연속"]
[91,"인천","김포","신김포장기#2 T/L","신김포S/S 154kV 신김포-장기#2T/L GIS 보통점검","신김포S/S 154kV 신김포-장기#2T/L GIS 보통점검","2021-03-12 10:00","2021-03-12 18:00","2021-03-12 10:00","2021-03-12 18:00","연속"]
[92,"인천","김포","왕길양촌#1 T/L","154kV왕길양촌#1T/L 피뢰기 설치공사","154kV왕길양촌#1T/L 피뢰기 설치공사","2021-03-19 08:00","2021-03-19 18:00","2021-03-19 08:00","2021-03-19 18:00","연속"]
[93,"인천","부평","송월남인천#1 T/L","남인천S/S 송월남인천#1 T/L 조작시험 공사","남인천S/S 송월남인천#1 T/L 조작시험 공사","2021-03-22 09:00","2021-03-22 14:00","취소","취소","연속"]
[94,"인천","부평","송현남인천 T/L","남인천S/S 송현남인천 T/L 조작시험 공사","남인천S/S 송현남인천 T/L 조작시험 공사","2021-03-24 14:00","2021-03-24 18:00","취소","취소","연속"]
[95,"인천","부평","인천남인천#2 T/L","남인천S/S 인천남인천#2 T/L 조작시험 공사","남인천S/S 인천남인천#2 T/L 조작시험 공사","2021-03-24 09:00","2021-03-24 14:00","취소","취소","연속"]
[96,"인천","부평","송월남인천#2 T/L","남인천S/S 송월남인천#2 T/L 조작시험 공사","남인천S/S 송월남인천#2 T/L 조작시험 공사","2021-03-22 14:00","2021-03-22 18:00","취소","취소","연속"]
[97,"인천","부평","송현포스코CC#2 T/L","154kV송현포스코CC#2T/L 피뢰기 설치공사","154kV송현포스코CC#2T/L 피뢰기 설치공사","2021-03-19 08:00","2021-03-19 18:00","취소","취소","연속"]
[98,"인천","부평","송현송월#1 T/L","154kV 송현-송월 #1 T/L OF케이블 선종교체공사","154kV 송현S/S ∼ 송월S/S [OF 1,200㎟(D) → XLPE 2,000㎟ 1C, 2.2km]","2021-03-15 09:00","2021-05-23 18:00","2021-03-15 09:00","2021-05-23 18:00","연속"]
[99,"인천","부평","신가좌S/S 154kV SEC CB 61620","신가좌S/S 154kV #61-#62 SEC GIS 보통점검 공사","신가좌S/S 154kV #61-#62 SEC GIS 보통점검 공사","2021-03-30 09:00","2021-03-30 18:00","2021-03-30 09:00","2021-03-30 18:00","연속"]
[100,"인천","부평","신현송현#2 T/L","신현S/S 신현송현#2 T/L GIS 하자점검 공사","신현S/S 신현송현#2 T/L GIS 하자점검 공사","2021-03-12 09:00","2021-03-12 18:00","취소","취소","연속"]
[101,"인천","부평","신현송현#1 T/L","신현S/S 신현송현#1 T/L GIS 하자점검 공사","신현S/S 신현송현#1 T/L GIS 하자점검 공사","2021-03-11 09:00","2021-03-11 18:00","취소","취소","연속"]
[102,"인천","부평","신가좌주안#1 T/L","154kV신가좌주안#1T/L 피뢰기 설치공사","154kV신가좌주안#1T/L 피뢰기 설치공사","2021-03-01 08:00","2021-03-01 13:00","2021-03-01 08:00","2021-03-01 13:00","연속"]
[103,"인천","부평","주안만수#2 T/L","주안S/S 주안만수#2T/L GIS 보통점검 공사","주안S/S 주안만수#2T/L GIS 보통점검 공사","2021-03-08 09:00","2021-03-08 18:00","취소","취소","연속"]
[104,"인천","부평","관교주안 T/L","주안S/S 주안관교T/L GIS 보통점검 공사","주안S/S 주안관교T/L GIS 보통점검 공사","2021-03-04 09:00","2021-03-04 18:00","취소","취소","연속"]
[105,"인천","부평","주안만수#1 T/L","주안S/S 주안만수#1T/L GIS 보통점검 공사","주안S/S 주안만수#1T/L GIS 보통점검 공사","2021-03-05 09:00","2021-03-05 18:00","취소","취소","연속"]
[106,"인천","부평","학익연수#2 T/L","학익S/S 학익연수#2 T/L 보통점검 공사","학익S/S 학익연수#2 T/L 보통점검 공사","2021-03-26 09:00","2021-03-26 18:00","취소","취소","연속"]
[107,"인천","부평","학익연수#1 T/L","학익S/S 학익연수#1 T/L 보통점검 공사","학익S/S 학익연수#1 T/L 보통점검 공사","2021-03-25 09:00","2021-03-25 18:00","취소","취소","연속"]
[108,"인천","부평","남인천학익#2 T/L","학익S/S 남인천학익#2 T/L GIS 보통점검 공사","학익S/S 남인천학익#2 T/L GIS 보통점검 공사","2021-03-19 09:00","2021-03-19 18:00","취소","취소","연속"]
[109,"인천","부평","남인천학익#1 T/L","학익S/S 남인천학익#1 T/L GIS 보통점검 공사","학익S/S 남인천학익#1 T/L GIS 보통점검 공사","2021-03-18 09:00","2021-03-18 18:00","취소","취소","연속"]
[110,"인천","시흥","오봉고잔#2 T/L","고잔S/S 154kV 오봉고잔#2T/L GIS보통점검","고잔S/S 154kV 오봉고잔#2T/L GIS보통점검","2021-03-23 10:00","2021-03-23 18:00","2021-03-23 10:00","2021-03-23 18:00","연속"]
[111,"인천","시흥","오봉고잔#1 T/L","고잔S/S 154kV 오봉고잔#1T/L GIS보통점검","고잔S/S 154kV 오봉고잔#1T/L GIS보통점검","2021-03-22 10:00","2021-03-22 18:00","2021-03-22 10:00","2021-03-22 18:00","연속"]
[112,"인천","시흥","신시흥남동#2 T/L","154kV 신시흥-남동#2 T/L 선종교체공사","남동EBG~J/B#2 0.926km 교체(OF→XLPE)","2021-03-09 09:00","2021-05-07 18:00","2021-03-09 07:00","2021-05-07 18:00","연속"]
[113,"인천","시흥","도림오봉#1 T/L","154kV 도림-오봉#1T/L 피뢰기 설치공사","154kV 도림-오봉#1T/L 피뢰기 설치공사 -1기(오봉CH)","2021-03-02 08:00","2021-03-02 18:00","2021-03-02 08:00","2021-03-02 18:00","연속"]
[114,"인천","시흥","동시화서시화 T/L","동시화S/S #5M.Tr 증설공사","#5M.Tr 초기가압","2021-03-10 13:30","2021-03-11 16:00","2021-03-10 13:30","2021-03-11 16:00","연속"]
[115,"인천","시흥","동시화서시화 T/L","동시화S/S GIS 설치공사","신규 60-61, 65-66SEC 모선보호반 설치에 따른 보호회로 이설","2021-03-07 09:00","2021-03-07 16:00","2021-03-07 09:00","2021-03-07 16:00","연속"]
[116,"인천","시흥","동시화서시화 T/L","서시화S/S 170kV GIS 대체공사(3차)","북시화서시화#1T/L, #1M.Tr, 170kV BUS-TIE GIS 대체(무부하가압 1시간) 기타부대공사 1식","2021-03-15 17:00","2021-03-15 18:00","2021-03-15 17:00","2021-03-15 18:00","연속"]
[117,"인천","시흥","서시화S/S 154kV CB 6100","서시화S/S 170kV GIS 대체공사(3차)","북시화서시화#1T/L, #1M.Tr, 170kV BUS-TIE GIS 대체 기타부대공사 1식","2021-03-12 07:30","2021-04-09 18:00","2021-03-12 07:30","2021-04-09 18:00","연속"]
[118,"인천","시흥","북시화서시화#1 T/L","서시화S/S 170kV GIS 대체공사(3차)","북시화서시화#1T/L, #1M.Tr, 170kV BUS-TIE GIS 대체 기타부대공사 1식","2021-03-12 07:30","2021-04-09 18:00","2021-03-12 07:30","2021-04-09 18:00","연속"]
[119,"인천","시흥","동시화서시화 T/L","서시화S/S 170kV GIS 대체공사(3차)","북시화서시화#1T/L, #1M.Tr, 170kV BUS-TIE GIS 대체(무부하가압 1시간) 기타부대공사 1식","2021-03-13 15:00","2021-03-13 16:30","2021-03-13 15:00","2021-03-13 16:30","연속"]
[120,"인천","시흥","서안양소래 T/L","154kV 서서울-소래T/L OPGW 증설공사","OPGW 24C→48C 교체(서안양~No.63) 및 OPGW 신규 48C 시설 (No.76~No.92)","2021-03-27 08:00","2021-04-03 18:00","2021-03-27 08:00","2021-04-03 18:00","연속"]
[121,"인천","시흥","온수소래 T/L","154kV 서서울-소래T/L OPGW 증설공사","GW→OPGW 교체 및 신규 48C 시설 (No.76~No.92)","2021-03-26 08:00","2021-04-03 18:00","2021-03-26 08:00","2021-03-28 18:00","연속"]
[122,"인천","시흥","신시흥도림#2 T/L","154kV 신시흥-남동T/L 지장송전선로 이설공사","○ 구간 : No.16~18 ○ 전력선 : ACSR/AW 410㎟ × 2B × 4C ○ 작업내용 : 임시선로→본선로 ※철탑 1기 설치(No.17)","2021-03-09 07:00","2021-03-14 18:00","2021-03-09 07:00","2021-03-14 18:00","연속"]
[123,"인천","시흥","신시흥남동#2 T/L","154kV 신시흥-남동T/L 지장송전선로 이설공사","○ 구간 : No.16~18 ○ 전력선 : ACSR/AW 410㎟ × 2B × 4C ○ 작업내용 : 임시선로→본선로 ※철탑 1기 설치(No.17)","2021-03-09 07:00","2021-03-14 18:00","2021-03-09 07:00","2021-03-14 18:00","연속"]
[124,"인천","시흥","신시흥도림#1 T/L","154kV 신시흥-남동T/L 지장송전선로 이설공사","○ 구간 : No.16~18 ○ 전력선 : ACSR/AW 410㎟ × 2B × 4C ○ 작업내용 : 임시선로→본선로 ※철탑 1기 설치(No.17)","2021-03-03 07:00","2021-03-08 18:00","2021-03-03 07:00","2021-03-08 18:00","연속"]
[125,"인천","시흥","신시흥남동#1 T/L","154kV 신시흥-남동T/L 지장송전선로 이설공사","○ 구간 : No.16~18 ○ 전력선 : ACSR/AW 410㎟ × 2B × 4C ○ 작업내용 : 임시선로→본선로 ※철탑 1기 설치(No.17)","2021-03-03 07:00","2021-03-08 18:00","2021-03-03 07:00","2021-03-08 18:00","연속"]
[126,"인천","직할","갈산S/S 154kV CB 6100","345kV 갈산S/S #61, 62 D.Tr GIS설치공사","-170kV GIS 2CCT 설치","2021-03-05 18:00","2021-03-06 18:00","2021-03-05 18:00","2021-03-06 18:00","연속"]
[127,"인천","직할","갈산S/S 154kV #60 BUS","345kV 갈산S/S #61, 62 D.Tr GIS 설치공사","-170kV GIS 2CCT 설치 - 기타부대공사 1식 설치","2021-03-02 09:00","2021-03-06 18:00","2021-03-02 09:00","2021-03-06 18:00","연속"]
[128,"인천","직할","갈산S/S 154kV #61 BUS","345kV 갈산S/S #61, 62 D.Tr GIS 설치공사","-170kV GIS 2CCT 설치 - 기타부대공사 1식 설치","2021-03-02 09:00","2021-03-06 18:00","2021-03-02 09:00","2021-03-06 18:00","연속"]
[129,"인천","직할","갈산S/S 154kV CB 6100","345kV 갈산S/S #61, 62 D.Tr GIS설치공사","-170kV GIS 2CCT 설치","2021-03-11 18:00","2021-03-12 18:00","2021-03-11 18:00","2021-03-12 18:00","연속"]
[130,"인천","직할","계양원창 T/L","임학계양T/L 항공장애표시구 정비공사","임학계양#1T/L 항공장애표시구 철거 및 임학계양#2T/L 추가시설","2021-03-22 07:00","2021-03-24 13:00","2021-03-22 07:00","2021-03-24 13:00","연속"]
[131,"인천","직할","임학계양#1 T/L","임학계양T/L 항공장애표시구 정비공사","임학계양#1T/L 항공장애표시구 철거 및 임학계양#2T/L 추가시설","2021-03-22 07:00","2021-03-24 13:00","2021-03-22 07:00","2021-03-24 13:00","연속"]
[132,"인천","직할","계양북인천 T/L","임학계양T/L 항공장애표시구 정비공사","임학계양#1T/L 항공장애표시구 철거 및 임학계양#2T/L 추가시설","2021-03-24 14:00","2021-03-26 18:00","2021-03-24 14:00","2021-03-26 18:00","연속"]
[133,"인천","직할","임학계양#2 T/L","임학계양T/L 항공장애표시구 정비공사","임학계양#1T/L 항공장애표시구 철거 및 임학계양#2T/L 추가시설","2021-03-24 14:00","2021-03-26 18:00","2021-03-24 14:00","2021-03-26 18:00","연속"]
[134,"인천","직할","신부평고강#2 T/L","154kV신부평고강#2T/L 피뢰기 설치공사","154kV신부평고강#2T/L 피뢰기 설치공사","2021-03-20 08:00","2021-03-20 11:00","취소","취소","연속"]
[135,"인천","직할","신부평고강#1 T/L","154kV신부평고강#1T/L 피뢰기 설치공사","154kV신부평고강#1T/L 피뢰기 설치공사","2021-03-20 11:00","2021-03-21 18:00","취소","취소","매일"]
[136,"인천","직할","신부평도당#1 T/L","154kV 갈산-부흥,도당 지중T/L 인출정비공사","○ 154kV XLPE 2,000㎟, 2C×0.4km(갈산-도당)설치 및 기설선로 철거","2021-03-30 10:00","2021-04-22 18:00","2021-03-30 10:00","2021-04-22 18:00","연속"]
[137,"인천","직할","부천도당#2 T/L","도당S/S 도당부천#2T/L GIS 하자점검","도당S/S 도당부천#1T/L GIS 하자점검","2021-03-03 14:00","2021-03-03 18:00","취소","취소","연속"]
[138,"인천","직할","부천도당#1 T/L","도당S/S 도당부천#1T/L GIS 초기점검","도당S/S 도당부천#1T/L GIS 초기점검","2021-03-03 09:30","2021-03-03 14:00","취소","취소","연속"]
[139,"인천","직할","경서북인천#1 T/L","북인천S/S 경서북인천#1T/L 보호반대체","북인천S/S 경서북인천#1T/L 보호반대체","2021-03-22 09:30","2021-03-26 18:00","취소","취소","연속"]
[140,"인천","직할","신부평중동#1 T/L","신부평,중동S/S 신부평중동#1T/L 하자점검(양단)","신부평,중동S/S 신부평중동#1T/L 신부평(조작), 중동(하자)","2021-03-29 09:30","2021-03-29 18:00","2021-03-29 09:30","2021-03-29 18:00","연속"]
[141,"인천","직할","신부평부흥#2 T/L","154kV 갈산-부흥,도당 지중T/L 인출정비공사","○ 154kV XLPE 2,000㎟, 2C×0.2㎞(갈산-부흥)설치 및 기설선로 철거","2021-03-08 10:00","2021-03-29 18:00","2021-03-08 10:00","2021-03-29 18:00","연속"]
[142,"인천","직할","신부평중동#2 T/L","중동S/S 신부평중동#2T/L 하자점검","중동S/S 신부평중동#2T/L 하자점검","2021-03-30 09:30","2021-03-30 18:00","2021-03-30 09:30","2021-03-30 18:00","연속"]
[143,"인천","직할","신부평중동#3 T/L","중동S/S 신부평중동#3T/L 하자점검","중동S/S 신부평중동#3T/L 하자점검","2021-03-31 09:30","2021-03-31 18:00","2021-03-31 09:30","2021-03-31 18:00","연속"]
[144,"인천","직할","중동화곡#1 T/L","154kV중동화곡#1T/L 피뢰기 설치공사","154kV중동화곡#1T/L 피뢰기 설치공사","2021-03-27 08:00","2021-03-28 18:00","취소","취소","매일"]
[145,"인천","직할","신부평중동#1 T/L","신부평,중동S/S 신부평중동#1T/L 하자점검(양단)","신부평,중동S/S 신부평중동#1T/L 신부평(조작), 중동(하자)","2021-03-29 09:30","2021-03-29 18:00","취소","취소","연속"]
[146,"경기북부","고양","양주고양#1 T/L","고양시국도대체우회도로 지장이설공사(양주-고양)","철탑 : 3기설치 및 2기 철거","2021-03-23 07:00","2021-03-30 18:00","2021-03-23 07:00","2021-03-30 18:00","연속"]
[147,"경기북부","고양","양주고양#2 T/L","고양시국도대체우회도로 지장이설공사(양주-고양)","철탑 : 3기설치 및 2기 철거","2021-03-15 07:00","2021-03-22 18:00","2021-03-15 07:00","2021-03-22 18:00","연속"]
[148,"경기북부","고양","양주금촌#2 T/L","20-21년 가공송전 정비회사 총액공사","ㅇ 154kV 송전선로용 피뢰기 설치공사","2021-03-16 07:00","2021-03-19 18:00","2021-03-16 07:00","2021-03-19 18:00","연속"]
[149,"경기북부","고양","덕이호수#2 T/L","2021 고양P/O 변전정비회사 총액공사(덕이-호수#2)","170kV GIS 보통점검","2021-03-30 10:00","2021-03-30 18:00","2021-03-30 10:00","2021-03-30 18:00","연속"]
[150,"경기북부","고양","덕이호수#1 T/L","2021 고양P/O 변전정비회사 총액공사(덕이-호수#1)","170kV GIS 보통점검","2021-03-29 10:00","2021-03-29 18:00","2021-03-29 10:00","2021-03-29 18:00","연속"]
[151,"경기북부","고양","문산월롱#2 T/L","2021년 가공송전 순시점검 위탁공사","송전설비 정밀점검 No.1~13","2021-03-24 07:30","2021-03-25 18:00","2021-03-10 07:30","2021-03-11 18:00","연속"]
[152,"경기북부","고양","신덕은문산#2 T/L","2021년 가공송전 순시점검 위탁공사","송전설비 정밀점검 No.9~19, 초기점검 No.10~11","2021-03-24 07:30","2021-03-25 18:00","2021-03-10 07:30","2021-03-11 18:00","연속"]
[153,"경기북부","고양","문산월롱#1 T/L","2021년 가공송전 순시점검 위탁공사","송전설비 정밀점검 No.1~13","2021-03-22 07:30","2021-03-23 18:00","2021-03-08 07:30","2021-03-09 18:00","연속"]
[154,"경기북부","고양","신덕은문산#1 T/L","2021년 가공송전 순시점검 위탁공사","송전설비 정밀점검 No.9~19, 초기점검 No.10~11","2021-03-22 07:30","2021-03-23 18:00","2021-03-08 07:30","2021-03-09 18:00","연속"]
[155,"경기북부","고양","신덕은S/S #4 M.Tr","2021 고양P/O 변전정비회사 총액공사(#4M.Tr 2차 GIS)","170kV GIS 보통점검","2021-03-11 10:00","2021-03-11 18:00","취소","취소","연속"]
[156,"경기북부","고양","일산송포#1 T/L","2021 고양P/O 변전정비회사 총액공사(일산-송포#1 GIS)","170kV GIS 하자점검","2021-03-09 10:00","2021-03-09 18:00","2021-03-09 10:00","2021-03-09 18:00","연속"]
[157,"경기북부","고양","일산송포#2 T/L","2021 고양P/O 변전정비회사 총액공사(일산-송포#2 GIS)","170kV GIS 하자점검","2021-03-10 10:00","2021-03-10 18:00","2021-03-10 10:00","2021-03-10 18:00","연속"]
[158,"경기북부","구리","덕소S/S 154KV SEC CB 65660","일진제 154kV GIS 수동조작장치 구조개선공사","일진제 154kV GIS 수동조작장치 구조개선공사","2021-03-03 14:00","2021-03-03 18:00","2021-03-03 14:00","2021-03-03 18:00","연속"]
[159,"경기북부","구리","덕소S/S 154KV CB 6100","일진제 154kV GIS 수동조작장치 구조개선공사","일진제 154kV GIS 수동조작장치 구조개선공사","2021-03-04 09:00","2021-03-04 14:00","2021-03-04 09:00","2021-03-04 14:00","연속"]
[160,"경기북부","구리","덕소마석#2 T/L","일진제 154kV GIS 수동조작장치 구조개선공사","일진제 154kV GIS 수동조작장치 구조개선공사","2021-03-29 12:00","2021-03-29 15:00","2021-03-29 12:00","2021-03-29 15:00","연속"]
[161,"경기북부","구리","덕소마석#1 T/L","일진제 154kV GIS 수동조작장치 구조개선공사","일진제 154kV GIS 수동조작장치 구조개선공사","2021-03-29 09:00","2021-03-29 12:00","2021-03-29 09:00","2021-03-29 12:00","연속"]
[162,"경기북부","구리","신장덕소#2 T/L","일진제 154kV GIS 수동조작장치 구조개선공사","일진제 154kV GIS 수동조작장치 구조개선공사","2021-03-16 14:00","2021-03-16 18:00","2021-03-16 14:00","2021-03-16 18:00","연속"]
[163,"경기북부","구리","신장덕소#1 T/L","일진제 154kV GIS 수동조작장치 구조개선공사","일진제 154kV GIS 수동조작장치 구조개선공사","2021-03-16 09:00","2021-03-16 14:00","2021-03-16 09:00","2021-03-16 14:00","연속"]
[164,"경기북부","구리","덕소S/S 154KV CB 6200","일진제 154kV GIS 수동조작장치 구조개선공사","일진제 154kV GIS 수동조작장치 구조개선공사","2021-03-04 14:00","2021-03-04 18:00","2021-03-04 14:00","2021-03-04 18:00","연속"]
[165,"경기북부","구리","덕소S/S 154KV SEC CB 60610","일진제 154kV GIS 수동조작장치 구조개선공사","일진제 154kV GIS 수동조작장치 구조개선공사","2021-03-03 09:00","2021-03-03 14:00","2021-03-03 09:00","2021-03-03 14:00","연속"]
[166,"경기북부","구리","미금덕소#1 T/L","송전선로 추락방지시설 설치공사","154kV 미금-덕소T/L 추락방지시설 5기 설치(8호~12호)","2021-03-08 08:00","2021-03-10 18:00","2021-03-08 08:00","2021-03-10 18:00","연속"]
[167,"경기북부","구리","미금S/S 154kV SEC CB 65660","`20~21 구리전력 변전정비 총액공사","미금SS #65-66 SEC GIS 개폐타임측정","2021-03-19 09:00","2021-03-19 18:00","2021-03-19 09:00","2021-03-19 18:00","연속"]
[168,"경기북부","구리","미금덕소#2 T/L","송전선로 추락방지시설 설치공사","154kV 미금-덕소T/L 추락방지시설 5기 설치(8호~12호)","2021-03-11 08:00","2021-03-12 18:00","2021-03-11 08:00","2021-03-12 18:00","연속"]
[169,"경기북부","구리","미금S/S 154kV CB 6100","`20~21 구리전력 변전정비 총액공사","미금S/S 154kV #! BUS-TIE GIS 초기점검공사","2021-03-18 09:00","2021-03-18 18:00","2021-03-18 09:00","2021-03-18 18:00","연속"]
[170,"경기북부","구리","서종S/S 154kV CB 6100","일진제 154kV GIS 수동조작장치 구조개선공사","일진제 154kV GIS 수동조작장치 구조개선공사","2021-03-25 09:00","2021-03-25 12:00","2021-03-25 09:00","2021-03-25 12:00","연속"]
[171,"경기북부","구리","신포천덕계#1 T/L","'20~'21년 경기북부 직할 가공송전 정비회사 총액공사","154kV 피뢰기 설치공사","2021-03-22 07:00","2021-03-30 18:00","2021-03-22 07:00","2021-03-30 18:00","연속"]
[172,"경기북부","구리","신포천전곡#2 T/L","'20~'21년 경기북부 직할 가공송전 정비회사 총액공사","154kV 피뢰기 설치공사 상단병가선로","2021-03-22 07:00","2021-03-22 18:00","2021-03-22 07:00","2021-03-22 18:00","연속"]
[173,"경기북부","구리","팔당H/P 154kV #2 M.Tr 1차 GIS","팔당수력S/Y 장기사용 154kV GIS 대체공사","○ 154kV GIS x 4CCT 철거 ○ 154kV GIS x 5CCT 설치 ○ 154kV 모선보호반 x 1Set 설치 ○ 기타 부대공사 1식","2021-03-19 07:00","2021-04-08 18:00","2021-03-19 07:00","2021-04-08 18:00","연속"]
[174,"경기북부","구리","팔당H/P 154kV BUS","팔당수력S/Y 장기사용 154kV GIS 대체공사","○ 154kV GIS x 4CCT 철거 ○ 154kV GIS x 5CCT 설치 ○ 154kV 모선보호반 x 1Set 설치 ○ 기타 부대공사 1식","2021-03-19 07:00","2021-03-21 18:00","2021-03-19 07:00","2021-03-21 18:00","연속"]
[175,"경기북부","구리","덕소팔당HP T/L","팔당수력S/Y 장기사용 154kV GIS 대체공사","○ 154kV GIS x 4CCT 철거 ○ 154kV GIS x 5CCT 설치 ○ 154kV 모선보호반 x 1Set 설치 ○ 기타 부대공사 1식","2021-03-19 07:00","2021-03-21 18:00","2021-03-19 07:00","2021-03-21 18:00","연속"]
[176,"경기북부","구리","팔당H/P 154kV CB 6133","팔당수력S/Y 장기사용 154kV GIS 대체공사","○ 154kV GIS x 4CCT 철거 ○ 154kV GIS x 5CCT 설치 ○ 154kV 모선보호반 x 1Set 설치 ○ 기타 부대공사 1식","2021-03-19 07:00","2021-03-21 18:00","2021-03-19 07:00","2021-03-21 18:00","연속"]
[177,"경기북부","구리","덕소팔당HP청평HP T/L","팔당수력S/Y 장기사용 154kV GIS 대체공사","○ 154kV GIS x 4CCT 철거 ○ 154kV GIS x 5CCT 설치 ○ 154kV 모선보호반 x 1Set 설치 ○ 기타 부대공사 1식","2021-03-19 07:00","2021-04-08 18:00","2021-03-19 07:00","2021-04-08 18:00","연속"]
[178,"경기북부","구리","포천S/S 154kV #2 BUS","포천S/S BUS-TIE 이설공사","○ #65BUS 철거 (기존 BUS TIE GCB)","2021-03-08 09:00","2021-03-09 18:00","2021-03-08 09:00","2021-03-09 18:00","연속"]
[179,"경기북부","구리","포천S/S 포천열병합 T/L CB 677","포천SS 포천-열병합T/L DS 과열보수","포천SS 포천-열병합T/L DS 과열보수","2021-03-09 09:00","2021-03-09 18:00","취소","취소","연속"]
[180,"경기북부","구리","포천S/S 154kV #1 BUS","포천S/S BUS-TIE 이설공사","○ #60BUS, 철구 철거 ○ 기존 BUS TIE GCB 및 DS 철거","2021-03-10 09:00","2021-03-12 18:00","2021-03-10 09:00","2021-03-12 18:00","연속"]
[181,"경기북부","직할","백석덕계#1 T/L","'20~'21년 경기북부 직할 가공송전 정비회사 총액공사","154kV 피뢰기 설치공사 하단병가선로","2021-03-30 07:00","2021-03-30 18:00","2021-03-30 07:00","2021-03-30 18:00","연속"]
[182,"경기북부","직할","양주은평#1 T/L","20-21년 가공송전 정비회사 총액공사","ㅇ 압축인류크램프 교체","2021-03-15 07:00","2021-03-15 18:00","2021-03-15 07:00","2021-03-15 18:00","연속"]
[183,"경기북부","직할","양주금촌#1 T/L","20-21년 가공송전 정비회사 총액공사","ㅇ 96년도 상반기 이전 성능저하 국산애자 교체","2021-03-15 07:00","2021-03-15 18:00","2021-03-15 07:00","2021-03-15 18:00","연속"]
[184,"경기북부","직할","양주쌍문#2 T/L","'20-21 변전정비 총액공사","170kV GIS 하자점검","2021-03-24 09:00","2021-03-24 18:00","2021-03-24 09:00","2021-03-24 18:00","연속"]
[185,"경기북부","직할","양주쌍문#1 T/L","'20-21 변전정비 총액공사","170kV GIS 하자점검","2021-03-23 09:00","2021-03-23 18:00","2021-03-23 09:00","2021-03-23 18:00","연속"]
[186,"경기북부","직할","양주지축#2 T/L","20-21 변전정비 총액공사","170kV GIS 하자점검","2021-03-11 09:00","2021-03-11 18:00","2021-03-11 09:00","2021-03-11 18:00","연속"]
[187,"경기","군포","목내안산복합#1 T/L","목내S/S 목내-안산C/C #1T/L GIS 조작시험","목내S/S 목내-안산C/C #1T/L GIS 조작시험","2021-03-09 09:00","2021-03-09 18:00","2021-03-09 09:00","2021-03-09 18:00","연속"]
[188,"경기","군포","서서울#2소래 T/L","154kV 서서울-서안양-소래T/L OPGW 증설공사","* 서서울S/T ~ No.53(서안양C/H)간 OP-S-S24→48 교체 16.441km * 서안양C/H ~ 서안양ICT실간 FOFC 증설(24C) 5.430km * No.41 ~ No.45간 FOFC 교체(24→48C) 1.250km * 서서울S/S ICT실 ~ 서서울S/T FOFC 교체(24→48C) 0.640km * 접속, 최종시험 및 기타 부","2021-03-11 07:00","2021-03-23 18:00","2021-03-10 07:00","2021-03-22 18:00","연속"]
[189,"경기","군포","서서울#2서안양 T/L","154kV 서서울-서안양-소래T/L OPGW 증설공사","* 서서울S/T ~ No.53(서안양C/H)간 OP-S-S24→48 교체 16.441km * 서안양C/H ~ 서안양ICT실간 FOFC 증설(24C) 5.430km * No.41 ~ No.45간 FOFC 교체(24→48C) 1.250km * 서서울S/S ICT실 ~ 서서울S/T FOFC 교체(24→48C) 0.640km * 접속, 최종시험 및 기타 부","2021-03-24 07:00","2021-03-26 18:00","2021-03-23 07:00","2021-03-25 18:00","연속"]
[190,"경기","군포","서서울율전#2 T/L","154kV 서서울-율전T/L 5,6호 안전이격확보공사","- 철탑교체(인클로징공법) 2기 - 전선교체(4~6호) 0.542km - 기타(현수애자 및 금구류 교체)","2021-03-01 08:00","2021-03-01 18:00","2021-03-01 08:00","2021-03-01 18:00","연속"]
[191,"경기","군포","서서울율전#1 T/L","154kV 서서울-율전T/L 5,6호 안전이격확보공사","- 철탑교체(인클로징공법) 2기 - 전선교체(4~6호) 0.542km - 기타(현수애자 및 금구류 교체)","2021-03-02 08:00","2021-03-08 18:00","2021-03-02 08:00","2021-03-08 18:00","연속"]
[192,"경기","군포","서서울율전#2 T/L","154kV 서서울-율전T/L 5,6호 안전이격확보공사","- 철탑교체(인클로징공법) 2기 - 전선교체(4~6호) 0.542km - 기타(현수애자 및 금구류 교체)","2021-03-09 08:00","2021-03-13 18:00","2021-03-09 08:00","2021-03-13 18:00","연속"]
[193,"경기","군포","목내안산복합#2 T/L","조작시험 및 인출DS 구동부 내부 ILMD 교체","안산CC측 인출DS 구동부 내부 ILMD 교체/목내SS측 차단기 조작시험(병행)","2021-03-08 09:00","2021-03-08 18:00","2021-03-08 09:00","2021-03-08 18:00","연속"]
[194,"경기","동부","감곡가남#2 T/L","154kV감곡-가남T/L 불량애자 및 국산애자 교체공사","154kV감곡-가남T/L 불량애자 및 국산애자 교체공사","2021-03-16 08:00","2021-03-17 18:00","2021-03-20 08:00","2021-03-21 18:00","매일"]
[195,"경기","동부","감곡가남#1 T/L","154kV감곡-가남T/L 불량애자 및 국산애자 교체공사","154kV감곡-가남T/L 불량애자 및 국산애자 교체공사","2021-03-15 08:00","2021-03-15 18:00","2021-03-13 08:00","2021-03-13 18:00","연속"]
[196,"경기","동부","신용인동백#2 T/L","21년 동부 변전정비회사 총액공사","동백:신용인-동백#2T/L보호반대체(~5),신용인-동백#2T/L GIS(보통)","2021-03-03 09:30","2021-03-05 18:00","2021-03-03 09:30","2021-03-05 18:00","연속"]
[197,"경기","동부","신용인동백#1 T/L","21년 동부 변전정비회사 총액공사","동백:신용인-동백#1T/L GIS(보통)","2021-03-02 09:30","2021-03-02 18:00","2021-03-02 09:30","2021-03-02 18:00","연속"]
[198,"경기","동부","오포모현#1 T/L","21년 동부 변전정비회사 총액공사","모현:오포-모현#1T/L GIS(보통)","2021-03-31 09:30","2021-04-02 18:00","2021-03-31 09:30","2021-04-02 18:00","연속"]
[199,"경기","동부","모현용인#1 T/L","21년 동부 변전정비회사 총액공사","모현:모현-용인#1T/L GIS(보통)","2021-03-29 09:30","2021-03-29 14:00","2021-03-29 09:30","2021-03-29 14:00","연속"]
[200,"경기","동부","오포모현#2 T/L","21년 동부 변전정비회사 총액공사","모현:오포-모현#2T/L GIS(보통)","2021-03-30 09:30","2021-03-30 18:00","2021-03-30 09:30","2021-03-30 18:00","연속"]
[201,"경기","동부","모현용인#2 T/L","21년 동부 변전정비회사 총액공사","모현:모현-용인#2T/L GIS(보통)","2021-03-29 14:00","2021-03-29 18:00","2021-03-29 14:00","2021-03-29 18:00","연속"]
[202,"경기","동부","분당오포#2 T/L","21년 동부 변전정비회사 총액공사","분당:분당-오포#2T/L GIS(하자)","2021-03-05 09:30","2021-03-05 18:00","2021-03-05 09:30","2021-03-05 18:00","연속"]
[203,"경기","동부","분당오포#1 T/L","21년 동부 변전정비회사 총액공사","분당:분당-오포#1T/L GIS(하자)","2021-03-04 09:30","2021-03-04 18:00","2021-03-04 09:30","2021-03-04 18:00","연속"]
[204,"경기","동부","산성수서#2 T/L","21년 동부 변전정비회사 총액공사","산성-수서#2T/L GIS(보통)","2021-03-18 14:00","2021-03-18 18:00","2021-03-18 14:00","2021-03-18 18:00","연속"]
[205,"경기","동부","성현산성#1 T/L","21년 동부 변전정비회사 총액공사","산성:산성-성현#1T/L GIS(보통)","2021-03-08 09:30","2021-03-08 18:00","2021-03-08 09:30","2021-03-08 18:00","연속"]
[206,"경기","동부","성현산성#2 T/L","21년 동부 변전정비회사 총액공사","산성:산성-성현#2T/L GIS(보통)","2021-03-09 09:30","2021-03-09 18:00","2021-03-09 09:30","2021-03-09 18:00","연속"]
[207,"경기","동부","산성수서#1 T/L","21년 동부 변전정비회사 총액공사","산성:산성-수서#1T/L GIS(보통)","2021-03-18 09:30","2021-03-18 14:00","2021-03-18 09:30","2021-03-18 14:00","연속"]
[208,"경기","동부","성현분당#1 T/L","154kV야탑-성현#1T/L 정밀점검","154kV야탑-성현#1T/L 안전상 휴전","2021-03-15 09:00","2021-03-19 18:00","2021-03-15 09:00","2021-03-19 18:00","매일"]
[209,"경기","동부","성현S/S 154kV CB 6100","21년 동부 변전정비회사 총액공사","성현:#1Sh.C GIS(조작), 6100GIS(조작)","2021-03-10 14:00","2021-03-10 18:00","2021-03-10 14:00","2021-03-10 18:00","연속"]
[210,"경기","동부","성현분당#1 T/L","154kV성현-분당#1T/L 과열개소 정비","154kV성현-분당T/L 과열개소 정비","2021-03-03 09:00","2021-03-03 12:00","2021-03-03 09:00","2021-03-03 12:00","연속"]
[211,"경기","동부","성현분당#2 T/L","154kV성현-분당#2T/L 피뢰기설치","피뢰기 설치작업(1~41호)","2021-03-22 09:00","2021-03-26 18:00","2021-03-22 09:00","2021-03-26 18:00","매일"]
[212,"경기","동부","성현분당#2 T/L","154kV성현-분당#2T/L 과열개소 정비","154kV성현-분당T/L 과열개소 정비","2021-03-03 13:00","2021-03-03 17:00","2021-03-03 13:00","2021-03-03 17:00","연속"]
[213,"경기","동부","동판교야탑 T/L","21년 동부 변전정비회사 총액공사","야탑:동판교-야탑T/L (조작)","2021-03-05 09:30","2021-03-05 18:00","2021-03-05 09:30","2021-03-05 18:00","연속"]
[214,"경기","동부","중원야탑 T/L","21년 동부 변전정비회사 총액공사","야탑:6100,중원-야탑T/L(조작)","2021-03-25 14:00","2021-03-25 18:00","2021-03-25 14:00","2021-03-25 18:00","연속"]
[215,"경기","동부","오천용인#2 T/L","21년 동부 변전정비회사 총액공사","오천:용인-오천#2T/L GIS(하자)","2021-03-10 09:30","2021-03-10 18:00","2021-03-10 09:30","2021-03-10 18:00","연속"]
[216,"경기","동부","오천용인#1 T/L","21년 동부 변전정비회사 총액공사","오천:용인-오천#1T/L GIS(하자)","2021-03-09 09:30","2021-03-09 18:00","2021-03-09 09:30","2021-03-09 18:00","연속"]
[217,"경기","동부","분당오포#1 T/L","154kV성현-분당#2T/L 피뢰기 설치(안전상휴전)","154kV성현-분당#2T/L 피뢰기 설치 안전상휴전","2021-03-25 09:00","2021-03-26 18:00","2021-03-25 09:00","2021-03-26 18:00","매일"]
[218,"경기","동부","분당오포#2 T/L","154kV성현-분당#1T/L 과열개소 정비","154kV성현-분당#1T/L 안전상 휴전","2021-03-03 09:00","2021-03-03 12:00","2021-03-03 09:00","2021-03-03 12:00","연속"]
[219,"경기","동부","분당오포#1 T/L","154kV성현-분당#2T/L 과열개소 정비","154kV성현-분당#2T/L 안전상 휴전","2021-03-03 13:00","2021-03-03 17:00","2021-03-03 13:00","2021-03-03 17:00","연속"]
[220,"경기","동부","오천율현#2 T/L","21년 동부 변전정비회사 총액공사","율현:율현-오천#2T/L GIS(보통)","2021-03-12 09:30","2021-03-12 18:00","2021-03-12 09:30","2021-03-12 18:00","연속"]
[221,"경기","동부","오천율현#1 T/L","21년 동부 변전정비회사 총액공사","율현:율현-오천#1T/L GIS(보통)","2021-03-11 09:30","2021-03-11 18:00","2021-03-11 09:30","2021-03-11 18:00","연속"]
[222,"경기","동부","이천율현#1 T/L","이천S/S 초전도시험동 액화질소 탱크철거","전력연구원 탱크철거 안전이격확보","2021-03-10 10:00","2021-03-10 14:00","2021-03-14 11:00","2021-03-14 15:00","연속"]
[223,"경기","동부","이천가남#2 T/L","이천S/S 초전도시험동 액화질소 탱크철거","전력연구원 탱크철거 안전이격확보","2021-03-10 10:00","2021-03-10 14:00","2021-03-14 11:00","2021-03-14 15:00","연속"]
[224,"경기","성남","신수원북동탄#1 T/L","154kV 신수원-북동탄 등 2개소 인출변경공사","○ 154kV 신수원-북동탄#1T/L 인출변경 - 선종 : 154kV XLPE 2,000㎟ 1C(D) - 내용 : EB-G 1개소 철거 및 신설 (기설 신수원-북동탄#1에서 예비(프렉스T/L)로 인출변경)","2021-03-08 09:00","2021-04-02 18:00","2021-03-08 09:00","2021-04-02 18:00","연속"]
[225,"경기","성남","신용인S/S 154kV SEC CB 60610","21년 성남전력지사 변전정비회사 총액공사","60-61-1DS 에어누기점검, 60-61-0 조작시험","2021-03-31 09:00","2021-03-31 14:00","2021-03-31 09:00","2021-03-31 14:00","연속"]
[226,"경기","성남","신용인S/S 154kV SEC CB 65660","21년 성남전력지사 변전정비회사 총액공사","65-66-2DS 에어누기점검, 65-66SEC 조작시험","2021-03-31 14:00","2021-03-31 18:00","2021-03-31 14:00","2021-03-31 18:00","연속"]
[227,"경기","성남","신용인용인#2 T/L","21년 성남전력지사 변전정비회사 총액공사","- GIS 보통점검 - LA 보통점검 - CVT 보통점검","2021-03-12 09:00","2021-03-12 18:00","2021-03-12 09:00","2021-03-12 18:00","연속"]
[228,"경기","성남","신용인용인#1 T/L","21년 성남전력지사 변전정비회사 총액공사","- GIS 보통점검 - LA 보통점검 - CVT 보통점검","2021-03-11 09:00","2021-03-11 18:00","2021-03-11 09:00","2021-03-11 18:00","연속"]
[229,"경기","직할","의왕동안양#2 T/L","21년 경기 직할 변전정비회사 총액공사","동안양 : 의왕-동안양 #2T/L GCB 보통점검","2021-03-15 09:00","2021-03-15 18:00","2021-03-15 09:00","2021-03-15 18:00","연속"]
[230,"경기","직할","서서울#2봉담#2 T/L","21년 경기 직할 변전정비회사 총액공사","봉담 : 서서울2-봉담#2T/L GIS 하자점검","2021-03-03 09:00","2021-03-03 18:00","2021-03-03 09:00","2021-03-03 18:00","연속"]
[231,"경기","직할","서서울#2봉담#1 T/L","21년 경기 직할 변전정비회사 총액공사","봉담 : 서서울2-봉담#1T/L GIS 하자","2021-03-04 09:00","2021-03-04 18:00","2021-03-04 09:00","2021-03-04 18:00","연속"]
[232,"경기","직할","봉담남수원#1 T/L","21년 경기 직할 변전정비회사 총액공사","봉담 : 봉담-남수원#1T/L GIS 하자","2021-03-08 09:00","2021-03-08 18:00","2021-03-08 09:00","2021-03-08 18:00","연속"]
[233,"경기","직할","봉담남수원#2 T/L","21년 경기 직할 변전정비회사 총액공사","봉담 : 봉담-남수원#2T/L GIS 하자","2021-03-09 09:00","2021-03-09 18:00","2021-03-09 09:00","2021-03-09 18:00","연속"]
[234,"경기","직할","안양#2C/C 154kV CB 6100","21년 경기 직할 변전정비회사 총액공사","안양복합 : #6100BUS-TIE GIS 하자","2021-03-03 09:00","2021-03-03 18:00","2021-03-03 09:00","2021-03-03 18:00","연속"]
[235,"경기","직할","율전의왕#1 T/L","2020-2021년도 송전정비회사 총액공사","154kV 서서울-율전#2T/L 22호 점퍼지지애자 교체 관련 안전이격거리확보","2021-03-04 08:00","2021-03-04 14:00","2021-03-04 08:00","2021-03-04 14:00","연속"]
[236,"경기","직할","서수원율전#2 T/L","2020-2021년도 송전정비회사 총액공사","154kV 서서울-율전#2T/L 22호 점퍼지지애자 교체 관련 안전이격거리확보","2021-03-04 08:00","2021-03-04 14:00","2021-03-04 08:00","2021-03-04 14:00","연속"]
[237,"경기","직할","화성발안#1 T/L","화성S/S 154kV 장기사용 GIS 대체공사","화성S/S 154kV 장기사용 GIS 대체 X 14BAY","2021-03-24 09:00","2021-04-30 18:00","취소","취소","연속"]
[238,"경기","직할","화성S/S 154kV #65 BUS","화성S/S 154kV 장기사용 GIS 대체공사","화성S/S 154kV 장기사용 GIS 대체 X 14BAY","2021-03-24 09:00","2021-03-31 18:00","취소","취소","연속"]
[239,"경기","직할","화성S/S 154kV #62 Sh.C CB 6279","화성S/S 154kV 장기사용 GIS 대체공사","화성S/S 154kV 장기사용 GIS 대체 X 14BAY","2021-03-24 09:00","2021-04-30 18:00","취소","취소","연속"]
[240,"경기","직할","화성S/S 154kV CB 6100","화성S/S 154kV 장기사용 GIS 대체공사","화성S/S 154kV 장기사용 GIS 대체 X 14BAY","2021-03-24 09:00","2021-04-30 18:00","취소","취소","연속"]
[241,"경기","평택","포승만호 T/L","만호,포승S/S 154kV 만호-포승T/L GIS 보통점검","만호S/S 154kV 만호-포승T/L GIS 보통점검 / 일진제 인출DS 인터록와이어 경로변경 및 DS조작핀 확인 / 포승S/S 154kV 만호-포승T/L GIS 조작시험","2021-03-26 10:00","2021-03-26 18:00","2021-03-26 10:00","2021-03-26 18:00","연속"]
[242,"경기","평택","서운삼죽 T/L","서울-세종간 도로개설 관련 지장이설 임시휴전","154kV 서운-안성T/L 32~36호, 45~49호","2021-03-22 07:00","2021-03-31 18:00","2021-03-22 07:00","2021-03-31 18:00","연속"]
[243,"경기","평택","서운안성#2 T/L","서울-세종간 도로개설 관련 지장이설 임시휴전","154kV 서운-안성T/L 32~36호, 45~49호","2021-03-22 07:00","2021-03-31 18:00","2021-03-22 07:00","2021-03-31 18:00","연속"]
[244,"경기","평택","서운광혜원 T/L","서운S/S 154kV 서운-광혜원T/L GIS 릴리프 밸브 교체","서운S/S 154kV 서운-광혜원T/L GIS 릴리프 밸브 교체","2021-03-03 10:00","2021-03-03 14:00","2021-03-03 10:00","2021-03-03 14:00","연속"]
[245,"경기","평택","서운S/S 154kV CB 6100","서운S/S 154kV #60-#65 B/TGIS 릴리프 밸브 교체","서운S/S 154kV #60-#65 B/T GIS 릴리프 밸브 교체","2021-03-03 14:00","2021-03-03 18:00","2021-03-03 14:00","2021-03-03 18:00","연속"]
[246,"경기","평택","서운삼죽 T/L","2020~21년 직할 송전정비회사 총액공사","아킹혼설치(no.34,35,37,39,42,47,49,53), 불량애자교체(No.91)","2021-03-11 07:30","2021-03-14 18:00","2021-03-11 07:30","2021-03-14 18:00","매일"]
[247,"경기","평택","소사벌안성 T/L","154kV 소사벌-안성T/L EBA 절연유 교체작업","소사벌C/H 소사벌-안성T/L A,B,C상 절연유 교체","2021-03-11 09:00","2021-03-12 17:00","2021-03-11 09:00","2021-03-12 17:00","매일"]
[248,"경기","평택","송탄소사벌 T/L","154kV 소사벌S/S #4M.Tr 증설공사","#65BUS 무부하가압","2021-03-24 09:00","2021-03-25 09:00","2021-03-24 09:00","2021-03-25 09:00","연속"]
[249,"경기","평택","송탄안성 T/L","송탄,안성S/S 154kV 송탄-안성T/L GIS 보통점검","송탄S/S 154kV 송탄-안성T/L GIS 보통점검 및 VX 보조계전기 교체 / 안성S/S 154kV 송탄-안성T/L GIS 하자점검","2021-03-05 10:00","2021-03-05 18:00","2021-03-05 10:00","2021-03-05 18:00","연속"]
[250,"경기","평택","서운안성#1 T/L","안성S/S 154kV 서운-안성#1T/L GIS 하자점검","안성S/S 154kV 서운-안성#1T/L GIS 하자점검","2021-03-06 10:00","2021-03-06 18:00","2021-03-06 10:00","2021-03-06 18:00","연속"]
[251,"경기","평택","서운안성#2 T/L","안성S/S 154kV 서운-안성#2T/L GIS 하자점검","안성S/S 154kV 서운-안성#2T/L GIS 하자점검","2021-03-13 10:00","2021-03-13 18:00","2021-03-13 10:00","2021-03-13 18:00","연속"]
[252,"경기","평택","원정평택T/P#1 T/L","가공송전 순시점검 위탁공사","154kV 원정-평택화력T/L 운휴선로 정비공사 관련 초기점검 시행 - 작업구간 : S/T~No.7","2021-03-09 10:00","2021-03-09 13:00","2021-03-15 10:00","2021-03-15 13:00","연속"]
[253,"경기","평택","원정평택T/P#2 T/L","가공송전 순시점검 위탁공사","154kV 원정-평택화력T/L 운휴선로 정비공사 관련 초기점검 시행 - 작업구간 : S/T~No.7","2021-03-09 13:00","2021-03-09 17:00","2021-03-15 13:00","2021-03-15 17:00","연속"]
[254,"경기","평택","둔포추팔#1 T/L","추팔S/S 154kV 둔포-추팔#1T/L 송전선로 보호반 대체공사","추팔S/S 154kV 둔포-추팔#1T/L 송전선로 보호반 대체공사","2021-03-08 10:00","2021-03-10 18:00","2021-03-08 10:00","2021-03-10 18:00","연속"]
[255,"경기","평택","둔포추팔#2 T/L","추팔S/S 154kV 둔포-추팔#2T/L 송전선로 보호반 대체공사","추팔S/S 154kV 둔포-추팔#2T/L 송전선로 보호반 대체공사","2021-03-16 10:00","2021-03-18 18:00","2021-03-16 10:00","2021-03-18 18:00","연속"]
[256,"경기","평택","평택추팔#2 T/L","154kV 평택-추팔T/L No.21, 41, 41 안전이격 확보공사","임시선로 구성","2021-03-22 08:00","2021-03-31 19:00","2021-03-22 08:00","2021-03-31 19:00","연속"]
[257,"경기","평택","평택추팔#1 T/L","154kV 평택-추팔T/L No.21, 41, 41 안전이격 확보공사","임시선로 구성","2021-03-22 08:00","2021-03-31 19:00","2021-03-22 08:00","2021-03-31 19:00","연속"]
[258,"경기","평택","평택TP평택CC#1 T/L","평택C/C 154kV 평택복합#1 T/L #2DS 보수공사","평택C/C 154kV 평택복합#1 T/L #2DS 보수공사","2021-03-03 14:00","2021-03-03 18:00","2021-03-03 14:00","2021-03-03 18:00","연속"]
[259,"강원","강릉","강릉횡계#1 T/L","2020년 170kV GIS 하자점검","○ 2021년 170kV GIS 보통점검 : 강릉S/S 강릉-횡계#2T/L","2021-03-02 10:00","2021-03-02 18:00","2021-03-02 10:00","2021-03-02 18:00","연속"]
[260,"강원","강릉","강릉횡계#2 T/L","2020년 170kV GIS 하자점검","○ 2021년 170kV GIS 보통점검 : 강릉S/S 강릉-횡계#2T/L","2021-03-03 10:00","2021-03-03 18:00","2021-03-03 10:00","2021-03-03 18:00","연속"]
[261,"강원","강릉","횡계평창 T/L","방재테이프 부착 등 케이블헤드 부착공사","케이블 입상부 방재테이프 부착(PE 개소)","2021-03-24 09:00","2021-03-24 18:00","2021-03-24 09:00","2021-03-24 18:00","연속"]
[262,"강원","강릉","횡계올림픽 T/L","방재테이프 부착 등 케이블헤드 부착공사","케이블 입상부 방재테이프 부착(PE 개소)","2021-03-24 09:00","2021-03-24 18:00","2021-03-24 09:00","2021-03-24 18:00","연속"]
[263,"강원","동해","동해강릉 T/L","2020~21년도 동해전력지사 송전정비회사 총액공사","154kV 동해-강릉T/L 송전선로용 피뢰기 설치 No.53~89, 37기 111SET 설치","2021-03-02 08:00","2021-03-05 18:00","취소","취소","매일"]
[264,"강원","동해","동해T/P 154kV #2 BUS","동해화력S/Y 장기사용 170kV GIS 대체공사","- 170kV GIS 7CCT 대체 - 동해화력S/Y 변전소 SA화","2021-03-15 14:00","2021-03-15 18:00","2021-03-15 14:00","2021-03-15 18:00","연속"]
[265,"강원","동해","동해T/P 154kV #1 BUS","동해화력S/Y 장기사용 170kV GIS 대체공사","- 170kV GIS 7CCT 대체 - 동해화력S/Y 변전소 SA화","2021-03-16 10:00","2021-03-17 10:00","2021-03-16 10:00","2021-03-17 10:00","연속"]
[266,"강원","동해","이원동해TP T/L","21-22년도 지중송전설비 위탁정비공사","동해화력T/L 인출 EBA 절연유 채취 - 이원-동해TP 6상 - 삼척-동해TP 6상","2021-03-22 09:00","2021-03-23 18:00","취소","취소","연속"]
[267,"강원","동해","삼척동해TP T/L","21-22년도 지중송전설비 위탁정비공사","동해화력T/L 인출 EBA 절연유 채취 - 이원-동해TP 6상 - 삼척-동해TP 6상","2021-03-22 09:00","2021-03-23 18:00","2021-03-29 09:00","2021-03-30 18:00","연속"]
[268,"강원","동해","동해T/P 154kV #1 BUS","동해화력S/Y 장기사용 170kV GIS 대체공사","- 170kV GIS 7CCT 대체 - 동해화력S/Y 변전소 SA화","2021-03-15 10:00","2021-03-15 14:00","2021-03-15 10:00","2021-03-15 14:00","연속"]
[269,"강원","동해","동해T/P 154kV #2 BUS","동해화력S/Y 장기사용 170kV GIS 대체공사","- 170kV GIS 7CCT 대체 - 동해화력S/Y 변전소 SA화","2021-03-03 18:00","2021-03-09 18:00","2021-03-03 18:00","2021-03-09 18:00","연속"]
[270,"강원","동해","울진삼척GP#1 T/L","20~21년 태백전력지사 송전정비회사 총액공사","송전용 피뢰기 설치","2021-03-29 08:00","2021-04-02 18:00","2021-03-29 08:00","2021-04-02 18:00","연속"]
[271,"강원","동해","울진삼척GP#2 T/L","동해전력지사 2021년 170kV GIS 정밀점검","1. GIS 정밀점검 2. 가스 누기 관련 스페이서 점검","2021-03-15 09:00","2021-03-21 18:00","2021-03-15 09:00","2021-03-21 18:00","연속"]
[272,"강원","동해","삼척G/P 154kV CB 6B7 (#1S.Tr)","동해전력지사 2021년 170kV GIS 정밀점검","1. GIS 정밀점검 2. 가스 누기 관련 스페이서 점검","2021-03-08 09:00","2021-03-14 18:00","2021-03-08 09:00","2021-03-14 18:00","연속"]
[273,"강원","동해","태백삼척GP#1 T/L","동해전력지사 2021년 170kV GIS 정밀점검","1. GIS 정밀점검 2. 가스 누기 관련 스페이서 점검","2021-03-22 09:00","2021-03-28 18:00","2021-03-22 09:00","2021-03-28 18:00","연속"]
[274,"강원","동해","동해이원#2 T/L","2020~21년도 동해전력지사 송전정비회사 총액공사","154kV 동해-이원#2T/L 송전선로용 피뢰기 설치 No.6~28, 23기 69SET 설치","2021-03-08 08:00","2021-03-10 18:00","취소","취소","매일"]
[275,"강원","원주","신제천남원주#1 T/L","○ 154kV 신제천-남원주T/L 추락방지시설 설치공사","○ 154kV 신제천-남원주T/L 추락방지시설 설치공사 - 38~96호 추락방지시설 설치공사","취 소","취 소","취소","취소","매일"]
[276,"강원","원주","신제천남원주#2 T/L","2020~2021 원주전력지사 송전정비회사 총액공사","○ 154kV 신제천-남원주#2T/L No.38~96 피뢰기 설치공사 ○ 154kV 신제천-남원주 No.38~96 추락방지시설 설치공사","취 소","취 소","취소","취소","매일"]
[277,"강원","원주","홍천상남#1 T/L","2020~2021년 송전정비회사 총액공사","국산 지지애자 교체 : 홍천S/S 인출, No.1,44,46,148,상남S/S 인출","2021-03-29 08:00","2021-03-30 18:00","2021-03-29 08:00","2021-03-30 18:00","매일"]
[278,"강원","원주","홍천상남#2 T/L","2020~2021년 송전정비회사 총액공사","국산 지지애자 교체 : 홍천S/S 인출, No.1,44,46,148,상남S/S 인출","2021-03-31 08:00","2021-04-01 18:00","2021-03-31 08:00","2021-04-01 18:00","매일"]
[279,"강원","원주","원주북원주#2 T/L","방재테이프 부착 등 케이블헤드철탑 보강공사","케이블 입상부 방재테이프 부착(PE 개소)","2021-03-22 09:00","2021-03-22 18:00","2021-03-20 09:00","2021-03-20 18:00","연속"]
[280,"강원","원주","원주서원주#2 T/L","170kV GIS 인출측 정밀점검","170kV GIS 인출측 정밀점검","2021-03-02 10:00","2021-03-03 18:00","취소","취소","연속"]
[281,"강원","원주","원주북원주#1 T/L","방재테이프 부착 등 케이블헤드철탑 보강공사","케이블 입상부 방재테이프 부착(PE 개소)","2021-03-22 09:00","2021-03-22 18:00","2021-03-20 09:00","2021-03-20 18:00","연속"]
[282,"강원","원주","둔내횡성#1 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","ㅇ 170kV 장기사용 GIS 철거/설치 ㅇ SA 운영장치 시험","2021-03-23 08:00","2021-04-03 18:00","취소","취소","연속"]
[283,"강원","원주","북원주횡성#2 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","ㅇ 170kV 장기사용 GIS 철거/설치 ㅇ 디지털화공사 케이블 철거 및 광케이블 포설 ㅇ SA 운영장치 시험","2021-03-23 08:00","2021-04-04 18:00","취소","취소","연속"]
[284,"강원","원주","북원주횡성#1 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","ㅇ 북원주-횡성#2T/L 월부싱 철거 안전이격확보","2021-03-24 08:00","2021-03-25 18:00","취소","취소","연속"]
[285,"강원","원주","북원주횡성#1 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","ㅇ 170kV 장기사용 GIS 철거/설치 ㅇ 디지털화공사 케이블 철거 및 광케이블 포설 ㅇ SA 운영장치 시험","2021-03-02 08:00","2021-03-19 18:00","취소","취소","연속"]
[286,"강원","원주","북원주횡성#2 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","ㅇ 북원주-횡성#1T/L 월부싱철거/설치 안전이격 확보","2021-03-15 08:00","2021-03-16 18:00","취소","취소","연속"]
[287,"강원","원주","북원주횡성#2 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","ㅇ 북원주-횡성#1T/L 월부싱철거/설치 안전이격 확보","2021-03-03 08:00","2021-03-04 18:00","취소","취소","연속"]
[288,"강원","직할","남춘천춘천열병합#2 T/L","2020~2021년 강원직할 송전정비회사 총액공사(피뢰기 설치)","송전선로용 피뢰기 설치(16기)","취 소","취 소","취소","취소","연속"]
[289,"강원","직할","북춘천춘천HP T/L","2020~2021년 강원직할 송전정비회사 총액공사(피뢰기 설치)","송전선로용 피뢰기 설치(1기)","취 소","취 소","취소","취소","연속"]
[290,"강원","직할","철원화천#2 T/L","2020~2021년 강원직할 송전정비회사 총액공사(피뢰기 설치)","송전선로용 피뢰기 설치(6기)","취 소","취 소","취소","취소","연속"]
[291,"강원","직할","춘천소양강HP T/L","2020~2021년 강원직할 송전정비회사 총액공사(피뢰기 설치)","송전선로용 피뢰기 설치(23기)","취 소","취 소","취소","취소","연속"]
[292,"강원","직할","양구화천HP#2 T/L","화천HP 보호배전반 이설공사","양구화천HP #2T/L 임시운전반 > DCS 제어감시경보포인트 이설","2021-03-04 09:00","2021-03-05 18:00","2021-03-04 09:00","2021-03-05 18:00","연속"]
[293,"강원","직할","북춘천화천HP T/L","화천HP 보호배전반 이설공사","북춘천-화천HP T/L 임시운전반&gtDCS 제어감시경보 케이블 이설","2021-03-08 09:00","2021-03-09 18:00","2021-03-08 09:00","2021-03-09 18:00","연속"]
[294,"강원","직할","화천화천HP#1 T/L","화천HP 보호배전반 이설공사","화천화천HP #1T/L 보호배전반 이설","2021-03-22 09:00","2021-03-24 18:00","2021-03-22 09:00","2021-03-24 18:00","연속"]
[295,"강원","직할","화천H/P 154kV CB 6133","2020-2021 강원본부 직할 변전정비 총액공사","154kV 공압식 차단기 전자변 교체(화천HP #1M.Tr 2차)","2021-03-10 09:00","2021-03-10 18:00","2021-03-10 09:00","2021-03-10 18:00","연속"]
[296,"강원","직할","가평화천HP T/L","화천HP 보호배전반 이설공사","가평-화천HP T/L 임시운전반&gtDCS 제어감시경보 케이블 이설","2021-03-10 09:00","2021-03-11 18:00","2021-03-10 09:00","2021-03-11 18:00","연속"]
[297,"강원","직할","화천화천HP#2 T/L","화천HP 보호배전반 이설공사","화천화천HP #2T/L 보호배전반 이설","2021-03-25 09:00","2021-03-27 18:00","2021-03-25 09:00","2021-03-27 18:00","연속"]
[298,"강원","직할","양구화천HP#1 T/L","화천HP 보호배전반 이설공사","양구화천HP #1T/L 임시운전반 > DCS 제어감시경보포인트 이설","2021-03-02 09:00","2021-03-03 18:00","2021-03-02 09:00","2021-03-03 18:00","연속"]
[299,"강원","태백","동영월영월CC T/L","21-22년도 지중송전설비 위탁정비공사","영월화력T/L 인출 EBA 절연유 채취 - 정선-영월CC 3상 - 동영월-영월CC 3상","2021-03-25 09:00","2021-03-25 18:00","2021-03-25 09:00","2021-03-25 18:00","연속"]
[300,"강원","태백","정선영월CC T/L","21-22년도 지중송전설비 위탁정비공사","영월화력T/L 인출 EBA 절연유 채취 - 정선-영월CC 3상 - 동영월-영월CC 3상","2021-03-24 09:00","2021-03-24 18:00","2021-03-24 09:00","2021-03-24 18:00","연속"]
[301,"강원","태백","이원태백 T/L","154kV 태원T/L 와이어형 추락방지시설 설치 공사","와이어형 추락방지시설 설치","취 소","취 소","취소","취소","연속"]
[302,"강원","태백","태백삼척GP#1 T/L","20~21년 태백전력지사 송전정비회사 총액공사","송전용 피뢰기 설치","취 소","취 소","취소","취소","연속"]
[303,"충북","직할","태백삼척GP#1 T/L","20~21년 태백전력지사 송전정비회사 총액공사","송전용 피뢰기 설치","2021-03-15 08:00","2021-03-26 18:00","2021-03-15 08:00","2021-03-26 18:00","연속"]
[304,"충북","직할","진천광혜원#2 T/L","2020~21년 직할 송전정비회사 총액공사","불량애자교체(no.11,45,50)","2021-03-13 07:30","2021-03-14 18:00","2021-03-13 07:30","2021-03-14 18:00","매일"]
[305,"충북","직할","서운광혜원 T/L","2020~21년 직할 송전정비회사 총액공사","점퍼소켓교체(no.95), 불량애자교체(No.30,57)","2021-03-08 07:30","2021-03-10 18:00","취소","취소","매일"]
[306,"충북","직할","진천광혜원#1 T/L","2020~21년 직할 송전정비회사 총액공사","154kV 서운-광혜원T/L 휴전에따른 안전이격조치","2021-03-08 07:30","2021-03-08 18:00","취소","취소","연속"]
[307,"충북","직할","사리괴산 T/L","2020-2021년 청주전력지사 송전정비회사 총액공사","- 전력선 교체 : No.69~73 - 추락방지시설 설치 : No.69~73","2021-03-25 07:00","2021-03-26 18:00","취소","취소","연속"]
[308,"충북","청주","음성사리 T/L","2020-2021년 청주전력지사 송전정비회사 총액공사","- 전력선 교체 : No.69~73 - 추락방지시설 설치 : No.69~73","2021-03-22 07:00","2021-03-24 18:00","취소","취소","연속"]
[309,"충북","청주","남청주청주#3 T/L","154kV 신옥천-옥천 등 5개 T/L 송전피뢰기 설치공사","154kV 신옥천-옥천 등 5개 T/L 801set 송전피뢰기 설치공사 - 휴전일자 : 2021.3.2~3.5 / 3.9~3.12 / 3.16~3.17","2021-03-09 08:00","2021-03-12 18:00","취소","취소","매일"]
[310,"충북","청주","남청주죽림#1 T/L","2020-2021년 청주전력지사 송전정비회사 총액공사","- 전력선 교체 : No.5~10, No.14~15 - 추락방지시설 설치 : No.5~10, No.14~15","2021-03-27 07:00","2021-03-28 18:00","취소","취소","연속"]
[311,"충북","청주","남청주청주#2 T/L","154kV 신옥천-옥천 등 5개 T/L 송전피뢰기 설치공사","154kV 신옥천-옥천 등 5개 T/L 801set 송전피뢰기 설치공사","2021-03-26 08:00","2021-03-26 18:00","취소","취소","매일"]
[312,"충북","청주","남청주오송#1 T/L","154kV 신옥천-옥천 등 5개 T/L 송전피뢰기 설치공사","154kV 신옥천-옥천 등 5개 T/L 801set 송전피뢰기 설치공사","2021-03-21 08:00","2021-03-21 18:00","취소","취소","매일"]
[313,"충북","청주","남청주청주#3 T/L","154kV 신옥천-옥천 등 5개 T/L 송전피뢰기 설치공사","154kV 신옥천-옥천 등 5개 T/L 801set 송전피뢰기 설치공사 - 휴전일자 : 2021.3.2~3.5 / 3.9~3.12 / 3.16~3.17","2021-03-16 08:00","2021-03-17 18:00","취소","취소","매일"]
[314,"충북","청주","남청주청주#1 T/L","154kV 신옥천-옥천 등 5개 T/L 송전피뢰기 설치공사","154kV 신옥천-옥천 등 5개 T/L 801set 송전피뢰기 설치공사 - 휴전일자 : 2021.3.2~3.5 / 3.9~3.12 / 3.16~3.17","2021-03-16 08:00","2021-03-17 18:00","취소","취소","매일"]
[315,"충북","청주","남청주오송#1 T/L","154kV 신옥천-옥천 등 5개 T/L 송전피뢰기 설치공사","154kV 신옥천-옥천 등 5개 T/L 801set 송전피뢰기 설치공사","2021-03-13 08:00","2021-03-14 18:00","취소","취소","매일"]
[316,"충북","청주","남청주청주#1 T/L","154kV 신옥천-옥천 등 5개 T/L 송전피뢰기 설치공사","154kV 신옥천-옥천 등 5개 T/L 801set 송전피뢰기 설치공사 - 휴전일자 : 2021.3.2~3.5 / 3.9~3.12 / 3.16~3.17","2021-03-09 08:00","2021-03-12 18:00","취소","취소","매일"]
[317,"충북","청주","남청주오송#1 T/L","154kV 신옥천-옥천 등 5개 T/L 송전피뢰기 설치공사","154kV 신옥천-옥천 등 5개 T/L 801set 송전피뢰기 설치공사","2021-03-06 08:00","2021-03-07 18:00","취소","취소","매일"]
[318,"충북","청주","남청주청주#3 T/L","154kV 신옥천-옥천 등 5개 T/L 송전피뢰기 설치공사","154kV 신옥천-옥천 등 5개 T/L 801set 송전피뢰기 설치공사 - 휴전일자 : 2021.3.2~3.5 / 3.9~3.12 / 3.16~3.17","2021-03-02 08:00","2021-03-05 18:00","취소","취소","매일"]
[319,"충북","청주","남청주청주#1 T/L","154kV 신옥천-옥천 등 5개 T/L 송전피뢰기 설치공사","154kV 신옥천-옥천 등 5개 T/L 801set 송전피뢰기 설치공사 - 휴전일자 : 2021.3.2~3.5 / 3.9~3.12 / 3.16~3.17","2021-03-02 08:00","2021-03-05 18:00","취소","취소","매일"]
[320,"충북","청주","상주보은 T/L","154kV 상주T/L No.93-1 안전이격 확보공사","154kV 상주T/L No.93-1 기설설탑 철거 및 신설철탑 건설 지상고 부족에 따른 안전이격 확보공사 시행(F2-17m -> Ba2-28m)","2021-03-10 07:00","2021-03-11 18:00","취소","취소","매일"]
[321,"충북","청주","상주보은 T/L","154kV 상주T/L No.93-1 안전이격 확보공사","154kV 상주T/L No.93-1 기설설탑 철거 및 신설철탑 건설 지상고 부족에 따른 안전이격 확보공사 시행(F2-17m -> Ba2-28m)","2021-03-06 07:00","2021-03-06 18:00","취소","취소","연속"]
[322,"충북","청주","신옥천S/S 154kV CB 6200","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 154kV #2BUSTIE GIS 초기점검","2021-03-09 09:30","2021-03-09 18:00","취소","취소","연속"]
[323,"충북","청주","신옥천S/S 154kV CB 6100","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 154kV #1BUSTIE GIS 초기점검","2021-03-08 09:30","2021-03-08 18:00","취소","취소","연속"]
[324,"충북","청주","신옥천남대전#4 T/L","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 154kV 신옥천-남대전#4T/L GIS 초기점검","2021-03-05 09:30","2021-03-05 18:00","취소","취소","연속"]
[325,"충북","청주","신옥천남대전#3 T/L","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 154kV 신옥천-남대전#3T/L GIS 초기점검","2021-03-04 09:30","2021-03-04 18:00","취소","취소","연속"]
[326,"충북","청주","신옥천S/S 154kV CB 6300","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 154kV #3BUSTIE GIS 초기점검","2021-03-10 09:30","2021-03-10 18:00","취소","취소","연속"]
[327,"충북","청주","신옥천남대전#1 T/L","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 154kV 신옥천-남대전#1T/L GIS 초기점검","2021-03-02 09:30","2021-03-02 18:00","취소","취소","연속"]
[328,"충북","청주","신옥천남대전#2 T/L","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 154kV 신옥천-남대전#2T/L GIS 초기점검","2021-03-03 09:30","2021-03-03 18:00","취소","취소","연속"]
[329,"충북","청주","신옥천S/S 154kV SEC CB 60610","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 154kV #60-61BUSSEC GIS 초기점검","2021-03-11 09:30","2021-03-11 18:00","취소","취소","연속"]
[330,"충북","청주","신옥천S/S 154kV SEC CB 61620","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 154kV #61-62BUSSEC GIS 초기점검","2021-03-12 09:30","2021-03-12 18:00","취소","취소","연속"]
[331,"충북","청주","신옥천S/S 154kV SEC CB 65660","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 154kV #65-66BUSSEC GIS 초기점검","2021-03-15 09:30","2021-03-15 18:00","취소","취소","연속"]
[332,"충북","청주","신옥천S/S 154kV SEC CB 66670","20-21년 청주전력 변전정비회사 총액공사","신옥천S/S 154kV 66-67BUSSEC GIS 초기점검","2021-03-25 09:30","2021-03-25 18:00","취소","취소","연속"]
[333,"충북","청주","상주영동 T/L","154kV 상주T/L No.93-1 안전이격 확보공사","154kV 상주T/L No.93-1 기설설탑 철거 및 신설철탑 건설 지상고 부족에 따른 안전이격 확보공사 시행(F2-17m -> Ba2-28m)","2021-03-07 07:00","2021-03-09 18:00","취소","취소","매일"]
[334,"충북","청주","오송북청주#2 T/L","154kV 신옥천-옥천 등 5개 T/L 송전피뢰기 설치공사","154kV 신옥천-옥천 등 5개 T/L 801set 송전피뢰기 설치공사","2021-03-06 08:00","2021-03-07 18:00","2021-03-06 08:00","2021-03-07 18:00","연속"]
[335,"충북","청주","옥천영동 T/L","154kV 상주T/L 정밀점검","2020 가공송전 순시점검 위탁공사 154kV 상주T/L No.1~110 정밀점검","2021-03-16 08:30","2021-03-19 18:00","취소","취소","매일"]
[336,"충북","청주","옥천보은 T/L","154kV 상주T/L 정밀점검","2020 가공송전 순시점검 위탁공사 154kV 상주T/L No.1~110 정밀점검","2021-03-12 08:30","2021-03-15 18:00","취소","취소","매일"]
[337,"충북","충주","사리초정#1 T/L","2020-2021년 청주전력지사 송전정비회사 총액공사","- 전력선 교체 : No.32~34, No.39~40 - 가공지선 교체 : No.34~36 - 추락방지시설 설치 : No.32~34, No.34~36 No.39~40","2021-03-29 07:00","2021-04-01 12:00","취소","취소","연속"]
[338,"충북","충주","금왕남음성#2 T/L","20-21년 충주전력지사 변전정비 총액공사","남음성S/S 금왕-남음성#2T/L 개폐타임 측정 금왕S/S 금왕-남음성#2T/L LA 점검","2021-03-24 10:00","2021-03-24 18:00","취소","취소","연속"]
[339,"충북","충주","금왕남음성#1 T/L","20-21년 충주전력지사 변전정비 총액공사","남음성S/S 금왕-남음성#1T/L CB 개폐타임 측정 남음성S/S 금왕-남음성#1T/L #2 BUS DS 조작부 래치 교체","2021-03-15 10:00","2021-03-15 18:00","2021-03-15 10:00","2021-03-15 18:00","연속"]
[340,"충북","충주","왕암북충주 T/L","2020-2021년 송전정비회사 총액공사","전력선 교체 (No.9-18)","2021-03-15 07:00","2021-03-21 18:00","취소","취소","연속"]
[341,"충북","충주","왕암충주 T/L","2020-2021년 송전정비회사 총액공사","전력선 교체 (No.9-18)","2021-03-22 07:00","2021-03-28 18:00","취소","취소","연속"]
[342,"충북","충주","음성금왕#2 T/L","20-21년 충주전력지사 변전정비 총액공사","음성S/S 음성-금왕#2T/L LA점검 및 개폐타임 측정 금왕S/S 음성-금왕#2T/L 개폐타임 측정","2021-03-16 14:00","2021-03-16 18:00","취소","취소","연속"]
[343,"충북","충주","음성금왕#1 T/L","20-21년 충주전력지사 변전정비 총액공사","음성S/S 음성-금왕#1T/L LA점검 및 개폐타임 측정 금왕S/S 음성-금왕#1T/L 개폐타임 측정","2021-03-16 10:00","2021-03-16 14:00","취소","취소","연속"]
[344,"충북","충주","풍동음성#1 T/L","2020~21년 직할 송전정비회사 총액공사","아킹혼설치(6기),불량애자교체(5기),항공장애표시등철거(7기)","2021-03-03 10:00","2021-03-03 16:00","2021-03-03 10:00","2021-03-03 16:00","연속"]
[345,"충북","충주","풍동음성#2 T/L","2020~21년 직할 송전정비회사 총액공사","불량애자교체(No.22,46,72,78)","2021-03-22 10:00","2021-03-22 16:00","취소","취소","연속"]
[346,"대전충남","대전","신옥천남대전#4 T/L","남대전S/S 154kV 신옥천-남대전#4T/L GIS 보통점검","남대전S/S 154kV 신옥천-남대전#4T/L GIS 보통점검","2021-03-02 10:00","2021-03-02 18:00","취소","취소","연속"]
[347,"대전충남","대전","팔봉두마#1 T/L","두마S/S 170kV GIS DS부 전수조사","두마S/S 170kV GIS DS부 전수조사 - 617, 6133 GIS","2021-03-16 09:00","2021-03-18 18:00","취소","취소","연속"]
[348,"대전충남","대전","팔봉두마#2 T/L","두마S/S 170kV GIS DS부 전수조사","두마S/S 170kV GIS DS부 전수조사 - 627, 6233 GIS","2021-03-23 09:00","2021-03-25 18:00","취소","취소","연속"]
[349,"대전충남","대전","신계룡두마#1 T/L","154kV 신계룡-두마T/L OPGW 증설공사","신계룡S/S ~ 두마S/S 간 가공지선(ACSR 97SQ)를 OPGW/100SQ로 변경","2021-03-09 08:00","2021-03-11 18:00","취소","취소","매일"]
[350,"대전충남","대전","신계룡두마#2 T/L","154kV 신계룡-두마T/L OPGW 증설공사","신계룡S/S ~ 두마S/S 간 가공지선(ACSR 97SQ)를 OPGW/100SQ로 변경","2021-03-09 08:00","2021-03-11 18:00","취소","취소","매일"]
[351,"대전충남","서산","서산태안 T/L","154kV 서산-태안T/L 불량개소 정비","154kV 서산-태안T/L 불량개소 정비: No.58","2021-03-05 08:00","2021-03-05 12:00","2021-03-05 08:00","2021-03-05 12:00","연속"]
[352,"대전충남","서산","대산석문#2 T/L","154kV 일진제 GIS 인출 DS 개선공사","154kV 대산-석문#2T/L 인출 DS 개선 (병행)154kV 대산-석문#2T/L 수동조작장치 구조 개선","2021-03-24 09:00","2021-03-26 18:00","2021-03-24 09:00","2021-03-26 18:00","연속"]
[353,"대전충남","서산","대산석문#1 T/L","154kV 대산-석문#1T/L 불량개소 정비","154kV 대산-석문#1T/L 불량개소 정비 : No.23, 34","2021-03-10 09:00","2021-03-10 13:00","취소","취소","연속"]
[354,"대전충남","서산","대산성연 T/L","21년 서산P/O 170kV GIS 정밀점검","성연S/S 154kV 대산-성연T/L GIS(617) 정밀점검","2021-03-15 10:00","2021-03-17 14:00","취소","취소","연속"]
[355,"대전충남","서산","당진송악#2 T/L","154kV 합덕-송악T/L 피뢰기 설치공사","154kV 합덕-송악T/L 피뢰기 설치 - No.60~97(38기) - 4회선 병가철탑 안전이격확보","2021-03-22 08:00","2021-03-26 18:00","2021-03-22 08:00","2021-03-26 18:00","매일"]
[356,"대전충남","서산","신당진당진#1 T/L","154kV 신당진-당진#1T/L 송전선로 정밀점검","154kV 신당진-당진#1T/L 송전선로 정밀점검 : No.1~44 (병행)154kV 합덕-송악#1T/L 피뢰기 설치공사 4회선 안전이격 확보 : No.52~59","2021-03-18 08:00","2021-03-20 18:00","2021-03-18 08:00","2021-03-20 18:00","매일"]
[357,"대전충남","서산","신당진서산#1 T/L","154kV 신당진-서산#1T/L 불량개소 정비","154kV신당진-서산#1T/L 불량개소 정비: No.33","2021-03-10 13:00","2021-03-10 17:00","취소","취소","연속"]
[358,"대전충남","서산","태안태안화력 T/L","154kV 태안-태안화력T/L 피뢰기 설치공사","154kV 태안-태안화력T/L 피뢰기 설치공사 -No. 1~51(51기) (병행)태안화력S/S 154kV GIS(627) 정밀점검 (3.8~3.10)","2021-03-08 10:00","2021-03-12 18:00","2021-03-08 10:00","2021-03-12 18:00","매일"]
[359,"대전충남","서산","합덕송악#2 T/L","21년 서산P/O 변전정비 총액공사","합덕S/S 154kV 합덕-송악#2T/L GIS 하자점검","2021-03-11 10:00","2021-03-11 18:00","2021-03-11 10:00","2021-03-11 18:00","연속"]
[360,"대전충남","서산","아산합덕#2 T/L","21년 서산P/O 변전정비 총액공사","합덕S/S 154kV 아산-합덕#2T/L GIS 하자점검","2021-03-09 10:00","2021-03-09 18:00","2021-03-09 10:00","2021-03-09 18:00","연속"]
[361,"대전충남","서산","아산합덕#1 T/L","21년 서산P/O 변전정비 총액공사","합덕S/S 154kV 아산-합덕#1T/L GIS 하자점검","2021-03-08 10:00","2021-03-08 18:00","2021-03-08 10:00","2021-03-08 18:00","연속"]
[362,"대전충남","서산","합덕송악#1 T/L","154kV 합덕-송악T/L 피뢰기 설치공사","154kV 합덕-송악T/L 피뢰기 설치 - No.1~98(98기)","2021-03-15 08:00","2021-03-31 18:00","2021-03-15 08:00","2021-03-31 18:00","매일"]
[363,"대전충남","서산","해미홍성 T/L","21년 서산P/O 170kV GIS 정밀점검","해미S/S 154kV 해미-홍성T/L GIS(637) 정밀점검","2021-03-29 10:00","2021-03-31 18:00","취소","취소","연속"]
[364,"대전충남","세종","부강월산#1 T/L","[송전]154kV 부강-월산T/L 정밀점검","[송전]154kV 부강-월산T/L No.1~43 정밀점검","2021-03-08 08:00","2021-03-12 18:00","취소","취소","매일"]
[365,"대전충남","세종","부강월산#2 T/L","[송전]154kV 부강-월산T/L 정밀점검","[송전]154kV 부강-월산T/L No.1~43 정밀점검","2021-03-15 08:00","2021-03-19 18:00","취소","취소","매일"]
[366,"대전충남","세종","세종서세종#2 T/L","[변전]세종PO변전정비총액공사","170KV GIS 보통점검공사","2021-03-31 09:00","2021-03-31 18:00","2021-03-31 09:00","2021-03-31 18:00","연속"]
[367,"대전충남","세종","세종서세종#1 T/L","[변전]세종PO변전정비총액공사","170KV GIS 보통점검공사","2021-03-12 09:00","2021-03-12 18:00","2021-03-12 09:00","2021-03-12 18:00","연속"]
[368,"대전충남","세종","세종둔곡#1 T/L","[변전]세종PO변전정비총액공사","170KV GIS 보통점검공사","2021-03-26 09:00","2021-03-26 12:00","취소","취소","연속"]
[369,"대전충남","세종","세종둔곡#2 T/L","[변전]세종PO변전정비총액공사","170KV GIS 보통점검공사","2021-03-26 12:00","2021-03-26 18:00","취소","취소","연속"]
[370,"대전충남","세종","천안전의#2 T/L","154kV 북오송S/S 및 분기T/L 건설공사","○ 154kV 북오송S/S 최초가압 ○ 154kV 북오송-전의#1T/L 최초가압","2021-03-09 10:00","2021-03-10 18:00","2021-03-09 10:00","2021-03-10 18:00","연속"]
[371,"대전충남","세종","천안전의#2 T/L","154kV 북오송S/S 및 분기T/L 건설공사","○ 154kV 북오송S/S 최초가압 ○ 154kV 북오송-전의#2T/L 최초가압","2021-03-17 10:00","2021-03-18 18:00","2021-03-17 10:00","2021-03-18 18:00","연속"]
[372,"대전충남","세종","조치원전의#2 T/L","[변전]세종PO변전정비총액공사","170kV GIS 보통점검 및 기타설비 점검","2021-03-30 09:00","2021-03-30 18:00","취소","취소","연속"]
[373,"대전충남","세종","조치원전의#1 T/L","[변전]세종PO변전정비총액공사","170kV GIS 보통점검 및 기타설비 점검","2021-03-29 09:00","2021-03-29 18:00","취소","취소","연속"]
[374,"대전충남","아산","한샘둔포#1 T/L","154kV 직산분기T/L 건설공사","ㅇ 공사구간 : 한샘-둔포 15,17호 ~ 직산분기 1호 ㅇ 공사내용 : 직결선로 원복","2021-03-02 09:00","2021-03-03 18:00","2021-03-02 09:00","2021-03-03 18:00","연속"]
[375,"대전충남","아산","한샘둔포#2 T/L","154kV 직산분기T/L 건설공사","ㅇ 공사구간 : 한샘-둔포 15,17호 ~ 직산분기 1호 ㅇ 공사내용 : 직결선로 원복","2021-03-04 09:00","2021-03-05 18:00","2021-03-04 09:00","2021-03-05 18:00","연속"]
[376,"대전충남","아산","천안전의#1 T/L","천안변전소 구내 C/H철탑 친환경 도장공사","-천안C/H, 성거C/H 친환경 도장공사","2021-03-26 08:00","2021-03-26 18:00","2021-03-26 08:00","2021-03-26 18:00","매일"]
[377,"대전충남","아산","천안전의#1 T/L","천안변전소 구내 C/H철탑 친환경 도장공사","-천안C/H, 성거C/H 친환경 도장공사","2021-03-22 08:00","2021-03-23 18:00","2021-03-22 08:00","2021-03-23 18:00","매일"]
[378,"대전충남","아산","천안전의#2 T/L","천안변전소 구내 C/H철탑 친환경 도장공사","-천안C/H, 성거C/H 친환경 도장공사","2021-03-24 08:00","2021-03-25 18:00","2021-03-24 08:00","2021-03-25 18:00","매일"]
[379,"대전충남","아산","천안전의#2 T/L","천안변전소 구내 C/H철탑 친환경 도장공사","-천안C/H, 성거C/H 친환경 도장공사","2021-03-27 08:00","2021-03-27 18:00","2021-03-27 08:00","2021-03-27 18:00","매일"]
[380,"대전충남","아산","서천안탕정#2 T/L","154kV 인주-불당T/L C/H 건설공사","임시선로 → 본선로 가선 시행","2021-03-09 09:00","2021-03-17 18:00","2021-03-29 09:00","2021-04-06 18:00","연속"]
[381,"대전충남","아산","인주탕정#2 T/L","154kV 인주-불당T/L C/H 건설공사","임시선로 → 본선로 가선 시행","2021-03-18 09:00","2021-03-26 18:00","취소","취소","연속"]
[382,"대전충남","아산","인주탕정#1 T/L","154kV 인주-불당T/L C/H 건설공사","임시선로 → 본선로 가선 시행","2021-03-09 09:00","2021-03-17 18:00","2021-03-29 09:00","2021-04-06 18:00","연속"]
[383,"대전충남","아산","서천안탕정#1 T/L","154kV 인주-불당T/L C/H 건설공사","임시선로 → 본선로 가선 시행","2021-03-18 09:00","2021-03-26 18:00","취소","취소","연속"]
[384,"대전충남","직할","대덕둔지 T/L","일진제 154kV GIS 수동조작장치 구조개선","일진제 154kV GIS 수동조작장치 구조개선","2021-03-09 09:00","2021-03-09 18:00","2021-03-09 09:00","2021-03-09 18:00","연속"]
[385,"대전충남","직할","동대전신탄진#2 T/L","신탄진S/S 154kV 취약설비GIS화 공사","전력구 설치공사 관련 안전이격 사전작업 - 인출단로기 철거 및 P.T, LA 이설작업","2021-03-18 09:00","2021-03-20 18:00","취소","취소","연속"]
[386,"대전충남","직할","동대전신탄진#1 T/L","신탄진S/S 154kV 취약설비GIS화 공사","전력구 설치공사 관련 안전이격 사전작업 - 인출단로기 철거 및 P.T, LA 이설작업","2021-03-22 09:00","2021-03-24 18:00","취소","취소","연속"]
[387,"대전충남","직할","부강신탄진 T/L","신탄진S/S 154kV 취약설비GIS화 공사","전력구 설치공사 관련 안전이격 사전작업 - 인출단로기 철거 및 P.T, LA 이설작업","2021-03-15 09:00","2021-03-17 18:00","취소","취소","연속"]
[388,"대전충남","직할","신탄진대청HP T/L","신탄진S/S 154kV 취약설비GIS화 공사","전력구 설치공사 관련 안전이격 사전작업 - 인출단로기 철거 및 P.T, LA 이설작업","2021-03-25 09:00","2021-03-27 18:00","취소","취소","연속"]
[389,"대전충남","청양","관창보령CC T/L","[송전]345kV 청양-신온양 등 5개T/L 송전선로용 피뢰기 설치공사","154kV관창-보령복합T/L 송전선로용 피뢰기 설치공사 - No.1~37, 보령복합 No.1,2 (39기)","2021-03-16 07:00","2021-03-19 18:00","2021-03-16 07:00","2021-03-19 18:00","매일"]
[390,"대전충남","청양","옥산장항#2 T/L","154kV 동군산-장항T/L 피뢰기 설치공사","4회선구간 송전용 피뢰기 설치( No.18~38호간)를 위한 안전이격거리 확보","2021-03-15 07:00","2021-03-16 18:00","2021-03-15 07:00","2021-03-16 18:00","매일"]
[391,"대전충남","청양","청양신풍#2 T/L","[송전]154kV 청양-신풍#2T/L 피뢰기설치공사","154kV 청양-신풍#2T/L No.49~63 피뢰기 설치공사 시행","2021-03-10 08:00","2021-03-12 18:00","2021-03-10 08:00","2021-03-12 18:00","매일"]
[392,"대전충남","청양","옥산장항#2 T/L","154kV 동군산-장항T/L 피뢰기 설치공사","4회선구간 송전용 피뢰기 설치( No.18~38호간)를 위한 안전이격거리 확보 ","2021-03-15 07:00","2021-03-16 07:00","취소","취소","매일"]
[393,"전북","군산","군공군산CC#2 T/L","지중송전 위탁정비공사 OF선로 절연유 채유","지중송전선로 OF접속함 절연유 채유","2021-03-17 09:00","2021-03-18 18:00","2021-03-17 09:00","2021-03-18 18:00","연속"]
[394,"전북","군산","군공소룡#1 T/L","군산P/O 154kV 이상 차단기 보통점검","소룡S/S 657 CB 보통점검","2021-03-22 10:00","2021-03-22 18:00","취소","취소","연속"]
[395,"전북","군산","한국유리 T/L CB","군산P/O 노후배전반 대체공사","- 노후배전반 1면 교체","취소","취소","취소","취소","연속"]
[396,"전북","군산","군공군산CC#1 T/L","지중송전 위탁정비공사 OF선로 절연유 채유","지중송전선로 OF접속함 절연유 채유","2021-03-15 09:00","2021-03-16 18:00","2021-03-15 09:00","2021-03-16 18:00","연속"]
[397,"전북","군산","군공소룡#2 T/L","군산P/O 154kV 이상 차단기 보통점검","군공S/S 687, 소룡S/S 647 CB 보통점검","2021-03-23 10:00","2021-03-23 18:00","취소","취소","연속"]
[398,"전북","군산","군공내초#1 T/L","지중송전 위탁정비공사 OF선로 절연유 채유","지중송전선로 OF접속함 절연유 채유","2021-03-20 09:00","2021-03-20 18:00","취소","취소","연속"]
[399,"전북","군산","군공내초#2 T/L","지중송전 위탁정비공사 OF선로 절연유 채유","지중송전선로 OF접속함 절연유 채유","2021-03-21 09:00","2021-03-21 18:00","취소","취소","연속"]
[400,"전북","군산","군산S/S 154kV SEC CB 66670","군산P/O 154kV 이상 차단기 보통점검","군산S/S 66-67-0 CB 보통점검","취소","취소","취소","취소","연속"]
[401,"전북","군산","군산S/S 154kV SEC CB 61620","군산P/O 154kV 이상 차단기 보통점검","군산S/S 61-62-0 CB 보통점검","취소","취소","취소","취소","연속"]
[402,"전북","군산","내초군장#2 T/L","군산P/O 154kV 이상 차단기 보통점검","군장S/S 637, 내초S/S 667 CB 보통점검","2021-03-11 10:00","2021-03-11 18:00","2021-03-11 10:00","2021-03-11 18:00","연속"]
[403,"전북","군산","내초군장#1 T/L","군산P/O 154kV 이상 차단기 보통점검","군장S/S 627, 내초S/S 657 CB 보통점검","2021-03-10 10:00","2021-03-10 18:00","2021-03-10 10:00","2021-03-10 18:00","연속"]
[404,"전북","군산","동군산장항#1 T/L","154kV 동군산-장항 #1T/L 피뢰기설치공사","피뢰기 설치공사 No.18~38호간","2021-03-15 07:00","2021-03-16 18:00","취소","취소","매일"]
[405,"전북","군산","새만금소룡#2 T/L","154kV 새만금-소룡T/L 리콜 접속함 교체공사","리콜(하자) R타입 PMJ 접속함 23상 교체공사","2021-03-22 09:00","2021-04-04 18:00","2021-03-22 09:00","2021-04-04 18:00","연속"]
[406,"전북","군산","새만금S/S 154kV SEC CB 61620","군산P/O 차단기 조작시험 점검공사","군산P/O 차단기 조작시험 점검공사","취소","취소","취소","취소","연속"]
[407,"전북","군산","새만금S/S 154kV SEC CB 66670","군산P/O 차단기 조작시험 점검공사","군산P/O 차단기 조작시험 점검공사","취소","취소","취소","취소","연속"]
[408,"전북","군산","새만금S/S 154kV CB 6300","군산P/O 차단기 조작시험 점검공사","군산P/O 차단기 조작시험 점검공사","취소","취소","취소","취소","연속"]
[409,"전북","군산","새만금소룡#2 T/L","154kV 새만금-소룡T/L 리콜 접속함 교체공사(안전이격)","리콜(하자) R타입 PMJ 접속함 23상 교체공사(토목작업)","2021-03-08 09:00","2021-03-11 18:00","취소","취소","연속"]
[410,"전북","군산","새만금S/S 154kV CB 6200","군산P/O 차단기 조작시험 점검공사","군산P/O 차단기 조작시험 점검공사","취소","취소","취소","취소","연속"]
[411,"전북","군산","새만금소룡#1 T/L","154kV 새만금-소룡T/L 리콜 접속함 교체공사","리콜(하자) R타입 PMJ 접속함 23상 교체공사","2021-03-08 09:00","2021-03-21 18:00","취소","취소","연속"]
[412,"전북","군산","서군산소룡#2 T/L","154kV 서군산-소룡 #2T/L 전선접속개소 정비공사","송전선로 전선접속개소 정비공사 No.6~9호간","2021-03-08 07:00","2021-03-09 18:00","취소","취소","연속"]
[413,"전북","군산","함열영등#2 T/L","154KV 낭산 분기T/L 건설공사(안전이격)","○ 위치 : 154kV 영등-함열T/L 56-57호 ~ 신설 154kV 낭산S/S ○ 규모 : ACSR 410×2B×4C×2.065km, 철탑 7기 ○ 금회작업 내용 : 가선로 환원 및 본선로(신설1호) 구성","2021-03-22 07:00","2021-03-22 18:00","2021-03-22 07:00","2021-03-22 18:00","연속"]
[414,"전북","군산","함열영등#1 T/L","154KV 낭산 분기T/L 건설공사","○ 위치 : 154kV 영등-함열T/L 56-57호 ~ 신설 154kV 낭산S/S ○ 규모 : ACSR 410×2B×4C×2.065km, 철탑 7기 ○ 금회작업 내용 : 가선로 환원 및 본선로(신설1호) 구성","2021-03-19 07:00","2021-03-31 18:00","2021-03-19 07:00","2021-03-31 18:00","연속"]
[415,"전북","김제","신김제S/S 154kV SEC CB 66670","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (5차분)","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","2021-03-02 09:00","2021-03-12 18:00","2021-03-02 09:00","2021-03-12 18:00","연속"]
[416,"전북","김제","신김제S/S 154kV #66 BUS","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (5차분)","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","2021-03-02 09:00","2021-03-12 18:00","2021-03-02 09:00","2021-03-12 18:00","연속"]
[417,"전북","김제","신김제S/S 154kV #61 BUS","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분)","- 6244, (구)남전주#1, 65-66-0 SEC GIS 교체 - 인출변경에 따른 케이블 이설 1식 - 기타 부대공사 1식","2021-03-18 16:00","2021-04-03 16:00","2021-03-18 16:00","2021-04-03 16:00","연속"]
[418,"전북","김제","신김제S/S 154kV CB 6200","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분)","- 6244, (구)남전주#1, 65-66-0 SEC GIS 교체 - 인출변경에 따른 케이블 이설 1식 - 기타 부대공사 1식","2021-03-18 16:00","2021-04-03 16:00","2021-03-18 16:00","2021-04-03 16:00","연속"]
[419,"전북","김제","신김제S/S 154kV SEC CB 60610","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분)","- 6244, (구)남전주#1, 65-66-0 SEC GIS 교체 - 인출변경에 따른 케이블 이설 1식 - 기타 부대공사 1식","2021-03-18 16:00","2021-04-03 16:00","2021-03-18 16:00","2021-04-03 16:00","연속"]
[420,"전북","김제","신김제S/S 154kV SEC CB 61620","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분)","- 6244, (구)남전주#1, 65-66-0 SEC GIS 교체 - 인출변경에 따른 케이블 이설 1식 - 기타 부대공사 1식","2021-03-18 16:00","2021-04-03 16:00","2021-03-18 16:00","2021-04-03 16:00","연속"]
[421,"전북","김제","신김제정공#2 T/L","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분)(시험가압)","- 6244, (구)남전주#1, 65-66-0 SEC GIS 교체 - 인출변경에 따른 케이블 이설 1식 - 기타 부대공사 1식","2021-03-18 09:00","2021-03-18 16:00","2021-03-18 09:00","2021-03-18 16:00","연속"]
[422,"전북","김제","신김제S/S 154kV SEC CB 65660","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분)","- 6244, (구)남전주#1, 65-66-0 SEC GIS 교체 - 인출변경에 따른 케이블 이설 1식 - 기타 부대공사 1식","2021-03-15 09:00","2021-04-30 18:00","2021-03-15 09:00","2021-04-30 18:00","연속"]
[423,"전북","김제","신김제S/S 154kV SEC CB 66670","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분)","- 6244, (구)남전주#1, 65-66-0 SEC GIS 교체 - 인출변경에 따른 케이블 이설 1식 - 기타 부대공사 1식","2021-03-15 09:00","2021-04-30 18:00","2021-03-15 09:00","2021-04-30 18:00","연속"]
[424,"전북","김제","신김제S/S 154kV SEC CB 61620","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (5차분)","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","취소","취소","취소","취소","연속"]
[425,"전북","김제","신김제S/S 154kV #60 BUS","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (5차분)","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","취소","취소","취소","취소","연속"]
[426,"전북","김제","신김제S/S 154kV #61 BUS","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (5차분)","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","취소","취소","취소","취소","연속"]
[427,"전북","김제","신김제S/S 154kV CB 6100","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (5차분)","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","취소","취소","취소","취소","연속"]
[428,"전북","김제","신김제S/S 154kV #65 BUS","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (5차분)","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","취소","취소","취소","취소","연속"]
[429,"전북","김제","신김제S/S 154kV #65 BUS","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분)","- 6244, (구)남전주#1, 65-66-0 SEC GIS 교체 - 인출변경에 따른 케이블 이설 1식 - 기타 부대공사 1식","취소","취소","취소","취소","연속"]
[430,"전북","김제","신김제S/S 154kV CB 6100","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분)","- 6244, (구)남전주#1, 65-66-0 SEC GIS 교체 - 인출변경에 따른 케이블 이설 1식 - 기타 부대공사 1식","취소","취소","취소","취소","연속"]
[431,"전북","김제","신김제S/S 154kV #66 BUS","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분)","- 6244, (구)남전주#1, 65-66-0 SEC GIS 교체 - 인출변경에 따른 케이블 이설 1식 - 기타 부대공사 1식","취소","취소","취소","취소","연속"]
[432,"전북","김제","신김제S/S 154kV CB 6200","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분)","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","취소","취소","취소","취소","연속"]
[433,"전북","김제","신김제정공#1 T/L","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (5차분)(시험가압)","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","2021-03-11 09:00","2021-03-12 18:00","2021-03-11 09:00","2021-03-12 18:00","연속"]
[434,"전북","김제","신김제전주#2 T/L","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (5차분)(안전이격)","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","2021-03-02 09:00","2021-03-03 18:00","2021-03-02 09:00","2021-03-03 18:00","연속"]
[435,"전북","김제","신김제남전주#1 T/L","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (5차분)(인출변경)","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식 (657 CB 남전주#1 -> 687CB로 이동)","2021-03-02 09:00","2021-03-12 18:00","2021-03-02 09:00","2021-03-12 18:00","연속"]
[436,"전북","김제","신김제S/S 154kV SEC CB 65660","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (5차분)","- 154kV GIS 14CCT, PT 2BAY 교체 - 배열에 따른 감시,제어, 경보 케이블 이설 - 기타 부대공사 1식","2021-03-02 09:00","2021-03-12 18:00","2021-03-02 09:00","2021-03-12 18:00","연속"]
[437,"전북","김제","정공담양 T/L","정공S/S 170kV GIS 교체공사 (안전이격)","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2021-03-08 09:30","2021-03-28 18:00","2021-03-08 09:30","2021-03-28 18:00","매일"]
[438,"전북","김제","정공S/S 154kV #1 BUS","정공S/S 170kV GIS 교체공사(60-61 BUS SEC 설치공사)","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2021-03-19 13:00","2021-04-02 13:00","2021-03-19 13:00","2021-04-02 13:00","연속"]
[439,"전북","김제","신김제정공#1 T/L","정공S/S 170kV GIS 교체공사 (시험가압)","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2021-03-18 16:00","2021-03-19 16:00","2021-03-18 16:00","2021-03-19 16:00","연속"]
[440,"전북","김제","정공S/S 154kV #2 BUS","정공S/S 170kV GIS 교체공사(65-66 BUS SEC 설치공사)","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2021-03-08 09:30","2021-03-19 13:00","2021-03-08 09:30","2021-03-19 13:00","연속"]
[441,"전북","김제","신김제정공#1 T/L","정공S/S 170kV GIS 교체공사(시험가압)","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2021-03-31 13:00","2021-04-02 09:00","2021-03-31 13:00","2021-04-02 09:00","연속"]
[442,"전북","김제","정공칠보HP T/L","정공S/S 170kV GIS 교체공사  (안전이격)","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2021-03-08 09:30","2021-03-28 18:00","2021-03-08 09:30","2021-03-28 18:00","매일"]
[443,"전북","김제","신김제정공#1 T/L","정공S/S 170kV GIS 교체공사 (시험가압)","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2021-03-04 13:00","2021-03-05 13:00","2021-03-04 13:00","2021-03-05 13:00","연속"]
[444,"전북","직할","신남원남원#2 T/L","154kV 남원S/S 옥외철구설비 GIS화 공사","○ 154kV 신남원-남원#2T/L 인출구간 변경 및 GIS설비로 이전","2021-03-25 08:00","2021-04-12 18:00","2021-04-12 08:00","2021-05-14 18:00","연속"]
[445,"전북","직할","곡성남원#2 T/L","154kV 남원S/S 옥외철구설비 GIS화 공사","○ 154kV 곡성-남원#2T/L 인출구간 변경 및 GIS설비로 이전","2021-03-25 08:00","2021-04-12 18:00","2021-04-12 08:00","2021-05-14 18:00","연속"]
[446,"전북","직할","남원S/S 남원전철#1 T/L CB 657","154kV 남원S/S 옥외철구설비 GIS화 공사","○ 154kV 남원-전철#1T/L 인출구간 변경 및 GIS설비로 이전","취소","취소","취소","취소","연속"]
[447,"전북","직할","남원임실#2 T/L","154kV 남원S/S 옥외철구설비 GIS화 공사","○ 154kV 남원-임실#2T/L 인출구간 변경 및 GIS설비로 이전","2021-03-05 08:00","2021-03-24 18:00","취소","취소","연속"]
[448,"전북","직할","신남원남원#1 T/L","154kV 남원S/S 옥외철구설비 GIS화 공사","○ 154kV 신남원-남원#1T/L 인출구간 변경 및 GIS설비로 이전","2021-03-05 08:00","2021-03-24 18:00","취소","취소","연속"]
[449,"전북","직할","남원S/S 남원전철#1 T/L CB 667","154kV 남원S/S 옥외철구설비 GIS화 공사","○ 154kV 남원-전철#2T/L 인출구간 변경 및 GIS설비로 이전","취소","취소","취소","취소","연속"]
[450,"전북","직할","동전주북전주#2 T/L","동전주S/S SA혼용시스템 설치공사","○ 개소 : 154kV 동전주-북전주#2T/L","취소","취소","취소","취소","연속"]
[451,"전북","직할","동전주태평#1 T/L","동전주S/S SA혼용시스템 설치공사","○ 개소 : 154kV 동전주-태평#1T/L","취소","취소","취소","취소","연속"]
[452,"전북","직할","동전주S/S 전주전철#2 T/L CB 637","동전주S/S SA혼용시스템 설치공사","○ 개소: 154kV 전주전철#2T/L","취소","취소","취소","취소","연속"]
[453,"전북","직할","신김제동전주#1 T/L","동전주S/S SA혼용시스템 설치공사","○ 개소 : 154kV 신김제-동전주#1T/L","2021-03-15 09:00","2021-03-16 18:00","취소","취소","연속"]
[454,"전북","직할","무주S/S 154kV #2 BUS","(2차)무주S/S 154kV GIS 교체공사","- 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2021-03-03 10:00","2021-03-19 15:00","취소","취소","연속"]
[455,"전북","직할","금산무주#1 T/L","(2차)무주S/S 154kV GIS 교체공사(Main 교체)","- 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2021-03-03 10:00","2021-04-13 15:00","취소","취소","연속"]
[456,"전북","직할","무주S/S 154kV #65 PT CB","(2차)무주S/S 154kV GIS 교체공사(Main 교체)","- 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","취소","취소","취소","취소","연속"]
[457,"전북","직할","무주진안 T/L","(2차)무주S/S 154kV GIS 교체공사(시험가압)","*** 154kV #60BUS 무부하 가압 선로 - 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)\n(* 무주-진안, 무주-용담수력T/L 둘중 한 개 선로 시험가압 가능)","2021-03-30 15:00","2021-03-31 15:00","취소","취소","연속"]
[458,"전북","직할","무주S/S 154kV #60 PT CB","(2차)무주S/S 154kV GIS 교체공사","- 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","취소","취소","취소","취소","연속"]
[459,"전북","직할","무주S/S 154kV #1 BUS","(2차)무주S/S 154kV GIS 교체공사","-무주S/S 170kV 장기사용 GIS 교체공사(# 60 BUS)","2021-03-19 15:00","2021-03-31 15:00","취소","취소","연속"]
[460,"전북","직할","무주진안 T/L","(2차)무주S/S 154kV GIS 교체공사(시험가압)","*** 무부하 가압용 선로 - 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)\n(* 무주-진안, 무주-용담수력T/L 둘중 한 개 선로 시험가압 가능)","2021-03-18 15:00","2021-03-19 15:00","취소","취소","연속"]
[461,"전북","직할","무주S/S 154kV #2 BUS","(2차)무주S/S 154kV GIS 교체공사","- 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2021-03-31 15:00","2021-04-13 15:00","취소","취소","연속"]
[462,"전북","직할","무주S/S 154kV CB 6100","(2차)무주S/S 154kV GIS 교체공사(Main 교체)","- 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2021-03-03 10:00","2021-04-13 15:00","취소","취소","연속"]
[463,"전북","직할","무주용담수력 T/L","(2차)무주S/S 154kV GIS 교체공사(안전이격)","- 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2021-03-09 09:00","2021-03-09 11:00","취소","취소","연속"]
[464,"전북","직할","무주용담수력 T/L","(2차)무주S/S 154kV GIS 교체공사(시험가압)","*** 154kV #60BUS 무부하 가압 선로 - 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)\n(* 무주-진안, 무주-용담수력T/L 둘중 한 개 선로 시험가압 가능)","2021-03-30 15:00","2021-03-31 15:00","취소","취소","연속"]
[465,"전북","직할","무주용담수력 T/L","(2차)무주S/S 154kV GIS 교체공사(시험가압)","*** 154kV #60BUS 무부하 가압 선로 - 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)\n(* 무주-진안, 무주-용담수력T/L 둘중 한 개 선로 시험가압 가능)","2021-03-18 15:00","2021-03-19 15:00","취소","취소","연속"]
[466,"전북","직할","금산무주#2 T/L","(2차)무주S/S 154kV GIS 교체공사(안전이격)","- 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2021-03-09 11:00","2021-03-09 13:00","취소","취소","연속"]
[467,"전북","직할","북전주봉동#1 T/L","봉동S/S 북전주-봉동#1T/L 보통점검","봉동S/S 북전주-봉동#1T/L 보통점검","2021-03-04 09:00","2021-03-04 18:00","취소","취소","연속"]
[468,"전북","직할","팔봉봉동#1 T/L","봉동S/S 팔봉-봉동#1T/L 보통점검","봉동S/S 팔봉-봉동#1T/L 보통점검","2021-03-08 09:00","2021-03-08 18:00","취소","취소","연속"]
[469,"전북","직할","팔봉봉동#2 T/L","봉동S/S 팔봉-봉동#2T/L 보통점검","봉동S/S 팔봉-봉동#2T/L 보통점검","2021-03-17 09:00","2021-03-17 18:00","취소","취소","연속"]
[470,"전북","직할","북전주용담수력 T/L","북전주S/S 북전주-용담수력T/L 조작시험","북전주S/S 북전주-용담수력T/L 조작시험","2021-03-03 09:00","2021-03-03 18:00","2021-03-03 09:00","2021-03-03 18:00","연속"]
[471,"전북","직할","북전주봉동#2 T/L","봉동S/S 북전주-봉동#2T/L 보통점검","○ 관내 154kV 이상 차단기 점검공사 - 북전주S/S 154kV 북전주-봉동#2/TL 전자변교체(조작시험포함)","2021-03-05 09:00","2021-03-05 18:00","취소","취소","연속"]
[472,"전북","직할","이리탄소#2 T/L","탄소S/S 이리-탄소#2T/L 초기점검","탄소S/S 이리-탄소#2T/L 초기점검","2021-03-16 09:00","2021-03-16 18:00","취소","취소","연속"]
[473,"전북","직할","이리탄소#1 T/L","탄소S/S 이리-탄소#1T/L 초기점검","탄소S/S 이리-탄소#1T/L 초기점검","2021-03-15 09:00","2021-03-15 18:00","취소","취소","연속"]
[474,"전북","직할","전주탄소#1 T/L","탄소S/S 탄소-전주#1T/L 초기점검","탄소S/S 탄소-전주#1T/L 초기점검","2021-03-10 09:00","2021-03-10 18:00","취소","취소","연속"]
[475,"전북","직할","전주탄소#2 T/L","탄소S/S 탄소-전주#2T/L 초기점검","탄소S/S 탄소-전주#2T/L 초기점검","2021-03-11 09:00","2021-03-11 18:00","취소","취소","연속"]
[476,"광주전남","강진","신화순나주#1 T/L","154kV 신화순-나주T/L 지장철탑 이설공사","강진광주간 고속도로 관련 지장철탑 이설 154kV 신화순-나주T/L 52-55호 (154kV 나주-금천T/L 89-92호 병가) 철탑 1기 철거, 1기 신설(53호), 임시철탑 1기","2021-03-14 09:00","2021-03-18 18:00","취소","취소","연속"]
[477,"광주전남","강진","나주엄다#2 T/L","2020~21년 직할 송전정비회사 총액공사","154kV 왕곡-나주#2T/L 피뢰기 설치공사 관련 4회선 병가구간 안전이격거리 확보차","2021-03-02 08:00","2021-03-02 18:00","2021-03-04 08:00","2021-03-04 18:00","연속"]
[478,"광주전남","강진","나주금천#2 T/L","154kV 신화순-나주T/L 지장철탑 이설공사","강진광주간 고속도로 관련 지장철탑 이설 154kV 신화순-나주T/L 52-55호 (154kV 나주-금천T/L 89-92호 병가) 철탑 1기 철거, 1기 신설(53호), 임시철탑 1기","2021-03-10 09:00","2021-03-13 18:00","2021-03-29 09:00","2021-04-02 18:00","연속"]
[479,"광주전남","강진","신화순나주#2 T/L","154kV 신화순-나주T/L 지장철탑 이설공사","강진광주간 고속도로 관련 지장철탑 이설 154kV 신화순-나주T/L 52-55호 (154kV 나주-금천T/L 89-92호 병가) 철탑 1기 철거, 1기 신설(53호), 임시철탑 1기","2021-03-10 09:00","2021-03-13 18:00","취소","취소","연속"]
[480,"광주전남","강진","나주금천#1 T/L","154kV 신화순-나주T/L 지장철탑 이설공사","강진광주간 고속도로 관련 지장철탑 이설 154kV 신화순-나주T/L 52-55호 (154kV 나주-금천T/L 89-92호 병가) 철탑 1기 철거, 1기 신설(53호), 임시철탑 1기","2021-03-14 09:00","2021-03-18 18:00","취소","취소","연속"]
[481,"광주전남","강진","나주영암#2 T/L","154kV 나주-영암T/L No.20 지장철탑 이설공사","봉황농어촌도로 204호선 확포장사업 관련 154kV 나주-영암T/L No.20 철탑 이설(신설1, 철거1)","2021-03-20 08:00","2021-03-22 18:00","2021-03-20 08:00","2021-03-22 18:00","연속"]
[482,"광주전남","강진","나주영암#1 T/L","154kV 나주-영암T/L No.20 지장철탑 이설공사","봉황농어촌도로 204호선 확포장사업 관련 154kV 나주-영암T/L No.20 철탑 이설(신설1, 철거1)","2021-03-20 08:00","2021-03-21 18:00","2021-03-20 08:00","2021-03-21 18:00","매일"]
[483,"광주전남","강진","남창해남CS#1 T/L","154kV 남창S/S GIS화 공사","○ 제어케이블 철거, 설치 및 결선 × 1식 ○ 기타 부대작업 × 1식","2021-03-15 09:00","2021-03-20 18:00","2021-03-15 09:00","2021-03-20 18:00","연속"]
[484,"광주전남","강진","남창해남CS#2 T/L","154kV 남창S/S GIS화 공사","○ 제어케이블 철거, 설치 및 결선 × 1식 ○ 기타 부대작업 × 1식","2021-03-22 09:00","2021-03-27 18:00","2021-03-22 09:00","2021-03-27 18:00","연속"]
[485,"광주전남","강진","진도서제주HVDC #2 Pole CB","'20~'21년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) #Bipole(#1, 2 Pole) 연차점검","2021-03-04 09:00","2021-03-13 18:00","2021-03-04 09:00","2021-03-13 18:00","연속"]
[486,"광주전남","강진","진도진도CS#2 T/L","'20~21년 #2HVDC 변환설비 위탁정비공사","변환설비 연차점검 및 변전설비 정밀점검(#1 C.Tr 및 #1,2 C.Tr 1차 GIS) 무부하가압","2021-03-07 09:00","2021-03-08 09:00","2021-03-07 09:00","2021-03-08 09:00","연속"]
[487,"광주전남","강진","진도C/S 154kV #2 BUS","'20~21년 #2HVDC 변환설비 위탁정비공사","변환설비 연차점검 및 변전설비 정밀점검(#1 C.Tr 및 #1,2 C.Tr 1차 GIS) 무부하가압","2021-03-07 09:00","2021-03-08 09:00","2021-03-07 09:00","2021-03-08 09:00","연속"]
[488,"광주전남","강진","해남해남CS#2 T/L","남창-해남C/S OPGW 교체공사","남창-해남C/S OPGW 교체공사중 병가구간 ( 해남-해남C/S) 휴전","2021-03-22 09:00","2021-03-25 18:00","2021-03-22 09:00","2021-03-25 18:00","연속"]
[489,"광주전남","광주","신광주계림#2 T/L","345kV 신광주-신화순등5개T/L 피뢰기설치공사","345kV 신광주-신화순등5개T/L 피뢰기설치공사 - 154kV 신광주-계림#2T/L(12기)","2021-03-01 09:00","2021-03-01 18:00","2021-03-01 09:00","2021-03-01 18:00","연속"]
[490,"광주전남","광주","신광주일곡#2 T/L","154kV 신광주-일곡T/L 지중화 전력구공사","수직구 세미실드 장비반입에 따른 선로인근 대형장비(크레인) 작업","2021-03-11 07:00","2021-03-12 18:00","취소","취소","매일"]
[491,"광주전남","순천","광양순천#1 T/L","세니온 송전선로 보호IED성능개선","세니온 송전선로 보호IED성능개선","2021-03-22 10:00","2021-03-22 18:00","취소","취소","연속"]
[492,"광주전남","순천","순천율촌#1 T/L","세니온 송전선로 보호IED성능개선","세니온 송전선로 보호IED성능개선","2021-03-29 10:00","2021-03-29 18:00","취소","취소","연속"]
[493,"광주전남","순천","광양순천#2 T/L","세니온 송전선로 보호IED성능개선","세니온 송전선로 보호IED성능개선","2021-03-23 10:00","2021-03-23 18:00","취소","취소","연속"]
[494,"광주전남","순천","순천율촌#2 T/L","세니온 송전선로 보호IED성능개선","세니온 송전선로 보호IED성능개선","2021-03-30 10:00","2021-03-30 18:00","취소","취소","연속"]
[495,"광주전남","순천","순천승주#1 T/L","세니온 송전선로 보호IED성능개선","세니온 송전선로 보호IED성능개선","2021-03-12 10:00","2021-03-12 18:00","취소","취소","연속"]
[496,"광주전남","순천","순천승주#2 T/L","YPPP제 송전선로 계전기 성능개선","YPPP제 송전선로 계전기 성능개선","2021-03-15 10:00","2021-03-15 18:00","취소","취소","연속"]
[497,"광주전남","순천","여천여수#2 T/L","20-21년 순천전력지사 변전정비회사 총액공사","여수SS 여천-여수#2T/L GIS 보통점검 및 여천SS 여천-여수#2T/L LA(A,B,C) 보통점검","2021-03-26 09:00","2021-03-26 18:00","2021-03-26 09:00","2021-03-26 18:00","연속"]
[498,"광주전남","순천","여천여수산단#1 T/L","20-21년 변전정비회사 총액공사","여천S/S 여천-여수산단#1T/L GIS 보통점검","2021-03-22 09:00","2021-03-22 18:00","2021-03-22 09:00","2021-03-22 18:00","연속"]
[499,"광주전남","직할","충장농성#1 T/L","2020~21년 직할 변전정비회사 총액공사","변전설비 기기점검","2021-03-10 09:00","2021-03-10 13:00","2021-03-29 09:00","2021-03-29 13:00","연속"]
[500,"광주전남","직할","충장농성#2 T/L","2020~21년 직할 변전정비회사 총액공사","변전설비 기기점검","2021-03-10 13:00","2021-03-10 18:00","2021-03-29 13:00","2021-03-29 18:00","연속"]
[501,"광주전남","직할","일곡비아#2 T/L","2020~21년 직할 변전정비회사 총액공사","변전설비 기기점검","2021-03-19 13:00","2021-03-19 18:00","2021-03-19 13:00","2021-03-19 18:00","연속"]
[502,"광주전남","직할","일곡비아#1 T/L","2020~21년 직할 변전정비회사 총액공사","변전설비 기기점검","2021-03-19 09:00","2021-03-19 13:00","2021-03-19 09:00","2021-03-19 13:00","연속"]
[503,"광주전남","직할","실증시험장 154kV CB 6100","왕곡실증시험장 170kV GIS 실증기기 조작시험","실증기기(6100CB) 주 1회 2~3회 동작시험","2021-03-01 09:00","2021-03-31 18:00","2021-03-01 09:00","2021-03-31 18:00","연속"]
[504,"광주전남","직할","평동왕곡#2 T/L","154kV 왕곡S/S #1,4M.Tr 증설공사(#4M.Tr 측)","154kV 왕곡S/S #1,4M.Tr 증설공사","2021-03-02 10:00","2021-03-10 18:00","2021-03-05 08:00","2021-03-12 18:00","연속"]
[505,"광주전남","직할","왕곡나주#2 T/L","154kV 왕곡S/S #1,4M.Tr 증설공사(#4M.Tr 측)","154kV 왕곡S/S #1,4M.Tr 증설공사","2021-03-02 10:00","2021-03-09 18:00","2021-03-04 08:00","2021-03-05 18:00","연속"]
[506,"광주전남","직할","매월화정#2 T/L","154kV 매월-화정T/L 일부구간 지장선로 이설공사","- 공사목적 : 도시철도 2호선 사업시행에 따른 지중선로 지장구간 이설 - 공사구간: 154kV 매월-화정T/L 맨홀 #6 ~ 맨홀#9 (0.96km)","2021-03-02 09:00","2021-03-27 18:00","2021-03-02 09:00","2021-03-27 18:00","연속"]
[507,"광주전남","직할","매월화정#1 T/L","154kV 매월-화정T/L 일부구간 지장선로 이설공사","- 공사목적 : 도시철도 2호선 사업시행에 따른 지중선로 지장구간 이설 - 공사구간: 154kV 매월-화정T/L 맨홀 #6 ~ 맨홀#9 (0.96km)","2021-03-30 09:00","2021-04-24 18:00","2021-03-30 09:00","2021-04-24 18:00","연속"]
[508,"광주전남","직할","수완흑석#2 T/L","2020~21년 직할 변전정비회사 총액공사","변전설비 기기점검","2021-03-05 13:00","2021-03-05 18:00","2021-03-05 13:00","2021-03-05 18:00","연속"]
[509,"광주전남","직할","수완흑석#1 T/L","2020~21년 직할 변전정비회사 총액공사","변전설비 기기점검","2021-03-05 09:00","2021-03-05 13:00","2021-03-05 09:00","2021-03-05 13:00","연속"]
[510,"대구",null,"수완흑석#1 T/L","2020~21년 직할 변전정비회사 총액공사","변전설비 기기점검","2021-03-05 09:00","2021-03-05 13:00","취소","취소","연속"]
[511,"대구","경산","범물남대구#1 T/L","범물S/S 154kV GIS 교체공사","범물S/S 154kV GIS 교체공사(6233 TEST선로)","2021-03-09 18:00","2021-03-10 09:00",{"$f":"G515","v":"2021-03-09 18:00"},"2021-03-10 09:00","연속"]
[512,"대구","경산","범물남대구#1 T/L","범물S/S 154kV GIS 교체공사","범물S/S 154kV GIS 교체공사(6233 TEST선로)","2021-03-16 18:00","2021-03-17 09:00","2021-03-16 18:00","2021-03-17 09:00","연속"]
[513,"대구","경산","범물남대구#1 T/L","범물S/S 154kV GIS 교체공사","범물S/S 154kV GIS 교체공사(6233 TEST선로)","2021-03-23 18:00","2021-03-26 18:00","2021-03-23 18:00","2021-03-26 18:00","연속"]
[514,"대구","경산","신경산노변 T/L","154kV 신경산-노변 등 5개T/L EBA 비표준형 자기애관 교체공사","154kV 신경산-노변 등 5개T/L EBA 비표준형 자기애관 교체공사","2021-03-15 08:00","2021-03-21 18:00","2021-03-15 08:00","2021-03-21 18:00","연속"]
[515,"대구","경산","신경산진량 T/L","154kV 신경산-노변 등 5개T/L EBA 비표준형 자기애관 교체공사","154kV 신경산-노변 등 5개T/L EBA 비표준형 자기애관 교체공사","2021-03-22 08:00","2021-03-28 18:00","2021-03-22 08:00","2021-03-28 18:00","연속"]
[516,"대구","달성","고령다산#2 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2021-03-15 08:00","2021-03-20 18:00","2021-03-15 08:00","2021-03-20 18:00","연속"]
[517,"대구","달성","고령S/S 154kV #60 BUS","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2021-03-25 18:00","2021-03-26 18:00","2021-03-25 18:00","2021-03-26 18:00","연속"]
[518,"대구","달성","고령S/S 154kV #61 BUS","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2021-03-25 17:00","2021-03-25 18:00","2021-03-25 17:00","2021-03-25 18:00","연속"]
[519,"대구","달성","고령다산#1 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2021-03-21 08:00","2021-03-26 18:00","2021-03-21 08:00","2021-03-26 18:00","연속"]
[520,"대구","달성","고령쌍림#1 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2021-03-21 08:00","2021-03-25 18:00","2021-03-21 08:00","2021-03-25 18:00","연속"]
[521,"대구","달성","고령S/S 154kV #65 BUS","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2021-03-19 18:00","2021-03-20 18:00","2021-03-19 18:00","2021-03-20 18:00","연속"]
[522,"대구","달성","고령S/S 154kV #66 BUS","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2021-03-19 17:00","2021-03-19 18:00","2021-03-19 17:00","2021-03-19 18:00","연속"]
[523,"대구","달성","고령쌍림#2 T/L","고령변전소 154kV 송전선로 인출변경","고령변전소 154kV 송전선로 인출변경","2021-03-15 08:00","2021-03-21 18:00","2021-03-15 08:00","2021-03-21 18:00","연속"]
[524,"대구","달성","다사달서#2 T/L","154kV 팔달-강창 지장이설공사(가공)","C/H(No.25, 29) 설치 안전이격","2021-03-08 09:00","2021-03-11 18:00","취소","취소","연속"]
[525,"대구","달성","다사달서#1 T/L","154kV 팔달-강창 지장이설공사(가공)","C/H(No.25, 29) 설치 안전이격","2021-03-03 09:00","2021-03-11 18:00","취소","취소","연속"]
[526,"대구","달성","달성S/S 154kV #1 BUS","달성S/S 달성-월배T/L SW 증설(TEST선로)","달성S/S 달성-월배T/L SW 증설(TEST선로)","2021-03-13 09:00","2021-03-14 18:00",{"$f":"G530","v":"2021-03-13 09:00"},"2021-03-14 18:00","연속"]
[527,"대구","달성","달성상인#1 T/L","달성S/S 달성-월배T/L SW 증설(TEST선로)","달성S/S 달성-월배T/L SW 증설(TEST선로)","2021-03-06 09:00","2021-03-07 18:00","2021-03-06 09:00","2021-03-07 18:00","연속"]
[528,"대구","달성","달성상인#1 T/L","달성S/S 달성-월배T/L SW 증설(TEST선로)","달성S/S 달성-월배T/L SW 증설(TEST선로)","2021-03-13 09:00","2021-03-14 18:00","2021-03-13 09:00","2021-03-14 18:00","연속"]
[529,"대구","달성","달성S/S 154kV #2 BUS","달성S/S 달성-월배T/L SW 증설","달성S/S 달성-월배T/L SW 증설","2021-03-02 09:00","2021-03-07 18:00","2021-03-02 09:00","2021-03-07 18:00","연속"]
[530,"대구","달성","대구봉덕#2 T/L","대구,봉덕S/S 대구-봉덕#2T/L GIS 보통점검","대구,봉덕S/S 대구-봉덕#2T/L GIS 보통점검","2021-03-17 09:00","2021-03-17 18:00","2021-03-17 09:00","2021-03-17 18:00","연속"]
[531,"대구","달성","대구봉덕#1 T/L","대구,봉덕S/S 대구-봉덕#1T/L GIS 보통점검","대구,봉덕S/S 대구-봉덕#1T/L GIS 보통점검","2021-03-16 09:00","2021-03-16 18:00","2021-03-16 09:00","2021-03-16 18:00","연속"]
[532,"대구","달성","두류봉덕#2 T/L","두류,봉덕S/S 두류-봉덕#2T/L GIS 보통점검","두류,봉덕S/S 두류-봉덕#2T/L GIS 보통점검","2021-03-10 09:00","2021-03-10 18:00","2021-03-10 09:00","2021-03-10 18:00","연속"]
[533,"대구","달성","두류봉덕#1 T/L","두류,봉덕S/S 두류-봉덕#1T/L GIS 보통점검","두류,봉덕S/S 두류-봉덕#1T/L GIS 보통점검","2021-03-09 09:00","2021-03-09 18:00","2021-03-09 09:00","2021-03-09 18:00","연속"]
[534,"대구","직할","공평서침산 T/L","154kV공평-서침산T/L OF 선종교체 공사","OF 케이블을 XLPE 케이블로 교체 구간 : 공평EBG~J/B#4","2021-03-09 09:00","2021-04-09 18:00","2021-03-09 09:00","2021-04-09 18:00","연속"]
[535,"대구","직할","시지효목#1 T/L","21-22년 대구본부 직할 지중송전 위탁정비공사","ㅇ EBA절연유 채유","2021-03-12 10:00","2021-03-12 18:00","2021-03-12 10:00","2021-03-12 18:00","연속"]
[536,"대구","포항","건천천북#2 T/L","154kV 건천-천북T/L No.6~8 지장송전선로 지중화공사","신경주역세권개발에 따른 154kV 건천-천북T/L No.6~8 지중화공사(요청자시행) - 작업내용 : No.6~8 임시선로구성 - 철탑신설 : No.6,8 - 철탑보강 : No.5,9 - 철탑철거 : No.6,7,8","2021-03-06 08:00","2021-03-11 18:00","2021-03-06 08:00","2021-03-11 18:00","연속"]
[537,"대구","포항","건천천북#1 T/L","154kV 건천-천북T/L No.6~8 지장송전선로 지중화공사","신경주역세권개발에 따른 154kV 건천-천북T/L No.6~8 지중화공사(요청자시행) - 작업내용 : No.6~8 임시선로구성 - 철탑신설 : No.6,8 - 철탑보강 : No.5,9 - 철탑철거 : No.6,7,8","2021-03-02 08:00","2021-03-05 18:00","2021-03-02 08:00","2021-03-05 18:00","연속"]
[538,"대구","포항","영일포항#2 T/L","154kV 영일-포항T/L 안전이격거리확보공사 [동시휴전]","- No.15 철탑 상부재 일부 교체 - No.13~15 전력선 및 OPGW 교체 - No.14, 15 고정형 추락방지장치 설치","2021-03-02 07:30","2021-03-07 18:00","2021-03-02 07:30","2021-03-07 18:00","연속"]
[539,"대구","포항","영일포항#1 T/L","154kV 영일-포항T/L 안전이격거리확보공사 [동시휴전]","- No.15 철탑 상부재 일부 교체 - No.13~15 전력선 및 OPGW 교체 - No.14, 15 고정형 추락방지장치 설치","2021-03-02 07:30","2021-03-07 18:00","2021-03-02 07:30","2021-03-07 18:00","연속"]
[540,"경북","구미","산동군위#1 T/L","154kV 산동-군위T/L 안전이격확보공사(No.3~7)","154kV 산동-군위T/L 안전이격확보공사(No.3~7) 철탑 설치 : 4기, 철거 :4기, 가선로구성 철거/설치 : 4기","2021-03-06 07:00","2021-03-18 18:00","2021-03-06 07:00","2021-03-18 18:00","연속"]
[541,"경북","영주","봉화현종산풍력 T/L","154kV 봉화분기T/L 상간스페이서 설치공사","154kV 봉화분기T/L 상간스페이서 설치공사","2021-03-09 07:00","2021-03-09 18:00","2021-03-09 07:00","2021-03-09 18:00","연속"]
[542,"경북","영주","봉화울진 T/L","154kV 봉화분기T/L 상간스페이서 설치공사","154kV 봉화분기T/L 상간스페이서 설치공사","2021-03-10 07:00","2021-03-10 18:00","2021-03-10 07:00","2021-03-10 18:00","연속"]
[543,"경북","영주","신영주안동#1 T/L","신영주S/S 154kV 옥외철구설비 현대화공사","MOSAIC PNL 개조공사 관련 설비제어 케이블 이설","2021-03-25 13:00","2021-03-25 18:00","2021-03-25 13:00","2021-03-25 18:00","연속"]
[544,"경북","영주","신영주안동#2 T/L","신영주S/S 154kV 옥외철구설비 현대화공사","MOSAIC PNL 개조공사 관련 설비제어 케이블 이설","2021-03-25 08:00","2021-03-25 13:00","2021-03-25 08:00","2021-03-25 13:00","연속"]
[545,"경북","직할","현종산풍력평해#1 T/L","20~21년 경북본부 직할 변전정비회사 총액공사","피뢰기 추가 설치","2021-03-02 09:00","2021-03-02 18:00","2021-03-02 09:00","2021-03-02 18:00","연속"]
[546,"부산울산","동부산","구서노포#2 T/L","구서S/S 154kV GIS 차단기 동작시험","구서S/S 154kV GIS 차단기 동작시험(구서-노포#2T/L)","2021-03-24 09:30","2021-03-24 17:00","2021-03-24 09:30","2021-03-24 17:00","연속"]
[547,"부산울산","동부산","신양산구서#2 T/L","21년 가공송전 협력회사 총액공사(동부산전력지사)","○ 96년도 이전 국산애자 교체 : 2,4,10,22,37호 ○ 추락방지장치 설치(와이어형) : 21,22,40호","2021-03-02 08:00","2021-03-05 18:00","2021-03-02 08:00","2021-03-05 18:00","연속"]
[548,"부산울산","동부산","구서명장#2 T/L","21년 가공송전 협력회사 총액공사(동부산전력지사)","○ 96년도 이전 국산애자 교체, 추락방지장치 설치(와이어형) 154kV 신양산-구서#2T.L 작업관련 안전이격 확보용","2021-03-02 08:00","2021-03-05 18:00","2021-03-02 08:00","2021-03-05 18:00","연속"]
[549,"부산울산","동부산","신양산구서#1 T/L","동부산전력지사 관내 OPGW 항공장애표시구 설치공사","154kV 신양산-수영#1/L 항공구 설치공사 안전이격확보용 휴전","2021-03-17 08:00","2021-03-17 18:00","취소","취소","연속"]
[550,"부산울산","동부산","신양산구서#2 T/L","동부산전력지사 관내 OPGW 항공장애표시구 설치공사","154kV 신양산-수영#2T/L 항공구 설치공사 안전이격확보용 휴전","2021-03-18 08:00","2021-03-18 18:00","취소","취소","연속"]
[551,"부산울산","동부산","구서노포#1 T/L","구서S/S 154kV GIS 차단기 동작시험","구서S/S 154kV GIS 차단기 동작시험(구서-노포#1T/L)","2021-03-23 09:30","2021-03-23 17:00",{"$f":"G555","v":"2021-03-23 09:30"},"2021-03-23 17:00","연속"]
[552,"부산울산","동부산","신울산명례#1 T/L","명례S/S 154kV GIS 보통점검","명례S/S 154kV GIS 보통점검(신울산-명례#1T/L)","2021-03-10 09:30","2021-03-11 17:00","2021-03-10 09:30","2021-03-11 17:00","연속"]
[553,"부산울산","동부산","신울산명례#2 T/L","명례S/S 154kV GIS 보통점검","명례S/S 154kV GIS 보통점검(신울산-명례#2T/L)","2021-03-12 09:30","2021-03-13 17:00","2021-03-12 09:30","2021-03-13 17:00","연속"]
[554,"부산울산","동부산","수영정보#2 T/L","수영S/S 154kV GIS 차단기 동작시험","수영S/S 154kV GIS 차단기 동작시험(수영-정보#2T/L)","2021-03-20 09:30","2021-03-20 17:00","2021-03-20 09:30","2021-03-20 17:00","연속"]
[555,"부산울산","북부산","북부산구포#3 T/L","20-21 북부산전력지사 변전 총액공사","구포S/S 154kV 북부산-구포#3T/L GIS 보통점검","2021-03-31 10:00","2021-03-31 18:00","2021-03-31 10:00","2021-03-31 18:00","연속"]
[556,"부산울산","북부산","호포매리#2 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","○ #2T/L 임시선로 구성(4회선, 매리-김해#2 포함) ○ 가철탑 24-1, 1-1호 설치","2021-03-18 07:00","2021-03-20 18:00","2021-03-19 07:00","2021-03-21 18:00","연속"]
[557,"부산울산","북부산","매리김해#2 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","○ #2T/L 임시선로 구성(4회선, 호포-매리#2 포함) ○ 가철탑 24-1, 1-1호 설치","2021-03-18 07:00","2021-03-20 18:00","2021-03-19 07:00","2021-03-21 18:00","연속"]
[558,"부산울산","북부산","호포매리#1 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","○ #1T/L 임시선로 구성(4회선, 매리-김해#1 포함) ○ 가철탑 24-1, 1-1호 설치","2021-03-25 07:00","2021-03-27 18:00","2021-03-26 07:00","2021-03-28 18:00","연속"]
[559,"부산울산","북부산","매리김해#1 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","○ #1T/L 임시선로 구성(4회선, 호포-매리#1 포함) ○ 가철탑 24-1, 1-1호 설치","2021-03-25 07:00","2021-03-27 18:00","2021-03-26 07:00","2021-03-28 18:00","연속"]
[560,"부산울산","북부산","북부산양산 T/L","20-21 북부산전력지사 변전 총액공사","북부산S/S 154kV 북부산-양산T/L GIS 초기점검","2021-03-26 10:00","2021-03-26 18:00",{"$f":"G564","v":"2021-03-26 10:00"},"2021-03-26 18:00","연속"]
[561,"부산울산","북부산","언양산막#1 T/L","20-21년 북부산전력지사 가공송전정비회사 총액공사","154kV 언양-산막#1T/L 96년 상반기 이전 성능저하 애자교체공사 . 추락방지장치 설치, 1-72호(총 9기)","2021-03-13 08:00","2021-03-24 17:00","2021-03-13 08:00","2021-03-24 17:00","연속"]
[562,"부산울산","북부산","양산산막#2 T/L","20-21년 북부산전력지사 가공송전정비회사 총액공사","154kV 언양-산막#2T/L 추락방지장치 설치","2021-03-13 08:00","2021-03-14 17:00","2021-03-13 08:00","2021-03-14 17:00","연속"]
[563,"부산울산","북부산","양산산막#1 T/L","20-21년 북부산전력지사 가공송전정비회사 총액공사","154kV 언양-산막#1T/L 추락방지장치 설치","2021-03-13 08:00","2021-03-14 17:00","2021-03-13 08:00","2021-03-14 17:00","연속"]
[564,"부산울산","북부산","서창산막#2 T/L","20-21년 북부산전력지사 가공송전정비회사 총액공사","154kV 서창-산막#2T/L 추락방지장치 설치, 60, 70, 71, 72호","2021-03-06 08:00","2021-03-07 17:00","2021-03-06 08:00","2021-03-07 17:00","연속"]
[565,"부산울산","북부산","서창산막#2 T/L","20-21년 북부산전력지사 가공송전정비회사 총액공사","154kV 서창-산막#1T/L 추락방지장치 설치를 위한 안전이격휴전","2021-03-27 08:00","2021-03-28 17:00","취소","취소","연속"]
[566,"부산울산","북부산","언양산막#2 T/L","20-21년 북부산전력지사 가공송전정비회사 총액공사","154kV 서창-산막#1T/L 추락방지장치 설치를 위한 안전이격휴전 67, 70, 71, 72호","2021-03-27 08:00","2021-03-28 17:00","취소","취소","연속"]
[567,"부산울산","북부산","서창산막#1 T/L","20-21년 북부산전력지사 가공송전정비회사 총액공사","154kV 서창-산막#1T/L 추락방지장치 설치","2021-03-27 08:00","2021-03-28 17:00","취소","취소","연속"]
[568,"부산울산","북부산","언양산막#2 T/L","20-21년 북부산전력지사 가공송전정비회사 총액공사","154kV 언양-산막#2T/L 96년 상반기 이전 성능저하 애자교체공사, 추락방지장치 설치, 4-73호(총 7기)","2021-03-04 08:00","2021-03-12 17:00",{"$f":"G572","v":"2021-03-04 08:00"},{"$f":"H572","v":"2021-03-12 17:00"},"연속"]
[569,"부산울산","북부산","서창산막#1 T/L","20-21년 북부산전력지사 가공송전정비회사 총액공사","154kV 서창-산막#2T/L 추락방지장치 설치를 위한 안전이격휴전","2021-03-06 08:00","2021-03-07 17:00","취소","취소","연속"]
[570,"부산울산","북부산","양산삼랑진PP T/L","20-21년 북부산전력지사 가공송전정비회사 총액공사","154kV 양산-삼랑진T/L 애자교체공사 및 추락방지장치 설치","2021-03-29 08:00","2021-04-01 17:00","취소","취소","연속"]
[571,"부산울산","북부산","엄궁학장#1 T/L","20-21 북부산전력지사 변전 총액공사","엄궁S/S 154kV 엄궁-학장#1T/L 차단기 동작시험","2021-03-22 10:00","2021-03-22 17:00",{"$f":"G575","v":"2021-03-22 10:00"},"2021-03-22 17:00","연속"]
[572,"부산울산","북부산","엄궁학장#2 T/L","20-21 북부산전력지사 변전 총액공사","엄궁S/S 154kV 엄궁-학장#2T/L 차단기 동작시험","2021-03-22 10:00","2021-03-22 17:00","2021-03-22 10:00","2021-03-22 17:00","연속"]
[573,"부산울산","북부산","모라엄궁#1 T/L","20-21 북부산전력지사 변전 총액공사","엄궁S/S 154kV 모라-엄궁#1T/L 차단기 동작시험","2021-03-23 10:00","2021-03-23 13:00","2021-03-23 10:00","2021-03-23 13:00","연속"]
[574,"부산울산","북부산","호포물금 T/L","20-21 북부산전력지사 변전 총액공사","호포S/S 154kV 호포-물금T/L GIS 보통점검","2021-03-03 10:00","2021-03-03 18:00","2021-03-03 10:00","2021-03-03 18:00","연속"]
[575,"부산울산","울산","남울산처용#1 T/L","20-21년 변전정비회사 총액공사","- GIS 하자점검","2021-03-16 09:00","2021-03-16 18:00","2021-03-16 09:00","2021-03-16 18:00","연속"]
[576,"부산울산","울산","남울산처용#2 T/L","345kV 신울산복합-북부산T/L 건설공사","- 작업내용 : 345kV 신울산복합-북부산T/L 점퍼취부(안전이격)","2021-03-17 07:00","2021-03-17 18:00","2021-03-17 07:00","2021-03-17 18:00","연속"]
[577,"부산울산","울산","동울산방어진 T/L","154kV 동울산-방어진T/L 피뢰기 설치공사","154kV 동울산-방어진T/L No.39,40 피뢰기 설치공사","2021-03-20 07:00","2021-03-21 18:00","2021-03-20 07:00","2021-03-21 18:00","연속"]
[578,"부산울산","울산","두왕영남TP#1 T/L","울산S/S 154kV SW 증설공사","○ 울산-영남T/P #1T/L 전력케이블 포설 및 접속(남부건설본부 지중건설부) ○ 두왕-울산#1T/L, 울산-영남T/P #1T/L 보호반 이설(설비보강부) ○ 울산-울산T/P #1T/L 전력케이블 선종교체(설비보강부) ○ 두왕-울산#1T/L, 울산-영남T/P #1T/L 최초가압 및 실부하가압(설비보강부)","2021-03-02 07:00","2021-04-09 18:00","2021-03-02 07:00","2021-04-09 18:00","연속"]
[579,"부산울산","울산","방어진영남TP#1 T/L","154㎸ 방어진-영남TP#1T/L OPGW 교체공사","154㎸ 방어진-영남TP#1T/L OPGW 5.686㎞(120SQ/24C) 시설, C/H↔ICT실간 비금속광케이블 0.79㎞ 등 부대설비 1식","2021-03-06 07:00","2021-03-07 18:00","2021-03-06 07:00","2021-03-07 18:00","연속"]
[580,"부산울산","울산","신울산S/S 154kV T BUS TIE CB 6400","신울산S/S 154kV 현대화공사","TR-BUS DS(6408) 철거","2021-03-08 09:30","2021-03-09 17:00","2021-03-08 09:30","2021-03-09 17:00","연속"]
[581,"부산울산","울산","신울산언양#1 T/L","철탑 추락방지장치 설치공사","추락방지장치 와이어형(수직,수평) 설치공사 - 구간 : 154kV 신울산-언양T/L No.66,66-1 / 64,65,67 추가시공","2021-03-29 07:00","2021-03-30 18:00","2021-03-29 07:00","2021-03-30 18:00","연속"]
[582,"부산울산","울산","신울산언양#2 T/L","철탑 추락방지장치 설치공사","추락방지장치 와이어형(수직,수평) 설치공사 - 구간 : 154kV 신울산-언양T/L No.66,66-1 / 64,65,67 추가시공","2021-03-31 07:00","2021-04-01 18:00","2021-03-31 07:00","2021-04-01 18:00","연속"]
[583,"부산울산","울산","옥동외동#2 T/L","2021년 울산전력지사 송전철탑 추락방지시설 설치공사","154kV 외동-외동T/L 추락방지지설 설치 : 28기 병행 : 2021년 가공송전 순시점검 위탁공사(정밀점검)","2021-03-12 08:00","2021-03-17 18:00","2021-03-12 08:00","2021-03-17 18:00","연속"]
[584,"부산울산","울산","옥동외동#2 T/L","2020-21년도 송전정비회사 총액공사","① 96년 상반기 이전 성능저하 국산애자 교체 (21.03.26 07:00 ~ 13:00) - 작업구간 : 154kV 신울산-태화#2T/L No. 4, 30 - [안전이격] 154kV외동-옥동#1,2T/L ② 태풍관련 조치사항 상간스페이서 설치 (21.03.26 13:00 ~ 18:00) - 작업구간 : 154kV 신울산-태화#1 No.29~30, 외동-옥동#2T/L No.6~7 - [안전이격] 154kV 신울산-태화#2, 외동-옥동#1T/L ※특이사항 : 3회선 휴전작업 후 4회선 휴전","2021-03-26 07:00","2021-03-26 18:00","2021-03-26 07:00","2021-03-26 18:00","연속"]
[585,"부산울산","울산","옥동외동#1 T/L","2021년 울산전력지사 송전철탑 추락방지시설 설치공사","154kV 외동-외동T/L 추락방지지설 설치 : 28기 병행 : 2021년 가공송전 순시점검 위탁공사(정밀점검)","2021-03-22 08:00","2021-03-27 18:00","2021-03-22 08:00","2021-03-27 18:00","연속"]
[586,"부산울산","울산","신온산온산#3 T/L","21년 상반기 154kV GIS 정밀점검 공사","- GIS 정밀점검","2021-03-15 09:00","2021-03-16 18:00","2021-03-15 09:00","2021-03-16 18:00","연속"]
[587,"부산울산","울산","신온산온산#1 T/L","21년 상반기 154kV GIS 정밀점검 공사","- GIS 정밀점검관련 시험가압1H","2021-03-18 17:00","2021-03-18 18:00","2021-03-18 17:00","2021-03-18 18:00","연속"]
[588,"부산울산","울산","신온산온산#2 T/L","21년 상반기 154kV GIS 정밀점검 공사","- GIS 정밀점검","2021-03-10 09:00","2021-03-11 18:00","2021-03-10 09:00","2021-03-11 18:00","연속"]
[589,"부산울산","울산","신온산온산#1 T/L","21년 상반기 154kV GIS 정밀점검 공사","- GIS 정밀점검","2021-03-08 09:00","2021-03-09 18:00","2021-03-08 09:00","2021-03-09 18:00","연속"]
[590,"부산울산","울산","용연울산TP#2 T/L","20-21년 변전정비회사 총액공사","- 송전선로 보호반 대체 - 용연)GIS 하자점검(성현)- - 용연)LA 보통점검 - 울산TP)GIS 초기점검 - 용연)가스배관 구조 변경(모선휴전필요함) - 최원재 과장님 PITR 정기시험 병행","2021-03-08 09:00","2021-03-10 18:00","2021-03-08 09:00","2021-03-10 18:00","연속"]
[591,"부산울산","울산","용연울산TP#1 T/L","20-21년 변전정비회사 총액공사","- 송전선로 보호반 대체","2021-03-29 09:00","2021-03-31 18:00","2021-03-29 09:00","2021-03-31 18:00","연속"]
[592,"부산울산","울산","용연울산TP#3 T/L","345kV 북부산-울산TPT/L 보조암 설치공사(안전이격)","태풍 고장 관련 345kV 북부산-울산TPT/L 보조암 설치 - 공사구간 : 4호 - 특이사항 : 남부건설본부 345kV 북부산-울산TPT/L 휴전일정과 병행 - 병가구간 : 용연-울산TP#3T/L 5호","2021-03-22 07:00","2021-03-25 18:00","2021-03-22 07:00","2021-03-25 18:00","연속"]
[593,"부산울산","울산","울산울산TP#1 T/L","울산S/S 154kV SW 증설공사","○ 울산-영남T/P #1T/L 전력케이블 포설 및 접속(남부건설본부 지중건설부) ○ 두왕-울산#1T/L, 울산-영남T/P #1T/L 보호반 이설(설비보강부) ○ 울산-울산T/P #1T/L 전력케이블 선종교체(설비보강부) ○ 두왕-울산#1T/L, 울산-영남T/P #1T/L 최초가압 및 실부하가압(설비보강부)","2021-03-02 07:00","2021-04-09 18:00","2021-03-02 07:00","2021-04-09 18:00","연속"]
[594,"부산울산","울산","울산울산TP#2 T/L","21년 상반기 154kV GIS 정밀점검 공사","- 울산S/S SK 에너지 NAC T/L 시험가압 1H","2021-03-26 17:00","2021-03-26 18:00","2021-03-26 17:00","2021-03-26 18:00","연속"]
[595,"부산울산","울산","울주직동#2 T/L","21년도 가공송전 순시점검 위탁공사","안전거리확보(345kV 울주-고리#1T/L 휴전관련)","2021-03-16 09:00","2021-03-19 18:00","2021-03-16 09:00","2021-03-19 18:00","연속"]
[596,"부산울산","울산","울주외동#2 T/L","2021년 울산전력지사 송전철탑 추락방지시설 설치공사","154kV 울주-외동T/L 추락방지지설 설치 : 44기 병행 : 2021년 가공송전 순시점검 위탁공사(정밀점검)","2021-03-18 08:00","2021-03-27 18:00","2021-03-18 08:00","2021-03-27 18:00","연속"]
[615,"부산울산","울산","울주입실#1 T/L","2021년 울산전력지사 송전철탑 추락방지시설 설치공사","154kV 울주-입실T/L 추락방지지설 설치 : 4기","2021-03-08 08:00","2021-03-09 18:00","2021-03-08 08:00","2021-03-09 18:00","연속"]
[616,"부산울산","울산","울주외동#1 T/L","2021년 울산전력지사 송전철탑 추락방지시설 설치공사","154kV 울주-외동T/L 추락방지지설 설치 : 44기 병행 : 2021년 가공송전 순시점검 위탁공사(정밀점검)","2021-03-08 08:00","2021-03-17 18:00","2021-03-08 08:00","2021-03-17 18:00","연속"]
[617,"부산울산","울산","울주직동#1 T/L","21년도 가공송전 순시점검 위탁공사","안전거리확보(345kV 울주-고리NP#2T/L 휴전관련)","2021-03-30 09:00","2021-04-02 18:00","2021-03-30 09:00","2021-04-02 18:00","연속"]
[618,"부산울산","울산","울주입실#2 T/L","2021년 울산전력지사 송전철탑 추락방지시설 설치공사","154kV 울주-입실T/L 추락방지지설 설치 : 4기","2021-03-18 08:00","2021-03-19 18:00","2021-03-18 08:00","2021-03-19 18:00","연속"]
[619,"부산울산","울산","웅촌서창#1 T/L","관내 변전소 태풍피해 외벽 복구공사","웅촌S/S 외벽 드라이비트 파손부 보수 및 교체 79.6㎡","2021-03-02 09:00","2021-03-05 18:00","2021-03-02 09:00","2021-03-05 18:00","매일"]
[620,"부산울산","울산","웅촌서창#2 T/L","2020-21년 울산전력지사 변전협력회사 총액공사","-송전선로 보호반 대체","2021-03-15 09:00","2021-03-17 18:00","2021-03-15 09:00","2021-03-17 18:00","연속"]
[621,"부산울산","직할","학장개금#2 T/L","20-21년 직할 변전정비회사 총액공사","개금S/S 학장-개금#1, 2T/L GIS 차단기 조작시험","2021-03-05 09:30","2021-03-05 18:00","2021-03-05 09:30","2021-03-05 18:00","연속"]
[622,"부산울산","직할","학장개금#1 T/L","20-21년 직할 변전정비회사 총액공사","개금S/S 학장-개금#1, 2T/L GIS 차단기 조작시험","2021-03-05 09:30","2021-03-05 18:00","2021-03-05 09:30","2021-03-05 18:00","연속"]
[623,"부산울산","직할","부산수정#2 T/L","20-21년 직할 변전정비회사 총액공사","부산-수정#2T/L 43CA OFF 오경보 조치 및 PITR 업데이트 부산-수정#2T/L GIS 차단기 조작시험","2021-03-09 09:30","2021-03-09 18:00","2021-03-09 09:30","2021-03-09 18:00","연속"]
[624,"부산울산","직할","부산수정#1 T/L","20-21년 직할 변전정비회사 총액공사","부산-수정#1T/L 43CA OFF 오경보 조치 및 PITR 업데이트 부산-수정#1T/L GIS 차단기 조작시험","2021-03-09 09:30","2021-03-09 18:00","2021-03-09 09:30","2021-03-09 18:00","연속"]
[625,"경남","함안","중리가야#1 T/L","154kV 중리-가야T/L 20,21,38호 안전이격확보공사","철탑교체(3기) 및 전력선 교체(19~23, 37~39호간)","2021-03-02 07:00","2021-03-08 18:00","취소","취소","연속"]
[626,"경남","진주","함양거창#1 T/L","154kV 함양-거창T/L C/H(1호) 특별점검","154kV 함양-거창T/L C/H(1호) 특별점검","2021-03-03 09:30","2021-03-03 11:30",{"$f":"G612","v":"2021-03-03 09:30"},"2021-03-03 11:30","연속"]
[627,"경남","진주","함양거창#2 T/L","154kV 함양-거창T/L C/H(1호) 특별점검","154kV 함양-거창T/L C/H(1호) 특별점검","2021-03-03 11:30","2021-03-03 13:00","2021-03-03 11:30","2021-03-03 13:00","연속"]
[628,"경남","진주","사봉개양#2 T/L","154kV 사봉-개양#2T/L 송전선로용 접근금지 위험표지판 설치","154kV 사봉-개양#2T/L 송전선로용 접근금지 위험표지판 설치","2021-03-06 08:30","2021-03-06 15:00","2021-03-06 08:30","2021-03-06 15:00","연속"]
[629,"경남","직할","창원S/S 154kV #60 BUS","창원S/S 154kV Sh.C 설치공사","○ 154kV Sh.C 2BANK 설치 ○ 154kV GIS 1CCT 구내이설 ○ 154kV GCB 4대 설치","취소","취소","취소","취소","연속"]
[630,"경남","함안","중리가야#2 T/L","154kV 중리-가야T/L 20,21,38호 안전이격확보공사","철탑교체(3기) 및 전력선교체(19~23,37~39호간)","2021-03-09 07:00","2021-03-13 18:00","취소","취소","연속"]
[631,"경남","직할","창원천선#1 T/L","창원S/S 154kV Sh.C 설치공사(시험가압선로)","○ 154kV Sh.C 2BANK 설치 ○ 154kV GIS 1CCT 구내이설 ○ 154kV GCB 4대 설치","취소","취소","취소","취소","연속"]
[632,"경남","직할","신김해S/S 154kV SEC CB 60610","신김해S/S 154kV 60-61SEC GIS 초기점검","신김해S/S 154kV 60-61SEC GIS 초기점검","취소","취소","취소","취소","연속"]
[633,"경남","직할","신김해S/S 154kV SEC CB 65660","신김해S/S 154kV 65-66SEC GIS 초기점검","신김해S/S 154kV 65-66SEC GIS 초기점검","취소","취소","취소","취소","연속"]
[634,"경남","함안","진영수산#1 T/L","수산S/S 154kV 진영-수산#1T/L GIS 하자점검","수산S/S 154kV 진영-수산#1T/L GIS 하자점검","2021-03-11 09:30","2021-03-11 17:30",{"$f":"G620","v":"2021-03-11 09:30"},"2021-03-11 17:30","연속"]
[635,"경남","함안","진영수산#2 T/L","수산S/S 154kV 진영-수산#2T/L GIS 하자점검","수산S/S 154kV 진영-수산#2T/L GIS 하자점검","2021-03-12 09:30","2021-03-12 17:30","2021-03-12 09:30","2021-03-12 17:30","연속"]
[636,"경남","진주","사천개양#1 T/L","154kV 사천-개양#1T/L 송전선로 정밀점검","154kV 사천-개양#1T/L 송전선로 정밀점검","2021-03-15 08:30","2021-03-19 17:00","2021-03-15 08:30","2021-03-19 17:00","매일"]
[637,"경남","직할","신월삼정#1 T/L","삼정S/S 신월-삼정#1T/L 하자점검","삼정S/S 신월-삼정#1T/L 하자점검","2021-03-15 09:30","2021-03-15 17:30","2021-03-15 09:30","2021-03-15 17:30","연속"]
[638,"경남","직할","신월삼정#2 T/L","삼정S/S 신월-삼정#2T/L 하자점검","삼정S/S 신월-삼정#2T/L 하자점검","2021-03-16 09:30","2021-03-16 17:30","2021-03-16 09:30","2021-03-16 17:30","연속"]
[639,"경남","직할","신김해삼정#1 T/L","신김해,삼정S/S 신김해-삼정#1T/L 하자점검","신김해,삼정S/S 신김해-삼정#1T/L 하자점검 (병행) 신김해S/S 신김해-삼정#1T/L PT,LA 보통점검","2021-03-17 09:30","2021-03-17 17:30","2021-03-17 09:30","2021-03-17 17:30","연속"]
[640,"경남","직할","신김해삼정#2 T/L","신김해,삼정S/S 신김해-삼정#2T/L 하자점검","신김해,삼정S/S 신김해-삼정#2T/L 하자점검","2021-03-18 09:30","2021-03-18 17:30","2021-03-18 09:30","2021-03-18 17:30","연속"]
[641,"경남","함안","신마산칠서#2 T/L","칠서S/S 154kV 신마산-칠서#2T/L GIS 초기점검","칠서S/S 154kV 신마산-칠서#2T/L GIS 초기점검 신마산S/S 154kV 신마산-칠서#2T/L GCB 조작시험","취소","취소","취소","취소","연속"]
[642,"경남","진주","의령동진주#1 T/L","154kV 의령-함양T/L 송전용 피뢰기 설치공사 안전이격거리 확보","154kV 의령-함양T/L 송전용 피뢰기 설치공사 안전이격거리 확보","2021-03-20 07:00","2021-03-20 12:00","취소","취소","연속"]
[643,"경남","진주","의령함양 T/L","154kV 의령-함양T/L 송전용 피뢰기 설치공사(2기)","154kV 의령-함양T/L 송전용 피뢰기 설치공사(2기)","2021-03-20 07:00","2021-03-20 12:00",{"$f":"G629","v":"2021-03-20 07:00"},{"$f":"H629","v":"2021-03-20 12:00"},"연속"]
[644,"경남","통영","신고성통영 T/L","154kV 신고성-통영T/L 피뢰기설치공사","154kV 신고성-통영T/L 피뢰기설치공사(79~113호)","2021-03-20 08:00","2021-03-21 18:00",{"$f":"G630","v":"2021-03-20 08:00"},{"$f":"H630","v":"2021-03-21 18:00"},"매일"]
[645,"경남","진주","의령동진주#2 T/L","154kV 의령-동진주#2T/L 송전용 피뢰기 설치공사(68기)","154kV 의령-동진주#2T/L 송전용 피뢰기 설치공사(68기)","2021-03-20 12:00","2021-03-21 18:00","취소","취소","연속"]
[646,"경남","진주","사천개양#2 T/L","154kV 사천-개양#2T/L 송전선로 정밀점검","154kV 사천-개양#2T/L 송전선로 정밀점검","2021-03-22 08:30","2021-03-26 17:00",{"$f":"G632","v":"2021-03-22 08:30"},{"$f":"H632","v":"2021-03-26 17:00"},"매일"]
[647,"경남","진주","개양S/S 154kV CB 6100","개양S/S SPS보호반 대체공사","개양S/S SPS보호반 대체공사","2021-03-22 09:00","2021-03-24 18:00",{"$f":"G633","v":"2021-03-22 09:00"},{"$f":"H633","v":"2021-03-24 18:00"},"연속"]
[648,"경남","진주","의령동진주#2 T/L","154kV 의령-동진주#2T/L 송전용 피뢰기 설치공사(68기)","154kV 의령-동진주#2T/L 송전용 피뢰기 설치공사(68기)","2021-03-27 07:00","2021-03-28 18:00","취소","취소","연속"]
[649,"경남","통영","신고성통영 T/L","154kV 신고성-통영T/L 피뢰기설치공사","154kV 신고성-통영T/L 피뢰기설치공사(114~149호)","2021-03-27 08:00","2021-03-28 18:00",{"$f":"G635","v":"2021-03-27 08:00"},{"$f":"H635","v":"2021-03-28 18:00"},"매일"]
[650,"경남","통영","신고성삼천포#2 T/L","신고성-삼천포#2T/L 보호반 대체","1. 신고성S/S 신고성-삼천포 #2T/L 보호반 대체 2. 삼천포S/S 신고성-삼천포 #2T/L 보호반 대체","2021-03-29 09:00","2021-04-02 18:00",{"$f":"G636","v":"2021-03-29 09:00"},{"$f":"H636","v":"2021-04-02 18:00"},"연속"]
[651,"강원","직할","화천화천HP#1 T/L","화천HP 보호배전반 이설공사","외장재 대체","2021-03-25 09:00","2021-03-25 18:00","2021-03-25 09:00","2021-03-25 18:00","매일"]
[652,"강원","직할","화천화천HP#2 T/L","화천HP 보호배전반 이설공사","외장재 대체","2021-03-24 09:00","2021-03-24 18:00","2021-03-24 09:00","2021-03-24 18:00","매일"]
[651,"광주전남","직할","신광주장성#1 T/L","피뢰기설치공사","피뢰기설치공사","2021-03-29 07:00","2021-03-31 18:00","2021-03-29 07:00","2021-03-31 18:00","매일"]