{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":16,"n_cols":11,"rows_kept":16,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2021년도 4월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #4 M.Tr","21년 신가평변전소 765kV GIS 정밀점검공사","85BAY 765kV GIS 정밀점검","2021-04-26 09:00","2021-05-14 18:00","취소","취소","연속"]
[2,"대전충남","서산","당진T/P CB 8900","21년 서산P/O 345/765KV GIS 정밀점검공사","당진화력S/S 765kV 9호기 1차-10호기 1차 TIE GIS(8900) 보통점검","2021-04-19 10:00","2021-04-21 18:00","취소","취소","연속"]
[3,"대전충남","서산","당진T/P CB 8971","21년 서산P/O 345/765KV GIS 정밀점검공사","당진화력S/S 765kV 10호기 1차 GIS (8971) 보통점검","2021-04-26 10:00","2021-04-28 18:00","취소","취소","연속"]
[4,"대전충남","서산","당진T/P CB 8171","21년 서산P/O 765kV GIS 정밀점검공사","당진화력S/S 765kV #1 Tie.Tr 1차 GIS(8171) 정밀점검","2021-04-19 10:00","2021-04-30 18:00","2021-04-12 10:00","2021-04-16 18:00","연속"]
[5,"대전충남","서산","당진T/P CB 8500","21년 서산P/O 345/765KV GIS 정밀점검공사","당진화력S/S 765kV 5호기 1차-6호기 1차 TIE GIS(8500) 보통점검","2021-04-05 10:00","2021-04-07 18:00","취소","취소","연속"]
[6,"대전충남","서산","신서산신중부#1 T/L","[송전] 765kV 신서산-신중부T/L 항공구 교체공사","765kV 신서산-신중부T/L 98~99호 항공구 교체","2021-04-29 08:00","2021-04-29 18:00","취소","취소","연속"]
[7,"대전충남","서산","신서산신중부#2 T/L","[21년 가공송전 순시점검 위탁공사] 정밀점검","765kV 신서산-신중부#2T/L 정밀점검 - No.1~169(169기)","2021-04-19 08:00","2021-04-28 18:00","취소","취소","매일"]
[8,"부산울산","동부산","신고리N/P CB 8600","신고리 5,6호기 접속설비공사","8672CB, 8662DS, 8602DS, 8622DS 설치","2021-04-06 09:00","2021-06-30 18:00","2021-04-19 09:00","2021-06-30 18:00","연속"]
[9,"부산울산","동부산","신고리N/P #3 Tie-Tr","신고리S/S 765kV M.Tr 보통점검","신고리S/S 765kV M.Tr 보통점검(#3M.Tr)","2021-04-05 09:00","2021-04-09 18:00","2021-04-05 09:00","2021-04-09 18:00","연속"]
[10,"부산울산","동부산","신고리N/P #2호기 주변압기 CB 8171, 8100","신고리 2호기 6차 계획예방정비","전력용변압기 일반점검 및 구내 선로 점검, 보호계전기 시험 등","2021-04-25 09:00","2021-05-18 18:00","2021-04-25 09:00","2021-05-18 18:00","연속"]
[11,"대전충남","서산","당진T/P #9호기 주변압기 CB 8900, 8972","○  9,10호기 Common Outage","○ 9,10호기 Common Outage(21.04.19(월) ~ ’21.04.29(목)) 중 10호기 주변압기 복전 후, 9호기 '21.04.19(월) 11시~'21.04.26(월) 16시 정전 - 9,10호기 역률개선장치 전기실 및 예비 보조변압기 안착","2021-04-19 11:00","2021-04-26 16:00","2021-04-19 11:00","2021-04-26 16:00","연속"]
[12,"대전충남","서산","당진T/P #10호기 주변압기 CB 8900, 8971","○  10호기 계획예방정비공사(B급)","○ 10호기 계획예방정비공사(21.03.13(토) 00시 ~ ’21.06.11(금) 24시) 중 9호기 주변압기 복전 후, '21.04.26(월) 17시 ~ '21.06.03(목) 10시 정전 - 전력용변압기 정비, 갑종보호계전기 시험 등","2021-04-26 17:00","2021-06-03 10:00","2021-04-26 17:00","2021-06-03 10:00","연속"]

{"sheet":"345설비","index":1,"n_rows":244,"n_cols":11,"rows_kept":244,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2021년도 4월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","영등포","신광명S/S 345kV #70 BUS","345kV 신광명S/S GIS 용량대체공사","63kA GIS 설치 및 대체","2021-04-24 10:00","2021-04-29 10:00","2021-04-24 10:00","2021-04-29 10:00","연속"]
[2,"남서울","영등포","신광명영등포#2 T/L","345kV 신광명S/S GIS 용량대체공사","63kA GIS 설치 및 대체","2021-04-28 10:00","2021-04-29 10:00","2021-04-28 10:00","2021-04-29 10:00","연속"]
[3,"남서울","영등포","신광명S/S #4 M.Tr","신광명S/S 345kV 7322 DS 동작불량 정비 및 절연보강","7322 DS 동작불량 정비, 3차측 절연보강, 7300, 7372 조작 등","2021-04-05 09:00","2021-04-07 18:00","2021-04-05 09:00","2021-04-07 18:00","연속"]
[4,"남서울","영등포","신광명S/S 345kV #75 BUS","345kV 신광명S/S GIS 용량대체공사","63kA GIS 설치 및 대체","2021-04-19 10:00","2021-04-24 10:00","2021-04-29 10:00","2021-05-04 10:00","연속"]
[5,"남서울","영등포","신광명영등포#1 T/L","345kV 신광명S/S GIS 용량대체공사","63kA GIS 설치 및 대체","2021-04-23 10:00","2021-04-24 10:00","2021-05-03 10:00","2021-05-04 10:00","연속"]
[6,"남서울","직할","영등포S/S 345kV #70 BUS","345kV 신광명S/S GIS 용량대체공사","무부하가압용 선로 휴전 사전조치차","2021-04-28 10:00","2021-04-29 10:00","2021-04-28 10:00","2021-04-29 10:00","연속"]
[7,"남서울","직할","영등포S/S 345kV #70 BUS","345kV 신광명S/S GIS 용량대체공사","무부하가압용 선로 휴전 사전조치차","2021-04-23 10:00","2021-04-24 10:00","2021-05-03 10:00","2021-05-04 10:00","연속"]
[8,"남서울","직할","영등포S/S #2 M.Tr","영등포S/S RTU 접지관련 보수","영등포S/S RTU 접지경보관련 해소 작업","2021-04-06 10:00","2021-04-06 18:00","2021-04-06 10:00","2021-04-06 18:00","연속"]
[9,"남서울","동서울","신용인동서울#2 T/L","동서울S/S 신용인-동서울#2T/L 362kV GIS 개폐장치 정밀점검","362kV GIS 개폐장치 정밀점검","2021-04-20 09:00","2021-04-28 18:00","2021-04-22 09:00","2021-04-30 18:00","연속"]
[10,"인천","김포","가정개폐소 CB 7600","가정개폐소 345kV #1 Sh.R TIE GIS 보통점검","가정개폐소 345kV #1 Sh.R TIE (7600CB) GIS 보통점검","2021-04-15 10:00","2021-04-15 18:00","2021-04-15 10:00","2021-04-15 18:00","연속"]
[11,"인천","김포","가정개폐소 CB 7471","가정개폐소 345kV 가정-인천CC#1T/L GIS 유압게이지 교체","가정개폐소 345kV 가정-인천CC#1T/L (7471CB) GIS A상 유압게이지 교체작업","2021-04-16 10:00","2021-04-16 18:00","2021-04-16 10:00","2021-04-16 18:00","연속"]
[12,"인천","김포","가정개폐소 CB 7500","가정개폐소 345kV 신가좌-가정#1T/L TIE GIS 보통점검","가정개폐소 345kV 신가좌-가정#1T/L TIE (7500CB) GIS 보통점검","2021-04-14 10:00","2021-04-14 18:00","2021-04-14 10:00","2021-04-14 18:00","연속"]
[13,"인천","김포","가정개폐소 CB 7571","가정개폐소 345kV 신가좌-가정#1T/L GIS 보통점검","가정개폐소 345kV 신가좌-가정#1T/L (7571CB) GIS 보통점검","2021-04-13 10:00","2021-04-13 18:00","2021-04-13 10:00","2021-04-13 18:00","연속"]
[14,"인천","김포","가정개폐소 CB 7472","가정개폐소 345kV 가정-갈산#1T/L GIS 보통점검","가정개폐소 345kV 가정-갈산#1T/L (7472CB) GIS 보통점검","2021-04-12 10:00","2021-04-12 18:00","2021-04-12 10:00","2021-04-12 18:00","연속"]
[15,"인천","김포","가정개폐소 CB 7400","가정개폐소 345kV 가정-갈산#1T/L TIE GIS 보통점검","가정개폐소 345kV 가정-갈산#1T/L TIE (7400CB) GIS 보통점검","2021-04-09 10:00","2021-04-09 18:00","2021-04-09 10:00","2021-04-09 18:00","연속"]
[16,"인천","김포","가정개폐소 CB 7200","가정개폐소 345kV 가정-갈산#3T/L TIE GIS 보통점검","가정개폐소 345kV 가정-갈산#3T/L TIE (7200CB) GIS 보통점검","2021-04-08 10:00","2021-04-08 18:00","2021-04-08 10:00","2021-04-08 18:00","연속"]
[17,"인천","김포","가정개폐소 CB 7271","가정개폐소 345kV 가정-인천CC#2T/L GIS 보통점검","가정개폐소 345kV 가정-인천CC#2T/L(7271CB) GIS 보통점검","2021-04-07 10:00","2021-04-07 18:00","2021-04-07 10:00","2021-04-07 18:00","연속"]
[18,"인천","김포","신김포S/S #3 Sh.R CB","신김포S/S 345kV #3Sh.R 1차 GIS 개폐제어기 설치공사","신김포S/S 345kV #3Sh.R 1차(7671CB) GIS 개폐제어기 설치공사","2021-04-19 09:00","2021-04-23 18:00","2021-04-19 09:00","2021-04-23 18:00","연속"]
[19,"인천","김포","신김포S/S #4 Sh.R CB","신김포S/S 345kV #4Sh.R 1차 GIS 개폐제어기 설치공사","신김포S/S 345kV #4Sh.R 1차(7272CB) GIS 개폐제어기 설치공사","2021-04-12 09:00","2021-04-16 18:00","2021-04-12 09:00","2021-04-16 18:00","연속"]
[20,"인천","김포","신김포S/S #2 Sh.R CB","신김포S/S 345kV #2Sh.R 1차 GIS 개폐제어기 설치공사","신김포S/S 345kV #2Sh.R 1차(7271CB) GIS 개폐제어기 설치공사","2021-04-05 09:00","2021-04-09 18:00","2021-04-05 09:00","2021-04-09 18:00","연속"]
[21,"인천","부평","서인천C/C CB 7100","서인천S/Y 345kV 7100 GIS 조작시험","서인천S/Y 345kV 7100 GIS 조작시험","2021-04-07 13:00","2021-04-07 18:00","2021-04-07 13:00","2021-04-07 18:00","연속"]
[22,"인천","부평","서인천C/C CB 7171","서인천S/Y 345kV 7171 GIS 조작시험","서인천S/Y 345kV 7171 GIS 조작시험","2021-04-07 09:00","2021-04-07 13:00","2021-04-07 09:00","2021-04-07 13:00","연속"]
[23,"인천","부평","서인천CC신인천CC#2 T/L","서인천S/Y 345kV 7577 GIS 하자점검","서인천S/Y 345kV 7577 GIS 하자점검","2021-04-05 09:00","2021-04-05 13:00","2021-04-05 09:00","2021-04-05 18:00","연속"]
[24,"인천","부평","서인천C/C #2 Sh.R CB","서인천S/Y 345kV 7479 GIS 조작시험","서인천S/Y 345kV 7479 GIS 조작시험","2021-04-16 13:00","2021-04-16 18:00","2021-04-16 13:00","2021-04-16 18:00","연속"]
[25,"인천","부평","서인천CC신인천CC#2 T/L","서인천S/Y 345kV 7777 GIS 하자점검","서인천S/Y 345kV 7777 GIS 하자점검","2021-04-05 13:00","2021-04-05 18:00","취소","취소","연속"]
[26,"인천","부평","서인천CC신인천CC#1 T/L","서인천S/Y 345kV 7077 GIS 하자점검","서인천S/Y 345kV 7077 GIS 하자점검","2021-04-09 09:00","2021-04-09 13:00","2021-04-09 09:00","2021-04-09 18:00","연속"]
[27,"인천","부평","서인천CC신인천CC#1 T/L","서인천S/Y 345kV 7277 GIS 하자점검","서인천S/Y 345kV 7277 GIS 하자점검","2021-04-09 13:00","2021-04-09 18:00","취소","취소","연속"]
[28,"인천","부평","서인천C/C CB 7172","서인천S/Y 345kV 7172 GIS 조작시험","서인천S/Y 345kV 7172 GIS 조작시험","2021-04-12 09:00","2021-04-12 18:00","2021-04-12 09:00","2021-04-12 18:00","연속"]
[29,"인천","부평","서인천C/C #1 Sh.R CB","서인천S/Y 345kV 7379 GIS 조작시험","서인천S/Y 345kV 7379 GIS 조작시험","2021-04-16 09:00","2021-04-16 13:00","2021-04-16 09:00","2021-04-16 13:00","연속"]
[30,"인천","부평","신가좌S/S #2 M.Tr","신가좌S/S #2M.Tr 보통점검 및 Sh.R, GIS 휴전작업","신가좌S/S #2M.Tr 보통점검, 1,2,3차 LA 보통점검 #2S.Tr 보통점검 7372 GIS 초기점검, 6244 GIS 조작시험 2-1,2 Sh.R 보통점검, 2-3Sh.R 하자점검 2-1,2,3 VCB 조작시험","2021-04-19 09:00","2021-04-23 18:00","2021-04-19 09:00","2021-04-23 18:00","연속"]
[31,"인천","부평","신경서S/S #1 M.Tr","신경서S/S #1M.Tr 보통점검","신경서S/S #1M.Tr 보통점검 1,2차 LA 보통점검 7100, 7172 GIS 조작시험 4189 GIS 보통점검 #1S.Tr 보통점검(절연유채유 및 분석)","2021-04-26 09:00","2021-04-28 18:00","2021-04-26 09:00","2021-04-28 18:00","연속"]
[32,"인천","부평","신경서포스코CC#1 T/L","345kV 신경서-포스코SY T/L DTS 보수공사","#1T/L 포스코EBG 종단접속함 DTS 보수","2021-04-05 09:00","2021-04-13 18:00","2021-04-05 09:00","2021-04-13 18:00","연속"]
[33,"인천","시흥","신시흥#1S/S #3 M.Tr","신시흥#1S/S 154kV 신시흥남동#2T/L GIS대체(#3M.Tr)","신시흥#1S/S 154kV 신시흥남동#2T/L GIS대체(#3M.Tr)","2021-04-18 18:00","2021-04-19 18:00","2021-04-18 18:00","2021-04-19 18:00","연속"]
[34,"인천","시흥","신시흥#1S/S #3 M.Tr","신시흥#1S/S 154kV 신시흥남동#2T/L GIS대체(#3M.Tr)","신시흥#1S/S 154kV 신시흥남동#2T/L GIS대체(#3M.Tr)","2021-04-14 17:00","2021-04-14 18:00","2021-04-14 17:00","2021-04-14 18:00","연속"]
[35,"인천","시흥","영흥1TP영흥2TP#1 T/L","영흥#2T/P 345kV 영흥TP연락#1T/L GIS 조작시험","영흥#2T/P 345kV 영흥TP연락#1T/L GIS 조작시험","2021-04-06 10:00","2021-04-06 18:00","2021-04-06 10:00","2021-04-06 18:00","연속"]
[36,"인천","시흥","영흥T/P CB 7800","영흥#2T/P 345kV 신시흥-영흥TP#1T/L TIE GIS 조작시험","영흥#2T/P 345kV 신시흥-영흥TP#1T/L TIE GIS 조작시험","2021-04-01 14:00","2021-04-01 18:00","2021-04-01 14:00","2021-04-01 18:00","연속"]
[37,"인천","시흥","영흥T/P CB 7871","영흥#2T/P 345kV 신시흥-영흥TP#1T/L GIS 조작시험","영흥#2T/P 345kV 신시흥-영흥TP#1T/L GIS 조작시험","2021-04-01 10:00","2021-04-01 14:00","2021-04-01 10:00","2021-04-01 14:00","연속"]
[38,"인천","시흥","영흥T/P CB 7500","영흥T/P 345kV 7500 GIS 보통점검","영흥T/P 345kV 신시흥-영흥TP#4T/L-#4G.Tr TIE GIS(7500) 보통점검","2021-04-13 10:00","2021-04-13 18:00","2021-04-13 10:00","2021-04-13 18:00","연속"]
[39,"경기북부","구리","신가평포천LNGCC#1 T/L","2021년 345kV GIS 보통점검","2021년 345kV GIS 보통점검","2021-04-01 09:00","2021-04-01 18:00","2021-04-01 09:00","2021-04-01 18:00","연속"]
[40,"경기북부","직할","신파주양주#1 T/L","양주변전소 옥외철구 GIS화 공사","배전반 및 감시제어시스템 이설(모자이크 → SA)","2021-04-01 09:00","2021-04-07 18:00","2021-04-01 09:00","2021-04-07 18:00","연속"]
[41,"경기북부","구리","신포천포천LNGCC#1 T/L","2021년 345kV GIS 보통점검","2021년 345kV GIS 보통점검","2021-04-02 09:00","2021-04-02 18:00","2021-04-02 09:00","2021-04-02 18:00","연속"]
[42,"경기북부","구리","신가평미금#1 T/L","20~21년 구리전력지사 변전정비회사 총액공사","장기사용 배전반 교체공사 - 345kV 신가평-미금#1T/L보호반 교체","2021-04-05 09:00","2021-04-14 18:00","2021-04-05 09:00","2021-04-14 18:00","연속"]
[43,"경기북부","구리","포천천연복합S/S #1 G.Tr CB","2021년 345kV GIS 보통점검","2021년 345kV GIS 보통점검","2021-04-06 09:00","2021-04-06 18:00","2021-04-06 09:00","2021-04-06 18:00","연속"]
[44,"경기북부","고양","신덕은S/S #3 M.Tr","21년 고양P/O 변전정비회사 총액공사","유펌프 회로보완 #3M.Tr 1차(7371,7300) GIS 보통점검","2021-04-08 09:00","2021-04-09 18:00","2021-04-08 09:00","2021-04-09 18:00","연속"]
[45,"경기북부","직할","양주중부#1 T/L","345kV 양주-중부T/L 자기애관 교체공사","345kV 양주-중부T/L 9, 10호C/H 자기애관 교체공사 1. 접지 및 비계설치 작업준비 2. 애관해체 3. 애관 조립 및 주유 4. 비계해체 및 현장정리 5. 무부하 가압","2021-04-12 09:00","2021-04-25 18:00","2021-04-12 09:00","2021-04-25 18:00","연속"]
[46,"경기북부","직할","신의정부미금#2 T/L","2020~2021년 경기북부직할 가공송전 정비회사 총액공사","154kV 송전용 피뢰기 설치 상단 병가선로","2021-04-15 07:30","2021-04-15 18:00","2021-04-15 07:30","2021-04-15 18:00","연속"]
[47,"경기북부","구리","미금S/S CB 7371","`20~21 구리전력 변전정비 총액공사","미금S/S 7371 차단기 개폐타임 측정","2021-04-16 09:00","2021-04-16 14:00","취소","취소","연속"]
[48,"경기북부","고양","신파주신덕은#1 T/L","'20~'21년 고양전력지사 변전정비회사 총액공사","71BAY B/F 보호반 교체공사","2021-04-19 09:00","2021-04-23 18:00","2021-04-19 09:00","2021-04-23 18:00","연속"]
[49,"경기북부","고양","신덕은S/S CB 7100","'20~'21년 고양전력지사 변전정비회사 총액공사","71BAY B/F 보호반 교체공사","2021-04-19 09:00","2021-04-23 18:00","취소","취소","연속"]
[50,"경기북부","고양","신덕은S/S #1 M.Tr","'20~'21년 고양전력지사 변전정비회사 총액공사","71BAY B/F 보호반 교체공사","2021-04-19 09:00","2021-04-23 18:00","2021-04-19 09:00","2021-04-23 18:00","연속"]
[51,"경기북부","구리","미금S/S #2 M.Tr","20~21년 구리전력지사 변전정비회사 총액공사","장기사용 배전반 교체공사 - 미금S/S 345kV #73BAY B/F보호반 교체","2021-04-19 09:00","2021-04-23 18:00","2021-04-26 09:00","2021-04-30 18:00","연속"]
[52,"경기북부","구리","동서울미금#1 T/L","20~21년 구리전력지사 변전정비회사 총액공사","장기사용 배전반 교체공사 - 미금S/S 345kV #73BAY B/F보호반 교체","2021-04-19 09:00","2021-04-23 18:00","2021-04-26 09:00","2021-04-30 18:00","연속"]
[53,"경기북부","구리","미금S/S CB 7271","미금S/S 감시제어설비 교체공사","미금-성동#2T/L GIS(7271CB,DS) 관련 감시제어케이블 교체","2021-04-19 09:00","2021-04-23 18:00","2021-04-19 09:00","2021-04-23 18:00","연속"]
[54,"경기북부","구리","신가평S/S #4 Sh.R CB","신가평변전소 345kV #4SH.R 내부점검","신가평변전소 345kV #4SH.R 내부점검","2021-04-19 09:00","2021-04-23 18:00","2021-04-22 09:00","2021-04-22 18:00","연속"]
[55,"경기북부","구리","미금S/S 345kV #75 BUS","미금성동#3T/L 7552DS 가스누기 보수","미금성동#3T/L 7552DS 가스누기 보수","2021-04-26 09:00","2021-04-30 18:00","취소","취소","연속"]
[56,"경기북부","구리","미금S/S CB 7500","`20~21 구리전력 변전정비 총액공사","미금S/S 7500 차단기 개폐타임 측정","2021-04-26 09:00","2021-04-26 14:00","취소","취소","연속"]
[57,"경기북부","구리","신가평S/S #3 Sh.R CB","신가평변전소 345kV #3Sh.R 내부점검","신가평변전소 345kV #3SH.R 내부점검","2021-04-26 09:00","2021-04-30 18:00","2021-04-26 09:00","2021-04-30 18:00","연속"]
[58,"경기북부","구리","신포천S/S #2 M.Tr","신포천S/S #2M.Tr 내부점검공사","신포천S/S #2M.Tr 요주의II 에 따른 내부점검공사","2021-04-26 09:00","2021-04-30 18:00","취소","취소","연속"]
[59,"경기북부","직할","양주중부#2 T/L","345kV 양주-중부T/L 자기애관 교체공사","345kV 양주-중부T/L 9, 10호C/H 자기애관 교체공사","2021-04-26 09:00","2021-05-09 18:00","2021-04-26 09:00","2021-05-09 18:00","연속"]
[60,"경기북부","구리","미금S/S CB 7600","`20~21 구리전력 변전정비 총액공사","미금S/S 7600 차단기 개폐타임 측정","2021-04-26 14:00","2021-04-26 18:00","취소","취소","연속"]
[61,"경기북부","구리","미금S/S CB 7671","`20~21 구리전력 변전정비 총액공사","미금S/S 7671 차단기 개폐타임 측정","2021-04-28 09:00","2021-04-28 14:00","취소","취소","연속"]
[62,"경기북부","구리","미금S/S CB 7272","`20~21 구리전력 변전정비 총액공사","미금S/S 345kV 7272 GIS 조작시험","2021-04-28 14:00","2021-04-28 18:00","2021-04-16 09:00","2021-04-16 14:00","연속"]
[63,"경기","군포","서서울#2S/S #6 M.Tr","서서울2SS #6M.Tr 3차 동대 과열보수","서서울2SS #6M.Tr 3차 동대 과열보수","2021-04-01 09:00","2021-04-01 18:00","2021-04-01 09:00","2021-04-01 18:00","연속"]
[64,"경기","군포","신안산S/S CB 7072","신안산S/S 7000, 7072 GIS 하자점검","신안산S/S 7000, 7072 GIS 하자점검","2021-04-12 14:00","2021-04-12 18:00","2021-04-12 14:00","2021-04-12 18:00","연속"]
[65,"경기","군포","신안산S/S CB 7000","신안산S/S 7000, 7072 GIS 하자점검","신안산S/S 7000, 7072 GIS 하자점검","2021-04-12 09:00","2021-04-12 14:00","2021-04-12 09:00","2021-04-12 14:00","연속"]
[66,"경기","동부","곤지암S/S #1 M.Tr","곤지암S/S 종합예방진단시스템 설치 공사","곤지암S/S 종합예방진단시스템 설치 공사","2021-04-05 09:00","2021-04-05 18:00","2021-04-05 09:00","2021-04-05 18:00","연속"]
[67,"경기","동부","곤지암S/S #4 M.Tr","곤지암S/S 종합예방진단시스템 설치 공사","곤지암S/S 종합예방진단시스템 설치 공사","2021-04-06 09:00","2021-04-06 18:00","2021-04-06 09:00","2021-04-06 18:00","연속"]
[68,"경기","성남","신성남S/S #5 M.Tr","2021년 성남전력 변전정비회사 총액공사","주변압기 누유보수 - 7600,7672 조작점검 - 1,2,3차 LA 보통점검 - 2차 GIS 조작점검 - 송유펌프 보수 - 부싱절연유 채유","2021-04-05 09:00","2021-04-09 18:00","2021-04-05 09:00","2021-04-09 18:00","연속"]
[69,"경기","성남","신성남S/S #2 M.Tr","2021년 성남전력 변전정비회사 총액공사","#2M.Tr 누유 보수 - 7200,7272 조작점검 - 2차 LA 보통점검 - 2차 GIS 하자점검 - 3차 LA 보통점검","2021-04-12 09:00","2021-04-16 18:00","2021-04-12 09:00","2021-04-16 18:00","연속"]
[70,"경기","성남","신수원S/S 345kV #1 BUS","345kV 신수원S/S GIS 용량대체공사(72Bay)","3CB 용량대체(63kA)","2021-04-01 09:00","2021-04-18 18:00","2021-04-01 09:00","2021-04-18 18:00","연속"]
[71,"경기","성남","신수원S/S #2 M.Tr","345kV 신수원S/S GIS 용량대체공사(72Bay)","3CB 용량대체(63kA)","2021-04-01 09:00","2021-06-11 18:00","2021-04-01 09:00","2021-06-11 18:00","연속"]
[72,"경기","성남","신안성신수원#2 T/L","345kV 신수원S/S GIS 용량대체공사(72Bay)","#70BUS 설치시 안전이격확보","2021-04-11 09:00","2021-04-11 18:00","2021-04-11 09:00","2021-04-11 18:00","연속"]
[73,"경기","성남","신안성신수원#2 T/L","345kV 신수원S/S GIS 용량대체공사(72Bay)","#70BUS 철거시 안전이격확보","2021-04-04 09:00","2021-04-04 18:00","2021-04-04 09:00","2021-04-04 18:00","연속"]
[74,"경기","성남","신안성신수원#2 T/L","345kV 신수원S/S GIS 용량대체공사(72Bay)","#70BUS 24시간 무부하 가압","2021-04-17 18:00","2021-04-18 18:00","2021-04-17 18:00","2021-04-18 18:00","연속"]
[75,"경기","성남","신안성신수원#1 T/L","345kV 신수원S/S GIS 용량대체공사(72Bay)","3CB 용량대체(63kA)","2021-04-01 09:00","2021-06-11 18:00","2021-04-01 09:00","2021-06-11 18:00","연속"]
[76,"경기","성남","신안성신성남#2 T/L","345kV 신용인-동서울T/L 지장철탑 이설공사(이천오산)","345kV 신용인-동서울T/L 7-1호 지장철탑 이설(요청자 시행 공사)","2021-04-15 08:00","2021-04-28 18:00","2021-04-11 08:00","2021-04-20 18:00","연속"]
[77,"경기","성남","신안성신성남#1 T/L","345kV 신용인-동서울T/L 지장철탑 이설공사(이천오산)","345kV 신용인-동서울T/L 7-1호 지장철탑 이설(요청자 시행 공사)","2021-04-01 08:00","2021-04-14 18:00","2021-04-01 13:00","2021-04-10 18:00","연속"]
[78,"경기","성남","신안성신용인#2 T/L","345kV 신안성-신용인#2T/L 스페이서댐퍼 점검 및 교체공사","345kV 신안성-신용인#2T/L 불량 스페이서댐퍼 점검 및 교체","2021-04-28 09:00","2021-04-28 18:00","취소","취소","연속"]
[79,"경기","성남","신용인S/S #4 M.Tr","2021년 성남전력 변전정비회사 총액공사","주변압기 하자점검 - CVT 설치 - 7800, 7872 하자점검 - 1,2차 LA 하자점검 - 2차 GIS 조작점검 - CT단자함 제작사하자보수","2021-04-07 09:00","2021-04-09 18:00","취소","취소","연속"]
[80,"경기","성남","신용인동서울#1 T/L","345kV 신용인-동서울T/L 지장철탑 이설공사(이천오산)","345kV 신용인-동서울T/L 7-1호 지장철탑 이설(요청자 시행 공사)","2021-04-01 08:00","2021-04-14 18:00","2021-04-01 13:00","2021-04-10 18:00","연속"]
[81,"경기","성남","신용인동서울#2 T/L","345kV 신용인-동서울T/L 지장철탑 이설공사(이천오산)","345kV 신용인-동서울T/L 7-1호 지장철탑 이설(요청자 시행 공사)","2021-04-15 08:00","2021-04-27 18:00","2021-04-11 08:00","2021-04-20 18:00","연속"]
[82,"경기","직할","화성S/S #1 M.Tr","20-21년 경기직할 변전정비회사 총액공사","화성S/S #1M.Tr 보통점검, 2차 LA 보통, 3차 LA 대체 7372GIS 조작시험, 3차기기 조작시험","2021-04-05 09:00","2021-04-06 18:00","취소","취소","연속"]
[83,"경기","직할","화성S/S #3 M.Tr","345kV 화성S/S GIS 용량대체공사","#3M.Tr Bay 조정 75 -> 78 Bay","2021-04-05 09:00","2021-05-07 18:00","2021-04-05 09:00","2021-05-07 18:00","연속"]
[84,"경기","직할","화성평택T/P#1 T/L","2020-2021년도 송전정비회사 총액공사","수촌-조암#2T/L 송전용 피뢰기 설치 관련 안전이격거리확보","2021-04-27 09:00","2021-04-27 18:00","2021-04-27 09:00","2021-04-27 18:00","연속"]
[85,"경기","직할","화성S/S 345kV #76 BUS","345kV 화성S/S GIS 용량대체공사"," #76BUS 모선대체","2021-03-31 11:00","2021-04-30 18:00","2021-03-31 11:00","2021-04-30 18:00","연속"]
[86,"경기","평택","고덕S/S #4 M.Tr","고덕S/S 345kV #4 M.Tr 2차 GIS 불량보수","고덕S/S 345kV #4 M.Tr 2차 GIS 유압조작기 교체","2021-04-22 10:00","2021-04-23 18:00","2021-04-22 10:00","2021-04-23 18:00","연속"]
[87,"경기","평택","고덕S/S 345kV #1 BUS","345kV 고덕#2S/S 건설사업","345kV 고덕#2S/S 건설사업 - 고덕#1S/S 362kV GIS 2CB 증설","2021-04-26 09:00","2021-05-21 18:00","2021-04-26 09:00","2021-05-21 18:00","연속"]
[88,"경기","평택","평택T/P SEC CB 70710","평택T/P 345kV #70-#71 SEC GIS 하자점검","평택T/P 345kV #70-#71 SEC GIS 하자점검","2021-04-19 10:00","2021-04-19 18:00","취소","취소","연속"]
[89,"경기","평택","평택TP신평택CC #1 CLR CB","평택T/P 345kV #1 CLR #7077 GIS 하자점검","평택T/P 345kV #1 CLR #7077 GIS 하자점검","2021-04-07 10:00","2021-04-08 18:00","취소","취소","연속"]
[90,"경기","평택","평택TP신평택CC #1 CLR CB","평택T/P 345kV #1 CLR #7177 GIS 하자점검","평택T/P 345kV #1 CLR #7177 GIS 하자점검","2021-04-07 10:00","2021-04-08 18:00","취소","취소","연속"]
[91,"경기","평택","평택TP신평택CC #2 CLR CB","평택T/P 345kV #2 CLR #7677 GIS 하자점검","평택T/P 345kV #2 CLR #7677 GIS 하자점검","2021-04-01 10:00","2021-04-02 18:00","취소","취소","연속"]
[92,"경기","평택","평택T/P SEC CB 75760","평택T/P 345kV #75-#76 SEC GIS 하자점검","평택T/P 345kV #75-#76 SEC GIS 하자점검","2021-04-05 10:00","2021-04-05 18:00","취소","취소","연속"]
[93,"경기","평택","평택TP신평택CC #2 CLR CB","평택T/P 345kV #2 CLR #7577 GIS 하자점검","평택T/P 345kV #2 CLR #7577 GIS 하자점검","2021-04-01 10:00","2021-04-02 18:00","취소","취소","연속"]
[94,"강원","동해","동해S/S #3 M.Tr","2021년 동해전력지사 변전정비 총액공사","M.Tr 보통점검","2021-04-05 09:00","2021-04-08 18:00","2021-04-05 09:00","2021-04-08 18:00","연속"]
[95,"강원","강릉","신양양양양PP T/L","2021년도 강릉전력지사 가공송전선로 순시점검 위탁공사","정밀점검 345kV 신양양분기 T/L No.1~5","2021-04-15 09:00","2021-04-16 18:00","2021-04-15 09:00","2021-04-16 18:00","매일"]
[96,"강원","동해","삼척T/P #3 Tie-Tr","동해전력지사 2021년 170kV GIS 정밀점검"," GIS 정밀점검 2. 가스 누기 관련 스페이서 점검","2021-04-19 09:00","2021-04-25 18:00","2021-04-19 09:00","2021-04-25 18:00","연속"]
[97,"강원","강릉","양양P/P CB 7300","2021년 강릉전력지사 362kV GIS 정밀점검","2021년 362kV GIS 정밀점검 - CB부 정밀점검","2021-04-19 09:00","2021-04-24 18:00","취소","취소","연속"]
[98,"강원","동해","동해삼척GP#1 T/L","2021년 동해전력지사 변전정비 총액공사","CVT 교체공사","2021-04-26 09:00","2021-04-26 18:00","2021-04-26 09:00","2021-04-26 18:00","연속"]
[99,"강원","동해","동해삼척GP#2 T/L","2021년 동해전력지사 변전정비 총액공사","CVT 대체공사","2021-04-27 09:00","2021-04-27 18:00","2021-04-27 09:00","2021-04-27 18:00","연속"]
[100,"강원","강릉","양양P/P CB 7371","2021년 강릉전력지사 362kV GIS 정밀점검","2021년 362kV GIS 정밀점검 - CB부 정밀점검","2021-04-28 09:00","2021-05-03 18:00","2021-04-26 09:00","2021-05-01 18:00","연속"]
[101,"충북","직할","신중부남청주#1 T/L","345kV 신중부-남청주T/L (No.60, 61) 안전이격확보공사","철탑(No.60, 61) 교체 - 신중부-남청주#1T/L 구성(신설)","2021-04-17 07:00","2021-04-21 18:00","취소","취소","연속"]
[102,"충북","직할","신중부남청주#2 T/L","345kV 신중부-남청주T/L(No.60, 61) 안전이격확보공사","철탑(No.60, 61) 교체 - 345kV 신중부-남청주#2T/L 구성(신설)","2021-04-22 07:00","2021-04-26 18:00","취소","취소","연속"]
[103,"충북","직할","서안성신진천#2 T/L","345kV 신진천S/S 용량부족 GIS 대체공사 (안전이격확보)","345kV GIS #70BUS 및 (#71~74BAY)51DS 대체(8차분) 크레인 사용 안전이격거리 확보","2021-04-01 09:00","2021-04-06 18:00","2021-04-01 09:00","2021-04-06 18:00","연속"]
[104,"충북","직할","신진천S/S 345kV #75 BUS","345kV 신진천S/S 용량부족 GIS 대체공사 (#75BUS)","345kV GIS #75BUS 및 (#71~74BAY)52,02DS 대체(9차분)","2021-04-22 08:00","2021-05-17 18:00","2021-04-22 08:00","2021-05-17 18:00","연속"]
[105,"충북","직할","신중부신진천#1 T/L","345kV 신진천S/S 용량부족 GIS 대체공사 (안전이격확보)","345kV GIS #70BUS 및 (#71~74BAY)51DS 대체(8차분) 크레인 사용 안전이격거리 확보","2021-04-07 09:00","2021-04-08 18:00","2021-04-07 09:00","2021-04-08 18:00","연속"]
[106,"충북","청주","신옥천청양 T/L","20-21년 청주전력 변전정비 총액","345kV CVT 교체","2021-04-21 10:00","2021-04-21 18:00","2021-04-27 10:00","2021-04-27 18:00","연속"]
[107,"충북","청주","신옥천신계룡 T/L","20-21년 청주전력 변전정비 총액","345kV CVT 교체","2021-04-22 10:00","2021-04-22 18:00","2021-04-28 10:00","2021-04-28 18:00","연속"]
[108,"충북","청주","신옥천북경남 T/L","345kV 신옥천-북경남T/L 안전이격확보공사","345kV 신옥천-북경남T/L No.281,283 철탑 및 전선교체","2021-04-02 08:00","2021-04-10 18:00","2021-04-02 08:00","2021-04-10 18:00","연속"]
[109,"충북","청주","신옥천무주양수 T/L","345kV 신옥천-북경남T/L 안전이격확보공사","345kV 신옥천-북경남T/L No.281,283 철탑 및 전선교체","2021-04-11 08:00","2021-04-15 18:00","2021-04-11 08:00","2021-04-15 18:00","연속"]
[110,"충북","청주","신옥천무주양수 T/L","345kV 신옥천-북경남T/L 안전이격확보공사","345kV 신옥천-북경남T/L No.281,283 철탑 및 전선교체","2021-04-01 08:00","2021-04-01 18:00","2021-04-01 08:00","2021-04-01 18:00","연속"]
[111,"충북","충주","신제천S/S CB 7200 (SVC 휴전)","신제천S/S 345kV SVC 초기점검","신제천S/S 345kV SVC 초기점검","2021-04-26 09:00","2021-04-30 18:00","2021-04-26 09:00","2021-04-30 18:00","연속"]
[112,"충북","충주","신제천S/S CB 7271 (SVC 휴전)","신제천S/S 345kV SVC 초기점검","신제천S/S 345kV SVC 초기점검","2021-04-26 09:00","2021-04-30 18:00","취소","취소","연속"]
[113,"충북","충주","신제천S/S #4 M.Tr","20-21년 충주전력지사 변전정비 총액공사","신제천S/S #4M.Tr 1차 CVT 설치 신제천S/S #4M.Tr 3차 VCB(4289) 점검","2021-04-15 10:00","2021-04-16 18:00","2021-04-15 10:00","2021-04-16 18:00","연속"]
[114,"충북","충주","신제천S/S #3 M.Tr","20-21년 충주전력지사 변전정비 총액공사","신제천S/S #3M.Tr 1차 CVT 설치 신제천S/S #3M.Tr 3차 VCB(4379 등 5대) 점검 및 절연화 시공","2021-04-12 10:00","2021-04-14 18:00","2021-04-12 10:00","2021-04-14 18:00","연속"]
[115,"충북","충주","신충주S/S CB 7071 (STATCOM 휴전)","소방설비작동점검 용역","신충주S/S STATCOM 제어동 소방설비 작동점검","2021-04-06 09:30","2021-04-06 18:00","2021-04-21 09:30","2021-04-21 18:00","연속"]
[116,"충북","충주","신충주S/S CB 7000 (STATCOM 휴전)","소방설비작동점검 용역","신충주S/S STATCOM 제어동 소방설비 작동점검","2021-04-06 09:30","2021-04-06 18:00","취소","취소","연속"]
[117,"대전충남","서산","당진T/P CB 7200","21년 서산P/O 345/765KV GIS 정밀점검공사","당진화력S/S 765kV #1 Tie.Tr 2차-2호기 1차 TIE GIS(7200) 정밀점검","2021-04-12 10:00","2021-04-16 18:00","2021-04-12 10:00","2021-04-16 18:00","연속"]
[118,"대전충남","서산","북당진S/S CB 7672","21년도 변전협력회사 총액공사","북당진S/S 345kV #1 M.Tr 1차 GIS(7672) 초기점검","2021-04-27 09:00","2021-04-27 18:00","2021-04-27 09:00","2021-04-27 18:00","연속"]
[119,"대전충남","서산","북당진S/S CB 7600","21년도 변전협력회사 총액공사","북당진S/S 345kV 7671T/L-#1 M.Tr 1차 TIE GIS(7600) 초기점검","2021-04-14 09:00","2021-04-14 18:00","2021-04-14 09:00","2021-04-14 18:00","연속"]
[120,"대전충남","서산","북당진S/S CB 7671","21년도 변전협력회사 총액공사","북당진S/S 345kV 7671T/L GIS(7671) 초기점검","2021-04-15 09:00","2021-04-15 18:00","2021-04-15 09:00","2021-04-15 18:00","연속"]
[121,"대전충남","서산","북당진S/S CB 7B72","21년도 변전협력회사 총액공사","북당진S/S 345kV #1C.Tr 1차 GIS(7B72) 초기점검","2021-04-30 09:00","2021-04-30 18:00","2021-04-30 09:00","2021-04-30 18:00","연속"]
[122,"대전충남","서산","북당진현대제철 T/L","345kV 신송산S/S 건설공사(일반)","북당진-현대제철 T/L 송전선로 보호반 이설 및 설치 등","2021-04-21 09:00","2021-04-30 18:00","2021-04-21 09:00","2021-04-30 18:00","연속"]
[123,"대전충남","서산","북당진S/S CB 7B00","21년도 변전협력회사 총액공사","북당진S/S 345kV P1 #1FL T/L-#1C.Tr TIE GIS(7B00) 초기점검","2021-04-26 09:00","2021-04-26 18:00","2021-04-26 09:00","2021-04-26 18:00","연속"]
[124,"대전충남","서산","북당진S/S CB 7B71","21년도 변전협력회사 총액공사","북당진S/S 345kV P1 #1 FL GIS(7B71) 초기점검","2021-04-16 09:00","2021-04-16 18:00","2021-04-16 09:00","2021-04-16 18:00","연속"]
[125,"대전충남","서산","신당진개폐소북당진 T/L","345kV 신당진개폐소-북당진T/L 정밀점검","345kV 현대제철 #신당진-북당진 정밀점검 345kV GS-EPS분기 #신당진-북당진 정밀점검","2021-04-05 08:00","2021-04-09 18:00","2021-04-05 08:00","2021-04-09 18:00","매일"]
[126,"대전충남","서산","신당진개폐소현대제철 T/L","345kV 신송산S/S 건설공사(일반)","신당진개폐소-현대제철 T/L 송전선로 보호반 이설 및 설치","2021-04-10 09:00","2021-04-20 18:00","2021-04-10 09:00","2021-04-20 18:00","연속"]
[127,"대전충남","서산","신당진개폐소태안TP#2 T/L","345kV 신당진-북당진T/L 정밀점검[병가구간]","345kV 신당진개폐소-태안화력#2 No.126,127 정밀점검 [4회선 병가구간]","2021-04-05 08:00","2021-04-05 18:00","2021-04-05 08:00","2021-04-05 18:00","연속"]
[128,"대전충남","서산","신당진S/S CB 7672","'21년 장기 미동작 차단기 조작시험","신당진S/S 345kV #2 M.Tr 1차 7672 CB 조작시험","2021-04-20 14:00","2021-04-20 18:00","2021-04-20 14:00","2021-04-20 18:00","연속"]
[129,"대전충남","서산","신당진S/S CB 7100","'21년 장기 미동작 차단기 조작시험","신당진S/S 345kV 신당진연락#1-신서산#1T/L TIE 7100 CB 조작시험","2021-04-13 14:00","2021-04-13 18:00","2021-04-13 14:00","2021-04-13 18:00","연속"]
[130,"대전충남","서산","신당진S/S CB 7171","'21년 장기 미동작 차단기 조작시험","신당진S/S 345kV 7171 CB 조작시험","2021-04-13 10:00","2021-04-13 14:00","2021-04-13 10:00","2021-04-13 14:00","연속"]
[131,"대전충남","서산","신당진S/S CB 7471","'21년 장기 미동작 차단기 조작시험","신당진S/S 345kV 신당진연락#1T/L 7471 CB 조작시험","2021-04-20 10:00","2021-04-20 14:00","2021-04-20 10:00","2021-04-20 14:00","연속"]
[132,"대전충남","서산","신당진S/S CB 7600","'21년 장기 미동작 차단기 조작시험","신당진S/S 345kV #2 M.Tr 1차-TIE 7600 CB 조작시험","2021-04-06 10:00","2021-04-06 14:00","2021-04-06 10:00","2021-04-06 14:00","연속"]
[133,"대전충남","서산","신서산S/S #3 Sh.R CB","21년도 변전협력회사 총액공사","신서산S/S 345kV #3 Sh.R 및 GIS(7571) 보통점검","2021-04-28 09:00","2021-04-28 18:00","2021-04-28 09:00","2021-04-28 18:00","연속"]
[134,"대전충남","서산","태안T/P SEC CB 71720","21년 서산P/O 345kV GIS 조작로드 교체공사","태안화력S/S 345kV #71-#72 SEC GIS (71-72-0) 조작로드 교체 및 정밀점검","2021-04-26 10:00","2021-05-04 18:00","2021-04-26 10:00","2021-05-04 18:00","연속"]
[135,"대전충남","서산","태안T/P CB 7A72","21년 서산P/O 345kV GIS 조작로드 교체공사","태안화력S/S 345kV #10 GEN 1차 GIS (7A72) 조작로드 교체 및 정밀점검","2021-04-19 10:00","2021-04-23 18:00","2021-04-19 10:00","2021-04-23 18:00","연속"]
[136,"대전충남","서산","태안T/P CB 7A00","21년 서산P/O 345kV GIS 조작로드 교체공사","태안화력S/S 345kV 신서산#2T/L-#10 GEN 1차 TIE GIS (7A00) 조작로드 교체 및 정밀점검","2021-04-12 10:00","2021-04-16 18:00","2021-04-12 10:00","2021-04-16 18:00","연속"]
[137,"대전충남","서산","태안T/P CB 7A71","21년 서산P/O 345kV GIS 조작로드 교체공사","태안화력S/S 345kV 신서산-태안화력#2T/L GIS (7A71) 조작로드 교체 및 정밀점검","2021-04-05 10:00","2021-04-09 18:00","2021-04-05 10:00","2021-04-09 18:00","연속"]
[138,"대전충남","서산","태안T/P #1 M.Tr","'21년 장기 미동작 차단기 조작시험","태안T/P 345kV #1 M.Tr 2차 6144 CB 조작시험","2021-04-22 14:00","2021-04-22 18:00","2021-04-22 14:00","2021-04-22 18:00","연속"]
[139,"대전충남","서산","태안T/P #2 M.Tr","'21년 장기 미동작 차단기 조작시험","태안T/P 345kV #2 M.Tr 2차 6244 CB 조작시험","2021-04-22 10:00","2021-04-22 14:00","2021-04-22 10:00","2021-04-22 14:00","연속"]
[140,"대전충남","서산","태안T/P 345kV #71 BUS","21년 서산P/O 345kV GIS 조작로드 교체공사","태안화력S/S 345kV #71-#72 SEC GIS (71-72-0) 조작로드 교체 및 정밀점검","2021-04-26 10:00","2021-05-04 18:00","취소","취소","연속"]
[141,"대전충남","아산","아산S/S #4 M.Tr","아산S/S 345kV #4M.Tr 1차 부싱절연유 채유","아산S/S 345kV #4M.Tr 1차 부싱절연유 채유","2021-04-26 09:00","2021-04-26 18:00","2021-04-26 09:00","2021-04-26 18:00","연속"]
[142,"대전충남","아산","아산S/S CB 7100","아산S/S 345kV 7100, 7272 GIS 보통점검","아산S/S 345kV 7100, 7272 GIS 보통점검","2021-04-05 09:00","2021-04-05 14:00","2021-04-05 09:00","2021-04-05 14:00","연속"]
[143,"대전충남","아산","아산S/S CB 7272","아산S/S 345kV 7100, 7272 GIS 보통점검","아산S/S 345kV 7100, 7272 GIS 보통점검","2021-04-05 14:00","2021-04-05 18:00","취소","취소","연속"]
[144,"대전충남","아산","아산S/S CB 7471","아산S/S 345kV 7471 GIS 보통점검","아산S/S 345kV 7471 GIS 보통점검","2021-04-09 09:00","2021-04-09 14:00","2021-04-09 09:00","2021-04-09 14:00","연속"]
[145,"대전충남","아산","아산S/S #2 M.Tr","아산S/S 345kV #2M.Tr 1차 부싱절연유 채유","아산S/S 345kV #2M.Tr 1차 부싱절연유 채유","2021-04-19 09:00","2021-04-19 18:00","2021-04-19 09:00","2021-04-19 18:00","연속"]
[146,"대전충남","청양","보령TP보령CC#1 T/L","345kV 보령연락#1T/L 관련기기 점검","보령C/C 362kV GIS(7171), LA, CVT 보통점검, 7100CB 부동작예방 조작시험 ○ 보령T/P LA 보통점검","2021-04-26 09:00","2021-04-27 18:00","2021-04-26 09:00","2021-04-27 18:00","매일"]
[147,"대전충남","청양","아산보령TP#2 T/L","[송전]345kV 청양-보령 등 9개TL 항공장애표시구 설치공사","345kV아산-보령화력#2T/L 항공장애표시구 설치","2021-04-26 07:00","2021-04-29 18:00","2021-04-26 07:00","2021-04-29 18:00","매일"]
[148,"대전충남","청양","청양S/S #1 M.Tr","청양S/S 345kV #1M.Tr 관련기기 점검","1,2차 차단기 부동작예방 조작시험(7671, 7600, 6144) ○ 부싱 절연유 채유 ○ 3차 GPT C상 건전성 점검","2021-04-08 09:00","2021-04-09 18:00","2021-04-08 09:00","2021-04-09 18:00","연속"]
[149,"대전충남","청양","신계룡청양 T/L","청양S/S #71BAY B/F PNL 대체 및 관련기기 점검","청양S/S #71BAY B/F PNL 대체 ○ 청양S/S 7171CB 부동작예방 조작시험","2021-04-19 09:00","2021-04-23 18:00","2021-04-19 09:00","2021-04-23 18:00","연속"]
[150,"대전충남","청양","청양보령TP#1 T/L","청양S/S #71BAY B/F PNL 대체 및 관련기기 점검","청양S/S #71BAY B/F PNL 대체 ○ 양단 송전선로 보호반 성능개선","2021-04-19 09:00","2021-04-23 18:00","2021-04-19 09:00","2021-04-23 18:00","연속"]
[151,"대전충남","청양","청양신탕정 T/L"," [송전]345kV 청양-신온양 등 5개 T/L 피뢰기 설치공사","345kV 청양-신탕정T/L 피뢰기 설치공사 No.1~56 호 철탑 송전용 피뢰기 설치 ","2021-04-19 08:00","2021-04-27 18:00","취소","취소","매일"]
[152,"전북","군산","군산S/S #2 M.Tr","345kV 주변압기 정밀점검 공사","#2M.Tr A 상 정밀점검","2021-04-26 09:00","2021-05-01 18:00","2021-04-26 09:00","2021-05-01 18:00","연속"]
[153,"전북","군산","군산신김제#2 T/L","소도체 이도조정공사","이도조정 1~20","2021-04-05 07:00","2021-04-08 18:00","2021-04-05 07:00","2021-04-08 18:00","연속"]
[154,"전북","직할","신남원S/S CB 7271","21년도 전북본부 직할 362kV GIS 차단기 정밀점검공사(7271)","신남원S/S 신옥천-신남원 #1 TL CB(7271) 단독 차단기 정밀점검","2021-04-23 09:00","2021-04-26 18:00","2021-04-23 09:00","2021-04-26 18:00","연속"]
[155,"전북","직할","신남원신광주#1 T/L","345kV 신남원-신광주 등 3개T/L 추락방지장치 설치공사(비상시 즉시 가압 가능)","345kV 신남원-신광주 #1T/L 추락방지시설 설치공사(매일조작 가능)","2021-04-12 08:00","2021-05-14 17:00","2021-04-12 08:00","2021-05-14 17:00","연속"]
[156,"전북","직할","신남원S/S CB 7172","21년도 전북본부 직할 362kV GIS 차단기 정밀점검공사(7172)","신남원S/S 신남원-한빛NP #2 TL CB(7172) 단독 차단기 정밀점검","2021-04-27 09:00","2021-04-30 18:00","2021-04-27 09:00","2021-04-30 18:00","연속"]
[157,"전북","직할","신남원S/S CB 7171","21년도 전북본부 직할 362kV GIS 차단기 정밀점검공사(7171)","신남원S/S 신옥천-신남원 #2 TL CB(7171) 단독 차단기 정밀점검","2021-04-19 09:00","2021-04-22 18:00","2021-04-19 09:00","2021-04-22 18:00","연속"]
[158,"전북","직할","신남원S/S #1 M.Tr","345kV 신남원S/S #64D.Tr 증설 관련 토목공사","제어케이블 덕트(D-140) 신설 ○ 작업내용 : 터파기 및 콘크리트 타설 ○ 작업구간 : #1M.Tr 2차측 부싱 인근 작업","2021-04-19 10:00","2021-04-26 17:00","2021-04-19 10:00","2021-04-26 17:00","연속"]
[159,"광주전남","광주","신광주S/S #4 M.Tr","21년 변전정비회사 총액공사(신광주 #4M.Tr)","21년 변전정비회사 총액공사(신광주 #4M.Tr) - M.Tr 보통점검 - 1차 GIS 보통점검 (7872,7800CB)","2021-04-12 09:00","2021-04-14 18:00","2021-04-12 09:00","2021-04-14 18:00","연속"]
[160,"광주전남","광주","신광주S/S #2 M.Tr","21년 변전정비회사 총액공사(신광주 #2M.Tr)","21년 변전정비회사 총액공사(신광주 #2M.Tr) - M.Tr 하자점검 - 1차 GIS 보통점검 (7472,7400CB)","2021-04-05 09:00","2021-04-07 18:00","2021-04-05 09:00","2021-04-07 18:00","연속"]
[161,"광주전남","광주","신광주S/S CB 7672","21년 광주정비회사 총액공사 (345 GIS 보통점검)","신광주S/S 신광주-신화순#2T/L (7672CB) 보통점검","2021-04-29 09:00","2021-04-29 18:00","2021-04-29 09:00","2021-04-29 18:00","연속"]
[162,"광주전남","광주","신광주S/S CB 7200","21년 광주정비회사 총액공사 (345 GIS 보통점검)","신광주S/S 신광주-한빛 #2T/L 7200CB 보통점검","2021-04-09 09:00","2021-04-09 18:00","2021-04-09 09:00","2021-04-09 18:00","연속"]
[163,"광주전남","광주","신광주신화순#1 T/L","21년 광주정비회사 총액공사 (345 GIS 보통점검)","신광주S/S 신광주-신화순#2T/L 보통점검","2021-04-23 07:00","2021-04-27 18:00","2021-04-23 07:00","2021-04-27 18:00","연속"]
[164,"광주전남","광주","신남원신광주#2 T/L","21년 광주정비회사 총액공사 (345 GIS 보통점검,CVT하자)","신광주S/S 신남원-신광주#2T/L (77300,7371CB) 보통 및 CVT 하자점검","2021-04-01 09:00","2021-04-02 18:00","2021-04-01 09:00","2021-04-02 18:00","연속"]
[165,"광주전남","광주","신광주S/S CB 7600","21년 광주정비회사 총액공사 (345 GIS 보통점검)","신광주S/S 신광주-신화순#2T/L (7600CB) 보통점검","2021-04-27 09:00","2021-04-27 18:00","취소","취소","연속"]
[166,"광주전남","광주","신화순S/S #1 M.Tr","21년 변전정비회사 총액공사","신화순 #1M.Tr TPI 불량분 교체","2021-04-16 09:00","2021-04-16 18:00","2021-04-16 09:00","2021-04-16 18:00","연속"]
[167,"광주전남","광주","신화순S/S 345kV #2 BUS","신화순S/S 345kV #1Sh.R 증설공사","345kV #1Sh.R x 1bank 설치 - 362kV GIS 3CB 설치 - 기타부대공사 1식","2021-04-14 09:00","2021-04-20 18:00","2021-04-14 09:00","2021-04-20 18:00","연속"]
[168,"광주전남","광주","신화순S/S #2 M.Tr","신화순S/S 345kV #1Sh.R 증설공사","345kV #1Sh.R x 1bank 설치 - 362kV GIS 3CB 설치 - 기타부대공사 1식","2021-04-13 09:00","2021-04-13 18:00","2021-04-13 09:00","2021-04-13 18:00","연속"]
[169,"광주전남","목포","한빛2NP한빛3NP#4 T/L","2020-21년 목포전력지사 변전정비회사 총액공사","345kV GIS 보통점검","2021-04-26 09:00","2021-04-26 18:00","취소","취소","연속"]
[170,"광주전남","목포","한빛#2N/P CB 7771","2020-21년 목포전력지사 변전정비회사 총액공사","345kV GIS 보통점검","2021-04-27 09:00","2021-04-27 18:00","2021-04-27 09:00","2021-04-27 18:00","연속"]
[171,"광주전남","순천","신남원광양#1 T/L","345kV 광양S/S 용량부족GIS 대체공사(#70BUS) 사용전검사","345kV 광양S/S 용량부족GIS 대체공사(#70BUS) 관련 사용전검사","2021-04-01 10:00","2021-04-02 18:00","취소","취소","연속"]
[172,"광주전남","순천","광양S/S 345kV #75 BUS","345kV 광양S/S 362kV GIS 용량변경대체공사(#75BUS)","345kV 광양S/S 362kV GIS 용량변경대체공사(#75BUS) - 71,72,73 Bay 측 모선 교체","2021-04-05 10:00","2021-04-30 18:00","2021-04-05 10:00","2021-04-30 18:00","연속"]
[173,"광주전남","순천","신남원광양#1 T/L","345kV 광양S/S 362kV GIS 용량변경대체공사(무부하가압)","345kV 광양S/S 362kV GIS 용량변경대체공사(무부하가압) - 71,72,73 Bay 측 모선 교체","2021-04-28 10:00","2021-04-29 10:00","취소","취소","연속"]
[174,"광주전남","순천","신남원광양#1 T/L","345kV 광양S/S 362kV GIS 용량변경대체공사(사용전검사)","345kV 광양S/S 362kV GIS 용량변경대체공사(사용전검사) - 71,72,73 Bay 측 모선 교체","2021-04-29 10:00","2021-04-30 18:00","취소","취소","연속"]
[175,"광주전남","순천","여수T/P #2 Tie-Tr","345kV 여수화력S/Y 345kV M.Tr 및 SW 증설공사","345kV M.Tr 및 GIS 설치","2021-04-05 09:00","2021-04-09 18:00","2021-04-05 09:00","2021-04-09 18:00","연속"]
[176,"광주전남","순천","광양여수TP T/L","345kV 광양CC-신여수T/L 건설공사","지지물 : 철탑 24기(가철탑 4기 별도) 2. 전력선 : ACSR/AW 480㎟×2B×2C 8.6km","2021-04-01 07:00","2021-04-04 18:00","2021-04-27 11:00","2021-04-28 11:00","연속"]
[177,"광주전남","순천","율촌CC여수TP T/L","345kV 광양CC-신여수T/L 건설공사","지지물 : 철탑 24기(가철탑 4기 별도) 2. 전력선 : ACSR/AW 480㎟×2B×2C 8.6km","2021-04-05 07:00","2021-04-08 18:00","2021-04-05 07:00","2021-04-09 18:00","연속"]
[178,"대구","칠곡","서대구S/S CB 7471","서대구S/S 345kV GCB 공기조작부 정밀점검","서대구S/S 345kV GCB 공기조작부 정밀점검","2021-04-05 09:00","2021-04-06 18:00","2021-04-05 09:00","2021-04-06 18:00","연속"]
[179,"대구","칠곡","서대구S/S CB 7172","서대구S/S 345kV GCB 공기조작부 정밀점검","서대구S/S 345kV GCB 공기조작부 정밀점검","2021-04-01 09:00","2021-04-02 18:00","2021-04-01 09:00","2021-04-02 18:00","연속"]
[180,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S 현대화 공사(토목)","전력구 H파일 인발작업 안전이격 확보","2021-04-13 08:00","2021-04-13 18:00","2021-04-13 08:00","2021-04-13 18:00","연속"]
[181,"대구","칠곡","서대구선산#1 T/L","서대구S/S 서대구-선산 #1 T/L 7402 DS 조작불량 보수","서대구S/S 서대구-선산 #1 T/L 7402 DS 조작불량 보수","2021-04-08 09:00","2021-04-08 18:00","2021-04-15 09:00","2021-04-15 18:00","연속"]
[182,"대구","칠곡","서대구S/S CB 7400","서대구S/S 345kV GCB 공기조작부 정밀점검","서대구S/S 345kV GCB 공기조작부 정밀점검","2021-04-08 09:00","2021-04-09 18:00","2021-04-15 09:00","2021-04-16 18:00","연속"]
[183,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S 현대화 공사 (건축)","종합제어동 외벽 PNL 부착 관련 안전이격 확보","2021-04-05 08:00","2021-04-10 18:00","2021-04-12 08:00","2021-04-16 18:00","연속"]
[184,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S 현대화 공사 (건축)","345kV 현장제어동 외벽 PNL 부착 관련 안전이격 확보","2021-04-26 08:00","2021-04-30 18:00","2021-04-19 08:00","2021-04-23 18:00","연속"]
[185,"대구","칠곡","서대구S/S CB 7600","서대구S/S 345kV GCB 공기조작부 정밀점검","서대구S/S 345kV GCB 공기조작부 정밀점검","2021-04-15 09:00","2021-04-16 18:00","2021-04-08 09:00","2021-04-09 18:00","연속"]
[186,"대구","칠곡","서대구S/S CB 7671","서대구S/S 345kV GCB 공기조작부 정밀점검","서대구S/S 345kV GCB 공기조작부 정밀점검","2021-04-12 09:00","2021-04-13 18:00","2021-04-12 09:00","2021-04-13 18:00","연속"]
[187,"대구","칠곡","서대구S/S 345kV #1 BUS","서대구S/S #70BUS 모선측 7451 DS 조작불량 보수","서대구S/S #70BUS 모선측 7451 DS 조작불량 보수","2021-04-05 09:00","2021-04-05 18:00","취소","취소","연속"]
[188,"대구","포항","신포항S/S #3 M.Tr","신포항S/S #3M.Tr 보통점검","신포항S/S #3M.Tr 보통점검, 7871, 7872 조작시험","2021-04-27 09:00","2021-04-28 18:00","2021-04-27 09:00","2021-04-28 18:00","연속"]
[189,"대구","포항","신포항S/S 345kV #1 BUS","신포항S/S 345kV #70BUS 모선측 DS 과열개소 보수","신포항S/S 345kV #70BUS 모선측 DS 과열개소 보수","2021-04-05 09:00","2021-04-06 18:00","2021-04-05 09:00","2021-04-06 18:00","연속"]
[190,"대구","포항","신포항S/S 345kV #2 BUS","신포항S/S 345kV #75BUS 모선측 DS 과열개소 보수","신포항S/S 345kV #75BUS 모선측 DS 과열개소 보수","2021-04-07 09:00","2021-04-08 18:00","2021-04-07 09:00","2021-04-08 18:00","연속"]
[191,"경북","구미","선산신포항 T/L","2020-21년 구미전력지사 변전정비업체 총액공사","7471, 7400 GIS 조작시험","2021-04-19 09:00","2021-04-19 18:00","2021-04-19 09:00","2021-04-19 18:00","연속"]
[192,"경북","구미","북대구선산 T/L","2020-21년 구미전력지사 변전정비업체 총액공사","7371, 7300 GIS 조작시험","2021-04-15 09:00","2021-04-15 18:00","2021-04-15 09:00","2021-04-15 18:00","연속"]
[193,"경북","구미","서대구선산#1 T/L","2020-21년 구미전력지사 가공송전정비회사 총액공사","96년 상반기 이전 성능저하 국산애자 교체공사","2021-04-24 13:00","2021-04-24 15:00","2021-04-24 13:00","2021-04-24 15:00","연속"]
[194,"경북","구미","서대구선산#2 T/L","2020-21년 구미전력지사 가공송전정비회사 총액공사","96년 상반기 이전 성능저하 국산애자 교체공사","2021-04-24 15:00","2021-04-24 17:00","2021-04-24 15:00","2021-04-24 17:00","연속"]
[195,"경북","직할","신영주안동CC T/L","345kV 신영주-안동CC T/L 정밀점검","345kV 신영주-안동CC T/L 정밀점검 No.51.1 ~ 77","2021-04-12 09:00","2021-04-14 18:00","2021-04-12 09:00","2021-04-14 18:00","연속"]
[196,"경북","직할","신영주청송PP T/L","345kV 신영주-청송PP T/L 정밀점검","345kV 신영주-청송PP T/L 정밀점검 No.180~225","2021-04-06 09:00","2021-04-09 18:00","2021-04-26 08:00","2021-04-29 18:00","연속"]
[197,"부산울산","동부산","신양산북부산#2 T/L","신양산S/S 345kV GIS 차단기 동작시험","신양산S/S 345kV GIS 차단기 동작시험(신양산-북부산#2T/L)","2021-04-01 09:30","2021-04-01 17:00","취소","취소","연속"]
[198,"부산울산","동부산","신양산북부산#1 T/L","신양산S/S 345kV GIS 보통점검","신양산S/S 345kV GIS 보통점검(신양산-북부산#1T/L)","2021-04-06 09:30","2021-04-07 17:00","2021-04-01 09:30","2021-04-02 17:00","연속"]
[199,"부산울산","동부산","신양산S/S #1 M.Tr","신양산S/S 345kV GIS 차단기 동작시험","신양산S/S 345kV GIS 차단기 동작시험(#1M.Tr)","2021-04-19 09:30","2021-04-20 17:00","2021-04-12 09:00","2021-04-13 18:00","연속"]
[200,"부산울산","동부산","신양산S/S #2 M.Tr","신양산S/S 345kV GIS 차단기 동작시험","신양산S/S 345kV GIS 차단기 동작시험(#2M.Tr)","2021-04-26 09:30","2021-04-27 17:00","2021-04-15 09:00","2021-04-16 18:00","연속"]
[201,"부산울산","북부산","북부산S/S #1 Sh.R CB 7677","20-21 북부산전력지사 변전 총액공사","북부산S/S 서부산-북부산#1T/L 7671,7600,7677 GIS 하자점검 #1 Sh.R ","2021-04-05 09:00","2021-04-06 18:00","2021-04-05 09:00","2021-04-06 18:00","연속"]
[202,"부산울산","북부산","북부산신울산#1 T/L","20-21 북부산전력지사 변전 총액공사","북부산S/S 345kV 북부산-신울산#1T/L 7171, 7100 GIS 하자점검","2021-04-08 10:00","2021-04-09 18:00","2021-04-08 10:00","2021-04-09 18:00","연속"]
[203,"부산울산","울산","동울산S/S #3 M.Tr","20-21년 울산전력지사 변전총액공사","7472 차단기 동작시험","2021-04-01 09:00","2021-04-01 18:00","2021-04-01 09:00","2021-04-01 18:00","연속"]
[204,"부산울산","울산","신온산울산TP T/L","345kV 남울산분기T/L 건설사업","345kV 남울산-울산TP #2, 남울산-신온산 #1 전력선 연긴선(최초가압)","2021-04-19 07:00","2021-04-30 18:00","2021-04-19 07:00","2021-04-30 18:00","연속"]
[205,"부산울산","울산","신울산S/S #1 M.Tr","신울산S/S 154kV 현대화공사","TR-BUS DS(6168) 철거","2021-04-03 09:30","2021-04-04 17:00","2021-04-03 09:30","2021-04-04 17:00","연속"]
[206,"부산울산","울산","신울산S/S #4 M.Tr","신울산S/S 154kV 현대화공사","TR-BUS DS(6468) 철거","2021-04-10 09:30","2021-04-11 17:00","2021-04-10 09:30","2021-04-11 17:00","연속"]
[207,"부산울산","울산","신울산S/S CB 7372","20-21년 울산전력지사 변전총액공사","7372 차단기 동작시험 및 A,B상 전자변 교체","2021-04-26 09:00","2021-04-26 18:00","2021-04-26 09:00","2021-04-26 18:00","연속"]
[208,"부산울산","울산","신울산S/S CB 7471","20-21년 울산전력지사 변전총액공사","7471 차단기 동작시험 및 A,B상 전자변 교체","2021-04-27 09:00","2021-04-27 18:00","2021-04-27 09:00","2021-04-27 18:00","연속"]
[209,"부산울산","울산","신울산S/S CB 7400","20-21년 울산전력지사 변전총액공사","7400,7572 차단기 동작시험","2021-04-28 09:00","2021-04-28 14:00","2021-04-28 09:00","2021-04-28 14:00","연속"]
[210,"부산울산","울산","신울산S/S CB 7572","20-21년 울산전력지사 변전총액공사","7400,7572 차단기 동작시험","2021-04-28 14:00","2021-04-28 18:00","2021-04-28 14:00","2021-04-28 18:00","연속"]
[211,"부산울산","울산","북부산울산TP#2 T/L","345kV 남울산분기T/L 건설사업","작업내용 : 345kV 남울산-울산TP #2, 남울산-신온산 #1 전력선 연긴선(안전이격)","2021-04-19 07:00","2021-04-30 18:00","2021-04-19 07:00","2021-04-30 18:00","연속"]
[212,"부산울산","울산","북부산울산TP#2 T/L","울산복합S/Y 345kV SW증설공사","345kV 울산복합-북부산#2T/L 송전선로 계통연결 후 본가압","2021-04-16 09:00","2021-04-16 18:00","2021-04-16 09:00","2021-04-16 18:00","연속"]
[213,"부산울산","울산","울산C/C #2 Tie-Tr","20-21년 변전정비회사 총액공사","51T관련 3차측 CT 점검(보호제어과) - 43PDA 교체 - 2차 GIS는 하반기 정밀점검 - 2차 LA 대체는 동해전력지사 대여해준거 받으면 대체 - 3차 GIS(LS) DS 보수","2021-04-22 09:00","2021-04-22 18:00","취소","취소","연속"]
[214,"부산울산","울산","울주S/S CB 7A00","20-21년 울산전력지사 변전총액공사","7A00 차단기 동작시험","2021-04-01 09:00","2021-04-01 18:00","2021-04-01 09:00","2021-04-01 18:00","연속"]
[215,"부산울산","울산","울주S/S CB 7771","20-21년 울산전력지사 변전총액공사","7771, 7871 차단기 동작시험","2021-04-02 09:00","2021-04-02 14:00","2021-04-02 09:00","2021-04-02 14:00","연속"]
[216,"부산울산","울산","울주S/S #3 M.Tr","20-21년 울산전력지사 변전총액공사","1,2차 LA 대체 - #3S.Tr 보통점검","2021-04-30 09:00","2021-04-30 18:00","2021-04-30 09:00","2021-04-30 18:00","연속"]
[217,"부산울산","울산","울주S/S #4 M.Tr","20-21년 울산전력지사 변전총액공사","7872 차단기 동작시험 - 1,2차 LA 대체 - #4S.Tr 보통점검","2021-04-16 09:00","2021-04-16 18:00","2021-04-16 09:00","2021-04-16 18:00","연속"]
[218,"부산울산","울산","울주S/S CB 7871","20-21년 울산전력지사 변전총액공사","7771, 7871 차단기 동작시험","2021-04-02 14:00","2021-04-02 18:00","2021-04-02 14:00","2021-04-02 18:00","연속"]
[219,"부산울산","직할","신대연S/S #1 M.Tr","신대연S/S 종합예방진단시스템 설치관련 실측(안전이격)","신대연S/S 종합예방진단시스템 OLTC PD 측정장치 설치관련","2021-04-22 10:00","2021-04-22 18:00","2021-04-22 10:00","2021-04-22 18:00","연속"]
[220,"부산울산","직할","신대연S/S #2 M.Tr","신대연S/S 종합예방진단시스템 설치관련 실측(안전이격)","신대연S/S 종합예방진단시스템 OLTC PD 측정장치 설치관련","2021-04-23 10:00","2021-04-23 18:00","2021-04-23 10:00","2021-04-23 18:00","연속"]
[221,"경남","직할","신김해S/S CB 7200","신김해S/S 7200CB 보통점검","신김해S/S 7200CB 보통점검","2021-04-30 09:30","2021-04-30 17:30","2021-04-30 09:30","2021-04-30 17:30","연속"]
[222,"경남","진주","의령S/S CB 7900","의령S/S 345kV 의령-신마산#1T/L- TIE B상 CT박스교체","의령S/S 345kV 의령-신마산#1T/L- TIE B상 CT박스교체","2021-04-01 10:00","2021-04-02 18:00","2021-04-01 10:00","2021-04-02 18:00","연속"]
[223,"경남","진주","광양하동TP#1 T/L","345kV 광양-하동화력T/L 전력선 교체 공사","광양-하동화력T/L No.14~17호 접속설비 해소를 위한 전선교체공사 2. 광양-하동화력T/L No.1~25호 추락방지시설 설치","2021-04-14 07:00","2021-04-20 19:00","2021-04-14 07:00","2021-04-20 19:00","연속"]
[224,"경남","진주","광양하동TP#2 T/L","345kV 광양-하동화력T/L 전력선 교체 공사","광양-하동화력T/L No.14~17호 접속설비 해소를 위한 전선교체공사 2. 광양-하동화력T/L No.1~25호 추락방지시설 설치","2021-04-21 07:00","2021-04-27 19:00","2021-04-21 07:00","2021-04-27 19:00","연속"]
[225,"경남","진주","하동T/P CB 7200","하동T/P 345kV #2M.Tr 1차 TIE GIS(7200) 보통점검","하동T/P 345kV #2M.Tr 1차 TIE GIS(7200) 보통점검","2021-04-06 10:00","2021-04-06 16:00","2021-04-06 10:00","2021-04-06 16:00","연속"]
[226,"경남","진주","하동T/P CB 7572","하동T/P 345kV #5M.Tr 1차 GIS(7572) 조작시험","하동T/P 345kV #5M.Tr 1차 GIS(7572) 조작시험 [병행] 7522 C상 PT 및 상부모선 배관누기 관련 O-RING 교체","2021-04-12 10:00","2021-04-13 18:00","2021-04-12 10:00","2021-04-13 18:00","연속"]
[227,"경남","진주","하동T/P CB 7500","하동T/P 345kV #5M.Tr 1차 TIE GIS(7500) 조작시험","하동T/P 345kV #5M.Tr 1차 TIE GIS(7500) 조작시험 [병행] 7522 C상 PT 및 상부모선 배관누기 관련 O-RING 교체","2021-04-12 13:00","2021-04-13 18:00","2021-04-12 13:00","2021-04-13 18:00","연속"]
[228,"경남","진주","하동T/P CB 7672","하동T/P 345kV #6M.Tr 1차 GIS(7672) 조작시험","하동T/P 345kV #6M.Tr 1차 GIS(7672) 조작시험","2021-04-15 10:00","2021-04-15 16:00","2021-04-15 10:00","2021-04-15 16:00","연속"]
[229,"경남","통영","신고성S/S #3 M.Tr","신고성S/S #3M.Tr 보호반 대체","신고성S/S #3M.Tr 보호반 대체","2021-04-26 09:30","2021-04-30 18:00","2021-04-26 09:30","2021-04-30 18:00","연속"]
[230,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력T/L 추락방지시설 설치 공사","추락방지시설 설치(하동-하동화력T/L 병가구간)","2021-04-18 10:00","2021-04-18 19:00","2021-04-18 10:00","2021-04-18 19:00","연속"]
[231,"경남","진주","의령하동화력#2 T/L","345kV 75BAY B/F PNL 대체공사","345kV 75BAY B/F PNL 대체공사","2021-04-19 09:00","2021-04-22 18:00","2021-04-19 09:00","2021-04-22 18:00","연속"]
[232,"인천",null,"인천C/C #1,2GT 주변압기 CB 7500, 7572","보호계전기 시험 및 정기검사","보호계전기 시험 및 정기검사","2021-04-05 09:00","2021-05-20 18:00","2021-04-05 09:00","2021-05-20 18:00","연속"]
[233,"인천",null,"인천C/C #1ST 주변압기 CB 7600, 7672","보호계전기 시험 및 정기검사","보호계전기 시험 및 정기검사","2021-04-05 09:00","2021-05-20 18:00","2021-04-05 09:00","2021-05-20 18:00","연속"]
[234,"부산울산",null,"부산C/C #5,6GT 주변압기 CB 7500, 7571","부산복합 계획예방정비관련 변압기 점검","부산복합 계획예방정비관련 변압기 점검","2021-04-06 09:00","2021-06-30 18:00","2021-04-06 09:00","2021-06-30 18:00","연속"]
[235,"경북",null,"한울N/P #3호기 주변압기 CB 7900, 7972","3호기 16차 계획예방정비","○ 주변압기 및 소내/대기보조변압기 정밀점검 ○ 보호계전기 개체/연동시험 등 ○ 주발전기 재권선 공사","2021-04-23 10:00","2021-05-30 16:00","2021-04-23 10:00","2021-05-30 16:00","연속"]
[236,"대구",null,"월성N/P #1 기동용 변압기 CB 7671, 7600","월성 1호기 제1차 영구정지 안전유지설비 점검 ","○ 홀수모선 휴전작업","2021-04-12 09:00","2021-04-16 18:00","2021-04-12 09:00","2021-04-16 18:00","연속"]
[237,"대구",null,"월성N/P #1 기동용 변압기 CB 7671, 7600","월성 1호기 제3차 안전유지설비점검 관련 전원절체시험","○ SST->UST 소내전원절체시험","2021-04-19 09:00","2021-04-21 18:00","2021-04-19 09:00","2021-04-21 18:00","연속"]
[238,"대구",null,"월성N/P #1호기 주변압기 CB 7200, 7272","월성 1호기 제2차 안전유지설비점검 관련 전원절체시험","○ UST->SST 소내전원절체시험","2021-04-19 09:00","2021-04-21 18:00","2021-04-19 09:00","2021-04-21 18:00","연속"]
[239,"광주전남",null,"여수T/P #1 Tie-Tr","무부하가압","무부하가압","2021-04-27 11:00","2021-04-28 11:00","2021-04-27 11:00","2021-04-28 11:00","연속"]
[240,"광주전남",null,"광양S/S #2 M.Tr","345kV 광양S/S 362kV GIS 용량변경대체공사(무부하가압)","345kV 광양S/S 362kV GIS 용량변경대체공사(무부하가압) - 71,72,73 Bay 측 모선 교체","2021-04-28 10:00","2021-04-29 10:00","2021-04-28 10:00","2021-04-30 18:00","연속"]

{"sheet":"154설비","index":2,"n_rows":614,"n_cols":11,"rows_kept":614,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2021년도 4월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","미금광장 T/L","2021년 성동P/O 변전정비회사 총액공사","154kV GIS 보통점검","2021-04-29 10:00","2021-04-29 18:00","2021-04-29 10:00","2021-04-29 18:00","연속"]
[2,"서울","성동","화양광장 T/L","2021년 성동P/O 변전정비회사 총액공사","154kV GIS 보통점검","2021-04-30 10:00","2021-04-30 18:00","2021-04-30 10:00","2021-04-30 18:00","연속"]
[3,"서울","성동","구의광장#2 T/L","154kV 구의S/S 가스변압기 교체공사(3차분 무부하가압)","154kV 구의S/S 가스변압기 교체공사(3차분 무부하가압)","2021-04-19 10:00","2021-04-21 10:00","2021-04-19 10:00","2021-04-21 10:00","연속"]
[4,"서울","성동","광장뚝도#1 T/L","2021년 성동P/O 154kV GIS 정밀점검공사","뚝도S/S 광장뚝도#1T/L GIS 정밀점검","2021-04-12 09:30","2021-04-13 17:30","2021-04-12 09:30","2021-04-13 17:30","연속"]
[5,"서울","성동","성동S/S CB 6100","모선보호반 계전기 성능개선","모선보호용 86B Reset 회로 및 BF회로 성능개선","2021-04-08 10:00","2021-04-08 14:00","2021-04-08 10:00","2021-04-08 14:00","연속"]
[6,"서울","성동","성동S/S CB 6200","모선보호반 계전기 성능개선","모선보호용 86B Reset 회로 및 BF회로 성능개선","2021-04-08 14:00","2021-04-08 18:00","2021-04-08 14:00","2021-04-08 18:00","연속"]
[7,"서울","성동","화양성수 T/L","2021년 성동P/O 변전정비회사 총액공사","154kV GIS 보통점검(성수), 조작시험(화양)","2021-04-09 09:30","2021-04-09 18:00","2021-04-09 09:30","2021-04-09 18:00","연속"]
[8,"서울","성동","군자성수 T/L","2021년 성동P/O 변전정비회사 총액공사","154kV GIS 보통점검(성수), 조작시험(군자)","2021-04-08 09:30","2021-04-08 18:00","2021-04-08 09:30","2021-04-08 18:00","연속"]
[9,"서울","성동","성수뚝도#1 T/L","2021년 성동P/O 변전정비회사 총액공사","154kV GIS 보통점검 (양단)","2021-04-05 09:30","2021-04-05 18:00","2021-04-05 09:30","2021-04-05 18:00","연속"]
[10,"서울","성동","양주쌍문#1 T/L","2021년 성동P/O 변전정비회사 총액공사","154kV GIS 보통점검","2021-04-12 10:00","2021-04-12 17:00","2021-04-12 10:00","2021-04-12 17:00","연속"]
[11,"서울","성동","왕십리용두 T/L","21년 성동P/O 노후 보호배전반 교체공사","왕십리, 용두S/S 154kV 왕십리-용두T/L 보호배전반 노후대체","2021-04-26 10:00","2021-04-29 17:00","2021-04-26 10:00","2021-04-29 17:00","연속"]
[12,"서울","성동","상봉휘경#2 T/L","2021년 성동P/O 변전정비회사 총액공사","154kV GIS 하자점검","2021-04-19 10:00","2021-04-19 18:00","2021-04-19 10:00","2021-04-19 18:00","연속"]
[13,"서울","중부","당인리여의 T/L","서울복합발전소 내 지장송전선로 이설공사","발전소내 맨홀#4(JB24,23) 구조물 연장 시공에 따른 근접 선로 휴전\n(해당선로 : 당인리여의, 중부용산#1T/L 동시휴전)","2021-04-15 09:00","2021-05-30 18:00","취소","취소","연속"]
[14,"서울","중부","원흥상암 T/L","2020~2021 가공송전 정비회사 총액공사","불량애자교체 및 점퍼지지애자 교체","2021-03-08 07:30","2021-03-08 18:00","2021-04-09 07:30","2021-04-09 18:00","연속"]
[15,"서울","중부","수색S/S CB 6100","수색S/S 154kV BUSTIE 이설공사","154kV BUSTIE GCB 이설","2021-04-05 09:00","2021-04-14 18:00","2021-04-05 09:00","2021-04-14 18:00","연속"]
[16,"서울","중부","수색S/S 154kV #2 BUS","수색S/S 154kV BUSTIE 이설공사","154kV #2DS 및 GCB 모선연결 o 154kV #2DS 및 GCB 시험가압","2021-04-08 16:00","2021-04-14 18:00","2021-04-08 16:00","2021-04-14 18:00","연속"]
[17,"서울","중부","수색S/S 154kV #1 BUS","수색S/S 154kV BUSTIE 이설공사","154kV #1DS 및 GCB 설치 ㅇ 154kV LA 이설","2021-04-05 09:00","2021-04-08 16:00","2021-04-05 09:00","2021-04-08 16:00","연속"]
[18,"서울","중부","원흥수색#1 T/L","21년 중부전력 변전정비회사 총액공사","170kV GIS 조작시험,T2코일 미세조정","2021-04-23 10:00","2021-04-23 18:00","2021-04-23 10:00","2021-04-23 18:00","연속"]
[19,"서울","중부","양주은평#2 T/L","양주-은평 안전이격 확보공사","철탑 1기 철거 및 신설","2021-04-26 07:30","2021-05-23 18:00","2021-04-26 07:30","2021-05-23 18:00","연속"]
[20,"서울","중부","은평녹번#1 T/L","154kV 은평-녹번T/L 케이블 선종교체공사","은평S/S ~ J/B#3, 3구간 (종단접속 1개소, 중간접속 3개소) OF-XLPE 선종교체공사","2021-04-12 09:00","2021-07-16 18:00","2021-04-12 09:00","2021-07-16 18:00","연속"]
[21,"서울","중부","양주은평#1 T/L","양주-은평 안전이격 확보공사","철탑 1기 철거 및 신설","2021-04-19 07:30","2021-04-25 18:00","2021-04-19 07:30","2021-04-25 18:00","연속"]
[22,"서울","중부","중부아현 T/L","21년 중부전력 변전정비회사 총액공사","송전선로 보호반 대체, 170kV GIS 조작시험","2021-04-12 10:00","2021-04-15 18:00","2021-04-12 10:00","2021-04-15 18:00","연속"]
[23,"서울","중부","중부S/S SEC CB 65660","21년 중부전력 변전정비회사 총액공사","170kV GIS 조작시험","2021-04-05 10:00","2021-04-05 18:00","2021-04-05 10:00","2021-04-05 18:00","연속"]
[24,"서울","중부","중부S/S CB 6200","모선보호반 계전기 성능개선","모선보호용 86B Reset 회로 및 BF회로 성능개선","2021-04-02 14:00","2021-04-02 18:00","2021-04-02 14:00","2021-04-02 18:00","연속"]
[25,"서울","중부","중부S/S CB 6100","모선보호반 계전기 성능개선","모선보호용 86B Reset 회로 및 BF회로 성능개선","2021-04-02 10:00","2021-04-02 14:00","2021-04-02 10:00","2021-04-02 14:00","연속"]
[26,"서울","중부","중부S/S SEC CB 60610","21년 중부전력 변전정비회사 총액공사","170kV GIS 조작시험","2021-04-01 10:00","2021-04-01 18:00","2021-04-01 10:00","2021-04-01 18:00","연속"]
[27,"서울","중부","중부용산#1 T/L","서울복합발전소 내 지장송전선로 이설공사","발전소 내 맨홀#4(JB#24,23) 구조물 연장시공에 따른 휴전\n(해당선로 : 중부용산1, 당인리여의T/L )","2021-04-15 09:00","2021-05-30 18:00","2021-04-15 09:00","2021-05-30 18:00","연속"]
[28,"서울","중부","지축현저#2 T/L","2020~2021 가공송전 정비회사 총액공사","지축현저#2 No.4 피뢰기 설치","2021-03-10 07:30","2021-03-10 18:00","2021-04-10 07:30","2021-04-10 18:00","연속"]
[29,"서울","중부","지축현저#1 T/L","2020~2021 가공송전 정비회사 총액공사","수색은평#2 No.4 4회선 철탑 피뢰기 설치에 따른 병가선로 휴전","2021-03-09 07:30","2021-03-09 18:00","2021-04-11 07:30","2021-04-11 18:00","연속"]
[30,"서울","중부","현저서대문#2 T/L","21년 중부전력 변전정비회사 총액공사","170kV GIS 초기점검","2021-04-02 10:00","2021-04-02 18:00","2021-04-02 10:00","2021-04-02 18:00","연속"]
[31,"서울","중부","현저서대문#1 T/L","21년 중부전력 변전정비회사 총액공사","170kV GIS 초기점검","2021-04-01 10:00","2021-04-01 18:00","2021-04-01 10:00","2021-04-01 18:00","연속"]
[32,"서울","직할","서소문S/S CB 6100","21년 직할 변전협력 총액공사","GIS조작시험","2021-04-05 10:00","2021-04-05 18:00","2021-04-05 10:00","2021-04-05 18:00","연속"]
[33,"남서울","강남","대치논현#1 T/L","170kV GIS 하자점검-변전협력","170kV GIS 하자점검-변전협력","2021-04-08 10:00","2021-04-08 18:00","2021-04-08 10:00","2021-04-08 18:00","연속"]
[34,"남서울","강남","대치논현#2 T/L","170kV GIS 하자점검-변전협력","170kV GIS 하자점검-변전협력","2021-04-09 10:00","2021-04-09 18:00","2021-04-09 10:00","2021-04-09 18:00","연속"]
[35,"남서울","강남","동빙고반포#2 T/L","170kV GIS 개폐타임-변전협력","170kV GIS 개폐타임-변전협력","2021-04-15 14:00","2021-04-15 18:00","2021-04-15 14:00","2021-04-15 18:00","연속"]
[36,"남서울","강남","동빙고반포#1 T/L","170kV GIS 개폐타임-변전협력","170kV GIS 개폐타임-변전협력","2021-04-15 10:00","2021-04-15 14:00","2021-04-15 10:00","2021-04-15 14:00","연속"]
[37,"남서울","강남","신성남염곡#2 T/L","신성남-염곡#1,2T/L 자기애관 교체공사","신성남-염곡#1,2T/L 자기애관 교체공사","2021-04-26 09:00","2021-05-02 18:00","취소","취소","연속"]
[38,"남서울","강남","신성남염곡#1 T/L","신성남-염곡#1,2T/L 자기애관 교체공사","신성남-염곡#1,2T/L 자기애관 교체공사","2021-04-19 09:00","2021-04-25 18:00","취소","취소","연속"]
[39,"남서울","동서울","강남S/S CB 6200","170kV GIS 보호반성능개선","170kV GIS 보호반성능개선","2021-04-06 09:00","2021-04-06 13:00","취소","취소","연속"]
[40,"남서울","동서울","강남S/S CB 6100","170kV GIS 보호반성능개선","170kV GIS 보호반성능개선","2021-04-06 13:00","2021-04-06 18:00","취소","취소","연속"]
[41,"남서울","동서울","강동천호#1 T/L","170kV GIS 조작시험,보통점검","170kV GIS 조작시험(전자변교체),보통점검","2021-04-16 09:00","2021-04-16 18:00","2021-04-16 09:00","2021-04-16 18:00","연속"]
[42,"남서울","동서울","강동천호#2 T/L","170kV GIS 조작시험,보통점검","170kV GIS 조작시험(전자변교체),보통점검","2021-04-19 09:00","2021-04-19 18:00","2021-04-19 09:00","2021-04-19 18:00","연속"]
[43,"남서울","동서울","동서울서종#2 T/L","20-21년 가공송전 협력회사 총액공사","154kV 동서울-서종T/L 전선접속개소 전선교체공사","2021-04-12 09:00","2021-04-16 18:00","2021-04-12 09:00","2021-04-16 18:00","연속"]
[44,"남서울","동서울","동서울신장#1 T/L","2021년도 동서울P/O 가공송전 순시점검 위탁공사","#1T/L 정밀점검(동서울S/T~신장C/H) / 한전KPS 작업","2021-04-12 08:00","2021-04-14 18:00","2021-04-12 08:00","2021-04-14 18:00","연속"]
[45,"남서울","동서울","동서울서종#1 T/L","20-21년 가공송전 협력회사 총액공사","154kV 동서울-서종T/L 전선접속개소 전선교체공사","2021-04-05 09:00","2021-04-09 18:00","2021-04-05 09:00","2021-04-09 18:00","연속"]
[46,"남서울","동서울","동서울신장#2 T/L","2021년도 동서울P/O 가공송전 순시점검 위탁공사","#2T/L 정밀점검(동서울S/T~신장C/H) / 한전KPS 작업","2021-04-19 08:00","2021-04-21 18:00","2021-04-19 08:00","2021-04-21 18:00","연속"]
[47,"남서울","동서울","석촌S/S CB 6100","170kV GIS 보호반성능개선","170kV GIS 보호반성능개선","2021-04-12 13:00","2021-04-12 18:00","취소","취소","연속"]
[48,"남서울","동서울","가락수서#1 T/L","170kV GIS 정기점검","170kV GIS 조작시험","2021-04-20 09:00","2021-04-20 13:00","2021-04-30 09:00","2021-04-30 13:00","연속"]
[49,"남서울","동서울","가락수서#2 T/L","170kV GIS 정기점검","170kV GIS 조작시험","2021-04-20 13:00","2021-04-20 18:00","2021-04-30 13:00","2021-04-30 18:00","연속"]
[50,"남서울","동서울","위례S/S 154kV #65 BUS","154kV 동서울-위례 SW 증설공사","170kV GIS 2CCT 설치","2021-04-30 09:00","2021-05-03 18:00","취소","취소","연속"]
[51,"남서울","동서울","위례S/S CB 6200","170kV GIS 하자점검, 보호반성능개선","170kV GIS 하자점검, 보호반성능개선","2021-04-05 09:00","2021-04-05 13:00","취소","취소","연속"]
[52,"남서울","동서울","동남위례#1 T/L","154kV 동서울-위례 SW 증설공사","170kV GIS 2CCT 설치 무부하가압","2021-04-28 17:00","2021-04-29 18:00","취소","취소","연속"]
[53,"남서울","동서울","위례S/S CB 6100","170kV GIS 하자점검, 보호반성능개선","170kV GIS 하자점검, 보호반성능개선","2021-04-05 13:00","2021-04-05 18:00","취소","취소","연속"]
[54,"남서울","동서울","위례S/S SEC CB 65660","위례S/S 154kV 65-66 SEC CB 하자점검","위례S/S 154kV 65-66 SEC CB 하자점검","2021-04-07 09:00","2021-04-07 13:00","취소","취소","연속"]
[55,"남서울","동서울","위례S/S SEC CB 60610","위례S/S 154kV 60-61 SEC CB 하자점검","위례S/S 154kV 60-61 SEC CB 하자점검","2021-04-07 13:00","2021-04-07 18:00","취소","취소","연속"]
[56,"남서울","동서울","위례S/S 154kV #60 BUS","154kV 동서울-위례 SW 증설공사","170kV GIS 2CCT 설치","2021-04-26 09:00","2021-04-29 18:00","취소","취소","연속"]
[57,"남서울","동서울","풍납S/S CB 6100","170kV GIS 보호반성능개선","170kV GIS 보호반성능개선","2021-04-12 09:00","2021-04-12 13:00","취소","취소","연속"]
[58,"남서울","동서울","풍납석촌#2 T/L","170kV GIS 보호반교체","170kV GIS 보호반교체","2021-04-13 09:00","2021-04-16 18:00","취소","취소","연속"]
[59,"남서울","동서울","풍납석촌#1 T/L","170kV GIS 보호반교체","170kV GIS 보호반교체","2021-04-05 09:00","2021-04-08 18:00","취소","취소","연속"]
[60,"남서울","영등포","광명S/S 154kV #2 BUS","광명S/S 신광명-광명#2T/L GIS 2DS 보수","#2DS부 가동자 및 고동자 교체","2021-04-03 09:00","2021-04-04 18:00","취소","취소","연속"]
[61,"남서울","영등포","신광명광명#1 T/L","광명S/S 신광명-광명#2T/L GIS 2DS 보수","#2DS부 가동자 및 고동자 교체","2021-04-03 09:00","2021-04-04 18:00","2021-04-03 09:00","2021-04-04 18:00","연속"]
[62,"남서울","영등포","신광명광명#2 T/L","광명S/S 신광명-광명#2T/L GIS 2DS 보수","#2DS부 가동자 및 고동자 교체","2021-04-03 09:00","2021-04-04 18:00","2021-04-03 09:00","2021-04-04 18:00","연속"]
[63,"남서울","영등포","신광명구공#1 T/L","20~21 영등포PO 변전정비회사 총액공사","170kV GIS 초기점검","2021-04-01 09:00","2021-04-01 18:00","취소","취소","연속"]
[64,"남서울","영등포","신광명구공#2 T/L","20~21 영등포PO 변전정비회사 총액공사","170kV GIS 초기점검","2021-04-02 09:00","2021-04-02 18:00","취소","취소","연속"]
[65,"남서울","영등포","구로S/S CB 6100","20~21 영등포PO 변전정비회사 총액공사","모선통합 - M.Tr 보호배전반 교체관련 사전조작","2021-04-05 09:00","2021-04-09 18:00","2021-04-05 09:00","2021-04-09 18:00","연속"]
[66,"남서울","영등포","구로S/S CB 6100","20~21 영등포PO 변전정비회사 총액공사","모선통합 - M.Tr 보호배전반 교체관련 사전조작","2021-04-12 09:00","2021-04-16 18:00","2021-04-12 09:00","2021-04-16 18:00","연속"]
[67,"남서울","영등포","독산대방#2 T/L","2020년 영등포P/O 170kV GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정","2021-04-01 09:00","2021-04-02 18:00","2021-04-01 09:00","2021-04-02 18:00","연속"]
[68,"남서울","영등포","독산S/S CB 6100","독산S/S 154kV 모선보호반 성능개선","영인제 모선보호반 성능개선","2021-04-14 09:00","2021-04-14 18:00","취소","취소","연속"]
[69,"남서울","영등포","양천S/S 154kV #2 BUS","154kV 양평-양천T/L 선종교체공사","선종 및 회선길이 : 154kV XLPE 2,000㎟ × 2회선(S)-0.992km, - 154kV XLPE 1,200㎟ × 2회선(B)","2021-04-16 10:00","2021-04-16 15:00","취소","취소","연속"]
[70,"남서울","영등포","중동화곡#1 T/L","화곡S/S 170kV GIS 전자변 교체, 조작시험(중동-화곡#1)","공압식 차단기 지연트립 발생 관련 전자변 교체 시행 - 차단기 조작시험","2021-04-08 09:00","2021-04-08 14:00","취소","취소","연속"]
[71,"남서울","영등포","중동화곡#2 T/L","화곡S/S 170kV GIS 전자변 교체, 조작시험(중동-화곡#1)","공압식 차단기 지연트립 발생 관련 전자변 교체 시행 - 차단기 조작시험","2021-04-08 14:00","2021-04-08 18:00","취소","취소","연속"]
[72,"남서울","직할","양평S/S CB 6100","170kV GIS 조작시험 및 모선보호반 성능개선","170kV GIS 조작시험 모선보호반 성능개선","2021-04-19 09:00","2021-04-19 14:00","취소","취소","연속"]
[73,"남서울","직할","여의노량진 T/L","170kV GIS 정밀점검공사_#1M.Tr 무부하 가압","170kV GIS 정밀점검공사_#1M.Tr 무부하 가압","2021-04-10 09:00","2021-04-10 14:00","취소","취소","연속"]
[74,"남서울","직할","당인리여의 T/L","170kV GIS 정밀점검공사","170kV GIS 정밀점검공사","2021-04-01 09:00","2021-04-03 14:00","취소","취소","연속"]
[75,"남서울","직할","여의노량진 T/L","170kV GIS 정밀점검공사_#2M.Tr 무부하 가압","170kV GIS 정밀점검공사_#2M.Tr 무부하 가압","2021-04-14 09:00","2021-04-14 14:00","취소","취소","연속"]
[76,"남서울","직할","여의노량진 T/L","170kV GIS 정밀점검공사_#3M.Tr 무부하 가압","170kV GIS 정밀점검공사_#3M.Tr 무부하 가압","2021-04-16 13:00","2021-04-16 18:00","취소","취소","연속"]
[77,"남서울","직할","여의S/S 154kV #1 BUS","170kV GIS 정밀점검공사_#3M.Tr 무부하 가압","170kV GIS 정밀점검공사_#3M.Tr 무부하 가압","2021-04-16 13:00","2021-04-16 18:00","취소","취소","연속"]
[78,"남서울","직할","여의S/S 154kV #1 BUS","170kV GIS 정밀점검공사_#1M.Tr 무부하 가압","170kV GIS 정밀점검공사_#1M.Tr 무부하 가압","2021-04-10 09:00","2021-04-10 14:00","취소","취소","연속"]
[79,"남서울","직할","여의S/S 154kV #2 BUS","170kV GIS 정밀점검공사_#2M.Tr 무부하 가압","170kV GIS 정밀점검공사_#2M.Tr 무부하 가압","2021-04-14 09:00","2021-04-14 14:00","취소","취소","연속"]
[80,"인천","김포","경서양촌#2 T/L","경서S/S 154kV 경서-양촌#2T/L GIS 정밀점검","경서S/S 154kV 경서-양촌#2T/L GIS 정밀점검","2021-04-28 09:00","2021-04-30 18:00","2021-04-28 09:00","2021-04-30 18:00","연속"]
[81,"인천","김포","경서양촌#2 T/L","경서S/S 154kV 경서-양촌#2T/L GIS 정밀점검","경서S/S 154kV 경서-양촌#2T/L GIS 정밀점검","2021-04-28 09:00","2021-04-30 18:00","취소","취소","연속"]
[82,"인천","김포","양촌양곡#2 T/L","20년도 가공송전순시점검 위탁공사(초기점검)","154kV 양촌_양곡T/L 초기점검 대상 : No.1,2,3,8,9,10,12,13,14","2021-04-02 09:00","2021-04-02 18:00","2021-04-02 09:00","2021-04-02 18:00","연속"]
[83,"인천","김포","양촌양곡#1 T/L","20년도 가공송전순시점검 위탁공사(초기점검)","154kV 양촌_양곡T/L 초기점검 대상 : No.1,2,3,8,9,10,12,13,14","2021-04-01 09:00","2021-04-01 18:00","2021-04-01 09:00","2021-04-01 18:00","연속"]
[84,"인천","김포","양촌양곡#2 T/L","20년도 가공송전순시점검 위탁공사(초기점검)","154kV 양촌_양곡T/L 초기점검 대상 : No.1,2,3,8,9,10,12,13,14","2021-04-02 09:00","2021-04-02 18:00","취소","취소","연속"]
[85,"인천","김포","양촌양곡#1 T/L","20년도 가공송전순시점검 위탁공사(초기점검)","154kV 양촌_양곡T/L 초기점검 대상 : No.1,2,3,8,9,10,12,13,14","2021-04-01 09:00","2021-04-01 18:00","취소","취소","연속"]
[86,"인천","시흥","신시흥남동#1 T/L","154kV 신시흥-남동#1 T/L 선종교체공사","남동EBG~J/B#2 0.926km 교체(OF→XLPE)","2021-04-30 16:00","2021-06-30 18:00","취소","취소","연속"]
[87,"인천","시흥","신시흥남동#1 T/L","154kV 신시흥-남동#1 T/L 선종교체공사","남동EBG~J/B#2 0.926km 교체(OF→XLPE)","2021-04-30 16:00","2021-06-30 18:00","취소","취소","연속"]
[88,"인천","시흥","시화동시화#1 T/L","동시화S/S 154kV 시화-동시화#1T/L GIS 조작시험","동시화S/S 154kV 시화-동시화#1T/L GIS 조작시험","2021-04-20 10:00","2021-04-20 18:00","2021-04-20 10:00","2021-04-20 18:00","연속"]
[89,"인천","시흥","시화동시화#2 T/L","동시화S/S 154kV 시화-동시화#2T/L GIS 조작시험","동시화S/S 154kV 시화-동시화#2T/L GIS 조작시험","2021-04-21 10:00","2021-04-21 18:00","2021-04-21 10:00","2021-04-21 18:00","연속"]
[90,"인천","시흥","시화동시화#2 T/L","동시화S/S 154kV 시화-동시화#2T/L GIS 조작시험","동시화S/S 154kV 시화-동시화#2T/L GIS 조작시험","2021-04-21 10:00","2021-04-21 18:00","취소","취소","연속"]
[91,"인천","시흥","시화동시화#1 T/L","동시화S/S 154kV 시화-동시화#1T/L GIS 조작시험","동시화S/S 154kV 시화-동시화#1T/L GIS 조작시험","2021-04-20 10:00","2021-04-20 18:00","취소","취소","연속"]
[92,"인천","시흥","북시화서시화#2 T/L","북시화,서시화S/S 154kV 북시화서시화SA#2 T/L GIS 초기점검","북시화,서시화S/S 154kV 북시화서시화SA#2 T/L GIS 초기점검","2021-04-14 10:00","2021-04-14 18:00","2021-04-14 10:00","2021-04-14 18:00","연속"]
[93,"인천","시흥","동시화서시화 T/L","서시화S/S 170kV GIS 대체공사(3차)","북시화서시화#1T/L, #1M.Tr, 170kV BUS-TIE GIS 대체(무부하가압 24시간)","2021-04-08 17:00","2021-04-09 18:00","2021-04-08 17:00","2021-04-09 18:00","연속"]
[94,"인천","시흥","동시화서시화 T/L","서시화S/S 170kV GIS 대체공사(3차)","북시화서시화#1T/L, #1M.Tr, 170kV BUS-TIE GIS 대체(무부하가압 24시간)","2021-04-08 17:00","2021-04-09 18:00","취소","취소","연속"]
[95,"인천","시흥","동시화서시화 T/L","서시화S/S 170kV GIS 대체공사(3차)","북시화서시화#1T/L, #1M.Tr, 170kV BUS-TIE GIS 대체(무부하가압 24시간)","2021-04-05 15:00","2021-04-06 16:30","2021-04-05 15:00","2021-04-06 16:30","연속"]
[96,"인천","시흥","동시화서시화 T/L","서시화S/S 170kV GIS 대체공사(3차)","북시화서시화#1T/L, #1M.Tr, 170kV BUS-TIE GIS 대체(무부하가압 24시간)","2021-04-05 15:00","2021-04-06 16:30","취소","취소","연속"]
[97,"인천","시흥","북시화서시화#2 T/L","북시화,서시화S/S 154kV 북시화서시화SA#2 T/L GIS 초기점검","북시화,서시화S/S 154kV 북시화서시화SA#2 T/L GIS 초기점검","2021-04-14 10:00","2021-04-14 18:00","취소","취소","연속"]
[98,"인천","시흥","신광명소래 T/L","154kV 서서울-소래T/L OPGW 증설공사","OPGW 24C→48C 교체 (No.63~No.76)","2021-04-04 08:00","2021-04-04 18:00","2021-04-04 08:00","2021-04-04 18:00","연속"]
[99,"인천","시흥","신광명소래 T/L","154kV 서서울-소래T/L OPGW 증설공사","OPGW 24C→48C 교체 (No.63~No.76)","2021-04-04 08:00","2021-04-04 18:00","취소","취소","연속"]
[100,"인천","시흥","온수소래 T/L","154kV 서서울-소래T/L OPGW 증설공사","GW→OPGW 교체 및 신규 48C 시설 (No.76~No.92)","2021-04-03 08:00","2021-04-03 18:00","2021-04-03 08:00","2021-04-03 18:00","연속"]
[101,"인천","시흥","서서울소래 T/L","154kV 서서울-소래T/L OPGW 증설공사","OPGW 24C→48C 교체 (서안양C/H~No.53~No.76)","2021-04-04 08:00","2021-04-07 18:00","2021-04-04 08:00","2021-04-07 18:00","연속"]
[102,"인천","시흥","서서울소래 T/L","154kV 서서울-소래T/L OPGW 증설공사","OPGW 24C→48C 교체 (서안양C/H~No.53~No.76)","2021-04-04 08:00","2021-04-07 18:00","취소","취소","연속"]
[103,"인천","시흥","온수소래 T/L","154kV 서서울-소래T/L OPGW 증설공사","GW→OPGW 교체 및 신규 48C 시설 (No.76~No.92)","2021-04-03 08:00","2021-04-03 18:00","취소","취소","연속"]
[104,"인천","직할","임학계양#1 T/L","계양S/S 임학계양#1T/L 170kV GIS 정밀점검","계양S/S 임학계양#1T/L 170kV GIS 정밀점검","2021-04-26 09:00","2021-04-28 18:00","2021-04-26 09:00","2021-04-28 18:00","연속"]
[105,"인천","직할","임학계양#2 T/L","계양S/S 임학계양#2T/L 170kV GIS 정밀점검","계양S/S 임학계양#2T/L 170kV GIS 정밀점검","2021-04-29 09:00","2021-05-01 18:00","2021-04-29 09:00","2021-05-01 18:00","연속"]
[106,"인천","직할","임학계양#2 T/L","계양S/S 임학계양#2T/L 170kV GIS 정밀점검","계양S/S 임학계양#2T/L 170kV GIS 정밀점검","2021-04-29 09:00","2021-05-01 18:00","취소","취소","연속"]
[107,"인천","직할","임학계양#1 T/L","계양S/S 임학계양#1T/L 170kV GIS 정밀점검","계양S/S 임학계양#1T/L 170kV GIS 정밀점검","2021-04-26 09:00","2021-04-28 18:00","취소","취소","연속"]
[108,"인천","직할","신부평고강#2 T/L","고강S/S 신부평고강#2T/L 170kV GIS 보통점검","고강S/S 신부평고강#2T/L 170kV GIS 보통점검","2021-04-03 14:00","2021-04-03 18:00","취소","취소","연속"]
[109,"인천","직할","고강화곡#2 T/L","고강S/S 고강화곡#2T/L 170kV GIS 조작시험","고강S/S 고강화곡#2T/L 170kV GIS 조작시험","2021-04-10 14:00","2021-04-10 18:00","2021-04-10 14:00","2021-04-10 18:00","연속"]
[110,"인천","직할","고강화곡#1 T/L","고강S/S 고강화곡#1T/L 170kV GIS 조작시험","고강S/S 고강화곡#1T/L 170kV GIS 조작시험","2021-04-10 09:00","2021-04-10 14:00","2021-04-10 09:00","2021-04-10 14:00","연속"]
[111,"인천","직할","고강화곡#3 T/L","고강S/S 고강화곡#3T/L 170kV GIS 초기점검","고강S/S 고강화곡#3T/L 170kV GIS 초기점검","2021-04-03 09:00","2021-04-03 14:00","2021-04-03 09:00","2021-04-03 14:00","연속"]
[112,"인천","직할","고강화곡#2 T/L","고강S/S 고강화곡#2T/L 170kV GIS 조작시험","고강S/S 고강화곡#2T/L 170kV GIS 조작시험","2021-04-10 14:00","2021-04-10 18:00","취소","취소","연속"]
[113,"인천","직할","고강화곡#1 T/L","고강S/S 고강화곡#1T/L 170kV GIS 조작시험","고강S/S 고강화곡#1T/L 170kV GIS 조작시험","2021-04-10 09:00","2021-04-10 14:00","취소","취소","연속"]
[114,"인천","직할","고강화곡#3 T/L","고강S/S 고강화곡#3T/L 170kV GIS 초기점검","고강S/S 고강화곡#3T/L 170kV GIS 초기점검","2021-04-03 09:00","2021-04-03 14:00","취소","취소","연속"]
[115,"인천","직할","신부평고강#2 T/L","고강S/S 신부평고강#2T/L 170kV GIS 보통점검","고강S/S 신부평고강#2T/L 170kV GIS 보통점검","2021-04-03 14:00","2021-04-03 18:00","취소","취소","연속"]
[116,"인천","직할","신부평도당#2 T/L","154kV 갈산-부흥,도당 지중T/L 인출정비공사","154kV XLPE 2,000㎟, 2C×0.4km(갈산-도당)설치 및 기설선로 철거","2021-04-23 10:00","2021-05-20 18:00","2021-04-23 10:00","2021-05-20 18:00","연속"]
[117,"인천","직할","신부평도당#2 T/L","154kV 갈산-부흥,도당 지중T/L 인출정비공사","154kV XLPE 2,000㎟, 2C×0.4km(갈산-도당)설치 및 기설선로 철거","2021-04-23 10:00","2021-05-20 18:00","취소","취소","연속"]
[118,"인천","직할","인천CC북인천#1 T/L","북인천S/S 인천CC북인천#1T/L 170kV GIS 정밀점검","북인천S/S 인천CC북인천#1T/L 170kV GIS 정밀점검","2021-04-19 09:00","2021-04-21 18:00","취소","취소","연속"]
[119,"인천","직할","북인천원창 T/L","북인천S/S 북인천원창T/L 170kV GIS 보통점검","북인천S/S 북인천원창T/L 170kV GIS 보통점검","2021-04-27 09:00","2021-04-27 18:00","2021-04-27 09:00","2021-04-27 18:00","연속"]
[120,"인천","직할","계양북인천 T/L","북인천S/S 계양북인천T/L 170kV GIS 보통점검","북인천S/S 계양북인천T/L 170kV GIS 보통점검","2021-04-26 09:00","2021-04-26 18:00","취소","취소","연속"]
[121,"인천","직할","계양북인천 T/L","북인천S/S 계양북인천T/L 170kV GIS 보통점검","북인천S/S 계양북인천T/L 170kV GIS 보통점검","2021-04-26 09:00","2021-04-26 18:00","취소","취소","연속"]
[122,"인천","직할","인천CC북인천#1 T/L","북인천S/S 인천CC북인천#1T/L 170kV GIS 정밀점검","북인천S/S 인천CC북인천#1T/L 170kV GIS 정밀점검","2021-04-19 09:00","2021-04-21 18:00","취소","취소","연속"]
[123,"인천","직할","인천CC북인천#2 T/L","북인천S/S 인천CC북인천#2T/L 170kV GIS 정밀점검","북인천S/S 인천CC북인천#2T/L 170kV GIS 정밀점검","2021-04-22 09:00","2021-04-24 18:00","취소","취소","연속"]
[124,"인천","직할","북인천원창 T/L","북인천S/S 북인천원창T/L 170kV GIS 보통점검","북인천S/S 북인천원창T/L 170kV GIS 보통점검","2021-04-27 09:00","2021-04-27 18:00","취소","취소","연속"]
[125,"인천","직할","인천CC북인천#2 T/L","북인천S/S 인천CC북인천#2T/L 170kV GIS 정밀점검","북인천S/S 인천CC북인천#2T/L 170kV GIS 정밀점검","2021-04-22 09:00","2021-04-24 18:00","취소","취소","연속"]
[126,"인천","직할","신부평고강#1 T/L","154kV 신부평-고강#1T/L 자기애관 교체공사","154kV 신부평-고강#1T/L 자기애관 교체공사","2021-04-17 09:00","2021-04-17 18:00","취소","취소","연속"]
[127,"인천","직할","신부평고강#1 T/L","154kV 신부평-고강#1T/L 자기애관 교체공사","154kV 신부평-고강#1T/L 자기애관 교체공사","2021-04-17 09:00","2021-04-17 18:00","취소","취소","연속"]
[128,"인천","직할","신부평임학#1 T/L","임학S/S 신부평임학#1T/L 전자변교체 및 조작시험","신부평S/S 신부평임학#2T/L 보통점검","2021-04-12 09:30","2021-04-12 18:00","2021-04-12 09:30","2021-04-12 18:00","연속"]
[129,"인천","직할","신부평임학#2 T/L","임학S/S 신부평임학#2T/L 전자변교체 및 조작시험","신부평S/S 신부평임학#2T/L 보통점검","2021-04-13 09:30","2021-04-13 18:00","2021-04-13 09:30","2021-04-13 18:00","연속"]
[130,"인천","직할","중동S/S S/T T/L CB (부천복합 S/T)","중동S/S S/T T/L 170kV GIS 하자점검","중동S/S S/T T/L 170kV GIS 하자점검","2021-04-05 09:30","2021-04-05 18:00","2021-04-05 09:30","2021-04-05 18:00","연속"]
[131,"인천","직할","중동S/S S/T T/L CB (부천복합 S/T)","중동S/S S/T T/L 170kV GIS 하자점검","중동S/S S/T T/L 170kV GIS 하자점검","2021-04-05 09:30","2021-04-05 18:00","취소","취소","연속"]
[132,"경기북부","고양","신덕은금촌#1 T/L","20-21년 가공송전 협력회사 총액공사","송전선로용 피뢰기 설치","2021-04-01 07:00","2021-04-02 18:00","2021-04-01 07:00","2021-04-02 18:00","연속"]
[133,"경기북부","고양","신파주원흥#2 T/L","20-21년 가공송전 협력회사 총액공사","송전선로용 피뢰기 설치(병가선로 휴전)","2021-04-01 07:00","2021-04-01 18:00","2021-04-01 07:00","2021-04-01 18:00","연속"]
[134,"경기북부","고양","고양일산#1 T/L","21-22년 지중송전설비 위탁정비공사","154kV 고양-일산#1T/L 고양C/H 피뢰기점검","2021-04-01 09:00","2021-04-02 18:00","2021-04-01 09:00","2021-04-02 18:00","연속"]
[135,"경기북부","구리","청평H/P CB 6400","영인제 154kV 모선보호반 성능개선","154kV 모선보호반(영인기술제) 펌웨어 업그레이드 시행","2021-04-01 11:00","2021-04-01 15:00","2021-04-01 11:00","2021-04-01 15:00","연속"]
[136,"경기북부","고양","신파주원흥#1 T/L","20-21년 가공송전 협력회사 총액공사","송전선로용 피뢰기 설치","2021-04-02 07:00","2021-04-02 18:00","2021-04-02 07:00","2021-04-02 18:00","연속"]
[137,"경기북부","고양","양주고양#2 T/L","고양시국도대체우회도로 지장이설공사(양주-고양)","철탑 3기 설치 및 2기 철거","2021-04-05 07:00","2021-04-12 18:00","2021-04-05 07:00","2021-04-12 18:00","연속"]
[138,"경기북부","직할","양주녹양#2 T/L","20-21년 가공송전 협력회사 총액공사","154kV 송전선로용 피뢰기 설치","2021-04-05 07:00","2021-04-16 18:00","2021-04-05 07:00","2021-04-16 18:00","연속"]
[139,"경기북부","직할","양주쌍문#1 T/L","20-21년 가공송전 협력회사 총액공사","송전선로용 피뢰기 설치(병가선로 휴전)","2021-04-05 07:00","2021-04-05 18:00","2021-04-05 07:00","2021-04-05 18:00","연속"]
[140,"경기북부","고양","고양일산#2 T/L","21-22년 지중송전설비 위탁정비공사","154kV 고양-일산#2T/L 고양C/H 피뢰기점검","2021-04-05 09:00","2021-04-06 18:00","2021-04-05 09:00","2021-04-06 18:00","연속"]
[141,"경기북부","구리","신포천포천#1 T/L","포천S/S 신포천-포천#1T/L CB 부싱 과열 보수","포천S/S 신포천-포천#1T/L CB 부싱 과열 보수","2021-04-05 09:00","2021-04-05 18:00","2021-04-05 09:00","2021-04-05 18:00","연속"]
[142,"경기북부","구리","신포천동두천#1 T/L","2020~2021년 경기북부직할 가공송전 정비회사 총액공사","154kV 송전용 피뢰기 설치 하단병가선로","2021-04-06 07:30","2021-04-06 18:00","2021-04-06 07:30","2021-04-06 18:00","연속"]
[143,"경기북부","구리","신포천포천#2 T/L","2020~2021년 경기북부직할 가공송전 정비회사 총액공사","154kV 송전용 피뢰기 설치","2021-04-06 07:30","2021-04-09 18:00","2021-04-06 07:30","2021-04-09 18:00","연속"]
[144,"경기북부","구리","미금구리#1 T/L","`20~21 구리전력 변전정비 총액공사","미금S/S 154kV 미금-구리#1T/L GIS 초기점검","2021-04-06 09:00","2021-04-06 18:00","2021-04-06 09:00","2021-04-06 18:00","연속"]
[145,"경기북부","구리","미금광장 T/L","'20~21년 구리전력 변전정비 총액공사","미금S/S 154kV 미금-광장T/L GIS 하자점검","2021-04-08 09:00","2021-04-08 18:00","2021-04-08 09:00","2021-04-08 18:00","연속"]
[146,"경기북부","구리","포천운천#2 T/L","2020~2021년 경기북부직할 가공송전 정비회사 총액공사","154kV 송전용 피뢰기 설치 하단병가선로","2021-04-09 07:30","2021-04-09 18:00","2021-04-09 07:30","2021-04-09 18:00","연속"]
[147,"경기북부","구리","팔당H/P CB 6133","팔당수력S/Y 장기사용 154kV GIS 대체공사","154kV GIS 4CCT 철거, 154kV GIS 5CCT, 154kV 모선보호반 1Set 설치","2021-04-12 07:00","2021-05-14 18:00","2021-04-12 07:00","2021-05-14 18:00","연속"]
[148,"경기북부","구리","팔당H/P 154kV #60 BUS CB","팔당수력S/Y 장기사용 154kV GIS 대체공사","154kV GIS 4CCT 철거, 154kV GIS 5CCT, 154kV 모선보호반 1Set 설치","2021-04-12 07:00","2021-05-14 18:00","2021-04-12 07:00","2021-05-14 18:00","연속"]
[149,"경기북부","직할","신의정부송우#2 T/L","2020~2021년 경기북부직할 가공송전 정비회사 총액공사","154kV 송전용 피뢰기 설치","2021-04-12 07:30","2021-04-16 18:00","2021-04-12 07:30","2021-04-16 18:00","연속"]
[150,"경기북부","구리","덕소팔당HP T/L","팔당수력S/Y 장기사용 154kV GIS 대체공사","154kV GIS 4CCT 철거, 154kV GIS 5CCT, 154kV 모선보호반 1Set 설치","2021-04-12 09:00","2021-05-14 18:00","2021-04-12 09:00","2021-05-14 18:00","연속"]
[151,"경기북부","직할","양주S/S SEC CB 60610","'20-21 변전정비 총액공사","170kV GIS 초기점검","2021-04-12 09:00","2021-04-12 14:00","2021-04-12 09:00","2021-04-12 14:00","연속"]
[152,"경기북부","직할","양주S/S SEC CB 61620","'20-21 변전정비 총액공사","170kV GIS 초기점검","2021-04-12 14:00","2021-04-12 18:00","2021-04-12 14:00","2021-04-12 18:00","연속"]
[153,"경기북부","고양","양주고양#1 T/L","고양시국도대체우회도로 지장이설공사(양주-고양)","철탑 3기 설치 및 2기 철거","2021-04-13 07:00","2021-04-20 18:00","2021-04-13 07:00","2021-04-20 18:00","연속"]
[154,"경기북부","구리","미금구리#2 T/L","`20~21 구리전력 변전정비 총액공사","미금S/S 154kV 미금-구리#2T/L GIS 초기점검","2021-04-13 09:00","2021-04-13 18:00","2021-04-13 09:00","2021-04-13 18:00","연속"]
[155,"경기북부","직할","양주S/S CB 6100","'20-21 변전정비 총액공사","170kV GIS 초기점검","2021-04-13 09:00","2021-04-13 14:00","2021-04-13 09:00","2021-04-13 14:00","연속"]
[156,"경기북부","직할","양주S/S CB 6200","'20-21 변전정비 총액공사","170kV GIS 초기점검","2021-04-13 14:00","2021-04-13 18:00","2021-04-13 14:00","2021-04-13 18:00","연속"]
[157,"경기북부","직할","양주S/S CB 6300","'20-21 변전정비 총액공사","170kV GIS 초기점검","2021-04-14 09:00","2021-04-14 18:00","2021-04-14 09:00","2021-04-14 18:00","연속"]
[158,"경기북부","고양","일산S/S SEC CB 60610","차단기 조작시험-변전총액공사","60-61,65-66 차단기 조작시험","2021-04-14 10:00","2021-04-14 12:00","2021-04-14 10:00","2021-04-14 12:00","연속"]
[159,"경기북부","고양","일산S/S SEC CB 65660","차단기 조작시험-변전총액공사","60-61,65-66 차단기 조작시험","2021-04-14 13:00","2021-04-14 15:00","2021-04-14 13:00","2021-04-14 15:00","연속"]
[160,"경기북부","직할","녹양백석#2 T/L","20-21년 가공송전 협력회사 총액공사","송전선로용 피뢰기 설치(병가선로 휴전)","2021-04-15 07:00","2021-04-16 18:00","2021-04-15 07:00","2021-04-16 18:00","연속"]
[161,"경기북부","구리","미금화양 T/L","'20~21년 구리전력 변전정비 총액공사","미금S/S 154kV 미금-화양T/L GIS 하자점검","2021-04-15 09:00","2021-04-15 18:00","2021-04-15 09:00","2021-04-15 18:00","연속"]
[162,"경기북부","직할","옥정송우#2 T/L","2020~2021년 경기북부직할 가공송전 정비회사 총액공사","154kV 송전용 피뢰기 설치 하단 병가선로","2021-04-16 07:30","2021-04-16 18:00","2021-04-16 07:30","2021-04-16 18:00","연속"]
[163,"경기북부","직할","양주녹양#1 T/L","2021년 가공송전 순시점검 위탁공사","송전설비 정밀점검 154kV 양주-녹양#1T/L No.0.01~54.99","2021-04-19 08:00","2021-04-27 18:00","2021-04-19 08:00","2021-04-27 18:00","연속"]
[164,"경기북부","직할","양주쌍문#2 T/L","2021년 가공송전 순시점검 위탁공사","송전설비 정밀점검 154kV 양주-쌍문#2T/L 안전이격거리 확보휴전","2021-04-19 08:00","2021-04-19 18:00","2021-04-19 08:00","2021-04-19 18:00","연속"]
[165,"경기북부","고양","원흥상암 T/L","154kV 원흥-상암T/L(향동) 접속함 해체점검","154kV 원흥-상암T/L(향동) J/B #1,2 접속함 해체점검","2021-04-19 09:00","2021-04-30 18:00","2021-04-19 09:00","2021-04-30 18:00","연속"]
[166,"경기북부","고양","지축현저#1 T/L","2021 고양P/O 변전정비회사 총액공사(지축-현저#1)","170kV GIS 하자점검","2021-04-19 09:30","2021-04-19 18:00","2021-04-19 09:30","2021-04-19 18:00","연속"]
[167,"경기북부","구리","별내진접 T/L","`20~21 구리전력 변전정비 총액공사","별내S/S 154kV 별내-진접T/L GIS 보통점검","2021-04-20 09:00","2021-04-20 18:00","2021-04-20 09:00","2021-04-20 18:00","연속"]
[168,"경기북부","고양","지축현저#2 T/L","2021 고양P/O 변전정비회사 총액공사(지축-현저#2)","170kV GIS 하자점검","2021-04-20 09:30","2021-04-20 18:00","2021-04-20 09:30","2021-04-20 18:00","연속"]
[169,"경기북부","구리","미금S/S SEC CB 60610","'20~21 구리전력 변전정비 총액공사","미금S/S 154kV #60-61 SEC GIS 조작시험","2021-04-22 09:00","2021-04-22 18:00","2021-04-22 09:00","2021-04-22 18:00","연속"]
[170,"경기북부","고양","양주금촌#2 T/L","2021년 금촌S/S 170kV GIS 교체공사","170kV GIS 교체공사(1차분, 양주금촌#2T/L)","2021-04-26 09:00","2021-05-12 13:00","2021-04-26 09:00","2021-05-12 13:00","연속"]
[171,"경기북부","직할","녹양백석#1 T/L","2021년 가공송전 순시점검 위탁공사","송전설비 정밀점검 154kV 녹양-백석#1T/L 안전이격거리 확보휴전","2021-04-27 08:00","2021-04-27 18:00","2021-04-27 08:00","2021-04-27 18:00","연속"]
[172,"경기","군포","남군포산본#1 T/L","남군포S/S 남군포-산본#1T/L GIS 하자점검","일진제 트립와이어 구조개선","2021-04-05 09:00","2021-04-05 14:00","2021-04-05 09:00","2021-04-05 14:00","연속"]
[173,"경기","군포","남군포산본#2 T/L","남군포S/S 남군포-산본#2T/L GIS 하자점검","일진제 트립와이어 구조개선","2021-04-05 14:00","2021-04-05 18:00","2021-04-05 14:00","2021-04-05 18:00","연속"]
[174,"경기","군포","마도사강#1 T/L","사강S/S 마도-사강#1T/L GIS 보통점검","사강S/S 마도-사강#1T/L GIS 보통점검","2021-04-08 09:00","2021-04-08 13:00","2021-04-08 09:00","2021-04-08 13:00","연속"]
[175,"경기","군포","마도사강#2 T/L","사강S/S 마도-사강#2T/L GIS 보통점검","사강S/S 마도-사강#2T/L GIS 보통점검","2021-04-08 13:00","2021-04-08 18:00","2021-04-08 13:00","2021-04-08 18:00","연속"]
[176,"경기","군포","산본안양#2 T/L","'20-21년도 송전정비회사 총액공사","성능저하국산 점퍼지지애자 교체 2련","2021-04-19 13:00","2021-04-19 18:00","2021-04-19 13:00","2021-04-19 18:00","연속"]
[177,"경기","군포","산본안양#1 T/L","'20-21년도 송전정비회사 총액공사","성능저하국산 점퍼지지애자 교체 3련","2021-04-19 08:00","2021-04-19 13:00","2021-04-19 08:00","2021-04-19 13:00","연속"]
[178,"경기","군포","산본안양#1 T/L","산본S/S 산본-안양#1T/L GIS 보통점검","산본S/S 산본-안양#1T/L GIS 보통점검","2021-04-01 09:00","2021-04-01 18:00","2021-04-01 09:00","2021-04-01 18:00","연속"]
[179,"경기","군포","서서울#2서안양 T/L","154kV 서서울2-서안양T/L 정밀점검(가공송전위탁공사)","154kV 서서울2-서안양T/L 정밀점검(가공송전위탁공사)","2021-04-07 09:00","2021-04-09 18:00","2021-04-07 09:00","2021-04-09 18:00","매일"]
[180,"경기","군포","서서울산본#2 T/L","2020-2021년도 송전정비회사 총액공사","서서울-산본#2T/L 송전용피뢰기 설치공사 (14기)","2021-04-12 09:00","2021-04-16 18:00","2021-04-12 09:00","2021-04-16 18:00","연속"]
[181,"경기","군포","서서울남군포#1 T/L","서서울S/S 서서울-남군포#1T/L GIS 하자점검","일진제 트립와이어 구조개선","2021-04-06 09:00","2021-04-06 14:00","2021-04-06 09:00","2021-04-06 14:00","연속"]
[182,"경기","군포","서서울남군포#2 T/L","서서울S/S 서서울-남군포#2T/L GIS 하자점검","일진제 트립와이어 구조개선","2021-04-06 14:00","2021-04-06 18:00","2021-04-06 14:00","2021-04-06 18:00","연속"]
[183,"경기","군포","서서울서수원#2 T/L","'20-21년도 송전정비회사 총액공사","성능저하국산 점퍼지지애자 교체 : 2련(2기)","2021-04-08 15:00","2021-04-08 19:00","2021-04-08 15:00","2021-04-08 19:00","연속"]
[184,"경기","군포","서서울#2일동#2 T/L","일동S/S 서서울2-일동#2T/L GIS 보통점검, 피뢰기 보통점검","서서울2-일동#2T/L GIS 보통점검, 피뢰기(A,B,C) 보통점검","2021-04-15 14:00","2021-04-15 18:00","2021-04-15 14:00","2021-04-15 18:00","연속"]
[185,"경기","군포","서서울#2일동#1 T/L","일동S/S 서서울2-일동#1T/L GIS 보통점검, 피뢰기 보통점검","서서울2-일동#1T/L GIS 보통점검, 피뢰기(A,B,C) 보통점검","2021-04-15 09:00","2021-04-15 14:00","2021-04-15 09:00","2021-04-15 14:00","연속"]
[186,"경기","군포","조암구문천#2 T/L","2020-2021년도 송전정비회사 총액공사","수촌-조암#2T/L 송전용 피뢰기 설치 관련 안전이격거리확보","2021-04-24 09:00","2021-04-25 18:00","2021-04-24 09:00","2021-04-25 18:00","매일"]
[187,"경기","동부","성현산성#3 T/L","21년 동부 변전정비회사 총액공사","산성:산성-성현#3T/L GIS(보통) 성현:산성-성현#3T/L GIS(조작)","2021-04-09 09:00","2021-04-09 18:00","2021-04-09 09:00","2021-04-09 18:00","연속"]
[188,"경기","동부","성현분당#2 T/L","154kV야탑-성현#2T/L 정밀점검(안전상 휴전)","154kV야탑-성현#2T/L 안전상 휴전","2021-04-05 09:00","2021-04-07 18:00","2021-04-05 09:00","2021-04-07 18:00","매일"]
[189,"경기","동부","곤지암초월#1 T/L","21년 동부 변전정비회사 총액공사","초월:곤지암-초월#1T/L(조작) 곤지암-초월#2T/L(조작)","2021-04-08 09:00","2021-04-08 14:00","2021-04-08 09:00","2021-04-08 14:00","연속"]
[190,"경기","동부","곤지암초월#2 T/L","21년 동부 변전정비회사 총액공사","초월:곤지암-초월#1T/L(조작) 곤지암-초월#2T/L(조작)","2021-04-08 14:00","2021-04-08 18:00","2021-04-08 14:00","2021-04-08 18:00","연속"]
[191,"경기","성남","남사동탄#2 T/L","2021년 성남전력 변전정비회사 총액공사","170kV GIS 보통점검","2021-04-02 09:00","2021-04-02 18:00","2021-04-02 09:00","2021-04-02 18:00","연속"]
[192,"경기","성남","남사동탄#1 T/L","2021년 성남전력 변전정비회사 총액공사","170kV GIS 하자점검","2021-04-01 09:00","2021-04-01 18:00","2021-04-01 09:00","2021-04-01 18:00","연속"]
[193,"경기","성남","진위동탄#1 T/L","2021년 성남전력 변전정비회사 총액공사","GIS 하자점검","2021-04-20 09:00","2021-04-20 18:00","2021-04-20 09:00","2021-04-20 18:00","연속"]
[194,"경기","성남","진위동탄#2 T/L","2021년 성남전력 변전정비회사 총액공사","GIS 하자점검","2021-04-21 09:00","2021-04-21 18:00","2021-04-21 09:00","2021-04-21 18:00","연속"]
[195,"경기","성남","기흥신갈#1 T/L","2021년 성남전력 변전정비회사 총액공사","GIS 초기점검","2021-04-29 09:00","2021-04-29 18:00","2021-04-29 09:00","2021-04-29 18:00","연속"]
[196,"경기","직할","조암구문천#2 T/L","20-21년 경기직할 변전정비회사 총액공사","구문천S/S GIS 보통점검 및 가스배관 누기보수 ES인터록 및 사활경보 확인","2021-04-19 09:00","2021-04-19 18:00","2021-04-19 09:00","2021-04-19 18:00","연속"]
[197,"경기","직할","의왕동안양#1 T/L","20-21년 경기직할 변전정비회사 총액공사","동안양S/S 의왕-동안양#1T/L CB 보통점검, GIS 하자점검, LA 보통점검","2021-04-02 09:00","2021-04-02 18:00","2021-04-02 09:00","2021-04-02 18:00","연속"]
[198,"경기","직할","관양동안양#1 T/L","20-21년 경기직할 변전정비회사 총액공사","동안양S/S 관양-동안양#1T/L GIS 누기개소 파악, 상호인터록 시험","2021-04-08 09:00","2021-04-09 18:00","2021-04-08 09:00","2021-04-09 18:00","연속"]
[199,"경기","직할","서수원율전#1 T/L","'20-21년도 송전정비회사 총액공사","성능저하국산 점퍼지지애자 교체 관련 안전이격거리확보","2021-04-08 15:00","2021-04-08 19:00","2021-04-08 15:00","2021-04-08 19:00","연속"]
[200,"경기","직할","서수원율전#1 T/L","20-21년 경기직할 변전정비회사 총액공사","서수원S/S 서수원-율전#1T/L GIS 조작시험, 43LR 경보수용, 인터록시험","2021-04-07 09:00","2021-04-07 14:00","2021-04-07 09:00","2021-04-07 14:00","연속"]
[201,"경기","직할","서수원율전#2 T/L","20-21년 경기직할 변전정비회사 총액공사","서수원S/S 서수원-율전#1T/L GIS 조작시험, 43LR 경보수용, 인터록시험","2021-04-07 14:00","2021-04-07 18:00","2021-04-07 14:00","2021-04-07 18:00","연속"]
[202,"경기","직할","수촌조암#2 T/L","2020-2021년도 송전정비회사 총액공사","154kV 수촌-조암#2T/L 피뢰기 설치공사(15기)","2021-04-24 09:00","2021-04-28 18:00","2021-04-24 09:00","2021-04-28 18:00","연속"]
[203,"경기","직할","서서울율전#2 T/L","20-21년 변전정비회사 총액공사","율전S/S 서서울-율전#2T/L GIS 보통점검","2021-04-30 09:00","2021-04-30 18:00","2021-04-30 09:00","2021-04-30 18:00","연속"]
[204,"경기","직할","서서울율전#1 T/L","20-21년 변전정비회사 총액공사","율전S/S 서서울-율전#1T/L GIS 보통점검","2021-04-29 09:00","2021-04-29 18:00","2021-04-29 09:00","2021-04-29 18:00","연속"]
[205,"경기","직할","율전의왕#1 T/L","154kV 율전-의왕T/L 정밀점검(가공송전 위탁공사)","154kV 율전-의왕#1T/L 정밀점검(가공송전 위탁공사)","2021-04-20 09:00","2021-04-21 18:00","2021-04-20 09:00","2021-04-21 18:00","매일"]
[206,"경기","직할","율전의왕#2 T/L","154kV 율전-의왕T/L 정밀점검(가공송전 위탁공사)","154kV 율전-의왕#2T/L 정밀점검(가공송전 위탁공사)","2021-04-22 09:00","2021-04-23 18:00","2021-04-22 09:00","2021-04-23 18:00","매일"]
[207,"경기","직할","화성남양#1 T/L","2021년 경기직할 154kV GIS 정밀점검공사","2021년 경기직할 154kV GIS 정밀점검공사","2021-04-30 09:00","2021-05-02 18:00","2021-04-30 09:00","2021-05-02 18:00","연속"]
[208,"경기","직할","화성마도 T/L","20-21년 경기직할 변전정비회사 총액공사","화성S/S 화성-마도T/L GIS 조작시험","2021-04-17 14:00","2021-04-17 18:00","2021-04-17 14:00","2021-04-17 18:00","연속"]
[209,"경기","직할","화성장덕 T/L","20-21년 경기직할 변전정비회사 총액공사","화성S/S 화성-장덕T/L GIS 조작시험","2021-04-17 09:00","2021-04-17 14:00","2021-04-17 09:00","2021-04-17 14:00","연속"]
[210,"경기","평택","서운광혜원 T/L","서울-세종간 도로개설 관련 지장이설공사","154kV 서운-안성T/L 34, 35, 47호 임시 3기, 철거 4기","2021-04-17 07:00","2021-04-26 18:00","2021-04-17 07:00","2021-04-26 18:00","연속"]
[211,"경기","평택","서운안성#1 T/L","서울-세종간 도로개설 관련 지장이설공사","154kV 서운-안성T/L 34, 35, 47호 임시 3기, 철거 4기","2021-04-17 07:00","2021-04-26 18:00","2021-04-17 07:00","2021-04-26 18:00","연속"]
[212,"경기","평택","서운삼죽 T/L","서울-세종간 도로개설 관련 지장이설공사","154kV 서운-안성T/L 34, 35, 47호 임시 3기, 철거 4기","2021-04-07 07:00","2021-04-16 18:00","2021-04-07 07:00","2021-04-16 18:00","연속"]
[213,"경기","평택","서운안성#2 T/L","서울-세종간 도로개설 관련 지장이설공사","154kV 서운-안성T/L 34, 35, 47호 임시 3기, 철거 4기","2021-04-07 07:00","2021-04-16 18:00","2021-04-07 07:00","2021-04-16 18:00","연속"]
[214,"경기","평택","송탄소사벌 T/L","소사벌S/S 154kV 송탄-소사벌 T/L GIS 정밀점검","소사벌S/S 154kV 송탄-소사벌 T/L GIS 정밀점검","2021-04-12 10:00","2021-04-14 18:00","2021-04-12 10:00","2021-04-14 18:00","연속"]
[215,"경기","평택","오성C/C CB 6433","오성C/C 154kV #S/T 1차 GIS 정밀점검","오성C/C 154kV #S/T 1차 GIS 정밀점검","2021-04-26 10:00","2021-04-28 18:00","2021-04-26 10:00","2021-04-28 18:00","연속"]
[216,"경기","평택","평택오성CC#1 T/L","154kV 평택-오성CC 등 2개T/L 지중화공사","C/H 3호, 7호 피뢰기 설치 -2~3호 간 항공장애표시구 및 2호 항공등 정비","2021-04-06 08:00","2021-04-06 18:00","2021-04-06 08:00","2021-04-06 18:00","연속"]
[217,"경기","평택","오성C/C CB 6133","오성C/C 154kV #1 G/T 1차 GIS 정밀점검","오성C/C 154kV #1 G/T 1차 GIS 정밀점검","2021-04-19 10:00","2021-04-21 18:00","2021-04-19 10:00","2021-04-21 18:00","연속"]
[218,"경기","평택","오성C/C CB 6333","오성C/C 154kV #3 G/T 1차 GIS 정밀점검","오성C/C 154kV #3 G/T 1차 GIS 정밀점검","2021-04-22 10:00","2021-04-24 18:00","2021-04-22 10:00","2021-04-24 18:00","연속"]
[219,"경기","평택","송탄오성CC#2 T/L","154kV 평택-오성CC 등 2개T/L 지중화공사","C/H 3호, 7호 피뢰기 설치 -2~3호 간 항공장애표시구 및 2호 항공등 정비","2021-04-06 08:00","2021-04-06 18:00","2021-04-06 08:00","2021-04-06 18:00","연속"]
[220,"경기","평택","평택오성CC#2 T/L","154kV 평택-오성CC 등 2개T/L 지중화공사","C/H 3호, 7호 피뢰기 설치 -2~3호 간 항공장애표시구 및 2호 항공등 정비","2021-04-07 08:00","2021-04-07 18:00","2021-04-07 08:00","2021-04-07 18:00","연속"]
[221,"경기","평택","송탄오성CC#1 T/L","154kV 평택-오성CC 등 2개T/L 지중화공사","C/H 3호, 7호 피뢰기 설치 -2~3호 간 항공장애표시구 및 2호 항공등 정비","2021-04-07 08:00","2021-04-07 18:00","2021-04-07 08:00","2021-04-07 18:00","연속"]
[222,"경기","평택","고덕진위#2 T/L","진위S/S 고덕-진위#2 T/L GIS 정밀점검","진위S/S 고덕-진위#2 T/L GIS 정밀점검","2021-04-08 10:00","2021-04-10 18:00","2021-04-08 10:00","2021-04-10 18:00","연속"]
[223,"경기","평택","포승평택TP#1 T/L","포승-평택T/P #1T/L GIS 점검","평택T/P 포승-평택T/P #1T/L GIS(보통점검) 포승S/S 포승-평택T/P #1T/L GIS(조작시험)","2021-04-15 10:00","2021-04-15 18:00","2021-04-15 10:00","2021-04-15 18:00","연속"]
[224,"경기","평택","포승평택TP#2 T/L","포승-평택T/P #2T/L GIS 점검","평택T/P 포승-평택T/P #2T/L GIS(보통점검) 포승S/S 포승-평택T/P #2T/L GIS(조작시험)","2021-04-16 10:00","2021-04-16 18:00","2021-04-16 10:00","2021-04-16 18:00","연속"]
[225,"경기","평택","포승청북 T/L","포승S/S 포승-청북T/L 조작시험","포승S/S 포승-청북T/L 조작시험 청북S/S 포승-청북T/L 유압력계 교체","2021-04-30 10:00","2021-04-30 18:00","2021-04-30 10:00","2021-04-30 18:00","연속"]
[226,"강원","강릉","동해강릉 T/L","154kV 강릉 등 8개 T/L 피뢰기 설치 공사","피뢰기 설치공사 154kV 강릉T/L No.8-1 ~ 53","2021-04-15 09:00","2021-04-30 18:00","2021-04-15 09:00","2021-04-30 18:00","매일"]
[227,"강원","동해","동해동영월 T/L","154kV 동해-정선간 OPGW 교체공사","OPGW(OP-S-L48) 52.772km 교체시설","2021-04-26 08:00","2021-06-09 18:00","2021-04-26 08:00","2021-06-09 18:00","연속"]
[228,"강원","동해","동해정선 T/L","2020~21년 동해전력지사 송전정비회사 총액공사","154kV 동해-정선T/L No.193~198 전선교체  및 스페이서 및 SB 댐퍼 교체","2021-04-19 08:00","2021-04-23 18:00","2021-04-19 08:00","2021-04-23 18:00","연속"]
[229,"강원","동해","동해이원#2 T/L","2020~21년 동해전력지사 송전정비회사 총액공사","154kV 동해-이원#2T/L 송전선로용 피뢰기 설치 (23기)","2021-04-12 08:00","2021-04-14 18:00","2021-04-12 08:00","2021-04-14 18:00","매일"]
[230,"강원","동해","동해북평#1 T/L","2021년 동해전력지사 변전정비 총액공사","GIS 보통점검","2021-04-21 09:00","2021-04-21 18:00","2021-04-21 09:00","2021-04-21 18:00","연속"]
[231,"강원","동해","동해북평#2 T/L","2021년 동해전력지사 변전정비 총액공사","GIS 보통점검","2021-04-22 09:00","2021-04-22 18:00","2021-04-22 09:00","2021-04-22 18:00","연속"]
[232,"강원","동해","삼척G/P 154kV #62 BUS CB","동해전력지사 2021년 170kV GIS 정밀점검","GIS 정밀점검, 가스 누기 관련 스페이서 점검","2021-04-05 09:00","2021-04-08 13:00","취소","취소","연속"]
[233,"강원","동해","삼척G/P CB 6B7","동해전력지사 2021년 170kV GIS 정밀점검","GIS 정밀점검, 가스 누기 관련 스페이서 점검","2021-04-05 09:00","2021-04-11 18:00","취소","취소","연속"]
[234,"강원","동해","삼척G/P 154kV #66 BUS CB","동해전력지사 2021년 170kV GIS 정밀점검","GIS 정밀점검, 가스 누기 관련 스페이서 점검","2021-04-01 13:00","2021-04-03 18:00","취소","취소","연속"]
[235,"강원","동해","삼척G/P 154kV #62 BUS CB","동해전력지사 2021년 170kV GIS 정밀점검","GIS 정밀점검, 가스 누기 관련 스페이서 점검","2021-04-12 09:00","2021-04-15 13:00","취소","취소","연속"]
[236,"강원","동해","삼척G/P 154kV #67 BUS CB","동해전력지사 2021년 170kV GIS 정밀점검","GIS 정밀점검, 가스 누기 관련 스페이서 점검","2021-04-08 13:00","2021-04-10 18:00","취소","취소","연속"]
[237,"강원","동해","삼척G/P 154kV #67 BUS CB","동해전력지사 2021년 170kV GIS 정밀점검","GIS 정밀점검, 가스 누기 관련 스페이서 점검","2021-04-26 09:00","2021-04-30 18:00","취소","취소","연속"]
[238,"강원","동해","태백삼척GP#2 T/L","동해전력지사 2021년 170kV GIS 정밀점검","GIS 정밀점검, 가스 누기 관련 스페이서 점검","2021-04-12 09:00","2021-04-18 18:00","취소","취소","연속"]
[239,"강원","동해","삼척G/P 154kV #67 BUS CB","동해전력지사 2021년 170kV GIS 정밀점검","GIS 정밀점검, 가스 누기 관련 스페이서 점검","2021-04-15 13:00","2021-04-17 18:00","취소","취소","연속"]
[240,"강원","동해","삼척G/P 154kV #62 BUS CB","동해전력지사 2021년 170kV GIS 정밀점검","GIS 정밀점검, 가스 누기 관련 스페이서 점검","2021-04-19 09:00","2021-04-22 13:00","취소","취소","연속"]
[241,"강원","동해","삼척G/P 154kV #67 BUS CB","동해전력지사 2021년 170kV GIS 정밀점검","GIS 정밀점검, 가스 누기 관련 스페이서 점검","2021-04-22 13:00","2021-04-24 18:00","취소","취소","연속"]
[242,"강원","동해","울진삼척GP#2 T/L","동해전력지사 2021년 170kV GIS 정밀점검","GIS 정밀점검, 가스 누기 관련 스페이서 점검","2021-04-26 09:00","2021-04-30 18:00","2021-04-26 09:00","2021-04-30 18:00","연속"]
[243,"강원","동해","삼척동해TP T/L","2020~21년 동해전력지사 송전정비회사 총액공사","154kV 삼척-동해TPT/L 아킹혼 설치 (22기)","2021-04-09 09:00","2021-04-10 18:00","2021-04-09 09:00","2021-04-10 18:00","매일"]
[244,"강원","동해","이원삼척 T/L","2020~21년 동해전력지사 송전정비회사 총액공사","154kV 이원-삼척T/L 아킹혼 설치 No.1~삼척S/T (35기)","2021-04-05 08:00","2021-04-08 18:00","2021-04-05 08:00","2021-04-08 18:00","매일"]
[245,"강원","원주","주진둔내#2 T/L","2020~2021년 송전정비회사 총액공사(원주)","관형지지물 보강(No.75)","2021-04-10 09:00","2021-04-13 18:00","취소","취소","연속"]
[246,"강원","원주","주진둔내#1 T/L","2020~2021년 송전정비회사 총액공사(원주)","관형지지물 보강(No.75)","2021-04-10 09:00","2021-04-13 18:00","취소","취소","연속"]
[247,"강원","원주","남원주원주#1 T/L","2020~2021년 송전정비회사 총액공사(원주)","애자련 보강(원주S/S 인출)","2021-04-01 08:00","2021-04-01 18:00","2021-04-01 08:00","2021-04-01 18:00","연속"]
[248,"강원","원주","남원주원주#2 T/L","2020~2021년 송전정비회사 총액공사(원주)","애자련 보강(원주S/S 인출)","2021-04-02 08:00","2021-04-02 18:00","2021-04-02 08:00","2021-04-02 18:00","연속"]
[249,"강원","원주","원주서원주#1 T/L","2021년 원주전력지사 변전정비 총액공사","2021년 원주전력지사 변전정비 총액공사","2021-04-05 10:00","2021-04-05 18:00","취소","취소","연속"]
[250,"강원","원주","원주서원주#2 T/L","170kV GIS 인출측 정밀점검","170kV GIS 인출측 정밀점검","2021-04-01 10:00","2021-04-02 18:00","취소","취소","연속"]
[251,"강원","원주","둔내횡성#1 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","170kV 장기사용 GIS 철거/설치 ㅇ SA 운영장치 시험","2021-04-27 08:00","2021-05-08 18:00","2021-04-27 08:00","2021-05-08 18:00","연속"]
[252,"강원","원주","둔내횡성#2 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","170kV GIS 무부하 가압 시험","2021-04-14 14:00","2021-04-15 18:00","2021-04-14 14:00","2021-04-15 18:00","연속"]
[253,"강원","원주","둔내횡성#2 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","170kV GIS 무부하 가압 시험","2021-04-22 14:00","2021-04-23 18:00","2021-04-22 14:00","2021-04-23 18:00","연속"]
[254,"강원","원주","둔내횡성#2 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","170kV GIS 무부하 가압 시험","2021-04-08 14:00","2021-04-09 18:00","2021-04-08 14:00","2021-04-09 18:00","연속"]
[255,"강원","원주","횡성S/S 154kV #1 BUS","횡성S/S 170kV GIS 장기사용 GIS 대체공사","170kV 장기사용 GIS 철거/설치, SA 운영장치 시험","2021-04-27 08:00","2021-05-01 18:00","2021-04-27 08:00","2021-05-01 18:00","연속"]
[256,"강원","원주","횡성S/S 154kV #1 BUS","횡성S/S 170kV GIS 장기사용 GIS 대체공사","170kV 장기사용 GIS 철거/설치, SA 운영장치 시험","2021-04-22 14:00","2021-04-23 18:00","2021-04-22 14:00","2021-04-23 18:00","연속"]
[257,"강원","원주","횡성S/S 154kV #1 BUS","횡성S/S 170kV GIS 장기사용 GIS 대체공사","170kV 장기사용 GIS 철거/설치, SA 운영장치 시험","2021-04-15 08:00","2021-04-20 18:00","2021-04-15 08:00","2021-04-20 18:00","연속"]
[258,"강원","원주","횡성S/S 154kV #2 BUS","횡성S/S 170kV GIS 장기사용 GIS 대체공사","170kV 장기사용 GIS 철거/설치, SA 운영장치 시험","2021-04-12 14:00","2021-04-15 14:00","2021-04-12 14:00","2021-04-15 14:00","연속"]
[259,"강원","원주","횡성S/S 154kV #1 BUS","횡성S/S 170kV GIS 장기사용 GIS 대체공사","170kV 장기사용 GIS 철거/설치, SA 운영장치 시험","2021-04-05 08:00","2021-04-12 14:00","2021-04-05 08:00","2021-04-12 14:00","연속"]
[260,"강원","원주","북원주횡성#2 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","170kV 장기사용 GIS 철거/설치, SA 운영장치 시험","2021-04-27 08:00","2021-05-09 18:00","2021-04-27 08:00","2021-05-09 18:00","연속"]
[261,"강원","원주","북원주횡성#1 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","북원주-횡성#2T/L 월부싱 철거 안전이격확보","2021-04-28 08:00","2021-04-29 18:00","2021-04-28 08:00","2021-04-29 18:00","연속"]
[262,"강원","원주","북원주횡성#1 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","170kV 장기사용 GIS 철거/설치, SA 운영장치 시험","2021-04-05 08:00","2021-04-22 18:00","2021-04-05 08:00","2021-04-22 18:00","연속"]
[263,"강원","원주","북원주횡성#2 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","북원주-횡성#1T/L 월부싱철거/설치 안전이격 확보","2021-04-06 08:00","2021-04-07 18:00","2021-04-06 08:00","2021-04-07 18:00","연속"]
[264,"강원","원주","북원주횡성#2 T/L","횡성S/S 170kV GIS 장기사용 GIS 대체공사","북원주-횡성#1T/L 월부싱철거/설치 안전이격 확보","2021-04-19 08:00","2021-04-20 18:00","2021-04-19 08:00","2021-04-20 18:00","연속"]
[265,"강원","직할","북춘천화천HP T/L","'21년 강원본부 직할 154kV GIS 정밀점검공사","북춘천S/S 154kV 북춘천-화천HP T/L GIS 정밀점검공사","2021-04-19 09:00","2021-04-21 18:00","2021-04-24 09:00","2021-04-26 13:00","연속"]
[266,"강원","직할","북춘천춘천HP T/L","'21년 강원본부 직할 154kV GIS 정밀점검공사","북춘천S/S 154kV 북춘천-춘천HP T/L GIS 정밀점검공사","2021-04-15 09:00","2021-04-17 18:00","2021-04-21 09:00","2021-04-23 13:00","연속"]
[267,"강원","직할","춘천북춘천#2 T/L","'21년 강원본부 직할 154kV GIS 정밀점검공사","북춘천S/S 154kV 춘천-북춘천 #2 T/L GIS 정밀점검공사","2021-04-12 09:00","2021-04-14 18:00","2021-04-18 13:00","2021-04-20 18:00","연속"]
[268,"강원","직할","춘천북춘천#1 T/L","'21년 강원본부 직할 154kV GIS 정밀점검공사","북춘천S/S 154kV 춘천-북춘천 #1 T/L GIS 정밀점검공사","2021-04-08 09:00","2021-04-10 18:00","2021-04-15 09:00","2021-04-17 13:00","연속"]
[269,"강원","직할","철원화천#2 T/L","154kV 화천S/S 외장재 교체공사","노후 외장재 철거, 외장재 설치, 도장공사 : 고탄성아크릴도장","2021-04-09 08:00","2021-04-14 18:00","2021-04-09 08:00","2021-04-14 18:00","연속"]
[270,"강원","직할","철원화천#1 T/L","154kV 화천S/S 외장재 교체공사","노후 외장재 철거, 외장재 설치, 도장공사 : 고탄성아크릴도장","2021-04-05 08:00","2021-04-10 18:00","2021-04-05 08:00","2021-04-10 18:00","연속"]
[271,"강원","태백","태백고한 T/L","20~21년 변전정비회사 총액공사","고한S/S : 태백-고한T/L GIS 정밀점검","2021-04-26 10:00","2021-04-28 18:00","2021-04-26 10:00","2021-04-28 18:00","연속"]
[272,"강원","태백","고한영월 T/L","20~21년 변전정비회사 총액공사","고한-영월T/L GIS 정밀점검","2021-04-19 10:00","2021-04-21 18:00","2021-04-19 10:00","2021-04-21 18:00","연속"]
[273,"강원","태백","신제천영월CC#2 T/L","20~21년 변전정비회사 총액공사","신제천-영월CC #2T/L GIS 조작시험","2021-04-02 14:00","2021-04-02 18:00","2021-04-02 14:00","2021-04-02 18:00","연속"]
[274,"강원","태백","신제천영월CC#1 T/L","20~21년 변전정비회사 총액공사","신제천-영월CC #1T/L GIS 조작시험","2021-04-02 10:00","2021-04-02 14:00","2021-04-02 10:00","2021-04-02 14:00","연속"]
[275,"강원","태백","단양영월CC#2 T/L","20~21년 변전정비회사 총액공사","단양-영월CC #2T/L GIS 조작시험","2021-04-01 14:00","2021-04-01 18:00","2021-04-01 14:00","2021-04-01 18:00","연속"]
[276,"강원","태백","영월C/C CB 6100G","20~21년 변전정비회사 총액공사","#60-65 BUS TIE GIS 조작시험","2021-04-05 14:00","2021-04-05 18:00","2021-04-05 14:00","2021-04-05 18:00","연속"]
[277,"강원","태백","단양영월CC#1 T/L","20~21년 변전정비회사 총액공사","단양-영월CC #1GIS 조작시험","2021-04-01 10:00","2021-04-01 14:00","2021-04-01 10:00","2021-04-01 14:00","연속"]
[278,"강원","태백","제천영월#2 T/L","20~21년 변전정비회사 총액공사","제천-영월 #2T/L GIS 조작시험","2021-04-15 14:00","2021-04-15 18:00","2021-04-15 14:00","2021-04-15 18:00","연속"]
[279,"강원","태백","제천영월#1 T/L","20~21년 변전정비회사 총액공사","제천-영월 #1T/L GIS 조작시험","2021-04-15 10:00","2021-04-15 14:00","2021-04-15 10:00","2021-04-15 14:00","연속"]
[280,"강원","태백","영월S/S CB 6100","20~21년 변전정비회사 총액공사","#60-65 BUS TIE GIS 조작시험","2021-04-09 14:00","2021-04-09 18:00","2021-04-09 14:00","2021-04-09 18:00","연속"]
[281,"강원","태백","영월_영월CC T/L","20~21년 변전정비회사 총액공사","영월-영월CC T/L GIS 보통점검","2021-04-07 10:00","2021-04-08 18:00","2021-04-07 10:00","2021-04-08 18:00","매일"]
[282,"강원","태백","도계태백 T/L","20~21년 변전정비회사 총액공사","도계-태백 T/L GIS 조작시험","2021-04-29 14:00","2021-04-29 18:00","2021-04-29 14:00","2021-04-29 18:00","연속"]
[283,"강원","태백","이원태백 T/L","20~21년 변전정비회사 총액공사","이원-태백 T/L GIS 조작시험","2021-04-29 10:00","2021-04-29 14:00","2021-04-29 10:00","2021-04-29 14:00","연속"]
[284,"강원","태백","태백영월 T/L","20~21년 변전정비회사 총액공사","태백-영월 #1T/L GIS 조작시험","2021-04-12 10:00","2021-04-12 18:00","2021-04-12 10:00","2021-04-12 18:00","연속"]
[285,"강원","태백","태백삼척GP#1 T/L","20~21년 변전정비회사 총액공사","태백-삼척GP #1T/L GIS 조작시험","2021-04-06 10:00","2021-04-06 14:00","2021-04-06 10:00","2021-04-06 14:00","연속"]
[286,"강원","태백","태백삼척GP#2 T/L"," 20~21년 태백전력지사 송전정비회사 총액공사","울진-삼척GP#1 송전용 피뢰기 설치시 작업자 안전이격 확보","2021-04-01 10:00","2021-04-02 14:00","취소","취소","매일"]
[287,"충북","직할","남음성덕산#1 T/L","2021년 직할 가공송전선로 순시점검 위탁공사","154kV 남음성-덕산#1T/L 정밀점검","2021-04-19 09:00","2021-04-23 18:00","2021-04-19 09:00","2021-04-23 18:00","매일"]
[288,"충북","직할","남음성덕산#2 T/L","2021년 직할 가공송전선로 순시점검 위탁공사","154kV 남음성-덕산#2T/L 정밀점검","2021-04-26 09:00","2021-04-30 18:00","2021-04-26 09:00","2021-04-30 18:00","매일"]
[289,"충북","직할","진천덕산#2 T/L","2021년 직할 가공송전선로 순시점검 위탁공사","154kV 진천-덕산#2T/L 정밀점검","2021-04-12 09:00","2021-04-16 18:00","2021-04-12 09:00","2021-04-16 18:00","매일"]
[290,"충북","직할","진천덕산#1 T/L","2021년 직할 가공송전선로 순시점검 위탁공사","154kV 진천-덕산#1T/L 정밀점검","2021-04-05 09:00","2021-04-09 18:00","2021-04-05 09:00","2021-04-09 18:00","매일"]
[291,"충북","청주","오창국사#2 T/L","21년도 청주전력 170kV GIS 정밀점검공사","국사S/S 154kV 오창-국사#2T/L GIS 정밀점검","2021-04-03 09:00","2021-04-04 18:00","2021-04-03 09:00","2021-04-04 18:00","연속"]
[292,"충북","청주","남청주오송#1 T/L","154kV 신옥천-옥천 등 5개 T/L 송전피뢰기 설치공사","154kV 신옥천-옥천 등 5개 T/L 801set 송전피뢰기 설치공사","2021-04-24 08:00","2021-04-24 18:00","2021-04-24 08:00","2021-04-24 18:00","매일"]
[293,"충북","청주","남청주오송#1 T/L","154kV 신옥천-옥천 등 5개 T/L 송전피뢰기 설치공사","154kV 신옥천-옥천 등 5개 T/L 801set 송전피뢰기 설치공사","2021-04-17 08:00","2021-04-18 18:00","2021-04-17 08:00","2021-04-18 18:00","매일"]
[294,"충북","청주","남청주오송#1 T/L","154kV 신옥천-옥천 등 5개 T/L 송전피뢰기 설치공사","154kV 신옥천-옥천 등 5개 T/L 801set 송전피뢰기 설치공사","2021-04-10 08:00","2021-04-11 18:00","2021-04-10 08:00","2021-04-11 18:00","매일"]
[295,"충북","청주","상주보은 T/L","154kV 상주T/L No.93-1 안전이격 확보공사","154kV 상주T/L No.93-1 기설설탑 철거 및 신설철탑 건설\n지상고 부족에 따른 안전이격 확보공사 시행(F2-17m -> Ba2-28m)","2021-04-10 07:00","2021-04-11 18:00","2021-04-10 07:00","2021-04-11 18:00","매일"]
[296,"충북","청주","상주보은 T/L","154kV 상주T/L No.93-1 안전이격 확보공사","154kV 상주T/L No.93-1 기설설탑 철거 및 신설철탑 건설\n지상고 부족에 따른 안전이격 확보공사 시행(F2-17m -> Ba2-28m)","2021-04-01 07:00","2021-04-01 18:00","2021-04-01 07:00","2021-04-01 18:00","연속"]
[297,"충북","청주","국사봉명#1 T/L","20-21년 청주전력 변전정비 총액","170kV GIS 보통점검","2021-04-29 10:00","2021-04-29 18:00","2021-04-29 10:00","2021-04-29 18:00","연속"]
[298,"충북","청주","국사봉명#2 T/L","20-21년 청주전력 변전정비 총액","170kV GIS 보통점검","2021-04-30 10:00","2021-04-30 18:00","2021-04-30 10:00","2021-04-30 18:00","연속"]
[299,"충북","청주","북오송전의#1 T/L","154kV 북오송분기T/L 추락방지시설 설치공사","추락방지시설 19기 설치","2021-04-15 08:00","2021-04-17 18:00","2021-04-15 08:00","2021-04-17 18:00","매일"]
[300,"충북","청주","북오송전의#2 T/L","154kV 북오송분기T/L 추락방지시설 설치공사","추락방지시설 19기 설치","2021-04-12 08:00","2021-04-14 18:00","2021-04-12 08:00","2021-04-14 18:00","매일"]
[301,"충북","청주","동천안북오송#1 T/L","154kV 북오송분기T/L 추락방지시설 설치공사","추락방지시설 19기 설치","2021-04-12 08:00","2021-04-14 18:00","2021-04-12 08:00","2021-04-14 18:00","매일"]
[302,"충북","청주","동천안북오송#2 T/L","154kV 북오송분기T/L 추락방지시설 설치공사","추락방지시설 19기 설치","2021-04-15 08:00","2021-04-17 18:00","2021-04-15 08:00","2021-04-17 18:00","매일"]
[303,"충북","청주","상주영동 T/L","154kV 상주T/L No.93-1 안전이격 확보공사","154kV 상주T/L No.93-1 기설설탑 철거 및 신설철탑 건설\n지상고 부족에 따른 안전이격 확보공사 시행(F2-17m -> Ba2-28m)","2021-04-02 07:00","2021-04-04 18:00","2021-04-02 07:00","2021-04-04 18:00","매일"]
[304,"충북","청주","오송북청주#2 T/L","154kV 신옥천-옥천 등 5개 T/L 송전피뢰기 설치공사","154kV 신옥천-옥천 등 5개 T/L 801set 송전피뢰기 설치공사","2021-04-10 08:00","2021-04-11 18:00","2021-04-10 08:00","2021-04-11 18:00","연속"]
[305,"충북","청주","남청주오송#2 T/L","21년도 청주전력 170kV GIS 정밀점검공사","오송S/S 154kV 남청주-오송#2T/L GIS 정밀점검","2021-04-10 09:00","2021-04-12 18:00","취소","취소","연속"]
[306,"충북","청주","오창국사#1 T/L","20-21년 청주전력 변전정비 총액","170kV GIS 보통점검","2021-04-16 10:00","2021-04-16 18:00","취소","취소","연속"]
[307,"충북","청주","옥천보은 T/L","154kV 상주T/L 정밀점검","2021 가공송전 순시점검 위탁공사 154kV 상주T/L No.1~110 정밀점검","2021-04-12 08:30","2021-04-15 18:00","취소","취소","매일"]
[308,"충북","청주","옥천영동 T/L","154kV 상주T/L 정밀점검","2021 가공송전 순시점검 위탁공사 154kV 상주T/L No.1~110 정밀점검","2021-04-18 08:30","2021-04-21 18:00","취소","취소","매일"]
[309,"충북","충주","금왕남음성#2 T/L","20-21년 충주전력지사 변전정비 총액공사","남음성S/S 금왕-남음성#2T/L 차단기 조작시험, LA 점검","2021-04-20 10:00","2021-04-20 18:00","취소","취소","연속"]
[310,"충북","충주","신제천왕암#1 T/L","20-21년 충주전력지사 변전정비 총액공사","남음성S/S 금왕-남음성#2T/L 차단기 조작시험, LA 점검","2021-04-01 10:00","2021-04-01 18:00","2021-04-01 10:00","2021-04-01 18:00","연속"]
[311,"충북","충주","신제천왕암#2 T/L","20-21년 충주전력지사 변전정비 총액공사","남음성S/S 금왕-남음성#2T/L 차단기 조작시험, LA 점검","2021-04-02 10:00","2021-04-02 18:00","2021-04-02 10:00","2021-04-02 18:00","연속"]
[312,"충북","충주","풍동장연 T/L","2021년 충주전력지사 가공송전 순시점검 위탁공사","정밀점검 (S/S~38)","2021-04-19 09:00","2021-04-23 18:00","2021-04-19 09:00","2021-04-23 18:00","매일"]
[313,"충북","충주","신제천제천#1 T/L","20-21년 충주전력지사 변전정비 총액공사","남음성S/S 금왕-남음성#2T/L 차단기 조작시험, LA 점검","2021-04-09 10:00","2021-04-09 18:00","2021-04-09 10:00","2021-04-09 18:00","연속"]
[314,"충북","충주","충주충주HP#1 T/L","2021년 충주전력지사 가공송전 순시점검 위탁공사","정밀점검 (충주S/S, 1~6, 23, S/T)","2021-04-05 09:00","2021-04-06 18:00","2021-04-26 09:00","2021-04-27 18:00","매일"]
[315,"충북","충주","충주충주HP#2 T/L","2021년 충주전력지사 가공송전 순시점검 위탁공사","정밀점검 (충주S/S, 1~6, 23, S/T)","2021-04-07 09:00","2021-04-08 18:00","2021-04-28 09:00","2021-04-29 18:00","매일"]
[316,"충북","충주","충주장연 T/L","2021년 충주전력지사 가공송전 순시점검 위탁공사","정밀점검 (S/S~38)","2021-04-12 09:00","2021-04-16 18:00","취소","취소","매일"]
[317,"대전충남","대전","팔봉두마#2 T/L","[송전]154kV 신옥천-서대전 등 6개T/L 피뢰기 설치공사","[송전] 154kV 신계룡-두마#2T/L 피뢰기 설치공사 안전확보","2021-04-15 07:00","2021-04-16 18:00","취소","취소","매일"]
[318,"대전충남","대전","팔봉두마#1 T/L","[송전]154kV 신옥천-서대전 등 6개T/L 피뢰기 설치공사","[송전] 154kV 신계룡-은진#2T/L 피뢰기 설치공사 안전확보","2021-04-09 07:00","2021-04-12 18:00","취소","취소","매일"]
[319,"대전충남","대전","신옥천서대전 T/L","[송전]154kV 신옥천-서대전 등 6개T/L 피뢰기 설치공사","[송전] 154kV 신옥천-서대전 T/L 피뢰기 설치공사","2021-04-22 07:00","2021-05-06 18:00","2021-04-22 07:00","2021-05-06 18:00","매일"]
[320,"대전충남","대전","신계룡두마#1 T/L","154kV 신계룡-두마T/L OPGW 증설공사","신계룡S/S ~ 두마S/S 간 가공지선(ACSR 97SQ)를 OPGW/100SQ로 변경","2021-04-19 08:00","2021-04-21 18:00","2021-04-01 08:00","2021-04-01 18:00","매일"]
[321,"대전충남","대전","신계룡두마#2 T/L","154kV 신계룡-두마T/L OPGW 증설공사","신계룡S/S ~ 두마S/S 간 가공지선(ACSR 97SQ)를 OPGW/100SQ로 변경","2021-04-19 08:00","2021-04-21 18:00","2021-04-01 08:00","2021-04-01 18:00","매일"]
[322,"대전충남","대전","용운대화#1 T/L","[송전]154kV 신옥천-서대전 등 6개T/L 피뢰기 설치공사","[송전]154kV 신옥천-용운 #2T/L 피뢰기 설치공사 안전확보","2021-04-05 07:00","2021-04-05 18:00","2021-04-05 07:00","2021-04-05 18:00","연속"]
[323,"대전충남","서산","석문당진화력#2 T/L","154kV 석문-당진화력T/L 피뢰기 교체공사 및 EBA절연유 채유","154kV 석문-당진화력T/L 피뢰기 교체공사 및 EBA절연유 채유","2021-04-13 09:00","2021-04-15 18:00","2021-04-13 09:00","2021-04-15 18:00","연속"]
[324,"대전충남","서산","석문당진화력#1 T/L","154kV 석문-당진화력T/L 피뢰기 교체공사 및 EBA절연유 채유","154kV 석문-당진화력T/L 피뢰기 교체공사 및 EBA절연유 채유","2021-04-06 09:00","2021-04-08 18:00","2021-04-06 09:00","2021-04-08 18:00","연속"]
[325,"대전충남","서산","대산석문#1 T/L","154kV 대산-석문#1T/L 불량개소 정비","154kV 대산-석문#1T/L 불량개소 정비 : No.23, 34","2021-04-02 09:00","2021-04-02 13:00","2021-04-19 08:00","2021-04-19 18:00","연속"]
[326,"대전충남","서산","GSEPS#1 T/L","154kV GS-EPS#1 T/L 피뢰기 설치공사","154kV GS-EPS#1 T/L 피뢰기 설치공사, 345kV 북당진-현대제철T/L 피뢰기 설치공사","2021-04-26 09:00","2021-04-27 18:00","2021-04-26 09:00","2021-04-27 18:00","매일"]
[327,"대전충남","서산","GSEPS#2 T/L","345kV GS-EPS분기 T/L 항공장애표시구 설치공사","345kV GS-EPS분기 T/L 항공장애표시구 설치공사, 4회선 병가철탑 안전이격확보","2021-04-07 09:00","2021-04-07 18:00","2021-04-07 09:00","2021-04-07 18:00","매일"]
[328,"대전충남","서산","신당진서산#1 T/L","154kV 신당진-서산#1T/L 불량개소 정비","154kV신당진-서산#1T/L 불량개소 정비: No.33","2021-04-02 13:00","2021-04-02 17:00","2021-04-20 08:00","2021-04-20 18:00","연속"]
[329,"대전충남","서산","서산태안화력 T/L","'21년 장기 미동작 차단기 조작시험","태안T/P 154kV 서산-태안화력T/L 617 CB 조작시험","2021-04-15 10:00","2021-04-15 14:00","2021-04-16 10:00","2021-04-16 14:00","연속"]
[330,"대전충남","서산","해미홍성 T/L","21년 서산P/O 154kV GIS 정밀점검공사","해미S/S 154kV 해미-홍성 T/L GIS(637) 정밀점검","2021-04-21 10:00","2021-04-23 18:00","취소","취소","연속"]
[331,"대전충남","서산","서산해미 T/L","21년 서산P/O 154kV GIS 정밀점검공사","해미S/S 154kV 서산-해미 T/L GIS(617) 정밀점검","2021-04-19 10:00","2021-04-21 18:00","취소","취소","연속"]
[332,"대전충남","세종","신풍공주#1 T/L","[변전]세종PO변전정비총액공사","공주S/S 신풍-공주#1,2T/L 조작시험","2021-04-14 09:00","2021-04-14 12:00","2021-04-14 09:00","2021-04-14 12:00","연속"]
[333,"대전충남","세종","신풍공주#2 T/L","[변전]세종PO변전정비총액공사","공주S/S 신풍-공주#1,2T/L 조작시험","2021-04-14 12:00","2021-04-14 15:00","2021-04-14 12:00","2021-04-14 15:00","연속"]
[334,"대전충남","세종","덕진대화#2 T/L","[변전]세종PO변전정비총액공사","덕진S/S 덕진-대화#1,2T/L 조작시험","2021-04-05 11:00","2021-04-05 13:00","2021-04-05 11:00","2021-04-05 13:00","연속"]
[335,"대전충남","세종","덕진공주#2 T/L","[송전]국제과학비즈니스벨트 지장송전선로 지중화공사(요청자시행)","요청자(한국토지주택공사) 직접시행 지중화공사","2021-04-01 07:00","2021-04-02 18:00","2021-04-01 07:00","2021-04-02 18:00","연속"]
[336,"대전충남","세종","덕진유성#2 T/L","[송전]국제과학비즈니스벨트 지장송전선로 지중화공사(요청자시행)","요청자(한국토지주택공사) 직접시행 지중화공사","2021-04-01 07:00","2021-04-02 18:00","2021-04-01 07:00","2021-04-02 18:00","연속"]
[337,"대전충남","세종","덕진대화#1 T/L","[변전]세종PO변전정비총액공사","덕진S/S 덕진-대화#1,2T/L 조작시험","2021-04-05 09:00","2021-04-05 11:00","2021-04-05 09:00","2021-04-05 11:00","연속"]
[338,"대전충남","세종","덕진공주#1 T/L","[송전]국제과학비즈니스벨트 지장송전선로 지중화공사(요청자시행)","요청자(한국토지주택공사) 직접시행 지중화공사","2021-04-03 07:00","2021-04-03 18:00","2021-04-03 07:00","2021-04-03 18:00","연속"]
[339,"대전충남","세종","덕진유성#1 T/L","[송전]국제과학비즈니스벨트 지장송전선로 지중화공사(요청자시행)","요청자(한국토지주택공사) 직접시행 지중화공사","2021-04-03 07:00","2021-04-03 18:00","2021-04-03 07:00","2021-04-03 18:00","연속"]
[340,"대전충남","세종","둔곡송강#1 T/L","[송전]154kV 둔곡-송강#1T/L 지지애자 교체공사","154kV 둔곡-송강#1T/L No.5 지지애자 교체","2021-04-01 08:00","2021-04-01 12:00","2021-04-01 08:00","2021-04-01 12:00","연속"]
[341,"대전충남","세종","둔곡송강#2 T/L","[송전]154kV 둔곡-송강#1T/L 지지애자 교체공사","154kV 둔곡-송강#1T/L No.10 지지애자 교체","2021-04-01 12:00","2021-04-01 18:00","2021-04-01 12:00","2021-04-01 18:00","연속"]
[342,"대전충남","세종","부강신탄진 T/L","[변전]세종PO변전정비총액공사","부강S/S 부강-신탄진T/L 보통점검 및 LA 초기점검","2021-04-07 09:00","2021-04-07 18:00","2021-04-07 09:00","2021-04-07 18:00","연속"]
[343,"대전충남","세종","부강월산#1 T/L","[송전]154kV 부강-월산T/L 지장송전선로 이설공사","154kV 부강-월산T/L No.29-1~35 추락방지장치 설치 스페이서 간격 조정","2021-04-05 07:00","2021-04-09 18:00","2021-04-05 07:00","2021-04-09 18:00","연속"]
[344,"대전충남","세종","부강월산#2 T/L","[송전]154kV 부강-월산T/L 지장송전선로 이설공사","154kV 부강-월산T/L No.29-1~35 추락방지장치 설치 스페이서 간격 조정","2021-04-12 07:00","2021-04-14 18:00","2021-04-12 07:00","2021-04-14 18:00","연속"]
[345,"대전충남","세종","부강대청HP T/L","[변전]세종PO변전정비총액공사","부강S/S 부강-대청H/P T/L 보통점검 및 LA 초기점검","2021-04-06 09:00","2021-04-06 18:00","2021-04-06 09:00","2021-04-06 18:00","연속"]
[346,"대전충남","아산","신온양석곡#1 T/L","[21년 가공송전 순시점검 위탁공사] 정밀점검","154kV 신온양-한샘#1T/L 초기점검 - No.2~7(6기) - 4회선 병가 철탑","2021-04-12 08:00","2021-04-12 18:00","2021-04-12 08:00","2021-04-12 18:00","연속"]
[347,"대전충남","아산","신온양석곡#2 T/L","[21년 가공송전 순시점검 위탁공사] 정밀점검","154kV 신온양-한샘#2T/L 초기점검 - No.2~7(6기) - 4회선 병가 철탑","2021-04-14 08:00","2021-04-14 18:00","2021-04-14 08:00","2021-04-14 18:00","연속"]
[348,"대전충남","아산","신온양한샘#1 T/L","[21년 가공송전 순시점검 위탁공사] 정밀점검","154kV 신온양-한샘#1T/L 초기점검 - No.2~17(16기)","2021-04-12 08:00","2021-04-13 18:00","2021-04-12 08:00","2021-04-13 18:00","매일"]
[349,"대전충남","아산","신온양한샘#2 T/L","[21년 가공송전 순시점검 위탁공사] 정밀점검","154kV 신온양-한샘#2T/L 초기점검 - No.2~17(16기)","2021-04-14 08:00","2021-04-15 18:00","2021-04-14 08:00","2021-04-15 18:00","매일"]
[350,"대전충남","아산","예산응봉#2 T/L","154kV 예산변전소 미래화공사","154kV 예산변전소 미래화공사","2021-04-22 09:00","2021-04-22 18:00","취소","취소","연속"]
[351,"대전충남","아산","아산예산#1 T/L","154kV 예산변전소 미래화공사","154kV 예산변전소 미래화공사","2021-04-19 09:00","2021-04-19 18:00","2021-04-19 09:00","2021-04-19 18:00","연속"]
[352,"대전충남","아산","예산응봉#1 T/L","154kV 예산변전소 미래화공사","154kV 예산변전소 미래화공사","2021-04-21 09:00","2021-04-21 18:00","취소","취소","연속"]
[353,"대전충남","아산","아산예산#2 T/L","154kV 예산변전소 미래화공사","154kV 예산변전소 미래화공사","2021-04-20 09:00","2021-04-20 18:00","2021-04-20 09:00","2021-04-20 18:00","연속"]
[354,"대전충남","아산","서천안탕정#1 T/L","154kV 인주-불당T/L C/H 건설사업","임시선로 → 본선로 이설","2021-04-07 09:00","2021-04-15 18:00","취소","취소","연속"]
[355,"대전충남","아산","인주탕정#2 T/L","154kV 인주-불당T/L C/H 건설사업","임시선로 → 본선로 이설","2021-04-07 09:00","2021-04-15 18:00","취소","취소","연속"]
[356,"대전충남","아산","한샘직산#1 T/L","(송전)154kV 한샘-직산T/L 안전이격 확보공사","154kV 한샘-직산T/L No.4-6호간 안전이격 확보공사 - 공사내용 : 철탑 보강 1기(계탑)","2021-04-19 09:00","2021-04-20 18:00","취소","취소","연속"]
[357,"대전충남","아산","한샘직산#2 T/L","(송전)154kV 한샘-직산T/L 안전이격 확보공사","154kV 한샘-직산T/L No.4-6호간 안전이격 확보공사 - 공사내용 : 철탑 보강 1기(계탑)","2021-04-19 09:00","2021-04-20 18:00","취소","취소","연속"]
[358,"대전충남","직할","동대전신탄진#1 T/L","154kV 동대전-신탄진T/L 안전이격거리 확보공사","지상고 부족 및 정전 유도로부터의 안전을 확보 - 철탑 :3기 신설(No.7, 8, 13), 1기 보강(No.14)","2021-04-21 09:00","2021-05-10 18:00","2021-04-28 09:00","2021-05-17 18:00","연속"]
[359,"대전충남","직할","동대전신탄진#2 T/L","154kV 동대전-신탄진T/L 안전이격거리 확보공사","지상고 부족 및 정전 유도로부터의 안전을 확보 - 철탑 :3기 신설(No.7, 8, 13), 1기 보강(No.14)","2021-04-21 09:00","2021-05-10 18:00","2021-04-28 09:00","2021-05-17 18:00","연속"]
[360,"대전충남","청양","보령TP보령CC T/L","보령T/P 보령복합T/L GIS 정밀점검","보령T/P 보령복합T/L GIS 정밀점검 ○ 보령C/C 보령복합T/L GIS 보통점검 및 LA, CVT 보통점검","2021-04-14 09:00","2021-04-16 18:00","2021-04-14 09:00","2021-04-16 18:00","연속"]
[361,"대전충남","청양","관창보령TP T/L","보령T/P 관창-보령화력T/L GIS 정밀점검","관창S/S GIS보통점검 및 전자변교체 ○ 보령T/P LA, CVT 보통점검","2021-04-12 09:00","2021-04-14 18:00","2021-04-12 09:00","2021-04-14 18:00","연속"]
[362,"대전충남","청양","청양신풍#1 T/L","154kV 청양-신풍#1T/L 관련기기 점검","청양S/S 차단기 부동작예방 조작시험 ○ 신풍S/S 누기개소 점검, GIS 보통점검","2021-04-06 09:00","2021-04-06 18:00","2021-04-06 09:00","2021-04-06 18:00","연속"]
[363,"전북","군산","군공소룡#2 T/L","군산P/O 154kV 이상 차단기 보통점검","군공S/S 687, 소룡S/S 647 CB 보통점검  (비상시 즉시가압 가능)","2021-04-23 10:00","2021-04-23 18:00","2021-04-23 10:00","2021-04-23 18:00","연속"]
[364,"전북","군산","군공소룡#1 T/L","군산P/O 154kV 이상 차단기 보통점검","소룡S/S 657 CB 보통점검  (비상시 즉시가압 가능)","2021-04-22 10:00","2021-04-22 18:00","2021-04-22 10:00","2021-04-22 18:00","연속"]
[365,"전북","군산","군공내초#2 T/L","지중송전 위탁정비공사 OF선로 절연유 채유","지중송전선로 OF접속함 절연유 채유  (비상시 즉시가압 가능)","2021-04-11 09:00","2021-04-11 18:00","취소","취소","연속"]
[366,"전북","군산","군공S/S CB 6100","군산P/O 차단기 조작시험공사","군공S/S 6100차단기 조작시험 (비상시 즉시가압 가능)","2021-04-20 13:00","2021-04-20 18:00","2021-04-20 13:00","2021-04-20 18:00","연속"]
[367,"전북","군산","군공내초#1 T/L","지중송전 위탁정비공사 OF선로 절연유 채유","지중송전선로 OF접속함 절연유 채유 (비상시 즉시가압 가능)","2021-04-10 09:00","2021-04-10 18:00","취소","취소","연속"]
[368,"전북","군산","군산동군산#2 T/L","군산P/O 154kV 이상 차단기 점검공사","군산S/S 6B7CB 보통점검 (비상시 즉시가압 가능)","2021-04-07 09:00","2021-04-07 18:00","취소","취소","연속"]
[369,"전북","군산","군산동군산#1 T/L","군산P/O 154kV 이상 차단기 점검공사","군산S/S 6A7CB 보통점검 (비상시 즉시가압 가능)","2021-04-06 09:00","2021-04-06 18:00","취소","취소","연속"]
[370,"전북","군산","군산서군산#2 T/L","군산P/O 154kV 이상 차단기 점검공사","군산S/S 6D7CB 보통점검 (비상시 즉시가압 가능)","2021-04-28 09:00","2021-04-28 18:00","2021-04-28 09:00","2021-04-28 18:00","연속"]
[371,"전북","군산","군산영등#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사"," OPGW교체(24C→48C) (비상시 즉시가압 가능)","2021-04-09 07:00","2021-04-16 18:00","취소","취소","매일"]
[372,"전북","군산","군산이리#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사"," OPGW교체(24C→48C) (비상시 즉시가압 가능)","2021-04-10 07:00","2021-04-16 18:00","취소","취소","매일"]
[373,"전북","군산","군산이리#1 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사"," OPGW교체(24C→48C) (비상시 즉시가압 가능)","2021-04-24 07:00","2021-04-25 18:00","취소","취소","매일"]
[374,"전북","군산","군산영등#1 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사"," OPGW교체(24C→48C) (비상시 즉시가압 가능)","2021-04-24 07:00","2021-04-30 18:00","취소","취소","매일"]
[375,"전북","군산","군산서군산#1 T/L","군산P/O 154kV 이상 차단기 점검공사","군산S/S 6C7CB 보통점검 (비상시 즉시가압 가능)","2021-04-27 09:00","2021-04-27 18:00","2021-04-27 09:00","2021-04-27 18:00","연속"]
[376,"전북","군산","내초군장#1 T/L","군산P/O 차단기 조작시험 공사","내초-군장1TL 조작시험 (비상시 즉시가압 가능)","2021-04-16 09:00","2021-04-16 12:00","2021-04-16 09:00","2021-04-16 12:00","연속"]
[377,"전북","군산","내초군장#2 T/L","군산P/O 차단기 조작시험 공사","내초-군장2TL 조작시험 (비상시 즉시가압 가능)","2021-04-16 13:00","2021-04-16 18:00","2021-04-16 13:00","2021-04-16 18:00","연속"]
[378,"전북","군산","동군산장항#1 T/L","154kV 동군산-장항 #1T/L 피뢰기설치공사","송전선로 피뢰기 설치공사 No.18~38호간  (비상시 즉시가압 가능)","2021-04-14 07:00","2021-04-15 18:00","취소","취소","매일"]
[379,"전북","군산","동군산장항#2 T/L","군산P/O 차단기 조작시험 공사","군산P/O 차단기 조작시험 공사 (비상시 즉시가압 가능)","2021-04-13 09:00","2021-04-13 14:00","취소","취소","연속"]
[380,"전북","군산","동군산군산CC#1 T/L","군산P/O 차단기 조작시험 공사","군산P/O 차단기 조작시험 공사 (비상시 즉시가압 가능)","2021-04-17 09:00","2021-04-17 14:00","취소","취소","연속"]
[381,"전북","군산","비응군장#1 T/L","군산P/O 154kV 이상 차단기 점검공사","비응S/S 647CB 보통점검 (비상시 즉시가압 가능)","2021-04-20 10:00","2021-04-20 18:00","2021-04-20 10:00","2021-04-20 18:00","연속"]
[382,"전북","군산","비응군장#2 T/L","군산P/O 154kV 이상 차단기 점검공사","비응S/S 667CB 보통점검 (비상시 즉시가압 가능)","2021-04-21 10:00","2021-04-21 18:00","2021-04-21 10:00","2021-04-21 18:00","연속"]
[383,"전북","군산","새만금소룡#2 T/L","154kV 새만금-소룡T/L 리콜 접속함 교체공사","리콜(하자) R타입 PMJ 접속함 23상 교체공사(토목작업)","2021-04-19 09:00","2021-05-02 18:00","2021-04-19 09:00","2021-05-02 18:00","연속"]
[384,"전북","군산","새만금소룡#1 T/L","154kV 새만금-소룡T/L 리콜 접속함 교체공사","리콜(하자) R타입 PMJ 접속함 23상 교체공사","2021-04-05 09:00","2021-04-18 18:00","2021-04-05 09:00","2021-04-18 18:00","연속"]
[385,"전북","군산","새만금소룡#2 T/L","154kV 새만금-소룡T/L 리콜 접속함 교체공사(양회선 동시휴전)","리콜(하자) R타입 PMJ 접속함 23상 교체공사(토목작업)","2021-04-05 09:00","2021-04-08 18:00","2021-04-05 09:00","2021-04-08 18:00","연속"]
[386,"전북","군산","새만금비응#1 T/L","군산P/O 차단기 조작시험 공사","군산P/O 차단기 조작시험 공사 (비상시 즉시가압 가능)","2021-04-14 09:00","2021-04-14 18:00","취소","취소","연속"]
[387,"전북","군산","새만금비응#2 T/L","군산P/O 차단기 조작시험 공사","군산P/O 차단기 조작시험 공사 (비상시 즉시가압 가능)","2021-04-15 09:00","2021-04-15 18:00","2021-04-15 09:00","2021-04-15 18:00","연속"]
[388,"전북","군산","서군산소룡#1 T/L","군산P/O 차단기 조작시험 공사","군산P/O 차단기 조작시험 공사 (비상시 즉시가압 가능)","2021-04-09 09:00","2021-04-09 18:00","2021-04-09 09:00","2021-04-09 18:00","연속"]
[389,"전북","군산","서군산소룡#2 T/L","154kV 서군산-소룡 #2T/L 전선접속개소 정비공사","송전선로 전선접속개소 정비공사 No.6~9호간","2021-04-12 07:00","2021-04-13 18:00","2021-04-12 07:00","2021-04-13 18:00","연속"]
[390,"전북","군산","영등팔봉#1 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","OPGW교체(24C→48C) (비상시 즉시가압 가능)","2021-04-19 00:07","2021-04-21 18:00","취소","취소","매일"]
[391,"전북","군산","영등팔봉#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","OPGW교체(24C→48C) (비상시 즉시가압 가능)","2021-04-19 07:00","2021-04-21 18:00","취소","취소","매일"]
[392,"전북","김제","정주고창#1 T/L","관내S/S 154kV 차단기 조작시험","고창S/S 154kV 차단기 조작시험 (비상시 즉시가압 가능)","2021-04-08 09:00","2021-04-08 18:00","취소","취소","연속"]
[393,"전북","김제","정주고창#2 T/L","관내S/S 154kV 차단기 조작시험","고창S/S 154kV 차단기 조작시험 (비상시 즉시가압 가능)","2021-04-09 09:00","2021-04-09 18:00","취소","취소","연속"]
[394,"전북","김제","신김제남전주#1 T/L","154kV 신김제-남전주#1T/L 송전선로 피뢰기 설치공사","No.1~36호 송전선로 피뢰기 설치공사  (비상시 즉시가압 가능)","2021-04-26 09:00","2021-04-30 18:00","2021-04-26 09:00","2021-04-30 18:00","매일"]
[395,"전북","김제","김제부안#1 T/L","154kV 김제-부안#1T/L 초기점검","154kV 김제-부안#1T/L 초기점검(No.1~65호)  (비상시 즉시가압 가능)","2021-04-19 09:00","2021-04-23 18:00","2021-04-19 09:00","2021-04-23 18:00","매일"]
[396,"전북","김제","김제부안#2 T/L","154kV 김제-부안#2T/L 초기점검","154kV 김제-부안#2T/L 초기점검(No.1~65호)  (비상시 즉시가압 가능)","2021-04-26 09:00","2021-04-30 18:00","2021-04-26 09:00","2021-04-30 18:00","매일"]
[397,"전북","김제","신김제S/S CB 6200","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분)","(구)남전주#1, 65-66-0 SEC GIS 교체, 인출변경에 따른 케이블 이설 1식","2021-04-03 16:00","2021-04-30 13:00","2021-04-03 16:00","2021-04-30 13:00","연속"]
[398,"전북","김제","신김제S/S SEC CB 65660","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분)","(구)남전주#1, 65-66-0 SEC GIS 교체, 인출변경에 따른 케이블 이설 1식","2021-04-03 16:00","2021-04-30 13:00","2021-04-03 16:00","2021-04-30 13:00","연속"]
[399,"전북","김제","신김제S/S SEC CB 66670","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분)","(구)남전주#1, 65-66-0 SEC GIS 교체, 인출변경에 따른 케이블 이설 1식","2021-04-03 16:00","2021-04-30 13:00","2021-04-03 16:00","2021-04-30 13:00","연속"]
[400,"전북","김제","신김제S/S CB 6100","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분)","(구)남전주#1, 65-66-0 SEC GIS 교체, 인출변경에 따른 케이블 이설 1식","2021-04-03 16:00","2021-04-30 13:00","2021-04-03 16:00","2021-04-30 13:00","연속"]
[401,"전북","김제","신김제S/S 154kV #66 BUS","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분)","(구)남전주#1, 65-66-0 SEC GIS 교체, 인출변경에 따른 케이블 이설 1식","2021-04-03 16:00","2021-04-30 13:00","2021-04-03 16:00","2021-04-30 13:00","연속"]
[402,"전북","김제","신김제정공#1 T/L","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분)(시험가압)","(구)남전주#1, 65-66-0 SEC GIS 교체, 인출변경에 따른 케이블 이설 1식","2021-04-02 09:00","2021-04-03 16:00","2021-04-02 09:00","2021-04-03 16:00","연속"]
[403,"전북","김제","신김제동전주#2 T/L","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분)(인출변경)","(구)남전주#1, 65-66-0 SEC GIS 교체, 인출변경에 따른 케이블 이설 1식\n- 647CB 신김제-동전주 #2 T/L => 667CB 로 이동","2021-04-19 09:00","2021-04-30 18:00","2021-04-19 09:00","2021-04-30 18:00","연속"]
[404,"전북","김제","신김제전주#2 T/L","154kV 신김제-전주#2T/L 송전선로 피뢰기 설치공사","No.6~55호 송전선로 피뢰기 설치공사  (비상시 즉시가압 가능)","2021-04-26 09:00","2021-04-30 18:00","2021-04-26 09:00","2021-04-30 18:00","매일"]
[405,"전북","김제","신김제전주#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","OPGW교체(24C→48C) (비상시 즉시가압 가능)","2021-04-08 07:00","2021-04-09 18:00","취소","취소","매일"]
[406,"전북","김제","신김제남전주#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","OPGW교체(24C→48C) (비상시 즉시가압 가능)","2021-04-03 07:00","2021-04-09 18:00","취소","취소","매일"]
[407,"전북","김제","신김제전주#1 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","OPGW교체(24C→48C) (비상시 즉시가압 가능)","2021-04-03 07:00","2021-04-07 18:00","취소","취소","매일"]
[408,"전북","김제","신김제정공#2 T/L","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분) (인출변경)","(구)남전주#1, 65-66-0 SEC GIS 교체, 인출변경에 따른 케이블 이설 1식\n- 647CB 신김제-동전주 #2 T/L => 667CB 로 이동","2021-04-19 09:00","2021-04-30 18:00","2021-04-19 09:00","2021-04-30 18:00","연속"]
[409,"전북","김제","신김제동전주#2 T/L","신김제S/S 노후 GIS 교체 및 인출재배열 공사 (6차분) (안전이격)","(구)남전주#1, 65-66-0 SEC GIS 교체, 인출변경에 따른 케이블 이설 1식 (비상시 즉시가압 가능)","2021-04-05 07:00","2021-04-06 18:00","2021-04-05 07:00","2021-04-06 18:00","매일"]
[410,"전북","김제","정공S/S 154kV #60 BUS","정공S/S 170kV GIS 교체공사","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2021-04-07 13:00","2021-04-12 13:00","2021-04-07 13:00","2021-04-12 13:00","연속"]
[411,"전북","김제","신김제정공#1 T/L","정공S/S 170kV GIS 교체공사 시험가압","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2021-04-11 13:00","2021-04-12 13:00","2021-04-11 13:00","2021-04-12 13:00","연속"]
[412,"전북","김제","정공S/S 154kV #65 BUS","정공S/S 170kV GIS 교체공사","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2021-04-12 13:00","2021-04-25 13:00","2021-04-12 13:00","2021-04-25 13:00","연속"]
[413,"전북","김제","신김제정공#1 T/L","정공S/S 170kV GIS 교체공사 시험가압","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2021-04-07 11:00","2021-04-07 13:00","2021-04-07 11:00","2021-04-07 13:00","연속"]
[414,"전북","김제","정공S/S CB 6100","정공S/S 170kV GIS 교체공사","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2021-04-05 09:00","2021-04-25 18:00","2021-04-05 09:00","2021-04-25 18:00","연속"]
[415,"전북","김제","정공S/S 154kV #65 BUS","정공S/S 170kV GIS 교체공사","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2021-04-05 09:00","2021-04-07 13:00","2021-04-05 09:00","2021-04-07 13:00","연속"]
[416,"전북","김제","정공정주#2 T/L","정공S/S 170kV GIS 교체공사 (MAIN 교체)","170kV GIS 7BAY 철거 및 설치 170kV GIS 3BAY 설치 기타부대공사","2021-04-05 09:00","2021-04-25 18:00","2021-04-05 09:00","2021-04-25 18:00","연속"]
[417,"전북","직할","신남원남원#2 T/L","154kV 남원S/S 옥외철구설비 GIS화 공사","154kV 신남원-남원#2T/L 인출구간 변경 및 GIS설비로 이전","2021-04-14 08:00","2021-04-30 18:00","2021-04-14 08:00","2021-04-30 18:00","연속"]
[418,"전북","직할","곡성남원#2 T/L","154kV 남원S/S 옥외철구설비 GIS화 공사","154kV 곡성-남원#2T/L 인출구간 변경 및 GIS설비로 이전","2021-04-14 08:00","2021-04-30 18:00","2021-04-22 08:00","2021-04-30 13:00","연속"]
[419,"전북","직할","신김제동전주#1 T/L","동전주S/S SA혼용시스템 설치공사","154kV 신김제-동전주#1T/L SA 설치공사 (비상시 즉시가압 가능)","2021-04-16 09:00","2021-04-16 18:00","2021-04-16 09:00","2021-04-16 18:00","연속"]
[420,"전북","직할","무주용담수력 T/L","무주S/S 154kV GIS 교체공사(전문) (시험가압)","154kV #60BUS 무부하 가압 선로 - 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체\n(대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT) (비상 즉시가압 가능)","2021-04-20 15:00","2021-04-21 15:00","취소","취소","연속"]
[421,"전북","직할","무주S/S CB 6100","무주S/S 154kV GIS 교체공사(Main 교체)","170kV GIS 50kA(1250/2000A) GIS 5CCT 대체\n(대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2021-04-05 10:00","2021-05-15 15:00","취소","취소","연속"]
[422,"전북","직할","무주S/S 154kV #1 BUS","무주S/S 170kV 장기사용 GIS 교체공사","무주S/S 170kV 장기사용 GIS 교체공사","2021-04-21 15:00","2021-05-02 15:00","취소","취소","연속"]
[423,"전북","직할","금산무주#1 T/L","무주S/S 154kV GIS 교체공사(Main 교체)"," 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 \n(대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2021-04-05 10:00","2021-05-15 15:00","취소","취소","연속"]
[424,"전북","직할","무주S/S 154kV #2 BUS","무주S/S 154kV GIS 교체공사(전문)"," 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체 \n(대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2021-04-05 10:00","2021-04-21 15:00","취소","취소","연속"]
[425,"전북","직할","무주용담수력 T/L","(2차)무주S/S 154kV GIS 교체공사(안전이격)","154kV #60BUS 무부하 가압 선로 - 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체\n(대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT) (비상 즉시가압 가능)","2021-04-11 09:00","2021-04-11 11:00","취소","취소","연속"]
[426,"전북","직할","금산무주#2 T/L","(2차)무주S/S 154kV GIS 교체공사(안전이격)","154kV #60BUS 무부하 가압 선로 - 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체\n(대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT) (비상 즉시가압 가능)","2021-04-11 11:00","2021-04-11 13:00","취소","취소","연속"]
[427,"전북","직할","무주진안 T/L","무주S/S 154kV GIS 교체공사(전문)(시험가압)","154kV #60BUS 무부하 가압 선로 - 170kV GIS 50kA(1250/2000A) GIS 5CCT 대체\n(대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT) (비상 즉시가압 가능)","2021-04-20 15:00","2021-04-21 15:00","취소","취소","연속"]
[428,"전북","직할","팔봉봉동#2 T/L","전북본부 관내 EBA 자기애관 교체공사","기설 EBA 자기애관 철거 및 폴리머애관 설치","2021-04-19 09:00","2021-04-25 18:00","취소","취소","연속"]
[429,"전북","직할","팔봉봉동#1 T/L","전북본부 관내 EBA 자기애관 교체공사","기설 EBA 자기애관 철거 및 폴리머애관 설치","2021-04-12 09:00","2021-04-18 18:00","2021-04-12 09:00","2021-04-18 18:00","연속"]
[430,"전북","직할","북전주봉동#2 T/L","2020~2021년 전북 직할 변전정비회사 총액공사","관내 154kV 이상 차단기 점검공사 - 북전주S/S 154kV 북전주-봉동#2/TL 전자변교체\n(조작시험포함,  비상시 즉시가압 가능)","2021-04-09 09:00","2021-04-09 18:00","2021-04-09 09:00","2021-04-09 18:00","연속"]
[431,"전북","직할","탄소이리#2 T/L","관내 154kV 차단기 하자점검","관내 154kV 차단기 하자점검  (비상시 즉시가압 가능)","2021-04-22 09:00","2021-04-22 18:00","2021-04-22 09:00","2021-04-22 18:00","연속"]
[432,"전북","직할","탄소이리#1 T/L","관내 154kV 차단기 하자점검","관내 154kV 차단기 하자점검  (비상시 즉시가압 가능)","2021-04-21 09:00","2021-04-21 18:00","2021-04-21 09:00","2021-04-21 18:00","연속"]
[433,"전북","직할","탄소전주#2 T/L","관내 154kV 차단기 하자점검","관내 154kV 차단기 하자점검  (비상시 즉시가압 가능)","2021-04-20 09:00","2021-04-20 18:00","2021-04-20 09:00","2021-04-20 18:00","연속"]
[434,"전북","군산","군산이리#1 T/L","154kV 군산-이리T/L 송전선로 회전 스페이서 설치공사","154kV 군산-이리T/L 송전선로 회전 스페이서 설치공사","2021-04-09 07:00","2021-04-09 18:00","2021-04-09 07:00","2021-04-09 18:00","연속"]
[435,"전북","직할","탄소전주#1 T/L","관내 154kV 차단기 하자점검","관내 154kV 차단기 하자점검 - 탄소측 하자점검, 전주측 보통점검 \n (비상시 즉시가압 가능)","2021-04-19 09:00","2021-04-19 18:00","2021-04-19 09:00","2021-04-19 18:00","연속"]
[436,"광주전남","강진","나주금천#1 T/L","154kV 신화순-나주T/L 지장철탑 이설공사","강진광주간 고속도로 관련 지장철탑 이설 154kV 신화순-나주T/L 52-55호 (154kV 나주-금천T/L 89-92호 병가) 철탑 1기 철거, 1기 신설(53호), 임시철탑 1기","2021-04-26 08:00","2021-04-30 18:00","취소","취소","연속"]
[437,"광주전남","강진","나주금천#1 T/L","154kV 신화순-나주T/L 지장철탑 이설공사","강진광주간 고속도로 관련 지장철탑 이설 154kV 신화순-나주T/L 52-55호 (154kV 나주-금천T/L 89-92호 병가) 철탑 1기 철거, 1기 신설(53호), 임시철탑 1기","2021-04-03 08:00","2021-04-08 18:00","2021-04-25 09:00","2021-04-30 18:00","연속"]
[438,"광주전남","강진","남창완도#1 T/L","154kV 남창-완도#1 등 2개T/L 지중화공사","공사목적 : 남창S/S GIS 현대화에 따른 인출모선 재배열 공사 공사구간 : 154kV 남창-완도#1 EBA~EBG (남창S/S 구내)","2021-04-12 09:00","2021-04-23 18:00","취소","취소","연속"]
[439,"광주전남","강진","남창완도#2 T/L","154kV 남창S/S GIS화 공사","제어케이블 철거, 설치 및 결선 × 1식 ○ 기타 부대작업 × 1식","2021-04-26 09:00","2022-05-03 18:00","2021-05-10 09:00","2022-06-30 18:00","연속"]
[440,"광주전남","강진","강진남창#1 T/L","154kV 남창S/S GIS화 공사","제어케이블 철거, 설치 및 결선 × 1식 ○ 기타 부대작업 × 1식","2021-04-26 09:00","2022-05-03 18:00","2021-05-10 09:00","2022-06-30 18:00","연속"]
[441,"광주전남","강진","강진남창#2 T/L","154kV 남창-완도#1 등 2개T/L 지중화공사","남창S/S GIS 현대화에 따른 인출모선 재배열 공사 공사구간\n강진-남창#2T/L EBA~ EBG (남창S/S 구내)","2021-04-05 09:00","2021-04-23 18:00","2021-04-19 09:00","2021-05-07 18:00","연속"]
[442,"광주전남","강진","신강진대불#2 T/L","2020~21년 송전정비회사 총액공사","154kV 신강진-해남#1T/L 피뢰기 설치공사 - 병가구간 피뢰기 설치(안전이격휴전)","2021-04-14 07:00","2021-04-16 18:00","2021-04-14 07:00","2021-04-16 18:00","연속"]
[443,"광주전남","광주","계림승주#1 T/L","154kV 계림-승주#1 T/L 불량애자교체","20-21년 송전협력회사 총액공사 154kV 계림-승주#1 T/L 불량애자교체(2, 71, 89호)","2021-04-21 07:00","2021-04-22 18:00","2021-04-21 07:00","2021-04-22 18:00","매일"]
[444,"광주전남","광주","북광주계림#1 T/L","20~21년 광주전력지사 변전정비회사 총액공사","북광주-계림#1T/L GIS 보통점검","2021-04-02 10:00","2021-04-02 14:00","2021-04-02 10:00","2021-04-02 14:00","연속"]
[445,"광주전남","광주","북광주계림#2 T/L","20~21년 광주전력지사 변전정비회사 총액공사","북광주-계림#2T/L GIS 보통점검","2021-04-02 14:00","2021-04-02 18:00","2021-04-02 14:00","2021-04-02 18:00","연속"]
[446,"광주전남","광주","신광주계림#1 T/L","20~21년 광주전력지사 변전정비회사 총액공사","신광주-계림#1T/L GIS 보통점검","2021-04-30 10:00","2021-04-30 18:00","2021-04-30 10:00","2021-04-30 18:00","연속"]
[447,"광주전남","순천","광양순천#1 T/L","세니온 송전선로 보호IED성능개선","세니온 송전선로 보호IED성능개선","2021-04-07 10:00","2021-04-07 18:00","취소","취소","연속"]
[448,"광주전남","순천","광양순천#2 T/L","광양-순천T/L OPGW 교체공사","광양-순천T/L 광코어 부족구간 OPGW 교체","2021-04-27 08:00","2021-05-03 18:00","취소","취소","연속"]
[449,"광주전남","순천","순천승주#2 T/L","YPPP제 송전선로 계전기 성능개선","YPPP제 송전선로 계전기 성능개선","2021-04-12 10:00","2021-04-12 18:00","2021-04-02 10:00","2021-04-02 18:00","연속"]
[450,"광주전남","순천","순천승주#1 T/L","세니온 송전선로 보호IED성능개선","세니온 송전선로 보호IED성능개선","2021-04-09 10:00","2021-04-09 18:00","취소","취소","연속"]
[451,"광주전남","순천","율촌여수산단#1 T/L","율촌-화치 #2T/L 정밀점검 4회선 병가구간 휴전","21년 가공송전 순시점검 위탁공사 율촌-화치 #2T/L 정밀점검 및 절연저항측정","2021-04-13 08:00","2021-04-13 18:00","2021-04-15 08:00","2021-04-15 18:00","연속"]
[452,"광주전남","순천","율촌여수산단#2 T/L","율촌-화치 #1T/L 정밀점검 4회선 병가구간 휴전","21년 가공송전 순시점검 위탁공사 율촌-화치 #1T/L 정밀점검 및 절연저항측정","2021-04-08 08:00","2021-04-08 18:00","2021-04-12 08:00","2021-04-12 18:00","매일"]
[453,"광주전남","순천","여수TP화치#2 T/L","345kV 광양CC-신여수T/L 건설공사","지지물 : 철탑 24기(가철탑 4기 별도), 전력선 : ACSR/AW 480㎟×2B×2C 8.6km","2021-04-30 07:00","2021-05-04 18:00","2021-04-30 07:00","2021-05-04 18:00","연속"]
[454,"광주전남","순천","여수TP화치#1 T/L","345kV 광양CC-신여수T/L 건설공사","지지물 : 철탑 24기(가철탑 4기 별도), 전력선 : ACSR/AW 480㎟×2B×2C 8.6km","2021-04-20 07:00","2021-04-29 18:00","2021-04-20 07:00","2021-04-29 18:00","연속"]
[455,"광주전남","순천","여수TP용성#1 T/L","345kV 여수화력S/Y #4M.Tr 증설공사","345kV 여수화력S/Y #4M.Tr 2차 GIS 설치","2021-04-21 09:00","2021-04-28 18:00","2021-04-21 09:00","2021-04-28 18:00","연속"]
[456,"광주전남","순천","여수TP여천#1 T/L","345kV 여수화력S/Y #4M.Tr 증설공사","345kV 여수화력S/Y #4M.Tr 2차 GIS 설치 작업","2021-04-20 09:00","2021-04-20 18:00","2021-04-20 09:00","2021-04-20 18:00","연속"]
[457,"광주전남","순천","여천호남TP#2 T/L","345kV 광양CC-신여수T/L 건설공사","지지물 : 철탑 24기(가철탑 4기 별도), 전력선 : ACSR/AW 480㎟×2B×2C 8.6km","2021-04-12 07:00","2021-04-15 18:00","2021-04-12 07:00","2021-04-15 18:00","연속"]
[458,"광주전남","순천","여천호남TP#1 T/L","345kV 광양CC-신여수T/L 건설공사","지지물 : 철탑 24기(가철탑 4기 별도), 전력선 : ACSR/AW 480㎟×2B×2C 8.6km","2021-04-16 07:00","2021-04-19 18:00","2021-04-16 07:00","2021-04-19 18:00","연속"]
[459,"광주전남","순천","순천율촌#1 T/L","순천-율촌 #1T/L 정밀점검","21년 가공송전 순시점검 위탁공사 순천-율촌 #1T/L 정밀점검 및 절연저항측정","2021-04-13 08:00","2021-04-13 18:00","2021-04-29 08:00","2021-05-01 18:00","연속"]
[460,"광주전남","순천","순천율촌#2 T/L","순천-율촌 #2T/L 정밀점검","21년 가공송전 순시점검 위탁공사 순천-율촌 #2T/L 정밀점검 및 절연저항측정","2021-04-08 08:00","2021-04-08 18:00","2021-04-26 08:00","2021-04-28 18:00","연속"]
[461,"광주전남","순천","순천율촌#1 T/L","순천-율촌 #1T/L 정밀점검","21년 가공송전 순시점검 위탁공사 순천-율촌 #1T/L 정밀점검 및 절연저항측정","2021-04-19 08:00","2021-04-20 18:00","취소","취소","매일"]
[462,"광주전남","순천","순천율촌#2 T/L","순천-율촌 #2T/L 정밀점검","21년 가공송전 순시점검 위탁공사 순천-율촌 #2T/L 정밀점검 및 절연저항측정","2021-04-21 08:00","2021-04-22 18:00","취소","취소","매일"]
[463,"광주전남","순천","호남TP여수TP#1 T/L","호남화력S/Y 전담운영체계 구축공사","보호 PNL 설치, SA 결선 및 시험","2021-04-19 09:00","2021-04-23 18:00","2021-04-19 09:00","2021-04-23 18:00","연속"]
[464,"광주전남","순천","호남TP여수TP# 2T/L","호남화력S/Y 전담운영체계 구축공사","보호 PNL 설치, SA 결선 및 시험","2021-04-26 09:00","2021-04-30 18:00","2021-04-26 09:00","2021-04-30 18:00","연속"]
[465,"광주전남","순천","율촌화치#1 T/L","율촌-화치 #1T/L 정밀점검 및 절연저항측정","21년 가공송전 순시점검 위탁공사 율촌-화치 #1T/L 정밀점검 및 절연저항측정","2021-04-06 08:00","2021-04-08 18:00","2021-04-12 08:00","2021-04-14 18:00","매일"]
[466,"광주전남","순천","율촌화치#2 T/L","율촌-화치 #2T/L 정밀점검 및 절연저항측정","21년 가공송전 순시점검 위탁공사 율촌-화치 #2T/L 정밀점검 및 절연저항측정","2021-04-09 08:00","2021-04-13 18:00","2021-04-15 08:00","2021-04-20 18:00","매일"]
[467,"광주전남","직할","왕곡나주#2 T/L","154kV 왕곡S/S #1,4M.Tr 증설공사","154kV 왕곡S/S #1,4M.Tr 증설공사 최종 무부하가압","2021-04-13 11:00","2021-04-15 11:00","2021-04-13 11:00","2021-04-15 11:00","연속"]
[468,"대구","경산","범물남대구#2 T/L","범물S/S 154kV GIS 교체공사","2차시 TEST선로","2021-04-13 18:00","2021-04-14 09:00","2021-04-12 18:00","2021-04-13 09:00","연속"]
[469,"대구","경산","범물남대구#2 T/L","범물S/S 154kV GIS 교체공사","2차시 TEST선로","2021-04-18 18:00","2021-04-19 09:00","2021-04-17 18:00","2021-04-18 09:00","연속"]
[470,"대구","경산","대구범물#1 T/L","범물S/S 154kV GIS 교체공사","2차시(657대체)","2021-04-12 09:00","2021-04-23 18:00","2021-04-12 09:00","2021-04-23 18:00","연속"]
[471,"대구","달성","논공달성#1 T/L","논공S/S 논공-달성#1T/L 정밀점검","논공S/S 논공-달성#1T/L 정밀점검","2021-04-12 09:00","2021-04-13 18:00","2021-04-12 09:00","2021-04-13 18:00","연속"]
[472,"대구","달성","논공달성#2 T/L","논공S/S 논공-달성#2T/L 정밀점검","논공S/S 논공-달성#2T/L 정밀점검","2021-04-14 09:00","2021-04-15 18:00","2021-04-14 09:00","2021-04-15 18:00","연속"]
[473,"대구","달성","논공현풍#1 T/L","논공S/S 논공-현풍#1T/L 정밀점검","논공S/S 논공-현풍#1T/L 정밀점검","2021-04-19 09:00","2021-04-20 18:00","2021-04-19 09:00","2021-04-20 18:00","연속"]
[474,"대구","달성","논공현풍#2 T/L","논공S/S 논공-현풍#2T/L 정밀점검","논공S/S 논공-현풍#2T/L 정밀점검","2021-04-21 09:00","2021-04-22 18:00","2021-04-21 09:00","2021-04-22 18:00","연속"]
[475,"대구","달성","논공현풍#2 T/L","논공S/S #4M.Tr(6433) GIS 정밀점검 TEST선로","논공S/S #4M.Tr(6433) GIS 정밀점검 TEST선로","2021-04-29 13:00","2021-04-29 18:00","2021-04-29 13:00","2021-04-29 18:00","연속"]
[476,"대구","달성","논공현풍#1 T/L","논공S/S #1M.Tr(6133) GIS 정밀점검 TEST선로","논공S/S #1M.Tr(6133) GIS 정밀점검 TEST선로","2021-04-04 13:00","2021-04-04 18:00","2021-04-04 13:00","2021-04-04 18:00","연속"]
[477,"대구","달성","논공현풍#2 T/L","논공S/S #2M.Tr(6233) GIS 정밀점검 TEST선로","논공S/S #2M.Tr(6233) GIS 정밀점검 TEST선로","2021-04-11 13:00","2021-04-11 18:00","2021-04-11 13:00","2021-04-11 18:00","연속"]
[478,"대구","달성","논공현풍#1 T/L","논공S/S #3M.Tr(6333) GIS 정밀점검 TEST선로","논공S/S #3M.Tr(6333) GIS 정밀점검 TEST선로","2021-04-27 13:00","2021-04-27 18:00","2021-04-27 13:00","2021-04-27 18:00","연속"]
[479,"대구","달성","대구청도#1 T/L","154kV 대구-청도 등 4개T/L 피뢰기 설치공사","154kV 송전선로용 피뢰기 495 SET 설치(165기)\n(154kV 대구-청도#1T/L, 154kV 고령-쌍림#1T/L, 154kV 북대구-팔달#2T/L, 154kV 대구-봉덕#1T/L)","2021-04-19 07:00","2021-04-19 18:00","2021-04-19 07:00","2021-04-19 18:00","연속"]
[480,"대구","직할","남대구동인#2 T/L","21-22년 대구본부 직할 지중송전 위탁정비공사","절연유 열화진단 시행","2021-04-22 10:00","2021-04-22 18:00","2021-04-22 10:00","2021-04-22 18:00","연속"]
[481,"대구","직할","내당두류#1 T/L","내당S/S 내당-두류#1 GIS 보통점검","내당S/S 내당-두류#1 GIS 보통점검","2021-04-28 09:30","2021-04-28 18:00","2021-04-28 09:30","2021-04-28 18:00","연속"]
[482,"대구","직할","내당두류#2 T/L","내당S/S 내당-두류#2 GIS 보통점검","내당S/S 내당-두류#2 GIS 보통점검","2021-04-29 09:30","2021-04-29 18:00","2021-04-29 09:30","2021-04-29 18:00","연속"]
[483,"대구","칠곡","김천금릉#1 T/L","154kV 김천-금릉T/L 지장이설공사","김천-금릉T/L No.12 ㅇ공사내용:지장철탑 이설","2021-04-14 08:00","2021-05-13 18:00","2021-04-14 08:00","2021-05-13 18:00","연속"]
[484,"경북","구미","남인동인동#2 T/L","2021년도 가공송전 순시점검 위탁공사","154kV 남인동-인동#2 T/L 정밀점검(남인동ST~인동ST)","2021-04-12 08:30","2021-04-16 18:00","2021-04-12 08:30","2021-04-16 18:00","매일"]
[485,"경북","구미","남인동인동#1 T/L","2021년도 가공송전 순시점검 위탁공사","154kV 남인동-인동#1 T/L 정밀점검(남인동ST~인동ST)","2021-04-05 08:30","2021-04-09 18:00","2021-04-05 08:30","2021-04-09 18:00","매일"]
[486,"경북","구미","동상주점촌#1 T/L","154kV 동상주-점촌T/L 지장이설공사","154kV 동상주-점촌T/L No.8 C/H 조립, 전선교체 및 이동, No.13 철탑보강","2021-04-01 08:00","2021-04-07 18:00","2021-04-05 08:00","2021-04-09 18:00","연속"]
[487,"경북","구미","동상주점촌#2 T/L","154kV 동상주-점촌T/L 지장이설공사","154kV 동상주-점촌T/L No.8 C/H 조립, 전선교체 및 이동, No.13 철탑보강","2021-04-01 08:00","2021-04-07 18:00","2021-04-05 08:00","2021-04-09 18:00","연속"]
[488,"경북","구미","상주보은 T/L","2020-21년 구미전력지사 변전정비업체 총액공사","154kV 모선보호반 교체공사","2021-04-08 11:00","2021-04-08 11:30","2021-04-23 11:00","2021-04-23 11:30","연속"]
[489,"경북","구미","상주영동 T/L","2020-21년 구미전력지사 변전정비업체 총액공사","154kV 모선보호반 교체공사","2021-04-08 13:00","2021-04-08 13:30","2021-04-23 13:00","2021-04-23 13:30","연속"]
[490,"경북","구미","선산청리#1 T/L","2020-21년 구미전력지사 변전정비업체 총액공사","선산S/S GIS 하자점검 - 청리S/S LA 보통점검","2021-04-09 09:00","2021-04-09 14:00","2021-04-09 09:00","2021-04-09 14:00","연속"]
[491,"경북","구미","선산청리#2 T/L","2020-21년 구미전력지사 변전정비업체 총액공사","선산S/S GIS 하자점검","2021-04-09 14:00","2021-04-09 18:00","2021-04-09 14:00","2021-04-09 18:00","연속"]
[492,"경북","영주","점촌단양 T/L","영주전력지사 '96년 상반기 이전 국산애자 교체공사","154kV 점촌-단양T/L 성능저하 애자교체","2021-04-23 07:00","2021-04-24 18:00","2021-04-18 07:00","2021-04-19 18:00","매일"]
[493,"경북","영주","예천점촌#2 T/L","영주전력지사 '96년 상반기 이전 국산애자 교체공사","154kV 예천-점촌T/L 성능저하 애자교체","2021-04-25 07:00","2021-04-26 18:00","2021-04-24 07:00","2021-04-25 18:00","매일"]
[494,"경북","영주","예천점촌#1 T/L","영주전력지사 '96년 상반기 이전 국산애자 교체공사","154kV 예천-점촌T/L 성능저하 애자교체","2021-04-22 07:00","2021-04-23 18:00","2021-04-17 07:00","2021-04-18 18:00","매일"]
[495,"경북","영주","점촌문경 T/L","영주전력지사 '96년 상반기 이전 국산애자 교체공사","154kV 점촌-문경T/L 성능저하 애자교체","2021-04-25 07:00","2021-04-25 18:00","2021-04-24 07:00","2021-04-24 18:00","연속"]
[496,"경북","직할","풍산안동CC#1 T/L","20~21년 경북본부 직할 변전정비회사 총액공사","GIS 보통점검","2021-04-16 09:00","2021-04-16 18:00","2021-04-16 09:00","2021-04-16 18:00","연속"]
[497,"경북","직할","풍산안동CC#2 T/L","20~21년 경북본부 직할 변전정비회사 총액공사","GIS 보통점검","2021-04-23 09:00","2021-04-23 18:00","2021-04-23 09:00","2021-04-23 18:00","연속"]
[498,"경북","직할","영덕진보#1 T/L","154kV 영덕-진보#1T/L 정밀점검","154kV 영덕-진보#1T/L 정밀점검 No.1~97","2021-04-19 09:00","2021-04-28 18:00","2021-04-19 09:00","2021-04-28 18:00","매일"]
[499,"부산울산","동부산","신양산구서#1 T/L","동부산전력지사 관내 OPGW 항공장애표시구 설치공사","154kV 신양산-수영#1/L 항공구 설치공사 안전이격확보용 휴전","2021-04-19 09:00","2021-04-19 18:00","2021-04-19 09:00","2021-04-19 18:00","연속"]
[500,"부산울산","동부산","신양산구서#2 T/L","동부산전력지사 관내 OPGW 항공장애표시구 설치공사","154kV 신양산-수영#2T/L 항공구 설치공사 안전이격확보용 휴전","2021-04-27 09:00","2021-04-27 18:00","2021-04-27 09:00","2021-04-27 18:00","연속"]
[501,"부산울산","동부산","노포정관#1 T/L","노포S/S 154kV GIS 차단기 동작시험","노포S/S 154kV GIS 차단기 동작시험(노포-정관#1T/L)","2021-04-08 09:30","2021-04-08 17:00","2021-04-08 09:30","2021-04-08 17:00","연속"]
[502,"부산울산","동부산","노포정관#2 T/L","노포S/S 154kV GIS 차단기 동작시험","노포S/S 154kV GIS 차단기 동작시험(노포-정관#2T/L)","2021-04-09 09:30","2021-04-09 17:00","2021-04-09 09:30","2021-04-09 17:00","연속"]
[503,"부산울산","동부산","미남S/S SEC CB 60610","미남S/S 154kV 모선보호반 성능개선","미남S/S 154kV 모선보호반 성능개선(60-61-0)","2021-04-19 09:30","2021-04-19 17:00","취소","취소","연속"]
[504,"부산울산","동부산","미남S/S CB 6100","미남S/S 154kV 모선보호반 성능개선","미남S/S 154kV 모선보호반 성능개선(6100)","2021-04-19 09:30","2021-04-19 17:00","취소","취소","연속"]
[505,"부산울산","동부산","미남S/S SEC CB 65660","미남S/S 154kV 모선보호반 성능개선","미남S/S 154kV 모선보호반 성능개선(65-66-0)","2021-04-19 09:30","2021-04-19 17:00","취소","취소","연속"]
[506,"부산울산","동부산","신양산수영#2 T/L","수영S/S 154kV GIS 정밀점검공사","수영S/S 154kV GIS 정밀점검공사(신양산-수영#2T/L)","2021-04-27 09:00","2021-04-29 18:00","2021-04-27 09:00","2021-04-29 18:00","연속"]
[507,"부산울산","동부산","신양산수영#1 T/L","수영S/S 154kV GIS 정밀점검공사","수영S/S 154kV GIS 정밀점검공사(신양산-수영#1T/L)","2021-04-19 09:00","2021-04-21 18:00","2021-04-19 09:00","2021-04-21 18:00","연속"]
[508,"부산울산","동부산","정관S/S CB 6100","정관S/S 154kV 모선보호반 성능개선","정관S/S 154kV 모선보호반 성능개선","2021-04-20 09:30","2021-04-20 17:00","2021-04-19 09:30","2021-04-19 17:00","연속"]
[509,"부산울산","북부산","북부산구포#2 T/L","20-21 북부산전력지사 변전 총액공사","구포S/S 154kV 북부산-구포#2T/L 차단기 동작시험","2021-04-14 13:00","2021-04-14 18:00","2021-04-14 13:00","2021-04-14 18:00","연속"]
[510,"부산울산","북부산","북부산구포#1 T/L","20-21 북부산전력지사 변전 총액공사","구포S/S 북부산-구포#1T/L 차단기 동작시험","2021-04-14 10:00","2021-04-14 13:00","2021-04-14 10:00","2021-04-14 13:00","연속"]
[511,"부산울산","북부산","호포물금 T/L","2021 북부산전력지사 154kV GIS 정밀점검","물금S/S 154kV #2M.Tr 1차(6333) GIS 정밀점검 (시험가압선로 : 호포-물금T/L, #65BUS)","2021-04-27 17:00","2021-04-27 18:00","취소","취소","연속"]
[512,"부산울산","북부산","물금삼랑진PP#2 T/L","20-21 북부산전력지사 변전 총액공사","물금S/S 154kV 물금-삼랑진#1,2T/L 차단기 동작시험","2021-04-23 10:00","2021-04-23 14:00","2021-04-23 10:00","2021-04-23 14:00","연속"]
[513,"부산울산","북부산","북부산삼랑진PP T/L","북부산전력지사 가공송전선로 추락방지장치 설치","북부산전력지사 가공송전선로 추락방지장치 설치공사(북부산-삼랑진T/L 2~3호)","2021-04-19 07:30","2021-04-20 18:00","2021-04-19 07:30","2021-04-20 18:00","연속"]
[514,"부산울산","북부산","북부산호포 T/L","20-21 북부산전력지사 변전 총액공사","북부산S/S 154kV 북부산-호포T/L 보호반 대체","2021-04-26 09:00","2021-04-28 18:00","2021-04-26 09:00","2021-04-29 18:00","연속"]
[515,"부산울산","북부산","북부산양산 T/L","북부산전력지사 가공송전선로 추락방지장치 설치","북부산전력지사 가공송전선로 추락방지장치 설치공사(북부산-삼랑진T/L 2~3호, 양산분기 1호 등 4기, 총 6기)","2021-04-21 07:30","2021-04-24 18:00","2021-04-21 07:30","2021-04-24 18:00","연속"]
[516,"부산울산","북부산","양산산막#1 T/L","2021 북부산전력지사 154kV GIS 정밀점검","산막S/S 154kV #1M.Tr 1차(6133) GIS 정밀점검 (시험가압선로 : 양산-산막#1T/L, #60BUS)","2021-04-09 17:00","2021-04-09 18:00","2021-04-09 17:00","2021-04-09 18:00","연속"]
[517,"부산울산","북부산","서창산막#2 T/L","20-21 북부산전력지사 변전총액공사","산막S/S 154kV 서창-산막#2T/L GIS 차단기 전자변교체","2021-04-02 10:00","2021-04-02 18:00","2021-04-02 10:00","2021-04-02 18:00","연속"]
[518,"부산울산","북부산","양산산막#1 T/L","2021 북부산전력지사 154kV GIS 정밀점검","산막S/S 154kV 양산-산막#1T/L(617) GIS 정밀점검","2021-04-05 09:00","2021-04-06 18:00","취소","취소","연속"]
[519,"부산울산","북부산","언양산막#2 T/L","북부산전력지사 가공송전선로 추락방지장치 설치","북부산전력지사 가공송전선로 추락방지장치 설치공사(언양산막T/L 1호등 16기)","2021-04-12 07:30","2021-04-18 18:00","2021-04-12 07:30","2021-04-18 18:00","연속"]
[520,"부산울산","북부산","언양산막#1 T/L","북부산전력지사 가공송전선로 추락방지장치 설치","북부산전력지사 가공송전선로 추락방지장치 설치공사(언양산막T/L 1호등 16기)","2021-04-04 07:30","2021-04-11 18:00","2021-04-04 07:30","2021-04-11 18:00","연속"]
[521,"부산울산","북부산","서창산막#1 T/L","2021 북부산전력지사 154kV GIS 정밀점검","산막S/S 154kV 서창-산막#1T/L(637) GIS 정밀점검","2021-04-07 09:00","2021-04-08 18:00","취소","취소","연속"]
[522,"부산울산","북부산","서창산막#2 T/L","북부산전력지사 가공송전선로 추락방지장치 설치 병가구간 안전확보","추락방지장치 설치공사 병가구간 작업자 안전확보(언양-산막T/L 67~72호 구간)","2021-04-17 07:30","2021-04-18 18:00","2021-04-17 07:30","2021-04-18 18:00","연속"]
[523,"부산울산","북부산","서창산막#1 T/L","북부산전력지사 가공송전선로 추락방지장치 설치 병가구간 안전확보","추락방지장치 설치공사 병가구간 작업자 안전확보(언양-산막T/L 67~72호 구간)","2021-04-17 07:30","2021-04-18 18:00","2021-04-17 07:30","2021-04-18 18:00","연속"]
[524,"부산울산","북부산","양산산막#2 T/L","북부산전력지사 가공송전선로 추락방지장치 설치 병가구간 안전확보","추락방지장치 설치공사 병가구간 작업자 안전확보(언양-산막T/L 67~72호 구간)","2021-04-10 07:30","2021-04-11 18:00","취소","취소","연속"]
[525,"부산울산","북부산","양산산막#1 T/L","북부산전력지사 가공송전선로 추락방지장치 설치 병가구간 안전확보","추락방지장치 설치공사 병가구간 작업자 안전확보(언양-산막T/L 67~72호 구간)","2021-04-10 07:30","2021-04-11 18:00","2021-04-10 07:30","2021-04-11 18:00","연속"]
[526,"부산울산","북부산","물금삼랑진PP#1 T/L","2021년 가공송전 순시점검 위탁공사(북부산전력지사)","154kV 물금-삼랑진#1T/L 전선교체공사 인수점검","2021-04-05 08:00","2021-04-16 18:00","2021-04-05 08:00","2021-04-16 18:00","매일"]
[527,"부산울산","북부산","양산삼랑진PP T/L","북부산전력지사 가공송전선로 추락방지장치 설치","추락방지장치 설치공사(양산분기 1호 등 4기)","2021-04-25 07:30","2021-04-26 18:00","2021-04-25 07:30","2021-04-26 18:00","연속"]
[528,"부산울산","북부산","양산산막#2 T/L","20-21 북부산전력지사 변전 총액공사","양산S/S 154kV 양산-산막#2T/L 차단기 동작시험","2021-04-16 10:00","2021-04-16 18:00","2021-04-16 10:00","2021-04-16 18:00","연속"]
[529,"부산울산","서부산","신녹산녹산#2 T/L","154kV 신녹산-녹산#2T/L 성능개선","154kV 신녹산-녹산#2T/L 성능개선","2021-04-02 10:00","2021-04-02 18:00","2021-04-02 10:00","2021-04-02 18:00","연속"]
[530,"부산울산","서부산","신녹산녹산#1 T/L","154kV 신녹산-녹산#1T/L 성능개선","154kV 신녹산-녹산#1T/L 성능개선","2021-04-01 10:00","2021-04-01 18:00","2021-04-01 10:00","2021-04-01 18:00","연속"]
[531,"부산울산","서부산","신김해지사#1 T/L","지사S/S 154kV 신김해-지사#1T/L 차단기동작시험","지사S/S 154kV 신김해-지사#1T/L 차단기동작시험","2021-04-06 10:00","2021-04-06 18:00","2021-04-06 10:00","2021-04-06 18:00","연속"]
[532,"부산울산","서부산","신김해지사#2 T/L","지사S/S 154kV 신김해-지사#2T/L 차단기동작시험","지사S/S 154kV 신김해-지사#2T/L 차단기동작시험","2021-04-08 10:00","2021-04-08 18:00","2021-04-08 10:00","2021-04-08 18:00","연속"]
[533,"부산울산","울산","남울산신온산#2 T/L","2021년도 가공송전 순시점검 위탁공사(울산)","신온산-울산TPT/L정밀점검을 위한 안전이격","2021-04-22 08:00","2021-04-22 18:00","2021-04-22 08:00","2021-04-22 18:00","연속"]
[534,"부산울산","울산","남울산처용#1 T/L","345kV 신울산복합-북부산T/L 건설사업","345kV 신울산복합-북부산T/L 아킹혼 설치(안전이격)","2021-04-02 07:00","2021-04-02 18:00","2021-04-05 07:00","2021-04-05 18:00","연속"]
[535,"부산울산","울산","남울산처용#2 T/L","345kV 신울산복합-북부산T/L 건설사업","345kV 신울산복합-북부산T/L 아킹혼 설치(안전이격)","2021-04-03 07:00","2021-04-03 18:00","2021-04-09 07:00","2021-04-09 18:00","연속"]
[536,"부산울산","울산","남울산신온산#1 T/L","2021년도 가공송전 순시점검 위탁공사(울산)","신온산-울산TPT/L정밀점검을 위한 안전이격","2021-04-22 08:00","2021-04-22 18:00","취소","취소","연속"]
[537,"부산울산","울산","두왕영남TP#2 T/L","울산S/S 154kV SW 증설공사","○ 울산-울산T/P #2T/L 전력케이블 선종교체(설비보강부)\n○ 두왕-울산#2T/L, 울산-영남T/P #2T/L 최초가압 및 실부하가압(설비보강부)","2021-04-12 07:00","2021-05-21 18:00","2021-04-12 07:00","2021-05-21 18:00","연속"]
[538,"부산울산","울산","신울산두왕#2 T/L","울산S/S 154kV SW 증설공사","○ 두왕-울산#1T/L 지중송전선로 최초가압 24Hr(남부건설본부 송전건설부)\n○ 두왕-울산#2T/L 실부하가압 및 Angle 측정(설비보강부)","2021-04-07 09:00","2021-04-08 18:00","2021-04-07 09:00","2021-04-08 18:00","연속"]
[539,"부산울산","울산","신울산울산#2 T/L","신울산S/S 154kV 현대화공사","TR-BUS DS(6N8) 철거","2021-04-12 09:30","2021-04-12 17:00","2021-04-12 09:30","2021-04-12 17:00","연속"]
[540,"부산울산","울산","신울산두왕#1 T/L","신울산S/S 154kV 현대화공사","TR-BUS DS(6K8) 철거","2021-04-11 09:30","2021-04-11 17:00","2021-04-11 09:30","2021-04-11 17:00","연속"]
[541,"부산울산","울산","신울산웅촌#2 T/L","지중송전 대한製 열경화공법 EBG 교체공사","EBG 취약개소 교체공사","2021-04-12 09:00","2021-04-21 18:00","2021-04-12 09:00","2021-04-21 18:00","연속"]
[542,"부산울산","울산","신울산언양#1 T/L","지중송전 대한製 열경화공법 EBG 교체공사","EBG 취약개소 교체공사","2021-04-22 09:00","2021-04-30 18:00","2021-04-22 09:00","2021-04-30 18:00","연속"]
[543,"부산울산","울산","신울산울산#1 T/L","20-21년 울산전력지사 변전총액공사","차단기 동작시험, 전자변 교체 - 43PDA 교체","2021-04-13 09:00","2021-04-13 18:00","2021-04-13 09:00","2021-04-13 18:00","연속"]
[544,"부산울산","울산","온산처용#2 T/L","2021년 가공송전 순시점검 위탁공사(울산)","신온산-울산TP T/L 정밀점검에 따른 안전이격 확보","2021-04-19 08:00","2021-04-21 18:00","2021-04-19 08:00","2021-04-21 18:00","연속"]
[545,"부산울산","울산","남울산용연#2 T/L","21년 상반기 울산전력지사 GIS 정밀점검","시험가압","2021-04-08 17:00","2021-04-08 18:00","2021-04-08 17:00","2021-04-08 18:00","연속"]
[546,"부산울산","울산","용연울산TP#3 T/L","2021년 가공송전 협력회사 총액공사","지지애자 교체 및 보조암 설치에 따른 안전이격 확보 - 345kV 북부산-울산TPT/L 4호","2021-04-01 08:00","2021-04-04 18:00","2021-04-01 08:00","2021-04-04 18:00","연속"]
[547,"부산울산","울산","남울산용연#1 T/L","21년 상반기 울산전력지사 GIS 정밀점검","시험가압","2021-04-06 17:00","2021-04-06 18:00","2021-04-06 17:00","2021-04-06 18:00","연속"]
[548,"부산울산","울산","울산울산TP#2 T/L","울산S/S 154kV SW 증설공사","○ 울산-울산T/P #2T/L 전력케이블 선종교체(설비보강부) \n○ 두왕-울산#2T/L, 울산-영남T/P #2T/L 최초가압 및 실부하가압","2021-04-12 07:00","2021-05-21 18:00","2021-04-12 07:00","2021-05-21 18:00","연속"]
[549,"부산울산","울산","울산울산TP#2 T/L","울산전력지사 상반기 GIS 정밀점검","SK에너지 NAC 시험가압1H","2021-04-02 17:00","2021-04-02 18:00","2021-04-02 17:00","2021-04-02 18:00","연속"]
[550,"부산울산","울산","온산처용#2 T/L","21년 상반기 울산전력지사 GIS 정밀점검","시험가압","2021-04-13 17:00","2021-04-13 18:00","2021-04-13 17:00","2021-04-13 18:00","연속"]
[551,"부산울산","직할","수정범일#1 T/L","20-21년 직할 변전정비회사 총액공사","범일S/S 수정-범일#1T/L GIS 차단기 조작시험","2021-04-06 09:30","2021-04-06 14:00","2021-04-06 09:30","2021-04-06 14:00","연속"]
[552,"부산울산","직할","범일서면#2 T/L","20-21년 직할 변전정비회사 총액공사","범일S/S 범일-서면#2T/L GIS 차단기 조작시험","2021-04-12 09:00","2021-04-12 18:00","2021-04-12 09:00","2021-04-12 18:00","연속"]
[553,"부산울산","직할","범일서면#1 T/L","20-21년 직할 변전정비회사 총액공사","범일S/S 범일-서면#1T/L GIS 차단기 조작시험","2021-04-12 09:30","2021-04-12 09:00","2021-04-12 09:00","2021-04-12 18:00","연속"]
[554,"부산울산","직할","수정범일#2 T/L","20-21년 직할 변전정비회사 총액공사","범일S/S 수정-범일#2T/L GIS 차단기 조작시험","2021-04-06 14:00","2021-04-06 18:00","2021-04-06 14:00","2021-04-06 18:00","연속"]
[555,"경남","직할","마천진해#2 T/L","154kV 마천-진해#2T/L 송전선로 정밀점검","154kV 마천-진해#2T/L 송전선로 정밀점검(3~33)","2021-04-26 08:00","2021-04-29 18:00","취소","취소","매일"]
[556,"경남","직할","마천진해#1 T/L","154kV 마천-진해#1T/L 송전선로 정밀점검","154kV 마천-진해#1T/L 송전선로 정밀점검(3~33)","2021-04-05 08:00","2021-04-08 18:00","취소","취소","매일"]
[557,"경남","직할","장유마천#1 T/L","154kV 장유마천#1 T/L 송전선로 정밀점검","장유마천#1 T/L 송전선로 정밀점검(1~61) ※주말작업제외","2021-04-07 08:00","2021-04-16 18:00","2021-04-07 08:00","2021-04-16 18:00","매일"]
[558,"경남","직할","장유마천#2 T/L","154kV 장유마천#2 T/L 송전선로 정밀점검","장유마천#2 T/L 송전선로 정밀점검(1~61) ※주말작업제외","2021-04-19 08:00","2021-04-27 18:00","2021-04-19 08:00","2021-04-27 18:00","매일"]
[559,"경남","직할","신김해지사#1 T/L","154kV 신김해-지사#1T/L 송전선로 정밀점검","154kV 신김해-지사#1T/L 송전선로 정밀점검(1~29)","2021-04-12 08:00","2021-04-15 18:00","2021-04-12 08:00","2021-04-15 18:00","매일"]
[560,"경남","직할","신김해진영#1 T/L","154kV 진례S/S 건설공사","154kV 진례S/S 건설공사","2021-04-05 10:00","2021-04-23 13:00","2021-04-05 10:00","2021-04-23 13:00","연속"]
[561,"경남","직할","신김해지사#2 T/L","154kV 신김해-지사#2T/L 송전선로 정밀점검","154kV 신김해-지사#2T/L 송전선로 정밀점검(1~29)","2021-04-19 08:00","2021-04-23 18:00","2021-04-19 08:00","2021-04-23 18:00","매일"]
[562,"경남","직할","신월동읍#2 T/L","154kV신월-동읍#2 T/L 애자련 보강, SB댐퍼 설치","154kV 신월-동읍#2T/L 33-34호 애자련 보강, SB댐퍼설치(1,20,32,33호)","2021-04-28 07:00","2021-04-30 18:00","2021-04-28 07:00","2021-04-30 18:00","매일"]
[563,"경남","직할","신월동읍#1 T/L","154kV신월-동읍#1 T/L 애자련 보강","154kV 신월-동읍#1T/L 33-34호 애자련 보강공사","2021-04-26 07:00","2021-04-27 18:00","2021-04-26 07:00","2021-04-27 18:00","매일"]
[564,"경남","직할","신월삼정#2 T/L","154kV신월-동읍#2 T/L SB댐퍼설치(안전작업거리 확보 휴전)","154kV신월-동읍#2 T/L SB댐퍼설치(1,20,32,33)) 안전작업거리 확보휴전","2021-04-28 07:00","2021-04-30 18:00","2021-04-28 07:00","2021-04-30 18:00","연속"]
[565,"경남","직할","안민천선#2 T/L","안민S/S 안민-천선#2T/L 조작시험","안민S/S 안민-천선#2T/L 조작시험","2021-04-09 13:30","2021-04-09 17:30","2021-04-09 13:30","2021-04-09 17:30","연속"]
[566,"경남","직할","안민천선#1 T/L","안민S/S 안민-천선#1T/L 조작시험","안민S/S 안민-천선#1T/L 조작시험","2021-04-09 09:30","2021-04-09 13:30","2021-04-09 09:30","2021-04-09 13:30","연속"]
[567,"경남","직할","신김해장유#1 T/L","154kV 신김해-지사#1T/L 송전선로 정밀점검","154kV 신김해-지사#1T/L 송전선로 정밀점검(2~9) 안전작업거리 확보 휴전","2021-04-14 08:00","2021-04-15 18:00","취소","취소","매일"]
[568,"경남","직할","신김해장유#2 T/L","154kV 장유-마천#1, 신김해-지사#2T/L 송전선로 정밀점검","154kV 장유-마천#1T/L 송전선로 정밀점검(1~4) 154kV 신김해-지사#2T/L 송전선로 정밀점검(2~9) 안전작업거리 확보 휴전","2021-04-16 08:00","2021-04-20 18:00","취소","취소","매일"]
[569,"경남","직할","신김해장유#1 T/L","154kV 장유-마천#2T/L 송전선로 정밀점검","154kV 장유-마천#2T/L 송전선로 정밀점검(1~4) 안전작업거리 확보 휴전","2021-04-26 08:00","2021-04-28 18:00","취소","취소","매일"]
[570,"경남","직할","천선진해#1 T/L","진해S/S 천선-진해#1T/L 조작시험","진해S/S 천선-진해#1T/L 조작시험","2021-04-15 09:30","2021-04-15 13:30","취소","취소","연속"]
[571,"경남","직할","천선진해#2 T/L","진해S/S 천선-진해#2T/L 조작시험","진해S/S 천선-진해#2T/L 조작시험","2021-04-15 13:30","2021-04-15 17:30","취소","취소","연속"]
[572,"경남","직할","의창차룡#1 T/L","차룡S/S 의창-차룡#1T/L 보통점검","차룡S/S 의창-차룡#1T/L 보통점검","2021-04-30 09:30","2021-04-30 17:30","취소","취소","연속"]
[573,"경남","직할","창공월림#2 T/L","154kV창공-월림#2 T/L 피뢰기 설치공사","154kV창공-월림#2 T/L 피뢰기 설치공사(8~14)","2021-04-18 07:00","2021-04-18 18:00","취소","취소","연속"]
[574,"경남","직할","창원창공#1 T/L","154kV창원-창공#1 T/L 피뢰기 설치공사","154kV창원-창공#1 T/L 피뢰기 설치공사(1~7)","2021-04-18 07:00","2021-04-18 18:00","취소","취소","연속"]
[575,"경남","진주","의령동진주#2 T/L","154kV 의령-동진주#2T/L 송전용 피뢰기 설치공사(68기)","154kV 의령-동진주#2T/L 송전용 피뢰기 설치공사(68기)","2021-04-24 07:00","2021-04-25 18:00","2021-04-17 07:00","2021-04-18 18:00","연속"]
[576,"경남","진주","사봉개양#1 T/L","사봉S/S 154kV 사봉-개양#1T/L GIS 하자점검","사봉S/S 154kV 사봉-개양#1T/L GIS 하자점검","2021-04-27 10:00","2021-04-27 18:00","2021-04-27 10:00","2021-04-27 18:00","연속"]
[577,"경남","진주","동진주진주#1 T/L","진주S/S 옥외철구 현대화 공사 부지확보","진주S/S 옥외철구 현대화 공사 부지확보 [병행] 동진주-진주#1T/L CB조작시험, PT,LA 보통점검","2021-04-14 09:00","2021-04-18 18:00","2021-04-24 09:00","2021-04-25 18:00","연속"]
[578,"경남","진주","동진주진주#2 T/L","진주S/S 옥외철구 현대화 공사 부지확보","진주S/S 옥외철구 현대화 공사 부지확보 [병행] 동진주-진주#2T/L CB조작시험, PT대체 ,LA 보통점검","2021-04-17 09:00","2021-04-21 18:00","2021-04-24 09:00","2021-04-25 18:00","연속"]
[579,"경남","진주","하동하동화력#1 T/L","154V 하동-하동화력 T/L 추락방지시설 설치 공사","추락방지시설 설치(광양-하동화력T/L 병가구간)","2021-04-14 07:00","2021-04-20 19:00","2021-04-14 07:00","2021-04-20 19:00","연속"]
[580,"경남","진주","하동하동화력#2 T/L","154V 하동-하동화력 T/L 추락방지시설 설치 공사","추락방지시설 설치(광양-하동화력T/L 병가구간)","2021-04-21 07:00","2021-04-27 19:00","2021-04-21 07:00","2021-04-27 19:00","연속"]
[581,"경남","진주","쌍림합천#2 T/L","합천S/S 154kV 쌍림-합천#2T/L 조작시험","합천S/S 154kV 쌍림-합천#2T/L 조작시험","2021-04-02 14:00","2021-04-02 18:00","2021-04-02 14:00","2021-04-02 18:00","연속"]
[582,"경남","진주","쌍림합천#1 T/L","합천S/S 154kV 쌍림-합천#1T/L 조작시험","합천S/S 154kV 쌍림-합천#1T/L 조작시험","2021-04-02 10:00","2021-04-02 14:00","2021-04-02 10:00","2021-04-02 14:00","연속"]
[583,"경남","통영","고성통영 T/L","154kV 신고성-통영(고성-통영)T/L 추락방지장치 설치공사","154kV 신고성-통영(고성-통영)T/L 추락방지장치 설치공사(146,149)","2021-04-18 07:30","2021-04-18 18:00","2021-04-18 07:30","2021-04-18 18:00","연속"]
[584,"경남","통영","고성통영 T/L","154kV 신고성-통영T/L 피뢰기 설치공사(안전이격거리확보)","154kV 신고성-통영T/L 피뢰기 설치공사(안전이격거리확보)","2021-04-03 07:30","2021-04-03 18:00","2021-04-03 07:30","2021-04-03 18:00","연속"]
[585,"경남","통영","고성안정#2 T/L","154kV 신고성-통영T/L 피뢰기 설치공사(안전이격거리확보)","154kV 신고성-통영T/L 피뢰기 설치공사(안전이격거리확보)","2021-04-03 07:30","2021-04-03 18:00","2021-04-03 07:30","2021-04-03 18:00","연속"]
[586,"경남","통영","신고성삼천포#1 T/L","신고성-삼천포#1T/L 보호반 SA화 등 3건","신고성-삼천포#1T/L 보호반 SA화","2021-04-05 10:00","2021-04-07 18:00","2021-04-05 10:00","2021-04-07 18:00","연속"]
[587,"경남","통영","신고성통영 T/L","154kV 신고성-통영T/L 피뢰기 설치공사","154kV 신고성-통영T/L 피뢰기 설치공사(116~149)","2021-04-10 07:30","2021-04-11 18:00","2021-04-10 07:30","2021-04-11 18:00","매일"]
[588,"경남","통영","신고성통영 T/L","154kV 신고성-통영T/L 피뢰기 설치공사","154kV 신고성-통영T/L 피뢰기 설치공사(79~115)","2021-04-03 07:30","2021-04-04 18:00","2021-04-03 07:30","2021-04-04 18:00","매일"]
[589,"경남","통영","신고성거제#2 T/L","154kV 신고성-거제#2T/L SB댐퍼 교체공사","154kV 신고성-거제#2T/L SB댐퍼 교체공사(145)","2021-04-17 07:30","2021-04-17 18:00","2021-04-17 07:30","2021-04-17 18:00","연속"]
[590,"경남","통영","신고성통영 T/L","154kV 신고성-통영T/L 추락방지장치 설치공사","154kV 신고성-통영T/L 추락방지장치 설치공사(146,149)","2021-04-17 07:30","2021-04-17 18:00","2021-04-17 07:30","2021-04-17 18:00","연속"]
[591,"경남","통영","통영거제#2 T/L","154kV 신고성-통영T/L 추락방지장치 설치공사 안전이격거리확보","154kV 신고성-통영(고성-통영)T/L 추락방지장치 설치공사 안전이격거리확보","2021-04-18 07:30","2021-04-18 18:00","2021-04-18 07:30","2021-04-18 18:00","연속"]
[592,"경남","통영","통영거제#1 T/L","154kV 신고성-통영T/L 추락방지장치 설치공사(안전이격거리확보)","154kV 신고성-통영T/L 추락방지장치 설치공사 관련 안전이격거리확보","2021-04-17 07:30","2021-04-17 18:00","2021-04-17 07:30","2021-04-17 18:00","연속"]
[593,"경남","통영","통영거제#1 T/L","154kV 통영-거제#1T/L 피뢰기 설치공사","154kV 통영-거제#1T/L 피뢰기 설치공사(9호)","2021-04-11 07:30","2021-04-11 18:00","2021-04-11 07:30","2021-04-11 18:00","연속"]
[594,"경남","통영","통영거제#2 T/L","통영S/S 통영-거제#2T/L GIS 선로ES 모터 교체(제작사)","통영S/S 통영-거제#2T/L GIS 선로ES 모터 교체","2021-04-19 10:00","2021-04-19 18:00","2021-04-19 10:00","2021-04-19 18:00","연속"]
[595,"경남","함안","신마산동읍#1 T/L","154kV신월-동읍#1,2T/L 애자련 보강(안전작업거리 확보 휴전)","154kV 신월-동읍#1,2T/L 33-34호 애자련 보강공사 안전작업거리 확보","2021-04-26 07:00","2021-05-01 18:00","2021-04-26 07:00","2021-05-01 18:00","매일"]
[596,"경남","함안","신마산의창#2 T/L","2021 함안전력 정비회사 총액공사 피뢰기 설치","154kV 신마산-의창#2T/L 피뢰기 설치","2021-04-26 07:00","2021-05-01 18:00","취소","취소","매일"]
[597,"경남","함안","신마산마산#2 T/L","2021 함안전력 정비회사 총액공사 피뢰기 설치관련 안전거리 확보","154kV 신마산-마산#1T/L 피뢰기 설치관련 안전거리 확보","2021-04-10 07:00","2021-04-10 18:00","2021-04-10 07:00","2021-04-10 18:00","연속"]
[598,"경남","함안","신마산서마산 T/L","2021 함안전력 정비회사 총액공사 피뢰기 설치관련 안전거리 확보","154kV 신마산-마산#1T/L 피뢰기 설치관련 안전거리 확보","2021-04-10 07:00","2021-04-10 18:00","2021-04-10 07:00","2021-04-10 18:00","연속"]
[599,"경남","함안","신마산동읍#2 T/L","신마산S/S 154kV 신마산-동읍#2T/L CB 조작시험","신마산S/S 154kV 신마산-동읍#2T/L CB 조작시험","2021-04-15 09:30","2021-04-15 13:30","2021-04-15 09:30","2021-04-15 13:30","연속"]
[600,"경남","함안","신마산마산#1 T/L","2021 함안전력 정비회사 총액공사 피뢰기 설치","154kV 신마산-마산#1T/L 피뢰기 설치(6~44호)","2021-04-08 07:00","2021-04-10 18:00","2021-04-08 07:00","2021-04-10 18:00","매일"]
[601,"경남","함안","신마산진동 T/L","신마산S/S 154kV 신마산-진동T/L CB 조작시험","신마산S/S 154kV 신마산-진동T/L CB 조작시험 및 전자변 교체","2021-04-29 09:30","2021-04-29 17:30","취소","취소","연속"]
[602,"경남","함안","신마산중리#2 T/L","신마산S/S 154kV 신마산-중리#2T/L CB 조작시험","신마산S/S 154kV 신마산-중리#2T/L CB 조작시험","2021-04-22 13:30","2021-04-22 17:30","2021-04-22 13:30","2021-04-22 17:30","연속"]
[603,"경남","함안","신마산중리#1 T/L","신마산S/S 154kV 신마산-중리#1T/L CB 조작시험","신마산S/S 154kV 신마산-중리#1T/L CB 조작시험","2021-04-22 09:30","2021-04-22 13:30","2021-04-22 09:30","2021-04-22 13:30","연속"]
[604,"경남","함안","창녕초동#1 T/L","창녕S/S 154kV 창녕-초동#1T/L CB 조작시험","창녕S/S 154kV 창녕-초동#1T/L CB 조작시험 및 전자변 교체","2021-04-05 09:30","2021-04-05 17:30","2021-04-05 09:30","2021-04-05 17:30","연속"]
[605,"경남","함안","창녕구지#2 T/L","창녕S/S 154kV 창녕-구지#2T/L CB 조작시험","창녕S/S 154kV 창녕-구지#2T/L CB 조작시험 및 전자변 교체","2021-04-11 08:00","2021-04-11 14:00","취소","취소","연속"]
[606,"경남","함안","칠서창녕#2 T/L","154kV 신마산-칠서T/L 지장철탑 이설공사","154kV 신마산-칠서T/L 43호 수평 추락방지장치 설치","2021-04-01 08:00","2021-04-01 18:00","2021-04-01 08:00","2021-04-01 18:00","연속"]
[607,"경남","함안","신마산칠서#1 T/L","154kV 신마산-칠서T/L 지장철탑 이설공사","154kV 신마산-칠서T/L 43호 수평 추락방지장치 설치","2021-04-01 08:00","2021-04-01 18:00","2021-04-01 08:00","2021-04-01 18:00","연속"]
[608,"경남","진주","의령동진주#1 T/L","154kV 의령-함양T/L 송전용 피뢰기 설치공사 안전이격거리 확보","154kV 의령-함양T/L 송전용 피뢰기 설치공사 안전이격거리 확보","2021-04-03 07:00","2021-04-03 12:00","2021-04-03 07:00","2021-04-03 12:00","연속"]
[609,"경남","진주","의령동진주#2 T/L","154kV 의령-동진주#2T/L 송전용 피뢰기 설치공사(68기)","154kV 의령-동진주#2T/L 송전용 피뢰기 설치공사(68기)","2021-04-03 12:00","2021-04-04 18:00","2021-04-03 12:00","2021-04-04 18:00","연속"]
[610,"경남","진주","의령동진주#2 T/L","154kV 의령-동진주#2T/L 송전용 피뢰기 설치공사(68기)","154kV 의령-동진주#2T/L 송전용 피뢰기 설치공사(68기)","2021-04-10 07:00","2021-04-11 18:00","2021-04-10 07:00","2021-04-11 18:00","연속"]