{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":35,"n_cols":11,"rows_kept":35,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2021년도 6월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #1 M.Tr","신가평S/S 종합예방진단시스템 설치","○ 케이블 포설 및 배관 설치 길이 산출 ○ OLTC 부분방전 센서 설치위치 간섭여부 확인 ○ 부싱진단장치 제작을 위한 시험탭 규격 실측","2021-06-16 09:00","2021-06-16 18:00","취소","취소","연속"]
[2,"경기북부","구리","신가평S/S #3 M.Tr","신가평S/S 종합예방진단시스템 설치","○ 케이블 포설 및 배관 설치 길이 산출 ○ OLTC 부분방전 센서 설치위치 간섭여부 확인 ○ 부싱진단장치 제작을 위한 시험탭 규격 실측","2021-06-17 09:00","2021-06-17 18:00","2021-06-17 09:00","2021-06-17 18:00","연속"]
[3,"경기북부","구리","신가평S/S #4 M.Tr","신가평S/S 종합예방진단시스템 설치","○ 케이블 포설 및 배관 설치 길이 산출 ○ OLTC 부분방전 센서 설치위치 간섭여부 확인 ○ 부싱진단장치 제작을 위한 시험탭 규격 실측","2021-06-18 09:00","2021-06-18 18:00","취소","취소","연속"]
[4,"경기북부","구리","신태백신가평#2 T/L","20~21년 구리전력지사 변전정비회사 총액공사","장기사용 배전반 교체공사 - 신가평S/S 765kV #83BAY B/F보호반 교체(강원병행)","2021-06-24 09:00","2021-07-04 18:00","2021-06-25 09:00","2021-07-05 18:00","연속"]
[5,"경기북부","구리","신가평S/S #2 M.Tr","20~21년 구리전력지사 변전정비회사 총액공사","장기사용 배전반 교체공사 - 신가평S/S 765kV #83BAY B/F보호반 교체(신태백-신가평#2T/L 병행)","2021-06-24 09:00","2021-07-04 18:00","2021-06-24 09:00","2021-07-04 18:00","연속"]
[6,"경기","성남","신안성S/S #3 M.Tr","2021년 성남전력 변전정비회사 총액공사","- A-1 TANK MDU 교체 - B-2 OFU 압력계 교체 - C-1 부싱압력모니터 교체 - 옥외분전반교체","2021-06-28 09:00","2021-06-30 18:00","2021-06-28 09:00","2021-06-30 18:00","연속"]
[7,"강원","태백","신태백S/S #3 M.Tr","765kV 신태백S/S #3M.Tr 보호반 및 기타 보호반 대체","1. #3M.Tr 보호반 대체 2. AC PNL 대체","2021-06-01 09:00","2021-06-13 18:00","2021-06-01 09:00","2021-06-13 18:00","연속"]
[8,"강원","태백","신태백신가평#1 T/L","2021년 강원본부 가공송전 순시점검 위탁공사","765kV 신태백-신가평#1T/L 정밀점검 317기","2021-06-14 08:00","2021-06-22 18:00","2021-06-16 08:00","2021-06-24 18:00","연속"]
[9,"충북","직할","신중부S/S #3 M.Tr CB (8500,8572)","765kV 신중부S/S #3M.Tr 증설공사","- 765kV M.Tr 설치 * 1Bank - 765kV GIS 설치 * 1CB - 345kV GIS 설치 * 2CB","2021-06-21 10:00","2021-06-25 16:00","2021-06-28 10:00","2021-06-30 16:00","연속"]
[10,"충북","직할","신중부S/S CB 8500","765kV 신중부S/S #3M.Tr 증설공사","- 765kV M.Tr 설치 * 1Bank - 765kV GIS 설치 * 1CB - 345kV GIS 설치 * 2CB","2021-06-21 10:00","2021-06-25 16:00","취소","취소","연속"]
[11,"충북","직할","신중부S/S #5 M.Tr","신중부S/S 765kV 주변압기 하자보수","765kV 신중부S/S #5M.Tr 제작사 하자보수","2021-06-27 09:00","2021-06-27 18:00","2021-07-04 09:00","2021-07-04 18:00","연속"]
[12,"충북","직할","신중부S/S #4 M.Tr","신중부S/S 765kV 주변압기 하자보수","765kV 신중부S/S #4M.Tr 제작사 하자보수","2021-06-26 09:00","2021-06-26 18:00","2021-07-03 09:00","2021-07-03 18:00","연속"]
[13,"충북","직할","신중부신안성#1 T/L","2021년 직할 가공송전선로 순시점검 위탁공사","765kV 신중부-신안성#1T/L 정밀점검","2021-06-01 07:30","2021-06-06 18:00","2021-06-01 07:30","2021-06-06 18:00","매일"]
[14,"충북","직할","신중부신안성#2 T/L","2021년 직할 가공송전선로 순시점검 위탁공사","765kV 신중부-신안성#2T/L 정밀점검","2021-06-07 07:30","2021-06-12 18:00","2021-06-07 07:30","2021-06-12 18:00","매일"]
[15,"충북","직할","신중부S/S CB 8872","765kV 신중부S/S 800kV GIS 유압매커니즘 보수","조작실패 방지를 위한 유압매커니즘 컨트롤밸브 플러그 교체","2021-06-16 09:00","2021-06-16 18:00","취소","취소","연속"]
[16,"충북","직할","신중부S/S CB 8871","765kV 신중부S/S 800kV GIS 유압매커니즘 보수","조작실패 방지를 위한 유압매커니즘 컨트롤밸브 플러그 교체","2021-06-10 09:00","2021-06-10 18:00","취소","취소","연속"]
[17,"충북","직할","신중부S/S CB 8671","765kV 신중부S/S 800kV GIS 유압매커니즘 보수","조작실패 방지를 위한 유얍매커니즘 컨트롤밸브 플러그 교체","2021-06-01 09:00","2021-06-01 18:00","2021-06-01 09:00","2021-06-01 18:00","연속"]
[18,"충북","직할","신중부S/S CB 8700","765kV 신중부S/S 800kV GIS 유압매커니즘 보수","조작실패 방지를 위한 유압매커니즘 컨트롤밸브 플러그 교체","2021-06-09 09:00","2021-06-09 18:00","취소","취소","연속"]
[19,"충북","직할","신중부S/S CB 8600","765kV 신중부S/S 800kV GIS 유압매커니즘 보수","조작실패 방지를 위한 유얍매커니즘 컨트롤밸브 플러그 교체","2021-06-02 09:00","2021-06-02 18:00","취소","취소","연속"]
[20,"충북","직할","신중부S/S CB 8771","765kV 신중부S/S 800kV GIS 유압매커니즘 보수","조작실패 방지를 위한 유얍매커니즘 컨트롤밸브 플러그 교체","2021-06-08 09:00","2021-06-08 18:00","취소","취소","연속"]
[21,"충북","직할","신중부S/S CB 8800","765kV 신중부S/S 800kV GIS 유압매커니즘 보수","조작실패 방지를 위한 유압매커니즘 컨트롤밸브 플러그 교체","2021-06-15 09:00","2021-06-15 18:00","취소","취소","연속"]
[22,"충북","직할","신중부S/S CB 8672","765kV 신중부S/S 800kV GIS 유압매커니즘 보수","조작실패 방지를 위한 유얍매커니즘 컨트롤밸브 플러그 교체","2021-06-03 09:00","2021-06-03 18:00","취소","취소","연속"]
[23,"충북","직할","신중부S/S CB 8571","765kV 신중부S/S 800kV GIS 유압매커니즘 보수","조작실패 방지를 위한 유얍매커니즘 컨트롤밸브 플러그 교체","2021-06-28 09:00","2021-06-28 18:00","2021-07-01 09:00","2021-07-01 18:00","연속"]
[24,"대전충남","서산","당진T/P CB 8100","'21년 서산P/O 765kV GIS 정밀점검공사","당진화력S/S 765kV #1TIE Tr 1차-1호기 1차 TIE GIS(8100) 정밀점검","2021-06-07 09:00","2021-06-11 18:00","2021-06-07 09:00","2021-06-11 18:00","연속"]
[25,"대전충남","서산","신서산S/S CB 8500"," 21년 서산P/O 345kV/765KV 점검공사","신서산S/S 신중부1T/L-#4 M.Tr 1차 GIS(8500) 보통점검 ","2021-06-21 10:00","2021-06-23 14:00","2021-06-21 10:00","2021-06-23 14:00","연속"]
[26,"부산울산","동부산","신고리N/P 765kV #2 BUS","신고리 5,6호기 접속설비공사","- 8672CB 설치 관련 #2BUS 모선 연결 - #2BUS PRO 86B Lock Out 계전기 교체","2021-06-07 09:00","2021-06-12 18:00","2021-06-07 09:00","2021-06-12 18:00","연속"]
[27,"부산울산","동부산","신고리N/P 765kV #1 BUS","신고리 5,6호기 접속설비공사","- #1BUS PRO 86B Lock Out 계전기 교체","2021-06-17 09:00","2021-06-18 18:00","2021-06-17 09:00","2021-06-18 18:00","연속"]
[28,"부산울산","동부산","신고리N/P #2 Tie-Tr","신고리S/S 가스누기개소 조치 관련 시험가압","신고리S/S 가스누기개소 조치 관련 시험가압(#80BUS)","2021-06-18 16:00","2021-06-18 18:00","2021-06-18 16:00","2021-06-18 18:00","연속"]
[29,"부산울산","동부산","신고리N/P #2 Tie-Tr","신고리 5,6호기 접속설비공사","- 8672CB 시험가압을 위한 시험가압선로(#2M.Tr)","2021-06-11 09:00","2021-06-12 18:00","2021-06-11 09:00","2021-06-12 18:00","연속"]
[30,"부산울산",null,"신고리N/P #3호기 주변압기 (CB 8272)","765kV 신고리 5,6호기 접속설비공사","○ 신고리6호기 접속용 8672CB 설치","2021-06-07 09:00","2021-06-12 18:00","취소","취소","연속"]
[31,"부산울산",null,"신고리N/P #4호기 주변압기 (CB 8372)","765kV 신고리 5,6호기 접속설비공사","○ 신고리6호기 접속용 8672CB 설치","2021-06-07 09:00","2021-06-12 18:00","취소","취소","연속"]

{"sheet":"345설비","index":1,"n_rows":346,"n_cols":11,"rows_kept":346,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2021년도 6월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S 345kV #2 BUS","2021년 성동P/O 변전협력회사 총액공사","345kV #2BUS 모선보호반 교체","2021-06-28 09:30","2021-07-01 18:00","취소","취소","연속"]
[2,"서울","성동","성동S/S 345kV #1 BUS","2021년 성동P/O 변전협력회사 총액공사","345kV #1BUS 모선보호반 교체","2021-06-21 09:30","2021-06-24 18:00","취소","취소","연속"]
[3,"서울","중부","양주중부#1 T/L","양주중부#1T/L 자기애관 교체공사","지중송전 종단접속함용 자기애관 교체(양주중부#1T/L 향동EBA)","2021-06-28 09:00","2021-06-30 18:00","2021-06-28 09:00","2021-06-30 18:00","연속"]
[4,"남서울","강남","신양재S/S #2 Sh.R CB","362kV GIS 조작시험- 변전협력","- 362kV GIS 조작시험 - 접지확인, B,C상 카운터 교체","2021-06-17 10:00","2021-06-17 18:00","2021-06-17 10:00","2021-06-17 18:00","연속"]
[5,"남서울","강남","신성남신양재 #2 T/L","OF케이블 절연유 채유","OF케이블 절연유 채유","2021-06-07 09:00","2021-06-09 18:00","2021-06-07 09:00","2021-06-09 18:00","연속"]
[6,"남서울","강남","신성남신양재 #1 T/L","OF케이블 절연유 채유","OF케이블 절연유 채유","2021-06-02 09:00","2021-06-04 18:00","2021-06-02 09:00","2021-06-04 18:00","연속"]
[7,"남서울","동서울","동서울S/S #1 M.Tr","동서울S/S #1M.Tr 부싱절연유 시료 채유","부싱절연유 가스 분석 이상에 따른 3개월 추적분석 시료채유","2021-06-04 09:00","2021-06-04 18:00","취소","취소","연속"]
[8,"남서울","동서울","동서울S/S #1 M.Tr","동서울S/S 345kV 노후 주변압기 교체 및 이설공사","○ 345kV M.Tr (단상,166.7MVA) * 9대 철거 ○ 345kV M.Tr (단상,166.7MVA) * 2대 재사용철거 ○ 345kV M.Tr (단상,166.7MVA) * 11대 설치 ○ 기타 부대작업 * 1식","2021-06-14 09:00","2021-07-30 18:00","취소","취소","연속"]
[9,"남서울","동서울","동서울S/S #2 M.Tr","345kV #2M.Tr 초기점검","345kV #2M.Tr 초기점검","2021-06-14 09:00","2021-06-18 18:00","취소","취소","연속"]
[10,"남서울","동서울","동서울S/S #3 M.Tr","345kV #3M.Tr 보호반대체, 7572, 6344 CB 조작시험","345kV #3M.Tr 보호반대체, 7572, 6344 CB 조작시험","2021-06-07 09:00","2021-06-11 18:00","취소","취소","연속"]
[11,"남서울","영등포","신광명S/S #1 M.Tr","신광명S/S 345kV #1M.Tr 보수","- 345kV DS 동작불량 보수 - GCB 조작시험 - 컴프레셔 부품 교체, Air V/V 보수","2021-06-01 09:00","2021-06-03 18:00","2021-06-01 09:00","2021-06-03 18:00","연속"]
[12,"남서울","영등포","신시흥신광명#1 T/L","21년 가공송전선로 순시점검 위탁공사","345kV 송전선로 정밀점검(14기)","2021-06-21 09:00","2021-06-22 18:00","취소","취소","매일"]
[13,"남서울","영등포","신시흥신광명#2 T/L","21년 가공송전선로 순시점검 위탁공사","345kV 송전선로 정밀점검(14기)","2021-06-23 09:00","2021-06-24 18:00","취소","취소","매일"]
[14,"남서울","직할","신문래S/S #4 M.Tr","345kV 주변압기,차단기 초기점검","345kV 주변압기 초기점검 345kV 차단기 초기점검(7400,7272)","2021-06-10 09:00","2021-06-11 18:00","2021-06-10 09:00","2021-06-11 18:00","연속"]
[15,"남서울","직할","신광명신문래#3 T/L","345kV 차단기 초기점검","345kV 차단기 초기점검(7271)","2021-06-10 09:00","2021-06-11 18:00","2021-06-10 09:00","2021-06-11 18:00","연속"]
[16,"남서울","영등포","신광명S/S #4 M.Tr","신광명S/S 345kV #4M.Tr 부싱 점검","신광명 #4M.Tr 부싱 점검","2021-06-04 08:00","2021-06-04 18:00","2021-06-04 08:00","2021-06-04 18:00","연속"]
[17,"남서울","영등포","신광명S/S #2 M.Tr","신광명S/S 345kV #2M.Tr 보수","- 345kV DS 동작불량 보수 - GCB 조작시험 - 컴프레셔 부품 교체, Air V/V 보수","2021-06-07 09:00","2021-06-09 18:00","2021-06-07 09:00","2021-06-09 18:00","연속"]
[18,"인천","김포","가정개폐소 CB 7500","가정개폐소 345kV 신가좌-가정#1T/L TIE GIS 보통점검","가정개폐소 345kV 신가좌-가정#1T/L TIE (7500CB) GIS 보통점검","2021-06-01 10:00","2021-06-01 18:00","2021-06-01 10:00","2021-06-01 18:00","연속"]
[19,"인천","김포","가정개폐소 CB 7600","가정개폐소 345kV #1 Sh.R TIE GIS 보통점검","가정개폐소 345kV #1 Sh.R TIE (7600CB) GIS 보통점검","2021-06-02 10:00","2021-06-02 18:00","2021-06-02 10:00","2021-06-02 18:00","연속"]
[20,"인천","김포","신김포S/S SEC CB 75760","신김포S/S 345kV #75-#76 SEC GIS 보통점검","신김포S/S 345kV #75-#76 SEC GIS 보통점검","2021-06-22 10:00","2021-06-22 18:00","2021-06-22 10:00","2021-06-22 18:00","연속"]
[21,"인천","김포","신김포S/S SEC CB 70710","신김포S/S 345kV #70-#71 SEC GIS 보통점검","신김포S/S 345kV #70-#71 SEC GIS 보통점검","2021-06-21 10:00","2021-06-21 18:00","2021-06-21 10:00","2021-06-21 18:00","연속"]
[22,"인천","김포","신김포S/S CB 7572","신김포S/S 345kV 신김포-서인천CC T/L GIS 보통점검","신김포S/S 345kV 신김포-서인천CC T/L (7572CB) GIS 보통점검","2021-06-18 10:00","2021-06-18 18:00","2021-06-18 10:00","2021-06-18 18:00","연속"]
[23,"인천","김포","신김포S/S CB 7500","신김포S/S 345kV 7500CB GIS 보통점검","신김포S/S 345kV 신김포신파주#2-신김포서인천CC TIE (7500CB) GIS 보통점검","2021-06-17 10:00","2021-06-17 18:00","2021-06-17 10:00","2021-06-17 18:00","연속"]
[24,"인천","김포","신김포S/S CB 7571","신김포S/S 345kV 신김포-신파주#2T/L GIS 보통점검","신김포S/S 345kV 신김포-신파주#2T/L (7571CB) GIS 보통점검","2021-06-16 10:00","2021-06-16 18:00","2021-06-16 10:00","2021-06-16 18:00","연속"]
[25,"인천","김포","신김포S/S CB 7671","신김포S/S 345kV #3Sh.R 1차 GIS 개폐제어기 설치공사","신김포S/S 345kV #3Sh.R 1차(7671CB) GIS 개폐제어기 설치공사","2021-06-07 09:00","2021-06-11 18:00","2021-06-23 09:00","2021-06-30 18:00","연속"]
[26,"인천","부평","서인천C/C CB 7471","서인천S/Y 345kV 7471 GIS 조작시험","서인천S/Y 345kV 7471 GIS 조작시험 -전자변 교체","2021-06-21 09:00","2021-06-21 18:00","2021-06-21 09:00","2021-06-21 18:00","연속"]
[27,"인천","부평","서인천C/C CB 7400","서인천S/Y 345kV 7400 GIS 조작시험","서인천S/Y 345kV 7400 GIS 조작시험 -전자변 교체","2021-06-22 09:00","2021-06-22 18:00","2021-06-22 09:00","2021-06-22 18:00","연속"]
[28,"인천","부평","서인천C/C CB 7471","서인천S/Y 345kV 7471 GIS 조작시험","서인천S/Y 345kV 7471 GIS 조작시험 -전자변 교체","2021-06-21 09:00","2021-06-21 18:00","취소","취소","연속"]
[29,"인천","부평","신가좌가정#2 T/L","345kV 신가좌-가정#2T/L 고정형 폴리머 점퍼지지애자 설치","345kV 신가좌-가정#1T/L 고정형 폴리머 점퍼지지애자 설치, 스페이서 간격조정, 추락방지 시설 설치","2021-06-16 08:00","2021-06-17 18:00","취소","취소","매일"]
[30,"인천","부평","신가좌가정#1 T/L","345kV 신가좌-가정#1T/L 고정형 폴리머 점퍼지지애자 설치","345kV 신가좌-가정#1T/L 고정형 폴리머 점퍼지지애자 설치 및 추락방지시설 설치","2021-06-14 08:00","2021-06-15 18:00","취소","취소","매일"]
[31,"인천","부평","신가좌S/S CB 7471","신가좌S/S 345kV 7471 GIS 보통점검","신가좌S/S 345kV 7471 GIS 보통점검","2021-06-17 09:00","2021-06-17 18:00","2021-06-17 09:00","2021-06-17 18:00","연속"]
[32,"인천","부평","신가좌신시흥#1 T/L","345kV 신가좌-신시흥#1T/L 고정형 폴리머 점퍼지지애자 설치","345kV 신가좌-신시흥#1T/L 고정형 폴리머 점퍼지지애자 설치","2021-06-28 08:00","2021-06-30 18:00","취소","취소","연속"]
[33,"인천","부평","신경서S/S CB 7400","신경서S/S 362kV 7400 GIS 조작시험","신경서S/S 362kV 7400 GIS 조작시험","2021-06-03 09:00","2021-06-03 13:00","2021-06-03 09:00","2021-06-03 13:00","연속"]
[34,"인천","부평","신경서S/S CB 7472","신경서S/S 362kV 7472 GIS 조작시험","신경서S/S 362kV 7472 GIS 조작시험","2021-06-03 13:00","2021-06-03 18:00","2021-06-03 13:00","2021-06-03 18:00","연속"]
[35,"인천","부평","신경서S/S CB 7372","신경서S/S 345kV 7372 GIS 조작시험","신경서S/S 345kV 7372 GIS 조작시험","2021-06-08 09:00","2021-06-08 18:00","2021-06-08 09:00","2021-06-08 18:00","연속"]
[36,"인천","부평","신경서S/S CB 7300","신경서S/S 345kV 7300 GIS 조작시험","신경서S/S 345kV 7300 GIS 조작시험","2021-06-09 09:00","2021-06-09 13:00","2021-06-09 09:00","2021-06-09 13:00","연속"]
[37,"인천","부평","신경서S/S CB 7371","신경서S/S 345kV 7371 GIS 조작시험","신경서S/S 345kV 7371 GIS 조작시험","2021-06-09 13:00","2021-06-09 18:00","2021-06-09 13:00","2021-06-09 18:00","연속"]
[38,"인천","부평","신경서S/S CB 7171","신경서S/S 345kV 7171 GIS 보통점검","신가좌S/S 345kV 7171 GIS 보통점검","2021-06-14 09:00","2021-06-14 18:00","2021-06-14 09:00","2021-06-14 18:00","연속"]
[39,"인천","부평","신경서S/S #3 M.Tr","신경서S/S #3M.Tr 보호반 교체공사","신경서S/S #3M.Tr 보호반 교체공사 - 7500, 7572 GIS 조작시험 - 6344 GIS 보통점검","2021-06-28 09:00","2021-07-02 18:00","2021-06-28 09:00","2021-07-02 18:00","연속"]
[40,"인천","부평","포스코C/C CB 7200","포스코S/Y 345kV 7200 GIS 보통점검","포스코S/Y 345kV 7200 GIS 보통점검","2021-06-21 09:00","2021-06-21 18:00","2021-06-21 09:00","2021-06-21 18:00","연속"]
[41,"인천","부평","포스코C/C CB 7100","포스코S/Y 345kV 7100 GIS 보통점검","포스코S/Y 345kV 7100 GIS 보통점검","2021-06-18 09:00","2021-06-18 18:00","2021-06-18 09:00","2021-06-18 18:00","연속"]
[42,"인천","부평","포스코C/C CB 7300","포스코S/Y 345kV 7300 GIS 보통점검","포스코S/Y 345kV 7300 GIS 보통점검","2021-06-17 09:00","2021-06-17 18:00","2021-06-17 09:00","2021-06-17 18:00","연속"]
[43,"인천","부평","포스코C/C CB 7171","포스코S/Y 345kV 7171 GIS 보통점검","포스코S/Y 345kV 7171 GIS 보통점검","2021-06-25 09:00","2021-06-25 18:00","2021-06-25 09:00","2021-06-25 18:00","연속"]
[44,"인천","부평","포스코C/C CB 7400","포스코S/Y 345kV 7400 GIS 보통점검","포스코S/Y 345kV 7400 GIS 보통점검","2021-06-23 09:00","2021-06-23 18:00","2021-06-23 09:00","2021-06-23 18:00","연속"]
[45,"인천","부평","포스코C/C CB 7371","포스코S/Y 345kV 7371 GIS 보통점검","포스코S/Y 345kV 7371 GIS 보통점검","2021-06-24 09:00","2021-06-24 18:00","2021-06-24 09:00","2021-06-24 18:00","연속"]
[46,"인천","부평","포스코C/C CB 7471","포스코S/Y 345kV 7471 GIS 보통점검","포스코S/Y 345kV 7471 GIS 보통점검","2021-06-22 09:00","2021-06-22 18:00","2021-06-22 09:00","2021-06-22 18:00","연속"]
[47,"인천","부평","포스코C/C CB 7271","포스코S/Y 345kV 7271 GIS 보통점검","포스코S/Y 345kV 7271 GIS 보통점검","2021-06-15 09:00","2021-06-15 18:00","2021-06-15 09:00","2021-06-15 18:00","연속"]
[48,"인천","시흥","신시흥#1S/S CB 7C71","신시흥S/S 362kV GIS 메카니즘 세척작업","신시흥S/S 362kV GIS 메카니즘 세척작업 - 7100 등 30개 GIS 메카니즘 세척","2021-06-02 09:00","2021-06-02 14:00","2021-06-02 09:00","2021-06-02 14:00","연속"]
[49,"인천","시흥","신시흥신광명#1 T/L","345kV 신시흥-신광명#1T/L 고정형 폴리머 점퍼지지애자 설치","345kV 신시흥-신광명#1T/L 고정형 폴리머 점퍼지지애자 설치","2021-06-28 08:00","2021-06-30 18:00","취소","취소","연속"]
[50,"인천","시흥","신시흥신광명#2 T/L","신시흥S/S 7ABay B/F 보호반 대체","신시흥S/S 7ABay B/F 보호반 대체","2021-06-21 09:00","2021-06-25 18:00","취소","취소","연속"]
[51,"인천","시흥","신시흥#1S/S #2 M.Tr","신시흥S/S 7ABay B/F 보호반 대체","신시흥S/S 7ABay B/F 보호반 대체","2021-06-21 09:00","2021-06-25 18:00","취소","취소","연속"]
[52,"인천","시흥","신시흥영흥TP#3 T/L","21년 가공송전설비 순시점검 위탁공사","ㅇ 21년 가공송전설비 순시점검 위탁공사 - 345kV 신시흥-영흥#3T/L 정밀점검 시행","2021-06-07 08:00","2021-06-12 18:00","2021-06-07 08:00","2021-06-12 18:00","연속"]
[53,"인천","시흥","신시흥#1S/S CB 7C00","신시흥S/S 362kV GIS 메카니즘 세척작업","신시흥S/S 362kV GIS 메카니즘 세척작업 - 7100 등 30개 GIS 메카니즘 세척","2021-06-02 14:00","2021-06-02 18:00","2021-06-02 14:00","2021-06-02 18:00","연속"]
[54,"인천","시흥","서서울#2신시흥#2 T/L","신시흥S/S 76Bay B/F 보호반 대체","신시흥S/S 76Bay B/F 보호반 대체","2021-06-14 09:00","2021-06-18 18:00","취소","취소","연속"]
[55,"인천","시흥","신시흥#2S/S #4 M.Tr","신시흥S/S 76Bay B/F 보호반 대체","신시흥S/S 76Bay B/F 보호반 대체","2021-06-14 09:00","2021-06-18 18:00","취소","취소","연속"]
[56,"인천","시흥","신시흥#2S/S #6 M.Tr","신시흥#2S/S 345kV #6 M.Tr 1,2차 GIS 조작시험","신시흥#2S/S 345kV #6 M.Tr 1,2차 GIS 조작시험","2021-06-04 09:00","2021-06-04 18:00","2021-06-08 09:00","2021-06-08 18:00","연속"]
[57,"인천","시흥","신시흥#2S/S #5 M.Tr","신시흥#2S/S 345kV #5 M.Tr 1,2차 GIS 조작시험","신시흥#2S/S 345kV #5 M.Tr 1,2차 GIS 조작시험","2021-06-03 09:00","2021-06-03 18:00","취소","취소","연속"]
[58,"인천","시흥","신시흥영흥TP#1 T/L","21년 가공송전설비 순시점검 위탁공사","ㅇ 21년 가공송전설비 순시점검 위탁공사 - 345kV 신시흥-영흥#1T/L 정밀점검 시행","2021-06-01 08:00","2021-06-05 18:00","취소","취소","연속"]
[59,"인천","시흥","영흥T/P CB 7900","영흥#2T/P 345kV 영흥TP연락#2T/L TIE GIS 정밀점검","영흥#2T/P 345kV 영흥TP연락#2T/L TIE GIS 정밀점검","2021-06-14 09:00","2021-06-16 18:00","2021-06-14 09:00","2021-06-16 18:00","연속"]
[60,"인천","시흥","영흥T/P CB 7971","영흥#2T/P 345kV 영흥TP연락#2T/L GIS 정밀점검","영흥#2T/P 345kV 영흥TP연락#2T/L GIS 정밀점검","2021-06-16 09:00","2021-06-19 18:00","2021-06-16 09:00","2021-06-19 18:00","연속"]
[61,"인천","시흥","영흥1TP영흥2TP#1 T/L","영흥#2S/Y 영흥TP연락#1 T/L 부싱 염해도포","영흥#2S/Y 영흥TP연락#1 T/L 부싱 염해도포","2021-06-23 09:00","2021-06-23 18:00","2021-06-23 09:00","2021-06-23 18:00","연속"]
[62,"인천","직할","신부평S/S CB 7272","신부평S/S #2M.Tr 1차 7272 GIS 조작시험 및 전자변교체","신부평S/S #2M.Tr 1차 7272 GIS 조작시험 및 전자변교체","2021-06-21 09:00","2021-06-22 18:00","2021-06-30 09:00","2021-06-30 18:00","연속"]
[63,"인천","직할","서인천CC신부평#4 T/L","345kV 서인천CC-신부평 등 2개T/L 절연유 채취밸브 설치공사","대상 : 345kV 서인천CC-신부평#4T/L (13개소) 내용 : 활선 고정형 절연유 채취밸브 설치 및 절연유 채유","2021-06-21 09:00","2021-06-27 18:00","2021-06-21 09:00","2021-06-27 18:00","연속"]
[64,"인천","직할","신부평S/S CB 7400","신부평S/S 7400BUSTIE GIS 조작시험 및 전자변교체","신부평S/S 7400BUSTIE GIS 조작시험 및 전자변교체","2021-06-23 09:00","2021-06-24 18:00","2021-06-23 09:00","2021-06-24 18:00","연속"]
[65,"인천","직할","신부평S/S CB 7300","신부평S/S 7300BUSTIE GIS 조작시험 및 전자변교체","신부평S/S 7300BUSTIE GIS 조작시험 및 전자변교체","2021-06-28 09:00","2021-06-29 18:00","2021-06-28 09:00","2021-06-29 18:00","연속"]
[66,"인천","직할","신부평S/S CB 7271","2021년도 362kV GIS정밀점검(신부평SS 서인천CC신부평#2TL)","2021년도 362kV 7271 GIS정밀점검(신부평S/S 서인천CC신부평#2TL)","2021-06-08 09:00","2021-06-11 18:00","2021-06-08 09:00","2021-06-11 18:00","연속"]
[67,"인천","직할","신부평S/S CB 7200","2021년도 362kV GIS정밀점검(신부평SS 7200 BUSTIE)","2021년도 362kV GIS정밀점검(신부평SS 7200 BUSTIE)","2021-06-01 09:00","2021-06-04 18:00","2021-06-01 09:00","2021-06-04 18:00","연속"]
[68,"인천","직할","서인천CC신부평#1 T/L","345kV 서인천CC-신부평 등 2개T/L 절연유 채취밸브 설치공사","대상 : 345kV 서인천CC-신부평#1T/L (12개소) 내용 : 활선 고정형 절연유 채취밸브 설치 및 절연유 채유","2021-06-14 09:00","2021-06-20 18:00","2021-06-14 09:00","2021-06-20 18:00","연속"]
[69,"인천","직할","신부평S/S CB 7100","신부평S/S 7100BUSTIE GIS 조작시험 및 전자변교체(A,C상)","신부평S/S 7100BUSTIE GIS 조작시험 및 전자변교체","2021-06-18 09:00","2021-06-18 18:00","2021-06-18 09:00","2021-06-18 18:00","연속"]
[70,"경기북부","고양","신덕은S/S #4 M.Tr","21년 고양P/O 345kV 주변압기 정밀점검공사","신덕은S/S #4M.Tr 정밀점검공사","2021-06-14 10:00","2021-06-22 14:00","2021-06-14 10:00","2021-06-22 14:00","연속"]
[71,"경기북부","고양","신덕은S/S #1 M.Tr","21년 고양P/O 345kV 주변압기 정밀점검공사","신덕은S/S #1M.Tr C상 정밀점검공사","2021-06-22 14:00","2021-06-25 18:00","2021-06-22 14:00","2021-06-25 18:00","연속"]
[72,"경기북부","고양","신파주신덕은#2 T/L","20-21년 고양전력지사 가공송전 정비회사 총액공사","ㅇ 불량애자교체","2021-06-09 07:00","2021-06-11 18:00","2021-06-09 07:00","2021-06-11 18:00","연속"]
[73,"경기북부","고양","신김포신파주#2 T/L","20-21년 고양전력지사 가공송전 정비회사 총액공사","ㅇ 항공장애표시구 설치","2021-06-04 07:00","2021-06-04 18:00","취소","취소","연속"]
[74,"경기북부","구리","미금S/S CB 7272","`20~21 구리전력 변전정비 총액공사","미금S/S 345kV 7272 차단기 개폐타임 측정","2021-06-09 09:00","2021-06-09 18:00","2021-06-09 09:00","2021-06-09 18:00","연속"]
[75,"경기북부","구리","미금S/S STATCOM CB","345kV 미금S/S 용량부족 차단기 대체공사","345kV 미금S/S 용량부족 차단기 대체공사 - #79BAY GIS 대체(50kA→63kA) - 기타 부대공사 1식","2021-06-01 09:00","2021-08-20 18:00","취소","취소","연속"]
[76,"경기북부","구리","신가평S/S #2 Sh.R CB","`20~21 구리전력 변전정비 총액공사","신가평S/S #2Sh.R 7379 차단기 개폐타임 측정 전자변 교체","2021-06-14 09:00","2021-06-14 18:00","2021-06-14 09:00","2021-06-14 18:00","연속"]
[77,"경기북부","구리","신가평신의정부#1 T/L","2020~2021년 경기북부본부 직할 가공송전 정비회사 총액공사","피뢰기 설치공사 상단병가선로","2021-06-01 07:30","2021-06-04 18:00","2021-06-01 07:30","2021-06-04 18:00","연속"]
[78,"경기북부","직할","신의정부S/S #4 M.Tr","20-21년 직할 변전정비회사 총액공사","신의정부S/S 345kV #4M.Tr B상 2차 부싱 절연유 유중가스 추적관리 (2차 부싱 C2H2 : 0.2ppm) 신의정부S/S 345kV 예비M.Tr 장기사용 부싱 점검(유중가스분석, 절연열화 측정)","2021-06-02 09:00","2021-06-02 18:00","2021-06-02 09:00","2021-06-02 18:00","연속"]
[79,"경기북부","직할","신의정부S/S #2 Sh.R CB","2020-2021년 경기북부 직할 변전정비회사 총액공사","신의정부S/S 345kV #2Sh.R 보호반 교체","2021-06-28 09:00","2021-07-02 18:00","2021-06-28 09:00","2021-07-02 18:00","연속"]
[80,"경기북부","직할","신의정부S/S #3 M.Tr","20-21년 직할 변전정비회사 총액공사","신의정부S/S 345kV #3M.Tr C상 1, 2차 부싱 절연유 유중가스 추적관리 (1차 부싱 C2H2 : 0.2 / 2차 부싱 C2H2 : 0.3)","2021-06-01 09:00","2021-06-01 18:00","2021-06-01 09:00","2021-06-01 18:00","연속"]
[81,"경기북부","직할","양주S/S #2 M.Tr","345kV 양주S/S 종합예방진단시스템 설치","○ 종합예방진단시스템 설치 × 1식 ○ 345, 154kV M.Tr 유중가스, 부싱, OLTC진단, 분석장비 설치 × 1식 ○ 345, 154kV GIS 부분방전 진단, 차단기 동작분석 장비 설치 × 1식 ○ 온라인부분방전진단시스템 철거 × 1식 ○ 기타부대공사 × 1식","2021-06-23 10:00","2021-06-23 18:00","2021-06-23 10:00","2021-06-23 18:00","연속"]
[82,"경기북부","직할","양주S/S #1 M.Tr","345kV 양주S/S 종합예방진단시스템 설치","○ 종합예방진단시스템 설치 × 1식 ○ 345, 154kV M.Tr 유중가스, 부싱, OLTC진단, 분석장비 설치 × 1식 ○ 345, 154kV GIS 부분방전 진단, 차단기 동작분석 장비 설치 × 1식 ○ 온라인부분방전진단시스템 철거 × 1식 ○ 기타부대공사 × 1식","2021-06-22 10:00","2021-06-22 18:00","2021-06-22 10:00","2021-06-22 18:00","연속"]
[83,"경기북부","직할","양주S/S #3 M.Tr","345kV 양주S/S 종합예방진단시스템 설치","○ 종합예방진단시스템 설치 × 1식 ○ 345, 154kV M.Tr 유중가스, 부싱, OLTC진단, 분석장비 설치 × 1식 ○ 345, 154kV GIS 부분방전 진단, 차단기 동작분석 장비 설치 × 1식 ○ 온라인부분방전진단시스템 철거 × 1식 ○ 기타부대공사 × 1식","2021-06-24 10:00","2021-06-24 18:00","2021-06-24 10:00","2021-06-24 18:00","연속"]
[84,"경기북부","직할","양주S/S #4 M.Tr","345kV 양주S/S 종합예방진단시스템 설치","○ 종합예방진단시스템 설치 × 1식 ○ 345, 154kV M.Tr 유중가스, 부싱, OLTC진단, 분석장비 설치 × 1식 ○ 345, 154kV GIS 부분방전 진단, 차단기 동작분석 장비 설치 × 1식 ○ 온라인부분방전진단시스템 철거 × 1식 ○ 기타부대공사 × 1식","2021-06-25 10:00","2021-06-25 18:00","2021-06-25 10:00","2021-06-25 18:00","연속"]
[85,"경기","군포","서서울#2S/S #5 M.Tr","서서울2S/S #5M.Tr 1차 포스트 새집 제거","서서울2S/S #5M.Tr 1차 포스트 새집 제거","2021-06-09 09:00","2021-06-09 18:00","2021-06-09 09:00","2021-06-09 18:00","연속"]
[86,"경기","군포","서서울S/S #2 M.Tr","서서울#1S/S 345kV #2M.Tr 보통점검","- #2M.Tr 보통점검 - 7500,7572 GIS 조작시험 - 3차 과열보수 작업","2021-06-10 09:00","2021-06-11 18:00","2021-06-10 09:00","2021-06-11 18:00","연속"]
[87,"경기","군포","서서울S/S #3 M.Tr","서서울#1S/S 345kV #3M.Tr 초기점검","-#3M.Tr 초기점검, 7600,7672 GIS 조작시험","2021-06-08 09:00","2021-06-09 18:00","2021-06-08 09:00","2021-06-09 18:00","연속"]
[88,"경기","군포","신안산S/S #4 M.Tr","신안산S/S 종합예방진단시스템 설치공사","신안산S/S 종합예방진단시스템 설치공사","2021-06-24 09:00","2021-06-25 14:00","2021-06-24 09:00","2021-06-25 14:00","연속"]
[89,"경기","군포","신안산S/S #3 M.Tr","신안산S/S 종합예방진단시스템 설치공사","신안산S/S 종합예방진단시스템 설치공사","2021-06-22 14:00","2021-06-23 18:00","2021-06-22 14:00","2021-06-23 18:00","연속"]
[90,"경기","군포","신안산S/S #1 M.Tr","신안산S/S 종합예방진단시스템 설치공사","신안산S/S 종합예방진단시스템 설치공사","2021-06-21 09:00","2021-06-22 14:00","2021-06-21 09:00","2021-06-22 14:00","연속"]
[91,"경기","동부","곤지암S/S #1M.Tr","곤지암S/S 종합예방진단시스템 설치공사","곤지암S/S 종합예방진단시스템 설치공사","2021-06-29 09:00","2021-06-29 14:00","2021-06-29 09:00","2021-06-29 14:00","연속"]
[92,"경기","동부","곤지암S/S #2M.Tr","곤지암S/S 종합예방진단시스템 설치공사","곤지암S/S 종합예방진단시스템 설치공사","2021-06-29 14:00","2021-06-29 18:00","2021-06-29 14:00","2021-06-29 18:00","연속"]
[93,"경기","동부","곤지암S/S #3M.Tr","곤지암S/S 종합예방진단시스템 설치공사","곤지암S/S 종합예방진단시스템 설치공사","2021-06-30 09:00","2021-06-30 14:00","2021-06-30 09:00","2021-06-30 14:00","연속"]
[94,"경기","동부","곤지암S/S #4M.Tr","곤지암S/S 종합예방진단시스템 설치공사","곤지암S/S 종합예방진단시스템 설치공사","2021-06-29 14:00","2021-06-30 18:00","2021-06-29 14:00","2021-06-30 18:00","연속"]
[95,"경기","동부","곤지암S/S #1 Sh.R CB","21년 동부 변전정비회사 총액공사","곤지암:7271,7371,7179차단기(조작) 7371(A,B,C)전자변교체(I)","2021-06-17 12:00","2021-06-17 15:00","2021-06-17 12:00","2021-06-17 15:00","연속"]
[96,"경기","동부","곤지암S/S CB 7271","21년 동부 변전정비회사 총액공사","곤지암:7271,7371,7179차단기(조작) 7371(A,B,C)전자변교체(I)","2021-06-17 09:00","2021-06-17 12:00","2021-06-17 09:00","2021-06-17 12:00","연속"]
[97,"경기","동부","곤지암S/S CB 7200","21년 동부 변전정비회사 총액공사","곤지암:7171,7200 차단기(조작) 7200(A)전자변교체(I)","2021-06-16 14:00","2021-06-16 18:00","2021-06-16 14:00","2021-06-16 18:00","연속"]
[98,"경기","동부","곤지암S/S CB 7171","21년 동부 변전정비회사 총액공사","곤지암:7171,7200 차단기(조작) 7200(A)전자변교체(I)","2021-06-16 09:00","2021-06-16 14:00","2021-06-16 09:00","2021-06-16 14:00","연속"]
[99,"경기","동부","곤지암S/S CB 7371","21년 동부 변전정비회사 총액공사","곤지암:7271,7371,7179차단기(조작) 7371(A,B,C)전자변교체(I)","2021-06-17 15:00","2021-06-17 18:00","2021-06-17 15:00","2021-06-17 18:00","연속"]
[100,"경기","성남","신성남S/S #4 M.Tr","2021년 성남전력 변전정비회사 총액공사","GIS 보통점검, LA,PT 보통점검","2021-06-10 09:00","2021-06-10 18:00","2021-06-10 09:00","2021-06-10 18:00","연속"]
[101,"경기","성남","신성남S/S SEC CB 75760","2021년 성남전력지사 변전정비회사 총액공사","GIS 조작시험","2021-06-18 14:00","2021-06-18 18:00","2021-06-18 14:00","2021-06-18 18:00","연속"]
[102,"경기","성남","신성남S/S SEC CB 70710","2021년 성남전력지사 변전정비회사 총액공사","GIS 조작시험","2021-06-18 09:00","2021-06-18 14:00","2021-06-18 09:00","2021-06-18 14:00","연속"]
[103,"경기","성남","신성남S/S #3 M.Tr","2021년 성남전력 변전정비회사 총액공사","1,2차 GIS 보통점검","2021-06-24 09:00","2021-06-24 18:00","2021-06-24 09:00","2021-06-24 18:00","연속"]
[104,"경기","성남","신수원삼성#1 T/L","2021년 성남전력 변전정비회사 총액공사","GIS 보통점검, 보호계전기 성능개선","2021-06-21 09:00","2021-06-21 18:00","취소","취소","연속"]
[105,"경기","성남","신수원S/S #4 M.Tr","2021년 성남전력 변전정비회사 총액공사","1차측 GIS 하자점검, 2차측 GIS 정밀점검","2021-06-29 09:00","2021-07-01 18:00","2021-06-29 09:00","2021-07-01 18:00","연속"]
[106,"경기","성남","신수원S/S #3 M.Tr","2021년 성남전력 변전정비회사 총액공사","1차 GIS 하자점검, 보호반 교체","2021-06-14 09:00","2021-06-25 18:00","2021-06-14 09:00","2021-06-25 18:00","연속"]
[107,"경기","성남","신수원S/S 345kV #1 BUS","345kV 신수원S/S GIS 용량대체공사(72Bay)_무부하","7271 CB 무부하 가압","2021-06-09 11:00","2021-06-10 11:00","2021-06-09 11:00","2021-06-10 11:00","연속"]
[108,"경기","성남","신수원삼성#2 T/L","2021년 성남전력 변전정비회사 총액공사","GIS 보통점검, 보호계전기 성능개선","2021-06-23 10:00","2021-06-23 18:00","2021-06-23 10:00","2021-06-23 18:00","연속"]
[109,"경기","성남","신안성S/S CB 7871","21년 성남전력지사 변전정비회사 총액공사","메커니즘 그리스 제거","2021-06-01 09:00","2021-06-01 14:00","2021-06-01 09:00","2021-06-01 14:00","연속"]
[110,"경기","성남","신안성S/S CB 7800","21년 성남전력지사 변전정비회사 총액공사","메커니즘 그리스 제거","2021-06-01 14:00","2021-06-01 18:00","2021-06-01 14:00","2021-06-01 18:00","연속"]
[111,"경기","성남","신안성S/S CB 7A72","21년 성남전력지사 변전정비회사 총액공사","메커니즘 그리스 제거","2021-06-02 14:00","2021-06-02 18:00","2021-06-02 14:00","2021-06-02 18:00","연속"]
[112,"경기","성남","신안성S/S CB 7B72","21년 성남전력지사 변전정비회사 총액공사","메커니즘 그리스 제거","2021-06-03 09:00","2021-06-03 14:00","2021-06-03 09:00","2021-06-03 14:00","연속"]
[113,"경기","성남","신안성S/S CB 7C71","21년 성남전력지사 변전정비회사 총액공사","메커니즘 그리스 제거","2021-06-03 14:00","2021-06-03 18:00","2021-06-03 14:00","2021-06-03 18:00","연속"]
[114,"경기","성남","신안성S/S CB 7C00","21년 성남전력지사 변전정비회사 총액공사","메커니즘 그리스 제거","2021-06-04 09:00","2021-06-04 14:00","2021-06-04 09:00","2021-06-04 14:00","연속"]
[115,"경기","성남","신안성S/S CB 7C72","21년 성남전력지사 변전정비회사 총액공사","메커니즘 그리스 제거","2021-06-04 14:00","2021-06-04 18:00","2021-06-04 14:00","2021-06-04 18:00","연속"]
[116,"경기","성남","신안성신수원#2 T/L","345kV 신안성-신수원#2T/L 송전선로 정밀점검","345kV 신안성-신수원#2T/L(No.57~67) 송전선로 정밀점검","2021-06-17 09:00","2021-06-22 18:00","취소","취소","매일"]
[117,"경기","성남","신용인삼성 T/L","345kV 신안성-신수원#2T/L 송전선로 정밀점검","345kV 신안성-신수원#2T/L(No.57~67) 송전선로 정밀점검 [4회선 철탑-안전이격거리 확보]","2021-06-17 09:00","2021-06-22 18:00","취소","취소","매일"]
[118,"경기","직할","화성평택TP#1 T/L","345kV 화성S/S GIS 용량대체공사","#4M.Tr Bay 조정관련 무부하가압 선로 휴전","2021-06-10 10:00","2021-06-11 18:00","2021-07-01 09:00","2021-07-02 18:00","연속"]
[119,"경기","직할","화성S/S #2 M.Tr","20-21년 경기직할 변전정비회사 총액공사","화성S/S #2M.Tr 보통점검, 3차 LA 대체, 7472 GIS 조작시험","2021-06-14 09:00","2021-06-16 18:00","2021-06-14 09:00","2021-06-16 18:00","연속"]
[120,"경기","직할","화성S/S 345kV #70 BUS","20-21년 경기직할 변전정비회사 총액공사","화성S/S #70BUS 가스누기보수","2021-06-28 09:00","2021-07-02 18:00","2021-06-28 09:00","2021-07-02 18:00","연속"]
[121,"경기","직할","화성S/S #3 M.Tr","345kV 화성S/S GIS 용량대체공사","#4M.Tr Bay 조정관련 철구보강 안전이격거리 확보차","2021-06-05 08:00","2021-06-06 18:00","2021-06-19 09:00","2021-06-20 18:00","연속"]
[122,"경기","평택","고덕S/S 345kV #2 BUS","345kV 고덕#2S/S 건설사업","345kV 고덕#2S/S 건설사업 - 고덕#1S/S 362kV GIS 2CB 증설","2021-06-07 09:00","2021-06-25 18:00","2021-06-07 09:00","2021-06-25 18:00","연속"]
[123,"경기","평택","서안성S/S #3 M.Tr","서안성S/S 345kV #3 M.Tr 부싱절연유 채유","서안성S/S 345kV #3 M.Tr 부싱절연유 채유","2021-06-11 10:00","2021-06-11 14:00","2021-06-11 10:00","2021-06-11 14:00","연속"]
[124,"경기","평택","서안성S/S #2 M.Tr","서안성S/S 345kV #2 M.Tr 부싱절연유 채유","서안성S/S 345kV #2 M.Tr 부싱절연유 채유","2021-06-10 14:00","2021-06-10 18:00","2021-06-10 14:00","2021-06-10 18:00","연속"]
[125,"경기","평택","서안성S/S #1 M.Tr","서안성S/S 345kV #1 M.Tr 부싱절연유 채유","서안성S/S 345kV #1 M.Tr 부싱절연유 채유","2021-06-10 10:00","2021-06-10 14:00","2021-06-10 10:00","2021-06-10 14:00","연속"]
[126,"경기","평택","평택T/P CB 7172","평택T/P 345kV #3 T/P 1차 GIS(7172) 보통점검","평택T/P 345kV #3 T/P 1차 GIS(7172) 보통점검","2021-06-02 10:00","2021-06-02 18:00","2021-06-02 10:00","2021-06-02 18:00","연속"]
[127,"경기","평택","평택T/P CB 7271","평택T/P 345kV #4 T/P 1차 GIS(7271) 보통점검","평택T/P 345kV #4 T/P 1차 GIS(7271) 보통점검","2021-06-03 10:00","2021-06-03 18:00","2021-06-03 10:00","2021-06-03 18:00","연속"]
[128,"경기","평택","평택T/P CB 7200","평택T/P #3,4 SU Tr 1차-#4 T/P 1(7200) 보통점검","평택T/P 345kV #3,4 SU Tr 1차-#4 T/P 1(7200) 보통점검","2021-06-04 10:00","2021-06-04 18:00","2021-06-04 10:00","2021-06-04 18:00","연속"]
[129,"경기","평택","평택T/P CB 7272","평택T/P 345kV #3,4 SU Tr 1차 GIS(7272) 보통점검","평택T/P 345kV #3,4 SU Tr 1차 GIS(7272) 보통점검","2021-06-07 10:00","2021-06-07 18:00","2021-06-07 10:00","2021-06-07 18:00","연속"]
[130,"경기","평택","평택T/P CB 7471","평택T/P 345kV #3 TIE Tr 1차 GIS(7471) 보통점검","평택T/P 345kV #3 TIE Tr 1차 GIS(7471) 보통점검","2021-06-08 10:00","2021-06-08 18:00","2021-06-08 10:00","2021-06-08 18:00","연속"]
[131,"경기","평택","평택T/P CB 7400","평택T/P #1T/P 1차-#3 TIE Tr 1차 (7400) 보통점검","평택T/P #1T/P 1차-#3 TIE Tr 1차 (7400) 보통점검","2021-06-09 10:00","2021-06-09 18:00","2021-06-09 10:00","2021-06-09 18:00","연속"]
[132,"경기","평택","평택T/P CB 7472","평택T/P 345kV #1 T/P 1차 GIS (7472) 보통점검","평택T/P 345kV #1 T/P 1차 GIS (7472) 보통점검","2021-06-14 10:00","2021-06-14 18:00","2021-06-14 10:00","2021-06-14 18:00","연속"]
[133,"경기","평택","평택T/P CB 7672","평택T/P 345kV #2 T/P 1차 GIS(7672) 보통점검","평택T/P 345kV #2 T/P 1차 GIS(7672) 보통점검","2021-06-16 10:00","2021-06-16 18:00","2021-06-16 10:00","2021-06-16 18:00","연속"]
[134,"경기","평택","평택T/P CB 7571","평택T/P 345kV 화성-평택 #2T/L GIS(7571) 보통점검","평택T/P 345kV 화성-평택 #2T/L GIS(7571) 보통점검","2021-06-15 10:00","2021-06-15 18:00","2021-06-15 10:00","2021-06-15 18:00","연속"]
[135,"강원","강릉","안인개폐소신양양 T/L","20-21년도 강릉전력지사 송전정비회사 총액공사","○ 불량애자교체 : 345kV 양양양수(안인개폐소신양양)T/L no.27,30,35,37,39,40,45,46,47,49,51,52","2021-06-01 08:00","2021-06-04 18:00","취소","취소","매일"]
[136,"강원","태백","신태백S/S CB 7471, 7400, 7472, 7479","765kV 신태백S/S 345kV 용량부족차단기 대체 및 SW증설공사","74Bay GIS 40kA 4000A 3CB 철거 74Bay GIS 63kA 6300A 3CB 설치 기타 부대공사 1식","2021-06-01 09:00","2021-08-31 18:00","2021-06-01 09:00","2021-08-31 18:00","연속"]
[137,"강원","강릉","양양P/P CB 7200","양양PP 컨트롤블록 교체","○ 양양PP 컨트롤블록 교체 - 7200 CB","2021-06-01 10:00","2021-06-02 18:00","취소","취소","연속"]
[138,"강원","강릉","양양P/P CB 7272","양양PP 컨트롤블록 교체","○ 양양PP 컨트롤블록 교체 - 7272 CB","2021-06-03 10:00","2021-06-04 18:00","취소","취소","연속"]
[139,"강원","강릉","양양P/P 345kV #1 BUS","2021년 강릉전력지사 362kV GIS 정밀점검","○ 2021년 362kV GIS 정밀점검 - 무부하 가압","2021-06-04 09:00","2021-06-04 18:00","2021-06-02 10:00","2021-06-02 18:00","연속"]
[140,"강원","동해","삼척G/P CB 7672","동해전력지사 2021년 362kV GIS 정밀점검","1. GIS 정밀점검","2021-06-07 09:00","2021-06-10 18:00","2021-06-07 09:00","2021-06-10 18:00","연속"]
[141,"강원","강릉","신양양S/S CB 7200","장기미동작 차단기 조작시험","- 신양양S/S 154kV 장기미동작 차단기 조작시험","2021-06-10 10:00","2021-06-10 14:00","2021-06-10 10:00","2021-06-10 14:00","연속"]
[142,"강원","강릉","신양양S/S CB 7271","장기미동작 차단기 조작시험","- 신양양S/S 154kV 장기미동작 차단기 조작시험","2021-06-10 14:00","2021-06-10 18:00","2021-06-10 14:00","2021-06-10 18:00","연속"]
[143,"강원","동해","동해S/S CB 7272","동해전력지사 2021년 362kV GIS 정밀점검","1. GIS 정밀점검","2021-06-14 09:00","2021-06-17 18:00","2021-06-21 09:00","2021-06-24 18:00","연속"]
[144,"강원","동해","동해삼척GP#1 T/L","345kV 동해-삼척GPT/L 전선접속개소 전선교체공사","No.110~120 전선접속개소 전선교체","2021-06-21 08:00","2021-06-29 18:00","2021-06-30 08:00","2021-07-08 18:00","연속"]
[145,"강원","동해","동해S/S CB 7372","동해전력지사 2021년 362kV GIS 정밀점검","1. GIS 정밀점검","2021-06-21 09:00","2021-06-24 18:00","2021-06-28 09:00","2021-07-01 18:00","연속"]
[146,"강원","강릉","양양P/P CB 7372","양양PP 컨트롤블록 교체","○ 양양PP 컨트롤블록 교체 - 7372 CB","2021-06-21 10:00","2021-06-22 14:00","2021-06-21 10:00","2021-06-22 14:00","연속"]
[147,"강원","강릉","양양P/P CB 7271","양양PP 컨트롤블록 교체","○ 양양PP 컨트롤블록 교체 - 7271 CB","2021-06-23 10:00","2021-06-24 14:00","취소","취소","연속"]
[148,"강원","강릉","양양P/P CB 7172","양양PP 컨트롤블록 교체","○ 양양PP 컨트롤블록 교체 - 7172 CB","2021-06-24 14:00","2021-06-25 18:00","2021-06-24 14:00","2021-06-25 18:00","연속"]
[149,"강원","동해","동해S/S CB 7572","동해전력지사 2021년 362kV GIS 정밀점검","1. GIS 정밀점검","2021-06-28 09:00","2021-07-01 18:00","2021-06-14 09:00","2021-06-17 18:00","연속"]
[150,"강원","동해","동해삼척GP#2 T/L","345kV 동해-삼척GPT/L 전선접속개소 전선교체공사","No.110~120 전선접속개소 전선교체","2021-06-30 08:00","2021-07-08 18:00","2021-06-24 08:00","2021-06-29 18:00","연속"]
[151,"충북","직할","신중부신진천#1 T/L","신중부S/S 345kV GIS 하자점검","신중부S/S 345kV GIS 신중부-신진천#1T/L 7972, 7900CB","2021-06-03 09:00","2021-06-04 18:00","2021-06-03 09:00","2021-06-04 18:00","연속"]
[152,"충북","직할","신중부신진천#2 T/L","신중부S/S 345kV GIS 하자점검","신중부S/S 345kV GIS 신중부-신진천#2T/L 7A72, 7A00CB 하자점검","2021-06-10 09:00","2021-06-11 18:00","2021-06-10 09:00","2021-06-11 18:00","연속"]
[153,"충북","직할","신진천S/S #2 M.Tr","21년 직할 변전협력회사 총액공사","유사고장 방지 대책 이행 - 주변압기 1차측 CVT 설치","2021-06-20 10:00","2021-06-20 18:00","2021-06-20 10:00","2021-06-20 18:00","연속"]
[154,"충북","직할","서안성신진천#2 T/L","2021년 직할 가공송전선로 순시점검 위탁공사","345kV 서안성-신진천#2T/L 정밀점검","2021-06-22 07:30","2021-06-30 18:00","2021-06-22 07:30","2021-06-30 18:00","매일"]
[155,"충북","직할","신중부신진천#1 T/L","345kV 신진천S/S 축소형모자익 대체공사","축소형모자익 대체 관련 조작시험","2021-06-21 10:00","2021-06-21 12:00","취소","취소","연속"]
[156,"충북","직할","서안성신진천#1 T/L","2021년 직할 가공송전선로 순시점검 위탁공사","345kV 서안성-신진천#1T/L 정밀점검","2021-06-12 07:30","2021-06-21 18:00","2021-06-12 07:30","2021-06-21 18:00","매일"]
[157,"충북","직할","신진천S/S #4 M.Tr","345kV 신진천S/S #5M.Tr 증설공사","#5M.Tr 증설분 무부하가압(345kV GIS ~154kV GIS 부싱)","2021-06-26 11:00","2021-06-27 18:00","2021-06-26 09:00","2021-06-27 18:00","연속"]
[158,"충북","직할","신진천S/S #3 M.Tr","345kV 신진천S/S 축소형모자익 대체공사","축소형모자익 대체 관련 조작시험","2021-06-26 09:00","2021-06-26 11:00","취소","취소","연속"]
[159,"충북","직할","신중부신진천#2 T/L","345kV 신진천S/S 축소형모자익 대체공사","축소형모자익 대체 관련 조작시험","2021-06-19 10:00","2021-06-19 12:00","취소","취소","연속"]
[160,"충북","직할","신진천S/S #1 M.Tr","21년 직할 변전협력회사 총액공사","유사고장 방지 대책 이행 - 주변압기 1차측 CVT 설치","2021-06-19 10:00","2021-06-19 18:00","2021-06-19 10:00","2021-06-19 18:00","연속"]
[161,"충북","청주","남청주S/S #1 M.Tr","20-21년 청주전력 변전정비 총액","362kV GIS 하자점검","2021-06-04 09:00","2021-06-04 18:00","2021-06-04 09:00","2021-06-04 18:00","연속"]
[162,"충북","청주","세종남청주#1 T/L","2020-2021년 청주전력지사 송전정비회사 총액공사","1. 항공도장 : No.30(부분도색), 45","2021-06-09 07:00","2021-06-10 18:00","2021-06-09 07:00","2021-06-10 18:00","매일"]
[163,"충북","청주","세종남청주#2 T/L","2020-2021년 청주전력지사 송전정비회사 총액공사","1. 항공도장 : No.30(부분도색), 45 2. 불량애자교체 : No.32, 46","2021-06-11 07:00","2021-06-12 18:00","2021-06-11 07:00","2021-06-12 18:00","매일"]
[164,"충북","청주","남청주S/S #4 M.Tr","20-21년 청주전력 변전정비 총액","3차측 VCB 노후교체","2021-06-14 09:00","2021-06-15 18:00","2021-06-14 09:00","2021-06-15 18:00","연속"]
[165,"충북","청주","신옥천세종#1 T/L","2020-2021년 청주전력지사 송전정비회사 총액공사","1. 항공도장 : No.44, 49, 64, 68, 73(부분도색) 2. 추락방지시설 설치 : No.57, 58","2021-06-11 07:00","2021-06-12 18:00","2021-06-11 07:00","2021-06-12 18:00","매일"]
[166,"충북","청주","신옥천북경남 T/L","20-21년 청주전력 변전정비 총액","72BAY B/F PNL 교체","2021-06-07 09:00","2021-06-10 18:00","2021-06-07 09:00","2021-06-10 18:00","연속"]
[167,"충북","청주","신옥천세종#2 T/L","20-21년 청주전력 변전정비 총액","72BAY B/F PNL 교체","2021-06-07 09:00","2021-06-10 18:00","2021-06-07 09:00","2021-06-10 18:00","연속"]
[168,"충북","충주","신제천S/S #2 M.Tr","20-21년 충주전력지사 변전정비 총액공사","#2M.Tr 1차 CVT 설치 및 1,2차 부싱 절연유 채유","2021-06-23 10:00","2021-06-24 18:00","2021-06-23 10:00","2021-06-24 18:00","연속"]
[169,"충북","충주","신제천S/S #4 M.Tr","신제천S/S #4M.Tr 종합예방진단시스템 구축공사","신제천S/S #4M.Tr 종합예방진단시스템 구축공사","2021-06-22 13:00","2021-06-22 16:00","2021-06-22 13:00","2021-06-22 16:00","연속"]
[170,"충북","충주","신제천S/S #3 M.Tr","신제천S/S #3M.Tr 종합예방진단시스템 구축공사","신제천S/S #3M.Tr 종합예방진단시스템 구축공사","2021-06-22 09:00","2021-06-22 12:00","2021-06-22 09:00","2021-06-22 12:00","연속"]
[171,"대전충남","대전","신계룡S/S #3 M.Tr","신계룡S/S 345kV 76B/F PNL 교체공사","신계룡S/S 345kV 76B/F PNL 교체공사 및 병행작업","2021-06-21 10:00","2021-06-25 18:00","2021-06-21 10:00","2021-06-25 18:00","연속"]
[172,"대전충남","서산","당진T/P CB 7271","21년 장기 미동작 차단기 조작시험","당진화력S/S 765kV #1 Tie.Tr 2차 7271 CB 조작시험","2021-06-22 14:00","2021-06-22 18:00","2021-06-22 14:00","2021-06-22 18:00","연속"]
[173,"대전충남","서산","당진T/P CB 7172","21년 장기 미동작 차단기 조작시험","당진화력S/S 345kV 1호기 1차 7172 CB 조작시험","2021-06-22 10:00","2021-06-22 14:00","2021-06-22 10:00","2021-06-22 14:00","연속"]
[174,"대전충남","서산","당진T/P CB 7171","'21년 서산P/O 345/765kV GIS 점검공사","당진T/P #71TIE Tr 1차 GIS(7171) 정밀점검","2021-06-07 09:00","2021-06-11 18:00","2021-06-07 09:00","2021-06-11 18:00","연속"]
[175,"대전충남","서산","당진T/P CB 7200","'21년 서산P/O 345/765kV GIS 점검공사","당진T/P #1TIE Tr 2차-2호기 1차 GIS(7200) 정밀점검","2021-06-14 09:00","2021-06-18 18:00","2021-06-14 09:00","2021-06-18 18:00","연속"]
[176,"대전충남","서산","북당진현대제철 T/L","345kV GS-EPS분기 T/L 피뢰기 설치공사","345kV GS-EPS분기 T/L 피뢰기 설치","2021-06-07 08:00","2021-06-11 18:00","2021-06-07 08:00","2021-06-11 18:00","매일"]
[177,"대전충남","서산","북당진현대제철 T/L","345kV 신송산분기T/L 건설공사","345kV 현대제철T/L 본선로 구성","2021-06-30 09:00","2021-07-09 18:00","2021-06-30 09:00","2021-07-09 18:00","연속"]
[178,"대전충남","서산","신당진개폐소현대제철 T/L","345kV 신송산분기T/L 건설공사","345kV 현대제철T/L 본선로 구성","2021-06-20 09:00","2021-06-29 18:00","2021-06-20 09:00","2021-06-29 18:00","연속"]
[179,"대전충남","서산","신서산아산#1 T/L","154kV 합덕-송악T/L 피뢰기 설치공사","154kV 합덕-송악T/L 피뢰기 설치 - No.2~28(27기) - 4회선 병가철탑 안전이격확보 [병행] 서산전력지사 송전운영부 154kV 합덕-송악 T/L 정밀점검 4회선 병가철탑","2021-06-14 08:00","2021-06-17 18:00","취소","취소","매일"]
[180,"대전충남","서산","신서산태안TP#2 T/L","345kV 신서산-태안화력T/L 항공장애표시구 설치 공사","345kV 신서산-태안화력T/L 항공장애표시구 설치 공사","2021-06-17 08:00","2021-06-17 18:00","취소","취소","연속"]
[181,"대전충남","서산","신서산S/S #4 Sh.R CB","21년 장기 미동작 차단기 조작시험","신서산S/S 345KV #4 Sh.R 7779 CB 조작시험","2021-06-15 10:00","2021-06-15 14:00","2021-06-15 10:00","2021-06-15 14:00","연속"]
[182,"대전충남","서산","신서산S/S #5 Sh.R CB","21년 장기 미동작 차단기 조작시험","신서산S/S 345KV #5 Sh.R 7979 CB 조작시험","2021-06-15 14:00","2021-06-15 18:00","2021-06-15 14:00","2021-06-15 18:00","연속"]
[183,"대전충남","서산","태안T/P 345kV #76 BUS","21년 서산P/O 변전협력회사 총액공사","태안T/P 345kV #76BUS 모선보호반 대체","2021-06-21 09:00","2021-06-25 18:00","취소","취소","연속"]
[184,"대전충남","천안","신온양S/S #3 M.Tr","신온양S/S 345kV #3M.Tr 1,2차 부싱절연유 채유","신온양S/S 345kV #3M.Tr 1,2차 부싱절연유 채유","2021-06-21 09:00","2021-06-21 18:00","2021-06-21 09:00","2021-06-21 18:00","연속"]
[185,"대전충남","천안","신탕정S/S #4 M.Tr","신탕정S/S 345kV #4 M.Tr 누유개소 보수 및 초기점검","신탕정S/S 345kV #4 M.Tr 누유개소 보수 및 초기점검","2021-06-21 09:00","2021-06-25 18:00","2021-06-21 09:00","2021-06-25 18:00","연속"]
[186,"대전충남","천안","신탕정S/S #2 M.Tr","신탕정S/S 345kV #2M.Tr 정밀점검 ","신탕정S/S 345kV #2M.Tr 정밀점검 ","2021-06-01 09:00","2021-06-18 18:00","2021-06-01 09:00","2021-06-18 18:00","연속"]
[187,"대전충남","청양","아산보령TP#2 T/L","보령T/P 아산-보령화력#2T/L 부싱 가스 누기개소 정비","보령T/P 아산-보령화력#2T/L 부싱 가스 누기개소 정비","2021-06-14 09:00","2021-06-18 18:00","2021-06-14 09:00","2021-06-18 18:00","연속"]
[188,"대전충남","청양","청양보령TP#1 T/L","보령T/P 청양-보령화력#1T/L 부싱 가스 누기개소 정비","보령T/P 청양-보령화력#1T/L 부싱 가스 누기개소 정비","2021-06-07 09:00","2021-06-11 18:00","2021-06-07 09:00","2021-06-11 18:00","연속"]
[189,"대전충남","청양","청양S/S 345kV SEC CB 75760","2021년 청양P/O 362kV GIS 정밀점검공사","○ 362kV GIS(75-76-0) 정밀점검","2021-06-21 09:00","2021-06-25 18:00","2021-06-21 09:00","2021-06-25 18:00","연속"]
[190,"대전충남","청양","청양S/S 345kV SEC CB 70710","2021년 청양P/O 362kV GIS 정밀점검공사","○ 362kV GIS(70-71-0) 정밀점검","2021-06-14 09:00","2021-06-18 18:00","2021-06-14 09:00","2021-06-18 18:00","연속"]
[191,"대전충남","청양","청양S/S CB 7600","2021년 청양P/O 362kV GIS 정밀점검공사","○ 362kV GIS(7600) 정밀점검","2021-06-07 09:00","2021-06-11 18:00","2021-06-07 09:00","2021-06-11 18:00","연속"]
[192,"전북","군산","군산S/S CB 7600","군산S/S 345kV 차단기 보통점검 (7600 CB)","군산S/S 7600 CB 보통점검","2021-06-09 09:00","2021-06-09 18:00","2021-06-09 09:00","2021-06-09 18:00","연속"]
[193,"전북","군산","청양군산#1 T/L","청양-군산T/L 추락방지시설설치공사","- 1~26호간 추락방지시설설치","2021-06-21 07:00","2021-06-28 18:00","2021-06-21 07:00","2021-06-28 18:00","연속"]
[194,"전북","군산","청양군산#2 T/L","청양-군산T/L 추락방지시설설치공사","- 1~26호간 추락방지시설설치","2021-06-29 07:00","2021-07-06 18:00","2021-06-29 07:00","2021-07-06 18:00","연속"]
[195,"전북","군산","군산S/S CB 7672","군산S/S 345kV 차단기 보통점검 (7672 CB)","군산S/S 7672 CB 보통점검","2021-06-08 09:00","2021-06-08 18:00","2021-06-08 09:00","2021-06-08 18:00","연속"]
[196,"전북","군산","새만금S/S #1 Sh.R CB","군산P/O 조상설비 점검공사","- 345kV #1Sh.R 하자점검","2021-06-10 09:00","2021-06-11 18:00","2021-06-10 09:00","2021-06-11 18:00","연속"]
[197,"전북","김제","신김제S/S CB 7371","2021년 김제P/O 345kV 차단기 정밀점검공사(7371 CB)","7371 차단기 정밀점검 (기기 단독휴전)","2021-06-21 10:00","2021-06-25 18:00","2021-06-21 10:00","2021-06-25 18:00","연속"]
[198,"전북","김제","신김제S/S 345kV #2 BUS","2021년 김제P/O 345kV 차단기 정밀점검공사(시험가압)","7172, 7672, #3M.Tr 시험가압","2021-06-04 16:00","2021-06-04 18:00","2021-06-04 16:00","2021-06-04 18:00","연속"]
[199,"전북","김제","신김제S/S 345kV #1 BUS","2021년 김제P/O 345kV 차단기 정밀점검공사(시험가압)","7371 차단기 무부하 시험가압","2021-06-25 16:00","2021-06-25 18:00","2021-06-25 16:00","2021-06-25 18:00","연속"]
[200,"전북","김제","군산신김제#1 T/L","2021년 김제P/O 345kV 차단기 정밀점검공사(시험가압)","7371 차단기 무부하 시험가압","2021-06-25 16:00","2021-06-25 18:00","2021-06-25 16:00","2021-06-25 18:00","연속"]
[201,"전북","김제","신김제S/S CB 7372","2021년 김제P/O 345kV 차단기 정밀점검공사 (7372 CB)","7372 차단기 정밀점검","2021-06-07 10:00","2021-06-11 18:00","2021-06-07 10:00","2021-06-11 18:00","연속"]
[202,"전북","김제","군산신김제#1 T/L","2021년 김제P/O 345kV 차단기 정밀점검공사(시험가압)","7372 차단기 무부하 시험가압","2021-06-11 16:00","2021-06-11 18:00","2021-06-11 16:00","2021-06-11 18:00","연속"]
[203,"전북","김제","신김제S/S 345kV #2 BUS","2021년 김제P/O 345kV 차단기 정밀점검공사(시험가압)","7372 차단기 무부하 시험가압","2021-06-11 16:00","2021-06-11 18:00","2021-06-11 16:00","2021-06-11 18:00","연속"]
[204,"전북","김제","신김제S/S CB 7172","2021년 김제P/O 345kV 차단기 정밀점검공사 (7172 CB)","7172 차단기 정밀점검 (기기 단독휴전)","2021-06-14 10:00","2021-06-18 18:00","2021-06-14 10:00","2021-06-18 18:00","연속"]
[205,"전북","김제","군산신김제#1 T/L","2021년 김제P/O 345kV 차단기 정밀점검공사(시험가압)","7172, 7672 차단기 및 #3M.Tr 무부하 시험가압","2021-06-04 16:00","2021-06-04 18:00","2021-06-04 16:00","2021-06-04 18:00","연속"]
[206,"전북","김제","군산신김제#2 T/L","2021년 김제P/O 345kV 차단기 정밀점검공사(시험가압)","7172 차단기 무부하 시험가압","2021-06-18 16:00","2021-06-18 18:00","2021-06-18 16:00","2021-06-18 18:00","연속"]
[207,"전북","직할","신옥천무주양수 T/L","362kV GIS 개선사항 제작사 합동점검","362kV GIS 개선사항 제작사 합동점검","2021-06-02 09:00","2021-06-02 18:00","2021-06-02 09:00","2021-06-02 18:00","연속"]
[208,"전북","직할","북경남무주양수 T/L","362kV GIS 개선사항 제작사 합동점검","362kV GIS 개선사항 제작사 합동점검","2021-06-01 09:00","2021-06-01 18:00","2021-06-01 09:00","2021-06-01 18:00","연속"]
[209,"전북","직할","신남원한빛NP#2 T/L","345kV 신남원-한빛T/L 항공장애표시도장","No32~39호","2021-06-07 09:00","2021-06-18 18:00","취소","취소","연속"]
[210,"전북","직할","신남원S/S #1 M.Tr","2021년도 변전소 종합예방진단시스템 구축공사(규격 실측)","2021년도 변전소 종합예방진단시스템 구축 - 부싱 시험탭 분리 및 규격 실측 - OLTC센서 설치가능여부 확인 및 센서부 실측","2021-06-07 10:00","2021-06-07 14:00","2021-06-07 10:00","2021-06-07 14:00","연속"]
[211,"광주전남","강진","신화순신강진#1 T/L"," 신화순S/S 345kV #1Sh.R 증설공사","- 345kV #1Sh.R x 1bank 설치 - 362kV GIS 3CB 설치 - 기타부대공사 1식","2021-06-01 08:00","2021-06-02 18:00","2021-06-01 08:00","2021-06-02 18:00","연속"]
[212,"광주전남","강진","신강진S/S #4 M.Tr","2020-2021년 강진전력지사 변전협력회사 총액공사","신강진S/S #4M.Tr 보통점검 신강진S/S #4M.Tr 2차 LA A,B,C보통점검 ※ 비상시 즉시가압 가능","2021-06-14 10:00","2021-06-15 18:00","2021-06-14 10:00","2021-06-15 18:00","연속"]
[213,"광주전남","광주","신남원신광주#1 T/L","21년 광주정비회사 총액공사 (345 GIS 보통점검,CVT하자)","신광주S/S 신남원-신광주#1T/L (7471CB) 보통 및 CVT 하자점검 - 비상시 즉시 가압 불가","2021-06-01 09:00","2021-06-01 18:00","2021-06-01 09:00","2021-06-01 18:00","연속"]
[214,"광주전남","목포","한빛#2N/P CB 7600","2020-21년 목포전력지사 변전정비회사 총액공사","변전설비 기기점검 비상 시 20분내 가압 가능","2021-06-22 09:00","2021-06-22 18:00","2021-06-22 09:00","2021-06-22 18:00","연속"]
[215,"광주전남","목포","한빛#2N/P CB 7771","2020-21년 목포전력지사 변전정비회사 총액공사","변전설비 기기점검 비상 시 20분이내 가압 가능","2021-06-23 09:00","2021-06-23 18:00","2021-06-23 09:00","2021-06-23 18:00","연속"]
[216,"광주전남","목포","신남원한빛NP#1 T/L","2021년 직할 가공송전 순시점검 위탁공사","345kV 신남원-한빛NP #1T/L 정밀점검","2021-06-22 09:00","2021-06-23 18:00","취소","취소","매일"]
[217,"광주전남","목포","한빛#2N/P CB 7671","2020-21년 목포전력지사 변전정비회사 총액공사","변전설비 기기점검 비상 시 20분내 가압 가능","2021-06-21 09:00","2021-06-21 18:00","2021-06-21 09:00","2021-06-21 18:00","연속"]
[218,"광주전남","목포","한빛#3N/P CB 7B00","2021년 목포전력지사 개폐장치 보통점검 및 전자변 교체공사","2021년 목포전력지사 개폐장치 보통점검 및 전자변 교체공사(비상시 즉시 가압 불가)","2021-06-08 10:00","2021-06-08 18:00","2021-06-08 10:00","2021-06-08 18:00","연속"]
[219,"광주전남","목포","한빛#3N/P CB 7B71","2021년 목포전력지사 개폐장치 보통점검 및 전자변 교체공사","2021년 목포전력지사 개폐장치 보통점검 및 전자변 교체공사(비상시 즉시 가압 불가)","2021-06-09 10:00","2021-06-09 18:00","2021-06-09 10:00","2021-06-09 18:00","연속"]
[220,"광주전남","순천","광양S/S #3 M.Tr","#3M.Tr 1,2차 부싱절연유 채유","#3M.Tr 1,2차 부싱절연유 채유 / 바상시 즉시가압 가능","2021-06-22 09:00","2021-06-22 18:00","2021-06-22 09:00","2021-06-22 18:00","연속"]
[221,"광주전남","순천","광양광양CC#2 T/L","광양-광양복합 #2T/L 정밀점검","21년 가공송전 순시점검 위탁공사 광양-광양복합 #2T/L 정밀점검 및 절연저항측정","2021-06-14 09:00","2021-06-18 18:00","2021-06-14 09:00","2021-06-18 18:00","매일"]
[222,"광주전남","순천","광양S/S 345kV SEC CB 70710","20-21년 순천전력지사 변전협력회사 총액공사","광양 70-71-0 SEC GIS 초기점검 비상시 즉시가압 가능","2021-06-03 09:00","2021-06-03 18:00","2021-06-03 09:00","2021-06-03 18:00","연속"]
[223,"광주전남","순천","광양S/S 345kV SEC CB 75760","20-21년 순천전력지사 변전협력회사 총액공사","광양 75-76-0 SEC GIS 초기점검 비상시 즉시가압 가능","2021-06-04 09:00","2021-06-04 18:00","2021-06-04 09:00","2021-06-04 18:00","연속"]
[224,"광주전남","순천","광양S/S #1 M.Tr","#1M.Tr 1,2차 부싱절연유 채유","#1M.Tr 1,2차 부싱절연유 채유 / 바상시 즉시가압 가능","2021-06-08 09:00","2021-06-08 18:00","2021-06-08 09:00","2021-06-08 18:00","연속"]
[225,"광주전남","순천","광양광양제철#1 T/L","광양-광양복합 #1T/L 정밀점검 4회선 병가구간 휴전","21년 가공송전 순시점검 위탁공사 광양-광양복합 #1T/L 정밀점검 및 절연저항측정","2021-06-07 08:00","2021-06-10 18:00","2021-06-07 08:00","2021-06-10 18:00","매일"]
[226,"광주전남","순천","광양광양CC#1 T/L","광양-광양복합 #1T/L 정밀점검","21년 가공송전 순시점검 위탁공사 광양-광양복합 #1T/L 정밀점검 및 절연저항측정","2021-06-07 09:00","2021-06-11 18:00","2021-06-07 09:00","2021-06-11 18:00","매일"]
[227,"광주전남","순천","광양광양제철#2 T/L","광양-광양복합 #2T/L 정밀점검 4회선 병가구간 휴전","21년 가공송전 순시점검 위탁공사 광양-광양복합 #2T/L 정밀점검 및 절연저항측정","2021-06-14 08:00","2021-06-17 18:00","2021-06-14 08:00","2021-06-17 18:00","매일"]
[228,"광주전남","순천","광양S/S #2 M.Tr","#2M.Tr 1,2차 부싱절연유 채유","#2M.Tr 1,2차 부싱절연유 채유 / 바상시 즉시가압 가능","2021-06-15 09:00","2021-06-15 18:00","2021-06-15 09:00","2021-06-15 18:00","연속"]
[229,"광주전남","순천","여수T/P #3 Tie-Tr","여수화력S/Y 345kV #4M.Tr 및 S.W 증설공사","- 여수화력S/Y 345kV #73Bay B/F PNL 개조","2021-06-08 09:00","2021-06-11 18:00","2021-06-08 09:00","2021-06-11 18:00","연속"]
[230,"광주전남","순천","광양여수TP T/L","345kV #4M.Tr 및 S.W 증설공사","- 345kV #4M.Tr 1차 GIS 증설","2021-06-21 09:00","2021-06-24 18:00","2021-06-21 09:00","2021-06-24 18:00","연속"]
[231,"광주전남","순천","율촌C/C CB 7100","2021년 순천전력지사 362, 170kV GIS 보통 및 정밀점검공사","광양-율촌CCT/L - GTG TIE GIS 7100CB 전자변 교체 비상시 즉시가압 불가","2021-06-03 09:00","2021-06-03 18:00","2021-06-03 09:00","2021-06-03 18:00","연속"]
[232,"광주전남","순천","율촌C/C CB 7271","2021년 순천전력지사 362, 170kV GIS 보통 및 정밀점검공사","율촌CC-여수TPT/L GIS 7271CB 전자변 교체 비상시 즉시가압 불가","2021-06-17 09:00","2021-06-17 18:00","2021-06-17 09:00","2021-06-17 18:00","연속"]
[233,"광주전남","순천","율촌C/C CB 7200","2021년 순천전력지사 362, 170kV GIS 보통 및 정밀점검공사","율촌복합S/Y 345kV 율촌CC-여수TP T/L - STG GIS 전자변 교체 비상시 즉시가압 불가","2021-06-18 09:00","2021-06-18 18:00","2021-06-18 09:00","2021-06-18 18:00","연속"]
[234,"광주전남","순천","율촌C/C CB 7171","2021년 순천전력지사 362, 170kV GIS 보통 및 정밀점검공사","광양-율촌CCT/L GIS 7171CB 전자변 교체 비상시 즉시가압 불가","2021-06-02 09:00","2021-06-02 18:00","2021-06-02 09:00","2021-06-02 18:00","연속"]
[235,"대구","달성","북경남고령#2 T/L","20-21년도 달성전력지사 가공송전정비회사 총액공사","항공장애표시구 설치(No.41~42, 44~45, 46~47, 56~59)","2021-06-21 08:00","2021-06-23 18:00","2021-06-21 08:00","2021-06-23 18:00","매일"]
[236,"대구","달성","대구S/S #1 M.Tr","대구S/S 60-65 모선보호반 대체","대구S/S 60-65 모선보호반 대체","2021-06-30 11:30","2021-06-30 12:00","2021-06-30 11:30","2021-06-30 12:00","연속"]
[237,"대구","칠곡","신포항북대구 T/L","345kV 북대구S/S #4M.Tr 증설공사","362kV GIS 1CB 설치","2021-06-22 09:00","2021-07-09 18:00","2021-06-22 09:00","2021-07-09 18:00","연속"]
[238,"대구","칠곡","북대구S/S #1 M.Tr","북대구S/S M.Tr 부싱절연유 채유, 7372 장기미동작 점검","북대구S/S M.Tr 부싱절연유 채유, 7372 장기미동작 점검","2021-06-11 09:30","2021-06-11 18:00","2021-06-11 09:30","2021-06-11 18:00","연속"]
[239,"대구","칠곡","북대구S/S #2 M.Tr","북대구S/S 345kV M.Tr 부싱절연유 채유, GIS장기미동작 점검","북대구S/S 345kV M.Tr 부싱절연유 채유, GIS장기미동작 점검","2021-06-10 09:30","2021-06-10 18:00","2021-06-10 09:30","2021-06-10 18:00","연속"]
[240,"대구","칠곡","북대구S/S 345kV #1 BUS","345kV 북대구S/S #4M.Tr 증설공사","362kV GIS 1CB 설치","2021-06-22 09:00","2021-07-09 18:00","2021-06-22 09:00","2021-07-09 18:00","연속"]
[241,"대구","칠곡","서대구S/S #2 M.Tr","서대구S/S #2M.Tr 부싱절연유 채유, 1,2차 CB 보통점검","서대구S/S #2M.Tr 부싱절연유 채유, 1,2차 CB 보통점검","2021-06-01 09:30","2021-06-01 18:00","2021-06-01 09:30","2021-06-01 18:00","연속"]
[242,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S 제어동 건축공사","제어동 작업 관련 안전이격 확보","2021-06-14 09:00","2021-06-18 18:00","2021-06-14 09:00","2021-06-18 18:00","연속"]
[243,"대구","칠곡","서대구고령#1 T/L","서대구S/S 서대구-고령 #1TL LA 보통점검","서대구S/S 서대구-고령 #1TL LA 보통점검","2021-06-18 09:30","2021-06-18 13:00","취소","취소","연속"]
[244,"대구","칠곡","북경남서대구#2 T/L","서대구S/S 345kV GCB 장기미동작 점검","서대구S/S 345kV GCB 장기미동작 점검","2021-06-18 13:00","2021-06-18 18:00","취소","취소","연속"]
[245,"대구","칠곡","서대구S/S #3 M.Tr","서대구S/S #3M.Tr 보통점검, 6344GCB 장기미동작 점검","서대구S/S #3M.Tr 보통점검, 6344GCB 장기미동작 점검","2021-06-25 09:30","2021-06-25 18:00","2021-06-25 09:30","2021-06-25 18:00","연속"]
[246,"대구","칠곡","서대구S/S CB 7872","서대구S/S 345kV GCB 장기미동작 점검","서대구S/S 345kV GCB 장기미동작 점검","2021-06-10 09:30","2021-06-10 18:00","2021-06-10 09:30","2021-06-10 18:00","연속"]
[247,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S #1M.Tr 보통점검, OFU 오일,필터교체","서대구S/S #1M.Tr 보통점검, OFU 오일,필터교체","2021-06-30 09:30","2021-06-30 18:00","2021-06-30 09:30","2021-06-30 18:00","연속"]
[248,"대구","포항","신포항신월성NP#3 T/L","345kV 영포 외 9개 T/L 점퍼지지애자설치 등 송전정비공사","○ 전력선교체 및 폴리머점퍼지지애자 설치 - 전력선 설치/철거 : ACSR 480㎟*4B*2C, 14.645C－km - 가공지선 설치/철거 : ACSR 120㎟ 7.623C－km - 점퍼지지애자 설치 : 191기, 585SET (345kV : 114기, 154kV : 77기)","2021-06-01 08:00","2021-06-05 18:00","2021-06-01 08:00","2021-06-05 18:00","연속"]
[249,"대구","포항","신포항신월성NP#4 T/L","345kV 영포 외 9개 T/L 점퍼지지애자설치 등 송전정비공사","○ 전력선교체 및 폴리머점퍼지지애자 설치 - 전력선 설치/철거 : ACSR 480㎟*4B*2C, 14.645C－km - 가공지선 설치/철거 : ACSR 120㎟ 7.623C－km - 점퍼지지애자 설치 : 191기, 585SET (345kV : 114기, 154kV : 77기)","2021-06-07 08:00","2021-06-11 18:00","2021-06-07 08:00","2021-06-11 18:00","연속"]
[250,"대구","포항","신포항S/S CB 7172","신포항S/S 7172 CB 전자변 교체작업","신포항S/S 7172 CB 전자변 교체작업","2021-06-08 09:00","2021-06-08 18:00","2021-06-08 09:00","2021-06-08 18:00","연속"]
[251,"대구","포항","신포항S/S CB 7271","신포항S/S 7271 CB 전자변 교체작업","신포항S/S 7271 CB 전자변 교체작업","2021-06-09 09:00","2021-06-09 18:00","2021-06-09 09:00","2021-06-09 18:00","연속"]
[252,"대구","포항","신포항S/S CB 7372","신포항S/S 7372 CB 전자변 교체작업","신포항S/S 7372 CB 전자변 교체작업","2021-06-10 09:00","2021-06-11 18:00","2021-06-10 09:00","2021-06-11 18:00","연속"]
[253,"대구","포항","신포항S/S CB 7200","신포항S/S 7200 CB 전자변 교체작업","신포항S/S 7200 CB 전자변 교체작업","2021-06-14 09:00","2021-06-14 18:00","2021-06-14 09:00","2021-06-14 18:00","연속"]
[254,"대구","포항","신포항S/S CB 7471","신포항S/S 7471CB 전자변 교체작업","신포항S/S 7471 CB 전자변 교체작업","2021-06-15 09:00","2021-06-16 18:00","2021-06-15 09:00","2021-06-16 18:00","연속"]
[255,"대구","포항","신포항S/S CB 7400","신포항S/S 7400CB 전자변 교체작업","신포항S/S 7400 CB 전자변 교체작업","2021-06-17 09:00","2021-06-18 18:00","2021-06-17 09:00","2021-06-18 18:00","연속"]
[256,"대구","포항","신포항신영일 T/L","2020~21년 포항전력지사 가공송전 협력회사 총액공사","345kV 신포항-신영일T/L 30~33호 스페이서 댐퍼 점검","2021-06-21 08:00","2021-06-21 18:00","2021-06-21 08:00","2021-06-21 18:00","연속"]
[257,"대구","포항","신포항S/S CB 7571","신포항S/S 7571CB 전자변 교체작업","신포항S/S 7571 CB 전자변 교체작업","2021-06-22 09:00","2021-06-22 18:00","2021-06-22 09:00","2021-06-22 18:00","연속"]
[258,"대구","포항","신포항S/S CB 7500","신포항S/S 7500CB 전자변 교체작업","신포항S/S 7500 CB 전자변 교체작업","2021-06-23 09:00","2021-06-23 18:00","2021-06-23 09:00","2021-06-23 18:00","연속"]
[259,"대구","포항","신포항S/S CB 7572","신포항S/S 7572CB 전자변 교체작업","신포항S/S 7572 CB 전자변 교체작업","2021-06-24 09:00","2021-06-24 18:00","2021-06-24 09:00","2021-06-24 18:00","연속"]
[260,"대구","포항","신포항S/S CB 7671","신포항S/S 7671CB 전자변 교체작업","신포항S/S 7671CB 전자변 교체작업","2021-06-25 09:00","2021-06-25 18:00","2021-06-25 09:00","2021-06-25 18:00","연속"]
[261,"대구","포항","신포항S/S CB 7771","신포항S/S 7771CB 전자변 교체작업","신포항S/S 7771CB 전자변 교체작업","2021-06-28 09:00","2021-06-28 18:00","2021-06-28 09:00","2021-06-28 18:00","연속"]
[262,"대구","포항","신포항S/S CB 7700","신포항S/S 7700CB 전자변 교체작업","신포항S/S 7700CB 전자변 교체작업","2021-06-29 09:00","2021-06-29 18:00","2021-06-29 09:00","2021-06-29 18:00","연속"]
[263,"대구","포항","신포항S/S CB 7772","신포항S/S 7772CB 전자변 교체작업","신포항S/S 7772CB 전자변 교체작업","2021-06-30 09:00","2021-06-30 18:00","2021-06-30 09:00","2021-06-30 18:00","연속"]
[264,"대구","포항","신포항S/S CB 7472","신포항S/S 7472CB 전자변 교체작업","신포항S/S 7472 CB 전자변 교체작업","2021-06-01 09:00","2021-06-01 18:00","2021-06-01 09:00","2021-06-01 18:00","연속"]
[265,"대구","포항","울주월성NP#2 T/L","345kV 영포 외 9개 T/L 점퍼지지애자설치 등 송전정비공사","○ 전력선교체 및 폴리머점퍼지지애자 설치 - 전력선 설치/철거 : ACSR 480㎟*4B*2C, 14.645C－km - 가공지선 설치/철거 : ACSR 120㎟ 7.623C－km - 점퍼지지애자 설치 : 191기, 585SET (345kV : 114기, 154kV : 77기)","2021-06-07 08:00","2021-06-11 18:00","2021-06-07 08:00","2021-06-11 18:00","연속"]
[266,"대구","포항","월성N/P CB 7572","월성S/Y #3MO.Tr C상 GIB 교체","월성S/Y #3MO.Tr C상 GIB 교체","2021-06-01 09:00","2021-06-10 18:00","취소","취소","연속"]
[267,"대구","포항","월성N/P CB 7500","월성S/Y #3MO.Tr C상 GIB 교체","월성S/Y #3MO.Tr C상 GIB 교체","2021-06-01 09:00","2021-06-10 18:00","취소","취소","연속"]
[268,"대구","포항","울주월성NP#1 T/L","345kV 영포 외 9개 T/L 점퍼지지애자설치 등 송전정비공사","○ 전력선교체 및 폴리머점퍼지지애자 설치 - 전력선 설치/철거 : ACSR 480㎟*4B*2C, 14.645C－km - 가공지선 설치/철거 : ACSR 120㎟ 7.623C－km - 점퍼지지애자 설치 : 191기, 585SET (345kV : 114기, 154kV : 77기)","2021-06-01 08:00","2021-06-05 18:00","2021-06-01 08:00","2021-06-05 18:00","연속"]
[269,"대구","포항","월성N/P CB 7672","월성S/Y 7672 GIS 보통점검","월성S/Y 7672 GIS 보통점검","2021-06-15 09:00","2021-06-15 18:00","취소","취소","연속"]
[270,"대구","포항","월성N/P CB 7600","월성S/Y 7600 GIS 보통점검","월성S/Y 7600 GIS 보통점검","2021-06-14 09:00","2021-06-14 18:00","취소","취소","연속"]
[271,"경북","영주","신영주S/S #3 M.Tr","신영주S/S 154kV 옥외철구설비 현대화공사","154kV 옥외철구설비 부하전환(→GIS)","2021-06-07 08:00","2021-06-11 18:00","2021-06-07 08:00","2021-06-11 18:00","연속"]
[272,"경북","영주","신영주S/S STATCOM CB","신영주S/S 345kV STATCOM 점검공사","신영주S/S 345kV STATCOM 점검공사","2021-06-14 09:00","2021-06-25 18:00","2021-06-21 09:00","2021-07-02 18:00","연속"]
[273,"경북","영주","신영주한울NP#2 T/L","345kV 신영주-한울NP2T/L 전선접속개소 전선교체공사","345kV 신영주-한울NP2#2T/L 전선교체공사","2021-06-21 08:00","2021-06-27 18:00","2021-06-17 08:00","2021-06-23 18:00","연속"]
[274,"경북","영주","한울2NP한울3NP#4 T/L","2021년 영주전력지사 가공송전순시점검 위탁공사 정밀점검","2021년 영주전력지사 가공송전순시점검 위탁공사 정밀점검","2021-06-04 09:00","2021-06-04 18:00","2021-06-24 09:00","2021-06-24 18:00","연속"]
[275,"경북","영주","한울2NP한울3NP#3 T/L","2021년 영주전력지사 가공송전순시점검 위탁공사 정밀점검","2021년 영주전력지사 가공송전순시점검 위탁공사 정밀점검","2021-06-03 09:00","2021-06-03 18:00","2021-06-03 09:00","2021-06-03 18:00","연속"]
[276,"경북","영주","신영주한울NP#1 T/L","345kV 신영주-한울NP2T/L 전선접속개소 전선교체공사","345kV 신영주-한울NP2#1T/L 전선교체공사","2021-06-14 08:00","2021-06-20 18:00","2021-06-10 08:00","2021-06-16 18:00","연속"]
[277,"경북","영주","신한울한울#1 T/L","'20-21년 영주전력지사 가공송전협력 총액공사","345kV 신한울-한울연락T/L 철탑보강공사","2021-06-28 09:00","2021-07-06 18:00","2021-06-28 09:00","2021-07-06 18:00","연속"]
[278,"부산울산","동부산","신양산북부산#1 T/L","20-21년 동부산전력지사 송전 정비회사 총액공사","○고정형 폴리머 점퍼지지애자 설치","2021-06-25 08:00","2021-06-26 18:00","2021-06-25 08:00","2021-06-26 18:00","연속"]
[279,"부산울산","동부산","신양산북부산#2 T/L","신양산S/S 345kV GIS 차단기 동작시험","1.신양산S/S 345kV GIS 차단기 동작시험 2.LA,CVT 하자점검","2021-06-07 09:30","2021-06-08 17:00","2021-06-01 09:30","2021-06-02 17:00","연속"]
[280,"부산울산","북부산","북부산S/S CB 7900","20-21 북부산전력지사 변전총액공사","북부산S/S 345kV #4Sh.R 7900,7972,7A77 차단기 동작시험 및 #2Sh.R 보호반 회로개선","2021-06-08 09:00","2021-06-08 18:00","2021-06-08 09:00","2021-06-08 18:00","연속"]
[281,"부산울산","북부산","북부산S/S #4 M.Tr","북부산S/S 345kV 변압기 3차측 현대화 공사","북부산S/S 345kV #4M.Tr 3차측 현대화 공사","2021-06-01 09:00","2021-07-16 18:00","2021-06-01 09:00","2021-07-16 18:00","연속"]
[282,"부산울산","북부산","북부산S/S CB 7972","20-21 북부산전력지사 변전총액공사","북부산S/S 345kV #4Sh.R 7900,7972,7A77 차단기 동작시험 및 #2Sh.R 보호반 회로개선","2021-06-08 09:00","2021-06-08 18:00","2021-06-08 09:00","2021-06-08 18:00","연속"]
[283,"부산울산","북부산","북부산S/S #4 Sh.R CB","20-21 북부산전력지사 변전총액공사","북부산S/S 345kV #4Sh.R 7900,7972,7A77 차단기 동작시험 및 #2Sh.R 보호반 회로개선","2021-06-08 09:00","2021-06-08 18:00","2021-06-08 09:00","2021-06-08 18:00","연속"]
[284,"부산울산","북부산","북부산신울산#2 T/L","2020~2021년 북부산 가공송전정비회사 총액공사","345kV 북부산-신울산T/L 17호 만곡개소 교체공사","2021-06-14 08:00","2021-06-17 18:00","취소","취소","연속"]
[285,"부산울산","북부산","북부산신울산#1 T/L","2020~2021년 북부산 가공송전정비회사 총액공사","345kV 북부산-신울산T/L 17호 만곡개소 교체공사","2021-06-09 08:00","2021-06-12 18:00","취소","취소","연속"]
[286,"부산울산","북부산","북부산S/S Sh.R CB","2021년 북부산PO 345kV 변압기 정밀점검","북부산S/S 345kV #2Sh.R 정밀점검","2021-06-21 09:00","2021-06-25 18:00","취소","취소","연속"]
[287,"부산울산","북부산","북부산S/S 345kV SEC CB 70710","20-21 북부산전력지사 변전 총액공사","북부산S/S 345kV 70-71 BUS-SECTION GIS 보통점검","2021-06-29 10:00","2021-06-29 18:00","2021-06-29 10:00","2021-06-29 18:00","연속"]
[288,"부산울산","북부산","북부산S/S 345kV SEC CB 75760","20-21 북부산전력지사 변전 총액공사","북부산S/S 345kV 75-76 BUS-SECTION GIS 보통점검","2021-06-30 10:00","2021-06-30 18:00","2021-06-30 10:00","2021-06-30 18:00","연속"]
[289,"부산울산","서부산","서부산S/S CB 7571","서부산S/S 345kV 7571 GIS 차단기 동작시험","서부산S/S 345kV 7571 GIS 차단기 동작시험","2021-06-01 09:00","2021-06-01 18:00","취소","취소","연속"]
[290,"부산울산","서부산","서부산S/S CB 7500","서부산S/S 345kV 7500 GIS 차단기 동작시험","서부산S/S 345kV 7500 GIS 차단기 동작시험","2021-06-02 09:00","2021-06-02 18:00","취소","취소","연속"]
[291,"부산울산","울산","동울산월성NP T/L","폴리머지지애자 및 추락방지장치 설치","(태풍 고장개소) 345kV 동울산-월성NP(임시) T/L 66호 - 폴리머지지애자 및 추락방지장치 설치","2021-06-01 08:00","2021-06-02 18:00","2021-06-01 08:00","2021-06-02 18:00","연속"]
[292,"부산울산","울산","동울산신울산 T/L","폴리머지지애자 및 추락방지장치 설치","(태풍 고장개소) 345kV 동울산-신울산(임시) T/L 48,50호 - 폴리머지지애자 및 추락방지장치 설치","2021-06-03 08:00","2021-06-05 18:00","2021-06-03 08:00","2021-06-05 18:00","연속"]
[293,"부산울산","울산","신온산신울산#2 T/L","345kV 신온산S/S 차단기 용량부족 대체공사","71BAY 362kV GIS 대체","2021-06-01 09:00","2021-07-15 18:00","2021-06-01 09:00","2021-07-15 18:00","연속"]
[294,"부산울산","울산","신온산S/S 345kV #1 BUS","345kV 신온산S/S 차단기 용량부족 대체공사","71BAY 362kV GIS 대체","2021-06-01 09:00","2021-06-07 18:00","2021-06-01 09:00","2021-06-08 18:00","연속"]
[295,"부산울산","울산","신온산S/S 345kV #2 BUS","345kV 신온산S/S 차단기 용량부족 대체공사","71BAY 362kV GIS 대체","2021-06-08 09:00","2021-06-14 18:00","취소","취소","연속"]
[296,"부산울산","울산","신온산S/S S-OIL#5 T/L CB","345kV 신온산S/S 차단기 용량부족 대체공사","71BAY 362kV GIS 대체","2021-06-01 09:00","2021-07-15 18:00","2021-06-01 09:00","2021-07-09 18:00","연속"]
[297,"부산울산","울산","신울산S/S #2 M.Tr","신울산S/S 154kV 현대화공사","TR-BUS, 6268DS 철거","2021-06-05 08:30","2021-06-06 17:00","2021-06-05 08:30","2021-06-06 17:00","연속"]
[298,"부산울산","울산","신울산S/S #5 M.Tr","신울산S/S 154kV 현대화공사","TR-BUS 철거","2021-06-01 08:30","2021-06-01 17:00","2021-06-01 08:30","2021-06-02 17:00","연속"]
[299,"부산울산","울산","울주고리NP#2 T/L","20~21년 가공송전 협력회사 총액공사(동부산전력지사)","○ 폴리머 점퍼지지애자 설치(14기)","2021-06-19 08:00","2021-06-27 18:00","2021-06-19 08:00","2021-06-27 18:00","연속"]
[300,"부산울산","울산","울주고리NP#1 T/L","20~21년 가공송전 협력회사 총액공사(동부산전력지사)","○ 폴리머 점퍼지지애자 설치(22기)","2021-06-28 08:00","2021-07-10 18:00","2021-06-28 08:00","2021-07-10 18:00","연속"]
[301,"부산울산","울산","울주월성NP#1 T/L","20-21년 변전정비회사 총액공사","- LA 대체 - 7900, 7971 차단기 동작시험","2021-06-14 09:00","2021-06-14 18:00","취소","취소","연속"]
[302,"경남","직할","신김해신녹산#2 T/L","345kV 신김해-신녹산#2T/L 소도체 이도조정","345kV 신김해-신녹산#2T/L 소도체 이도조정 및 스페이서 교체 (19~20, 21~22)","2021-06-17 07:00","2021-06-18 18:00","2021-06-17 07:00","2021-06-18 18:00","연속"]
[303,"경남","직할","신김해S/S CB 7400","신김해S/S 7400 GIS 정밀점검","신김해S/S 7400 GIS 정밀점검","2021-06-07 09:00","2021-06-11 18:00","2021-06-07 09:00","2021-06-11 18:00","연속"]
[304,"경남","직할","신김해S/S #2 M.Tr","신김해S/S 7400 GIS 정밀점검 시험가압","신김해S/S 7400 GIS 정밀점검 시험가압 (병행)#2M.Tr 부싱 도블측정 및 절연유 채유 / 6244 초기점검 / 3차PT 보통점검","2021-06-07 09:00","2021-06-11 18:00","2021-06-07 09:00","2021-06-11 18:00","연속"]
[305,"경남","직할","신김해북부산#2 T/L","신김해S/S 7472 GIS 정밀점검","신김해S/S 7472 GIS 정밀점검 (시험가압용 선로)","2021-06-04 13:00","2021-06-04 18:00","2021-06-04 13:00","2021-06-04 18:00","연속"]
[306,"경남","직할","신김해S/S 345kV #1 BUS","신김해S/S 345kV CT 집합반 교체공사","신김해S/S 345kV CT 집합반 교체공사","2021-06-30 09:30","2021-06-30 17:30","2021-06-30 09:30","2021-06-30 17:30","연속"]
[307,"경남","직할","신김해S/S 345kV #2 BUS","신김해S/S 345kV CT 집합반 교체공사","신김해S/S 345kV CT 집합반 교체공사","2021-06-29 09:30","2021-06-29 17:30","2021-06-29 09:30","2021-06-29 17:30","연속"]
[308,"경남","직할","신김해S/S 345kV #1 BUS","신김해S/S 345kV CT 집합반 교체공사","신김해S/S 345kV CT 집합반 교체공사","2021-06-28 09:30","2021-06-28 17:30","2021-06-28 09:30","2021-06-28 17:30","연속"]
[309,"경남","직할","신김해S/S #3 M.Tr","신김해S/S #77Bay B/F PNL 교체공사","신김해S/S #77Bay B/F PNL 교체공사","2021-06-21 09:30","2021-06-25 17:30","2021-06-21 09:30","2021-06-25 17:30","연속"]
[310,"경남","직할","신김해신녹산#1 T/L","신김해S/S #77Bay B/F PNL 교체공사","신김해S/S #77Bay B/F PNL 교체공사","2021-06-21 09:30","2021-06-25 17:30","2021-06-21 09:30","2021-06-25 17:30","연속"]
[311,"경남","직할","신김해S/S #2 M.Tr","신김해S/S 7472CB GIS 정밀점검","신김해S/S 7472CB GIS 정밀점검 (시험가압 휴전)","2021-06-04 13:00","2021-06-04 18:00","2021-06-04 13:00","2021-06-04 18:00","연속"]
[312,"경남","직할","창원S/S #3 M.Tr","창원S/S #3M.Tr 하자점검","창원S/S #3M.Tr 하자점검 (병행) 6344 대시포트 누유조치","2021-06-01 09:30","2021-06-03 17:30","2021-06-01 09:30","2021-06-03 17:30","연속"]
[313,"경남","진주","산청P/P CB 7200","산청P/P 의령-산청양수#2T/L-#2M.Tr 1차 (7200)보통점검","산청P/P 의령-산청양수#2T/L-#2M.Tr 1차 CB(7200)보통점검","2021-06-21 10:00","2021-06-21 18:00","2021-06-21 10:00","2021-06-21 18:00","연속"]
[314,"경남","진주","의령산청양수#2 T/L","의령S/S 의령-산청양수#2T/L GIS 보통점검 및 LA대체","의령S/S 의령-산청양수#2T/L GIS 보통점검 및 LA대체 [병행] 산청P/P 의령-산청양수#2T/L LA대체","2021-06-07 10:00","2021-06-07 18:00","2021-06-07 10:00","2021-06-07 18:00","연속"]
[315,"경남","진주","의령S/S #2 M.Tr","의령S/S #2M.Tr 1차 CB(7572) 보통점검","의령S/S #2M.Tr 1차 CB(7572) 보통점검 [병행] #2M.Tr 2,3차 CB 보통점검 및 LA 대체, #2S.Tr 보통점검, #2STR VCB 보통점검, 부싱유 채우","2021-06-14 10:00","2021-06-14 18:00","2021-06-14 10:00","2021-06-14 18:00","연속"]
[316,"경남","통영","신마산삼천포화력#2 T/L","삼천포,신고성S/S 차단기 용량대체공사","송전선로 인출변경 작업","2021-06-28 10:00","2021-07-09 18:00","2021-06-28 10:00","2021-07-09 18:00","연속"]
[317,"경남","통영","삼천포T/P #1 Tie T/L CB (7200,7272)","삼천포,신고성S/S 차단기 용량대체공사","송전선로 인출변경 작업","2021-06-14 10:00","2021-06-25 18:00","2021-06-14 10:00","2021-06-25 18:00","연속"]
[318,"경남","통영","신마산삼천포화력#1 T/L","삼천포,신고성S/S 차단기 용량대체공사","송전선로 인출변경 작업","2021-06-14 10:00","2021-06-25 18:00","2021-06-14 10:00","2021-06-25 18:00","연속"]
[319,"경남","통영","신고성S/S CB 7A72G","삼천포,신고성S/S 차단기 용량대체공사","송전선로 인출변경 작업","2021-06-14 10:00","2021-06-25 18:00","2021-06-14 10:00","2021-06-25 18:00","연속"]
[320,"경남","통영","신고성S/S CB 7A00G","삼천포,신고성S/S 차단기 용량대체공사","송전선로 인출변경 작업","2021-06-14 10:00","2021-06-25 18:00","2021-06-14 10:00","2021-06-25 18:00","연속"]
[321,"경남","함안","북경남S/S CB 7B00","북경남 345kV #7Sh.R 1차-신옥천T/L TIE GIS 보통점검","북경남 345kV #7Sh.R 1차-신옥천T/L TIE GIS 보통점검(7B00)","2021-06-03 09:30","2021-06-03 17:30","2021-06-03 09:30","2021-06-03 17:30","연속"]
[322,"경남","함안","북경남S/S CB 7900","북경남 345kV #6Sh.R 1차-서대구#2T/L GIS 보통점검","북경남 345kV #6Sh.R 1차-서대구#2T/L GIS 7900 보통점검","2021-06-01 09:30","2021-06-01 17:30","2021-06-01 09:30","2021-06-01 17:30","연속"]
[323,"경남","함안","북경남S/S CB 7B71","북경남 345kV #7Sh.R 1차 GIS 보통점검","북경남 345kV #7Sh.R 1차 GIS 보통점검(7B71)","2021-06-02 09:30","2021-06-02 17:30","2021-06-02 09:30","2021-06-02 17:30","연속"]
[324,"경남","함안","북경남무주양수 T/L","'96년 상반기 이전 국산애자 교체공사","애자련 교체","2021-06-10 08:00","2021-06-11 18:00","2021-06-10 08:00","2021-06-11 18:00","연속"]
[325,"경남","함안","신마산S/S #5 M.Tr","신마산S/S 345kV #5 M.Tr 1차 GIS 하자점검 외","신마산S/S 345kV #5 M.Tr 1차 GIS 하자점검 2차 GCB 조작시험","2021-06-28 09:30","2021-06-28 17:30","2021-06-28 09:30","2021-06-28 17:30","연속"]
[326,"경남","함안","의령신마산#2 T/L","345kV 의령-신마산T/L 전선교체 및 추락방지시설 설치공사","전선교체 : 50~59호간 추락방지시설설치 : 1~59호","2021-06-17 07:00","2021-06-26 18:30","2021-06-17 07:00","2021-06-26 18:30","연속"]
[327,"경남","함안","신마산S/S #1 M.Tr","신마산S/S 345kV #1 M.Tr 1차 GIS 하자점검 외","신마산S/S 345kV #1 M.Tr 1차 GIS 하자점검 2차 GCB 조작시험","2021-06-17 09:30","2021-06-17 17:30","2021-06-17 09:30","2021-06-17 17:30","연속"]
[328,"경남","함안","의령신마산#1 T/L","345kV 의령-신마산T/L 전선교체 및 추락방지시설 설치공사","전선교체 : 50~59호간 추락방지시설설치 : 1~59호","2021-06-07 07:00","2021-06-16 18:30","2021-06-07 07:00","2021-06-16 18:30","연속"]
[329,"경남","함안","신마산S/S CB 7100","신마산S/S 345kV 신김해#2T/L-#1 M.Tr 1차 하자점검","신마산S/S 345kV 345kV 신김해#2T/L-#1 M.Tr 1차 하자점검(7100)","2021-06-16 09:30","2021-06-16 17:30","2021-06-16 09:30","2021-06-16 17:30","연속"]
[330,"부산울산",null,"고리N/P 강압변압기#1 (CB 7671, 7600)","피뢰기 및 애자류 절연코팅 - 조작 차단기 : PCB 7671, 7600  (SAT#1,2)","○ 변압기 전,후단 애자류 절연코팅","2021-06-11 09:00","2021-06-15 18:00","2021-06-11 09:00","2021-06-15 18:00","연속"]
[331,"부산울산",null,"고리N/P 강압변압기#2 (CB 7D71, 7D00)","피뢰기 및 애자류 절연코팅 - 조작 차단기 : PCB 7D71, 7D00  (SAT#3,4)","○ 변압기 전,후단 애자류 절연코팅","2021-06-21 09:00","2021-06-23 18:00","2021-06-21 09:00","2021-06-23 18:00","연속"]
[332,"대구",null,"월성N/P #3호기 주변압기 (CB 7500, 7572)","월성3호기 18차 O/H 중 주변압기 점검 * 조작차단기 : CB 7500, 7572","○ 주변압기 점검","2021-05-31 09:00","2021-06-11 11:00","2021-05-31 09:00","2021-06-11 11:00","연속"]
[333,"대구",null,"월성N/P #3 기동용변압기 (CB 7600, 7672)","월성3호기 18차 O/H 중 기동변압기 점검 * 조작차단기 : CB 7600, 7672","○ 기동용변압기 점검","2021-06-12 09:00","2021-06-20 19:00","2021-06-12 09:00","2021-06-20 19:00","연속"]
[334,"대구",null,"신월성N/P #1호기 주변압기 (CB 7400, 7472) ","신월성 1호기 6차 계획예방정비 #1 소내전원절체시험 *조작차단기 : PCB 7400, 7472","○ 소내전원절체시험시 주변압기 모의 신호에 의한 PCB 개방","2021-06-09 09:00","2021-06-09 18:00","2021-06-15T09:00:00","2021-06-15T16:00:00","연속"]
[335,"경북",null,"한울N/P #3 대기보조변압기 SAT 02N (CB 7600, 7672)","3호기 16차 계획예방정비 - 조작차단기 : PCB 7600, 7672","○ 보호계전기 개체/연동시험","2021-06-14 10:00","2021-06-14 18:00","2021-06-14 10:00","2021-06-14 18:00","연속"]
[336,"경북",null,"한울N/P #3 대기보조변압기 SAT 02M (CB 7500, 7572)","3호기 16차 계획예방정비 - 조작차단기 : PCB 7500, 7572","○ 대기보조변압기 정밀점검","2021-06-15 15:00","2021-06-30 14:00","2021-06-15 15:00","2021-06-30 14:00","연속"]
[337,"경북",null,"한울N/P #3 대기보조변압기 SAT 02M (CB 7500, 7572)","3호기 16차 계획예방정비 - 조작차단기 : PCB 7500, 7572","○ 보호계전기 개체/연동시험","2021-06-29 10:00","2021-06-29 18:00","2021-06-29 10:00","2021-06-29 18:00","연속"]
[338,"경북",null,"한울N/P #4호기 주변압기 (CB 7A00, 7A72)","4호기 MTR/GEN 갑종보호 연동시험 - 조작차단기 : PCB 7A00, 7A72","○ 4호기 계회예방정비관련 ○ 주변압기 / GEN 갑종보호 연동시험","2021-06-17 10:00","2021-07-24 14:00","2021-06-17 10:00","2021-07-24 14:00","연속"]
[339,"경북",null,"한울N/P #5호기 대기보조변압기 (CB 7E00, 7E72)","5호기 12차 계획예방정비 - 조작차단기 : PCB 7E00, 7E72","○ 대기보조변압기 일반점검 ","2021-06-03 09:00","2021-06-11 14:00","2021-06-03 09:00","2021-06-11 14:00","연속"]
[340,"경북",null,"한울N/P #5호기 주변압기 (CB 7D00, 7D72)","5호기 12차 계획예방정비 - 조작차단기 : PCB 7D00, 7D72","○ 소내전원 절체시험","2021-06-14 14:00","2021-06-14 18:00","2021-06-14 14:00","2021-06-14 18:00","연속"]
[341,"전북","김제","신김제S/S #1 M.Tr","7172 차단기 무부하 시험가압","7172 차단기 무부하 시험가압","2021-06-18 16:00","2021-06-18 18:00","2021-06-18 16:00","2021-06-18 18:00","연속"]
[342,"부산울산",null,"신온산S/S #4 M.Tr","#70 BUS 임시 End Cover부 시험가압","#70 BUS 임시 End Cover부 시험가압","2021-06-07 18:00","2021-06-08 18:00","2021-06-07 18:00","2021-06-08 18:00","연속"]

{"sheet":"154설비","index":2,"n_rows":619,"n_cols":11,"rows_kept":619,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2021년도 6월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","구의광장#2 T/L","'21년 성동P/O 노후 보호배전반 교체공사","구의, 광장S/S 154kV 구의광장#2T/L 보호배전반 노후대체","2021-06-14 10:00","2021-06-17 18:00","2021-06-14 10:00","2021-06-17 18:00","연속"]
[2,"서울","성동","창동S/S CB 6100","모선보호반 계전기 성능개선","모선보호용 86B Reset 회로 및 BF회로 성능개선","2021-06-01 14:00","2021-06-01 17:00","2021-06-01 14:00","2021-06-01 17:00","연속"]
[3,"서울","성동","화양광장 T/L","21년 구리전력지사 가공송전 위탁회사 정밀점검(154kV 화양T/L)","가공송전운영업무 기준에 근거한 위탁회사 정밀점검 154kV 광장-화양T/L No.31~32","2021-06-23 08:00","2021-06-24 18:00","2021-06-23 08:00","2021-06-24 18:00","연속"]
[4,"서울","성동","성동휘경#1 T/L","21년 성동P/O 변전협력회사 총액공사","154kV   보통점검","2021-06-04 09:30","2021-06-04 18:00","2021-06-04 09:30","2021-06-04 18:00","연속"]
[5,"서울","성동","상봉휘경#1 T/L","2021년 성동P/O 변전협력회사 총액공사","154kV   보통점검","2021-06-17 10:00","2021-06-17 18:00","2021-06-17 10:00","2021-06-17 18:00","연속"]
[6,"서울","성동","성동휘경#2 T/L","21년 성동P/O 변전협력회사 총액공사","154kV   보통점검(휘경) 154kV   조작시험, 전자변 교체(성동)","2021-06-03 09:30","2021-06-03 18:00","2021-06-03 09:30","2021-06-03 18:00","연속"]
[7,"서울","중부","상암등촌#2 T/L","상암등촌#2T/L 피뢰기 열화진단","상암등촌#2T/L 피뢰기 열화진단","2021-06-23 10:00","2021-06-23 17:00","2021-06-23 10:00","2021-06-23 17:00","연속"]
[8,"서울","중부","상암등촌#1 T/L","상암등촌#1T/L 피뢰기 열화진단","상암등촌#1T/L 피뢰기 열화진단","2021-06-22 10:00","2021-06-22 17:00","2021-06-22 10:00","2021-06-22 17:00","연속"]
[9,"서울","중부","수색S/S CB 6100","모선보호반 계전기 성능개선","모선보호용 86B Reset 회로 및 BF회로 성능개선","2021-06-01 10:00","2021-06-01 14:00","2021-06-01 10:00","2021-06-01 14:00","연속"]
[10,"서울","중부","용산동빙고 T/L","OF케이블 절연유 채유","용산동빙고T/L OF케이블 절연유분석 시료 채취","2021-06-11 10:00","2021-06-11 14:00","2021-06-11 10:00","2021-06-11 14:00","연속"]
[11,"서울","직할","서대문세종로 T/L","21년 직할 170kV   정밀점검공사","  정밀점검공사","2021-06-28 09:00","2021-06-29 18:00","2021-06-28 09:00","2021-06-29 18:00","연속"]
[12,"남서울","강남","반포S/S CB 6100","170kV   개폐타임,전자변 교체-변전협력","170kV   개폐타임,전자변 교체-변전협력","2021-06-18 10:00","2021-06-18 18:00","2021-06-23 10:00","2021-06-23 18:00","연속"]
[13,"남서울","강남","신양재신사#1 T/L","170kV   점검-변전협력","신사 : 170kV   보통점검 신양재 : 170kV   개폐타임","2021-06-21 10:00","2021-06-21 18:00","2021-06-28 10:00","2021-06-28 18:00","연속"]
[14,"남서울","강남","신양재신사#2 T/L","170kV   점검-변전협력","신사 : 170kV   보통점검 신양재 : 170kV   개폐타임","2021-06-22 10:00","2021-06-22 18:00","2021-06-29 10:00","2021-06-29 18:00","연속"]
[15,"남서울","강남","신양재신사#3 T/L","170kV   점검-변전협력","신사 : 170kV   개폐타임, 전자변 교체 신양재 : 170kV   보통점검","2021-06-23 10:00","2021-06-23 18:00","2021-06-30 10:00","2021-06-30 18:00","연속"]
[16,"남서울","강남","신양재역삼#2 T/L","170kV   조작시험-변전협력","170kV   조작시험-변전협력","2021-06-18 12:00","2021-06-18 15:00","2021-06-18 12:00","2021-06-18 15:00","연속"]
[17,"남서울","강남","신양재역삼#3 T/L","170kV   조작시험-변전협력","170kV   조작시험-변전협력","2021-06-18 15:00","2021-06-18 18:00","2021-06-18 15:00","2021-06-18 18:00","연속"]
[18,"남서울","강남","신양재역삼#1 T/L","170kV   조작시험-변전협력","170kV   조작시험-변전협력","2021-06-18 10:00","2021-06-18 12:00","2021-06-18 10:00","2021-06-18 12:00","연속"]
[19,"남서울","동서울","동서울S/S CB 6100","170kV GCB 조작시험","170kV GCB 조작시험","2021-06-21 09:00","2021-06-21 14:00","2021-06-21 09:00","2021-06-21 14:00","연속"]
[20,"남서울","동서울","동서울S/S SEC CB 66670","170kV GCB 보통점검 및 전자변교체","170kV GCB 보통점검 및 전자변교체","2021-06-04 09:00","2021-06-04 18:00","2021-06-04 09:00","2021-06-04 18:00","연속"]
[21,"남서울","동서울","동서울S/S SEC CB 65660","170kV GCB 보통점검","170kV GCB 보통점검","2021-06-02 09:00","2021-06-02 18:00","2021-06-02 09:00","2021-06-02 18:00","연속"]
[22,"남서울","동서울","동서울S/S SEC CB 60610","170kV GCB 보통점검 및 전자변교체","170kV GCB 보통점검 및 전자변교체","2021-06-01 09:00","2021-06-01 18:00","2021-06-01 09:00","2021-06-01 18:00","연속"]
[23,"남서울","동서울","동서울S/S SEC CB 62670","170kV GCB 조작시험","170kV GCB 조작시험","2021-06-21 14:00","2021-06-21 18:00","2021-06-21 14:00","2021-06-21 18:00","연속"]
[24,"남서울","동서울","동서울S/S SEC CB 61620","170kV GCB보통점검","170kV GCB보통점검","2021-06-03 09:00","2021-06-03 18:00","2021-06-03 09:00","2021-06-03 18:00","연속"]
[25,"남서울","영등포","광명구공#2 T/L","154kV 광명 인출전력구 OF케이블 선종교체공사","OF케이블 선종교체 : 0.25km 및 중간접속 3상, 종단접속 3상","2021-06-01 09:00","2021-07-15 18:00","2021-06-01 09:00","2021-07-15 18:00","연속"]
[26,"남서울","영등포","구공S/S 154kV #66 BUS","구공S/S 154kV 장기사용   교체공사","광명-구공 #2T/L   교체 구#2DS 분리","2021-06-01 09:00","2021-06-04 17:00","취소","취소","연속"]
[27,"남서울","영등포","구공대림#1 T/L","구공S/S 154kV 장기사용   교체공사","광명-구공 #2T/L   교체 #66BUS 무부하가압선로","2021-06-04 09:00","2021-06-04 17:00","취소","취소","연속"]
[28,"남서울","영등포","구공대림#1 T/L","구공S/S 154kV 장기사용   교체공사","광명-구공 #2T/L   교체 #61BUS 무부하 가압선로","2021-06-10 18:00","2021-06-11 18:00","취소","취소","연속"]
[29,"남서울","영등포","구공S/S 154kV #66 BUS","구공S/S 154kV 장기사용   교체공사","광명-구공 #2T/L   교체 #2DS 연결","2021-06-14 09:00","2021-06-18 18:00","취소","취소","연속"]
[30,"남서울","영등포","구공대림#1 T/L","구공S/S 154kV 장기사용   교체공사","광명-구공 #2T/L   교체 #66BUS 무부하 가압선로","2021-06-17 18:00","2021-06-18 18:00","취소","취소","연속"]
[31,"남서울","영등포","구공S/S 154kV #61 BUS","구공S/S 154kV 장기사용   교체공사","광명-구공 #2T/L   교체 #1DS 연결","2021-06-07 09:00","2021-06-11 18:00","취소","취소","연속"]
[32,"남서울","직할","신문래노들 T/L","170kV   조작시험","170kV   조작시험","2021-06-07 10:00","2021-06-07 12:00","2021-06-07 10:00","2021-06-07 12:00","연속"]
[33,"남서울","직할","노들노량진 T/L","170kV   조작시험","170kV   조작시험","2021-06-08 10:00","2021-06-08 15:00","2021-06-08 10:00","2021-06-08 15:00","연속"]
[34,"남서울","직할","신문래노량진 T/L","170kV   조작시험","170kV   조작시험","2021-06-09 10:00","2021-06-09 12:00","2021-06-09 10:00","2021-06-09 12:00","연속"]
[35,"남서울","직할","구공대림#1 T/L","170kV   정밀점검공사_구공대림#1T/L","170kV   정밀점검공사_구공대림#1T/L","2021-06-30 14:00","2021-07-02 18:00","취소","취소","연속"]
[36,"남서울","직할","대림독산 T/L","170kV   정밀점검공사_대림독산T/L","170kV   정밀점검공사_대림독산T/L","2021-06-28 09:00","2021-06-30 14:00","취소","취소","연속"]
[37,"남서울","직할","신림S/S 154kV #1 BUS","170kV   정밀점검공사_#1M.Tr 무부하가압용","170kV   정밀점검공사_#1M.Tr 무부하가압용","2021-06-16 09:00","2021-06-16 14:00","취소","취소","연속"]
[38,"남서울","직할","신림S/S 154kV #1 BUS","170kV   정밀점검공사_#2M.Tr 무부하가압용","170kV   정밀점검공사_#2M.Tr 무부하가압용","2021-06-18 13:00","2021-06-18 18:00","취소","취소","연속"]
[39,"남서울","직할","신림S/S CB 6100","170kV   정밀점검공사","170kV   정밀점검공사 _60-65BUSTIE","2021-06-21 09:00","2021-06-23 14:00","취소","취소","연속"]
[40,"남서울","직할","신림S/S 154kV #1 BUS","170kV   정밀점검공사_6100B/T 무부하가압용","170kV   정밀점검공사_6100B/T 무부하가압용","2021-06-21 09:00","2021-06-23 14:00","취소","취소","연속"]
[41,"남서울","직할","신림봉천 T/L","170kV   정밀점검공사_6100B/T 무부하가압용","170kV   정밀점검공사_6100B/T 무부하가압용","2021-06-23 09:00","2021-06-23 14:00","취소","취소","연속"]
[42,"남서울","직할","신림봉천 T/L","직할 170kV   정밀점검공사","170kV   정밀점검공사","2021-06-07 09:00","2021-06-09 14:00","취소","취소","연속"]
[43,"남서울","직할","사당신림 T/L","170kV   정밀점검공사","170kV   정밀점검공사","2021-06-09 14:00","2021-06-11 18:00","2021-06-09 14:00","2021-06-11 18:00","연속"]
[44,"남서울","직할","신림봉천 T/L","170kV   정밀점검공사_#1M.Tr 무부하가압용","170kV   정밀점검공사_#1M.Tr 무부하가압용","2021-06-16 09:00","2021-06-16 14:00","취소","취소","연속"]
[45,"남서울","직할","신림봉천 T/L","170kV   정밀점검공사_ #2M.Tr 무부하가압용","170kV   정밀점검공사_ #2M.Tr 무부하가압용","2021-06-18 13:00","2021-06-18 18:00","취소","취소","연속"]
[46,"인천","김포","경서양촌#2 T/L","154kV 신경서-왕길 등 3개 T/L C/H 보강공사","가. 대상선로 : 154kV 경서-양촌#2[경서C/H] 나. 시공내용 : 케이블 입상부 난연테이프 시공","2021-06-09 09:00","2021-06-10 18:00","2021-06-09 09:00","2021-06-10 18:00","연속"]
[47,"인천","김포","경서양촌#1 T/L","154kV 신경서-왕길 등 3개 T/L C/H 보강공사","가. 대상선로 : 154kV 경서-양촌#1[경서C/H] 나. 시공내용 : 케이블 입상부 난연테이프 시공","2021-06-07 09:00","2021-06-08 18:00","2021-06-07 09:00","2021-06-08 18:00","연속"]
[48,"인천","김포","신김포장기#1 T/L","장기S/S 154kV 신김포-장기#1T/L   유압블럭 교체작업","장기S/S 154kV 신김포-장기#1T/L   유압블럭 교체작업","2021-06-14 10:00","2021-06-14 18:00","2021-06-14 10:00","2021-06-14 18:00","연속"]
[49,"인천","김포","신김포양곡#1 T/L","신김포,양곡S/S 154kV 신김포-양곡#1T/L   보통점검","신김포,양곡S/S 154kV 신김포-양곡#1T/L   보통점검","2021-06-15 10:00","2021-06-15 18:00","2021-06-15 10:00","2021-06-15 18:00","연속"]
[50,"인천","김포","왕길양촌#2 T/L","154kV 신경서-왕길 등 3개 T/L C/H 보강공사","가. 대상선로 : 154kV 왕길-양촌#2[왕길양촌#1,#2C/H] 나. 시공내용 : 케이블 입상부 난연테이프 시공","2021-06-16 09:00","2021-06-17 18:00","2021-06-16 09:00","2021-06-17 18:00","연속"]
[51,"인천","김포","신경서왕길#1 T/L","154kV 신경서-왕길 등 3개 T/L C/H 보강공사","가. 대상선로 : 154kV 신경서-왕길#1[왕길#1,#2C/H] 나. 시공내용 : 케이블 입상부 난연테이프 시공","2021-06-01 09:00","2021-06-02 18:00","2021-06-01 09:00","2021-06-02 18:00","연속"]
[52,"인천","김포","왕길양촌#1 T/L","154kV 신경서-왕길 등 3개 T/L C/H 보강공사","가. 대상선로 : 154kV 왕길-양촌#1[왕길양촌#1,#2C/H] 나. 시공내용 : 케이블 입상부 난연테이프 시공","2021-06-14 09:00","2021-06-15 18:00","2021-06-14 09:00","2021-06-15 18:00","연속"]
[53,"인천","김포","왕길양촌#1 T/L","154kV 왕길S/S 170kV SW 증설공사","-170kV   50kA 2,000A - 1CCT 증설 -#2BUS 무부하 가압용","2021-06-10 18:00","2021-06-11 18:00","2021-06-10 18:00","2021-06-11 18:00","연속"]
[54,"인천","김포","왕길양촌#1 T/L","154kV 왕길S/S 170kV SW 증설공사","-170kV   50kA 2,000A - 1CCT 증설 -#1BUS 무부하 가압용","2021-06-04 18:00","2021-06-05 18:00","2021-06-04 18:00","2021-06-05 18:00","연속"]
[55,"인천","김포","신경서왕길#2 T/L","154kV 신경서-왕길 등 3개 T/L C/H 보강공사","가. 대상선로 : 154kV 신경서-왕길#2[왕길#1,#2C/H] 나. 시공내용 : 케이블 입상부 난연테이프 시공","2021-06-03 09:00","2021-06-04 18:00","2021-06-03 09:00","2021-06-04 18:00","연속"]
[56,"인천","부평","남동관교#1 T/L","154kV 남동-관교#1T/L 고정형 폴리머 점퍼지지애자 설치","154kV 남동-관교#1T/L 고정형 폴리머 점퍼지지애자 설치, 추락방지시설 설치","2021-06-22 08:00","2021-06-22 13:00","취소","취소","연속"]
[57,"인천","부평","남동관교#2 T/L","154kV 남동-관교#2T/L 고정형 폴리머 점퍼지지애자 설치","154kV 남동-관교#1T/L 고정형 폴리머 점퍼지지애자 설치, 추락방지시설 설치","2021-06-22 13:00","2021-06-22 18:00","취소","취소","연속"]
[58,"인천","부평","남인천학익#2 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2021-06-29 09:00","2021-06-30 18:00","2021-06-29 09:00","2021-06-30 18:00","연속"]
[59,"인천","부평","남인천학익#1 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2021-06-02 09:00","2021-06-03 18:00","2021-06-02 09:00","2021-06-03 18:00","연속"]
[60,"인천","부평","송현포스코CC#2 T/L","154kV 송현포스코CC#2 T/L 피뢰기 설치공사","154kV 송현포스코CC#2 T/L 피뢰기 설치공사","2021-06-15 14:00","2021-06-15 18:00","2021-06-15 14:00","2021-06-15 18:00","연속"]
[61,"인천","부평","신가좌신현#1 T/L","345kV 신가좌S/S 154kV Sh.R   설치공사","170kV  (50kA, 1250A) 1CCT 증설 #66BUS 무부하 가압용","2021-06-18 09:00","2021-06-19 18:00","2021-06-18 09:00","2021-06-19 18:00","연속"]
[62,"인천","부평","신가좌신현#2 T/L","345kV 신가좌S/S 154kV Sh.R   설치공사","154kV Sh.R(60 MVAR) 1BANK 증설 *모선배선용 철구 BEAM 설치시 해당 T/L과 접촉우려","2021-06-21 09:00","2021-06-22 18:00","2021-06-21 09:00","2021-06-22 18:00","연속"]
[63,"인천","부평","신가좌신현#2 T/L","신가좌S/S 신가좌신현#2T/L   조작시험","신가좌S/S 신가좌신현#2T/L   조작시험","2021-06-01 13:00","2021-06-01 18:00","2021-06-01 13:00","2021-06-01 18:00","연속"]
[64,"인천","부평","신가좌신현#1 T/L","신가좌S/S 신가좌신현#1T/l   조작시험","신가좌S/S 신가좌신현#1T/l   조작시험","2021-06-01 09:00","2021-06-01 13:00","2021-06-01 09:00","2021-06-01 13:00","연속"]
[65,"인천","부평","신가좌인천#2 T/L","신가좌S/S 154kV 신가좌인천#2T/L   조작시험","신가좌S/S 154kV 신가좌인천#2T/L   조작시험 -AUX 교체 인천S/S 154kV 신가좌인천#2T/L   조작시험 -전자변 교체","2021-06-25 09:00","2021-06-25 18:00","2021-06-25 09:00","2021-06-25 18:00","연속"]
[66,"인천","부평","신가좌S/S 154kV #61 BUS","345kV 신가좌S/S 154kV Sh.R   설치공사","170kV   (50kA 1250A) 1CCT 증설","2021-06-08 09:00","2021-06-13 18:00","2021-06-08 09:00","2021-06-13 18:00","연속"]
[67,"인천","부평","신가좌부개#2 T/L","신가좌S/S 154kV 신가좌부개#2T/L   보통점검","신가좌S/S 154kV 신가좌부개#2T/L   보통점검 부개S/S 154kV 신가좌부개#2T/L   보통점검","2021-06-30 09:00","2021-06-30 18:00","2021-06-30 09:00","2021-06-30 18:00","연속"]
[68,"인천","부평","신가좌S/S 154kV #66 BUS","345kV 신가좌S/S 154kv Sh.R   설치공사","170kV  (50kA 1250A) 1CCT 증설","2021-06-14 09:00","2021-06-19 18:00","2021-06-14 09:00","2021-06-19 18:00","연속"]
[69,"인천","부평","신가좌신현#1 T/L","345kV 신가좌S/S 154kV Sh.R   설치공사","170kV  (50kA, 1250A) 1CCT 증설 #61BUS 무부하 가압용","2021-06-12 09:00","2021-06-13 18:00","2021-06-12 09:00","2021-06-13 18:00","연속"]
[70,"인천","부평","신현포스코CC#2 T/L","신현S/S 신현포스코CC#2T/L 하자점검","신현S/S 신현포스코CC#2T/L 하자점검","2021-06-29 09:00","2021-06-29 18:00","2021-06-29 09:00","2021-06-29 18:00","연속"]
[71,"인천","부평","신현포스코CC#1 T/L","신현S/S 신현포스코CC#1T/L 하자점검 및 전자변 교체","신현S/S 신현포스코CC#1T/L 하자점검 및 전자변 교체","2021-06-28 09:00","2021-06-28 18:00","2021-06-28 09:00","2021-06-28 18:00","연속"]
[72,"인천","부평","신가좌인천#3 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2021-06-09 09:00","2021-06-10 18:00","2021-06-09 09:00","2021-06-10 18:00","연속"]
[73,"인천","부평","인천남인천#1 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2021-06-22 09:00","2021-06-22 18:00","2021-06-22 09:00","2021-06-22 18:00","연속"]
[74,"인천","부평","인천남인천#2 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2021-06-23 09:00","2021-06-24 18:00","2021-06-23 09:00","2021-06-24 18:00","연속"]
[75,"인천","부평","신가좌인천#1 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2021-06-08 09:00","2021-06-08 18:00","2021-06-08 09:00","2021-06-08 18:00","연속"]
[76,"인천","부평","주안만수#2 T/L","주안S/S 주안만수#2T/L   보통점검","주안S/S 주안만수#2T/L   보통점검","2021-06-03 13:00","2021-06-03 18:00","2021-06-03 13:00","2021-06-03 18:00","연속"]
[77,"인천","부평","주안만수#1 T/L","주안S/S 주안만수#1T/L   보통점검","주안S/S 주안만수#1T/L   보통점검","2021-06-03 09:00","2021-06-03 13:00","2021-06-03 09:00","2021-06-03 13:00","연속"]
[78,"인천","부평","관교주안 T/L","주안S/S 154kV 주안관교T/L   보통점검","주안S/S 154kV 주안관교T/L   보통점검 -전자변 교체","2021-06-11 09:00","2021-06-11 18:00","2021-06-11 09:00","2021-06-11 18:00","연속"]
[79,"인천","부평","신가좌주안#1 T/L","154kV 신가좌-주안#1T/L 피뢰기 설치공사","154kV 신가좌-주안#1T/L 피뢰기 설치공사","2021-06-26 08:00","2021-06-26 18:00","2021-06-26 08:00","2021-06-26 18:00","연속"]
[80,"인천","부평","영종중산 T/L","중산S/S 154kV 영종중산T/L   조작시험","중산S/S 154kV 영종중산T/L   조작시험","2021-06-04 09:00","2021-06-04 18:00","2021-06-04 09:00","2021-06-04 18:00","연속"]
[81,"인천","부평","학익연수#2 T/L","학익S/S 154kV 학익연수#2T/L 보통점검 및 전자변교체","학익S/S 154kV 학익연수#2T/L 보통점검 및 전자변교체","2021-06-18 09:00","2021-06-18 18:00","2021-06-18 09:00","2021-06-18 18:00","연속"]
[82,"인천","부평","학익연수#1 T/L","학익S/S 154kV 학익연수#1T/L   보통점검","학익S/S 154kV 학익연수#1T/L   보통점검 전자변 교체","2021-06-11 09:00","2021-06-11 18:00","2021-06-11 09:00","2021-06-11 18:00","연속"]
[83,"인천","시흥","신시흥남동#1 T/L","남동S/S 154kV 신시흥남동#1 T/L   조작시험","남동S/S 154kV 신시흥남동#1 T/L   조작시험","2021-06-09 14:00","2021-06-09 18:00","2021-06-09 14:00","2021-06-09 18:00","연속"]
[84,"인천","시흥","남동동춘 T/L","남동,동춘S/S 154kV 남동동춘 T/L   조작시험","남동,동춘S/S 154kV 남동동춘 T/L   조작시험","2021-06-09 09:00","2021-06-09 14:00","2021-06-09 09:00","2021-06-09 14:00","연속"]
[85,"인천","시흥","서안양소래 T/L","20-21년 가공송전정비 협력회사 총액공사","ㅇ 성능저하애자 교체공사 - 서안양-소래T/L No.75,75-1,76,86,92","2021-06-09 08:00","2021-06-09 14:00","2021-06-09 08:00","2021-06-09 14:00","매일"]
[86,"인천","시흥","신광명소래 T/L","20-21년 가공송전정비 협력회사 총액공사","ㅇ 피뢰기 설치 - 서서울2-소래T/L No.81~92 (12기)","2021-06-07 09:00","2021-06-07 18:00","2021-06-07 09:00","2021-06-07 18:00","연속"]
[87,"인천","시흥","서서울#2소래 T/L","20-21년 가공송전정비 협력회사 총액공사","ㅇ 성능저하애자 교체공사 - 서서울2-소래T/L No.75,75-1,92 ㅇ 피뢰기 설치 - 서서울2-소래T/L No.81~92 (12기)","2021-06-07 08:00","2021-06-08 18:00","2021-06-07 08:00","2021-06-08 18:00","매일"]
[88,"인천","시흥","서서울#2소래 T/L","도림-오봉 등 4개 T/L C/H 방재설비 보강공사","1. 대상선로 : 154kV 서서울-소래[목감#1,2 C/H] 2. 시공내용 : 케이블 입상부 난연테이프 시공","2021-06-21 09:00","2021-06-22 18:00","2021-06-21 09:00","2021-06-22 18:00","연속"]
[89,"인천","시흥","신시흥#1S/S SEC CB 65660","신시흥#1S/S 154kV #65-#66 SEC   조작시험","신시흥#1S/S 154kV #65-#66 SEC   조작시험","2021-06-07 14:00","2021-06-07 18:00","2021-06-07 14:00","2021-06-07 18:00","연속"]
[90,"인천","시흥","신시흥#2S/S CB 6400","신시흥#2S/S 154kV #63-#68 BUS TIE   조작시험","신시흥#2S/S 154kV #63-#68 BUS TIE   조작시험","2021-06-07 09:00","2021-06-07 14:00","2021-06-07 09:00","2021-06-07 14:00","연속"]
[91,"인천","시흥","신시흥#2S/S SEC CB 67680","신시흥#2S/S 154kV #67-#68 SEC   하자점검","신시흥#2S/S 154kV #67-#68 SEC   하자점검","2021-06-02 09:00","2021-06-02 18:00","2021-06-02 09:00","2021-06-02 18:00","연속"]
[92,"인천","시흥","신시흥#2S/S SEC CB 62630","신시흥#2S/S 154kV #62-#63 SEC   하자점검","신시흥#2S/S 154kV #62-#63 SEC  (2019) 하자점검","2021-06-01 09:00","2021-06-01 18:00","2021-06-01 09:00","2021-06-01 18:00","연속"]
[93,"인천","시흥","신시흥시화#1 T/L","20-21년 가공송전정비 협력회사 총액공사","ㅇ 성능저하애자 교체공사 - 신시흥-시화T/L No.17,18 (2기)","2021-06-11 08:00","2021-06-11 18:00","2021-06-11 08:00","2021-06-11 18:00","매일"]
[94,"인천","시흥","신시흥시화#2 T/L","20-21년 가공송전정비 협력회사 총액공사","ㅇ 성능저하애자 교체공사 - 신시흥-시화T/L No.17,18 (2기)","2021-06-10 08:00","2021-06-10 18:00","2021-06-10 08:00","2021-06-10 18:00","매일"]
[95,"인천","시흥","오봉고잔#1 T/L","154kV 오봉고잔#1 T/L 사활표시관련 PITR 점검","154kV 오봉고잔#1 T/L 사활표시관련 PITR 점검","2021-06-10 09:00","2021-06-10 18:00","2021-06-10 09:00","2021-06-10 18:00","연속"]
[96,"인천","시흥","도림오봉#2 T/L","도림-오봉 등 4개 T/L C/H 방재설비 보강공사","1. 대상선로 : 154kV 도림-오봉#2(B)[오봉C/H] 2. 시공내용 : 케이블 입상부 난연테이프 시공","2021-06-16 09:00","2021-06-17 18:00","2021-06-19 09:00","2021-06-20 18:00","연속"]
[97,"인천","시흥","도림오봉#1 T/L","도림-오봉 등 4개 T/L C/H 방재설비 보강공사","1. 대상선로 : 154kV 도림-오봉#1(B)[오봉C/H] 2. 시공내용 : 케이블 입상부 난연테이프 시공","2021-06-14 09:00","2021-06-15 18:00","2021-06-12 09:00","2021-06-13 18:00","연속"]
[98,"인천","직할","계양원창 T/L","154kV 계양-원창T/L 고정형 폴리머 점퍼지지애자 설치","154kV 계양-원창T/L 고정형 폴리머 점퍼지지애자 설치","2021-06-09 08:00","2021-06-09 18:00","2021-06-16 08:00","2021-06-16 18:00","연속"]
[99,"인천","직할","신부평도당#2 T/L","도당S/S 신부평도당#2TL 하자점검","도당S/S 신부평도당#2TL 하자점검","2021-06-04 09:00","2021-06-04 18:00","2021-06-04 09:00","2021-06-04 18:00","연속"]
[100,"인천","직할","갈산도당#1 T/L","도당S/S 신부평도당#1TL 하자점검","도당S/S 신부평도당#1TL 하자점검","2021-06-03 09:00","2021-06-03 18:00","2021-06-05 09:00","2021-06-05 18:00","연속"]
[101,"인천","직할","부천도당#2 T/L","부천S/S 도당부천#2TL 보통점검","부천S/S 도당부천#2TL 보통점검 도당S/S 도당부천#2TL 하자점검","2021-06-15 09:00","2021-06-15 18:00","2021-06-15 09:00","2021-06-15 18:00","연속"]
[102,"인천","직할","부천신정#1 T/L","부천S/S 부천신정#1TL 보통점검","부천S/S 부천신정#1TL 보통점검","2021-06-01 09:00","2021-06-01 18:00","2021-06-01 09:00","2021-06-01 18:00","연속"]
[103,"인천","직할","부천신정#2 T/L","부천S/S 부천신정#2TL 보통점검","부천S/S 부천신정#2TL 보통점검","2021-06-02 09:00","2021-06-02 18:00","2021-06-02 09:00","2021-06-02 18:00","연속"]
[104,"인천","직할","부천원미#1 T/L","부천S/S 부천원미#1TL 보통점검","부천S/S 부천원미#1TL 보통점검 원미S/S 부천원미#1TL 조작시험 및 전자변교체","2021-06-10 09:00","2021-06-10 18:00","2021-06-16 09:00","2021-06-16 18:00","연속"]
[105,"인천","직할","부천원미#2 T/L","부천S/S 부천원미#2TL 보통점검","부천S/S 부천원미#2TL 보통점검 원미S/S 부천원미#2TL 조작시험 및 전자변교체","2021-06-11 09:00","2021-06-11 18:00","2021-06-17 09:00","2021-06-17 18:00","연속"]
[106,"인천","직할","부천도당#1 T/L","부천S/S 도당부천#1TL 보통점검","부천S/S 도당부천#1TL 보통점검 도당S/S 도당부천#1TL 하자점검","2021-06-14 09:00","2021-06-14 18:00","2021-06-14 09:00","2021-06-14 18:00","연속"]
[107,"인천","직할","경서북인천#2 T/L","북인천S/S 경서북인천#2T/L  조작시험","북인천S/S 경서북인천#2T/L  조작시험 및 전자변교체","2021-06-18 09:00","2021-06-18 18:00","2021-06-18 09:00","2021-06-18 18:00","연속"]
[108,"인천","직할","인천CC북인천#2 T/L","북인천S/S 인천CC북인천#2T/L 170kV   정밀점검","북인천S/S 인천CC북인천#2T/L 170kV   정밀점검","2021-06-03 09:00","2021-06-05 18:00","2021-06-03 09:00","2021-06-05 18:00","연속"]
[109,"인천","직할","신부평고강#2 T/L","2021년도 170kV  정밀점검(신부평S/S 신부평고강#2TL)","2021년도 170kV  정밀점검(신부평S/S 신부평고강#2TL)","2021-06-12 09:30","2021-06-13 18:00","2021-06-12 09:30","2021-06-13 18:00","연속"]
[110,"인천","직할","신부평고강#1 T/L","2021년도 170kV  정밀점검(신부평S/S 신부평고강#1TL)","2021년도 170kV  정밀점검(신부평S/S 신부평고강#1TL)","2021-06-19 08:00","2021-06-20 18:00","2021-06-19 08:00","2021-06-20 18:00","연속"]
[111,"인천","직할","신부평임학#1 T/L","임학S/S 신부평임학#1T/L SA변전소 혼용시스템 공사","임학S/S 신부평임학#1T/L SA변전소 혼용시스템 공사","2021-06-10 09:00","2021-06-10 18:00","2021-06-10 09:00","2021-06-10 18:00","연속"]
[112,"인천","직할","신부평임학#2 T/L","임학S/S 신부평임학#2T/L SA변전소 혼용시스템 공사","임학S/S 신부평임학#2T/L SA변전소 혼용시스템 공사","2021-06-11 09:00","2021-06-11 18:00","2021-06-07 09:00","2021-06-07 18:00","연속"]
[113,"인천","직할","신부평임학#1 T/L","170kV  정밀점검 무부하가압용(공항철도계양#2TL)","170kV  정밀점검 무부하가압용(공항철도계양#2TL)-신부평임학#1TL","2021-06-09 09:00","2021-06-09 18:00","2021-06-09 09:00","2021-06-09 18:00","연속"]
[114,"인천","직할","임학계양#2 T/L","임학S/S 임학계양#2T/L SA변전소 혼용시스템 공사","임학S/S 임학계양#2T/L SA변전소 혼용시스템 공사","2021-06-04 09:00","2021-06-04 18:00","2021-06-04 09:00","2021-06-04 18:00","연속"]
[115,"인천","직할","임학계양#1 T/L","임학S/S 임학계양#1T/L SA변전소 혼용시스템 공사","임학S/S 임학계양#1T/L SA변전소 혼용시스템 공사","2021-06-03 09:00","2021-06-03 18:00","2021-06-11 09:00","2021-06-11 18:00","연속"]
[116,"인천","직할","중동화곡#1 T/L","154kV 중동-화곡#1T/L 고정형 폴리머 점퍼지지애자 및 피뢰기 설치","154kV 중동-화곡#1T/L 고정형 폴리머 점퍼지지애자 및 피뢰기 설치","2021-06-10 08:00","2021-06-10 18:00","2021-06-12 08:00","2021-06-12 18:00","연속"]
[117,"인천","직할","중동화곡#2 T/L","154kV 중동-화곡#2T/L 고정형 폴리머 점퍼지지애자 설치","154kV 중동-화곡#2T/L 고정형 폴리머 점퍼지지애자 설치","2021-06-11 08:00","2021-06-11 18:00","2021-06-13 08:00","2021-06-13 18:00","연속"]
[118,"경기북부","고양","양주고양#2 T/L","154kV 양주-고양#2T/L 고양국도대체건설 지장이설","대상 : 154kV 양주-고양#2T/L No.34-37 내용 : 철탑 3기 철거, 2기(관형지지물) 설치 기타 : 관형지지물 정밀점검 및 공사 추가시공 관련 휴전기간 추가신청","2021-06-07 07:00","2021-06-11 18:00","취소","취소","연속"]
[119,"경기북부","고양","양주고양#1 T/L","154kV 양주-고양#1T/L 고양국도대체건설 지장이설","대상 : 154kV 양주-고양#1T/L No.34-37 내용 : 철탑 3기 철거, 2기(관형지지물) 설치","2021-06-12 07:00","2021-06-16 18:00","취소","취소","연속"]
[120,"경기북부","고양","월롱금촌#2 T/L","170kV 차단기 조작시험 - 변전총액공사","금촌S/S 637,647   조작시험","2021-06-10 13:00","2021-06-10 18:00","2021-06-10 13:00","2021-06-10 18:00","연속"]
[121,"경기북부","고양","월롱금촌#1 T/L","170kV 차단기 조작시험 - 변전총액공사","금촌S/S 637,647   조작시험","2021-06-10 10:00","2021-06-10 13:00","2021-06-09 09:00","2021-06-10 13:00","연속"]
[122,"경기북부","고양","지도능곡#1 T/L","170kV   차단기 조작시험 - 변전총액공사","능곡S/S 지도-능곡#1,2T/L 차단기 조작시험","2021-06-03 10:00","2021-06-03 13:00","2021-06-03 10:00","2021-06-03 13:00","연속"]
[123,"경기북부","고양","지도능곡#2 T/L","170kV   차단기 조작시험 - 변전총액공사","능곡S/S 지도-능곡#1,2T/L 차단기 조작시험","2021-06-03 13:00","2021-06-03 18:00","2021-06-03 13:00","2021-06-03 18:00","연속"]
[124,"경기북부","고양","신파주문발#1 T/L","2021 고양P/O 변전정비회사 총액공사","170kV   보통점검","2021-06-02 10:00","2021-06-02 18:00","2021-06-02 10:00","2021-06-02 18:00","연속"]
[125,"경기북부","고양","신덕은금촌#2 T/L","20-21년 고양전력지사 가공송전 정비회사 총액공사","ㅇ 성능저하 국산애자 교체","2021-06-03 07:00","2021-06-03 18:00","취소","취소","연속"]
[126,"경기북부","고양","신덕은금촌#1 T/L","2021년 상반기 고양P/O 170kV   정밀점검공사","2021년 상반기 고양P/O 170kV   정밀점검공사","2021-06-01 09:30","2021-06-02 18:00","2021-06-01 09:30","2021-06-02 18:00","연속"]
[127,"경기북부","고양","일산S/S 154KV #60 BUS","2021년 상반기 고양P/O 170kV   정밀점검공사","2021년 상반기 고양P/O 170kV   정밀점검공사(모선DS부)","2021-06-07 09:30","2021-06-08 12:00","2021-06-07 09:30","2021-06-08 12:00","연속"]
[128,"경기북부","고양","일산S/S 154KV #65 BUS","2021년 상반기 고양P/O 170kV   정밀점검공사","2021년 상반기 고양P/O 170kV   정밀점검공사(모선DS부)","2021-06-08 12:00","2021-06-09 18:00","2021-06-08 12:00","2021-06-09 18:00","연속"]
[129,"경기북부","고양","일산호수#2 T/L","2021년 상반기 고양P/O 170kV   정밀점검공사","2021년 상반기 고양P/O 170kV   정밀점검공사","2021-06-07 09:30","2021-06-09 18:00","2021-06-07 09:30","2021-06-09 18:00","연속"]
[130,"경기북부","고양","일산지도#2 T/L","2021-2022년 지중송전설비 위탁정비공사","PD 측정을 위한 C/H 시스접지선 상별분리","2021-06-23 07:00","2021-06-24 18:00","2021-06-23 07:00","2021-06-24 18:00","연속"]
[131,"경기북부","고양","일산지도#1 T/L","2021-2022년 지중송전설비 위탁정비공사","PD 측정을 위한 C/H 시스접지선 상별분리","2021-06-21 07:00","2021-06-22 18:00","2021-06-21 07:00","2021-06-22 18:00","연속"]
[132,"경기북부","고양","양주지축#1 T/L","20-21년 고양전력지사 가공송전 정비회사 총액공사","ㅇ 154kV 송전선로용 피뢰기 설치","2021-06-07 07:00","2021-06-08 18:00","2021-06-07 07:00","2021-06-08 18:00","연속"]
[133,"경기북부","구리","가평청평HP#2 T/L","2020년 가공송전 순시점검 위탁공사(정밀점검)","154kV 가평-청평HPT/L 정밀점검","2021-06-14 08:00","2021-06-17 18:00","취소","취소","연속"]
[134,"경기북부","구리","가평청평HP#1 T/L","2021년 가공송전 순시점검 위탁공사(정밀점검)","154kV 가평-청평HPT/L 정밀점검","2021-06-07 08:00","2021-06-10 18:00","취소","취소","연속"]
[135,"경기북부","구리","내촌용정#2 T/L","2020~2021년 경기북부본부 직할 가공송전 정비회사 총액공사","피뢰기 설치공사 상단병가선로","2021-06-08 07:30","2021-06-08 18:00","2021-06-08 07:30","2021-06-08 18:00","연속"]
[136,"경기북부","구리","진건별내#2 T/L","154kV 별내S/S #4M.Tr 증설공사","별내S/S #4M.Tr 증설공사 - M.Tr,   무부하가압","2021-06-28 09:00","2021-06-30 18:00","2021-06-28 09:00","2021-06-30 18:00","연속"]
[137,"경기북부","구리","진건별내#2 T/L","154kV 별내S/S #4M.Tr 증설공사","154kV 별내S/S #4M.Tr 170kV   개폐장치 설치 - 시험가압선로(#1BUS)","2021-06-04 09:00","2021-06-07 18:00","2021-06-04 09:00","2021-06-07 18:00","연속"]
[138,"경기북부","구리","별내S/S 154kV #2 BUS","154kV 별내S/S #4M.Tr 증설공사","별내S/S #4M.Tr 증설공사 - M.Tr,   무부하가압","2021-06-28 09:00","2021-06-30 18:00","2021-06-28 09:00","2021-06-30 18:00","연속"]
[139,"경기북부","구리","서종청평PP#2 T/L","`20~21년 구리전력 변전정비 총액공사","일진제 154kV   수동조작장치 구조개선 공사","2021-06-15 14:00","2021-06-15 18:00","2021-06-15 14:00","2021-06-15 18:00","연속"]
[140,"경기북부","구리","서종청평PP#1 T/L","154kV 서종-청평PP #1T/L 피뢰기설치공사","서종-청평PP #1T/L No.1~66 피뢰기 설치","2021-06-03 07:00","2021-06-11 18:00","2021-06-21 07:00","2021-06-29 18:00","연속"]
[141,"경기북부","구리","신포천동두천#1 T/L","2020~2021년 경기북부본부 직할 가공송전 정비회사 총액공사","피뢰기 설치공사","2021-06-09 07:30","2021-06-15 18:00","2021-06-09 07:30","2021-06-15 18:00","연속"]
[142,"경기북부","구리","진건별내#1 T/L","진건S/S #1M.Tr 증설공사","진건S/S #1M.Tr 증설공사 - M.Tr,  , SIS 시험가압 선로","2021-06-11 18:00","2021-06-12 18:00","2021-06-11 18:00","2021-06-12 18:00","연속"]
[143,"경기북부","구리","진건S/S 154kV #60 BUS","진건S/S #1M.Tr 증설공사","진건S/S #1M.Tr 증설공사 - 170kV   #60BUS측 준공시험 - M.Tr,  , SIS 무부하가압","2021-06-09 09:00","2021-06-12 18:00","2021-06-09 09:00","2021-06-12 18:00","연속"]
[144,"경기북부","구리","진접S/S CB 6100","`20~21년 구리전력 변전정비 총액공사","진접S/S 154kV #60-65 BUSTIE   조작시험","2021-06-10 09:00","2021-06-10 18:00","2021-06-10 09:00","2021-06-10 18:00","연속"]
[145,"경기북부","구리","포천운천#2 T/L","20~21년 구리전력지사 변전정비회사 총액공사","- 154kV CVT 이설공사(A상→B상)","2021-06-04 09:00","2021-06-04 18:00","2021-06-04 09:00","2021-06-04 18:00","연속"]
[146,"경기북부","구리","신포천포천#1 T/L","20~21년 구리전력지사 변전정비회사 총액공사","- 154kV CVT 이설공사(A상→B상)","2021-06-01 09:00","2021-06-01 18:00","2021-06-01 09:00","2021-06-01 18:00","연속"]
[147,"경기북부","구리","포천운천#1 T/L","20~21년 구리전력지사 변전정비회사 총액공사","- 154kV CVT 이설공사(A상→B상)","2021-06-03 09:00","2021-06-03 18:00","2021-06-03 09:00","2021-06-03 18:00","연속"]
[148,"경기북부","구리","신포천포천#2 T/L","20~21년 구리전력지사 변전정비회사 총액공사","- 154kV CVT 이설공사(A상→B상)","2021-06-02 09:00","2021-06-02 18:00","2021-06-02 09:00","2021-06-02 18:00","연속"]
[149,"경기북부","직할","백석덕계#2 T/L","'20-21 변전정비 총액공사","170kV   보통점검","2021-06-01 09:00","2021-06-01 18:00","2021-06-01 09:00","2021-06-01 18:00","연속"]
[150,"경기북부","직할","신의정부내촌#1 T/L","2020~2021년 경기북부본부 직할 가공송전 정비회사 총액공사","피뢰기 설치공사","2021-06-01 07:30","2021-06-08 18:00","2021-06-01 07:30","2021-06-08 18:00","연속"]
[151,"경기북부","직할","양주은평#2 T/L","20-21년 고양전력지사 가공송전 정비회사 총액공사","ㅇ 154kV 송전선로용 피뢰기 설치","2021-06-07 07:00","2021-06-08 18:00","2021-06-07 07:00","2021-06-08 18:00","연속"]
[152,"경기북부","직할","옥정동두천#1 T/L","2020~2021년 경기북부본부 직할 가공송전 정비회사 총액공사","피뢰기 설치공사 상단병가선로","2021-06-14 07:30","2021-06-15 18:00","2021-06-14 07:30","2021-06-15 18:00","연속"]
[153,"경기북부","구리","미금광장 T/L","21년 구리전력지사 가공송전 위탁회사 정밀점검(154kV 화양T/L)","가공송전운영업무 기준에 근거한 위탁회사 정밀점검 154kV 미금-광장T/L No.3,8~10,13~18,22~31","2021-06-23 08:00","2021-06-24 18:00","2021-06-23 08:00","2021-06-24 18:00","연속"]
[154,"경기","군포","남군포산본#1 T/L","154kV 남군포S/S #1M.Tr 증설공사","154kV #1M.Tr 무부하가압","2021-06-28 09:00","2021-06-29 18:00","2021-06-28 09:00","2021-06-29 18:00","연속"]
[155,"경기","군포","남안산목내#2 T/L","신안산선 복선전철 공사관련 지장선로 이설공사","154kV 남안산-목내T/L M/H#8~9 지장이설 154kV 안산-안산복합T/L M/H#8~9 지장이설","2021-06-22 08:00","2021-07-02 18:00","2021-06-22 08:00","2021-07-02 18:00","연속"]
[156,"경기","군포","남안산목내#1 T/L","신안산선 복선전철 공사관련 지장선로 이설공사","154kV 남안산-목내T/L M/H#8~9 지장이설 154kV 안산-안산복합T/L M/H#8~9 지장이설","2021-06-11 08:00","2021-06-21 18:00","2021-06-11 08:00","2021-06-21 18:00","연속"]
[157,"경기","군포","사강남양#1 T/L","남양S/S 남양-사강#1T/L   순간압력상승 경보 수용","남양S/S 남양-사강#1T/L   순간압력상승 경보 수용","2021-06-17 10:00","2021-06-17 18:00","2021-06-17 10:00","2021-06-17 18:00","연속"]
[158,"경기","군포","사강남양#2 T/L","남양S/S 남양-사강#2T/L   순간압력상승 경보 수용","남양S/S 남양-사강#2T/L   순간압력상승 경보 수용","2021-06-18 10:00","2021-06-18 18:00","2021-06-18 10:00","2021-06-18 18:00","연속"]
[159,"경기","군포","반월시화#1 T/L","반월S/S 반월-시화#1TL   불량패킹 재시공","반월S/S 반월-시화#1TL   불량패킹 재시공","2021-06-08 09:00","2021-06-08 13:00","2021-06-08 09:00","2021-06-08 13:00","연속"]
[160,"경기","군포","반월시화#2 T/L","반월S/S 반월-시화#2TL   불량패킹 재시공","반월S/S 반월-시화#2TL   불량패킹 재시공","2021-06-08 13:00","2021-06-08 17:00","2021-06-08 13:00","2021-06-08 17:00","연속"]
[161,"경기","군포","산본안양#1 T/L","21-22년 지중송전 위탁정비공사","산본-안양T/L 케이블헤드 피뢰기 점검","2021-06-16 09:00","2021-06-16 18:00","2021-06-16 09:00","2021-06-16 18:00","연속"]
[162,"경기","군포","산본안양#2 T/L","21-22년 지중송전 위탁정비공사","산본-안양T/L 케이블헤드 피뢰기 점검","2021-06-17 09:00","2021-06-17 18:00","2021-06-17 09:00","2021-06-17 18:00","연속"]
[163,"경기","군포","서서울#2봉담#2 T/L","154kV 서서울2-봉담#2T/L 정밀점검(가공송전위탁공사)","154kV 서서울2-봉담#2T/L 정밀점검(가공송전위탁공사)","2021-06-03 09:00","2021-06-04 18:00","2021-06-03 09:00","2021-06-04 18:00","매일"]
[164,"경기","군포","서서울#2소래 T/L","2020-2021년도 송전정비회사 총액공사","점퍼지지애자련 교체3련 교체","2021-06-25 12:00","2021-06-25 18:00","2021-06-25 12:00","2021-06-25 18:00","연속"]
[165,"경기","군포","서서울#2봉담#1 T/L","154kV 서서울2-봉담#1T/L 정밀점검(가공송전위탁공사)","154kV 서서울2-봉담#1T/L 정밀점검(가공송전위탁공사)","2021-06-01 09:00","2021-06-02 18:00","2021-06-01 09:00","2021-06-02 18:00","매일"]
[166,"경기","군포","서서울산본#1 T/L","서서울-산본#1T/L 보호배전반 대체","서서울-산본#1T/L 보호배전반 대체 지중송전 위탁공사(병행)","2021-06-21 08:00","2021-06-23 12:00","2021-06-21 08:00","2021-06-23 12:00","연속"]
[167,"경기","군포","서서울산본#2 T/L","서서울-산본#2T/L 보호배전반 대체","서서울-산본#2T/L 보호배전반 대체 지중송전 위탁공사(병행)","2021-06-23 13:00","2021-06-25 18:00","2021-06-23 13:00","2021-06-25 18:00","연속"]
[168,"경기","군포","서서울#2서안양 T/L","도림-오봉 등 4개 T/L C/H 방재설비 보강공사","1. 대상선로 : 154kV 서서울-서안양[목감#1,2 C/H] 2. 시공내용 : 케이블 입상부 난연테이프 시공","2021-06-09 14:00","2021-06-11 18:00","2021-06-09 14:00","2021-06-11 18:00","연속"]
[169,"경기","군포","성곡중시화 T/L","성곡-중시화T/L 보호배전반 대체","성곡-중시화T/L 보호배전반 대체","2021-06-14 08:00","2021-06-16 18:00","2021-06-14 08:00","2021-06-16 18:00","연속"]
[170,"경기","군포","신안산성포#2 T/L","신안산성포#2 T/L 보호배전반 대체","신안산성포#2 T/L 보호배전반 대체","2021-06-16 09:00","2021-06-18 18:00","2021-06-16 09:00","2021-06-18 18:00","연속"]
[171,"경기","군포","장덕마도 T/L","장덕S/S 축소형모자익 대체공사","장덕S/S 축소형모자익 대체공사","2021-06-14 09:00","2021-06-16 18:00","2021-06-14 09:00","2021-06-16 18:00","연속"]
[172,"경기","군포","화성장덕 T/L","장덕S/S 축소형모자익 대체공사","장덕S/S 축소형모자익 대체공사","2021-06-11 09:00","2021-06-13 18:00","2021-06-11 09:00","2021-06-13 18:00","매일"]
[173,"경기","동부","오천율현#2 T/L","154kV 오천-율현#2T/L C/H 및 LA점검","154kV 오천-율현#2T/L C/H#25 C/H 및 LA점검","2021-06-11 09:00","2021-06-11 18:00","2021-06-11 09:00","2021-06-11 18:00","연속"]
[174,"경기","동부","오천율현#1 T/L","154kV 오천-율현#1T/L C/H 및 LA점검","154kV 오천-율현#1T/L C/H#25 C/H 및 LA점검","2021-06-09 09:00","2021-06-09 18:00","2021-06-09 09:00","2021-06-09 18:00","연속"]
[175,"경기","성남","남사S/S 154kV #1 BUS","154kV 덕성S/S 건설공사 무부하 가압용","ㅇ 170kV   x 10CCT 설치 ㅇ 154kV M.Tr x 2BANK 설치 ㅇ 25.8kV E  x 13CCT, x 2Bay 설치 ㅇ 기타 부대공사 x 1식","2021-06-22 12:00","2021-06-23 12:00","2021-06-22 12:00","2021-06-23 12:00","연속"]
[176,"경기","성남","남사동탄#1 T/L","154kV 덕성S/S 건설공사 무부하 가압용","ㅇ 170kV   x 10CCT 설치 ㅇ 154kV M.Tr x 2BANK 설치 ㅇ 25.8kV E  x 13CCT, x 2Bay 설치 ㅇ 기타 부대공사 x 1식","2021-06-22 12:00","2021-06-23 12:00","2021-06-22 12:00","2021-06-23 12:00","연속"]
[177,"경기","성남","신성남서판교 #1 T/L","2021년 성남전력 변전정비회사 총액공사","  보통점검","2021-06-09 09:00","2021-06-09 18:00","2021-06-09 09:00","2021-06-09 18:00","연속"]
[178,"경기","성남","신성남정자#2 T/L","2021년 성남전력 변전정비회사 총액공사","  보통점검, 보호반 교체","2021-06-28 09:00","2021-06-30 18:00","2021-06-28 09:00","2021-06-30 18:00","연속"]
[179,"경기","성남","신수원S/S 154kV #61BUS","345kV 신수원S/S   용량대체공사(72Bay)_무부하용","345kV 신수원S/S   용량대체공사(72Bay)_무부하용","2021-06-08 09:00","2021-06-08 11:00","2021-06-08 09:00","2021-06-08 11:00","연속"]
[180,"경기","성남","신수원S/S 154kV #67BUS","154kV 신수원-북동탄T/L 등 2개소 인출변경","154kV 신수원-북동탄T/L 등 2개소 인출변경_무부하용","2021-06-29 15:00","2021-06-30 15:00","2021-06-29 15:00","2021-06-30 15:00","연속"]
[181,"경기","성남","용인남사#2 T/L","154kV 덕성분기T/L 건설공사","- 공사구간 : 154kV 용인-남사T/L No.25~No.28 - 공사내용 : A410B 4C-0.4km, 2C-0.7km, 3기 신설, 1기 철거","2021-06-26 08:00","2021-07-07 18:00","2021-06-26 08:00","2021-07-07 18:00","연속"]
[182,"경기","성남","용인남사#1 T/L","154kV 덕성분기T/L 건설공사","- 공사구간 : 154kV 용인-남사T/L No.25~No.28 - 공사내용 : A410B 4C-0.4km, 2C-0.7km, 3기 신설, 1기 철거","2021-06-01 08:00","2021-06-25 18:00","2021-06-01 08:00","2021-06-25 18:00","연속"]
[183,"경기","성남","모현용인#1 T/L","154kV 덕성S/S 건설공사 무부하 가압용","ㅇ 170kV   x 10CCT 설치 ㅇ 154kV M.Tr x 2BANK 설치 ㅇ 25.8kV E  x 13CCT, x 2Bay 설치 ㅇ 기타 부대공사 x 1식","2021-06-22 09:00","2021-06-22 12:00","2021-06-22 09:00","2021-06-22 12:00","연속"]
[184,"경기","직할","남수원발안#2 T/L","2020-2021년도 송전정비회사 총액공사","점퍼지지애자련 교체 관련 안전이격거리확보","2021-06-22 08:00","2021-06-23 18:00","2021-06-22 08:00","2021-06-23 18:00","연속"]
[185,"경기","직할","남수원발안#1 T/L","2020-2021년도 송전정비회사 총액공사","점퍼지지애자련 교체 관련 안전이격거리확보","2021-06-24 08:00","2021-06-25 12:00","2021-06-24 08:00","2021-06-25 12:00","연속"]
[186,"경기","직할","봉담남수원#1 T/L","2020-2021년도 송전정비회사 총액공사","점퍼지지애자련 21련 교체","2021-06-22 08:00","2021-06-23 18:00","2021-06-22 08:00","2021-06-23 18:00","연속"]
[187,"경기","직할","봉담남수원#2 T/L","2020-2021년도 송전정비회사 총액공사","점퍼지지애자련 18련 교체","2021-06-24 08:00","2021-06-25 12:00","2021-06-24 08:00","2021-06-25 12:00","연속"]
[188,"경기","직할","서서울서수원 #2 T/L","20-21년 경기직할 변전정비회사 총액공사","서수원S/S 서서울-서수원#2T/L   조작시험, 43LR 경보수용","2021-06-11 09:00","2021-06-11 18:00","2021-06-11 09:00","2021-06-11 18:00","연속"]
[189,"경기","직할","수촌조암#2 T/L","20-21년 경기직할 변전정비회사 총액공사","수촌S/S 수촌-조암#2T/L   하자점검","2021-06-10 09:00","2021-06-10 18:00","2021-06-10 09:00","2021-06-10 18:00","연속"]
[190,"경기","직할","율전의왕#2 T/L","20-21년 경기직할 변전정비회사 총액공사","율전S/S 율전-의왕#2T/L   보통점검 의왕S/S 율전-의왕#2T/L   하자점검, LA 보통점검","2021-06-15 09:00","2021-06-15 18:00","2021-06-15 09:00","2021-06-15 18:00","연속"]
[191,"경기","직할","율전의왕#1 T/L","20-21년 경기직할 변전정비회사 총액공사","율전S/S 율전-의왕#1T/L   보통점검 의왕S/S 율전-의왕#1T/L   하자점검, LA 보통점검","2021-06-14 09:00","2021-06-14 18:00","2021-06-14 09:00","2021-06-14 18:00","연속"]
[192,"경기","직할","동안양안양CC#2 T/L","20-21년 경기직할 변전정비회사 총액공사","안양열병합 DS 부분방전 발생관련 내부 DS점검","2021-06-09 09:00","2021-06-10 18:00","2021-06-09 09:00","2021-06-10 18:00","연속"]
[193,"경기","직할","관양평촌#1 T/L","20-21년 경기직할 변전정비회사 총액공사","평촌S/S 관양-평촌#1T/L   보통점검, 상호인터록 시험","2021-06-04 09:00","2021-06-04 18:00","2021-06-04 09:00","2021-06-04 18:00","연속"]
[194,"경기","직할","안양평촌#2 T/L","20-21년 경기직할 변전정비회사 총액공사","평촌S/S 안양-평촌#1,2T/L   조작시험","2021-06-02 14:00","2021-06-02 18:00","2021-06-02 14:00","2021-06-02 18:00","연속"]
[195,"경기","직할","안양평촌#1 T/L","20-21년 경기직할 변전정비회사 총액공사","평촌S/S 안양-평촌#1,2T/L   조작시험","2021-06-02 09:00","2021-06-02 14:00","2021-06-02 09:00","2021-06-02 14:00","연속"]
[196,"경기","직할","관양평촌#2 T/L","20-21년 경기직할 변전정비회사 총액공사","평촌S/S 관양-평촌#2T/L   보통점검, PITR 접점 송수신시험","2021-06-03 09:00","2021-06-03 18:00","2021-06-03 09:00","2021-06-03 18:00","연속"]
[197,"경기","평택","원정만호#2 T/L","154kV 원정만호#2 T/L   점검","원정S/S 원정-만호#2T/L   보통점검 만호S/S 원정-만호#2T/L   보통점검","2021-06-30 10:00","2021-06-30 18:00","2021-06-09 10:00","2021-06-09 10:00","연속"]
[198,"경기","평택","만호청북#1 T/L","154kV 만호-청북T/L 휴전","154kV 만호-청북T/L 보호반 대체 만호S/S 만호-청북T/L   보통점검","2021-06-01 10:00","2021-06-03 18:00","2021-06-28 10:00","2021-06-30 18:00","연속"]
[199,"경기","평택","삼죽광혜원 T/L","삼죽S/S 삼죽-광혜원 T/L   보통점검","삼죽S/S 삼죽-광혜원 T/L   보통점검","2021-06-29 10:00","2021-06-29 18:00","2021-06-22 10:00","2021-06-22 18:00","연속"]
[200,"경기","평택","서운삼죽 T/L","2021년 직할 가공송전선로 순시점검 위탁공사","345kV 서안성-신진천#1T/L 정밀점검","2021-06-12 07:30","2021-06-13 18:00","2021-06-12 07:30","2021-06-13 18:00","매일"]
[201,"경기","평택","소사벌안성 T/L","154kV 소사벌S/S #4M.Tr 증설공사","#4M.Tr 최초가압(무부하)","2021-06-30 10:00","2021-07-01 10:00","2021-06-30 10:00","2021-07-01 10:00","연속"]
[202,"경기","평택","청북평택#2 T/L","평택S/S 청북-평택#2T/L #2DS 과열보수","평택S/S 청북-평택#2T/L #2DS 과열보수","2021-06-04 10:00","2021-06-04 18:00","2021-06-04 10:00","2021-06-04 18:00","연속"]
[203,"경기","평택","원정평택T/P#1 T/L","원정평택T/P#1 T/L   점검","평택T/P 원정평택T/P#1 T/L   보통점검 원정S/S 원정평택T/P#1 T/L   조작시험","2021-06-17 10:00","2021-06-17 18:00","2021-06-17 10:00","2021-06-17 18:00","연속"]
[204,"경기","평택","원정평택T/P#2 T/L","원정평택T/P#2 T/L   점검","평택T/P 원정평택T/P#2 T/L   보통점검 원정S/S 원정평택T/P#2 T/L   조작시험","2021-06-18 10:00","2021-06-18 18:00","2021-06-18 10:00","2021-06-18 18:00","연속"]
[205,"강원","강릉","북평영동TP#1 T/L","20-21년도 강릉전력지사 송전정비회사 총액공사","○ SB댐퍼 설치 : 154kV 영동TP강릉T/L no.2,3,4,5,66,67,68,69(작업자 안전을 위한 병가구간 휴전), 154kV 영동화력T/L No.89, 90, 91","2021-06-01 08:00","2021-06-02 12:00","2021-06-01 08:00","2021-06-02 12:00","매일"]
[206,"강원","강릉","강릉횡계#2 T/L","20-21년도 강릉전력지사 송전정비회사 총액공사","○ SB댐퍼 설치 : 154kV 영동TP강릉T/L no.2,3,4,5,66,67,68,69(작업자 안전을 위한 병가구간 휴전)","2021-06-01 08:00","2021-06-01 18:00","2021-06-01 08:00","2021-06-01 18:00","연속"]
[207,"강원","강릉","강릉영동TP T/L","20-21년도 강릉전력지사 송전정비회사 총액공사","○ SB댐퍼 설치 : 154kV 영동TP강릉T/L no.2,3,4,5,66,67,68,69","2021-06-01 08:00","2021-06-01 18:00","2021-06-01 08:00","2021-06-01 18:00","연속"]
[208,"강원","원주","원주서원주#2 T/L","170kV   인출측 정밀점검","170kV   인출측 정밀점검","2021-06-01 10:00","2021-06-02 18:00","2021-06-07 10:00","2021-06-08 18:00","연속"]
[209,"강원","강릉","속초간성#2 T/L","20-21년도 강릉전력지사 송전정비회사 총액공사","○ SB댐퍼 설치 : 154kV 인성T/L no.142-144(작업자 안전을 위한 병가구간 휴전)","2021-06-02 12:00","2021-06-02 18:00","2021-06-02 12:00","2021-06-02 18:00","연속"]
[210,"강원","강릉","간성인제#1 T/L","20-21년도 강릉전력지사 송전정비회사 총액공사","○ SB댐퍼 설치 : 154kV 인성T/L no.142-144","2021-06-02 12:00","2021-06-02 18:00","2021-06-02 12:00","2021-06-02 18:00","연속"]
[211,"강원","강릉","동해영동TP T/L","20-21년도 강릉전력지사 송전정비회사 총액공사","○ SB댐퍼 설치 : 154kV 강릉(동해영동TP)T/L no.2,3,4,5 154kV 동해분기(동해영동TP)T/L no.50,51,52","2021-06-03 08:00","2021-06-03 18:00","2021-06-03 08:00","2021-06-03 18:00","연속"]
[212,"강원","강릉","북평영동TP#2 T/L","20-21년도 강릉전력지사 송전정비회사 총액공사","○ SB댐퍼 설치 : 154kV 강릉(동해영동TP)T/L no.2,3,4,5 154kV 동해분기(동해영동TP)T/L no.50,51,52(작업자 안전을 위한 병가구간 휴전) 154kV 영동화력T/L No.47~92","2021-06-03 08:00","2021-06-09 18:00","2021-06-03 08:00","2021-06-09 18:00","매일"]
[213,"강원","직할","북춘천화천HP T/L","154kV 화천T/L No.50~55 안전이격 확보공사","안전이격확보공사 (철탑교체 및 전력선 교체)","2021-06-03 09:00","2021-06-07 18:00","2021-06-06 09:00","2021-06-10 18:00","연속"]
[214,"강원","원주","원주서원주#1 T/L","원주북원주#2T/L OPGW 금구류탈락 관련 정비작업","원주서원주#1T/L 7호 OPGW 금구류(댐퍼) 자리 이탈관련 금구류 재취부","2021-06-03 10:00","2021-06-03 18:00","2021-06-03 10:00","2021-06-03 18:00","연속"]
[215,"강원","동해","동해이원#2 T/L","20~21년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해-이원#2T/L 피뢰기 교체","2021-06-03 10:00","2021-06-03 18:00","2021-06-03 10:00","2021-06-03 18:00","연속"]
[216,"강원","원주","남원주원주#2 T/L","2020~2021년 송전정비 협력회사 총액공사","○ 애자련 보강(원주S/S 인출)","2021-06-04 09:00","2021-06-04 18:00","2021-06-04 09:00","2021-06-04 18:00","연속"]
[217,"강원","동해","이원삼척 T/L","20~21년 동해전력지사 변전협력회사 총액공사","1. 삼척S/S 이원-삼척T/L 피뢰기 교체 2. 차단기 조작시험","2021-06-04 10:00","2021-06-04 18:00","2021-06-04 10:00","2021-06-04 18:00","연속"]
[218,"강원","직할","춘천북춘천#1 T/L","21년 강원본부 직할 154kV   정밀점검공사","○ 북춘천S/S 154kV 춘천-북춘천 #1 T/L   정밀점검공사","2021-06-06 09:00","2021-06-08 14:00","2021-06-01 09:00","2021-06-03 18:00","연속"]
[219,"강원","원주","신제천남원주#2 T/L","2020~2021년 원주전력지사 송전정비회사 총액공사","○ 신제천-남원주#2T/L 피뢰기 및 추락방지시설 설치공사","2021-06-07 07:00","2021-06-13 18:00","2021-06-28 07:00","2021-06-30 18:00","매일"]
[220,"강원","동해","이원동해TP T/L","차단기 장기미동작 조작시험","이원-동해TP 차단기 장기미동작 조작시험(이원S/S)","2021-06-08 09:00","2021-06-08 11:00","2021-06-08 09:00","2021-06-08 11:00","연속"]
[221,"강원","강릉","평창올림픽 T/L","장기미동작 차단기 조작시험","- 평창S/S 154kV 장기미동작 차단기 조작시험","2021-06-08 10:00","2021-06-08 14:00","2021-06-08 10:00","2021-06-08 14:00","연속"]
[222,"강원","직할","북춘천춘천HP T/L","21년 강원본부 직할 154kV   정밀점검공사","○ 북춘천S/S 154kV 북춘천-춘천HP T/L   정밀점검공사","2021-06-08 14:00","2021-06-10 18:00","2021-06-10 09:00","2021-06-12 18:00","연속"]
[223,"강원","강릉","속초간성#2 T/L","장기미동작 차단기 조작시험","- 속초S/S 154kV 장기미동작 차단기 조작시험","2021-06-09 10:00","2021-06-09 14:00","2021-06-09 10:00","2021-06-09 14:00","연속"]
[224,"강원","동해","이원도계 T/L","차단기 장기미동작 조작시험","이원-도계T/L 차단기 장기미동작 조작시험(양단)","2021-06-09 13:00","2021-06-09 18:00","2021-06-09 13:00","2021-06-09 18:00","연속"]
[225,"강원","동해","동해정선 T/L","154KV 영월화력T/L 안전이격확보공사","No.175~178 안전이격확보공사 - 철탑 신설/철거 : 4기/4기","2021-06-10 08:00","2021-06-20 18:00","2021-06-10 08:00","2021-06-20 18:00","연속"]
[226,"강원","강릉","동해강릉 T/L","20-21년도 강릉전력지사 송전정비회사 총액공사","○ SB댐퍼 설치 : 154kV 강릉(동해강릉)T/L no.66,67,68,69","2021-06-10 08:00","2021-06-10 18:00","2021-06-10 08:00","2021-06-10 18:00","연속"]
[227,"강원","동해","북평영동TP#1 T/L","2020~21년 동해전력지사 송전정비회사 총액공사","154kV 동해-강릉T/L No.87~89 병가구간 작업자 안전확보위한 휴전 (상단 : 동해-강릉, 하단 : 북평-영동TP#1)","2021-06-10 08:00","2021-06-10 18:00","2021-06-10 08:00","2021-06-10 18:00","연속"]
[228,"강원","강릉","강릉횡계#1 T/L","20-21년 강릉전력지사 송전정비회사 총액공사","○ SB댐퍼 설치 : 154kV 강릉(동해강릉)T/L no.66,67,68,69(작업자 안전을 위한 병가구간 휴전)","2021-06-10 08:00","2021-06-10 18:00","2021-06-10 08:00","2021-06-10 18:00","연속"]
[229,"강원","직할","춘천북춘천#2 T/L","21년 강원본부 직할 154kV   정밀점검공사","○ 북춘천S/S 154kV 춘천-북춘천 #2 T/L   정밀점검공사","2021-06-11 09:00","2021-06-13 18:00","2021-06-04 09:00","2021-06-06 18:00","연속"]
[230,"강원","원주","신제천남원주#1 T/L","21년 원주전력지사 피뢰기 및 추락방지시설 설치공사","○ 신제천-남원주#1T/L No.38~96 추락방지시설 설치","2021-06-14 07:00","2021-06-20 18:00","2021-06-24 07:00","2021-06-26 18:00","매일"]
[231,"강원","태백","이원태백 T/L","154kV 태원T/L 와이어형 추락방지장치 설치공사","와이어형 추락방지장치 설치","2021-06-14 08:00","2021-06-18 18:00","취소","취소","연속"]
[232,"강원","직할","철원화천#1 T/L","154kV 화천S/S 외장재 교체공사","○ 노후 외장재 철거 : 외벽 드라이비트 철거 등 ○ 외장재 설치 : 외벽 메탈판넬, AL시트패널 설치 등 ○ 도장공사 : 고탄성아크릴도장, 수성페인트 칠 등 ○ 기타공사 : 폐기물처리(건축폐자재:10t, 혼합폐기물:5t, 드라이비트:83㎥)","2021-06-14 08:00","2021-06-19 18:00","2021-06-14 08:00","2021-06-19 18:00","연속"]
[233,"강원","직할","철원화천#2 T/L","154kV 화천S/S 외장재 교체공사","○ 노후 외장재 철거 : 외벽 드라이비트 철거 등 ○ 외장재 설치 : 외벽 메탈판넬, AL시트패널 설치 등 ○ 도장공사 : 고탄성아크릴도장, 수성페인트 칠 등 ○ 기타공사 : 폐기물처리(건축폐자재:10t, 혼합폐기물:5t, 드라이비트:83㎥)","2021-06-14 08:00","2021-06-16 18:00","2021-06-17 08:00","2021-06-19 18:00","연속"]
[234,"강원","직할","화천화천HP#2 T/L","154kV 화천S/S 외장재 교체공사","○ 노후 외장재 철거 : 외벽 드라이비트 철거 등 ○ 외장재 설치 : 외벽 메탈판넬, AL시트패널 설치 등 ○ 도장공사 : 고탄성아크릴도장, 수성페인트 칠 등 ○ 기타공사 : 폐기물처리(건축폐자재:10t, 혼합폐기물:5t, 드라이비트:83㎥)","2021-06-17 09:00","2021-06-19 18:00","2021-06-14 08:00","2021-06-16 18:00","연속"]
[235,"강원","태백","도계태백 T/L","154kV 태원T/L 와이어형 추락방지장치 설치공사","와이어형 추락방지장치 설치","2021-06-21 08:00","2021-06-25 18:00","취소","취소","연속"]
[236,"강원","태백","신제천영월CC#1 T/L","'21~22년 강원본부 지중송전설비 위탁정비공사","154kV 정선-영월CCT/L EBA 절연유 채취 및 피뢰기 점검 154kV 신제천-영월CC#1T/L 피뢰기 점검","2021-06-21 08:00","2021-06-22 18:00","2021-06-21 08:00","2021-06-22 18:00","연속"]
[237,"강원","태백","정선영월CC T/L","'21~22년 강원본부 지중송전설비 위탁정비공사","154kV 정선-영월CCT/L EBA 절연유 채취 및 피뢰기 점검 154kV 신제천-영월CC#1T/L 피뢰기 점검","2021-06-21 08:00","2021-06-22 18:00","2021-06-21 08:00","2021-06-22 18:00","연속"]
[238,"강원","직할","춘천북춘천#1 T/L","춘천#1M.Tr 증설공사","춘천 #1M.Tr 증설공사(170kV   증설공사)","2021-06-21 09:00","2021-06-22 18:00","2021-06-21 09:00","2021-06-22 18:00","연속"]
[239,"강원","직할","상남인제#1 T/L","'20~21년 강원직할 송전협력회사 총액공사","성능저하 지지애자 교체","2021-06-21 09:00","2021-06-21 18:00","2021-06-21 09:00","2021-06-21 18:00","연속"]
[240,"강원","직할","상남인제#2 T/L","'20~21년 강원직할 송전협력회사 총액공사","성능저하 지지애자 교체","2021-06-22 09:00","2021-06-22 18:00","2021-06-22 09:00","2021-06-22 18:00","연속"]
[241,"강원","태백","동영월영월CC T/L","'21~22년 강원본부 지중송전설비 위탁정비공사","154kV 동영월-영월CCT/L EBA 절연유 채취 및 피뢰기 점검 154kV 신제천-영월CC#2T/L 피뢰기 점검","2021-06-23 08:00","2021-06-24 18:00","2021-06-23 08:00","2021-06-24 18:00","연속"]
[242,"강원","태백","신제천영월CC#2 T/L","'21~22년 강원본부 지중송전설비 위탁정비공사","154kV 동영월-영월CCT/L EBA 절연유 채취 및 피뢰기 점검 154kV 신제천-영월CC#2T/L 피뢰기 점검","2021-06-23 08:00","2021-06-24 18:00","2021-06-23 08:00","2021-06-24 18:00","연속"]
[243,"강원","직할","화천화천HP#1 T/L","'20~21년 강원직할 송전협력회사 총액공사","성능저하 지지애자 교체","2021-06-23 09:00","2021-06-23 18:00","2021-06-23 09:00","2021-06-23 18:00","연속"]
[244,"강원","직할","춘천열병합S/Y 154kV STATION AUX Tr CB","21년 상반기 장기 미동작 차단기 조작시험","○ 154kV 춘천열병합S/Y Station Aux TR 차단기 조작시험","2021-06-25 10:00","2021-06-25 18:00","취소","취소","연속"]
[245,"강원","직할","의암H/P 154kV #2 M.Tr 2차 CB","2020~2021년 강원본부 직할 변전정비 총액공사","○ 154kV #2M.Tr 2차 GCB 보통점검 ○ GCB 전자변 교체","2021-06-28 09:00","2021-06-28 18:00","취소","취소","연속"]
[246,"충북","충주","감곡가남#1 T/L","20-21년 충주전력지사 변전정비 총액공사","154kV LA 보통점검","2021-06-30 10:00","2021-06-30 16:00","2021-06-21 07:30","2021-06-23 18:00","연속"]
[247,"충북","청주","국사봉명#1 T/L","2020-2021년 청주전력지사 송전정비회사 총액공사","사다리 설치 : No.1","2021-06-14 07:00","2021-06-15 18:00","취소","취소","매일"]
[248,"충북","충주","금왕남음성#1 T/L","20-21년 충주전력지사 변전정비 총액공사","수동트립장치 구조개선(유사고장 방지)","2021-06-11 10:00","2021-06-11 14:00","2021-06-11 10:00","2021-06-11 14:00","연속"]
[249,"충북","충주","금왕남음성#2 T/L","2020~21년 직할 송전정비회사 총액공사","154kV 음성-금왕#1T/L 병가구간 휴전작업에 따른 휴전","2021-06-27 07:30","2021-06-28 18:00","2021-06-27 07:30","2021-06-28 18:00","매일"]
[250,"충북","직할","남음성덕산#1 T/L","담수지 인근 헬기 안전운항을 위한 OPGW 항공장애표시구 시설공사","○ 공사구간 - 154kV 남음성-덕산#1T/L 20∼21호 - 154kV 진천-덕산#2T/L 26∼27호 ○ OPGW 항공장애표시구 10EA 시설 ○ 시공사 : 한전KDN, 시공관리책임자 : 윤일한 (H.P:010-2865-0613)","2021-06-29 09:00","2021-06-29 18:00","2021-06-29 09:00","2021-06-29 18:00","연속"]
[251,"충북","직할","남음성덕산#2 T/L","2020~21년 직할 송전정비회사 총액공사","항공장애표시구 설치 (No.20~21, 1경간)","2021-06-03 07:30","2021-06-03 12:00","2021-06-03 07:30","2021-06-03 12:00","연속"]
[252,"충북","청주","북청주봉명#1 T/L","북청주S/S 154kV 신규수용 SW 증설공사","154kV 지중T/L 1CCT 증설 배전반 설치 및 부대작업","2021-06-16 11:00","2021-06-17 18:00","2021-06-16 11:00","2021-06-17 18:00","연속"]
[253,"충북","청주","북청주봉명#1 T/L","북청주S/S 154kV 신규수용 SW 증설공사","154kV 지중T/L 1CCT 증설 배전반 설치 및 부대작업","2021-06-24 10:00","2021-06-25 18:00","2021-06-24 10:00","2021-06-25 18:00","연속"]
[254,"충북","청주","북청주봉명#2 T/L","북청주S/S 154kV 신규수용 SW 증설공사","154kV 지중T/L 1CCT 증설 배전반 설치 및 부대작업","2021-06-12 14:00","2021-06-14 09:00","2021-06-12 14:00","2021-06-14 09:00","연속"]
[255,"충북","청주","북청주봉명#2 T/L","2021년 청주전력지사 170kV   정밀점검공사","봉명S/S 북청주-봉명#2T/L 170kV   정밀점검","2021-06-05 09:00","2021-06-06 18:00","2021-06-05 09:00","2021-06-06 18:00","연속"]
[256,"충북","충주","북충주S/S CB 6100","20-21년 충주전력지사 변전정비 총액공사","CB 개폐타임 측정 및 조작시험","2021-06-04 10:00","2021-06-04 14:00","2021-06-04 10:00","2021-06-04 14:00","연속"]
[257,"충북","충주","북충주충주 T/L","154kV 왕암-충주T/L 요청자시행 지장철탑이설공사","철탑교체 1기(69호)","2021-06-15 09:00","2021-06-18 18:00","2021-06-15 09:00","2021-06-18 18:00","연속"]
[258,"충북","충주","북충주충주 T/L","154kV 왕암-충주T/L 요청자시행 지장철탑이설공사","철탑교체 1기(69호)","2021-06-07 09:00","2021-06-09 18:00","2021-06-07 09:00","2021-06-09 18:00","연속"]
[259,"충북","청주","사직북청주#1 T/L","20-21년 청주전력 변전정비 총액","송전선로 보호반 교체","2021-06-23 09:00","2021-06-24 18:00","취소","취소","연속"]
[260,"충북","청주","사직북청주#2 T/L","154kV 사직-북청주#2T/L 접속함 접지선 정비공사","* 대상 : 154kV 사직-북청주#2T/L J/B#8 C상 * 내용 : 맨홀 #8 C상 접속함 접지선 정비","2021-06-09 12:00","2021-06-09 15:00","취소","취소","연속"]
[261,"충북","직할","서운광혜원 T/L","2021년 직할 가공송전선로 순시점검 위탁공사","345kV 서안성-신진천#2T/L 정밀점검","2021-06-29 07:30","2021-06-30 18:00","2021-06-29 07:30","2021-06-30 18:00","매일"]
[262,"충북","청주","서청주사직#2 T/L","154kV 서청주-사직#2T/L 접속함 방식층 정비공사","* 대상 : 154kV 서청주-사직#2T/L J/B#7 C상 * 내용 : 맨홀 #7 접속함 C상 방식층 정비","2021-06-27 10:00","2021-06-27 17:00","취소","취소","연속"]
[263,"충북","직할","신진천S/S SEC CB 60610","345kV 신진천S/S 축소형모자익 대체공사","축소형모자익 대체 관련 조작시험","2021-06-22 13:00","2021-06-22 14:00","취소","취소","연속"]
[264,"충북","직할","신진천S/S CB 6100","345kV 신진천S/S 축소형모자익 대체공사","축소형모자익 대체 관련 조작시험","2021-06-21 16:00","2021-06-21 17:00","취소","취소","연속"]
[265,"충북","직할","신진천S/S SEC CB 61620","345kV 신진천S/S 축소형모자익 대체공사","축소형모자익 대체 관련 조작시험","2021-06-22 14:00","2021-06-22 15:00","취소","취소","연속"]
[266,"충북","직할","신진천S/S CB 6200","345kV 신진천S/S 축소형모자익 대체공사","축소형모자익 대체 관련 조작시험","2021-06-22 10:00","2021-06-22 11:00","취소","취소","연속"]
[267,"충북","직할","신진천S/S CB 6300","345kV 신진천S/S 축소형모자익 대체공사","축소형모자익 대체 관련 조작시험","2021-06-22 11:00","2021-06-22 12:00","취소","취소","연속"]
[268,"충북","직할","신진천S/S 154kV #65 BUS","345kV 신진천S/S #5M.Tr 증설공사","#5M.Tr 증설분 무부하가압(345kV   ~154kV   부싱) 상체크","2021-06-27 09:00","2021-06-27 18:00","2021-06-27 09:00","2021-06-27 18:00","연속"]
[269,"충북","직할","신진천S/S SEC CB 65660","345kV 신진천S/S 축소형모자익 대체공사","축소형모자익 대체 관련 조작시험","2021-06-23 10:00","2021-06-23 11:00","취소","취소","연속"]
[270,"충북","직할","신진천S/S SEC CB 66670","345kV 신진천S/S 축소형모자익 대체공사","축소형모자익 대체 관련 조작시험","2021-06-23 11:00","2021-06-23 12:00","취소","취소","연속"]
[271,"충북","직할","신진천오창#1 T/L","154kV 신진천-오창T/L OPGW 증설공사","○ 공사구간 : 신진천S/S ∼ 오창S/S ○ 공사내용 : 가공지선 ACSR 97㎟ 철거 및 OPGW 100㎟ 시설 ○ 시 공 사 : 한전KDN, 시공관리책임자 : 백승갑 (H.P:010-4141-1352)","2021-06-05 08:00","2021-06-06 18:00","2021-06-05 08:00","2021-06-06 18:00","연속"]
[272,"충북","직할","신진천오창#1 T/L","345kV 신진천S/S 축소형모자익 대체공사","축소형모자익 대체 관련 조작시험","2021-06-23 13:00","2021-06-23 14:00","취소","취소","연속"]
[273,"충북","직할","신진천오창#2 T/L","154kV 신진천-오창T/L OPGW 증설공사","○ 공사구간 : 신진천S/S ∼ 오창S/S ○ 공사내용 : 가공지선 ACSR 97㎟ 철거 및 OPGW 100㎟ 시설 ○ 시 공 사 : 한전KDN, 시공관리책임자 : 백승갑 (H.P:010-4141-1352)","2021-06-12 08:00","2021-06-13 18:00","2021-06-12 08:00","2021-06-13 18:00","연속"]
[274,"충북","직할","신진천오창#2 T/L","345kV 신진천S/S 축소형모자익 대체공사","축소형모자익 대체 관련 조작시험","2021-06-21 13:00","2021-06-21 14:00","취소","취소","연속"]
[275,"충북","직할","신진천진천#1 T/L","154kV 신진천-오창T/L OPGW 증설공사","○ 공사구간 : 신진천S/S ∼ 오창S/S ○ 공사내용 : 가공지선 ACSR 97㎟ 철거 및 OPGW 100㎟ 시설 ○ 시 공 사 : 한전KDN, 시공관리책임자 : 백승갑 (H.P:010-4141-1352)","2021-06-13 08:00","2021-06-13 18:00","취소","취소","연속"]
[276,"충북","직할","신진천진천#1 T/L","345kV 신진천S/S 축소형모자익 대체공사","축소형모자익 대체 관련 조작시험","2021-06-21 14:00","2021-06-21 15:00","취소","취소","연속"]
[277,"충북","직할","신진천진천#2 T/L","154kV 신진천-오창T/L OPGW 증설공사","○ 공사구간 : 신진천S/S ∼ 오창S/S ○ 공사내용 : 가공지선 ACSR 97㎟ 철거 및 OPGW 100㎟ 시설 ○ 시 공 사 : 한전KDN, 시공관리책임자 : 백승갑 (H.P:010-4141-1352)","2021-06-12 08:00","2021-06-12 18:00","취소","취소","연속"]
[278,"충북","직할","신진천진천#2 T/L","2020~21년 직할 송전정비회사 총액공사","아킹혼 설치(21기), 불량애자 교체(6기)","2021-06-05 07:30","2021-06-06 18:00","취소","취소","매일"]
[279,"충북","직할","신진천진천#2 T/L","345kV 신진천S/S 축소형모자익 대체공사","축소형모자익 대체 관련 조작시험","2021-06-21 15:00","2021-06-21 16:00","취소","취소","연속"]
[280,"충북","충주","신충주감곡#1 T/L","신충주S/S 170kV   가스누기 보수","신충주S/S 신충주-감곡#1T/L 170kV   가스누기 관련 #60,65BUS 밸런스 밸로우즈 설치 및 무부하 가압","2021-06-01 09:00","2021-06-08 18:00","2021-06-01 09:00","2021-06-08 18:00","연속"]
[281,"충북","충주","신충주감곡#2 T/L","2020~21년 직할 송전정비회사 총액공사","피뢰기 설치(72기), 불량애자 교체(4기), 추락방지시설 설치(4기)","2021-06-10 07:30","2021-06-23 18:00","2021-06-10 07:30","2021-06-23 18:00","매일"]
[282,"충북","충주","신충주음성#1 T/L","2020~21년 직할 송전정비회사 총액공사","피뢰기 설치(21기), 불량애자 교체(2기)","2021-06-24 07:30","2021-06-26 18:00","2021-06-24 07:30","2021-06-26 18:00","매일"]
[283,"충북","충주","신충주음성#1 T/L","2020~21년 직할 송전정비회사 총액공사","피뢰기 설치(45기), 불량애자 교체(2기), 추락방지시설 설치(3기)","2021-06-14 07:30","2021-06-20 18:00","2021-06-14 07:30","2021-06-20 18:00","매일"]
[284,"충북","충주","신충주음성#2 T/L","20-21년 충주전력지사 변전정비 총액공사","음성S/S 신충주-음성#2T/L CVT 교체","2021-06-21 10:00","2021-06-21 18:00","2021-06-21 10:00","2021-06-21 18:00","연속"]
[285,"충북","청주","오창국사#1 T/L","2020-2021년 청주전력지사 송전정비회사 총액공사","사다리 설치 : No.18","2021-06-14 07:00","2021-06-15 18:00","취소","취소","매일"]
[286,"충북","청주","오창국사#2 T/L","오창변전소 154kV   1CCT 설치공사","#60BUS 도킹후 건전성 확인을 위한 무부하 가압","2021-06-23 17:00","2021-06-24 17:00","2021-06-23 17:00","2021-06-24 17:00","연속"]
[287,"충북","청주","오창국사#2 T/L","오창변전소 154kV   1CCT 설치공사","#65BUS 도킹후 건전성 확인을 위한 무부하 가압","2021-06-19 17:00","2021-06-20 17:00","2021-06-19 17:00","2021-06-20 17:00","연속"]
[288,"충북","충주","왕암여주#2 T/L","2020~21년 직할 송전정비회사 총액공사","추락방지시설 설치(2기)","2021-06-10 07:30","2021-06-11 18:00","2021-06-10 07:30","2021-06-11 18:00","매일"]
[289,"충북","충주","왕암충주 T/L","154kV 왕암-충주T/L 요청자시행 지장철탑이설공사","철탑교체 1기(69호)","2021-06-10 09:00","2021-06-14 18:00","2021-06-10 09:00","2021-06-14 18:00","연속"]
[290,"충북","충주","음성금왕#1 T/L","2020~21년 직할 송전정비회사 총액공사","불량애자 교체(5기), 추락방지시설 설치(2기)","2021-06-26 07:30","2021-06-28 18:00","2021-06-26 07:30","2021-06-28 18:00","매일"]
[291,"충북","충주","제천영월#1 T/L","154kV 제천-영월T/L 용량증대 전선교체공사","전선교체 59km, 철탑교체 20기","2021-06-01 08:00","2021-06-15 18:00","2021-06-01 08:00","2021-06-15 18:00","연속"]
[292,"충북","충주","제천영월#2 T/L","154kV 제천-영월T/L 용량증대 전선교체공사","전선교체 59km, 철탑교체 20기","2021-06-16 08:00","2021-06-30 18:00","2021-06-16 08:00","2021-06-30 18:00","연속"]
[293,"충북","직할","진천광혜원#1 T/L","20-21년 충북 직할 변전정비회사 총액공사","광혜원S/S 154kV 진천-광혜원#1T/L   보통점검(6/7) 진천S/S 154kV 진천-광혜원#1T/L   보통점검(6/8)","2021-06-07 10:00","2021-06-08 18:00","2021-06-07 10:00","2021-06-08 18:00","매일"]
[294,"충북","직할","진천광혜원#2 T/L","20-21년 충북 직할 변전정비회사 총액공사","광혜원S/S 154kV 진천-광혜원#2T/L   보통점검(6/22) 진천S/S 154kV 진천-광혜원#2T/L   보통점검(6/23)","2021-06-22 10:00","2021-06-23 18:00","2021-06-22 10:00","2021-06-23 18:00","매일"]
[295,"충북","직할","진천덕산#1 T/L","2020~21년 직할 송전정비회사 총액공사","항공장애표시구 설치 (No.26~27, 1경간)","2021-06-03 12:00","2021-06-03 18:00","2021-06-03 12:00","2021-06-03 18:00","연속"]
[296,"충북","직할","진천덕산#2 T/L","담수지 인근 헬기 안전운항을 위한 OPGW 항공장애표시구 시설공사","○ 공사구간 - 154kV 남음성-덕산#1T/L 20∼21호 - 154kV 진천-덕산#2T/L 26∼27호 ○ OPGW 항공장애표시구 10EA 시설 ○ 시공사 : 한전KDN, 시공관리책임자 : 윤일한 (H.P:010-2865-0613)","2021-06-30 09:00","2021-06-30 18:00","2021-06-30 09:00","2021-06-30 18:00","연속"]
[297,"충북","충주","충주장연 T/L","154kV 충주-풍동T/L 접속개소 전력선교체공사","전력선 교체(No.49-53)","2021-06-03 07:00","2021-06-05 18:00","2021-06-10 07:00","2021-06-12 18:00","연속"]
[298,"충북","충주","풍동음성#1 T/L","2020~21년 직할 송전정비회사 총액공사","불량애자 교체(5기), 아킹혼 설치(6기)","2021-06-07 07:30","2021-06-09 18:00","2021-06-07 07:30","2021-06-09 18:00","매일"]
[299,"대전충남","대전","신옥천서대전 T/L","[송전] 154kV 신옥천-서대전등 8개T/L 철탑도장공사","[송전] 154kV 신옥천-서대전T/L 철탑도장공사","2021-06-03 07:00","2021-06-22 18:00","2021-06-04 08:00","2021-06-22 18:00","매일"]
[300,"대전충남","서산","서산해미 T/L","21년 서산P/O 154kV   정밀점검공사","서산S/S 서산-해미T/L 617  정밀점검 서산S/S 피뢰기 보통점검","2021-06-21 09:00","2021-06-25 18:00","취소","취소","연속"]
[301,"대전충남","서산","송악GSEPS#1 T/L","154kV GS-EPS#1 T/L 피뢰기 설치공사","154kV GS-EPS#1 T/L 피뢰기 설치공사 No.1~6(6기) (안전이격거리 확보) 345kV 북당진-현대제철 피뢰기 설치공사 No.11~16(5기)","2021-06-08 08:00","2021-06-09 18:00","2021-06-08 08:00","2021-06-09 18:00","매일"]
[302,"대전충남","서산","당진송악#2 T/L","154kV 합덕-송악T/L 피뢰기 설치공사","154kV 합덕-송악T/L 피뢰기 설치 - No.60~97(38기) - 4회선 병가철탑 안전이격확보 (병행) 서산전력지사 송전운영 154kV 합덕-송악 T/L 4회선 병가철탑 정밀점검","2021-06-18 08:00","2021-06-24 18:00","취소","취소","매일"]
[303,"대전충남","서산","신당진당진#1 T/L","154kV 신당진-당진#1 T/L 정밀점검","154kV 신당진-당진#1 T/L No.1-44 (정밀점검) 154kV 합덕송악#1 T/L No.52-59 (병가구간 및 정밀점검) 병행작업(서산전력지사 송전정비) -154kV 합덕-송악#1 T/L 피뢰기설치 안전작업거리이격","2021-06-28 08:00","2021-07-02 18:00","취소","취소","매일"]
[304,"대전충남","서산","신당진S/S SEC CB 65660","21년 장기 미동작 차단기 조작시험","신당진S/S 154kV #65-#66 SEC 65-66-0 CB 조작시험","2021-06-10 14:00","2021-06-10 18:00","2021-06-10 14:00","2021-06-10 18:00","연속"]
[305,"대전충남","서산","신당진S/S CB 6200","21년 장기 미동작 차단기 조작시험","신당진S/S 154kV #61-#66 BUS TIE 6200 CB 조작시험","2021-06-08 14:00","2021-06-08 18:00","2021-06-08 14:00","2021-06-08 18:00","연속"]
[306,"대전충남","서산","신당진S/S CB 6100","21년 장기 미동작 차단기 조작시험","신당진S/S 154kV #60-#65 BUS TIE 6100 CB 조작시험","2021-06-08 10:00","2021-06-08 14:00","2021-06-08 10:00","2021-06-08 14:00","연속"]
[307,"대전충남","서산","신당진S/S SEC CB 60610","21년 장기 미동작 차단기 조작시험","신당진S/S 154kV #60-#61 SEC 60-61-0 CB 조작시험","2021-06-10 10:00","2021-06-10 14:00","2021-06-10 10:00","2021-06-10 14:00","연속"]
[308,"대전충남","서산","합덕송악#1 T/L","154kV 합덕-송악 T/L 피뢰기 설치공사","154kV 합덕-송악#1T/L No.1~98(98기) (병행) 154kV 합덕-송악T/L 정밀점검","2021-06-14 08:00","2021-06-30 18:00","취소","취소","매일"]
[309,"대전충남","세종","둔곡송강#1 T/L","21년 세종P/O 170kV   정밀점검 및 보통점검공사","○2021년도 170kV   정밀점검 및 보통점검 - 170kV   정밀점검 10BAY - 170kV   보통점검 16BAY","2021-06-14 09:00","2021-06-14 18:00","2021-06-14 09:00","2021-06-14 18:00","연속"]
[310,"대전충남","세종","둔곡송강#2 T/L","21년 세종P/O 170kV   정밀점검 및 보통점검공사","○2021년도 170kV   정밀점검 및 보통점검 - 170kV   정밀점검 10BAY - 170kV   보통점검 16BAY","2021-06-15 09:00","2021-06-15 18:00","2021-06-15 09:00","2021-06-15 18:00","연속"]
[311,"대전충남","세종","부강월산#1 T/L","154kV 세종분기T/L 건설공사","1. 구간 : (기설)154㎸ 부강-월산T/L No.17-19 ~ (신설)154㎸ 세종분기 T/L No.3(CH) 2. 선로길이 : 1.197㎞ (4C-0.507㎞, 2C-0.690㎞) 3. 지 지 물 : 4기(154kV용 4각철탑 2기, 154kV용 관형지지물 1기, 임시 철탑 1기) 4","2021-06-06 07:00","2021-06-09 18:00","2021-06-06 07:00","2021-06-09 18:00","연속"]
[312,"대전충남","세종","부강월산#2 T/L","154kV 세종분기T/L 건설공사","1. 구간 : (기설)154㎸ 부강-월산T/L No.17-19 ~ (신설)154㎸ 세종분기 T/L No.3(CH) 2. 선로길이 : 1.197㎞ (4C-0.507㎞, 2C-0.690㎞) 3. 지 지 물 : 4기(154kV용 4각철탑 2기, 154kV용 관형지지물 1기, 임시 철탑 1기) 4","2021-06-02 07:00","2021-06-05 18:00","2021-06-02 07:00","2021-06-05 18:00","연속"]
[313,"대전충남","세종","서세종조치원 T/L","[제어]154kV 조치원-월산T/L OPGW 교체공사","조치원S/S ~ 월산S/S 간 OPGW 교체 (24C→48C 광케이블 용량 증설)","2021-06-21 08:00","2021-06-21 18:00","2021-06-14 07:00","2021-06-19 18:00","연속"]
[314,"대전충남","세종","월산S/S CB 6100","21년 세종P/O 170kV   정밀점검 및 보통점검공사","○2021년도 170kV   정밀점검 및 보통점검 - 170kV   정밀점검 10BAY - 170kV   보통점검 16BAY","2021-06-28 09:00","2021-06-29 18:00","2021-06-28 09:00","2021-06-29 18:00","연속"]
[315,"대전충남","세종","천안전의#1 T/L","21년 세종P/O 170kV   정밀점검 및 보통점검공사","○2021년도 170kV   정밀점검 및 보통점검 - 170kV   정밀점검 10BAY - 170kV   보통점검 16BAY","2021-06-03 09:00","2021-06-04 18:00","2021-06-03 09:00","2021-06-04 18:00","연속"]
[316,"대전충남","세종","조치원전의#2 T/L","[송전]154kV 조치원-전의T/L 지장송전선로 이설공사","154kV 조치원-전의T/L No.20~24 지장송전선로 임시선로 구성","2021-06-14 07:00","2021-06-20 18:00","취소","취소","연속"]
[317,"대전충남","세종","조치원월산 T/L","[제어]154kV 조치원-월산T/L OPGW 교체공사","조치원S/S ~ 월산S/S 간 OPGW 교체 (24C→48C 광케이블 용량 증설) ※ 서세종-조치원T/L 병행작업예정 (양회선 동시휴전 필요)","2021-06-21 08:00","2021-06-21 18:00","2021-06-19 07:00","2021-06-26 18:00","연속"]
[318,"대전충남","세종","조치원전의#1 T/L","[송전]154kV 조치원-전의T/L 지장송전선로 이설공사","154kV 조치원-전의T/L No.20~24 지장송전선로 임시선로 구성","2021-06-22 07:00","2021-06-28 18:00","취소","취소","연속"]
[319,"대전충남","세종","덕진대화#1 T/L"," 154kV 덕진-대화T/L(용산지구) 지장송전선로 지중화공사 ","No.4~6 지중화 ","2021-06-28 07:00","2021-06-30 18:00","2021-06-28 07:00","2021-06-30 18:00","연속"]
[320,"대전충남","세종","덕진대화#2 T/L"," 154kV 덕진-대화T/L(용산지구) 지장송전선로 지중화공사 ","No.4~6 지중화 ","2021-06-25 07:00","2021-06-27 18:00","2021-06-25 07:00","2021-06-27 18:00","연속"]
[321,"대전충남","직할","신탄진대청HP T/L","154kV 대청분기T/L 피뢰기 설치공사","No.1~7 피뢰기 설치공사","2021-06-01 08:00","2021-06-01 18:00","2021-06-01 08:00","2021-06-01 18:00","연속"]
[322,"대전충남","천안","아산예산#2 T/L","[송전]154kV 아산-예산T/L 안전이격 확보공사","○ Enclosing 설치 : 4기(No.39, 40, 41, 43호) ○ 계탑 : 1기(No.42호) ○ 가철주 설치/철거 : 1기(No.42호) ○ 전선교체 : No.35~39, 39~43, 43~44호 구간","2021-06-30 07:00","2021-07-04 18:00","2021-06-30 07:00","2021-07-04 18:00","연속"]
[323,"대전충남","천안","아산예산#1 T/L","[송전]154kV 아산-예산T/L 안전이격 확보공사","○ Enclosing 설치 : 4기(No.39, 40, 41, 43호) ○ 계탑 : 1기(No.42호) ○ 가철주 설치/철거 : 1기(No.42호) ○ 전선교체 : No.35~39, 39~43, 43~44호 구간","2021-06-23 07:00","2021-06-29 18:00","2021-06-23 07:00","2021-06-29 18:00","연속"]
[324,"대전충남","천안","아산예산#2 T/L","[송전]154kV 아산-예산T/L 안전이격 확보공사","○ Enclosing 설치 : 4기(No.39, 40, 41, 43호) ○ 계탑 : 1기(No.42호) ○ 가철주 설치/철거 : 1기(No.42호) ○ 전선교체 : No.35~39, 39~43, 43~44호 구간","2021-06-21 07:00","2021-06-22 18:00","2021-06-21 07:00","2021-06-22 18:00","연속"]
[325,"대전충남","천안","아산인주#1 T/L","아산S/S 154kV 장기사용   교체공사","170kV  8CCT 교체","2021-06-30 10:00","2021-07-21 18:00","취소","취소","연속"]
[326,"대전충남","천안","온양풍세#1 T/L","온양S/S 154kV 장기사용   대체공사","온양S/S 154kV 장기사용   대체공사(3CCT 교체)","2021-06-11 10:00","2021-06-12 10:00","취소","취소","연속"]
[327,"대전충남","천안","아산온양#1 T/L","온양S/S 154kV 장기사용   대체공사","온양S/S 154kV 장기사용   대체공사(3CCT 교체)","2021-06-08 08:00","2021-06-18 10:00","취소","취소","연속"]
[328,"대전충남","천안","온양풍세#1 T/L","온양S/S 154kV 장기사용   대체공사","온양S/S 154kV 장기사용   대체공사(3CCT 교체)","2021-06-09 09:00","2021-06-09 10:00","취소","취소","연속"]
[329,"대전충남","천안","온양풍세#1 T/L","온양S/S 154kV 장기사용   대체공사","온양S/S 154kV 장기사용   대체공사(3CCT 교체)","2021-06-21 10:00","2021-06-22 10:00","취소","취소","연속"]
[330,"대전충남","천안","온양풍세#1 T/L","온양S/S 154kV 장기사용   대체공사","온양S/S 154kV 장기사용   대체공사(3CCT 교체)","2021-06-19 09:00","2021-06-19 10:00","취소","취소","연속"]
[331,"대전충남","천안","아산온양#2 T/L","온양S/S 154kV 장기사용   대체공사","온양S/S 154kV 장기사용   대체공사(3CCT 교체)","2021-06-18 10:00","2021-06-30 10:00","취소","취소","연속"]
[332,"대전충남","천안","천안전의#2 T/L","천안S/S 154kV 천안전의#2 T/L   정밀점검","천안S/S 154kV 천안전의#2 T/L   정밀점검","2021-06-07 09:00","2021-06-09 18:00","2021-06-07 09:00","2021-06-09 18:00","연속"]
[333,"대전충남","천안","인주탕정#1 T/L","154kV 인주-불당T/L C/H 건설공사","임시선로 → 본선로 가선 시행","2021-06-07 07:00","2021-06-15 18:00","2021-06-07 07:00","2021-06-15 18:00","연속"]
[334,"대전충남","천안","서천안탕정#1 T/L","154kV 인주-불당T/L C/H 건설공사","임시선로 → 본선로 가선 시행","2021-06-16 07:00","2021-06-24 18:00","2021-06-16 07:00","2021-06-24 18:00","연속"]
[335,"대전충남","천안","서천안탕정#2 T/L","154kV 인주-불당T/L C/H 건설공사","임시선로 → 본선로 가선 시행","2021-06-07 07:00","2021-06-15 18:00","2021-06-07 07:00","2021-06-15 18:00","연속"]
[336,"대전충남","천안","인주탕정#2 T/L","154kV 인주-불당T/L C/H 건설공사","임시선로 → 본선로 가선 시행","2021-06-16 07:00","2021-06-24 18:00","2021-06-16 07:00","2021-06-24 18:00","연속"]
[337,"대전충남","청양","신서천대천#1 T/L","154kV 대천S/S 미래화 사업","T/L 인출 LS 철거 및 CVT, LA 이설 설치 - 지중 전력구 시공 공간 및 안전이격 확보","2021-06-08 09:00","2021-06-09 18:00","2021-06-22 09:00","2021-06-22 18:00","연속"]
[338,"대전충남","청양","관창대천#1 T/L","154kV 대천S/S 미래화 사업","T/L 인출 LS 철거 및 CVT, LA 이설 설치 - 지중 전력구 시공 공간 및 안전이격 확보","2021-06-16 09:00","2021-06-17 18:00","2021-06-25 09:00","2021-06-25 18:00","연속"]
[339,"대전충남","청양","관창대천#2 T/L","154kV 대천S/S 미래화 사업","T/L 인출 LS 철거 및 CVT, LA 이설 설치 - 지중 전력구 시공 공간 및 안전이격 확보","2021-06-14 09:00","2021-06-15 18:00","2021-06-24 09:00","2021-06-24 18:00","연속"]
[340,"대전충남","청양","신서천대천#2 T/L","154kV 대천S/S 미래화 사업","T/L 인출 LS 철거 및 CVT, LA 이설 설치 - 지중 전력구 시공 공간 및 안전이격 확보","2021-06-10 09:00","2021-06-11 18:00","2021-06-23 09:00","2021-06-23 18:00","연속"]
[341,"대전충남","청양","옥산장항#2 T/L","154kV 동군산-장항T/L 피뢰기 설치공사","4회선구간 송전용 피뢰기 설치( No.18~38호간)를 위한 안전이격거리 확보","2021-06-05 07:00","2021-06-06 18:00","2021-06-05 07:00","2021-06-06 18:00","매일"]
[342,"전북","군산","군공S/S CB 6100","군산P/O 노후배전반 대체공사","- 모선보호반 대체","2021-06-07 09:00","2021-06-11 18:00","2021-06-07 09:00","2021-06-11 18:00","연속"]
[343,"전북","군산","군산서군산#1 T/L","군산P/O 154kV 이상 차단기 점검공사","군산S/S 6C7CB 보통점검 (비상시 즉시 가압가능)","2021-06-17 09:00","2021-06-17 18:00","취소","취소","연속"]
[344,"전북","군산","군산영등#2 T/L","군산-영등T/L 상간스페이서 및 회전스페이서설치공사","상간스페이서설치 : 14~19,41~42호간 (비상시 즉시 가압가능)","2021-06-14 07:00","2021-06-16 18:00","취소","취소","연속"]
[345,"전북","군산","군산이리#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km (비상시 즉시 가압가능)","2021-06-12 07:00","2021-06-15 18:00","취소","취소","매일"]
[346,"전북","군산","군산영등#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km (비상시 즉시 가압가능)","2021-06-12 07:00","2021-06-13 18:00","취소","취소","매일"]
[347,"전북","군산","군산이리#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km (비상시 즉시 가압가능)","2021-06-19 07:00","2021-06-20 18:00","취소","취소","매일"]
[348,"전북","군산","군산영등#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km (비상시 즉시 가압가능)","2021-06-19 07:00","2021-06-21 18:00","취소","취소","매일"]
[349,"전북","군산","군산영등#1 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km (비상시 즉시 가압가능)","2021-06-22 07:00","2021-06-28 18:00","취소","취소","매일"]
[350,"전북","군산","군산이리#1 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km (비상시 즉시 가압가능)","2021-06-26 07:00","2021-06-27 18:00","취소","취소","매일"]
[351,"전북","군산","군산이리#1 T/L","군산-이리T/L 상간스페이서설치공사","상간스페이서설치 : 12~13호간 (비상시 즉시 가압가능)","2021-06-07 07:00","2021-06-07 18:00","2021-06-07 07:00","2021-06-07 18:00","연속"]
[352,"전북","군산","군산이리#2 T/L","군산-이리T/L 상간스페이서설치공사","상간스페이서설치 : 12~13호간 (비상시 즉시 가압가능)","2021-06-08 07:00","2021-06-08 18:00","2021-06-08 07:00","2021-06-08 18:00","연속"]
[353,"전북","군산","군산영등#1 T/L","군산-영등T/L 상간스페이서 및 회전스페이서설치공사","상간스페이서설치 : 12~13호간 (비상시 즉시 가압가능)","2021-06-09 07:00","2021-06-11 18:00","취소","취소","연속"]
[354,"전북","군산","군산서군산#2 T/L","군산P/O 154kV 이상 차단기 점검공사","군산S/S 6D7CB 보통점검 (비상시 즉시 가압가능)","2021-06-18 09:00","2021-06-18 18:00","취소","취소","연속"]
[355,"전북","군산","비응군장#1 T/L","군산P/O 21년도 170kV   정밀점검공사","- 군장S/S 677 CB 정밀점검","2021-06-09 09:00","2021-06-10 18:00","2021-06-09 09:00","2021-06-10 18:00","연속"]
[356,"전북","군산","비응군장#2 T/L","군산P/O 21년도 170kV   정밀점검공사","- 군장S/S 687 CB 정밀점검","2021-06-07 09:00","2021-06-08 18:00","2021-06-07 09:00","2021-06-08 18:00","연속"]
[357,"전북","군산","군공내초#1 T/L","내초S/S 제어케이블 정비공사(SA혼용시스템 설치)","내초S/S 154kV 군공-내초#1T/L SA혼용시스템 제어케이블 설치","2021-06-25 09:00","2021-06-25 18:00","2021-06-25 09:00","2021-06-25 18:00","연속"]
[358,"전북","군산","내초군장#1 T/L","내초S/S 제어케이블 정비공사(SA혼용시스템 설치)","내초S/S 154kV 내초-군장#1T/L SA혼용시스템 제어케이블 설치","2021-06-23 09:00","2021-06-23 18:00","2021-06-23 09:00","2021-06-23 18:00","연속"]
[359,"전북","군산","내초S/S SE열병합#1 T/L CB  ","내초S/S 제어케이블 정비공사(SA혼용시스템 설치)","내초S/S 154kV 내초-SE열병합#1T/L SA혼용시스템 제어케이블 설치","2021-06-29 09:00","2021-06-29 18:00","2021-06-29 09:00","2021-06-29 18:00","연속"]
[360,"전북","군산","내초S/S SE열병합#2 T/L CB","내초S/S 제어케이블 정비공사(SA혼용시스템 설치)","내초S/S 154kV 내초-SE열병합#2T/L SA혼용시스템 제어케이블 설치","2021-06-30 09:00","2021-06-30 18:00","2021-06-30 09:00","2021-06-30 18:00","연속"]
[361,"전북","군산","군공내초#2 T/L","내초S/S 제어케이블 정비공사(SA혼용시스템 설치)","내초S/S 154kV 군공-내초#2T/L SA혼용시스템 제어케이블 설치","2021-06-28 09:00","2021-06-28 18:00","2021-06-28 09:00","2021-06-28 18:00","연속"]
[362,"전북","군산","내초군장#2 T/L","내초S/S 제어케이블 정비공사(SA혼용시스템 설치)","내초S/S 154kV 내초-군장#2T/L SA혼용시스템 제어케이블 설치","2021-06-24 09:00","2021-06-24 18:00","2021-06-24 09:00","2021-06-24 18:00","연속"]
[363,"전북","군산","동군산장항#2 T/L","군산P/O 차단기 조작시험 공사","군산P/O 차단기 조작시험 공사 (비상시 즉시 가압가능)","2021-06-07 09:00","2021-06-07 14:00","취소","취소","연속"]
[364,"전북","군산","동군산장항#1 T/L","154kV 동군산-장항 #1T/L 피뢰기설치공사","피뢰기 설치공사 No.18~38호간 (비상시 즉시 가압가능)","2021-06-05 07:00","2021-06-06 18:00","취소","취소","매일"]
[365,"전북","군산","군산서군산#1 T/L","154kV 군산-서군산T/L 노후취약지지물 교체공사","No.54 노후 취약지지물 교체","2021-06-30 07:00","2021-07-01 18:00","취소","취소","연속"]
[366,"전북","군산","군산서군산#2 T/L","154kV 군산-서군산T/L 노후취약지지물 교체공사","No.54 노후 취약지지물 교체","2021-06-28 07:00","2021-06-29 18:00","취소","취소","연속"]
[367,"전북","군산","서군산소룡#2 T/L","군산PO 기타변전설비 점검공사","군산PO 기타변전설비 점검공사","2021-06-02 09:00","2021-06-03 18:00","2021-06-02 09:00","2021-06-03 18:00","연속"]
[368,"전북","군산","새만금소룡#1 T/L","군산P/O 21년도 170kV   정밀점검공사","- 소룡S/S 687 CB 정밀점검","2021-06-14 09:00","2021-06-15 18:00","2021-06-14 09:00","2021-06-15 18:00","연속"]
[369,"전북","군산","영등팔봉#1 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km (비상시 즉시 가압가능)","2021-06-05 07:00","2021-06-06 18:00","2021-06-05 07:00","2021-06-06 18:00","매일"]
[370,"전북","군산","군산영등#2 T/L","21년도 군산P/O 170kV   정밀점검","- 영등S/S 군산-영등#2 T/L   정밀점검","2021-06-05 09:00","2021-06-06 18:00","2021-06-05 09:00","2021-06-06 18:00","연속"]
[371,"전북","군산","영등팔봉#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km (비상시 즉시 가압가능)","2021-06-05 07:00","2021-06-06 18:00","2021-06-05 07:00","2021-06-06 18:00","매일"]
[372,"전북","군산","이리백산#1 T/L","군산P/O 차단기 조작시험공사","군산P/O 차단기 조작시험공사 (비상시 즉시 가압가능)","2021-06-02 09:30","2021-06-02 10:30","2021-06-02 09:30","2021-06-02 10:30","연속"]
[373,"전북","군산","탄소이리#2 T/L","군산P/O 차단기 조작시험공사","군산P/O 차단기 조작시험공사 (비상시 즉시 가압가능)","2021-06-01 10:30","2021-06-01 12:00","2021-06-01 10:30","2021-06-01 12:00","연속"]
[374,"전북","군산","탄소이리#1 T/L","군산P/O 차단기 조작시험공사","군산P/O 차단기 조작시험공사 (비상시 즉시 가압가능)","2021-06-01 09:30","2021-06-01 10:30","2021-06-01 09:30","2021-06-01 10:30","연속"]
[375,"전북","군산","이리백산#2 T/L","군산P/O 차단기 조작시험공사","군산P/O 차단기 조작시험공사 (비상시 즉시 가압가능)","2021-06-02 10:30","2021-06-02 12:00","2021-06-02 10:30","2021-06-02 12:00","연속"]
[376,"전북","군산","팔봉두마#2 T/L","군산P/O 차단기 조작시험공사","군산P/O 차단기 조작시험공사 (비상시 즉시 가압가능)","2021-06-01 10:30","2021-06-01 12:00","2021-06-01 10:30","2021-06-01 12:00","연속"]
[377,"전북","군산","팔봉두마#1 T/L","군산P/O 차단기 조작시험공사","군산P/O 차단기 조작시험공사 (비상시 즉시 가압가능)","2021-06-01 09:30","2021-06-01 10:30","2021-06-01 09:30","2021-06-01 10:30","연속"]
[378,"전북","김제","고창홍농 T/L","345kV 신남원-한빛T/L 항공장애표시도장","No32~39호 병가구간 휴전 (비상시 즉시 가압가능)","2021-06-07 09:00","2021-06-18 18:00","취소","취소","연속"]
[379,"전북","김제","고창영광 T/L","관내S/S 154kV 차단기 보통점검","관내S/S 154kV 차단기 보통점검","2021-06-04 09:00","2021-06-04 18:00","취소","취소","연속"]
[380,"전북","김제","정주고창#2 T/L","고창S/S 정주-고창#2T/L   가스누기 보수공사","  접지단자, O-ring 등 부품교체 및 점검","2021-06-01 09:00","2021-06-02 18:00","취소","취소","연속"]
[381,"전북","김제","김제부안#2 T/L","154kV 김제-부안#2T/L 초기점검","154kV 김제-부안#2T/L 초기점검(No.1~65호) (비상시 즉시 가압가능)","2021-06-21 09:00","2021-06-25 18:00","2021-06-21 09:00","2021-06-25 18:00","매일"]
[382,"전북","김제","김제부안#1 T/L","154kV 김제-부안#1T/L 초기점검","154kV 김제-부안#2T/L 초기점검(No.1~65호) (비상시 즉시 가압가능)","2021-06-14 09:00","2021-06-18 18:00","2021-06-14 09:00","2021-06-18 18:00","매일"]
[383,"전북","김제","신김제전주#1 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사"," OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km (비상시 즉시 가압가능)","2021-06-01 07:00","2021-06-05 18:00","2021-06-01 07:00","2021-06-05 18:00","매일"]
[384,"전북","김제","신김제정공#1 T/L","154kV 신김제-정공T/L피뢰기 설치공사","No.6~88호 피뢰기 설치 (비상시 즉시 가압가능)","2021-06-01 09:00","2021-06-11 18:00","2021-06-01 09:00","2021-06-11 18:00","연속"]
[385,"전북","김제","정공S/S 154kV #66BUS","정공S/S 170kV   교체공사","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-02 09:00","2021-06-04 13:00","2021-06-02 09:00","2021-06-04 13:00","연속"]
[386,"전북","김제","정공S/S CB 6100","정공S/S 170kV   교체공사","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-02 09:00","2021-06-20 18:00","2021-06-02 09:00","2021-06-20 18:00","연속"]
[387,"전북","김제","정공S/S 154kV #66BUS","정공S/S 170kV   교체공사","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-21 09:00","2021-06-23 13:00","2021-06-21 09:00","2021-06-23 13:00","연속"]
[388,"전북","김제","정공S/S 154kV #65BUS","정공S/S 170kV   교체공사","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-21 09:00","2021-06-23 13:00","2021-06-21 09:00","2021-06-23 13:00","연속"]
[389,"전북","김제","신김제정공#1 T/L","정공S/S 170kV   교체공사 무부하가압","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-23 11:00","2021-06-23 13:00","2021-06-23 11:00","2021-06-23 13:00","연속"]
[390,"전북","김제","정공S/S 154kV #61BUS","정공S/S 170kV   교체공사","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-23 13:00","2021-06-28 13:00","2021-06-23 13:00","2021-06-28 13:00","연속"]
[391,"전북","김제","정공S/S 154kV #60BUS","정공S/S 170kV   교체공사","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-23 13:00","2021-06-28 13:00","2021-06-23 13:00","2021-06-28 13:00","연속"]
[392,"전북","김제","신김제정공#1 T/L","정공S/S 170kV   교체공사 무부하가압","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-27 13:00","2021-06-28 13:00","2021-06-27 13:00","2021-06-28 13:00","연속"]
[393,"전북","김제","정공S/S 154kV #65BUS","정공S/S 170kV   교체공사","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-28 13:00","2021-07-11 18:00","2021-06-28 13:00","2021-07-11 18:00","연속"]
[394,"전북","김제","정공S/S 154kV #66BUS","정공S/S 170kV   교체공사","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-28 13:00","2021-07-11 18:00","2021-06-28 13:00","2021-07-11 18:00","연속"]
[395,"전북","김제","신김제정공#1 T/L","정공S/S 170kV   교체공사 무부하가압","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-04 11:00","2021-06-04 13:00","2021-06-04 11:00","2021-06-04 13:00","연속"]
[396,"전북","김제","정공S/S 154kV #60BUS","정공S/S 170kV   교체공사","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-04 13:00","2021-06-09 13:00","2021-06-04 13:00","2021-06-09 13:00","연속"]
[397,"전북","김제","정공S/S 154kV #61BUS","정공S/S 170kV   교체공사","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-04 13:00","2021-06-09 13:00","2021-06-04 13:00","2021-06-09 13:00","연속"]
[398,"전북","김제","정공S/S 154kV #65BUS","정공S/S 170kV   교체공사","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-09 13:00","2021-06-20 18:00","2021-06-09 13:00","2021-06-20 18:00","연속"]
[399,"전북","김제","정공S/S 154kV #66BUS","정공S/S 170kV   교체공사","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-09 13:00","2021-06-20 18:00","2021-06-09 13:00","2021-06-20 18:00","연속"]
[400,"전북","김제","정공칠보HP T/L","정공S/S 170kV   교체공사","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사 (정공-정주#1 과 정공-칠보수력 둘중 하나 시행가능)","2021-06-02 09:00","2021-06-20 18:00","2021-06-02 09:00","2021-06-20 18:00","연속"]
[401,"전북","김제","정공S/S 154kV #65BUS","정공S/S 170kV   교체공사","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-02 09:00","2021-06-04 13:00","2021-06-02 09:00","2021-06-04 13:00","연속"]
[402,"전북","김제","정공S/S CB 6200","정공S/S 170kV   교체공사","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-02 09:00","2021-06-20 18:00","2021-06-02 09:00","2021-06-20 18:00","연속"]
[403,"전북","김제","정공S/S CB 6100","정공S/S 170kV   교체공사","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-21 09:00","2021-07-11 18:00","2021-06-21 09:00","2021-07-11 18:00","연속"]
[404,"전북","김제","정공정주#1 T/L","정공S/S 170kV   교체공사","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사 (정공-정주#1 과 정공-칠보수력 둘중 하나 시행가능)","2021-06-02 09:00","2021-06-20 18:00","2021-06-02 09:00","2021-06-20 18:00","연속"]
[405,"전북","김제","정공S/S CB 6200","정공S/S 170kV   교체공사","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-21 09:00","2021-07-11 18:00","2021-06-21 09:00","2021-07-11 18:00","연속"]
[406,"전북","김제","정공담양 T/L","정공S/S 170kV   교체공사","170kV   7BAY 철거 및 설치 170kV   3BAY 설치 기타부대공사","2021-06-21 09:00","2021-07-11 18:00","2021-06-21 09:00","2021-07-11 18:00","연속"]
[407,"전북","직할","동전주S/S CB 6100","동전주S/S 170kV   교체공사","○ 170kV   7Bay 철거 및 설치 ○ 170kV   2Bay 설치 ○ 기타 부대공사","2021-06-07 09:00","2021-06-26 18:00","2021-06-07 09:00","2021-06-26 18:00","연속"]
[408,"전북","직할","동전주북전주#1 T/L","동전주S/S 장기사용 170kV   교체공사","○ 170kV   7Bay 철거 및 설치 ○ 170kV   2Bay 설치 ○ 기타 부대공사","2021-06-07 09:00","2021-06-26 18:00","2021-06-07 09:00","2021-06-26 18:00","연속"]
[409,"전북","직할","동전주태평#2 T/L","동전주S/S 170kV   교체공사(인근bay휴전,시험가압)","○ 170kV   7Bay 철거 및 설치 ○ 170kV   2Bay 설치 ○ 기타 부대공사","2021-06-07 09:00","2021-06-26 18:00","2021-06-07 09:00","2021-06-26 18:00","연속"]
[410,"전북","직할","신김제동전주#2 T/L","동전주S/S 장기사용 170kV   교체공사(인출변경)","○ 170kV   7Bay 철거 및 설치 ○ 170kV   2Bay 설치 ○ 기타 부대공사","2021-06-28 09:00","2021-07-01 18:00","2021-06-28 09:00","2021-07-01 18:00","연속"]
[411,"전북","직할","무주용담수력 T/L","(3차)무주S/S 154kV   교체공사(시험가압)","*** 154kV #60BUS 무부하 가압 선로 - 170kV   50kA(1250/2000A)   5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2021-06-26 15:00","2021-06-27 15:00","취소","취소","연속"]
[412,"전북","직할","무주S/S 154kV #1 BUS","(3차)무주S/S 154kV   교체공사(Main 교체)","- 170kV   50kA(1250/2000A)   5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2021-06-27 15:00","2021-07-11 15:00","취소","취소","연속"]
[413,"전북","직할","금산무주#2 T/L","(2차)무주S/S 154kV   교체공사(안전이격)","- 170kV   50kA(1250/2000A)   5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2021-06-05 11:00","2021-06-05 13:00","2021-06-05 11:00","2021-06-05 13:00","연속"]
[414,"전북","직할","무주용담수력 T/L","(2차)무주S/S 154kV   교체공사(안전이격)","- 170kV   50kA(1250/2000A)   5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2021-06-05 09:00","2021-06-05 11:00","2021-06-05 09:00","2021-06-05 11:00","연속"]
[415,"전북","직할","무주S/S 154kV #2 BUS","(3차)무주S/S 154kV   교체공사(Main 교체)","- 170kV   50kA(1250/2000A)   5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2021-06-17 10:00","2021-06-27 15:00","취소","취소","연속"]
[416,"전북","직할","무주진안 T/L","(3차)무주S/S 154kV   교체공사(시험가압)","*** 154kV #60BUS 무부하 가압 선로 - 170kV   50kA(1250/2000A)   5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2021-06-26 15:00","2021-06-27 15:00","취소","취소","연속"]
[417,"전북","직할","금산무주#2 T/L","(3차)무주S/S 154kV   교체공사(Main 교체)","- 170kV   50kA(1250/2000A)   5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2021-06-17 10:00","2021-07-25 15:00","취소","취소","연속"]
[418,"전북","직할","무주S/S CB 6100","(3차)무주S/S 154kV   교체공사(Main 교체)","- 170kV   50kA(1250/2000A)   5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2021-06-17 10:00","2021-07-25 15:00","취소","취소","연속"]
[419,"전북","직할","금산무주#1 T/L","(3차)무주S/S 154kV   교체공사(안전이격)","- 170kV   50kA(1250/2000A)   5CCT 대체 (대상설비 : 금산-무주#1, #2T/L, #1, #2 M.Tr 1차, BUS-TIE, BUS-PT)","2021-06-19 11:00","2021-06-19 13:00","취소","취소","연속"]
[420,"전북","직할","팔봉봉동#2 T/L","관내S/S 170kV   차단기 점검공사","154kV 차단기 보통점검 (비상시 즉시 가압가능)","2021-06-03 09:00","2021-06-03 18:00","2021-06-03 09:00","2021-06-03 18:00","연속"]
[421,"전북","직할","팔봉봉동#1 T/L","관내S/S 170kV   차단기 점검공사","154kV 차단기 보통점검 (비상시 즉시 가압가능)","2021-06-02 09:00","2021-06-02 18:00","2021-06-02 09:00","2021-06-02 18:00","연속"]
[422,"전북","직할","북전주봉동#2 T/L","2021년 전북 직할 관내S/S 170kV   정밀점검","- 170kV   CB 및 상부부스 정밀점검","2021-06-14 09:00","2021-06-16 18:00","2021-06-14 09:00","2021-06-16 18:00","연속"]
[423,"전북","직할","북전주진안 T/L","2021년 전북 직할 관내S/S 170kV   정밀점검","- 170kV   CB 및 상부부스 정밀점검","2021-06-07 09:00","2021-06-09 18:00","2021-06-07 09:00","2021-06-09 18:00","연속"]
[424,"전북","군산","군산동군산#1 T/L","송전선로 자기애자 교체공사","송전선로 자기애자 교체공사","2021-06-17 09:00","2021-06-17 18:00","2021-06-17 09:00","2021-06-17 18:00","연속"]
[425,"전북","직할","무주진안 T/L","2021년 전북 직할 관내S/S 170kV   정밀점검","- 170kV   CB 및 상부부스 정밀점검","2021-06-10 09:00","2021-06-12 18:00","2021-06-10 09:00","2021-06-12 18:00","연속"]
[426,"광주전남","강진","나주금천#2 T/L","154kV 신화순-나주T/L 지장철탑 이설공사","강진광주간 고속도로 관련 지장철탑 이설 154kV 신화순-나주T/L 52-55호 (154kV 나주-금천T/L 89-92호 병가) 철탑 1기 철거, 1기 신설(53호), 임시철탑 1기","2021-06-05 08:00","2021-06-10 18:00","2021-06-05 08:00","2021-06-10 18:00","연속"]
[427,"광주전남","강진","강진남창#1 T/L","154kV 남창S/S  화 공사","○ 제어케이블 철거, 설치 및 결선 × 1식 ○ 기타 부대작업 × 1식","2021-06-07 09:00","2022-06-30 18:00","2021-06-07 09:00","2022-06-30 18:00","연속"]
[428,"광주전남","강진","남창해남CS#1 T/L","154kV 남창S/S  화 공사(일반)","○ #2M.Tr 인출변경(옥외철구→ ) 상체크","2021-06-21 09:00","2021-06-21 18:00","2021-06-21 09:00","2021-06-21 18:00","연속"]
[429,"광주전남","강진","남창완도#2 T/L","154kV 남창S/S  화 공사","○ 제어케이블 철거, 설치 및 결선 × 1식 ○ 기타 부대작업 × 1식","2021-06-07 09:00","2022-06-30 18:00","2021-06-07 09:00","2022-06-30 18:00","연속"]
[430,"광주전남","강진","남창해남CS#1 T/L","154kV 남창S/S  화 공사","○ 남창S/S  (1차분) 무부하가압","2021-06-03 09:00","2021-06-04 18:00","2021-06-03 09:00","2021-06-04 18:00","연속"]
[431,"광주전남","강진","신강진대불#1 T/L","2020~21년 송전정비회사 총액공사","[비상시 즉시가압 가능] 성능저하국산애자 교체(고정형 폴리머 점퍼지지 애자 설치) 신강진대불#2 No.37,40,52(16련)","2021-06-07 07:00","2021-06-08 18:00","2021-06-07 07:00","2021-06-08 18:00","매일"]
[432,"광주전남","강진","진도진도CS#2 T/L","21년 강진전력지사   보통점검","진도C/S 진도-진도C/S #2T/L   보통점검 비상시 즉시가압 가능(20분이내)","2021-06-03 10:00","2021-06-03 18:00","취소","취소","연속"]
[433,"광주전남","강진","해남진도#2 T/L","21년 강진전력지사   보통점검","해남S/S 해남진도#2T/L   보통점검(비상시 20분내 즉시가압 가능)","2021-06-16 09:00","2021-06-17 18:00","2021-06-16 09:00","2021-06-17 18:00","연속"]
[434,"광주전남","강진","해남진도#1 T/L","21년 강진전력지사   보통점검","해남S/S 해남진도#1T/L   보통점검(비상시 20분내 즉시가압 가능)","2021-06-14 09:00","2021-06-15 18:00","2021-06-14 09:00","2021-06-15 18:00","연속"]
[435,"광주전남","광주","신광주곡성#1 T/L","154kV 순창분기T/L 건설공사","○ 위 치 : 154kV 신광주-곡성T/L No.75,77 ~ 신설 154kV 순창S/S ○ 규 모 : ACSR 410×S×4C×.0853km, 철탑 2기 ○ 작업내용 : 본선로 구성(기설 No.75,77 ~ 신설 순창S/S) - 가압 : 신광주-순창, 순창-곡성#1T/L ○ 비상시 즉시가압여부 : 곤란","2021-06-25 07:00","2021-07-07 18:00","2021-06-26 07:00","2021-07-14 18:00","연속"]
[436,"광주전남","광주","신광주곡성#2 T/L","154kV 순창분기T/L 건설공사","○ 위 치 : 154kV 신광주-곡성T/L No.75,77 ~ 신설 154kV 순창S/S ○ 규 모 : ACSR 410×S×4C×.0853km, 철탑 2기 ○ 작업내용 : 본선로 구성(기설 No.75,77 ~ 신설 순창S/S) - 가압 : 신광주-순창, 순창-곡성#2T/L ○ 비상시 즉시가압여부 : 곤란","2021-06-01 07:00","2021-06-24 18:00","2021-06-01 07:00","2021-06-25 18:00","연속"]
[437,"광주전남","광주","정공담양 T/L","'20~21년 광주전력지사 변전정비회사 총액공사","-담양S/S 담양-김제T/L LA 보통점검 -담양S/S 정공-담양T/L LA 보통점검","2021-06-10 13:00","2021-06-10 17:00","2021-06-07 12:00","2021-06-07 15:00","연속"]
[438,"광주전남","광주","담양김제 T/L","'20~21년 광주전력지사 변전정비회사 총액공사","-담양S/S 담양-김제T/L LA 보통점검 -담양S/S 정공-담양T/L LA 보통점검","2021-06-10 09:00","2021-06-10 13:00","2021-06-07 09:00","2021-06-07 12:00","연속"]
[439,"광주전남","목포","나주엄다#2 T/L","세니온제 송전선로 보호 IED 성능개선","IED 펌웨어 업데이트 및 내부 콘덴서 교체 ※비상시 20분내 즉시가압 가능","2021-06-04 14:00","2021-06-04 18:00","2021-06-04 14:00","2021-06-04 18:00","연속"]
[440,"광주전남","목포","나주엄다#1 T/L","세니온제 송전선로 보호 IED 성능개선","IED 펌웨어 업데이트 및 내부 콘덴서 교체 ※비상시 20분내 즉시가압 가능","2021-06-04 09:00","2021-06-04 14:00","2021-06-04 09:00","2021-06-04 14:00","연속"]
[441,"광주전남","목포","고창영광 T/L","2021년 목포전력지사 개폐장치 보통점검 및 전자변 교체공사","2021년 목포전력지사 개폐장치 보통점검 및 전자변 교체공사 비상시 즉시가압 불가","2021-06-01 10:00","2021-06-01 18:00","취소","취소","연속"]
[442,"광주전남","목포","고창홍농 T/L","2020-21년 목포전력지사 변전정비회사 총액공사","변전설비 기기점검 비상 시 20분내 가압가능","2021-06-17 09:00","2021-06-17 18:00","취소","취소","연속"]
[443,"광주전남","순천","순천율촌#1 T/L"," 순천-율촌 #1T/L 정밀점검","21년 가공송전 순시점검 위탁공사 순천-율촌 #1T/L 정밀점검 및 절연저항측정","2021-06-22 08:00","2021-06-22 18:00","2021-06-28 08:00","2021-06-28 18:00","연속"]
[444,"광주전남","순천","순천율촌#2 T/L"," 순천-율촌 #2T/L 정밀점검","21년 가공송전 순시점검 위탁공사 순천-율촌 #1T/L 정밀점검 및 절연저항측정","2021-06-23 08:00","2021-06-23 18:00","2021-06-29 08:00","2021-06-29 18:00","연속"]
[445,"광주전남","순천","여천여수산단#2 T/L","20-21년 순천전력지사 변전협력회사 총액공사","여천 여천-여수산단 #2TL   타임측정 비상시 즉시가압 가능","2021-06-07 14:00","2021-06-07 18:00","2021-06-07 14:00","2021-06-07 18:00","연속"]
[446,"광주전남","순천","여천여수산단#1 T/L","20-21년 순천전력지사 변전협력회사 총액공사","여수산단 여천-여수산단 #1TL   보통점검, 여천 여천-여수산단 #1TL   타임측정, 비상시 즉시가압 가능","2021-06-07 09:00","2021-06-07 14:00","2021-06-07 09:00","2021-06-07 14:00","연속"]
[447,"광주전남","순천","여수TP화치#1 T/L","345kV 광양CC-신여수T/L 건설공사","1. 지지물 : 철탑 24기(가철탑 4기 별도) 2. 전력선 : ACSR/AW 480㎟×2B×2C 8.6km","2021-06-11 07:00","2021-06-21 18:00","2021-06-11 07:00","2021-06-21 18:00","연속"]
[448,"광주전남","순천","호남TP여수TP#2 T/L","345kV 광양CC-신여수T/L 건설공사","가선로를 본선로로 구성 - 154kV 호남TP-여수TP T/L No.13-여수TP ST간 전력선 이동","2021-06-29 07:00","2021-07-01 18:00","2021-06-29 07:00","2021-07-01 18:00","연속"]
[449,"광주전남","순천","호남TP여수TP#1 T/L","345kV 광양CC-신여수T/L 건설공사","가선로를 본선로로 구성 - 154kV 호남TP-여수TP T/L No.13-여수TP ST간 전력선 이동","2021-06-26 07:00","2021-06-28 18:00","2021-06-26 07:00","2021-06-28 18:00","연속"]
[450,"광주전남","순천","여수TP화치#2 T/L","345kV 광양CC-신여수T/L 건설공사","1. 지지물 : 철탑 24기(가철탑 4기 별도) 2. 전력선 : ACSR/AW 480㎟×2B×2C 8.6km","2021-06-22 07:00","2021-06-25 18:00","2021-06-22 07:00","2021-06-25 18:00","연속"]
[451,"광주전남","순천","율촌화치#1 T/L","154kV 율촌S/S 세풍-율촌T/L 증설공사","○ 170kV   x 2CCT 설치 ○ 송전선로 보호반 x 2면 설치 ○ 기타 부대공사 x 1식 ○ 공사감독 : 조연진","2021-06-12 18:00","2021-06-14 18:00","2021-06-12 18:00","2021-06-14 18:00","연속"]
[452,"광주전남","순천","율촌민자#1 T/L","154kV 율촌S/S 세풍-율촌T/L 증설공사","○ 170kV   x 2CCT 설치 ○ 송전선로 보호반 x 2면 설치 ○ 기타 부대공사 x 1식 ○ 공사감독 : 조연진","2021-06-10 09:00","2021-06-12 18:00","2021-06-10 09:00","2021-06-12 18:00","연속"]
[453,"광주전남","순천","율촌민자#2 T/L","154kV 율촌S/S 세풍-율촌T/L 증설공사","○ 170kV   x 2CCT 설치 ○ 송전선로 보호반 x 2면 설치 ○ 기타 부대공사 x 1식 ○ 공사감독 : 조연진","2021-06-07 09:00","2021-06-09 18:00","2021-06-07 09:00","2021-06-09 18:00","연속"]
[454,"광주전남","순천","율촌S/S 154kV #2 BUS","154kV 율촌S/S 세풍-율촌T/L 증설공사","○ 170kV   x 2CCT 설치 ○ 송전선로 보호반 x 2면 설치 ○ 기타 부대공사 x 1식 ○ 공사감독 : 조연진","2021-06-07 09:00","2021-06-14 18:00","2021-06-07 09:00","2021-06-14 18:00","연속"]
[455,"대구","경산","진량노변 T/L","2020-21년 경산전력지사 가공송전정비회사 총액공사","- 피뢰기 설치 및 국산애자교체 안전확보","2021-06-06 07:30","2021-06-06 18:00","2021-06-06 07:30","2021-06-06 18:00","연속"]
[456,"대구","경산","신경산노변 T/L","2020-21년 경산전력지사 가공송전정비회사 총액공사","- 피뢰기 설치 및 국산애자교체","2021-06-06 07:30","2021-06-06 12:00","2021-06-06 07:30","2021-06-06 12:00","연속"]
[457,"대구","경산","범물남대구#2 T/L","범물S/S 154kV   교체공사(4차시)","범물S/S 154kV   교체공사(4차시 TEST)","2021-06-07 18:00","2021-06-08 09:00","2021-06-07 18:00","2021-06-08 09:00","연속"]
[458,"대구","경산","범물남대구#2 T/L","범물S/S 154kV   교체공사(4차시)","범물S/S 154kV   교체공사(4차시 TEST)","2021-06-18 18:00","2021-06-23 18:00","2021-06-18 18:00","2021-06-23 18:00","연속"]
[459,"대구","경산","범물S/S 154kV #2 BUS","범물S/S 154kV   교체공사(4차시)","범물S/S 154kV   교체공사(4차시)","2021-06-08 09:00","2021-06-21 09:00","2021-06-08 09:00","2021-06-21 09:00","연속"]
[460,"대구","경산","신서하양#2 T/L","20~21년 경산전력지사 변전정비회사 총액공사","-   보통점검","2021-06-14 09:30","2021-06-14 18:00","취소","취소","연속"]
[461,"대구","경산","신서하양#1 T/L","20~21년 경산전력지사 변전정비회사 총액공사","-   보통점검","2021-06-17 09:30","2021-06-18 18:00","2021-06-17 09:30","2021-06-18 18:00","연속"]
[462,"대구","달성","고령논공#1 T/L","논공S/S 고령-논공#1T/L   정밀점검","논공S/S 고령-논공#1T/L   정밀점검","2021-06-05 09:00","2021-06-06 18:00","2021-06-05 09:00","2021-06-06 18:00","연속"]
[463,"대구","달성","고령논공#2 T/L","논공S/S 고령-논공#2T/L   정밀점검","논공S/S 고령-논공#2T/L   정밀점검","2021-06-12 09:00","2021-06-13 18:00","2021-06-12 09:00","2021-06-13 18:00","연속"]
[464,"대구","달성","다산강창#2 T/L","강창S/S 다산-강창#2T/L 차단기 동작특성시험","강창S/S 다산-강창#2T/L 차단기 동작특성시험","2021-06-03 09:00","2021-06-03 18:00","2021-06-03 09:00","2021-06-03 18:00","연속"]
[465,"대구","달성","강창성서#1 T/L","강창S/S 강창-성서#1T/L   보통점검","강창S/S 강창-성서#1T/L   보통점검","2021-06-27 09:00","2021-06-27 18:00","2021-06-27 09:00","2021-06-27 18:00","연속"]
[466,"대구","달성","다산강창#1 T/L","강창S/S 다산-강창#1T/L 차단기 동작특성시험","강창S/S 다산-강창#1T/L 차단기 동작특성시험","2021-06-02 09:00","2021-06-02 18:00","2021-06-02 09:00","2021-06-02 18:00","연속"]
[467,"대구","달성","강창성서#2 T/L","강창S/S 강창-성서#2T/L   보통점검","강창S/S 강창-성서#2T/L   보통점검","2021-06-26 09:00","2021-06-26 18:00","2021-06-26 09:00","2021-06-26 18:00","연속"]
[468,"대구","달성","고령쌍림#1 T/L","154kV 고령-쌍림T/L 취약지지물 교체공사","철탑 2기 철거, 2기 설치, 전력선 교체(1.727km, ACSR330㎟*S*2C)","2021-06-21 07:00","2021-06-25 18:00","2021-06-28 07:00","2021-07-02 18:00","연속"]
[469,"대구","달성","고령쌍림#2 T/L","154kV 고령-쌍림T/L 취약지지물 교체공사","철탑 2기 철거, 2기 설치, 전력선 교체(1.727km, ACSR330㎟*S*2C)","2021-06-26 07:00","2021-06-30 18:00","2021-07-03 07:00","2021-07-07 18:00","연속"]
[470,"대구","달성","창녕구지#2 T/L","구지S/S 창넝-구지#2T/L   보통점검","구지S/S 창넝-구지#2T/L   보통점검","2021-06-01 09:00","2021-06-01 18:00","2021-06-01 09:00","2021-06-01 18:00","연속"]
[471,"대구","달성","다사달서#1 T/L","154kV 팔달-강창 지장송전선로 지중화공사(가공)","No.21~25 전력선 철거 및 설치 안전이격","2021-06-08 08:00","2021-06-15 18:00","2021-06-08 08:00","2021-06-15 18:00","연속"]
[472,"대구","달성","다사달서#2 T/L","154kV 팔달-강창 지장송전선로 지중화공사(가공)","No.21~25 전력선 철거 및 설치 안전이격","2021-06-14 08:00","2021-06-15 18:00","2021-06-14 08:00","2021-06-15 18:00","연속"]
[473,"대구","달성","달성상인#2 T/L","달성S/S 달성-상인#2T/L 차단기 동작특성시험","달성S/S 달성-상인#2T/L 차단기 동작특성시험","2021-06-22 09:00","2021-06-22 18:00","2021-06-22 09:00","2021-06-22 18:00","연속"]
[474,"대구","달성","달성상인#1 T/L","달성S/S 달성-상인#1T/L 차단기 동작특성시험","달성S/S 달성-상인#1T/L 차단기 동작특성시험","2021-06-21 09:00","2021-06-21 18:00","2021-06-21 09:00","2021-06-21 18:00","연속"]
[475,"대구","달성","대구범물#1 T/L","대구S/S 60-65 모선보호반 대체","대구S/S 60-65 모선보호반 대체","2021-06-30 10:00","2021-06-30 10:30","2021-06-30 10:00","2021-06-30 10:30","연속"]
[476,"대구","달성","대구자인#1 T/L","대구S/S 60-65 모선보호반 대체","대구S/S 60-65 모선보호반 대체","2021-06-30 10:30","2021-06-30 11:00","2021-06-30 10:30","2021-06-30 11:00","연속"]
[477,"대구","달성","대구자인#2 T/L","대구S/S 60-65 모선보호반 대체","대구S/S 60-65 모선보호반 대체","2021-06-30 11:00","2021-06-30 11:30","2021-06-30 11:00","2021-06-30 11:30","연속"]
[478,"대구","달성","상인봉덕#1 T/L","봉덕S/S 상인-봉덕#1T/L   보통점검","봉덕S/S 상인-봉덕#1T/L   보통점검","2021-06-10 09:00","2021-06-10 18:00","2021-06-10 09:00","2021-06-10 18:00","연속"]
[479,"대구","달성","상인봉덕#2 T/L","봉덕S/S 상인-봉덕#2T/L   보통점검","봉덕S/S 상인-봉덕#2T/L   보통점검","2021-06-11 09:00","2021-06-11 18:00","2021-06-11 09:00","2021-06-11 18:00","연속"]
[480,"대구","직할","공평서침산 T/L","21-22년 대구본부 직할 지중송전 위탁정비공사","ㅇ 절연유 열화진단 시행","2021-06-27 09:00","2021-06-27 18:00","취소","취소","연속"]
[481,"대구","직할","공평침산 T/L","21-22년 대구본부 직할 지중송전 위탁정비공사","ㅇ 절연유 열화진단 시행","2021-06-26 09:00","2021-06-26 18:00","2021-06-26 09:00","2021-06-26 18:00","연속"]
[482,"대구","직할","동인내당#2 T/L","21-22년 대구본부 직할 지중송전 위탁정비공사","ㅇ 절연유 열화진단 시행","2021-06-17 09:00","2021-06-18 18:00","2021-06-17 09:00","2021-06-18 18:00","연속"]
[483,"대구","직할","동인내당#1 T/L","21-22년 대구본부 직할 지중송전 위탁정비공사","ㅇ 절연유 열화진단 시행","2021-06-09 09:00","2021-06-10 18:00","2021-06-09 09:00","2021-06-10 18:00","연속"]
[484,"대구","직할","시지효목#2 T/L","효목S/S 시지-효목#2   보통점검","효목S/S 시지-효목#2   보통점검","2021-06-23 09:30","2021-06-23 18:00","2021-06-23 09:30","2021-06-23 18:00","연속"]
[485,"대구","직할","시지효목#1 T/L","효목S/S 시지-효목#1   보통점검","효목S/S 시지-효목#1   보통점검","2021-06-22 09:30","2021-06-22 18:00","2021-06-22 09:30","2021-06-22 18:00","연속"]
[486,"대구","칠곡","북대구구암#2 T/L","구암S/S 154kV 647   정밀점검","구암S/S 154kV 647   정밀점검","2021-06-07 09:30","2021-06-09 18:00","2021-06-07 09:30","2021-06-09 18:00","연속"]
[487,"대구","칠곡","관음구암#2 T/L","구암S/S 154kV 647  정밀점검 무부하가압","구암S/S 154kV 647  정밀점검 무부하가압","2021-06-08 13:00","2021-06-09 18:00","2021-06-08 13:00","2021-06-09 18:00","연속"]
[488,"대구","칠곡","김천금릉#1 T/L","'20~21년도 칠곡전력지사 가공송전정비회사 총액공사","성주-금릉T/L 병가철탑 작업관련 안전확보","2021-06-07 08:00","2021-06-07 18:00","2021-06-07 08:00","2021-06-07 18:00","연속"]
[489,"대구","칠곡","김천금릉#1 T/L","김천S/S 6179   차단부 정밀점검(무부하)","김천S/S 6179   차단부 정밀점검(무부하)","2021-06-15 15:00","2021-06-15 18:00","2021-06-15 15:00","2021-06-15 18:00","연속"]
[490,"대구","칠곡","북대구팔달#1 T/L","북대구S/S 697  차단부 정밀점검","북대구S/S 697  차단부 정밀점검","2021-06-17 09:30","2021-06-18 18:00","2021-06-17 09:30","2021-06-18 18:00","연속"]
[491,"대구","칠곡","북대구팔달#2 T/L","북대구S/S 6A7  차단부 정밀점검","북대구S/S 6A7  차단부 정밀점검","2021-06-21 09:30","2021-06-22 18:00","2021-06-21 09:30","2021-06-22 18:00","연속"]
[492,"대구","칠곡","북대구왜관#2 T/L","서대구S/S 170kV   설치공사","170kV   부싱조립 안전이격 확보","2021-06-16 08:00","2021-06-16 12:00","2021-06-16 08:00","2021-06-16 12:00","연속"]
[493,"대구","칠곡","서대구성주#2 T/L","'20~21년도 칠곡전력지사 가공송전정비회사 총액공사","154kV서대구-성주#2T/L피뢰기설치","2021-06-14 12:00","2021-06-18 18:00","2021-06-14 12:00","2021-06-18 18:00","연속"]
[494,"대구","칠곡","성주금릉#1 T/L","'20~21년도 칠곡전력지사 가공송전정비회사 총액공사","애자련 교체","2021-06-07 08:00","2021-06-07 18:00","2021-06-07 08:00","2021-06-07 18:00","연속"]
[495,"대구","칠곡","칠곡인동#2 T/L","칠곡전력지사 가공송전 순시점검 위탁공사","154kV 칠곡인동TL 정밀점검","2021-06-01 08:30","2021-06-09 18:00","2021-06-01 08:30","2021-06-09 18:00","연속"]
[496,"경북","영주","봉화현종산풍력 T/L","2021년 영주전력지사 170kV   정밀점검","- 617 정밀점검","2021-06-24 08:00","2021-06-26 18:00","2021-06-24 08:00","2021-06-26 18:00","연속"]
[497,"경북","영주","예천점촌#1 T/L","154kV 신영주-영주 등 3개T/L 피뢰기설치공사","154kV 신영주-영주 등 3개T/L 피뢰기설치공사","2021-06-07 09:00","2021-06-08 18:00","2021-06-25 09:00","2021-06-26 18:00","매일"]
[498,"경북","영주","동상주점촌#2 T/L","2021년 영주전력지사 170kV   정밀점검","2021년 영주전력지사 170kV   정밀점검","2021-06-23 09:00","2021-06-23 18:00","취소","취소","연속"]
[499,"경북","직할","안동동안동#1 T/L","20-21년 경북직할 송전정비회사 총액공사","성능저하 점퍼지지애자 교체 No.2,4,21,24 수직수평 추락방지장치 설치 No.10,11","2021-06-07 08:00","2021-06-10 18:00","2021-06-07 08:00","2021-06-10 18:00","연속"]
[500,"경북","직할","동안동임하HP T/L","20-21년 경북직할 송전정비회사 총액공사","성능저하 점퍼지지애자 교체 No.S/T,1,33","2021-06-10 09:00","2021-06-10 18:00","2021-06-10 09:00","2021-06-10 18:00","연속"]
[501,"경북","직할","안동동안동#2 T/L","20-21년 경북직할 송전정비회사 총액공사","성능저하 점퍼지지애자 교체 No.7 수직수평 추락방지장치 설치 No.10,11","2021-06-11 08:00","2021-06-11 18:00","2021-06-11 08:00","2021-06-11 18:00","연속"]
[502,"경북","직할","안동풍산 T/L","20-21년 경북직할 송전정비회사 총액공사","수직수평 추락방지장치 설치No.26,28,37,49,56","2021-06-14 08:00","2021-06-15 18:00","취소","취소","연속"]
[503,"경북","직할","울진현종산풍력 T/L","20~21년 경북본부 직할 변전정비회사 총액공사","  하자점검(현종산)   조작시험(울진)","2021-06-08 09:00","2021-06-08 18:00","2021-06-08 09:00","2021-06-08 18:00","연속"]
[504,"경북","직할","영덕진보#1 T/L","154kV 진보S/S #4M.Tr 증설공사","최초가압","2021-06-21 10:00","2021-06-23 16:00","2021-06-21 10:00","2021-06-23 16:00","연속"]
[505,"경북","직할","진보S/S 154kV GS영양풍력#2T/L CB","154kV 진보S/S #4M.Tr 증설공사","154kV   설치","2021-06-01 09:00","2021-06-04 18:00","2021-06-01 09:00","2021-06-04 18:00","연속"]
[506,"경북","직할","영덕진보#1 T/L","154kV 진보S/S #4M.Tr 증설공사","154kV   설치","2021-06-01 09:00","2021-06-05 18:00","2021-06-01 09:00","2021-06-05 18:00","연속"]
[507,"경북","직할","현종산풍력평해#2 T/L","154kV 현종산풍력-평해#2T/L 초기점검","○154kV 현종산풍력-평해#2TT/L No.1~13 초기점검","2021-06-23 09:00","2021-06-23 18:00","2021-06-23 09:00","2021-06-23 18:00","연속"]
[508,"경북","직할","울진현종산풍력 T/L","154kV 울진-현종산풍력T/L 초기점검","○154kV 울진-현종산풍력T/L No.105~117 초기점검","2021-06-24 09:00","2021-06-24 18:00","2021-06-23 09:00","2021-06-23 18:00","연속"]
[509,"경북","직할","봉화현종산풍력 T/L","2021년 영주전력지사 170kV   정밀점검","- 617 정밀점검","2021-06-24 08:00","2021-06-26 18:00","취소","취소","연속"]
[510,"경북","직할","현종산풍력평해#1 T/L","154kV 현종산풍력-평해#1T/L 초기점검","○154kV 현종산풍력-평해T/L No.1~13 초기점검","2021-06-24 09:00","2021-06-24 18:00","2021-06-24 09:00","2021-06-24 18:00","연속"]
[511,"부산울산","동부산","신양산구서#1 T/L","동부산전력지사 가공송전 취약설비 정비공사","154kV신양산-구서#1T/L 28,31,41호 압축일류클램프 교체공사","2021-06-10 07:00","2021-06-11 18:00","2021-06-28 07:00","2021-06-29 18:00","연속"]
[512,"부산울산","동부산","신양산구서#2 T/L","동부산전력지사 가공송전 취약설비 정비공사","154kV신양산-구서#2T/L 6,7,8,19,20,22,31,34,41호 압축일류클램프 교체공사","2021-06-14 07:00","2021-06-18 18:00","2021-06-21 07:00","2021-06-25 18:00","연속"]
[513,"부산울산","동부산","신양산S/S SEC CB 60610","신양산S/S 154kV   하자점검","신양산S/S 154kV   하자점검(60-61-0)","2021-06-01 09:30","2021-06-01 17:00","2021-06-03 09:30","2021-06-03 17:00","연속"]
[514,"부산울산","동부산","신양산S/S SEC CB 65660","신양산S/S 154kV   하자점검","신양산S/S 154kV   하자점검(65-66-0)","2021-06-02 09:30","2021-06-02 17:00","2021-06-04 09:30","2021-06-04 17:00","연속"]
[515,"부산울산","동부산","명례정관 T/L","정관S/S 154kV   정밀점검 공사","정관S/S 154kV   정밀점검 관련 시험가압(6100)","2021-06-17 17:00","2021-06-17 18:00","2021-06-17 17:00","2021-06-17 18:00","연속"]
[516,"부산울산","동부산","명례정관 T/L","정관S/S 154kV   정밀점검 공사","정관S/S 154kV   정밀점검 관련 시험가압(정관-고리T/L)","2021-06-01 17:00","2021-06-01 18:00","2021-06-01 17:00","2021-06-01 18:00","연속"]
[517,"부산울산","동부산","노포정관#2 T/L","정관S/S 154kV   정밀점검 공사","정관S/S 154kV   정밀점검 공사(노포-정관#2T/L)","2021-06-09 09:00","2021-06-10 18:00","2021-06-09 09:00","2021-06-10 18:00","연속"]
[518,"부산울산","동부산","정관S/S CB 6100","정관S/S 154kV   정밀점검 공사","정관S/S 154kV   정밀점검 공사(6100)","2021-06-16 09:00","2021-06-17 18:00","2021-06-16 09:00","2021-06-17 18:00","연속"]
[519,"부산울산","동부산","명례정관 T/L","정관S/S 154kV   정밀점검 공사","정관S/S 154kV   정밀점검 관련 시험가압(#2M.Tr)","2021-06-15 17:00","2021-06-15 18:00","2021-06-15 17:00","2021-06-15 18:00","연속"]
[520,"부산울산","동부산","노포정관#1 T/L","정관S/S 154kV   정밀점검 공사","정관S/S 154kV   정밀점검 공사(노포-정관#1T/L)","2021-06-07 09:00","2021-06-08 18:00","2021-06-07 09:00","2021-06-08 18:00","연속"]
[521,"부산울산","동부산","명례정관 T/L","정관S/S 154kV   정밀점검 공사","정관S/S 154kV   정밀점검 관련 시험가압(#1M.Tr)","2021-06-03 17:00","2021-06-03 18:00","2021-06-03 17:00","2021-06-03 18:00","연속"]
[522,"부산울산","북부산","북부산구포#2 T/L","20-21 북부산전력지사 변전 총액공사","구포S/S 154kV 북부산-구포#2T/L 차단기 동작시험","2021-06-11 13:00","2021-06-11 16:00","2021-06-11 13:00","2021-06-11 16:00","연속"]
[523,"부산울산","북부산","북부산구포#1 T/L","20-21 북부산전력지사 변전 총액공사","구포S/S 154kV 북부산-구포#1T/L 차단기 동작시험","2021-06-11 10:00","2021-06-11 13:00","2021-06-11 10:00","2021-06-11 13:00","연속"]
[524,"부산울산","북부산","물금삼랑진PP#2 T/L","2021년 북부산전력지사 154kV   정밀점검","물금S/S 154kV 6333   정밀점검 (시험가압1h 선로 : 물금-삼랑진#2T/L)","2021-06-10 17:00","2021-06-10 18:00","2021-06-10 17:00","2021-06-10 18:00","연속"]
[525,"부산울산","북부산","북부산호포 T/L","2020~2021년 북부산 가공송전정비회사 총액공사(안전확보 휴전)","154kV 북부산-물금T/L 이도조정(안전확보 휴전) - 13~14호","2021-06-28 08:00","2021-06-29 18:00","2021-06-05 08:00","2021-06-06 18:00","연속"]
[526,"부산울산","북부산","북부산S/S SEC CB 61620","20-21 북부산전력지사 변전 총액공사","북부산S/S 154kV 61-62 BUS-SECTION 차단기 동작시험","2021-06-23 14:00","2021-06-23 18:00","취소","취소","연속"]
[527,"부산울산","북부산","북부산S/S CB 6300","20-21 북부산전력지사 변전 총액공사","북부산S/S 154kV 6300 BUS-TIE 차단기 동작시험","2021-06-23 10:00","2021-06-23 14:00","취소","취소","연속"]
[528,"부산울산","북부산","북부산S/S CB 6200","20-21 북부산전력지사 변전 총액공사","북부산S/S 154kV 6200 BUS-TIE 차단기 동작시험","2021-06-22 14:00","2021-06-22 18:00","취소","취소","연속"]
[529,"부산울산","북부산","북부산S/S CB 6100","20-21 북부산전력지사 변전 총액공사","북부산S/S 154kV 6100 BUS-TIE 차단기 동작시험","2021-06-22 10:00","2021-06-22 14:00","취소","취소","연속"]
[530,"부산울산","북부산","북부산미남#2 T/L","154kV 북부산-미남T/L 철탑추락방지시설 및 피뢰기 설치","154kV 북부산-미남T/L 철탑추락방지시설 및 피뢰기 설치(1~23호) 23기","2021-06-14 07:30","2021-06-16 18:00","2021-06-28 07:30","2021-07-02 18:00","연속"]
[531,"부산울산","북부산","북부산S/S SEC CB 65660","20-21 북부산전력지사 변전 총액공사","북부산S/S 154kV 65-66 BUS-SECTION 차단기 동작시험","2021-06-24 14:00","2021-06-24 18:00","취소","취소","연속"]
[532,"부산울산","북부산","북부산물금 T/L","2020~2021년 북부산 가공송전정비회사 총액공사","154kV 북부산-물금T/L 이도조정 - 13~14호","2021-06-28 08:00","2021-06-29 18:00","2021-06-05 08:00","2021-06-06 18:00","연속"]
[533,"부산울산","북부산","북부산양산 T/L","2020~2021년 북부산 가공송전정비회사 총액공사(안전확보)","상간스페이서 설치 안전확보 휴전 - 23~24호, 57~61호","2021-06-01 08:00","2021-06-02 18:00","취소","취소","연속"]
[534,"부산울산","북부산","북부산삼랑진PP T/L","2020~2021년 북부산 가공송전정비회사 총액공사","상간스페이서 설치 - 23~24호, 57~61호","2021-06-01 08:00","2021-06-02 18:00","취소","취소","연속"]
[535,"부산울산","북부산","북부산미남#1 T/L","154kV 북부산-미남T/L 철탑추락방지시설 및 피뢰기 설치","154kV 북부산-미남T/L 철탑추락방지시설 및 피뢰기 설치(1~23호) 23기","2021-06-16 07:30","2021-06-25 18:00","2021-06-21 07:30","2021-06-25 18:00","연속"]
[536,"부산울산","북부산","북부산호포 T/L","2020~2021년 북부산 가공송전정비회사 총액공사","상간스페이서 설치 - 23~24호","2021-06-03 08:00","2021-06-03 18:00","2021-06-13 08:00","2021-06-13 18:00","연속"]
[537,"부산울산","북부산","북부산물금 T/L","2020~2021년 북부산 가공송전정비회사 총액공사(안전확보 휴전)","상간스페이서 설치 (안전확보 휴전) - 23~24호","2021-06-03 08:00","2021-06-03 18:00","2021-06-13 08:00","2021-06-13 18:00","연속"]
[538,"부산울산","북부산","북부산S/S SEC CB 60610","20-21 북부산전력지사 변전 총액공사","북부산S/S 154kV 60-61 BUS-SECTION 차단기 동작시험","2021-06-24 10:00","2021-06-24 14:00","취소","취소","연속"]
[539,"부산울산","북부산","북부산S/S SEC CB 66670","20-21 북부산전력지사 변전 총액공사","북부산S/S 154kV 66-67 BUS-SECTION 차단기 동작시험","2021-06-21 10:00","2021-06-21 18:00","취소","취소","연속"]
[540,"부산울산","북부산","서창산막#2 T/L","154kV 서창-산막T/L 53~64호 지장철탑 이설공사","154kV 서창-산막T/L 53~64호 지장철탑 이설공사 CH 2기 및 가철탑1기 신설, 철탑 9기 철거(가선로 구성)","2021-06-12 08:00","2021-06-13 18:00","2021-06-12 08:00","2021-06-13 18:00","연속"]
[541,"부산울산","북부산","서창산막#1 T/L","154kV 서창-산막T/L 53~64호 지장철탑 이설공사","154kV 서창-산막T/L 53~64호 지장철탑 이설공사, CH 2기 및 가철탑1기 신설, 철탑 9기 철거(2T/L 휴전 시 안전이격 확보)","2021-06-12 08:00","2021-06-13 18:00","2021-06-12 08:00","2021-06-13 18:00","연속"]
[542,"부산울산","북부산","언양산막#1 T/L","언양-산막T/L 상간스페이서 설치 ","언양-산막T/L 상간스페이서 설치 ","2021-06-25 07:30","2021-06-30 18:00","2021-06-25 08:00","2021-06-25 18:00","연속"]
[543,"부산울산","북부산","언양산막#2 T/L","언양-산막T/L 상간스페이서 설치 ","언양-산막T/L 상간스페이서 설치 ","2021-06-17 07:30","2021-06-24 18:00","2021-06-24 08:00","2021-06-24 18:00","연속"]
[544,"부산울산","북부산","서창산막#2 T/L","154kV 서창-산막T/L 53~64호 지장철탑 이설공사","154kV 서창-산막T/L 53~64호 지장철탑 이설공사, CH 2기 및 가철탑1기 신설, 철탑 9기 철거(1T/L 휴전 시 안전이격 확보)","2021-06-19 08:00","2021-06-20 18:00","2021-06-19 08:00","2021-06-20 18:00","연속"]
[545,"부산울산","북부산","서창산막#1 T/L","154kV 서창-산막T/L 53~64호 지장철탑 이설공사","154kV 서창-산막T/L 53~64호 지장철탑 이설공사 CH 2기 및 가철탑1기 신설, 철탑 9기 철거(가선로 구성)","2021-06-19 08:00","2021-06-20 18:00","2021-06-19 08:00","2021-06-20 18:00","연속"]
[546,"부산울산","북부산","서창산막#2 T/L","154kV 언양-산막T/L 철탑추락방지시설 설치(병가구간 안전확보)","154kV 언양-산막T/L 철탑추락방지시설 설치(70~73호 구간 병가 안전확보)","2021-06-05 07:30","2021-06-06 18:00","취소","취소","연속"]
[547,"부산울산","북부산","서창산막#1 T/L","154kV 언양-산막T/L 철탑추락방지시설 설치(병가구간 안전확보)","154kV 언양-산막T/L 철탑추락방지시설 설치(70~73호 구간 병가 안전확보)","2021-06-05 07:30","2021-06-06 18:00","취소","취소","연속"]
[548,"부산울산","북부산","물금삼랑진PP#1 T/L","154kV 물금-삼랑진 등 2개T/L 접속설비 대체공사","0 물금-삼랑진 #1T/L : 철탑추락방지장치, 송전용 피뢰기 설치","2021-06-07 08:00","2021-06-21 18:00","2021-06-28 08:00","2021-07-11 18:00","연속"]
[549,"부산울산","북부산","물금삼랑진PP#2 T/L","154kV 물금-삼랑진 등 2개T/L 접속설비 대체공사","0 물금-삼랑진 #1T/L 휴전작업 안전확보","2021-06-07 08:00","2021-06-11 18:00","2021-06-28 08:00","2021-07-02 18:00","연속"]
[550,"부산울산","북부산","물금삼랑진PP#2 T/L","154kV 물금-삼랑진 등 2개T/L 접속설비 대체공사","0 물금-삼랑진 #2T/L : 전선접속개소 전력선 교체, 추락방지장치 설치","2021-06-22 08:00","2021-07-15 18:00","취소","취소","연속"]
[551,"부산울산","북부산","양산삼랑진PP T/L","20-21 북부산전력지사 변전총액공사","양산S/S 154kV 양산-삼랑진T/L 차단기 동작시험","2021-06-17 10:00","2021-06-17 18:00","취소","취소","연속"]
[552,"부산울산","북부산","서부산엄궁#1 T/L","20-21 북부산전력지사 변전 총액공사","엄궁S/S 154kV 서부산-엄궁#1T/L   보통점검","2021-06-24 10:00","2021-06-24 18:00","2021-06-24 10:00","2021-06-24 18:00","연속"]
[553,"부산울산","북부산","서부산엄궁#2 T/L","20-21 북부산전력지사 변전 총액공사","엄궁S/S 154kV 서부산-엄궁#2T/L   보통점검","2021-06-25 10:00","2021-06-25 18:00","2021-06-25 10:00","2021-06-25 18:00","연속"]
[554,"부산울산","서부산","신녹산녹산#1 T/L","순아변전소 건설공사","순아변전소 최초가압(시험가압)","2021-06-15 13:00","2021-06-16 18:00","2021-06-12 09:00","2021-06-13 18:00","연속"]
[555,"부산울산","서부산","신녹산용원#1 T/L","순아변전소 건설공사","순아변전소 최초가압(시험가압)","2021-06-15 13:00","2021-06-16 18:00","취소","취소","연속"]
[556,"부산울산","서부산","용원녹공#2 T/L","용원S/S 154kV #2M.Tr 1차   정밀점검관련 시험가압","용원S/S 154kV #2M.Tr 1차   정밀점검관련 시험가압","2021-06-16 09:00","2021-06-16 18:00","2021-06-17 18:00","2021-06-17 20:00","연속"]
[557,"부산울산","서부산","신녹산용원#1 T/L","용원S/S 154kV #1M.Tr 1차   정밀점검관련 시험가압","용원S/S 154kV #1M.Tr 1차   정밀점검관련 시험가압","2021-06-09 09:00","2021-06-09 18:00","2021-06-10 18:00","2021-06-10 20:00","연속"]
[558,"부산울산","서부산","신녹산용원#1 T/L","용원S/S 154kV #1BUSTIE   정밀점검관련 시험가압","용원S/S 154kV #1BUSTIE   정밀점검관련 시험가압","2021-06-02 09:00","2021-06-02 18:00","2021-06-02 18:00","2021-06-02 20:00","연속"]
[559,"부산울산","울산","동울산방어진 T/L","154kV 산하S/S 건설공사","-동울산-방어진 T/L 보호반 대체작업 -파이분기 긴선작업 -무부하가압(6.21~6.22), 사용전검사(6.23~24), 실부하가압(6.24)","2021-06-09 09:00","2021-06-24 18:00","2021-06-09 09:00","2021-06-24 18:00","연속"]
[560,"부산울산","울산","방어진영남TP#2 T/L","방어진영남TP#2 T/L 전선교체공사","방어진영남TP#2 T/L 전선교체 (No.1~No.5, 2.114km)","2021-06-05 07:00","2021-06-09 18:00","2021-06-26 07:00","2021-06-30 18:00","연속"]
[561,"부산울산","울산","신온산S/S 154kV #62 BUS","20-21년 변전정비회사 총액공사","- 모선보호반 성능개선(영인기술 입회) - 6300   보통점검","2021-06-04 09:00","2021-06-04 18:00","2021-06-04 09:00","2021-06-04 18:00","연속"]
[562,"부산울산","울산","신울산울산#2 T/L","신울산S/S 154kV 현대화공사","기설기초 철거 및 터파기","2021-06-18 08:30","2021-06-19 17:00","2021-06-18 08:30","2021-06-19 17:00","연속"]
[563,"부산울산","울산","신울산웅촌#1 T/L","20-21년 변전정비회사 총액공사","- 차단기 동작시험","2021-06-04 09:00","2021-06-04 14:00","2021-06-04 09:00","2021-06-04 14:00","연속"]
[564,"부산울산","울산","신울산명례#2 T/L","20~21년 가공송전 협력회사 총액공사(동부산전력지사)","○ 철탑 도장작업","2021-06-23 08:00","2021-06-24 18:00","2021-06-23 08:00","2021-06-24 18:00","연속"]
[565,"부산울산","울산","신울산언양#1 T/L","신울산S/S 154kV 현대화공사","TR-BUS 철거","2021-06-09 08:30","2021-06-09 17:00","2021-06-09 08:30","2021-06-09 17:00","연속"]
[566,"부산울산","울산","신울산매암#3 T/L","신울산S/S 154kV 현대화공사","TR-BUS 철거 및 기초 공사","2021-06-11 08:30","2021-06-11 17:00","2021-06-11 08:30","2021-06-11 17:00","연속"]
[567,"부산울산","울산","신울산명례#1 T/L","20~21년 가공송전 협력회사 총액공사(동부산전력지사)","○ 철탑 도장작업","2021-06-21 08:00","2021-06-22 18:00","2021-06-21 08:00","2021-06-22 18:00","연속"]
[568,"부산울산","울산","신울산웅촌#2 T/L","20-21년 변전정비회사 총액공사","- 차단기 동작시험","2021-06-04 14:00","2021-06-04 18:00","2021-06-04 14:00","2021-06-04 18:00","연속"]
[569,"부산울산","울산","신울산언양#2 T/L","신울산S/S 154kV 현대화공사","TR-BUS 철거","2021-06-08 08:30","2021-06-08 17:00","2021-06-08 08:30","2021-06-08 17:00","연속"]
[570,"부산울산","울산","신울산울산#1 T/L","신울산S/S 154kV 현대화공사","기설기초 철거 및 터파기","2021-06-21 08:30","2021-06-22 17:00","2021-06-21 08:30","2021-06-22 17:00","연속"]
[571,"부산울산","울산","신울산명례#1 T/L","신울산S/S 154kV 현대화공사","기설기초 철거 및 터파기","2021-06-16 08:30","2021-06-17 17:00","2021-06-16 08:30","2021-06-17 17:00","연속"]
[572,"부산울산","울산","신울산매암#1 T/L","20-21년 변전정비회사 총액공사","- 매암)  보통점검 - 신울산) PT 보통점검","2021-06-23 09:00","2021-06-23 18:00","2021-06-23 09:00","2021-06-23 18:00","연속"]
[573,"부산울산","울산","신울산매암#2 T/L","20-21년 변전정비회사 총액공사","- 매암)  보통점검 - 신울산)  보통점검,전자변 교체,PT 보통점검","2021-06-24 09:00","2021-06-24 18:00","2021-06-24 09:00","2021-06-24 18:00","연속"]
[574,"부산울산","울산","신울산매암#3 T/L","20-21년 변전정비회사 총액공사","- 차단기동작시험,전자변 교체","2021-06-25 09:00","2021-06-25 18:00","2021-06-25 09:00","2021-06-25 18:00","연속"]
[575,"부산울산","울산","신울산명례#2 T/L","신울산S/S 154kV 현대화공사","기설기초 철거 및 터파기","2021-06-14 08:30","2021-06-15 17:00","2021-06-14 08:30","2021-06-15 17:00","연속"]
[576,"부산울산","울산","신울산언양#1 T/L","2020~21년도 가공송전 정비회사 총액공사","154kV 신울산-언양T/L 철탑도장공사(안전이격 확보) - 작업구간 : No. 27,28","2021-06-02 07:30","2021-06-03 18:00","2021-06-02 07:30","2021-06-03 18:00","연속"]
[577,"부산울산","울산","옥동외동#2 T/L","154kV 외동-옥동#2T/L 상간스페이서 설치공사","ㅁ 상간스페이서 설치공사 - 구간 : 154kV 외동-옥동#2T/L No.48~49 - 고장우려개소 본부 지시사항","2021-06-07 07:00","2021-06-07 18:00","2021-06-07 07:00","2021-06-07 18:00","연속"]
[578,"부산울산","울산","옥동외동#1 T/L","154kV 외동-옥동#1T/L 상간스페이서 설치공사","ㅁ 상간스페이서 설치공사 - 구간 : 154kV 외동-옥동#1T/L No.48~49 - 고장우려개소 본부 지시사항","2021-06-08 07:00","2021-06-08 18:00","2021-06-08 07:00","2021-06-08 18:00","연속"]
[579,"부산울산","울산","용연울산TP#1 T/L","20-21년 변전정비회사 총액공사","- 송전선로 보호반 대체-&gt6월에   대체와 병행","2021-06-28 09:00","2021-06-30 18:00","2021-06-28 09:00","2021-06-30 18:00","연속"]
[580,"부산울산","울산","용연울산TP#3 T/L","20-21년 변전정비회사 총액공사","- 순간상승압력계 교체","2021-06-24 09:00","2021-06-24 18:00","2021-06-24 09:00","2021-06-24 18:00","연속"]
[581,"부산울산","울산","용연울산TP#2 T/L","20-21년 변전정비회사 총액공사","- 송전선로 보호반 대체-&gt6월에   대체와 병행 - 용연)  하자점검(성현)-6월에   대체와 병행 - 용연)LA 보통점검-&gt6월에   대체와 병행","2021-06-21 09:00","2021-06-23 18:00","2021-06-21 09:00","2021-06-23 18:00","연속"]
[582,"부산울산","울산","울주외동#2 T/L","154kV 울주-외동#2T/L 상간스페이서 설치공사","ㅁ 상간스페이서 설치공사 - 구간 : 154kV 울주-외동#2T/L No.29~30 - 고장우려개소 본부 지시사항","2021-06-08 07:00","2021-06-08 18:00","2021-06-08 07:00","2021-06-08 18:00","연속"]
[583,"부산울산","울산","울주외동#1 T/L","154kV 울주-외동#1T/L 상간스페이서 설치공사","ㅁ 상간스페이서 설치공사 - 구간 : 154kV 울주-외동#1T/L No.29~30 - 고장우려개소 본부 지시사항","2021-06-07 07:00","2021-06-07 18:00","2021-06-07 07:00","2021-06-07 18:00","연속"]
[584,"부산울산","직할","개금S/S 154kV #2 BUS","2021년 북부산전력지사 154kV   정밀점검","개금S/S 154kV 6233   정밀점검 (시험가압 선로 : 덕포-개금#2T/L, #65BUS)","2021-06-03 17:00","2021-06-03 18:00","2021-06-03 17:00","2021-06-03 18:00","연속"]
[585,"부산울산","직할","개금S/S 154kV #2 BUS","2021년 북부산전력지사 154kV   정밀점검","개금S/S 154kV 6133   정밀점검 (시험가압 선로 : 덕포-개금#2T/L, #65BUS)","2021-06-08 17:00","2021-06-08 18:00","2021-06-08 17:00","2021-06-08 18:00","연속"]
[586,"부산울산","직할","수정S/S CB 6100","20-21년 직할 변전정비회사 총액공사","수정S/S 154kV BUS-TIE   조작시험 및 전자변 교체","2021-06-04 10:00","2021-06-04 18:00","2021-06-04 10:00","2021-06-04 18:00","연속"]
[587,"경남","직할","신김해주촌#2 T/L","신김해S/S 신김해-주촌#2T/L 초기점검","신김해S/S 신김해-주촌#2T/L 초기점검","2021-06-30 09:30","2021-06-30 17:30","2021-06-30 09:30","2021-06-30 17:30","연속"]
[588,"경남","직할","신김해주촌#1 T/L","신김해S/S 신김해-주촌#1T/L 초기점검","신김해S/S 신김해-주촌#1T/L 초기점검","2021-06-18 09:30","2021-06-18 17:30","2021-06-18 09:30","2021-06-18 17:30","연속"]
[589,"경남","직할","신김해삼정#1 T/L","154kV 신김해-삼정#1T/L 소도체 이도조정","154kV 신김해-삼정#1T/L 소도체 이도조정 (6~7,7~8,10~11)","2021-06-08 07:00","2021-06-09 18:00","2021-06-08 07:00","2021-06-09 18:00","연속"]
[590,"경남","직할","신김해삼정#2 T/L","154kV 신김해-삼정#2T/L 소도체 이도조정","154kV 신김해-삼정#2T/L 소도체 이도조정 (7~8,10~11)","2021-06-10 07:00","2021-06-11 18:00","2021-06-10 07:00","2021-06-11 18:00","연속"]
[591,"경남","직할","신월삼정#1 T/L","신월S/S 신월-삼정#1T/L   정밀점검","신월S/S 신월-삼정#1T/L   정밀점검","2021-06-21 08:00","2021-06-23 18:00","2021-06-21 08:00","2021-06-23 18:00","연속"]
[592,"경남","직할","신월동읍#1 T/L","신월S/S 154kV BUS-TIE   정밀점검(BUS 일시절체용)","신월S/S 154kV BUS-TIE   정밀점검(BUS 일시절체용)","2021-06-18 14:00","2021-06-18 16:00","2021-06-18 14:00","2021-06-18 16:00","연속"]
[593,"경남","직할","신월삼정#1 T/L","신월S/S 154kV BUS-TIE   정밀점검(시험가압 선로)","신월S/S 154kV BUS-TIE   정밀점검(시험가압 선로)","2021-06-18 14:00","2021-06-18 16:00","2021-06-18 14:00","2021-06-18 16:00","연속"]
[594,"경남","직할","신월동읍#2 T/L","신월S/S #2M.Tr 1차   정밀점검(시험가압용)","신월S/S #2M.Tr 1차   정밀점검(시험가압용)","2021-06-10 14:00","2021-06-10 16:00","2021-06-25 14:00","2021-06-25 16:00","연속"]
[595,"경남","직할","신월동읍#1 T/L","신월S/S #1M.Tr 1차   정밀점검(시험가압용)","신월S/S #1M.Tr 1차   정밀점검(시험가압용)","2021-06-08 14:00","2021-06-08 16:00","2021-06-15 14:00","2021-06-15 16:00","연속"]
[596,"경남","직할","신월삼정#2 T/L","신월S/S 신월-삼정#2T/L   정밀점검","신월S/S 신월-삼정#2T/L   정밀점검","2021-06-14 08:00","2021-06-16 18:00","2021-06-28 08:00","2021-06-30 18:00","연속"]
[597,"경남","직할","안민천선#2 T/L","154kV 완암-안민#2T/L 소도체 이도조정 안전작업거리확보","154kV 완암-안민#2T/L 소도체 이도조정 안전작업거리확보","2021-06-14 07:00","2021-06-15 18:00","취소","취소","매일"]
[598,"경남","진주","진주개양#2 T/L","154kV 진주-개양T/L 송전선로 정밀점검(15기)","154kV 진주-개양T/L 송전선로 정밀점검","2021-06-19 08:00","2021-06-20 18:00","2021-06-26 08:00","2021-06-27 18:00","매일"]
[599,"경남","진주","사봉개양#2 T/L","안전작업거리 확보 휴전","154kV 진주-개양T/L 송전선로 정밀점검 시, 안전이격거리 확보를 위한 병행휴전","2021-05-22 08:00","2021-05-22 18:00","취소","취소","연속"]
[600,"경남","진주","진주개양#1 T/L","154kV 진주-개양T/L 송전선로 정밀점검(15기)","154kV 진주-개양T/L 송전선로 정밀점검","2021-06-19 08:00","2021-06-20 18:00","2021-06-26 08:00","2021-06-27 18:00","매일"]
[601,"경남","진주","사봉개양#1 T/L","안전작업거리 확보 휴전","154kV 진주-개양T/L 송전선로 정밀점검 시, 안전이격거리 확보를 위한 병행휴전","2021-05-23 08:00","2021-05-23 18:00","취소","취소","연속"]
[602,"경남","진주","삼천포사천#2 T/L","사천S/S 23kV Sh.C 증설공사","□ 사천S/S 23kV Sh.C 5MVar x 4Bank 증설 　○ 삼천포-사천#2T/L CPD 전원 관로 이설 작업","2021-06-09 09:00","2021-06-09 18:00","2021-06-09 09:00","2021-06-09 18:00","연속"]
[603,"경남","진주","하동S/S CB 6100","하동S/S #1BUS-TIE(6100)   보통점검","하동S/S #1BUS-TIE(6100)   보통점검","2021-06-15 10:00","2021-06-15 18:00","2021-06-15 10:00","2021-06-15 18:00","연속"]
[604,"경남","진주","산청함양 T/L","함양S/S 옥외철구설비 제각공사","제각관련 작업안전거리 확보차","2021-06-01 14:00","2021-06-01 18:00","2021-06-01 14:00","2021-06-01 18:00","연속"]
[605,"경남","진주","의령함양 T/L","함양S/S 옥외철구설비 제각공사","제각관련 작업안전거리 확보차","2021-06-01 09:00","2021-06-01 14:00","2021-06-01 09:00","2021-06-01 14:00","연속"]
[606,"경남","통영","삼천포사천#1 T/L","154kV 신고성-삼천포#1T/L 피뢰기 설치공사(6~22호)","154kV 신고성-삼천포#1T/L 피뢰기 설치공사(6~22호) 안전이격거리 확보휴전","2021-06-07 07:30","2021-06-08 18:00","2021-06-07 07:30","2021-06-08 18:00","매일"]
[607,"경남","통영","신고성삼천포#1 T/L","154kV 신고성-삼천포#1T/L 피뢰기 설치공사","154kV 신고성-삼천포#1T/L 피뢰기 설치공사(6~22호)","2021-06-07 07:30","2021-06-08 18:00","2021-06-07 07:30","2021-06-08 18:00","매일"]
[608,"경남","통영","신고성거제#1 T/L","154kV 진동-안정#1T/L 항공장애표시구 설치공사(안전이격거리 확보)","154kV 진동-안정#1T/L 항공장애표시구 설치공사(안전이격거리 확보)","2021-06-12 07:30","2021-06-12 18:00","2021-06-12 07:30","2021-06-12 18:00","연속"]
[609,"경남","통영","통영거제#1 T/L","154kV 통영-거제#1T/L 추락방지시설 설치공사","154kV 통영-거제#1T/L 추락방지시설 설치공사(10~72호)","2021-06-19 07:30","2021-06-20 18:00","2021-06-19 07:30","2021-06-20 18:00","매일"]
[610,"경남","통영","통영거제#2 T/L","154kV 통영-거제#2T/L 추락방지시설 설치공사","154kV 통영-거제#2T/L 추락방지시설 설치공사","2021-06-26 07:30","2021-06-27 18:00","2021-06-26 07:30","2021-06-27 18:00","매일"]
[611,"경남","함안","주촌삼계#2 T/L  ","삼계S/S 154kV 주촌-삼계#2T/L   조작시험","삼계S/S 154kV 주촌-삼계#2T/L   조작시험","2021-06-23 13:30","2021-06-23 17:30","2021-06-23 13:30","2021-06-23 17:30","연속"]
[612,"경남","함안","주촌삼계#1 T/L  ","삼계S/S 154kV 주촌-삼계#1T/L   조작시험","삼계S/S 154kV 주촌-삼계#1T/L   조작시험","2021-06-23 09:30","2021-06-23 13:30","2021-06-23 09:30","2021-06-23 13:30","연속"]
[613,"경남","함안","신마산동읍#1 T/L","154kV신마산-의창T/L 등 OPGW 교체 공사","1. 신마산-의창T/L 등 11km 광코어 48-&gt96코어 증설 2. 신월-동읍T/L 10km 광코어 24-&gt48코어 증설 3. 창원-창공T/L 5km 광코어 24-&gt48코어 증설","2021-06-08 08:00","2021-06-19 18:00","2021-06-08 08:00","2021-06-19 18:00","연속"]
[614,"경남","함안","신마산의창#2 T/L","154kV 신마산-의창T/L 등 OPGW 교체공사","1. 신마산-의창T/L 등 11km 광코어 48-96코어 증설 2. 신월-동읍T/L 10km 광코어 24-48코어 증설 3. 창원-창공T/L 5km 광코어 24-48코어 증설","2021-06-08 08:00","2021-06-19 18:00","2021-06-08 08:00","2021-06-19 18:00","연속"]
[615,"경남","함안","창녕초동#2 T/L","창녕S/S 154kV 창녕-초동#2T/L GCB 조작시험","창녕S/S 154kV 창녕-초동#2T/L GCB 조작시험","2021-06-23 09:30","2021-06-23 13:30","2021-06-23 09:30","2021-06-23 13:30","연속"]