{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":13,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"765설비","index":0,"n_rows":8,"n_cols":11,"rows_kept":8,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 8월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"부산울산","동부산","북경남신고리NP#2 T/L","신고리S/S 765kV GIS 정밀점검 공사","신고리S/S 765kV GIS 정밀점검 공사(8371GIS)","2022-08-09 09:00","2022-08-14 18:00","2022-08-09 09:00","2022-08-14 18:00","연속"]
[2,"부산울산","동부산","신고리N/P #1 Tie-Tr","신고리 5,6호기 접속설비공사","신고리-고리 #4T/L CH 인하선 이격거리 확보","2022-08-16 09:00","2022-08-16 18:00","2022-08-16 09:00","2022-08-16 18:00","연속"]
[3,"부산울산","동부산","신고리N/P #2 Tie-Tr","신고리 5,6호기 접속설비공사","- #2M.Tr 이설 - #4M.Tr 가압('22.11.15) - 8771, 8700 설치 - #2M.Tr 2차측 이설","2022-08-17 09:00","2023-11-15 18:00","2022-08-17 09:00","2023-11-15 18:00","연속"]
[4,"부산울산",null,"신고리N/P #4호기 주변압기 (CB 8300, 8372)","신고리4호기 2차 계획예방정비 *조작 차단기 : CB 8300, 8372","○ SWYD 8300, 8372 차단기 정밀점검 ○ 주변압기 점검","2022-08-09 09:00","2022-09-09 18:00","2022-08-09 09:00","2022-09-09 18:00","연속"]

{"sheet":"345설비","index":1,"n_rows":29,"n_cols":11,"rows_kept":29,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 8월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","강남","신양재S/S #1 Sh.R CB","2022년 강남전력지사 345kV Sh.R 정밀점검","2022년 강남전력지사 345kV Sh.R 정밀점검 - 점검대상 : #1Sh.R - 병행작업 1. GIS 조작시험 2. Sh.R 보호반 대체","2022-07-04 09:00","2022-07-15 18:00","취소","취소","연속"]
[2,"남서울","동서울","동서울S/S SVC CB","동서울SS 345kV SVC M.Tr A,B,C상 정밀점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-08-16 07:00","2022-08-31 18:00","2022-08-16 07:00","2022-08-31 18:00","연속"]
[3,"남서울","동서울","동서울S/S #2 Sh.R CB","동서울SS #2Sh.R 보통, 7A72,7079 GIS 하자점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-08-08 09:00","2022-08-12 18:00","2022-08-08 09:00","2022-08-12 18:00","연속"]
[4,"남서울","직할","신문래S/S #2 Sh.R CB","345kV #2Sh.R 초기점검 공사","345kV #2Sh.R 초기점검 공사","2022-08-23 09:00","2022-08-24 18:00","2022-08-23 09:00","2022-08-24 18:00","연속"]
[5,"경기북부","고양","신파주S/S SVC CB","'22년 신파주S/S SVC 보통점검공사","- SVC 보통점검공사","2022-08-22 09:00","2022-08-31 11:00","2022-08-22 09:00","2022-08-31 11:00","연속"]
[6,"경기북부","구리","미금S/S #6 Sh.R CB","22년도 구리전력지사 345kV M.Tr, Sh.R 점검공사","미금S/S 345kV #6Sh.R 정밀점검","2022-08-29 09:00","2022-09-02 18:00","취소","취소","연속"]
[7,"경기북부","구리","미금S/S CB 7272","22년도 구리전력지사 345kV M.Tr, Sh.R 점검공사","미금S/S 345kV #6Sh.R 정밀점검","2022-08-29 09:00","2022-09-02 18:00","취소","취소","연속"]
[8,"경기북부","구리","미금S/S CB 7200","22년도 구리전력지사 345kV M.Tr, Sh.R 점검공사","미금S/S 345kV #6Sh.R 정밀점검","2022-08-29 09:00","2022-09-02 18:00","취소","취소","연속"]
[9,"경기북부","구리","신가평S/S CB 7371","22년도 구리전력지사 345kV M.Tr, Sh.R 점검공사","신가평S/S 345kV #2Sh.R 정밀점검","2022-08-22 09:00","2022-08-26 18:00","2022-08-22 09:00","2022-08-26 18:00","연속"]
[10,"경기북부","구리","신가평S/S CB 7300","22년도 구리전력지사 345kV M.Tr, Sh.R 점검공사","신가평S/S 345kV #2Sh.R 정밀점검","2022-08-22 09:00","2022-08-26 18:00","2022-08-22 09:00","2022-08-26 18:00","연속"]
[11,"경기북부","구리","신가평S/S #2 Sh.R CB","22년도 구리전력지사 345kV M.Tr, Sh.R 점검공사","신가평S/S 345kV #2Sh.R 정밀점검","2022-08-22 09:00","2022-08-26 18:00","2022-08-22 09:00","2022-08-26 18:00","연속"]
[12,"경기","성남","신안성S/S #6 Sh.R CB","22년 성남전력 362kV GIS 정밀점검공사","- GIS 정밀점검(7979) - B/F 대체, Sh.R 보호반 대체","2022-08-29 09:00","2022-09-08 18:00","2022-08-29 09:00","2022-09-08 18:00","연속"]
[13,"경기","성남","신안성S/S CB 7971","22년 성남전력 362kV GIS 정밀점검공사","- GIS 정밀점검(7979) - B/F 대체, Sh.R 보호반 대체","2022-08-29 09:00","2022-09-08 18:00","2022-08-29 09:00","2022-09-08 18:00","연속"]
[14,"경기","성남","신안성신수원#1 T/L","22년 성남전력 362kV GIS 정밀점검공사","- GIS 정밀점검(7979) - B/F 대체, Sh.R 보호반 대체","2022-08-29 09:00","2022-09-08 18:00","2022-08-29 09:00","2022-09-08 18:00","연속"]
[15,"경기","평택","고덕S/S #4 M.Tr","고덕S/S 345kV #4M.Tr C상 상부 누유보수","고덕S/S 345kV #4M.Tr C상 상부 누유보수","2022-08-24 10:00","2022-08-24 18:00","2022-08-24 10:00","2022-08-24 18:00","연속"]
[16,"경기","평택","고덕#2S/S #2 M.Tr","에어퍼스트 증설 무부하가압","에어퍼스트 증설관련 무부하가압","2022-08-11 10:00","2022-08-12 10:00","2022-08-11 10:00","2022-08-12 10:00","연속"]
[17,"경기","평택","고덕#2S/S #3 M.Tr","에어퍼스트 증설관련 무부하가압","에어퍼스트 증설관련 무부하가압","2022-08-17 10:00","2022-08-18 10:00","2022-08-17 10:00","2022-08-18 10:00","연속"]
[18,"경기","평택","고덕#2S/S #2 M.Tr","에어퍼스트 증설관련 무부하가압","에어퍼스트 증설관련 무부하가압","2022-08-25 10:00","2022-08-26 10:00","2022-08-25 10:00","2022-08-26 10:00","연속"]
[19,"대전세종충남","서산","신당진S/S CB 7100","신당진S/S 345kV 7100 개리차 과발생 관련 점검","신당진S/S 345kV 7100 개리차 과발생 관련 점검 (A,B,C상 개리차 5.8ms)","2022-08-25 09:00","2022-08-25 18:00","2022-08-25 09:00","2022-08-25 18:00","연속"]
[20,"대전세종충남","서산","신서산S/S CB 7700","신서산S/S 345kV 7700 CB Oil 펌프 과동작 관련 점검","신서산S/S 345kV 7700 CB Oil 펌프 과동작 관련 점검","2022-08-23 09:00","2022-08-23 18:00","2022-08-23 09:00","2022-08-23 18:00","연속"]
[21,"전북","직할","신남원한빛NP#1 T/L","345kV 신남원-한빛#1T/L No.172~301 추락방지시설 설치공사","□ 시공구간 : 345kV 신남원-한빛#1T/L No.172~301 구간 □ 시공내용 ○ 추락방지시설 설치 : 126기[수직,수평(#1T/L)]","2022-08-16 08:00","2022-08-26 18:00","2022-08-01 08:00","2022-08-12 18:00","연속"]
[22,"대구","포항","신포항신월성NP#2 T/L","신포항S/S 7402DS 과열개소 보수","신포항S/S 7402DS 과열개소 보수","2022-08-01 09:00","2022-08-01 18:00","2022-08-01 09:00","2022-08-01 18:00","연속"]
[23,"부산울산","울산","신온산S/S #4 M.Tr","신온산S/S 154kV APK T/L 인출변경공사","GIS 기초공사 관련 안전이격거리 확보","2022-08-15 09:00","2022-08-19 18:00","2022-08-15 09:00","2022-08-19 18:00","매일"]
[24,"부산울산","울산","신온산S/S #1 M.Tr","22년 상반기 154kV 개폐장치 정밀점검 공사","- 신온산-온산#2T/L 2DS, 고려아연 #2T/L #1,2DS 가스누기보수 공사 관련 안전이격","2022-08-29 09:00","2022-09-02 18:00","2022-08-29 09:00","2022-09-02 18:00","연속"]
[25,"대구",null,"월성N/P #3호기 주변압기 (CB 7500, 7572)","월성3호기 19차 O/H 중 주변압기 점검 * 조작차단기 : CB 7500, 7572","○ 주변압기 점검 ○ GIB 개선 공사","2022-08-24 09:00","2022-09-25 18:00","2022-08-24 09:00","2022-09-25 18:00","연속"]

{"sheet":"154설비","index":2,"n_rows":28,"n_cols":11,"rows_kept":28,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 8월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","동서울","동서울가락#2 T/L","154kV 동서울-송파,가락T/L 지중화공사","154kV 동서울S/S ~ J/B#7간 지중송전케이블 설치 ○ 선종 및 길이 : XLPE2,500SQ, 약 3.0km","2022-08-22 09:00","2022-09-17 18:00","2022-08-22 09:00","2022-09-17 18:00","연속"]
[2,"남서울","영등포","신광명광명#2 T/L","광명S/S 인출전력구 OF케이블 선종교체공사","OF/XLPE 2,000SQ 0.350km(D) 교체 이종 및 단말접속 12상 및 기타부대공사","2022-08-22 08:00","2022-10-31 18:00","2022-08-22 08:00","2022-10-31 18:00","연속"]
[3,"남서울","영등포","신광명시흥#1 T/L","'22-'23년 가공송전 협력회사 총액공사(추락방지시설 설치)","-154kV 신광명-시흥#1T/L 수평단 추락방지시설 설치","2022-08-29 09:00","2022-09-02 18:00","2022-08-29 09:00","2022-09-02 18:00","연속"]
[4,"인천","부평","신경서경서#3 T/L","신경서경서#3 T/L GIS 조작불량 관련 점검","신경서경서#3 T/L GIS 조작불량 관련 점검","2022-08-01 09:00","2022-08-01 18:00","2022-08-01 09:00","2022-08-01 18:00","연속"]
[5,"강원","강릉","북평영동TP#2 T/L","2022년 영동화력S/Y 디지털화공사","RTU → SA혼용운영시스템 SCADA 제어케이블 이설","2022-08-02 09:00","2022-08-03 18:00","2022-08-02 09:00","2022-08-03 18:00","연속"]
[6,"충북","충주","신충주음성#1 T/L","신충주S/S 154kV 재세능원#1T/L 케이블 접속","CH 설치 및 케이블 접속 관련 크레인 안전이격 확보 (즉시가압 가능)","2022-08-27 09:00","2022-08-28 18:00","취소","취소","연속"]
[7,"대전세종충남","천안","예산응봉#1 T/L","154kV 예산S/S 미래화공사","ㅇ T/L 인출변경","2022-08-02 10:00","2022-08-09 17:00","2022-08-03 10:00","2022-08-09 17:00","연속"]
[8,"대전세종충남","천안","아산예산#1 T/L","154kV 예산S/S 미래화공사","ㅇ T/L 인출변경\n(3일~17일 유사시 투입가능)","2022-08-18 10:00","2022-08-26 17:00","2022-08-03 10:00","2022-08-26 17:00","연속"]
[9,"전북","김제","신김제남전주#2 T/L","345kV 신김제S/S #63D.Tr 증설공사","154kV #63D.Tr 1차 GIS 증설구간 무부하가압 - #62BUS 건전성 확인","2022-08-22 16:00","2022-08-23 09:00","2022-08-22 16:00","2022-08-23 09:00","연속"]
[10,"전북","김제","신김제남전주#2 T/L","345kV 신김제S/S #63D.Tr 증설공사","154kV #63D.Tr 1차 GIS 증설구간 무부하가압 - #67BUS 건전성 확인","2022-08-24 16:00","2022-08-25 09:00","2022-08-24 16:00","2022-08-25 09:00","연속"]
[11,"전북","군산","영등낭산#1T/L","154kV 영등-낭산T/L 안전이격 확보공사","철탑공사 : 설치(6기), 철거(7기) / 전력선 교체 : 0.732C-㎞ / 임시선로 철거 및 기타 부대공사","2022-08-01 09:00","2022-08-13 18:00","취소","취소","연속"]
[12,"전북","군산","영등낭산#2T/L","154kV 영등-낭산T/L 안전이격 확보공사","철탑공사 : 설치(6기), 철거(7기) / 전력선 교체 : 0.732C-㎞ / 임시선로 철거 및 기타 부대공사","2022-08-14 09:00","2022-08-21 18:00","취소","취소","연속"]
[13,"경북","직할","안동풍산 T/L","안동지역 전기공급시설 전력구공사","안동풍산T/L 근처 가시설 작업(장비 안전이격)","2022-08-01 08:00","2022-08-01 18:00","2022-08-01 08:00","2022-08-01 18:00","연속"]
[14,"경북","직할","풍산동상주개폐소 T/L","안동지역 전기공급시설 전력구공사","안동풍산T/L 근처 가시설 작업(장비 안전이격)","2022-08-02 08:00","2022-08-02 18:00","취소","취소","연속"]
[15,"부산울산","서부산","서부산다대#1 T/L","21-22년 서부산전력지사 지중송전위탁 정비공사","OF케이블 절연유 시료채취 작업","2022-08-22 09:00","2022-08-23 18:00","2022-08-22 09:00","2022-08-23 18:00","연속"]
[16,"부산울산","서부산","서부산다대#2 T/L","21-22년 서부산전력지사 지중송전위탁 정비공사","OF케이블 절연유 시료채취 작업","2022-08-24 09:00","2022-08-25 18:00","2022-08-24 09:00","2022-08-25 18:00","연속"]
[17,"부산울산","서부산","순아S/S #2 BUS","154kV 명지-순아T/L SW 증설공사","○ 170kV 50kA GIS 3,150A 2BAY 설치 ○ 170kV 50kA GIS 2,000A 3BAY 설치 ○ 170kV BUS-PT 3,150A 1BAY 설치","2022-08-22 09:30","2022-09-07 18:00","2022-08-22 09:30","2022-09-07 18:00","연속"]
[18,"부산울산","서부산","신녹산순아#1 T/L","154kV 명지-순아T/L SW 증설공사","○ 170kV 50kA GIS 3,150A 2BAY 설치 ○ 170kV 50kA GIS 2,000A 3BAY 설치 ○ 170kV BUS-PT 3,150A 1BAY 설치","2022-08-22 09:30","2022-09-07 18:00","2022-08-22 09:30","2022-09-07 18:00","연속"]
[19,"부산울산","서부산","신녹산순아#2 T/L","154kV 명지-순아T/L SW 증설공사","○ 170kV 50kA GIS 3,150A 2BAY 설치 ○ 170kV 50kA GIS 2,000A 3BAY 설치 ○ 170kV BUS-PT 3,150A 1BAY 설치","2022-08-22 09:30","2022-09-07 18:00","2022-08-22 09:30","2022-09-07 18:00","연속"]
[20,"부산울산","서부산","순아S/S #1 BUS","154kV 명지-순아T/L SW 증설공사","○ 170kV 50kA GIS 3,150A 2BAY 설치 ○ 170kV 50kA GIS 2,000A 3BAY 설치 ○ 170kV BUS-PT 3,150A 1BAY 설치","2022-08-22 09:30","2022-09-07 18:00","2022-08-22 09:30","2022-09-07 18:00","연속"]
[21,"부산울산","서부산","신김해지사#2 T/L","지사S/S 154kV 신김해-지사#2T/L GIS 보통점검","지사S/S 154kV 신김해-지사#2T/L GIS 보통점검","2022-08-11 09:00","2022-08-11 18:00","취소","취소","연속"]
[22,"부산울산","서부산","신김해지사#1 T/L","지사S/S 154kV 신김해-지사#1T/L GIS 보통점검","지사S/S 154kV 신김해-지사#1T/L GIS 보통점검","2022-08-10 09:00","2022-08-10 18:00","취소","취소","연속"]
[23,"부산울산","울산","방어진영남TP#2 T/L","154kV방어진-영남TP T/L 접속설비보강공사","#2T/L 휴전 작업 ㅇ 피뢰기 설치 : NO.6~17 ㅇ 폴리머지지애자 설치 : NO.6~17","2022-08-02 07:00","2022-08-02 18:00","2022-08-02 07:00","2022-08-02 18:00","연속"]
[24,"부산울산","울산","신온산온산#2 T/L","22년 상반기 154kV 개폐장치 정밀점검 공사","- 신온산-온산#2T/L 2DS, 고려아연 #2T/L #1,2DS 가스누기보수 공사 - GIS 정밀점검(신온산), 차단기 동작시험(온산)","2022-08-29 09:00","2022-09-02 18:00","2022-08-29 09:00","2022-09-02 18:00","연속"]