{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":13,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"765설비","index":0,"n_rows":13,"n_cols":11,"rows_kept":13,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]],"flags":["formulas_cached_only"]}
["2022년도 9월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #2 M.Tr","2022~23 구리전력 변전협력 총액공사","신가평S/S #2M.Tr 본체 컨서베이터 고무백, 유면계점검","2022-09-14 09:00","2022-09-14 18:00","2022-09-14 09:00","2022-09-14 18:00","연속"]
[2,"강원","태백","신태백S/S CB 8471","신태백S/S 765kV GIS 유압장치 교체공사","신태백S/S 765kV 8471CB B-S POLE 유압장치 교체","2022-09-28 10:00","2022-09-30 18:00","2022-09-28 10:00","2022-09-30 18:00","연속"]
[3,"충북","직할","신중부S/S #3 M.Tr","신중부S/S 765kV GIS 하자보수","8500CB GIS 정밀점검 및 부품교체","2022-09-20 10:00","2022-09-23 18:00","2022-09-20 10:00","2022-09-23 18:00","연속"]
[4,"충북","직할","신중부S/S CB 8500","신중부변전소 765kV GIS 하자보수","GIS 내부 정밀점검 및 부품교체","2022-09-15 10:00","2022-09-23 18:00","2022-09-15 10:00","2022-09-23 18:00","연속"]
[5,"부산울산","동부산","북경남신고리NP#2 T/L","신고리S/S 765kV GIS 정밀점검 시험가압","신고리S/S 765kV GIS 정밀점검 시험가압(8300,8372)","2022-09-07 18:00","2022-09-08 09:00","2022-08-30 16:00","2022-08-30 18:00","연속"]
[6,"부산울산","동부산","신고리N/P #1 Tie-Tr","신고리S/S 765kV GIS 정밀점검 관련 시험가압","신고리S/S 765kV GIS 정밀점검 관련 시험가압(8400)","2022-09-23 18:00","2022-09-24 09:00","취소","취소","연속"]
[7,"부산울산","동부산","북경남신고리NP#1 T/L","신고리S/S 765kV GIS 결상회로 개선","신고리S/S 765kV GIS 결상회로 개선(북경남신고리#1TL)","2022-09-22 09:00","2022-09-22 18:00","취소","취소","연속"]
[8,"경남","함안","북경남S/S #4 M.Tr","북경남S/S 765kV #4 M.Tr B-2상 누유확인","북경남S/S 765kV #4 M.Tr B-2상 누유확인 및 96P 방수커버 설치","2022-09-30 09:30","2022-09-30 17:30","2022-09-30 09:30","2022-09-30 17:30","연속"]
[9,"경남","함안","북경남S/S #5 M.Tr","북경남S/S 765kV #5 M.Tr 96P 방수커버 설치","북경남S/S 765kV #5 M.Tr 96P 방수커버 설치","2022-09-29 09:30","2022-09-29 17:30","2022-09-29 09:30","2022-09-29 17:30","연속"]

{"sheet":"345설비","index":1,"n_rows":272,"n_cols":11,"rows_kept":272,"cut":false,"hidden":false,"merged":[[2,6,2,7],[2,8,2,9],[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5]],"flags":["formulas_cached_only"]}
["2022년도 9월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #1 M.Tr","2022년 성동P/O 변전협력회사 총액공사","-154kV GIS 보통점검","2022-09-06 10:00","2022-09-06 17:00","2022-09-06 10:00","2022-09-06 17:00","연속"]
[2,"서울","중부","중부S/S #2 Sh.R CB","22~23년 중부전력지사 변전 협력회사 총액공사","1차 GIS A상 유면계 보수","2022-09-26 10:00","2022-09-26 17:00","2022-09-26 10:00","2022-09-26 17:00","연속"]
[3,"남서울","강남","신양재S/S #4 Sh.R CB","22-23년도 강남전력지사 변전협력회사 총액공사","-GIS 조작시험 -69Q 회로보완","2022-09-02 14:00","2022-09-02 18:00","2022-09-02 14:00","2022-09-02 18:00","연속"]
[4,"남서울","강남","신양재S/S #3 Sh.R CB","22-23년도 강남전력지사 변전협력회사 총액공사","-GIS 조작시험 -69Q 회로보완 -LCP PNL ATS 교체","2022-09-02 09:00","2022-09-02 14:00","2022-09-02 09:00","2022-09-02 14:00","연속"]
[5,"남서울","강남","신양재S/S 345kV #2 PT CB","22-23년도 강남전력지사 변전협력회사 총액공사","-GIS 보통점검","2022-09-05 09:00","2022-09-05 18:00","취소","취소","연속"]
[6,"남서울","강남","신양재S/S 345kV #1 PT CB","22-23년도 강남전력지사 변전협력회사 총액공사","-GIS 보통점검","2022-09-05 09:00","2022-09-05 18:00","취소","취소","연속"]
[7,"남서울","동서울","동서울미금#1 T/L","동서울SS 동서울-미금1TL GIS 보통점검(7172,7100)","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-09-20 09:00","2022-09-20 18:00","취소","취소","연속"]
[8,"남서울","동서울","동서울S/S #3 M.Tr","동서울S/S 154kV 옥외철구 GIS화 공사","○ 154kV GIS * 34CCT 설치. ○ 보호배전반 설치 및 이설, 철거 등 1식 ○ 옥외철구 설비 * 1식 철거","2022-09-18 09:00","2022-10-01 18:00","2022-09-16 09:00","2022-09-29 18:00","연속"]
[9,"남서울","동서울","동서울미금#2 T/L","동서울SS 동서울-미금2TL GIS 조작시험(7272,7200)","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-09-21 09:00","2022-09-21 18:00","2022-09-21 09:00","2022-09-21 18:00","연속"]
[10,"남서울","동서울","곤지암동서울#1 T/L","동서울SS 곤지암-동서울1TL GIS, LA 보통점검(7171)","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-09-20 09:00","2022-09-20 14:00","2022-09-29 09:00","2022-09-29 18:00","연속"]
[11,"남서울","동서울","곤지암동서울#2 T/L","동서울SS 곤지암-동서울2TL GIS 조작시험(7271)","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-09-20 14:00","2022-09-20 18:00","2022-09-30 099:00","2022-09-30 18:00","연속"]
[12,"남서울","동서울","동서울미금#2 T/L","'22~'23년 동서울전력지사 가공송전 협력회사 총액공사","점퍼지지애자 교체공사","2022-09-27 10:00","2022-09-27 17:00","2022-09-27 10:00","2022-09-27 17:00","연속"]
[13,"남서울","동서울","동서울S/S #1 M.Tr","동서울S/S 154kV 옥외철구 GIS화 공사","○ 154kV GIS * 34CCT 설치. ○ 보호배전반 설치 및 이설, 철거 등 1식 ○ 옥외철구 설비 * 1식 철거","2022-09-01 09:00","2022-09-15 18:00","2022-09-01 09:00","2022-09-15 18:00","연속"]
[14,"남서울","영등포","신광명신문래#1 T/L","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","345kV 63kA GIS 24CB 설치","2022-09-01 10:00","2022-12-06 18:00","2022-09-01 10:00","2022-12-06 18:00","연속"]
[15,"남서울","영등포","신시흥신광명#1 T/L","'22-'23년 가공송전 협력회사 총액공사","추락방지시설 설치공사","2022-09-19 08:00","2022-09-21 18:00","2022-09-19 08:00","2022-09-21 18:00","연속"]
[16,"남서울","영등포","신광명S/S #2 M.Tr","신광명 노후 주변압기 교체공사(#2M.Tr)","345kV M.Tr 교체 3대","2022-09-01 09:00","2022-10-14 18:00","2022-09-01 09:00","2022-10-14 18:00","연속"]
[17,"인천","부평","신경서S/S #1 Sh.R CB","신경서S/S #1Sh.R 보통점검 및 7179GIS 조작시험","신경서S/S #1Sh.R 보통점검 및 7179GIS 조작시험","2022-09-01 09:00","2022-09-01 18:00","2022-09-01 09:00","2022-09-01 18:00","연속"]
[18,"인천","부평","신가좌S/S #1 M.Tr","신가좌S/S #1M.Tr 3차측 VCB교체관련 무부하가압","신가좌S/S #1M.Tr 3차측 VCB교체관련 무부하가압","2022-09-01 12:00","2022-09-02 18:00","2022-09-01 12:00","2022-09-02 18:00","연속"]
[19,"인천","부평","서인천C/C CB 7300","서인천S/Y 7300GIS 보통점검","서인천S/Y 7300GIS 보통점검","2022-09-13 09:00","2022-09-13 18:00","2022-09-13 09:00","2022-09-13 18:00","연속"]
[20,"인천","부평","신인천C/C CB 7671","신인천S/Y 7671GIS 보통점검","신인천S/Y 7671GIS 보통점검","2022-09-13 09:00","2022-09-13 18:00","2022-09-13 09:00","2022-09-13 18:00","연속"]
[21,"인천","시흥","신시흥영흥TP#4 T/L","영흥S/Y 신시흥영흥TP#4 T/L 염해방지 도포","영흥S/Y 신시흥영흥TP#4 T/L 염해방지 도포","2022-09-13 09:00","2022-09-13 18:00","2022-09-13 09:00","2022-09-13 18:00","연속"]
[22,"인천","부평","서인천C/C CB 7371","서인천S/Y 7371GIS 보통점검","서인천S/Y 7371GIS 보통점검","2022-09-14 09:00","2022-09-14 18:00","2022-09-14 09:00","2022-09-14 18:00","연속"]
[23,"인천","부평","신인천C/C CB 7772","신인천S/Y 7772GIS 보통점검","신인천S/Y 7772GIS 보통점검","2022-09-14 09:00","2022-09-14 18:00","2022-09-14 09:00","2022-09-14 18:00","연속"]
[24,"인천","시흥","서서울#2신시흥#2 T/L","신시흥S/S 서서울2신시흥#2 T/L 결상회로보완 및 보호반 성능개선","신시흥S/S 서서울2신시흥#2 T/L 결상회로보완 및 보호반 성능개선 7600, 7671 GIS 조작시험","2022-09-14 09:00","2022-09-15 18:00","2022-09-14 09:00","2022-09-15 18:00","연속"]
[25,"인천","시흥","신시흥영흥TP#2 T/L","영흥S/Y 신시흥영흥TP#2 T/L 염해방지 도포","영흥S/Y 신시흥영흥TP#2 T/L 염해방지 도포","2022-09-14 09:00","2022-09-14 18:00","2022-09-14 09:00","2022-09-14 18:00","연속"]
[26,"인천","시흥","신시흥영흥TP#3 T/L","영흥#2S/Y 신시흥영흥TP#3 T/L 염해방지 도포","영흥#2S/Y 신시흥영흥TP#3 T/L 염해방지 도포","2022-09-15 09:00","2022-09-15 18:00","2022-09-15 09:00","2022-09-15 18:00","연속"]
[27,"인천","부평","인천C/C CB 7600","인천복합S/Y 7600GIS 조작","인천복합S/Y 7600GIS 조작","2022-09-16 09:00","2022-09-16 13:00","2022-09-16 09:00","2022-09-16 13:00","연속"]
[28,"인천","시흥","신가좌신시흥#1 T/L","신시흥S/S 신가좌신시흥#1 T/L 결상회로보완","신시흥S/S 신가좌신시흥#1 T/L 결상회로보완","2022-09-16 09:00","2022-09-16 14:00","2022-09-16 09:00","2022-09-16 14:00","연속"]
[29,"인천","시흥","신시흥영흥TP#1 T/L","영흥#2S/Y 신시흥영흥TP#1 T/L 염해방지 도포","영흥#2S/Y 신시흥영흥TP#1 T/L 염해방지 도포","2022-09-16 09:00","2022-09-16 18:00","2022-09-16 09:00","2022-09-16 18:00","연속"]
[30,"인천","부평","인천C/C CB 7671","인천복합S/Y 7671GIS 조작","인천복합S/Y 7671GIS 조작","2022-09-16 13:00","2022-09-16 18:00","2022-09-16 13:00","2022-09-16 18:00","연속"]
[31,"인천","시흥","신시흥신광명#1 T/L","신시흥S/S 신시흥신광명#1 T/L 결상회로보완","신시흥S/S 신시흥신광명#1 T/L 결상회로보완 7971 GIS 조작시험","2022-09-16 14:00","2022-09-16 18:00","취소","취소","연속"]
[32,"인천","부평","서인천C/C #75 BUS","서인천S/Y 75BUS 모선보호반 교체","서인천S/Y 75BUS 모선보호반 교체","2022-09-19 09:00","2022-09-23 18:00","취소","취소","연속"]
[33,"인천","시흥","신시흥#1S/S #3 M.Tr","신시흥#1S/S 345kV #3 M.Tr 보통점검","신시흥#1S/S 345kV #3 M.Tr 보통점검 7872 GIS 정밀점검 병행","2022-09-19 09:00","2022-09-23 18:00","2022-09-19 09:00","2022-09-23 18:00","연속"]
[34,"인천","시흥","영흥1TP영흥2TP#1 T/L","영흥S/Y, 영흥#2S/Y 영흥TP연락#1 T/L 염해방지 도포","영흥S/Y, 영흥#2S/Y 영흥TP연락#1 T/L 염해방지 도포","2022-09-19 09:00","2022-09-20 18:00","2022-09-19 09:00","2022-09-20 18:00","연속"]
[35,"인천","시흥","영흥1TP영흥2TP#2 T/L","영흥S/Y, 영흥#2S/Y 영흥TP연락#2 T/L 염해방지 도포","영흥S/Y, 영흥#2S/Y 영흥TP연락#2 T/L 염해방지 도포","2022-09-21 09:00","2022-09-22 18:00","2022-09-21 09:00","2022-09-22 18:00","연속"]
[36,"인천","시흥","신가좌신시흥#2 T/L","신시흥S/S 신가좌신시흥#2 T/L 결상회로보완","신시흥S/S 신가좌신시흥#2 T/L 결상회로보완 7C71 GIS 조작시험","2022-09-23 09:00","2022-09-23 14:00","2022-09-23 09:00","2022-09-23 14:00","연속"]
[37,"인천","시흥","영흥T/P CB 7871","22년 시흥전력지사 362kV GIS 정밀점검 및 누기보수공사","영흥#2T/P 345kV 신시흥-영흥TP#1T/L GIS(7871) 정밀점검","2022-09-26 08:00","2022-09-28 18:00","2022-09-26 08:00","2022-09-28 18:00","연속"]
[38,"인천","직할","신부평S/S #1 M.Tr","신부평S/S #1M.Tr 배기팬 교체공사","신부평S/S #1M.Tr 배기팬 교체공사","2022-09-26 09:00","2022-09-27 18:00","2022-09-26 09:00","2022-09-27 18:00","연속"]
[39,"인천","시흥","영흥T/P CB 7371","영흥T/P 345kV 7371 GIS 보통점검","영흥T/P 345kV 7371 GIS 보통점검","2022-09-27 09:00","2022-09-27 18:00","2022-09-27 09:00","2022-09-27 18:00","연속"]
[40,"인천","시흥","영흥T/P CB 7372","영흥T/P 345kV 7372 GIS 보통점검","영흥T/P 345kV 7372 GIS 보통점검","2022-09-28 09:00","2022-09-28 18:00","2022-09-28 09:00","2022-09-28 18:00","연속"]
[41,"인천","직할","신부평S/S #2 M.Tr","신부평S/S #2M.Tr 배기팬 교체공사","신부평S/S #2M.Tr 배기팬 교체공사","2022-09-28 09:00","2022-09-29 18:00","2022-09-28 09:00","2022-09-29 18:00","연속"]
[42,"인천","시흥","영흥T/P CB 7800","22년 시흥전력지사 362kV GIS 정밀점검 및 누기보수공사","영흥#2T/P 345kV 신시흥-영흥TP#1T/L GIS(7800) 정밀점검","2022-09-29 08:00","2022-10-01 18:00","2022-09-29 08:00","2022-10-01 18:00","연속"]
[43,"경기북부","고양","신파주신덕은#1 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 정밀점검 병가선로","2022-09-26 07:00","2022-09-26 18:00","2022-09-26 07:00","2022-09-26 18:00","연속"]
[44,"경기북부","고양","신덕은S/S #2 M.Tr","신덕은S/S 170kV GIS PD센서 불량교체","신덕은S/S 170kV GIS PD센서 불량교체 - #2M.TR 1DS부(2MTR, 60BUS 휴전)","2022-09-06 09:00","2022-09-08 18:00","2022-09-06 09:00","2022-09-08 18:00","연속"]
[45,"경기북부","고양","신파주신덕은#2 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 정밀점검 병가선로","2022-09-13 07:00","2022-09-13 18:00","2022-09-13 07:00","2022-09-13 18:00","연속"]
[46,"경기북부","고양","신덕은S/S #3 M.Tr","345kV 관내 주변압기 상부 안전 난간대 설치","345kV 관내 주변압기 상부 안전 난간대 설치","2022-09-14 10:00","2022-09-14 18:00","2022-09-14 10:00","2022-09-14 18:00","연속"]
[47,"경기북부","고양","신덕은S/S #4 M.Tr","22년 고양전력지사 345kV 주변압기 및 OLTC 정밀점검공사","신덕은S/S #4M.Tr C상 본체 보통점검 및 OLTC 정밀점검","2022-09-27 09:00","2022-09-30 18:00","2022-09-27 09:00","2022-09-30 18:00","연속"]
[48,"경기북부","구리","미금S/S #3 Sh.R CB","22~23년 구리전력 변전협력 총액공사","미금S/S 345kV #3Sh.R 96D 방수커버 설치","2022-09-05 12:00","2022-09-05 15:00","2022-09-05 12:00","2022-09-05 15:00","연속"]
[49,"경기북부","구리","신가평미금#2 T/L","2022~23 구리전력 변전협력 총액공사","미금S/S 345kV 신가평-미금#2T/L GIS (7871, 7800) 보통점검","2022-09-15 09:00","2022-09-16 18:00","2022-09-15 09:00","2022-09-16 18:00","연속"]
[50,"경기북부","구리","미금성동#4 T/L","345kV 미금S/S 용량부족 차단기 대체공사","345kV 미금S/S 용량부족 차단기 대체공사(#77Bay) - 345kV 50kA GIS → 63kA GIS 용량대체","2022-09-19 09:00","2022-12-02 18:00","2022-09-19 09:00","2022-12-02 18:00","연속"]
[51,"경기북부","구리","동서울미금#1 T/L","2022~23 구리전력 변전협력 총액공사","미금S/S 345kV 동서울-미금#1T/L GIS (7371, 7300) 보통점검","2022-09-19 09:00","2022-09-20 18:00","2022-09-19 09:00","2022-09-20 18:00","연속"]
[52,"경기북부","구리","미금S/S #6 Sh.R","2022~23 구리전력 변전협력 총액공사","미금S/S 345kV #6Sh.R 7679 GIS 보통점검","2022-09-28 09:00","2022-09-28 18:00","2022-09-28 09:00","2022-09-28 18:00","연속"]
[53,"경기북부","구리","신가평미금#1 T/L","345kV 미금S/S 용량부족 차단기 대체공사","345kV 미금S/S 용량부족 차단기 대체공사(#77Bay) - 345kV 50kA GIS → 63kA GIS 용량대체","2022-09-19 09:00","2022-12-02 18:00","2022-09-19 09:00","2022-12-02 18:00","연속"]
[54,"경기북부","구리","미금성동#2 T/L","2022~23 구리전력 변전협력 총액공사","미금S/S 345kV 미금-성동#2T/L GIS (7271, 7200) 보통점검","2022-09-01 09:00","2022-09-02 18:00","2022-09-01 09:00","2022-09-02 18:00","매일"]
[55,"경기북부","구리","미금S/S #2 Sh.R CB","22~23년 구리전력 변전협력 총액공사","미금S/S 345kV #2Sh.R 96D 방수커버 설치","2022-09-05 09:00","2022-09-05 12:00","2022-09-05 09:00","2022-09-05 12:00","연속"]
[56,"경기북부","구리","미금S/S #2 M.Tr","미금S/S 종합예방진단시스템 설치","○ 미금S/S 종합예방진단시스템 설치 관련 규격 실측 - OLTC 부분방전 센서 및 설치위치 간섭여부 확인 - 부싱진단장치 제작 관련 시험탭 규격 실측 - DGA 배관 설치 길이 산출","2022-09-19 09:00","2022-09-19 18:00","2022-09-19 09:00","2022-09-19 18:00","연속"]
[57,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 종합예방진단시스템 설치","○ 미금S/S 종합예방진단시스템 설치 관련 규격 실측 - OLTC 부분방전 센서 및 설치위치 간섭여부 확인 - 부싱진단장치 제작 관련 시험탭 규격 실측 - DGA 배관 설치 길이 산출","2022-09-15 09:00","2022-09-15 18:00","2022-09-15 09:00","2022-09-15 18:00","연속"]
[58,"경기북부","구리","미금S/S #3 M.Tr","미금S/S 종합예방진단시스템 설치","○ 미금S/S 종합예방진단시스템 설치 관련 규격 실측 - OLTC 부분방전 센서 및 설치위치 간섭여부 확인 - 부싱진단장치 제작 관련 시험탭 규격 실측 - DGA 배관 설치 길이 산출","2022-09-14 09:00","2022-09-14 18:00","2022-09-14 09:00","2022-09-14 18:00","연속"]
[59,"경기북부","구리","신가평포천LNGCC#2 T/L","2022~23 구리전력 변전협력 총액공사","송전선로 단상 자동재투입용 GIS 결상회로 개선","2022-09-21 09:00","2022-09-21 18:00","2022-09-21 09:00","2022-09-21 18:00","연속"]
[60,"경기북부","구리","신가평S/S CB 7471","2022~23 구리전력 변전협력 총액공사","신가평S/S 345kV #3Sh.R GIS (7471) 보통점검","2022-09-29 09:00","2022-09-29 18:00","2022-09-29 09:00","2022-09-29 18:00","연속"]
[61,"경기북부","구리","신포천S/S #2 M.Tr","22년도 구리전력지사 345kV M.Tr, Sh.R 점검공사","신포천S/S 345kV #2M.Tr A,B상 보통점검 신포천S/S 345kV #2M.Tr C상 정밀점검 신포천S/S 345kV #2M.Tr A,B,C상 OLTC 정밀점검","2022-09-05 09:00","2022-09-16 18:00","2022-09-05 09:00","2022-09-16 18:00","연속"]
[62,"경기북부","구리","신포천포천LNGCC#2 T/L","2022~23 구리전력 변전협력 총액공사","송전선로 단상 자동재투입용 GIS 결상회로 개선","2022-09-23 09:00","2022-09-23 18:00","2022-09-23 09:00","2022-09-23 18:00","연속"]
[63,"경기북부","구리","신포천S/S CB 7571","2022~23 구리전력 변전협력 총액공사","신포천S/S 345kV 신포천-동두천CC#1T/L 7571 GIS 개폐타임 측정","2022-09-27 09:00","2022-09-27 14:00","2022-09-27 09:00","2022-09-27 14:00","연속"]
[64,"경기북부","구리","신포천S/S CB 7500","2022~23 구리전력 변전협력 총액공사","신포천S/S 345kV 신포천-동두천CC#1T/L TIE 7500 GIS 개폐타임 측정","2022-09-27 14:00","2022-09-27 18:00","2022-09-27 14:00","2022-09-27 18:00","연속"]
[65,"경기북부","구리","신포천포천LNGCC#1 T/L","2022~23 구리전력 변전협력 총액공사","송전선로 단상 자동재투입용 GIS 결상회로 개선","2022-09-22 09:00","2022-09-22 18:00","2022-09-22 09:00","2022-09-22 18:00","연속"]
[66,"경기북부","직할","신덕은동두천CC#1 T/L","2022-2023년 경기북부 직할 변전협력회사 총액공사","신덕은-동두천CC #1TL 재폐로 결상회로 개선","2022-09-20 09:00","2022-09-20 18:00","2022-09-20 09:00","2022-09-20 18:00","연속"]
[67,"경기북부","직할","신의정부미금#1 T/L","2022-2023년 경기북부 직할 변전협력회사 총액공사","신의정부S/S 362kV GIS 7571 조작시험 및 결상회로 개선 미금S/S GIS, CVT, LA 보통점검, 결상회로 개선","2022-09-14 09:00","2022-09-14 18:00","2022-09-14 09:00","2022-09-14 18:00","연속"]
[68,"경기북부","직할","신의정부미금#2 T/L","2022-2023년 경기북부 직할 변전협력회사 총액공사","신의정부S/S 362kV GIS 7571 조작시험 및 결상회로 개선 미금S/S GIS, CVT, LA 보통점검, 결상회로 개선","2022-09-13 09:00","2022-09-13 18:00","2022-09-13 09:00","2022-09-13 18:00","연속"]
[69,"경기북부","직할","신의정부S/S #1 Sh.R CB","22-23년 경기북부 직할 변전협력회사 총액공사","#1Sh.R 권선온도계 교체","2022-09-06 09:00","2022-09-06 18:00","2022-09-06 09:00","2022-09-06 18:00","연속"]
[70,"경기북부","직할","양주S/S #4 M.Tr","22-23년 경기북부 직할 변전협력회사 총액공사","양주S/S 345kV #4M.Tr 정밀점검(본체: A,B상, OLTC: C상)","2022-09-19 09:00","2022-09-23 18:00","2022-09-19 09:00","2022-09-23 18:00","연속"]
[71,"경기북부","직할","양주중부#1 T/L","2022-2023년 경기북부 직할 변전협력회사 총액공사","양주S/S 362kV GIS 7571, 7500 보통점검, 7579 CB 조작시험","2022-09-15 09:00","2022-09-16 18:00","2022-09-15 09:00","2022-09-16 18:00","매일"]
[72,"경기북부","직할","양주S/S #2 M.Tr","22-23년 경기북부 직할 변전협력회사 총액공사","양주S/S 345kV #2M.Tr 보호배전반 대체","2022-09-13 09:00","2022-09-16 18:00","2022-09-13 09:00","2022-09-16 18:00","연속"]
[73,"경기","군포","서서울S/S CB 7571","서서울SS 7571 전자변교체","서서울SS 서서울-신광명#1T/L 7571 전자변교체","2022-09-19 09:00","2022-09-21 18:00","2022-09-19 09:00","2022-09-21 18:00","연속"]
[74,"경기","군포","서서울S/S CB 7671","서서울SS 7671 전자변교체","서서울SS 서서울-신광명#2T/L 7671전자변교체","2022-09-28 09:00","2022-09-30 18:00","2022-09-28 09:00","2022-09-30 18:00","연속"]
[75,"경기","군포","서서울S/S CB 7500","서서울SS 7500 전자변교체","서서울SS 서서울-신광명#1T/L 7500 전자변교체","2022-09-22 09:00","2022-09-24 18:00","2022-09-22 09:00","2022-09-24 18:00","연속"]
[76,"경기","군포","서서울신광명#1 T/L","서서울SS 7571,7500 결상회로 개선, CVT 보통점검","서서울SS 서서울-신광명#1T/L 7571,7500 결상회로 개선,CVT보통점검","2022-09-26 09:00","2022-09-26 18:00","2022-09-26 09:00","2022-09-26 18:00","연속"]
[77,"경기","군포","서서울신광명#2 T/L","서서울SS 7671,7600 결상회로 개선,CVT 보통점검","서서울SS 서서울-신광명#2T/L 7671,7600 결상회로 개선,CVT보통점검","2022-09-27 09:00","2022-09-27 18:00","취소","취소","연속"]
[78,"경기","군포","신안산S/S #4 M.Tr","신안산S/S #4 M.Tr 2차 GIS 보통점검","신안산S/S #4 M.Tr 2차 GIS 보통점검","2022-09-26 09:00","2022-09-26 18:00","2022-09-26 09:00","2022-09-26 18:00","연속"]
[79,"경기","군포","신안산S/S #3 M.Tr","신안산S/S #3 M.Tr 보통점검","신안산S/S #3 M.Tr 보통점검","2022-09-15 09:00","2022-09-16 18:00","2022-09-15 09:00","2022-09-16 18:00","연속"]
[80,"경기","군포","신안산S/S #1 M.Tr","신안산S/S #1 M.Tr 보통점검","신안산S/S #1 M.Tr 보통점검","2022-09-13 09:00","2022-09-14 18:00","2022-09-13 09:00","2022-09-14 18:00","연속"]
[81,"경기","동부","곤지암신충주#1 T/L","여주복합발전소 연계선로 건설공사","345kV 곤지암-신충주T/L 92~97호 임시 2기","2022-09-16 07:00","2022-09-28 18:00","2022-09-16 07:00","2022-09-28 18:00","연속"]
[82,"경기","동부","곤지암신충주#2 T/L","여주복합발전소 연계선로 건설공사","345kV 곤지암-신충주T/L 92~97호 임시 2기","2022-09-03 07:00","2022-09-15 18:00","2022-09-03 07:00","2022-09-15 18:00","연속"]
[83,"경기","성남","신성남신양재#1 T/L","2022년 성남전력지사 변전협력회사 총액공사","7871,7800 조작시험 - 러버히터 재설치 - 에어링 밸브 점검 - 7800BAY 보호반 접점변경","2022-09-13 09:00","2022-09-13 18:00","2022-09-13 09:00","2022-09-13 18:00","연속"]
[84,"경기","성남","신성남S/S #4 M.Tr","22년 성남전력지사 M.Tr 보통점검 공사","- VCB대체관련 안전이격 확보","2022-09-17 09:00","2022-09-17 12:00","2022-09-17 09:00","2022-09-17 12:00","연속"]
[85,"경기","성남","신성남S/S #5 M.Tr","22년 성남전력지사 M.Tr 보통점검 공사","- M.Tr 보통점검 - 부싱절연유 채유 - 순간압력센서 설치 - 2차 GIS 보통점검 - 3차 모선,DS 보통점검 - S.Tr 초기점검 - VCB 대체","2022-09-17 09:00","2022-09-18 18:00","취소","취소","연속"]
[86,"경기","성남","신수원S/S #3 M.Tr","신수원S/S 종합예방진단시스템 설치공사","신수원S/S 종합예방진단시스템 설치공사","2022-09-19 09:00","2022-09-19 18:00","2022-09-19 09:00","2022-09-19 18:00","연속"]
[87,"경기","성남","신수원S/S #2 M.Tr","22년 성남전력지사 M.Tr 보통점검 공사","- M.Tr 보통점검 - 7272 하자점검 - 2차 GIS 조작시험, 3차 GIS 보통점검 - CVT 초기점검 - 1차 LA 대체, 2차 LA 보통점검 - 3차 모선 보통점검 - 순간압력센서 설치","2022-09-15 09:00","2022-09-16 18:00","2022-09-15 09:00","2022-09-16 18:00","연속"]
[88,"경기","성남","신수원S/S #1 M.Tr","2022년 성남전력지사 변전협력회사 총액공사","- 3차 GIS 가스치환","2022-09-22 09:00","2022-09-23 18:00","2022-09-22 09:00","2022-09-23 18:00","연속"]
[89,"경기","성남","신수원S/S #4 M.Tr","신수원S/S 종합예방진단시스템 설치공사","신수원S/S 종합예방진단시스템 설치공사","2022-09-20 09:00","2022-09-20 18:00","2022-09-20 09:00","2022-09-20 18:00","연속"]
[90,"경기","성남","신안성신용인#2 T/L","345kV 신안성-신용인T/L OPGW 증설공사","* 신안성S/T ~ 신용인S/T간 GW→OPGW 120SQ 48C 신설 26.507km * 신안성S/T ~ 신안성ICT실간 FOFC 48C 신설 0.430km * 신용인S/T ~ 신용인ICT실간 FOFC 48C 신설 0.308km * 접속, 최종시험 및 기타 부대공사 1식","2022-09-14 07:00","2022-10-28 18:00","2022-09-14 07:00","2022-10-28 18:00","연속"]
[91,"경기","성남","신안성S/S CB 7B72","2022년 성남전력 362/170kV GIS 보통점검 공사","- GIS 보통점검","2022-09-26 09:00","2022-09-26 18:00","2022-09-26 09:00","2022-09-26 18:00","연속"]
[92,"경기","성남","신안성S/S CB 7B00","2022년 성남전력 362/170kV GIS 보통점검 공사","- GIS 보통점검","2022-09-27 09:00","2022-09-27 18:00","2022-09-27 09:00","2022-09-27 18:00","연속"]
[93,"경기","성남","신안성S/S CB 7B71","2022년 성남전력 362/170kV GIS 보통점검 공사","- GIS 보통점검","2022-09-13 09:00","2022-09-13 18:00","2022-09-13 09:00","2022-09-13 18:00","연속"]
[94,"경기","성남","신안성신성남#2 T/L","345kV 신안성-신용인T/L OPGW 증설공사","* 신안성S/T ~ 신용인S/T간 GW→OPGW 120SQ 48C 신설 26.507km * 신안성S/T ~ 신안성ICT실간 FOFC 48C 신설 0.430km * 신용인S/T ~ 신용인ICT실간 FOFC 48C 신설 0.308km * 접속, 최종시험 및 기타 부대공사 1식","2022-09-14 07:00","2022-10-25 18:00","2022-09-14 07:00","2022-10-25 18:00","연속"]
[95,"경기","성남","신용인동서울#1 T/L","345kV 신용인-동서울T/L No.53 지장철탑 이설공사(서울세종)","서울세종 고속도로 개설관련 지장철탑 이설공사(요청자 부담 공사) - 임시선로 구성 후 본선로 구성 시행 - 1기 철거 1기 신설 - 시공업체 : 신우전설(주), 감리업체 : (주)동성기술감리단","2022-09-01 07:30","2022-09-07 18:00","2022-09-01 07:30","2022-09-07 18:00","연속"]
[96,"경기","성남","신용인신수원 T/L","2022년 성남전력지사 변전협력회사 총액공사","- CVT 대체","2022-09-26 09:00","2022-09-27 18:00","2022-09-26 09:00","2022-09-27 18:00","연속"]
[97,"경기","직할","화성S/S #1 M.Tr","화성S/S 154kV 장기사용 GIS 교체공사","#1M.Tr 2차 GIS 대체","2022-09-13 09:00","2022-10-16 18:00","2022-09-13 09:00","2022-10-16 18:00","연속"]
[98,"경기","평택","고덕#2S/S #2 M.Tr","고덕#2S/S 154kV SW 증설공사","고덕2-에어퍼스트#1T/L GIS 증설","2022-09-06 11:00","2022-09-07 11:00","2022-09-06 11:00","2022-09-07 11:00","연속"]
[99,"경기","평택","고덕고덕2#1 T/L","345kV 고덕#2S/S 건설공사","#3M.Tr 무부하가압용","2022-09-15 09:00","2022-09-16 18:00","2022-09-15 09:00","2022-09-16 18:00","연속"]
[100,"경기","평택","고덕#2S/S #2 BUS","345kV 고덕#2S/S 건설공사","#3M.Tr 무부하가압용","2022-09-15 09:00","2022-09-16 18:00","2022-09-15 09:00","2022-09-16 18:00","연속"]
[101,"경기","평택","서안성S/S CB 7671","345kV 서안성S/S GIS 증설공사","- 362kV GIS 3CB 증설 - 보호배전반 등 설치 x 1식","2022-09-13 09:00","2022-09-14 18:00","2022-09-13 09:00","2022-09-14 18:00","연속"]
[102,"경기","평택","서안성S/S #2 BUS","345kV 서안성S/S GIS 증설공사","- 362kV GIS 3CB 증설 - 보호배전반 등 설치 x 1식","2022-09-13 09:00","2022-09-14 18:00","2022-09-13 09:00","2022-09-14 18:00","연속"]
[103,"경기","평택","화성평택TP#1 T/L","22년 평택전력지사 변전협력회사 총액공사","평택T/P 345kV 화성-평택#1T/L 인출DS 인디케이터 불량 보수","2022-09-13 10:00","2022-09-13 18:00","2022-09-08 10:00","2022-09-08 18:00","연속"]
[104,"강원","강릉","신양양S/S #2 M.Tr","2022년 345kV M.Tr 정밀점검","신양양S/S #2M.Tr 정밀점검","2022-09-19 10:00","2022-10-07 18:00","2022-09-19 10:00","2022-10-07 18:00","연속"]
[105,"강원","강릉","신양양S/S #3 M.Tr","2022년 변전협력회사 총액공사","차단기 조작시험 (7400,7472), #2-2Sh.R 초기점검 #2S.Tr 보통점검 신양양S/S #3M.Tr 3차 CB, #2S.Tr 조작시험","2022-09-14 10:00","2022-09-15 18:00","취소","취소","연속"]
[106,"강원","강릉","안인개폐소신양양 T/L","2022~2023년 강릉전력지사 가공송전헙력회사 총액공사","○ 수직, 수평 추락방지장치 설치(345kV 양양양수T/L No.3~192)","2022-09-01 07:00","2022-09-29 18:00","2022-09-01 07:00","2022-09-29 18:00","매일"]
[107,"강원","강릉","신양양양양PP T/L","2022년 변전협력회사 총액공사","양양양수 피뢰기 대체 신양양S/S(7100), 양양PP(7171) 조작시험 362kV GIS 보통점검","2022-09-28 10:00","2022-09-30 18:00","2022-09-30 08:00","2022-09-30 12:00","연속"]
[108,"강원","동해","신제천동해#2 T/L","2022년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검","2022-09-23 08:00","2022-09-28 18:00","2022-09-23 08:00","2022-09-26 18:00","연속"]
[109,"강원","동해","신제천동해#1 T/L","2022년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검","2022-09-15 08:00","2022-09-22 18:00","2022-09-19 08:00","2022-09-22 18:00","연속"]
[110,"강원","태백","신태백S/S CB 7672","신태백S/S 345kV GIS 유압장치 하자보수","신태백S/S 345kV GIS 7672CB 스탑밸브, 유압력 게이지 교체 및 고정피팅 보강","2022-09-13 09:30","2022-09-13 18:00","2022-09-14 09:30","2022-09-14 18:00","연속"]
[111,"강원","태백","신태백S/S CB 7772","신태백S/S 345kV GIS 유압장치 하자보수","신태백S/S 345kV GIS 7772CB 스탑밸브, 유압력 게이지 교체 및 고정피팅 보강","2022-09-23 09:30","2022-09-23 13:30","2022-09-23 09:30","2022-09-23 13:30","연속"]
[112,"강원","태백","신태백S/S CB 7700","신태백S/S 345kV GIS 유압장치 하자보수","신태백S/S 345kV GIS 7700CB 스탑밸브, 유압력 게이지 교체 및 고정피팅 보강","2022-09-22 13:30","2022-09-22 18:00","2022-09-22 13:30","2022-09-22 18:00","연속"]
[113,"강원","태백","신태백S/S CB 7771","신태백S/S 345kV GIS 유압장치 하자보수","신태백S/S 345kV GIS 7771CB 스탑밸브, 유압력 게이지 교체 및 고정피팅 보강","2022-09-22 09:30","2022-09-22 13:30","2022-09-22 09:30","2022-09-22 13:30","연속"]
[114,"강원","태백","신태백S/S CB 7600","신태백S/S 345kV GIS 유압장치 하자보수","신태백S/S 345kV GIS 7600CB 스탑밸브, 유압력 게이지 교체 및 고정피팅 보강","2022-09-21 13:30","2022-09-21 18:00","2022-09-21 13:30","2022-09-21 18:00","연속"]
[115,"강원","태백","신태백S/S CB 7671","신태백S/S 345kV GIS 유압장치 하자보수","신태백S/S 345kV GIS 7671CB 스탑밸브, 유압력 게이지 교체 및 고정피팅 보강","2022-09-21 09:30","2022-09-21 13:30","2022-09-21 09:30","2022-09-21 13:30","연속"]
[116,"강원","태백","신태백S/S CB 7572","신태백S/S 345kV GIS 유압장치 하자보수","신태백S/S 345kV GIS 7572CB 스탑밸브, 유압력 게이지 교체 및 고정피팅 보강","2022-09-20 13:30","2022-09-20 18:00","2022-09-20 13:30","2022-09-20 18:00","연속"]
[117,"강원","태백","신태백S/S CB 7500","신태백S/S 345kV GIS 유압장치 하자보수","신태백S/S 345kV GIS 7500CB 스탑밸브, 유압력 게이지 교체 및 고정피팅 보강","2022-09-20 09:30","2022-09-20 13:30","2022-09-20 09:30","2022-09-20 13:30","연속"]
[118,"강원","태백","신태백S/S CB 7571","신태백S/S 345kV GIS 유압장치 하자보수","신태백S/S 345kV GIS 7571CB 스탑밸브, 유압력 게이지 교체 및 고정피팅 보강","2022-09-19 13:30","2022-09-19 18:00","2022-09-19 13:30","2022-09-19 18:00","연속"]
[119,"강원","태백","신태백S/S CB 7472","신태백S/S 345kV GIS 유압장치 하자보수","신태백S/S 345kV GIS 7472CB 스탑밸브, 유압력 게이지 교체 및 고정피팅 보강","2022-09-19 09:30","2022-09-19 13:30","2022-09-19 09:30","2022-09-19 13:30","연속"]
[120,"강원","태백","신태백S/S CB 7372","신태백S/S 345kV GIS 유압장치 하자보수","신태백S/S 345kV GIS 7372CB 스탑밸브, 유압력 스위치, 게이지 교체 및 고정피팅 보강","2022-09-15 13:30","2022-09-15 18:00","2022-09-15 13:30","2022-09-15 18:00","연속"]
[121,"강원","태백","신태백S/S CB 7300","신태백S/S 345kV GIS 유압장치 하자보수","신태백S/S 345kV GIS 7300CB 스탑밸브, 유압력 게이지 교체 및 고정피팅 보강","2022-09-15 09:30","2022-09-15 13:30","2022-09-15 09:30","2022-09-15 13:30","연속"]
[122,"강원","태백","신태백S/S CB 7371","신태백S/S 345kV GIS 유압장치 하자보수","신태백S/S 345kV GIS 7371CB 스탑밸브, 유압력 게이지 교체 및 고정피팅 보강","2022-09-14 09:30","2022-09-14 13:30","2022-09-23 13:30","2022-09-23 18:00","연속"]
[123,"강원","태백","신태백S/S CB 7471","22-23년 태백전력지사 변전협력회사 총액공사","신태백S/S 345kV #2Sh.R 69Q 인디게이터 불량 보수 및 가스검출계전기 교체","2022-09-16 09:00","2022-09-16 18:00","2022-09-16 09:00","2022-09-16 18:00","연속"]
[124,"강원","태백","신태백S/S #2 Sh.R CB","22-23년 태백전력지사 변전협력회사 총액공사","신태백S/S 345kV #2Sh.R 69Q 인디게이터 불량 보수 및 가스검출계전기 교체","2022-09-16 09:00","2022-09-16 18:00","2022-09-16 09:00","2022-09-16 18:00","연속"]
[125,"강원","태백","신태백S/S CB 7400","22-23년 태백전력지사 변전협력회사 총액공사","신태백S/S 345kV #2Sh.R 69Q 인디게이터 불량 보수 및 가스검출계전기 교체","2022-09-16 09:00","2022-09-16 18:00","2022-09-16 09:00","2022-09-16 18:00","연속"]
[126,"충북","직할","신중부신진천#1 T/L","신중부S/S 345kV LS산전제 GIS 부품교체","DS부 부분방전 해소를 위한 부품교체","2022-09-05 10:00","2022-09-06 18:00","2022-09-20 10:00","2022-09-21 18:00","연속"]
[127,"충북","직할","신중부신진천#2 T/L","신중부S/S 345kV LS산전제 GIS 부품교체","DS부 부분방전 해소를 위한 부품교체","2022-09-07 10:00","2022-09-08 18:00","2022-09-22 10:00","2022-09-23 18:00","연속"]
[128,"충북","청주","남청주S/S CB 7600","남청주S/S 345kV 장기사용 GIS 교체공사","76 BAY 2CB 철거 3CB 설치","2022-09-01 09:00","2022-09-18 18:00","2022-09-01 09:00","2022-09-18 18:00","연속"]
[129,"충북","청주","남청주S/S CB 7672","남청주S/S 345kV 장기사용 GIS 교체공사","76 BAY 2CB 철거 3CB 설치","2022-09-19 09:00","2022-10-03 18:00","2022-09-19 09:00","2022-10-03 18:00","연속"]
[130,"충북","청주","남청주S/S #3 M.Tr","남청주S/S 345kV 장기사용 GIS 교체공사","76 BAY 2CB 철거 3CB 설치","2022-09-17 09:00","2022-09-18 18:00","2022-09-17 09:00","2022-09-18 18:00","연속"]
[131,"충북","청주","남청주S/S #3 M.Tr","남청주S/S 345kV 장기사용 GIS 교체공사","76 BAY 2CB 철거 3CB 설치","2022-09-03 09:00","2022-09-04 18:00","2022-09-03 09:00","2022-09-04 18:00","연속"]
[132,"충북","청주","신옥천신남원#1 T/L","345kV 신옥천-신남원T/L No.184~196 안전이격확보공사","1. 구간 : 345kV 신옥천~신남원T/L Nol184~196 2. 공사수량 - 지지물 4기교체(산형강 3기, 관형주1기) - 전선교체 : 3,166C-km(No.184~186, 190~196) - 전선이동(재사용) : 1,821C-km(No.186~190) - OPGW 교체 : 4.8km (No.186~198)","2022-09-20 08:00","2022-09-26 18:00","취소","취소","연속"]
[133,"충북","청주","신옥천S/S #1 M.Tr","제작사 입회 DS부 조작기어 점검 및 보수작업","신옥천S/S #1M.Tr 170 GIS 제작사 입회 6146 DS부 웜기어 점검 및 보수작업 시행 (설비 하자기간에 따른 이른 점검)","2022-09-06 10:00","2022-09-07 18:00","2022-09-06 10:00","2022-09-07 18:00","연속"]
[134,"충북","청주","신옥천신남원#2 T/L","345kV 신옥천-신남원T/L No.184~196 안전이격 확보공사","1. 구간 : 345kV 신옥천~신남원T/L No.184~196 2. 공사수량 - 지지물 4기교체(산형강 3기, 관형주1기) - 전선교체 : 3,166C-km(No.184~186, 190~196) - 전선이동(재사용) : 1,821C-km(No.186~190) - OPGW 교체 : 4.8km (No.186~198)","2022-09-27 08:00","2022-10-06 18:00","취소","취소","연속"]
[135,"충북","충주","신제천S/S #2 TCSC CB","신제천S/S #1,2TCSC 하자점검","신제천S/S #1,2TCSC 하자점검","2022-09-23 09:00","2022-09-25 18:00","취소","취소","연속"]
[136,"충북","충주","신제천S/S #1 TCSC CB","신제천S/S #1,2TCSC 하자점검","신제천S/S #1,2TCSC 하자점검","2022-09-19 09:00","2022-09-22 18:00","취소","취소","연속"]
[137,"충북","충주","신제천신충주#2 T/L","345kV 신제천-신충주 등 6개 T/L 송전피뢰기 설치공사","345kV 신제천-신충주#2 T/L No.1~59,79~96 송전피뢰기 설치공사","2022-09-13 07:00","2022-09-23 18:00","취소","취소","매일"]
[138,"충북","충주","신충주S/S #4 M.Tr","345kV 신충주S/S 종합예방진단시스템 설치 관련 M.Tr 규격조사","신충주S/S 종합예방진단시스템 구축공사 -부싱 시험탭 분리 및 규격 실측 -OLTC센서 설치가능여부 확인 및 센서부 실측 ※충주전력지사 정비팀 병행작업※ -345kV #4M.Tr GIS 보통점검, 부싱 절연유 채유","2022-09-16 09:00","2022-09-16 18:00","2022-09-23 09:00","2022-09-23 18:00","연속"]
[139,"충북","충주","신충주S/S #3 M.Tr","345kV 신충주S/S 종합예방진단시스템 설치 관련 M.Tr 규격조사","신충주S/S 종합예방진단시스템 구축공사 -부싱 시험탭 분리 및 규격 실측 -OLTC센서 설치가능여부 확인 및 센서부 실측 ※충주전력지사 정비팀 병행작업※ -345kV #3M.Tr GIS 보통점검, 부싱절연유 채유","2022-09-15 09:00","2022-09-15 18:00","2022-09-22 09:00","2022-09-22 18:00","연속"]
[140,"충북","충주","신충주S/S #2 M.Tr","345kV 신충주S/S 종합예방진단시스템 설치 관련 M.Tr 규격조사","※ 22년도 점검계획물량 미대상[병행작업불가]으로 단독 작업 시행※ 신충주S/S 종합예방진단시스템 구축공사 -부싱 시험탭 분리 및 규격 실측 -OLTC센서 설치가능여부 확인 및 센서부 실측","2022-09-14 13:00","2022-09-14 18:00","2022-09-21 13:00","2022-09-21 18:00","연속"]
[141,"충북","충주","신충주S/S #1 M.Tr","345kV 신충주S/S 종합예방진단시스템 설치 관련 M.Tr 규격조사","※ 22년도 점검계획물량 미대상[병행작업불가]으로 단독 작업 시행※ 신충주S/S 종합예방진단시스템 구축공사 -부싱 시험탭 분리 및 규격 실측 -OLTC센서 설치가능여부 확인 및 센서부 실측","2022-09-14 09:00","2022-09-14 13:00","2022-09-21 09:00","2022-09-21 13:00","연속"]
[142,"충북","충주","신제천신충주#1 T/L","22-23년 충주전력지사 변전정비 총액공사","신충주S/S 신제천-신충주#1T/L , TIE GIS 보통점검","2022-09-07 09:00","2022-09-07 18:00","취소","취소","연속"]
[143,"대전세종충남","대전","신계룡청양 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지장치 설치공사","[송전] 345kV 신옥천-청양T/L 추락방지장치 설치공사","2022-09-30 08:00","2022-09-30 18:00","2022-09-30 08:00","2022-09-30 18:00","연속"]
[144,"대전세종충남","대전","신옥천신계룡 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지장치 설치공사","[송전] 345kV 신옥천-청양T/L 추락방지장치 설치공사","2022-09-23 08:00","2022-09-29 18:00","2022-09-23 08:00","2022-09-29 18:00","매일"]
[145,"대전세종충남","서산","당진T/P CB 7100","'22년 서산P/O 변전협력회사 총액공사","당진화력S/S 345kV 1호기 인출 LA 대체 -(병행) 당진화력S/S 345kV 1호기 7172 CB 보통점검","2022-09-07 09:00","2022-09-08 18:00","2022-09-07 09:00","2022-09-08 18:00","연속"]
[146,"대전세종충남","서산","당진T/P CB 7172","'22년 서산P/O 변전협력회사 총액공사","당진화력S/S 345kV 1호기 인출 LA 대체 -(병행) 당진화력S/S 345kV 1호기 7172 CB 보통점검","2022-09-07 09:00","2022-09-08 18:00","2022-09-07 09:00","2022-09-08 18:00","연속"]
[147,"대전세종충남","서산","북당진S/S #1 BUS","북당진변전소 7951DS 고장복구 작업","북당진변전소 7951DS B상 고장복구 작업","2022-09-01 09:00","2022-09-06 18:00","2022-09-01 09:00","2022-09-06 18:00","연속"]
[148,"대전세종충남","서산","북당진S/S #2 BUS","북당진변전소 2단계 HVDC용 GIS설치공사","북당진변전소 2단계 HVDC용 GIS 설치공사(무부하가압, 79,7A Bay)","2022-09-07 09:00","2022-09-08 18:00","2022-09-07 09:00","2022-09-07 18:00","연속"]
[149,"대전세종충남","서산","신당진개폐소태안TP#1 T/L","신당진개폐소 개폐소-태안화력#1T/L GIS 가스누기 보수공사","신당진개폐소 345kV 개폐소-태안화력#1T/L GIS 가스누기 보수공사 - (병행1) 신당진개폐소 7A71CB, 7A00CB, LA, CVT 보통점검, - (병행2) 태안T/P LA, CVT 하자점검","2022-09-05 08:00","2022-09-08 18:00","2022-09-05 08:00","2022-09-08 18:00","연속"]
[150,"대전세종충남","서산","신당진개폐소태안TP#2 T/L","개폐소-태안화력#2T/L T/L 보호반 대체공사","신당진개폐소, 태안화력S/Y 개폐소-태안화력#2T/L T/L 보호반 대체공사 - (병행) 신당진개폐소 7C00CB, LA 보통점검","2022-09-13 08:00","2022-09-17 18:00","2022-09-13 08:00","2022-09-17 18:00","연속"]
[151,"대전세종충남","서산","신서산신당진#1 T/L","'22년 서산P/O 변전협력회사 총액공사","신당진S/S 345kV 신서산-신당진#1T/L 7172 CB, LA, 보통점검 CVT 하자점검 -(병행) 신서산S/S 345kV 신서산-신당진#1T/L 7872 CB 보통점검","2022-09-13 09:00","2022-09-13 18:00","취소","취소","연속"]
[152,"대전세종충남","천안","신온양S/S #4 M.Tr","신온양S/S 345kV #4 M.Tr 보통점검","신온양S/S 345kV #4 M.Tr 보통점검","2022-09-22 09:00","2022-09-23 18:00","2022-09-22 09:00","2022-09-23 18:00","연속"]
[153,"대전세종충남","천안","신탕정S/S #3 M.Tr","신탕정S/S 345kV #3 M.Tr 보통점검","신탕정S/S 345kV #3 M.Tr 보통점검","2022-09-15 09:00","2022-09-16 18:00","2022-09-15 09:00","2022-09-16 18:00","연속"]
[154,"대전세종충남","천안","아산S/S #1 M.Tr","345kV 아산S/S 취약설비 보강 및 배전반 정비공사","- 모자익배전반 철거 * 1식 - 집중감시제어반+디지탈축소형모자익배전반 설치 *1식","2022-09-19 09:00","2022-10-14 18:00","취소","취소","연속"]
[155,"대전세종충남","천안","아산S/S #1 M.Tr","아산S/S 345kV #1 M.Tr 2차 부싱절연유 채유","(배전반 정비공사 취소시)아산S/S 345kV #1 M.Tr 2차 부싱절연유 채유","2022-09-05 09:00","2022-09-05 18:00","2022-09-05 09:00","2022-09-05 18:00","연속"]
[156,"대전세종충남","천안","아산S/S #4 M.Tr","아산S/S 345kV #4 M.Tr 1,2차 부싱절연유 채유","아산S/S 345kV #4 M.Tr 1,2차 부싱절연유 채유","2022-09-07 09:00","2022-09-07 18:00","2022-09-07 09:00","2022-09-07 18:00","연속"]
[157,"대전세종충남","천안","신서산아산#2 T/L","345kV 아산S/S 취약설비 보강 및 배전반 정비공사","- 모자익배전반 철거 * 1식 - 집중감시제어반+디지탈축소형모자익배전반 설치 *1식","2022-09-19 09:00","2022-10-14 18:00","취소","취소","연속"]
[158,"대전세종충남","천안","아산S/S #2 M.Tr","아산S/S 345kV #2 M.Tr 정밀점검","(배전반 정비공사 취소시)아산S/S 345kV #2 M.Tr 정밀점검","2022-09-19 09:00","2022-10-07 18:00","2022-09-19 09:00","2022-10-07 18:00","연속"]
[159,"대전세종충남","청양","보령C/C CB 7171","보령C/C 345kV 차단기 부동작 예방 조작시험(7171)","보령C/C 345kV 차단기 부동작 예방 조작시험(7171)","2022-09-19 09:00","2022-09-19 14:00","2022-09-19 09:00","2022-09-19 14:00","연속"]
[160,"대전세종충남","청양","보령C/C CB 7271","보령C/C 345kV 차단기 부동작 예방 조작시험(7271)","보령C/C 345kV 차단기 부동작 예방 조작시험(7271)","2022-09-19 14:00","2022-09-19 18:00","2022-09-19 14:00","2022-09-19 18:00","연속"]
[161,"대전세종충남","청양","청양S/S CB 7272","청양S/S 345kV 차단기 부동작 예방 조작시험(7272)","청양S/S 345kV 차단기 부동작 예방 조작시험(7272)","2022-09-13 15:00","2022-09-13 18:00","2022-09-13 15:00","2022-09-13 18:00","연속"]
[162,"대전세종충남","청양","청양신탕정#1 T/L","청양S/S 73Bay B/F PNL 및 송전선로 보호반 교체공사","청양S/S 73Bay B/F PNL 및 송전선로 보호반 교체공사","2022-09-19 09:00","2022-09-23 18:00","취소","취소","연속"]
[163,"대전세종충남","청양","청양군산#2 T/L","청양S/S 73Bay B/F PNL 교체공사","청양S/S 73Bay B/F PNL 교체공사","2022-09-26 09:00","2022-09-30 18:00","취소","취소","연속"]
[164,"대전세종충남","청양","신옥천청양 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지시설 설치공사","[송전] 345kV 신옥천-청양T/L 철탑 추락방지시설 설치공사","2022-09-14 08:00","2022-09-22 18:00","2022-09-14 08:00","2022-09-22 18:00","매일"]
[165,"대전세종충남","청양","청양S/S CB 7200","청양S/S 345kV 차단기 부동작 예방 조작시험(7200)","청양S/S 345kV 차단기 부동작 예방 조작시험(7200)","2022-09-13 11:00","2022-09-13 15:00","2022-09-13 11:00","2022-09-13 15:00","연속"]
[166,"대전세종충남","청양","청양S/S CB 7271","청양S/S 345kV 차단기 부동작 예방 조작시험(7271)","청양S/S 345kV 차단기 부동작 예방 조작시험(7271)","2022-09-13 09:00","2022-09-13 11:00","2022-09-13 09:00","2022-09-13 11:00","연속"]
[167,"전북","김제","신김제한빛NP#2 T/L","345kV 신김제-한빛T/L 추락방지시설 설치공사","○ 수직 및 수평#2T/L 추락방지시설 설치 : No.26~221(196기)","2022-09-28 09:00","2022-10-19 18:00","2022-09-28 09:00","2022-10-19 18:00","연속"]
[168,"전북","직할","신남원S/S #2 BUS","22~23년도 전북직할 변전협력회사 총액공사","신남원S/S 345kV #75BUS 보호반 대체","2022-09-26 09:00","2022-09-30 18:00","2022-09-26 09:00","2022-09-30 18:00","연속"]
[169,"전북","직할","신남원S/S #1 BUS","22~23년도 전북직할 변전협력회사 총액공사","신남원S/S 345kV #70BUS 보호반 대체","2022-09-19 09:00","2022-09-23 18:00","2022-09-19 09:00","2022-09-23 18:00","연속"]
[170,"전북","군산","군산S/S #1 Sh.R CB"," 군산S/S 345kV #1Sh.R 차단기 조작시험"," 군산S/S 345kV #1Sh.R 차단기 조작시험","2022-09-20 09:00","2022-09-20 18:00","2022-09-20 09:00","2022-09-20 18:00","연속"]
[171,"전북","군산","군산S/S #4 M.Tr"," 군산S/S 345kV #4 M.Tr 차단기 조작시험"," 군산S/S 345kV #4 M.Tr 차단기 조작시험","2022-09-22 09:00","2022-09-22 18:00","2022-09-22 09:00","2022-09-22 18:00","연속"]
[172,"전북","군산","새만금S/S #1 Sh.R CB"," 새만금S/S 345kV #1 Sh.R 차단기 조작시험"," 새만금S/S 345kV #1 Sh.R 차단기 조작시험","2022-09-23 09:00","2022-09-23 18:00","2022-09-23 09:00","2022-09-23 18:00","연속"]
[173,"광주전남","광주","신광주한빛NP#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","신광주S/S 362kV GIS 차단기 조작시험 및 전자변교체(7271,7200),LA점검 -비상시 즉시가압 불가-","2022-09-21 09:00","2022-09-22 18:00","2022-09-21 09:00","2022-09-22 18:00","연속"]
[174,"광주전남","광주","신광주S/S #1 M.Tr","22~23년 광주전력지사 변전협력회사 총액공사","#1M.Tr 2차 GIS 보통점검 및 3차 PT 점검","2022-09-01 09:00","2022-09-02 18:00","2022-09-01 09:00","2022-09-02 18:00","연속"]
[175,"광주전남","광주","신광주S/S #2 M.Tr","22-23 광주전력 변전협력회사 총액공사","#2M.Tr 보호반 교체","2022-09-15 09:00","2022-09-23 18:00","2022-09-15 09:00","2022-09-23 18:00","연속"]
[176,"광주전남","광주","신화순S/S #2 M.Tr","22-23 광주전력 변전협력회사 총액공사","#2M.Tr 보호반 교체","2022-09-27 09:00","2022-10-05 18:00","2022-09-27 09:00","2022-10-05 18:00","연속"]
[177,"광주전남","광주","신화순S/S CB 7800","22~23년 광주전력지사 변전협력회사 총액공사","신화순S/S 362kV GIS 차단기 조작시험(7800) -비상시 즉시가압 불가-","2022-09-26 09:00","2022-09-26 18:00","2022-09-26 09:00","2022-09-26 18:00","연속"]
[178,"광주전남","목포","신광주한빛NP#1 T/L","[변전] 유사고장 재발방지대책 시행","- 송운(변전)-1085 관련 송전선로 재폐로 GIS 결상회로 개선","2022-09-14 09:00","2022-09-14 18:00","2022-09-14 09:00","2022-09-14 18:00","연속"]
[179,"광주전남","순천","광양C/C CB 7271","'22-23년 순천전력지사 변전협력회사 총액공사","광양C/C 345kV 광양-광양CC#1T/L 7271 CB 타임측정","2022-09-30 13:00","2022-09-30 15:30","2022-09-30 13:00","2022-09-30 15:30","연속"]
[180,"광주전남","순천","광양C/C CB 7171","'22-23년 순천전력지사 변전협력회사 총액공사","광양C/C 345kV 광양-광양CC#1T/L 7171 CB 타임측정","2022-09-30 15:30","2022-09-30 18:00","2022-09-30 15:30","2022-09-30 18:00","연속"]
[181,"광주전남","순천","광양C/C CB 7371","'22-23년 순천전력지사 변전협력회사 총액공사","광양C/C 345kV #1M.Tr 1차 7371 CB 타임측정","2022-09-30 09:00","2022-09-30 13:00","2022-09-30 09:00","2022-09-30 13:00","연속"]
[182,"광주전남","순천","광양S/S #2 M.Tr","2022-23년 순천전력지사 변전협력회사 총액공사","광양S/S #2M.Tr 1차 GIS 상부 가스 누기 조치 및 1, 3차 LA 보통점검, 1,2차 부싱 절연유채유","2022-09-29 09:00","2022-09-29 18:00","2022-09-20 09:00","2022-09-20 18:00","연속"]
[183,"광주전남","순천","광양S/S #1 M.Tr","2022-23년 순천전력지사 변전협력회사 총액공사","광양S/S #1M.Tr 1차 GIS 상부 가스 누기 조치 및 1, 3차 LA 보통점검, 1,2차 부싱 절연유채유","2022-09-28 09:00","2022-09-28 18:00","2022-09-19 09:00","2022-09-19 18:00","연속"]
[184,"광주전남","순천","신남원광양#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 345Kv 신남원-광양#2T/L CVT(A상) 초기점검","2022-09-16 09:00","2022-09-16 14:00","2022-09-16 09:00","2022-09-16 14:00","연속"]
[185,"광주전남","순천","신남원광양#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 345Kv 신남원-광양#1T/L CVT(A, B상) 하자점검 및 (C상) 대체","2022-09-14 09:00","2022-09-15 18:00","2022-09-14 09:00","2022-09-15 18:00","연속"]
[186,"광주전남","순천","광양S/S SEC CB 70710","22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 345Kv #70-71BUS SEC GIS 초기점검","2022-09-13 09:00","2022-09-13 18:00","2022-09-13 09:00","2022-09-13 18:00","연속"]
[187,"광주전남","순천","신강진광양#1 T/L","2022년 가공송전 순시점검 위탁공사","광양-하동TP #2T/L 73호 과열개소 정비 관련 4회선 구간 안전이격거리 확보","2022-09-06 09:00","2022-09-06 18:00","취소","취소","연속"]
[188,"광주전남","순천","광양하동TP#2 T/L","2022년 가공송전 순시점검 위탁공사","광양-하동TP #2T/L 73호 과열개소 정비","2022-09-06 09:00","2022-09-06 18:00","취소","취소","연속"]
[189,"광주전남","순천","여수T/P #4 Tie-Tr","종합예방진단시스템 5차분 설치공사","부싱 누설전류 센서 수치 측정","2022-09-27 10:00","2022-09-27 15:00","취소","취소","연속"]
[190,"광주전남","순천","여수T/P #2 Tie-Tr","종합예방진단시스템 5차분 설치공사","부싱 누설전류 센서 수치 측정","2022-09-26 10:00","2022-09-26 15:00","취소","취소","연속"]
[191,"광주전남","순천","여수T/P #1 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y 345Kv #1M.Tr 보통점검(OFU), 3차 GPT 하자점검, 1, 2차 LA 대체 및 부싱절연유 채유","2022-09-13 09:00","2022-09-16 18:00","2022-09-13 09:00","2022-09-16 18:00","연속"]
[192,"광주전남","순천","여수T/P CB 7172","362 GIS 정밀점검","GIS 정밀점검","2022-09-21 14:00","2022-09-23 18:00","2022-09-21 14:00","2022-09-23 18:00","연속"]
[193,"광주전남","순천","여수T/P CB 7100","362 GIS 정밀점검","정밀점검","2022-09-19 09:00","2022-09-21 14:00","2022-09-19 09:00","2022-09-21 14:00","연속"]
[194,"광주전남","순천","여수T/P #3 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y 여수화력S/Y #3M.Tr, 2차 GIS 보통점검 및 1차 CB 타임측정, 7300 CB 타임측정","2022-09-22 09:00","2022-09-23 18:00","2022-09-22 09:00","2022-09-23 18:00","연속"]
[195,"대구","달성","북경남고령#2 T/L","고령S/S 북경남-고령#2T/L GIS, PT, LA 보통점검","고령S/S 북경남-고령#2T/L GIS, PT, LA 보통점검","2022-09-26 09:00","2022-09-27 18:00","2022-09-26 09:00","2022-09-27 18:00","연속"]
[196,"대구","달성","고령S/S #3 M.Tr","고령S/S #3M.Tr 휴전작업","-부싱절연유 채유 -#1S.Tr CB 대체 -1차 차단기 동작특성시험","2022-09-28 09:00","2022-09-30 18:00","2022-09-28 09:00","2022-09-30 18:00","연속"]
[197,"대구","달성","북경남고령#1 T/L","고령S/S 북경남-고령#1T/L GIS 차단기동작특성시험","고령S/S 북경남-고령#1T/L GIS 차단기동작특성시험","2022-09-16 09:00","2022-09-16 18:00","2022-09-16 09:00","2022-09-16 18:00","연속"]
[198,"대구","달성","북경남대구#1 T/L","345kV 북경남-대구T/L 안전이격거리 확보공사","345kV 북경남-대구T/L 안전이격거리 확보공사 전선교체","2022-09-28 07:00","2022-10-03 18:00","2022-09-28 07:00","2022-10-03 18:00","연속"]
[199,"대구","칠곡","북대구S/S #2 M.Tr","북대구S/S #2M.Tr 보통점검","북대구S/S #2M.Tr 보통점검","2022-09-20 09:30","2022-09-20 18:00","2022-09-20 09:30","2022-09-20 18:00","연속"]
[200,"대구","칠곡","북대구S/S #3 M.Tr","북대구S/S #3M.Tr 보통점검","북대구S/S #3M.Tr 보통점검","2022-09-16 09:30","2022-09-16 18:00","2022-09-16 09:30","2022-09-16 18:00","연속"]
[201,"대구","칠곡","북대구S/S #1 M.Tr","북대구S/S #1M.Tr 초기점검","북대구S/S #1M.Tr 초기점검","2022-09-19 09:30","2022-09-19 18:00","2022-09-19 09:30","2022-09-19 18:00","연속"]
[202,"대구","칠곡","서대구S/S #3 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구-남인동#2T/L, #3M.Tr 부하전환(철구 → GIS)","2022-09-26 08:30","2022-09-28 18:00","2022-09-26 08:30","2022-09-28 18:00","연속"]
[203,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구-남인동#1T/L, #4M.Tr 부하전환(철구 → GIS)","2022-09-13 08:30","2022-09-16 18:00","2022-09-13 08:30","2022-09-16 18:00","연속"]
[204,"대구","포항","신포항S/S #3 M.Tr","신포항S/S #3M.Tr 부싱절연유 추적관리개소 채유","신포항S/S #3M.Tr 부싱절연유 추적관리개소 채유","2022-09-27 09:00","2022-09-27 18:00","2022-09-27 09:00","2022-09-27 18:00","연속"]
[205,"대구","포항","신포항북대구 T/L","2022~23년도 대구직할 가공송전 협력회사 총액공사","345kV신포항-북대구T/L No.49~148 추락방지장치 설치","2022-09-20 07:30","2022-10-06 18:00","2022-09-20 07:30","2022-10-06 18:00","연속"]
[206,"대구","포항","월성N/P CB 7500","월성S/Y 7500,7572 GIS 보통점검","월성S/Y 7500,7572 GIS 보통점검","2022-09-14 09:00","2022-09-14 18:00","2022-09-14 09:00","2022-09-14 18:00","연속"]
[207,"대구","포항","월성N/P CB 7672","월성S/Y 7672 GIS 보통점검","월성S/Y 7672 GIS 보통점검","2022-09-26 09:00","2022-09-26 18:00","2022-09-26 09:00","2022-09-26 18:00","연속"]
[208,"대구","포항","월성N/P CB 7572","월성S/Y 7500,7572 GIS 보통점검","월성S/Y 7500,7572 GIS 보통점검","2022-09-14 09:00","2022-09-14 18:00","2022-09-14 09:00","2022-09-14 18:00","연속"]
[209,"대구","포항","울주월성NP#1 T/L","염해방지 애자코팅 공사","염해방지 애자코팅 공사","2022-09-14 09:00","2022-09-14 18:00","2022-09-14 09:00","2022-09-14 18:00","연속"]
[210,"경북","구미","선산S/S #1 BUS","선산S/S 345kV 장기사용 GIS 용량교체공사","#1BUS 철거 등","2022-09-26 09:00","2022-10-01 18:00","2022-09-26 09:00","2022-10-01 18:00","연속"]
[211,"경북","구미","선산S/S #1 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","기초설치관련 안전이격 확보","2022-09-19 09:00","2022-09-20 18:00","2022-09-19 09:00","2022-09-20 18:00","연속"]
[212,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","기초설치관련 안전이격 확보","2022-09-21 09:00","2022-09-22 18:00","2022-09-21 09:00","2022-09-22 18:00","연속"]
[213,"경북","구미","선산S/S #3 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","기초설치관련 안전이격 확보","2022-09-21 09:00","2022-09-22 18:00","2022-09-21 09:00","2022-09-22 18:00","연속"]
[214,"경북","구미","선산신포항 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","#1BUS 철거 관련 안전이격 확보","2022-09-30 09:00","2022-09-30 18:00","2022-09-30 09:00","2022-09-30 18:00","연속"]
[215,"경북","구미","서대구선산#1 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","기초설치관련 안전이격 확보","2022-09-19 09:00","2022-09-20 18:00","2022-09-19 09:00","2022-09-20 18:00","연속"]
[216,"경북","구미","선산S/S #2 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","기초설치관련 안전이격 확보","2022-09-23 09:00","2022-09-23 18:00","2022-09-23 09:00","2022-09-23 18:00","연속"]
[217,"경북","구미","서대구선산#2 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","기초설치관련 안전이격 확보","2022-09-23 09:00","2022-09-24 18:00","2022-09-23 09:00","2022-09-24 18:00","연속"]
[218,"경북","영주","신제천신영주#1 T/L","2022년 가공송전 순시점검 위탁공사-정밀점검","2022년 가공송전 순시점검 위탁공사-정밀점검 시행","2022-09-19 09:00","2022-09-21 18:00","취소","취소","연속"]
[219,"경북","영주","신영주S/S #1 TCSC CB","신영주S/S 345kV TCSC 점검공사","- 신영주S/S 345kV #1TCSC 점검공사","2022-09-26 09:00","2022-09-29 18:00","2022-09-27 09:00","2022-09-30 18:00","연속"]
[220,"경북","영주","신제천신영주#2 T/L","2022년 가공송전 순시점검 위탁공사-정밀점검","2022년 가공송전 순시점검 위탁공사-정밀점검 시행","2022-09-26 09:00","2022-09-28 18:00","취소","취소","연속"]
[221,"경북","영주","신영주S/S #2 TCSC CB","신영주S/S 345kV TCSC 점검공사","- 신영주S/S 345kV #2TCSC 점검공사","2022-09-30 09:00","2022-10-02 18:00","2022-10-01 09:00","2022-10-03 18:00","연속"]
[222,"부산울산","동부산","신양산고리NP#1 T/L","345kV 신양산-고리NPT/L 불량압축인류크램프 정비공사","압축인류크램프 정비","2022-09-14 07:00","2022-09-19 18:00","2022-09-14 07:00","2022-09-19 18:00","연속"]
[223,"부산울산","동부산","신양산신대연#1 T/L","신양산S/S 345kV 용량부족 차단기 교체공사 1차","신양산 345kV 용량부족 차단기 교체공사 1차 - 72BAY GIS 교체(7271,7200)","2022-09-19 09:00","2022-12-17 18:00","2022-09-19 09:00","2022-12-17 18:00","연속"]
[224,"부산울산","동부산","신양산북부산#2 T/L","신양산S/S 345kV 용량부족 차단기 교체공사 1차","신양산 345kV 용량부족 차단기 교체공사 1차 - 72BAY GIS 교체(7271,7200) - 345kV 신양산-북부산 #2T/L 외장형 LA 이설","2022-09-13 09:00","2022-09-13 18:00","2022-09-13 09:00","2022-09-13 18:00","연속"]
[225,"부산울산","동부산","신양산고리NP#2 T/L","345kV 신양산-고리NPT/L 불량압축인류크램프 정비공사","압축인류크램프 정비","2022-09-20 07:00","2022-09-25 18:00","2022-09-20 07:00","2022-09-25 18:00","연속"]
[226,"부산울산","동부산","신양산S/S #4 M.Tr","신양산S/S 345kV M.Tr 3차측 현대화 공사","345kV #4M.Tr 3차측 현대화공사","2022-09-15 09:00","2022-10-02 18:00","2022-09-15 09:00","2022-10-02 18:00","연속"]
[227,"부산울산","동부산","신양산북부산#1 T/L","신양산S/S 345kV 용량부족 차단기 교체공사 1차","신양산 345kV 용량부족 차단기 교체공사 1차 - 72BAY GIS 교체(7271,7200) - 345kV 신양산-북부산 #1T/L 외장형 LA 이설","2022-09-14 09:00","2022-09-14 18:00","2022-09-14 09:00","2022-09-14 18:00","연속"]
[228,"부산울산","북부산","신김해북부산#1 T/L","345kV 신김해-북부산#1T/L 송전선로 정밀점검","송전선로 정밀점검(1~57호) 철탑 추락방지장치 설치","2022-09-15 08:00","2022-09-23 18:00","2022-09-15 08:00","2022-09-23 18:00","연속"]
[229,"부산울산","서부산","서부산S/S #1 Sh.R CB","서부산S/S 345kV #1Sh.R 보통점검","서부산S/S 345kV #1Sh.R 보통점검 병행 : 345kV #1Sh.R 7177 GIS 초기점검","2022-09-13 09:00","2022-09-15 18:00","2022-09-13 09:00","2022-09-15 18:00","연속"]
[230,"부산울산","울산","남울산S/S #2 M.Tr","22~23년 변전협력회사 총액공사","- M.Tr 하자점검 - 2차 GIS(6571, 6500) 하자점검 - 2차 피뢰기 하자점검 - 예비D/L EGIS(4584)하자점검","2022-09-05 09:00","2022-09-06 18:00","2022-09-05 09:00","2022-09-06 18:00","연속"]
[231,"부산울산","울산","신온산S/S #4 M.Tr","신온산S/S 154kV APK T/L 인출변경공사","6G7 GIS 증설","2022-09-13 09:00","2022-09-20 18:00","취소","취소","연속"]
[232,"부산울산","울산","신온산S/S #3 M.Tr","345kV 신온산S/S 용량부족 차단기 대체공사","74Bay #2BUS, 7471, 7400, 7472GIS 대체(안전이격거리 확보)","2022-09-26 09:00","2022-10-28 15:00","2022-09-26 09:00","2022-10-28 15:00","매일"]
[233,"부산울산","울산","신온산남울산#1 T/L","345kV 신온산S/S 용량부족 차단기 대체공사","74Bay #2BUS, 7471, 7400, 7472GIS 대체","2022-09-26 09:00","2022-12-02 15:00","2022-09-26 09:00","2022-12-02 15:00","연속"]
[234,"부산울산","울산","신온산S/S #2 M.Tr","345kV 신온산S/S 용량부족 차단기 대체공사","74Bay #2BUS, 7471, 7400, 7472GIS 대체","2022-09-26 09:00","2022-12-02 15:00","2022-09-26 09:00","2022-12-02 15:00","연속"]
[235,"부산울산","울산","신온산S/S #2 BUS","345kV 신온산S/S 용량부족 차단기 대체공사","74Bay #2BUS, 7471, 7400, 7472GIS 대체","2022-09-26 09:00","2022-10-21 15:00","2022-09-26 09:00","2022-10-21 15:00","연속"]
[236,"부산울산","울산","신울산S/S #4 M.Tr","신울산S/S 154kV 현대화공사","#4M.Tr 2차측 예비모선 철거","2022-09-05 08:30","2022-09-05 18:00","2022-09-05 08:30","2022-09-05 18:00","연속"]
[237,"부산울산","울산","신울산고리NP#2 T/L","신울산S/S 345kV 차단기 용량대체공사","- 345kV GIS 대체 관련 송전선로 접속지점 변경(구 73BAY → 신 73BAY) - 345kV GIS 대체 관련 보호배전반 이설 및 연동시험","2022-09-05 09:00","2022-09-23 18:00","2022-09-01 09:00","2022-09-23 18:00","연속"]
[238,"부산울산","울산","신울산S/S #1 M.Tr","신울산S/S 154kV 현대화공사","#1M.Tr 2차측 인출변경 - 관로공사 및 전력케이블 포결선 - 3차측 현대화공사(울산전력지사)","2022-09-14 08:30","2022-11-11 18:00","2022-09-14 08:30","2022-11-11 18:00","연속"]
[239,"부산울산","울산","신울산S/S CB 7300G","신울산S/S 345kV 차단기 용량대체공사","신 GIS 73BAY 무부하가압","2022-09-19 09:00","2022-09-20 18:00","2022-09-19 09:00","2022-09-20 18:00","연속"]
[240,"부산울산","울산","신울산S/S CB 7371G","신울산S/S 345kV 차단기 용량대체공사","신 GIS 73BAY 무부하가압","2022-09-19 09:00","2022-09-20 18:00","2022-09-19 09:00","2022-09-20 18:00","연속"]
[241,"부산울산","울산","신울산S/S #70G BUS","신울산S/S 345kV 차단기 용량대체공사","신 GIS 73BAY 무부하가압","2022-09-19 09:00","2022-09-20 18:00","2022-09-19 09:00","2022-09-20 18:00","연속"]
[242,"부산울산","울산","울산C/C #2 BUS","울산복합 보호제어설비 전담운영 공사","울산복합 보호제어설비 전담운영 공사","2022-09-22 09:00","2022-09-22 20:00","취소","취소","연속"]
[243,"부산울산","울산","울산C/C #2 BUS","울산복합 보호제어설비 전담운영 공사","울산복합 보호제어설비 전담운영 공사","2022-09-15 09:00","2022-09-15 20:00","취소","취소","연속"]
[244,"부산울산","울산","울산C/C #1 BUS","울산복합 보호제어설비 전담운영 공사","울산복합 보호제어설비 전담운영 공사","2022-09-06 09:00","2022-09-06 20:00","취소","취소","연속"]
[245,"부산울산","직할","신대연S/S #1 Sh.R CB","2022년 직할 345kV M.Tr 정밀점검공사","신대연S/S 345kV #1Sh.R 정밀점검","2022-09-13 09:00","2022-09-16 18:00","2022-09-13 09:00","2022-09-16 18:00","연속"]
[246,"경남","직할","신김해창원#2 T/L","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-09-28 14:00","2022-09-30 18:00","2022-09-28 14:00","2022-09-30 18:00","연속"]
[247,"경남","직할","신마산신김해#1 T/L","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-09-26 08:00","2022-09-28 14:00","2022-09-26 08:00","2022-09-28 14:00","연속"]
[248,"경남","직할","신김해창원#1 T/L","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-09-21 14:00","2022-09-23 18:00","2022-09-21 14:00","2022-09-23 18:00","연속"]
[249,"경남","직할","신마산신김해#2 T/L","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-09-19 08:00","2022-09-21 14:00","2022-09-19 08:00","2022-09-21 14:00","연속"]
[250,"경남","직할","신김해신녹산#2 T/L","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-09-14 08:00","2022-09-16 17:30","2022-09-14 08:00","2022-09-16 17:30","연속"]
[251,"경남","진주","의령S/S #3 M.Tr","의령S/S #3M.Tr 2차(6344) GIS 정밀점검","의령S/S #3M.Tr 2차(6344) GIS 정밀점검","2022-09-15 09:00","2022-09-16 18:00","2022-09-15 09:00","2022-09-16 18:00","연속"]
[252,"경남","진주","하동T/P SEC CB 75760","하동T/P #70-71, #75-76 BUS SEC 조작시험","하동T/P #70-71, #75-76 BUS SEC 조작시험","2022-09-02 14:00","2022-09-02 17:00","2022-09-02 14:00","2022-09-02 17:00","연속"]
[253,"경남","진주","하동T/P SEC CB 70710","하동T/P #70-71, #75-76 BUS SEC 조작시험","하동T/P #70-71, #75-76 BUS SEC 조작시험","2022-09-02 10:00","2022-09-02 14:00","2022-09-02 10:00","2022-09-02 14:00","연속"]
[254,"경남","통영","신고성S/S #1 M.Tr","신고성S/S #1M.Tr 1,2차 부싱절연유 채유 및 도블","신고성S/S #1M.Tr 1,2차 부싱절연유 채유 및 도블","2022-09-26 10:00","2022-09-26 18:00","2022-09-26 10:00","2022-09-26 18:00","연속"]
[255,"경남","통영","신고성S/S #4 M.Tr","신고성S/S #4M.Tr C상 H1 부싱절연유 채유","- 신고성S/S #4M.Tr C상 H1 부싱절연유 채유","2022-09-15 10:00","2022-09-15 18:00","2022-09-15 10:00","2022-09-15 18:00","연속"]
[256,"경남","통영","신고성S/S 예비 M.Tr CB","신고성S/S 예비 M.Tr X1 부싱절연유 채유","- 신고성S/S 예비 M.Tr X1 부싱절연유 채유","2022-09-15 10:00","2022-09-15 18:00","취소","취소","연속"]
[257,"경남","함안","북경남S/S CB 7572","북경남S/S 345kV 북경남-대구#2T/L 7572 단독 차단기 점검","북경남S/S 345kV 북경남-대구#2T/L 7572 단독 GIS 보통점검","2022-09-15 09:30","2022-09-15 17:30","2022-09-15 09:30","2022-09-15 17:30","연속"]
[258,"대구",null,"월성N/P #1 기동용변압기 (CB 7671, 7600)","월성 1호기 소내절체시험 관련 SST 휴전 및 가압 * 조작차단기 : CB7671,7600","○ 소내절체시험","2022-09-05 09:00","2022-09-09 18:00","2022-09-05 09:00","2022-09-09 18:00","연속"]
[259,"대구",null,"월성N/P #1 주변압기 (CB 7272, 7200)","월성 1호기 소내절체시험 관련 MOT 휴전 및 가압 * 조작차단기 : CB7272,7200","○ 소내절체시험","2022-09-05 09:00","2022-09-09 18:00","2022-09-05 09:00","2022-09-09 18:00","연속"]
[260,"대구",null,"월성N/P #3 기동용변압기 (CB 7600, 7672)","월성3호기 19차 O/H 중 기동변압기 점검 및 소내모선 정전 작업 * 조작차단기 : CB 7600, 7672","○ 기동용변압기 점검 ○ 소내모선 정전작업","2022-09-22 18:00","2022-10-01 18:00","2022-09-22 18:00","2022-10-01 18:00","연속"]
[261,"광주전남",null,"한빛N/P #1 X02 기동변압기 (CB 7F00, 7F72)","한빛1호기 26차 계획예방정비 * 조작차단기 : CB 7F00, 7F72","○ 한빛2호기 계획예방정비 수행 ○ 차단기 교체 공사를 위한 휴전","2022-09-08 00:01","2022-09-13 06:00","2022-09-08 00:01","2022-09-13 06:00","연속"]
[262,"광주전남",null,"한빛N/P #1 X01 기동변압기 (CB 7200, 7271)","한빛1호기 16차 계획예방정비 * 조작차단기 : CB 7200, 7271","○ 한빛2호기 계획예방정비 수행 ○ GIB 개선 공사","2022-09-13 06:00","2022-10-22 18:00","2022-09-13 06:00","2022-10-22 18:00","연속"]
[263,"광주전남",null,"한빛N/P #6 주변압기 (CB 7E71, 7E00)","한빛6호기 14차 O/H 중 주변압기 점검 * 조작차단기: 7E00, 7E71 CB","○ 주변압기 점검 ○ 갑종보호계전기 점검","2022-09-28 10:00","2022-10-19 14:00","2022-09-28 10:00","2022-10-19 14:00","연속"]
[264,"강원",null,"양양P/P #4호기 주변압기 (CB 7300,7372)","보조기기 절연저항 측정 등","보조기기 절연저항 측정 등","2022-09-16 09:00","2022-09-16 18:00","2022-09-16 09:00","2022-09-16 18:00","연속"]
[265,"경남",null,"산청P/P #1호기 주변압기 (CB 7100,7172)","계획중간정비","계획중간정비","2022-09-17 09:00","2022-09-17 20:00","2022-09-17 09:00","2022-09-17 20:00","연속"]
[266,"강원",null,"양양P/P #1호기 주변압기 (CB 7100,7172)","UCB Operating Rod 측정 등","UCB Operating Rod 측정 등","2022-09-19 09:00","2022-09-19 18:00","2022-09-19 09:00","2022-09-19 18:00","연속"]
[267,"강원",null,"양양P/P #2호기 주변압기 (CB 7271,7200)","UCB Operating Rod 측정 등","UCB Operating Rod 측정 등","2022-09-20 09:00","2022-09-23 18:00","2022-09-20 09:00","2022-09-23 18:00","연속"]
[268,"경남",null,"산청P/P #2호기 주변압기 (CB 7200,7271)","계획중간정비","계획중간정비","2022-09-24 09:00","2022-09-24 20:00","2022-09-24 09:00","2022-09-24 20:00","연속"]

{"sheet":"154설비","index":2,"n_rows":509,"n_cols":11,"rows_kept":509,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4]],"flags":["formulas_cached_only"]}
["2022년도 9월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","금오상계#1 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","추락방지장치 설치 : 3기 , 번호찰 설치 : 14기","2022-09-06 07:30","2022-09-06 13:00","2022-09-06 07:30","2022-09-06 13:00","연속"]
[2,"서울","성동","금오상계#2 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","추락방지장치 설치 : 3기 , 번호찰 설치 : 14기","2022-09-06 13:00","2022-09-06 18:00","2022-09-06 13:00","2022-09-06 18:00","연속"]
[3,"서울","성동","성동휘경#2 T/L","'22년 성동P/O 노후 보호배전반 교체공사","성동, 휘경S/S 154kV 성동-휘경#2T/L 보호배전반 노후대체","2022-09-19 10:00","2022-09-22 18:00","2022-09-19 10:00","2022-09-22 18:00","연속"]
[4,"서울","성동","신내상봉 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검(양단)","2022-09-14 10:00","2022-09-14 18:00","2022-09-14 10:00","2022-09-14 18:00","연속"]
[5,"서울","성동","양주쌍문#1 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","추락방지장치 설치 : 9기, 피뢰기 설치 : 11기, 번호찰 설치 : 12기","2022-09-07 07:30","2022-09-07 18:00","2022-09-07 07:30","2022-09-07 18:00","연속"]
[6,"서울","성동","돈암안암#1 T/L","안암 및 휘경변전소 인출 OF케이블 선종교체공사","1. 공사명 : 안암 및 휘경변전소 인출 OF케이블 선종교체공사 2. 대상선로 : 안암노원#1, 돈암안암#1T/L 3. 공사내용 : 변전소내 화재확산 방지 OF→XLPE 선종교체 4. 공사구간 : 종단접속함(EBG)~J/B#1-2 구간","2022-09-26 09:00","2022-12-07 18:00","2022-09-26 09:00","2022-11-24 18:00","연속"]
[7,"서울","성동","안암노원#1 T/L","안암 및 휘경변전소 인출 OF케이블 선종교체공사","1. 공사명 : 안암 및 휘경변전소 인출 OF케이블 선종교체공사 2. 대상선로 : 안암노원#1, 돈암안암#1T/L 3. 공사내용 : 변전소내 화재확산 방지 OF→XLPE 선종교체 4. 공사구간 : 종단접속함(EBG)~J/B#1-2 구간","2022-09-26 09:00","2022-12-07 18:00","2022-09-26 09:00","2022-12-07 18:00","연속"]
[8,"서울","성동","화양광장 T/L","'21~22년 성동P/O 지중송전 위탁정비공사","기중종단접속함(EBA) 절연유 분석 위한 채취작업","2022-09-20 10:00","2022-09-21 17:00","2022-09-20 10:00","2022-09-21 17:00","연속"]
[9,"서울","성동","미금화양 T/L","'21~22년 성동P/O 지중송전 위탁정비공사","기중종단접속함(EBA) 절연유 분석 위한 채취작업","2022-09-20 10:00","2022-09-21 17:00","2022-09-20 10:00","2022-09-21 17:00","연속"]
[10,"서울","중부","상암등촌#2 T/L","22년 중부P/O 170kV GIS/GCB 정밀점검공사","170kV GIS 정밀점검","2022-09-21 10:00","2022-09-22 18:00","취소","취소","연속"]
[11,"서울","중부","상암등촌#1 T/L","22년 중부P/O 170kV GIS/GCB 정밀점검공사","170kV GIS 정밀점검","2022-09-19 10:00","2022-09-20 18:00","취소","취소","연속"]
[12,"서울","중부","원흥상암 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","추락방지장치 설치 : 4기","2022-09-01 07:30","2022-09-02 18:00","2022-09-01 07:30","2022-09-02 18:00","연속"]
[13,"서울","중부","능곡상암#1 T/L","22년 중부P/O 170kV GIS/GCB 정밀점검공사","170kV GIS 정밀점검","2022-09-13 10:00","2022-09-14 18:00","2022-09-13 10:00","2022-09-14 18:00","연속"]
[14,"서울","중부","능곡상암#2 T/L","22년 중부P/O 170kV GIS/GCB 정밀점검공사","170kV GIS 정밀점검","2022-09-15 10:00","2022-09-16 18:00","2022-09-15 10:00","2022-09-16 18:00","연속"]
[15,"서울","중부","원흥수색#1 T/L","22년 중부P/O 170kV GIS/GCB 정밀점검공사","170kV GIS 정밀점검","2022-09-26 10:00","2022-09-27 18:00","2022-09-26 10:00","2022-09-27 18:00","연속"]
[16,"서울","중부","양주은평#2 T/L","154kV 양주-은평T/L No.14 안전이격확보공사","철탑 1기 철거 및 관형지지물 1기 설치","2022-09-13 07:30","2022-11-02 18:00","2022-09-13 07:30","2022-11-02 18:00","연속"]
[17,"서울","중부","양주은평#1 T/L","154kV 양주-은평T/L No.14 안전이격확보공사","철탑 철거 1기 및 관형지지물 설치 1기","2022-09-01 07:30","2022-09-08 18:00","2022-09-01 07:30","2022-09-08 18:00","연속"]
[18,"서울","직할","중앙서소문 T/L","22년 154kV GIS 정밀점검 공사","-#4M.Tr 1차 시험가압시 계통 사전조작필요","2022-09-07 15:00","2022-09-07 18:00","2022-09-07 15:00","2022-09-07 18:00","연속"]
[19,"서울","직할","종로서소문 T/L","22년 154kV GIS 정밀점검 공사","-#4M.Tr 1차 시험가압시 계통 사전조작필요","2022-09-07 15:00","2022-09-07 18:00","2022-09-07 15:00","2022-09-07 18:00","연속"]
[20,"서울","직할","서소문S/S #1 BUS","22년 직할 변전협력 총액","-154kV PT 보통점검","2022-09-21 10:00","2022-09-21 14:00","2022-09-21 10:00","2022-09-21 14:00","연속"]
[21,"서울","직할","서소문S/S #2 BUS","22년 170kV GIS 정밀점검","-서소문 #4M.Tr 1차 시험가압","2022-09-07 09:30","2022-09-07 18:00","2022-09-07 09:30","2022-09-07 18:00","연속"]
[22,"서울","직할","서소문S/S #2 BUS","22년 직할 변전협력 총액","-154kV PT 보통점검","2022-09-21 14:00","2022-09-21 18:00","2022-09-21 14:00","2022-09-21 18:00","연속"]
[23,"서울","직할","운니원남#1 T/L","22년 직할 변전협력 총액","-154kV GIS 보통점검","2022-09-14 10:00","2022-09-14 18:00","2022-09-14 10:00","2022-09-14 18:00","연속"]
[24,"서울","직할","운니원남#2 T/L","22년 직할 변전협력 총액","-154kV GIS 보통점검","2022-09-15 10:00","2022-09-15 18:00","2022-09-15 10:00","2022-09-15 18:00","연속"]
[25,"서울","직할","원남미아#2 T/L","22년 직할 변전협력 총액","-154kV GIS 보통점검","2022-09-20 10:00","2022-09-20 18:00","2022-09-20 10:00","2022-09-20 18:00","연속"]
[26,"서울","직할","원남미아#1 T/L","22년 직할 변전협력 총액","-154kV GIS 보통점검","2022-09-19 10:00","2022-09-19 18:00","2022-09-19 10:00","2022-09-19 18:00","연속"]
[27,"서울","직할","중앙서소문 T/L","22년 직할 변전협력 총액","154kV PT 보통점검시 계통 사전조작필요","2022-09-21 10:00","2022-09-21 18:00","2022-09-21 10:00","2022-09-21 18:00","연속"]
[28,"서울","직할","종로서소문 T/L","22년 직할 변전협력 총액","154kV PT 보통점검시 계통 사전조작필요","2022-09-21 10:00","2022-09-21 18:00","2022-09-21 10:00","2022-09-21 18:00","연속"]
[29,"남서울","강남","신양재과천#2 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 신양재-과천2","2022-09-05 08:00","2022-09-06 18:00","2022-09-05 08:00","2022-09-06 18:00","연속"]
[30,"남서울","강남","과천동안양#2 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 과천-동안양#2","2022-09-02 16:00","2022-09-02 18:00","2022-09-02 16:00","2022-09-02 18:00","연속"]
[31,"남서울","강남","과천동안양#1 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 과천-동안양#1","2022-09-02 16:00","2022-09-02 18:00","2022-09-02 16:00","2022-09-02 18:00","연속"]
[32,"남서울","강남","반포S/S CB 6100","22-23년도 강남전력지사 변전협력회사 총액공사","-GIS 조작시험","2022-09-15 09:00","2022-09-15 13:00","2022-09-15 09:00","2022-09-15 13:00","연속"]
[33,"남서울","강남","동빙고반포#2 T/L","'22-'23년 가공송전 협력회사 총액공사","추락방지시설 설치공사","2022-09-30 12:00","2022-09-30 18:00","2022-09-30 12:00","2022-09-30 18:00","연속"]
[34,"남서울","강남","동빙고반포#1 T/L","'22-'23년 가공송전 협력회사 총액공사","추락방지시설 설치공사","2022-09-30 08:00","2022-09-30 12:00","2022-09-30 08:00","2022-09-30 12:00","연속"]
[35,"남서울","강남","사당신림 T/L","22-23년도 강남전력지사 변전협력회사 총액공사","-GIS 조작시험","2022-09-19 09:00","2022-09-19 14:00","2022-09-19 09:00","2022-09-19 14:00","연속"]
[36,"남서울","동서울","가락S/S #2 BUS","154kV 동서울-송파,가락T/L 지중화공사","154kV 동서울-가락T/L 무부하 가압용 BUS 휴전","2022-09-14 09:50","2022-09-14 10:00","2022-09-14 09:50","2022-09-14 10:00","연속"]
[37,"남서울","동서울","강동풍납#2 T/L","강동SS 강동-풍납2TL GIS 베어링발청조치(유사고장)","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-09-24 14:00","2022-09-24 18:00","2022-09-24 14:00","2022-09-24 18:00","연속"]
[38,"남서울","동서울","강동천호#2 T/L","강동SS 강동-천호2TL GIS 전자변교체,조작시험","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-09-03 14:00","2022-09-03 18:00","취소","취소","연속"]
[39,"남서울","동서울","강동풍납#1 T/L","강동SS 강동-풍납1TL GIS 베어링발청조치(유사고장)","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-09-24 09:00","2022-09-24 14:00","2022-09-24 09:00","2022-09-24 14:00","연속"]
[40,"남서울","동서울","강동천호#1 T/L","강동SS 강동-천호1TL GIS 전자변교체,조작시험","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-09-03 09:00","2022-09-03 14:00","취소","취소","연속"]
[41,"남서울","동서울","도곡개포 T/L","154kV 개포-신양재,도곡T/L 지장이설공사","양재대로 구조개선 사업(지하차도 건설)에 따른 전력설비 이설 □ 사업구간 : 154kV 도곡-개포T/L J/B#1 ~ M/H#2 □ 주요공정 - 케이블 철거 : XLPE 2,000㎟, 1C-0.32km(기설전력구+관로) - 케이블 설치 : XLPE 2,000㎟, 1C-0.35km(신설전력구+관로) - 케이블 접속 : 2개소","2022-09-15 09:00","2022-10-13 18:00","2022-09-26 09:00","2022-10-22 18:00","연속"]
[42,"남서울","동서울","염곡개포#1 T/L","154kV 염곡-개포T/L 누유개소 정비공사","154kV 염곡-개포#1T/L 누유개소 정비","2022-09-26 18:00","2022-10-08 18:00","2022-09-26 18:00","2022-10-08 18:00","연속"]
[43,"남서울","동서울","동서울#2S/S #64 BUS","154kV 동서울-가락#2T/L 무부하가압","인터록, 상 확인","2022-09-14 09:50","2022-09-14 10:00","취소","취소","연속"]
[44,"남서울","동서울","동서울#2S/S #69 BUS","154kV 동서울-가락#2T/L 무부하가압","인터록, 상 확인","2022-09-14 10:00","2022-09-15 10:00","2022-09-14 10:00","2022-09-15 10:00","연속"]
[45,"남서울","동서울","동서울#2S/S #68 BUS","세종-포천 고속도로 건설 지장송전선로 지중화공사","154kV 팔수T/L 지중화공사 무부하 가압","2022-09-17 10:00","2022-09-18 10:00","취소","취소","연속"]
[46,"남서울","동서울","동서울위례#2 T/L","345kV 동서울#2S/S 건설공사","동서울2-위례#2T/L 실부하 가압 조작","2022-09-15 09:00","2022-09-15 18:00","취소","취소","연속"]
[47,"남서울","동서울","동서울위례#1 T/L","345kV 동서울#2S/S 건설공사","동서울2-위례#1T/L 실부하 가압 조작","2022-09-16 09:00","2022-09-16 18:00","취소","취소","연속"]
[48,"남서울","동서울","동서울#2S/S #63 BUS","세종-포천 고속도로 건설 지장송전선로 지중화공사","154kV 팔수T/L 지중화공사 무부하 가압 관련 건전성 확인","2022-09-17 09:50","2022-09-17 10:00","취소","취소","연속"]
[49,"남서울","동서울","동서울#2S/S #63 BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-신장T/L 지중화공사 무부하 가압","2022-09-22 09:50","2022-09-22 10:00","취소","취소","연속"]
[50,"남서울","동서울","동서울#2S/S #68 BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-신장T/L 지중화공사 관련 BUS 무부하가압 관련 휴전","2022-09-22 10:00","2022-09-23 10:00","취소","취소","연속"]
[51,"남서울","동서울","동서울#2S/S #63 BUS","154kV 동서울-송파#2T/L 무부하가압","154kV 동서울-송파#2T/L 무부하가압 부스","2022-09-28 10:00","2022-09-29 10:00","취소","취소","연속"]
[52,"남서울","동서울","동서울#2S/S #68 BUS","154kV 동서울-송파#2T/L 무부하가압","154kV 동서울-송파#2T/L 무부하가압 부스","2022-09-28 10:00","2022-09-29 10:00","2022-09-28 10:00","2022-09-29 10:00","연속"]
[53,"남서울","동서울","동서울#2S/S #68 BUS","동서울S/S 154kV 옥외철구 GIS화 공사","○ 옥외철구 -> GIS 운전전환 ○ 기타 부대작업 1식","2022-09-14 10:00","2022-09-15 10:00","2022-09-14 10:00","2022-09-15 10:00","연속"]
[54,"남서울","동서울","동서울#2S/S #63 BUS","동서울S/S 154kV 옥외철구 GIS화 공사","○ 옥외철구 -> GIS 운전전환 ○ 기타 부대작업 1식","2022-09-14 09:50","2022-09-14 10:00","취소","취소","연속"]
[55,"남서울","동서울","동서울S/S #61 BUS(신)","세종-포천 고속도로 건설 지장송전선로 지중화공사","154kV 팔수T/L 지중화공사 무부하 가압","2022-09-17 09:50","2022-09-17 10:00","취소","취소","연속"]
[56,"남서울","동서울","동서울S/S #67 BUS(신)","세종-포천 고속도로 건설 지장송전선로 지중화공사","154kV 팔수T/L 지중화공사 관련 BUS 무부하가압 관련 휴전","2022-09-17 10:00","2022-09-18 10:00","취소","취소","연속"]
[57,"남서울","동서울","동서울신장#1 T/L","154kV 동서울-강동 등 3개T/L 지중화공사","세종-포천 고속도로 건설 지장송전선로 지중화(이설) 요청에 따른 송전선로 일부구간 지중화공사","2022-09-24 09:00","2022-10-01 18:00","취소","취소","연속"]
[58,"남서울","동서울","동서울신장#2 T/L","154kV 동서울-강동 등 3개T/L 지중화공사","세종-포천 고속도로 건설 지장송전선로 지중화(이설) 요청에 따른 송전선로 일부구간 지중화공사","2022-09-19 09:00","2022-09-23 18:00","취소","취소","연속"]
[59,"남서울","동서울","동서울S/S 팔당취수장 T/L CB","세종-포천 고속도로 건설 지장송전선로 지중화공사","154kV 팔수T/L No.1~2 지중화공사(한국수자원공사 시행)","2022-09-14 09:00","2022-09-18 18:00","취소","취소","연속"]
[60,"남서울","동서울","동서울S/S #66 BUS(신)","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-신장T/L 무부하 가압용 BUS 휴전","2022-09-30 10:00","2022-10-01 10:00","2022-09-28 10:00","2022-09-29 10:00","연속"]
[61,"남서울","동서울","동서울S/S #65 BUS(신)","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-신장T/L 무부하 가압용 BUS 휴전","2022-09-30 10:00","2022-10-01 10:00","취소","취소","연속"]
[62,"남서울","동서울","동서울S/S #67 BUS(신)","154kV 동서울-송파,가락T/L 지중화공사","154kV 동서울-송파T/L 무부하 가압용 BUS 휴전","2022-09-28 10:00","2022-09-29 10:00","2022-09-28 10:00","2022-09-29 10:00","연속"]
[63,"남서울","동서울","동서울S/S #62 BUS(신)","세종-포천 고속도로 건설 지장송전선로 지중화공사","154kV 팔수T/L 지중화공사 무부하 가압","2022-09-17 09:50","2022-09-17 10:00","취소","취소","연속"]
[64,"남서울","동서울","동서울S/S #61 BUS(신)","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-신장T/L 지중화공사 무부하 가압","2022-09-30 09:50","2022-09-30 10:00","2022-09-28 09:50","2022-09-28 10:00","연속"]
[65,"남서울","동서울","동서울S/S #60 BUS(신)","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-신장T/L 지중화공사 무부하 가압","2022-09-30 09:50","2022-09-30 10:00","취소","취소","연속"]
[66,"남서울","동서울","동서울S/S #62 BUS(신)","154kV 동서울-송파#2T/L 무부하가압","인터록, 상 확인","2022-09-28 09:50","2022-09-28 10:00","취소","취소","연속"]
[67,"남서울","동서울","동서울S/S #67 BUS(신)","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-신장T/L 지중화공사 관련 BUS 무부하가압 관련 휴전","2022-09-22 10:00","2022-09-23 10:00","취소","취소","연속"]
[68,"남서울","동서울","동서울S/S #66 BUS(신)","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-신장T/L 지중화공사 관련 BUS 무부하가압 관련 휴전","2022-09-22 10:00","2022-09-23 10:00","2022-09-22 10:00","2022-09-23 10:00","연속"]
[69,"남서울","동서울","동서울S/S #62 BUS(신)","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-신장T/L 지중화공사 무부하 가압","2022-09-22 09:50","2022-09-22 10:00","취소","취소","연속"]
[70,"남서울","동서울","동서울S/S #61 BUS(신)","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-신장T/L 지중화공사 무부하 가압","2022-09-22 09:50","2022-09-22 10:00","취소","취소","연속"]
[71,"남서울","동서울","동서울S/S #66 BUS(신)","세종-포천 고속도로 건설 지장송전선로 지중화공사","154kV 팔수T/L 지중화공사 관련 BUS 무부하가압 관련 휴전","2022-09-17 10:00","2022-09-18 10:00","취소","취소","연속"]
[72,"남서울","동서울","논현선릉#1 T/L","선릉SS 논현-선릉 #1TL 170kV GIS 조작시험","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-09-07 08:00","2022-09-07 13:00","2022-09-07 08:00","2022-09-07 13:00","연속"]
[73,"남서울","동서울","논현선릉#2 T/L","선릉SS 논현-선릉 #2TL 170kV GIS 조작시험","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-09-07 13:00","2022-09-07 17:00","2022-09-07 13:00","2022-09-07 17:00","연속"]
[74,"남서울","동서울","동서울송파#2 T/L","154kV 동서울-송파,가락T/L 지중화공사","154kV 동서울S/S ~ 거여C/H간 지중송전케이블 설치 ○ 선종 및 길이 : XLPE2,500SQ, 약 3.0km","2022-09-27 09:00","2022-09-29 18:00","2022-09-27 09:00","2022-09-29 18:00","연속"]
[75,"남서울","동서울","송파S/S #2 BUS","154kV 동서울-송파,가락T/L 지중화공사","154kV 동서울-송파T/L 무부하 가압용 BUS 휴전","2022-09-28 09:50","2022-09-28 10:00","2022-09-28 09:50","2022-09-28 10:00","연속"]
[76,"남서울","동서울","신장S/S #1 BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-신장T/L 무부하 가압용 BUS 휴전","2022-09-30 09:50","2022-09-30 10:00","취소","취소","연속"]
[77,"남서울","동서울","신장S/S #2 BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-신장T/L 무부하 가압용 BUS 휴전","2022-09-22 09:50","2022-09-22 10:00","취소","취소","연속"]
[78,"남서울","동서울","동서울위례#1 T/L","세종-포천 고속도로 건설 지장송전선로 지중화공사","154kV 팔수T/L 지중화공사 관련 무부하가압 선로","2022-09-17 09:00","2022-09-18 18:00","취소","취소","연속"]
[79,"남서울","동서울","동서울위례#1 T/L","154kV 동서울-송파#2T/L 무부하가압","154kV 동서울-송파#2T/L 무부하가압 선로","2022-09-28 09:00","2022-09-29 18:00","2022-09-28 09:00","2022-09-29 18:00","연속"]
[80,"남서울","동서울","동서울위례#1 T/L","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-신장T/L 지중화공사 관련 무부하가압 선로","2022-09-22 09:00","2022-09-23 18:00","2022-09-22 09:00","2022-09-23 18:00","연속"]
[81,"남서울","동서울","송파잠실#4 T/L","잠실SS 송파-잠실4TL GIS 베어링발청조치(유사고장)","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-09-22 09:00","2022-09-22 18:00","2022-09-22 09:00","2022-09-22 18:00","연속"]
[82,"남서울","영등포","독산S/S CB 6100","영등포전력지사 154kV GIS 정밀점검공사","154kV BUS TIE 정밀점검","2022-09-15 09:00","2022-09-16 18:00","2022-09-15 09:00","2022-09-16 18:00","연속"]
[83,"남서울","영등포","대림독산 T/L","영등포전력지사 154kV GIS 정밀점검공사","154kV 대림-독산T/L GIS 정밀점검","2022-09-05 09:00","2022-09-06 18:00","2022-09-05 09:00","2022-09-06 18:00","연속"]
[84,"남서울","영등포","시흥독산#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(#4M.Tr 1차 GIS)","2022-09-20 13:00","2022-09-20 18:00","2022-09-20 13:00","2022-09-20 18:00","연속"]
[85,"남서울","영등포","시흥독산#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(#3M.Tr 1차 GIS)","2022-09-22 13:00","2022-09-22 18:00","2022-09-22 13:00","2022-09-22 18:00","연속"]
[86,"남서울","영등포","시흥독산#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(#2M.Tr 1차 GIS)","2022-09-14 13:00","2022-09-14 18:00","2022-09-14 13:00","2022-09-14 18:00","연속"]
[87,"남서울","영등포","시흥독산#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(#1M.Tr 1차 GIS)","2022-09-02 13:00","2022-09-02 18:00","2022-09-02 13:00","2022-09-02 18:00","연속"]
[88,"남서울","영등포","독산대방#2 T/L","영등포전력지사 154kV GIS 정밀점검공사","154kV 독산-대방#2T/L GIS 정밀점검","2022-09-28 09:00","2022-09-29 18:00","2022-09-28 09:00","2022-09-29 18:00","연속"]
[89,"남서울","영등포","독산대방#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","154kV 독산-대방#1T/L GIS 정밀점검","2022-09-26 09:00","2022-09-27 18:00","2022-09-26 09:00","2022-09-27 18:00","연속"]
[90,"남서울","영등포","구공독산 T/L","영등포전력지사 154kV GIS 정밀점검공사","154kV 구공-독산T/L GIS 정밀점검","2022-09-07 09:00","2022-09-08 18:00","2022-09-07 09:00","2022-09-08 18:00","연속"]
[91,"남서울","영등포","당인리목동#1 T/L","'22-'23년 가공송전 협력회사 총액공사(추락방지시설 설치)","-154kV 당인리-목동T/L 수평단 추락방지시설 설치","2022-09-14 14:00","2022-09-15 18:00","취소","취소","연속"]
[92,"남서울","영등포","당인리목동#2 T/L","'22-'23년 가공송전 협력회사 총액공사(추락방지시설 설치)","-154kV 당인리-목동T/L 수평단 추락방지시설 설치","2022-09-14 08:00","2022-09-14 14:00","취소","취소","연속"]
[93,"남서울","영등포","신광명시흥#2 T/L","'22-'23년 가공송전 협력회사 총액공사(추락방지시설 설치)","-154kV 신광명-시흥#2T/L 수평단 추락방지시설 설치","2022-09-05 08:00","2022-09-08 18:00","2022-09-05 08:00","2022-09-08 18:00","연속"]
[94,"남서울","영등포","부천신정#1 T/L","2022~23년 영등포P/O 변전협력회사 총액공사","154kV 부천-신정#1T/L 보통점검","2022-09-29 09:00","2022-09-29 18:00","2022-09-29 09:00","2022-09-29 18:00","연속"]
[95,"남서울","영등포","부천신정#2 T/L","2022~23년 영등포P/O 변전협력회사 총액공사","154kV 부천-신정#2T/L 보통점검","2022-09-30 09:00","2022-09-30 18:00","2022-09-30 09:00","2022-09-30 18:00","연속"]
[96,"남서울","영등포","신광명온수 T/L","'22-'23년 가공송전 협력회사 총액공사(추락방지시설 설치)","-수평단 추락방지시설 설치","2022-09-22 08:00","2022-09-23 18:00","취소","취소","연속"]
[97,"남서울","직할","여의노량진 T/L","170kV GIS 정밀점검 무부하가압(#2M.Tr)","170kV GIS 정밀점검 무부하가압(#2M.Tr)","2022-09-16 15:00","2022-09-16 18:00","2022-09-16 15:00","2022-09-16 18:00","연속"]
[98,"남서울","직할","여의노량진 T/L","170kV GIS 정밀점검 무부하가압(#1M.Tr)","170kV GIS 정밀점검 무부하가압(#1M.Tr)","2022-09-14 15:00","2022-09-14 18:00","2022-09-14 15:00","2022-09-14 18:00","연속"]
[99,"남서울","직할","노들노량진 T/L","170kV GIS 정밀점검공사(노들-노량진T/L)","170kV GIS 정밀점검공사(노들-노량진T/L)","2022-09-26 09:00","2022-09-27 18:00","2022-09-25 09:00","2022-09-26 18:00","연속"]
[100,"남서울","직할","여의노량진 T/L","170kV GIS 정밀점검공사(여의-노량진T/L)","170kV GIS 정밀점검공사(여의-노량진T/L)","2022-09-28 09:00","2022-09-29 18:00","2022-09-28 09:00","2022-09-29 18:00","연속"]
[101,"남서울","직할","여의노량진 T/L","170kV GIS 정밀점검 무부하가압(#3M.Tr)","170kV GIS 정밀점검 무부하가압(#3M.Tr)","2022-09-20 15:00","2022-09-20 18:00","2022-09-20 15:00","2022-09-20 18:00","연속"]
[102,"남서울","동서울","동서울S/S #67 BUS(신)","동서울S/S #61D.Tr 현장개조 및 설치공사","M.Tr 1BANK 현장개조 및 설치 1, 2차 전력케이블 포설 및 접속","2022-09-29 10:00","2022-09-30 10:00","2022-09-29 10:00","2022-09-30 10:00","연속"]
[103,"남서울","동서울","동서울S/S #66 BUS(신)","동서울S/S #61D.Tr 현장개조 및 설치공사","M.Tr 1BANK 현장개조 및 설치 1, 2차 전력케이블 포설 및 접속","2022-09-29 10:00","2022-09-30 10:00","2022-09-29 10:00","2022-09-30 10:00","연속"]
[104,"남서울","동서울","동서울#2S/S #68 BUS","동서울S/S #61D.Tr 현장개조 및 설치공사","M.Tr 1BANK 현장개조 및 설치 1, 2차 전력케이블 포설 및 접속","2022-09-29 10:00","2022-09-30 10:00","2022-09-29 10:00","2022-09-30 10:00","연속"]
[105,"남서울","동서울","동서울위례#1 T/L","동서울S/S #61D.Tr 현장개조 및 설치공사","M.Tr 1BANK 현장개조 및 설치공사 1, 2차 전력케이블 포설 및 접속","2022-09-29 10:00","2022-09-30 10:00","2022-09-29 10:00","2022-09-30 10:00","연속"]
[106,"인천","김포","신김포S/S #61 BUS","신김포S/S 345kV #3M.Tr 증설공사(170kV GIS)","○ 170kV GIS x 1CCT 증설(#3M.Tr용)","2022-09-28 09:00","2022-10-01 18:00","취소","취소","연속"]
[107,"인천","김포","신김포S/S SEC CB 65660","신김포S/S 345kV #3M.Tr 증설공사(170kV GIS)","170kV GIS 무부하가압(61BUS)","2022-09-30 09:00","2022-10-01 18:00","취소","취소","연속"]
[108,"인천","김포","신김포S/S CB 6200","신김포S/S 345kV #3M.Tr 증설공사(170kV GIS)","170kV GIS 무부하가압(61BUS)","2022-09-30 09:00","2022-10-01 18:00","취소","취소","연속"]
[109,"인천","김포","신김포S/S #66 BUS","신김포S/S 345kV #3M.Tr 증설공사(170kV GIS)","○ 170kV GIS x 1CCT 증설(#3M.Tr용)","2022-09-28 09:00","2022-10-01 18:00","취소","취소","연속"]
[110,"인천","김포","왕길양촌#2 T/L","154kV 왕길S/S #4M.Tr GIS 설치공사","-154kV GIS × 4CCT 설치 -기타부대공사 × 1식 설치","2022-09-14 08:00","2022-10-05 18:00","2022-09-14 08:00","2022-10-05 18:00","연속"]
[111,"인천","부평","부개원미#2 T/L","부개S/S SA혼용화관련 케이블 이설공사","부개S/S SA혼용화관련 케이블 이설공사","2022-09-24 09:00","2022-09-24 18:00","2022-09-24 09:00","2022-09-24 18:00","연속"]
[112,"인천","부평","신가좌부개#2 T/L","부개S/S SA혼용화관련 케이블 이설공사","부개S/S SA혼용화관련 케이블 이설공사","2022-09-30 09:00","2022-09-30 18:00","2022-09-15 09:00","2022-09-15 18:00","연속"]
[113,"인천","부평","신가좌부개#1 T/L","부개S/S SA혼용화관련 케이블 이설공사","부개S/S SA혼용화관련 케이블 이설공사","2022-09-29 09:00","2022-09-29 18:00","2022-09-16 09:00","2022-09-16 18:00","연속"]
[114,"인천","부평","부개원미#1 T/L","부개S/S SA혼용화관련 케이블 이설공사","부개S/S SA혼용화관련 케이블 이설공사","2022-09-25 09:00","2022-09-25 18:00","2022-09-25 09:00","2022-09-25 18:00","연속"]
[115,"인천","부평","부흥부개#1 T/L","부개S/S SA혼용화관련 케이블 이설공사","부개S/S SA혼용화관련 케이블 이설공사","2022-09-17 09:00","2022-09-17 18:00","2022-09-17 09:00","2022-09-17 18:00","연속"]
[116,"인천","부평","신현송현#1 T/L","송현S/S 신현송현#1T/L GIS 보통점검","송현S/S 신현송현#1T/L GIS 보통점검","2022-09-15 09:00","2022-09-15 18:00","2022-09-15 09:00","2022-09-15 18:00","연속"]
[117,"인천","부평","신가좌신현#1 T/L","신가좌S/S 신가좌신현#1T/L 조작시험 및 보조계전기, 전자변 교체","신가좌S/S 신가좌신현#1T/L 조작시험 및 보조계전기, 전자변 교체","2022-09-16 09:00","2022-09-16 18:00","2022-09-16 09:00","2022-09-16 18:00","연속"]
[118,"인천","부평","신가좌S/S Sh.R CB","신가좌S/S #1Sh.R 6179GIS 초기점검","신가좌S/S #1Sh.R 6179GIS 초기점검","2022-09-05 09:00","2022-09-05 18:00","취소","취소","연속"]
[119,"인천","부평","인천CC포스코CC#1 T/L","인천CC포스코CC#1T/L GIS 조작시험","인천CC포스코CC#1T/L GIS 조작시험","2022-09-06 09:00","2022-09-06 13:00","2022-09-06 09:00","2022-09-06 13:00","연속"]
[120,"인천","부평","인천CC포스코CC#2 T/L","인천CC포스코CC#1T/L GIS 조작시험","인천CC포스코CC#1T/L GIS 조작시험(일정 협의 전)","2022-09-06 13:00","2022-09-06 18:00","2022-09-06 13:00","2022-09-06 18:00","연속"]
[121,"인천","시흥","남동연수#1 T/L","남동S/S 154kV #3M.Tr 1차 GIS 정밀점검(무부하용)","남동S/S 154kV #3M.Tr 1차 GIS 정밀점검(무부하용)","2022-09-28 13:00","2022-09-28 18:00","2022-09-28 13:00","2022-09-28 18:00","연속"]
[122,"인천","시흥","남동연수#1 T/L","남동S/S 154kV #3M.Tr 1차 GIS 정밀점검(무부하용)","남동S/S 154kV #3M.Tr 1차 GIS 정밀점검(무부하용)","2022-09-27 08:00","2022-09-27 13:00","2022-09-27 08:00","2022-09-27 13:00","연속"]
[123,"인천","시흥","남동연수#1 T/L","남동S/S 154kV #2M.Tr 1차 GIS 정밀점검(무부하용)","남동S/S 154kV #2M.Tr 1차 GIS 정밀점검(무부하용)","2022-09-24 13:00","2022-09-24 18:00","2022-09-24 13:00","2022-09-24 18:00","연속"]
[124,"인천","시흥","남동연수#1 T/L","남동S/S 154kV #2M.Tr 1차 GIS 정밀점검(무부하용)","남동S/S 154kV #2M.Tr 1차 GIS 정밀점검(무부하용)","2022-09-23 08:00","2022-09-23 13:00","2022-09-23 08:00","2022-09-23 13:00","연속"]
[125,"인천","시흥","남동연수#1 T/L","남동S/S 154kV #1M.Tr 1차 GIS 정밀점검(무부하용)","남동S/S 154kV #1M.Tr 1차 GIS 정밀점검(무부하용)","2022-09-20 08:00","2022-09-20 13:00","2022-09-20 08:00","2022-09-20 13:00","연속"]
[126,"인천","시흥","남동연수#1 T/L","남동S/S 154kV #1M.Tr 1차 GIS 정밀점검(무부하용)","남동S/S 154kV #1M.Tr 1차 GIS 정밀점검(무부하용)","2022-09-21 13:00","2022-09-21 18:00","2022-09-21 13:00","2022-09-21 18:00","연속"]
[127,"인천","시흥","신시흥도림#1 T/L","도림S/S 170kV 신시흥도림#1T/L GIS 누유보수","도림S/S 170kV 신시흥도림#1T/L GIS 누유보수","2022-09-26 09:00","2022-09-26 14:00","2022-09-26 09:00","2022-09-26 14:00","연속"]
[128,"인천","시흥","도림오봉#1 T/L","도림S/S 170kV 도림오봉#1 T/L GIS 누유보수","도림S/S 170kV 도림오봉#1 T/L GIS 누유보수","2022-09-26 14:00","2022-09-26 18:00","2022-09-26 14:00","2022-09-26 18:00","연속"]
[129,"인천","시흥","북시화서시화#3 T/L","북시화, 서시화S/S 154kV 북시화서시화#3 T/L GIS 보통점검","북시화, 서시화S/S 154kV 북시화서시화#3 T/L GIS 보통점검","2022-09-30 09:00","2022-09-30 18:00","2022-09-30 09:00","2022-09-30 18:00","연속"]
[130,"인천","시흥","북시화서시화#2 T/L","북시화S/S 154kV 북시화서시화#2T/L GIS 초기점검","북시화S/S 154kV 북시화서시화#2T/L GIS 초기점검","2022-09-26 09:00","2022-09-26 18:00","2022-09-26 09:00","2022-09-26 18:00","연속"]
[131,"인천","시흥","서서울#2소래 T/L","154kV 서서울-소래T/L 추락방지시설 설치공사","ㅇ 추락방지시설 설치(수평) - No.45~92(설치대상 : 총 37기)","2022-09-28 08:00","2022-10-04 18:00","2022-09-28 08:00","2022-10-04 18:00","매일"]
[132,"인천","시흥","온수소래 T/L","154kV 서서울-소래T/L 추락방지시설 설치공사\n(공사명, 공사내용 확인 필요)","ㅇ 추락방지시설 설치(수평) - No.45~92(설치대상 : 총 37기)\n(공사명, 공사내용 확인 필요)","2022-09-24 08:00","2022-09-25 18:00","2022-09-24 08:00","2022-09-25 18:00","매일"]
[133,"인천","시흥","서안양소래 T/L","154kV 서서울-소래T/L 추락방지시설 설치공사","ㅇ 추락방지시설 설치(수평) - No.45~92(설치대상 : 총 37기)","2022-09-21 08:00","2022-09-27 18:00","2022-09-21 08:00","2022-09-27 18:00","매일"]
[134,"인천","시흥","신광명소래 T/L","154kV 서서울-소래T/L 추락방지시설 설치공사","ㅇ 추락방지시설 설치(수평) - No.45~92(설치대상 : 총 37기) - No.76부터 4회선 병가구간","연기(10/1~10/3)","연기(10/1~10/3)","취소","취소","매일"]
[135,"인천","시흥","신시흥남동#2 T/L","신시흥S/S 154kV 신시흥남동#2 T/L CVT 대체","신시흥S/S 154kV 신시흥남동#2 T/L CVT 대체","2022-09-29 09:00","2022-09-29 18:00","2022-09-29 09:00","2022-09-29 18:00","연속"]
[136,"인천","시흥","신시흥S/S CB 6100","신시흥#1S/S 154kV 60-65 모선보호반 대체공사","신시흥#1S/S 154kV 60-65 모선보호반 대체 신시흥#1S/S 154kV #60-#65 BUS TIE GIS 조작시험","2022-09-19 09:00","2022-09-23 18:00","2022-09-19 09:00","2022-09-23 18:00","연속"]
[137,"인천","시흥","신시흥북시화#1 T/L","154kV 신시흥-시화 등 2개T/L 추락방지시설 설치공사","ㅇ 추락방지시설 설치(수평) - 시화T/L : No.14~17(4기) - 북시화T/L : No.1~5(5기, 시화T/L 병가구간)","2022-09-17 08:00","2022-09-17 18:00","2022-09-17 08:00","2022-09-17 18:00","매일"]
[138,"인천","시흥","신시흥북시화#2 T/L","154kV 신시흥-시화 등 2개T/L 추락방지시설 설치공사","ㅇ 추락방지시설 설치(수평) - 시화T/L : No.14~17(4기) - 북시화T/L : No.1~5(5기, 시화T/L 병가구간)","2022-09-18 08:00","2022-09-18 18:00","2022-09-18 08:00","2022-09-18 18:00","매일"]
[139,"인천","시흥","신시흥시화#2 T/L","154kV 신시흥-시화 등 2개T/L 추락방지시설 설치공사","ㅇ 추락방지시설 설치(수평) - 시화T/L : No.14~17(4기) - 북시화T/L : No.1~5(5기, 시화T/L 병가구간)","2022-09-18 08:00","2022-09-20 18:00","2022-09-18 08:00","2022-09-20 18:00","매일"]
[140,"인천","시흥","신시흥S/S CB 6300","신시흥#2S/S 154kV #62-#67 모선보호반 대체공사","신시흥#2S/S 154kV #62-#67 모선보호반 대체 신시흥#2S/S 154kV #62-#67 BUS TIE GIS 조작시험","2022-09-26 09:00","2022-09-30 18:00","2022-09-26 09:00","2022-09-30 18:00","연속"]
[141,"인천","시흥","신시흥시화#1 T/L","154kV 신시흥-시화 등 2개T/L 추락방지시설 설치공사","ㅇ 추락방지시설 설치(수평) - 시화T/L : No.14~17(4기) - 북시화T/L : No.1~5(5기, 시화T/L 병가구간)","2022-09-15 08:00","2022-09-17 18:00","2022-09-15 08:00","2022-09-17 18:00","매일"]
[142,"인천","시흥","신시흥S/S CB 6400","신시흥#2S/S 154kV #63-#68 BUS TIE GIS 보통점검","신시흥#2S/S 154kV #63-#68 BUS TIE GIS 보통점검","2022-09-14 09:00","2022-09-14 18:00","2022-09-14 09:00","2022-09-14 18:00","연속"]
[143,"인천","직할","신부평임학#1 T/L","임학S/S 신부평임학#1T/L GIS 정밀점검","임학S/S 신부평임학#1T/L GIS 정밀점검","2022-09-19 09:00","2022-09-21 14:00","취소","취소","연속"]
[144,"인천","직할","신부평임학#2 T/L","임학S/S 신부평임학#2T/L GIS 정밀점검","임학S/S 신부평임학#2T/L GIS 정밀점검","2022-09-21 14:00","2022-09-23 18:00","취소","취소","연속"]
[145,"경기북부","고양","양주고양#2 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 정밀점검 병가선로","2022-09-05 07:00","2022-09-05 13:00","2022-09-05 07:00","2022-09-05 13:00","연속"]
[146,"경기북부","고양","고양S/S CB 6100","효성제 170kV GIS 스프링타입 그리스 재도포","효성제 170kV GIS 스프링타입 그리스 재도포 -고양S/S","2022-09-14 09:00","2022-09-14 18:00","2022-09-14 09:00","2022-09-14 18:00","연속"]
[147,"경기북부","고양","양주고양#1 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 정밀점검 병가선로","2022-09-05 13:00","2022-09-05 18:00","2022-09-05 13:00","2022-09-05 18:00","연속"]
[148,"경기북부","고양","양주고양#1 T/L","22~23년 고양전력지사 가공송전협력회사 총액공사","추락방지시설 설치, 지지애자 교체 공사","2022-09-28 07:00","2022-09-30 18:00","2022-09-19 07:00","2022-09-21 18:00","연속"]
[149,"경기북부","고양","양주금촌#2 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 정밀점검 병가선로","2022-09-27 07:00","2022-09-27 18:00","2022-09-27 07:00","2022-09-27 18:00","연속"]
[150,"경기북부","고양","양주금촌#1 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 정밀점검 병가선로","2022-09-13 07:00","2022-09-16 18:00","2022-09-13 07:00","2022-09-16 18:00","연속"]
[151,"경기북부","고양","신덕은금촌#1 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 정밀점검","2022-09-26 07:00","2022-09-30 18:00","2022-09-26 07:00","2022-09-30 18:00","연속"]
[152,"경기북부","고양","신덕은S/S SEC CB 65660","22~23 고양전력 변전협력회사 총액공사","□ 신덕은S/S #61-#66 BUS 보호반 교체","2022-09-19 09:00","2022-09-23 18:00","2022-09-19 09:00","2022-09-23 18:00","연속"]
[153,"경기북부","고양","신덕은S/S SEC CB 60610","22~23 고양전력 변전협력회사 총액공사","□ 신덕은S/S #61-#66 BUS 보호반 교체","2022-09-19 09:00","2022-09-23 18:00","2022-09-19 09:00","2022-09-23 18:00","연속"]
[154,"경기북부","고양","신덕은S/S CB 6200","22~23 고양전력 변전협력회사 총액공사","□ 신덕은S/S #61-#66 BUS 보호반 교체","2022-09-19 09:00","2022-09-23 18:00","2022-09-19 09:00","2022-09-23 18:00","연속"]
[155,"경기북부","고양","신덕은금촌#2 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 정밀점검","2022-09-13 07:00","2022-09-16 18:00","2022-09-13 07:00","2022-09-16 18:00","연속"]
[156,"경기북부","고양","신덕은S/S #60 BUS","신덕은S/S 170kV GIS PD센서 불량교체","신덕은S/S 170kV GIS PD센서 불량교체 - #2M.TR 1DS부(2MTR, 60BUS 휴전)","2022-09-06 09:00","2022-09-08 18:00","2022-09-06 09:00","2022-09-08 18:00","연속"]
[157,"경기북부","고양","신파주원흥#2 T/L","22~23년 고양전력지사 가공송전협력회사 총액공사","추락방지시설 설치 공사","2022-09-05 07:00","2022-09-08 18:00","2022-09-05 07:00","2022-09-08 18:00","연속"]
[158,"경기북부","고양","일산S/S CB 6200","2022년 고양P/O 변전정비회사 총액공사","효성제 170kV 전동스프링방식 GIS 투입베어링 점검","2022-09-26 10:00","2022-09-26 18:00","2022-09-26 10:00","2022-09-26 18:00","연속"]
[159,"경기북부","고양","고양일산#2 T/L","일산변전소 옥외PT 하우징설치공사","화재확산 방지를 위한 옥외PT 하우징설치공사","2022-09-26 09:00","2022-10-02 18:00","2022-09-26 09:00","2022-10-02 18:00","연속"]
[160,"경기북부","구리","덕소팔당HP청평HP T/L","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-09-30 14:00","2022-09-30 18:00","2022-09-30 14:00","2022-09-30 18:00","연속"]
[161,"경기북부","구리","덕소팔당HP T/L","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-09-30 09:00","2022-09-30 14:00","2022-09-30 09:00","2022-09-30 14:00","연속"]
[162,"경기북부","구리","미금S/S SEC CB 65660","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","- 미금S/S 154kV #65-#66 SEC GIS 조작시험","2022-09-14 09:00","2022-09-14 14:00","2022-09-22 09:00","2022-09-22 14:00","연속"]
[163,"경기북부","구리","진건별내#1 T/L","22년도 구리전력지사 154kV GIS 정밀점검공사","154kV 정밀점검","2022-09-13 09:00","2022-09-14 18:00","2022-09-13 09:00","2022-09-14 18:00","연속"]
[164,"경기북부","구리","진건별내#2 T/L","22년도 구리전력지사 154kV GIS 정밀점검공사","154kV 정밀점검","2022-09-15 09:00","2022-09-16 18:00","2022-09-15 09:00","2022-09-16 18:00","연속"]
[165,"경기북부","구리","신포천포천#2 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치(수평)","2022-09-19 07:00","2022-09-23 18:00","2022-09-19 07:00","2022-09-23 18:00","연속"]
[166,"경기북부","구리","신포천동두천#1 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치(수직+수평)","2022-09-22 07:00","2022-09-30 18:00","2022-09-22 07:00","2022-09-30 18:00","연속"]
[167,"경기북부","구리","서홍천청평PP T/L","청평양수SY 노후 154kV GIS 노후 대체공사","○ 170kV GIS(50kA, 2000A) 철거 x 5CCT ○ 170kV GIS(50kA, 2000A) 설치 x 5CCT ○ 154kV 모선보호배전반 x 1Set ○ 154kV 옥외분전반 x 1면 ○ 제어케이블 포·결선 철거 및 설치 x 1식 ○ 기타 부대공사 x 1식","2022-09-26 09:00","2022-10-07 18:00","2022-09-26 09:00","2022-10-07 18:00","연속"]
[168,"경기북부","구리","서종청평PP#2 T/L","청평양수SY 노후 154kV GIS 노후 대체공사","○ 170kV GIS(50kA, 2000A) 철거 x 5CCT ○ 170kV GIS(50kA, 2000A) 설치 x 5CCT ○ 154kV 모선보호배전반 x 1Set ○ 154kV 옥외분전반 x 1면 ○ 제어케이블 포·결선 철거 및 설치 x 1식 ○ 기타 부대공사 x 1식","2022-09-26 09:00","2022-10-07 18:00","2022-09-26 09:00","2022-10-07 18:00","연속"]
[169,"경기북부","구리","포천운천#2 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치(수평)","2022-09-19 07:00","2022-09-19 18:00","2022-09-19 07:00","2022-09-19 18:00","연속"]
[170,"경기북부","구리","포천운천#1 T/L","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","- 포천S/S 154kV 포천-운천#1T/L GCB 조작시험","2022-09-20 09:00","2022-09-20 18:00","2022-09-20 09:00","2022-09-20 18:00","연속"]
[171,"경기북부","구리","용정포천#1 T/L","22-23 구리전력 변전협력 총액공사","154kV GCB 보통점검","2022-09-26 09:00","2022-09-26 18:00","2022-09-26 09:00","2022-09-26 18:00","연속"]
[172,"경기북부","구리","용정포천#2 T/L","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","- 포천S/S 154kV 포천-용정#2T/L GCB 조작시험","2022-09-15 09:00","2022-09-15 18:00","2022-09-29 09:00","2022-09-29 18:00","연속"]
[173,"경기북부","직할","용현도봉#2 T/L","154kV 장암S/S 옥내화관련 인출선로 정비공사","장암S/S 옥내화관련 인출 케이블타워 부지 옹벽설치","2022-09-13 09:00","2022-10-14 18:00","취소","취소","연속"]
[174,"경기북부","직할","신포천동두천#1 T/L","22-23 변전협력 총액공사","개폐타임 측정 및 순간압력센서 교체","2022-09-01 10:00","2022-09-01 18:00","2022-09-01 10:00","2022-09-01 18:00","연속"]
[175,"경기북부","직할","신의정부S/S SEC CB 65660","22-23 변전협력 총액공사","170kV GIS 보통점검","2022-09-20 09:00","2022-09-20 18:00","2022-09-20 09:00","2022-09-20 18:00","연속"]
[176,"경기북부","직할","신의정부송우#2 T/L","2022년도 가공송전 순시점검 위탁공사","초기점검","2022-09-16 12:00","2022-09-16 18:00","2022-09-16 12:00","2022-09-16 18:00","연속"]
[177,"경기북부","직할","신의정부내촌#2 T/L","22-23 변전협력 총액공사","170kV GIS 보통점검","2022-09-14 09:00","2022-09-14 18:00","2022-09-14 09:00","2022-09-14 18:00","연속"]
[178,"경기북부","직할","신의정부S/S SEC CB 60610","22-23 변전협력 총액공사","170kV GIS 보통점검","2022-09-15 09:00","2022-09-15 18:00","2022-09-15 09:00","2022-09-15 18:00","연속"]
[179,"경기북부","직할","신의정부송우#1 T/L","2022년도 가공송전 순시점검 위탁공사","초기점검","2022-09-16 08:00","2022-09-16 12:00","2022-09-16 08:00","2022-09-16 12:00","연속"]
[180,"경기북부","직할","신의정부송우#1 T/L","22-23 변전협력 총액공사","170kV GIS 보통점검","2022-09-21 09:00","2022-09-21 18:00","취소","취소","연속"]
[181,"경기","군포","마도사강#1 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 31기","2022-09-22 07:00","2022-09-22 12:00","2022-09-22 07:00","2022-09-22 12:00","매일"]
[182,"경기","군포","마도사강#2 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 31기","2022-09-22 12:00","2022-09-22 18:00","2022-09-22 12:00","2022-09-22 18:00","매일"]
[183,"경기","군포","화성마도 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 45기","2022-09-24 07:00","2022-09-24 12:00","2022-09-24 07:00","2022-09-24 12:00","매일"]
[184,"경기","군포","사강남양#2 T/L","사강S/S #4M.Tr 1차 GIS 정밀점검 무부하가압용","사강S/S #4M.Tr 1차 GIS 정밀점검 무부하가압용","2022-09-16 16:00","2022-09-16 18:00","2022-09-16 16:00","2022-09-16 18:00","연속"]
[185,"경기","군포","서서울#2일동#1 T/L","서서울2-일동#1T/L 보호배전반 대체공사, GIS 보통점검","서서울2-일동#1T/L 보호배전반 대체공사, GIS 보통점검","2022-09-18 09:00","2022-09-20 18:00","2022-09-18 09:00","2022-09-20 18:00","연속"]
[186,"경기","군포","서서울#2일동#2 T/L","서서울2-일동#2T/L 보호배전반 대체공사, GIS 보통점검","서서울2-일동#2T/L 보호배전반 대체공사, GIS 보통점검","2022-09-21 09:00","2022-09-23 18:00","2022-09-21 09:00","2022-09-23 18:00","연속"]
[187,"경기","군포","서서울#2서안양 T/L","154kV 서서울-소래T/L 추락방지시설 설치공사","ㅇ 추락방지시설 설치(수평) - No.45~92(설치대상 : 총 37기)","2022-09-13 08:00","2022-09-14 18:00","2022-09-13 08:00","2022-09-14 18:00","매일"]
[188,"경기","군포","화성장덕 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 45기","2022-09-24 12:00","2022-09-24 18:00","2022-09-24 12:00","2022-09-24 18:00","매일"]
[189,"경기","군포","장덕마도 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 45기","2022-09-21 12:00","2022-09-21 18:00","2022-09-21 12:00","2022-09-21 18:00","매일"]
[190,"경기","군포","수촌조암#1 T/L","조암SS #4M.Tr 1차 GIS 정밀점검 무부하가압용","조암SS #4M.Tr 1차 GIS 정밀점검 무부하가압용","2022-09-20 16:00","2022-09-20 18:00","2022-09-20 16:00","2022-09-20 18:00","연속"]
[191,"경기","군포","시화중시화 T/L","중시화SS #4M.Tr 1차 GIS 정밀점검 무부하가압용","중시화SS #4M.Tr 1차 GIS 정밀점검 무부하가압용","2022-09-30 16:00","2022-09-30 18:00","2022-09-30 16:00","2022-09-30 18:00","연속"]
[192,"경기","동부","분당S/S SEC CB 65660","22년 동부 변전정비협력공사","분당 : 60-61(조작) ,65-66(조작)","2022-09-23 14:00","2022-09-23 18:00","2022-09-23 14:00","2022-09-23 18:00","연속"]
[193,"경기","동부","분당S/S SEC CB 60610","22년 동부 변전정비협력공사","분당 : 60-61(조작) ,65-66(조작)","2022-09-23 09:30","2022-09-23 14:00","2022-09-23 09:30","2022-09-23 14:00","연속"]
[194,"경기","동부","분당S/S CB 6100","22년 동부 변전정비협력공사","분당 : 6100(조작) G/T#1(조작) [9.14-10.6]","2022-09-22 09:30","2022-09-22 18:00","2022-09-22 09:30","2022-09-22 18:00","연속"]
[195,"경기","동부","성현S/S CB 6100","22년 동부 변전정비협력공사","성현 : 6100(조작) ,6179(조작)","2022-09-21 09:30","2022-09-21 18:00","2022-09-21 09:30","2022-09-21 18:00","연속"]
[196,"경기","동부","초월성현#1 T/L","초월S/S #5M.Tr 증설사업","초월S/S #5M.Tr 증설공사 -#2BUS무부하가압용","2022-09-30 17:00","2022-10-01 18:00","2022-09-30 17:00","2022-10-01 18:00","연속"]
[197,"경기","성남","서안성남사#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사 [주말제외]","2022-09-27 08:00","2022-09-30 13:00","2022-09-27 08:00","2022-09-30 13:00","매일"]
[198,"경기","성남","덕성남사#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사 [주말제외]","2022-09-27 08:00","2022-09-30 18:00","2022-09-27 08:00","2022-09-30 18:00","매일"]
[199,"경기","성남","서안성남사#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사 [주말제외]","2022-09-21 08:00","2022-09-26 18:00","2022-09-21 08:00","2022-09-26 18:00","매일"]
[200,"경기","성남","덕성남사#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사 [주말제외]","2022-09-20 08:00","2022-09-26 18:00","2022-09-20 08:00","2022-09-26 18:00","매일"]
[201,"경기","성남","신봉이의#2 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","신봉이의, 율전동수원, 서수원율전 수직/수평 추락방지장치 설치","2022-09-16 13:00","2022-09-20 18:00","2022-09-16 13:00","2022-09-20 18:00","연속"]
[202,"경기","성남","신봉이의#1 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","신봉이의, 율전동수원, 서수원율전 수직/수평 추락방지장치 설치","2022-09-13 07:00","2022-09-16 12:00","2022-09-13 07:00","2022-09-16 12:00","연속"]
[203,"경기","성남","신성남서판교#2 T/L","2022년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험 - 순간압력센서 설치","2022-09-27 14:00","2022-09-27 18:00","2022-09-27 14:00","2022-09-27 18:00","연속"]
[204,"경기","성남","신성남S/S CB 6400","2022년 성남전력 362/170kV GIS 보통점검 공사","- GIS 보통점검","2022-09-21 09:00","2022-09-21 18:00","2022-09-21 09:00","2022-09-21 18:00","연속"]
[205,"경기","성남","신성남서판교#1 T/L","2022년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험 - 순간압력센서 설치","2022-09-27 09:00","2022-09-27 14:00","2022-09-27 09:00","2022-09-27 14:00","연속"]
[206,"경기","성남","신성남S/S SEC CB 67680","2022년 성남전력 362/170kV GIS 보통점검 공사","- GIS 보통점검","2022-09-20 14:00","2022-09-20 18:00","2022-09-20 14:00","2022-09-20 18:00","연속"]
[207,"경기","성남","신성남S/S SEC CB 62630","2022년 성남전력 362/170kV GIS 보통점검 공사","- GIS 보통점검","2022-09-20 09:00","2022-09-20 14:00","2022-09-20 09:00","2022-09-20 14:00","연속"]
[208,"경기","성남","신성남정자#2 T/L","2022년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2022-09-23 14:00","2022-09-23 18:00","2022-09-23 14:00","2022-09-23 18:00","연속"]
[209,"경기","성남","신성남정자#1 T/L","2022년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2022-09-23 09:00","2022-09-23 14:00","2022-09-23 09:00","2022-09-23 14:00","연속"]
[210,"경기","성남","신수원S/S CB 6300","2022년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험 - 순간압력센서 설치","2022-09-29 14:00","2022-09-29 18:00","2022-09-29 14:00","2022-09-29 18:00","연속"]
[211,"경기","성남","신수원S/S SEC CB 60610","2022년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험 - 순간압력센서 설치","2022-09-29 09:00","2022-09-29 14:00","2022-09-29 09:00","2022-09-29 14:00","연속"]
[212,"경기","성남","신수원S/S SEC CB 61620","2022년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2022-09-30 09:00","2022-09-30 14:00","2022-09-30 09:00","2022-09-30 14:00","연속"]
[213,"경기","성남","신수원S/S SEC CB 66670","2022년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2022-09-30 14:00","2022-09-30 18:00","2022-09-30 14:00","2022-09-30 18:00","연속"]
[214,"경기","성남","용인덕성#2 T/L","22년 가공송전 순시점검 위탁공사[경기 직할]","154kV 덕성-남사 및 용인-덕성T/L 초기점검(4회선 병가구간)","2022-09-30 13:00","2022-09-30 18:00","2022-09-30 13:00","2022-09-30 18:00","매일"]
[215,"경기","성남","신용인용인#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사(4회선 병가구간,안전거리) [주말제외]","2022-09-16 08:00","2022-09-19 18:00","2022-09-16 08:00","2022-09-19 18:00","매일"]
[216,"경기","성남","용인덕성#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사 [주말제외]","2022-09-13 08:00","2022-09-20 18:00","2022-09-13 08:00","2022-09-20 18:00","매일"]
[217,"경기","직할","봉담남수원#1 T/L","봉담S/S #1M.Tr 설치공사","봉담S/S #1M.Tr 설치공사 M.Tr 무부하가압","2022-09-03 09:00","2022-09-05 09:00","2022-09-03 09:00","2022-09-05 09:00","연속"]
[218,"경기","직할","서서울서수원#1 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 17기","2022-09-23 07:00","2022-09-26 18:00","2022-09-23 07:00","2022-09-26 18:00","매일"]
[219,"경기","직할","서서울서수원#2 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 17기","2022-09-27 07:00","2022-09-28 18:00","2022-09-27 07:00","2022-09-28 18:00","매일"]
[220,"경기","직할","서서울율전#2 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","신봉이의, 율전동수원, 서수원율전 수직/수평 추락방지장치 설치","2022-09-21 07:00","2022-09-21 18:00","2022-09-21 07:00","2022-09-21 18:00","연속"]
[221,"경기","직할","서서울율전#1 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","신봉이의, 율전동수원, 서수원율전 수직/수평 추락방지장치 설치","2022-09-30 07:00","2022-09-30 18:00","2022-09-30 07:00","2022-09-30 18:00","연속"]
[222,"경기","직할","서수원율전#2 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","신봉이의, 율전동수원, 서수원율전 수직/수평 추락방지장치 설치 (주말제외)","2022-09-21 07:00","2022-09-26 18:00","2022-09-21 07:00","2022-09-26 18:00","매일"]
[223,"경기","직할","서수원율전#1 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","신봉이의, 율전동수원, 서수원율전 수직/수평 추락방지장치 설치","2022-09-27 07:00","2022-09-30 18:00","2022-09-27 07:00","2022-09-30 18:00","매일"]
[224,"경기","직할","화성S/S #60 BUS","화성S/S 154kV 장기사용 GIS 교체공사","#1M.Tr 2차, 화성-발안#1T/L, #60-#65BUS TIE GIS 1DS 및 CB 대체","2022-09-19 09:00","2022-10-01 18:00","2022-09-19 09:00","2022-10-01 18:00","연속"]
[225,"경기","직할","화성S/S #65 BUS","화성S/S 154kV 장기사용 GIS 교체공사","#1M.Tr 2차, 화성-발안#1T/L, #60-#65BUS TIE GIS 2DS 분리 및 마감","2022-09-13 09:00","2022-09-16 18:00","2022-09-13 09:00","2022-09-16 18:00","연속"]
[226,"경기","직할","화성S/S CB 6100","화성S/S 154kV 장기사용 GIS 교체공사","154kV #60-#65 BUS TIE GIS 대체","2022-09-13 09:00","2022-10-16 18:00","2022-09-13 09:00","2022-10-16 18:00","연속"]
[227,"경기","직할","화성발안#1 T/L","화성S/S 154kV 장기사용 GIS 교체공사","154kV 화성-발안#1T/L GIS 대체","2022-09-13 09:00","2022-10-16 18:00","2022-09-13 09:00","2022-10-16 18:00","연속"]
[228,"경기","직할","화성마도 T/L","화성S/S 154kV 장기사용 GIS 교체공사","#65BUS 무부하가압","2022-09-16 09:00","2022-09-16 18:00","2022-09-16 09:00","2022-09-16 18:00","연속"]
[229,"경기","직할","화성마도 T/L","화성S/S 154kV 장기사용 GIS 교체공사","#60BUS 무부하가압","2022-09-30 09:00","2022-10-01 18:00","2022-09-30 09:00","2022-10-01 18:00","연속"]
[230,"경기","직할","화성남양#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","#1, 2T/L 조작시험","2022-09-26 14:00","2022-09-26 18:00","2022-09-26 14:00","2022-09-26 18:00","연속"]
[231,"경기","직할","화성남양#1 T/L","2022-23 경기본부 직할변전협력회사 총액공사","#1, 2T/L 조작시험","2022-09-26 09:00","2022-09-26 14:00","2022-09-26 09:00","2022-09-26 14:00","연속"]
[232,"경기","평택","서안성안성#2 T/L","서안성안성#2T/L 보호배전반 불량보수","서안성안성#2T/L 보호배전반 불량보수","2022-09-14 09:00","2022-09-14 18:00","2022-09-14 09:00","2022-09-14 18:00","연속"]
[233,"경기","평택","고덕평택#2 T/L","154kV 고덕#2-평택,동평택 지중T/L 인출정비공사","1. 공사목적 : 345kV 고덕2S/S 건설에 따른 계통 보강 2. 공사구간 : 345kV 고덕2S/S ～ 154kV 고덕-평택, 동평택T/L J/B#1 3. 선종 및 회선길이 - 고덕2-평택 : 154kV XLPE 1200㎟ 2회선(D)-0.0435㎞ - 고덕2-동평택 : 154kV XLPE 1200㎟ 2회선-0.438㎞","2022-09-01 09:00","2022-09-23 18:00","2022-09-01 09:00","2022-09-23 18:00","연속"]
[234,"경기","평택","고덕평택#1 T/L","154kV 고덕#2-평택,동평택 지중T/L 인출정비공사","1. 공사목적 : 345kV 고덕2S/S 건설에 따른 계통 보강 2. 공사구간 : 345kV 고덕2S/S ～ 154kV 고덕-평택, 동평택T/L J/B#1 3. 선종 및 회선길이 - 고덕2-평택 : 154kV XLPE 1200㎟ 2회선(D)-0.0435㎞ - 고덕2-동평택 : 154kV XLPE 1200㎟ 2회선-0.438㎞","2022-09-24 09:00","2022-10-16 18:00","2022-09-24 09:00","2022-10-16 18:00","연속"]
[235,"경기","평택","서운광혜원 T/L","서울-세종간 도로개설 관련 지장이설공사","154kV 서운-안성T/L 46, 47호 신설 2기","2022-09-15 07:00","2022-09-27 18:00","2022-09-15 07:00","2022-09-27 18:00","연속"]
[236,"경기","평택","서운안성#1 T/L","서울-세종간 도로개설 관련 지장이설공사","154kV 서운-안성T/L 46, 47호 신설 2기","2022-09-15 07:00","2022-09-27 18:00","2022-09-15 07:00","2022-09-27 18:00","연속"]
[237,"경기","평택","서운삼죽 T/L","서울-세종간 도로개설 관련 지장이설공사","154kV 서운-안성T/L 46, 47호 신설 2기","2022-09-28 07:00","2022-10-10 18:00","2022-09-28 07:00","2022-10-10 18:00","연속"]
[238,"경기","평택","서운안성#2 T/L","서울-세종간 도로개설 관련 지장이설공사","154kV 서운-안성T/L 46, 47호 신설 2기","2022-09-28 07:00","2022-10-10 18:00","2022-09-28 07:00","2022-10-10 18:00","연속"]
[239,"강원","강릉","신양양인제#2 T/L","2022~2023년 강릉전력지사 가공송전헙력회사 총액공사","○ 345kV 안인개폐소-신양양T/L 4회선 병가구간 작업자 안전을 위한 휴전 - 수직, 수평 추락방지장치 설치 작업","2022-09-28 07:00","2022-09-29 18:00","2022-09-28 07:00","2022-09-29 18:00","매일"]
[240,"강원","강릉","주진평창#1 T/L","2022년 강원본부 주진S/S #3M.Tr 증설공사","임시 SPS 설치","2022-09-30 09:00","2022-09-30 18:00","취소","취소","연속"]
[241,"강원","강릉","주진둔내#1 T/L","2022년 강원본부 주진S/S #3M.Tr 증설공사","임시 SPS 설치","2022-09-30 09:00","2022-09-30 18:00","취소","취소","연속"]
[242,"강원","원주","북원주횡성#2 T/L","2022~2023년 송전협력회사 총액공사","○ 추락방지장치 설치","2022-09-14 08:00","2022-09-20 17:00","취소","취소","매일"]
[243,"강원","원주","북원주횡성#1 T/L","2022~2023년 송전협력회사 총액공사","○ 추락방지장치 설치","2022-09-21 08:00","2022-09-30 17:00","취소","취소","매일"]
[244,"강원","원주","상남S/S #1 BUS","'22년 상남S/S 모선구분차단기 설치공사","154kV BUS TIE × 1CCT 154kV BUS SEC × 2CCT 154kV PT&ES × 1Bay 기타 부대공사 × 1식","2022-09-14 09:00","2022-09-29 18:00","2022-09-14 09:00","2022-09-29 18:00","연속"]
[245,"강원","원주","홍천상남#1 T/L","'22년 상남S/S 모선구분차단기 설치공사","154kV BUS TIE × 1CCT 154kV BUS SEC × 2CCT 154kV PT&ES × 1Bay 기타 부대공사 × 1식","2022-09-28 09:00","2022-09-29 18:00","2022-09-28 09:00","2022-09-29 18:00","연속"]
[246,"강원","원주","홍천상남#2 T/L","'22년 상남S/S 모선구분차단기 설치공사","(안전이격 확보 휴전) 154kV BUS TIE × 1CCT 154kV BUS SEC × 2CCT 154kV PT&ES × 1Bay 기타 부대공사 × 1식","2022-09-19 09:00","2022-09-21 18:00","2022-09-19 09:00","2022-09-21 18:00","매일"]
[247,"강원","원주","홍천상남#1 T/L","'22년 상남S/S 모선구분차단기 설치공사","(안전이격 확보 휴전) 154kV BUS TIE × 1CCT 154kV BUS SEC × 2CCT 154kV PT&ES × 1Bay 기타 부대공사 × 1식","2022-09-15 09:00","2022-09-17 18:00","2022-09-15 09:00","2022-09-17 18:00","매일"]
[248,"강원","원주","상남인제#2 T/L","'22년 상남S/S 모선구분차단기 설치공사","(안전이격 확보 휴전) 154kV BUS TIE × 1CCT 154kV BUS SEC × 2CCT 154kV PT&ES × 1Bay 기타 부대공사 × 1식","2022-09-19 09:00","2022-09-24 18:00","2022-09-19 09:00","2022-09-24 18:00","매일"]
[249,"강원","원주","횡성홍천#1 T/L","2022~2023년 송전정비회사 총액공사(원주)","○ 수직, 수평 추락방지장치 설치","2022-09-14 08:00","2022-09-20 18:00","2022-09-14 08:00","2022-09-20 18:00","매일"]
[250,"강원","원주","홍천소양강HP T/L","154kV 남춘천-춘천 등 2개T/L 용량증대 전선교체공사","소양T/L No.23~91-3 추락방지장치 설치 No.74~91-3 전선교체","2022-09-29 07:00","2022-10-24 18:00","2022-09-29 07:00","2022-10-24 18:00","연속"]
[251,"강원","원주","횡성홍천#2 T/L","2022~2023년 송전정비회사 총액공사(원주)","○ 수직, 수평 추락방지장치 설치","2022-09-21 08:00","2022-09-30 18:00","2022-09-21 08:00","2022-09-30 18:00","매일"]
[252,"강원","직할","북춘천화천HP T/L","2022~2023년 강원본부 직할 가공송전협력회사 총액공사","154kV 한강분기T/L No.2~10 추락방지장치 설치(회선명 : 북춘천화천HPT/L)","2022-09-14 08:00","2022-09-14 18:00","2022-09-03 08:00","2022-09-03 18:00","연속"]
[253,"강원","직할","서홍천춘천열병합 T/L","2022~2023년 강원직할 가공송전 협력회사 총액공사","154kV 서홍천-춘천열병합T/L 추락방지장치 설치","2022-09-16 08:00","2022-09-24 18:00","2022-09-16 08:00","2022-09-24 18:00","매일"]
[254,"강원","직할","양구화천HP#2 T/L","2022~2023년 강원본부 직할 가공송전협력회사 총액공사","154kV 양구-화천HP #2T/L No.23, 25 피뢰기설치(낙뢰피해개소복구)","2022-09-01 08:00","2022-09-01 18:00","2022-09-01 08:00","2022-09-01 18:00","연속"]
[255,"강원","직할","양구화천HP#2 T/L","43PDA 캠스위치 불량조치","- 양구S/S 양구-화천HP #2T/L 보호배전반 43PDA 캠스위치 교체","2022-09-01 10:00","2022-09-01 18:00","2022-09-01 10:00","2022-09-01 18:00","연속"]
[256,"강원","직할","가평춘천HP T/L","2022~2023년 강원본부 직할 가공송전협력회사 총액공사","154kV 한강분기T/L No.2~10 추락방지장치 설치(회선명 : 가평춘천HPT/L)","2022-09-15 08:00","2022-09-15 18:00","2022-09-04 08:00","2022-09-04 18:00","연속"]
[257,"강원","직할","춘천북춘천#2 T/L","154kV 남춘천-춘천 등 2개T/L 용량증대 전선교체공사","춘천분기T/L No.11~25 추락방지장치 설치","2022-09-24 07:00","2022-09-26 18:00","2022-09-24 07:00","2022-09-26 18:00","매일"]
[258,"강원","직할","춘천소양강HP T/L","154kV 남춘천-춘천 등 2개T/L 용량증대 전선교체공사","춘천분기T/L No.1~25 추락방지장치 설치","2022-09-24 07:00","2022-09-28 18:00","2022-09-24 07:00","2022-09-28 18:00","매일"]
[259,"강원","직할","춘천북춘천#1 T/L","154kV 남춘천-춘천 등 2개T/L 용량증대 전선교체공사","춘천분기T/L No.11~25 추락방지장치 설치","2022-09-14 07:00","2022-09-16 18:00","2022-09-14 07:00","2022-09-16 18:00","매일"]
[260,"강원","직할","남춘천춘천 T/L","154kV 남춘천-춘천 등 2개T/L 용량증대 전선교체공사","154kV 소양T/L No.23~74, 춘천분기T/L No.1~25 추락방지장치 설치","2022-09-14 07:00","2022-09-23 18:00","2022-09-14 07:00","2022-09-23 18:00","매일"]
[261,"강원","직할","청평PP춘천열병합 T/L","2022~2023년 강원직할 가공송전 협력회사 총액공사","154kV 청평PP-춘천열병합T/L 추락방지장치 설치","2022-09-15 08:00","2022-09-15 18:00","2022-09-15 08:00","2022-09-15 18:00","연속"]
[262,"강원","직할","가평화천HP T/L","2022년 가공송전 순시점검 위탁공사(직할)","154kV 화천 No.1 가공지선 과열개소 점검 및 조치","2022-09-13 09:00","2022-09-13 18:00","2022-09-18 09:00","2022-09-18 18:00","연속"]
[263,"강원","직할","화천화천HP#2 T/L","2022~2023년 강원본부 직할 변전협력회사 총액공사","화천, 화천HP 154kV 화천-화천HP #2 T/L 보호배전반 대체공사","2022-09-13 09:00","2022-09-16 18:00","2022-09-13 09:00","2022-09-16 18:00","연속"]
[264,"강원","직할","화천화천HP#1 T/L","2022~2023년 강원본부 직할 변전협력회사 총액공사","화천, 화천HP 154kV 화천-화천HP #1 T/L 보호배전반 대체공사","2022-09-05 09:00","2022-09-08 18:00","2022-09-05 09:00","2022-09-08 18:00","연속"]
[265,"강원","태백","정선영월CC T/L","2022년 태백전력지사 154KV GIS 정밀점검공사","154kV 영월CC 정선-영월CC#1 T/L GIS 정밀점검","2022-09-28 10:00","2022-09-30 18:00","2022-09-28 09:00","2022-09-30 18:00","연속"]
[266,"강원","태백","동영월영월CC T/L","2022년 태백전력지사 154KV GIS 정밀점검공사","154kV 영월CC 동영월-영월CC T/L GIS 정밀점검","2022-09-26 09:00","2022-09-27 18:00","2022-09-26 09:00","2022-09-27 18:00","연속"]
[267,"강원","태백","단양영월CC#2 T/L","2022년 태백전력지사 154KV GIS 정밀점검공사","154kV 영월CC 단양-영월CC#2 T/L GIS 정밀점검","2022-09-22 10:00","2022-09-24 18:00","2022-09-22 10:00","2022-09-24 18:00","연속"]
[268,"강원","태백","신제천영월CC#2 T/L","22-23년 태백전력지사 변전협력회사 총액공사","영월C/C S/Y 154kV 신제천-영월C/C#2T/L GIS 보통점검","2022-09-15 14:00","2022-09-15 18:00","2022-09-15 14:00","2022-09-15 18:00","연속"]
[269,"강원","태백","단양영월CC#1 T/L","2022년 태백전력지사 154KV GIS 정밀점검공사","154kV 영월CC 단양-영월CC#1 T/L GIS 정밀점검","2022-09-19 10:00","2022-09-21 18:00","2022-09-14 09:00","2022-09-16 18:00","연속"]
[270,"강원","태백","신제천영월CC#1 T/L","22-23년 태백전력지사 변전협력회사 총액공사","영월C/C S/Y 154kV 신제천-영월C/C#1T/L GIS 보통점검","2022-09-15 09:00","2022-09-15 14:00","2022-09-15 09:00","2022-09-15 14:00","연속"]
[271,"강원","태백","고한영월 T/L","영월 에코윈드 접속설비 건설","태백T/L 가선로 구성","2022-09-07 09:00","2022-09-08 18:00","2022-09-07 09:00","2022-09-08 18:00","연속"]
[272,"강원","태백","태백영월 T/L","영월 에코윈드 접속설비 건설","태백T/L 가선로 구성","2022-09-05 09:00","2022-09-06 18:00","2022-09-05 09:00","2022-09-06 18:00","연속"]
[273,"강원","태백","태백삼척GP#1 T/L","2022~2023년 태백전력지사 가공송전 협력회사 총액공사","기술개발과제(에너지 포집장치) 시범설치","2022-09-19 09:00","2022-09-19 15:00","2022-09-19 09:00","2022-09-19 15:00","연속"]
[274,"강원","태백","태백고한 T/L","영월-고한-태백간 OPGW 교체공사","- OPGW(OP-S-L48) 12.315km 교체","2022-09-24 08:00","2022-10-04 18:00","2022-09-24 08:00","2022-10-04 18:00","연속"]
[275,"강원","태백","태백삼척GP#2 T/L","2022~2023년 태백전력지사 가공송전 협력회사 총액공사","No. 146~148구간 가공지선 항공장애표시구 교체","2022-09-25 09:00","2022-09-25 12:00","2022-09-25 09:00","2022-09-25 12:00","연속"]
[276,"충북","직할","진천광혜원#1 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","154kV 장기사용 GIS 대체작업 및 GIS 설치 완료 후 #60, 65 BUS 무부하가압","2022-09-24 09:00","2022-09-30 16:00","취소","취소","연속"]
[277,"충북","직할","진천덕산#1 T/L","170kV LS제 GIS 가스주입구 개선공사","가스 오회수 방지를 위한 가스배관 개선","2022-09-14 10:00","2022-09-14 18:00","2022-09-24 10:00","2022-09-24 18:00","연속"]
[278,"충북","직할","진천덕산#2 T/L","170kV LS제 GIS 가스주입구 개선공사","가스 오회수 방지를 위한 가스배관 개선","2022-09-15 10:00","2022-09-15 18:00","2022-10-01 10:00","2022-10-01 18:00","연속"]
[279,"충북","직할","신진천진천#1 T/L","170kV LS제 GIS 가스주입구 개선공사","가스 오회수 방지를 위한 가스배관 개선","2022-09-17 10:00","2022-09-17 18:00","취소","취소","연속"]
[280,"충북","직할","신진천진천#2 T/L","170kV LS제 GIS 가스주입구 개선공사","가스 오회수 방지를 위한 가스배관 개선","2022-09-24 10:00","2022-09-24 18:00","취소","취소","연속"]
[281,"충북","청주","신옥천추부#1 T/L","170kV GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 170kV GIS 하자점검 (설비 하자기간에 따른 수급기간 점검)","2022-09-07 10:00","2022-09-07 18:00","2022-09-07 10:00","2022-09-07 18:00","연속"]
[282,"충북","청주","옥천영동 T/L","2022년 청주전력지사 170kV GIS 정밀점검공사","영동S/S 154kV #1BUS-TIE GIS 정밀점검 후 무부하가압","2022-09-08 09:00","2022-09-08 18:00","2022-09-08 09:00","2022-09-08 18:00","연속"]
[283,"충북","청주","남청주오송#1 T/L","송전 추락방지시설 설치공사","1. 공 사 명 : 154kV 남청주-청주 등 4개T/L 추락방지시설 설치공사 2. 공사장소 : 154kV 남청주-오송T/L No.38~56 3. 공사내역 : 수평 추락방지시설 설치","2022-09-24 07:00","2022-09-25 18:00","2022-09-24 07:00","2022-09-25 18:00","연속"]
[284,"충북","청주","신진천오창#2 T/L","2022년 청주전력지사 170kV GIS 정밀점검공사","오창S/S 154kV 신진천오창#2T/L GIS 정밀점검","2022-09-05 09:00","2022-09-06 18:00","취소","취소","연속"]
[285,"충북","청주","신옥천옥천#1 T/L","옥천S/S 고속철도#1T/L 1DS부 교체작업","옥천S/S 고속철도#1T/L 1,2DS부 제작사 입회 교체작업 후 시험가압","2022-09-20 10:00","2022-09-21 12:00","취소","취소","매일"]
[286,"충북","청주","신옥천옥천#1 T/L","옥천S/S 고속철도#2T/L 1DS부 교체작업","옥천S/S 고속철도#2T/L 1DS부 제작사 입회 교체작업 후 시험가압","2022-09-23 10:00","2022-09-23 12:00","취소","취소","연속"]
[287,"충북","청주","율량봉명#1 T/L","170 GIS 초기점검","[22-23 청주전력 변전정비 총액공사] 154kV 170GIS 초기점검","2022-09-14 10:00","2022-09-14 18:00","2022-09-14 10:00","2022-09-14 18:00","연속"]
[288,"충북","충주","감곡가남#2 T/L","22-23년 충주전력지사 변전정비 총액공사","감곡S/S 감곡-가남#2T/L LA 점검","2022-09-19 10:00","2022-09-19 18:00","2022-09-24 10:00","2022-09-25 18:00","연속"]
[289,"충북","충주","감곡가남#1 T/L","2022년 가공 송전선로 추락방지장치 설치공사","감곡가남#1T/L No.1~22 추락방지장치 설치공사","2022-09-26 07:30","2022-09-30 18:00","2022-09-24 07:30","2022-09-25 18:00","매일"]
[290,"충북","충주","음성금왕#1 T/L","2022년 가공 송전선로 추락방지장치 설치공사","음성-금왕#1T/L 추락방지장치 No.1-1~65 설치공사 * 추석(9.9,9.12) 및 주말 제외, 총 13일","2022-09-05 07:30","2022-09-23 18:00","취소","취소","매일"]
[291,"충북","충주","음성금왕#2 T/L","22-23년 충주전력지사 변전정비 총액공사","금왕S/S 음성-금왕#2T/L GIS 보통점검","2022-09-21 09:00","2022-09-21 18:00","2022-09-21 09:00","2022-09-21 18:00","연속"]
[292,"충북","충주","점촌단양 T/L","단양S/S 154kV 장기사용 GIS 대체공사","○ 점촌-단양 T/L 인출변경 (구 GIS → 신 GIS) ○ 점촌-단양 T/L 감시·제어케이블 이설 (구 GIS → 신 GIS, 현장정보처리반 → SA현장정보처리반)","2022-09-03 08:00","2022-09-04 18:00","2022-09-03 08:00","2022-09-04 18:00","연속"]
[293,"충북","충주","문경단양 T/L","단양S/S 154kV 장기사용 GIS 대체공사","○ 문경-단양 T/L 인출변경 (구 GIS → 신 GIS) ○ 문경-단양 T/L 감시·제어케이블 이설 (구 GIS → 신 GIS, 현장정보처리반 → SA현장정보처리반)","2022-09-17 08:00","2022-09-18 18:00","2022-09-17 08:00","2022-09-18 18:00","연속"]
[294,"충북","충주","단양영월CC#2 T/L","단양S/S 154kV 장기사용 GIS 대체공사","○ 단양-영월CC #2 T/L 인출변경 (구 GIS → 신 GIS) ○ 단양-영월CC #2 T/L 감시·제어케이블 이설 (구 GIS → 신 GIS, 현장정보처리반 → SA현장정보처리반)","2022-09-19 08:00","2022-09-22 18:00","2022-09-19 08:00","2022-09-22 18:00","연속"]
[295,"충북","충주","신제천왕암#2 T/L","154kV 신제천-제천T/L 용량증대 전선교체공사","전력선 교체 : 38경간 추락방지 장치 : 수직 10기, 수평 36기 설치","2022-09-26 07:00","2022-10-05 18:00","2022-09-26 07:00","2022-10-05 18:00","연속"]
[296,"충북","충주","신충주감곡#2 T/L","2022년 직할 가공송전선로 순시점검 위탁공사","신충주감곡#2T/L 2회선구간 No. 51~62(12기) 및 병가구간 No.77~88(12기) 정밀점검 및 절연저항 측정(No.1,3,5,7,8,14,16) * 총 8일, 휴일(토, 일) 제외","2022-09-19 07:30","2022-09-28 18:00","2022-09-19 07:30","2022-09-28 18:00","매일"]
[297,"충북","충주","신충주음성#1 T/L","2022년 직할 가공송전선로 순시점검 위탁공사","신충주음성#1T/L 병가구간 No. 64~70(6기), 2회선구간 No.71 정밀점검 및 병가구간 No. 1,3,5,7,8,14,16(7기) 절연저항측정","2022-09-19 07:30","2022-09-21 18:00","2022-09-19 07:30","2022-09-23 18:00","매일"]
[298,"충북","충주","왕암여주#2 T/L","2022년 직할 가공송전선로 순시점검 위탁공사","신충주감곡#2T/L No.77~85 추락방지장치 설치 및 송전선로 정밀점검 을 위한 병가선로 휴전 * 주말제외, 총 5일","2022-09-22 07:30","2022-09-28 18:00","2022-09-26 07:30","2022-09-28 18:00","매일"]
[299,"충북","충주","제천영월#1 T/L","154kV 제천-영월T/L 용량증대 전선교체공사","철탑교체 8기, 전선교체 7.28km","2022-09-19 08:00","2022-09-25 18:00","2022-09-19 08:00","2022-09-25 18:00","연속"]
[300,"충북","충주","제천영월#2 T/L","154kV 제천-영월T/L 용량증대 케이블 교체공사","제천S/S ~ 제천C/T 지중케이블 철거, 포설, 접속","2022-09-26 09:00","2022-10-21 18:00","2022-09-26 09:00","2022-10-21 18:00","연속"]
[301,"충북","충주","신제천제천#2 T/L","154kV 신제천-제천T/L 용량증대 케이블 교체공사","제천S/S ~ 제천C/T 지중케이블 철거, 포설, 접속","2022-09-19 09:00","2022-10-14 18:00","2022-09-19 09:00","2022-10-14 18:00","연속"]
[302,"충북","충주","충주충주HP#1 T/L","22-23년 충주전력지사 변전정비 총액공사","충주S/S 154kV 충주-수력#1T/L 장기사용 보호배전반 대체","2022-09-26 09:00","2022-09-28 18:00","취소","취소","연속"]
[303,"충북","충주","북충주충주 T/L","154kV 왕암-충주 등 2개T/L 압축인류클램프 정비공사","154kV 북충주-충주 TL 압축인류클램프 정비공사","2022-09-19 07:00","2022-09-21 18:00","2022-09-19 07:00","2022-09-21 18:00","매일"]
[304,"충북","충주","충주충주HP#2 T/L","22-23년 충주전력지사 변전정비 총액공사","충주S/S 154kV 충주-수력#2T/L 장기사용 보호배전반 대체","2022-09-29 09:00","2022-09-30 18:00","취소","취소","연속"]
[305,"대전세종충남","대전","금산무주#2 T/L","금산S/S 효성제 170kV GIS 스프링 조작기구 부적합사항 처리","금산S/S 효성제 170kV GIS 스프링 조작기구 부적합사항 처리 - 금산무주#2T/L GIS","2022-09-14 09:00","2022-09-14 18:00","2022-09-14 09:00","2022-09-14 18:00","연속"]
[306,"대전세종충남","대전","금산무주#1 T/L","금산S/S 효성제 170kV GIS 스프링 조작기구 부적합사항 처리","금산S/S 효성제 170kV GIS 스프링 조작기구 부적합사항 처리 - 금산무주#1T/L GIS","2022-09-13 09:00","2022-09-13 18:00","2022-09-13 09:00","2022-09-13 18:00","연속"]
[307,"대전세종충남","대전","신옥천서대전 T/L","[지중]22~23년 지중송전설비 위탁정비공사","○ 피뢰기 절연열화 진단 - 신옥천서대전T/L No.108 3상","2022-09-21 09:00","2022-09-22 18:00","취소","취소","매일"]
[308,"대전세종충남","대전","신계룡두마#2 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지장치 설치공사","[송전] 345kV 신옥천-청양T/L 추락방지장치 설치공사 안전거리 확보차","2022-09-30 08:00","2022-09-30 18:00","2022-09-30 08:00","2022-09-30 18:00","연속"]
[309,"대전세종충남","대전","신계룡두마#1 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지시설 설치공사","[송전] 345kV 신옥천-청양T/L 철탑 추락방지시설 설치공사 안전거리 확보차","2022-09-22 08:00","2022-09-22 18:00","2022-09-22 08:00","2022-09-22 18:00","연속"]
[310,"대전세종충남","대전","신옥천유천 T/L","[지중]22~23년 지중송전설비 위탁정비공사","○ 피뢰기 절연열화 진단 - 신옥천유천T/L No.1","2022-09-26 09:00","2022-09-27 18:00","취소","취소","매일"]
[311,"대전세종충남","서산","신당진당진#2 T/L","'22년 서산P/O 변전협력회사 총액공사","당진S/S 154kV 신당진-당진#2T/L 657 CB 하자점검","2022-09-14 09:00","2022-09-14 18:00","2022-09-14 09:00","2022-09-14 18:00","연속"]
[312,"대전세종충남","서산","신당진당진#1 T/L","'22년 서산P/O 변전협력회사 총액공사","당진S/S 154kV 신당진-당진#1T/L 647 CB 하자점검","2022-09-16 09:00","2022-09-16 18:00","2022-09-16 09:00","2022-09-16 18:00","연속"]
[313,"대전세종충남","서산","태안안면#1 T/L","[송전]154kV 태안-안면T/L 전선교체공사","○ 공사구간 : 154kV 태안-안면T/L No.1~71(1공구 : No.1~33, 2공구 : No.33~71) ○ 전력선 : ACSR/AW 330㎟ × S × 2C -> ASCC/TW 430㎟ × S × 2C 21.778km(전선교체)","2022-09-19 07:00","2022-10-28 18:00","2022-09-19 07:00","2022-10-28 18:00","연속"]
[314,"대전세종충남","세종","덕진대화#2 T/L","[변전]2022년 세종P/O 변전협력회사 총액공사","○154kV GIS 보통점검","2022-09-14 10:00","2022-09-14 18:00","2022-09-14 10:00","2022-09-14 18:00","연속"]
[315,"대전세종충남","세종","둔곡송강#1 T/L","[변전]2022년 세종P/O 변전협력회사 총액공사","○154kV GIS 하자점검","2022-09-15 10:00","2022-09-15 18:00","2022-09-13 10:00","2022-09-13 18:00","연속"]
[316,"대전세종충남","세종","부강신탄진 T/L","[송전]154kV 부강-신탄진 추락방지시설 설치공사","[송전]154kV 부강-신탄진 추락방지시설 설치공사 - No. 1~57, 62 (63기)","2022-09-14 07:00","2022-09-23 18:00","2022-09-14 07:00","2022-09-23 18:00","매일"]
[317,"대전세종충남","세종","부강대청HP T/L","[송전]154kV 부강-대청 추락방지시설 설치공사","[송전]154kV 부강-대청 추락방지시설 설치공사 - No.7~42 (36기)","2022-09-27 07:00","2022-09-29 18:00","2022-09-27 07:00","2022-09-29 18:00","매일"]
[318,"대전세종충남","세종","세종부강#2 T/L","[송전]154kV 부강-신탄진 추락방지시설 설치공사 병가선로","[송전]154kV 부강-신탄진 추락방지시설 설치공사 병가선로 - No. 1~6","2022-09-14 07:00","2022-09-14 18:00","2022-09-14 07:00","2022-09-14 18:00","연속"]
[319,"대전세종충남","세종","세종CC서세종#2 T/L","[변전]2022년 세종P/O 154kV GIS 정밀점검공사","154kV GIS 정밀점검 시행(10BAY)","2022-09-21 09:00","2022-09-22 18:00","취소","취소","연속"]
[320,"대전세종충남","세종","세종CC서세종#1 T/L","[변전]2022년 세종P/O 154kV GIS 정밀점검공사","154kV GIS 정밀점검 시행(10BAY)","2022-09-19 09:00","2022-09-20 18:00","취소","취소","연속"]
[321,"대전세종충남","세종","세종월산#1 T/L","[변전]2022년 세종P/O 154kV GIS 정밀점검공사","154kV GIS 정밀점검 시행(10BAY)","2022-09-26 09:00","2022-09-27 18:00","2022-09-26 09:00","2022-09-27 18:00","연속"]
[322,"대전세종충남","세종","세종월산#2 T/L","[변전]2022년 세종P/O 154kV GIS 정밀점검공사","154kV GIS 정밀점검 시행(10BAY)","2022-09-28 09:00","2022-09-29 18:00","2022-09-28 09:00","2022-09-29 18:00","연속"]
[323,"대전세종충남","세종","천안전의#2 T/L","[변전]2022년 세종P/O 변전협력회사 총액공사","○154kV GIS 보통점검 - 병행 : LA 보통점검","2022-09-16 10:00","2022-09-16 18:00","2022-09-16 10:00","2022-09-16 18:00","연속"]
[324,"대전세종충남","세종","조치원전의#2 T/L","[송전]154kV 조치원-전의T/L 안전이격거리확보공사","○ 공사구간 : 154kV 조치원-전의T/L No.36~39 ○ 지지물 : 1기 교체(37호), 1기 인클로징(38호) ○ 전력선 교체 : ASCC 430 x S x 2C, 0.808km(36~39호) ○ 가공지선 설치 : ACSR 97 x S x 1C (37~39호)","2022-09-29 07:00","2022-09-30 18:00","취소","취소","연속"]
[325,"대전세종충남","세종","조치원전의#1 T/L","[송전]154kV 조치원-전의T/L 안전이격거리확보공사","○ 공사구간 : 154kV 조치원-전의T/L No.36~39 ○ 지지물 : 1기 교체(37호), 1기 인클로징(38호) ○ 전력선 교체 : ASCC 430 x S x 2C, 0.808km(36~39호) ○ 가공지선 설치 : ACSR 97 x S x 1C (37~39호)","2022-09-28 07:00","2022-09-29 07:00","취소","취소","연속"]
[326,"대전세종충남","세종","조치원전의#2 T/L","[송전]154kV 조치원-전의T/L 안전이격거리확보공사","○ 공사구간 : 154kV 조치원-전의T/L No.36~39 ○ 지지물 : 1기 교체(37호), 1기 인클로징(38호) ○ 전력선 교체 : ASCC 430 x S x 2C, 0.808km(36~39호) ○ 가공지선 설치 : ACSR 97 x S x 1C (37~39호)","2022-09-26 07:00","2022-09-28 07:00","취소","취소","연속"]
[327,"대전세종충남","직할","송강신일#2 T/L","[지중]22~23년 지중송전설비 위탁정비공사","○ OF케이블 절연유 분석 - J/B#10-1, J/B#10, 신일S/S EBG","2022-09-19 09:00","2022-09-20 18:00","2022-09-19 09:00","2022-09-20 18:00","매일"]
[328,"대전세종충남","직할","송강신일#1 T/L","[송전]154kV 송강-신일T/L OF케이블 선종교체공사","○ 공사구간 : 154kV 송강-신일 #1T/L M/H#4~신일S/S ○ 선종교체 : 154kV OF 2000㎟ → 154kV XLPE 2000㎟ (2.3km)","2022-09-30 09:00","2022-12-15 18:00","취소","취소","연속"]
[329,"대전세종충남","직할","신탄진대청HP T/L","[송전]154kV 신탄진-대청 추락방지시설 설치공사","[송전]154kV 신탄진-대청 추락방지시설 설치공사 - No.42~56, 62 (16기)","2022-09-26 07:00","2022-09-26 18:00","2022-09-26 07:00","2022-09-26 18:00","연속"]
[330,"대전세종충남","천안","불당서천안#1 T/L","22년 170kV GIS 정밀점검 공사","- 154KV GIS 차단부 정밀점검 - 상부모선,쳄버 정밀점검","2022-09-14 09:00","2022-09-16 18:00","2022-09-14 09:00","2022-09-16 18:00","연속"]
[331,"대전세종충남","천안","불당서천안#2 T/L","22년 170kV GIS 정밀점검 공사","- 154KV GIS 차단부 정밀점검 - 상부모선,쳄버 정밀점검 - 메카니즘 점검","2022-09-19 09:00","2022-09-21 18:00","2022-09-19 09:00","2022-09-21 18:00","연속"]
[332,"대전세종충남","천안","신온양한샘#2 T/L","345kV 아산-화성 등 15개 T/L 추락방지시설 설치공사","154kV 신온양-한샘#2T/L No.2~43 추락방지시설(수평) 설치","2022-09-29 08:00","2022-09-30 18:00","2022-09-29 08:00","2022-09-30 18:00","매일"]
[333,"대전세종충남","천안","신온양석곡#1 T/L","345kV 아산-화성 등 15개 T/L 추락방지시설 설치공사","[4회선 병가철탑 안전거리확보] 154kV 신온양-한샘#1T/L No.2~7 추락방지시설(수평) 설치","2022-09-26 08:00","2022-09-26 18:00","2022-09-26 08:00","2022-09-26 18:00","연속"]
[334,"대전세종충남","천안","신온양한샘#1 T/L","345kV 아산-화성 등 15개 T/L 추락방지시설 설치공사","154kV 신온양-한샘#1T/L No.2~43 추락방지시설(수직,수평) 설치","2022-09-26 08:00","2022-09-28 18:00","2022-09-26 08:00","2022-09-28 18:00","매일"]
[335,"대전세종충남","천안","신온양석곡#2 T/L","345kV 아산-화성 등 15개 T/L 추락방지시설 설치공사","[4회선 병가철탑 안전거리확보] 154kV 신온양-한샘#2T/L No.2~7 추락방지시설(수평) 설치","2022-09-29 08:00","2022-09-29 18:00","2022-09-29 08:00","2022-09-29 18:00","연속"]
[336,"대전세종충남","천안","아산합덕#2 T/L","아산S/S 154kV 장기사용GIS 교체공사","Line PT 회로보완(MCCB교체)","2022-09-15 09:00","2022-09-15 12:00","2022-09-17 09:00","2022-09-17 12:00","연속"]
[337,"대전세종충남","천안","아산인주#1 T/L","아산S/S 154kV 장기사용GIS 교체공사","Line PT 회로보완(MCCB교체)","2022-09-15 13:00","2022-09-15 18:00","2022-09-17 13:00","2022-09-17 18:00","연속"]
[338,"대전세종충남","천안","풍세장재#1 T/L","22년 170kV GIS 정밀점검 공사","- 154KV GIS 차단부 정밀점검 - 상부모선,쳄버 정밀점검 - 메카니즘 점검","2022-09-26 07:00","2022-09-28 18:00","2022-09-26 07:00","2022-09-28 18:00","연속"]
[339,"대전세종충남","천안","장재천안#1 T/L","[송전]'22~'23년 천안전력지사 가공송전협력회사 총액공사","ㅇ공사내용 : 애자련보강공사 ㅇ대상철탑 : 154kV 장재-천안 No.7(4회선),8(4회선),10,11 ※ (4회선) 154kV 풍세-장재T/L No.19, 20 ㅇ공사내용 : 애자련보강 (1련 -> 2련) ㅇ사 유 : 고속도로 개설","2022-09-26 07:00","2022-09-28 18:00","2022-09-26 07:00","2022-09-28 18:00","연속"]
[340,"대전세종충남","천안","풍세장재#2 T/L","22년 170kV GIS 정밀점검 공사","- 154KV GIS 차단부 정밀점검 - 상부모선,쳄버 정밀점검 - 메카니즘 점검","2022-09-29 07:00","2022-10-01 18:00","2022-09-29 07:00","2022-10-01 18:00","연속"]
[341,"대전세종충남","천안","장재천안#2 T/L","[송전]'22~'23년 천안전력지사 가공송전협력회사 총액공사","ㅇ공사내용 : 애자련보강공사 ㅇ대상철탑 : 154kV 장재-천안 No.7(4회선),8(4회선),10,11 ※ (4회선) 154kV 풍세-장재T/L No.19, 20 ㅇ공사내용 : 애자련보강 (1련 -> 2련) ㅇ사 유 : 고속도로 개설","2022-09-29 07:00","2022-10-01 18:00","2022-09-29 07:00","2022-10-01 18:00","연속"]
[342,"대전세종충남","천안","서천안탕정#2 T/L","345kV 아산-화성 등 15개 T/L 추락방지시설 설치공사","[4회선 병가철탑 안전거리확보] 154kV 신온양-한샘#1T/L No.42 추락방지시설(수평) 설치","2022-09-28 08:00","2022-09-28 18:00","2022-09-24 08:00","2022-09-24 18:00","연속"]
[343,"대전세종충남","천안","서천안탕정#1 T/L","345kV 아산-화성 등 15개 T/L 추락방지시설 설치공사","[4회선 병가철탑 안전거리확보] 154kV 신온양-한샘#1T/L No.42 추락방지시설(수평) 설치","2022-09-30 08:00","2022-09-30 18:00","2022-09-25 08:00","2022-09-25 18:00","연속"]
[344,"대전세종충남","청양","부여논산#1 T/L","[송전] 전선접속개소 과열발생개소 정비(4회선 안전이격거리 확보)","[송전] 전선접속개소 과열발생개소 정비(4회선 안전이격거리 확보)","2022-09-15 09:00","2022-09-16 18:00","2022-09-15 09:00","2022-09-16 18:00","매일"]
[345,"대전세종충남","청양","청양신풍#1 T/L","청양S/S 철구 추락방지장치 설치","변전소 철구 추락방지장치 설치 - 청양신풍#T/L S/T","2022-09-06 09:00","2022-09-06 18:00","2022-09-06 09:00","2022-09-06 18:00","연속"]
[346,"대전세종충남","청양","청양신풍#2 T/L","청양S/S 철구 추락방지장치 설치","변전소 철구 추락방지장치 설치 - 청양신풍#2T/L S/T","2022-09-05 09:00","2022-09-05 18:00","2022-09-05 09:00","2022-09-05 18:00","연속"]
[347,"대전세종충남","청양","옥산부여#2 T/L","[송전] 전선접속개소 과열발생개소 정비","[송전] 전선접속개소 과열발생개소 정비","2022-09-15 09:00","2022-09-16 18:00","2022-09-15 09:00","2022-09-16 18:00","매일"]
[348,"대전세종충남","청양","청양S/S SEC CB 60610","154kV 차단기 부동작 예방 조작시험","154kV 차단기 부동작 예방 조작시험","2022-09-07 09:00","2022-09-07 14:00","2022-09-07 09:00","2022-09-07 14:00","연속"]
[349,"대전세종충남","청양","청양S/S SEC CB 65660","154kV 차단기 부동작 예방 조작시험","154kV 차단기 부동작 예방 조작시험","2022-09-07 14:00","2022-09-07 18:00","2022-09-07 14:00","2022-09-07 18:00","연속"]
[350,"대전세종충남","천안","아산예산#2 T/L","154kV 예산S/S 미래화공사 ","인출 모선 철거(아산-예산#2T/L)","2022-09-08 08:00","2022-09-08 11:00","2022-09-08 08:00","2022-09-08 11:00","연속"]
[351,"대전세종충남","천안","예산응봉#1 T/L","154kV 예산S/S 미래화공사 ","인출 모선 철거(예산-응봉#1T/L)","2022-09-08 11:00","2022-09-08 14:00","2022-09-08 11:00","2022-09-08 14:00","연속"]
[352,"대전세종충남","천안","예산응봉#2 T/L","154kV 예산S/S 미래화공사 ","인출 모선 철거(예산-응봉#2T/L)","2022-09-08 14:00","2022-09-08 17:00","2022-09-08 14:00","2022-09-08 17:00","연속"]
[353,"전북","군산","군산서군산#2 T/L","154kV 군산-서군산T/L 취약지지물 교체공사","기설철탑 철거 1기 신설철탑 건설 1기","2022-09-17 07:00","2022-09-18 18:00","취소","취소","연속"]
[354,"전북","군산","군산서군산#1 T/L","154kV 군산-서군산T/L 취약지지물 교체공사","기설철탑 철거 1기 신설철탑 건설 1기","2022-09-14 07:00","2022-09-16 18:00","취소","취소","연속"]
[355,"전북","군산","왕궁봉동#2 T/L","154kV 왕궁분기T/L 건설공사","○ 위 치 : (신설) 왕궁분기T/L C/H철탑 ○ 규 모 : ACSR 410㎟ × S × 4C, 0.359km, C/H 1기 ○ 작업내용 : C/H철탑 하단암 발판 보강 작업","2022-09-06 15:00","2022-09-06 19:00","2022-09-06 15:00","2022-09-06 19:00","연속"]
[356,"전북","군산","왕궁봉동#1 T/L","154kV 왕궁분기T/L 건설공사","○ 위 치 : (신설) 왕궁분기T/L C/H철탑 ○ 규 모 : ACSR 410㎟ × S × 4C, 0.359km, C/H 1기 ○ 작업내용 : C/H철탑 하단암 발판 보강 작업","2022-09-05 15:00","2022-09-05 19:00","2022-09-05 15:00","2022-09-05 19:00","연속"]
[357,"전북","김제","남원임실#1 T/L","2022년 김제전력지사 170kV GIS 정밀점검","2022년 김제전력지사 170kV GIS 정밀점검","2022-09-05 09:00","2022-09-06 18:00","2022-09-05 09:00","2022-09-06 18:00","연속"]
[358,"전북","김제","남원임실#2 T/L","2022년 김제전력지사 170kV GIS 정밀점검","2022년 김제전력지사 170kV GIS 정밀점검","2022-09-07 09:00","2022-09-08 18:00","2022-09-14 09:00","2022-09-15 18:00","연속"]
[359,"전북","직할","북전주봉동#1 T/L","22-23 전북직할 변전협력 총액공사","170kV GIS 보통점검","2022-09-01 15:00","2022-09-01 20:00","2022-09-01 15:00","2022-09-01 20:00","연속"]
[360,"전북","직할","북전주봉동#2 T/L","22-23 전북직할 변전협력 총액공사","170kV GIS 조작시험","2022-09-02 15:00","2022-09-02 20:00","2022-09-02 15:00","2022-09-02 20:00","연속"]
[361,"전북","직할","신김제동전주#1 T/L","  345kV 신옥천-신남원 등 8개T/L 추락방지시설 설치공사","154kV 신김제-동전주T/L No.77~83 7기 내용 : 수직 추락방지시설 설치 ","2022-09-05 07:00","2022-09-05 11:00","2022-09-05 07:00","2022-09-05 11:00","연속"]
[362,"전북","직할","진안장수#1 T/L","  345kV 신옥천-신남원 등 8개T/L 추락방지시설 설치공사","154kV 진안-장수T/L No.1~49 2기 내용 : 수직 추락방지시설 설치 ","2022-09-07 07:00","2022-09-07 11:00","취소","취소","연속"]
[363,"전북","직할","무주진안 T/L","  345kV 신옥천-신남원 등 8개T/L 추락방지시설 설치공사","154kV 무주분기T/L No.44 1기 내용 : 수직 추락방지시설 설치 ","2022-09-08 07:00","2022-09-08 11:00","2022-09-08 07:00","2022-09-08 11:00","연속"]
[364,"전북","군산","영등팔봉#1 T/L","군산P/O 154kV  이상 차단기 보통점검 공사","군산P/O 154kV  이상 차단기 보통점검 공사","2022-09-26 09:00","2022-09-26 18:00","2022-09-26 09:00","2022-09-26 18:00","연속"]
[365,"전북","군산","영등팔봉#2 T/L","군산P/O 154kV  이상 차단기 보통점검 공사","군산P/O 154kV  이상 차단기 보통점검 공사","2022-09-27 09:00","2022-09-27 18:00","2022-09-27 09:00","2022-09-27 18:00","연속"]
[366,"전북","군산","서군산소룡#2 T/L","군산P/O 154kV  이상 차단기 보통점검 공사","군산P/O 154kV  이상 차단기 보통점검 공사","2022-09-28 09:00","2022-09-28 18:00","2022-09-28 09:00","2022-09-28 18:00","연속"]
[367,"광주전남","강진","화원진도#1 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- No.1, 2, 4회선구간 작업자 안전이격확보 휴전(상시 가압조건 유지)","2022-09-25 07:00","2022-09-26 18:00","2022-10-15 08:00","2022-10-16 18:00","매일"]
[368,"광주전남","강진","화원진도#1 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- 4회선구간 작업자 안전이격확보 휴전(상시 가압조건 유지)","2022-09-30 07:00","2022-10-01 18:00","2022-10-08 08:00","2022-10-11 18:00","매일"]
[369,"광주전남","강진","화원진도#2 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- 4회선구간 작업자 안전이격확보 휴전(상시 가압조건 유지)","2022-09-25 07:00","2022-09-29 18:00","2022-10-15 08:00","2022-10-19 18:00","매일"]
[370,"광주전남","강진","화원진도#2 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- 4회선구간 작업자 안전이격확보 휴전(상시 가압조건 유지)","2022-09-07 07:00","2022-09-08 18:00","2022-09-07 07:00","2022-09-08 18:00","매일"]
[371,"광주전남","강진","화원진도#1 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- 4회선구간 작업자 안전이격확보 휴전(상시 가압조건 유지)","2022-09-02 07:00","2022-09-06 18:00","2022-09-02 07:00","2022-09-06 18:00","매일"]
[372,"광주전남","강진","진도진도CS#1 T/L","진도C/S 154kV Sh.R 설치공사","170kV GIS Sh.R Bay 전체 무부하가압","2022-09-28 09:00","2022-09-29 16:00","취소","취소","연속"]
[373,"광주전남","강진","진도C/S #1 BUS","진도C/S 154kV Sh.R 설치공사","170kV GIS Sh.R Bay 전체 무부하가압","2022-09-28 09:00","2022-09-29 16:00","취소","취소","연속"]
[374,"광주전남","강진","진도진도CS#1 T/L","진도C/S 154kV Sh.R 설치공사","154kV Sh.R 시험가압","2022-09-29 16:00","2022-09-29 18:00","취소","취소","연속"]
[375,"광주전남","강진","진도C/S #1 BUS","진도C/S 154kV Sh.R 설치공사","154kV Sh.R 시험가압","2022-09-29 16:00","2022-09-29 18:00","취소","취소","연속"]
[376,"광주전남","강진","해남C/S #1 Sh.C CB","22년도 #1HVDC 변환설비 위탁정비공사 연차점검","#1HVDC(해남, 제주C/S) #1,2Pole 변환설비 연차점검 - 필터설비","2022-09-23 09:00","2022-09-30 18:00","2022-09-13 09:00","2022-09-16 18:00","연속"]
[377,"광주전남","강진","해남C/S #1 DTF CB","22년도 #1HVDC 변환설비 위탁정비공사 연차점검","#1HVDC(해남, 제주C/S) #1, 2Pole 변환설비 연차점검 - 필터설비","2022-09-23 09:00","2022-09-30 18:00","2022-09-23 09:00","2022-09-30 18:00","연속"]
[378,"광주전남","강진","해남C/S #2 Sh.C CB","22년도 #1HVDC 변환설비 위탁정비공사 연차점검","#1HVDC(해남, 제주C/S) #1,2Pole 변환설비 연차점검 - 필터설비","2022-09-23 09:00","2022-09-30 18:00","2022-09-13 09:00","2022-09-16 18:00","연속"]
[379,"광주전남","강진","해남C/S #1 HPF CB","22년도 #1HVDC 변환설비 위탁정비공사 연차점검","#1HVDC(해남, 제주C/S) #1,2Pole 변환설비 연차점검 - 필터설비","2022-09-23 09:00","2022-09-30 18:00","2022-09-23 09:00","2022-09-30 18:00","연속"]
[380,"광주전남","강진","해남C/S #2 HPF CB","22년도 #1HVDC 변환설비 위탁정비공사 연차점검","#1HVDC(해남, 제주C/S) #1,2Pole 변환설비 연차점검 - 필터설비","2022-09-23 09:00","2022-09-30 18:00","2022-09-23 09:00","2022-09-30 18:00","연속"]
[381,"광주전남","강진","해남C/S #2 DTF CB","22년도 #1HVDC 변환설비 위탁정비공사 연차점검","#1HVDC(해남, 제주C/S) #1,2Pole 변환설비 연차점검 - 필터설비","2022-09-23 09:00","2022-09-30 18:00","2022-09-23 09:00","2022-09-30 18:00","연속"]
[382,"광주전남","강진","제주해남HVDC(1연계선) #1 Pole CB","22년도 #1HVDC 변환설비 위탁정비공사 연차점검","#1HVDC(해남, 제주C/S) #1Pole 변환설비 연차점검 -Thyristor Valve C.Tr, AC Filter, 공조설비, 냉각설비, 제어설비 등","2022-09-20 09:00","2022-09-30 18:00","2022-09-20 09:00","2022-09-30 18:00","연속"]
[383,"광주전남","강진","제주해남HVDC(1연계선) #2 Pole CB","22년도 #1HVDC 변환설비 위탁정비공사 연차점검","#1HVDC(해남, 제주C/S) #2Pole 변환설비 연차점검 -Thyristor Valve C.Tr, AC Filter, 공조설비, 냉각설비, 제어설비 등","2022-09-23 09:00","2022-10-03 18:00","2022-09-23 09:00","2022-10-03 18:00","연속"]
[384,"광주전남","강진","해남해남CS#1 T/L","22~23년 송전협력회사 총액공사","대상선로 : 남창-해남CS No.1~19 작업명 : 수직 및 수평추락방지장치 설치 공사업체 : (유)신세계전력","2022-09-26 09:00","2022-09-27 18:00","2022-09-20 09:00","2022-09-25 18:00","매일"]
[385,"광주전남","강진","남창해남CS#1 T/L","22~23년 송전협력회사 총액공사","대상선로 : 남창-해남CS No.1~19 작업명 : 수직 및 수평추락방지장치 설치 공사업체 : (유)신세계전력","2022-09-26 09:00","2022-09-27 18:00","2022-09-24 09:00","2022-09-25 18:00","매일"]
[386,"광주전남","강진","해남해남CS#2 T/L","22~23년 송전협력회사 총액공사","대상선로 : 남창-해남CS No.1~19 작업명 : 수직 및 수평추락방지장치 설치 공사업체 : (유)신세계전력","2022-09-28 09:00","2022-09-29 18:00","2022-09-26 09:00","2022-09-30 18:00","매일"]
[387,"광주전남","강진","남창해남CS#2 T/L","22~23년 송전협력회사 총액공사","대상선로 : 남창-해남CS No.1~19 작업명 : 수직 및 수평추락방지장치 설치 공사업체 : (유)신세계전력","2022-09-28 09:00","2022-09-29 18:00","2022-09-26 09:00","2022-09-27 18:00","매일"]
[388,"광주전남","강진","삼호화원#2 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- No. 4회선구간 안전이격화보 휴전(0.1 ~ 1호),","2022-09-06 07:00","2022-09-06 18:00","2022-09-06 07:00","2022-09-06 18:00","연속"]
[389,"광주전남","강진","삼호화원#1 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- 4회선구간 안전이격화보 휴전(1 ~ 2호),","2022-09-02 07:00","2022-09-03 18:00","2022-09-02 07:00","2022-09-03 18:00","매일"]
[390,"광주전남","강진","삼호화원#1 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- No. 4회선구간 안전이격화보 휴전(1 ~ 2호),","2022-09-25 07:00","2022-09-26 18:00","2022-10-15 08:00","2022-10-19 18:00","매일"]
[391,"광주전남","강진","삼호화원#1 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- No. 4회선구간 안전이격화보 휴전(0.1 ~ 1호),","2022-09-29 07:00","2022-09-29 18:00","2022-10-19 08:00","2022-10-19 18:00","연속"]
[392,"광주전남","광주","계림S/S SEC CB 61600","22~23년 광주전력지사 변전협력회사 총액공사","계림S/S 154kV #61-60 SEC GIS 전자변 교체","2022-09-13 09:00","2022-09-13 18:00","2022-09-13 09:00","2022-09-13 18:00","연속"]
[393,"광주전남","광주","계림S/S SEC CB 66650","22~23년 광주전력지사 변전협력회사 총액공사","계림S/S 154kV #66-65 SEC GIS 전자변 교체","2022-09-14 09:00","2022-09-14 18:00","2022-09-14 09:00","2022-09-14 18:00","연속"]
[394,"광주전남","광주","계림S/S CB 6200","22~23년 광주전력지사 변전협력회사 총액공사","계림S/S 154kV #61-66 BUS TIE GIS 전자변 교체","2022-09-15 09:00","2022-09-15 18:00","2022-09-15 09:00","2022-09-15 18:00","연속"]
[395,"광주전남","광주","담양일곡#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","담양S/S 담양-일곡#2T/L CVT 보통점검(비상시 즉시가압 불가)","2022-09-05 09:00","2022-09-05 18:00","2022-09-05 09:00","2022-09-05 18:00","연속"]
[396,"광주전남","광주","담양일곡#1 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 담양-김제T/L, #1M.Tr, #1B/T, #1PT","2022-09-24 15:00","2022-09-25 15:00","취소","취소","연속"]
[397,"광주전남","광주","정공담양 T/L","22~23년 광주전력지사 변전협력회사 총액공사","담양S/S 정공-담양T/L CVT 보통점검(비상시 즉시가압 불가)","2022-09-07 09:00","2022-09-07 18:00","2022-09-07 09:00","2022-09-07 18:00","연속"]
[398,"광주전남","광주","담양일곡#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","담양S/S 담양-일곡#1T/L CVT 보통점검(비상시 즉시가압 불가)","2022-09-06 09:00","2022-09-06 18:00","2022-09-06 09:00","2022-09-06 18:00","연속"]
[399,"광주전남","광주","담양S/S #2 BUS","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 담양-김제T/L, #1M.Tr, #1B/T, #1PT","2022-09-19 09:00","2022-09-20 18:00","취소","취소","연속"]
[400,"광주전남","광주","담양김제 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 담양-김제T/L, #1M.Tr, #1B/T, #1PT","2022-09-19 09:00","2022-10-02 18:00","취소","취소","연속"]
[401,"광주전남","광주","담양김제 T/L","22~23년 광주전력지사 변전협력회사 총액공사","담양S/S 담양-김제T/L CVT 보통점검(비상시 즉시가압 불가)","2022-09-08 09:00","2022-09-08 18:00","2022-09-08 09:00","2022-09-08 18:00","연속"]
[402,"광주전남","광주","담양일곡#1 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 담양-김제T/L, #1M.Tr, #1B/T, #1PT","2022-09-30 09:00","2022-10-01 18:00","취소","취소","연속"]
[403,"광주전남","광주","담양S/S #2 BUS","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 담양-김제T/L, #1M.Tr, #1B/T, #1PT","2022-09-26 09:00","2022-10-01 18:00","취소","취소","연속"]
[404,"광주전남","광주","신화순화순#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","신화순S/S 신화순-화순#2T/L LA 점검 화순S/S 170kV GIS 보통점검 -비상시 즉시가압 불가-","2022-09-16 09:00","2022-09-16 18:00","2022-09-16 09:00","2022-09-16 18:00","연속"]
[405,"광주전남","광주","신화순화순#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","신화순S/S 신화순-화순#1T/L PT,LA 점검 화순S/S 170kV GIS 보통점검 -비상시 즉시가압 불가-","2022-09-14 09:00","2022-09-14 18:00","2022-09-14 09:00","2022-09-14 18:00","연속"]
[406,"광주전남","광주","일곡비아#2 T/L","154kV 일곡-비아 T/L 지중화공사","가. 설치분 1) 구 간 : 신설 맨홀#5 ∼ 일곡S/S 2) 선종/길이 : 154kV XLPE 2,000㎟ × 2C(D) × 0.374km 3) 케 이 블 : 포설 1구간, 접속 : 2개소 (PMIJ×1개소, 종단접속×1개소) 나. 철거분 1) 구 간 : 기설 맨홀#1 ∼ 일곡C/T 13호 2) 선종/길이 : 154kV XLPE 2,000㎟ × 2C(D) × 0.93km","2022-09-01 09:00","2022-09-30 18:00","취소","취소","연속"]
[407,"광주전남","목포","화원안좌#2 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- 전선교체공사 1~47호(가공 : 송전운영부, 해저케이블 : 중부건설본부)","2022-09-24 07:00","2022-10-13 18:00","2022-10-03 08:00","2022-10-22 18:00","연속"]
[408,"광주전남","목포","화원안좌#1 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- 전선교체공사 1~47호(가공 : 송전운영부, 해저케이블 : 중부건설본부)","2022-09-01 12:00","2022-09-23 18:00","2022-09-01 12:00","2022-09-23 18:00","연속"]
[409,"광주전남","목포","엄다무안햇빛#2 T/L","154KV 엄다-운남 지중T/L 증설 관로공사","154KV 엄다-운남 지중T/L 증설 관로공사 - 관로공사 : 관로신설(76.8m), EBA 기초, 울타리 설치 및 도로포장","2022-09-19 09:00","2022-09-21 18:00","2022-09-19 09:00","2022-09-21 18:00","매일"]
[410,"광주전남","목포","엄다무안햇빛#1 T/L","154KV 엄다-운남 지중T/L 증설 관로공사","154KV 엄다-운남 지중T/L 증설 관로공사 - 관로공사 : 관로신설(76.8m), EBA 기초, 울타리 설치 및 도로포장","2022-09-14 09:00","2022-09-16 18:00","2022-09-14 09:00","2022-09-16 18:00","매일"]
[411,"광주전남","순천","광양순천#1 T/L","(주)세니온 154kV 송전선로 보호 IED 성능개선","(주)세니온 154kV 송전선로 보호 IED 성능개선","2022-09-15 09:00","2022-09-15 18:00","2022-09-15 09:00","2022-09-15 18:00","연속"]
[412,"광주전남","순천","벌교고흥#1 T/L","345kV 신강진-광양등 29개T/L 추락방지시설 설치공사","목적 : 철탑승탑자의 추락방지를 위한 추락방지시설 설치 내용 : 수직, 수평 추락방지 와이어 설치","2022-09-12 08:00","2022-09-30 18:00","2022-09-13 08:00","2022-09-28 18:00","매일"]
[413,"광주전남","순천","율촌여수산단#1 T/L","2022년 순천전력지사 170kV 정밀점검공사","GIS 정밀점검","2022-09-26 09:00","2022-09-27 18:00","취소","취소","연속"]
[414,"광주전남","순천","율촌여수산단#2 T/L","2022년 순천전력지사 170kV 정밀점검공사","GIS 정밀점검","2022-09-28 09:00","2022-09-29 18:00","취소","취소","연속"]
[415,"광주전남","순천","여수TP용성#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","용성S/S 여수TP-용성#2T/L LA(A, B, C) 하자점검 여수화력S/Y 여수TP-용성#2T/L GIS 보통점검 및 상시여자 보조계전기 교체","2022-09-29 10:00","2022-09-29 18:00","취소","취소","연속"]
[416,"광주전남","순천","여수TP여천#1 T/L","2022년 순천전력지사 170kV 정밀점검공사","GIS 정밀점검","2022-09-13 09:00","2022-09-14 18:00","취소","취소","연속"]
[417,"광주전남","순천","여수TP화치#1 T/L","'22-23년 순천전력지사 변전정비 총액공사","154kV 송전선로 보호반 대체","2022-09-14 09:00","2022-09-16 18:00","취소","취소","연속"]
[418,"광주전남","순천","여수TP여천#2 T/L","2022년 순천전력지사 170kV 정밀점검공사","GIS 정밀점검","2022-09-15 09:00","2022-09-16 18:00","취소","취소","연속"]
[419,"광주전남","순천","호남TP여수TP#1 T/L","2022년 순천전력지사 170kV 정밀점검공사","GIS 정밀점검","2022-09-19 09:00","2022-09-20 18:00","취소","취소","연속"]
[420,"광주전남","순천","호남TP여수TP#2 T/L","2022년 순천전력지사 170kV 정밀점검공사","GIS 정밀점검","2022-09-21 09:00","2022-09-22 18:00","취소","취소","연속"]
[421,"광주전남","순천","여수TP용성#1 T/L","대한제 열경화공법 EBG 보강공사","여수TP-용성#1 T/L EBG 해체점검(6상)","2022-09-21 09:00","2022-09-29 18:00","취소","취소","연속"]
[422,"광주전남","순천","여수T/P CB 6100","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #60-65 BUS-Pro 보호반 대체","2022-09-26 09:00","2022-09-29 18:00","2022-09-26 09:00","2022-09-29 18:00","연속"]
[423,"광주전남","순천","여수T/P SEC CB 60610","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #60-65 BUS-Pro 보호반 대체","2022-09-26 09:00","2022-09-27 18:00","2022-09-26 09:00","2022-09-27 18:00","연속"]
[424,"광주전남","순천","여수T/P #60 BUS","2022년 순천전력지사 170kV 정밀점검공사","GIS 정밀점검","2022-09-26 09:00","2022-09-27 18:00","취소","취소","연속"]
[425,"광주전남","순천","여수T/P SEC CB 65660","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #60-65 BUS-Pro 보호반 대체","2022-09-28 09:00","2022-09-29 18:00","2022-09-28 09:00","2022-09-29 18:00","연속"]
[426,"광주전남","순천","여수T/P #65 BUS","2022년 순천전력지사 170kV 정밀점검공사","GIS 정밀점검","2022-09-28 09:00","2022-09-29 18:00","취소","취소","연속"]
[427,"광주전남","순천","여수TP용성#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","용성S/S 여수TP-용성#1T/L LA(A, B, C) 하자점검","2022-09-28 09:00","2022-09-28 14:00","취소","취소","연속"]
[428,"광주전남","순천","율촌화치#1 T/L","2022년 순천전력지사 170kV 정밀점검공사","GIS 정밀점검","2022-09-19 09:00","2022-09-20 18:00","취소","취소","연속"]
[429,"광주전남","순천","율촌화치#2 T/L","2022년 순천전력지사 170kV 정밀점검공사","GIS 정밀점검","2022-09-21 09:00","2022-09-22 18:00","취소","취소","연속"]
[430,"대구","경산","대구청도#2 T/L","청도S/S 154kV GIS 교체공사","TEST선로","2022-09-27 18:00","2022-09-28 09:30","2022-09-27 18:00","2022-09-28 09:30","연속"]
[431,"대구","경산","대구청도#1 T/L","청도S/S 154kV GIS 교체공사","TEST선로","2022-09-22 18:00","2022-09-23 09:30","2022-09-22 18:00","2022-09-23 09:30","연속"]
[432,"대구","달성","다사달서 T/L","다사-달서T/L 보호반 대체","다사-달서T/L 보호반 대체","2022-09-21 09:00","2022-09-23 18:00","2022-09-21 09:00","2022-09-23 18:00","연속"]
[433,"대구","달성","대구청도#1 T/L","2022년 가공송전 순시점검 위탁공사","154kV 대구-청도T/L No.17~20 초기점검","2022-09-15 09:00","2022-09-15 14:00","2022-09-15 09:00","2022-09-15 14:00","연속"]
[434,"대구","달성","대구청도#2 T/L","2022년 가공송전 순시점검 위탁공사","154kV 대구-청도T/L No.17~20 초기점검","2022-09-16 09:00","2022-09-16 14:00","2022-09-16 09:00","2022-09-16 14:00","연속"]
[435,"대구","칠곡","서대구칠곡#2 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구-칠곡#2T/L 부하전환(철구 → GIS)","2022-09-19 08:30","2022-09-21 18:00","2022-09-19 08:30","2022-09-21 18:00","연속"]
[436,"대구","칠곡","서대구칠곡#1 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구-칠곡#1T/L 부하전환(철구 → GIS)","2022-09-29 08:30","2022-10-01 18:00","2022-09-29 08:30","2022-10-01 18:00","연속"]
[437,"대구","칠곡","서대구남인동#2 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구-남인동#2T/L, #3M.Tr 부하전환(철구 → GIS)","2022-09-26 08:30","2022-09-28 18:00","2022-09-26 08:30","2022-09-28 18:00","연속"]
[438,"대구","칠곡","북대구연락#1 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","북대구연락#1,2T/L 부하전환(철구 → GIS)","2022-09-22 08:30","2022-09-24 18:00","2022-09-22 08:30","2022-09-24 18:00","연속"]
[439,"대구","칠곡","북대구연락#2 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","북대구연락#1,2T/L 부하전환(철구 → GIS)","2022-09-22 08:30","2022-09-24 18:00","2022-09-22 08:30","2022-09-24 18:00","연속"]
[440,"대구","칠곡","서대구남인동#1 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구-남인동#1T/L, #4M.Tr 부하전환(철구 → GIS)","2022-09-13 08:30","2022-09-16 18:00","2022-09-13 08:30","2022-09-16 18:00","연속"]
[441,"대구","포항","건천천북#2 T/L","건천S/S 건천-천북#2TL 677 GIS 조작시험","건천S/S 건천-천북#2TL 677 GIS 조작시험","2022-09-19 09:00","2022-09-19 18:00","2022-09-19 09:00","2022-09-19 18:00","연속"]
[442,"경북","구미","상주보은 T/L","154kV 화동S/S 건설공사","○ 화동S/S 보호반 이설(상주→화동) 및 시험 ○ 화동분기T/L OPGW 및 구내통신설비 설치 및 시험 ○ 화동S/S 무부하 가압, 사용전검사, 실부하 가압","2022-09-15 09:00","2022-09-24 18:00","2022-09-15 09:00","2022-09-24 18:00","연속"]
[443,"경북","구미","청리상주#1 T/L","2022-23년도 구미전력지사 가공송전정비 협력회사 총액공사","154kV 청리-상주T/L 추락방지시설 설치공사 총 17기(1, 41~54, 56~57호)","2022-09-19 08:00","2022-09-21 18:00","2022-09-19 08:00","2022-09-21 18:00","매일"]
[444,"경북","구미","청리상주#2 T/L","2022-23년도 구미전력지사 가공송전정비 협력회사 총액공사","154kV 청리-상주T/L 추락방지시설 설치공사 총 17기(1, 41~54, 56~57호)","2022-09-22 08:00","2022-09-23 18:00","2022-09-22 08:00","2022-09-23 18:00","매일"]
[445,"경북","영주","신영주영주#1 T/L","22-23년 영주전력지사 변전협력회사 총액공사","154kV GIS 초기점검","2022-09-20 09:00","2022-09-20 18:00","2022-09-20 09:00","2022-09-20 18:00","연속"]
[446,"경북","영주","신영주영주#2 T/L","22-23년 영주전력지사 변전협력회사 총액공사","154kV GIS 초기점검","2022-09-21 09:00","2022-09-21 18:00","2022-09-21 09:00","2022-09-21 18:00","연속"]
[447,"경북","직할","안동동안동#2 T/L","22~23년 경북본부 직할 변전협력회사 총액공사","GIS 조작시험","2022-09-20 14:00","2022-09-20 18:00","2022-09-20 14:00","2022-09-20 18:00","연속"]
[448,"경북","직할","안동동안동#1 T/L","22~23년 경북본부 직할 변전협력회사 총액공사","GIS 조작시험","2022-09-20 10:00","2022-09-20 14:00","2022-09-20 10:00","2022-09-20 14:00","연속"]
[449,"경북","직할","풍산안동CC#2 T/L","풍산S/S #3M.Tr 최초가압","○ 풍산S/S #3M.Tr 최초가압","2022-09-13 13:00","2022-09-14 13:00","2022-09-13 13:00","2022-09-14 13:00","연속"]
[450,"부산울산","동부산","구서노포#1 T/L","직할 지중송전 대한전선製 열경화공법 EBG 보강공사","EBG 가스채취밸브 설치 및 스프링유닛 압축길이 조정","2022-09-19 09:00","2022-09-23 18:00","2022-09-19 09:00","2022-09-23 18:00","연속"]
[451,"부산울산","동부산","구서노포#2 T/L","직할 지중송전 대한전선製 열경화공법 EBG 보강공사","EBG 가스채취밸브 설치 및 스프링유닛 압축길이 조정","2022-09-26 09:00","2022-09-30 18:00","2022-09-26 09:00","2022-10-05 18:00","연속"]
[452,"부산울산","북부산","북부산미남#1 T/L","2022년 북부산전력지사 154kV GIS정밀점검","미남S/S 154kV 북부산-미남#1T/L GIS 정밀점검","2022-09-26 08:00","2022-09-27 18:00","2022-09-26 08:00","2022-09-27 18:00","연속"]
[453,"부산울산","북부산","북부산미남#2 T/L","154kV 북부산-미남T/L OPGW 증설공사","1. 북부산-미남간 OPGW 증설 : 5.9km 2. OPGW 코아접속 및 시험","2022-09-21 08:00","2022-09-25 18:00","2022-09-21 08:00","2022-09-25 18:00","연속"]
[454,"부산울산","북부산","물금삼랑진PP#2 T/L","2022-2023년 북부산전력지사 가공송전 협력회사 총액공사","공종 : 애자교체(불량애자)","2022-09-13 08:00","2022-09-14 18:00","2022-09-13 08:00","2022-09-14 18:00","연속"]
[455,"부산울산","북부산","학장개금#1 T/L","2022 북부산전력지사 154kV GIS 정밀점검","학장S/S 154kV 학장-개금#1T/L GIS 정밀점검","2022-09-29 08:00","2022-09-30 18:00","2022-09-29 08:00","2022-09-30 18:00","연속"]
[456,"부산울산","서부산","서부산다대#2 T/L","을숙도지하차도 지장 지중송전선로 이설공사","을숙도대교~장림고개간 지하차도 지장 지중송전선로 이설","2022-09-13 09:00","2022-09-30 18:00","2022-09-13 09:00","2022-09-30 18:00","매일"]
[457,"부산울산","서부산","서부산다대#1 T/L","을숙도지하차도 지장 지중송전선로 이설공사","을숙도대교~장림고개간 지하차도 지장 지중송전선로 이설","2022-09-13 09:00","2022-09-30 18:00","2022-09-13 09:00","2022-09-30 18:00","매일"]
[458,"부산울산","서부산","신김해지사#1 T/L","지사S/S 154kV 신김해-지사#1T/L GIS 보통점검","지사S/S 154kV 신김해-지사#1T/L GIS 보통점검","2022-09-27 09:00","2022-09-27 18:00","2022-09-27 09:00","2022-09-27 18:00","연속"]
[459,"부산울산","서부산","신김해지사#2 T/L","지사S/S 154kV 신김해-지사#2T/L GIS 보통점검","지사S/S 154kV 신김해-지사#2T/L GIS 보통점검","2022-09-28 09:00","2022-09-28 18:00","2022-09-28 09:00","2022-09-28 18:00","연속"]
[460,"부산울산","울산","남울산처용#1 T/L","154kV 추락방지장치 설치 공사","154kV 남울산-처용 수직,수평 추락방지장치 설치(No.1,6~18)","2022-09-15 07:30","2022-09-16 18:00","2022-09-15 07:30","2022-09-16 18:00","연속"]
[461,"부산울산","울산","남울산용연#1 T/L","154kV 추락방지장치 설치 공사","154kV 남울산-용연 #1 수직,수평 추락방지장치 설치(No.1~3)","2022-09-30 07:30","2022-09-30 18:00","2022-09-30 07:30","2022-09-30 18:00","연속"]
[462,"부산울산","울산","동울산산하#1 T/L","154kV 추락방지장치 설치 공사(안전이격)","산하분기(산하-효문) 추락방지장치 설치 안전이격 휴전","2022-09-26 07:30","2022-09-26 18:00","2022-09-26 07:30","2022-09-26 18:00","연속"]
[463,"부산울산","울산","두왕울산#1 T/L","154kV 추락방지장치 설치공사","두왕-울산 #1 수직, 수평 추락방지장치 설치","2022-09-05 07:30","2022-09-07 18:00","2022-09-05 07:30","2022-09-07 18:00","연속"]
[464,"부산울산","울산","반천언양#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","송전철탑 추락방지장치(수평) 및 피뢰기 설치","2022-09-02 07:00","2022-09-02 18:00","2022-09-02 07:00","2022-09-02 18:00","연속"]
[465,"부산울산","울산","반천언양#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","송전철탑 추락방지장치(수평) 및 피뢰기 설치","2022-09-14 07:00","2022-09-14 18:00","2022-09-14 07:00","2022-09-14 18:00","연속"]
[466,"부산울산","울산","산하효문#1 T/L","154kV 추락방지장치 설치 공사","154KV 산하분기(산하-효문) 수직,수평 추락방지장치 설치(No.10~32)","2022-09-26 07:30","2022-09-29 18:00","2022-09-26 07:30","2022-09-29 18:00","연속"]
[467,"부산울산","울산","성암울산TP#1 T/L","154kV 추락방지장치 설치 공사","154kV 성암-울산tp #1 수직,수평 추락방지장치 설치(No.1~9)","2022-09-23 07:30","2022-09-23 18:00","2022-09-23 07:30","2022-09-23 18:00","연속"]
[468,"부산울산","울산","옥동외동#2 T/L","2022~2023년 울산전력지사 가공송전협력회사 총액공사","-국산애자교체 : No.6,7","2022-09-22 08:00","2022-09-23 18:00","2022-09-22 08:00","2022-09-23 18:00","연속"]
[469,"부산울산","울산","옥동외동#1 T/L","2022~2023년 울산전력지사 가공송전협력회사 총액공사","-국산애자교체 : No.1,7","2022-09-19 08:00","2022-09-21 18:00","2022-09-19 08:00","2022-09-21 18:00","연속"]
[470,"부산울산","울산","온산처용#1 T/L","154kV 추락방지장치 설치공사","온산-처용#1 수직, 수평 추락방지장치 설치(No.11~20)","2022-09-13 07:30","2022-09-14 18:00","취소","취소","연속"]
[471,"부산울산","울산","울산영남TP#1 T/L","154kV 추락방지장치 설치 공사","154kV 울산-영남tp #1 수직,수평 추락방지장치 설치(No.1~21)","2022-09-19 07:30","2022-09-22 18:00","2022-09-19 07:30","2022-09-22 18:00","연속"]
[472,"부산울산","울산","신울산웅촌#2 T/L","2022~2023년 울산전력지사 가공송전협력회사 총액공사","-국산애자교체 : No.12","2022-09-27 08:00","2022-09-27 18:00","2022-09-27 08:00","2022-09-27 18:00","연속"]
[473,"부산울산","울산","신울산웅촌#1 T/L","2022~2023년 울산전력지사 가공송전협력회사 총액공사","-국산애자교체 : No.11","2022-09-26 08:00","2022-09-26 18:00","2022-09-26 08:00","2022-09-26 18:00","연속"]
[474,"부산울산","울산","직동반천#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","송전철탑 추락방지장치(수평) 및 피뢰기 설치","2022-09-13 07:00","2022-09-18 18:00","2022-09-13 07:00","2022-09-18 18:00","연속"]
[475,"부산울산","울산","직동반천#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","송전철탑 추락방지장치(수평) 및 피뢰기 설치","2022-09-01 07:00","2022-09-07 18:00","2022-09-01 07:00","2022-09-07 18:00","연속"]
[476,"부산울산","울산","울주직동#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","송전철탑 추락방지장치(수평) 및 피뢰기 설치","2022-09-03 07:00","2022-09-07 18:00","2022-09-03 07:00","2022-09-07 18:00","연속"]
[477,"부산울산","울산","울주직동#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","송전철탑 추락방지장치(수평) 및 피뢰기 설치","2022-09-15 07:00","2022-09-18 18:00","2022-09-15 07:00","2022-09-18 18:00","연속"]
[478,"부산울산","울산","온산처용#2 T/L","처용S/S 154kV 대한유화T/L GIS 대체공사","154kV GIS 50kA 2,000A 1CCT 대체","2022-09-27 18:00","2022-09-28 18:00","2022-09-27 18:00","2022-09-28 18:00","연속"]
[479,"부산울산","울산","온산처용#2 T/L","처용S/S 154kV 대한유화T/L GIS 대체공사","154kV GIS 50kA 2,000A 1CCT 대체","2022-09-23 18:00","2022-09-23 19:00","2022-09-23 18:00","2022-09-23 19:00","연속"]
[480,"부산울산","직할","부산수정#2 T/L","21-22년 서부산전력지사 지중송전위탁 정비공사","OF케이블 절연유 시료채취 작업","2022-09-17 09:00","2022-09-18 18:00","2022-09-17 09:00","2022-09-18 18:00","연속"]
[481,"부산울산","직할","부산수정#1 T/L","21-22년 서부산전력지사 지중송전위탁 정비공사","OF케이블 절연유 시료채취 작업","2022-09-03 09:00","2022-09-04 18:00","2022-09-03 09:00","2022-09-04 18:00","연속"]
[482,"경남","직할","창공월림#1 T/L","154kV 창공-월림T/L 4-5호 인근 공사현장 안전확보","154kV 창공-월림T/L 4-5호 송전선로 직하 공장신축 공사현장 안전확보(민원)","2022-09-15 09:00","2022-10-15 18:00","2022-09-15 09:00","2022-10-15 18:00","연속"]
[483,"경남","직할","창공월림#2 T/L","154kV 창공-월림T/L 4-5호 인근 공사현장 안전확보","154kV 창공-월림T/L 4-5호 송전선로 직하 공장신축 공사현장 안전확보(민원)","2022-09-15 09:00","2022-10-15 18:00","2022-09-15 09:00","2022-10-15 18:00","연속"]
[484,"경남","진주","중리가야#2 T/L","가야S/S 중리-가야#2T/L GIS 정밀점검","가야S/S 중리-가야#2T/L GIS 정밀점검","2022-09-03 09:00","2022-09-04 18:00","2022-09-03 09:00","2022-09-04 18:00","연속"]
[485,"경남","진주","하동개양#2 T/L","154kV 하동-개양T/L 추락방지장치 설치","□ 휴전설비 : 하동-개양, 하동-하동TP, 태금-하동, 하동-남해T/L □ 설치대상 ○ 154kV 하동-개양T/L No.6~108호(104기) ☞ 6회선 철탑(No.88) 설치시 하동-하동TP, 태금-하동, 하동-남해T/L 안전작업거리확보 휴전필요 ☞ 4회선 철탑(No.89~108) 설치시 안전작업거리확보를 위한 하동-개양#1,2T/L동시휴전 필요","2022-09-19 07:00","2022-09-25 18:00","2022-09-19 07:00","2022-09-25 18:00","매일"]
[486,"경남","진주","하동개양#2 T/L","154kV 하동-개양T/L 추락방지장치 설치","□ 휴전설비 : 하동-개양, 하동-하동TP, 태금-하동, 하동-남해T/L □ 설치대상 ○ 154kV 하동-개양T/L No.6~108호(104기) ☞ 6회선 철탑(No.88) 설치시 하동-하동TP, 태금-하동, 하동-남해T/L 안전작업거리확보 휴전필요 ☞ 4회선 철탑(No.89~108) 설치시 안전작업거리확보를 위한 하동-개양#1,2T/L동시휴전 필요","2022-09-30 07:00","2022-10-03 18:00","2022-09-30 07:00","2022-10-03 18:00","매일"]
[487,"경남","진주","하동개양#1 T/L","154kV 하동-개양T/L 추락방지장치 설치","□ 휴전설비 : 하동-개양, 하동-하동TP, 태금-하동, 하동-남해T/L □ 설치대상 ○ 154kV 하동-개양T/L No.6~108호(104기) ☞ 6회선 철탑(No.88) 설치시 하동-하동TP, 태금-하동, 하동-남해T/L 안전작업거리확보 휴전필요 ☞ 4회선 철탑(No.89~108) 설치시 안전작업거리확보를 위한 하동-개양#1,2T/L동시휴전 필요","2022-09-24 07:00","2022-10-03 18:00","2022-09-24 07:00","2022-10-03 18:00","매일"]
[488,"경남","진주","가야사봉#1 T/L","사봉S/S 가야-사봉#1T/L GIS 보통점검","사봉S/S 가야-사봉#1T/L GIS 보통점검","2022-09-26 10:00","2022-09-26 18:00","2022-09-14 10:00","2022-09-14 18:00","연속"]
[489,"경남","진주","의령산청 T/L","산청S/S 의령-산청T/L LA 교체","[병행] 의령S/S 의령-산청T/L GIS조작, LA하자, PT보통점검","2022-09-24 10:00","2022-09-24 18:00","2022-09-24 10:00","2022-09-24 18:00","연속"]
[490,"경남","진주","산청함양 T/L","산청S/S 산청-함양T/L LA 교체","산청S/S 산청-함양T/L LA 교체","2022-09-17 10:00","2022-09-17 18:00","2022-09-17 10:00","2022-09-17 18:00","연속"]
[491,"경남","진주","광양하동#2 T/L","154kV 하동-개양T/L 추락방지장치 설치","□ 휴전설비 : 광양-하동T/L □ 설치대상 ○ 154kV 하동-개양T/L No.89~108호(20기) ☞ 4회선 철탑(No.89~108) 설치시 안전작업거리확보를 위한 광양-하동#1,2T/L동시휴전 필요","2022-09-17 07:00","2022-09-18 18:00","2022-09-17 07:00","2022-09-18 18:00","매일"]
[492,"경남","진주","광양하동#1 T/L","154kV 하동-개양T/L 추락방지장치 설치","□ 휴전설비 : 광양-하동T/L □ 설치대상 ○ 154kV 하동-개양T/L No.89~108호(20기) ☞ 4회선 철탑(No.89~108) 설치시 안전작업거리확보를 위한 광양-하동#1,2T/L동시휴전 필요","2022-09-17 07:00","2022-09-18 18:00","2022-09-17 07:00","2022-09-18 18:00","매일"]
[493,"경남","진주","하동하동화력 T/L","154kV 하동-개양T/L 추락방지장치 설치","□ 휴전설비 : 하동-개양, 하동-하동TP, 태금-하동, 하동-남해T/L □ 설치대상 ○ 154kV 하동-개양T/L No.6~108호(104기) ☞ 6회선 철탑(No.88) 설치시 하동-하동TP, 태금-하동, 하동-남해T/L 안전작업거리확보 휴전필요 ☞ 4회선 철탑(No.89~108) 설치시 안전작업거리확보를 위한 하동-개양#1,2T/L동시휴전 필요","2022-09-24 07:00","2022-09-24 13:00","2022-09-24 07:00","2022-09-24 13:00","연속"]
[494,"경남","통영","신고성거제#1 T/L","거제S/S 인출송전선로 지중이설공사 임시선로 구성","○ 임시선로 구성 (5회선, 임시철탑 5기 신설) - 통영-거제T/L 69호~거제S/S (0.8km, HSATCIR/AW330*S*2C) - 신고성-거제T/L 196호~거제S/S (0.8km, HSATCIR/AW410*S*2C) - 삼성조선T/L 3호~거제 (0.8km, HSATCIR/AW330*S*1C)","2022-09-25 07:00","2022-09-25 18:00","2022-09-25 07:00","2022-09-25 18:00","연속"]
[495,"경남","통영","신고성거제#2 T/L","거제S/S 인출송전선로 지중이설공사 임시선로 구성","○ 임시선로 구성 (5회선, 임시철탑 5기 신설) - 통영-거제T/L 69호~거제S/S (0.8km, HSATCIR/AW330*S*2C) - 신고성-거제T/L 196호~거제S/S (0.8km, HSATCIR/AW410*S*2C) - 삼성조선T/L 3호~거제 (0.8km, HSATCIR/AW330*S*1C)","2022-09-24 07:00","2022-09-24 18:00","2022-09-24 07:00","2022-09-24 18:00","연속"]
[496,"경남","통영","통영거제#2 T/L","거제S/S 154kV 통영-거제#2T/L GIS 정밀점검","1. 거제S/S 154kV 통영-거제#2T/L GIS 정밀점검 2. 병행 : 임시선로 구성 (5회선, 임시철탑 5기 신설) - 통영-거제T/L 69호~거제S/S (0.8km, HSATCIR/AW330*S*2C) - 신고성-거제T/L 196호~거제S/S (0.8km, HSATCIR/AW410*S*2C) - 삼성조선T/L 3호~거제 (0.8km, HSATCIR/AW330*S*1C)","2022-09-24 07:00","2022-09-25 18:00","2022-09-24 07:00","2022-09-25 18:00","연속"]
[497,"경남","통영","신고성거제#2 T/L","거제S/S 인출송전선로 지중이설공사 임시선로 구성","○ 임시선로 구성 (5회선, 임시철탑 5기 신설) - 통영-거제T/L 69호~거제S/S (0.8km, HSATCIR/AW330*S*2C) - 신고성-거제T/L 196호~거제S/S (0.8km, HSATCIR/AW410*S*2C) - 삼성조선T/L 3호~거제 (0.8km, HSATCIR/AW330*S*1C)","2022-09-18 07:00","2022-09-18 18:00","2022-09-18 07:00","2022-09-18 18:00","연속"]
[498,"경남","통영","통영거제#1 T/L","거제S/S 154kV 통영-거제#1T/L GIS 정밀점검","1. 거제S/S 154kV 통영-거제#1T/L GIS 정밀점검 2. 병행 : 직할송전 임시선로 구성 (5회선, 임시철탑 5기 신설) - 통영-거제T/L 69호~거제S/S (0.8km, HSATCIR/AW330*S*2C) - 신고성-거제T/L 196호~거제S/S (0.8km, HSATCIR/AW410*S*2C) - 삼성조선T/L 3호~거제 (0.8km, HSATCIR/AW330*S*1C)","2022-09-17 09:00","2022-09-18 18:00","2022-09-17 09:00","2022-09-18 18:00","연속"]
[499,"경남","통영","신고성거제#2 T/L","거제S/S 인출송전선로 지중이설공사 임시선로 구성","○ 임시선로 구성 (5회선, 임시철탑 5기 신설) - 통영-거제T/L 69호~거제S/S (0.8km, HSATCIR/AW330*S*2C) - 신고성-거제T/L 196호~거제S/S (0.8km, HSATCIR/AW410*S*2C) - 삼성조선T/L 3호~거제 (0.8km, HSATCIR/AW330*S*1C)","2022-09-09 07:00","2022-09-12 18:00","2022-09-09 07:00","2022-09-12 18:00","매일"]
[500,"경남","통영","통영거제#1 T/L","거제S/S 인출송전선로 지중이설공사 임시선로 구성","○ 임시선로 구성 (5회선, 임시철탑 5기 신설) - 통영-거제T/L 69호~거제S/S (0.8km, HSATCIR/AW330*S*2C) - 신고성-거제T/L 196호~거제S/S (0.8km, HSATCIR/AW410*S*2C) - 삼성조선T/L 3호~거제 (0.8km, HSATCIR/AW330*S*1C)","2022-09-09 07:00","2022-09-12 18:00","2022-09-09 07:00","2022-09-12 18:00","매일"]
[501,"경남","함안","호포매리#1 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","154kV 호포-매리T/L 24호 본철탑 조립시 안전이격 확보","2022-09-17 07:00","2022-09-20 18:00","2022-09-17 07:00","2022-09-20 18:00","매일"]
[502,"경남","함안","매리김해#1 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","154kV 호포-매리T/L 24호 본철탑 조립시 안전이격 확보","2022-09-17 07:00","2022-09-20 18:00","2022-09-17 07:00","2022-09-20 18:00","매일"]
[503,"경남","함안","창녕초동#2 T/L","154kV 창녕-초동#2T/L 항공장애표시구 교체공사","154kV 창녕-초동T/L 39~40호 인근 상습적인 항공구 소음 민원 발생관련 소음발생 억제차 항공구 교체작업 시행","2022-09-15 08:00","2022-09-16 18:00","2022-09-15 08:00","2022-09-16 18:00","매일"]
[504,"경남","함안","창녕초동#1 T/L","창녕S/S 154kV 창녕-초동#1T/L GCB 조작시험","창녕S/S 154kV 창녕-초동#1T/L GCB 조작시험, OPGW 관련시험(전자제어)","2022-09-14 09:30","2022-09-14 17:30","2022-09-14 09:30","2022-09-14 17:30","연속"]
[505,"광주전남","강진","화원진도#1 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- No.1, 2, 4회선구간 작업자 안전이격확보 휴전(상시 가압조건 유지)","2022-09-25 07:00","2022-09-26 18:00","2022-10-20 08:00","2022-10-21 18:00","매일"]