{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":13,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"765설비","index":0,"n_rows":17,"n_cols":11,"rows_kept":17,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2023년도 9월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #3 M.Tr","신가평S/S 유입 과도서지 차단 접지개선 공사","예방진단시스템 MLU 접지 개선 - MLU 내부 접지동대(BUS Bar) 1개 → 3개 분리 - MLU Mesh 접지 포인트 변경","2023-09-06 09:00","2023-09-07 18:00","2023-09-06 09:00","2023-09-07 18:00","연속"]
[2,"경기","성남","신안성S/S #3 M.Tr","23년 성남전력 765kV 주변압기 보통점검공사","-주변압기 보통점검 -8600, 8672 GIS 보통점검(병행)","2023-09-11 09:00","2023-09-22 18:00","2023-09-11 09:00","2023-09-22 18:00","연속"]
[3,"경기","성남","신중부신안성#2 T/L","23년 성남전력지사 765kV GIS 보통점검공사","- GIS 보통점검","2023-09-23 09:00","2023-09-24 18:00","2023-09-23 09:00","2023-09-24 18:00","연속"]
[4,"경기","성남","신중부신안성#1 T/L","23년 성남전력지사 변전협력회사 총액공사","-HSGS 유압기 보수(효성 입회)","2023-09-09 09:00","2023-09-10 18:00","2023-09-09 09:00","2023-09-10 18:00","연속"]
[5,"경기","성남","신안성S/S #5 M.Tr","23년 성남전력지사 변전협력회사 총액공사","#5M.Tr OLTC 감온센서 설치 및 TAP제어 시험","2023-09-07 09:00","2023-09-08 18:00","2023-09-07 09:00","2023-09-08 18:00","연속"]
[6,"충북","직할","신중부S/S #4 M.Tr","신중부S/S 345kV DS 내부부품 교체 작업","345kV GIS DS부 부분방전 발생에 따른 DS 내부부품 교체공사 대상 : 7961, 7901DS(2대)","2023-09-12 09:00","2023-09-13 18:00","2023-09-12 09:00","2023-09-13 18:00","연속"]
[7,"충북","직할","신중부S/S #5 M.Tr","신중부S/S 345kV DS 내부부품 교체 작업","345kV GIS DS부 부분방전 발생에 따른 DS 내부부품 교체공사 대상 : 7B61, 7B01DS(2대)","2023-09-14 09:00","2023-09-15 18:00","2023-09-14 09:00","2023-09-15 18:00","연속"]
[8,"대전세종충남","서산","당진T/P Tie-Tr","당진화력S/S 765kV #1TIE-Tr B상 교체공사","당진화력S/S 765kV #1TIE-Tr B상 교체공사 (병행) 당진화력S/S 765kV #1TIE-Tr B상 1,2차 GIB 교체공사 (장대현)","2023-09-17 09:00","2023-10-13 18:00","2023-09-17 09:00","2023-10-13 18:00","연속"]
[9,"대전세종충남","서산","신서산당진TP#1 T/L","당진화력S/S 765kV #1TIE-Tr B상 교체공사","안전이격거리 확보를 위한 신서산-당진화력#1T/L 휴전","2023-09-17 09:00","2023-09-17 18:00","2023-09-17 09:00","2023-09-17 18:00","연속"]
[10,"부산울산","동부산","북경남신고리NP#1 T/L","신고리S/S 북경남-신고리#1T/L HSGS Acc C상 부품교체","신고리S/S 북경남-신고리#1T/L HSGS Acc C상 부품교체","2023-09-08 09:00","2023-09-08 18:00","2023-09-08 09:00","2023-09-08 18:00","연속"]
[11,"경남","함안","북경남S/S #3 M.Tr","북경남S/S 765kV #3 M.Tr 보통점검","북경남S/S 765kV #3 M.Tr 보통점검","2023-09-18 09:00","2023-09-23 18:00","2023-09-18 09:00","2023-09-23 18:00","연속"]
[12,"경남","함안","북경남S/S #5 M.Tr","북경남S/S 765kV #5 M.Tr 보통점검","북경남S/S 765kV #5 M.Tr 보통점검","2023-09-04 09:00","2023-09-09 18:00","2023-09-04 09:00","2023-09-09 18:00","연속"]
[13,"경남","함안","북경남S/S #4 M.Tr","북경남S/S 765kV #4 M.Tr 보통점검","북경남S/S 765kV #4 M.Tr 보통점검","2023-09-11 09:00","2023-09-16 18:00","2023-09-11 09:00","2023-09-16 18:00","연속"]

{"sheet":"345설비","index":1,"n_rows":339,"n_cols":11,"rows_kept":339,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]],"flags":["formulas_cached_only"]}
["2023년도 9월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","미금성동#1 T/L","2023년 성동P/O 변전협력회사 총액공사","Line PT 단자함 지상부 이설(지상4m -> 1m)","2023-09-18 09:00","2023-09-19 18:00","2023-09-18 09:00","2023-09-19 18:00","연속"]
[2,"서울","성동","성동S/S #3 M.Tr","성동S/S 345kV #3M.Tr 누유개소 보수","누유개소 보수","2023-09-04 09:00","2023-09-07 18:00","2023-09-04 09:00","2023-09-07 18:00","연속"]
[3,"서울","중부","중부S/S #1 BUS","23년 중부 개폐장치 정밀점검","GIS 정밀점검","2023-09-18 10:00","2023-09-22 18:00","2023-09-18 10:00","2023-09-22 18:00","연속"]
[4,"서울","중부","양주중부#1 T/L","23년 중부 개폐장치 정밀점검","GIS 정밀점검","2023-09-11 10:00","2023-09-15 18:00","취소","취소","연속"]
[5,"서울","중부","중부S/S #1 BUS","23년 중부 개폐장치 정밀점검","GIS 정밀점검","2023-09-11 10:00","2023-09-15 18:00","2023-09-11 10:00","2023-09-15 18:00","연속"]
[6,"서울","중부","중부S/S CB 7372","23 중부P/O 총액공사","7352DS 이음점검","2023-09-21 10:00","2023-09-21 18:00","취소","취소","연속"]
[7,"서울","중부","중부S/S #2 BUS","23 중부P/O 총액공사","7352DS 이음관련","2023-09-25 10:00","2023-09-26 18:00","2023-09-25 10:00","2023-09-26 18:00","연속"]
[8,"서울","중부","양주중부#2 T/L","23년 중부 개폐장치 정밀점검","GIS 정밀점검","2023-09-18 10:00","2023-09-22 18:00","취소","취소","연속"]
[9,"남서울","강남","신양재S/S #2 M.Tr","2023년 강남전력지사 170kV GIS 정밀점검공사","- 대상설비 : #2M.Tr 2차 GIS","2023-09-21 09:00","2023-09-22 18:00","2023-09-21 09:00","2023-09-22 18:00","연속"]
[10,"남서울","강남","신성남신양재#2 T/L","345kV 신성남-신양재#1,2T/L(S) 유지접속함(7상) 교체공사","345kV 신성남-신양재#1,2T/L(S) 유지접속함(7상) 교체","2023-09-04 09:00","2023-09-27 18:00","2023-09-04 09:00","2023-09-27 18:00","연속"]
[11,"남서울","동서울","동서울S/S #3 Sh.R CB","동서울S/S #3Sh.R 초기점검 등 3개소","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-09-04 09:00","2023-09-05 18:00","취소","취소","연속"]
[12,"남서울","동서울","신성남동서울#1 T/L","22~23년 동서울전력지사 가공송전 협력회사 총액공사","추락방지(수평)장치 설치","2023-09-11 07:00","2023-09-12 17:30","2023-09-11 07:00","2023-09-12 17:30","연속"]
[13,"남서울","동서울","신성남동서울#2 T/L","22~23년 동서울전력지사 가공송전 협력회사 총액공사","추락방지(수평)장치 설치","2023-09-13 07:00","2023-09-14 17:30","2023-09-13 07:00","2023-09-14 17:30","연속"]
[14,"남서울","직할","신문래S/S CB 7471","345kV GIS 하자점검공사","345kV GIS 하자점검공사","2023-09-04 09:00","2023-09-04 18:00","2023-09-04 09:00","2023-09-04 18:00","연속"]
[15,"남서울","직할","신문래S/S #2 M.Tr","345kV 주변압기 보통점검공사","345kV 주변압기 보통점검공사","2023-09-06 09:00","2023-09-07 18:00","2023-09-06 09:00","2023-09-07 18:00","연속"]
[16,"남서울","직할","신문래S/S #3 M.Tr","345kV 주변압기 보통점검공사","345kV 주변압기 보통점검공사","2023-09-11 09:00","2023-09-12 18:00","2023-09-11 09:00","2023-09-12 18:00","연속"]
[17,"남서울","직할","신문래S/S #1 M.Tr","345kV 주변압기 보통점검공사","345kV 주변압기 보통점검공사","2023-09-13 09:00","2023-09-14 18:00","2023-09-13 09:00","2023-09-14 18:00","연속"]
[18,"남서울","직할","신문래S/S #4 M.Tr","345kV 주변압기 하자점검공사","345kV 주변압기 하자점검공사 - 신문래 #4M.Tr 1차 GIS 하자점검공사 - 신문래 7400 BUS TIE 하자점검공사","2023-09-04 09:00","2023-09-05 18:00","2023-09-04 09:00","2023-09-05 18:00","연속"]
[19,"인천","김포","가정개폐소 CB 7371","가정개폐소 345kV 신가좌-가정#2T/L(7371) GIS 보통점검","가정개폐소 345kV 신가좌-가정#2T/L(7371) GIS 보통점검","2023-09-18 10:00","2023-09-18 18:00","2023-09-18 10:00","2023-09-18 18:00","연속"]
[20,"인천","김포","가정개폐소 CB 7300","가정 345kV 신가좌가정#2T/L TIE(7300) GIS 보통점검","가정개폐소 345kV 신가좌-가정#2T/L TIE(7300) GIS 보통점검","2023-09-19 10:00","2023-09-19 18:00","2023-09-19 10:00","2023-09-19 18:00","연속"]
[21,"인천","김포","가정개폐소 CB 7471","가정개폐소 345kV 가정-인천CC#1T/L(7471) GIS 보통점검","가정개폐소 345kV 가정-인천CC#1T/L(7471) GIS 보통점검","2023-09-20 10:00","2023-09-20 18:00","2023-09-20 10:00","2023-09-20 18:00","연속"]
[22,"인천","김포","가정개폐소 CB 7272","가정개폐소 345kV 가정-갈산#3T/L(7272) GIS 보통점검","가정개폐소 345kV 가정-갈산#3T/L(7272) GIS 보통점검","2023-09-21 10:00","2023-09-21 18:00","2023-09-21 10:00","2023-09-21 18:00","연속"]
[23,"인천","김포","신김포신인천CC T/L","345kV 신김포-서(신)인천CCT/L 추락방지시설 설치공사","추락방지시설 설치공사","2023-09-21 09:00","2023-09-23 18:00","2023-09-21 09:00","2023-09-23 18:00","연속"]
[24,"인천","김포","신김포서인천CC T/L","345kV 신김포-서(신)인천CCT/L 추락방지시설 설치공사","추락방지시설 설치공사","2023-09-25 09:00","2023-09-27 18:00","2023-09-25 09:00","2023-09-27 18:00","연속"]
[25,"인천","부평","신가좌S/S #1 M.Tr","신가좌S/S 345kV #1 M.Tr 휴전작업","345kV #1 M.Tr 보호반 대체 345kV #1 M.Tr 2,3차 GIS 보통점검 신가좌S/S 23kV #1-1 Sh.R 및 전용 CB 보통점검","2023-09-11 09:00","2023-09-15 18:00","취소","취소","연속"]
[26,"인천","부평","신가좌S/S #2 M.Tr","신가좌S/S 345kV #2 M.Tr 휴전작업","신가좌S/S 345kV #2 M.Tr 초기점검 및 보호반대체 4279VCB 대체 공사 (#2,3M.Tr 동시휴전 필요) 23kV Sh.R 용 CB 보통점검","2023-09-16 09:00","2023-09-22 18:00","2023-09-16 09:00","2023-09-22 18:00","연속"]
[27,"인천","부평","신가좌S/S #3 M.Tr","신가좌S/S 23kV 4279VCB 대체 공사","4279VCB 대체 공사 - VCB대체 공사시에 3차측 동대 활선부 접촉위험으로 #2,3M,tr 동시휴전 필요","2023-09-16 09:00","2023-09-17 18:00","2023-09-16 09:00","2023-09-17 18:00","연속"]
[28,"인천","부평","인천C/C #70 BUS","인천CC S/Y 345kV 7251DS PD 발생 관련 내부점검","인천CC S/Y 345kV 7251DS PD 발생 관련 내부점검","2023-09-29 09:00","2023-09-30 18:00","2023-09-29 09:00","2023-09-30 18:00","연속"]
[29,"인천","부평","인천C/C CB 7671","인천CC S/Y 345kV 인천복합 #2 S/T 7671 GIS 보통점검","인천CC S/Y 345kV 인천복합 #2 S/T 7671 GIS 보통점검","2023-09-25 09:00","2023-09-25 18:00","2023-09-25 09:00","2023-09-25 18:00","연속"]
[30,"인천","시흥","신시흥영흥TP#4 T/L","345kV 신시화분기T/L 건설공사","1) 기설 345kV 영흥T/L No.55 - 신설No.1 C/T 2) 기설 345kV 영흥T/L No.58 - 신설No.2 C/T 3) 기설 345kV 영흥T/L No.72 - 기설 345kV 신시흥S/S 인출정비","2023-09-16 07:00","2023-10-13 18:00","2023-09-16 07:00","2023-10-13 18:00","연속"]
[31,"인천","시흥","신시흥#1S/S #3 M.Tr","신시흥S/S 345kV #3M.Tr 콘서베이터 누유점검 및 접속단자 교체","신시흥S/S 345kV #3M.Tr 콘서베이터 누유점검 및 1,2차 접속단자 교체 - 옥외 DS 절연커버 시공","2023-09-25 09:00","2023-09-27 18:00","2023-09-25 09:00","2023-09-27 18:00","연속"]
[32,"인천","시흥","신시흥영흥TP#2 T/L","345kV 신시화분기T/L 건설공사","1) 기설 345kV 영흥T/L No.55 - 신설No.1 C/T 2) 기설 345kV 영흥T/L No.58 - 신설No.2 C/T 3) 기설 345kV 영흥T/L No.72 - 기설 345kV 신시흥S/S 인출정비","2023-09-18 07:00","2023-10-13 18:00","2023-09-18 07:00","2023-10-13 18:00","연속"]
[33,"인천","시흥","신시흥영흥TP#1 T/L","345kV 신시화분기T/L 건설공사","1) 기설 345kV 영흥T/L No.55 - 신설No.1 C/T 2) 기설 345kV 영흥T/L No.58 - 신설No.2 C/T 3) 기설 345kV 영흥T/L No.72 - 기설 345kV 신시흥S/S 인출정비","2023-09-16 07:00","2023-09-17 18:00","2023-09-16 07:00","2023-09-17 18:00","연속"]
[34,"인천","직할","서인천CC신부평#1 T/L","345kV 서인천CC-신부평#1T/L OF케이블 절연유 채유","345kV 서인천CC-신부평#1T/L OF케이블 절연유 채유 - 서인천EBG ~ J/B#20(17개소)","2023-09-18 09:00","2023-09-19 18:00","2023-09-18 09:00","2023-09-19 18:00","연속"]
[35,"인천","직할","신부평S/S CB 7471","신부평S/S 345kV 7471 GIS 조작시험","신부평S/S 345kV 7471 GIS 조작시험","2023-09-20 09:30","2023-09-20 18:00","2023-09-25 09:30","2023-09-25 18:00","연속"]
[36,"인천","직할","신부평S/S CB 7271","신부평S/S 345kV 7271 GIS 조작시험","신부평S/S 345kV 7271 GIS 조작시험","2023-09-21 09:30","2023-09-21 14:00","2023-09-27 09:30","2023-09-27 14:00","연속"]
[37,"인천","직할","신부평S/S CB 7371","신부평S/S 345kV 7371 GIS 조작시험","신부평S/S 345kV 7371 GIS 조작시험","2023-09-21 14:00","2023-09-21 18:00","2023-09-27 14:00","2023-09-27 18:00","연속"]
[38,"경기북부","고양","신덕은S/S #2 M.Tr","신덕은S/S 345kV #2M.Tr 산화방지제 투입 및 여과","신덕은S/S #2M.Tr A,B,C상 절연유 성능저하에 따른 산화방지제 투입 및 여과 시행","2023-09-11 09:00","2023-09-14 18:00","2023-09-11 09:00","2023-09-14 18:00","연속"]
[39,"경기북부","고양","신덕은S/S #4 M.Tr","'22~23년 고양전력지사 변전협력회사 총액공사","신덕은S/S #4M.Tr 3차 피뢰기 A,B,C상 보통점검","2023-09-21 09:00","2023-09-21 18:00","2023-09-21 09:00","2023-09-21 18:00","연속"]
[40,"경기북부","고양","신김포신파주#1 T/L","2022~2023년 고양전력지사 가공송전협력회사 총액공사","철탑추락방지시설 설치","2023-09-18 07:00","2023-09-20 18:00","2023-09-18 07:00","2023-09-20 18:00","연속"]
[41,"경기북부","구리","신가평미금#1 T/L","2022~23 구리전력 변전협력 총액공사","미금S/S 345kV 신가평-미금#1T/L 피뢰기 하자점검(9.4) 신가평S/S 345kV 7772, 7700GIS 보통점검(9.4~9.5)","2023-09-01 11:30","2023-09-02 18:00","2023-09-01 11:30","2023-09-02 18:00","연속"]
[42,"경기북부","구리","동서울미금#2 T/L","2022~23 구리전력 변전협력 총액공사","미금S/S 345kV 동서울-미금#2T/L 피뢰기 하자점검","2023-09-01 09:00","2023-09-01 11:30","2023-09-01 09:00","2023-09-01 11:30","연속"]
[43,"경기북부","구리","신가평미금#2 T/L","345kV 미금변전소 용량부족 차단기 대체공사(5차)","용량부족 차단기 교체 25CB","2023-09-11 09:00","2023-12-01 18:00","2023-09-11 09:00","2023-12-01 18:00","연속"]
[44,"경기북부","구리","미금S/S CB 7871","345kV 미금변전소 용량부족 차단기 대체공사(5차)","용량부족 차단기 교체 25CB","2023-09-11 09:00","2023-12-01 18:00","취소","취소","연속"]
[45,"경기북부","구리","미금S/S CB 7800","345kV 미금변전소 용량부족 차단기 대체공사(5차)","용량부족 차단기 교체 25CB","2023-09-11 09:00","2023-12-01 18:00","취소","취소","연속"]
[46,"경기북부","구리","미금S/S CB 7672","2022~23 구리전력 변전협력 총액공사","미금S/S 7652DS 부분방전 발생 관련 내부점검","2023-09-06 09:00","2023-09-08 18:00","취소","취소","연속"]
[47,"경기북부","구리","미금S/S #2 BUS","2022~23 구리전력 변전협력 총액공사","미금S/S 7652DS 부분방전 발생 관련 내부점검","2023-09-06 09:00","2023-09-08 18:00","취소","취소","연속"]
[48,"경기북부","구리","미금S/S #2 M.Tr","22~23년 구리전력 변전협력 총액공사","미금S/S 345kV #2M.Tr A상 1차 부싱절연유 채유","2023-09-27 09:00","2023-09-27 18:00","2023-09-27 09:00","2023-09-27 18:00","연속"]
[49,"경기북부","구리","미금S/S #1 M.Tr","22~23년 구리전력 변전협력 총액공사","미금S/S 345kV #1M.Tr A상 2차 부싱절연유 채유","2023-09-26 09:00","2023-09-26 18:00","2023-09-26 09:00","2023-09-26 18:00","연속"]
[50,"경기북부","구리","신가평S/S CB 7672","2022~23 구리전력 변전협력 총액공사","신가평S/S 신가평-신의정부#1T/L GIS 보통점검 7672","2023-09-18 09:00","2023-09-18 18:00","2023-09-18 09:00","2023-09-18 18:00","연속"]
[51,"경기북부","구리","신가평신의정부#2 T/L","신가평S/S 신가평-신의정부#2T/L 내부점검","신가평S/S 신가평-신의정부#2T/L 내부점검 - 7562DS 부분방전 발생관련 내부점검 시행","2023-09-04 09:00","2023-09-08 18:00","2023-09-04 09:00","2023-09-08 18:00","연속"]
[52,"경기북부","구리","신포천S/S #2 M.Tr","22~23년 구리전력 변전협력 총액공사","신포천S/S 345kV #3M.Tr 부싱절연유 채유","2023-09-06 09:00","2023-09-06 18:00","2023-09-06 09:00","2023-09-06 18:00","연속"]
[53,"경기북부","구리","신포천S/S #1 M.Tr","22~23년 구리전력 변전협력 총액공사","신포천S/S 345kV #3M.Tr 부싱절연유 채유","2023-09-05 09:00","2023-09-05 18:00","2023-09-05 09:00","2023-09-05 18:00","연속"]
[54,"경기북부","구리","신포천S/S CB 7600","2022~23 구리전력 변전협력 총액공사","신포천S/S 신포천-동두천CC #2T/L-TIE GIS 보통점검 7600","2023-09-19 09:00","2023-09-19 18:00","2023-09-19 09:00","2023-09-19 18:00","연속"]
[55,"경기북부","구리","신포천S/S CB 7671","2022~23 구리전력 변전협력 총액공사","신포천S/S 신포천-동두천CC #2T/L GIS 보통점검 7671","2023-09-21 09:00","2023-09-21 18:00","2023-09-21 09:00","2023-09-21 18:00","연속"]
[56,"경기북부","구리","신포천S/S #3 M.Tr","22~23년 구리전력 변전협력 총액공사","신포천S/S 345kV #3M.Tr 부싱절연유 채유","2023-09-07 09:00","2023-09-07 18:00","2023-09-07 09:00","2023-09-07 18:00","매일"]
[57,"경기북부","구리","포천C/C CB 7172","2022~23 구리전력 변전협력 총액공사","포천C/C 345kV #1S/U TR 1차 7172 GIS 조작시험","2023-09-11 15:30","2023-09-11 18:00","2023-09-11 15:30","2023-09-11 18:00","연속"]
[58,"경기북부","구리","포천C/C CB 7100","2022~23 구리전력 변전협력 총액공사","포천C/C 345kV 신포천포천CC#1T/L-#1S/U TR 1차 7100 GIS 조작시험","2023-09-11 13:00","2023-09-11 15:30","2023-09-11 13:00","2023-09-11 15:30","연속"]
[59,"경기북부","구리","포천C/C CB 7171","2022~23 구리전력 변전협력 총액공사","포천C/C 345kV 신포천-포천CC #1T/L 7171 GIS 조작시험","2023-09-11 09:00","2023-09-11 12:00","2023-09-11 09:00","2023-09-11 12:00","연속"]
[60,"경기북부","구리","포천C/C CB 7372","2022~23 구리전력 변전협력 총액공사","포천C/C 345kV #4S/U TR 1차 7372 GIS 조작시험","2023-09-14 15:30","2023-09-14 18:00","2023-09-14 15:30","2023-09-14 18:00","연속"]
[61,"경기북부","구리","포천C/C CB 7300","2022~23 구리전력 변전협력 총액공사","포천C/C 345kV 신포천포천CC#2T/L-#4S/UTR 1차 7300 GIS 조작시험","2023-09-14 13:00","2023-09-14 15:30","2023-09-14 13:00","2023-09-14 15:30","연속"]
[62,"경기북부","구리","포천C/C CB 7371","2022~23 구리전력 변전협력 총액공사","포천C/C 345kV 신포천-포천CC #2T/L 7371 GIS 조작시험","2023-09-14 09:00","2023-09-14 12:00","2023-09-14 09:00","2023-09-14 12:00","연속"]
[63,"경기북부","구리","포천C/C CB 7272","2022~23 구리전력 변전협력 총액공사","포천C/C 345kV #3S/U TR 1차 7272 GIS 조작시험","2023-09-12 15:30","2023-09-12 18:00","2023-09-12 15:30","2023-09-12 18:00","연속"]
[64,"경기북부","구리","포천C/C CB 7200","2022~23 구리전력 변전협력 총액공사","포천C/C 345kV #2S/U TR-#3S/U TR TIE 7200 GIS 조작시험","2023-09-12 13:00","2023-09-12 15:30","2023-09-12 13:00","2023-09-12 15:30","연속"]
[65,"경기북부","구리","포천C/C CB 7271","2022~23 구리전력 변전협력 총액공사","포천C/C 345kV #2S/U TR 1차 7271 GIS 조작시험","2023-09-12 09:00","2023-09-12 12:00","2023-09-12 09:00","2023-09-12 12:00","연속"]
[66,"경기북부","직할","신포천동두천CC#2 T/L","22-23년도 직할 변전협력회사 총액공사","동두천CC 362kV GIS 7621-1,2,3 조작시험","2023-09-14 09:00","2023-09-14 18:00","2023-09-14 09:00","2023-09-14 18:00","연속"]
[67,"경기북부","직할","신포천동두천CC#1 T/L","22-23년도 직할 변전협력회사 총액공사","동두천CC 362kV GIS 7571 보통점검, 7521-1,2,3 조작시험","2023-09-13 09:00","2023-09-13 18:00","2023-09-13 09:00","2023-09-13 18:00","연속"]
[68,"경기북부","직할","동두천C/C CB 7200","22-23년도 직할 변전협력회사 총액공사","동두천CC 362kV GIS 7200 보통점검","2023-09-12 09:00","2023-09-12 18:00","2023-09-12 09:00","2023-09-12 18:00","연속"]
[69,"경기북부","직할","동두천C/C CB 7271","22-23년도 직할 변전협력회사 총액공사","동두천CC 362kV GIS 7271 보통점검","2023-09-11 09:00","2023-09-11 18:00","2023-09-11 09:00","2023-09-11 18:00","연속"]
[70,"경기북부","직할","동두천C/C CB 7100","22-23년도 직할 변전협력회사 총액공사","동두천CC 362kV GIS 7100 보통점검","2023-09-05 09:00","2023-09-05 18:00","2023-09-05 09:00","2023-09-05 18:00","연속"]
[71,"경기북부","직할","동두천C/C CB 7171","22-23년도 직할 변전협력회사 총액공사","동두천CC 362kV GIS 7171 보통점검","2023-09-04 09:00","2023-09-04 18:00","2023-09-04 09:00","2023-09-04 18:00","연속"]
[72,"경기북부","직할","신의정부S/S #1 M.Tr","23년 경기북부 직할 345kV M.Tr 및 OLTC 정밀점검 공사","신의정부S/S #1M.Tr A,B,C상 정밀점검","2023-09-04 09:00","2023-09-15 18:00","2023-09-04 09:00","2023-09-15 18:00","연속"]
[73,"경기북부","직할","신의정부양주#2 T/L","345kV 신의정부S/S CLR용 GIS 설치공사","신의정부-양주#2TL GIS ↔ #2CLR 2차측 GIB 연결용 LA, 단상GIB 설치 등","2023-09-11 09:00","2023-10-08 18:00","2023-09-11 09:00","2023-10-08 18:00","연속"]
[74,"경기북부","직할","신의정부S/S #2 M.Tr","23년 경기북부 직할 345kV M.Tr 및 OLTC 정밀점검 공사","신의정부S/S #2M.Tr A,B상 정밀점검 신의정부S/S #2M.Tr C상 보통점검","2023-09-18 09:00","2023-09-27 18:00","2023-09-18 09:00","2023-09-27 18:00","연속"]
[75,"경기북부","직할","양주S/S #4 Sh.R CB","22-23년도 직할 변전협력회사 총액공사","양주SS 362kV 7672 GIS 전자변교체, #4Sh.R GIS 하자보수","2023-09-07 09:00","2023-09-07 18:00","2023-09-07 09:00","2023-09-07 18:00","연속"]
[76,"경기북부","직할","양주S/S CB 7600","22-23년도 직할 변전협력회사 총액공사","양주SS 362kV 7672 GIS 전자변교체, #4Sh.R GIS 하자보수","2023-09-07 09:00","2023-09-07 18:00","2023-09-07 09:00","2023-09-07 18:00","연속"]
[77,"경기북부","직할","양주S/S CB 7672","22-23년도 직할 변전협력회사 총액공사","양주SS 362kV 7672 GIS 전자변교체, #4Sh.R GIS 하자보수","2023-09-07 09:00","2023-09-07 18:00","2023-09-07 09:00","2023-09-07 18:00","연속"]
[78,"경기북부","직할","양주중부#2 T/L","2022~2023년 고양전력지사 가공송전협력회사 총액공사","피뢰기 설치, 지지애자 교체","2023-09-15 07:00","2023-09-15 18:00","2023-09-15 07:00","2023-09-15 18:00","연속"]
[79,"경기북부","직할","양주중부#1 T/L","2022~2023년 고양전력지사 가공송전협력회사 총액공사","지지애자 교체","2023-09-27 07:00","2023-09-27 18:00","2023-09-27 07:00","2023-09-27 18:00","연속"]
[80,"경기북부","직할","양주S/S #2 M.Tr","양주S/S HVDC GIS 설치공사","- 154kV GIS X 2CCT 설치 - 22.9kV GIS X 3CCT 설치","2023-09-18 09:00","2023-09-26 18:00","2023-09-18 09:00","2023-09-26 18:00","연속"]
[81,"경기","군포","서서울#2신시흥#2 T/L","서서울#2S/S 362kV GIS PD발생개소 보수","서서울#2S/S 362kV GIS PD발생개소 보수","2023-09-18 09:00","2023-09-19 18:00","2023-09-18 09:00","2023-09-19 18:00","연속"]
[82,"경기","군포","서서울#2신시흥#1 T/L","서서울#2S/S 362kV GIS PD발생개소 보수","서서울#2S/S 362kV GIS PD발생개소 보수","2023-09-25 09:00","2023-09-26 18:00","2023-09-25 09:00","2023-09-26 18:00","연속"]
[83,"경기","군포","서서울S/S CB 7571","서서울S/S 서서울-신광명#1T/L(7571) GIS 조작시험","서서울S/S 서서울-신광명#1T/L(7571) GIS 조작시험","2023-09-01 09:00","2023-09-01 14:00","2023-09-01 09:00","2023-09-01 14:00","연속"]
[84,"경기","군포","신온양서서울#1 T/L","2022-23 평택전력지사 가공송전 협력회사 총액공사","추락방지장치(수평) 설치","2023-09-16 07:00","2023-09-17 18:00","취소","취소","연속"]
[85,"경기","군포","신온양서서울#1 T/L","2022-23 평택전력지사 가공송전 협력회사 총액공사","추락방지장치(수평) 설치","2023-09-23 07:00","2023-09-24 18:00","취소","취소","연속"]
[86,"경기","군포","서서울신광명#2 T/L","서서울S/S 서서울-신광명#2T/L(7671) GIS 조작시험","서서울S/S 서서울-신광명#2T/L(7671) GIS 조작시험 및 PT,LA 보통점검","2023-09-01 14:00","2023-09-01 18:00","2023-09-01 14:00","2023-09-01 18:00","연속"]
[87,"경기","동부","곤지암여주복합#1 T/L","2022-2023년 성남전력지사 가공송전 협력회사 총액공사","345kV 곤지암-여주복합T/L 53~54호 가공지선 교체","2023-09-09 07:00","2023-09-10 18:00","2023-09-09 07:00","2023-09-10 18:00","연속"]
[88,"경기","동부","곤지암동서울#2 T/L","추락방지장치(수평) 설치공사","31기","2023-09-21 07:00","2023-09-23 18:00","2023-09-21 07:00","2023-09-23 18:00","연속"]
[89,"경기","동부","곤지암동서울#1 T/L","추락방지장치(수평) 설치공사","31기","2023-09-16 07:00","2023-09-20 18:00","2023-09-16 07:00","2023-09-20 18:00","연속"]
[90,"경기","성남","신성남S/S SEC CB 70710","23년 성남전력 170, 362kV GIS 보통점검공사","- 70-71SEC GIS 보통점검","2023-09-19 09:00","2023-09-19 18:00","2023-09-19 09:00","2023-09-19 18:00","연속"]
[91,"경기","성남","신성남S/S SEC CB 75760","23년 성남전력 170, 362kV GIS 보통점검공사","- 75-76SEC GIS 보통점검","2023-09-20 09:00","2023-09-20 18:00","2023-09-20 09:00","2023-09-20 18:00","연속"]
[92,"경기","성남","신성남S/S #6 M.Tr","성남전력지사 23kV Sh.R 설치공사","- 무부하가압용","2023-09-25 09:00","2023-09-26 18:00","2023-09-25 09:00","2023-09-26 18:00","연속"]
[93,"경기","성남","신성남S/S #5 M.Tr","23년 성남전력지사 변전협력회사 총액공사","- 부싱 절연유 채유","2023-09-21 14:00","2023-09-21 18:00","2023-09-21 14:00","2023-09-21 18:00","연속"]
[94,"경기","성남","신안성신성남#1 T/L","추락방지장치(수평) 설치공사","1기(4회선 병가구간)","2023-09-24 07:00","2023-09-24 18:00","2023-09-24 07:00","2023-09-24 18:00","연속"]
[95,"경기","성남","신성남S/S #2 M.Tr","23년 성남전력지사 변전협력회사 총액공사","- 부싱 절연유 채유 - 4287SIS 보통점검","2023-09-21 09:00","2023-09-21 14:00","2023-09-21 09:00","2023-09-21 14:00","연속"]
[96,"경기","성남","서서울#2신성남#2 T/L","23년 성남전력지사 변전협력회사 총액공사","- CVT 초기점검(A, B), 보통점검(C) - LA 보통점검(A, B, C)","2023-09-22 09:00","2023-09-22 14:00","2023-09-22 09:00","2023-09-22 14:00","연속"]
[97,"경기","성남","서서울#2신성남#1 T/L","23년 성남전력지사 변전협력회사 총액공사","- CVT 보통점검 - LA 보통점검","2023-09-22 14:00","2023-09-22 18:00","2023-09-22 14:00","2023-09-22 18:00","연속"]
[98,"경기","성남","신성남S/S STATCOM CB","23년 성남전력지사 STATCOM 보통점검공사","- STATCOM 정밀점검 - 7000, 7072GIS 보통점검 - STATCOM M.Tr 보통점검","2023-09-05 09:00","2023-09-22 18:00","2023-09-05 09:00","2023-09-08 18:00","연속"]
[99,"경기","성남","신성남동서울#1 T/L","추락방지장치(수평) 설치공사","41기","2023-09-24 07:00","2023-09-27 18:00","2023-09-24 07:00","2023-09-27 18:00","연속"]
[100,"경기","성남","신수원S/S #1 M.Tr","23년 성남전력지사 변전협력회사 총액공사","- (B상)154kV GIS 탱크 인입부 과열 보수","2023-09-19 09:00","2023-09-19 18:00","2023-09-19 09:00","2023-09-19 18:00","연속"]
[101,"경기","성남","신수원S/S #4 M.Tr","23년 성남전력지사 변전협력회사 총액공사","-1차 하우징 누유 점검","2023-09-12 09:00","2023-09-14 18:00","2023-09-12 09:00","2023-09-14 18:00","연속"]
[102,"경기","성남","신안성신수원#1 T/L","23년 성남전력지사 변전협력회사 총액공사","-GIS 보통점검","2023-09-07 09:00","2023-09-07 18:00","2023-09-07 09:00","2023-09-07 18:00","연속"]
[103,"경기","성남","신안성S/S #6 Sh.R CB","23년 성남전력 170, 362kV GIS 보통점검공사","-GIS 보통점검","2023-09-14 09:00","2023-09-14 18:00","2023-09-14 09:00","2023-09-14 18:00","연속"]
[104,"경기","성남","신안성S/S #5 Sh.R CB","23년 성남전력 170, 362kV GIS 보통점검공사","-GIS 보통점검","2023-09-12 09:00","2023-09-12 18:00","2023-09-12 09:00","2023-09-12 18:00","연속"]
[105,"경기","성남","신안성서안성#2 T/L","23년 성남전력지사 변전협력회사 총액공사","-유사고장 회로보완","2023-09-18 09:00","2023-09-18 18:00","2023-09-18 09:00","2023-09-18 18:00","연속"]
[106,"경기","직할","화성평택TP#2 T/L","2022-23년 경기본부 직할 변전협력회사 총액공사","화성S/S 화성-평택TP#2T/L LA, CVT 보통점검","2023-09-01 09:00","2023-09-01 18:00","2023-09-01 09:00","2023-09-01 18:00","연속"]
[107,"경기","평택","고덕#2S/S #3 M.Tr","345kV 고덕#2S/S M.Tr 2차측 GIB 접지보강공사","345kV 고덕#2S/S #3M.Tr 2차측 GIB 접지보강","2023-09-13 09:00","2023-09-14 18:00","2023-09-13 09:00","2023-09-14 18:00","연속"]
[108,"경기","평택","고덕#2S/S #2 M.Tr","345kV 고덕#2S/S M.Tr 2차측 GIB 접지보강공사","345kV 고덕#2S/S #2M.Tr 2차측 GIB 접지보강","2023-09-11 09:00","2023-09-12 18:00","2023-09-11 09:00","2023-09-12 18:00","연속"]
[109,"경기","평택","고덕#2S/S #1 M.Tr","345kV 고덕#2S/S M.Tr 2차측 GIB 접지보강공사","345kV 고덕#2S/S #1M.Tr 2차측 GIB 접지보강","2023-09-07 09:00","2023-09-08 18:00","2023-09-07 09:00","2023-09-08 18:00","연속"]
[110,"경기","평택","고덕S/S #2 M.Tr","23년 평택전력지사 변전협력회사 총액공사","고덕S/S #2M.Tr 변압기 보통점검, 7472,7400GIS 보통점검, 6244GIS 보통점검 및 DC케이블 이설, 4289,4289-1,2,3 SIS 보통점검","2023-09-14 09:00","2023-09-15 18:00","2023-09-14 09:00","2023-09-15 18:00","연속"]
[111,"경기","평택","고덕S/S STATCOM CB","고덕S/S 345kV STATCOM Yard 포장공사","하계 STATCOM Yard 잡초접촉에 의한 지락고장 예방 및 제약비용 절감을 위한 포장공사","2023-09-18 09:00","2023-09-22 18:00","취소","취소","연속"]
[112,"경기","평택","고덕S/S #1 M.Tr","23년 평택전력지사 변전협력회사 총액공사","고덕S/S #1M.Tr 3차측 PT FUSE 교체","2023-09-27 09:00","2023-09-27 18:00","2023-09-27 09:00","2023-09-27 18:00","연속"]
[113,"경기","평택","화성평택TP#1 T/L","23년 평택전력지사 변전협력회사 총액공사","평택T/P 화성-평택T/P 7621DS인디케이터 보수","2023-09-02 09:00","2023-09-02 18:00","2023-09-02 09:00","2023-09-02 18:00","연속"]
[114,"강원","강릉","신양양S/S #1 BUS","2023년 362kV GIS 정밀점검 무부하가압","362kV GIS 정밀점검 - (11~15일) 7400 GIS 정밀점검 - (18~22일) 7472 GIS 정밀점검","2023-09-15 13:00","2023-09-15 15:00","2023-09-15 13:00","2023-09-15 15:00","연속"]
[115,"강원","강릉","신양양S/S #2 BUS","2023년 362kV GIS 정밀점검 무부하가압","362kV GIS 정밀점검 - (11~15일) 7400 GIS 정밀점검 - (18~22일) 7472 GIS 정밀점검","2023-09-22 13:00","2023-09-22 15:00","2023-09-22 13:00","2023-09-22 15:00","연속"]
[116,"강원","강릉","신양양S/S #1 M.Tr","2023 강릉전력지사 변전협력회사 총액공사","부싱절연유 채유","2023-09-06 10:00","2023-09-06 14:00","2023-09-06 10:00","2023-09-06 14:00","연속"]
[117,"강원","강릉","신양양S/S CB 7472","2023년 362kV GIS 정밀점검","362kV GIS 정밀점검(7472)","2023-09-18 09:00","2023-09-22 18:00","2023-09-18 09:00","2023-09-22 18:00","연속"]
[118,"강원","강릉","신양양S/S CB 7400","2023년 362kV GIS 정밀점검","362kV GIS 정밀점검(7400)","2023-09-11 09:00","2023-09-15 18:00","2023-09-11 09:00","2023-09-15 18:00","연속"]
[119,"강원","강릉","신양양S/S #3 M.Tr","2023년 362kV GIS 정밀점검","362kV GIS 정밀점검 - (11~15일) 7400 GIS 정밀점검 - (18~22일) 7472 GIS 정밀점검","2023-09-11 09:00","2023-09-22 18:00","취소","취소","연속"]
[120,"강원","강릉","신양양S/S #2 M.Tr","2023 강릉전력지사 변전협력회사 총액공사","부싱절연유 채유","2023-09-06 14:00","2023-09-06 18:00","2023-09-06 14:00","2023-09-06 18:00","연속"]
[121,"강원","강릉","안인개폐소양양PP T/L","2022~2023년 가공송전협력회사 총액공사","○ 점퍼웨이트 댐퍼 설치(No.164), 스페이서댐퍼 교체(No.115~116, 116~117, 141~142, 145, 173)","2023-09-13 07:30","2023-09-18 18:00","2023-09-13 07:30","2023-09-18 18:00","매일"]
[122,"강원","강릉","안인개폐소신양양 T/L","2022~2023년 가공송전협력회사 총액공사","○ 점퍼웨이트 댐퍼 설치(No.164), 스페이서댐퍼 교체(No.94~95, 169)","2023-09-11 07:30","2023-09-12 18:00","2023-09-11 07:30","2023-09-12 18:00","매일"]
[123,"강원","태백","신태백한울NP#1 T/L","345kV 울태/L 고정형 폴리머점퍼지지애자 및 수평추락방지장치 설치공사 ","345kV 신태백-한울NP2T/L 고정형 폴리머점퍼지지애자 및 수평추락방지장치 설치공사","2023-09-11 08:00","2023-09-17 18:00","취소","취소","연속"]
[124,"강원","태백","신태백한울NP#2 T/L","345kV 울태/L 고정형 폴리머점퍼지지애자 및 수평추락방지장치 설치공사 ","345kV 신태백-한울NP2T/L 고정형 폴리머점퍼지지애자 및 수평추락방지장치 설치공사","2023-09-18 08:00","2023-09-24 18:00","취소","취소","연속"]
[125,"강원","강릉","신양양S/S #1 BUS","2023년 362kV GIS 정밀점검","362kV GIS 정밀점검 - (11~15일) 7400 GIS 정밀점검 - (18~22일) 7472 GIS 정밀점검","2023-09-15 13:00","2023-09-15 15:00","취소","취소","연속"]
[126,"강원","강릉","신양양S/S #2 BUS","2023년 362kV GIS 정밀점검","362kV GIS 정밀점검 - (11~15일) 7400 GIS 정밀점검 - (18~22일) 7472 GIS 정밀점검","2023-09-22 13:00","2023-09-22 15:00","취소","취소","연속"]
[127,"강원","동해","동해S/S #1 M.Tr","22~23 동해전력지사 변전정비팀 총액공사","- 1,2,3차 LA ABC상 보통점검 - 3차 PT 보통점검","2023-09-18 09:30","2023-09-19 18:00","2023-09-18 09:30","2023-09-19 18:00","연속"]
[128,"강원","동해","삼척G/P #3 Tie-Tr","22~23 동해전력지사 변전정비팀 총액공사","2차,3차 LA ABC상 보통점검 7600 GIS 보통점검","2023-09-25 09:30","2023-09-25 18:00","2023-09-25 09:30","2023-09-25 18:00","연속"]
[129,"강원","동해","삼척G/P CB 7500","23년 동해P/O 362GIS 정밀점검공사","GIS 정밀점검","2023-09-21 09:30","2023-09-23 18:00","2023-09-21 09:30","2023-09-23 18:00","연속"]
[130,"강원","동해","삼척G/P #2 Tie-Tr","22~23 동해전력지사 변전정비팀 총액공사","2차,3차 LA ABC상 보통점검","2023-09-26 09:30","2023-09-26 18:00","2023-09-26 09:30","2023-09-26 18:00","연속"]
[131,"강원","동해","삼척G/P CB 7571","23년 동해P/O 362GIS 정밀점검공사","GIS 정밀점검","2023-09-18 09:30","2023-09-20 18:00","2023-09-18 09:30","2023-09-20 18:00","연속"]
[132,"강원","동해","삼척G/P CB 7772","23년 동해P/O 362GIS 정밀점검공사","GIS 정밀점검","2023-09-05 09:30","2023-09-08 18:00","2023-09-05 09:30","2023-09-08 18:00","연속"]
[133,"강원","동해","삼척G/P CB 7400","23년 동해P/O 362GIS 정밀점검공사","GIS 정밀점검","2023-09-14 09:30","2023-09-16 18:00","2023-09-14 09:30","2023-09-16 18:00","연속"]
[134,"강원","동해","삼척G/P CB 7471","23년 동해P/O 362GIS 정밀점검공사","GIS 정밀점검","2023-09-11 09:30","2023-09-13 18:00","2023-09-11 09:30","2023-09-13 18:00","연속"]
[135,"강원","태백","신태백한울NP#2 T/L","345kV 울태/L 고정형 폴리머점퍼지지애자 및 수평추락방지장치 설치공사","345kV 신태백-한울NP2T/L 고정형 폴리머점퍼지지애자 및 수평추락방지장치 설치공사","2023-09-18 08:00","2023-09-24 18:00","취소","취소","연속"]
[136,"강원","태백","신태백한울NP#1 T/L","345kV 울태/L 고정형 폴리머점퍼지지애자 및 수평추락방지장치 설치공사","345kV 신태백-한울NP2T/L 고정형 폴리머점퍼지지애자 및 수평추락방지장치 설치공사","2023-09-11 08:00","2023-09-17 18:00","취소","취소","연속"]
[137,"충북","직할","신중부S/S #2 BUS","신중부S/S 345kV DS 내부부품 교체 작업","345kV GIS DS부 부분방전 발생에 따른 #2BUS DS 내부부품 교체공사 대상 : 7952, 7A52, 7B52, 7C52DS(4대)","2023-09-19 09:00","2023-09-22 18:00","2023-09-19 09:00","2023-09-22 18:00","연속"]
[138,"충북","직할","신진천S/S #1 M.Tr","22-23년 충북직할 변전협력회사 총액공사","#1M.Tr 1차 PT보통점검, 1,2차 LA 보통점검, 3차 모선 지지애자 절연커버 적용","2023-09-18 10:00","2023-09-19 18:00","2023-09-18 10:00","2023-09-19 18:00","연속"]
[139,"충북","직할","신중부신진천#2 T/L","22-23년 충북직할 변전협력회사 총액공사","신진천SS : 345kV 신중부-신진천 #2T/L CVT 보통점검 신중부SS : 345kV 신중부-신진천#2T/L DS 핀교체(병행)","2023-09-21 10:00","2023-09-22 18:00","취소","취소","연속"]
[140,"충북","직할","신진천S/S #2 M.Tr","22-23년 충북직할 변전협력회사 총액공사","1차 CVT 보통점검","2023-09-26 10:00","2023-09-26 18:00","2023-09-26 10:00","2023-09-26 18:00","연속"]
[141,"충북","청주","세종남청주#2 T/L","`22~23년 청주전력지사 송전협력회사 총액공사","No.54,55 폴리머지지애자 설치","2023-09-07 08:00","2023-09-07 18:00","2023-09-07 08:00","2023-09-07 18:00","매일"]
[142,"충북","청주","남청주S/S #4 M.Tr","남청주S/S #4M.Tr,GIS 정밀점검","-#4M.Tr 정밀점검 -#4M.Tr 1차 GIS, 1차 TIE GIS 정밀점검","2023-09-18 09:00","2023-09-27 18:00","2023-09-18 09:00","2023-09-27 18:00","연속"]
[143,"충북","청주","신옥천세종#2 T/L","`22~23년 청주전력지사 송전협력회사 총액공사","No.57,58 추락방지장치 설치","2023-09-08 08:00","2023-09-08 18:00","2023-09-08 08:00","2023-09-08 18:00","매일"]
[144,"충북","청주","신옥천세종#1 T/L","`22~23년 청주전력지사 송전협력회사 총액공사","No.57,58 추락방지장치 설치 No.1 폴리머지지애자 설치","2023-09-07 08:00","2023-09-07 18:00","취소","취소","매일"]
[145,"충북","청주","신옥천S/S CB 7600","22-23년 청주전력 변전협력회사 총액공사","362kV GIS 보통점검","2023-09-18 08:00","2023-09-20 18:00","취소","취소","연속"]
[146,"충북","청주","신옥천S/S CB 7672","22-23년 청주전력 변전협력회사 총액공사","362kV GIS 보통점검","2023-09-18 08:00","2023-09-20 18:00","취소","취소","연속"]
[147,"충북","청주","신옥천S/S CB 7671","22-23년 청주전력 변전협력회사 총액공사","362kV GIS 보통점검","2023-09-18 08:00","2023-09-20 18:00","취소","취소","연속"]
[148,"충북","청주","신옥천S/S CB 7772","22-23년 청주전력 변전협력회사 총액공사","362kV GIS 보통점검","2023-09-25 08:00","2023-09-26 18:00","취소","취소","연속"]
[149,"충북","청주","신옥천S/S CB 7700","22-23년 청주전력 변전협력회사 총액공사","362kV GIS 보통점검","2023-09-25 08:00","2023-09-26 18:00","취소","취소","연속"]
[150,"충북","충주","신제천S/S #4 M.Tr","345kV 신제천S/S #4 M.Tr 대체공사","9.19 ~ 9.20 : #4 M.Tr 무부하가압용 9.21 ~ 9.22 : #4 M.Tr 실부하가압용","2023-09-19 09:00","2023-09-22 18:00","2023-09-19 09:00","2023-09-22 18:00","연속"]
[151,"충북","충주","신제천신영주#1 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평 추락방지장치 설치 [No.1~165(162기] 추석(9.28~10.1) 제외, 주말 작업 있음","2023-09-19 08:00","2023-10-16 17:00","취소","취소","매일"]
[152,"충북","충주","신제천S/S #2 TCSC CB","신제천S/S 345kV #1,2TCSC 하자보수","1. C&P 하자보수 2. 냉각설비 하자보수 3. 전력설비 하자보수 4. 옥외설비 (플랫폼) 하단 제초작업","2023-09-16 09:00","2023-09-18 18:00","2023-09-16 09:00","2023-09-18 18:00","연속"]
[153,"충북","충주","신제천S/S CB 7971","22-23년 충주전력지사 변전정비 총액공사","신제천S/S 345kV 신제천-동해#1T/L 및 동해#1T/L-TIE GIS 보통점검","2023-09-14 09:00","2023-09-14 18:00","취소","취소","연속"]
[154,"충북","충주","신제천S/S #1 TCSC CB","신제천S/S 345kV #1,2TCSC 하자보수","1. C&P 하자보수 2. 냉각설비 하자보수 3. 전력설비 하자보수 4. 옥외설비 (플랫폼) 하단 제초작업","2023-09-13 09:00","2023-09-15 18:00","2023-09-13 09:00","2023-09-15 18:00","연속"]
[155,"충북","충주","신제천S/S CB 7471","22-23년 충주전력지사 변전정비 총액공사","신제천S/S 7471,7400 GIS 보통점검","2023-09-22 09:00","2023-09-22 18:00","취소","취소","연속"]
[156,"대전세종충남","대전","신계룡S/S #2 M.Tr","신계룡S/S #2M.Tr 1,2차 LA 초기점검","신계룡S/S #2M.Tr 1,2차 LA 초기점검","2023-09-25 09:00","2023-09-25 18:00","2023-09-25 09:00","2023-09-25 18:00","연속"]
[157,"대전세종충남","서산","당진T/P CB 7100","23년도 345kV 차단기 조작시험","23년도 345kV 장기미동작 차단기 조작시험","2023-09-21 14:00","2023-09-21 18:00","2023-09-21 14:00","2023-09-21 18:00","연속"]
[158,"대전세종충남","서산","당진T/P CB 7171","23년도 345kV 차단기 조작시험","23년도 345kV 장기미동작 차단기 조작시험","2023-09-21 10:00","2023-09-21 14:00","2023-09-21 10:00","2023-09-21 14:00","연속"]
[159,"대전세종충남","서산","북당진S/S CB 7172","23년 서산P/O 345kV GIS 보통점검공사","북당진S/S 345kV 7172 GIS 보통점검","2023-09-22 09:00","2023-09-22 18:00","2023-09-22 09:00","2023-09-22 18:00","연속"]
[160,"대전세종충남","서산","북당진S/S CB 7171","23년 서산P/O 345kV GIS 보통점검공사","북당진S/S 345kV 7171 GIS 보통점검","2023-09-20 09:00","2023-09-20 18:00","2023-09-20 09:00","2023-09-20 18:00","연속"]
[161,"대전세종충남","서산","북당진S/S CB 7100","23년 서산P/O 345kV GIS 보통점검공사","북당진S/S 345kV 7100 GIS 보통점검","2023-09-18 09:00","2023-09-18 18:00","2023-09-18 09:00","2023-09-18 18:00","연속"]
[162,"대전세종충남","서산","신당진개폐소 CB 7B71","23년 서산P/O 345kV GIS 보통점검공사","신당진개폐소 345kV 7B71 GIS 보통점검","2023-09-04 09:00","2023-09-04 18:00","2023-09-04 09:00","2023-09-04 18:00","연속"]
[163,"대전세종충남","서산","신당진개폐소 CB 7D00","23년 서산P/O 345kV GIS 보통점검공사","신당진개폐소 345kV 7D00 GIS 보통점검","2023-09-06 09:00","2023-09-06 18:00","2023-09-06 09:00","2023-09-06 18:00","연속"]
[164,"대전세종충남","서산","신당진개폐소 CB 7D71","23년 서산P/O 345kV GIS 보통점검공사","신당진개폐소 345kV 7D71 GIS 보통점검","2023-09-08 09:00","2023-09-08 18:00","2023-09-08 09:00","2023-09-08 18:00","연속"]
[165,"대전세종충남","서산","신당진S/S #2 M.Tr","23년 서산P/O 345kV이하 변압기 보통점검공사","신당진S/S 345kV #2M.Tr 보통점검 및 누유보수","2023-09-18 09:00","2023-09-22 18:00","2023-09-18 09:00","2023-09-22 18:00","연속"]
[166,"대전세종충남","서산","신당진S/S #1 M.Tr","23년 서산P/O 345kV이하 변압기 보통점검공사","신당진S/S 345kV #1M.Tr 보통점검 및 누유보수","2023-09-11 09:00","2023-09-15 18:00","2023-09-11 09:00","2023-09-15 18:00","연속"]
[167,"대전세종충남","서산","신서산S/S #4 Sh.R CB","23년 서산P/O 변전협력회사 총액공사","신서산S/S 345kV #4Sh.R 하자점검","2023-09-13 09:00","2023-09-13 18:00","2023-09-13 09:00","2023-09-13 18:00","연속"]
[168,"대전세종충남","서산","신서산S/S #5 Sh.R CB","23년 서산P/O 변전협력회사 총액공사","신서산S/S 345kV #5Sh.R 보통점검","2023-09-15 09:00","2023-09-15 18:00","2023-09-15 09:00","2023-09-15 18:00","연속"]
[169,"대전세종충남","서산","태안T/P CB 7372","23년 서산P/O 345kV GIS 보통점검공사","태안화력S/Y 345kV 7372 GIS 보통점검","2023-09-14 09:00","2023-09-14 18:00","2023-09-14 09:00","2023-09-14 18:00","연속"]
[170,"대전세종충남","서산","태안T/P CB 7300","23년 서산P/O 345kV GIS 보통점검공사","태안화력S/Y 345kV 7300 GIS 보통점검","2023-09-12 09:00","2023-09-12 18:00","2023-09-12 09:00","2023-09-12 18:00","연속"]
[171,"대전세종충남","서산","태안T/P CB 7871","23년 서산P/O 345kV GIS 보통점검공사","태안화력S/Y 345kV 7871 GIS 보통점검 및 보조계전기 교체","2023-09-25 09:00","2023-09-26 18:00","2023-09-25 09:00","2023-09-26 18:00","연속"]
[172,"대전세종충남","서산","태안T/P #71 BUS","태안화력S/Y 345kV 현대제 차단기 조작로드 교체공사","태안화력S/Y 345kV 71-72-0 CB 조작로드 교체공사 - CB 상부에 71BUS 위치하여 BUS 휴전필요","2023-09-11 09:00","2023-09-22 18:00","취소","취소","연속"]
[173,"대전세종충남","천안","신온양신탕정#2 T/L","(7월취소시)신온양S/S 345kV 78B/F 교체 및 결상회로 보완작업","(7월취소시)신온양S/S 345kV 78B/F 교체 및 결상회로 보완작업","2023-09-22 09:00","2023-09-27 18:00","취소","취소","연속"]
[174,"대전세종충남","천안","신온양서서울#1 T/L","(7월취소시)신온양S/S 345kV 78B/F 교체 및 결상회로 보완작업","(7월취소시)신온양S/S 345kV 78B/F 교체 및 결상회로 보완작업","2023-09-22 09:00","2023-09-27 18:00","취소","취소","연속"]
[175,"대전세종충남","천안","신온양서서울#2 T/L","(8월취소시)신온양S/S 345kV 77B/F 교체 및 결상회로 보완작업","(8월취소시)신온양S/S 345kV 77B/F 교체 및 결상회로 보완작업","2023-09-18 09:00","2023-09-21 18:00","취소","취소","연속"]
[176,"대전세종충남","천안","신온양S/S #4 M.Tr","(8월취소시)신온양S/S 345kV 77B/F 교체 및 결상회로 보완작업","(8월취소시)신온양S/S 345kV 77B/F 교체 및 결상회로 보완작업","2023-09-18 09:00","2023-09-21 18:00","2023-09-18 09:00","2023-09-21 18:00","연속"]
[177,"대전세종충남","천안","신온양S/S CB 7700","신온양S/S 345kV 7700 GIS 보통점검","신온양S/S 345kV 7700 GIS 보통점검","2023-09-06 09:00","2023-09-06 18:00","2023-09-06 09:00","2023-09-06 18:00","연속"]
[178,"대전세종충남","천안","신탕정S/S #2 M.Tr","신탕정S/S 345kV #2M.Tr 부싱관련 누유보수","신탕정S/S 345kV #2M.Tr 부싱관련 누유보수","2023-09-21 09:00","2023-09-22 18:00","2023-09-21 09:00","2023-09-22 18:00","연속"]
[179,"대전세종충남","천안","아산보령TP#1 T/L","아산S/S 23kV #1-2Sh.R 설치관련 안전이격 휴전","아산S/S 23kV #1-2Sh.R 설치관련 안전이격 휴전","2023-09-11 09:00","2023-09-11 18:00","2023-09-11 09:00","2023-09-11 18:00","연속"]
[180,"대전세종충남","천안","아산S/S #1 M.Tr","아산S/S 23kV #1-2Sh.R 설치관련 무부하가압","아산S/S 23kV #1-2Sh.R 설치관련 무부하가압","2023-09-18 09:00","2023-09-19 18:00","2023-09-18 09:00","2023-09-19 18:00","연속"]
[181,"대전세종충남","천안","신서산아산#1 T/L","아산S/S 345kV 신서산-아산#1T/L LA, CVT 보통점검","아산S/S 345kV 신서산-아산#1T/L LA, CVT 보통점검","2023-09-20 09:00","2023-09-20 18:00","2023-09-20 09:00","2023-09-20 18:00","연속"]
[182,"대전세종충남","천안","아산S/S CB 7171","아산SS 345kV 7171CB 보통점검","아산SS 345kV 7171CB 보통점검","2023-09-20 09:00","2023-09-20 18:00","취소","취소","연속"]
[183,"대전세종충남","천안","아산보령TP#2 T/L","아산S/S 345kV 아산-보령화력#2T/L LA, CVT 보통점검","아산S/S 345kV 아산-보령화력#2T/L LA, CVT 보통점검","2023-09-21 09:00","2023-09-21 18:00","2023-09-21 09:00","2023-09-21 18:00","연속"]
[184,"대전세종충남","천안","아산S/S CB 7172","아산SS 345kV 7172CB 보통점검","아산SS 345kV 7172CB 보통점검","2023-09-21 09:00","2023-09-21 18:00","취소","취소","연속"]
[185,"대전세종충남","천안","아산화성#2 T/L","아산S/S 345kV 아산-화성#2T/L LA, CVT 보통점검","아산S/S 345kV 아산-화성#2T/L LA, CVT 보통점검","2023-09-22 09:00","2023-09-22 18:00","2023-09-22 09:00","2023-09-22 18:00","연속"]
[186,"대전세종충남","천안","아산S/S CB 7271","아산SS 345kV 7271, 7200CB 보통점검","아산SS 345kV 7271, 7200CB 보통점검","2023-09-22 09:00","2023-09-22 14:00","취소","취소","연속"]
[187,"대전세종충남","천안","아산S/S #2 M.Tr","아산S/S 345kV #2M.Tr 부싱절연유 채유","아산S/S 345kV #2M.Tr 부싱절연유 채유","2023-09-25 09:00","2023-09-25 18:00","2023-09-25 09:00","2023-09-25 18:00","연속"]
[188,"대전세종충남","천안","아산S/S CB 7200","아산SS 345kV 7271, 7200CB 보통점검","아산SS 345kV 7271, 7200CB 보통점검","2023-09-22 14:00","2023-09-22 18:00","취소","취소","연속"]
[189,"대전세종충남","청양","보령C/C CB 7472","청양P/O 362kV GIS 보통점검공사","보령C/C 362kV 7472 GIS 보통점검","2023-09-27 10:00","2023-09-27 18:00","2023-09-27 10:00","2023-09-27 18:00","연속"]
[190,"대전세종충남","청양","보령C/C CB 7471","청양P/O 362kV GIS 보통점검공사","보령C/C 362kV 7471 GIS 보통점검","2023-09-26 10:00","2023-09-26 18:00","2023-09-26 10:00","2023-09-26 18:00","연속"]
[191,"대전세종충남","청양","보령C/C CB 7400","청양P/O 362kV GIS 보통점검공사","보령C/C 362kV 7400 GIS 보통점검","2023-09-25 10:00","2023-09-25 18:00","2023-09-25 10:00","2023-09-25 18:00","연속"]
[192,"대전세종충남","청양","청양S/S CB 7472","청양P/O 362kV GIS 보통점검공사","청양S/S 362kV 7472 GIS 보통점검","2023-09-06 08:00","2023-09-06 18:00","2023-09-06 08:00","2023-09-06 18:00","연속"]
[193,"대전세종충남","청양","청양S/S CB 7500","청양P/O 362kV GIS 보통점검공사","청양S/S 362kV 7500 GIS 보통점검","2023-09-07 08:00","2023-09-07 18:00","2023-09-07 08:00","2023-09-07 18:00","연속"]
[194,"대전세종충남","청양","청양신보령TP T/L","청양P/O 변전협력회사 총액공사","345kV 청양-신보령T/L - 청양S/S LA 초기점검(A,B,C) 및 GIS 보통점검(7271)","2023-09-11 07:30","2023-09-11 18:00","취소","취소","연속"]
[195,"대전세종충남","청양","신옥천청양 T/L","(8월 취소시)[송전] 345kV 신옥천-청양등 2개TL추락방지 설치공사","(8월 취소시)[송전] 345kV 신옥천-청양T/L 추락방지장치 설치공사","2023-09-11 08:00","2023-09-22 18:00","취소","취소","매일"]
[196,"대전세종충남","청양","청양S/S #2 M.Tr","청양P/O 변전협력회사 총액공사","청양S/S 345kV #2M.Tr - 345kV 7772(화), 7700(수) GIS 보통점검(병행) - 170kV 6244 GIS 보통점검(목~금 병행) - 25.8kV VCB 부동작예방 조작시험(4279-1, 4279-2) / 4279 VCB 하자점검 / 4276 DS 보통점검 - 23kV #2-1, #2-2 Sh.R 보통점검","2023-09-12 07:30","2023-09-15 18:00","2023-09-12 07:30","2023-09-15 18:00","연속"]
[197,"대전세종충남","청양","청양S/S CB 7772","(345kV #2M.Tr 취소시)청양P/O 362kV GIS 보통점검공사","청양S/S 362kV 7772 GIS 보통점검","2023-09-12 08:00","2023-09-12 18:00","취소","취소","연속"]
[198,"대전세종충남","청양","청양S/S CB 7700","(345kV #2M.Tr 취소시)청양P/O 362kV GIS 보통점검공사","청양S/S 362kV 7700 GIS 보통점검","2023-09-13 08:00","2023-09-13 18:00","취소","취소","연속"]
[199,"대전세종충남","청양","청양S/S #1 M.Tr","청양P/O 변전협력회사 총액공사","청양S/S 345kV #1M.Tr - #1M.Tr 보통점검(예비변압기 포함) / 7671, 7600 차단기 부동작예방 조작시험 / 170kV 6144 GIS 보통점검(병행,화~수) - 3차측 VCB 대체(4179, 4189, 4179-1) / 4179-2 VCB 조작시험 / 4176, 4186, 4176-1 DS 보통점검 - AC, DC 분전반 대체(#1M.Tr용 AC/DC 1면) / 부싱절연유채유","2023-09-18 07:30","2023-09-22 18:00","2023-09-18 07:30","2023-09-22 18:00","연속"]
[200,"대전세종충남","청양","청양S/S 예비 M.Tr CB","청양P/O 변전협력회사 총액공사","청양S/S 345kV #1M.Tr - #1M.Tr 보통점검(예비변압기 포함) / 7671, 7600 차단기 부동작예방 조작시험 / 170kV 6144 GIS 보통점검(병행,화~수) - 3차측 VCB 대체(4179, 4189, 4179-1) / 4179-2 VCB 조작시험 / 4176, 4186, 4176-1 DS 보통점검 - AC, DC 분전반 대체(#1M.Tr용 AC/DC 1면) / 부싱절연유채유","2023-09-18 07:30","2023-09-22 18:00","취소","취소","연속"]
[201,"대전세종충남","청양","청양S/S SEC CB 75760","청양P/O 변전협력회사 총액공사","362kV GIS 차단기 조작시험 (상시개방) - 75-76-0","2023-09-26 16:00","2023-09-26 18:00","2023-09-26 16:00","2023-09-26 18:00","연속"]
[202,"대전세종충남","청양","청양S/S SEC CB 70710","청양P/O 변전협력회사 총액공사","362kV GIS 차단기 조작시험 (상시개방) - 70-71-0","2023-09-26 18:00","2023-09-26 20:00","2023-09-26 18:00","2023-09-26 20:00","연속"]
[203,"대전세종충남","청양","청양S/S CB 7372","청양P/O 362kV GIS 보통점검공사","청양S/S 362kV 7372 GIS 보통점검","2023-09-05 08:00","2023-09-05 18:00","취소","취소","연속"]
[204,"대전세종충남","청양","청양군산#1 T/L","[송전] 345kV 청양-군산#1T/L No.94 철탑 변형개소 보강공사","345kV 청양-군산#1T/L No.94 철탑 가공지선 암 부재 변형개소 보강공사 ※ 태풍시기 도래 전 조치 필요","2023-09-04 07:00","2023-09-07 18:00","2023-09-04 07:00","2023-09-07 18:00","매일"]
[205,"대전세종충남","청양","청양S/S CB 7371","청양P/O 362kV GIS 보통점검공사","청양S/S 362kV 7371 GIS 보통점검","2023-09-01 08:00","2023-09-01 18:00","2023-09-01 08:00","2023-09-01 18:00","연속"]
[206,"대전세종충남","청양","청양S/S CB 7271","(청양-신보령T/L 취소시)청양P/O 362kV GIS 보통점검공사","청양S/S 362kV 7271 GIS 보통점검","2023-09-11 08:00","2023-09-11 18:00","2023-09-11 08:00","2023-09-11 18:00","연속"]
[207,"전북","군산","새만금S/S #3 M.Tr","새만금S/S #3M.Tr TPI 구성변경 및 연동시험","□ 새만금S/S #3M.Tr TPI 구성변경 및 OLTC TAP 연동시험 - 작업내용 : #3M.Tr 휴전 후 LCP 내부 T/D 설치 및 Tap 연동시험 - 시공회사 : 유호전기공업(주) - 작업기간 : ‘23. 9. 26(화) 09:00 ~ 9. 27(수) 18:00 - 업무담당 : 예방정비팀 권형주, 이진영","2023-09-26 09:00","2023-09-27 18:00","2023-09-11 09:00","2023-09-12 18:00","연속"]
[208,"전북","김제","신김제S/S #2 M.Tr","신김제S/S 345kV #2M.Tr 2차 GIS 보통점검","신김제S/S 345kV #2M.Tr 2차 GIS 보통점검","2023-09-26 09:00","2023-09-26 18:00","2023-09-26 09:00","2023-09-26 18:00","연속"]
[209,"전북","김제","신김제S/S CB 7600","신김제S/S 345kV #3M.Tr 1차-TIE(단독) GIS 보통점검","신김제S/S 345kV #3M.Tr 1차-TIE(단독) GIS 보통점검","2023-09-18 09:00","2023-09-18 18:00","2023-09-18 09:00","2023-09-18 18:00","연속"]
[210,"전북","김제","신김제S/S #1 M.Tr","신김제S/S 345kV #1M.Tr 2차 GIS 보통점검","신김제S/S 345kV #1M.Tr 2차 GIS 보통점검","2023-09-25 09:00","2023-09-25 18:00","2023-09-25 09:00","2023-09-25 18:00","연속"]
[211,"전북","직할","신남원S/S CB 7100","신옥천-신남원#2T/L(7100 CB) 단일차단기 보통점검","345kV급 단일차단기 보통점검","2023-09-25 09:00","2023-09-25 18:00","취소","취소","연속"]
[212,"전북","직할","신남원광양#1 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 75Bay BF 보호배전반 대체 및 LA, CVT 보통점검","2023-09-04 09:00","2023-09-08 18:00","취소","취소","연속"]
[213,"전북","직할","신남원S/S CB 7600","신남원S/S 345kV 단일차단기 보통점검(즉시가압 가능)","신남원S/S 345kV 단일차단기 보통점검(즉시가압 가능)","2023-09-18 09:00","2023-09-18 18:00","2023-09-18 09:00","2023-09-18 18:00","연속"]
[214,"전북","직할","신남원의령#2 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 74Bay BF 보호배전반 대체 및 CVT 보통점검","2023-09-11 09:00","2023-09-15 18:00","취소","취소","연속"]
[215,"전북","직할","신남원한빛NP#2 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 71Bay BF 보호배전반 대체 및 LA 보통점검","2023-09-24 09:00","2023-09-28 18:00","취소","취소","연속"]
[216,"전북","직할","신남원한빛NP#1 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 72Bay BF 보호배전반 대체","2023-09-19 09:00","2023-09-23 18:00","취소","취소","연속"]
[217,"전북","직할","신남원신광주#1 T/L","23년 전북직할 변전협력회사 총액공사","신남원S/S 345kV 신남원-신광주 #1T/L LA, CVT 보통점검","2023-09-01 09:00","2023-09-01 18:00","취소","취소","연속"]
[218,"전북","직할","신옥천신남원#1 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 72Bay BF 보호배전반 대체 및 CVT 보통점검","2023-09-19 09:00","2023-09-23 18:00","취소","취소","연속"]
[219,"전북","직할","신옥천신남원#2 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 71Bay BF 보호배전반 대체 및 LA 보통점검","2023-09-24 09:00","2023-09-28 18:00","취소","취소","연속"]
[220,"전북","직할","신남원신광주#2 T/L","23년 전북직할 변전협력회사 총액공사","신남원S/S 345kV 신남원-신광주 #2T/L LA 보통점검","2023-09-18 09:00","2023-09-18 18:00","취소","취소","연속"]
[221,"광주전남","강진","신강진S/S #1 M.Tr","2022~23년도 강진전력지사 변전협력회사 총액공사","2022~23년도 강진전력지사 변전협력회사 총액공사 신강진 #1M.Tr A,B,C 1차부싱 절연열화 측정","2023-09-26 08:00","2023-09-26 11:00","2023-09-26 08:00","2023-09-26 11:00","연속"]
[222,"광주전남","강진","신화순신강진#1 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","철탑 추락방지장치(수직, 수평) 설치공사","2023-09-11 07:00","2023-09-22 18:00","2023-09-11 07:00","2023-09-22 18:00","매일"]
[223,"광주전남","강진","신강진S/S #4 M.Tr","2022~23년도 강진전력지사 변전협력회사 총액공사","2022~23년도 강진전력지사 변전협력회사 총액공사 #4M.Tr A,B,C 1차부싱 절연열화 측정","2023-09-26 14:00","2023-09-26 18:00","2023-09-26 14:00","2023-09-26 18:00","연속"]
[224,"광주전남","강진","신강진S/S #2 M.Tr","2022~23년도 강진전력지사 변전협력회사 총액공사","2022~23년도 강진전력지사 변전협력회사 총액공사 신강진 #2M.Tr A,B,C 1차부싱 절연열화 측정","2023-09-26 11:00","2023-09-26 14:00","2023-09-26 11:00","2023-09-26 14:00","연속"]
[225,"광주전남","광주","신광주신화순#1 T/L","23년 광주전력지사 변전협력회사 총액공사","- 76BAY 차단실패보호반 교체","2023-09-04 09:00","2023-09-14 18:00","취소","취소","연속"]
[226,"광주전남","광주","신광주S/S CB 7171","7171 GIS 보통점검","7171 GIS 보통점검","2023-09-25 08:00","2023-09-25 18:00","취소","취소","연속"]
[227,"광주전남","광주","신광주S/S CB 7200","7200 CB 조작시험","7200 CB 조작시험","2023-09-26 08:00","2023-09-26 18:00","취소","취소","연속"]
[228,"광주전남","광주","신광주한빛NP#2 T/L","7200 CB 조작시험,CVT 보통점검","7200 CB 조작시험,CVT 보통점검","2023-09-26 08:00","2023-09-26 18:00","취소","취소","연속"]
[229,"광주전남","광주","신광주S/S #3 M.Tr","23년 광주전력지사 변전협력회사 총액공사","- 76BAY 차단실패보호반 교체 - 345kV M.Tr 보통점검 - 362kV GIS 조작시험(7600,7672) - #3M.Tr 3차 차단기 교체(3차 Main, #1,2Sh.R, S.Tr) - 3차측 DS 점검","2023-09-04 09:00","2023-09-14 18:00","취소","취소","연속"]
[230,"광주전남","광주","신광주S/S #2 BUS","장기사용 345kV #2BUS 모선보호반 교체","장기사용 345kV #2BUS 모선보호반 교체","2023-09-25 08:00","2023-09-28 18:00","취소","취소","연속"]
[231,"광주전남","광주","신광주S/S #1 M.Tr","23년 광주전력지사 변전협력회사 총액공사","- #1M.Tr 3차 차단기 교체(3차 Main)","2023-09-20 09:00","2023-09-22 18:00","취소","취소","연속"]
[232,"광주전남","광주","신광주S/S CB 7172","7172 GIS 보통점검","7172 GIS 보통점검","2023-09-20 08:00","2023-09-20 18:00","취소","취소","연속"]
[233,"광주전남","광주","신남원신광주#2 T/L","2023년 가공송전선로 순시점검 위탁공사(과열정비)","345kV 신남원-신광주 #2T/L 137호 A,C상 과열개소 정비","2023-09-18 13:00","2023-09-18 16:00","취소","취소","연속"]
[234,"광주전남","광주","신광주S/S #2 M.Tr","23년 광주전력지사 변전협력회사 총액공사","- #2M.Tr 3차 차단기 교체(3차 Main)","2023-09-18 09:00","2023-09-19 18:00","취소","취소","연속"]
[235,"광주전남","광주","신남원신광주#1 T/L","2023년 가공송전선로 순시점검 위탁공사(과열정비)","345kV 신남원-신광주 #1T/L 137호 A,B,C상 과열개소 정비","2023-09-18 09:00","2023-09-18 12:00","취소","취소","연속"]
[236,"광주전남","광주","신광주S/S #1 BUS","장기사용 345kV #1BUS 모선보호반 교체","장기사용 345kV #1BUS 모선보호반 교체","2023-09-18 08:00","2023-09-21 18:00","취소","취소","연속"]
[237,"광주전남","광주","신광주S/S CB 7672","7672 CB 조작시험","7672 CB 조작시험","2023-09-13 08:00","2023-09-13 18:00","2023-09-13 08:00","2023-09-13 18:00","연속"]
[238,"광주전남","광주","신화순신강진#2 T/L","신화순S/S 345kV 신화순-신강진 #2T/L (유사고장)","345kV 세니온제 보호계전기 성능개선","2023-09-18 09:00","2023-09-18 18:00","2023-09-18 09:00","2023-09-18 18:00","연속"]
[239,"광주전남","순천","광양CC여수TP#2 T/L","345kV 광양CC-신여수 지중T/L 운영시스템,온라인PD 설치공사","지중송전선로와 부대설비에 대한 실시간 감시, 제어를 통한 안정적인 전력공급(휴전작업공정 : EBA,EBG 센서 및 카메라 설치작업) 즉시가압여부 : 가능, 소요시간 20분","2023-09-20 09:00","2023-09-21 18:00","2023-09-20 09:00","2023-09-21 18:00","매일"]
[240,"광주전남","순천","광양CC여수TP#1 T/L","345kV 광양CC-신여수 지중T/L 운영시스템,온라인PD 설치공사","지중송전선로와 부대설비에 대한 실시간 감시, 제어를 통한 안정적인 전력공급(휴전작업공정 : EBA,EBG 센서 및 카메라 설치작업) 즉시가압여부 : 가능, 소요시간 20분","2023-09-18 09:00","2023-09-19 18:00","2023-09-18 09:00","2023-09-19 18:00","매일"]
[241,"광주전남","순천","신강진광양#2 T/L","광양S/S 362kV GIS 용량부족 GIS 교체공사(안전이격)","광양S/S 362kV GIS 용량부족 GIS 교체공사(철구 기초보강) - 77BAY측 철구 기초 보강을 위해 안전이격 휴전","2023-09-05 08:00","2023-09-06 18:00","2023-09-05 08:00","2023-09-06 18:00","연속"]
[242,"광주전남","순천","신강진광양#1 T/L","광양S/S 362kV GIS 용량부족 GIS 교체공사(안전이격)","광양S/S 362kV GIS 용량부족 GIS 교체공사(철구 기초보강) - 77BAY측 철구 기초 보강을 위해 안전이격 휴전","2023-09-04 08:00","2023-09-04 18:00","2023-09-04 08:00","2023-09-04 18:00","연속"]
[243,"광주전남","순천","광양S/S SEC CB 70710","22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 70-71 BUS-SEC GIS 하자점검","2023-09-11 09:00","2023-09-11 18:00","2023-09-11 09:00","2023-09-11 18:00","연속"]
[244,"광주전남","순천","광양율촌CC T/L","22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 광양-율촌CC T/L LA 보통점검 CVT 하자점검(즉시가압가능)","2023-09-14 09:00","2023-09-14 18:00","2023-09-14 09:00","2023-09-14 18:00","연속"]
[245,"광주전남","순천","신강진광양#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 신강진-광양 #1T/L LA 보통점검(즉시가압가능)","2023-09-18 09:00","2023-09-18 18:00","취소","취소","연속"]
[246,"광주전남","순천","신강진광양#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 신강진-광양 #2T/L LA 보통점검(즉시가압가능)","2023-09-19 09:00","2023-09-19 18:00","취소","취소","연속"]
[247,"광주전남","순천","신강진광양#1 T/L","광양S/S 362kV GIS 용량부족 GIS 교체공사(안전이격)","광양S/S 362kV GIS 용량부족 GIS 교체공사(철구 기초보강) - 77BAY측 철구 기초 보강을 위해 안전이격 휴전","2023-09-20 08:00","2023-09-20 18:00","2023-09-20 08:00","2023-09-20 18:00","연속"]
[248,"광주전남","순천","신강진광양#2 T/L","광양S/S 362kV GIS 용량부족 GIS 교체공사(안전이격)","광양S/S 362kV GIS 용량부족 GIS 교체공사(철구 기초보강) - 77BAY측 철구 기초 보강을 위해 안전이격 휴전","2023-09-21 08:00","2023-09-22 18:00","2023-09-21 08:00","2023-09-22 18:00","연속"]
[249,"광주전남","순천","여수T/P #1 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S #1M.Tr A,B상 1차 부싱교체, 예비M.Tr 1차 부싱교체, 2차 GIS 정밀점검, 1,2차 LA 초기점검, 4184,4179-1,4189 타임측정 및 A상 권선온도계 교체(즉시가압불가)","2023-09-18 09:00","2023-09-22 18:00","취소","취소","연속"]
[250,"광주전남","순천","여수T/P CB 7471","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S 광양-여수TPT/L(7471) GIS 하자점검(즉시가압 가능)","2023-09-01 09:00","2023-09-01 18:00","2023-09-01 09:00","2023-09-01 18:00","연속"]
[251,"광주전남","순천","여수T/P CB 7400","22-23년 순천전력지사 변전협력회사 총액공사","광양-여수TP T/L-#4 M.Tr 1차 CB A(7400) GIS 하자점검(즉시가압 가능)","2023-09-04 09:00","2023-09-04 18:00","취소","취소","연속"]
[252,"광주전남","순천","여수T/P #4 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","여수화력 #4M.Tr 하자점검","2023-09-04 09:00","2023-09-08 18:00","2023-09-04 09:00","2023-09-08 18:00","연속"]
[253,"광주전남","순천","여수T/P CB 7472","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S #4M.Tr 1차 GIS(7472) GIS 하자점검(즉시가압 가능)","2023-09-05 09:00","2023-09-05 18:00","취소","취소","연속"]
[254,"광주전남","순천","여수T/P #2 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S #2M.Tr 보통점검(즉시가압가능)","2023-09-11 09:00","2023-09-15 18:00","2023-09-11 09:00","2023-09-15 18:00","연속"]
[255,"광주전남","순천","광양율촌CC T/L","345kV 율촌CC분기 T/L EBA 자기애관 교체공사","광양-율촌CC 3상, 율촌CC-여수TP 3상 애관교체(자기애관 → 폴리머애관) 즉시가압여부 : 가능, 소요시간 30분","2023-09-18 09:00","2023-09-20 18:00","취소","취소","연속"]
[256,"광주전남","순천","율촌CC여수TP T/L","345kV 율촌CC분기 T/L EBA 자기애관 교체공사","광양-율촌CC 3상, 율촌CC-여수TP 3상 애관교체(자기애관 → 폴리머애관) 즉시가압여부 : 가능, 소요시간 30분","2023-09-13 09:00","2023-09-15 18:00","취소","취소","연속"]
[257,"대구","달성","북경남고령#2 T/L","서대구-고령T/L OPGW 증설공사 관련 안전확보 휴전(북경남-고령2)","[안전확보]서대구-고령T/L OPGW 증설공사에 따른 작업인근 선로 휴전 - 작업구간 : 서대구-고령T/L S/T ~ No.5호","2023-09-19 07:00","2023-09-20 18:00","2023-09-19 07:00","2023-09-20 18:00","연속"]
[258,"대구","달성","서대구고령#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 서대구-고령T/L 수평 추락방지장치 설치공사(345kV 고령-의령,154kV 서대구-남구미 T/L 병가선로)(안전확보)","2023-09-13 07:00","2023-09-27 18:00","2023-09-13 07:00","2023-09-27 18:00","연속"]
[259,"대구","달성","고령의령#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 서대구-고령T/L 수평 추락방지장치 설치공사(345kV 고령-의령,154kV 서대구-남구미 T/L 병가선로)(안전확보)","2023-09-18 07:00","2023-09-24 18:00","2023-09-18 07:00","2023-09-24 18:00","연속"]
[260,"대구","달성","대구S/S #1 M.Tr","#1M.Tr 보호PNL 대체 및 2차 LA 초기점검","#1M.Tr 보호PNL 대체 및 2차 LA 초기점검","2023-09-18 09:00","2023-09-22 18:00","2023-09-18 09:00","2023-09-22 18:00","연속"]
[261,"대구","칠곡","북대구S/S #3 M.Tr","북대구S/S #3M.Tr 보통점검","북대구S/S #3M.Tr 보통점검","2023-09-13 09:30","2023-09-14 18:00","2023-09-13 09:30","2023-09-14 18:00","연속"]
[262,"대구","칠곡","북대구S/S CB 7200","북대구S/S 345kV GIS 장기미동작점검(7200)","북대구S/S 345kV GIS 장기미동작점검(7200)","2023-09-01 09:30","2023-09-01 14:00","2023-09-01 09:30","2023-09-01 14:00","연속"]
[263,"대구","칠곡","북대구S/S CB 7272","북대구S/S 345kV GIS 장기미동작점검(7272)","북대구S/S 345kV GIS 장기미동작점검(7272)","2023-09-01 14:00","2023-09-01 18:00","2023-09-01 14:00","2023-09-01 18:00","연속"]
[264,"대구","칠곡","북대구S/S #2 M.Tr","북대구S/S #2M.Tr 보통점검","북대구S/S #2M.Tr 보통점검","2023-09-11 09:30","2023-09-12 18:00","2023-09-11 09:30","2023-09-12 18:00","연속"]
[265,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S #4M.Tr LA 및 PT 보통점검","서대구S/S #4M.Tr LA 및 PT 보통점검","2023-09-22 09:30","2023-09-22 18:00","2023-09-22 09:30","2023-09-22 18:00","연속"]
[266,"대구","칠곡","서대구S/S #3 M.Tr","서대구S/S #3M.Tr PT 및 7671,7600 GCB 점검","서대구S/S 345kV #3M.Tr PT 및 7671,7600 GCB 점검","2023-09-21 09:30","2023-09-21 18:00","2023-09-21 09:30","2023-09-21 18:00","연속"]
[267,"대구","칠곡","서대구S/S CB 7872","서대구S/S 345kV GCB 보통점검(7872)","서대구S/S 345kV GCB 보통점검(7872)","2023-09-05 09:30","2023-09-05 18:00","2023-09-05 09:30","2023-09-05 18:00","연속"]
[268,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S 345kV #1M.Tr LA, PT, GCB, DS 점검","서대구S/S 345kV #1M.Tr LA, PT, GCB, DS 점검","2023-09-18 09:30","2023-09-19 18:00","2023-09-18 09:30","2023-09-19 18:00","연속"]
[269,"대구","칠곡","서대구S/S #2 M.Tr","서대구S/S 345kV #2M.Tr LA, PT 보통점검","서대구S/S 345kV #2M.Tr LA, PT 보통점검","2023-09-20 09:30","2023-09-20 18:00","2023-09-20 09:30","2023-09-20 18:00","연속"]
[270,"대구","포항","선산신포항 T/L","345kV 영포 외 15개 T/L 추락방지장치 설치 등 송전정비공사","345kV 선산-신포항T/L 수평 추락방지장치 설치","2023-09-18 07:00","2023-09-27 18:00","취소","취소","연속"]
[271,"대구","포항","신포항북대구 T/L","345kV 영포 외 15개 T/L 추락방지장치 설치 등 송전정비공사","345kV 신포항-북대구T/L 수평 추락방지장치 설치","2023-09-01 07:00","2023-09-15 18:00","2023-09-01 07:00","2023-09-15 18:00","연속"]
[272,"경북","구미","선산S/S #4 M.Tr","2022-23년 구미전력지사 변전협력업체 총액공사","- 1,2차 부싱 절연유 채유 - 1,2,3차 LA 보통점검 - TCC PNL DC 전원 분리 - 7700, 7772 GIS 초기점검","2023-09-06 09:00","2023-09-08 18:00","2023-09-06 09:00","2023-09-08 18:00","연속"]
[273,"경북","구미","선산S/S #3 M.Tr","2022-23년 구미전력지사 변전협력업체 총액공사","- TCC PNL 제어케이블 철거 및 이설","2023-09-22 09:00","2023-09-27 18:00","2023-09-22 09:00","2023-09-27 18:00","연속"]
[274,"경북","구미","선산신포항 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사(4차)","○ 7451DS 교체","2023-09-18 09:00","2023-09-27 18:00","2023-09-18 09:00","2023-09-27 18:00","연속"]
[275,"경북","구미","선산S/S #70 BUS","선산S/S 345kV 장기사용 GIS 용량교체공사(4차)","○ 7451DS 교체","2023-09-18 09:00","2023-09-27 18:00","2023-09-18 09:00","2023-09-27 18:00","연속"]
[276,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사(4차)","○ 73BAY 75BUS 단상모선 교체 무부하 가압","2023-09-15 16:00","2023-09-18 09:00","2023-09-15 16:00","2023-09-18 09:00","연속"]
[277,"경북","구미","선산S/S #75 BUS","선산S/S 345kV 장기사용 GIS 용량교체공사(4차)","○ 73BAY 75BUS 단상모선 교체","2023-09-11 09:00","2023-09-18 09:00","2023-09-11 09:00","2023-09-18 09:00","연속"]
[278,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사(4차)","○ 7451DS 교체 무부하 가압","2023-09-26 16:00","2023-09-27 18:00","2023-09-26 16:00","2023-09-27 18:00","연속"]
[279,"경북","영주","신제천신영주#2 T/L","2023년 가공송전 순시점검 위탁공사 정밀점검","345kV 신제천-신영주T/L 정밀점검","2023-09-22 09:00","2023-09-27 18:00","2023-09-22 09:00","2023-09-27 18:00","매일"]
[280,"경북","영주","신영주S/S STATCOM CB","영주전력지사 신영주S/S 345kV STATCOM 성능개선공사","영주전력지사 신영주S/S 345kV STATCOM 성능개선공사","2023-09-19 09:00","2023-10-16 18:00","2023-09-19 09:00","2023-10-16 18:00","연속"]
[281,"경북","영주","신제천신영주#1 T/L","2023년 가공송전 순시점검 위탁공사 정밀점검","345kV신영주-신제천T/L 정밀점검","2023-09-18 09:00","2023-09-21 18:00","2023-09-18 09:00","2023-09-21 18:00","매일"]
[282,"경북","영주","한울2NP한울3NP#4 T/L","22-23년 영주전력지사 변전협력회사 총액공사","- 초고압 애자 절연 코팅공사","2023-09-25 09:00","2023-09-27 18:00","2023-09-25 09:00","2023-09-27 18:00","연속"]
[283,"경북","영주","한울2NP한울3NP#3 T/L","22-23년 영주전력지사 변전협력회사 총액공사","- 초고압 애자 절연 코팅공사","2023-09-07 09:00","2023-09-09 18:00","2023-09-07 09:00","2023-09-09 18:00","연속"]
[284,"경북","영주","신한울한울#2 T/L","한울3발S/Y 345kV 7E21DS 가스누기 불량보수","- 한울3발S/Y 345kV 7E21DS 가스누기 불량보수","2023-09-04 09:00","2023-09-06 18:00","2023-09-04 09:00","2023-09-06 18:00","연속"]
[285,"부산울산","동부산","신양산신대연#2 T/L","2023년 가공송전 순시점검 위탁공사 정밀점검","345kV 신양산-신대연 #2T/L 정밀점검 및 피뢰기 갭혼 교체 작업","2023-09-20 09:00","2023-09-22 18:00","2023-09-20 09:00","2023-09-22 18:00","연속"]
[286,"부산울산","동부산","신양산S/S #4 M.Tr","신양산S/S #4M.Tr 주변압기 보통점검","신양산S/S #4M.Tr 주변압기 보통점검 병행)7672,7600GIS 보통점검 병행)부싱절연유 채유 병행) #4M.Tr 3차 SIS 초기점검 병행)#2S.Tr SIS 초기점검 병행)#4-1,4-2Sh.R SIS 초기점검","2023-09-18 09:00","2023-09-19 18:00","2023-09-18 09:00","2023-09-19 18:00","연속"]
[287,"부산울산","북부산","서부산북부산#3 T/L","23년 북부산전력지사 345kV GIS 정밀점검공사","북부산S/S 345kV #3Sh.R GIS 정밀점검 시험가압 - 시험가압선로 : 서부산-북부산#3T/L","2023-09-09 18:00","2023-09-09 19:00","2023-09-09 18:00","2023-09-09 19:00","연속"]
[288,"부산울산","북부산","북부산S/S CB 7871","23년 북부산전력지사 345kV GIS 정밀점검공사","북부산S/S 345kV 서부산-북부산#3T/L GIS 정밀점검 - 점검대상 : 7871 GIS","2023-09-04 08:00","2023-09-09 18:00","취소","취소","연속"]
[289,"부산울산","북부산","북부산S/S #3 Sh.R CB","23년 북부산전력지사 345kV GIS 정밀점검공사","북부산S/S 345kV #3Sh.R GIS 정밀점검 - 점검대상 : 7877 GIS","2023-09-06 08:00","2023-09-09 18:00","2023-09-06 08:00","2023-09-09 18:00","연속"]
[290,"부산울산","북부산","북부산울산TP#1 T/L","345kV 북부산-신울산 등 3개T/L 수평추락방지장치 설치공사","345kV 북부산-울산TP#1T/L 수평추락방지장치 설치 : 28~148호, 104기","2023-09-16 08:00","2023-09-27 18:00","취소","취소","연속"]
[291,"부산울산","북부산","북부산S/S #2 Sh.R CB","23년 북부산전력지사 345kV GIS 정밀점검공사","북부산S/S 345kV 서부산-북부산#2T/L, #2Sh.R 정밀점검 - 점검대상 : 7971, 7900 ,7977 GIS","2023-09-18 08:00","2023-09-26 18:00","2023-09-18 08:00","2023-09-26 18:00","연속"]
[292,"부산울산","서부산","서부산S/S #2 Sh.R CB","서부산S/S 345kV 차단기 용량부족 대체공사","서부산S/S 72BAY(서부산-북부산#2T/L, #2Sh.R, #1M.Tr) 차단기 용량부족 대체 ○ 345kV GIS 40kA 4,000A×4CB 철거 ○ 345kV GIS 63kA 6,300A×4CB 설치","2023-09-11 09:00","2023-12-22 18:00","2023-09-16 09:00","2023-12-22 18:00","연속"]
[293,"부산울산","서부산","서부산S/S CB 7371","서부산S/S 345kV 서부산-북부산#3T/L GIS(7371) 보통점검","서부산S/S 345kV 서부산-북부산#3T/L GIS(7371) 보통점검","2023-09-09 09:00","2023-09-09 14:00","2023-09-10 15:00","2023-09-10 18:00","연속"]
[294,"부산울산","서부산","서부산북부산#2 T/L","서부산S/S 345kV 차단기 용량부족 대체공사","서부산S/S 72BAY(서부산-북부산#2T/L, #2Sh.R, #1M.Tr) 차단기 용량부족 대체 ○ 345kV GIS 40kA 4,000A×4CB 철거 ○ 345kV GIS 63kA 6,300A×4CB 설치","2023-09-11 09:00","2023-12-22 18:00","2023-09-16 09:00","2023-12-22 18:00","연속"]
[295,"부산울산","서부산","서부산S/S #1 M.Tr","서부산S/S 345kV 차단기 용량부족 대체공사","서부산S/S 72BAY(서부산-북부산#2T/L, #2Sh.R, #1M.Tr) 차단기 용량부족 대체 ○ 345kV GIS 40kA 4,000A×4CB 철거 ○ 345kV GIS 63kA 6,300A×4CB 설치","2023-09-11 09:00","2023-12-22 18:00","2023-09-16 09:00","2023-12-22 18:00","연속"]
[296,"부산울산","서부산","서부산S/S CB 7372","서부산S/S 345kV #3 M.Tr 1차 GIS(7372) 보통점검","서부산S/S 345kV #3 M.Tr 1차 GIS(7372) 보통점검","2023-09-10 09:00","2023-09-10 18:00","취소","취소","연속"]
[297,"부산울산","서부산","서부산북부산#1 T/L","서부산S/S 345kV #2M.Tr 고장복구 대체공사","서부산S/S 345kV #2M.Tr 고장복구 대체공사 1. 서부산S/S 345kV #2M.Tr 존공시험[23.09.04~07] 2. 서부산S/S 345kV #2M.Tr 시험가압[23.09.07~08]","2023-09-07 09:00","2023-09-08 18:00","2023-09-07 09:00","2023-09-08 18:00","연속"]
[298,"부산울산","서부산","서부산S/S #2 M.Tr","서부산S/S 345kV #2M.Tr 고장복구 대체공사","서부산S/S 345kV #2M.Tr 고장복구 대체공사 1. 서부산S/S 345kV #2M.Tr 존공시험[23.09.04~07] 2. 서부산S/S 345kV #2M.Tr 시험가압[23.09.07~08]","2023-09-04 09:00","2023-09-08 18:00","2023-09-04 09:00","2023-09-08 18:00","연속"]
[299,"부산울산","서부산","서부산S/S CB 7300","북부산#3T/L-#3 M.Tr 1차 TIE GIS(7300) 보통점검","북부산#3T/L-#3 M.Tr 1차 TIE GIS(7300) 보통점검","2023-09-09 14:00","2023-09-09 18:00","취소","취소","연속"]
[300,"부산울산","서부산","서부산S/S #3 Sh.R CB","서부산S/S 345kV #3 Sh.R 1차 GIS(7377) 보통점검","서부산S/S 345kV #3 Sh.R 1차 GIS(7377) 보통점검","2023-09-10 09:00","2023-09-10 18:00","2023-09-10 18:00","2023-09-10 21:00","연속"]
[301,"부산울산","서부산","서부산S/S #3,4GT CB","서부산S/S 345kV #3,4 G/T GIS(7472) 보통점검","서부산S/S 345kV #3,4 G/T GIS(7472) 보통점검 ※ 9.13~22 수세정 및 법정검사예정","2023-09-13 09:00","2023-09-13 18:00","취소","취소","연속"]
[302,"부산울산","서부산","신김해신녹산#2 T/L","신녹산S/S 345kV 7371, 7300 GIS 보통점검","신녹산S/S 345kV 7371, 7300 GIS 보통점검","2023-09-12 09:00","2023-09-12 18:00","취소","취소","연속"]
[303,"부산울산","서부산","신김해신녹산#1 T/L","신녹산S/S 345kV 7271, 7200 GIS 보통점검","신녹산S/S 345kV 7271, 7200 GIS 보통점검","2023-09-11 09:00","2023-09-11 18:00","취소","취소","연속"]
[304,"부산울산","서부산","신김해신녹산#1 T/L","23년 서부산전력지사 가공송전 순시점검 위탁공사","154kV 미음-녹산#1T/L 정밀점검간 안전이격","2023-09-21 08:00","2023-09-22 18:00","2023-09-21 08:00","2023-09-22 18:00","연속"]
[305,"부산울산","울산","남울산S/S CB 7372","22~23년 변전협력회사 총액공사","- 일진제 GIS 하자보수","2023-09-11 09:00","2023-09-13 18:00","2023-09-11 09:00","2023-09-13 18:00","연속"]
[306,"부산울산","울산","남울산S/S CB 7572","22~23년 변전협력회사 총액공사","- 일진제 GIS 하자보수","2023-09-25 09:00","2023-09-27 18:00","2023-09-25 09:00","2023-09-27 18:00","연속"]
[307,"부산울산","울산","울산C/C CB 7A72","23년 울산전력지사 개폐장치 보통점검공사","- 7A72 GIS 보통점검","2023-09-22 09:00","2023-09-22 18:00","2023-09-22 09:00","2023-09-22 18:00","연속"]
[308,"부산울산","울산","울산C/C CB 7500","23년 울산전력지사 개폐장치 보통점검공사","- 7500 GIS 보통점검","2023-09-20 09:00","2023-09-20 18:00","2023-09-20 09:00","2023-09-20 18:00","연속"]
[309,"부산울산","울산","울산C/C CB 7872","23년 울산전력지사 개폐장치 보통점검공사","- 7872 GIS 보통점검","2023-09-26 09:00","2023-09-26 18:00","2023-09-26 09:00","2023-09-26 18:00","연속"]
[310,"부산울산","울산","울주S/S #3 M.Tr","22~23년 변전협력회사 총액공사","- 6B1, 6B2DS 스페이서부 가스누기 보수 안전이격","2023-09-18 09:00","2023-09-22 18:00","2023-09-18 09:00","2023-09-22 18:00","연속"]
[311,"경남","직할","신김해S/S CB 7271","신김해S/S 신마산-신김해#1T/L(7271) GIS 조작시험","신김해S/S 신마산-신김해#1T/L(7271) GIS 조작시험","2023-09-22 09:00","2023-09-22 18:00","취소","취소","연속"]
[312,"경남","직할","신김해S/S CB 7771","신김해S/S 신김해-신녹산#1T/L(7771) GIS 조작시험","신김해S/S 신김해-신녹산#1T/L(7771) GIS 조작시험","2023-09-21 09:00","2023-09-21 18:00","취소","취소","연속"]
[313,"경남","직할","신김해북부산#2 T/L","신김해S/S 74BAY 용량부족 GIS 대체공사","신김해S/S 74BAY 용량부족 GIS 대체공사","2023-09-07 09:00","2023-09-15 18:00","2023-09-09 09:00","2023-09-15 18:00","연속"]
[314,"경남","직할","신김해S/S #2 M.Tr","신김해S/S 74BAY 용량부족 GIS 대체공사","신김해S/S 74BAY 용량부족 GIS 대체공사","2023-09-07 09:00","2023-09-15 18:00","2023-09-09 09:00","2023-09-15 18:00","연속"]
[315,"경남","직할","신김해S/S #3 M.Tr","신김해S/S #3M.Tr 1,2차 차단기 GIS 조작시험","신김해S/S #3M.Tr 1차(7772,7700), 2차(6344) 조작시험 및 부싱 절연유 채유","2023-09-25 09:00","2023-09-25 18:00","2023-09-25 09:00","2023-09-25 18:00","연속"]
[316,"경남","직할","신김해S/S CB 7871","신김해S/S 신김해-신녹산#2T/L(7871) GIS 보통점검","신김해S/S 신김해-신녹산#2T/L(7871) GIS 보통점검","2023-09-26 09:00","2023-09-26 18:00","2023-09-26 09:00","2023-09-26 18:00","연속"]
[317,"경남","직할","신김해북부산#1 T/L","154kV 신김해-진례#2T/L 아킹혼 철거 안전이격거리 확보","○ 154kV 신김해-진례#2T/L 아킹혼 철거 - 108호, 119호(2개소)","2023-09-24 08:30","2023-09-24 18:00","2023-09-24 08:30","2023-09-24 18:00","연속"]
[318,"경남","진주","의령산청양수#1 T/L","345lkV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#1T/L측 수직,수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.1~130 (345kV 의령-하동화력 T/L과 병가 구간 No.112~129)","2023-09-18 07:00","2023-10-20 18:00","2023-09-18 07:00","2023-10-20 18:00","매일"]
[319,"경남","진주","의령신마산#1 T/L","의령S/S 345kV 의령-신마산#1T/L 7571 GIS 보통 등","[주] 의령S/S 345kV 의령-신마산#1T/L 7571 GIS 보통 7900, 7971 [병행] LA 초기점검, PT 보통점검","2023-09-20 08:30","2023-09-21 18:00","취소","취소","연속"]
[320,"경남","진주","의령신마산#2 T/L","의령S/S 345kV 의령-신마산#2T/L LA 초기점검","의령S/S 345kV 의령-신마산#2T/L LA 초기점검","2023-09-22 08:30","2023-09-22 18:00","취소","취소","연속"]
[321,"경남","진주","고령의령#1 T/L","의령S/S 345kV 고령-의령#1T/L 7671 GIS 보통점검","의령S/S 345kV 고령-의령#1T/L 7671 GIS 보통점검","2023-09-23 08:30","2023-09-23 18:00","취소","취소","연속"]
[322,"경남","진주","고령의령#2 T/L","의령S/S 345kV 고령-의령#2T/L 7571 GIS 보통,PT하자","의령S/S 345kV 고령-의령#2T/L 7571 GIS 보통,PT하자","2023-09-24 08:30","2023-09-24 18:00","취소","취소","연속"]
[323,"경남","진주","의령S/S #2 M.Tr","의령S/S 345kV #2M.Tr 2차 LA초기 점검 등","[주] 의령S/S 345kV #2M.Tr 2차 LA초기 점검 및 1,2차 부싱유 채유 [병행1] 6244 GIS 조작 [병행2] 4279, 4284 VCB 조작 [병행3] 427-1,427-2 VCB 보통점검","2023-09-25 08:30","2023-09-25 18:00","취소","취소","연속"]
[324,"경남","진주","하동T/P CB 7272","하동T/P 345kV 7200, 7272 GIS 조작시험","하동T/P 345kV 7200, 7272 GIS 조작시험","2023-09-05 14:00","2023-09-05 18:00","2023-09-05 14:00","2023-09-05 18:00","연속"]
[325,"경남","진주","하동T/P CB 7200","하동T/P 345kV 7200, 7272 GIS 조작시험","하동T/P 345kV 7200, 7272 GIS 조작시험","2023-09-05 10:00","2023-09-05 14:00","2023-09-05 10:00","2023-09-05 14:00","연속"]
[326,"경남","통영","신고성고성하이TP#2 T/L","고성하이SY 345kV 신고성-고성하이발전#2TL GIS7171 보통점검","1. 고성하이S/Y 345kV 신고성-고성하이발전#2T/L GIS 7171 보통점검 2. 고성하이S/Y 345kV TIE GIS 7100 CT 점검","2023-09-20 09:00","2023-09-20 18:00","취소","취소","연속"]
[327,"경남","통영","신고성S/S #2 M.Tr","신고성S/S 345kV #2M.Tr 부싱절연유 채유 등 2건","1. 신고성S/S 345kV #2M.Tr B상(H1, X1) 부싱절연유 채유 2. 3차 VCB 조작시험","2023-09-19 14:00","2023-09-19 18:00","2023-09-19 14:00","2023-09-19 18:00","연속"]
[328,"경남","통영","신고성S/S #1 M.Tr","신고성S/S 345kV #1M.Tr 부싱절연유 채유","1. 신고성S/S 345kV #1M.Tr H1(A,B상) 부싱절연유 채유 2. 신고성S/S 345kV #1M.Tr X1(A,B,C상) 부싱절연유 채유","2023-09-19 09:00","2023-09-19 14:00","2023-09-19 09:00","2023-09-19 14:00","연속"]
[329,"경남","통영","신고성S/S CB 7671","신고성S/S 345kV #G6호기 1차 GIS 7671 보통점검","신고성S/S 345kV #G6호기 1차 GIS 7671 보통점검","2023-09-18 09:00","2023-09-18 18:00","2023-09-18 09:00","2023-09-18 18:00","연속"]
[330,"경남","함안","신마산신김해#2 T/L","154kV 진례-진영#2T/L 아킹혼 철거 안전이격거리 확보","○ 154kV 진례-진영#2T/L 아킹혼 철거 - 5~6호(2개소)","2023-09-16 08:30","2023-09-16 18:00","2023-09-16 08:30","2023-09-16 18:00","연속"]
[331,"경남","함안","신마산신김해#2 T/L","154kV 신김해-진례#2T/L 아킹혼 철거 안전이격거리 확보","○ 154kV 신김해-진례#2T/L 아킹혼 철거 - 4~9호, 24~25호(8개소)","2023-09-23 08:30","2023-09-23 18:00","2023-09-23 08:30","2023-09-23 18:00","연속"]
[332,"경남","함안","신마산S/S #4 M.Tr","신마산S/S 345kV #4 M.Tr 보통점검 등","신마산S/S 345kV #4 M.Tr 보통점검 등","2023-09-21 09:30","2023-09-21 17:30","2023-09-21 09:30","2023-09-21 17:30","연속"]
[333,"경남","함안","신마산S/S #1 M.Tr","신마산S/S 345kV #1 M.Tr 보통점검 등","신마산S/S 345kV #1 M.Tr 보통점검 등","2023-09-18 09:30","2023-09-19 17:30","2023-09-18 09:30","2023-09-19 17:30","연속"]
[334,"인천",null,"인천C/C #5,6GT 주변압기 (CB 7B71, 7B00)","주변압기 정밀점검, 갑종보호계전기 및 변환기 시험","주변압기 정밀점검, 갑종보호계전기 및 변환기 시험","2023-09-04 09:00","2023-12-29 17:00","2023-09-04 09:00","2023-12-29 17:00","연속"]
[335,"인천",null,"인천C/C #3ST 주변압기 (CB 7B00, 7B72)","주변압기 GIB 정비, 갑종보호계전기 및 변환기 시험","주변압기 GIB 정비, 갑종보호계전기 및 변환기 시험","2023-09-04 09:00","2023-12-29 17:00","2023-09-04 09:00","2023-12-29 17:00","연속"]

{"sheet":"154설비","index":2,"n_rows":680,"n_cols":11,"rows_kept":680,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2023년도 9월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","구의S/S #2 BUS","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T) - 1DS 분리, CB,1DS 부 교체","2023-09-18 15:00","2023-09-27 18:00","취소","취소","연속"]
[2,"서울","성동","구의S/S CB 6100","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T)","2023-09-01 09:00","2023-09-27 18:00","취소","취소","연속"]
[3,"서울","성동","천호구의#2 T/L","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T) - 2BUS 무부하가압","2023-09-05 15:00","2023-09-06 15:00","취소","취소","연속"]
[4,"서울","성동","구의S/S #1 BUS","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T) - 1DS 분리, CB,1DS 부 교체","2023-09-06 15:00","2023-09-18 15:00","취소","취소","연속"]
[5,"서울","성동","천호구의#2 T/L","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T) - 1BUS, CB, 1DS 무부하가압","2023-09-15 15:00","2023-09-18 15:00","취소","취소","연속"]
[6,"서울","성동","구의광장#2 T/L","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T)","2023-09-01 09:00","2023-09-27 18:00","취소","취소","연속"]
[7,"서울","성동","천호구의#2 T/L","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T) - 1BUS, CB, 1DS 무부하가압","2023-09-26 15:00","2023-09-27 15:00","취소","취소","연속"]
[8,"서울","성동","원남미아#1 T/L","2023년 성동P/O 변전 협력회사 총액공사","154kV GIS 조작시험","2023-09-07 10:00","2023-09-07 17:00","2023-09-07 10:00","2023-09-07 17:00","연속"]
[9,"서울","성동","금오상계#1 T/L","송전운영부 수평각도 조정기 설치공사","레일형 수평추락방지장치 설치","2023-09-15 07:00","2023-09-15 14:00","2023-09-15 07:00","2023-09-15 14:00","연속"]
[10,"서울","성동","금오상계#2 T/L","송전운영부 수평각도 조정기 설치공사","레일형 수평추락방지장치 설치","2023-09-15 14:00","2023-09-15 18:00","2023-09-15 14:00","2023-09-15 18:00","연속"]
[11,"서울","성동","양주쌍문#1 T/L","2022~2023년 가공송전 협력회사 총액공사","장기사용애자 교체 및 레일형 수평추락방지장치 설치","2023-09-14 14:00","2023-09-14 18:00","취소","취소","연속"]
[12,"서울","성동","양주쌍문#2 T/L","2022~2023년 가공송전 협력회사 총액공사","레일형 수평추락방지장치 설치","2023-09-14 07:00","2023-09-14 14:00","취소","취소","연속"]
[13,"서울","중부","상암등촌#1 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 상암-등촌T/L No.1(1기) 수평 추락방지시설 설치공사","2023-09-11 14:00","2023-09-11 18:00","2023-09-11 14:00","2023-09-11 18:00","연속"]
[14,"서울","중부","상암등촌#2 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 상암-등촌T/L No.1(1기) 수평 추락방지시설 설치공사","2023-09-11 07:00","2023-09-11 14:00","2023-09-11 07:00","2023-09-11 14:00","연속"]
[15,"서울","중부","지축현저#1 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","레일형 수평추락방지장치 설치 : 지축현저 N0.4, 4.1 (강관주)","2023-09-12 07:00","2023-09-13 14:00","2023-09-12 07:00","2023-09-13 14:00","연속"]
[16,"서울","중부","지축현저#2 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","레일형 수평추락방지장치 설치 : 지축현저 N0.4, 4.1 (강관주)","2023-09-13 14:00","2023-09-13 18:00","2023-09-13 14:00","2023-09-13 18:00","연속"]
[17,"서울","직할","순화동빙고 T/L","23년 직할 변전협력회사 총액공사","송전선로 보호반대체","2023-09-18 10:00","2023-09-21 18:00","2023-09-18 10:00","2023-09-21 18:00","연속"]
[18,"서울","직할","원남S/S CB 6100","23년 직할 변전협력회사 총액공사","170kV GIS 조작시험","2023-09-01 10:00","2023-09-01 18:00","2023-09-01 10:00","2023-09-01 18:00","연속"]
[19,"서울","직할","원남미아#2 T/L","154kV 원남-미아T/L 선종교체공사","1.대상선로 : 154㎸ 원남-미아 #2T/L 2.공사내용 : OF케이블 및 급유설비 철거, XLPE 및 Triplex 케이블 설치 ○ #2T/L : Triplex 1000㎟ 1C-0.8km XLPE 1200㎟ 1C-0.7km / 접속 7개소[중간 6개 종단 1개]","2023-09-01 09:00","2023-12-29 18:00","2023-09-01 09:00","2023-12-29 18:00","연속"]
[20,"서울","직할","중앙서소문 T/L","23년 직할 변전협력회사 총액공사","전자변 교체","2023-09-01 10:00","2023-09-01 18:00","2023-09-01 10:00","2023-09-01 18:00","연속"]
[21,"남서울","강남","논현논일#1 T/L","2023년 강남전력지사 170kV GIS 정밀점검공사","- 대상설비 :논현-논일#1,2T/L GIS","2023-09-09 09:00","2023-09-10 18:00","2023-09-09 07:00","2023-09-10 18:00","연속"]
[22,"남서울","강남","논현논일#2 T/L","2023년 강남전력지사 170kV GIS 정밀점검공사","- 대상설비 :논현-논일#1,2T/L GIS","2023-09-16 09:00","2023-09-17 18:00","2023-09-16 07:00","2023-09-17 18:00","연속"]
[23,"남서울","강남","동빙고반포#2 T/L","'22-'23년 가공송전 협력회사 총액공사(추락방지설치공사)","추락방지장치 설치공사 -수평부 암에 와이어 설치","2023-09-25 07:00","2023-09-26 18:00","2023-09-25 07:00","2023-09-26 18:00","연속"]
[24,"남서울","강남","신양재사당#1 T/L","'22-'23년 가공송전 협력회사 총액공사(추락방지설치공사)","추락방지장치 설치공사 -수평부 암에 와이어 설치","2023-09-18 07:00","2023-09-27 18:00","2023-09-18 07:00","2023-09-27 18:00","연속"]
[25,"남서울","강남","신양재신사#3 T/L","신사S/S 23kV 장기사용 GIS 교체공사","○ 23kV SA화 이전 154kV LID 수용","2023-09-11 09:00","2023-09-11 18:00","2023-09-11 09:00","2023-09-11 18:00","연속"]
[26,"남서울","강남","신사S/S #1 BUS","신사S/S 23kV 장기사용 GIS 교체공사","○ 23kV SA화 이전 154kV LID 수용","2023-09-04 09:00","2023-09-04 18:00","2023-09-04 09:00","2023-09-04 18:00","연속"]
[27,"남서울","강남","신사S/S #2 BUS","신사S/S 23kV 장기사용 GIS 교체공사","○ 23kV SA화 이전 154kV LID 수용","2023-09-05 09:00","2023-09-05 18:00","2023-09-05 09:00","2023-09-05 18:00","연속"]
[28,"남서울","강남","신양재신사#1 T/L","신사S/S 23kV 장기사용 GIS 교체공사","○ 23kV SA화 이전 154kV LID 수용","2023-09-15 09:00","2023-09-15 18:00","2023-09-15 09:00","2023-09-15 18:00","연속"]
[29,"남서울","강남","신양재신사#2 T/L","신사S/S 23kV 장기사용 GIS 교체공사","○ 23kV SA화 이전 154kV LID 수용","2023-09-14 09:00","2023-09-14 18:00","2023-09-14 09:00","2023-09-14 18:00","연속"]
[30,"남서울","강남","신사반포#2 T/L","신사S/S 23kV 장기사용 GIS 교체공사","○ 23kV SA화 이전 154kV LID 수용","2023-09-07 09:00","2023-09-07 18:00","2023-09-07 09:00","2023-09-07 18:00","연속"]
[31,"남서울","강남","신사반포#1 T/L","신사S/S 23kV 장기사용 GIS 교체공사","○ 23kV SA화 이전 154kV LID 수용","2023-09-06 09:00","2023-09-06 18:00","2023-09-06 09:00","2023-09-06 18:00","연속"]
[32,"남서울","강남","신양재과천#1 T/L","2023년 강남전력지사 170kV GIS 정밀점검공사","- 대상설비 : #60-61 GIS - 무부하가압 : #60BUS, 신양재-과천#1","2023-09-20 16:00","2023-09-20 18:00","2023-09-20 16:00","2023-09-20 18:00","연속"]
[33,"남서울","강남","신양재과천#2 T/L","2023년 강남전력지사 170kV GIS 정밀점검공사","- 대상설비 : #65-66 GIS","2023-09-26 16:00","2023-09-26 18:00","2023-09-26 16:00","2023-09-26 18:00","연속"]
[34,"남서울","동서울","가락S/S #2 BUS","2023년 동서울전력지사 170kV GIS 정밀점검","2023년 동서울전력지사 170kV GIS 정밀점검 -대상 : 가락S/S 동남-가락T/L 정밀점검","2023-09-22 09:00","2023-09-23 13:00","2023-09-22 09:00","2023-09-23 13:00","연속"]
[35,"남서울","동서울","가락수서#1 T/L","2023년 동서울전력지사 170kV GIS 정밀점검","2023년 동서울전력지사 170kV GIS 정밀점검 -대상 : 가락S/S 동남-가락T/L 무부하가압용","2023-09-23 12:00","2023-09-23 13:00","2023-09-23 12:00","2023-09-23 13:00","연속"]
[36,"남서울","동서울","가락S/S #1 BUS","2023년 동서울전력지사 170kV GIS 정밀점검","2023년 동서울전력지사 170kV GIS 정밀점검 -대상 : 동남-가락T/L #1BUS 휴전용","2023-09-23 13:00","2023-09-24 18:00","2023-09-23 13:00","2023-09-24 18:00","연속"]
[37,"남서울","동서울","강동천호#2 T/L","2023년 동서울전력지사 170kV GIS 정밀점검","2023년 동서울전력지사 170kV GIS 정밀점검 -대상 : 강동-천호#2T/L","2023-09-09 09:00","2023-09-10 18:00","2023-09-09 09:00","2023-09-10 18:00","연속"]
[38,"남서울","동서울","강동천호#1 T/L","2023년 동서울전력지사 170kV GIS 정밀점검","2023년 동서울전력지사 170kV GIS 정밀점검 -대상 : 강동-천호#1T/L","2023-09-02 09:00","2023-09-03 18:00","2023-09-02 09:00","2023-09-03 18:00","연속"]
[39,"남서울","동서울","신양재개포 T/L","154kV 개포-신양재,도곡T/L 지장이설공사","양재대로 구조개선 사업(지하차도 건설)에 따른 전력설비 이설 □ 사업구간 : 154kV 신양재-개포T/L J/B#20 ~ M/H#19 □ 주요공정 - 케이블 철거 : XLPE 2,000㎟, 1C-0.32km(기설전력구+관로) - 케이블 설치 : XLPE 2,000㎟, 1C-0.35km(신설전력구+관로) - 케이블 접속 : 2개소","2023-09-15 07:00","2023-09-28 18:00","2023-09-11 07:00","2023-09-28 18:00","연속"]
[40,"남서울","동서울","도곡개포 T/L","154kV 개포-신양재,도곡T/L 지장이설공사","양재대로 구조개선 사업(지하차도 건설)에 따른 전력설비 이설 □ 사업구간 : 154kV 도곡-개포T/L J/B#1 ~ M/H#2 □ 주요공정 - 케이블 철거 : XLPE 2,000㎟, 1C-0.32km(기설전력구+관로) - 케이블 설치 : XLPE 2,000㎟, 1C-0.35km(신설전력구+관로) - 케이블 접속 : 2개소","2023-09-01 07:00","2023-09-14 18:00","취소","취소","연속"]
[41,"남서울","동서울","가락동남 T/L","동서울P/O 170kV GIS 정밀점검","2023년도 동서울전력지사 170kV GIS 정밀점검","2023-09-18 09:00","2023-09-24 18:00","2023-09-18 09:00","2023-09-24 18:00","연속"]
[42,"남서울","동서울","동남위례#1 T/L","동서울P/O 170kV GIS 정밀점검","2023년도 동서울전력지사 170kV GIS 정밀점검 -#2BUS측 무부하가압용","2023-09-19 12:00","2023-09-19 13:00","2023-09-19 12:00","2023-09-19 13:00","연속"]
[43,"남서울","동서울","동남S/S #1 BUS","동서울P/O 170kV GIS 정밀점검","2023년도 동서울전력지사 170kV GIS 정밀점검 -#1BUS 측 정밀점검","2023-09-19 13:00","2023-09-20 18:00","2023-09-19 13:00","2023-09-20 18:00","연속"]
[44,"남서울","동서울","동남S/S #2 BUS","동서울P/O 170kV GIS 정밀점검","2023년도 동서울전력지사 170kV GIS 정밀점검 -#2BUS 측 정밀점검","2023-09-11 09:00","2023-09-12 13:00","2023-09-11 09:00","2023-09-12 13:00","연속"]
[45,"남서울","동서울","동남수서 T/L","동서울P/O 170kV GIS 정밀점검","2023년도 동서울전력지사 170kV GIS 정밀점검","2023-09-11 09:00","2023-09-13 18:00","2023-09-11 09:00","2023-09-13 18:00","연속"]
[46,"남서울","동서울","동남S/S #2 BUS","동서울P/O 170kV GIS 정밀점검","2023년도 동서울전력지사 170kV GIS 정밀점검 -#2BUS 측 정밀점검","2023-09-18 09:00","2023-09-19 13:00","2023-09-18 09:00","2023-09-19 13:00","연속"]
[47,"남서울","동서울","동남S/S #1 BUS","동서울P/O 170kV GIS 정밀점검","2023년도 동서울전력지사 170kV GIS 정밀점검 - #1BUS 측 정밀점검","2023-09-12 13:00","2023-09-13 18:00","2023-09-12 13:00","2023-09-13 18:00","연속"]
[48,"남서울","동서울","동남위례#1 T/L","동서울P/O 170kV GIS 정밀점검","2023년도 동서울전력지사 170kV GIS 정밀점검 - #2BUS 측 무부하가압용","2023-09-12 12:00","2023-09-12 13:00","2023-09-12 12:00","2023-09-12 13:00","연속"]
[49,"남서울","동서울","동서울S/S SEC CB 63640","동서울S/S 63-64 SEC GIS 초기점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-09-14 09:00","2023-09-14 18:00","2023-09-14 09:00","2023-09-14 18:00","연속"]
[50,"남서울","동서울","동서울가락#2 T/L","동서울S/S 동서울-가락 #2T/L GIS 초기점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-09-13 09:00","2023-09-13 18:00","2023-09-13 09:00","2023-09-13 18:00","연속"]
[51,"남서울","동서울","동서울S/S SEC CB 68690","동서울S/S 68-69 SEC GIS 초기점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-09-15 09:00","2023-09-15 18:00","2023-09-15 09:00","2023-09-15 18:00","연속"]
[52,"남서울","동서울","산성수서#1 T/L","'23~24년 동서울 지중위탁 총액공사","산성-수서 관로구간 설비점검","2023-09-04 08:00","2023-09-05 18:00","2023-09-04 08:00","2023-09-05 18:00","연속"]
[53,"남서울","동서울","산성수서#2 T/L","'23~24년 동서울 지중위탁 총액공사","산성-수서 관로구간 설비점검","2023-09-04 08:00","2023-09-05 18:00","2023-09-04 08:00","2023-09-05 18:00","연속"]
[54,"남서울","동서울","잠실탄천#2 T/L","잠실S/S 잠실-탄천 #2T/L GIS 조작시험","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-09-02 14:00","2023-09-02 18:00","2023-09-02 14:00","2023-09-02 18:00","연속"]
[55,"남서울","동서울","잠실탄천#1 T/L","잠실S/S 잠실-탄천 #1T/L GIS 조작시험","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-09-02 09:00","2023-09-02 14:00","2023-09-02 09:00","2023-09-02 14:00","연속"]
[56,"남서울","동서울","탄천대치#2 T/L","영동대로 지하공간 복합개발 지장송전선로 이설공사","영동대로 지하공간 복합개발 지장송전선로 이설","2023-09-25 09:00","2023-11-17 18:00","2023-09-25 09:00","2023-11-17 18:00","연속"]
[57,"남서울","동서울","탄천대치#1 T/L","영동대로 지하공간 복합개발 지장송전선로 이설공사","영동대로 지하공간 복합개발 지장송전선로 이설","2023-09-25 09:00","2023-10-27 18:00","2023-09-25 09:00","2023-10-27 18:00","연속"]
[58,"남서울","동서울","풍납S/S #2 BUS","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS 5CCT 철거 및 설치 - 기타부대공사","2023-09-08 13:00","2023-10-13 18:00","2023-09-15 13:00","2023-10-20 18:00","연속"]
[59,"남서울","영등포","구공독산 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","구공S/S 170kV GIS 보통 독산S/S 170kV GIS 조작","2023-09-01 09:00","2023-09-01 18:00","2023-09-01 09:00","2023-09-01 18:00","연속"]
[60,"남서울","영등포","신광명소래 T/L","'22-'23년 가공송전 협력회사 총액공사(추락방지설치공사)","추락방지장치 설치공사 -수평부 암에 와이어 설치","2023-09-23 07:00","2023-09-23 13:00","취소","취소","연속"]
[61,"남서울","영등포","신광명시흥#1 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 보통, 조작","2023-09-06 09:00","2023-09-06 18:00","2023-09-06 09:00","2023-09-06 18:00","연속"]
[62,"남서울","영등포","온수소래 T/L","'22-'23년 가공송전 협력회사 총액공사(추락방지설치공사)","추락방지장치 설치공사 -수평부 암에 와이어 설치","2023-09-23 13:00","2023-09-24 18:00","취소","취소","연속"]
[63,"남서울","직할","신길S/S CB 6100","23kV GIS 부하절체 관련 모선 분리 시행","23kV GIS 부하절체 관련 모선 분리 시행 - 신길S/S 길남D/L 계통변경 시행","2023-09-11 09:00","2023-09-11 18:00","2023-09-11 09:00","2023-09-11 18:00","연속"]
[64,"남서울","직할","사당신림 T/L","154kV 사당-신림T/L 사당인출 구간 OF케이블 선종교체공사","□ 교체구간 : 154kV 사당-신림T/L 사당S/S ~ M/H#3-1","2023-09-06 09:00","2023-11-16 18:00","취소","취소","연속"]
[65,"남서울","직할","신문래구로#2 T/L","OF케이블 절연유 채유밸브 설치","OF케이블 절연유 채유밸브 설치(SJ/B#1) - 천왕구로T/L 긴급복구 공사로 인한 기존일정 취소 후 재신청","2023-09-21 09:00","2023-09-22 18:00","2023-09-21 09:00","2023-09-22 18:00","연속"]
[66,"남서울","직할","여의노량진 T/L","154kV 여의-노량진T/L Triplex 접속함 리콜","□ 작업내용 : 154kV 여의-노량진T/L J/B#5 C상, J/B#6 B상 해체 후 재접속","2023-09-12 09:00","2023-09-25 18:00","2023-09-12 09:00","2023-09-25 18:00","연속"]
[67,"인천","김포","신김포양곡#2 T/L","154kV 신김포-양곡 등 2개T/L 인출변경공사","[신김포-양곡#2T/L] - 선종 : 154kV XLPE 2,000㎟ - 구간 : M/H#8 ~ 옥외 GIS EBG 361m - 접속 : 종단접속(1개소), 중간접속(1개소)","2023-09-23 09:00","2023-10-10 18:00","2023-09-23 09:00","2023-10-10 18:00","연속"]
[68,"인천","김포","왕길양촌#1 T/L","왕길S/S 154kV 왕길-양촌#1T/L GIS 보통점검","왕길S/S 154kV 왕길-양촌#1T/L GIS 보통점검 - 양촌S/S 154kV 왕길-양촌#1T/L GIS 보통점검 병행","2023-09-11 10:00","2023-09-11 18:00","2023-09-11 10:00","2023-09-11 18:00","연속"]
[69,"인천","김포","왕길양촌#2 T/L","왕길S/S 154kV 왕길-양촌#2T/L GIS 보통점검","왕길S/S 154kV 왕길-양촌#2T/L GIS 보통점검 - 양촌S/S 154kV 왕길-양촌#2T/L GIS 보통점검 병행","2023-09-14 10:00","2023-09-14 18:00","2023-09-14 10:00","2023-09-14 18:00","연속"]
[70,"인천","부평","신가좌부개#2 T/L","임학, 부개S/S 154kV GIS 교체공사","부개S/S 154kV GIS 교체공사 -#1bus 무부하가압용","2023-09-21 12:00","2023-09-22 12:00","2023-09-21 12:00","2023-09-22 12:00","연속"]
[71,"인천","부평","부개S/S #2 BUS","임학, 부개S/S 154kV GIS 교체공사","부개S/S 154kV GIS 교체공사 -#2m.tr 1차 gis 교체","2023-09-22 12:00","2023-10-06 12:00","2023-09-22 12:00","2023-10-06 12:00","연속"]
[72,"인천","부평","부개S/S #1 BUS","임학, 부개S/S 154kV GIS 교체공사","부개S/S 154kV GIS 교체공사 -#2M.Tr 1차 GIS 교체","2023-09-17 10:00","2023-09-22 12:00","2023-09-17 10:00","2023-09-22 12:00","연속"]
[73,"인천","부평","신가좌부개#2 T/L","임학, 부개S/S 154kV GIS 교체공사","부개S/S 154kV GIS 교체공사 -#2M.Tr 1차 GIS 교체 관련 #2BUS 무부하가압","2023-09-26 12:00","2023-09-27 12:00","2023-09-26 12:00","2023-09-27 12:00","연속"]
[74,"인천","부평","부개S/S #2 BUS","임학, 부개S/S 154kV GIS 교체공사","부개S/S 154kV GIS 교체공사 -#2M.Tr 1차 GIS 교체","2023-09-16 08:00","2023-09-17 10:00","2023-09-16 08:00","2023-09-17 10:00","연속"]
[75,"인천","부평","신가좌부개#2 T/L","임학, 부개S/S 154kV GIS 교체공사","부개S/S 154kV GIS 교체공사 -#2BUS 무부하가압용","2023-09-17 09:00","2023-09-17 10:00","2023-09-17 09:00","2023-09-17 10:00","연속"]
[76,"인천","부평","송현포스코CC#2 T/L","154kV 송현-포스코CCT/L 추락방지시설 및 항공시설물 정비공사","- 추락방지시설 설치 - 고광도 항공장애표시등 위치변경 및 신규설치","2023-09-18 08:00","2023-09-23 18:00","취소","취소","연속"]
[77,"인천","부평","신가좌부개#2 T/L","23~24년 지중송전위탁정비공사","절연유 채유","2023-09-20 09:00","2023-09-22 18:00","취소","취소","연속"]
[78,"인천","부평","신경서왕길#1 T/L","22~23년도 김포, 부평전력지사 가공송전 협력회사 총액공사","추락방지장치 설치","2023-09-19 07:00","2023-09-21 18:00","취소","취소","연속"]
[79,"인천","부평","신경서경서#3 T/L","신경서S/S 154kV 신경서-경서#3T/L 보호배전반 대체","신경서S/S 154kV 신경서-경서#3T/L 보호배전반 대체","2023-09-23 09:00","2023-09-27 18:00","2023-09-23 09:00","2023-09-27 18:00","연속"]
[80,"인천","부평","신경서왕길#2 T/L","22~23년도 김포, 부평전력지사 가공송전 협력회사 총액공사","추락방지장치 설치","2023-09-25 07:00","2023-09-27 18:00","취소","취소","연속"]
[81,"인천","부평","신경서S/S SEC CB 65660","신경서S/S 154kV #61-66BUS 모선보호반 대체","신경서S/S 154kV #61-66BUS 모선보호반 대체","2023-09-18 09:00","2023-09-22 18:00","2023-09-18 09:00","2023-09-22 18:00","연속"]
[82,"인천","부평","신경서S/S CB 6200","신경서S/S 154kV #61-66BUS 모선보호반 대체","신경서S/S 154kV #61-66BUS 모선보호반 대체","2023-09-18 09:00","2023-09-22 18:00","2023-09-18 09:00","2023-09-22 18:00","연속"]
[83,"인천","부평","신경서S/S SEC CB 60610","신경서S/S 154kV #61-66BUS 모선보호반 대체","신경서S/S 154kV #61-66BUS 모선보호반 대체","2023-09-18 09:00","2023-09-22 18:00","2023-09-18 09:00","2023-09-22 18:00","연속"]
[84,"인천","부평","인천C/C 현대제철#2T/L CB","154kV 현대제철T/L 추락방지시설 설치공사","- 추락방지시설 설치","2023-09-18 08:00","2023-09-23 18:00","취소","취소","연속"]
[85,"인천","부평","신가좌인천#1 T/L","인천S/S 154kV 6133 GIS 정밀점검 관련 무부하가압","인천S/S 154kV 6133 GIS 정밀점검 관련 무부하가압","2023-09-16 09:00","2023-09-16 18:00","2023-09-16 09:00","2023-09-16 18:00","연속"]
[86,"인천","부평","신가좌인천#3 T/L","인천S/S 154kV 신가좌인천#3T/L GIS 정밀점검","인천S/S 154kV 신가좌인천#3T/L GIS 정밀점검","2023-09-18 09:00","2023-09-20 18:00","2023-09-18 09:00","2023-09-20 18:00","연속"]
[87,"인천","부평","인천남인천#2 T/L","인천남인천#2 T/L 휴전작업","1. 인천S/S 154kV 인천남인천#2 T/L GIS 보통점검 2. 남인천S/S 154kV 인천남인천#2 T/L GIS 조작시험 3. 인천S/S 6233 GIS 정밀점검 관련 무부하가압","2023-09-23 09:00","2023-09-23 18:00","2023-09-23 09:00","2023-09-23 18:00","연속"]
[88,"인천","시흥","오봉고잔#1 T/L","고잔S/S 154kV 오봉고잔#1,2T/L IED 성능개선","고잔S/S 154kV 오봉고잔#1,2T/L IED 성능개선","2023-09-20 09:00","2023-09-20 14:00","2023-09-20 09:00","2023-09-20 14:00","연속"]
[89,"인천","시흥","오봉고잔#2 T/L","고잔S/S 154kV 오봉고잔#1,2T/L IED 성능개선","고잔S/S 154kV 오봉고잔#1,2T/L IED 성능개선","2023-09-20 14:00","2023-09-20 18:00","2023-09-20 14:00","2023-09-20 18:00","연속"]
[90,"인천","시흥","신시흥남동#2 T/L","154kV 신시흥-남동T/L 용량증대 선종교체공사","154kV 신시흥-남동(D)#1,2 T/L 5.2 C-km","2023-09-20 09:00","2023-11-20 18:00","취소","취소","연속"]
[91,"인천","시흥","시화동시화#1 T/L","SVL 교체공사","구형 SVL 교체공사","2023-09-23 09:00","2023-09-24 18:00","2023-09-23 09:00","2023-09-24 18:00","연속"]
[92,"인천","시흥","신광명소래 T/L","가공송전 협력회사 총액공사(154kV 서소T/L 추락방지)","송전철탑 추락방지장치 수평 설치 - 대상 : No.48~82","2023-09-16 07:00","2023-09-17 18:00","2023-09-16 07:00","2023-09-17 18:00","매일"]
[93,"인천","시흥","온수소래 T/L","가공송전 협력회사 총액공사(154kV 서소T/L 추락방지)","송전철탑 추락방지장치 수평 설치 - 대상 : No.48~82","2023-09-23 07:00","2023-09-24 18:00","2023-09-23 07:00","2023-09-24 18:00","매일"]
[94,"인천","시흥","서안양소래 T/L","가공송전 협력회사 총액공사(154kV 서소T/L 추락방지)","송전철탑 추락방지장치 수평 설치 - 대상 : No.48~82","2023-09-23 07:00","2023-09-25 18:00","2023-09-23 07:00","2023-09-25 18:00","매일"]
[95,"인천","시흥","서서울#2소래 T/L","가공송전 협력회사 총액공사(154kV 서소T/L 추락방지)","송전철탑 추락방지장치 수평 설치 - 대상 : No.48~82","2023-09-16 07:00","2023-09-22 18:00","2023-09-16 07:00","2023-09-22 18:00","매일"]
[96,"인천","시흥","신시화S/S CB 6400","인수점검 미비사항 보완","인수점검 미비사항 보완","2023-09-01 09:00","2023-10-13 18:00","취소","취소","연속"]
[97,"인천","시흥","신시화S/S CB 6371","인수점검 미비사항 보완","인수점검 미비사항 보완","2023-09-01 09:00","2023-10-13 18:00","취소","취소","연속"]
[98,"인천","시흥","신시화S/S CB 6500","인수점검 미비사항 보완","인수점검 미비사항 보완","2023-09-01 09:00","2023-10-13 18:00","취소","취소","연속"]
[99,"인천","시흥","신시화S/S SEC CB 65660","인수점검 미비사항 보완","인수점검 미비사항 보완","2023-09-01 09:00","2023-10-13 18:00","취소","취소","연속"]
[100,"인천","시흥","신시화중시화#2 T/L","인수점검 미비사항 보완","인수점검 미비사항 보완","2023-09-01 09:00","2023-10-13 18:00","취소","취소","연속"]
[101,"인천","시흥","신시화S/S CB 6571","인수점검 미비사항 보완","인수점검 미비사항 보완","2023-09-01 09:00","2023-10-13 18:00","취소","취소","연속"]
[102,"인천","시흥","신시화중시화#1 T/L","인수점검 미비사항 보완","인수점검 미비사항 보완","2023-09-01 09:00","2023-10-13 18:00","취소","취소","연속"]
[103,"인천","시흥","신시화남정왕#1 T/L","인수점검 미비사항 보완","인수점검 미비사항 보완","2023-09-01 09:00","2023-10-13 18:00","취소","취소","연속"]
[104,"인천","시흥","신시화S/S CB 6671","인수점검 미비사항 보완","인수점검 미비사항 보완","2023-09-01 09:00","2023-10-13 18:00","취소","취소","연속"]
[105,"인천","시흥","신시화S/S CB 6300","인수점검 미비사항 보완","인수점검 미비사항 보완","2023-09-01 09:00","2023-10-13 18:00","취소","취소","연속"]
[106,"인천","시흥","신시화S/S CB 6600","인수점검 미비사항 보완","인수점검 미비사항 보완","2023-09-01 09:00","2023-10-13 18:00","취소","취소","연속"]
[107,"인천","시흥","신시화S/S SEC CB 60610","인수점검 미비사항 보완","인수점검 미비사항 보완","2023-09-01 09:00","2023-10-13 18:00","취소","취소","연속"]
[108,"인천","시흥","신시화S/S CB 6471","인수점검 미비사항 보완","인수점검 미비사항 보완","2023-09-01 09:00","2023-10-13 18:00","취소","취소","연속"]
[109,"인천","시흥","신시화남정왕#2 T/L","인수점검 미비사항 보완","인수점검 미비사항 보완","2023-09-01 09:00","2023-10-13 18:00","취소","취소","연속"]
[110,"인천","시흥","신시흥남동#1 T/L","가공송전 협력회사 총액공사(154kV 남동T/L 추락방지)","송전철탑 추락방지장치 수평 설치 - 대상 : No.1~36","2023-09-26 07:00","2023-09-29 18:00","2023-09-24 07:00","2023-09-27 18:00","연속"]
[111,"인천","시흥","신시흥도림#1 T/L","가공송전 협력회사 총액공사(154kV 남동T/L 추락방지)","송전철탑 추락방지장치 수평 설치 - 대상 : No.1~36","2023-09-26 07:00","2023-09-28 18:00","취소","취소","연속"]
[112,"인천","시흥","신시흥도림#2 T/L","가공송전 협력회사 총액공사(154kV 남동T/L 추락방지)","송전철탑 추락방지장치 수평 설치 - 대상 : No.1~36","2023-09-30 07:00","2023-10-02 18:00","취소","취소","연속"]
[113,"인천","시흥","신시흥남동#2 T/L","가공송전 협력회사 총액공사(154kV 남동T/L 추락방지)","송전철탑 추락방지장치 수평 설치 - 대상 : No.1~36","2023-09-30 07:00","2023-10-03 18:00","취소","취소","매일"]
[114,"인천","시흥","신시흥북시화#2 T/L","신시흥S/S 154kV 신시흥북시화#2T/L 메커니즘 부품 교체","신시흥S/S 154kV 신시흥북시화#2T/L 메커니즘 부품 교체","2023-09-21 09:00","2023-09-21 18:00","2023-09-21 09:00","2023-09-21 18:00","연속"]
[115,"인천","시흥","도림오봉#1 T/L","가공송전 협력회사 총액공사(154kV 남동T/L 추락방지)","송전철탑 추락방지장치 수평 설치 - 대상 : No.1~36","2023-09-29 07:00","2023-09-29 18:00","2023-09-24 07:00","2023-09-24 18:00","연속"]
[116,"인천","시흥","오봉남동#1 T/L","오봉S/S 154kV 오봉남동#1T/L GIS 보통점검","오봉S/S 154kV 오봉남동#1T/L GIS 보통점검 남동S/S 154kV 오봉남동#1T/L GIS 보통점검 병행","2023-09-18 09:00","2023-09-19 18:00","2023-09-18 09:00","2023-09-19 18:00","연속"]
[117,"인천","직할","계양북인천 T/L","계양S/S 154kV 계양-북인천T/L GIS SA 혼용공사","계양S/S 154kV 계양-북인천T/L GIS SA 혼용공사","2023-09-22 09:30","2023-09-22 18:00","2023-09-22 09:30","2023-09-22 18:00","연속"]
[118,"인천","직할","계양원창 T/L","계양S/S 154kV 계양-원창T/L GIS SA 혼용공사","계양S/S 154kV 계양-원창T/L GIS SA 혼용공사","2023-09-18 09:30","2023-09-18 18:00","2023-09-18 09:30","2023-09-18 18:00","연속"]
[119,"인천","직할","임학계양#1 T/L","계양S/S 154kV 임학-계양#1T/L GIS SA 혼용공사","계양S/S 154kV 임학-계양#1T/L GIS SA 혼용공사","2023-09-20 09:30","2023-09-20 18:00","2023-09-20 09:30","2023-09-20 18:00","연속"]
[120,"인천","직할","임학계양#2 T/L","계양S/S 154kV 임학-계양#2T/L GIS SA 혼용공사","계양S/S 154kV 임학-계양#2T/L GIS SA 혼용공사","2023-09-21 09:30","2023-09-21 18:00","2023-09-21 09:30","2023-09-21 18:00","연속"]
[121,"인천","직할","고강화곡#1 T/L","154kV 강서S/S 건설사업(고강-강서 GIS 증설)","- 154kV GIS 1CCT 설치 - 기타 부대공사 1식","2023-09-21 16:00","2023-09-22 16:00","2023-09-21 16:00","2023-09-22 16:00","연속"]
[122,"인천","직할","고강화곡#1 T/L","154kV 강서S/S 건설사업(고강-강서 GIS 증설)","- 154kV GIS 1CCT 설치 - 기타 부대공사 1식","2023-09-19 13:00","2023-09-20 13:00","2023-09-19 13:00","2023-09-20 13:00","연속"]
[123,"인천","직할","신부평고강#2 T/L","23~24년 지중송전위탁정비공사(인천본부 직할)","154kV 신부평-고강#2T/L 원종C/T 및 피뢰기 점검","2023-09-16 09:00","2023-09-16 18:00","2023-09-16 09:00","2023-09-16 18:00","연속"]
[124,"인천","직할","부흥부개#1 T/L","SVL 교체공사","구형 SVL 교체공사","2023-09-16 09:00","2023-09-17 18:00","2023-09-16 09:00","2023-09-17 18:00","연속"]
[125,"인천","직할","신부평임학#1 T/L","임학S/S 신부평임학#1T/L 조작시험","임학S/S 신부평임학#1T/L 조작시험","2023-09-19 09:30","2023-09-19 14:00","2023-09-15 09:30","2023-09-15 14:00","연속"]
[126,"인천","직할","신부평임학#2 T/L","임학S/S 신부평임학#2T/L 조작시험","임학S/S 신부평임학#2T/L 조작시험","2023-09-19 14:00","2023-09-19 18:00","2023-09-15 14:00","2023-09-15 18:00","연속"]
[127,"경기북부","고양","월롱금촌#1 T/L","22-23 변전협력회사 총액공사","170kV GIS 보통점검","2023-09-19 09:00","2023-09-19 18:00","2023-09-19 09:00","2023-09-19 18:00","연속"]
[128,"경기북부","고양","월롱금촌#2 T/L","22-23 변전협력회사 총액공사","170kV GIS 보통점검","2023-09-20 09:00","2023-09-20 18:00","2023-09-20 09:00","2023-09-20 18:00","연속"]
[129,"경기북부","고양","원흥상암 T/L","154kV원흥-수색 연결 관로공사","송전관로 신설 L=150m","2023-09-04 08:00","2023-09-07 18:00","취소","취소","연속"]
[130,"경기북부","고양","원흥수색#1 T/L","154kV원흥-수색 연결 관로공사","송전관로 신설 L=150m","2023-09-04 08:00","2023-09-07 18:00","취소","취소","연속"]
[131,"경기북부","고양","능곡상암#1 T/L","22~23년 고양P/O 변전협력회사 총액공사","170kV GIS 차단기 조작시험","2023-09-25 10:00","2023-09-25 14:00","2023-09-25 10:00","2023-09-25 14:00","연속"]
[132,"경기북부","고양","능곡상암#2 T/L","22~23년 고양P/O 변전협력회사 총액공사","170kV GIS 차단기 조작시험","2023-09-26 10:00","2023-09-26 14:00","2023-09-26 10:00","2023-09-26 14:00","연속"]
[133,"경기북부","고양","문산월롱#2 T/L","22-23 변전협력회사 총액공사","170kV GIS 보통점검","2023-09-05 09:00","2023-09-05 18:00","2023-09-05 09:00","2023-09-05 18:00","연속"]
[134,"경기북부","고양","문산월롱#1 T/L","22-23 변전협력회사 총액공사","170kV GIS 보통점검","2023-09-04 09:00","2023-09-04 18:00","2023-09-04 09:00","2023-09-04 18:00","연속"]
[135,"경기북부","고양","일산송포#1 T/L","22-23 변전협력회사 총액공사","170kV GIS 보통점검","2023-09-13 09:00","2023-09-13 18:00","2023-09-13 09:00","2023-09-13 18:00","연속"]
[136,"경기북부","고양","일산송포#2 T/L","22-23 변전협력회사 총액공사","170kV GIS 보통점검","2023-09-14 09:00","2023-09-14 18:00","2023-09-14 09:00","2023-09-14 18:00","연속"]
[137,"경기북부","고양","신덕은문산#1 T/L","154kV 신덕은-문산#1T/L 방식부 보강공사","○ 154kV 신덕은-문산#1T/L J/B#1-1 A상, J/B#1 A, B상 방식부 보강","2023-09-21 09:00","2023-09-22 18:00","2023-09-21 09:00","2023-09-22 18:00","연속"]
[138,"경기북부","고양","일산S/S CB 6100","22-23 변전협력회사 총액공사","170kV GIS 보통점검","2023-09-12 09:00","2023-09-12 18:00","2023-09-12 09:00","2023-09-12 18:00","연속"]
[139,"경기북부","구리","가평청평HP#1 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-09-07 09:00","2023-09-07 18:00","2023-09-07 09:00","2023-09-07 18:00","연속"]
[140,"경기북부","구리","가평화천HP T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-09-08 09:00","2023-09-08 18:00","2023-09-08 09:00","2023-09-08 18:00","연속"]
[141,"경기북부","구리","가평청평HP#2 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사 -가평S/S LA 대체, CVT 보통점검, 청평HP CVT LA 보통점검, GCB 조작시험","2023-09-11 09:00","2023-09-12 18:00","2023-09-11 09:00","2023-09-12 18:00","연속"]
[142,"경기북부","구리","가평춘천HP T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사 가평측 LA 보통점검 CVT 대체","2023-09-22 09:00","2023-09-22 18:00","2023-09-22 09:00","2023-09-22 18:00","연속"]
[143,"경기북부","구리","덕소진건#1 T/L","23-24년 직할 지중송전설비 위탁정비공사 (피뢰기 점검)","C/T 피뢰기 점검","2023-09-12 09:00","2023-09-12 14:00","2023-09-12 09:00","2023-09-12 14:00","연속"]
[144,"경기북부","구리","마석청평HP#1 T/L","'22~23년 구리송전협력 총액공사(추락방지장치설치)","추락방지장치 설치","2023-09-18 08:00","2023-09-22 18:00","2023-09-18 08:00","2023-09-22 18:00","연속"]
[145,"경기북부","구리","덕소마석#2 T/L","'22~23년 구리송전협력 총액공사(추락방지장치설치)","추락방지장치 설치","2023-09-18 08:00","2023-09-18 18:00","2023-09-18 08:00","2023-09-18 18:00","연속"]
[146,"경기북부","구리","신포천전곡#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","수평추락방지시설 및 피뢰기설치","2023-09-04 07:30","2023-09-07 12:00","2023-09-04 07:30","2023-09-07 12:00","연속"]
[147,"경기북부","구리","신포천전곡#1 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-09-15 14:00","2023-09-15 18:00","2023-09-15 14:00","2023-09-15 18:00","연속"]
[148,"경기북부","구리","신포천백학#1 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-09-13 09:00","2023-09-13 14:00","2023-09-13 09:00","2023-09-13 14:00","연속"]
[149,"경기북부","구리","신포천백학#2 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-09-13 14:00","2023-09-13 18:00","2023-09-13 14:00","2023-09-13 18:00","연속"]
[150,"경기북부","구리","신포천포천#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","성능저하국산애자교체(154kV 신포천-포천#2T/L No.16,34~39)","2023-09-25 12:00","2023-09-27 18:00","2023-09-25 12:00","2023-09-27 18:00","연속"]
[151,"경기북부","구리","신포천덕계#2 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-09-14 09:00","2023-09-14 18:00","2023-09-14 09:00","2023-09-14 18:00","연속"]
[152,"경기북부","구리","곤지암용문#2 T/L","용문S/S 감시제어설비 디지털화 공사","□ 용문S/S 감시제어설비 디지털화 공사 - 154kV 곤지암-용문#2T/L GIS, PRO PNL 감시/제어케이블 이설","2023-09-15 09:00","2023-09-15 18:00","2023-09-15 09:00","2023-09-15 18:00","연속"]
[153,"경기북부","구리","지제용문#1 T/L","용문S/S 감시제어설비 디지털화 공사","□ 용문S/S 감시제어설비 디지털화 공사 - 154kV 지제-용문#1T/L GIS, PRO PNL 감시/제어케이블 이설","2023-09-25 09:00","2023-09-25 18:00","2023-09-25 09:00","2023-09-25 18:00","연속"]
[154,"경기북부","구리","지제용문#2 T/L","용문S/S 감시제어설비 디지털화 공사","□ 용문S/S 감시제어설비 디지털화 공사 - 154kV 지제-용문#2T/L GIS, PRO PNL 감시/제어케이블 이설","2023-09-26 09:00","2023-09-26 18:00","2023-09-26 09:00","2023-09-26 18:00","연속"]
[155,"경기북부","구리","곤지암용문#1 T/L","용문S/S 감시제어설비 디지털화 공사","□ 용문S/S 감시제어설비 디지털화 공사 - 154kV 곤지암-용문#1T/L GIS, PRO PNL 감시/제어케이블 이설","2023-09-14 09:00","2023-09-14 18:00","2023-09-14 09:00","2023-09-14 18:00","연속"]
[156,"경기북부","구리","운천철원#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 운천-철원T/L No.1~8,10,14~23,25~66","2023-09-11 07:00","2023-09-15 18:00","2023-09-11 07:00","2023-09-15 18:00","연속"]
[157,"경기북부","구리","운천철원#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 운천-철원T/L No.1~8,10,14~23,25~66","2023-09-04 07:00","2023-09-08 18:00","2023-09-04 07:00","2023-09-08 18:00","연속"]
[158,"경기북부","구리","문막지제#1 T/L","'22~23년 구리전력 가공송전협력 총액공사(추락방지장치설치)","추락방지장치 설치(수평)","2023-09-04 08:00","2023-09-08 18:00","2023-09-04 08:00","2023-09-08 18:00","연속"]
[159,"경기북부","구리","문막지제#2 T/L","'22~23년 구리전력 가공송전협력 총액공사(추락방지장치설치)","추락방지장치 설치(수평)","2023-09-11 08:00","2023-09-15 18:00","2023-09-11 08:00","2023-09-15 18:00","연속"]
[160,"경기북부","구리","덕소진건#2 T/L","'22~23년 구리전력 가공송전협력 총액공사(추락방지장치설치)","추락방지장치 설치(수평)","2023-09-25 08:00","2023-09-25 18:00","2023-09-25 08:00","2023-09-25 18:00","연속"]
[161,"경기북부","구리","진건별내#1 T/L","23-24년 직할 지중송전설비 위탁정비공사 (피뢰기 점검)","C/T 피뢰기 점검","2023-09-13 09:00","2023-09-13 14:00","2023-09-13 09:00","2023-09-13 14:00","연속"]
[162,"경기북부","구리","진건별내#2 T/L","23-24년 직할 지중송전설비 위탁정비공사 (피뢰기 점검)","C/T 피뢰기 점검","2023-09-13 14:00","2023-09-13 18:00","2023-09-13 14:00","2023-09-13 18:00","연속"]
[163,"경기북부","구리","청평HP의암HP T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사 청평HP LA CVT 보통점검","2023-09-25 09:00","2023-09-25 18:00","2023-09-25 09:00","2023-09-25 18:00","연속"]
[164,"경기북부","구리","포천운천#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","포천운천#2T/L No.6,61~63 지지애자교체공사","2023-09-21 07:30","2023-09-27 12:00","2023-09-21 07:30","2023-09-27 12:00","연속"]
[165,"경기북부","구리","포천운천#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","병가선로(신포천-포천#2T/L No.34 성능저하국산애자교체공사)","2023-09-27 12:00","2023-09-27 18:00","2023-09-27 12:00","2023-09-27 18:00","연속"]
[166,"경기북부","구리","용정포천#1 T/L","154kV 포천변전소 옥내화 토건공사","H-PILE 인발을 위한 안전이격거리 확보","2023-09-01 09:00","2023-09-01 13:00","2023-09-01 09:00","2023-09-01 13:00","연속"]
[167,"경기북부","구리","포천운천#1 T/L","154kV 포천변전소 옥내화 토건공사","H-PILE 인발을 위한 안전이격거리 확보","2023-09-01 09:00","2023-09-01 13:00","2023-09-01 09:00","2023-09-01 13:00","연속"]
[168,"경기북부","구리","용정포천#2 T/L","154kV 포천변전소 옥내화 토건공사","H-PILE 인발을 위한 안전이격거리 확보","2023-09-01 13:00","2023-09-12 18:00","2023-09-01 13:00","2023-09-12 18:00","연속"]
[169,"경기북부","직할","신포천동두천#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 신포천-동두천T/L No.24,28,31~35","2023-09-20 07:00","2023-09-20 18:00","2023-09-20 07:00","2023-09-20 18:00","연속"]
[170,"경기북부","직할","신포천동두천#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 신포천-동두천T/L No.24,28,31~35","2023-09-21 07:00","2023-09-21 18:00","2023-09-21 07:00","2023-09-21 18:00","연속"]
[171,"경기북부","직할","양주S/S #66 BUS","양주S/S HVDC GIS 설치공사","154kV 1CCT","2023-09-12 11:00","2023-09-12 13:00","2023-09-12 11:00","2023-09-12 13:00","연속"]
[172,"경기북부","직할","양주S/S #61 BUS","양주S/S HVDC GIS 설치공사","154kV 1CCT","2023-09-12 09:00","2023-09-12 11:00","2023-09-12 09:00","2023-09-12 11:00","연속"]
[173,"경기북부","직할","양주고양#1 T/L","양주S/S HVDC GIS 설치공사","154kV 1CCT","2023-09-13 09:00","2023-09-16 18:00","2023-09-13 09:00","2023-09-16 18:00","연속"]
[174,"경기북부","직할","양주고양#2 T/L","2022~2023년 고양전력지사 가공송전협력회사 총액공사","철탑추락방지시설 설치","2023-09-01 07:00","2023-09-06 18:00","2023-09-01 07:00","2023-09-06 18:00","연속"]
[175,"경기북부","직할","양주S/S #67 BUS","양주S/S HVDC GIS 설치공사","154kV 1CCT","2023-09-14 09:00","2023-09-16 18:00","2023-09-14 09:00","2023-09-16 18:00","연속"]
[176,"경기북부","직할","양주쌍문#1 T/L","2023 가공송전 순시점검 위탁공사","송전설비 정밀점검","2023-09-11 07:30","2023-09-15 18:00","2023-09-11 07:30","2023-09-15 18:00","연속"]
[177,"경기북부","직할","양주쌍문#2 T/L","22-23년도 직할 변전협력회사 총액공사","양주S/S 양주-쌍문#2T/L 보호반 대체","2023-09-19 09:00","2023-09-21 18:00","2023-09-19 09:00","2023-09-21 18:00","연속"]
[178,"경기북부","직할","양주금촌#1 T/L","2022~2023년 고양전력지사 가공송전협력회사 총액공사","철탑추락방지시설 설치","2023-09-26 07:00","2023-09-27 18:00","2023-09-26 07:00","2023-09-27 18:00","연속"]
[179,"경기북부","직할","양주S/S #62 BUS","양주S/S HVDC GIS 설치공사","154kV 1CCT","2023-09-04 09:00","2023-09-14 09:00","2023-09-04 09:00","2023-09-14 09:00","연속"]
[180,"경기북부","직할","양주금촌#2 T/L","2022~2023년 고양전력지사 가공송전협력회사 총액공사","철탑추락방지시설 설치","2023-09-04 07:00","2023-09-12 18:00","2023-09-04 07:00","2023-09-12 18:00","연속"]
[181,"경기북부","직할","옥정동두천#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 옥정-동두천T/L No.2~11,17~24,28,31~36","2023-09-21 07:00","2023-09-25 18:00","2023-09-21 07:00","2023-09-25 18:00","연속"]
[182,"경기북부","직할","옥정송우#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 옥정-송우T/L No.2~8,12","2023-09-22 07:00","2023-09-25 18:00","2023-09-22 07:00","2023-09-25 18:00","연속"]
[183,"경기북부","직할","옥정송우#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 옥정-송우T/L No.2~8,12","2023-09-18 07:00","2023-09-19 18:00","2023-09-18 07:00","2023-09-19 18:00","연속"]
[184,"경기북부","직할","옥정동두천#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 옥정-동두천T/L No.2~11,17~24,28,31~36","2023-09-18 07:00","2023-09-20 18:00","2023-09-18 07:00","2023-09-20 18:00","연속"]
[185,"경기북부","직할","장암방학#2 T/L","장암S/S 170kV GIS 유압 조작기 교체공사","장암S/S 장암-방학#2T/L 170kV GIS 유압조작기 교체","2023-09-04 14:00","2023-09-04 18:00","2023-09-04 14:00","2023-09-04 18:00","연속"]
[186,"경기북부","직할","용현장암#1 T/L","장암S/S 170kV GIS 유압 조작기 교체공사","장암S/S 용현-장암#1T/L 170kV GIS 유압조작기 교체","2023-09-11 08:00","2023-09-11 14:00","2023-09-11 08:00","2023-09-11 14:00","연속"]
[187,"경기북부","직할","별내장암 T/L","23년도 경기북부 직할 170kV GIS 초기점검 및 정밀점검 공사","장암S/S 별내-장암T/L GIS 초기점검","2023-09-12 08:00","2023-09-12 18:00","2023-09-12 08:00","2023-09-12 18:00","연속"]
[188,"경기북부","직할","장암방학#1 T/L","장암S/S 170kV GIS 유압 조작기 교체공사","장암S/S 장암-방학#1T/L 170kV GIS 유압조작기 교체","2023-09-04 08:00","2023-09-04 14:00","2023-09-04 08:00","2023-09-04 14:00","연속"]
[189,"경기북부","직할","운천전곡#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","154kV 운천-전곡#1T/L No.1~76 수평추락방지시설 및 피뢰기설치","2023-09-07 12:30","2023-09-25 12:00","2023-09-07 12:30","2023-09-25 12:00","연속"]
[190,"경기","군포","마도사강#2 T/L","154kV 화성-장덕T/L 등 2개 선로 OPGW 증설공사","* OPGW 증설(OP-S-L24→OP-S-L48) 17.991km * 광케이블 증설(FOFC-24C→FOFC-48C) 0.638km * 항공장애표시구 교체 71개 * 광코어 접속, 광케이블 최종시험 및 기타 부대공사 1식","2023-09-18 07:00","2023-09-27 18:00","취소","취소","연속"]
[191,"경기","군포","서안양소래 T/L","23-24년 지중송전설비 위탁정비공사","LA 및 C/T 점검","2023-09-27 09:00","2023-09-27 18:00","2023-09-27 09:00","2023-09-27 18:00","연속"]
[192,"경기","군포","신안산S/S CB 6200","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023-09-08 12:00","2023-09-08 18:00","2023-09-08 12:00","2023-09-08 18:00","연속"]
[193,"경기","군포","신안산S/S CB 6100","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023-09-08 09:00","2023-09-08 12:00","2023-09-08 09:00","2023-09-08 12:00","연속"]
[194,"경기","군포","시화중시화 T/L","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023-09-20 09:00","2023-09-20 18:00","2023-09-20 09:00","2023-09-20 18:00","연속"]
[195,"경기","군포","성곡중시화 T/L","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023-09-26 12:00","2023-09-26 18:00","2023-09-26 12:00","2023-09-26 18:00","연속"]
[196,"경기","동부","곤지암S/S CB 6200","23년 동부전력 170kV GIS 정밀점검","곤지암:6200,61BUS(정밀)","2023-09-21 09:00","2023-09-23 18:00","2023-09-21 09:00","2023-09-23 18:00","연속"]
[197,"경기","동부","곤지암S/S CB 6100","23년 동부전력 170kV GIS 정밀점검","곤지암:6100,60BUS(정밀)","2023-09-18 09:00","2023-09-20 18:00","2023-09-18 09:00","2023-09-20 18:00","연속"]
[198,"경기","동부","곤지암S/S #65 BUS","23년 동부전력 170kV GIS 정밀점검","곤지암:6100,65BUS(정밀)","2023-09-19 13:00","2023-09-20 18:00","2023-09-19 13:00","2023-09-20 18:00","연속"]
[199,"경기","동부","곤지암S/S #66 BUS","23년 동부전력 170kV GIS 정밀점검","곤지암:6200,66BUS(정밀)","2023-09-22 13:00","2023-09-23 18:00","2023-09-22 13:00","2023-09-23 18:00","연속"]
[200,"경기","동부","곤지암S/S #61 BUS","23년 동부전력 170kV GIS 정밀점검","곤지암:6200,61BUS(정밀)","2023-09-21 09:00","2023-09-22 13:00","2023-09-21 09:00","2023-09-22 13:00","연속"]
[201,"경기","동부","곤지암S/S #60 BUS","23년 동부전력 170kV GIS 정밀점검","곤지암:6100,60BUS(정밀)","2023-09-18 09:00","2023-09-19 13:00","2023-09-18 09:00","2023-09-19 13:00","연속"]
[202,"경기","동부","성현분당#2 T/L","분당S/S 154kV 장기사용 GIS 교체공사","#2S/T 교체 안전이격 확보용 - 즉시가압 가능","2023-09-22 08:00","2023-10-11 18:00","2023-09-22 08:00","2023-10-11 18:00","연속"]
[203,"경기","동부","분당오포#1 T/L","분당S/S 154kV 장기사용 GIS 교체공사","#2G/T 교체 안전이격 확보용 - 즉시가압 가능","2023-09-05 08:00","2023-09-21 18:00","2023-09-05 08:00","2023-09-21 18:00","연속"]
[204,"경기","동부","초월성현#1 T/L","성현S/S 장기사용 154kV GIS 교체공사(3차)","성현S/S 장기사용 154kV GIS 교체공사(3차, 안전이격) - 즉시가압 불가. 붓싱철거 필요","2023-09-01 09:00","2023-09-21 18:00","2023-09-01 09:00","2023-09-21 18:00","연속"]
[205,"경기","동부","오천율현#2 T/L","23년 동부전력 170kV GIS 정밀점검","곤지암:6100 무부하가압용","2023-09-27 09:00","2023-09-27 18:00","2023-09-27 09:00","2023-09-27 18:00","연속"]
[206,"경기","동부","오천율현#1 T/L","23년 동부전력 170kV GIS 정밀점검","곤지암:6100 무부하가압용","2023-09-26 09:00","2023-09-26 18:00","2023-09-26 09:00","2023-09-26 18:00","연속"]
[207,"경기","동부","초월S/S CB 6100","23년 동부 변전협력총액공사","초월:6100(2DS 누기보수) (~26) 65BUS","2023-09-25 09:30","2023-09-26 18:00","2023-09-25 09:30","2023-09-26 18:00","연속"]
[208,"경기","동부","초월성현#2 T/L","23년 동부 변전협력총액공사","초월:6100(2DS 누기보수) (~26) 무부하 가압 선로","2023-09-26 16:00","2023-09-26 18:00","2023-09-26 16:00","2023-09-26 18:00","연속"]
[209,"경기","성남","용인덕성#2 T/L","23년 성남전력지사 변전협력회사 총액공사","- GIS 하자점검","2023-09-13 09:00","2023-09-13 18:00","2023-09-13 09:00","2023-09-13 18:00","연속"]
[210,"경기","성남","신성남서판교#2 T/L","23년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2023-09-14 09:00","2023-09-14 18:00","2023-09-14 09:00","2023-09-14 18:00","연속"]
[211,"경기","성남","신성남S/S SEC CB 67680","23년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2023-09-18 09:00","2023-09-18 14:00","2023-09-18 09:00","2023-09-18 14:00","연속"]
[212,"경기","성남","신성남S/S CB 6400","23년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2023-09-18 14:00","2023-09-18 18:00","2023-09-18 14:00","2023-09-18 18:00","연속"]
[213,"경기","성남","신용인S/S SEC CB 65660","23년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2023-09-22 14:00","2023-09-22 18:00","2023-09-22 14:00","2023-09-22 18:00","연속"]
[214,"경기","성남","신용인S/S #1 EM.Tr  CB","23년 성남전력 154, 345kV 주변압기 보통점검공사","-변압기 보통점검","2023-09-25 09:00","2023-09-26 18:00","2023-09-25 09:00","2023-09-26 18:00","연속"]
[215,"경기","성남","신용인S/S CB 6300","23년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2023-09-08 09:00","2023-09-08 18:00","2023-09-08 09:00","2023-09-08 18:00","연속"]
[216,"경기","성남","신용인용인#2 T/L","154kV 신용인-동백-마북T/L 광선로 증설공사","○ OPGW 교체(OP-S-L24→OP-S-L48) 2.948km ○ 광케이블 교체(FOFC-24C→FOFC-48C) 0.731km ○ 항공장애표시구 교체 6개 ○ 광코어 접속, 광케이블 최종시험 및 기타 부대공사 1식 - 신용인-동백T/L No.1 병가철탑 작업 관련으로 휴전 필요","2023-09-18 07:00","2023-09-21 18:00","2023-09-18 07:00","2023-09-21 18:00","연속"]
[217,"경기","성남","신용인동백#1 T/L","154kV 신용인-동백-마북T/L 광선로 증설공사","○ OPGW 교체(OP-S-L24→OP-S-L48) 2.948km ○ 광케이블 교체(FOFC-24C→FOFC-48C) 0.731km ○ 항공장애표시구 교체 6개 ○ 광코어 접속, 광케이블 최종시험 및 기타 부대공사 1식","2023-09-18 07:00","2023-09-21 18:00","2023-09-18 07:00","2023-09-21 18:00","연속"]
[218,"경기","성남","신용인S/S CB 6100","23년 성남전력지사 변전협력회사 총액공사","- GIS 보통점검","2023-09-04 09:00","2023-09-04 14:00","2023-09-04 09:00","2023-09-04 14:00","연속"]
[219,"경기","성남","신용인S/S CB 6200","23년 성남전력지사 변전협력회사 총액공사","- GIS 보통점검","2023-09-04 14:00","2023-09-04 18:00","2023-09-04 14:00","2023-09-04 18:00","연속"]
[220,"경기","성남","신용인S/S SEC CB 60610","23년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2023-09-22 09:00","2023-09-22 14:00","2023-09-22 09:00","2023-09-22 14:00","연속"]
[221,"경기","성남","신성남정자#3 T/L","23년 성남전력지사 변전협력회사 총액공사","- 보호반 이설 공사","2023-09-11 09:00","2023-09-13 18:00","2023-09-11 09:00","2023-09-13 18:00","연속"]
[222,"경기","직할","과천동안양#2 T/L","2023년 가공송전 순시점검 위탁공사","안전이격확보(의왕동안양T/L 정밀점검) 및 초기점검(8,9호)","2023-09-18 08:00","2023-09-20 18:00","2023-09-18 08:00","2023-09-20 18:00","연속"]
[223,"경기","직할","발안향남#2 T/L","2022-23년 경기본부 직할 변전협력회사 총액공사","발안,향남S/S 발안-향남#2T/L GIS 보통점검","2023-09-16 09:00","2023-09-16 14:00","2023-09-16 09:00","2023-09-16 14:00","연속"]
[224,"경기","직할","발안향남#1 T/L","2022-23년 경기본부 직할 변전협력회사 총액공사","발안,향남S/S 발안-향남#1T/L GIS 보통점검","2023-09-16 14:00","2023-09-16 18:00","2023-09-16 14:00","2023-09-16 18:00","연속"]
[225,"경기","직할","화성발안#2 T/L","2022-23년 경기본부 직할 변전협력회사 총액공사","발안S/S 화성-발안#2T/L GIS 보통점검 화성S/S 화성-발안#2T/L GIS 하자점검","2023-09-09 09:00","2023-09-09 18:00","취소","취소","연속"]
[226,"경기","직할","화성발안#1 T/L","2022-23년 경기본부 직할 변전협력회사 총액공사","발안S/S 화성-발안#1T/L GIS 보통점검 화성S/S 화성-발안#1T/L GIS 하자점검","2023-09-02 09:00","2023-09-02 18:00","취소","취소","연속"]
[227,"경기","직할","서수원율전#1 T/L","154kV 서수원S/S #5M.TR 설치공사","[154kV #5M.Tr 무부하 가압] 1. 154kV #1BUS, #43BUS 앵글측정 2. 154kV #1BUS, #48BUS 앵글측정 3. 4400 BUS TIE CB 앵글측정 4. 154kV #2BUS, #43BUS 앵글측정 5. 154kV 서수원-율전#1T/L로 #5M.Tr 24시간 무부하 가압","2023-09-21 09:00","2023-09-22 18:00","2023-09-21 09:00","2023-09-22 18:00","연속"]
[228,"경기","직할","율전의왕#2 T/L","2023년 가공송전 순시점검 위탁공사","안전이격확보(의왕동안양T/L 정밀점검)","2023-09-16 08:00","2023-09-17 18:00","2023-09-16 08:00","2023-09-17 18:00","매일"]
[229,"경기","직할","의왕동안양#1 T/L","2023년 가공송전 순시점검 위탁공사","154kV 의왕동안양#1T/L 정밀점검","2023-09-16 08:00","2023-09-20 18:00","2023-09-16 08:00","2023-09-20 18:00","연속"]
[230,"경기","직할","의왕동안양#2 T/L","2023년 가공송전 순시점검 위탁공사","154kV 의왕동안양#2T/L 정밀점검(NO 34~39)","2023-09-25 09:00","2023-09-26 18:00","2023-09-25 09:00","2023-09-26 18:00","연속"]
[231,"경기","직할","이의S/S CB 6100","2022-23년 경기본부 직할 변전협력회사 총액공사","이의S/S 6100 GIS 보통점검","2023-09-21 09:00","2023-09-21 18:00","2023-09-21 09:00","2023-09-21 18:00","연속"]
[232,"경기","직할","화성마도 T/L","2022-23년 경기본부 직할 변전협력회사 총액공사","화성S/S 화성-마도T/L GIS 보통점검","2023-09-03 09:00","2023-09-03 18:00","취소","취소","연속"]
[233,"경기","직할","화성S/S #67 BUS","화성S/S 154kV 신규수용공사(화성전철) ","#69Sh.C #2BUS 철거 후 임시마감 처리 ","2023-09-01 09:00","2023-09-02 16:00","2023-09-01 09:00","2023-09-02 16:00","연속"]
[234,"경기","직할","화성남양#1 T/L","화성S/S 154kV 신규수용공사(화성전철) ","화성전철 GIS #2BUS 무부하가압 ","2023-09-02 11:00","2023-09-02 16:00","2023-09-02 11:00","2023-09-02 16:00","연속"]
[235,"경기","직할","화성S/S #62 BUS","화성S/S 154kV 신규수용공사(화성전철) "," #69Sh.C #1BUS 철거 후 화성전철GIS 설치 ","2023-09-02 16:00","2023-09-10 10:00","2023-09-02 16:00","2023-09-10 10:00","연속"]
[236,"경기","직할","화성남양#1 T/L","화성S/S 154kV 신규수용공사(화성전철) ","화성전철 GIS #1BUS 무부하가압 ","2023-09-09 10:00","2023-09-10 10:00","2023-09-09 10:00","2023-09-10 10:00","연속"]
[237,"경기","직할","화성S/S #67 BUS","화성S/S 154kV 신규수용공사(화성전철) ","화성전철GIS #2BUS 설치 ","2023-09-10 10:00","2023-09-17 13:00","2023-09-10 10:00","2023-09-17 13:00","연속"]
[238,"경기","직할","화성남양#1 T/L","화성S/S 154kV 신규수용공사(화성전철) ","화성전철 GIS 최종 무부하가압(DS투입) ","2023-09-16 09:00","2023-09-17 18:00","2023-09-16 09:00","2023-09-17 18:00","연속"]
[239,"경기","직할","화성S/S #62 BUS","화성S/S 154kV 신규수용공사(화성전철) ","화성전철GIS #1BUS 무부하가압(DS투입) ","2023-09-17 13:00","2023-09-17 18:00","2023-09-17 13:00","2023-09-17 18:00","연속"]
[240,"경기","직할","화성S/S #66 BUS","화성S/S 154kV 신규수용공사(화성전철) ","화성전철#1T/L GIS 증설 ","2023-09-18 09:00","2023-09-19 18:00","2023-09-18 09:00","2023-09-19 18:00","연속"]
[241,"경기","직할","화성S/S #61 BUS","화성S/S 154kV 신규수용공사(화성전철) ","화성전철#1T/L GIS 증설 ","2023-09-19 18:00","2023-09-24 18:00","2023-09-19 18:00","2023-09-24 18:00","연속"]
[242,"경기","직할","화성수촌#2 T/L","화성S/S 154kV 신규수용공사(화성전철) ","화성전철#1T/L GIS 증설 무부하가압","2023-09-23 16:00","2023-09-24 18:00","2023-09-23 16:00","2023-09-24 18:00","연속"]
[243,"경기","직할","화성S/S #66 BUS","화성S/S 154kV 신규수용공사(화성전철) ","화성전철#1T/L GIS 증설 ","2023-09-25 09:00","2023-10-09 13:00","2023-09-25 09:00","2023-10-09 13:00","연속"]
[244,"경기","평택","고덕진위#2 T/L","23-24년 지중송전설비 위탁정비공사(평택전력지사)","케이블타워 및 피뢰기 점검","2023-09-15 14:00","2023-09-15 18:00","2023-09-15 14:00","2023-09-15 18:00","연속"]
[245,"경기","평택","고덕송탄#2 T/L","23년 평택전력지사 변전협력회사 총액공사","고덕S/S 고덕-송탄#2T/L GIS 보통점검 및 DC케이블 이설","2023-09-26 09:00","2023-09-26 18:00","2023-09-26 09:00","2023-09-26 18:00","연속"]
[246,"경기","평택","고덕송탄#1 T/L","23년 평택전력지사 변전협력회사 총액공사","고덕S/S 고덕-송탄#1T/L GIS 보통점검 및 DC케이블 이설","2023-09-25 09:00","2023-09-25 18:00","2023-09-25 09:00","2023-09-25 18:00","연속"]
[247,"경기","평택","고덕진위#1 T/L","23-24년 지중송전설비 위탁정비공사(평택전력지사)","케이블타워 및 피뢰기 점검","2023-09-15 08:00","2023-09-15 14:00","2023-09-15 08:00","2023-09-15 14:00","연속"]
[248,"경기","평택","서안성S/S #1 EM.Tr CB","23년 평택전력지사 변전협력회사 총액공사","서안성S/S #1EM.Tr 96P 교체","2023-09-01 09:00","2023-09-01 18:00","2023-09-01 09:00","2023-09-01 18:00","연속"]
[249,"경기","평택","서운안성#1 T/L","세종-포천간 도로개설 관련 지장이설공사(154kV 1T/L)","철탑 5기 신설, 8기 철거","2023-09-11 07:00","2023-09-23 18:00","2023-09-11 07:00","2023-09-23 18:00","연속"]
[250,"경기","평택","서운삼죽 T/L","23년 평택전력지사 변전협력회사 총액공사","서운S/S 서운-삼죽T/L GIS 보통점검","2023-09-02 09:00","2023-09-02 18:00","2023-09-02 09:00","2023-09-02 18:00","연속"]
[251,"경기","평택","서운광혜원 T/L","23년 평택전력지사 변전협력회사 총액공사","서운S/S 서운-광혜원T/L GIS 보통점검","2023-09-09 09:00","2023-09-09 18:00","2023-09-09 09:00","2023-09-09 18:00","연속"]
[252,"경기","평택","송탄오성CC#2 T/L","23-24년 지중송전설비 위탁정비공사(평택전력지사)","케이블타워 및 피뢰기 점검","2023-09-22 08:00","2023-09-22 18:00","2023-09-22 08:00","2023-09-22 18:00","연속"]
[253,"경기","평택","송탄오성CC#1 T/L","23-24년 지중송전설비 위탁정비공사(평택전력지사)","케이블타워 및 피뢰기 점검","2023-09-21 08:00","2023-09-21 18:00","2023-09-21 08:00","2023-09-21 18:00","연속"]
[254,"경기","평택","원정평택TP#2 T/L","23년 평택전력지사 변전협력회사 총액공사","원정S/S 원정-평택T/P#2T/L GIS 보통점검","2023-09-23 09:00","2023-09-23 18:00","2023-09-23 09:00","2023-09-23 18:00","연속"]
[255,"경기","평택","원정평택TP#1 T/L","23년 평택전력지사 변전협력회사 총액공사","원정S/S 원정-평택T/P#1T/L GIS 보통점검","2023-09-16 09:00","2023-09-16 18:00","2023-09-16 09:00","2023-09-16 18:00","연속"]
[256,"경기","평택","둔포추팔#2 T/L","154kV 오산-평택T/L 등 13개T/L 추락방지장치(수평) 설치공사","추락방지장치(수평) 18기 설치","2023-09-21 09:00","2023-09-23 18:00","2023-09-21 09:00","2023-09-23 18:00","연속"]
[257,"경기","평택","평택추팔#1 T/L","154kV 오산-평택T/L 등 13개T/L 추락방지장치(수평) 설치공사","추락방지장치(수평) 19기 설치","2023-09-18 09:00","2023-09-21 18:00","2023-09-18 09:00","2023-09-20 18:00","연속"]
[258,"경기","평택","평택추팔#2 T/L","154kV 오산-평택T/L 등 13개T/L 추락방지장치(수평) 설치공사","추락방지장치(수평) 19기 설치","2023-09-25 09:00","2023-09-26 18:00","2023-09-25 09:00","2023-09-26 18:00","연속"]
[259,"경기","평택","포승평택TP#1 T/L","23년 평택전력지사 변전협력회사 총액공사","포승S/S 포승-평택T/P#1T/L GIS 보통점검","2023-09-27 09:00","2023-09-27 18:00","2023-09-27 09:00","2023-09-27 18:00","연속"]
[260,"강원","강릉","속초간성#2 T/L","2023년 강릉전력지사 변전협력회사 총액공사","170kV GIS, LA, PT 보통점검","2023-09-05 10:00","2023-09-05 18:00","2023-09-05 10:00","2023-09-05 18:00","연속"]
[261,"강원","강릉","북강릉주문진#2 T/L","2022~2023년 가공송전협력회사 총액공사","○ 관형지지물용 가이드 레일 설치(No.1, 2)","2023-09-05 07:30","2023-09-06 18:00","2023-09-05 07:30","2023-09-06 18:00","매일"]
[262,"강원","강릉","강릉북강릉#1 T/L","2022~2023년 가공송전협력회사 총액공사","○ 관형지지물용 가이드 레일 설치(No.2, 45)","2023-09-04 07:30","2023-09-05 18:00","2023-09-04 07:30","2023-09-05 18:00","매일"]
[263,"강원","강릉","북강릉주문진#1 T/L","2022~2023년 가공송전협력회사 총액공사","○ 관형지지물용 가이드 레일 설치(No.1, 2)","2023-09-07 07:30","2023-09-08 18:00","2023-09-07 07:30","2023-09-08 18:00","매일"]
[264,"강원","강릉","강릉북강릉#2 T/L","2022~2023년 가공송전협력회사 총액공사","○ 관형지지물용 가이드 레일 설치(No.2, 45)","2023-09-07 07:30","2023-09-08 18:00","2023-09-07 07:30","2023-09-08 18:00","매일"]
[265,"강원","강릉","신양양속초#2 T/L","23년 가공송전선로 순시점검 위탁공사","○ 과열개소 진단 및 정비(154kV 신양양-속초 #2T/L No.31)","2023-09-08 08:00","2023-09-08 18:00","2023-09-08 08:00","2023-09-08 18:00","연속"]
[266,"강원","강릉","신양양양양#1 T/L","강릉전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검(CB)","2023-09-11 09:00","2023-09-13 14:00","2023-09-11 09:00","2023-09-13 14:00","연속"]
[267,"강원","강릉","신양양양양#2 T/L","강릉전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검(CB)","2023-09-13 14:00","2023-09-15 18:00","2023-09-13 14:00","2023-09-15 18:00","연속"]
[268,"강원","강릉","평창올림픽 T/L","2023 변전협력회사 총액공사","올림픽S/S 170kV GIS, LA 보통점검","2023-09-14 10:00","2023-09-14 18:00","취소","취소","연속"]
[269,"강원","강릉","횡계올림픽 T/L","2023 변전협력회사 총액공사","올림픽S/S 170kV GIS, LA 보통점검","2023-09-15 10:00","2023-09-15 18:00","취소","취소","연속"]
[270,"강원","동해","동해정선 T/L","2023년 가공송전선로 순시점검 위탁공사","154kV 동해-정선T/L 지장수목벌채","2023-09-20 09:00","2023-09-20 18:00","2023-09-20 09:00","2023-09-20 18:00","연속"]
[271,"강원","동해","동해동영월 T/L","22~23 동해전력지사 변전정비팀 총액공사","LA ABC상 보통점검","2023-09-22 09:30","2023-09-22 18:00","2023-09-22 09:30","2023-09-22 18:00","연속"]
[272,"강원","동해","태백삼척GP#1 T/L","노후 송전선로 보호배전반 대체 공사","노후 송전선로 보호배전반 대체 공사","2023-09-18 10:00","2023-09-21 18:00","2023-09-18 10:00","2023-09-21 18:00","연속"]
[273,"강원","동해","울진삼척GP#1 T/L","22~23 동해전력지사 변전정비팀 총액공사","LA ABC상 보통점검","2023-09-21 13:00","2023-09-21 18:00","2023-09-21 13:00","2023-09-21 18:00","연속"]
[274,"강원","동해","울진삼척GP#2 T/L","22~23 동해전력지사 변전정비팀 총액공사","LA ABC상 보통점검","2023-09-21 09:30","2023-09-21 13:00","2023-09-21 09:30","2023-09-21 13:00","연속"]
[275,"강원","원주","남원주원주#1 T/L","'22~23년 원주전력지사 송전정비회사 총액공사","- 수평형 추락방지장치 설치","2023-09-23 07:00","2023-09-24 18:00","2023-09-23 07:00","2023-09-24 18:00","연속"]
[276,"강원","원주","남원주원주#2 T/L","'22~23년 원주전력지사 송전정비회사 총액공사","- 피뢰기 및 수평형 추락방지장치 설치","2023-09-16 07:00","2023-09-17 18:00","2023-09-16 07:00","2023-09-17 18:00","연속"]
[277,"강원","원주","남원주원주#1 T/L","2023년 원주전력지사 가공송전선로 순시점검 위탁공사","154kV 남원주-원주#1T/L 전구간(28기) 정밀점검(정기검사 대상)","2023-09-18 07:30","2023-09-20 18:00","2023-09-18 07:30","2023-09-20 18:00","매일"]
[278,"강원","원주","남원주원주#2 T/L","2023년 원주전력지사 가공송전선로 순시점검 위탁공사","154kV 남원주-원주#2T/L 전구간(28기) 정밀점검(정기검사 대상)-주말제외","2023-09-21 07:30","2023-09-25 18:00","2023-09-21 07:30","2023-09-25 18:00","매일"]
[279,"강원","원주","문막지제#1 T/L","2023년 원주전력지사 변전협력회사 총액공사","장기미동작 차단기 동작시험, 전자변 교체","2023-09-19 10:00","2023-09-19 18:00","2023-09-19 10:00","2023-09-19 18:00","연속"]
[280,"강원","원주","홍천상남#1 T/L","345kV 동해 등 5개T/L 추락방지 설치공사","○ 추락방지장치 수평구명줄 설치 147기","2023-09-11 07:00","2023-09-27 18:00","2023-09-11 07:00","2023-09-27 18:00","매일"]
[281,"강원","원주","서원주문막#1 T/L","'22~23년 구리전력 가공송전협력 총액공사(추락방지장치설치)","추락방지장치 설치(수평) - 병가선로 휴전으로 안전확보","2023-09-13 08:00","2023-09-13 18:00","2023-09-13 08:00","2023-09-13 18:00","연속"]
[282,"강원","원주","서원주문막#1 T/L","'22~23년 원주전력지사 송전정비회사 총액공사","- 추락방지장치 설치","2023-09-18 07:00","2023-09-22 18:00","2023-09-18 07:00","2023-09-22 18:00","연속"]
[283,"강원","원주","서원주문막#2 T/L","'22~23년 원주전력지사 송전정비회사 총액공사","- 추락방지장치 설치","2023-09-25 07:00","2023-09-27 18:00","2023-09-25 07:00","2023-09-27 18:00","연속"]
[284,"강원","원주","서원주문막#2 T/L","'22~23년 구리전력 가공송전협력 총액공사(추락방지장치설치)","추락방지장치 설치(수평) - 병가선로 휴전으로 안전확보","2023-09-12 08:00","2023-09-12 18:00","2023-09-12 08:00","2023-09-12 18:00","연속"]
[285,"강원","원주","홍천소양강HP T/L","2023년 가공송전 순시점검 위탁공사","154kV 소양T/L No.24~25 수목벌채","2023-09-22 09:00","2023-09-22 18:00","2023-09-22 09:00","2023-09-22 18:00","연속"]
[286,"강원","직할","홍천남춘천 T/L","2023년 강원본부 직할 154kV GIS, GCB 정밀점검 공사","2023년 강원본부 직할 154kV GIS, GCB 정밀점검 공사 - 남춘천S/S 154kV 홍천-남춘천 T/L GIS 정밀점검","2023-09-18 09:00","2023-09-21 18:00","2023-09-18 09:00","2023-09-21 18:00","연속"]
[287,"강원","직할","상남인제#2 T/L","2023년 가공송전 순시점검 위탁공사","154kV 상제 T/L No.17~18 수목벌채","2023-09-26 09:00","2023-09-27 18:00","2023-09-26 09:00","2023-09-27 18:00","매일"]
[288,"강원","직할","간성인제#1 T/L","2022~2023년 강원본부 직할 가공송전협력회사 총액공사","수평 추락방지장치 설치","2023-09-18 08:00","2023-09-20 18:00","2023-09-18 08:00","2023-09-20 18:00","매일"]
[289,"강원","직할","간성인제#2 T/L","2022~2023년 강원본부 직할 가공송전협력회사 총액공사","수평 추락방지장치 설치","2023-09-21 08:00","2023-09-23 18:00","2023-09-21 08:00","2023-09-23 18:00","매일"]
[290,"강원","직할","가평춘천HP T/L","2023년 강원본부 직할 154kV GIS, GCB 정밀점검 공사","2023년 강원본부 직할 154kV GIS, GCB 정밀점검 공사 - 춘천HP 154kV 가평춘천HP T/L GIS 정밀점검","2023-09-25 09:00","2023-09-27 18:00","2023-09-25 09:00","2023-09-27 18:00","연속"]
[291,"강원","직할","춘천소양강HP T/L","2023년 가공송전 순시점검 위탁공사","154kV 춘천분기 No.5~6 수목벌채","2023-09-25 09:00","2023-09-25 18:00","2023-09-25 09:00","2023-09-25 18:00","연속"]
[292,"강원","태백","고한영월에코윈드 T/L","22-23년 태백전력지사 변전협력회사 총액공사","고한S/S 154kV 고한-영월T/L LA 보통점검","2023-09-22 09:00","2023-09-22 18:00","2023-09-22 09:00","2023-09-22 18:00","연속"]
[293,"강원","태백","태백고한 T/L","2023년 태백전력지사 변전협력회사 총액공사","154kV 태백-고한T/L 보호반 교체 154kV 태백-고한T/L LA보통점검(병행)","2023-09-11 09:00","2023-09-15 18:00","2023-09-11 09:00","2023-09-15 18:00","연속"]
[294,"강원","태백","태백삼척GP#2 T/L","2023년 가공송전 순시점검 위탁공사","송전선로 선하지 지장수목 벌채","2023-09-17 08:00","2023-09-17 15:00","2023-09-17 08:00","2023-09-17 15:00","연속"]
[295,"강원","태백","태백삼척GP#2 T/L","2023년 가공송전 순시점검 위탁공사","송전선로 선하지 지장수목 벌채","2023-09-24 08:00","2023-09-24 15:00","2023-09-24 08:00","2023-09-24 15:00","연속"]
[296,"강원","태백","태백삼척GP#2 T/L","2023년 가공송전 순시점검 위탁공사","송전선로 선하지 지장수목 벌채","2023-09-03 08:00","2023-09-03 15:00","2023-09-03 08:00","2023-09-03 15:00","연속"]
[297,"강원","태백","태백삼척GP#2 T/L","2023년 가공송전 순시점검 위탁공사","송전선로 선하지 지장수목 벌채","2023-09-10 08:00","2023-09-10 15:00","2023-09-10 08:00","2023-09-10 15:00","연속"]
[298,"충북","직할","신진천S/S SEC CB 66670","22-23년 충북직할 변전협력회사 총액공사","신진천변전소 #66-67SEC GIS 노후 전자변 교체","2023-09-12 10:00","2023-09-12 18:00","취소","취소","연속"]
[299,"충북","직할","신진천S/S SEC CB 60610","직할 변전협력회사 총액공사","장기미동작 차단기 조작시험","2023-09-21 10:00","2023-09-21 18:00","취소","취소","연속"]
[300,"충북","직할","신진천S/S SEC CB 61620","22-23년 충북직할 변전협력회사 총액공사","신진천변전소 #61-62SEC GIS 노후 전자변 교체","2023-09-22 10:00","2023-09-22 18:00","취소","취소","연속"]
[301,"충북","직할","신진천진천#1 T/L","22-23년 충북직할 변전협력회사 총액공사","154kV GIS 보통점검","2023-09-25 10:00","2023-09-25 18:00","취소","취소","연속"]
[302,"충북","직할","신진천S/S SEC CB 65660","22-23년 충북직할 변전협력회사 총액공사","신진천변전소 #65-66SEC GIS 보통점검","2023-09-26 10:00","2023-09-26 18:00","취소","취소","연속"]
[303,"충북","직할","신진천S/S CB 6200","22-23년 충북직할 변전협력회사 총액공사","154kV GIS 보통점검","2023-09-27 10:00","2023-09-27 18:00","취소","취소","연속"]
[304,"충북","직할","신진천진천#2 T/L","22-23년 충북직할 변전협력회사 총액공사","신진천변전소154kV 신진천-진천#2T/L GIS 노후 전자변 교체","2023-09-13 10:00","2023-09-13 18:00","취소","취소","연속"]
[305,"충북","직할","신진천진천#2 T/L","직할 변전협력회사 총액공사","장기미동작 차단기 조작시험","2023-09-20 10:00","2023-09-20 18:00","취소","취소","연속"]
[306,"충북","청주","오창국사#1 T/L","22-23년 청주전력 변전협력회사 총액공사","170kV GIS 보통점검","2023-09-21 09:00","2023-09-21 18:00","2023-09-21 09:00","2023-09-21 18:00","연속"]
[307,"충북","청주","남청주오송#1 T/L","남청주S/S 154kV 장기사용 GIS 대체공사","154kV 남청주-오송#1T/L 인출Bay 변경","2023-09-16 08:00","2023-09-19 18:00","2023-09-16 08:00","2023-09-19 18:00","연속"]
[308,"충북","청주","남청주청주#1 T/L","`22~`23년 청주전력지사 송전협력회사 총액공사","아킹혼 6기(21,22,23,25,26,30) 폴리머지지애자 6기(2,3,30,66,83,88) 설치","2023-09-11 08:00","2023-09-13 18:00","취소","취소","매일"]
[309,"충북","청주","남청주청주#3 T/L","`22~`23년 청주전력지사 송전협력회사 총액공사","아킹혼 6기(21,22,23,25,26,30) 폴리머지지애자 6기(2,3,30,66,83,88) 설치","2023-09-11 08:00","2023-09-13 18:00","취소","취소","매일"]
[310,"충북","청주","남청주오송#2 T/L","남청주S/S 154kV 장기사용 GIS 대체공사","154kV 남청주-오송#2T/L 인출Bay 변경","2023-09-22 08:00","2023-09-25 18:00","2023-09-22 08:00","2023-09-25 18:00","연속"]
[311,"충북","청주","북청주봉명#2 T/L","장기미동작 차단기 조작시험","장기미동작 차단기 조작시험 대상 : 북청주봉명#2T/L 개폐타임 측정 등","2023-09-22 10:00","2023-09-22 14:00","2023-09-22 10:00","2023-09-22 14:00","연속"]
[312,"충북","청주","북오송전의#2 T/L","154kV 북오송분기 하자처리","154kV 북오송분기T/L 하자처리 공사","2023-09-18 09:00","2023-09-19 18:00","2023-09-18 09:00","2023-09-19 18:00","매일"]
[313,"충북","청주","동천안북오송#1 T/L","154kV 북오송분기 하자처리","154kV 북오송분기T/L 하자처리 공사","2023-09-18 09:00","2023-09-19 18:00","2023-09-18 09:00","2023-09-19 18:00","매일"]
[314,"충북","청주","서청주사직#2 T/L","22-23년 변전협력회사 총액공사","차단기 조작용 전자변교체","2023-09-26 09:00","2023-09-26 18:00","취소","취소","연속"]
[315,"충북","충주","감곡가남#2 T/L","22-23년 충주전력지사 변전정비 총액공사","감곡S/S 154kV 감곡-가남#2T/L GIS 보통점검","2023-09-26 09:00","2023-09-26 18:00","취소","취소","연속"]
[316,"충북","충주","감곡가남#1 T/L","22-23년 충주전력지사 변전정비 총액공사","감곡S/S 154kV 감곡-가남#1T/L GIS 보통점검","2023-09-20 09:00","2023-09-20 18:00","취소","취소","연속"]
[317,"충북","충주","음성금왕#2 T/L","23년 충북본부 직할 송전정비 협력회사 총액공사","추락방지장치 설치 154kV 음성-금왕T/L No.40 ~ 64","2023-09-24 07:30","2023-10-05 18:00","취소","취소","매일"]
[318,"충북","충주","금왕남음성#2 T/L","23년 충북본부 직할 송전정비 협력회사 총액공사","추락방지장치 설치 (병가철탑 휴전) 154kV 음성-금왕T/L No.40 ~ 64","2023-09-17 07:30","2023-09-23 18:00","취소","취소","매일"]
[319,"충북","충주","금왕남음성#1 T/L","23년 충북본부 직할 송전정비 협력회사 총액공사","추락방지장치 설치 (병가철탑 휴전) 154kV 음성-금왕T/L No.40 ~ 64","2023-09-24 07:30","2023-10-05 18:00","취소","취소","매일"]
[320,"충북","충주","점촌단양 T/L","345kV 신제천-신충주 등 6개T/L 송전피뢰기 설치공사","154kV 점촌-단양T/L 송전피뢰기 설치","2023-09-23 07:00","2023-09-24 18:00","취소","취소","매일"]
[321,"충북","충주","점촌단양 T/L","345kV 신제천-신충주 등 6개T/L 송전피뢰기 설치공사","154kV 점촌-단양T/L 송전피뢰기 설치","2023-09-16 07:00","2023-09-17 18:00","취소","취소","매일"]
[322,"충북","충주","북충주충주 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 [No.68~112(45기)]","2023-09-23 08:00","2023-09-24 17:00","2023-09-23 08:00","2023-09-24 17:00","매일"]
[323,"충북","충주","신제천S/S #62 BUS","345kV 신제천S/S #4 M.Tr 대체공사","#4 M.Tr 대체분 154kV 무부하가압 및 실부하 위상체크용","2023-09-19 09:00","2023-09-22 18:00","2023-09-19 09:00","2023-09-22 18:00","연속"]
[324,"충북","충주","신충주음성#1 T/L","22-23년 충주전력지사 변전정비 총액공사","신충주S/S 154kV 신충주-음성#1T/L GIS 박동원","2023-09-25 09:00","2023-09-25 18:00","취소","취소","연속"]
[325,"충북","충주","신충주북충주#1 T/L","2023년도 가공송전 순시점검 위탁공사","154kV 신충주-북충주 #1T/L No.87 지장수목 벌채","2023-09-25 07:00","2023-09-26 18:00","2023-09-25 07:00","2023-09-26 18:00","매일"]
[326,"충북","충주","신충주음성#2 T/L","22-23년 충주전력지사 변전정비 총액공사","신충주S/S 154kV 신충주-음성#2T/L GIS","2023-09-26 09:00","2023-09-26 18:00","취소","취소","연속"]
[327,"충북","충주","왕암충주 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 [No.1~112(93기)]","2023-09-16 08:00","2023-09-22 17:00","2023-09-16 08:00","2023-09-22 17:00","매일"]
[328,"충북","충주","왕암북충주 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 [No.1~58(48기)","2023-09-25 08:00","2023-09-27 17:00","2023-09-25 08:00","2023-09-27 17:00","매일"]
[329,"충북","충주","풍동음성#1 T/L","23년 충북본부 직할 송전정비 협력회사 총액공사","풍동-음성T/L 추락방지장치 설치 154kV 풍동음성T/L No. 1 ~ 92","2023-09-10 07:30","2023-09-16 18:00","취소","취소","매일"]
[330,"충북","충주","음성괴산 T/L","23년 충북본부 직할 송전정비 협력회사 총액공사","풍동-음성T/L 추락방지장치 설치 154kV 풍동음성T/L No. 54 ~ 92 (병행선로 휴전)","2023-09-10 07:30","2023-09-16 18:00","취소","취소","매일"]
[331,"충북","충주","음성금왕#1 T/L","23년 충북본부 직할 송전정비 협력회사 총액공사","추락방지장치 설치 154kV 음성-금왕T/L No.40 ~ 64","2023-09-17 07:30","2023-09-23 18:00","취소","취소","매일"]
[332,"충북","충주","음성사리 T/L","23년 충북본부 직할 송전정비 협력회사 총액공사","풍동-음성T/L 추락방지장치 설치 154kV 풍동음성T/L No. 54 ~ 92 (병행선로 휴전)","2023-09-03 07:30","2023-09-09 18:00","취소","취소","매일"]
[333,"충북","충주","장연S/S #1 BUS","장연S/S 154, 23kV 장기사용 GIS 대체공사(SA 병행)","154kV 장기사용 GIS 대체 (#2 M.Tr 1차 GIS 등 6Bay)","2023-09-22 09:00","2023-10-09 18:00","2023-09-22 09:00","2023-10-09 18:00","연속"]
[334,"충북","충주","장연S/S #2 BUS","장연S/S 154, 23kV 장기사용 GIS 대체공사(SA 병행)","154kV 장기사용 GIS 대체 (#2 M.Tr 1차 GIS 등 6Bay)","2023-09-22 09:00","2023-10-09 18:00","2023-09-22 09:00","2023-10-09 18:00","연속"]
[335,"충북","충주","충주장연 T/L","장연S/S 154, 23kV 장기사용 GIS 대체공사(SA 병행)","154kV 장기사용 GIS 대체 (#2 M.Tr 1차 GIS 등 6Bay)","2023-09-22 09:00","2023-10-09 18:00","2023-09-22 09:00","2023-10-09 18:00","연속"]
[336,"충북","충주","충주충주HP#1 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 [No.7~22(16기)]","2023-09-18 08:00","2023-09-19 17:00","2023-09-18 08:00","2023-09-19 17:00","매일"]
[337,"충북","충주","충주충주HP#2 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 [No.7~22(16기)]","2023-09-23 08:00","2023-09-24 17:00","2023-09-23 08:00","2023-09-24 17:00","매일"]
[338,"충북","충주","풍동음성#2 T/L","23년 충북본부 직할 송전정비 협력회사 총액공사","풍동-음성T/L 추락방지장치 설치 154kV 풍동음성T/L No. 1 ~ 92 총 78기","2023-09-01 07:30","2023-09-09 18:00","취소","취소","매일"]
[339,"대전세종충남","대전","신옥천남대전#4 T/L","[송전]345kV신옥천-청양등17개T/L추락방지시설 설치공사","[송전] 154kV 신옥천-남대전삼사T/L 추락방지시설 설치공사","2023-09-25 08:00","2023-10-12 18:00","2023-09-25 08:00","2023-10-12 18:00","매일"]
[340,"대전세종충남","대전","신옥천남대전#1 T/L","[송전]345kV신옥천-청양등17개T/L추락방지시설 설치공사","[송전] 154kV 신옥천-남대전T/L 추락방지시설 설치공사","2023-09-11 08:00","2023-09-22 18:00","2023-09-11 08:00","2023-09-22 18:00","매일"]
[341,"대전세종충남","대전","신옥천남대전#1 T/L","[송전취소시]남대전S/S 신옥천-남대전#1T/L GIS 초기점검","[송전취소시]남대전S/S 신옥천-남대전#1T/L GIS 초기점검","2023-09-19 09:00","2023-09-19 18:00","2023-09-19 09:00","2023-09-19 18:00","연속"]
[342,"대전세종충남","대전","신옥천남대전#4 T/L","[송전취소시]남대전S/S 신옥천-남대전#4T/L GIS 초기점검","[송전취소시]남대전S/S 신옥천-남대전#4T/L GIS 초기점검","2023-09-26 09:00","2023-09-26 18:00","2023-09-26 09:00","2023-09-26 18:00","연속"]
[343,"대전세종충남","대전","신계룡두마#1 T/L","신계룡,두마S/S 154kV 신계룡-두마#1T/L 보호반 교체","신계룡,두마S/S 154kV 신계룡-두마#1T/L 보호반 교체","2023-09-11 09:00","2023-09-13 13:00","2023-09-11 09:00","2023-09-13 13:00","연속"]
[344,"대전세종충남","대전","신계룡두마#2 T/L","신계룡,두마S/S 154kV 신계룡-두마#2T/L 보호반 교체","신계룡,두마S/S 154kV 신계룡-두마#2T/L 보호반 교체","2023-09-13 13:00","2023-09-15 18:00","2023-09-13 13:00","2023-09-15 18:00","연속"]
[345,"대전세종충남","서산","석문당진화력#1 T/L","서산P/O 154kV 효성제 CB 베어링 교체공사","당진화력S/S 154kV 석문-당진화력#1T/L 617 CB 베어링 교체 (병행1) 석문S/S 617 GIS IED 성능개선 (병행2) 당진화력S/S 617 GIS 보통점검 (병행3) 석문S/S 617 GIS 보통점검","2023-09-19 09:00","2023-09-20 18:00","취소","취소","매일"]
[346,"대전세종충남","서산","석문당진화력#2 T/L","서산P/O 154kV 효성제 CB 베어링 교체공사","당진화력S/S 154kV 석문-당진화력#1T/L 627 CB 베어링 교체 (병행1) 석문S/S 687 GIS IED 성능개선 (병행2) 당진화력S/S 627 GIS 보통점검 (병행3) 석문S/S 687 GIS 보통점검","2023-09-21 09:00","2023-09-22 18:00","취소","취소","매일"]
[347,"대전세종충남","서산","대산석문#1 T/L","154kV 대산-석문T/L 항공장애표시구 설치","154kV 대산-석문T/L 항공장애표시구 설치(8경간) No.19~20,29~30,31~34,35~36,38~40","2023-09-18 08:00","2023-09-21 18:00","취소","취소","매일"]
[348,"대전세종충남","서산","서산해미 T/L","23년 서산P/O 장기사용 배전반 교체공사","154kV 서산-해미T/L 보호반 대체공사","2023-09-11 09:00","2023-09-14 18:00","취소","취소","연속"]
[349,"대전세종충남","서산","서산홍성 T/L","23년 서산P/O 장기사용 배전반 교체공사","154kV 서산-홍성T/L 보호반 대체공사","2023-09-04 09:00","2023-09-07 18:00","2023-09-04 09:00","2023-09-07 18:00","연속"]
[350,"대전세종충남","서산","서산대산 T/L","23년 서산P/O 장기사용 배전반 교체공사","154kV 서산-대산T/L 보호반 대체공사","2023-09-25 09:00","2023-09-27 18:00","2023-09-25 09:00","2023-09-27 18:00","연속"]
[351,"대전세종충남","서산","신당진서산#2 T/L","154kV 신당진-서산 T/L 상간스페이서 설치","상간스페이서 설치 : No.57~58","2023-09-26 08:00","2023-09-27 18:00","2023-09-21 08:00","2023-09-22 18:00","매일"]
[352,"대전세종충남","서산","서산태안 T/L","154kV 태안분기T/L 건설공사","154jV 태안분기T/L 건설공사 휴전작업 개요(154kV 서산-태안T/L) ○ No.59~62 상단 전력선 공중이동 연,긴선 ○ No.58~64 하단 전력선 연,긴선 ○ No.79~태안S/T 연,긴선","2023-09-07 07:00","2023-09-20 18:00","2023-09-07 07:00","2023-09-20 18:00","연속"]
[353,"대전세종충남","서산","서산태안화력 T/L","154kV 태안분기T/L 건설공사","154jV 태안분기T/L 건설공사 휴전작업 개요(No.51,57,58) ○ No.51~58 및 No.57~58 전력선 공중이동 연,긴선","2023-09-03 07:00","2023-09-06 18:00","2023-09-03 07:00","2023-09-06 18:00","연속"]
[354,"대전세종충남","서산","서산태안 T/L","태안S/S 154kV 모선구분차단기 및 태안분기T/L GIS 증설공사","#1BUS 휴전작업 절연 안전이격 확보","2023-09-07 09:00","2023-09-07 18:00","2023-09-07 09:00","2023-09-07 18:00","연속"]
[355,"대전세종충남","서산","서산태안 T/L","태안S/S 154kV 모선구분차단기 및 태안분기T/L GIS 증설공사","#2BUS 휴전작업 절연 안전이격 확보","2023-09-13 09:00","2023-09-13 18:00","2023-09-13 09:00","2023-09-13 18:00","연속"]
[356,"대전세종충남","서산","태안태안화력 T/L","154kV 태안분기T/L 건설공사","154kV 태안분기T/L 건설공사 휴전작업 개요(154kV 태안-태안화력T/L) ○ No.59~62 상단 전력선 공중이동 연,긴선 ○ No.58~64 하단 전력선 연,긴선 ○ N79~태안S/T 연,긴선","2023-09-21 07:00","2023-10-11 18:00","2023-09-21 07:00","2023-10-11 18:00","연속"]
[357,"대전세종충남","서산","서산태안화력 T/L","태안화력S/Y 154kV 옥외 기타설비 내장화공사","태안화력S/Y 154kV 옥외 기타설비(LA, CVT) 내장화공사","2023-09-03 09:00","2023-09-06 18:00","2023-09-03 09:00","2023-09-06 18:00","연속"]
[358,"대전세종충남","서산","태안태안화력 T/L","154kV 태안화력T/L 전선접속개소 전선교체공사","154kV 태안-태안화력T/L 전력선 교체공사(3개소) - No.2~6, 6~8, 11~13","2023-09-21 08:00","2023-09-27 18:00","2023-09-21 08:00","2023-09-27 18:00","연속"]
[359,"대전세종충남","서산","합덕송악#1 T/L","154kV 합덕S/S 당진전철#1,2T/L 증설공사","154kV 합덕S/S 당진전철#1,2T/L 상확인 및 실부하운전","2023-09-18 10:00","2023-09-18 18:00","취소","취소","연속"]
[360,"대전세종충남","서산","해미홍성 T/L","154kV 해미-홍성T/L 정밀점검","(송전) 9/18~9/27 154kV 해미-홍성T/L 정밀점검(S/T~No.64)_매일_주말제외 (변전) 9/25~9/27 154kV 해미-홍성T/L 보호반 대체_연속","2023-09-18 08:00","2023-09-27 18:00","취소","취소","연속"]
[361,"대전세종충남","세종","덕진공주#1 T/L","[변전]'23년 세종전력지사 변전협력회사 총액공사","○ 덕진S/S 154kV 덕진-공주#1T/L GIS 차단기 전자변 교체","2023-09-11 10:00","2023-09-11 18:00","2023-09-11 10:00","2023-09-11 18:00","연속"]
[362,"대전세종충남","세종","세종월산#1 T/L","월산S/S 남부열병합#1,2T/L 증설공사","월산S/S 남부열병합#1,2T/L 증설 - 증설 선로 상회전 검사","2023-09-22 08:00","2023-09-22 18:00","2023-09-27 08:00","2023-09-27 18:00","연속"]
[363,"대전세종충남","세종","월산서세종 T/L","[변전]'23년 세종전력지사 변전협력회사 총액공사","○154kV GIS 보통점검 -LA 보통점검 병행","2023-09-18 10:00","2023-09-18 18:00","2023-09-18 10:00","2023-09-18 18:00","연속"]
[364,"대전세종충남","세종","월산S/S CB 6100","월산S/S 남부열병합#1,2T/L 증설공사","월산S/S 남부열병합#1,2T/L 증설 - 모선보호반 연동시험","2023-09-21 08:00","2023-09-21 18:00","2023-09-26 08:00","2023-09-26 18:00","연속"]
[365,"대전세종충남","세종","월산S/S #1 BUS","월산S/S 남부열병합#1,2T/L 증설공사","월산S/S 남부열병합#1,2T/L 증설 - 증설 선로 상회전 검사","2023-09-22 08:00","2023-09-22 13:00","2023-09-27 08:00","2023-09-27 13:00","연속"]
[366,"대전세종충남","세종","월산S/S #2 BUS","월산S/S 남부열병합#1,2T/L 증설공사","월산S/S 남부열병합#1,2T/L 증설 - 증설 선로 상회전 검사","2023-09-22 13:00","2023-09-22 18:00","2023-09-27 13:00","2023-09-27 18:00","연속"]
[367,"대전세종충남","직할","동대전신탄진#1 T/L","154kV 동대전-신탄진T/L No.19~21 안전이격공사","154kV 동대전-신탄진T/L No.19~21 안전이격공사(철탑3기신설) #1,#2T/L 양회선 동시휴전 신청","2023-09-20 09:00","2023-11-10 18:00","2023-09-20 09:00","2023-11-10 18:00","연속"]
[368,"대전세종충남","직할","동대전신탄진#2 T/L","154kV 동대전-신탄진T/L No.19~21 안전이격공사","154kV 동대전-신탄진T/L No.19~21 안전이격공사(철탑3기신설) #1,#2T/L 양회선 동시휴전 신청","2023-09-20 09:00","2023-11-10 18:00","2023-09-20 09:00","2023-11-10 18:00","연속"]
[369,"대전세종충남","직할","둔곡송강#1 T/L","2023년 직할 170kV GIS 정밀점검 공사","2023년 직할 170kV GIS 정밀점검 공사 (병행) 송전선로 보호반 세니온제 IED 성능개선","2023-09-09 09:00","2023-09-10 18:00","2023-09-09 09:00","2023-09-10 18:00","연속"]
[370,"대전세종충남","직할","송강신일#2 T/L","신일S/S 170kV GIS 주기도래점검","신일S/S 170kV GIS 보통점검","2023-09-07 09:00","2023-09-07 16:00","2023-09-07 09:00","2023-09-07 16:00","연속"]
[371,"대전세종충남","직할","부강신탄진 T/L","부강-신탄진T/L CB 주기도래 점검(보통점검)","- 부강-신탄진T/L CB 보통점검 - CVT 보통점검, LA제외(21년 점검 시행)","2023-09-18 09:00","2023-09-18 18:00","2023-09-18 09:00","2023-09-18 18:00","연속"]
[372,"대전세종충남","직할","신탄진대청HP T/L","154kV 신탄진S/S 미래화 관련 전력구 설치공사(토목)","- 가시설물 설치 관련 안전이격 확보","2023-09-20 09:00","2023-09-27 18:00","2023-09-20 09:00","2023-09-27 18:00","연속"]
[373,"대전세종충남","천안","둔포직산#1 T/L","추락방지장치 설치공사","154kV 직산-둔포 #1T/L 추락방지장치 설치","2023-09-20 07:00","2023-09-20 17:00","2023-09-14 07:00","2023-09-14 17:00","연속"]
[374,"대전세종충남","천안","둔포직산#2 T/L","추락방지장치 설치공사","154kV 직산-둔포 #2T/L 추락방지장치 설치","2023-09-21 07:00","2023-09-21 17:00","2023-09-15 07:00","2023-09-15 17:00","연속"]
[375,"대전세종충남","천안","서천안탕정#2 T/L","154kV 서천안-탕정#2T/L 보호배전반 성능개선","154kV 서천안-탕정#2T/L 보호배전반 성능개선","2023-09-12 09:00","2023-09-12 18:00","2023-09-12 09:00","2023-09-12 18:00","연속"]
[376,"대전세종충남","천안","서천안탕정#1 T/L","154kV 서천안-탕정#1T/L 보호배전반 성능개선","154kV 서천안-탕정#1T/L 보호배전반 성능개선","2023-09-11 09:00","2023-09-11 18:00","2023-09-11 09:00","2023-09-11 18:00","연속"]
[377,"대전세종충남","천안","서천안S/S SEC CB 60610","서천안SS 154kV 60-61-0GIS 보통점검","서천안SS 154kV 60-61-0GIS 보통점검","2023-09-14 09:00","2023-09-14 18:00","취소","취소","연속"]
[378,"대전세종충남","천안","서천안S/S SEC CB 65660","서천안SS 154kV 65-66-0GIS 보통점검","서천안SS 154kV 65-66-0GIS 보통점검","2023-09-13 09:00","2023-09-13 18:00","취소","취소","연속"]
[379,"대전세종충남","천안","둔포석곡#2 T/L","추락방지장치 설치공사","154kV 둔포-석곡 #2T/L 추락방지장치 설치","2023-09-27 07:00","2023-09-27 17:00","2023-09-19 07:00","2023-09-19 17:00","연속"]
[380,"대전세종충남","천안","둔포석곡#1 T/L","추락방지장치 설치공사","154kV 둔포-석곡 #1T/L 추락방지장치 설치","2023-09-26 07:00","2023-09-26 17:00","2023-09-18 07:00","2023-09-18 17:00","연속"]
[381,"대전세종충남","천안","아산인주#2 T/L","추락방지장치 설치공사","154kV 아산-인주 #2T/L 추락방지장치 설치","2023-09-11 07:00","2023-09-12 17:00","취소","취소","매일"]
[382,"대전세종충남","천안","아산예산#1 T/L","(송전)22~23년 천안전력지사 가공송전협력회사 총액공사","공사구간 ㅇ154kV 아산-예산 #1T/L 추락방지장치 설치 ㅇ154kV 아산-온양#2T/L 추락방지장치 설치","2023-09-21 06:00","2023-09-27 18:00","취소","취소","매일"]
[383,"대전세종충남","천안","아산온양#2 T/L","(송전)22~23년 천안전력지사 가공송전협력회사 총액공사","공사구간 ㅇ154kV 아산-예산 #1T/L 추락방지장치 설치 ㅇ154kV 아산-온양#2T/L 추락방지장치 설치","2023-09-26 06:00","2023-10-06 18:00","취소","취소","매일"]
[384,"대전세종충남","천안","아산인주#2 T/L","(8월취소시)아산,인주S/S 154kV 아산-인주#2T/L 보호반 교체","(8월취소시)아산,인주S/S 154kV 아산-인주#2T/L 보호반 교체","2023-09-11 09:00","2023-09-15 18:00","취소","취소","연속"]
[385,"대전세종충남","천안","아산온양#1 T/L","(송전)22~23년 천안전력지사 가공송전협력회사 총액공사","공사구간 ㅇ154kV 아산-예산 #2T/L 추락방지장치 설치 ㅇ154kV 아산-온양#1T/L 추락방지장치 설치","2023-09-11 06:00","2023-09-15 18:00","취소","취소","매일"]
[386,"대전세종충남","천안","아산예산#2 T/L","(송전)22~23년 천안전력지사 가공송전협력회사 총액공사","공사구간 ㅇ154kV 아산-예산 #2T/L 추락방지장치 설치 ㅇ154kV 아산-온양#1T/L 추락방지장치 설치","2023-09-14 06:00","2023-09-20 18:00","취소","취소","매일"]
[387,"대전세종충남","천안","아산인주#1 T/L","추락방지장치 설치공사","154kV 아산-인주 #1T/L 추락방지장치 설치","2023-09-07 07:00","2023-09-08 17:00","취소","취소","매일"]
[388,"대전세종충남","천안","아산인주#1 T/L","(8월취소시)아산,인주S/S 154kV 아산-인주#1T/L 보호반 교체","(8월취소시)아산,인주S/S 154kV 아산-인주#1T/L 보호반 교체","2023-09-04 09:00","2023-09-08 18:00","취소","취소","연속"]
[389,"대전세종충남","천안","아산합덕#1 T/L","아산S/S 154kV 아산-합덕#1T/L EDS부 보수","아산S/S 154kV 아산-합덕#1T/L EDS부 보수","2023-09-04 09:00","2023-09-05 18:00","취소","취소","연속"]
[390,"대전세종충남","천안","아산예산#1 T/L","154kV #5,#6 EM.Tr 1차측 전력케이블 설차공사","154kV #6 EM.Tr 1차측 EBG_KP접속에 따른 인출 활선부위 안전이격거리확보 T/L 휴전수반","2023-09-06 09:00","2023-09-07 18:00","2023-09-06 09:00","2023-09-07 18:00","매일"]
[391,"대전세종충남","천안","온양풍세#1 T/L","(송전)22~23년 천안전력지사 가공송전협력회사 총액공사","공사구간 ㅇ154kV 아산-온양#1T/L 추락방지장치 설치 ※ 154kV 온양-풍세#1T/L 안전거리 확보","2023-09-11 06:00","2023-09-12 18:00","취소","취소","매일"]
[392,"대전세종충남","천안","인주불당#2 T/L","인주S/S 154kV 인주-불당#2T/L CB 개폐타임 측정","인주S/S 154kV 인주-불당#2T/L CB 개폐타임 측정","2023-09-15 14:00","2023-09-15 18:00","취소","취소","연속"]
[393,"대전세종충남","천안","인주불당#1 T/L","인주S/S 154kV 인주-불당#1T/L CB 개폐타임 측정","인주S/S 154kV 인주-불당#1T/L CB 개폐타임 측정","2023-09-15 09:00","2023-09-15 14:00","취소","취소","연속"]
[394,"대전세종충남","천안","온양풍세#2 T/L","추락방지장치 설치공사","154kV 온양-풍세 #2T/L 추락방지장치 설치","2023-09-25 07:00","2023-09-25 17:00","2023-09-13 07:00","2023-09-13 17:00","연속"]
[395,"대전세종충남","천안","풍세장재#2 T/L","154kV 풍세-장재#2T/L 보호배전반 성능개선","154kV 풍세-장재#2T/L 보호배전반 성능개선","2023-09-19 09:00","2023-09-19 18:00","2023-09-19 09:00","2023-09-19 18:00","연속"]
[396,"대전세종충남","천안","풍세장재#1 T/L","154kV 풍세-장재#1T/L 보호배전반 성능개선","154kV 풍세-장재#1T/L 보호배전반 성능개선","2023-09-18 09:00","2023-09-18 18:00","2023-09-18 09:00","2023-09-18 18:00","연속"]
[397,"대전세종충남","천안","한샘직산#2 T/L","추락방지장치 설치공사","154kV 한샘-직산 #2T/L 추락방지장치 설치","2023-09-21 07:00","2023-09-21 17:00","2023-09-15 07:00","2023-09-15 17:00","연속"]
[398,"대전세종충남","천안","한샘직산#1 T/L","추락방지장치 설치공사","154kV 한샘-직산 #1T/L 추락방지장치 설치","2023-09-20 07:00","2023-09-20 17:00","2023-09-14 07:00","2023-09-14 17:00","연속"]
[399,"대전세종충남","청양","관창대천#2 T/L","[송전] 2023년 가공송전 순시점검 위탁공사(청양전력)","154kV 관창-대천T/L 전선접속개소 과열 정비 1. 작업내역 : 과열개소 정비 2. 작업개소 : No.25","2023-09-21 08:00","2023-09-21 18:00","취소","취소","연속"]
[400,"대전세종충남","청양","관창보령TP T/L","청양P/O 변전협력회사 총액공사","154kV 관창-보령화력#T/L 보호반 대체공사 - 관창S/S 차단기 조작시험 - 보령T/P 차단기 조작시험","2023-09-04 10:00","2023-09-06 18:00","취소","취소","연속"]
[401,"대전세종충남","청양","관창대천#1 T/L","청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","154kV 관창-대천#1T/L - 관창S/S GIS 보통점검 및 노후보조계전기 교체","2023-09-07 10:00","2023-09-08 18:00","취소","취소","연속"]
[402,"대전세종충남","청양","보령TP보령CC T/L","청양P/O 변전협력회사 총액공사","154kV 보령복합T/L - 보령T/P 차단기 조작시험","2023-09-25 10:00","2023-09-25 18:00","취소","취소","연속"]
[403,"대전세종충남","청양","신서천옥산#1 T/L","[송전] 2023년 가공송전 순시점검 위탁공사(청양전력)","154kV 옥산-서천T/L 전선접속개소 과열 정비 1. 작업내역 : 과열개소 정비 2. 작업개소 : No.5","2023-09-18 08:00","2023-09-19 18:00","취소","취소","매일"]
[404,"대전세종충남","청양","신서천대천#1 T/L","[송전] 2023년 가공송전 순시점검 위탁공사(청양전력)","154kV 대천-서천T/L 전선접속개소 과열 정비 1. 작업내역 : 과열개소 정비 2. 작업개소 : No.1, 5, 8, 10, 12, 22, 35, 91","2023-09-18 08:00","2023-09-19 18:00","취소","취소","매일"]
[405,"대전세종충남","청양","신서천대천#2 T/L","[송전] 2023년 가공송전 순시점검 위탁공사(청양전력)","154kV 대천-서천T/L 전선접속개소 과열 정비 1. 작업내역 : 과열개소 정비 2. 작업개소 : No.12, 35","2023-09-20 08:00","2023-09-20 18:00","취소","취소","연속"]
[406,"대전세종충남","청양","신서천옥산#2 T/L","[송전] 2023년 가공송전 순시점검 위탁공사(청양전력)","154kV 대천-서천T/L 전선접속개소 과열 정비 (병가철탑 휴전) 1. 작업내역 : 과열개소 정비 2. 작업개소 : No.12, 35","2023-09-20 08:00","2023-09-20 18:00","취소","취소","연속"]
[407,"대전세종충남","청양","청양신풍#2 T/L","청양P/O 변전협력회사 총액공사","154kV 청양-신풍#2TL - 청양S/S 차단기 조작시험 및 LA 초기점검(A,B,C)","2023-09-05 08:00","2023-09-05 18:00","취소","취소","연속"]
[408,"대전세종충남","청양","신서천옥산#1 T/L","청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","154kV 옥산-서천#1T/L - 옥산S/S 170kV GIS 보통점검 및 노후보조계전기 교체 - 옥산S/S LA 보통점검(A,B,C)","2023-09-26 10:00","2023-09-27 18:00","취소","취소","연속"]
[409,"대전세종충남","청양","신서천옥산#2 T/L","청양P/O 변전협력회사 총액공사","154kV 옥산-서천#2T/L - 옥산S/S 차단기 조작시험","2023-09-22 10:00","2023-09-22 18:00","취소","취소","연속"]
[410,"대전세종충남","청양","청양은하#2 T/L","(8월취소시)청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","154kV 청양-은하 #2T/L (8월취소시) - 은하S/S GIS 보통점검 및 노후보조계전기 교체 - 청양S/S 차단기 조작시험","2023-09-12 10:00","2023-09-12 18:00","2023-09-12 10:00","2023-09-12 18:00","연속"]
[411,"대전세종충남","청양","은하홍성#2 T/L","154kV 은하-홍성T/L 정밀점검","[서산] 9/18~9/22 154kV 은하-홍성T/L 정밀점검(S/T~No.49)_매일_주말제외 [서산] 9/25~9/27 154kV 은하-홍성T/L 점퍼지지애자 교체공사, 항공장애표시구 설치공사 [청양] 9/18~9/22 154kV 은하-홍성T/L 수평추락방지장치 설치공사","2023-09-18 08:00","2023-09-27 18:00","2023-09-18 08:00","2023-09-27 18:00","매일"]
[412,"대전세종충남","청양","옥산장항#2 T/L","청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","154kV 옥산-장항#2T/L - 장항S/S GIS 보통점검 및 노후보조계전기 교체 - 장항S/S LA초기점검(A,B,C) - 옥산S/S 차단기 조작시험","2023-09-21 10:00","2023-09-21 18:00","취소","취소","연속"]
[413,"대전세종충남","청양","옥산장항#1 T/L","청양P/O 변전협력회사 총액공사","154kV 옥산-장항#1T/L - 옥산S/S 차단기 조작시험 - 장항S/S LA 초기점검(A,B,C)","2023-09-25 10:00","2023-09-25 18:00","취소","취소","연속"]
[414,"대전세종충남","청양","동군산장항#1 T/L","청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","- 170kV GIS 보통점검(동군산-장항#1T/L 보호반 대체공사 취소시 당일작업)","2023-09-12 10:00","2023-09-12 18:00","2023-09-12 10:00","2023-09-12 18:00","연속"]
[415,"대전세종충남","청양","청양관창#1 T/L","[송전] 154kV 청양-관창T/L 지장송전선로 이설공사","○ 공사구간 : 154kV 청양-관창T/L No.3~8 ○ 지지물 : 신설 1기 설치, 임시 2기 설치/철거, 기설 1기 철거 ○ 전력선 : ACSR 410 x 2B x 2C, 1.473km(전선교체)","2023-09-18 07:00","2023-09-20 18:00","취소","취소","연속"]
[416,"대전세종충남","청양","청양은하#1 T/L","[송전] 154kV 청양-은하#1T/L 철탑 추락방지장치 설치공사(수평)","154kV 청양-은하#1T/L 철탑 추락방지장치 설치공사(수평) * 9.20~9.22 : 154kV 은하-홍성#2T/L 4회선 구간 작업","2023-09-13 08:00","2023-09-22 18:00","2023-09-13 08:00","2023-09-22 18:00","매일"]
[417,"대전세종충남","청양","청양S/S SEC CB 65660","청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","청양S/S 154kV 65-66-0 B/S - 170kV GIS 보통점검 및 노후보조계전기 교체","2023-09-04 10:00","2023-09-05 18:00","2023-09-25 10:00","2023-09-26 18:00","연속"]
[418,"대전세종충남","청양","청양관창#2 T/L","[송전] 154kV 청양-관창T/L 지장송전선로 이설공사","○ 공사구간 : 154kV 청양-관창T/L No.3~8 ○ 지지물 : 신설 1기 설치, 임시 2기 설치/철거, 기설 1기 철거 ○ 전력선 : ACSR 410 x 2B x 2C, 1.473km(전선교체)","2023-09-21 07:00","2023-09-23 18:00","취소","취소","연속"]
[419,"대전세종충남","청양","해미홍성 T/L","청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","- 170kV GIS 보통점검(해미-홍성T/L 보호반 대체공사 취소시 당일작업)","2023-09-25 10:00","2023-09-25 18:00","2023-09-16 10:00","2023-09-16 18:00","연속"]
[420,"대전세종충남","청양","서산홍성 T/L","청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","- 170kV GIS 보통점검(서산-홍성T/L 보호반 대체공사 취소시 당일작업)","2023-09-18 10:00","2023-09-18 18:00","2023-09-06 10:00","2023-09-06 18:00","연속"]
[421,"대전세종충남","청양","은하홍성#1 T/L","청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","154kV 은하-홍성 #1T/L (양단작업) - 은하,홍성S/S GIS 보통점검 - 노후보조계전기 교체","2023-09-11 08:00","2023-09-11 18:00","취소","취소","연속"]
[422,"전북","군산","내초SE열병합#1 T/L","SE열병합 154kV 내초-SE열병합#1T/L 차단기 정밀점검","SE열병합 154kV 내초-SE열병합#1T/L 차단기 정밀점검","2023-09-25 09:00","2023-09-26 18:00","2023-09-25 09:00","2023-09-26 18:00","연속"]
[423,"전북","군산","군산동군산#1 T/L","154kV 동군산S/S-군산CC T/L 개폐장치 증설공사(시험가압)","170kV GIS X 2CCT (동군산 1CCT, 군산CC 1CCT)","2023-09-09 18:00","2023-09-10 09:00","취소","취소","연속"]
[424,"전북","군산","군산동군산#1 T/L","154kV 동군산S/S-군산CC T/L 개폐장치 증설공사(시험가압)","170kV GIS X 2CCT (동군산 1CCT, 군산CC 1CCT)","2023-09-16 18:00","2023-09-17 09:00","취소","취소","연속"]
[425,"전북","군산","비응군장#1 T/L","비응S/S #1M.Tr 개폐장치 설치공사(170kV GIS)","170kV GIS x 1CCT (6133)","2023-09-21 18:00","2023-09-22 18:00","2023-09-21 18:00","2023-09-22 18:00","연속"]
[426,"전북","군산","비응군장#1 T/L","비응S/S #1M.Tr 개폐장치 설치공사(170kV GIS)","170kV GIS x 1CCT (6133)","2023-09-15 18:00","2023-09-16 18:00","2023-09-15 18:00","2023-09-16 18:00","연속"]
[427,"전북","군산","군산서군산#1 T/L","154kV 군산-서군산1T/L 차단기 보통점검","154kV 군산-서군산1T/L 차단기 보통점검","2023-09-15 09:00","2023-09-15 14:00","취소","취소","연속"]
[428,"전북","군산","군산서군산#2 T/L","154kV 군산-서군산2T/L 차단기 보통점검","154kV 군산-서군산2T/L 차단기 보통점검","2023-09-15 14:00","2023-09-15 18:00","취소","취소","연속"]
[429,"전북","군산","군산영등#1 T/L","군산P/O 154kV GIS 보통점검","영등S/S 154kV 군산-영등#1T/L GIS 보통점검","2023-09-13 07:00","2023-09-13 18:00","2023-09-13 07:00","2023-09-13 18:00","연속"]
[430,"전북","군산","군산영등#2 T/L","군산P/O 154kV GIS 보통점검","영등S/S 154kV 군산-영등#2T/L GIS 보통점검","2023-09-14 07:00","2023-09-14 18:00","2023-09-14 07:00","2023-09-14 18:00","연속"]
[431,"전북","군산","팔봉왕궁#1 T/L","군산P/O 154kV 차단기 보통점검","왕궁S/S 154kV 왕궁-팔봉#1T/L 차단기 보통점검","2023-09-04 09:00","2023-09-04 18:00","2023-09-04 09:00","2023-09-04 18:00","연속"]
[432,"전북","군산","왕궁봉동#1 T/L","군산P/O 154kV 차단기 보통점검","왕궁S/S 154kV 왕궁-봉동#1T/L 차단기 보통점검","2023-09-06 09:00","2023-09-06 18:00","2023-09-06 09:00","2023-09-06 18:00","연속"]
[433,"전북","군산","왕궁봉동#2 T/L","군산P/O 154kV 차단기 보통점검","왕궁S/S 154kV 왕궁-봉동#2T/L 차단기 보통점검","2023-09-07 09:00","2023-09-07 18:00","2023-09-07 09:00","2023-09-07 18:00","연속"]
[434,"전북","군산","팔봉왕궁#2 T/L","군산P/O 154kV 차단기 보통점검","왕궁S/S 154kV 왕궁-팔봉#2T/L 차단기 보통점검","2023-09-05 09:00","2023-09-05 18:00","2023-09-05 09:00","2023-09-05 18:00","연속"]
[435,"전북","군산","영등팔봉#1 T/L","팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검","팔봉S/S 154kV #4M.Tr 1차 차단기 정밀점검","2023-09-21 17:00","2023-09-21 18:00","취소","취소","연속"]
[436,"전북","군산","팔봉S/S CB 6100","팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검","팔봉S/S 154kV #4M.Tr 1차 GIS 정밀점검","2023-09-20 09:00","2023-09-22 18:00","취소","취소","연속"]
[437,"전북","군산","팔봉S/S #65 BUS","팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검","팔봉S/S 154kV #4M.Tr 1차 GIS 정밀점검","2023-09-22 09:00","2023-09-22 18:00","취소","취소","연속"]
[438,"전북","군산","팔봉S/S #60 BUS","팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검","팔봉S/S 154kV #4M.Tr 1차 GIS 정밀점검","2023-09-20 09:00","2023-09-21 18:00","취소","취소","연속"]
[439,"전북","군산","영등팔봉#1 T/L","팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검","팔봉S/S 154kV #4M.Tr 1차 차단기 정밀점검","2023-09-22 17:00","2023-09-22 18:00","취소","취소","연속"]
[440,"전북","김제","고창홍농 T/L","고창/S 154kV #3M.Tr 1차 GIS 정밀점검공사","고창S/S 154kV #3M.Tr 1차 GIS 정밀점검공사 -시험가압(#1BUS, 고창-홍농T/L)","2023-09-01 15:00","2023-09-01 16:00","2023-09-01 15:00","2023-09-01 16:00","연속"]
[441,"전북","김제","남전주임실#2 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","신김제-동전주T/L 교차구간 안전이격거리 확보차 양회선 휴전","2023-09-04 08:00","2023-09-09 17:00","2023-09-11 08:00","2023-09-15 17:00","연속"]
[442,"전북","김제","남전주임실#2 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","신김제-동전주T/L 교차구간 안전이격거리 확보차 양회선 휴전","2023-09-20 08:00","2023-09-20 17:00","2023-09-20 08:00","2023-09-20 17:00","연속"]
[443,"전북","김제","남전주임실#2 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","신김제-동전주T/L 교차구간 안전이격거리 확보차 양회선 휴전","2023-09-16 08:00","2023-09-16 17:00","2023-09-16 08:00","2023-09-16 17:00","연속"]
[444,"전북","김제","신김제정공#2 T/L","정공S/S 154kV 신김제-정공#2T/L GIS 정밀점검공사","정공S/S 154kV 신김제-정공#2T/L GIS 정밀점검공사","2023-09-21 09:00","2023-09-22 18:00","취소","취소","연속"]
[445,"전북","김제","신김제정공#1 T/L","정공S/S 154kV 신김제-정공#1T/L GIS 정밀점검공사","정공S/S 154kV 신김제-정공#1T/L GIS 정밀점검공사","2023-09-18 09:00","2023-09-19 18:00","취소","취소","연속"]
[446,"전북","김제","정공담양 T/L","정공S/S 154kV #3M.Tr 1차 GIS 정밀점검공사","정공S/S 154kV #3M.Tr 1차 GIS 정밀점검공사 - 시험가압(#1,2BUS, 정공-담양T/L, #6100TIE)","2023-09-13 13:00","2023-09-14 16:00","2023-09-05 13:00","2023-09-06 16:00","매일"]
[447,"전북","김제","정공S/S CB 6200","정공S/S 154kV #3M.Tr 1차 GIS 정밀점검공사","정공S/S 154kV #3M.Tr 1차 GIS 정밀점검공사 - 시험가압(#1,2BUS, 정공-담양T/L, #6200TIE)","2023-09-12 09:00","2023-09-14 18:00","2023-09-04 09:00","2023-09-06 18:00","연속"]
[448,"전북","직할","신김제동전주#2 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","No.33∼36 전력선 연긴선","2023-09-20 08:00","2023-09-23 17:00","2023-09-20 08:00","2023-09-23 17:00","연속"]
[449,"전북","직할","신김제동전주#1 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","No.33∼36 전력선 연긴선","2023-09-16 08:00","2023-09-19 17:00","2023-09-16 08:00","2023-09-19 17:00","연속"]
[450,"전북","직할","동전주북전주#1 T/L","154kV 북전주S/S 디지털 혼용시스템 설치공사","○ 제어케이블 이설공사(RTU → 디지털 혼용장치반)","2023-09-21 09:00","2023-09-21 18:00","2023-09-21 09:00","2023-09-21 18:00","연속"]
[451,"전북","직할","동전주북전주#2 T/L","154kV 북전주S/S 디지털 혼용시스템 설치공사","○ 제어케이블 이설공사(RTU → 디지털 혼용장치반)","2023-09-25 09:00","2023-09-25 18:00","2023-09-25 09:00","2023-09-25 18:00","연속"]
[452,"전북","직할","북전주진안 T/L","154kV 북전주S/S 디지털 혼용시스템 설치공사","○ 제어케이블 이설공사(RTU → 디지털 혼용장치반)","2023-09-26 09:00","2023-09-26 18:00","2023-09-26 16:00","2023-09-26 22:00","연속"]
[453,"전북","직할","북전주S/S CB 6100","154kV 북전주S/S 디지털 혼용시스템 설치공사","○ 제어케이블 이설공사 (RTU → 디지털 혼용장치반)","2023-09-20 09:00","2023-09-20 18:00","2023-09-20 09:00","2023-09-20 18:00","연속"]
[454,"전북","직할","신남원S/S #2 BUS","신남원S/S ESS 건설공사","- 154kV GIS 9Bay 증설 - 154kV M.Tr 60MVA 6bank 설치 - 모선보호반 추가 및 제어케이블 포설/결선 등","2023-09-05 09:30","2023-09-22 15:00","취소","취소","연속"]
[455,"전북","직할","전주서곡#1 T/L","노후배전반 대체공사(보통점검 병행)","노후배전반 대체공사(보통점검 병행)","2023-09-11 09:00","2023-09-13 14:00","취소","취소","연속"]
[456,"전북","직할","전주서곡#2 T/L","노후배전반 대체공사(보통점검 병행)","노후배전반 대체공사(보통점검 병행)","2023-09-13 14:00","2023-09-15 18:00","취소","취소","연속"]
[457,"전북","직할","무주진안 T/L","23년 전북직할 변전협력회사 총액공사","154kV 무주-진안T/L LA, CVT 보통점검","2023-09-14 09:00","2023-09-14 18:00","2023-09-14 16:00","2023-09-14 22:00","연속"]
[458,"광주전남","강진","남창해남CS#1 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","추락방지장치 설치, 고정형 폴리머 점퍼지지애자 교체","2023-09-19 07:00","2023-09-21 18:00","취소","취소","매일"]
[459,"광주전남","강진","남창S/S 모선연계T/L CB","2022~23년도 강진전력지사 변전협력회사 총액공사","2022~23년도 강진전력지사 변전협력회사 총액공사 남창S/S 모선연결T/L GIS 초기점검","2023-09-19 10:00","2023-09-19 14:00","취소","취소","연속"]
[460,"광주전남","강진","강진남창#2 T/L","2022~23년도 강진전력지사 변전협력회사 총액공사","2022~23년도 강진전력지사 변전협력회사 총액공사 남창S/S 강진-남창 #2T/L GIS 초기점검","2023-09-19 14:00","2023-09-19 18:00","취소","취소","연속"]
[461,"광주전남","강진","신강진대불#1 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","항공장애표시구 설치공사","2023-09-25 07:00","2023-09-27 18:00","2023-09-25 07:00","2023-09-27 18:00","매일"]
[462,"광주전남","강진","화원진도#1 T/L","22~23년 철탑 추락방지장치 설치공사","공사명 : 22~23년 철탑 추락방지장치 설치공사 공사구간 : 40~78호","2023-09-04 07:00","2023-09-07 18:00","2023-09-04 07:00","2023-09-07 18:00","매일"]
[463,"광주전남","강진","해남진도#2 T/L","22~23년 철탑 추락방지장치 설치공사","공사명 : 22~23년 철탑 추락방지장치 설치공사 공사구간 : 1~110호","2023-09-11 07:00","2023-09-21 18:00","2023-09-07 07:00","2023-09-18 18:00","매일"]
[464,"광주전남","강진","해남해남CS#1 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","해남-해남CS T/L 추락방지장치(수직,수평) 설치공사","2023-09-11 07:00","2023-09-20 18:00","2023-09-07 07:00","2023-09-18 18:00","매일"]
[465,"광주전남","강진","화원진도#2 T/L","22~23년 목포 송전 협력회사 총액공사(추락방지)","154kV 화원-진도T/L 수평추락방지장치 설치 1~39호","2023-09-04 07:00","2023-09-08 18:00","취소","취소","매일"]
[466,"광주전남","광주","계림남광주 T/L","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2023-09-18 09:00","2023-10-20 18:00","취소","취소","연속"]
[467,"광주전남","광주","계림승주#1 T/L","22-23년 광주변전총액(계림S/S 계림-승주#1T/L PNL 대체)","계림, 승주S/S 계림-승주#1T/L PNL 대체","2023-09-18 09:00","2023-09-21 18:00","2023-09-04 08:00","2023-09-07 18:00","연속"]
[468,"광주전남","광주","계림S/S CB 6100","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2023-09-18 09:00","2023-10-20 18:00","취소","취소","연속"]
[469,"광주전남","광주","계림충장#2 T/L","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2023-09-18 09:00","2023-10-20 18:00","취소","취소","연속"]
[470,"광주전남","광주","계림승주#1 T/L","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","-BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2T/L #60BUS 신설분 무부하 가압","2023-09-26 13:00","2023-09-27 13:00","취소","취소","연속"]
[471,"광주전남","광주","남광주화순#2 T/L","22~23년 직할 가공송전 협력회사 총액공사(수평 추락방지장치 설치)","수평 추락방지장치 설치 (남광주-화순1~337호, 화순-승주 290~296호 병가)","2023-09-18 08:00","2023-09-27 18:00","2023-09-27 08:00","2023-09-27 18:00","연속"]
[472,"광주전남","광주","장성영광#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","장성S/S 154kV 장성-영광#1T/L GIS 보통점검","2023-09-22 09:00","2023-09-22 18:00","취소","취소","연속"]
[473,"광주전남","광주","장성영광#2 T/L","154KV 장성-영광T/L 추락방지장치 설치 및 보조암 설치","-추락방지장치 설치 ㅇ구간 : 154kV 장성-영광 #2T/L No.21~68 ㅇ작업내용 : 철탑 추락방지장치 설치(수평) - 철탑 보조암 설치 ㅇ구간 : 154kV 장성-영광 #2T/L No.49,54,56,65 ㅇ작업내용 : 철탑 보조암 설치","2023-09-04 07:00","2023-09-09 18:00","2023-09-07 07:00","2023-09-08 18:00","매일"]
[474,"광주전남","광주","장성영광#1 T/L","154KV 장성-영광T/L 선종교체공사(NO.1～NO.126)","ㅇ구간 : 154kV 장성-영광 #1T/L No.1~126 ㅇ경간 : 35.9km 전선교체 ㅇ시공사 : 청보전설(주) ㅇ작업내용 : 용량증대 전선교체(ASCC 430SQ로 전량교체)","2023-09-11 08:00","2023-10-31 18:00","2023-09-11 08:00","2023-10-31 18:00","연속"]
[475,"광주전남","광주","하남장성#2 T/L","154KV 장성-영광T/L 선종교체공사(NO.1～NO.126)","※No.15~21 4회선 구간 관련으로 하남-장성#2T/L 안전휴전 시행 ㅇ구간 : 154kV 장성-영광 #1T/L No.1~126 ㅇ경간 : 35.9km 전선교체 ㅇ시공사 : 청보전설(주) ㅇ작업내용 : 용량증대 전선교체(ASCC 430SQ로 전량교체)","2023-09-11 08:00","2023-09-20 18:00","2023-09-11 08:00","2023-09-20 18:00","연속"]
[476,"광주전남","광주","화순승주#1 T/L","22~23년 직할 가공송전 협력회사 총액공사(수평 추락방지장치 설치)","수평 추락방지장치 설치 (남광주-화순1~337호, 화순-승주 290~296호 병가)","2023-09-27 08:00","2023-09-27 18:00","2023-09-14 08:00","2023-09-27 18:00","연속"]
[477,"광주전남","목포","고창영광 T/L","154KV 장성-영광T/L 선종교체공사(NO.1～NO.126)","※No.126 4회선 구간 관련으로 고창-영광T/L 안전휴전 시행 ㅇ구간 : 154kV 장성-영광 #1T/L No.1~126 ㅇ경간 : 35.9km 전선교체 ㅇ시공사 : 청보전설(주) ㅇ작업내용 : 용량증대 전선교체(ASCC 430SQ로 전량교체)","2023-09-11 08:00","2023-09-11 18:00","2023-09-11 08:00","2023-09-11 18:00","연속"]
[478,"광주전남","목포","장성영광#1 T/L","22-23년 목포전력지사 변전협력회사 총액공사","장성-영광#1T/L 154kV LA 보통점검","2023-09-18 09:00","2023-09-18 18:00","취소","취소","연속"]
[479,"광주전남","목포","장성영광#2 T/L","22-23년 목포전력지사 변전협력회사 총액공사","장성-영광#2T/L 154kV LA, CVT 보통점검","2023-09-19 09:00","2023-09-19 18:00","취소","취소","연속"]
[480,"광주전남","목포","고창홍농 T/L","154KV 장성-영광T/L 선종교체공사(NO.1～NO.126)","※No.126 4회선 구간 관련으로 고창-홍농T/L 안전휴전 시행 ㅇ구간 : 154kV 장성-영광 #1T/L No.1~126 ㅇ경간 : 35.9km 전선교체 ㅇ시공사 : 청보전설(주) ㅇ작업내용 : 용량증대 전선교체(ASCC 430SQ로 전량교체)","2023-09-11 08:00","2023-09-11 18:00","2023-09-11 08:00","2023-09-11 18:00","연속"]
[481,"광주전남","순천","광양하동#2 T/L","154kV 광양-하동T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - No.38~91호, 53기","2023-09-11 08:00","2023-09-15 18:00","2023-09-11 08:00","2023-09-15 18:00","매일"]
[482,"광주전남","순천","광양하동#1 T/L","154kV 광양-하동T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - No.38~91호, 53기","2023-09-01 08:00","2023-09-08 18:00","2023-09-01 08:00","2023-09-08 18:00","매일"]
[483,"광주전남","순천","서순천주암HP T/L","22-23년 순천전력지사 변전협력회사 총액공사","서순천S/S 서순천-주암HP T/L GIS 타임측정(즉시가압가능)","2023-09-07 09:00","2023-09-07 18:00","2023-09-07 09:00","2023-09-07 18:00","연속"]
[484,"광주전남","순천","순천승주#1 T/L","154kV 순천-승주T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - No.1~171호, 87기","2023-09-18 08:00","2023-09-27 18:00","취소","취소","매일"]
[485,"광주전남","순천","계림승주#1 T/L","154kV 순천-승주T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - No.2~9호, 4회선 구간","2023-09-20 08:00","2023-09-20 18:00","취소","취소","연속"]
[486,"광주전남","순천","계림승주#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","승주S/S 계림-승주#2T/L GIS 보통점검 및 상시여자 보조계전기 교체_피뢰기 교체","2023-09-21 09:00","2023-09-21 18:00","2023-09-21 09:00","2023-09-21 18:00","연속"]
[487,"광주전남","순천","승주주암HP T/L","22-23년 순천전력지사 변전협력회사 총액공사","승주S/S 승주-주암HP T/L GIS 보통점검 및 보조계전기 교체(즉시가압)","2023-09-06 09:00","2023-09-06 18:00","2023-09-06 09:00","2023-09-06 18:00","연속"]
[488,"광주전남","순천","여수TP용성#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S 여수TP-용성#2T/L GIS 보통점검 및 보조계전기 교체 용성S/S 여수TP-용성#2T/L GIS 보통점검, LA(A, B, C) 보통점검 및 상시여자 보조계전기 교체","2023-09-20 09:00","2023-09-20 18:00","취소","취소","연속"]
[489,"광주전남","순천","여수TP여천#1 T/L","23년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검(즉시가압 불가)","2023-09-18 09:00","2023-09-21 18:00","취소","취소","연속"]
[490,"광주전남","순천","여수TP용성#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S 여수TP-용성#1T/L GIS 보통점검 및 보조계전기 교체 용성S/S 여수TP-용성#1T/L GIS 보통점검, LA(A, B, C) 보통점검 및 상시여자 보조계전기 교체 및 압력계 교체(즉시가압 불가)","2023-09-18 09:00","2023-09-19 18:00","취소","취소","연속"]
[491,"광주전남","순천","여수TP여천#2 T/L","가공송전 위탁공사 정밀점검(여수TP-여천#2 T/L)","가공송전 위탁공사 정밀점검(여수TP-여천#2 T/L) : 8기","2023-09-08 08:00","2023-09-08 18:00","취소","취소","연속"]
[492,"광주전남","순천","여수TP여천#1 T/L","가공송전 위탁공사 정밀점검(여수TP-여천#1 T/L)","가공송전 위탁공사 정밀점검(여수TP-여천#1 T/L) : 8기","2023-09-06 08:00","2023-09-06 18:00","취소","취소","연속"]
[493,"광주전남","순천","여수TP용성#2 T/L","가공송전 위탁공사 정밀점검(여수TP-용성#2 T/L)","가공송전 위탁공사 정밀점검(여수TP-용성#2 T/L) : 4기","2023-09-05 09:00","2023-09-05 18:00","취소","취소","연속"]
[494,"광주전남","순천","여수TP용성#1 T/L","가공송전 위탁공사 정밀점검(여수TP-용성#1 T/L)","가공송전 위탁공사 정밀점검(여수TP-용성#1 T/L) : 4기","2023-09-04 09:00","2023-09-04 18:00","취소","취소","연속"]
[495,"광주전남","순천","여수TP여천#1 T/L","여수T/P-여천#1 T/L 보호배전반 43PDA 교체","여수T/P-여천#1 T/L 보호배전반 43PDA 교체 - PDA 자동운전 불가(PDA 모터 이상으로 추정) - 현재 PDA 수동운전 중 - 제작사 입회 하에 PDA 교체","2023-09-23 10:00","2023-09-23 14:00","2023-09-23 10:00","2023-09-23 14:00","연속"]
[496,"광주전남","순천","여수T/P CB 6100","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S #6100 BUS-TIE GIS 보통점검(즉시가압가능)","2023-09-25 09:00","2023-09-25 18:00","2023-09-25 09:00","2023-09-25 18:00","연속"]
[497,"광주전남","순천","호남TP여수TP#1 T/L","23년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검(즉시가압 불가)","2023-09-25 09:00","2023-09-26 18:00","취소","취소","연속"]
[498,"광주전남","순천","여수T/P CB 6200","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S #6200 BUS-TIE GIS 보통점검(즉시가압가능)","2023-09-26 09:00","2023-09-26 18:00","2023-09-26 09:00","2023-09-26 18:00","연속"]
[499,"광주전남","순천","여수TP여천#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여천S/S 여수TP-여천1T/L LA 점검 및 GIS 타임측정(즉시가압가능)","2023-09-27 09:00","2023-09-27 14:00","취소","취소","연속"]
[500,"광주전남","순천","여수TP여천#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여천S/S 여수TP-여천#2T/L GIS 타임측정(즉시가압가능)","2023-09-27 14:00","2023-09-27 18:00","취소","취소","연속"]
[501,"광주전남","순천","용성여수산단#1 T/L","가공송전 위탁공사 정밀점검(용성여수산단#1 T/L)","가공송전 위탁공사 정밀점검(용성여수산단#1 T/L) : 16기","2023-09-04 09:00","2023-09-04 18:00","취소","취소","연속"]
[502,"광주전남","순천","용성여수산단#2 T/L","가공송전 위탁공사 정밀점검(용성여수산단#2 T/L)","가공송전 위탁공사 정밀점검(용성여수산단#2 T/L) : 16기","2023-09-05 09:00","2023-09-05 18:00","취소","취소","연속"]
[503,"광주전남","순천","율촌여수산단#2 T/L","가공송전 위탁공사 정밀점검(율촌여수산단#2 T/L) : 51기","가공송전 위탁공사 정밀점검(율촌여수산단#2 T/L) : 51기","2023-09-18 09:00","2023-09-21 18:00","취소","취소","매일"]
[504,"광주전남","순천","율촌여수산단#1 T/L","가공송전 위탁공사 정밀점검(율촌여수산단#1 T/L)","가공송전 위탁공사 정밀점검(율촌여수산단#1 T/L) : 51기","2023-09-11 09:00","2023-09-14 18:00","취소","취소","매일"]
[505,"광주전남","순천","순천율촌#1 T/L","가공송전 위탁공사 정밀점검(율촌CC-여수TP T/L) 11기","가공송전 위탁공사 정밀점검(율촌CC-여수TP T/L) 11기 -율촌CC분기 4회선 병가 구간 휴전(순천-율촌#1)","2023-09-14 09:00","2023-09-14 18:00","2023-09-14 09:00","2023-09-14 18:00","연속"]
[506,"광주전남","순천","순천율촌#2 T/L","가공송전 위탁공사 정밀점검(광양-율촌CC T/L) 11기","가공송전 위탁공사 정밀점검(광양-율촌CC T/L) 11기 -율촌CC분기 4회선 병가 구간 휴전(순천-율촌#2)","2023-09-19 09:00","2023-09-19 18:00","2023-09-19 09:00","2023-09-19 18:00","연속"]
[507,"광주전남","직할","남광주금천#2 T/L","금천S/S 남광주-금천#2T/L CB 유압펌프 베벨기어 수리","금천S/S 남광주-금천#2T/L CB 유압펌프 베벨기어 수리","2023-09-21 09:00","2023-09-21 18:00","취소","취소","연속"]
[508,"광주전남","직할","비아하남#2 T/L","154KV 장성-영광T/L 선종교체공사(NO.1～NO.126)","※고려시멘트T/L 횡단 구간(5~6, 9~10) 관련으로 T분기 분리 시행 ㅇ구간 : 154kV 장성-영광 #1T/L No.1~126 ㅇ경간 : 35.9km 전선교체 ㅇ시공사 : 청보전설(주) ㅇ작업내용 : 용량증대 전선교체(ASCC 430SQ로 전량교체)","2023-09-13 08:00","2023-09-15 18:00","2023-09-13 08:00","2023-09-13 09:00","연속"]
[509,"광주전남","직할","비아하남#2 T/L","2022~23년 직할 변전협력회사 총액공사","170kV GIS 차단기 조작시험, CVT 대체, LA 1차(A,B,C) 초기점검, 공기배출밸브 구조개선","2023-09-18 09:00","2023-09-18 18:00","2023-09-05 09:00","2023-09-05 18:00","연속"]
[510,"광주전남","직할","하남장성#2 T/L","22~23년 직할 가공송전 협력회사 총액공사(수평 추락방지장치 설치)","수평 추락방지장치 설치 (비아-하남 29~74호, 하남-장성T/L 2~20호 병가)","2023-09-06 08:00","2023-09-08 18:00","취소","취소","연속"]
[511,"광주전남","직할","비아하남#2 T/L","22~23년 직할 가공송전 협력회사 총액공사(수평 추락방지장치 설치)","수평 추락방지장치 설치 (비아-하남 29~74호, 하남-장성T/L 2~20호 병가)","2023-09-04 08:00","2023-09-08 18:00","취소","취소","연속"]
[512,"광주전남","강진","남창해남CS#1 T/L"," 154kV 남창S/S GIS화 공사(전문)","  170GIS 2차분 설치(170GIS 61BUS GIS 설치, 무부하가압)","2023-09-19 14:00","2023-09-20 14:00","2023-09-19 14:00","2023-09-20 14:00","연속"]
[513,"광주전남","강진","남창S/S 모선연계T/L CB"," 154kV 남창S/S GIS화 공사(전문)","  170GIS 2차분 설치(170GIS 61BUS GIS 설치, 무부하가압)","2023-09-19 14:00","2023-09-20 14:00","2023-09-19 14:00","2023-09-20 14:00","연속"]
[514,"광주전남","강진","남창해남CS#1 T/L"," 154kV 남창S/S GIS화 공사(전문)","  170GIS 2차분 설치(170GIS 66BUS GIS 설치, 무부하가압)","2023-09-21 14:00","2023-09-22 14:00","2023-09-21 14:00","2023-09-22 14:00","연속"]
[515,"광주전남","강진","남창S/S 모선연계T/L CB"," 154kV 남창S/S GIS화 공사(전문)","  170GIS 2차분 설치(170GIS 66BUS GIS 설치, 무부하가압)","2023-09-21 14:00","2023-09-22 14:00","2023-09-21 14:00","2023-09-22 14:00","연속"]
[516,"광주전남","순천","순천승주#1 T/L","승주S/S 순천-승주#1T/L GIS CB 유압시스템 교체","승주S/S 순천-승주#1T/L GIS CB 유압시스템 교체 ","2023-09-18 09:00","2023-09-19 18:00","취소","취소","연속"]
[517,"광주전남","목포","영광홍농 T/L","154kV 영광-홍농 등 4개T/L 선종교체공사","154kV 영광-홍농 등 4개T/L 선종교체공사","2023-09-25 07:00","2023-10-31 18:00","2023-09-25 07:00","2023-10-31 18:00","연속"]
[518,"대구","달성","논공달성#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 논공-달성T/L 수평 추락방지장치 설치공사(안전확보)","2023-09-04 07:00","2023-09-07 18:00","2023-09-04 07:00","2023-09-07 18:00","연속"]
[519,"대구","달성","논공달성#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 논공-달성T/L 수평 추락방지장치 설치공사(안전확보)","2023-09-08 07:00","2023-09-12 18:00","2023-09-08 07:00","2023-09-12 18:00","연속"]
[520,"대구","달성","논공현풍#2 T/L","2022~23년 달성전력지사 가공송전협력회사 총액공사","폴리머 점퍼지지애자 교체공사","2023-09-07 07:00","2023-09-07 18:00","취소","취소","연속"]
[521,"대구","달성","다사달서 T/L","2022~23년 달성전력지사 가공송전협력회사 총액공사","폴리머 점퍼지지애자 교체공사","2023-09-05 07:00","2023-09-06 18:00","2023-09-05 07:00","2023-09-06 18:00","연속"]
[522,"대구","달성","달서강창 T/L","2022~23년 달성전력지사 가공송전협력회사 총액공사","폴리머 점퍼지지애자 교체공사","2023-09-12 07:00","2023-09-13 18:00","2023-09-12 07:00","2023-09-13 18:00","연속"]
[523,"대구","달성","구지서구지#1 T/L","154kV 서구지S/S 엘앤에프 신규수용공사","170kV GIS * 2CCT 설치 무부하 가압[TEST 선로]","2023-09-01 09:00","2023-09-02 18:00","2023-08-18T09:00:00","2023-08-19T18:00:00","연속"]
[524,"대구","달성","강창성서#2 T/L","154kV 성서S/S 지역난방 신규수용공사","○ 170kV GIS 2CCT 증설(무부하가압)","2023-09-22 13:00","2023-09-23 18:00","2023-09-22 13:00","2023-09-23 18:00","연속"]
[525,"대구","달성","강창성서#2 T/L","154kV 성서S/S 지역난방 신규수용공사","○ 170kV GIS 2CCT 증설(무부하가압)","2023-09-15 13:00","2023-09-16 18:00","2023-09-15 13:00","2023-09-16 18:00","연속"]
[526,"대구","달성","성서S/S #2 BUS","154kV 성서S/S 지역난방 신규수용공사","○ 170kV GIS 2CCT 증설","2023-09-18 09:00","2023-09-23 18:00","2023-09-18 09:00","2023-09-23 18:00","연속"]
[527,"대구","달성","성서S/S #1 BUS","154kV 성서S/S 지역난방 신규수용공사","○ 170kV GIS 2CCT 증설","2023-09-13 09:00","2023-09-16 18:00","2023-09-13 09:00","2023-09-16 18:00","연속"]
[528,"대구","칠곡","농소김천#1 T/L","22-23 칠곡전력 가공송전협력 총액공사","관형지지물용 가이드레일 설치","2023-09-14 07:30","2023-09-14 11:30","2023-09-14 07:30","2023-09-14 11:30","연속"]
[529,"대구","칠곡","어모김천#1 T/L","김천S/S 154kV 637GCB COMP 불량 교체","김천S/S 154kV 637GCB COMP 불량 교체","2023-09-25 09:00","2023-09-25 18:00","2023-09-25 09:00","2023-09-25 18:00","연속"]
[530,"대구","칠곡","서대구남인동#1 T/L","22-23 칠곡전력 가공송전협력 총액공사","관형지지물용 가이드레일 설치","2023-09-17 07:30","2023-09-17 16:00","2023-09-17 07:30","2023-09-17 16:00","연속"]
[531,"대구","칠곡","서대구남구미#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 서대구-고령T/L 수평 추락방지장치 설치공사(345kV 고령-의령,154kV 서대구-남구미 T/L 병가선로)(안전확보)","2023-09-26 07:00","2023-09-26 18:00","취소","취소","연속"]
[532,"대구","칠곡","서대구남인동#2 T/L","22-23 칠곡전력 가공송전협력 총액공사","관형지지물용 가이드레일 설치","2023-09-17 07:30","2023-09-17 16:00","2023-09-17 07:30","2023-09-17 16:00","연속"]
[533,"대구","포항","건천S/S #2 BUS","'23년 상반기 포항전력지사 154kV GIS 기기점검공사","건천S/S 6B7 GIS 정밀점검","2023-09-05 13:00","2023-09-06 18:00","취소","취소","연속"]
[534,"대구","포항","건천천북#2 T/L","'23년 상반기 포항전력지사 154kV GIS 기기점검공사","건천S/S 677 GIS 정밀점검","2023-09-11 09:00","2023-09-13 18:00","2023-09-11 09:00","2023-09-13 18:00","연속"]
[535,"대구","포항","건천S/S #1 BUS","'23년 상반기 포항전력지사 154kV GIS 기기점검공사","건천S/S 6B7 GIS 정밀점검","2023-09-04 09:00","2023-09-05 13:00","취소","취소","연속"]
[536,"대구","포항","아화건천#2 T/L","'23년 상반기 포항전력지사 154kV GIS 기기점검공사","건천S/S 637 GIS 정밀점검","2023-09-18 09:00","2023-09-20 18:00","취소","취소","연속"]
[537,"대구","포항","건천천북#1 T/L","'23년 상반기 포항전력지사 154kV GIS 기기점검공사","건천S/S 6B7 GIS 정밀점검","2023-09-04 09:00","2023-09-06 18:00","취소","취소","연속"]
[538,"대구","포항","아화건천#2 T/L","'23년 상반기 포항전력지사 154kV GIS 기기점검공사","건천S/S 6133 GIS 정밀점검[TEST]","2023-09-22 12:00","2023-09-23 18:00","취소","취소","연속"]
[539,"대구","포항","건천S/S #1 BUS","'23년 상반기 포항전력지사 154kV GIS 기기점검공사","건천S/S 677 GIS 정밀점검","2023-09-11 09:00","2023-09-12 13:00","취소","취소","연속"]
[540,"대구","포항","건천S/S #2 BUS","'23년 상반기 포항전력지사 154kV GIS 기기점검공사","건천S/S 677 GIS 정밀점검","2023-09-12 13:00","2023-09-13 18:00","취소","취소","연속"]
[541,"대구","포항","아화건천#2 T/L","'23년 상반기 포항전력지사 154kV GIS 기기점검공사","건천S/S 6100 GIS 정밀점검[TEST]","2023-09-26 12:00","2023-09-27 18:00","취소","취소","연속"]
[542,"경북","구미","청리상주#1 T/L","2022-23년도 구미전력지사 가공송전정비 협력회사 총액공사","154kV 청리-상주T/L 철탑 추락방지장치 설치공사(No.1, 41~57)","2023-09-18 08:00","2023-09-20 17:00","2023-09-18 08:00","2023-09-20 17:00","연속"]
[543,"경북","구미","청리상주#2 T/L","2022-23년도 구미전력지사 가공송전정비 협력회사 총액공사","154kV 청리-상주T/L 철탑 추락방지장치 설치공사(No.1, 41~57)","2023-09-18 08:00","2023-09-20 17:00","2023-09-18 08:00","2023-09-20 17:00","연속"]
[544,"경북","구미","화동영동 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- GIS 초기점검 - #1DS부 누유관련 댐퍼 교체","2023-09-15 09:30","2023-09-15 14:00","2023-09-15 09:30","2023-09-15 14:00","연속"]
[545,"경북","구미","상주화동#1 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- #2DS부 누기개소 점검","2023-09-25 09:30","2023-09-26 18:00","2023-09-25 09:30","2023-09-26 18:00","연속"]
[546,"경북","구미","화동보은 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- GIS 초기점검","2023-09-15 14:00","2023-09-15 18:00","2023-09-15 14:00","2023-09-15 18:00","연속"]
[547,"경북","직할","안동동안동#2 T/L","동안동S/S 154kV SW 증설 및 GIS 교체공사","○ 154kV GIS 7CCT 철거, 11CCT 설치 - 1차수(8.28~9.9) : 154kV GIS 3CCT 설치","2023-09-08 09:00","2023-09-09 18:00","2023-09-08 09:00","2023-09-09 18:00","연속"]
[548,"경북","직할","안동동안동#2 T/L","동안동S/S 154kV SW 증설 및 GIS 교체공사","○ 154kV GIS 7CCT 철거, 11CCT 설치 - 1차수(8.28~9.9) : 154kV GIS 3CCT 설치","2023-09-01 09:00","2023-09-02 18:00","2023-09-01 09:00","2023-09-02 18:00","연속"]
[549,"경북","직할","영덕진보#2 T/L","22~23년 경북본부 직할 변전협력회사 총액공사","GIS 보통점검","2023-09-20 09:00","2023-09-21 14:00","2023-09-20 09:00","2023-09-21 14:00","매일"]
[550,"경북","직할","영덕진보#1 T/L","22~23년 경북본부 직할 변전협력회사 총액공사","GIS 보통점검","2023-09-18 09:00","2023-09-19 14:00","2023-09-18 09:00","2023-09-19 14:00","매일"]
[551,"경북","직할","영덕평해#1 T/L","22-23년 경북직할 송전협력회사 총액공사","154kV 영덕-평해T/L 수평 추락방지장치 설치 No.1~114","2023-09-11 08:00","2023-09-26 18:00","2023-09-11 08:00","2023-09-26 18:00","연속"]
[552,"경북","직할","청하영덕#2 T/L","22~23년 경북본부 직할 변전협력회사 총액공사","메터용 CT비 변경","2023-09-22 14:00","2023-09-22 18:00","2023-09-22 14:00","2023-09-22 18:00","연속"]
[553,"경북","직할","울진현종산풍력 T/L","울진S/S 장기사용 GIS 교체공사 4차분","울진S/S 장기사용 GIS 교체공사 4차분","2023-09-04 09:00","2023-09-26 18:00","취소","취소","연속"]
[554,"경북","직할","울진삼척GP#1 T/L","울진S/S 장기사용 GIS 교체공사 4차분","울진S/S 장기사용 GIS 교체공사 4차분_#1BUS 무부하 가압용","2023-09-19 09:00","2023-09-20 18:00","2023-09-19 09:00","2023-09-20 18:00","연속"]
[555,"경북","직할","울진삼척GP#1 T/L","울진S/S 장기사용 GIS 교체공사 4차분","울진S/S 장기사용 GIS 교체공사 4차분_#2BUS 무부하 가압용","2023-09-05 09:00","2023-09-06 18:00","2023-09-05 09:00","2023-09-06 18:00","연속"]
[556,"경북","직할","영덕진보#1 T/L","진보S/S 154kV 동안동-진보T/L 증설공사","무부하가압","2023-09-06 16:00","2023-09-08 18:00","2023-09-06 16:00","2023-09-08 18:00","연속"]
[557,"경북","직할","안동풍산 T/L","154㎸ 안동-풍산T/L 29~31호간 지장송전선로 이설공사","1. 대상선로 : 154㎸ 안동-풍산 송전선로 2. 공사구간 : No.29 ～ No.31(HSTACIR/AW 240㎟(단도체), 1회선) 3. 공사내역 : 송전선로 신설 및 철거(신설 No.30, 31, 철거 기설 No.30, 31)","2023-09-18 09:00","2023-09-23 18:00","2023-09-18 09:00","2023-09-23 18:00","연속"]
[558,"부산울산","동부산","구서노포#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-09-18 08:00","2023-09-22 18:00","2023-09-18 08:00","2023-09-22 18:00","연속"]
[559,"부산울산","동부산","노포정관#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-09-18 08:00","2023-09-22 18:00","2023-09-18 08:00","2023-09-22 18:00","연속"]
[560,"부산울산","동부산","구서노포#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-09-25 08:00","2023-09-27 18:00","2023-09-25 08:00","2023-09-27 18:00","연속"]
[561,"부산울산","동부산","노포정관#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-09-25 08:00","2023-09-27 18:00","2023-09-25 08:00","2023-09-27 18:00","연속"]
[562,"부산울산","동부산","신울산명례#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-09-11 08:00","2023-09-13 18:00","2023-09-11 08:00","2023-09-13 18:00","연속"]
[563,"부산울산","동부산","신울산명례#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-09-04 08:00","2023-09-07 18:00","2023-09-04 08:00","2023-09-07 18:00","연속"]
[564,"부산울산","동부산","서창산막#2 T/L","서창S/S 687GIS 차단기 동작시험","서창S/S 687GIS 차단기 동작시험","2023-09-24 09:30","2023-09-24 14:00","2023-09-24 09:30","2023-09-24 14:00","연속"]
[565,"부산울산","동부산","서창산막#1 T/L","서창S/S 667GIS 보통점검","서창S/S 667GIS 보통점검","2023-09-23 09:30","2023-09-23 17:00","2023-09-23 09:30","2023-09-23 17:00","연속"]
[566,"부산울산","동부산","신양산구서#1 T/L","2022~2023년 동부산 가공송전 협력회사 총액공사","-폴리머점퍼지지애자 설치 및 추락방지장치 설치","2023-09-04 07:00","2023-09-08 18:00","취소","취소","연속"]
[567,"부산울산","동부산","신양산구서#2 T/L","2022~2023년 동부산 가공송전 협력회사 총액공사","-폴리머점퍼지지애자 설치 및 추락방지장치 설치","2023-09-11 07:00","2023-09-15 18:00","취소","취소","연속"]
[568,"부산울산","북부산","대저모라#1 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","모라S/S 154kV 대저-모라#1T/L GIS 정밀점검","2023-09-25 08:00","2023-09-27 18:00","2023-09-25 08:00","2023-09-27 18:00","연속"]
[569,"부산울산","북부산","모라S/S #1 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","모라S/S 154kV 대저-모라#1T/L GIS 정밀점검 휴전설비 : #1BUS","2023-09-26 08:00","2023-09-27 18:00","2023-09-26 08:00","2023-09-27 18:00","연속"]
[570,"부산울산","북부산","모라S/S #2 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","모라S/S 154kV 대저-모라#1T/L GIS 정밀점검 휴전설비 : #2BUS","2023-09-25 08:00","2023-09-25 18:00","2023-09-25 08:00","2023-09-25 18:00","연속"]
[571,"부산울산","북부산","호포물금 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","물금S/S 154kV 호포-물금T/L GIS 정밀점검","2023-09-18 08:00","2023-09-20 18:00","2023-09-18 08:00","2023-09-20 18:00","연속"]
[572,"부산울산","북부산","북부산미남#1 T/L","북부산전력지사 154kV 효성제 전동스프링 메커니즘 보강공사","북부산S/S 170kV 북부산-미남#1T/L GIS 메커니즘 보강공사","2023-09-25 09:00","2023-09-25 18:00","2023-09-25 09:00","2023-09-25 18:00","연속"]
[573,"부산울산","북부산","북부산S/S SEC CB 60610","북부산전력지사 154kV 효성제 전동스프링 메커니즘 보강공사","북부산S/S 170kV #60-61 B/S GIS 메커니즘 보강공사","2023-09-18 09:00","2023-09-18 18:00","2023-09-18 09:00","2023-09-18 18:00","연속"]
[574,"부산울산","북부산","북부산양산 T/L","북부산전력지사 154kV 효성제 전동스프링 메커니즘 보강공사","북부산S/S 170kV 북부산-양산T/L GIS 메커니즘 보강공사","2023-09-19 09:00","2023-09-19 18:00","2023-09-26 09:00","2023-09-26 18:00","연속"]
[575,"부산울산","북부산","북부산S/S CB 6200","북부산전력지사 154kV 효성제 전동스프링 메커니즘 보강공사","북부산S/S 170kV #6200 B/T GIS 메커니즘 보강공사","2023-09-20 09:00","2023-09-20 18:00","2023-09-20 09:00","2023-09-20 18:00","연속"]
[576,"부산울산","북부산","북부산삼랑진PP T/L","북부산전력지사 154kV 효성제 전동스프링 메커니즘 보강공사","북부산S/S 170kV 북부산-삼랑진T/L GIS 메커니즘 보강공사","2023-09-27 09:00","2023-09-27 18:00","2023-09-27 09:00","2023-09-27 18:00","연속"]
[577,"부산울산","북부산","북부산미남#2 T/L","북부산전력지사 154kV 효성제 전동스프링 메커니즘 보강공사","북부산S/S 170kV 북부산-미남#2T/L GIS 메커니즘 보강공사","2023-09-26 09:00","2023-09-26 18:00","2023-09-19 09:00","2023-09-19 18:00","연속"]
[578,"부산울산","북부산","북부산호포 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치(안전확보)","154kV 북부산-물금T/L 수평 추락방지장치 설치(4회선 15기) 다회선 철탑 작업 안전확보","2023-09-23 08:30","2023-09-24 18:00","취소","취소","연속"]
[579,"부산울산","북부산","북부산S/S SEC CB 66670","북부산전력지사 154kV 효성제 전동스프링 메커니즘 보강공사","북부산S/S 170kV #66-67 B/S GIS 메커니즘 보강공사","2023-09-22 09:00","2023-09-22 18:00","2023-09-22 09:00","2023-09-22 18:00","연속"]
[580,"부산울산","북부산","북부산물금 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치","154kV 북부산-물금T/L 수평 추락방지장치 설치(2회선 12기, 4회선 15기)","2023-09-21 08:30","2023-09-25 18:00","2023-09-21 08:30","2023-09-24 18:00","연속"]
[581,"부산울산","북부산","양산산막#1 T/L","양산S/S 154kV GIS 누기조치","양산S/S 154kV 양산-산막#1T/L 누기조치","2023-09-12 09:00","2023-09-13 18:00","취소","취소","연속"]
[582,"부산울산","북부산","호포매리#1 T/L","154kV 호포-매리T/L OPGW 증설공사","호포-매리T/L No.1~No.16호간 OPGW 교체","2023-09-12 09:00","2023-09-17 18:00","취소","취소","매일"]
[583,"부산울산","서부산","서부산다대#1 T/L","서부산S/S 345kV 차단기 용량부족 대체공사","서부산S/S 345kV 차단기 용량부족 대체공사 관련 집중감시제어반 DB 수용","2023-09-18 09:00","2023-09-22 18:00","2023-09-18 09:00","2023-09-22 18:00","연속"]
[584,"부산울산","서부산","서부산엄궁#1 T/L","서부산S/S 345kV 차단기 용량부족 대체공사","서부산S/S 345kV 차단기 용량부족 대체공사 관련 집중감시제어반 DB 수용","2023-09-18 09:00","2023-09-22 18:00","2023-09-18 09:00","2023-09-22 18:00","연속"]
[585,"부산울산","서부산","신녹산S/S #1 Sh.C CB","신녹산S/S 154kV #1 Sh.C GCB 설치공사","신녹산S/S 154kV #1 Sh.C GCB 설치공사","2023-09-04 09:00","2023-12-29 18:00","2023-09-04 09:00","2023-12-29 18:00","연속"]
[586,"부산울산","울산","남울산신온산#1 T/L","345kv 동울산-월성NP등 6개T/L 추락방지장치 등 설치공사","철탑 추락방지장치","2023-09-05 07:00","2023-09-08 18:00","2023-09-05 07:00","2023-09-08 18:00","연속"]
[587,"부산울산","울산","남울산처용#2 T/L","154kV 추락방지장치 설치공사(수평)","ㅇ 남울산-처용#2 추락방지장치 설치(수평) - 1~18 (10기)","2023-09-18 07:30","2023-09-21 18:00","2023-09-18 07:30","2023-09-21 18:00","연속"]
[588,"부산울산","울산","남울산신온산#2 T/L","345kv 동울산-월성NP등 6개T/L 추락방지장치 등 설치공사","철탑 추락방지장치 및 폴리머점퍼지지애자 설치","2023-09-19 07:00","2023-09-25 18:00","2023-09-19 07:00","2023-09-25 18:00","연속"]
[589,"부산울산","울산","남울산처용#1 T/L","154kV 추락방지장치 설치공사(수평)","ㅇ 남울산-처용#1 추락방지장치 설치(수평) - 1호 (1기)","2023-09-22 07:30","2023-09-22 18:00","2023-09-22 07:30","2023-09-22 18:00","연속"]
[590,"부산울산","울산","산하방어진#1 T/L","22~23년 변전협력회사 총액공사","- 방어진측 SA 시스템화, 피뢰기 보통점검, GIS 보통점검 - 산하측 GIS 하자점검","2023-09-18 09:00","2023-09-20 18:00","2023-09-18 09:00","2023-09-20 18:00","연속"]
[591,"부산울산","울산","효문방어진 T/L","22~23년 변전협력회사 총액공사","- 방어진측 SA 시스템화, 피뢰기 보통점검, GIS 보통점검 - 효문측 차단기 동작시험","2023-09-25 09:00","2023-09-27 18:00","2023-09-25 09:00","2023-09-27 18:00","연속"]
[592,"부산울산","울산","성암울산TP#1 T/L","154kV 추락방지장치 설치공사(수평)","ㅇ성암-울산TP#1 추락방지장치 설치(수평) - 1~9호 5기","2023-09-14 07:30","2023-09-15 18:00","2023-09-14 07:30","2023-09-15 18:00","연속"]
[593,"부산울산","울산","신울산매암#2 T/L","23년 울산전력지사 개폐장치 보통점검공사","- 신울산측 GIS 보통점검, 피뢰기 보통점검 - 매암측 GIS 보통점검","2023-09-29 09:00","2023-09-29 18:00","2023-09-29 09:00","2023-09-29 18:00","연속"]
[594,"부산울산","울산","신울산S/S SEC CB 62630","23년 울산전력지사 개폐장치 보통점검공사","- GIS 보통점검","2023-09-27 09:00","2023-09-27 18:00","2023-09-27 09:00","2023-09-27 18:00","연속"]
[595,"부산울산","울산","신울산S/S SEC CB 66670","22~23년 변전협력회사 총액공사","- GIS 보통점검","2023-09-22 09:00","2023-09-22 18:00","2023-09-22 09:00","2023-09-22 18:00","연속"]
[596,"부산울산","울산","신울산S/S SEC CB 61620","22~23년 변전협력회사 총액공사","- GIS 보통점검","2023-09-21 09:00","2023-09-21 18:00","2023-09-21 09:00","2023-09-21 18:00","연속"]
[597,"부산울산","울산","신울산S/S CB 6400","23년 울산전력지사 개폐장치 보통점검공사","- GIS 보통점검","2023-09-20 09:00","2023-09-20 18:00","2023-09-20 09:00","2023-09-20 18:00","연속"]
[598,"부산울산","울산","용연울산TP#1 T/L","울산화력S/Y 장기사용 GIS 교체공사(5차)","○ 울산화력S/Y #66BUS 시험가압(24Hr)","2023-09-13 18:00","2023-09-14 18:00","2023-09-21T17:00:00","2023-09-21T18:00:00","연속"]
[599,"부산울산","울산","용연울산TP#2 T/L","울산화력S/Y 장기사용 GIS 교체공사(5차)","○ 154kV 용연-울산T/P#2T/L GIS 교체","2023-09-06 18:00","2023-09-06 18:00","2023-09-18T09:00:00","2023-11-10T18:00:00","연속"]
[600,"부산울산","울산","용연울산TP#2 T/L","울산화력S/Y 장기사용 GIS 교체공사(5차)","○ 울산화력S/Y #66BUS 시험가압(24Hr)","2023-09-20 18:00","2023-09-22 18:00","취소","취소","연속"]
[601,"부산울산","울산","두왕울산#2 T/L","23년 울산전력지사 170kV GIS 대체공사","- 효성폴리, 태광T/L GIS 대체공사 시험가압선로","2023-09-21 18:00","2023-09-22 18:00","2023-09-21 18:00","2023-09-22 18:00","연속"]
[602,"부산울산","울산","울산매암 T/L","23년 울산전력지사 170kV GIS 대체공사","- 효성폴리, 태광T/L GIS 대체공사 - 울산-매암T/L 작업안전확보","2023-09-04 09:00","2023-09-06 14:00","2023-09-04 09:00","2023-09-06 14:00","연속"]
[603,"부산울산","울산","두왕울산#1 T/L","23년 울산전력지사 170kV GIS 대체공사","- 효성폴리, 태광T/L GIS 대체공사 - 작업안전확보 및 시험가압선로","2023-09-06 14:00","2023-09-10 18:00","2023-09-06 14:00","2023-09-10 18:00","연속"]
[604,"부산울산","울산","울산매암 T/L","23년 울산전력지사 170kV GIS 대체공사","- 효성폴리, 태광T/L GIS 대체공사 - 작업안전확보","2023-09-11 09:00","2023-09-13 14:00","2023-09-11 09:00","2023-09-13 14:00","연속"]
[605,"부산울산","울산","두왕울산#1 T/L","23년 울산전력지사 170kV GIS 대체공사","- 효성폴리, 태광T/L GIS 대체공사 - 작업안전확보 및 시험가압선로","2023-09-13 14:00","2023-09-16 18:00","2023-09-13 14:00","2023-09-16 18:00","연속"]
[606,"부산울산","울산","울산T/P #61 BUS","울산화력S/Y 장기사용 GIS 교체공사(5차)","○ 울산화력S/Y #61BUS 상체크","2023-09-22 17:00","2023-09-22 18:00","취소","취소","연속"]
[607,"부산울산","울산","울산T/P #66 BUS","울산화력S/Y 장기사용 GIS 교체공사(5차)","○ 154kV 6200 BUS-TIE GIS 교체 → #66BUS 철거 및 신규 GIS 설치, 준공시험, 시험가압 및 실부하가압","2023-09-14 09:00","2023-09-22 18:00","취소","취소","연속"]
[608,"부산울산","울산","울산T/P #61 BUS","울산화력S/Y 장기사용 GIS 교체공사(5차)","○ 154kV 6200 BUS-TIE GIS 교체 → #61BUS, #1DS, CB 철거 및 신규 GIS 설치","2023-09-07 09:00","2023-09-13 18:00","취소","취소","연속"]
[609,"부산울산","울산","울산T/P #66 BUS","울산화력S/Y 장기사용 GIS 교체공사(5차)","○ 154kV 6200 BUS-TIE, #61-66BUS PT, 용연-울산TP#2T/L GIS 교체 → #2DS 철거 및 고깔처리","2023-09-04 09:00","2023-09-06 18:00","2023-09-18T09:00:00","2023-09-21T18:00:00","연속"]
[610,"부산울산","울산","울주외동#1 T/L","22~23년 변전협력회사 총액공사","- 6C2DS 스페이서부 가스누기 보수","2023-09-25 09:00","2023-09-27 18:00","2023-09-25 09:00","2023-09-27 18:00","연속"]
[611,"부산울산","울산","울주외동#2 T/L","22~23년 변전협력회사 총액공사","- 6B1, 6B2DS 스페이서부 가스누기 보수 안전이격","2023-09-18 09:00","2023-09-22 18:00","2023-09-18 09:00","2023-09-22 18:00","연속"]
[612,"부산울산","울산","웅촌서창#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-09-04 08:00","2023-09-06 18:00","2023-09-04 08:00","2023-09-06 18:00","연속"]
[613,"부산울산","울산","웅촌서창#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-09-07 08:00","2023-09-08 18:00","2023-09-07 08:00","2023-09-08 18:00","연속"]
[614,"부산울산","울산","신울산웅촌#2 T/L","345kv 동울산-월성NP등 6개T/L 추락방지장치 등 설치공사","철탑 추락방지장치","2023-09-14 07:00","2023-09-15 18:00","2023-09-14 07:00","2023-09-15 18:00","연속"]
[615,"부산울산","울산","신울산웅촌#1 T/L","154kV 추락방지장치 설치공사(수평)","ㅇ신울산-웅촌#1 추락방지장치 설치(수평) - 2~34호 26기","2023-09-04 07:30","2023-09-13 18:00","2023-09-04 07:30","2023-09-13 18:00","연속"]
[616,"부산울산","울산","온산처용#2 T/L","154kV 추락방지장치 설치공사(수평)","ㅇ 온산-처용#2 추락방지장치 설치(수평) - 11~20호 (10기)","2023-09-25 07:30","2023-09-27 18:00","2023-09-25 07:30","2023-09-27 18:00","연속"]
[617,"부산울산","직할","우동대연 T/L","대연S/S 6100 BUS TIE CB 대체 공사","대연S/S 6100 BUS TIE CB 대체 및 운휴 설비 철거공사","2023-09-19 08:30","2023-09-19 09:00","2023-09-19 07:30","2023-09-19 08:00","연속"]
[618,"부산울산","직할","정보대연 T/L","23년 직할 170kV GIS 정밀점검공사","정보-대연T/L GIS 정밀점검공사","2023-09-19 08:00","2023-09-19 08:30","2023-09-19 07:00","2023-09-19 07:30","연속"]
[619,"부산울산","직할","우동대연 T/L","23년 직할 170kV GIS 정밀점검공사","우동-대연T/L GIS 정밀점검공사","2023-09-16 09:00","2023-09-16 10:00","2023-09-16 09:00","2023-09-16 10:00","연속"]
[620,"경남","직할","신김해진례#2 T/L","154kV 신김해-진례#2T/L 송전선로 정밀점검","○ 154kV 신김해-진례#2T/L 송전선로 정밀점검 - 2~3호,15~23호,26~28호(14기) ○ 154kV 신김해-진례#2T/L 아킹혼 철거 - 4~9호, 24~25호(8개소)","2023-09-22 08:30","2023-09-24 18:00","2023-09-22 08:30","2023-09-24 18:00","매일"]
[621,"경남","직할","신김해지사#1 T/L","154kV 신김해-장유#1T/L 송전선로 정밀점검","154kV 신김해-장유#1T/L 송전선로 정밀점검 안전확보(2-8)","2023-09-18 08:00","2023-09-18 18:00","2023-09-18 08:00","2023-09-18 18:00","연속"]
[622,"경남","직할","신김해지사#2 T/L","154kV 신김해-장유#2T/L 송전선로 정밀점검","154kV 신김해-장유#2T/L 송전선로 정밀점검 안전확보(2-8)","2023-09-20 08:00","2023-09-20 18:00","2023-09-20 08:00","2023-09-20 18:00","연속"]
[623,"경남","직할","장유마천#2 T/L","154kV 신김해-장유#2T/L 송전선로 정밀점검","154kV 신김해-장유#2T/L 송전선로 정밀점검 안전확보(9-13)","2023-09-19 10:00","2023-09-20 18:00","2023-09-19 10:00","2023-09-20 18:00","매일"]
[624,"경남","직할","장유마천#1 T/L","154kV 신김해-장유#1T/L 송전선로 정밀점검","154kV 신김해-장유#1T/L 송전선로 정밀점검 안전확보(9-13)","2023-09-19 08:00","2023-09-20 11:00","2023-09-19 08:00","2023-09-20 11:00","매일"]
[625,"경남","직할","주촌삼계#1 T/L","154kV 주촌-삼계T/L 수평 추락방지장치 설치공사","154kV 주촌-삼계T/L 수평 추락방지장치 설치공사","2023-09-19 07:00","2023-09-22 18:00","2023-09-19 07:00","2023-09-22 18:00","매일"]
[626,"경남","직할","신김해주촌#2 T/L","154kV 신김해-주촌T/L 수평 추락방지장치 설치공사","154kV 신김해-주촌T/L 수평 추락방지장치 설치공사","2023-09-18 07:00","2023-09-21 18:00","2023-09-18 07:00","2023-09-21 18:00","매일"]
[627,"경남","진주","진주개양#1 T/L","154kV 사봉-개양T/L 가공송전선로 정밀점검[#1병가]","154kV 사봉-개양T/L 가공송전선로 정밀점검 #2T/L 52~55호 4회선 철탑 병가구간","2023-09-23 08:30","2023-09-24 18:00","2023-09-23 08:30","2023-09-24 18:00","매일"]
[628,"경남","진주","진주개양#2 T/L","154kV 사봉-개양T/L 가공송전선로 정밀점검[#1병가]","154kV 사봉-개양T/L 가공송전선로 정밀점검 #1T/L 52~55호 4회선 철탑 병가구간","2023-09-09 08:30","2023-09-10 18:00","취소","취소","매일"]
[629,"경남","진주","의령동진주#2 T/L","154kV 의령-동진주T/L 피뢰기 열화진단","154kV 의령-동진주#2T/L 피뢰기 열화진단","2023-09-26 08:00","2023-09-26 18:00","취소","취소","연속"]
[630,"경남","진주","의령동진주#1 T/L","154kV 의령-동진주T/L 피뢰기 열화진단","154kV 의령-동진주#1T/L 피뢰기 열화진단","2023-09-25 08:00","2023-09-25 18:00","취소","취소","연속"]
[631,"경남","진주","사봉개양#1 T/L","154kV 사봉-개양T/L 가공송전선로 정밀점검","154kV 사봉-개양T/L 가공송전선로 정밀점검","2023-09-02 08:30","2023-09-03 18:00","2023-09-02 08:30","2023-09-03 18:00","매일"]
[632,"경남","진주","가야사봉#2 T/L","154kV 사봉-개양T/L 가공송전선로 정밀점검[#1병가]","154kV 사봉-개양T/L 가공송전선로 정밀점검 #1T/L 2~7호 4회선 철탑 병가구간","2023-09-02 08:30","2023-09-03 18:00","2023-09-02 08:30","2023-09-03 18:00","매일"]
[633,"경남","진주","사봉개양#1 T/L","154kV 사봉-개양T/L 가공송전선로 정밀점검","154kV 사봉-개양T/L 가공송전선로 정밀점검","2023-09-09 08:30","2023-09-10 18:00","2023-09-09 08:30","2023-09-10 18:00","매일"]
[634,"경남","진주","가야사봉#1 T/L","154kV 사봉-개양T/L 가공송전선로 정밀점검[#1병가]","154kV 사봉-개양T/L 가공송전선로 정밀점검 #12/L 2~7호 4회선 철탑 병가구간","2023-09-16 08:30","2023-09-17 18:00","2023-09-16 08:30","2023-09-17 18:00","매일"]
[635,"경남","진주","사봉개양#2 T/L","154kV 사봉-개양T/L 가공송전선로 정밀점검","154kV 사봉-개양T/L 가공송전선로 정밀점검","2023-09-16 08:30","2023-09-17 18:00","2023-09-16 08:30","2023-09-17 18:00","매일"]
[636,"경남","진주","사봉개양#2 T/L","154kV 사봉-개양T/L 가공송전선로 정밀점검","154kV 사봉-개양T/L 가공송전선로 정밀점검","2023-09-23 08:30","2023-09-24 18:00","2023-09-23 08:30","2023-09-24 18:00","매일"]
[637,"경남","진주","사천개양#1 T/L","사천S/S 154kV 사천-개양#1T/L GIS 조작, LA 초기점검","사천S/S 154kV 사천-개양#1T/L GIS 조작, LA 초기점검","2023-09-26 10:00","2023-09-26 18:00","2023-09-26 10:00","2023-09-26 18:00","연속"]
[638,"경남","진주","사천개양#2 T/L","사천S/S 154kV 사천-개양#2T/L GIS 조작, LA 초기점검","[주]사천S/S 154kV 사천-개양#2T/L GIS 조작, LA 초기점검 [병행] 개양S/S GIS 보통점검","2023-09-27 10:00","2023-09-27 18:00","2023-09-27 10:00","2023-09-27 18:00","연속"]
[639,"경남","진주","산청함양 T/L","154kV 의령-함양T/L 가공송전선로 정밀점검","154kV 의령-함양T/L 가공송전선로 정밀점검","2023-09-25 08:30","2023-09-27 18:00","취소","취소","매일"]
[640,"경남","진주","의령산청 T/L","154kV 의령-산청T/L 가공송전선로 정밀점검","154kV 의령-산청T/L 가공송전선로 정밀점검","2023-09-11 08:30","2023-09-15 18:00","취소","취소","매일"]
[641,"경남","진주","의령동진주#2 T/L","154kV 의령-동진주 #1, 2 T/L 철탑 추락방지장치 설치","154kV 의령-동진주 #2 T/L 철탑 수평 추락방지장치 설치공사 (매일) - 철탑 수평 추락방지장치 설치 : No.1~73(73기) - 평일작업 - 병가구간 : 의령-산청 T/L No.1~7 (9.23 안전작업거리확보 휴전 예정)","2023-09-23 07:30","2023-09-27 18:00","2023-09-23 07:30","2023-09-27 18:00","매일"]
[642,"경남","진주","의령산청 T/L","[안전작업거리확보 휴전] 154kV 철탑 추락방지시설 설치공사","154kV 의령-동진주 #2T/L 병가구간 안전작업거리 확보 휴전 1. 휴전설비 : 의령-동진주 #2 T/L, 의령-산청 T/L 2. 설치대상 - 154kV 의령-동진주 T/L No.1~73호(67~73호 병가구간) - No.67~73 작업시 의령-산청 T/(1~7호 병가구간) 안전작업거리확보 휴전 필요","2023-09-22 07:30","2023-09-22 18:00","2023-09-22 07:30","2023-09-22 18:00","연속"]
[643,"경남","진주","의령함양 T/L","154kV 의령-함양T/L 가공송전선로 정밀점검","154kV 의령-함양T/L 가공송전선로 정밀점검","2023-09-04 08:30","2023-09-08 18:00","취소","취소","매일"]
[644,"경남","진주","의령S/S #1 EM.Tr CB","의령S/S ESS 정기점검 및 1차 GIS E6133 보통점검","의령S/S ESS 정기점검 및 1차 GIS E6133 보통점검","2023-09-18 10:00","2023-09-22 18:00","2023-09-18 10:00","2023-09-22 18:00","연속"]
[645,"경남","진주","의령함양 T/L","[안전작업거리확보 휴전] 154kV 철탑 추락방지시설 설치공사","154kV 의령-동진주 #1T/L 병가구간 안전작업거리 확보 휴전 1. 휴전설비 : 의령-동진주 #1 T/L, 의령-함양 T/L 2. 설치대상 - 154kV 의령-동진주 T/L No.1~73호(67~73호 병가구간) - No.67~73 작업시 의령-함양 T/L(1~7호 병가구간) 안전작업거리확보 휴전 필요","2023-09-18 07:30","2023-09-18 18:00","2023-09-18 07:30","2023-09-18 18:00","연속"]
[646,"경남","진주","의령동진주#1 T/L","154kV 의령-동진주 #1, 2 T/L 철탑 추락방지장치 설치","154kV 의령-동진주 #1 T/L 철탑 수평 추락방지장치 설치공사 (매일) - 철탑 수평 추락방지장치 설치 : No.1~73(73기) - 평일작업 - 병가구간 : 의령-함양 T/L No.1~7 (9.18 안전작업거리확보 휴전 예정)","2023-09-17 07:30","2023-09-22 18:00","2023-09-17 07:30","2023-09-22 18:00","매일"]
[647,"경남","통영","삼천포사천#1 T/L","삼천포(SA)S/S 154kV 삼천포-사천#1T/L GIS 하자점검 등","1. 삼천포(SA)S/S 154kV 삼천포-사천#1T/L GIS 메커니즘 부품교체(효성) 2. 삼천포(SA)S/S 154kV 삼천포-사천#1T/L GIS 하자점검","2023-09-18 10:00","2023-09-19 18:00","2023-09-18 10:00","2023-09-19 18:00","매일"]
[648,"경남","통영","삼천포사천#2 T/L","삼천포(SA)S/S 154kV 삼천포-사천#2T/L GIS 하자점검 등","1. 삼천포(SA)S/S 154kV 삼천포-사천#2T/L GIS 메커니즘 부품교체(효성) 2. 삼천포(SA)S/S 154kV 삼천포-사천#2T/L GIS 하자점검","2023-09-20 10:00","2023-09-21 18:00","2023-09-20 10:00","2023-09-21 18:00","매일"]
[649,"경남","통영","신고성고성 T/L","신고성S/S 154kV신고성-고성T/L GIS, LA, CVT 보통점검","신고성S/S 154kV신고성-고성T/L GIS 보통점검 신고성S/S 154kV신고성-고성T/L LA, CVT 보통점검","2023-09-23 09:30","2023-09-23 18:00","2023-09-23 09:30","2023-09-23 18:00","연속"]
[650,"경남","통영","신고성거제#2 T/L","154kV 진동-안정#2T/L 추락방지장치 설치공사 안전작업거리 확보","154kV 진동-안정#2T/L 추락방지장치 설치공사 안전작업거리 확보","2023-09-24 09:00","2023-09-24 18:00","2023-09-24 09:00","2023-09-24 18:00","연속"]
[651,"경남","통영","진동안정#2 T/L","154kV 통영복합S/Y 건설공사(안전확보)","154kV 통영복합S/Y 건설 - 154kV GIS 13CCT 설치 - 보호배전반이설 및 신설 - 기타부대공사 154kV 고성-안정2T/L 선로분기 작업","2023-09-23 09:00","2023-09-26 18:00","2023-09-23 09:00","2023-09-26 18:00","연속"]
[652,"경남","통영","진동안정#1 T/L","154kV 통영복합S/Y 건설공사(안전확보)","154kV 통영복합S/Y 건설 - 154kV GIS 13CCT 설치 - 보호배전반이설 및 신설 - 기타부대공사 154kV 고성-안정2T/L 선로분기 작업","2023-09-16 09:00","2023-09-19 18:00","2023-09-16 09:00","2023-09-19 18:00","연속"]
[653,"경남","통영","고성안정#1 T/L","154kV 통영복합S/Y 건설공사","154kV 통영복합S/Y 건설 - 154kV GIS 13CCT 설치 - 보호배전반이설 및 신설 - 기타부대공사 154kV 고성-안정2T/L 선로분기 작업","2023-09-23 09:00","2023-09-26 18:00","2023-09-23 09:00","2023-09-26 18:00","연속"]
[654,"경남","통영","고성안정#2 T/L","154kV 통영복합S/Y 건설공사","154kV 통영복합S/Y 건설 - 154kV GIS 13CCT 설치 - 보호배전반이설 및 신설 - 기타부대공사 154kV 고성-안정2T/L 선로분기 작업","2023-09-16 09:00","2023-09-22 18:00","2023-09-16 09:00","2023-09-22 18:00","연속"]
[655,"경남","통영","고성통영 T/L","통영S/S 고성-통영T/L DC 접지개소 확인","통영S/S 고성-통영T/L DC 접지개소 확인","2023-09-09 09:00","2023-09-09 14:00","2023-09-09 09:00","2023-09-09 14:00","연속"]
[656,"경남","통영","신고성통영 T/L","통영S/S 신고성-통영T/L DC 접지개소 확인","통영S/S 신고성-통영T/L DC 접지개소 확인","2023-09-09 14:00","2023-09-09 18:00","2023-09-09 14:00","2023-09-09 18:00","연속"]
[657,"경남","함안","신월동읍#1 T/L","동읍S/S 신월-동읍#1 T/L GIS 보통점검","동읍S/S 신월-동읍#1 T/L GIS 보통점검","2023-09-18 09:30","2023-09-18 17:30","2023-09-18 09:30","2023-09-18 17:30","연속"]
[658,"경남","함안","신월동읍#2 T/L","동읍S/S 신월-동읍#2 T/L GIS 보통점검","동읍S/S 신월-동읍#2 T/L GIS 보통점검","2023-09-25 09:30","2023-09-25 17:30","2023-09-25 09:30","2023-09-25 17:30","연속"]
[659,"경남","함안","매리김해#2 T/L","154kV 매리-김해T/L 수평 추락방지장치 설치공사","154kV 매리-김해T/L 수평 추락방지장치 설치공사","2023-09-23 07:00","2023-09-24 18:00","취소","취소","연속"]
[660,"경남","함안","매리김해#1 T/L","154kV 매리-김해T/L 수평 추락방지장치 설치공사","154kV 매리-김해T/L 수평 추락방지장치 설치공사","2023-09-16 07:00","2023-09-17 18:00","취소","취소","매일"]
[661,"경남","함안","호포매리#2 T/L","154kV 호포-매리T/L 수평 추락방지장치 설치공사","154kV 호포-매리T/L 수평 추락방지장치 설치공사","2023-09-23 07:00","2023-09-24 18:00","취소","취소","연속"]
[662,"경남","함안","호포매리#1 T/L","154kV 호포-매리T/L 수평 추락방지장치 설치공사","154kV 호포-매리T/L 수평 추락방지장치 설치공사","2023-09-16 07:00","2023-09-17 18:00","취소","취소","매일"]
[663,"경남","함안","신마산칠서#1 T/L","154kV 신마산-칠서#1T/L 선하지 태양광발전 설치","태양광발전 설치 공사 관련 안전확보 휴전 ○ 대상 : 154kV 신마산-칠서#1T/L 19~20호 ○ 신청사유 : 선하지 인근(최단 3.2m) 태양광 설치 작업 관련 안전 확보 ○ 조치계획 : #1T/L 휴전 및 접지 시행 등","2023-09-18 08:00","2023-09-20 18:00","2023-09-18 08:00","2023-09-20 18:00","매일"]
[664,"경남","함안","김해어방#1 T/L","어방S/S 김해-어방#1 T/L GIS 보통점검","어방S/S 김해-어방#1 T/L GIS 보통점검","2023-09-21 09:30","2023-09-21 17:30","2023-09-21 09:30","2023-09-21 17:30","연속"]
[665,"경남","함안","신마산중리#2 T/L","중리S/S 신마산-중리#2 T/L GIS 보통점검","중리S/S 신마산-중리#2 T/L GIS 보통점검","2023-09-26 09:30","2023-09-26 17:30","2023-09-26 09:30","2023-09-26 17:30","연속"]
[666,"경남","함안","신마산중리#1 T/L","중리S/S 신마산-중리#1 T/L GIS 보통점검","중리S/S 신마산-중리#1 T/L GIS 보통점검","2023-09-22 09:30","2023-09-22 17:30","2023-09-22 09:30","2023-09-22 17:30","연속"]
[667,"경남","함안","진례진영#2 T/L","154kV 진례-진영#2T/L 송전선로 정밀점검","○ 154kV 진례-진영#2T/L 송전선로 정밀점검 - 1~4호호(4기) ○ 154kV 진례-진영#2T/L 아킹혼 철거 - 5~6호(2개소)","2023-09-16 08:30","2023-09-16 18:00","2023-09-16 08:30","2023-09-16 18:00","연속"]
[668,"경남","함안","창녕초동#1 T/L","창녕S/S 154kV 옥외철구 설비 GIS화 공사(임시모선 시험가압)","창녕S/S 154kV 옥외철구 설비 GIS화 공사(임시모선 연결, 시험가압)","2023-09-06 18:00","2023-09-07 18:00","2023-09-06 18:00","2023-09-07 18:00","연속"]
[669,"경남","함안","칠서창녕#1 T/L","창녕S/S 154kV 옥외철구 GIS화 공사(송전선로 인출변경)","창녕S/S 154kV 옥외철구 GIS화 공사(송전선로 인출변경)","2023-09-23 08:30","2023-09-27 18:00","취소","취소","연속"]
[670,"경남","함안","창녕초동#2 T/L","창녕S/S 154kV 옥외철구 설비 GIS화 공사(임시모선 시험가압)","창녕S/S 154kV 옥외철구 설비 GIS화 공사(임시모선 연결, 시험가압)","2023-09-04 18:00","2023-09-05 18:00","2023-09-04 18:00","2023-09-05 18:00","연속"]
[671,"경남","함안","창녕초동#1 T/L","창녕S/S 154kV 옥외철구 설비 GIS화 공사(변압기 인출변경)","창녕S/S 154kV 옥외철구 설비 GIS화 공사(변압기 인출변경, 시험가압)","2023-09-10 17:00","2023-09-11 17:00","2023-09-10 17:00","2023-09-11 17:00","연속"]
[672,"경남","함안","창녕초동#2 T/L","창녕S/S 154kV 옥외철구 설비 GIS화 공사(변압기 인출변경)","창녕S/S 154kV 옥외철구 설비 GIS화 공사(변압기 인출변경,시험가압)","2023-09-14 17:00","2023-09-15 17:00","2023-09-14 17:00","2023-09-15 17:00","연속"]
[673,"경남","함안","칠서창녕#2 T/L","창녕S/S 154kV 옥외철구 GIS화 공사(송전선로 인출변경)","창녕S/S 154kV 옥외철구 GIS화 공사(송전선로 인출변경)","2023-09-23 08:30","2023-09-27 18:00","취소","취소","연속"]
[674,"경남","함안","신마산칠서#2 T/L","칠서S/S 신마산-칠서SA#2 T/L GIS 발청보수","칠서S/S 신마산-칠서SA#2 T/L GIS 발청보수","2023-09-22 13:30","2023-09-22 17:30","2023-09-22 13:30","2023-09-22 17:30","연속"]
[675,"경남","함안","신마산칠서#1 T/L","칠서S/S 신마산-칠서SA#1 T/L GIS 발청보수","칠서S/S 신마산-칠서SA#1 T/L GIS 발청보수","2023-09-22 09:30","2023-09-22 13:30","2023-09-22 09:30","2023-09-22 13:30","연속"]
[676,"경기","평택","평택추팔#1 T/L","154kV 오산-평택T/L 등 13개T/L 추락방지장치(수평) 설치공사","추락방지장치(수평) 19기 설치","2023-09-18 09:00","2023-09-21 18:00","2023-09-23 09:00","2023-09-23 18:00","연속"]