{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":4,"n_cols":11,"rows_kept":4,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2023년도 12월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]

{"sheet":"345설비","index":1,"n_rows":197,"n_cols":11,"rows_kept":197,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2023년도 12월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #2 M.Tr","2023년 성동P/O 변전협력회사 총액공사","- M.Tr, 3차 LA, 3차 PT 보통점검 - 170kV GIS 조작시험 - 변압기실 공조 FAN 교체 - M.Tr PNL 교체","2023-12-04 09:00","2023-12-12 18:00","취소","취소","연속"]
[2,"서울","성동","미금성동#2 T/L","2023년 성동P/O 변전협력회사 총액공사","-B/F PNL 교체 -PT함 이설","2023-12-04 09:00","2023-12-06 18:00","취소","취소","연속"]
[3,"남서울","강남","신양재S/S #3 Sh.R CB","22-23년도 강남전력지사 변전협력회사 총액공사","#3Sh.R 보통점검","2023-12-11 08:00","2023-12-11 18:00","2023-12-11 08:00","2023-12-11 18:00","연속"]
[4,"남서울","동서울","동서울미금#1 T/L","345kV 동서울#2S/S 건설공사","345kV GIS 6CB 증설모선 시험가압 선로","2023-12-21 09:00","2023-12-22 18:00","취소","취소","연속"]
[5,"남서울","동서울","동서울S/S #1 Sh.R CB","동서울S/S #1Sh.R 개폐제어기 설치공사","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-12-18 09:00","2023-12-22 18:00","2023-12-18 09:00","2023-12-22 18:00","연속"]
[6,"남서울","동서울","동서울S/S #75 BUS","345kV 동서울#2S/S 건설공사","345kV GIS 6CB 증설","2023-12-18 09:00","2023-12-22 18:00","2023-12-11 09:00","2023-12-15 18:00","연속"]
[7,"남서울","동서울","곤지암동서울#1 T/L","345kV 동서울#2S/S 건설공사","345kV GIS 6CB 증설모선 시험가압 선로","2023-12-14 09:00","2023-12-15 18:00","취소","취소","연속"]
[8,"남서울","동서울","동서울S/S #2 Sh.R CB","동서울S/S #2Sh.R 개폐제어기 설치공사","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-12-14 09:00","2023-12-16 18:00","2023-12-13 09:00","2023-12-15 18:00","연속"]
[9,"남서울","동서울","동서울S/S #76 PT CB","동서울S/S 345kV #76PT GIS 보통점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-12-11 15:00","2023-12-11 18:00","취소","취소","연속"]
[10,"남서울","동서울","동서울S/S #75 PT CB","동서울S/S 345kV #75PT GIS 보통점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-12-11 13:00","2023-12-11 15:00","취소","취소","연속"]
[11,"남서울","동서울","동서울S/S #71 PT CB","동서울S/S 345kV #71PT GIS 보통점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-12-11 11:00","2023-12-11 13:00","취소","취소","연속"]
[12,"남서울","동서울","동서울S/S #70 BUS","345kV 동서울#2S/S 건설공사","345kV GIS 6CB 증설","2023-12-11 09:00","2023-12-15 18:00","2023-12-18 09:00","2023-12-22 18:00","연속"]
[13,"남서울","동서울","동서울S/S #3 Sh.R CB","동서울S/S #3Sh.R 개폐제어기 설치공사","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-12-11 09:00","2023-12-13 18:00","2023-12-11 09:00","2023-12-12 18:00","연속"]
[14,"남서울","동서울","동서울S/S #70 PT CB","동서울S/S 345kV #70PT GIS 보통점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-12-11 09:00","2023-12-11 11:00","취소","취소","연속"]
[15,"남서울","동서울","동서울S/S SEC CB 75760","345kV 동서울#2S/S 건설공사","345kV GIS 6CB 증설모선 시험가압용","2023-12-21 09:00","2023-12-22 18:00","2023-12-14 09:00","2023-12-15 18:00","연속"]
[16,"남서울","동서울","동서울S/S SEC CB 70710","345kV 동서울#2S/S 건설공사","345kV GIS 6CB 증설모선 시험가압용","2023-12-14 09:00","2023-12-15 18:00","2023-12-21 09:00","2023-12-22 18:00","연속"]
[17,"남서울","영등포","서서울신광명#2 T/L","'22-'23년 가공송전 협력회사 총액공사","추락방지장치 설치공사","2023-12-01 07:00","2023-12-04 12:00","취소","취소","연속"]
[18,"남서울","영등포","신광명S/S #4 M.Tr","신광명SS #4M.Tr 3차 EGIS 설치공사","- #4M.Tr 3차 EGIS 공급용 전력케이블 접속 - 보호게전기 정정 및 시험","2023-12-16 09:00","2023-12-17 18:00","2023-12-16 09:00","2023-12-17 18:00","연속"]
[19,"남서울","영등포","신광명S/S #1 M.Tr","2022~23년 영등포전력지사 변전협력회사 총액공사","신광명S/S #1M.Tr 3차측 VCB 교체 및 옥외분전반 대체","2023-12-04 09:00","2023-12-06 18:00","취소","취소","연속"]
[20,"남서울","영등포","서서울신광명#1 T/L","'22-'23년 가공송전 협력회사 총액공사","추락방지장치 설치공사","2023-12-04 12:00","2023-12-13 18:00","취소","취소","연속"]
[21,"인천","김포","신김포서인천CC T/L","345kV 신김포-서(신)인천CCT/L 추락방지시설 설치공사","추락방지시설 설치공사","2023-12-07 07:00","2023-12-09 18:00","취소","취소","연속"]
[22,"인천","김포","신김포S/S #3 M.Tr","신김포S/S 345kV #3M.Tr CCTV 설치","신김포S/S 345kV #3M.Tr CCTV 설치","2023-12-04 09:00","2023-12-04 18:00","2023-12-04 09:00","2023-12-04 18:00","연속"]
[23,"인천","부평","신가좌S/S #4 M.Tr","신가좌S/S 345kV #4 M.Tr 3차측 과열 보수","신가좌S/S 345kV #4 M.Tr 3차측 과열 보수","2023-12-06 09:00","2023-12-07 18:00","2023-12-06 09:00","2023-12-07 18:00","연속"]
[24,"인천","부평","신가좌S/S #2 M.Tr","신가좌S/S 345kV #2 M.Tr 3차측 과열 보수","신가좌S/S 345kV #2 M.Tr 3차측 과열 보수","2023-12-04 09:00","2023-12-05 18:00","2023-12-04 09:00","2023-12-05 18:00","연속"]
[25,"인천","부평","신가좌S/S #3 M.Tr","신가좌S/S 345kV #3 M.Tr 보통점검 및 C상 OFU 누유보수","신가좌S/S 345kV #3 M.Tr 보통점검 및 C상 OFU 누유보수 6333GIS 보통점검 및 보조계전기교체 ","2023-12-01 09:00","2023-12-03 18:00","2023-12-02 09:00","2023-12-03 18:00","연속"]
[26,"인천","부평","인천C/C #1 Tie-Tr","인천CC S/Y 345kV #1 TIE TR 휴전작업","인천CC S/Y 345kV #1 TIE Tr 보통점검 인천CC S/Y 345kV #1 TIE Tr 3차측 CT 결선 변경 인천CC S/Y 345kV #1 TIE Tr 1차 7171GIS 조작시험","2023-12-04 09:00","2023-12-05 18:00","취소","취소","연속"]
[27,"인천","시흥","신시흥#1S/S #3 M.Tr","신시흥S/S 23kV 4389 VCB 대체공사","신시흥S/S 4389 VCB 대체공사(#5M.Tr 휴전)","2023-12-18 09:00","2023-12-19 18:00","취소","취소","연속"]
[28,"인천","시흥","신시흥#2S/S #5 M.Tr","신시흥S/S 23kV 4579, 4589 VCB 대체공사","신시흥S/S 4579, 4589 VCB 대체공사(#5M.Tr 휴전)","2023-12-20 09:00","2023-12-22 18:00","2023-12-20 09:00","2023-12-22 18:00","연속"]
[29,"인천","시흥","신시흥#2S/S #6 M.Tr","신시흥S/S #4 S.Tr 대체공사","신시흥S/S #4 S.Tr 대체공사(#6M.Tr 휴전)","2023-12-11 09:00","2023-12-15 18:00","2023-12-11 09:00","2023-12-15 18:00","연속"]
[30,"인천","부평","서인천C/C #1 Sh.R CB","서인천C/C 345kV #1 Sh.R 보통점검 및 절연열화 시험","서인천C/C 345kV #1 Sh.R 보통점검 절연열화 측정","2023-12-06 09:00","2023-12-06 18:00","2023-12-06 09:00","2023-12-06 18:00","연속"]
[31,"인천","시흥","영흥1TP영흥2TP#2 T/L","영흥S/Y 7271 차단기 포지션 밸브 점검","영흥S/Y 7271 차단기 포지션 밸브 점검","2023-12-04 09:00","2023-12-04 18:00","2023-12-04 09:00","2023-12-04 18:00","연속"]
[32,"인천","김포","신김포S/S #3 Sh.R CB","신김포S/S 345kV #3Sh.R 보통점검","신김포S/S 345kV #3Sh.R 보통점검","2023-12-04 09:00","2023-12-04 18:00","2023-12-04 09:00","2023-12-04 18:00","연속"]
[33,"인천","김포","신김포S/S #4 Sh.R CB","신김포S/S 345kV #4Sh.R 보통점검","신김포S/S 345kV #4Sh.R 보통점검","2023-12-05 09:00","2023-12-05 18:00","2023-12-05 09:00","2023-12-05 18:00","연속"]
[34,"경기북부","구리","신가평미금#2 T/L","345kV 미금S/S #4M.Tr 증설공사","○ #4M.Tr 무부하 가압 ○ 사용전 검사","2023-12-18 09:00","2023-12-22 18:00","2023-12-18 09:00","2023-12-22 18:00","연속"]
[35,"경기북부","구리","미금S/S CB 7800","345kV 미금S/S #4M.Tr 증설공사","○ #4M.Tr 무부하 가압 ○ 사용전 검사","2023-12-18 09:00","2023-12-22 18:00","2023-12-18 09:00","2023-12-22 18:00","연속"]
[36,"경기북부","구리","미금S/S STATCOM CB","미금S/S 345kV #79BAY B/F반 교체공사","미금S/S 345kV #79BAY B/F반 교체공사","2023-12-04 09:00","2023-12-08 18:00","2023-12-04 09:00","2023-12-08 18:00","연속"]
[37,"경기북부","직할","신의정부S/S #4 M.Tr","22-23년 변전 협력회사 총액공사","96B 보호반 회로 보완 작업","2023-12-05 09:00","2023-12-06 18:00","2023-12-05 09:00","2023-12-06 18:00","연속"]
[38,"경기","군포","서서울#2S/S #6 M.Tr","서서울2S/S 7A72, 7B72 GIS 보통점검","서서울2S/S 7A72, 7B72 GIS 보통점검","2023-12-04 14:00","2023-12-04 18:00","취소","취소","연속"]
[39,"경기","군포","서서울#2S/S #5 M.Tr","서서울2S/S 7A72, 7B72 GIS 보통점검","서서울2S/S 7A72, 7B72 GIS 보통점검","2023-12-04 09:00","2023-12-04 14:00","취소","취소","연속"]
[40,"경기","군포","화성서서울#1 T/L","서서울S/S 화성-서서울#1,2T/L CVT 보통점검","서서울S/S 화성-서서울#1,2T/L CVT 보통점검","2023-12-09 09:00","2023-12-09 14:00","2023-12-09 09:00","2023-12-09 14:00","연속"]
[41,"경기","군포","화성서서울#2 T/L","서서울S/S 화성-서서울#1,2T/L CVT 보통점검","서서울S/S 화성-서서울#1,2T/L CVT 보통점검","2023-12-09 14:00","2023-12-09 18:00","2023-12-09 14:00","2023-12-09 18:00","연속"]
[42,"경기","군포","서서울S/S #4 M.Tr","서서울S/S #4M.Tr 누유보수, 7872 전자변 교체 및 조작시험","서서울S/S #4M.Tr 누유보수, 7872 전자변 교체 및 조작시험","2023-12-04 09:00","2023-12-08 18:00","취소","취소","연속"]
[43,"경기","동부","곤지암여주복합#2 T/L","추락방지장치(수평) 설치공사","추락방지장치 설치 80기","2023-12-16 08:00","2023-12-17 18:00","2023-12-16 08:00","2023-12-17 18:00","연속"]
[44,"경기","동부","곤지암여주복합#1 T/L","추락방지장치(수평) 설치공사","추락방지장치 설치 80기","2023-12-09 08:00","2023-12-10 18:00","2023-12-09 08:00","2023-12-10 18:00","연속"]
[45,"경기","동부","곤지암여주복합#1 T/L","추락방지장치(수평) 설치공사","추락방지장치 설치 80기","2023-12-02 08:00","2023-12-03 18:00","2023-12-02 08:00","2023-12-03 18:00","연속"]
[46,"경기","동부","신충주T여주복합#1 T/L","345kV 신용인-동서울 등 16개T/L 추락방지장치 설치공사(신제천여주복합 T/L)","추락방지장치(수평) 설치 No.97 ~ 139 (2회선 철탑 39기)(신제천여주복합 T/L)","2023-12-02 07:00","2023-12-03 18:00","2023-12-02 07:00","2023-12-03 18:00","연속"]
[47,"경기","성남","신성남동서울#2 T/L","2023~2024년 지중송전설비 위탁정비공사(경기본부 성남전력지사)","154kV신성남동서울#2T/L C/T 및 LA점검","2023-12-19 09:00","2023-12-19 18:00","취소","취소","연속"]
[48,"경기","성남","신성남동서울#1 T/L","2023~2024년 지중송전설비 위탁정비공사(경기본부 성남전력지사)","154kV신성남동서울#1T/L C/T 및 LA점검","2023-12-18 09:00","2023-12-18 18:00","취소","취소","연속"]
[49,"경기","성남","신안성신수원#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치","2023-12-04 09:00","2023-12-08 18:00","취소","취소","연속"]
[50,"경기","성남","신안성서안성#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치(병가)","2023-12-07 09:00","2023-12-08 18:00","취소","취소","연속"]
[51,"경기","평택","고덕#2S/S #2 M.Tr","345kV 고덕2S/S M.Tr 과열발생 조치공사","345kV 고덕2S/S M.Tr 과열발생 조치공사","2023-12-11 09:00","2023-12-15 18:00","2023-12-11 09:00","2023-12-15 18:00","연속"]
[52,"경기","평택","고덕고덕2#1 T/L","345kV 고덕2S/S M.Tr 과열발생 조치공사","345kV 고덕2S/S M.Tr 과열발생 조치공사(무부하가압용 설비)","2023-12-14 13:00","2023-12-15 18:00","2023-12-14 13:00","2023-12-15 18:00","연속"]
[53,"경기","평택","고덕#2S/S #2 BUS","345kV 고덕2S/S M.Tr 과열발생 조치공사","345kV 고덕2S/S M.Tr 과열발생 조치공사(무부하가압용 설비)","2023-12-14 13:00","2023-12-15 18:00","2023-12-14 13:00","2023-12-15 18:00","연속"]
[54,"경기","평택","고덕#2S/S #1 M.Tr","345kV 고덕2S/S M.Tr 과열발생 조치공사","345kV 고덕2S/S M.Tr 과열발생 조치공사","2023-12-04 09:00","2023-12-08 18:00","2023-12-04 09:00","2023-12-08 18:00","연속"]
[55,"경기","평택","고덕고덕2#2 T/L","345kV 고덕2S/S M.Tr 과열발생 조치공사","345kV 고덕2S/S M.Tr 과열발생 조치공사(무부하가압용 설비)","2023-12-07 13:00","2023-12-08 18:00","2023-12-07 13:00","2023-12-08 18:00","연속"]
[56,"경기","평택","고덕#2S/S #1 BUS","345kV 고덕2S/S M.Tr 과열발생 조치공사","345kV 고덕2S/S M.Tr 과열발생 조치공사(무부하가압용 설비)","2023-12-07 13:00","2023-12-08 18:00","2023-12-07 13:00","2023-12-08 18:00","연속"]
[57,"경기","평택","고덕#2S/S #3 M.Tr","345kV 고덕2S/S M.Tr 과열발생 조치공사","345kV 고덕2S/S M.Tr 과열발생 조치공사","2023-12-18 09:00","2023-12-22 18:00","2023-12-18 09:00","2023-12-22 18:00","연속"]
[58,"경기","평택","고덕고덕2#2 T/L","345kV 고덕2S/S M.Tr 과열발생 조치공사","345kV 고덕2S/S M.Tr 과열발생 조치공사(무부하가압용 설비)","2023-12-21 13:00","2023-12-22 18:00","2023-12-21 13:00","2023-12-22 18:00","연속"]
[59,"경기","평택","고덕#2S/S #1 BUS","345kV 고덕2S/S M.Tr 과열발생 조치공사","345kV 고덕2S/S M.Tr 과열발생 조치공사(무부하가압용 설비)","2023-12-21 13:00","2023-12-22 18:00","2023-12-21 13:00","2023-12-22 18:00","연속"]
[60,"경기","평택","고덕S/S STATCOM CB","고덕S/S 345kV STATCOM용 GIS 케이블 결선 및 준공시험","케이블 포설 및 결선, DB시험 등 준공시험","2023-12-11 09:00","2023-12-15 18:00","2023-12-11 09:00","2023-12-15 18:00","연속"]
[61,"경기","평택","서안성신진천#1 T/L","23년 평택전력 변전협력회사 총액공사","서안성S/S 서안성-신진천#1T/L 보호배전반 대체공사","2023-12-01 09:00","2023-12-15 18:00","취소","취소","연속"]
[62,"경기","평택","화성평택TP#1 T/L","23년 평택전력지사 변전협력회사 총액공사","평택T/P 화성-평택T/P 7621DS인디케이터 보수","2023-12-02 09:00","2023-12-02 18:00","2023-12-02 09:00","2023-12-02 18:00","연속"]
[63,"강원","강릉","신양양S/S #1 M.Tr","2023 강릉전력지사 변전협력회사 총액공사","3차 LA(A,B,C상) 대체","2023-12-06 10:00","2023-12-06 18:00","2023-12-06 10:00","2023-12-06 18:00","연속"]
[64,"강원","강릉","신양양S/S #2 M.Tr","2023 강릉전력지사 변전협력회사 총액공사","3차 LA(A,B,C상) 대체","2023-12-07 10:00","2023-12-07 18:00","2023-12-07 10:00","2023-12-07 18:00","연속"]
[65,"강원","태백","신태백S/S CB 7571","2023년 태백전력지사 변전협력회사 총액공사","신태백S/S 345kV 75BAY B/F 보호반 교체 345kV GIS(콘덴서 Type) 절연열화 측정(병행)","2023-12-11 09:00","2023-12-22 18:00","2023-12-11 09:00","2023-12-22 18:00","연속"]
[66,"강원","태백","신태백한울NP#1 T/L","345kV 신태백-한울NP2T/L 산불피해개소 전선교체공사","산불피해개소 전선교체공사","2023-12-11 09:00","2023-12-24 18:00","취소","취소","연속"]
[67,"강원","태백","신태백S/S #3 Sh.R CB","2023년 태백전력지사 변전협력회사 총액공사","신태백S/S 345kV 75BAY B/F 보호반 교체 345kV GIS(콘덴서 Type) 절연열화 측정(병행)","2023-12-11 09:00","2023-12-22 18:00","2023-12-11 09:00","2023-12-22 18:00","연속"]
[68,"충북","충주","신제천S/S CB 7471","22-23년 충주전력지사 변전정비 총액공사","신제천S/S 345kV 신제천-여주복합T/L GIS 보통점검","2023-12-07 09:00","2023-12-07 14:00","2023-12-07 09:00","2023-12-07 14:00","연속"]
[69,"충북","충주","신제천S/S CB 7400","22-23년 충주전력지사 변전정비 총액공사","신제천S/S 345kV 신제천-여주복합T/L-TIE GIS 보통점검","2023-12-07 14:00","2023-12-07 18:00","2023-12-07 14:00","2023-12-07 18:00","연속"]
[70,"대전세종충남","대전","신옥천신계룡 T/L","신계룡S/S 345kV GIS DS 모터 불량 보수","신계룡S/S 345kV GIS DS 모터 불량 보수","2023-12-05 09:00","2023-12-05 18:00","2023-12-05 09:00","2023-12-05 18:00","연속"]
[71,"대전세종충남","대전","신계룡S/S #1 BUS","신계룡S/S 345kV GIS DS 모터 불량 보수","신계룡S/S 345kV GIS DS 모터 불량 보수","2023-12-05 09:00","2023-12-05 18:00","2023-12-05 09:00","2023-12-05 18:00","연속"]
[72,"대전세종충남","서산","신당진S/S #3 M.Tr","23년 서산P/O 변전협력회사 총액공사","신당진S/S 345kV #3M.Tr 3차 PT, #3-1,2 Sh.R 보통점검","2023-12-01 09:00","2023-12-01 18:00","2023-12-01 09:00","2023-12-01 18:00","연속"]
[73,"대전세종충남","서산","태안T/P SEC CB 71720","태안화력S/Y 345kV 옥외설비 GIS 내장화공사","(무부하가압) 태안화력S/Y 345kV 개폐소-태안화력#2T/L 옥외설비 GIS 내장화공사","2023-12-21 09:00","2023-12-22 09:00","취소","취소","연속"]
[74,"대전세종충남","서산","태안T/P #72 BUS","태안화력S/Y 345kV 옥외설비 GIS 내장화공사","(무부하가압) 태안화력S/Y 345kV 개폐소-태안화력#2T/L 옥외설비 GIS 내장화공사","2023-12-21 09:00","2023-12-22 09:00","취소","취소","연속"]
[75,"대전세종충남","서산","신당진개폐소태안TP#2 T/L","태안화력S/Y 345kV 옥외설비 GIS 내장화공사","(10월 휴전 취소시) 태안화력S/Y 345kV 개폐소-태안화력#2T/L 옥외설비 GIS 내장화공사 (병행) 345kV 개폐소-태안화력#2T/L 보호반 대체","2023-12-04 09:00","2023-12-22 18:00","취소","취소","연속"]
[76,"대전세종충남","천안","신온양S/S #4 M.Tr","(11월취소시)신온양S/S 345kV 77B/F 교체 및 결상회로 보완","(11월취소시)신온양S/S 345kV 77B/F 교체 및 결상회로 보완작업","2023-12-04 09:00","2023-12-07 18:00","취소","취소","연속"]
[77,"대전세종충남","천안","신온양신탕정#2 T/L","(11월취소시)신온양S/S 345kV 78B/F 교체, 결상회로 보완작업","(11월취소시)신온양S/S 345kV 78B/F 교체, 결상회로 보완작업","2023-12-11 09:00","2023-12-14 18:00","취소","취소","연속"]
[78,"대전세종충남","천안","신온양서서울#1 T/L","(11월취소시)신온양S/S 345kV 78B/F 교체, 결상회로 보완작업","(11월취소시)신온양S/S 345kV 78B/F 교체, 결상회로 보완작업","2023-12-11 09:00","2023-12-14 18:00","취소","취소","연속"]
[79,"대전세종충남","천안","신온양서서울#2 T/L","(11월취소시)신온양S/S 345kV 77B/F 교체 및 결상회로 보완","(11월취소시)신온양S/S 345kV 77B/F 교체 및 결상회로 보완","2023-12-04 09:00","2023-12-07 18:00","취소","취소","연속"]
[80,"대전세종충남","천안","신탕정S/S #4 M.Tr","신탕정S/S #4M.Tr 점검","신탕정S/S #4M.Tr 점검","2023-12-04 09:00","2023-12-06 18:00","취소","취소","연속"]
[81,"대전세종충남","청양","보령C/C CB 7471","(11월취소시)청양P/O 362kV GIS 보통점검공사","(11월취소시)보령C/C 362kV 7471 GIS 보통점검","2023-12-04 10:00","2023-12-04 18:00","취소","취소","연속"]
[82,"대전세종충남","청양","청양S/S CB 7700","(11월취소시)청양P/O 362kV GIS 보통점검공사","(11월취소시)청양S/S 362kV 7700 GIS 보통점검","2023-12-07 08:00","2023-12-07 18:00","취소","취소","연속"]
[83,"대전세종충남","청양","청양S/S CB 7772","(11월취소시)청양P/O 362kV GIS 보통점검공사","(11월취소시)청양S/S 362kV 7772 GIS 보통점검","2023-12-08 08:00","2023-12-08 18:00","취소","취소","연속"]
[84,"대전세종충남","청양","청양S/S CB 7372","(11월취소시)청양P/O 362kV GIS 보통점검공사","(11월취소시)청양S/S 362kV 7372 GIS 보통점검","2023-12-06 08:00","2023-12-06 18:00","취소","취소","연속"]
[85,"대전세종충남","청양","청양S/S CB 7371","(11월취소시)청양P/O 362kV GIS 보통점검공사","(11월취소시)청양S/S 362kV 7371 GIS 보통점검","2023-12-05 08:00","2023-12-05 18:00","취소","취소","연속"]
[86,"대전세종충남","청양","청양S/S CB 7172","(11월취소시)청양P/O 변전협력회사 총액공사","(11월 취소시) 청양S/S 345kV 청양-보령화력#1T/L CB (7172) C상 전자변 교체","2023-12-04 08:00","2023-12-04 18:00","취소","취소","연속"]
[87,"대전세종충남","청양","청양신보령TP T/L","(11월취소시)청양P/O 변전협력회사 총액공사","(11월 취소시)345kV 청양-신보령T/L - 청양S/S LA 초기점검(A,B,C)","2023-12-01 08:00","2023-12-01 18:00","취소","취소","연속"]
[88,"전북","군산","군산신김제#2 T/L","군산변전소 345kV GIS 대체공사(기기)","○ 362kV GIS 40kA 4000A × 10CB(PT Bay 포함) 철거 ○ 362kV GIS 50kA 4000A × 10CB(PT Bay 포함) 설치 ○ 기초 BaseChennel × 4Bay분 설치 ○ 기타부대공사 × 1식","2023-12-03 16:00","2023-12-04 16:00","2023-12-03 16:00","2023-12-04 16:00","연속"]
[89,"전북","군산","군산S/S #1 M.Tr","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-07 16:00","2023-12-07 18:00","2023-12-07 16:00","2023-12-07 18:00","연속"]
[90,"전북","군산","군산S/S #1 M.Tr","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-14 16:00","2023-12-15 18:00","2023-12-14 16:00","2023-12-15 18:00","연속"]
[91,"전북","군산","군산S/S #1 M.Tr","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-24 18:00","2023-12-25 18:00","2023-12-24 18:00","2023-12-25 18:00","연속"]
[92,"전북","군산","군산S/S #1 M.Tr","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-25 18:00","2023-12-26 18:00","2023-12-25 18:00","2023-12-26 18:00","연속"]
[93,"전북","군산","군산S/S #3 M.Tr","군산P/O 기타변전 설비 점검 공사","군산P/O #3M.Tr PT 점검","2023-12-28 09:00","2023-12-28 18:00","2023-12-27 09:00","2023-12-27 18:00","연속"]
[94,"전북","군산","군산새만금#1 T/L","345kV 군산-새만금 등 8개T/L 추락방지장치 설치공사","□ 공사개요 ○ 설치 철탑 : 345kV 군산-새만금#1T/L No.1~88 (관형주 제외) ○ 추락방지장치 : 수평설치(73기)","2023-12-05 07:00","2023-12-11 18:00","취소","취소","매일"]
[95,"전북","군산","군산새만금#2 T/L","345kV 군산-새만금 등 8개T/L 추락방지장치 설치공사","□ 공사개요 ○ 설치 철탑 : 345kV 군산-새만금#2T/L No.1~88 (관형주 제외) ○ 추락방지장치 : 수평설치(73기)","2023-12-12 07:00","2023-12-18 18:00","취소","취소","매일"]
[96,"전북","군산","청양군산#1 T/L","군산S/S 345kV 장기사용 GIS 대체공사(일반)","○ 송전선로 보호반 이설(청양-군산#1T/L) ○ 인출송전선로 이설(73Bay →74Bay) ○ LA, CVT 이설(73Bay →74Bay) ○345kV 인출철구보강(POST 부재 및 볼트규격 변경)","2023-12-27 07:00","2024-01-05 18:00","2023-12-28 07:00","2024-01-06 18:00","연속"]
[97,"전북","김제","신김제S/S #3 M.Tr","신김제S/S #3M.Tr 3차 LA,GPT점검, 1차 차단기 절연열화측정","신김제S/S 345kV #3M.Tr 3차 LA,GPT점검 및 1차 차단기 절연열화측정","2023-12-01 09:00","2023-12-01 18:00","2023-12-01 09:00","2023-12-01 18:00","연속"]
[98,"전북","직할","신남원신광주#1 T/L","23년 전북직할 변전협력회사 총액공사","신남원S/S 345kV 신남원-신광주 #1T/L LA, CVT 보통점검","2023-12-11 09:00","2023-12-11 18:00","2023-12-11 09:00","2023-12-11 18:00","연속"]
[99,"전북","직할","신남원S/S CB 7100","신남원S/S 7100 TIE 단일차단기 점검(즉시가압가능)","신남원S/S 7100 TIE 단일차단기 점검(즉시가압가능)","2023-12-18 09:00","2023-12-18 18:00","취소","취소","연속"]
[100,"전북","직할","신옥천신남원#2 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 71Bay BF 보호배전반 대체 및 CVT 대체","2023-12-18 09:00","2023-12-21 18:00","취소","취소","연속"]
[101,"전북","직할","신남원한빛NP#2 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 71Bay BF 보호배전반 대체 및 LA 보통점검","2023-12-18 09:00","2023-12-21 18:00","취소","취소","연속"]
[102,"전북","직할","신남원S/S CB 7771","신남원S/S 신남원-신광주#1T/L CB 정밀점검(7771)","신남원S/S 신남원-신광주#1T/L CB 정밀점검(7771)","2023-12-04 09:00","2023-12-08 18:00","2023-12-04 09:00","2023-12-08 18:00","연속"]
[103,"전북","직할","신남원신광주#1 T/L","2023년 전북 직할 362kV GIS 정밀점검(무부하가압용)","2023년 전북 직할 362kV GIS 정밀점검 공사 - 7700CB 단독차단기 정밀점검 - 무부하가압용 선로","2023-12-29 17:00","2023-12-29 18:00","취소","취소","연속"]
[104,"전북","직할","신남원신광주#2 T/L","23년 전북직할 변전협력회사 총액공사","신남원S/S 345kV 신남원-신광주 #2T/L LA 보통점검","2023-12-12 09:00","2023-12-12 18:00","취소","취소","연속"]
[105,"전북","직할","신남원신광주#1 T/L","2023년 전북 직할 362kV GIS 정밀점검(무부하가압용)","2023년 전북 직할 362kV GIS 정밀점검 공사 - 7771CB 단독차단기 정밀점검 - 무부하가압용 선로","2023-12-08 17:00","2023-12-08 18:00","2023-12-08 17:00","2023-12-08 18:00","연속"]
[106,"전북","직할","신옥천신남원#1 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 72Bay BF 보호배전반 대체 및 CVT 보통점검","2023-12-26 09:00","2023-12-29 18:00","취소","취소","연속"]
[107,"전북","직할","신남원한빛NP#1 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 72Bay BF 보호배전반 대체","2023-12-26 09:00","2023-12-29 18:00","취소","취소","연속"]
[108,"전북","직할","신남원신광주#2 T/L","2023년 전북 직할 362kV GIS 정밀점검(무부하가압용)","2023년 전북 직할 362kV GIS 정밀점검 공사 - 7871CB 단독차단기 정밀점검 - 무부하가압용 선로","2023-12-15 17:00","2023-12-15 18:00","취소","취소","연속"]
[109,"전북","직할","신남원의령#2 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 74Bay BF 보호배전반 대체 및 CVT 보통점검","2023-12-26 09:00","2023-12-29 18:00","2023-12-26 09:00","2023-12-29 18:00","연속"]
[110,"전북","직할","신남원신광주#2 T/L","2023년 전북 직할 362kV GIS 정밀점검(무부하가압용)","2023년 전북 직할 362kV GIS 정밀점검 공사 - 7800CB 단독차단기 정밀점검 - 무부하가압용 선로","2023-12-22 17:00","2023-12-22 18:00","취소","취소","연속"]
[111,"전북","직할","신남원광양#1 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 75Bay BF 보호배전반 대체 및 LA, CVT 보통점검","2023-12-18 09:00","2023-12-21 18:00","2023-12-13 09:00","2023-12-16 18:00","연속"]
[112,"광주전남","강진","신강진S/S #4 M.Tr","2022~23년도 강진전력지사 변전협력회사 총액공사","2022~23년도 강진전력지사 변전협력회사 총액공사 신강진S/S #4M.Tr 1차 부싱 절연열화 측정","2023-12-01 10:00","2023-12-01 18:00","2023-12-01 10:00","2023-12-01 18:00","연속"]
[113,"광주전남","광주","신광주S/S CB 7172","7172 GIS 보통점검","7172 GIS 보통점검,즉시가압가능","2023-12-06 08:00","2023-12-06 18:00","취소","취소","연속"]
[114,"광주전남","광주","신광주신화순#2 T/L","22~23년 송전협력회사 총액공사","신광주-신화순T/L 추락방지장치 설치공사(No.1~121)","2023-12-04 08:00","2023-12-09 18:00","취소","취소","매일"]
[115,"광주전남","광주","신광주신화순#1 T/L","23년 광주전력지사 변전협력회사 총액공사","- 76BAY 차단실패보호반 교체","2023-12-04 09:00","2023-12-12 18:00","2023-12-04 09:00","2023-12-12 18:00","연속"]
[116,"광주전남","광주","신광주S/S #3 M.Tr","23년 광주전력지사 변전협력회사 총액공사","- 76BAY 차단실패보호반 교체 - 345kV M.Tr 보통점검 - #3M.Tr 3차 차단기 교체(3차 Main) - 3차측 과열조치 시행","2023-12-04 09:00","2023-12-12 18:00","2023-12-04 09:00","2023-12-12 18:00","연속"]
[117,"광주전남","광주","신광주S/S CB 7171","7171 GIS 보통점검","7171 GIS 보통점검,즉시가압가능","2023-12-07 08:00","2023-12-07 18:00","취소","취소","연속"]
[118,"광주전남","광주","신남원신광주#1 T/L","2023년 가공송전선로 순시점검 위탁공사","345kV 신남원-신광주T/L 137호 과열정비 시행","2023-12-07 09:00","2023-12-07 11:00","취소","취소","연속"]
[119,"광주전남","광주","신남원신광주#2 T/L","'22~23년 광주 변전협력회사 총액공사","신남원-신광주#2T/L CVT 교체","2023-12-07 12:00","2023-12-07 18:00","2023-12-12 09:00","2023-12-12 18:00","연속"]
[120,"광주전남","광주","신광주한빛NP#2 T/L","2023년 가공송전선로 순시점검 위탁공사","345kV 신광주-한빛NP 73,100,134호 과열정비 시행","2023-12-08 08:00","2023-12-08 12:00","취소","취소","연속"]
[121,"광주전남","광주","신광주S/S CB 7200","7200 CB 조작시험","7200 CB 조작시험,즉시가압가능","2023-12-08 08:00","2023-12-08 18:00","취소","취소","연속"]
[122,"광주전남","광주","신광주한빛NP#2 T/L","7200 CB 조작시험,CVT 보통점검","7200 CB 조작시험,CVT 보통점검,즉시가압가능","2023-12-08 08:00","2023-12-08 18:00","취소","취소","연속"]
[123,"광주전남","광주","신광주한빛NP#1 T/L","2023년 가공송전선로 순시점검 위탁공사","345kV 신광주-한빛NP 73,100,134호 과열정비 시행","2023-12-08 13:00","2023-12-08 18:00","취소","취소","연속"]
[124,"광주전남","광주","신광주신화순#1 T/L","22~23년 송전협력회사 총액공사","신광주-신화순T/L 추락방지장치 설치공사(No.1~121)","2023-12-11 08:00","2023-12-16 18:00","취소","취소","매일"]
[125,"광주전남","광주","신광주S/S #1 BUS","장기사용 345kV #1BUS 모선보호반 교체","장기사용 345kV #1BUS 모선보호반 교체,즉시가압불가","2023-12-11 08:00","2023-12-14 18:00","취소","취소","연속"]
[126,"광주전남","광주","신광주S/S #2 BUS","장기사용 345kV #2BUS 모선보호반 교체","장기사용 345kV #2BUS 모선보호반 교체,즉시가압불가","2023-12-18 08:00","2023-12-21 18:00","취소","취소","연속"]
[127,"광주전남","목포","한빛2NP한빛3NP#4 T/L","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","- 362kV GIS(40kA 4000A #2BUS) × 1식 철거(모선DS 18개 포함) - 362kV GIS(63kA 6300A #2BUS) × 1식 설치(모선DS 18개 포함) - 78,79,7A BAY CVT 내장화 설치 - 기기기초 보강, 제어케이블 분리 및 결선 × 1식 - 기타 부대공사","2023-12-28 09:00","2023-12-28 18:00","취소","취소","연속"]
[128,"광주전남","목포","한빛2NP한빛3NP#3 T/L","22~23년 목포 송전 협력회사 총액공사(추락방지)","345kV 한빛연락#3T/L 추락방지장치 설치","2023-12-05 07:00","2023-12-05 18:00","2023-12-05 07:00","2023-12-05 18:00","연속"]
[129,"광주전남","목포","한빛1NP한빛2NP#1 T/L","22~23년 목포 송전 협력회사 총액공사(추락방지)","345kV 한빛연락#1T/L 추락방지장치 설치","2023-12-05 07:00","2023-12-05 18:00","취소","취소","연속"]
[130,"광주전남","목포","한빛2NP한빛3NP#4 T/L","22~23년 목포 송전 협력회사 총액공사(추락방지)","345kV 한빛연락#4T/L 추락방지장치 설치","2023-12-06 07:00","2023-12-06 18:00","2023-12-06 07:00","2023-12-06 18:00","연속"]
[131,"광주전남","목포","한빛1NP한빛2NP#2 T/L","22~23년 목포 송전 협력회사 총액공사(추락방지)","345kV 한빛연락#2T/L 추락방지장치 설치","2023-12-06 07:00","2023-12-06 18:00","취소","취소","연속"]
[132,"광주전남","목포","한빛2NP한빛3NP#3 T/L","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","- 362kV GIS(40kA 4000A #2BUS) × 1식 철거(모선DS 18개 포함) - 362kV GIS(63kA 6300A #2BUS) × 1식 설치(모선DS 18개 포함) - 78,79,7A BAY CVT 내장화 설치 - 기기기초 보강, 제어케이블 분리 및 결선 × 1식 - 기타 부대공사","2023-12-27 09:00","2023-12-27 18:00","취소","취소","연속"]
[133,"광주전남","목포","한빛1NP한빛2NP#2 T/L","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","- 362kV GIS(40kA 4000A #2BUS) × 1식 철거(모선DS 18개 포함) - 362kV GIS(63kA 6300A #2BUS) × 1식 설치(모선DS 18개 포함) - 78,79,7A BAY CVT 내장화 설치 - 기기기초 보강, 제어케이블 분리 및 결선 × 1식 - 기타 부대공사","2023-12-23 09:00","2023-12-23 18:00","취소","취소","연속"]
[134,"광주전남","목포","한빛1NP한빛2NP#1 T/L","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","- 362kV GIS(40kA 4000A #2BUS) × 1식 철거(모선DS 18개 포함) - 362kV GIS(63kA 6300A #2BUS) × 1식 설치(모선DS 18개 포함) - 78,79,7A BAY CVT 내장화 설치 - 기기기초 보강, 제어케이블 분리 및 결선 × 1식 - 기타 부대공사","2023-12-24 09:00","2023-12-24 18:00","취소","취소","연속"]
[135,"광주전남","목포","신남원한빛NP#1 T/L","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","- 362kV GIS(40kA 4000A #2BUS) × 1식 철거(모선DS 18개 포함) - 362kV GIS(63kA 6300A #2BUS) × 1식 설치(모선DS 18개 포함) - 78,79,7A BAY CVT 내장화 설치 - 기기기초 보강, 제어케이블 분리 및 결선 × 1식 - 기타 부대공사","2023-12-25 09:00","2023-12-25 18:00","취소","취소","연속"]
[136,"광주전남","목포","신남원한빛NP#2 T/L","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","- 362kV GIS(40kA 4000A #2BUS) × 1식 철거(모선DS 18개 포함) - 362kV GIS(63kA 6300A #2BUS) × 1식 설치(모선DS 18개 포함) - 78,79,7A BAY CVT 내장화 설치 - 기기기초 보강, 제어케이블 분리 및 결선 × 1식 - 기타 부대공사","2023-12-26 09:00","2023-12-26 18:00","취소","취소","연속"]
[137,"광주전남","목포","한빛#2N/P #2 BUS","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","- 362kV GIS(40kA 4000A #2BUS) × 1식 철거(모선DS 18개 포함) - 362kV GIS(63kA 6300A #2BUS) × 1식 설치(모선DS 18개 포함) - 78,79,7A BAY CVT 내장화 설치 - 기기기초 보강, 제어케이블 분리 및 결선 × 1식 - 기타 부대공사","2023-12-22 09:00","2024-02-07 18:00","취소","취소","연속"]
[138,"광주전남","순천","광양C/C CB 7171","22-23년 순천전력지사 변전협력회사 총액공사","GIS 차단기 조작시험 및 절연열화 측정","2023-12-13 09:00","2023-12-13 12:00","취소","취소","연속"]
[139,"광주전남","순천","광양C/C CB 7172","22-23년 순천전력지사 변전협력회사 총액공사","GIS 차단기 조작시험 및 절연열화 측정","2023-12-13 15:00","2023-12-13 18:00","취소","취소","연속"]
[140,"광주전남","순천","광양C/C CB 7100","22-23년 순천전력지사 변전협력회사 총액공사","GIS 차단기 조작시험 및 절연열화 측정","2023-12-13 12:00","2023-12-13 15:00","취소","취소","연속"]
[141,"광주전남","순천","광양여수TP T/L","345kV 광양-여수TP 일부구간 지중화 공사","345kV 광양-여수TP 일부 지중화 관련 C/T 설치공사","2023-12-25 09:00","2023-12-29 18:00","2023-12-26 09:00","2023-12-29 18:00","연속"]
[142,"광주전남","순천","광양율촌CC T/L","345kV 광양-여수TP 일부구간 지중화 공사","345kV 광양-여수TP 일부 지중화 관련 C/T 설치공사","2023-12-18 09:00","2023-12-22 18:00","2023-12-18 09:00","2023-12-22 18:00","연속"]
[143,"광주전남","순천","광양S/S #2 M.Tr","22-23년 순천전력지사 변전협력회사 총액공사","#2M.Tr 3차 MAIN VCB 대체(즉시가압 불가)","2023-12-13 08:00","2023-12-14 18:00","취소","취소","연속"]
[144,"광주전남","순천","광양S/S #1 M.Tr","22-23년 순천전력지사 변전협력회사 총액공사","#1M.Tr 3차 MAIN VCB 대체","2023-12-11 08:00","2023-12-12 18:00","취소","취소","연속"]
[145,"광주전남","순천","광양S/S #3 M.Tr","22-23년 순천전력지사 변전협력회사 총액공사","2차 LA 대체","2023-12-04 08:00","2023-12-04 18:00","취소","취소","연속"]
[146,"광주전남","순천","광양광양제철#1 T/L","345kV 광양-광양CC #1T/L 피뢰기 설치공사","345kV 광양-광양CC #1T/L 피뢰기 설치공사를 위한 병가선로(광양제철#1T/L) 휴전","2023-12-04 07:00","2023-12-12 18:00","2023-12-04 07:00","2023-12-12 18:00","매일"]
[147,"광주전남","순천","광양광양CC#1 T/L","345kV 광양-광양CC #1T/L 피뢰기 설치공사","345kV 광양-광양CC #1T/L 피뢰기 설치공사(No.1~60호)","2023-12-04 07:00","2023-12-12 18:00","2023-12-04 07:00","2023-12-12 18:00","매일"]
[148,"광주전남","순천","여수T/P #3 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","GIS 1차 절연열화측정 및 2차 보조계전기 교체","2023-12-15 10:00","2023-12-15 18:00","취소","취소","연속"]
[149,"광주전남","순천","율촌C/C CB 7271","22-23년 순천전력지사 변전협력회사 총액공사","GIS 차단기 조작시험 및 절연열화 측정","2023-12-08 09:00","2023-12-08 18:00","취소","취소","연속"]
[150,"광주전남","순천","율촌CC여수TP T/L","345kV 율촌CC분기 T/L EBA 자기애관 교체공사","광양-율촌CC 3상, 율촌CC-여수TP 3상 애관교체(자기애관 → 폴리머애관)","2023-12-07 09:00","2023-12-09 18:00","취소","취소","연속"]
[151,"광주전남","순천","광양율촌CC T/L","345kV 율촌CC분기 T/L EBA 자기애관 교체공사","광양-율촌CC 3상, 율촌CC-여수TP 3상 애관교체(자기애관 → 폴리머애관)","2023-12-04 09:00","2023-12-06 18:00","취소","취소","연속"]
[152,"대구","칠곡","서대구S/S #2 M.Tr","서대구S/S 345kV 주변압기측 현대화 공사","신설 변압기용 Gantry Tower 조립관련 안전거리 확보 M.Tr 1차측 POST 철구 보강관련 안전거리 확보","2023-12-26 08:00","2023-12-29 18:00","2023-12-26 08:00","2023-12-29 18:00","연속"]
[153,"대구","칠곡","서대구S/S #1 BUS","서대구S/S 7251 DS 과열보수","서대구S/S 7251 DS 과열보수","2023-12-06 09:30","2023-12-06 18:00","2023-12-06 09:30","2023-12-06 18:00","연속"]
[154,"대구","칠곡","서대구S/S #3 M.Tr","서대구S/S 345kV 주변압기측 현대화 공사","신설 변압기용 Gantry Tower 조립관련 안전거리 확보 M.Tr 1차측 POST 철구 보강관련 안전거리 확보","2023-12-18 08:00","2023-12-21 18:00","2023-12-18 08:00","2023-12-21 18:00","연속"]
[155,"대구","칠곡","서대구S/S CB 7171","서대구S/S 7171 GCB 보통점검","서대구S/S 7171 GCB 보통점검","2023-12-06 09:30","2023-12-06 18:00","2023-12-06 09:30","2023-12-06 18:00","연속"]
[156,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S 345kV 주변압기측 현대화 공사","신설 변압기용 Gantry Tower 조립관련 안전거리 확보","2023-12-15 08:00","2023-12-15 18:00","2023-12-15 08:00","2023-12-15 18:00","연속"]
[157,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S 345kV 주변압기측 현대화 공사","신설 변압기용 Gantry Tower 조립관련 안전거리 확보","2023-12-14 08:00","2023-12-14 18:00","2023-12-14 08:00","2023-12-14 18:00","연속"]
[158,"대구","칠곡","북경남서대구#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 북경남-서대구T/L 수평 추락방지장치 설치공사(345kV 신옥천-북경남T/L 병가선로)(안전확보)","2023-12-04 07:00","2023-12-08 18:00","2023-12-04 07:00","2023-12-08 18:00","연속"]
[159,"대구","포항","신월성N/P CB 7172","22~23년도 포항전력지사 변전총액공사","신월성S/Y 71BAY B/F반 교체","2023-12-18 09:00","2023-12-22 18:00","2023-12-18 09:00","2023-12-22 18:00","연속"]
[160,"대구","포항","신포항신월성NP#4 T/L","22~23년도 포항전력지사 변전총액공사","신월성S/Y 71BAY B/F반 교체","2023-12-18 09:00","2023-12-22 18:00","2023-12-18 09:00","2023-12-22 18:00","연속"]
[161,"대구","포항","신포항S/S #1 M.Tr","신포항S/S 345kV 주변압기측 현대화 공사","신포항S/S 345kV 주변압기측 현대화 공사","2023-12-11 08:00","2023-12-27 17:00","2023-12-11 08:00","2023-12-27 17:00","연속"]
[162,"대구","포항","월성N/P CB 7200","22~23년도 포항전력지사 변전총액공사","월성S/Y 7200 GIS 보통점검","2023-12-04 09:00","2023-12-04 18:00","2023-12-04 09:00","2023-12-04 18:00","연속"]
[163,"대구","포항","월성N/P CB 7272","22~23년도 포항전력지사 변전총액공사","월성S/Y 7272 GIS 보통점검","2023-12-04 09:00","2023-12-04 18:00","2023-12-04 09:00","2023-12-04 18:00","연속"]
[164,"부산울산","동부산","신양산S/S #4 M.Tr","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 75BAY MICRO PILE 작업(안전이격)","2023-12-03 08:00","2023-12-03 18:00","2023-12-17 08:00","2023-12-17 18:00","연속"]
[165,"부산울산","동부산","신양산고리NP#2 T/L","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 75BAY MICRO PILE 작업(안전이격)","2023-12-02 08:00","2023-12-02 18:00","2023-12-16 08:00","2023-12-16 18:00","연속"]
[166,"부산울산","북부산","북부산신울산#2 T/L","345kV 북부산-신울산 등 3개T/L 수평추락방지장치 설치공사","345kV 북부산-신울산#2T/L 수평추락방지장치 설치 : 1~110호, 87기","2023-12-16 08:00","2023-12-22 18:00","2023-12-16 08:00","2023-12-22 18:00","매일"]
[167,"부산울산","북부산","북부산S/S #4 M.Tr","345kV 북부산 STATCOM 23kV 개폐장치 설치공사 외 2건","345kV 북부산 STATCOM 23kV 개폐장치 설치공사(전문) 외 2건 공사 무부하시험","2023-12-05 14:00","2023-12-06 14:00","2023-12-05 14:00","2023-12-06 14:00","연속"]
[168,"부산울산","북부산","북부산S/S #3 M.Tr","345kV 북부산 STATCOM 23kV 개폐장치 설치공사 외 2건","345kV 북부산 STATCOM 23kV 개폐장치 설치공사(전문) 외 2건 공사 무부하시험","2023-12-04 13:00","2023-12-05 13:00","2023-12-04 13:00","2023-12-05 13:00","연속"]
[169,"부산울산","북부산","북부산S/S #4 Sh.R CB","22-23년 북부산전력지사 변전총액공사","북부산S/S 345kV #4Sh.R 보통점검","2023-12-01 09:00","2023-12-01 18:00","2023-12-01 09:00","2023-12-01 18:00","연속"]
[170,"부산울산","북부산","북부산S/S CB 7900","22-23년 북부산전력지사 변전총액공사","북부산S/S 345kV #4Sh.R 보통점검","2023-12-01 09:00","2023-12-01 18:00","2023-12-01 09:00","2023-12-01 18:00","연속"]
[171,"부산울산","북부산","북부산S/S CB 7972","22-23년 북부산전력지사 변전총액공사","북부산S/S 345kV #4Sh.R 보통점검","2023-12-01 09:00","2023-12-01 18:00","2023-12-01 09:00","2023-12-01 18:00","연속"]
[172,"부산울산","울산","울산C/C #2 Tie-Tr","22~23년 변전협력회사 총액공사","- B/F 보호반 대체 - M.Tr 보통점검 - 1차 GIS(7871,7800) 보통점검 - 2차 GIS 보통점검 - 3차 GIS 보통점검 - #2S.Tr 보통점검","2023-12-01 09:00","2023-12-03 18:00","2023-12-01 09:00","2023-12-03 18:00","연속"]
[173,"부산울산","울산","울주S/S #3 M.Tr","22~23년 변전협력회사 총액공사","- 6B2DS 스페이서 가스 누기보수","2023-12-04 09:00","2023-12-06 18:00","2023-12-04 09:00","2023-12-06 18:00","연속"]
[174,"경남","직할","신김해S/S CB 7171","신김해S/S 신김해-신마산#2T/L(7171) GIS 조작시험","신김해S/S 신김해-신마산#2T/L(7171) GIS 조작시험","2023-12-01 09:00","2023-12-01 14:00","2023-12-01 09:00","2023-12-01 14:00","연속"]
[175,"경남","진주","의령산청양수#1 T/L","345lkV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#1T/L측 수직,수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.1~130 (345kV 의령-하동화력 T/L과 병가 구간 No.112~129)","2023-12-01 07:00","2023-12-15 18:00","2023-12-01 07:00","2023-12-15 18:00","매일"]
[176,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#2T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.134~151","2023-12-03 07:00","2023-12-03 18:00","취소","취소","연속"]
[177,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#1T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.134~151","2023-12-10 07:00","2023-12-10 18:00","취소","취소","연속"]
[178,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#1T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.134~151","2023-12-17 07:00","2023-12-17 18:00","취소","취소","연속"]
[179,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#1T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.134~151","2023-12-24 07:00","2023-12-24 18:00","취소","취소","연속"]
[180,"경남","진주","의령산청양수#2 T/L","345lkV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#2T/L측 수직,수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.1~130 (345kV 의령-하동화력 T/L과 병가 구간 No.112~129)","2023-12-16 07:00","2023-12-29 18:00","2023-12-16 07:00","2023-12-29 18:00","매일"]
[181,"경남","통영","신고성S/S #2 M.Tr","신고성S/S 345kV #2M.Tr C상 H1 부싱절연유 채유","신고성S/S 345kV #2M.Tr C상 H1 부싱절연유 채유","2023-12-01 10:00","2023-12-01 18:00","2023-12-01 10:00","2023-12-01 18:00","연속"]
[182,"경남","함안","북경남S/S CB 7700","북경남S/S 345kV #5,7Sh.R 교체공사","345kV #5,7Sh.R 철거 및 설치 × 2대 345kV GIB 개조 × 1식 기기기초 보강 × 1식 기타 부대공사 × 1식","2023-12-04 09:00","2023-12-06 18:00","2023-12-07 09:00","2023-12-09 09:00","연속"]
[183,"경남","함안","북경남S/S CB 7B71","북경남S/S 345kV #5,7Sh.R 교체공사","345kV #5,7Sh.R 철거 및 설치 × 2대 345kV GIB 개조 × 1식 기기기초 보강 × 1식 기타 부대공사 × 1식","2023-12-04 09:00","2023-12-06 18:00","2023-12-04 09:00","2023-12-06 18:00","연속"]
[184,"경남","함안","신옥천북경남 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 북경남-서대구T/L 수평 추락방지장치 설치공사(345kV 신옥천-북경남T/L 병가선로)(안전확보)","2023-12-04 07:00","2023-12-08 18:00","2023-12-04 07:00","2023-12-08 18:00","연속"]
[185,"경남","함안","북경남S/S CB 7B00","북경남S/S 345kV #5,7Sh.R 교체공사","345kV #5,7Sh.R 철거 및 설치 × 2대 345kV GIB 개조 × 1식 기기기초 보강 × 1식 기타 부대공사 × 1식","2023-12-04 09:00","2023-12-06 18:00","2023-12-04 09:00","2023-12-06 18:00","연속"]
[186,"경남","함안","북경남S/S #5 Sh.R CB","북경남S/S 345kV #5,7Sh.R 교체공사","345kV #5,7Sh.R 철거 및 설치 × 2대 345kV GIB 개조 × 1식 기기기초 보강 × 1식 기타 부대공사 × 1식","2023-12-04 09:00","2023-12-06 18:00","2023-12-07 09:00","2023-12-09 09:00","연속"]
[187,"경남","함안","북경남S/S CB 7771","북경남S/S 345kV #5,7Sh.R 교체공사","345kV #5,7Sh.R 철거 및 설치 × 2대 345kV GIB 개조 × 1식 기기기초 보강 × 1식 기타 부대공사 × 1식","2023-12-04 09:00","2023-12-06 18:00","2023-12-07 09:00","2023-12-09 09:00","연속"]
[188,"경남","함안","북경남S/S #7 Sh.R CB","북경남S/S 345kV #5,7Sh.R 교체공사","345kV #5,7Sh.R 철거 및 설치 × 2대 345kV GIB 개조 × 1식 기기기초 보강 × 1식 기타 부대공사 × 1식","2023-12-04 09:00","2023-12-06 18:00","2023-12-04 09:00","2023-12-06 18:00","연속"]
[189,"경남","함안","신마산신김해#2 T/L","OPGW 항공장애표시구 설치공사","항공장애표시구 211개 설치","2023-12-04 07:00","2023-12-04 18:00","2023-12-07 07:00","2023-12-07 18:00","연속"]
[190,"경남","함안","신마산신김해#2 T/L","154kV 진례-진영#2T/L 정밀점검 관련 안전이격거리 확보","1. 154kV 진례-진영#2T/L 1호~4호 정밀점검 2. 154kV 진례-진영#2T/L 5호~6호 피뢰기 아킹혼 철거 3. 안전이격거리 확보","2023-12-08 09:00","2023-12-08 18:00","2023-12-08 09:00","2023-12-08 18:00","연속"]
[191,"경북",null,"한울N/P #1 S.Tr (CB 7300, 7372)","한울1호기 제 25차 계획예방정비 * 조작차단기: 7300, 7372","○  비상보조변압기 점검","2023-12-14 14:00","2023-12-27 16:00","2023-12-14 14:00","2023-12-27 16:00","연속"]
[192,"부산울산",null,"고리N/P #1호기 주변압기 (CB 7200, 7272)","고리1호기 제3차 영구정지 정기검사 * 조작차단기 : CB 7200, 7272","○ 주변압기 고압부싱 교체 및 정밀점검 ○ 갑종 디지털 보호계전기 교체 ○ 고리1호기-통합스위치야드 간 접지망 연계 ○ 수전전력 전력량계 신설","2023-12-21 09:00","2024-12-22 18:00","2023-12-21 09:00","2024-12-22 18:00","연속"]
[193,"광주전남",null,"한빛N/P #3호기 주변압기 (CB 7771, 7700)","한빛3호기 19차 계획예방정비 수행 * 조작차단기 : PCB 7700, 7771","○ 주변압기(C상) 내부정밀점검","2023-12-22 10:00","2024-02-07 23:59","2023-12-22 10:00","2024-02-07 23:59","연속"]

{"sheet":"154설비","index":2,"n_rows":329,"n_cols":11,"rows_kept":329,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2023년도 12월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","구의광장#1 T/L","2023년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2023-12-05 10:00","2023-12-05 17:00","취소","취소","연속"]
[2,"서울","성동","천호구의#2 T/L","2023년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2023-12-06 10:00","2023-12-06 17:00","취소","취소","연속"]
[3,"서울","성동","성동휘경#1 T/L","2023년 성동P/O 변전정비회사 총액공사","154kV GIS 보통점검","2023-10-26 09:00","2023-10-26 18:00","2023-12-07 09:00","2023-12-07 18:00","연속"]
[4,"서울","성동","성동휘경#2 T/L","2023년 성동P/O 변전정비회사 총액공사","154kV GIS 조작시험","2023-10-27 09:00","2023-10-27 18:00","2023-12-08 09:00","2023-12-08 18:00","연속"]
[5,"서울","성동","구의광장#1 T/L","구의S/S 154kV 장기사용 GIS 교체공사","○ 구의S/S 구의-광장#2 T/L, BUS TIE 무부하가압","2023-12-12 15:00","2023-12-13 15:00","2023-12-09 09:00","2023-12-10 18:00","연속"]
[6,"서울","성동","천호구의#1 T/L","구의S/S 154kV 장기사용 GIS 교체공사","○ 구의S/S 구의-광장#2 T/L, BUS TIE 무부하가압 모선전환","2023-12-13 09:00","2023-12-13 15:00","2023-12-10 09:00","2023-12-10 13:00","연속"]
[7,"서울","성동","천호구의#2 T/L","구의S/S 154kV 장기사용 GIS 교체공사","○ 구의S/S 구의-광장#2 T/L, BUS TIE 무부하가압 모선전환","2023-12-13 09:00","2023-12-13 15:00","2023-12-10 13:00","2023-12-10 18:00","연속"]
[8,"서울","성동","창동쌍문#2 T/L","창동S/S 154kV 장기사용 GIS 교체공사","창동S/S 154kV GIS 교체 × 6CCT - 2차분 #1BUS 무부하가압 시험가압선로","2023-12-13 09:00","2023-12-14 18:00","취소","취소","연속"]
[9,"서울","성동","창동S/S #2 BUS","창동S/S 154kV 장기사용 GIS 교체공사","창동S/S 154kV 장기사용 GIS 교체공사 2차분 설치 - 상계창동#2T/L, #2M.Tr 1차, #1-2BUS PT&ES","2023-12-10 09:00","2023-12-22 18:00","2023-12-10 09:00","2023-12-22 18:00","연속"]
[10,"서울","성동","창동쌍문#2 T/L","창동S/S 154kV 장기사용 GIS 교체공사","창동S/S 154kV GIS 교체 × 6CCT - 2차분 #2BUS 무부하가압 시험가압선로(최종가압)","2023-12-21 09:00","2023-12-22 18:00","취소","취소","연속"]
[11,"서울","성동","방학창동#2 T/L","창동S/S 154kV 장기사용 GIS 교체공사","창동S/S 154kV GIS 교체 : 상계창동#2T/L, #2M.Tr 1차, BUS PT&ES : #2BUS 무부하가압 시험가압선로","2023-12-21 09:00","2023-12-22 18:00","2023-12-21 09:00","2023-12-22 18:00","연속"]
[12,"서울","성동","상계창동#1 T/L","창동S/S 154kV 장기사용 GIS 교체공사(전문)","상계창동#2T/L, #2M.Tr 1차, BUS PT&ES GIS 교체(2차분) - #2BUS 무부하가압 시험가압선로","2023-12-21 09:00","2023-12-22 18:00","취소","취소","연속"]
[13,"서울","성동","상계창동#1 T/L","창동S/S 154kV 장기사용 GIS 교체공사(전문)","상계창동#2T/L, #2M.Tr 1차, BUS PT&ES GIS 교체(2차분) - #1BUS 무부하가압 시험가압선로","2023-12-13 09:00","2023-12-14 18:00","취소","취소","연속"]
[14,"서울","성동","방학창동#2 T/L","창동S/S 154kV 장기사용 GIS 교체공사","창동S/S 154kV GIS 교체 : 상계창동#2T/L, #2M.Tr 1차, BUS PT&ES : #1BUS 무부하가압 시험가압선로","2023-12-13 09:00","2023-12-14 18:00","2023-12-08 09:00","2023-12-09 18:00","연속"]
[15,"서울","중부","녹번세종로 T/L","154kV 녹번세종로T/L 누유 긴급보수 공사","154kV 녹번세종로T/L JB#5~14 구간 B상 누유관련 추가보수작업","2023-12-01 09:00","2023-12-01 18:00","2023-12-01 09:00","2023-12-01 18:00","연속"]
[16,"서울","중부","동빙고반포#2 T/L","OF케이블 절연유 채유","동빙고반포#2T/L OF케이블 절연유분석 시료 채취","2023-12-05 09:00","2023-12-05 15:00","2023-12-04 14:00","2023-12-04 18:00","연속"]
[17,"서울","중부","동빙고반포#1 T/L","OF케이블 절연유 채유","동빙고반포#1T/L OF케이블 절연유분석 시료 채취","2023-12-04 09:00","2023-12-04 14:00","2023-12-04 09:00","2023-12-04 14:00","연속"]
[18,"서울","중부","상암등촌#2 T/L","2023년 가공송전선로 순시점검 위탁공사","154kV 상암-등촌T/L No.7(염창C/T) 인근 지장수목 전지","2023-12-01 13:00","2023-12-01 18:00","취소","취소","연속"]
[19,"서울","중부","상암등촌#1 T/L","2023년 가공송전선로 순시점검 위탁공사","154kV 상암-등촌T/L No.7(염창C/T) 인근 지장수목 전지","2023-12-01 08:00","2023-12-01 13:00","취소","취소","연속"]
[20,"서울","중부","중부용산#2 T/L","OF케이블 절연유 채유","중부용산#2T/L OF케이블 절연유분석 시료 채취","2023-12-01 09:00","2023-12-01 18:00","취소","취소","연속"]
[21,"서울","직할","종로서소문 T/L","154kV 종로서소문T/L EBG 가스 채취밸브 취부","154kV종로서소문T/L EBG 가스 채취밸브 취부","2023-12-04 09:00","2023-12-07 18:00","2023-12-04 09:00","2023-12-07 18:00","연속"]
[22,"남서울","강남","신양재신사#1 T/L","22-23년도 강남전력지사 변전협력회사 총액공사","- 신양재-신사#1T/L 보호반 43PDA 점검","2023-12-01 09:00","2023-12-01 18:00","취소","취소","연속"]
[23,"남서울","영등포","천왕구로#1 T/L","154kV 천왕-구로T/L 절연유 보충","○154kV 천왕-구로T/L 절연유 보충","2023-12-05 09:00","2023-12-05 14:00","2023-12-05 09:00","2023-12-05 14:00","연속"]
[24,"남서울","영등포","천왕구로#2 T/L","154kV 천왕-구로T/L 절연유 보충","○154kV 천왕-구로T/L 절연유 보충","2023-12-05 14:00","2023-12-05 18:00","2023-12-05 14:00","2023-12-05 18:00","연속"]
[25,"남서울","영등포","상암등촌#1 T/L","154kV 상암-등촌T/L 절연유 보충","○154kV 상암-등촌T/L 절연유 보충","2023-12-03 09:00","2023-12-03 14:00","2023-12-03 09:00","2023-12-03 14:00","연속"]
[26,"남서울","영등포","상암등촌#2 T/L","154kV 상암-등촌T/L 절연유 보충","○154kV 상암-등촌T/L 절연유 보충","2023-12-03 14:00","2023-12-03 18:00","2023-12-03 14:00","2023-12-03 18:00","연속"]
[27,"남서울","영등포","천왕오류#2 T/L","154kV 천왕-오류T/L 절연유 채유","○154kV 천왕-오류T/L 절연유 채유","2023-12-07 14:00","2023-12-07 18:00","취소","취소","연속"]
[28,"남서울","영등포","천왕오류#1 T/L","154kV 천왕-오류T/L 절연유 채유","○154kV 천왕-오류T/L 절연유 채유","2023-12-07 09:00","2023-12-07 14:00","취소","취소","연속"]
[29,"인천","김포","경서양촌#2 T/L","검단3구역 전력구 운영시스템 설치공사","-CCTV 및 부분방전 측정단자함, ILS, 다기능진단장치, 출입자 감시·제어, 부대설비 제어 등 설치 등","2023-12-06 09:00","2023-12-07 18:00","2023-12-06 09:00","2023-12-07 18:00","연속"]
[30,"인천","김포","신경서경서#3 T/L","경서S/S 154kV 신경서-경서#3T/L IED 정정","경서S/S 154kV 신경서-경서#3T/L IED 시각동기화","2023-12-01 13:00","2023-12-01 18:00","2023-12-01 13:00","2023-12-01 18:00","연속"]
[31,"인천","김포","경서양촌#1 T/L","검단3구역 전력구 운영시스템 설치공사","-CCTV 및 부분방전 측정단자함, ILS, 다기능진단장치, 출입자 감시·제어, 부대설비 제어 등 설치 등","2023-12-04 09:00","2023-12-05 18:00","2023-12-04 09:00","2023-12-05 18:00","연속"]
[32,"인천","부평","송현포스코CC#2 T/L","154kV 송현-포스코CCT/L 추락방지시설 설치공사","- 추락방지시설 설치 - 항공구 탈락개소 보강","2023-12-18 07:00","2023-12-21 18:00","취소","취소","연속"]
[33,"인천","부평","송현포스코CC#1 T/L","154kV 송현-포스코CCT/L 추락방지시설 설치공사","- 추락방지시설 설치 - 항공구 탈락개소 보강","2023-12-13 07:00","2023-12-16 18:00","취소","취소","연속"]
[34,"인천","부평","신가좌S/S SEC CB 60610","신가좌S/S 154kV #60-#61 SEC CB 보통점검","신가좌S/S 154kV #60-#61 SEC CB 보통점검","2023-12-08 09:00","2023-12-08 12:00","2023-12-08 09:00","2023-12-08 12:00","연속"]
[35,"인천","부평","신가좌S/S SEC CB 65660","신가좌S/S 154kV #65-#66 SEC CB 보통점검","신가좌S/S 154kV #65-#66 SEC CB 보통점검","2023-12-08 12:00","2023-12-08 18:00","2023-12-08 12:00","2023-12-08 18:00","연속"]
[36,"인천","부평","신가좌S/S SEC CB 66670","신가좌S/S 154kV #66-#67 SEC CB 보통점검","신가좌S/S 154kV #66-#67 SEC CB 보통점검","2023-12-11 09:00","2023-12-11 18:00","2023-12-11 09:00","2023-12-11 18:00","연속"]
[37,"인천","부평","인천C/C 현대제철#2T/L CB","154kV 현대제철T/L 추락방지시설 설치공사","- 추락방지시설 설치","2023-12-18 07:00","2023-12-21 18:00","취소","취소","연속"]
[38,"인천","부평","인천C/C 현대제철#1T/L CB","154kV 현대제철T/L 추락방지시설 설치공사","- 추락방지시설 설치","2023-12-13 07:00","2023-12-16 18:00","취소","취소","연속"]
[39,"인천","부평","신가좌인천#3 T/L","154kV 신가좌인천#3T/L GIS 보통점검","154kV 신가좌인천#3T/L GIS 보통점검","2023-12-09 09:00","2023-12-09 18:00","2023-12-09 09:00","2023-12-09 18:00","연속"]
[40,"인천","부평","남인천학익#1 T/L","154kV 남인천-학익#1T/L SA혼용화 / 조작시험","154kV 남인천-학익#1T/L SA혼용화 / 조작시험","2023-12-01 09:00","2023-12-01 18:00","취소","취소","연속"]
[41,"인천","부평","남인천학익#2 T/L","학익S/S 154kV 남인천학익#2 T/L GIS SA 혼용화","학익S/S 154kV 남인천학익#2 T/L GIS SA 혼용화","2023-12-02 09:00","2023-12-02 18:00","취소","취소","연속"]
[42,"인천","시흥","신광명소래 T/L","소래S/S 154kV 신광명소래 T/L GIS 전자변 교체","소래S/S 154kV 신광명소래 T/L GIS 전자변 교체","2023-12-05 09:00","2023-12-05 18:00","취소","취소","연속"]
[43,"인천","시흥","신시흥S/S CB 6400","신시흥#2S/S 154kV #63-#68 BUS TIE GIS 누기점검","신시흥#2S/S 154kV #63-#68 BUS TIE GIS 누기점검(6400)","2023-12-05 09:00","2023-12-05 18:00","2023-12-05 09:00","2023-12-05 18:00","연속"]
[44,"인천","시흥","신시흥S/S CB 6300","신시흥#2S/S 154kV #62#67 BUS TIE GIS 누기점검","신시흥#2S/S 154kV #62-#67 BUS TIE GIS 누기점검(6300)","2023-12-04 09:00","2023-12-04 18:00","2023-12-04 09:00","2023-12-04 18:00","연속"]
[45,"인천","직할","임학계양#2 T/L","EBG 보강공사","대한전선제 EBG 가스채취밸브 설치 및 스프링유니트 점검","2023-12-05 09:00","2023-12-05 18:00","2023-12-05 09:00","2023-12-05 18:00","연속"]
[46,"인천","직할","임학계양#1 T/L","EBG 보강공사","대한전선제 EBG 가스채취밸브 설치 및 스프링유니트 점검","2023-12-06 09:00","2023-12-06 18:00","2023-12-06 09:00","2023-12-06 18:00","연속"]
[47,"경기북부","고양","월롱S/S #2 BUS","154kV 월롱S/S #1,2M.Tr 증설공사","154kV 월롱S/S #1,2M.Tr용 170kV GIS 설치 - 모선연장 및 #2M.Tr용 기설 모선 대체 - #2BUS CB, DS부 조립","2023-12-04 09:00","2023-12-15 18:00","2023-12-04 09:00","2023-12-15 18:00","연속"]
[48,"경기북부","구리","청평HP의암HP T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","추락방지시설 설치공사 : 청평HP~No.32","2023-12-04 07:00","2023-12-07 18:00","2023-12-11 07:00","2023-12-05 18:00","매일"]
[49,"경기","군포","마도사강#2 T/L","154kV 화성-장덕T/L OPGW 증설공사","* OPGW 증설(OP-S-L24→OP-S-L48) 17.991km * 광케이블 증설(FOFC-24C→FOFC-48C) 0.638km * 항공장애표시구 교체 71개 * 광코어 접속, 광케이블 최종시험 및 기타 부대공사 1식","2023-12-16 07:00","2023-12-17 18:00","취소","취소","연속"]
[50,"경기","군포","마도사강#2 T/L","154kV 화성-장덕T/L OPGW 증설공사","* OPGW 증설(OP-S-L24→OP-S-L48) 17.991km * 광케이블 증설(FOFC-24C→FOFC-48C) 0.638km * 항공장애표시구 교체 71개 * 광코어 접속, 광케이블 최종시험 및 기타 부대공사 1식","2023-12-09 07:00","2023-12-11 18:00","취소","취소","연속"]
[51,"경기","군포","마도사강#2 T/L","154kV 화성-장덕T/L OPGW 증설공사","* OPGW 증설(OP-S-L24→OP-S-L48) 17.991km * 광케이블 증설(FOFC-24C→FOFC-48C) 0.638km * 항공장애표시구 교체 71개 * 광코어 접속, 광케이블 최종시험 및 기타 부대공사 1식","2023-12-02 07:00","2023-12-03 18:00","2023-12-02 07:00","2023-12-03 18:00","연속"]
[52,"경기","군포","마도사강#2 T/L","154kV 화성-장덕T/L OPGW 증설공사","* OPGW 증설(OP-S-L24→OP-S-L48) 17.991km * 광케이블 증설(FOFC-24C→FOFC-48C) 0.638km * 항공장애표시구 교체 71개 * 광코어 접속, 광케이블 최종시험 및 기타 부대공사 1식","2023-12-22 07:00","2023-12-24 18:00","취소","취소","연속"]
[53,"경기","군포","화성마도 T/L","154kV 화성-장덕T/L OPGW 증설공사","* OPGW 증설(OP-S-L24→OP-S-L48) 17.991km * 광케이블 증설(FOFC-24C→FOFC-48C) 0.638km * 항공장애표시구 교체 71개 * 광코어 접속, 광케이블 최종시험 및 기타 부대공사 1식","2023-12-22 07:00","2023-12-24 18:00","취소","취소","연속"]
[54,"경기","군포","목내성곡#1 T/L","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023-12-04 09:00","2023-12-04 14:00","2023-12-04 09:00","2023-12-04 14:00","연속"]
[55,"경기","군포","성곡S/S CB 6100","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023-12-04 14:00","2023-12-04 18:00","2023-12-04 14:00","2023-12-04 18:00","연속"]
[56,"경기","군포","조암구문천#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 5기","2023-12-03 07:00","2023-12-03 18:00","취소","취소","연속"]
[57,"경기","군포","수촌조암#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 11기","2023-12-03 07:00","2023-12-03 18:00","취소","취소","연속"]
[58,"경기","군포","수촌조암#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 11기","2023-12-02 07:00","2023-12-02 18:00","취소","취소","연속"]
[59,"경기","군포","조암구문천#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 5기","2023-12-02 07:00","2023-12-02 18:00","취소","취소","연속"]
[60,"경기","군포","성곡중시화 T/L","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023-12-08 09:00","2023-12-08 18:00","2023-12-08 09:00","2023-12-08 18:00","연속"]
[61,"경기","동부","곤지암이천#1 T/L","22-23 동부전력지사 송전협력회사 총액공사","수평 추락방지장치 설치공사, 29~53호","2023-12-04 08:00","2023-12-07 18:00","취소","취소","연속"]
[62,"경기","동부","곤지암이천#2 T/L","22-23 동부전력지사 송전협력회사 총액공사","수평 추락방지장치 설치공사, 29~53호","2023-12-11 08:00","2023-12-14 18:00","취소","취소","연속"]
[63,"경기","동부","오포모현#1 T/L","345kV 신용인-동서울 등 16개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 No.4 ~ 26 (2회선 철탑 17기, 4회선 철탑 1기)","2023-12-04 08:00","2023-12-05 18:00","2023-12-04 08:00","2023-12-05 18:00","연속"]
[64,"경기","동부","모현용인#1 T/L","345kV 신용인-동서울 등 16개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 No.1 ~ 51 (2회선 철탑 32기, 4회선 철탑 1기)","2023-12-09 08:00","2023-12-10 18:00","2023-12-09 08:00","2023-12-10 18:00","연속"]
[65,"경기","동부","오포모현#2 T/L","345kV 신용인-동서울 등 16개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 No.4 ~ 26 (2회선 철탑 17기, 4회선 철탑 1기)","2023-12-06 08:00","2023-12-07 18:00","2023-12-06 08:00","2023-12-07 18:00","연속"]
[66,"경기","동부","모현용인#1 T/L","345kV 신용인-동서울 등 16개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 No.1 ~ 51 (2회선 철탑 32기, 4회선 철탑 1기)","2023-12-02 08:00","2023-12-03 18:00","2023-12-02 08:00","2023-12-03 18:00","연속"]
[67,"경기","동부","모현용인#2 T/L","345kV 신용인-동서울 등 16개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 No.1 ~ 51 (2회선 철탑 32기, 4회선 철탑 1기)","2023-12-16 08:00","2023-12-17 18:00","2023-12-16 08:00","2023-12-17 18:00","연속"]
[68,"경기","동부","모현용인#1 T/L","345kV 신용인-동서울 등 16개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 No.1 ~ 51 (2회선 철탑 32기, 4회선 철탑 1기)","2023-12-23 08:00","2023-12-23 13:00","취소","취소","연속"]
[69,"경기","동부","오포모현#2 T/L","345kV 신용인-동서울 등 16개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 No.4 ~ 26 (2회선 철탑 17기, 4회선 철탑 1기)","2023-12-23 08:00","2023-12-23 13:00","취소","취소","연속"]
[70,"경기","동부","모현용인#2 T/L","345kV 신용인-동서울 등 16개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 No.1 ~ 51 (2회선 철탑 32기, 4회선 철탑 1기)","2023-12-23 13:00","2023-12-23 18:00","취소","취소","연속"]
[71,"경기","동부","오포모현#1 T/L","345kV 신용인-동서울 등 16개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 No.1 ~ 51 (2회선 철탑 32기, 4회선 철탑 1기)","2023-12-23 13:00","2023-12-23 18:00","취소","취소","연속"]
[72,"경기","성남","오천율현#1 T/L","22-23년 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사","2023-12-11 08:00","2023-12-11 18:00","2023-12-11 08:00","2023-12-11 18:00","연속"]
[73,"경기","성남","오천율현#2 T/L","22-23년 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사","2023-12-12 08:00","2023-12-12 18:00","2023-12-12 08:00","2023-12-12 18:00","연속"]
[74,"경기","성남","신용인용인#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(4회선 구간)","2023-12-01 08:00","2023-12-01 18:00","2023-12-01 08:00","2023-12-01 18:00","연속"]
[75,"경기","성남","신용인동백#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(4회선 구간)","2023-12-01 08:00","2023-12-01 12:00","2023-12-01 08:00","2023-12-01 12:00","연속"]
[76,"경기","성남","신용인기흥#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(4회선 구간)","2023-12-01 12:00","2023-12-01 18:00","2023-12-01 12:00","2023-12-01 18:00","연속"]
[77,"경기","성남","신용인기흥#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(4회선 구간)","2023-12-08 08:00","2023-12-08 14:00","2023-12-08 08:00","2023-12-08 14:00","연속"]
[78,"경기","직할","의왕동안양#1 T/L","2023년 가공송전 순시점검 위탁공사","154kV 의왕동안양#1T/L 정밀점검","2023-12-07 08:00","2023-12-07 18:00","2023-12-07 08:00","2023-12-07 18:00","연속"]
[79,"경기","직할","남수원발안#2 T/L","2022-23년 경기본부 직할 변전협력회사 총액공사","발안S/S 남수원-발안#2T/L GIS 보통점검","2023-12-01 14:00","2023-12-01 18:00","2023-12-01 14:00","2023-12-01 18:00","연속"]
[80,"경기","직할","발안향남#1 T/L","2022-23년 경기본부 직할 변전협력회사 총액공사","발안,향남S/S 발안-향남1T/L GIS 보통점검","2023-12-02 14:00","2023-12-02 18:00","2023-12-02 14:00","2023-12-02 18:00","연속"]
[81,"경기","직할","발안향남#2 T/L","2022-23년 경기본부 직할 변전협력회사 총액공사","발안,향남S/S 발안-향남2T/L GIS 보통점검","2023-12-02 09:00","2023-12-02 14:00","2023-12-02 09:00","2023-12-02 14:00","연속"]
[82,"경기","직할","남수원발안#1 T/L","2022-23년 경기본부 직할 변전협력회사 총액공사","발안S/S 남수원-발안#1T/L GIS 보통점검","2023-12-01 09:00","2023-12-01 14:00","2023-12-01 09:00","2023-12-01 14:00","연속"]
[83,"경기","직할","율전의왕#2 T/L","2023년 가공송전 순시점검 위탁공사","안전이격확보(의왕동안양T/L 정밀점검)","2023-12-07 08:00","2023-12-07 18:00","2023-12-07 08:00","2023-12-07 18:00","연속"]
[84,"경기","직할","동수원우만#2 T/L","2023년 가공송전 순시점검 위탁공사","철탑 추락방지장치 설치공사 및 국산불량애자 교체","2023-12-06 08:00","2023-12-06 18:00","2023-12-06 08:00","2023-12-06 18:00","연속"]
[85,"경기","평택","고덕송탄#2 T/L","23년 평택전력 변전협력회사 총액공사","고덕S/S 고덕-송탄#2T/L GIS 보통점검","2023-12-02 09:00","2023-12-02 18:00","2023-12-02 09:00","2023-12-02 18:00","연속"]
[86,"경기","평택","고덕진위#2 T/L","오산-평택T/L 등 13개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치","2023-12-04 07:00","2023-12-07 18:00","2023-12-04 07:00","2023-12-07 18:00","연속"]
[87,"경기","평택","소사벌안성 T/L","23-24년 지중송전설비 위탁정비공사(평택전력지사)","소사벌C/T EBA 절연유 채유","2023-12-01 09:00","2023-12-02 18:00","취소","취소","연속"]
[88,"경기","평택","오산향남#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사 및 국산불량애자 교체","2023-12-23 07:00","2023-12-24 18:00","2023-12-23 07:00","2023-12-24 18:00","연속"]
[89,"경기","평택","오산향남#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사 및 국산불량애자 교체","2023-12-16 07:00","2023-12-17 18:00","2023-12-16 07:00","2023-12-17 18:00","연속"]
[90,"강원","직할","춘천북춘천#2 T/L","2022~2023년 강원본부 직할 가공송전협력회사 총액공사","추락방지장치 설치","2023-12-04 07:30","2023-12-09 18:00","2023-12-04 07:30","2023-12-09 18:00","매일"]
[91,"강원","직할","화천S/S CB 6100","22~23년 강원본부 직할 변전협력회사 총액공사","화천S/S 154kV 모선보호반 대체","2023-12-04 10:00","2023-12-07 18:00","2023-12-04 10:00","2023-12-07 18:00","연속"]
[92,"강원","태백","태백영월에코윈드 T/L","2023년 태백전력지사 변전협력회사 총액공사","영월에코윈드S/Y 154kV 태백영월에코윈드 T/L GIS 초기점검","2023-12-01 09:00","2023-12-01 18:00","취소","취소","연속"]
[93,"강원","태백","태백고한 T/L","2023년 태백전력지사 변전협력회사 총액공사","154kV 태백고한 T/L PNL 대체공사","2023-12-12 09:00","2023-12-15 18:00","2023-12-12 09:00","2023-12-15 18:00","연속"]
[94,"충북","직할","신진천진천#1 T/L","22-23년 충북직할 변전협력회사 총액공사","- 신진천S/S 154kV GIS 보통점검","2023-12-19 09:00","2023-12-19 18:00","취소","취소","연속"]
[95,"충북","직할","신진천S/S SEC CB 65660","22-23년 충북직할 변전협력회사 총액공사","- 신진천S/S 154kV GIS 보통점검","2023-12-11 09:00","2023-12-11 18:00","취소","취소","연속"]
[96,"충북","직할","신진천S/S SEC CB 61620","22-23년 충북직할 변전협력회사 총액공사","신진천S/S 154kV #61-62 SEC GIS 보통점검 전자변교체","2023-12-12 09:00","2023-12-12 18:00","취소","취소","연속"]
[97,"충북","직할","신진천S/S CB 6200","22-23년 충북직할 변전협력회사 총액공사","신진천S/S 154kV #61-66 TIE GIS 보통점검","2023-12-13 09:00","2023-12-13 18:00","2023-12-01 09:00","2023-12-01 18:00","연속"]
[98,"충북","직할","신진천S/S CB 6100","22-23년 충북직할 변전협력회사 총액공사","장기미동작 차단기 조작시험","2023-12-14 09:00","2023-12-14 18:00","취소","취소","연속"]
[99,"충북","직할","신진천진천#2 T/L","22-23년 충북직할 변전협력회사 총액공사","신진천S/S 154kV 신진천-진천 #2T/L GIS 노후 전자변 교체","2023-12-15 09:00","2023-12-15 18:00","취소","취소","연속"]
[100,"충북","직할","신진천S/S SEC CB 66670","22-23년 충북직할 변전협력회사 총액공사","신진천S/S 154kV #66-#67 SEC GIS 보통점검 차단부 전자변 교체","2023-12-07 09:00","2023-12-07 18:00","취소","취소","연속"]
[101,"충북","충주","감곡S/S CB 6100","22-23년 충주전력지사 변전정비 총액공사","감곡S/S 154kV #6100 BUS-TIE GIS 보통점검","2023-12-01 09:00","2023-12-01 14:00","취소","취소","연속"]
[102,"충북","충주","신제천제천#1 T/L","22-23년 충주전력지사 변전정비 총액공사","신제천S/S 154kV 신제천-제천#1T/L LA 보통점검","2023-12-05 10:00","2023-12-05 14:00","취소","취소","연속"]
[103,"충북","충주","신제천S/S SEC CB 61620","22-23년 충주전력지사 변전정비 총액공사","신체천S/S 154kV #61-62 B/S GIS 보통점검","2023-12-11 09:00","2023-12-11 14:00","취소","취소","연속"]
[104,"충북","충주","신제천S/S SEC CB 66670","22-23년 충주전력지사 변전정비 총액공사","신제천S/S 154kV #66-67 B/S GIS 보통점검","2023-12-11 14:00","2023-12-11 18:00","취소","취소","연속"]
[105,"충북","충주","신충주음성#1 T/L","22-23년 충주전력지사 변전정비 총액공사","음성S/S 154kV 신충주-음성#1T/L GIS 초기점검 및 LA 보통점검","2023-12-01 09:00","2023-12-01 14:00","취소","취소","연속"]
[106,"충북","충주","신충주음성#2 T/L","22-23년 충주전력지사 변전정비 총액공사","음성S/S 154kV 신충주-음성#2T/L GIS 초기점검 및 LA 보통점검","2023-12-01 14:00","2023-12-01 18:00","취소","취소","연속"]
[107,"대전세종충남","대전","부여논산#1 T/L","[송전] 154kV 논산-은진T/L 정밀점검","[송전] 154kV 논산-은진T/L 정밀점검 안전거리 확보차","2023-12-04 08:00","2023-12-05 18:00","2023-12-04 08:00","2023-12-05 18:00","매일"]
[108,"대전세종충남","대전","논산은진#2 T/L","[송전] 154kV 논산-은진T/L 정밀점검","[송전] 154kV 논산-은진T/L 정밀점검","2023-12-04 08:00","2023-12-11 18:00","2023-12-04 08:00","2023-12-11 18:00","매일"]
[109,"대전세종충남","대전","신계룡유성#2 T/L","[송전취소시]신계룡S/S 신계룡-가수원#2T/L CVT 하자점검","[송전취소시]신계룡S/S 154kV 신계룡-가수원#2T/L CVT 하자점검","2023-12-14 09:00","2023-12-14 12:00","취소","취소","연속"]
[110,"대전세종충남","서산","대산S/S SEC CB 60610","154kV 대산S/S #4M.Tr 증설공사","#61-#66모선보호반 Feeder 증설 및 연동시험","2023-12-07 08:00","2023-12-07 18:00","취소","취소","연속"]
[111,"대전세종충남","서산","대산S/S SEC CB 65660","154kV 대산S/S #4M.Tr 증설공사","#61-#66모선보호반 Feeder 증설 및 연동시험","2023-12-07 08:00","2023-12-07 18:00","취소","취소","연속"]
[112,"대전세종충남","서산","대산S/S CB 6200","154kV 대산S/S #4M.Tr 증설공사","#61-#66모선보호반 Feeder 증설 및 연동시험","2023-12-07 08:00","2023-12-07 18:00","취소","취소","연속"]
[113,"대전세종충남","서산","대산석문#1 T/L","154kV 대산S/S #4M.Tr 증설공사","#4M.Tr 주모선 및 가공지선 연결","2023-12-06 08:00","2023-12-06 18:00","취소","취소","연속"]
[114,"대전세종충남","서산","신당진S/S SEC CB 65660","'23년 서산P/O 154kV 이하 개폐장치 보통점검","신당진S/S 154kV 65-66-0 CB","2023-12-05 10:00","2023-12-05 18:00","2023-12-05 10:00","2023-12-05 18:00","연속"]
[115,"대전세종충남","서산","신당진S/S SEC CB 60610","'23년 서산P/O 154kV 이하 개폐장치 보통점검","신당진S/S 154kV 60-61-0 CB","2023-12-04 10:00","2023-12-04 18:00","2023-12-04 10:00","2023-12-04 18:00","연속"]
[116,"대전세종충남","서산","신당진당진#1 T/L","23년 서산P/O 154kV 이하 개폐장치 보통점검","신당진S/S 154kV 신당진-당진#1T/L * 11월 휴전 취소 시","2023-12-01 10:00","2023-12-01 18:00","취소","취소","연속"]
[117,"대전세종충남","서산","태안태안화력#2 T/L","154kV 태안화력T/L 전선접속개소 전선교체공사","154kV 태안-태안화력T/L 전력선 교체공사(3개소) - No.2~6, 6~8, 11~13","2023-12-11 08:00","2023-12-15 18:00","취소","취소","연속"]
[118,"대전세종충남","서산","태안태안화력#1 T/L","154kV 태안화력T/L 전선접속개소 전선교체공사","154kV 서산-태안화력T/L 전력선 교체공사(3개소) - No.2~6, 11~13","2023-12-04 08:00","2023-12-08 18:00","취소","취소","연속"]
[119,"대전세종충남","세종","덕진대화#2 T/L","[송전]154kV 덕진-대화#2T/L 추락방지시설 설치공사","[송전]154kV 덕진-대화#2T/L 추락방지시설 설치공사 - No.9, 15 (2기)","2023-12-14 07:00","2023-12-14 12:00","2023-12-14 07:00","2023-12-14 12:00","연속"]
[120,"대전세종충남","세종","세종부강#2 T/L","(11월취소시)[변전]'23년 세종전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검 시행(11BAY)","2023-12-06 09:00","2023-12-07 18:00","취소","취소","연속"]
[121,"대전세종충남","세종","세종부강#1 T/L","(11월취소시)[변전]'23년 세종전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검 시행(11BAY)","2023-12-04 09:00","2023-12-05 18:00","취소","취소","연속"]
[122,"대전세종충남","세종","세종둔곡#1 T/L","[송전]154kV 세종-둔곡#1T/L 추락방지시설 설치공사","[송전]154kV 세종-둔곡#1T/L 추락방지시설 설치공사 - No.2~14 (13기)","2023-12-06 07:00","2023-12-11 18:00","취소","취소","매일"]
[123,"대전세종충남","세종","세종둔곡#2 T/L","[송전]154kV 세종-둔곡#2T/L 추락방지시설 설치공사","[송전]154kV 세종-둔곡#2T/L 추락방지시설 설치공사 - No.2~14 (13기)","2023-12-12 07:00","2023-12-13 18:00","2023-12-12 07:00","2023-12-13 18:00","매일"]
[124,"대전세종충남","세종","서세종조치원 T/L","[변전]2023년 세종P/O 변전협력회사 총액공사","154kV 서세종-조치원T/L C상 부싱 과열의심개소 점검","2023-12-04 10:00","2023-12-04 17:00","취소","취소","연속"]
[125,"대전세종충남","직할","부강신탄진 T/L","154kV 신탄진S/S 미래화사업 전력구 설치공사","154kV 신탄진S/S 미래화사업 전력구 설치공사","2023-12-01 08:00","2023-12-07 17:00","2023-12-01 08:00","2023-12-07 17:00","매일"]
[126,"대전세종충남","천안","서천안탕정#2 T/L","서천안-탕정#2T/L 보호배전반 성능개선","서천안-탕정#2T/L 보호배전반 성능개선","2023-12-13 09:00","2023-12-13 18:00","취소","취소","연속"]
[127,"대전세종충남","천안","서천안탕정#1 T/L","서천안-탕정#1T/L 보호배전반 성능개선","서천안-탕정#1T/L 보호배전반 성능개선","2023-12-12 09:00","2023-12-12 18:00","취소","취소","연속"]
[128,"대전세종충남","천안","아산합덕#1 T/L","아산S/S 154kV 아산-합덕#1T/L EDS부 보수","아산S/S 154kV 아산-합덕#1T/L EDS부 보수","2023-12-11 09:00","2023-12-12 18:00","취소","취소","연속"]
[129,"대전세종충남","천안","아산예산#1 T/L","(11월 취소시)154kV 아산-예산#1T/L 보호배전반 교체","아산,예산S/S 154kV 아산-예산#1T/L 보호배전반 교체","2023-12-04 09:00","2023-12-07 18:00","취소","취소","연속"]
[130,"대전세종충남","천안","아산인주#1 T/L","(11월취소시)아산,인주S/S 아산-인주#1T/L 보호반 교체","(11월취소시)아산,인주S/S 아산-인주#1T/L 보호반 교체","2023-12-04 09:00","2023-12-07 18:00","취소","취소","연속"]
[131,"대전세종충남","천안","아산예산#2 T/L","(11월 취소시)154kV 아산-예산#2T/L 보호배전반 교체","아산,예산S/S 154kV 아산-예산#2T/L 보호배전반 교체","2023-12-11 09:00","2023-12-14 18:00","취소","취소","연속"]
[132,"대전세종충남","천안","아산S/S SEC CB 65660","아산S/S 154kV 65-66 GIS 초기점검","아산S/S 154kV 65-66 GIS 초기점검","2023-12-06 09:00","2023-12-06 18:00","취소","취소","연속"]
[133,"대전세종충남","천안","아산인주#2 T/L","(11월취소시)아산,인주S/S 아산-인주#2T/L 보호반 교체","(11월취소시)아산,인주S/S 아산-인주#2T/L 보호반 교체","2023-12-11 09:00","2023-12-14 18:00","취소","취소","연속"]
[134,"대전세종충남","천안","아산S/S SEC CB 60610","아산S/S 154kV 60-61 GIS 초기점검","아산S/S 154kV 60-61 GIS 초기점검","2023-12-05 09:00","2023-12-05 18:00","취소","취소","연속"]
[135,"대전세종충남","천안","장재천안#2 T/L","(11월취소시) 154kV 장재-천안#2T/L 보호배전반 교체","장재,천안S/S 154kV 장재-천안#2T/L 보호배전반 교체","2023-12-11 09:00","2023-12-14 18:00","취소","취소","연속"]
[136,"대전세종충남","천안","장재천안#1 T/L","(11월취소시) 154kV 장재-천안#1T/L 보호배전반 교체","장재,천안S/S 154kV 장재-천안#1T/L 보호배전반 교체","2023-12-04 09:00","2023-12-07 18:00","취소","취소","연속"]
[137,"대전세종충남","천안","풍세장재#1 T/L","154kV 풍세-장재#1T/L 보호배전반 성능개선","154kV 풍세-장재#1T/L 보호배전반 성능개선","2023-12-19 09:00","2023-12-19 18:00","취소","취소","연속"]
[138,"대전세종충남","천안","풍세장재#2 T/L","154kV 풍세-장재#2T/L 보호배전반 성능개선","154kV 풍세-장재#2T/L 보호배전반 성능개선","2023-12-20 09:00","2023-12-20 18:00","취소","취소","연속"]
[139,"대전세종충남","청양","관창보령TP T/L","(11월취소시)청양P/O 변전협력회사 총액공사","(11월취소시) 154kV 관창-보령화력T/L - 관창S/S 차단기 조작시험 - 보령T/P 차단기 조작시험","2023-12-07 10:00","2023-12-07 12:00","취소","취소","연속"]
[140,"대전세종충남","청양","청양관창#1 T/L","(11월취소시)청양P/O 변전협력회사 총액공사","(11월취소시) 154kV 청양-관창#1T/L - 청양, 관창S/S 차단기 조작시험(양단) - 청양S/S LA 초기점검(A,B,C)","2023-12-06 08:00","2023-12-06 18:00","취소","취소","연속"]
[141,"대전세종충남","청양","관창보령CC T/L","(11월취소시)청양P/O 변전협력회사 총액공사","(11월 취소시)154kV 관창-보령복합T/L - 관창S/S 차단기 조작시험","2023-12-05 13:00","2023-12-05 16:00","취소","취소","연속"]
[142,"대전세종충남","청양","관창대천#2 T/L","(11월취소시)청양P/O 변전협력회사 총액공사","(11월 취소시)154kV 관창-대천#2TL - 관창S/S 차단기 조작시험","2023-12-05 10:00","2023-12-05 12:00","2023-12-05 10:00","2023-12-05 12:00","연속"]
[143,"대전세종충남","청양","관창대천#1 T/L","(11월취소시)청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","(11월 취소시)154kV 관창-대천#1T/L - 관창S/S GIS 보통점검 및 노후보조계전기 교체","2023-12-03 10:00","2023-12-04 18:00","2023-12-03 10:00","2023-12-04 18:00","연속"]
[144,"대전세종충남","청양","보령T/P CB 6100","(11월취소시)청양P/O 변전협력회사 총액공사","(11월취소시) 보령T/P 154kV 6100 BUS TIE GIS 보통점검","2023-12-04 10:00","2023-12-04 18:00","취소","취소","연속"]
[145,"대전세종충남","청양","보령TP보령CC T/L","(11월취소시)청양P/O 변전협력회사 총액공사","(11월 취소시) 154kV 보령복합T/L - 보령T/P 차단기 조작시험","2023-12-06 10:00","2023-12-06 12:00","취소","취소","연속"]
[146,"대전세종충남","청양","옥산장항#2 T/L","(11월취소시)청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","(11월 송전휴전 취소시)154kV 옥산-장항#2T/L - 장항S/S GIS 보통점검 및 노후보조계전기 교체 - 세니온제 성능개선 - 장항S/S LA초기점검(A,B,C) - 옥산S/S 차단기 조작시험","2023-12-06 10:00","2023-12-06 18:00","취소","취소","연속"]
[147,"대전세종충남","청양","신서천옥산#2 T/L","(11월취소시)청양P/O 변전협력회사 총액공사","(11월취소시)154kV 옥산-서천#2T/L - 옥산S/S 차단기 조작시험","2023-12-08 10:00","2023-12-08 14:00","2023-12-08 10:00","2023-12-08 14:00","연속"]
[148,"대전세종충남","청양","신서천옥산#1 T/L","(11월취소시)청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","(11월취소시)154kV 옥산-서천#1T/L - 옥산S/S 170kV GIS 보통점검 및 노후보조계전기 교체 - 옥산S/S LA 보통점검(A,B,C)","2023-12-07 10:00","2023-12-08 18:00","취소","취소","연속"]
[149,"대전세종충남","청양","동군산장항#1 T/L","(11월취소시)청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","(11월 취소시)154kV 동군산- 장항#1T/L - 장항S/S LA 초기점검(A,B,C) 및 CVT 초기점검 - 170kV GIS 보통점검","2023-12-05 10:00","2023-12-05 18:00","취소","취소","연속"]
[150,"대전세종충남","청양","동군산장항#2 T/L","(11월취소시)청양P/O 변전협력회사 총액공사","(11월 취소시)154kV 동군산-장항#2T/L - 장항S/S GIS 보통점검 및 CVT 보통점검","2023-12-08 10:00","2023-12-08 18:00","취소","취소","연속"]
[151,"대전세종충남","청양","청양신풍#2 T/L","(11월취소시)청양P/O 변전협력회사 총액공사","(11월취소시) 154kV 청양-신풍#2TL - 청양S/S 차단기 조작시험 및 LA 초기점검(A,B,C)","2023-12-01 08:00","2023-12-01 18:00","취소","취소","연속"]
[152,"대전세종충남","청양","청양은하#2 T/L","(11월취소시)청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","(11월취소시)154kV 청양-은하 #2T/L - 은하S/S GIS 보통점검 및 노후보조계전기 교체 - 청양S/S 차단기 조작시험 및 LA(A,B,C) 초기점검","2023-12-01 08:00","2023-12-01 18:00","취소","취소","연속"]
[153,"대전세종충남","청양","서산홍성 T/L","(11월취소시)청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","(11월취소시)154kV 서산-홍성#T/L - 170kV GIS 보통점검, LA(A,B,C) 보통점검(병행)","2023-12-01 10:00","2023-12-01 18:00","취소","취소","연속"]
[154,"전북","군산","군공S/S CB 6100","군산P/O 154kV 차단기 보통점검","군공S/S 154kV BUS-TIE 차단기 보통점검","2023-12-13 09:00","2023-12-13 14:00","2023-12-13 09:00","2023-12-13 14:00","연속"]
[155,"전북","군산","동군산군산CC#2 T/L","154kV 동군산-군산복합2T/L 차단기 보통점검","154kV 동군산-군산복합2T/L 차단기 보통점검","2023-12-26 14:00","2023-12-26 18:00","취소","취소","연속"]
[156,"전북","군산","군산C/C #2 BUS","154kV 동군산S/S-군산CC T/L 개폐장치 증설공사","170kV GIS X 2CCT (동군산 1CCT, 군산CC 1CCT)","2023-12-26 09:00","2023-12-27 10:00","2023-12-26 09:00","2023-12-27 10:00","매일"]
[157,"전북","군산","군산C/C #1 BUS","154kV 동군산S/S-군산CC T/L 개폐장치 증설공사","170kV GIS X 2CCT (동군산 1CCT, 군산CC 1CCT)","2023-12-27 10:30","2023-12-27 11:00","2023-12-27 10:30","2023-12-27 11:00","매일"]
[158,"전북","군산","군산C/C CB 6100","군산P/O 154kV GIS 보통점검","군산복합 154kV 6100 BUS-TIE GIS 보통점검","2023-12-04 09:00","2023-12-04 14:00","2023-12-04 09:00","2023-12-04 14:00","연속"]
[159,"전북","군산","동군산군산CC#1 T/L","154kV 동군산-군산복합1T/L 차단기 보통점검","154kV 동군산-군산복합1T/L 차단기 보통점검","2023-12-26 09:00","2023-12-26 14:00","취소","취소","연속"]
[160,"전북","군산","군산C/C #2 BUS","154kV 동군산S/S-군산CC T/L 개폐장치 증설공사","170kV GIS X 2CCT (동군산 1CCT, 군산CC 1CCT)","2023-12-27 10:00","2023-12-27 10:30","2023-12-27 10:00","2023-12-27 10:30","매일"]
[161,"전북","군산","군산C/C CB 6100","154kV 동군산S/S-군산CC T/L 개폐장치 증설공사","170kV GIS X 2CCT (동군산 1CCT, 군산CC 1CCT)","2023-12-28 09:00","2023-12-29 18:00","2023-12-28 09:00","2023-12-29 18:00","연속"]
[162,"전북","군산","군산서군산#2 T/L","군산P/O 차단기 보통점검공사","군산S/S 군산-서군산#2T/L GIS 보통점검","2023-12-01 14:00","2023-12-01 18:00","취소","취소","연속"]
[163,"전북","군산","군산서군산#1 T/L","군산P/O 차단기 보통점검공사","군산S/S 군산-서군산#1T/L GIS 보통점검","2023-12-01 09:00","2023-12-01 14:00","취소","취소","연속"]
[164,"전북","군산","군산S/S SEC CB 61620","군산P/O 154kV 이상 차단기 보통점검","군산S/S #61-62SEC 차단기 보통점검","2023-12-04 09:00","2023-12-04 13:00","취소","취소","연속"]
[165,"전북","군산","군산S/S #60 BUS","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-25 09:00","2023-12-26 18:00","취소","취소","연속"]
[166,"전북","군산","군산S/S #65 BUS","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-15 09:00","2023-12-25 18:00","2023-12-24 18:00","2023-12-26 18:00","연속"]
[167,"전북","군산","군산S/S #60 BUS","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-08 09:00","2023-12-15 18:00","2023-12-07 18:00","2023-12-24 18:00","연속"]
[168,"전북","군산","군산S/S #3 Sh.C CB","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-05 09:00","2023-12-26 18:00","2023-12-05 09:00","2023-12-26 18:00","연속"]
[169,"전북","군산","군산S/S CB 6100","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-05 09:00","2023-12-26 18:00","2023-12-05 09:00","2023-12-26 18:00","연속"]
[170,"전북","군산","군산이리#1 T/L","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-05 09:00","2023-12-26 18:00","2023-12-05 09:00","2023-12-26 18:00","연속"]
[171,"전북","군산","군산S/S #2 Sh.C CB","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-05 09:00","2023-12-26 18:00","2023-12-05 09:00","2023-12-26 18:00","연속"]
[172,"전북","군산","군산S/S 60-65 PT CB","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-05 09:00","2023-12-26 18:00","취소","취소","연속"]
[173,"전북","군산","군산S/S #65 BUS","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-05 09:00","2023-12-07 18:00","2023-12-05 09:00","2023-12-07 18:00","연속"]
[174,"전북","군산","군산S/S #1 Sh.C CB","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-05 09:00","2023-12-26 18:00","2023-12-05 09:00","2023-12-26 18:00","연속"]
[175,"전북","군산","군산S/S SEC CB 65660","군산P/O 154kV 이상 차단기 보통점검","군산S/S #65-66SEC 차단기 보통점검","2023-12-04 15:30","2023-12-04 18:00","취소","취소","연속"]
[176,"전북","군산","군산S/S SEC CB 60610","군산P/O 154kV 이상 차단기 보통점검","군산S/S #60-61SEC 차단기 보통점검","2023-12-04 13:00","2023-12-04 15:30","취소","취소","연속"]
[177,"전북","군산","군산S/S #61 BUS","군산S/S 170kV 장기사용 GIS 대체공사(무부하가압용)","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-25 18:00","2023-12-26 18:00","취소","취소","연속"]
[178,"전북","군산","군산영등#1 T/L","군산S/S 170kV 장기사용 GIS 대체공사(무부하가압용)","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-25 18:00","2023-12-26 18:00","취소","취소","연속"]
[179,"전북","군산","군산S/S #66 BUS","군산S/S 170kV 장기사용 GIS 대체공사(무부하가압용)","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-24 18:00","2023-12-25 18:00","취소","취소","연속"]
[180,"전북","군산","군산영등#1 T/L","군산S/S 170kV 장기사용 GIS 대체공사(무부하가압용)","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-24 18:00","2023-12-25 18:00","취소","취소","연속"]
[181,"전북","군산","군산영등#1 T/L","군산S/S 170kV 장기사용 GIS 대체공사(무부하가압용)","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-14 18:00","2023-12-15 18:00","취소","취소","연속"]
[182,"전북","군산","군산S/S #61 BUS","군산S/S 170kV 장기사용 GIS 대체공사(무부하가압용)","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-14 18:00","2023-12-15 18:00","취소","취소","연속"]
[183,"전북","군산","군산영등#1 T/L","군산S/S 170kV 장기사용 GIS 대체공사(무부하가압용)","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-07 16:00","2023-12-07 18:00","취소","취소","연속"]
[184,"전북","군산","군산S/S #66 BUS","군산S/S 170kV 장기사용 GIS 대체공사(무부하가압용)","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-12-07 16:00","2023-12-07 18:00","취소","취소","연속"]
[185,"전북","군산","군산영등#2 T/L","154kV 군산-영등#2T/L 차단기 보통점검","차단기 보통점검","2023-12-07 09:00","2023-12-07 14:00","취소","취소","매일"]
[186,"전북","군산","군산S/S SEC CB 66670","군산P/O 154kV 이상 차단기 보통점검","군산S/S #66-67SEC 차단기 보통점검","2023-12-04 13:00","2023-12-04 16:00","취소","취소","연속"]
[187,"전북","군산","군산동군산#1 T/L","154kV 동군산S/S-군산CC T/L 개폐장치 증설공사(시험가압선로)","170kV GIS X 2CCT (동군산 1CCT, 군산CC 1CCT)","2023-12-28 09:00","2023-12-29 18:00","취소","취소","연속"]
[188,"전북","군산","동군산군산복합#3 T/L CB","154kV 동군산S/S-군산CC T/L 개폐장치 증설공사","170kV GIS X 2CCT (동군산 1CCT, 군산CC 1CCT)","2023-12-28 09:00","2023-12-29 18:00","취소","취소","연속"]
[189,"전북","군산","탄소이리#1 T/L","345kV 군산-새만금 등 8개T/L 추락방지장치 설치공사","□ 공사개요 ○ 설치 철탑 : 154kV 이리-탄소#1T/L No.1~63 (관형주 제외) ○ 추락방지장치 : 수평설치(51기)","2023-12-19 09:00","2023-12-23 18:00","취소","취소","연속"]
[190,"전북","군산","탄소이리#2 T/L","345kV 군산-새만금 등 8개T/L 추락방지장치 설치공사","□ 공사개요 ○ 설치 철탑 : 154kV 이리-탄소#2T/L No.1~63 (관형주 제외) ○ 추락방지장치 : 수평설치(51기)","2023-12-24 09:00","2023-12-28 18:00","취소","취소","연속"]
[191,"전북","군산","팔봉왕궁#2 T/L","전북본부 관내 EBA 자기애관 교체공사","기설 EBA 자기애관 철거 및 폴리머애관 설치","2023-12-18 09:00","2023-12-22 18:00","취소","취소","연속"]
[192,"전북","군산","팔봉왕궁#1 T/L","전북본부 관내 EBA 자기애관 교체공사","기설 EBA 자기애관 철거 및 폴리머애관 설치","2023-12-11 09:00","2023-12-15 18:00","취소","취소","연속"]
[193,"전북","김제","정주고창#1 T/L","관내S/S 170kV GIS 보통점검","관내S/S 170kV GIS 보통점검","2023-12-18 09:00","2023-12-18 18:00","취소","취소","연속"]
[194,"전북","김제","정주고창#2 T/L","관내S/S 170kV GIS 보통점검","관내S/S 170kV GIS 보통점검","2023-12-19 09:00","2023-12-19 18:00","취소","취소","연속"]
[195,"전북","김제","신김제정공#2 T/L","정공S/S 170kV 정공-신김제#2T/L GIS 정밀점검","정공S/S 170kV 정공-신김제#2T/L GIS 정밀점검","2023-12-07 08:30","2023-12-08 18:00","취소","취소","연속"]
[196,"전북","김제","정공정주#2 T/L","정공S/S 170kV 정공-정주#2T/L GIS 보통점검","정공S/S 170kV 정공-정주#2T/L GIS 보통점검","2023-12-20 09:00","2023-12-20 18:00","취소","취소","연속"]
[197,"전북","김제","신김제정공#1 T/L","정공S/S 170kV 정공-신김제#1T/L GIS 정밀점검","정공S/S 170kV 정공-신김제#1T/L GIS 정밀점검","2023-12-05 08:30","2023-12-06 18:00","취소","취소","연속"]
[198,"전북","직할","동전주북전주#2 T/L","23년 전북직할 변전협력회사 총액공사","154kV 동전주-북전주 #2 T/L CVT 보통점검","2023-12-12 09:00","2023-12-12 18:00","2023-12-12 09:00","2023-12-12 18:00","연속"]
[199,"전북","직할","동전주북전주#1 T/L","23년 전북직할 변전협력회사 총액공사","154kV 동전주-북전주 #1 T/L CVT 보통점검","2023-12-08 09:00","2023-12-08 18:00","2023-12-08 09:00","2023-12-08 18:00","연속"]
[200,"전북","직할","북전주봉동#2 T/L","23년 전북직할 변전협력회사 총액공사","154kV 북전주-봉동 #2 T/L LA 보통점검","2023-12-07 09:00","2023-12-07 18:00","2023-12-07 09:00","2023-12-07 18:00","연속"]
[201,"광주전남","강진","강진남창#1 T/L","154kV 영신분기T/L 건설공사","□ 154kV 영신분기T/L 건설공사 ㅇ 임시선로 구성(No.53 - 가철탑 - No.54) ㅇ 용량증대 전선교체 공사(No.50~54)","2023-12-01 07:00","2023-12-04 18:00","2023-12-01 07:00","2023-12-04 18:00","연속"]
[202,"광주전남","강진","나주금천#2 T/L","세니온 보호계전기 일제 성능개선 시행(나주,금천)","세니온 보호계전기 일제 성능개선 시행 - 나주S/S 나주-금천#1,2T/L - 보호반 IED 펌웨어 업데이트","2023-12-07 14:00","2023-12-07 18:00","취소","취소","연속"]
[203,"광주전남","강진","나주금천#1 T/L","세니온 보호계전기 일제 성능개선 시행(나주,금천)","세니온 보호계전기 일제 성능개선 시행 - 나주S/S 나주-금천#1,2T/L - 보호반 IED 펌웨어 업데이트","2023-12-07 10:00","2023-12-07 14:00","취소","취소","연속"]
[204,"광주전남","강진","남창해남CS#2 T/L","2022~23년 강진전력지사 변전협력회사 총액공사","남창S/S 남창-해남CS#2T/L GIS 차단기 조작시험","2023-12-01 09:00","2023-12-01 18:00","취소","취소","연속"]
[205,"광주전남","강진","남창완도#1 T/L","154kV 남창-완도#1T/L 복도체화 건설공사","해남완도지역 신재생E 수용성강화 및 제주완도간 #3HVDC 안정적 운영을 위한 154kV 송전선로 보강","2023-12-05 09:00","2023-12-08 18:00","2023-12-05 09:00","2023-12-08 18:00","연속"]
[206,"광주전남","강진","남창해남CS#1 T/L","2022~23년 강진전력지사 변전협력회사 총액공사","남창S/S 남창-해남CS#1T/L GIS 차단기 조작시험","2023-12-04 09:00","2023-12-04 18:00","취소","취소","연속"]
[207,"광주전남","강진","남창완도#1 T/L","154kV 남창-완도1π분기T/L 건설공사","ㅁ154kV 남창-완도T/L No.42호 철탑상향(인클로징) 공사 ㅇ 송전철탑 조립(#1T/L)","2023-12-13 07:00","2023-12-28 18:00","2023-12-13 07:00","2023-12-28 18:00","연속"]
[208,"광주전남","강진","해남진도#1 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","수평추락방지장치 설치 및 고정형폴리머 점퍼지지애자 설치","2023-12-04 07:00","2023-12-04 18:00","취소","취소","매일"]
[209,"광주전남","강진","남창해남CS#2 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","수평추락방지장치 설치 및 고정형폴리머 점퍼지지애자 설치","2023-12-13 07:00","2023-12-15 18:00","취소","취소","매일"]
[210,"광주전남","강진","해남해남CS#2 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","수평 추락방지장치 설치공사","2023-12-04 07:00","2023-12-15 18:00","취소","취소","매일"]
[211,"광주전남","강진","화원진도#1 T/L","2023년도 가공송전선로 순시점검 위탁공사","154kV 화원-진도#1T/L 정밀점검","2023-12-01 08:00","2023-12-01 17:00","2023-12-01 14:00","2023-12-01 18:00","연속"]
[212,"광주전남","광주","계림승주#1 T/L","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","-BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2T/L #60BUS 신설분 무부하 가압","2023-12-15 13:00","2023-12-16 13:00","취소","취소","연속"]
[213,"광주전남","광주","계림남광주 T/L","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2023-12-04 09:00","2024-01-05 18:00","취소","취소","연속"]
[214,"광주전남","광주","계림충장#2 T/L","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2023-12-04 09:00","2024-01-05 18:00","취소","취소","연속"]
[215,"광주전남","광주","계림S/S CB 6100","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2023-12-04 09:00","2024-01-05 18:00","취소","취소","연속"]
[216,"광주전남","광주","정공담양 T/L","2023년 가공송전선로 순시점검 위탁공사","154kV 정공-담양T/L 137,140호 과열정비 시행","2023-12-06 09:00","2023-12-06 12:00","취소","취소","연속"]
[217,"광주전남","광주","신광주계림#2 T/L","신광주-계림#2T/L 장기사용 보호반 교체","신광주, 계림S/S 신광주-계림#2T/L 장기사용 보호반 교체, 즉시가압불가","2023-12-04 09:00","2023-12-07 18:00","취소","취소","연속"]
[218,"광주전남","광주","신화순매월#2 T/L","2023년 직할 가공 송전협력회사 총액공사(직할)","수평 추락방지장치 설치","2023-12-11 07:00","2023-12-15 18:00","취소","취소","매일"]
[219,"광주전남","광주","신화순매월#1 T/L","2023년 직할 가공 송전협력회사 총액공사(직할)","수평 추락방지장치 설치","2023-12-04 07:00","2023-12-08 18:00","취소","취소","매일"]
[220,"광주전남","광주","신광주장성#2 T/L","154kV 장성-영광#2T/L 선종교체공사(무부하)","154kV 장성-영광#2T/L 선종교체공사 관련 송전선로 무부하가압 조작","2023-12-13 09:00","2023-12-13 18:00","2023-12-13 09:00","2023-12-13 18:00","연속"]
[221,"광주전남","목포","목포북항#2 T/L","북항S/S 154kV 장기사용 GIS 교체공사(4차)","목포-북항#2T/L GIS 교체","2023-12-18 09:00","2024-01-26 18:00","취소","취소","연속"]
[222,"광주전남","목포","장성영광#1 T/L","[변전] 임시 SPS반 CT 케이블 재이설","- (즉시가압가능) 임시 SPS 미사용으로 인한 CT 케이블 원복","2023-12-15 09:00","2023-12-15 13:00","2023-12-15 09:00","2023-12-15 13:00","연속"]
[223,"광주전남","목포","장성영광#2 T/L","[변전] 임시 SPS반 CT 케이블 재이설","- (즉시가압가능) 임시 SPS 미사용으로 인한 CT 케이블 원복","2023-12-15 13:00","2023-12-15 18:00","2023-12-15 13:00","2023-12-15 18:00","연속"]
[224,"광주전남","목포","고창홍농 T/L","22~23년 목포 송전 협력회사 총액공사(추락방지)","154kV 고창-홍농 수평 추락방지장치 설치","2023-12-04 07:00","2023-12-04 18:00","취소","취소","연속"]
[225,"광주전남","순천","서순천S/S 순천전철#2T/L CB","22-23년 순천전력지사 변전협력회사 총액공사","순천전철#2T/L GIS 차단기 조작시험(송전선로 설비 없음, GIS 신청)","2023-12-12 10:00","2023-12-12 14:00","취소","취소","연속"]
[226,"광주전남","순천","서순천S/S 순천전철#1T/L CB","22-23년 순천전력지사 변전협력회사 총액공사","순천전철#1T/L GIS 차단기 조작시험(송전선로 설비 없음, GIS 신청)","2023-12-05 10:00","2023-12-05 14:00","취소","취소","연속"]
[227,"광주전남","순천","여수소라#2 T/L","154kV 여수-소라T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No. 1~33, 27기","2023-12-14 07:00","2023-12-15 17:00","취소","취소","매일"]
[228,"광주전남","순천","여수소라#1 T/L","154kV 여수-소라T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No. 1~33, 27기","2023-12-11 07:00","2023-12-13 17:00","취소","취소","매일"]
[229,"광주전남","순천","여천여수#2 T/L","154kV 여천-여수T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No. 11~22, 12기","2023-12-15 07:00","2023-12-15 17:00","취소","취소","연속"]
[230,"광주전남","순천","여천여수#1 T/L","154kV 여천-여수T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No. 11~22, 12기","2023-12-13 07:00","2023-12-13 17:00","취소","취소","연속"]
[231,"광주전남","순천","여수T/P #65 BUS","22-23년 순천전력지사 변전협력회사 총액공사","GS 칼텍스 여수#2T/L #2DS 가스누기해소 공사","2023-12-26 09:00","2023-12-27 18:00","취소","취소","연속"]
[232,"광주전남","순천","여수TP화치#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","TL 보호반(즉시가압 불가) 대체","2023-12-18 09:00","2023-12-22 18:00","취소","취소","연속"]
[233,"광주전남","순천","여수T/P SEC CB 65660","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2023-12-15 13:40","2023-12-15 14:00","취소","취소","연속"]
[234,"광주전남","순천","여수T/P SEC CB 60610","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2023-12-15 13:20","2023-12-15 13:40","취소","취소","연속"]
[235,"광주전남","순천","여수T/P CB 6100","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2023-12-08 13:00","2023-12-08 13:20","취소","취소","연속"]
[236,"광주전남","순천","여수TP용성#1 T/L","'2022~23년 가공송전 협력회사 총액공사","SB댐퍼 설치 (여수TP-용성#1 T/L) : 5기","2023-12-13 08:00","2023-12-13 18:00","취소","취소","연속"]
[237,"광주전남","순천","여수T/P SEC CB 65660","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2023-12-08 13:40","2023-12-08 14:00","취소","취소","연속"]
[238,"광주전남","순천","여수T/P SEC CB 60610","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2023-12-08 13:20","2023-12-08 13:40","취소","취소","연속"]
[239,"광주전남","순천","여수T/P CB 6200","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2023-12-15 13:00","2023-12-15 13:20","취소","취소","연속"]
[240,"광주전남","순천","여천호남TP#1 T/L","154kV 코타핀 교체공사","○ #1 12,13,14,24,25,26,27,28,29,30,31호 총 11기 코타핀 교체공사 시행","2023-12-04 09:00","2023-12-06 18:00","취소","취소","매일"]
[241,"광주전남","순천","용성여수산단#1 T/L","'2022~23년 가공송전 협력회사 총액공사","SB댐퍼 설치 (여수TP-용성#2 T/L) : 5기","2023-12-12 08:00","2023-12-12 18:00","취소","취소","연속"]
[242,"광주전남","순천","여수TP용성#2 T/L","'2022~23년 가공송전 협력회사 총액공사","SB댐퍼 설치 (여수TP-용성#2 T/L) : 5기","2023-12-12 08:00","2023-12-12 18:00","취소","취소","연속"]
[243,"광주전남","순천","용성여수산단#2 T/L","'2022~23년 가공송전 협력회사 총액공사","SB댐퍼 설치 (여수TP-용성#1 T/L) : 5기","2023-12-13 08:00","2023-12-13 18:00","취소","취소","연속"]
[244,"광주전남","순천","용성여수산단#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","#1DS 가스누기 해소공사","2023-12-28 09:00","2023-12-29 18:00","취소","취소","연속"]
[245,"광주전남","순천","여수TP용성#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","용성S/S 여수TP-용성#1T/L GIS 불량 유압력계 교체(즉시가압 불가)","2023-12-06 09:00","2023-12-07 18:00","취소","취소","연속"]
[246,"광주전남","순천","율촌여수산단#2 T/L","가공송전 위탁공사 정밀점검(율촌여수산단#2 T/L) : 51기","가공송전 위탁공사 정밀점검(율촌여수산단#2 T/L) : 51기","2023-12-11 09:00","2023-12-14 18:00","취소","취소","매일"]
[247,"광주전남","순천","율촌민자#2 T/L","154kV 율촌민자T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No. 1~9, 9기","2023-12-08 07:00","2023-12-08 17:00","취소","취소","연속"]
[248,"광주전남","순천","율촌민자#1 T/L","154kV 율촌민자#1T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No. 1~9, 9기","2023-12-07 07:00","2023-12-07 17:00","취소","취소","연속"]
[249,"광주전남","순천","율촌여수산단#1 T/L","가공송전 위탁공사 정밀점검(율촌여수산단#1 T/L)","가공송전 위탁공사 정밀점검(율촌여수산단#1 T/L) : 51기","2023-12-04 09:00","2023-12-07 18:00","취소","취소","매일"]
[250,"광주전남","순천","율촌여수산단#2 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No. 1~51, 28기","2023-12-21 07:00","2023-12-22 17:00","취소","취소","매일"]
[251,"광주전남","순천","율촌여수산단#1 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No. 1~51, 28기","2023-12-18 07:00","2023-12-20 17:00","취소","취소","매일"]
[252,"광주전남","순천","호남TP여수TP#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","LA 대체","2023-12-14 10:00","2023-12-14 18:00","취소","취소","연속"]
[253,"광주전남","순천","호남TP여수TP#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","LA 대체","2023-12-15 10:00","2023-12-15 18:00","취소","취소","연속"]
[254,"광주전남","순천","화치S/S 덕양전철#2T/L CB","22-23년 순천전력지사 변전협력회사 총액공사","덕양전철#2T/L GIS 차단기 조작시험(송전선로 없음, GIS 신청)","2023-12-12 15:00","2023-12-12 18:00","취소","취소","연속"]
[255,"광주전남","순천","화치S/S 덕양전철#1T/L CB","22-23년 순천전력지사 변전협력회사 총액공사","덕양전철#1T/L GIS 차단기 조작시험(송전선로 없음, GIS 신청)","2023-12-05 15:00","2023-12-05 18:00","취소","취소","연속"]
[256,"대구","경산","경산자인#2 T/L","2022~23년 대구직할 가공송전 협력회사 총액공사","수평 추락방지장치 설치공사","2023-12-04 07:30","2023-12-08 18:00","2023-12-07 07:30","2023-12-13 18:00","연속"]
[257,"대구","경산","신경산진량 T/L","2022-23년 경산전력지사 가공송전 협력회사 총액공사","(안전확보) 철탑추락방지장치 설치 - 작업구간 : No.21","2023-12-07 12:00","2023-12-07 15:00","취소","취소","연속"]
[258,"대구","달성","논공S/S #1 EM.Tr CB","논공S/S FR-ESS 정기점검","논공S/S FR-ESS 정기점검","2023-12-04 09:00","2023-12-08 18:00","2023-12-04 09:00","2023-12-08 18:00","연속"]
[259,"대구","달성","달서S/S #60-#61 BUS","달서S/S 장기사용 170kV GIS 교체공사","달서S/S 장기사용 170kV GIS 교체공사","2023-12-13 09:00","2023-12-16 09:00","취소","취소","연속"]
[260,"대구","달성","달서S/S #65-#66 BUS","달서S/S 장기사용 170kV GIS 교체공사","달서S/S 장기사용 170kV GIS 교체공사","2023-12-18 09:00","2023-12-21 16:00","취소","취소","연속"]
[261,"대구","달성","달서S/S #65-#66 BUS","달서S/S 장기사용 170kV GIS 교체공사","달서S/S 장기사용 170kV GIS 교체공사","2023-12-11 09:00","2023-12-13 09:00","취소","취소","연속"]
[262,"대구","달성","달서S/S #60-#61 BUS","달서S/S 장기사용 170kV GIS 교체공사","달서S/S 장기사용 170kV GIS 교체공사","2023-12-21 16:00","2023-12-22 18:00","취소","취소","연속"]
[263,"대구","달성","달서S/S #65-#66 BUS","달서S/S 장기사용 170kV GIS 교체공사","달서S/S 장기사용 170kV GIS 교체공사","2023-12-04 09:00","2023-12-07 16:00","취소","취소","연속"]
[264,"대구","달성","달서S/S #60-#61 BUS","달서S/S 장기사용 170kV GIS 교체공사","달서S/S 장기사용 170kV GIS 교체공사","2023-12-07 16:00","2023-12-08 18:00","취소","취소","연속"]
[265,"대구","달성","대구자인#1 T/L","2022~23년 대구직할 가공송전 협력회사 총액공사","수평 추락방지장치 설치공사","2023-12-11 07:30","2023-12-13 18:00","취소","취소","연속"]
[266,"대구","달성","대구자인#2 T/L","2022~23년 대구직할 가공송전 협력회사 총액공사","수평 추락방지장치 설치공사","2023-12-04 07:30","2023-12-08 18:00","2023-12-07 07:30","2023-12-13 18:00","연속"]
[267,"대구","달성","고령쌍림#2 T/L","변전소 외벽 보강공사","(안전확보)변전소 외벽 보강공사","2023-12-02 09:00","2023-12-10 18:00","2023-12-02 09:00","2023-12-10 18:00","연속"]
[268,"대구","직할","남대구동인#1 T/L","남대구S/S 154kV GIS 교체(TEST선로)","○ #1BUS 무부하가압(2H)","2023-12-08 14:00","2023-12-08 16:00","2023-12-08 14:00","2023-12-08 16:00","연속"]
[269,"대구","직할","남대구동인#1 T/L","남대구S/S 154kV GIS 교체(TEST선로)","○ #2BUS 무부하가압(24H)","2023-12-06 16:00","2023-12-07 16:00","2023-12-06 16:00","2023-12-07 16:00","연속"]
[270,"대구","직할","남대구S/S #1 BUS","남대구S/S 154kV GIS 교체 및 증설공사","○ #1BUS측 인터록 등 준공시험 ○ #1BUS~#1DS간 무부하 시험가압","2023-12-07 16:00","2023-12-08 16:00","취소","취소","연속"]
[271,"대구","칠곡","북대구관음#2 T/L","관음S/S 154kV GIS 대체공사(안전확보)","관음S/S 154kV GIS 대체공사(2차) -대상: 관음-구암#2, #2M.Tr 1차, SEC DS","2023-12-14 09:00","2023-12-15 18:00","취소","취소","연속"]
[272,"대구","칠곡","관음S/S #1 BUS","관음S/S 154kV GIS 대체공사","관음S/S 154kV GIS 대체공사(2차) -대상: 관음-구암#2, #2M.Tr 1차, SEC DS","2023-12-22 14:00","2023-12-22 18:00","취소","취소","연속"]
[273,"대구","칠곡","관음S/S #2 BUS","관음S/S 154kV GIS 대체공사","관음S/S 154kV GIS 대체공사(2차) -대상: 관음-구암#2, #2M.Tr 1차, SEC DS","2023-12-11 09:00","2023-12-22 14:00","취소","취소","연속"]
[274,"대구","칠곡","남구미농소#2 T/L","22-23년 칠곡전력 가공송전협력 총액공사","관형지지물용 가이드레일 설치(안전확보)","2023-12-04 12:30","2023-12-04 18:00","2023-12-04 12:30","2023-12-04 18:00","연속"]
[275,"대구","칠곡","남구미농소#1 T/L","22-23년 칠곡전력 가공송전협력 총액공사","관형지지물용 가이드레일 설치(안전확보)","2023-12-04 07:30","2023-12-04 12:30","2023-12-04 07:30","2023-12-04 12:30","연속"]
[276,"대구","칠곡","성주금릉#1 T/L","22-23년 칠곡전력 가공송전협력 총액공사","관형지지물용 가이드레일 설치(안전확보)","2023-12-02 07:30","2023-12-02 18:00","취소","취소","연속"]
[277,"대구","칠곡","성주금릉#2 T/L","22-23년 칠곡전력 가공송전협력 총액공사","관형지지물용 가이드레일 설치(안전확보)","2023-12-02 07:30","2023-12-02 18:00","취소","취소","연속"]
[278,"대구","포항","건천천북#1 T/L","건천S/S 6100 GIS 주접점이탈조치[무부하가압]","건천S/S 6100 GIS 주접점이탈조치[무부하가압]","2023-12-06 12:00","2023-12-07 18:00","2023-12-06 12:00","2023-12-07 18:00","연속"]
[279,"경북","구미","청리상주#2 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- LA 보통점검","2023-12-01 09:00","2023-12-01 14:00","2023-12-01 09:00","2023-12-01 14:00","연속"]
[280,"경북","구미","상주화동#1 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- #2DS부 누기개소 점검","2023-12-04 09:30","2023-12-05 18:00","2023-12-09 09:30","2023-12-10 18:00","연속"]
[281,"경북","영주","예천점촌#1 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","LA 대체","2023-12-06 14:00","2023-12-06 18:00","2023-12-06 14:00","2023-12-06 18:00","연속"]
[282,"경북","영주","동상주점촌#1 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","LA 대체","2023-12-06 09:00","2023-12-06 14:00","2023-12-06 09:00","2023-12-06 14:00","연속"]
[283,"경북","직할","안동동안동#2 T/L","동안동S/S 154kV SW 증설 및 GIS 교체공사","동안동-진보 #2T/L 무부하가압 선로","2023-12-26 09:00","2023-12-27 18:00","2023-12-26 09:00","2023-12-27 18:00","연속"]
[284,"경북","직할","안동동안동#2 T/L","동안동S/S 154kV SW 증설 및 GIS 교체공사","154kV GIS 2CCT 교체 - #2M.Tr, 동안동-임하HP T/L(동안동-진보#2), PT&ES","2023-12-08 09:00","2023-12-09 18:00","2023-12-08 09:00","2023-12-09 18:00","연속"]
[285,"부산울산","북부산","북부산호포 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치","154kV 호포분기, 북부산-물금T/L 수평 추락방지장치 설치(호포분기 5기, 북부산-물금T/L 1~9호 등)","2023-12-04 08:30","2023-12-08 18:00","취소","취소","연속"]
[286,"부산울산","북부산","북부산물금 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치 안전확보","154kV 호포분기, 북부산-물금T/L 수평 추락방지장치 설치(호포분기 5기, 북부산-물금T/L 1~9호 등) 4회선 철탑구간 안전확보","2023-12-07 08:30","2023-12-08 18:00","취소","취소","연속"]
[287,"부산울산","북부산","북부산양산 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치공사","154kV 북부산-삼랑진T/L 수평 추락방지장치 설치 4회선 병가구간 상하회선 안전확보(1호 등 2회선 철탑 12기, 4회선 철탑 33기)","2023-12-11 08:30","2023-12-17 18:00","취소","취소","연속"]
[288,"부산울산","북부산","북부산삼랑진PP T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치공사","154kV 북부산-삼랑진T/L 수평 추락방지장치 설치(1호 등 2회선 철탑 12기, 4회선 철탑 33기)","2023-12-11 08:30","2023-12-20 18:00","2023-12-15 08:30","2023-12-17 18:00","연속"]
[289,"부산울산","북부산","북부산양산 T/L","세니온제 송전선로 보호반 성능개선","154kV 북부산-양산T/L 세니온제 송전선로 보호반 성능개선","2023-12-01 09:00","2023-12-01 18:00","2023-12-01 09:00","2023-12-01 18:00","연속"]
[290,"부산울산","북부산","서창산막#2 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치","154kV 서창-산막#2T/L 수평 추락방지장치 설치(25~69호, 32기)","2023-12-02 08:30","2023-12-03 18:00","2023-12-02 08:30","2023-12-03 18:00","연속"]
[291,"부산울산","북부산","서창산막#2 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치","154kV 서창-산막#2T/L 수평 추락방지장치 설치(25~69호, 32기)","2023-12-09 08:30","2023-12-10 18:00","2023-12-09 08:30","2023-12-10 18:00","연속"]
[292,"부산울산","서부산","신녹산녹산#2 T/L","신녹산, 녹산S/S 신녹산-녹산#2T/L 보호반 대체작업","신녹산, 녹산S/S 신녹산-녹산#2T/L 보호반 대체작업","2023-12-06 09:00","2023-12-08 18:00","2023-12-06 09:00","2023-12-08 18:00","연속"]
[293,"부산울산","울산","옥동외동#2 T/L","옥동S/S 154kV 장기사용 GIS 교체공사","옥동S/S 외동-옥동#2T/L 장기사용 GIS 교체","2023-12-04 09:00","2023-12-22 18:00","2023-12-04 09:00","2023-12-22 18:00","연속"]
[294,"부산울산","울산","온산처용#1 T/L","345kv 동울산-월성NP등 6개T/L 추락방지장치 등 설치공사","철탑 추락방지장치 및 폴리머점퍼지지애자 설치","2023-12-04 07:00","2023-12-06 18:00","2023-12-04 07:00","2023-12-06 18:00","연속"]
[295,"부산울산","울산","남울산용연#2 T/L","23년 용연S/S 154kV 고객공급GIS 대체공사","효성#1T/L GIS 대체관련 시험가압(1Hr)","2023-12-11 18:00","2023-12-11 19:00","2023-12-11 18:00","2023-12-11 19:00","연속"]
[296,"부산울산","울산","남울산용연#2 T/L","23년 용연S/S 154kV 고객공급GIS 대체공사","효성#1T/L GIS 대체관련 시험가압(24Hr)","2023-12-15 18:00","2023-12-16 18:00","2023-12-15 18:00","2023-12-16 18:00","연속"]
[297,"부산울산","울산","남울산용연#2 T/L","23년 용연S/S 154kV 고객공급GIS 대체공사","효성#1T/L GIS 대체관련 시험가압(24Hr)","2023-12-22 08:00","2023-12-23 09:00","2023-12-22 08:00","2023-12-23 09:00","연속"]
[298,"부산울산","울산","성암울산TP#2 T/L","울산화력S/Y 154kV 장기사용 GIS 교체공사 (7차분)","#6100 BUS-TIE, 60-65 PT&ES 교체 -#60BUS 시험가압 (24시간)","2023-12-21 17:00","2023-12-22 18:00","2023-12-21 17:00","2023-12-22 18:00","연속"]
[299,"부산울산","울산","울산T/P #60 BUS","울산화력S/Y 154kV 장기사용 GIS 교체공사(7차분)","#6100 BUS-TIE, #60-65 PT&ES 교체 -#6101DS, 6100CB, #60 BUS PT&ES 철거 및 설치, 시험가압(24시간)","2023-12-04 09:00","2023-12-09 18:00","2023-12-04 09:00","2023-12-09 18:00","연속"]
[300,"부산울산","울산","성암울산TP#2 T/L","울산화력S/Y 154kV 장기사용 GIS 교체공사 (7차분)","#6100 BUS-TIE, 60-65 PT&ES 교체 -안전이격거리확보 -#60BUS 시험가압 (24시간)","2023-12-04 09:00","2023-12-09 18:00","2023-12-04 09:00","2023-12-09 18:00","연속"]
[301,"부산울산","울산","성암울산TP#2 T/L","울산화력S/Y 154kV 장기사용 GIS 교체공사 (7차분)","#6100 BUS-TIE, 60-65 PT&ES 교체 -#65BUS 시험가압 (1시간)","2023-12-01 17:00","2023-12-01 18:00","2023-12-01 17:00","2023-12-01 18:00","연속"]
[302,"부산울산","울산","울산T/P #60 BUS","울산화력S/Y 154kV 장기사용 GIS 교체공사 (7차분)","#6100 BUS-TIE, 60-65 PT&ES 교체 -#65BUS 시험가압 (#2DS투입상태 1시간)","2023-12-22 17:00","2023-12-22 18:00","2023-12-22 17:00","2023-12-22 18:00","연속"]
[303,"부산울산","울산","울산T/P #65 BUS","울산화력S/Y 154kV 장기사용 GIS 교체공사 (7차분)","#6100 BUS-TIE, 60-65 PT&ES 교체 -#6102DS, #65 BUS PT&ES 철거 및 설치, 시험가압(24시간)","2023-12-11 09:00","2023-12-22 17:00","2023-12-11 09:00","2023-12-22 17:00","연속"]
[304,"부산울산","울산","울산영남TP#2 T/L","울산-울산TP 등 2개T/L 철탑 철거공사","철탑 철거","2023-12-12 07:00","2023-12-15 18:00","2023-12-12 07:00","2023-12-15 18:00","연속"]
[305,"부산울산","울산","울주외동#1 T/L","22~23년 변전협력회사 총액공사","- 6C2DS 스페이서 가스 누기보수","2023-12-07 09:00","2023-12-08 18:00","2023-12-07 09:00","2023-12-08 18:00","연속"]
[306,"부산울산","울산","울주외동#2 T/L","22~23년 변전협력회사 총액공사","- 6B2DS 스페이서 가스 누기보수","2023-12-04 09:00","2023-12-06 18:00","2023-12-04 09:00","2023-12-06 18:00","연속"]
[307,"경남","직할","신김해진례#2 T/L","OPGW 취약개소 금구류 정비공사(안전이격)","댐퍼1개 교체 및 2개 정비","2023-12-04 07:00","2023-12-04 18:00","2023-12-04 07:00","2023-12-04 18:00","연속"]
[308,"경남","직할","안민천선#2 T/L","154kV 안민-천선T/L 수평 추락방지장치 설치공사","154kV 안민-천선T/L 수평 추락방지장치 설치공사","2023-12-10 07:00","2023-12-10 18:00","2023-12-10 07:00","2023-12-10 18:00","연속"]
[309,"경남","직할","안민천선#1 T/L","154kV 안민-천선T/L 수평 추락방지장치 설치공사","154kV 안민-천선T/L 수평 추락방지장치 설치공사","2023-12-09 07:00","2023-12-09 18:00","2023-12-09 07:00","2023-12-09 18:00","연속"]
[310,"경남","통영","신고성거제#2 T/L","OPGW 항공장애표시구 설치공사(안전이격)","항공장애표시구 211개 설치","2023-12-09 07:00","2023-12-10 18:00","2023-12-09 07:00","2023-12-10 18:00","매일"]
[311,"경남","통영","진동안정#1 T/L","154kV 가스공사2T/L 수급지점변경공사(시험가압선로)","1. GIS(170kV 50kA 1,250A) x 1CCT 철거 2. 기타 부대공사 x 1식 3. 시험가압선로","2023-12-15 09:00","2023-12-15 18:00","취소","취소","연속"]
[312,"경남","통영","진동안정#1 T/L","154kV 가스공사2T/L 수급지점변경공사(시험가압선로)","1. GIS(170kV 50kA 1,250A) x 1CCT 철거 2. 기타 부대공사 x 1식 3. 시험가압선로","2023-12-12 09:00","2023-12-12 18:00","취소","취소","연속"]
[313,"경남","통영","안정통영CC#2 T/L","통영복합S/Y 154kV 가스공사T/L 신규수용공사(시험가압선로)","1. GIS(170kV 50kA 1,250A) x 1CCT 설치 2. 기타 부대공사 x 1식 3. 시험가압선로","2023-12-05 09:00","2023-12-06 18:00","2023-12-05 09:00","2023-12-06 18:00","연속"]
[314,"경남","통영","안정통영CC#1 T/L","안정S/S 154kV 안정-통영복합#1T/L GIS 조작시험","안정S/S 154kV 안정-통영복합#1T/L GIS 조작시험 및 LA 보통점검","2023-12-19 09:30","2023-12-19 18:00","2023-12-19 09:30","2023-12-19 18:00","연속"]
[315,"경남","통영","고성통영CC#1 T/L","고성S/S 154kV 고성-통영복합#1T/L LA A,B,C상 교체","고성S/S 154kV 고성-통영복합#1T/L LA A,B,C상 교체","2023-12-18 09:30","2023-12-18 18:00","2023-12-18 09:30","2023-12-18 18:00","연속"]
[316,"경남","함안","청도밀양#2 T/L","154kV 부북분기T/L 건설공사","154kV 청도-밀양T/L No.76~C/T 간 전선 연긴선 (#1,2T/L 수직배열에 따른 동시휴전 필요, #2T/L 안전이격 확보 휴전)","2023-12-23 07:00","2023-12-26 18:00","취소","취소","연속"]
[317,"경남","함안","청도밀양#1 T/L","154kV 부북S/S 및 부북분기T/L 건설공사","-154kV 청도-밀양T/L No.76~C/T 간 전선 연긴선(23~26) (#1,2T/L 수직배열에 따른 동시 휴전 필요) - 154kV 청도-밀양#1T/L 보호반 대체작업(26~29)","2023-12-23 07:00","2023-12-30 18:00","취소","취소","연속"]
[318,"경남","함안","서마산진동#2 T/L","성능저하 점퍼지지애자 교체공사","구 신마산-서마산(신마산-서마산T/L) 58호, 진동분기(신마산-진동T/L) 5, 35, 40호 성능저하 점퍼지지애자 교체공사 - 서마산분기T/L 증설이후 철탑번호 변경","2023-12-14 07:00","2023-12-14 18:00","2023-12-14 07:00","2023-12-14 18:00","연속"]
[319,"경남","함안","신마산마산#2 T/L","신마산-서마산#1T/L 성능저하 점퍼지지애자 교체공사 안전거리 확보","신마산-서마산(신마산-서마산#1T/L) 2, 3, 4, 5, 6, 7, 8호 성능저하 점퍼지지애자 교체공사 안전거리 확보","2023-12-09 07:00","2023-12-11 18:00","2023-12-09 07:00","2023-12-11 18:00","매일"]
[320,"경남","함안","신마산서마산#1 T/L","신마산-서마산#1T/L 성능저하 점퍼지지애자 교체공사","신마산-서마산(신마산-서마산#1T/L) 2, 3, 4, 5, 6, 7, 8, 9, 26호 성능저하 점퍼지지애자 교체공사","2023-12-09 07:00","2023-12-11 18:00","2023-12-09 07:00","2023-12-11 18:00","매일"]
[321,"경남","함안","신마산마산#1 T/L","신마산-서마산#1T/L 성능저하 점퍼지지애자 교체공사 안전거리 확보","신마산-서마산(신마산-서마산#1T/L) 2, 3, 4, 5, 6, 7, 8호 성능저하 점퍼지지애자 교체공사 안전거리 확보","2023-12-09 07:00","2023-12-11 18:00","2023-12-09 07:00","2023-12-11 18:00","매일"]
[322,"경남","함안","신마산서마산#2 T/L","성능저하 점퍼지지애자 교체공사","구 진동분기(서마산-진동T/L) 1,2호 성능저하 점퍼지지애자 교체공사 - 서마산분기T/L 증설이후 철탑번호 변경","2023-12-12 07:00","2023-12-12 18:00","2023-12-12 07:00","2023-12-12 18:00","연속"]
[323,"경남","함안","중리가야#2 T/L","중리-가야#1T/L 성능저하 점퍼지지애자 교체공사 안전거리 확보차","중리-가야#1T/L 49호 성능저하 점퍼지지애자 교체공사 안전거리 확보차","2023-12-09 07:00","2023-12-09 18:00","취소","취소","연속"]
[324,"경남","함안","중리가야#1 T/L","중리-가야#1T/L 성능저하 점퍼지지애자 교체공사","중리-가야#1T/L 49호 성능저하 점퍼지지애자 교체공사","2023-12-09 07:00","2023-12-09 18:00","취소","취소","연속"]
[325,"경남","함안","진례진영#2 T/L","154kV 진례-진영#2T/L 정밀점검","1. 154kV 진례-진영#2T/L 1호~4호 정밀점검 2. 154kV 진례-진영#2T/L 5호~6호 피뢰기 아킹혼 철거","2023-12-08 09:00","2023-12-08 18:00","2023-12-08 09:00","2023-12-08 18:00","연속"]