{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":23,"n_cols":11,"rows_kept":23,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2024년도 4월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기","성남","신안성S/S #4 M.Tr","24년 성남전력지사 변전협력회사 총액공사","7A BAY B/F PNL 대체 #4M.Tr 누유보수 7A71 GIS 보통점검 ","2024-04-15 09:00","2024-04-23 18:00","2024-04-15 09:00","2024-04-23 18:00","연속"]
[2,"경기북부","구리","신안성신가평 T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","765kV 신안성-신가평T/L 항공장애등 설치 : No.131,132,146,147","2024-04-27 09:00","2024-04-28 18:00","취소","취소","연속"]
[3,"강원","태백","신태백신가평#2 T/L","2024~2025 강원본부 직할 가공송전협력회사 공사","765kV 신태백 T/L No.268-269 항공장애표시구 교체(민원)","2024-04-16 09:00","2024-04-16 18:00","취소","취소","연속"]
[4,"강원","태백","신태백S/S #1 BUS","2024년 태백전력지사 변전협력회사 공사","신태백S/S 765kV #1 BUS B/P PNL 교체","2024-04-15 09:00","2024-04-19 18:00","취소","취소","연속"]
[5,"강원","태백","신태백신가평#1 T/L","2024~2025 강원본부 직할 가공송전협력회사 공사","765kV 신태백 T/L No.268-269 항공장애표시구 교체(민원)","2024-04-15 09:00","2024-04-15 18:00","취소","취소","연속"]
[6,"충북","직할","신중부신안성#2 T/L","신중부-신안성 #2T/L 2nd PNL 보호계전기 점검 및 조치","신중부변전소 765kV 신중부-신안성 #2T/L 2nd PNL 통신경보 발생 관련 보호계전기점검 및 조치","2024-04-19 10:00","2024-04-19 18:00","2024-04-19 10:00","2024-04-19 18:00","연속"]
[7,"대전세종충남","서산","신서산당진TP#1 T/L","23년 서산P/O 장기사용 노후배전반 대체공사","(즉시가압 불가) 당진화력S/S 765kV #83B/F반 교체공사","2024-04-01 09:00","2024-04-05 18:00","취소","취소","연속"]
[8,"대전세종충남","서산","당진T/P CB 8372","23년 서산P/O 장기사용 노후배전반 대체공사","(즉시가압 불가) 당진화력S/S 765kV #83B/F반 교체공사","2024-04-01 09:00","2024-04-05 18:00","취소","취소","연속"]
[9,"대전세종충남","서산","당진T/P CB 8571","'24년 서산P/O 765kV GIS 보통점검공사","당진화력S/S 765kV 8571 GIS 보통점검 및 보조계전기 교체","2024-04-04 09:30","2024-04-05 18:00","2024-04-04 09:30","2024-04-05 18:00","연속"]
[10,"대전세종충남","서산","당진T/P CB 8971","'24년 서산P/O 765kV GIS 보통점검공사","당진화력S/S 765kV 8971 GIS 보통점검","2024-04-22 09:30","2024-04-22 18:00","취소","취소","연속"]
[11,"대전세종충남","서산","당진T/P CB 8771","'24년 서산P/O 765kV GIS 보통점검공사","당진화력S/S 765kV 8771 GIS 보통점검 및 보조계전기 교체","2024-04-24 09:30","2024-04-25 18:00","2024-04-24 09:30","2024-04-25 18:00","연속"]
[12,"대전세종충남","서산","신서산S/S #1 BUS","'23년 서산P/O 장기사용 배전반 교체공사","신서산S/S 765kV #1BUS 보호반 대체공사","2024-04-22 09:00","2024-04-26 18:00","취소","취소","연속"]
[13,"대전세종충남","서산","신서산S/S CB 8572","'24년 서산P/O 765kV GIS 보통점검공사","신서산S/S 765kV 8572 GIS 보통점검","2024-04-18 09:30","2024-04-18 18:00","2024-04-18 09:30","2024-04-18 18:00","연속"]
[14,"대전세종충남","서산","신서산S/S CB 8500","'24년 서산P/O 765kV GIS 보통점검공사","신서산S/S 765kV 8500 GIS 보통점검","2024-04-16 09:30","2024-04-16 18:00","2024-04-16 09:30","2024-04-16 18:00","연속"]
[15,"대전세종충남","서산","신서산S/S CB 8571","'24년 서산P/O 765kV GIS 보통점검공사","신서산S/S 765kV 8571 GIS 보통점검 및 보조계전기 교체","2024-04-01 09:30","2024-04-02 18:00","2024-04-01 09:30","2024-04-02 18:00","연속"]
[16,"대전세종충남","서산","신서산신중부#2 T/L","2023~2024년 천안전력지사 가공송전 협력회사 총액공사","765kV 신서산-신중부T/L No. 36~37 항공장애표시구 교체","2024-04-03 07:00","2024-04-03 18:00","취소","취소","연속"]
[17,"경북","영주","신한울N/P #1 Tie-Tr","신한울S/S 765kV #1,2M.Tr 보통점검 공사","신한울S/S 765kV #1M.Tr 보통점검 공사","2024-04-15 09:00","2024-04-19 18:00","취소","취소","연속"]
[18,"경북","영주","신한울N/P #2 Tie-Tr","신한울S/S 765kV #1,2M.Tr 보통점검 공사","신한울S/S 765kV #2M.Tr 보통점검 공사","2024-04-22 09:00","2024-04-26 18:00","취소","취소","연속"]
[19,"부산울산","동부산","신고리N/P #4 Tie-Tr","신고리S/S #4M.Tr 보통점검","신고리S/S #4M.Tr 보통점검","2024-04-22 09:00","2024-04-30 18:00","취소","취소","연속"]

{"sheet":"345설비","index":1,"n_rows":295,"n_cols":11,"rows_kept":295,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2024년도 4월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","미금성동#2 T/L","2024~25년 성동전력지사 변전협력회사 공사","- B/F PNL 대체","2024-04-15 10:00","2024-04-18 18:00","취소","취소","연속"]
[2,"서울","성동","성동S/S #2 M.Tr","2024~25년 성동전력지사 변전협력회사 공사","#2 M.Tr PNL 대체작업","2024-04-15 10:00","2024-04-24 18:00","2024-04-15 10:00","2024-04-24 18:00","연속"]
[3,"서울","중부","중부S/S CB 7400","24-25 중부전력지사 변전협력 총액공사","차단기 조작시험","2024-04-26 14:00","2024-04-26 18:00","2024-04-26 14:00","2024-04-26 18:00","연속"]
[4,"서울","중부","중부S/S CB 7100","24-25 중부전력지사 변전협력 총액공사","차단기 조작시험","2024-04-26 10:00","2024-04-26 14:00","2024-04-08 10:00","2024-04-08 14:00","연속"]
[5,"서울","중부","양주중부#1 T/L","24-25 중부전력지사 변전협력 총액공사","차단기 조작시험","2024-04-08 10:00","2024-04-08 18:00","2024-04-08 10:00","2024-04-08 18:00","연속"]
[6,"서울","중부","중부S/S #2 M.Tr","24-25 중부전력지사 변전협력 총액공사","M.Tr 보통점검, 1,3차 PT 보통점검(A,B,C), 3차 LA 보통점검(A,B,C), 1,2차 조작시험, 7200 TIE 조작시험, #2S.Tr 1차 VCB, LS 보통점검, #2S.Tr 보통점검","2024-04-01 09:00","2024-04-03 18:00","취소","취소","연속"]
[7,"서울","중부","중부S/S #2 BUS","24-25 중부전력지사 변전협력 총액공사","7352DS 이음부 점검","2024-04-11 10:00","2024-04-24 18:00","2024-04-11 10:00","2024-04-24 18:00","연속"]
[8,"서울","중부","중부S/S CB 7372","24-25 중부전력지사 변전협력 총액공사","7352DS 이음 점검","2024-04-11 10:00","2024-04-24 18:00","2024-04-11 10:00","2024-04-24 18:00","연속"]
[9,"서울","중부","양주중부#2 T/L","24-25 중부전력지사 변전협력 총액공사","차단기 조작시험","2024-04-09 10:00","2024-04-09 18:00","2024-04-09 10:00","2024-04-09 18:00","연속"]
[10,"남서울","동서울","곤지암동서울#2 T/L","345kV 동서울S/S 종합정비공사","- 345kV M.Tr(단상, 166.7MVA, FOA) × 6대(이설) - 345,154kV GIB × 2조(신설) - 345kV M.Tr 감시,제어,계측,보호 제어케이블 포설 및 결선 × 1식 - 345kV GIS 감시,제어,계측 제어케이블 재사용철거 및 포설 × 1식 - 23kV Sh.R(삼상, 30Mvar) × 6대(이설)","2024-04-01 09:00","2024-04-30 18:00","취소","취소","연속"]
[11,"남서울","영등포","서서울신광명#1 T/L","2024~25년 가공송전 협력회사 공사(수평 추락방지장치 설치)","345kV 서서울-신광명#1T/L 추락방지장치 설치 - No.22,24호 수직 추락방지장치 미설치 개소 설치","2024-04-15 07:00","2024-04-26 18:00","취소","취소","연속"]
[12,"남서울","직할","신광명신문래#1 T/L","345kV 차단기 균압콘덴서 정전용량 측정","345kV 차단기 균압콘덴서 정전용량 측정","2024-04-18 09:00","2024-04-18 14:00","취소","취소","연속"]
[13,"남서울","직할","신문래S/S #70 BUS","345kV 차단기 균압콘덴서 정전용량 측정","345kV 차단기 균압콘덴서 정전용량 측정","2024-04-18 09:00","2024-04-18 18:00","취소","취소","연속"]
[14,"남서울","직할","신광명신문래#2 T/L","345kV 차단기 균압콘덴서 정전용량 측정","345kV 차단기 균압콘덴서 정전용량 측정","2024-04-18 14:00","2024-04-18 18:00","취소","취소","연속"]
[15,"인천","김포","신김포S/S #3 M.Tr","신김포S/S 345kV #3M.Tr 초기점검","신김포S/S 345kV #3M.Tr 초기점검 - 신김포S/S 345kV #3M.Tr 1, 2차 GIS 초기점검 - GIB 상간단락바 설치","2024-04-25 09:00","2024-04-26 18:00","2024-04-25 09:00","2024-04-26 18:00","연속"]
[16,"인천","김포","신김포S/S #2 M.Tr","신김포S/S 345kV #2M.Tr 2차 GIB 상간단락바 설치","신김포S/S 345kV #2M.Tr 2차 GIB 상간단락바 설치","2024-04-24 09:00","2024-04-24 18:00","2024-04-24 09:00","2024-04-24 18:00","연속"]
[17,"인천","김포","신김포S/S #1 M.Tr","신김포S/S 345kV #1M.Tr 2차 GIB 상간단락바 설치","신김포S/S 345kV #1M.Tr 2차 GIB 상간단락바 설치","2024-04-22 09:00","2024-04-23 18:00","2024-04-22 09:00","2024-04-23 18:00","연속"]
[18,"인천","부평","서인천C/C #1 M.Tr","서인천C/C 345kV #1 M.Tr 부싱유 채유","서인천C/C 345kV #1 M.Tr 부싱유 채유","2024-04-19 09:00","2024-04-19 18:00","2024-04-19 09:00","2024-04-19 18:00","연속"]
[19,"인천","부평","서인천C/C #2 CLR CB","서인천C/C 345kV #75-77 CLR #7777 GIS 보통점검","서인천C/C 345kV #75-77 CLR #7777 GIS 보통점검","2024-04-12 09:00","2024-04-12 18:00","2024-04-12 09:00","2024-04-12 18:00","연속"]
[20,"인천","부평","서인천C/C #2 CLR CB","서인천C/C 345kV #75-77 CLR #7577 GIS 보통점검","서인천C/C 345kV #75-77 CLR #7577 GIS 보통점검","2024-04-11 09:00","2024-04-11 18:00","2024-04-11 09:00","2024-04-11 18:00","연속"]
[21,"인천","부평","서인천C/C #1 CLR CB","서인천C/C 345kV #70-72 CLR #7277 GIS 보통점검","서인천C/C 345kV #70-72 CLR #7277 GIS 보통점검","2024-04-09 09:00","2024-04-09 18:00","2024-04-09 09:00","2024-04-09 18:00","연속"]
[22,"인천","부평","서인천C/C #1 CLR CB","서인천C/C 345kV #70-72 CLR #7077 GIS 보통점검","서인천C/C 345kV #70-72 CLR #7077 GIS 보통점검","2024-04-08 09:00","2024-04-08 18:00","2024-04-08 09:00","2024-04-08 18:00","연속"]
[23,"인천","부평","서인천C/C #3 Sh.R CB","서인천C/C 345kV #3Sh.R 보통점검","서인천C/C 345kV #3Sh.R 보통점검","2024-04-18 09:00","2024-04-18 18:00","2024-04-18 09:00","2024-04-18 18:00","연속"]
[24,"인천","부평","신가좌S/S #4 M.Tr","신가좌S/S 345kV #4 M.Tr 보호반대체 공사 등","신가좌S/S 345kV #4M.Tr 휴전작업","2024-04-29 09:00","2024-05-03 18:00","취소","취소","연속"]
[25,"인천","부평","신가좌S/S #1 M.Tr","신가좌S/S 345kV #1 M.Tr 보호반대체 공사 등","신가좌S/S 345kV #1 M.Tr 휴전작업","2024-04-22 09:00","2024-04-26 18:00","취소","취소","연속"]
[26,"인천","부평","신경서S/S #3 M.Tr","신경서S/S 345kV #3 M.Tr OFU 필터 교체공사","신경서S/S 345kV #3 M.Tr OFU 필터 교체공사","2024-04-01 09:00","2024-04-01 18:00","2024-04-01 09:00","2024-04-01 18:00","연속"]
[27,"인천","부평","포스코C/C CB 7271","포스코S/Y 345kV 포스코SY-인천CC#2T/L GIS 보통점검","포스코S/Y 345kV 포스코SY-인천CC#2T/L GIS 보통점검","2024-04-09 09:00","2024-04-09 18:00","2024-04-09 09:00","2024-04-09 18:00","연속"]
[28,"인천","부평","포스코C/C CB 7200","포스코S/Y 345kV 포스코SY-인천CC#2T/L TIE GIS보통점검","포스코S/Y 345kV 포스코SY-인천CC#2T/L TIE GIS 보통점검","2024-04-08 09:00","2024-04-08 18:00","2024-04-08 09:00","2024-04-08 18:00","연속"]
[29,"인천","부평","포스코C/C CB 7100","포스코S/Y 345kV 포스코SY-인천CC#1T/L TIE GIS보통점검","포스코S/Y 345kV 포스코SY-인천CC#1T/L TIE GIS보통점검","2024-04-19 09:00","2024-04-19 18:00","2024-04-19 09:00","2024-04-19 18:00","연속"]
[30,"인천","부평","포스코C/C CB 7171","포스코S/Y 345kV 포스코SY-인천CC#1T/L GIS 보통점검","포스코S/Y 345kV 포스코SY-인천CC#1T/L GIS 보통점검","2024-04-18 09:00","2024-04-18 18:00","2024-04-18 09:00","2024-04-18 18:00","연속"]
[31,"인천","부평","포스코C/C CB 7471","포스코S/Y 345kV 신경서-포스코SY#2T/L 7471GIS 보통점검","포스코S/Y 345kV 신경서-포스코SY#2T/L 7471GIS 보통점검","2024-04-16 09:00","2024-04-16 18:00","2024-04-16 09:00","2024-04-16 18:00","연속"]
[32,"인천","부평","포스코C/C CB 7400","345kV 신경서-포스코SY#2T/L TIE 7400 GIS보통점검","345kV 신경서-포스코SY#2T/L TIE 7400 GIS보통점검","2024-04-15 09:00","2024-04-15 18:00","2024-04-15 09:00","2024-04-15 18:00","연속"]
[33,"인천","부평","포스코C/C CB 7371","포스코S/Y 345kV 신경서-포스코SY#1T/L 7371GIS 보통점검","포스코S/Y 345kV 신경서-포스코SY#1T/L GIS 보통점검","2024-04-12 09:00","2024-04-12 18:00","2024-04-12 09:00","2024-04-12 18:00","연속"]
[34,"인천","부평","포스코C/C CB 7300","신경서-포스코SY#1T/L TIE 7300GIS 보통점검","포스코S/Y 345kV 신경서-포스코SY#1T/L TIE 7300GIS 보통점검","2024-04-11 09:00","2024-04-11 18:00","2024-04-11 09:00","2024-04-11 18:00","연속"]
[35,"인천","부평","서인천C/C #70 BUS","서인천C/C 345kV #70 BUS 모선보호반 대체","서인천C/C 345kV #70 BUS 모선보호반 대체","2024-05-27 09:00","2024-05-31 18:00","취소","취소","연속"]
[36,"인천","시흥","신시화영흥TP#1 T/L","신시화S/S 362kV GIS 가스 누기 보수공사","영흥T/P-신시화#1T/L CH 가스 누기 보수","2024-04-17 09:00","2024-04-18 18:00","2024-04-17 09:00","2024-04-18 18:00","연속"]
[37,"인천","시흥","신시흥#1S/S #1 M.Tr","신시흥S/S 154kV Sh.R 증설공사","- 신규 #1S.Tr 기초 및 기기설치 (#1M.Tr 3차측 VCB 교체 및 Sh.R, Sh.R 용 GIS 기초타설)","2024-04-29 09:00","2024-06-28 18:00","2024-04-29 09:00","2024-06-28 18:00","연속"]
[38,"인천","시흥","영흥1TP영흥2TP#2 T/L","영흥#2S/Y 345kV 7971, 7900 GIS 보통점검","영흥#2S/Y 345kV 영흥TP연락#2T/L(7971), 영흥TP연락#2T/L TIE(7900) GIS 보통점검","2024-04-08 09:00","2024-04-09 18:00","2024-04-08 09:00","2024-04-09 18:00","연속"]
[39,"인천","시흥","신시화영흥TP#2 T/L","영흥S/Y 345kV #75Bay B/F 보호반 대체","영흥S/Y 345kV #75Bay B/F 보호반 대체","2024-04-22 09:00","2024-04-30 18:00","2024-04-22 09:00","2024-04-30 18:00","연속"]
[40,"인천","시흥","영흥T/P CB 7572","영흥S/Y 345kV #75Bay B/F 보호반 대체","영흥S/Y 345kV #75Bay B/F 보호반 대체","2024-04-22 09:00","2024-04-30 18:00","2024-04-22 09:00","2024-04-30 18:00","연속"]
[41,"인천","직할","갈산S/S CB 7571, 7500","갈산S/S #4M.Tr 증설공사","갈산S/S 345kV GIS 도킹(#70BUS), 무부하가압","2024-04-17 11:00","2024-04-18 11:00","2024-04-17 11:00","2024-04-18 11:00","연속"]
[42,"인천","직할","갈산S/S #1 M.Tr","갈산S/S #4M.Tr 증설 및 154kV GIS 신규수용공사","갈산S/S 154kV GIS 도킹 시 인접BAY 휴전(#1M.Tr)","2024-04-30 09:00","2024-05-10 09:00","2024-04-30 09:00","2024-05-10 09:00","연속"]
[43,"인천","직할","갈산S/S CB 7571, 7500","갈산S/S #4M.Tr 증설공사","갈산S/S 345kV GIS 도킹(#75BUS) 및 #4M.Tr 무부하가압","2024-04-20 13:00","2024-04-21 14:00","2024-04-20 13:00","2024-04-21 14:00","연속"]
[44,"인천","직할","갈산S/S #75 BUS","갈산S/S #4M.Tr 증설공사","갈산S/S #4M.Tr 공사관련 345kV 모선 도킹 (#75BUS)","2024-04-18 11:00","2024-04-21 14:00","2024-04-18 11:00","2024-04-21 14:00","연속"]
[45,"인천","직할","갈산S/S #70 BUS","갈산S/S #4M.Tr 증설공사","갈산S/S #4M.Tr 공사관련 345kV 모선 도킹 (#70BUS)","2024-04-15 09:00","2024-04-18 11:00","2024-04-15 09:00","2024-04-18 11:00","연속"]
[46,"인천","직할","서인천CC신부평#2 T/L","23~24년 지중송전위탁정비공사","절연유 채취","2024-04-01 09:00","2024-04-04 18:00","2024-04-01 09:00","2024-04-04 18:00","연속"]
[47,"인천","직할","서인천CC신부평#3 T/L","23~24년 지중송전위탁정비공사","절연유 채취","2024-04-15 09:00","2024-04-18 18:00","취소","취소","연속"]
[48,"경기북부","고양","신덕은S/S #1 M.Tr","24-25년 고양변전협력 총액공사","#1M.Tr C상 주변압기 보통점검","2024-04-22 09:00","2024-04-23 18:00","2024-04-22 09:00","2024-04-23 18:00","연속"]
[49,"경기북부","고양","신파주신덕은#1 T/L","24~25년 고양전력지사 변전협력회사 공사","362kV GIS 보통점검(7171, 7100)","2024-04-23 09:00","2024-04-24 18:00","2024-04-29 09:00","2024-04-30 18:00","연속"]
[50,"경기북부","구리","미금S/S STATCOM CB","2024년 미금S/S 345kV STATCOM 냉각설비 보통점검공사","STATCOM 냉각설비 보통점검","2024-04-15 09:00","2024-04-19 18:00","취소","취소","연속"]
[51,"경기북부","구리","신가평신의정부#2 T/L","신가평S/S 345kV GIS 인출변경 및 모선 용량대체공사","기기기초 마이크로파일 시공","2024-04-29 08:00","2024-05-19 18:00","2024-04-08 08:00","2024-04-28 18:00","연속"]
[52,"경기북부","구리","신가평S/S #1 BUS","신가평S/S 345kV GIS 모선 용량대체 공사(전문)","345kV #70BUS 용량대체(63kA 4000A - 63kA 6300A) 345kV #70BUS 모선PT대체 345kV #70BUS측 51DS대체(7351~7851)","2024-04-08 09:00","2024-06-30 18:00","2024-04-08 09:00","2024-06-30 18:00","연속"]
[53,"경기북부","구리","신가평포천LNGCC#1 T/L","신가평S/S 345kV GIS 인출변경 및 모선 용량대체공사","기기기초 마이크로파일 시공","2024-04-08 08:00","2024-04-28 18:00","2024-04-29 08:00","2024-05-19 18:00","연속"]
[54,"경기북부","구리","포천LNGC/C CB 7172","2024~25년 구리전력지사 변전협력회사 공사","포천LNG C/C #1G/T TR GIS 2차 보통점검 및 절연열화 측정 7172","2024-04-16 09:00","2024-04-16 18:00","2024-04-16 09:00","2024-04-16 18:00","연속"]
[55,"경기북부","구리","포천LNGC/C CB 7371","2024~25년 구리전력지사 변전협력회사 공사","포천LNG C/C 신가평포천LNGCC#2T/L GIS 보통점검 및 절연열화 측정 7371","2024-04-15 09:00","2024-04-15 18:00","취소","취소","연속"]
[56,"경기북부","구리","포천LNGC/C CB 7300","2024~25년 구리전력지사 변전협력회사 공사","포천LNG C/C 신가평포천LNGCC #2T/L-#1S/T TR GIS 2차 절연열화 측정 7300","2024-04-17 09:00","2024-04-17 14:00","취소","취소","연속"]
[57,"경기북부","구리","포천LNGC/C CB 7471","2024~25년 구리전력지사 변전협력회사 공사","포천LNG C/C 신가평포천LNG CC #1T/L 보통점검 및 절연열화 측정 7471","2024-04-11 09:00","2024-04-11 18:00","취소","취소","연속"]
[58,"경기북부","구리","포천LNGC/C CB 7400","2024~25년 구리전력지사 변전협력회사 공사","포천LNG C/C 신가평포천LNG CC #1T/L TIE 보통점검 및 절연열화 측정 7400","2024-04-12 09:00","2024-04-12 18:00","취소","취소","연속"]
[59,"경기북부","구리","포천LNGC/C CB 7372","2024~25년 구리전력지사 변전협력회사 공사","포천LNG C/C #1S/T TR GIS 2차 절연열화 측정 7372","2024-04-17 14:00","2024-04-17 18:00","취소","취소","연속"]
[60,"경기북부","직할","양주S/S #5 Sh.R CB","24-25년도 직할 변전협력회사 총액공사","#5Sh.R GIS 개폐타임 측정","2024-04-26 10:00","2024-04-26 18:00","2024-04-26 10:00","2024-04-26 18:00","연속"]
[61,"경기","군포","서서울#2S/S CB 7C71","서서울2S/S 서서울2-화성#1T/L(7C71) 콘덴서 절연열화 측정","서서울2S/S 서서울2-화성#1T/L(7C71) 콘덴서 절연열화 측정","2024-04-26 13:00","2024-04-26 18:00","2024-04-26 13:00","2024-04-26 18:00","연속"]
[62,"경기","군포","서서울#2S/S CB 7C00","서서울2S/S 서서울2-화성#1T/L(7C00) 콘덴서 절연열화 측정","서서울2S/S 서서울2-화성#1T/L(7C00) 콘덴서 절연열화 측정","2024-04-26 09:00","2024-04-26 13:00","2024-04-26 09:00","2024-04-26 13:00","연속"]
[63,"경기","군포","서서울S/S CB 7672","서서울S/S 서서울-신광명#2T/L(7672) CB 조작시험","서서울S/S 서서울-신광명#2T/L(7672) CB 조작시험","2024-04-25 15:00","2024-04-25 18:00","2024-04-25 15:00","2024-04-25 18:00","연속"]
[64,"경기","군포","서서울S/S CB 7671","서서울S/S 서서울-신광명#2T/L(7671) CB 조작시험","서서울S/S 서서울-신광명#2T/L(7671) CB 조작시험","2024-04-25 12:00","2024-04-25 15:00","2024-04-25 12:00","2024-04-25 15:00","연속"]
[65,"경기","군포","서서울S/S CB 7772","서서울S/S 신온양-서서울#2T/L(7700, 7772) 조작시험","서서울S/S 신온양-서서울#2T/L(7700, 7772) 조작시험","2024-04-19 09:00","2024-04-19 14:00","2024-04-19 09:00","2024-04-19 14:00","연속"]
[66,"경기","군포","서서울S/S #4 M.Tr","서서울S/S #4M.Tr 7872 GIS 전자변교체","서서울S/S #4M.Tr 7872 GIS 전자변교체","2024-04-01 09:00","2024-04-03 18:00","2024-04-01 09:00","2024-04-03 18:00","연속"]
[67,"경기","군포","서서울S/S CB 7400","서서울S/S 신온양-서서울#1T/L(7400, 7472) 조작시험","서서울S/S 신온양-서서울#1T/L(7400, 7472) 조작시험","2024-04-18 09:00","2024-04-18 14:00","2024-04-18 09:00","2024-04-18 14:00","연속"]
[68,"경기","군포","서서울S/S CB 7600","서서울S/S 서서울-신광명#2T/L(7600) CB 조작시험","서서울S/S 서서울-신광명#2T/L(7600) CB 조작시험","2024-04-25 09:00","2024-04-25 12:00","2024-04-25 09:00","2024-04-25 12:00","연속"]
[69,"경기","동부","곤지암S/S CB 7271","24년 동부 변전협력총액공사","곤지암:7271(조작시험),7200(조작시험) *균압콘덴서 절연열화 측정","2024-04-05 09:30","2024-04-05 14:00","2024-04-05 09:30","2024-04-05 14:00","연속"]
[70,"경기","동부","곤지암S/S #1 Sh.R CB","24년 동부 변전협력총액공사","곤지암:7171(조작시험),7179(조작시험) *균압콘덴서 절연열화 측정","2024-04-03 14:00","2024-04-03 18:00","2024-04-03 14:00","2024-04-03 18:00","연속"]
[71,"경기","동부","곤지암S/S CB 7100","24년 동부 변전협력총액공사","곤지암:7171(조작시험),7179(조작시험) *균압콘덴서 절연열화 측정","2024-04-03 09:30","2024-04-03 14:00","2024-04-03 09:30","2024-04-03 14:00","연속"]
[72,"경기","동부","곤지암S/S #1 M.Tr","24년 동부 변전협력총액공사","곤지암:7172(조작시험),7100(조작시험) *균압콘덴서 절연열화 측정 4189(조작시험)","2024-04-01 09:00","2024-04-01 18:00","2024-04-01 09:00","2024-04-01 18:00","연속"]
[73,"경기","동부","곤지암S/S CB 7200","24년 동부 변전협력총액공사","곤지암:7271(조작시험),7200(조작시험) *균압콘덴서 절연열화 측정","2024-04-05 14:00","2024-04-05 18:00","2024-04-05 14:00","2024-04-05 18:00","연속"]
[74,"경기","성남","신성남S/S STATCOM CB","24년 성남전력지사 변전협력회사 총액공사","- 7000,7072 GIS 조작시험 - STATCOM 열화상카메라 보수","2024-04-01 09:00","2024-04-05 18:00","취소","취소","연속"]
[75,"경기","성남","신성남동서울#1 T/L","345kV 신성남-동서울T/L No.46 애자련 보강","345kV 신성남-동서울T/L No.46 애자련 보강 변경전 : 현수 1련, 변경후 : 현수 2련 사유 : 서울-세종 고속도로 횡단개소 애자련 보강","2024-04-29 07:00","2024-04-29 18:00","취소","취소","연속"]
[76,"경기","성남","신성남동서울#2 T/L","345kV 신성남-동서울T/L No.46 애자련 보강","345kV 신성남-동서울T/L No.46 애자련 보강 변경전 : 현수 1련, 변경후 : 현수 2련 사유 : 서울-세종 고속도로 횡단개소 애자련 보강","2024-04-30 07:00","2024-04-30 18:00","취소","취소","연속"]
[77,"경기","성남","신안성신수원#2 T/L","24년 성남전력지사 변전협력회사 총액공사","7A BAY B/F PNL 대체","2024-04-15 09:00","2024-04-23 18:00","2024-04-15 09:00","2024-04-23 18:00","연속"]
[78,"경기","성남","신용인S/S #4 M.Tr","2024년 성남전력 345, 154 GIS 보통점검공사","7800, 7872 보통점검 2차 GIS 보통점검 1,2,3차 LA 보통점검","2024-04-04 09:00","2024-04-05 18:00","2024-04-04 09:00","2024-04-05 18:00","연속"]
[79,"경기","성남","신수원S/S #3 M.Tr","2024년 성남전력 345, 154 GIS 보통점검공사","7500, 7572 GIS 보통점검 2차 GIS 조작시험 1차, 2차 LA 하자점검 부싱절연유 채유 ","2024-04-11 09:30","2024-04-11 18:00","2024-04-11 09:30","2024-04-11 18:00","연속"]
[80,"경기","직할","화성S/S #3 M.Tr","345kV 화성S/S GIS 용량대체공사","345kV #75BUS GIS 용량대체 안전이격거리 확보","2024-04-22 09:00","2024-04-25 18:00","2024-04-22 09:00","2024-04-25 18:00","연속"]
[81,"경기","직할","화성S/S #2 M.Tr","345kV 화성S/S GIS 용량대체공사","345kV #75BUS GIS 용량대체 안전이격거리 확보","2024-04-13 07:00","2024-04-14 18:00","2024-04-13 07:00","2024-04-14 18:00","연속"]
[82,"경기","직할","화성S/S #1 M.Tr","345kV 화성S/S GIS 용량대체공사","345kV #75BUS GIS 용량대체 안전이격거리 확보","2024-04-06 07:00","2024-04-07 18:00","2024-04-06 07:00","2024-04-07 18:00","연속"]
[83,"경기","직할","화성S/S #75 BUS","345kV 화성S/S GIS 용량대체공사","345kV #75BUS GIS 용량대체","2024-04-01 07:00","2024-05-17 18:00","2024-04-01 07:00","2024-05-17 18:00","연속"]
[84,"경기","평택","고덕S/S #1 M.Tr","고덕S/S 345kV M.Tr 2차 GIB 과열개선","고덕S/S 345kV #1M.Tr 2차 GIB 과열개선","2024-04-15 09:00","2024-04-19 18:00","2024-04-15 09:00","2024-04-19 18:00","연속"]
[85,"강원","강릉","강릉T/P CB 7100","2024년 강릉전력지사 변전협력회사 총액공사","362kV GIS 하자점검","2024-04-09 10:00","2024-04-09 18:00","2024-04-09 10:00","2024-04-09 18:00","연속"]
[86,"강원","강릉","강릉T/P CB 7271","2024년 강릉전력지사 변전협력회사 총액공사","362kV GIS 하자점검","2024-04-11 10:00","2024-04-11 18:00","2024-04-11 10:00","2024-04-11 18:00","연속"]
[87,"강원","강릉","강릉T/P CB 7172","2024년 강릉전력지사 변전협력회사 총액공사","362kV GIS 하자점검","2024-04-16 10:00","2024-04-16 18:00","2024-04-16 10:00","2024-04-16 18:00","연속"]
[88,"강원","강릉","강릉T/P CB 7200","2024년 강릉전력지사 변전협력회사 총액공사","362kV GIS 하자점검","2024-04-12 10:00","2024-04-12 18:00","2024-04-12 10:00","2024-04-12 18:00","연속"]
[89,"강원","강릉","강릉T/P CB 7272","2024년 강릉전력지사 변전협력회사 총액공사","362kV GIS 하자점검","2024-04-17 10:00","2024-04-17 18:00","2024-04-17 10:00","2024-04-17 18:00","연속"]
[90,"강원","강릉","강릉T/P CB 7171","2024년 강릉전력지사 변전협력회사 총액공사","362kV GIS 하자점검","2024-04-08 10:00","2024-04-08 18:00","2024-04-08 10:00","2024-04-08 18:00","연속"]
[91,"강원","강릉","안인개폐소양양PP T/L","2024-2025년 송전협력회사 공사","○ 점퍼스페이서댐퍼 교체 : 345kV 양양양수T/L No.25, 148","2024-04-25 08:00","2024-04-26 18:00","2024-04-25 08:00","2024-04-26 18:00","매일"]
[92,"강원","강릉","안인개폐소 CB 7472","2024년 강릉전력지사 변전협력회사 총액공사","362kV GIS 하자점검","2024-04-05 10:00","2024-04-05 18:00","2024-04-29 09:00","2024-04-29 18:00","연속"]
[93,"강원","강릉","안인개폐소 CB 7400","2024년 강릉전력지사 변전협력회사 총액공사","362kV GIS 하자점검","2024-04-04 10:00","2024-04-04 18:00","2024-04-04 10:00","2024-04-04 18:00","연속"]
[94,"강원","강릉","안인개폐소 CB 7300","2024년 강릉전력지사 변전협력회사 총액공사","362kV GIS 하자점검","2024-04-02 10:00","2024-04-02 18:00","2024-04-02 10:00","2024-04-02 18:00","연속"]
[95,"강원","강릉","안인개폐소 CB 7272","2024년 강릉전력지사 변전협력회사 총액공사","362kV GIS 하자점검","2024-04-01 10:00","2024-04-01 18:00","2024-04-01 10:00","2024-04-01 18:00","연속"]
[96,"강원","강릉","안인개폐소 CB 7372","2024년 강릉전력지사 변전협력회사 총액공사","362kV GIS 하자점검","2024-04-03 10:00","2024-04-03 18:00","2024-04-03 10:00","2024-04-03 18:00","연속"]
[97,"강원","동해","동해S/S #2 M.Tr","24년~25년 동해전력지사 변전정비회사 총액공사","2차 GIS 보통점검, 1,2차LA보통점검, 3차CB,DS보통점검, SH.R 보통점검","2024-04-22 09:30","2024-04-24 18:00","2024-04-29 09:00","2024-05-01 18:00","연속"]
[98,"충북","직할","신진천S/S #5 M.Tr","24-25년 충북직할 변전협력회사 공사","신진천S/S 345kV #5M.Tr 보통점검 신진천S/S 345kV #5M.Tr 1차 GIS 보통점검","2024-04-15 09:00","2024-04-17 18:00","2024-04-15 09:00","2024-04-17 18:00","연속"]
[99,"충북","청주","세종남청주#1 T/L","345kV 신옥천북경남등 8개T/L 추락방지장치 설치공사","345kV 세종남청주 #1T/L 추락방지장치 설치(수평설치) 1. 내용 : 세종남청주#1T/L 수평 추락방지장치 설치 2. 구간 : No.31~56","2024-04-01 07:00","2024-04-04 18:00","2024-04-01 07:00","2024-04-04 18:00","매일"]
[100,"충북","청주","세종남청주#2 T/L","345kV 신옥천북경남등 8개T/L 추락방지장치 설치공사","345kV 세종남청주 #2T/L 추락방지장치 설치(수평설치) 1. 내용 : 세종남청주#2T/L 수평 추락방지장치 설치 2. 구간 : No.31~56","2024-04-11 07:00","2024-04-14 18:00","취소","취소","매일"]
[101,"충북","청주","남청주S/S #2 M.Tr","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-04-15 08:00","2024-05-03 18:00","2024-04-15 08:00","2024-05-03 18:00","연속"]
[102,"충북","청주","신옥천S/S #1 M.Tr","2024~2025년 청주전력지사 변전협력회사 공사","3차측 23kV VCB 교체(1-1,1-2), 점검(4179) 23kV Sh.R 보통점검(1-1,1-2) M.Tr 2차측 피뢰기 교체","2024-04-16 09:00","2024-04-18 18:00","2024-04-16 09:00","2024-04-18 18:00","연속"]
[103,"충북","청주","신옥천세종#1 T/L","345kV 신옥천북경남등 8개T/L 추락방지장치 설치공사","345kV 신옥천세종 #1T/L 추락방지장치 설치(수평설치) 1. 내용 : 신옥천세종#1T/L 수평 추락방지장치 설치 2. 구간 : No.1~48","2024-04-11 07:00","2024-04-18 18:00","취소","취소","매일"]
[104,"충북","청주","신옥천세종#2 T/L","345kV 신옥천북경남등 8개T/L 추락방지장치 설치공사","345kV 신옥천세종 #2T/L 추락방지장치 설치(수평설치) 1. 내용 : 신옥천세종#2T/L 수평 추락방지장치 설치 2. 구간 : No.1~48","2024-04-19 07:00","2024-04-26 18:00","취소","취소","매일"]
[105,"충북","청주","신옥천S/S #2 M.Tr","2024~2025년 청주전력지사 변전협력회사 공사","345kV M.Tr 보통점검 3차측 23kV VCB 교체(2-1,2-2) 23kV Sh.R 보통점검(2-1,2-2) M.Tr 2차측 피뢰기 교체","2024-04-22 09:00","2024-04-25 18:00","2024-04-22 09:00","2024-04-25 18:00","연속"]
[106,"충북","충주","신제천S/S CB 7471","'24-25년 충주전력지사 변전정비 총액공사","신제천S/S 345kV 여주복합T/L LA 대체공사","2024-04-26 09:00","2024-04-26 14:00","2024-04-26 09:00","2024-04-26 14:00","연속"]
[107,"충북","충주","신제천S/S CB 7371","'24-25년 충주전력지사 변전정비 총액공사","신제천S/S 345kV 신제천-신충주#2T/L GIS 및 LA 보통점검","2024-04-25 09:00","2024-04-25 18:00","2024-04-25 09:00","2024-04-25 18:00","연속"]
[108,"충북","충주","신제천S/S CB 7771","'24-25년 충주전력지사 변전정비 총액공사","신제천S/S 345kV 신제천-신영주#2T/L GIS 보통점검 및 LA 보통점검","2024-04-24 09:00","2024-04-24 18:00","2024-04-24 09:00","2024-04-24 18:00","연속"]
[109,"충북","충주","신제천S/S #4 M.Tr","'24-25년 충주전력지사 변전정비 총액공사","신제천S/S 345kV #4M.Tr 본체 초기점검 및 4289 VCB 보통점검","2024-04-22 09:00","2024-04-24 18:00","2024-04-22 09:00","2024-04-24 18:00","연속"]
[110,"충북","충주","신제천S/S #3 M.Tr","'24-25년 충주전력지사 변전정비 총액공사","신제천S/S 345kV #3M.Tr 본체 보통점검 / 7772,7700,6344 GIS 보통점검 / 3차 GPT 보통점검 / 1차 CVT 보통점검 4375,4175-11/12,4185,4385DS 보통점검 / 4189,4389,4379,4179-11,12 VCB 보통점검","2024-04-15 09:00","2024-04-18 18:00","2024-04-15 09:00","2024-04-18 18:00","연속"]
[111,"대전세종충남","서산","신당진개폐소태안TP#1 T/L","'23년 서산P/O 장기사용 배전반 교체공사","신당진개폐소, 태안화력S/Y 345kV 개폐소-태안화력#1T/L 보호반 대체공사","2024-04-29 09:00","2024-05-03 18:00","취소","취소","연속"]
[112,"대전세종충남","서산","신당진S/S #3 M.Tr","24년 서산P/O 변전협력회사 총액공사","신당진S/S 345kV #3M.Tr 3차측 4395 DS 과열발생에 의한 (신당진S/S 23kV Sh.R 미운전시 즉시가압 가능)","2024-04-16 09:00","2024-04-18 18:00","2024-04-16 09:00","2024-04-18 18:00","연속"]
[113,"대전세종충남","서산","신당진S/S #2 M.Tr","'24년 서산P/O 변전협력회사 총액공사","신당진S/S 345kV #2M.Tr B,C상 공기주머니 교체","2024-04-03 09:00","2024-04-05 18:00","2024-04-03 09:00","2024-04-05 18:00","연속"]
[114,"대전세종충남","서산","신서산신당진#1 T/L","345kV 신서산-태안화력등 19개 T/L 수평추락방지설치공사","345kV 신서산-신당진#1T/L 수평추락방지설치공사 (NO.1~6, 33~42 등 16기)","2024-04-29 08:00","2024-04-30 18:00","취소","취소","매일"]
[115,"대전세종충남","서산","신서산S/S #3 Sh.R CB","'24년 서산P/O 345kV GIS 보통점검공사","신서산S/S 345kV 7579 GIS 보통점검","2024-04-16 09:30","2024-04-16 18:00","2024-04-16 09:30","2024-04-16 18:00","연속"]
[116,"대전세종충남","서산","신서산S/S CB 7571","'24년 서산P/O 345kV GIS 보통점검공사","신서산S/S 345kV 7571 GIS 보통점검","2024-04-18 09:30","2024-04-18 18:00","2024-04-18 09:30","2024-04-18 18:00","연속"]
[117,"대전세종충남","서산","신서산아산#2 T/L","'24~'25년도 송전협력회사 공사","(송전)345kV 신서산-신당진#1T/L 항공구 설치공사(병가선로) No.32~33, 39~40","2024-04-29 08:00","2024-04-29 18:00","2024-04-29 08:00","2024-04-29 18:00","매일"]
[118,"대전세종충남","서산","신서산아산#1 T/L","'24~'25년도 송전협력회사 공사","(송전)345kV 신서산-신당진#2T/L 항공구 설치공사(병가선로) No.32~33, 39~40","2024-04-09 08:00","2024-04-09 18:00","취소","취소","매일"]
[119,"대전세종충남","서산","신서산S/S CB 7771","'23년 서산P/O 장기사용 배전반 교체공사","신서산S/S 345kV 77BAY B/F 보호반 대체공사","2024-04-08 09:00","2024-04-12 18:00","취소","취소","연속"]
[120,"대전세종충남","서산","신서산신당진#2 T/L","'23년 서산P/O 장기사용 배전반 교체공사","신서산S/S 345kV 77BAY B/F 보호반 대체공사","2024-04-08 09:00","2024-04-12 18:00","취소","취소","연속"]
[121,"대전세종충남","서산","신서산S/S CB 7672","'24년 서산P/O 345kV GIS 보통점검공사","신서산S/S 345kV 7672 GIS 보통점검","2024-04-02 09:30","2024-04-02 18:00","2024-04-02 09:30","2024-04-02 18:00","연속"]
[122,"대전세종충남","서산","신서산S/S CB 7A00","'24년 서산P/O 345kV GIS 보통점검공사","신서산S/S 345kV 7A00 GIS 보통점검","2024-04-04 09:30","2024-04-04 18:00","2024-04-04 09:30","2024-04-04 18:00","연속"]
[123,"대전세종충남","서산","태안T/P CB 7571","'24년 서산P/O 345kV GIS 보통점검공사","태안화력S/Y 345kV 7571 GIS 보통점검","2024-04-23 09:30","2024-04-23 18:00","취소","취소","연속"]
[124,"대전세종충남","서산","태안T/P #71 BUS","태안화력S/Y 345kV 현대제 차단기 조작로드 교체공사","태안화력S/Y 345kV 현대제 차단기 조작로드 교체공사 (71-72-0 SEC CB) (CB 상부로 BUS가 지나감으로 인한 BUS 휴전신청)","2024-04-08 09:00","2024-04-19 18:00","취소","취소","연속"]
[125,"대전세종충남","서산","태안T/P SEC CB 76770","'24년 서산P/O 345kV GIS 보통점검공사","태안화력S/Y 345kV 76-77-0 SEC GIS 보통점검","2024-04-25 09:30","2024-04-25 18:00","2024-04-25 09:30","2024-04-25 18:00","연속"]
[126,"대전세종충남","세종","세종S/S #3 M.Tr","[변전]'24년 세종전력지사 변전협력회사 총액공사","○ 345kV M.Tr 보통점검 - 1/2/3차 GIS, 3차 LA 보통점검 병행","2024-04-01 09:00","2024-04-03 18:00","2024-04-01 09:00","2024-04-03 18:00","연속"]
[127,"대전세종충남","천안","신온양서서울#1 T/L","(3월취소시)신온양S/S 345kV 78B/F 교체 및 결상회로 보완작업","(3월취소시)신온양S/S 345kV 78B/F 교체 및 결상회로 보완작업","2024-04-22 09:00","2024-04-25 18:00","취소","취소","연속"]
[128,"대전세종충남","천안","신온양신탕정#2 T/L","(3월취소시)신온양S/S 345kV 78B/F 교체 및 결상회로 보완작업","(3월취소시)신온양S/S 345kV 78B/F 교체 및 결상회로 보완작업","2024-04-22 09:00","2024-04-25 18:00","취소","취소","연속"]
[129,"대전세종충남","천안","신온양S/S #4 M.Tr","(3월취소시)신온양S/S 345kV 77B/F 교체 및 결상회로 보완작업","(3월취소시)신온양S/S 345kV 77B/F 교체 및 결상회로 보완작업","2024-04-15 09:00","2024-04-18 18:00","취소","취소","연속"]
[130,"대전세종충남","천안","신온양서서울#2 T/L","(3월취소시)신온양S/S 345kV 77B/F 교체 및 결상회로 보완작업","(3월취소시)신온양S/S 345kV 77B/F 교체 및 결상회로 보완작업","2024-04-15 09:00","2024-04-18 18:00","취소","취소","연속"]
[131,"대전세종충남","천안","신온양S/S #3 M.Tr","신탕정S/S 345kV #3M.Tr 부싱절연유 채유","신탕정S/S 345kV #3M.Tr 부싱절연유 채유","2024-04-11 09:00","2024-04-11 18:00","2024-04-11 09:00","2024-04-11 18:00","연속"]
[132,"대전세종충남","천안","신온양S/S CB 7900","신온양S/S 345kV 7971, 7900 CB 개폐타임 측정","신온양S/S 345kV 7971, 7900 CB 개폐타임 측정","2024-04-08 14:00","2024-04-08 18:00","2024-04-08 14:00","2024-04-08 18:00","연속"]
[133,"대전세종충남","천안","신온양S/S CB 7971","신온양S/S 345kV 7971, 7900 CB 개폐타임 측정","신온양S/S 345kV 7971, 7900 CB 개폐타임 측정","2024-04-08 09:00","2024-04-08 14:00","2024-04-08 09:00","2024-04-08 14:00","연속"]
[134,"대전세종충남","천안","신온양신탕정#2 T/L","345kV 신온양-신탕정T/L 추락방지장치 설치공사","345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치","2024-04-08 07:00","2024-04-12 18:00","취소","취소","매일"]
[135,"대전세종충남","천안","신온양신탕정#1 T/L","345kV 신온양-신탕정T/L 추락방지장치 설치공사","345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치","2024-04-01 07:00","2024-04-05 18:00","취소","취소","매일"]
[136,"대전세종충남","천안","신탕정S/S CB 7400","신탕정S/S 345kV 7400 GIS 보통점검","신탕정S/S 345kV 7400 GIS 보통점검","2024-04-09 09:00","2024-04-09 18:00","2024-04-09 09:00","2024-04-09 18:00","연속"]
[137,"대전세종충남","천안","신탕정S/S CB 7371","신탕정S/S 345kV 7300 GIS 보통점검","신탕정S/S 345kV 7300 GIS 보통점검","2024-04-08 09:00","2024-04-08 18:00","2024-04-08 09:00","2024-04-08 18:00","연속"]
[138,"대전세종충남","천안","청양신탕정#1 T/L","345kV 신온양-신탕정T/L 추락방지장치 설치공사","[병가철탑]345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치","2024-04-08 07:00","2024-04-12 18:00","취소","취소","매일"]
[139,"대전세종충남","천안","청양신탕정#2 T/L","345kV 신온양-신탕정T/L 추락방지장치 설치공사","[병가철탑]345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치","2024-04-01 07:00","2024-04-05 18:00","취소","취소","매일"]
[140,"대전세종충남","천안","신탕정S/S CB 7300","신탕정S/S 345kV 7371 GIS 보통점검","신탕정S/S 345kV 7371 GIS 보통점검","2024-04-05 09:00","2024-04-05 18:00","2024-04-05 09:00","2024-04-05 18:00","연속"]
[141,"대전세종충남","천안","신탕정S/S 7172","신탕정S/S 345kV 7172 GIS 보통점검","신탕정S/S 345kV 7172 GIS 보통점검","2024-04-02 09:00","2024-04-02 18:00","2024-04-02 09:00","2024-04-02 18:00","연속"]
[142,"대전세종충남","천안","신탕정S/S CB 7200","신탕정S/S 345kV 7200 GIS 보통점검","신탕정S/S 345kV 7200 GIS 보통점검","2024-04-03 09:00","2024-04-03 18:00","2024-04-03 09:00","2024-04-03 18:00","연속"]
[143,"대전세종충남","천안","신탕정S/S CB 7272","신탕정S/S 345kV 7272 GIS 보통점검","신탕정S/S 345kV 7272 GIS 보통점검","2024-04-04 09:00","2024-04-04 18:00","2024-04-04 09:00","2024-04-04 18:00","연속"]
[144,"대전세종충남","천안","신탕정S/S CB 7100","신탕정S/S 345kV 7100 GIS 보통점검","신탕정S/S 345kV 7100 GIS 보통점검","2024-04-01 09:00","2024-04-01 18:00","2024-04-01 09:00","2024-04-01 18:00","연속"]
[145,"대전세종충남","천안","아산보령TP#1 T/L","아산S/S 23kV #1-1Sh.R 설치 관련 안전이격거리 확보","(청양P/O 신청분 취소시)아산S/S 23kV #1-1Sh.R 설치 관련 안전이격거리 확보 유사시 30분이내 즉시가압 가능","2024-04-24 09:00","2024-04-24 18:00","취소","취소","연속"]
[146,"대전세종충남","천안","아산보령TP#2 T/L","345kV 아산-보령화력T/L 추락방지장치 설치공사","345kV 아산-보령화력T/L No. 124 ~ 190 수평 추락방지장치 설치","2024-04-15 07:00","2024-04-19 18:00","취소","취소","매일"]
[147,"대전세종충남","천안","아산S/S #1 M.Tr","아산S/S 23kV #1-1Sh.R 설치관련 무부하가압","아산S/S 23kV #1-1Sh.R 설치관련 무부하가압","2024-04-29 09:00","2024-04-30 18:00","2024-04-29 09:00","2024-04-30 18:00","연속"]
[148,"대전세종충남","천안","아산보령TP#1 T/L","345kV 아산-보령화력T/L 추락방지장치 설치공사","345kV 아산-보령화력T/L No. 124 ~ 190 수평 추락방지장치 설치","2024-04-22 07:00","2024-04-26 18:00","2024-04-22 07:00","2024-04-26 18:00","매일"]
[149,"대전세종충남","청양","아산보령TP#1 T/L","345kV LA, PT GIS 내장화공사(345 아산-보령화력#1)","345kV LA, PT GIS 내장화공사(4.8~4.17) 345 아산-보령화력#1 / #75BUS 휴전","2024-04-01 09:00","2024-04-12 18:00","취소","취소","연속"]
[150,"대전세종충남","청양","보령T/P #75 BUS","345kV LA, PT GIS 내장화공사(345 아산-보령화력#1)","345kV LA, PT GIS 내장화공사(4.8~4.17) 345 아산-보령화력#1 / #75BUS 휴전","2024-04-11 09:00","2024-04-12 18:00","취소","취소","연속"]
[151,"대전세종충남","청양","보령TP보령CC#1 T/L","345kV LA, PT GIS 내장화공사(345 보령연락#1)","345kV LA, PT GIS 내장화공사(4.17~4.27) 345 보령연락#1 / #70BUS 휴전","2024-04-15 09:00","2024-04-26 18:00","취소","취소","연속"]
[152,"대전세종충남","청양","보령T/P #70 BUS","345kV LA, PT GIS 내장화공사(345 보령연락#1)","345kV LA, PT GIS 내장화공사(4.17~4.27) 345 보령연락#1 / #70BUS 휴전","2024-04-25 09:00","2024-04-26 18:00","취소","취소","연속"]
[153,"대전세종충남","청양","보령TP보령CC#1 T/L","보령화력 345kV LA & PT 내장화 공사","보령화력 345kV LA & PT 내장화공사 관련 무부하 가압","2024-04-11 09:00","2024-04-12 18:00","취소","취소","연속"]
[154,"대전세종충남","청양","아산보령TP#1 T/L","보령화력 345kV LA & PT 내장화 공사","보령화력 345kV LA & PT 내장화공사 관련 무부하 가압","2024-04-24 09:00","2024-04-26 18:00","취소","취소","연속"]
[155,"대전세종충남","청양","청양신탕정#1 T/L","(3월취소시)345 73BAY B/F, 청양-신탕정#1T/L 보호반 대체","(3월취소시)청양S/S 345kV 73BAY B/F 보호반 및 청양신탕정#1T/L 보호반 대체(4.8~4.13) (73BAY 휴전 불가시 청양-신탕정 #1T/L 만 단독 휴전 4.8~4.13) - 7300, 7371, 7372 조작시험 병행","2024-04-08 09:00","2024-04-13 18:00","취소","취소","연속"]
[156,"대전세종충남","청양","신계룡청양 T/L","[송전] 345kV 신옥천-청양T/L 수평 추락방지장치 설치공사","345kV 신옥천-청양T/L 수평 추락방지장치 설치공사 (65기)","2024-04-12 07:00","2024-04-24 18:00","2024-04-12 07:00","2024-04-24 18:00","매일"]
[157,"대전세종충남","청양","청양신보령TP T/L","(3월취소시)청양P/O 변전협력회사 총액공사","(3월취소시)345kV 청양-신보령T/L 보호반 대체공사 - 청양S/S 7271 , 7200 조작시험, - 청양S/S LA 하자점검(A,B,C)","2024-04-25 09:00","2024-04-27 18:00","취소","취소","연속"]
[158,"대전세종충남","청양","청양군산#2 T/L","(3월취소시)345 73BAY B/F, 청양-신탕정#1T/L 보호반대체","(3월취소시)청양S/S 345kV 73BAY B/F 보호반 및 청양신탕정#1T/L 보호반 대체(4.8~13) (73BAY 휴전 불가시 청양-신탕정 #1T/L 만 단독 휴전 4.8~4.13) - 7300, 7371, 7372 조작시험 병행","2024-04-08 09:00","2024-04-13 18:00","취소","취소","연속"]
[159,"전북","군산","군산S/S #75 BUS","군산변전소 345kV GIS 대체공사","○ 362kV GIS 40kV 4000A × 10CB 철거(4Bay, PT Bay 포함) ○ 362kV GIS 50kV 4000A × 10CB 설치(4Bay, PT Bay 포함) ○ 362kV GIS 50kV 4000A × 10CB 설치(4Bay, PT Bay 포함) ○ 기타부대공사 × 1식","2024-04-30 08:00","2024-05-07 18:00","취소","취소","연속"]
[160,"전북","군산","군산S/S #70 BUS","군산변전소 345kV GIS 대체공사","○ 362kV GIS 40kV 4000A × 10CB 철거(4Bay, PT Bay 포함) ○ 362kV GIS 50kV 4000A × 10CB 설치(4Bay, PT Bay 포함) ○ 362kV GIS 50kV 4000A × 10CB 설치(4Bay, PT Bay 포함) ○ 기타부대공사 × 1식","2024-04-22 08:00","2024-04-29 18:00","취소","취소","연속"]
[161,"전북","군산","새만금S/S #1 Sh.R CB","군산P/O 조상설비 점검공사","- 345kV #1Sh.R 보통점검","2024-04-17 09:00","2024-04-19 18:00","2024-04-17 09:00","2024-04-19 18:00","연속"]
[162,"전북","김제","신김제S/S #2 M.Tr","신김제S/S 345kV #2M.Tr 1,2차 부싱유 채유","신김제S/S 345kV #2M.Tr 1,2차 부싱유 채유","2024-04-04 09:00","2024-04-04 18:00","2024-04-04 09:00","2024-04-04 18:00","연속"]
[163,"전북","직할","신남원광양#2 T/L","24년 전북직할 변전협력 총액공사","신남원-광양 #2 T/L LA, CVT 보통점검","2024-04-24 09:00","2024-04-24 18:00","2024-04-24 09:00","2024-04-24 18:00","연속"]
[164,"전북","군산","군산S/S CB 7600","군산변전소 345kV GIS 대체공사","○ 362kV GIS 40kV 4000A × 10CB 철거(4Bay, PT Bay 포함) ○ 362kV GIS 50kV 4000A × 10CB 설치(4Bay, PT Bay 포함) ○ 362kV GIS 50kV 4000A × 10CB 설치(4Bay, PT Bay 포함) ○ 기타부대공사 × 1식","2024-04-28 18:00","2024-04-29 18:00","2024-04-28 18:00","2024-04-29 18:00","연속"]
[165,"광주전남","광주","신광주S/S CB 7571","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-22 09:00","2024-04-22 18:00","2024-04-22 09:00","2024-04-22 18:00","연속"]
[166,"광주전남","광주","신광주S/S CB 7800","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-16 09:00","2024-04-16 18:00","2024-04-16 09:00","2024-04-16 18:00","연속"]
[167,"광주전남","광주","신광주S/S CB 7472","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-24 09:00","2024-04-24 18:00","2024-04-24 09:00","2024-04-24 18:00","연속"]
[168,"광주전남","광주","신광주S/S CB 7400","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-25 09:00","2024-04-25 18:00","2024-04-25 09:00","2024-04-25 18:00","연속"]
[169,"광주전남","광주","신남원신광주#1 T/L","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-25 09:00","2024-04-26 18:00","취소","취소","연속"]
[170,"광주전남","광주","신광주S/S CB 7471","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-26 09:00","2024-04-26 18:00","2024-04-26 09:00","2024-04-26 18:00","연속"]
[171,"광주전남","광주","신광주S/S CB 7371","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-29 09:00","2024-04-29 18:00","2024-04-29 09:00","2024-04-29 18:00","연속"]
[172,"광주전남","광주","신남원신광주#2 T/L","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-29 09:00","2024-04-30 18:00","취소","취소","연속"]
[173,"광주전남","광주","신광주S/S CB 7300","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-30 09:00","2024-04-30 18:00","2024-04-30 09:00","2024-04-30 18:00","연속"]
[174,"광주전남","광주","신광주신화순#1 T/L","24~25년 광주전력지사 송전협력회사 총액공사","345kV 신광주-신화순#1T/L 수평 추락방지장치 설치공사(No.1~121)","2024-04-01 07:00","2024-04-12 18:00","2024-04-01 07:00","2024-04-12 18:00","매일"]
[175,"광주전남","광주","신광주신화순#2 T/L","24~25년 광주전력지사 송전협력회사 총액공사","345kV 신광주-신화순#2T/L 수평 추락방지장치 설치공사(No.1~121)","2024-04-15 07:00","2024-04-26 18:00","2024-04-15 07:00","2024-04-26 18:00","매일"]
[176,"광주전남","광주","신광주S/S #1 M.Tr","2024~2025년 광주전력지사 변전협력회사 공사","-주변압기 보통점검 -7172보통점검","2024-04-02 09:00","2024-04-05 18:00","2024-04-02 09:00","2024-04-05 18:00","연속"]
[177,"광주전남","광주","신광주S/S #1 Sh.R CB","2024~2025년 광주전력지사 변전협력회사 공사","#1Sh.R 1차(7572), 선로측(7579) CB 조작시험","2024-04-08 09:00","2024-04-08 18:00","2024-04-08 09:00","2024-04-08 18:00","연속"]
[178,"광주전남","광주","신광주S/S CB 7872","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-15 09:00","2024-04-15 18:00","2024-04-15 09:00","2024-04-15 18:00","연속"]
[179,"광주전남","광주","신광주S/S CB 7600","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-19 09:00","2024-04-19 18:00","2024-04-19 09:00","2024-04-19 18:00","연속"]
[180,"광주전남","광주","신광주S/S CB 7671","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-18 09:00","2024-04-18 18:00","2024-04-18 09:00","2024-04-18 18:00","연속"]
[181,"광주전남","광주","신광주S/S CB 7672","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-17 09:00","2024-04-17 18:00","2024-04-17 09:00","2024-04-17 18:00","연속"]
[182,"광주전남","광주","신광주S/S #4 M.Tr","2024~2025년 광주전력지사 변전협력회사 공사","-주변압기 보통점검 -7800,7872 보통","2024-04-16 09:00","2024-04-19 18:00","2024-04-16 09:00","2024-04-19 18:00","연속"]
[183,"광주전남","광주","신광주S/S CB 7500","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-23 09:00","2024-04-23 18:00","2024-04-23 09:00","2024-04-23 18:00","연속"]
[184,"광주전남","광주","신화순S/S CB 7972","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-01 09:00","2024-04-01 18:00","2024-04-01 09:00","2024-04-01 18:00","연속"]
[185,"광주전남","광주","신화순S/S #1 M.Tr","24년 광주전력지사 170kV 이상 GIS 보통점검","- 170kV GIS 보통점검","2024-04-01 09:00","2024-04-02 18:00","2024-04-01 09:00","2024-04-02 18:00","연속"]
[186,"광주전남","광주","신화순S/S CB 7900","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-02 09:00","2024-04-02 18:00","2024-04-02 09:00","2024-04-02 18:00","연속"]
[187,"광주전남","광주","신화순S/S CB 7971","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-03 09:00","2024-04-03 18:00","2024-04-03 09:00","2024-04-03 18:00","연속"]
[188,"광주전남","광주","신화순S/S CB 7871","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-04 09:00","2024-04-04 18:00","2024-04-04 09:00","2024-04-04 18:00","연속"]
[189,"광주전남","광주","신화순S/S CB 7800","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-05 09:00","2024-04-05 18:00","2024-04-05 09:00","2024-04-05 18:00","연속"]
[190,"광주전남","광주","신화순S/S CB 7A71","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-08 09:00","2024-04-08 18:00","2024-04-08 09:00","2024-04-08 18:00","연속"]
[191,"광주전남","광주","신화순신강진#1 T/L","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-08 09:00","2024-04-09 18:00","2024-04-08 09:00","2024-04-09 18:00","연속"]
[192,"광주전남","광주","신화순S/S CB 7A00","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-09 09:00","2024-04-09 18:00","2024-04-09 09:00","2024-04-09 18:00","연속"]
[193,"광주전남","광주","신화순S/S #2 M.Tr","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-10 09:00","2024-04-11 18:00","2024-04-10 09:00","2024-04-11 18:00","연속"]
[194,"광주전남","광주","신화순S/S CB 7772","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-10 09:00","2024-04-10 18:00","2024-04-10 09:00","2024-04-10 18:00","연속"]
[195,"광주전남","광주","신화순S/S #3 M.Tr","2024~2025년 광주전력지사 변전협력회사 공사","-주변압기 보통점검","2024-04-30 09:00","2024-05-03 18:00","2024-04-30 09:00","2024-05-03 18:00","연속"]
[196,"광주전남","광주","신화순S/S CB 7700","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-11 09:00","2024-04-11 18:00","2024-04-11 09:00","2024-04-11 18:00","연속"]
[197,"광주전남","광주","신화순S/S CB 7771","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-04-12 09:00","2024-04-12 18:00","2024-04-12 09:00","2024-04-12 18:00","연속"]
[198,"광주전남","목포","한빛1NP한빛2NP#1 T/L","2024~2025년 목포전력지사 변전협력회사 공사","한빛#1S/Y 7372, 7300 GIS 조작시험 한빛#2S/Y 7572 GIS 초기점검","2024-04-15 09:00","2024-04-16 18:00","2024-04-15 09:00","2024-04-16 18:00","연속"]
[199,"광주전남","목포","한빛2NP한빛3NP#4 T/L","2024~2025년 목포전력지사 변전협력회사 공사","한빛#2S/Y 7A72 GIS 초기시험 한빛#3S/Y 7B72, 7B00 GIS 하자점검","2024-04-22 09:00","2024-04-24 18:00","2024-04-22 09:00","2024-04-24 18:00","연속"]
[200,"광주전남","목포","한빛1NP한빛2NP#2 T/L","2024~2025년 목포전력지사 변전협력회사 공사","한빛#1S/Y 7472, 7400 GIS 조작시험 한빛#2S/Y 7572 GIS 초기점검","2024-04-17 09:00","2024-04-18 18:00","2024-04-17 09:00","2024-04-18 18:00","연속"]
[201,"광주전남","순천","광양S/S #2 M.Tr","345kV 광양S/S 362kV GIS 용량변경 교체공사(#75BUS)","345kV 광양S/S 362kV GIS 용량변경 교체공사(#75BUS 관련) -362kV GIS #75BUS(74,75,76BAY) 교체공사 안전이격","2024-04-18 08:00","2024-04-20 18:00","2024-04-18 08:00","2024-04-20 18:00","연속"]
[202,"광주전남","순천","광양광양제철#2 T/L","고객 측 휴전 요청","광양제철T/L 용량증대공사 광양제철소 공사감독자 진선화(010-3520-5031)","2024-04-22 07:00","2024-05-11 18:00","2024-04-22 07:00","2024-05-11 18:00","연속"]
[203,"광주전남","순천","광양S/S SEC CB 70710","345kV 광양S/S 362kV GIS 용량변경 교체공사(무부하)","345kV 광양S/S 362kV GIS 용량변경 교체공사(#70BUS 무부하) - 362kV GIS(#70BUS) 교체공사 무부하 가압","2024-04-10 08:00","2024-04-11 18:00","2024-04-10 08:00","2024-04-11 18:00","연속"]
[204,"광주전남","순천","광양S/S #75 BUS","345kV 광양S/S 362kV GIS 용량변경 교체공사","345kV 광양S/S 362kV GIS 용량변경 교체공사 - 362kV GIS #75BUS(74,75,76BAY) 교체공사","2024-04-15 08:00","2024-04-30 18:00","2024-04-15 08:00","2024-04-30 18:00","연속"]
[205,"광주전남","순천","광양S/S #1 M.Tr","24-25년 순천전력지사 변전협력회사 공사","광양S/S #1M.Tr , 1차 LA A,B,C, 2차 LA A,B,C, 3차 LA A,B,C, 3차 GPT A,B,C, 3차 MAIN VCB 초기점검","2024-04-15 09:00","2024-04-18 18:00","2024-04-15 09:00","2024-04-18 18:00","연속"]
[206,"광주전남","순천","광양S/S #2 M.Tr","24-25년 순천전력지사 변전협력회사 공사","광양S/S #2M.Tr , 1차 LA A,B,C, 2차 LA A,B,C, 3차 LA A,B,C, 3차 GPT A,B,C, 3차 MAIN VCB 초기점검","2024-04-22 09:00","2024-04-25 18:00","2024-04-22 09:00","2024-04-25 18:00","연속"]
[207,"광주전남","순천","광양S/S SEC CB 75760","345kV 광양S/S 362kV GIS 용량변경 교체공사(무부하)","345kV 광양S/S 362kV GIS 용량변경 교체공사(#75BUS 무부하) - 362kV GIS(#75BUS) 교체공사 무부하 가압","2024-04-29 08:00","2024-04-30 18:00","2024-04-29 08:00","2024-04-30 18:00","연속"]
[208,"광주전남","순천","광양광양CC#2 T/L","고객 측 휴전 요청","작업구간(광양제철) 안전확보 광양제철소 공사감독자 진선화(010-3520-5031)","2024-04-22 07:00","2024-05-11 18:00","2024-04-22 07:00","2024-05-11 18:00","연속"]
[209,"광주전남","순천","광양광양제철#1 T/L","고객 측 휴전 요청","광양제철T/L 용량증대공사 광양제철소 공사감독자 진선화(010-3520-5031)","2024-04-01 07:00","2024-04-21 18:00","2024-04-01 07:00","2024-04-21 18:00","연속"]
[210,"광주전남","순천","광양광양CC#1 T/L","고객 측 휴전 요청","작업구간(광양제철) 안전확보 광양제철소 공사감독자 진선화(010-3520-5031)","2024-04-01 07:00","2024-04-21 18:00","2024-04-01 07:00","2024-04-21 18:00","연속"]
[211,"광주전남","순천","여수T/P CB 7471","여수화력 345kV GIS 모선 PT 회로 개선관련 조작시험","여수화력 345kV GIS 모선 PT 회로 개선관련 조작시험","2024-04-03 09:00","2024-04-03 18:00","2024-04-03 09:00","2024-04-03 18:00","연속"]
[212,"광주전남","순천","여수T/P #75 BUS","여수화력 345kV GIS 모선 PT 회로 개선","여수화력 345kV GIS 모선 PT 회로 개선","2024-04-04 09:00","2024-04-04 18:00","취소","취소","연속"]
[213,"광주전남","순천","광양여수TP T/L","345kV 광양-여수TPT/L 추락방지시설 설치공사","수평 추락방지시설 설치 - No.1~137호, 90기","2024-04-01 07:00","2024-04-09 18:00","2024-04-01 07:00","2024-04-09 18:00","매일"]
[214,"광주전남","순천","여수T/P #70 BUS","여수화력 345kV GIS 모선 PT 회로 개선","여수화력 345kV GIS 모선 PT 회로 개선","2024-04-02 09:00","2024-04-02 18:00","2024-04-02 09:00","2024-04-02 18:00","연속"]
[215,"광주전남","순천","율촌CC여수TP T/L","345kV 율촌CC-여수TPT/L 추락방지시설 설치공사","수평 추락방지시설 설치 - No.1~67호, 67기","2024-04-11 07:00","2024-04-17 18:00","2024-04-11 07:00","2024-04-17 18:00","매일"]
[216,"대구","경산","울주신경산#1 T/L","345kV 울주-신경산 등 6개T/L 수평 추락방지장치설치공사","345kV 울주-신경산#2T/L 수평 추락방지장치설치공사","2024-04-25 07:00","2024-05-21 18:00","2024-04-25 07:00","2024-05-21 18:00","연속"]
[217,"대구","경산","신경산S/S #1 M.Tr","'24년 경산P/O 주변압기 정밀점검 및 보통점검 공사","- M.Tr 보통, 부싱절연유(전문), 7000,7072 보통, 절연열화측정(전문), 6144 조작시험(협력)","2024-04-22 09:30","2024-04-23 18:00","2024-04-22 09:30","2024-04-23 18:00","연속"]
[218,"대구","경산","신경산S/S #2 M.Tr","'24년 경산P/O 주변압기 정밀점검 및 보통점검 공사","- M.Tr 보통, 부싱절연유, 2,3차 LA 보통, 3차PT 보통(전문), 7100,7172 보통(전문)","2024-04-24 09:30","2024-04-25 18:00","2024-04-24 09:30","2024-04-25 18:00","연속"]
[219,"대구","경산","신경산대구#1 T/L","'24년 경산P/O GIS 정밀점검 및 보통점검 공사","- 7171 GIS 보통점검","2024-04-26 09:30","2024-04-26 18:00","취소","취소","연속"]
[220,"대구","경산","신경산S/S #3 M.Tr","'24년 경산P/O 주변압기 정밀점검 및 보통점검 공사","- M.Tr 보통, 부싱절연유, 2,3차 LA 보통, 3차PT 보통(전문), 7300,7372 보통(전문)","2024-04-29 09:30","2024-04-30 18:00","2024-04-29 09:30","2024-04-30 18:00","연속"]
[221,"대구","경산","울주신경산#2 T/L","345kV 울주-신경산 등 6개T/L 수평 추락방지장치설치공사","345kV 울주-신경산#1T/L 수평 추락방지장치설치공사","2024-04-01 07:00","2024-04-24 18:00","2024-04-01 07:00","2024-04-24 18:00","연속"]
[222,"대구","달성","서대구고령#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 서대구-고령T/L 수평 추락방지장치 설치공사(154kV 서대구-남구미 T/L 병가선로)(안전확보)","2024-04-04 07:00","2024-04-12 18:00","2024-04-03 07:00","2024-04-12 18:00","연속"]
[223,"대구","달성","북경남고령#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 북경남-고령T/L 수평 추락방지장치 설치공사(345kV 북경남-대구 T/L병가선로)(안전확보)","2024-04-17 07:00","2024-05-03 18:00","2024-04-17 07:00","2024-05-03 18:00","연속"]
[224,"대구","달성","북경남대구#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 북경남-대구T/L 수평 추락방지장치 설치공사(345kV 북경남-고령 T/L, 대구-청도T/L 병가선로)(안전확보)","2024-04-15 07:00","2024-04-25 18:00","2024-04-15 07:00","2024-04-25 18:00","연속"]
[225,"대구","달성","대구S/S #2 BUS","[TEST] 7300, 7372CB 무부하가압","[TEST] 7300, 7372CB 무부하가압","2024-04-26 17:00","2024-04-26 18:00","2024-04-26 17:00","2024-04-26 18:00","연속"]
[226,"대구","달성","대구S/S #3 M.Tr","#73Bay 정밀점검 및 변압기보호반, 2차 LA 대체","#73Bay 정밀점검 및 변압기보호반, 2차 LA 대체","2024-04-22 09:00","2024-04-26 18:00","2024-04-22 09:00","2024-04-26 18:00","연속"]
[227,"대구","달성","대구S/S #1 BUS","[TEST] 7371CB 무부하가압","[TEST] 7371CB 무부하가압","2024-04-19 17:00","2024-04-19 18:00","2024-04-19 17:00","2024-04-19 18:00","연속"]
[228,"대구","칠곡","북대구S/S CB 7371","북대구S/S 7371 GIS 장기미동작점검","북대구S/S 7371 GIS 장기미동작점검","2024-04-19 09:30","2024-04-19 14:00","2024-04-19 09:30","2024-04-19 14:00","연속"]
[229,"대구","칠곡","북대구S/S CB 7300","북대구S/S 7300 GIS 장기미동작점검","북대구S/S 7300 GIS 장기미동작점검","2024-04-19 14:00","2024-04-19 18:00","2024-04-19 14:00","2024-04-19 18:00","연속"]
[230,"대구","칠곡","북대구S/S CB 7372","북대구S/S 7372 GIS 장기미동작점검","북대구S/S 7372 GIS 장기미동작점검","2024-04-22 09:30","2024-04-22 14:00","2024-04-29 09:30","2024-04-29 14:00","연속"]
[231,"대구","칠곡","북대구S/S CB 7272","북대구S/S 7272 GIS 장기미동작점검","북대구S/S 7272 GIS 장기미동작점검","2024-04-09 14:00","2024-04-09 18:00","2024-04-09 14:00","2024-04-09 18:00","연속"]
[232,"대구","칠곡","북대구S/S CB 7172","북대구S/S 7172 GIS 장기미동작점검","북대구S/S 7172 GIS 장기미동작점검","2024-04-18 14:00","2024-04-18 18:00","2024-04-18 14:00","2024-04-18 18:00","연속"]
[233,"대구","칠곡","북대구S/S CB 7100","북대구S/S 7100 GIS 장기미동작점검","북대구S/S 7100 GIS 장기미동작점검","2024-04-18 09:30","2024-04-18 14:00","2024-04-18 09:30","2024-04-18 14:00","연속"]
[234,"대구","칠곡","북대구S/S CB 7400","북대구S/S 7400 GIS 장기미동작점검","북대구S/S 7400 GIS 장기미동작점검","2024-04-22 14:00","2024-04-22 18:00","2024-04-29 14:00","2024-04-29 18:00","연속"]
[235,"대구","칠곡","북대구S/S CB 7200","북대구S/S 7200 GIS 장기미동작점검","북대구S/S 7200 GIS 장기미동작점검","2024-04-09 09:30","2024-04-09 14:00","2024-04-09 09:30","2024-04-09 14:00","연속"]
[236,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S #1M.Tr 보통점검, 7171 GCB 장기미동작점검","서대구S/S #1M.Tr 보통점검, 7171 GCB 장기미동작점검","2024-04-11 09:30","2024-04-12 18:00","2024-04-11 09:30","2024-04-12 18:00","연속"]
[237,"대구","칠곡","서대구S/S #3 M.Tr","서대구S/S 7671, 7600 GCB 보통점검","서대구S/S 7671, 7600 GCB 보통점검","2024-04-01 09:30","2024-04-01 18:00","2024-04-01 09:30","2024-04-01 18:00","연속"]
[238,"대구","포항","신포항청송PP T/L","345kV 영포 외 15개 T/L 추락방지장치 설치 등 송전정비공사","345kV 신포항-청송PPT/L 수평추락방지장치 설치","2024-04-11 07:00","2024-04-12 18:00","2024-04-11 07:00","2024-04-12 18:00","연속"]
[239,"대구","포항","신포항신영일 T/L","345kV 영포 외 15개 T/L 추락방지장치 설치 등 송전정비공사","345kV 신포항-신영일T/L 수평추락방지장치 설치","2024-04-03 07:00","2024-04-09 18:00","2024-04-03 07:00","2024-04-09 18:00","연속"]
[240,"대구","포항","신포항S/S #2 BUS","2024~25년도 포항전력지사 변전총액공사","신포항S/S 345kV 조작불량 DS 보수","2024-04-15 09:00","2024-04-19 18:00","2024-04-15 09:00","2024-04-19 18:00","연속"]
[241,"대구","포항","월성N/P #71 BUS","월성N/P 연계 345kV GIS 용량대체공사(77Bay 대체)","월성N/P 연계 345kV GIS 용량대체공사 ○ 345kV GIS × 18CB 대체 ○ 보호반 설치 및 이설 ○ 제어케이블 포설 및 결선 ○ 기타 부대공사 × 1식","2024-04-20 09:00","2024-04-24 18:00","2024-04-20 09:00","2024-04-24 18:00","연속"]
[242,"대구","포항","월성N/P #76 BUS","월성N/P 연계 345kV GIS 용량대체공사(77Bay 대체)","월성N/P 연계 345kV GIS 용량대체공사 ○ 345kV GIS × 18CB 대체 ○ 보호반 설치 및 이설 ○ 제어케이블 포설 및 결선 ○ 기타 부대공사 × 1식","2024-04-25 09:00","2024-05-09 18:00","2024-04-25 09:00","2024-05-09 18:00","연속"]
[243,"대구","포항","울주월성NP#1 T/L","월성N/P연계345kVGIS용량대체공사_77Bay 대체_Test선로","월성N/P 연계 345kV GIS 용량대체공사 ○ 345kV GIS × 18CB 대체 ○ 보호반 설치 및 이설 ○ 제어케이블 포설 및 결선 ○ 기타 부대공사 × 1식","2024-04-23 14:00","2024-04-24 09:00","2024-04-23 14:00","2024-04-24 09:00","연속"]
[244,"대구","포항","신울산월성NP#1 T/L","월성N/P 연계 345kV GIS 용량대체공사(77Bay 대체)","월성N/P 연계 345kV GIS 용량대체공사 ○ 345kV GIS × 18CB 대체 ○ 보호반 설치 및 이설 ○ 제어케이블 포설 및 결선 ○ 기타 부대공사 × 1식","2024-04-20 09:00","2024-06-19 18:00","2024-04-20 09:00","2024-06-19 18:00","연속"]
[245,"대구","포항","월성N/P CB 7772","월성N/P 연계 345kV GIS 용량대체공사(77Bay 대체)","월성N/P 연계 345kV GIS 용량대체공사 ○ 345kV GIS × 18CB 대체 ○ 보호반 설치 및 이설 ○ 제어케이블 포설 및 결선 ○ 기타 부대공사 × 1식","2024-04-20 09:00","2024-06-19 18:00","2024-04-20 09:00","2024-06-19 18:00","연속"]
[246,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사(4차)","○ 70BAY GIS 교체(70BUS 무부하 가압)","2024-04-22 09:00","2024-04-23 09:00","2024-04-22 09:00","2024-04-23 09:00","연속"]
[247,"경북","구미","선산S/S #70 BUS","선산S/S 345kV 장기사용 GIS 용량교체공사(4차)","○ 70BAY GIS 교체(내전압 시험 후 70BUS 연결)","2024-04-15 09:00","2024-04-23 09:00","2024-04-15 09:00","2024-04-23 09:00","연속"]
[248,"경북","영주","신영주S/S #3 M.Tr","2024-25년 영주전력지사 변전협력회사 공사","GIS 하자점검","2024-04-02 09:00","2024-04-03 18:00","2024-04-02 09:00","2024-04-03 18:00","연속"]
[249,"경북","영주","신영주S/S #1 M.Tr","2024-25년 영주전력지사 변전협력회사 공사","GIS 하자점검","2024-04-15 09:00","2024-04-17 18:00","2024-04-15 09:00","2024-04-17 18:00","연속"]
[250,"경북","영주","신제천신영주#2 T/L","345kV 신제천-신영주T/L 정밀점검","345kV 신제천-신영주T/L 정밀점검","2024-04-22 09:00","2024-04-26 18:00","취소","취소","연속"]
[251,"경북","영주","신영주S/S #2 M.Tr","2024-25년 영주전력지사 변전협력회사 공사","GIS 하자점검","2024-04-29 09:00","2024-04-29 18:00","2024-04-29 09:00","2024-04-29 18:00","연속"]
[252,"경북","영주","신제천신영주#1 T/L","345kV 신제천-신영주T/L 정밀점검","345kV 신제천-신영주T/L 정밀점검","2024-04-15 09:00","2024-04-19 18:00","취소","취소","연속"]
[253,"경북","직할","청송P/P CB 7200","24~25년 경북본부 직할 변전협력회사 공사","가스 누기개소 조치","2024-04-16 09:00","2024-04-17 18:00","2024-04-16 09:00","2024-04-17 18:00","연속"]
[254,"부산울산","동부산","고리N/P #75 BUS","고리NP S/Y 이음발생관련 내부점검","고리NP S/Y 이음발생관련 내부점검(#75BUS)","2024-04-22 09:00","2024-05-03 18:00","2024-04-22 09:00","2024-05-03 18:00","연속"]
[255,"부산울산","동부산","신양산고리NP#1 T/L","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 용량부족차단기 교체공사(3차) - 휴전대상 : 7671,7600 CB - 작업내용 : 신양산-고리#1T/L 인출BAY 변경작업(76-&gt75BAY) 및 내전압, 시험가압, 본가압 - 작업대상 : 7521DS GIB(일부 기설치), 부싱, 인하선 설치 ※ 75BAY 휴전 중(~5/1)","2024-04-18 08:00","2024-05-03 18:00","2024-04-18 08:00","2024-05-03 18:00","연속"]
[256,"부산울산","동부산","신양산북부산#1 T/L","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 용량부족차단기 교체공사 3차 - #3M.Tr 인출BAY 이설 완료에 따른 시험가압(24h)","2024-04-17 10:00","2024-04-18 10:00","2024-04-17 10:00","2024-04-18 10:00","연속"]
[257,"부산울산","동부산","신양산북부산#1 T/L","2024-2025년 동부산 가공송전협력회사 공사","폴리머점퍼지지애자 설치","2024-04-15 07:00","2024-04-16 18:00","2024-04-15 07:00","2024-04-16 18:00","연속"]
[258,"부산울산","동부산","신양산S/S CB 7472","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 용량부족차단기 교체공사(3차) - 휴전대상 : 7400, 7472 CB - 작업내용 : #3M.Tr 인출BAY 변경작업(75-&gt74BAY) 및 시험가압, 본가압 - 작업대상 : 7422DS GIB(일부 기설치), 부싱, 인하선 설치 ※#3M.Tr 휴전 중(~4/26)","2024-04-08 08:00","2024-04-18 18:00","2024-04-08 08:00","2024-04-18 18:00","연속"]
[259,"부산울산","동부산","신양산S/S CB 7400","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 용량부족차단기 교체공사(3차) - 휴전대상 : 7400, 7472 CB - 작업내용 : #3M.Tr 인출BAY 변경작업(75-&gt74BAY) 및 시험가압, 본가압 - 작업대상 : 7422DS GIB(일부 기설치), 부싱, 인하선 설치 ※#3M.Tr 휴전 중(~4/26)","2024-04-08 08:00","2024-04-18 18:00","2024-04-08 08:00","2024-04-18 18:00","연속"]
[260,"부산울산","북부산","북부산신울산#1 T/L","345kV 북부산-신울산 #1T/L 정밀점검","345kV 북부산-신울산 #1T/L 정밀점검 -점검대상 : 총 115기(No.1 ~ 110호 113기 및 S/T 2기)","2024-04-29 09:00","2024-05-08 18:00","2024-04-29 09:00","2024-05-08 18:00","연속"]
[261,"부산울산","울산","남울산S/S #2 M.Tr","남울산S/S 345kV 일진제 GIS 하자조치","남울산S/S 345kV 일진제 GIS 하자조치(7300 유압 조작기 교체 및 7392 발청보수)","2024-04-30 09:00","2024-05-02 18:00","2024-04-30 09:00","2024-05-02 18:00","연속"]
[262,"부산울산","울산","동울산신울산 T/L","24~25년 변전협력회사 총액공사","- LA 보통점검","2024-04-02 09:00","2024-04-02 18:00","2024-04-02 09:00","2024-04-02 18:00","연속"]
[263,"부산울산","울산","신울산S/S CB 7371","24~25년 변전협력회사 총액공사","- 7371 GIS 하자점검","2024-04-12 09:00","2024-04-12 18:00","2024-04-12 09:00","2024-04-12 18:00","연속"]
[264,"부산울산","울산","신울산S/S CB 7200","24~25년 변전협력회사 총액공사","- 7200 GIS 하자점검","2024-04-11 09:00","2024-04-11 18:00","2024-04-11 09:00","2024-04-11 18:00","연속"]
[265,"부산울산","울산","신울산S/S CB 7271","24~25년 변전협력회사 총액공사","- 7271 GIS 하자점검","2024-04-08 09:00","2024-04-08 18:00","2024-04-08 09:00","2024-04-08 18:00","연속"]
[266,"부산울산","울산","신울산S/S #70 BUS","신울산S/S 345kV 용량대체공사","- 71BAY 무부하가압","2024-04-26 09:00","2024-04-27 18:00","2024-04-26 09:00","2024-04-27 18:00","연속"]
[267,"부산울산","울산","신울산S/S #3 M.Tr","24~25년 변전협력회사 총액공사","- M.Tr 하자점검 - 3차 Sh.R 보호반 대체","2024-04-29 09:00","2024-05-03 18:00","2024-04-29 09:00","2024-05-03 18:00","연속"]
[268,"부산울산","울산","신온산신울산#2 T/L","신울산S/S 345kV 용량대체공사","- 71BAY 무부하가압","2024-04-26 09:00","2024-04-27 18:00","2024-04-26 09:00","2024-04-27 18:00","연속"]
[269,"부산울산","울산","울주월성NP#1 T/L","24~25년 변전협력회사 총액공사","- LA, CVT 보통점검 - GIS(7971, 7900) 차단기 동작시험","2024-04-30 09:00","2024-04-30 18:00","2024-04-30 09:00","2024-04-30 18:00","연속"]
[270,"경남","직할","신김해북부산#2 T/L","345kV 신김해-북부산#2T/L 추락방지장치 설치공사","345kV 신김해-북부산#2T/L 추락방지장치 설치공사(345kV 신마산-신김해T/L 병가개소)","2024-04-27 07:00","2024-04-28 12:00","2024-04-27 07:00","2024-04-28 12:00","매일"]
[271,"경남","직할","신마산신김해#1 T/L","345kV 신마산-신김해#1T/L 추락방지장치 설치공사","345kV 신마산-신김해#1T/L 1~97호 추락방지장치 설치공사","2024-04-24 07:00","2024-04-28 18:00","2024-04-24 07:00","2024-04-28 18:00","매일"]
[272,"경남","직할","신김해북부산#2 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-04-15 07:00","2024-04-19 18:00","2024-04-15 07:00","2024-04-19 18:00","매일"]
[273,"경남","직할","신김해북부산#1 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-04-11 07:00","2024-04-12 18:00","2024-04-11 07:00","2024-04-12 18:00","매일"]
[274,"경남","직할","신김해북부산#1 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-04-08 07:00","2024-04-09 18:00","2024-04-08 07:00","2024-04-09 18:00","매일"]
[275,"경남","직할","신마산신김해#2 T/L","345kV 신마산-신김해#2T/L 추락방지장치 설치공사","345kV 신마산-신김해#2T/L 1~97호 추락방지장치 설치공사","2024-04-30 07:00","2024-05-04 18:00","2024-04-30 07:00","2024-05-04 18:00","매일"]
[276,"경남","직할","신김해북부산#1 T/L","345kV 신김해-북부산#1T/L 추락방지장치 설치공사","345kV 신김해-북부산#1T/L 추락방지장치 설치공사(345kV 신마산-신김해T/L 병가개소)","2024-04-28 12:00","2024-04-28 18:00","2024-04-28 12:00","2024-04-28 18:00","매일"]
[277,"경남","직할","창원S/S #3 M.Tr","창원S/S 345kV #3 M.Tr 보통점검","창원S/S 345kV #3 M.Tr 보통점검","2024-04-17 09:00","2024-04-19 18:00","2024-04-17 09:00","2024-04-19 18:00","연속"]
[278,"경남","진주","의령산청양수#1 T/L","345lkV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#1T/L측 수직,수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.1~130 (345kV 의령-하동화력 T/L과 병가 구간 No.112~129)","2024-04-01 07:30","2024-04-05 18:00","2024-04-01 07:30","2024-04-05 18:00","연속"]
[279,"경남","진주","의령산청양수#1 T/L","345lkV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#1T/L측 수직,수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.1~130 (345kV 의령-하동화력 T/L과 병가 구간 No.112~129)","2024-04-08 07:30","2024-04-12 18:00","취소","취소","연속"]
[280,"경남","진주","의령산청양수#2 T/L","345lkV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#2T/L측 수직,수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.1~130 (345kV 의령-하동화력 T/L과 병가 구간 No.112~129)","2024-04-22 07:30","2024-04-26 18:00","2024-04-22 07:30","2024-04-26 18:00","연속"]
[281,"경남","진주","고령의령#1 T/L","의령S/S 345kV 7600 TIE GIS 보통점검 등","의령S/S 345kV 고령-의령#1T/L 7600 TIE 7600 GIS 보통점검 [병행] 고령-의령#1T/L 7671 GIS C상 유압 셋팅 [제작사]","2024-04-08 09:00","2024-04-08 17:00","2024-04-08 09:00","2024-04-08 17:00","연속"]
[282,"경남","진주","의령산청양수#2 T/L","345lkV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#2T/L측 수직,수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.1~130 (345kV 의령-하동화력 T/L과 병가 구간 No.112~129)","2024-04-29 07:30","2024-05-03 18:00","2024-04-29 07:30","2024-05-03 18:00","연속"]
[283,"경남","진주","의령산청양수#1 T/L","345lkV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#2T/L측 수직,수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.1~130 (345kV 의령-하동화력 T/L과 병가 구간 No.112~129)","2024-04-15 07:30","2024-04-19 18:00","2024-04-15 07:30","2024-04-19 18:00","매일"]
[284,"경남","통영","신고성S/S #3 M.Tr","신고성S/S 345kV #3M.Tr 2차 GIS 조작시험","신고성S/S 345kV #3M.Tr 2차 GIS 조작시험 - 1차 GIS 도블 - 3차 모선 도블 및 메가 - 1,2차 부싱절연유 채유 - 3차측 VCB 조작시험","2024-04-15 10:00","2024-04-16 18:00","2024-04-15 10:00","2024-04-16 18:00","연속"]
[285,"경남","통영","신고성S/S #4 M.Tr","신고성S/S 345kV #4M.Tr 2차 GIS 조작시험","신고성S/S 345kV #4M.Tr 2차 GIS 조작시험 - 1차 GIS 도블 - 3차 모선 도블 및 메가 - 1,2차 부싱절연유 채유 - 1,2차 LA 교체 - 3차측 VCB 조작시험 - 3차 LA 초기점검","2024-04-17 10:00","2024-04-18 18:00","2024-04-17 10:00","2024-04-18 18:00","연속"]
[286,"대전세종충남",null,"청양신보령TP T/L","신보령T/P #72Bay 보통점검","신보령T/P #72Bay 보통점검","2024-04-01 09:00","2024-04-19 18:00","2024-04-01 09:00","2024-04-19 18:00","연속"]
[287,"대전세종충남",null,"신보령T/P #1 BUS","모선 점검","모선 점검","2024-04-15 09:00","2024-04-19 18:00","2024-04-15 09:00","2024-04-19 18:00","연속"]
[288,"대전세종충남",null,"신보령T/P #2 BUS","모선 점검","모선 점검","2024-04-22 09:00","2024-04-23 18:00","2024-04-22 09:00","2024-04-23 18:00","연속"]
[289,"남서울","동서울","신용인동서울#2 T/L","345kV 동서울S/S 종합정비공사","- 345kV M.Tr(단상, 166.7MVA, FOA) × 6대(이설) - 345,154kV GIB × 2조(신설) - 345kV M.Tr 감시,제어,계측,보호 제어케이블 포설 및 결선 × 1식 - 345kV GIS 감시,제어,계측 제어케이블 재사용철거 및 포설 × 1식 - 23kV Sh.R(삼상, 30Mvar) × 6대(이설)","2024-04-01 09:00","2024-04-30 18:00","2024-04-01 09:00","2024-04-30 18:00","연속"]
[290,"강원",null,"강릉T/P #1 G.Tr (CB 7100, 7172)","강릉T/P #1호기 갑종보호계전기 정기검사","강릉T/P #1호기 갑종보호계전기 정기검사","2024-04-11 09:00","2024-05-31 09:00","2024-04-11 09:00","2024-05-31 09:00","연속"]
[291,"강원",null,"안인개폐소강릉TP#1 T/L","강릉T/P #1호기 갑종보호계전기 정기검사","강릉T/P #1호기 갑종보호계전기 정기검사","2024-04-11 09:00","2024-05-31 09:00","2024-04-11 09:00","2024-05-31 09:00","연속"]

{"sheet":"154설비","index":2,"n_rows":690,"n_cols":11,"rows_kept":690,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2024년도 4월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","미금광장 T/L","2024년 성동P/O 변전협력회사 공사","- 154kV GIS 보통점검","2024-04-04 09:30","2024-04-04 17:00","취소","취소","연속"]
[2,"서울","성동","화양광장 T/L","2024년 성동P/O 변전협력회사 공사","- 154kV GIS 보통점검","2024-04-03 09:30","2024-04-03 17:00","취소","취소","연속"]
[3,"서울","성동","광장뚝도#1 T/L","2024년 성동P/O 변전협력회사 공사","- 154kV GIS 보통점검","2024-04-15 09:30","2024-04-15 17:00","취소","취소","연속"]
[4,"서울","성동","군자화양#2 T/L","2024년 성동P/O 변전협력회사 공사","- 154kV GIS 보통점검","2024-04-16 09:30","2024-04-16 17:00","취소","취소","연속"]
[5,"서울","성동","군자화양#1 T/L","2024년 성동P/O 변전협력회사 공사","- 154kV GIS 보통점검","2024-04-19 09:30","2024-04-19 17:00","취소","취소","연속"]
[6,"서울","성동","안암노원#1 T/L","장위 재개발관련 지장송전선로 이설공사","1. 대상선로 : 154kV 안암-노원#1 T/L 2. 공사내용 : 지장송전선로 이설(M/H#6호 ~ M/H#9호)","2024-04-01 09:00","2024-05-17 18:00","2024-04-01 09:00","2024-05-17 18:00","연속"]
[7,"서울","성동","안암노원#2 T/L","장위 재개발관련 지장송전선로 이설공사","1. 대상선로 : 154kV 안암-노원#1 T/L 2. 공사내용 : 지장송전선로 이설(M/H#6호 ~ M/H#9호)","2024-04-01 09:00","2024-05-17 18:00","취소","취소","연속"]
[8,"서울","성동","광장뚝도#2 T/L","2024년 성동P/O 154kV GIS 정밀점검","- 154kV GIS 정밀점검","2024-04-29 09:00","2024-04-30 18:00","취소","취소","연속"]
[9,"서울","성동","창동쌍문#1 T/L","2024년 성동P/O 154kV GIS 정밀점검","- 154kV GIS 정밀점검","2024-04-15 09:00","2024-04-16 18:00","취소","취소","연속"]
[10,"서울","성동","창동쌍문#2 T/L","2024년 성동P/O 154kV GIS 정밀점검","- 154kV GIS 정밀점검","2024-04-17 09:00","2024-04-18 18:00","취소","취소","연속"]
[11,"서울","성동","성동휘경#1 T/L","2024년 성동P/O 변전협력회사 공사","- 154kV GIS 보통점검","2024-04-17 09:30","2024-04-17 17:00","2024-04-17 09:30","2024-04-17 17:00","연속"]
[12,"서울","성동","상봉휘경#1 T/L","2024년 성동P/O 변전협력회사 공사","- 154kV GIS 보통점검","2024-04-22 09:30","2024-04-22 17:00","2024-04-22 09:30","2024-04-22 17:00","연속"]
[13,"서울","성동","상봉휘경#2 T/L","2024년 성동P/O 변전협력회사 공사","- 154kV GIS 보통점검","2024-04-23 09:30","2024-04-23 17:00","2024-04-23 09:30","2024-04-23 17:00","연속"]
[14,"서울","성동","휘경종암#1 T/L","2024년 성동P/O 변전협력회사 공사","- 154kV GIS 보통점검","2024-04-24 09:30","2024-04-24 17:00","2024-04-24 09:30","2024-04-24 17:00","연속"]
[15,"서울","성동","휘경종암#2 T/L","2024년 성동P/O 변전협력회사 공사","- 154kV GIS 보통점검","2024-04-25 09:30","2024-04-25 17:00","2024-04-25 09:30","2024-04-25 17:00","연속"]
[16,"서울","성동","성동휘경#2 T/L","2024년 성동P/O 변전협력회사 공사","- 154kV GIS 보통점검","2024-04-18 09:30","2024-04-18 17:00","2024-04-18 09:30","2024-04-18 17:00","연속"]
[17,"서울","중부","상암등촌#2 T/L","2024년 가공송전선로 순시점검 위탁공사","154kV 상암-등촌T/L No.7(염창C/T) 인근 지장수목 전지","2024-04-01 13:00","2024-04-01 18:00","2024-04-01 08:00","2024-04-01 18:00","연속"]
[18,"서울","중부","상암등촌#1 T/L","2024년 가공송전선로 순시점검 위탁공사","154kV 상암-등촌T/L No.7(염창C/T) 인근 지장수목 전지","2024-04-01 08:00","2024-04-01 13:00","2024-04-01 08:00","2024-04-01 18:00","연속"]
[19,"서울","중부","신촌순화 T/L","24년 중부전력지사 170kV GIS 정밀점검","CB 정밀점검","2024-04-22 09:00","2024-04-23 18:00","취소","취소","연속"]
[20,"서울","중부","중부S/S CB 6100","24-25 중부전력지사 변전협력 총액공사","차단기 보통점검","2024-04-29 10:00","2024-04-29 18:00","2024-04-29 10:00","2024-04-29 18:00","연속"]
[21,"서울","중부","중부S/S SEC CB 60610","24-25 중부전력지사 변전협력 총액공사","차단기 조작시험","2024-04-30 10:00","2024-04-30 14:00","2024-04-30 10:00","2024-04-30 14:00","연속"]
[22,"서울","중부","중부S/S SEC CB 65660","24-25 중부전력지사 변전협력 총액공사","차단기 조작시험","2024-04-30 14:00","2024-04-30 18:00","2024-04-30 14:00","2024-04-30 18:00","연속"]
[23,"서울","중부","중부용산#1 T/L","24-25 중부전력지사 변전협력 총액공사","차단기 조작시험","2024-04-25 14:00","2024-04-25 18:00","취소","취소","연속"]
[24,"서울","중부","중부S/S CB 6200","24-25 중부전력지사 변전협력 총액공사","차단기 조작시험","2024-04-25 10:00","2024-04-25 14:00","2024-04-25 10:00","2024-04-25 14:00","연속"]
[25,"서울","중부","중부당인리#1 T/L","24-25 중부전력지사 변전협력 총액공사","차단기 보통점검","2024-04-23 10:00","2024-04-23 18:00","2024-04-23 10:00","2024-04-23 18:00","연속"]
[26,"남서울","강남","신양재신사#3 T/L","강남P/O 170kV GIS 정밀점검(신양재-신사#3 점검)","강남P/O 170kV GIS 정밀점검(신양재-신사#3 점검)","2024-04-11 08:00","2024-04-13 15:00","2024-04-11 08:00","2024-04-13 15:00","연속"]
[27,"남서울","동서울","강동상일#1 T/L","154kV 강일S/S 건설사업","- 공사목적 : 하남미사지구 및 대용량 신규고객 안정적 전력공급 - 사업규모 : 지하형 변전소, 60MVA×2Bank [최종 4Bank] - 공사위치 : 서울시 강동구 상일동 405 (상일S/S 부지 내)","2024-04-13 09:00","2024-04-14 18:00","2024-04-13 09:00","2024-04-14 18:00","연속"]
[28,"남서울","동서울","상일S/S #1 BUS","154kV 강일S/S 건설사업","- 공사목적 : 하남미사지구 및 대용량 신규고객 안정적 전력공급 - 사업규모 : 지하형 변전소, 60MVA×2Bank [최종 4Bank] - 공사위치 : 서울시 강동구 상일동 405 (상일S/S 부지 내)","2024-04-13 09:00","2024-04-13 18:00","2024-04-13 09:00","2024-04-13 18:00","연속"]
[29,"남서울","동서울","상일S/S #2 BUS","154kV 강일S/S 건설사업","- 공사목적 : 하남미사지구 및 대용량 신규고객 안정적 전력공급 - 사업규모 : 지하형 변전소, 60MVA×2Bank [최종 4Bank] - 공사위치 : 서울시 강동구 상일동 405 (상일S/S 부지 내)","2024-04-14 09:00","2024-04-14 18:00","2024-04-14 09:00","2024-04-14 18:00","연속"]
[30,"남서울","동서울","송파잠실#4 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","송파S/S 송파-잠실#4T/L GIS 조작시험","2024-04-23 09:00","2024-04-23 18:00","2024-04-23 09:00","2024-04-23 18:00","연속"]
[31,"남서울","동서울","산성수서#1 T/L","8호선 복정역 승강편의시설 및 위례선 도시철도(트램)공사","복정역 1번 출구 E/L설치 및 위례선 도시철도(트램) 건설 (발주처 : 서울지하철공사 / 서울시 도시기반시설본부) - 고도제한 저지상고개소 공사현장 지하철 이용시민 안전확보","2024-04-01 10:00","2024-09-30 17:00","2024-04-01 10:00","2024-09-30 17:00","연속"]
[32,"남서울","동서울","가락수서#2 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","수서S/S 가락-수서#2T/L GIS 조작시험","2024-04-02 09:00","2024-04-02 18:00","2024-04-02 09:00","2024-04-02 18:00","연속"]
[33,"남서울","동서울","가락수서#1 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","수서S/S 가락-수서#1T/L GIS 조작시험","2024-04-01 09:00","2024-04-01 18:00","2024-04-01 09:00","2024-04-01 18:00","연속"]
[34,"남서울","동서울","신장덕소#1 T/L","154kV 강일S/S 건설사업","- 공사목적 : 하남미사지구 및 대용량 신규고객 안정적 전력공급 - 사업규모 : 지하형 변전소, 60MVA×2Bank [최종 4Bank] - 공사위치 : 서울시 강동구 상일동 405 (상일S/S 부지 내)","2024-04-13 09:00","2024-04-14 18:00","2024-04-13 09:00","2024-04-14 18:00","연속"]
[35,"남서울","동서울","신장S/S #1 BUS","154kV 강일S/S 건설사업","- 공사목적 : 하남미사지구 및 대용량 신규고객 안정적 전력공급 - 사업규모 : 지하형 변전소, 60MVA×2Bank [최종 4Bank] - 공사위치 : 서울시 강동구 상일동 405 (상일S/S 부지 내)","2024-04-13 09:00","2024-04-13 18:00","2024-04-13 09:00","2024-04-13 18:00","연속"]
[36,"남서울","동서울","신장S/S #2 BUS","154kV 강일S/S 건설사업","- 공사목적 : 하남미사지구 및 대용량 신규고객 안정적 전력공급 - 사업규모 : 지하형 변전소, 60MVA×2Bank [최종 4Bank] - 공사위치 : 서울시 강동구 상일동 405 (상일S/S 부지 내)","2024-04-14 09:00","2024-04-14 18:00","2024-04-14 09:00","2024-04-14 18:00","연속"]
[37,"남서울","동서울","동서울위례#2 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","동서울#2,위례S/S 동서울#2-위례#2T/L GIS 하자점검","2024-04-16 09:00","2024-04-16 18:00","2024-04-16 09:00","2024-04-16 18:00","연속"]
[38,"남서울","동서울","동서울위례#1 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","동서울#2,위례S/S 동서울#2-위례#1T/L GIS 하자점검","2024-04-15 09:00","2024-04-15 18:00","2024-04-15 09:00","2024-04-15 18:00","연속"]
[39,"남서울","동서울","송파잠실#3 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","송파,잠실S/S 송파-잠실#3T/L GIS 조작시험","2024-04-22 09:00","2024-04-22 18:00","2024-04-22 09:00","2024-04-22 18:00","연속"]
[40,"남서울","동서울","탄천선릉#1 T/L","154kV 탄천-선릉T/L 지장송전선로 이설공사","공사구간 : 탄천S/S EBG ~ J/B#2, 1.1km 대상 : 154kV 탄천-선릉 #1T/L(XLPE 2,000㎟) - 중간접속 2개소, 종단접속 1개소, 케이블 철거 및 설치","2024-04-01 09:00","2024-04-30 18:00","2024-04-01 09:00","2024-04-30 18:00","연속"]
[41,"남서울","동서울","탄천S/S #65 BUS","154KV 탄천-선릉T/L 지장송전선로 이설공사","탄천-선릉#1T/L 가압 전 상체크 시험","2024-04-29 09:00","2024-04-29 18:00","2024-04-29 09:00","2024-04-29 18:00","연속"]
[42,"남서울","동서울","강동풍납#1 T/L","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS x 5CCT 교체 - 기타부대공사","2024-04-15 09:00","2024-05-24 18:00","2024-04-15 09:00","2024-05-24 18:00","연속"]
[43,"남서울","동서울","풍납S/S #1 BUS","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS x 5CCT 교체 - 기타부대공사","2024-04-17 14:00","2024-05-10 18:00","2024-04-17 14:00","2024-04-19 18:00","연속"]
[44,"남서울","동서울","풍납석촌#1 T/L","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS x 5CCT 교체 - 기타부대공사","2024-04-17 13:00","2024-04-17 14:00","2024-04-17 13:00","2024-04-17 14:00","연속"]
[45,"남서울","동서울","풍납S/S #2 BUS","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS x 5CCT 교체 - 기타부대공사","2024-04-15 09:00","2024-04-17 14:00","2024-04-15 09:00","2024-04-17 14:00","연속"]
[46,"남서울","동서울","강동풍납#2 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","풍납S/S 강동-풍납#2T/L GIS 초기점검","2024-04-11 09:00","2024-04-11 18:00","2024-04-11 09:00","2024-04-11 18:00","연속"]
[47,"남서울","영등포","가양등촌#1 T/L","154kV 강서S/S 건설사업","154kV 강서S/S 건설사업 - 강서S/S 무부하가압 선로","2024-04-23 09:00","2024-04-24 18:00","2024-04-23 09:00","2024-04-24 18:00","연속"]
[48,"남서울","영등포","신광명광명#2 T/L","154kV 신광명-광명#2T/L OF 밸브판넬 보수","ㅇ154kV 신광명-광명#2T/L OF 밸브판넬 보수","2024-04-22 09:00","2024-04-25 18:00","2024-04-22 09:00","2024-04-25 18:00","연속"]
[49,"남서울","영등포","구공S/S #61 BUS","구공S/S 154kV 장기사용 GIS 교체 및 모선구분 차단기 설치공사","＊#4M.Tr 1차, 61-62BUS SEC GIS 설치 ○ GIS(170kV 50kA 1000/2000A, 6BAY) 철거 ○ GIS(170kV 50kA 1250/2000/3150A, 7BAY) 설치 ○ GIS 교체에 따른 광·제어케이블 포설 및 결선 ○ 모선보호반(62-67), CPD(62-67) 설치","2024-04-11 09:00","2024-05-03 18:00","2024-04-11 09:00","2024-05-03 18:00","연속"]
[50,"남서울","영등포","천왕구로#2 T/L","24년도 영등포전력지사 170kV GIS 정밀점검공사","24년도 영등포전력지사 170kV GIS 정밀점검공사 대상 : 천왕-구로#2T/L","2024-04-15 09:00","2024-04-16 18:00","2024-04-15 09:00","2024-04-16 18:00","연속"]
[51,"남서울","영등포","신문래구로#1 T/L","24년도 영등포전력지사 170kV GIS 정밀점검공사","24년도 영등포전력지사 170kV GIS 정밀점검공사 대상 : 신문래-구로#1T/L","2024-04-11 09:00","2024-04-12 18:00","2024-04-11 09:00","2024-04-12 18:00","연속"]
[52,"남서울","영등포","천왕구로#1 T/L","24년도 영등포전력지사 170kV GIS 정밀점검공사","24년도 영등포전력지사 170kV GIS 정밀점검공사 대상 : 천왕-구로#1T/L","2024-04-17 09:00","2024-04-18 18:00","2024-04-17 09:00","2024-04-18 18:00","연속"]
[53,"남서울","영등포","구로S/S CB 6100","24년도 영등포전력지사 170kV GIS 정밀점검공사","24년도 영등포전력지사 170kV GIS 정밀점검공사 대상 : 6100 BUS-TIE","2024-04-29 09:00","2024-04-30 18:00","2024-04-29 09:00","2024-04-30 18:00","연속"]
[54,"남서울","영등포","구로S/S #1 BUS","24년도 영등포전력지사 170kV GIS 정밀점검공사","24년도 영등포전력지사 170kV GIS 정밀점검공사 대상 : 6100 BUS-TIE (무부하가압용)","2024-04-29 09:00","2024-04-30 18:00","2024-04-29 09:00","2024-04-30 18:00","연속"]
[55,"남서울","영등포","천왕구로#1 T/L","24년도 영등포전력지사 170kV GIS 정밀점검공사","24년도 영등포전력지사 170kV GIS 정밀점검공사 대상 : 6100 BUS-TIE (무부하가압용)","2024-04-30 16:00","2024-04-30 18:00","2024-04-30 16:00","2024-04-30 18:00","연속"]
[56,"남서울","영등포","구로S/S #1 BUS","24년도 영등포전력지사 170kV GIS 정밀점검공사","24년도 영등포전력지사 170kV GIS 정밀점검공사 대상 : #1M.Tr 1차 (무부하가압용)","2024-04-23 16:00","2024-04-23 18:00","2024-04-23 16:00","2024-04-23 18:00","연속"]
[57,"남서울","영등포","천왕구로#1 T/L","24년도 영등포전력지사 170kV GIS 정밀점검공사","24년도 영등포전력지사 170kV GIS 정밀점검공사 대상 : #1M.Tr 1차 (무부하가압용)","2024-04-23 16:00","2024-04-23 18:00","2024-04-23 16:00","2024-04-23 18:00","연속"]
[58,"남서울","영등포","천왕구로#1 T/L","24년도 영등포전력지사 170kV GIS 정밀점검공사","24년도 영등포전력지사 170kV GIS 정밀점검공사 대상 : #2M.Tr 1차 (무부하가압용)","2024-04-25 16:00","2024-04-25 18:00","2024-04-25 16:00","2024-04-25 18:00","연속"]
[59,"남서울","영등포","구로S/S #1 BUS","24년도 영등포전력지사 170kV GIS 정밀점검공사","24년도 영등포전력지사 170kV GIS 정밀점검공사 대상 : #2M.Tr 1차 (무부하가압용)","2024-04-25 16:00","2024-04-25 18:00","2024-04-25 16:00","2024-04-25 18:00","연속"]
[60,"남서울","영등포","독산대방#1 T/L","대한제 EBG 가스채취밸브 설치공사","가스채취밸브 설치 및 스프링유니트 점검","2024-04-20 09:00","2024-04-21 18:00","2024-04-20 09:00","2024-04-21 18:00","연속"]
[61,"남서울","영등포","독산대방#1 T/L","대한제 EBG 가스채취밸브 설치공사","가스채취밸브 설치 및 스프링유니트 점검","2024-04-13 09:00","2024-04-14 18:00","2024-04-13 09:00","2024-04-14 18:00","연속"]
[62,"남서울","영등포","구공독산 T/L","대한제 EBG 가스채취밸브 설치공사","가스채취밸브 설치 및 스프링유니트 점검","2024-04-29 09:00","2024-04-30 18:00","2024-04-29 09:00","2024-04-30 18:00","연속"]
[63,"남서울","영등포","독산대방#2 T/L","대한제 EBG 가스채취밸브 설치공사","가스채취밸브 설치 및 스프링유니트 점검","2024-04-27 09:00","2024-04-28 18:00","2024-04-27 09:00","2024-04-28 18:00","연속"]
[64,"남서울","영등포","목동양천#2 T/L","목동S/S 170kV GIS 조작시험","-목동-양천#1,2","2024-04-16 14:00","2024-04-16 18:00","2024-04-16 14:00","2024-04-16 18:00","연속"]
[65,"남서울","영등포","당인리목동#2 T/L","목동S/S 170kV GIS 조작시험","-당인리-목동#1,2","2024-04-12 14:00","2024-04-12 18:00","2024-04-12 14:00","2024-04-12 18:00","연속"]
[66,"남서울","영등포","목동양천#1 T/L","목동S/S 170kV GIS 조작시험","-목동-양천#1,2","2024-04-16 09:00","2024-04-16 14:00","2024-04-16 09:00","2024-04-16 14:00","연속"]
[67,"남서울","영등포","당인리목동#1 T/L","목동S/S 170kV GIS 조작시험","-당인리-목동#1,2","2024-04-12 09:00","2024-04-12 14:00","2024-04-12 09:00","2024-04-12 14:00","연속"]
[68,"남서울","영등포","오류목동 T/L","목동S/S 170kV GIS 조작시험","-오류-목동","2024-04-11 09:00","2024-04-11 18:00","2024-04-11 09:00","2024-04-11 18:00","연속"]
[69,"남서울","영등포","신문래목동#2 T/L","목동S/S 170kV GIS 조작시험","-신문래-목동#1,2","2024-04-08 14:00","2024-04-08 18:00","2024-04-08 14:00","2024-04-08 18:00","연속"]
[70,"남서울","영등포","신문래목동#1 T/L","목동S/S 170kV GIS 조작시험","-신문래-목동#1,2","2024-04-08 09:00","2024-04-08 14:00","2024-04-08 09:00","2024-04-08 14:00","연속"]
[71,"남서울","영등포","신정목동#2 T/L","목동S/S 170kV GIS 조작시험","-신정-목동#1,2","2024-04-13 14:00","2024-04-13 18:00","2024-04-13 14:00","2024-04-13 18:00","연속"]
[72,"남서울","영등포","신정목동#1 T/L","목동S/S 170kV GIS 조작시험","-신정-목동#1,2","2024-04-13 09:00","2024-04-13 14:00","2024-04-13 09:00","2024-04-13 14:00","연속"]
[73,"남서울","영등포","신광명소래 T/L","2024~25년 가공송전 협력회사 공사(수평 추락방지장치 설치)","154kV 신광명소래T/L 추락방지장치 설치","2024-04-15 07:00","2024-04-15 18:00","2024-04-15 07:00","2024-04-15 18:00","연속"]
[74,"남서울","영등포","천왕온수#2 T/L","대한제 EBG 가스채취밸브 설치공사","가스채취밸브 설치 및 스프링유니트 점검","2024-04-22 09:00","2024-04-25 18:00","2024-04-22 09:00","2024-04-25 18:00","연속"]
[75,"남서울","영등포","신광명온수 T/L","온수S/S 170kV GIS 조작시험","-신광명-온수","2024-04-26 09:00","2024-04-26 18:00","2024-04-26 09:00","2024-04-26 18:00","연속"]
[76,"남서울","영등포","온수소래 T/L","온수S/S 170kV GIS 조작시험","-온수-소래","2024-04-15 18:00","2024-04-15 20:00","2024-04-15 18:00","2024-04-15 20:00","연속"]
[77,"남서울","영등포","신광명천왕#2 T/L","대한제 EBG 가스채취밸브 설치공사","가스채취밸브 설치 및 스프링유니트 점검","2024-04-03 09:00","2024-04-04 18:00","2024-04-03 09:00","2024-04-04 18:00","연속"]
[78,"남서울","영등포","신광명천왕#1 T/L","대한제 EBG 가스채취밸브 설치공사","가스채취밸브 설치 및 스프링유니트 점검","2024-04-01 09:00","2024-04-02 18:00","2024-04-01 09:00","2024-04-02 18:00","연속"]
[79,"남서울","영등포","신광명천왕#3 T/L","대한제 EBG 가스채취밸브 설치공사","가스채취밸브 설치 및 스프링유니트 점검","2024-04-11 09:00","2024-04-12 18:00","2024-04-11 09:00","2024-04-12 18:00","연속"]
[80,"남서울","영등포","고강화곡#2 T/L","대한제 EBG 가스채취밸브 설치공사","가스채취밸브 설치 및 스프링유니트 점검","2024-04-17 09:00","2024-04-18 18:00","2024-04-17 09:00","2024-04-18 18:00","연속"]
[81,"남서울","영등포","고강화곡#1 T/L","대한제 EBG 가스채취밸브 설치공사","가스채취밸브 설치 및 스프링유니트 점검","2024-04-15 09:00","2024-04-16 18:00","2024-04-15 09:00","2024-04-16 18:00","연속"]
[82,"인천","김포","김포장기#2 T/L","154kV 불로S/S 건설공사","- M.Tr(154/23kV, 15/20MVA × 3대) × 2Bank - GIS(170kV 50kA) × 10CCT - GIS(25.8kV 25kA) × 13CCT - 기타 부대설비 × 1식","2024-04-15 09:00","2024-04-16 18:00","취소","취소","연속"]
[83,"인천","김포","양촌양곡#1 T/L","양곡S/S 154kV 양촌-양곡#1T/L SA 혼용화 공사","양곡S/S 154kV 양촌-양곡#1T/L SA 혼용화 공사","2024-04-19 09:00","2024-04-19 18:00","취소","취소","연속"]
[84,"인천","김포","신김포양곡#1 T/L","양곡S/S 154kV 신김포-양곡#1T/L SA 혼용화 공사","양곡S/S 154kV 신김포-양곡#1T/L SA 혼용화 공사","2024-04-22 09:00","2024-04-22 18:00","취소","취소","연속"]
[85,"인천","김포","양촌양곡#2 T/L","양곡S/S 154kV 양촌-양곡#2T/L SA 혼용화 공사","양곡S/S 154kV 양촌-양곡#2T/L SA 혼용화 공사 - 양곡S/S 154kV 양촌-양곡#2T/L GIS 조작시험","2024-04-29 09:00","2024-04-29 18:00","취소","취소","연속"]
[86,"인천","김포","왕길양촌#2 T/L","'24~'25년 부평, 김포전력지사 가공송전 협력회사 총액공사","수평 추락방지시설 설치","2024-04-01 07:00","2024-04-03 18:00","2024-04-01 07:00","2024-04-03 18:00","매일"]
[87,"인천","김포","왕길양촌#1 T/L","'24~'25년 부평, 김포전력지사 가공송전 협력회사 총액공사","수평 추락방지시설 설치","2024-04-04 07:00","2024-04-04 18:00","2024-04-04 07:00","2024-04-04 18:00","매일"]
[88,"인천","김포","경서양촌#2 T/L","'24~'25년 부평, 김포전력지사 가공송전 협력회사 총액공사","수평 추락방지시설 설치","2024-04-11 07:00","2024-04-14 18:00","2024-04-11 07:00","2024-04-14 18:00","매일"]
[89,"인천","김포","경서양촌#1 T/L","'24~'25년 부평, 김포전력지사 가공송전 협력회사 총액공사","수평 추락방지시설 설치","2024-04-15 07:00","2024-04-17 18:00","2024-04-15 07:00","2024-04-17 18:00","매일"]
[90,"인천","김포","양촌양곡#1 T/L","24~25년 가공송전 협력회사 공사 (추락방지시설 설치)","수평 추락방지시설 설치","2024-04-18 08:00","2024-04-21 18:00","취소","취소","연속"]
[91,"인천","김포","양촌양곡#2 T/L","24~25년 가공송전 협력회사 공사 (추락방지시설 설치)","수평 추락방지시설 설치","2024-04-27 08:00","2024-04-30 18:00","취소","취소","연속"]
[92,"인천","부평","송현포스코CC#1 T/L","154kV 송현-포스코CCT/L 추락방지시설 및 항공시설물 정비공사","[신시흥남동 휴전 취소시] - 추락방지시설 설치 - 고광도 항공장애표시등 위치변경 및 신규설치","2024-04-22 07:00","2024-04-27 18:00","취소","취소","연속"]
[93,"인천","부평","송현포스코CC#2 T/L","154kV 송현-포스코CCT/L 추락방지시설 및 항공시설물 정비공사","[신시흥남동 휴전 취소시] - 추락방지시설 설치 - 고광도 항공장애표시등 위치변경 및 신규설치","2024-04-15 07:00","2024-04-20 18:00","취소","취소","연속"]
[94,"인천","부평","신가좌S/S SEC CB 61620","신가좌S/S 154kV #61-#62 SEC GIS 보통점검","신가좌S/S 154kV #61-#62 SEC GIS 보통점검","2024-04-30 09:00","2024-04-30 18:00","2024-04-30 09:00","2024-04-30 18:00","연속"]
[95,"인천","부평","신가좌S/S SEC CB 60610","신가좌S/S 154kV #60-#61 SEC GIS 보통점검","신가좌S/S 154kV #60-#61 SEC GIS 보통점검","2024-04-29 09:00","2024-04-29 18:00","2024-04-29 09:00","2024-04-29 18:00","연속"]
[96,"인천","부평","계양원창 T/L","154kV 계양-원창 T/L 보호반 교체공사","154kV 계양-원창 T/L 보호반 교체","2024-04-23 09:00","2024-04-26 18:00","취소","취소","연속"]
[97,"인천","부평","인천C/C 현대제철#2T/L CB","154kV 송현-포스코CCT/L 추락방지시설 및 항공시설물 정비공사","[신시흥남동 휴전 취소시] - 추락방지시설 설치 - 고광도 항공장애표시등 위치변경 및 신규설치","2024-04-15 07:00","2024-04-20 18:00","취소","취소","연속"]
[98,"인천","부평","인천C/C 현대제철#1T/L CB","154kV 송현-포스코CCT/L 추락방지시설 및 항공시설물 정비공사","[신시흥남동 휴전 취소시] - 추락방지시설 설치 - 고광도 항공장애표시등 위치변경 및 신규설치","2024-04-22 07:00","2024-04-27 18:00","취소","취소","연속"]
[99,"인천","시흥","온수소래 T/L","가공송전 협력회사 공사(154kV 서소T/L 추락방지설치)","서안양소래,온수소래T/L 송전철탑 추락방지장치 수평 설치 - 대상 : No.76~82 (7기)","2024-04-27 07:00","2024-04-28 18:00","취소","취소","매일"]
[100,"인천","시흥","서안양소래 T/L","가공송전 협력회사 공사(154kV 서소T/L 추락방지설치)","서안양소래,온수소래T/L 송전철탑 추락방지장치 수평 설치 - 대상 : No.76~82 (7기)","2024-04-26 07:00","2024-04-28 18:00","취소","취소","매일"]
[101,"인천","시흥","서서울#2소래 T/L","케이블타워 피뢰기 교체공사","154kV 서서울2소래T/L 피뢰기 교체공사(소래C/T)","2024-04-23 09:00","2024-04-25 18:00","취소","취소","연속"]
[102,"인천","시흥","신시흥S/S SEC CB 67680","신시흥#2S/S 154kV #67-#68 SEC GIS 보통점검","신시흥#2S/S 154kV #67-#68 SEC GIS 보통점검","2024-04-12 09:00","2024-04-12 18:00","2024-04-12 09:00","2024-04-12 18:00","연속"]
[103,"인천","시흥","신시흥S/S SEC CB 62630","신시흥#2S/S 154kV #62-#63 SEC GIS 보통점검","신시흥#2S/S 154kV #62-#63 SEC GIS 보통점검","2024-04-11 09:00","2024-04-11 18:00","2024-04-11 09:00","2024-04-11 18:00","연속"]
[104,"인천","시흥","신시흥시화#2 T/L","신시흥#2S/S 154kV 신시흥시화#2T/L GIS 보통점검","신시흥#2S/S 154kV 신시흥시화#2T/L GIS 보통점검 - LA, CVT 보통점검","2024-04-29 09:00","2024-04-29 18:00","2024-04-29 09:00","2024-04-29 18:00","연속"]
[105,"인천","직할","갈산S/S #65 BUS","갈산S/S #4M.Tr 증설 및 154kV GIS 신규수용공사","갈산S/S 154kV GIS 모선 도킹(#65BUS)","2024-04-30 09:00","2024-05-03 09:00","2024-04-30 09:00","2024-05-03 09:00","연속"]
[106,"인천","직할","임학계양#1 T/L","23~24년 지중송전 위탁정비공사","피뢰기 및 C/T점검","2024-04-19 09:00","2024-04-19 18:00","2024-04-19 09:00","2024-04-19 18:00","연속"]
[107,"인천","직할","임학계양#2 T/L","154kV 불로S/S 건설공사","- M.Tr(154/23kV, 15/20MVA × 3대) × 2Bank - GIS(170kV 50kA) × 10CCT - GIS(25.8kV 25kA) × 13CCT - 기타 부대설비 × 1식","2024-04-15 09:00","2024-04-16 18:00","취소","취소","연속"]
[108,"인천","직할","신부평도당#2 T/L","도당S/S 도당#2T/L 170kV GIS 보통점검","도당S/S 도당#2T/L 170kV GIS 보통점검","2024-04-01 09:30","2024-04-01 18:00","2024-04-01 09:30","2024-04-01 18:00","연속"]
[109,"인천","직할","부천원미#2 T/L","부천S/S 부천원미#2T/L 170kV GIS 정밀점검","부천S/S 부천원미#2T/L 170kV GIS 정밀점검","2024-04-17 14:00","2024-04-19 18:00","2024-04-17 14:00","2024-04-19 18:00","연속"]
[110,"인천","직할","부천원미#1 T/L","부천S/S 부천원미#1T/L 170kV GIS 정밀점검","부천S/S 부천원미#1T/L 170kV GIS 정밀점검","2024-04-15 09:30","2024-04-17 14:00","2024-04-15 09:30","2024-04-17 14:00","연속"]
[111,"인천","직할","부천도당#1 T/L","부천S/S 도당부천#1T/L 170kV GIS 정밀점검","부천S/S 도당부천#1T/L 170kV GIS 정밀점검","2024-04-22 09:30","2024-04-24 14:00","2024-04-22 09:30","2024-04-24 14:00","연속"]
[112,"인천","직할","부천도당#2 T/L","부천S/S 도당부천#2T/L 170kV GIS 정밀점검","부천S/S 도당부천#2T/L 170kV GIS 정밀점검","2024-04-24 14:00","2024-04-26 18:00","2024-04-24 14:00","2024-04-26 18:00","연속"]
[113,"인천","직할","갈산부흥#2 T/L","부흥S/S 갈산부흥#2T/L GIS 조작시험","부흥S/S 갈산부흥#2T/L GIS 조작시험","2024-04-13 14:00","2024-04-13 18:00","2024-04-20 14:00","2024-04-20 18:00","연속"]
[114,"인천","직할","부흥부개#2 T/L","154kV 신부평-고강T/L 등 4개T/L 구형 SVL 교체공사","154kV 신부평-고강T/L 등 4개T/L 구형 SVL(피뢰기) 및 접지설비 교체공사","2024-04-27 09:00","2024-04-28 18:00","취소","취소","연속"]
[115,"인천","직할","갈산부흥#1 T/L","부흥S/S 갈산부흥#1T/L GIS 조작시험","부흥S/S 갈산부흥#1T/L GIS 조작시험","2024-04-03 09:30","2024-04-03 14:00","2024-04-03 09:30","2024-04-03 14:00","연속"]
[116,"인천","직할","갈산부흥#3 T/L","부흥S/S 갈산부흥#3T/L 조작시험","부흥S/S 갈산부흥#3T/L 조작시험","2024-04-04 09:30","2024-04-04 14:00","2024-04-04 09:30","2024-04-04 14:00","연속"]
[117,"인천","직할","신부평중동#2 T/L","신부평S/S 신부평중동#2T/L 정밀점검","신부평S/S 신부평중동#2T/L 정밀점검","2024-04-29 09:30","2024-05-01 14:00","2024-04-29 09:30","2024-05-01 14:00","연속"]
[118,"인천","직할","부개원미#2 T/L","원미S/S #4M.Tr 1차 GIS 무부하가압용","원미S/S #4M.Tr 1차 GIS 무부하가압용","2024-04-04 14:00","2024-04-04 18:00","2024-04-13 14:00","2024-04-13 18:00","연속"]
[119,"경기북부","고양","양주고양#2 T/L","2024년 가공송전 순시점검 위탁공사(고양)","초기점검","2024-04-02 09:00","2024-04-02 18:00","2024-04-02 09:00","2024-04-02 18:00","연속"]
[120,"경기북부","고양","양주고양#1 T/L","24~25년 고양전력지사 가공송전협력회사 공사","SB댐퍼 정비","2024-04-08 07:00","2024-04-08 18:00","2024-04-08 07:00","2024-04-08 18:00","연속"]
[121,"경기북부","고양","고양일산#1 T/L","24-25 변전협력 총액공사","170kV GIS 보통점검","2024-04-03 09:00","2024-04-03 18:00","2024-04-03 09:00","2024-04-03 18:00","연속"]
[122,"경기북부","고양","월롱금촌#1 T/L","24~25년 고양전력지사 가공송전협력회사 공사","애자교체","2024-04-05 07:00","2024-04-05 18:00","2024-04-05 07:00","2024-04-05 18:00","연속"]
[123,"경기북부","고양","월롱금촌#2 T/L","24~25년 고양전력지사 가공송전협력회사 공사","압축인류크램프, 애자교체","2024-04-01 07:00","2024-04-01 18:00","2024-04-01 07:00","2024-04-01 18:00","연속"]
[124,"경기북부","고양","양주금촌#1 T/L","24~25년 고양전력지사 가공송전협력회사 공사","압축인류크램프 정비 및 애자교체","2024-04-08 07:00","2024-04-09 18:00","2024-04-08 07:00","2024-04-09 18:00","연속"]
[125,"경기북부","고양","양주금촌#2 T/L","24~25년 고양전력지사 가공송전협력회사 공사","압축인류크램프 정비","2024-04-01 07:00","2024-04-02 18:00","2024-04-01 07:00","2024-04-02 18:00","연속"]
[126,"경기북부","고양","남면백석#1 T/L","24~25년 고양전력지사 가공송전협력회사 공사","피뢰기, sb댐퍼 설치","2024-04-11 07:00","2024-04-12 18:00","2024-04-11 07:00","2024-04-12 18:00","연속"]
[127,"경기북부","고양","능곡상암#2 T/L","24~25년 고양전력지사 변전협력회사 공사","170kV GIS 차단기 조작시험","2024-04-19 10:00","2024-04-19 14:00","2024-04-19 10:00","2024-04-19 14:00","연속"]
[128,"경기북부","고양","능곡상암#1 T/L","24~25년 고양전력지사 변전협력회사 공사","170kV GIS 차단기 조작시험","2024-04-18 10:00","2024-04-18 14:00","2024-04-18 10:00","2024-04-18 14:00","연속"]
[129,"경기북부","고양","지도능곡#1 T/L","24~25년 고양전력지사 변전협력회사 공사","170kV GIS 차단기 조작시험","2024-04-09 10:00","2024-04-09 14:00","2024-04-11 10:00","2024-04-11 13:00","연속"]
[130,"경기북부","고양","지도능곡#2 T/L","24~25년 고양전력지사 변전협력회사 공사","170kV GIS 차단기 조작시험","2024-04-11 10:00","2024-04-11 14:00","2024-04-11 13:00","2024-04-11 15:00","연속"]
[131,"경기북부","고양","덕이호수#1 T/L","24-25 변전협력 총액공사","170kV GIS 보통점검","2024-04-17 09:00","2024-04-17 18:00","2024-04-17 09:00","2024-04-17 18:00","연속"]
[132,"경기북부","고양","덕이호수#2 T/L","24-25 변전협력 총액공사","170kV GIS 보통점검","2024-04-18 09:00","2024-04-18 18:00","2024-04-18 09:00","2024-04-18 18:00","연속"]
[133,"경기북부","고양","문발운정#1 T/L","24-25 변전협력 총액공사","170kV GIS 보통점검","2024-04-11 09:00","2024-04-11 18:00","2024-04-11 09:00","2024-04-11 18:00","연속"]
[134,"경기북부","고양","신파주문발#2 T/L","문발S/S 154kV ASE코리아 신규수용 SW 증설공사","문발S/S 154kV ASE코리아 신규수용 SW 증설공사 - 154kV GIS 2CCT 증설 - 문발열병합 #1T/L, 문발운정#2T/L 벨로우즈 교체","2024-04-30 09:00","2024-05-02 18:00","2024-04-30 09:00","2024-05-02 18:00","연속"]
[135,"경기북부","고양","문발파주열병합#1 T/L","문발S/S 154kV ASE코리아 신규수용 SW 증설공사","문발S/S 154kV ASE코리아 신규수용 SW 증설공사 - 154kV GIS 2CCT 증설 - 문발열병합 #1T/L, 문발운정#2T/L 벨로우즈 교체","2024-04-24 09:00","2024-05-02 18:00","2024-04-24 09:00","2024-05-02 18:00","연속"]
[136,"경기북부","고양","신파주문발#1 T/L","24-25 변전협력 총액공사","170kV GIS 보통점검","2024-04-16 09:00","2024-04-16 18:00","2024-04-16 09:00","2024-04-16 18:00","연속"]
[137,"경기북부","고양","문발운정#2 T/L","24-25 변전협력 총액공사","170kV GIS 보통점검","2024-04-12 09:00","2024-04-12 18:00","2024-04-12 09:00","2024-04-12 18:00","연속"]
[138,"경기북부","고양","신덕은S/S #66 BUS","신덕은S/S 154kV 고객선로 SW 증설공사","-170kV GIS 1CCT 설치","2024-04-30 09:00","2024-05-03 18:00","2024-04-30 09:00","2024-05-03 18:00","연속"]
[139,"경기북부","고양","신파주원흥#2 T/L","24~25년 고양전력지사 가공송전협력회사 공사","압축인류크램프, 애자교체","2024-04-09 07:00","2024-04-09 18:00","2024-04-09 07:00","2024-04-09 18:00","연속"]
[140,"경기북부","고양","원흥상암 T/L","2024년 가공송전 순시점검 위탁공사(고양)","정밀점검","2024-04-23 08:00","2024-04-25 18:00","2024-04-23 08:00","2024-04-25 18:00","연속"]
[141,"경기북부","고양","원흥수색#1 T/L","2024년 가공송전 순시점검 위탁공사(고양)","정밀점검","2024-04-16 09:00","2024-04-18 18:00","2024-04-16 09:00","2024-04-18 18:00","연속"]
[142,"경기북부","고양","일산S/S CB 6100","24~25년 고양전력지사 변전협력회사 공사","170kV GIS 차단기 조작시험","2024-04-15 10:00","2024-04-15 14:00","2024-04-15 10:00","2024-04-15 14:00","연속"]
[143,"경기북부","고양","고양일산#2 T/L","24~25년 고양전력지사 가공송전협력회사 공사","압축인류크램프 정비, 애자 교체","2024-04-04 07:00","2024-04-04 18:00","2024-04-04 07:00","2024-04-04 18:00","연속"]
[144,"경기북부","고양","일산지도#2 T/L","24~25년 고양전력지사 가공송전협력회사 공사","피뢰기 설치, 압축인류크램프 정비, 애자 교체","2024-04-03 07:00","2024-04-04 18:00","2024-04-03 07:00","2024-04-04 18:00","연속"]
[145,"경기북부","고양","일산S/S SEC CB 60610","24~25년 고양전력지사 변전협력회사 공사","170kV GIS 차단기 조작시험","2024-04-16 10:00","2024-04-16 14:00","2024-04-16 10:00","2024-04-16 14:00","연속"]
[146,"경기북부","고양","일산S/S SEC CB 65660","24~25년 고양전력지사 변전협력회사 공사","170kV GIS 차단기 조작시험","2024-04-17 10:00","2024-04-17 14:00","2024-04-17 10:00","2024-04-17 14:00","연속"]
[147,"경기북부","고양","양주지축#2 T/L","24-25 변전협력 총액공사","170kV GIS 보통점검","2024-04-23 09:00","2024-04-23 18:00","2024-04-23 09:00","2024-04-23 18:00","연속"]
[148,"경기북부","구리","내촌용정#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 내촌-용정T/L No.6~31","2024-04-24 12:00","2024-04-26 18:00","2024-04-24 12:00","2024-04-26 18:00","연속"]
[149,"경기북부","구리","내촌용정#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 내촌-용정T/L No.6~31","2024-04-22 07:00","2024-04-24 12:00","2024-04-22 07:00","2024-04-24 12:00","연속"]
[150,"경기북부","구리","옥정송우#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-04-15 09:00","2024-04-15 18:00","2024-04-15 09:00","2024-04-15 18:00","연속"]
[151,"경기북부","구리","신포천백학#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-04-22 09:00","2024-04-22 18:00","2024-04-22 09:00","2024-04-22 18:00","연속"]
[152,"경기북부","구리","신포천동두천#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-04-18 09:00","2024-04-18 18:00","2024-04-18 09:00","2024-04-18 18:00","연속"]
[153,"경기북부","구리","운천전곡#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-04-17 14:00","2024-04-17 18:00","2024-04-17 14:00","2024-04-17 18:00","연속"]
[154,"경기북부","구리","운천철원#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 운천-철원T/L No.59~66","2024-04-29 12:00","2024-04-30 18:00","2024-04-29 12:00","2024-04-30 18:00","연속"]
[155,"경기북부","구리","운천전곡#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-04-17 09:00","2024-04-17 14:00","2024-04-17 09:00","2024-04-17 14:00","연속"]
[156,"경기북부","구리","운천철원#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 운천-철원T/L No.65,66","2024-04-29 07:00","2024-04-29 12:00","2024-04-29 07:00","2024-04-29 12:00","연속"]
[157,"경기북부","구리","서홍천청평PP T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-04-08 09:00","2024-04-08 18:00","2024-04-08 09:00","2024-04-08 18:00","연속"]
[158,"경기북부","구리","서종청평PP#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-04-02 09:00","2024-04-02 18:00","2024-04-02 09:00","2024-04-02 18:00","연속"]
[159,"경기북부","구리","서종청평PP#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-04-01 09:00","2024-04-01 18:00","2024-04-01 09:00","2024-04-01 18:00","연속"]
[160,"경기북부","구리","청평PP춘천열병합 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-04-04 09:00","2024-04-04 18:00","2024-04-04 09:00","2024-04-04 18:00","연속"]
[161,"경기북부","구리","포천운천#2 T/L","154kV 포천S/S 옥내화 건설공사","송전선로 이설 및 가압","2024-04-01 09:00","2024-04-12 18:00","2024-04-01 09:00","2024-04-12 18:00","연속"]
[162,"경기북부","구리","신포천포천#1 T/L","154kV 포천S/S 옥내화 건설공사","송전선로 이설 및 가압","2024-04-01 09:00","2024-04-12 18:00","2024-04-01 09:00","2024-04-12 18:00","연속"]
[163,"경기북부","직할","양주녹양#2 T/L","24-25 변전협력 총액공사","녹양S/S 양주-녹양#2T/L GIS : 개폐타임 양주S/S 양주-녹양#2T/L GIS : 보통점검","2024-04-09 10:00","2024-04-09 18:00","2024-04-09 10:00","2024-04-09 18:00","연속"]
[164,"경기북부","직할","녹양백석#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 녹양-백석T/L No.5~12","2024-04-11 07:00","2024-04-11 18:00","2024-04-11 07:00","2024-04-11 18:00","연속"]
[165,"경기북부","직할","녹양백석#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 녹양-백석T/L No.5~12","2024-04-12 07:00","2024-04-12 18:00","2024-04-12 07:00","2024-04-12 18:00","연속"]
[166,"경기북부","직할","옥정동두천#2 T/L","24-25년 변전협력회사 총액공사","동두천SS 옥정-동두천#2TL 개폐타임측정","2024-04-02 09:00","2024-04-02 18:00","2024-04-02 09:00","2024-04-02 18:00","연속"]
[167,"경기북부","직할","옥정동두천#1 T/L","24-25년 변전협력회사 총액공사","동두천SS 옥정-동두천#1TL 개폐타임측정","2024-04-01 09:00","2024-04-01 18:00","2024-04-01 09:00","2024-04-01 18:00","연속"]
[168,"경기북부","직할","백석덕계#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 백석-덕계T/L No.6~9,22~28","2024-04-11 07:00","2024-04-11 18:00","2024-04-11 07:00","2024-04-11 18:00","연속"]
[169,"경기북부","직할","백석덕계#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 백석-덕계T/L No.6~9,22~28","2024-04-12 07:00","2024-04-12 18:00","2024-04-12 07:00","2024-04-12 18:00","연속"]
[170,"경기북부","직할","신의정부내촌#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 신의정부-내촌T/L No.1~4","2024-04-17 12:00","2024-04-17 18:00","2024-04-17 12:00","2024-04-17 18:00","연속"]
[171,"경기북부","직할","신의정부내촌#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 신의정부-내촌T/L No.1~4","2024-04-17 07:00","2024-04-17 12:00","2024-04-17 07:00","2024-04-17 12:00","연속"]
[172,"경기북부","직할","신의정부송우#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 신의정부-송우T/L No.13,19~28,30~36,39,40,48,49","2024-04-15 07:00","2024-04-17 12:00","2024-04-15 07:00","2024-04-17 12:00","연속"]
[173,"경기북부","직할","신의정부송우#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 신의정부-송우T/L No.13,19~28,30~36,39,40,48,49","2024-04-17 12:00","2024-04-19 18:00","2024-04-17 12:00","2024-04-19 18:00","연속"]
[174,"경기북부","직할","양주녹양#1 T/L","24~25년 고양전력지사 가공송전협력회사 공사","추락방지장치 설치","2024-04-15 07:00","2024-04-19 18:00","2024-04-15 07:00","2024-04-19 18:00","연속"]
[175,"경기북부","직할","양주은평#1 T/L","24~25년 고양전력지사 가공송전협력회사 공사","압축인류크램프 교체","2024-04-22 07:00","2024-04-22 18:00","2024-04-22 07:00","2024-04-22 18:00","연속"]
[176,"경기북부","직할","양주지축#1 T/L","24~25년 고양전력지사 가공송전협력회사 공사","SB댐퍼 교체","2024-04-22 07:00","2024-04-22 18:00","2024-04-22 07:00","2024-04-22 18:00","연속"]
[177,"경기북부","직할","양주쌍문#2 T/L","24~25년 고양전력지사 가공송전협력회사 공사","병가구간","2024-04-15 07:00","2024-04-15 18:00","2024-04-15 07:00","2024-04-15 18:00","연속"]
[178,"경기북부","직할","양주S/S CB 6300","24-25 변전협력 총액공사","양주S/S 6300 BUS TIE GIS : 보통점검","2024-04-22 10:00","2024-04-22 18:00","취소","취소","연속"]
[179,"경기북부","직할","양주S/S CB 6200","24-25 변전협력 총액공사","양주S/S 6200 BUS TIE GIS : 보통점검","2024-04-24 10:00","2024-04-24 18:00","2024-04-24 10:00","2024-04-24 18:00","연속"]
[180,"경기북부","직할","양주S/S CB 6100","24-25 변전협력 총액공사","양주S/S 6100 BUS TIE GIS : 보통점검","2024-04-23 10:00","2024-04-23 18:00","2024-04-23 10:00","2024-04-23 18:00","연속"]
[181,"경기","군포","서서울남군포#2 T/L","서서울,남군포S/S 서서울-남군포#2T/L GIS 보통점검","서서울,남군포S/S 서서울-남군포#2T/L GIS 보통점검","2024-04-17 14:00","2024-04-17 18:00","2024-04-17 14:00","2024-04-17 18:00","연속"]
[182,"경기","군포","서서울남군포#1 T/L","서서울,남군포S/S 서서울-남군포#1T/L GIS 보통점검","서서울,남군포S/S 서서울-남군포#1T/L GIS 보통점검","2024-04-17 09:00","2024-04-17 14:00","2024-04-17 09:00","2024-04-17 14:00","연속"]
[183,"경기","군포","남군포산본#1 T/L","154kV 남군포S/S SW증설공사","○154kV GIS 1CCT 증설 - 송전선로 무부하가압 및 전압위상 측정","2024-04-24 09:00","2024-04-25 18:00","2024-04-24 09:00","2024-04-25 18:00","연속"]
[184,"경기","군포","마도사강#1 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 25기","2024-04-01 07:00","2024-04-02 17:00","2024-04-01 07:00","2024-04-02 17:00","연속"]
[185,"경기","군포","화성마도 T/L","154kV 마도-사강T/L OPGW 증설공사","- OPGW 증설교체(OP-S-L24→L48) 10.196km - 광코어 접속, 최종시험 및 기타 부대공사 1식 * 마도-사강#2T/L No.52 작업을 위한 휴전","2024-04-27 07:00","2024-04-29 18:00","2024-04-27 07:00","2024-04-29 18:00","연속"]
[186,"경기","군포","마도사강#2 T/L","154kV 마도-사강T/L OPGW 증설공사","- OPGW 증설교체(OP-S-L24→L48) 10.196km - 광코어 접속, 최종시험 및 기타 부대공사 1식","2024-04-27 07:00","2024-04-29 18:00","2024-04-27 07:00","2024-04-29 18:00","연속"]
[187,"경기","군포","마도사강#2 T/L","154kV 마도-사강T/L OPGW 증설공사","- OPGW 증설교체(OP-S-L24→L48) 10.196km - 광코어 접속, 최종시험 및 기타 부대공사 1식","2024-04-13 07:00","2024-04-19 18:00","2024-04-13 07:00","2024-04-19 18:00","연속"]
[188,"경기","군포","목내성곡#2 T/L","목내S/S 목내-성곡#2T/L GIS 보통점검","목내S/S 목내-성곡#2T/L GIS 보통점검","2024-04-12 14:00","2024-04-12 18:00","취소","취소","연속"]
[189,"경기","군포","목내성곡#1 T/L","목내S/S 목내-성곡#1T/L GIS 보통점검","목내S/S 목내-성곡#1T/L GIS 보통점검","2024-04-12 09:00","2024-04-12 14:00","취소","취소","연속"]
[190,"경기","군포","반월시화#2 T/L","반월,시화SS 반월-시화#2T/L 세니온 성능개선","반월,시화SS 반월-시화#2T/L 세니온 성능개선(F/W 업데이트 및 MAX488 교체)","2024-04-18 09:00","2024-04-18 18:00","2024-04-18 09:00","2024-04-18 18:00","연속"]
[191,"경기","군포","남군포산본#2 T/L","산본SS 남군포-산본#2T/L GIS 보통점검","산본SS 남군포-산본#2T/L GIS 보통점검","2024-04-16 09:00","2024-04-16 18:00","2024-04-16 09:00","2024-04-16 18:00","연속"]
[192,"경기","군포","서서울#2서안양 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 28기","2024-04-03 07:00","2024-04-05 18:00","취소","취소","연속"]
[193,"경기","군포","성곡중시화 T/L","성곡SS 성곡-중시화T/L GIS 보통점검 및 세니온 성능개선","성곡SS 성곡-중시화T/L GIS 보통점검 및 성곡,중시화SS 송전선로보호반(단거리) 세니온 성능개선(F/W 업데이트)","2024-04-02 09:00","2024-04-02 18:00","취소","취소","연속"]
[194,"경기","군포","시화성곡 T/L","성곡S/S 시화-성곡T/L GIS 보통점검","성곡S/S 시화-성곡T/L GIS 보통점검 시화S/S 시화-성곡T/L GIS 조작시험","2024-04-11 09:00","2024-04-11 18:00","취소","취소","연속"]
[195,"경기","군포","신시흥시화#2 T/L","시화S/S 신시흥-시화#2T/L GIS 및 LA 보통점검","시화S/S 신시흥-시화#2T/L GIS 및 LA 보통점검","2024-04-09 09:00","2024-04-09 14:00","2024-04-09 09:00","2024-04-09 14:00","연속"]
[196,"경기","군포","시화동시화#1 T/L","시화SS 시화-동시화#1T/L GIS 조작시험 및 세니온 성능개선","시화SS 시화-동시화#1T/L GIS 조작시험 및 송전선로보호반(단거리) 세니온 성능개선(F/W 업데이트)","2024-04-04 09:00","2024-04-04 14:00","2024-04-04 09:00","2024-04-04 14:00","연속"]
[197,"경기","군포","시화동시화#2 T/L","시화SS 시화-동시화#2T/L GIS 조작시험 및 세니온 성능개선","시화SS 시화-동시화#2T/L GIS 조작시험 및 송전선로보호반(단거리) 세니온 성능개선(F/W 업데이트)","2024-04-04 14:00","2024-04-04 18:00","2024-04-04 14:00","2024-04-04 18:00","연속"]
[198,"경기","군포","시화중시화 T/L","시화SS 시화-중시화T/L GIS 보통점검 및 세니온 성능개선","시화SS 시화-중시화T/L GIS 보통점검 및 시화,중시화SS 송전선로보호반(단거리) 세니온 성능개선(F/W 업데이트)","2024-04-03 09:00","2024-04-03 18:00","2024-04-03 09:00","2024-04-03 18:00","연속"]
[199,"경기","군포","신시흥시화#1 T/L","시화S/S 신시흥-시화#1T/L GIS 및 LA 보통점검","시화S/S 신시흥-시화#1T/L GIS 및 LA 보통점검","2024-04-09 14:00","2024-04-09 18:00","2024-04-09 14:00","2024-04-09 18:00","연속"]
[200,"경기","군포","산본안양#1 T/L","2024년 가공송전 순시점검 위탁공사","154kV 산본안양#1T/L 정밀점검","2024-04-08 08:00","2024-04-09 18:00","취소","취소","연속"]
[201,"경기","군포","산본안양#2 T/L","2024년 가공송전 순시점검 위탁공사","154kV 산본안양#2T/L 정밀점검","2024-04-11 08:00","2024-04-12 18:00","취소","취소","연속"]
[202,"경기","군포","서서울#2일동#2 T/L","2024년 상반기 군포전력 170kV GIS 정밀점검","2024년 상반기 군포전력 170kV GIS 정밀점검(서서울#2-일동#2T/L)","2024-04-25 09:00","2024-04-26 18:00","2024-04-25 09:00","2024-04-26 18:00","연속"]
[203,"경기","군포","일동S/S CB 6100","2024년 상반기 군포전력 170kV GIS 정밀점검","2024년 상반기 군포전력 170kV GIS 정밀점검(6100 BUS-TIE)","2024-04-29 09:00","2024-04-30 18:00","2024-04-29 09:00","2024-04-30 18:00","연속"]
[204,"경기","군포","서서울#2일동#1 T/L","2024년 상반기 군포전력 170kV GIS 정밀점검","2024년 상반기 군포전력 170kV GIS 정밀점검(서서울#2-일동#1T/L)","2024-04-23 09:00","2024-04-24 18:00","2024-04-23 09:00","2024-04-24 18:00","연속"]
[205,"경기","동부","곤지암초월#1 T/L","24-25 동부전력지사 송전협력회사 총액공사","수평 추락방지장치 설치공사(1~59호)","2024-04-05 08:00","2024-04-17 18:00","2024-04-05 08:00","2024-04-17 18:00","연속"]
[206,"경기","동부","곤지암초월#2 T/L","24-25 동부전력지사 송전협력회사 총액공사","곤지암-초월#2T/L 1~59호 추락방지장치 설치공사","2024-04-18 08:00","2024-04-25 18:00","2024-04-18 08:00","2024-04-25 18:00","연속"]
[207,"경기","동부","오포모현#2 T/L","345kV 신용인-동서울 등 16개 T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 4회선 20기, 2회선 11","2024-04-27 07:00","2024-04-27 12:00","2024-04-27 07:00","2024-04-27 12:00","연속"]
[208,"경기","동부","오포모현#1 T/L","345kV 신용인-동서울 등 16개 T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 4회선 20기, 2회선 11","2024-04-27 13:00","2024-04-27 18:00","2024-04-27 13:00","2024-04-27 18:00","연속"]
[209,"경기","동부","분당오포#2 T/L","345kV 신용인-동서울 등 16개 T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 4회선 20기, 2회선 11","2024-04-27 13:00","2024-04-27 18:00","2024-04-27 13:00","2024-04-27 18:00","연속"]
[210,"경기","동부","분당오포#1 T/L","345kV 신용인-동서울 등 16개 T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 4회선 20기, 2회선 11","2024-04-27 07:00","2024-04-27 12:00","2024-04-27 07:00","2024-04-27 12:00","연속"]
[211,"경기","동부","분당오포#2 T/L","345kV 신용인-동서울 등 16개 T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 4회선 20기, 2회선 11","2024-04-06 07:00","2024-04-07 18:00","취소","취소","연속"]
[212,"경기","동부","성현분당#1 T/L","345kV 신용인-동서울 등 16개 T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 4회선 20기, 2회선 11","2024-04-06 07:00","2024-04-07 18:00","취소","취소","연속"]
[213,"경기","동부","분당오포#2 T/L","345kV 신용인-동서울 등 16개 T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 4회선 20기, 2회선 11","2024-04-11 09:00","2024-04-11 18:00","취소","취소","연속"]
[214,"경기","동부","왕암여주#2 T/L","24-25 동부전력지사 송전협력회사 총액공사","왕암-여주#2T/L 158~161호 추락방지장치 설치공사","2024-04-29 08:00","2024-04-29 18:00","2024-04-29 08:00","2024-04-29 18:00","연속"]
[215,"경기","동부","왕암여주#1 T/L","24-25 동부전력지사 송전협력회사 총액공사","왕암-여주#1T/L 158~161호 추락방지장치 설치공사","2024-04-26 08:00","2024-04-26 18:00","2024-04-26 08:00","2024-04-26 18:00","연속"]
[216,"경기","동부","오천율현#1 T/L","오천S/S #4M.Tr 증설공사",": #4M.Tr 1차 GIS (#61BUS) 증설분 무부하가압 시행","2024-04-06 09:00","2024-04-08 18:00","2024-04-06 09:00","2024-04-08 18:00","연속"]
[217,"경기","동부","오천율현#1 T/L","오천S/S #4M.Tr 증설공사",": #4M.Tr 1차 GIS (#66BUS) 증설분 무부하가압 시행","2024-04-13 09:00","2024-04-15 18:00","2024-04-13 09:00","2024-04-15 18:00","연속"]
[218,"경기","동부","서판교중원#1 T/L","24년 동부 변전협력총액공사","중원:서판교-중원#1TL(세니온 성능개선)","2024-04-01 09:30","2024-04-01 18:00","2024-04-01 09:30","2024-04-01 18:00","연속"]
[219,"경기","동부","초월성현#1 T/L","24-25 동부전력지사 송전협력회사 총액공사","초월-성현#1T/L 44-58호 추락방지장치 설치공사","2024-04-15 08:00","2024-04-17 18:00","취소","취소","연속"]
[220,"경기","동부","초월성현#2 T/L","24-25 동부전력지사 송전협력회사 총액공사","초월-성현#2T/L 44~58호 추락방지장치 설치공사","2024-04-23 08:00","2024-04-25 18:00","취소","취소","연속"]
[221,"경기","동부","곤지암S/S #61 BUS","24년 동부 변전협력총액공사","곤지암SS 61-66BUS PRO 대체","2024-04-22 09:00","2024-04-26 18:00","취소","취소","연속"]
[222,"경기","성남","신성남S/S SEC CB 61620","24년 성남전력지사 변전협력회사 총액공사","GIS 조작시험","2024-04-16 09:00","2024-04-16 14:00","취소","취소","연속"]
[223,"경기","성남","신성남S/S SEC CB 66670","24년 성남전력지사 변전협력회사 총액공사","GIS 조작시험","2024-04-16 14:00","2024-04-16 18:00","취소","취소","연속"]
[224,"경기","성남","신성남S/S SEC CB 62630","24년 성남전력지사 변전협력회사 총액공사","GIS 조작시험","2024-04-17 09:00","2024-04-17 14:00","취소","취소","연속"]
[225,"경기","성남","신성남S/S SEC CB 67680","24년 성남전력지사 변전협력회사 총액공사","GIS 조작시험","2024-04-17 14:00","2024-04-17 18:00","취소","취소","연속"]
[226,"경기","성남","신용인기흥#1 T/L","24-25년 경기직할 가공송전 협력회사 총액공사","고정형 폴리머 점퍼지지애자 및 철탑 추락방지장치 설치공사","2024-04-17 08:00","2024-04-18 18:00","2024-04-17 08:00","2024-04-18 18:00","연속"]
[227,"경기","성남","신용인S/S CB 6200","24년 성남전력지사 변전협력회사 총액공사","GIS 조작시험","2024-04-23 14:00","2024-04-23 18:00","2024-04-23 14:00","2024-04-23 18:00","연속"]
[228,"경기","성남","신용인동백#2 T/L","24-25년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사","2024-04-12 08:00","2024-04-12 18:00","2024-04-12 08:00","2024-04-12 18:00","연속"]
[229,"경기","성남","신용인기흥#2 T/L","24-25년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사","2024-04-09 08:00","2024-04-11 18:00","2024-04-09 08:00","2024-04-11 18:00","연속"]
[230,"경기","성남","신용인용인#1 T/L","24-25년 경기직할 가공송전 협력회사 총액공사","고정형 폴리머 점퍼지지애자 및 철탑 추락방지장치 설치공사","2024-04-04 08:00","2024-04-12 18:00","취소","취소","연속"]
[231,"경기","성남","신용인S/S CB 6300","24년 성남전력지사 변전협력회사 총액공사","GIS 조작시험","2024-04-24 09:00","2024-04-24 14:00","2024-04-24 09:00","2024-04-24 14:00","연속"]
[232,"경기","성남","신용인S/S SEC CB 60610","24년 성남전력지사 변전협력회사 총액공사","GIS 조작시험","2024-04-24 14:00","2024-04-24 18:00","취소","취소","연속"]
[233,"경기","성남","신용인S/S SEC CB 65660","24년 성남전력지사 변전협력회사 총액공사","GIS 조작시험","2024-04-25 09:00","2024-04-25 14:00","취소","취소","연속"]
[234,"경기","성남","신용인용인#2 T/L","24-25년 경기직할 가공송전 협력회사 총액공사","고정형 폴리머 점퍼지지애자 및 추락방지장치 설치공사","2024-04-15 08:00","2024-04-19 18:00","취소","취소","연속"]
[235,"경기","성남","신용인S/S CB 6100","24년 성남전력지사 변전협력회사 총액공사","GIS 조작시험","2024-04-23 09:00","2024-04-23 14:00","2024-04-23 09:00","2024-04-23 14:00","연속"]
[236,"경기","성남","신용인동백#2 T/L","24-25년 경기직할 가공송전 협력회사 총액공사","고정형 폴리머 점퍼지지애자 설치공사(안전거리)","2024-04-19 13:00","2024-04-19 18:00","2024-04-19 13:00","2024-04-19 18:00","연속"]
[237,"경기","성남","신용인동백#1 T/L","24-25년 경기직할 가공송전 협력회사 총액공사","국산 불량애자 교체공사(96년 상반기 이전)","2024-04-19 08:00","2024-04-19 13:00","2024-04-19 08:00","2024-04-19 13:00","연속"]
[238,"경기","성남","신용인S/S SEC CB 66670","24년 성남전력지사 변전협력회사 총액공사","GIS 조작시험","2024-04-26 09:00","2024-04-26 14:00","취소","취소","연속"]
[239,"경기","성남","신용인S/S SEC CB 61620","24년 성남전력지사 변전협력회사 총액공사","GIS 조작시험","2024-04-25 14:00","2024-04-25 18:00","취소","취소","연속"]
[240,"경기","성남","모현용인#2 T/L","2024년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검 CVT 하자점검, LA 보통점검","2024-04-03 09:00","2024-04-04 18:00","취소","취소","연속"]
[241,"경기","성남","모현용인#1 T/L","2024년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검 CVT 하자점검, LA 보통점검","2024-04-01 09:00","2024-04-02 18:00","취소","취소","연속"]
[242,"경기","성남","신성남정자#2 T/L","2024년 성남전력 345, 154 GIS 보통점검공사","(정자)GIS 보통점검 (신성남)GIS 조작시험","2024-04-12 09:00","2024-04-12 14:00","2024-04-12 09:00","2024-04-12 14:00","연속"]
[243,"경기","성남","신수원S/S #65 BUS","신수원S/S 154kV 동반T/L GIS 교체공사","동반#2T/L GIS 교체","2024-04-15 09:30","2024-04-16 14:00","2024-04-15 09:30","2024-04-16 14:00","연속"]
[244,"경기","성남","신수원S/S #60 BUS","신수원S/S 154kV 동반T/L GIS 교체공사","동반#2T/L GIS 교체","2024-04-16 14:00","2024-04-23 14:00","2024-04-16 14:00","2024-04-23 14:00","연속"]
[245,"경기","성남","신수원S/S #65 BUS","신수원S/S 154kV 동반T/L GIS 교체공사","동반#2T/L GIS 교체","2024-04-23 08:00","2024-04-25 18:00","2024-04-23 08:00","2024-04-25 18:00","연속"]
[246,"경기","성남","용인덕성#1 T/L","2024년 성남전력 170kV GIS 정밀점검공사 ","6200, 6533 무부하가압용 ","2024-04-23 21:00","2024-04-23 18:00","2024-04-23 21:00","2024-04-23 18:00","연속"]
[247,"경기","직할","서서울서수원#2 T/L","2024-25년 경기본부 직할 변전협력회사 총액공사","서수원: 서서울-서수원#2T/L 조작시험 - 전자변교체","2024-04-26 09:00","2024-04-26 18:00","2024-04-26 09:00","2024-04-26 18:00","연속"]
[248,"경기","직할","서서울서수원#1 T/L","2024-25년 경기본부 직할 변전협력회사 총액공사","서수원: 서서울-서수원#1T/L 조작시험 - 전자변교체","2024-04-23 09:00","2024-04-23 18:00","2024-04-23 09:00","2024-04-23 18:00","연속"]
[249,"경기","직할","율전의왕#1 T/L","의왕S/S 남군포-의왕#3T/L 증설공사","의왕S/S #2BUS 무부하가압","2024-04-03 14:00","2024-04-04 14:00","2024-04-03 14:00","2024-04-04 14:00","연속"]
[250,"경기","평택","고덕송탄#1 T/L","고덕S/S 154kV 고덕-송탄T/L 인출변경공사","#1T/L 인출변경","2024-04-15 09:00","2024-05-14 18:00","2024-05-09 09:00","2024-06-05 18:00","연속"]
[251,"경기","평택","오성C/C SEC CB 65660","24년도 평택전력 변전협력회사 총액공사","오성C/C 65-66 SEC 170kV GIS 보통점검","2024-04-04 09:00","2024-04-04 14:00","2024-04-04 09:00","2024-04-04 14:00","연속"]
[252,"경기","평택","오성C/C CB 6200","24년도 평택전력 변전협력회사 총액공사","오성C/C #2BUSTIE 170kV GIS 보통점검","2024-04-04 14:00","2024-04-04 18:00","2024-04-04 14:00","2024-04-04 18:00","연속"]
[253,"경기","평택","청북평택#2 T/L","154kV 오산-평택T/L 등 13개T/L 추락방지장치(수평) 설치공사","추락방지장치(수평) 31기 설치","2024-04-15 09:00","2024-04-17 18:00","2024-04-15 09:00","2024-04-17 18:00","연속"]
[254,"경기","평택","만호청북#1 T/L","154kV 오산-평택T/L 등 13개T/L 추락방지장치(수평) 설치공사","추락방지장치(수평) 31기 설치","2024-04-15 09:00","2024-04-17 18:00","취소","취소","연속"]
[255,"경기","평택","청북평택#1 T/L","154kV 오산-평택T/L 등 13개T/L 추락방지장치(수평) 설치공사","추락방지장치(수평) 31기 설치","2024-04-18 09:00","2024-04-20 18:00","2024-04-18 09:00","2024-04-20 18:00","연속"]
[256,"경기","평택","둔포추팔#1 T/L","154kV 오산-평택T/L 등 13개T/L 추락방지장치(수평) 설치공사","추락방지장치(수평) 18기 설치","2024-04-26 09:00","2024-04-28 15:00","취소","취소","연속"]
[257,"경기","평택","둔포추팔#2 T/L","154kV 오산-평택T/L 등 13개T/L 추락방지장치(수평) 설치공사","추락방지장치(수평) 1기 설치","2024-04-28 15:00","2024-04-28 18:00","취소","취소","연속"]
[258,"경기","평택","평택추팔#2 T/L","154kV 오산-평택T/L 등 13개T/L 추락방지장치(수평) 설치공사","추락방지장치(수평) 1기 설치","2024-04-28 12:00","2024-04-28 15:00","2024-04-28 12:00","2024-04-28 15:00","연속"]
[259,"경기","평택","평택추팔#1 T/L","154kV 오산-평택T/L 등 13개T/L 추락방지장치(수평) 설치공사","추락방지장치(수평) 1기 설치","2024-04-28 15:00","2024-04-28 18:00","2024-04-28 15:00","2024-04-28 18:00","연속"]
[260,"경기","평택","포승청북 T/L","154kV 오산-평택T/L 등 13개T/L 추락방지장치(수평) 설치공사","추락방지장치(수평) 31기 설치","2024-04-18 09:00","2024-04-20 18:00","취소","취소","연속"]
[261,"강원","강릉","동해강릉 T/L","2024-2025년 송전협력회사 공사","○ 수평 추락방지장치 설치 : 154kV 동해분기T/L No.1~53.1, 강릉T/L No.8.1~63","2024-04-24 08:00","2024-05-07 18:00","2024-04-24 08:00","2024-05-07 18:00","매일"]
[262,"강원","강릉","동해영동TP T/L","2024-2025년 송전협력회사 공사","○ 수평 추락방지장치 설치 : 154kV 동해분기T/L No.1~53.1","2024-04-11 08:00","2024-04-12 18:00","2024-04-11 08:00","2024-04-12 18:00","매일"]
[263,"강원","동해","동해T/P 동해바이오매스T/L CB","24년~25년 동해전력지사 변전정비회사 총액공사","GIS 보통점검","2024-04-19 09:30","2024-04-19 18:00","2024-04-19 09:30","2024-04-19 18:00","연속"]
[264,"강원","동해","동해강릉 T/L","24~25년 동해전력지사 가공송전 협력회사공사","154kV 동해-강릉T/L 전선접속개소 해소 및 관형지지물 가이드레일 설치","2024-04-17 08:00","2024-04-23 18:00","2024-04-17 08:00","2024-04-23 18:00","연속"]
[265,"강원","동해","동해영동TP T/L","24~25년 동해전력지사 가공송전 협력회사공사","154kV 동해-영동TPT/L 전선접속개소 해소 및 관형지지물 가이드레일 설치","2024-04-15 08:00","2024-04-19 18:00","2024-04-15 08:00","2024-04-19 18:00","연속"]
[266,"강원","동해","북평영동TP#1 T/L","24년~25년 동해전력지사 변전정비회사 총액공사","GIS 정밀점검","2024-04-22 09:30","2024-04-24 18:00","2024-04-22 09:30","2024-04-24 18:00","연속"]
[267,"강원","동해","북평영동TP#2 T/L","24년~25년 동해전력지사 변전정비회사 총액공사","GIS 정밀점검","2024-04-25 09:30","2024-04-27 18:00","2024-04-25 09:30","2024-04-27 18:00","연속"]
[268,"강원","동해","태백삼척GP#2 T/L","24년~25년 동해전력지사 변전정비회사 총액공사","GIS 보통점검, LA점검","2024-04-15 09:30","2024-04-15 18:00","2024-04-15 09:30","2024-04-15 18:00","연속"]
[269,"강원","원주","문막지제#1 T/L","24-25년 원주전력지사 변전협력회사 총액공사","차단기 동작시험, CVT, 피뢰기 점검","2024-04-01 10:00","2024-04-01 18:00","2024-04-01 10:00","2024-04-01 18:00","연속"]
[270,"강원","원주","문막지제#2 T/L","24-25년 원주전력지사 변전협력회사 총액공사","차단기 동작시험, CVT, 피뢰기 점검","2024-04-02 10:00","2024-04-02 18:00","2024-04-02 10:00","2024-04-02 18:00","연속"]
[271,"강원","원주","상남인제#2 T/L","24-25년 원주전력지사 변전협력회사 총액공사","차단기 동작시험","2024-04-05 10:00","2024-04-05 18:00","2024-04-05 10:00","2024-04-05 18:00","연속"]
[272,"강원","원주","홍천상남#2 T/L","24-25년 원주전력지사 변전협력회사 총액공사","차단기 동작시험","2024-04-03 10:00","2024-04-03 18:00","2024-04-03 10:00","2024-04-03 18:00","연속"]
[273,"강원","원주","홍천소양강HP T/L","2024년 가공송전 순시점검 위탁공사","154kV 소양T/L 정밀점검","2024-04-01 09:00","2024-04-09 18:00","2024-04-01 09:00","2024-04-09 18:00","연속"]
[274,"강원","직할","홍천남춘천 T/L","2024~25년 강원직할 변전정비 총액공사","○ 남춘천S/S 154kV 홍천-남춘천T/L 보호배전반 대체 ○ (원주전력)홍천S/S 154kV 남춘천-춘천T/L 보호배전반 대체","2024-03-25 09:00","2024-03-29 18:00","취소","취소","연속"]
[275,"강원","직할","북춘천춘천HP T/L","2024~2025년 강원본부 직할 변전협력회사 공사","□ 북춘천S/S 154kV 북춘천-춘천HPT/L GIS 보통점검","2024-04-08 09:00","2024-04-08 18:00","2024-04-08 09:00","2024-04-08 18:00","연속"]
[276,"강원","직할","춘천북춘천#2 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","□ 북춘천S/S 154kV 춘천-북춘천#2T/L GIS 보통점검 □ 북춘천S/S 154kV 춘천-북춘천#2T/L GIS 누유 개소 점검","2024-04-04 09:00","2024-04-04 18:00","2024-04-04 09:00","2024-04-04 18:00","연속"]
[277,"강원","직할","춘천북춘천#1 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","□ 북춘천S/S 154kV 춘천-북춘천#1T/L GIS 보통점검","2024-04-03 09:00","2024-04-03 18:00","2024-04-03 09:00","2024-04-03 18:00","연속"]
[278,"강원","직할","서홍천청평PP T/L","24~25년 강원본부 직할 변전협력회사 공사","서홍천청평PP T/L GIS 보통점검","2024-04-12 10:00","2024-04-12 18:00","취소","취소","연속"]
[279,"강원","직할","서홍천춘천열병합 T/L","765kV 신안성-신가평 등 12개T/L 추락방지 설치공사","345kV 신가평-포천LNG #2T/L 추락방지 설치(병가(하단) : 서홍천-춘천열병합)","2024-04-29 07:00","2024-05-03 18:00","2024-04-29 07:00","2024-05-03 18:00","연속"]
[280,"강원","직할","서홍천청평PP T/L","765kV 신안성-신가평 등 12개T/L 추락방지 설치공사","345kV 신가평-포천LNG #1T/L 추락방지 설치(병가(하단) : 서홍천-청평)","2024-04-08 07:00","2024-04-12 18:00","2024-04-08 07:00","2024-04-12 18:00","연속"]
[281,"강원","직할","인제양구#2 T/L","154kV 상제 등 3개 T/L 추락방지장치 설치공사","154KV 양구 T/L 추락방지장치 설치","2024-04-08 09:00","2024-04-19 18:00","2024-04-08 09:00","2024-04-19 18:00","매일"]
[282,"강원","직할","양구화천HP#2 T/L","24~25년 강원본부 직할 변전협력회사 공사","양구화천HP#2 T/L GIS, GCB 보통점검","2024-04-11 10:00","2024-04-11 18:00","2024-04-11 10:00","2024-04-11 18:00","연속"]
[283,"강원","직할","양구화천HP#1 T/L","24~25년 강원본부 직할 변전협력회사 공사","양구화천HP#1 T/L GIS, GCB 보통점검","2024-04-18 10:00","2024-04-18 18:00","2024-04-18 10:00","2024-04-18 18:00","연속"]
[284,"강원","직할","상남인제#2 T/L","154kV 상제 등 3개 T/L 추락방지장치 설치공사","154kV 상제, 양구 T/L 추락방지장치 설치공사","2024-04-22 09:00","2024-05-03 18:00","2024-04-22 09:00","2024-05-03 18:00","매일"]
[285,"강원","직할","철원화천#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 병가선로 - 대상 : 154kV 운천-철원T/L No.65,66 - 병가선로 : 154kV 철원-화천T/L No.2,3","2024-04-29 07:00","2024-04-29 12:00","2024-04-29 07:00","2024-04-29 12:00","연속"]
[286,"강원","직할","철원화천#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 병가선로 - 대상 : 154kV 운천-철원T/L No.65,66 - 병가선로 : 154kV 철원-화천T/L No.2,3","2024-04-29 12:00","2024-04-29 18:00","2024-04-29 12:00","2024-04-29 18:00","연속"]
[287,"강원","직할","철원S/S 비즌비츠로#1T/L CB","2024~2025년 강원본부 직할 변전협력회사 공사","○ 철원S/S 154kV 비즌비츠로T/L GIS 가스누기 보수","2024-04-16 09:00","2024-04-16 18:00","2024-04-16 09:00","2024-04-16 18:00","연속"]
[288,"강원","직할","춘천소양강HP T/L","2024년 가공송전 순서짐검 위탁공사","154kV 소양 T/L 정밀점검","2024-04-15 09:00","2024-04-17 18:00","2024-04-15 09:00","2024-04-17 18:00","연속"]
[289,"강원","직할","화천화천HP#1 T/L","2024년 가공송전 순시점검 위탁공사","154kV 화천수력 T/L 정밀점검","2024-04-18 09:00","2024-04-29 18:00","2024-04-18 09:00","2024-04-29 18:00","연속"]
[290,"강원","직할","화천화천HP#2 T/L","2024년 가공송전 순시점검 위탁공사","154kV 화천수력 T/L 정밀점검","2024-04-30 09:00","2024-05-10 18:00","2024-04-30 09:00","2024-05-10 18:00","연속"]
[291,"강원","태백","고한영월에코윈드 T/L","2024~2025년 태백전력지사 가공송전 협력회사 총액공사","154kV 고한-영월에코윈드T/L 빙설해 피해구간 전력선 소손개소 전선교체 시행","2024-04-01 09:00","2024-04-09 18:00","2024-04-01 09:00","2024-04-09 18:00","연속"]
[292,"강원","태백","태백고한 T/L","2024-2025년 태백전력지사 변전협력회사 공사","154kV 태백고한 T/L PNL 대체공사 고한S/S 154kV 태백-고한T/L GIS 보통점검 (병행) 고한S/S 154kV 태백-고한T/L LA 초기점검 (병행)","2024-04-15 09:00","2024-04-18 18:00","2024-04-15 09:00","2024-04-18 18:00","연속"]
[293,"충북","직할","신진천오창#1 T/L","2024년 가공송전선로 순시점검 위탁공사","154kV 신진천-진천 T/L 정밀점검 (154kV 신진천-오창 T/L No.1~2 병가구간)","2024-04-25 08:00","2024-04-26 18:00","취소","취소","매일"]
[294,"충북","직할","신진천S/S SEC CB 61620","24~25 직할 변전협력회사 총액공사(장기미동작)","신진천S/S 154kV #61-#62 SEC CB 장기미동작 차단기 조작시험","2024-04-04 14:00","2024-04-04 18:00","취소","취소","연속"]
[295,"충북","직할","신진천진천#2 T/L","2024년 가공송전선로 순시점검 위탁공사","154kV 신진천-진천 T/L 정밀점검","2024-04-22 08:00","2024-04-26 18:00","취소","취소","매일"]
[296,"충북","직할","신진천S/S CB 6300","24~25 직할 변전협력회사 총액공사(장기미동작)","신진천S/S 154kV #62-#67 BUS TIE CB 장기미동작 차단기 조작시험","2024-04-19 15:30","2024-04-19 18:00","2024-04-19 15:30","2024-04-19 18:00","연속"]
[297,"충북","직할","신진천S/S CB 6200","24~25 직할 변전협력회사 총액공사(장기미동작)","신진천S/S 154kV #61-#66 BUS TIE CB 장기미동작 차단기 조작시험","2024-04-19 13:00","2024-04-19 15:30","2024-04-19 13:00","2024-04-19 15:30","연속"]
[298,"충북","직할","신진천S/S CB 6100","24~25 직할 변전협력회사 총액공사(장기미동작)","신진천S/S 154kV #60-#65 BUS TIE CB 장기미동작 차단기 조작시험","2024-04-19 09:00","2024-04-19 12:00","2024-04-19 09:00","2024-04-19 12:00","연속"]
[299,"충북","직할","신진천오창#2 T/L","2024년 가공송전선로 순시점검 위탁공사","154kV 신진천-진천 T/L 정밀점검 (154kV 신진천-오창 T/L No.1~2 병가구간)","2024-04-18 08:00","2024-04-19 18:00","취소","취소","매일"]
[300,"충북","직할","신진천진천#2 T/L","154kV 신진천-오창T/L OPGW 증설공사","4회선 병가구간 2~3호 OPGW 증설","2024-04-17 07:00","2024-04-17 18:00","취소","취소","연속"]
[301,"충북","직할","신진천진천#1 T/L","2024년 가공송전선로 순시점검 위탁공사","154kV 신진천-진천 T/L 정밀점검","2024-04-15 08:00","2024-04-19 18:00","취소","취소","매일"]
[302,"충북","직할","신진천S/S SEC CB 60610","24~25 직할 변전협력회사 총액공사(장기미동작)","신진천S/S 154kV #60-#61 SEC CB 장기미동작 차단기 조작시험","2024-04-04 10:00","2024-04-04 14:00","취소","취소","연속"]
[303,"충북","직할","신진천S/S #66 BUS","154kV 문백S/S 및 분기T/L 건설공사","1. 154kV 문백S/S 최초가압 2. 154kV 신진천-문백#1T/L 최초가압","2024-04-22 10:00","2024-04-22 18:00","취소","취소","연속"]
[304,"충북","직할","신진천오창#1 T/L","154kV 문백S/S 및 분기T/L 건설공사","1. 154kV 신진천-문백#1T/L, 문백-오창#1T/L 건설공사 2. 154kV 문백S/S 최초가압 3. 154kV 신진천-문백#1T/L, 문백-오창#1T/L 최초가압","2024-04-17 07:00","2024-04-24 18:00","2024-04-17 07:00","2024-04-24 18:00","연속"]
[305,"충북","직할","신진천S/S SEC CB 66670","24~25 직할 변전협력회사 총액공사(장기미동작)","신진천S/S 154kV #66-#67 SEC CB 장기미동작 차단기 조작시험","2024-04-12 14:00","2024-04-12 18:00","취소","취소","연속"]
[306,"충북","직할","신진천S/S SEC CB 65660","24~25 직할 변전협력회사 총액공사(장기미동작)","신진천S/S 154kV #65-#66 SEC CB 장기미동작 차단기 조작시험","2024-04-12 10:00","2024-04-12 14:00","취소","취소","연속"]
[307,"충북","직할","진천S/S #61 BUS","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #4M.Tr 1차측 1DS부 정밀점검","2024-04-18 12:00","2024-04-19 16:00","2024-04-18 12:00","2024-04-19 16:00","연속"]
[308,"충북","직할","진천S/S CB 6200","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #4M.Tr 2DS 무부하 가압용","2024-04-18 10:00","2024-04-18 12:00","2024-04-18 10:00","2024-04-18 12:00","연속"]
[309,"충북","직할","진천S/S #66 BUS","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #3M.Tr 1차측 2DS 건전성 확인 및 진천S/S 154kV #4M.Tr 1차측 2DS 정밀정검","2024-04-17 12:00","2024-04-18 12:00","2024-04-17 12:00","2024-04-18 12:00","연속"]
[310,"충북","직할","진천S/S CB 6200","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #3M.Tr 1,2DS 무부하 가압용","2024-04-17 10:00","2024-04-17 14:00","2024-04-17 10:00","2024-04-17 14:00","연속"]
[311,"충북","직할","진천S/S #61 BUS","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #3M.Tr 1차측 1DS부 정밀점검","2024-04-16 12:00","2024-04-17 12:00","2024-04-16 12:00","2024-04-17 12:00","연속"]
[312,"충북","직할","진천S/S CB 6200","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #3M.Tr 2DS 무부하 가압용","2024-04-16 10:00","2024-04-16 12:00","2024-04-16 10:00","2024-04-16 12:00","연속"]
[313,"충북","직할","진천S/S #66 BUS","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #3M.Tr 1차측 2DS부 정밀점검","2024-04-15 09:00","2024-04-16 12:00","2024-04-15 09:00","2024-04-16 12:00","연속"]
[314,"충북","직할","진천S/S #60 BUS","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #1M.Tr 1차측 1DS부 정밀점검","2024-04-30 12:00","2024-05-01 12:00","취소","취소","연속"]
[315,"충북","직할","진천S/S CB 6100","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #1M.Tr 2DS 무부하 가압용","2024-04-30 10:00","2024-04-30 12:00","취소","취소","연속"]
[316,"충북","직할","진천S/S #65 BUS","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #1M.Tr 1차측 2DS부 정밀점검","2024-04-29 09:00","2024-04-30 12:00","취소","취소","연속"]
[317,"충북","직할","진천S/S #65 BUS","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #60-65 BUS TIE GIS 2DS 무부하 가압","2024-04-26 16:00","2024-04-26 18:00","취소","취소","연속"]
[318,"충북","직할","진천S/S SEC CB 65660","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #60-65 BUS TIE GIS 2DS 무부하 가압용","2024-04-26 16:00","2024-04-26 18:00","취소","취소","연속"]
[319,"충북","직할","진천S/S SEC CB 60610","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #60-65 BUS TIE GIS 1DS 무부하 가압용","2024-04-26 14:00","2024-04-26 16:00","2024-04-26 14:00","2024-04-26 16:00","연속"]
[320,"충북","직할","진천S/S #60 BUS","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #60-65 BUS TIE GIS 1DS 정밀점검","2024-04-25 12:00","2024-04-26 16:00","취소","취소","연속"]
[321,"충북","직할","진천S/S SEC CB 65660","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #60-65 BUS TIE GIS 2DS 무부하 가압용","2024-04-25 10:00","2024-04-25 12:00","취소","취소","연속"]
[322,"충북","직할","진천S/S CB 6100","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #60-65 BUS TIE GIS 정밀점검 공사","2024-04-24 14:00","2024-04-26 18:00","취소","취소","연속"]
[323,"충북","직할","진천S/S #65 BUS","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #60-65 BUS TIE GIS 2DS 정밀점검","2024-04-24 14:00","2024-04-25 12:00","취소","취소","연속"]
[324,"충북","직할","진천S/S #66 BUS","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #5M.Tr 1차측 2DS부 무부하 가압","2024-04-24 12:00","2024-04-24 14:00","2024-04-24 12:00","2024-04-24 14:00","연속"]
[325,"충북","직할","진천S/S CB 6200","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #5M.Tr 1,2DS 무부하 가압용","2024-04-24 10:00","2024-04-24 14:00","2024-04-24 10:00","2024-04-24 14:00","연속"]
[326,"충북","직할","진천S/S #61 BUS","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #5M.Tr 1차측 1DS부 정밀점검","2024-04-23 12:00","2024-04-24 12:00","2024-04-23 12:00","2024-04-24 12:00","연속"]
[327,"충북","직할","진천S/S CB 6200","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #5M.Tr 2DS 무부하 가압용","2024-04-23 10:00","2024-04-23 12:00","2024-04-23 10:00","2024-04-23 12:00","연속"]
[328,"충북","직할","진천S/S #66 BUS","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #5M.Tr 1차측 2DS부 정밀점검","2024-04-22 09:00","2024-04-23 12:00","2024-04-22 09:00","2024-04-23 12:00","연속"]
[329,"충북","직할","진천S/S #66 BUS","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #4M.Tr 1차측 2DS 무부하 가압","2024-04-19 16:00","2024-04-19 18:00","2024-04-19 16:00","2024-04-19 18:00","연속"]
[330,"충북","직할","진천S/S CB 6200","'24년 충북 직할 154kV GIS 정밀점검공사","진천S/S 154kV #4M.Tr 1,2DS 무부하 가압용","2024-04-19 14:00","2024-04-19 18:00","2024-04-19 14:00","2024-04-19 18:00","연속"]
[331,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-04-15 08:00","2024-04-18 14:00","2024-04-15 08:00","2024-04-18 14:00","연속"]
[332,"충북","청주","남청주청주#4 T/L","2024~2025년 송전정비 협력회사 총액공사","154kV 남청주-청주#2,#4T/L(아킹혼, 폴리머지지애자 설치) 1. 내용 : 아킹혼, 폴리머지지애자 설치 2. 구간 : 남청주S/S~청주S/S","2024-04-15 08:00","2024-05-03 18:00","2024-04-15 08:00","2024-05-03 18:00","매일"]
[333,"충북","청주","남청주청주#2 T/L","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-04-15 08:00","2024-05-03 18:00","2024-04-15 08:00","2024-05-03 18:00","연속"]
[334,"충북","청주","남청주S/S #61 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-04-18 14:00","2024-04-26 14:00","2024-04-18 14:00","2024-04-26 14:00","연속"]
[335,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-04-26 14:00","2024-05-03 18:00","2024-04-26 14:00","2024-05-03 18:00","연속"]
[336,"충북","청주","화동보은 T/L","2024~2025년 청주전력지사 변전협력회사 공사","170kV GIS 보통점검","2024-04-08 10:00","2024-04-08 18:00","취소","취소","연속"]
[337,"충북","청주","화동영동 T/L","2024~2025년 송전정비 협력회사 총액공사","154kV 화동-영동T/L 추락방지장치 설치(수평설치) 1. 내용 : 화동-영동T/L 수평 추락방지장치 설치 2. 구간 : 154kV 화동-영동T/L 60~110호 154kV 영동분기T/L 1~61호","2024-04-01 08:00","2024-04-15 18:00","취소","취소","매일"]
[338,"충북","청주","옥천영동 T/L","2024~2025년 송전정비 협력회사 총액공사","154kV 옥천-영동T/L 추락방지장치 설치(수평설치) 1. 내용 : 옥천-영동T/L 수평 추락방지장치 설치 2. 구간 : 154kV 영동분기T/L 1~61호","2024-04-16 08:00","2024-04-22 18:00","취소","취소","매일"]
[339,"충북","청주","오창국사#2 T/L","154kV 문백S/S 및 분기T/L 건설공사","1. 154kV 문백S/S 최초가압 2. 154kV 문백-오창#1T/L 무부하가압","2024-04-22 10:00","2024-04-23 18:00","취소","취소","연속"]
[340,"충북","청주","옥천보은 T/L","2024~2025년 청주전력지사 변전협력회사 공사","170kV GIS 보통점검(옥천,보은 양단점검) LA 체","2024-04-03 10:00","2024-04-03 18:00","취소","취소","연속"]
[341,"충북","청주","신옥천옥천#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사","170kV GIS 보통점검","2024-04-11 10:00","2024-04-11 18:00","2024-04-11 10:00","2024-04-11 18:00","연속"]
[342,"충북","청주","신옥천옥천#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사","170kV GIS 보통점검","2024-04-12 10:00","2024-04-12 18:00","2024-04-12 10:00","2024-04-12 18:00","연속"]
[343,"충북","충주","금왕남음성#2 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","154kV 금왕-남음성#2T/L 수평 추락방지장치 및 피뢰기 설치 - 수평 추락방지장치(23기) : No.2~6, 9~26 - 피뢰기 설치(25기) : No.2~26","2024-04-22 07:30","2024-04-26 18:00","2024-04-22 07:30","2024-04-26 18:00","매일"]
[344,"충북","충주","북충주충주 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (42기)","2024-04-12 07:30","2024-04-19 16:30","2024-04-12 07:30","2024-04-19 16:30","매일"]
[345,"충북","충주","신제천S/S SEC CB 66670","'24-25년 충주전력지사 변전정비 총액공사","신제천S/S 154kV #66-67BUS SEC 보통점검","2024-04-26 13:00","2024-04-26 18:00","취소","취소","연속"]
[346,"충북","충주","신제천왕암#2 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.1, 28~37)","2024-04-22 07:30","2024-04-23 16:30","취소","취소","매일"]
[347,"충북","충주","신제천왕암#1 T/L","345kV 신제천-신충주 등 6개T/L 피뢰기 설치공사","154kV 신제천-왕암#1T/L No.1~37 피뢰기설치","2024-04-13 07:00","2024-04-14 18:00","취소","취소","매일"]
[348,"충북","충주","신제천왕암#1 T/L","345kV 신제천-신충주 등 6개T/L 피뢰기 설치공사","154kV 신제천-왕암#1T/L No.1~37 피뢰기설치","2024-04-07 07:00","2024-04-07 18:00","취소","취소","매일"]
[349,"충북","충주","신제천제천#1 T/L","345kV 신제천-신충주 등 6개T/L 피뢰기 설치공사","154kV 신제천-제천#1T/L No.1~27.10 피뢰기설치","2024-04-07 07:00","2024-04-08 18:00","취소","취소","매일"]
[350,"충북","충주","신제천S/S SEC CB 60610","'24-25년 충주전력지사 변전정비 총액공사","신제천S/S 154kV #60-#61 SEC GIS 보통점검","2024-04-30 10:00","2024-04-30 14:00","취소","취소","연속"]
[351,"충북","충주","신제천S/S SEC CB 61620","'24-25년 충주전력지사 변전정비 총액공사","신제천S/S 154kV #61-#62 SEC GIS 보통점검","2024-04-30 14:00","2024-04-30 18:00","취소","취소","연속"]
[352,"충북","충주","신제천제천#1 T/L","345kV 신제천-신충주 등 6개T/L 피뢰기 설치공사","154kV 신제천-제천#1T/L No.1~27.10 피뢰기설치","2024-04-12 07:00","2024-04-14 18:00","취소","취소","매일"]
[353,"충북","충주","신충주북충주#1 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 : 43기 - No.1~25 (25기) - No.70~87 (18기)","2024-04-01 07:30","2024-04-07 16:30","2024-04-01 07:30","2024-04-07 16:30","매일"]
[354,"충북","충주","신충주북충주#2 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 : 43기 - No.1~25, 70~87","2024-04-08 07:30","2024-04-12 16:30","2024-04-08 07:30","2024-04-12 16:30","매일"]
[355,"충북","충주","신충주음성#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","154kV 신충주-음성#1T/L 피뢰기 설치 - 피뢰기 설치(7기) : No.64~70","2024-04-29 07:30","2024-04-30 18:00","취소","취소","매일"]
[356,"충북","충주","왕암충주 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 : 46기 (No.27, 51~58, 71~95, 97~105, 107, 108, 110)","2024-04-22 07:30","2024-04-28 16:30","취소","취소","매일"]
[357,"충북","충주","왕암북충주 T/L","2024~2025년 충주전력지사 송전협력회사 공사","154kV 왕암-북충주T/L No.20등 12개소 압축인류클램프 보수공사","2024-04-01 07:30","2024-04-04 18:00","취소","취소","매일"]
[358,"충북","충주","음성금왕#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","154kV 음성-금왕#1T/L 수평 추락방지장치 및 피뢰기 설치, 애자교체 - 수평 추락방지장치(60기) : No.1, 8~57, 60~65 - 피뢰기 설치(69기) : No.1~65 - 애자교체(1기) : 음성S/T","2024-04-11 07:30","2024-04-30 18:00","취소","취소","매일"]
[359,"충북","충주","충주충주HP#2 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.7~22)","2024-04-15 07:30","2024-04-19 16:30","2024-04-15 07:30","2024-04-19 16:30","매일"]
[360,"충북","충주","충주충주HP#1 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.7~22)","2024-04-22 07:30","2024-04-24 16:30","2024-04-22 07:30","2024-04-24 16:30","매일"]
[361,"대전세종충남","대전","신옥천남대전#3 T/L","남대전SA 154kV 신옥천-남대전#3/L GIS 초기점검","남대전SA 154kV 신옥천-남대전#3/L GIS 초기점검","2024-04-16 09:00","2024-04-16 18:00","2024-04-16 09:00","2024-04-16 18:00","연속"]
[362,"대전세종충남","대전","신옥천남대전#2 T/L","남대전SA 154kV 신옥천-남대전#2T/L GIS 초기점검","남대전SA 154kV 신옥천-남대전#2T/L GIS 초기점검","2024-04-15 09:00","2024-04-15 18:00","2024-04-15 09:00","2024-04-15 18:00","연속"]
[363,"대전세종충남","대전","남대전신흥#3 T/L","남대전SA 154kV 남대전-신흥#3T/L GIS 초기점검","남대전SA 154kV 남대전-신흥#3T/L GIS 초기점검","2024-04-17 09:00","2024-04-17 18:00","2024-04-17 09:00","2024-04-17 18:00","연속"]
[364,"대전세종충남","대전","신계룡은진#1 T/L","[송전] 345kV 신옥천-청양 등 8개T/L 철탑 추락방지시설 설치공사","[송전] 154kV 신계룡-은진 #1T/L 철탑 추락방지시설 설치공사","2024-04-22 07:00","2024-05-08 18:00","취소","취소","매일"]
[365,"대전세종충남","대전","신계룡두마#1 T/L","[송전] 345kV 신옥천-청양 등 8개T/L 철탑 추락방지시설 설치공사","[송전] 154kV 신계룡-두마 #1T/L 철탑 추락방지시설 설치공사","2024-04-17 07:00","2024-04-29 18:00","취소","취소","매일"]
[366,"대전세종충남","대전","용운대화#1 T/L","[송전] 154kV 신옥천-용운 등 2개T/L 추락방지시설 설치공사","[송전] 154kV 용운-대화#1T/L 추락방지시설 및 피뢰기 설치공사","2024-04-22 07:00","2024-04-22 18:00","2024-04-22 07:00","2024-04-22 18:00","매일"]
[367,"대전세종충남","대전","용운대화#2 T/L","[송전] 154kV 신옥천-용운 등 2개T/L 추락방지시설 설치공사","[송전] 154kV 용운-대화#2T/L 추락방지시설 설치공사","2024-04-15 07:00","2024-04-15 18:00","2024-04-15 07:00","2024-04-15 18:00","매일"]
[368,"대전세종충남","대전","신옥천용운#2 T/L","[송전] 154kV 신옥천-용운 등 2개T/L 추락방지시설 설치공사","[송전] 154kV 신옥천-용운#2T/L 추락방지시설 설치공사","2024-04-22 07:00","2024-04-26 18:00","2024-04-22 07:00","2024-04-26 18:00","매일"]
[369,"대전세종충남","대전","신옥천용운#1 T/L","[송전] 154kV 신옥천-용운 등 2개T/L 추락방지시설 설치공사","[송전] 154kV 신옥천-용운#1T/L 추락방지시설 설치공사","2024-04-15 07:00","2024-04-19 18:00","2024-04-15 07:00","2024-04-19 18:00","매일"]
[370,"대전세종충남","서산","석문당진화력#2 T/L","효성제 170kV GIS 베어링 교체공사","(3월 휴전신청 취소시) 당진화력S/S 154kV 석문-당진화력#2T/L 627 CB 베어링 교체 (병행) 석문S/S 154kV 석문-당진화력#2T/L IED 성능개선 (병행) 석문S/S 154kV 석문-당진화력#2T/L 687 CB 보통점검 (병행) 당진화력S/S 154kV 석문-당진화력#2T/L 627 CB 보통점검","2024-04-24 09:00","2024-04-25 18:00","취소","취소","매일"]
[371,"대전세종충남","서산","석문당진화력#1 T/L","효성제 170kV GIS 베어링 교체공사","(3월 휴전신청 취소시) 당진화력S/S 154kV 석문-당진화력T/L 617 CB 베어링 교체 (병행) 석문S/S 154kV 석문-당진화력#1T/L IED 성능개선 (병행) 석문S/S 154kV 석문-당진화력#1T/L 617 CB 보통점검 (병행) 당진화력S/S 154kV 석문-당진화력#1T/L 617CB 보통점검","2024-04-22 09:00","2024-04-23 18:00","취소","취소","매일"]
[372,"대전세종충남","서산","대산석문#2 T/L","24년 서산P/O 변전협력회사 총액공사","(3월 휴전 취소시) 대산S/S 154kV 대산-석문#2T/L CB 조작시험, 전자변, 에어링밸브 교체, CVT 대체 (병행) 석문S/S 154kV 대산-석문#2T/L IED 성능개선","2024-04-26 09:30","2024-04-26 18:00","취소","취소","연속"]
[373,"대전세종충남","서산","서산대산#4 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","154kV 서산-대산#4T/L 수평 추락방지 설치공사 (No.1~76 등 76기)","2024-04-09 08:00","2024-04-18 18:00","2024-04-09 08:00","2024-04-18 18:00","매일"]
[374,"대전세종충남","서산","대산대산복합#2 T/L","대산S/S 154kV 차단기 조작시험","대산S/S 6B7 CB","2024-04-17 09:00","2024-04-17 14:00","취소","취소","연속"]
[375,"대전세종충남","서산","대산석문#1 T/L","24년 서산P/O 변전협력회사 총액공사","(3월 휴전 취소시) 대산S/S 154kV 대산-석문#!T/L CVT 대체","2024-04-19 09:30","2024-04-19 18:00","취소","취소","연속"]
[376,"대전세종충남","서산","신당진당진#1 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","154kV 신당진-당진#1T/L 수평 추락방지 설치공사 (No.1~5, 14~35 등 27기)","2024-04-19 08:00","2024-04-23 18:00","2024-04-19 08:00","2024-04-23 18:00","매일"]
[377,"대전세종충남","서산","신당진서산#2 T/L","'24년 서산P/O 변전협력회사 총액공사","신당진S/S 154kV 신당진-서산#2T/L 667 GIS 보통점검 (병행) 신당진S/S 154kV 신당진-서산#2T/L CVT 대체 (병행) 서산S/S 154kV 신당진-서산#2T/L 637 GIS 보통점검 (병행) 서산S/S 154kV 신당진-서산#2T/L LA 보통점검","2024-04-04 09:00","2024-04-04 18:00","2024-04-04 09:00","2024-04-04 18:00","연속"]
[378,"대전세종충남","서산","신당진서산#1 T/L","'24~'25년도 송전협력회사 공사","(송전)154kV 신당진-서산#1T/L 점퍼지지애자 교체공사 No.60 (변전병행) 154kV 신당진-서산#1T/L 657GIS 보통점검 154kV 신당진-서산#1T/L LA 보통점검","2024-04-05 08:00","2024-04-05 18:00","2024-04-05 08:00","2024-04-05 18:00","매일"]
[379,"대전세종충남","서산","신당진당진#2 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","154kV 신당진-당진#2T/L 수평 추락방지 설치공사 (No.1~5, 14~35 등 27기)","2024-04-24 08:00","2024-04-26 18:00","2024-04-24 08:00","2024-04-26 18:00","매일"]
[380,"대전세종충남","서산","서산태안#2 T/L","태안S/S 154kV 모선구분차단기 설치공사(안전이격)","안전이격 확보 휴전","2024-04-29 07:00","2024-05-01 20:00","취소","취소","매일"]
[381,"대전세종충남","서산","태안태안화력#2 T/L","태안S/S 154kV 모선구분차단기 설치공사","종카바 무부하가압","2024-04-30 08:00","2024-04-30 09:00","2024-04-30 08:00","2024-04-30 09:00","연속"]
[382,"대전세종충남","서산","태안태안화력#2 T/L","154kV 태안-태안화력T/L 전력선 교체공사","154kV 태안-태안화력#2T/L 전력선 교체공사 (No.2~6, 6~8, 11~13 등 3개소)","2024-04-22 08:00","2024-04-26 18:00","2024-04-22 08:00","2024-04-26 18:00","연속"]
[383,"대전세종충남","서산","태안T/P #1 BUS","태안화력S/Y 154kV CVT GIS 내장화 공사","(즉시가압 가능) 태안화력S/Y 154kV 태안-태안화력#1T/L GIS 무부하가압","2024-04-19 09:00","2024-04-19 18:00","2024-04-19 09:00","2024-04-19 18:00","연속"]
[384,"대전세종충남","서산","태안T/P CB 6100","태안화력S/Y 154kV CVT GIS 내장화 공사","(즉시가압 가능) 태안화력S/Y 154kV 태안-태안화력#1T/L GIS 무부하가압","2024-04-19 09:00","2024-04-19 18:00","2024-04-19 09:00","2024-04-19 18:00","연속"]
[385,"대전세종충남","서산","태안T/P #1 BUS","태안화력S/Y 154kV CVT GIS 내장화 공사","(즉시가압 가능) 태안화력S/Y 154kV 태안-태안화력#2T/L GIS 무부하가압","2024-04-26 09:00","2024-04-26 18:00","2024-04-26 09:00","2024-04-26 18:00","연속"]
[386,"대전세종충남","서산","태안T/P CB 6100","태안화력S/Y 154kV CVT GIS 내장화 공사","(즉시가압 가능) 태안화력S/Y 154kV 태안-태안화력#2T/L GIS 무부하가압","2024-04-26 09:00","2024-04-26 18:00","2024-04-26 09:00","2024-04-26 18:00","연속"]
[387,"대전세종충남","서산","태안태안화력#1 T/L","154kV 태안-태안화력T/L 전력선 교체공사","154kV 태안-태안화력#1T/L 전력선 교체공사 (No.2~6, 11~13 등 2개소)","2024-04-15 08:00","2024-04-19 18:00","2024-04-15 08:00","2024-04-19 18:00","연속"]
[388,"대전세종충남","서산","합덕송악#2 T/L","'24~'25년도 송전협력회사 공사","154kV 합덕-송악#2T/L 점퍼지지애자 교체공사 No.54,51","2024-04-24 08:00","2024-04-25 18:00","2024-04-24 08:00","2024-04-25 18:00","매일"]
[389,"대전세종충남","서산","합덕송악#1 T/L","'24~'25년도 송전협력회사 공사","154kV 합덕-송악#1T/L 점퍼지지애자 교체공사 No.52,54,58,59","2024-04-22 08:00","2024-04-23 18:00","2024-04-22 08:00","2024-04-23 18:00","매일"]
[390,"대전세종충남","서산","해미홍성 T/L","'23년 서산P/O 장기사용 배전반 교체공사","(3월 휴전 취소시) 해미, 홍성S/S 154kV 해미-홍성T/L 보호반 대체공사","2024-04-01 09:00","2024-04-03 18:00","취소","취소","연속"]
[391,"대전세종충남","서산","서산해미 T/L","'23년 서산P/O 장기사용 배전반 교체공사","서산, 해미S/S 154kV 서산-해미T/L 보호반 대체공사","2024-04-15 09:00","2024-04-17 18:00","취소","취소","연속"]
[392,"대전세종충남","세종","덕진공주#2 T/L","[송전]154kV 덕진-공주#2T/L 압축인류크램프 교체공사","[송전]154kV 덕진-공주#2T/L 압축인류크램프 교체공사 - No.75,79 (2기)","2024-04-15 07:00","2024-04-15 18:00","2024-04-15 07:00","2024-04-15 18:00","연속"]
[393,"대전세종충남","세종","덕진공주#1 T/L","[송전]154kV 덕진-공주#1T/L 압축인류크램프 교체공사","[송전]154kV 덕진-공주#1T/L 압축인류크램프 교체공사 - No.35,43,72,79 (4기)","2024-04-12 07:00","2024-04-12 18:00","2024-04-12 07:00","2024-04-12 18:00","연속"]
[394,"대전세종충남","세종","서세종S/S CB 6100","[변전]'24년 세종전력지사 변전협력회사 총액공사","○ 154kV GIS 보통점검","2024-04-01 10:00","2024-04-01 18:00","2024-04-01 10:00","2024-04-01 18:00","연속"]
[395,"대전세종충남","세종","세종둔곡#1 T/L","[송전]154kV 세종-둔곡#1T/L 추락방지장치 설치공사","[송전]154kV 세종-둔곡#1T/L 추락방지장치 설치공사 - No.2~14 (13기)","2024-04-25 07:00","2024-05-01 18:00","2024-04-25 07:00","2024-05-01 18:00","매일"]
[396,"대전세종충남","세종","조치원월산 T/L","[송전]154kV 조치원-월산T/L 추락방지장치 설치공사","[송전]154kV 조치원-월산T/L 추락방지장치 설치공사 - No.20~35 (16기)","2024-04-16 07:00","2024-04-22 18:00","2024-04-16 07:00","2024-04-22 18:00","매일"]
[397,"대전세종충남","세종","서세종조치원 T/L","[송전]154kV 조치원-월산T/L 추락방지장치 설치공사","[송전]154kV 조치원-월산T/L 추락방지장치 설치공사 - No.20~35 (16기)","2024-04-23 07:00","2024-04-24 18:00","2024-04-23 07:00","2024-04-24 18:00","매일"]
[398,"대전세종충남","직할","대화둔산#2 T/L","세니온제 보호계전기 성능개선 공사","세니온제 보호계전기 성능개선 공사 ㅁ 대상 : 동대전-대화#1, 동대전-대화#2, 대화-둔산#2, 둔곡-송강#1T/L","2024-04-17 09:00","2024-04-17 18:00","2024-04-17 09:00","2024-04-17 18:00","연속"]
[399,"대전세종충남","직할","둔곡송강#1 T/L","세니온제 보호계전기 성능개선 공사","세니온제 보호계전기 성능개선 공사 ㅁ 대상 : 동대전-대화#1, 동대전-대화#2, 대화-둔산#2, 둔곡-송강#1T/L","2024-04-20 09:00","2024-04-20 18:00","취소","취소","연속"]
[400,"대전세종충남","직할","둔곡송강#1 T/L","[송전] 154kV 둔곡-송강T/L 추락방지시설 설치공사","[송전] 154kV 둔곡-송강#1T/L 추락방지시설 및 피뢰기 설치공사","2024-04-29 07:00","2024-05-01 18:00","취소","취소","매일"]
[401,"대전세종충남","천안","아산인주#2 T/L","154kV 아산-인주T/L 추락방지장치 설치공사","[평일휴전불가시 주말휴전시행]154kV 아산-인주T/L No. 1 ~ 25 추락방지장치 설치","2024-04-28 07:00","2024-04-30 17:00","취소","취소","매일"]
[402,"대전세종충남","천안","아산인주#1 T/L","(3월취소시)아산,인주S/S 아산-인주#1T/L 보호반 교체","(3월취소시)아산,인주S/S 아산-인주#1T/L 보호반 교체","2024-04-01 09:00","2024-04-04 18:00","취소","취소","연속"]
[403,"대전세종충남","천안","아산인주#1 T/L","154kV 아산-인주T/L 추락방지장치 설치공사","[평일휴전불가시 주말휴전시행]154kV 아산-인주T/L No. 1 ~ 25 추락방지장치 설치","2024-04-25 07:00","2024-04-27 17:00","취소","취소","매일"]
[404,"대전세종충남","천안","아산인주#2 T/L","(3월취소시)아산,인주S/S 아산-인주#2T/L 보호반 교체","(3월취소시)아산,인주S/S 아산-인주#2T/L 보호반 교체","2024-04-08 09:00","2024-04-11 18:00","취소","취소","연속"]
[405,"대전세종충남","천안","인주불당#1 T/L","154kV 인주-불당T/L 추락방지장치 설치공사","[평일휴전불가시 주말시행]154kV 인주-불당T/L No. 45 ~ 63 추락방지장치 설치","2024-04-13 07:00","2024-04-17 18:00","2024-04-13 07:00","2024-04-17 18:00","매일"]
[406,"대전세종충남","천안","인주불당#2 T/L","154kV 인주-불당T/L 추락방지장치 설치공사","[평일휴전불가시 주말시행]154kV 인주-불당T/L No. 45 ~ 63 추락방지장치 설치","2024-04-18 07:00","2024-04-22 18:00","2024-04-18 07:00","2024-04-22 18:00","매일"]
[407,"대전세종충남","천안","장재천안#2 T/L","장재,천안S/S 154kV 장재-천안#2T/L 보호배전반 대체","장재,천안S/S 154kV 장재-천안#2T/L 보호배전반 대체","2024-04-22 09:00","2024-04-25 18:00","취소","취소","연속"]
[408,"대전세종충남","천안","장재천안#1 T/L","장재,천안S/S 154kV 장재-천안#1T/L 보호배전반 대체","장재,천안S/S 154kV 장재-천안#1T/L 보호배전반 대체","2024-04-15 09:00","2024-04-18 18:00","취소","취소","연속"]
[409,"대전세종충남","천안","천안전의#1 T/L","154kV 소정분기T/L 건설공사","○ 154kV 소정S/S ~ 154kV 천안-전의T/L 4회선 분기선로 구성 -154kV 소정분기T/L No.1, 2 철탑 신설 및 선로 가선 -154kV 천안-전의T/L No.29, 31, 32 철탑보강","2024-04-15 07:00","2024-04-22 18:00","취소","취소","매일"]
[410,"대전세종충남","천안","풍세장재#2 T/L","풍세,장재S/S 154kV 풍세-장재#2T/L 보호반 성능개선","풍세,장재S/S 154kV 풍세-장재#2T/L 보호반 성능개선","2024-04-30 09:00","2024-04-30 18:00","취소","취소","연속"]
[411,"대전세종충남","천안","풍세장재#1 T/L","풍세,장재S/S 154kV 풍세-장재#1T/L 보호반 성능개선","풍세,장재S/S 154kV 풍세-장재#1T/L 보호반 성능개선","2024-04-29 09:00","2024-04-29 18:00","취소","취소","연속"]
[412,"대전세종충남","천안","한샘직산#1 T/L","154kV 한샘-직산T/L 추락방지장치 설치공사","154kV 한샘-직산T/L No. 7 ~ 8 추락방지장치 설치","2024-04-23 07:00","2024-04-23 12:00","2024-04-23 07:00","2024-04-23 12:00","연속"]
[413,"대전세종충남","천안","한샘직산#2 T/L","154kV 한샘-직산T/L 추락방지장치 설치공사","154kV 한샘-직산T/L No. 7 ~ 8 추락방지장치 설치","2024-04-23 13:00","2024-04-23 17:00","2024-04-23 13:00","2024-04-23 17:00","연속"]
[414,"대전세종충남","청양","청양관창#1 T/L","청양P/O 변전협력회사 총액공사","관창S/S 청양-관창#1 T/L GIS 보통점검 추가공사","2024-04-24 09:00","2024-04-24 18:00","2024-04-24 09:00","2024-04-24 18:00","연속"]
[415,"대전세종충남","청양","관창보령CC T/L","(송전취소시)154kV 관창-보령복합T/L GIS 정밀점검","(송전취소시)154kV 관창-보령복합T/L GIS 정밀점검","2024-04-17 09:00","2024-04-19 18:00","취소","취소","연속"]
[416,"대전세종충남","청양","관창보령CC T/L","[송전] 154kV 보관T/L 수평 추락방지장치 설치공사","154kV 보관T/L 수평 추락방지장치 설치공사 (39기)","2024-04-05 07:00","2024-04-11 18:00","2024-04-05 07:00","2024-04-11 18:00","매일"]
[417,"대전세종충남","청양","관창보령TP T/L","154kV 관창-보령화력T/L 보호배전반 대체공사","154kV 관창-보령화력T/L 보호배전반 대체공사","2024-04-01 09:00","2024-04-04 18:00","2024-04-01 09:00","2024-04-04 18:00","연속"]
[418,"대전세종충남","청양","관창보령TP T/L","(변전취소시) 154kV 보관T/L 수평 추락방지장치 설치공사","(변전취소시)154kV 보관T/L 수평 추락방지장치 설치공사 (39기)","2024-04-01 07:00","2024-04-04 18:00","취소","취소","매일"]
[419,"대전세종충남","청양","신서천대천#2 T/L","154kV 관창-대천 등 2개T/L 지장송전선로 이설공사(1차)","□ 공 사 명 : 154㎸ 관창-대천 등 2개T/L 지장송전선로 이설공사 □ 공사목적 : 보령시 스포츠파크 조성관련 송전선로 이설 요구(보령시) □ 사업개요 ○ 공사구간 : 154kV 관창-대천(상단), 대천-서천T/L(하단) No.1~5 ○ 지 지 물 : 철탑 4기 설치, 2기 철거, 임시 2기 ○ 전 력 선 : ACSR 410","2024-04-24 07:00","2024-05-01 18:00","2024-04-24 07:00","2024-05-01 18:00","연속"]
[420,"대전세종충남","청양","관창대천#1 T/L","청양P/O 변전협력회사 총액공사","대천S/S 관창-대천#1 T/L GIS 하자점검","2024-04-30 09:00","2024-04-30 18:00","취소","취소","연속"]
[421,"대전세종충남","청양","관창대천#1 T/L","154kV 관창-대천 등 2개T/L 지장송전선로 이설공사(1차)","□ 공 사 명 : 154㎸ 관창-대천 등 2개T/L 지장송전선로 이설공사 □ 공사목적 : 보령시 스포츠파크 조성관련 송전선로 이설 요구(보령시) □ 사업개요 ○ 공사구간 : 154kV 관창-대천(상단), 대천-서천T/L(하단) No.1~5 ○ 지 지 물 : 철탑 4기 설치, 2기 철거, 임시 2기 ○ 전 력 선 : ACSR 410","2024-04-24 07:00","2024-05-01 18:00","2024-04-24 07:00","2024-05-01 18:00","연속"]
[422,"대전세종충남","청양","보령C/C #3ST 주변압기 CB","청양P/O 변전협력회사 총액공사","보령C/C 154kV #3 ST.Tr 1차 CB 보통점검 추가공사","2024-04-19 09:00","2024-04-19 18:00","2024-04-19 09:00","2024-04-19 18:00","연속"]
[423,"대전세종충남","청양","보령TP보령CC T/L","[송전] 154kV 보관T/L 수평 추락방지장치 설치공사","154kV 보관T/L 수평 추락방지장치 설치공사 (39기)","2024-04-11 07:00","2024-04-11 18:00","2024-04-11 07:00","2024-04-11 18:00","매일"]
[424,"대전세종충남","청양","보령C/C #5GT 주변압기 CB","청양P/O 변전협력회사 총액공사","보령C/C 154kV #5 GT.Tr 1차 CB 보통점검 추가공사","2024-04-17 09:00","2024-04-17 18:00","2024-04-17 09:00","2024-04-17 18:00","연속"]
[425,"대전세종충남","청양","보령C/C #6GT 주변압기 CB","청양P/O 변전협력회사 총액공사","보령C/C 154kV #6 GT.Tr 1차 CB 보통점검 추가공사","2024-04-18 09:00","2024-04-18 18:00","2024-04-18 09:00","2024-04-18 18:00","연속"]
[426,"대전세종충남","청양","신서천옥산#2 T/L","170kV GIS 정밀점검 발주공사","옥산S/S 옥산-서천#2 T/L 정밀점검","2024-04-21 09:00","2024-04-23 18:00","2024-04-21 09:00","2024-04-23 18:00","연속"]
[427,"대전세종충남","청양","옥산장항#2 T/L","170kV GIS 정밀점검 발주공사","옥산S/S 옥산-장항#2 T/L 정밀점검","2024-04-25 09:00","2024-04-27 18:00","2024-04-25 09:00","2024-04-27 18:00","연속"]
[428,"대전세종충남","청양","옥산장항#1 T/L","170kV GIS 정밀점검 발주공사","옥산S/S 옥산-장항#1 T/L 정밀점검","2024-04-29 09:00","2024-05-01 18:00","취소","취소","연속"]
[429,"대전세종충남","청양","은하홍성#1 T/L","(3월취소시)청양P/O 변전협력회사 총액공사","(3월취소시)154kV 은하-홍성#1T/L 보호반 대체공사","2024-04-16 09:00","2024-04-18 18:00","2024-04-16 09:00","2024-04-18 18:00","연속"]
[430,"대전세종충남","청양","동군산장항#1 T/L","청양P/O 변전협력회사 총액공사","장항S/S 동군산-장항#1 T/L 보호배전반 대체공사","2024-04-29 09:00","2024-05-02 18:00","취소","취소","연속"]
[431,"대전세종충남","청양","동군산장항#2 T/L","청양P/O 변전협력회사 총액공사","장항S/S 동군산-장항#2 T/L GIS 보통점검 추가공사","2024-04-25 09:00","2024-04-25 18:00","취소","취소","연속"]
[432,"대전세종충남","청양","청양관창#1 T/L","[송전]154kV 청양-관창T/L 지장이설공사","○ 공사구간 : 154kV 청양-관창T/L No.3~8 ○ 지지물 : 신설 1기 설치, 임시 2기 설치/철거, 기설 1기 철거 ○ 전력선 : ACSR 410 x 2B x 2C, 1.473km(전선교체)","2024-04-24 07:00","2024-04-28 18:00","2024-04-24 07:00","2024-04-28 18:00","연속"]
[433,"대전세종충남","청양","청양관창#2 T/L","[송전]154kV 청양-관창T/L 지장이설공사","○ 공사구간 : 154kV 청양-관창T/L No.3~8 ○ 지지물 : 신설 1기 설치, 임시 2기 설치/철거, 기설 1기 철거 ○ 전력선 : ACSR 410 x 2B x 2C, 1.473km(전선교체)","2024-04-29 07:00","2024-05-03 18:00","2024-04-29 07:00","2024-05-03 18:00","연속"]
[434,"전북","군산","비응군장#2 T/L","154kV 비응S/S #4M.Tr 개폐장치 설치공사 (170kV GIS)","170kV GIS x 1CCT (6433)","2024-04-26 15:00","2024-04-27 15:00","2024-04-26 15:00","2024-04-27 15:00","연속"]
[435,"전북","군산","영등팔봉#2 T/L","154kV 영등-팔봉T/L 지장철탑 이설공사","154kV 영등-팔봉T/L 지장철탑 이설공사 ○ 대 상 : 154kV 영등-팔봉T/L No.1~5 ○ 내 용 : No.1~5 철탑 철거, No.5 (C/T)설치","2024-04-25 07:00","2024-04-27 18:00","취소","취소","연속"]
[436,"전북","군산","영등팔봉#1 T/L","154kV 영등-팔봉T/L 지장철탑 이설공사","154kV 영등-팔봉T/L 지장철탑 이설공사 ○ 대 상 : 154kV 영등-팔봉T/L No.1~5 ○ 내 용 : No.1~5 철탑 철거, No.5 (C/T)설치","2024-04-22 07:00","2024-04-24 18:00","취소","취소","연속"]
[437,"전북","군산","왕궁봉동#1 T/L","군산P/O 154kV이상 차단기 점검공사","군산P/O 154kV이상 차단기 점검공사","2024-04-02 09:00","2024-04-02 18:00","2024-04-02 09:00","2024-04-02 18:00","연속"]
[438,"전북","군산","왕궁봉동#2 T/L","군산P/O 154kV이상 차단기 점검공사","군산P/O 154kV이상 차단기 점검공사","2024-04-03 09:00","2024-04-03 18:00","2024-04-03 09:00","2024-04-03 18:00","연속"]
[439,"전북","군산","이리백산#2 T/L","154kV 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2024-04-28 08:00","2024-05-02 18:00","취소","취소","연속"]
[440,"전북","군산","이리백산#2 T/L","154kV 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2024-04-15 08:00","2024-04-19 18:00","취소","취소","연속"]
[441,"전북","군산","이리백산#1 T/L","154kV 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2024-04-20 08:00","2024-04-27 18:00","취소","취소","연속"]
[442,"전북","군산","팔봉왕궁#1 T/L","전북본부 관내 EBA 자기애관 교체공사","기설 EBA 자기애관 철거 및 폴리머애관 설치","2024-04-08 09:00","2024-04-12 18:00","취소","취소","연속"]
[443,"전북","군산","팔봉왕궁#2 T/L","전북본부 관내 EBA 자기애관 교체공사","기설 EBA 자기애관 철거 및 폴리머애관 설치","2024-04-15 09:00","2024-04-19 18:00","취소","취소","연속"]
[444,"전북","김제","고창홍농 T/L","154kV 고창-영광T/L No.45~142 선종교체공사","154kV 고창-영광T/L No.45~142 선종교체공사 - 전력선 교체 32.185km (ASCR330 →ASCCT/W430) - 新전선용 금구류 교체 (압축인류클램프, 현수클램프 등)","2024-04-22 07:30","2024-06-07 18:00","2024-05-13 08:00","2024-06-01 17:00","연속"]
[445,"전북","김제","백산김제#1 T/L","154kV 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2024-04-28 08:00","2024-05-02 18:00","취소","취소","연속"]
[446,"전북","김제","백산김제#1 T/L","154kV 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2024-04-15 08:00","2024-04-19 18:00","취소","취소","연속"]
[447,"전북","김제","백산김제#2 T/L","154kV 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2024-04-20 08:00","2024-04-27 18:00","취소","취소","연속"]
[448,"전북","직할","남원임실#1 T/L","154kV 남원-임실T/L 추락방지시설 관련 하자처리공사","154kV 남원-임실#1T/L 71호 가공암 수평 추락방지시설 보수","2024-04-29 09:00","2024-04-29 18:00","2024-04-29 09:00","2024-04-29 18:00","연속"]
[449,"전북","직할","신김제동전주#1 T/L","154kV 차단기 보통점검(즉시가압 가능)","154kV 차단기 보통점검(즉시가압 가능)","2024-04-02 14:00","2024-04-02 20:00","2024-04-02 14:00","2024-04-02 20:00","연속"]
[450,"전북","직할","신김제동전주#2 T/L","154kV 차단기 보통점검(즉시가압 가능)","154kV 차단기 보통점검(즉시가압 가능)","2024-04-03 14:00","2024-04-03 20:00","2024-04-03 14:00","2024-04-03 20:00","연속"]
[451,"전북","직할","북전주봉동#1 T/L","154kV 차단기 조작시험 (즉시가압 가능)","154kV 차단기 조작시험 (즉시가압 가능)","2024-04-18 09:00","2024-04-18 18:00","2024-04-18 09:00","2024-04-18 18:00","연속"]
[452,"전북","직할","탄소이리#1 T/L","154kV 차단기 보통점검(즉시가압 가능)","154kV 차단기 보통점검(즉시가압 가능)","2024-04-04 09:00","2024-04-04 18:00","2024-04-04 09:00","2024-04-04 18:00","연속"]
[453,"전북","직할","탄소이리#2 T/L","154kV 차단기 보통점검(즉시가압 가능)","154kV 차단기 보통점검(즉시가압 가능)","2024-04-16 09:00","2024-04-16 18:00","2024-04-16 09:00","2024-04-16 18:00","연속"]
[454,"광주전남","강진","신강진대불#2 T/L","2024년 가공송전 순시점검 위탁공사","신강진해남#1T/L 정밀점검 4회선 구간 휴전","2024-04-01 09:00","2024-04-02 18:00","2024-04-22 09:00","2024-04-23 18:00","매일"]
[455,"광주전남","강진","신강진대불#1 T/L","2024년 가공송전 순시점검 위탁공사","신강진해남#2T/L 정밀점검 4회선 구간 휴전","2024-04-11 09:00","2024-04-12 18:00","2024-04-11 09:00","2024-04-12 18:00","매일"]
[456,"광주전남","강진","해남진도#2 T/L","22~23년 철탑추락방지장치 설치공사","22~23년 철탑 추락방지장치 설치공사(수평) - 공사대상 : 154kV 해남-진도#2T/L 75~86,96~101,105~110호(24기) ,해남-해남CS#1T/L 병가 구간 2~3호(2기)","2024-04-22 07:00","2024-04-24 18:00","2024-04-22 07:00","2024-04-24 18:00","매일"]
[457,"광주전남","강진","화원진도#2 T/L","22~23년 철탑추락방지장치 설치공사","22~23년 철탑 추락방지장치 설치공사 - 공사대상 : 154kV 화원-진도#2T/L 40~78호 (39기)","2024-04-02 07:00","2024-04-04 18:00","2024-04-02 07:00","2024-04-04 18:00","매일"]
[458,"광주전남","강진","화원진도#1 T/L","22~23년 철탑추락방지장치 설치공사","22~23년 철탑 추락방지장치 설치공사 - 공사대상 : 154kV 화원-진도#1T/L 40~60,62,68호 (23기)","2024-04-08 07:00","2024-04-09 18:00","2024-04-08 07:00","2024-04-09 18:00","매일"]
[459,"광주전남","강진","해남해남CS#2 T/L","2024~2025년 강진전력지사 송전협력회사 공사","해남-해남CS#2T/L 수평추락방지장치 설치공사 1~81호","2024-04-01 07:00","2024-04-09 18:00","2024-04-01 07:00","2024-04-09 18:00","매일"]
[460,"광주전남","강진","남창해남CS#1 T/L","2024~2025년 강진전력지사 송전협력회사 공사","남창-해남CS#1T/L 수평추락방지장치 설치공사(4회선구간)","2024-04-25 07:00","2024-04-26 18:00","2024-04-25 07:00","2024-04-26 18:00","매일"]
[461,"광주전남","강진","해남해남CS#1 T/L","2024~2025년 강진전력지사 송전협력회사 공사","해남-해남CS#1T/L 수평추락방지장치 설치공사 1~81호","2024-04-22 07:00","2024-04-29 18:00","2024-04-22 07:00","2024-04-29 18:00","매일"]
[462,"광주전남","강진","남창해남CS#2 T/L","2024~2025년 강진전력지사 송전협력회사 공사","남창-해남CS#2T/L 수평추락방지장치 설치공사(4회선구간)","2024-04-01 07:00","2024-04-02 18:00","2024-04-01 07:00","2024-04-02 18:00","매일"]
[463,"광주전남","광주","남광주금천#2 T/L","대한전선製 EBG 가스채취밸브 보강공사","송운(송전)-321(2021.03.30) 지중송전선로 EBG 고장원인 조사결과 및 재발방지대책 알림 관련으로 대한전선제 EBG 보강 시행","2024-04-22 09:00","2024-04-23 18:00","취소","취소","연속"]
[464,"광주전남","광주","남광주금천#1 T/L","대한전선製 EBG 가스채취밸브 보강공사","송운(송전)-321(2021.03.30) 지중송전선로 EBG 고장원인 조사결과 및 재발방지대책 알림 관련으로 대한전선제 EBG 보강 시행","2024-04-24 09:00","2024-04-25 18:00","취소","취소","연속"]
[465,"광주전남","광주","담양일곡#1 T/L","대한전선製 EBG 가스채취밸브 보강공사","송운(송전)-321(2021.03.30) 지중송전선로 EBG 고장원인 조사결과 및 재발방지대책 알림 관련으로 대한전선제 EBG 보강 시행","2024-04-11 09:00","2024-04-12 18:00","취소","취소","연속"]
[466,"광주전남","광주","담양일곡#2 T/L","대한전선製 EBG 가스채취밸브 보강공사","송운(송전)-321(2021.03.30) 지중송전선로 EBG 고장원인 조사결과 및 재발방지대책 알림 관련으로 대한전선제 EBG 보강 시행","2024-04-08 09:00","2024-04-09 18:00","취소","취소","연속"]
[467,"광주전남","광주","신광주계림#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","신광주, 계림S/S 신광주-계림#2T/L PNL 대체","2024-04-22 09:00","2024-04-26 18:00","2024-04-01 09:00","2024-04-05 18:00","연속"]
[468,"광주전남","광주","신광주일곡#1 T/L","신광주-일곡#1T/L #3ES 제작사 점검(LS)","신광주-일곡#1T/L 선로 ES 불량조치(제작사)","2024-04-20 09:00","2024-04-20 18:00","2024-04-20 09:00","2024-04-20 18:00","연속"]
[469,"광주전남","광주","신화순매월#2 T/L","효천지구 하자케이블 교체공사(요청자 직접 시행)","○ 구간 : 광주효천1 154kV 신화순-매월T/L No.69 ~ 69-1 ○ 회선수 및 길이 : 1상, 약 218m ○ 작업 내역 : 케이블 철거 및 포설, 접속, 기타 작업 및 현장시험(내전압) ○ 시행자 : 한국토지주택공사 광주전남지역본부","2024-04-15 09:00","2024-04-30 18:00","2024-04-15 09:00","2024-04-30 18:00","연속"]
[470,"광주전남","목포","엄다목포#1 T/L","대한전선製 EBG 가스채취밸브 보강공사","송운(송전)-321(2021.03.30) 지중송전선로 EBG 고장원인 조사결과 및 재발방지대책 알림 관련으로 대한전선제 EBG 보강 시행","2024-04-03 09:00","2024-04-04 18:00","취소","취소","연속"]
[471,"광주전남","목포","장성영광#1 T/L","154kV 영광-홍농 등 4개T/L 선종교체공사","1. 공사명 : 154kV 영광-홍농 등 4개T/L 선종교체공사 2. 공사내용 ○ 내용 : 고창-홍농(홍농분기) 선종교체공사를 위한 안전휴전 ○ 구간 : 고창-홍농T/L No.45 ~홍농S/S ※ 안전휴전 구간 : 장성-영광 No.126 4회선(상단) 분기철탑","2024-04-22 07:00","2024-05-02 18:00","취소","취소","연속"]
[472,"광주전남","순천","광양하동#2 T/L","고객 측 휴전 요청","작업구간(광양제철) 안전확보 광양제철소 공사감독자 진선화(010-3520-5031)","2024-04-24 07:00","2024-04-26 18:00","2024-04-24 07:00","2024-04-26 18:00","연속"]
[473,"광주전남","순천","광양태금#1 T/L","고객 측 휴전 요청","작업구간(광양제철) 안전확보 광양제철소 공사감독자 진선화(010-3520-5031)","2024-04-09 07:00","2024-04-12 18:00","2024-04-09 07:00","2024-04-12 18:00","연속"]
[474,"광주전남","순천","광양하동#1 T/L","고객 측 휴전 요청","작업구간(광양제철) 안전확보 광양제철소 공사감독자 진선화(010-3520-5031)","2024-04-03 07:00","2024-04-05 18:00","2024-04-03 07:00","2024-04-05 18:00","연속"]
[475,"광주전남","순천","광양태금#2 T/L","고객 측 휴전 요청","작업구간(광양제철) 안전확보 광양제철소 공사감독자 진선화(010-3520-5031)","2024-04-30 07:00","2024-05-02 18:00","2024-04-30 07:00","2024-05-02 18:00","연속"]
[476,"광주전남","순천","백운세풍#1 T/L","154kV 광양항-세풍 지중T/L 건설공사","중간접속함 교체(154kV 백운-세풍#1T/L 2B A상, B상, M/H#22)","2024-04-03 09:00","2024-04-29 18:00","취소","취소","연속"]
[477,"광주전남","순천","계림승주#1 T/L","24-25년 순천전력지사 변전협력회사 공사","승주S/S 계림-승주#1T/L PNL 통신방식 변경작업(즉시가압 가능)","2024-04-16 09:00","2024-04-17 18:00","2024-04-16 09:00","2024-04-17 18:00","연속"]
[478,"광주전남","순천","용성여수산단#2 T/L","여수산단개폐소 용성-여수산단#2T/L #1DS 가스누기 해소공사","#1DS 가스누기 해소공사","2024-04-24 09:00","2024-04-25 18:00","취소","취소","연속"]
[479,"광주전남","순천","여수TP화치#1 T/L","24-25년 순천전력지사 변전협력회사 공사","여수화력,화치S/S 여수TP화치#1 T/L PNL 대체(즉시가압불가)","2024-04-15 09:00","2024-04-19 18:00","2024-04-15 09:00","2024-04-19 18:00","연속"]
[480,"광주전남","순천","호남TP여수TP#1 T/L","154kV 호남TP-여수TPT/L 추락방지시설 설치공사","수평 추락방지시설 설치 - No.3~13호, 12기","2024-04-26 07:00","2024-04-26 18:00","2024-04-26 07:00","2024-04-26 18:00","연속"]
[481,"광주전남","순천","여수T/P #65 BUS","GS 칼텍스 여수#2T/L #2DS 가스누기해소 공사","#2DS 가스누기해소 공사","2024-04-22 09:00","2024-04-23 18:00","취소","취소","연속"]
[482,"광주전남","순천","여수T/P CB 6200","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-04-19 15:40","2024-04-19 16:00","취소","취소","연속"]
[483,"광주전남","순천","여수T/P SEC CB 60610","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-04-19 15:20","2024-04-19 15:40","취소","취소","연속"]
[484,"광주전남","순천","호남TP여수TP#2 T/L","154kV 호남TP-여수TPT/L 추락방지시설 설치공사","수평 추락방지시설 설치 - No.3~13호, 12기","2024-04-29 07:00","2024-04-29 18:00","2024-04-29 07:00","2024-04-29 18:00","연속"]
[485,"광주전남","순천","여수T/P CB 6100","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-04-12 15:40","2024-04-12 16:00","취소","취소","연속"]
[486,"광주전남","순천","여수T/P SEC CB 60610","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-04-12 15:20","2024-04-12 15:40","취소","취소","연속"]
[487,"광주전남","순천","여수T/P SEC CB 65660","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-04-12 15:00","2024-04-12 15:20","취소","취소","연속"]
[488,"광주전남","순천","여수T/P SEC CB 65660","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-04-19 15:00","2024-04-19 15:20","취소","취소","연속"]
[489,"광주전남","순천","여수TP여천#1 T/L","여천S/S 한화CA5 T/L 인출변경 및 안전이격 휴전","여천S/S 한화CA5 T/L 인출변경 및 안전이격 휴전","2024-04-24 09:00","2024-04-25 18:00","2024-04-24 09:00","2024-04-25 18:00","매일"]
[490,"광주전남","순천","여수TP용성#1 T/L","용성S/S 여수TP-용성#1T/L GIS 불량 유압력계 교체","GIS 불량 유압력계 교체","2024-04-04 09:00","2024-04-05 18:00","취소","취소","연속"]
[491,"광주전남","순천","율촌여수산단#1 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - No.2~27호, 26기","2024-04-18 07:00","2024-04-22 18:00","취소","취소","매일"]
[492,"광주전남","순천","율촌여수산단#2 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - No.2~27호, 26기","2024-04-23 07:00","2024-04-25 18:00","취소","취소","매일"]
[493,"광주전남","순천","태금하동화력 T/L","24-25년 순천전력지사 변전협력회사 공사","태금-하동T/P T/L GIS 하자점검","2024-04-01 09:00","2024-04-01 18:00","2024-04-01 09:00","2024-04-01 18:00","연속"]
[494,"광주전남","직할","나주금천#1 T/L","22~23년 철탑추락방지장치 설치공사","22~23년 철탑 추락방지장치 설치공사 - 공사대상 : 154kV 나주-영암#2T/L, 나주-금천#1 병가구간 2,3,9,10호 (4기)","2024-04-11 07:00","2024-04-11 18:00","2024-04-11 07:00","2024-04-11 18:00","매일"]
[495,"광주전남","직할","나주금천#2 T/L","22~23년 철탑추락방지장치 설치공사","22~23년 철탑 추락방지장치 설치공사(수평) - 공사대상 : 154kV 나주-영암#1T/L ,나주-금천#2T/L 병가 구간 2,3,9,10호(4기)","2024-04-17 07:00","2024-04-17 18:00","2024-04-17 07:00","2024-04-17 18:00","매일"]
[496,"광주전남","직할","농성화정#1 T/L","2024~2025년 직할 변전협력회사 공사","170kV 차단기 조작시험 등","2024-04-17 09:00","2024-04-17 14:00","2024-04-17 09:00","2024-04-17 14:00","연속"]
[497,"광주전남","직할","농성화정#2 T/L","2024~2025년 직할 변전협력회사 공사","170kV 차단기 조작시험 등","2024-04-17 14:00","2024-04-17 18:00","2024-04-17 14:00","2024-04-17 18:00","연속"]
[498,"광주전남","직할","매월화정#1 T/L","효천지구 하자케이블 교체공사(요청자 직접 시행)","○ 구간 : 광주효천1 154kV 신화순-매월T/L No.69 ~ 69-1 ○ 회선수 및 길이 : 1상, 약 218m ○ 작업 내역 : 케이블 철거 및 포설, 접속, 기타 작업 및 현장시험(내전압) ○ 시행자 : 한국토지주택공사 광주전남지역본부","2024-04-29 18:00","2024-04-30 18:00","취소","취소","연속"]
[499,"광주전남","직할","신화순매월#1 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 수평추락방지장치 설치 및 고정형 클램프 교체 작업구간 : 신화순-매월 1~66호","2024-04-01 09:00","2024-04-12 18:00","2024-04-01 09:00","2024-04-12 18:00","연속"]
[500,"광주전남","직할","매월화정#2 T/L","대한전선製 EBG 가스채취밸브 보강공사","송운(송전)-321(2021.03.30) 지중송전선로 EBG 고장원인 조사결과 및 재발방지대책 알림 관련으로 대한전선제 EBG 보강 시행","2024-04-15 09:00","2024-04-18 18:00","취소","취소","연속"]
[501,"광주전남","직할","비아하남#2 T/L","2024~2025년 직할 변전협력회사 공사","170kV GIS 차단기 조작시험 등","2024-04-19 09:00","2024-04-19 14:00","2024-04-19 09:00","2024-04-19 18:00","연속"]
[502,"광주전남","직할","하남장성#1 T/L","2024~2025년 직할 변전협력회사 공사","170kV GIS 차단기 조작시험","2024-04-18 09:00","2024-04-18 14:00","2024-04-18 09:00","2024-04-18 14:00","연속"]
[503,"광주전남","직할","하남장성#2 T/L","2024~2025년 직할 변전협력회사 공사","170kV GIS 차단기 조작시험","2024-04-18 14:00","2024-04-18 18:00","2024-04-18 14:00","2024-04-18 18:00","연속"]
[504,"대구","달성","고령논공#2 T/L","논공S/S GIS보통점검","논공S/S GIS보통점검","2024-04-09 09:00","2024-04-09 18:00","2024-04-09 09:00","2024-04-09 18:00","연속"]
[505,"대구","달성","고령논공#1 T/L","GIS보통점검","고령 : GIS, CVT, LA보통 논공 : GIS보통","2024-04-08 09:00","2024-04-08 18:00","2024-04-08 09:00","2024-04-08 18:00","연속"]
[506,"대구","달성","고령서구지#2 T/L","2024년 가공송전 순시점검 위탁공사","154kV 고령-서구지T/L 초기점검","2024-04-22 09:00","2024-04-25 17:00","2024-04-22 09:00","2024-04-25 17:00","연속"]
[507,"대구","달성","논공달성#2 T/L","GIS보통(논공S/S), CB조작(달성S/S)","GIS보통(논공S/S), CB조작(달성S/S)","2024-04-19 09:00","2024-04-19 18:00","2024-04-19 09:00","2024-04-19 18:00","연속"]
[508,"대구","달성","논공달성#1 T/L","GIS보통(논공S/S), CB조작(달성S/S)","GIS보통(논공S/S), CB조작(달성S/S)","2024-04-12 09:00","2024-04-12 18:00","2024-04-12 09:00","2024-04-12 18:00","연속"]
[509,"대구","달성","고령다산#1 T/L","GIS,CVT,LA보통점검","GIS,CVT,LA보통점검","2024-04-02 09:00","2024-04-02 18:00","2024-04-02 09:00","2024-04-02 18:00","연속"]
[510,"대구","달성","다산강창#1 T/L","GIS, CVT, LA보통(다산S/S), GIS보통(강창S/S)","GIS, CVT, LA보통(다산S/S), GIS보통(강창S/S)","2024-04-26 09:00","2024-04-26 18:00","2024-04-26 09:00","2024-04-26 18:00","연속"]
[511,"대구","달성","다산강창#2 T/L","GIS, CVT, LA보통(다산S/S), GIS보통(강창S/S)","GIS, CVT, LA보통(다산S/S), GIS보통(강창S/S)","2024-04-25 09:00","2024-04-25 18:00","2024-04-25 09:00","2024-04-25 18:00","연속"]
[512,"대구","달성","고령다산#2 T/L","GIS,CVT,LA보통점검","GIS,CVT,LA보통점검","2024-04-04 09:00","2024-04-04 18:00","2024-04-04 09:00","2024-04-04 18:00","연속"]
[513,"대구","달성","대구범물#1 T/L","GIS정밀(대구S/S), GIS하자(범물S/S)","GIS정밀(대구S/S), GIS하자(범물S/S)","2024-04-08 09:00","2024-04-09 18:00","2024-04-08 09:00","2024-04-09 18:00","연속"]
[514,"대구","달성","대구청도#1 T/L","[TEST] 6344GIS CB무부하가압","[TEST] 6344GIS CB무부하가압","2024-04-26 17:00","2024-04-26 18:00","2024-04-26 17:00","2024-04-26 18:00","연속"]
[515,"대구","달성","대구범물#2 T/L","GIS정밀(대구S/S), GIS하자(범물S/S)","GIS정밀(대구S/S), GIS하자(범물S/S)","2024-04-11 09:00","2024-04-12 18:00","2024-04-11 09:00","2024-04-12 18:00","연속"]
[516,"대구","달성","대구청도#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 북경남-대구T/L 수평 추락방지장치 설치공사(345kV 북경남-고령 T/L, 대구-청도T/L 병가선로)(안전확보)","2024-04-15 07:00","2024-04-15 18:00","2024-04-15 07:00","2024-04-15 18:00","연속"]
[517,"대구","달성","대구봉덕#1 T/L","GIS정밀(대구S/S), GIS보통(봉덕S/S)","GIS정밀(대구S/S), GIS보통(봉덕S/S)","2024-04-15 09:00","2024-04-16 18:00","2024-04-15 09:00","2024-04-16 18:00","연속"]
[518,"대구","달성","대구봉덕#2 T/L","GIS정밀(대구S/S), GIS보통(봉덕S/S)","GIS정밀(대구S/S), GIS보통(봉덕S/S)","2024-04-17 09:00","2024-04-18 18:00","2024-04-17 09:00","2024-04-18 18:00","연속"]
[519,"대구","달성","두류봉덕#2 T/L","GIS정밀점검(두류S/S), GIS 보통(봉덕S/S)","GIS정밀점검(두류S/S), GIS 보통(봉덕S/S)","2024-04-03 09:00","2024-04-04 18:00","2024-04-03 09:00","2024-04-04 18:00","연속"]
[520,"대구","달성","두류봉덕#1 T/L","GIS정밀점검(두류S/S), GIS 보통(봉덕S/S)","GIS정밀점검(두류S/S), GIS 보통(봉덕S/S)","2024-04-01 09:00","2024-04-02 18:00","2024-04-01 09:00","2024-04-02 18:00","연속"]
[521,"대구","달성","상인봉덕#1 T/L","154kV 상인-봉덕 지중T/L 지장송전선로 이설공사","154kV 상인-봉덕 지중T/L 지장송전선로 이설공사","2024-04-15 09:00","2024-05-03 18:00","2024-04-15 09:00","2024-05-03 18:00","연속"]
[522,"대구","달성","상인봉덕#1 T/L","2024년 가공송전 순시점검 위탁공사","154kV 상인-봉덕T/L 수목벌채","2024-04-11 09:00","2024-04-11 17:00","2024-04-11 09:00","2024-04-11 17:00","연속"]
[523,"대구","달성","상인봉덕#2 T/L","2024년 가공송전 순시점검 위탁공사","154kV 상인-봉덕T/L 수목벌채","2024-04-12 09:00","2024-04-12 17:00","2024-04-12 09:00","2024-04-12 17:00","연속"]
[524,"대구","직할","남대구S/S #1 BUS","남대구S/S 154kV GIS 교체 및 증설공사","○ 170kV GIS M.Tr 1차 및 T/L Bay 철거/설치, SW 2회선 증설 ○ 제어(광)케이블 포설 및 결선","2024-04-26 14:00","2024-05-09 16:00","취소","취소","연속"]
[525,"대구","직할","남대구동인#1 T/L","남대구S/S 154kV GIS 교체 및 증설공사(TEST선로)","○ #2BUS 무부하가압","2024-04-26 13:30","2024-04-26 14:00","취소","취소","연속"]
[526,"대구","직할","범물남대구#2 T/L","남대구S/S 154kV GIS 교체 및 증설공사","○ 170kV GIS M.Tr 1차 및 T/L Bay 철거/설치, SW 2회선 증설 ○ 제어(광)케이블 포설 및 결선","2024-04-24 09:00","2024-05-22 16:00","취소","취소","연속"]
[527,"대구","직할","내당두류#1 T/L","내당S/S 내당-두류 #1T/L GIS 보통점검","내당S/S 내당-두류 #1T/L GIS 보통점검","2024-04-24 09:00","2024-04-24 18:00","2024-04-24 09:00","2024-04-24 18:00","연속"]
[528,"대구","직할","동인내당#2 T/L","내당S/S 동인-내당#2T/L GIS 보통점검","내당S/S 동인-내당#2T/L GIS 보통점검","2024-04-23 09:00","2024-04-23 18:00","2024-04-23 09:00","2024-04-23 18:00","연속"]
[529,"대구","직할","동인내당#1 T/L","내당S/S 동인-내당#1T/L GIS 보통점검","내당S/S 동인-내당#1T/L GIS 보통점검","2024-04-22 09:00","2024-04-22 18:00","2024-04-22 09:00","2024-04-22 18:00","연속"]
[530,"대구","직할","내당두류#2 T/L","내당S/S 내당-두류 #2T/L GIS 보통점검","내당S/S 내당-두류 #2T/L GIS 보통점검","2024-04-25 09:00","2024-04-25 18:00","2024-04-25 09:00","2024-04-25 18:00","연속"]
[531,"대구","칠곡","북대구관음#2 T/L","관음S/S 154kV GIS 대체공사(안전확보,무부하)","관음S/S 154kV GIS 대체공사(4차) -대상: 북대구-관음#1, BUS TIE","2024-04-22 09:00","2024-04-24 14:00","2024-04-24 09:00","2024-04-25 14:00","연속"]
[532,"대구","칠곡","관음S/S CB 6100","관음S/S 154kV GIS 대체공사(4차)","관음S/S 154kV GIS 대체공사(4차) -대상: 북대구-관음#1, BUS-TIE","2024-04-11 09:00","2024-05-03 18:00","2024-04-11 09:00","2024-05-03 18:00","연속"]
[533,"대구","칠곡","관음S/S #1 BUS","관음S/S 154kV GIS 대체공사","관음S/S 154kV GIS 대체공사(4차) -대상: 북대구-관음#1, BUS TIE","2024-04-15 09:00","2024-04-24 14:00","2024-04-15 09:00","2024-04-22 09:00","연속"]
[534,"대구","칠곡","북대구관음#2 T/L","관음S/S 154kV GIS 대체공사(안전확보)","관음S/S 154kV GIS 대체공사(4차) -대상: 북대구-관음#1, BUS TIE","2024-04-15 09:00","2024-04-15 18:00","2024-04-15 09:00","2024-04-15 18:00","연속"]
[535,"대구","칠곡","북대구관음#2 T/L","관음S/S 154kV GIS 대체공사(안전확보,무부하)","관음S/S 154kV GIS 대체공사(4차) -대상: 북대구-관음#1, BUS TIE","2024-04-12 09:00","2024-04-12 18:00","2024-04-12 09:00","2024-04-14 18:00","연속"]
[536,"대구","칠곡","북대구관음#1 T/L","관음S/S 154kV GIS 대체공사(4차)","관음S/S 154kV GIS 대체공사(4차) -대상: 북대구-관음#1, BUS-TIE","2024-04-11 09:00","2024-05-03 18:00","2024-04-11 09:00","2024-05-03 18:00","연속"]
[537,"대구","칠곡","관음S/S #2 BUS","관음S/S 154kV GIS 대체공사","관음S/S 154kV GIS 대체공사(4차) -대상: 북대구-관음#1, BUS TIE","2024-04-24 14:00","2024-05-03 14:00","2024-04-22 14:00","2024-05-03 14:00","연속"]
[538,"대구","칠곡","어모김천#2 T/L","154kV 송전선로 보호배전반 점검","- 어모, 김천S/S 어모-김천#2T/L 보호배전반 초기점검","2024-04-16 11:00","2024-04-16 17:00","2024-04-16 11:00","2024-04-16 17:00","연속"]
[539,"대구","포항","청하영덕#2 T/L","345kV 영포 외 15개 T/L 추락방지장치 설치 등 송전정비공사","154kV 청하-영덕#2T/L 수평추락방지장치 설치","2024-04-26 07:00","2024-05-13 18:00","2024-04-26 07:00","2024-05-13 18:00","연속"]
[540,"경북","구미","남인동인동#1 T/L","(안전확보) 신옥천-북경남 등 8개T/L 수평 추락방지장치 설치공사","(안전확보) 칠곡-인동#2T/L 수평 추락방지장치 설치 안전확보차 - 칠곡-인동#2T/L No.119~120호","2024-04-25 07:00","2024-04-25 18:00","2024-05-02 07:00","2024-05-02 18:00","연속"]
[541,"경북","구미","남인동인동#2 T/L","(안전확보) 신옥천-북경남 등 8개T/L 수평 추락방지장치 설치공사","(안전확보) 칠곡-인동#1T/L 수평 추락방지장치 설치 안전확보차 - 칠곡-인동#1T/L No.119~120호","2024-04-15 07:00","2024-04-15 18:00","2024-04-15 07:00","2024-04-15 18:00","연속"]
[542,"경북","구미","선산산동#1 T/L","송전선로 인근 골프장 안전 그물망 설치 관련 안전이격거리 확보차","154kV 선산-산동T/L No.11~12 인근 골프장 안전그물망 설치","2024-04-04 09:00","2024-04-12 18:00","2024-04-08 09:00","2024-04-12 18:00","매일"]
[543,"경북","구미","선산산동#2 T/L","송전선로 인근 골프장 안전 그물망 설치 관련 안전이격거리 확보차","154kV 선산-산동T/L No.11~12 인근 골프장 안전그물망 설치","2024-04-04 09:00","2024-04-12 18:00","2024-04-08 09:00","2024-04-12 18:00","매일"]
[544,"경북","구미","선산청리#2 T/L","2024-25년 구미전력지사 변전협력회사 공사","[선산S/S] - GIS 보통점검[정밀] - LA 하자점검 - 154kV GIS DS 방압변 점검 [청리S/S] - LA 교체","2024-04-08 14:00","2024-04-08 18:00","취소","취소","연속"]
[545,"경북","구미","선산청리#1 T/L","2024-25년 구미전력지사 변전협력회사 공사","[선산S/S] - GIS 보통점검[정밀] - LA 하자점검 - 154kV GIS DS 방압변 점검 [청리S/S] - LA 교체","2024-04-08 09:00","2024-04-08 14:00","취소","취소","연속"]
[546,"경북","구미","청리상주#1 T/L","345kV 서대구-선산 등 6개T/L 피뢰기 및 추락방지시설 설치공사","154kV 청리-상주#1T/L 피뢰기 설치","2024-04-29 07:00","2024-05-03 18:00","취소","취소","매일"]
[547,"경북","구미","선산청리#2 T/L","345kV 서대구-선산 등 6개T/L 피뢰기 및 추락방지시설 설치공사","154kV 선산-청리#2T/L 피뢰기 설치","2024-04-22 07:00","2024-05-03 18:00","취소","취소","매일"]
[548,"경북","영주","문경단양 T/L","154kV 단양T/L 추락방지장치 설치공사","154kV 단양T/L 추락방지장치 설치","2024-04-13 09:00","2024-04-14 18:00","2024-04-13 09:00","2024-04-14 18:00","매일"]
[549,"경북","영주","문경단양 T/L","154kV 단양T/L 추락방지장치 설치공사","154kV 단양T/L 추락방지장치 설치","2024-04-06 09:00","2024-04-07 18:00","2024-04-06 09:00","2024-04-07 18:00","매일"]
[550,"경북","영주","점촌단양 T/L","154kV 단양T/L 수평 추락방지장치 설치공사","154kV 단양T/L 수평 추락방지장치 설치","2024-04-27 09:00","2024-04-28 18:00","2024-04-27 09:00","2024-04-28 18:00","매일"]
[551,"경북","영주","점촌단양 T/L","154kV 단양T/L 수평 추락방지장치 설치공사","154kV 단양T/L 수평 추락방지장치 설치","2024-04-20 09:00","2024-04-21 18:00","2024-04-20 09:00","2024-04-21 18:00","매일"]
[552,"경북","직할","안동동안동#1 T/L","154kV 안동-동안동T/L 용량증대 선종교체공사","□ 목 적 : 154kV 진보-동안동T/L 건설이후 상정고장 시 154kV 안동-동안동T/L 과부하 해소 □ 위 치 : 경북 안동시 □ 규 모 ○ ACSR 410㎟×S×2C×8.86㎞ 철거 ○ ASCC/TW 520㎟×S×2C×8.86㎞ 설치","2024-04-15 09:00","2024-05-31 18:00","2024-04-15 09:00","2024-05-31 18:00","연속"]
[553,"경북","직할","안동동안동#2 T/L","154kV 안동-동안동T/L 용량증대 선종교체공사","□ 목 적 : 154kV 진보-동안동T/L 건설이후 상정고장 시 154kV 안동-동안동T/L 과부하 해소 □ 위 치 : 경북 안동시 □ 규 모 ○ ACSR 410㎟×S×2C×8.86㎞ 철거 ○ ASCC/TW 520㎟×S×2C×8.86㎞ 설치","2024-04-15 09:00","2024-05-31 18:00","2024-04-15 09:00","2024-05-31 18:00","연속"]
[554,"경북","직할","동안동임하HP T/L","154kV 안동-동안동T/L 용량증대 선종교체공사","□ 목 적 : 154kV 진보-동안동T/L 건설이후 상정고장 시 154kV 안동-동안동T/L 과부하 해소 □ 위 치 : 경북 안동시 □ 규 모 ○ ACSR 410㎟×S×2C×8.86㎞ 철거 ○ ASCC/TW 520㎟×S×2C×8.86㎞ 설치","2024-04-22 09:00","2024-04-24 18:00","2024-04-22 09:00","2024-04-24 18:00","연속"]
[555,"경북","직할","동안동임하HP T/L","154kV 안동-동안동T/L 용량증대 선종교체공사","□ 목 적 : 154kV 진보-동안동T/L 건설이후 상정고장 시 154kV 안동-동안동T/L 과부하 해소 □ 위 치 : 경북 안동시 □ 규 모 ○ ACSR 410㎟×S×2C×8.86㎞ 철거 ○ ASCC/TW 520㎟×S×2C×8.86㎞ 설치","2024-04-29 09:00","2024-05-01 18:00","2024-04-29 09:00","2024-05-01 18:00","연속"]
[556,"경북","직할","안동동안동#1 T/L","'24-25년 경북직할 송전협력회사 공사","154kV 안동-동안동#1T/L No.1~31 추락방지장치 설치","2024-04-01 08:00","2024-04-05 18:00","2024-04-01 08:00","2024-04-05 18:00","연속"]
[557,"경북","직할","울진삼척GP#1 T/L","24~25년 경북본부 직할 변전협력회사 공사","GIS 초기점검","2024-04-23 09:00","2024-04-23 14:00","2024-04-23 09:00","2024-04-23 14:00","연속"]
[558,"경북","직할","울진삼척GP#2 T/L","24~25년 경북본부 직할 변전협력회사 공사","GIS 초기점검","2024-04-24 09:00","2024-04-24 14:00","2024-04-24 09:00","2024-04-24 14:00","연속"]
[559,"경북","직할","의성안계#1 T/L","24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검","2024-04-30 09:00","2024-04-30 14:00","2024-04-30 09:00","2024-04-30 14:00","연속"]
[560,"경북","직할","풍산안동CC#2 T/L","24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검","2024-04-12 09:00","2024-04-12 18:00","2024-04-12 09:00","2024-04-12 18:00","연속"]
[561,"경북","직할","풍산안동CC#1 T/L","24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검","2024-04-08 09:00","2024-04-08 18:00","2024-04-08 09:00","2024-04-08 18:00","연속"]
[562,"경북","직할","안동풍산 T/L","154㎸ 안동-풍산T/L 29~31호간 지장이설공사(요청자 직접시행)","1. 대상선로 : 154㎸ 안동-풍산 송전선로 2. 공사구간 : No.29 ～ No.31(HSTACIR/AW 240㎟(단도체), 1회선) 3. 공사내역 : 송전선로 신설 및 철거(신설 No.31, 철거 기설 No.30, 31)","2024-04-01 09:00","2024-04-04 18:00","2024-04-01 09:00","2024-04-04 18:00","연속"]
[563,"경북","직할","현종산풍력평해#2 T/L","24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검, 가스압력계 교체","2024-04-18 09:00","2024-04-18 14:00","2024-04-18 09:00","2024-04-18 14:00","연속"]
[564,"부산울산","동부산","구서S/S #2 BUS","154kV 구서S/S 장기사용 GIS 교체공사(3차)","○ 154kV 신양산-구서#1T/L, #2M.Tr 1차 GIS #2DS 철거 및 고깔처리","2024-04-06 09:00","2024-04-09 18:00","취소","취소","연속"]
[565,"부산울산","동부산","신양산구서#1 T/L","154kV 구서S/S 장기사용 GIS 교체공사(3차)","○ 154kV 신양산-구서#1T/L GIS 교체","2024-04-06 09:00","2024-05-11 18:00","취소","취소","연속"]
[566,"부산울산","동부산","구서S/S #1 BUS","154kV 구서S/S 장기사용 GIS 교체공사(3차)","○ 154kV 신양산-구서#1T/L, #2M.Tr 1차 GIS 철거 및 설치","2024-04-09 09:00","2024-04-18 18:00","취소","취소","연속"]
[567,"부산울산","동부산","구서S/S #2 BUS","154kV 구서S/S 장기사용 GIS 교체공사(3차)","○ 154kV 신양산-구서#1T/L, #2M.Tr 1차 GIS 철거 및 설치","2024-04-19 09:00","2024-05-11 17:00","취소","취소","연속"]
[568,"부산울산","동부산","노포정관#1 T/L","2024-2025년 동부산 가공송전협력회사 공사","폴리머점퍼지지애자 설치","2024-04-29 07:00","2024-04-30 18:00","2024-04-29 07:00","2024-04-30 18:00","연속"]
[569,"부산울산","동부산","노포정관#2 T/L","2024-2025년 동부산 가공송전협력회사 공사","폴리머점퍼지지애자 설치","2024-04-26 07:00","2024-04-26 18:00","2024-04-26 07:00","2024-04-26 18:00","연속"]
[570,"부산울산","동부산","수영우동 T/L","우동S/S 617GIS 차단기 동작시험(수영우동T/L)","우동S/S 617GIS 차단기 동작시험(수영우동T/L) 병행)수영S/S 627 GIS 보통점검","2024-04-13 09:30","2024-04-13 17:00","2024-04-13 09:30","2024-04-13 17:00","연속"]
[571,"부산울산","동부산","우동대연 T/L","우동S/S 627GIS 차단기 동작시험(우동대연T/L)","우동S/S 627GIS 차단기 동작시험(우동대연T/L)","2024-04-14 09:30","2024-04-14 17:00","2024-04-14 09:30","2024-04-14 17:00","연속"]
[572,"부산울산","북부산","학장개금#2 T/L","24-25년 북부산전력지사 변전총액공사","개금S/S 학장-개금#2T/L GIS 조작시험","2024-04-12 13:00","2024-04-12 18:00","2024-04-12 13:00","2024-04-12 18:00","연속"]
[573,"부산울산","북부산","학장개금#1 T/L","24-25년 북부산전력지사 변전총액공사","개금S/S 학장-개금#1T/L GIS 조작시험","2024-04-12 09:00","2024-04-12 13:00","2024-04-12 09:00","2024-04-12 13:00","연속"]
[574,"부산울산","북부산","개금범천#1 T/L","개금S/S 154kV 장기사용 GIS 교체공사","개금S/S 154kV 장기사용 GIS 교체공사 - 개금범천#1,2T/L 대체","2024-04-29 09:00","2024-05-17 18:00","2024-04-29 09:00","2024-05-17 18:00","연속"]
[575,"부산울산","북부산","구포S/S CB 6100","24-25년 북부산전력지사 변전총액공사","구포S/S 6100 GIS 초기점검","2024-04-16 09:00","2024-04-16 18:00","2024-04-16 09:00","2024-04-16 18:00","연속"]
[576,"부산울산","북부산","북부산구포#2 T/L","24-25년 북부산전력지사 변전총액공사","구포S/S 북부산-구포#2T/L GIS 초기점검","2024-04-04 09:00","2024-04-04 18:00","2024-04-04 09:00","2024-04-04 18:00","연속"]
[577,"부산울산","북부산","북부산구포#1 T/L","24-25년 북부산전력지사 변전총액공사","구포S/S 북부산-구포#1T/L GIS 초기점검","2024-04-03 09:00","2024-04-03 18:00","2024-04-03 09:00","2024-04-03 18:00","연속"]
[578,"부산울산","북부산","구포대저#1 T/L","24-25년 북부산전력지사 변전총액공사","대저S/S 구포-대저#1T/L GIS 하자점검","2024-04-01 09:00","2024-04-01 18:00","2024-04-01 09:00","2024-04-01 18:00","연속"]
[579,"부산울산","북부산","구포대저#2 T/L","24-25년 북부산전력지사 변전총액공사","대저S/S 구포-대저#2T/L GIS 하자점검","2024-04-02 09:00","2024-04-02 18:00","2024-04-02 09:00","2024-04-02 18:00","연속"]
[580,"부산울산","북부산","모라엄궁#1 T/L","24-25년 북부산전력지사 변전총액공사","모라S/S 모라-엄궁#1T/L GIS 조작시험","2024-04-19 09:00","2024-04-19 18:00","2024-04-19 09:00","2024-04-19 18:00","연속"]
[581,"부산울산","북부산","모라S/S CB 6100","24-25년 북부산전력지사 변전총액공사","모라S/S 154kV 6100 B/T GIS 조작시험","2024-04-11 09:00","2024-04-11 18:00","2024-04-11 09:00","2024-04-11 18:00","연속"]
[582,"부산울산","북부산","미남S/S CB 6100","24년 북부산전력지사 154kV GIS 정밀점검 공사","미남S/S 154kV 6100 B/T GIS 정밀점검","2024-04-24 08:00","2024-04-25 18:00","2024-04-24 08:00","2024-04-25 18:00","연속"]
[583,"부산울산","북부산","미남S/S #60 BUS","24년 북부산전력지사 154kV GIS 정밀점검 공사","미남S/S 154kV 6100 B/T GIS 정밀점검","2024-04-24 08:00","2024-04-25 18:00","2024-04-24 08:00","2024-04-25 18:00","연속"]
[584,"부산울산","북부산","북부산양산 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치 안전확보","154kV 북부산-삼랑진T/L 수평 추락방지장치 설치(11~36, 41~46호 33기) 4회선 병가철탑 상하회선 안전확보","2024-04-01 07:00","2024-04-07 18:00","취소","취소","연속"]
[585,"부산울산","북부산","북부산삼랑진PP T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치","154kV 북부산-삼랑진T/L 수평 추락방지장치 설치(11~36, 41~46호 33기)","2024-04-01 07:00","2024-04-07 18:00","취소","취소","연속"]
[586,"부산울산","북부산","언양산막#2 T/L","154kV 언양-산막T/L OPGW 증설공사","OPGW 교체 : 23.3km","2024-04-08 08:00","2024-04-30 18:00","2024-04-08 08:00","2024-04-30 18:00","매일"]
[587,"부산울산","북부산","서창산막#1 T/L","154kV 언양-산막T/L OPGW 증설공사","OPGW 교체 : 23.3km","2024-04-27 08:00","2024-04-28 18:00","취소","취소","연속"]
[588,"부산울산","북부산","모라엄궁#1 T/L","엄궁S/S 154kV #1M.Tr 대체공사","- 노후 변압기 대체(엄궁S/S 154kV #1M.Tr) - 대체 시험가압 선로","2024-04-08 09:00","2024-04-09 18:00","2024-04-08 09:00","2024-04-09 18:00","연속"]
[589,"부산울산","북부산","호포매리#1 T/L","154kV 대동분기T/L 건설공사","지지물 : 관형지지물 1기, 케이블타워 2기, 가철탑 2기 전력선 : TACSR 240㎟ × S × 2C - 1.01km","2024-04-20 07:00","2024-04-21 18:00","2024-04-20 07:00","2024-04-21 18:00","연속"]
[590,"부산울산","북부산","호포매리#1 T/L","154kV 대동분기T/L 건설공사","지지물 : 관형지지물 1기, 케이블타워 2기, 가철탑 2기 전력선 : TACSR 240㎟ × S × 2C - 1.01km","2024-04-13 07:00","2024-04-14 18:00","2024-04-13 07:00","2024-04-14 18:00","연속"]
[591,"부산울산","북부산","호포매리#2 T/L","154kV 대동분기T/L 건설공사","지지물 : 관형지지물 1기, 케이블타워 2기, 가철탑 2기 전력선 : TACSR 240㎟ × S × 2C - 1.01km","2024-04-27 07:00","2024-04-28 18:00","2024-04-27 07:00","2024-04-28 18:00","연속"]
[592,"부산울산","서부산","용원녹공#2 T/L","2024년 상반기 서부산전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검(DS부 제외)","2024-04-03 09:00","2024-04-04 18:00","2024-04-03 09:00","2024-04-04 18:00","연속"]
[593,"부산울산","서부산","용원녹공#1 T/L","2024년 상반기 서부산전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검(DS부 제외)","2024-04-01 09:00","2024-04-02 18:00","2024-04-01 09:00","2024-04-02 18:00","연속"]
[594,"부산울산","서부산","녹산S/S #2 BUS","녹산S/S 154kV 장기사용 GIS 교체공사","녹산S/S 154kV 장기사용 GIS 교체공사(1차분) -미음-녹산#2T/L, #2M.Tr 1차 GIS 대체 - #6232DS, #622DSB 철거 및 신규 GIS 설치","2024-04-18 09:00","2024-05-03 17:00","2024-04-18 09:00","2024-05-03 17:00","연속"]
[595,"부산울산","서부산","신녹산녹산#1 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","녹산S/S 154kV 장기사용 GIS 교체공사(1차분) -미음-녹산#2T/L, #2M.Tr 1차 GIS 대체 - #1BUS 시험가압 24시간 (#1DS개방상태)","2024-04-16 17:00","2024-04-17 17:00","2024-04-16 17:00","2024-04-17 17:00","연속"]
[596,"부산울산","서부산","녹산S/S #1 BUS","녹산S/S 154kV 장기사용 GIS 교체공사","녹산S/S 154kV 장기사용 GIS 교체공사(1차분) -미음-녹산#2T/L, #2M.Tr 1차 GIS 대체 - #6231DS, 6233CB, #621DS, #627CB 철거 및 신규 GIS 설치","2024-04-08 09:00","2024-04-17 18:00","2024-04-08 09:00","2024-04-17 18:00","연속"]
[597,"부산울산","서부산","신녹산녹산#1 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","녹산S/S 154kV 장기사용 GIS 교체공사(1차분) -미음-녹산#2T/L, #2M.Tr 1차 GIS 대체 - #6232DS, #622DS 고깔 및 #2BUS 시험가압 1시간","2024-04-05 17:00","2024-04-05 18:00","2024-04-05 17:00","2024-04-05 18:00","연속"]
[598,"부산울산","서부산","서부산다대#2 T/L","2024년 상반기 서부산전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검(DS부 제외)","2024-04-10 09:00","2024-04-11 18:00","2024-04-10 09:00","2024-04-11 18:00","연속"]
[599,"부산울산","서부산","서부산다대#1 T/L","2024년 상반기 서부산전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검(DS부 제외)","2024-04-08 09:00","2024-04-09 18:00","2024-04-08 09:00","2024-04-09 18:00","연속"]
[600,"부산울산","서부산","서부산S/S #66 BUS","서부산S/S 345kV 용량부족 차단기 대체공사","154kV 변전설비 집중감시제어반 DB 수용","2024-04-29 09:00","2024-04-30 18:00","2024-04-29 09:00","2024-04-30 18:00","연속"]
[601,"부산울산","서부산","서부산S/S #61 BUS","서부산S/S 345kV 용량부족 차단기 대체공사","154kV 변전설비 집중감시제어반 DB 수용","2024-04-22 09:00","2024-04-24 18:00","2024-04-22 09:00","2024-04-24 18:00","연속"]
[602,"부산울산","서부산","서부산S/S #65 BUS","서부산S/S 345kV 용량부족 차단기 대체공사","154kV 변전설비 집중감시제어반 DB 수용","2024-04-15 09:00","2024-04-17 18:00","2024-04-15 09:00","2024-04-17 18:00","연속"]
[603,"부산울산","서부산","서부산엄궁#2 T/L","서부산S/S 154kV 서부산-엄궁#2T/L GIS 동작시험","서부산S/S 154kV 서부산-엄궁#2T/L GIS 동작시험","2024-04-12 09:00","2024-04-12 18:00","2024-04-12 09:00","2024-04-12 18:00","연속"]
[604,"부산울산","서부산","서부산엄궁#1 T/L","서부산S/S 154kV 서부산-엄궁#1T/L GIS 동작시험","서부산S/S 154kV 서부산-엄궁#1T/L GIS 동작시험","2024-04-17 09:00","2024-04-17 18:00","2024-04-17 09:00","2024-04-17 18:00","연속"]
[605,"부산울산","서부산","서부산S/S #60 BUS","서부산S/S 345kV 용량부족 차단기 대체공사","154kV 변전설비 집중감시제어반 DB 수용","2024-04-01 09:00","2024-04-03 18:00","2024-04-01 09:00","2024-04-03 18:00","연속"]
[606,"부산울산","울산","신울산웅촌#2 T/L","24~25년 변전협력회사 총액공사","- 양단 GIS 차단기 동작시험","2024-04-18 09:00","2024-04-18 18:00","2024-04-18 09:00","2024-04-18 18:00","연속"]
[607,"부산울산","울산","신울산두왕#1 T/L","24~25년 변전협력회사 총액공사","- 양단 GIS 하자점검 - 신울산측 6800 GIS 하자점검","2024-04-01 09:00","2024-04-02 18:00","2024-04-01 09:00","2024-04-02 18:00","연속"]
[608,"부산울산","울산","신울산두왕#2 T/L","24~25년 변전협력회사 총액공사","- 양단 GIS 하자점검 - 신울산측 6900 GIS 하자점검","2024-04-03 09:00","2024-04-04 18:00","2024-04-03 09:00","2024-04-04 18:00","연속"]
[609,"부산울산","울산","신울산언양#1 T/L","24~25년 변전협력회사 총액공사","- GIS 차단기 동작시험","2024-04-05 09:00","2024-04-05 14:00","2024-04-05 09:00","2024-04-05 14:00","연속"]
[610,"부산울산","울산","신울산매암#2 T/L","신울산S/S 154kV 현대화공사","신울산-매암#2T/L C/H설치 및 시험가압","2024-04-16 09:00","2024-04-19 18:00","2024-04-16 09:00","2024-04-19 18:00","연속"]
[611,"부산울산","울산","신울산S/S CB 6471G","신울산S/S 154kV 현대화공사","신울산-매암#1T/L C/H설치 및 시험가압","2024-04-16 09:00","2024-04-19 18:00","2024-04-16 09:00","2024-04-19 18:00","연속"]
[612,"부산울산","울산","신울산매암#1 T/L","신울산S/S 154kV 현대화공사","신울산-매암#1T/L C/H설치 및 시험가압","2024-04-16 09:00","2024-04-19 18:00","2024-04-16 09:00","2024-04-19 18:00","연속"]
[613,"부산울산","울산","신울산S/S CB 6571G","신울산S/S 154kV 현대화공사","신울산-매암#2T/L C/H설치 및 시험가압","2024-04-16 09:00","2024-04-19 18:00","2024-04-16 09:00","2024-04-19 18:00","연속"]
[614,"부산울산","울산","신울산웅촌#1 T/L","24~25년 변전협력회사 총액공사","- 양단 GIS 차단기 동작시험","2024-04-17 09:00","2024-04-17 18:00","2024-04-17 09:00","2024-04-17 18:00","연속"]
[615,"부산울산","울산","신울산울산#2 T/L","신울산S/S 154kV 현대화공사","신울산-매암#1,2T/L C/H설치관련 시험가압","2024-04-18 18:00","2024-04-19 18:00","2024-04-18 18:00","2024-04-19 18:00","연속"]
[616,"부산울산","울산","신울산옥동#1 T/L","24~25년 변전협력회사 총액공사","- 양단 GIS 차단기 동작시험","2024-04-19 09:00","2024-04-19 14:00","2024-04-19 09:00","2024-04-19 14:00","연속"]
[617,"부산울산","울산","신울산옥동#2 T/L","24~25년 변전협력회사 총액공사","- 양단 GIS 차단기 동작시험","2024-04-19 14:00","2024-04-19 18:00","2024-04-19 14:00","2024-04-19 18:00","연속"]
[618,"부산울산","울산","신울산명례#1 T/L","2024-2025년 동부산 가공송전협력회사 공사","폴리머점퍼지지애자 설치","2024-04-22 07:00","2024-04-22 18:00","2024-04-22 07:00","2024-04-22 18:00","연속"]
[619,"부산울산","울산","신울산매암#3 T/L","신울산S/S 154kV 현대화공사","신울산-매암#3T/L 관로 상부 GIS 기초공사","2024-04-22 09:00","2024-04-25 18:00","2024-04-22 09:00","2024-04-25 18:00","연속"]
[620,"부산울산","울산","신울산매암#3 T/L","신울산S/S 154kV 현대화공사","신울산-매암#3T/L C/H설치 및 시험가압","2024-04-22 09:00","2024-04-24 18:00","2024-04-22 09:00","2024-04-24 18:00","연속"]
[621,"부산울산","울산","신울산S/S CB 6671G","신울산S/S 154kV 현대화공사","신울산-매암#3T/L C/H설치 및 시험가압","2024-04-22 09:00","2024-04-24 18:00","2024-04-22 09:00","2024-04-24 18:00","연속"]
[622,"부산울산","울산","신울산명례#2 T/L","2024-2025년 동부산 가공송전협력회사 공사","폴리머점퍼지지애자 설치","2024-04-23 07:00","2024-04-25 18:00","2024-04-23 07:00","2024-04-25 18:00","연속"]
[623,"부산울산","울산","신울산울산#1 T/L","신울산S/S 154kV 현대화공사","신울산-매암#3T/L C/H설치관련 시험가압","2024-04-23 18:00","2024-04-24 18:00","2024-04-23 18:00","2024-04-24 18:00","연속"]
[624,"부산울산","울산","신울산태화#1 T/L","신울산S/S 154kV 현대화공사","신울산S/S 7구간 기초, 연락#2T/L 구성 및 태화#1T/L 인출변경","2024-04-26 09:00","2024-06-28 18:00","취소","취소","연속"]
[625,"부산울산","울산","반천언양#2 T/L","24년 154kV 개폐장치 정밀점검 공사","- 154kV GIS 정밀점검 시험가압 1H","2024-04-30 14:00","2024-04-30 18:00","2024-04-30 14:00","2024-04-30 18:00","연속"]
[626,"부산울산","울산","반천언양#1 T/L","24년 154kV 개폐장치 정밀점검 공사","- 154kV GIS 정밀점검 시험가압 1H","2024-04-25 14:00","2024-04-25 18:00","2024-04-25 14:00","2024-04-25 18:00","연속"]
[627,"부산울산","울산","반천언양#2 T/L","24년 154kV 개폐장치 정밀점검 공사","- 154kV GIS 정밀점검 시험가압 1H","2024-04-23 14:00","2024-04-23 18:00","2024-04-23 14:00","2024-04-23 18:00","연속"]
[628,"부산울산","울산","신울산언양#2 T/L","154kV 추락방지장치 설치공사","[휴전] 신울산-언양#2 추락방지장치 설치 - 1~63호","2024-04-01 07:30","2024-04-04 18:00","2024-04-01 07:30","2024-04-04 18:00","연속"]
[629,"부산울산","울산","반천언양#1 T/L","154kV 언양-산막T/L OPGW 증설공사","OPGW 교체 : 23.3km","2024-04-08 08:00","2024-04-12 18:00","2024-04-08 08:00","2024-04-12 18:00","연속"]
[630,"부산울산","울산","옥동외동#1 T/L","154kV 추락방지장치 설치공사","[휴전]외동-옥동#1 추락방지장치 설치 - 1~35호","2024-04-29 07:30","2024-04-30 18:00","2024-04-29 07:30","2024-04-30 18:00","연속"]
[631,"부산울산","울산","용연울산TP#2 T/L","24~25년 변전협력회사 총액공사","- GIS 보통점검","2024-04-24 09:00","2024-04-24 18:00","2024-04-24 09:00","2024-04-24 18:00","연속"]
[632,"부산울산","울산","울산영남TP#2 T/L","154kV 추락방지장치 설치공사","[휴전] 울산-영남#2 추락방지장치 설치 - 1~21호 ch1기 포함","2024-04-11 07:30","2024-04-12 18:00","2024-04-11 07:30","2024-04-12 18:00","연속"]
[633,"부산울산","울산","울산영남TP#1 T/L","154kV 추락방지장치 설치공사","[휴전] 울산-영남#1 추락방지장치 설치 - 1~21호 ch1기 포함","2024-04-08 07:30","2024-04-09 18:00","2024-04-08 07:30","2024-04-09 18:00","연속"]
[634,"부산울산","울산","울주입실#2 T/L","24~25년 변전협력회사 총액공사","- LA, CVT 보통점검","2024-04-15 09:00","2024-04-15 18:00","2024-04-15 09:00","2024-04-15 18:00","연속"]
[635,"부산울산","울산","울주입실#1 T/L","24~25년 변전협력회사 총액공사","- LA, CVT 보통점검","2024-04-04 09:00","2024-04-04 18:00","2024-04-04 09:00","2024-04-04 18:00","연속"]
[636,"부산울산","울산","울주직동#2 T/L","24~25년 변전협력회사 총액공사","- 양단 LA 보통점검 - 직동측 GIS 보통점검","2024-04-23 09:00","2024-04-23 18:00","2024-04-23 09:00","2024-04-23 18:00","연속"]
[637,"부산울산","울산","울주직동#1 T/L","24~25년 변전협력회사 총액공사","- 양단 LA 보통점검 - 직동측 GIS 보통점검","2024-04-22 09:00","2024-04-22 18:00","2024-04-22 09:00","2024-04-22 18:00","연속"]
[638,"부산울산","울산","울주외동#2 T/L","24~25년 변전협력회사 총액공사","- CVT 보통점검","2024-04-08 14:00","2024-04-08 18:00","2024-04-08 14:00","2024-04-08 18:00","연속"]
[639,"부산울산","울산","울주외동#1 T/L","24~25년 변전협력회사 총액공사","- CVT 보통점검","2024-04-08 09:00","2024-04-08 14:00","2024-04-08 09:00","2024-04-08 14:00","연속"]
[640,"부산울산","울산","웅촌서창#2 T/L","24~25년 변전협력회사 총액공사","- GIS 차단기 동작시험","2024-04-16 14:00","2024-04-16 18:00","2024-04-16 14:00","2024-04-16 18:00","연속"]
[641,"부산울산","울산","웅촌서창#1 T/L","24~25년 변전협력회사 총액공사","- GIS 차단기 동작시험","2024-04-16 09:00","2024-04-16 14:00","2024-04-16 09:00","2024-04-16 14:00","연속"]
[642,"부산울산","직할","범일서면#2 T/L","154kV 범일S/S #3M.Tr 증설공사","- 신설 #1BUS GIB(Reducer) 설치 - 기설 #1BUS END COVER부 SPACER 교체","2024-04-01 09:00","2024-04-05 18:00","취소","취소","연속"]
[643,"경남","직할","녹공마천#1 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-04-25 07:00","2024-04-25 18:00","2024-04-25 07:00","2024-04-25 18:00","연속"]
[644,"경남","직할","녹공마천#2 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-04-26 07:00","2024-04-26 18:00","2024-04-26 07:00","2024-04-26 18:00","연속"]
[645,"경남","직할","신김해진례#2 T/L","154kV 신김해-진례#2T/L 추락방지장치 설치공사","154kV 신김해-진례#2T/L 추락방지장치 설치공사(345kV 신마산-신김해T/L 병가개소)","2024-04-30 07:00","2024-05-01 18:00","2024-04-30 07:00","2024-05-01 18:00","매일"]
[646,"경남","직할","신김해진례#1 T/L","154kV 신김해-진례#1T/L 추락방지장치 설치공사","154kV 신김해-진례#1T/L 추락방지장치 설치공사(345kV 신마산-신김해T/L 병가개소)","2024-04-24 07:00","2024-04-25 18:00","2024-04-24 07:00","2024-04-25 18:00","매일"]
[647,"경남","직할","안민천선#1 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-04-05 07:00","2024-04-06 18:00","2024-04-05 07:00","2024-04-06 18:00","매일"]
[648,"경남","직할","안민천선#2 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-04-02 07:00","2024-04-03 18:00","2024-04-02 07:00","2024-04-03 18:00","매일"]
[649,"경남","진주","중리가야#2 T/L","154kV 중리-가야#1T/L 추락방지장치 설치공사 안전거리 확보","154kV 중리-가야#1T/L 추락방지장치 설치공사 안전거리 확보(작업 및 접지 없음)","2024-04-06 07:00","2024-04-07 18:00","2024-04-06 07:00","2024-04-07 18:00","매일"]
[650,"경남","진주","중리가야#1 T/L","154kV 중리-가야#1T/L 추락방지장치 설치공사","154kV 중리-가야#1T/L 추락방지장치 설치공사(수평 및 중간클램프 개선)","2024-04-06 07:00","2024-04-09 18:00","2024-04-06 07:00","2024-04-09 18:00","매일"]
[651,"경남","진주","가야사봉#1 T/L","154kV 가야-사봉 #1,2 T/L 철탑 추락방지장치 설치","154kV 가야-사봉 #1,2 T/L 철탑 수평 추락방지장치 설치공사 (매일) - 수평 추락방지장치 설치 : No.14~43, 50 (31기) - 평일작업 실시, 주말작업 X","2024-04-25 07:30","2024-04-26 18:00","2024-04-25 07:30","2024-04-26 18:00","매일"]
[652,"경남","진주","가야사봉#2 T/L","154kV 가야-사봉 #1,2 T/L 철탑 추락방지장치 설치","154kV 가야-사봉 #1,2 T/L 철탑 수평 추락방지장치 설치공사 (매일) - 수평 추락방지장치 설치 : No.14~43, 50 (31기) - 평일작업 실시, 주말작업 X","2024-04-29 07:30","2024-05-01 18:00","2024-04-29 07:30","2024-05-01 18:00","매일"]
[653,"경남","진주","사봉개양#2 T/L","사봉S/S 154kV 사봉-개양#2T/L GIS 보통점검","사봉S/S 154kV 사봉-개양#2T/L GIS 보통점검","2024-04-05 14:00","2024-04-05 17:00","2024-04-05 14:00","2024-04-05 17:00","연속"]
[654,"경남","진주","사봉개양#1 T/L","사봉S/S 154kV 사봉-개양#1T/L GIS 보통점검","사봉S/S 154kV 사봉-개양#1T/L GIS 보통점검","2024-04-05 10:00","2024-04-05 14:00","2024-04-05 10:00","2024-04-05 14:00","연속"]
[655,"경남","진주","사천개양#1 T/L","154kV 사천-개양 #1T/L 철탑 추락방지장치 설치","154kV 사천-개양 #1T/L 철탑 수평 추락방지장치 설치공사 (매일) - 수평 추락방지장치 설치 : No.7~86 (80기) - 74~86호 수평배열로 인한 4월 20일 #1, 2T/L 동시휴전 예정","2024-04-23 07:30","2024-04-26 18:00","2024-04-23 07:30","2024-04-26 18:00","매일"]
[656,"경남","진주","의령산청 T/L","154kV 의령-산청 T/L 철탑 추락방지장치 설치","154kV 의령-산청 T/L 철탑 수평 추락방지장치 설치공사 (매일) - 수평 추락방지장치 설치 : No.8~64, 1~17(74기) - 평일 휴전작업 실시, 주말작업 X","2024-04-22 07:30","2024-04-23 18:00","취소","취소","매일"]
[657,"경남","진주","의령산청 T/L","154kV 의령-산청 T/L 철탑 추락방지장치 설치","154kV 의령-산청 T/L 철탑 수평 추락방지장치 설치공사 (매일) - 수평 추락방지장치 설치 : No.8~64, 1~17(74기) - 평일 휴전작업 실시, 주말작업 X","2024-04-17 07:30","2024-04-19 18:00","취소","취소","매일"]
[658,"경남","진주","산청함양 T/L","154kV 산청-함양 T/L 철탑 추락방지장치 설치","154kV 산청-함양 T/L 철탑 수평 추락방지장치 설치공사 (매일) - 수평 추락방지장치 설치 : No.64~132, 1~17 (86기) - 평일작업 실시, 주말 휴전 작업 X","2024-04-29 07:30","2024-04-30 18:00","2024-04-02 07:30","2024-04-08 18:00","매일"]
[659,"경남","진주","산청함양 T/L","154kV 산청-함양 T/L 철탑 추락방지장치 설치","154kV 산청-함양 T/L 철탑 수평 추락방지장치 설치공사 (매일) - 수평 추락방지장치 설치 : No.64~132, 1~17 (86기) - 평일작업 실시, 주말 휴전 작업 X","2024-04-24 07:30","2024-04-26 18:00","취소","취소","매일"]
[660,"경남","진주","의령동진주#1 T/L","의령S/S 154kV 의령-동진주#1T/L GIS 보통점검 등","의령S/S 154kV 의령-동진주#1T/L GIS 보통점검 [병행] LA(A, B, C), PT(A) 보통점검","2024-04-04 10:00","2024-04-04 17:00","2024-04-04 10:00","2024-04-04 17:00","연속"]
[661,"경남","진주","의령함양 T/L","154kV 의령-함양 T/L 철탑 추락방지장치 설치","154kV 의령-함양 T/L 철탑 수평 추락방지장치 설치공사 (매일) - 수평 추락방지장치 설치 : No.8~132 (125기) - 평일휴전작업 실시, 주말 휴전작업 X, 선거일 작업 X","2024-04-01 07:30","2024-04-05 18:00","취소","취소","매일"]
[662,"경남","진주","의령함양 T/L","154kV 의령-함양 T/L 철탑 추락방지장치 설치","154kV 의령-함양 T/L 철탑 수평 추락방지장치 설치공사 (매일) - 수평 추락방지장치 설치 : No.8~132 (125기) - 평일휴전작업 실시, 주말 휴전작업 X, 선거일 작업 X","2024-04-08 07:30","2024-04-11 18:00","2024-04-09 07:30","2024-04-16 18:00","매일"]
[663,"경남","진주","쌍림합천#1 T/L","154kV 쌍림-합천#1T/L 피뢰기 설치작업","154kV 쌍림-합천#1T/L 피뢰기 설치작업 - №1, 20, 28, 42, 63, 81(6기)","2024-04-02 07:00","2024-04-04 18:00","2024-04-02 07:00","2024-04-04 18:00","매일"]
[664,"경남","통영","신고성거제#2 T/L","154kV 거류개폐소 건설공사","거류개폐소 GIS 14CCT 설치 - 금회 신고성-거제#2T/L 송전선로 분기 및, 신고성-거류, 거류-거제#2T/L 가압","2024-04-19 18:00","2024-04-22 18:00","2024-04-19 18:00","2024-04-22 18:00","연속"]
[665,"경남","통영","신고성거제#1 T/L","154kV 거류개폐소 건설공사","거류개폐소 GIS 14CCT 설치 - 금회 신고성-거제#1T/L 송전선로 분기 및, 신고성-거류, 거류-거제#1T/L 가압","2024-04-26 18:00","2024-04-29 18:00","2024-04-26 18:00","2024-04-29 18:00","연속"]
[666,"경남","통영","고성통영 T/L","154kV 거류개폐소 건설공사","거류개폐소 GIS 14CCT 설치 - 금회 고성-통영T/L 송전선로 분기 및, 고성-거류, 거류-통영#1T/L 가압","2024-04-06 06:30","2024-04-07 18:00","2024-04-06 06:30","2024-04-07 18:00","연속"]
[667,"경남","통영","신고성통영 T/L","154kV 거류개폐소 건설공사","거류개폐소 GIS 14CCT 설치 - 금회 신고성-통영T/L 송전선로 분기 및, 신고성-거류#3, 거류-통영#2T/L 가압","2024-04-13 06:30","2024-04-14 18:00","2024-04-13 06:30","2024-04-14 18:00","연속"]
[668,"경남","통영","고성통영CC#1 T/L","154kV 거류개폐소 건설공사","거류개폐소 GIS 14CCT 설치 - 금회 신고성-거제#1T/L 송전선로 분기 및, 신고성-거류, 거류-거제#1T/L 가압","2024-04-26 18:00","2024-04-29 18:00","2024-04-26 18:00","2024-04-29 18:00","연속"]
[669,"경남","통영","고성통영CC#2 T/L","154kV 거류개폐소 건설공사","거류개폐소 GIS 14CCT 설치 - 금회 신고성-거제#2T/L 송전선로 분기 및, 신고성-거류, 거류-거제#2T/L 가압","2024-04-19 18:00","2024-04-22 18:00","2024-04-19 18:00","2024-04-22 18:00","연속"]
[670,"경남","함안","매리김해#2 T/L","154kV 마천-진해T/L 등 16개 T/L 추락방지장치 설치","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-04-27 07:00","2024-04-28 18:00","취소","취소","매일"]
[671,"경남","함안","매리김해#1 T/L","154kV 마천-진해T/L 등 16개 T/L 추락방지장치 설치","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-04-13 07:00","2024-04-14 18:00","취소","취소","매일"]
[672,"경남","함안","매리김해#2 T/L","154kV 마천-진해T/L 등 16개 T/L 추락방지장치 설치","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-04-14 07:00","2024-04-14 18:00","취소","취소","연속"]
[673,"경남","함안","매리김해#1 T/L","154kV 마천-진해T/L 등 16개 T/L 추락방지장치 설치","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-04-20 07:00","2024-04-21 18:00","취소","취소","매일"]
[674,"경남","함안","매리김해#2 T/L","154kV 마천-진해T/L 등 16개 T/L 추락방지장치 설치","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-04-20 07:00","2024-04-21 18:00","취소","취소","매일"]
[675,"경남","함안","매리김해#1 T/L","154kV 마천-진해T/L 등 16개 T/L 추락방지장치 설치","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-04-27 07:00","2024-04-28 18:00","취소","취소","매일"]
[676,"경남","함안","한림정삼계#2 T/L","삼계S/S 154kV 한림정-삼계#2T/L GIS LID 이설","삼계S/S 154kV 한림정-삼계#2T/L GIS LID 이설","2024-04-06 09:30","2024-04-07 17:30","2024-04-06 09:30","2024-04-07 17:30","연속"]
[677,"경남","함안","진영수산#1 T/L","수산S/S 154kV 진영-수산#1T/L GIS 보통점검","수산S/S 154kV 진영-수산#1T/L GIS 보통점검","2024-04-16 09:30","2024-04-16 17:30","2024-04-16 09:30","2024-04-16 17:30","연속"]
[678,"경남","함안","진영수산#2 T/L","수산S/S 154kV 진영-수산#2T/L GIS 보통점검","수산S/S 154kV 진영-수산#2T/L GIS 보통점검","2024-04-18 09:30","2024-04-18 17:30","2024-04-18 09:30","2024-04-18 17:30","연속"]
[679,"경남","함안","신마산칠서#1 T/L","신마산S/S 154kV 신마산-칠서#1T/L GCB 조작시험","신마산S/S 154kV 신마산-칠서#1T/L GCB 조작시험","2024-04-30 09:30","2024-04-30 17:30","2024-04-30 09:30","2024-04-30 17:30","연속"]
[680,"경남","함안","신마산서마산#1 T/L","154kV 신마산-중리#1,2T/L 용량증대 전선교체공사 안전이격거리확보","용량증대 전선교체공사 ACSR330SQ-ASCC/TW430SQ (신마산S/T~9호) 안전확보","2024-04-11 07:00","2024-04-19 18:00","2024-04-11 07:00","2024-04-19 18:00","연속"]
[681,"경남","함안","신마산중리#2 T/L","154kV 신마산-중리#2T/L 용량증대 전선교체공사","용량증대 전선교체공사 ACSR330SQ-ASCC/TW430SQ (신마산S/T~9호)","2024-04-11 07:00","2024-04-19 18:00","2024-04-11 07:00","2024-04-19 18:00","연속"]
[682,"경남","함안","신마산중리#1 T/L","154kV 신마산-중리#1T/L 용량증대 전선교체공사","용량증대 전선교체공사 ACSR330SQ-ASCC/TW430SQ (신마산S/T~9호)","2024-04-11 07:00","2024-04-19 18:00","2024-04-11 07:00","2024-04-19 18:00","연속"]
[683,"경남","함안","진례진영#1 T/L","154kV 진례-진영#1T/L 추락방지장치 설치공사","154kV 진례-진영#1T/L 추락방지장치 설치공사(345kV 신마산-신김해T/L 병가개소)","2024-04-26 07:00","2024-04-26 12:00","2024-04-26 07:00","2024-04-26 12:00","매일"]
[684,"경남","함안","진례진영#2 T/L","154kV 진례-진영#2T/L 추락방지장치 설치공사","154kV 진례-진영#2T/L 추락방지장치 설치공사(345kV 신마산-신김해T/L 병가개소)","2024-04-26 12:00","2024-04-26 18:00","2024-04-26 12:00","2024-04-26 18:00","매일"]
[685,"경남","함안","한림정삼계#1 T/L","154kV 한림정-삼계#2T/L 추락방지장치 설치공사","154kV 한림정-삼계#2T/L 수평형 추락방지장치 및 중간클램프 개선","2024-04-11 07:00","2024-04-12 18:00","2024-04-11 07:00","2024-04-12 18:00","매일"]
[686,"남서울",null,"풍납석촌#1 T/L","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS x 5CCT 교체 - 기타부대공사","2024-04-19 17:00","2024-04-19 18:00","2024-04-19 17:00","2024-04-19 18:00","연속"]