{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":12,"n_cols":11,"rows_kept":12,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2024년도 6월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"충북","직할","신중부S/S #5 M.Tr","신중부S/S 345kV GIS 콘덴서 절연열화 진단","송운(변전)-1076(’23. 9.25)「345kV GIS(콘덴서) 고장예방 및 최적화 운전방안 알림」관련 신중부S/S 345kV GIS 콘덴서 절연열화 진단","2024-06-18 13:00","2024-06-18 15:00","2024-06-18 13:00","2024-06-18 15:00","연속"]
[2,"충북","직할","신중부S/S #4 M.Tr","신중부S/S 345kV GIS 콘덴서 절연열화 진단","송운(변전)-1076(’23. 9.25)「345kV GIS(콘덴서) 고장예방 및 최적화 운전방안 알림」관련 신중부S/S 345kV GIS 콘덴서 절연열화 진단","2024-06-18 08:00","2024-06-18 10:00","2024-06-18 08:00","2024-06-18 10:00","연속"]
[3,"대전세종충남","서산","당진T/P CB 8971","24년 서산P/O 765kV GIS 보통점검공사","(즉시가압 가능) 당진화력S/S 765kV 8971 CB 보통점검","2024-06-04 09:30","2024-06-04 18:00","2024-06-04 09:30","2024-06-04 18:00","연속"]
[4,"대전세종충남","서산","신서산S/S CB 8500","24년 서산P/O 765kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 765kV 8500 CB 보통점검","2024-06-04 09:30","2024-06-05 18:00","2024-06-04 09:30","2024-06-05 18:00","연속"]
[5,"대전세종충남","서산","신서산S/S CB 8572","24년 서산P/O 765kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 765kV 8572 CB 보통점검","2024-06-12 09:30","2024-06-13 18:00","2024-06-12 09:30","2024-06-13 18:00","연속"]
[6,"대전세종충남","서산","신서산신중부#2 T/L","[5월 취소시] 23~24년 천안전력지사 가공송전 협력회사 총액공사","[즉시가압가능]765kV 신서산-신중부T/L No. 36~37 항공장애표시구 교체","2024-06-05 07:00","2024-06-05 18:00","취소","취소","연속"]
[7,"경북","영주","신한울N/P #2 Tie-Tr","신한울S/S 765kV #1,2M.Tr 보통점검 공사","신한울S/S 765kV #2M.Tr 보통점검 공사","2024-06-17 09:00","2024-06-21 18:00","2024-06-17 09:00","2024-06-21 18:00","연속"]
[8,"경북","영주","신한울N/P #1 Tie-Tr","신한울S/S 765kV #1,2M.Tr 보통점검 공사","신한울S/S 765kV #1M.Tr 보통점검 공사","2024-06-10 09:00","2024-06-14 18:00","2024-06-10 09:00","2024-06-14 18:00","연속"]

{"sheet":"345설비","index":1,"n_rows":405,"n_cols":11,"rows_kept":405,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2024년도 6월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","미금성동#2 T/L","2024~25년 성동전력지사 변전협력회사 공사","- B/F PNL 대체","2024-06-10 10:00","2024-06-13 18:00","취소","취소","연속"]
[2,"서울","성동","성동S/S #2 M.Tr","2024~25년 성동전력지사 변전협력회사 공사","B/F PNL 대체","2024-06-10 10:00","2024-06-13 18:00","취소","취소","연속"]
[3,"서울","중부","중부S/S #3 M.Tr","중부S/S 154kV 장기사용 GIS 교체공사(2차)","- 154kV GIS 교체 시험가압용","2024-06-12 17:00","2024-06-13 13:00","2024-06-13 17:00","2024-06-14 09:00","연속"]
[4,"서울","중부","중부S/S #3 M.Tr","중부S/S 154kV 장기사용 GIS 교체공사(2차)","- 154kV GIS 교체 시험가압용","2024-06-28 15:00","2024-06-28 18:00","취소","취소","연속"]
[5,"서울","중부","중부S/S #3 M.Tr","중부S/S 154kV 장기사용 GIS 교체공사(2차)","- 154kV GIS 교체 시험가압용","2024-06-27 17:00","2024-06-28 14:00","2024-06-28 15:00","2024-06-29 18:00","연속"]
[6,"남서울","동서울","동서울S/S #6 M.Tr","345kV 동서울S/S 종합정비공사","○ 500kV 동서울변환소 및 옥내화부지 확보관련 사전정비공사 - 23kV Sh.R 이설 관련 주변압기 휴전 - 기타 부대작업 1식","2024-06-03 09:00","2024-06-07 18:00","2024-06-03 09:00","2024-06-07 18:00","연속"]
[7,"남서울","강남","신양재S/S #3 M.Tr","24-25년도 강남전력지사 변전협력회사 총액공사","주)345kV GIS 조작시험(7300TIE, #3M.Tr 1,2차) 병행)345kV 73Bay 휴전","2024-06-03 10:00","2024-06-04 18:00","2024-06-03 10:00","2024-06-04 18:00","연속"]
[8,"남서울","영등포","서서울신광명#1 T/L","345kV 신광명S/S 용량증대 구내 전력구공사","345kV 신광명S/S 차단기 고장전류 초과에 따른 차단용량 증대 및 SW 증설을 위한 변전소 구내 전력구공사","2024-06-10 08:00","2024-06-15 17:00","2024-06-10 08:00","2024-06-15 17:00","연속"]
[9,"남서울","동서울","신성남동서울#1 T/L","345kV 동서울S/S 종합정비공사","○ 500kV 동서울변환소 및 옥내화부지 확보관련 사전정비공사 - 345kV GIS 제어케이블 이설 - 기타 부대작업 1식","2024-06-10 09:00","2024-07-05 18:00","2024-06-10 09:00","2024-07-05 18:00","연속"]
[10,"남서울","동서울","동서울S/S #1 Sh.R CB","345kV 동서울S/S 종합정비공사","○ 500kV 동서울변환소 및 옥내화부지 확보관련 사전정비공사 - 345kV Sh.R, GIS 제어케이블 이설관련 송전선로 휴전 - 기타 부대작업 1식","2024-06-10 09:00","2024-07-05 18:00","2024-06-10 09:00","2024-07-05 18:00","연속"]
[11,"남서울","영등포","서서울신광명#2 T/L","345kV 신광명S/S 용량증대 구내 전력구공사","345kV 신광명S/S 차단기 고장전류 초과에 따른 차단용량 증대 및 SW 증설을 위한 변전소 구내 전력구공사","2024-06-17 08:00","2024-06-22 17:00","2024-06-17 08:00","2024-06-22 17:00","연속"]
[12,"남서울","강남","신양재S/S #1 Sh.R CB","24-25년도 강남전력지사 변전협력회사 총액공사","주)345kV GIS 조작시험(신양재S/S 345kV #1Sh.R) 병행)345kV 71Bay 휴전","2024-06-25 10:00","2024-06-26 18:00","취소","취소","연속"]
[13,"남서울","강남","신양재S/S #1 M.Tr","24-25년도 강남전력지사 변전협력회사 총액공사","주)345kV GIS 조작시험(7100TIE, #1M.Tr 1,2차) 병행)345kV 71Bay 휴전","2024-06-25 10:00","2024-06-26 18:00","2024-06-25 10:00","2024-06-26 18:00","연속"]
[14,"남서울","영등포","서서울신광명#1 T/L","신광명S/S GIS 용량대체공사","- 345kV 63kA GIS 27CB 설치 - 기타 부대공사","2024-06-26 09:00","2024-06-27 18:00","2024-06-26 09:00","2024-06-27 18:00","연속"]
[15,"인천","김포","신김포S/S #4 Sh.R CB","신김포S/S 345kV #4 Sh.R 1차 GIS(7272) 보통점검","신김포S/S 345kV #4 Sh.R 1차 GIS(7272) 보통점검","2024-06-07 09:00","2024-06-07 18:00","2024-06-07 09:00","2024-06-07 18:00","연속"]
[16,"인천","김포","신김포S/S #3 Sh.R CB","신김포S/S 345kV #3 Sh.R 1차 GIS(7671) 보통점검","신김포S/S 345kV #3 Sh.R 1차 GIS(7671) 보통점검","2024-06-05 09:00","2024-06-05 18:00","2024-06-05 09:00","2024-06-05 18:00","연속"]
[17,"인천","김포","신김포S/S #2 Sh.R CB","신김포S/S 345kV #2 Sh.R 1차 GIS(7271) 보통점검","신김포S/S 345kV #2 Sh.R 1차 GIS(7271) 보통점검","2024-06-04 09:00","2024-06-04 18:00","2024-06-04 09:00","2024-06-04 18:00","연속"]
[18,"인천","김포","신김포S/S #1 Sh.R CB","신김포S/S 345kV #1 Sh.R 보통점검","신김포S/S 345kV #1 Sh.R 보통점검","2024-06-03 09:00","2024-06-03 18:00","2024-06-03 09:00","2024-06-03 18:00","연속"]
[19,"인천","부평","서인천C/C #3 Sh.R CB","서인천C/C 345kV #3 Sh.R 보통점검","서인천C/C 345kV #3 Sh.R 보통점검","2024-06-20 09:00","2024-06-21 18:00","취소","취소","연속"]
[20,"인천","부평","신가좌S/S #3 M.Tr","신가좌S/S #3M.Tr 2차 GIS(6344) 정밀점검","신가좌S/S #3M.Tr 2차 GIS(6344) 정밀점검","2024-06-03 09:00","2024-06-05 18:00","2024-06-03 09:00","2024-06-05 18:00","연속"]
[21,"인천","부평","신가좌S/S #4 M.Tr","신가좌S/S 345kV #4 M.Tr 보호반대체 공사 등","신가좌S/S 345kV #4M.Tr 보호반대체 공사","2024-06-17 09:00","2024-06-21 18:00","2024-06-17 09:00","2024-06-21 18:00","연속"]
[22,"인천","부평","신가좌S/S #1 M.Tr","신가좌S/S 345kV #1 M.Tr 보호반대체 공사 등 정기검사","신가좌S/S 345kV #1M.Tr 보호반대체 공사","2024-06-10 09:00","2024-06-14 18:00","2024-06-10 09:00","2024-06-14 18:00","연속"]
[23,"인천","부평","신경서S/S #1 M.Tr","신경서S/S 345kV #1 M.Tr 보통점검 외 하위설비 정기검사","신경서S/S 345kV #1 M.Tr 보통점검 외 하위설비 정기검사","2024-06-24 09:00","2024-06-26 18:00","2024-06-24 09:00","2024-06-26 18:00","연속"]
[24,"인천","부평","신김포신인천CC T/L","신인천S/Y 신김포신인천CC T/L 보호반 대체공사","신인천S/Y 신김포신인천CC T/L 보호반 대체공사","2024-06-03 09:00","2024-06-07 18:00","2024-06-03 09:00","2024-06-07 18:00","연속"]
[25,"인천","부평","신인천C/C SEC CB 75760","신인천C/C 345kV #75-#76 SEC GIS 절연열화 측정","신인천C/C 345kV #75-#76 SEC GIS 절연열화 측정","2024-06-01 09:00","2024-06-01 12:00","2024-06-01 09:00","2024-06-01 12:00","연속"]
[26,"인천","부평","신인천C/C SEC CB 76770","신인천C/C 345kV #76-#77 SEC GIS 절연열화 측정","신인천C/C 345kV #76-#77 SEC GIS 절연열화 측정","2024-06-01 13:00","2024-06-01 18:00","2024-06-01 13:00","2024-06-01 18:00","연속"]
[27,"인천","부평","인천C/C CB 7C72","인천CC S/Y 345kV 7C72GIS 절연열화 측정","인천CC S/Y 345kV 7C72GIS 절연열화 측정","2024-06-19 15:00","2024-06-19 18:00","2024-06-19 15:00","2024-06-19 18:00","연속"]
[28,"인천","부평","인천C/C #70 BUS","인천CC S/Y 345kV 7251DS PD 발생 관련 내부 보수","인천CC S/Y 345kV 7251DS PD 발생 관련 GIS 내부 보수","2024-06-08 09:00","2024-06-09 18:00","2024-06-08 09:00","2024-06-09 18:00","연속"]
[29,"인천","부평","인천C/C CB 7C00","인천CC S/Y 345kV 7C00GIS 절연열화 측정","인천CC S/Y 345kV 7C00GIS 절연열화 측정","2024-06-19 09:00","2024-06-19 12:00","2024-06-19 09:00","2024-06-19 12:00","연속"]
[30,"인천","부평","인천C/C CB 7B72","인천CC S/Y 345kV 7B72GIS 절연열화 측정","인천CC S/Y 345kV 7B72GIS 절연열화 측정","2024-06-18 12:00","2024-06-18 18:00","2024-06-18 12:00","2024-06-18 18:00","연속"]
[31,"인천","부평","인천C/C CB 7B71","인천CC S/Y 345kV 7B71GIS 절연열화 측정","인천CC S/Y 345kV 7B71GIS 절연열화 측정","2024-06-18 09:00","2024-06-18 12:00","2024-06-18 09:00","2024-06-18 12:00","연속"]
[32,"인천","부평","인천C/C CB 7B00","인천CC S/Y 345kV 7B00GIS 절연열화 측정","인천CC S/Y 345kV 7B00GIS 절연열화 측정","2024-06-17 12:00","2024-06-17 18:00","2024-06-17 12:00","2024-06-17 18:00","연속"]
[33,"인천","부평","인천C/C CB 7A72","인천CC S/Y 345kV 7A72GIS 절연열화 측정","인천CC S/Y 345kV 7A72GIS 절연열화 측정","2024-06-17 09:00","2024-06-17 12:00","2024-06-17 09:00","2024-06-17 12:00","연속"]
[34,"인천","부평","인천C/C CB 7472","인천CC 362kV 7472GIS 절연열화 측정","인천CC 362kV 7472GIS 절연열화 측정","2024-06-15 12:00","2024-06-15 18:00","2024-06-15 12:00","2024-06-15 18:00","연속"]
[35,"인천","부평","인천C/C CB 7400","인천CC 362kV 7400 TIE-GIS 절연열화 측정","인천CC 362kV 7400 TIE-GIS 절연열화 측정","2024-06-15 09:00","2024-06-15 12:00","2024-06-15 09:00","2024-06-15 12:00","연속"]
[36,"인천","부평","인천C/C CB 7A71","인천CC S/Y 345kV 7A71GIS 절연열화 측정","인천CC S/Y 345kV 7A71GIS 절연열화 측정","2024-06-14 12:00","2024-06-14 18:00","2024-06-14 12:00","2024-06-14 18:00","연속"]
[37,"인천","부평","인천C/C CB 7A00","인천CC S/Y 345kV 7A00GIS 절연열화 측정","인천CC S/Y 345kV 7A00GIS 절연열화 측정","2024-06-14 09:00","2024-06-14 12:00","2024-06-14 09:00","2024-06-14 12:00","연속"]
[38,"인천","부평","인천C/C SEC CB 75760","인천CC S/Y 345kV #75-#76 SEC GIS 절연열화 측정","인천CC S/Y 345kV #75-#76 SEC GIS 절연열화 측정","2024-06-13 12:00","2024-06-13 18:00","2024-06-13 12:00","2024-06-13 18:00","연속"]
[39,"인천","부평","인천C/C SEC CB 70710","인천CC S/Y 345kV #70-#71 SEC GIS 절연열화 측정","인천CC S/Y 345kV #70-#71 SEC GIS 절연열화 측정","2024-06-13 09:00","2024-06-13 12:00","2024-06-13 09:00","2024-06-13 12:00","연속"]
[40,"인천","부평","인천C/C CB 7672","인천CC 362kV 7672GIS 절연열화 측정","인천CC 362kV 7672GIS 절연열화 측정","2024-06-12 12:00","2024-06-12 18:00","2024-06-12 12:00","2024-06-12 18:00","연속"]
[41,"인천","부평","인천C/C CB 7671","인천CC 362kV 7671GIS 절연열화 측정","인천CC 362kV 7671GIS 절연열화 측정","2024-06-12 09:00","2024-06-12 12:00","2024-06-12 09:00","2024-06-12 12:00","연속"]
[42,"인천","부평","인천C/C CB 7600","인천CC 362kV 7600GIS 절연열화 측정","인천CC 362kV 7600GIS 절연열화 측정","2024-06-11 12:00","2024-06-11 18:00","2024-06-11 12:00","2024-06-11 18:00","연속"]
[43,"인천","부평","인천C/C CB 7572","인천CC 362kV 7572GIS 절연열화 측정","인천CC 362kV 7572GIS 절연열화 측정","2024-06-11 09:00","2024-06-11 12:00","2024-06-11 09:00","2024-06-11 12:00","연속"]
[44,"인천","부평","인천C/C CB 7571","인천CC 362kV 7571GIS 절연열화 측정","인천CC 362kV 7571GIS 절연열화 측정","2024-06-10 12:00","2024-06-10 18:00","2024-06-10 12:00","2024-06-10 18:00","연속"]
[45,"인천","부평","인천C/C CB 7500","인천CC 362kV 7500GIS 절연열화 측정","인천CC 362kV 7500GIS 절연열화 측정","2024-06-10 09:00","2024-06-10 12:00","2024-06-10 09:00","2024-06-10 12:00","연속"]
[46,"인천","부평","인천C/C CB 7C71","인천CC S/Y 345kV 7C71GIS 절연열화 측정","인천CC S/Y 345kV 7C71GIS 절연열화 측정","2024-06-19 12:00","2024-06-19 15:00","2024-06-19 12:00","2024-06-19 15:00","연속"]
[47,"인천","시흥","신시화S/S #2 M.Tr","신시화S/S 345kV M.Tr 2차측 170kV 단상 GIB 교체공사","345kV #2M.Tr 2차측 170kV 단상 GIB 교체","2024-06-06 09:00","2024-06-15 18:00","2024-06-06 09:00","2024-06-15 18:00","연속"]
[48,"인천","시흥","신시화S/S #3 M.Tr","신시화S/S 345kV M.Tr 2차측 170kV 단상 GIB 교체공사","345kV #3M.Tr 2차측 170kV 단상 GIB 교체","2024-06-16 09:00","2024-06-25 18:00","2024-06-16 09:00","2024-06-25 18:00","연속"]
[49,"인천","시흥","신시흥#1S/S CB 7900","신시흥S/S 345kV 7900 CB 균압콘덴서 절연열화 측정","신시흥S/S 345kV 7900 CB 균압콘덴서 절연열화 측정","2024-06-13 12:00","2024-06-13 15:00","2024-06-13 12:00","2024-06-13 15:00","연속"]
[50,"인천","시흥","신시흥#1S/S CB 7971","신시흥S/S 345kV 7971 CB 균압콘덴서 절연열화 측정","신시흥S/S 345kV 7971 CB 균압콘덴서 절연열화 측정","2024-06-13 09:00","2024-06-13 12:00","2024-06-13 09:00","2024-06-13 12:00","연속"]
[51,"인천","시흥","신시흥#1S/S CB 7C00","신시흥S/S 345kV 7C00 CB 균압콘덴서 절연열화 측정","신시흥S/S 345kV 7C00 CB 균압콘덴서 절연열화 측정","2024-06-11 15:00","2024-06-11 18:00","2024-06-11 15:00","2024-06-11 18:00","연속"]
[52,"인천","시흥","신시흥#1S/S CB 7C71","신시흥S/S 345kV 7C71 CB 균압콘덴서 절연열화 측정","신시흥S/S 345kV 7C71 CB 균압콘덴서 절연열화 측정","2024-06-11 09:00","2024-06-11 15:00","2024-06-11 09:00","2024-06-11 15:00","연속"]
[53,"인천","시흥","신시흥#1S/S CB 7B72","신시흥S/S 345kV 7B72 CB 균압콘덴서 절연열화 측정","신시흥S/S 345kV 7B72 CB 균압콘덴서 절연열화 측정","2024-06-10 15:00","2024-06-10 18:00","취소","취소","연속"]
[54,"인천","시흥","신시흥#1S/S CB 7B00","신시흥S/S 345kV 7B00 CB 균압콘덴서 절연열화 측정","신시흥S/S 345kV 7B00 CB 균압콘덴서 절연열화 측정","2024-06-10 12:00","2024-06-10 15:00","취소","취소","연속"]
[55,"인천","시흥","신시흥#1S/S CB 7B71","신시흥S/S 345kV 7B71 CB 균압콘덴서 절연열화 측정","신시흥S/S 345kV 7B71 CB 균압콘덴서 절연열화 측정","2024-06-10 09:00","2024-06-10 12:00","취소","취소","연속"]
[56,"인천","시흥","신시흥#1S/S CB 7871","신시흥S/S 345kV 7871 CB 균압콘덴서 절연열화측정","신시흥S/S 345kV 7871 CB 균압콘덴서 절연열화측정","2024-06-12 09:00","2024-06-12 12:00","취소","취소","연속"]
[57,"인천","시흥","신시흥#1S/S CB 7872","신시흥S/S 345kV 7872 CB 균압콘덴서 절연열화측정","신시흥S/S 345kV 7872 CB 균압콘덴서 절연열화측정","2024-06-12 15:00","2024-06-12 18:00","취소","취소","연속"]
[58,"인천","시흥","신시흥#1S/S CB 7A72","신시흥S/S 345kV 7A72 CB 균압콘덴서 절연열화측정","신시흥S/S 345kV 7A72 CB 균압콘덴서 절연열화측정","2024-06-13 09:00","2024-06-13 18:00","취소","취소","연속"]
[59,"인천","시흥","신시흥#1S/S CB 7771","신시흥S/S 345kV 7771 CB 균압콘덴서 절연열화측정","신시흥S/S 345kV 7771 CB 균압콘덴서 절연열화측정","2024-06-14 09:00","2024-06-14 14:00","2024-06-14 09:00","2024-06-14 14:00","연속"]
[60,"인천","시흥","신시흥#1S/S CB 7700","신시흥S/S 345kV 7700 CB 균압콘덴서 절연열화측정","신시흥S/S 345kV 7700 CB 균압콘덴서 절연열화측정","2024-06-14 14:00","2024-06-14 18:00","2024-06-14 14:00","2024-06-14 18:00","연속"]
[61,"인천","시흥","신시흥#1S/S CB 7800","신시흥S/S 345kV 7800 CB 균압콘덴서 절연열화측정","신시흥S/S 345kV 7800 CB 균압콘덴서 절연열화측정","2024-06-12 12:00","2024-06-12 15:00","취소","취소","연속"]
[62,"인천","시흥","신시흥#2S/S CB 7500","신시흥S/S 345kV 7500 CB 균압콘덴서 절연열화 측정","신시흥S/S 345kV 7500 CB 균압콘덴서 절연열화 측정","2024-06-17 15:00","2024-06-17 18:00","2024-06-17 15:00","2024-06-17 18:00","연속"]
[63,"인천","시흥","신시흥#2S/S CB 7672","신시흥S/S 345kV 7672 CB 균압콘덴서 절연열화 측정","신시흥S/S 345kV 7672 CB 균압콘덴서 절연열화 측정","2024-06-17 12:00","2024-06-17 15:00","2024-06-17 12:00","2024-06-17 15:00","연속"]
[64,"인천","시흥","신시흥#2S/S CB 7600","신시흥S/S 345kV 7600 CB 균압콘덴서 절연열화 측정","신시흥S/S 345kV 7600 CB 균압콘덴서 절연열화 측정","2024-06-17 09:00","2024-06-17 12:00","취소","취소","연속"]
[65,"인천","시흥","신시흥#2S/S CB 7172","신시흥S/S 345kV 7172 CB 균압콘덴서 절연열화측정","신시흥S/S 345kV 7172 CB 균압콘덴서 절연열화측정","2024-06-19 14:00","2024-06-19 18:00","2024-06-19 14:00","2024-06-19 18:00","연속"]
[66,"인천","시흥","신시흥#2S/S CB 7400","신시흥S/S 345kV 7400 CB 균압콘덴서 절연열화측정","신시흥S/S 345kV 7400 CB 균압콘덴서 절연열화측정","2024-06-18 09:00","2024-06-18 12:00","2024-06-18 09:00","2024-06-18 12:00","연속"]
[67,"인천","시흥","신시흥#2S/S CB 7372","신시흥S/S 345kV 7372 CB 균압콘덴서 절연열화측정","신시흥S/S 345kV 7372 CB 균압콘덴서 절연열화측정","2024-06-18 15:00","2024-06-18 18:00","2024-06-18 15:00","2024-06-18 18:00","연속"]
[68,"인천","시흥","신시흥#2S/S CB 7200","신시흥S/S 345kV 7200 CB 균압콘덴서 절연열화측정","신시흥S/S 345kV 7200 CB 균압콘덴서 절연열화측정","2024-06-19 09:00","2024-06-19 14:00","2024-06-19 09:00","2024-06-19 14:00","연속"]
[69,"인천","시흥","신시흥#2S/S CB 7300","신시흥S/S 345kV 7300 CB 균압콘덴서 절연열화측정","신시흥S/S 345kV 7300 CB 균압콘덴서 절연열화측정","2024-06-18 12:00","2024-06-18 15:00","취소","취소","연속"]
[70,"인천","시흥","영흥T/P CB 7671","영흥#2S/Y 345kV 7671 CB 균압콘덴서 절연열화 측정","영흥#2S/Y 345kV 7671 CB 균압콘덴서 절연열화 측정","2024-06-04 09:00","2024-06-04 12:00","2024-06-04 09:00","2024-06-04 12:00","연속"]
[71,"인천","시흥","영흥T/P CB 7871","영흥#2S/Y 345kV 7871 CB 균압콘덴서 절연열화 측정","영흥#2S/Y 345kV 7871 CB 균압콘덴서 절연열화 측정","2024-06-03 09:00","2024-06-03 12:00","취소","취소","연속"]
[72,"인천","시흥","영흥T/P CB 7800","영흥#2S/Y 345kV 7800 CB 균압콘덴서 절연열화 측정","영흥#2S/Y 345kV 7800 CB 균압콘덴서 절연열화 측정","2024-06-03 12:00","2024-06-03 15:00","취소","취소","연속"]
[73,"인천","시흥","영흥T/P CB 7772","영흥#2S/Y 345kV 7772 CB 균압콘덴서 절연열화 측정","영흥#2S/Y 345kV 7772 CB 균압콘덴서 절연열화 측정","2024-06-03 15:00","2024-06-03 18:00","취소","취소","연속"]
[74,"인천","시흥","영흥T/P CB 7600","영흥#2S/Y 345kV 7600 CB 균압콘덴서 절연열화 측정","영흥#2S/Y 345kV 7600 CB 균압콘덴서 절연열화 측정","2024-06-04 12:00","2024-06-04 15:00","2024-06-04 12:00","2024-06-04 15:00","연속"]
[75,"인천","시흥","영흥T/P CB 7672","영흥#2S/Y 345kV 7672 CB 균압콘덴서 절연열화 측정","영흥#2S/Y 345kV 7672 CB 균압콘덴서 절연열화 측정","2024-06-04 15:00","2024-06-04 18:00","2024-06-04 15:00","2024-06-04 18:00","연속"]
[76,"인천","시흥","영흥T/P CB 7300","영흥#1S/Y 345kV 7300 CB 균압콘덴서 절연열화측정","영흥#1S/Y 345kV 7300 CB 균압콘덴서 절연열화측정","2024-06-07 12:00","2024-06-07 15:00","2024-06-07 12:00","2024-06-07 15:00","연속"]
[77,"인천","시흥","영흥T/P CB 7371","영흥#1S/Y 345kV 7371 CB 균압콘덴서 절연열화측정","영흥#1S/Y 345kV 7371 CB 균압콘덴서 절연열화측정","2024-06-07 09:00","2024-06-07 12:00","2024-06-07 09:00","2024-06-07 12:00","연속"]
[78,"인천","시흥","영흥T/P CB 7171","영흥#1S/Y 345kV 7171 CB 균압콘덴서 절연열화 측정","영흥#1S/Y 345kV 7171 CB 균압콘덴서 절연열화 측정","2024-06-20 09:00","2024-06-20 18:00","2024-06-20 09:00","2024-06-20 18:00","연속"]
[79,"인천","시흥","영흥T/P CB 7472","영흥#1S/Y 345kV 7472 CB 균압콘덴서 절연열화 측정","영흥#1S/Y 345kV 7472 CB 균압콘덴서 절연열화 측정","2024-06-05 15:00","2024-06-05 18:00","2024-06-05 15:00","2024-06-05 18:00","연속"]
[80,"인천","시흥","영흥T/P CB 7400","영흥#1S/Y 345kV 7400 CB 균압콘덴서 절연열화 측정","영흥#1S/Y 345kV 7400 CB 균압콘덴서 절연열화 측정","2024-06-05 12:00","2024-06-05 15:00","2024-06-05 12:00","2024-06-05 15:00","연속"]
[81,"인천","시흥","영흥T/P CB 7471","영흥#1S/Y 345kV 7471 CB 균압콘덴서 절연열화 측정","영흥#1S/Y 345kV 7471 CB 균압콘덴서 절연열화 측정","2024-06-05 09:00","2024-06-05 12:00","2024-06-05 09:00","2024-06-05 12:00","연속"]
[82,"인천","시흥","영흥T/P CB 7372","영흥#1S/Y 345kV 7372 CB 균압콘덴서 절연열화측정","영흥#1S/Y 345kV 7372 CB 균압콘덴서 절연열화측정","2024-06-07 15:00","2024-06-07 18:00","2024-06-07 15:00","2024-06-07 18:00","연속"]
[83,"인천","직할","갈산S/S #75 BUS","갈산S/S #4M.Tr 증설공사","갈산S/S #4M.Tr 증설공사 관련 7752 가스밸브 보수작업","2024-06-04 09:00","2024-06-05 13:00","취소","취소","연속"]
[84,"경기북부","고양","신덕은S/S #2 M.Tr","24~25 고양전력 변전부 총액공사","345kV M.Tr 보통점검 (#2M.Tr A,B,C)","2024-06-03 09:00","2024-06-04 18:00","2024-06-03 09:00","2024-06-04 18:00","연속"]
[85,"경기북부","고양","신덕은동두천CC#1 T/L","24~25년 고양전력지사 가공송전협력회사 공사","병가선로 휴전","2024-06-10 07:00","2024-06-14 18:00","2024-06-10 07:00","2024-06-14 18:00","연속"]
[86,"경기북부","고양","신덕은S/S #4 M.Tr","24~25년 고양전력지사 변전협력회사 총액공사","362kV GIS 절연열화 측정(7472,7400 GIS)","2024-06-18 09:00","2024-06-18 18:00","2024-06-18 09:00","2024-06-18 18:00","연속"]
[87,"경기북부","고양","신덕은S/S #3 M.Tr","24~25년 고양전력지사 변전협력회사 총액공사","362kV GIS 절연열화 측정(7371,7300 GIS)","2024-06-10 09:00","2024-06-10 18:00","2024-06-10 09:00","2024-06-10 18:00","연속"]
[88,"경기북부","고양","신파주신덕은#2 T/L","24~25년 고양전력지사 변전협력회사 총액공사","362kV GIS 절연열화 측정(7271,7200 GIS)","2024-06-03 09:00","2024-06-03 18:00","2024-06-03 09:00","2024-06-03 18:00","연속"]
[89,"경기북부","고양","신파주S/S SVC CB","2024년도 신파주S/S 345kV SVC 보통점검공사","2024년도 신파주S/S 345kV SVC 보통점검 - 공사 내용 : TCR, FC, Cooling System, C&P PNL 등 - 공사 기간 : 2024. 6. 10 ~ 2024. 7. 5","2024-06-10 09:00","2024-07-05 18:00","취소","취소","연속"]
[90,"경기북부","고양","신덕은S/S #4 M.Tr","신덕은S/S 154kV 고객선로 SW 증설공사","-170kV GIS 1CCT 설치 - 1DS~CHD 무부하가압","2024-06-13 09:00","2024-06-14 18:00","2024-06-13 09:00","2024-06-14 18:00","연속"]
[91,"경기북부","구리","동서울미금#1 T/L","24~25년 구리전력지사 변전협력회사 공사","동서울미금#1TL CVT초기점검, 7371 차단기 질소충진","2024-06-03 09:00","2024-06-03 18:00","2024-06-03 09:00","2024-06-03 18:00","연속"]
[92,"경기북부","구리","동서울미금#2 T/L","24~25년 경기북부 직할 가공송전협력회사공사","345kV 신의정부-미금#1T/L 추락방지시설 설치 및 지지애자교체공사(병가구간)","2024-06-10 07:00","2024-06-10 18:00","2024-06-10 07:00","2024-06-10 18:00","연속"]
[93,"경기북부","구리","신가평미금#1 T/L","24~25년 구리전력지사 변전협력회사 공사","미금S/S 신가평-미금#1TL CVT하자점검 - 7700, 7772 절연열화 측정","2024-06-17 09:00","2024-06-17 18:00","취소","취소","연속"]
[94,"경기북부","구리","미금S/S #1 BUS Sh.R (CB 7079)","24~25년 구리전력지사 변전협력회사 공사","- 미금S/S 7079조작시험, 7579,7179,7279 절연열화 측정(06.18) - 7279 보통점검 및 절연열화 측정(06.19)","2024-06-18 09:00","2024-06-19 18:00","2024-06-18 09:00","2024-06-19 18:00","매일"]
[95,"경기북부","구리","미금성동#2 T/L","24~25년 구리전력지사 변전협력회사 공사","- 미금S/S 미금-성동#2TL 7271, 7200 조작시험 및 절연열화 측정 - 7379,7479 #3,4Sh.R 차단기 절연열화 측정","2024-06-20 09:00","2024-06-20 14:00","취소","취소","매일"]
[96,"경기북부","구리","미금S/S #3 Sh.R CB","24~25년 구리전력지사 변전협력회사 공사","- 미금S/S 미금-성동#2TL 7271, 7200 조작시험 및 절연열화 측정 - 7379,7479 #3,4Sh.R 차단기 절연열화 측정","2024-06-20 14:00","2024-06-20 16:00","2024-06-20 14:00","2024-06-20 16:00","매일"]
[97,"경기북부","구리","미금S/S #4 Sh.R CB","24~25년 구리전력지사 변전협력회사 공사","- 미금S/S 미금-성동#2TL 7271, 7200 조작시험 및 절연열화 측정 - 7379,7479 #3,4Sh.R 차단기 절연열화 측정","2024-06-20 16:00","2024-06-20 18:00","2024-06-20 16:00","2024-06-20 18:00","매일"]
[98,"경기북부","구리","신가평미금#2 T/L","24~25년 구리전력지사 변전협력회사 공사","신가평-미금#2TL CVT하자점검(06.11) - 신가평S/S 신가평-미금#2T/L 7800,7872 절연열화 측정 - 7871초기점검(06.12) - 7800초기점검(06.13)","2024-06-11 09:00","2024-06-13 18:00","취소","취소","연속"]
[99,"경기북부","구리","신포천S/S CB 7300","24~25년 구리전력지사 변전협력회사 공사","신포천S/S 73BAY 조작시험 - 신포천-포천CC #1T/L 7371 조작시험 - 신포천-포천CC #1T/L - #1Sh.R 1차 GIS 7300 조작시험 - #1Sh.R 1차 GIS 7372 조작시험","2024-06-24 13:00","2024-06-24 15:00","2024-06-24 13:00","2024-06-24 15:00","매일"]
[100,"경기북부","구리","신포천S/S CB 7371","24~25년 구리전력지사 변전협력회사 공사","신포천S/S 73BAY 조작시험 - 신포천-포천CC #1T/L 7371 조작시험 - 신포천-포천CC #1T/L - #1Sh.R 1차 GIS 7300 조작시험 - #1Sh.R 1차 GIS 7372 조작시험","2024-06-24 09:00","2024-06-24 12:00","2024-06-24 09:00","2024-06-24 12:00","매일"]
[101,"경기북부","구리","신포천S/S #1 Sh.R CB","24~25년 구리전력지사 변전협력회사 공사","신포천S/S 73BAY 조작시험 - 신포천-포천CC #1T/L 7371 조작시험 - 신포천-포천CC #1T/L - #1Sh.R 1차 GIS 7300 조작시험 - #1Sh.R 1차 GIS 7372 조작시험","2024-06-24 15:00","2024-06-24 18:00","2024-06-24 15:00","2024-06-24 18:00","매일"]
[102,"경기북부","구리","신포천S/S CB 7372","24~25년 구리전력지사 변전협력회사 공사","신포천S/S 75BAY 조작시험 - 신포천-동두천CC #1T/L 7571 조작시험 - 신포천-동두천CC #1T/L - TIE GIS 7500 조작시험 - 신포천S/S #1Sh.R GIS 7379 조작시험","2024-06-27 15:00","2024-06-27 18:00","2024-06-27 15:00","2024-06-27 18:00","연속"]
[103,"경기북부","구리","신포천S/S CB 7500","24~25년 구리전력지사 변전협력회사 공사","신포천S/S 75BAY 조작시험 - 신포천-동두천CC #1T/L 7571 조작시험 - 신포천-동두천CC #1T/L - TIE GIS 7500 조작시험 - 신포천S/S #1Sh.R GIS 7379 조작시험","2024-06-27 13:00","2024-06-27 15:00","2024-06-27 13:00","2024-06-27 15:00","연속"]
[104,"경기북부","구리","신포천S/S CB 7571","24~25년 구리전력지사 변전협력회사 공사","신포천S/S 75BAY 조작시험 - 신포천-동두천CC #1T/L 7571 조작시험 - 신포천-동두천CC #1T/L - TIE GIS 7500 조작시험 - 신포천S/S #1Sh.R GIS 7379 조작시험","2024-06-27 09:00","2024-06-27 12:00","2024-06-27 09:00","2024-06-27 12:00","연속"]
[105,"경기북부","구리","신포천S/S CB 7472","24~25년 구리전력지사 변전협력회사 공사","신포천S/S 74BAY 조작시험 - 신포천-포천CC #2T/L 7471 조작시험 - 신포천-포천CC #2T/L - #3M.Tr 1차 GIS 7400 조작시험 - #3M.Tr 1차 GIS 7472 조작시험","2024-06-25 15:00","2024-06-25 18:00","2024-06-25 15:00","2024-06-25 18:00","연속"]
[106,"경기북부","구리","신포천S/S CB 7400","24~25년 구리전력지사 변전협력회사 공사","신포천S/S 74BAY 조작시험 - 신포천-포천CC #2T/L 7471 조작시험 - 신포천-포천CC #2T/L - #3M.Tr 1차 GIS 7400 조작시험 - #3M.Tr 1차 GIS 7472 조작시험","2024-06-25 13:00","2024-06-25 15:00","2024-06-25 13:00","2024-06-25 15:00","연속"]
[107,"경기북부","구리","신포천S/S CB 7471","24~25년 구리전력지사 변전협력회사 공사","신포천S/S 74BAY 조작시험 - 신포천-포천CC #2T/L 7471 조작시험 - 신포천-포천CC #2T/L - #3M.Tr 1차 GIS 7400 조작시험 - #3M.Tr 1차 GIS 7472 조작시험","2024-06-25 09:00","2024-06-25 12:00","2024-06-25 09:00","2024-06-25 12:00","연속"]
[108,"경기북부","구리","포천C/C CB 7372","24~25년 구리전력지사 변전협력회사 공사","포천C/C #4S/U Tr 1차 7372 보통점검 및 절연열화 측정","2024-06-07 09:00","2024-06-07 18:00","2024-06-07 09:00","2024-06-07 18:00","연속"]
[109,"경기북부","구리","신포천포천LNGCC#1 T/L","2024년 가공송전 순시점검 위탁공사(구리)","정밀점검","2024-06-03 09:00","2024-06-03 18:00","2024-06-03 09:00","2024-06-03 18:00","연속"]
[110,"경기북부","구리","신포천포천LNGCC#2 T/L","2024년 가공송전 순시점검 위탁공사(구리)","정밀점검","2024-06-04 09:00","2024-06-04 18:00","2024-06-04 09:00","2024-06-04 18:00","연속"]
[111,"경기북부","직할","신덕은동두천CC#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지시설 설치 - 대상 : 345kV 신덕은-동두천CC#2T/L No.18~76","2024-06-18 07:00","2024-06-28 18:00","2024-06-18 07:00","2024-06-28 18:00","연속"]
[112,"경기북부","직할","신의정부S/S #2 Sh.R CB","2024-25년 경기북부 직할 변전협력 총액공사","신의정부S/S 345kV #2Sh.R 냉각설비 세정","2024-06-11 09:00","2024-06-11 14:00","2024-06-11 09:00","2024-06-11 14:00","연속"]
[113,"경기북부","직할","신의정부S/S CB 7772","2024-25년 경기북부 직할 변전협력 총액공사","신의정부S/S 345kV #2Sh.R 냉각설비 세정","2024-06-11 09:00","2024-06-11 14:00","2024-06-11 09:00","2024-06-11 14:00","연속"]
[114,"경기북부","직할","신의정부S/S #3 Sh.R CB","2024-25년 경기북부 직할 변전협력 총액공사","신의정부S/S 345kV #3Sh.R 냉각설비 세정","2024-06-10 14:00","2024-06-10 18:00","2024-06-10 14:00","2024-06-10 18:00","연속"]
[115,"경기북부","직할","신의정부S/S CB 7700","2024-25년 경기북부 직할 변전협력 총액공사","신의정부S/S 345kV #2Sh.R 냉각설비 세정","2024-06-11 09:00","2024-06-11 14:00","2024-06-11 09:00","2024-06-11 14:00","연속"]
[116,"경기북부","직할","신의정부S/S #1 Sh.R CB","2024-25년 경기북부 직할 변전협력 총액공사","신의정부S/S 345kV #1Sh.R 냉각설비 세정","2024-06-10 09:00","2024-06-10 14:00","2024-06-10 09:00","2024-06-10 14:00","연속"]
[117,"경기북부","직할","양주S/S CB 7300","362,170kV GIS 보통점검 공사","362,170kV GIS 보통점검, 전자변 교체","2024-06-19 09:00","2024-06-19 18:00","2024-06-19 09:00","2024-06-19 18:00","연속"]
[118,"경기북부","직할","양주중부#2 T/L","24-25년 경기북부본부 직할 변전협력회사 총액공사","양주-중부 #2T/L LA 보통점검(A, B, C상)","2024-06-24 08:00","2024-06-24 18:00","2024-06-24 08:00","2024-06-24 18:00","연속"]
[119,"경기북부","직할","신의정부양주#1 T/L","24-25년 직할 변전협력회사 총액공사","양주변전소 신의정부-양주#1T/L CVT C상 초기점검","2024-06-27 09:00","2024-06-27 18:00","2024-06-27 09:00","2024-06-27 18:00","연속"]
[120,"경기북부","직할","양주S/S CB 7271","24-25년 직할 변전협력회사 총액공사","양주S/S GIS 개폐타임, 콘덴서 절연열화 측정(7271)","2024-06-28 10:00","2024-06-28 14:00","2024-06-28 10:00","2024-06-28 14:00","연속"]
[121,"경기북부","직할","양주S/S CB 7200","24-25년 직할 변전협력회사 총액공사","양주S/S GIS 개폐타임, 콘덴서 절연열화 측정(7200)","2024-06-28 14:00","2024-06-28 17:00","2024-06-28 14:00","2024-06-28 17:00","연속"]
[122,"경기북부","직할","양주S/S STATCOM CB","양주S/S 345kV STATCOM 수냉각설비 점검","양주S/S 345kV STATCOM 수냉각설비 점검","2024-06-03 09:00","2024-06-07 18:00","취소","취소","연속"]
[123,"경기북부","직할","양주S/S #2 M.Tr","24-25변전협력회사 총액공사","브르홀쯔계전기 교체","2024-06-03 09:00","2024-06-05 18:00","2024-06-03 09:00","2024-06-05 18:00","연속"]
[124,"경기북부","직할","양주S/S CB 7371","362,170kV GIS 보통점검 공사","362,170kV GIS 보통점검, 전자변 교체","2024-06-18 09:00","2024-06-18 18:00","2024-06-18 09:00","2024-06-18 18:00","연속"]
[125,"경기북부","직할","양주S/S STATCOM CB","양주S/S 345kV STATCOM 수냉각설비 점검공사","양주S/S 345kV STATCOM 수냉각설비 점검공사","2024-06-03 09:00","2024-06-07 18:00","취소","취소","연속"]
[126,"경기북부","직할","신파주양주#2 T/L","24-25년 직할 변전협력회사 총액공사","양주S/S GIS 개폐타임, 콘덴서 절연열화 측정(7471) CVT 교체","2024-06-25 10:00","2024-06-26 17:00","2024-06-25 10:00","2024-06-26 17:00","연속"]
[127,"경기","군포","서서울S/S #1 M.Tr","서서울S/S #1M.Tr 1차 7300,7372 GIS 조작시험 등","서서울S/S #1M.Tr 1차 7300,7372 GIS 조작시험 및 3차 VCB 조작시험","2024-06-17 09:00","2024-06-17 18:00","취소","취소","연속"]
[128,"경기","군포","서서울S/S CB 7571","서서울-신광명#1T/L 7571 GIS 조작시험","서서울-신광명#1T/L 7571 GIS 조작시험","2024-06-26 09:00","2024-06-26 18:00","2024-06-26 09:00","2024-06-26 18:00","연속"]
[129,"경기","군포","신안산S/S #70 BUS","신안산S/S 345kV #70BUS 모선보호반 대체공사","신안산S/S 345kV #70BUS 모선보호반 대체공사 시행","2024-06-03 09:00","2024-06-07 18:00","2024-06-03 09:00","2024-06-07 18:00","연속"]
[130,"경기","군포","신안산S/S #75 BUS","신안산S/S 345kV #75BUS 모선보호반 대체공사","신안산S/S 345kV #75BUS 모선보호반 대체공사 시행","2024-06-10 09:00","2024-06-14 18:00","2024-06-10 09:00","2024-06-14 18:00","연속"]
[131,"경기","동부","곤지암S/S #1 Sh.R CB","24-25년 동부 변전협력 총액공사","곤지암:7100(조작),7179(조작) 콘덴서 절연열화 측정 (여주복합#2T/L,#1Sh.R)","2024-06-03 14:00","2024-06-03 18:00","2024-06-03 14:00","2024-06-03 18:00","연속"]
[132,"경기","동부","곤지암S/S CB 7100","24-25년 동부 변전협력 총액공사","곤지암:7100(조작),7179(조작) 콘덴서 절연열화 측정 (여주복합#2T/L,#1Sh.R)","2024-06-03 09:30","2024-06-03 14:00","2024-06-03 09:30","2024-06-03 14:00","연속"]
[133,"경기","동부","곤지암S/S CB 7500","24-25년 동부 변전협력 총액공사","곤지암:7572(조작),7500(조작) 콘덴서 절연열화 측정 (#3M.Tr)","2024-06-04 14:00","2024-06-04 18:00","2024-06-04 14:00","2024-06-04 18:00","연속"]
[134,"경기","동부","곤지암S/S CB 7572","24-25년 동부 변전협력 총액공사","곤지암:7572(조작),7500(조작) 콘덴서 절연열화 측정 (#3M.Tr)","2024-06-04 09:30","2024-06-04 14:00","2024-06-04 09:30","2024-06-04 14:00","연속"]
[135,"경기","성남","신성남S/S #3 M.Tr","2024년 성남전력 변전협력회사 총액공사","변압기 추락방지시설 설치","2024-06-21 09:00","2024-06-21 18:00","2024-06-21 09:00","2024-06-21 18:00","연속"]
[136,"경기","성남","신성남S/S #2 M.Tr","2024년 성남전력 변전협력회사 총액공사","변압기 추락방지시설 설치","2024-06-20 09:00","2024-06-20 18:00","2024-06-20 09:00","2024-06-20 18:00","연속"]
[137,"경기","성남","신성남S/S STATCOM CB","2024년 성남전력 변전협력회사 총액공사","S.TR 절체 시험","2024-06-10 08:00","2024-06-10 10:00","2024-06-10 08:00","2024-06-10 10:00","연속"]
[138,"경기","성남","신성남동서울#2 T/L","345kV 신성남-동서울T/L No.46 애자련 보강공사","345kV 신성남-동서울T/L No.46 애자련 보강(1련 -> 2련) - 사유 : 서울세종 고속도록 횡단구간 애자련 보강","2024-06-07 08:00","2024-06-07 18:00","2024-06-07 08:00","2024-06-07 18:00","연속"]
[139,"경기","성남","신용인신수원 T/L","2024년 성남전력 변전협력회사 총액공사","(신수원) 7171,7100 절연열화, LA 하자점검 (신용인) 7771,7700 절연열화, LA 초기점검","2024-06-18 09:00","2024-06-19 18:00","2024-06-18 09:00","2024-06-19 18:00","연속"]
[140,"경기","성남","신용인S/S #3 M.Tr","2024년 성남전력 345, 154 GIS 보통점검공사","7572 GIS 보통점검, 절연열화","2024-06-05 09:00","2024-06-05 18:00","2024-06-05 09:00","2024-06-05 18:00","연속"]
[141,"경기","성남","신용인삼성 T/L","2024년 성남전력 변전협력회사 총액공사","CVT 점검, 7671, 7600 절연열화 측정","2024-06-25 09:00","2024-06-25 18:00","2024-06-25 09:00","2024-06-25 18:00","연속"]
[142,"경기","직할","화성신안산#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 2회선 10기, 4회선 10기","2024-06-17 07:00","2024-06-21 18:00","2024-06-17 07:00","2024-06-21 18:00","연속"]
[143,"경기","직할","화성서서울#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 2회선 10기, 345kV 화성-신안산T/L 병가선로 3기)","2024-06-20 07:00","2024-06-21 18:00","취소","취소","연속"]
[144,"경기","직할","화성신안산#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 2회선 10기, 4회선 10기","2024-06-24 07:00","2024-06-28 18:00","2024-06-24 07:00","2024-06-28 18:00","연속"]
[145,"경기","직할","화성서서울#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 2회선 10기, 345kV 화성-신안산T/L 병가선로 3기)","2024-06-27 07:00","2024-06-28 18:00","취소","취소","연속"]
[146,"경기","직할","화성S/S CB 7100","2024-25년 경기본부 직할 변전협력회사 총액공사","화성S/S 345kV 화성-신평택#1T/L TIE GIS(7100) - GIS 콘덴서 절연열화 측정","2024-06-03 09:00","2024-06-03 11:00","2024-06-03 09:00","2024-06-03 11:00","연속"]
[147,"경기","직할","화성S/S CB 7200","2024-25년 경기본부 직할 변전협력회사 총액공사","화성S/S 345kV 화성-신평택#2T/L TIE GIS(7200) - GIS 콘덴서 절연열화 측정","2024-06-03 11:00","2024-06-03 14:00","2024-06-03 11:00","2024-06-03 14:00","연속"]
[148,"경기","직할","화성S/S CB 7471","2024-25년 경기본부 직할 변전협력회사 총액공사","화성S/S 345kV 아산-화성#2T/L GIS(7471) - GIS 콘덴서 절연열화 측정","2024-06-03 14:00","2024-06-03 16:00","2024-06-03 14:00","2024-06-03 16:00","연속"]
[149,"경기","직할","화성S/S CB 7400","2024-25년 경기본부 직할 변전협력회사 총액공사","화성S/S 345kV 아산-화성#2T/L-#2M 1차(7400) - GIS 콘덴서 절연열화 측정","2024-06-03 16:00","2024-06-03 18:00","2024-06-03 16:00","2024-06-03 18:00","연속"]
[150,"경기","평택","고덕#2S/S CB 7272","24년도 평택전력 154,345kV GIS 보통점검","고덕2S/S 345kV 고덕-고덕2#1T/L GIS(7272) 보통점검","2024-06-18 09:00","2024-06-18 14:00","2024-06-18 09:00","2024-06-18 14:00","연속"]
[151,"경기","평택","고덕#2S/S CB 7371","24년도 평택전력 154,345kV GIS 보통점검","고덕2S/S 345kV 고덕-고덕2#2T/L GIS(7371) 보통점검","2024-06-18 14:00","2024-06-18 18:00","2024-06-18 14:00","2024-06-18 18:00","연속"]
[152,"경기","평택","고덕#2S/S CB 7271","24년도 평택전력 154,345kV GIS 보통점검","고덕2S/S 345kV #1M.Tr 1차 GIS(7271) 보통점검","2024-06-28 09:00","2024-06-28 14:00","2024-06-28 09:00","2024-06-28 14:00","연속"]
[153,"경기","평택","고덕#2S/S CB 7200","24년도 평택전력 154,345kV GIS 보통점검","고덕2S/S 345kV #1M.Tr 1차 TIE GIS(7200) 보통점검","2024-06-28 14:00","2024-06-28 18:00","2024-06-28 14:00","2024-06-28 18:00","연속"]
[154,"경기","평택","고덕S/S CB 7972","24년도 평택전력 154,345kV GIS 보통점검","고덕S/S 345kV 고덕-고덕C/S #3F GIS(7972) 보통점검","2024-06-17 09:00","2024-06-17 14:00","2024-06-17 09:00","2024-06-17 14:00","연속"]
[155,"경기","평택","고덕S/S CB 7A71","24년도 평택전력 154,345kV GIS 보통점검","고덕S/S 345kV 고덕-고덕C/S #4F GIS(7A71) 보통점검","2024-06-17 14:00","2024-06-17 18:00","2024-06-17 14:00","2024-06-17 18:00","연속"]
[156,"경기","평택","고덕#2서안성#1 T/L","평택 브레인시티 지중화공사(안전이격)","평택 브레인시티 지중화공사(고덕-진위T/L) 가공송전선로 가선을 위하여 병가된 고덕-서안성T/L 안전이격확보","2024-06-07 09:00","2024-06-13 18:00","2024-06-07 09:00","2024-06-13 18:00","매일"]
[157,"경기","평택","고덕#2서안성#2 T/L","평택 브레인시티 지중화공사(안전이격)","평택 브레인시티 지중화공사(고덕-진위T/L) 가공송전선로 가선을 위하여 병가된 고덕-서안성T/L 안전이격확보","2024-06-07 09:00","2024-06-07 18:00","2024-06-07 09:00","2024-06-07 18:00","매일"]
[158,"경기","평택","고덕#2서안성#2 T/L","평택 브레인시티 지중화공사(안전이격)","평택 브레인시티 지중화공사(고덕-진위T/L) 가공송전선로 가선을 위하여 병가된 고덕-서안성T/L 안전이격확보","2024-06-19 09:00","2024-06-24 18:00","2024-06-19 09:00","2024-06-24 18:00","매일"]
[159,"경기","평택","평택T/P #2 TIE Tr","24년 평택전력 345kV TIE.Tr 및 GIS 보통점검","평택T/P 345kV #2TIE.Tr 변압기 및 1차, TIE(7371,7300) GIS 보통점검","2024-06-03 09:00","2024-06-05 18:00","2024-06-03 09:00","2024-06-05 18:00","연속"]
[160,"경기","평택","평택T/P #3 TIE Tr","24년 평택전력 345kV TIE.Tr 및 GIS 보통점검","평택T/P 345kV #3TIE.Tr 변압기 및 1차, TIE(7471,7400) GIS 보통점검","2024-06-10 09:00","2024-06-12 18:00","2024-06-10 09:00","2024-06-12 18:00","연속"]
[161,"경기","평택","평택T/P CB 7600","평택T/P 345kV GIS 보통점검","평택T/P 345kV 평택화성#1-#2MAIN TR 1차(7600) 보통점검","2024-06-12 14:00","2024-06-12 18:00","2024-06-12 14:00","2024-06-12 18:00","연속"]
[162,"경기","평택","평택T/P CB 7672","평택T/P 345kV GIS 보통점검","평택T/P 345kV #2MAIN TR 1차(7672) 보통점검","2024-06-12 09:00","2024-06-12 14:00","2024-06-12 09:00","2024-06-12 14:00","연속"]
[163,"경기","평택","평택T/P CB 7571","24년 평택전력 345kV GIS 보통점검","평택T/P 345kV 화성-평택T/P#2T/L GIS(7571) 보통점검","2024-06-05 09:00","2024-06-05 14:00","2024-06-05 09:00","2024-06-05 14:00","연속"]
[164,"경기","평택","평택T/P CB 7572","24년 평택전력 345kV GIS 보통점검","평택T/P 345kV #1-2ST.Tr 1차 GIS(7572) 보통점검","2024-06-05 14:00","2024-06-05 18:00","2024-06-05 14:00","2024-06-05 18:00","연속"]
[165,"경기","평택","평택T/P CB 7172","24년 평택전력 345kV GIS 보통점검","평택T/P 345kV #3MAIN TR(#3T/P) 1차 GIS(7172) 보통점검","2024-06-07 09:00","2024-06-07 18:00","2024-06-07 09:00","2024-06-07 18:00","연속"]
[166,"경기","평택","평택T/P CB 7271","평택T/P 345kV GIS 보통점검","평택T/P 345kV #4MAIN TR(#4T/P) 1차 GIS(7271) 보통점검","2024-06-10 09:00","2024-06-10 14:00","2024-06-10 09:00","2024-06-10 14:00","연속"]
[167,"경기","평택","평택T/P CB 7200","평택T/P 345kV GIS 보통점검","평택T/P 345kV #4MAIN TR 1차-#3,4ST.Tr GIS(7200) 보통점검","2024-06-10 14:00","2024-06-10 18:00","2024-06-10 14:00","2024-06-10 18:00","연속"]
[168,"강원","강릉","신양양S/S CB 7200","2024년 강릉전력지사 변전협력회사 공사","차단기 조작시험, 콘덴서 절연열화 측정","2024-06-03 14:00","2024-06-03 18:00","취소","취소","연속"]
[169,"강원","강릉","안인개폐소신양양 T/L","2024년 강릉전력지사 변전협력회사 공사","차단기 조작시험, 균압콘덴서 점검","2024-06-03 10:00","2024-06-03 18:00","2024-06-03 10:00","2024-06-03 18:00","연속"]
[170,"강원","강릉","신양양S/S #3 M.Tr","2024년 강릉전력지사 변전협력회사 공사","1차 GIS 균압콘덴서 점검, #2-1,2Sh.R, #2S.Tr CB, #2-1,2Sh.R CB 점검","2024-06-04 10:00","2024-06-05 18:00","2024-06-04 10:00","2024-06-05 18:00","연속"]
[171,"강원","강릉","신양양S/S #2 M.Tr","2024년 강릉전력지사 변전협력회사 총액공사","3차 LA 대체, 차단기 조작시험, 콘덴서 절연열화 측정","2024-06-14 10:00","2024-06-14 18:00","2024-06-14 10:00","2024-06-14 18:00","연속"]
[172,"강원","강릉","신양양S/S #1 M.Tr","2024년 강릉전력지사 변전협력회사 총액공사","3차 LA 대체, #1-1,2 Sh.R, #1,S.Tr CB, #1-1,2Sh.R CB 보통점검, 차단기 조작시험, 콘덴서 절연열화 측정","2024-06-12 10:00","2024-06-13 18:00","2024-06-12 10:00","2024-06-13 18:00","연속"]
[173,"강원","강릉","신양양S/S CB 7271","2024년 강릉전력지사 변전협력회사 공사","차단기 조작시험, 콘덴서 절연열화 측정","2024-06-03 10:00","2024-06-03 14:00","취소","취소","연속"]
[174,"강원","강릉","양양P/P CB 7171","2024년 강릉전력지사 변전협력회사 공사","362kV GIS 보통점검 (7171CB)","2024-06-10 10:00","2024-06-10 18:00","2024-06-10 10:00","2024-06-10 18:00","연속"]
[175,"강원","동해","동해S/S #1 M.Tr","2024년 동해전력지사 Sh.R 보호반 대체공사","1. #1 Sh.R 보호반 대체","2024-06-19 09:00","2024-06-21 18:00","2024-06-19 09:00","2024-06-21 18:00","연속"]
[176,"강원","동해","동해S/S CB 7500","2024년~25년 동해전력지사 변전협력회사 총액공사","1. 7500 CB 투입 개리차 조정(효성)","2024-06-24 09:30","2024-06-24 18:00","2024-06-24 09:30","2024-06-24 18:00","연속"]
[177,"강원","동해","동해S/S #2 M.Tr","2024년 동해전력지사 Sh.R 보호반 대체공사","1. #2 Sh.R 보호반 대체","2024-06-26 09:00","2024-06-28 18:00","2024-06-26 09:00","2024-06-28 18:00","연속"]
[178,"강원","동해","삼척G/P CB 7572","2024~25년 동해전력지사 변전협력회사 총액공사","1. 7572 CB 보통점검","2024-06-13 09:30","2024-06-13 18:00","2024-06-13 09:30","2024-06-13 18:00","연속"]
[179,"강원","동해","삼척G/P #3 Tie-Tr","2024~25년 동해전력지사 변전협력회사 총액공사","1. M.Tr 보통점검 2. 7672 CB 보통점검 3. #3 M.Tr 2차, 3차 GIS 보통점검 4. 2차 LA 보통점검 5. 사다리 철거 및 추락방지장치설치","2024-06-10 09:30","2024-06-12 18:00","2024-06-10 09:30","2024-06-12 18:00","연속"]
[180,"충북","직할","신중부S/S #6 Sh.R CB","신중부S/S 345kV GIS 콘덴서 절연열화 진단","송운(변전)-1076(’23. 9.25)「345kV GIS(콘덴서) 고장예방 및 최적화 운전방안 알림」관련 신중부S/S 345kV GIS 콘덴서 절연열화 진단","2024-06-18 15:00","2024-06-18 18:00","2024-06-18 15:00","2024-06-18 18:00","연속"]
[181,"충북","직할","신중부S/S #5 Sh.R CB","신중부S/S 345kV GIS 콘덴서 절연열화 진단","송운(변전)-1076(’23. 9.25)「345kV GIS(콘덴서) 고장예방 및 최적화 운전방안 알림」관련 신중부S/S 345kV GIS 콘덴서 절연열화 진단","2024-06-18 10:00","2024-06-18 12:00","2024-06-18 10:00","2024-06-18 12:00","연속"]
[182,"충북","직할","신중부S/S #1 BUS","신중부S/S 345kV GIS 콘덴서 절연열화 진단","송운(변전)-1076(’23. 9.25)「345kV GIS(콘덴서) 고장예방 및 최적화 운전방안 알림」관련 신중부S/S 345kV GIS 콘덴서 절연열화 진단","2024-06-18 08:00","2024-06-18 18:00","2024-06-18 08:00","2024-06-18 18:00","연속"]
[183,"충북","직할","신중부S/S #2 BUS","신중부S/S 345kV GIS 콘덴서 절연열화 진단","송운(변전)-1076(’23. 9.25)「345kV GIS(콘덴서) 고장예방 및 최적화 운전방안 알림」관련 신중부S/S 345kV GIS 콘덴서 절연열화 진단","2024-06-19 08:00","2024-06-19 18:00","2024-06-19 08:00","2024-06-19 18:00","연속"]
[184,"충북","직할","신중부남청주#2 T/L","신중부S/S 345kV GIS 콘덴서 절연열화 진단","송운(변전)-1076(’23. 9.25)「345kV GIS(콘덴서) 고장예방 및 최적화 운전방안 알림」관련 신중부S/S 345kV GIS 콘덴서 절연열화 진단","2024-06-19 15:00","2024-06-19 18:00","2024-06-19 15:00","2024-06-19 18:00","연속"]
[185,"충북","직할","신중부신진천#1 T/L","신중부S/S 345kV GIS 콘덴서 절연열화 진단","송운(변전)-1076(’23. 9.25)「345kV GIS(콘덴서) 고장예방 및 최적화 운전방안 알림」관련 신중부S/S 345kV GIS 콘덴서 절연열화 진단","2024-06-19 08:00","2024-06-19 10:00","2024-06-19 08:00","2024-06-19 10:00","연속"]
[186,"충북","직할","신중부신진천#2 T/L","신중부S/S 345kV GIS 콘덴서 절연열화 진단","송운(변전)-1076(’23. 9.25)「345kV GIS(콘덴서) 고장예방 및 최적화 운전방안 알림」관련 신중부S/S 345kV GIS 콘덴서 절연열화 진단","2024-06-19 10:00","2024-06-19 12:00","2024-06-19 10:00","2024-06-19 12:00","연속"]
[187,"충북","직할","신중부남청주#1 T/L","신중부S/S 345kV GIS 콘덴서 절연열화 진단","송운(변전)-1076(’23. 9.25)「345kV GIS(콘덴서) 고장예방 및 최적화 운전방안 알림」관련 신중부S/S 345kV GIS 콘덴서 절연열화 진단","2024-06-19 13:00","2024-06-19 15:00","2024-06-19 13:00","2024-06-19 15:00","연속"]
[188,"충북","직할","신진천S/S #2 M.Tr","24-25년 충북 직할 변전협력회사 공사","신진천S/S 345kV #2M.Tr 3차 VCB(4289) 대체 및 #2S.Tr 대체","2024-06-10 09:00","2024-06-14 18:00","2024-06-10 09:00","2024-06-14 18:00","연속"]
[189,"충북","청주","남청주S/S #3 M.Tr","24년 345kV 주변압기 정밀점검","#3M.Tr 정밀점검","2024-06-03 09:00","2024-06-16 18:00","2024-06-03 09:00","2024-06-16 18:00","연속"]
[190,"충북","청주","남청주S/S #2 M.Tr","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-06-03 08:00","2024-06-21 18:00","취소","취소","연속"]
[191,"충북","청주","세종남청주#1 T/L","345kV 신옥천북경남 등 8개T/L 추락방지장치 설치공사","345kV 세종남청주T/L 추락방지장치 설치 - 세종남청주#1T/L No.32~57 (26기, 수평설치)","2024-06-18 07:00","2024-06-21 18:00","2024-06-18 07:00","2024-06-21 18:00","매일"]
[192,"충북","청주","세종남청주#2 T/L","345kV 신옥천북경남 등 8개T/L 추락방지장치 설치공사","345kV 세종남청주T/L 추락방지장치 설치 - 세종남청주#2T/L No.32~57 (26기, 수평설치)","2024-06-24 07:00","2024-06-26 18:00","2024-06-24 07:00","2024-06-26 18:00","매일"]
[193,"충북","청주","신옥천신남원#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사","362kV GIS 보통점검","2024-06-03 09:00","2024-06-04 18:00","2024-06-03 09:00","2024-06-04 18:00","연속"]
[194,"충북","충주","신제천신영주#2 T/L","345kV 신제천-신영주T/L OPGW 낙뢰소손 관련 교체공사","#2T/L No.5~12호 3.057km 1드럼 연선교체, 항공구 31개 재설치","2024-06-06 07:00","2024-06-09 18:00","취소","취소","연속"]
[195,"충북","충주","신충주S/S #1 M.Tr","24-25년 충주전력지사 변전정비 총액공사","신충주S/S 345kV #1M.Tr A상 2차부싱 접속부 과열로 안한 점검","2024-06-05 10:00","2024-06-05 15:00","2024-06-05 10:00","2024-06-05 15:00","연속"]
[196,"충북","충주","신충주T신충주 T/L","2024-2025년 성남전력지사 가공송전 협력회사공사","345kV 신제천여주복합T/L No.33~34,35~36 가공지선 및 항공구교체 (6/5~10) (병행휴전) 신충주T분기T/L","2024-06-05 09:00","2024-06-10 18:00","취소","취소","연속"]
[197,"대전세종충남","서산","신당진개폐소현대제철 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","(5월휴전 취소시) 수평 추락방지장치 설치공사 (No.1.1~44), 즉시가압(20분 이내)가능, 주말작업 없음","2024-06-28 08:00","2024-07-03 18:00","취소","취소","매일"]
[198,"대전세종충남","서산","신당진개폐소북당진 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.1.1~65), 즉시가압(20분 이내)가능","2024-06-10 08:00","2024-06-14 18:00","2024-06-10 08:00","2024-06-14 18:00","매일"]
[199,"대전세종충남","서산","신당진개폐소태안TP#2 T/L","'24~'25년도 서산전력지사 송전협력회사","345kV 신당진-태안화력#2T/L 항공구 설치공사, 즉시가압(20분이내)불가 No.44~45 등 8경간 *5월 휴전 승인시 취소요청 *주말작업 X","2024-06-12 08:00","2024-06-18 18:00","취소","취소","매일"]
[200,"대전세종충남","서산","신서산신당진#1 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.1~6,33~42) , 즉시가압(20분 이내) 가능","2024-06-03 08:00","2024-06-04 18:00","취소","취소","매일"]
[201,"대전세종충남","서산","신서산신당진#2 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.1~6,33~42), 즉시가압(20분 이내)가능, 휴일작업(6일) 없음","2024-06-05 08:00","2024-06-07 18:00","취소","취소","매일"]
[202,"대전세종충남","서산","신서산S/S CB 7971","24년 서산P/O 345kV GIS 정밀점검공사","(즉시가압 불가) 신서산S/S 345kV 7971 CB 정밀점검","2024-06-10 09:30","2024-06-14 18:00","2024-06-10 09:30","2024-06-14 18:00","연속"]
[203,"대전세종충남","서산","신서산S/S CB 7771","24년 서산P/O 345kV GIS 정밀점검공사","(즉시가압 불가) 신서산S/S 345kV 7771 CB 정밀점검","2024-06-24 09:30","2024-06-28 18:00","2024-06-24 09:30","2024-06-28 18:00","연속"]
[204,"대전세종충남","서산","신서산태안TP#2 T/L","'24~'25년도 서산전력지사 송전협력회사","345kV 신서산-태안화력#2T/L 항공구 설치공사, 즉시가압(20분이내)불가 No.39~40 등 4경간 *5월 휴전 승인시 취소요청","2024-06-19 08:00","2024-06-21 18:00","취소","취소","매일"]
[205,"대전세종충남","서산","신서산S/S #5 Sh.R CB","24년 서산P/O 345kV GIS 정밀점검공사","(즉시가압 불가) 신서산S/S 345kV 7979 CB 정밀점검","2024-06-17 09:30","2024-06-21 18:00","취소","취소","연속"]
[206,"대전세종충남","서산","태안T/P CB 7600","24년 서산P/O 변전협력회사 총액공사","(즉시가압 불가) 태안화력S/Y 345kV 7600 CB 유압 메커니즘부 교체","2024-06-03 09:30","2024-06-05 18:00","취소","취소","연속"]
[207,"대전세종충남","천안","신온양서서울#2 T/L","신온양S/S 345kV 77Bay B/F 보호배전반 대체","(즉시가압불가)신온양S/S 345kV 77Bay B/F 보호배전반 대체","2024-06-04 09:00","2024-06-07 18:00","취소","취소","연속"]
[208,"대전세종충남","천안","신온양S/S #4 M.Tr","신온양S/S 345kV 77Bay B/F 보호배전반 대체","(즉시가압불가)신온양S/S 345kV 77Bay B/F 보호배전반 대체","2024-06-04 09:00","2024-06-07 18:00","취소","취소","연속"]
[209,"대전세종충남","천안","신온양신탕정#2 T/L","신온양S/S 345kV 78Bay B/F 보호배전반 대체","(즉시가압불가)신온양S/S 345kV 78Bay B/F 보호배전반 대체","2024-06-11 09:00","2024-06-14 18:00","취소","취소","연속"]
[210,"대전세종충남","천안","신온양신탕정#1 T/L","[5월취소시]345kV 신온양-신탕정T/L 추락방지장치 설치공사","[즉시가압가능]345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치 [병가철탑] 신온양신탕정#1(상단), 청양신탕정#1(하단)","2024-06-10 07:00","2024-06-14 18:00","취소","취소","매일"]
[211,"대전세종충남","천안","신온양서서울#1 T/L","신온양S/S 345kV 78Bay B/F 보호배전반 대체","(즉시가압불가)신온양S/S 345kV 78Bay B/F 보호배전반 대체","2024-06-11 09:00","2024-06-14 18:00","취소","취소","연속"]
[212,"대전세종충남","천안","신탕정S/S #2 M.Tr","신탕정S/S 345kV #2M.Tr 누유보수","(즉시가압불가)신탕정S/S 345kV #2M.Tr 라디에이터 상부 누유보수","2024-06-25 09:00","2024-06-27 18:00","2024-06-25 09:00","2024-06-27 18:00","연속"]
[213,"대전세종충남","천안","신탕정S/S CB 7100","신탕정S/S 345kV 7100 GIS 보통점검","(즉시가압가능)신탕정S/S 345kV 7100 GIS 보통점검","2024-06-03 09:00","2024-06-03 18:00","2024-06-03 09:00","2024-06-03 18:00","연속"]
[214,"대전세종충남","천안","신탕정S/S CB 7172","신탕정S/S 345kV 7172 GIS 보통점검","(즉시가압가능)신탕정S/S 345kV 7172 GIS 보통점검","2024-06-04 09:00","2024-06-04 18:00","2024-06-04 09:00","2024-06-04 18:00","연속"]
[215,"대전세종충남","천안","신탕정S/S CB 7200","신탕정S/S 345kV 7200 GIS 보통점검","(즉시가압가능)신탕정S/S 345kV 7200 GIS 보통점검","2024-06-05 09:00","2024-06-05 18:00","2024-06-05 09:00","2024-06-05 18:00","연속"]
[216,"대전세종충남","천안","신탕정S/S CB 7272","신탕정S/S 345kV 7272 GIS 보통점검","(즉시가압가능)신탕정S/S 345kV 7272 GIS 보통점검","2024-06-06 09:00","2024-06-06 18:00","2024-06-06 09:00","2024-06-06 18:00","연속"]
[217,"대전세종충남","천안","신탕정S/S CB 7371","신탕정S/S 345kV 7300 GIS 보통점검","(즉시가압가능)신탕정S/S 345kV 7300 GIS 보통점검","2024-06-07 09:00","2024-06-07 18:00","2024-06-07 09:00","2024-06-07 18:00","연속"]
[218,"대전세종충남","천안","신탕정S/S CB 7300","신탕정S/S 345kV 7371 GIS 보통점검","(즉시가압가능)신탕정S/S 345kV 7371 GIS 보통점검","2024-06-10 09:00","2024-06-10 18:00","2024-06-10 09:00","2024-06-10 18:00","연속"]
[219,"대전세종충남","천안","신탕정S/S CB 7400","신탕정S/S 345kV 7400 GIS 보통점검","(즉시가압가능)신탕정S/S 345kV 7400 GIS 보통점검","2024-06-11 09:00","2024-06-11 18:00","2024-06-11 09:00","2024-06-11 18:00","연속"]
[220,"대전세종충남","천안","청양신탕정#1 T/L","[5월취소시]345kV 신온양-신탕정T/L 추락방지장치 설치공사","[즉시가압가능]345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치 [병가철탑] 신온양신탕정#1(상단), 청양신탕정#1(하단)","2024-06-10 07:00","2024-06-14 18:00","취소","취소","매일"]
[221,"대전세종충남","천안","신온양신탕정#2 T/L","[5월취소시]345kV 신온양-신탕정T/L 추락방지장치 설치공사","[즉시가압가능]345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치 [병가철탑] 신온양신탕정#2(상단), 청양신탕정#2(하단)","2024-06-17 07:00","2024-06-21 18:00","취소","취소","매일"]
[222,"대전세종충남","천안","청양신탕정#2 T/L","[5월취소시]345kV 신온양-신탕정T/L 추락방지장치 설치공사","[즉시가압가능]345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치 [병가철탑] 신온양신탕정#2(상단), 청양신탕정#2(하단)","2024-06-17 07:00","2024-06-21 18:00","취소","취소","매일"]
[223,"대전세종충남","천안","아산S/S CB 7100","아산S/S 345kV 7100 GIS 보통점검","(즉시가압가능)아산S/S 345kV 7100 GIS 보통점검","2024-06-12 09:00","2024-06-12 18:00","2024-06-12 09:00","2024-06-12 18:00","연속"]
[224,"대전세종충남","천안","아산S/S CB 7272","아산S/S 345kV 7272 GIS 보통점검","(즉시가압가능)아산S/S 345kV 7272 GIS 보통점검","2024-06-13 09:00","2024-06-13 18:00","2024-06-13 09:00","2024-06-13 18:00","연속"]
[225,"대전세종충남","천안","아산S/S CB 7471","아산S/S 345kV 7471 GIS 보통점검","(즉시가압가능)아산S/S 345kV 7471 GIS 보통점검","2024-06-14 09:00","2024-06-14 18:00","2024-06-14 09:00","2024-06-14 18:00","연속"]
[226,"대전세종충남","청양","보령C/C CB 7271","청양P/O 전문 발주공사(복합 7271 보통)","보령C/C 345KV 보령연락#1T/L 7271 - 보령 7271 보통점검 - 즉시가압 가능","2024-06-18 09:00","2024-06-18 18:00","2024-06-18 09:00","2024-06-18 18:00","연속"]
[227,"대전세종충남","청양","보령C/C CB 7372","청양P/O 전문 발주공사(복합 7371 보통)","보령C/C 345kV #3 M.Tr 1차 7371 - 보령 7371 보통점검 - 즉시가압 가능","2024-06-19 09:00","2024-06-19 18:00","2024-06-19 09:00","2024-06-19 18:00","연속"]
[228,"대전세종충남","청양","보령C/C CB 7171","청양P/O 전문 발주공사(복합 7171 보통)","보령C/C 345KV 보령연락#1T/L 7171 - 보령 7171 보통점검 - 즉시가압 가능","2024-06-17 09:00","2024-06-17 18:00","2024-06-17 09:00","2024-06-17 18:00","연속"]
[229,"대전세종충남","청양","보령C/C SEC CB 75760","청양P/O 전문 발주공사(복합 75-76-0 보통)","보령C/C 345kV #75-#76 SEC 75760 - 보령 75760 보통점검 - 즉시가압 가능","2024-06-14 09:00","2024-06-14 18:00","2024-06-14 09:00","2024-06-14 18:00","연속"]
[230,"대전세종충남","청양","보령C/C SEC CB 70710","청양P/O 전문 발주공사(복합 70710 보통)","보령C/C 345kV #70-#71 SEC 70710 - 보령 70710 보통점검 - 즉시가압 가능","2024-06-13 09:00","2024-06-13 18:00","2024-06-13 09:00","2024-06-13 18:00","연속"]
[231,"대전세종충남","청양","보령T/P CB 7300","청양P/O 변전협력 총액공사(화력 7300 보통)","보령T/P #3 M.Tr 1차-#3,4 SU TR 1차 7300 - 보령 7300 보통점검 - 즉시가압 가능","2024-06-25 09:00","2024-06-25 18:00","2024-06-25 09:00","2024-06-25 18:00","연속"]
[232,"대전세종충남","청양","보령T/P CB 7572","청양P/O 전문 발주공사(화력 7572 보통)","보령T/P 345kV #5 M.Tr 1차 7572 - 보령 7572 보통점검 - 즉시가압 가능","2024-06-12 09:00","2024-06-12 18:00","2024-06-12 09:00","2024-06-12 18:00","연속"]
[233,"대전세종충남","청양","보령T/P CB 7571","청양P/O 전문 발주공사(화력 7571 보통)","보령T/P 345kV 아산-보령화력#2T/L 7571 - 보령 7571 보통점검 - 즉시가압 가능","2024-06-11 09:00","2024-06-11 18:00","2024-06-11 09:00","2024-06-11 18:00","연속"]
[234,"대전세종충남","청양","보령T/P CB 7500","청양P/O 전문 발주공사(화력 7500 보통)","보령T/P 아산보령화력#2T/L-#5M.Tr1차 7500 - 보령 7500 보통점검 - 즉시가압 가능","2024-06-10 09:00","2024-06-10 18:00","2024-06-10 09:00","2024-06-10 18:00","연속"]
[235,"대전세종충남","청양","보령T/P CB 7371","청양P/O 변전협력 총액공사(화력 7371 보통)","보령T/P 345kV #3 M.Tr 1차 7371 - 보령 7371 보통점검 - 즉시가압 가능","2024-06-26 09:00","2024-06-26 18:00","2024-06-26 09:00","2024-06-26 18:00","연속"]
[236,"대전세종충남","청양","보령TP보령CC#1 T/L","(5월취소시)보령화력 345kV LA & PT 내장화 공사","(5월취소시)보령화력 345kV LA & PT 내장화공사 관련 무부하 가압 -즉시가압 불가","2024-06-27 09:00","2024-06-28 18:00","취소","취소","연속"]
[237,"대전세종충남","청양","보령T/P #75 BUS","(5월취소시)345kV LA, PT GIS 내장화공사(아산-보령화력#1)","(5월취소시)345kV LA, PT GIS 내장화공사(6.27~6.28) 345 아산-보령화력#1 / #75BUS 휴전 - 즉시가압 불가","2024-06-27 09:00","2024-06-28 18:00","취소","취소","연속"]
[238,"대전세종충남","청양","아산보령TP#1 T/L","345kV LA, PT GIS 내장화공사(345 아산-보령화력#1)","345kV LA, PT GIS 내장화공사(6.17~6.28) 345 아산-보령화력#1 / #75BUS 휴전 - 즉시가압 불가","2024-06-17 09:00","2024-06-28 18:00","취소","취소","연속"]
[239,"대전세종충남","청양","보령T/P CB 7372","청양P/O 변전협력 총액공사(화력 7372 보통)","보령T/P 345kV #3,4 SU TR 1차 7372 - 보령 7372 보통점검 - 즉시가압 가능","2024-06-27 09:00","2024-06-27 18:00","2024-06-27 09:00","2024-06-27 18:00","연속"]
[240,"대전세종충남","청양","보령T/P #75 BUS","345kV LA, PT GIS 내장화공사(345 아산-보령화력#1)","345kV LA, PT GIS 내장화공사(6.27~6.28) 345 아산-보령화력#1 / #75BUS 휴전 - 즉시가압 불가","2024-06-27 09:00","2024-06-28 18:00","취소","취소","연속"]
[241,"대전세종충남","청양","청양S/S CB 7300","청양P/O 변전협력 총액공사(7300 조작)","345kV 청양-신탕정#1 - 청군#2 TIE GIS 7300 - 청양S/S 7300 조작시험 - 즉시가압 가능","2024-06-12 14:00","2024-06-12 18:00","2024-06-12 14:00","2024-06-12 18:00","연속"]
[242,"대전세종충남","청양","청양S/S CB 7571","청양P/O 변전협력 총액공사(7571 조작)","345kV 청양 TIE GIS 7571(청양-신탕정#2T/L GIS) - 청양S/S 7571 조작시험 - 즉시가압 가능","2024-06-13 09:00","2024-06-13 14:00","2024-06-13 09:00","2024-06-13 14:00","연속"]
[243,"대전세종충남","청양","청양S/S CB 7500","청양P/O 변전협력 총액공사(7500 조작)","345kV 청양 TIE GIS 7500(청양신탕정#2T/L-TIE GIS) - 청양S/S 7500 조작시험 - 즉시가압 가능","2024-06-13 14:00","2024-06-13 18:00","2024-06-13 14:00","2024-06-13 18:00","연속"]
[244,"대전세종충남","청양","청양S/S CB 7772","청양P/O 변전협력 총액공사(7772 조작)","345kV #2M.Tr 1차 GIS (7772) - 청양S/S 7772 조작시험 - 즉시가압 가능","2024-06-18 09:00","2024-06-18 14:00","2024-06-18 09:00","2024-06-18 14:00","연속"]
[245,"대전세종충남","청양","청양군산#2 T/L","345kV 청양군산#2T/L 애자련 보강","No.175 애자련 보강(2련)","2024-06-25 08:00","2024-06-27 18:00","취소","취소","연속"]
[246,"대전세종충남","청양","청양군산#1 T/L","(5월 휴전취소시)345kV 청양군산#1T/L 가공지선 교체공사","No.131~137, 162~165","2024-06-17 08:00","2024-06-24 18:00","취소","취소","연속"]
[247,"대전세종충남","청양","청양군산#1 T/L","[송전] 345kV 청양-군산#1T/L 가공지선 교체 및 애자련 보강","345kV 청양-군산#1T/L 가공지선 교체 및 애자련 보강","2024-06-24 08:00","2024-06-29 18:00","취소","취소","매일"]
[248,"대전세종충남","청양","청양S/S SEC CB 75760","청양P/O 변전협력 총액공사(75-76-0 보통)","345kV #75-#76 SEC GIS (75-76-0) - 청양S/S 75-76-0 보통점검 - 즉시가압 가능","2024-06-19 14:00","2024-06-18 18:00","2024-06-19 14:00","2024-06-18 18:00","연속"]
[249,"대전세종충남","청양","청양S/S CB 7371","청양P/O 변전협력 총액공사(7371 조작)","345kV 청양-신탕정#1 T/L 7371 - 청양S/S 7371 조작시험 - 즉시가압 가능","2024-06-12 09:00","2024-06-12 14:00","2024-06-12 09:00","2024-06-12 14:00","연속"]
[250,"대전세종충남","청양","청양S/S CB 7700","청양P/O 변전협력 총액공사(7700 조작)","345kV #2M.Tr - TIE GIS (7700) - 청양S/S 7700 조작시험 - 즉시가압 가능","2024-06-18 14:00","2024-06-18 18:00","2024-06-18 14:00","2024-06-18 18:00","연속"]
[251,"대전세종충남","청양","청양S/S SEC CB 70710","청양P/O 변전협력 총액공사(70-71-0 보통)","345kV #70-#71 SEC GIS (70-71-0) - 청양S/S 70-71-0 보통점검 - 즉시가압 가능","2024-06-19 09:00","2024-06-19 18:00","2024-06-19 09:00","2024-06-19 18:00","연속"]
[252,"전북","군산","군산S/S #3 M.Tr","군산P/O 170kV GIS 정밀점검 공사","군산S/S #3M.Tr 2차 GIS 정밀점검","2024-06-26 09:00","2024-06-27 18:00","2024-06-26 09:00","2024-06-27 18:00","연속"]
[253,"전북","군산","군산S/S #75 BUS","군산변전소 345kV GIS 대체공사","○ 362kV GIS 4000A (40→50kA) × 10CB 교체(4Bay) ○ 기타부대공사 1식","2024-06-18 09:00","2024-07-25 18:00","취소","취소","연속"]
[254,"전북","군산","군산S/S CB 7600","군산변전소 345kV GIS 대체공사(#1BUS 무부하가압)","○ 362kV GIS 40kV 4000A × 10CB 철거(4Bay, PT Bay 포함) ○ 362kV GIS 50kV 4000A × 10CB 설치(4Bay, PT Bay 포함) ○ 기타부대공사 × 1식","2024-06-16 18:00","2024-06-17 18:00","2024-06-16 18:00","2024-06-17 18:00","연속"]
[255,"전북","군산","군산S/S #70 BUS","군산변전소 345kV GIS 대체공사","○ 362kV GIS 40kV 4000A × 10CB 철거(4Bay, PT Bay 포함) ○ 362kV GIS 50kV 4000A × 10CB 설치(4Bay, PT Bay 포함) ○ 362kV GIS 50kV 4000A × 10CB 설치(4Bay, PT Bay 포함) ○ 기타부대공사 × 1식","2024-06-10 09:00","2024-06-17 18:00","취소","취소","연속"]
[256,"전북","군산","군산S/S CB 7600","군산변전소 345kV GIS 대체공사(#2BUS 무부하가압)","○ 362kV GIS 40kV 4000A × 10CB 철거(4Bay, PT Bay 포함) ○ 362kV GIS 50kV 4000A × 10CB 설치(4Bay, PT Bay 포함) ○ 기타부대공사 × 1식","2024-06-24 18:00","2024-06-25 18:00","2024-06-24 18:00","2024-06-25 18:00","연속"]
[257,"전북","군산","새만금S/S #3 M.Tr","군산P/O 345kV M.Tr OLTC 정밀점검","새만금S/S 345kV #3M.Tr OLTC 정밀점검","2024-06-13 09:00","2024-06-15 18:00","2024-06-13 09:00","2024-06-15 18:00","연속"]
[258,"전북","군산","새만금S/S #2 M.Tr","군산P/O 345kV M.Tr OLTC 정밀점검","새만금S/S 345kV #2M.Tr OLTC 정밀점검","2024-06-10 09:00","2024-06-12 18:00","2024-06-10 09:00","2024-06-12 18:00","연속"]
[259,"전북","김제","신김제S/S CB 7172","신김제S/S 345kV #1M.Tr 1차 7172 GIS 보통점검","신김제S/S 345kV #1M.Tr 1차 7172 GIS 보통점검","2024-06-05 09:00","2024-06-05 18:00","2024-06-05 09:00","2024-06-05 18:00","연속"]
[260,"전북","김제","신김제S/S #2 M.Tr","24년 김제P/O 부싱유 채유공사","부싱유 채유공사","2024-06-26 09:00","2024-06-26 18:00","2024-06-26 09:00","2024-06-26 18:00","연속"]
[261,"전북","김제","신김제S/S #4 M.Tr","24년 김제P/O 부싱유 채유공사","부싱유 채유공사","2024-06-25 09:00","2024-06-25 18:00","2024-06-25 09:00","2024-06-25 18:00","연속"]
[262,"전북","직할","신남원의령#1 T/L","'24년 가공송전 순시점검 위탁공사","□ 345kV 신남원-의령#1T/L No.180.99 □ 작업내용 : 가공지선 접지단자 설치","2024-06-18 09:00","2024-06-18 18:00","2024-06-18 09:00","2024-06-18 18:00","연속"]
[263,"전북","군산","군산S/S #2 M.Tr"," 군산S/S 170kV GIS대체공사(6차, 무부하가압)"," 군산S/S 170kV GIS대체공사(6차, 무부하가압)","2024-06-12 17:30","2024-06-12 18:00","2024-06-12 17:30","2024-06-12 18:00","연속"]
[264,"전북","군산","군산S/S #2 M.Tr"," 군산S/S 170kV GIS대체공사(6차, 무부하가압)"," 군산S/S 170kV GIS대체공사(6차, 무부하가압)","2024-06-16 18:00","2024-06-17 18:00","2024-06-16 18:00","2024-06-17 18:00","연속"]
[265,"전북","군산","군산S/S #2 M.Tr"," 군산S/S 170kV GIS대체공사(6차, 무부하가압)"," 군산S/S 170kV GIS대체공사(6차, 무부하가압)","2024-06-23 17:00","2024-06-24 18:00","2024-06-23 17:00","2024-06-24 18:00","연속"]
[266,"광주전남","광주","신광주S/S CB 7600","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-06-13 08:00","2024-06-13 18:00","2024-06-13 08:00","2024-06-13 18:00","연속"]
[267,"광주전남","광주","신광주S/S #4 M.Tr","2024~2025년 광주전력지사 변전협력회사 공사","-주변압기 보통점검 -7800,7872 보통","2024-06-24 09:00","2024-06-27 18:00","2024-06-24 09:00","2024-06-27 18:00","연속"]
[268,"광주전남","광주","신광주S/S #1 M.Tr","2024~2025년 광주전력지사 변전협력회사 공사","-주변압기 보통점검 -7172보통점검","2024-06-11 09:00","2024-06-14 18:00","2024-06-11 09:00","2024-06-14 18:00","연속"]
[269,"광주전남","광주","신광주S/S CB 7500","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-06-03 09:00","2024-06-03 18:00","2024-06-03 09:00","2024-06-03 18:00","연속"]
[270,"광주전남","광주","신광주S/S CB 7300","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-06-05 08:00","2024-06-05 18:00","2024-06-05 08:00","2024-06-05 18:00","연속"]
[271,"광주전남","광주","신광주S/S CB 7400","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-06-10 08:00","2024-06-10 18:00","2024-06-10 08:00","2024-06-10 18:00","연속"]
[272,"광주전남","광주","신광주S/S CB 7400","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-06-11 08:00","2024-06-11 18:00","2024-06-11 08:00","2024-06-11 18:00","연속"]
[273,"광주전남","광주","신광주S/S CB 7671","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-06-12 08:00","2024-06-12 18:00","2024-06-12 08:00","2024-06-12 18:00","연속"]
[274,"광주전남","광주","신남원신광주#1 T/L","신광주S/S 345kV #2M.Tr 교체공사","- 장기사용 주변압기 교체공사(무부하가압)","2024-06-26 13:00","2024-06-27 13:00","2024-06-26 13:00","2024-06-27 13:00","연속"]
[275,"광주전남","광주","신광주S/S CB 7800","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-06-03 08:00","2024-06-03 18:00","2024-06-03 08:00","2024-06-03 18:00","연속"]
[276,"광주전남","광주","신광주S/S CB 7872","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-06-04 08:00","2024-06-04 18:00","2024-06-04 08:00","2024-06-04 18:00","연속"]
[277,"광주전남","광주","신광주S/S #1 Sh.R CB","2024~2025년 광주전력지사 변전협력회사 공사","#1Sh.R 1차(7572) CB 조작시험 7500CB 보통점검","2024-06-04 09:00","2024-06-04 18:00","2024-06-04 09:00","2024-06-04 18:00","연속"]
[278,"광주전남","광주","신광주S/S CB 7472","신광주S/S 345kV #2M.Tr 교체공사","- 장기사용 주변압기 교체공사","2024-06-03 09:00","2024-06-30 18:00","2024-06-03 09:00","2024-06-30 18:00","연속"]
[279,"광주전남","광주","신광주S/S #1 BUS","24~25년 광주전력지사 변전협력회사 총액공사","장기사용 345kV #1BUS 모선보호반 교체","2024-06-10 08:00","2024-06-13 18:00","취소","취소","연속"]
[280,"광주전남","광주","신광주S/S #2 BUS","24~25년 광주전력지사 변전협력회사 총액공사","장기사용 345kV #2BUS 모선보호반 교체","2024-06-10 08:00","2024-06-13 18:00","취소","취소","연속"]
[281,"광주전남","순천","광양CC여수TP#2 T/L","2024 가공송전 위탁공사 (초기점검)","신설 345kV 광양CC-여수TP T/L No.1∼No.20호 초기점검","2024-06-05 09:00","2024-06-06 18:00","2024-06-05 09:00","2024-06-06 18:00","매일"]
[282,"광주전남","순천","광양CC여수TP#1 T/L","2024 가공송전 위탁공사 (초기점검)","신설 345kV 광양CC-여수TP T/L No.1∼No.20호 초기점검","2024-06-03 09:00","2024-06-04 18:00","2024-06-03 09:00","2024-06-04 18:00","매일"]
[283,"광주전남","순천","광양C/C #2 BUS","24-25년 순천전력지사 변전정비 총액공사","75BUS PT NFB 교체","2024-06-10 09:00","2024-06-10 18:00","2024-06-10 09:00","2024-06-10 18:00","연속"]
[284,"광주전남","순천","광양S/S SEC CB 70710","광양S/S 345kV #70-#71 SEC 절연열화 측정","광양S/S 345kV #70-#71 SEC 절연열화 측정(즉시가압가능)","2024-06-10 08:00","2024-06-10 18:00","2024-06-10 08:00","2024-06-10 18:00","연속"]
[285,"광주전남","순천","광양S/S SEC CB 75760","광양S/S 345kV #75-#76 SEC 절연열화 측정","광양S/S 345kV #75-#76 SEC 절연열화 측정(즉시가압가능)","2024-06-11 08:00","2024-06-11 18:00","2024-06-11 08:00","2024-06-11 18:00","연속"]
[286,"광주전남","순천","광양S/S CB 7871","광양S/S 345kV 신강진-광양#1T/L(7871) 절연열화 측정","광양S/S 345kV 신강진-광양#1T/L(7871) 절연열화 측정(즉시가압가능)","2024-06-24 08:00","2024-06-24 18:00","2024-06-24 08:00","2024-06-24 18:00","연속"]
[287,"광주전남","순천","광양S/S CB 7800","광양S/S 345kV 신강진-광양#1T/L(7800) 절연열화 측정","광양S/S 345kV 신강진-광양#1T/L(7800) 절연열화 측정(즉시가압가능)","2024-06-25 08:00","2024-06-25 18:00","2024-06-25 08:00","2024-06-25 18:00","연속"]
[288,"광주전남","순천","광양S/S CB 7771","광양S/S 345kV #신강진-광양#2T/L(7771) 절연열화 측정","광양S/S 345kV 신강진-광양#2T/L(7771) 절연열화 측정(즉시가압가능)","2024-06-26 08:00","2024-06-26 18:00","2024-06-26 08:00","2024-06-26 18:00","연속"]
[289,"광주전남","순천","광양S/S #70 BUS","345kV 광양S/S 362kV GIS 용량변경 교체공사(무부하)","345kV 광양S/S 362kV GIS 용량변경 교체공사(75BAY 무부하) - 362kV GIS(75BAY) 교체공사 무부하 가압","2024-06-03 07:00","2024-06-04 07:00","2024-06-03 07:00","2024-06-04 07:00","연속"]
[290,"광주전남","순천","광양S/S SEC CB 70710","345kV 광양S/S 362kV GIS 용량변경 교체공사(무부하)","345kV 광양S/S 362kV GIS 용량변경 교체공사(75BAY 무부하) - 362kV GIS(75BAY) 교체공사 무부하 가압","2024-06-03 07:00","2024-06-04 07:00","2024-06-03 07:00","2024-06-04 07:00","연속"]
[291,"광주전남","순천","광양S/S SEC CB 75760","345kV 광양S/S 362kV GIS 용량변경 교체공사(무부하)","345kV 광양S/S 362kV GIS 용량변경 교체공사(75BAY 무부하) - 362kV GIS(75BAY) 교체공사 무부하 가압","2024-06-04 07:00","2024-06-05 07:00","2024-06-04 07:00","2024-06-05 07:00","연속"]
[292,"광주전남","순천","광양S/S #75 BUS","345kV 광양S/S 362kV GIS 용량변경 교체공사(무부하)","345kV 광양S/S 362kV GIS 용량변경 교체공사(75BAY 무부하) - 362kV GIS(75BAY) 교체공사 무부하 가압","2024-06-04 07:00","2024-06-05 07:00","2024-06-04 07:00","2024-06-05 07:00","연속"]
[293,"광주전남","순천","광양하동TP#1 T/L","345kV 광양S/S 362kV GIS 용량변경 교체공사(인출변경)","345kV 광양S/S 362kV GIS 용량변경 교체공사(인출변경) - 광양하동TP #1선로 인출변경 원상복구","2024-06-05 07:00","2024-06-11 18:00","2024-06-05 07:00","2024-06-11 18:00","연속"]
[294,"광주전남","순천","광양하동TP#2 T/L","345kV 광양S/S 362kV GIS 용량변경 교체공사(인출변경)","345kV 광양S/S 362kV GIS 용량변경 교체공사(인출변경) - 광양하동TP #2선로 인출변경 원상복구","2024-06-12 07:00","2024-06-17 18:00","2024-06-12 07:00","2024-06-17 18:00","연속"]
[295,"광주전남","순천","신강진광양#1 T/L","345kV 광양S/S 362kV GIS 용량변경 교체공사(인출변경)","345kV 광양S/S 362kV GIS 용량변경 교체공사(인출변경) - 광양하동TP #2선로 인출변경 원상복구를 위한 안전이격","2024-06-12 07:00","2024-06-17 18:00","취소","취소","연속"]
[296,"광주전남","순천","광양S/S #3 M.Tr","24-25년 순천전력지사 변전협력회사 공사","광양S/S #3M.Tr 1차,2차 LA 대체, 3차 GPT 보통점검 및 추락방지장치 설치","2024-06-17 09:00","2024-06-19 18:00","2024-06-17 09:00","2024-06-19 18:00","연속"]
[297,"광주전남","순천","여수T/P CB 7472","24-25년 순천전력지사 변전정비 총액공사","PT 회로개선","2024-06-11 09:00","2024-06-11 18:00","2024-06-11 09:00","2024-06-11 18:00","연속"]
[298,"광주전남","순천","여수T/P #75 BUS","24-25년 순천전력지사 변전정비 총액공사","PT 회로개선","2024-06-11 09:00","2024-06-11 18:00","2024-06-11 09:00","2024-06-11 18:00","연속"]
[299,"광주전남","순천","여수T/P CB 7271","여수화력S/S 광양CC-여수TP #2T/L(7271) 절연열화 측정","여수화력S/S 345kV 광양CC-여수TP #2T/L(7271) 절연열화 측정(즉시가압가능)","2024-06-17 08:00","2024-06-17 18:00","2024-06-17 08:00","2024-06-17 18:00","연속"]
[300,"광주전남","순천","여수T/P CB 7372","여수화력S/S 345kV #3M.Tr 1차(7372) 절연열화 측정","여수화력S/S 345kV #3M.Tr 1차(7372) 절연열화 측정(즉시가압가능)","2024-06-28 08:00","2024-06-28 18:00","2024-06-28 08:00","2024-06-28 18:00","연속"]
[301,"광주전남","순천","여수T/P #1 Tie-Tr","24-25년 순천전력지사 변전협력회사 공사","#1M.Tr 1차 부싱 교체(A,C상), 추락방지장치 설치 및 4184,4189,4179-1 VCB 조작시험","2024-06-10 09:00","2024-06-14 18:00","2024-06-10 09:00","2024-06-14 18:00","연속"]
[302,"광주전남","순천","율촌CC여수TP T/L","345kV 율촌CC-여수TPT/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No.4~67호","2024-06-12 07:00","2024-06-18 18:00","2024-06-12 07:00","2024-06-18 18:00","매일"]
[303,"대구","경산","신경산S/S CB 7371","24년 경산P/O GIS 정밀점검 및 보통점검 공사","- 7371 GIS 보통점검","2024-06-27 09:30","2024-06-27 18:00","2024-06-27 09:30","2024-06-27 18:00","연속"]
[304,"대구","경산","신경산대구#2 T/L","345kV 울주-신경산 등 6개T/L 추락방지장치설치공사","(안전확보) 철탑추락방지장치 설치 - 작업구간 : No.31~107","2024-06-11 07:00","2024-06-24 18:00","2024-06-11 07:00","2024-06-24 18:00","연속"]
[305,"대구","칠곡","북대구S/S #1 M.Tr","북대구S/S #1M.Tr / 2차 GIS, LA 하자점검","북대구S/S #1M.Tr / 2차 GIS, LA 하자점검","2024-06-03 09:30","2024-06-04 18:00","2024-06-03 09:30","2024-06-04 18:00","연속"]
[306,"대구","포항","신영일S/S #3 M.Tr","2024~25년도 포항전력지사 변전총액공사","신영일S/S 7500,7572 GIS 보통점검. 4389 GIS 조작시험 및 보조RY교체, 전자변 교체","2024-06-24 09:00","2024-06-25 18:00","2024-06-24 09:00","2024-06-25 18:00","연속"]
[307,"대구","포항","신영일S/S #4 M.Tr","2024~25년도 포항전력지사 변전총액공사","신영일S/S 7700,7772, 4489 GIS 보통점검 및 보조RY교체","2024-06-26 09:00","2024-06-26 18:00","2024-06-26 09:00","2024-06-26 18:00","연속"]
[308,"대구","포항","신포항신영일 T/L","2024~25년도 포항전력지사 변전총액공사","345kV 신영일S/S 일근화관련 경보 분리(종합-&gt개별) 및 조작시험 등","2024-06-20 09:00","2024-06-20 18:00","2024-06-20 09:00","2024-06-20 18:00","연속"]
[309,"대구","포항","신영일안동CC T/L","2024~25년도 포항전력지사 변전총액공사","345kV 신영일S/S 일근화관련 경보 분리(종합-&gt개별) 및 조작시험 등","2024-06-19 09:00","2024-06-19 18:00","2024-06-19 09:00","2024-06-19 18:00","연속"]
[310,"대구","포항","신월성N/P CB 7472","24~25년도 포항전력지사 변전총액공사","신월성S/Y 7400,7472 GIS 정밀점검, 74BAY B/F반 대체","2024-06-10 09:00","2024-06-15 18:00","2024-06-10 09:00","2024-06-15 18:00","연속"]
[311,"대구","포항","신포항신월성NP#3 T/L","24~25년도 포항전력지사 변전총액공사","신월성S/Y 7400,7472 GIS 정밀점검, 74BAY B/F반 대체, 송전선로 보호반 대체","2024-06-10 09:00","2024-06-21 18:00","2024-06-10 09:00","2024-06-21 18:00","연속"]
[312,"대구","포항","월성NP신월성NP#1 T/L","24~25년도 포항전력지사 변전총액공사","신월성S/Y 73BAY B/F반 대체, 7322 가스 누기 보수","2024-06-27 09:00","2024-07-05 18:00","2024-06-27 09:00","2024-07-05 18:00","연속"]
[313,"대구","포항","신월성N/P CB 7372","24~25년도 포항전력지사 변전총액공사","신월성S/Y 73BAY B/F반 대체, 7322 가스 누기 보수","2024-06-27 09:00","2024-07-05 18:00","2024-06-27 09:00","2024-07-05 18:00","연속"]
[314,"대구","포항","신포항S/S #3 M.Tr","신포항S/S 345kV 주변압기측 현대화 공사","신포항S/S 345kV 주변압기측 현대화 공사","2024-06-03 08:00","2024-06-07 17:00","2024-06-17 08:00","2024-06-25 17:00","연속"]
[315,"대구","포항","신포항S/S #4 M.Tr","신포항S/S 345kV 주변압기측 현대화 공사","신포항S/S 345kV 주변압기측 현대화 공사","2024-06-10 08:00","2024-06-14 17:00","2024-07-15 08:00","2024-07-23 17:00","연속"]
[316,"대구","포항","월성N/P #76 BUS","월성N/P 연계 345kV GIS 용량대체공사(75Bay 대체)","월성N/P 연계 345kV GIS 용량대체공사 ○ 345kV GIS × 18CB 대체 ○ 보호반 설치 및 이설 ○ 제어케이블 포설 및 결선 ○ 기타 부대공사 × 1식","2024-06-25 09:00","2024-07-09 09:00","2024-06-25 09:00","2024-07-09 09:00","연속"]
[317,"대구","포항","월성N/P CB 7372","24~25년도 포항전력지사 변전총액공사","월성S/Y 7300,7372 GIS 보통점검, 7371 GIS 조작시험","2024-06-11 09:00","2024-06-12 18:00","2024-06-11 09:00","2024-06-12 18:00","연속"]
[318,"대구","포항","울주월성NP#1 T/L","월성N/P 연계 345kV GIS 용량대체공사(75Bay 대체)","월성N/P 연계 345kV GIS 용량대체공사 ○ 345kV GIS × 18CB 대체 ○ 보호반 설치 및 이설 ○ 제어케이블 포설 및 결선 ○ 기타 부대공사 × 1식","2024-06-18 09:00","2024-08-30 18:00","2024-06-18 09:00","2024-08-30 18:00","연속"]
[319,"대구","포항","월성N/P CB 7572","월성N/P 연계 345kV GIS 용량대체공사(75Bay 대체)","월성N/P 연계 345kV GIS 용량대체공사 ○ 345kV GIS × 18CB 대체 ○ 보호반 설치 및 이설 ○ 제어케이블 포설 및 결선 ○ 기타 부대공사 × 1식","2024-06-18 09:00","2024-08-30 18:00","2024-06-18 09:00","2024-08-30 18:00","연속"]
[320,"부산울산","동부산","고리N/P #2 CLR (CB 7577, 7677)","고리NP S/Y 345kV 7577 GIS 차단기 동작시험","고리NP S/Y 345kV 7577 GIS 차단기 동작시험 병행)7577GIS 절연열화 측정","2024-06-11 09:30","2024-06-11 17:00","취소","취소","연속"]
[321,"부산울산","동부산","고리N/P CB 7371","고리NP S/Y 7371 GIS 보통점검","고리NP S/Y 7371 GIS 보통점검 병행) 7371GIS 절연열화 측정","2024-06-04 09:30","2024-06-04 17:00","2024-06-04 09:30","2024-06-04 17:00","연속"]
[322,"부산울산","동부산","고리N/P #1 CLR (CB 7077, 7177)","고리NP S/Y 345kV 7077 GIS 차단기 동작시험","고리NP S/Y 345kV 7077 GIS 차단기 동작시험 병행)7077GIS 절연열화 측정","2024-06-10 09:30","2024-06-10 17:00","취소","취소","연속"]
[323,"부산울산","동부산","신고리고리NP#4 T/L","2024-2025년 동부산 가공송전 협력회사 공사","345kV 신고리-고리NP#4 지선 철거","2024-06-13 07:00","2024-06-13 18:00","취소","취소","연속"]
[324,"부산울산","동부산","신고리고리NP#1 T/L","2024-2025년 동부산 가공송전 협력회사 공사","345kV 신고리-고리NP#1 불량정비","2024-06-11 07:00","2024-06-12 18:00","취소","취소","연속"]
[325,"부산울산","동부산","신고리고리NP#2 T/L","765kV 신고리 5, 6호기 접속설비 공사","#2M.Tr 신설","2024-06-09 18:00","2024-06-10 18:00","2024-06-09 18:00","2024-06-10 18:00","연속"]
[326,"부산울산","동부산","신양산고리NP#1 T/L","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 용량부족차단기 교체공사(4차) - 76BAY 기기기초(MP) 관련 안전이격 휴전","2024-06-24 08:00","2024-06-26 18:00","2024-06-24 08:00","2024-06-26 18:00","연속"]
[327,"부산울산","북부산","북부산신울산#2 T/L","345kV 북부산-신울산 #2T/L 정밀점검","345kV 북부산-신울산 #2T/L 정밀점검 -점검대상 : 총 115기(No.1 ~ 110호 113기 및 S/T 2기)","2024-06-10 09:00","2024-06-18 18:00","2024-06-10 09:00","2024-06-18 18:00","연속"]
[328,"부산울산","북부산","북부산S/S #3 M.Tr","24-25년 북부산전력지사 변전총액공사","북부산S/S 345kV #3M.Tr 부싱절연유 채유","2024-06-04 08:00","2024-06-04 12:00","2024-06-04 08:00","2024-06-04 12:00","연속"]
[329,"부산울산","북부산","북부산S/S STATCOM CB","북부산S/S STATCOM 설치공사","STATCOM 부하 시험","2024-06-03 10:00","2024-06-30 18:00","2024-06-03 10:00","2024-06-30 18:00","연속"]
[330,"부산울산","북부산","북부산S/S CB 7A71","북부산S/S STATCOM 설치공사","STATCOM 부하 시험","2024-06-03 10:00","2024-06-30 18:00","취소","취소","연속"]
[331,"부산울산","북부산","신김해북부산#2 T/L","345kV 신김해-북부산 #2T/L 35.1 호 초기점검","345kV 신김해-북부산 #2T/L 35.1 호 초기점검","2024-06-08 09:00","2024-06-09 18:00","2024-06-08 09:00","2024-06-09 18:00","연속"]
[332,"부산울산","서부산","서부산S/S #3 Sh.R CB","서부산S/S 345kV #3Sh.R 보통점검","서부산S/S 345kV #3Sh.R 보통점검","2024-06-10 09:00","2024-06-12 18:00","2024-06-10 09:00","2024-06-12 18:00","연속"]
[333,"부산울산","서부산","서부산S/S #2 Sh.R CB","서부산S/S 345kV #2Sh.R 보통점검","서부산S/S 345kV #2Sh.R 보통점검","2024-06-03 09:00","2024-06-05 18:00","2024-06-03 09:00","2024-06-05 18:00","연속"]
[334,"부산울산","서부산","서부산S/S CB 7372","서부산S/S 345kV 7372 GIS 동작시험","서부산S/S 345kV 7372 GIS 동작시험","2024-06-07 09:00","2024-06-07 18:00","2024-06-07 09:00","2024-06-07 18:00","연속"]
[335,"부산울산","서부산","서부산S/S CB 7371","서부산S/S 345kV 7371 GIS 동작시험","서부산S/S 345kV 7371 GIS 동작시험","2024-06-05 09:00","2024-06-05 18:00","2024-06-05 09:00","2024-06-05 18:00","연속"]
[336,"부산울산","서부산","서부산S/S CB 7300","서부산S/S 345kV 7300 GIS 동작시험","서부산S/S 345kV 7300 GIS 동작시험","2024-06-05 09:00","2024-06-05 18:00","2024-06-05 09:00","2024-06-05 18:00","연속"]
[337,"부산울산","서부산","신김해신녹산#1 T/L","신녹산S/S 신김해-신녹산#1T/L 보호 PNL 대체","신녹산S/S 신김해-신녹산#1T/L 보호 PNL 대체","2024-06-17 09:00","2024-06-21 18:00","2024-06-17 09:00","2024-06-21 18:00","연속"]
[338,"부산울산","서부산","신녹산S/S #3 M.Tr","2024년 서부산전력지사 154kV GIS 정밀점검공사","2024년 서부산전력지사 154kV GIS 정밀점검공사","2024-06-06 10:00","2024-06-07 18:00","2024-06-06 10:00","2024-06-07 18:00","연속"]
[339,"부산울산","서부산","신김해신녹산#2 T/L","신녹산S/S 신김해-신녹산#2T/L 보호 PNL 대체","신녹산S/S 신김해-신녹산#2T/L 보호 PNL 대체","2024-06-10 09:00","2024-06-14 18:00","2024-06-10 09:00","2024-06-14 18:00","연속"]
[340,"부산울산","울산","남울산S/S CB 7572","24년 울산전력지사 변전협력회사 총액공사","- 2점절 균압콘덴서 절연열화 측정(7572)","2024-06-12 14:00","2024-06-12 18:00","2024-06-12 14:00","2024-06-12 18:00","연속"]
[341,"부산울산","울산","남울산S/S CB 7371","24년 울산전력지사 변전협력회사 총액공사","- 2점절 균압콘덴서 절연열화 측정(7371)","2024-06-12 09:00","2024-06-12 14:00","2024-06-12 09:00","2024-06-12 14:00","연속"]
[342,"부산울산","울산","동울산월성NP T/L","345kV 추락방지장치 설치공사","수평 추락방지장치 및 폴리머점퍼지지애자 설치 : 345kV 동울산-월성NPT/L 1~70호","2024-06-10 07:00","2024-06-21 18:00","2024-06-05 07:00","2024-06-18 18:00","연속"]
[343,"부산울산","울산","신온산S/S CB 7571","24년 울산전력지사 변전협력회사 총액공사","- 2점절 균압콘덴서 절연열화 측정(7571)","2024-06-13 14:00","2024-06-13 18:00","2024-06-13 14:00","2024-06-13 18:00","연속"]
[344,"부산울산","울산","신온산S/S CB 7172","24년 울산전력지사 변전협력회사 총액공사","- 2점절 균압콘덴서 절연열화 측정(7172)","2024-06-13 09:00","2024-06-13 14:00","2024-06-13 09:00","2024-06-13 14:00","연속"]
[345,"부산울산","울산","신온산남울산#1 T/L","2024년 가공송전 순시점검 위탁공사","- 345kV 신온산-남울산#1T/L 정밀점검 및 초기점검 - 작업구간 : 초기점검(1,2,4,5,16~19호), 정밀점검(20~21호) - 병가선로 : 154kV 남울산-신온산 #2T/L(18~21호의 자선로)","2024-06-17 08:30","2024-06-18 18:00","2024-06-17 08:30","2024-06-18 18:00","연속"]
[346,"부산울산","울산","신온산남울산#2 T/L","2024년 가공송전 순시점검 위탁공사","345kV 신온산-남울산 #2T/L 정밀점검 및 초기점검 - 작업구간 : 초기점검(1,2,4,5,16~19호), 정밀점검(22~신온산S/T) - 병가선로 : 154kV 남울산-신온산 #1T/L(18~21호의 자선로) 154kV 온산-처용 #1T/L(22~30호의 자선로)","2024-06-19 08:30","2024-06-21 18:00","2024-06-19 08:30","2024-06-21 18:00","연속"]
[347,"부산울산","울산","신울산S/S #4 M.Tr","24년 울산전력지사 변전협력회사 총액공사","- #4M.Tr 3차 현대화 - 부싱절연유채유(추적분석)","2024-06-03 09:00","2024-06-07 18:00","2024-06-03 09:00","2024-06-07 18:00","연속"]
[348,"부산울산","울산","신울산S/S #2 M.Tr","신울산S/S 345kV #2,4M.Tr 3차 현대화공사","- #2M.Tr 3차 현대화 - #2M.Tr 2차 관로설치","2024-06-24 09:00","2024-09-06 18:00","2024-06-24 09:00","2024-09-06 18:00","연속"]
[349,"부산울산","울산","신울산S/S #1 M.Tr","345kv신울산S/S STATCOM 설치공사","345kv신울산S/S STATCOM 설치공사 STATCOM용 소내변압기 설치","2024-06-10 09:00","2024-06-18 18:00","2024-06-10 09:00","2024-06-18 18:00","연속"]
[350,"부산울산","울산","울주S/S CB 7A71","24년 울산전력지사 변전협력회사 총액공사","- 2점절 균압콘덴서 절연열화 측정(7A71)","2024-06-19 09:00","2024-06-19 14:00","2024-06-19 09:00","2024-06-19 14:00","연속"]
[351,"부산울산","울산","울주S/S CB 7671","24년 울산전력지사 변전협력회사 총액공사","- 2점절 균압콘덴서 절연열화 측정","2024-06-18 11:00","2024-06-18 14:00","2024-06-18 11:00","2024-06-18 14:00","연속"]
[352,"부산울산","울산","울주S/S CB 7571","24년 울산전력지사 변전협력회사 총액공사","- 2점절 균압콘덴서 절연열화 측정","2024-06-18 09:00","2024-06-18 11:00","2024-06-18 09:00","2024-06-18 11:00","연속"]
[353,"부산울산","울산","울주S/S CB 7500","24년 울산전력지사 변전협력회사 총액공사","- 2점절 균압콘덴서 절연열화 측정","2024-06-18 14:00","2024-06-18 16:00","2024-06-18 14:00","2024-06-18 16:00","연속"]
[354,"부산울산","울산","울주S/S #3 M.Tr","24년 울산전력지사 변전협력회사 총액공사","- 2차 GIS 보통점검 - 2차 피뢰기 보통점검 - 1,2차 부싱 절연유 채유","2024-06-13 09:00","2024-06-14 18:00","2024-06-20 09:00","2024-06-21 18:00","연속"]
[355,"부산울산","울산","울주S/S CB 7A00","24년 울산전력지사 변전협력회사 총액공사","- 2점절 균압콘덴서 절연열화 측정(7A00)","2024-06-19 14:00","2024-06-19 18:00","2024-06-19 14:00","2024-06-19 18:00","연속"]
[356,"부산울산","직할","신대연S/S #2 Sh.R CB","신대연S/S 345kV #2Sh.R GIS 정밀점검","신대연S/S 345kV #2Sh.R GIS 정밀점검","2024-06-10 09:00","2024-06-10 18:00","2024-06-10 09:00","2024-06-10 18:00","연속"]
[357,"경남","진주","신남원의령#1 T/L","345kV 신남원-의령T/L 추락방지장치 설치작업","345kV 신남원-의령T/L 추락방지장치 설치작업 대상 : 78~83, 117~121호(11기)","2024-06-01 07:00","2024-06-02 18:00","취소","취소","매일"]
[358,"경남","김해송변전부","신김해북부산#2 T/L","신김해S/S 신김해북부산#2 T/L 휴전","신김해S/S 7571, 7500 초기점검","2024-06-01 09:30","2024-06-02 17:30","2024-06-01 09:30","2024-06-02 17:30","연속"]
[359,"경남","함안","신마산신고성#2 T/L","OPGW 항공장애표시구 설치공사","항공장애표시구 1개 교체","2024-06-02 09:00","2024-06-02 18:00","2024-06-02 09:00","2024-06-02 18:00","연속"]
[360,"경남","진주","신남원의령#2 T/L","345kV 신남원-의령T/L 추락방지장치 설치작업","345kV 신남원-의령T/L 추락방지장치 설치작업 대상 : 78~83, 117~121호(11기)","2024-06-03 07:00","2024-06-04 18:00","2024-06-03 07:00","2024-06-04 18:00","매일"]
[361,"경남","직할","창원신고성#2 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-06-03 07:00","2024-06-04 18:00","2024-06-08 07:00","2024-06-09 18:00","매일"]
[362,"경남","직할","신김해창원#1 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-06-03 07:00","2024-06-07 18:00","2024-06-03 07:00","2024-06-09 18:00","매일"]
[363,"경남","김해송변전부","신김해신녹산#1 T/L","신김해S/S 신김해신녹산#1 T/L 휴전","7771절연열화,조작시험, 7700절연열화측정","2024-06-03 09:30","2024-06-03 17:30","2024-06-03 09:30","2024-06-03 17:30","연속"]
[364,"경남","함안","신마산S/S CB 7400","신마산S/S 345kV의령#2TL-#4M.Tr 1차 TIE 누기보수 외","신마산S/S 345kV 의령#2T/L-#4M.Tr 1차 TIE GIS 누기보수 및 보통점검","2024-06-03 09:30","2024-06-04 17:30","2024-06-03 09:30","2024-06-04 17:30","연속"]
[365,"경남","진주","하동T/P CB 7400","하동T/P 345kV 7400, 7472 GIS 조작시험","하동T/P 345kV 7400, 7472 GIS 조작시험","2024-06-03 10:00","2024-06-03 18:00","2024-06-03 10:00","2024-06-03 18:00","연속"]
[366,"경남","진주","하동T/P CB 7472","하동T/P 345kV 7400, 7472 GIS 조작시험","하동T/P 345kV 7400, 7472 GIS 조작시험","2024-06-03 10:00","2024-06-03 18:00","2024-06-03 10:00","2024-06-03 18:00","연속"]
[367,"경남","함안","의령신마산#2 T/L","신마산S/S 345kV 의령#2T/L-#4M.Tr 1차 TIE 시험가압","신마산S/S 345kV 의령#2T/L-#4M.Tr 1차 TIE GIS 시험가압(1H)","2024-06-04 17:30","2024-06-04 18:30","취소","취소","연속"]
[368,"경남","함안","북경남S/S CB 7771","북경남S/S 345kV #5Sh.R 1차 선로측 GIS 균압콘덴서측정","북경남S/S 345kV #5Sh.R 1차 선로측 GIS(7771) 균압콘덴서측정[단독휴전]","2024-06-05 09:30","2024-06-05 13:30","2024-06-05 09:30","2024-06-05 13:30","연속"]
[369,"경남","김해송변전부","신김해S/S CB 7172","신김해S/S 345kV 신김해-창원#1T/L GIS(7172)휴전","7172 조작시험","2024-06-05 09:30","2024-06-05 14:30","취소","취소","연속"]
[370,"경남","진주","하동T/P CB 7500","하동T/P 345kV 7500, 7572 GIS 조작시험","하동T/P 345kV 7500, 7572 GIS 조작시험","2024-06-05 10:00","2024-06-05 18:00","2024-06-05 10:00","2024-06-05 18:00","연속"]
[371,"경남","진주","하동T/P CB 7572","하동T/P 345kV 7500, 7572 GIS 조작시험","하동T/P 345kV 7500, 7572 GIS 조작시험","2024-06-05 10:00","2024-06-05 18:00","2024-06-05 10:00","2024-06-05 18:00","연속"]
[372,"경남","함안","북경남S/S #6Sh.R CB","북경남S/S 345kV #6Sh.R 1차 GIS 보통점검 외","북경남S/S 345kV #6Sh.R 1차 GIS(7979) 보통점검 및 균압콘덴서측정[단독휴전]","2024-06-07 09:30","2024-06-07 17:30","2024-06-07 09:30","2024-06-07 17:30","연속"]
[373,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#2T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.134~151 3. 기타사항 : 345kV의령-산청양수T/L 과 병가","2024-06-08 07:30","2024-06-09 18:00","2024-06-08 07:30","2024-06-09 18:00","매일"]
[374,"경남","진주","의령산청양수#1 T/L","345lkV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#1T/L측 수직,수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.112~129 3.기타사항 : 345kV 의령-하동화력 T/L과 병가 구간","2024-06-08 07:30","2024-06-09 18:00","2024-06-08 07:30","2024-06-09 18:00","매일"]
[375,"경남","김해송변전부","신김해S/S #5 M.Tr","신김해S/S 345kV #5 M.Tr 휴전","7600,7672,6544 조작시험 1,2차 중성부싱 절연유채취","2024-06-08 09:30","2024-06-09 17:30","2024-06-08 09:30","2024-06-09 17:30","연속"]
[376,"경남","직할","신김해창원#1 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-06-10 07:00","2024-06-14 18:00","2024-06-11 07:00","2024-06-14 18:00","매일"]
[377,"경남","진주","의령S/S #1 M.Tr","의령S/S 345kV #1M.Tr 정밀점검","의령S/S 345kV #1M.Tr 정밀점검 [병행] OLTC 정밀점검 [병행] 1, 2, 3차 LA(A, B, C) 대체 [병행] 3차 PT(A, B, C) 보통 [병행] 345kV #1M.Tr 1차(7372) GIS 정밀","2024-06-10 09:00","2024-06-21 18:00","2024-06-10 09:00","2024-06-21 18:00","연속"]
[378,"경남","김해송변전부","신김해S/S CB 7272","신김해S/S 345kV 신김해-창원#2T/L GIS(7272)휴전","7272절연열화,조작시험","2024-06-10 09:30","2024-06-10 15:30","취소","취소","연속"]
[379,"경남","김해송변전부","신김해신녹산#2 T/L","신김해S/S 신김해신녹산#2 T/L 휴전","7871절연열화,조작시험, 7800절연열화측정","2024-06-10 09:30","2024-06-10 17:30","2024-06-10 09:30","2024-06-10 17:30","연속"]
[380,"경남","함안","북경남S/S #7Sh.R CB","북경남S/S 345kV #7Sh.R 1차 GIS 보통점검 외","북경남S/S 345kV #7Sh.R 1차 선로측 GIS(7B79) 보통점검 및 균압콘덴서측정[단독휴전]","2024-06-10 09:30","2024-06-10 17:30","2024-06-10 09:30","2024-06-10 17:30","연속"]
[381,"경남","함안","북경남S/S #5Sh.R CB","북경남S/S 345kV #5Sh.R 1차 GIS(7779) 보통점검 외","북경남S/S 345kV #5Sh.R 1차 GIS(7779) 보통점검 외[단독휴전]","2024-06-12 09:30","2024-06-12 17:30","2024-06-12 09:30","2024-06-12 17:30","연속"]
[382,"경남","김해송변전부","신김해S/S CB 7772","신김해S/S 345kV #3 M.Tr 1차 GIS(7772)휴전","7772 절연열화측정","2024-06-13 09:30","2024-06-13 14:30","2024-06-13 09:30","2024-06-13 14:30","연속"]
[383,"경남","함안","북경남S/S CB 7B72","북경남S/S 345kV 신옥천-북경남T/L GIS(7B72) 보통점검 외","북경남S/S 345kV 신옥천-북경남T/L GIS(7B72) 보통점검 외[단독휴전]","2024-06-13 09:30","2024-06-13 17:30","2024-06-13 09:30","2024-06-13 17:30","연속"]
[384,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#2T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.134~151 3. 기타사항 : 345kV의령-산청양수T/L 과 병가","2024-06-15 07:30","2024-06-16 18:00","2024-06-15 07:30","2024-06-16 18:00","매일"]
[385,"경남","진주","의령산청양수#1 T/L","345lkV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#1T/L측 수직,수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.112~129 3.기타사항 : 345kV 의령-하동화력 T/L과 병가 구간","2024-06-15 07:30","2024-06-16 18:00","2024-06-15 07:30","2024-06-16 18:00","매일"]
[386,"경남","직할","신김해창원#2 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-06-17 07:00","2024-06-21 18:00","2024-06-19 07:00","2024-06-21 18:00","매일"]
[387,"경남","함안","신마산S/S CB 7171","신마산S/S 345kV 신마산-신김해#2T/L GIS 보통점검","신마산S/S 345kV 신마산-신김해#2T/L GIS(7171) 보통점검[단독휴전]","2024-06-17 09:30","2024-06-17 17:30","2024-06-17 09:30","2024-06-17 17:30","연속"]
[388,"경남","함안","신마산S/S CB 7100","신마산S/S 345kV 신김해#2TL-#1 M.Tr 1차 TIE 보통점검","신마산S/S 345kV 신김해#2T/L-#1 M.Tr 1차 TIE GIS(7100) 보통점검[단독휴전]","2024-06-18 09:30","2024-06-18 17:30","2024-06-18 09:30","2024-06-18 17:30","연속"]
[389,"경남","진주","의령산청양수#2 T/L","시험가압 선로(의령 345kV #1M.Tr/1차 GIS(7372) 정밀)","의령S/S 345kV #1M.Tr/1차 GIS(7372) 정밀점검 시험가압 선로","2024-06-19 10:00","2024-06-21 18:00","2024-06-19 10:00","2024-06-21 18:00","연속"]
[390,"경남","통영","신고성S/S CB 7300","신고성S/S 3호기 7300 GIS 보통점검","신고성S/S 3호기 7300CB 보통점검","2024-06-20 09:30","2024-06-20 18:00","2024-06-20 09:30","2024-06-20 18:00","연속"]
[391,"경남","통영","신고성S/S CB 7371","신고성S/S 3호기 7371 GIS 보통점검","신고성S/S 3호기 7371CB 보통점검","2024-06-21 09:30","2024-06-21 18:00","2024-06-21 09:30","2024-06-21 18:00","연속"]
[392,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#1T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.134~151 3. 기타사항 : 345kV의령-산청양수T/L과 병가","2024-06-22 07:30","2024-06-23 18:00","2024-06-22 07:30","2024-06-23 18:00","매일"]
[393,"경남","진주","의령산청양수#2 T/L","345lkV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#2T/L측 수직,수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.112~129 3.기타사항 : 345kV 의령-하동화력 T/L과 병가 구간","2024-06-22 07:30","2024-06-23 18:00","2024-06-22 07:30","2024-06-23 18:00","매일"]
[394,"경남","직할","신김해창원#2 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-06-24 07:00","2024-06-28 18:00","2024-06-24 07:00","2024-06-28 18:00","매일"]
[395,"경남","진주","의령산청양수#2 T/L","의령S/S 345kV 의령-산청양수#2T/L GIS 정밀점검","의령S/S 345kV 의령-산청양수#2T/L GIS 정밀점검 [병행1] 산청양수 345kV 7200 GIS 조작, 7172 GIS 보통 [병행2] LA(A, B, C) 초기, PT A 초기 / B, C 보통","2024-06-24 09:00","2024-06-28 18:00","2024-06-24 09:00","2024-06-28 18:00","연속"]
[396,"경남","함안","신마산S/S CB 7371","신마산S/S 345kV 의령-신마산#1T/L GIS 보통점검","신마산S/S 345kV 의령-신마산#1T/L GIS(7371)보통점검[단독휴전]","2024-06-24 09:30","2024-06-24 17:30","2024-06-24 09:30","2024-06-24 17:30","연속"]
[397,"경남","함안","신마산S/S CB 7300","신마산S/S 345kV 의령#1T/L-#3 M.Tr TIE 보통점검","신마산S/S 345kV 의령#1T/L-#3 M.Tr 1차 TIE GIS(7300)보통점검[단독휴전]","2024-06-25 09:30","2024-06-25 17:30","2024-06-25 09:30","2024-06-25 17:30","연속"]
[398,"경남","함안","신마산S/S CB 7271","신마산S/S 345kV 신마산-신김해#1T/L GIS 보통점검","신마산S/S 345kV 신마산-신김해#1T/L GIS(7271) 보통점검[단독휴전]","2024-06-27 09:30","2024-06-27 17:30","2024-06-27 09:30","2024-06-27 17:30","연속"]
[399,"경남","함안","신마산S/S CB 7200","신마산S/S 345kV 신김해#1T/L-#2 M.Tr TIE 보통점검","신마산S/S 345kV 신김해#1T/L-#2 M.Tr 1차 TIE GIS(7200) 보통점검[단독휴전]","2024-06-28 09:30","2024-06-28 17:30","2024-06-28 09:30","2024-06-28 17:30","연속"]
[400,"경남","진주","의령산청양수#2 T/L","345lkV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#2T/L측 수직,수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.112~129 3.기타사항 : 345kV 의령-하동화력 T/L과 병가 구간","2024-06-29 07:30","2024-06-30 18:00","2024-06-29 07:30","2024-06-30 18:00","매일"]
[401,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#1T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.134~151 3. 기타사항 : 345kV의령-산청양수T/L과 병가","2024-06-29 07:30","2024-06-30 18:00","2024-06-29 07:30","2024-06-30 18:00","매일"]

{"sheet":"154설비","index":2,"n_rows":713,"n_cols":11,"rows_kept":713,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2024년도 6월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","광장뚝도#2 T/L","2024년 성동P/O 변전협력회사 공사","- 154kV GIS 보통점검","2024-06-04 09:00","2024-06-04 18:00","2024-06-04 09:00","2024-06-04 18:00","연속"]
[2,"서울","성동","구의광장#2 T/L","2024년 성동P/O 170kV GIS 정밀점검","- 170kV GIS 정밀점검","2024-06-24 09:00","2024-06-25 18:00","취소","취소","연속"]
[3,"서울","성동","구의광장#1 T/L","2024년 성동P/O 170kV GIS 정밀점검(시험가압)","- 170kV GIS 정밀점검","2024-06-14 16:00","2024-06-14 18:00","취소","취소","연속"]
[4,"서울","성동","화양광장 T/L","2024년 성동P/O 변전협력회사 공사","- 154kV GIS 보통점검","2024-06-11 09:30","2024-06-11 17:00","취소","취소","연속"]
[5,"서울","성동","미금광장 T/L","2024년 성동P/O 변전협력회사 공사","- 154kV GIS 보통점검","2024-06-10 09:30","2024-06-10 17:00","취소","취소","연속"]
[6,"서울","성동","광장뚝도#1 T/L","2024년 성동P/O 변전협력회사 공사","- 154kV GIS 보통점검","2024-06-03 09:30","2024-06-03 17:00","2024-06-03 09:30","2024-06-03 17:00","연속"]
[7,"서울","성동","군자화양#1 T/L","2024년 성동P/O 변전협력회사 공사","- 154kV GIS 보통점검","2024-06-12 09:30","2024-06-12 17:00","취소","취소","연속"]
[8,"서울","성동","군자화양#2 T/L","2024년 성동P/O 변전협력회사 공사","- 154kV GIS 보통점검","2024-06-13 09:30","2024-06-13 17:00","취소","취소","연속"]
[9,"서울","성동","성수뚝도#2 T/L","2024년 성동P/O 170kV GIS 정밀점검","- 170kV GIS 정밀점검","2024-06-28 09:00","2024-06-29 18:00","취소","취소","연속"]
[10,"서울","성동","성수뚝도#1 T/L","2024년 성동P/O 170kV GIS 정밀점검","- 170kV GIS 정밀점검","2024-06-26 09:00","2024-06-27 18:00","취소","취소","연속"]
[11,"서울","성동","광장뚝도#1 T/L","2024~25년 성동전력지사 변전협력회사 공사","170kV GIS 보통점검","2024-06-11 10:00","2024-06-11 18:00","2024-06-11 10:00","2024-06-11 18:00","연속"]
[12,"서울","성동","군자성수 T/L","2024~25년 성동전력지사 변전협력회사 공사","170kV GIS 보통점검","2024-06-10 10:00","2024-06-10 18:00","취소","취소","연속"]
[13,"서울","성동","수유미아 T/L","수유분기 170kV GIS 증설공사","- 170kV GIS 증설공사 관련 설비 감압(증설 옆 베이) - #2BUS 시험 가압","2024-06-17 09:00","2024-06-24 18:00","2024-06-17 09:00","2024-06-24 18:00","연속"]
[14,"서울","성동","수유미아 T/L","수유분기 170kV GIS 증설공사","- 170kV GIS 증설공사 관련 설비 감압(증설 옆 베이) - #1BUS 시험 가압","2024-06-10 09:00","2024-06-16 18:00","2024-06-10 09:00","2024-06-16 18:00","연속"]
[15,"서울","중부","녹번세종로 T/L","154kV 녹번S/S #4M.Tr용 GIS 설치공사","154kV 녹번S/S #4M.Tr용 1차 GIS 설치공사 무부하가압","2024-06-19 09:00","2024-06-20 13:00","2024-06-19 09:00","2024-06-20 13:00","연속"]
[16,"서울","중부","녹번세종로 T/L","154kV 녹번S/S #4M.Tr용 GIS 설치공사","154kV 녹번S/S #4M.Tr용 1차 GIS 설치공사 무부하가압","2024-06-26 09:00","2024-06-27 13:00","2024-06-26 09:00","2024-06-27 13:00","연속"]
[17,"서울","중부","당인리S/S SEC CB 60610","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검","2024-06-20 10:00","2024-06-21 18:00","2024-06-20 10:00","2024-06-21 18:00","연속"]
[18,"서울","중부","당인리S/S #60 BUS","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검","2024-06-21 10:00","2024-06-21 18:00","2024-06-21 10:00","2024-06-21 18:00","연속"]
[19,"서울","중부","당인리S/S #61 BUS","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검(시험가압)","2024-06-27 10:00","2024-06-27 18:00","2024-06-27 10:00","2024-06-27 18:00","연속"]
[20,"서울","중부","당인리S/S CB 6200","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검","2024-06-26 10:00","2024-06-27 18:00","2024-06-26 10:00","2024-06-27 18:00","연속"]
[21,"서울","중부","당인리S/S #60 BUS","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검(시험가압)","2024-06-19 10:00","2024-06-19 18:00","2024-06-19 10:00","2024-06-19 18:00","연속"]
[22,"서울","중부","당인리S/S CB 6100","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검","2024-06-18 10:00","2024-06-19 18:00","2024-06-18 10:00","2024-06-19 18:00","연속"]
[23,"서울","중부","중부당인리#1 T/L","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검","2024-06-19 10:00","2024-06-19 18:00","2024-06-19 10:00","2024-06-19 18:00","연속"]
[24,"서울","중부","중부당인리#2 T/L","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검","2024-06-25 10:00","2024-06-25 18:00","2024-06-25 10:00","2024-06-25 18:00","연속"]
[25,"서울","중부","당인리S/S #65 BUS","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검","2024-06-25 10:00","2024-06-25 18:00","2024-06-25 10:00","2024-06-25 18:00","연속"]
[26,"서울","중부","당인리S/S SEC CB 65660","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검","2024-06-24 10:00","2024-06-25 18:00","2024-06-24 10:00","2024-06-25 18:00","연속"]
[27,"서울","중부","중부당인리#1 T/L","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검","2024-06-21 10:00","2024-06-21 18:00","2024-06-21 10:00","2024-06-21 18:00","연속"]
[28,"서울","중부","능곡상암#1 T/L","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검","2024-06-20 10:00","2024-06-20 18:00","2024-06-20 10:00","2024-06-20 18:00","연속"]
[29,"서울","중부","능곡상암#1 T/L","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검","2024-06-11 10:00","2024-06-11 18:00","2024-06-11 10:00","2024-06-11 18:00","연속"]
[30,"서울","중부","능곡상암#2 T/L","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검","2024-06-07 10:00","2024-06-07 18:00","2024-06-07 10:00","2024-06-07 18:00","연속"]
[31,"서울","중부","능곡상암#1 T/L","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검","2024-06-04 10:00","2024-06-04 18:00","2024-06-04 10:00","2024-06-04 18:00","연속"]
[32,"서울","중부","옥인운니#2 T/L","2024년 중부전력지사 170kV GIS 정밀점검(보통)","170kV GIS 보통점검","2024-06-20 10:00","2024-06-20 18:00","2024-06-20 10:00","2024-06-20 18:00","연속"]
[33,"서울","중부","옥인운니#1 T/L","2024년 중부전력지사 170kV GIS 정밀점검(보통)","170kV GIS 보통점검","2024-06-19 10:00","2024-06-19 18:00","2024-06-19 10:00","2024-06-19 18:00","연속"]
[34,"서울","중부","중부S/S #66 BUS","중부S/S 154kV 장기사용 GIS 교체공사(2차)","- 154kV GIS 교체(#6200B/T, 중부신촌T/L, 중부아현T/L) - 기타 부대공사","2024-06-13 13:00","2024-06-28 14:00","2024-06-14 09:00","2024-06-29 14:00","연속"]
[35,"서울","중부","중부연대 T/L","중부S/S 154kV 장기사용 GIS 교체공사(2차 시험가압용)","- 154kV GIS 교체(#6200B/T, 중부신촌T/L, 중부아현T/L) - 기타 부대공사","2024-06-27 17:00","2024-06-28 14:00","취소","취소","연속"]
[36,"서울","중부","중부S/S #61 BUS","중부S/S 154kV 장기사용 GIS 교체공사(2차)","#61BUS 인터록시험 및 조작시험","2024-06-28 14:00","2024-06-28 18:00","2024-06-29 14:00","2024-06-29 18:00","연속"]
[37,"서울","중부","중부연대 T/L","중부S/S 154kV 장기사용 GIS 교체공사(2차 시험가압용)","- 154kV GIS 교체(#6200B/T, 중부신촌T/L, 중부아현T/L) - 기타 부대공사","2024-06-12 17:00","2024-06-13 13:00","취소","취소","연속"]
[38,"서울","중부","중부S/S #61 BUS","중부S/S 154kV 장기사용 GIS 교체공사(2차)","- 154kV GIS 교체(#6200B/T, 중부신촌T/L, 중부아현T/L) - 기타 부대공사","2024-06-03 09:00","2024-06-13 13:00","2024-06-03 09:00","2024-06-14 09:00","연속"]
[39,"서울","직할","용두안암#1 T/L","용두S/S 154kV #3M.Tr 증설공사","용두S/S 154kV #3M.Tr 1차 GIS 설치 관련 모선도킹시 인접 감압BAY 및 무부하가압 시험가압선로","2024-06-17 09:00","2024-06-21 18:00","2024-06-17 09:00","2024-06-21 18:00","연속"]
[40,"서울","직할","용두안암#1 T/L","용두S/S 154kV #3M.Tr 증설공사","용두S/S 154kV #3M.Tr 1차 GIS 설치 관련 모선도킹시 인접BAY 감압 및 무부하가압 시험가압선로","2024-06-24 09:00","2024-06-28 18:00","2024-06-24 09:00","2024-06-28 18:00","연속"]
[41,"서울","직할","운니원남#1 T/L","24년 직할 변전정비협력회사 총액공사","운니 : 조작시험 원남 : 조작시험","2024-06-03 09:00","2024-06-03 18:00","2024-06-03 09:00","2024-06-03 18:00","연속"]
[42,"서울","직할","운니원남#2 T/L","24년 직할 변전정비협력회사 총액공사","운니 : 조작시험 원남 : 조작시험","2024-06-04 09:00","2024-06-04 18:00","2024-06-04 09:00","2024-06-04 18:00","연속"]
[43,"서울","직할","원남미아#2 T/L","24년 직할 변전정비협력회사 총액공사","미아 : 조작시험 원남 : 조작시험","2024-06-05 09:00","2024-06-05 18:00","2024-06-05 09:00","2024-06-05 18:00","연속"]
[44,"서울","직할","중앙서소문 T/L","중앙서소문 T/L EBG 가스채취밸브 설치","중앙서소문 T/L EBG 가스채취밸브 설치","2024-06-03 09:00","2024-06-04 18:00","2024-06-03 09:00","2024-06-04 18:00","연속"]
[45,"남서울","영등포","마곡가양#1 T/L","24년도 영등포전력지사 154kV GIS 정밀점검공사","24년도 영등포전력지사 154kV GIS 정밀점검공사 대상 : 마곡-가양#1T/L","2024-06-01 09:00","2024-06-02 18:00","2024-06-01 09:00","2024-06-02 18:00","연속"]
[46,"남서울","동서울","동서울S/S SEC CB 63640","2024~2025년도 동서울전력지사 변전협력회사 총액공사","63-64 BUS-SEC GIS하자점검","2024-06-03 09:00","2024-06-03 18:00","2024-06-03 09:00","2024-06-03 18:00","연속"]
[47,"남서울","영등포","신광명천왕#1 T/L","효성제 170kV GIS 메커니즘 점검","효성제 170kV GIS 메커니즘 점검","2024-06-03 09:00","2024-06-03 18:00","2024-06-03 09:00","2024-06-03 18:00","연속"]
[48,"남서울","영등포","가양등촌#1 T/L","24년도 영등포전력지사 154kV GIS 정밀점검공사","24년도 영등포전력지사 154kV GIS 정밀점검공사 대상 : 가양-등촌#1T/L","2024-06-03 09:00","2024-06-04 18:00","2024-06-03 09:00","2024-06-04 18:00","연속"]
[49,"남서울","동서울","동서울서종#1 T/L","세종-포천 고속도로 건설 지장선로 지중화공사","154kV 동서울-서종T/L No.92 인수검사 이상내역 조치작업 - 상표시찰 부착","2024-06-03 09:00","2024-06-03 18:00","2024-06-03 09:00","2024-06-03 18:00","연속"]
[50,"남서울","직할","신문래영오#1 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2024-06-03 09:00","2024-06-03 18:00","2024-06-03 09:00","2024-06-03 18:00","연속"]
[51,"남서울","동서울","동서울서종#2 T/L","세종-포천 고속도로 건설 지장선로 지중화공사","154kV 동서울-서종T/L No.92 인수검사 이상내역 조치작업 - 상표시찰 부착","2024-06-04 09:00","2024-06-04 18:00","2024-06-04 09:00","2024-06-04 18:00","연속"]
[52,"남서울","직할","신문래영오#2 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2024-06-04 09:00","2024-06-04 18:00","2024-06-04 09:00","2024-06-04 18:00","연속"]
[53,"남서울","동서울","동서울S/S SEC CB 68690","2024~2025년도 동서울전력지사 변전협력회사 총액공사","68-69 BUS-SEC GIS하자점검","2024-06-04 09:00","2024-06-04 18:00","2024-06-04 09:00","2024-06-04 18:00","연속"]
[54,"남서울","영등포","대방신길#2 T/L","2024~25년 영등포전력지사 변전협력회사 총액공사","대방신길#2 조작시험","2024-06-04 09:00","2024-06-04 18:00","2024-06-04 09:00","2024-06-04 18:00","연속"]
[55,"남서울","영등포","신광명천왕#2 T/L","효성제 170kV GIS 메커니즘 점검","효성제 170kV GIS 메커니즘 점검","2024-06-04 09:00","2024-06-04 18:00","2024-06-04 09:00","2024-06-04 18:00","연속"]
[56,"남서울","영등포","신광명천왕#3 T/L","효성제 170kV GIS 메커니즘 점검","효성제 170kV GIS 메커니즘 점검","2024-06-05 09:00","2024-06-05 18:00","2024-06-05 09:00","2024-06-05 18:00","연속"]
[57,"남서울","동서울","동서울S/S CB 6500","2024~2025년도 동서울전력지사 변전협력회사 총액공사","6500 BUS-TIE GIS하자점검","2024-06-05 09:00","2024-06-05 18:00","2024-06-05 09:00","2024-06-05 18:00","연속"]
[58,"남서울","영등포","가양등촌#2 T/L","24년도 영등포전력지사 154kV GIS 정밀점검공사","24년도 영등포전력지사 154kV GIS 정밀점검공사 대상 : 가양-등촌#2T/L","2024-06-05 09:00","2024-06-06 18:00","2024-06-05 09:00","2024-06-06 18:00","연속"]
[59,"남서울","동서울","송파석촌#2 T/L","EBG 해체점검공사","154kV 송파-석촌T/L EBG 해체점검","2024-06-06 17:00","2024-06-29 18:00","2024-06-06 17:00","2024-06-29 18:00","연속"]
[60,"남서울","영등포","화곡S/S CB 6100","2024~25년 영등포전력지사 변전협력회사 총액공사","화곡S/S 6100 조작시험","2024-06-07 09:00","2024-06-07 18:00","2024-06-07 09:00","2024-06-07 18:00","연속"]
[61,"남서울","영등포","마곡가양#2 T/L","24년도 영등포전력지사 154kV GIS 정밀점검공사","24년도 영등포전력지사 154kV GIS 정밀점검공사 대상 : 마곡-가양#2T/L","2024-06-08 09:00","2024-06-09 18:00","2024-06-08 09:00","2024-06-09 18:00","연속"]
[62,"남서울","동서울","탄천대치#2 T/L","154kV 탄천-대치T/L 지장선로 이설공사","서울시 이설요청에 따른 154kV 탄천-대치T/L 일부구간 이설 및 전구간 케이블 교체","2024-06-10 08:00","2024-07-30 18:00","취소","취소","연속"]
[63,"남서울","영등포","신광명온수 T/L","효성제 170kV GIS 메커니즘 점검","효성제 170kV GIS 메커니즘 점검","2024-06-10 09:00","2024-06-10 14:00","취소","취소","연속"]
[64,"남서울","영등포","천왕오류#1 T/L","154kV 천왕-오류#1T/L 보호반 교체","154kV 천왕-오류#1T/L 보호반 교체","2024-06-10 09:00","2024-06-12 14:00","2024-06-10 09:00","2024-06-12 14:00","연속"]
[65,"남서울","영등포","천왕오류#2 T/L","154kV 천왕-오류#2T/L 보호반 교체","154kV 천왕-오류#2T/L 보호반 교체","2024-06-12 14:00","2024-06-14 18:00","2024-06-12 14:00","2024-06-14 18:00","연속"]
[66,"남서울","영등포","신광명광명#2 T/L","154kV 신광명-광명#2T/L 누유개소 보수","ㅇ154kV 신광명-광명#2T/L 누유개소 보수","2024-06-10 09:00","2024-06-14 18:00","2024-06-10 09:00","2024-06-14 18:00","연속"]
[67,"남서울","직할","신문래양평#1 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2024-06-10 09:00","2024-06-10 14:00","2024-06-10 09:00","2024-06-10 14:00","연속"]
[68,"남서울","동서울","동서울신장#1 T/L","세종-포천 고속도로 건설 지장선로 지중화공사","154kV 동서울-신장T/L No.3 인수검사 이상내역 조치작업 - 상표시찰, 번호판가대 부착","2024-06-10 09:00","2024-06-11 18:00","2024-06-10 09:00","2024-06-11 18:00","연속"]
[69,"남서울","직할","신문래양평#2 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2024-06-10 14:00","2024-06-10 18:00","2024-06-10 14:00","2024-06-10 18:00","연속"]
[70,"남서울","동서울","동서울신장#2 T/L","세종-포천 고속도로 건설 지장선로 지중화공사","154kV 동서울-신장T/L No.3 인수검사 이상내역 조치작업 - 상표시찰, 번호판가대 부착","2024-06-12 09:00","2024-06-13 18:00","2024-06-12 09:00","2024-06-13 18:00","연속"]
[71,"남서울","강남","신양재과천#1 T/L","24-25년도 강남전력지사 변전협력회사 총액공사","154kV GIS 조작시험(신양재S/S 154kV 신양재-과천#1T/L)","2024-06-12 10:00","2024-06-12 14:00","2024-06-12 10:00","2024-06-12 14:00","연속"]
[72,"남서울","강남","신양재과천#2 T/L","24-25년도 강남전력지사 변전협력회사 총액공사","154kV GIS 조작시험(신양재S/S 154kV 신양재-과천#2T/L)","2024-06-12 14:00","2024-06-12 18:00","2024-06-12 14:00","2024-06-12 18:00","연속"]
[73,"남서울","영등포","가양등촌#1 T/L","24년도 영등포전력지사 154kV GIS 정밀점검공사","24년도 영등포전력지사 154kV GIS 정밀점검공사 대상 : #1M.Tr 1차 무부하가압용","2024-06-12 16:00","2024-06-12 18:00","취소","취소","연속"]
[74,"남서울","영등포","가양등촌#1 T/L","24년도 영등포전력지사 154kV GIS 정밀점검공사","24년도 영등포전력지사 154kV GIS 정밀점검공사 대상 : #2M.Tr 1차 무부하가압용","2024-06-14 16:00","2024-06-14 18:00","취소","취소","연속"]
[75,"남서울","영등포","광명구공#2 T/L","구공S/S 154kV 장기사용 GIS 교체 및 모선구분 차단기 설치공사","(3차분)61BUS 무부하가압 ○ GIS(170kV 50kA 1000/2000A, 6BAY) 철거 ○ GIS(170kV 50kA 1250/2000/3150A, 7BAY) 설치 ○ GIS 교체에 따른 광·제어케이블 포설 및 결선 ○ 모선보호반(62-67), CPD(62-67) 설치","2024-06-20 18:00","2024-06-21 18:00","취소","취소","연속"]
[76,"남서울","영등포","구공S/S #66 BUS","구공S/S 154kV 장기사용 GIS 교체 및 모선구분 차단기 설치공사","(3차분) 66BUS 휴전 : 2DS, #66 모선, 상부 설치 및 준공시험 ○ GIS(170kV 50kA 1000/2000A, 6BAY) 철거 ○ GIS(170kV 50kA 1250/2000/3150A, 7BAY) 설치 ○ GIS 교체에 따른 광·제어케이블 포설 및 결선 ○ 모선보호반(62-67), CPD(62-67) 설치","2024-06-24 09:00","2024-07-04 18:00","2024-06-24 09:00","2024-07-04 18:00","연속"]
[77,"인천","김포","경서북인천#1 T/L","경서S/S 154kV 경서-북인천#1T/L GIS 조작시험","경서S/S 154kV 경서-북인천#1T/L GIS 조작시험","2024-06-11 10:00","2024-06-11 18:00","2024-06-11 10:00","2024-06-11 18:00","연속"]
[78,"인천","김포","경서북인천#2 T/L","경서S/S 154kV 경서-북인천#2T/L GIS 조작시험","경서S/S 154kV 경서-북인천#2T/L GIS 조작시험","2024-06-12 10:00","2024-06-12 18:00","2024-06-12 10:00","2024-06-12 18:00","연속"]
[79,"인천","김포","신경서경서#1 T/L","경서S/S 154kV 신경서-경서#1T/L GIS 조작시험","경서S/S 154kV 신경서-경서#1T/L GIS 조작시험","2024-06-10 10:00","2024-06-10 18:00","2024-06-10 10:00","2024-06-10 18:00","연속"]
[80,"인천","김포","신김포양곡#1 T/L","양곡S/S 154kV 신김포-양곡#1T/L GIS SA 혼용화 공사","양곡S/S 154kV 신김포-양곡#1T/L GIS SA 혼용화 공사 (병행) 양곡S/S 154kV 신김포-양곡#1T/L GIS 보통점검 (병행) 신김포S/S 154kV 신김포-양곡#1T/L GIS 보통점검","2024-06-18 09:00","2024-06-18 18:00","취소","취소","연속"]
[81,"인천","부평","송현포스코CC#1 T/L","154kV 송현-포스코CCT/L 추락방지시설 및 항공시설물 정비공사","- 수평형 추락방지시설 설치 - 항공장애표시구 탈락개소 정비","2024-06-01 07:00","2024-06-02 18:00","2024-06-01 07:00","2024-06-02 18:00","연속"]
[82,"인천","부평","송현포스코CC#2 T/L","154kV 송현-포스코CCT/L 추락방지시설 및 항공시설물 정비공사","- 수평형 추락방지시설 설치 - 항공장애표시구 탈락개소 정비","2024-06-08 07:00","2024-06-09 18:00","2024-06-08 07:00","2024-06-09 18:00","연속"]
[83,"인천","부평","신가좌S/S #62 BUS","신가좌S/S #3M.Tr 2차 GIS 정밀점검 관련 무부하가압","신가좌S/S #3M.Tr 2차 GIS 정밀점검 관련 무부하가압","2024-06-05 09:00","2024-06-05 18:00","2024-06-05 09:00","2024-06-05 18:00","연속"]
[84,"인천","부평","신가좌인천#3 T/L","신가좌S/S #3M.Tr 2차 GIS 정밀점검 관련 무부하가압","신가좌S/S #3M.Tr 2차 GIS 정밀점검 관련 무부하가압","2024-06-05 09:00","2024-06-05 18:00","2024-06-05 09:00","2024-06-05 18:00","연속"]
[85,"인천","부평","신가좌주안#1 T/L","2024-25년 부평,김포전력 가공송전협력회사 공사","피뢰기, 폴리머 설치","2024-06-22 07:30","2024-06-23 18:00","2024-06-22 09:00","2024-06-22 18:00","매일"]
[86,"인천","부평","신가좌인천#1 T/L","신가좌S/S 신가좌인천#1T/L GIS(627) 정밀점검","신가좌S/S 신가좌인천#1T/L GIS(627) 정밀점검","2024-06-17 09:00","2024-06-19 18:00","취소","취소","연속"]
[87,"인천","부평","신가좌부개#1 T/L","신가좌S/S 신가좌부개#1T/L GIS(667) 정밀점검","신가좌S/S 신가좌부개#1T/L GIS(667) 정밀점검","2024-06-24 09:00","2024-06-26 18:00","2024-06-24 09:00","2024-06-26 18:00","연속"]
[88,"인천","부평","신경서S/S #60 BUS","신경서S/S 154kV #60 BUS 휴전","신경서S/S 154kV #60 BUS 휴전 (신경서-경서 #3TL 631DS 메커니즘 교체 공사)","2024-06-17 09:00","2024-06-19 18:00","2024-06-17 09:00","2024-06-19 18:00","연속"]
[89,"인천","부평","신경서경서#3 T/L","신경서S/S 154kV 신경서-경서#3T/L #1DS 메커니즘 교체 공사","신경서S/S 154kV 신경서-경서#3T/L GIS #1DS 메커니즘 교체 공사","2024-06-17 09:00","2024-06-19 18:00","2024-06-17 09:00","2024-06-19 18:00","연속"]
[90,"인천","부평","신경서중산 T/L","신경서S/S 154kV 신경서-중산T/L GIS 인출DS 인디케이터 교체","신경서S/S 154kV 신경서-중산T/L GIS 인출DS 인디케이터 교체","2024-06-20 09:00","2024-06-21 18:00","2024-06-20 09:00","2024-06-21 18:00","연속"]
[91,"인천","부평","계양원창 T/L","154kV 계양-원창 T/L 보호반 교체공사","154kV 계양-원창 T/L 보호반 교체","2024-06-24 09:00","2024-06-27 18:00","취소","취소","연속"]
[92,"인천","부평","인천CC현대제철#2 T/L","154kV 현대제철T/L 추락방지시설 및 항공시설물 정비공사","- 수평형 추락방지시설 설치 - 항공장애표시구 탈락개소 정비","2024-06-08 07:00","2024-06-09 18:00","2024-06-08 07:00","2024-06-09 18:00","연속"]
[93,"인천","부평","인천CC현대제철#1 T/L","154kV 현대제철T/L 추락방지시설 및 항공시설물 정비공사","- 수평형 추락방지시설 설치 - 항공장애표시구 탈락개소 정비","2024-06-01 07:00","2024-06-02 18:00","2024-06-01 07:00","2024-06-02 18:00","연속"]
[94,"인천","부평","신가좌주안#2 T/L","154kV 주안-관교 등 4개T/L EBG 가스채취밸브 설치공사","EBG 가스채취밸브 설치 및 스프링 유니트 점검 시행","2024-06-10 09:00","2024-06-12 18:00","2024-06-09 09:00","2024-06-09 18:00","연속"]
[95,"인천","부평","주안만수#2 T/L","154kV 주안-관교 등 4개T/L EBG 가스채취밸브 설치공사","EBG 가스채취밸브 설치 및 스프링 유니트 점검 시행","2024-06-08 09:00","2024-06-09 18:00","취소","취소","연속"]
[96,"인천","부평","주안만수#1 T/L","주안S/S 모자익 철거 관련 케이블 철거","주안S/S 모자익 철거 관련 케이블 철거","2024-06-06 09:00","2024-06-06 18:00","2024-06-08 09:00","2024-06-08 18:00","연속"]
[97,"인천","부평","관교주안 T/L","154kV 주안-관교 등 4개T/L EBG 가스채취밸브 설치공사","EBG 가스채취밸브 설치 및 스프링 유니트 점검 시행","2024-06-13 09:00","2024-06-14 18:00","2024-06-16 13:00","2024-06-16 18:00","연속"]
[98,"인천","시흥","오봉고잔#1 T/L","고잔S/S 154kV 오봉고잔#1T/L GIS 정밀점검","고잔S/S 154kV 오봉고잔#1T/L GIS CB 정밀점검","2024-06-10 08:00","2024-06-12 13:00","취소","취소","연속"]
[99,"인천","시흥","오봉고잔#2 T/L","고잔S/S 154kV 오봉고잔#2T/L GIS 정밀점검","고잔S/S 154kV 오봉고잔#2T/L GIS CB 정밀점검","2024-06-12 13:00","2024-06-14 18:00","취소","취소","연속"]
[100,"인천","시흥","남동동춘 T/L","남동S/S 154kV 남동동춘T/L GIS 조작시험","남동S/S 154kV 남동동춘T/L GIS 조작시험 - 세니온제 보호IED 성능개선 병행","2024-06-04 09:00","2024-06-04 18:00","2024-06-04 09:00","2024-06-04 18:00","연속"]
[101,"인천","시흥","신시흥남동#1 T/L","남동S/S 154kV 신시흥남동#1T/L GIS 조작시험","남동S/S 154kV 신시흥남동#1T/L GIS 조작시험","2024-06-29 09:00","2024-06-29 14:00","취소","취소","연속"]
[102,"인천","시흥","신시흥남동#2 T/L","남동S/S 154kV 신시흥남동#2T/L GIS 조작시험","남동S/S 154kV 신시흥남동#2T/L GIS 조작시험","2024-06-29 14:00","2024-06-29 18:00","취소","취소","연속"]
[103,"인천","시흥","신시화남정왕#2 T/L","남정왕S/S 신시화-남정왕#2T/L GIS 초기점검","남정왕S/S 신시화-남정왕#2T/L GIS 초기점검","2024-06-27 14:00","2024-06-27 18:00","2024-06-27 14:00","2024-06-27 18:00","연속"]
[104,"인천","시흥","신시화남정왕#1 T/L","남정왕S/S 신시화-남정왕#1T/L GIS초기점검","남정왕S/S 신시화-남정왕#1T/L GIS 초기점검","2024-06-27 09:00","2024-06-27 14:00","2024-06-27 09:00","2024-06-27 14:00","연속"]
[105,"인천","시흥","북시화서시화#3 T/L","서시화S/S 154kV 북시화서시화#3T/L GIS 조작시험","서시화S/S 154kV 북시화서시화#3T/L GIS 조작시험 - 북시화S/S 154kV 북시화서시화#3T/L GIS 조작시험 병행","2024-06-26 09:00","2024-06-26 18:00","2024-06-26 09:00","2024-06-26 18:00","연속"]
[106,"인천","시흥","동시화서시화 T/L","서시화S/S 154kV 동시화서시화T/L GIS 조작시험","서시화S/S 154kV 동시화서시화T/L GIS 조작시험 - 세니온제 보호IED 성능개선 병행","2024-06-03 09:00","2024-06-03 18:00","2024-06-03 09:00","2024-06-03 18:00","연속"]
[107,"인천","시흥","서서울#2소래 T/L","소래S/S 154kV 서서울2소래T/L GIS 조작시험","소래S/S 154kV 서서울2소래T/L GIS 조작시험","2024-06-01 14:00","2024-06-01 18:00","2024-06-01 14:00","2024-06-01 18:00","연속"]
[108,"인천","시흥","소래S/S CB 6100","소래S/S 154kV 6100B/T GIS 조작시험","소래S/S 154kV 6100B/T(60-65) GIS 조작시험","2024-06-08 15:00","2024-06-08 18:00","2024-06-08 15:00","2024-06-08 18:00","연속"]
[109,"인천","시흥","온수소래 T/L","소래S/S 154kV 온수소래T/L GIS 조작시험","소래S/S 154kV 온수소래T/L GIS 조작시험","2024-06-01 09:00","2024-06-01 14:00","2024-06-01 09:00","2024-06-01 14:00","연속"]
[110,"인천","시흥","신광명소래 T/L","소래S/S 154kV 신광명소래T/L GIS 조작시험","소래S/S 154kV 신광명소래T/L GIS 조작시험","2024-06-08 09:00","2024-06-08 12:00","2024-06-08 09:00","2024-06-08 12:00","연속"]
[111,"인천","시흥","서안양소래 T/L","소래S/S 154kV 서안양소래T/L GIS 조작시험","소래S/S 154kV 서안양소래T/L GIS 조작시험","2024-06-08 12:00","2024-06-08 15:00","2024-06-08 12:00","2024-06-08 15:00","연속"]
[112,"인천","시흥","신시화S/S CB 6671","신시화S/S 154kV 6671 GIS 초기점검","신시화S/S #63M.Tr 1차 GIS 초기점검","2024-06-27 14:00","2024-06-27 18:00","2024-06-27 14:00","2024-06-27 18:00","연속"]
[113,"인천","시흥","신시화S/S CB 6571","신시화S/S 154kV 6571 GIS 초기점검","신시화S/S #3M.Tr 2차 GIS 초기점검","2024-06-27 09:00","2024-06-27 14:00","2024-06-27 09:00","2024-06-27 14:00","연속"]
[114,"인천","시흥","신시화S/S CB 6471","신시화S/S 154kV 6471 GIS 초기점검","신시화S/S #62M.Tr 1차 GIS 초기점검","2024-06-24 14:00","2024-06-24 18:00","2024-06-24 14:00","2024-06-24 18:00","연속"]
[115,"인천","시흥","신시화S/S CB 6371","신시화S/S 154kV 6371 GIS 초기점검","신시화S/S #2M.Tr 2차 GIS 초기점검","2024-06-24 09:00","2024-06-24 14:00","2024-06-24 09:00","2024-06-24 14:00","연속"]
[116,"인천","시흥","신시화S/S SEC CB 65660","신시화S/S 154kV 65-66 Sec. GIS 초기점검","신시화S/S 154kV 65-66 Sec. GIS 초기점검","2024-06-26 14:00","2024-06-26 18:00","2024-06-26 14:00","2024-06-26 18:00","연속"]
[117,"인천","시흥","신시화S/S SEC CB 60610","신시화S/S 154kV 60-61 Sec. GIS 초기점검","신시화S/S 154kV 60-61 Sec. GIS 초기점검","2024-06-26 09:00","2024-06-20 14:00","2024-06-26 09:00","2024-06-26 14:00","연속"]
[118,"인천","시흥","신시화중시화#2 T/L","신시화S/S 신시화-중시화#2T/L GIS 초기점검","신시화S/S 신시화-중시화#2T/L GIS 초기점검","2024-06-25 14:00","2024-06-25 18:00","2024-06-25 14:00","2024-06-25 18:00","연속"]
[119,"인천","시흥","신시화중시화#1 T/L","신시화S/S 신시화-중시화#1T/L GIS 초기점검","신시화S/S 신시화-중시화#1T/L GIS 초기점검","2024-06-25 09:00","2024-06-25 14:00","2024-06-25 09:00","2024-06-25 14:00","연속"]
[120,"인천","시흥","신시화남정왕#2 T/L","신시화SS 345kV #4M.Tr, #2Sh.R, 154kV GIS 증설","○ #66BUS 무부하가압 - 345kV #4M.Tr 증설(1차 75Bay, 2차 67Bay GIS) - 345kV #2Sh.R 증설(76Bay) - 154kV 신규수용 증설공사(67Bay)","2024-06-07 09:00","2024-06-07 18:00","2024-06-07 09:00","2024-06-07 18:00","연속"]
[121,"인천","시흥","신시화S/S #61 BUS","신시화SS 345kV #4M.Tr, #2Sh.R, 154kV GIS 증설","○ #61BUS 상체크 시험 - 345kV #4M.Tr 증설(1차 75Bay, 2차 67Bay GIS) - 345kV #2Sh.R 증설(76Bay) - 154kV 신규수용 증설공사(67Bay)","2024-06-07 09:00","2024-06-07 18:00","2024-06-07 09:00","2024-06-07 18:00","연속"]
[122,"인천","시흥","신시화남정왕#2 T/L","신시화SS 345kV #4M.Tr, #2Sh.R, 154kV GIS 증설","○ #61BUS 상체크시험 - 345kV #4M.Tr 증설(1차 75Bay, 2차 67Bay GIS) - 345kV #2Sh.R 증설(76Bay) - 154kV 신규수용 증설공사(67Bay)","2024-06-05 09:00","2024-06-06 18:00","2024-06-05 09:00","2024-06-06 18:00","연속"]
[123,"인천","시흥","신시흥도림#2 T/L","신시흥S/S 154kV Sh.R 증설공사","345kV #1M.Tr 2차 POST 철거","2024-06-15 09:00","2024-06-16 12:00","2024-06-15 09:00","2024-06-16 12:00","연속"]
[124,"인천","시흥","신시흥S/S #63 Sh.C CB","신시흥#1S/S 154kV #63Sh.C GIS 조작시험","신시흥#1S/S 154kV #63Sh.C GIS 조작시험","2024-06-21 14:00","2024-06-21 18:00","취소","취소","연속"]
[125,"인천","시흥","신시흥S/S SEC CB 61620","신시흥#1S/S 154kV #61-#62 SEC GIS 보통점검","신시흥#1S/S 154kV #61-#62 SEC GIS 보통점검","2024-06-05 09:00","2024-06-05 18:00","2024-06-05 09:00","2024-06-05 18:00","연속"]
[126,"인천","시흥","신시흥S/S #61 Sh.C CB","신시흥#1S/S 154kV #61Sh.C GIS 조작시험","신시흥#1S/S 154kV #61Sh.C GIS 조작시험","2024-06-21 09:00","2024-06-21 14:00","취소","취소","연속"]
[127,"인천","시흥","신시흥북시화#1 T/L","신시흥S/S 154kV 신시흥북시화#1T/L 보호반 대체","신시흥S/S 154kV 신시흥북시화#1T/L 보호반 대체 - 북시화S/S 154kV 신시흥북시화#1T/L 보호반 대체 병행","2024-06-10 09:00","2024-06-14 18:00","2024-06-10 09:00","2024-06-14 18:00","연속"]
[128,"인천","시흥","신시흥S/S #65 Sh.C CB","신시흥#2S/S 154kV #65 Sh.C GIS 조작시험","신시흥#2S/S 154kV #65 Sh.C GIS 조작시험","2024-06-27 09:00","2024-06-27 18:00","취소","취소","연속"]
[129,"인천","시흥","신시흥북시화#2 T/L","신시흥S/S 154kV 신시흥북시화#2T/L 보호반 대체","신시흥S/S 154kV 신시흥북시화#2T/L 보호반 대체 - 북시화S/S 154kV 신시흥북시화#2T/L 보호반 대체 병행","2024-06-17 09:00","2024-06-21 18:00","2024-06-17 09:00","2024-06-21 18:00","연속"]
[130,"인천","직할","갈산도당#1 T/L","154kV 신부평-고강T/L 등 4개T/L 구형 SVL 교체공사","154kV 신부평-고강T/L 등 4개T/L 구형 SVL(피뢰기) 및 접지설비 교체공사","2024-06-03 09:00","2024-06-05 18:00","2024-06-03 09:00","2024-06-05 18:00","연속"]
[131,"인천","직할","부천도당#2 T/L","154kV 도당S/S #4M.Tr 증설공사","도당S/S 170kV GIS 도킹(#61BUS), 무부하 가압","2024-06-07 09:00","2024-06-08 18:00","2024-06-07 09:00","2024-06-08 18:00","연속"]
[132,"인천","직할","부천도당#2 T/L","154kV 도당S/S #4M.Tr 증설공사","도당S/S 170kV GIS 도킹(#66BUS), 무부하 가압","2024-06-14 09:00","2024-06-15 18:00","2024-06-14 09:00","2024-06-15 18:00","연속"]
[133,"인천","직할","부천신정#2 T/L","부천S/S 170kV 부천 신정#2T/L 보통점검","부천S/S 170kV 부천 신정#2T/L 보통점검","2024-06-21 09:30","2024-06-21 18:00","2024-06-21 09:30","2024-06-21 18:00","연속"]
[134,"인천","직할","부천신정#1 T/L","부천S/S 170kV 부천 신정#1T/L 보통점검","부천S/S 170kV 부천 신정#1T/L 보통점검","2024-06-20 09:30","2024-06-20 18:00","2024-06-20 09:30","2024-06-20 18:00","연속"]
[135,"인천","직할","부흥부개#1 T/L","부흥S/S 부흥부개#1T/L GIS 조작시험","부흥S/S 부흥부개#1T/L GIS 조작시험","2024-06-03 09:30","2024-06-03 18:00","취소","취소","연속"]
[136,"인천","직할","부흥부개#2 T/L","154kV 신부평-고강T/L 등 4개T/L 구형 SVL 교체공사","154kV 신부평-고강T/L 등 4개T/L 구형 SVL(피뢰기) 및 접지설비 교체공사","2024-06-01 09:00","2024-06-02 18:00","2024-06-01 09:00","2024-06-02 18:00","연속"]
[137,"인천","직할","신부평고강#1 T/L","154kV 신부평-고강T/L 등 4개T/L 구형 SVL 교체공사","154kV 신부평-고강T/L 등 4개T/L 구형 SVL(피뢰기) 및 접지설비 교체공사","2024-06-08 09:00","2024-06-09 18:00","취소","취소","연속"]
[138,"인천","직할","신부평고강#2 T/L","154kV 신부평-고강#2T/L 보통점검","154kV 신부평-고강#2T/L 보통점검","2024-06-15 09:00","2024-06-15 18:00","취소","취소","연속"]
[139,"인천","직할","부개원미#1 T/L","원미S/S 부개원미#1T/L GIS조작시험","원미S/S 부개원미#1T/L GIS조작시험","2024-06-04 09:00","2024-06-04 14:00","취소","취소","연속"]
[140,"인천","직할","부개원미#2 T/L","원미S/S 부개원미#2T/L GIS조작시험","원미S/S 부개원미#2T/L GIS조작시험","2024-06-04 14:00","2024-06-04 18:00","취소","취소","연속"]
[141,"인천","직할","신부평임학#2 T/L","임학, 부개S/S 154kV GIS 교체공사","PT&ES, 신부평임학#1T/L #2BUS측 무부하가압","2024-06-21 10:00","2024-06-22 10:00","취소","취소","연속"]
[142,"인천","직할","신부평임학#2 T/L","임학, 부개S/S 154kV GIS 교체공사","PT&ES, 신부평임학#1T/L #1BUS측 무부하가압","2024-06-13 10:00","2024-06-14 10:00","취소","취소","연속"]
[143,"인천","직할","신부평임학#2 T/L","임학, 부개S/S 154kV GIS 교체공사","PT&ES, 신부평임학#1T/L #2BUS측 무부하가압","2024-06-05 14:00","2024-06-06 14:00","취소","취소","연속"]
[144,"인천","직할","신부평임학#1 T/L","임학, 부개S/S 154kV GIS 교체공사","신부평-임학#1T/L 장기사용 GIS 교체","2024-06-01 09:00","2024-06-22 18:00","취소","취소","연속"]
[145,"인천","시흥","신시화S/S #66 BUS","신시화SS 345kV #4M.Tr, #2Sh.R, 154kV GIS 증설","○ #66BUS 상체크 시험 - 345kV #4M.Tr 증설(1차 75Bay, 2차 67Bay GIS) - 345kV #2Sh.R 증설(76Bay) - 154kV 신규수용 증설공사(67Bay)","2024-06-01 07:00","2024-06-06 18:00","2024-06-01 07:00","2024-06-06 18:00","연속"]
[146,"경기북부","고양","백학남면#1 T/L","24-25 변전협력 총액공사","170kV GIS 보통점검","2024-06-04 09:00","2024-06-04 18:00","취소","취소","연속"]
[147,"경기북부","고양","남면백석#1 T/L","24~25년 고양전력지사 가공송전협력회사 공사","피뢰기 설치, SB댐퍼 교체, 불량애자 교체","2024-06-10 07:00","2024-06-14 18:00","2024-06-10 07:00","2024-06-14 18:00","연속"]
[148,"경기북부","고양","신파주문발#2 T/L","문발S/S 154kV ASE코리아 신규수용 SW 증설공사","문발S/S 154kV ASE코리아 신규수용 SW 증설공사 - 문발ASE#1,2T/L 무부하 시험가압","2024-06-10 09:00","2024-06-13 18:00","2024-06-10 09:00","2024-06-13 18:00","연속"]
[149,"경기북부","고양","백학남면#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지시설 설치 - 대상 : 154kV 백학-남면#2T/L No.33~61","2024-06-25 07:00","2024-06-28 18:00","취소","취소","연속"]
[150,"경기북부","고양","일산송포#2 T/L","154kV 송포S/S 디지털화 공사","154kV 송포S/S 디지털화 공사","2024-06-14 09:00","2024-06-14 18:00","2024-06-14 09:00","2024-06-14 18:00","연속"]
[151,"경기북부","고양","일산송포#1 T/L","154kV 송포S/S 디지털화 공사","154kV 송포S/S 디지털화 공사","2024-06-13 09:00","2024-06-13 18:00","2024-06-13 09:00","2024-06-13 18:00","연속"]
[152,"경기북부","고양","신파주송포#1 T/L","24~25년 고양전력지사 변전협력회사 총액공사","170kV GIS 차단기 조작시험","2024-06-11 09:00","2024-06-11 18:00","2024-06-11 09:00","2024-06-11 18:00","연속"]
[153,"경기북부","고양","신파주송포#2 T/L","24~25년 고양전력지사 변전협력회사 총액공사","170kV GIS 차단기 조작시험","2024-06-12 09:00","2024-06-12 18:00","2024-06-12 09:00","2024-06-12 18:00","연속"]
[154,"경기북부","고양","운정덕이#2 T/L","24-25 변전협력 총액공사","170kV GIS 보통점검","2024-06-18 09:00","2024-06-18 18:00","2024-06-18 09:00","2024-06-18 18:00","연속"]
[155,"경기북부","고양","운정덕이#1 T/L","24-25 변전협력 총액공사","170kV GIS 보통점검","2024-06-17 09:00","2024-06-17 18:00","2024-06-17 09:00","2024-06-17 18:00","연속"]
[156,"경기북부","고양","월롱S/S #1 BUS","154kV 월롱S/S #1,2M.Tr 증설공사(무부하 시험가압)","154kV 월롱S/S #1,2M.Tr 증설공사 - 주변압기, 170kV GIS, 25.8kV EGIS 무부하 시험가압","2024-06-10 09:00","2024-06-11 09:00","2024-06-10 09:00","2024-06-11 09:00","연속"]
[157,"경기북부","고양","문산월롱#2 T/L","154kV 월롱S/S #1,2M.Tr 증설공사(무부하 시험가압)","154kV 월롱S/S #1,2M.Tr 증설공사 - 주변압기, 170kV GIS, 25.8kV EGIS 무부하 시험가압","2024-06-10 09:00","2024-06-12 09:00","2024-06-10 09:00","2024-06-12 09:00","연속"]
[158,"경기북부","고양","월롱S/S #2 BUS","154kV 월롱S/S #1,2M.Tr 증설공사(무부하 시험가압)","154kV 월롱S/S #1,2M.Tr 증설공사 - 주변압기, 170kV GIS, 25.8kV EGIS 시험가압","2024-06-11 09:00","2024-06-12 09:00","2024-06-11 09:00","2024-06-12 09:00","연속"]
[159,"경기북부","고양","고양일산#2 T/L","24~25년 고양전력지사 가공송전협력회사 공사","병가선로 휴전","2024-06-03 07:00","2024-06-05 18:00","2024-06-03 07:00","2024-06-05 18:00","연속"]
[160,"경기북부","고양","일산지도#2 T/L","24~25년 고양전력지사 가공송전협력회사 공사","피뢰기 설치, 점퍼선 정비, 불량애자 교체","2024-06-03 07:00","2024-06-05 18:00","2024-06-03 07:00","2024-06-05 18:00","연속"]
[161,"경기북부","고양","일산호수#1 T/L","154kV 호수S/S #4M.Tr 증설 및 디지털화공사","154kV 일산-호수#1T/L GIS, PRO PNL 감시/제어케이블 이설","2024-06-26 09:00","2024-06-26 18:00","2024-06-26 09:00","2024-06-26 18:00","연속"]
[162,"경기북부","고양","호수S/S 호수난방#1T/L CB","154kV 호수S/S #4M.Tr 증설 및 디지털화공사","154kV 호수-난방#1T/L GIS, PRO PNL 감시/제어케이블 이설","2024-06-26 09:00","2024-06-26 18:00","2024-06-26 09:00","2024-06-26 18:00","연속"]
[163,"경기북부","고양","호수S/S 호수난방#2T/L CB","154kV 호수S/S #4M.Tr 증설 및 디지털화공사","154kV 호수-난방#2T/L GIS, PRO PNL 감시/제어케이블 이설","2024-06-27 09:00","2024-06-27 18:00","2024-06-27 09:00","2024-06-27 18:00","연속"]
[164,"경기북부","고양","덕이호수#1 T/L","154kV 호수S/S #4M.Tr 증설 및 디지털화공사","154kV 덕이-호수#1T/L GIS, PRO PNL 감시/제어케이블 이설","2024-06-27 09:00","2024-06-27 18:00","2024-06-27 09:00","2024-06-27 18:00","연속"]
[165,"경기북부","고양","일산호수#2 T/L","154kV 호수S/S #4M.Tr 증설 및 디지털화공사","154kV 일산-호수#2T/L GIS, PRO PNL 감시/제어케이블 이설","2024-06-28 09:00","2024-06-28 18:00","2024-06-28 09:00","2024-06-28 18:00","연속"]
[166,"경기북부","고양","덕이호수#2 T/L","154kV 호수S/S #4M.Tr 증설 및 디지털화공사","154kV 덕이-호수#2T/L GIS, PRO PNL 감시/제어케이블 이설","2024-06-28 09:00","2024-06-28 18:00","2024-06-28 09:00","2024-06-28 18:00","연속"]
[167,"경기북부","구리","가평청평HP#1 T/L","765kV 신안성-신가평 등 12개T/L 추락방지 설치공사","수직 및 수평 추락방지 설치(36기)","2024-06-24 07:00","2024-06-28 18:00","2024-06-24 07:00","2024-06-28 18:00","연속"]
[168,"경기북부","구리","내촌용정#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 내촌-용정#1T/L No.32,33","2024-06-14 07:00","2024-06-14 18:00","2024-06-14 07:00","2024-06-14 18:00","연속"]
[169,"경기북부","구리","신장덕소#1 T/L","23~24년 직할 지중송전설비 위탁정비공사","C/T 리드선 연결금구 교체","2024-06-11 14:00","2024-06-11 18:00","취소","취소","연속"]
[170,"경기북부","구리","덕소팔당HP청평HP T/L","765kV 신안성-신가평 등 12개T/L 추락방지 설치공사","수직 및 수평 추락방지 설치(68기)","2024-06-04 07:00","2024-06-21 18:00","2024-06-04 07:00","2024-06-21 18:00","연속"]
[171,"경기북부","구리","덕소마석#1 T/L","23~24년 직할 지중송전설비 위탁정비공사","C/T 리드선 연결금구 교체 및 피뢰기 점검","2024-06-25 08:00","2024-06-25 18:00","2024-06-25 08:00","2024-06-25 18:00","연속"]
[172,"경기북부","구리","신장덕소#2 T/L","23~24년 직할 지중송전설비 위탁정비공사","C/T 리드선 연결금구 교체","2024-06-11 08:00","2024-06-11 14:00","2024-06-11 08:00","2024-06-11 18:00","연속"]
[173,"경기북부","구리","덕소팔당HP T/L","23~24년 직할 지중송전설비 위탁정비공사","C/T 리드선 연결금구 교체","2024-06-03 08:00","2024-06-03 17:00","2024-06-03 08:00","2024-06-03 17:00","연속"]
[174,"경기북부","구리","덕소마석#2 T/L","23~24년 직할 지중송전설비 위탁정비공사","C/T 리드선 연결금구 교체 및 피뢰기 점검","2024-06-26 08:00","2024-06-26 18:00","2024-06-26 08:00","2024-06-26 18:00","연속"]
[175,"경기북부","구리","신포천백학#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지시설 설치 - 대상 : 154kV 신포천-백학#2T/L No.7~39","2024-06-18 07:00","2024-06-24 18:00","2024-06-18 07:00","2024-06-24 18:00","연속"]
[176,"경기북부","구리","포천운천#1 T/L","154kV 포천S/S 옥내화","1. EBA접속 및무부하 가압 2. 사용전검사 후 실부하가압","2024-06-10 09:00","2024-06-21 18:00","2024-06-10 09:00","2024-06-21 18:00","연속"]
[177,"경기북부","구리","포천운천#2 T/L","24~25년 경기북부 직할 가공송전협력회사공사","154kV 포천-운천#2T/L 피뢰기설치공사","2024-06-03 07:00","2024-06-05 18:00","2024-06-03 07:00","2024-06-05 18:00","연속"]
[178,"경기북부","구리","용정포천#2 T/L","154kV 포천S/S 옥내화","1. EBA접속 및무부하 가압 2. 사용전검사 후 실부하가압","2024-06-10 09:00","2024-06-21 18:00","2024-06-10 09:00","2024-06-21 18:00","연속"]
[179,"경기북부","직할","녹양백석#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 녹양-백석T/L No.5~12","2024-06-17 07:00","2024-06-17 18:00","2024-06-17 07:00","2024-06-17 18:00","연속"]
[180,"경기북부","직할","백석덕계#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 백석-덕계T/L No.6~9,22~28","2024-06-17 07:00","2024-06-17 18:00","2024-06-17 07:00","2024-06-17 18:00","연속"]
[181,"경기북부","직할","신의정부송우#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 신의정부-송우#1T/L No.1~4","2024-06-07 13:00","2024-06-07 18:00","2024-06-07 13:00","2024-06-07 18:00","연속"]
[182,"경기북부","직할","신의정부송우#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 신의정부-송우#2T/L No.1~4","2024-06-07 07:00","2024-06-07 13:00","2024-06-07 07:00","2024-06-07 13:00","연속"]
[183,"경기북부","직할","신의정부내촌#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 신의정부-내촌T/L No.1~4","2024-06-07 07:00","2024-06-07 13:00","2024-06-07 07:00","2024-06-07 13:00","연속"]
[184,"경기북부","직할","신의정부내촌#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 신의정부-내촌T/L No.1~4","2024-06-07 13:00","2024-06-07 18:00","2024-06-07 13:00","2024-06-07 18:00","연속"]
[185,"경기북부","직할","양주S/S SEC CB 66670","24-25 변전협력 총액공사","154kV GIS 보통점검","2024-06-10 09:00","2024-06-10 18:00","2024-06-10 09:00","2024-06-10 18:00","연속"]
[186,"경기북부","직할","옥정송우#2 T/L","(주)세니온 보호계전기 성능개선 시행","유사 불량사례 발생 가능성 사전 제거를 위한 성능개선","2024-06-05 09:00","2024-06-05 18:00","2024-06-03 09:00","2024-06-03 18:00","연속"]
[187,"경기북부","직할","운천전곡#1 T/L","24~25년 경기북부 직할 가공송전협력회사공사","154kV 포천-운천#2T/L 피뢰기설치공사(병가구간)","2024-06-03 07:00","2024-06-04 18:00","2024-06-03 07:00","2024-06-04 18:00","연속"]
[188,"경기북부","고양","신덕은S/S #61 BUS","신덕은S/S 154kV 고객선로 SW 증설공사","170kV GIS 1CCT 설치 - 신덕은-DIG #2 T/L 1DS~CHD 무부하가압","2024-06-13 09:00","2024-06-14 18:00","2024-06-13 09:00","2024-06-14 18:00","연속"]
[189,"경기","동부","오천율현#2 T/L","오천SS #4M.Tr 증설공사","오천:#4M.Tr 증설 관련 무부하가압용","2024-06-27 09:00","2024-06-28 18:00","취소","취소","연속"]
[190,"경기","동부","초월성현#2 T/L","24-25 동부전력지사 송전협력회사 총액공사","수평 추락방지장치 설치공사(1~43, 59호) 및 애자교체(0.1,1,3호)","2024-06-05 08:00","2024-06-13 18:00","2024-06-05 08:00","2024-06-13 18:00","연속"]
[191,"경기","동부","곤지암초월#2 T/L","24-25 동부전력지사 송전협력회사 총액공사","수평추락방지설치(44~58호, 초월-성현#2T/L과 4회선 병가) 및 애자교체(50,51,58호)","2024-06-10 08:00","2024-06-20 18:00","취소","취소","연속"]
[192,"경기","성남","오천용인#1 T/L","2024년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검 무부하가압용","2024-06-04 15:00","2024-06-04 18:00","2024-06-04 15:00","2024-06-04 18:00","연속"]
[193,"경기","성남","오천용인#2 T/L","2024년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검 무부하가압용","2024-06-24 09:00","2024-06-25 18:00","2024-06-24 09:00","2024-06-25 18:00","연속"]
[194,"경기","성남","신용인용인#1 T/L","24-25년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사[4회선 병가]","2024-06-04 07:00","2024-06-07 18:00","2024-06-04 07:00","2024-06-07 18:00","연속"]
[195,"경기","성남","신용인용인#2 T/L","24-25년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사[4회선 병가]","2024-06-08 07:00","2024-06-08 18:00","2024-06-08 07:00","2024-06-08 18:00","연속"]
[196,"경기","성남","신용인용인#2 T/L","24-25년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사[4회선 병가]","2024-06-10 07:00","2024-06-11 18:00","2024-06-10 07:00","2024-06-11 18:00","연속"]
[197,"경기","성남","용인덕성#2 T/L","24-25년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사[4회선 병가]","2024-06-08 07:00","2024-06-08 18:00","2024-06-08 07:00","2024-06-08 18:00","연속"]
[198,"경기","성남","용인덕성#1 T/L","24-25년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사[4회선 병가]","2024-06-06 07:00","2024-06-06 18:00","2024-06-06 07:00","2024-06-06 18:00","연속"]
[199,"경기","군포","남수원발안#2 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 4회선 21기(봉담-남수원T/L 병가선로)","2024-06-08 08:00","2024-06-09 18:00","취소","취소","연속"]
[200,"경기","군포","봉담남수원#1 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 4회선 21기(봉담-남수원T/L 병가선로)","2024-06-08 08:00","2024-06-09 18:00","취소","취소","연속"]
[201,"경기","군포","남수원발안#2 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 4회선 21기(봉담-남수원T/L 병가선로)","2024-06-15 08:00","2024-06-16 13:00","취소","취소","연속"]
[202,"경기","군포","봉담남수원#1 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 4회선 21기(봉담-남수원T/L 병가선로)","2024-06-15 08:00","2024-06-16 13:00","취소","취소","연속"]
[203,"경기","군포","남수원발안#1 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 4회선 21기(봉담-남수원T/L 병가선로)","2024-06-16 13:00","2024-06-16 18:00","취소","취소","연속"]
[204,"경기","군포","봉담남수원#2 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 4회선 21기(봉담-남수원T/L 병가선로)","2024-06-16 13:00","2024-06-16 18:00","취소","취소","연속"]
[205,"경기","군포","남수원발안#1 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 4회선 21기(봉담-남수원T/L 병가선로)","2024-06-22 08:00","2024-06-23 18:00","취소","취소","연속"]
[206,"경기","군포","봉담남수원#2 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 4회선 21기(봉담-남수원T/L 병가선로)","2024-06-22 08:00","2024-06-23 18:00","취소","취소","연속"]
[207,"경기","군포","남수원발안#1 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 4회선 21기(봉담-남수원T/L 병가선로)","2024-06-29 08:00","2024-06-30 18:00","취소","취소","연속"]
[208,"경기","군포","봉담남수원#2 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 4회선 21기(봉담-남수원T/L 병가선로)","2024-06-29 08:00","2024-06-30 18:00","취소","취소","연속"]
[209,"경기","군포","화성남양#1 T/L","군포전력지사 지중송전 위탁전문회사","화성-남양#1T/L 절연유 채유","2024-06-01 08:00","2024-06-01 18:00","2024-06-01 08:00","2024-06-01 18:00","연속"]
[210,"경기","직할","화성발안#1 T/L","23-24년 지중송전설비 위탁정비공사(평택전력지사) ","케이블타워 및 피뢰기 점검 ","2024-06-03 08:00","2024-06-03 18:00","2024-06-03 08:00","2024-06-03 18:00","연속"]
[211,"경기","직할","화성발안#2 T/L","23-24년 지중송전설비 위탁정비공사(평택전력지사) ","케이블타워 및 피뢰기 점검 ","2024-06-07 08:00","2024-06-07 18:00","2024-06-07 08:00","2024-06-07 18:00","연속"]
[212,"경기","직할","화성S/S CB 6200","2024-25년 경기본부 직할 변전협력회사 총액공사","화성: 154kV #61-#66 모선보호반 대체","2024-06-24 09:00","2024-06-28 18:00","2024-06-24 09:00","2024-06-28 18:00","연속"]
[213,"경기","직할","화성S/S CB 6100","2024-25년 경기본부 직할 변전협력회사 총액공사","화성: 154kV #60-#65 모선보호반 대체","2024-06-17 09:00","2024-06-21 18:00","2024-06-17 09:00","2024-06-21 18:00","연속"]
[214,"경기","평택","고덕#2S/S CB 6671","24년도 평택전력 154,345kV GIS 보통점검","고덕2S/S 154kV #1M.Tr 2차 GIS(6671) 보통점검","2024-06-27 09:00","2024-06-27 18:00","2024-06-27 09:00","2024-06-27 18:00","연속"]
[215,"경기","평택","고덕#2S/S CB 6972","24년도 평택전력 154,345kV GIS 보통점검","고덕2S/S 154kV 고덕2-삼성P4#1T/L GIS(6972) 보통점검","2024-06-26 14:00","2024-06-26 18:00","2024-06-26 14:00","2024-06-26 18:00","연속"]
[216,"경기","평택","고덕#2S/S CB 6971","24년도 평택전력 154,345kV GIS 보통점검","고덕2S/S 154kV 고덕2-평택#1T/L GIS(6272) 보통점검","2024-06-26 09:00","2024-06-26 14:00","2024-06-26 09:00","2024-06-26 14:00","연속"]
[217,"경기","평택","고덕#2S/S CB 6C00","24년도 평택전력 154,345kV GIS 보통점검","고덕2S/S 154kV 6CBay TIE GIS(6C00) 보통점검","2024-06-25 14:00","2024-06-25 18:00","2024-06-25 14:00","2024-06-25 18:00","연속"]
[218,"경기","평택","고덕#2S/S CB 6C71","24년도 평택전력 154,345kV GIS 보통점검","고덕2S/S 154kV 고덕2-에어퍼스트#2T/L GIS(6C71) 보통점검","2024-06-25 09:00","2024-06-25 14:00","2024-06-25 09:00","2024-06-25 14:00","연속"]
[219,"경기","평택","고덕#2S/S CB 6A71","24년도 평택전력 154,345kV GIS 보통점검","고덕2S/S 154kV 고덕2-삼성P4#2T/L GIS(6A71) 보통점검","2024-06-24 14:00","2024-06-24 18:00","2024-06-24 14:00","2024-06-24 18:00","연속"]
[220,"경기","평택","고덕#2S/S CB 6A00","24년도 평택전력 154,345kV GIS 보통점검","고덕2S/S 154kV 6ABay TIE GIS(6A00) 보통점검","2024-06-24 09:00","2024-06-24 14:00","2024-06-24 09:00","2024-06-24 14:00","연속"]
[221,"경기","평택","고덕#2S/S CB 6900","24년도 평택전력 154,345kV GIS 보통점검","고덕2S/S 154kV 69Bay TIE GIS(6900) 보통점검","2024-06-21 14:00","2024-06-21 18:00","2024-06-21 14:00","2024-06-21 18:00","연속"]
[222,"경기","평택","고덕#2S/S CB 6971","24년도 평택전력 154,345kV GIS 보통점검","고덕2S/S 154kV 고덕2-평택#2T/L GIS(6971) 보통점검","2024-06-21 09:00","2024-06-21 14:00","2024-06-21 09:00","2024-06-21 14:00","연속"]
[223,"경기","평택","고덕#2S/S 6672","24년도 평택전력 154,345kV GIS 보통점검","고덕2S/S 154kV 고덕2-삼성P3#1T/L GIS 보통점검","2024-06-20 14:00","2024-06-20 18:00","2024-06-20 14:00","2024-06-20 18:00","연속"]
[224,"경기","평택","고덕#2S/S 6400","24년도 평택전력 154,345kV GIS 보통점검","고덕2S/S 154kV 64Bay TIE GIS 보통점검","2024-06-03 09:00","2024-06-03 14:00","2024-06-03 09:00","2024-06-03 14:00","연속"]
[225,"경기","평택","고덕#2S/S 6600","24년도 평택전력 154,345kV GIS 보통점검","고덕2S/S 154kV 66Bay TIE GIS 보통점검","2024-06-20 09:00","2024-06-20 14:00","2024-06-20 09:00","2024-06-20 14:00","연속"]
[226,"경기","평택","고덕#2S/S 6472","24년도 평택전력 154,345kV GIS 보통점검","고덕2S/S 154kV 고덕2-에어퍼스트#1T/L GIS 보통점검","2024-06-03 14:00","2024-06-03 18:00","2024-06-03 14:00","2024-06-03 18:00","연속"]
[227,"경기","평택","고덕S/S #61 BUS","평택 브레인시티 지중화공사","○ 대상선로 : 154KV 고덕-진위#1,2T/L ○ 공사구간 : J/B#7 ~ 도일C/T ○ 공사규모 : 154kV XLPE 2,500㎟, 2회선 4.9km","2024-06-17 10:00","2024-06-18 10:00","2024-06-17 10:00","2024-06-18 10:00","연속"]
[228,"경기","평택","고덕진위#2 T/L","평택 브레인시티 지중화공사","○ 대상선로 : 154KV 고덕-진위#1,2T/L ○ 공사구간 : J/B#7 ~ 도일C/T ○ 공사규모 : 154kV XLPE 2,500㎟, 2회선 4.9km","2024-06-19 09:00","2024-07-02 17:00","2024-06-19 09:00","2024-07-02 17:00","연속"]
[229,"경기","평택","고덕진위#1 T/L","평택 브레인시티 지중화공사","○ 대상선로 : 154KV 고덕-진위#1,2T/L ○ 공사구간 : J/B#7 ~ 도일C/T ○ 공사규모 : 154kV XLPE 2,500㎟, 2회선 4.9km","2024-06-03 09:00","2024-06-18 17:00","2024-06-03 09:00","2024-06-18 17:00","연속"]
[230,"경기","평택","원정만호#2 T/L","24년도 평택전력 변전협력회사 총액공사","만호,원정S/S 원정-만호#2T/L 세니온제 보호반 성능개선 및 만호S/S 170kV GIS 보통점검","2024-06-07 09:00","2024-06-07 18:00","2024-06-07 09:00","2024-06-07 18:00","연속"]
[231,"경기","평택","원정S/S CB 6100","24년도 평택전력 변전협력회사 총액공사","원정S/S 154kV #6100 BUSTIE GIS 보통점검","2024-06-05 09:00","2024-06-05 18:00","2024-06-05 09:00","2024-06-05 18:00","연속"]
[232,"경기","평택","둔포추팔#1 T/L","154kV 오산-평택T/L 등 13개T/L 추락방지장치(수평) 설치공사","추락방지장치(수평) 18기 설치","2024-06-03 09:00","2024-06-05 15:00","2024-06-03 09:00","2024-06-05 15:00","연속"]
[233,"경기","평택","둔포추팔#2 T/L","154kV 오산-평택T/L 등 13개T/L 추락방지장치(수평) 설치공사","추락방지장치(수평) 1기 설치","2024-06-05 15:00","2024-06-05 18:00","2024-06-05 15:00","2024-06-05 18:00","연속"]
[234,"경기","평택","평택추팔#1 T/L","154kV 오산-평택T/L 등 13개T/L 추락방지장치(수평) 설치공사","추락방지장치(수평) 1기 설치","2024-06-05 15:00","2024-06-05 18:00","2024-06-05 15:00","2024-06-05 18:00","연속"]
[235,"경기","평택","평택추팔#2 T/L","154kV 오산-평택T/L 등 13개T/L 추락방지장치(수평) 설치공사","추락방지장치(수평) 1기 설치","2024-06-05 12:00","2024-06-05 15:00","2024-06-05 12:00","2024-06-05 15:00","연속"]
[236,"경기","성남","신봉이의#1 T/L"," 24-25년 경기직할 가공송전 협력회사 총액공사","불량애자 교체공사[4회선 병가]","2024-06-13 07:00","2024-06-13 18:00","2024-06-13 07:00","2024-06-13 18:00","연속"]
[237,"경기","성남","신봉이의#2 T/L"," 24-25년 경기직할 가공송전 협력회사 총액공사","불량애자 교체공사[4회선 병가]","2024-06-14 07:00","2024-06-14 18:00","2024-06-14 07:00","2024-06-14 18:00","연속"]
[238,"경기","성남","신성남서판교#1 T/L"," 2024년 성남전력 345, 154 GIS 보통점검공사","GIS 보통점검","2024-06-19 14:00","2024-06-19 18:00","2024-06-19 14:00","2024-06-19 18:00","연속"]
[239,"강원","강릉","간성S/S #2 BUS","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","#65-66B/S 설치 및 간성인제#1T/L 대체","2024-06-03 09:00","2024-06-12 12:00","2024-06-03 09:00","2024-06-12 12:00","연속"]
[240,"강원","강릉","속초간성#1 T/L","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","무부하 시험가압","2024-06-20 09:00","2024-06-21 18:00","2024-06-20 09:00","2024-06-21 18:00","연속"]
[241,"강원","강릉","간성S/S #1 BUS","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","#60-61B/S 설치 및 간성인제#1T/L 대체","2024-06-12 12:00","2024-06-21 18:00","2024-06-12 12:00","2024-06-21 18:00","연속"]
[242,"강원","강릉","속초간성#1 T/L","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","무부하 시험가압","2024-06-10 09:00","2024-06-11 18:00","2024-06-10 09:00","2024-06-11 18:00","연속"]
[243,"강원","강릉","간성S/S #2 BUS","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","154kV 간성인제#1T/L 대체공사","2024-06-24 09:00","2024-06-28 18:00","2024-06-24 09:00","2024-06-28 18:00","연속"]
[244,"강원","강릉","속초간성#1 T/L","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","안전이격 확보","2024-06-03 09:00","2024-06-03 18:00","2024-06-03 09:00","2024-06-03 18:00","연속"]
[245,"강원","강릉","간성인제#1 T/L","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","154kV 간성인제#1T/L 대체공사","2024-06-03 09:00","2024-06-28 18:00","2024-06-03 09:00","2024-06-28 18:00","연속"]
[246,"강원","강릉","속초간성#1 T/L","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","안전이격 확보","2024-06-14 09:00","2024-06-14 18:00","2024-06-14 09:00","2024-06-14 18:00","연속"]
[247,"강원","강릉","횡계올림픽 T/L","2024-2025년 강릉전력지사 송전협력회사 공사","○ 수평 추락방지장치 설치 : 154kV 횡계-평창T/L No.2~5, 올림픽분기T/L No.1","2024-06-13 08:00","2024-06-13 18:00","2024-06-13 08:00","2024-06-13 18:00","연속"]
[248,"강원","강릉","평창올림픽 T/L","2024-2025년 강릉전력지사 송전협력회사 공사","○ 수평 추락방지장치 설치 : 154kV 횡계-평창T/L No.7~96, 올림픽분기T/L No.1","2024-06-14 08:00","2024-06-26 18:00","2024-06-14 08:00","2024-06-26 18:00","매일"]
[249,"강원","동해","동해T/P#1 G.Tr CB 6183","2024년~25년 동해전력지사 변전협력회사 총액공사","1. 제작사 매커니즘 점검","2024-06-18 09:30","2024-06-18 13:30","2024-06-18 09:30","2024-06-18 13:30","연속"]
[250,"강원","동해","이원동해TP T/L","2024년~25년 동해전력지사 변전협력회사 총액공사","1. 제작사 매커니즘 점검","2024-06-19 09:30","2024-06-19 13:30","2024-06-19 09:30","2024-06-19 13:30","연속"]
[251,"강원","동해","삼척동해TP T/L","2024년~25년 동해전력지사 변전협력회사 총액공사","1. 제작사 매커니즘 점검","2024-06-19 14:00","2024-06-19 18:00","2024-06-19 14:00","2024-06-19 18:00","연속"]
[252,"강원","동해","태백삼척GP#1 T/L","2024~25년 동해전력지사 변전협력회사 총액공사","1. 647 차단기 보통점검 2. (병행) 송전선로보호반 초기점검(계통운영부)","2024-06-18 09:30","2024-06-18 18:00","2024-06-18 09:30","2024-06-18 18:00","연속"]
[253,"강원","동해","울진삼척GP#2 T/L","2024~25년 동해전력지사 변전협력회사 총액공사","1. 687 차단기 보통점검","2024-06-20 09:30","2024-06-20 18:00","2024-06-20 09:30","2024-06-20 18:00","연속"]
[254,"강원","원주","원주북원주#2 T/L","`23~24년 강원본부 지중송전설비 위탁정비공사","작업내용 : 154kV 원주북원주 인출C/H 피뢰기 점검 작업기간 - 원주-북원주#1T/L : `24.6.26 08:00 ~ 13:00 - 원주-북원주#2T/L : `24.6.26 13:00 ~ 18:00","2024-06-26 13:00","2024-06-26 18:00","취소","취소","연속"]
[255,"강원","원주","원주서원주#1 T/L","`23~24년 강원본부 지중송전설비 위탁정비공사","작업내용 : 154kV 원주서원주 인출C/H 피뢰기 점검 작업기간 - 원주-서원주#1T/L : `24.6.25 08:00 ~ 13:00 - 원주-서원주#2T/L : `24.6.25 13:00 ~ 18:00","2024-06-25 08:00","2024-06-25 13:00","2024-06-25 08:00","2024-06-25 13:00","연속"]
[256,"강원","원주","원주북원주#1 T/L","`23~24년 강원본부 지중송전설비 위탁정비공사","작업내용 : 154kV 원주북원주 인출C/H 피뢰기 점검 작업기간 - 원주-북원주#1T/L : `24.6.26 08:00 ~ 13:00 - 원주-북원주#2T/L : `24.6.26 13:00 ~ 18:00","2024-06-26 08:00","2024-06-26 13:00","취소","취소","연속"]
[257,"강원","원주","원주서원주#2 T/L","`23~24년 강원본부 지중송전설비 위탁정비공사","작업내용 : 154kV 원주서원주 인출C/H 피뢰기 점검 작업기간 - 원주-서원주#1T/L : `24.6.25 08:00 ~ 13:00 - 원주-서원주#2T/L : `24.6.25 13:00 ~ 18:00","2024-06-25 13:00","2024-06-25 18:00","2024-06-25 13:00","2024-06-25 18:00","연속"]
[258,"강원","원주","서원주문막#1 T/L","2024년 원주전력지사 154kV GIS 정밀점검 공사","154kV GIS 정밀점검","2024-06-03 09:00","2024-06-05 18:00","취소","취소","연속"]
[259,"강원","원주","서원주문막#2 T/L","2024년 원주전력지사 154kV GIS 정밀점검 공사","154kV GIS 정밀점검","2024-06-06 09:00","2024-06-08 18:00","취소","취소","연속"]
[260,"강원","원주","상남인제#2 T/L","24-25년 원주전력지사 변전협력회사 총액공사","차단기 동작시험","2024-06-26 10:00","2024-06-26 18:00","2024-06-26 10:00","2024-06-26 18:00","연속"]
[261,"강원","원주","횡성홍천#2 T/L","2024~2025년 원주전력지사 송전협력회사 공사","- 154kV 북원주횡성T/L No.19~125 추락방지장치 및 피뢰기설치 ※ 154kV 횡성홍천 No.1~57 병가구간 [동시휴전 필요]","2024-06-15 07:00","2024-06-16 18:00","2024-06-15 07:00","2024-06-16 18:00","매일"]
[262,"강원","원주","북원주횡성#1 T/L","2024~2025년 원주전력지사 송전협력회사 공사","- 154kV 북원주횡성T/L No.19~125 추락방지장치 및 피뢰기설치 ※ 154kV 횡성홍천 No.1~57 병가구간 [동시휴전 필요]","2024-06-15 07:00","2024-06-16 18:00","2024-06-15 07:00","2024-06-16 18:00","매일"]
[263,"강원","원주","횡성홍천#2 T/L","2024~2025년 원주전력지사 송전협력회사 공사","- 154kV 북원주횡성T/L No.19~125 추락방지장치 및 피뢰기설치 ※ 154kV 횡성홍천 No.1~57 병가구간 [동시휴전 필요]","2024-06-08 07:00","2024-06-09 18:00","2024-06-08 07:00","2024-06-09 18:00","매일"]
[264,"강원","원주","북원주횡성#1 T/L","2024~2025년 원주전력지사 송전협력회사 공사","- 154kV 북원주횡성T/L No.19~125 추락방지장치 설치","2024-06-08 07:00","2024-06-09 18:00","2024-06-08 07:00","2024-06-09 18:00","매일"]
[265,"강원","원주","북원주횡성#2 T/L","2024~2025년 원주전력지사 송전협력회사 공사","- 154kV 북원주횡성T/L No.19~125 추락방지장치 설치","2024-06-01 07:00","2024-06-02 18:00","취소","취소","매일"]
[266,"강원","원주","횡성홍천#1 T/L","2024~2025년 원주전력지사 송전협력회사 공사","- 154kV 북원주횡성T/L No.19~125 추락방지장치 설치 ※ 154kV 횡성홍천T/L No.1~57 병가구간 동시휴전필요","2024-06-01 07:00","2024-06-02 18:00","취소","취소","매일"]
[267,"강원","직할","청평HP의암HP T/L","2024년 강원직할 가공송전 순시점검 위탁공사","154kV 의암T/L No.13 수목벌채 시행","2024-06-10 09:00","2024-06-11 18:00","2024-06-10 09:00","2024-06-11 18:00","연속"]
[268,"강원","직할","인제양구#1 T/L","154kV 상제 등 3개 T/L 추락방지장치 설치공사","154kV 양구 T/L 추락방지장치 설치공사","2024-06-17 07:00","2024-06-28 18:00","2024-06-17 07:00","2024-06-28 18:00","매일"]
[269,"강원","직할","상남인제#1 T/L","154kV 상제 등 3개 T/L 추락방지장치 설치공사","154kV 상제 T/L 추락방지장치 설치공사","2024-06-03 07:00","2024-06-14 18:00","2024-06-03 07:00","2024-06-14 18:00","매일"]
[270,"강원","직할","가평춘천HP T/L","154kV 상제 등 3개 T/L 추락방지장치 설치공사","154kV 화천 T/L 추락방지장치 설치공사","2024-06-24 09:00","2024-06-26 18:00","2024-06-24 09:00","2024-06-26 18:00","연속"]
[271,"강원","직할","청평PP춘천열병합 T/L","2024-2025년 강원본부 직할 송전협력회사 공사","154kV 청평양수 #3,4 T/L No.25 압축인류 클램프 보수","2024-06-04 09:00","2024-06-04 14:00","2024-06-04 09:00","2024-06-04 14:00","연속"]
[272,"강원","직할","가평화천HP T/L","154kV 상제 등 3개 T/L 추락방지장치 설치공사","154kV 화천T/L 추락방지장치 설치공사","2024-06-03 09:00","2024-06-14 18:00","2024-06-03 09:00","2024-06-14 18:00","연속"]
[273,"강원","직할","북춘천화천HP T/L","154kV 상제 등 3개 T/L 추락방지장치 설치공사","154kV 화천 T/L 추락방지장치 설치공사","2024-06-17 09:00","2024-06-21 18:00","2024-06-17 09:00","2024-06-21 18:00","연속"]
[274,"강원","태백","동해동영월 T/L","2024~2025년 태백전력지사 가공송전 협력회사 총액공사","154kV 동해-동영월T/L 수평추락방지장치 설치 동영월S/S 동해-동영월T/L GIS 정밀점검(병행)","2024-06-10 08:00","2024-06-23 18:00","2024-06-10 08:00","2024-06-23 18:00","매일"]
[275,"강원","태백","동해동영월 T/L","2024년 태백전력지사 154kV GIS 정밀점검공사","동영월S/S 동해-동영월T/L GIS 정밀점검 영월화력 수평추락방지장치 설치(병행)","2024-06-17 09:00","2024-06-19 18:00","취소","취소","연속"]
[276,"강원","태백","동영월영월CC T/L","2024년 태백전력지사 154kV GIS 정밀점검공사","동영월S/S 154kV 동영월-영월CC T/L GIS 정밀점검 154kV 동영월-영월CCT/L 수평추락방지장치 설치(병행)","2024-06-24 09:00","2024-06-26 18:00","취소","취소","연속"]
[277,"강원","태백","동영월영월CC T/L","2024~2025년 태백전력지사 가공송전 협력회사 총액공사","154kV 동영월-영월CCT/L 수평추락방지장치 설치 동영월S/S 154kV 동영월-영월CC T/L GIS 정밀점검(병행)","2024-06-24 09:00","2024-06-30 18:00","2024-06-24 09:00","2024-06-30 18:00","매일"]
[278,"강원","태백","제천영월#2 T/L","2024-2025년 태백전력지사 변전협력회사 공사","영월S/S 154kV 제천-영월#2T/L GIS 조작시험 영월S/S 154kV 제천-영월#2T/L 송전선로 보호반 성능개선(병행)","2024-06-27 09:00","2024-06-27 18:00","2024-06-27 09:00","2024-06-27 18:00","연속"]
[279,"강원","태백","제천영월#1 T/L","2024-2025년 태백전력지사 변전협력회사 공사","영월S/S 154kV 제천-영월#1T/L GIS 조작시험 영월S/S 154kV 제천-영월#1T/L 송전선로 보호반 성능개선(병행)","2024-06-26 09:00","2024-06-26 18:00","2024-06-26 09:00","2024-06-26 18:00","연속"]
[280,"강원","태백","태백S/S #65 BUS","154kV 태백S/S #2M.Tr 증설공사","#2M.Tr 최초가압","2024-06-27 14:00","2024-06-28 14:00","취소","취소","연속"]
[281,"강원","태백","태백영월에코윈드 T/L","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치 - 기타 부대공사","2024-06-04 10:00","2024-06-07 18:00","취소","취소","연속"]
[282,"강원","태백","태백S/S #65 BUS","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치 - 기타 부대공사","2024-06-04 10:00","2024-06-07 18:00","취소","취소","연속"]
[283,"강원","태백","태백삼척GP#1 T/L","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치 - 기타 부대공사","2024-06-06 10:00","2024-06-07 18:00","취소","취소","연속"]
[284,"강원","태백","태백S/S #60 BUS","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치 - 기타 부대공사","2024-06-10 10:00","2024-06-14 18:00","취소","취소","연속"]
[285,"강원","태백","태백영월에코윈드 T/L","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치 - 기타 부대공사","2024-06-10 10:00","2024-06-14 18:00","취소","취소","연속"]
[286,"강원","태백","태백삼척GP#1 T/L","154kV 태백S/S #2M.Tr 증설공사","#2M.Tr 최초가압","2024-06-26 14:00","2024-06-28 14:00","취소","취소","연속"]
[287,"강원","태백","태백S/S #60 BUS","154kV 태백S/S #2M.Tr 증설공사","#2M.Tr 최초가압","2024-06-26 14:00","2024-06-27 14:00","취소","취소","연속"]
[288,"강원","태백","태백삼척GP#1 T/L","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치 - 기타 부대공사","2024-06-13 10:00","2024-06-14 18:00","취소","취소","연속"]
[289,"충북","직할","진천덕산#2 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","154kV 진천-덕산#2T/L 피뢰기 설치 및 애자교체 (No.1~27 피뢰기 설치, No.15 애자교체)","2024-06-10 07:00","2024-06-12 18:00","2024-06-10 07:00","2024-06-12 18:00","매일"]
[290,"충북","직할","신진천진천#1 T/L","'24-25년 충북 직할 154kV GIS 정밀점검 공사","진천S/S 154kV 신진천-진천#1T/L 정밀점검","2024-06-08 09:00","2024-06-10 18:00","취소","취소","연속"]
[291,"충북","직할","신진천진천#2 T/L","'24-25년 충북 직할 154kV GIS 정밀점검 공사","진천S/S 154kV 신진천-진천#2T/L 정밀점검","2024-06-01 09:00","2024-06-03 18:00","취소","취소","연속"]
[292,"충북","직할","진천광혜원#2 T/L","'24-25년 충북 직할 154kV GIS 정밀점검 공사","진천S/S 154kV 진천-광혜원#2T/L 정밀점검","2024-06-22 09:00","2024-06-24 18:00","2024-06-22 09:00","2024-06-24 18:00","연속"]
[293,"충북","직할","진천광혜원#1 T/L","'24-25년 충북 직할 154kV GIS 정밀점검 공사","진천S/S 154kV 진천-광혜원#1T/L 정밀점검","2024-06-15 09:00","2024-06-17 18:00","2024-06-15 09:00","2024-06-17 18:00","연속"]
[294,"충북","청주","남청주S/S #67 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체","2024-06-25 14:00","2024-06-30 14:00","취소","취소","연속"]
[295,"충북","청주","남청주청주#2 T/L","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-06-03 08:00","2024-06-21 18:00","취소","취소","연속"]
[296,"충북","청주","남청주청주#4 T/L","2024~2025년 송전정비 협력회사 총액공사","154kV 남청주-청주#2,#4T/L(아킹혼, 폴리머지지애자 설치) 1. 내용 : 아킹혼, 폴리머지지애자 설치 2. 구간 : 남청주S/S~청주S/S","2024-06-03 08:00","2024-06-21 18:00","취소","취소","매일"]
[297,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-06-03 08:00","2024-06-06 14:00","취소","취소","연속"]
[298,"충북","청주","남청주S/S #61 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-06-06 14:00","2024-06-14 14:00","취소","취소","연속"]
[299,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체","2024-06-30 14:00","2024-07-02 18:00","취소","취소","연속"]
[300,"충북","청주","남청주오송#1 T/L","남청주S/S 154kV 장기사용 GIS 대체공사(2차)","#66-67 SEC GIIS 대체 (무부하가압용)","2024-06-29 14:00","2024-06-30 14:00","취소","취소","연속"]
[301,"충북","청주","남청주청주#1 T/L","2024~2025년 송전정비 협력회사 총액공사","154kV 남청주-청주#1,#3T/L(아킹혼, 폴리머지지애자 설치) 1. 내용 : 아킹혼, 폴리머지지애자 설치 2. 구간 : 남청주S/S~청주S/S","2024-06-24 08:00","2024-06-27 18:00","취소","취소","매일"]
[302,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-06-14 14:00","2024-06-21 18:00","취소","취소","연속"]
[303,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체","2024-06-24 08:00","2024-06-25 14:00","취소","취소","연속"]
[304,"충북","청주","남청주청주#3 T/L","2024~2025년 송전정비 협력회사 총액공사","154kV 남청주-청주#1,#3T/L(아킹혼, 폴리머지지애자 설치) 1. 내용 : 아킹혼, 폴리머지지애자 설치 2. 구간 : 남청주S/S~청주S/S","2024-06-24 08:00","2024-06-27 18:00","취소","취소","매일"]
[305,"충북","청주","남청주S/S SEC CB 67660","남청주S/S 154kV 장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체","2024-06-24 08:00","2024-07-02 18:00","취소","취소","연속"]
[306,"충북","청주","국사봉명#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사","170kV GIS 보통점검 CVT, LA 점검","2024-06-19 10:00","2024-06-19 18:00","2024-06-19 10:00","2024-06-19 18:00","연속"]
[307,"충북","청주","북청주봉명#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사","170kV GIS 보통점검","2024-06-20 10:00","2024-06-20 18:00","2024-06-20 10:00","2024-06-20 18:00","연속"]
[308,"충북","청주","국사봉명#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사","170kV GIS 보통점검 CVT, LA 점검","2024-06-18 10:00","2024-06-18 18:00","2024-06-18 10:00","2024-06-18 18:00","연속"]
[309,"충북","청주","서청주사직#1 T/L","대한전선제 열경화공법 EBG 보강공사","청주S/S, 사직S/S 154kV 서청주-사직T/L EBG 보강공사","2024-06-01 09:00","2024-06-02 18:00","취소","취소","연속"]
[310,"충북","청주","서청주사직#2 T/L","대한전선제 열경화공법 EBG 보강공사","청주S/S, 사직S/S 154kV 서청주-사직T/L EBG 보강공사","2024-06-22 09:00","2024-06-23 18:00","취소","취소","연속"]
[311,"충북","청주","신진천오창#1 T/L","24년 청주전력지사 170kV GIS 정밀점검","오창S/S 154kV 신진천-오창#1T/L GIS 정밀점검","2024-06-10 09:00","2024-06-11 18:00","취소","취소","연속"]
[312,"충북","청주","오창국사#1 T/L","24년 청주전력지사 170kV GIS 정밀점검","오창S/S 154kV 나투라페이퍼T/L GIS 정밀점검 무부하 가압","2024-06-17 16:00","2024-06-17 18:00","2024-06-17 16:00","2024-06-17 18:00","연속"]
[313,"충북","청주","오창국사#1 T/L","24년 청주전력지사 170kV GIS 정밀점검","오창S/S 154kV #6100BUS-TIE GIS 정밀점검 무부하 가압","2024-06-19 16:00","2024-06-19 18:00","취소","취소","연속"]
[314,"충북","청주","오창국사#1 T/L","24년 청주전력지사 170kV GIS 정밀점검","오창S/S 154kV 오창-국사#1T/L GIS 정밀점검","2024-06-12 09:00","2024-06-13 18:00","취소","취소","연속"]
[315,"충북","청주","오창S/S CB 6100","24년 청주전력지사 170kV GIS 정밀점검","오창S/S 154kV 나투라페이퍼T/L GIS 정밀점검 무부하 가압","2024-06-17 16:00","2024-06-17 18:00","2024-06-17 16:00","2024-06-17 18:00","연속"]
[316,"충북","청주","오창S/S #1 BUS","24년 청주전력지사 170kV GIS 정밀점검","오창S/S 154kV 나투라페이퍼1T/L GIS 정밀점검 무부하 가압","2024-06-17 16:00","2024-06-17 18:00","2024-06-17 16:00","2024-06-17 18:00","연속"]
[317,"충북","청주","죽림청주열병#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사","170kV GIS 보통점검","2024-06-03 10:00","2024-06-03 18:00","2024-06-03 10:00","2024-06-03 18:00","연속"]
[318,"충북","청주","죽림청주열병#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사","170kV GIS 보통점검","2024-06-04 10:00","2024-06-04 18:00","2024-06-04 10:00","2024-06-04 18:00","연속"]
[319,"충북","충주","감곡S/S CB 6100","2024년 충주전력지사 170kV GIS 정밀점검","감곡S/S 170kV 동부#2T/L GIS 정밀점검 후 무부하가압용","2024-06-18 17:00","2024-06-18 18:00","2024-06-18 17:00","2024-06-18 18:00","연속"]
[320,"충북","충주","감곡S/S #2 BUS","2024년 충주전력지사 170kV GIS 정밀점검","감곡S/S 170kV 동부#2T/L GIS 정밀점검 후 무부하가압용","2024-06-18 17:00","2024-06-18 18:00","2024-06-18 17:00","2024-06-18 18:00","연속"]
[321,"충북","충주","신충주감곡#2 T/L","2024년 충주전력지사 170kV GIS 정밀점검","감곡S/S 170kV 동부#2T/L GIS 정밀점검 후 무부하가압용","2024-06-18 17:00","2024-06-18 18:00","2024-06-18 17:00","2024-06-18 18:00","연속"]
[322,"충북","충주","신충주감곡#2 T/L","2024년 충주전력지사 170kV GIS 정밀점검","감곡S/S 170kV 동부#1T/L GIS 정밀점검 후 무부하가압용","2024-06-20 17:00","2024-06-20 18:00","취소","취소","연속"]
[323,"충북","충주","감곡S/S #1 BUS","2024년 충주전력지사 170kV GIS 정밀점검","감곡S/S 170kV 동부#1T/L GIS 정밀점검 후 무부하가압용","2024-06-20 17:00","2024-06-20 18:00","취소","취소","연속"]
[324,"충북","충주","감곡S/S CB 6100","2024년 충주전력지사 170kV GIS 정밀점검","감곡S/S 170kV 동부#1T/L GIS 정밀점검 후 무부하가압용","2024-06-20 17:00","2024-06-20 18:00","취소","취소","연속"]
[325,"충북","충주","금왕남음성#2 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","154kV 금왕-남음성#2T/L 피뢰기 설치(No.42)","2024-06-02 07:00","2024-06-02 18:00","2024-06-02 07:00","2024-06-02 18:00","매일"]
[326,"충북","충주","남음성덕산#2 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","154kV 남음성-덕산#2T/L 피뢰기 설치(No.1~5, 17~21)","2024-06-02 07:00","2024-06-02 18:00","2024-06-02 07:00","2024-06-02 18:00","매일"]
[327,"충북","충주","신제천왕암#2 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.1, 28-37)","2024-06-01 07:30","2024-06-02 16:30","2024-06-01 07:30","2024-06-02 16:30","매일"]
[328,"충북","충주","신제천남원주#1 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.1~37)","2024-06-22 07:30","2024-06-23 16:30","취소","취소","매일"]
[329,"충북","충주","신제천왕암#1 T/L","345kV 신제천-신충주 등 6개T/L 피뢰기 설치공사","154kV 신제천-왕암#1T/L No.1~27 피뢰기 설치(6.7 작업없음)","2024-06-08 07:00","2024-06-09 18:00","취소","취소","매일"]
[330,"충북","충주","신제천제천#1 T/L","345kV 신제천-신충주 등 6개T/L 피뢰기 설치공사","154kV 신제천-제천#1T/L No.1~27.9 피뢰기 설치","2024-06-08 07:00","2024-06-09 18:00","취소","취소","매일"]
[331,"충북","충주","신제천남원주#1 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.1~37)","2024-06-15 07:30","2024-06-16 16:30","취소","취소","매일"]
[332,"충북","충주","왕암충주 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.9~112)","2024-06-03 07:30","2024-06-07 16:30","2024-06-03 07:30","2024-06-07 16:30","매일"]
[333,"충북","충주","음성사리 T/L","154kV 음성천연가스S/Y 건설공사","- 154kV 음성-사리T/L 보호배전반 철거 및 설치","2024-06-04 09:00","2024-06-20 18:00","2024-06-04 09:00","2024-06-20 18:00","연속"]
[334,"충북","충주","음성괴산 T/L","154kV 음성천연가스S/Y 건설공사","- 154kV 음성-괴산T/L 보호배전반 철거 및 설치","2024-06-21 09:00","2024-07-01 18:00","2024-06-21 09:00","2024-07-01 18:00","연속"]
[335,"충북","충주","제천영월#1 T/L","2024년 충주전력지사 170kV GIS 정밀점검","제천S/S 170kV 6100 BUS TIE GIS 정밀점검 후 무부하가압용","2024-06-05 17:00","2024-06-05 18:00","취소","취소","연속"]
[336,"충북","충주","충주S/S #65 BUS","2024년 충주전력지사 170kV GIS 정밀점검","충주S/S 170kV #1Sh.C GIS 정밀점검 후 무부하가압용","2024-06-26 17:00","2024-06-26 18:00","2024-06-26 17:00","2024-06-26 18:00","연속"]
[337,"충북","충주","충주충주HP#1 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.7~22)","2024-06-03 07:30","2024-06-05 16:30","2024-06-03 07:30","2024-06-05 16:30","매일"]
[338,"충북","충주","충주S/S SEC CB 65660","2024년 충주전력지사 170kV GIS 정밀점검","충주S/S 170kV #1Sh.C GIS 정밀점검 후 무부하가압용","2024-06-26 17:00","2024-06-26 18:00","2024-06-26 17:00","2024-06-26 18:00","연속"]
[339,"충북","충주","충주S/S CB 6100","2024년 충주전력지사 170kV GIS 정밀점검","충주S/S 170kV #1Sh.C GIS 정밀점검 후 무부하가압용","2024-06-26 17:00","2024-06-26 18:00","2024-06-26 17:00","2024-06-26 18:00","연속"]
[340,"충북","충주","풍동음성#2 T/L","음성천연가스발전소 154kV 송전선로 건설공사(동서발전 시행)","- 본선로 구성을 위한 휴전(4회선 2파이분기)","2024-06-04 08:00","2024-06-20 18:00","2024-06-04 08:00","2024-06-20 18:00","연속"]
[341,"충북","충주","풍동음성#1 T/L","음성천연가스발전소 154kV 송전선로 건설공사(동서발전 시행)","- 본선로 구성을 위한 휴전(4회선 2파이분기)","2024-06-21 08:00","2024-07-01 18:00","2024-06-21 08:00","2024-07-01 18:00","연속"]
[342,"대전세종충남","대전","추부금산#1 T/L","[송전][즉시가압O]154kV 추부-금산#1등2개T/L추락방지 설치공사","[송전][주말작업제외][즉시가압가능]154kV 추부-금산#1 등 2개T/L 추락방지장치 설치공사","2024-06-07 07:00","2024-06-27 18:00","취소","취소","매일"]
[343,"대전세종충남","대전","팔봉두마#2 T/L","154kV 팔봉-두마T/L 용량증대 전선교체공사","공사구간 : 154kV 팔봉-두마T/L No.67~109 공사내용 : ACSR 240㎟ → ASCC/TW 310㎟ x S x 2C, 15km 전선교체 저지상고 및 취약 철탑 교체 6기","2024-06-24 07:00","2024-07-24 18:00","취소","취소","연속"]
[344,"대전세종충남","대전","신옥천서대전 T/L","[송전][즉시가압O]154kV 신옥천-서대전T/L 지장수목벌채작업","[송전][즉시가압O]154kV 신옥천-서대전T/L 지장수목벌채작업","2024-06-19 07:00","2024-06-21 18:00","취소","취소","매일"]
[345,"대전세종충남","대전","신옥천유천 T/L","유천S/S 154kV 신옥천-유천T/L GIS 송전선로 보호반 대체","유천S/S 154kV 신옥천-유천T/L GIS 송전선로 보호반 대체","2024-06-10 09:00","2024-06-13 18:00","2024-06-10 09:00","2024-06-13 18:00","연속"]
[346,"대전세종충남","대전","추부S/S #1 BUS","추부S/S 154kV #3M.Tr 증설공사","- 154kV M.Tr * 1Bank 설치 - 154kV GIS * 1CCT 설치 - 23kV GIS * 3CCT 설치","2024-06-25 09:00","2024-06-27 18:00","취소","취소","연속"]
[347,"대전세종충남","대전","신옥천추부#1 T/L","추부S/S 154kV #3M.Tr 증설공사","- 154kV M.Tr * 1Bank 설치 - 154kV GIS * 1CCT 설치 - 23kV GIS * 3CCT 설치","2024-06-24 17:00","2024-06-25 09:00","취소","취소","연속"]
[348,"대전세종충남","대전","추부S/S CB 6100","추부S/S 154kV #3M.Tr 증설공사","- 154kV M.Tr * 1Bank 설치 - 154kV GIS * 1CCT 설치 - 23kV GIS * 3CCT 설치","2024-06-24 17:00","2024-06-25 09:00","취소","취소","연속"]
[349,"대전세종충남","대전","추부S/S #2 BUS","추부S/S 154kV #3M.Tr 증설공사","- 154kV M.Tr * 1Bank 설치 - 154kV GIS * 1CCT 설치 - 23kV GIS * 3CCT 설치","2024-06-20 09:00","2024-06-25 09:00","취소","취소","연속"]
[350,"대전세종충남","대전","신옥천추부#1 T/L","추부S/S 154kV #3M.Tr 증설공사","- 154kV M.Tr * 1Bank 설치 - 154kV GIS * 1CCT 설치 - 23kV GIS * 3CCT 설치","2024-06-19 17:00","2024-06-20 09:00","취소","취소","연속"]
[351,"대전세종충남","대전","추부S/S #1 BUS","추부S/S 154kV #3M.Tr 증설공사","- 154kV M.Tr * 1Bank 설치 - 154kV GIS * 1CCT 설치 - 23kV GIS * 3CCT 설치","2024-06-17 09:00","2024-06-20 09:00","취소","취소","연속"]
[352,"대전세종충남","대전","신옥천추부#2 T/L","[송전][즉시가압O]154kV 추부-금산#1등2개T/L추락방지 설치공사","[송전][주말작업제외][즉시가압가능] 154kV 추부-금산#1 등 2개T/L 추락방지장치 설치공사","2024-06-03 07:00","2024-06-12 18:00","취소","취소","매일"]
[353,"대전세종충남","대전","추부S/S CB 6100","추부S/S 154kV #3M.Tr 증설공사","- 154kV M.Tr * 1Bank 설치 - 154kV GIS * 1CCT 설치 - 23kV GIS * 3CCT 설치","2024-06-19 17:00","2024-06-20 09:00","취소","취소","연속"]
[354,"대전세종충남","서산","석문당진화력#2 T/L","효성제 170kV GIS 베어링 교체공사","(5월 휴전신청 취소시) (즉시가압 가능) 당진화력S/S 154kV 석문-당진화력#2T/L 627 CB 베어링 교체 (병행) 석문S/S 154kV 석문-당진화력#2T/L IED 성능개선 (병행) 석문S/S 154kV 석문-당진화력#2T/L 687 CB 보통점검 (병행) 당진화력S/S 154kV 석문-당진화력#2T/L 627 CB 보통점검","2024-06-13 09:00","2024-06-14 18:00","취소","취소","매일"]
[355,"대전세종충남","서산","석문당진화력#1 T/L","효성제 170kV GIS 베어링 교체공사","(5월 휴전신청 취소시) (즉시가압 가능) 당진화력S/S 154kV 석문-당진화력T/L 617 CB 베어링 교체 (병행) 석문S/S 154kV 석문-당진화력#1T/L IED 성능개선 (병행) 석문S/S 154kV 석문-당진화력#1T/L 617 CB 보통점검 (병행) 당진화력S/S 154kV 석문-당진화력#1T/L 617CB 보통점검","2024-06-11 09:30","2024-06-12 18:00","취소","취소","매일"]
[356,"대전세종충남","서산","대산석문#1 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.35~37,43,46,47), 즉시가압(20분 이내)가능","2024-06-17 08:00","2024-06-17 18:00","취소","취소","연속"]
[357,"대전세종충남","서산","대산석문#2 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.28~34,38~42,44,45), 즉시가압(20분 이내)가능","2024-06-18 08:00","2024-06-18 18:00","취소","취소","연속"]
[358,"대전세종충남","서산","서산대산 T/L","23년 서산P/O 장기사용 배전반 교체공사","(즉시가압 불가) (5월 휴전취소시) 서산,대산S/S 154kV 서산-대산T/L 보호반 대체","2024-06-03 09:00","2024-06-05 18:00","2024-06-03 09:00","2024-06-05 18:00","연속"]
[359,"대전세종충남","서산","서산홍성 T/L","'24~'25년도 서산전력지사 송전협력회사","154kV 서산-홍성T/L 항공구 설치공사, 즉시가압(20분이내)불가 No.67.1~68 1경간 *5월 휴전 승인시 취소요청","2024-06-07 08:00","2024-06-07 18:00","취소","취소","연속"]
[360,"대전세종충남","서산","서산해미 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (154kV 서산T/L No.65~135, 154kV 해미분기T/L No.1~30) 즉시가압(20분 이내)가능, 주말작업 없음","2024-06-19 09:00","2024-06-27 18:00","2024-06-17 09:00","2024-06-25 18:00","매일"]
[361,"대전세종충남","서산","신당진서산#1 T/L","'24~'25년도 서산전력지사 송전협력회사","154kV 신당진-서산#1T/L 점퍼지지애자 교체공사, 즉시가압(20분이내)불가 No.60 (1기)","2024-06-24 08:00","2024-06-24 18:00","2024-06-24 08:00","2024-06-24 18:00","연속"]
[362,"대전세종충남","서산","서산태안#1 T/L","'24~'25년도 서산전력지사 송전협력회사","154kV 서산-대산T/L 항공구 설치공사, 즉시가압(20분이내)불가 No.9~10,11~12(2경간) *5월 휴전 승인시 취소요청 *154 서산-대산T/L 병가선로, 서산-대산T/L 휴전 미승인시 취소요청","2024-06-05 08:00","2024-06-05 18:00","취소","취소","연속"]
[363,"대전세종충남","서산","서산대산 T/L","'24~'25년도 서산전력지사 송전협력회사","154kV 서산-대산T/L 항공구 설치공사, 즉시가압(20분이내)불가 No.9~10,11~12(2경간) *5월 휴전 승인시 취소요청","2024-06-05 08:00","2024-06-05 18:00","취소","취소","연속"]
[364,"대전세종충남","서산","해미홍성 T/L","'24~'25년도 서산전력지사 송전협력회사 공사","154kV 해미-홍성T/L 항공장애표시구 설치공사 No.8~9,17~19, 즉시가압(20분이내) 불가능 *154kV 은하-홍성#2T/L 병가구간은 (No.8~9)이므로 은하홍성 휴전 미승인시에도 휴전 승인 요청","2024-06-10 08:00","2024-06-11 18:00","취소","취소","매일"]
[365,"대전세종충남","세종","덕진공주#1 T/L","154kV 덕진-공주#1T/L 불량애자 교체공사","154kV 덕진-공주#1T/L No.3,4,6 3기 / 6개소","2024-06-12 09:00","2024-06-14 18:00","2024-06-12 09:00","2024-06-14 18:00","매일"]
[366,"대전세종충남","세종","덕진유성#1 T/L","154kV 덕진-유성#1T/L 불량애자 교체공사","154kV 덕진-유성#1T/L No.25 1기 / 1개소","2024-06-12 09:00","2024-06-14 18:00","2024-06-12 09:00","2024-06-14 18:00","매일"]
[367,"대전세종충남","세종","덕진유성#2 T/L","154kV 덕진-유성#2T/L 불량애자 교체 공사","154kV 덕진-유성#2T/L No.8 1기 / 1개소 불량애자 교체 공사","2024-06-03 09:00","2024-06-11 18:00","2024-06-05 09:00","2024-06-11 18:00","매일"]
[368,"대전세종충남","세종","덕진공주#2 T/L","154kV 덕진-공주#2T/L 불량애자 교체공사 및 피뢰기 설치공사","불량애자교체 공사 : 154kV 덕진-공주#2T/L S/T, No.3,4,8,28 4기 / 7개소피뢰기 설치공사 : 154kV 덕진-공주#2T/L No.1 등 31개 철탑","2024-06-03 09:00","2024-06-11 18:00","2024-06-05 09:00","2024-06-11 18:00","매일"]
[369,"대전세종충남","세종","서세종S/S CB 6100","[변전]'24년 세종전력지사 변전협력회사 총액공사","○ 154kV GIS 보통점검","2024-06-04 10:00","2024-06-04 18:00","2024-06-04 10:00","2024-06-04 18:00","연속"]
[370,"대전세종충남","세종","서세종조치원 T/L","[변전]'24년 세종전력지사 변전협력회사 총액공사(5월 휴전 취소시)","○ 154kV GIS 보통점검 -조치원S/S GIS, LA 보통점검 -서세종S/S GIS 보통점검 -조치원S/S 전자변 교체 병행","2024-06-05 10:00","2024-06-05 18:00","2024-06-05 10:00","2024-06-05 18:00","연속"]
[371,"대전세종충남","세종","월산서세종 T/L","[지중] 23-24 지중송전설비 위탁정비공사(5월 휴전 취소시)","○ EBA 절연유 채유 - 154kV 월산-서세종 C/T 3상 EBA 절연유 채유 - 세종전력지사 서세종S/S 154kV GIS 보통점검 병행 - 세종전력지사 월산S/S 154kV GIS 차단기 조작시험 병행","2024-06-12 09:00","2024-06-12 18:00","취소","취소","연속"]
[372,"대전세종충남","세종","세종둔곡#1 T/L","[변전]'24년 세종전력지사 변전협력회사 총액공사","○154kV GIS 보통점검","2024-06-10 10:00","2024-06-10 18:00","2024-06-10 10:00","2024-06-10 18:00","연속"]
[373,"대전세종충남","세종","세종S/S #65 BUS","세종S/S 154kV #61D.Tr 증설(무부하 가압)","세종S/S 154kV #61D.Tr 증설(무부하 가압)","2024-06-20 11:00","2024-06-21 11:00","2024-06-20 11:00","2024-06-21 11:00","연속"]
[374,"대전세종충남","세종","세종서세종#2 T/L","세종S/S 154kV #61D.Tr 증설(무부하 가압)","세종S/S 154kV #61D.Tr 증설(무부하 가압)","2024-06-20 09:00","2024-06-21 11:00","2024-06-20 09:00","2024-06-21 11:00","연속"]
[375,"대전세종충남","세종","세종S/S #60 BUS","세종S/S 154kV #61D.Tr 증설(무부하 가압)","세종S/S 154kV #61D.Tr 증설(무부하 가압)","2024-06-20 09:00","2024-06-20 11:00","2024-06-20 09:00","2024-06-20 11:00","연속"]
[376,"대전세종충남","세종","세종S/S CB 6100","세종S/S 154kV #61D.Tr 증설(무부하 가압)","세종S/S 154kV #61D.Tr 증설(무부하 가압)","2024-06-20 09:00","2024-06-21 11:00","2024-06-20 09:00","2024-06-21 11:00","연속"]
[377,"대전세종충남","세종","세종S/S CB 6100","세종S/S 154kV #61D.Tr 증설공사(모선보호반 연동시험)","세종S/S 154kV #61D.Tr 증설공사(모선보호반 연동시험)","2024-06-19 09:00","2024-06-19 18:00","2024-06-19 09:00","2024-06-19 18:00","연속"]
[378,"대전세종충남","세종","세종둔곡#2 T/L","[변전]'24년 세종전력지사 변전협력회사 총액공사","○154kV GIS 보통점검","2024-06-11 10:00","2024-06-11 18:00","2024-06-11 10:00","2024-06-11 18:00","연속"]
[379,"대전세종충남","세종","조치원월산 T/L","[변전]'24년 세종전력지사 변전협력회사 총액공사(5월 휴전 취소시)","○ 154kV GIS 보통점검 -월산,조치원S/S GIS, LA 보통점검 -조치원S/S 전자변 교체 병행","2024-06-03 10:00","2024-06-03 18:00","2024-06-03 10:00","2024-06-03 18:00","연속"]
[380,"대전세종충남","천안","둔포석곡#1 T/L","둔포S/S 154kV 둔포-석곡#1T/L CB 개폐타임측정","(즉시가압가능)둔포S/S 154kV 둔포-석곡#1T/L CB 개폐타임측정","2024-06-18 09:00","2024-06-18 18:00","2024-06-18 09:00","2024-06-18 18:00","연속"]
[381,"대전세종충남","천안","둔포석곡#2 T/L","둔포S/S 154kV 둔포-석곡#2T/L CB 개폐타임측정","(즉시가압가능)둔포S/S 154kV 둔포-석곡#2T/L CB 개폐타임측정","2024-06-19 09:00","2024-06-19 18:00","2024-06-19 09:00","2024-06-19 18:00","연속"]
[382,"대전세종충남","천안","불당서천안#1 T/L","불당S/S 154kV 불당-서천안#1T/L CB 개폐타임측정","(즉시가압가능)불당S/S 154kV 불당-서천안#1T/L CB 개폐타임측정","2024-06-20 09:00","2024-06-20 18:00","2024-06-20 09:00","2024-06-20 18:00","연속"]
[383,"대전세종충남","천안","장재불당#1 T/L","불당S/S 154kV 장재-불당#1T/L CB 개폐타임측정","(즉시가압가능)불당S/S 154kV 장재-불당#1T/L CB 개폐타임측정","2024-06-18 09:00","2024-06-18 18:00","취소","취소","연속"]
[384,"대전세종충남","천안","장재불당#2 T/L","불당S/S 154kV 장재-불당#2T/L CB 개폐타임측정","(즉시가압가능)불당S/S 154kV 장재-불당#2T/L CB 개폐타임측정","2024-06-19 09:00","2024-06-19 18:00","취소","취소","연속"]
[385,"대전세종충남","천안","불당서천안#2 T/L","불당S/S 154kV 불당-서천안#2T/L CB 개폐타임측정","(즉시가압가능)불당S/S 154kV 불당-서천안#2T/L CB 개폐타임측정","2024-06-21 09:00","2024-06-21 18:00","2024-06-21 09:00","2024-06-21 18:00","연속"]
[386,"대전세종충남","천안","신온양한샘#1 T/L","[5월 취소시]154kV 신온양-한샘T/L 추락방지장치 설치공사","[즉시가압가능]154kV 신온양-한샘T/L 추락방지장치 설치 4회선 병가철탑 신온양한샘#1(상단), 신온양석곡#1(하단)","2024-06-04 07:00","2024-06-04 17:00","2024-06-04 07:00","2024-06-04 17:00","연속"]
[387,"대전세종충남","천안","신온양석곡#2 T/L","[5월 취소시]154kV 신온양-석곡T/L 추락방지장치 설치공사","[즉시가압가능]154kV 신온양-한샘T/L 추락방지장치 설치 4회선 병가철탑 신온양한샘#2(상단), 신온양석곡#2(하단)","2024-06-03 07:00","2024-06-03 17:00","2024-06-03 07:00","2024-06-03 17:00","연속"]
[388,"대전세종충남","천안","신온양석곡#1 T/L","[5월 취소시]154kV 신온양-석곡T/L 추락방지장치 설치공사","[즉시 가압가능] 154kV 신온양-석곡T/L 추락방지장치 설치 4회선 병가철탑 신온양한샘#1(상단), 신온양석곡#1(하단)","2024-06-04 07:00","2024-06-04 17:00","2024-06-04 07:00","2024-06-04 17:00","연속"]
[389,"대전세종충남","천안","신온양한샘#2 T/L","[5월 취소시]154kV 신온양-한샘T/L 추락방지장치 설치공사","[즉시 가압가능] 154kV 신온양-한샘T/L 추락방지장치 설치 4회선 병가철탑 신온양한샘#2(상단), 신온양석곡#2(하단)","2024-06-03 07:00","2024-06-03 17:00","2024-06-03 07:00","2024-06-03 17:00","연속"]
[390,"대전세종충남","천안","아산합덕#1 T/L","아산S/S 154kV 아산-합덕#1T/L GIS 보통점검","(즉시가압가능)아산S/S 154kV 아산-합덕#1T/L GIS 보통점검","2024-06-10 09:00","2024-06-10 18:00","2024-06-10 09:00","2024-06-10 18:00","연속"]
[391,"대전세종충남","천안","아산온양#1 T/L","[5월 취소시]'24~25년 천안전력지사 가공송전 협력회사 총액공사","[즉시가압가능]154kV 아산-온양T/L 추락방지장치 및 점퍼지지애자 설치","2024-06-10 07:00","2024-06-14 18:00","취소","취소","매일"]
[392,"대전세종충남","천안","아산인주#1 T/L","아산, 인주S/S 154kV 아산인주#1T/L 보호배전반 대체","(즉시가압불가)아산, 인주S/S 154kV 아산인주#1T/L 보호배전반 대체","2024-06-15 09:00","2024-06-17 18:00","취소","취소","연속"]
[393,"대전세종충남","천안","아산온양#2 T/L","[5월 취소시]'24~25년 천안전력지사 가공송전 협력회사 총액공사","[즉시가압가능]154kV 아산-온양T/L 추락방지장치 및 점퍼지지애자 설치","2024-06-17 07:00","2024-06-21 18:00","취소","취소","매일"]
[394,"대전세종충남","천안","아산합덕#2 T/L","아산S/S 154kV 아산-합덕#2T/L GIS 보통점검","(즉시가압가능)아산S/S 154kV 아산-합덕#2T/L GIS 보통점검","2024-06-28 09:00","2024-06-28 18:00","2024-06-28 09:00","2024-06-28 18:00","연속"]
[395,"대전세종충남","천안","아산예산#2 T/L","아산, 예산S/S 154kV 아산예산#2T/L 보호배전반 대체","(즉시가압불가)아산, 예산S/S 154kV 아산예산#2T/L 보호배전반 대체","2024-06-24 09:00","2024-06-27 18:00","취소","취소","연속"]
[396,"대전세종충남","천안","아산온양#1 T/L","'24~25년 천안전력지사 가공송전 협력회사 총액공사","154kV 아산-예산#2T/L, 아산온양#1T/L 피뢰기설치 [병가철탑 아산-예산#2T/L 1~13호] 아산-온양#1T/L(상단), 아산-예산#2T/L(하단)","2024-06-24 07:00","2024-06-28 18:00","취소","취소","매일"]
[397,"대전세종충남","천안","아산인주#2 T/L","아산, 인주S/S 154kV 아산인주#2T/L 보호배전반 대체","(즉시가압불가)아산, 인주S/S 154kV 아산인주#2T/L 보호배전반 대체","2024-06-22 09:00","2024-06-24 18:00","취소","취소","연속"]
[398,"대전세종충남","천안","아산예산#1 T/L","아산, 예산S/S 154kV 아산예산#1T/L 보호배전반 대체","(즉시가압불가)아산, 예산S/S 154kV 아산예산#1T/L 보호배전반 대체","2024-06-17 09:00","2024-06-20 18:00","취소","취소","연속"]
[399,"대전세종충남","천안","아산예산#2 T/L","'24~25년 천안전력지사 가공송전 협력회사 총액공사","154kV 아산-예산#2T/L, 아산온양#1T/L 피뢰기설치 [병가철탑 아산-예산#2T/L 1~13호] 아산-온양#1T/L(상단), 아산-예산#2T/L(하단)","2024-06-24 07:00","2024-06-28 18:00","취소","취소","매일"]
[400,"대전세종충남","천안","아산인주#2 T/L","[5월취소시]154kV 아산-인주T/L 추락방지장치 설치공사","[즉시가압가능]154kV 아산-인주T/L No. 1 ~ 25 추락방지장치 설치","2024-06-15 07:00","2024-06-16 18:00","취소","취소","매일"]
[401,"대전세종충남","천안","아산인주#1 T/L","[5월취소시]154kV 아산-인주T/L 추락방지장치 설치공사","[즉시가압가능]154kV 아산-인주T/L No. 1 ~ 25 추락방지장치 설치","2024-06-08 07:00","2024-06-09 18:00","취소","취소","매일"]
[402,"대전세종충남","천안","장재천안#1 T/L","천안, 장재S/S 154kV 장재천안#1T/L 보호배전반 대체","(즉시가압불가)천안, 장재S/S 154kV 장재천안#1T/L 보호배전반 대체","2024-06-04 09:00","2024-06-07 18:00","취소","취소","연속"]
[403,"대전세종충남","천안","장재천안#2 T/L","천안, 장재S/S 154kV 장재천안#2T/L 보호배전반 대체","(즉시가압불가)천안, 장재S/S 154kV 장재천안#2T/L 보호배전반 대체","2024-06-11 09:00","2024-06-14 18:00","취소","취소","연속"]
[404,"대전세종충남","천안","천안전의#2 T/L","천안S/S 154kV 천안-전의#2T/L GIS 보통점검","(5월취소시)(즉시가압가능)천안S/S 154kV 천안-전의#2T/L GIS 보통점검","2024-06-14 09:00","2024-06-14 18:01","2024-06-14 09:00","2024-06-14 18:00","연속"]
[405,"대전세종충남","천안","신탕정탕정#2 T/L","탕정S/S 154kV 신탕정-탕정#2T/L CB 개폐타임측정","(즉시가압가능)탕정S/S 154kV 신탕정-탕정#2T/L CB 개폐타임측정","2024-06-13 09:00","2024-06-13 18:00","취소","취소","연속"]
[406,"대전세종충남","천안","신탕정탕정#1 T/L","탕정S/S 154kV 신탕정-탕정#1T/L CB 개폐타임측정","(즉시가압가능)탕정S/S 154kV 신탕정-탕정#1T/L CB 개폐타임측정","2024-06-12 09:00","2024-06-12 18:00","취소","취소","연속"]
[407,"대전세종충남","천안","풍세장재#1 T/L","풍세, 장재S/S 154kV 풍세장재#1T/L 보호반 성능개선","(즉시가압불가)풍세, 장재S/S 154kV 풍세장재#1T/L 보호반 성능개선","2024-06-25 09:00","2024-06-25 18:00","취소","취소","연속"]
[408,"대전세종충남","천안","풍세장재#2 T/L","풍세, 장재S/S 154kV 풍세장재#2T/L 보호반 성능개선","(즉시가압불가)풍세, 장재S/S 154kV 풍세장재#2T/L 보호반 성능개선","2024-06-26 09:00","2024-06-26 18:00","취소","취소","연속"]
[409,"대전세종충남","천안","온양풍세#2 T/L","[5월 취소시]'24~25년 천안전력지사 가공송전 협렵회사 총액공사","[즉시가압가능]154kV 온양-풍세T/L 추락방지장치 및 피뢰기 설치 [4회선병가]아산온양#2(상단), 온양풍세#2(하단) No.1~6","2024-06-17 07:00","2024-06-17 18:00","2024-06-17 07:00","2024-06-17 18:00","연속"]
[410,"대전세종충남","천안","온양풍세#1 T/L","[5월 취소시]'24~25년 천안전력지사 가공송전 협력회사 총액공사","[즉시가압가능]154kV 온양-풍세T/L 추락방지장치 및 피뢰기 설치 [4회선병가]아산온양#1(상단), 온양풍세#1(하단) No.1~6","2024-06-10 07:00","2024-06-10 18:00","2024-06-10 07:00","2024-06-10 18:00","연속"]
[411,"대전세종충남","청양","관창보령CC T/L","170kV GIS 정밀점검 공사(관창, 관복)5월취소시","170kV GIS 정밀점검 공사(관창, 관복) 5월취소시 - 한국초고압 - 즉시가압 불가","2024-06-24 09:00","2024-06-26 18:00","2024-06-24 09:00","2024-06-26 18:00","연속"]
[412,"대전세종충남","청양","관창보령TP T/L","154kV LA, PT GIS 내장화공사(관창-보령화력)","154kV LA, PT GIS 내장화공사(6.10~6.15) - 즉시가압 불가","2024-06-10 09:00","2024-06-15 18:00","2024-06-10 09:00","2024-06-15 18:00","연속"]
[413,"대전세종충남","청양","신서천옥산#2 T/L","170kV GIS 정밀점검 발주공사(옥서#2)","옥산S/S 옥산-서천#2 T/L 정밀점검 - 병행작업 피뢰기 총액공사 - 즉시가압 불가","2024-06-19 09:00","2024-06-21 18:00","취소","취소","연속"]
[414,"대전세종충남","청양","옥산장항#1 T/L","170kV GIS 정밀점검 공사(옥산, 옥장#1)5월취소시","170kV GIS 정밀점검 공사(옥산, 옥장#1) 5월취소시 - 한국초고압 - 즉시가압 불가","2024-06-11 09:00","2024-06-13 18:00","2024-06-11 09:00","2024-06-13 18:00","연속"]
[415,"대전세종충남","청양","옥산부여#2 T/L","170kV GIS 정밀점검 공사(옥산, 옥부#2)","170kV GIS 정밀점검 공사(옥산, 옥부#2) - 한국초고압 - 즉시가압 불가","2024-06-03 09:00","2024-06-05 18:00","2024-06-03 09:00","2024-06-05 18:00","연속"]
[416,"대전세종충남","청양","은하홍성#1 T/L","청양P/O 변전협력회사 총액공사(은홍#1 보호반)","154kV 은하-홍성#1T/L 보호반 대체공사 - 즉시가압 불가","2024-06-03 09:00","2024-06-05 18:00","2024-06-03 09:00","2024-06-05 18:00","연속"]
[417,"대전세종충남","청양","동군산장항#2 T/L","(5월취소시)청양P/O 변전협력 총액공사(동장#2)","장항S/S 동군산-장항#2 T/L GIS 보통점검 추가공사 - 5월 취소시 - 즉시가압 가능","2024-06-07 09:00","2024-06-07 18:00","취소","취소","연속"]
[418,"전북","군산","군공내초#1 T/L","154kV 군공-내초T/L OF케이블 절연유 체유작업","154kV 군공-내초T/L OF케이블 절연유 체유작업","2024-06-24 09:00","2024-06-26 18:00","2024-06-24 09:00","2024-06-26 18:00","연속"]
[419,"전북","군산","군공내초#2 T/L","154kV 군공-내초T/L OF케이블 절연유 체유작업","154kV 군공-내초T/L OF케이블 절연유 체유작업","2024-06-27 09:00","2024-06-29 18:00","2024-06-27 09:00","2024-06-29 18:00","연속"]
[420,"전북","군산","군산동군산#1 T/L","군산P/O 170kV GIS 정밀점검 공사","군산S/S 군산-동군산#1T/L GIS 정밀점검공사","2024-06-17 09:00","2024-06-18 18:00","2024-06-17 09:00","2024-06-18 18:00","연속"]
[421,"전북","군산","군산동군산#2 T/L","군산P/O 170kV GIS 정밀점검 공사","군산S/S 군산-동군산#2T/L GIS 정밀점검공사","2024-06-19 09:00","2024-06-20 18:00","2024-06-19 09:00","2024-06-20 18:00","연속"]
[422,"전북","군산","군산서군산#1 T/L","군산P/O 170kV GIS 정밀점검 공사","군산S/S 군산-서군산#1T/L GIS 정밀점검공사","2024-06-24 09:00","2024-06-25 18:00","2024-06-24 09:00","2024-06-25 18:00","연속"]
[423,"전북","군산","군산서군산#2 T/L","군산P/O 170kV GIS 정밀점검 공사","군산S/S 군산-서군산#2T/L GIS 정밀점검공사","2024-06-26 09:00","2024-06-27 18:00","2024-06-26 09:00","2024-06-27 18:00","연속"]
[424,"전북","군산","군산동군산#2 T/L","군산P/O 170kV GIS 정밀점검 공사(6333GIS 무부하 가압)","군산S/S #3M.Tr 2차 GIS 정밀점검","2024-06-27 16:00","2024-06-27 17:00","2024-06-27 16:00","2024-06-27 17:00","연속"]
[425,"전북","군산","군산S/S #67 BUS","군산P/O 170kV GIS 정밀점검 공사(6333GIS 무부하 가압)","군산S/S #3M.Tr 2차 GIS 정밀점검","2024-06-27 16:00","2024-06-27 17:00","2024-06-27 16:00","2024-06-27 17:00","연속"]
[426,"전북","군산","동군산장항#1 T/L","군산P/O 154kV 차단기 정밀점검 공사","동군산S/S 154kV 동군산-장항#1T/L 차단기 정밀점검","2024-06-10 09:00","2024-06-12 18:00","2024-06-10 09:00","2024-06-12 18:00","연속"]
[427,"전북","군산","동군산장항#2 T/L","동군산S/S SA혼용화 공사","동군산S/S 154kV 동군산-장항#2T/L SA혼용화 공사","2024-06-13 09:00","2024-06-14 18:00","2024-06-13 09:00","2024-06-14 18:00","연속"]
[428,"전북","군산","비응군장#2 T/L","154kV 비응S/S #4M.Tr 증설공사 (무부하가압 및 앵글측정)","154kV M.Tr x 1BANK 설치 154kV GIS x 1CCT 설치 23kV SIS x 10BAY(8CCT) 설치","2024-06-18 09:00","2024-06-20 18:00","2024-06-18 09:00","2024-06-20 18:00","연속"]
[429,"전북","김제","고창홍농 T/L","154kV 정주-고창 등 2개T/L 선종교체공사","- 공사구간 :154kV 정주-고창T/L No.92~95(병가구간) - 전력선 교체 : 44.076C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, 현수클램프 등]","2024-06-20 07:30","2024-06-22 17:00","취소","취소","매일"]
[430,"전북","김제","고창영광 T/L","154kV 정주-고창 등 2개T/L 선종교체공사","- 공사구간 :154kV 정주-고창T/L No.81~95 - 전력선 교체 : 44.076C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, 현수클램프 등]","2024-06-10 07:30","2024-06-23 17:00","취소","취소","연속"]
[431,"전북","김제","김제S/S #1 EM.Tr CB","김제ESS 방화구획재 시공","김제ESS 방화구획재 시공","2024-06-10 09:00","2024-06-12 18:00","2024-06-10 09:00","2024-06-12 18:00","연속"]
[432,"전북","김제","남전주임실#1 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","남전주-임실T/L 본선로 구성 양회선 휴전","2024-06-27 08:00","2024-07-05 17:00","2024-06-27 08:00","2024-07-05 17:00","연속"]
[433,"전북","김제","남전주임실#2 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","남전주-임실T/L 본선로 구성 양회선 휴전","2024-06-27 08:00","2024-07-05 17:00","2024-06-27 08:00","2024-07-05 17:00","연속"]
[434,"전북","김제","백산김제#2 T/L","백산S/S 154kV #4M.Tr 1차 차단기 정밀점검","백산S/S 154kV #4M.Tr 1차 차단기 정밀점검(6.12~13, 연속)","2024-06-21 15:00","2024-06-21 15:30","2024-06-21 15:00","2024-06-21 15:30","연속"]
[435,"전북","김제","백산김제#2 T/L","백산S/S 154kV #3M.Tr 1차 차단기 정밀점검","백산S/S 154kV #3M.Tr 1차 차단기 정밀점검(6.10~11, 연속)","2024-06-19 15:00","2024-06-19 15:30","2024-06-19 15:00","2024-06-19 15:30","연속"]
[436,"전북","김제","김제부안#2 T/L","부안S/S 154kV #4M.Tr 1차 차단기 정밀점검","부안S/S 154kV #4M.Tr 1차 차단기 정밀점검(6.13~14, 연속)","2024-06-14 15:00","2024-06-14 18:00","2024-06-14 15:00","2024-06-14 18:00","연속"]
[437,"전북","김제","김제부안#1 T/L","부안S/S 154kV #2M.Tr 1차 차단기,단로기 정밀점검","부안S/S 154kV #2M.Tr 1차 차단기,단로기 정밀점검(6.17~19, 연속)","2024-06-11 15:00","2024-06-12 18:00","2024-06-11 15:00","2024-06-12 18:00","매일"]
[438,"전북","김제","신김제S/S #1 EM.Tr CB","신김제ESS 방화구획재 시공","신김제ESS 방화구획재 시공","2024-06-13 09:00","2024-06-14 18:00","2024-06-13 09:00","2024-06-14 18:00","연속"]
[439,"전북","김제","정주고창#1 T/L","154kV 정주-고창 등 2개T/L 선종교체공사","- 공사구간 : No.1~95 - 전력선 교체 : 44.076C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, 현수클램프 등]","2024-06-10 07:30","2024-07-26 18:00","2024-06-10 07:30","2024-07-26 18:00","연속"]
[440,"전북","김제","정공정주#1 T/L","154kV 정주-정공T/L 세니온 보호계전기 성능개선","(주) 세니온 보호계전기 성능개선","2024-06-27 15:00","2024-06-27 18:00","취소","취소","연속"]
[441,"전북","김제","정공정주#2 T/L","154kV 정주-정공T/L 세니온 보호계전기 성능개선","(주) 세니온 보호계전기 성능개선","2024-06-28 15:00","2024-06-28 18:00","취소","취소","연속"]
[442,"전북","직할","동전주북전주#2 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사","154kV 동전주-북전주T/L No.1~53 수평 추락방지장치 및 조류착지방지장치 설치","2024-06-03 09:00","2024-06-05 18:00","취소","취소","매일"]
[443,"전북","직할","금산무주#1 T/L","세니온 보호계전기 성능개선","세니온제 보호계전기 성능개선 - 메인보드교체 - 펌웨어 업데이트","2024-06-03 15:00","2024-06-03 22:00","2024-06-03 15:00","2024-06-03 22:00","연속"]
[444,"전북","직할","금산무주#2 T/L","세니온 보호계전기 성능개선","세니온제 보호계전기 성능개선 - 메인보드교체 - 펌웨어 업데이트","2024-06-05 15:00","2024-06-05 20:00","2024-06-05 15:00","2024-06-05 20:00","연속"]
[445,"전북","직할","무주진안 T/L","세니온 보호계전기 성능개선","세니온제 보호계전기 성능개선 - 펌웨어 업데이트 - 양단 변전소 작업","2024-06-04 15:00","2024-06-04 22:00","2024-06-04 15:00","2024-06-04 22:00","연속"]
[446,"전북","직할","왕궁봉동#2 T/L","24-25 전북직할 변전협력회사 공사","154kV GIS 보통점검","2024-06-12 09:00","2024-06-12 18:00","2024-06-12 09:00","2024-06-12 18:00","연속"]
[447,"전북","직할","왕궁봉동#1 T/L","24-25 전북직할 변전협력회사 공사","154kV GIS 보통점검","2024-06-11 09:00","2024-06-11 18:00","2024-06-11 09:00","2024-06-11 18:00","연속"]
[448,"전북","직할","북전주진안 T/L","세니온 보호계전기 성능개선","세니온제 보호계전기 성능개선 - 펌웨어 업데이트 - 양단 변전소 작업","2024-06-13 15:00","2024-06-13 20:00","2024-06-13 15:00","2024-06-13 20:00","연속"]
[449,"전북","직할","신김제전주#1 T/L","24-25 전북직할 변전협력회사 공사","154kV GIS 보통점검","2024-06-17 09:00","2024-06-17 18:00","2024-06-17 09:00","2024-06-17 18:00","연속"]
[450,"전북","직할","진안장수#1 T/L","345kV 신옥천-신남원 등 3개T/L 수평 추락방지시설 설치공사","154kV 진안-장수T/L No.1~49 수평 추락방지장치 및 조류착지방지장치 설치","2024-06-17 07:00","2024-06-21 17:00","2024-06-17 07:00","2024-06-21 17:00","매일"]
[451,"전북","직할","진안장수#2 T/L","345kV 신옥천-신남원 등 3개T/L 수평 추락방지시설 설치공사","154kV 진안-장수T/L No.1~49 수평 추락방지장치 및 조류착지방지장치 설치","2024-06-24 07:00","2024-06-28 17:00","2024-06-24 07:00","2024-06-28 17:00","매일"]
[452,"전북","군산","군산C/C #1 M.Tr CB"," 군산복합 6133 차단기 파일럿 밸브 교체"," 군산복합 6133 차단기 파일럿 밸브 교체","2024-06-11 09:00","2024-06-12 18:00","2024-06-11 09:00","2024-06-12 18:00","연속"]
[453,"전북","군산","군산S/S SEC CB 61620"," 군산P/O 154kV이상 차단기 점검공사"," 군산P/O 154kV이상 차단기 점검공사","2024-06-05 09:00","2024-06-05 13:00","2024-06-05 09:00","2024-06-05 13:00","연속"]
[454,"전북","군산","군산S/S SEC CB 66670"," 군산P/O 154kV이상 차단기 점검공사"," 군산P/O 154kV이상 차단기 점검공사","2024-06-05 13:00","2024-06-05 18:00","2024-06-05 13:00","2024-06-05 18:00","연속"]
[455,"전북","군산","군산S/S CB 6300"," 군산P/O 154kV이상 차단기 점검공사"," 군산P/O 154kV이상 차단기 점검공사","2024-06-07 09:00","2024-06-07 13:00","2024-06-07 09:00","2024-06-07 13:00","연속"]
[456,"전북","군산","군산영등#2 T/L"," 군산S/S 170kV GIS대체공사(6차)"," 군산S/S 170kV GIS대체공사(6차)","2024-06-10 08:00","2024-06-24 18:00","2024-06-10 08:00","2024-06-25 18:00","연속"]
[457,"전북","군산","군산S/S #61 BUS"," 군산S/S 170kV GIS대체공사(6차)"," 군산S/S 170kV GIS대체공사(6차)","2024-06-12 18:00","2024-06-17 18:00","2024-06-12 18:00","2024-06-18 18:00","연속"]
[458,"전북","군산","군산S/S #66 BUS"," 군산S/S 170kV GIS대체공사(6차)"," 군산S/S 170kV GIS대체공사(6차)","2024-06-17 18:00","2024-06-24 17:00","2024-06-18 18:00","2024-06-25 17:00","연속"]
[459,"전북","군산","군산S/S #61 BUS"," 군산S/S 170kV GIS대체공사(6차)"," 군산S/S 170kV GIS대체공사(6차)","2024-06-24 17:00","2024-06-24 18:00","2024-06-25 17:00","2024-06-25 18:00","연속"]
[460,"광주전남","강진","나주엄다#2 T/L","세니온 보호계전기 일제 성능개선 시행(나주,엄다)","세니온 보호계전기 일제 성능개선 시행(나주,엄다) - 나주-엄다 #1,2T/L - IED반 MAX 488교체, IED반 F/W업데이트","2024-06-05 14:00","2024-06-05 18:00","2024-06-05 14:00","2024-06-05 18:00","연속"]
[461,"광주전남","강진","보성벌교 T/L","2024년 가공송전 순시점검 위탁공사","보성벌교T/L 정밀점검","2024-06-18 08:00","2024-06-28 18:00","취소","취소","매일"]
[462,"광주전남","강진","보성S/S 고흥태양광T/L CB","보성S/S 효성제 170kV GIS 개선","- 캠 및 베어링 교체","2024-06-17 10:00","2024-06-17 18:00","2024-06-17 10:00","2024-06-17 18:00","연속"]
[463,"광주전남","강진","화원진도#2 T/L","'22~23년 철탑추락방지장치 설치공사","화원-진도#2T/L 수평추락방지장치 설치 40~78호 39기","2024-06-18 07:00","2024-06-21 18:00","2024-06-03 07:00","2024-06-07 18:00","매일"]
[464,"광주전남","강진","화원진도#2 T/L","2024~2025년 강진전력지사 변전협력회사 공사","가. 진도S/S 효성제 #5M.Tr 1차 GIS 주접점 이탈 관련 차단부 교체 관련 무부하 가압","2024-06-12 09:00","2024-06-13 18:00","2024-06-12 09:00","2024-06-13 18:00","연속"]
[465,"광주전남","강진","진도진도CS#1 T/L","2024년~2025년 강진전력지사 변전협력회사 공사","- 유면게이지 누유 관련 조치","2024-06-11 10:00","2024-06-11 18:00","2024-06-11 10:00","2024-06-11 18:00","연속"]
[466,"광주전남","강진","진도진도CS#2 T/L","2024년~2025년 강진전력지사 변전협력회사 공사","- 유압시스템 벤팅용 하우징 누유 관련 조치","2024-06-12 10:00","2024-06-12 18:00","2024-06-12 10:00","2024-06-12 18:00","연속"]
[467,"광주전남","광주","계림남광주 T/L","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2024-06-08 09:00","2024-07-10 18:00","취소","취소","연속"]
[468,"광주전남","광주","계림S/S CB 6100","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2024-06-08 09:00","2024-07-10 18:00","취소","취소","연속"]
[469,"광주전남","광주","계림충장#2 T/L","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2024-06-08 09:00","2024-07-10 18:00","취소","취소","연속"]
[470,"광주전남","광주","계림승주#1 T/L","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","-BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2T/L #60BUS 신설분 무부하 가압","2024-06-18 13:00","2024-06-19 13:00","2024-06-18 13:00","2024-06-19 13:00","연속"]
[471,"광주전남","광주","담양일곡#1 T/L","대한전선製 EBG 가스채취밸브 보강공사","송운(송전)-321(2021.03.30) 지중송전선로 EBG 고장원인 조사결과 및 재발방지대책 알림 관련으로 대한전선제 EBG 보강 시행","2024-06-05 09:00","2024-06-07 18:00","2024-06-05 09:00","2024-06-07 18:00","연속"]
[472,"광주전남","광주","담양일곡#2 T/L","대한전선製 EBG 가스채취밸브 보강공사","송운(송전)-321(2021.03.30) 지중송전선로 EBG 고장원인 조사결과 및 재발방지대책 알림 관련으로 대한전선제 EBG 보강 시행","2024-06-10 09:00","2024-06-11 18:00","2024-06-10 09:00","2024-06-11 18:00","연속"]
[473,"광주전남","광주","신광주계림#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","신광주, 계림S/S 신광주-계림#2T/L PNL 대체","2024-06-17 09:00","2024-06-21 18:00","취소","취소","연속"]
[474,"광주전남","광주","일곡비아#1 T/L","24년 광주전력지사 170kV 이상 GIS 보통점검","- 170kV GIS 보통점검","2024-06-05 08:00","2024-06-05 18:00","2024-06-05 08:00","2024-06-05 18:00","연속"]
[475,"광주전남","목포","목포북항#1 T/L","대한전선製 EBG 가스채취밸브 보강공사","송운(송전)-321(2021.03.30) 지중송전선로 EBG 고장원인 조사결과 및 재발방지대책 알림 관련으로 대한전선제 EBG 보강 시행","2024-06-19 09:00","2024-06-20 18:00","2024-06-19 09:00","2024-06-20 18:00","연속"]
[476,"광주전남","목포","목포북항#2 T/L","대한전선製 EBG 가스채취밸브 보강공사","송운(송전)-321(2021.03.30) 지중송전선로 EBG 고장원인 조사결과 및 재발방지대책 알림 관련으로 대한전선제 EBG 보강 시행","2024-06-24 09:00","2024-06-25 18:00","2024-06-24 09:00","2024-06-25 18:00","연속"]
[477,"광주전남","목포","나주엄다#2 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체공사","모선 절체용(BUS-TIE 교체로 인한 양DS투입 불가)","2024-06-14 14:00","2024-06-14 14:30","취소","취소","연속"]
[478,"광주전남","목포","엄다목포#2 T/L","대한전선製 EBG 가스채취밸브 보강공사","송운(송전)-321(2021.03.30) 지중송전선로 EBG 고장원인 조사결과 및 재발방지대책 알림 관련으로 대한전선제 EBG 보강 시행","2024-06-17 09:00","2024-06-18 18:00","2024-06-17 09:00","2024-06-18 18:00","연속"]
[479,"광주전남","목포","엄다목포#1 T/L","대한전선製 EBG 가스채취밸브 보강공사","송운(송전)-321(2021.03.30) 지중송전선로 EBG 고장원인 조사결과 및 재발방지대책 알림 관련으로 대한전선제 EBG 보강 시행","2024-06-12 09:00","2024-06-13 18:00","2024-06-12 09:00","2024-06-13 18:00","연속"]
[480,"광주전남","목포","나주엄다#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체공사","엄다-목포#2T/L, BUS-TIE #1BUS측 무부하가압용","2024-06-13 14:00","2024-06-14 14:00","취소","취소","연속"]
[481,"광주전남","목포","엄다목포#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체공사","모선 절체용(BUS-TIE 교체로 인한 양DS투입 불가)","2024-06-14 14:00","2024-06-14 14:30","취소","취소","연속"]
[482,"광주전남","목포","엄다무안햇빛#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체공사","모선 절체용(BUS-TIE 교체로 인한 양DS투입 불가)","2024-06-14 14:00","2024-06-14 14:30","취소","취소","연속"]
[483,"광주전남","목포","엄다S/S #2 BUS","엄다S/S 154kV 이하 장기사용 GIS 교체공사","엄다-목포#2T/L, BUS-TIE #2BUS, #2DS측 설치","2024-06-14 14:00","2024-07-01 10:00","취소","취소","연속"]
[484,"광주전남","목포","엄다무안햇빛#2 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체공사","모선 절체용(BUS-TIE 교체로 인한 양DS투입 불가)","2024-06-14 14:00","2024-06-14 14:30","취소","취소","연속"]
[485,"광주전남","목포","엄다목포#2 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","엄다목포#2T/L GIS 교체","2024-06-17 09:00","2024-07-22 18:00","2024-06-17 09:00","2024-07-22 18:00","연속"]
[486,"광주전남","목포","엄다S/S CB 6100","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","154kV BUS-TIE GIS 교체","2024-06-17 09:00","2024-07-22 18:00","2024-06-17 09:00","2024-07-22 18:00","연속"]
[487,"광주전남","목포","엄다무안햇빛#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","BUS-TIE 교체로 인한 #2BUS 모선절체용","2024-06-19 14:00","2024-06-19 14:30","2024-06-19 14:00","2024-06-19 14:30","연속"]
[488,"광주전남","목포","엄다목포#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","BUS-TIE 교체로 인한 #2BUS 모선절체용","2024-06-19 14:00","2024-06-19 14:30","2024-06-19 14:00","2024-06-19 14:30","연속"]
[489,"광주전남","목포","엄다무안햇빛#2 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","BUS-TIE 교체로 인한 #2BUS 모선절체용","2024-06-19 14:00","2024-06-19 14:30","2024-06-19 14:00","2024-06-19 14:30","연속"]
[490,"광주전남","목포","나주엄다#2 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","BUS-TIE 교체로 인한 #2BUS 모선절체용","2024-06-19 14:00","2024-06-19 14:30","2024-06-19 14:00","2024-06-19 14:30","연속"]
[491,"광주전남","목포","엄다S/S #1 BUS","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","엄다-목포#2T/L, 154kV BUS-TIE #1DS, #1BUS 교체","2024-06-19 14:00","2024-07-03 14:00","2024-06-19 14:00","2024-07-03 14:00","연속"]
[492,"광주전남","목포","나주엄다#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","BUS-TIE 교체로 인한 #2BUS 모선절체용","2024-06-19 14:00","2024-06-19 14:30","2024-06-19 14:00","2024-06-19 14:30","연속"]
[493,"광주전남","목포","나주엄다#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체공사","모선 절체용(BUS-TIE 교체로 인한 양DS투입 불가)","2024-06-14 14:00","2024-06-14 14:30","취소","취소","연속"]
[494,"광주전남","순천","장흥벌교 T/L","피뢰기 설치공사","장흥-벌교t/l 피뢰기 설치 (31기)","2024-06-10 09:00","2024-06-14 18:00","취소","취소","매일"]
[495,"광주전남","순천","보성벌교 T/L","154kV 보성-벌교T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No.123~144호","2024-06-03 07:00","2024-06-05 18:00","취소","취소","매일"]
[496,"광주전남","순천","장흥벌교 T/L","'22~23년 철탑 추락방지장치 설치공사","철탑 추락방지장치(수평) 설치 (1,7~64,64,1,65~101,103~105,107~121호, 115기)","2024-06-03 06:00","2024-06-17 18:00","2024-06-17 07:00","2024-06-28 18:00","매일"]
[497,"광주전남","순천","승주서순천 T/L","2024년 지중송전협력회사 총액공사","154kV 승주-서순천 T/L EBG~EBA 간 병행지선 설치작업 안전확보 차","2024-06-19 15:30","2024-06-19 17:00","취소","취소","연속"]
[498,"광주전남","순천","서순천주암HP T/L","2024년 지중송전협력회사 총액공사","154kV 서순천-주암HP T/L EBG~EBA 간 병행지선 설치작업 안전확보 차","2024-06-19 13:00","2024-06-19 15:30","취소","취소","연속"]
[499,"광주전남","순천","서순천주암HP T/L","금구류 교체공사","소라-서순천 t/l 금구류 교체공사(병가철탑 휴전)","2024-06-28 08:00","2024-06-28 18:00","2024-06-28 08:00","2024-06-28 18:00","연속"]
[500,"광주전남","순천","여수소라#1 T/L","24년 순천전력지사 362,170kV GIS 정밀,보통점검공사","소라S/S 여수-소라#1T/L GIS 보통점검","2024-06-04 09:00","2024-06-04 18:00","2024-06-03 09:00","2024-06-05 18:00","연속"]
[501,"광주전남","순천","여수소라#2 T/L","24년 순천전력지사 362,170kV GIS 정밀,보통점검공사","소라S/S 여수-소라#2T/L GIS 보통점검","2024-06-05 09:00","2024-06-05 18:00","2024-06-10 09:00","2024-06-12 18:00","연속"]
[502,"광주전남","순천","소라서순천#1 T/L","24년 순천전력지사 362,170kV GIS 정밀,보통점검공사","소라S/S 소라-서순천#1T/L GIS 보통점검","2024-06-11 09:00","2024-06-11 18:00","2024-06-11 09:00","2024-06-11 18:00","연속"]
[503,"광주전남","순천","소라서순천#2 T/L","금구류 교체공사","소라-서순천 t/l 금구류 교체공사","2024-06-28 09:00","2024-06-28 18:00","2024-06-28 09:00","2024-06-28 18:00","연속"]
[504,"광주전남","순천","순천승주#1 T/L","154kV 순천-승주T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No.1호","2024-06-07 07:00","2024-06-07 13:00","2024-06-07 07:00","2024-06-07 13:00","연속"]
[505,"광주전남","순천","순천승주#2 T/L","154kV 순천-승주T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No.1호","2024-06-07 13:00","2024-06-07 18:00","2024-06-07 13:00","2024-06-07 18:00","연속"]
[506,"광주전남","순천","승주서순천 T/L","154kV 승주-서순천T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No.1~96호","2024-06-19 07:00","2024-06-27 18:00","2024-06-19 07:00","2024-06-27 18:00","매일"]
[507,"광주전남","순천","용성여수산단#2 T/L","24-25년 순천전력지사 변전총액공사","여수산단 용성여수산단#2 T/L #2DS 가스누기조치","2024-06-10 09:00","2024-06-11 18:00","취소","취소","연속"]
[508,"광주전남","순천","여천여수산단#1 T/L","24년 순천전력지사 362,170kV GIS 정밀,보통점검공사","여수산단S/Y 여천-여수산단#1T/L GIS 보통점검","2024-06-21 09:00","2024-06-21 18:00","2024-06-21 09:00","2024-06-21 18:00","연속"]
[509,"광주전남","순천","용성여수산단#1 T/L","24년 순천전력지사 362,170kV GIS 정밀,보통점검공사","여수산단,용성S/S 용성-여수산단#1T/L GIS 보통점검","2024-06-17 09:00","2024-06-18 18:00","2024-06-17 09:00","2024-06-18 18:00","매일"]
[510,"광주전남","순천","여수T/P #65 BUS","GS 칼텍스 여수#2T/L #2DS 가스누기해소 공사","#2DS 가스누기해소 공사","2024-06-13 09:00","2024-06-14 18:00","취소","취소","연속"]
[511,"광주전남","순천","여수T/P SEC CB 65660","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-06-21 15:00","2024-06-21 15:20","취소","취소","연속"]
[512,"광주전남","순천","여수T/P CB 6100","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-06-21 15:40","2024-06-21 16:00","취소","취소","연속"]
[513,"광주전남","순천","여수T/P SEC CB 65660","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-06-28 15:00","2024-06-28 15:20","취소","취소","연속"]
[514,"광주전남","순천","여수T/P SEC CB 60610","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-06-28 15:20","2024-06-28 15:40","취소","취소","연속"]
[515,"광주전남","순천","여수T/P CB 6200","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-06-28 15:40","2024-06-28 16:00","취소","취소","연속"]
[516,"광주전남","순천","여수T/P SEC CB 60610","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-06-21 15:20","2024-06-21 15:40","취소","취소","연속"]
[517,"광주전남","순천","여천S/S SEC CB 60610","24-25년 순천전력지사 변전정비 총액공사","모선보호반 피더증설","2024-06-17 09:00","2024-06-18 18:00","2024-06-17 09:00","2024-06-18 18:00","연속"]
[518,"광주전남","순천","여천S/S CB 6100","24-25년 순천전력지사 변전정비 총액공사","모선보호반 피더증설","2024-06-17 09:00","2024-06-18 18:00","2024-06-17 09:00","2024-06-18 18:00","연속"]
[519,"광주전남","순천","여천S/S SEC CB 65660","24-25년 순천전력지사 변전정비 총액공사","모선보호반 피더증설","2024-06-17 09:00","2024-06-18 18:00","2024-06-17 09:00","2024-06-18 18:00","연속"]
[520,"광주전남","순천","여수TP용성#1 T/L","용성S/S 여수TP-용성#1T/L GIS 불량 유압력계 교체","GIS 불량 유압력계 교체","2024-06-03 09:00","2024-06-04 18:00","취소","취소","연속"]
[521,"광주전남","순천","율촌S/S #60 BUS","24-25년 순천전력지사 변전정비 총액공사","#1DS 가스누기 조치","2024-06-17 09:00","2024-06-24 18:00","2024-06-17 09:00","2024-06-24 18:00","연속"]
[522,"광주전남","순천","율촌민자#2 T/L","154kV 율촌민자T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No.1~9호","2024-06-11 07:00","2024-06-11 18:00","취소","취소","연속"]
[523,"광주전남","순천","율촌민자#1 T/L","154kV 율촌민자T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No.1~9호","2024-06-10 07:00","2024-06-10 18:00","취소","취소","연속"]
[524,"광주전남","순천","율촌민자#3 T/L","24-25 순천전력지사 변전정비 총액공사","24-25 순천전력지사 변전정비 총액공사 -#1DS 가스누기 조치","2024-06-19 09:00","2024-06-24 18:00","2024-06-19 09:00","2024-06-24 18:00","연속"]
[525,"광주전남","순천","율촌여수산단#2 T/L","24-25 순천전력지사 변전정비 총액공사","24-25 순천전력지사 변전정비 총액공사 -#1DS 가스누기 조치","2024-06-19 09:00","2024-06-24 18:00","취소","취소","연속"]
[526,"광주전남","순천","광양태금#1 T/L","24년 순천전력지사 362,170kV GIS 정밀,보통점검공사","태금S/S 광양-태금#1T/L GIS 보통점검","2024-06-07 09:00","2024-06-07 18:00","2024-06-07 09:00","2024-06-07 18:00","연속"]
[527,"광주전남","순천","여천호남TP#2 T/L","24년 순천전력지사 362,170kV GIS 정밀,보통점검공사","호남T/P 여천-호남TP#2T/L GIS 보통점검","2024-06-14 09:00","2024-06-14 18:00","2024-06-14 09:00","2024-06-14 18:00","연속"]
[528,"광주전남","순천","여천호남TP#1 T/L","24년 순천전력지사 362,170kV GIS 정밀,보통점검공사","호남T/P 여천-호남TP#1T/L GIS 보통점검","2024-06-12 09:00","2024-06-12 18:00","2024-06-12 09:00","2024-06-12 18:00","연속"]
[529,"광주전남","직할","나주금천#2 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 수직, 수평추락방지장치 설치 및 고정형 클램프 교체 작업구간 : 나주-금천 1~7, 110, 110-1호","2024-06-03 07:00","2024-06-05 18:00","2024-06-03 07:00","2024-06-05 18:00","매일"]
[530,"광주전남","직할","나주금천#1 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 수직, 수평추락방지장치 설치 및 고정형 클램프 교체 작업구간 : 나주-금천 1~7, 110, 110-1호","2024-06-17 07:00","2024-06-19 18:00","2024-06-17 07:00","2024-06-19 18:00","매일"]
[531,"광주전남","직할","남광주금천#1 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 수직, 수평추락방지장치 설치 및 고정형 클램프 교체 작업구간 : 신화순-매월 7~82호","2024-06-03 07:00","2024-06-14 18:00","2024-06-03 07:00","2024-06-14 18:00","매일"]
[532,"광주전남","직할","남광주금천#2 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 수직, 수평추락방지장치 설치 및 고정형 클램프 교체 작업구간 : 신화순-매월 7~82호","2024-06-17 07:00","2024-06-27 18:00","2024-06-17 07:00","2024-06-27 18:00","매일"]
[533,"광주전남","직할","농성화정#2 T/L","대한전선製 EBG 가스채취밸브 보강공사","송운(송전)-321(2021.03.30) 지중송전선로 EBG 고장원인 조사결과 및 재발방지대책 알림 관련으로 대한전선제 EBG 보강 시행","2024-06-03 09:00","2024-06-04 18:00","2024-06-03 09:00","2024-06-04 18:00","연속"]
[534,"광주전남","직할","비아하남#2 T/L","'24년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 보통점검","2024-06-07 09:00","2024-06-07 18:00","취소","취소","연속"]
[535,"광주전남","직할","수완흑석#1 T/L","'24년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 보통,정밀점검","2024-06-10 09:00","2024-06-13 18:00","2024-06-10 09:00","2024-06-13 18:00","연속"]
[536,"광주전남","직할","비아하남#1 T/L","'24년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 보통,정밀점검","2024-06-03 09:00","2024-06-05 18:00","2024-06-03 09:00","2024-06-05 18:00","연속"]
[537,"광주전남","직할","수완흑석#2 T/L","'24년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 보통점검","2024-06-14 09:00","2024-06-14 18:00","2024-06-14 09:00","2024-06-14 18:00","연속"]
[538,"광주전남","직할","하남흑석#2 T/L","'24년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검","2024-06-19 14:00","2024-06-21 18:00","2024-06-19 14:00","2024-06-21 18:00","연속"]
[539,"광주전남","직할","하남흑석#1 T/L","'24년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검","2024-06-17 09:00","2024-06-19 14:00","2024-06-17 09:00","2024-06-19 14:00","연속"]
[540,"대구","경산","경산S/S #1 EM.Tr CB","경산ESS 방화구획재 설치공사","경산ESS 방화구획재 설치공사","2024-06-10 09:00","2024-06-14 18:00","2024-06-10 09:00","2024-06-14 18:00","연속"]
[541,"대구","경산","대구범물#2 T/L","고속철도대구#2T/L 고장복구관련 무부하 가압용","고속철도대구#2T/L 고장복구관련 무부하 가압용 선로","2024-06-27 18:00","2024-06-28 18:00","2024-06-27 18:00","2024-06-28 18:00","연속"]
[542,"대구","경산","시지효목#2 T/L","24~25년 경산P/O 변전협력회사 총액공사","- PD 발생관련 GIS 점검","2024-06-19 09:30","2024-06-20 18:00","2024-06-19 09:30","2024-06-20 18:00","연속"]
[543,"대구","경산","영천S/S #1 EM.Tr CB","PD 발생관련 23kV GIS 내부점검","PD 발생관련 23kV GIS 내부점검","2024-06-17 09:00","2024-06-20 18:00","2024-06-17 09:00","2024-06-20 18:00","연속"]
[544,"대구","경산","영천S/S #2 EM.Tr CB","PD 발생관련 23kV GIS 내부점검","PD 발생관련 23kV GIS 내부점검","2024-06-24 09:00","2024-06-27 18:00","2024-06-24 09:00","2024-06-27 18:00","연속"]
[545,"대구","경산","청도부북#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 대구-청도T/L 수평 추락방지장치 설치공사(154kV 청도-부북T/L 병가선로) (안전확보)","2024-06-17 07:00","2024-06-18 18:00","2024-06-17 07:00","2024-06-18 18:00","연속"]
[546,"대구","경산","청도부북#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 대구-청도T/L 수평 추락방지장치 설치공사(154kV 청도-부북T/L 병가선로) (안전확보)","2024-06-10 07:00","2024-06-11 18:00","2024-06-10 07:00","2024-06-11 18:00","연속"]
[547,"대구","달성","강창성서#2 T/L","차단기 동작특성시험(강창,성서SS)","차단기 동작특성시험(강창,성서SS)","2024-06-25 09:00","2024-06-25 18:00","2024-06-25 09:00","2024-06-25 18:00","연속"]
[548,"대구","달성","다사달서 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 왜관-다사T/L 수평 추락방지장치 설치공사(다사-달서 병가선로)(안전확보)","2024-06-26 07:00","2024-06-27 18:00","2024-06-26 07:00","2024-06-27 18:00","연속"]
[549,"대구","달성","대구범물#2 T/L","2024~25년 대구직할 가공송전 협력회사 공사","154kV 대구-범물T/L 수평 추락방지장치 설치공사","2024-06-20 07:30","2024-06-27 18:00","2024-06-20 07:30","2024-06-27 18:00","연속"]
[550,"대구","달성","대구범물#1 T/L","2024~25년 대구직할 가공송전 협력회사 공사","154kV 대구-범물T/L 수평 추락방지장치 설치공사","2024-06-12 07:30","2024-06-19 18:00","2024-06-12 07:30","2024-06-19 18:00","연속"]
[551,"대구","달성","현풍유가#2 T/L","[TEST]현풍S/S 6233GIS 정밀점검 무부하","[TEST]현풍S/S 6233GIS 정밀점검 무부하","2024-06-20 17:00","2024-06-20 18:00","2024-06-20 17:00","2024-06-20 18:00","연속"]
[552,"대구","직할","남대구동인#1 T/L","남대구S/S 154kV GIS 교체 및 증설공사(TEST선로)","○ #2BUS 무부하가압","2024-06-20 15:30","2024-06-20 16:00","2024-06-20 15:30","2024-06-20 16:00","연속"]
[553,"대구","직할","남대구동인#1 T/L","남대구S/S 154kV GIS 교체 및 증설공사(TEST선로)","○ #2BUS 무부하가압","2024-06-19 14:00","2024-06-20 14:00","2024-06-19 14:00","2024-06-20 14:00","연속"]
[554,"대구","직할","남대구S/S #2 BUS","남대구S/S 154kV GIS 교체 및 증설공사","○ 170kV GIS M.Tr 1차 및 T/L Bay 철거/설치 ○ 제어(광)케이블 포설 및 결선","2024-06-10 09:00","2024-06-20 14:00","2024-06-10 09:00","2024-06-20 14:00","연속"]
[555,"대구","직할","범물남대구#1 T/L","남대구S/S 154kV GIS 교체 및 증설공사(TEST선로)","○ #1BUS 무부하가압","2024-06-08 16:00","2024-06-10 09:00","2024-06-08 16:00","2024-06-10 09:00","연속"]
[556,"대구","직할","남대구S/S #1 BUS","남대구S/S 154kV GIS 교체 및 증설공사","○ 170kV GIS M.Tr 1차 및 T/L Bay 철거/설치 ○ 제어(광)케이블 포설 및 결선","2024-06-01 14:00","2024-06-10 09:00","2024-06-01 14:00","2024-06-10 09:00","연속"]
[557,"대구","직할","범물남대구#1 T/L","남대구S/S 154kV GIS 교체 및 증설공사(TEST선로)","○ #2BUS 무부하가압","2024-06-01 13:30","2024-06-01 14:00","2024-06-01 13:30","2024-06-01 14:00","연속"]
[558,"대구","칠곡","농소김천#2 T/L","김천SA 농소-김천SA#2T/L 6A7 GIS 하자점검","김천SA 농소-김천SA#2T/L 6A7 GIS 하자점검","2024-06-12 09:30","2024-06-12 14:00","2024-06-12 09:30","2024-06-12 14:00","연속"]
[559,"대구","칠곡","김천금릉#2 T/L","김천S/S 김천-금릉#2T/L 677 GIS 조작시험","김천S/S 김천-금릉#2T/L 677 GIS 조작시험","2024-06-14 14:00","2024-06-14 18:00","2024-06-14 14:00","2024-06-14 18:00","연속"]
[560,"대구","칠곡","농소김천#1 T/L","김천S/S LA B상 교체, LA/PT 보통점검","김천S/S LA B상 교체, LA/PT 보통점검","2024-06-05 09:30","2024-06-05 18:00","2024-06-05 09:30","2024-06-05 18:00","매일"]
[561,"대구","포항","건천천북#2 T/L","154kV 건천-천북T/L 지장송전선로 이설공사","철탑 2기 설치, 2기 철거 전선교체 3.355km","2024-06-10 07:00","2024-06-24 18:00","2024-06-10 07:00","2024-06-24 18:00","연속"]
[562,"대구","포항","건천천북#1 T/L","154kV 건천-천북T/L 지장송전선로 이설공사","철탑 2기 설치, 2기 철거 전선교체 3.355km","2024-06-10 07:00","2024-06-24 18:00","2024-06-10 07:00","2024-06-24 18:00","연속"]
[563,"경북","구미","청리상주#1 T/L","154kV 상주S/S 인출선로 일부구간 지중화공사","○ 목적 : 조류착지방지장치 설치 및 철탑도장","2024-06-03 08:00","2024-06-03 18:00","2024-06-03 08:00","2024-06-03 17:00","연속"]
[564,"경북","구미","청리상주#2 T/L","154kV 상주S/S 인출선로 일부구간 지중화공사","○ 목적 : 조류착지방지장치 설치 및 철탑도장","2024-06-03 08:00","2024-06-03 18:00","2024-06-03 08:00","2024-06-03 17:00","연속"]
[565,"경북","영주","점촌문경 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2024-06-19 14:00","2024-06-21 18:00","2024-06-19 14:00","2024-06-21 18:00","연속"]
[566,"경북","영주","문경단양 T/L","2024-25년 영주전력지사 변전협력회사 공사","보호반 대체","2024-06-22 09:00","2024-06-23 18:00","2024-06-22 09:00","2024-06-23 18:00","연속"]
[567,"경북","영주","봉화울진 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2024-06-05 14:00","2024-06-07 18:00","2024-06-05 14:00","2024-06-07 18:00","연속"]
[568,"경북","영주","봉화현종산풍력 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2024-06-03 09:00","2024-06-05 14:00","2024-06-03 09:00","2024-06-05 14:00","연속"]
[569,"경북","영주","영주S/S #1 EM.Tr CB","영주S/S ESS 화재확산방지재 보강공사","영주S/S ESS 화재확산방지재 보강공사(BAT, EP.Tr 2차측 각 14개소씩)","2024-06-17 09:00","2024-06-20 18:00","2024-06-17 09:00","2024-06-20 18:00","연속"]
[570,"경북","영주","동상주점촌#1 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2024-06-03 09:00","2024-06-05 14:00","취소","취소","연속"]
[571,"경북","영주","동상주점촌#2 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2024-06-05 14:00","2024-06-07 18:00","취소","취소","연속"]
[572,"경북","영주","예천점촌#1 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2024-06-10 09:00","2024-06-12 14:00","취소","취소","연속"]
[573,"경북","영주","예천점촌#2 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2024-06-12 14:00","2024-06-14 18:00","취소","취소","연속"]
[574,"경북","영주","점촌문경 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2024-06-17 09:00","2024-06-19 14:00","2024-06-17 09:00","2024-06-19 14:00","연속"]
[575,"경북","영주","점촌단양 T/L","2024-25년 영주전력지사 변전협력회사 공사","보호반 대체","2024-06-15 09:00","2024-06-16 18:00","2024-06-15 09:00","2024-06-16 18:00","연속"]
[576,"경북","직할","풍산안동CC#2 T/L","24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검","2024-06-07 09:00","2024-06-07 18:00","2024-06-07 09:00","2024-06-07 18:00","연속"]
[577,"경북","직할","풍산안동CC#1 T/L","24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검","2024-06-05 09:00","2024-06-05 18:00","2024-06-05 09:00","2024-06-05 18:00","연속"]
[578,"경북","직할","영덕진보#2 T/L","진보S/S 주변압기 정밀점검 공사","#2M.Tr 무부하가압","2024-06-22 13:00","2024-06-24 18:00","2024-06-22 13:00","2024-06-24 18:00","연속"]
[579,"경북","직할","영덕진보#1 T/L","진보S/S 주변압기 정밀점검 공사","#1M.Tr 무부하가압","2024-06-15 13:00","2024-06-17 18:00","2024-06-15 13:00","2024-06-17 18:00","연속"]
[580,"부산울산","동부산","명례장안 T/L","명례S/S 154kV 금양 신규수용공사","○ 170kV GIS 2CCT 증설 - 시험가압선로 (#2BUS, 금양#1,2T/L #2DS투입상태_24시간)","2024-06-28 15:00","2024-06-29 15:00","2024-06-28 15:00","2024-06-29 15:00","연속"]
[581,"부산울산","동부산","명례장안 T/L","명례S/S 154kV 금양 신규수용공사","○ 170kV GIS 2CCT 증설 - 명례장안T/L #2DS 감압 ( 금양#1T/L #2DS 도체연결 ) - 시험가압선로 (#2BUS, 금양#1,2T/L #2DS개방상태_24시간)","2024-06-17 09:00","2024-06-20 18:00","2024-06-17 09:00","2024-06-20 18:00","연속"]
[582,"부산울산","동부산","명례장안 T/L","명례S/S 154kV 금양 신규수용공사","○ 170kV GIS 2CCT 증설 - 명례장안T/L #1DS 감압 ( 금양#1T/L #1DS 도체연결 ) - 시험가압선로 (#1BUS, 금양#1,2T/L #1DS투입상태_24시간)","2024-06-10 09:00","2024-06-13 18:00","2024-06-10 09:00","2024-06-13 18:00","연속"]
[583,"부산울산","동부산","신양산S/S SEC CB 65660","신양산S/S 65-66-0GIS 보통점검","신양산S/S 65-66-0GIS 보통점검","2024-06-18 09:30","2024-06-18 17:00","2024-06-18 09:30","2024-06-18 17:00","연속"]
[584,"부산울산","동부산","신양산S/S SEC CB 60610","신양산S/S 60-61-0GIS 보통점검","신양산S/S 60-61-0GIS 보통점검","2024-06-17 09:30","2024-06-17 17:00","2024-06-17 09:30","2024-06-17 17:00","연속"]
[585,"부산울산","동부산","우동대연 T/L","OF케이블 옥외 압력유조 밀폐하우징 공사","1. 공사사유 및 목적 : 케이블헤드 부지 내 압력유조 화재 시 설비 피해로 인한 인명 및 경제적 손실 방지를 위해 압력유조 밀폐구조물을 설치하고자 함 2. 공사개요 ○ ST 각파이프 설치 : 836M ○ STS 타공판 설치 : 467㎡ ○ 앵커볼트 설치 : 377EA ○ 기타공사 등 1식","2024-06-01 09:00","2024-06-02 18:00","2024-06-01 09:00","2024-06-02 18:00","연속"]
[586,"부산울산","동부산","우동대연 T/L","OF케이블 옥외 압력유조 밀폐하우징 공사 시행","1. 공사사유 및 목적 : 케이블헤드 부지 내 압력유조 화재 시 설비 피해로 인한 인명 및 경제적 손실 방지를 위해 압력유조 밀폐구조물을 설치하고자 함 2. 공사개요 ○ ST 각파이프 설치 : 836M ○ STS 타공판 설치 : 467㎡ ○ 앵커볼트 설치 : 377EA ○ 기타공사 등 1식","2024-06-08 09:00","2024-06-08 18:00","2024-06-08 09:00","2024-06-08 18:00","연속"]
[587,"부산울산","동부산","정보대연 T/L","OF케이블 옥외 압력유조 밀폐하우징 공사","1. 공사사유 및 목적 : 케이블헤드 부지 내 압력유조 화재 시 설비 피해로 인한 인명 및 경제적 손실 방지를 위해 압력유조 밀폐구조물을 설치하고자 함 2. 공사개요 ○ ST 각파이프 설치 : 836M ○ STS 타공판 설치 : 467㎡ ○ 앵커볼트 설치 : 377EA ○ 기타공사 등 1식","2024-06-15 09:00","2024-06-16 18:00","2024-06-15 09:00","2024-06-16 18:00","연속"]
[588,"부산울산","동부산","정보대연 T/L","OF케이블 옥외 압력유조 밀폐하우징 공사 시행","1. 공사사유 및 목적 : 케이블헤드 부지 내 압력유조 화재 시 설비 피해로 인한 인명 및 경제적 손실 방지를 위해 압력유조 밀폐구조물을 설치하고자 함 2. 공사개요 ○ ST 각파이프 설치 : 836M ○ STS 타공판 설치 : 467㎡ ○ 앵커볼트 설치 : 377EA ○ 기타공사 등 1식","2024-06-09 09:00","2024-06-09 18:00","2024-06-09 09:00","2024-06-09 18:00","연속"]
[589,"부산울산","북부산","대저S/S CB 6200","대저S/S 154kV 6200 B/T 점검","대저S/S 154kV 6200 B/T 점검","2024-06-05 09:00","2024-06-05 18:00","2024-06-05 09:00","2024-06-05 18:00","연속"]
[590,"부산울산","북부산","모라S/S CB 6100","24-25년 북부산전력지사 변전총액공사","모라S/S 154kV 6100 B/T GIS 조작시험","2024-06-10 09:00","2024-06-10 18:00","2024-06-10 09:00","2024-06-10 18:00","연속"]
[591,"부산울산","북부산","모라엄궁#1 T/L","24-25년 북부산전력지사 변전총액공사","모라,엄궁S/S 모라-엄궁#1T/L GIS 조작시험","2024-06-07 09:00","2024-06-07 18:00","2024-06-07 09:00","2024-06-07 18:00","연속"]
[592,"부산울산","북부산","북부산양산 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치","154kV 북부산-삼랑진T/L 수평 추락방지장치 설치(11~36, 41~46호 33기)(북부산-양산 측 회선)","2024-06-19 07:00","2024-06-22 18:00","2024-06-19 07:00","2024-06-22 18:00","연속"]
[593,"부산울산","북부산","북부산삼랑진PP T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치","154kV 북부산-삼랑진T/L 수평 추락방지장치 설치(11~36, 41~46호 33기)","2024-06-12 07:00","2024-06-18 18:00","2024-06-12 07:00","2024-06-18 18:00","연속"]
[594,"부산울산","북부산","북부산양산 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치 안전확보","154kV 북부산-삼랑진T/L 수평 추락방지장치 설치(11~36, 41~46호 33기) 4회선 병가철탑 상하회선 안전확보","2024-06-12 07:00","2024-06-14 18:00","2024-06-12 07:00","2024-06-14 18:00","연속"]
[595,"부산울산","북부산","모라엄궁#1 T/L","엄궁S/S 154kV #1M.Tr 대체공사","- 노후 변압기 대체(엄궁S/S 154kV #1M.Tr) - 대체 시험가압 선로","2024-06-05 09:00","2024-06-06 18:00","2024-06-05 09:00","2024-06-06 18:00","연속"]
[596,"부산울산","북부산","호포매리#2 T/L","154kV 대동분기T/L 건설공사","지지물 : 관형지지물 1기, 케이블타워 2기, 가철탑 2기 전력선 : TACSR 240㎟ × S × 2C - 1.01km","2024-04-27 07:00","2024-04-28 18:00","2024-04-27 07:00","2024-04-28 18:00","연속"]
[597,"부산울산","북부산","호포매리#2 T/L","154kV 대동분기T/L 건설공사","지지물 : 관형지지물 1기, 케이블타워 2기, 가철탑 2기 전력선 : TACSR 240㎟ x S x 2C -1.01km","2024-06-01 06:00","2024-06-02 18:00","2024-06-01 06:00","2024-06-02 18:00","연속"]
[598,"부산울산","서부산","용원녹공#1 T/L","2024년 서부산전력지사 154kV GIS 정밀점검공사","2024년 서부산전력지사 154kV GIS 정밀점검공사(시험가압 선로)","2024-06-02 17:00","2024-06-02 18:00","2024-06-02 17:00","2024-06-02 18:00","연속"]
[599,"부산울산","서부산","용원녹공#2 T/L","서부산전력지사 상반기 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2024-06-10 09:00","2024-06-11 18:00","2024-06-10 09:00","2024-06-11 18:00","연속"]
[600,"부산울산","서부산","용원녹공#1 T/L","서부산전력지사 상반기 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2024-06-03 09:00","2024-06-04 18:00","2024-06-03 09:00","2024-06-04 18:00","연속"]
[601,"부산울산","서부산","서부산S/S #61 BUS","2024년 서부산전력지사 154kV GIS 정밀점검공사","2024년 서부산전력지사 154kV GIS 정밀점검공사(시험가압용)","2024-06-18 17:00","2024-06-18 18:00","2024-06-18 17:00","2024-06-18 18:00","연속"]
[602,"부산울산","서부산","서부산다대#1 T/L","서부산S/S 154kV #1 S/T GIS 차단부 교체공사","서부산S/S 154kV #1 S/T GIS 차단부 교체공사[시험가압]","2024-06-02 09:00","2024-06-03 18:00","2024-06-02 09:00","2024-06-03 18:00","연속"]
[603,"부산울산","서부산","서부산S/S #60 BUS","서부산S/S 154kV #1 S/T GIS 차단부 교체공사","서부산S/S 154kV #1 S/T GIS 차단부 교체공사[시험가압]","2024-06-02 09:00","2024-06-03 18:00","2024-06-02 09:00","2024-06-03 18:00","연속"]
[604,"부산울산","서부산","서부산S/S #60 BUS","2024년 서부산전력지사 154kV GIS 정밀점검공사","2024년 서부산전력지사 154kV GIS 정밀점검공사(시험가압용)","2024-06-14 17:00","2024-06-14 18:00","2024-06-14 17:00","2024-06-14 18:00","연속"]
[605,"부산울산","울산","두왕울산#2 T/L","154kV 추락방지장치 설치공사","11기 / CH 1기 포함 추락방지장치 설치","2024-06-13 09:00","2024-06-14 18:00","2024-06-13 09:00","2024-06-14 18:00","연속"]
[606,"부산울산","울산","신울산두왕#1 T/L","154kV 추락방지장치 설치공사","신울산-두왕 1~7호 - 총 수직수평 1 (2 3 3.1 4 5) 7","2024-06-11 09:00","2024-06-13 18:00","2024-06-11 09:00","2024-06-13 18:00","연속"]
[607,"부산울산","울산","반천언양#2 T/L","효성제GIS 조작부 발청보수","- 반천측 효성제 조작부 발청보수","2024-06-11 14:00","2024-06-11 18:00","2024-06-11 14:00","2024-06-11 18:00","연속"]
[608,"부산울산","울산","직동반천#1 T/L","효성제GIS 조작부 발청보수","- 반천측 효성제 조작부 발청보수","2024-06-12 09:00","2024-06-12 14:00","2024-06-12 09:00","2024-06-12 14:00","연속"]
[609,"부산울산","울산","직동반천#2 T/L","효성제GIS 조작부 발청보수","- 반천측 효성제 조작부 발청보수","2024-06-12 14:00","2024-06-12 18:00","2024-06-12 14:00","2024-06-12 18:00","연속"]
[610,"부산울산","울산","반천언양#1 T/L","효성제GIS 조작부 발청보수","- 반천측 효성제 조작부 발청보수","2024-06-11 09:00","2024-06-11 14:00","2024-06-11 09:00","2024-06-11 14:00","연속"]
[611,"부산울산","울산","산하방어진#1 T/L","2024년 가공송전 순시점검 위탁공사(울산)","- 154kV 동울산-산하 #2T/L 초기점검(154kV 산하-방어진 병가선로) - 점검구간(동울산S/S ~ 산하S/S)","2024-06-11 08:00","2024-06-12 18:00","2024-06-11 08:00","2024-06-12 18:00","연속"]
[612,"부산울산","울산","신온산온산#1 T/L","24년 울산전력지사 변전협력회사 총액공사","- 신온산측 GIS 보통점검 - 온산측 차단기 동작시험 - 세니온제 보호반 성능개선(계통시험)","2024-06-11 09:00","2024-06-11 18:00","2024-06-11 09:00","2024-06-11 18:00","연속"]
[613,"부산울산","울산","신온산온산#2 T/L","24년 울산전력지사 변전협력회사 총액공사","- 온산측 차단기 동작시험 - 세니온제 보호반 성능개선(계통시험)","2024-06-12 09:00","2024-06-12 18:00","2024-06-12 09:00","2024-06-12 18:00","연속"]
[614,"부산울산","울산","신온산온산#3 T/L","24년 울산전력지사 변전협력회사 총액공사","- 차단기 조작시험","2024-06-07 09:00","2024-06-07 18:00","2024-06-07 09:00","2024-06-07 18:00","연속"]
[615,"부산울산","울산","남울산신온산#2 T/L","2024년 가공송전 순시점검 위탁공사","- 345kV 신온산-남울산#1T/L 정밀점검 및 초기점검 - 작업구간 : 초기점검(1,2,4,5,16~19호), 정밀점검(20~21호) - 병가선로 : 154kV 남울산-신온산 #2T/L(18~21호의 자선로)","2024-06-17 08:30","2024-06-18 18:00","2024-06-17 08:30","2024-06-18 18:00","연속"]
[616,"부산울산","울산","남울산신온산#1 T/L","2024년 가공송전 순시점검 위탁공사","345kV 신온산-남울산 #2T/L 정밀점검 및 초기점검 - 작업구간 : 초기점검(1,2,4,5,16~19호), 정밀점검(22~신온산S/T) - 병가선로 : 154kV 남울산-신온산 #1T/L(18~21호의 자선로) 154kV 온산-처용 #1T/L(22~30호의 자선로)","2024-06-19 08:30","2024-06-21 18:00","2024-06-19 08:30","2024-06-21 18:00","연속"]
[617,"부산울산","울산","신울산울산#2 T/L","신울산S/S 154kV 현대화공사","인출포스트 및 빔 구조검토 현척","2024-06-17 09:00","2024-06-17 13:00","2024-06-17 09:00","2024-06-17 13:00","연속"]
[618,"부산울산","울산","신울산언양#2 T/L","154kV 추락방지장치 설치공사","신울산-언양#2 1~67 추락방지장치 설치","2024-06-01 07:30","2024-06-07 18:00","2024-06-01 07:30","2024-06-07 18:00","연속"]
[619,"부산울산","울산","신울산명례#2 T/L","신울산S/S 154kV 현대화공사","인출포스트 및 빔 구조검토 현척","2024-06-03 09:00","2024-06-03 13:00","2024-06-03 09:00","2024-06-03 13:00","연속"]
[620,"부산울산","울산","신울산웅촌#2 T/L","신울산S/S 154kV 현대화공사","인출포스트 및 빔 구조검토 현척","2024-06-12 13:00","2024-06-12 18:00","2024-06-12 13:00","2024-06-12 18:00","연속"]
[621,"부산울산","울산","신울산웅촌#1 T/L","신울산S/S 154kV 현대화공사","인출포스트 및 빔 구조검토 현척","2024-06-12 09:00","2024-06-12 13:00","2024-06-12 09:00","2024-06-12 13:00","연속"]
[622,"부산울산","울산","신울산울산#1 T/L","154kV 추락방지장치 설치공사","추락방지장치 설치 17기 1 [2 3 3.1(관형) 4 5] 6 7 8 9 10 11 12 13 14 15 16(CH)","2024-06-10 07:30","2024-06-12 18:00","2024-06-10 07:30","2024-06-12 18:00","연속"]
[623,"부산울산","울산","신울산S/S SEC CB 66670G","24년 울산전력지사 변전협력회사 총액공사","- GIS 하자점검 - 효성제 조작부 발청보수","2024-06-04 14:00","2024-06-04 18:00","2024-06-04 14:00","2024-06-04 18:00","연속"]
[624,"부산울산","울산","신울산두왕#2 T/L","신울산S/S 154kV 현대화공사","인출포스트 및 빔 구조검토 현척","2024-06-17 13:00","2024-06-17 18:00","2024-06-17 13:00","2024-06-17 18:00","연속"]
[625,"부산울산","울산","신울산S/S SEC CB 61620G","24년 울산전력지사 변전협력회사 총액공사","- GIS 하자점검 - 효성제 조작부 발청보수","2024-06-04 09:00","2024-06-04 14:00","2024-06-04 09:00","2024-06-04 14:00","연속"]
[626,"부산울산","울산","신울산명례#1 T/L","신울산S/S 154kV 현대화공사","인출포스트 및 빔 구조검토 현척","2024-06-03 13:00","2024-06-03 18:00","2024-06-03 13:00","2024-06-03 18:00","연속"]
[627,"부산울산","울산","언양산막#1 T/L","154kV 석계분기T/L 건설공사","지지물 : 154kV 산형강철탑 6기(가철탑 1기 포함) 전력선 : ACSR 410 * 2B * 2,4C","2024-06-21 07:00","2024-06-25 18:00","2024-06-21 07:00","2024-06-25 18:00","연속"]
[628,"부산울산","울산","언양산막#2 T/L","154kV 석계분기T/L 건설공사","지지물 : 154kV 산형강철탑 6기(가철탑 1기 포함) 전력선 : ACSR 410 * 2B * 2,4C","2024-06-26 07:00","2024-06-30 18:00","2024-06-26 07:00","2024-06-30 18:00","연속"]
[629,"부산울산","울산","옥동외동#1 T/L","154kV 추락방지장치 설치공사","외동옥동 #1T/L 추락방지장치 설치 1~4호","2024-06-17 07:30","2024-06-24 18:00","2024-06-17 07:30","2024-06-24 18:00","연속"]
[630,"부산울산","울산","온산처용#1 T/L","2024년 가공송전 순시점검 위탁공사","345kV 신온산-남울산 #2T/L 정밀점검 및 초기점검 - 작업구간 : 초기점검(1,2,4,5,16~19호), 정밀점검(22~신온산S/T) - 병가선로 : 154kV 남울산-신온산 #1T/L(18~21호의 자선로) 154kV 온산-처용 #1T/L(22~30호의 자선로)","2024-06-19 08:30","2024-06-21 18:00","2024-06-19 08:30","2024-06-21 18:00","연속"]
[631,"부산울산","울산","온산처용#1 T/L","24년 울산전력지사 변전협력회사 총액공사","- 차단기 조작시험","2024-06-10 09:00","2024-06-10 18:00","취소","취소","연속"]
[632,"부산울산","울산","온산처용#2 T/L","24년 울산전력지사 변전협력회사 총액공사","- 차단기 조작시험","2024-06-14 09:00","2024-06-14 18:00","2024-06-14 09:00","2024-06-14 18:00","연속"]
[633,"부산울산","울산","울산영남TP#2 T/L","세니온제 보호반 성능개선","- 세니온제 보호반 성능개선(계통시험)","2024-06-03 09:00","2024-06-04 18:00","2024-06-03 09:00","2024-06-04 18:00","연속"]
[634,"부산울산","울산","울주외동#2 T/L","154kV 추락방지장치 설치공사","울주-외동#2 추락방지장치 설치 1~44호","2024-06-20 07:30","2024-06-26 18:00","2024-06-20 07:30","2024-06-26 18:00","연속"]
[635,"부산울산","울산","울주입실#2 T/L","154kV 추락방지장치 설치공사","울주-입실#2 T/L 추락방지장치 설치 1~4호","2024-06-25 07:30","2024-06-26 18:00","2024-06-25 07:30","2024-06-26 18:00","연속"]
[636,"부산울산","울산","효문방어진 T/L","154kV 추락방지장치 설치공사","효문방어진 5~20호 설치","2024-06-08 07:30","2024-06-09 18:00","2024-06-08 07:30","2024-06-09 18:00","연속"]
[637,"부산울산","울산","효문방어진 T/L","154kV 추락방지장치 설치공사","효문-방어진 5~20 추락방지장치 설치","2024-06-15 07:30","2024-06-16 18:00","2024-06-15 07:30","2024-06-16 18:00","연속"]
[638,"부산울산","직할","수정범일#2 T/L","범일S/S 수정-범일#1,2T/L 세니온 보호반 성능개선","수정-범일#1,2T/L 세니온 보호반 성능개선(계통시험팀, 세니온)","2024-06-19 09:30","2024-06-20 18:00","2024-06-19 09:30","2024-06-20 18:00","연속"]
[639,"부산울산","직할","수정범일#1 T/L","범일S/S 수정-범일#1,2T/L 세니온 보호반 성능개선","수정-범일#1,2T/L 세니온 보호반 성능개선(계통시험팀, 세니온)","2024-06-19 09:30","2024-06-20 18:00","2024-06-19 09:30","2024-06-20 18:00","연속"]
[640,"부산울산","직할","범일서면#2 T/L","154kV 범일S/S #3M.Tr 증설공사","- 신설 #1BUS GIB(Reducer) 설치 - 기설 #1BUS END COVER부 SPACER 교체 - 170kV GIS 및 #3M.Tr 무부하 시험가압","2024-06-14 09:00","2024-06-18 18:00","2024-06-14 09:00","2024-06-18 18:00","연속"]
[641,"부산울산","직할","수정S/S #1 BUS","154kV 부산-수정 지중T/L OF케이블 선종교체공사","154kV 부산-수정(지중)T/L OF1200을 XLPE1200으로 교체","2024-06-13 09:00","2024-06-13 18:00","2024-06-13 09:00","2024-06-13 18:00","연속"]
[642,"부산울산","직할","양정범천 T/L","24년 직할 상반기 170kV GIS 정밀점검","양정S/S 154kV 양정-범천T/L GIS 정밀점검","2024-06-10 09:00","2024-06-11 18:00","2024-06-10 09:00","2024-06-11 18:00","연속"]
[643,"부산울산","직할","신대연양정#2 T/L","24년 직할 상반기 170kV GIS 정밀점검","양정S/S 154kV 신대연-양정#2T/L GIS 정밀점검","2024-06-05 09:00","2024-06-06 18:00","2024-06-05 09:00","2024-06-06 18:00","연속"]
[644,"부산울산","직할","신대연양정#1 T/L","24년 직할 상반기 170kV GIS 정밀점검","양정S/S 154kV 신대연-양정#1T/L GIS 정밀점검","2024-06-03 09:00","2024-06-04 18:00","2024-06-03 09:00","2024-06-04 18:00","연속"]
[645,"경남","직할","신월삼정#1 T/L","삼정S/S 154kV 신월-삼정#1T/L GIS PD조치","삼정S/S 154kV 신월-삼정#1T/L GIS(697) GIS PD조치","취소","취소","취소","취소","연속"]
[646,"경남","통영","거류거제#1 T/L","154kV 삼성조선T/L 피뢰기 설치공사","154kV 삼성조선T/L 피뢰기 설치공사","2024-06-01 01:00","2024-06-02 22:00","2024-06-01 01:00","2024-06-02 22:00","연속"]
[647,"경남","통영","거제S/S 삼성조선T/L CB","154kV 삼성조선T/L 피뢰기 설치공사","154kV 삼성조선T/L 피뢰기 설치공사","2024-06-01 01:00","2024-06-02 22:00","2024-06-01 01:00","2024-06-02 22:00","연속"]
[648,"경남","통영","신고성거류#2 T/L","154kV 신고성-거류#2T/L 추락방지장치 설치공사","154kV 신고성-거류#2T/L 추락방지장치 설치공사","2024-06-01 07:00","2024-06-02 18:00","2024-06-01 07:00","2024-06-02 18:00","매일"]
[649,"경남","함안","가야사봉#1 T/L","154kV 가야-사봉#1T/L 추락방지장치 설치공사","154kV 가야-사봉#1T/L 수평형 추락방지장치 및 수직형 중간클램프 개선 수평 추락방지장치 설치 : No.14~43, 50 (31기)","2024-06-01 07:00","2024-06-02 18:00","2024-06-01 07:00","2024-06-02 18:00","연속"]
[650,"경남","김해송변전부","신김해지사#1 T/L","154kV 신김해-지사T/L 등 OPGW 증설공사","1) OPGW(100㎟) 22km 교체 2) 항공장애표시구 157개 교체 3) 접속함체 11개소 시설 및 교체","2024-06-03 07:00","2024-06-07 18:00","2024-06-03 07:00","2024-06-05 18:00","연속"]
[651,"경남","진주","거창합천#2 T/L","154kV 거창-합천 #2T/L 수평 추락방지장치 설치공사","154kV 거창-합천 #2T/L 수평 추락방지장치 설치공사 No. 1~3, 5~74-1, 76~82","2024-06-03 07:30","2024-06-05 18:00","2024-06-03 07:30","2024-06-05 18:00","매일"]
[652,"경남","진주","함양거창#2 T/L","154kV 거창-합천 #2T/L 작업에 따른 안전이격 거리 확보 휴전","154kV 거창-합천 #2T/L 수평 추락방지장치 설치공사 No. 1~3, 5~74-1, 76~82","2024-06-05 07:30","2024-06-05 18:00","2024-06-05 07:30","2024-06-05 18:00","연속"]
[653,"경남","진주","하동하동화력 T/L","154kV 하동-남해T/L 점퍼지지애자 설치작업 관련 안전거리확보","154kV 하동-남해T/L 점퍼지지애자 설치작업 관련 안전거리확보 - 1~109호(19기)","2024-06-06 07:00","2024-06-06 18:00","2024-06-06 07:00","2024-06-06 18:00","매일"]
[654,"경남","통영","신고성거류#2 T/L","154kV 신고성-거류#2T/L 추락방지장치 설치공사","154kV 신고성-거류#2T/L 추락방지장치 설치공사","2024-06-06 07:00","2024-06-06 18:00","2024-06-06 07:00","2024-06-06 18:00","매일"]
[655,"경남","함안","가야사봉#1 T/L","가야S/S 154kV 가야-사봉#1T/L GIS 정밀 점검(CB+DS)","가야S/S 154kV 가야-사봉#1T/L GIS 정밀 점검(CB+DS)","2024-06-06 09:30","2024-06-08 17:30","취소","취소","연속"]
[656,"경남","통영","거제아주#1 T/L","아주S/S 거제-아주#1,2T/L GIS 조작시험","아주S/S 거제-아주#1,2T/L GIS 조작시험","2024-06-06 09:30","2024-06-06 14:00","취소","취소","연속"]
[657,"경남","통영","거제아주#2 T/L","아주S/S 거제-아주#1,2T/L GIS 조작시험","아주S/S 거제-아주#1,2T/L GIS 조작시험","2024-06-06 14:00","2024-06-06 18:00","취소","취소","연속"]
[658,"경남","함안","가야사봉#1 T/L","가야S/S154kV가야-사봉#1T/L GIS 정밀점검 2DS시험가압","가야S/S 154kV가야-사봉#1T/L GIS 정밀 점검 2DS시험가압","2024-06-06 17:30","2024-06-06 18:30","취소","취소","연속"]
[659,"경남","진주","의령함양 T/L","154kV 의령-함양T/L 추락방지장치 설치","154kV 의령-함양T/L 피뢰기 설치작업 등 - 1~132호(132기)","2024-06-07 07:00","2024-06-07 18:00","2024-06-07 07:00","2024-06-07 18:00","연속"]
[660,"경남","통영","삼천포사천#1 T/L","154kV 삼천포사천#1 T/L 추락방지장치 설치공사","154kV 삼천포사천#1 T/L 추락방지장치 설치공사","2024-06-07 07:00","2024-06-07 18:00","취소","취소","매일"]
[661,"경남","통영","거류거제#2 T/L","154kV 삼성조선T/L 피뢰기 설치공사","154kV 삼성조선T/L 피뢰기 설치공사","2024-06-08 01:00","2024-06-09 21:00","2024-06-08 01:00","2024-06-09 21:00","연속"]
[662,"경남","통영","거제S/S 삼성조선T/L CB","154kV 삼성조선T/L 피뢰기 설치공사","154kV 삼성조선T/L 피뢰기 설치공사","2024-06-08 01:00","2024-06-09 21:00","2024-06-08 01:00","2024-06-09 21:00","연속"]
[663,"경남","함안","가야사봉#2 T/L","154kV 가야-사봉#2T/L 추락방지장치 설치공사","154kV 가야-사봉#2T/L 수평형 추락방지장치 및 수직형 중간클램프 개선 - 수평 추락방지장치 설치 : No.14~43, 50 (31기)","2024-06-08 07:00","2024-06-09 18:00","2024-06-08 07:00","2024-06-09 18:00","매일"]
[664,"경남","통영","신고성거류#2 T/L","154kV 신고성-거류#2T/L 추락방지장치 설치공사","154kV 신고성-거류#2T/L 추락방지장치 설치공사","2024-06-08 07:00","2024-06-09 18:00","2024-06-08 07:00","2024-06-09 18:00","매일"]
[665,"경남","김해송변전부","신김해지사#2 T/L","154kV 신김해-지사T/L 등 OPGW 증설공사","1) OPGW(100㎟) 22km 교체 2) 항공장애표시구 157개 교체 3) 접속함체 11개소 시설 및 교체","2024-06-08 07:00","2024-06-14 18:00","2024-06-06 07:00","2024-06-14 18:00","연속"]
[666,"경남","통영","신고성거제#1 T/L","154kV 거제변전소 인출 가공송전선로 이설 임시선로 구성공사(1차)","154kV 신고성-거제#1T/L S/T ~ 가철탑4호 간 가선","2024-06-08 08:00","2024-06-09 18:00","취소","취소","연속"]
[667,"경남","함안","가야사봉#1 T/L","가야SS 154kV가야-사봉#1TL GIS 정밀점검 1DS,CB 시험가압","가야SS 154kV가야-사봉#1TL GIS 정밀점검 1DS,CB 시험가압","2024-06-08 17:30","2024-06-08 18:30","취소","취소","연속"]
[668,"경남","함안","신마산중리#1 T/L","154kV 신마산-중리#1T/L 용량증대 전선교체공사","용량증대 전선교체공사 ACSR330SQ-ASCC/TW430SQ (신마산S/T~9호)","2024-06-10 07:00","2024-06-21 18:00","2024-06-10 07:00","2024-06-21 18:00","연속"]
[669,"경남","함안","신마산서마산#1 T/L","154kV 신마산-중리#1,2T/L 용량증대 전선교체공사 안전이격거리확보","용량증대 전선교체공사 ACSR330SQ-ASCC/TW430SQ (신마산S/T~9호) 안전확보","2024-06-10 07:00","2024-06-21 18:00","2024-06-10 07:00","2024-06-21 18:00","연속"]
[670,"경남","통영","삼천포사천#1 T/L","154kV 삼천포사천#1 T/L 추락방지장치 설치공사","154kV 삼천포사천#1 T/L 추락방지장치 설치공사","2024-06-10 07:00","2024-06-10 18:00","취소","취소","매일"]
[671,"경남","진주","쌍림합천#1 T/L","154kV 쌍림-합천T/L 피뢰기 설치작업 관련 안전거리확보","154kV 쌍림-합천T/L 피뢰기 설치작업","2024-06-10 07:00","2024-06-12 18:00","2024-06-10 07:00","2024-06-12 18:00","매일"]
[672,"경남","함안","신마산중리#2 T/L","154kV 신마산-중리#2T/L 용량증대 전선교체공사","용량증대 전선교체공사 ACSR330SQ-ASCC/TW430SQ (신마산S/T~9호)","2024-06-10 07:00","2024-06-21 18:00","2024-06-10 07:00","2024-06-21 18:00","연속"]
[673,"경남","김해송변전부","신김해진례#1 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-06-13 07:00","2024-06-14 18:00","2024-06-13 07:00","2024-06-14 18:00","매일"]
[674,"경남","진주","의령함양 T/L","154kV 의령-함양T/L 추락방지장치 설치","154kV 의령-함양T/L 피뢰기 설치작업 등 - 1~132호(132기)","2024-06-13 07:00","2024-06-20 18:00","2024-06-13 07:00","2024-06-20 18:00","매일"]
[675,"경남","함안","초동밀양#1 T/L","초동-밀양T/L 항공장애표시구 설치 공사","초동-밀양T/L 9~10호 OPGW 항공장애구 설치 초동-밀양T/L 13~14호 OPGW 항공장애구 설치 초동-밀양T/L 14~15호 OPGW 항공자애구 설치","2024-06-13 09:00","2024-06-13 18:00","2024-06-13 09:00","2024-06-13 18:00","연속"]
[676,"경남","진주","사천개양#2 T/L","사천-개양T/L 수평 추락방지장치 설치공사","사천-개양T/L 수평 추락방지장치 설치공사 No.7~73","2024-06-14 07:30","2024-06-18 18:00","2024-06-14 07:30","2024-06-18 18:00","매일"]
[677,"경남","통영","신고성거류#3 T/L","신고성S/S 신고성-거류#3T/L GIS 조작시험","신고성S/S 신고성-거류#3T/L GIS 조작시험","2024-06-14 09:30","2024-06-14 14:00","2024-06-14 09:30","2024-06-14 14:00","연속"]
[678,"경남","통영","신고성고성 T/L","신고성S/S 신고성-고성T/L GIS 조작시험","신고성S/S 신고성-고성T/L GIS 조작시험","2024-06-14 14:00","2024-06-14 18:00","2024-06-14 14:00","2024-06-14 18:00","연속"]
[679,"경남","김해송변전부","매리김해#2 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-06-15 07:00","2024-06-16 18:00","2024-06-15 07:00","2024-06-16 18:00","매일"]
[680,"경남","김해송변전부","매리김해#1 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-06-15 07:00","2024-06-16 18:00","2024-06-15 07:00","2024-06-16 18:00","매일"]
[681,"경남","통영","신고성거류#2 T/L","154kV 신고성-거류#2T/L 추락방지장치 설치공사","154kV 신고성-거류#2T/L 추락방지장치 설치공사","2024-06-15 07:00","2024-06-16 18:00","2024-06-15 07:00","2024-06-16 18:00","매일"]
[682,"경남","통영","신고성거제#2 T/L","154kV 거제변전소 인출 가공송전선로 이설 임시선로 구성공사(2차)","1. 154kV 신고성-거제#2T/L S/T ~ 가철탑4호 간 가선 2. 154kV 통영-거제#1T/L 70호 중, 하단 암보강(안전거리 확보)(신고성-거제#2T/L 196호와 병가철탑)","2024-06-15 08:00","2024-06-16 18:00","취소","취소","연속"]
[683,"경남","통영","통영거제#2 T/L","154kV 거제변전소 인출 가공송전선로 이설 임시선로 구성공사(1차)"," ","2024-06-15 08:00","2024-06-15 18:00","2024-06-15 08:00","2024-06-15 18:00","연속"]
[684,"경남","통영","통영거제#1 T/L","154kV 거제변전소 인출 가공송전선로 이설 임시선로 구성공사(2차)","1. 154kV 통영-거제#1T/L S/T ~ 가철탑4-1호 간 가선 2. 154kV 통영-거제#1T/L 70호 중, 하단 암보강","2024-06-15 08:00","2024-06-16 18:00","취소","취소","연속"]
[685,"경남","김해송변전부","김해어방#1 T/L","김해S/S 김해어방#1 T/L 휴전","김해S/S 김해어방#1 T/L 베어링발청보수","2024-06-15 09:30","2024-06-15 13:30","2024-06-15 09:30","2024-06-15 13:30","연속"]
[686,"경남","김해송변전부","삼계어방#2 T/L","어방S/S 삼계어방#2 T/L 휴전","어방S/S 삼계어방#2 T/L 베어링발청보수","2024-06-15 13:30","2024-06-15 17:30","2024-06-15 13:30","2024-06-15 17:30","연속"]
[687,"경남","통영","통영거제#1 T/L","154kV 삼성조선T/L 피뢰기 설치공사","154kV 삼성조선T/L 피뢰기 설치공사","2024-06-16 08:00","2024-06-16 17:00","2024-06-16 08:00","2024-06-16 17:00","연속"]
[688,"경남","김해송변전부","김해어방#2 T/L","김해S/S 김해어방#2 T/L 휴전","김해,어방S/S 김해어방#2 T/L 베어링발청보수","2024-06-16 09:30","2024-06-16 17:30","2024-06-16 09:30","2024-06-16 17:30","연속"]
[689,"경남","진주","의령동진주#1 T/L","154kV 의령-함양T/L 피뢰기 설치작업 관련 안전거리확보","154kV 의령-함양T/L 피뢰기 설치작업 관련 4회선 구간 안전거리확보 - 1~7호(7기)","2024-06-17 07:00","2024-06-17 18:00","2024-06-17 07:00","2024-06-17 18:00","매일"]
[690,"경남","김해송변전부","김해S/S CB 6100","김해S/S 154kV #1-#2 BUS TIE GIS 휴전","김해S/S 154kV #1-#2 BUS TIE GIS 베어링발청보수","2024-06-17 09:30","2024-06-17 13:30","2024-06-17 09:30","2024-06-17 13:30","연속"]
[691,"경남","직할","신월동읍#2 T/L","154kV 신월-동읍T/L 피뢰기 열화진단","154kV 신월-동읍#2T/L 피뢰기 열화진단","2024-06-18 09:00","2024-06-18 18:00","2024-06-18 09:00","2024-06-18 18:00","연속"]
[692,"경남","진주","함양거창#2 T/L","거창-함양T/L 수평 추락방지장치 설치공사","거창-함양T/L 수평 추락방지장치 설치공사 No.30~65","2024-06-21 07:30","2024-06-25 18:00","2024-06-21 07:30","2024-06-25 18:00","매일"]
[693,"경남","통영","신고성거류#2 T/L","154kV 신고성-거류#2T/L 추락방지장치 설치공사","154kV 신고성-거류#2T/L 추락방지장치 설치공사","2024-06-22 07:00","2024-06-23 18:00","2024-06-22 07:00","2024-06-23 18:00","매일"]
[694,"경남","진주","동진주진주#2 T/L","154kV 동진주-진주T/L 피뢰기 설치작업","154kV 동진주-진주T/L 피뢰기 설치작업 - 1~4호(4기)","2024-06-22 07:00","2024-06-23 18:00","2024-06-22 07:00","2024-06-23 18:00","매일"]
[695,"경남","진주","동진주진주#1 T/L","154kV 동진주-진주T/L 피뢰기 설치작업","154kV 동진주-진주T/L 피뢰기 설치작업 - 1~4호(4기)","2024-06-22 07:00","2024-06-23 18:00","2024-06-22 07:00","2024-06-23 18:00","매일"]
[696,"경남","통영","삼천포사천#1 T/L","154kV 삼천포사천#1 T/L 추락방지장치 설치공사","154kV 삼천포사천#1 T/L 추락방지장치 설치공사","2024-06-22 07:00","2024-06-23 18:00","2024-06-01 07:00","2024-06-02 18:00","매일"]
[697,"경남","통영","고성통영CC#1 T/L","154kV 고성-통영복합#1T/L GIS 하자점검 등","154kV 고성-통영복합#1T/L GIS 하자점검 등","2024-06-22 09:30","2024-06-22 18:00","2024-06-22 09:30","2024-06-22 18:00","연속"]
[698,"경남","진주","사천개양#1 T/L","사천-개양T/L 수평 추락방지장치 설치공사","사천-개양T/L 수평 추락방지장치 설치공사 No.7~73","2024-06-26 07:30","2024-06-28 18:00","2024-06-26 07:30","2024-06-28 18:00","매일"]
[699,"경남","김해송변전부","신김해진례#2 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-06-28 07:00","2024-06-28 18:00","2024-06-28 07:00","2024-06-28 18:00","매일"]
[700,"경남","김해송변전부","매리김해#2 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-06-29 07:00","2024-06-30 18:00","2024-06-29 07:00","2024-06-30 18:00","매일"]
[701,"경남","통영","신고성거류#2 T/L","154kV 신고성-거류#2T/L 추락방지장치 설치공사","154kV 신고성-거류#2T/L 추락방지장치 설치공사","2024-06-29 07:00","2024-06-30 18:00","2024-06-29 07:00","2024-06-30 18:00","매일"]
[702,"경남","통영","삼천포사천#2 T/L","154kV 삼천포사천#2 T/L 추락방지장치 설치공사","154kV 삼천포사천#2 T/L 추락방지장치 설치공사","2024-06-29 07:00","2024-06-30 18:00","2024-06-08 07:00","2024-06-09 18:00","매일"]
[703,"경남","김해송변전부","매리김해#1 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2024-06-29 07:00","2024-06-30 18:00","2024-06-29 07:00","2024-06-30 18:00","매일"]
[704,"경남","통영","안정통영CC#1 T/L","154kV 안정-통영복합#1T/L GIS 보통점검 등","154kV 안정-통영복합#1T/L GIS 보통점검 등","2024-06-29 09:30","2024-06-29 18:00","2024-06-29 09:30","2024-06-29 18:00","연속"]
[705,"대구",null,"청하영덕#2 T/L","수평추락방지장치 설치","수평추락방지장치 설치(6/5~6/6 무부하로 연속)","2024-06-03 07:00","2024-06-17 18:00","2024-06-03 07:00","2024-06-17 18:00"," 매일"]
[706,"대구",null,"영덕진보#2 T/L","수평추락방지장치 설치","수평추락방지장치 설치","2024-06-03 07:00","2024-06-03 18:00","2024-06-03 07:00","2024-06-03 18:00","매일"]
[707,"대구",null,"신영일청하#1 T/L","수평추락방지장치 설치","수평추락방지장치 설치","2024-06-13 07:00","2024-06-20 18:00","2024-06-13 07:00","2024-06-20 18:00","매일"]
[708,"대구",null,"신영일서포항#2 T/L","수평추락방지장치 설치","수평추락방지장치 설치","2024-06-19 07:00","2024-06-20 18:00","2024-06-19 07:00","2024-06-20 18:00","매일"]
[709,"전북",null,"군산S/S #61 BUS","군산S/S 170kV GIS대체공사(6차)","군산S/S 170kV GIS대체공사(6차)","2024-06-10 09:00","2024-06-12 18:00","2024-06-10 09:00","2024-06-12 18:00","연속"]