{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":9,"n_cols":11,"rows_kept":9,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2024년도 7월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신안성신가평 T/L","신가평S/S 계통보호설비 이설","신가평S/S 감시실 이설에 따른 계통보호설비 이설 - 신가평-신안성 T/L 1계열 7.8 - 신가평-신안성 T/L 2계열 7.9","2024-07-15 09:00","2024-07-15 18:00","취소","취소","연속"]
[2,"경기북부","구리","신태백신가평#2 T/L","신가평S/S 계통보호설비 이설","신가평S/S 감시실 이설에 따른 계통보호설비 이설 - 신가평-신태백 #1T/L 1계열 7.1 - 신가평-신태백 #1T/L 2계열 7.2 - 신가평-신태백 #2T/L 1계열 7.3 - 신가평-신태백 #2T/L 2계열 7.4","2024-07-17 09:00","2024-07-17 18:00","취소","취소","연속"]
[3,"경기북부","구리","신태백신가평#1 T/L","신가평S/S 계통보호설비 이설","신가평S/S 감시실 이설에 따른 계통보호설비 이설 - 신가평-신태백 #1T/L 1계열 7.1 - 신가평-신태백 #1T/L 2계열 7.2 - 신가평-신태백 #2T/L 1계열 7.3 - 신가평-신태백 #2T/L 2계열 7.4 [병행] 신가평-신태백 #1T/L HSGS 점검","2024-07-16 09:00","2024-07-16 18:00","취소","취소","연속"]
[4,"경북","영주","신한울N/P #2 Tie-Tr","신한울S/S 765kV #1,2M.Tr 보통점검 공사","신한울S/S 765kV #2M.Tr 보통점검 공사","2024-07-08 09:00","2024-07-12 18:00","2024-07-08 09:00","2024-07-12 18:00","연속"]
[5,"경북","영주","신한울N/P #1 Tie-Tr","신한울S/S 765kV #1,2M.Tr 보통점검 공사","신한울S/S 765kV #1M.Tr 보통점검 공사","2024-07-01 09:00","2024-07-05 18:00","2024-07-01 09:00","2024-07-05 18:00","연속"]

{"sheet":"345설비","index":1,"n_rows":154,"n_cols":11,"rows_kept":154,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2024년도 7월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","미금성동#2 T/L","2024~25년 성동전력지사 변전협력회사 공사","- B/F PNL 대체","2024-07-08 10:00","2024-07-11 18:00","취소","취소","연속"]
[2,"서울","성동","성동S/S #2 M.Tr","2024~25년 성동전력지사 변전협력회사 공사","B/F PNL 대체","2024-07-08 10:00","2024-07-11 18:00","취소","취소","연속"]
[3,"서울","중부","중부S/S #3 M.Tr","24-25년 중부전력지사 변전협력회사 총액공사","#3M.Tr 부싱 점검","2024-07-02 09:00","2024-07-04 18:00","2024-07-02 09:00","2024-07-04 18:00","연속"]
[4,"남서울","강남","신양재S/S #3 Sh.R CB","24-25년도 강남전력지사 변전협력회사 총액공사","주)345kV GIS 조작시험(신양재S/S 345kV #3Sh.R) 병행)#74B/F PNL 대체공사","2024-07-15 10:00","2024-07-19 18:00","취소","취소","연속"]
[5,"남서울","강남","신양재S/S #4 Sh.R CB","24-25년도 강남전력지사 변전협력회사 총액공사","주)345kV GIS 조작시험(신양재S/S 345kV #3Sh.R) 병행)#74B/F PNL 대체공사","2024-07-15 10:00","2024-07-19 18:00","취소","취소","연속"]
[6,"남서울","동서울","동서울S/S #2 Sh.R CB","345kV 동서울S/S 종합정비공사","○ 500kV 동서울변환소 본관동 착공관련 사전정비작업 - 345kV GIS 및 Sh.R 본체 제어케이블 이설","2024-07-08 09:00","2024-08-02 18:00","2024-07-08 09:00","2024-07-31 18:00","연속"]
[7,"남서울","동서울","곤지암동서울#1 T/L","345kV 동서울S/S 종합정비공사","500kV 동서울 변환소 부지확보 관련 사전 정비공사 - 345kV GIS 제어케이블 이설 및 부대작업","2024-07-22 09:00","2024-08-16 18:00","2024-07-22 09:00","2024-08-16 18:00","연속"]
[8,"인천","김포","신김포신파주#1 T/L","24-25년 부평,김포전력지사 가공송전 협력회사 공사","수평 추락방지시설 설치","2024-07-12 08:00","2024-07-12 16:00","취소","취소","연속"]
[9,"인천","김포","신김포서인천CC T/L","2024년 가공송전 순시점검 위탁공사","송전선로 애자오염 시스템 시범적용을 위한 설치 작업","2024-07-09 09:00","2024-07-09 18:00","취소","취소","연속"]
[10,"인천","부평","서인천C/C CB 7171","서인천C/C 345kV 신김포-서인천CC T/L 7171GIS조작시험","서인천C/C 345kV 신김포-서인천CC T/L 7171GIS조작시험","2024-07-01 12:00","2024-07-01 18:00","2024-07-01 12:00","2024-07-01 18:00","연속"]
[11,"인천","부평","서인천C/C CB 7100","서인천C/C 345kV 7100GIS 조작시험","서인천C/C 345kV 7100GIS 조작시험","2024-07-01 09:00","2024-07-01 12:00","2024-07-01 09:00","2024-07-01 12:00","연속"]
[12,"인천","부평","서인천C/C CB 7172","서인천C/C 345kV #1 M.Tr 1차 7172GIS 조작시험","서인천C/C 345kV #1 M.Tr 1차 7172GIS 조작시험","2024-07-02 09:00","2024-07-02 12:00","2024-07-02 09:00","2024-07-02 12:00","연속"]
[13,"인천","부평","서인천C/C CB 7272","서인천C/C 345kV #2 M.Tr 1차 7272GIS 조작시험","서인천C/C 345kV #2 M.Tr 1차 7272GIS 조작시험","2024-07-02 12:00","2024-07-02 18:00","2024-07-02 12:00","2024-07-02 18:00","연속"]
[14,"인천","부평","서인천C/C CB 7372","서인천C/C 345kV #3 M.Tr 1차 7372GIS 조작시험","서인천C/C 345kV #3 M.Tr 1차 7372GIS 조작시험","2024-07-04 09:00","2024-07-04 12:00","취소","취소","연속"]
[15,"인천","부평","서인천C/C CB 7400","서인천신부평#3T/L-#4M.Tr TIE 7400GIS 조작시험","서인천C/C 서인천신부평#3T/L-#4M.Tr TIE 7400GIS 조작시험","2024-07-04 12:00","2024-07-04 18:00","취소","취소","연속"]
[16,"인천","부평","서인천C/C CB 7471","서인천C/C 서인천CC-신부평#3T/L 7471GIS 조작시험","서인천C/C 서인천CC-신부평#3T/L 7471GIS 조작시험","2024-07-05 09:00","2024-07-05 12:00","취소","취소","연속"]
[17,"인천","부평","서인천C/C CB 7472","서인천C/C 345kV #4 M.Tr 1차 7472GIS 조작시험","서인천C/C 345kV #4 M.Tr 1차 7472GIS 조작시험","2024-07-05 12:00","2024-07-05 18:00","취소","취소","연속"]
[18,"인천","부평","서인천C/C CB 7300","서인천C/C 서인천신부평#2T/L-#3M.Tr 7300GIS 조작시험","서인천C/C 서인천신부평#2T/L-#3M.Tr TIE GIS 조작시험","2024-07-10 09:00","2024-07-10 12:00","취소","취소","연속"]
[19,"인천","부평","서인천C/C CB 7371","서인천C/C 서인천신부평#2T/L 7371GIS 조작시험","서인천C/C 서인천신부평#2T/L 7371GIS 조작시험","2024-07-10 12:00","2024-07-10 18:00","취소","취소","연속"]
[20,"인천","부평","신가좌S/S CB 7472","신가좌S/S 345kV #3 M.Tr 1차 GIS 조작시험","신가좌S/S 345kV #3 M.Tr 1차 GIS 및 절연열화 측정","2024-07-04 09:00","2024-07-04 18:00","취소","취소","연속"]
[21,"인천","부평","신경서S/S CB 7371","신경서S/S 345kV 신경서-포스코S/Y#1T/L GIS 조작시험","신경서S/S 345kV 신경서-포스코S/Y#1T/L GIS 조작시험","2024-07-03 09:00","2024-07-03 12:00","취소","취소","연속"]
[22,"인천","부평","신경서S/S CB 7571","신경서S/S 345kV 신경서-포스코S/Y#2T/L GIS 조작시험","신경서S/S 345kV 신경서-포스코S/Y#2T/L GIS 조작시험","2024-07-03 12:00","2024-07-03 18:00","취소","취소","연속"]
[23,"인천","부평","신인천C/C CB 7500","신인천C/C 345kV 3MT101 TIE 7500GIS 조작시험","신인천C/C 345kV 3MT101 TIE 7500GIS 조작시험","2024-07-05 14:00","2024-07-05 18:00","2024-07-05 14:00","2024-07-05 18:00","연속"]
[24,"인천","부평","신인천C/C CB 7900","신인천C/C 345kV 4MT001 TIE 7900GIS 조작시험","신인천C/C 345kV 4MT001 TIE 7900GIS 조작시험","2024-07-02 12:00","2024-07-02 18:00","2024-07-02 12:00","2024-07-02 18:00","연속"]
[25,"인천","부평","신인천C/C CB 7872","신인천C/C 345kV 4MT201 7872GIS 조작시험","신인천C/C 345kV 4MT201 7872GIS 조작시험","2024-07-02 09:00","2024-07-02 12:00","2024-07-02 09:00","2024-07-02 12:00","연속"]
[26,"인천","부평","신인천C/C CB 7871","신인천C/C 신경서-신인천C/C T/L 7871 GIS 조작시험","신인천C/C 345kV 신경서-신인천C/C T/L 7871 GIS 조작시험","2024-07-01 13:00","2024-07-01 18:00","2024-07-01 13:00","2024-07-01 18:00","연속"]
[27,"인천","부평","신인천C/C CB 7800","신경서신인천T/L-4MT201 TIE 7800 GIS 조작시험","신경서신인천T/L-4MT201 TIE 7800 GIS 조작시험","2024-07-01 09:00","2024-07-01 12:00","2024-07-01 09:00","2024-07-01 12:00","연속"]
[28,"인천","부평","신인천C/C CB 7672","신인천C/C 345kV 3MT201 7672GIS 조작시험","신인천C/C 345kV 3MT201 GIS 조작시험","2024-07-08 09:00","2024-07-08 12:00","2024-07-08 09:00","2024-07-08 12:00","연속"]
[29,"인천","부평","신인천C/C CB 7700","신인천C/C 신김포신인천T/L-4MT101 TIE 7700GIS 조작시험","신인천C/C 신김포신인천T/L-4MT101 TIE 7700GIS 조작시험","2024-07-08 12:00","2024-07-08 15:00","2024-07-08 12:00","2024-07-08 15:00","연속"]
[30,"인천","부평","신인천C/C SEC CB 71720","신인천C/C 345kV #71-#72 SEC GIS 조작시험","신인천C/C 345kV #71-#72 SEC GIS 조작시험","2024-07-08 15:00","2024-07-08 18:00","2024-07-08 15:00","2024-07-08 18:00","연속"]
[31,"인천","부평","신인천C/C CB 7771","신인천C/C 345kV 신김포-신인천C/C T/L 7771GIS 조작시험","신인천C/C 345kV 신김포-신인천C/C T/L 7771GIS 조작시험","2024-07-09 09:00","2024-07-09 12:00","2024-07-09 09:00","2024-07-09 12:00","연속"]
[32,"인천","부평","신인천C/C CB 7772","신인천C/C 345kV 4MT101 7772GIS 조작시험","신인천C/C 345kV 4MT101 7772GIS 조작시험","2024-07-09 12:00","2024-07-09 15:00","2024-07-09 12:00","2024-07-09 15:00","연속"]
[33,"인천","부평","신인천C/C CB 7972","신인천C/C 345kV 4MT001 7972GIS 조작시험","신인천C/C 345kV 4MT001 7972GIS 조작시험","2024-07-09 15:00","2024-07-09 18:00","2024-07-09 15:00","2024-07-09 18:00","연속"]
[34,"인천","부평","신인천C/C SEC CB 70710","신인천C/C 345kV #70-#71 SEC GIS 조작시험","신인천C/C 345kV #70-#71 SEC GIS 조작시험","2024-07-06 08:00","2024-07-06 10:00","2024-07-06 08:00","2024-07-06 10:00","연속"]
[35,"인천","부평","신인천C/C CB 7671","신인천C/C 345kV 3MT001 7671GIS 조작시험","신인천C/C 345kV 3MT001 7671GIS 조작시험","2024-07-06 12:00","2024-07-06 14:00","2024-07-06 12:00","2024-07-06 14:00","연속"]
[36,"인천","부평","신인천C/C CB 7572","신인천C/C 345kV 3MT101 7572GIS 조작시험","신인천C/C 345kV 3MT101 7572GIS 조작시험","2024-07-06 14:00","2024-07-06 18:00","2024-07-06 14:00","2024-07-06 18:00","연속"]
[37,"인천","부평","신인천C/C CB 7600","신인천C/C 3MT001-3MT201 TIE 7600GIS 조작시험","신인천C/C 3MT001-3MT201 TIE 7600GIS 조작시험","2024-07-06 14:00","2024-07-06 16:00","2024-07-06 14:00","2024-07-06 16:00","연속"]
[38,"인천","부평","인천C/C CB 7471","인천CC S/Y 345kV 신경서-인천CC#2T/L GIS 조작시험","인천CC S/Y 345kV 신경서-인천CC#2T/L GIS 조작시험 및 절연열화 측정","2024-07-03 09:00","2024-07-03 18:00","2024-07-03 09:00","2024-07-03 18:00","연속"]
[39,"인천","시흥","신시흥#1S/S #2 M.Tr","신시흥S/S #2M.Tr 2차 GIS 베어링 교체","신시흥S/S #2M.Tr 2차 GIS 베어링 부품 교체","2024-07-03 09:00","2024-07-03 18:00","2024-07-06 09:00","2024-07-06 18:00","연속"]
[40,"인천","시흥","신시흥#1S/S #1 M.Tr","신시흥S/S 154kV Sh.R 증설공사","- 신규 #1S.Tr 기초 및 기기설치 (#1M.Tr 3차측 VCB 교체 및 Sh.R, Sh.R 용 GIS 기초타설)","2024-07-01 09:00","2024-07-31 18:00","취소","취소","연속"]
[41,"인천","시흥","신시흥#2S/S #6 M.Tr","신시흥S/S #6M.Tr 2차 GIS 조작시험","신시흥S/S #6M.Tr 2차 GIS 조작시험","2024-07-12 14:00","2024-07-12 18:00","2024-07-12 14:00","2024-07-12 18:00","연속"]
[42,"인천","직할","갈산S/S CB 7371","갈산S/S 362kV 갈산신광명#2T/L GIS 유압조작기 밸브 설치공사","갈산S/S 362kV 갈산신광명#2T/L GIS 유압조작기 밸브 설치공사(7371)","2024-07-09 09:00","2024-07-09 14:00","취소","취소","연속"]
[43,"인천","직할","갈산S/S CB 7300","갈산S/S 362kV 갈산신광명#2T/L GIS 유압조작기 밸브 설치공사","갈산S/S 362kV 갈산신광명#2T/L GIS 유압조작기 밸브 설치공사(7300)","2024-07-09 09:00","2024-07-09 14:00","취소","취소","연속"]
[44,"인천","직할","신부평S/S CB 7371","신부평S/S 서인천CC신부평#3T/L GIS 조작시험","신부평S/S 서인천CC신부평#3T/L GIS 조작시험","2024-07-03 09:00","2024-07-03 14:00","2024-07-03 09:00","2024-07-03 14:00","연속"]
[45,"경기북부","고양","신파주S/S SVC CB","2024년도 신파주S/S 345kV SVC 보통점검공사","2024년도 신파주S/S 345kV SVC 보통점검 - 공사 내용 : TCR, FC, Cooling System, C&P PNL 등 - 공사 기간 : 2024. 7. 8 ~ 2024. 8. 2","2024-07-08 09:00","2024-08-02 18:00","2024-07-08 09:00","2024-08-02 18:00","연속"]
[46,"경기북부","구리","미금S/S CB 7972","24-25년 구리전력지사 변전협력회사 총액공사","미금S/S 345kV 79BAY B/F 보호반 대체공사 - 구PNL 철거 및 신PNL 입상 - 신규 케이블 결선 - 연동시험 및 준공시험","2024-07-29 09:00","2024-08-02 18:00","2024-07-29 09:00","2024-08-02 18:00","연속"]
[47,"경기북부","구리","신가평포천LNGCC#1 T/L","신가평S/S 345kV GIS 모선 용량대체 공사","345kV #70BUS 및 51DS(7351~7851) 무부하가압","2024-07-01 09:00","2024-07-07 18:00","취소","취소","연속"]
[48,"경기북부","구리","신가평포천LNGCC#2 T/L","신가평S/S 계통보호설비 이설","신가평S/S 감시실 이설에 따른 계통보호설비 이설 - 신가평-포천LNG #2T/L 1계열 7.3 - 신가평-포천LNG #2T/L 2계열 7.4","2024-07-25 09:00","2024-07-25 18:00","취소","취소","연속"]
[49,"경기북부","구리","신가평포천LNGCC#1 T/L","신가평S/S 계통보호설비 이설","신가평S/S 감시실 이설에 따른 계통보호설비 이설 - 신가평-포천LNG #1T/L 1계열 7.1 - 신가평-포천LNG #1T/L 2계열 7.2","2024-07-24 09:00","2024-07-24 18:00","취소","취소","연속"]
[50,"경기북부","직할","신의정부S/S #4 M.Tr","24-25년도 직할 변전협력회사 총액공사","7672CB Line PT B상 DC접지 조치","2024-07-02 09:00","2024-07-02 18:00","2024-07-02 09:00","2024-07-02 18:00","연속"]
[51,"경기북부","직할","양주S/S STATCOM CB","양주S/S 345kV STATCOM 수냉각설비 점검","양주S/S 345kV STATCOM 수냉각설비 점검","2024-07-01 09:00","2024-07-05 18:00","2024-07-01 09:00","2024-07-05 18:00","연속"]
[52,"경기북부","직할","양주S/S STATCOM CB","양주S/S 345kV STATCOM 수냉각설비 점검공사","양주S/S 345kV STATCOM 수냉각설비 점검공사","2024-07-01 09:00","2024-07-05 18:00","취소","취소","연속"]
[53,"경기","동부","곤지암여주복합#2 T/L","345kV 신용인-동서울등 16개T/L 추락방지장치 설치공사","추락방지장치 설치 80기(잔여 7기)","2024-07-04 07:00","2024-07-04 18:00","취소","취소","연속"]
[54,"경기","동부","곤지암여주복합#1 T/L","345kV 신용인-동서울등 16개T/L 추락방지장치 설치공사","추락방지장치 설치 80기(잔여 18기)","2024-07-05 07:00","2024-07-05 18:00","취소","취소","연속"]
[55,"경기","동부","신제천신충주T#1 T/L","345kV 신용인-동서울등 16개T/L 추락방지장치 설치공사","추락방지장치 설치 39기","2024-07-11 07:00","2024-07-12 18:00","취소","취소","연속"]
[56,"경기","동부","신충주여주복합#2 T/L","345kV 신용인-동서울등 16개T/L 추락방지장치 설치공사","추락방지장치 설치 39기","2024-07-09 07:00","2024-07-10 18:00","취소","취소","연속"]
[57,"경기","성남","신안성S/S CB 7B71","2024년 성남전력지사 변전협력회사 총액공사","-7B79 GIS 조작시험 -7B00, 7B71, 7B79 절연열화 측정","2024-07-08 09:00","2024-07-08 18:00","2024-07-08 09:00","2024-07-08 18:00","연속"]
[58,"경기","성남","신안성S/S CB 7771","2024년 성남전력지사 변전협력회사 총액공사","-#5Sh.R 보통점검 -7779 GIS 조작시험 -7700, 7771, 7779 절연열화 측정","2024-07-02 09:00","2024-07-03 18:00","2024-07-02 09:00","2024-07-03 18:00","연속"]
[59,"경기","성남","신안성S/S CB 7700","2024년 성남전력지사 변전협력회사 총액공사","-#5Sh.R 보통점검 -7779 GIS 조작시험 -7700, 7771, 7779 절연열화 측정","2024-07-02 09:00","2024-07-03 18:00","2024-07-02 09:00","2024-07-03 18:00","연속"]
[60,"경기","성남","신안성S/S #5 Sh.R CB","2024년 성남전력지사 변전협력회사 총액공사","-#5Sh.R 보통점검 -7779 GIS 조작시험 -7700, 7771, 7779 절연열화 측정","2024-07-02 09:00","2024-07-03 18:00","2024-07-02 09:00","2024-07-03 18:00","연속"]
[61,"경기","성남","신안성S/S CB 7971","2024년 성남전력지사 변전협력회사 총액공사","-#6Sh.R 보통점검 -7979 GIS 조작시험 -7900, 7971, 7979 절연열화 측정","2024-07-04 09:00","2024-07-05 18:00","2024-07-04 09:00","2024-07-05 18:00","연속"]
[62,"경기","성남","신안성S/S CB 7900","2024년 성남전력지사 변전협력회사 총액공사","-#6Sh.R 보통점검 -7979 GIS 조작시험 -7900, 7971, 7979 절연열화 측정","2024-07-04 09:00","2024-07-05 18:00","2024-07-04 09:00","2024-07-05 18:00","연속"]
[63,"경기","성남","신안성S/S #6 Sh.R CB","2024년 성남전력지사 변전협력회사 총액공사","-#6Sh.R 보통점검 -7979 GIS 조작시험 -7900, 7971, 7979 절연열화 측정","2024-07-04 09:00","2024-07-05 18:00","2024-07-04 09:00","2024-07-05 18:00","연속"]
[64,"경기","성남","신안성S/S CB 7B00","2024년 성남전력지사 변전협력회사 총액공사","-7B79 GIS 조작시험 -7B00, 7B71, 7B79 절연열화 측정","2024-07-08 09:00","2024-07-08 18:00","2024-07-08 09:00","2024-07-08 18:00","연속"]
[65,"경기","성남","신용인S/S CB 7772","2024년 성남전력지사 변전협력회사 총액공사","-7772, 7779 절연열화 측정","2024-07-05 09:00","2024-07-05 18:00","2024-07-05 09:00","2024-07-05 18:00","연속"]
[66,"경기","성남","신용인S/S #1 Sh.R CB","2024년 성남전력지사 변전협력회사 총액공사","-7772, 7779 절연열화 측정","2024-07-05 09:00","2024-07-05 18:00","2024-07-05 09:00","2024-07-05 18:00","연속"]
[67,"경기","직할","화성신안산#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 4회선 7기","2024-07-07 12:00","2024-07-07 18:00","2024-07-07 12:00","2024-07-07 18:00","연속"]
[68,"경기","직할","화성신안산#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 4회선 7기","2024-07-06 07:00","2024-07-07 12:00","2024-07-06 07:00","2024-07-07 12:00","연속"]
[69,"충북","청주","남청주S/S #3 M.Tr","24년 345kV 주변압기 정밀점검","#3M.Tr 정밀점검","2024-07-17 09:00","2024-07-31 18:00","2024-07-17 09:00","2024-07-31 18:00","연속"]
[70,"충북","청주","남청주S/S #4 M.Tr","2024~2025년 청주전력지사 변전협력회사 공사","345kV M.Tr 1차측 부싱 초기점검 (부싱교체 관련 초기점검)","2024-07-16 09:00","2024-07-16 18:00","2024-07-16 09:00","2024-07-16 18:00","연속"]
[71,"충북","청주","남청주S/S #1 BUS","2024~2025년 청주전력지사 변전협력회사 공사","345kV GIS 균압콘덴서 절연열화 측정","2024-07-15 13:00","2024-07-15 14:00","취소","취소","연속"]
[72,"충북","청주","남청주S/S #1 M.Tr","24년 345kV 주변압기 정밀점검","#1M.Tr 정밀점검","2024-07-01 09:00","2024-07-14 18:00","2024-07-01 09:00","2024-07-14 18:00","연속"]
[73,"충북","청주","남청주S/S #2 M.Tr","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-07-02 08:00","2024-07-20 18:00","취소","취소","연속"]
[74,"충북","청주","남청주S/S #5 M.Tr","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 보통점검(#5M.Tr 2차측)","2024-07-15 09:00","2024-07-15 18:00","2024-07-15 09:00","2024-07-15 18:00","연속"]
[75,"대전세종충남","서산","신서산S/S #5 Sh.R CB","24년 서산P/O 345kV GIS 정밀점검공사","(즉시가압 불가) 신서산S/S 345kV #5Sh.R 7979 GIS 정밀점검","2024-07-01 09:30","2024-07-05 18:00","2024-07-01 09:30","2024-07-05 18:00","연속"]
[76,"대전세종충남","서산","태안T/P CB 7671","24년 서산P/O 변전협력회사 총액공사","(즉시가압 불가) 태안화력S/S 345kV 신서산-태안화력#1T/L 1차 7671CB A상 대체","2024-07-22 09:30","2024-07-26 18:00","취소","취소","연속"]
[77,"대전세종충남","천안","신온양신탕정#1 T/L","[6월취소시]345kV 신온양-신탕정T/L 추락방지장치 설치공사","[즉시가압가능]345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치 [병가철탑] 신온양신탕정#1(상단), 청양신탕정#1(하단)","2024-07-08 07:00","2024-07-12 18:00","취소","취소","매일"]
[78,"대전세종충남","천안","신온양S/S CB 7671","345kV 북당진-신탕정T/L SW증설공사","345kV 청양-신온양#2T/L 보호배전반 설치 345kV 76BAY B/F PNL 교체","2024-07-01 09:00","2024-07-12 18:00","2024-07-01 09:00","2024-07-12 18:00","연속"]
[79,"대전세종충남","천안","신온양S/S CB 7600","345kV 북당진-신탕정T/L SW증설공사","345kV 청양-신온양#2T/L 보호배전반 설치 345kV 76BAY B/F PNL 교체","2024-07-01 09:00","2024-07-12 18:00","2024-07-01 09:00","2024-07-12 18:00","연속"]
[80,"대전세종충남","천안","신탕정S/S CB 7271","신탕정S/S 345kV 7171, 7271 GIS 콘덴서 절연열화 측정","(즉시가압가능)신탕정S/S 345kV 7171, 7271 GIS 콘덴서 절연열화 측정","2024-07-04 14:00","2024-07-04 18:00","2024-07-04 14:00","2024-07-04 18:00","연속"]
[81,"대전세종충남","천안","신탕정S/S CB 7171","신탕정S/S 345kV 7171, 7271 GIS 콘덴서 절연열화 측정","(즉시가압가능)신탕정S/S 345kV 7171, 7271 GIS 콘덴서 절연열화 측정","2024-07-04 09:00","2024-07-04 14:00","2024-07-04 09:00","2024-07-04 14:00","연속"]
[82,"대전세종충남","천안","청양신탕정#1 T/L","[6월취소시]345kV 신온양-신탕정T/L 추락방지장치 설치공사","[즉시가압가능]345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치 [병가철탑] 신온양신탕정#1(상단), 청양신탕정#1(하단)","2024-07-08 07:00","2024-07-12 18:00","취소","취소","매일"]
[83,"대전세종충남","천안","신탕정S/S CB 7471","신탕정S/S 345kV 7471, 7472 GIS 콘덴서 절연열화 측정","(즉시가압가능)신탕정S/S 345kV 7471, 7472 GIS 콘덴서 절연열화 측정","2024-07-10 09:00","2024-07-10 14:00","2024-07-10 09:00","2024-07-10 14:00","연속"]
[84,"대전세종충남","천안","신탕정S/S CB 7472","신탕정S/S 345kV 7471, 7472 GIS 콘덴서 절연열화 측정","(즉시가압가능)신탕정S/S 345kV 7471, 7472 GIS 콘덴서 절연열화 측정","2024-07-10 14:00","2024-07-10 18:00","2024-07-10 14:00","2024-07-10 18:00","연속"]
[85,"대전세종충남","천안","신온양신탕정#2 T/L","[6월취소시]345kV 신온양-신탕정T/L 추락방지장치 설치공사","[즉시가압가능]345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치 [병가철탑] 신온양신탕정#2(상단), 청양신탕정#2(하단)","2024-07-15 07:00","2024-07-19 18:00","취소","취소","매일"]
[86,"대전세종충남","천안","신탕정S/S CB 7500","신탕정S/S 345kV 7500, 7571 GIS 콘덴서 절연열화 측정","(즉시가압가능)신탕정S/S 345kV 7500, 7571 GIS 콘덴서 절연열화 측정","2024-07-17 09:00","2024-07-17 14:00","2024-07-17 09:00","2024-07-17 14:00","연속"]
[87,"대전세종충남","천안","신탕정S/S CB 7571","신탕정S/S 345kV 7500, 7571 GIS 콘덴서 절연열화 측정","(즉시가압가능)신탕정S/S 345kV 7500, 7571 GIS 콘덴서 절연열화 측정","2024-07-17 14:00","2024-07-17 18:00","2024-07-17 14:00","2024-07-17 18:00","연속"]
[88,"대전세종충남","천안","청양신탕정#2 T/L","[6월취소시]345kV 신온양-신탕정T/L 추락방지장치 설치공사","[즉시가압가능]345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치 [병가철탑] 신온양신탕정#2(상단), 청양신탕정#2(하단)","2024-07-15 07:00","2024-07-19 18:00","취소","취소","매일"]
[89,"대전세종충남","청양","청양군산#2 T/L","[송전]345KV 청양군산#2T/L 애자련 보강","345KV 청양군산#1T/L 애자련 보강","2024-07-10 08:00","2024-07-12 18:00","취소","취소","연속"]
[90,"대전세종충남","청양","청양군산#1 T/L","[송전]345KV 청양군산#1T/L 가공지선 교체 및 애자련 보강","345KV 청양군산#1T/L 가공지선 교체 및 애자련 보강","2024-07-02 08:00","2024-07-09 18:00","취소","취소","연속"]
[91,"전북","군산","군산신김제#2 T/L","345kV 군산-신김제#2T/L 품질불량 의심 접속함 교체공사","345kV 군산-신김제#2T/L(D) J/B#4 A상 중간접속함 해체 및 재접속","2024-07-01 09:00","2024-07-05 18:00","2024-07-01 09:00","2024-07-05 18:00","연속"]
[92,"전북","군산","군산S/S #70 BUS","군산변전소 345kV GIS 대체공사(기기)","○ 362kV GIS 4000A 40kA × 10CB(50kA) 교체 ○ 기타 부대공사 × 1식","2024-07-16 08:00","2024-07-23 18:00","취소","취소","연속"]
[93,"전북","군산","군산S/S #1 Sh.R CB","군산변전소 345kV GIS 대체공사(기기)","○ 362kV GIS 4000A 40kA × 10CB(50kA) 교체 ○ 기타 부대공사 × 1식","2024-07-22 15:00","2024-07-23 15:00","2024-07-22 15:00","2024-07-23 15:00","연속"]
[94,"전북","군산","군산S/S #75 BUS","군산변전소 345kV GIS 대체공사(기기)","○ 362kV GIS 4000A 40kA × 10CB(50kA) 교체 ○ 기타 부대공사 × 1식","2024-07-24 08:00","2024-07-31 18:00","취소","취소","연속"]
[95,"전북","군산","군산S/S #1 Sh.R CB","군산변전소 345kV GIS 대체공사(기기)","○ 362kV GIS 4000A 40kA × 10CB(50kA) 교체 ○ 기타 부대공사 × 1식","2024-07-30 15:00","2024-07-31 15:00","2024-07-30 15:00","2024-07-31 15:00","연속"]
[96,"전북","직할","신옥천신남원#2 T/L","345kV 신옥천-신남원 등 3개T/L 수평추락방지시설 설치공사","345kV 신옥천-신남원#1T/L 1~183호","2024-07-22 07:30","2024-08-02 18:00","2024-07-22 07:30","2024-08-02 18:00","연속"]
[97,"전북","직할","신옥천신남원#1 T/L","345kV 신옥천-신남원 등 3개T/L 수평추락방지시설 설치공사","345kV 신옥천-신남원#1T/L 1~183호","2024-07-11 07:30","2024-07-21 18:00","2024-07-11 07:30","2024-07-21 18:00","연속"]
[98,"광주전남","광주","신광주S/S #2 M.Tr","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체","2024-07-01 09:00","2024-07-31 18:00","취소","취소","연속"]
[99,"광주전남","광주","신광주S/S #1 BUS","장기사용 345kV #1BUS 모선보호반 교체","장기사용 345kV #1BUS 모선보호반 교체","2024-07-01 08:00","2024-07-05 18:00","취소","취소","연속"]
[100,"광주전남","광주","신광주신화순#1 T/L","24~25년 광주전력지사 송전협력회사 총액공사","345kV 신광주-신화순#1T/L 수평 추락방지장치 설치공사(No.1~121)","2024-07-01 07:00","2024-07-12 18:00","2024-07-01 07:00","2024-07-12 18:00","매일"]
[101,"광주전남","광주","신남원신광주#1 T/L","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체","2024-07-29 13:00","2024-07-30 13:00","2024-07-29 13:00","2024-07-30 13:00","연속"]
[102,"광주전남","광주","신광주S/S #1 Sh.R CB","2024~2025년 광주전력지사 변전협력회사 공사","#1Sh.R 1차(7572) CB 조작시험 7500CB 보통점검","2024-07-23 09:00","2024-07-23 18:00","2024-07-23 09:00","2024-07-23 18:00","연속"]
[103,"광주전남","광주","신광주신화순#2 T/L","24~25년 광주전력지사 송전협력회사 총액공사","345kV 신광주-신화순#2T/L 수평 추락방지장치 설치공사(No.1~121)","2024-07-15 07:00","2024-07-26 18:00","2024-07-15 07:00","2024-07-26 18:00","매일"]
[104,"광주전남","광주","신광주S/S CB 7472","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체","2024-07-01 09:00","2024-07-31 18:00","2024-07-01 09:00","2024-07-31 18:00","연속"]
[105,"광주전남","광주","신광주S/S #2 BUS","장기사용 345kV #2BUS 모선보호반 교체","장기사용 345kV #2BUS 모선보호반 교체","2024-07-08 08:00","2024-07-12 18:00","취소","취소","연속"]
[106,"광주전남","광주","신광주S/S #3 M.Tr","24년 광주전력지사 변전협력회사 총액공사","- 76BAY 차단실패보호반 교체 - 345kV M.Tr 보통점검 - 362kV GIS 보통점검(7600) - #3M.Tr 3차 차단기 교체(3차 Main) - 3차측 DS 점검","2024-07-06 09:00","2024-07-10 18:00","취소","취소","연속"]
[107,"광주전남","광주","신광주신화순#1 T/L","24년 광주전력지사 변전협력회사 총액공사","- 76BAY 차단실패보호반 교체","2024-07-06 09:00","2024-07-10 18:00","취소","취소","연속"]
[108,"광주전남","광주","신광주S/S #1 M.Tr","2024~2025년 광주전력지사 변전협력회사 공사","-주변압기 보통점검 -7172보통점검","2024-07-02 09:00","2024-07-05 18:00","취소","취소","연속"]
[109,"광주전남","광주","신광주S/S CB 7300","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체","2024-07-01 09:00","2024-07-31 18:00","2024-07-01 09:00","2024-07-31 18:00","연속"]
[110,"광주전남","광주","신광주S/S #4 M.Tr","2024~2025년 광주전력지사 변전협력회사 공사","-주변압기 보통점검 -7800,7872 보통","2024-07-09 09:00","2024-07-12 18:00","취소","취소","연속"]
[111,"광주전남","목포","한빛2NP한빛3NP#3 T/L","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사 7C Bay 3CB 교체(71,72,00) 주말, 휴일작업 있음","2024-07-17 08:00","2024-09-13 19:00","2024-07-17 08:00","2024-09-13 19:00","연속"]
[112,"광주전남","목포","한빛#3N/P CB 7C71","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사 7C Bay 3CB 교체(71,72,00) 주말, 휴일작업 있음","2024-07-17 08:00","2024-09-13 19:00","2024-07-17 08:00","2024-09-13 19:00","연속"]
[113,"광주전남","순천","광양C/C #2 BUS","24-25년 순천전력지사 변전정비 총액공사","75BUS PT NFB 교체","2024-07-08 09:00","2024-07-08 18:00","2024-07-08 09:00","2024-07-08 18:00","연속"]
[114,"광주전남","순천","광양율촌CC T/L","광양변전소 광양율촌CC T/L(7371,7300) GIS 절연열화측정","광양변전소 광양율촌CC T/L(7371,7300) GIS 절연열화측정(즉시가압가능)","2024-07-15 08:00","2024-07-15 18:00","2024-07-15 08:00","2024-07-15 18:00","연속"]
[115,"광주전남","순천","광양S/S CB 7471","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","광양S/S 광양-여수TPT/L(7471CB) GIS 보통점검","2024-07-02 08:00","2024-07-02 18:00","2024-07-02 08:00","2024-07-02 18:00","연속"]
[116,"광주전남","순천","광양S/S CB 7171","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","광양S/S 신남원-광양#2T/L(7171CB) GIS 보통점검","2024-07-01 08:00","2024-07-01 18:00","2024-07-01 08:00","2024-07-01 18:00","연속"]
[117,"광주전남","순천","율촌CC여수TP T/L","율촌CC-여수T/P GIS 결상회로 개선","율촌CC-여수T/P GIS 결상회로 개선(즉시가압가능)","2024-07-22 09:00","2024-07-22 18:00","2024-07-22 09:00","2024-07-22 18:00","연속"]
[118,"광주전남","순천","여수T/P #75 BUS","여수화력 345kV GIS 모선 PT 회로 개선관련","PT 회로개선","2024-07-10 09:00","2024-07-10 18:00","2024-07-10 09:00","2024-07-10 18:00","연속"]
[119,"광주전남","순천","여수T/P CB 7472","여수화력 345kV GIS 모선 PT 회로 개선관련 조작시험","여수화력 345kV GIS 모선 PT 회로 개선관련 조작시험","2024-07-10 09:00","2024-07-10 18:00","2024-07-10 09:00","2024-07-10 18:00","연속"]
[120,"광주전남","순천","율촌C/C CB 7171","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","율촌C/C 광양-율촌CCT/L(7171CB) GIS 보통점검","2024-07-03 08:00","2024-07-03 18:00","2024-07-03 08:00","2024-07-03 18:00","연속"]
[121,"대구","포항","신포항S/S #4 M.Tr","신포항S/S 345kV 주변압기측 현대화 공사","신포항S/S 345kV 주변압기측 현대화 공사","2024-07-15 08:00","2024-07-23 17:00","2024-07-15 08:00","2024-07-23 17:00","연속"]
[122,"대구","달성","고령S/S #1 Sh.R CB","고령S/S 345kV #1 Sh.R 휴전","7A00,7A72,7A79 CB 균압콘덴서 측정","2024-07-12 09:00","2024-07-12 18:00","2024-07-12 09:00","2024-07-12 18:00","연속"]
[123,"대구","달성","고령S/S CB 7500","7500 CB 균압콘덴서 측정","7500 CB 균압콘덴서 측정","2024-07-10 12:00","2024-07-10 15:00","2024-07-10 12:00","2024-07-10 15:00","연속"]
[124,"대구","달성","고령S/S CB 7872","7872 CB 균압콘덴서 측정","7872 CB 균압콘덴서 측정","2024-07-10 15:00","2024-07-10 18:00","2024-07-10 15:00","2024-07-10 18:00","연속"]
[125,"대구","달성","고령의령#2 T/L","CVT대체(고령SS)","CVT대체(고령SS)","2024-07-16 09:00","2024-07-17 18:00","2024-07-16 09:00","2024-07-17 18:00","연속"]
[126,"대구","달성","고령S/S CB 7571","7571 CB 균압콘덴서 측정","7571 CB 균압콘덴서 측정","2024-07-10 09:00","2024-07-10 12:00","2024-07-10 09:00","2024-07-10 12:00","연속"]
[127,"대구","달성","고령S/S CB 7100","7100 CB 균압콘덴서 측정","7100 CB 균압콘덴서 측정","2024-07-09 14:00","2024-07-09 18:00","2024-07-09 14:00","2024-07-09 18:00","연속"]
[128,"대구","달성","고령S/S CB 7172","7172 CB 균압콘덴서 측정","7172 CB 균압콘덴서 측정","2024-07-09 09:00","2024-07-09 14:00","2024-07-09 09:00","2024-07-09 14:00","연속"]
[129,"대구","칠곡","북대구S/S CB 7472","북대구S/S 7472 GIS 조작시험","북대구S/S 7472 GIS 조작시험","2024-07-04 14:00","2024-07-04 18:00","2024-07-04 14:00","2024-07-04 18:00","연속"]
[130,"대구","칠곡","서대구S/S CB 7771","서대구S/S 7771 GCB 조작시험","서대구S/S 7771 GCB 조작시험","2024-07-03 09:00","2024-07-03 14:00","2024-07-03 09:00","2024-07-03 14:00","연속"]
[131,"대구","칠곡","서대구S/S CB 7872","서대구S/S 7872 GCB 조작시험","서대구S/S 7872 GCB 조작시험","2024-07-03 14:00","2024-07-03 18:00","2024-07-03 14:00","2024-07-03 18:00","연속"]
[132,"대구","칠곡","서대구S/S CB 7200","서대구S/S 7200 GCB 조작시험","서대구S/S 7200 GCB 조작시험","2024-07-01 14:00","2024-07-01 18:00","2024-07-01 14:00","2024-07-01 18:00","연속"]
[133,"대구","칠곡","서대구S/S CB 7572","서대구S/S 7572 GCB 조작시험","서대구S/S 7572 GCB 조작시험","2024-07-02 14:00","2024-07-02 18:00","2024-07-02 14:00","2024-07-02 18:00","연속"]
[134,"대구","칠곡","서대구S/S CB 7271","서대구S/S 7271 GCB 조작시험","서대구S/S 7271 GCB 조작시험","2024-07-01 09:30","2024-07-01 14:00","2024-07-01 09:30","2024-07-01 14:00","연속"]
[135,"대구","칠곡","서대구S/S CB 7472","서대구S/S 7472 GCB 조작시험","서대구S/S 7472 GCB 조작시험","2024-07-04 09:30","2024-07-04 14:00","2024-07-04 09:30","2024-07-04 14:00","연속"]
[136,"대구","칠곡","서대구S/S CB 7571","서대구S/S 7571 GCB 조작시험","서대구S/S 7571 GCB 조작시험","2024-07-02 09:00","2024-07-02 14:00","2024-07-02 09:00","2024-07-02 14:00","연속"]
[137,"대구","포항","신포항신영일 T/L","345kV 영포 외 15개 T/L 추락방지장치 설치 등 송전정비공사","345kV 신포항-신영일T/L 수평추락방지장치 설치","2024-07-12 07:00","2024-07-12 18:00","2024-07-12 07:00","2024-07-12 18:00","연속"]
[138,"대구","포항","선산신포항 T/L","345kV 영포 외 15개 T/L 추락방지장치 설치 등 송전정비공사","345kV 선산-신포항T/L 수평추락방지장치 설치","2024-07-17 07:00","2024-07-17 18:00","2024-07-17 07:00","2024-07-17 18:00","연속"]
[139,"대구","포항","신포항북대구 T/L","345kV 영포 외 15개 T/L 추락방지장치 설치 등 송전정비공사","345kV 신포항-북대구T/L 수평추락방지장치 설치","2024-07-18 07:00","2024-07-18 18:00","2024-07-18 07:00","2024-07-18 18:00","연속"]
[140,"대구","포항","월성N/P #71 BUS","월성N/P 연계 345kV GIS 용량대체공사(75Bay 대체)","월성N/P 연계 345kV GIS 용량대체공사 ○ 345kV GIS × 18CB 대체 ○ 보호반 설치 및 이설 ○ 제어케이블 포설 및 결선 ○ 기타 부대공사 × 1식","2024-07-06 09:00","2024-07-20 09:00","2024-07-06 09:00","2024-07-20 09:00","연속"]
[141,"대구","포항","월성N/P SEC CB 70710","2024~25년도 포항전력지사 변전총액공사","월성S/Y 70-71 GIS 조작시험","2024-07-23 09:00","2024-07-23 14:00","2024-07-23 09:00","2024-07-23 14:00","연속"]
[142,"대구","포항","월성N/P SEC CB 70710","월성N/P 연계 345kV GIS 용량대체공사(75Bay 대체)","월성N/P 연계 345kV GIS 용량대체공사 ○ 345kV GIS × 18CB 대체 ○ 보호반 설치 및 이설 ○ 제어케이블 포설 및 결선 ○ 기타 부대공사 × 1식","2024-07-19 14:00","2024-07-20 09:00","2024-07-19 14:00","2024-07-20 09:00","연속"]
[143,"대구","포항","월성N/P SEC CB 75760","2024~25년도 포항전력지사 변전총액공사","월성S/Y 75-76 GIS 조작시험","2024-07-23 14:00","2024-07-23 18:00","2024-07-23 14:00","2024-07-23 18:00","연속"]
[144,"대구","포항","월성N/P SEC CB 75760","월성N/P 연계 345kV GIS 용량대체공사(75Bay 대체)","월성N/P 연계 345kV GIS 용량대체공사 ○ 345kV GIS × 18CB 대체 ○ 보호반 설치 및 이설 ○ 제어케이블 포설 및 결선 ○ 기타 부대공사 × 1식","2024-07-01 14:00","2024-07-02 09:00","2024-07-01 14:00","2024-07-02 09:00","연속"]
[145,"경북","직할","신영일안동CC T/L","청송면봉산 풍력발전단지 연계 송전선로 건설공사","○ 작업내용 : 345kV 영포T/L No.198,201 철탑보강에 따른 자재 실측","2024-07-09 08:00","2024-07-10 18:00","2024-07-06 08:00","2024-07-07 18:00","연속"]
[146,"경북","직할","신포항청송PP T/L","청송면봉산 풍력발전단지 연계 송전선로 건설공사","○ 작업내용 : 345kV 영포T/L No.198,201 철탑보강에 따른 자재 실측","2024-07-11 08:00","2024-07-12 18:00","2024-07-13 08:00","2024-07-14 18:00","연속"]
[147,"경남","진주","신남원의령#2 T/L","OPGW 취약개소 금구류 정비공사","신남원-의령T/L 11호 등 8개소 금구류 정비 - 현수클램프 교체 5개소 - 내장클램프 교체 1개소 - SB댐퍼 교체 2개소","2024-07-04 07:00","2024-07-04 18:00","2024-07-04 07:00","2024-07-04 18:00","연속"]
[148,"강원",null,"양양P/P #1호기 주변압기 (CB 7100, 7172)","#1,2 계획중간정비","#1,2 Main Tr. No Load 냉각수 배관 교체","2024-07-02 09:00","2024-07-03 23:59","2024-07-02 09:00","2024-07-03 23:59","연속"]
[149,"강원",null,"양양P/P #2호기 주변압기 (CB 7271, 7200)","#1,2 계획중간정비","#1,2 Main Tr. No Load 냉각수 배관 교체","2024-07-02 09:00","2024-07-03 23:59","2024-07-02 09:00","2024-07-03 23:59","연속"]
[150,"강원",null,"양양P/P #3호기 주변압기 (CB 7200, 7272)","#3 계획중간정비","#3 주변압기 점검","2024-07-26 09:00","2024-07-26 18:00","2024-07-26 09:00","2024-07-26 18:00","연속"]

{"sheet":"154설비","index":2,"n_rows":135,"n_cols":11,"rows_kept":135,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2024년도 7월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","구의광장#2 T/L","2024년 성동P/O 170kV GIS 정밀점검","- 170kV GIS 정밀점검","2024-07-01 09:00","2024-07-02 18:00","2024-07-01 09:00","2024-07-02 18:00","연속"]
[2,"서울","성동","성수뚝도#1 T/L","2024년 성동P/O 170kV GIS 정밀점검","- 170kV GIS 정밀점검","2024-07-03 09:00","2024-07-04 18:00","취소","취소","연속"]
[3,"서울","성동","성수뚝도#2 T/L","2024년 성동P/O 170kV GIS 정밀점검","- 170kV GIS 정밀점검","2024-07-05 09:00","2024-07-06 18:00","취소","취소","연속"]
[4,"인천","김포","신김포S/S CB 6100","신김포S/S 154kV #60-#65 BUS TIE GIS 보통점검","신김포S/S 154kV #60-#65 BUS TIE GIS 보통점검 (6100)","2024-07-01 10:00","2024-07-01 18:00","취소","취소","연속"]
[5,"인천","시흥","서시화S/S KGETS T/L CB","서시화S/S 코어엔텍T/L GIS 조작시험","서시화S/S 코어엔텍T/L GIS 조작시험","2024-07-12 09:00","2024-07-12 14:00","취소","취소","연속"]
[6,"인천","시흥","신시흥S/S CB 6100","신시흥S/S 154kV 6100 B/T GIS 조작시험","신시흥S/S 154kV 6100(60-65) B/T GIS 조작시험","2024-07-10 09:00","2024-07-10 12:00","취소","취소","연속"]
[7,"인천","시흥","신시흥S/S SEC CB 66670","신시흥S/S 154kV 66-67 Sec. GIS 보통점검","신시흥S/S 154kV 66-67 Sec. GIS 보통점검","2024-07-09 15:00","2024-07-09 18:00","취소","취소","연속"]
[8,"인천","시흥","신시흥S/S SEC CB 65660","신시흥S/S 154kV 65-66 Sec. GIS 조작시험","신시흥S/S 154kV 65-66 Sec. GIS 조작시험","2024-07-09 12:00","2024-07-09 15:00","취소","취소","연속"]
[9,"인천","시흥","신시흥S/S SEC CB 60610","신시흥S/S 154kV 60-61 Sec. GIS 조작시험","신시흥S/S 154kV 60-61 Sec. GIS 조작시험","2024-07-09 09:00","2024-07-09 12:00","취소","취소","연속"]
[10,"인천","시흥","신시흥S/S CB 6300","신시흥S/S 154kV 6300 B/T GIS 보통점검","신시흥S/S 154kV 6300(62-67) B/T GIS 보통점검 - 전자변 교체","2024-07-10 15:00","2024-07-10 18:00","취소","취소","연속"]
[11,"인천","시흥","신시흥S/S CB 6400","신시흥S/S 154kV 6400 B/T GIS 조작시험","신시흥S/S 154kV 6400(63-68) B/T GIS 조작시험","2024-07-10 12:00","2024-07-10 15:00","취소","취소","연속"]
[12,"경기","군포","화성남양#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 7기 345kV 화성-신안산T/L 4회선 병가선로","2024-07-07 12:00","2024-07-07 18:00","취소","취소","연속"]
[13,"경기","군포","화성남양#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 7기 345kV 화성-신안산T/L 4회선 병가선로","2024-07-06 07:00","2024-07-07 12:00","취소","취소","연속"]
[14,"경기","동부","곤지암S/S #62 BUS","곤지암S/S 154kV #65M.Tr 증설공사","#65M.Tr 무부하가압(#1DS부 상확인)","2024-07-16 09:00","2024-07-16 13:00","취소","취소","연속"]
[15,"경기","동부","곤지암S/S #67 BUS","곤지암S/S 154kV #65M.Tr 증설공사","#65M.Tr 무부하가압(#2DS부 상확인)","2024-07-16 13:00","2024-07-17 18:00","취소","취소","연속"]
[16,"경기","동부","곤지암이천#2 T/L","곤지암S/S 154kV #65M.Tr 증설공사","#65M.Tr 무부하가압","2024-07-16 09:00","2024-07-17 18:00","취소","취소","연속"]
[17,"경기","성남","신성남정자#1 T/L","2024년 성남전력 변전협력회사 총액공사","-인출 ES 조작 불가로 조작기 교체","2024-07-01 09:00","2024-07-01 18:00","취소","취소","연속"]
[18,"경기","직할","화성수촌#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 3기 154kV 화성-마도, 154kV 화성-발안T/L 6회선 병가선로","2024-07-13 07:00","2024-07-13 18:00","취소","취소","연속"]
[19,"경기","직할","화성발안#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 3기 154kV 화성-마도, 154kV 화성-발안T/L 6회선 병가선로","2024-07-13 07:00","2024-07-13 18:00","취소","취소","연속"]
[20,"경기","직할","화성장덕 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 3기 154kV 화성-장덕, 154kV 화성-발안T/L 6회선 병가선로","2024-07-13 07:00","2024-07-13 18:00","취소","취소","연속"]
[21,"경기","직할","화성마도 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 3기 154kV 화성-수촌, 154kV 화성-발안T/L 6회선 병가선로","2024-07-14 07:00","2024-07-14 18:00","취소","취소","연속"]
[22,"경기","직할","화성수촌#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 3기 154kV 화성-마도, 154kV 화성-발안T/L 6회선 병가선로","2024-07-14 07:00","2024-07-14 18:00","취소","취소","연속"]
[23,"경기","직할","화성발안#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 3기 154kV 화성-마도, 154kV 화성-발안T/L 6회선 병가선로","2024-07-14 07:00","2024-07-14 18:00","취소","취소","연속"]
[24,"경기","평택","고덕S/S #66 BUS","평택 브레인시티 지중화공사","○ 대상선로 : 154KV 고덕-진위#1,2T/L ○ 공사구간 : J/B#7 ~ 도일C/T ○ 공사규모 : 154kV XLPE 2,500㎟, 2회선 4.9km","2024-07-01 10:00","2024-07-02 10:00","2024-07-01 10:00","2024-07-02 10:00","연속"]
[25,"강원","강릉","속초간성#1 T/L","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","무부하 시험가압","2024-06-10 09:00","2024-06-11 18:00","2024-07-04 09:00","2024-07-05 18:00","연속"]
[26,"강원","강릉","속초간성#1 T/L","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","무부하 시험가압","2024-07-18 09:00","2024-07-19 18:00","2024-07-18 09:00","2024-07-19 18:00","연속"]
[27,"충북","청주","남청주S/S #67 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체","2024-07-24 14:00","2024-07-29 14:00","취소","취소","연속"]
[28,"충북","청주","남청주오송#1 T/L","남청주S/S 154kV 장기사용 GIS 대체공사(2차)","#66-67 SEC GIIS 대체 (무부하가압용)","2024-07-28 14:00","2024-07-29 14:00","취소","취소","연속"]
[29,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체","2024-07-29 14:00","2024-07-31 18:00","취소","취소","연속"]
[30,"충북","청주","남청주청주#1 T/L","남청주S/S 154kV 장기사용 GIS 대체공사(2차)","#66-67 SEC GIIS 대체 (무부하가압용)","2024-07-30 14:00","2024-07-31 14:00","취소","취소","연속"]
[31,"충북","청주","남청주청주#1 T/L","남청주S/S 154kV 장기사용 GIS 대체공사(2차)","#66-67 SEC GIIS 대체 (무부하가압용)","2024-07-23 14:00","2024-07-24 14:00","취소","취소","연속"]
[32,"충북","청주","남청주S/S SEC CB 67660","남청주S/S 154kV 장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체","2024-07-23 08:00","2024-07-31 18:00","취소","취소","연속"]
[33,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체","2024-07-23 08:00","2024-07-24 14:00","취소","취소","연속"]
[34,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-07-13 14:00","2024-07-20 18:00","취소","취소","연속"]
[35,"충북","청주","남청주S/S #61 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-07-05 14:00","2024-07-13 14:00","취소","취소","연속"]
[36,"충북","청주","남청주청주#2 T/L","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-07-02 08:00","2024-07-20 18:00","취소","취소","연속"]
[37,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-07-02 08:00","2024-07-05 14:00","취소","취소","연속"]
[38,"충북","청주","남청주청주#4 T/L","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체(고장전류 저감 관련)","2024-07-02 08:00","2024-07-20 18:00","취소","취소","연속"]
[39,"대전세종충남","대전","팔봉두마#1 T/L","154kV 팔봉-두마T/L No.67~109 선종교체공사","선종교체공사 안전이격 휴전","2024-07-22 07:00","2024-07-26 18:00","2024-07-22 07:00","2024-07-26 18:00","연속"]
[40,"대전세종충남","대전","팔봉두마#2 T/L","154kV 팔봉-두마T/L 용량증대 전선교체공사","공사구간 : 154kV 팔봉-두마T/L No.67~109 공사내용 : ACSR 240㎟ → ASCC/TW 310㎟ x S x 2C, 15km 전선교체 저지상고 및 취약 철탑 교체 6기","2024-07-11 07:00","2024-08-09 18:00","2024-07-11 07:00","2024-08-09 18:00","연속"]
[41,"대전세종충남","대전","신계룡은진#1 T/L","154kV 팔봉-두마T/L No.67~109 선조교체공사","No.106~108 구간 안전이격 휴전","2024-07-15 07:00","2024-07-19 18:00","2024-07-15 07:00","2024-07-19 18:00","매일"]
[42,"대전세종충남","대전","추부금산#1 T/L","[송전][즉시가압O]345kV 신옥천-청양등8개T/L 추락방지설치공사","[송전][주말작업제외][즉시가압O] 345kV 신옥천-청양 등 8개T/L 철탑 추락방지시설 설치공사","2024-07-18 07:00","2024-08-07 18:00","취소","취소","매일"]
[43,"대전세종충남","대전","신옥천추부#2 T/L","[송전][즉시가압O]345kV신옥천-청양등8개T/L 추락방지설치공사","[송전][주말작업제외][즉시가압가능] 345kV 신옥천-청양 등 8개T/L 철탑 추락방지시설 설치공사","2024-07-15 07:00","2024-07-23 18:00","취소","취소","매일"]
[44,"대전세종충남","대전","추부S/S CB 6100","추부S/S 154kV #3M.Tr 증설공사","- 154kV M.Tr * 1Bank 설치 - 154kV GIS * 1CCT 설치 - 23kV GIS * 3CCT 설치","2024-07-12 09:00","2024-07-12 18:00","취소","취소","연속"]
[45,"대전세종충남","대전","추부S/S #2 BUS","추부S/S 154kV #3M.Tr 증설공사","- 154kV M.Tr * 1Bank 설치 - 154kV GIS * 1CCT 설치 - 23kV GIS * 3CCT 설치","2024-07-15 15:00","2024-07-16 18:00","취소","취소","연속"]
[46,"대전세종충남","대전","추부S/S #1 BUS","추부S/S 154kV #3M.Tr 증설공사","- 154kV M.Tr * 1Bank 설치 - 154kV GIS * 1CCT 설치 - 23kV GIS * 3CCT 설치","2024-07-15 09:00","2024-07-15 15:00","취소","취소","연속"]
[47,"대전세종충남","대전","신옥천추부#1 T/L","추부S/S 154kV #3M.Tr 증설공사","- 154kV M.Tr * 1Bank 설치 - 154kV GIS * 1CCT 설치 - 23kV GIS * 3CCT 설치","2024-07-15 09:00","2024-07-16 18:00","취소","취소","연속"]
[48,"대전세종충남","대전","추부S/S CB 6100","추부S/S 154kV #3M.Tr 증설공사","- 154kV M.Tr * 1Bank 설치 - 154kV GIS * 1CCT 설치 - 23kV GIS * 3CCT 설치","2024-07-15 09:00","2024-07-16 18:00","취소","취소","연속"]
[49,"대전세종충남","서산","석문당진화력#1 T/L","서산P/O 효성제 170kV GIS 베어링 교체공사","(6월 휴전신청 취소시) (즉시가압 가능) 당진화력S/S 154kV 석문-당진화력T/L 617 CB 베어링 교체 (병행) 석문S/S 154kV 석문-당진화력#1T/L IED 성능개선 (병행) 석문S/S 154kV 석문-당진화력#1T/L 617 CB 보통점검 (병행) 당진화력S/S 154kV 석문-당진화력#1T/L 617CB 보통점검","2024-07-01 09:30","2024-07-02 18:00","취소","취소","매일"]
[50,"대전세종충남","서산","석문당진화력#2 T/L","서산P/O 효성제 170kV GIS 베어링 교체공사","(6월 휴전신청 취소시) (즉시가압 가능) 당진화력S/S 154kV 석문-당진화력#2T/L 627 CB 베어링 교체 (병행) 석문S/S 154kV 석문-당진화력#2T/L IED 성능개선 (병행) 석문S/S 154kV 석문-당진화력#2T/L 687 CB 보통점검 (병행) 당진화력S/S 154kV 석문-당진화력#2T/L 627 CB 보통점검","2024-07-03 09:00","2024-07-04 18:00","취소","취소","매일"]
[51,"전북","군산","동군산군산CC#3 T/L","군산P/O 154kV 이상 차단기 보통점검공사","군산P/O 154kV 이상 차단기 보통점검공사","2024-07-02 09:00","2024-07-02 18:00","2024-07-02 09:00","2024-07-02 18:00","연속"]
[52,"전북","군산","군산서군산#2 T/L","군산P/O 170kV GIS 정밀점검 공사","군산S/S 군산-서군산#2T/L GIS 정밀점검공사","2024-07-01 09:00","2024-07-02 18:00","2024-07-01 09:00","2024-07-02 18:00","연속"]
[53,"전북","군산","내초군장#1 T/L","군산P/O 170kV GIS정밀점검공사(6233 #2BUS 무부하가압용)","6233 차단기 정밀점검 #2BUS 무부하 가압용","2024-07-13 17:00","2024-07-13 18:00","2024-07-13 17:00","2024-07-13 18:00","연속"]
[54,"전북","군산","내초군장#1 T/L","군산P/O 170kV GIS정밀점검공사(6233 #1BUS 무부하가압용)","6233 차단기 정밀점검 #1BUS 무부하 가압용","2024-07-12 17:00","2024-07-12 18:00","2024-07-12 17:00","2024-07-12 18:00","연속"]
[55,"전북","군산","내초군장#1 T/L","군산P/O 170kV GIS정밀점검공사(6133 #2BUS 무부하가압용)","6133 차단기 정밀점검 #2BUS 무부하 가압용","2024-07-10 17:00","2024-07-10 18:00","2024-07-10 17:00","2024-07-10 18:00","연속"]
[56,"전북","군산","내초군장#1 T/L","군산P/O 170kV GIS정밀점검공사(6133 #1BUS 무부하가압용)","6133 차단기 정밀점검 #1BUS 무부하 가압용","2024-07-09 17:00","2024-07-09 18:00","2024-07-09 17:00","2024-07-09 18:00","연속"]
[57,"전북","군산","군산동군산#1 T/L","군산P/O 170kV GIS 정밀점검공사(무부하 가압용)","동군산S/S 6333 차단기 정밀점검","2024-07-04 17:00","2024-07-04 18:00","취소","취소","연속"]
[58,"전북","김제","정주부안#1 T/L","154kV 정주-고창 등 2개T/L 선종교체공사","- 공사구간 : 154kV 정주-고창T/L No.1~17(병가구간) - 전력선 교체 : 44.076C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, 현수클램프 등]","2024-07-26 07:30","2024-07-27 18:00","2024-08-15 08:00","2024-08-16 17:00","매일"]
[59,"전북","김제","정주부안#2 T/L","154kV 정주-고창 등 2개T/L 선종교체공사","- 공사구간 : 154kV 정주-고창T/L No.17~22 (병가구간) - 전력선 교체 : 44.076C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, 현수클램프 등]","2024-07-07 07:30","2024-07-08 18:00","2024-07-27 08:00","2024-07-28 17:00","매일"]
[60,"전북","김제","정주부안#1 T/L","154kV 정주-고창 등 2개T/L 선종교체공사","- 공사구간 : 154kV 정주-고창T/L No.1~17(병가구간) - 전력선 교체 : 44.076C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, 현수클램프 등]","2024-07-07 07:30","2024-07-20 18:00","2024-07-27 08:00","2024-08-09 17:00","연속"]
[61,"전북","김제","정주고창#2 T/L","154kV 정주-고창 등 2개T/L 선종교체공사","- 공사구간 : 154kV 정주-고창T/L No.17~22 (병가구간) - 전력선 교체 : 44.076C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, 현수클램프 등]","2024-07-21 07:00","2024-08-29 18:00","2024-08-10 08:00","2024-09-26 17:00","연속"]
[62,"전북","김제","정주부안#2 T/L","154kV 정주-고창 등 2개T/L 선종교체공사","- 공사구간 : 154kV 정주-고창T/L No.17~22 (병가구간) - 전력선 교체 : 44.076C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, 현수클램프 등]","2024-07-21 07:30","2024-08-01 18:00","2024-08-10 08:00","2024-08-21 17:00","연속"]
[63,"전북","직할","남원임실#1 T/L","'24년 가공송전 순시점검 위탁공사","154kV 남원-임실T/L OPGW 부적합 개소 정비","2024-07-09 09:00","2024-07-09 18:00","2024-07-09 09:00","2024-07-09 18:00","연속"]
[64,"전북","직할","북전주봉동#2 T/L","24-25 전북직할 변전협력회사 공사","154kV GIS 보통점검","2024-07-04 09:00","2024-07-04 18:00","2024-07-04 09:00","2024-07-04 18:00","연속"]
[65,"전북","직할","왕궁봉동#1 T/L","24-25 전북직할 변전협력회사 공사","154kV GIS 보통점검","2024-07-01 09:00","2024-07-01 18:00","2024-07-01 09:00","2024-07-01 18:00","연속"]
[66,"전북","직할","왕궁봉동#2 T/L","24-25 전북직할 변전협력회사 공사","154kV GIS 보통점검","2024-07-02 09:00","2024-07-02 18:00","2024-07-02 09:00","2024-07-02 18:00","연속"]
[67,"전북","직할","북전주봉동#1 T/L","24-25 전북직할 변전협력회사 공사","154kV GIS 보통점검","2024-07-03 09:00","2024-07-03 18:00","2024-07-03 09:00","2024-07-03 18:00","연속"]
[68,"전북","직할","진안장수#1 T/L","진안-장수#1T/L 송전선로 보호반 대체공사","진안-장수#1T/L 송전선로 보호반 대체공사","2024-07-15 09:00","2024-07-19 18:00","취소","취소","연속"]
[69,"전북","직할","진안장수#2 T/L","진안-장수#2T/L 송전선로 보호반 대체공사","진안-장수#2T/L 송전선로 보호반 대체공사","2024-07-22 09:00","2024-07-26 18:00","취소","취소","연속"]
[70,"전북","직할","신김제전주#1 T/L","24-25 전북직할 변전협력회사 공사","154kV GIS 보통점검","2024-07-08 09:00","2024-07-08 18:00","2024-07-08 09:00","2024-07-08 18:00","연속"]
[71,"전북","직할","북전주진안 T/L","24년 전북본부 직할 154kV 차단기 정밀점검 공사","24년 전북본부 직할 154kV 차단기 정밀점검 공사 - 진안변전소 1M.Tr 6133 GIS 정밀점검 - 무부하 가압용 선로 : 북전주-진안TL","2024-07-16 17:30","2024-07-16 18:00","2024-07-16 17:30","2024-07-16 18:00","연속"]
[72,"광주전남","강진","완도완도CS T/L","남창-완도CS 등 2개 T/L OPGW 불량구간 교체","남창-완도C/S, 완도C/S-완도 OPGW 불량구간 교체 관련 근거 : 광전본(전자)-7780","2024-07-08 09:00","2024-07-16 18:00","취소","취소","연속"]
[73,"광주전남","강진","남창완도CS T/L","남창-완도CS 등 2개 T/L OPGW 불량구간 교체","남창-완도C/S, 완도C/S-완도 OPGW 불량구간 교체 관련근거 : 광전본(전자)-7780","2024-07-08 09:00","2024-07-16 18:00","취소","취소","연속"]
[74,"광주전남","강진","해남진도#1 T/L","22~23년 철탑추락방지장치 설치공사","22~23년 철탑추락방지장치 설치공사(수평) 작업대상 : 1,4~74,87~95,102~104호 83기","2024-07-01 08:00","2024-07-11 18:00","2024-07-01 08:00","2024-07-11 18:00","매일"]
[75,"광주전남","광주","신광주계림#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","신광주, 계림S/S 신광주-계림#2T/L PNL 대체","2024-07-15 09:00","2024-07-19 18:00","취소","취소","연속"]
[76,"광주전남","목포","안좌읍동#1 T/L CB","154kV 읍동개폐소 건설사업","○170kV GIS 5CCT 설치","2024-07-30 09:00","2024-07-31 18:00","취소","취소","연속"]
[77,"광주전남","목포","나주엄다#2 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","154kV BUS-TIE 교체로 인한 #1BUS 모선절체용","2024-07-04 14:00","2024-07-04 14:30","2024-07-04 14:00","2024-07-04 14:30","연속"]
[78,"광주전남","목포","엄다S/S #2 BUS","엄다S/S 154kV 이하 장기사용 GIS 교체공사","엄다-목포#2T/L, BUS-TIE #2BUS, #2DS측 설치","2024-07-04 14:00","2024-07-22 10:00","2024-07-04 14:00","2024-07-22 10:00","연속"]
[79,"광주전남","목포","엄다무안햇빛#2 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","154kV BUS-TIE 교체로 인한 #1BUS 모선절체용","2024-07-04 14:00","2024-07-04 14:30","2024-07-04 14:00","2024-07-04 14:30","연속"]
[80,"광주전남","목포","나주엄다#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","엄다-목포#2T/L, BUS-TIE 교체분 GIS 무부하가압용","2024-07-03 14:00","2024-07-04 15:00","2024-07-03 14:00","2024-07-04 15:00","연속"]
[81,"광주전남","목포","엄다무안햇빛#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","154kV BUS-TIE 교체로 인한 #1BUS 모선절체용","2024-07-04 14:00","2024-07-04 14:30","2024-07-04 14:00","2024-07-04 14:30","연속"]
[82,"광주전남","목포","엄다목포#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","154kV BUS-TIE 교체로 인한 #1BUS 모선절체용","2024-07-04 14:00","2024-07-04 14:30","2024-07-04 14:00","2024-07-04 14:30","연속"]
[83,"광주전남","목포","나주엄다#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","엄다-목포#2T/L, BUS-TIE 교체분 GIS 무부하가압용","2024-07-19 10:00","2024-07-20 10:00","2024-07-19 10:00","2024-07-20 10:00","연속"]
[84,"광주전남","목포","나주엄다#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","엄다-목포#2T/L, BUS-TIE 교체분 GIS 무부하가압용","2024-07-22 15:00","2024-07-22 17:00","2024-07-22 15:00","2024-07-22 17:00","연속"]
[85,"광주전남","목포","엄다S/S #1 BUS","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","엄다-목포#1T/L, #3M.Tr GIS #1DS, 상부모선, CB철거작업","2024-07-25 09:00","2024-08-14 18:00","2024-07-25 09:00","2024-08-14 18:00","연속"]
[86,"광주전남","목포","엄다목포#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","엄다-목포#1T/L GIS 교체작업","2024-07-23 09:00","2024-09-10 18:00","2024-07-23 09:00","2024-09-10 18:00","연속"]
[87,"광주전남","순천","곡성구례#2 T/L","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","구례S/S 곡성-구례#1,2T/L GIS 보통점검","2024-07-04 14:00","2024-07-04 18:00","취소","취소","연속"]
[88,"광주전남","순천","곡성구례#1 T/L","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","구례S/S 곡성-구례#1,2T/L GIS 보통점검","2024-07-04 09:00","2024-07-04 14:00","취소","취소","연속"]
[89,"광주전남","순천","광양백운#2 T/L","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","백운S/S 광양-백운#1,2T/L GIS 보통점검","2024-07-05 14:00","2024-07-05 18:00","2024-07-05 14:00","2024-07-05 18:00","연속"]
[90,"광주전남","순천","광양백운#1 T/L","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","백운S/S 광양-백운#1,2T/L GIS 보통점검","2024-07-05 09:00","2024-07-05 14:00","2024-07-05 09:00","2024-07-05 14:00","연속"]
[91,"광주전남","순천","순천승주#1 T/L","순천-승주#1T/L 보호계전기 성능개선(세니온제)","순천-승주#1T/L 보호계전기 성능개선(세니온제)(즉시가압불가)","2024-07-11 09:00","2024-07-11 18:00","2024-07-11 09:00","2024-07-11 18:00","연속"]
[92,"광주전남","순천","광양순천#2 T/L","광양-순천#2T/L 보호계전기 성능개선(세니온제)","광양-순천#2T/L 보호계전기 성능개선(세니온제)(즉시가압불가","2024-07-02 09:00","2024-07-02 18:00","2024-07-02 09:00","2024-07-02 18:00","연속"]
[93,"광주전남","순천","광양순천#1 T/L","광양-순천#1T/L 보호계전기 성능개선(세니온제)","광양-순천#1T/L 보호계전기 성능개선(세니온제)(즉시가압불가)","2024-07-01 09:00","2024-07-01 18:00","2024-07-01 09:00","2024-07-01 18:00","연속"]
[94,"광주전남","순천","승주S/S CB 6100","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","승주S/S #6100 BUS-TIE GIS 보통점검","2024-07-08 09:00","2024-07-08 18:00","2024-07-08 09:00","2024-07-08 18:00","연속"]
[95,"광주전남","순천","용성여수산단#2 T/L","24-25년 순천전력지사 변전총액공사","여수산단 용성여수산단#2 T/L #2DS 가스누기조치","2024-07-24 09:00","2024-07-25 18:00","취소","취소","연속"]
[96,"광주전남","순천","여수TP여천#1 T/L","154kV 여수TP-여천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-07-16 07:00","2024-07-17 18:00","취소","취소","매일"]
[97,"광주전남","순천","여수T/P #65 BUS","GS 칼텍스 여수#2T/L #2DS 가스누기해소 공사","#2DS 가스누기해소 공사","2024-07-11 09:00","2024-07-12 18:00","취소","취소","연속"]
[98,"광주전남","순천","호남TP여수TP#2 T/L","154kV 호남TP-여수TPT/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-07-03 07:00","2024-07-04 18:00","취소","취소","매일"]
[99,"광주전남","순천","호남TP여수TP#1 T/L","154kV 호남TP-여수TPT/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-07-01 07:00","2024-07-02 18:00","취소","취소","매일"]
[100,"광주전남","순천","여수TP여천#2 T/L","154kV 여수TP-여천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-07-18 07:00","2024-07-19 18:00","취소","취소","매일"]
[101,"광주전남","순천","여수T/P SEC CB 65660","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-07-19 15:00","2024-07-19 15:20","취소","취소","연속"]
[102,"광주전남","순천","여수T/P SEC CB 60610","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-07-19 15:20","2024-07-19 15:40","취소","취소","연속"]
[103,"광주전남","순천","여수T/P CB 6200","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-07-26 15:40","2024-07-26 16:00","취소","취소","연속"]
[104,"광주전남","순천","여수T/P SEC CB 65660","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-07-26 15:00","2024-07-26 15:20","취소","취소","연속"]
[105,"광주전남","순천","여수T/P CB 6100","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-07-19 15:40","2024-07-19 16:00","취소","취소","연속"]
[106,"광주전남","순천","여수T/P SEC CB 60610","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-07-26 15:20","2024-07-26 15:40","취소","취소","연속"]
[107,"광주전남","순천","용성여수산단#2 T/L","154kV 용성-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-07-24 07:00","2024-07-25 18:00","취소","취소","매일"]
[108,"광주전남","순천","용성여수산단#1 T/L","154kV 용성-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-07-22 07:00","2024-07-23 18:00","취소","취소","매일"]
[109,"광주전남","순천","여수TP용성#1 T/L","용성S/S 여수TP-용성#1T/L GIS 불량 유압력계 교체","GIS 불량 유압력계 교체","2024-07-01 09:00","2024-07-02 18:00","취소","취소","연속"]
[110,"광주전남","순천","율촌여수산단#1 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-07-08 07:00","2024-07-10 18:00","취소","취소","매일"]
[111,"광주전남","순천","율촌여수산단#2 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-07-11 07:00","2024-07-15 18:00","취소","취소","매일"]
[112,"광주전남","순천","순천율촌#1 T/L","순천-율촌#1T/L 가스누기조치","율촌S/S 순천-율촌#1T/L 가스누기조치(즉시가압 불가)","2024-07-09 09:00","2024-07-10 18:00","2024-07-09 09:00","2024-07-10 18:00","연속"]
[113,"광주전남","순천","율촌S/S #66 BUS","순천-율촌#1T/L 가스누기조치","율촌S/S 순천-율촌#1T/L 가스누기조치(즉시가압불가)","2024-07-09 09:00","2024-07-10 18:00","2024-07-09 09:00","2024-07-10 18:00","연속"]
[114,"대구","달성","강창성서#1 T/L","강창성서#1 T/L 양단 차단기동작특성시험","강창성서#1 T/L 양단 차단기동작특성시험","2024-07-23 09:00","2024-07-23 18:00","2024-07-23 09:00","2024-07-23 18:00","연속"]
[115,"대구","달성","강창다사 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 왜관-다사T/L 수평 추락방지장치 설치공사(강창-다사 병가선로)(안전확보)","2024-07-02 07:00","2024-07-03 18:00","2024-07-02 07:00","2024-07-03 18:00","연속"]
[116,"대구","달성","달서와룡#2 T/L","GIS 하자(와룡), GIS 초기(달서)","GIS 하자(와룡), GIS 초기(달서)","2024-07-31 09:00","2024-07-31 18:00","취소","취소","연속"]
[117,"대구","달성","달서와룡#1 T/L","GIS 보통(와룡), GIS 초기(달서)","GIS 보통(와룡), GIS 초기(달서)","2024-07-30 09:00","2024-07-30 18:00","취소","취소","연속"]
[118,"대구","달성","대구봉덕#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 대구-봉덕T/L 수평 추락방지장치 설치공사","2024-07-04 07:00","2024-07-08 18:00","취소","취소","연속"]
[119,"대구","달성","대구봉덕#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 대구-봉덕#2T/L 수평 추락방지장치 설치공사","2024-07-09 07:00","2024-07-11 18:00","취소","취소","연속"]
[120,"대구","달성","상인봉덕#1 T/L","154kV 상인-봉덕 지중T/L 지장송전선로 이설공사","154kV 상인-봉덕 지중T/L 지장송전선로 이설공사","2024-07-24 09:00","2024-08-13 18:00","취소","취소","연속"]
[121,"대구","직할","범물남대구#1 T/L","범물-남대구#1T/L GIS 초기점검","범물-남대구#1T/L GIS 초기점검","2024-07-17 09:30","2024-07-17 18:00","취소","취소","연속"]
[122,"대구","칠곡","농소김천#2 T/L","154kV 김천S/S 현대화공사","○ 농소-김천#2T/L 송전선로 인출변경","2024-07-15 08:00","2024-07-16 18:00","2024-07-15 08:00","2024-07-16 18:00","연속"]
[123,"대구","포항","영일포항#1 T/L","24년 포항전력지사 가공송전 순시점검 위탁공사","초기점검","2024-07-12 09:00","2024-07-12 12:00","2024-07-12 09:00","2024-07-12 12:00","연속"]
[124,"대구","포항","영일포항#2 T/L","24년 포항전력지사 가공송전 순시점검 위탁공사","초기점검","2024-07-12 13:00","2024-07-12 17:00","2024-07-12 13:00","2024-07-12 17:00","연속"]
[125,"경북","직할","진보S/S 영양풍력T/L CB","24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검","2024-07-23 09:00","2024-07-23 18:00","2024-07-23 09:00","2024-07-23 18:00","연속"]
[126,"경북","직할","안동풍산 T/L","154㎸ 안동-풍산T/L 29~31호간 지장이설공사(요청자 직접시행)","1. 대상선로 : 154㎸ 안동-풍산 송전선로 2. 공사구간 : No.29 ～ No.31(HSTACIR/AW 240㎟(단도체), 1회선) 3. 공사내역 : 송전선로 신설 및 철거(신설 No.31, 철거 기설 No.30, 31)","2024-07-11 09:00","2024-07-14 18:00","2024-07-11 09:00","2024-07-14 18:00","연속"]
[127,"부산울산","북부산","양산삼랑진PP T/L","24-25년 북부산전력지사 변전총액공사","삼랑진S/Y 154kV 양산-삼랑진PPT/L GIS 가스누기","2024-07-01 09:00","2024-07-02 18:00","취소","취소","연속"]
[128,"부산울산","울산","신울산언양#1 T/L","신울산S/S 154kV 현대화공사","인출포스트 및 빔 구조검토 현척","2024-07-01 09:00","2024-07-01 13:00","2024-07-01 09:00","2024-07-01 13:00","연속"]
[129,"부산울산","울산","언양산막#1 T/L","154kV 석계분기T/L 건설공사","지지물 : 154kV 산형강철탑 5기 전력선 : ACSR 410 * 2B * 4C","2024-07-15 07:00","2024-07-18 18:00","2024-07-15 07:00","2024-07-18 18:00","연속"]
[130,"부산울산","울산","언양산막#2 T/L","154kV 석계분기T/L 건설공사","지지물 : 154kV 산형강철탑 5기 전력선 : ACSR 410 * 2B * 4C","2024-07-19 07:00","2024-07-22 18:00","2024-07-19 07:00","2024-07-22 18:00","연속"]
[131,"경남","직할","천선진해#1 T/L","154kV 천선-진해#1T/L 인출변경공사","○ 154kV 진해S/S 옥내화 건설공사 - 154kV 천선-진해#1T/L 인출변경공사(7/11 ~ 8/1) - 천선-진해#1T/L GIS 사용 전 검사 (8/2 ~ 3)","2024-07-11 08:30","2024-08-03 17:30","2024-07-11 08:30","2024-08-03 17:30","연속"]