{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":6,"n_cols":11,"rows_kept":6,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2024년도 8월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경북","영주","신한울N/P #1 Tie-Tr","신한울S/S 765kV #1,2M.Tr 보통점검 공사","신한울S/S 765kV #1M.Tr 보통점검 공사","2024-08-05 09:00","2024-08-09 18:00","2024-08-05 09:00","2024-08-09 18:00","연속"]
[2,"경북","영주","신한울N/P #2 Tie-Tr","신한울S/S 765kV #1,2M.Tr 보통점검 공사","신한울S/S 765kV #2M.Tr 보통점검 공사","2024-08-12 09:00","2024-08-16 18:00","2024-08-12 09:00","2024-08-16 18:00","연속"]

{"sheet":"345설비","index":1,"n_rows":110,"n_cols":11,"rows_kept":110,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2024년도 8월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","중부S/S #1 Sh.R CB","2024년 중부전력지사 변전정비 협력회사 총액공사","GIS 점검","2024-08-06 10:00","2024-08-06 18:00","2024-08-06 10:00","2024-08-06 18:00","연속"]
[2,"남서울","동서울","동서울S/S SVC CB","345kV 동서울S/S 종합정비공사","○ 500kV 동서울 변환소 부지확보 관련 사전정비 작업 - 345kV GIS 및 SVC 관련 제어케이블 이설","2024-08-01 09:00","2024-08-30 18:00","2024-08-01 09:00","2024-08-30 18:00","연속"]
[3,"남서울","동서울","곤지암동서울#2 T/L","345kV 동서울S/S 종합정비공사","○ 500kV 동서울 변환소 부지확보 관련 사전정비 작업 - 345kV GIS 제어케이블 이설","2024-08-19 09:00","2024-09-13 18:00","2024-08-19 09:00","2024-09-13 18:00","연속"]
[4,"남서울","직할","신문래S/S #1 Sh.R CB","균압콘덴서 절연열화 측정","균압콘덴서 절연열화 측정","2024-08-28 09:00","2024-08-28 18:00","2024-08-28 09:00","2024-08-28 18:00","연속"]
[5,"인천","시흥","신시흥#1S/S #1 M.Tr","신시흥S/S 154kV Sh.R 증설공사","- 신규 #1S.Tr 기초 및 기기설치 (154kV Sh.R 및 Sh.R 용 GIS 기초공사)","2024-08-01 09:00","2024-08-31 18:00","취소","취소","연속"]
[6,"경기북부","구리","미금S/S #5 Sh.R CB","24-25 구리전력 변전협력 총액공사","345kV Sh.R 보통점검","2024-08-14 09:00","2024-08-14 18:00","2024-08-14 09:00","2024-08-14 18:00","연속"]
[7,"경기북부","구리","미금S/S #4 Sh.R CB","24-25 구리전력 변전협력 총액공사","345kV Sh.R 보통점검","2024-08-13 09:00","2024-08-13 18:00","2024-08-13 09:00","2024-08-13 18:00","연속"]
[8,"경기북부","구리","미금S/S STATCOM CB","2024년 미금S/S 345kV STATCOM 냉각설비 보통점검공사","- STATCOM 냉각설비 보통점검 - 냉각설비 전원공급 ELCB 교체","2024-08-19 09:00","2024-08-23 18:00","2024-08-19 09:00","2024-08-23 18:00","연속"]
[9,"경기북부","구리","미금S/S #2 Sh.R CB","24-25 구리전력 변전협력 총액공사","345kV Sh.R 보통점검","2024-08-12 09:00","2024-08-12 18:00","2024-08-12 09:00","2024-08-12 18:00","연속"]
[10,"경기북부","구리","동서울미금#2 T/L","345kV 미금변전소 용량부족 차단기 대체공사","345kV 용량부족 차단기 교체 * 25CB","2024-08-12 09:00","2024-12-20 18:00","2024-08-12 09:00","2024-12-20 18:00","연속"]
[11,"경기북부","구리","신가평S/S #4 Sh.R CB","24-25 구리전력 변전협력 총액공사","345kV Sh.R 보통점검","2024-08-19 09:00","2024-08-19 18:00","2024-08-19 09:00","2024-08-19 18:00","연속"]
[12,"경기","평택","고덕S/S STATCOM CB","2024년 고덕S/S 345kV STATCOM 보통점검","고덕S/S 345kV STATCOM 보통점검 - Valve SPS 보드 교체작업 - VCS 등 보통점검","2024-08-19 09:00","2024-10-04 18:00","2024-08-19 09:00","2024-10-04 18:00","연속"]
[13,"충북","충주","신제천신영주#1 T/L","345kV 신제천-신영주T/L No.55 취약철탑 교체공사","철탑신설 1기, 철탑철거 2기 (가철탑 2기)","2024-08-26 07:00","2024-08-30 16:00","2024-08-26 07:00","2024-08-30 16:00","연속"]
[14,"대전세종충남","서산","당진T/P CB 7200","24년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 당진화력S/S 345kV 7200CB 균압콘덴서 절연열화 진단","2024-08-01 09:30","2024-08-01 12:00","2024-08-01 09:30","2024-08-01 12:00","연속"]
[15,"대전세종충남","서산","당진T/P CB 7272","24년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 당진화력S/S 345kV 7272CB 균압콘덴서 절연열화 진단","2024-08-01 13:00","2024-08-01 15:30","2024-08-01 13:00","2024-08-01 15:30","연속"]
[16,"대전세종충남","서산","북당진S/S #2 BUS","북당진S/S 345kV 북당진-신탕정T/L GIS 설치공사","72BAY 1CB(7271) 설치 73BAY 2CB(7371,7300) 설치","2024-08-26 09:00","2024-08-30 18:00","2024-08-26 09:00","2024-08-30 18:00","연속"]
[17,"대전세종충남","서산","신당진개폐소 CB 7C71","24년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 신당진개폐소 345kV 7C71 CB 균압콘덴서 절연열화 진단","2024-08-13 09:30","2024-08-13 12:00","2024-08-13 09:30","2024-08-13 12:00","연속"]
[18,"대전세종충남","서산","신당진개폐소 CB 7B71","24년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 신당진개폐소 345kV 7B71CB 균압콘덴서 절연열화 진단","2024-08-12 13:00","2024-08-12 15:30","2024-08-12 13:00","2024-08-12 15:30","연속"]
[19,"대전세종충남","서산","신당진개폐소 CB 7D00","24년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 신당진개폐소 345kV 7D00 CB 균압콘덴서 절연열화 진단","2024-08-13 13:00","2024-08-13 15:30","2024-08-13 13:00","2024-08-13 15:30","연속"]
[20,"대전세종충남","서산","신당진개폐소 CB 7A72","24년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 신당진개폐소 345kV 7A72CB 균압콘덴서 절연열화 진단","2024-08-12 09:30","2024-08-12 12:00","2024-08-12 09:30","2024-08-12 12:00","연속"]
[21,"대전세종충남","서산","신서산S/S CB 7871","24년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 신서산S/S 345kV 7871 CB 균압콘덴서 절연열화 진단","2024-08-26 09:30","2024-08-26 12:30","2024-08-26 09:30","2024-08-26 12:30","연속"]
[22,"대전세종충남","서산","신서산S/S CB 7672","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 345kV 7672 GIS 보통점검","2024-08-27 09:30","2024-08-27 18:00","2024-08-27 09:30","2024-08-27 18:00","연속"]
[23,"대전세종충남","서산","신서산S/S CB 7772","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 345kV 7772 GIS 보통점검","2024-08-29 09:30","2024-08-29 18:00","2024-08-29 09:30","2024-08-29 18:00","연속"]
[24,"대전세종충남","서산","신서산S/S CB 7571","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 345kV 7571 GIS 보통점검","2024-08-22 09:30","2024-08-22 18:00","2024-08-22 09:30","2024-08-22 18:00","연속"]
[25,"대전세종충남","서산","신서산태안TP#1 T/L","24년 서산P/O 변전협력회사 총액공사","(T/L 즉시가압 가능) 태안화력S/S 345kV 신서산-태안화력#1T/L 1차 7671CB A상 대체 - 7600 Tie CB 휴전필요 : GIS 대체관련 안전이격확보","2024-08-05 09:30","2024-08-07 18:00","2024-08-05 09:30","2024-08-07 18:00","매일"]
[26,"대전세종충남","서산","태안T/P CB 7671","24년 서산P/O 변전협력회사 총액공사","(즉시가압불가)태안화력S/S 345kV 신서산-태안화력#1T/L 1차 7671CB A상 대체","2024-08-07 18:00","2024-08-09 18:00","2024-08-07 18:00","2024-08-09 18:00","연속"]
[27,"대전세종충남","천안","청양신탕정#2 T/L","[7월취소시]345kV 신온양-신탕정T/L 추락방지장치 설치공사","[즉시가압가능]345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치 [병가철탑] 신온양신탕정#2(상단), 청양신탕정#2(하단)","2024-08-12 07:00","2024-08-16 18:00","취소","취소","매일"]
[28,"대전세종충남","천안","신온양신탕정#1 T/L","[7월취소시]345kV 신온양-신탕정T/L 추락방지장치 설치공사","[즉시가압가능]345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치 [병가철탑] 신온양신탕정#1(상단), 청양신탕정#1(하단)","2024-08-05 07:00","2024-08-09 18:00","취소","취소","매일"]
[29,"대전세종충남","천안","청양신탕정#1 T/L","[7월취소시]345kV 신온양-신탕정T/L 추락방지장치 설치공사","[즉시가압가능]345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치 [병가철탑] 신온양신탕정#1(상단), 청양신탕정#1(하단)","2024-08-05 07:00","2024-08-09 18:00","취소","취소","매일"]
[30,"대전세종충남","천안","신온양신탕정#2 T/L","[7월취소시]345kV 신온양-신탕정T/L 추락방지장치 설치공사","[즉시가압가능]345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치 [병가철탑] 신온양신탕정#2(상단), 청양신탕정#2(하단)","2024-08-12 07:00","2024-08-16 18:00","취소","취소","매일"]
[31,"대전세종충남","청양","청양군산#1 T/L","[7월 취소시]345KV 청양군산#1T/L 가공지선 교체","345KV 청양군산#1T/L 가공지선 교체 및 애자련 보강","2024-08-26 08:00","2024-09-02 18:00","2024-08-16 08:00","2024-08-23 18:00","연속"]
[32,"대전세종충남","청양","청양군산#2 T/L","[7월 취소시]345KV 청양군산#2T/L 애자련 보강","345KV 청양군산#1T/L 애자련 보강","2024-08-21 08:00","2024-08-23 18:00","2024-08-26 08:00","2024-08-28 18:00","연속"]
[33,"전북","군산","군산S/S #1 Sh.R CB","군산변전소 345kV GIS 대체공사(기기)","○ 362kV GIS 4000A 40kA × 10CB(50kA) 교체 ○ 기타 부대공사 × 1식","2024-08-30 15:00","2024-08-31 15:00","2024-08-30 15:00","2024-08-31 15:00","연속"]
[34,"전북","군산","군산S/S #1 Sh.R CB","군산변전소 345kV GIS 대체공사(기기)","○ 362kV GIS 4000A 40kA × 10CB(50kA) 교체 ○ 기타 부대공사 × 1식","2024-08-22 15:00","2024-08-23 15:00","2024-08-22 15:00","2024-08-23 15:00","연속"]
[35,"전북","군산","군산S/S #70 BUS","군산변전소 345kV GIS 대체공사","○ 362kV GIS 40kA 4000A × 10CB(4Bay) 철거 ○ 362kV GIS 50kA 4000A × 10CB(4Bay) 신설 ○ 기타부대공사 × 1식.","2024-08-16 08:00","2024-08-23 18:00","2024-08-16 08:00","2024-08-23 18:00","연속"]
[36,"전북","군산","군산S/S #75 BUS","군산변전소 345kV GIS 대체공사","○ 362kV GIS 40kA 4000A × 10CB(4Bay) 철거 ○ 362kV GIS 50kA 4000A × 10CB(4Bay) 신설 ○ 기타부대공사 × 1식.","2024-08-24 08:00","2024-08-31 18:00","2024-08-24 08:00","2024-08-31 18:00","연속"]
[37,"광주전남","광주","신광주S/S CB 7300","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체","2024-08-01 09:00","2024-08-31 18:00","취소","취소","연속"]
[38,"광주전남","광주","신광주S/S CB 7472","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체","2024-08-01 09:00","2024-08-31 18:00","취소","취소","연속"]
[39,"광주전남","광주","신광주S/S #2 M.Tr","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체","2024-08-01 09:00","2024-08-31 18:00","취소","취소","연속"]
[40,"광주전남","광주","신광주신화순#1 T/L","24~25년 광주전력지사 송전협력회사 총액공사","345kV 신광주-신화순#1T/L 수평 추락방지장치 설치공사(No.1~121)","2024-08-05 07:00","2024-08-16 18:00","2024-08-05 07:00","2024-08-16 18:00","매일"]
[41,"광주전남","광주","신광주신화순#2 T/L","24~25년 광주전력지사 송전협력회사 총액공사","345kV 신광주-신화순#2T/L 수평 추락방지장치 설치공사(No.1~121)","2024-08-19 07:00","2024-08-30 18:00","2024-08-19 07:00","2024-08-30 18:00","매일"]
[42,"광주전남","광주","신광주S/S #1 BUS","장기사용 345kV #1BUS 모선보호반 교체","장기사용 345kV #1BUS 모선보호반 교체","2024-08-19 08:00","2024-08-23 18:00","취소","취소","연속"]
[43,"광주전남","광주","신광주S/S CB 7572","345kV Sh.R 권선온도계 교체 및 리액터 점검","345kV Sh.R 권선온도계 교체 및 리액터 점검","2024-08-21 08:00","2024-08-21 18:00","2024-08-21 08:00","2024-08-21 18:00","연속"]
[44,"광주전남","광주","신광주S/S CB 7500","345kV Sh.R 권선온도계 교체 및 리액터 점검","345kV Sh.R 권선온도계 교체 및 리액터 점검","2024-08-21 08:00","2024-08-21 18:00","2024-08-21 08:00","2024-08-21 18:00","연속"]
[45,"광주전남","광주","신광주S/S #1 Sh.R CB","345kV Sh.R 권선온도계 교체 및 리액터 점검","345kV Sh.R 권선온도계 교체 및 리액터 점검","2024-08-21 08:00","2024-08-21 18:00","2024-08-21 08:00","2024-08-21 18:00","연속"]
[46,"광주전남","광주","신남원신광주#1 T/L","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체","2024-08-26 13:00","2024-08-28 13:00","취소","취소","연속"]
[47,"광주전남","광주","신광주S/S CB 7472","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체","2024-08-01 09:00","2024-08-31 18:00","취소","취소","연속"]
[48,"광주전남","광주","신광주S/S CB 7300","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체","2024-08-01 09:00","2024-08-31 18:00","취소","취소","연속"]
[49,"광주전남","광주","신광주S/S #2 M.Tr","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체","2024-08-01 09:00","2024-08-31 18:00","취소","취소","연속"]
[50,"광주전남","광주","신광주신화순#1 T/L","24~25년 광주전력지사 송전협력회사 총액공사","345kV 신광주-신화순#1T/L 수평 추락방지장치 설치공사(No.1~121)","2024-08-05 07:00","2024-08-16 18:00","취소","취소","매일"]
[51,"광주전남","광주","신광주신화순#2 T/L","24~25년 광주전력지사 송전협력회사 총액공사","345kV 신광주-신화순#2T/L 수평 추락방지장치 설치공사(No.1~121)","2024-08-19 07:00","2024-08-30 18:00","취소","취소","매일"]
[52,"광주전남","광주","신광주S/S #1 BUS","장기사용 345kV #1BUS 모선보호반 교체","장기사용 345kV #1BUS 모선보호반 교체","2024-08-19 08:00","2024-08-23 18:00","취소","취소","연속"]
[53,"광주전남","광주","신광주S/S CB 7572","345kV Sh.R 권선온도계 교체 및 리액터 점검","345kV Sh.R 권선온도계 교체 및 리액터 점검","2024-08-21 08:00","2024-08-21 18:00","취소","취소","연속"]
[54,"광주전남","광주","신광주S/S CB 7500","345kV Sh.R 권선온도계 교체 및 리액터 점검","345kV Sh.R 권선온도계 교체 및 리액터 점검","2024-08-21 08:00","2024-08-21 18:00","취소","취소","연속"]
[55,"광주전남","광주","신광주S/S #1 Sh.R CB","345kV Sh.R 권선온도계 교체 및 리액터 점검","345kV Sh.R 권선온도계 교체 및 리액터 점검","2024-08-21 08:00","2024-08-21 18:00","취소","취소","연속"]
[56,"광주전남","광주","신광주S/S #2 BUS","장기사용 345kV #2BUS 모선보호반 교체","장기사용 345kV #2BUS 모선보호반 교체","2024-08-26 08:00","2024-08-30 18:00","취소","취소","연속"]
[57,"광주전남","광주","신남원신광주#1 T/L","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체","2024-08-26 13:00","2024-08-28 13:00","취소","취소","연속"]
[58,"광주전남","광주","신광주S/S #2 BUS","장기사용 345kV #2BUS 모선보호반 교체","장기사용 345kV #2BUS 모선보호반 교체","2024-08-26 08:00","2024-08-30 18:00","취소","취소","연속"]
[59,"광주전남","순천","광양C/C CB 7171","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압가능)","2024-08-13 08:00","2024-08-13 18:00","2024-08-13 08:00","2024-08-13 18:00","연속"]
[60,"광주전남","순천","광양C/C CB 7171","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압가능)","2024-08-13 08:00","2024-08-13 18:00","취소","취소","연속"]
[61,"광주전남","순천","광양S/S CB 7300","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압가능)","2024-08-12 14:00","2024-08-12 18:00","2024-08-12 14:00","2024-08-12 18:00","연속"]
[62,"광주전남","순천","광양S/S CB 7371","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압가능)","2024-08-12 09:00","2024-08-12 14:00","2024-08-12 09:00","2024-08-12 14:00","연속"]
[63,"광주전남","순천","광양S/S CB 7600","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압 가능)","2024-08-09 14:00","2024-08-09 18:00","2024-08-09 14:00","2024-08-09 18:00","연속"]
[64,"광주전남","순천","광양S/S CB 7671","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압 가능)","2024-08-09 09:00","2024-08-09 14:00","2024-08-09 09:00","2024-08-09 14:00","연속"]
[65,"광주전남","순천","광양S/S CB 7700","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압 가능)","2024-08-08 14:00","2024-08-08 18:00","2024-08-08 14:00","2024-08-08 18:00","연속"]
[66,"광주전남","순천","광양S/S CB 7771","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압 가능)","2024-08-08 08:00","2024-08-08 14:00","2024-08-08 08:00","2024-08-08 14:00","연속"]
[67,"광주전남","순천","광양S/S SEC CB 75760","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압 가능)","2024-08-07 09:00","2024-08-07 18:00","2024-08-07 09:00","2024-08-07 18:00","연속"]
[68,"광주전남","순천","광양S/S CB 7300","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압가능)","2024-08-12 14:00","2024-08-12 18:00","취소","취소","연속"]
[69,"광주전남","순천","광양S/S CB 7371","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압가능)","2024-08-12 09:00","2024-08-12 14:00","취소","취소","연속"]
[70,"광주전남","순천","광양S/S CB 7600","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압 가능)","2024-08-09 14:00","2024-08-09 18:00","취소","취소","연속"]
[71,"광주전남","순천","광양S/S CB 7671","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압 가능)","2024-08-09 09:00","2024-08-09 14:00","취소","취소","연속"]
[72,"광주전남","순천","광양S/S CB 7700","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압 가능)","2024-08-08 14:00","2024-08-08 18:00","취소","취소","연속"]
[73,"광주전남","순천","광양S/S CB 7771","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압 가능)","2024-08-08 08:00","2024-08-08 14:00","취소","취소","연속"]
[74,"광주전남","순천","광양S/S SEC CB 75760","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압 가능)","2024-08-07 09:00","2024-08-07 18:00","취소","취소","연속"]
[75,"광주전남","순천","여수T/P CB 7172","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압가능)","2024-08-14 08:00","2024-08-14 18:00","2024-08-14 08:00","2024-08-14 18:00","연속"]
[76,"광주전남","순천","여수T/P CB 7172","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압가능)","2024-08-14 08:00","2024-08-14 18:00","취소","취소","연속"]
[77,"광주전남","순천","율촌C/C CB 7172","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압가능)","2024-08-19 14:00","2024-08-19 18:00","2024-08-19 14:00","2024-08-19 18:00","연속"]
[78,"광주전남","순천","율촌C/C CB 7200","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압가능)","2024-08-15 08:00","2024-08-15 14:00","2024-08-15 08:00","2024-08-15 14:00","연속"]
[79,"광주전남","순천","율촌C/C CB 7272","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압가능)","2024-08-15 14:00","2024-08-15 18:00","2024-08-15 14:00","2024-08-15 18:00","연속"]
[80,"광주전남","순천","율촌C/C CB 7100","24-25년 순천전력지사 변전회사 총액공사","GIS 절연열화 측정(즉시가압가능)","2024-08-19 08:00","2024-08-19 14:00","2024-08-19 08:00","2024-08-19 14:00","연속"]
[81,"대구","경산","신경산S/S #1 BUS","24~25년 경산P/O 변전협력회사 총액공사","- 7000, 7072 GIS 도블측정","2024-08-29 09:30","2024-08-29 14:00","2024-08-29 09:30","2024-08-29 14:00","연속"]
[82,"대구","경산","신경산S/S #2 BUS","24~25년 경산P/O 변전협력회사 총액공사","- 7000, 7072 GIS 도블측정","2024-08-29 14:00","2024-08-29 18:00","2024-08-29 14:00","2024-08-29 18:00","연속"]
[83,"대구","경산","신경산S/S #4 M.Tr","24~25년 경산P/O 변전협력회사 총액공사","7672 GIS 제작사 및 협력회사 점검","2024-08-20 09:00","2024-08-21 18:00","2024-08-20 09:00","2024-08-21 18:00","연속"]
[84,"대구","경산","신경산S/S #1 M.Tr","24~25년 경산P/O 변전협력회사 총액공사","- 7000, 7072 GIS 도블측정","2024-08-29 09:30","2024-08-29 18:00","2024-08-29 09:30","2024-08-29 18:00","연속"]
[85,"대구","칠곡","북대구S/S #2 M.Tr","북대구S/S #2M.Tr 96P Flexible Hose 교체","북대구S/S #2M.Tr 96P Flexible Hose 교체","2024-08-06 09:30","2024-08-06 18:00","2024-08-06 09:30","2024-08-06 18:00","연속"]
[86,"대구","칠곡","북대구S/S #3 M.Tr","북대구S/S #3M.Tr 96P Flexible Hose 교체","북대구S/S #3M.Tr 96P Flexible Hose 교체","2024-08-07 09:30","2024-08-07 18:00","2024-08-07 09:30","2024-08-07 18:00","연속"]
[87,"대구","포항","신울산월성NP#1 T/L","월성N/P 연계 345kV GIS 용량대체공사(75Bay 대체)","월성N/P 연계 345kV GIS 용량대체공사 ○ 345kV GIS × 18CB 대체 ○ 보호반 설치 및 이설 ○ 제어케이블 포설 및 결선 ○ 기타 부대공사 × 1식","2024-08-07 14:00","2024-08-08 09:00","2024-08-07 14:00","2024-08-08 09:00","연속"]
[88,"대구","포항","월성N/P SEC CB 75760","월성N/P 연계 345kV GIS 용량대체공사(75Bay 대체)","월성N/P 연계 345kV GIS 용량대체공사 ○ 345kV GIS × 18CB 대체 ○ 보호반 설치 및 이설 ○ 제어케이블 포설 및 결선 ○ 기타 부대공사 × 1식","2024-08-05 09:00","2024-08-06 09:00","2024-08-05 09:00","2024-08-06 09:00","연속"]
[89,"대구","포항","월성N/P #76 BUS","월성N/P 연계 345kV GIS 용량대체공사(75Bay 대체)","월성N/P 연계 345kV GIS 용량대체공사 ○ 345kV GIS × 18CB 대체 ○ 보호반 설치 및 이설 ○ 제어케이블 포설 및 결선 ○ 기타 부대공사 × 1식","2024-08-05 09:00","2024-08-06 09:00","2024-08-05 09:00","2024-08-06 09:00","연속"]
[90,"대구","포항","월성N/P #71 BUS","월성N/P 연계 345kV GIS 용량대체공사(75Bay 대체)","월성N/P 연계 345kV GIS 용량대체공사 ○ 345kV GIS × 18CB 대체 ○ 보호반 설치 및 이설 ○ 제어케이블 포설 및 결선 ○ 기타 부대공사 × 1식","2024-08-06 09:00","2024-08-08 18:00","2024-08-06 09:00","2024-08-08 18:00","연속"]
[91,"경북","영주","신태백한울NP#2 T/L","2024년 한울2발S/Y 345kV GIS 정밀점검","2024년 한울2발S/Y 345kV GIS 정밀점검","2024-08-26 09:00","2024-08-30 18:00","2024-08-26 09:00","2024-08-30 18:00","연속"]
[92,"경북","영주","신태백한울NP#1 T/L","2024년 한울2발S/Y 345kV GIS 정밀점검","2024년 한울2발S/Y 345kV GIS 정밀점검","2024-08-19 09:00","2024-08-23 18:00","2024-08-19 09:00","2024-08-23 18:00","연속"]
[93,"경북","영주","한울#2N/P #2 BUS","2024년 한울2발S/Y 345kV GIS 정밀점검공사","2024년 한울2발S/Y 345kV GIS 정밀점검공사","2024-08-09 09:00","2024-08-09 18:00","2024-08-09 09:00","2024-08-09 18:00","연속"]
[94,"경북","영주","한울#3N/P CB 7E72","동해안변환소 AC배후계통(변전) 건설공사","- 동해안변환소 AC배후계통건설 관련 사전작업 RTU 및 집감반 신규설치(보호반 설치를 위한 공간확보)","2024-08-22 09:00","2024-08-23 18:00","2024-08-22 09:00","2024-08-23 18:00","연속"]
[95,"경북","영주","신한울한울#1 T/L","동해안변환소 AC배후계통(변전) 건설공사","- 동해안변환소 AC배후계통건설 관련 사전작업 RTU 및 집감반 신규설치(보호반 설치를 위한 공간확보)","2024-08-13 09:00","2024-08-14 18:00","2024-08-13 09:00","2024-08-14 18:00","연속"]
[96,"경북","영주","신한울한울#2 T/L","동해안변환소 AC배후계통(변전) 건설공사","- 동해안변환소 AC배후계통건설 관련 사전작업 RTU 및 집감반 신규설치(보호반 설치를 위한 공간확보)","2024-08-22 09:00","2024-08-23 18:00","2024-08-22 09:00","2024-08-23 18:00","연속"]
[97,"경북","영주","한울#3N/P CB 7D72","동해안변환소 AC배후계통(변전) 건설공사","- 동해안변환소 AC배후계통건설 관련 사전작업 RTU 및 집감반 신규설치(보호반 설치를 위한 공간확보)","2024-08-13 09:00","2024-08-14 18:00","2024-08-13 09:00","2024-08-14 18:00","연속"]
[98,"부산울산","동부산","신양산S/S #2 BUS","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 용량부족차단기 교체공사(4차)(안전이격) - 모선DS부 END COVER 제거 - 76BAY GIS 연결 설치","2024-08-02 09:00","2024-08-03 18:00","취소","취소","매일"]
[99,"부산울산","동부산","신양산고리NP#1 T/L","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 용량부족차단기 교체공사(4차)(안전이격) - 76BAY GIS 인출측 설치 및 조립","2024-08-17 09:00","2024-08-18 18:00","2024-08-17 09:00","2024-08-18 18:00","연속"]
[100,"부산울산","서부산","서부산S/S #3 Sh.R CB","서부산S/S 345kV #3Sh.R 보통점검","서부산S/S 345kV #3Sh.R 보통점검","2024-08-12 09:00","2024-08-14 18:00","2024-08-12 09:00","2024-08-14 18:00","연속"]
[101,"부산울산","울산","신울산S/S #2 M.Tr","신울산S/S #2M.Tr 3차 현대화 공사","-신울산S/S #2M.Tr 3차 현대화 공사 -7372,7300 GIS 하자점검 -1차 CVT 보통점검","2024-08-19 09:00","2024-10-31 18:00","2024-08-19 09:00","2024-10-31 18:00","연속"]
[102,"경남","진주","신남원의령#2 T/L","345kV 신남원-의령T/L 추락방지장치 설치 공사","345kV 신남원-의령T/L 추락방지장치 설치 공사 1~136호(136기)","2024-08-30 09:00","2024-09-13 18:00","2024-08-30 09:00","2024-09-13 18:00","매일"]
[103,"경남","진주","고령의령#2 T/L","345kV 신남원-의령T/L 추락방지장치 설치 공사 관련 안전거리확보","345kV 신남원-의령T/L 추락방지장치 설치 공사 1~136호(136기) - 2~4호(3기) 안전거리 확보 휴전","2024-08-30 09:00","2024-09-02 18:00","2024-08-30 09:00","2024-09-02 18:00","매일"]
[104,"경남","진주","고령의령#1 T/L","345kV 신남원-의령T/L 추락방지장치 설치 공사 관련 안전거리확보","345kV 신남원-의령T/L 추락방지장치 설치 공사 1~136호(136기) - 2~4호(3기) 안전거리 확보 휴전","2024-08-19 09:00","2024-08-20 18:00","2024-08-19 09:00","2024-08-20 18:00","매일"]
[105,"경남","진주","신남원의령#1 T/L","345kV 신남원-의령T/L 추락방지장치 설치 공사","345kV 신남원-의령T/L 추락방지장치 설치 공사 1~136호(136기)","2024-08-19 09:00","2024-08-29 18:00","2024-08-19 09:00","2024-08-29 18:00","매일"]
[106,"경남","함안","신마산S/S #4 M.Tr","신마산S/S #4M.Tr 1차 EBG 해체점검","신마산S/S #4M.Tr 1차 EBG 해체점검","2024-08-19 09:00","2024-08-30 18:00","취소","취소","연속"]

{"sheet":"154설비","index":2,"n_rows":112,"n_cols":11,"rows_kept":112,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2024년도 8월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"인천","시흥","신시흥도림#2 T/L","신시흥S/S 154kV Sh.R 증설공사","345kV #1M.Tr 2차 POST 철거","2024-08-17 09:00","2024-08-18 18:00","취소","취소","연속"]
[2,"경기북부","고양","지축삼송열병합#2 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 보통점검(한전 측 작업) 전력량계 교체 및 시험(지역난방공사 측 작업)","2024-08-28 09:30","2024-08-29 17:00","2024-08-28 09:30","2024-08-29 17:00","연속"]
[3,"경기북부","고양","지축삼송열병합#1 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 보통점검(한전 측 작업) 전력량계 교체 및 시험(지역난방공사 측 작업)","2024-08-26 09:30","2024-08-27 17:00","2024-08-26 09:30","2024-08-27 17:00","연속"]
[4,"대전세종충남","대전","팔봉두마#1 T/L","154kV 팔봉-두마T/L No.67~109 선종교체공사","공사구간 : 154kV 팔봉-두마T/L No.67~109 공사내용 : ACSR 240㎟ → ASCC/TW 310㎟ x S x 2C, 15km 전선교체 저지상고 및 취약 철탑 교체 6기","2024-08-05 07:00","2024-08-31 18:00","2024-08-05 07:00","2024-08-31 18:00","연속"]
[5,"대전세종충남","대전","신계룡은진#2 T/L","154kV 팔봉-두마T/L No.67~109 선종교체공사","No.106~108 구간 안전이격 휴전","2024-08-26 07:00","2024-08-29 18:00","2024-08-26 07:00","2024-08-29 18:00","연속"]
[6,"대전세종충남","대전","신계룡은진#1 T/L","154kV 팔봉-두마T/L No.67~109 선종교체공사","No.106~108 구간 안전이격 휴전","2024-08-21 07:00","2024-08-23 18:00","2024-08-21 07:00","2024-08-23 18:00","연속"]
[7,"대전세종충남","대전","신옥천추부#2 T/L","[송전][즉시가압O]345kV 신옥천-청양등8개T/L추락방지설치공사","[송전][주말작업제외][즉시가압O]345kV 신옥천-청양등8개T/L추락방지설치공사","2024-08-12 07:00","2024-08-21 18:00","취소","취소","매일"]
[8,"대전세종충남","대전","추부S/S CB 6100","추부S/S 154kV #3M.Tr 증설공사(무부하)","#1BUS 무부하 가압 시행","2024-08-09 07:00","2024-08-09 09:00","취소","취소","연속"]
[9,"대전세종충남","대전","추부S/S #1 BUS","추부S/S 154kV #3M.Tr 증설공사","- 154kV M.Tr(20MVA*3) * 1Bank 설치 - 154kV GIS 1CCT, 23kV GIS 3CCT 설치 - M.Tr 2차 전력케이블 설치 - 기타 부대작업 등","2024-08-08 16:00","2024-08-09 09:00","취소","취소","매일"]
[10,"대전세종충남","대전","추부S/S #2 BUS","추부S/S 154kV #3M.Tr 증설공사","- 154kV M.Tr(20MVA*3) * 1Bank 설치 - 154kV GIS 1CCT, 23kV GIS 3CCT 설치 - M.Tr 2차 전력케이블 설치 - 기타 부대작업 등","2024-08-12 16:00","2024-08-13 09:00","취소","취소","매일"]
[11,"대전세종충남","대전","추부금산#1 T/L","[송전][즉시가압O]345kV 신옥천-청양등8개T/L추락방지설치공사","[송전][주말작업제외][즉시가압O]345kV 신옥천-청양등8개T/L추락방지설치공사","2024-08-16 07:00","2024-09-05 18:00","취소","취소","매일"]
[12,"대전세종충남","대전","추부S/S CB 6100","추부S/S 154kV #3M.Tr 증설공사(무부하)","#1BUS 무부하 가압 시행","2024-08-13 07:00","2024-08-13 09:00","취소","취소","연속"]
[13,"대전세종충남","서산","석문당진화력#2 T/L","서산P/O 효성제 170kV GIS 베어링 교체공사","(7월 휴전신청 취소시) (즉시가압 가능) 당진화력S/S 154kV 석문-당진화력#2T/L 627 CB 베어링 교체 (병행) 석문S/S 154kV 석문-당진화력#2T/L IED 성능개선 (병행) 석문S/S 154kV 석문-당진화력#2T/L 687 CB 보통점검 (병행) 당진화력S/S 154kV 석문-당진화력#2T/L 627 CB 보통점검","2024-08-21 09:30","2024-08-22 18:00","취소","취소","매일"]
[14,"대전세종충남","서산","석문당진화력#1 T/L","서산P/O 효성제 170kV GIS 베어링 교체공사","(7월 휴전신청 취소시) (즉시가압 가능) 당진화력S/S 154kV 석문-당진화력#1T/L 617 CB 베어링 교체 (병행) 석문S/S 154kV 석문-당진화력#1T/L IED 성능개선 (병행) 석문S/S 154kV 석문-당진화력#1T/L 617 CB 보통점검 (병행) 당진화력S/S 154kV 석문-당진화력#1T/L 617CB 보통점검","2024-08-19 09:30","2024-08-20 18:00","취소","취소","매일"]
[15,"전북","군산","군공소룡#1 T/L","군산P/O 170kV GIS 정밀점검 공사","군산P/O 170kV GIS 정밀점검 공사","2024-08-12 09:00","2024-08-14 18:00","2024-08-12 09:00","2024-08-14 18:00","연속"]
[16,"전북","군산","군공소룡#2 T/L","군산P/O 170kV GIS 정밀점검 공사","군산P/O 170kV GIS 정밀점검 공사 군공S/S 687 차단기 정밀점검 소룡S/S 647 차단기 정밀점검(모선DS 포함)","2024-08-19 09:00","2024-08-21 18:00","2024-08-19 09:00","2024-08-21 18:00","연속"]
[17,"전북","군산","새만금소룡#2 T/L","군산P/O 170kV GIS 정밀점검 공사(무부하가압용)","군공S/S 687CB, 소룡S/S 647CB 및 641DS 무부하가압","2024-08-20 17:30","2024-08-20 18:00","2024-08-20 17:30","2024-08-20 18:00","연속"]
[18,"전북","군산","은진함열#2 T/L","24년 군산 P/O 장기사용 배전반 교체공사","154kV 함열-은진#2T/L 보호반 대체(8.24~8.26, 연속)","2024-08-24 09:00","2024-08-26 18:00","2024-08-24 09:00","2024-08-26 18:00","연속"]
[19,"전북","군산","은진함열#1 T/L","24년 군산 P/O 장기사용 배전반 교체공사","154kV 함열-은진#1T/L 보호반 대체(8.19~8.21, 연속)","2024-08-19 09:00","2024-08-21 18:00","2024-08-19 09:00","2024-08-21 18:00","연속"]
[20,"전북","김제","고창영광 T/L","154kV 정주-고창 등 2개T/L 선종교체공사","- 공사구간 :154kV 정주-고창T/L No.81~95 - 전력선 교체 : 44.076C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, 현수클램프 등]","2024-08-22 08:00","2024-09-03 17:00","2024-08-22 08:00","2024-09-03 17:00","연속"]
[21,"전북","김제","정주부안#1 T/L","154kV 정주-고창 등 2개T/L 선종교체공사","- 공사구간 : 154kV 정주-고창T/L No.1~17(병가구간) - 전력선 교체 : 44.076C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, 현수클램프 등]","2024-08-10 08:00","2024-08-21 17:00","취소","취소","연속"]
[22,"전북","김제","정주고창#1 T/L","154kV 정주-고창 등 2개T/L 선종교체공사","- 공사구간 : No.1~95 - 전력선 교체 : 44.076C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, 현수클램프 등]","2024-08-10 08:00","2024-09-26 17:00","취소","취소","연속"]
[23,"전북","김제","정주부안#2 T/L","154kV 정주-고창 등 2개T/L 선종교체공사","- 공사구간 : 154kV 정주-고창T/L No.17~22 (병가구간) - 전력선 교체 : 44.076C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, 현수클램프 등]","2024-08-20 08:00","2024-08-21 17:00","취소","취소","매일"]
[24,"전북","직할","신김제동전주#2 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","신김제-동전주T/L 조립간 절연간격 확보","2024-08-26 08:00","2024-08-27 17:00","2024-08-26 08:00","2024-08-27 17:00","연속"]
[25,"전북","직할","무주용담수력 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사","154kV 무주-용담T/L 수평 추락방지시설 설치 - 154kV 북전주-진안T/L No.51~104","2024-08-05 07:30","2024-08-11 16:30","2024-08-05 07:30","2024-08-11 16:30","매일"]
[26,"전북","직할","무주진안 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사","154kV 무주-진안T/L 수평 추락방지시설 설치 - 154kV 북전주-진안T/L No.104~175 - 154kV 무주분기T/L No.1~45","2024-08-12 07:30","2024-08-19 16:30","2024-08-12 07:30","2024-08-19 16:30","매일"]
[27,"전북","직할","북전주진안 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사","154kV 북전주-진안T/L 수평 추락방지시설 설치 - 154kV 북전주-진안T/L No.1~175","2024-08-20 07:30","2024-08-28 16:30","2024-08-20 07:30","2024-08-28 16:30","매일"]
[28,"전북","직할","북전주용담수력 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사","154kV 북전주-용담T/L 수평 추락방지시설 설치 - 154kV 북전주-진안T/L No.1~50","2024-08-01 07:30","2024-08-04 16:30","2024-08-01 07:30","2024-08-04 16:30","매일"]
[29,"광주전남","강진","화원진도#2 T/L","'24년 강진전력지사 효성제 170kV GIS 개선 공사","가. 진도S/S 효성제 #5M.Tr 1차 GIS 주접점 이탈 관련 차단부 교체 관련 무부하 가압","2024-08-07 09:00","2024-08-08 18:00","2024-08-07 09:00","2024-08-08 18:00","연속"]
[30,"광주전남","강진","화원진도#2 T/L","'24년 강진전력지사 효성제 170kV GIS 개선 공사","가. 진도S/S 효성제 #5M.Tr 1차 GIS 주접점 이탈 관련 차단부 교체 관련 무부하 가압","2024-08-07 09:00","2024-08-08 18:00","취소","취소","연속"]
[31,"광주전남","광주","장성영광#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","장성S/S 154kV 장성-영광#2T/L GIS 조작시험","2024-08-08 14:00","2024-08-08 18:00","취소","취소","연속"]
[32,"광주전남","광주","장성영광#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","장성S/S 154kV 장성-영광#1T/L GIS 조작시험","2024-08-08 09:00","2024-08-08 14:00","취소","취소","연속"]
[33,"광주전남","광주","장성영광#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","장성S/S 154kV 장성-영광#2T/L GIS 조작시험","2024-08-08 14:00","2024-08-08 18:00","취소","취소","연속"]
[34,"광주전남","광주","장성영광#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","장성S/S 154kV 장성-영광#1T/L GIS 조작시험","2024-08-08 09:00","2024-08-08 14:00","취소","취소","연속"]
[35,"광주전남","광주","계림충장#3 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 154kV 계림-충장#3T/L GIS 조작시험","2024-08-23 09:00","2024-08-23 14:00","취소","취소","연속"]
[36,"광주전남","광주","계림충장#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 154kV 계림-충장#2T/L GIS 조작시험","2024-08-22 14:00","2024-08-22 18:00","취소","취소","연속"]
[37,"광주전남","광주","계림충장#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 154kV 계림-충장#1T/L GIS 조작시험","2024-08-22 09:00","2024-08-22 14:00","취소","취소","연속"]
[38,"광주전남","광주","계림충장#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 154kV 계림-충장#1T/L GIS 조작시험","2024-08-22 09:00","2024-08-22 14:00","취소","취소","연속"]
[39,"광주전남","광주","계림충장#3 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 154kV 계림-충장#3T/L GIS 조작시험","2024-08-23 09:00","2024-08-23 14:00","취소","취소","연속"]
[40,"광주전남","광주","계림충장#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 154kV 계림-충장#2T/L GIS 조작시험","2024-08-22 14:00","2024-08-22 18:00","취소","취소","연속"]
[41,"광주전남","목포","엄다무안햇빛#2 T/L","GE제 IED 펌웨어 업그레이드 시행(엄다, 무안햇빛)","GE제 IED 펌웨어 업그레이드 시행(엄다, 무안햇빛) - 엄다-무안햇빛#2T/L - IED 펌웨어 업그레이드","2024-08-12 10:00","2024-08-14 18:00","2024-08-12 10:00","2024-08-14 18:00","연속"]
[42,"광주전남","목포","남악북항#1 T/L","남악S/S 154kV #3M.Tr 증설공사","전체 무부하가압","2024-08-22 10:00","2024-08-23 15:00","2024-08-22 10:00","2024-08-23 15:00","연속"]
[43,"광주전남","목포","나주엄다#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","1차 교체분 무부하가압용","2024-08-02 10:00","2024-08-03 10:00","취소","취소","연속"]
[44,"광주전남","목포","나주엄다#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","1차 교체분 무부하가압용","2024-08-05 16:00","2024-08-05 18:00","취소","취소","연속"]
[45,"광주전남","목포","엄다목포#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","엄다-목포#1T/L, #3M.Tr 1차, PT&ES GIS 교체작업","2024-08-06 09:00","2024-09-27 18:00","취소","취소","연속"]
[46,"광주전남","목포","엄다S/S #1 BUS","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","엄다-목포#1T/L, #3M.Tr 1차, PT&ES #1BUS, #1DS, CB 교체","2024-08-08 14:00","2024-08-29 14:00","취소","취소","연속"]
[47,"광주전남","목포","나주엄다#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","엄다-목포#1T/L, #3M.Tr 1차, PT&ES #1BUS측 무부하가압용","2024-08-28 14:00","2024-08-29 14:00","취소","취소","연속"]
[48,"광주전남","목포","엄다S/S #2 BUS","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","엄다-목포#1T/L, #3M.Tr 1차, PT&ES #2BUS측 교체","2024-08-29 14:00","2024-09-27 14:00","취소","취소","연속"]
[49,"광주전남","순천","장흥벌교 T/L","154kV 장흥-벌교T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-19 07:00","2024-08-21 18:00","2024-08-19 07:00","2024-08-21 18:00","매일"]
[50,"광주전남","순천","보성벌교 T/L","154kV 장흥-벌교T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-22 07:00","2024-08-23 18:00","2024-08-22 07:00","2024-08-23 18:00","매일"]
[51,"광주전남","순천","보성벌교 T/L","154kV 장흥-벌교T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-22 07:00","2024-08-23 18:00","취소","취소","매일"]
[52,"광주전남","순천","장흥벌교 T/L","154kV 장흥-벌교T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-19 07:00","2024-08-21 18:00","취소","취소","매일"]
[53,"광주전남","순천","소라서순천#2 T/L","154kV 소라-서순천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-02 07:00","2024-08-02 18:00","2024-08-02 07:00","2024-08-02 18:00","연속"]
[54,"광주전남","순천","서순천주암HP T/L","154kV 소라-서순천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-02 07:00","2024-08-02 18:00","2024-08-02 07:00","2024-08-02 18:00","연속"]
[55,"광주전남","순천","서순천주암HP T/L","154kV 소라-서순천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-02 07:00","2024-08-02 18:00","취소","취소","연속"]
[56,"광주전남","순천","소라서순천#2 T/L","154kV 소라-서순천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-02 07:00","2024-08-02 18:00","취소","취소","연속"]
[57,"광주전남","순천","순천승주#2 T/L","154kV 순천-승주T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-01 16:00","2024-08-01 18:00","2024-08-01 16:00","2024-08-01 18:00","연속"]
[58,"광주전남","순천","계림승주#2 T/L","154kV 순천-승주T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-01 09:00","2024-08-01 16:00","2024-08-01 09:00","2024-08-01 16:00","연속"]
[59,"광주전남","순천","순천승주#1 T/L","154kV 순천-승주T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-01 07:00","2024-08-01 16:00","2024-08-01 07:00","2024-08-01 16:00","연속"]
[60,"광주전남","순천","계림승주#2 T/L","154kV 순천-승주T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-01 09:00","2024-08-01 16:00","취소","취소","연속"]
[61,"광주전남","순천","순천승주#1 T/L","154kV 순천-승주T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-01 07:00","2024-08-01 16:00","취소","취소","연속"]
[62,"광주전남","순천","율촌여수산단#2 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-29 07:00","2024-08-30 18:00","취소","취소","매일"]
[63,"광주전남","순천","율촌여수산단#1 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-26 07:00","2024-08-28 18:00","취소","취소","매일"]
[64,"광주전남","순천","용성여수산단#2 T/L","24-25년 순천전력지사 변전총액공사","여수산단 용성여수산단#2 T/L #1DS 가스누기조치","2024-08-13 09:00","2024-08-14 18:00","취소","취소","연속"]
[65,"광주전남","순천","용성여수산단#2 T/L","154kV 용성-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-13 07:00","2024-08-14 18:00","취소","취소","매일"]
[66,"광주전남","순천","율촌여수산단#2 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-29 07:00","2024-08-30 18:00","취소","취소","매일"]
[67,"광주전남","순천","율촌여수산단#1 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-26 07:00","2024-08-28 18:00","취소","취소","매일"]
[68,"광주전남","순천","용성여수산단#2 T/L","24-25년 순천전력지사 변전총액공사","여수산단 용성여수산단#2 T/L #1DS 가스누기조치","2024-08-13 09:00","2024-08-14 18:00","취소","취소","연속"]
[69,"광주전남","순천","용성여수산단#2 T/L","154kV 용성-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-13 07:00","2024-08-14 18:00","취소","취소","매일"]
[70,"광주전남","순천","여수T/P CB 6200","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-08-23 15:40","2024-08-23 16:00","취소","취소","연속"]
[71,"광주전남","순천","여수T/P SEC CB 60610","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-08-23 15:20","2024-08-23 15:40","취소","취소","연속"]
[72,"광주전남","순천","여수TP여천#1 T/L","154kV 여수TP-여천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-05 07:00","2024-08-06 18:00","취소","취소","매일"]
[73,"광주전남","순천","여수TP여천#2 T/L","154kV 여수TP-여천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-07 07:00","2024-08-08 18:00","취소","취소","매일"]
[74,"광주전남","순천","여수T/P #65 BUS","GS 칼텍스 여수#2T/L #2DS 가스누기해소 공사","#2DS 가스누기해소 공사","2024-08-08 09:00","2024-08-09 18:00","취소","취소","연속"]
[75,"광주전남","순천","여수TP용성#1 T/L","154kV 여수TP-용성T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-16 07:00","2024-08-16 13:00","취소","취소","연속"]
[76,"광주전남","순천","여수TP용성#2 T/L","154kV 여수TP-용성T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-16 13:00","2024-08-16 18:00","취소","취소","연속"]
[77,"광주전남","순천","여수T/P SEC CB 65660","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-08-23 15:00","2024-08-23 15:20","취소","취소","연속"]
[78,"광주전남","순천","여수T/P CB 6100","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-08-16 15:40","2024-08-16 16:00","취소","취소","연속"]
[79,"광주전남","순천","여수T/P SEC CB 60610","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-08-16 15:20","2024-08-16 15:40","취소","취소","연속"]
[80,"광주전남","순천","여수T/P SEC CB 65660","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-08-16 15:00","2024-08-16 15:20","취소","취소","연속"]
[81,"광주전남","순천","여수TP용성#2 T/L","154kV 여수TP-용성T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-16 13:00","2024-08-16 18:00","취소","취소","연속"]
[82,"광주전남","순천","여수TP용성#1 T/L","154kV 여수TP-용성T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-16 07:00","2024-08-16 13:00","취소","취소","연속"]
[83,"광주전남","순천","여수T/P #65 BUS","GS 칼텍스 여수#2T/L #2DS 가스누기해소 공사","#2DS 가스누기해소 공사","2024-08-08 09:00","2024-08-09 18:00","취소","취소","연속"]
[84,"광주전남","순천","여수TP여천#2 T/L","154kV 여수TP-여천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-07 07:00","2024-08-08 18:00","취소","취소","매일"]
[85,"광주전남","순천","여수TP여천#1 T/L","154kV 여수TP-여천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-08-05 07:00","2024-08-06 18:00","취소","취소","매일"]
[86,"광주전남","순천","여수T/P CB 6200","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-08-23 15:40","2024-08-23 16:00","취소","취소","연속"]
[87,"광주전남","순천","여수T/P SEC CB 60610","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-08-23 15:20","2024-08-23 15:40","취소","취소","연속"]
[88,"광주전남","순천","여수T/P SEC CB 65660","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-08-23 15:00","2024-08-23 15:20","취소","취소","연속"]
[89,"광주전남","순천","여수T/P CB 6100","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-08-16 15:40","2024-08-16 16:00","취소","취소","연속"]
[90,"광주전남","순천","여수T/P SEC CB 60610","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-08-16 15:20","2024-08-16 15:40","취소","취소","연속"]
[91,"광주전남","순천","여수T/P SEC CB 65660","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-08-16 15:00","2024-08-16 15:20","취소","취소","연속"]
[92,"광주전남","순천","여수TP용성#1 T/L","용성S/S 여수TP-용성#1T/L GIS 불량 유압력계 교체","GIS 불량 유압력계 교체","2024-08-15 09:00","2024-08-16 18:00","취소","취소","연속"]
[93,"광주전남","순천","여수TP용성#1 T/L","용성S/S 여수TP-용성#1T/L GIS 불량 유압력계 교체","GIS 불량 유압력계 교체","2024-08-15 09:00","2024-08-16 18:00","취소","취소","연속"]
[94,"광주전남","순천","태금하동#1 T/L","효성제 170kv gis 부품 교체 시행","효성제 170kv gis 부품 교체 시행(즉시가압불가)","2024-08-05 09:00","2024-08-05 18:00","2024-08-05 09:00","2024-08-05 18:00","연속"]
[95,"광주전남","순천","태금하동화력 T/L","효성제 170kv gis 부품 교체 시행","효성제 170kv gis 부품 교체 시행(즉시가압불가)","2024-08-06 09:00","2024-08-06 18:00","2024-08-06 09:00","2024-08-06 18:00","연속"]
[96,"광주전남","순천","태금하동#1 T/L","효성제 170kv gis 부품 교체 시행","효성제 170kv gis 부품 교체 시행(즉시가압불가)","2024-08-05 09:00","2024-08-05 18:00","취소","취소","연속"]
[97,"광주전남","순천","태금하동화력 T/L","효성제 170kv gis 부품 교체 시행","효성제 170kv gis 부품 교체 시행(즉시가압불가)","2024-08-06 09:00","2024-08-06 18:00","취소","취소","연속"]
[98,"대구","달성","다사달서 T/L","강창달서 등 2개T/L EBA애관 교체공사","강창달서 등 2개T/L EBA애관 교체공사(해체점검 후속조치)","2024-08-06 09:00","2024-08-08 18:00","2024-08-06 09:00","2024-08-08 18:00","연속"]
[99,"대구","달성","상인봉덕#1 T/L","154kV 상인-봉덕 지중T/L 지장송전선로 이설공사","154kV 상인-봉덕 지중T/L 지장송전선로 이설공사","2024-08-26 09:00","2024-09-13 18:00","취소","취소","연속"]
[100,"대구","포항","건천천북#1 T/L","154kV 건천-천북T/L 지장송전선로 이설공사","철탑2기 설치 및 철거, 전력선 교체 3.355km","2024-08-19 07:00","2024-08-30 18:00","2024-08-19 07:00","2024-08-30 18:00","연속"]
[101,"대구","포항","건천천북#2 T/L","154kV 건천-천북T/L 지장송전선로 이설공사","철탑2기 설치 및 철거, 전력선 교체 3.355km","2024-08-19 07:00","2024-08-30 18:00","2024-08-19 07:00","2024-08-30 18:00","연속"]
[102,"대구","포항","신영일청하#2 T/L","2024~25년도 포항전력지사 변전총액공사","신영일S/S 무인화 관련 제어포인트 시험","2024-08-01 09:00","2024-08-01 18:00","2024-08-01 09:00","2024-08-01 18:00","연속"]
[103,"경북","직할","안동동안동#1 T/L","154kV 안동-동안동T/L 용량증대 선종교체공사","154kV 안동-동안동T/L #2T/L No.18~23 선종교체","2024-08-05 08:00","2024-08-07 18:00","취소","취소","연속"]
[104,"경북","직할","안동동안동#2 T/L","154kV 안동-동안동T/L 용량증대 선종교체공사","154kV 안동-동안동#2T/L No.18~23 선종교체","2024-08-05 08:00","2024-08-07 18:00","취소","취소","연속"]
[105,"경북","직할","안동풍산 T/L","154㎸ 안동-풍산T/L 29~31호간 지장이설공사(요청자 직접시행)","1. 대상선로 : 154㎸ 안동-풍산T/L 2. 공사구간 : No.29 ~ No.31(HSTACIR/AW 240㎟(단도체), 1회선) 3. 공사내역 : 송전선로 설치(신설 No.30-1) 및 전력선 가선","2024-08-01 08:00","2024-08-04 18:00","취소","취소","연속"]
[106,"부산울산","울산","신울산매암#3 T/L","신울산S/S 154kV 현대화공사","신울산S/S 구내 신울산-매암#3T/L 인출변경","2024-08-19 09:00","2024-09-13 18:00","취소","취소","연속"]
[107,"부산울산","울산","언양산막#1 T/L","154kV 석계분기T/L 건설공사","지지물 : 154kV 산형강철탑 5기 전력선 : ACSR 410 * 2B * 4C","2024-08-12 07:00","2024-08-15 18:00","2024-08-12 07:00","2024-08-15 18:00","연속"]
[108,"부산울산","울산","언양산막#2 T/L","154kV 석계분기T/L 건설공사","지지물 : 154kV 산형강철탑 5기 전력선 : ACSR 410 * 2B * 4C","2024-08-16 07:00","2024-08-19 18:00","2024-08-16 07:00","2024-08-19 18:00","연속"]