{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":16,"n_cols":11,"rows_kept":16,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2024년도 9월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기","성남","신중부신안성#1 T/L"," 2024년 성남전력 765 GIS 보통, 345 GIS 정밀점검공사","8800, 8871 GIS 보통점검","2024-09-09 09:00","2024-09-10 18:00","2024-09-09 09:00","2024-09-10 18:00","연속"]
[2,"경기","성남","신안성S/S CB 8671"," 2024년 성남전력 765kV GIS 정밀점검공사","8671 차단기 정밀점검","2024-09-23 09:00","2024-10-04 18:00","2024-09-23 09:00","2024-10-04 18:00","연속"]
[3,"대전세종충남","서산","당진T/P CB 8371","24년 서산P/O 765kV GIS 보통점검공사","(즉시가압 가능) 당진화력S/S 765kV 8371 CB 보통점검 및 보호계전기 교체","2024-09-23 09:30","2024-09-24 18:00","2024-09-23 09:30","2024-09-24 18:00","연속"]
[4,"대전세종충남","서산","당진T/P CB 8300","24년 서산P/O 765kV GIS 보통점검공사","(즉시가압 가능) 당진화력S/S 765kV 8300 CB 보통점검 및 보호계전기 교체","2024-09-11 09:30","2024-09-12 18:00","2024-09-11 09:30","2024-09-12 18:00","연속"]
[5,"대전세종충남","서산","당진T/P CB 8372","24년 서산P/O 765kV GIS 보통점검공사","(즉시가압 가능) 당진화력S/S 765kV 8372 CB 보통점검 및 보호계전기 교체","2024-09-09 09:30","2024-09-10 18:00","2024-09-09 09:30","2024-09-10 18:00","연속"]
[6,"대전세종충남","서산","당진T/P CB 8471","24년 서산P/O 765kV GIS 보통점검공사","(즉시가압 가능) 당진화력S/S 765kV 8471 CB 보통점검 및 보호계전기 교체","2024-09-25 09:30","2024-09-26 18:00","2024-09-25 09:30","2024-09-26 18:00","연속"]
[7,"대전세종충남","서산","신서산S/S CB 8372","24년 서산P/O 765kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 765kV 8372 CB 보통점검 및 보호계전기 교체","2024-09-02 09:30","2024-09-03 18:00","2024-09-02 09:30","2024-09-03 18:00","연속"]
[8,"대전세종충남","서산","신서산S/S CB 8671","24년 서산P/O 765kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 765kV 8671 CB 보통점검 및 보호계전기 교체","2024-09-30 09:30","2024-10-01 18:00","2024-09-30 09:30","2024-10-01 18:00","연속"]
[9,"대전세종충남","서산","신서산S/S #3 M.Tr","'24년 서산P/O 변전협력회사 총액공사","(즉시가압 불가) 신서산S/S 765kV #3M.Tr 보통점검","2024-09-30 09:30","2024-10-11 18:00","취소","취소","연속"]
[10,"대전세종충남","서산","신서산S/S CB 8300","24년 서산P/O 765kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 765kV 8300 CB 보통점검 및 보호계전기 교체","2024-09-04 09:30","2024-09-05 18:00","2024-09-04 09:30","2024-09-05 18:00","연속"]
[11,"경북","영주","신한울N/P #2 Tie-Tr","신한울S/S 765kV #1,2M.Tr 보통점검 공사","신한울S/S 765kV #2M.Tr 보통점검 공사","2024-09-09 09:00","2024-09-13 18:00","취소","취소","연속"]
[12,"경북","영주","신한울N/P #1 Tie-Tr","신한울S/S 765kV #1,2M.Tr 보통점검 공사","신한울S/S 765kV #1M.Tr 보통점검 공사","2024-09-02 09:00","2024-09-06 18:00","취소","취소","연속"]

{"sheet":"345설비","index":1,"n_rows":381,"n_cols":11,"rows_kept":381,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2024년도 9월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #2 M.Tr","2024~25년 성동전력지사 변전협력회사 공사","B/F PNL 대체","2024-09-23 10:00","2024-09-27 18:00","취소","취소","연속"]
[2,"서울","성동","미금성동#2 T/L","2024~25년 성동전력지사 변전협력회사 공사","- B/F PNL 대체","2024-09-23 10:00","2024-09-27 18:00","취소","취소","연속"]
[3,"서울","중부","중부S/S #1 M.Tr","2024년 중부전력지사 변전정비 협력회사 총액공사","1차 PT A, B, C 보통점검 3차 LA A, B, C 보통점검 3차 PT A, B, C 보통점검","2024-09-02 10:00","2024-09-02 18:00","2024-09-02 10:00","2024-09-02 18:00","연속"]
[4,"서울","중부","중부S/S #2 M.Tr","중부S/S 154kV 장기사용 GIS 교체공사(3차)","- 154kV GIS 교체(#2M.Tr 2차, 중부연대T/L, 중부마포T/L) - 기타 부대공사","2024-09-11 09:00","2024-10-18 18:00","2024-09-11 09:00","2024-10-18 18:00","연속"]
[5,"서울","중부","중부S/S #3 M.Tr","중부S/S 154kV 장기사용 GIS 교체공사(3차)","- 154kV GIS 교체(#2M.Tr 2차, 중부연대T/L, 중부마포T/L) 관련 시험가압 설비","2024-09-13 15:00","2024-09-13 18:00","2024-09-13 15:00","2024-09-13 18:00","연속"]
[6,"서울","중부","중부S/S #2 M.Tr","2024년 중부전력지사 변전정비 협력회사 총액공사","#2M.Tr 보통점검, 물청소 1차 7272CB 조작시험 1차 PT A, B, C상 보통점검 3차 LA A, B, C상 보통점검 3차 PT A, B, C상 보통점검 추락방지장치 설치","2024-09-03 10:00","2024-09-05 18:00","2024-09-04 10:00","2024-09-06 18:00","연속"]
[7,"남서울","강남","신성남신양재#2 T/L","345kV 신성남-신양재T/L 유지접속함(8상) 교체공사 2차분","○ 345kV 신성남-신양재T/L 잔여 유지접속함 8상 추가 교체 - J/B#24번 : #1T/L A,B,C상(완료) - J/B#18번 : #2T/L A,B,C상(9~10월), #1T/L B,C상(10~12월)","2024-09-02 09:00","2024-10-21 09:00","2024-09-02 09:00","2024-10-21 09:00","연속"]
[8,"남서울","동서울","신용인동서울#1 T/L","345kV 동서울S/S 종합정비공사","500kV 동서울변환소 부지확보 관련 사전 정비공사 - 345kV GIS 제어케이블 이설","2024-09-02 09:00","2024-09-30 18:00","2024-09-02 09:00","2024-09-30 18:00","연속"]
[9,"남서울","영등포","서서울신광명#2 T/L","남광명분기 전력구공사 1단계","광명·시흥 도시첨단산업단지 및 신안산선 전철 신규부하 공급을 위해 기설 345kV 서서울-신광명T/L을 지중화하여 신설 345kV 신목감S/S에 연결하는 전력구 공사","2024-09-23 09:00","2024-10-18 18:00","2024-09-23 09:00","2024-10-18 18:00","연속"]
[10,"남서울","영등포","신광명S/S #1 M.Tr","345kV 신광명S/S #1M.Tr 교체공사","노후 주변압기 #1M.Tr 교체","2024-09-02 09:00","2024-10-18 18:00","2024-09-02 09:00","2024-10-18 18:00","연속"]
[11,"남서울","영등포","서서울신광명#1 T/L","2024~25년 가공송전 협력회사 공사(수직, 수평 추락방지장치 설치)","345kV 서서울-신광명#1T/L 추락방지장치 설치 - No.22,24호 수직 추락방지장치 미설치 개소 설치 - 38개소 수평 추락방지장치 설치","2024-09-02 07:00","2024-09-11 18:00","2024-09-02 07:00","2024-09-11 18:00","연속"]
[12,"남서울","직할","신광명신문래#2 T/L","신문래S/S 차단부 절연열화 진단","신문래S/S 차단부 절연열화 진단","2024-09-12 09:00","2024-09-12 18:00","2024-09-12 09:00","2024-09-12 18:00","연속"]
[13,"인천","김포","가정개폐소 CB 7171","가정개폐소 345kV #2 Sh.R 1차 GIS (7171) 조작시험","가정개폐소 345kV #2 Sh.R 1차 GIS (7171) 조작시험","2024-09-13 09:00","2024-09-13 18:00","2024-09-13 09:00","2024-09-13 18:00","연속"]
[14,"인천","김포","신김포S/S SEC CB 70710","신김포S/S 345kV #70-#71 SEC GIS 보통점검","신김포S/S 345kV #70-#71 SEC GIS 보통점검","2024-09-19 10:00","2024-09-19 18:00","2024-09-19 10:00","2024-09-19 18:00","연속"]
[15,"인천","김포","신김포S/S SEC CB 75760","신김포S/S 345kV #75-#76 SEC GIS 보통점검","신김포S/S 345kV #75-#76 SEC GIS 보통점검","2024-09-20 10:00","2024-09-20 18:00","2024-09-20 10:00","2024-09-20 18:00","연속"]
[16,"인천","김포","신김포서인천CC T/L","2024년 가공송전 순시점검 위탁공사","송전선로 애자오염 시스템 시범적용을 위한 설치 작업","2024-09-23 09:00","2024-09-23 18:00","2024-09-23 09:00","2024-09-23 18:00","연속"]
[17,"인천","부평","서인천C/C CB 7472","서인천C/C 345kV #4 M.Tr 1차 7472GIS 조작시험","서인천C/C 345kV #4 M.Tr 1차 7472GIS 조작시험","2024-09-05 12:00","2024-09-05 18:00","2024-09-05 12:00","2024-09-05 18:00","연속"]
[18,"인천","부평","서인천C/C CB 7471","서인천C/C 서인천CC-신부평#3T/L 7471GIS 조작시험","서인천C/C 서인천CC-신부평#3T/L 7471GIS 조작시험","2024-09-05 09:00","2024-09-05 12:00","2024-09-05 09:00","2024-09-05 12:00","연속"]
[19,"인천","부평","서인천C/C CB 7372","서인천C/C 345kV #3 M.Tr 1차 7372GIS 조작시험","서인천C/C 345kV #3 M.Tr 1차 7372GIS 조작시험","2024-09-04 09:00","2024-09-04 12:00","2024-09-04 09:00","2024-09-04 12:00","연속"]
[20,"인천","부평","서인천C/C CB 7400","서인천신부평#3T/L-#4M.Tr TIE 7400GIS 조작시험","서인천C/C 서인천신부평#3T/L-#4M.Tr TIE 7400GIS 조작시험","2024-09-04 12:00","2024-09-04 18:00","2024-09-04 12:00","2024-09-04 18:00","연속"]
[21,"인천","부평","신가좌S/S CB 7472","신가좌S/S 345kV #3 M.Tr 1차 GIS 조작시험","신가좌S/S 345kV #3 M.Tr 1차 GIS 및 절연열화 측정","2024-09-13 09:00","2024-09-13 18:00","2024-09-13 09:00","2024-09-13 12:00","연속"]
[22,"인천","부평","신가좌S/S #2 BUS","신가좌S/S 345kV #2 BUS 모선보호반 교체","신가좌S/S 345kV #2 BUS 모선보호반 교체 및 #3GROP GIS 절연열화","2024-09-30 09:00","2024-10-04 18:00","2024-09-30 09:00","2024-10-04 18:00","연속"]
[23,"인천","부평","신가좌S/S CB 7471","신가좌S/S 345kV 신가좌-신시흥#2T/L GIS 정밀점검","신가좌S/S 345kV 신가좌-신시흥#2T/L GIS 정밀점검 (7471)","2024-09-27 09:00","2024-09-27 18:00","2024-09-27 09:00","2024-09-27 18:00","연속"]
[24,"인천","부평","신가좌S/S CB 7371","신가좌S/S 345kV 신가좌신시흥#1T/L GIS 조작시험","신가좌S/S 345kV 신가좌신시흥#1T/L GIS 조작시험 및 절연열화 측정","2024-09-13 12:00","2024-09-13 18:00","2024-09-13 12:00","2024-09-13 18:00","연속"]
[25,"인천","부평","신경서서인천CC T/L","신경서서인천CC T/L 보호반 교체 공사","신경서서인천CC T/L 보호반 교체 공사","2024-09-09 09:00","2024-09-13 18:00","2024-09-09 09:00","2024-09-13 18:00","연속"]
[26,"인천","부평","신경서S/S CB 7571","신경서S/S 345kV 신경서-포스코S/Y#2T/L GIS 조작시험","신경서S/S 345kV 신경서-포스코S/Y#2T/L GIS 조작시험","2024-09-02 12:00","2024-09-02 18:00","2024-09-02 12:00","2024-09-02 18:00","연속"]
[27,"인천","부평","신경서S/S CB 7371","신경서S/S 345kV 신경서-포스코S/Y#1T/L GIS 조작시험","신경서S/S 345kV 신경서-포스코S/Y#1T/L GIS 조작시험","2024-09-02 09:00","2024-09-02 12:00","2024-09-02 09:00","2024-09-02 12:00","연속"]
[28,"인천","부평","인천C/C CB 7500","인천CC 345kV 7500 GIS 휴전(7572 CB A상 대체)","인천CC S/Y 345kV 인천CC#3,4G/T-인천CC#1,2G/T TIE GIS 휴전 (7572 CB A상 대체)","2024-09-21 09:00","2024-09-24 18:00","2024-09-21 09:00","2024-09-24 18:00","연속"]
[29,"인천","부평","인천C/C #1 Sh.R CB","인천CC S/Y 345kV #1 Sh.R 휴전(7572 CB A상 대체)","인천CC S/Y 345kV #1 Sh.R 휴전 (7572 CB A상 대체)","2024-09-21 09:00","2024-09-21 18:00","2024-09-21 09:00","2024-09-21 18:00","연속"]
[30,"인천","부평","인천C/C CB 7472","인천CC 가정인천CC#1T/L CLR 휴전(7572 CB A상 대체)","인천CC S/Y 345kV 가정인천CC#1T/L CLR GIS 휴전 (7572 CB A상 대체)","2024-09-21 09:00","2024-09-21 18:00","2024-09-21 09:00","2024-09-21 18:00","연속"]
[31,"인천","부평","인천C/C #76 BUS","인천CC 345kV #76 BUS 휴전(7572 CB A상 대체)","인천CC S/Y 345kV #76 BUS 휴전(7572 CB A상 대체)","2024-09-21 09:00","2024-09-24 18:00","2024-09-21 09:00","2024-09-24 18:00","연속"]
[32,"인천","시흥","신시화S/S #3 M.Tr","신시화S/S 345kV #3 M.Tr 초기 및 하자점검","신시화S/S 345kV #3 M.Tr 초기 및 하자점검 - OLTC 초기점검 - 7400,7472 GIS 초기점검 병행 - #1S.Tr, #1S.Tr GIS 초기점검 병행","2024-09-23 09:00","2024-09-27 18:00","2024-09-23 09:00","2024-09-27 18:00","연속"]
[33,"인천","시흥","신시흥신시화#1 T/L","2024년 가공송전 순시점검 위탁공사(시흥전력)","애자오염진단시스템 설치","2024-09-09 09:00","2024-09-09 18:00","2024-09-09 09:00","2024-09-09 18:00","연속"]
[34,"인천","시흥","신시화S/S CB 7200","신시화S/S 362kV GIS 유압조작기 체크밸브 설치","신시화S/S 362kV GIS 유압조작기 체크밸브 설치(7200)","2024-09-09 09:00","2024-09-09 18:00","2024-09-09 09:00","2024-09-09 18:00","연속"]
[35,"인천","시흥","신시화S/S CB 7571","신시화S/S 362kV GIS 유압조작기 체크밸브 설치","신시화S/S 362kV GIS 유압조작기 체크밸브 설치(7571)","2024-09-10 09:00","2024-09-10 18:00","2024-09-10 09:00","2024-09-10 18:00","연속"]
[36,"인천","시흥","신시화S/S CB 7471","신시화S/S 362kV GIS 유압조작기 체크밸브 설치","신시화S/S 362kV GIS 유압조작기 체크밸브 설치(7471)","2024-09-19 09:00","2024-09-19 18:00","2024-09-19 09:00","2024-09-19 18:00","연속"]
[37,"인천","시흥","신시화S/S #2 M.Tr","신시화S/S 345kV #2 M.Tr 초기 및 하자점검","신시화S/S 345kV #2 M.Tr 초기 및 하자점검 - OLTC 초기점검 - 7300,7372 GIS 초기점검 병행","2024-09-02 09:00","2024-09-06 18:00","2024-09-02 09:00","2024-09-06 18:00","연속"]
[38,"인천","시흥","신시화S/S #1Sh.R CB","신시화S/S 345kV #1 Sh.R 초기점검","신시화S/S 345kV #1 Sh.R 초기점검 - 7671, 7600 GIS 초기점검 병행","2024-09-30 09:00","2024-10-02 18:00","2024-09-30 09:00","2024-10-02 18:00","매일"]
[39,"인천","시흥","신시화S/S CB 7271","신시화S/S 362kV GIS 유압조작기 체크밸브 설치","신시화S/S 362kV GIS 유압조작기 체크밸브 설치(7271)","2024-09-12 09:00","2024-09-12 18:00","2024-09-12 09:00","2024-09-12 18:00","연속"]
[40,"인천","시흥","신시화S/S CB 7371","신시화S/S 362kV GIS 유압조작기 체크밸브 설치","신시화S/S 362kV GIS 유압조작기 체크밸브 설치(7371)","2024-09-13 09:00","2024-09-13 18:00","2024-09-13 09:00","2024-09-13 18:00","연속"]
[41,"인천","시흥","신시화S/S CB 7500","신시화S/S 362kV GIS 유압조작기 체크밸브 설치","신시화S/S 362kV GIS 유압조작기 체크밸브 설치(7500)","2024-09-11 09:00","2024-09-11 18:00","2024-09-11 09:00","2024-09-11 18:00","연속"]
[42,"인천","시흥","신가좌신시흥#1 T/L","신시흥S/S 7B Bay B/F반 대체","신시흥S/S 7B Bay B/F반 대체 - #1M.Tr 보호반 대체 병행","2024-09-09 09:00","2024-09-13 18:00","취소","취소","연속"]
[43,"인천","시흥","신시흥#1S/S #1 M.Tr","신시흥S/S 7B Bay B/F반 대체","신시흥S/S 7B Bay B/F반 대체 - #1M.Tr 보호반 대체 병행","2024-09-09 09:00","2024-09-13 18:00","2024-09-09 09:00","2024-09-13 18:00","연속"]
[44,"인천","시흥","신시흥#1S/S CB 7B71","신시흥#1S/S 345kV 7B71 CB 균압콘덴서 절연열화측정","신시흥#1S/S 345kV 7B71 CB 균압콘덴서 절연열화측정","2024-09-05 09:00","2024-09-05 12:00","2024-09-05 09:00","2024-09-05 12:00","연속"]
[45,"인천","시흥","신가좌신시흥#1 T/L","24-25년 부평,김포전력지사 가공송전 협력회사 공사","[병행참여] 암교체 및 고정형폴리머점퍼지지애자 설치 ※ 병행공사(타공사) : 추락방지시설 하자조치","2024-09-09 07:30","2024-09-13 18:00","2024-09-09 07:30","2024-09-13 18:00","매일"]
[46,"인천","시흥","신시흥신광명#1 T/L","24-25년 부평,김포전력지사 가공송전 협력회사 공사","[병행참여] 고정형폴리머점퍼지지애자 설치 ※ 병행공사(타공사) : 추락방지시설 하자조치","2024-09-09 07:30","2024-09-13 18:00","2024-09-09 07:30","2024-09-13 18:00","매일"]
[47,"인천","시흥","신시흥신광명#2 T/L","24-25년 부평,김포전력지사 가공송전 협력회사 공사","고정형폴리머점퍼지지애자 및 피뢰기 설치 ※ 병행공사(타공사) : 추락방지시설 하자조치","2024-09-21 07:30","2024-09-22 18:00","2024-09-21 07:30","2024-09-22 18:00","매일"]
[48,"인천","시흥","신가좌신시흥#2 T/L","24-25년 부평,김포전력지사 가공송전 협력회사 공사","암 교체 및 고정형폴리머점퍼지지애자 설치 ※ 병행공사(타공사) : 추락방지시설 하자조치","2024-09-21 07:30","2024-09-22 18:00","2024-09-21 07:30","2024-09-22 18:00","매일"]
[49,"인천","시흥","신시흥#1S/S #2 M.Tr","신시흥S/S #2M.Tr 2차 GIS 베어링 교체","신시흥S/S #2M.Tr 2차 GIS 베어링 부품 교체","2024-09-20 09:00","2024-09-20 18:00","2024-09-20 09:00","2024-09-20 18:00","연속"]
[50,"인천","시흥","신시흥#1S/S CB 7800","신시흥#1S/S 345kV 7800 CB 균압콘덴서 절연열화측정","신시흥#1S/S 345kV 7800 CB 균압콘덴서 절연열화측정","2024-09-27 09:00","2024-09-27 14:00","취소","취소","연속"]
[51,"인천","시흥","신시흥#1S/S #3 M.Tr","신시흥S/S 345kV #3M.Tr 2차 GIS 정밀점검","신시흥S/S 345kV #3M.Tr 2차 GIS 정밀점검","2024-09-30 08:00","2024-10-02 18:00","2024-09-30 08:00","2024-10-02 18:00","연속"]
[52,"인천","시흥","신시흥#2S/S CB 7600","신시흥S/S 345kV 7600 CB 균압콘덴서 절연열화 측정","신시흥S/S 345kV 7600 CB 균압콘덴서 절연열화 측정","2024-09-03 14:00","2024-09-03 18:00","2024-09-03 14:00","2024-09-03 18:00","연속"]
[53,"인천","시흥","영흥T/P CB 7800","영흥#2S/Y 345kV 7800 CB 균압콘덴서 절연열화 측정","영흥#2S/Y 345kV 7800 CB 균압콘덴서 절연열화 측정","2024-09-10 12:00","2024-09-10 15:00","2024-09-10 12:00","2024-09-10 15:00","연속"]
[54,"인천","시흥","영흥T/P CB 7772","영흥#2S/Y 345kV 7772 CB 균압콘덴서 절연열화 측정","영흥#2S/Y 345kV 7772 CB 균압콘덴서 절연열화 측정","2024-09-10 15:00","2024-09-10 18:00","2024-09-10 15:00","2024-09-10 18:00","연속"]
[55,"인천","시흥","영흥T/P CB 7871","영흥#2S/Y 345kV 7871 CB 균압콘덴서 절연열화 측정","영흥#2S/Y 345kV 7871 CB 균압콘덴서 절연열화 측정","2024-09-10 09:00","2024-09-10 12:00","2024-09-10 09:00","2024-09-10 12:00","연속"]
[56,"인천","시흥","신시흥영흥TP#1 T/L","영흥#2S/Y 345kV 7771, 7700 GIS 보통점검","영흥#2S/Y 345kV 신시흥영흥TP#1T/L(7771), 신시흥영흥TP#1T/L-#6G/T TIE(7700) GIS 보통점검 - 균압콘덴서 절연열화 측정 병행","2024-09-19 09:00","2024-09-19 18:00","2024-09-19 09:00","2024-09-19 18:00","연속"]
[57,"인천","시흥","신시흥영흥TP#2 T/L","영흥S/Y 345kV #74Bay B/F 보호반 대체","영흥S/Y 345kV #74Bay B/F 보호반 대체","2024-09-23 09:00","2024-09-27 18:00","2024-09-23 09:00","2024-09-27 18:00","연속"]
[58,"인천","시흥","영흥T/P CB 7100","영흥#1S/Y 345kV 7100 CB 균압콘덴서 절연열화측정","영흥#1S/Y 345kV 7100 CB 균압콘덴서 절연열화측정","2024-09-04 09:00","2024-09-04 14:00","2024-09-04 09:00","2024-09-04 14:00","연속"]
[59,"인천","시흥","영흥T/P CB 7172","영흥#1S/Y 345kV 7172 CB 균압콘덴서 절연열화측정","영흥#1S/Y 345kV 7172 CB 균압콘덴서 절연열화측정","2024-09-04 14:00","2024-09-04 18:00","2024-09-04 14:00","2024-09-04 18:00","연속"]
[60,"인천","시흥","영흥T/P CB 7200","영흥#1S/Y 345kV 7200 CB 균압콘덴서 절연열화측정","영흥#1S/Y 345kV 7200 CB 균압콘덴서 절연열화측정","2024-09-11 09:00","2024-09-11 14:00","2024-09-11 09:00","2024-09-11 14:00","연속"]
[61,"인천","시흥","영흥T/P CB 7272","영흥#1S/Y 345kV 7272 CB 균압콘덴서 절연열화측정","영흥#1S/Y 345kV 7272 CB 균압콘덴서 절연열화측정","2024-09-11 14:00","2024-09-11 18:00","2024-09-11 14:00","2024-09-11 18:00","연속"]
[62,"인천","시흥","영흥T/P CB 7472","영흥S/Y 345kV #74Bay B/F 보호반 대체","영흥S/Y 345kV #74Bay B/F 보호반 대체","2024-09-23 09:00","2024-09-27 18:00","2024-09-23 09:00","2024-09-27 18:00","연속"]
[63,"인천","직할","갈산S/S #75 BUS","갈산S/S #4M.Tr 증설공사","갈산S/S #4M.Tr 증설공사 관련 7752 가스밸브 보수작업","2024-09-10 09:00","2024-09-11 16:00","2024-09-10 09:00","2024-09-11 16:00","연속"]
[64,"경기북부","고양","신덕은동두천CC#1 T/L","24~25년 고양전력지사 변전협력회사 공사","362kV GIS 보통점검(7571, 7500)","2024-09-30 09:00","2024-10-01 18:00","취소","취소","연속"]
[65,"경기북부","고양","신덕은S/S #3 M.Tr","24~25년 고양전력지사 변전협력회사 공사","345kV GIS 절연열화 측정(7371,7300)","2024-09-02 09:00","2024-09-03 18:00","취소","취소","연속"]
[66,"경기북부","고양","신덕은S/S #1 BUS","24~25년 고양전력지사 변전협력회사 공사","345kV GIS 절연열화 측정(7371)","2024-09-02 09:00","2024-09-02 18:00","2024-09-02 09:00","2024-09-02 18:00","연속"]
[67,"경기북부","고양","신덕은S/S #4 M.Tr","24~25년 고양전력지사 변전협력회사 총액공사","345kV #4M.Tr 주변압기 누유개소 점검","2024-09-04 09:00","2024-09-06 18:00","2024-09-09 09:00","2024-09-11 18:00","연속"]
[68,"경기북부","고양","신덕은동두천CC#2 T/L","고양전력지사 가공송전협력공사","추락방지장치(수평) 설치","2024-09-03 07:00","2024-09-13 18:00","2024-09-03 07:00","2024-09-13 18:00","연속"]
[69,"경기북부","고양","신덕은파주문산CC#2 T/L","24~25년 고양전력지사 변전협력회사 공사","345kV GIS 절연열화 측정(7300)","2024-09-03 09:00","2024-09-03 18:00","2024-09-03 09:00","2024-09-03 18:00","연속"]
[70,"경기북부","고양","신파주신덕은#1 T/L","고양전력 가공송전협력공사","추락방지장치(수평) 설치","2024-09-30 07:00","2024-10-02 18:00","2024-09-30 07:00","2024-10-02 18:00","연속"]
[71,"경기북부","구리","동서울미금#1 T/L","345kV 미금S/S 용량부족 차단기 대체공사(동서울S/S 인출DS 개방 및 #71Bay 투입)","용량부족 차단기 대체공사 25CCT(동서울S/S 인출DS 개방 및 #71Bay 투입)","2024-09-02 09:00","2024-12-20 18:00","2024-08-26 09:00","2024-12-20 18:00","연속"]
[72,"경기북부","구리","미금S/S #2 M.Tr","345kV 미금S/S 용량부족 차단기 대체공사","용량부족 차단기 대체공사 25CCT","2024-09-19 09:00","2024-12-20 18:00","2024-09-19 09:00","2024-12-20 18:00","연속"]
[73,"경기북부","구리","미금S/S CB 7271","24~25년 구리전력지사 변전협력회사 공사","미금S/S 7271,7200 GIS 조작시험 및 절연열화 측정","2024-09-10 09:00","2024-09-10 14:00","2024-09-10 09:00","2024-09-10 14:00","연속"]
[74,"경기북부","구리","미금S/S CB 7200","24~25년 구리전력지사 변전협력회사 공사","미금S/S 7271,7200 GIS 조작시험 및 절연열화 측정","2024-09-10 14:00","2024-09-10 18:00","2024-09-10 14:00","2024-09-10 18:00","연속"]
[75,"경기북부","구리","미금S/S #6 Sh.R CB","2024~25년 구리전력 변전협력회사 공사","신가평S/S 345kV #4M.Tr 2차 - 신가평미금#2TL 7800 GIS 절연열화 측정 미금S/S 345kV #6Sh.R #6Sh.R 7679 GIS 조작시험, 절연열화 측정","2024-09-12 09:00","2024-09-12 14:00","2024-09-12 09:00","2024-09-12 14:00","연속"]
[76,"경기북부","구리","미금S/S #3 M.Tr","24-25년 구리전력지사 변전협력회사 총액공사","미금S/S 345kV #3M.Tr 보호반 대체공사 - 구PNL 철거 및 신PNL 입상 - 신규 케이블 결선 - 연동시험 및 준공시험","2024-09-09 09:00","2024-09-13 18:00","2024-09-09 09:00","2024-09-13 18:00","연속"]
[77,"경기북부","구리","미금S/S #4 M.Tr","24-25 구리전력 변전협력 총액공사","345kV M.Tr 초기점검","2024-09-02 09:00","2024-09-04 18:00","취소","취소","연속"]
[78,"경기북부","구리","신가평신의정부#2 T/L","신가평S/S 345kV GIS 모선 용량대체 공사(전문)","345kV #75BUS 75bay 측 주모선 철거 안전이격 345kV #7552 DS 철거 안전이격","2024-09-30 08:00","2024-10-02 13:00","2024-09-30 08:00","2024-10-02 13:00","연속"]
[79,"경기북부","구리","신가평신의정부#1 T/L","신가평S/S 345kV GIS 모선 용량대체 공사(전문)","345kV #75BUS 76bay 측 주모선 철거 안전이격 345kV #7652 DS 철거 안전이격","2024-09-25 13:00","2024-09-30 08:00","2024-09-25 13:00","2024-09-30 08:00","연속"]
[80,"경기북부","구리","신가평미금#2 T/L","신가평S/S 345kV GIS 모선 용량대체 공사(전문)","345kV #75BUS 78bay 측 주모선 철거 안전이격 345kV #7852 DS 철거 안전이격","2024-09-19 08:00","2024-09-23 08:00","2024-09-19 08:00","2024-09-23 08:00","연속"]
[81,"경기북부","구리","신가평S/S #2 BUS","신가평S/S 345kV GIS 모선 용량대체 공사(전문)","345kV #75BUS 용량대체(63kA 4000A - 63kA 6300A) 345kV #75BUS 모선PT대체 345kV #75BUS측 52DS대체(7352~7852)","2024-09-05 09:00","2024-11-29 18:00","2024-09-05 09:00","2024-11-29 18:00","연속"]
[82,"경기북부","구리","신가평S/S CB 7572","24-25년 구리전력지사 변전협력회사 총액공사","신가평S/S 7502DS A상 부분방전 발생(플로팅)관련 점검 - 7502DS A상 내부점검 및 예상부품 교체","2024-09-03 19:00","2024-09-04 18:00","2024-09-03 19:00","2024-09-04 18:00","연속"]
[83,"경기북부","구리","신가평S/S CB 7500","24-25년 구리전력지사 변전협력회사 총액공사","신가평S/S 7502DS A상 부분방전 발생(플로팅)관련 점검 - 7502DS A상 내부점검 및 예상부품 교체","2024-09-03 19:00","2024-09-04 18:00","2024-09-03 19:00","2024-09-04 18:00","연속"]
[84,"경기북부","구리","신가평미금#1 T/L","신가평S/S 345kV GIS 모선 용량대체 공사(전문)","345kV #75BUS 77bay 측 주모선 철거 안전이격 345kV #7752 DS 철거 안전이격","2024-09-23 08:00","2024-09-25 13:00","2024-09-23 08:00","2024-09-25 13:00","연속"]
[85,"경기북부","구리","신포천S/S CB 7471","24~25년 구리전력지사 변전협력회사 공사","신포천S/S 74BAY 조작시험 - 신포천-포천CC #2T/L 7471 조작시험 - 신포천-포천CC #2T/L - #3M.Tr 1차 GIS 7400 조작시험 - #3M.Tr 1차 GIS 7472 조작시험","2024-09-24 09:00","2024-09-24 12:00","2024-09-24 09:00","2024-09-24 12:00","연속"]
[86,"경기북부","구리","신포천S/S #1 Sh.R CB","24~25년 구리전력지사 변전협력회사 공사","신포천S/S 73BAY 조작시험 - 신포천-포천CC #1T/L 7371 조작시험 - 신포천-포천CC #1T/L - #1Sh.R 1차 GIS 7300 조작시험 - #1Sh.R 1차 GIS 7372 조작시험","2024-09-23 15:00","2024-09-23 18:00","2024-09-23 15:00","2024-09-23 18:00","매일"]
[87,"경기북부","구리","신포천S/S CB 7300","24~25년 구리전력지사 변전협력회사 공사","신포천S/S 73BAY 조작시험 - 신포천-포천CC #1T/L 7371 조작시험 - 신포천-포천CC #1T/L - #1Sh.R 1차 GIS 7300 조작시험 - #1Sh.R 1차 GIS 7372 조작시험","2024-09-23 13:00","2024-09-23 15:00","2024-09-23 13:00","2024-09-23 15:00","매일"]
[88,"경기북부","구리","신포천S/S CB 7371","24~25년 구리전력지사 변전협력회사 공사","신포천S/S 73BAY 조작시험 - 신포천-포천CC #1T/L 7371 조작시험 - 신포천-포천CC #1T/L - #1Sh.R 1차 GIS 7300 조작시험 - #1Sh.R 1차 GIS 7372 조작시험","2024-09-23 09:00","2024-09-23 12:00","2024-09-23 09:00","2024-09-23 12:00","연속"]
[89,"경기북부","구리","신포천S/S CB 7671","24~25년 구리전력지사 변전협력회사 공사","신포천S/S 조작시험 - 신포천S/S #1Sh.R GIS 7379 조작시험 - 신포천S/S 신포천-동두천CC #TL GIS 7671 조작시험","2024-09-26 14:00","2024-09-26 18:00","2024-09-26 14:00","2024-09-26 18:00","연속"]
[90,"경기북부","구리","신포천S/S CB 7372","24~25년 구리전력지사 변전협력회사 공사","신포천S/S 조작시험 - 신포천S/S #1Sh.R GIS 7379 조작시험 - 신포천S/S 신포천-동두천CC #TL GIS 7671 조작시험","2024-09-26 09:00","2024-09-26 14:00","2024-09-26 09:00","2024-09-26 14:00","연속"]
[91,"경기북부","구리","신포천S/S CB 7500","24~25년 구리전력지사 변전협력회사 공사","신포천S/S 75BAY 조작시험 - 신포천-동두천CC #1T/L 7571 조작시험 - 신포천-동두천CC #1T/L - TIE GIS 7500 조작시험 - 신포천S/S #1Sh.R GIS 7379 조작시험","2024-09-25 13:00","2024-09-25 15:00","2024-09-25 13:00","2024-09-25 15:00","연속"]
[92,"경기북부","구리","신포천S/S CB 7571","24~25년 구리전력지사 변전협력회사 공사","신포천S/S 75BAY 조작시험 - 신포천-동두천CC #1T/L 7571 조작시험 - 신포천-동두천CC #1T/L - TIE GIS 7500 조작시험 - 신포천S/S #1Sh.R GIS 7379 조작시험","2024-09-25 09:00","2024-09-25 12:00","2024-09-25 09:00","2024-09-25 12:00","연속"]
[93,"경기북부","구리","신포천S/S CB 7472","24~25년 구리전력지사 변전협력회사 공사","신포천S/S 74BAY 조작시험 - 신포천-포천CC #2T/L 7471 조작시험 - 신포천-포천CC #2T/L - #3M.Tr 1차 GIS 7400 조작시험 - #3M.Tr 1차 GIS 7472 조작시험","2024-09-24 15:00","2024-09-24 18:00","2024-09-24 15:00","2024-09-24 18:00","연속"]
[94,"경기북부","구리","신포천S/S CB 7400","24~25년 구리전력지사 변전협력회사 공사","신포천S/S 74BAY 조작시험 - 신포천-포천CC #2T/L 7471 조작시험 - 신포천-포천CC #2T/L - #3M.Tr 1차 GIS 7400 조작시험 - #3M.Tr 1차 GIS 7472 조작시험","2024-09-24 13:00","2024-09-24 15:00","2024-09-24 13:00","2024-09-24 15:00","연속"]
[95,"경기북부","구리","포천C/C CB 7200","2024~25 구리전력 변전협력 총액공사","포천C/C #2S/U - #3S/U Tr GIS 7200 가스압력계 교체 및 경보시험","2024-09-03 09:00","2024-09-03 18:00","2024-09-03 09:00","2024-09-03 18:00","연속"]
[96,"경기북부","구리","포천LNGC/C #2 BUS","24-25년 구리전력지사 변전협력회사 총액공사","포천LNG C/C 345kV #2BUS PT 방수처리 - 모선 휴전(7172,7272,7372,7400CB 개방) 방수처리","2024-09-02 09:00","2024-09-04 18:00","2024-09-02 09:00","2024-09-04 18:00","연속"]
[97,"경기북부","직할","신의정부S/S #4 M.Tr","경기북부 직할 및 양주전력TF 362, 170kV GIS 보통점검 공사","신의정부S/S #4M.Tr 2차 GIS 보통점검","2024-09-23 09:00","2024-09-23 18:00","2024-09-23 09:00","2024-09-23 18:00","연속"]
[98,"경기북부","직할","양주S/S #5 Sh.R CB","24-25년 변전 직할 협력회사 총액공사","절연열화 측정 시행(와트값 기준치 초과)","2024-09-24 10:00","2024-09-24 17:00","2024-09-24 10:00","2024-09-24 17:00","연속"]
[99,"경기북부","직할","양주S/S #4 Sh.R CB","24-25년 변전 직할 협력회사 총액공사","GIS 하자점검","2024-09-25 10:00","2024-09-25 17:00","2024-09-25 10:00","2024-09-25 17:00","연속"]
[100,"경기북부","직할","신파주양주#1 T/L","고양전력 가공송전협력공사","추락방지장치(수평) 설치","2024-09-25 07:00","2024-09-27 18:00","2024-09-25 07:00","2024-09-27 18:00","연속"]
[101,"경기북부","직할","신파주양주#2 T/L","24-25년 직할 변전협력회사 총액공사","양주S/S GIS 개폐타임, 콘덴서 절연열화 측정(7471) CVT 교체","2024-09-23 10:00","2024-09-24 17:00","2024-09-23 10:00","2024-09-24 17:00","연속"]
[102,"경기북부","직할","양주S/S #6 Sh.R CB","24-25년 변전 직할 협력회사 총액공사","#5Sh.R(절연열화 측정) 인접설비 휴전 시행","2024-09-24 10:00","2024-09-24 17:00","2024-09-24 10:00","2024-09-24 17:00","연속"]
[103,"경기북부","직할","양주S/S #2 M.Tr","24-25년 양주TF 변전협력회사 총액공사","#2변압기 A상 2차 절연유 채유","2024-09-03 09:00","2024-09-04 18:00","2024-09-03 09:00","2024-09-04 18:00","연속"]
[104,"경기북부","직할","양주S/S CB 7672","24-25년 변전 직할 협력회사 총액공사","GIS 하자점검","2024-09-25 10:00","2024-09-25 17:00","2024-09-25 10:00","2024-09-25 17:00","연속"]
[105,"경기","성남","신성남S/S #1 M.Tr"," 신성남S/S 154kV #1,2,3,4Sh.R 설치사업","기초파쇄 시 설비진동(GIS)","2024-09-04 16:00","2024-10-15 16:00","2024-09-11 16:00","2024-10-22 16:00","연속"]
[106,"경기","평택","고덕S/S #2 C.Tr CB"," 24-25년 북당진-고덕 변환설비 위탁정비공사","24년도 연차점검 시행(#2Pole) - Valve, C.Tr, Filter, DC Hall 등 연차점검 시행","2024-09-02 09:00","2024-09-13 18:00","2024-09-02 09:00","2024-09-13 18:00","연속"]
[107,"경기","평택","북당진고덕HVDC #2 Pole CB"," 24-25년 북당진-고덕 변환설비 위탁정비공사","24년도 연차점검 시행(#2Pole) - Valve, C.Tr, Filter, DC Hall 등 연차점검 시행","2024-09-02 09:00","2024-09-13 18:00","2024-09-02 09:00","2024-09-13 18:00","연속"]
[108,"경기","직할","화성S/S CB 7371"," 2024-25년 경기본부 직할 변전협력회사 공사"," 화성: 아산-화성#1T/L GIS 초기점검(7371,7300) - GIS 콘덴서 절연열화측정","2024-09-05 09:00","2024-09-05 14:00","2024-09-05 09:00","2024-09-05 14:00","연속"]
[109,"경기","직할","화성S/S CB 7300"," 2024-25년 경기본부 직할 변전협력회사 공사","화성: 아산-화성#1T/L GIS 초기점검(7371,7300) - GIS 콘덴서 절연열화측정","2024-09-05 14:00","2024-09-05 18:00","2024-09-05 14:00","2024-09-05 18:00","연속"]
[110,"경기","직할","화성S/S #2 CLR CB"," 2024-25년 경기본부 직할 변전협력회사 공사","화성: 7577, 7677 GIS 보통점검 - GIS 콘덴서 절연열화측정","2024-09-06 09:00","2024-09-06 18:00","2024-09-06 09:00","2024-09-06 18:00","연속"]
[111,"경기","직할","화성S/S #4 M.Tr"," 화성S/S #4M.Tr 96TC 경보발생 관련 교체작업.","화성S/S #4M.Tr 96TC 교체","2024-09-06 09:00","2024-09-06 18:00","2024-09-06 09:00","2024-09-06 18:00","연속"]
[112,"경기","직할","화성S/S #2 CLR CB"," 2024-25년 경기본부 직할 변전협력회사 공사","화성: 7577, 7677 GIS 보통점검 - GIS 콘덴서 절연열화측정","2024-09-06 09:00","2024-09-06 18:00","2024-09-06 09:00","2024-09-06 18:00","연속"]
[113,"경기","평택","평택T/P CB 7271"," 평택T/P 345kV GIS 보통점검","평택T/P 345kV #4MAIN TR(#4T/P) 1차 GIS(7271) 보통점검","2024-09-10 09:00","2024-09-10 14:00","2024-09-10 09:00","2024-09-10 14:00","연속"]
[114,"경기","평택","평택T/P CB 7200"," 평택T/P 345kV GIS 보통점검","평택T/P 345kV #4MAIN TR 1차-#3,4ST.Tr GIS(7200) 보통점검","2024-09-10 14:00","2024-09-10 18:00","2024-09-10 14:00","2024-09-10 18:00","연속"]
[115,"경기","군포","신시흥신안산#1 T/L"," 24-25년 군포 가공송전협력회사 공사","345kV 신시흥신안산#1T/L 이도조정","2024-09-13 07:00","2024-09-14 18:00","2024-09-13 07:00","2024-09-14 18:00","연속"]
[116,"경기","성남","신안성신성남#1 T/L"," 345kV 신용인-동서울 No.7-1 항공도장작업(고객시행)","345kV 신용인-동서울 No.7-1 항공주간장애표지 탈색에 따른 재도장 - 이천오산고속도로 지장철탑이설공사시 시행한 항공도장 하자발생 보완 - 화성광주고속도로(주) 직접시행(요청자측 부담공사) - 4회선구간(신용인-동서울7-1호, 신성남-동서울 64-1호)","2024-09-19 07:00","2024-09-19 18:00","2024-09-19 07:00","2024-09-19 18:00","연속"]
[117,"경기","직할","화성신안산#1 T/L"," (군포)철탑추락방지장치(수평) 설치공사"," 철탑추락방지장치(수평) 설치 : 4회선 7기","2024-09-19 07:00","2024-09-19 18:00","2024-09-19 07:00","2024-09-19 18:00","연속"]
[118,"경기","성남","신안성신수원#1 T/L"," 2024년 성남전력 변전협력회사 총액공사","(신수원) LA 하자점검, 7271, 7200 GIS 절연열화 측정 (신안성) 7972 GIS 절연열화 측정","2024-09-19 09:00","2024-09-20 12:00","2024-09-19 09:00","2024-09-20 12:00","연속"]
[119,"경기","성남","신안성신성남#2 T/L"," 345kV 신용인-동서울 No.7-1 항공도장작업(고객시행)","345kV 신용인-동서울 No.7-1 항공주간장애표지 탈색에 따른 재도장 - 이천오산고속도로 지장철탑이설공사시 시행한 항공도장 하자발생 보완 - 화성광주고속도로(주) 직접시행(요청자측 부담공사) - 4회선구간(신용인-동서울7-1호, 신성남-동서울 64-1호)","2024-09-20 07:00","2024-09-20 18:00","2024-09-20 07:00","2024-09-20 18:00","연속"]
[120,"경기","성남","신용인동서울#2 T/L"," 345kV 신용인-동서울 No.7-1 항공도장작업(고객시행)","345kV 신용인-동서울 No.7-1 항공주간장애표지 탈색에 따른 재도장 - 이천오산고속도로 지장철탑이설공사시 시행한 항공도장 하자발생 보완 - 화성광주고속도로(주) 직접시행(요청자측 부담공사) - 4회선구간(신용인-동서울7-1호, 신성남-동서울 64-1호)","2024-09-20 07:00","2024-09-20 18:00","취소","취소","연속"]
[121,"경기","직할","화성신안산#2 T/L"," (군포)철탑추락방지장치(수평) 설치공사"," 철탑추락방지장치(수평) 설치 : 4회선 7기","2024-09-20 07:00","2024-09-20 18:00","2024-09-20 07:00","2024-09-20 18:00","연속"]
[122,"경기","성남","신용인삼성 T/L"," 24-25년 경기직할 가공송전 협력회사 총액공사","피뢰기 설치공사[4회선 병가/안전거리휴전]","2024-09-23 07:00","2024-09-23 18:00","2024-09-23 07:00","2024-09-23 18:00","연속"]
[123,"경기","동부","곤지암S/S CB 7571"," 24-25년 동부 변전협력총액공사","곤지암:7571 GIS 유압펌프 볼트조임","2024-09-23 09:00","2024-09-25 18:00","2024-09-23 09:00","2024-09-25 18:00","연속"]
[124,"경기","직할","화성S/S #2 M.Tr"," 2024-25년 경기본부 직할 변전협력회사 공사","화성: #2M.Tr 보호반 대체(~13) - 3차 LA A,B,C 하자","2024-09-23 09:00","2024-09-27 18:00","2024-09-23 09:00","2024-09-27 18:00","연속"]
[125,"경기","평택","고덕S/S #2 C.Tr CB"," 24-25년 북당진-고덕 변환설비 위탁정비공사","24년도 연차점검 시행(Bi-Pole) - Valve, C.Tr, Filter, DC Hall 등 연차점검 시행","2024-09-23 09:00","2024-10-18 18:00","취소","취소","연속"]
[126,"경기","평택","북당진고덕HVDC #1 Pole CB"," 24-25년 북당진-고덕 변환설비 위탁정비공사","24년도 연차점검 시행(Bi-Pole) - Valve, C.Tr, Filter, DC Hall 등 연차점검 시행","2024-09-23 09:00","2024-10-18 18:00","취소","취소","연속"]
[127,"경기","평택","고덕S/S #1 C.Tr CB"," 24-25년 북당진-고덕 변환설비 위탁정비공사","24년도 연차점검 시행(Bi-Pole) - Valve, C.Tr, Filter, DC Hall 등 연차점검 시행","2024-09-23 09:00","2024-10-18 18:00","취소","취소","연속"]
[128,"경기","평택","북당진고덕HVDC #2 Pole CB"," 24-25년 북당진-고덕 변환설비 위탁정비공사","24년도 연차점검 시행(Bi-Pole) - Valve, C.Tr, Filter, DC Hall 등 연차점검 시행","2024-09-23 09:00","2024-10-18 18:00","취소","취소","연속"]
[129,"경기","평택","평택T/P #1 TIE Tr"," 평택T/P 345kV TIE.Tr 및 1차, TIE GIS 보통점검"," 평택T/P 345kV #1TIE.Tr 및 1차(7171), 2,3차 GIS 보통점검 및 3차 GIS 보호계전기 교체, #1S.Tr 대체","2024-09-23 09:00","2024-09-25 18:00","2024-09-23 09:00","2024-09-25 18:00","연속"]
[130,"경기","평택","평택T/P CB 7600"," 24년 평택전력 345kV GIS 보통점검","평택T/P 345kV 평택화성#1-#2T/P1차 GIS(7600) 보통점검","2024-09-24 09:00","2024-09-24 18:00","2024-09-24 09:00","2024-09-24 18:00","연속"]
[131,"경기","평택","평택T/P CB 7200"," 평택T/P 345kV GIS 보통점검","평택T/P 345kV #4MAIN TR 1차-#3,4ST.Tr GIS(7200) 보통점검","2024-09-25 09:00","2024-09-25 18:00","2024-09-25 09:00","2024-09-25 18:00","연속"]
[132,"경기","동부","곤지암S/S CB 7671"," 24-25년 동부 변전협력총액공사","곤지암:7671 GIS 유압펌프 볼트조임","2024-09-26 09:00","2024-09-28 18:00","2024-09-26 09:00","2024-09-28 18:00","연속"]
[133,"경기","평택","고덕2#S/S CB 7571","24년도 평택전력 345&154kV GIS 보통점검","고덕#2S/S 154kV GIS (7571) 하자점검","2024-09-26 09:00","2024-09-26 14:00","2024-09-26 09:00","2024-09-26 14:00","연속"]
[134,"경기","평택","고덕2#S/S CB 7500","24년도 평택전력 345&154kV GIS 보통점검","고덕#2S/S 154kV GIS (7500) 하자점검","2024-09-26 14:00","2024-09-26 18:00","2024-09-26 14:00","2024-09-26 18:00","연속"]
[135,"경기","군포","신안산S/S #4 M.Tr"," 신안산S/S #4M.Tr 보통점검","신안산S/S #4M.Tr 보통점검","2024-09-30 09:00","2024-09-30 18:00","2024-09-30 09:00","2024-09-30 18:00","연속"]
[136,"경기","직할","화성S/S SEC CB 70710"," 2024-25년 경기본부 직할 변전협력회사 공사","화성: 70-71SEC GIS 보통점검 - GIS 콘덴서 절연열화측정 #3M.Tr 1차 7672 CB - GIS 콘덴서 절연열화측정 - 가스경보 수정, 가스측정","2024-09-30 09:00","2024-09-30 18:00","2024-09-30 09:00","2024-09-30 18:00","연속"]
[137,"경기","직할","화성S/S CB 7672"," 2024-25년 경기본부 직할 변전협력회사 공사","화성: 70-71SEC GIS 보통점검 - GIS 콘덴서 절연열화측정 #3M.Tr 1차 7672 CB - GIS 콘덴서 절연열화측정 - 가스경보 수정, 가스측정","2024-09-30 09:00","2024-09-30 11:00","2024-09-30 09:00","2024-09-30 11:00","연속"]
[138,"강원","강릉","신양양S/S CB 7171","2024년 강릉전력지사 변전협력회사 공사","균압콘덴서 점검","2024-09-09 14:00","2024-09-09 18:00","2024-09-09 14:00","2024-09-09 18:00","연속"]
[139,"강원","강릉","양양P/P #2 BUS","2024년 강릉전력지사 변전협력회사 공사","모선보호반 대체","2024-09-30 09:00","2024-10-04 18:00","2024-09-30 09:00","2024-10-04 18:00","연속"]
[140,"강원","강릉","안인개폐소양양PP T/L","2024년 강릉전력지사 변전협력회사 공사","모선보호반 대체","2024-09-23 09:00","2024-09-27 18:00","2024-09-23 09:00","2024-09-27 18:00","연속"]
[141,"강원","강릉","양양P/P CB 7271","2024년 강릉전력지사 변전협력회사 공사","균압콘덴서 점검","2024-09-09 10:00","2024-09-09 14:00","2024-09-09 10:00","2024-09-09 14:00","연속"]
[142,"강원","강릉","양양P/P #1 BUS","2024년 강릉전력지사 변전협력회사 공사","모선보호반 대체","2024-09-23 09:00","2024-09-27 18:00","2024-09-23 09:00","2024-09-27 18:00","연속"]
[143,"강원","동해","동해S/S CB 7271","2024~2025년 동해전력지사 변전협력회사 공사","균압콘덴서측정, CB조작시험","2024-09-03 13:00","2024-09-03 15:00","2024-09-03 13:00","2024-09-03 15:00","연속"]
[144,"강원","동해","동해S/S CB 7100","2024~2025년 동해전력지사 변전협력회사 공사","균압콘덴서측정, CB조작시험","2024-09-03 09:00","2024-09-03 12:00","2024-09-03 09:00","2024-09-03 12:00","연속"]
[145,"강원","동해","동해S/S CB 7300","2024~2025년 동해전력지사 변전협력회사 공사","균압콘덴서측정, CB조작시험","2024-09-03 15:00","2024-09-03 18:00","2024-09-03 15:00","2024-09-03 18:00","연속"]
[146,"강원","동해","동해S/S CB 7772","동해S/S 362kV GIS 정밀점검","345kV GIS 정밀점검","2024-09-30 09:00","2024-10-04 18:00","2024-09-30 09:00","2024-10-04 18:00","연속"]
[147,"강원","동해","동해안인개폐소#1 T/L","345kV 동해-안인개폐소T/L 국산 불량애자교체공사","불량애자교체","2024-09-30 07:00","2024-10-04 18:00","2024-09-30 07:00","2024-10-04 18:00","연속"]
[148,"강원","동해","동해S/S CB 7700","동해S/S 362kV GIS 정밀점검","345kV GIS 정밀점검","2024-09-23 09:00","2024-09-27 18:00","2024-09-23 09:00","2024-09-27 18:00","연속"]
[149,"강원","동해","동해S/S STATCOM CB","2024~2025년 동해전력지사 변전협력회사 공사","2024년 정기검사","2024-09-23 09:00","2024-09-24 18:00","2024-09-23 09:00","2024-09-24 18:00","연속"]
[150,"강원","태백","신태백S/S CB 7471","2024-2025년 태백전력지사 변전협력회사 공사","신태백S/S 345kV 7471CB 보통점검","2024-09-24 09:00","2024-09-24 18:00","2024-09-24 09:00","2024-09-24 18:00","연속"]
[151,"강원","태백","신태백S/S CB 7671","2024-2025년 태백전력지사 변전협력회사 공사","신태백S/S 345kV 7671CB 보통점검","2024-09-25 09:00","2024-09-25 18:00","2024-09-25 09:00","2024-09-25 18:00","연속"]
[152,"강원","태백","신태백한울NP#1 T/L","2024-2025년 태백전력지사 변전협력회사 공사","신태백S/S 345kV 75BAY B/F 보호반 교체","2024-09-23 09:00","2024-09-27 18:00","취소","취소","연속"]
[153,"강원","태백","신태백S/S CB 7600","2024-2025년 태백전력지사 변전협력회사 공사","신태백S/S 345kV 7600CB 보통점검","2024-09-26 09:00","2024-09-26 18:00","2024-09-26 09:00","2024-09-26 18:00","연속"]
[154,"충북","직할","신중부남청주#2 T/L","345kV 신중부-신청주T/L 용량증대 전선교체공사","○ 시공내용 : 전력선 교체(용량증대 전선용 금구류 교체 포함) 27경간, 10km","2024-09-30 07:00","2024-10-04 18:00","2024-09-30 07:00","2024-10-04 18:00","연속"]
[155,"충북","직할","서안성신진천#1 T/L","2024년 가공송전선로 순시점검 위탁공사","345kV 서안성-신진천T/L 초기점검","2024-09-19 09:00","2024-09-19 18:00","2024-09-19 09:00","2024-09-19 18:00","연속"]
[156,"충북","직할","서안성신진천#2 T/L","2024년 가공송전선로 순시점검 위탁공사","345kV 서안성-신진천T/L 초기점검","2024-09-20 09:00","2024-09-20 18:00","2024-09-20 09:00","2024-09-20 18:00","연속"]
[157,"충북","직할","신진천S/S #5 M.Tr","신진천S/S 345kV GIS 콘덴서 절연열화 진단","송운(변전)-1076(’23. 9.25)「345kV GIS(콘덴서) 고장예방 및 최적화 운전방안 알림」관련 신진천S/S 345kV GIS 콘덴서 절연열화 진단","2024-09-02 15:00","2024-09-02 17:00","2024-09-02 15:00","2024-09-02 17:00","연속"]
[158,"충북","직할","신진천S/S #1 M.Tr","24-25년 충북본부 직할 변전협력회사 공사","345kV #1M.Tr 보통점검","2024-09-23 09:00","2024-09-26 18:00","2024-09-23 09:00","2024-09-26 18:00","연속"]
[159,"충북","직할","신중부신진천#1 T/L","신진천S/S 345kV GIS 콘덴서 절연열화 진단","송운(변전)-1076(’23. 9.25)「345kV GIS(콘덴서) 고장예방 및 최적화 운전방안 알림」관련 신진천S/S 345kV GIS 콘덴서 절연열화 진단","2024-09-02 10:00","2024-09-02 12:00","2024-09-02 10:00","2024-09-02 12:00","연속"]
[160,"충북","직할","신진천S/S #2 M.Tr","24-25년 충북본부 직할 변전협력회사 공사","345kV #2M.Tr 1차 7472CB 보통점검, 부싱 절연유 채유","2024-09-09 10:00","2024-09-09 16:00","2024-09-09 10:00","2024-09-09 16:00","연속"]
[161,"충북","직할","신중부신진천#2 T/L","신진천S/S 345kV GIS 콘덴서 절연열화 진단","송운(변전)-1076(’23. 9.25)「345kV GIS(콘덴서) 고장예방 및 최적화 운전방안 알림」관련 신진천S/S 345kV GIS 콘덴서 절연열화 진단","2024-09-02 13:00","2024-09-02 15:00","2024-09-02 13:00","2024-09-02 15:00","연속"]
[162,"충북","직할","신진천S/S #3 M.Tr","24-25년 충북본부 직할 변전협력회사 공사","345kV GIS DS(7602) 모터 교체","2024-09-10 09:00","2024-09-10 18:00","2024-09-10 09:00","2024-09-10 18:00","연속"]
[163,"충북","청주","남청주S/S #2 M.Tr","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-09-02 08:00","2024-09-27 18:00","2024-09-02 08:00","2024-09-27 18:00","연속"]
[164,"충북","청주","남청주S/S #5 M.Tr","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 보통점검(#5M.Tr 2차측)","2024-09-28 09:00","2024-09-28 18:00","2024-09-28 09:00","2024-09-28 18:00","연속"]
[165,"충북","청주","남청주S/S #4 M.Tr","24년 청주전력지사 345kV 주변압기/OLTC 정밀점검","#4M.Tr 주변압기, OLTC 정밀점검","2024-09-30 09:00","2024-10-11 18:00","2024-09-30 09:00","2024-10-11 18:00","연속"]
[166,"충북","청주","남청주S/S #1 M.Tr","24년 청주전력지사 345kV 주변압기/OLTC 정밀점검","#1M.Tr 주변압기, OLTC 정밀점검","2024-09-02 09:00","2024-09-14 18:00","2024-09-02 09:00","2024-09-14 18:00","연속"]
[167,"충북","청주","신옥천세종#1 T/L","345kV 신옥천북경남 등 8개T/L 추락방지장치 설치공사","공사개요 : 신옥천세종#1T/L 추락방지장치 수평설치 공사장소 : 신옥천세종#1T/L No.1~48(55기)","2024-09-20 07:00","2024-09-27 18:00","2024-09-20 07:00","2024-09-27 18:00","매일"]
[168,"충북","청주","신옥천S/S #2 M.Tr","2024~2025년 청주전력지사 변전협력회사 공사","M.Tr 누유보수 및 3차측 PT 점검","2024-09-04 08:00","2024-09-04 18:00","2024-09-04 08:00","2024-09-04 18:00","연속"]
[169,"충북","청주","신옥천세종#2 T/L","345kV 신옥천북경남 등 8개T/L 추락방지장치 설치공사","공사개요 : 신옥천세종#2T/L 추락방지장치 수평설치 공사장소 : 신옥천세종#2T/L No.1~48(55기)","2024-09-28 07:00","2024-10-02 18:00","2024-09-28 07:00","2024-10-02 18:00","매일"]
[170,"충북","충주","신제천S/S CB 7600","'24-25년 충주전력지사 변전정비 총액공사","신제천S/S 345kV 신제천-신영주#1T/L-TIE(7600) GISi 보통점검 및 콘덴서 절연열화 측정","2024-09-27 09:00","2024-09-27 18:00","2024-09-27 09:00","2024-09-27 18:00","연속"]
[171,"충북","충주","신제천S/S #2 M.Tr","신제천S/S 362KV GIS PD관련 제작사 하자보수","#2M.Tr 1차 DS(7302,7362) 부품교체","2024-09-25 09:00","2024-09-27 18:00","2024-09-25 09:00","2024-09-27 18:00","연속"]
[172,"충북","충주","신충주T여주복합#1 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.140-160호)","2024-09-23 07:00","2024-09-25 16:00","2024-09-23 07:00","2024-09-25 16:00","매일"]
[173,"충북","충주","신제천신영주#2 T/L","345kV 신제천-신영주T/L OPGW 낙뢰소손 교체공사","#2T/L No.5~12호 3.057km 교체 및 항공구 31개 설치","2024-09-12 07:00","2024-09-15 18:00","2024-09-12 07:00","2024-09-15 18:00","연속"]
[174,"충북","충주","신충주여주복합#2 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.140-160)","2024-09-26 07:00","2024-09-28 16:00","2024-09-26 07:00","2024-09-28 16:00","연속"]
[175,"충북","충주","신충주T여주복합#1 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.140-160호)","2024-09-23 07:00","2024-09-25 16:00","취소","취소","매일"]
[176,"대전세종충남","대전","신계룡S/S #1 BUS","신계룡S/S 345kV #2M.Tr 1차 TIE 균압콘덴서 절연열화 측정","신계룡S/S 345kV #2M.Tr 1차 TIE 균압콘덴서 절연열화 측정","2024-09-10 09:00","2024-09-10 13:00","2024-09-10 09:00","2024-09-10 13:00","연속"]
[177,"대전세종충남","대전","신계룡S/S CB 7400","신계룡S/S 345kV #2 M.Tr 1차 TIE 차단기 개폐타임 측정","신계룡S/S 345kV #2 M.Tr 1차 TIE 차단기 개폐타임 측정","2024-09-10 09:00","2024-09-10 13:00","취소","취소","연속"]
[178,"대전세종충남","대전","신계룡S/S #2 BUS","신계룡S/S 345kV #2M.Tr 1차 균압콘덴서 절연열화 측정","신계룡S/S 345kV #2M.Tr 1차 균압콘덴서 절연열화 측정","2024-09-10 13:00","2024-09-10 18:00","2024-09-10 13:00","2024-09-10 18:00","연속"]
[179,"대전세종충남","대전","신계룡S/S #1 BUS","신계룡S/S 345kV 신계룡-신옥천T/L 균압콘덴서 절연열화 측정","신계룡S/S 345kV 신계룡-신옥천T/L 균압콘덴서 절연열화 측정","2024-09-11 09:00","2024-09-11 13:00","2024-09-11 09:00","2024-09-11 13:00","연속"]
[180,"대전세종충남","대전","신계룡S/S CB 7271","신계룡S/S 345kV 신옥천-신계룡T/L GIS 차단기 개폐타임 측정","신계룡S/S 345kV 신옥천-신계룡T/L GIS 차단기 개폐타임 측정","2024-09-11 09:00","2024-09-11 18:00","2024-09-11 09:00","2024-09-11 18:00","연속"]
[181,"대전세종충남","대전","신계룡S/S CB 7472","신계룡S/S 345kV #2 M.Tr 1차 GIS 차단기 개폐타임 측정","신계룡S/S 345kV #2 M.Tr 1차 GIS 차단기 개폐타임 측정","2024-09-10 13:00","2024-09-10 18:00","취소","취소","연속"]
[182,"대전세종충남","서산","당진T/P CB 7172","당진T/P 345kV 차단기 조작시험","당진T/P 345kV 1호기 1차 7172 CB 조작시험","2024-09-25 10:00","2024-09-25 14:00","2024-09-25 10:00","2024-09-25 14:00","연속"]
[183,"대전세종충남","서산","당진T/P #71 Tie-Tr","'24년 서산P/O 변전협력회사 총액공사","(즉시가압 불가) 당진화력S/S 345kV #71 TIE-Tr 부싱절연유 채유, 부싱 절연열화진단","2024-09-27 09:00","2024-09-27 18:00","2024-09-27 09:00","2024-09-27 18:00","연속"]
[184,"대전세종충남","서산","당진T/P CB 7171","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 345kV 7171 GIS 보통점검","2024-09-26 09:30","2024-09-27 18:00","2024-09-26 09:30","2024-09-27 18:00","연속"]
[185,"대전세종충남","서산","북당진S/S CB 7172","24년 서산P/O 변전협력회사 총액공사","(즉시가압 가능) 북당진S/S 345kV 7172CB 균압콘덴서 절연열화 진단","2024-09-06 13:00","2024-09-06 15:30","취소","취소","연속"]
[186,"대전세종충남","서산","북당진S/S CB 7171","24년 서산P/O 변전협력회사 총액공사","(즉시가압 가능) 북당진S/S 345kV 7171CB 균압콘덴서 절연열화 진단","2024-09-06 09:30","2024-09-06 12:00","취소","취소","연속"]
[187,"대전세종충남","서산","북당진S/S #1 BUS","북당진S/S 345kV 북당진-신탕정T/L GIS 설치공사","72BAY 1CB(7271) 설치 73BAY 2CB(7371,7300) 설치","2024-09-02 09:00","2024-09-06 18:00","2024-09-02 09:00","2024-09-06 18:00","연속"]
[188,"대전세종충남","서산","북당진S/S CB 7200","북당진S/S 345kV 북당진-신탕정T/L GIS 설치공사","72BAY 1CB(7271) 설치 73BAY 2CB(7371,7300) 설치","2024-09-02 09:00","2024-10-25 18:00","2024-09-02 09:00","2024-10-25 18:00","연속"]
[189,"대전세종충남","서산","신당진개폐소 SEC CB 7C7D0","24년 서산P/O 변전협력회사 총액공사","(즉시가압 가능) 신당진개폐소 345kV 7C-7D-0CB 균압콘덴서 절연열화 진단","2024-09-04 12:30","2024-09-04 14:30","2024-09-04 12:30","2024-09-04 14:30","연속"]
[190,"대전세종충남","서산","신당진개폐소 SEC CB 7A7B0","24년 서산P/O 변전협력회사 총액공사","(즉시가압 가능) 신당진개폐소 345kV 7A-7B-0CB 균압콘덴서 절연열화 진단","2024-09-04 09:30","2024-09-04 11:30","2024-09-04 09:30","2024-09-04 11:30","연속"]
[191,"대전세종충남","서산","신당진개폐소 CB 7C72","24년 서산P/O 변전협력회사 총액공사","(즉시가압 가능) 신당진개폐소 345kV 7C72CB 균압콘덴서 절연열화 진단","2024-09-13 09:30","2024-09-13 12:00","2024-09-13 09:30","2024-09-13 12:00","연속"]
[192,"대전세종충남","서산","신당진개폐소 CB 7D71","24년 서산P/O 변전협력회사 총액공사","(즉시가압 가능) 신당진개폐소 345kV 7D71CB 균압콘덴서 절연열화 진단","2024-09-13 13:00","2024-09-13 15:30","2024-09-13 13:00","2024-09-13 15:30","연속"]
[193,"대전세종충남","서산","신당진개폐소태안TP#2 T/L","'23년 서산P/O 장기사용 배전반 교체공사","(즉시가압 불가)신당진개폐소, 태안화력S/Y 345kV 신당진개폐소-태안화력#2T/L 보호반 대체공사","2024-09-23 09:00","2024-09-27 18:00","2024-09-23 09:00","2024-09-27 18:00","연속"]
[194,"대전세종충남","서산","신서산신당진#1 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.1~6,33~42) , 즉시가압(20분 이내) 가능","2024-09-09 08:00","2024-09-10 18:00","2024-09-09 08:00","2024-09-10 18:00","매일"]
[195,"대전세종충남","서산","신서산신당진#2 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.1~6,33~42) , 즉시가압(20분 이내) 가능","2024-09-11 08:00","2024-09-12 18:00","2024-09-11 08:00","2024-09-12 18:00","매일"]
[196,"대전세종충남","서산","신당진S/S CB 7472","24년 서산P/O 변전협력회사 총액공사","(즉시가압 가능) 신당진S/S 345kV 7472CB 균압콘덴서 절연열화 진단","2024-09-04 16:30","2024-09-04 18:30","2024-09-04 16:30","2024-09-04 18:30","연속"]
[197,"대전세종충남","서산","신당진S/S CB 7471","24년 서산P/O 변전협력회사 총액공사","(즉시가압 가능) 신당진S/S 345kV 7471CB 균압콘덴서 절연열화 진단","2024-09-04 14:30","2024-09-04 16:30","2024-09-04 14:30","2024-09-04 16:30","연속"]
[198,"대전세종충남","서산","신서산S/S CB 7900","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 345kV 7900 GIS 보통점검","2024-09-03 09:30","2024-09-04 18:00","2024-09-03 09:30","2024-09-04 18:00","연속"]
[199,"대전세종충남","서산","신서산S/S CB 7971","24년 서산P/O 345kV GIS 정밀점검공사","(즉시가압 불가) 신서산S/S 345kV 7971 CB 정밀점검","2024-09-09 09:30","2024-09-13 18:00","2024-09-09 09:30","2024-09-13 18:00","연속"]
[200,"대전세종충남","서산","신서산S/S CB 7A72","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 345kV 7A72 GIS 보통점검","2024-09-05 09:30","2024-09-06 18:00","2024-09-05 09:30","2024-09-06 18:00","연속"]
[201,"대전세종충남","서산","신서산S/S CB 7572","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 345kV 7572 GIS 보통점검","2024-09-23 09:30","2024-09-24 18:00","2024-09-23 09:30","2024-09-24 18:00","연속"]
[202,"대전세종충남","서산","신서산S/S #3 Sh.R CB","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 345kV 7579 GIS 보통점검","2024-09-09 09:30","2024-09-10 18:00","2024-09-09 09:30","2024-09-10 18:00","매일"]
[203,"대전세종충남","서산","신서산S/S CB 7972","24년 서산P/O 345kV GIS 정밀점검공사","(즉시가압 불가) 신서산S/S 345kV 7972 CB 정밀점검","2024-09-23 09:30","2024-09-27 18:00","2024-09-23 09:30","2024-09-27 18:00","연속"]
[204,"대전세종충남","서산","신서산태안TP#1 T/L","24년 서산P/O 변전협력회사 총액공사","(8월 휴전 취소시)(T/L 즉시가압 가능) 태안화력S/S 345kV 신서산-태안화력#1T/L 1차 7671CB A상 대체 - 7600 Tie CB 휴전필요 : GIS 대체관련 안전이격확보","2024-09-02 09:30","2024-09-04 18:00","2024-09-02 09:30","2024-09-04 18:00","매일"]
[205,"대전세종충남","서산","태안T/P CB 7871","태안T/P 345kV 차단기 조작시험","태안T/P 345kV #1M.Tr 2차 6144 CB 조작시험","2024-09-12 10:00","2024-09-12 14:00","2024-09-12 10:00","2024-09-12 14:00","연속"]
[206,"대전세종충남","천안","신온양서서울#2 T/L","신온양S/S 345kV 77Bay B/F 보호반 대체","(즉시가압불가)신온양S/S 345kV 77Bay B/F 보호반 대체","2024-09-02 09:00","2024-09-05 18:00","취소","취소","연속"]
[207,"대전세종충남","천안","신온양서서울#1 T/L","신온양S/S 345kV 78Bay B/F 보호반 대체","(즉시가압불가)신온양S/S 345kV 78Bay B/F 보호반 대체","2024-09-23 09:00","2024-09-27 18:00","취소","취소","연속"]
[208,"대전세종충남","천안","신온양신탕정#2 T/L","신온양S/S 345kV 78Bay B/F 보호반 대체","(즉시가압불가)신온양S/S 345kV 78Bay B/F 보호반 대체","2024-09-23 09:00","2024-09-27 18:00","취소","취소","연속"]
[209,"대전세종충남","천안","신온양S/S #4 M.Tr","신온양S/S 345kV #4M.Tr 부싱절연유 채유","(즉시가압가능)(B/F반 대체 휴전취소시)신온양S/S 345kV #4M.Tr 부싱절연유 채유","2024-09-19 09:00","2024-09-19 18:00","2024-09-19 09:00","2024-09-19 18:00","연속"]
[210,"대전세종충남","천안","신온양S/S #4 M.Tr","신온양S/S 345kV 77Bay B/F 보호반 대체","(즉시가압불가)신온양S/S 345kV 77Bay B/F 보호반 대체","2024-09-02 09:00","2024-09-05 18:00","취소","취소","연속"]
[211,"대전세종충남","천안","청양신탕정#2 T/L","[8월취소시]345kV 신온양-신탕정T/L 추락방지장치 설치공사","[즉시가압가능]345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치 345kV 청양-신탕정#2T/L No.14 애자련교체(애자섬락) [병가철탑] 신온양신탕정#2(상단), 청양신탕정#2(하단) [병행작업] 조류착지방지장치 설치","2024-09-23 07:00","2024-09-27 18:00","취소","취소","매일"]
[212,"대전세종충남","천안","신온양신탕정#1 T/L","[8월취소시]345kV 신온양-신탕정T/L 추락방지장치 설치공사","[즉시가압가능]345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치 [병가철탑] 신온양신탕정#1(상단), 청양신탕정#1(하단) [병행작업] 조류착지방지장치 설치","2024-09-16 07:00","2024-09-20 18:00","2024-09-16 07:00","2024-09-20 18:00","매일"]
[213,"대전세종충남","천안","청양신탕정#1 T/L","[8월취소시]345kV 신온양-신탕정T/L 추락방지장치 설치공사","[즉시가압가능]345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치 345kV 청양-신탕정#1T/L No. 82 애자련교체(애자섬락) [병가철탑] 신온양신탕정#1(상단), 청양신탕정#1(하단) [병행작업] 조류착지방지장치 설치","2024-09-16 07:00","2024-09-20 18:00","취소","취소","매일"]
[214,"대전세종충남","천안","신탕정S/S #2 M.Tr","신탕정S/S 345kV #2M.Tr 노후 보호반 대체","(즉시가압불가)신탕정S/S 345kV #2M.Tr 노후 보호반 대체","2024-09-23 09:00","2024-09-27 18:00","2024-09-23 09:00","2024-09-27 18:00","연속"]
[215,"대전세종충남","천안","신온양신탕정#2 T/L","[8월취소시]345kV 신온양-신탕정T/L 추락방지장치 설치공사","[즉시가압가능]345kV 신온양-신탕정T/L No. 1 ~ 25 추락방지장치 설치 [병가철탑] 신온양신탕정#2(상단), 청양신탕정#2(하단) [병행작업] 조류착지방지장치 설치","2024-09-23 07:00","2024-09-27 18:00","취소","취소","매일"]
[216,"대전세종충남","천안","신탕정S/S #1 M.Tr","신탕정S/S 345kV #1M.Tr 노후 보호반 대체","(즉시가압불가)신탕정S/S 345kV #1M.Tr 노후 보호반 대체","2024-09-10 09:00","2024-09-13 18:00","2024-09-10 09:00","2024-09-13 18:00","연속"]
[217,"대전세종충남","천안","아산S/S CB 7372","아산S/S 345kV 7372 CB 개폐타임측정 및 콘덴서 절연열화진단","(즉시가압가능)(아산S/S 345kV #1M.Tr 휴전 취소시)아산S/S 345kV 7372 CB 개폐타임측정 및 콘덴서 절연열화진단","2024-09-06 09:00","2024-09-06 18:00","취소","취소","연속"]
[218,"대전세종충남","천안","아산S/S #1 M.Tr","아산S/S 345kV #1M.Tr 부싱절연유 채유","(즉시가압가능)아산S/S 345kV #1M.Tr 부싱절연유 채유","2024-09-06 09:00","2024-09-06 18:00","2024-09-06 09:00","2024-09-06 18:00","연속"]
[219,"대전세종충남","천안","신서산아산#1 T/L","345kV 신서산-아산T/L 추락방지장치 설치공사","[즉시가압가능]345kV 신서산-아산T/L No. 74 ~ 123 추락방지장치 설치 [병가철탑](상단)신서산-아산#1No.74~113,(하단)아산-합덕#1No.13~52 [병행작업] 조류착지방지장치 설치","2024-09-25 07:00","2024-10-02 18:00","취소","취소","매일"]
[220,"대전세종충남","천안","아산S/S CB 7271","아산S/S 345kV 7271 CB 개폐타임측정 및 콘덴서 절연열화진단","(즉시가압가능)아산S/S 345kV 7271 CB 개폐타임측정 및 콘덴서 절연열화진단","2024-09-27 09:00","2024-09-27 18:00","2024-09-27 09:00","2024-09-27 18:00","연속"]
[221,"대전세종충남","천안","아산S/S CB 7500","아산S/S 345kV 7500, 7572 개폐타임측정 및 콘덴서 절연열화","(즉시가압가능)(아산S/S 345kV #2M.Tr 휴전 취소시)아산S/S 345kV 7500, 7572 CB 개폐타임측정 및 콘덴서 절연열화 진단","2024-09-11 09:00","2024-09-11 14:00","취소","취소","연속"]
[222,"대전세종충남","천안","아산S/S #2 M.Tr","아산S/S 345kV #2M.Tr 부싱절연유 채유","(즉시가압가능)아산S/S 345kV #2M.Tr 부싱절연유 채유","2024-09-11 09:00","2024-09-11 18:00","2024-09-11 09:00","2024-09-11 18:00","연속"]
[223,"대전세종충남","천안","아산S/S CB 7572","아산S/S 345kV 7500, 7572 개폐타임측정 및 콘덴서 절연열화","(즉시가압가능)(아산S/S 345kV #2M.Tr 휴전 취소시)아산S/S 345kV 7500, 7572 CB 개폐타임측정 및 콘덴서 절연열화 진단","2024-09-11 14:00","2024-09-11 18:00","취소","취소","연속"]
[224,"대전세종충남","천안","아산S/S #4 M.Tr","아산S/S 345kV #4M.Tr 부싱절연유 채유","(즉시가압가능)아산S/S 345kV #4M.Tr 부싱절연유 채유","2024-09-12 09:00","2024-09-12 18:00","2024-09-12 09:00","2024-09-12 18:00","연속"]
[225,"대전세종충남","천안","아산S/S CB 7800","아산S/S 345kV 7800 CB 개폐타임측정 및 콘덴서 절연열화","(즉시가압가능)(아산S/S 345kV #4M.Tr 휴전 취소시)아산S/S 345kV 7800 CB 개폐타임측정 및 콘덴서 절연열화진단","2024-09-12 09:00","2024-09-12 18:00","취소","취소","연속"]
[226,"대전세종충남","청양","보령C/C SEC CB 70710","청양P/O 변전전문 발주공사(복합 7071 보통)","청양P/O 변전전문 발주공사 - 보령복합 70-71-0 보통점검 (즉시가압 가능)","2024-09-23 09:00","2024-09-23 14:00","2024-09-23 09:00","2024-09-23 14:00","연속"]
[227,"대전세종충남","청양","보령C/C CB 7372","청양P/O 변전협력 총액공사(복합 7372 조작)","청양P/O 변전협력 총액공사 - 보령복합 7372 조작시험 (즉시가압 가능)","2024-09-12 14:00","2024-09-12 18:00","2024-09-12 14:00","2024-09-12 18:00","연속"]
[228,"대전세종충남","청양","보령C/C CB 7300","청양P/O 변전협력 총액공사(복합 7300 조작)","청양P/O 변전협력 총액공사 - 보령복합 7300 조작시험 (즉시가압 가능)","2024-09-12 09:00","2024-09-12 14:00","2024-09-12 09:00","2024-09-12 14:00","연속"]
[229,"대전세종충남","청양","보령C/C CB 7272","청양P/O 변전협력 총액공사(복합 7272 조작)","청양P/O 변전협력 총액공사 - 보령복합 7272 조작시험 (즉시가압 가능)","2024-09-11 14:00","2024-09-11 18:00","2024-09-11 14:00","2024-09-11 18:00","연속"]
[230,"대전세종충남","청양","보령C/C CB 7200","청양P/O 변전협력 총액공사(복합 7200 조작)","청양P/O 변전협력 총액공사 - 보령복합 7200 조작시험 (즉시가압 가능)","2024-09-11 09:00","2024-09-11 14:00","2024-09-11 09:00","2024-09-11 14:00","연속"]
[231,"대전세종충남","청양","보령C/C CB 7172","청양P/O 변전협력 총액공사(복합 7172 조작)","청양P/O 변전협력 총액공사 - 보령복합 7172 조작시험 (즉시가압 가능)","2024-09-10 14:00","2024-09-10 18:00","2024-09-10 14:00","2024-09-10 18:00","연속"]
[232,"대전세종충남","청양","보령C/C SEC CB 75760","청양P/O 변전전문 발주공사(복합 7576 보통)","청양P/O 변전전문 발주공사 - 보령복합 75-76-0 보통점검 (즉시가압 가능)","2024-09-23 14:00","2024-09-23 18:00","2024-09-23 14:00","2024-09-23 18:00","연속"]
[233,"대전세종충남","청양","보령C/C CB 7271","청양P/O 변전전문 발주공사(복합 7271 보통)","청양P/O 변전전문 발주공사 - 보령복합 7271 보통점검 (즉시가압 가능)","2024-09-24 09:00","2024-09-24 15:00","2024-09-24 09:00","2024-09-24 15:00","연속"]
[234,"대전세종충남","청양","보령C/C CB 7372","청양P/O 변전전문 발주공사(복합 7372 보통)","청양P/O 변전전문 발주공사 - 보령복합 7372 보통점검 (즉시가압 가능)","2024-09-25 09:00","2024-09-25 15:00","2024-09-25 09:00","2024-09-25 15:00","연속"]
[235,"대전세종충남","청양","보령C/C CB 7171","청양P/O 변전전문 발주공사(복합 7171 보통)","청양P/O 변전전문 발주공사 - 보령복합 7171 보통점검 (즉시가압 가능)","2024-09-26 09:00","2024-09-26 15:00","2024-09-26 09:00","2024-09-26 15:00","연속"]
[236,"대전세종충남","청양","보령C/C CB 7100","청양P/O 변전협력 총액공사(복합 7100 조작)","청양P/O 변전협력 총액공사 - 보령복합 7100 조작시험 (즉시가압 가능)","2024-09-10 09:00","2024-09-10 14:00","2024-09-10 09:00","2024-09-10 14:00","연속"]
[237,"대전세종충남","청양","아산보령TP#1 T/L","[송전] 345kV 청양-보령T/L 항공장애표시구 설치공사","1. 공사대상 : 345kV 청양-보령T/L No.1~1-1 (적색 4개) 2. 기타사항 ㅇ 345kV 아산-보령화력#1T/L과 병가구간으로 2개 회선 동시휴전 필요 ㅇ 미설치 시 항공시설법 위반으로 과태료 부과 대상","2024-09-11 08:00","2024-09-11 12:00","2024-09-11 08:00","2024-09-11 12:00","연속"]
[238,"대전세종충남","청양","청양보령TP#1 T/L","[송전] 345kV 청양-보령T/L 항공장애표시구 설치공사","1. 공사대상 : 345kV 청양-보령T/L No.1~1-1 (적색 4개) 2. 기타사항 ㅇ 345kV 아산-보령화력#1T/L과 병가구간으로 2개 회선 동시휴전 필요 ㅇ 미설치 시 항공시설법 위반으로 과태료 부과 대상","2024-09-11 08:00","2024-09-11 12:00","2024-09-11 08:00","2024-09-11 12:00","연속"]
[239,"대전세종충남","청양","청양S/S CB 7671","청양P/O 변전협력 총액공사(청양 7671 보통)","청양P/O 변전협력 총액공사 - 청양S/S 7671 보통점검 (즉시가압 가능)","2024-09-26 09:00","2024-09-26 15:00","2024-09-26 09:00","2024-09-26 15:00","연속"]
[240,"대전세종충남","청양","청양군산#1 T/L","[송전]345kV 청양군산#1T/L 가공지선 교체","No.131~137, 162~165 가공지선 교체","2024-09-23 08:00","2024-09-29 18:00","취소","취소","연속"]
[241,"대전세종충남","청양","청양신탕정#1 T/L","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L 최초가압전 선로정비 ㅇ정비대상 : 345kV 청양-신탕정T/L → 345kV 청양-신온양T/L 원복","2024-09-23 08:00","2024-11-28 18:00","취소","취소","연속"]
[242,"대전세종충남","청양","청양S/S #1 M.Tr","청양P/O 변전협력 총액공사(청양 #1M.Tr)","청양P/O 변전협력 총액공사 - 청양S/S #1M.Tr 휴전 - 1차 GIS 보통, 2차 GIS 조작, 3차 VCB 초기 - PT 하자, 부싱절연유 채유 (즉시가압 불가)","2024-09-09 09:00","2024-09-09 18:00","2024-09-09 09:00","2024-09-09 18:00","연속"]
[243,"대전세종충남","청양","청양신탕정#2 T/L","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L 최초가압전 선로정비 ㅇ정비대상 : 345kV 청양-신탕정T/L → 345kV 청양-신온양T/L 원복","2024-09-09 08:00","2024-09-27 18:00","취소","취소","연속"]
[244,"대전세종충남","청양","청양신온양#1 T/L CB","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L 최초가압전 선로정비 ㅇ정비대상 : 345kV 청양-신탕정T/L → 345kV 청양-신온양T/L 원복","2024-09-23 08:00","2024-10-01 18:00","취소","취소","연속"]
[245,"대전세종충남","청양","청양신온양#2 T/L CB","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L 최초가압전 선로정비 ㅇ정비대상 : 345kV 청양-신탕정T/L → 345kV 청양-신온양T/L 원복","2024-09-09 08:00","2024-09-11 18:00","취소","취소","연속"]
[246,"대전세종충남","청양","청양S/S CB 7372","청양P/O 변전협력 총액공사(청양 7372 조작)","청양P/O 변전협력 총액공사 - 청양S/S 7372 조작시험 (즉시가압 가능)","2024-09-30 14:00","2024-09-30 18:00","2024-09-30 14:00","2024-09-30 18:00","연속"]
[247,"대전세종충남","청양","청양S/S CB 7472","청양P/O 변전협력 총액공사(청양 7472 조작)","청양P/O 변전협력 총액공사 - 청양S/S 7472 조작시험 (즉시가압 가능)","2024-09-30 09:00","2024-09-30 14:00","2024-09-30 09:00","2024-09-30 14:00","연속"]
[248,"대전세종충남","청양","청양군산#2 T/L","[송전]345KV 청양군산#2T/L 애자련 보강","345KV 청양군산#1T/L 애자련 보강","2024-09-30 08:00","2024-10-03 18:00","취소","취소","연속"]
[249,"전북","군산","군산S/S #4 M.Tr","군산P/O 노후보호반 대체공사","군산S/S #4M.Tr 노후 보호반 대체공사","2024-09-09 09:00","2024-09-13 18:00","2024-09-09 09:00","2024-09-13 18:00","연속"]
[250,"전북","군산","군산신김제#2 T/L","345kV 군산-신김제#2T/L 품질불량 의심 접속함 교체공사","345kV 군산-신김제#2T/L(D) J/B#4 A상 중간접속함 해체 및 재접속","2024-09-02 09:00","2024-09-06 18:00","2024-09-02 09:00","2024-09-06 18:00","연속"]
[251,"전북","군산","군산S/S #2 M.Tr","군산S/S 170kV GIS 대체공사(6차, 무부하가압 선로)","- 군산S/S 군산-영등#2T/L 대체","2024-09-21 17:30","2024-09-21 18:00","2024-09-21 17:30","2024-09-21 18:00","연속"]
[252,"전북","군산","군산S/S #2 M.Tr","군산S/S 170kV GIS 대체공사(6차, 무부하가압 선로)","- 군산S/S 군산-영등#2T/L 대체","2024-09-26 18:00","2024-09-27 18:00","2024-09-26 18:00","2024-09-27 18:00","연속"]
[253,"전북","군산","새만금S/S #3 M.Tr","새만금S/S #3M.Tr 2차 부싱점검공사","새만금S/S #3M.Tr 2차 부싱점검공사","2024-09-12 09:00","2024-09-16 18:00","2024-09-12 09:00","2024-09-16 18:00","연속"]
[254,"전북","김제","신김제S/S #2 M.Tr","24년 김제P/O 부싱유 채유공사","부싱유 채유공사","2024-09-13 08:00","2024-09-13 18:00","2024-09-13 08:00","2024-09-13 18:00","연속"]
[255,"전북","김제","신김제S/S #1 M.Tr","24년 김제P/O 부싱유 채유공사","부싱유 채유공사","2024-09-12 08:00","2024-09-12 18:00","2024-09-12 08:00","2024-09-12 18:00","연속"]
[256,"전북","김제","신김제S/S #4 M.Tr","신김제S/S #4M.Tr OLTC 정밀점검","신김제S/S #4M.Tr OLTC 정밀점검","2024-09-09 09:00","2024-09-10 18:00","2024-09-09 09:00","2024-09-10 18:00","연속"]
[257,"전북","직할","신남원신광주#2 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사","345kV 신남원-신광주T/L No.1~115 수평 추락방지장치 및 조류착지방지장치 설치","2024-09-23 07:00","2024-10-01 17:00","취소","취소","매일"]
[258,"전북","직할","신남원광양#1 T/L","345kV 신남원-광양#1T/L 스페이서 철거공사","○ 345kV 볼트레스형 스페이서 철거 9EA ○ 구간 : No.212~214 구간","2024-09-06 09:00","2024-09-06 18:00","2024-09-06 09:00","2024-09-06 18:00","매일"]
[259,"광주전남","강진","신강진S/S #1 M.Tr","2024~25년 강진전력지사 변전협력회사 총액공사","신강진S/S #1M.Tr 1차 부싱 절연열화, 3차 BUS A, B, C상 PT 보통","2024-09-09 09:00","2024-09-09 18:00","2024-09-09 09:00","2024-09-09 18:00","연속"]
[260,"광주전남","강진","신화순신강진#2 T/L","2024~2025년 강진전력지사 송전협력회사 공사","신화순-신강진 224호 레일형 추락방지장치 설치공사","2024-09-26 07:00","2024-09-26 18:00","2024-09-26 07:00","2024-09-26 18:00","매일"]
[261,"광주전남","강진","신화순신강진#1 T/L","2024~2025년 강진전력지사 송전협력회사 공사","신화순-신강진 224호 레일형 추락방지장치 설치공사","2024-09-25 07:00","2024-09-25 18:00","2024-09-25 07:00","2024-09-25 18:00","매일"]
[262,"광주전남","강진","신강진S/S #2 M.Tr","2024~25년 강진전력지사 변전협력회사 총액공사","신강진S/S #2M.Tr A,B,C상 보통","2024-09-10 09:00","2024-09-12 18:00","2024-09-10 09:00","2024-09-12 18:00","연속"]
[263,"광주전남","강진","신강진S/S #1 M.Tr","2024-2025년 강진전력지사 변전협력회사 공사","신강진S/S #1M.Tr 1차 부싱 절연열화 측정 및 3차 BUS PT A,B,C상 보통점검","2024-09-09 09:00","2024-09-09 18:00","2024-09-09 09:00","2024-09-09 18:00","연속"]
[264,"광주전남","강진","신강진S/S #2 M.Tr","2024-2025년 강진전력지사 변전협력회사 공사","신강진S/S #2M.Tr A,B,C상 보통점검","2024-09-09 09:00","2024-09-12 18:00","2024-09-09 09:00","2024-09-12 18:00","연속"]
[265,"광주전남","광주","신광주S/S CB 7300","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체","2024-09-23 08:00","2024-10-18 18:00","2024-09-23 08:00","2024-10-18 18:00","연속"]
[266,"광주전남","광주","신광주S/S #1 BUS","장기사용 345kV #1BUS 모선보호반 교체","장기사용 345kV #1BUS 모선보호반 교체","2024-09-02 08:00","2024-09-06 18:00","취소","취소","연속"]
[267,"광주전남","광주","신광주S/S #2 BUS","장기사용 345kV #2BUS 모선보호반 교체","장기사용 345kV #2BUS 모선보호반 교체","2024-09-09 08:00","2024-09-13 18:00","취소","취소","연속"]
[268,"광주전남","광주","신광주S/S CB 7872","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-09-19 08:00","2024-09-19 18:00","2024-09-19 08:00","2024-09-19 18:00","연속"]
[269,"광주전남","광주","신광주S/S CB 7471","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-09-20 08:00","2024-09-20 18:00","2024-09-20 08:00","2024-09-20 18:00","연속"]
[270,"광주전남","광주","신광주S/S #2 M.Tr","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체","2024-09-23 08:00","2024-10-18 18:00","2024-09-23 08:00","2024-10-18 18:00","연속"]
[271,"광주전남","광주","신광주S/S CB 7400","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-09-25 08:00","2024-09-25 18:00","2024-09-25 08:00","2024-09-25 18:00","연속"]
[272,"광주전남","광주","신광주S/S CB 7400","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-09-24 08:00","2024-09-24 18:00","2024-09-24 08:00","2024-09-24 18:00","연속"]
[273,"광주전남","광주","신광주S/S CB 7500","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-09-23 08:00","2024-09-23 18:00","2024-09-23 08:00","2024-09-23 18:00","연속"]
[274,"광주전남","광주","신광주S/S CB 7472","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체","2024-09-23 08:00","2024-10-18 18:00","2024-09-23 08:00","2024-10-18 18:00","연속"]
[275,"광주전남","광주","신화순S/S #3 M.Tr","2024~2025년 광주전력지사 변전협력회사 공사","-주변압기 보통점검 -345kV GIS 조작시험(7500, 7572CB)","2024-09-03 09:00","2024-09-06 18:00","2024-09-03 09:00","2024-09-06 18:00","연속"]
[276,"광주전남","광주","신화순S/S CB 7800","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-09-11 08:00","2024-09-11 18:00","2024-09-11 08:00","2024-09-11 18:00","연속"]
[277,"광주전남","광주","신화순S/S CB 7900","24년 광주전력지사 170kV 이상 GIS 보통점검","- 362kV GIS 보통점검","2024-09-12 08:00","2024-09-12 18:00","2024-09-12 08:00","2024-09-12 18:00","연속"]
[278,"광주전남","목포","한빛1NP한빛2NP#1 T/L","[변전] 24~25년 목포전력지사 변전협력회사 총액공사","- 345kV 송 전 선 로 보 호 반 대 체","2024-09-24 09:00","2024-10-02 18:00","2024-09-24 09:00","2024-10-02 18:00","연속"]
[279,"광주전남","순천","광양하동TP#2 T/L","345kV 광양-하동TPT/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-09-25 07:00","2024-09-26 18:00","2024-09-25 07:00","2024-09-26 18:00","매일"]
[280,"광주전남","순천","여수T/P CB 7200","24-25년 순천전력지사 변전회사 총액공사","대시포트 누유로 인한 오링 교체 및 절연열화 측정(즉시가압 불가)","2024-09-02 08:00","2024-09-02 14:00","2024-09-02 08:00","2024-09-02 14:00","연속"]
[281,"대구","경산","신경산S/S #3 M.Tr","2024년 신경산 154kV GIS 교체공사","61-62-0 GIS 교체작업 안전확보","2024-09-26 11:00","2024-10-04 17:00","2024-09-26 11:00","2024-10-04 17:00","연속"]
[282,"대구","경산","신경산대구#1 T/L","345kV 울주-신경산 등 6개T/L 추락방지장치설치공사","(안전확보) 철탑추락방지장치 설치 - 작업구간 : No.2~30","2024-09-02 07:00","2024-09-06 18:00","2024-09-02 07:00","2024-09-06 18:00","연속"]
[283,"대구","경산","신경산대구#2 T/L","345kV 울주-신경산 등 6개T/L 추락방지장치설치공사","(안전확보) 철탑추락방지장치 설치 - 작업구간 : No.2~30","2024-09-09 07:00","2024-09-13 18:00","2024-09-09 07:00","2024-09-13 18:00","연속"]
[284,"대구","칠곡","북대구서대구#1 T/L","북대구S/S 7471 GIS 보통점검 및 Aux. Ry 전량교체","북대구S/S 7471 GIS 보통점검 및 Aux. Ry 전량교체","2024-09-23 09:30","2024-09-24 18:00","2024-09-23 09:30","2024-09-24 18:00","연속"]
[285,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S #1M.Tr 3차 64V 경보발생 관련 점검","서대구S/S #1M.Tr 3차 64V 경보발생 관련 점검","2024-09-27 09:30","2024-09-27 18:00","2024-09-27 09:30","2024-09-27 18:00","연속"]
[286,"대구","칠곡","북경남서대구#2 T/L","24~25년 칠곡전력지사 가공송전 협력회사 총액공사","345kV 북경남-서대구T/L 수평 추락방지장치 설치","2024-09-02 08:00","2024-09-09 18:00","2024-09-02 08:00","2024-09-09 18:00","연속"]
[287,"대구","칠곡","서대구S/S #3 M.Tr","서대구S/S 7671, 7600 GCB 보통점검","서대구S/S 7671, 7600 GCB 보통점검","2024-09-05 09:30","2024-09-05 18:00","2024-09-05 09:30","2024-09-05 18:00","연속"]
[288,"대구","칠곡","북경남서대구#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 북경남-서대구T/L 수평 추락방지장치 설치공사","2024-09-23 07:00","2024-10-09 18:00","2024-09-23 07:00","2024-10-09 18:00","연속"]
[289,"대구","포항","신포항신영일 T/L","2024~25년도 포항전력지사 변전총액공사","신영일S/S 7771 GIS 조작시험","2024-09-23 09:00","2024-09-23 18:00","2024-09-23 09:00","2024-09-23 18:00","연속"]
[290,"대구","포항","신포항청송PP T/L","2024~2025년 포항전력지사 가공송전 협력회사 공사","조류착지방지장치 설치","2024-09-19 07:00","2024-10-10 18:00","2024-09-19 07:00","2024-10-10 18:00","연속"]
[291,"대구","포항","신포항S/S #3 M.Tr","2024~25년도 포항전력지사 변전총액공사","신포항S/S #3M.Tr, 2차 LA,PT, 3차 LA,PT 초기점검 신포항S/S #3M.Tr 1차 LA,PT, 7871, 7872 GIS 보통점검 신포항S/S 6B72 GIS 하자점검","2024-09-26 09:00","2024-09-26 18:00","2024-09-26 09:00","2024-09-26 18:00","연속"]
[292,"대구","포항","월성NP신월성NP#2 T/L","2024~25년도 포항전력지사 변전총액공사","월성S/Y 7871 GIS 조작시험 및 월성연락#2T/L PT 보통점검 신월성S/Y 7271 GIS 조작시험","2024-09-19 09:00","2024-09-19 18:00","2024-09-19 09:00","2024-09-19 18:00","연속"]
[293,"경북","구미","선산S/S #1 M.Tr","2024-25년 구미전력지사 변전협력회사 공사","- 1차 7072 GIS 조작시험, 절연열화 측정 - 2차 6144 GIS 보통점검[정밀] - 154kV GIS DS 방압변 점검","2024-09-06 09:00","2024-09-06 18:00","2024-09-06 09:00","2024-09-06 18:00","연속"]
[294,"경북","구미","선산S/S #4 M.Tr","2024-25년 구미전력지사 변전협력회사 공사","- 1차 A,B상, 2차 A,B,C상 부싱 절연유 채유 - M.Tr 보통점검[정밀] - 변압기 추락방지장치 설치 - 2차 6444 GIS 보통점검[정밀] - 154kV GIS DS 방압변 점검","2024-09-04 09:00","2024-09-05 18:00","2024-09-04 09:00","2024-09-05 18:00","연속"]
[295,"경북","구미","서대구선산#1 T/L","2024-2025년 구미전력지사 송전협력회사 공사","345kV 서대구-선산#1T/L 추락방지시설 설치(수평 32기 No.1~29, 102, 103, 106)","2024-09-25 07:30","2024-10-02 18:00","2024-09-25 07:30","2024-10-02 18:00","매일"]
[296,"경북","구미","북대구선산 T/L","2024-2025년 구미전력지사 송전협력회사 공사","345kV 북대구-선산T/L 추락방지시설 설치(수평 3기 No.102, 103, 106)","2024-09-26 07:30","2024-09-26 18:00","2024-09-26 07:30","2024-09-26 18:00","매일"]
[297,"경북","영주","신제천신영주#2 T/L","345kV 신제천-신영주T/L 송전선로 정밀점검","345kV 신제천-신영주T/L 송전선로 정밀점검","2024-09-09 08:00","2024-09-13 17:00","2024-09-09 08:00","2024-09-13 17:00","매일"]
[298,"경북","영주","신제천신영주#1 T/L","345kV 신제천-신영주T/L 송전선로 정밀점검","345kV 신제천-신영주T/L 송전선로 정밀점검","2024-09-02 08:00","2024-09-06 17:00","2024-09-02 08:00","2024-09-06 17:00","매일"]
[299,"경북","영주","한울2N/P CB 7G71","2024~25년 영주전력지사 변전협력회사 총액공사","7G71 GIS 보통점검","2024-09-23 09:00","2024-09-23 18:00","2024-09-23 09:00","2024-09-23 18:00","연속"]
[300,"경북","영주","신태백한울NP#2 T/L","2024년 한울2발S/Y 345kV GIS 정밀점검","2024년 한울2발S/Y 345kV GIS 정밀점검","2024-09-02 09:00","2024-09-06 18:00","2024-09-02 09:00","2024-09-06 18:00","연속"]
[301,"경북","영주","한울2N/P CB 7F71","2024~25년 영주전력지사 변전협력회사 총액공사","7F71 GIS 보통점검","2024-09-24 09:00","2024-09-24 18:00","2024-09-24 09:00","2024-09-24 18:00","연속"]
[302,"경북","영주","한울2N/P CB 7G00","2024~25년 영주전력지사 변전협력회사 총액공사","7G00 GIS 보통점검","2024-09-23 09:00","2024-09-23 18:00","2024-09-23 09:00","2024-09-23 18:00","연속"]
[303,"경북","영주","한울2N/P CB 7G72","2024~25년 영주전력지사 변전협력회사 총액공사","7G72 GIS 보통점검","2024-09-25 09:00","2024-09-25 18:00","2024-09-25 09:00","2024-09-25 18:00","연속"]
[304,"경북","영주","한울2N/P CB 7F72","2024~25년 영주전력지사 변전협력회사 총액공사","7F72 GIS 보통점검","2024-09-25 09:00","2024-09-25 18:00","2024-09-25 09:00","2024-09-25 18:00","연속"]
[305,"경북","영주","한울2N/P CB 7F00","2024~25년 영주전력지사 변전협력회사 총액공사","7F00 GIS 보통점검","2024-09-24 09:00","2024-09-24 18:00","2024-09-24 09:00","2024-09-24 18:00","연속"]
[306,"경북","영주","신한울한울#1 T/L","동해안변환소 AC배후계통(변전) 건설공사","- 동해안변환소 AC배후계통건설 관련 사전작업 RTU 및 집감반 신규설치(신규 선로보호반 설치를 위한 공간확보)","2024-09-10 09:00","2024-09-11 18:00","2024-09-10 09:00","2024-09-11 18:00","연속"]
[307,"경북","영주","신한울한울#2 T/L","동해안변환소 AC배후계통(변전) 건설공사","- 동해안변환소 AC배후계통건설 관련 사전작업 RTU 및 집감반 신규설치(신규 선로보호반 설치를 위한 공간확보)","2024-09-24 09:00","2024-09-25 18:00","2024-09-24 09:00","2024-09-25 18:00","연속"]
[308,"경북","영주","한울3N/P CB 7D72","동해안변환소 AC배후계통(변전) 건설공사","- 동해안변환소 AC배후계통건설 관련 사전작업 RTU 및 집감반 신규설치(신규 선로보호반 설치를 위한 공간확보)","2024-09-24 09:00","2024-09-25 18:00","2024-09-24 09:00","2024-09-25 18:00","연속"]
[309,"경북","영주","한울3N/P CB 7D72","동해안변환소 AC배후계통(변전) 건설공사","- 동해안변환소 AC배후계통건설 관련 사전작업 RTU 및 집감반 신규설치(신규 선로보호반 설치를 위한 공간확보)","2024-09-10 09:00","2024-09-11 18:00","2024-09-10 09:00","2024-09-11 18:00","연속"]
[310,"경북","직할","신영주청송PP T/L","24년 가공송전 순시점검 위탁공사 정밀점검","정밀점검:345kV 신영주-청송PPT/L No.49~102","2024-09-09 09:00","2024-09-13 18:00","2024-09-09 09:00","2024-09-13 18:00","연속"]
[311,"부산울산","동부산","고리N/P #1 CLR CB","고리NP S/Y 345kV CLR 보호반 대체","1. 고리NP S/Y 345kV #1CLR B/F PNL 2. 고리NP S/Y 345kV #1CLR #1 1ST,2ND PNL, #1CLR #2 1ST,2ND PNL 3. 7077GIS 차단기 동작시험 4. 7077,7177GIS 절연열화 측정","2024-09-23 09:00","2024-10-02 18:00","2024-09-23 09:00","2024-10-02 18:00","연속"]
[312,"부산울산","동부산","신고리고리NP#1 T/L","2024-2025년 동부산전력지사 가공송전협력회사 공사","-불량개소정비","2024-09-19 07:00","2024-09-19 18:00","취소","취소","연속"]
[313,"부산울산","동부산","신고리고리NP#4 T/L","2024-2025년 동부산전력지사 가공송전협력회사 공사","-지선철거작업","2024-09-20 07:00","2024-09-20 18:00","취소","취소","연속"]
[314,"부산울산","동부산","신양산고리NP#1 T/L","신양산S/S 345kV 용량부족차단기 교체공사(4차)","신양산S/S 345kV 76BAY 내전압시험 관련 휴전(안전이격) - 9/6 08:00~10:00 - 9/8 14:00~16:00","2024-09-06 08:00","2024-09-08 18:00","2024-09-06 08:00","2024-09-08 18:00","매일"]
[315,"부산울산","동부산","신양산신대연#2 T/L","2024-2025년 동부산 가공송전협력회사 공사","폴리머점퍼지지애자 설치 및 조류착지방지장치 설치","2024-09-26 08:00","2024-09-26 18:00","2024-09-26 08:00","2024-09-26 18:00","연속"]
[316,"부산울산","동부산","신양산S/S #1 BUS","신양산S/S 345kV 용량부족차단기 교체공사(4차)","신양산S/S 345kV 76BAY GIS 시험가압(24H) - 시험가압 선로 : 신양산-북부산 #1T/L + 345kV #1BUS - 시험가압 대상 : 7671, 7600","2024-09-25 08:00","2024-09-26 08:00","2024-09-25 08:00","2024-09-26 08:00","연속"]
[317,"부산울산","동부산","신양산북부산#1 T/L","신양산S/S 345kV 용량부족차단기 교체공사(4차)","신양산S/S 345kV 76BAY GIS 시험가압(24H) - 시험가압 선로 : 신양산-북부산 #1T/L + 345kV #1BUS - 시험가압 대상 : 7671, 7600","2024-09-25 08:00","2024-09-26 08:00","2024-09-25 08:00","2024-09-26 08:00","연속"]
[318,"부산울산","동부산","신양산고리NP#1 T/L","2024년 가공송전 순시점검 위탁공사","송전선로 스페이서 댐퍼 설치 및 간격조정 시행","2024-09-23 09:00","2024-09-23 18:00","2024-09-23 09:00","2024-09-23 18:00","연속"]
[319,"부산울산","동부산","신양산신대연#1 T/L","2024-2025년 동부산 가공송전협력회사 공사","폴리머점퍼지지애자 설치 및 조류착지방지장치 설치","2024-09-24 07:00","2024-09-25 18:00","2024-09-24 07:00","2024-09-25 18:00","연속"]
[320,"부산울산","동부산","신양산북부산#2 T/L","2024-2025년 동부산 가공송전협력회사 공사","폴리머점퍼지지애자 설치 및 소도체 이도조정","2024-09-09 07:00","2024-09-12 18:00","2024-09-09 07:00","2024-09-12 18:00","연속"]
[321,"부산울산","동부산","신양산S/S CB 7500","신양산S/S 345kV 용량부족차단기 교체공사(4차)","신양산S/S 345kV #4M.Tr GIB 설치(75BAY) - 휴전대상 : 7500, 7572","2024-09-26 08:00","2024-10-15 18:00","2024-09-26 08:00","2024-10-15 18:00","연속"]
[322,"부산울산","동부산","신양산고리NP#2 T/L","신고리 1,2호기 지하전력구 신설 공사","신고리 1,2호기 지하전력구 신설 공사를 위한 흙막이 가시설 설치","2024-09-02 10:00","2025-03-03 10:00","취소","취소","연속"]
[323,"부산울산","동부산","신양산고리NP#1 T/L","신고리 1,2호기 지하전력구 신설 공사","신고리 1,2호기 지하전력구 신설 공사를 위한 흙막이 가시설 설치","2024-09-02 10:00","2025-03-03 10:00","취소","취소","연속"]
[324,"부산울산","동부산","신양산S/S CB 7572","신양산S/S 345kV 용량부족차단기 교체공사(4차)","신양산S/S 345kV #4M.Tr GIB 설치(75BAY) - 휴전대상 : 7500, 7572","2024-09-26 08:00","2024-10-15 18:00","2024-09-26 08:00","2024-10-15 18:00","연속"]
[325,"부산울산","북부산","북부산고리NP#2 T/L","신고리 1,2호기 지하전력구 신설 공사","신고리 1,2호기 지하전력구 신설 공사를 위한 흙막이 가시설 설치","2024-09-02 10:00","2025-03-03 10:00","취소","취소","연속"]
[326,"부산울산","북부산","북부산고리NP#1 T/L","신고리 1,2호기 지하전력구 신설 공사","신고리 1,2호기 지하전력구 신설 공사를 위한 흙막이 가시설 설치","2024-09-02 10:00","2025-03-03 10:00","취소","취소","연속"]
[327,"부산울산","북부산","북부산S/S #4 M.Tr","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S 345kV #4M.Tr 보호반 대체공사","2024-09-09 09:00","2024-09-13 18:00","2024-09-09 09:00","2024-09-13 18:00","연속"]
[328,"부산울산","북부산","북부산S/S #4 Sh.R CB","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S 345kV #4Sh.R 변압기추락방지장치 설치","2024-09-19 09:00","2024-09-19 18:00","2024-09-19 09:00","2024-09-19 18:00","연속"]
[329,"부산울산","북부산","북부산S/S #2 Sh.R CB","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S 345kV #2Sh.R 보통점검","2024-09-20 09:00","2024-09-20 18:00","2024-09-20 09:00","2024-09-20 18:00","연속"]
[330,"부산울산","북부산","북부산S/S #3 Sh.R CB","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S 345kV #3Sh.R 추락방지장치 설치","2024-09-26 09:00","2024-09-26 18:00","2024-09-26 09:00","2024-09-26 18:00","연속"]
[331,"부산울산","북부산","북부산신울산#1 T/L","2024년 가공송전선로 순시점검 위탁공사 정밀점검 및 기타보수","345kV 북부산-신울산#1T/L 정밀점검 잔여분 및 기타 보수작업 시행 22~27호","2024-09-25 09:00","2024-09-27 18:00","2024-09-25 09:00","2024-09-27 18:00","연속"]
[332,"부산울산","북부산","북부산S/S CB 7771","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S 345kV 신양산-북부산#2T/L 7771 GIS 조작시험","2024-09-25 09:00","2024-09-25 18:00","2024-09-25 09:00","2024-09-25 18:00","연속"]
[333,"부산울산","북부산","북부산S/S #1 Sh.R CB","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S 345kV #1Sh.R 추락방지장치 설치","2024-09-27 09:00","2024-09-27 18:00","2024-09-27 09:00","2024-09-27 18:00","연속"]
[334,"부산울산","서부산","신녹산S/S CB 7200","신녹산S/S 345kV GIS 동작시험 - 7200","신녹산S/S 345kV GIS 동작시험 - 7200","2024-09-24 09:00","2024-09-24 13:00","2024-09-24 09:00","2024-09-24 13:00","연속"]
[335,"부산울산","서부산","신녹산S/S CB 7372","신녹산S/S 345kV GIS 동작시험 - 7372","신녹산S/S 345kV GIS 동작시험 - 7372","2024-09-25 09:00","2024-09-25 18:00","2024-09-25 09:00","2024-09-25 18:00","연속"]
[336,"부산울산","서부산","신녹산S/S CB 7300","신녹산S/S 345kV GIS 동작시험 - 7300","신녹산S/S 345kV GIS 동작시험 - 7300","2024-09-24 13:00","2024-09-24 18:00","2024-09-24 13:00","2024-09-24 18:00","연속"]
[337,"부산울산","서부산","신녹산S/S CB 7272","신녹산S/S 345kV GIS 동작시험 - 7272","신녹산S/S 345kV GIS 동작시험 - 7272","2024-09-25 09:00","2024-09-25 18:00","2024-09-25 09:00","2024-09-25 18:00","연속"]
[338,"부산울산","울산","남울산울산TP#2 T/L","24년 울산전력지사 변전협력회사 총액공사","- 일진제 GIS 하자보수 7491DS 발청보수 - 일진제 GIS 하자보수 7471CB 유압조작기 교체 - 7471,7400 2점절 균압콘덴서 절연열화 측정","2024-09-23 09:00","2024-09-25 18:00","2024-09-23 09:00","2024-09-25 18:00","연속"]
[339,"부산울산","울산","울산C/C #3 Tie-Tr","24년 울산전력지사 변전협력회사 총액공사","-울산TP측 2차GIS 동작시험 -1,2차 LA 보통점검 -3차 PT 보통점검","2024-09-11 09:00","2024-09-11 18:00","2024-09-11 09:00","2024-09-11 18:00","연속"]
[340,"부산울산","울산","울주울산TP#2 T/L","2024년 가공송전 순시점검 위탁공사","송전선로 정밀점검 안전이격 확보","2024-09-26 09:00","2024-09-27 18:00","2024-09-26 09:00","2024-09-27 18:00","연속"]
[341,"부산울산","울산","울주울산TP#1 T/L","2024년 가공송전 순시점검 위탁공사","송전선로 정밀점검 안전이격 확보","2024-09-30 09:00","2024-10-01 18:00","2024-09-30 09:00","2024-10-01 18:00","연속"]
[342,"부산울산","직할","신대연S/S #1 M.Tr","신대연S/S 345kV GIS 정밀점검공사(7579)","신대연S/S #2Sh.R GIS (7579) 정밀점검 공사, 무부하가압","2024-09-13 17:00","2024-09-13 18:00","2024-09-13 17:00","2024-09-13 18:00","연속"]
[343,"부산울산","직할","신대연S/S #2 BUS","신대연S/S 345kV GIS 정밀점검공사(7579)","신대연S/S #2Sh.R GIS (7579) 정밀점검 공사, 무부하가압","2024-09-13 17:00","2024-09-13 18:00","2024-09-13 17:00","2024-09-13 18:00","연속"]
[344,"부산울산","직할","신양산신대연#1 T/L","신대연S/S 345kV GIS 정밀점검공사(7579)","신대연S/S #2Sh.R GIS (7579) 정밀점검 공사, 무부하가압","2024-09-13 17:00","2024-09-13 18:00","2024-09-13 17:00","2024-09-13 18:00","연속"]
[345,"부산울산","직할","신대연S/S #2 Sh.R CB","신대연S/S 345kV GIS 정밀점검공사(7579)","신대연S/S #2Sh.R GIS (7579) 정밀점검 공사","2024-09-10 09:00","2024-09-13 18:00","2024-09-10 09:00","2024-09-13 18:00","연속"]
[346,"경남","고성하이S/Y","신고성고성하이TP#1 T/L","신고성고성하이발전#1T/L 초기점검","충전부 점검, 볼트조임, 열화상, 접지저항측정점검","2024-09-02 08:30","2024-09-03 18:00","2024-09-02 08:30","2024-09-03 18:00","연속"]
[347,"경남","신마산","신마산S/S #4 M.Tr","신마산S/S #4M.Tr 1차 EBG 해체점검","신마산S/S #4M.Tr 1차 EBG 해체점검","2024-09-02 09:00","2024-09-13 18:00","2024-09-02 09:00","2024-09-13 18:00","연속"]
[348,"경남","북경남","북경남S/S #5 Sh.R CB","북경남S/S 345kV GIS 균압콘덴서 재측정 관련 휴전","북경남S/S 345kV GIS 균압콘덴서 재측정 관련 휴전(7700)","2024-09-03 09:00","2024-09-03 18:00","2024-09-03 09:00","2024-09-03 18:00","연속"]
[349,"경남","북경남","북경남S/S CB 7700","북경남S/S 345kV GIS 균압콘덴서 재측정 관련 휴전","북경남S/S 345kV GIS 균압콘덴서 재측정(7700)","2024-09-03 09:00","2024-09-03 18:00","2024-09-03 09:00","2024-09-03 18:00","연속"]
[350,"경남","북경남","북경남S/S #71 BUS","북경남S/S 345kV GIS 균압콘덴서 재측정 관련 휴전","북경남S/S 345kV GIS 균압콘덴서 재측정 관련 휴전(7771, 7871, 7A71, 7C71)","2024-09-03 09:00","2024-09-04 18:00","2024-09-03 09:00","2024-09-04 18:00","연속"]
[351,"경남","북경남","북경남S/S #6 Sh.R CB","북경남S/S 345kV GIS 균압콘덴서 재측정 관련 휴전","북경남S/S 345kV GIS 균압콘덴서 재측정 관련 휴전(7979)","2024-09-04 09:00","2024-09-04 18:00","2024-09-04 09:00","2024-09-04 18:00","연속"]
[352,"경남","의령","의령신마산#2 T/L","의령S/S 345kV 의령-신마산#2T/L 휴전작업","의령S/S 345kV 의령-신마산#2T/L 휴전작업 7A71, 7A00 GIS 보통점검 [병행] 의령-신마산#2T/L PT 보통점검","2024-09-04 09:00","2024-09-04 18:00","2024-09-30 09:00","2024-09-30 18:00","연속"]
[353,"경남","북경남","북경남S/S #6Sh.R CB","북경남S/S 345kV GIS 균압콘덴서 재측정 관련 휴전","북경남S/S 345kV GIS 균압콘덴서 재측정 관련 휴전(7979)","2024-09-04 09:00","2024-09-04 18:00","2024-09-04 09:00","2024-09-04 18:00","연속"]
[354,"경남","의령","의령하동화력#1 T/L","의령S/S 345kV 의령-하동화력#1T/L 휴전작업","의령S/S 345kV 의령-하동화력#1T/L 휴전작업 LA(A, B, C) 보통, PT(B, C) 대체","2024-09-05 09:00","2024-09-05 18:00","취소","취소","연속"]
[355,"경남","고성하이S/Y","고성T/P 7171","고성하이S/Y 신고성-고성하이S/Y GIS 보통점검","고성하이S/Y 신고성-고성하이S/Y GIS 보통점검","2024-09-06 09:30","2024-09-06 18:00","2024-09-06 09:30","2024-09-06 18:00","연속"]
[356,"경남","신김해","신마산신김해#1 T/L","신김해S/S 신마산신김해#1T/L LA,CPD 보통","신김해S/S 신마산신김해#1T/L LA,CPD 보통","2024-09-07 09:30","2024-09-07 17:30","2024-09-07 09:30","2024-09-07 17:30","연속"]
[357,"경남","신김해","신마산신김해#2 T/L","신김해S/S 신마산신김해#2T/L LA,CPD 보통","신김해S/S 신마산신김해#2T/L LA,CPD 보통","2024-09-08 09:30","2024-09-08 17:30","2024-09-08 09:30","2024-09-08 17:30","연속"]
[358,"경남","북경남","북경남서대구#1 T/L","북경남S/S 345kV GIS 균압콘덴서 재측정 관련 휴전","북경남S/S 345kV GIS 균압콘덴서 재측정 관련 휴전(7A00, 7A72)","2024-09-09 09:00","2024-09-09 18:00","2024-09-09 09:00","2024-09-09 18:00","연속"]
[359,"경남","북경남","북경남S/S #76 BUS","북경남S/S 345kV GIS 균압콘덴서 재측정 관련 휴전","북경남S/S 345kV GIS 균압콘덴서 재측정 관련 휴전(7A72)","2024-09-09 09:00","2024-09-09 18:00","2024-09-09 09:00","2024-09-09 18:00","연속"]
[360,"경남","의령","의령S/S CB 7600","의령S/S 345kV 7600 GIS 보통점검(차단기 단독)","의령S/S 345kV 7600 GIS 보통점검(차단기 단독)","2024-09-09 09:00","2024-09-09 15:00","2024-09-09 09:00","2024-09-09 15:00","연속"]
[361,"경남","신김해","신김해S/S #2 M.Tr","신김해S/S 345kV #2 M.Tr A상 보통","신김해S/S 345kV #2 M.Tr A상 보통","2024-09-09 09:30","2024-09-10 17:30","2024-09-09 09:30","2024-09-10 17:30","연속"]
[362,"경남","의령","의령S/S #2 M.Tr","의령S/S 345kV #2M.Tr 휴전 작업","1. 345kV #2M.Tr 1차 GIS(7572), 2차 GIS(6244) 보통점검 2. 1, 3차 LA 하자 / 1, 2차 부싱 절연유 채유 / 추락방지장치 설치 3. #2S.Tr 본체 보통 / 3차 VCB 4279,4284 보통, 427-1 조작 / 조류방지커버정비","2024-09-10 09:00","2024-09-11 18:00","2024-09-10 09:00","2024-09-11 18:00","연속"]
[363,"경남","의령","의령S/S CB 7500","의령S/S 345kV 7500 GIS 보통점검(차단기 단독)","의령S/S 345kV 7500 GIS 보통점검","2024-09-10 09:00","2024-09-10 18:00","2024-09-10 09:00","2024-09-10 18:00","연속"]
[364,"경남","신김해","신김해S/S #3 M.Tr","신김해S/S 345kV #3 M.Tr 보통","신김해S/S 345kV #3 M.Tr 보통","2024-09-11 09:30","2024-09-13 17:30","2024-09-11 09:30","2024-09-13 17:30","연속"]
[365,"경남","하동","의령하동화력#2 T/L","345kV 의령-하동화력#2T/L 휴전 작업","345kV 의령-하동화력#2T/L GIS 7571 보통 [병행] PT(B, C) 대체 / PT(A), LA(A,B,C) 보통 [병행, 의령] 7271, 7200 GIS 보통 [병행, 의령] PT(A,B,C), LA(A,B,C) 보통","2024-09-12 09:00","2024-09-12 18:00","취소","취소","연속"]
[366,"경남","신김해","신김해S/S #75 BUS","신김해S/S 345kV 용량부족 GIS 교체공사","신김해S/S 345kV 용량부족 GIS 교체공사","2024-09-19 09:00","2024-09-28 18:00","2024-09-19 09:00","2024-09-28 18:00","연속"]
[367,"경남","신고성","신고성S/S #4 M.Tr","신고성S/S #4M.Tr 3차측 설비점검 등","신고성S/S #4M.Tr 3차측 설비점검 등","2024-09-20 09:30","2024-09-20 18:00","2024-09-20 09:30","2024-09-20 18:00","연속"]
[368,"경남","북경남","북경남무주양수 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 북경남-무주양수T/L 수평 추락방지장치 설치공사","2024-09-24 07:00","2024-10-09 18:00","2024-09-24 07:00","2024-10-09 18:00","연속"]
[369,"경남","하동","하동T/P CB 7872","하동T/P 345kV 7800, 7872 GIS 조작시험","하동T/P 345kV 7800, 7872 GIS 조작시험","2024-09-24 10:00","2024-09-24 18:00","2024-09-24 10:00","2024-09-24 18:00","연속"]
[370,"경남","하동","하동T/P CB 7800","하동T/P 345kV 7800, 7872 GIS 조작시험","하동T/P 345kV 7800, 7872 GIS 조작시험","2024-09-24 10:00","2024-09-24 18:00","2024-09-24 10:00","2024-09-24 18:00","연속"]
[371,"경남","신고성","신고성S/S CB 7400","신고성S/S 345kV 4호기 7400 GIS 보통점검","신고성S/S 345kV 4호기 7400 GIS 보통점검","2024-09-25 09:30","2024-09-25 18:00","2024-09-25 09:30","2024-09-25 18:00","연속"]
[372,"경남","의령","의령S/S SEC CB 70710","의령S/S 345kV 70-71, 75-76-0 GIS 보통점검","의령S/S 345kV 70-71, 75-76-0 GIS 보통점검","2024-09-26 09:00","2024-09-26 14:00","2024-09-26 09:00","2024-09-26 14:00","연속"]
[373,"경남","신김해","신김해S/S #5 M.Tr","신김해S/S 345kV 용량부족 GIS 교체공사","신김해S/S 345kV 용량부족 GIS 교체공사","2024-09-26 09:00","2024-09-28 18:00","2024-09-26 09:00","2024-09-28 18:00","연속"]
[374,"경남","신고성","신고성S/S CB 7471","신고성S/S 345kV 4호기 7471 GIS 보통점검","신고성S/S 345kV 4호기 7471 GIS 보통점검","2024-09-26 09:30","2024-09-26 18:00","2024-09-26 09:30","2024-09-26 18:00","연속"]
[375,"경남","의령","의령S/S SEC CB 75760","의령S/S 345kV 70-71, 75-76-0 GIS 보통점검","의령S/S 345kV 70-71, 75-76-0 GIS 보통점검","2024-09-26 14:00","2024-09-26 17:00","2024-09-26 14:00","2024-09-26 17:00","연속"]
[376,"경남","신마산","신마산S/S #5 M.Tr","신마산S/S #5M.Tr 1차 EBG 해체점검","신마산S/S #5M.Tr 1차 EBG 해체점검","2024-09-30 09:00","2024-10-11 18:00","2024-09-30 09:00","2024-10-11 18:00","연속"]
[377,"경남","신김해","신김해S/S CB 7800","신김해S/S 7800 조작시험","신김해S/S 7800 조작시험","2024-09-30 09:30","2024-09-30 17:30","2024-09-30 09:30","2024-09-30 17:30","연속"]

{"sheet":"154설비","index":2,"n_rows":830,"n_cols":11,"rows_kept":830,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2024년도 9월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","구의광장#2 T/L","2024년 성동P/O 170kV GIS 정밀점검","- 170kV GIS 정밀점검","2024-09-02 09:00","2024-09-04 18:00","2024-09-01 09:00","2024-09-02 18:00","연속"]
[2,"서울","성동","구의광장#2 T/L","154kV 세니온제 단거리 송전선로 보호계전기 성능개선","154kV 세니온제 87 계전기 성능개선 시행 - 내용 : 87, 87+21 계전기 펌웨어 업데이트","2024-09-05 10:00","2024-09-05 18:00","취소","취소","연속"]
[3,"서울","성동","구의광장#1 T/L","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","구의-광장#1T/L, #2M.Tr 1차 GIS 교체","2024-09-09 09:00","2024-10-10 18:00","2024-09-09 09:00","2024-10-10 18:00","연속"]
[4,"서울","성동","구의S/S #1 BUS","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","구의-광장#1T/L, #2M.Tr 1차 GIS 교체","2024-09-12 15:00","2024-09-27 15:00","2024-09-12 15:00","2024-09-27 15:00","연속"]
[5,"서울","성동","구의광장#2 T/L","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","구의-광장#1T/L, #2M.Tr 1차 GIS 교체","2024-09-11 15:00","2024-09-12 15:00","2024-09-11 15:00","2024-09-12 15:00","연속"]
[6,"서울","성동","구의S/S CB 6100","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","구의-광장#1T/L, #2M.Tr 1차 GIS 교체","2024-09-09 09:00","2024-10-10 18:00","2024-09-09 09:00","2024-10-10 18:00","연속"]
[7,"서울","성동","구의광장#2 T/L","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","구의-광장#1T/L, #2M.Tr 1차 GIS 교체","2024-09-26 15:00","2024-09-27 15:00","2024-09-26 15:00","2024-09-27 15:00","연속"]
[8,"서울","성동","구의S/S #2 BUS","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","구의-광장#1T/L, #2M.Tr 1차 GIS 교체","2024-09-09 09:00","2024-09-12 15:00","2024-09-09 09:00","2024-09-12 15:00","연속"]
[9,"서울","성동","안암노원#2 T/L","장위 재개발관련 지장송전선로 이설공사","1. 대상선로 : 154kV 안암-노원#2 T/L 2. 공사내용 : 지장송전선로 이설","2024-09-02 09:00","2024-10-25 18:00","2024-09-02 09:00","2024-10-25 18:00","연속"]
[10,"서울","성동","성수뚝도#2 T/L","2024년 성동P/O 170kV GIS 정밀점검","- 170kV GIS 정밀점검","2024-09-09 09:00","2024-09-10 18:00","2024-09-07 09:00","2024-09-08 18:00","연속"]
[11,"서울","성동","성수뚝도#1 T/L","2024년 성동P/O 170kV GIS 정밀점검","- 170kV GIS 정밀점검","2024-09-05 09:00","2024-09-06 18:00","2024-09-05 09:00","2024-09-06 18:00","연속"]
[12,"서울","성동","성동마장#2 T/L","24년 성동P/O 변전협력회사 공사","154kV GIS 조작시험","2024-09-12 14:00","2024-09-12 18:00","2024-09-12 14:00","2024-09-12 18:00","연속"]
[13,"서울","성동","성동S/S #65 BUS","성동S/S 154kV Sh.R 설치공사","1. 154kV Sh.R(20MVAR×3) × 2조 설치 2. 154kV Sh.R 1차 GIS × 2Bay 설치 3. 기타 부대공사 × 1식","2024-09-25 09:00","2024-10-01 14:00","취소","취소","연속"]
[14,"서울","성동","성동마장#1 T/L","24년 성동P/O 변전협력회사 공사","154kV GIS 조작시험","2024-09-12 09:00","2024-09-12 14:00","2024-09-12 09:00","2024-09-12 14:00","연속"]
[15,"서울","성동","군자성수 T/L","2024~25년 성동P/O 변전협력회사 공사","170kV GIS 보통점검","2024-09-11 10:00","2024-09-11 18:00","2024-09-11 10:00","2024-09-11 18:00","연속"]
[16,"서울","성동","수유미아 T/L","수유분기 170kV GIS 증설공사","- 170kV GIS 증설공사 관련 설비 감압(증설 옆 베이) - #1BUS 시험 가압","2024-09-09 09:00","2024-09-12 18:00","2024-09-09 09:00","2024-09-12 18:00","연속"]
[17,"서울","성동","수유S/S #1 BUS","수유분기 170kV GIS 증설공사","- 170kV GIS 증설공사","2024-09-09 09:00","2024-09-12 18:00","2024-09-09 09:00","2024-09-12 18:00","연속"]
[18,"서울","성동","수유S/S #2 BUS","수유분기 170kV GIS 증설공사","- 170kV GIS 증설공사","2024-09-19 09:00","2024-09-24 18:00","2024-09-19 09:00","2024-09-24 18:00","연속"]
[19,"서울","성동","수유S/S CB 6100","수유분기 170kV GIS 증설공사","- 170kV GIS 증설공사 관련 설비 감압(증설 옆 베이)","2024-09-19 09:00","2024-09-24 18:00","2024-09-19 09:00","2024-09-24 18:00","연속"]
[20,"서울","성동","수유미아 T/L","수유분기 170kV GIS 증설공사","- 170kV GIS 증설공사 관련 설비 감압(증설 옆 베이) - #2BUS 시험 가압","2024-09-19 09:00","2024-09-24 18:00","2024-09-19 09:00","2024-09-24 18:00","연속"]
[21,"서울","성동","수유S/S #1 BUS","수유분기 170kV GIS 증설공사","- 170kV GIS 증설공사(준공시험 등)","2024-09-25 09:00","2024-09-26 18:00","2024-09-25 09:00","2024-09-26 18:00","연속"]
[22,"서울","성동","수유S/S CB 6100","수유분기 170kV GIS 증설공사","- 170kV GIS 증설공사 관련 설비 감압(증설 옆 베이)","2024-09-09 09:00","2024-09-12 18:00","2024-09-09 09:00","2024-09-12 18:00","연속"]
[23,"서울","성동","구리신내#1 T/L","신내중계 170kV GIS 증설공사","- 170kV GIS 정밀점검(#1BUS 시험가압)","2024-09-25 15:00","2024-09-25 18:00","취소","취소","연속"]
[24,"서울","성동","구리신내#1 T/L","신내중계 170kV GIS 증설공사","- 170kV GIS 정밀점검(#2BUS 시험가압)","2024-09-28 15:00","2024-09-28 18:00","취소","취소","연속"]
[25,"서울","성동","신내상봉 T/L","신내중계 170kV GIS 증설공사","- 170kV GIS 정밀점검(#2BUS 시험가압)","2024-09-28 15:00","2024-09-28 18:00","취소","취소","연속"]
[26,"서울","성동","신내상봉 T/L","신내중계 170kV GIS 증설공사","- 170kV GIS 정밀점검(#1BUS 시험가압)","2024-09-25 15:00","2024-09-25 18:00","취소","취소","연속"]
[27,"서울","성동","쌍문미아 T/L","154kV 수유분기(증) 지중T/L 건설공사","○ 구간 : 154kV 수유S/S ~ 쌍문미아 #2T/L 분기점 ○ 선종/회선수 - XLPE 1200㎟, 1회선-0.15km (쌍문-수유) - XLPE 1200㎟, 1회선-0.4km (수유-미아)","2024-09-09 09:00","2024-11-08 18:00","2024-09-09 09:00","2024-11-08 18:00","연속"]
[28,"서울","성동","양주쌍문#1 T/L","2024~25년 성동P/O 변전협력회사 공사","- 170kV GIS 보통점검","2024-09-23 10:00","2024-09-23 18:00","2024-09-23 10:00","2024-09-23 18:00","연속"]
[29,"서울","성동","군자화양#1 T/L","24년 성동P/O 변전협력회사 공사","154kV GIS 조작시험","2024-09-05 14:00","2024-09-05 18:00","2024-09-05 14:00","2024-09-05 18:00","연속"]
[30,"서울","성동","군자화양#2 T/L","24년 성동P/O 변전협력회사 공사","154kV GIS 보통점검","2024-09-11 09:00","2024-09-11 18:00","2024-09-11 09:00","2024-09-11 18:00","연속"]
[31,"서울","성동","미금화양 T/L","24년 성동P/O 변전협력회사 공사","154kV GIS 조작시험","2024-09-05 09:00","2024-09-05 14:00","2024-09-05 09:00","2024-09-05 14:00","연속"]
[32,"서울","중부","당인리S/S SEC CB 60610","2024년 중부전력지사 변전정비 협력회사 총액공사","유압시스템 보수","2024-09-11 10:00","2024-09-11 16:00","2024-09-11 10:00","2024-09-11 16:00","연속"]
[33,"서울","중부","당인리S/S SEC CB 65660","2024년 중부전력지사 변전정비 협력회사 총액공사","PT집합반 대체","2024-09-11 16:00","2024-09-12 16:00","2024-09-11 16:00","2024-09-12 16:00","연속"]
[34,"서울","중부","당인리S/S #66 BUS","2024년 중부전력지사 변전정비 협력회사 총액공사","PT집합반 대체","2024-09-11 16:00","2024-09-12 16:00","2024-09-11 16:00","2024-09-12 16:00","연속"]
[35,"서울","중부","당인리S/S #60 BUS","2024년 중부전력지사 변전정비 협력회사 총액공사","PT집합반 대체","2024-09-12 16:00","2024-09-13 18:00","2024-09-12 16:00","2024-09-13 18:00","연속"]
[36,"서울","중부","당인리S/S #61 BUS","2024년 중부전력지사 변전정비 협력회사 총액공사","PT집합반 대체","2024-09-12 16:00","2024-09-13 18:00","2024-09-12 16:00","2024-09-13 18:00","연속"]
[37,"서울","중부","당인리S/S SEC CB 60610","2024년 중부전력지사 변전정비 협력회사 총액공사","PT집합반 대체","2024-09-12 16:00","2024-09-13 18:00","2024-09-12 16:00","2024-09-13 18:00","연속"]
[38,"서울","중부","당인리S/S #61 BUS","2024년 중부전력지사 변전정비 협력회사 총액공사","PT집합반 대체","2024-09-11 10:00","2024-09-11 16:00","2024-09-11 10:00","2024-09-11 16:00","연속"]
[39,"서울","중부","당인리S/S CB 6100","2024년 중부전력지사 변전정비 협력회사 총액공사","불량개소 보수","2024-09-11 10:00","2024-09-13 18:00","2024-09-11 10:00","2024-09-13 18:00","연속"]
[40,"서울","중부","당인리S/S #60 BUS","2024년 중부전력지사 변전정비 협력회사 총액공사","PT집합반 대체","2024-09-11 10:00","2024-09-11 16:00","2024-09-11 10:00","2024-09-11 16:00","연속"]
[41,"서울","중부","당인리S/S #65 BUS","2024년 중부전력지사 변전정비 협력회사 총액공사","PT집합반 대체","2024-09-11 16:00","2024-09-12 16:00","2024-09-11 16:00","2024-09-12 16:00","연속"]
[42,"서울","중부","수색상암 T/L","2024년 중부전력지사 변전정비 협력회사 총액공사","유압시스템 불량 메인밸브 교체","2024-09-09 10:00","2024-09-10 18:00","2024-09-09 10:00","2024-09-10 18:00","연속"]
[43,"서울","중부","신촌순화 T/L","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검","2024-09-23 10:00","2024-09-24 18:00","취소","취소","연속"]
[44,"서울","중부","순화동빙고 T/L","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검","2024-09-04 10:00","2024-09-04 18:00","2024-09-04 10:00","2024-09-04 18:00","연속"]
[45,"서울","중부","중부신촌 T/L","154kV 신촌S/S 노후차단기 대체공사","154kV 신촌S/S 노후차단기 대체공사(#60BUS 도킹)","2024-09-30 13:00","2024-09-30 18:00","2024-09-30 13:00","2024-09-30 18:00","연속"]
[46,"서울","중부","중부신촌 T/L","154kV 신촌S/S 노후차단기 대체공사","154kV 신촌S/S 노후차단기 대체공사(#65BUS 모선가압)","2024-09-25 13:00","2024-09-25 18:00","2024-09-25 13:00","2024-09-25 18:00","연속"]
[47,"서울","중부","중부아현 T/L","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검","2024-09-10 10:00","2024-09-10 18:00","2024-09-10 10:00","2024-09-10 18:00","연속"]
[48,"서울","중부","중부연대 T/L","중부연대T/L EBG 가스채취밸브 설치","중부연대T/L EBG 가스채취밸브 설치","2024-09-26 09:00","2024-09-27 18:00","2024-09-26 09:00","2024-09-27 18:00","연속"]
[49,"서울","중부","양주은평#2 T/L","2024~2025년 서울본부 가공송전 협력회사 공사","154kV 양주-은평T/L 압축인류클램프 보수","2024-09-19 08:00","2024-09-20 18:00","2024-09-19 08:00","2024-09-20 18:00","연속"]
[50,"서울","중부","양주은평#1 T/L","2024~2025년 서울본부 가공송전 협력회사 공사","154kV 양주-은평T/L 압축인류클램프 보수","2024-09-11 08:00","2024-09-13 18:00","2024-09-11 08:00","2024-09-13 18:00","연속"]
[51,"서울","중부","중부S/S #66 BUS","중부S/S 154kV 장기사용 GIS 교체공사(3차)","- 154kV GIS 교체(#2M.Tr 2차, 중부연대T/L, 중부마포T/L) - 기타 부대공사","2024-09-11 09:00","2024-09-13 18:00","2024-09-11 09:00","2024-09-13 18:00","연속"]
[52,"서울","중부","중부S/S #61 BUS","중부S/S 154kV 장기사용 GIS 교체공사(3차)","- 154kV GIS 교체(#2M.Tr 2차, 중부연대T/L, 중부마포T/L) - 기타 부대공사","2024-09-19 09:00","2024-10-04 09:00","2024-09-19 09:00","2024-10-04 09:00","연속"]
[53,"서울","중부","중부연대 T/L","중부S/S 154kV 장기사용 GIS 교체공사(3차)","- 154kV GIS 교체(#2M.Tr 2차, 중부연대T/L, 중부마포T/L) - 기타 부대공사","2024-09-11 09:00","2024-10-18 18:00","2024-09-11 09:00","2024-10-18 18:00","연속"]
[54,"서울","중부","중부마포 T/L","중부S/S 154kV 장기사용 GIS 교체공사(3차)","- 154kV GIS 교체(#2M.Tr 2차, 중부연대T/L, 중부마포T/L) - 기타 부대공사","2024-09-11 09:00","2024-10-18 18:00","2024-09-11 09:00","2024-10-18 18:00","연속"]
[55,"서울","직할","돈암안암#1 T/L","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사(시험가압선로)","2024-09-11 17:00","2024-09-11 18:00","2024-09-11 17:00","2024-09-11 18:00","연속"]
[56,"서울","직할","돈암안암#2 T/L","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사(시험가압선로)","2024-09-14 17:00","2024-09-14 18:00","2024-09-14 17:00","2024-09-14 18:00","연속"]
[57,"서울","직할","돈암안암#1 T/L","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사","2024-09-02 09:00","2024-09-04 18:00","2024-09-23 09:00","2024-09-25 14:00","연속"]
[58,"서울","직할","돈암안암#2 T/L","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사","2024-09-04 14:00","2024-09-06 18:00","2024-09-25 14:00","2024-09-27 18:00","연속"]
[59,"서울","직할","돈암안암#1 T/L","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사(시험가압선로)","2024-09-10 17:00","2024-09-10 18:00","2024-09-10 17:00","2024-09-10 18:00","연속"]
[60,"서울","직할","성동마장#3 T/L","24년 서울본부 직할 154kV GIS 정밀점검 공사","154kV GIS 정밀점검 공사","2024-09-25 14:00","2024-09-27 18:00","2024-09-25 14:00","2024-09-27 18:00","연속"]
[61,"서울","직할","마장용두 T/L","24년 서울본부 직할 154kV GIS 정밀점검 공사","154kV GIS 정밀점검 공사","2024-09-23 09:00","2024-09-25 14:00","취소","취소","연속"]
[62,"서울","직할","서대문세종로 T/L","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사","2024-09-30 09:00","2024-10-02 18:00","2024-09-30 09:00","2024-10-02 18:00","연속"]
[63,"서울","직할","용두S/S #2 BUS","용두S/S 154kV #3M.Tr 증설공사","용두S/S 154kV #3M.Tr 1차 GIS 설치 관련 #2BUS 휴전(도킹)","2024-09-23 09:00","2024-09-27 18:00","2024-09-23 09:00","2024-09-27 18:00","연속"]
[64,"서울","직할","용두안암#1 T/L","용두S/S 154kV #3M.Tr 증설공사","용두S/S 154kV #3M.Tr 1차 GIS 설치 관련 모선도킹시 인접BAY 감압 및 무부하가압 시험가압선로(#1BUS 도킹)","2024-09-30 09:00","2024-10-04 18:00","2024-09-30 09:00","2024-10-04 18:00","연속"]
[65,"서울","직할","용두안암#1 T/L","용두S/S 154kV #3M.Tr 증설공사","용두S/S 154kV #3M.Tr 1차 GIS 설치 관련 모선도킹시 인접BAY 감압 및 무부하가압 시험가압선로","2024-09-23 09:00","2024-09-27 18:00","2024-09-23 09:00","2024-09-27 18:00","연속"]
[66,"서울","직할","용두S/S #1 BUS","용두S/S 154kV #3M.Tr 증설공사","용두S/S 154kV #3M.Tr 1차 GIS 설치 관련 #1BUS 휴전(도킹)","2024-09-30 09:00","2024-10-04 18:00","2024-09-30 09:00","2024-10-04 18:00","연속"]
[67,"서울","직할","중앙서소문 T/L","중앙서소문 T/L EBG 가스채취밸브 설치","중앙서소문 T/L EBG 가스채취밸브 설치","2024-09-02 09:00","2024-09-04 18:00","2024-09-02 09:00","2024-09-04 18:00","연속"]
[68,"남서울","강남","반포S/S CB 6100","24-25년도 강남전력지사 변전협력회사 총액공사","반포S/S BUS TIE 조작시험","2024-09-02 10:00","2024-09-02 18:00","2024-09-02 10:00","2024-09-02 18:00","연속"]
[69,"남서울","강남","사당봉천#1 T/L","24-25년도 강남전력지사 변전협력회사 총액공사","사당S/S 사당-봉천#1T/L 조작시험","2024-09-12 09:00","2024-09-12 14:00","2024-09-12 09:00","2024-09-12 14:00","연속"]
[70,"남서울","강남","사당봉천#2 T/L","24-25년도 강남전력지사 변전협력회사 총액공사","사당S/S 사당-봉천#2T/L 조작시험","2024-09-12 14:00","2024-09-12 18:00","2024-09-12 14:00","2024-09-12 18:00","연속"]
[71,"남서울","강남","신양재역삼#1 T/L","24-25년도 강남전력지사 변전협력회사 총액공사","신양재S/S 신양재-역삼#1T/L 조작시험","2024-09-07 09:00","2024-09-07 12:00","2024-09-07 09:00","2024-09-07 12:00","연속"]
[72,"남서울","강남","신양재역삼#2 T/L","24-25년도 강남전력지사 변전협력회사 총액공사","신양재S/S 신양재-역삼#2T/L 조작시험","2024-09-07 12:00","2024-09-07 15:00","2024-09-07 12:00","2024-09-07 15:00","연속"]
[73,"남서울","강남","신양재역삼#3 T/L","24-25년도 강남전력지사 변전협력회사 총액공사","신양재S/S 신양재-역삼#3T/L 조작시험","2024-09-07 15:00","2024-09-07 18:00","2024-09-07 15:00","2024-09-07 18:00","연속"]
[74,"남서울","동서울","강일상일#2 T/L","154kV 강일S/S GIS 및 EGIS 설치공사","- 154kV 강일-상일#2T/L 도체 점검(상부모선~챔버 접속부) - 부대작업 1식","2024-09-09 09:00","2024-09-11 18:00","2024-09-09 09:00","2024-09-11 18:00","연속"]
[75,"남서울","동서울","풍납석촌#1 T/L","'24~25년도 동서울전력지사 변전협력회사 총액공사","석촌S/S 154kV 송파-석촌#1T/L GIS정밀점검 무부하가압용","2024-09-10 09:00","2024-09-10 14:00","2024-09-10 09:00","2024-09-10 14:00","연속"]
[76,"남서울","동서울","풍납석촌#1 T/L","'24~25년도 동서울전력지사 변전협력회사 총액공사","석촌S/S 154kV 풍납-석촌#1T/L GIS 정밀점검","2024-09-30 09:00","2024-10-04 18:00","2024-09-30 09:00","2024-10-04 18:00","연속"]
[77,"남서울","동서울","풍납석촌#2 T/L","'24~25년도 동서울전력지사 변전협력회사 총액공사","석촌S/S 154kV 송파-석촌#2T/L GIS정밀점검 무부하가압용","2024-09-24 09:00","2024-09-24 14:00","2024-09-24 09:00","2024-09-24 14:00","연속"]
[78,"남서울","동서울","산성수서#2 T/L","'24~25년도 동서울전력지사 변전협력회사 총액공사","수서S/S 산성-수서 #2T/L GIS 조작시험","2024-09-23 09:00","2024-09-23 18:00","2024-09-23 09:00","2024-09-23 18:00","연속"]
[79,"남서울","동서울","위례S/S SEC CB 60610","'24~25년도 동서울전력지사 변전협력회사 총액공사","위례S/S 60-61 BUS-SEC GIS 보통점검","2024-09-09 09:00","2024-09-09 18:00","2024-09-09 09:00","2024-09-09 18:00","연속"]
[80,"남서울","동서울","위례S/S SEC CB 65660","'24~25년도 동서울전력지사 변전협력회사 총액공사","위례S/S 65-66 BUS-SEC GIS 보통점검","2024-09-10 09:00","2024-09-10 18:00","2024-09-10 09:00","2024-09-10 18:00","연속"]
[81,"남서울","동서울","위례S/S CB 6200","'24~25년도 동서울전력지사 변전협력회사 총액공사","위례S/S #2 BUS-TIE GIS 보통점검","2024-09-12 09:00","2024-09-12 18:00","2024-09-12 09:00","2024-09-12 18:00","연속"]
[82,"남서울","동서울","위례S/S CB 6100","'24~25년도 동서울전력지사 변전협력회사 총액공사","위례S/S #1BUS-TIE GIS 보통점검","2024-09-11 09:00","2024-09-11 18:00","2024-09-11 09:00","2024-09-11 18:00","연속"]
[83,"남서울","동서울","잠실S/S #2 BUS","잠실S/S 장기사용 23kV GIS 교체공사","LID이설","2024-09-03 08:00","2024-09-03 18:00","2024-09-09 8:00","2024-09-09 18:00","연속"]
[84,"남서울","동서울","송파잠실#3 T/L","잠실S/S 장기사용 23kV GIS 교체공사","LID이설","2024-09-23 08:00","2024-09-23 18:00","2024-09-23 08:00","2024-09-23 18:00","연속"]
[85,"남서울","동서울","잠실탄천#1 T/L","잠실S/S 장기사용 23kV GIS 교체공사","LID 이설","2024-09-07 08:00","2024-09-07 18:00","2024-09-07 08:00","2024-09-07 18:00","연속"]
[86,"남서울","동서울","잠실탄천#2 T/L","잠실S/S 장기사용 23kV GIS 교체공사","LID이설","2024-09-08 08:00","2024-09-08 18:00","2024-09-08 08:00","2024-09-08 18:00","연속"]
[87,"남서울","동서울","잠실S/S #1 BUS","잠실S/S 장기사용 23kV GIS 교체공사","LID이설","2024-09-02 08:00","2024-09-02 18:00","2024-09-10 8:00","2024-09-10 18:00","연속"]
[88,"남서울","동서울","송파잠실#2 T/L","잠실S/S 장기사용 23kV GIS 교체공사","LID이설","2024-09-05 14:00","2024-09-06 18:00","2024-09-05 14:00","2024-09-06 18:00","연속"]
[89,"남서울","동서울","송파잠실#1 T/L","잠실S/S 장기사용 23kV GIS 교체공사","LID이설","2024-09-04 08:00","2024-09-05 14:00","2024-09-04 08:00","2024-09-05 14:00","연속"]
[90,"남서울","동서울","송파잠실#4 T/L","잠실S/S 장기사용 23kV GIS 교체공사","LID이설","2024-09-24 08:00","2024-09-24 18:00","2024-09-24 08:00","2024-09-24 18:00","연속"]
[91,"남서울","영등포","신광명광명#1 T/L","154kV 신광명-광명#1,2T/L OF케이블 유압 원격감시 연계공사","154kV 신광명-광명#1,2T/L OF케이블 유압 원격감시 운영시스템 연계","2024-09-11 09:00","2024-09-11 18:00","2024-09-11 09:00","2024-09-11 18:00","연속"]
[92,"남서울","영등포","신광명광명#2 T/L","154kV 신광명-광명#1,2T/L OF케이블 유압 원격감시 연계공사","154kV 신광명-광명#1,2T/L OF케이블 유압 원격감시 운영시스템 연계","2024-09-12 09:00","2024-09-12 18:00","2024-09-12 09:00","2024-09-12 18:00","연속"]
[93,"남서울","영등포","구공S/S CB 6300","구공S/S 154kV 장기사용 GIS 교체공사","61-62, 66-67B/S, (신)6200 B/T GIS 설치완료에 따른 62-67 모선보호반 설치공사","2024-09-02 09:00","2024-09-06 18:00","2024-09-02 09:00","2024-09-06 18:00","연속"]
[94,"남서울","영등포","구공S/S SEC CB 65660","구공S/S 154kV 장기사용 GIS 교체공사","61-62, 66-67B/S, (신)6200 B/T GIS 설치 완료에 따른 62-67 모선보호반 설치공사","2024-09-02 09:00","2024-09-06 18:00","2024-09-02 09:00","2024-09-06 18:00","연속"]
[95,"남서울","영등포","구공독산 T/L","구공S/S 154kV 장기사용 GIS 교체공사","구공-독산T/L GIS 철거 및 신품 설치","2024-09-24 09:00","2024-10-24 18:00","2024-09-24 09:00","2024-10-24 18:00","연속"]
[96,"남서울","영등포","구공S/S #61 BUS","구공S/S 154kV 장기사용 GIS 교체공사","구공-독산T/L GIS 철거 및 신품 설치","2024-09-30 09:00","2024-10-11 18:00","2024-09-30 09:00","2024-10-11 18:00","연속"]
[97,"남서울","영등포","구공S/S SEC CB 60610","구공S/S 154kV 장기사용 GIS 교체공사","61-62, 66-67B/S, (신)6200 B/T GIS 설치 완료에 따른 62-67 모선보호반 설치공사","2024-09-02 09:00","2024-09-06 18:00","2024-09-02 09:00","2024-09-06 18:00","연속"]
[98,"남서울","영등포","신광명구공#1 T/L","2024~2025년 영등포전력지사 변전협력회사 총액공사","2024~2025년 영등포전력지사 변전협력회사 총액공사 공사내용 : 154kV 신광명-구공#1T/L GIS 보통점검","2024-09-09 09:00","2024-09-09 18:00","2024-09-09 09:00","2024-09-09 18:00","연속"]
[99,"남서울","영등포","신광명구공#2 T/L","2024~2025년 영등포전력지사 변전협력회사 총액공사","2024~2025년 영등포전력지사 변전협력회사 총액공사 공사내용 : 154kV 신광명-구공#2T/L GIS 보통점검","2024-09-10 09:00","2024-09-10 18:00","2024-09-10 09:00","2024-09-10 18:00","연속"]
[100,"남서울","영등포","신광명소래 T/L","효성제 170kV GIS 메커니즘 점검","효성제 170kV GIS 메커니즘 점검","2024-09-07 10:00","2024-09-07 18:00","2024-09-07 09:00","2024-09-07 18:00","연속"]
[101,"남서울","영등포","온수소래 T/L","2024~25년 영등포전력지사 변전협력회사 총액공사","온수SS 온수-소래T/L 조작시험","2024-09-07 09:00","2024-09-07 10:00","취소","취소","연속"]
[102,"남서울","영등포","천왕오류#2 T/L","2024~2025년 영등포전력지사 변전협력회사 총액공사","2024~2025년 영등포전력지사 변전협력회사 총액공사 공사내용 : 천왕-오류#2T/L 보호배전반 대체","2024-09-04 14:00","2024-09-06 18:00","취소","취소","연속"]
[103,"남서울","영등포","천왕오류#1 T/L","2024~2025년 영등포전력지사 변전협력회사 총액공사","2024~2025년 영등포전력지사 변전협력회사 총액공사 공사내용 : 천왕-오류#1T/L 보호배전반 대체","2024-09-02 09:00","2024-09-04 14:00","취소","취소","연속"]
[104,"남서울","영등포","중동화곡#1 T/L","2024~25년 영등포전력지사 변전협력회사 총액공사","화곡SS 중동-화곡#1T/L 조작시험","2024-09-28 09:00","2024-09-28 10:00","2024-09-28 09:00","2024-09-28 10:00","연속"]
[105,"남서울","영등포","중동화곡#2 T/L","2024~25년 영등포전력지사 변전협력회사 총액공사","화곡SS 중동-화곡#2T/L 조작시험","2024-09-28 10:00","2024-09-28 11:00","2024-09-28 10:00","2024-09-28 11:00","연속"]
[106,"남서울","직할","신문래양평#1 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2024-09-30 09:00","2024-09-30 14:00","2024-09-30 09:00","2024-09-30 14:00","연속"]
[107,"남서울","직할","신문래양평#2 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2024-09-30 14:00","2024-09-30 18:00","2024-09-30 14:00","2024-09-30 18:00","연속"]
[108,"인천","김포","경서양촌#2 T/L","검암플라시아 지장송전선로 지중화공사","○ XLPE 1,200㎟ 1.64 C-km ○ 케이블 포설 4구간, 케이블 접속 6개소","2024-09-02 09:00","2024-09-29 18:00","2024-09-02 09:00","2024-09-29 18:00","연속"]
[109,"인천","김포","신경서경서#2 T/L","경서S/S 154kV 신경서-경서#2T/L GIS 조작시험","경서S/S 154kV 신경서-경서#2T/L GIS 조작시험","2024-09-10 10:00","2024-09-10 18:00","2024-09-10 10:00","2024-09-10 18:00","연속"]
[110,"인천","김포","김포장기#2 T/L","김포S/S 154kV 김포-장기#2T/L GIS 보통점검","김포S/S 154kV 김포-장기#2T/L GIS 보통점검","2024-09-11 10:00","2024-09-11 18:00","취소","취소","연속"]
[111,"인천","김포","김포장기#1 T/L","김포S/S 154kV 김포-장기#1T/L GIS 보통점검","김포S/S 154kV 김포-장기#1T/L GIS 보통점검","2024-09-10 10:00","2024-09-10 18:00","취소","취소","연속"]
[112,"인천","김포","신김포양곡#1 T/L","양곡S/S 154kV 신김포-양곡#1T/L GIS SA 혼용화공사","(병행) 양곡S/S 154kV 신김포-양곡#1T/L GIS 보통점검 신김포S/S 154kV 신김포-양곡#1T/L GIS 보통점검","2024-09-28 09:00","2024-09-28 18:00","취소","취소","연속"]
[113,"인천","김포","양곡S/S CB 6100","양곡S/S 154kV 6100 BUS TIE GIS SA 혼용화공사","양곡S/S 154kV #1-#2 BUS TIE GIS(6100) SA 혼용화공사 (병행) GIS 보통점검","2024-09-21 09:00","2024-09-21 18:00","2024-09-21 09:00","2024-09-21 18:00","연속"]
[114,"인천","김포","양촌양곡#1 T/L","양곡S/S 154kV 양촌-양곡#1T/L 보호배전반 대체","양곡S/S 154kV 양촌-양곡#1T/L GIS 보호배전반 대체 (병행) 양촌S/S 154kV 양촌-양곡#1T/L 보호배전반 대체 양촌S/S 154kV 양촌-양곡#1T/L GIS 보통점검 양곡S/S 154kV 양촌-양곡#1T/L GIS SA 혼용화 공사","2024-09-30 09:00","2024-10-03 18:00","취소","취소","연속"]
[115,"인천","부평","관교만수#1 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2024-09-02 09:00","2024-09-02 18:00","취소","취소","연속"]
[116,"인천","부평","관교만수#2 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2024-09-03 09:00","2024-09-03 18:00","취소","취소","연속"]
[117,"인천","부평","남인천학익#2 T/L","남인천S/S 154kV 남인천학익#2 T/L SA 혼용화 공사","남인천S/S 154kV 남인천학익#2 T/L SA 혼용화 공사","2024-09-09 09:00","2024-09-09 18:00","취소","취소","연속"]
[118,"인천","부평","남인천S/S CB 6100","남인천S/S 154kV #1-#2 BUS TIE GIS 혼용화 공사","남인천S/S 154kV #1-#2 BUS TIE GIS 혼용화","2024-09-03 09:00","2024-09-03 18:00","2024-09-03 09:00","2024-09-03 18:00","연속"]
[119,"인천","부평","인천남인천#2 T/L","남인천S/S 인천남인천#2 T/L SA 혼용화","남인천S/S인천남인천#2 T/L SA 혼용화","2024-09-07 09:00","2024-09-07 18:00","2024-09-07 09:00","2024-09-07 18:00","연속"]
[120,"인천","부평","인천남인천#1 T/L","남인천S/S 인천남인천#1 T/L SA 혼용화","남인천S/S인천남인천#1 T/L SA 혼용화","2024-09-08 09:00","2024-09-08 18:00","2024-09-08 09:00","2024-09-08 18:00","연속"]
[121,"인천","부평","남인천학익#2 T/L","154kV 남인천-학익 등 2개T/L 지장이설 및 선종교체","ㅇ 케이블 선종교체 및 일부 개소 지장이설 ㅇ 선종 및 회선길이 : OF 2,000㎟→XLPE 2,000㎟ × 2C(13.7C-km)","2024-09-09 09:00","2024-10-20 18:00","2024-09-09 09:00","2024-10-20 18:00","연속"]
[122,"인천","부평","서인천CC신경서 T/L","154kV 서인천CC-신경서T/L 보호반 교체","154kV 서인천CC-신경서T/L 보호반 교체","2024-09-02 09:00","2024-09-06 18:00","취소","취소","연속"]
[123,"인천","부평","송현포스코CC#2 T/L","154kV 주안-관교 등 4개T/L EBG 가스채취밸브 설치공사","EBG 가스채취밸브 설치 및 스프링 유니트 점검 시행","2024-09-19 09:00","2024-09-21 18:00","취소","취소","연속"]
[124,"인천","부평","신가좌부개#1 T/L","23~24년 지중송전 위탁정비공사","절연유 채취","2024-09-09 09:00","2024-09-11 18:00","2024-09-09 09:00","2024-09-11 18:00","연속"]
[125,"인천","부평","신가좌신현#2 T/L","154kV 남동-관교 등 4개 T/L 노후 피뢰기 교체공사","피뢰기 교체공사(3상)","2024-09-04 09:00","2024-09-04 18:00","취소","취소","연속"]
[126,"인천","부평","신가좌신현#1 T/L","154kV 남동-관교 등 4개 T/L 노후 피뢰기 교체공사","피뢰기 교체공사(3상)","2024-09-03 09:00","2024-09-03 18:00","취소","취소","연속"]
[127,"인천","부평","신가좌인천#1 T/L","신가좌S/S 154kV 신가좌인천#1T/L GIS 정밀점검","신가좌S/S 154kV 신가좌인천#1T/L GIS 정밀점검","2024-09-30 09:00","2024-10-02 18:00","취소","취소","연속"]
[128,"인천","부평","신가좌S/S SEC CB 65660","신가좌S/S 154kV #65-#66 SEC 보통점검","신가좌S/S 154kV #65-#66 SEC 보통점검","2024-09-19 09:00","2024-09-19 18:00","취소","취소","연속"]
[129,"인천","부평","신가좌S/S SEC CB 66670","신가좌S/S 154kV #66-#67 SEC GIS 보통점검","신가좌S/S 154kV #66-#67 SEC GIS 보통점검","2024-09-13 09:00","2024-09-13 18:00","취소","취소","연속"]
[130,"인천","부평","신가좌부개#2 T/L","23~24년 지중송전 위탁정비공사","절연유 채취","2024-09-12 09:00","2024-09-13 18:00","2024-09-12 09:00","2024-09-13 18:00","연속"]
[131,"인천","부평","신경서S/S SEC CB 60610","신경서S/S 154kV #60-#61 SEC GIS 정밀점검","신경서S/S 154kV #60-#61 SEC GIS 정밀점검","2024-09-02 09:00","2024-09-04 18:00","취소","취소","연속"]
[132,"인천","부평","신경서S/S #60 BUS","신경서S/S #60-#61 SEC GIS 정밀점검 관련 무부하가압","신경서S/S 154kV #60-#61 SEC GIS 정밀점검 관련 무부하가압","2024-09-04 09:00","2024-09-04 18:00","취소","취소","연속"]
[133,"인천","부평","신경서경서#3 T/L","신경서S/S #60-#65 TIE GIS 정밀점검 관련 무부하가압","신경서S/S 154kV #60-#65 TIE GIS 정밀점검 관련 무부하가압","2024-09-25 09:00","2024-09-25 18:00","2024-09-25 09:00","2024-09-25 18:00","연속"]
[134,"인천","부평","신경서S/S #60 BUS","신경서S/S #60-#65 TIE GIS 정밀점검 관련 무부하가압","신경서S/S 154kV #60-#65 TIE GIS 정밀점검 관련 무부하가압","2024-09-25 09:00","2024-09-25 18:00","2024-09-25 09:00","2024-09-25 18:00","연속"]
[135,"인천","부평","신경서경서#3 T/L","신경서S/S #60-#61 SEC GIS 정밀점검 관련 무부하가압","신경서S/S 154kV #60-#61 SEC GIS 정밀점검 관련 무부하가압","2024-09-04 09:00","2024-09-04 18:00","취소","취소","연속"]
[136,"인천","부평","신경서S/S CB 6100","신경서S/S 154kV #60-#65 TIE GIS 정밀점검","신경서S/S 154kV #65-#66 TIE GIS 정밀점검","2024-09-23 09:00","2024-09-25 18:00","2024-09-23 09:00","2024-09-25 18:00","연속"]
[137,"인천","부평","신경서경서#3 T/L","신경서S/S #65-#66 SEC GIS 정밀점검 관련 무부하가압","신경서S/S 154kV #65-#66 SEC GIS 정밀점검 관련 무부하가압","2024-09-11 09:00","2024-09-11 18:00","2024-09-11 09:00","2024-09-11 18:00","연속"]
[138,"인천","부평","신경서S/S #65 BUS","신경서S/S #65-#66 SEC GIS 정밀점검 관련 무부하가압","신경서S/S 154kV #65-#66 SEC GIS 정밀점검 관련 무부하가압","2024-09-11 09:00","2024-09-11 18:00","2024-09-11 09:00","2024-09-11 18:00","연속"]
[139,"인천","부평","신경서S/S SEC CB 65660","신경서S/S 154kV #65-#66 SEC GIS 정밀점검","신경서S/S 154kV #65-#66 SEC GIS 정밀점검","2024-09-19 09:00","2024-09-21 18:00","2024-09-19 09:00","2024-09-21 18:00","연속"]
[140,"인천","부평","신현송현#1 T/L","신현S/S 154kV 신현송현#1 T/L GIS 보통점검","신현S/S 154kV 신현송현#1 T/L GIS 보통점검","2024-09-21 09:00","2024-09-21 18:00","2024-09-21 09:00","2024-09-21 18:00","연속"]
[141,"인천","부평","신가좌주안#1 T/L","24-25년 부평,김포전력지사 가공송전 협력회사 공사","수평추락, 고정형폴리머, 피뢰기 설치","2024-09-08 07:30","2024-09-08 18:00","취소","취소","연속"]
[142,"인천","부평","신가좌주안#2 T/L","24-25년 부평,김포전력지사 가공송전 협력회사 공사","수평추락 설치","2024-09-07 07:30","2024-09-07 18:00","취소","취소","연속"]
[143,"인천","부평","주안만수#1 T/L","주안S/S 주안만수#1T/L GIS 보통점검","주안S/S 주안만수#1T/L GIS 보통점검","2024-09-27 09:00","2024-09-27 18:00","취소","취소","연속"]
[144,"인천","부평","관교주안 T/L","주안S/S 주안관교 T/L GIS 모자익배선 철거 공사","주안S/S 주안관교 T/L GIS 모자익배선 철거 공사","2024-09-23 09:00","2024-09-23 18:00","취소","취소","연속"]
[145,"인천","부평","주안S/S CB 6100","주안S/S 154kV #1-#2 BUS TIE GIS 모자익 배선 철거","주안S/S 154kV #1-#2 BUS TIE GIS 모자익 배선 철거 및 보통점검","2024-09-19 09:00","2024-09-19 18:00","취소","취소","연속"]
[146,"인천","시흥","오봉고잔#1 T/L","고잔S/S 154kV 오봉고잔#1T/L GIS 정밀점검","고잔S/S 154kV 오봉고잔#1T/L GIS CB 정밀점검","2024-09-23 08:00","2024-09-24 18:00","취소","취소","연속"]
[147,"인천","시흥","오봉고잔#2 T/L","고잔S/S 154kV 오봉고잔#2T/L GIS 정밀점검","고잔S/S 154kV 오봉고잔#2T/L GIS CB 정밀점검","2024-09-25 08:00","2024-09-26 18:00","취소","취소","연속"]
[148,"인천","시흥","오봉남동#1 T/L","대한전선제 EBG 가스채취밸브 보강공사","대한전선제 EBG 가스채취밸브 보강공사","2024-09-02 08:00","2024-09-04 18:00","취소","취소","연속"]
[149,"인천","시흥","오봉남동#2 T/L","대한전선제 EBG 가스채취밸브 보강공사","대한전선제 EBG 가스채취밸브 보강공사","2024-09-05 08:00","2024-09-06 18:00","취소","취소","연속"]
[150,"인천","시흥","남동동춘 T/L","남동S/S 154kV 남동동춘T/L GIS 조작시험","남동S/S 154kV 남동동춘T/L GIS 조작시험 - 세니온제 보호IED 성능개선 병행","2024-09-20 09:00","2024-09-20 18:00","취소","취소","연속"]
[151,"인천","시흥","신시화남정왕#1 T/L","154kV 남정왕S/S #3M.Tr용 GIS 설치공사","154kV 남정왕S/S #3M.Tr 1차 GIS 설치 및 무부하가압","2024-09-28 09:00","2024-10-06 18:00","2024-09-28 09:00","2024-10-06 18:00","연속"]
[152,"인천","시흥","남시화남정왕#1 T/L","남정왕 154kV 남시화남정왕#1T/L 세니온제 제어IED 성능개선","남정왕 154kV 남시화남정왕#1T/L 세니온제 제어IED 성능개선 - 세니온제 보호IED 성능개선 병행","2024-09-19 09:00","2024-09-19 18:00","취소","취소","연속"]
[153,"인천","시흥","도림오봉#1 T/L","케이블타워 피뢰기교체공사 및 EBA 절연유 채취","- C/T 피뢰기교체 및 EBA 절연유 채취","2024-09-09 08:00","2024-09-10 18:00","취소","취소","연속"]
[154,"인천","시흥","도림오봉#2 T/L","케이블타워 피뢰기교체공사 및 EBA 절연유 채취","- C/T 피뢰기교체 및 EBA 절연유 채취","2024-09-11 08:00","2024-09-12 18:00","취소","취소","연속"]
[155,"인천","시흥","서서울#2소래 T/L","케이블타워 피뢰기 교체공사","154kV 서서울2소래T/L 피뢰기 교체공사(소래C/T)","2024-09-23 08:00","2024-09-24 18:00","취소","취소","연속"]
[156,"인천","시흥","서안양소래 T/L","케이블타워 피뢰기 교체공사","154kV 서안양소래T/L 피뢰기 교체공사(소래C/T)","2024-09-28 08:00","2024-09-29 18:00","2024-09-28 08:00","2024-09-29 18:00","연속"]
[157,"인천","시흥","신시화S/S #66 BUS","345kV 신시화S/S 170kV GIS 회로 수정공사","인터록 케이블 추가 포설 및 결선","2024-09-11 14:00","2024-09-11 18:00","2024-09-11 14:00","2024-09-11 18:00","연속"]
[158,"인천","시흥","신시화S/S #61 BUS","345kV 신시화S/S 170kV GIS 회로 수정공사","인터록 케이블 추가 포설 및 결선","2024-09-10 09:00","2024-09-10 14:00","2024-09-10 09:00","2024-09-10 14:00","연속"]
[159,"인천","시흥","신시화S/S #60 BUS","345kV 신시화S/S 170kV GIS 회로 수정공사","인터록 케이블 추가 포설 및 결선","2024-09-10 14:00","2024-09-10 18:00","2024-09-10 14:00","2024-09-10 18:00","연속"]
[160,"인천","시흥","신시화S/S #65 BUS","345kV 신시화S/S 170kV GIS 회로 수정공사","인터록 케이블 추가 포설 및 결선","2024-09-11 09:00","2024-09-11 14:00","2024-09-11 09:00","2024-09-11 14:00","연속"]
[161,"인천","시흥","신시흥남동#1 T/L","신시흥S/S 154kV 신시흥남동#1T/L GIS 베어링 교체","신시흥S/S 154kV 신시흥남동#1T/L GIS 베어링 부품 교체","2024-09-25 09:00","2024-09-25 18:00","취소","취소","연속"]
[162,"인천","시흥","신시흥시화#1 T/L","2024년 가공송전 순시점검 위탁공사(시흥전력)","애자오염진단시스템 설치","2024-09-10 09:00","2024-09-10 18:00","2024-09-10 09:00","2024-09-10 18:00","연속"]
[163,"인천","직할","임학계양#2 T/L","170kV 계양임학#2T/L GIS 보통점검(양단)","170kV 계양임학#2T/L GIS 보통점검(양단) - (계양) 보통점검 / (임학) 하자점검","2024-09-25 09:00","2024-09-25 18:00","2024-09-25 09:00","2024-09-25 18:00","연속"]
[164,"인천","직할","부천신정#2 T/L","부천S/S 170kV 부천신정#2T/L GIS 보통점검","부천S/S 170kV 부천신정#2T/L GIS 보통점검","2024-09-28 09:30","2024-09-28 18:00","2024-09-28 09:30","2024-09-28 18:00","연속"]
[165,"인천","직할","부흥부개#2 T/L","154kV 부흥-원미T/L SW 증설공사","154kV 부흥-원미T/L SW 증설공사 관련 170kV GIS 설치 및 무부하가압","2024-09-25 09:00","2024-09-26 18:00","2024-09-25 09:00","2024-09-26 18:00","연속"]
[166,"인천","직할","부흥부개#2 T/L","154kV 부흥-원미T/L SW 증설공사","154kV 부흥-원미T/L SW 증설공사 관련 170kV GIS 설치 및 무부하가압","2024-09-30 09:00","2024-10-01 18:00","2024-09-30 09:00","2024-10-01 18:00","연속"]
[167,"인천","직할","북인천원창 T/L","북인천S/S 170kV 북인천원창T/L GIS 정밀점검","북인천S/S 170kV 북인천원창T/L GIS 정밀점검","2024-09-26 09:00","2024-09-28 18:00","2024-09-26 09:00","2024-09-28 18:00","연속"]
[168,"인천","직할","계양북인천 T/L","북인천S/S 170kV 계양북인천T/L GIS 정밀점검","북인천S/S 170kV 계양북인천T/L GIS 정밀점검","2024-09-23 09:00","2024-09-25 18:00","취소","취소","연속"]
[169,"인천","직할","신부평고강#1 T/L","23~24년 지중송전 위탁정비공사","피뢰기 및 c/t점검, 절연유 채취","2024-09-14 09:00","2024-09-16 18:00","취소","취소","연속"]
[170,"인천","직할","신부평중동#1 T/L","170kV 신부평중동#1T/L 보호반대체(양단)","170kV 신부평중동#1T/L 보호반대체(양단) - (중동) GIS 단로기 회로보호차단기(CP) 설치 병행","2024-09-09 09:30","2024-09-11 18:00","2024-09-09 09:30","2024-09-11 18:00","연속"]
[171,"인천","직할","신부평중동#3 T/L","170kV 신부평중동#3T/L GIS 단로기 CP 설치","170kV 신부평중동#3T/L GIS 단로기 회로보호차단기(CP) 설치","2024-09-12 09:30","2024-09-12 18:00","2024-09-12 09:30","2024-09-12 18:00","연속"]
[172,"인천","직할","신부평고강#2 T/L","170kV 신부평고강#2T/L 보호반대체 및 GIS 보통점검(양단)","170kV 신부평고강#2T/L 보호반대체 및 GIS 보통점검(양단)","2024-09-07 09:00","2024-09-08 18:00","취소","취소","연속"]
[173,"인천","시흥","신시화남정왕#1 T/L","154kV 남정왕S/S #3M.Tr용 GIS 설치공사","154kV 남정왕S/S #3M.Tr 1차 GIS 설치 및 무부하가압","2024-09-28 09:00","2024-10-06 18:00","취소","취소","연속"]
[201,"경기북부","구리","신포천덕계#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지시설 설치 - 대상 : 154kV 신포천-덕계#1T/L No.65~70","2024-09-02 07:00","2024-09-02 18:00","취소","취소","연속"]
[224,"경기북부","직할","백석덕계#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지시설 설치 - 대상 : 154kV 백석-덕계#1T/L No.22~28","2024-09-02 07:00","2024-09-02 18:00","취소","취소","연속"]
[180,"경기북부","고양","덕이호수#1 T/L","덕이S/S 디지털화공사","덕이S/S 디지털화공사","2024-09-02 09:00","2024-09-02 18:00","2024-09-09 09:00","2024-09-09 18:00","연속"]
[200,"경기북부","구리","신포천전곡#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-09-02 09:00","2024-09-02 18:00","2024-09-02 09:00","2024-09-02 18:00","연속"]
[207,"경기북부","구리","곤지암용문#1 T/L","용문S/S 154kV 장기사용 GIS 교체공사(1차분)","□ 용문S/S 154kV 장기사용 GIS 교체공사(1차분) ○ 1차분 교체개소 : #2M.Tr 1차, 곤지암-용문#1T/L, BUS-TIE, PT&ES ○ 모선 휴전순서 : #60 → #65 → #60 → #65BUS ○ 휴전사유 : #1BUS, 1DS, CB부 철거 및 #1BUS 신규 GIS 설치","2024-09-02 09:00","2024-10-18 18:00","2024-09-19 09:00","2024-10-24 18:00","연속"]
[208,"경기북부","구리","용문S/S CB 6100","용문S/S 154kV 장기사용 GIS 교체공사(1차분)","□ 용문S/S 154kV 장기사용 GIS 교체공사(1차분) ○ 1차분 교체개소 : #2M.Tr 1차, 곤지암-용문#1T/L, BUS-TIE, PT&ES ○ 모선 휴전순서 : #60 → #65 → #60 → #65BUS ○ 휴전사유 : #1BUS, 1DS, CB부 철거 및 #1BUS 신규 GIS 설치","2024-09-02 09:00","2024-10-18 18:00","2024-09-19 09:00","2024-10-24 18:00","연속"]
[209,"경기북부","구리","용문S/S #1 BUS","용문S/S 154kV 장기사용 GIS 교체공사(1차분)","□ 용문S/S 154kV 장기사용 GIS 교체공사(1차분) ○ 1차분 교체개소 : #2M.Tr 1차, 곤지암-용문#1T/L, BUS-TIE, PT&ES ○ 모선 휴전순서 : #60 → #65 → #60 → #65BUS ○ 휴전사유 : #1BUS, 1DS, CB부 철거 및 #1BUS 신규 GIS 설치","2024-09-02 09:00","2024-09-13 18:00","2024-09-19 09:00","2024-09-27 18:00","연속"]
[222,"경기북부","직할","신포천동두천#2 T/L","24-25년 직할 변전 협력회사 총액공사","노후 배전반 대체","2024-09-02 09:00","2024-09-06 18:00","2024-09-02 09:00","2024-09-06 18:00","연속"]
[230,"경기북부","직할","옥정송우#1 T/L","경기북부 직할 및 양주전력TF 362, 170kV GIS 보통점검 공사","옥정SS 옥정-송우#1T/L GIS 보통점검","2024-09-02 09:00","2024-09-02 18:00","2024-09-11 09:00","2024-09-11 18:00","연속"]
[234,"경기북부","직할","신의정부용현#1 T/L","(주)영인 보호계전기 성능개선 시행","유사 불량사례 발생 가능성 사전 제거를 위한 성능개선","2024-09-02 09:00","2024-09-02 18:00","취소","취소","연속"]
[182,"경기북부","고양","백학남면#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지시설 설치 - 대상 : 154kV 백학-남면#2T/L No.2~35","2024-09-03 07:00","2024-09-06 18:00","취소","취소","연속"]
[197,"경기북부","구리","신포천백학#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지시설 설치 - 대상 : 154kV 신포천-백학#1T/L No.1~3,6,9~74","2024-09-03 07:00","2024-09-13 18:00","취소","취소","연속"]
[174,"경기북부","고양","양주고양#2 T/L","2024년 가공송전 순시점검 위탁공사(고양)","접속개소 과열 보수","2024-09-03 08:00","2024-09-03 15:00","2024-09-11 08:00","2024-09-11 15:00","연속"]
[175,"경기북부","고양","양주금촌#2 T/L","2024년 가공송전 순시점검 위탁공사(고양)","접속개소 과열 보수(병가선로 휴전)","2024-09-03 08:00","2024-09-03 15:00","2024-09-11 08:00","2024-09-11 15:00","연속"]
[179,"경기북부","고양","덕이호수#2 T/L","덕이S/S 디지털화공사","덕이S/S 디지털화공사","2024-09-03 09:00","2024-09-03 18:00","2024-09-10 09:00","2024-09-10 18:00","연속"]
[219,"경기북부","구리","덕소팔당HP T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-09-03 09:00","2024-09-03 18:00","2024-09-03 09:00","2024-09-03 18:00","연속"]
[233,"경기북부","직할","신의정부용현#2 T/L","(주)영인 보호계전기 성능개선 시행","유사 불량사례 발생 가능성 사전 제거를 위한 성능개선","2024-09-03 09:00","2024-09-03 18:00","취소","취소","연속"]
[177,"경기북부","고양","운정덕이#1 T/L","덕이S/S 디지털화공사","덕이S/S 디지털화공사","2024-09-04 09:00","2024-09-04 18:00","2024-09-04 09:00","2024-09-04 18:00","연속"]
[178,"경기북부","고양","운정덕이#2 T/L","덕이S/S 디지털화공사","덕이S/S 디지털화공사","2024-09-05 09:00","2024-09-05 18:00","2024-09-05 09:00","2024-09-05 18:00","연속"]
[214,"경기북부","구리","포천운천#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-09-05 09:00","2024-09-05 18:00","2024-09-05 09:00","2024-09-05 18:00","연속"]
[213,"경기북부","구리","운천철원#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-09-06 09:00","2024-09-06 18:00","2024-09-06 09:00","2024-09-06 18:00","연속"]
[176,"경기북부","고양","남면백석#2 T/L","고양전력 가공송전협력공사","추락방지장치(수평) 설치","2024-09-09 07:00","2024-09-13 18:00","2024-09-09 07:00","2024-09-13 18:00","연속"]
[211,"경기북부","구리","용정포천#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-09-09 09:00","2024-09-09 18:00","2024-09-09 09:00","2024-09-09 18:00","연속"]
[232,"경기북부","직할","용현장암#1 T/L","경기북부 직할 및 양주전력TF 362, 170kV GIS 보통점검 공사","용현SS 용현-장암#1T/L GIS 보통점검","2024-09-09 09:00","2024-09-09 18:00","2024-09-09 09:00","2024-09-09 18:00","연속"]
[191,"경기북부","구리","덕소마석#1 T/L","23~24년 직할 지중송전설비 위탁정비공사","C/T 리드선 연결금구 교체 및 피뢰기 점검","2024-09-10 08:00","2024-09-10 18:00","2024-09-10 08:00","2024-09-10 18:00","연속"]
[202,"경기북부","구리","신포천포천#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-09-10 09:00","2024-09-10 18:00","2024-09-10 09:00","2024-09-10 18:00","연속"]
[227,"경기북부","직할","양주S/S SEC CB 66670","24-25 변전협력 총액공사","170kV GIS 보통점검","2024-09-10 09:00","2024-09-10 14:00","2024-09-23 09:00","2024-09-23 18:00","연속"]
[231,"경기북부","직할","용현장암#2 T/L","경기북부 직할 및 양주전력TF 362, 170kV GIS 보통점검 공사","용현SS 용현-장암#2T/L GIS 보통점검","2024-09-10 09:00","2024-09-10 18:00","2024-09-10 09:00","2024-09-10 18:00","연속"]
[192,"경기북부","구리","덕소마석#2 T/L","23~24년 직할 지중송전설비 위탁정비공사","C/T 리드선 연결금구 교체 및 피뢰기 점검","2024-09-11 08:00","2024-09-11 18:00","2024-09-11 08:00","2024-09-11 18:00","연속"]
[226,"경기북부","직할","양주쌍문#2 T/L","24-25 변전협력 총액공사","170kV GIS 보통점검","2024-09-11 09:00","2024-09-11 14:00","2024-09-11 14:00","2024-09-11 18:00","연속"]
[196,"경기북부","구리","별내장암 T/L","23~24년 직할 지중송전설비 위탁정비공사","C/T 리드선 연결금구 교체 및 피뢰기 점검","2024-09-12 08:00","2024-09-12 18:00","2024-09-12 08:00","2024-09-12 18:00","연속"]
[187,"경기북부","구리","가평춘천HP T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-09-12 09:00","2024-09-12 18:00","2024-09-12 09:00","2024-09-12 18:00","연속"]
[206,"경기북부","구리","지제용문#2 T/L","용문S/S 154kV 장기사용 GIS 교체공사(1차분) 시험가압 휴전","□ 용문S/S 154kV 장기사용 GIS 교체공사(1차분) 시험가압 휴전 ○ 1차분 교체개소 : #2M.Tr 1차, 곤지암-용문#1T/L, BUS-TIE, PT&ES ○ 휴전사유 : #1BUS 신규 GIS 시험가압 진행하기 위해 무부하가압용 T/L 필요(지제-용문#2T/L)","2024-09-12 15:00","2024-09-13 15:00","2024-09-26 15:00","2024-09-28 11:00","연속"]
[186,"경기북부","구리","가평화천HP T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-09-13 09:00","2024-09-13 18:00","2024-09-13 09:00","2024-09-13 18:00","연속"]
[228,"경기북부","직할","양주S/S CB 6200","24-25 변전협력 총액공사","170kV GIS 보통점검","2024-09-13 14:00","2024-09-13 18:00","2024-09-23 09:00","2024-09-23 18:00","연속"]
[188,"경기북부","구리","미금구리#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-09-19 09:00","2024-09-19 14:00","2024-09-19 09:00","2024-09-19 14:00","연속"]
[205,"경기북부","구리","용문S/S #2 BUS","용문S/S 154kV 장기사용 GIS 교체공사(1차분)","□ 용문S/S 154kV 장기사용 GIS 교체공사(1차분) ○ 1차분 교체개소 : #2M.Tr 1차, 곤지암-용문#1T/L, BUS-TIE, PT&ES ○ 모선 휴전순서 : #60 → #65 → #60 → #65BUS ○ 휴전사유 : #2BUS, 2DS 철거 및 #2BUS, 2DS 신규 GIS 설치","2024-09-19 09:00","2024-10-01 18:00","2024-09-28 09:00","2024-10-08 18:00","연속"]
[189,"경기북부","구리","미금구리#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-09-19 14:00","2024-09-19 18:00","2024-09-19 14:00","2024-09-19 18:00","연속"]
[190,"경기북부","구리","구리신내#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-09-20 09:00","2024-09-20 18:00","2024-09-20 09:00","2024-09-20 18:00","연속"]
[212,"경기북부","구리","용정포천#1 T/L","23~24년 직할 지중송전설비 위탁정비공사","C/T 피뢰기 점검","2024-09-20 09:00","2024-09-20 14:00","2024-09-20 09:00","2024-09-20 14:00","연속"]
[204,"경기북부","구리","곤지암용문#2 T/L","용문S/S 154kV 장기사용 GIS 교체공사(1차분) 이격거리 휴전","□ 용문S/S 154kV 장기사용 GIS 교체공사(1차분) 이격거리 휴전 ○ 1차분 교체개소 : #2M.Tr 1차, 곤지암-용문#1T/L, BUS-TIE, PT&ES ○ 휴전사유 : 곤지암-용문#1T/L 월부싱, 외장형 LA 철거 시 이격거리 휴전 필요(곤지암-용문#2T/L, 지제-용문#2T/L)","2024-09-21 09:00","2024-09-21 13:00","2024-09-21 09:00","2024-09-21 13:00","연속"]
[210,"경기북부","구리","지제용문#2 T/L","용문S/S 154kV 장기사용 GIS 교체공사(1차분) 이격거리 휴전","□ 용문S/S 154kV 장기사용 GIS 교체공사(1차분) 이격거리 휴전 ○ 1차분 교체개소 : #2M.Tr 1차, 곤지암-용문#1T/L, BUS-TIE, PT&ES ○ 휴전사유 : 곤지암-용문#1T/L 월부싱, 외장형 LA 철거 시 이격거리 휴전 필요(곤지암-용문#2T/L, 지제-용문#2T/L)","2024-09-21 09:00","2024-09-21 13:00","2024-09-21 09:00","2024-09-21 13:00","연속"]
[181,"경기북부","고양","백학남면#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지시설 설치 - 대상 : 154kV 백학-남면#1T/L No.2~35","2024-09-23 07:00","2024-09-26 18:00","2024-09-23 07:00","2024-09-26 18:00","연속"]
[199,"경기북부","구리","신포천백학#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지시설 설치 - 대상 : 154kV 신포천-백학#2T/L No.1~3,6,40~74","2024-09-23 07:00","2024-09-26 18:00","2024-09-23 07:00","2024-09-26 18:00","연속"]
[215,"경기북부","구리","문막지제#1 T/L","구리송전협력회사 공사_피뢰기 설치","154kV 문막-지제#1T/L 피뢰기 설치 (No.1~81) 243set","2024-09-23 08:00","2024-10-04 18:00","2024-09-23 08:00","2024-10-04 18:00","연속"]
[220,"경기북부","직할","금오상계#2 T/L","24-25년 직할 변전 협력회사 총액공사","배전반 이설 대체","2024-09-23 09:00","2024-09-27 18:00","취소","취소","연속"]
[183,"경기북부","고양","신파주송포#1 T/L","(주)세니온 보호계전기 성능개선 시행","유사 불량사례 발생 가능성 사전 제거를 위한 성능개선","2024-09-24 09:00","2024-09-24 18:00","2024-09-24 09:00","2024-09-24 18:00","연속"]
[225,"경기북부","직할","신의정부금오#1 T/L","경기북부 직할 및 양주전력TF 362, 170kV GIS 보통점검 공사","신의정부SS 신의정부-금오#1T/L GIS 보통점검","2024-09-24 09:00","2024-09-24 18:00","2024-09-24 09:00","2024-09-24 18:00","연속"]
[184,"경기북부","고양","신파주송포#2 T/L","(주)세니온 보호계전기 성능개선 시행","유사 불량사례 발생 가능성 사전 제거를 위한 성능개선","2024-09-25 09:00","2024-09-25 18:00","2024-09-25 09:00","2024-09-25 18:00","연속"]
[217,"경기북부","구리","청평H/P #3 M.TR 2차 CB","24-25년 구리전력지사 변전협력회사 총액공사","6200DS 과열 보수","2024-09-25 09:00","2024-09-25 18:00","2024-09-25 09:00","2024-09-25 18:00","연속"]
[218,"경기북부","구리","청평H/P #2 M.TR 2차 CB","24-25년 구리전력지사 변전협력회사 총액공사","6200DS 과열 보수","2024-09-25 09:00","2024-09-25 18:00","2024-09-25 09:00","2024-09-25 18:00","연속"]
[195,"경기북부","구리","미금덕소#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-09-26 09:00","2024-09-26 18:00","2024-09-26 09:00","2024-09-26 18:00","연속"]
[198,"경기북부","구리","신포천덕계#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지시설 설치 - 대상 : 154kV 신포천-덕계#2T/L No.65~70","2024-09-27 07:00","2024-09-27 18:00","2024-09-27 07:00","2024-09-27 18:00","연속"]
[223,"경기북부","직할","백석덕계#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지시설 설치 - 대상 : 154kV 백석-덕계#2T/L No.22~28","2024-09-27 07:00","2024-09-27 18:00","2024-09-27 07:00","2024-09-27 18:00","연속"]
[194,"경기북부","구리","미금덕소#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-09-27 09:00","2024-09-27 18:00","2024-09-27 09:00","2024-09-27 18:00","연속"]
[185,"경기북부","고양","신덕은금촌#1 T/L","고양전력 가공송전협력공사","추락방지장치(수평) 설치","2024-09-30 07:00","2024-10-02 18:00","2024-09-30 07:00","2024-10-02 18:00","연속"]
[221,"경기북부","직할","녹양백석#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평추락방지장치 설치 - 154kV 녹양-백석#1T/L No.1~11","2024-09-30 07:00","2024-09-30 18:00","2024-09-30 07:00","2024-09-30 18:00","연속"]
[229,"경기북부","직할","양주녹양#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평추락방지장치 설치 - 154kV 녹양-백석#1T/L No.5~11","2024-09-30 07:00","2024-09-30 18:00","2024-09-30 07:00","2024-09-30 18:00","연속"]
[193,"경기북부","구리","미금광장 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-09-30 09:00","2024-09-30 18:00","2024-09-30 09:00","2024-09-30 18:00","연속"]
[216,"경기북부","구리","덕소진건#2 T/L","(주)세니온 보호계전기 성능개선 시행","유사 불량사례 발생 가능성 사전 제거를 위한 성능개선","2024-09-30 09:00","2024-09-30 18:00","2024-09-30 09:00","2024-09-30 18:00","연속"]
[203,"경기북부","구리","지제용문#2 T/L","용문S/S 154kV 장기사용 GIS 교체공사(1차분) 시험가압 휴전","□ 용문S/S 154kV 장기사용 GIS 교체공사(1차분) 시험가압 휴전 ○ 1차분 교체개소 : #2M.Tr 1차, 곤지암-용문#1T/L, BUS-TIE, PT&ES ○ 휴전사유 : #2BUS 신규 GIS 시험가압 진행하기 위해 무부하가압용 T/L 필요(지제-용문#2T/L)","2024-09-30 15:00","2024-10-01 15:00","2024-10-07 15:00","2024-10-09 11:00","연속"]
[235,"경기","군포","남군포산본#2 T/L","남군포S/S #4M.Tr 증설공사(#66BUS 무부하가압용)","남군포S/S #4M.Tr 1차 GIS(#66BUS) 증설관련 무부하가압용","2024-09-05 09:00","2024-09-06 18:00","취소","취소","연속"]
[236,"경기","군포","남군포의왕#1 T/L","남군포S/S 남군포-의왕#1T/L GIS 샤프트 및 C링 점검","남군포S/S 남군포-의왕#1T/L GIS 샤프트 및 C링 점검","2024-09-03 09:00","2024-09-03 14:00","취소","취소","연속"]
[237,"경기","군포","남군포의왕#2 T/L","남군포S/S 남군포-의왕#2T/L GIS 샤프트 및 C링 점검","남군포S/S 남군포-의왕#2T/L GIS 샤프트 및 C링 점검","2024-09-03 14:00","2024-09-03 18:00","취소","취소","연속"]
[238,"경기","군포","서서울남군포#3 T/L","남군포S/S 서서울-남군포#3T/L GIS 초기점검,샤프트 및 C링 점검","남군포S/S 서서울-남군포#3T/L GIS 초기점검,샤프트 및 C링 점검","2024-09-04 09:00","2024-09-04 18:00","취소","취소","연속"]
[239,"경기","군포","목내안산복합#1 T/L","목내S/S 목내-안산복합#1T/L GIS 조작시험","목내S/S 목내-안산복합#1T/L GIS 조작시험","2024-09-27 10:00","2024-09-27 13:00","취소","취소","연속"]
[240,"경기","군포","산본안양#1 T/L","[GIS 정밀]산본S/S 산본-안양#1T/L GIS 정밀점검","[GIS 정밀]산본S/S 산본-안양#1T/L GIS 정밀점검 시행","2024-09-30 09:00","2024-10-02 18:00","2024-09-30 09:00","2024-10-02 18:00","연속"]
[241,"경기","군포","산본안양#2 T/L","24-25년 군포 가공송전협력회사 공사","피뢰기 설치공사 : 154kV 산본-안양#2T/L 10기 30SET","2024-09-10 07:00","2024-09-10 18:00","2024-09-10 07:00","2024-09-10 18:00","연속"]
[242,"경기","군포","서서울#2봉담#1 T/L","20203~2024년 군포전력지사 지중송전 위탁전문공사","피뢰기,CT점검","2024-09-19 13:00","2024-09-19 18:00","취소","취소","연속"]
[243,"경기","군포","시화중시화 T/L","시화,중시화SS 시화-중시화T/L GIS 세니온 성능개선","시화,중시화SS 송전선로보호반(단거리) 세니온 성능개선(F/W 업데이트)","2024-09-04 09:00","2024-09-04 18:00","취소","취소","연속"]
[244,"경기","군포","시화성곡 T/L","성곡,시화S/S 시화-성곡T/L GIS 보통점검 및 조작시험","성곡,시화S/S 시화-성곡T/L GIS 보통점검 및 조작시험","2024-09-02 09:00","2024-09-02 18:00","취소","취소","연속"]
[245,"경기","군포","목내안산복합#2 T/L","안산복합SY 목내-안산복합2TL 누기개소 보수공사","안산복합SY 목내-안산복합2TL 누기개소 보수공사","2024-09-30 09:00","2024-10-02 18:00","취소","취소","연속"]
[246,"경기","군포","신시화중시화#1 T/L","중시화S/S 신시화-중시화#1T/L GIS 초기점검","중시화S/S 신시화-중시화#1T/L GIS 초기점검","2024-09-23 09:00","2024-09-23 13:00","2024-09-23 09:00","2024-09-23 13:00","연속"]
[247,"경기","군포","신시화중시화#2 T/L","중시화S/S 신시화-중시화#2T/L GIS 초기점검","중시화S/S 신시화-중시화#2T/L GIS 초기점검","2024-09-23 13:00","2024-09-23 18:00","2024-09-23 13:00","2024-09-23 18:00","연속"]
[248,"경기","동부","동판교야탑 T/L","23-24년 지중송전설비 위탁정비공사(성남전력지사)","대한전선 열경화공법 EBG 가스채취밸브 설치","2024-09-02 09:00","2024-09-05 18:00","취소","취소","연속"]
[249,"경기","동부","중원야탑 T/L","23-24년 지중송전설비 위탁정비공사(성남전력지사)","대한전선 열경화공법 EBG 가스채취밸브 설치","2024-09-23 09:00","2024-09-26 18:00","2024-09-23 09:00","2024-09-26 18:00","연속"]
[250,"경기","성남","신봉이의#2 T/L","(6월 순연) 24-25년 경기직할 가공송전 협력회사 총액공사","불량애자 교체공사[4회선 병가]","2024-09-02 07:00","2024-09-02 18:00","취소","취소","연속"]
[251,"경기","성남","신성남서판교#3 T/L","세니온제 송전선로 보호반 성능개선","세니온제 IED 성능개선","2024-09-06 09:00","2024-09-06 18:00","취소","취소","연속"]
[252,"경기","성남","신성남S/S CB 6400","2024년 성남전력 변전협력회사 총액공사","GIS 조작시험","2024-09-27 09:00","2024-09-27 18:00","2024-09-27 09:00","2024-09-27 18:00","연속"]
[253,"경기","성남","신성남S/S #61 BUS","2024년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검(1DS부)","2024-09-12 09:00","2024-09-13 15:00","2024-09-12 09:00","2024-09-13 15:00","연속"]
[254,"경기","성남","신성남S/S #66 BUS","2024년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검(2DS부)","2024-09-13 15:00","2024-09-14 18:00","2024-09-13 15:00","2024-09-14 18:00","연속"]
[255,"경기","성남","신성남S/S #61 BUS","2024년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검(6201DS부)","2024-09-19 09:00","2024-09-20 15:00","2024-09-19 09:00","2024-09-20 15:00","연속"]
[256,"경기","성남","신성남S/S #66 BUS","2024년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검(6202DS부)","2024-09-20 15:00","2024-09-21 18:00","2024-09-20 15:00","2024-09-21 18:00","연속"]
[257,"경기","성남","신성남과천#1 T/L","신성남S/S 154kV #1,2,3,4Sh.R 설치사업","· 기초파쇄 시 설비진동(GIS) · 공사 시 활선 안전이격 확보","2024-09-06 09:00","2024-12-10 18:00","2024-09-06 09:00","2024-12-10 18:00","연속"]
[258,"경기","성남","신성남S/S #66 BUS","2024년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검(2DS부)","2024-09-24 15:00","2024-09-25 18:00","2024-09-24 15:00","2024-09-25 18:00","연속"]
[259,"경기","성남","신성남S/S #61 BUS","2024년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검(1DS부)","2024-09-23 09:00","2024-09-24 15:00","2024-09-23 09:00","2024-09-24 15:00","연속"]
[260,"경기","성남","신성남S/S CB 6200","2024년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검","2024-09-19 09:00","2024-09-21 18:00","2024-09-19 09:00","2024-09-21 18:00","연속"]
[261,"경기","직할","관양동안양#2 T/L","동안양S/S 지중송전선로 인출정비 공사","154kV 관양-동안양T/L 인출정비 - 선종/길이 : XLPE 2000 / 0.426km","2024-09-19 08:00","2024-10-18 18:00","2024-09-19 08:00","2024-10-18 18:00","연속"]
[262,"경기","직할","봉담남수원#1 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 2회선 7기, 4회선 21기","2024-09-08 07:00","2024-09-11 18:00","2024-09-08 07:00","2024-09-11 18:00","연속"]
[263,"경기","직할","남수원발안#1 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 2회선 7기, 4회선 21기","2024-09-12 07:00","2024-09-14 18:00","2024-09-12 07:00","2024-09-14 18:00","연속"]
[264,"경기","직할","남수원발안#2 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 4회선 21기(봉담-남수원#2T/L 병가선로)","2024-09-08 07:00","2024-09-11 18:00","2024-09-08 07:00","2024-09-11 18:00","연속"]
[265,"경기","직할","봉담남수원#2 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 2회선 7기, 4회선 21기","2024-09-12 07:00","2024-09-14 18:00","2024-09-12 07:00","2024-09-14 18:00","연속"]
[266,"경기","직할","과천동안양#2 T/L","24-25년 군포 가공송전협력회사 공사","피뢰기 설치공사 : 154kV 과천-동안양#2T/L 4기 12SET","2024-09-02 07:00","2024-09-02 18:00","취소","취소","연속"]
[267,"경기","직할","의왕동안양#1 T/L","24-25년 군포 가공송전협력회사 공사","피뢰기 설치공사 : 154kV 의왕-동안양#1T/L 40기 120SET","2024-09-02 07:00","2024-09-06 18:00","취소","취소","연속"]
[268,"경기","직할","동안양안양CC#2 T/L","154kV 연락T/L 설치관련 안전이격 휴전","154kV 연락T/L 전력케이블 포설을 위한 기초파쇄작업 안전이격","2024-09-22 08:00","2024-09-22 18:00","2024-09-22 08:00","2024-09-22 18:00","연속"]
[269,"경기","직할","관양동안양#1 T/L","154kV 연락T/L 설치관련 안전이격 휴전","154kV 연락T/L 전력케이블 포설을 위한 기초파쇄작업 안전이격","2024-09-22 08:00","2024-09-22 18:00","2024-09-22 08:00","2024-09-22 18:00","연속"]
[270,"경기","직할","동안양안양CC#1 T/L","154kV 연락T/L 설치관련 안전이격 휴전","154kV 연락T/L 전력케이블 포설을 위한 기초파쇄작업 안전이격","2024-09-22 08:00","2024-09-22 18:00","2024-09-22 08:00","2024-09-22 18:00","연속"]
[271,"경기","직할","서수원율전#1 T/L","24-25년 군포 가공송전협력회사 공사","율전-의왕#1T/L 피뢰기 설치공사 병가구간 안전이격거리 확보","2024-09-09 07:00","2024-09-09 18:00","취소","취소","연속"]
[272,"경기","직할","서서울율전#1 T/L","24-25년 군포 가공송전협력회사 공사","율전-의왕#1T/L 피뢰기 설치공사 병가구간 안전이격거리 확보","2024-09-09 07:00","2024-09-09 18:00","취소","취소","연속"]
[273,"경기","직할","율전의왕#1 T/L","20203~2024년 군포전력지사 지중송전 위탁전문공사","피뢰기,CT점검","2024-09-05 09:00","2024-09-05 18:00","취소","취소","연속"]
[274,"경기","직할","율전의왕#2 T/L","24-25년 군포 가공송전협력회사 공사","피뢰기 설치공사 : 154kV 율전-의왕#2T/L 13기 39SET","2024-09-03 07:00","2024-09-04 18:00","취소","취소","연속"]
[275,"경기","성남","남사동탄#1 T/L"," 추락방지장치(수평) 설치공사","154kV 남사-동탄#1T/L 12기","2024-09-02 08:00","2024-09-03 18:00","취소","취소","연속"]
[276,"경기","성남","신용인용인#2 T/L"," 24-25년 경기직할 가공송전 협력회사 총액공사","피뢰기 설치공사","2024-09-03 07:00","2024-09-06 18:00","취소","취소","연속"]
[277,"경기","직할","율전의왕#2 T/L"," 24-25년 군포 가공송전협력회사 공사","피뢰기 설치공사 : 154kV 율전-의왕#2T/L 13기 39SET","2024-09-03 07:00","2024-09-04 18:00","취소","취소","연속"]
[278,"경기","동부","곤지암이천#2 T/L"," 곤지암S/S 154kV #65M.Tr 증설사업","증설설비(M.Tr, GIS, 전력케이블) 무부하가압","2024-09-03 09:00","2024-09-04 13:00","2024-09-03 09:00","2024-09-04 13:00","연속"]
[279,"경기","동부","곤지암S/S #62 BUS"," 곤지암S/S 154kV #65M.Tr 증설공사","#154kV 1DS, 전력케이블 상확인 · 증설설비 무부하가압","2024-09-03 09:00","2024-09-03 13:00","2024-09-03 09:00","2024-09-03 13:00","연속"]
[280,"경기","동부","성현S/S CB 6100"," 24-25년 동부 변전협력총액공사","성현:6100(조작),6179(조작)","2024-09-03 09:00","2024-09-03 14:00","2024-09-03 09:00","2024-09-03 14:00","연속"]
[281,"경기","동부","곤지암S/S #67 BUS"," 곤지암S/S 154kV #65M.Tr 증설공사","#154kV 2DS, 전력케이블 상확인 · 증설설비 무부하가압","2024-09-03 13:00","2024-09-04 13:00","2024-09-03 13:00","2024-09-04 13:00","연속"]
[282,"경기","성남","남사동탄#2 T/L"," 추락방지장치(수평) 설치공사","154kV 남사-동탄#2T/L 12기","2024-09-04 08:00","2024-09-05 18:00","취소","취소","연속"]
[283,"경기","평택","고덕#2S/S SEC CB 60610"," 24년도 평택전력 345&amp154kV GIS 보통점검","고덕#2S/S 154kV GIS 하자점검","2024-09-04 09:00","2024-09-04 14:00","2024-09-04 09:00","2024-09-04 14:00","연속"]
[284,"경기","평택","고덕#2S/S SEC CB 65660"," 24년도 평택전력 345&amp154kV GIS 보통점검","고덕#2S/S 154kV GIS 하자점검","2024-09-04 14:00","2024-09-04 18:00","2024-09-04 14:00","2024-09-04 18:00","연속"]
[285,"경기","동부","오천율현#1 T/L"," 24-25년 가공송전협력회사 총액공사(피뢰기 설치)","154kV 오천-율현#1T/L 송전선로용 피뢰기 설치 대상 : No.1~25(총 23기)","2024-09-05 07:00","2024-09-07 18:00","2024-09-05 07:00","2024-09-07 18:00","연속"]
[286,"경기","군포","남군포산본#2 T/L"," 남군포S/S #4M.Tr 증설공사(#66BUS 무부하가압용)","남군포S/S #4M.Tr 1차 GIS(#66BUS) 증설관련 무부하가압용","2024-09-05 09:00","2024-09-06 18:00","취소","취소","연속"]
[287,"경기","직할","수촌조암#2 T/L"," 수촌S/S #4M.Tr 증설공사"," #4M.Tr 설치관련 위상측정 및 무부하가압","2024-09-05 09:00","2024-09-06 18:00","2024-09-05 09:00","2024-09-06 18:00","연속"]
[288,"경기","직할","율전의왕#1 T/L"," 20203~2024년 군포전력지사 지중송전 위탁전문공사","피뢰기,CT점검","2024-09-05 09:00","2024-09-05 18:00","취소","취소","연속"]
[289,"경기","평택","고덕#2S/S CB 6400"," 24년도 평택전력 154,345kV GIS 보통점검","고덕2S/S 154kV 64Bay TIE GIS 보통점검","2024-09-05 09:00","2024-09-05 14:00","2024-09-05 09:00","2024-09-05 14:00","연속"]
[290,"경기","평택","송탄안성 T/L"," 24년도 평택전력 변전협력회사 총액공사","송탄, 안성S/S 송탄-안성T/L 170kV GIS 보통점검","2024-09-05 09:00","2024-09-05 18:00","취소","취소","연속"]
[291,"경기","평택","고덕#2S/S 고덕2에어퍼스트#1T/L CB"," 24년도 평택전력 154,345kV GIS 보통점검","고덕2S/S 154kV 고덕2-에어퍼스트#1T/L(6472) GIS 보통점검","2024-09-05 14:00","2024-09-05 18:00","2024-09-05 14:00","2024-09-05 18:00","연속"]
[292,"경기","성남","신성남서판교#3 T/L"," 세니온제 송전선로 보호반 성능개선","세니온제 IED 성능개선","2024-09-06 09:00","2024-09-06 18:00","취소","취소","연속"]
[293,"경기","평택","고덕#2동평택#2 T/L"," 24년도 평택전력 345&amp154kV GIS 보통점검","고덕#2S/S 154kV GIS (6872) 하자점검","2024-09-06 14:00","2024-09-06 18:00","취소","취소","연속"]
[294,"경기","직할","율전의왕#2 T/L"," 24-25년 군포 가공송전협력회사 공사","피뢰기 설치공사 : 154kV 율전-의왕#2T/L 9기 27SET","2024-09-09 07:00","2024-09-09 18:00","2024-09-09 07:00","2024-09-09 18:00","연속"]
[295,"경기","군포","사강남양#1 T/L"," 남양S/S 남양-사강 #1T/L 보통점검","남양S/S 남양-사강 #1T/L 보통점검","2024-09-09 09:00","2024-09-09 18:00","2024-09-09 09:00","2024-09-09 18:00","연속"]
[296,"경기","성남","기흥신갈#1 T/L"," 24-25년 경기직할 가공송전 협력회사 총액공사","불량애자 교체공사[4회선 병가]","2024-09-09 10:00","2024-09-09 18:00","2024-09-09 10:00","2024-09-09 18:00","연속"]
[297,"경기","군포","마도사강#1 T/L"," 20203~2024년 군포전력지사 지중송전 위탁전문공사","피뢰기,CT점검","2024-09-10 09:00","2024-09-10 18:00","2024-09-10 09:00","2024-09-10 18:00","연속"]
[298,"경기","동부","이천가남#1 T/L"," 가남S/S 154kV #4M.Tr 증설공사","인접 Bay 감압 및 무부하 가압 선로 기기설치 시 안전이격 확보","2024-09-10 09:00","2024-09-27 18:00","취소","취소","연속"]
[299,"경기","성남","덕성남사#2 T/L"," 덕성S/S 덕성-남사#2T/L GIS 누기보수","상부 BUS측 누기 보수","2024-09-10 09:00","2024-09-11 18:00","2024-09-10 09:00","2024-09-11 18:00","연속"]
[300,"경기","군포","사강남양#2 T/L"," 24-25년 군포 가공송전협력회사 공사","피뢰기 설치공사 : 154kV 남양-사강#2T/L 30기 90SET","2024-09-11 07:00","2024-09-12 18:00","2024-09-11 07:00","2024-09-12 18:00","연속"]
[301,"경기","동부","오포모현#2 T/L"," 24-25년 동부 변전협력총액공사","모현:오포-모현#2T/L(보통)","2024-09-11 09:00","2024-09-11 18:00","2024-09-11 09:00","2024-09-11 18:00","연속"]
[302,"경기","평택","서운삼죽 T/L"," 24년도 평택전력 변전협력회사 총액공사","서운,삼죽S/S 서운-삼죽T/L 보호배전반 대체공사 및 삼죽S/S 170kV GIS 보통점검","2024-09-11 09:00","2024-09-13 18:00","취소","취소","연속"]
[303,"경기","성남","신용인동백#2 T/L"," 24-25년 경기직할 가공송전 협력회사 총액공사","피뢰기 설치공사","2024-09-12 07:00","2024-09-12 18:00","2024-09-12 07:00","2024-09-12 18:00","연속"]
[304,"경기","군포","남군포산본#2 T/L"," 남군포S/S #4M.Tr 증설공사(#61BUS 무부하가압용)","남군포S/S #4M.Tr 1차 GIS(#61BUS) 증설관련 무부하가압용","2024-09-12 09:00","2024-09-13 18:00","2024-09-12 09:00","2024-09-13 18:00","연속"]
[305,"경기","직할","의왕동안양#2 T/L"," 20203~2024년 군포전력지사 지중송전 위탁전문공사","피뢰기,CT점검","2024-09-12 09:00","2024-09-12 13:00","2024-09-12 09:00","2024-09-12 13:00","연속"]
[306,"경기","평택","원정평택TP#1 T/L"," 24년도 평택전력 변전협력회사 총액공사","평택T/P 평택TP-원정#1T/L GIS 보통점검 및 원정S/S 평택TP-원정#2T/L GIS 조작시험 및 PT&LA 보통점검","2024-09-12 09:00","2024-09-12 18:00","취소","취소","연속"]
[307,"경기","성남","신용인S/S #62 BUS"," 세니온제 모선보호반 성능개선","세니온제 IED 성능개선","2024-09-13 09:00","2024-09-13 18:00","2024-09-13 09:00","2024-09-13 18:00","연속"]
[308,"경기","평택","원정평택TP#2 T/L"," 24년도 평택전력 변전협력회사 총액공사","평택T/P 평택TP-원정#1T/L GIS 보통점검 및 원정S/S 평택TP-원정#2T/L GIS 조작시험 및 PT&LA 보통점검","2024-09-13 09:00","2024-09-13 18:00","취소","취소","연속"]
[309,"경기","직할","화성남양#2 T/L"," (군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 4회선 7기","2024-09-19 07:00","2024-09-19 18:00","취소","취소","연속"]
[310,"경기","동부","곤지암용문#1 T/L"," 24-25 동부전력지사 송전협력회사 공사","수평 추락방지장치 설치공사(13~83호)","2024-09-19 07:30","2024-10-02 18:00","2024-09-19 07:30","2024-10-02 18:00","연속"]
[311,"경기","동부","가남S/S #2 BUS"," 가남S/S 154kV #4M.Tr 증설공사","#65BUS 설치 및 무부하 가압","2024-09-19 09:00","2024-09-27 14:00","2024-09-19 09:00","2024-09-27 14:00","연속"]
[312,"경기","평택","서운안성#1 T/L"," 24년도 평택전력 변전협력회사 총액공사","안성S/S 서운-안성#1T/L 170kV GIS 보통점검","2024-09-19 09:00","2024-09-19 18:00","취소","취소","연속"]
[313,"경기","직할","화성남양#1 T/L"," (군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 4회선 7기","2024-09-20 07:00","2024-09-20 18:00","취소","취소","연속"]
[314,"경기","평택","서운안성#2 T/L"," 24년도 평택전력 변전협력회사 총액공사","안성S/S 서운-안성#2T/L 170kV GIS 보통점검","2024-09-20 09:00","2024-09-20 18:00","취소","취소","연속"]
[315,"경기","평택","오성C/C CB 6100","  24년도 평택전력 변전협력회사 총액공사","오성C/C 6100 BUSTIE 170kV GIS 보통점검","2024-09-20 09:00","2024-09-20 14:00","2024-09-20 09:00","2024-09-20 14:00","연속"]
[316,"경기","평택","오성C/C SEC CB 60610","  24년도 평택전력 변전협력회사 총액공사"," 오성C/C 60-61SEC 170kV GIS 보통점검","2024-09-20 14:00","2024-09-20 18:00","2024-09-20 14:00","2024-09-20 18:00","연속"]
[317,"경기","직할","화성수촌#1 T/L"," (군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 2회선 13기, 4회선 7기","2024-09-21 07:00","2024-09-22 18:00","취소","취소","연속"]
[318,"경기","직할","화성발안#1 T/L"," (군포)추락방지장치(수평) 설치공사"," 철탑추락방지장치(수평) 설치 : 4회선 7기 (화성-수촌#1T/L 병가선로)","2024-09-21 07:00","2024-09-21 18:00","취소","취소","연속"]
[319,"경기","군포","서서울서수원#1 T/L"," 24-25년 군포 가공송전협력회사 공사","피뢰기 설치공사 : 154kV 서서울-서수원#1T/L 14기 42SET","2024-09-23 07:00","2024-09-24 18:00","2024-09-23 07:00","2024-09-24 18:00","연속"]
[320,"경기","성남","신용인기흥#2 T/L"," 24-25년 경기직할 가공송전 협력회사 총액공사","피뢰기 설치공사","2024-09-23 07:00","2024-09-25 18:00","2024-09-23 07:00","2024-09-25 18:00","연속"]
[321,"경기","동부","성현분당#2 T/L"," 24-25년 동부 변전협력총액공사","성현:성현-분당#2T/L(초기) 분당:성현-분당#2T/L(보통)","2024-09-23 09:00","2024-09-23 18:00","2024-09-23 09:00","2024-09-23 18:00","연속"]
[322,"경기","직할","안양평촌#1 T/L"," 2024-25년 경기본부 직할 변전협력회사 공사","평촌: 안양-평촌#1,#2T/L 조작시험 관양-평촌#1T/L A상 미터링 CT 시험","2024-09-23 09:00","2024-09-23 11:00","취소","취소","연속"]
[323,"경기","평택","원정만호#2 T/L"," 24년도 평택전력 변전협력회사 총액공사","만호,원정S/S 원정-만호#2T/L 세니온제 보호반 성능개선 및 만호S/S 170kV GIS 보통점검 , 원정S/S GIS 보통 및 공기조작부 분해점검","2024-09-23 09:00","2024-09-23 18:00","2024-09-23 09:00","2024-09-23 18:00","연속"]
[324,"경기","직할","안양평촌#2 T/L"," 2024-25년 경기본부 직할 변전협력회사 공사","평촌: 안양-평촌#1,#2T/L 조작시험 관양-평촌#1T/L A상 미터링 CT 시험","2024-09-23 11:00","2024-09-23 14:00","취소","취소","연속"]
[325,"경기","직할","관양평촌#1 T/L"," 2024-25년 경기본부 직할 변전협력회사 공사","평촌: 안양-평촌#1,#2T/L 조작시험 관양-평촌#1T/L A상 미터링 CT 시험","2024-09-23 14:00","2024-09-23 18:00","2024-09-23 14:00","2024-09-23 18:00","연속"]
[326,"경기","동부","초월S/S CB 6100"," 24-25년 동부 변전협력총액공사","초월:6100(보통)","2024-09-24 09:00","2024-09-24 18:00","2024-09-24 09:00","2024-09-24 18:00","연속"]
[327,"경기","성남","용인덕성#1 T/L"," 154kV 덕성S/S #1M.Tr용 170kV GIS 증설공사","증설 인접Bay 모선부 감압 및 무부하가압용","2024-09-24 09:00","2024-10-03 18:00","2024-09-24 09:00","2024-10-03 18:00","연속"]
[328,"경기","성남","모현용인#1 T/L"," 2024년 성남전력 변전협력회사 총액공사","보호반 대체","2024-09-25 09:00","2024-09-27 18:00","취소","취소","연속"]
[329,"경기","성남","신수원S/S CB 6300"," 2024년 성남전력 변전협력회사 총액공사","GIS 조작시험","2024-09-26 09:00","2024-09-26 14:00","취소","취소","연속"]
[330,"경기","성남","신수원S/S SEC CB 66670"," 2024년 성남전력 변전협력회사 총액공사","GIS 조작시험","2024-09-26 14:00","2024-09-26 18:00","취소","취소","연속"]
[331,"경기","직할","서수원율전#2 T/L"," 2024-25년 경기본부 직할 송전정비","경기 직할 송전 주 작업으로 변경 시행(직할변전→송전정비)","2024-09-27 07:00","2024-09-27 18:00","2024-09-27 07:00","2024-09-27 18:00","연속"]
[332,"경기","직할","화성발안#2 T/L"," (군포)추락방지장치(수평) 설치공사"," 철탑추락방지장치(수평) 설치 : 4회선 7기 (화성-수촌#2T/L 병가선로)","2024-09-28 07:00","2024-09-28 18:00","취소","취소","연속"]
[333,"경기","직할","화성수촌#2 T/L"," (군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 2회선 13기, 4회선 7기","2024-09-28 07:00","2024-09-29 18:00","취소","취소","연속"]
[334,"경기","성남","모현용인#2 T/L"," 2024년 성남전력 변전협력회사 총액공사","보호반 대체","2024-09-30 09:00","2024-10-02 18:00","2024-09-30 09:00","2024-10-02 18:00","연속"]
[335,"경기","평택","원정만호#1 T/L"," 24년도 평택전력 변전협력회사 총액공사"," 원정,만호S/S 원정-만호#1T/L 보호배전반 대체공사","2024-09-30 09:00","2024-10-02 18:00","2024-09-30 09:00","2024-10-02 18:00","연속"]
[336,"강원","강릉","속초간성#1 T/L","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","무부하 시험가압","2024-09-13 16:00","2024-09-14 18:00","2024-09-27 16:00","2024-09-28 18:00","연속"]
[337,"강원","강릉","간성S/S #2 BUS","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","1. #61-66 B/T 설치 2. 간성인제#2T/L 대체 3. 154kV PT GIS 설치 4. 154kV Sh.C GIS 철거","2024-09-23 08:00","2024-10-18 18:00","2024-09-30 08:00","2024-10-18 18:00","연속"]
[338,"강원","강릉","간성S/S #2 BUS","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","1. #61-66 B/T 설치 2. 간성인제#2T/L 대체 3. 154kV PT GIS 설치 4. 154kV Sh.C GIS 철거","2024-09-02 08:00","2024-09-03 12:00","2024-09-09 08:00","2024-09-10 12:00","연속"]
[339,"강원","강릉","간성인제#2 T/L","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","1. #61-66 B/T 설치 2. 간성인제#2T/L 대체 3. 154kV PT GIS 설치 4. 154kV Sh.C GIS 철거","2024-09-02 08:00","2024-10-25 18:00","2024-09-09 08:00","2024-10-25 18:00","연속"]
[340,"강원","강릉","간성인제#1 T/L","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","안전이격 확보","2024-09-02 08:00","2024-09-03 18:00","2024-09-30 08:00","2024-10-01 18:00","매일"]
[341,"강원","강릉","간성S/S #3 M.Tr CB","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","170kV GIS 대체공사 안전이격 확보","2024-09-02 08:00","2024-10-16 18:00","취소","취소","연속"]
[342,"강원","강릉","간성S/S #1 BUS","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","1. #61-66 B/T 설치 2. 간성인제#2T/L 대체 3. 154kV PT GIS 설치 4. 154kV Sh.C GIS 철거","2024-09-03 12:00","2024-09-14 18:00","2024-09-10 12:00","2024-09-28 18:00","연속"]
[343,"강원","강릉","간성인제#1 T/L","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","안전이격 확보","2024-09-09 08:00","2024-09-10 18:00","2024-09-09 08:00","2024-09-10 18:00","매일"]
[344,"강원","강릉","간성인제#1 T/L","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","안전이격 확보","2024-09-23 08:00","2024-09-24 18:00","2024-09-23 08:00","2024-09-24 18:00","매일"]
[345,"강원","강릉","주진평창#1 T/L","2024년 가공송전 순시점검 위탁공사","○ 정밀점검 - 154kV 주진-평창T/L No.1~57 정밀점검 시행","2024-09-02 08:30","2024-09-06 18:00","취소","취소","매일"]
[346,"강원","강릉","주진평창#2 T/L","2024년 가공송전 순시점검 위탁공사","○ 정밀점검 - 154kV 주진-평창T/L No.1~57 정밀점검 시행","2024-09-09 08:30","2024-09-13 18:00","취소","취소","매일"]
[347,"강원","동해","도계태백 T/L","2024~2025년 동해전력지사 변전협력회사 공사","도계 디지털화, LA초기점검, 차단기조작시험","2024-09-30 09:00","2024-10-01 18:00","2024-09-30 09:00","2024-10-01 18:00","연속"]
[348,"강원","동해","동해이원#1 T/L","2024년 가공송전선로 순시점검 위탁공사","○ 송전선로 정밀점검 ○ 추락방지장치 (수평) 설치","2024-09-09 07:00","2024-09-12 18:00","2024-09-09 07:00","2024-09-12 18:00","연속"]
[349,"강원","동해","동해동영월 T/L","2024년 가공송전선로 순시점검 위탁공사","○송전선로 정밀점검 ○추락방지장치(수평) 설치","2024-09-26 07:00","2024-10-12 18:00","2024-09-26 07:00","2024-10-12 18:00","연속"]
[350,"강원","동해","동해이원#2 T/L","2024년 가공송전선로 순시점검 위탁공사","○ 송전선로 정밀점검 ○ 추락방지장치 (수평) 설치","2024-09-23 07:00","2024-09-25 18:00","2024-09-23 07:00","2024-09-25 18:00","연속"]
[351,"강원","동해","태백삼척GP#2 T/L","2024~2025년 동해전력지사 변전협력회사 공사","GIS 보통점검, LA점검","2024-09-06 09:00","2024-09-06 18:00","2024-09-06 09:00","2024-09-06 18:00","연속"]
[352,"강원","원주","홍천소양강HP T/L","2024~2025년 강원본부 직할 송전협력회사 공사","애자련 교체","2024-09-30 08:00","2024-10-01 18:00","2024-09-30 08:00","2024-10-01 18:00","연속"]
[353,"강원","직할","남춘천춘천열병합#2 T/L","남춘천S/S 154kV 장기사용 GIS 대체공사","■ 1차 공정 - 154kV 남춘천-춘천열병합 #2T/L GIS 대체 - 154kV #1M.Tr 1차 GIS 대체 - 154kV BUS-TIE GIS 대체 - 154kV PT&ES GIS 대체","2024-09-19 09:00","2024-11-06 18:00","2024-09-19 09:00","2024-11-06 18:00","연속"]
[354,"강원","직할","남춘천S/S #2 BUS","남춘천S/S 154kV 장기사용 GIS 대체공사","■ 1차 공정 - 154kV 홍천-남춘천T/L GIS 대체 - 154kV #2M.Tr 1차 GIS 대체","2024-09-19 09:00","2024-10-02 18:00","2024-09-19 09:00","2024-10-02 18:00","연속"]
[355,"강원","직할","철원화천#2 T/L","2024년 강원본부 직할 154kV GIS, GCB 정밀점검 공사","□ 철원S/S 154kV 철원-화천#2T/L GIS 정밀점검 □ 철원S/S 154kV 철원-화천#2T/L LA 보통점검","2024-09-25 13:00","2024-09-28 18:00","2024-09-25 13:00","2024-09-28 18:00","연속"]
[356,"강원","직할","운천철원#1 T/L","2024년 강원본부 직할 154kV GIS, GCB 정밀점검 공사","□ 철원S/S 154kV 운천-철원#1T/L GIS 정밀점검 □ 철원S/S 154kV 운천-철원#1T/L LA 보통점검","2024-09-09 09:00","2024-09-11 13:00","2024-09-09 09:00","2024-09-11 13:00","연속"]
[357,"강원","직할","운천철원#2 T/L","2024년 강원본부 직할 154kV GIS, GCB 정밀점검 공사","□ 철원S/S 154kV 운천-철원#2T/L GIS 정밀점검 □ 철원S/S 154kV 운천-철원#2T/L LA 보통점검","2024-09-11 13:00","2024-09-13 18:00","2024-09-11 13:00","2024-09-13 18:00","연속"]
[358,"강원","직할","철원화천#1 T/L","2024년 강원본부 직할 154kV GIS, GCB 정밀점검 공사","□ 철원S/S 154kV 철원-화천#1T/L GIS 정밀점검 □ 철원S/S 154kV 철원-화천#1T/L LA 보통점검","2024-09-23 09:00","2024-09-25 13:00","2024-09-23 09:00","2024-09-25 13:00","연속"]
[359,"강원","직할","북춘천춘천HP T/L","2024~2025년 강원본부 직할 변전협력회사 공사","□ 춘천HP 154kV 북춘천-춘천HP T/L GCB 점검","2024-09-09 09:00","2024-09-09 18:00","2024-09-09 09:00","2024-09-09 18:00","연속"]
[360,"강원","직할","춘천북춘천#1 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","□ 춘천S/S 154kV 춘천-북춘천 #1T/L 보호배전반 교체 공사 □ 북춘천S/S 154kV 춘천-북춘천 #1T/L 보호배전반 교체 공사","2024-09-03 09:00","2024-09-06 18:00","취소","취소","연속"]
[361,"강원","직할","춘천북춘천#2 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","□ 춘천S/S 154kV 춘천-북춘천 #2T/L 보호배전반 교체 공사 □ 북춘천S/S 154kV 춘천-북춘천 #2T/L 보호배전반 교체 공사","2024-09-10 09:00","2024-09-13 18:00","2024-09-10 09:00","2024-09-13 18:00","연속"]
[362,"강원","직할","양구화천HP#1 T/L","2024년 강원본부 직할 154kV GIS, GCB 정밀점검 공사","□ 화천HP 154kV 양구-화천HP#1T/L GIS 정밀점검 □ 화천HP 154kV 양구-화천HP#1T/L LA 보통점검","2024-09-30 09:00","2024-10-02 13:00","2024-09-30 09:00","2024-10-02 13:00","연속"]
[363,"강원","태백","영월영월CC T/L","2024-2025년 태백전력지사 변전협력회사 공사","영월S/S 154kV 영월-영월CC T/L GIS 조작시험 영월C/C 154kV 영월-영월CC T/L GIS 조작시험(병행)","2024-09-11 09:00","2024-09-11 18:00","2024-09-11 09:00","2024-09-11 18:00","연속"]
[364,"강원","태백","태백S/S #65 BUS","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치 - 기타 부대공사","2024-09-24 10:00","2024-09-27 18:00","2024-09-24 10:00","2024-09-27 18:00","연속"]
[365,"강원","태백","태백S/S #60 BUS","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치 - 기타 부대공사","2024-09-30 10:00","2024-10-04 18:00","2024-09-30 10:00","2024-10-04 18:00","연속"]
[366,"강원","태백","태백영월에코윈드 T/L","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치 - 기타 부대공사","2024-09-30 10:00","2024-10-04 18:00","2024-09-30 10:00","2024-10-04 18:00","연속"]
[367,"강원","태백","태백삼척GP#1 T/L","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치 - 기타 부대공사","2024-09-26 10:00","2024-09-27 18:00","2024-09-26 10:00","2024-09-27 18:00","연속"]
[368,"강원","태백","태백영월에코윈드 T/L","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치 - 기타 부대공사","2024-09-24 10:00","2024-09-27 18:00","2024-09-24 10:00","2024-09-27 18:00","연속"]
[369,"충북","직할","신진천S/S SEC CB 60610","24-25년 충북본부 직할 변전협력회사 공사","효성제 154kV GIS 전자변 교체","2024-09-24 09:00","2024-09-24 18:00","취소","취소","연속"]
[370,"충북","직할","신진천S/S SEC CB 61620","24-25년 충북본부 직할 변전협력회사 공사","- 154kV GIS 보통점검 - 효성제 154kV GIS 전자변 교체","2024-09-25 09:00","2024-09-25 18:00","취소","취소","연속"]
[371,"충북","직할","신진천S/S SEC CB 65660","24-25년 충북본부 직할 변전협력회사 공사","- 154kV GIS 보통점검","2024-09-26 09:00","2024-09-26 18:00","취소","취소","연속"]
[372,"충북","직할","신진천S/S SEC CB 66670","24-25년 충북본부 직할 변전협력회사 공사","- 154kV GIS 보통점검 - 효성제 154kV GIS 전자변 교체","2024-09-27 09:00","2024-09-27 18:00","취소","취소","연속"]
[373,"충북","직할","신진천진천#1 T/L","24년 충북본부 직할 154kV GIS 정밀점검 공사","신진천S/S 154kV 신진천-진천#1T/L GIS 정밀점검","2024-09-07 07:00","2024-09-08 18:00","취소","취소","연속"]
[374,"충북","직할","신진천진천#2 T/L","24년 충북본부 직할 154kV GIS 정밀점검 공사","신진천S/S 154kV 신진천-진천#2T/L GIS 정밀점검","2024-09-21 07:00","2024-09-22 18:00","취소","취소","연속"]
[375,"충북","직할","진천덕산#2 T/L","24년 충북본부 직할 154kV GIS 정밀점검 공사","진천S/S 154kV 진천-덕산#2T/L GIS 정밀점검","2024-09-26 07:00","2024-09-27 18:00","2024-09-26 07:00","2024-09-27 18:00","연속"]
[376,"충북","직할","신진천진천#1 T/L","24년 충북본부 직할 154kV GIS 정밀점검 공사","진천S/S 154kV 신진천-진천#1T/L GIS 정밀점검","2024-09-28 07:00","2024-09-29 18:00","취소","취소","연속"]
[377,"충북","직할","진천덕산#1 T/L","24년 충북본부 직할 154kV GIS 정밀점검 공사","진천S/S 154kV 진천-덕산#1T/L GIS 정밀점검","2024-09-24 07:00","2024-09-25 18:00","2024-09-24 07:00","2024-09-25 18:00","연속"]
[378,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-09-02 08:00","2024-09-05 14:00","취소","취소","연속"]
[379,"충북","청주","남청주청주#2 T/L","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-09-02 08:00","2024-09-27 18:00","취소","취소","연속"]
[380,"충북","청주","남청주청주#4 T/L","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체 관련 고장용량 해소용","2024-09-02 08:00","2024-09-27 18:00","취소","취소","연속"]
[381,"충북","청주","남청주S/S SEC CB 65660","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#66BUS 무부하 가압용","2024-09-04 14:00","2024-09-05 14:00","취소","취소","연속"]
[382,"충북","청주","남청주S/S #61 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-09-05 14:00","2024-09-14 14:00","취소","취소","연속"]
[383,"충북","청주","남청주S/S SEC CB 60610","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#61BUS 무부하 가압용","2024-09-13 14:00","2024-09-14 14:00","취소","취소","연속"]
[384,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-09-19 14:00","2024-09-27 18:00","취소","취소","연속"]
[385,"충북","청주","남청주S/S #62 BUS","24년 청주전력지사 170kV GIS 정밀점검","남청주S/S 154kV #2Sh.C GIS 정밀점검 후 무부하 가압","2024-09-25 16:00","2024-09-25 18:00","2024-09-25 16:00","2024-09-25 18:00","연속"]
[386,"충북","청주","남청주S/S SEC CB 62610","24년 청주전력지사 170kV GIS 정밀점검","남청주S/S 154kV #2Sh.C GIS 정밀점검 후 무부하 가압","2024-09-25 16:00","2024-09-25 18:00","2024-09-25 16:00","2024-09-25 18:00","연속"]
[387,"충북","청주","남청주S/S SEC CB 65660","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#66BUS 무부하 가압용","2024-09-26 14:00","2024-09-27 18:00","취소","취소","연속"]
[388,"충북","청주","남청주S/S #62 BUS","24년 청주전력지사 170kV GIS 정밀점검","남청주S/S 154kV #7Sh.C GIS 정밀점검 후 무부하 가압","2024-09-27 16:00","2024-09-27 18:00","2024-09-27 16:00","2024-09-27 18:00","연속"]
[389,"충북","청주","남청주S/S SEC CB 62610","24년 청주전력지사 170kV GIS 정밀점검","남청주S/S 154kV #7Sh.C GIS 정밀점검 후 무부하 가압","2024-09-27 16:00","2024-09-27 18:00","2024-09-27 16:00","2024-09-27 18:00","연속"]
[390,"충북","청주","사직북청주#1 T/L","24년 청주전력지사 170kV GIS 정밀점검","사직S/S 154kV 사직-북청주#1T/L GIS 정밀점검","2024-09-23 08:00","2024-09-24 18:00","취소","취소","연속"]
[391,"충북","청주","신옥천유천 T/L","24-25년 변전협력회사 총액공사","보호배전반 대체(양단)","2024-09-09 09:00","2024-09-12 18:00","취소","취소","연속"]
[392,"충북","청주","남청주오송#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사","170kV GIS 보통점검","2024-09-11 10:00","2024-09-11 18:00","취소","취소","연속"]
[393,"충북","청주","남청주오송#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사","170kV GIS 보통점검","2024-09-10 10:00","2024-09-10 18:00","취소","취소","연속"]
[394,"충북","청주","오창국사#1 T/L","24년 청주전력지사 170kV GIS 정밀점검","오창S/S 154kV 오창-국사#1T/L GIS 정밀점검","2024-09-11 08:00","2024-09-12 18:00","취소","취소","연속"]
[395,"충북","청주","문백오창#1 T/L","24년 청주전력지사 170kV GIS 정밀점검","오창S/S 154kV 문백-오창#1T/L GIS 정밀점검","2024-09-09 08:00","2024-09-10 18:00","취소","취소","연속"]
[396,"충북","청주","옥천영동 T/L","세니온제 보호계전기 성능개선","154kV 옥천-영동T/L 계전기 성능개선","2024-09-26 10:30","2024-09-26 18:00","취소","취소","연속"]
[397,"충북","청주","율량봉명#2 T/L","봉명율량#2T/L 보호배전반대체","봉명율량#2T/L 보호배전반대체","2024-09-30 09:00","2024-10-02 18:00","2024-09-30 09:00","2024-10-02 18:00","연속"]
[398,"충북","청주","율량봉명#1 T/L","봉명율량#1T/L 보호배전반 대체","봉명율량#1T/L 보호배전반 대체","2024-09-02 09:00","2024-09-05 18:00","취소","취소","연속"]
[399,"충북","충주","신충주감곡#2 T/L","(주)세니온 보호계전기 일제 성능개선 시행","(주)세니온 보호계전기 일제 성능개선 시행 - 계통시험파트 및 세니온 제작사 입회","2024-09-03 10:00","2024-09-03 18:00","2024-09-03 10:00","2024-09-03 18:00","연속"]
[400,"충북","충주","신충주감곡#2 T/L","2024년 충주전력지사 170kV GIS 정밀점검","감곡S/S 170kV 동부#1 T/L GIS 정밀점검 후 무부하가압용","2024-09-13 17:00","2024-09-13 18:00","2024-09-13 17:00","2024-09-13 18:00","연속"]
[401,"충북","충주","감곡S/S CB 6100","2024년 충주전력지사 170kV GIS 정밀점검","감곡S/S 170kV 동부#1 T/L GIS 정밀점검 후 무부하가압용","2024-09-13 17:00","2024-09-13 18:00","2024-09-13 17:00","2024-09-13 18:00","연속"]
[402,"충북","충주","감곡S/S #1 BUS","'24-25년 충주전력지사 변전정비 총액공사","감곡S/S PT 집합반 대체, #1BUS 휴전","2024-09-30 09:00","2024-09-30 14:00","취소","취소","연속"]
[403,"충북","충주","감곡S/S #1 BUS","2024년 충주전력지사 170kV GIS 정밀점검","감곡S/S 170kV 동부#1 T/L GIS 정밀점검 후 무부하가압용","2024-09-13 17:00","2024-09-13 18:00","2024-09-13 17:00","2024-09-13 18:00","연속"]
[404,"충북","충주","감곡S/S #2 BUS","'24-25년 충주전력지사 변전정비 총액공사","감곡S/S PT 집합반 대체, #2BUS 모선 휴전","2024-09-30 14:00","2024-09-30 18:00","취소","취소","연속"]
[405,"충북","충주","신충주감곡#1 T/L","(주)세니온 보호계전기 일제 성능개선 시행","(주)세니온 보호계전기 일제 성능개선 시행 - 계통시험파트 및 세니온 제작사 입회","2024-09-02 10:00","2024-09-02 18:00","2024-09-02 10:00","2024-09-02 18:00","연속"]
[406,"충북","충주","금왕남음성#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","154kV 금왕-남음성#1T/L 수평 추락방지장치 설치 - 수평 추락방지장치(23기) : No.2~6, 9~26","2024-09-10 07:30","2024-09-12 18:00","취소","취소","매일"]
[407,"충북","충주","금왕남음성#2 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","154kV 금왕-남음성#2T/L 수평 추락방지장치 및 피뢰기 설치 - 수평 추락방지장치(23기) : No.2~6, 9~26 - 피뢰기 설치(25기) : No.2~26","2024-09-30 07:30","2024-10-02 18:00","취소","취소","매일"]
[408,"충북","충주","북충주충주 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.84-88,94)","2024-09-30 07:00","2024-09-30 16:00","2024-09-30 07:00","2024-09-30 16:00","연속"]
[409,"충북","충주","신제천S/S CB 6100","2024년 충주전력지사 170kV GIS 정밀점검","신제천S/S 170kV #1Sh.C GIS 정밀점검 후 무부하가압용","2024-09-03 17:00","2024-09-03 18:00","2024-09-03 17:00","2024-09-03 18:00","연속"]
[410,"충북","충주","신제천S/S #65 BUS","2024년 충주전력지사 170kV GIS 정밀점검","신제천S/S 170kV #2Sh.C GIS 정밀점검 후 무부하가압용","2024-09-05 17:00","2024-09-05 18:00","2024-09-05 17:00","2024-09-05 18:00","연속"]
[411,"충북","충주","신제천S/S CB 6100","2024년 충주전력지사 170kV GIS 정밀점검","신제천S/S 170kV #2Sh.C GIS 정밀점검 후 무부하가압용","2024-09-05 17:00","2024-09-05 18:00","2024-09-05 17:00","2024-09-05 18:00","연속"]
[412,"충북","충주","신제천제천#2 T/L","(주)세니온 보호계전기 일제 성능개선 시행","(주)세니온 보호계전기 일제 성능개선 시행 - 계통시험파트 및 세니온 제작사 입회","2024-09-12 10:00","2024-09-12 18:00","취소","취소","연속"]
[413,"충북","충주","신제천영월CC#1 T/L","2024~2025 충주전력지사 송전협력회사 공사","2024~2025 충주전력지사 송전협력회사 공사 수평추락방지장치 및 고정형 폴리머 점퍼지지애자 설치","2024-09-23 07:00","2024-09-25 18:00","2024-09-23 07:00","2024-09-25 18:00","매일"]
[414,"충북","충주","신제천영월CC#2 T/L","2024~2025 충주전력지사 송전협력회사 공사","2024~2025 충주전력지사 송전협력회사 공사 수평추락방지장치 및 고정형 폴리머 점퍼지지애자 설치","2024-09-26 07:00","2024-10-02 18:00","2024-09-26 07:00","2024-10-02 18:00","매일"]
[415,"충북","충주","신제천S/S #65 BUS","2024년 충주전력지사 170kV GIS 정밀점검","신제천S/S 170kV #1Sh.C GIS 정밀점검 후 무부하가압용","2024-09-03 17:00","2024-09-03 18:00","2024-09-03 17:00","2024-09-03 18:00","연속"]
[416,"충북","충주","신충주북충주#2 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.26-69호)","2024-09-08 07:00","2024-09-13 16:00","2024-09-08 07:00","2024-09-13 16:00","매일"]
[417,"충북","충주","신충주북충주#1 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.26-69호)","2024-09-02 07:00","2024-09-07 16:00","취소","취소","매일"]
[418,"충북","충주","신충주음성#1 T/L","'24-25년 충주전력지사 변전정비 총액공사","신충주,음성S/S 154kV GIS 보통점검 및 (주) 세니온 보호계전기 일제 성능개선 시행","2024-09-24 10:00","2024-09-24 18:00","취소","취소","연속"]
[419,"충북","충주","신충주음성#2 T/L","'24-25년 충주전력지사 변전정비 총액공사","신충주,음성S/S 154kV GIS 보통점검 및 (주) 세니온 보호계전기 일제 성능개선 시행","2024-09-25 10:00","2024-09-25 18:00","취소","취소","연속"]
[420,"충북","충주","신제천왕암#2 T/L","(주)세니온 보호계전기 일제 성능개선 시행","(주)세니온 보호계전기 일제 성능개선 시행 - 계통시험파트 및 세니온 제작사 입회","2024-09-20 10:00","2024-09-20 18:00","취소","취소","연속"]
[421,"충북","충주","왕암여주#2 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.26-69호)","2024-09-02 07:00","2024-09-07 16:00","취소","취소","매일"]
[422,"충북","충주","왕암여주#1 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.26-69호)","2024-09-08 07:00","2024-09-13 16:00","2024-09-08 07:00","2024-09-13 16:00","매일"]
[423,"충북","충주","신제천왕암#1 T/L","(주)세니온 보호계전기 일제 성능개선 시행","(주)세니온 보호계전기 일제 성능개선 시행 - 계통시험파트 및 세니온 제작사 입회","2024-09-19 10:00","2024-09-19 18:00","취소","취소","연속"]
[424,"충북","충주","음성금왕#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","154kV 음성-금왕#1T/L 수평 추락방지장치 및 피뢰기 설치, 애자교체 - 수평 추락방지장치(60기) : No.1, 8~57, 60~65 - 피뢰기 설치(69기) : No.1~65 - 애자교체(1기) : 음성S/T","2024-09-24 07:30","2024-10-02 18:00","취소","취소","매일"]
[425,"충북","충주","음성금왕#2 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","154kV 음성-금왕#2T/L 수평 추락방지장치 설치, 애자교체 - 수평 추락방지장치(30기) : No.1, 33~36.1, 40~57, 60~65 - 애자교체(3기) : 음성S/T, No.1, 1.1","2024-09-09 07:30","2024-09-12 18:00","취소","취소","매일"]
[426,"충북","충주","음성천연가스사리 T/L","음성천연가스발전소 수폐수처리설비 건설공사","음성천연SY~No.1호 철탑간 수폐수처리설비 건설공사 시행관련 중장비(크레인) 고장예방을 위한 안전이격거리확보","2024-09-03 07:00","2024-09-03 19:00","2024-09-03 07:00","2024-09-03 19:00","연속"]
[427,"충북","충주","음성음성천연가스#2 T/L","음성천연가스발전소 수폐수처리설비 건설공사","음성천연SY~No.1호 철탑간 수폐수처리설비 건설공사 시행관련 중장비(크레인) 고장예방을 위한 안전이격거리확보","2024-09-03 07:00","2024-09-03 19:00","2024-09-03 07:00","2024-09-03 19:00","연속"]
[428,"충북","충주","신제천제천#1 T/L","2024년 충주전력지사 170kV GIS 정밀점검","제천S/S 170kV 신제천-제천#1 T/L GIS 정밀점검","2024-09-09 09:00","2024-09-10 18:00","취소","취소","연속"]
[429,"충북","충주","충주충주HP#2 T/L","효성제 170kV 전동스프링 GIS 발청베어링 교체공사","충주S/S 154kV 충주-충주HP#2T/L GIS 발청베어링 교체공사","2024-09-27 14:00","2024-09-27 18:00","2024-09-27 14:00","2024-09-27 18:00","연속"]
[430,"충북","충주","왕암충주 T/L","효성제 170kV 전동스프링 GIS 발청베어링 교체공사","충주S/S 154kV 왕암-충주T/L GIS 발청베어링 교체공사","2024-09-26 14:00","2024-09-26 18:00","2024-09-26 14:00","2024-09-26 18:00","연속"]
[431,"충북","충주","충주S/S CB 6100","효성제 170kV 전동스프링 GIS 발청베어링 교체공사","충주S/S 154kV #60-#65 BUS SEC GIS 발청베어링 교체공사","2024-09-19 14:00","2024-09-19 18:00","2024-09-19 14:00","2024-09-19 18:00","연속"]
[432,"충북","충주","충주S/S SEC CB 60610","효성제 170kV 전동스프링 GIS 발청베어링 교체공사","충주S/S 154kV #60-#61 BUS SEC GIS 발청베어링 교체공사","2024-09-19 10:00","2024-09-19 14:00","2024-09-19 10:00","2024-09-19 14:00","연속"]
[433,"충북","충주","충주풍동 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.64-75호)","2024-09-23 07:00","2024-09-24 16:00","2024-09-23 07:00","2024-09-24 16:00","매일"]
[434,"충북","충주","풍동음성#1 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.64-75)","2024-09-25 07:00","2024-09-27 16:00","2024-09-25 07:00","2024-09-27 16:00","매일"]
[435,"충북","충주","풍동음성#2 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.64-75호)","2024-09-23 07:00","2024-09-24 16:00","2024-09-23 07:00","2024-09-24 16:00","매일"]
[436,"충북","충주","풍동장연 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.64-75)","2024-09-25 07:00","2024-09-27 16:00","2024-09-25 07:00","2024-09-27 16:00","매일"]
[437,"대전세종충남","대전","금산무주#2 T/L","금산S/S 154kV 금산-무주#2T/L GIS 보통점검","금산S/S 154kV 금산-무주#2T/L GIS 보통점검","2024-09-25 09:00","2024-09-25 18:00","2024-09-25 15:00","2024-09-25 21:00","연속"]
[438,"대전세종충남","대전","금산무주#1 T/L","금산S/S 154kV 금산-무주#1T/L GIS 보통점검","금산S/S 154kV 금산-무주#1T/L GIS 보통점검","2024-09-24 09:00","2024-09-24 18:00","2024-09-24 15:00","2024-09-24 21:00","연속"]
[439,"대전세종충남","대전","신옥천남대전#3 T/L","남대전SA 154kV 신옥천-남대전#3T/L GIS 계전기 업데이트","남대전SA 154kV 신옥천-남대전#3T/L GIS 계전기 업데이트","2024-09-23 09:00","2024-09-23 18:00","2024-09-23 09:00","2024-09-23 18:00","연속"]
[440,"대전세종충남","대전","신옥천남대전#4 T/L","남대전SA 154kV 신옥천-남대전#4T/L GIS 계전기 업데이트","남대전SA 154kV 신옥천-남대전#4T/L GIS 계전기 업데이트","2024-09-30 09:00","2024-09-30 18:00","2024-09-30 09:00","2024-09-30 18:00","연속"]
[441,"대전세종충남","대전","부여논산#1 T/L","논산S/S 154kV 부여-논산#1T/L GIS 정밀점검공사","논산S/S 154kV 부여-논산#1T/L GIS 정밀점검공사","2024-09-09 09:00","2024-09-10 18:00","취소","취소","연속"]
[442,"대전세종충남","대전","부여논산#2 T/L","논산S/S 154kV 부여-논산#2T/L GIS 정밀점검공사","논산S/S 154kV 부여-논산#2T/L GIS 정밀점검공사","2024-09-11 09:00","2024-09-12 18:00","취소","취소","연속"]
[443,"대전세종충남","대전","팔봉두마#2 T/L","154kV 팔봉-두마T/L No.67~109 선종교체공사","선종교체공사 안전이격 휴전","2024-09-02 07:00","2024-09-10 18:00","2024-09-02 15:00","2024-09-11 09:00","매일"]
[444,"대전세종충남","대전","팔봉두마#2 T/L","154kV 팔봉-두마T/L No.67~109 선종교체공사","공사구간 : 154kV 팔봉-두마T/L No.67~109 공사내용 : ACSR 240㎟ → ASCC/TW 310㎟ x S x 2C, 15km 전선교체 저지상고 및 취약 철탑 교체 6기","2024-09-23 07:00","2024-09-27 18:00","취소","취소","연속"]
[445,"대전세종충남","대전","신계룡두마#1 T/L","[송전][즉시가압O]345kV신옥천-청양등8개T/L추락방지설치공사","[송전][주말작업제외][즉시가압O]345kV 신옥천-청양 등 8개T/L 추락방지 설치공사","2024-09-23 06:00","2024-10-01 18:00","2024-09-23 06:00","2024-10-01 11:00","매일"]
[446,"대전세종충남","대전","신계룡은진#1 T/L","[송전][즉시가압O]345kV신옥천-청양등8개T/L추락방지설치공사","[송전][주말작업제외][즉시가압O]345kV신옥천-청양 등 8개 T/L 추락방지 설치공사","2024-09-25 06:00","2024-10-11 18:00","2024-09-25 06:00","2024-10-11 11:00","매일"]
[447,"대전세종충남","대전","신흥동대전#1 T/L","신흥S/S 154kV 신흥-동대전#1T/L GIS 차단기 개폐타임 측정","신흥S/S 154kV 신흥-동대전#1T/L GIS 차단기 개폐타임 측정","2024-09-26 09:00","2024-09-26 13:00","2024-09-26 09:00","2024-09-26 13:00","연속"]
[448,"대전세종충남","대전","신흥동대전#2 T/L","신흥S/S 154kV 신흥-동대전#2T/L GIS 차단기 개폐타임 측정","신흥S/S 154kV 신흥-동대전#2T/L GIS 차단기 개폐타임 측정","2024-09-26 13:00","2024-09-26 18:00","2024-09-26 13:00","2024-09-26 18:00","연속"]
[449,"대전세종충남","대전","신흥동대전#3 T/L","신흥S/S 154kV 신흥-동대전#3T/L GIS 차단기 개폐타임 측정","신흥S/S 154kV 신흥-동대전#3T/L GIS 차단기 개폐타임 측정","2024-09-27 09:00","2024-09-27 13:00","2024-09-27 09:00","2024-09-27 13:00","연속"]
[450,"대전세종충남","대전","남대전신흥#1 T/L","신흥S/S 154kV 남대전-신흥#1T/L GIS 차단기 개폐타임 측정","신흥S/S 154kV 남대전-신흥#1T/L GIS 차단기 개폐타임 측정","2024-09-27 09:00","2024-09-27 18:00","2024-09-27 09:00","2024-09-27 18:00","연속"]
[451,"대전세종충남","대전","추부금산#1 T/L","[송전][취소시][즉시가압O]신옥천-청양등8개T/L추락방지설치공사","[송전][주말작업제외][즉시가압O]345kV 신옥천-청양 등 8개T/L 추락방지 설치공사","2024-09-26 07:00","2024-10-18 18:00","취소","취소","매일"]
[452,"대전세종충남","대전","추부S/S #1 BUS","추부S/S 154kV #3M.Tr 증설공사","- 154kV M.Tr(20MVA*3) * 1Bank 설치 - 154kV GIS 1CCT, 23kV GIS 3CCT 설치 - M.Tr 2차 전력케이블 설치 - 기타 부대작업 등","2024-09-19 16:00","2024-09-20 09:00","2024-09-19 16:00","2024-09-20 09:00","매일"]
[453,"대전세종충남","대전","추부S/S CB 6100","추부S/S 154kV #3M.Tr 증설공사(무부하)","#1BUS 무부하 가압 시행","2024-09-20 07:00","2024-09-20 09:00","2024-09-20 07:00","2024-09-20 09:00","연속"]
[454,"대전세종충남","대전","추부S/S #2 BUS","추부S/S 154kV #3M.Tr 증설공사","- 154kV M.Tr(20MVA*3) * 1Bank 설치 - 154kV GIS 1CCT, 23kV GIS 3CCT 설치 - M.Tr 2차 전력케이블 설치 - 기타 부대작업 등","2024-09-23 16:00","2024-09-24 09:00","2024-09-23 16:00","2024-09-24 09:00","매일"]
[455,"대전세종충남","대전","신옥천추부#2 T/L","[송전][취소시][즉시가압O]신옥천-청양등8개T/L추락방지설치공사","[송전][주말작업제외][즉시가압O]345kV 신옥천-청양등8개T/L추락방지설치공사","2024-09-23 07:00","2024-10-01 18:00","취소","취소","매일"]
[456,"대전세종충남","대전","추부S/S CB 6100","추부S/S 154kV #3M.Tr 증설공사(무부하)","#2BUS 무부하 가압 시행","2024-09-24 07:00","2024-09-24 09:00","2024-09-24 07:00","2024-09-24 09:00","연속"]
[457,"대전세종충남","서산","석문당진화력#1 T/L","서산P/O 효성제 170kV GIS 베어링 교체공사","(8월 휴전신청 취소시) (즉시가압 가능) 당진화력S/S 154kV 석문-당진화력#1T/L 617 CB 베어링 교체 (병행) 석문S/S 154kV 석문-당진화력#1T/L IED 성능개선 (병행) 석문S/S 154kV 석문-당진화력#1T/L 617 CB 보통점검 (병행) 당진화력S/S 154kV 석문-당진화력#1T/L 617CB 보통점검","2024-09-09 09:30","2024-09-10 18:00","취소","취소","매일"]
[458,"대전세종충남","서산","석문당진화력#2 T/L","서산P/O 효성제 170kV GIS 베어링 교체공사","(8월 휴전신청 취소시) (즉시가압 가능) 당진화력S/S 154kV 석문-당진화력#2T/L 627 CB 베어링 교체 (병행) 석문S/S 154kV 석문-당진화력#2T/L IED 성능개선 (병행) 석문S/S 154kV 석문-당진화력#2T/L 687 CB 보통점검 (병행) 당진화력S/S 154kV 석문-당진화력#2T/L 627 CB 보통점검","2024-09-11 09:30","2024-09-12 18:00","취소","취소","매일"]
[459,"대전세종충남","서산","대산석문#2 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.28~34,38~42,44,45) , 즉시가압(20분 이내) 가능","2024-09-19 08:00","2024-09-19 18:00","2024-09-19 08:00","2024-09-19 18:00","연속"]
[460,"대전세종충남","서산","대산석문#1 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.35~37,43,46,47) , 즉시가압(20분 이내) 가능","2024-09-13 08:00","2024-09-13 18:00","2024-09-13 08:00","2024-09-13 18:00","연속"]
[461,"대전세종충남","서산","서산해미 T/L","'23년 서산P/O 장기사용 배전반 교체공사","(즉시가압 불가)서산, 해미S/S 154kV 서산-해미T/L 보호반 대체공사","2024-09-09 09:00","2024-09-11 18:00","2024-09-09 09:00","2024-09-11 18:00","연속"]
[462,"대전세종충남","서산","서산대산 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.15~83) , 즉시가압(20분 이내) 가능","2024-09-20 08:00","2024-09-27 18:00","2024-09-20 08:00","2024-09-27 18:00","매일"]
[463,"대전세종충남","서산","서산태안#1 T/L","'24~'25년도 서산전력지사 송전협력회사 공사","154kV 서산-대산T/L 항공구 설치공사 No.9~10, 11~12 (2경간) *154 서산-대산T/L 병가선로, 서산-대산T/L 휴전 미승인시 취소요청","2024-09-26 08:00","2024-09-27 18:00","취소","취소","매일"]
[464,"대전세종충남","서산","당진송악#2 T/L","'24~'25년 서산전력지사 송전협력회사","154kV 당진-송악T/L 추락방지장치(레일형) 설치공사 * 즉시가압 불가 * 154kV 합덕-송악TL 휴전 우선/ 합덕송악TL 휴전 미승인시 취소 요청","2024-09-23 08:00","2024-09-25 18:00","취소","취소","연속"]
[465,"대전세종충남","서산","당진송악#1 T/L","'24~'25년 서산전력지사 송전협력회사","154kV 당진-송악TL 추락방지장치(레일형) 설치공사 * 즉시가압 불가 * 154kV 합덕-송악TL 휴전 우선/ 합덕송악TL 휴전 미승인시 취소 요청","2024-09-30 08:00","2024-10-02 18:00","취소","취소","연속"]
[466,"대전세종충남","서산","신당진서산#2 T/L","24년 서산P/O 변전협력회사 총액공사","(즉시가압 가능) 신당진S/S 154kV 신당진-서산#2T/L GIS 하자점검 (병행) 서산S/S 154kV 신당진-서산#2T/L GIS 보통점검 (병행) 신당진S/S 신당진-서산#2T/L CVT 대체 (병행) 서산S/S 154kV 신당진-서산#2T/L LA 보통점검 (송전병행) 154kV 신당진-서산#2T/L 수평 추락방지 설치 (송전병행) 154kV 상간 스페이서 설치","2024-09-30 09:30","2024-10-01 18:00","2024-09-30 09:30","2024-10-01 18:00","매일"]
[467,"대전세종충남","서산","합덕송악#1 T/L","24년 서산P/O 154kV GIS 정밀점검공사","(즉시가압 불가) 합덕S/S 154kV 합덕-송악#1T/L 657 GIS 정밀점검공사","2024-09-23 09:30","2024-09-25 18:00","취소","취소","연속"]
[468,"대전세종충남","서산","합덕송악#2 T/L","24년 서산P/O 154kV GIS 정밀점검공사","(즉시가압 불가) 합덕S/S 154kV 합덕-송악#2T/L 687 GIS 정밀점검공사","2024-09-30 09:30","2024-10-02 18:00","취소","취소","연속"]
[469,"대전세종충남","세종","신풍공주#1 T/L","[송전] 154kV 신풍-공주#1T/L 피뢰기 설치공사","[송전] 154kV 신풍-공주#1T/L 피뢰기 설치공사 - No. 1~74(74기) ※ 요청 시 1시간 이내 가압 가능","2024-09-23 07:00","2024-10-04 18:00","2024-09-23 07:00","2024-10-04 18:00","매일"]
[470,"대전세종충남","세종","덕진대화#1 T/L","[변전]'24년 세종전력지사 변전협력회사 총액공사","○154kV GIS 차단기 조작시험 -전자변 교체 병행 -즉시가압 불가","2024-09-26 10:00","2024-09-26 18:00","취소","취소","연속"]
[471,"대전세종충남","세종","천안전의#1 T/L","[변전]'24년 세종전력지사 변전협력회사 총액공사","○ 154kV GIS 보통점검 -즉시가압 가능","2024-09-27 10:00","2024-09-27 18:00","취소","취소","연속"]
[472,"대전세종충남","직할","덕진대화#2 T/L","덕진,대화S/S 덕진-대화#2T/L 송전선로 보호반 대체공사","O 덕진,대화S/S 덕진-대화#2T/L 송전선로 보호반 대체","2024-09-23 09:00","2024-09-25 18:00","취소","취소","연속"]
[473,"대전세종충남","직할","송강신일#2 T/L","송강,신일S/S 송강-신일#2T/L 송전선로 보호반 대체공사","송강,신일S/S 송강-신일#2T/L 송전선로 보호반 대체","2024-09-09 09:00","2024-09-12 18:00","취소","취소","연속"]
[474,"대전세종충남","직할","둔곡송강#1 T/L","세니온제 보호계전기 성능개선 공사","ㅁ 세니온제 보호계전기 성능개선공사 ㅁ 기타사항 : 20분이내 가압조건가능, 휴전시간 최소화(09:00 ~ 14:00)","2024-09-28 09:00","2024-09-28 14:00","취소","취소","연속"]
[475,"대전세종충남","직할","동대전신탄진#1 T/L","154kV 신탄진S/S 미래화 관련 인출T/L 지중화공사","공사구간 : 신탄진S/S 인출 전력구 공사내용 : 인출선로 지중화 공사 휴전 필요사유 : 기존 가공선로 스트럭쳐 하부에서 지중송전 EBA 접속을 위한 크레인 사용시 사고 우려","2024-09-12 09:00","2024-09-12 18:00","2024-09-12 09:00","2024-09-12 18:00","연속"]
[476,"대전세종충남","직할","동대전신탄진#2 T/L","154kV 신탄진S/S 미래화 관련 인출T/L 지중화공사","공사구간 : 신탄진S/S 인출 전력구 공사내용 : 인출선로 지중화 공사 휴전 필요사유 : 기존 가공선로 스트럭쳐 하부에서 지중송전 EBA 접속을 위한 크레인 사용시 사고 우려","2024-09-19 09:00","2024-09-19 18:00","2024-09-19 09:00","2024-09-19 18:00","연속"]
[477,"대전세종충남","직할","부강신탄진 T/L","154kV 신탄진S/S 미래화 관련 인출T/L 지중화공사","공사구간 : 신탄진S/S 인출 전력구 공사내용 : 인출선로 지중화 공사 휴전 필요사유 : 기존 가공선로 스트럭쳐 하부에서 지중송전 EBA 접속을 위한 크레인 사용시 사고 우려","2024-09-26 09:00","2024-09-26 18:00","2024-09-26 09:00","2024-09-26 18:00","연속"]
[478,"대전세종충남","직할","신탄진대청HP T/L","154kV 신탄진S/S 미래화 관련 인출T/L 지중화공사","공사구간 : 신탄진S/S 인출 전력구 공사내용 : 인출선로 지중화 공사 휴전 필요사유 : 기존 가공선로 스트럭쳐 하부에서 지중송전 EBA 접속을 위한 크레인 사용시 사고 우려","2024-09-30 09:00","2024-09-30 18:00","2024-09-30 09:00","2024-09-30 18:00","연속"]
[479,"대전세종충남","천안","둔포추팔#2 T/L","둔포S/S 154kV 둔포-추팔#2T/L 보통점검","(즉시가압가능)둔포S/S 154kV 둔포-추팔#2T/L 보통점검","2024-09-06 09:00","2024-09-06 18:00","2024-09-06 09:00","2024-09-06 18:00","연속"]
[480,"대전세종충남","천안","장재불당#2 T/L","불당S/S 154kV 장재-불당#2T/L CB 개폐타임측정","(즉시가압가능)불당S/S 154kV 장재-불당#2T/L CB 개폐타임측정","2024-09-13 14:00","2024-09-13 18:00","취소","취소","연속"]
[481,"대전세종충남","천안","장재불당#1 T/L","불당S/S 154kV 장재-불당#1T/L CB 개폐타임측정","(즉시가압가능)불당S/S 154kV 장재-불당#1T/L CB 개폐타임측정","2024-09-13 09:00","2024-09-13 14:00","취소","취소","연속"]
[482,"대전세종충남","천안","서천안탕정#1 T/L","154kV 서천안-탕정T/L 추락방지장치 설치공사","[즉시가압가능, 주말작업없음]154kV 서천안-탕정T/L No. 3 ~ 23 추락방지장치 설치 [병행작업] 조류착지방지장치 설치","2024-09-13 07:00","2024-09-19 18:00","취소","취소","매일"]
[483,"대전세종충남","천안","신온양석곡#1 T/L","신온양, 석곡S/S 154kV 신온양-석곡#1T/L 성능개선","(즉시가압불가)신온양, 석곡S/S 154kV 신온양-석곡#1T/L 성능개선","2024-09-10 09:00","2024-09-10 18:00","취소","취소","연속"]
[484,"대전세종충남","천안","신온양석곡#2 T/L","신온양, 석곡S/S 154kV 신온양-석곡#2T/L 성능개선","(즉시가압불가)신온양, 석곡S/S 154kV 신온양-석곡#2T/L 성능개선","2024-09-26 09:00","2024-09-26 18:00","취소","취소","연속"]
[485,"대전세종충남","천안","신탕정S/S SEC CB 65660","신탕정S/S 154kV #65-#66 SEC GIS 보통점검","(즉시가압가능)신탕정S/S 154kV #65-#66 SEC GIS 보통점검","2024-09-25 09:00","2024-09-25 18:00","2024-09-25 09:00","2024-09-25 18:00","연속"]
[486,"대전세종충남","천안","아산인주#1 T/L","아산, 인주S/S 154kV 아산-인주#1T/L 보호배전반 대체","(즉시가압불가)아산, 인주S/S 154kV 아산-인주#1T/L 보호배전반 대체","2024-09-07 09:00","2024-09-09 18:00","취소","취소","연속"]
[487,"대전세종충남","천안","아산예산#1 T/L","154kV 아산-예산T/L 추락방지장치 설치공사","[즉시가압가능]154kV 아산-예산T/L No. 1 ~ 42 추락방지장치 설치 [병가철탑] (상단)아산-온양#2T/L No.2~14 / (하단)아산-예산#1T/L No.1~13 [병행작업] 조류착지방지장치 설치","2024-09-02 07:00","2024-09-06 18:00","취소","취소","매일"]
[488,"대전세종충남","천안","아산온양#2 T/L","154kV 아산-온양T/L 추락방지장치 설치공사","[즉시가압가능]154kV 아산-온양T/L No. 1 ~ 56 추락방지장치 설치 [병가철탑] (상단)아산-온양#2T/L No.2~14 / (하단)아산-예산#1T/L No.1~13 [병행작업] 조류착지방지장치 설치","2024-09-05 07:00","2024-09-12 18:00","취소","취소","매일"]
[489,"대전세종충남","천안","아산예산#1 T/L","아산, 예산S/S 154kV 아산-예산#1T/L 보호반 대체","(즉시가압불가)아산, 예산S/S 154kV 아산-예산#1T/L 보호반 대체","2024-09-10 09:00","2024-09-13 18:00","2024-09-10 09:00","2024-09-13 18:00","연속"]
[490,"대전세종충남","천안","아산예산#2 T/L","아산, 예산S/S 154kV 아산-예산#2T/L 보호반 대체","(즉시가압불가)아산, 예산S/S 154kV 아산-예산#2T/L 보호반 대체","2024-09-24 09:00","2024-09-27 18:00","취소","취소","연속"]
[491,"대전세종충남","천안","아산합덕#1 T/L","154kV 아산-합덕T/L 추락방지장치 설치공사","[즉시가압가능]154kV 아산-합덕T/L No. 1 ~ 53 추락방지장치 설치 [병가철탑](상단)신서산-아산#1No.74~113,(하단)아산-합덕#1No.13~52 [병행작업] 조류착지방지장치 설치","2024-09-24 07:00","2024-10-02 18:00","2024-09-24 07:00","2024-10-02 18:00","매일"]
[492,"대전세종충남","천안","온양풍세#2 T/L","154kV 아산-온양T/L 추락방지장치 설치공사","[즉시가압가능]154kV 아산-온양T/L No. 51 ~ 56 추락방지장치 설치 [병가철탑] (상단)아산-온양#2T/L No.51~56 / (하단)온양-풍세#2T/L No.1~6 [병행작업] 조류착지방지장치 설치","2024-09-12 07:00","2024-09-12 18:00","2024-09-12 07:00","2024-09-12 18:00","매일"]
[493,"대전세종충남","천안","아산인주#1 T/L","154kV 아산-인주T/L 추락방지장치 설치공사","[즉시가압가능]154kV 아산-인주T/L No. 1 ~ 25 추락방지장치 설치 [병행작업] 조류착지방지장치 설치","2024-09-07 07:00","2024-09-08 18:00","취소","취소","매일"]
[494,"대전세종충남","천안","인주불당#1 T/L","인주S/S 154kV 인주-불당#1, 2T/L CB 개폐타임측정","(즉시가압가능)인주S/S 154kV 인주-불당#1, 2T/L CB 개폐타임측정","2024-09-04 09:00","2024-09-04 14:00","취소","취소","연속"]
[495,"대전세종충남","천안","아산인주#2 T/L","345kV 북당진-신탕정T/L(1구간) OPGW 시설공사","[OPGW 신설] : 760m - 154kV 아산인주 #2T/L(인주불당#1T/L) 측 No.32 ~ 345kV 북당진신탕정T/L No.47 [OPGW 철거] : - 154kV 아산인주 #2T/L(인주불당#1T/L) 측 No.31 ~ 345kV 북당진신탕정T/L No.48","2024-09-16 07:00","2024-09-17 18:00","2024-09-16 07:00","2024-09-17 18:00","연속"]
[496,"대전세종충남","천안","아산인주#2 T/L","154kV 아산-인주 등 2개 T/L 송전선로 정비공사","1. 구 간 ○ 아산-인주T/L 정비(1.264km) 기28호∼기32호 가선(연긴선, 공중이동) ○ 인주-불당T/L 정비(0.828km) 기3∼기5호 조립,가선(연긴선, 공중이동) ○ 아산-인주T/L 기설32호 철탑보강 2. 지 지 물 ○ 신설 : 설치 2기[가철탑 1기(4C), 산형강 철탑 1기(2C), ○ 철거 : 철거 4기[가철탑","2024-09-28 07:00","2024-10-09 18:00","2024-09-28 07:00","2024-10-09 18:00","연속"]
[497,"대전세종충남","천안","아산인주#1 T/L","345kV 북당진-신탕정T/L(1구간) OPGW 시설공사","[OPGW 신설] : 760m - 154kV 아산인주 #1T/L(인주불당#2T/L) 측 No.32 ~ 345kV 북당진신탕정T/L No.47","2024-09-14 07:00","2024-09-15 18:00","2024-09-14 07:00","2024-09-15 18:00","연속"]
[498,"대전세종충남","천안","인주불당#2 T/L","345kV 북당진-신탕정T/L(1구간) OPGW 시설공사","[OPGW 신설] : 760m - 154kV 아산인주 #1T/L(인주불당#2T/L) 측 No.32 ~ 345kV 북당진신탕정T/L No.47","2024-09-14 07:00","2024-09-15 18:00","2024-09-14 07:00","2024-09-15 18:00","연속"]
[499,"대전세종충남","천안","인주불당#1 T/L","345kV 북당진-신탕정T/L(1구간) OPGW 시설공사","[OPGW 신설] : 760m - 154kV 아산인주 #2T/L(인주불당#1T/L) 측 No.32 ~ 345kV 북당진신탕정T/L No.47 [OPGW 철거] : - 154kV 아산인주 #2T/L(인주불당#1T/L) 측 No.31 ~ 345kV 북당진신탕정T/L No.48","2024-09-16 07:00","2024-09-17 18:00","2024-09-16 07:00","2024-09-17 18:00","연속"]
[500,"대전세종충남","천안","인주불당#1 T/L","154kV 아산-인주 등 2개 T/L 송전선로 정비공사","1. 구 간 ○ 아산-인주T/L 정비(1.264km) 기28호∼기32호 가선(연긴선, 공중이동) ○ 인주-불당T/L 정비(0.828km) 기3∼기5호 조립,가선(연긴선, 공중이동) ○ 아산-인주T/L 기설32호 철탑보강 2. 지 지 물 ○ 신설 : 설치 2기[가철탑 1기(4C), 산형강 철탑 1기(2C), ○ 철거 : 철거 4기[가철탑","2024-09-28 07:00","2024-10-04 18:00","2024-09-28 07:00","2024-10-04 18:00","연속"]
[501,"대전세종충남","천안","인주불당#2 T/L","인주S/S 154kV 인주-불당#1, 2T/L CB 개폐타임측정","(즉시가압가능)인주S/S 154kV 인주-불당#1, 2T/L CB 개폐타임측정","2024-09-04 14:00","2024-09-04 18:00","2024-09-04 14:00","2024-09-04 18:00","연속"]
[502,"대전세종충남","천안","장재천안#2 T/L","장재, 천안S/S 154kV 장재-천안#2T/L 보호반 대체","(즉시가압불가)장재, 천안S/S 154kV 장재-천안#2T/L 보호반 대체","2024-09-10 09:00","2024-09-13 18:00","취소","취소","연속"]
[503,"대전세종충남","천안","장재천안#1 T/L","장재, 천안S/S 154kV 장재-천안#1T/L 보호반 대체","(즉시가압불가)장재, 천안S/S 154kV 장재-천안#1T/L 보호반 대체","2024-09-20 09:00","2024-09-23 18:00","취소","취소","연속"]
[504,"대전세종충남","천안","장재천안#1 T/L","154kV 장재-천안T/L 추락방지장치 설치공사","[즉시가압가능,주말작업없음]154kV 장재-천안T/L No. 1 ~ 14 추락방지장치 설치 [병행작업] 조류착지방지장치 설치","2024-09-20 07:00","2024-09-23 18:00","취소","취소","매일"]
[505,"대전세종충남","천안","천안전의#2 T/L","천안S/S 154kV 천안-전의#2T/L GIS 보통점검","(즉시가압가능)천안S/S 154kV 천안-전의#2T/L GIS 보통점검","2024-09-24 09:00","2024-09-24 18:00","2024-09-24 09:00","2024-09-24 18:00","연속"]
[506,"대전세종충남","천안","신탕정탕정#2 T/L","탕정S/S 154kV 신탕정-탕정#2T/L CB 개폐타임측정","(즉시가압가능)탕정S/S 154kV 신탕정-탕정#2T/L CB 개폐타임측정","2024-09-09 14:00","2024-09-09 18:00","취소","취소","연속"]
[507,"대전세종충남","천안","신탕정탕정#1 T/L","탕정S/S 154kV 신탕정-탕정#1T/L CB 개폐타임측정","(즉시가압가능)탕정S/S 154kV 신탕정-탕정#1T/L CB 개폐타임측정","2024-09-09 09:00","2024-09-09 14:00","취소","취소","연속"]
[508,"대전세종충남","천안","풍세장재#2 T/L","154kV 풍세-장재T/L 추락방지장치 설치공사","[즉시가압가능]154kV 풍세-장재T/L No. 18 ~ 23 추락방지장치 설치 [병가철탑](상단)풍세-장재#2No.18~26,(하단)장재-천안#1No.1~9 [병행작업] 조류착지방지장치 설치","2024-09-23 07:00","2024-09-23 18:00","2024-09-23 07:00","2024-09-23 18:00","매일"]
[509,"대전세종충남","청양","관창보령CC T/L","청양P/O 변전전문 발주공사(관창 관복)","청양P/O 변전전문 발주공사 - 관창S/S 관창-보령복합T/L GIS 정밀점검 (즉시가압 불가)","2024-09-10 09:00","2024-09-12 18:00","2024-09-10 09:00","2024-09-12 18:00","연속"]
[510,"대전세종충남","청양","보령TP보령CC T/L","보령T/P 154kV GIS 내장화공사(보령복합T/L)","보령T/P 154kV GIS 내장화공사(보령복합T/L)","2024-09-19 09:00","2024-09-27 18:00","2024-09-19 09:00","2024-09-27 18:00","연속"]
[511,"대전세종충남","청양","청양신풍#2 T/L","[송전] 신풍-공주#1T/L의 피뢰기 설치공사 중 병가로 인한 휴전","[송전] 신풍-공주#1T/L의 피뢰기 설치공사 중 병가로 인한 휴전 - 병가구간 : 154kV 신풍-공주 No.1-1 ~ 1-14 ※ 요청 시 1시간 이내 가압 가능","2024-09-23 07:00","2024-09-25 18:00","2024-09-23 07:00","2024-09-25 18:00","매일"]
[512,"대전세종충남","청양","옥산장항#1 T/L","청양P/O 변전전문 발주공사(장항 옥장#1)","청양P/O 변전전문 발주공사 - 옥산-장항#1T/L GIS 정밀점검(양단) (즉시가압 불가)","2024-09-30 09:00","2024-10-04 18:00","2024-09-30 09:00","2024-10-04 18:00","연속"]
[513,"전북","군산","군공S/S #65 BUS","군산P/O 170kV GIS 정밀점검공사(무부하 가압용)","군공S/S #4M.Tr 1차 GIS 정밀점검공사","2024-09-03 17:30","2024-09-03 18:00","2024-09-03 17:30","2024-09-03 18:00","연속"]
[514,"전북","군산","군공소룡#2 T/L","군산P/O 170kV GIS 정밀점검공사(무부하 가압용)","군공S/S #4M.Tr 1차 GIS 정밀점검공사","2024-09-03 17:30","2024-09-03 18:00","2024-09-03 17:30","2024-09-03 18:00","연속"]
[515,"전북","군산","군산S/S #66 BUS","군산S/S 170kV GIS 대체공사(6차)","- 군산S/S 군산-영등#2T/L 대체","2024-09-27 18:00","2024-10-04 17:00","2024-09-27 18:00","2024-10-04 17:00","연속"]
[516,"전북","군산","군산S/S #61 BUS","군산S/S 170kV GIS 대체공사(6차)","- 군산S/S 군산-영등#2T/L 대체","2024-09-21 18:00","2024-09-27 18:00","2024-09-21 18:00","2024-09-27 18:00","연속"]
[517,"전북","군산","군산영등#2 T/L","군산S/S 170kV GIS 대체공사(6차)","- 군산S/S 군산-영등#2T/L 대체","2024-09-19 09:00","2024-10-04 18:00","2024-09-19 09:00","2024-10-04 18:00","연속"]
[518,"전북","군산","군산S/S #66 BUS","군산S/S 170kV GIS 대체공사(6차)","- 군산S/S 군산-영등#2T/L 대체","2024-09-19 09:00","2024-09-21 18:00","2024-09-19 09:00","2024-09-21 18:00","연속"]
[519,"전북","군산","함열낭산#1 T/L","154kV 낭산-함열T/L 초기점검","□ 공사개요 □ 초기점검 : 철탑 12기 □ 철탑 및 전선 접속개소 점검","2024-09-30 07:00","2024-10-01 18:00","2024-09-30 07:00","2024-10-01 18:00","매일"]
[520,"전북","군산","내초군장#2 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2024-09-25 08:00","2024-09-26 18:00","2024-09-25 08:00","2024-09-26 18:00","연속"]
[521,"전북","군산","내초군장#1 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2024-09-23 08:00","2024-09-24 18:00","2024-09-23 08:00","2024-09-24 18:00","연속"]
[522,"전북","군산","서군산소룡#1 T/L","154kV 서군산-소룡#1T/L 구형 공법 EBA 구조개선 공사","일진제 구형 공법 EBA 구조개선 공사","2024-09-23 09:00","2024-09-29 18:00","2024-09-02 09:00","2024-09-08 18:00","연속"]
[523,"전북","군산","영등팔봉#2 T/L","군산P/O 170kV GIS 정밀점검공사(무부하가압용)","영등S/S #3M.Tr 1차 GIS 정밀점검공사","2024-09-13 17:30","2024-09-13 18:00","2024-09-13 17:30","2024-09-13 18:00","연속"]
[524,"전북","군산","영등낭산#2 T/L","군산 P/O LA, CVT 점검공사","영등S/S 영등-낭산#2T/L LA A,B,C상 보통점검","2024-09-10 15:00","2024-09-10 22:00","2024-09-10 15:00","2024-09-10 22:00","연속"]
[525,"전북","군산","영등낭산#1 T/L","군산 P/O LA, CVT 점검공사","영등S/S 영등-낭산#1T/L LA A,B,C상 보통점검","2024-09-09 15:00","2024-09-09 22:00","2024-09-09 15:00","2024-09-09 22:00","연속"]
[526,"전북","군산","영등S/S #60 BUS","군산P/O 170kV GIS 정밀점검공사(무부하가압용)","영등S/S #3M.Tr 1차 GIS 정밀점검공사","2024-09-13 17:30","2024-09-13 18:00","2024-09-13 17:30","2024-09-13 18:00","연속"]
[527,"전북","군산","팔봉S/S #60 BUS","군산P/O 170kV GIS 정밀점검공사(무부하가압용)","팔봉S/S #3M.Tr 1차 GIS 정밀점검공사","2024-09-11 17:30","2024-09-11 18:00","2024-09-11 17:30","2024-09-11 18:00","연속"]
[528,"전북","군산","영등팔봉#1 T/L","군산P/O 170kV GIS 정밀점검공사(무부하가압용)","팔봉S/S #3M.Tr 1차 GIS 정밀점검공사","2024-09-11 17:30","2024-09-11 18:00","2024-09-11 17:30","2024-09-11 18:00","연속"]
[529,"전북","군산","은진함열#2 T/L","24년 군산 P/O 장기사용 배전반 교체공사","154kV 함열-은진#2T/L 보호반 대체(9.09~9.11, 연속)","2024-09-23 09:00","2024-09-25 18:00","2024-09-23 09:00","2024-09-25 18:00","연속"]
[530,"전북","군산","은진함열#1 T/L","24년 군산 P/O 장기사용 배전반 교체공사","154kV 함열-은진#1T/L 보호반 대체(9.04~9.06, 연속)","2024-09-19 09:00","2024-09-21 18:00","2024-09-19 09:00","2024-09-21 18:00","연속"]
[531,"전북","김제","고창홍농 T/L","154kV 정주-고창 등 2개T/L 선종교체공사","- 공사구간 :154kV 정주-고창T/L No.92~95(병가구간) - 전력선 교체 : 44.076C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, 현수클램프 등]","2024-09-01 08:00","2024-09-03 17:00","2024-09-20 08:00","2024-09-22 17:00","매일"]
[532,"전북","김제","김제S/S #1 EM.Tr CB","2024년 김제 FR-ESS 정밀점검","2024년 김제 FR-ESS 정밀점검","2024-09-02 09:00","2024-09-11 18:00","2024-09-02 09:00","2024-09-11 18:00","연속"]
[533,"전북","김제","담양김제 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2024-09-12 08:00","2024-09-12 18:00","2024-09-12 08:00","2024-09-12 18:00","연속"]
[534,"전북","김제","김제칠보HP T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2024-09-11 08:00","2024-09-11 18:00","2024-09-11 08:00","2024-09-11 18:00","연속"]
[535,"전북","김제","김제부안#1 T/L","'24~'25년 송전협력회사 공사(피뢰기 설치공사)","단위공사명 : 154kV 김제-부안 등 4개T/L 피뢰기 설치공사 작업 내용 - 선 로 명 : 154kV 김제-부안#2T/L - 작업구간 : 1 ~ 65호(65기, 195세트)","2024-09-19 08:00","2024-09-27 18:00","2024-09-19 08:00","2024-09-27 18:00","매일"]
[536,"전북","김제","정주부안#2 T/L","154kV 동부안S/S 건설공사","○ 154kV M.Tr × 3Bank ○ 170kV GIS × 11CCT, 25.8kV E-GIS × 21CCT ○ SA운영시스템 등 부대설비 공사 × 1식","2024-09-05 09:00","2024-09-12 18:00","2024-09-05 09:00","2024-09-13 18:00","연속"]
[537,"전북","김제","서고창S/S 해상풍력T/L CB","서고창S/S 154kV 해상풍력T/L 차단기 정밀점검(9.2~3, 연속)","서고창S/S 154kV 해상풍력T/L 차단기 정밀점검(9.2~3, 연속)","2024-09-02 09:00","2024-09-03 18:00","2024-09-02 09:00","2024-09-03 18:00","연속"]
[538,"전북","김제","신김제동전주#2 T/L","154kV 완산분기T/L 건설공사","- 작업내용 : #2T/L 가선로 구성 - 위 치 : 전주시 완산구 석구동 일원 - 규 모 : ACSR410㎟ × 2B × 4C(0.81km, 지지물 4기)","2024-09-30 07:00","2024-10-04 18:00","2024-09-30 07:00","2024-10-04 18:00","연속"]
[539,"전북","김제","신김제동전주#1 T/L","154kV 완산분기T/L 건설공사","- 작업내용 : #1T/L 가선로 구성 - 위 치 : 전주시 완산구 석구동 일원 - 규 모 : ACSR410㎟ × 2B × 4C(0.81km, 지지물 4기)","2024-09-23 07:00","2024-09-27 18:00","2024-09-23 07:00","2024-09-27 18:00","연속"]
[540,"전북","김제","정공담양 T/L","김제P/O 기타설비 대체공사","정공S/S 정공-담양T/L LA 대체","2024-09-04 09:00","2024-09-04 18:00","2024-09-04 09:00","2024-09-04 18:00","연속"]
[541,"전북","김제","정주고창#1 T/L","154kV 소성S/S 및 분기T/L 건설공사","○ 송전분야[작업기간 : 9.30 ~ 10.04 (5일간 연속)] - 작업내용 : 변전소 인입, 전선이동, 가철탑 철거 등 ○ 변전분야[작업기간 : 10.07 ~ 10.11 (5일간 연속)] - 작업내용 : 보호반 이설·설치, 대국시험, 변전기기 무부하 가압 및 PD측정, 실부하 가압","2024-09-30 07:00","2024-10-11 18:00","2024-10-04 07:00","2024-10-15 18:00","연속"]
[542,"전북","김제","정주고창#2 T/L","154kV 소성분기T/L 건설공사","○ 공사구간 : 154kV 정주-고창T/L 28~29호 ~ (신설) 154kV 소성S/S ○ 공사규모 : 관형지지물 2기, 가철탑 1기 ○ 선로길이 : 약 0.422km","2024-09-27 07:00","2024-09-28 18:00","2024-10-03 07:00","2024-10-04 18:00","연속"]
[543,"전북","직할","동전주태평#1 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2024-09-05 08:00","2024-09-06 18:00","2024-09-05 08:00","2024-09-06 18:00","연속"]
[544,"전북","직할","동전주태평#2 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2024-09-09 08:00","2024-09-10 18:00","2024-09-09 08:00","2024-09-10 18:00","연속"]
[545,"전북","직할","무주용담수력 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사","○ 154kV 무주-용담T/L 수평 추락방지시설 설치 : No.1~51~104","2024-09-30 09:00","2024-10-06 18:00","2024-09-30 09:00","2024-10-06 18:00","매일"]
[546,"전북","직할","왕궁봉동#2 T/L","24년 전북직할 170GIS 정밀점검 공사","봉동변전소 6133GIS CB, 1DS 무부하가압","2024-09-24 16:00","2024-09-24 17:00","2024-09-24 16:00","2024-09-24 17:00","연속"]
[547,"전북","직할","왕궁봉동#2 T/L","24년 전북직할 170GIS 정밀점검 공사","봉동변전소 6133GIS 2DS 무부하가압","2024-09-26 16:00","2024-09-26 16:30","2024-09-26 16:00","2024-09-26 16:30","연속"]
[548,"전북","직할","북전주봉동#2 T/L","24년 전북직할 170GIS 정밀점검 공사","봉동변전소 6233GIS CB+1DS 무부하가압","2024-09-10 16:00","2024-09-10 17:00","2024-09-10 16:00","2024-09-10 17:00","연속"]
[549,"전북","직할","북전주봉동#2 T/L","24년 전북직할 170GIS 정밀점검 공사","봉동변전소 6233GIS 2DS 무부하가압","2024-09-12 16:00","2024-09-12 16:30","2024-09-12 16:00","2024-09-12 16:30","연속"]
[550,"전북","직할","서곡태평#1 T/L","24년 전북직할 170GIS 정밀점검 공사","서곡변전소 6444GIS CB 무부하가압","2024-09-20 16:00","2024-09-20 16:30","2024-09-20 16:00","2024-09-20 16:30","연속"]
[551,"전북","직할","진안장수#1 T/L","24년 전북직할 170GIS 정밀점검 공사","장수변전소 6133GIS 2DS 무부하가압","2024-09-05 16:00","2024-09-05 16:30","2024-09-05 16:00","2024-09-05 16:30","연속"]
[552,"전북","직할","진안장수#1 T/L","24년 전북직할 170GIS 정밀점검 공사","장수변전소 6133GIS CB+1DS 무부하가압","2024-09-03 16:00","2024-09-03 17:00","2024-09-03 16:00","2024-09-03 17:00","연속"]
[553,"전북","직할","진안장수#2 T/L","진안-장수#2T/L 송전선로 보호반 대체공사","진안-장수#2T/L 송전선로 보호반 대체공사","2024-09-30 09:00","2024-10-04 18:00","2024-09-30 09:00","2024-10-04 18:00","연속"]
[554,"전북","직할","진안장수#1 T/L","진안-장수#1T/L 송전선로 보호반 대체공사","진안-장수#1T/L 송전선로 보호반 대체공사","2024-09-23 09:00","2024-09-27 18:00","2024-09-23 09:00","2024-09-27 18:00","연속"]
[555,"전북","직할","탄소전주#1 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2024-09-03 08:00","2024-09-03 18:00","2024-09-03 08:00","2024-09-03 18:00","연속"]
[556,"전북","직할","탄소전주#2 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2024-09-04 08:00","2024-09-04 18:00","2024-09-04 08:00","2024-09-04 18:00","연속"]
[557,"광주전남","강진","강진장흥#1 T/L","세니온제 보호배전반 일제 성능개선","세니온제 보호배전반 일제 성능개선 - 불량소자(MAX488교체), F/W업데이트 - (보호제어팀) Trip time 측정 및 연동시험","2024-09-06 09:00","2024-09-06 14:00","2024-09-06 09:00","2024-09-06 14:00","연속"]
[558,"광주전남","강진","강진남창#2 T/L","세니온제 보호배전반 일제 성능개선","세니온제 보호배전반 일제 성능개선 - 불량소자(MAX488교체), F/W업데이트 - (보호제어팀) Trip time 측정 및 연동시험","2024-09-13 09:00","2024-09-13 18:00","2024-09-13 09:00","2024-09-13 18:00","연속"]
[559,"광주전남","강진","강진장흥#2 T/L","세니온제 보호배전반 일제 성능개선","세니온제 보호배전반 일제 성능개선 - 불량소자(MAX488교체), F/W업데이트 - (보호제어팀) Trip time 측정 및 연동시험","2024-09-06 14:00","2024-09-06 18:00","2024-09-06 14:00","2024-09-06 18:00","연속"]
[560,"광주전남","강진","남창완도CS T/L","154kV 남창S/S GIS화 공사","남창S/S 남창-완도CS T/L GIS SA화 - 제작사 IED CID 입력 - 제어케이블 철거 및 광케이블 결선 - T/L 및 T/L PRO 조작, 경보, 인터록 시험 등","2024-09-30 09:00","2024-10-02 18:00","2024-09-30 09:00","2024-10-02 18:00","연속"]
[561,"광주전남","강진","남창해남CS#1 T/L","2024-2025년 강진전력지사 변전협력회사 공사","170kV GIS 초기점검","2024-09-12 09:00","2024-09-12 14:00","2024-09-12 09:00","2024-09-12 14:00","연속"]
[562,"광주전남","강진","남창해남CS#2 T/L","2024-2025년 강진전력지사 변전협력회사 공사","170kV GIS 하자점검","2024-09-12 14:00","2024-09-12 18:00","2024-09-12 14:00","2024-09-12 18:00","연속"]
[563,"광주전남","강진","보성벌교 T/L","'24년 강진전력지사 170kV 이상 GIS 보통점검 공사","'24년 강진전력지사 170kV 이상 GIS 보통점검 공사","2024-09-02 08:00","2024-09-02 13:00","취 소","취 소","연속"]
[564,"광주전남","강진","장흥보성 T/L","'24년 강진전력지사 170kV 이상 GIS 보통점검 공사","'24년 강진전력지사 170kV 이상 GIS 보통점검 공사","2024-09-02 13:00","2024-09-03 13:00","2024-09-02 13:00","2024-09-03 13:00","매일"]
[565,"광주전남","강진","보성벌교 T/L","2024년 가공송전 순시점검 위탁공사","보성-벌교T/L 64~121호 정밀점검","2024-09-23 08:00","2024-10-04 18:00","2024-09-23 08:00","2024-10-04 18:00","매일"]
[566,"광주전남","강진","삼호화원#2 T/L","154kV 삼호-화원 지중T/L 복도체화 건설공사","XLPE 2,000sq 2C-6.8km (포설 15구간, 접속 32개소) 휴일 작업 없음","2024-09-25 09:00","2024-10-27 18:00","취 소","취 소","연속"]
[567,"광주전남","강진","신강진해남#1 T/L","'24년 하반기 강진전력지사 효성제 170kV GIS 개선","170kV GIS 개선","2024-09-25 14:00","2024-09-25 18:00","취 소","취 소","연속"]
[568,"광주전남","강진","완도완도CS T/L","세니온제 보호배전반 일제 성능개선","세니온제 보호배전반 일제 성능개선 - 불량소자(max488 교체). f/w 업데이트","2024-09-20 09:00","2024-09-20 18:00","2024-09-20 09:00","2024-09-20 18:00","연속"]
[569,"광주전남","강진","남창완도 T/L","'24년 강진전력지사 170kV 이상 GIS 보통점검 공사","'24년 강진전력지사 170kV 이상 GIS 보통점검 공사","2024-09-11 10:00","2024-09-11 18:00","2024-09-11 10:00","2024-09-11 18:00","매일"]
[570,"광주전남","강진","장흥벌교 T/L","'24년 강진전력지사 170kV 이상 GIS 보통점검 공사","'24년 강진전력지사 170kV 이상 GIS 보통점검 공사","2024-09-03 13:00","2024-09-03 18:00","취 소","취 소","연속"]
[571,"광주전남","강진","강진장흥#2 T/L","22~23년 철탑 추락방지장치 설치공사","22~23년 철탑 추락방지장치 설치공사 공사대상 : 강진-장흥#2 T/L 54~58호 5기(장흥-벌교 병가부분)","2024-09-10 07:00","2024-09-10 18:00","2024-09-10 07:00","2024-09-10 18:00","연속"]
[572,"광주전남","강진","화원진도#2 T/L","22~23년 철탑 추락방지장치 설치공사","22~23년 철탑 추락방지장치 설치공사 공사대상 : 화원-진도#2 T/L 40~78호 39기","2024-09-26 07:00","2024-10-01 18:00","취소","취소","매일"]
[573,"광주전남","강진","화원진도#1 T/L","'24년 강진전력지사 170kV 이상 GIS 보통점검 공사","'24년 강진전력지사 170kV 이상 GIS 보통점검 공사","2024-09-05 13:00","2024-09-06 18:00","2024-09-05 13:00","2024-09-06 18:00","매일"]
[574,"광주전남","강진","화원진도#2 T/L","'24년 강진전력지사 170kV 이상 GIS 보통점검 공사","'24년 강진전력지사 170kV 이상 GIS 보통점검 공사","2024-09-04 13:00","2024-09-05 13:00","취 소","취 소","매일"]
[575,"광주전남","강진","해남진도#1 T/L","22~23년 철탑 추락방지장치 설치공사","22~23년 철탑 추락방지장치 설치공사 공사대상 : 해남-진도#1 T/L 1,4~8,16~74,87~95, 102~104 78기","2024-09-11 07:00","2024-09-25 18:00","취 소","취 소","매일"]
[576,"광주전남","강진","해남진도#1 T/L","'24년 강진전력지사 170kV 이상 GIS 보통점검 공사","'24년 강진전력지사 170kV 이상 GIS 보통점검 공사","2024-09-26 08:00","2024-09-26 13:00","취 소","취 소","연속"]
[577,"광주전남","강진","해남진도#1 T/L","'24년 하반기 강진전력지사 효성제 170kV GIS 개선","170kV GIS 개선","2024-09-26 10:00","2024-09-27 14:00","2024-09-26 10:00","2024-09-27 14:00","매일"]
[578,"광주전남","강진","해남진도#2 T/L","'24년 하반기 강진전력지사 효성제 170kV GIS 개선","170kV GIS 개선","2024-09-26 14:00","2024-09-27 18:00","2024-09-26 14:00","2024-09-27 18:00","매일"]
[579,"광주전남","강진","해남진도#1 T/L","'24년 강진전력지사 170kV 이상 GIS 보통점검 공사","'24년 강진전력지사 170kV 이상 GIS 보통점검 공사","2024-09-26 13:00","2024-09-26 18:00","취 소","취 소","연속"]
[580,"광주전남","광주","계림승주#2 T/L","2024~25년 광주전력지사 송전협력회사공사(추락방지)","154kV 계림-승주T/L 추락방지장치설치공사 No.2~107호 중 84기","2024-09-30 07:00","2024-10-04 18:00","2024-09-30 07:00","2024-10-04 18:00","매일"]
[581,"광주전남","광주","계림승주#1 T/L","2024~25년 광주전력지사 송전협력회사공사(추락방지)","154kV 계림-승주T/L 추락방지장치설치공사 No.2~107호 중 84기","2024-09-23 07:00","2024-09-27 18:00","2024-09-23 07:00","2024-09-27 18:00","매일"]
[582,"광주전남","광주","계림S/S SEC CB 65660","24년 광주전력지사 170kV 이상 GIS 보통점검","- 170kV GIS 보통점검","2024-09-13 09:00","2024-09-13 18:00","2024-09-13 09:00","2024-09-13 18:00","연속"]
[583,"광주전남","광주","신광주계림#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","신광주, 계림S/S 신광주-계림#2T/L PNL 대체","2024-09-09 09:00","2024-09-13 18:00","2024-09-09 09:00","2024-09-13 18:00","연속"]
[584,"광주전남","광주","신광주계림#1 T/L","'24~25년 광주전력지사 변전협력회사 공사","신광주S/S 신광주-계림 #1T/L LA 보통점검","2024-09-27 09:00","2024-09-27 18:00","2024-09-27 09:00","2024-09-27 18:00","연속"]
[585,"광주전남","광주","곡성구례#1 T/L","'24~25년 광주전력지사 변전협력회사 공사","곡성S/S 곡성-구례 #1T/L LA 및 CVT 보통점검","2024-09-11 09:00","2024-09-11 18:00","취 소","취 소","연속"]
[586,"광주전남","광주","담양S/S SEC CB 60610","24년 광주전력지사 170kV 이상 GIS 보통점검","- 170kV GIS 보통점검","2024-09-26 09:00","2024-09-26 18:00","2024-09-26 09:00","2024-09-26 18:00","연속"]
[587,"광주전남","광주","담양S/S SEC CB 65660","24년 광주전력지사 170kV 이상 GIS 보통점검","- 170kV GIS 보통점검","2024-09-27 09:00","2024-09-27 18:00","2024-09-27 09:00","2024-09-27 18:00","연속"]
[588,"광주전남","광주","신광주순창#2 T/L","'24~25년 광주전력지사 변전협력회사 공사","신광주S/S 신광주-순창 #2T/L LA 보통점검","2024-09-30 09:00","2024-09-30 18:00","취소","취소","연속"]
[589,"광주전남","광주","신광주일곡#2 T/L","'24~25년 광주전력지사 변전협력회사 공사","신광주S/S 신광주-일곡 #2T/L CVT 보통점검","2024-09-26 14:00","2024-09-26 18:00","2024-09-26 14:00","2024-09-26 18:00","연속"]
[590,"광주전남","광주","신광주일곡#1 T/L","'24~25년 광주전력지사 변전협력회사 공사","신광주S/S 신광주-일곡 #1T/L CVT 보통점검","2024-09-26 09:00","2024-09-26 14:00","2024-09-26 09:00","2024-09-26 14:00","연속"]
[591,"광주전남","광주","신화순화순#2 T/L","2024~25년 광주전력지사 송전협력회사공사(추락방지)","154kV 신화순-화순T/L 추락방지장치설치공사 No.1~57호 중 53기","2024-09-13 07:00","2024-09-20 18:00","2024-09-13 07:00","2024-09-20 18:00","매일"]
[592,"광주전남","광주","신화순화순#1 T/L","2024~25년 광주전력지사 송전협력회사공사(추락방지)","154kV 신화순-화순T/L 추락방지장치설치공사 No.1~57호 중 53기","2024-09-09 07:00","2024-09-12 18:00","2024-09-09 07:00","2024-09-12 18:00","매일"]
[593,"광주전남","광주","화순승주#1 T/L","'24~25년 광주전력지사 변전협력회사 공사","화순S/S 화순-승주 #1T/L LA 및 CVT 보통점검","2024-09-12 09:00","2024-09-12 18:00","2024-09-12 09:00","2024-09-12 18:00","연속"]
[594,"광주전남","목포","안좌S/S 스마트팜#2T/L CB","관내 효성제 170kV GIS(스프링 Type) 메커니즘 부품 교체 시행","관내 효성제 170kV GIS(스프링 Type) 메커니즘 부품 불량관련 교체","2024-09-10 09:00","2024-09-10 18:00","2024-09-10 09:00","2024-09-10 18:00","연속"]
[595,"광주전남","목포","안좌S/S 스마트팜#1T/L CB","관내 효성제 170kV GIS(스프링 Type) 메커니즘 부품 교체 시행","관내 효성제 170kV GIS(스프링 Type) 메커니즘 부품 불량관련 교체","2024-09-10 09:00","2024-09-10 18:00","2024-09-10 09:00","2024-09-10 18:00","연속"]
[596,"광주전남","목포","엄다목포#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","엄다-목포#1T/L GIS 교체작업","2024-07-23 09:00","2024-09-10 18:00","2024-09-06 09:00","2024-09-27 18:00","연속"]
[597,"광주전남","목포","나주엄다#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","엄다-목포#2T/L, BUS-TIE 교체분 GIS 무부하가압용","2024-09-04 14:00","2024-09-05 15:00","2024-09-11 14:00","2024-09-12 14:00","연속"]
[598,"광주전남","목포","엄다무안햇빛#2 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","154kV BUS-TIE 교체로 인한 #1BUS 모선절체용","2024-09-05 14:00","2024-09-05 14:30","2024-09-19 14:00","2024-09-19 14:30","연속"]
[599,"광주전남","목포","엄다S/S #2 BUS","엄다S/S 154kV 이하 장기사용 GIS 교체공사","엄다-목포#2T/L, BUS-TIE #2BUS, #2DS측 설치","2024-07-04 14:00","2024-07-22 10:00","2024-08-29 14:00","2024-09-27 14:00","연속"]
[600,"광주전남","목포","나주엄다#2 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","154kV BUS-TIE 교체로 인한 #1BUS 모선절체용","2024-09-05 14:00","2024-09-05 14:30","2024-09-19 14:00","2024-09-19 14:30","연속"]
[601,"광주전남","목포","엄다무안햇빛#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","154kV BUS-TIE 교체로 인한 #1BUS 모선절체용","2024-09-05 14:00","2024-09-05 14:30","2024-09-19 14:00","2024-09-19 14:30","연속"]
[602,"광주전남","목포","엄다목포#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","154kV BUS-TIE 교체로 인한 #1BUS 모선절체용","2024-09-05 14:00","2024-09-05 14:30","2024-09-19 14:00","2024-09-19 14:30","연속"]
[603,"광주전남","목포","운남S/S 신흥풍력T/L CB","관내 효성제 170kV GIS(스프링 Type) 메커니즘 부품 교체 시행","관내 효성제 170kV GIS(스프링 Type) 메커니즘 부품 불량관련 교체","2024-09-11 09:00","2024-09-11 18:00","2024-09-11 09:00","2024-09-11 18:00","연속"]
[604,"광주전남","순천","곡성구례#1 T/L","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","구례S/S 곡성-구례#1T/L GIS 보통점검","2024-09-12 09:00","2024-09-12 18:00","취 소","취 소","연속"]
[605,"광주전남","순천","곡성구례#2 T/L","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","구례S/S 곡성-구례#2T/L GIS 보통점검","2024-09-13 09:00","2024-09-13 18:00","취 소","취 소","연속"]
[606,"광주전남","순천","장흥벌교 T/L","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","벌교S/S 장흥-벌교T/L GIS 보통점검","2024-09-09 14:00","2024-09-09 18:00","취 소","취 소","연속"]
[607,"광주전남","순천","서순천벌교#2 T/L","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","벌교S/S 서순천-벌교#2T/L GIS 보통점검","2024-09-10 17:00","2024-09-10 22:00","2024-09-10 17:00","2024-09-10 22:00","연속"]
[608,"광주전남","순천","보성벌교 T/L","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","벌교S/S 보성-벌교T/L GIS 보통점검","2024-09-09 09:00","2024-09-09 14:00","취 소","취 소","연속"]
[609,"광주전남","순천","서순천벌교#1 T/L","벌교S/S 170kV GIS 순도불량 조치 공사","벌교S/S 170kV GIS 순도불량 조치 공사(17:00 ~ 10:00 매일 휴전)","2024-09-02 17:00","2024-09-06 10:00","2024-09-02 17:00","2024-09-06 10:00","매일"]
[610,"광주전남","순천","여수소라#1 T/L","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","소라S/S 여수-소라#1T/L GIS 보통점검","2024-09-23 09:00","2024-09-23 18:00","2024-09-23 09:00","2024-09-23 18:00","연속"]
[611,"광주전남","순천","순천승주#1 T/L","154kV 송전선로보호반 보호계전기 성능개선(세니온제)","154kV 송전선로보호반 보호계전기 성능개선(세니온제)","2024-09-10 09:00","2024-09-10 18:00","2024-09-10 09:00","2024-09-10 18:00","연속"]
[612,"광주전남","순천","순천승주#2 T/L","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","순천S/S 순천-승주#2T/L GIS 보통점검","2024-09-25 09:00","2024-09-25 18:00","2024-09-25 09:00","2024-09-25 18:00","연속"]
[613,"광주전남","순천","순천율촌#2 T/L","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","순천S/S 순천-율촌#2T/L GIS 보통점검","2024-09-26 09:00","2024-09-26 18:00","2024-09-26 09:00","2024-09-26 18:00","연속"]
[614,"광주전남","순천","승주서순천 T/L","154kV 승주-서순천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-09-27 07:00","2024-09-27 18:00","2024-09-27 07:00","2024-09-27 18:00","연속"]
[615,"광주전남","순천","여수TP여천#2 T/L","154kV 여수TP-여천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-09-04 07:00","2024-09-05 18:00","2024-09-04 07:00","2024-09-05 18:00","매일"]
[616,"광주전남","순천","여수T/P #65 BUS","GS 칼텍스 여수#2T/L #2DS 가스누기해소 공사","#2DS 가스누기해소 공사","2024-09-03 09:00","2024-09-04 18:00","취소","취소","연속"]
[617,"광주전남","순천","여수TP여천#1 T/L","154kV 여수TP-여천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-09-02 07:00","2024-09-03 18:00","2024-09-02 07:00","2024-09-03 18:00","매일"]
[618,"광주전남","순천","여수T/P CB 6200","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-09-27 15:40","2024-09-27 16:00","취소","취소","연속"]
[619,"광주전남","순천","여수T/P SEC CB 60610","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-09-27 15:20","2024-09-27 15:40","취소","취소","연속"]
[620,"광주전남","순천","여수T/P SEC CB 65660","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-09-27 15:00","2024-09-27 15:20","취소","취소","연속"]
[621,"광주전남","순천","호남TP여수TP#2 T/L","154kV 호남TP-여수TPT/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-09-26 07:00","2024-09-26 18:00","2024-09-26 07:00","2024-09-26 18:00","연속"]
[622,"광주전남","순천","호남TP여수TP#1 T/L","154kV 호남TP-여수TPT/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-09-25 07:00","2024-09-25 18:00","2024-09-25 07:00","2024-09-25 18:00","연속"]
[623,"광주전남","순천","여수T/P CB 6100","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-09-13 15:40","2024-09-13 16:00","취소","취소","연속"]
[624,"광주전남","순천","여수T/P SEC CB 60610","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-09-13 15:20","2024-09-13 15:40","취소","취소","연속"]
[625,"광주전남","순천","여수T/P SEC CB 65660","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-09-13 15:00","2024-09-13 15:20","취소","취소","연속"]
[626,"광주전남","순천","여수TP화치#2 T/L","24-25년 순천전력지사 변전회사 총액공사","여수T/P-화치#2T/L PNL 대체(즉시가압불가)","2024-09-09 09:00","2024-09-13 18:00","2024-09-09 09:00","2024-09-13 18:00","연속"]
[627,"광주전남","순천","여수TP용성#2 T/L","154kV 여수TP-용성T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-09-09 07:00","2024-09-09 13:00","2024-09-09 07:00","2024-09-09 13:00","연속"]
[628,"광주전남","순천","여수TP용성#1 T/L","154kV 여수TP-용성T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-09-06 07:00","2024-09-06 13:00","취 소","취 소","연속"]
[629,"광주전남","순천","여수T/P #66 BUS","24-25년 순천전력지사 변전정비 총액공사","#2DS 가스누기 조치","2024-09-05 09:00","2024-09-06 18:00","취 소","취 소","연속"]
[630,"광주전남","순천","용성여수산단#2 T/L","154kV 용성-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-09-09 07:00","2024-09-10 18:00","2024-09-09 07:00","2024-09-10 18:00","매일"]
[631,"광주전남","순천","용성여수산단#1 T/L","154kV 용성-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-09-06 07:00","2024-09-06 13:00","2024-09-06 07:00","2024-09-06 13:00","연속"]
[632,"광주전남","순천","여수TP용성#1 T/L","용성S/S 여수TP-용성#1T/L GIS 불량 유압력계 교체","GIS 불량 유압력계 교체","2024-09-05 09:00","2024-09-06 18:00","2024-09-05 09:00","2024-09-06 18:00","연속"]
[633,"광주전남","순천","순천율촌#1 T/L","24-25년 순천전력지사 변전회사 총액공사","순천-율촌#1T/L GIS #1,2DS 가스누기(즉시가압 불가)","2024-09-23 09:00","2024-09-25 18:00","2024-09-23 09:00","2024-09-25 18:00","연속"]
[634,"광주전남","순천","율촌여수산단#2 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-09-23 07:00","2024-09-24 18:00","취 소","취 소","매일"]
[635,"광주전남","순천","율촌여수산단#1 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-09-19 07:00","2024-09-20 18:00","취 소","취 소","매일"]
[636,"광주전남","순천","율촌민자#2 T/L","154kV 율촌민자T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-09-12 07:00","2024-09-12 18:00","2024-09-12 07:00","2024-09-12 18:00","연속"]
[637,"광주전남","순천","율촌민자#1 T/L","154kV 율촌민자T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-09-11 07:00","2024-09-11 18:00","2024-09-11 07:00","2024-09-11 18:00","연속"]
[638,"광주전남","순천","율촌S/S #61 BUS","24-25년 순천전력지사 변전회사 총액공사","순천-율촌#1T/L GIS #1,2DS 가스누기(즉시가압 불가)","2024-09-23 09:00","2024-09-24 14:00","2024-09-23 09:00","2024-09-24 14:00","연속"]
[639,"광주전남","순천","율촌S/S #66 BUS","24-25년 순천전력지사 변전회사 총액공사","순천-율촌#1T/L GIS #1,2DS 가스누기(즉시가압 불가)","2024-09-24 14:00","2024-09-25 18:00","2024-09-24 14:00","2024-09-25 18:00","연속"]
[640,"광주전남","순천","율촌여수산단#2 T/L","24-25년 순천전력지사 변전회사 총액공사","율촌-여수산단#2T/L GIS #1DS 가스누기(즉시가압 불가)","2024-09-30 09:00","2024-10-01 18:00","취 소","취 소","연속"]
[641,"광주전남","순천","율촌S/S #60 BUS","24-25년 순천전력지사 변전회사 총액공사","율촌-여수산단#2T/L GIS #1DS 가스누기(즉시가압 불가)","2024-09-30 09:00","2024-10-01 18:00","2024-09-30 09:00","2024-10-01 18:00","연속"]
[642,"광주전남","순천","태금하동화력 T/L","효성제 170kv gis 부품 교체 시행","효성제 170kv gis 부품 교체 시행(즉시가압 불가)","2024-09-04 09:00","2024-09-04 18:00","2024-09-04 09:00","2024-09-04 18:00","연속"]
[643,"광주전남","직할","남광주금천#1 T/L","`24년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 보통점검","2024-09-06 09:00","2024-09-06 18:00","2024-09-06 09:00","2024-09-06 18:00","연속"]
[644,"광주전남","직할","매월화정#2 T/L","세니온제 계전기 성능개선 시행(매월, 화정)","세니온제 계전기 성능개선 시행(매월, 화정) -매월-화정#2T/L","2024-09-04 09:00","2024-09-04 16:00","2024-09-04 09:00","2024-09-04 16:00","연속"]
[645,"광주전남","직할","비아하남#2 T/L","`24년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 보통점검","2024-09-20 09:00","2024-09-20 18:00","2024-09-20 09:00","2024-09-20 18:00","연속"]
[646,"광주전남","직할","비아하남#1 T/L","`24년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 보통점검","2024-09-19 09:00","2024-09-19 18:00","2024-09-19 09:00","2024-09-19 18:00","연속"]
[647,"광주전남","직할","수완흑석#1 T/L","`24년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검 및 보통점검","2024-09-09 09:00","2024-09-11 18:00","2024-09-09 09:00","2024-09-11 18:00","연속"]
[648,"광주전남","직할","농성화정#1 T/L","2024~2025년 광주전남본부 직할 변전협력회사 공사","170kV GIS Annunciator 전원 공급용 컨버터 교체","2024-09-04 09:00","2024-09-04 18:00","2024-09-04 09:00","2024-09-04 18:00","연속"]
[649,"광주전남","직할","하남흑석#2 T/L","`24년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검","2024-09-25 14:00","2024-09-27 18:00","2024-09-25 14:00","2024-09-27 18:00","연속"]
[650,"광주전남","직할","하남흑석#1 T/L","`24년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검","2024-09-23 09:00","2024-09-25 14:00","2024-09-23 09:00","2024-09-25 14:00","연속"]
[651,"광주전남","직할","수완흑석#2 T/L","`24년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 보통점검","2024-09-12 09:00","2024-09-12 18:00","2024-09-12 09:00","2024-09-12 18:00","연속"]
[652,"대구","경산","범물남대구#1 T/L","154kV 범물-남대구T/L 지중화 공사","154kV 범물-남대구 #1 T/L 지중화 공사 - 케이블 철거, 설치 및 접속","2024-09-23 09:00","2024-10-16 18:00","2024-09-23 09:00","2024-10-16 18:00","연속"]
[653,"대구","달성","창녕구지#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 창녕-구지T/L 수평 추락방지장치 설치공사(안전확보)","2024-09-16 13:00","2024-09-19 18:00","2024-09-16 13:00","2024-09-19 18:00","연속"]
[654,"대구","달성","창녕구지#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 창녕-구지T/L 수평 추락방지장치 설치공사(안전확보)","2024-09-13 07:00","2024-09-16 13:00","2024-09-13 07:00","2024-09-16 13:00","연속"]
[655,"대구","달성","고령논공#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 고령-논공T/L 수평 추락방지장치 설치공사","2024-09-26 07:00","2024-09-27 18:00","2024-09-26 07:00","2024-09-27 18:00","연속"]
[656,"대구","달성","고령논공#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 고령-논공T/L 수평 추락방지장치 설치공사","2024-09-24 07:00","2024-09-25 18:00","2024-09-24 07:00","2024-09-25 18:00","연속"]
[657,"대구","달성","대구범물#1 T/L","2024~25년 대구본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치공사","2024-09-09 07:30","2024-09-13 18:00","2024-09-09 07:30","2024-09-13 18:00","연속"]
[658,"대구","달성","대구봉덕#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 대구-봉덕T/L 수평 추락방지장치 설치공사","2024-09-05 07:00","2024-09-09 18:00","2024-09-05 07:00","2024-09-09 18:00","연속"]
[659,"대구","달성","대구봉덕#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 대구-봉덕T/L 수평 추락방지장치 설치공사","2024-09-02 07:00","2024-09-04 18:00","2024-09-02 07:00","2024-09-04 18:00","연속"]
[660,"대구","달성","상인봉덕#1 T/L","154kV 상인-봉덕 지중T/L 지장송전선로 이설공사","154kV 상인-봉덕 지중T/L 지장송전선로 이설공사","2024-09-23 09:00","2024-10-17 18:00","2024-09-23 09:00","2024-10-17 18:00","연속"]
[661,"대구","달성","논공현풍#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 논공-현풍T/L 수평 추락방지장치 설치공사","2024-09-10 07:00","2024-09-11 18:00","2024-09-10 07:00","2024-09-11 18:00","연속"]
[662,"대구","달성","논공현풍#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 논공-현풍T/L 수평 추락방지장치 설치공사","2024-09-20 07:00","2024-09-27 18:00","2024-09-20 07:00","2024-09-27 18:00","연속"]
[663,"대구","직할","공평서침산 T/L","연공부 이상부 보수작업","154kV 공평-서침산T/L J/B#2 B상 연공부 발열부 보수","2024-09-05 10:00","2024-09-05 18:00","2024-09-05 10:00","2024-09-05 18:00","연속"]
[664,"대구","직할","남대구동인#2 T/L","동인S/S 남대구-동인 #2T/L 보통점검","동인S/S 남대구-동인 #2T/L 보통점검","2024-09-09 09:30","2024-09-09 18:00","2024-09-09 09:30","2024-09-09 18:00","연속"]
[665,"대구","칠곡","어모김천#2 T/L","김천SA 어모-김천SA#2T/L 677 GIS 하자점검","김천SA 어모-김천SA#2T/L 677 GIS 하자점검","2024-09-13 09:30","2024-09-13 14:00","2024-09-13 09:30","2024-09-13 14:00","연속"]
[666,"대구","칠곡","농소김천#2 T/L","154kV 김천S/S 현대화공사","○ 송전선로 인출변경","2024-09-07 08:00","2024-09-09 18:00","2024-09-07 08:00","2024-09-09 18:00","연속"]
[667,"대구","칠곡","농소김천#1 T/L","김천S/S 657 GCB 조작시험, LA, PT 보통점검","김천S/S 657 GCB 조작시험, LA, PT 보통점검","2024-09-21 09:30","2024-09-21 18:00","2024-09-21 09:30","2024-09-21 18:00","연속"]
[668,"대구","포항","청하영덕#1 T/L","345kV 영포 외 15개 T/L 추락방지장치 설치 등 송전정비공사","154kV 청하-영덕#1T/L 수평추락방지장치 설치","2024-09-23 07:00","2024-09-24 18:00","2024-09-23 07:00","2024-09-24 18:00","매일"]
[669,"대구","포항","신영일청하#1 T/L","345kV 영포 외 15개 T/L 추락방지장치 설치 등 송전정비공사","154kV 신영일-청하#1T/L 수평추락방지장치 설치","2024-09-09 07:00","2024-09-13 18:00","2024-09-09 07:00","2024-09-13 18:00","매일"]
[670,"대구","포항","청하영덕#2 T/L","345kV 영포 외 15개 T/L 추락방지장치 설치 등 송전정비공사","154kV 청하-영덕#2T/L 수평추락방지장치 설치","2024-09-09 07:00","2024-09-10 18:00","2024-09-09 07:00","2024-09-10 18:00","매일"]
[671,"경북","구미","선산고아#2 T/L","선산S/S 154kV 구미 CC T/L 신규수용공사","서부발전 - 관로포설공사 1식 - 기타 부대작업 1식 한국전력 - GIS 설치 x 2 CCT - 기타 부대작업 1식","2024-09-02 09:00","2024-09-09 18:00","취소","취소","연속"]
[672,"경북","구미","선산고아#1 T/L","선산S/S 154kV 구미 CC T/L 신규수용공사","서부발전 - 관로포설공사 1식 - 기타 부대작업 1식 한국전력 - GIS 설치 x 2 CCT - 기타 부대작업 1식","2024-09-02 09:00","2024-10-10 18:00","2024-09-02 09:00","2024-10-10 18:00","연속"]
[673,"경북","구미","선산청리#2 T/L","345kV 서대구-선산 등 6개T/L 피뢰기 및 추락방지시설 설치공사","154kV 선산-청리#2T/L 피뢰기 설치","2024-09-10 07:00","2024-09-26 18:00","2024-09-10 07:00","2024-09-26 18:00","매일"]
[674,"경북","구미","청리상주#1 T/L","345kV 서대구-선산 등 6개T/L 피뢰기 및 추락방지시설 설치공사","154kV 청리-상주#1T/L 피뢰기 설치","2024-09-19 07:00","2024-09-26 18:00","2024-09-19 07:00","2024-09-26 18:00","매일"]
[675,"경북","구미","선산청리#1 T/L","2024-2025년 구미전력지사 송전협력회사 공사","154kV 선산-청리#1T/L 성능저하 애자교체공사(1기 No.105)","2024-09-27 07:30","2024-09-27 18:00","2024-09-27 07:30","2024-09-27 18:00","연속"]
[676,"경북","구미","청리상주#2 T/L","2024-2025년 구미전력지사 송전협력회사 공사","154kV 청리-상주#2T/L 성능저하 애자교체공사(3기 No.22, 30, 38)","2024-09-27 07:30","2024-09-27 18:00","2024-09-27 07:30","2024-09-27 18:00","연속"]
[677,"경북","구미","선산S/S #62 BUS"," 선산S/S 154kV 구미 CC T/L 신규수용공사"," 선산S/S 154kV 구미 CC T/L 신규수용공사","2024-09-30 09:00","2024-10-10 18:00","2024-09-30 09:00","2024-10-10 18:00","연속"]
[678,"경북","영주","문경단양 T/L","154kV 단양T/L 피뢰기 및 수직추락방지장치 설치","154kV 단양T/L 피뢰기 및 수직추락방지장치 설치","2024-09-28 08:00","2024-09-29 17:00","취소","취소","매일"]
[679,"경북","영주","영주봉화#2 T/L","2023~24년 경북본부 지중송전설비 위탁정비공사","○ 내용 : 154kV 영주-봉화#1,2T/L 피뢰기 열화진단(6상) - 작업장소 : C/T#81","2024-09-04 13:00","2024-09-04 18:00","취소","취소","연속"]
[680,"경북","영주","신영주예천#1 T/L","154kV 신영주-예천T/L 수평추락방지장치 설치","154kV 신영주-예천T/L 수평추락방지장치 설치 (154kV 예천-점촌 병가구간)","2024-09-02 08:00","2024-09-03 17:00","2024-09-21 08:00","2024-09-22 17:00","매일"]
[681,"경북","영주","동상주점촌#1 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2024-09-30 09:00","2024-10-02 14:00","2024-09-30 09:00","2024-10-02 14:00","연속"]
[682,"경북","영주","예천점촌#2 T/L","154kV 예천-점촌T/L 피뢰기 및 수평추락방지장치 설치","154kV 예천-점촌T/L 피뢰기 및 수평추락방지장치 설치","2024-09-23 08:00","2024-10-01 17:00","취소","취소","매일"]
[683,"경북","영주","점촌단양 T/L","154kV 단양T/L 수평추락방지장치 및 피뢰기 설치","154kV 단양T/L 수평추락방지장치 및 피뢰기 설치","2024-09-06 08:00","2024-09-14 17:00","2024-09-25 08:00","2024-10-03 17:00","매일"]
[684,"경북","영주","예천점촌#1 T/L","154kV 예천-점촌T/L 피뢰기 및 수평추락방지장치 설치","154kV 예천-점촌T/L 피뢰기 및 수평추락방지장치 설치","2024-09-02 08:00","2024-09-10 17:00","2024-09-21 08:00","2024-09-29T17:00:00","매일"]
[685,"경북","영주","점촌단양 T/L","154kV 단양T/L 수평추락방지장치 및 피뢰기 설치","154kV 단양T/L 수평추락방지장치 및 피뢰기 설치","취소","취소","취소","취소","매일"]
[686,"경북","직할","동안동임하HP T/L","154kV 안동-동안동T/L 용량증대 선종교체공사","154kV 안동-동안동T/L 용량증대 선종교체공사 - 154kV 안동-동안동#2T/L No.18~23호 선종교체 (병가구간 안전확보)","2024-09-23 07:00","2024-09-26 18:00","2024-09-23 07:00","2024-09-26 18:00","연속"]
[687,"경북","직할","안동동안동#1 T/L","`24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검","2024-09-19 09:00","2024-09-19 18:00","2024-09-19 09:00","2024-09-19 18:00","연속"]
[688,"경북","직할","안동안동HP T/L","`24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검","2024-09-30 09:00","2024-09-30 18:00","2024-09-30 09:00","2024-09-30 18:00","연속"]
[689,"경북","직할","안동동안동#2 T/L","`24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검","2024-09-20 09:00","2024-09-20 18:00","2024-09-20 09:00","2024-09-20 18:00","연속"]
[690,"경북","직할","안동동안동#1 T/L","154kV 안동-동안동T/L 용량증대 선종교체공사","154kV 안동-동안동T/L 용량증대 선종교체공사 - 154kV 안동-동안동#2T/L No.18~23호 선종교체(안전 확보 차)","2024-09-23 07:00","2024-09-26 18:00","2024-09-23 07:00","2024-09-26 18:00","연속"]
[691,"경북","직할","안동동안동#2 T/L","154kV 안동-동안동T/L 용량증대 선종교체공사","154kV 안동-동안동T/L 용량증대 선종교체공사 - 154kV 안동-동안동#2T/L No.18~23호 선종교체","2024-09-23 07:00","2024-09-26 18:00","2024-09-23 07:00","2024-09-26 18:00","연속"]
[692,"경북","직할","안동풍산 T/L","154㎸ 안동-풍산T/L 29~31호간 지장이설공사(요청자 직접시행)","1. 대상선로 : 154㎸ 안동-풍산T/L 2. 공사구간 : No.29 ~ No.31(HSTACIR/AW 240㎟(단도체), 1회선) 3. 공사내역 : 송전선로 설치(신설 No.30-1) 및 전력선 가선","2024-09-02 08:00","2024-09-06 18:00","2024-09-09 08:00","2024-09-13 18:00","연속"]
[693,"경북","직할","봉화현종산풍력 T/L","`24~25년 경북본부 직할 변전협력회사 공사","현종산S/Y 봉화-현종산T/L GIS 보통점검","2024-09-12 09:00","2024-09-12 18:00","2024-09-12 09:00","2024-09-12 18:00","연속"]
[694,"경북","직할","현종산풍력평해#2 T/L","`24~25년 경북본부 직할 변전협력회사 공사","현종산S/Y 현종산풍력-평해#2T/L GIS 조작점검","2024-09-13 09:00","2024-09-13 18:00","2024-09-13 09:00","2024-09-13 18:00","연속"]
[695,"경북","직할","현종산풍력평해#1 T/L","`24~25년 경북본부 직할 변전협력회사 공사","현종산S/Y 현종산풍력-평해#1T/L GIS 조작점검","2024-09-12 09:00","2024-09-12 18:00","2024-09-12 09:00","2024-09-12 18:00","연속"]
[696,"경북","직할","울진현종산풍력 T/L","`24~25년 경북본부 직할 변전협력회사 공사","현종산S/Y 울진-현종산풍력T/L GIS 보통점검 울진S/S 울진-현종산풍력T/L GIS 초기점검","2024-09-03 09:00","2024-09-04 18:00","2024-09-03 09:00","2024-09-04 18:00","매일"]
[697,"부산울산","동부산","노포정관#1 T/L","2024-2025년 동부산 가공송전협력회사 공사","폴리머점퍼지지애자 설치","2024-09-25 07:00","2024-09-27 18:00","2024-09-25 09:00","2024-09-27 18:00","연속"]
[698,"부산울산","동부산","노포정관#2 T/L","노포,정관S/S 노포-정관#2T/L 보호PNL 대체작업","노포,정관S/S 노포-정관#2T/L 보호PNL 대체작업 병행)정관S/S 637GIS 보통점검","2024-09-30 09:00","2024-10-02 18:00","2024-09-30 09:00","2024-10-02 18:00","연속"]
[699,"부산울산","동부산","수영정보#2 T/L","정보S/S 6233 GIS 정밀점검 시험가압 선로","정보S/S 6233 GIS 정밀점검 시험가압 선로","2024-09-21 17:00","2024-09-21 18:00","2024-09-21 17:00","2024-09-21 18:00","연속"]
[700,"부산울산","동부산","수영정보#1 T/L","정보S/S 627 GIS 정밀점검","정보S/S 627 GIS 정밀점검","2024-09-07 09:00","2024-09-08 18:00","2024-09-07 09:00","2024-09-08 18:00","연속"]
[701,"부산울산","동부산","수영정보#1 T/L","정보S/S 6133 GIS 정밀점검 시험가압 선로","정보S/S 6133 GIS 정밀점검 시험가압 선로","2024-09-14 17:00","2024-09-14 18:00","2024-09-14 17:00","2024-09-14 18:00","연속"]
[702,"부산울산","동부산","정보대연 T/L","정보S/S 657 GIS 정밀점검","정보S/S 657 GIS 정밀점검","2024-09-28 09:00","2024-09-29 18:00","2024-09-28 09:00","2024-09-29 18:00","연속"]
[703,"부산울산","북부산","개금범천#1 T/L","개금S/S 154kV GIS교체공사","개금범천#1T/L GIS교체","2024-09-23 09:00","2024-10-09 18:00","2024-09-23 09:00","2024-10-09 18:00","연속"]
[704,"부산울산","북부산","학장개금#2 T/L","24-25년 북부산전력지사 변전협력회사 공사","개금S/S 학장-개금#2T/L GIS 조작시험","2024-09-13 09:00","2024-09-13 18:00","2024-09-13 09:00","2024-09-13 18:00","연속"]
[705,"부산울산","북부산","북부산구포#3 T/L","24년 하반기 북부산전력지사 154kV GIS 정밀점검공사","북부산S/S 154kV 북부산-구포#3T/L GIS 정밀점검","2024-09-30 09:00","2024-10-01 18:00","2024-09-30 09:00","2024-10-01 18:00","연속"]
[706,"부산울산","북부산","물금S/S SEC CB 60610","24-25년 북부산전력지사 변전협력회사 공사","물금S/S 154kV 60-61-0GIS 단자대 보수 작업","2024-09-19 14:00","2024-09-19 18:00","2024-09-19 14:00","2024-09-19 18:00","연속"]
[707,"부산울산","북부산","물금삼랑진PP#2 T/L","24년 하반기 북부산전력지사 154kV GIS 정밀점검공사","물금S/S 154kV 6433 GIS 정밀점검 -시험가압선로 : 물금-삼랑진PP#2T/L, #66BUS","2024-09-27 17:00","2024-09-27 18:00","2024-09-27 17:00","2024-09-27 18:00","연속"]
[708,"부산울산","북부산","물금S/S CB 6100","24-25년 북부산전력지사 변전협력회사 공사","물금S/S 154kV 6100 B/T GIS 조작시험","2024-09-19 09:00","2024-09-19 14:00","2024-09-19 09:00","2024-09-19 14:00","연속"]
[709,"부산울산","북부산","언양산막#2 T/L","24년 하반기 북부산전력지사 154kV GIS 정밀점검공사","산막S/S 154kV #2M.Tr 1차 6233 GIS 정밀점검 -시험가압선로 : 언양-산막#2T/L, #2BUS","2024-09-22 17:00","2024-09-22 18:00","2024-09-22 17:00","2024-09-22 18:00","연속"]
[710,"부산울산","북부산","언양산막#1 T/L","24년 하반기 북부산전력지사 154kV GIS 정밀점검공사","산막S/S 154kV 6100B/T GIS 정밀점검 -시험가압선로 : 언양-산막#1T/L, #1BUS","2024-09-24 17:00","2024-09-24 18:00","2024-09-24 17:00","2024-09-24 18:00","연속"]
[711,"부산울산","북부산","양산삼랑진PP T/L","154kV 북부산-삼랑진 등 2개T/L 철탑보강 등 대체공사","154kV 양산-삼랑진T/L 아킹혼, SB 댐퍼 설치","2024-09-11 08:00","2024-09-12 18:00","2024-09-11 08:00","2024-09-12 18:00","연속"]
[712,"부산울산","북부산","물금삼랑진PP#2 T/L","154kV 북부산-삼랑진 등 2개T/L 철탑보강 등 대체공사","154kV 물금-삼랑진#2T/L 애자련 1련교체, 압축인류클램프 설치","2024-09-07 08:00","2024-09-10 18:00","2024-09-07 08:00","2024-09-10 18:00","연속"]
[713,"부산울산","북부산","물금삼랑진PP#1 T/L","154kV 북부산-삼랑진 등 2개T/L 철탑보강 등 대체공사","154kV 물금-삼랑진#1T/L 아킹혼 , SB 댐퍼설치, 애자련 1련교체","2024-09-07 08:00","2024-09-09 18:00","2024-09-07 08:00","2024-09-09 18:00","연속"]
[714,"부산울산","북부산","서부산엄궁#1 T/L","24년 하반기 북부산전력지사 154kV GIS 정밀점검공사","엄궁S/S 154kV 서부산-엄궁#1T/L GIS 정밀점검","2024-09-23 09:00","2024-09-24 18:00","2024-09-23 09:00","2024-09-24 18:00","연속"]
[715,"부산울산","북부산","모라엄궁#2 T/L","24년 하반기 북부산전력지사 154kV GIS 정밀점검공사","엄궁S/S 154kV 모라-엄궁#2T/L GIS 정밀점검","2024-09-19 09:00","2024-09-20 18:00","2024-09-19 09:00","2024-09-20 18:00","연속"]
[716,"부산울산","북부산","서부산엄궁#2 T/L","24년 하반기 북부산전력지사 154kV GIS 정밀점검공사","엄궁S/S 154kV 서부산-엄궁#2T/L GIS 정밀점검","2024-09-25 09:00","2024-09-26 18:00","2024-09-25 09:00","2024-09-26 18:00","연속"]
[717,"부산울산","북부산","호포물금 T/L","24년 하반기 북부산전력지사 154kV GIS 정밀점검공사","호포S/S 6333GIS 주접점 교체 -시험가압선로 : 호포S/S 154kV #1BUS, 호포-물금T/L","2024-09-12 18:00","2024-09-13 18:00","2024-09-12 18:00","2024-09-13 18:00","연속"]
[718,"부산울산","서부산","녹산S/S #1 BUS","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○1차분 (미음-녹산#2T/L, #2M.Tr 1차 대체, PT&ES설치) - 미음-녹산#2T/L, #2M.Tr 1차 1DS, CB 철거 및 신규GIS 설치 - 모선 PT&ES 설치 - #1BUS 시험가압 (1DS 개방상태) 24시간","2024-09-23 09:00","2024-10-05 18:00","2024-09-23 09:00","2024-10-05 18:00","연속"]
[719,"부산울산","서부산","미음녹산#1 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○1차분 (미음-녹산#2T/L, #2M.Tr 1차 대체, PT&ES설치) - 미음-녹산#2T/L, #2M.Tr 1차 1DS, CB 철거 및 신규GIS 설치 - 모선 PT&ES 설치 - #1BUS 시험가압 (1DS 개방상태) 24시간 - 안전거리이격확보(미음-녹산#1T/L) 미음-녹산#2T/L 부싱제거","2024-09-23 09:00","2024-09-26 18:00","2024-09-23 09:00","2024-09-26 18:00","연속"]
[720,"부산울산","서부산","신녹산녹산#1 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○1차분 (미음-녹산#2T/L, #2M.Tr 1차 대체, PT&ES설치) - 미음-녹산#2T/L, #2M.Tr 1차 2DS 철거 및 꼬깔처리 - #2BUS 시험가압 (2DS 개방상태) 1시간 - 시험가압선로 (신녹산-녹산#1T/L)","2024-09-13 17:00","2024-09-13 18:00","2024-09-13 17:00","2024-09-13 18:00","연속"]
[721,"부산울산","서부산","녹산S/S #2 BUS","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○1차분 (미음-녹산#2T/L, #2M.Tr 1차 대체, PT&ES설치) - 미음-녹산#2T/L, #2M.Tr 1차 2DS 철거 및 꼬깔처리","2024-09-10 09:00","2024-09-13 18:00","2024-09-10 09:00","2024-09-13 18:00","연속"]
[722,"부산울산","서부산","미음녹산#2 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 - 1차분 (미음-녹산 #2T/L, #2M.Tr 1차 대체, PT&ES 설치)","2024-09-10 09:00","2024-10-19 18:00","2024-09-10 09:00","2024-10-19 18:00","연속"]
[723,"부산울산","서부산","서부산다대#2 T/L","2024년 서부산전력지사 154kV GIS 정밀점검공사","다대S/S 154kV 서부산-다대#2T/L GIS 정밀점검","2024-09-11 09:00","2024-09-12 18:00","2024-09-11 09:00","2024-09-12 18:00","연속"]
[724,"부산울산","서부산","서부산다대#1 T/L","2024년 서부산전력지사 154kV GIS 정밀점검공사","다대S/S 154kV 서부산-다대#1T/L GIS 정밀점검","2024-09-09 09:00","2024-09-10 18:00","2024-09-09 09:00","2024-09-10 18:00","연속"]
[725,"부산울산","서부산","서부산S/S #61 BUS","2024년 서부산전력지사 154kV GIS 정밀점검공사","서부산S/S 154kV #61M.TR 1차 GIS 정밀점검(시험가압 모선)","2024-09-08 17:00","2024-09-08 18:00","2024-09-08 17:00","2024-09-08 18:00","연속"]
[726,"부산울산","서부산","용원녹공#2 T/L","용원S/S 용원-녹공#2T/L GIS 휴전작업","용원S/S 용원-녹공#2T/L GIS 휴전작업 (기계적 접점 보수)","2024-09-26 09:00","2024-09-26 18:00","2024-09-26 09:00","2024-09-26 18:00","연속"]
[727,"부산울산","울산","동울산효문#1 T/L","24년 울산전력지사 변전협력회사 총액공사","-동울산측 LA 대체 - 효문측 LA 보통점검","2024-09-19 09:00","2024-09-19 18:00","2024-09-19 09:00","2024-09-19 18:00","연속"]
[728,"부산울산","울산","동울산효문#2 T/L","24년 울산전력지사 변전협력회사 총액공사","-동울산측 LA 대체 - 효문측 LA 보통점검","2024-09-20 09:00","2024-09-20 18:00","2024-09-20 09:00","2024-09-20 18:00","연속"]
[729,"부산울산","울산","두왕울산#1 T/L","2024년 가공송전 순시점검 위탁공사","[초기점검] 154kV 신울산-두왕#1T/L 7호 154kV 두왕-울산#1T/L 1,2,10,11,12호","2024-09-10 08:00","2024-09-11 18:00","2024-09-10 08:00","2024-09-11 18:00","연속"]
[730,"부산울산","울산","신울산두왕#1 T/L","2024년 가공송전 순시점검 위탁공사","[초기점검] 154kV 신울산-두왕#1T/L 7호 154kV 두왕-울산#1T/L 1,2,10,11,12호","2024-09-10 08:00","2024-09-11 18:00","2024-09-10 08:00","2024-09-11 18:00","연속"]
[731,"부산울산","울산","신울산두왕#2 T/L","2024년 가공송전 순시점검 위탁공사","[초기점검] 154kV 신울산-두왕#2T/L 7호 154kV 두왕-울산#2T/L 1,2,10,11,12호","2024-09-12 08:00","2024-09-13 18:00","2024-09-12 08:00","2024-09-13 18:00","연속"]
[732,"부산울산","울산","두왕울산#2 T/L","2024년 가공송전 순시점검 위탁공사","[초기점검] 154kV 신울산-두왕#2T/L 7호 154kV 두왕-울산#2T/L 1,2,10,11,12호","2024-09-12 08:00","2024-09-13 18:00","2024-09-12 08:00","2024-09-13 18:00","연속"]
[733,"부산울산","울산","신울산매암#2 T/L","대한전선제 열경화공법 EBG 보강공사","EBG 해체, 가스채취밸브 설치, 스프링유닛 점검 등","2024-09-25 09:00","2024-09-26 18:00","2024-09-25 09:00","2024-09-26 18:00","연속"]
[734,"부산울산","울산","신울산매암#3 T/L","대한전선제 열경화공법 EBG 보강공사","EBG 해체, 가스채취밸브 설치, 스프링유닛 점검 등","2024-09-27 09:00","2024-09-28 18:00","2024-09-27 09:00","2024-09-28 18:00","연속"]
[735,"부산울산","울산","신울산매암#1 T/L","대한전선제 열경화공법 EBG 보강공사","EBG 해체, 가스채취밸브 설치, 스프링유닛 점검 등","2024-09-23 09:00","2024-09-24 18:00","2024-09-23 09:00","2024-09-24 18:00","연속"]
[736,"부산울산","울산","반천언양#1 T/L","대한전선제 열경화공법 EBG 보강공사","EBG 해체, 가스채취밸브 설치, 스프링유닛 점검 등","2024-09-09 09:00","2024-09-10 18:00","2024-09-09 09:00","2024-09-10 18:00","연속"]
[737,"부산울산","울산","언양산막#1 T/L","154kV 석계분기T/L 건설공사","지지물 : 154kV 산형강철탑 5기 전력선 : ACSR 410 * 2B * 4C","2024-09-30 07:00","2024-10-02 18:00","2024-09-30 07:00","2024-10-02 18:00","연속"]
[738,"부산울산","울산","반천언양#2 T/L","대한전선제 열경화공법 EBG 보강공사","EBG 해체, 가스채취밸브 설치, 스프링유닛 점검 등","2024-09-11 09:00","2024-09-12 18:00","2024-09-11 09:00","2024-09-12 18:00","연속"]
[739,"부산울산","울산","용연울산TP#2 T/L","24년 울산전력지사 변전협력회사 총액공사","-용연측 LA 대체 -용연측 GIS 보통점검 -효성제GIS 조작부 발청보수","2024-09-25 09:00","2024-09-25 18:00","2024-09-25 09:00","2024-09-25 18:00","연속"]
[740,"부산울산","울산","남울산용연#1 T/L","24년 울산전력지사 변전협력회사 총액공사","-용연측 LA 대체 -용연측 효성제 조작부 발청보수","2024-09-23 09:00","2024-09-23 18:00","2024-09-23 09:00","2024-09-23 18:00","연속"]
[741,"부산울산","울산","용연울산TP#1 T/L","24년 울산전력지사 변전협력회사 총액공사","-용연측 LA 대체","2024-09-24 09:00","2024-09-24 18:00","2024-09-24 09:00","2024-09-24 18:00","연속"]
[742,"부산울산","울산","울산매암 T/L","세니온제 송전선로 보호반 계전기 성능개선","세니온제 송전선로 보호반 계전기 성능개선","2024-09-20 09:00","2024-09-20 18:00","2024-09-20 09:00","2024-09-20 18:00","연속"]
[743,"부산울산","울산","울주S/S CB 6200","24년 울산전력지사 변전협력회사 총액공사","- 154kV 62-67 모선보호반 대체","2024-09-23 09:00","2024-09-27 18:00","2024-09-23 09:00","2024-09-27 18:00","연속"]
[744,"부산울산","울산","온산처용#1 T/L","24년 울산전력지사 변전협력회사 총액공사","-차단기 동작시험 -LA 보통점검","2024-09-12 09:00","2024-09-12 18:00","2024-09-12 09:00","2024-09-12 18:00","연속"]
[745,"부산울산","울산","온산처용#2 T/L","24년 울산전력지사 변전협력회사 총액공사","-차단기 동작시험 -LA 보통점검","2024-09-13 09:00","2024-09-13 18:00","2024-09-13 09:00","2024-09-13 18:00","연속"]
[746,"부산울산","울산","효문방어진 T/L","24년 울산전력지사 변전협력회사 총액공사","- 방어진측 LA 대체 -효문측 LA 보통점검","2024-09-28 09:00","2024-09-28 18:00","2024-09-28 09:00","2024-09-28 18:00","연속"]
[747,"부산울산","직할","우동대연 T/L","24~25년 서부산전력지사 가공송전협력회사 공사","1. 154kV 정보T/L S/T 추락방지장치 설치 2. 154kV 정보T/L 1~2, 5~6호 항공장애표시구 설치 및 이도 조정","2024-09-22 08:00","2024-09-22 18:00","2024-09-22 08:00","2024-09-22 18:00","연속"]
[748,"부산울산","직할","범일서면#1 T/L","24~25년 직할 변전협력회사 총액공사","범일S/S 범일-서면#1,2T/L GIS 조작시험","2024-09-09 09:30","2024-09-10 18:00","2024-09-09 09:30","2024-09-10 18:00","연속"]
[749,"부산울산","직할","범일서면#2 T/L","24~25년 직할 변전협력회사 총액공사","범일S/S 범일-서면#1,2T/L GIS 조작시험","2024-09-09 09:30","2024-09-10 18:00","2024-09-09 09:30","2024-09-10 18:00","연속"]
[750,"부산울산","직할","부산수정#2 T/L","154kV 부산-수정(지중)T/L OF케이블 선종교체공사","154kV 부산-수정(지중)T/L OF1200을 XLPE1200으로 교체","2024-09-11 09:00","2024-12-28 18:00","2024-09-11 09:00","2024-12-28 18:00","연속"]
[751,"경남","거류개폐소","거류거제#2 T/L","154kV 거류-거제#2T/L 추락방지장치 설치공사","154kV 거류-거제#2T/L 추락방지장치 설치공사","2024-09-01 07:00","2024-09-01 18:00","2024-09-01 07:00","2024-09-01 18:00","연속"]
[752,"경남","사천","삼천포사천#1 T/L","154kV 삼천포사천#1 T/L 추락방지장치 설치공사","154kV 삼천포사천#1 T/L 추락방지장치 설치공사","2024-09-02 07:00","2024-09-02 18:00","2024-09-02 07:00","2024-09-02 18:00","매일"]
[753,"경남","사천","삼천포사천#2 T/L","154kV 삼천포사천#1,2 T/L 추락방지장치 설치공사","154kV 삼천포사천#1,2 T/L 추락방지장치 설치공사","2024-09-02 07:00","2024-09-02 18:00","2024-09-02 07:00","2024-09-02 18:00","매일"]
[754,"경남","거류개폐소","신고성거류#2 T/L","154kV 신고성-거류#2T/L 추락방지장치 설치공사","154kV 신고성-거류#2T/L 추락방지장치 설치공사","2024-09-02 07:00","2024-09-06 18:00","2024-09-02 07:00","2024-09-06 18:00","매일"]
[755,"경남","김해","김해S/S #4 M.Tr CB","154kV 김해S/S 주변압기 대체공사","154kV 김해S/S 주변압기 대체공사(#4M.Tr) - #4M.Tr 철거 및 설치 - 전력케이블, NGR, 유효접지용 DS, 제어케이블 철거 및 설치 - 변압기실 흡음재 철거 및 설치 - 기타 부대공사 1식. 끝.","2024-09-02 09:00","2024-10-19 18:00","2024-09-02 09:00","2024-10-19 18:00","연속"]
[756,"경남","사천","사천개양#1 T/L","154kV 사천-개양#1,2 T/L 추락방지장치 설치공사","154kV 사천-개양#1,2 T/L 추락방지장치 설치공사 No.74~ 86 수평배열로 인한 #1, 2T/L 동시휴전 필요","2024-09-03 07:00","2024-09-03 18:00","2024-09-03 07:00","2024-09-03 18:00","연속"]
[757,"경남","사천","사천개양#2 T/L","154kV 사천-개양#1,2 T/L 추락방지장치 설치공사","154kV 사천-개양#1,2 T/L 추락방지장치 설치공사 No.74~ 86 수평배열로 인한 #1, 2T/L 동시휴전 필요","2024-09-03 07:00","2024-09-03 18:00","2024-09-03 07:00","2024-09-03 18:00","연속"]
[758,"경남","통영복합S/Y","통영C/C #2G.Tr CB","통영복합S/Y GTG#1-2 1차 GIS 초기점검","통영복합S/Y GTG#1-2 1차 GIS 초기점검","2024-09-03 09:30","2024-09-03 18:00","2024-09-03 09:30","2024-09-03 18:00","연속"]
[759,"경남","사천","삼천포사천#2 T/L","154kV 삼천포사천#2 T/L 추락방지장치 설치공사","154kV 삼천포사천#2 T/L 추락방지장치 설치공사","2024-09-04 07:00","2024-09-04 18:00","2024-09-06 07:00","2024-09-07 18:00","연속"]
[760,"경남","통영복합S/Y","통영C/C #1S.Tr CB","통영복합S/Y STG#1 1차 GIS 초기점검","통영복합S/Y STG#1 1차 GIS 초기점검","2024-09-04 09:30","2024-09-04 18:00","2024-09-04 09:30","2024-09-04 18:00","연속"]
[761,"경남","신김해","신김해지사#1 T/L","154kV 마천-진해T/L 등 16개T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 등 16개 T/L 추락방지장치 설치 및 교체공사 (신김해지사 17~24, 25~29호)","2024-09-05 07:00","2024-09-06 18:00","2024-09-05 07:00","2024-09-06 18:00","매일"]
[762,"경남","사천","삼천포사천#1 T/L","154kV 삼천포사천#1,2 T/L 추락방지장치 설치공사","154kV 삼천포사천#1,2 T/L 추락방지장치 설치공사 No.60~ 72 수평배열로 인한 #1, 2T/L 동시휴전 필요","2024-09-05 07:00","2024-09-05 18:00","2024-09-04 07:00","2024-09-05 18:00","연속"]
[763,"경남","통영복합S/Y","통영C/C #1G.Tr CB","통영복합S/Y GTG#1-1 1차 GIS 초기점검","통영복합S/Y GTG#1-1 1차 GIS 초기점검","2024-09-05 09:30","2024-09-05 18:00","2024-09-05 09:30","2024-09-05 18:00","연속"]
[764,"경남","통영복합S/Y","고성통영CC#1 T/L","154kV 고성-통영복합#1T/L GIS 초기점검 등","고성S/S, 통영복합S/S 154kV 고성-통영복합#1T/L GIS 초기점검 등","2024-09-05 09:30","2024-09-05 18:00","2024-09-05 09:30","2024-09-05 18:00","연속"]
[765,"경남","통영복합S/Y","거류통영복합#1 T/L","통영복합S/Y 거류-통영복합#1T/L GIS 초기점검","통영복합S/Y 거류-통영복합#1T/L GIS 초기점검","2024-09-06 09:30","2024-09-06 18:00","2024-09-06 09:30","2024-09-06 18:00","연속"]
[766,"경남","의령","의령동진주#2 T/L","154kV 의령-동진주#2T/L GIS 보통점검","154kV 의령-동진주#2T/L GIS 보통점검 [병행] PT(A), LA(A,B,C) 보통 [병행] 전자변(H) 교체","2024-09-06 10:00","2024-09-06 17:00","2024-09-12 10:00","2024-09-12 17:00","연속"]
[767,"경남","마천","녹공마천#1 T/L","마천S/S #1M.Tr 1차 GIS 정밀점검(시험가압용)","마천S/S #1M.Tr 1차 GIS 정밀점검(시험가압용)","2024-09-06 14:00","2024-09-06 18:00","2024-09-06 14:00","2024-09-06 18:00","연속"]
[768,"경남","마천","장유마천#2 T/L","24~25년 경남본부 직할 송전협력회사 공사","154kV 마천S/S 오손애자교체 등","2024-09-07 07:00","2024-09-12 18:00","2024-09-07 07:00","2024-09-12 18:00","연속"]
[769,"경남","거류개폐소","거류거제#2 T/L","154kV 거류-거제#2T/L 추락방지장치 설치공사","154kV 거류-거제#2T/L 추락방지장치 설치공사","2024-09-07 07:00","2024-09-08 18:00","2024-09-07 07:00","2024-09-08 18:00","매일"]
[770,"경남","마천","장유마천#1 T/L","24~25년 경남본부 직할 송전협력회사 공사","154kV 마천S/S 오손애자교체 등","2024-09-08 07:00","2024-09-08 18:00","2024-09-08 07:00","2024-09-08 18:00","연속"]
[771,"경남","거류개폐소","신고성거류#2 T/L","154kV 신고성-거류#2T/L 추락방지장치 설치공사","154kV 신고성-거류#2T/L 추락방지장치 설치공사","2024-09-09 07:00","2024-09-09 18:00","2024-09-09 07:00","2024-09-09 18:00","연속"]
[772,"경남","신고성","신고성고성 T/L","154kV 신고성-고성T/L 추락방지장치 설치공사","154kV 신고성-고성T/L 추락방지장치 설치공사","2024-09-09 07:00","2024-09-09 18:00","2024-09-09 07:00","2024-09-09 18:00","연속"]
[773,"경남","신마산","신마산S/S #60 BUS","신마산S/S 옥외철구설비 GIS화 공사","임시GIS기초공사 레미콘 타설 안전이격거리","2024-09-09 09:00","2024-09-09 12:00","2024-09-03 09:00","2024-09-03 12:00","연속"]
[774,"경남","마천","녹공마천#1 T/L","마천S/S 녹공마천#1 T/L GIS 정밀점검","마천S/S 녹공마천#1 T/L GIS 정밀점검","2024-09-09 09:30","2024-09-10 18:00","2024-09-09 09:30","2024-09-10 18:00","연속"]
[775,"경남","신마산","신마산S/S #65 BUS","신마산S/S 옥외철구설비 GIS화 공사","임시GIS기초공사 레미콘 타설 안전이격거리","2024-09-09 13:00","2024-09-09 17:00","2024-09-03 13:00","2024-09-03 17:00","연속"]
[776,"경남","거류개폐소","신고성거류#1 T/L","154kV 신고성-거류#1T/L 추락방지장치 설치공사","154kV 신고성-거류#1T/L 추락방지장치 설치공사","2024-09-10 07:00","2024-09-13 18:00","2024-09-10 07:00","2024-09-13 18:00","매일"]
[777,"경남","거류개폐소","신고성거류#3 T/L","154kV 신고성-거류#3T/L 추락방지장치 설치공사","154kV 신고성-거류#3T/L 추락방지장치 설치공사","2024-09-10 07:00","2024-09-10 18:00","2024-09-10 07:00","2024-09-10 18:00","연속"]
[778,"경남","신김해","신김해지사#2 T/L","154kV 마천-진해T/L 등 16개T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 등 16개 T/L 추락방지장치 설치 및 교체공사 (신김해지사 17~24, 25~29호)","2024-09-11 07:00","2024-09-12 18:00","2024-09-11 07:00","2024-09-12 18:00","매일"]
[779,"경남","통영복합S/Y","안정통영CC#1 T/L","154kV 안정-통영복합#1T/L GIS 초기점검 등","안정S/S, 통영복합S/S 154kV 고성-통영복합#1T/L GIS 초기점검 등","2024-09-11 09:30","2024-09-11 18:00","2024-09-11 09:30","2024-09-11 18:00","연속"]
[780,"경남","마천","녹공마천#2 T/L","마천S/S 녹공마천#2 T/L GIS 정밀점검","마천S/S 녹공마천#2 T/L GIS 정밀점검","2024-09-11 09:30","2024-09-12 18:00","2024-09-11 09:30","2024-09-12 18:00","연속"]
[781,"경남","통영복합S/Y","안정통영CC#2 T/L","154kV 안정-통영복합#2T/L GIS 초기점검 등","안정S/S, 통영복합S/S 154kV 고성-통영복합#2T/L GIS 초기점검 등","2024-09-12 09:30","2024-09-12 18:00","2024-09-12 09:30","2024-09-12 18:00","연속"]
[782,"경남","거창","거창합천#1 T/L","거창S/S 154kV 거창-합천#1T/L GIS 정밀점검","거창S/S 154kV 거창-합천#1T/L GIS 정밀점검 [병행, 거창] LA(A,B,C) 보통 [병행, 합천] 154kV 거창-합천#1T/L 조작","2024-09-12 10:00","2024-09-13 18:00","2024-09-12 10:00","2024-09-13 18:00","연속"]
[783,"경남","통영복합S/Y","거류통영복합#2 T/L","통영복합S/Y 거류-통영복합#2T/L GIS 초기점검","통영복합S/Y 거류-통영복합#2T/L GIS 초기점검","2024-09-13 09:30","2024-09-13 18:00","2024-09-13 09:30","2024-09-13 18:00","연속"]
[784,"경남","신마산","신마산중리#2 T/L","154kV 신마산-중리#2T/L 용량증대 전선교체공사","용량증대 전선교체공사 ACSR330SQ-ASCC/TW430SQ (신마산S/T~9호)","2024-09-14 07:00","2024-09-20 18:00","취소","취소","연속"]
[785,"경남","거류개폐소","거류거제#2 T/L","154kV 거류-거제#2T/L 추락방지장치 설치공사","154kV 거류-거제#2T/L 추락방지장치 설치공사","2024-09-14 07:00","2024-09-14 18:00","2024-09-14 07:00","2024-09-14 18:00","연속"]
[786,"경남","신마산","신마산중리#1 T/L","154kV 신마산-중리#2T/L 용량증대 전선교체공사 안전이격거리 확보","용량증대 전선교체공사 안전이격거리 확보","2024-09-14 07:00","2024-09-20 11:00","취소","취소","연속"]
[787,"경남","거제","거류거제#2 T/L","거제S/S 인출 송전선로 지중이설공사(임시선로 구성)(요청자시행)","154kV 거제S/S 인출 송전선로 지중이설공사(임시선로 구성)(요청자시행) ○ 154kV 신고성-거제#2T/L 196호(現 거류-거제#2T/L 78호) ~ 가철탑 2호 전선(가공지선 포함) 설치 ○ 154kV 거류-거제#2T/L 거제S/T ~ EBA 인하선 설치 ○ 154kV 신고성-거제#2T/L 196호(現 거류-거제#2T/L 78호) ~ 거제S/T 전선(가공지선 포함) 철거","2024-09-16 08:00","2024-09-17 18:00","2024-09-16 08:00","2024-09-17 18:00","연속"]
[788,"경남","거제","통영거제#1 T/L","거제S/S 인출 송전선로 지중이설공사(임시선로 구성)(요청자시행)","154kV 거제S/S 인출 송전선로 지중이설공사(임시선로 구성) ○ 154kV 통영-거제#1T/L 70호 ~ 가철탑 2호 전선(가공지선 포함) 설치, 거제S/T ~ EBA 인하선 설치, 기설 70호 ~ 거제S/T 전선(가공지선 포함) 철거","2024-09-16 08:00","2024-09-18 06:00","2024-09-16 08:00","2024-09-18 06:00","연속"]
[789,"경남","거제","통영거제#2 T/L","거제S/S 인출 송전선로 지중이설공사(임시선로 구성)(요청자시행)","154kV 거제S/S 인출 송전선로 지중이설공사(임시선로 구성)(요청자시행) ○ 154kV 통영-거제#2T/L 70호 ~ 가철탑 2호 전선(가공지선 포함) 설치 ○ 154kV 통영-거제#2T/L 거제S/T ~ EBA 인하선 설치 ○ 154kV 통영-거제#2T/L 기설 70호 ~ 거제S/T (가공지선 포함) 철거","2024-09-18 07:00","2024-09-18 18:00","2024-09-18 07:00","2024-09-18 18:00","연속"]
[790,"경남","거제","거류거제#1 T/L","거제S/S 인출 송전선로 지중이설공사(임시선로 구성)(요청자시행)","154kV 거제S/S 인출 송전선로 지중이설공사(임시선로 구성)(요청자시행) ○ 154kV 신고성-거제#1T/L 196호(現 거류-거제#1T/L 78호) ~ 가철탑 2호 전선(가공지선 포함) 설치 ○ 154kV 거류-거제#1T/L 거제S/T ~ EBA 인하선 설치 ○ 154kV 154kV 신고성-거제#1T/L 196호(現 거류-거제#1T/L 78호) ~ 거제S/T 전선(가공지선 포함) 철거","2024-09-18 07:00","2024-09-18 18:00","2024-09-18 07:00","2024-09-18 18:00","연속"]
[791,"경남","거류개폐소","신고성거류#1 T/L","154kV 신고성-거류#1T/L 추락방지장치 설치공사","154kV 신고성-거류#1T/L 추락방지장치 설치공사","2024-09-19 07:00","2024-09-20 18:00","2024-09-19 07:00","2024-09-20 18:00","매일"]
[792,"경남","중리","중리가야#1 T/L","154kV 신마산-중리#2T/L 용량증대 전선교체공사 안전이격거리 확보","용량증대 전선교체공사 안전이격거리 확보","2024-09-20 11:00","2024-09-20 18:00","취소","취소","연속"]
[793,"경남","삼계","삼계어방#1 T/L","154kV 마천-진해T/L 등 16개T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 등 16개 T/L 추락방지장치 설치 및 교체공사 (34`43호)","2024-09-21 07:00","2024-09-22 18:00","2024-09-21 07:00","2024-09-22 18:00","매일"]
[794,"경남","거류개폐소","거류거제#2 T/L","154kV 거류-거제#2T/L 추락방지장치 설치공사","154kV 거류-거제#2T/L 추락방지장치 설치공사","2024-09-21 07:00","2024-09-21 18:00","2024-09-21 07:00","2024-09-21 18:00","연속"]
[795,"경남","삼계","삼계어방#2 T/L","154kV 마천-진해T/L 등 16개T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 등 16개 T/L 추락방지장치 설치 및 교체공사 (34~43, 44~51, 1~5, 6,7,8,9,14,15,,16~24호)","2024-09-21 07:00","2024-09-22 18:00","2024-09-21 07:00","2024-09-22 18:00","매일"]
[796,"경남","거제","거류거제#1 T/L","거제S/S 인출 송전선로 지중이설공사(임시선로 구성)(예비1차)","154kV 거제S/S 인출 송전선로 지중이설공사(임시선로 구성)(요청자시행) [안전거리 확보 휴전] ○ 154kV 통영-거제#2T/L 70호 ~ 가철탑 2호 전선 설치, 154kV 통영-거제#2T/L 거제S/T ~ EBA 인하선 설치 ○ 154kV 통영-거제#1T/L 기설 70호 ~ 거제S/T 전선(가공지선 포함) 철거","2024-09-22 08:00","2024-09-22 18:00","2024-09-22 08:00","2024-09-22 18:00","연속"]
[797,"경남","거제","통영거제#2 T/L","거제S/S 인출 송전선로 지중이설공사(임시선로 구성)(예비1차)","154kV 거제S/S 인출 송전선로 지중이설공사(임시선로 구성)(요청자시행) ○ 154kV 통영-거제#2T/L 70호 ~ 가철탑 2호 전선(가공지선 포함) 설치 ○ 154kV 통영-거제#2T/L 거제S/T ~ EBA 인하선 설치 ○ 154kV 통영-거제#2T/L 기설 70호 ~ 거제S/T (가공지선 포함) 철거","2024-09-22 08:00","2024-09-22 18:00","2024-09-22 08:00","2024-09-22 18:00","연속"]
[798,"경남","개양","하동개양#2 T/L","154kV 정촌분기T/L 건설공사","ㅇ 154kV 하동-개양T/L 기설 No.18 철거 및 No.18(C/H) 신설, 전력선 공중이동","2024-09-23 06:00","2024-09-25 18:00","2024-09-23 06:00","2024-09-25 18:00","연속"]
[799,"경남","거류개폐소","신고성거류#1 T/L","154kV 신고성-거류#1T/L 추락방지장치 설치공사","154kV 신고성-거류#1T/L 추락방지장치 설치공사","2024-09-23 07:00","2024-09-27 18:00","2024-09-23 07:00","2024-09-27 18:00","매일"]
[800,"경남","칠서","칠서창녕#2 T/L","154kV 칠서-창녕#2T/L 추락방지장치 설치공사","154kV 칠서-창녕#2T/L 1~17호(14기) 수평형 추락방지장치 설치","2024-09-23 07:00","2024-09-24 18:00","2024-09-23 07:00","2024-09-24 18:00","매일"]
[801,"경남","칠서","신마산칠서#1 T/L","154kV 신마산-칠서#1T/L 추락방지장치 설치공사","154kV 신마산-칠서#1T/L 1~50호(45기) 수평형 추락방지장치 설치","2024-09-23 07:00","2024-09-25 18:00","2024-09-23 07:00","2024-09-25 18:00","매일"]
[802,"경남","신마산","신마산S/S #60 BUS","신마산S/S 옥외철구설비 GIS화 공사","임시GIS기초공사 레미콘 타설 안전이격거리","2024-09-23 09:00","2024-09-23 12:00","2024-09-23 09:00","2024-09-23 12:00","연속"]
[803,"경남","창녕","창녕초동#1 T/L","창녕S/S 창녕-초동#1T/L GIS 초기점검 외","창녕S/S 창녕-초동#1T/L GIS 및 LA 초기점검","2024-09-23 09:30","2024-09-23 17:30","2024-09-23 09:30","2024-09-23 17:30","연속"]
[804,"경남","김해","매리김해#1 T/L","김해S/S 매리김해#1 T/L GIS 보통","김해S/S 매리김해#1 T/L GIS 보통","2024-09-23 09:30","2024-09-23 17:30","2024-09-23 09:30","2024-09-23 17:30","연속"]
[805,"경남","신마산","신마산S/S #65 BUS","신마산S/S 옥외철구설비 GIS화 공사","임시GIS기초공사 레미콘 타설 안전이격거리","2024-09-23 13:00","2024-09-23 17:00","2024-09-23 13:00","2024-09-23 17:00","연속"]
[806,"경남","김해","매리김해#2 T/L","김해S/S 매리김해#2 T/L GIS 보통","김해S/S 매리김해#2 T/L GIS 보통","2024-09-24 09:30","2024-09-24 17:30","2024-09-24 09:30","2024-09-24 17:30","연속"]
[807,"경남","창녕","창녕초동#2 T/L","창녕S/S 창녕-초동#2T/L GIS 초기점검 외","창녕S/S 창녕-초동#2T/L GIS 및 LA 초기점검","2024-09-24 09:30","2024-09-24 17:30","2024-09-24 09:30","2024-09-24 17:30","연속"]
[808,"경남","김해","김해어방#1 T/L","김해S/S 김해-어방#1 T/L GIS 보통","김해S/S 김해-어방#1 T/L GIS 보통","2024-09-25 09:30","2024-09-25 17:30","2024-09-25 09:30","2024-09-25 17:30","연속"]
[809,"경남","개양","하동개양#1 T/L","154kV 정촌분기T/L 건설공사","ㅇ 154kV 하동-개양T/L 기설 No.18 철거 및 No.18(C/H) 신설, 전력선 공중이동","2024-09-26 06:00","2024-09-27 18:00","2024-09-26 06:00","2024-09-27 18:00","연속"]
[810,"경남","칠서","신마산칠서#2 T/L","154kV 신마산-칠서#2T/L 추락방지장치 설치공사","154kV 신마산-칠서#2T/L 1~5호,42호(6기) 수평형 추락방지장치 설치","2024-09-26 07:00","2024-09-26 18:00","2024-09-26 07:00","2024-09-26 18:00","연속"]
[811,"경남","칠서","칠서창녕#1 T/L","154kV 칠서-창녕#1T/L 추락방지장치 설치공사","154kV 칠서-창녕#1T/L 9호,18~55호(35기) 수평형 추락방지장치 설치","2024-09-26 07:00","2024-09-27 18:00","2024-09-26 07:00","2024-09-27 18:00","매일"]
[812,"경남","김해","김해어방#2 T/L","김해S/S 김해-어방#2 T/L GIS 보통","김해S/S 김해-어방#2 T/L GIS 보통","2024-09-26 09:30","2024-09-26 17:30","2024-09-26 09:30","2024-09-26 17:30","연속"]
[813,"경남","어방","삼계어방#1 T/L","어방S/S 삼계-어방#1 GIS 조작","어방S/S 삼계-어방#1 GIS 조작","2024-09-27 09:30","2024-09-27 17:30","2024-09-27 09:30","2024-09-27 17:30","연속"]
[814,"경남","매리","매리김해#1 T/L","154kV 마천-진해T/L 등 16개T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 등 16개 T/L 추락방지장치 설치 및 교체공사","2024-09-28 07:00","2024-09-29 18:00","2024-09-28 07:00","2024-09-29 18:00","매일"]
[815,"경남","거류개폐소","거류거제#2 T/L","154kV 거류-거제#2T/L 추락방지장치 설치공사","154kV 거류-거제#2T/L 추락방지장치 설치공사","2024-09-28 07:00","2024-09-28 18:00","2024-09-28 07:00","2024-09-28 18:00","연속"]
[816,"경남","매리","매리김해#2 T/L","154kV 마천-진해T/L 등 16개T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 등 16개 T/L 추락방지장치 설치 및 교체공사","2024-09-29 07:00","2024-09-29 18:00","2024-09-29 07:00","2024-09-29 18:00","매일"]
[817,"경남","거제","거류거제#1 T/L","거제S/S 인출 송전선로 지중이설공사(임시선로 구성)(예비2차)","154kV 거제S/S 인출 송전선로 지중이설공사(임시선로 구성)(요청자시행) ○ 154kV 거류-거제#1T/L 78호 ~ 가철탑 2호 전선(가공지선 포함) 설치 ○ 154kV 거류-거제#1T/L 거제S/T ~ EBA 인하선 설치 ○ 154kV 거류-거제#1T/L 기설 78호 ~ 거제S/T 전선(가공지선 포함) 철거","2024-09-29 08:00","2024-09-29 18:00","2024-09-29 08:00","2024-09-29 18:00","연속"]
[818,"경남","거제","통영거제#2 T/L","거제S/S 인출 송전선로 지중이설공사(임시선로 구성)(예비2차)","154kV 거제S/S 인출 송전선로 지중이설공사(임시선로 구성)(요청자시행) [안전거리 확보 휴전] ○ 154kV 거류-거제#2T/L 78호 ~ 가철탑 2호 전선 설치, 154kV 거류-거제#1T/L 거제S/T ~ EBA 인하선 설치 ○ 154kV 거류-거제#1T/L 기설 78호 ~ 거제S/T (가공지선 포함) 철거","2024-09-29 08:00","2024-09-29 18:00","2024-09-29 08:00","2024-09-29 18:00","연속"]
[819,"경남","의령","의령함양 T/L","154kV 의령-함양/L 피뢰기 설치 공사 등","154kV 의령-함양/L 피뢰기 설치 공사 등 - №1~132 (132기)","2024-09-30 07:00","2024-10-04 18:00","2024-09-30 07:00","2024-10-04 18:00","매일"]
[820,"경남","창녕","창녕초동#2 T/L","154kV 창녕-구지#1T/L 추락방지장치 설치공사(안전이격거리확보)","154kV 창녕-구지#1T/L 1~7호(7기) 피뢰기 및 고정형 폴리머지지애자 설치 관련 안전이격거리확보","2024-09-30 07:00","2024-09-30 18:00","2024-09-30 07:00","2024-09-30 18:00","연속"]
[821,"경남","거류개폐소","신고성거류#1 T/L","154kV 신고성-거류#1T/L 추락방지장치 설치공사","154kV 신고성-거류#1T/L 추락방지장치 설치공사","2024-09-30 07:00","2024-09-30 18:00","2024-09-30 07:00","2024-09-30 18:00","연속"]
[822,"경남","창녕","창녕구지#1 T/L","154kV 창녕-구지#1T/L 추락방지장치 설치공사","154kV 창녕-구지#1T/L 1~81호(76기) 수평형 추락방지장치 및 피뢰기, 폴리머 지지애자 설치","2024-09-30 07:00","2024-10-15 18:00","2024-09-30 07:00","2024-10-15 18:00","매일"]
[823,"경남","신마산","신마산S/S #60 BUS","신마산S/S 옥외철구설비 GIS화 공사","임시GIS기초공사 레미콘 타설 안전이격거리","2024-09-30 09:00","2024-09-30 12:00","2024-09-30 09:00","2024-09-30 12:00","연속"]
[824,"경남","사천","사천개양#1 T/L","사천S/S 154kV 사천-개양#1T/L GIS 조작시험","사천S/S 154kV 사천-개양#1T/L GIS 조작시험","2024-09-30 09:30","2024-09-30 14:00","2024-09-30 09:30","2024-09-30 14:00","연속"]
[825,"경남","신마산","신마산S/S #65 BUS","신마산S/S 옥외철구설비 GIS화 공사","임시GIS기초공사 레미콘 타설 안전이격거리","2024-09-30 13:00","2024-09-30 17:00","2024-09-30 13:00","2024-09-30 17:00","연속"]
[826,"경남","사천","사천개양#2 T/L","사천S/S 154kV 사천-개양#2T/L GIS 조작시험","사천S/S 154kV 사천-개양#2T/L GIS 조작시험","2024-09-30 14:00","2024-09-30 18:00","2024-09-30 14:00","2024-09-30 18:00","연속"]