{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":23,"n_cols":12,"rows_kept":23,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2],[2,11,3,11]]}
["2025년도 6월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S CB 8300","2025년 신가평S/S  GIS 점검공사","2025년 신가평S/S  GIS 점검공사 - 신태백#2T/L-#2M.Tr 1차 TIE GIS(8300) 단독차단기 보통점검","2025-06-09 09:00","2025-06-10 18:00","2025-06-09 09:00","2025-06-10 18:00","연속"]
[2,"경기북부","구리","신가평S/S CB 8371","2025년 신가평S/S  GIS 점검공사","2025년 신가평S/S  GIS 점검공사(6월 연기 대비) - 신태백-신가평#2T/L GIS(8371) 단독차단기 보통점검","2025-06-04 09:00","2025-06-05 18:00","2025-06-04 09:00","2025-06-05 18:00","연속"]
[3,"경기북부","구리","신가평S/S CB 8372","2025년 신가평S/S  GIS 점검공사","2025년 신가평S/S  GIS 점검공사 -#2 M.Tr 1차 GIS(8372) 단독차단기 보통점검","2025-06-11 09:00","2025-06-12 18:00","2025-06-11 09:00","2025-06-12 18:00","연속"]
[4,"경기북부","구리","신가평S/S CB 8471","2025년 신가평S/S  GIS 점검공사","2025년 신가평S/S  GIS 점검공사(6월 연기 대비) - 신태백-신가평#1T/L GIS(8471) 단독차단기 보통점검","2025-06-13 09:00","2025-06-14 18:00","2025-06-13 09:00","2025-06-14 18:00","연속"]
[5,"경기북부","구리","신가평S/S CB 8571","2025년 신가평S/S  GIS 점검공사","2025년 신가평S/S  GIS 점검공사(6월 연기 대비) - 신안성-신가평T/L GIS(8571) 단독차단기 보통점검","2025-06-16 09:00","2025-06-17 18:00","2025-06-16 09:00","2025-06-17 18:00","연속"]
[6,"경기북부","구리","신가평S/S CB 8500","2025년 신가평S/S  GIS 점검공사","2025년 신가평S/S  GIS 점검공사(6월 연기 대비) - 신안성-신가평T/L-#4 M.Tr 1차 GIS(8500) 단독차단기 보통점검","2025-06-18 09:00","2025-06-19 18:00","2025-06-18 09:00","2025-06-19 18:00","연속"]
[7,"경기북부","구리","신안성신가평 T/L"," 신안성-신가평 등 12개T/L 추락방지시설 설치공사"," 신안성-신가평T/L 고광도 항공장애등 설치 : No.131,132,146,147","2025-06-23 07:00","2025-06-27 18:00","취소","취소","연속"]
[8,"경기북부","구리","신가평S/S CB 8572","2025년 신가평S/S  GIS 점검공사","2025년 신가평S/S  GIS 점검공사(6월 연기 대비) - #4 M.Tr 1차 GIS(8572) 단독차단기 보통점검","2025-06-20 09:00","2025-06-21 18:00","2025-06-20 09:00","2025-06-21 18:00","연속"]
[9,"대전세종충남","서산","당진T/P CB 8100","25년 서산P/O  GIS 보통점검공사","(5월휴전취소시) (즉시가압가능) 당진T/P  8100 GIS 보통점검","2025-06-19 09:30","2025-06-20 18:00","취소","취소","연속"]
[10,"대전세종충남","서산","당진T/P CB 8171","25년 서산P/O  GIS 보통점검공사","(5월휴전취소시) (즉시가압가능) 당진T/P  8171 GIS 보통점검","2025-06-17 09:30","2025-06-18 18:00","취소","취소","연속"]
[11,"대전세종충남","서산","당진T/P CB 8472","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 당진T/P  8472 GIS 보통점검","2025-06-03 09:30","2025-06-04 18:00","2025-06-03 09:30","2025-06-04 18:00","연속"]
{"$rows_empty":7}
[{"$nulls":5}," "]

{"sheet":"345설비","index":1,"n_rows":370,"n_cols":12,"rows_kept":370,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2025년도 6월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","중부S/S #4 M.Tr","2025년 중부전력지사 변전협력회사 공사","- 피뢰기 카운터 개선","2025-06-09 10:00","2025-06-09 18:00","2025-06-09 10:00","2025-06-09 18:00","연속"]
[2,"남서울","동서울","동서울S/S CB 7971","2024-2025년도 동서울전력지사 변전협력회사 총액공사","동서울S/S 신용인-동서울#2T/L CB(7971) 조작시험","2025-06-20 12:00","2025-06-20 15:00","2025-06-20 12:00","2025-06-20 15:00","연속"]
[3,"남서울","동서울","동서울S/S CB 7771","2024-2025년도 동서울전력지사 변전협력회사 총액공사","동서울S/S 신성남-동서울#2T/L CB(7771) 조작시험","2025-06-20 09:00","2025-06-20 12:00","2025-06-20 09:00","2025-06-20 12:00","연속"]
[4,"남서울","동서울","동서울S/S CB 7872","2024-2025년도 동서울전력지사 변전협력회사 총액공사","동서울S/S #78BAY-#76BUS연결 CB(7872) 조작시험","2025-06-19 15:00","2025-06-19 18:00","2025-06-19 15:00","2025-06-19 18:00","연속"]
[5,"남서울","동서울","동서울S/S CB 7800","2024-2025년도 동서울전력지사 변전협력회사 총액공사","동서울S/S 신성남-동서울#1T/L #76BUS TIE CB(7800) 조작시험","2025-06-19 12:00","2025-06-19 15:00","2025-06-19 12:00","2025-06-19 15:00","연속"]
[6,"남서울","동서울","동서울S/S CB 7871","2024-2025년도 동서울전력지사 변전협력회사 총액공사","동서울S/S 신성남-동서울#1T/L CB(7871) 조작시험","2025-06-19 09:00","2025-06-19 12:00","2025-06-19 09:00","2025-06-19 12:00","연속"]
[7,"남서울","영등포","신광명S/S #2 M.Tr"," 신광명S/S GIS 용량대체 및 S/W 증설공사","-  63kA GIS 27CB 설치 - 기타 부대공사 1식","2025-06-09 09:00","2025-06-13 18:00","2025-06-09 09:00","2025-06-13 18:00","연속"]
[8,"인천","부평","서인천C/C #1 Sh.R CB","서인천복합S/Y  #1 Sh.R 1차 GIS 정밀점검","서인천복합S/Y  #1 Sh.R 1차 GIS 정밀점검","2025-06-30 09:00","2025-07-04 18:00","취소","취소","연속"]
[9,"인천","부평","서인천C/C #70 BUS","서인천복합S/Y #70BUS 모선보호반 교체공사","서인천복합S/Y #70BUS 모선보호반 교체공사","2025-06-04 09:00","2025-06-09 18:00","2025-06-04 09:00","2025-06-09 18:00","연속"]
[10,"인천","부평","서인천C/C #1 M.Tr","서인천복합S/Y  #1M.Tr 염해방지도포","서인천복합S/Y  #1M.Tr 염해방지도포","2025-06-09 09:00","2025-06-10 18:00","취소","취소","연속"]
[11,"인천","부평","서인천C/C CB 7A71","서인천C/C 7A Bay B/F 보호IED 성능개선","서인천C/C 7A Bay B/F 보호IED 성능개선 - 피앤씨테크제 보호IED 펌웨어 업데이트","2025-06-30 09:00","2025-06-30 18:00","취소","취소","연속"]
[12,"인천","부평","서인천C/C #4 Sh.R CB","서인천복합S/Y  #4 Sh.R 1차 GIS 정밀점검","서인천복합S/Y  #4 Sh.R 1차 GIS 정밀점검","2025-06-23 09:00","2025-06-27 18:00","2025-06-23 09:00","2025-06-27 18:00","연속"]
[13,"인천","부평","서인천C/C #3 Sh.R CB"," #3 Sh.R 1차 7B79 GIS 조작시험"," #3 Sh.R 1차 7B79 GIS 조작시험","2025-06-16 09:00","2025-06-16 18:00","2025-06-16 09:00","2025-06-16 18:00","연속"]
[14,"인천","부평","서인천C/C #4 M.Tr"," #4M.Tr 염해방지 도포"," #4M.Tr 염해방지 도포","2025-06-05 09:00","2025-06-06 18:00","취소","취소","연속"]
[15,"인천","부평","서인천C/C #3 M.Tr","서인천복합S/Y  #3M.Tr 염해방지도포","서인천복합S/Y  #3M.Tr 염해방지도포","2025-06-13 09:00","2025-06-14 18:00","2025-06-13 09:00","2025-06-14 18:00","연속"]
[16,"인천","부평","서인천C/C #2 M.Tr","서인천복합S/Y  #2M.Tr 염해방지도포","서인천복합S/Y  #2M.Tr 염해방지도포","2025-06-11 09:00","2025-06-12 18:00","2025-06-11 09:00","2025-06-12 18:00","연속"]
[17,"인천","부평","신경서서인천CC T/L"," 신경서서인천CCT/L CLR용 GIS 부싱 염해방지코팅"," 신경서서인천CCT/L CLR용 GIS 부싱 염해방지코팅","2025-06-19 09:00","2025-06-19 18:00","2025-06-19 09:00","2025-06-19 18:00","연속"]
[18,"인천","부평","신가좌S/S CB 7472"," #3 M.Tr 1차 7472 GIS 보통점검"," #3 M.Tr 1차 7472 GIS 보통점검","2025-06-27 09:00","2025-06-27 18:00","취소","취소","연속"]
[19,"인천","부평","신가좌S/S #1 BUS","신가좌S/S 345㎸ 용량부족 GIS 교체공사","신가좌S/S 345㎸ 용량부족 GIS 교체공사 - 72Bay 철거(3CB) 및 설치 (2CB) - 제어케이블 분리 및 결선 - 기타 부대작업","2025-06-02 09:00","2027-06-22 18:00","취소","취소","연속"]
[20,"인천","부평","신가좌S/S CB 7672"," #4 M.Tr 1차 7672 GIS 보통점검(열화)"," #4 M.Tr 1차 7672 GIS 보통점검(열화)","2025-06-14 09:00","2025-06-14 13:00","취소","취소","연속"]
[21,"인천","부평","신가좌S/S CB 7600"," #4 M.Tr 1차 TIE 7600 GIS 보통점검(열화)"," #4 M.Tr 1차 TIE 7600 GIS 보통점검(열화)","2025-06-14 13:00","2025-06-14 18:00","취소","취소","연속"]
[22,"인천","부평","신가좌S/S #2 M.Tr","신가좌S/S  #2 M.Tr 보통점검","신가좌S/S  #2 M.Tr 보통점검","2025-06-16 09:00","2025-06-20 18:00","취소","취소","연속"]
[23,"인천","부평","신가좌S/S #1 BUS","신가좌S/S  #70BUS 누기 보수 공사","신가좌S/S  #70BUS 누기 보수 공사","2025-06-09 09:00","2025-06-13 18:00","취소","취소","연속"]
[24,"인천","부평","신가좌S/S #4 M.Tr","신가좌S/S  #4M.Tr 보통점검","신가좌S/S  #4M.Tr 보통점검","2025-06-02 09:00","2025-06-06 18:00","취소","취소","연속"]
[25,"인천","부평","신가좌신시흥#2 T/L"," 신가좌-신시흥T/L No.15 태풍취약철탑 보강공사 등 2건","No.15 태풍취약철탑 보강공사(인클로징 공법) No.2~13 철탑보강 및 항공시설물 정비","2025-06-24 07:00","2025-06-30 18:00","취소","취소","연속"]
[26,"인천","부평","신가좌S/S #2 BUS","신가좌S/S 345㎸ 용량부족 GIS 교체공사","신가좌S/S 345㎸ 용량부족 GIS 교체공사 - 72Bay 철거(3CB) 및 설치 (2CB) - 제어케이블 분리 및 결선 - 기타 부대작업","2025-06-22 18:00","2025-07-27 18:00","취소","취소","연속"]
[27,"인천","부평","신가좌신시흥#2 T/L","신가좌S/S 345㎸ 용량부족 GIS 교체공사","345㎸ #70BUS 무부하 가압용 (24H)","2025-06-21 18:00","2025-06-22 18:00","취소","취소","연속"]
[28,"인천","부평","신가좌신시흥#1 T/L","신가좌S/S 345㎸ 용량부족 GIS 교체공사","345㎸ #70BUS 무부하 가압용 (24H)","2025-06-21 18:00","2025-06-22 18:00","취소","취소","연속"]
[29,"인천","부평","신가좌S/S #4 M.Tr","신가좌S/S 345㎸ 용량부족 GIS 교체공사","345㎸ #70BUS 무부하 가압용 (24H)","2025-06-21 18:00","2025-06-22 18:00","취소","취소","연속"]
[30,"인천","부평","신가좌신시흥#1 T/L"," 신가좌-신시흥T/L No.15 태풍취약철탑 보강공사 등 2건","No.15 태풍취약철탑 보강공사(인클로징 공법) No.2~13 철탑보강 및 항공시설물 정비","2025-06-17 07:00","2025-06-23 18:00","취소","취소","연속"]
[31,"인천","부평","신가좌신시흥#2 T/L"," 신가좌-신시흥T/L No.15 태풍취약철탑 보강공사","No.15 태풍취약철탑 보강공사(충전부 방호장치 설치)","2025-06-16 07:00","2025-06-16 18:00","취소","취소","연속"]
[32,"인천","부평","신경서S/S CB 7271"," 신경서-인천CC#1T/L 7271 GIS 조작시험"," 신경서-인천CC#1T/L 7271 GIS 조작시험","2025-06-20 09:00","2025-06-20 18:00","2025-06-20 09:00","2025-06-20 18:00","연속"]
[33,"인천","부평","신인천C/C SEC CB 70710"," 70-71,71-72SEC B/F 보호반 대체 공사"," 70-71,71-72SEC B/F 보호반 대체 공사","2025-06-16 09:00","2025-06-20 18:00","2025-06-16 09:00","2025-06-20 18:00","연속"]
[34,"인천","부평","신인천C/C SEC CB 71720"," 70-71,71-72SEC B/F 보호반 대체 공사"," 70-71,71-72SEC B/F 보호반 대체 공사","2025-06-16 09:00","2025-06-20 18:00","2025-06-16 09:00","2025-06-20 18:00","연속"]
[35,"인천","부평","신경서신인천CC T/L"," 신경서신인천CCT/L CLR용 GIS 부싱 염해방지코팅"," 신경서신인천CCT/L CLR용 GIS 부싱 염해방지코팅","2025-06-18 09:00","2025-06-18 18:00","2025-06-18 09:00","2025-06-18 18:00","연속"]
[36,"인천","부평","인천C/C #75 BUS","인천복합S/Y  #75-76 SEC GIS 정밀점검 무부하가압","인천복합S/Y  #75-76 SEC GIS 정밀점검 무부하가압","2025-06-20 14:00","2025-06-20 18:00","취소","취소","연속"]
[37,"인천","부평","인천C/C #1 Sh.R CB","인천복합S/Y #1Sh.R 7279 GIS 부싱 C상 누기 보수","인천복합S/Y #1Sh.R 7279 GIS 부싱 C상 누기 보수","2025-06-23 09:00","2025-06-25 18:00","취소","취소","연속"]
[38,"인천","부평","인천C/C CB 7B72","#5,6G/T-인천복합#3S/T 7B00 TIE GIS 보통점검(열화)","#5,6G/T-인천복합#3S/T 7B00 TIE GIS 보통점검(열화)","2025-06-17 09:00","2025-06-17 18:00","2025-06-17 09:00","2025-06-17 18:00","연속"]
[39,"인천","부평","인천C/C SEC CB 75760","인천복합S/Y  #75-76 SEC GIS 정밀점검","인천복합S/Y  #75-76 SEC GIS 정밀점검","2025-06-16 09:00","2025-06-20 18:00","취소","취소","연속"]
[40,"인천","부평","인천C/C #2 M.Tr","인천C/C  #2 TIE Tr 보통점검, 부싱유채유","인천C/C  #2 TIE Tr 보통점검, 부싱유채유, 기계적보호장치 교체","2025-06-09 09:00","2025-06-13 18:00","취소","취소","연속"]
[41,"인천","부평","인천C/C #1 M.Tr","인천복합S/Y  #1 Tie Tr 부싱유 채유","인천복합S/Y  #1 Tie Tr 부싱유 채유","2025-06-04 09:00","2025-06-04 18:00","2025-06-04 09:00","2025-06-04 18:00","연속"]
[42,"인천","부평","가정인천CC#1 T/L","인천C/C 74Bay 차단기 동작실패 보호반 대체 공사","인천C/C 74Bay 차단기 동작실패 보호반 대체 공사 및 #2Sh.R 7279 GIS C상 SF6 가스 누기 공사","2025-06-02 09:00","2025-06-06 18:00","취소","취소","연속"]
[43,"인천","부평","인천C/C #1 Sh.R CB","인천복합S/Y #1Sh.R 7279 GIS 부싱 C상 누기 보수","인천복합S/Y #1Sh.R 7279 GIS 부싱 C상 누기 보수","2025-06-02 09:00","2025-06-04 18:00","취소","취소","연속"]
[44,"인천","부평","신경서인천CC#2 T/L","인천C/C 74Bay 차단기 동작실패 보호반 대체 공사","인천C/C 74Bay 차단기 동작실패 보호반 대체 공사 및 #2Sh.R 7279 GIS C상 SF6 가스 누기 공사","2025-06-02 09:00","2025-06-06 18:00","취소","취소","연속"]
[45,"인천","부평","가정인천CC#1 T/L","가정-인천CC #1T/L 접속함 보수공사","가정-인천CC #1T/L(D2) J/B#2 A상 발열 및 소음으로 인한 보수공사 시행","2025-06-07 09:00","2025-06-08 18:00","취소","취소","연속"]
[46,"인천","부평","포스코CC인천CC#2 T/L"," 인천CC-포스코#2T/L CLR TOP HAT BOLT 교체"," 인천CC-포스코#2T/L CLR TOP HAT BOLT 교체","2025-06-21 09:00","2025-06-21 18:00","취소","취소","연속"]
[47,"인천","부평","신경서포스코CC#1 T/L"," 포스코SY신경서#1T/L CLR 인출부싱 염해방지 코팅"," 포스코SY신경서#1T/L CLR 인출부싱 염해방지 코팅","2025-06-07 09:00","2025-06-07 18:00","취소","취소","연속"]
[48,"인천","부평","포스코CC인천CC#1 T/L"," 인천CC-포스코#1T/L CLR TOP HAT BOLT 교체"," 인천CC-포스코#1T/L CLR TOP HAT BOLT 교체","2025-06-05 09:00","2025-06-05 18:00","취소","취소","연속"]
[49,"인천","부평","포스코C/C CB 7472","포스코S/Y #74Bay 차단기 동작실패 보호반 교체 공사","포스코S/Y #74Bay 차단기 동작실패 보호반 교체 공사","2025-06-08 09:00","2025-06-13 18:00","2025-06-08 09:00","2025-06-13 18:00","연속"]
[50,"인천","부평","신경서포스코CC#2 T/L","포스코S/Y #74Bay 차단기 동작실패 보호반 교체 공사","포스코S/Y #74Bay 차단기 동작실패 보호반 교체 공사","2025-06-08 09:00","2025-06-13 18:00","2025-06-08 09:00","2025-06-13 18:00","연속"]
[51,"인천","부평","가정인천CC#1 T/L"," 가정-인천CC#1T/L CLR Bypass 조작","가정-인천CC#1T/L CLR Bypass 조작","2025-06-21 07:00","2025-06-21 09:00","2025-06-15 07:00","2025-06-15 20:00","연속"]
[52,"인천","부평","가정인천CC#1 T/L","가정-인천CC#1T/L CLR Bypass 원복 조작","가정-인천CC#1T/L CLR Bypass 원복 조작","2025-06-28 07:00","2025-06-28 09:00","취소","취소","연속"]
[53,"인천","부평","신인천C/C SEC CB 75760"," 75-76,76-77SEC B/F 보호반 대체 공사"," 75-76,76-77SEC B/F 보호반 대체 공사","2025-06-16 09:00","2025-06-20 18:00","2025-06-16 09:00","2025-06-20 18:00","연속"]
[54,"인천","부평","인천C/C CB 7471","인천복합S/Y  신경서-인천CC#2T/L 정밀점검 무부하가압","인천복합S/Y  신경서-인천CC#2T/L 정밀점검 무부하가압","2025-06-13 14:00","2025-06-13 18:00","2025-06-13 14:00","2025-06-13 18:00","연속"]
[55,"인천","부평","인천C/C CB 7471","인천복합S/Y  신경서-인천CC#2T/L 7471 정밀점검","인천복합S/Y  신경서-인천CC#2T/L 7471 정밀점검","2025-06-09 09:00","2025-06-13 18:00","2025-06-09 09:00","2025-06-13 18:00","연속"]
[56,"인천","시흥","신시흥#1S/S #1 M.Tr","신시흥S/S 154kV Sh.R 증설공사","- #1M.Tr 2차 GIS 이설 및 Sh.R용 GIS 3Bay 설치 - #3Sh.R 기기 기초 시공","2025-06-02 09:00","2025-07-15 18:00","취소","취소","연속"]
[57,"인천","시흥","영흥T/P CB 7472","영흥#1S/Y 362kV GIS 정밀점검 공사(7472)","영흥#1S/Y 7472 CB 정밀점검 공사","2025-06-23 08:00","2025-06-27 18:00","2025-06-23 08:00","2025-06-27 18:00","연속"]
[58,"인천","시흥","영흥1TP영흥2TP#2 T/L","영흥#1S/Y 362kV GIS 정밀점검 공사(7271) 무부하가압","영흥#1S/Y 7271 CB 정밀점검 공사 무부하가압","2025-06-07 10:00","2025-06-07 18:00","2025-06-07 10:00","2025-06-07 18:00","연속"]
[59,"인천","시흥","영흥T/P CB 7271","영흥#1S/Y 362kV GIS 정밀점검 공사(7271)","영흥#1S/Y 7271 CB 정밀점검 공사","2025-06-04 08:00","2025-06-07 18:00","2025-06-04 08:00","2025-06-07 18:00","연속"]
[60,"인천","시흥","영흥T/P CB 7471","영흥#1S/Y 362kV GIS 정밀점검 공사(7471)","영흥#1S/Y 7471 CB 정밀점검 공사","2025-06-09 08:00","2025-06-13 18:00","2025-06-09 08:00","2025-06-13 18:00","연속"]
[61,"인천","시흥","신시흥영흥TP#2 T/L","영흥#1S/Y 362kV GIS 정밀점검 공사(7471) 무부하가압","영흥#1S/Y 7471 CB 정밀점검 공사 무부하가압","2025-06-13 08:00","2025-06-13 14:00","2025-06-13 08:00","2025-06-13 14:00","연속"]
[62,"인천","시흥","영흥T/P CB 7372","영흥#1S/Y 362kV GIS 정밀점검 공사(7372)","영흥#1S/Y 7372 CB 정밀점검 공사","2025-06-16 08:00","2025-06-20 18:00","2025-06-16 08:00","2025-06-20 18:00","연속"]
[63,"인천","직할","갈산S/S CB 7200","갈산S/S 7200 GIS 보통점검","갈산S/S 7200 GIS 보통점검","2025-06-05 09:00","2025-06-05 18:00","2025-06-05 09:00","2025-06-05 18:00","연속"]
[64,"인천","직할","갈산S/S CB 7272","갈산S/S #1M.Tr 1차 7272 GIS 보통점검","갈산S/S #1M.Tr 1차 7272 GIS 보통점검","2025-06-04 09:00","2025-06-04 18:00","2025-06-04 09:00","2025-06-04 18:00","연속"]
[65,"인천","직할","갈산S/S CB 7171","갈산S/S 가정갈산#1T/L 7171 GIS 보통점검","갈산S/S 가정갈산#1T/L 7171 GIS 보통점검","2025-06-02 09:00","2025-06-02 18:00","2025-06-02 09:00","2025-06-02 18:00","연속"]
[66,"인천","직할","갈산S/S CB 7271","갈산S/S 가정갈산#2T/L 7271 GIS 보통점검","갈산S/S 가정갈산#2T/L 7271 GIS 보통점검","2025-06-09 09:00","2025-06-09 18:00","2025-06-09 09:00","2025-06-09 18:00","연속"]
[67,"인천","직할","갈산S/S CB 7372","갈산S/S #2M.Tr 1차 7372 GIS 보통점검","갈산S/S #2M.Tr 1차 7372 GIS 보통점검","2025-06-11 09:00","2025-06-11 18:00","2025-06-11 09:00","2025-06-11 18:00","연속"]
[68,"인천","직할","갈산S/S CB 7300","갈산S/S 7300 GIS 보통점검","갈산S/S 7300 GIS 보통점검 및 유압조작기 체크밸브 설치","2025-06-12 09:00","2025-06-12 18:00","2025-06-12 09:00","2025-06-12 18:00","연속"]
[69,"인천","직할","갈산S/S CB 7471","갈산S/S 가정갈산#3T/L 7471 GIS 보통점검","갈산S/S 가정갈산#3T/L 7471 GIS 보통점검","2025-06-18 09:00","2025-06-18 18:00","2025-06-18 09:00","2025-06-18 18:00","연속"]
[70,"인천","직할","갈산S/S CB 7172","갈산S/S 갈산신광명#1T/L 7172 GIS 보통점검","갈산S/S 갈산신광명#1T/L 7172 GIS 보통점검","2025-06-19 09:00","2025-06-19 18:00","2025-06-19 09:00","2025-06-19 18:00","연속"]
[71,"인천","직할","갈산S/S CB 7100","갈산S/S 7100 GIS 보통점검","갈산S/S 7100 GIS 보통점검","2025-06-20 09:00","2025-06-20 18:00","2025-06-20 09:00","2025-06-20 18:00","연속"]
[72,"인천","직할","갈산S/S CB 7472","갈산S/S #3M.Tr 1차 7472 GIS 보통점검","갈산S/S #3M.Tr 1차 7472 GIS 보통점검","2025-06-23 09:00","2025-06-23 18:00","2025-06-23 09:00","2025-06-23 18:00","연속"]
[73,"인천","직할","갈산S/S CB 7400","갈산S/S 7400 GIS 보통점검","갈산S/S 7400 GIS 보통점검","2025-06-24 09:00","2025-06-24 18:00","2025-06-24 09:00","2025-06-24 18:00","연속"]
[74,"인천","직할","갈산S/S CB 7571","갈산S/S 갈산신광명#3T/L 7571 GIS 보통점검","갈산S/S 갈산신광명#3T/L 7571 GIS 보통점검","2025-06-25 09:00","2025-06-25 18:00","2025-06-25 09:00","2025-06-25 18:00","연속"]
[75,"인천","직할","갈산S/S #1 Sh.R CB","갈산S/S  #1Sh.R 방열판 청소","갈산S/S  #1Sh.R 방열판 청소 및 추락방지장치 설치","2025-06-26 09:00","2025-06-26 18:00","2025-06-26 09:00","2025-06-26 18:00","연속"]
[76,"인천","직할","갈산S/S #2 Sh.R CB","갈산S/S  #2Sh.R 방열판 청소","갈산S/S  #2Sh.R 방열판 청소 및 추락방지장치 설치","2025-06-27 09:00","2025-06-27 18:00","2025-06-27 09:00","2025-06-27 18:00","연속"]
[77,"인천","직할","갈산S/S CB 7500","갈산S/S 7500 GIS 보통점검","갈산S/S 7500 GIS 보통점검","2025-06-30 09:00","2025-06-30 18:00","취소","취소","연속"]
[78,"인천","직할","갈산S/S #4 M.Tr","갈산S/S 종합예방진단시스템 증설공사","부싱누설전류 진단장치 제작관련 현장 설비확인","2025-06-30 09:00","2025-06-30 18:00","취소","취소","연속"]
[79,"인천","직할","갈산S/S CB 7371","갈산S/S 갈산신광명#2T/L 7371 GIS 보통점검","갈산S/S 갈산신광명#2T/L 7371 GIS 보통점검 및 유압조작기 체크밸브 설치","2025-06-16 09:00","2025-06-16 18:00","2025-06-16 09:00","2025-06-16 18:00","연속"]
[80,"경기북부","구리","미금S/S #3 Sh.R CB","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7379)","2025-06-04 09:00","2025-06-04 18:00","2025-06-04 09:00","2025-06-04 18:00","연속"]
[81,"경기북부","구리","미금S/S #2 M.Tr","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  M.Tr 부싱절연유 채유","2025-06-26 14:00","2025-06-26 18:00","2025-06-26 14:00","2025-06-26 18:00","연속"]
[82,"경기북부","구리","미금S/S #1 M.Tr","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  M.Tr 부싱절연유 채유","2025-06-26 09:00","2025-06-26 14:00","2025-06-26 09:00","2025-06-26 14:00","연속"]
[83,"경기북부","구리","미금S/S #5 Sh.R CB","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7579)","2025-06-25 09:00","2025-06-25 18:00","2025-06-25 09:00","2025-06-25 18:00","연속"]
[84,"경기북부","구리","미금S/S CB 7500","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검(7500CB)","2025-06-24 09:00","2025-06-24 18:00","2025-06-24 09:00","2025-06-24 18:00","연속"]
[85,"경기북부","구리","미금S/S STATCOM CB","25년 미금S/S  STATCOM 보통점검 공사","미금S/S  STATCOM 보통점검","2025-06-23 09:00","2025-07-04 18:00","2025-06-23 09:00","2025-07-04 18:00","연속"]
[86,"경기북부","구리","미금S/S CB 7571","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검(7571CB)","2025-06-23 09:00","2025-06-23 18:00","2025-06-23 09:00","2025-06-23 18:00","연속"]
[87,"경기북부","구리","미금S/S #4 M.Tr","24-25 구리전력지사 변전협력회사 총액공사","미금 DC 접지 발생 관련 현장 확인","2025-06-23 09:00","2025-06-23 18:00","2025-06-23 09:00","2025-06-23 18:00","연속"]
[88,"경기북부","구리","동서울미금#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사"," 신의정부-미금#2T/L 지지애자교체(병가구간)","2025-06-21 12:00","2025-06-21 18:00","2025-06-21 12:00","2025-06-21 18:00","연속"]
[89,"경기북부","구리","신의정부미금#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사"," 신의정부-미금#2T/L 지지애자교체","2025-06-21 07:00","2025-06-21 18:00","2025-06-21 07:00","2025-06-21 18:00","연속"]
[90,"경기북부","구리","동서울미금#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사"," 신의정부-미금#2T/L 지지애자교체(병가구간)","2025-06-21 07:00","2025-06-21 12:00","2025-06-21 07:00","2025-06-21 12:00","연속"]
[91,"경기북부","구리","미금성동#3 T/L","25~26년 지중송전 협력회사 공사(경기북부본부 직할)","미금S/S BPT 점검","2025-06-10 09:00","2025-06-11 18:00","2025-06-10 09:00","2025-06-11 18:00","연속"]
[92,"경기북부","구리","미금S/S #6 Sh.R CB","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7679)","2025-06-09 09:00","2025-06-09 18:00","2025-06-09 09:00","2025-06-09 18:00","연속"]
[93,"경기북부","구리","미금S/S #4 Sh.R CB","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7479)","2025-06-05 09:00","2025-06-05 18:00","2025-06-05 09:00","2025-06-05 18:00","연속"]
[94,"경기북부","구리","신가평S/S #4 Sh.R CB","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7671)","2025-06-16 09:00","2025-06-16 18:00","2025-06-16 09:00","2025-06-16 18:00","연속"]
[95,"경기북부","구리","신가평S/S CB 7800","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7800)","2025-06-18 09:00","2025-06-18 18:00","2025-06-18 09:00","2025-06-18 18:00","연속"]
[96,"경기북부","구리","신가평신의정부#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사"," 신가평-신의정부T/L 수평추락방지시설 설치","2025-06-28 07:00","2025-06-28 18:00","2025-06-28 07:00","2025-06-28 18:00","연속"]
[97,"경기북부","구리","신가평미금#1 T/L","구리송전협력회사 공사_피뢰기 설치"," 신가평-미금#1T/L( 신가평-신의정부#2T/L 병가구간) 피뢰시 설치(No.2~7) 18set","2025-06-21 07:00","2025-06-22 18:00","2025-06-21 07:00","2025-06-22 18:00","연속"]
[98,"경기북부","구리","신가평S/S CB 7872","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7872)","2025-06-17 09:00","2025-06-17 18:00","2025-06-17 09:00","2025-06-17 18:00","연속"]
[99,"경기북부","구리","신가평S/S #2 Sh.R CB","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7371)","2025-06-10 09:00","2025-06-10 18:00","2025-06-10 09:00","2025-06-10 18:00","연속"]
[100,"경기북부","구리","신포천S/S CB 7171","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7171)","2025-06-19 09:00","2025-06-19 18:00","2025-06-19 09:00","2025-06-19 18:00","연속"]
[101,"경기북부","구리","포천C/C CB 7171","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7171)","2025-06-02 09:00","2025-06-02 18:00","2025-06-02 09:00","2025-06-02 18:00","연속"]
[102,"경기북부","직할","동두천C/C CB 7671","경기북부 직할 및 양주전력TF 362kV GIS 보통, 정밀점검 공사","동두천CC 7671 GIS CB 정밀점검","2025-06-02 09:00","2025-06-05 18:00","2025-06-02 09:00","2025-06-05 18:00","연속"]
[103,"경기북부","직할","신의정부S/S #1 Sh.R CB","2024-25년 경기북부 직할 변전협력 총액공사","신의정부S/S  #1Sh.R 보통점검 및 WTI 점검","2025-06-19 09:00","2025-06-20 18:00","2025-06-19 09:00","2025-06-20 18:00","연속"]
[104,"경기북부","직할","신의정부S/S #2 Sh.R CB","2024-25년 경기북부 직할 변전협력 총액공사","신의정부S/S  #2Sh.R 냉각설비 세척작업","2025-06-23 09:00","2025-06-23 13:00","2025-06-23 09:00","2025-06-23 13:00","연속"]
[105,"경기북부","직할","신의정부S/S #3 Sh.R CB","2024-25년 경기북부 직할 변전협력 총액공사","신의정부S/S  #3Sh.R 냉각설비 세척작업","2025-06-23 13:00","2025-06-23 18:00","2025-06-23 13:00","2025-06-23 18:00","연속"]
[106,"경기북부","직할","신의정부양주#2 T/L"," 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  신의정부-양주#2 T/L No.1~97","2025-06-16 07:00","2025-06-27 18:00","취소","취소","연속"]
[107,"경기북부","직할","신의정부S/S CB 7371","경기북부 직할 및 양주전력TF 362kV GIS 보통,정밀점검 공사","신의정부SS 7371 GIS 보통점검","2025-06-16 09:00","2025-06-16 18:00","2025-06-16 09:00","2025-06-16 18:00","연속"]
[108,"경기북부","직할","신의정부양주#1 T/L"," 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  신의정부-양주#1T/L No.10~97","2025-06-02 07:00","2025-06-13 18:00","취소","취소","연속"]
[109,"경기북부","직할","양주S/S CB 7500","양주S/S 동두천CC-양주T/L 증설공사"," CB 증설 2대, CLR 설치 2조","2025-06-09 09:00","2025-12-19 18:00","2025-06-16 09:00","2025-12-19 18:00","연속"]
[110,"경기북부","직할","양주S/S #4 M.Tr","'24-25년 변전협력회사 총액공사","A,B상 보통점검 및 부싱채유","2025-06-09 09:00","2025-06-13 18:00","2025-06-09 09:00","2025-06-13 18:00","연속"]
[111,"경기북부","직할","양주S/S #4 Sh.R CB","'24-25년 변전협력회사 총액공사","물청소","2025-06-10 09:00","2025-06-10 18:00","2025-06-10 09:00","2025-06-10 18:00","연속"]
[112,"경기북부","직할","양주중부#2 T/L","24~25년 고양전력 가공송전협력회사 총액공사","불량애자교체","2025-06-12 07:00","2025-06-12 17:00","2025-06-12 07:00","2025-06-12 17:00","연속"]
[113,"경기","군포","서서울S/S #4 M.Tr","서서울S/S #4M.Tr GIS 보통,CVT,3차GPT 대체,부싱유채유","서서울S/S #4M.Tr 1차 7800,7872 GIS 보통점검,CVT 및 3차 GPT 대체, 1차 부싱유채유,추락방지장치 설치,방호벽 사다리 철거 시행","2025-06-11 09:00","2025-06-13 18:00","취소","취소","연속"]
[114,"경기","군포","서서울S/S CB 7700","서서울S/S 신온양-서서울#2T/L 7700 TIE GIS 보통점검","서서울S/S  신온양-서서울#2T/L 7700 TIE GIS 보통점검 시행","2025-06-10 09:00","2025-06-10 18:00","취소","취소","연속"]
[115,"경기","군포","서서울S/S CB 7400","서서울S/S 신온양-서서울#1T/L 7400 TIE GIS 조작시험","서서울S/S  신온양-서서울#1T/L 7400 TIE GIS 조작시험 시행","2025-06-02 09:00","2025-06-02 18:00","취소","취소","연속"]
[116,"경기","군포","서서울S/S CB 7472","서서울S/S 신온양-서서울#1T/L 7472 GIS 보통점검","서서울S/S  신온양-서서울#1T/L 7472 GIS 보통점검 시행","2025-06-05 09:00","2025-06-05 18:00","2025-06-05 09:00","2025-06-05 18:00","연속"]
[117,"경기","군포","서서울S/S CB 7772","서서울S/S 신온양-서서울#2T/L 7772 GIS 보통점검","서서울S/S  신온양-서서울#2T/L 7772 GIS 보통점검 시행","2025-06-09 09:00","2025-06-09 18:00","취소","취소","연속"]
[118,"경기","동부","곤지암여주복합#2 T/L","추락방지장치 설치공사(곤지암여주CC #2)","곤지암여주CC #2T/L 추락방지장치 설치 80기(잔여 7기)","2025-06-23 07:00","2025-06-23 18:00","2025-06-23 07:00","2025-06-23 18:00","연속"]
[119,"경기","동부","곤지암S/S #1 Sh.R CB","곤지암S/S  7179 GIS 보통점검차","곤지암:#1Sh.R(보통),7179(보통) *누유","2025-06-12 09:00","2025-06-12 18:00","2025-06-12 09:00","2025-06-12 18:00","연속"]
[120,"경기","동부","곤지암여주복합#1 T/L","추락방지장치 설치공사(곤지암여주CC #1)","곤지암여주CC #1T/L 추락방지장치 설치 80기(잔여 18기)","2025-06-20 07:00","2025-06-20 18:00","2025-06-20 07:00","2025-06-20 18:00","연속"]
[121,"경기","동부","신제천신충주T#1 T/L","추락방지장치 설치공사(신제천-여주CC)","신제천 여주CC 추락방지장치 설치 39기","2025-06-16 07:00","2025-06-17 18:00","2025-06-16 07:00","2025-06-17 18:00","연속"]
[122,"경기","동부","신충주여주복합#2 T/L","추락방지장치 설치공사(신충주여주복합#2T/L)","신충주여주복합#2T/L 추락방지장치 설치 39기","2025-06-18 07:00","2025-06-19 18:00","2025-06-18 07:00","2025-06-19 18:00","연속"]
[123,"경기","성남","신성남S/S #5 M.Tr","2025년 성남전력 170kV GIS 정밀점검공사","신성남) #5M.Tr 2차 GIS 정밀점검 병행)m.tr 보통점검 병행)7600, 7672 gis 조작시험, 절연열화, 3차 4589하자점검","2025-06-11 09:00","2025-06-13 18:00","2025-06-11 09:00","2025-06-13 18:00","연속"]
[124,"경기","성남","신수원S/S CB 7271","2025년 성남전력 362, 170kV GIS 보통점검공사","신수원)7271 GIS 보통점검","2025-06-02 09:00","2025-06-02 18:00","2025-06-02 09:00","2025-06-02 18:00","연속"]
[125,"경기","성남","신안성S/S #70 BUS"," 동용인S/S  GIS 설치공사","○ 신안성S/S : GIS(362kV 63kA 8000A) X 5대 설치 ○ 동용인S/S : GIS(362kV 63kA 6300/4000A) X 12대 설치","2025-06-26 09:00","2025-06-30 18:00","2025-06-26 09:00","2025-06-30 18:00","연속"]
[126,"경기","성남","신안성S/S #75 BUS"," 동용인S/S  GIS 설치공사","○ 신안성S/S : GIS(362kV 63kA 8000A) X 5대 설치 ○ 동용인S/S : GIS(362kV 63kA 6300/4000A) X 12대 설치","2025-06-20 09:00","2025-06-25 18:00","2025-06-20 09:00","2025-06-25 18:00","연속"]
[127,"경기","성남","신안성신수원#1 T/L","2025년 성남전력 362, 170kV GIS 보통점검공사","신안성)7900, 7972 gis보통점검, 절연열화 신수원)7271 gis보통점검,절연열화","2025-06-04 09:00","2025-06-05 18:00","2025-06-04 09:00","2025-06-05 18:00","연속"]
[128,"경기","성남","신용인S/S CB 7700","2025년 성남전력 362, 170kV GIS 보통점검공사","7700, 7772 gis 보통점검, 절연열화","2025-06-30 09:00","2025-07-01 18:00","2025-06-30 09:00","2025-07-01 18:00","연속"]
[129,"경기","성남","신용인S/S #1 Sh.R CB","2025년 성남전력 362, 170kV GIS 보통점검공사","7700, 7772 gis 보통점검, 절연열화","2025-06-30 09:00","2025-07-01 18:00","2025-06-30 09:00","2025-07-01 18:00","연속"]
[130,"경기","직할","화성S/S #3 M.Tr","화성S/S #3M.Tr 보통점검","화성 : #3M.Tr 보통점검(~12) - 1차 GIS 하자점검, 2차 보통점검 - LA 1,2,3차 A,B,C 초기 점검 - 추락방지장치 설치","2025-06-09 09:00","2025-06-12 18:00","2025-06-09 09:00","2025-06-12 18:00","연속"]
[131,"경기","직할","화성S/S CB 7400","화성S/S 아산-화성#2T/L 7400 GIS 하자점검","화성 : 아산-화성#2T/L GIS 하자점검(7400) - GIS 콘덴서 절연열화 측정","2025-06-20 09:00","2025-06-20 18:00","2025-06-20 09:00","2025-06-20 18:00","연속"]
[132,"경기","직할","화성신안산#2 T/L","활선선로 중장비 접근 방지 시스템 구축 공사","화성 : 화성-신안산#2T/L 활선선로 중장비 접근 방지 시스템 구축 공사","2025-06-17 09:00","2025-06-18 18:00","2025-06-17 09:00","2025-06-18 18:00","연속"]
[133,"경기","직할","화성S/S CB 7471","화성S/S 아산-화성#2T/L 7471 GIS 하자점검","화성 : 아산-화성#2T/L GIS 하자점검(7471) - GIS 콘덴서 절연열화 측정","2025-06-13 09:00","2025-06-13 18:00","2025-06-13 09:00","2025-06-13 18:00","연속"]
[134,"경기","평택","고덕S/S STATCOM (CB 7800, 7872)","2025년 평택전력 변전협력회사 총액공사(고덕S/S STATCOM)","고덕S/S  STATCOM M.Tr (A,B,C,예비) 보통점검","2025-06-09 09:00","2025-06-11 18:00","2025-06-09 09:00","2025-06-11 18:00","연속"]
[135,"경기","평택","고덕S/S STATCOM (CB 7800, 7872)","2025년 평택전력 변전협력회사 총액공사(고덕S/S STATCOM)","고덕S/S  STATCOM M.Tr (A,B,C,예비) 보통점검","2025-06-09 09:00","2025-06-11 18:00","2025-06-09 09:00","2025-06-11 18:00","연속"]
[136,"경기","평택","서안성S/S CB 7571","2025년 평택전력 GIS 보통 및 정밀점검공사(서안성SS 7571)","서안성S/S  고덕2서안성#1 T/L GIS(7571 단독) 보통점검","2025-05-30 09:00","2025-05-30 14:00","2025-05-30 09:00","2025-05-30 14:00","연속"]
[137,"경기","평택","서안성S/S CB 7500","2025년 평택전력 GIS 보통 및 정밀점검공사(서안성SS 7500)","서안성S/S  고덕2서안성#1 T/L GIS(7500 단독) 보통점검","2025-05-30 14:00","2025-05-30 18:00","2025-05-30 14:00","2025-05-30 18:00","연속"]
[138,"경기","평택","서안성S/S #4 M.Tr","M.Tr 보통, 정밀점검 공사(서안성S/S #4M.Tr)","서안성S/S  #4 M.Tr 보통점검","2025-06-11 09:00","2025-06-13 18:00","2025-06-11 09:00","2025-06-13 18:00","연속"]
[139,"경기","평택","서안성S/S CB 7671","2025년 평택전력 GIS 보통 및 정밀점검공사(서안성SS 7671)","서안성S/S  고덕2서안성#2 T/L GIS(7671 단독) 보통점검","2025-05-29 09:00","2025-05-29 14:00","2025-05-29 09:00","2025-05-29 14:00","연속"]
[140,"경기","평택","서안성S/S CB 7671","2025년 평택전력 GIS 보통 및 정밀점검공사(서안성SS 7671)","서안성S/S  고덕2서안성#2 T/L GIS(7671 단독) 보통점검","2025-05-29 09:00","2025-05-29 14:00","2025-05-29 09:00","2025-05-29 14:00","연속"]
[141,"경기","평택","서안성S/S CB 7571","2025년 평택전력 GIS 보통 및 정밀점검공사(서안성SS 7571)","서안성S/S  고덕2서안성#1 T/L GIS(7571 단독) 보통점검","2025-05-30 09:00","2025-05-30 14:00","2025-05-30 09:00","2025-05-30 14:00","연속"]
[142,"경기","평택","서안성S/S CB 7500","2025년 평택전력 GIS 보통 및 정밀점검공사(서안성SS 7500)","서안성S/S  고덕2서안성#1 T/L GIS(7500 단독) 보통점검","2025-05-30 14:00","2025-05-30 18:00","2025-05-30 14:00","2025-05-30 18:00","연속"]
[143,"경기","평택","서안성S/S CB 7600","2025년 평택전력 GIS 보통 및 정밀점검공사(서안성SS 7600)","서안성S/S  고덕2서안성#2 T/L GIS(7600 단독) 보통점검","2025-05-29 14:00","2025-05-29 18:00","2025-05-29 14:00","2025-05-29 18:00","연속"]
[144,"경기","평택","서안성S/S CB 7600","2025년 평택전력 GIS 보통 및 정밀점검공사(서안성SS 7600)","서안성S/S  고덕2서안성#2 T/L GIS(7600 단독) 보통점검","2025-05-29 14:00","2025-05-29 18:00","2025-05-29 14:00","2025-05-29 18:00","연속"]
[145,"경기","평택","평택T/P CB 7B72","평택T/P  신평택 #1S/T 1차 GIS(7B72) 보통점검 ","평택T/P  신평택 #1S/T 1차 GIS(7B72) 보통점검 ","2025-06-10 09:00","2025-06-10 18:00","2025-06-10 09:00","2025-06-10 18:00","연속"]
[146,"경기","평택","평택T/P CB 7971","평택T/P  화성-신평택CC#2T/L GIS(7971) 보통점검","평택T/P  화성-신평택CC#2T/L GIS(7971) 보통점검","2025-06-18 09:00","2025-06-18 18:00","2025-06-18 09:00","2025-06-18 18:00","연속"]
[147,"경기","평택","평택T/P CB 7A72","평택T/P  신평택#2G/T 1차 GIS(7A72) 보통점검","평택T/P  신평택#2G/T 1차 GIS(7A72) 보통점검","2025-06-11 09:00","2025-06-11 18:00","2025-06-11 09:00","2025-06-11 18:00","연속"]
[148,"경기","평택","평택T/P CB 7A71","평택T/P  화성-신평택CC#1T/L GIS(7A71) 보통점검","평택T/P  화성-신평택CC#1T/L GIS(7A71) 보통점검","2025-06-19 09:00","2025-06-19 18:00","2025-06-19 09:00","2025-06-19 18:00","연속"]
[149,"경기","성남","신성남S/S #2 M.Tr","2025년 성남전력 M.Tr 보통,154kV 정밀/보통점검공사","2025년 성남전력 M.Tr 보통,154kV 정밀/보통점검공사","2025-06-06 09:00","2025-06-06 14:00","2025-06-06 09:00","2025-06-06 14:00","연속"]
[150,"경기","성남","신성남S/S #3 M.Tr","2025년 성남전력 M.Tr 보통,154kV 정밀/보통점검공사","2025년 성남전력 M.Tr 보통,154kV 정밀/보통점검공사","2025-06-06 14:00","2025-06-06 18:00","2025-06-06 14:00","2025-06-06 18:00","연속"]
[151,"강원","강릉","신양양S/S #3 M.Tr","신양양S/S 170kV GIS 증설 공사","170kV GIS 증설 관련 안전조치 휴전","2025-06-30 10:00","2025-07-11 18:00","2025-06-30 10:00","2025-07-11 18:00","매일"]
[152,"강원","강릉","신양양S/S #2 M.Tr","신양양S/S STATCOM용 23kV SIS 설치공사","#2M.Tr 3차 SIS BANK 신설 관련 전력케이블 포설 및 접속","2025-06-04 08:00","2025-06-06 17:00","2025-06-04 08:00","2025-06-06 17:00","연속"]
[153,"강원","강릉","신양양양양PP T/L","2025년 강릉전력지사 변전협력회사 공사"," CVT, LA 대체, 재폐로 회로보완","2025-06-04 10:00","2025-06-05 18:00","2025-06-04 10:00","2025-06-05 18:00","연속"]
[154,"강원","동해","동해S/S CB 7272","2024~25년 동해전력지사 변전협력회사공사","7272CB 장기미동작 차단기조작시험","2025-06-12 14:00","2025-06-12 18:00","2025-06-12 14:00","2025-06-12 18:00","연속"]
[155,"강원","동해","동해S/S CB 7372","2024~25년 동해전력지사 변전협력회사공사","7372CB 장기미동작 차단기조작시험","2025-06-12 09:00","2025-06-12 14:00","2025-06-12 09:00","2025-06-12 14:00","연속"]
[156,"강원","동해","동해안인개폐소#2 T/L"," 동해-안인개폐소T/L 국산불량애자 교체공사","국산불량애자 교체","2025-06-16 07:00","2025-06-22 18:00","2025-06-16 07:00","2025-06-22 18:00","연속"]
[157,"강원","동해","삼척G/P #2 M.Tr","2024~25년 동해전력지사 변전협력회사공사","부싱유 채취","2025-06-10 09:00","2025-06-10 13:00","2025-06-10 09:00","2025-06-10 13:00","연속"]
[158,"강원","동해","삼척G/P #3 M.Tr","2024~25년 동해전력지사 변전협력회사공사","부싱유 채취","2025-06-10 13:00","2025-06-10 18:00","2025-06-10 13:00","2025-06-10 18:00","연속"]
[159,"강원","태백","신태백한울NP#2 T/L","2024~2025년 태백전력지사 송전 협력회사 공사"," 신태백-한울NP2 #2 T/L 수평추락방지장치 및 폴리머 점퍼지지애자 설치","2025-06-09 07:00","2025-06-27 18:00","2025-06-09 07:00","2025-06-27 18:00","매일"]
[160,"충북","직할","신중부남청주#2 T/L"," 신청주S/S 건설사업"," 신중부-신청주 #2T/L,  신청주-남청주#2T/L 계통연계","2025-06-16 09:00","2025-06-20 18:00","2025-06-16 09:00","2025-06-20 18:00","연속"]
[161,"충북","직할","신중부남청주#1 T/L"," 신청주S/S 건설사업"," 신중부-신청주 #1T/L,  신청주-남청주#1T/L 계통연계","2025-06-09 09:00","2025-06-14 18:00","2025-06-09 09:00","2025-06-14 18:00","연속"]
[162,"충북","직할","서안성신진천#2 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 정비(4기), 스페이서 교체(1기), 조류착지방지장치 설치(2기)","2025-06-13 07:00","2025-06-13 18:00","취소","취소","연속"]
[163,"충북","직할","신진천S/S #4 M.Tr","25년 상반기 충북본부 직할 GIS 정밀점검 공사","신진천S/S 154kV #3Sh.C GIS 정밀점검 후 무부하가압용","2025-06-11 14:00","2025-06-11 15:00","2025-06-11 14:00","2025-06-11 15:00","연속"]
[164,"충북","직할","신진천S/S #4 M.Tr","25년 상반기 충북본부 직할 GIS 정밀점검 공사","신진천S/S 154kV #7Sh.C GIS 정밀점검 후 무부하가압용","2025-06-13 17:00","2025-06-13 18:00","2025-06-11 14:00","2025-06-11 15:00","연속"]
[165,"충북","직할","신진천S/S #4 M.Tr","25년 상반기 충북본부 직할 GIS 정밀점검 공사","신진천S/S 154kV #8Sh.C GIS 정밀점검 후 무부하가압용","2025-06-18 15:00","2025-06-18 16:00","2025-06-18 10:00","2025-06-18 16:00","연속"]
[166,"충북","청주","남청주S/S #2 M.Tr","24-25년 청주전력지사 변전부 총액공사","부싱 절연유 가스분석 C상 2차 부싱 이상 추적분석","2025-06-04 08:00","2025-06-04 18:00","2025-06-04 08:00","2025-06-04 18:00","연속"]
[167,"충북","청주","남청주S/S #3 M.Tr","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 하자점검(7672)","2025-06-25 10:00","2025-06-25 18:00","2025-06-25 10:00","2025-06-25 18:00","연속"]
[168,"충북","청주","세종남청주#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 하자점검(7671,7600) CVT 점검","2025-06-23 10:00","2025-06-24 18:00","2025-06-23 10:00","2025-06-24 18:00","연속"]
[169,"충북","청주","남청주S/S #4 M.Tr","24~25년 청주전력지사 변전협력회사 공사","부싱 절연유 채유 20년 이상 사용 부싱","2025-06-05 09:00","2025-06-05 13:00","2025-06-25 10:00","2025-06-25 18:00","연속"]
[170,"충북","청주","신옥천S/S CB 7500","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-06-18 08:00","2025-06-18 18:00","2025-06-18 08:00","2025-06-18 18:00","연속"]
[171,"충북","청주","신옥천S/S CB 7572","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-06-17 08:00","2025-06-17 18:00","2025-06-17 08:00","2025-06-17 18:00","연속"]
[172,"충북","충주","신제천신충주#2 T/L","2024~2025년 충주전력지사 송전협력회사 공사","2024~2025년 충주전력지사 송전협력회사 공사 압축인류클램프 교체(No.157) 및 항공장애표시구 설치(No.23~No.28)","2025-06-09 07:00","2025-06-13 18:00","취소","취소","매일"]
[173,"충북","충주","신제천S/S #2 BUS","신제천S/S 362KV GIS PD 제작사 하자보수","신제천S/S  #2BUS DS(7252,7352,7452)DS PD 하자보수","2025-06-09 09:00","2025-06-13 18:00","취소","취소","연속"]
[174,"충북","충주","신제천S/S #2 M.Tr","'24-25년 충주전력지사 변전정비 총액공사","신제천S/S  #2 M.Tr 보통점검 및 2차 GIS 보통점검","2025-06-09 09:00","2025-06-10 18:00","2025-06-09 09:00","2025-06-10 18:00","연속"]
[175,"충북","충주","신제천S/S #1 BUS","신제천S/S 362KV GIS PD 제작사 하자보수공사","신제천S/S  #1BUS DS(7651,7751,7951,7A51) PD 하자보수","2025-06-16 09:00","2025-06-21 18:00","취소","취소","연속"]
[176,"충북","충주","신제천신영주#2 T/L"," 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.1~165)","2025-06-02 07:00","2025-06-15 16:00","취소","취소","매일"]
[177,"충북","충주","신제천S/S #2 BUS","신제천S/S 362KV GIS PD 제작사 하자보수공사","신제천S/S  #2BUS DS(7652,7752,7952,7A52)하자보수","2025-06-23 09:00","2025-06-28 18:00","취소","취소","연속"]
[178,"충북","충주","신제천S/S #1 BUS","신제천S/S 362KV GIS PD 제작사 하자보수","신제천S/S  #1BUS DS(7251,7351,7451) PD 하자보수","2025-06-02 09:00","2025-06-06 18:00","취소","취소","연속"]
[179,"충북","충주","신제천신충주T#1 T/L"," 신용인-동서울 등 16개 T/L 추락방지장치 설치공사"," 신제천-여주CC T/L 추락방지장치 설치공사 - 신제천-여주CC 연계선로로 인한 휴전(신충주 T분기 실작업 없음)","2025-06-18 07:00","2025-06-19 18:00","취소","취소","연속"]
[180,"충북","충주","신충주S/S #4 M.Tr","신충주S/S 154kV 충주에코파크T/L 증설공사","신충주S/S 154kV 충주에코파크T/L 증설공사(#2BUS 무부하 가압용)","2025-06-27 09:00","2025-06-28 18:00","2025-06-19 09:00","2025-06-20 18:00","연속"]
[181,"대전세종충남","서산","당진T/P #72 M.Tr","당진화력S/S 차단기 조작시험 및 전자변 교체","(5월 휴전취소시) (즉시가압 불가) 당진화력S/S 차단기 조작시험 -  #72Tie Tr 1차 CB(7371) 개폐타임 측정 -  #72Tie Tr 2차 CB(6244) 개폐타임 측정 및 전자변 교체 -  #72Tie Tr 1차 - Tie CB(7300) 개폐타임 측정","2025-06-09 09:00","2025-06-09 18:00","2025-06-09 09:00","2025-06-09 18:00","연속"]
[182,"대전세종충남","서산","당진T/P #71 M.Tr","2024~2025년 변전협력회사 총액공사","당진T/P #71 Tie-Tr A~C, 예비상 부싱 절연유 채유[5월 휴전 취소 시]","2025-06-18 09:00","2025-06-19 18:00","2025-06-18 09:00","2025-06-19 18:00","연속"]
[183,"대전세종충남","서산","북당진현대제철 T/L"," 신송산분기T/L 건설공사","No.70 전선 이동(가철탑→본철탑) No.69∼No.71 전선 교체","2025-06-16 07:00","2025-06-28 18:00","2025-06-16 07:00","2025-06-28 18:00","연속"]
[184,"대전세종충남","서산","북당진S/S CB 7272","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 북당진S/S  7272 GIS 보통점검","2025-06-10 09:30","2025-06-11 18:00","2025-06-10 09:30","2025-06-11 18:00","연속"]
[185,"대전세종충남","서산","신당진개폐소태안TP#2 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-현대제철T/L 병가선로,  신당진개폐소-현대제철T/L 휴전 미승인시 휴전 취소 요청","2025-06-30 08:00","2025-06-30 18:00","2025-06-30 08:00","2025-06-30 18:00","연속"]
[186,"대전세종충남","서산","신당진개폐소현대제철 T/L"," 신송산분기T/L 건설공사","No.70 전선 이동(가철탑→본철탑) No.69∼No.71 전선 교체","2025-06-02 07:00","2025-06-14 18:00","2025-06-02 07:00","2025-06-14 18:00","연속"]
[187,"대전세종충남","서산","신당진신당진개폐소#1 T/L","신당진S/S  차단기 조작시험","(즉시가압 가능) 신당진S/S  신당진-연락#1T/L 차단기 개폐타임 측정","2025-06-19 09:00","2025-06-19 18:00","2025-06-19 09:00","2025-06-19 18:00","연속"]
[188,"대전세종충남","서산","신당진개폐소현대제철 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-태안화력#2T/L 병가선로,  신당진개폐소-태안화력#2T/L 휴전 미승인시 휴전 취소 요청","2025-06-30 08:00","2025-06-30 18:00","2025-06-30 08:00","2025-06-30 18:00","연속"]
[189,"대전세종충남","서산","신당진S/S CB 7172","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 신당진S/S  7172 GIS 보통점검","2025-06-12 09:30","2025-06-13 18:00","2025-06-12 09:30","2025-06-13 18:00","연속"]
[190,"대전세종충남","서산","신당진S/S CB 7100","신당진S/S  차단기 조작시험","(즉시가압 가능) 신당진S/S  7171-신서산#1T/L 차단기(7100) 개폐타임 측정","2025-06-05 09:00","2025-06-05 18:00","2025-06-05 09:00","2025-06-05 18:00","연속"]
[191,"대전세종충남","서산","신당진S/S CB 7672","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 신당진  7672 GIS 보통점검","2025-06-24 09:30","2025-06-25 18:00","2025-06-24 09:30","2025-06-25 18:00","연속"]
[192,"대전세종충남","서산","신당진S/S CB 7600","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 신당진  7600 GIS 보통점검","2025-06-26 09:30","2025-06-27 18:00","2025-06-26 09:30","2025-06-27 18:00","연속"]
[193,"대전세종충남","서산","신서산S/S CB 7872","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 신서산S/S  7872 GIS 보통점검","2025-06-03 09:30","2025-06-04 18:00","2025-06-03 09:30","2025-06-04 18:00","연속"]
[194,"대전세종충남","서산","태안T/P CB 7A00","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 태안T/P  7A00 GIS 보통점검","2025-06-19 09:30","2025-06-20 18:00","2025-06-19 09:30","2025-06-20 18:00","연속"]
[195,"대전세종충남","서산","태안T/P CB 7A71","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 태안T/P  7A71 GIS 보통점검","2025-06-17 09:30","2025-06-18 18:00","2025-06-17 09:30","2025-06-18 18:00","연속"]
[196,"대전세종충남","서산","태안T/P #1 M.Tr","태안T/P 154kV 차단기 조작시험","(즉시가압 가능) 태안T/P  #1 M.Tr 2차 차단기 개폐타임 측정","2025-06-18 09:00","2025-06-18 18:00","2025-06-18 09:00","2025-06-18 18:00","연속"]
[197,"대전세종충남","세종","세종S/S #1 BUS","세종S/S  #1,2Sh.R 증설공사","○  GIS 주모선 도킹 ○ #1BUS 인터록시험 ○ #1BUS 무부하가압","2025-06-30 09:00","2025-07-04 14:00","2025-06-30 09:00","2025-07-04 14:00","연속"]
[198,"대전세종충남","천안","신온양서서울#1 T/L","(5월 취소시)신온양S/S  #78Bay B/F PNL 대체","(즉시가압불가)신온양S/S  #78Bay 노후 B/F PNL 대체","2025-06-30 09:00","2025-07-04 18:00","2025-06-30 07:00","2025-07-04 18:00","연속"]
[199,"대전세종충남","천안","신온양서서울#1 T/L"," 신온양-서서울T/L 추락방지장치 설치공사","[즉시가압가능] 신온양-서서울T/L #T/L No. 1 ~ 25 추락방지장치 설치","2025-06-30 07:00","2025-07-04 18:00","2025-06-30 07:00","2025-07-04 18:00","매일"]
[200,"대전세종충남","천안","신온양S/S #4 M.Tr","(5월 취소시)신온양S/S  #77Bay B/F PNL 대체","(5월 취소시)(즉시가압불가)(장기미교체 대상)신온양S/S  #77Bay 노후 B/F PNL 대체 +(신온양-서서울#2T/L 취소시) 신온양S/S  #4M.Tr 부싱절연유 채유","2025-06-23 09:00","2025-06-27 18:00","취소","취소","연속"]
[201,"대전세종충남","천안","신온양서서울#2 T/L","(5월 취소시)신온양S/S  #77Bay B/F PNL 대체","(5월 취소시)(즉시가압불가)(장기미교체 대상)신온양S/S  #77Bay 노후 B/F PNL 대체","2025-06-23 09:00","2025-06-27 18:00","취소","취소","연속"]
[202,"대전세종충남","천안","신온양서서울#2 T/L"," 신온양-서서울T/L 추락방지장치 설치공사","[즉시가압가능] 신온양-서서울T/L #T/L No. 1 ~ 25 추락방지장치 설치","2025-06-23 07:00","2025-06-27 18:00","취소","취소","매일"]
[203,"대전세종충남","천안","신온양신탕정#2 T/L","(5월 취소시)  신온양신탕정#2T/L 보호반 대체","(5월 취소시)(즉시가압불가)(장기미교체대상)신온양S/S #78B/F 보호반,신온양, 신탕정S/S  신온양신탕정#2T/L 보호반 대체 +(신온양-서서울#1T/L 휴전 취소시)  신온양신탕정#2T/L 보호반 대체","2025-06-30 09:00","2025-07-04 18:00","2025-06-30 09:00","2025-07-04 18:00","연속"]
[204,"대전세종충남","천안","신서산아산#2 T/L"," 신서산-아산T/L 추락방지장치 설치공사, 정밀점검(4회선)","[즉시가압가능] 신서산-아산T/L No. 74 ~ 113 추락방지장치 설치 [병가철탑](상단)신서산-아산#2No.74~113,(하단)아산-합덕#2No.13~52 [병행작업]  신서산-신당진 등 2개T/L 4회선 병가철탑 정밀점검 (서산전력 송전부)","2025-06-09 07:00","2025-06-15 18:00","2025-06-09 07:00","2025-06-15 18:00","매일"]
[205,"대전세종충남","천안","신서산아산#1 T/L"," 신서산-아산T/L 추락방지장치 설치공사, 정밀점검","[즉시가압가능] 신서산-아산T/L No. 74 ~ 113 추락방지장치 설치 [병가철탑](상단)신서산-아산#1No.74~113,(하단)아산-합덕#1No.13~52 [병행작업]  신서산-신당진 등 2개T/L 4회선 병가철탑 정밀점검 (서산전력 송전부)","2025-06-02 07:00","2025-06-08 18:00","2025-06-02 07:00","2025-06-08 18:00","매일"]
[206,"대전세종충남","청양","보령C/C #70 BUS","보령복합S/Y  장기사용 GIS 교체 및 SW 증설","- (기설)BUS SEC 70-71-0 철거 및 GIB 설치","2025-06-04 09:00","2025-06-18 18:00","2025-06-04 09:00","2025-06-18 18:00","연속"]
[207,"대전세종충남","청양","청양S/S CB 7672","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  청양-보령화력#2T/L GIS 차단기 조작시험 (7672)","2025-06-16 10:00","2025-06-16 14:00","2025-06-16 10:00","2025-06-16 14:00","연속"]
[208,"대전세종충남","청양","신옥천청양 T/L","[송전][즉시가압O] 신옥천-청양등8개T/L 추락방지설치공사","[송전][즉시가압O] 신옥천-청양 등 8개T/L 추락방지 설치공사","2025-06-09 07:00","2025-06-18 11:00","취소","취소","매일"]
[209,"대전세종충남","청양","청양S/S CB 7200","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  청양신보령-청양보령복합T/L TIE GIS 차단기 조작시험 (7200)","2025-06-12 14:00","2025-06-12 18:00","취소","취소","연속"]
[210,"대전세종충남","청양","청양S/S CB 7500","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  청양신탕정#2T/L-TIE GIS 차단기 조작시험 (7500)","2025-06-17 14:00","2025-06-17 18:00","2025-06-17 14:00","2025-06-17 18:00","연속"]
[211,"대전세종충남","청양","청양S/S CB 7272","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  청양-보령복합T/L GIS 차단기 조작시험 (7272)","2025-06-16 10:00","2025-06-16 14:00","2025-06-16 10:00","2025-06-16 14:00","연속"]
[212,"전북","군산","군산신김제#2 T/L"," 군산-신김제#2T/L 품질불량 의심 접속함 교체공사"," 군산-신김제#2T/L(D) J/B#4 A상 중간접속함 해체 및 재접속","2025-06-09 09:00","2025-06-13 18:00","취소","취소","연속"]
[213,"전북","군산","군산S/S #1 Sh.R CB","군산변전소  GIS 대체공사(기기) (중복)","○ 362kV GIS 4000A 40kA × 10CB(50kA) 교체 ○ 기타 부대공사 × 1식","2025-06-09 18:00","2025-06-10 18:00","2025-06-09 18:00","2025-06-10 18:00","연속"]
[214,"전북","군산","새만금S/S CB 7271","24~25년 군산전력지사 변전협력회사 총액공사","- 공압식차단기 전자변 교체","2025-06-23 09:00","2025-06-23 18:00","2025-06-23 09:00","2025-06-23 18:00","연속"]
[215,"전북","군산","새만금S/S CB 7272","24~25년 군산전력지사 변전협력회사 총액공사","- 공압식차단기 전자변 교체","2025-06-25 09:00","2025-06-25 18:00","2025-06-25 09:00","2025-06-25 18:00","연속"]
[216,"전북","군산","새만금S/S CB 7200","24~25년 군산전력지사 변전협력회사 총액공사","- 공압식차단기 전자변 교체","2025-06-23 09:00","2025-06-23 18:00","2025-06-23 09:00","2025-06-23 18:00","연속"]
[217,"전북","직할","신옥천무주양수 T/L","새롬제  송전선로보호반 성능개선","새롬제  송전선로보호반 성능개선","2025-06-04 09:00","2025-06-04 18:00","2025-06-04 09:00","2025-06-04 18:00","연속"]
[218,"전북","직할","신남원신광주#1 T/L","'24~'25년 전북직할 가공송전 협력회사 공사(계속)","○  신남원-신광주T/L 피뢰기 설치공사(계속) - No.1~115","2025-06-02 07:30","2025-06-09 17:00","취소","취소","매일"]
[219,"전북","직할","신남원신광주#2 T/L","'24~'25년 전북직할 가공송전 협력회사 공사(계속)","○  신남원-신광주T/L 피뢰기 설치공사(계속) - No.1~115","2025-06-10 07:30","2025-06-17 17:00","취소","취소","매일"]
[220,"전북","직할","신남원한빛NP#1 T/L"," 154kV 고창-영광T/L 선종교체공사(안전이격)"," 154kV 고창-영광T/L 선종교체공사(안전이격)","2025-06-23 07:00","2025-07-18 18:00","2025-06-23 07:00","2025-07-18 18:00","매일"]
[221,"광주전남","강진","신강진S/S #3 M.Tr","2024-2025년 강진전력지사 변전협력회사 공사","가. 신강진S/S #3M.Tr\n, B, C 보통점검 나. 신강진S/S #3M.Tr 2차 LA A,B,C 보통점검 ※ 거래소 요청 시 휴전일정 협의 가능","2025-06-10 08:00","2025-06-12 18:00","2025-06-10 08:00","2025-06-12 18:00","연속"]
[222,"광주전남","강진","신강진광양#1 T/L","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","신강진S/S 신강진-광양 #1T/L GIS 보통점검","2025-06-13 09:00","2025-06-13 18:00","2025-06-13 09:00","2025-06-13 18:00","연속"]
[223,"광주전남","강진","신화순신강진#2 T/L","2024~25년 강진전력지사 송전협력회사 공사","철탑 추락방지장치 설치공사","2025-06-16 07:00","2025-06-20 18:00","2025-06-16 07:00","2025-06-20 18:00","매일"]
[224,"광주전남","강진","신강진광양#2 T/L","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","신강진S/S 신강진-광양 #2T/L GIS 보통점검","2025-06-16 09:00","2025-06-16 18:00","2025-06-16 09:00","2025-06-16 18:00","연속"]
[225,"광주전남","강진","신강진S/S #4 M.Tr","2024-2025년 강진전력지사 변전협력회사 공사","가. 신강진S/S #4M.Tr 1차 부싱 절연열화 측정 나. 신강진S/S #4M.Tr 3차 LA A,B,C, MAIN VCB, DS 보통점검 ※ 거래소 요청 시 휴전일정 협의 가능","2025-06-09 08:00","2025-06-09 18:00","2025-06-09 08:00","2025-06-09 18:00","연속"]
[226,"광주전남","강진","신강진S/S #3 M.Tr","'24~25년 강진전력지사 변전협력회사 공사","신강진S/S  74Bay B/F반 교체","2025-06-09 08:00","2025-06-20 18:00","취소","취소","연속"]
[227,"광주전남","강진","신강진광양#1 T/L","'24~25년 강진전력지사 변전협력회사 공사","신강진S/S  74Bay B/F반 교체","2025-06-09 08:00","2025-06-20 18:00","취소","취소","연속"]
[228,"광주전남","강진","신화순신강진#1 T/L","2024~25년 강진전력지사 송전협력회사 공사","철탑 추락방지장치 설치공사","2025-06-09 07:00","2025-06-13 18:00","2025-06-09 07:00","2025-06-13 18:00","매일"]
[229,"광주전남","광주","신광주S/S CB 7872","2025년 광주전력지사 변전협력회사 공사","1. 2025년 광주전력지사 변전협력회사 공사 - 신광주S/S  #4M.Tr 7800CB, 7872CB 조작시험 2. (발주) 2025년 광주전력지사 170kV GIS 점검공사 - 154kV #4M.Tr 2차 GIS 보통점검","2025-06-16 08:00","2025-06-16 13:00","2025-06-16 08:00","2025-06-16 13:00","연속"]
[230,"광주전남","광주","신광주S/S #1 BUS","장기사용  #1BUS 모선보호반 교체","장기사용  #1BUS 모선보호반 교체","2025-06-16 08:00","2025-06-18 18:00","취소","취소","연속"]
[231,"광주전남","광주","신광주S/S CB 7371","2025년 광주전력지사 변전협력회사 공사","신광주S/S  신남원-신광주 #2T/L 7300CB, 7371CB 조작시험","2025-06-13 13:00","2025-06-13 18:00","2025-06-13 13:00","2025-06-13 18:00","연속"]
[232,"광주전남","광주","신광주S/S CB 7300","2025년 광주전력지사 변전협력회사 공사","신광주S/S  신남원-신광주 #2T/L 7300CB, 7371CB 조작시험","2025-06-13 08:00","2025-06-13 13:00","2025-06-13 08:00","2025-06-13 13:00","연속"]
[233,"광주전남","광주","신광주신화순#2 T/L","'25년 광주전력지사 변전협력회사 공사","신광주S/S  신광주-신화순 #2T/L CVT, LA보통점검 및 7571CB, 7500CB 조작시험 신화순S/S  신광주-신화순 #2T/L CVT 보통점검 및 7871CB, 7800CB 조작시험","2025-06-10 08:00","2025-06-10 18:00","2025-06-10 08:00","2025-06-10 18:00","연속"]
[234,"광주전남","광주","신광주신화순#1 T/L","'25년 광주전력지사 변전협력회사 공사","신광주S/S  신광주-신화순 #1T/L CVT보통점검 및 7671CB, 7600CB 조작시험 신화순S/S  신광주-신화순 #1T/L CVT 보통점검 및 7771CB, 7700CB 조작시험","2025-06-09 08:00","2025-06-09 18:00","2025-06-09 08:00","2025-06-09 18:00","연속"]
[235,"광주전남","광주","신광주S/S CB 7672","피앤씨테크 보호반 성능개선","신광주S/S  76Bay B/F PNL 보호반 성능개선","2025-06-05 08:00","2025-06-05 18:00","2025-06-05 08:00","2025-06-05 18:00","연속"]
[236,"광주전남","광주","신광주S/S #4 M.Tr","2025년 광주전력지사 변전협력회사 공사","1. 2025년 광주전력지사 변전협력회사 공사 - 신광주S/S  #4M.Tr 7800CB, 7872CB 조작시험 2. (발주) 2025년 광주전력지사 170kV GIS 점검공사 - 154kV #4M.Tr 2차 GIS 보통점검","2025-06-16 09:00","2025-06-16 18:00","2025-06-16 09:00","2025-06-16 18:00","연속"]
[237,"광주전남","광주","신광주S/S CB 7671","피앤씨테크 보호반 성능개선","신광주S/S  76Bay B/F PNL 보호반 성능개선","2025-06-05 08:00","2025-06-05 18:00","2025-06-05 08:00","2025-06-05 18:00","연속"]
[238,"광주전남","광주","신광주S/S CB 7600","피앤씨테크 보호반 성능개선","신광주S/S  76Bay B/F PNL 보호반 성능개선","2025-06-05 08:00","2025-06-05 18:00","2025-06-05 08:00","2025-06-05 18:00","연속"]
[239,"광주전남","광주","신광주S/S CB 7800","2025년 광주전력지사 변전협력회사 공사","1. 2025년 광주전력지사 변전협력회사 공사 - 신광주S/S  #4M.Tr 7800CB, 7872CB 조작시험 2. (발주) 2025년 광주전력지사 170kV GIS 점검공사 - 154kV #4M.Tr 2차 GIS 보통점검","2025-06-16 13:00","2025-06-16 18:00","2025-06-16 13:00","2025-06-16 18:00","연속"]
[240,"광주전남","광주","신광주S/S CB 7271","2025년 광주전력지사 변전협력회사 공사","신광주S/S  신광주-한빛NP #2T/L 7200CB, 7271CB 조작시험","2025-06-17 08:00","2025-06-17 13:00","2025-06-17 08:00","2025-06-17 13:00","연속"]
[241,"광주전남","광주","신광주S/S CB 7200","2025년 광주전력지사 변전협력회사 공사","신광주S/S  신광주-한빛NP #2T/L 7200CB, 7271CB 조작시험","2025-06-17 13:00","2025-06-17 18:00","2025-06-17 13:00","2025-06-17 18:00","연속"]
[242,"광주전남","광주","신남원신광주#2 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 조류착지방지장치 설치 시행 - 신남원-신광주#2 116~164호","2025-06-25 08:00","2025-06-30 18:00","취소","취소","매일"]
[243,"광주전남","광주","신광주S/S #3 M.Tr","3M.Tr 변압기보호반 장기사용 교체","3M.Tr 변압기보호반 장기사용 교체","2025-06-23 08:00","2025-06-27 18:00","2025-06-23 08:00","2025-06-27 18:00","연속"]
[244,"광주전남","광주","신광주S/S #2 BUS","장기사용  #2BUS 모선보호반 교체","장기사용  #2BUS 모선보호반 교체","2025-06-19 08:00","2025-06-21 18:00","취소","취소","연속"]
[245,"광주전남","광주","신남원신광주#1 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 조류착지방지장치 설치 시행 - 신남원-신광주#1 116~164호","2025-06-19 08:00","2025-06-24 18:00","취소","취소","매일"]
[246,"광주전남","광주","신광주S/S #2 M.Tr","'25년 광주전력지사 변전협력회사 공사"," #2M.Tr 초기점검","2025-06-18 09:00","2025-06-20 18:00","2025-06-18 09:00","2025-06-20 18:00","연속"]
[247,"광주전남","광주","신화순신강진#1 T/L","'25년 광주전력지사 변전협력회사 공사","신화순S/S 신화순-신강진 #1T/L CVT 보통점검","2025-06-11 08:00","2025-06-11 18:00","2025-06-11 08:00","2025-06-11 18:00","연속"]
[248,"광주전남","광주","신화순S/S CB 7900","2025년 광주전력지사 변전협력회사 공사","신화순S/S  신화순-신강진#2T/L 7900CB, 7971CB 조작시험","2025-06-12 08:00","2025-06-12 13:00","2025-06-12 08:00","2025-06-12 13:00","연속"]
[249,"광주전남","광주","신화순S/S CB 7971","2025년 광주전력지사 변전협력회사 공사","신화순S/S  신화순-신강진#2T/L 7900CB, 7971CB 조작시험","2025-06-12 13:00","2025-06-12 18:00","2025-06-12 13:00","2025-06-12 18:00","연속"]
[250,"광주전남","광주","신화순S/S #1 Sh.R CB","'25년 광주전력지사 변전협력회사 공사","신화순S/S  Sh.R 차단기 점검","2025-06-13 09:00","2025-06-13 18:00","2025-06-13 09:00","2025-06-13 18:00","연속"]
[251,"광주전남","목포","한빛2NP한빛3NP#4 T/L","와이피피제 보호배전반 성능개선 시행","DS 상태 접점 감시 회로 변경 작업시간 : 1~2시간 / 시험시간 : 1시간 휴전일자 변경 가능 야간 작업 가능","2025-06-16 18:00","2025-06-16 21:00","2025-06-16 18:00","2025-06-16 21:00","연속"]
[252,"광주전남","목포","한빛2N/P CB 7771","한빛3호기 계획예방정비(O/H) 휴전","한빛3호기 계획예방정비(O/H) 휴전","2025-06-19 08:00","2025-08-19 18:00","2025-06-19 08:00","2025-08-19 18:00","연속"]
[253,"광주전남","목포","한빛2N/P CB 7571","한빛3호기 계획예방정비(O/H) 휴전","한빛3호기 계획예방정비(O/H) 휴전","2025-06-19 08:00","2025-08-19 18:00","2025-06-19 08:00","2025-08-19 18:00","연속"]
[254,"광주전남","목포","한빛2N/P CB 7700","한빛3호기 계획예방정비(O/H) 휴전","한빛3호기 계획예방정비(O/H) 휴전","2025-06-19 08:00","2025-08-19 18:00","2025-06-19 08:00","2025-08-19 18:00","연속"]
[255,"광주전남","목포","한빛2N/P CB 7671","한빛3호기 계획예방정비(O/H) 휴전","한빛3호기 계획예방정비(O/H) 휴전","2025-06-19 08:00","2025-08-19 18:00","2025-06-19 08:00","2025-08-19 18:00","연속"]
[256,"광주전남","목포","한빛2N/P CB 7500","한빛3호기 계획예방정비(O/H) 휴전","한빛3호기 계획예방정비(O/H) 휴전","2025-06-19 08:00","2025-08-19 18:00","2025-06-19 08:00","2025-08-19 18:00","연속"]
[257,"광주전남","목포","한빛2N/P CB 7600","한빛3호기 계획예방정비(O/H) 휴전","한빛3호기 계획예방정비(O/H) 휴전","2025-06-19 08:00","2025-08-19 18:00","2025-06-19 08:00","2025-08-19 18:00","연속"]
[258,"광주전남","목포","한빛2N/P #2 BUS","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","- 362kV GIS(40kA 4000A #2BUS) 철거 × 1식 - 362kV GIS(63kA 6300A #2BUS) 설치 × 1식 - 제어케이블 분리 및 결선 × 1식 - 기타 부대공사","2025-06-19 09:00","2025-08-12 18:00","취소","취소","연속"]
[259,"광주전남","목포","한빛2NP한빛3NP#3 T/L","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","- 362kV GIS(40kA 4000A #2BUS) 철거 × 1식 - 362kV GIS(63kA 6300A #2BUS) 설치 × 1식 - 제어케이블 분리 및 결선 × 1식 - 기타 부대공사","2025-06-30 19:00","2025-07-04 06:00","취소","취소","매일"]
[260,"광주전남","목포","한빛2NP한빛3NP#4 T/L","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","- 362kV GIS(40kA 4000A #2BUS) 철거 × 1식 - 362kV GIS(63kA 6300A #2BUS) 설치 × 1식 - 제어케이블 분리 및 결선 × 1식 - 기타 부대공사","2025-06-26 19:00","2025-06-30 06:00","취소","취소","매일"]
[261,"광주전남","목포","신김제한빛NP#1 T/L","유호전기 보호배전반 성능개선 시행","DS 상태 접점 감시 회로 변경 작업시간 : 1~2시간 / 시험시간 : 1시간 휴전일자 변경 가능 야간 작업 가능","2025-06-17 18:00","2025-06-17 21:00","2025-06-17 18:00","2025-06-17 21:00","연속"]
[262,"광주전남","목포","신김제한빛NP#2 T/L","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사 7D Bay 3CB 교체(71,72,00) #2 BUS 교체(모선측 DS 포함) 주말, 휴일작업 있음","2025-06-07 07:00","2025-06-10 18:00","취소","취소","연속"]
[263,"광주전남","목포","신김제한빛NP#1 T/L","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사 7D Bay 3CB 교체(71,72,00) #2 BUS 교체(모선측 DS 포함) 주말, 휴일작업 있음","2025-06-18 07:00","2025-06-19 14:00","취소","취소","연속"]
[264,"광주전남","순천","신강진광양#1 T/L"," 신강진-광양 T/L 추락방지시설 설치공사","수평추락방지시설 설치","2025-06-16 07:00","2025-06-20 18:00","2025-06-16 07:00","2025-06-20 18:00","매일"]
[265,"광주전남","순천","광양율촌CC T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양2, 광양-율촌CC 병가)","2025-06-16 07:00","2025-06-20 18:00","2025-06-16 07:00","2025-06-20 18:00","매일"]
[266,"광주전남","순천","신남원광양#2 T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양2, 광양-율촌CC 병가)","2025-06-16 07:00","2025-06-20 18:00","2025-06-16 07:00","2025-06-20 18:00","매일"]
[267,"광주전남","순천","신강진광양#2 T/L"," 신강진-광양 T/L 추락방지시설 설치공사","수평추락방지시설 설치","2025-06-23 07:00","2025-06-27 18:00","2025-06-23 07:00","2025-06-27 18:00","매일"]
[268,"광주전남","순천","광양S/S #2 M.Tr","25년 순천전력지사 부싱절연유 채유","광양S/S #2M.Tr 절연유 이상 관련 부싱절연유 채유","2025-06-10 14:00","2025-06-10 18:00","2025-06-10 14:00","2025-06-10 18:00","연속"]
[269,"광주전남","순천","광양하동TP#2 T/L"," 광양-하동TP T/L 추락방지시설 설치공사","수평추락방지시설 설치(3일 휴일 미작업)","2025-06-02 07:00","2025-06-05 18:00","2025-06-02 07:00","2025-06-05 18:00","매일"]
[270,"광주전남","순천","신남원광양#1 T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양1, 광양-여수TP 병가)","2025-06-09 07:00","2025-06-13 18:00","2025-06-09 07:00","2025-06-13 18:00","매일"]
[271,"광주전남","순천","광양S/S #1 M.Tr","25년 순천전력지사 부싱절연유 채유","광양S/S #1M.Tr 절연유 가스 이상 관련 부싱절연유 채유","2025-06-10 10:00","2025-06-10 14:00","2025-06-10 10:00","2025-06-10 14:00","연속"]
[272,"광주전남","순천","신남원광양#1 T/L","인출부싱 가스누기관련 보수작업","인출부싱 가스누기관련 보수작업","2025-06-10 09:00","2025-06-11 18:00","2025-06-10 09:00","2025-06-11 18:00","연속"]
[273,"광주전남","순천","광양여수TP T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양1, 광양-여수TP 병가)","2025-06-09 07:00","2025-06-13 18:00","2025-06-09 07:00","2025-06-13 18:00","매일"]
[274,"광주전남","순천","여수T/P #1 M.Tr","여수화력S/S #1M.Tr\n, B상 부싱 교체","여수화력S/S #1M.Tr\n, B상 부싱 교체","2025-06-23 10:00","2025-06-27 18:00","2025-06-23 10:00","2025-06-27 18:00","연속"]
[275,"광주전남","순천","여수T/P #3 M.Tr","여수화력  변압기 정밀점검","여수화력  변압기 정밀점검","2025-06-16 09:00","2025-06-20 18:00","취소","취소","연속"]
[276,"광주전남","순천","여수T/P #2 M.Tr","3차 DS과열관련 조치","3차 DS과열관련 조치","2025-06-04 09:00","2025-06-04 18:00","취소","취소","연속"]
[277,"대구","경산","신경산S/S #3 M.Tr","24~25년 경산P/O 변전협력회사 총액공사","- 누기개소보수","2025-06-12 09:30","2025-06-13 18:00","2025-06-12 09:30","2025-06-13 18:00","연속"]
[278,"대구","달성","북경남고령#2 T/L","북경남-고령#2T/L 정밀점검","북경남-고령#2T/L 정밀점검","2025-06-16 09:00","2025-06-20 18:00","2025-06-16 09:00","2025-06-20 18:00","연속"]
[279,"대구","달성","고령S/S #1 M.Tr","#1M.TR 정밀점검","#1M.TR 정밀점검","2025-06-09 09:00","2025-06-13 18:00","2025-06-09 09:00","2025-06-13 18:00","연속"]
[280,"대구","달성","북경남고령#1 T/L","#4M.TR 정밀점검 관련 무부하가압","#4M.TR 정밀점검 관련 무부하가압","2025-06-29 17:00","2025-06-29 18:00","2025-06-29 17:00","2025-06-29 18:00","연속"]
[281,"대구","달성","고령S/S #2 BUS","#4M.TR 정밀점검 관련 무부하가압","#4M.TR 정밀점검 관련 무부하가압","2025-06-29 17:00","2025-06-29 18:00","취소","취소","연속"]
[282,"대구","달성","고령S/S #4 M.Tr","#4M.TR 정밀점검","#4M.TR 정밀점검","2025-06-23 09:00","2025-06-29 18:00","2025-06-23 09:00","2025-06-29 18:00","연속"]
[283,"대구","달성","고령S/S #1 BUS","[TEST] 고령S/S 7571CB 정밀점검 관련 무부하가압휴전_","[TEST] 고령S/S 7571CB 정밀점검 관련 무부하가압휴전_","2025-06-14 17:00","2025-06-14 18:00","취소","취소","연속"]
[284,"대구","달성","서대구고령#2 T/L","[TEST] 고령S/S 7571 CB부 정밀점검 무부하가압선로_","[TEST] 고령S/S 7571 CB부 정밀점검 무부하가압선로_","2025-06-14 17:00","2025-06-14 18:00","2025-06-14 17:00","2025-06-14 18:00","연속"]
[285,"대구","달성","고령S/S #1 BUS","북경남-고령#2T/L 정밀점검 관련 무부하가압 휴전선로","북경남-고령#2T/L 정밀점검 관련 무부하가압 휴전선로","2025-06-20 17:00","2025-06-20 18:00","취소","취소","연속"]
[286,"대구","달성","고령S/S CB 7571","서대구-고령#2T/L CB 정밀점검","서대구-고령#2T/L CB 정밀점검(7571)","2025-06-12 09:00","2025-06-14 18:00","2025-06-12 09:00","2025-06-14 18:00","연속"]
[287,"대구","달성","고령S/S #2 BUS","[TEST] 고령S/S 7500CB 정밀점검 관련 무부하가압휴전_","[TEST] 고령S/S 7500CB 정밀점검 관련 무부하가압휴전_","2025-06-11 17:00","2025-06-11 18:00","취소","취소","연속"]
[288,"대구","달성","서대구고령#2 T/L","[TEST] 고령S/S 7500 CB부 정밀점검 무부하가압선로","[TEST] 고령S/S 7500 CB부 정밀점검 무부하가압선로","2025-06-11 17:00","2025-06-11 18:00","2025-06-11 17:00","2025-06-11 18:00","연속"]
[289,"대구","달성","고령S/S CB 7500","서대구-고령#2T/L TIE CB 정밀점검","서대구-고령#2T/L TIE CB 정밀점검(7500)","2025-06-09 09:00","2025-06-11 18:00","2025-06-09 09:00","2025-06-11 18:00","연속"]
[290,"대구","달성","고령의령#1 T/L"," 고령-의령 등 4개T/L 피뢰기 및 조류착지방지장치 설치공사"," 고령-의령#1T/L 피뢰기 및 조류착지방지장치 설치 - 주말간 환원(6/28~29)","2025-06-24 07:00","2025-07-01 18:00","2025-06-16T07:00:00","2025-06-23T18:00:00","연속"]
[291,"대구","달성","신경산대구#1 T/L","[TEST] 대구S/S #1M.TR 정밀점검 무부하가압 휴전","[TEST] 대구S/S #1M.TR 정밀점검 무부하가압 휴전","2025-06-22 17:00","2025-06-22 18:00","취소","취소","연속"]
[292,"대구","달성","북경남대구#1 T/L","북경남-대구#1T/L PT,LA 하자점검","북경남-대구#1T/L PT,LA 하자점검","2025-06-11 09:00","2025-06-11 18:00","2025-06-11 09:00","2025-06-11 18:00","연속"]
[293,"대구","달성","북경남대구#2 T/L"," 고령-의령 등 4개T/L 피뢰기 및 조류착지방지장치 설치공사"," 북경남-대구#2T/L 피뢰기 및 조류착지방지장치 설치","2025-06-16 07:00","2025-06-20 17:00","2025-06-16 07:00","2025-06-20 17:00","연속"]
[294,"대구","달성","대구S/S #1 M.Tr","#1M.TR 정밀점검","#1M.TR 정밀점검","2025-06-16 09:00","2025-06-22 18:00","취소","취소","연속"]
[295,"대구","달성","대구S/S #2 Sh.R CB","#2SH.R GIS 정밀점검","#2SH.R GIS 정밀점검","2025-06-30 09:00","2025-07-04 18:00","취소","취소","연속"]
[296,"대구","칠곡","신포항북대구 T/L","2025년 칠곡전력지사 362kV GIS 정밀점검공사","북대구S/S  7100 GIS 정밀점검 (무부하가압)","2025-06-11 18:00","2025-06-12 18:00","2025-06-11 18:00","2025-06-12 18:00","연속"]
[297,"대구","칠곡","북대구S/S CB 7100","2025년 칠곡전력지사 362kV GIS 정밀점검공사","북대구S/S  7100 GIS 정밀점검","2025-06-09 09:00","2025-06-12 18:00","2025-06-09 09:00","2025-06-12 18:00","연속"]
[298,"대구","칠곡","북대구선산 T/L","2025년 칠곡전력지사 362kV GIS 정밀점검공사","북대구S/S  7200,7272 GIS 정밀점검 및 무부하가압 선로","2025-06-16 18:00","2025-06-20 18:00","2025-06-16 18:00","2025-06-20 18:00","연속"]
[299,"대구","칠곡","서대구S/S #2 M.Tr"," 서대구S/S 현대화 관련 전력구공사","(안전확보) 8회선 전력구 1,025m 설치, 환기구 12개소 등","2025-06-18 08:00","2025-06-26 18:00","2025-06-18 08:00","2025-06-26 18:00","연속"]
[300,"대구","칠곡","서대구S/S #3 M.Tr","서대구S/S 7171, 7100 GCB 조작시험, PT 보통점검","서대구S/S 7171, 7100 GCB 조작시험, PT 보통점검","2025-06-27 09:30","2025-06-27 18:00","2025-06-27 09:30","2025-06-27 18:00","연속"]
[301,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S  주변압기측 현대화 공사","철공진 발생관련 PT 3차측 회로 보완","2025-06-30 09:00","2025-06-30 18:00","2025-06-30 09:00","2025-06-30 18:00","연속"]
[302,"대구","칠곡","서대구S/S #2 M.Tr","서대구S/S 154kV GIS 하자보수","서대구S/S 6700CB 어댑터플랜지 교체","2025-06-04 09:00","2025-06-07 18:00","취소","취소","연속"]
[303,"대구","칠곡","서대구S/S #1 M.Tr"," 서대구S/S 현대화 관련 전력구공사","(안전확보) 8회선 전력구 1,025m 설치, 환기구 12개소 등","2025-06-09 08:00","2025-06-17 18:00","2025-06-09 08:00","2025-06-17 18:00","연속"]
[304,"대구","포항","신영일S/S #4 M.Tr","2024~25년도 포항전력지사 변전협력회사 공사","신영일S/S #4M.Tr 7772, 7700 GIS 조작시험, 1차 LA, 3차 LA 하자점검, 3차 GIS 조작시험","2025-06-16 09:00","2025-06-17 18:00","2025-06-16 09:00","2025-06-17 18:00","연속"]
[305,"대구","포항","신영일S/S #3 M.Tr","2024~25년도 포항전력지사 변전협력회사 공사","신영일S/S #3M.Tr 7572, 7500 GIS 조작시험, 1차 LA, 2차 LA, 3차 LA 하자점검, 3차 GIS 조작시험","2025-06-19 09:00","2025-06-20 18:00","2025-06-19 09:00","2025-06-20 18:00","연속"]
[306,"대구","포항","신포항신월성NP#4 T/L","154kV 신영일-천북 등 19개 T/L 추락방지장치 설치공사"," 울주-월성NP#2T/L 추락방지장치 설치공사 [안전확보]","2025-06-16 07:00","2025-06-23 18:00","2025-06-16 07:00","2025-06-23 18:00","연속"]
[307,"대구","포항","울주월성NP#2 T/L","154kV 신영일-천북 등 19개 T/L 추락방지장치 설치공사"," 울주-월성NP#2T/L 추락방지장치 설치공사","2025-06-04 07:00","2025-06-23 18:00","2025-06-04 07:00","2025-06-23 18:00","연속"]
[308,"대구","포항","월성N/P SEC CB 70710","2024~25년도 포항전력지사 변전총액공사","월성S/Y 70-71 GIS 조작시험","2025-06-13 09:00","2025-06-13 14:00","2025-06-13 09:00","2025-06-13 14:00","연속"]
[309,"대구","포항","월성N/P SEC CB 75760","2024~25년도 포항전력지사 변전협력회사 공사","월성S/Y 75-76 GIS 조작시험","2025-06-13 14:00","2025-06-13 18:00","2025-06-13 14:00","2025-06-13 18:00","연속"]
[310,"경북","영주","신영주S/S #2 BUS","신영주S/S 7952DS 누기개소 보수","신영주S/S 7952DS 누기개소 보수","2025-06-12 09:00","2025-06-14 18:00","취소","취소","연속"]
[311,"경북","영주","신영주한울NP#2 T/L"," 신영주-한울NP2T/L 수평추락방지장치 설치"," 신영주-한울NP2T/L 수평추락방지장치 설치","2025-06-12 08:00","2025-06-21 17:00","취소","취소","매일"]
[312,"경북","영주","신영주한울NP#1 T/L"," 신영주-한울NP2T/L 수평추락방지장치 설치"," 신영주-한울NP2T/L 수평추락방지장치 설치","2025-06-02 08:00","2025-06-11 17:00","취소","취소","매일"]
[313,"경북","직할","안동C/C #1 M.Tr","24~25년 경북본부 직할 변전협력회사 공사","#1M.Tr 1,2차 GIS 및 3차 SIS 보통점검 변압기 추락방지장치 설치","2025-06-24 10:00","2025-06-25 18:00","2025-06-24 10:00","2025-06-25 18:00","연속"]
[314,"경북","직할","안동C/C #2 M.Tr","24~25년 경북본부 직할 변전협력회사 공사","#2M.Tr 1,2차 GIS 및 3차 SIS 보통점검 변압기 추락방지장치 설치","2025-06-26 10:00","2025-06-27 18:00","2025-06-26 10:00","2025-06-27 18:00","연속"]
[315,"경북","직할","신영주안동CC T/L","24~25년 경북직할가공송전협력회사공사","추락방지장치 설치","2025-06-23 07:00","2025-06-27 18:00","취소","취소","연속"]
[316,"경북","직할","청송P/P #1호기 주변압기 (CB 7100, 7172)","24~25년 경북본부 직할 변전협력회사 공사","7122 DS 모터 교체","2025-06-19 10:00","2025-06-19 18:00","2025-06-19 10:00","2025-06-19 18:00","연속"]
[317,"경북","직할","청송P/P #1호기 주변압기 (CB 7100, 7172)","24~25년 경북본부 직할 변전협력회사 공사","7122 DS 모터 교체","2025-06-19 10:00","2025-06-19 18:00","2025-06-19 10:00","2025-06-19 18:00","연속"]
[318,"경북","직할","신영주청송PP T/L","24~25년 경북직할가공송전협력회사공사","추락방지장치 설치","2025-06-09 07:00","2025-06-20 18:00","취소","취소","연속"]
[319,"부산울산","동부산","신고리고리NP#4 T/L","동부산전력 가공송전협력회사 공사","핸드레일 보수","2025-06-12 07:00","2025-06-12 18:00","취소","취소","연속"]
[320,"부산울산","동부산","신양산북부산#1 T/L","신양산S/S  용량부족차단기 교체공사","73BAY GIS 기초 시공 관련 안전이격","2025-06-07 08:00","2025-06-08 18:00","취소","취소","연속"]
[321,"부산울산","북부산","북부산S/S #76 BUS","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S  76BUS PRO 대체공사","2025-06-09 09:00","2025-06-12 18:00","취소","취소","연속"]
[322,"부산울산","북부산","북부산S/S #4 Sh.R CB","24-25년 북부산전력지사 변전총액공사","북부산S/S  #4Sh.R 부싱절연유 채유","2025-06-13 09:00","2025-06-13 18:00","2025-06-13 09:00","2025-06-13 18:00","연속"]
[323,"부산울산","북부산","북부산고리NP#2 T/L"," 북부산-고리NP T/L 상부재보강 및 154kV 피뢰기설치공사"," 북부산-고리NP T/L No.131호 상부재 보강","2025-06-23 08:00","2025-06-27 18:00","취소","취소","연속"]
[324,"부산울산","북부산","북부산S/S SEC CB 70710","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S  70-71,75-76 B/F PNL 대체","2025-06-09 09:00","2025-06-12 18:00","2025-06-09 09:00","2025-06-12 18:00","연속"]
[325,"부산울산","북부산","북부산고리NP#1 T/L"," 북부산-고리NP T/L 상부재보강 및 154kV 피뢰기설치공사"," 북부산-고리NP T/L No.131호 상부재 보강","2025-06-30 08:00","2025-07-04 18:00","취소","취소","연속"]
[326,"부산울산","서부산","신녹산S/S #2 M.Tr","신녹산S/S  #1M.Tr 증설공사","154kV 신녹산-명지#1T/L 철거 및 Sh.C 설치(감압)","2025-06-23 09:00","2025-06-28 18:00","2025-06-23 09:00","2025-06-28 18:00","연속"]
[327,"부산울산","서부산","신녹산S/S #2 M.Tr","신녹산S/S  #1M.Tr 증설공사","154kV 신녹산-명지#1T/L 철거(감압)","2025-06-16 09:00","2025-06-19 18:00","2025-06-16 09:00","2025-06-19 18:00","연속"]
[328,"부산울산","울산","남울산S/S #2 M.Tr","25년 울산전력지사 변전협력회사 공사","- 6800GIS 누기보수 조치 관련 시험가압(1HR)","2025-06-18 17:00","2025-06-18 18:00","2025-06-18 17:00","2025-06-18 18:00","연속"]
[329,"부산울산","울산","동울산신울산 T/L","2025년 가공송전 순시점검 위탁공사(울산)"," 동울산-신울산 지반변위 감시용 CCTV 가공지선 보조 전원설치 ○ 대상 :  동울산-신울산T/L ○ 구간 :  동울산-신울산T/L 25호","2025-06-10 09:00","2025-06-10 18:00","2025-06-10 09:00","2025-06-10 18:00","연속"]
[330,"부산울산","울산","동울산S/S #1 M.Tr","25년 울산전력지사 주변압기 및 OLTC 정밀점검 공사","- 변압기 보통점검, OLTC 정밀점검 - 1,2차 부싱절연유 채유 - 변압기 추락방지 장치 설치","2025-06-23 09:00","2025-06-25 18:00","2025-06-23 09:00","2025-06-25 18:00","연속"]
[331,"부산울산","울산","신온산남울산#1 T/L","2024-2025년 울산전력지사 가공송전협력회사 공사","[휴전작업 안전이격확보] 1) 내용: 온산-처용#2 4호 상단 파손애자(1장) 교체에 따른 안전이격확보 2) 기타: 신온산-남울산#1 27호, 온산-처용#2 4호 병가","2025-06-20 08:00","2025-06-20 12:00","2025-06-20 08:00","2025-06-20 12:00","연속"]
[332,"부산울산","울산","신온산S/S #2 M.Tr","25년 울산전력지사 주변압기 및 OLTC 정밀점검 공사","- 변압기 보통점검","2025-06-09 09:00","2025-06-10 18:00","2025-06-09 09:00","2025-06-10 18:00","연속"]
[333,"부산울산","울산","신울산고리NP#2 T/L"," 울주-고리NP등22개T/L 송전철탑 정비공사","폴리머점퍼지지애자 설치","2025-06-18 07:00","2025-06-19 18:00","취소","취소","연속"]
[334,"부산울산","울산","신울산S/S #4 M.Tr","25년 울산전력지사 주변압기 및 OLTC 정밀점검 공사","- 변압기 보통점검","2025-06-11 09:00","2025-06-12 18:00","2025-06-11 09:00","2025-06-12 18:00","연속"]
[335,"부산울산","울산","북부산신울산#1 T/L","25년 울산전력지사 변전협력회사 공사","- CVT 보통점검","2025-06-13 09:00","2025-06-13 18:00","취소","취소","연속"]
[336,"부산울산","울산","신울산고리NP#1 T/L"," 울주-고리NP등22개T/L 송전철탑 정비공사","폴리머점퍼지지애자 설치","2025-06-16 07:00","2025-06-17 18:00","취소","취소","연속"]
[337,"부산울산","울산","울산C/C #3 M.Tr","25년 울산전력지사 변전협력회사 공사","- 72Bay B/F 보호반, #3M.Tr 보호반 대체 - 울산화력) 2차 GIS 보통점검","2025-06-16 09:00","2025-06-20 18:00","2025-06-16 09:00","2025-06-20 18:00","연속"]
[338,"부산울산","울산","울주S/S #4 M.Tr","울주S/S #4M.Tr 보호반 개조공사","- 변압기 보호반 개조공사(6/23~6/27) - 변압기 보통점검(6/23~6/24) - 1,2차 부싱절연유 채유(6/23)","2025-06-23 09:00","2025-06-27 18:00","2025-06-23 09:00","2025-06-27 18:00","연속"]
[339,"부산울산","울산","울주울산TP#2 T/L","2025년 가공송전 순시점검 위탁공사(울산)"," 울주-울산TP#2T/L 초기점검 - 구간 :S/T ~3호, 15~26호 - 병가 : 15~26호(154kV 남울산-신온산T/L 5~16호)","2025-06-04 08:00","2025-06-05 18:00","2025-06-04 08:00","2025-06-05 18:00","연속"]
[340,"부산울산","직할","신대연S/S #1 BUS","24~25년 직할 변전협력회사 총액공사","신대연S/S #70BUS 모선보호PNL 대체","2025-06-09 09:00","2025-06-13 18:00","2025-06-09 09:00","2025-06-13 18:00","연속"]
[341,"부산울산","직할","신대연S/S #2 BUS","24~25년 직할 변전협력회사 총액공사","신대연S/S #75BUS 모선보호PNL 대체","2025-06-16 09:00","2025-06-20 18:00","2025-06-16 09:00","2025-06-20 18:00","연속"]
[342,"경남","김해송변전부","신김해S/S #1 M.Tr","신김해S/S  #1M.Tr 부싱시험탭 규격조사","신김해S/S  #1M.Tr 부싱시험탭 규격조사 - 종합예방진단 시스템 설치 관련","2025-06-02 09:30","2025-06-02 13:30","2025-06-02 09:30","2025-06-02 13:30","연속"]
[343,"경남","김해송변전부","신김해신녹산#1 T/L","154kV 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","2025-06-14 07:00","2025-06-15 18:00","2025-06-14 07:00","2025-06-15 18:00","매일"]
[344,"경남","김해송변전부","신김해S/S #2 M.Tr","신김해S/S  #2M.Tr 부싱시험탭 규격조사","신김해S/S  #2M.Tr 부싱시험탭 규격조사 - 종합예방진단 시스템 설치 관련","2025-06-02 13:30","2025-06-02 17:30","2025-06-02 13:30","2025-06-02 17:30","연속"]
[345,"경남","김해송변전부","신김해S/S #3 M.Tr","신김해S/S  #3M.Tr 부싱시험탭 규격조사","신김해S/S  #3M.Tr 부싱시험탭 규격조사 - 종합예방진단 시스템 설치 관련","2025-06-05 09:30","2025-06-05 13:30","2025-06-04T09:30:00","2025-06-04T13:30:00","연속"]
[346,"경남","김해송변전부","신김해S/S #4 M.Tr","신김해S/S  #4M.Tr 부싱시험탭 규격조사","신김해S/S  #4M.Tr 부싱시험탭 규격조사 - 종합예방진단 시스템 설치 관련","2025-06-05 13:30","2025-06-05 17:30","2025-06-04T13:30:00","2025-06-04T17:30:00","연속"]
[347,"경남","김해송변전부","신김해창원#1 T/L","154kV 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","2025-06-21 07:00","2025-06-22 18:00","2025-06-21 07:00","2025-06-22 18:00","매일"]
[348,"경남","직할","창원신고성#1 T/L"," 창원-삼천포화력T/L 추락방지시설 설치공사"," 창원-삼천포화력T/L 추락방지시설 설치공사","2025-06-09 07:00","2025-06-17 18:00","2025-06-09 07:00","2025-06-17 18:00","매일"]
[349,"경남","직할","창원신고성#2 T/L"," 창원-삼천포화력T/L 추락방지시설 설치공사"," 창원-삼천포화력T/L 추락방지시설 설치공사","2025-06-18 07:00","2025-06-26 18:00","2025-06-18 07:00","2025-06-26 18:00","매일"]
[350,"경남","진주","의령산청양수#1 T/L","산청P/P  7271 GIS 정밀점검","산청P/P  의령#1T/L-#2M.Tr 1차(7271) GIS 정밀점검","2025-06-23 09:00","2025-06-27 18:00","2025-06-23 09:00","2025-06-27 18:00","연속"]
[351,"경남","진주","의령산청양수#1 T/L","산청P/P  7100 GIS 정밀점검","산청P/P  의령#1T/L-#1M.Tr 1차(7100) GIS 정밀점검","2025-06-16 09:00","2025-06-20 18:00","2025-06-16 09:00","2025-06-20 18:00","연속"]
[352,"경남","진주","고령의령#2 T/L"," 고령-의령#2T/L 추락방지장치 및 폴리머 점퍼지지 설치공사"," 고령-의령#2T/L 39~116호(78기) 수평형 추락방지장치 및 6~101호(21기) 폴리머 점퍼지지애자 설치","2025-06-09 07:00","2025-06-13 18:00","취소","취소","매일"]
[353,"경남","진주","의령S/S #3 M.Tr","의령S/S  #3M.Tr 보통점검 등","의령S/S  #3M.Tr 보통점검 [병행] 변압기 추락방지 장치 설치 [병행] 1차 GIS(7872) 보통점검, 2차 GIS(6344) 보통점검 [병행] 1차 LA(A,B,C), 2차 LA(A,B,C), 3차 PT 보통점검 [병행] 방호벽 사다리 철거 등","2025-06-09 10:00","2025-06-13 18:00","2025-06-18T10:00:00","2025-06-18T18:00:00","연속"]
[354,"경남","진주","신남원의령#2 T/L"," 신남원-의령T/L 추락방지장치 설치 공사"," 신남원-의령T/L 추락방지장치 설치 공사 1~136호(136기)","2025-06-14 07:00","2025-06-15 18:00","2025-06-14 07:00","2025-06-15 18:00","매일"]
[355,"경남","진주","신남원의령#2 T/L"," 신남원-의령T/L 추락방지장치 설치 공사"," 신남원-의령T/L 추락방지장치 설치 공사 1~136호(136기)","2025-06-21 07:00","2025-06-22 18:00","2025-06-21 07:00","2025-06-22 18:00","매일"]
[356,"경남","진주","의령S/S #1 M.Tr","의령S/S  #1M.Tr 3차 LA(A,B,C) 초기점검 등","의령S/S  #1M.Tr 3차 LA(A,B,C) 초기점검 [병행] 3차 PT(A,B,C) 대체 [병행] 23kV #1S.Tr(A,B,C) 초기점검","2025-06-23 10:00","2025-06-23 18:00","2025-06-23 10:00","2025-06-23 18:00","연속"]
[357,"경남","진주","신남원의령#2 T/L"," 신남원-의령T/L 추락방지장치 설치 공사"," 신남원-의령T/L 추락방지장치 설치 공사 1~136호(136기)","2025-06-28 07:00","2025-06-29 18:00","취소","취소","매일"]
[358,"경남","진주","고령의령#1 T/L"," 고령-의령#1T/L 추락방지장치 및 폴리머 점퍼지지 설치공사"," 고령-의령#1T/L 39~116호(78기) 수평형 추락방지장치 및 8~104호(26기) 폴리머 점퍼지지애자 설치 ☞ 6/3(화) 대선일 작업 없음(선로운전)","2025-06-02 07:00","2025-06-07 18:00","취소","취소","매일"]
[359,"경남","통영","신고성S/S #1 M.Tr","신고성S/S M.Tr 3차측 현대화 관련 기타공사","신고성S/S #1M.Tr 3차 측 예비절체용 4125 DS 철거 및 관련 기타공사","2025-06-23 10:00","2025-06-27 18:00","2025-06-23 10:00","2025-06-27 18:00","연속"]
[360,"경남","함안","신옥천북경남 T/L","북경남S/S 신옥천북경남 T/L 7B00 절연열화 측정","북경남S/S 신옥천북경남 T/L 7B00 절연열화 측정","2025-06-19 16:00","2025-06-19 18:00","2025-06-19 16:00","2025-06-19 18:00","연속"]
[361,"경남","함안","북경남서대구#1 T/L","북경남S/S 서대구#1T/L 7A72 절연열화 측정","북경남S/S 서대구#1T/L 7A72 절연열화 측정","2025-06-16 09:30","2025-06-16 13:30","2025-06-16 09:30","2025-06-16 13:30","연속"]
[362,"경남","함안","북경남S/S #5 Sh.R CB","북경남S/S 7700GIS 절연열화 측정 관련 휴전","북경남S/S 7700GIS 절연열화 측정 관련 휴전","2025-06-17 09:30","2025-06-17 17:30","2025-06-17 09:30","2025-06-17 17:30","연속"]
[363,"경남","함안","북경남고령#2 T/L","북경남S/S 고령#2 T/L 7700, 7772 GIS 보통점검 외","북경남S/S 고령#2 T/L 7700, 7772 GIS 보통점검 및 7700 GIS 절연열화 측정","2025-06-17 09:30","2025-06-17 17:30","2025-06-17 09:30","2025-06-17 17:30","연속"]
[364,"경남","함안","북경남서대구#2 T/L","북경남S/S 서대구#2 T/L 7972 GIS 보통점검 외","북경남S/S 서대구#2 T/L 7972 GIS 보통점검 및 절연열화 측정","2025-06-18 09:30","2025-06-18 17:30","2025-06-18 09:30","2025-06-18 17:30","연속"]
[365,"경남","함안","북경남S/S #7Sh.R CB","북경남S/S #7Sh.R 1차 선로측 CB(7B71) 유도전압 이격 확보","북경남S/S  7B00 점검시 유도전압 이격거리 확보용 7B71 휴전","2025-06-19 16:00","2025-06-19 18:00","2025-06-19 16:00","2025-06-19 18:00","연속"]
[366,"경남","함안","의령신마산#1 T/L","신마산S/S  의령신마산#1 T/L GIS C상 LA 이음 조치","신마산S/S  의령신마산#1 T/L GIS C상 LA 이음 조치","2025-06-30 09:30","2025-07-01 17:30","취소","취소","연속"]

{"sheet":"154설비","index":2,"n_rows":753,"n_cols":12,"rows_kept":753,"cut":false,"hidden":false,"merged":[[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2025년도 6월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","광장S/S CB 6100","2025 성동전력지사 변전협력회사 공사","- 170kV GIS 조작시험","2025-06-27 09:00","2025-06-27 18:00","2025-06-27 09:00","2025-06-27 18:00","연속"]
[2,"서울","성동","천호구의#1 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 하자점검","2025-06-27 09:00","2025-06-27 18:00","취소","취소","연속"]
[3,"서울","성동","천호구의#2 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 하자점검","2025-06-30 09:00","2025-06-30 18:00","취소","취소","연속"]
[4,"서울","성동","구의광장#2 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 하자점검 (구의) - 170kV GIS 조작시험 (광장)","2025-06-26 09:00","2025-06-26 18:00","2025-06-26 09:00","2025-06-26 18:00","연속"]
[5,"서울","성동","구의광장#1 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 하자점검 (구의) - 170kV GIS 조작시험 (광장)","2025-06-25 09:00","2025-06-25 18:00","2025-06-25 09:00","2025-06-25 18:00","연속"]
[6,"서울","성동","장암방학#2 T/L","2025년 성동P/O 170kV GIS 정밀점검","170kV GIS 정밀점검","2025-06-19 09:00","2025-06-19 18:00","2025-06-23 09:00","2025-06-26 18:00","연속"]
[7,"서울","성동","방학창동#2 T/L","2025년 성동P/O 170kV GIS 정밀점검","170kV GIS 정밀점검","2025-06-23 09:00","2025-06-26 18:00","2025-06-23 09:00","2025-06-26 18:00","연속"]
[8,"서울","성동","장암방학#2 T/L","2025년 성동P/O 170kV GIS 정밀점검","170kV GIS 정밀점검","2025-06-26 09:00","2025-06-26 18:00","2025-06-26 09:00","2025-06-26 18:00","연속"]
[9,"서울","성동","장암방학#1 T/L","2025년 성동P/O 170kV GIS 정밀점검","170kV GIS 정밀점검","2025-06-30 09:00","2025-07-03 18:00","2025-06-30 09:00","2025-07-03 18:00","연속"]
[10,"서울","성동","방학창동#1 T/L","2025년 성동P/O 170kV GIS 정밀점검","170kV GIS 정밀점검","2025-06-16 09:00","2025-06-19 18:00","2025-06-16 09:00","2025-06-19 18:00","연속"]
[11,"서울","성동","수유미아#2 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 초기점검","2025-06-30 09:00","2025-06-30 18:00","2025-06-30 09:00","2025-06-30 18:00","연속"]
[12,"서울","성동","쌍문수유#1 T/L","2025년 성동P/O 170kV GIS 정밀점검","170kV GIS 정밀점검","2025-06-09 09:00","2025-06-10 18:00","취소","취소","연속"]
[13,"서울","성동","군자화양#1 T/L","2025년 성동P/O 변전협력회사 공사","-  GIS 조작시험","2025-06-11 09:00","2025-06-11 14:00","2025-06-11 09:00","2025-06-11 14:00","연속"]
[14,"서울","성동","화양광장 T/L","2025년 성동P/O 변전협력회사 공사","-  GIS 조작시험","2025-06-10 09:00","2025-06-10 18:00","취소","취소","연속"]
[15,"서울","성동","화양성수 T/L","2025년 성동P/O 변전협력회사 공사","-  GIS 조작시험","2025-06-25 09:00","2025-06-25 18:00","취소","취소","연속"]
[16,"서울","성동","미금화양 T/L","2025년 성동P/O 변전협력회사 공사","-  GIS 조작시험","2025-06-12 09:00","2025-06-12 18:00","취소","취소","연속"]
[17,"서울","성동","군자화양#2 T/L","2025년 성동P/O 변전협력회사 공사","-  GIS 조작시험","2025-06-11 14:00","2025-06-11 18:00","2025-06-11 14:00","2025-06-11 18:00","연속"]
[18,"서울","중부","동빙고S/S #1 BUS","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","시험 가압","2025-06-23 10:00","2025-06-24 18:00","2025-06-23 10:00","2025-06-24 18:00","연속"]
[19,"서울","중부","동빙고S/S #2 BUS","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","시험 가압","2025-06-25 10:00","2025-06-27 18:00","2025-06-25 10:00","2025-06-27 18:00","연속"]
[20,"서울","중부","중부S/S #65 BUS","2025년 중부S/S  장기사용 GIS 교체공사(2차)","-  GIS 교체(수색중부#1, 수색중부#2T/L) - 기타 부대공사","2025-06-02 09:00","2025-06-17 18:00","2025-06-02 09:00","2025-06-17 18:00","연속"]
[21,"서울","직할","미아S/S #2 BUS","송전선로 상시험을 위한 BUS 휴전 및 무부하가압","1. 공사명 :  원남-미아T/L(미아S/S 측) 선종교체공사 2. 공사내용 : OF케이블 선종교체(→XLPE) : 미아S/S EBG ∼ J/B#5 (2C×1.8㎞)","2025-06-26 09:00","2025-06-26 18:00","2025-06-26 09:00","2025-06-26 18:00","연속"]
[22,"서울","직할","미아S/S CB 6100","25년 직할 변전정비협력회사 총액공사"," GIS 보통점검","2025-06-09 10:00","2025-06-09 17:00","2025-06-09 10:00","2025-06-09 17:00","연속"]
[23,"서울","직할","용두S/S #1 BUS","2025년 서울직할  GIS 정밀점검공사","2025년 서울직할  GIS 정밀점검공사 1DS 점검 및 시험가압","2025-06-23 09:00","2025-06-24 14:00","2025-06-23 09:00","2025-06-24 14:00","연속"]
[24,"서울","직할","용두안암#1 T/L","2025년 서울직할  GIS 정밀점검공사","2025년 서울직할  GIS 정밀점검공사","2025-06-23 09:00","2025-06-25 18:00","2025-06-23 09:00","2025-06-25 18:00","연속"]
[25,"서울","직할","용두S/S #2 BUS","2025년 서울직할  GIS 정밀점검공사","2025년 서울직할  GIS 정밀점검공사 2DS 점검 및 시험가압","2025-06-24 14:00","2025-06-25 18:00","2025-06-24 14:00","2025-06-25 18:00","연속"]
[26,"서울","직할","용두S/S #1 BUS","2025년 서울직할  GIS 정밀점검공사","2025년 서울직할  GIS 정밀점검공사 1DS 점검 및 시험가압","2025-06-26 09:00","2025-06-27 14:00","2025-06-26 09:00","2025-06-27 14:00","연속"]
[27,"서울","직할","용두안암#2 T/L","2025년 서울직할  GIS 정밀점검공사","2025년 서울직할  GIS 정밀점검공사","2025-06-26 09:00","2025-06-28 18:00","2025-06-26 09:00","2025-06-28 18:00","연속"]
[28,"서울","직할","용두S/S #2 BUS","2025년 서울직할  GIS 정밀점검공사","2025년 서울직할  GIS 정밀점검공사 2DS 점검 및 시험가압","2025-06-27 14:00","2025-06-28 18:00","2025-06-27 14:00","2025-06-28 18:00","연속"]
[29,"남서울","동서울","산성수서#2 T/L"," 산성-수서T/L 지중화공사(2단계)"," 산성-수서#1T/L 지중화(2단계) - 발주처 : LH - 지중화공사에 따른 케이블 철거 및 포설, 접속","2025-06-11 09:00","2025-07-15 18:00","2025-06-11 09:00","2025-07-15 18:00","연속"]
[30,"남서울","동서울","탄천대치#1 T/L","2025년 동서울전력지사 170kV GIS 정밀점검","탄천S/S 대치-탄천#1T/L GIS 정밀점검","2025-06-30 09:00","2025-07-01 18:00","2025-06-30 09:00","2025-07-01 18:00","연속"]
[31,"남서울","동서울","탄천대치#1 T/L","2025년 동서울전력지사 170kV GIS 정밀점검","무부하가압용(탄천S/S 65-66 BUS SEC GIS 정밀점검)","2025-06-26 13:00","2025-06-26 18:00","2025-06-26 13:00","2025-06-26 18:00","연속"]
[32,"남서울","동서울","탄천S/S #65 BUS","2025년 동서울전력지사 170kV GIS 정밀점검","무부하가압용(탄천S/S 65-66 SEC CB)","2025-06-26 13:00","2025-06-26 18:00","2025-06-26 13:00","2025-06-26 18:00","연속"]
[33,"남서울","동서울","탄천대치#2 T/L","2025년 동서울전력지사 170kV GIS 정밀점검","무부하가압용(탄천S/S 60-61 BUS SEC GIS 정밀점검)","2025-06-24 13:00","2025-06-24 18:00","2025-06-24 13:00","2025-06-24 18:00","연속"]
[34,"남서울","동서울","탄천S/S #61 BUS","2025년 동서울전력지사 170kV GIS 정밀점검","무부하가압용(탄천S/S 60-61 SEC CB)","2025-06-24 13:00","2025-06-24 18:00","2025-06-24 13:00","2025-06-24 18:00","연속"]
[35,"남서울","동서울","탄천선릉#2 T/L","2025년 동서울전력지사 170kV GIS 정밀점검","탄천S/S 탄천-선릉#2T/L GIS 정밀점검","2025-06-18 09:00","2025-06-19 18:00","2025-06-18 09:00","2025-06-19 18:00","연속"]
[36,"남서울","동서울","탄천선릉#1 T/L","2025년 동서울전력지사 170kV GIS 정밀점검","탄천S/S 탄천-선릉#1T/L GIS정밀점검","2025-06-16 09:00","2025-06-17 18:00","2025-06-16 09:00","2025-06-17 18:00","연속"]
[37,"남서울","동서울","탄천대치#2 T/L","2025년 동서울전력지사 170kV GIS 정밀점검","무부하가압용(탄천S/S #4M.Tr GIS정밀점검)","2025-06-12 13:00","2025-06-12 18:00","2025-06-12 13:00","2025-06-12 18:00","연속"]
[38,"남서울","동서울","탄천S/S #61 BUS","2025년 동서울전력지사 170kV GIS 정밀점검","무부하가압용(탄천S/S #4M.Tr GIS정밀점검)","2025-06-12 13:00","2025-06-12 18:00","2025-06-12 13:00","2025-06-12 18:00","연속"]
[39,"남서울","동서울","탄천대치#1 T/L","2025년 동서울전력지사 170kV GIS 정밀점검","무부하가압용(탄천S/S #3M.Tr GIS정밀점검)","2025-06-10 13:00","2025-06-10 18:00","2025-06-10 13:00","2025-06-10 18:00","연속"]
[40,"남서울","동서울","탄천대치#1 T/L","2025년 동서울전력지사 170kV GIS 정밀점검","무부하가압용(탄천S/S #2M.Tr GIS정밀점검)","2025-06-05 13:00","2025-06-06 18:00","2025-06-05 13:00","2025-06-06 18:00","연속"]
[41,"남서울","동서울","탄천S/S #65 BUS","2025년 동서울전력지사 170kV GIS 정밀점검","무부하가압용(탄천S/S #3M.Tr GIS정밀점검)","2025-06-10 13:00","2025-06-10 18:00","2025-06-10 13:00","2025-06-10 18:00","연속"]
[42,"남서울","동서울","탄천S/S #65 BUS","2025년 동서울전력지사 170kV GIS 정밀점검","무부하가압용(탄천S/S #2M.Tr GIS정밀점검)","2025-06-05 13:00","2025-06-05 18:00","2025-06-05 13:00","2025-06-05 18:00","연속"]
[43,"남서울","영등포","마곡S/S #1 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 내용 : BUS TIE 정밀점검용 모선휴전","2025-06-07 09:00","2025-06-08 18:00","2025-06-07 09:00","2025-06-08 18:00","연속"]
[44,"남서울","영등포","마곡가양#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 내용 : BUSTIE 정밀점검 후 무부하 가압","2025-06-08 16:00","2025-06-08 18:00","2025-06-08 16:00","2025-06-08 18:00","연속"]
[45,"남서울","직할","대방신길#2 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2025-06-10 09:00","2025-06-10 18:00","2025-06-10 09:00","2025-06-10 18:00","연속"]
[46,"남서울","직할","여의S/S #1 Sh.R CB","170kV GIS 정밀점검공사(#1Sh.R 1차)","170kV GIS 정밀점검공사(#1Sh.R 1차)","2025-06-09 09:00","2025-06-10 18:00","2025-06-09 09:00","2025-06-10 18:00","연속"]
[47,"남서울","직할","여의노량진 T/L","170kV GIS 정밀점검공사(#1Sh.R 1차)","170kV GIS 정밀점검공사(무부하가압용)","2025-06-10 13:00","2025-06-10 18:00","2025-06-10 13:00","2025-06-10 18:00","연속"]
[48,"남서울","직할","여의S/S #2 BUS","170kV GIS 정밀점검공사(#1Sh.R 1차)","170kV GIS 정밀점검공사(무부하가압용)","2025-06-10 13:00","2025-06-10 18:00","2025-06-10 13:00","2025-06-10 18:00","연속"]
[49,"인천","김포","신경서경서#1 T/L","경서S/S  #4M.Tr 1차 GIS 정밀점검 무부하가압","경서S/S  #4M.Tr 1차 GIS 정밀점검 무부하가압","2025-06-22 10:00","2025-06-22 14:00","취소","취소","연속"]
[50,"인천","김포","경서S/S #1 BUS","경서S/S  경서-양촌#1T/L GIS 정밀점검(무부하가압용)","경서S/S  경서-양촌#1T/L GIS 정밀점검(무부하가압용) -#1BUS, 경서양촌#1T/L 자체 활용 무부하가압 (2시간 이내)","2025-06-06 10:00","2025-06-06 18:00","취소","취소","연속"]
[51,"인천","김포","신경서경서#1 T/L","경서S/S  #1M.Tr 1차 GIS 정밀점검(무부하가압용)","경서S/S  #1M.Tr 1차 GIS 정밀점검(무부하가압용) -#1BUS, 신경서경서#1T/L 활용 무부하가압 (2시간 이내)","2025-06-11 10:00","2025-06-11 14:00","취소","취소","연속"]
[52,"인천","김포","경서S/S #1 BUS","경서S/S  #1M.Tr 1차 GIS 정밀점검(무부하가압용)","경서S/S  #1M.Tr 1차 GIS 정밀점검(무부하가압용) -#1BUS, 신경서경서#1T/L 활용 무부하가압 (2시간 이내)","2025-06-11 10:00","2025-06-11 14:00","취소","취소","연속"]
[53,"인천","김포","신경서경서#1 T/L","경서S/S  #2M.Tr 1차 GIS 정밀점검(무부하가압용)","경서S/S  #2M.Tr 1차 GIS 정밀점검(무부하가압용) -#2BUS, 신경서경서#1T/L 활용 무부하가압 (2시간 이내)","2025-06-13 10:00","2025-06-13 18:00","취소","취소","연속"]
[54,"인천","김포","경서S/S #2 BUS","경서S/S  #2M.Tr 1차 GIS 정밀점검(무부하가압용)","경서S/S  #2M.Tr 1차 GIS 정밀점검(무부하가압용) -#2BUS, 신경서경서#1T/L 활용 무부하가압 (2시간 이내)","2025-06-13 10:00","2025-06-13 18:00","취소","취소","연속"]
[55,"인천","김포","신경서경서#2 T/L","EBG 가스 채취밸브 설치 및 해체점검 공사","- EBG 보호동관 가스 채취밸브 미 설치개소 보강","2025-06-17 08:00","2025-06-21 18:00","2025-06-17 08:00","2025-06-21 18:00","연속"]
[56,"인천","김포","경서S/S #1 BUS","경서S/S  #3M.Tr 1차 GIS 정밀점검(무부하가압용)","경서S/S  #3M.Tr 1차 GIS 정밀점검(무부하가압용) -#1BUS, 신경서경서#1T/L 활용 무부하가압 (2시간 이내)","2025-06-18 10:00","2025-06-18 14:00","취소","취소","연속"]
[57,"인천","김포","신경서경서#1 T/L","경서S/S  #3M.Tr 1차 GIS 정밀점검(무부하가압용)","경서S/S  #3M.Tr 1차 GIS 정밀점검(무부하가압용) -#1BUS, 신경서경서#1T/L 활용 무부하가압 (2시간 이내)","2025-06-18 10:00","2025-06-18 14:00","취소","취소","연속"]
[58,"인천","김포","경서S/S CB 6100","경서S/S  #1-#2 BUS TIE GIS 정밀점검","경서S/S  #1-#2 BUS TIE GIS 정밀점검(6100)","2025-06-04 09:00","2025-06-06 18:00","2025-06-04 09:00","2025-06-06 18:00","연속"]
[59,"인천","김포","신경서경서#1 T/L","경서S/S  6100 GIS 정밀점검(무부하가압용)","경서S/S  6100 GIS 정밀점검(무부하가압용) -#1BUS, 신경서경서#1T/L 활용 무부하가압 (2시간 이내)","2025-06-20 10:00","2025-06-20 18:00","2025-06-06 10:00","2025-06-06 18:00","연속"]
[60,"인천","김포","경서양촌#2 T/L","24-25년 부평,김포전력지사 가공송전 협력회사 공사","고정형폴리머 점퍼지지애자 설치","2025-06-24 07:30","2025-06-25 18:00","2025-06-24 07:30","2025-06-25 18:00","연속"]
[61,"인천","김포","경서양촌#1 T/L","경서S/S  경서-양촌#1T/L GIS 정밀점검","경서S/S  경서-양촌#1T/L GIS 정밀점검","2025-06-18 14:00","2025-06-20 18:00","취소","취소","연속"]
[62,"인천","김포","경서S/S #2 BUS","경서S/S  #4M.Tr 1차 GIS 정밀점검(무부하가압용)","경서S/S  #4M.Tr 1차 GIS 정밀점검(무부하가압용) -#2BUS, 신경서경서#1T/L 활용 무부하가압 (2시간 이내)","2025-06-22 10:00","2025-06-22 14:00","취소","취소","연속"]
[63,"인천","김포","경서S/S #1 BUS","경서S/S  6100 GIS 정밀점검(무부하가압용)","경서S/S  6100 GIS 정밀점검(무부하가압용) -#1BUS, 신경서경서#1T/L 활용 무부하가압 (2시간 이내)","2025-06-20 10:00","2025-06-20 18:00","2025-06-06 10:00","2025-06-06 18:00","연속"]
[64,"인천","김포","신김포S/S CB 6200","신김포S/S  #61-#66 BUS TIE GIS 보통점검","신김포S/S  #61-#66 BUS TIE GIS 보통점검(6200) -보조계전기(상시) 교체작업 병행","2025-06-05 10:00","2025-06-05 18:00","2025-06-05 10:00","2025-06-05 18:00","연속"]
[65,"인천","김포","신김포S/S SEC CB 60610","신김포S/S  #60-#61 BUS SEC GIS 보통점검","신김포S/S  #60-#61 BUS SEC GIS 보통점검 -보조계전기(상시) 교체작업 병행","2025-06-09 10:00","2025-06-09 18:00","2025-06-09 10:00","2025-06-09 18:00","연속"]
[66,"인천","김포","신김포S/S SEC CB 65660","신김포S/S  #65-#66 BUS SEC GIS 보통점검","신김포S/S  #65-#66 BUS SEC GIS 보통점검 -보조계전기(상시) 교체작업 병행","2025-06-10 10:00","2025-06-10 18:00","2025-06-10 10:00","2025-06-10 18:00","연속"]
[67,"인천","김포","양곡S/S CB 6100","양곡S/S  GIS 교체공사(4차)_B/T(6100)이용무부하","- BUS-TIE(6100) 이용 무부하 가압 - 양촌양곡#1T/L GIS 교체","2025-06-12 18:00","2025-06-13 18:00","취소","취소","연속"]
[68,"인천","김포","양곡S/S #65 BUS","양곡S/S  GIS 교체공사(4차)","- 양촌양곡#1T/L GIS 교체","2025-06-13 18:00","2025-06-22 14:00","취소","취소","연속"]
[69,"인천","김포","양곡S/S #60 BUS","양곡S/S  GIS 교체공사(4차)","- 양촌양곡#1T/L GIS 교체","2025-06-22 14:00","2025-06-22 18:00","취소","취소","연속"]
[70,"인천","김포","양곡S/S CB 6100","양곡S/S  GIS 교체공사(4차)_B/T(6100)이용무부하","- BUS-TIE(6100) 이용 무부하 가압 - 양촌양곡#1T/L GIS 교체","2025-06-09 18:00","2025-06-09 19:00","취소","취소","연속"]
[71,"인천","김포","양촌양곡#1 T/L","양곡S/S  GIS 교체공사(4차)","- 양촌양곡#1T/L GIS 교체","2025-06-08 16:00","2025-06-22 18:00","취소","취소","연속"]
[72,"인천","김포","양곡S/S #60 BUS","양곡S/S  GIS 교체공사(4차)","- 양촌양곡#1T/L GIS 교체 - 상체크 시험","2025-06-22 14:00","2025-06-22 18:00","취소","취소","연속"]
[73,"인천","김포","신경서왕길#1 T/L","24-25년 가공송전 협력회사 공사","수평추락방지시설 설치 등","2025-06-07 07:00","2025-06-09 18:00","2025-06-07 07:00","2025-06-09 18:00","매일"]
[74,"인천","김포","신경서왕길#2 T/L","24-25년 가공송전 협력회사 공사","수평추락방지시설 설치 등","2025-06-10 07:00","2025-06-12 18:00","2025-06-10 07:00","2025-06-12 18:00","매일"]
[75,"인천","부평","남인천S/S CB 6100","남인천S/S 6100 GIS  혼용화 공사 및 조작시험","남인천S/S 6100 GIS  혼용화 공사 및 조작시험","2025-06-21 09:00","2025-06-21 13:00","2025-06-21 09:00","2025-06-21 13:00","연속"]
[76,"인천","부평","관교만수#2 T/L"," 관교-만수#2T/L 637 GIS 보통점검(오후)"," 관교-만수#2T/L 637 GIS 보통점검(오후)","2025-06-20 09:00","2025-06-20 13:00","취소","취소","연속"]
[77,"인천","부평","주안만수#2 T/L"," 주안-만수#2T/L 647 GIS 보통점검(오후)"," 주안-만수#2T/L 647 GIS 보통점검(오후)","2025-06-20 13:00","2025-06-20 15:00","취소","취소","연속"]
[78,"인천","부평","부개원미#2 T/L"," 부개-원미#2T/L 667 GIS 보통점검"," 부개-원미#2T/L 667 GIS 보통점검","2025-06-10 09:00","2025-06-10 18:00","2025-06-10 09:00","2025-06-10 18:00","연속"]
[79,"인천","부평","부개원미#1 T/L"," 부개-원미#1T/L 657 GIS 보통점검"," 부개-원미#1T/L 657 GIS 보통점검","2025-06-09 09:00","2025-06-09 18:00","2025-06-09 09:00","2025-06-09 18:00","연속"]
[80,"인천","부평","신현송현#1 T/L"," 신현-송현#1T/L 617 GIS 보통점검(오전)"," 신현-송현#1T/L 617 GIS 보통점검(오전)","2025-06-20 09:00","2025-06-20 11:00","취소","취소","연속"]
[81,"인천","부평","송현송월#2 T/L"," 송현-송월#2T/L 627 GIS 보통점검(오후)"," 송현-송월#2T/L 627 GIS 보통점검(오후)","2025-06-20 11:00","2025-06-20 14:00","취소","취소","연속"]
[82,"인천","부평","신가좌S/S SEC CB 66670"," #66-#67 SEC GIS 보통점검"," #66-#67 SEC GIS 보통점검","2025-06-11 13:00","2025-06-11 18:00","취소","취소","연속"]
[83,"인천","부평","신가좌S/S SEC CB 65660"," #65-#66 SEC GIS 보통점검"," #65-#66 SEC GIS 보통점검","2025-06-11 09:00","2025-06-11 13:00","취소","취소","연속"]
[84,"인천","부평","신가좌주안#1 T/L","신가좌-주안#1T/L 647 GIS 보통 점검","신가좌-주안#1T/L 647 GIS 보통 점검","2025-06-01 09:00","2025-06-01 18:00","취소","취소","연속"]
[85,"인천","부평","신가좌주안#2 T/L"," 신가좌-주안#2T/L 617 GIS 보통"," 신가좌-주안#2T/L 617 GIS 보통","2025-06-02 09:00","2025-06-02 18:00","취소","취소","연속"]
[86,"인천","부평","신가좌S/S SEC CB 60610"," #60-#61 SEC GIS 조작시험"," #60-#61 SEC GIS 조작시험","2025-06-05 09:00","2025-06-05 11:00","취소","취소","연속"]
[87,"인천","부평","신가좌S/S SEC CB 61620"," #61-#62 SEC GIS 조작시험"," #61-#62 SEC GIS 조작시험","2025-06-05 11:00","2025-06-05 18:00","취소","취소","연속"]
[88,"인천","부평","신가좌신현#1 T/L","24~25년 가공송전 협력회사 공사","수평 추락방지시설 설치","2025-06-21 07:30","2025-06-21 18:00","2025-06-21 07:30","2025-06-21 18:00","연속"]
[89,"인천","부평","신가좌신현#2 T/L","24~25년 가공송전 협력회사 공사","수평 추락방지시설 설치","2025-06-22 07:30","2025-06-22 18:00","2025-06-22 07:30","2025-06-22 18:00","연속"]
[90,"인천","부평","신가좌S/S Sh.R CB","신가좌S/S  #1Sh.R 보호IED 성능개선","신가좌S/S  #1Sh.R 보호IED 성능개선 - 피앤씨테크제 보호IED 펌웨어 업데이트","2025-06-27 09:00","2025-06-27 18:00","2025-06-27 09:00","2025-06-27 18:00","연속"]
[91,"인천","부평","신경서경서#1 T/L"," 신경서-경서#1T/L 657 GIS GIS 보통점검(오전)"," 신경서-경서#1T/L 657 GIS GIS 보통점검(오전)","2025-06-16 09:00","2025-06-16 18:00","2025-06-16 09:00","2025-06-16 18:00","연속"]
[92,"인천","부평","서인천CC신경서 T/L","신경서-서인천CC T/L CLR TOP HAT BOLT 교체","신경서-서인천CC T/L CLR TOP HAT BOLT 교체, 보통점검","2025-06-30 09:00","2025-06-30 18:00","2025-06-30 09:00","2025-06-30 18:00","연속"]
[93,"인천","부평","영종경서 T/L","EBG 가스 채취밸브 설치 및 해체점검 공사","- EBG 보호동관 가스 채취밸브 미 설치개소 보강","2025-06-09 08:00","2025-06-13 18:00","2025-06-09 08:00","2025-06-13 18:00","연속"]
[94,"인천","부평","북인천원창 T/L"," 북인천-원창T/L 6B7 GIS 보통점검"," 북인천-원창T/L 6B7 GIS 보통점검","2025-06-02 14:00","2025-06-02 18:00","취소","취소","연속"]
[95,"인천","부평","영종을왕 T/L"," 영종-을왕T/L 접속함 해체점검","영종-을왕T/L J/B#4 C상 접속함 해체점검 (수분침투 원인 분석)","2025-06-17 09:00","2025-06-18 18:00","2025-06-17 09:00","2025-06-18 18:00","연속"]
[96,"인천","부평","인천C/C SEC CB 65660","#65-#66 SEC GIS 보통점검,상시여자교체(오후)","#65-#66 SEC GIS 보통점검,상시여자교체(오후)","2025-06-14 13:00","2025-06-14 18:00","2025-06-14 13:00","2025-06-14 18:00","연속"]
[97,"인천","부평","인천C/C SEC CB 60610","#60-#61 SEC GIS 보통점검,상시여자교체(오전)","#60-#61 SEC GIS 보통점검,상시여자교체(오전)","2025-06-14 09:00","2025-06-14 13:00","2025-06-14 09:00","2025-06-14 13:00","연속"]
[98,"인천","부평","인천CC현대제철#2 T/L"," 현대제철#2T/L 657 GIS 조작시험(오후)"," 현대제철#2T/L 657 GIS 조작시험(오후)","2025-06-11 13:00","2025-06-11 18:00","2025-06-11 13:00","2025-06-11 18:00","연속"]
[99,"인천","부평","인천CC현대제철#1 T/L"," 현대제철#1T/L 647 GIS 조작시험(오전)"," 현대제철#1T/L 647 GIS 조작시험(오전)","2025-06-11 09:00","2025-06-11 13:00","2025-06-11 09:00","2025-06-11 13:00","연속"]
[100,"인천","부평","인천C/C CB 6100","#60-#65 BUS TIE 6100 GIS 보통점검,상시여자교체","#60-#65 BUS TIE 6100 GIS 보통점검,상시여자교체","2025-06-05 09:00","2025-06-05 18:00","2025-06-05 09:00","2025-06-05 18:00","연속"]
[101,"인천","부평","인천남인천#2 T/L","인천-남인천#2T/L 627 GIS 보통점검,상시여자교체","인천-남인천#2T/L 627 GIS 보통점검,상시여자교체","2025-06-13 09:00","2025-06-13 18:00","2025-06-13 09:00","2025-06-13 18:00","연속"]
[102,"인천","부평","인천남인천#1 T/L"," 인천-남인천#1T/L 647 GIS 보통점검"," 인천-남인천#1T/L 647 GIS 보통점검","2025-06-12 09:00","2025-06-12 18:00","취소","취소","연속"]
[103,"인천","부평","신가좌인천#1 T/L","신가좌-인천#1T/L 617 GIS 보통점검, 상시여자교체(오전)","신가좌-인천#1T/L 617 GIS 보통점검, 상시여자교체(오전)","2025-06-09 09:00","2025-06-09 13:00","2025-06-09 09:00","2025-06-09 13:00","연속"]
[104,"인천","부평","신가좌인천#2 T/L","신가좌-인천#2T/L 627 GIS 보통점검,상시여자교체(오후)","신가좌-인천#2T/L 627 GIS 보통점검,상시여자교체(오후)","2025-06-09 13:00","2025-06-09 18:00","2025-06-10 13:00","2025-06-10 18:00","연속"]
[105,"인천","부평","주안S/S CB 6100"," 60-65 BUS 모선 보호반 대체공사"," 60-65 BUS 모선 보호반 대체공사","2025-06-19 15:00","2025-06-19 18:00","취소","취소","연속"]
[106,"인천","부평","주안만수#1 T/L"," 주안-만수#1T/L 667 GIS 보통점검"," 주안-만수#1T/L 667 GIS 보통점검","2025-06-19 13:00","2025-06-19 15:00","취소","취소","연속"]
[107,"인천","부평","관교주안 T/L","주안-관교 #1T/L 보통점검, 모자익철거","주안-관교 #1T/L 보통점검, 모자익철거","2025-06-19 09:00","2025-06-19 13:00","취소","취소","연속"]
[108,"인천","부평","학익연수#2 T/L"," 남인천-학익 등 2개T/L 지장이설 및 선종교체공사","ㅇ 공사내용 : 케이블 선종교체(OF→XLPE, 포설 : 9구간, 접속 : 10개소)","2025-06-23 09:00","2025-08-31 18:00","2025-06-23 09:00","2025-08-31 18:00","연속"]
[109,"인천","시흥","오봉남동#2 T/L","대한전선제 EBG 가스채취밸브 보강공사","대한전선제 EBG 가스채취밸브 보강공사","2025-06-17 08:00","2025-06-18 18:00","2025-06-17 08:00","2025-06-18 18:00","연속"]
[110,"인천","시흥","신시흥남동#2 T/L","인천남동 첨단산업단지  신시흥-남동T/L 지중화공사(가공)","1. 공사구간 :  신시흥-남동T/L No.35～신동C/T 2. 선로길이 : ACSR/AW 410㎟ × 2B × 2C, 0.364km 3. 지 지 물 : C/T 신설 1기, 임시철탑 2기, 철탑철거 2기","2025-06-12 08:00","2025-06-16 18:00","2025-06-12 08:00","2025-06-16 18:00","연속"]
[111,"인천","시흥","오봉남동#1 T/L","대한전선제 EBG 가스채취밸브 보강공사","대한전선제 EBG 가스채취밸브 보강공사","2025-06-10 08:00","2025-06-11 18:00","2025-06-10 08:00","2025-06-11 18:00","연속"]
[112,"인천","시흥","신시흥남동#1 T/L","인천남동 첨단산업단지  신시흥-남동T/L 지중화공사(가공)","1. 공사구간 :  신시흥-남동T/L No.35~신동C/T 2. 선로길이 : ACSR/AW 410㎟ × 2B × 2C, 0.364km 3. 지 지 물 : C/T 신설 1기, 임시철탑 2기, 철탑철거 2기","2025-06-05 08:00","2025-06-09 18:00","2025-06-05 08:00","2025-06-09 18:00","연속"]
[113,"인천","시흥","남정왕S/S #65 BUS","2025년 시흥전력지사 170kV GIS 정밀점검 공사","남정왕S/S  #2M.Tr 1차 GIS 정밀점검 시험가압 - 정밀점검 후 시험가압을 위한 휴전","2025-06-13 09:00","2025-06-13 18:00","2025-06-13 09:00","2025-06-13 18:00","연속"]
[114,"인천","시흥","남정왕S/S #60 BUS","2025년 시흥전력지사 170kV GIS 정밀점검 공사","남정왕S/S  6100 BUS TIE 정밀점검 무부하가압 - 정밀점검 후 무부하가압을 위한 휴전","2025-06-04 09:00","2025-06-06 18:00","2025-06-04 09:00","2025-06-06 18:00","연속"]
[115,"인천","시흥","남정왕S/S CB 6100","2025년 시흥전력지사 170kV GIS 정밀점검 공사","남정왕S/S  #1 BUS TIE(6100) GIS 정밀점검 - 정밀점검 및 무부하가압을 위한 휴전","2025-06-04 09:00","2025-06-06 18:00","2025-06-04 09:00","2025-06-06 18:00","연속"]
[116,"인천","시흥","남시화남정왕#2 T/L","2025년 시흥전력지사 170kV GIS 정밀점검 공사","남정왕S/S  #2M.Tr 1차 GIS 정밀점검 시험가압 - 정밀점검 후 시험가압을 위한 휴전","2025-06-13 09:00","2025-06-13 18:00","2025-06-13 09:00","2025-06-13 18:00","연속"]
[117,"인천","시흥","남정왕S/S #60 BUS","2025년 시흥전력지사 170kV GIS 정밀점검 공사","남정왕S/S  #1M.Tr 1차 GIS 정밀점검 시험가압 - 정밀점검 후 시험가압을 위한 휴전","2025-06-11 09:00","2025-06-11 18:00","2025-06-11 09:00","2025-06-11 18:00","연속"]
[118,"인천","시흥","남시화남정왕#1 T/L","2025년 시흥전력지사 170kV GIS 정밀점검 공사","남정왕S/S  #1M.Tr 1차 GIS 정밀점검 시험가압 - 정밀점검 후 시험가압을 위한 휴전","2025-06-11 09:00","2025-06-11 18:00","2025-06-11 09:00","2025-06-11 18:00","연속"]
[119,"인천","시흥","남시화남정왕#1 T/L","2025년 시흥전력지사 170kV GIS 정밀점검 공사","남정왕S/S  6100 BUS TIE 정밀점검 무부하가압 - 정밀점검 후 무부하가압을 위한 휴전","2025-06-06 09:00","2025-06-06 18:00","2025-06-06 09:00","2025-06-06 18:00","연속"]
[120,"인천","시흥","신시흥도림#1 T/L","도림S/S 신시흥도림#1T/L GIS 보통점검","도림S/S 신시흥도림#1T/L GIS 보통점검 -신시흥 신시흥도림#1T/L GIS 조작시험 병행","2025-06-04 09:00","2025-06-04 14:00","취소","취소","연속"]
[121,"인천","시흥","도림오봉#1 T/L","도림SS  도림오봉#1T/L GIS 보통점검","도림SS  도림오봉#1T/L GIS 보통점검","2025-06-04 14:00","2025-06-04 18:00","취소","취소","연속"]
[122,"인천","시흥","온수소래 T/L","소래S/S  온수소래T/L GIS 조작시험","소래S/S  온수소래T/L GIS 조작시험","2025-06-07 14:00","2025-06-07 18:00","2025-06-07 14:00","2025-06-07 18:00","연속"]
[123,"인천","시흥","신광명소래 T/L","소래S/S  신광명소래T/L GIS 조작시험","소래S/S  신광명소래T/L GIS 조작시험","2025-06-07 09:00","2025-06-07 14:00","2025-06-07 09:00","2025-06-07 14:00","연속"]
[124,"인천","시흥","서서울#2소래 T/L","피뢰기 열화진단 및 EBA 가스채취","- 피뢰기 열화진단 : 서소#1C/T, 서소#2C/T - EBA 가스채취 : 소래C/T","2025-06-15 08:00","2025-06-15 18:00","2025-06-15 08:00","2025-06-15 18:00","연속"]
[125,"인천","시흥","서안양소래 T/L","EBA 가스채취","EBA 가스채취","2025-06-14 08:00","2025-06-14 18:00","2025-06-14 08:00","2025-06-14 18:00","연속"]
[126,"인천","시흥","신시흥#1S/S #65 BUS","신시흥S/S  Sh.R 증설공사","- #65BUS adt bay 및 endcover 설치","2025-06-02 09:00","2025-06-08 18:00","취소","취소","연속"]
[127,"인천","시흥","신시흥S/S SEC CB 60610","신시흥S/S  #61-#62 SEC GIS 조작시험","신시흥S/S  #61-#62 SEC GIS 조작시험","2025-06-09 09:00","2025-06-09 12:00","2025-06-09 09:00","2025-06-09 12:00","연속"]
[128,"인천","시흥","신시흥도림#2 T/L","신시흥S/S  Sh.R 증설공사","- #60BUS 무부하 가압","2025-06-14 13:00","2025-06-15 13:00","취소","취소","연속"]
[129,"인천","시흥","신시흥S/S SEC CB 66670","신시흥S/S  #66-#67 SEC GIS 조작시험","신시흥S/S  #66-#67 SEC GIS 조작시험","2025-06-09 12:00","2025-06-09 15:00","2025-06-09 12:00","2025-06-09 15:00","연속"]
[130,"인천","시흥","신시흥S/S CB 6100","신시흥S/S  6100 B/T GIS 조작시험","신시흥S/S  6100(60-65) B/T GIS 조작시험","2025-06-02 09:00","2025-06-02 12:00","취소","취소","연속"]
[131,"인천","시흥","신시흥#1S/S #60 BUS","신시흥S/S  Sh.R 증설공사","- #60BUS adt bay 및 endcover 설치","2025-06-09 09:00","2025-06-15 18:00","취소","취소","연속"]
[132,"인천","시흥","신시흥도림#2 T/L","신시흥S/S  Sh.R 증설공사","- #65BUS 무부하 가압","2025-06-07 13:00","2025-06-08 13:00","취소","취소","연속"]
[133,"인천","시흥","신시흥S/S SEC CB 65660","신시흥S/S  65-66 Sec. GIS 조작시험","신시흥S/S  65-66 Sec. GIS 조작시험","2025-06-02 15:00","2025-06-02 18:00","2025-06-02 15:00","2025-06-02 18:00","연속"]
[134,"인천","시흥","신시흥S/S SEC CB 60610","신시흥S/S  60-61 Sec. GIS 조작시험","신시흥S/S  60-61 Sec. GIS 조작시험","2025-06-02 12:00","2025-06-02 15:00","2025-06-02 12:00","2025-06-02 15:00","연속"]
[135,"인천","시흥","신시흥S/S CB 6300","신시흥S/S  6300 B/T(62-67) GIS 조작시험","신시흥S/S  6300 B/T(62-67) GIS 조작시험","2025-06-09 15:00","2025-06-09 18:00","2025-06-09 15:00","2025-06-09 18:00","연속"]
[136,"인천","시흥","남동연수#2 T/L","연수S/S  남동연수#2 T/L GIS 보통점검","연수S/S  남동연수#2 T/L GIS 보통점검","2025-06-22 14:00","2025-06-22 18:00","2025-06-22 14:00","2025-06-22 18:00","연속"]
[137,"인천","시흥","남동연수#1 T/L","연수S/S  남동연수#1 T/L GIS 보통점검","연수S/S  남동연수#1 T/L GIS 보통점검","2025-06-22 09:00","2025-06-22 14:00","2025-06-22 09:00","2025-06-22 14:00","연속"]
[138,"인천","직할","갈산부흥#2 T/L"," 갈산-도당#2T/L 지중선로 인출정비공사(무부하가압)","○ 선종 및 회선수 :  XLPE 2000㎟, 1회선 0.4km ○ 공사내용 :  신부평-도당#2T/L 철거(1구간, 접속 2개소)  갈산-도당#2T/L 신설(1구간, 접속 2개소)","2025-06-21 09:00","2025-06-22 15:00","2025-06-21 09:00","2025-06-22 15:00","연속"]
[139,"인천","직할","갈산S/S #61 BUS"," 갈산-도당#2T/L 지중선로 인출정비공사(무부하가압)","○ 선종 및 회선수 :  XLPE 2000㎟, 1회선 0.4km ○ 공사내용 :  신부평-도당#2T/L 철거(1구간, 접속 2개소)  갈산-도당#2T/L 신설(1구간, 접속 2개소)","2025-06-21 09:00","2025-06-22 15:00","2025-06-21 09:00","2025-06-22 15:00","연속"]
[140,"인천","직할","임학계양#2 T/L","'24-'25년 가공송전 협력회사 공사","수평 추락방지시설 설치","2025-06-29 07:00","2025-06-30 18:00","2025-06-29 07:00","2025-06-30 18:00","매일"]
[141,"인천","직할","임학계양#1 T/L","'24-'25년 가공송전 협력회사 공사","수평 추락방지시설 설치","2025-06-27 07:00","2025-06-28 18:00","2025-06-27 07:00","2025-06-28 18:00","매일"]
[142,"인천","직할","도당S/S #66 BUS"," 갈산-도당#2T/L 지중선로 인출정비공사(무부하가압)","○ 선종 및 회선수 :  XLPE 2000㎟, 1회선 0.4km ○ 공사내용 :  신부평-도당#2T/L 철거(1구간, 접속 2개소)  갈산-도당#2T/L 신설(1구간, 접속 2개소)","2025-06-21 09:00","2025-06-22 15:00","2025-06-21 09:00","2025-06-22 15:00","연속"]
[143,"인천","직할","경서북인천#1 T/L","북인천S/S #3M.Tr 교체공사","북인천S/S #3M.Tr 무부하가압용","2025-06-28 09:00","2025-06-29 18:00","2025-06-28 09:00","2025-06-29 18:00","연속"]
[144,"인천","직할","북인천S/S #60 BUS"," 북인천S/S #3M.Tr 교체공사"," 북인천S/S #3M.Tr 교체공사 무부하가압","2025-06-28 09:00","2025-06-29 18:00","2025-06-28 09:00","2025-06-29 18:00","연속"]
[145,"인천","직할","경서북인천#2 T/L","북인천S/S 경서북인천#2T/L GIS 보통점검","북인천S/S 경서북인천#2T/L GIS 보통점검","2025-06-02 09:00","2025-06-02 18:00","2025-06-02 09:00","2025-06-02 18:00","연속"]
[146,"경기북부","고양","양주고양#2 T/L","24~25년 고양전력 가공송전협력회사 총액공사","항공시설물 설치, 금구류 교체","2025-06-04 07:00","2025-06-05 17:00","2025-06-04 07:00","2025-06-05 17:00","연속"]
[147,"경기북부","고양","월롱금촌#1 T/L","24~25년 고양전력 가공송전협력회사 총액공사","불량애자교체","2025-06-11 07:00","2025-06-11 13:00","2025-06-11 07:00","2025-06-11 13:00","연속"]
[148,"경기북부","고양","양주금촌#2 T/L","24~25년 고양전력 가공송전협력회사 총액공사","항공시설물 설치, 금구류 교체","2025-06-04 07:00","2025-06-05 17:00","2025-06-04 07:00","2025-06-05 17:00","연속"]
[149,"경기북부","고양","월롱금촌#2 T/L","24~25년 고양전력 가공송전협력회사 총액공사","불량애자교체, 항공구설치, 압축크램프교체","2025-06-11 13:00","2025-06-11 17:00","2025-06-11 13:00","2025-06-11 17:00","연속"]
[150,"경기북부","고양","고양일산#2 T/L","24~25년 고양전력 가공송전협력회사 총액공사","불량애자교체","2025-06-13 07:00","2025-06-13 17:00","2025-06-13 07:00","2025-06-13 17:00","연속"]
[151,"경기북부","고양","일산S/S #2G/T CB","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-06-10 09:00","2025-06-10 18:00","2025-06-10 09:00","2025-06-10 18:00","연속"]
[152,"경기북부","고양","일산S/S #1G/T CB","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-06-09 09:00","2025-06-09 18:00","2025-06-09 09:00","2025-06-09 18:00","연속"]
[153,"경기북부","고양","일산지도#2 T/L","24~25년 고양전력 가공송전협력회사 총액공사","불량애자교체, 점퍼선소켓교체","2025-06-13 07:00","2025-06-13 17:00","2025-06-13 07:00","2025-06-13 17:00","연속"]
[154,"경기북부","구리","미금구리#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 조작시험","2025-06-20 09:00","2025-06-20 14:00","2025-06-20 09:00","2025-06-20 14:00","연속"]
[155,"경기북부","구리","미금구리#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 조작시험","2025-06-20 14:00","2025-06-20 18:00","2025-06-20 14:00","2025-06-20 18:00","연속"]
[156,"경기북부","구리","신장덕소#2 T/L","구리송전협력회사 공사_피뢰기 설치"," 신장-덕소T/L 피뢰기 설치 (No.25~26) 2개소","2025-06-11 07:00","2025-06-11 18:00","2025-06-11 07:00","2025-06-11 18:00","연속"]
[157,"경기북부","구리","덕소팔당HP T/L","25~26년 지중송전 협력회사 공사(경기북부본부 직할)","C/T 금구류 교체","2025-06-19 09:00","2025-06-19 18:00","2025-06-19 09:00","2025-06-19 18:00","연속"]
[158,"경기북부","구리","덕소팔당HP청평HP T/L","25~26년 지중송전 협력회사 공사(경기북부본부 직할)","C/T 금구류 교체","2025-06-26 09:00","2025-06-26 18:00","2025-06-26 09:00","2025-06-26 18:00","연속"]
[159,"경기북부","구리","미금S/S #62 BUS","24-25년 구리전력지사 변전협력회사 총액공사","미금S/S DC 접지 발생관련 조치","2025-06-23 09:00","2025-06-23 18:00","2025-06-23 09:00","2025-06-23 18:00","연속"]
[160,"경기북부","구리","미금화양 T/L","구리송전협력회사 공사_수평 추락방지장치 설치"," 미금-화양T/L수평 가공암 추락방지장치 설치(No.3, 5, 6) 3개소","2025-06-12 07:00","2025-06-12 18:00","취소","취소","연속"]
[161,"경기북부","구리","미금광장 T/L","구리송전협력회사 공사_수평 추락방지장치 설치"," 미금-광장T/L 가공암 수평 추락방지장치 설치(No.3, 5, 6) 3개소","2025-06-11 07:00","2025-06-11 18:00","2025-06-11 07:00","2025-06-11 18:00","연속"]
[162,"경기북부","구리","동서울서종#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-06-17 09:00","2025-06-17 18:00","2025-06-17 09:00","2025-06-17 18:00","연속"]
[163,"경기북부","구리","동서울서종#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-06-16 09:00","2025-06-16 18:00","2025-06-16 09:00","2025-06-16 18:00","연속"]
[164,"경기북부","구리","신포천백학#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  신포천-백학#1 No.7~8,21~39 (母 : 345kV 신덕은-동두천CC#2T/L No.18~19,32~50)","2025-06-02 07:00","2025-06-04 18:00","2025-06-02 07:00","2025-06-04 18:00","연속"]
[165,"경기북부","구리","곤지암용문#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 초기점검","2025-06-19 09:00","2025-06-19 18:00","2025-06-19 09:00","2025-06-19 18:00","연속"]
[166,"경기북부","구리","곤지암용문#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 초기점검","2025-06-18 09:00","2025-06-18 18:00","2025-06-18 09:00","2025-06-18 18:00","연속"]
[167,"경기북부","구리","장암진접#1 T/L","남양주진접2 공공주택지구 송전선로 임시이설공사"," 진접분기T/L No.22~27 지중화 전 임시선로 구성","2025-06-10 07:00","2025-06-12 18:00","2025-06-10 07:00","2025-06-12 18:00","연속"]
[168,"경기북부","구리","장암진접#1 T/L","남양주진접2 공공주택지구 송전선로 임시이설공사"," 진접분기T/L No.22~27 지중화 전 임시선로 구성","2025-06-05 07:00","2025-06-05 18:00","취소","취소","연속"]
[169,"경기북부","구리","별내진접 T/L","남양주진접2 공공주택지구 송전선로 임시이설공사"," 진접분기T/L No.22~27 지중화 전 임시선로 구성","2025-06-06 07:00","2025-06-09 18:00","취소","취소","연속"]
[170,"경기북부","구리","포천운천#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","포천변전소 인출 철구 부재 교체","2025-06-20 07:00","2025-06-20 12:00","2025-06-20 07:00","2025-06-20 12:00","연속"]
[171,"경기북부","구리","용정포천#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","포천변전소 인출 철구 부재 교체","2025-06-19 07:00","2025-06-19 12:00","2025-06-19 07:00","2025-06-19 12:00","연속"]
[172,"경기북부","구리","신포천포천#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","포천변전소 인출 철구 부재 교체","2025-06-20 07:00","2025-06-20 12:00","2025-06-20 07:00","2025-06-20 12:00","연속"]
[173,"경기북부","구리","포천운천#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","포천변전소 인출 철구 부재 교체","2025-06-20 12:00","2025-06-20 18:00","2025-06-20 12:00","2025-06-20 18:00","연속"]
[174,"경기북부","구리","신포천포천#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","포천변전소 인출 철구 부재 교체","2025-06-19 12:00","2025-06-19 18:00","2025-06-19 12:00","2025-06-19 18:00","연속"]
[175,"경기북부","구리","용정포천#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","포천변전소 인출 철구 부재 교체","2025-06-19 12:00","2025-06-19 18:00","2025-06-19 12:00","2025-06-19 18:00","연속"]
[176,"경기북부","직할","신의정부금오#1 T/L","25년 직할 170kV GIS 점검공사","170kV GIS 정밀점검","2025-06-16 09:00","2025-06-17 18:00","2025-06-16 09:00","2025-06-17 18:00","연속"]
[177,"경기북부","직할","금오상계#2 T/L","25년 직할 170kV GIS 점검공사","170kV GIS 정밀점검(신의정부-금오2TL) 시험가압용 선로","2025-06-12 09:00","2025-06-12 18:00","2025-06-12 09:00","2025-06-12 18:00","연속"]
[178,"경기북부","직할","신의정부금오#2 T/L","25년 직할 170kV GIS 점검공사","170kV GIS 정밀점검(신의정부, 금오 양단)","2025-06-09 09:00","2025-06-12 18:00","2025-06-16 09:00","2025-06-19 18:00","연속"]
[179,"경기북부","직할","금오상계#1 T/L","25년 직할 170kV GIS 점검공사","170kV GIS 정밀점검(신의정부-금오1TL) 시험가압용 선로","2025-06-17 09:00","2025-06-17 18:00","2025-06-17 09:00","2025-06-17 18:00","연속"]
[180,"경기북부","직할","신포천동두천#2 T/L","345kV 동두천CC-양주T/L 건설공사","345kV 동두천CC-양주T/L 건설공사","2025-06-09 09:00","2025-06-13 18:00","2025-06-09 07:00","2025-06-13 18:00","연속"]
[181,"경기북부","직할","신포천동두천#1 T/L","345kV 동두천CC-양주T/L 건설공사","345kV 동두천CC-양주T/L 건설공사","2025-06-14 09:00","2025-06-17 18:00","2025-06-04 09:00","2025-06-08 18:00","연속"]
[182,"경기북부","직할","옥정동두천#1 T/L","345kV 동두천CC-양주T/L 건설공사","345kV 동두천CC-양주T/L 건설공사","2025-06-14 09:00","2025-06-17 18:00","2025-06-14 09:00","2025-06-17 18:00","연속"]
[183,"경기북부","직할","신의정부내촌#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","345kV 신가평-신의정부T/L 수평추락방지시설 설치(병가구간)","2025-06-28 07:00","2025-06-28 18:00","2025-06-28 07:00","2025-06-28 18:00","연속"]
[184,"경기북부","직할","신의정부S/S SEC CB 60610","25년 직할 170kV GIS 점검공사","170kV GIS 보통점검","2025-06-05 09:00","2025-06-05 18:00","2025-06-05 09:00","2025-06-05 18:00","연속"]
[185,"경기북부","직할","신의정부S/S CB 6300","25년 직할 170kV GIS 점검공사","170kV GIS 보통점검","2025-06-04 09:00","2025-06-04 18:00","2025-06-04 09:00","2025-06-04 18:00","연속"]
[186,"경기북부","직할","신의정부S/S CB 6200","25년 직할 170kV GIS 점검공사","170kV GIS 보통점검","2025-06-02 09:00","2025-06-02 18:00","2025-06-02 09:00","2025-06-02 18:00","연속"]
[187,"경기북부","직할","양주녹양#1 T/L","24-25 직할 변전협력 총액공사","양주-녹양#1T/L DS 점검","2025-06-11 09:00","2025-06-11 18:00","2025-06-11 09:00","2025-06-11 18:00","연속"]
[188,"경기북부","직할","양주쌍문#1 T/L","24~25년 고양전력 가공송전협력회사 총액공사","불량애자교체","2025-06-09 07:00","2025-06-10 17:00","2025-06-09 07:00","2025-06-10 17:00","연속"]
[189,"경기북부","직할","신의정부용현#2 T/L","용현SS 용현전철#2TL 무부하 시험가압","용현SS 용현전철#2TL 무부하 시험가압시 신의정부용현#2, #2BUS 이용 코레일 측 케이블 복구공사 일정에 따라 휴전일정 변경 가능","2025-06-02 09:00","2025-06-02 18:00","2025-06-02 09:00","2025-06-02 18:00","연속"]
[190,"경기북부","직할","운천전곡#2 T/L","25년 직할 170kV GIS 점검공사","170kV GIS 정밀점검(신포천-전곡2TL) 시험가압용 선로","2025-06-24 09:00","2025-06-24 18:00","2025-06-24 09:00","2025-06-24 18:00","연속"]
[191,"경기북부","직할","신포천전곡#2 T/L","25년 직할 170kV GIS 점검공사","170kV GIS 정밀점검","2025-06-23 09:00","2025-06-24 18:00","2025-06-23 09:00","2025-06-24 18:00","연속"]
[192,"경기북부","직할","운천전곡#1 T/L","25년 직할 170kV GIS 점검공사","170kV GIS 정밀점검(신포천-전곡1TL) 시험가압용 선로","2025-06-19 09:00","2025-06-19 18:00","2025-06-19 09:00","2025-06-19 18:00","연속"]
[193,"경기북부","직할","신포천전곡#1 T/L","25년 직할 170kV GIS 점검공사","170kV GIS 정밀점검","2025-06-18 09:00","2025-06-19 18:00","2025-06-18 09:00","2025-06-19 18:00","연속"]
[194,"경기","군포","목내성곡#2 T/L"," 목내-성곡#2T/L 대한제 EBG 가스채취밸브 설치공사"," 목내-성곡#2T/L 대한제 EBG 가스채취밸브 3상 설치","2025-06-30 08:00","2025-07-01 17:00","2025-06-30 08:00","2025-07-01 17:00","연속"]
[195,"경기","군포","서서울산본#1 T/L","산본S/S 서서울-산본#1T/L GIS 보통점검","산본S/S 서서울-산본#1T/L GIS 보통점검 시행","2025-06-18 09:00","2025-06-18 18:00","2025-06-18 09:00","2025-06-18 18:00","연속"]
[196,"경기","군포","서서울#2S/S SEC CB 68690","[GIS정밀]서서울2S/S #68-69 SEC GIS 정밀점검","서서울2S/S #68-69 SEC GIS 정밀점검 시행","2025-06-18 09:00","2025-06-19 18:00","취소","취소","연속"]
[197,"경기","군포","서서울#2S/S #63 BUS","[GIS정밀]서서울2S/S #63 BUS 무부하가압용 휴전","서서울2S/S #63-64 SEC GIS 정밀점검 관련 무부하가압용 휴전설비","2025-06-17 16:00","2025-06-17 18:00","취소","취소","연속"]
[198,"경기","군포","서서울#2일동#1 T/L","[GIS정밀]서서울2S/S 서서울2-일동#1T/L 무부하가압용 송전선로","서서울2S/S #63-64 SEC GIS 정밀점검 관련 무부하가압용 송전선로","2025-06-17 16:00","2025-06-17 18:00","취소","취소","연속"]
[199,"경기","군포","서서울#2S/S SEC CB 63640","[GIS정밀]서서울2S/S #63-64 SEC GIS 정밀점검","서서울2S/S #63-64 SEC GIS 정밀점검 시행","2025-06-16 09:00","2025-06-17 18:00","취소","취소","연속"]
[200,"경기","군포","서서울#2일동#2 T/L","[GIS정밀]서서울2S/S 서서울2-일동#2T/L GIS 정밀점검","서서울2S/S 서서울2-일동#2T/L GIS 정밀점검 시행","2025-06-12 09:00","2025-06-13 18:00","2025-06-12 09:00","2025-06-13 18:00","연속"]
[201,"경기","군포","서서울#2일동#1 T/L","[GIS정밀]서서울2S/S 서서울2-일동#1T/L GIS 정밀점검","서서울2S/S 서서울2-일동#1T/L GIS 정밀점검 시행","2025-06-10 09:00","2025-06-11 18:00","2025-06-10 09:00","2025-06-11 18:00","연속"]
[202,"경기","군포","서서울#2일동#1 T/L","[GIS정밀]서서울2S/S 서서울2-일동#1T/L 무부하가압용 송전선로","서서울2S/S #64-69 TIE GIS 정밀점검 관련 무부하가압용 송전선로","2025-06-26 16:00","2025-06-26 18:00","취소","취소","연속"]
[203,"경기","군포","서서울#2S/S #68 BUS","[GIS정밀]서서울2S/S #68 BUS 무부하가압용 휴전","서서울2S/S #64-69 TIE GIS 정밀점검 관련 무부하가압용 휴전설비","2025-06-26 16:00","2025-06-26 18:00","취소","취소","연속"]
[204,"경기","군포","서서울#2S/S CB 6600","[GIS정밀]서서울2S/S #64-69 TIE GIS 정밀점검","서서울2S/S #64-69 TIE GIS 정밀점검 시행","2025-06-25 09:00","2025-06-26 18:00","취소","취소","연속"]
[205,"경기","군포","서서울#2S/S #69 BUS","[GIS정밀]서서울2S/S #69 BUS 무부하가압용 휴전","서서울2S/S #64-69 TIE GIS 정밀점검 관련 무부하가압용 휴전설비","2025-06-25 09:00","2025-06-26 18:00","취소","취소","연속"]
[206,"경기","군포","서서울#2서안양 T/L","피뢰기 열화진단","- 피뢰기 열화진단 : 서소#1C/T, 서소#2C/T","2025-06-21 08:00","2025-06-21 18:00","취소","취소","연속"]
[207,"경기","군포","서서울#2일동#1 T/L","[GIS정밀]서서울2S/S 서서울2-일동#1T/L 무부하가압용 송전선로","서서울2S/S #63-68 TIE GIS 정밀점검 관련 무부하가압용 송전선로","2025-06-24 16:00","2025-06-24 18:00","취소","취소","연속"]
[208,"경기","군포","서서울#2S/S CB 6500","[GIS정밀]서서울2S/S #63-68 TIE GIS 정밀점검","서서울2S/S #63-68 TIE GIS 정밀점검 시행","2025-06-23 09:00","2025-06-24 18:00","취소","취소","연속"]
[209,"경기","군포","서서울#2S/S #68 BUS","[GIS정밀]서서울2S/S #68 BUS 무부하가압용 휴전","서서울2S/S #68-69 SEC GIS 정밀점검 관련 무부하가압용 휴전설비","2025-06-19 16:00","2025-06-19 18:00","취소","취소","연속"]
[210,"경기","군포","서서울#2S/S #68 BUS","[GIS정밀]서서울2S/S #68 BUS 무부하가압용 휴전","서서울2S/S #63-68 TIE GIS 정밀점검 관련 무부하가압용 휴전설비","2025-06-23 09:00","2025-06-24 18:00","취소","취소","연속"]
[211,"경기","군포","서서울#2일동#1 T/L","[GIS정밀]서서울2S/S 서서울2-일동#1T/L 무부하가압용 송전선로","서서울2S/S #68-69 SEC GIS 정밀점검 관련 무부하가압용 송전선로","2025-06-19 16:00","2025-06-19 18:00","취소","취소","연속"]
[212,"경기","군포","성포안산#2 T/L"," 성포-안산#2T/L 대한제 EBG 가스채취밸브 설치공사"," 성포-안산#2T/L 대한제 EBG 가스채취밸브 6상 설치","2025-06-09 08:00","2025-06-13 17:00","2025-06-09 08:00","2025-06-13 17:00","연속"]
[213,"경기","군포","반월시화#1 T/L","[GIS정밀]시화S/S 반월-시화#1T/L 무부하가압용 송전선로","시화S/S #3M.Tr 1차 GIS 정밀점검 관련 무부하가압용 송전선로","2025-06-02 14:00","2025-06-02 18:00","2025-06-02 14:00","2025-06-02 18:00","연속"]
[214,"경기","군포","반월시화#2 T/L","[GIS정밀]시화S/S 반월-시화#2T/L 무부하가압용 송전선로","시화S/S #4M.Tr 1차 GIS 정밀점검 관련 무부하가압용 송전선로","2025-06-05 14:00","2025-06-05 18:00","2025-06-05 14:00","2025-06-05 18:00","연속"]
[215,"경기","군포","시화성곡 T/L","시화S/S 시화-성곡T/L GIS 보통점검","시화S/S 시화-성곡T/L GIS 보통점검 시행","2025-06-04 09:00","2025-06-04 18:00","2025-06-04 09:00","2025-06-04 18:00","연속"]
[216,"경기","군포","신안산S/S #60 BUS","신안산S/S #60BUS 휴전(신안산-성포#1T/L 보수 관련)","신안산S/S 신안산-성포#1T/L GIS 611DS 구동모터 불량 보수 관련 #60BUS 휴전 시행","2025-06-27 09:00","2025-06-27 18:00","2025-06-27 09:00","2025-06-27 18:00","연속"]
[217,"경기","군포","신안산성포#1 T/L","신안산S/S 신안산-성포#1T/L 611DS 구동모터 불량 보수","신안산S/S 신안산-성포#1T/L GIS 611DS 구동모터 불량 보수 시행","2025-06-27 09:00","2025-06-27 18:00","2025-06-27 09:00","2025-06-27 18:00","연속"]
[218,"경기","군포","산본안양#2 T/L","안양S/S 산본-안양#2T/L GIS 보통, 유사고장 점검","안양S/S 산본-안양#2T/L GIS 보통점검 및 유사고장 점검 시행","2025-06-19 09:00","2025-06-19 18:00","2025-06-19 09:00","2025-06-19 18:00","연속"]
[219,"경기","군포","산본안양#1 T/L","안양S/S 산본-안양#1T/L GIS 보통, 유사고장 점검","안양S/S 산본-안양#1T/L GIS 보통점검 및 유사고장 점검 시행","2025-06-17 09:00","2025-06-17 18:00","2025-06-17 09:00","2025-06-17 18:00","연속"]
[220,"경기","군포","화성장덕#1 T/L","[GIS정밀]장덕S/S 화성-장덕#1T/L 무부하가압용 송전선로","장덕S/S 현대자동차#1T/L GIS 정밀점검 관련 무부하가압용 송전선로","2025-06-07 14:00","2025-06-07 18:00","2025-06-07 14:00","2025-06-07 18:00","연속"]
[221,"경기","동부","감곡가남#2 T/L"," 이천-가남 등 2개T/L 용량증대 선종교체공사"," 감곡-가남T/L No.25~가남S/S 18.2km, 선종교체 ACSR240㎟→ASCC310㎟","2025-06-17 09:00","2025-07-15 18:00","취소","취소","연속"]
[222,"경기","동부","감곡가남#1 T/L"," 이천-가남 등 2개T/L 용량증대 선종교체공사"," 감곡-가남T/L No.25~가남S/S 18.2km, 선종교체 ACSR240㎟→ASCC310㎟","2025-06-12 09:00","2025-06-16 18:00","취소","취소","연속"]
[223,"경기","동부","감곡가남#2 T/L"," 이천-가남 등 2개T/L 용량증대 선종교체공사"," 감곡-가남T/L No.25~가남S/S 18.2km, 선종교체 ACSR240㎟→ASCC310㎟","2025-06-09 09:00","2025-06-11 18:00","취소","취소","연속"]
[224,"경기","동부","감곡가남#1 T/L"," 이천-가남 등 2개T/L 용량증대 선종교체공사"," 감곡-가남T/L No.25~가남S/S 18.2km, 선종교체 ACSR240㎟→ASCC310㎟","2025-06-05 09:00","2025-06-08 18:00","취소","취소","연속"]
[225,"경기","동부","곤지암S/S SEC CB 66670","곤지암S/S  66-67 SEC GIS 보통점검","곤지암S/S  66-67 SEC GIS 보통점검","2025-06-11 09:00","2025-06-11 18:00","2025-06-11 09:00","2025-06-11 18:00","연속"]
[226,"경기","동부","곤지암S/S SEC CB 61620","곤지암S/S  61-62 SEC GIS 보통점검","곤지암S/S  61-62 SEC GIS 보통점검","2025-06-10 09:00","2025-06-10 18:00","2025-06-10 09:00","2025-06-10 18:00","연속"]
[227,"경기","동부","성현분당#1 T/L"," 성현-분당#1T/L 추락방지장치 설치공사","성현-분당#1T/L 수평추락방지장치 설치(야탑-성현#1T/L과 병가)","2025-06-02 08:00","2025-06-10 18:00","취소","취소","연속"]
[228,"경기","동부","오포모현#1 T/L"," 모현-용인T/L OPGW 증설 및 지중화공사","- OPGW 임시이설(1.944km) 및 본이설(4.706km) - OPGW 증설교체(24C-&gt48C) : 10.78km - 광코어 접속, 최종시험 및 기타 부대공사 1식","2025-06-01 07:00","2025-06-01 18:00","2025-06-01 07:00","2025-06-01 18:00","연속"]
[229,"경기","성남","북동탄동탄2열병합#2 T/L","2025년 성남전력 362, 170kV GIS 보통점검공사","gis 보통점검","2025-06-18 09:00","2025-06-19 18:00","2025-06-18 09:00","2025-06-19 18:00","연속"]
[230,"경기","성남","북동탄동탄2열병합#1 T/L","2025년 성남전력 362, 170kV GIS 보통점검공사","gis 보통점검","2025-06-16 09:00","2025-06-17 18:00","2025-06-16 09:00","2025-06-17 18:00","연속"]
[231,"경기","성남","삼미동탄2열병합#1 T/L","2025년 성남전력 362, 170kV GIS 보통점검공사","gis 보통점검","2025-06-09 09:00","2025-06-10 18:00","2025-06-09 09:00","2025-06-10 18:00","연속"]
[232,"경기","성남","삼미동탄2열병합#2 T/L","2025년 성남전력 362, 170kV GIS 보통점검공사","gis 보통점검","2025-06-11 09:00","2025-06-12 18:00","2025-06-11 09:00","2025-06-12 18:00","연속"]
[233,"경기","성남","삼미동탄2열병합#3 T/L","2025년 성남전력 362, 170kV GIS 보통점검공사","gis 보통점검","2025-06-26 09:00","2025-06-27 18:00","취소","취소","연속"]
[234,"경기","성남","신성남정자#1 T/L","2025년 성남전력 변전협력회사 총액공사","GIS 조작시험 limit 교체","2025-06-10 14:00","2025-06-10 18:00","취소","취소","연속"]
[235,"경기","성남","신성남서판교#2 T/L","2025년 성남전력 170kV GIS 정밀점검공사","신성남)GIS 정밀점검","2025-06-09 09:00","2025-06-11 18:00","2025-06-09 09:00","2025-06-11 18:00","연속"]
[236,"경기","성남","신수원S/S CB 6300","2025년 성남전력 변전협력회사 총액공사","gis 조작시험","2025-06-11 14:00","2025-06-11 18:00","2025-06-11 14:00","2025-06-11 18:00","연속"]
[237,"경기","성남","신수원S/S SEC CB 60610","2025년 성남전력 변전협력회사 총액공사","gis 조작시험","2025-06-10 09:00","2025-06-10 14:00","2025-06-10 09:00","2025-06-10 14:00","연속"]
[238,"경기","성남","신수원S/S SEC CB 66670","2025년 성남전력 변전협력회사 총액공사","gis 조작시험","2025-06-10 14:00","2025-06-10 18:00","2025-06-10 14:00","2025-06-10 18:00","연속"]
[239,"경기","성남","신수원S/S CB 6100","2025년 성남전력 변전협력회사 총액공사","gis 보통점검","2025-06-11 09:00","2025-06-11 14:00","2025-06-11 09:00","2025-06-11 14:00","연속"]
[240,"경기","성남","신용인S/S SEC CB 61620","2025년 성남전력 변전협력회사 총액공사","gis 보통점검","2025-06-13 09:00","2025-06-13 18:00","2025-06-13 09:00","2025-06-13 18:00","연속"]
[241,"경기","성남","모현용인#1 T/L","용인 은화삼지구 지장송전선로 지중화공사(요청자시행)","○ 철탑 : 6기 설치 및 11기 철거 - 신설 : 임시No.40,41,42,43,44,44-1 (6기) - 철거 : No.40,41,42,43,44 / 임시No.40,41,42,43,44,44-1 ○ 전력선 : ACSR410mm^2*2B*2C*1조(OPGW 100mm^2*1조 전자제어부 별도 시행) ○ 기타 부대공사 : 이도조정추가시공 기설No","2025-06-11 08:00","2025-06-20 18:00","취소","취소","연속"]
[242,"경기","성남","모현용인#2 T/L","용인 은화삼지구 지장송전선로 지중화공사(요청자시행)","○ 철탑 : 6기 설치 및 11기 철거 - 신설 : 임시No.40,41,42,43,44,44-1 (6기) - 철거 : No.40,41,42,43,44 / 임시No.40,41,42,43,44,44-1 ○ 전력선 : ACSR410mm^2*2B*2C*1조(OPGW 100mm^2*1조 전자제어부 별도 시행) ○ 기타 부대공사 : 이도조정추가시공 기설No","2025-06-01 08:00","2025-06-10 18:00","취소","취소","연속"]
[243,"경기","직할","관양동안양#2 T/L","관양S/S 관양-동안양#2T/L GIS 보통점검","관양: 관양-동안양#2T/L GIS 보통점검","2025-06-16 09:00","2025-06-16 18:00","2025-06-16 09:00","2025-06-16 18:00","연속"]
[244,"경기","직할","남군포의왕#3 T/L"," 의왕S/S 디지털화공사","전력설비 감시·제어·계측 디지털화","2025-06-02 09:00","2025-06-02 18:00","2025-06-02 09:00","2025-06-02 18:00","연속"]
[245,"경기","평택","서운삼죽 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치(64기), 애자교체(3기), 아킹혼 설치(2기), 압축인류클램프 교체(1기)","2025-06-23 07:00","2025-06-27 18:00","2025-06-23 07:00","2025-06-27 18:00","매일"]
[246,"경기","평택","송탄안성 T/L","2024-2025년 평택전력지사 송전정비 협력회사공사"," 송탄-안성T/L No.54~55 이도조정 및 No.25~30 조류착지방지 장치 설치","2025-06-16 08:00","2025-06-18 18:00","2025-06-16 08:00","2025-06-18 18:00","연속"]
[247,"경기","평택","소사벌안성 T/L","2024-2025년 평택전력지사 송전정비 협력회사공사"," 소사벌-안성T/L No.54~55 이도조정 및 조류착지방지장치 설치","2025-06-09 08:00","2025-06-11 18:00","2025-06-09 08:00","2025-06-11 18:00","연속"]
[248,"경기","평택","오산향남#2 T/L"," 오산-향남#2T/L 추락방지장치 설치","24-25년 경기본부 직할 송전협력회사 공사","2025-06-25 07:00","2025-07-02 18:00","취소","취소","연속"]
[249,"경기","평택","오산향남#1 T/L"," 오산-향남#1T/L 추락방지장치 설치","24-25년 경기본부 직할 송전협력회사 공사","2025-06-17 07:00","2025-06-24 18:00","취소","취소","연속"]
[250,"경기","평택","원정평택TP#1 T/L","2025 평택전력 변전협력 총액공사(원정평택1)","원정S/S 원정-평택T/P #1T/L GIS 조작시험, PT&LA 보통점검","2025-06-25 09:00","2025-06-25 18:00","취소","취소","연속"]
[251,"경기","평택","원정평택TP#2 T/L","2025 평택전력 변전협력 총액공사(원정평택2)","원정S/S 원정-평택T/P #2T/L GIS 조작시험, PT&LA 보통점검","2025-06-26 09:00","2025-06-26 18:00","취소","취소","연속"]
[252,"경기","평택","오산평택#2 T/L","평택 고덕지구 지중화공사(LH요청)","○ 공사구간 : 오산평택T/L No.59~61CT, 74CT~S/T ○ 전력선 가선 - ASCC [430mm^2] 1,322[C-km], ASCC [520mm^2] 0.226[C-km] ○ 전력선 철거 : ACSR 330[mm^2] 214[C-km] ○ 스페이서 등 금구류 설치 ※ 기타사항 : LH요청에 의한 지중화 사업","2025-06-25 09:00","2025-07-02 18:00","2025-06-25 09:00","2025-07-02 18:00","연속"]
[253,"경기","평택","오산평택#1 T/L","평택 고덕지구 지중화공사(LH요청)","○ 공사구간 : 오산평택T/L No.59~61CT, 74CT~S/T ○ 전력선 가선 - ASCC [430mm^2] 1,322[C-km], ASCC [520mm^2] 0.226[C-km] ○ 전력선 철거 : ACSR 330[mm^2] 214[C-km] ○ 스페이서 등 금구류 설치 ※ 기타사항 : LH요청에 의한 지중화 사업","2025-06-17 09:00","2025-06-24 18:00","2025-06-17 09:00","2025-06-24 18:00","연속"]
[254,"경기","평택","남사동탄#1 T/L","중동탄S/S 건설공사","중동탄S/S 건설공사관련 남사-동탄#1T/L ㅠ분기 공사","2025-06-16 09:00","2025-08-20 18:00","2025-06-16 09:00","2025-08-14 18:00","연속"]
[255,"경기","성남","신성남S/S CB 6100","25년 성남전력 효성제 부품발청 교체공사 "," - 부품교체","2025-06-05 09:00","2025-06-05 14:00","2025-06-05 09:00","2025-06-05 14:00","연속"]
[256,"경기","성남","신성남S/S CB 6300","25년 성남전력 효성제 부품발청 교체공사 "," - 부품교체","2025-06-05 14:00","2025-06-05 18:00","2025-06-05 14:00","2025-06-05 18:00","연속"]
[257,"경기","성남","신성남정자#1 T/L","2025년 성남전력 변전협력회사 총액공사 ","GIS 조작시험 및 Limit 교체","2025-06-10 09:00","2025-06-10 18:00","취소","취소","연속"]
[258,"경기","성남","신수원북동탄#1 T/L","2025년 성남전력 변전협력회사 총액공사 ","GIS 조작시험","2025-06-12 09:00","2025-06-12 14:00","2025-06-12 09:00","2025-06-12 14:00","연속"]
[259,"경기","성남","신수원북동탄#2 T/L","2025년 성남전력 변전협력회사 총액공사 ","GIS 조작시험","2025-06-12 14:00","2025-06-12 18:00","2025-06-12 14:00","2025-06-12 18:00","연속"]
[260,"강원","강릉","신양양속초#2 T/L","신양양S/S 170kV GIS 증설 공사","170kV GIS 증설 관련 안전조치 휴전","2025-06-30 10:00","2025-07-11 18:00","2025-06-30 10:00","2025-07-11 18:00","매일"]
[261,"강원","강릉","주문진양양#1 T/L","2024~2025년 가공송전협력회사 총액공사","○ 4회선 병가철탑 휴전작업 작업자 안전을 위한 휴전  북강릉-주문진#2T/L 추락방지장치 설치 (No.11~55)","2025-06-23 08:00","2025-06-26 18:00","2025-06-23 08:00","2025-06-26 18:00","매일"]
[262,"강원","강릉","주문진양양#2 T/L","2024~2025년 가공송전협력회사 총액공사","○ 4회선 병가철탑 휴전작업 작업자 안전을 위한 휴전  북강릉-주문진#1T/L 추락방지장치 설치 (No.11~55)","2025-06-19 08:00","2025-06-20 18:00","2025-06-19 08:00","2025-06-20 18:00","매일"]
[263,"강원","강릉","북강릉주문진#1 T/L","2024~2025년 가공송전협력회사 총액공사","○ 추락방지장치 설치 (No.11~55)","2025-06-13 08:00","2025-06-20 18:00","2025-06-13 08:00","2025-06-20 18:00","매일"]
[264,"강원","강릉","북강릉주문진#2 T/L","2024~2025년 가공송전협력회사 총액공사","○ 추락방지장치 설치 (No.11~55)","2025-06-23 08:00","2025-07-02 18:00","2025-06-23 08:00","2025-07-02 18:00","매일"]
[265,"강원","강릉","주진평창#1 T/L","345kV 신양양분기 등 4개 T/L 추락방지장치 설치 공사","수직 및 수평 추락방지장치 설치 :  주진평창 No.1~57","2025-06-04 08:00","2025-06-19 18:00","2025-06-04 08:00","2025-06-19 18:00","매일"]
[266,"강원","강릉","주진평창#2 T/L","345kV 신양양분기 등 4개 T/L 추락방지장치 설치공사","수평 추락방지장치 설치 :  주진 평창 No.1~57","2025-06-20 08:00","2025-06-30 18:00","2025-06-20 08:00","2025-06-30 18:00","매일"]
[267,"강원","강릉","평창올림픽 T/L","2025년 강릉전력지사 변전협력회사 총액공사"," 송전선로 보호반 대체(양단)","2025-06-09 10:00","2025-06-13 18:00","2025-06-09 10:00","2025-06-13 18:00","연속"]
[268,"강원","강릉","횡계S/S #2 BUS","2025년 강릉전력지사 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(횡계-올림픽TL #2DS 점검)","2025-06-18 14:00","2025-06-19 18:00","2025-06-18 14:00","2025-06-19 18:00","연속"]
[269,"강원","강릉","강릉횡계#1 T/L","2025년 강릉전력지사 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(횡계-올림픽TL 시험가압)","2025-06-18 09:00","2025-06-19 18:00","2025-06-18 09:00","2025-06-19 18:00","매일"]
[270,"강원","강릉","횡계S/S #1 BUS","2025년 강릉전력지사 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(횡계-평창TL #1DS 점검)","2025-06-23 09:00","2025-06-25 14:00","2025-06-23 09:00","2025-06-25 14:00","연속"]
[271,"강원","강릉","횡계평창 T/L","2025년 강릉전력지사 변전협력회사 총액공사"," 송전선로 보호반 대체","2025-06-23 10:00","2025-06-27 18:00","2025-06-23 10:00","2025-06-27 18:00","연속"]
[272,"강원","강릉","강릉횡계#1 T/L","2025년 강릉전력지사 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(횡계-평창TL 시험가압)","2025-06-25 09:00","2025-06-26 18:00","2025-06-25 09:00","2025-06-26 18:00","매일"]
[273,"강원","강릉","횡계S/S #2 BUS","2025년 강릉전력지사 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(횡계-평창TL #2DS 점검)","2025-06-25 14:00","2025-06-26 18:00","2025-06-25 14:00","2025-06-26 18:00","연속"]
[274,"강원","강릉","횡계S/S #1 BUS","2025년 강릉전력지사 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(횡계-올림픽TL #1DS 점검)","2025-06-16 09:00","2025-06-18 14:00","2025-06-16 09:00","2025-06-18 14:00","연속"]
[275,"강원","강릉","횡계올림픽 T/L","2025년 강릉전력지사 170kV GIS 정밀점검 공사","170kV GIS 정밀점검","2025-06-16 09:00","2025-06-19 18:00","2025-06-16 09:00","2025-06-19 18:00","연속"]
[276,"강원","동해","울진삼척GP#2 T/L","2024~2025년 태백전력지사 송전 협력회사 공사"," 울진-삼척GP#2 T/L 수평추락방지장치 및 폴리머 점퍼지지애자 설치","2025-06-16 07:00","2025-06-24 18:00","2025-06-16 07:00","2025-06-24 18:00","매일"]
[277,"강원","원주","원주S/S #61 BUS","원주S/S STATCOM Bay  GIS 설치공사","○  GIS(170kV, 50kA 2,000A) 1CCT 설치","2025-06-09 09:00","2025-06-13 18:00","2025-06-09 09:00","2025-06-13 18:00","연속"]
[278,"강원","원주","남원주원주#2 T/L","원주S/S STATCOM Bay  GIS 설치공사","○  GIS(170kV, 50kA 2,000A) 1CCT 설치","2025-06-19 09:00","2025-06-20 18:00","2025-06-19 09:00","2025-06-20 18:00","연속"]
[279,"강원","원주","원주S/S #66 BUS","원주S/S STATCOM Bay  GIS 설치공사","○  GIS(170kV, 50kA 2,000A) 1CCT 설치","2025-06-16 09:00","2025-06-20 18:00","2025-06-16 09:00","2025-06-20 18:00","연속"]
[280,"강원","원주","남원주원주#2 T/L","원주S/S STATCOM Bay  GIS 설치공사","○  GIS(170kV, 50kA 2,000A) 1CCT 설치","2025-06-12 09:00","2025-06-13 18:00","2025-06-12 09:00","2025-06-13 18:00","연속"]
[281,"강원","원주","상남인제#1 T/L","24-25년 원주전력지사 변전협력회사 총액공사","차단기 동작시험 피뢰기 하자점검","2025-06-23 10:00","2025-06-23 18:00","2025-06-23 10:00","2025-06-23 18:00","연속"]
[282,"강원","원주","서원주문막#1 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","○ 철탑 추락방지장치 설치","2025-06-09 09:00","2025-06-13 18:00","2025-06-09 09:00","2025-06-13 18:00","매일"]
[283,"강원","원주","서원주문막#2 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","○ 철탑 추락방지장치 설치","2025-06-16 09:00","2025-06-20 18:00","2025-06-16 09:00","2025-06-20 18:00","매일"]
[284,"강원","원주","홍천소양강HP T/L"," 홍천 STATCOM 건설사업","STATCOM 1식","2025-06-23 09:00","2025-06-24 18:00","2025-06-23 09:00","2025-06-24 18:00","연속"]
[285,"강원","원주","홍천S/S #61 BUS"," 홍천 STATCOM 건설사업","STATCOM 1식","2025-06-23 09:00","2025-06-27 18:00","2025-06-23 09:00","2025-06-27 18:00","연속"]
[286,"강원","원주","횡성홍천#2 T/L"," 홍천 STATCOM 건설사업","STATCOM 1식","2025-06-26 09:00","2025-06-27 18:00","2025-06-26 09:00","2025-06-27 18:00","연속"]
[287,"강원","직할","춘천북춘천#1 T/L","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","춘천S/S  BUS-TIE CB GIS 정밀점검 후 무부하 가압용","2025-06-27 09:00","2025-06-27 18:00","2025-06-27 09:00","2025-06-27 18:00","연속"]
[288,"강원","직할","춘천S/S #1 BUS","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","춘천S/S  춘천-북춘천#1T/L, 남춘천-춘천T/L GIS 정밀점검 후 무부하 가압용","2025-06-02 09:00","2025-06-02 18:00","2025-06-02 09:00","2025-06-02 18:00","연속"]
[289,"강원","직할","춘천소양강HP T/L"," 춘천분기 지장철탑 지중화 공사","C/T철탑 4기, 지중(0.46km(4C), 관로, XLPE1200) 설치 및 기설철탑2기 철거","2025-06-05 09:00","2025-06-16 18:00","2025-06-18 09:00","2025-06-29 18:00","연속"]
[290,"강원","직할","춘천S/S #2 BUS","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","춘천S/S  #4M.Tr 1차 GIS 정밀점검 후 무부하 가압용","2025-06-25 09:00","2025-06-25 14:00","2025-06-25 09:00","2025-06-25 14:00","연속"]
[291,"강원","직할","춘천S/S #1 BUS","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","춘천S/S  #3M.Tr 1차 GIS 정밀점검 후 무부하 가압용","2025-06-20 09:00","2025-06-20 18:00","2025-06-20 09:00","2025-06-20 18:00","연속"]
[292,"강원","직할","춘천북춘천#1 T/L","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","춘천S/S  #3M.Tr 1차 GIS 정밀점검 후 무부하 가압용","2025-06-20 09:00","2025-06-20 18:00","2025-06-20 09:00","2025-06-20 18:00","연속"]
[293,"강원","직할","춘천북춘천#2 T/L","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","춘천S/S  #2M.Tr 1차 GIS 정밀점검 후 무부하 가압용","2025-06-18 09:00","2025-06-18 14:00","2025-06-18 09:00","2025-06-18 14:00","연속"]
[294,"강원","직할","춘천S/S #2 BUS","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","춘천S/S  #2M.Tr 1차 GIS 정밀점검 후 무부하 가압용","2025-06-18 09:00","2025-06-18 14:00","2025-06-18 09:00","2025-06-18 14:00","연속"]
[295,"강원","직할","춘천S/S #1 BUS","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","춘천S/S  춘천-북춘천#2T/L, 춘천-소양강HPT/L GIS 정밀점검 후 무부하 가압용","2025-06-11 09:00","2025-06-16 18:00","2025-06-11 09:00","2025-06-16 18:00","매일"]
[296,"강원","직할","춘천북춘천#2 T/L"," 춘천-북춘천T/L No.42 지장철탑 이설공사","철탑인클로징 설치 : 1기(No.42) / 철탑철거 : 2기(No.42, 43) / 전력선 교체 : ACSR330㎟×S, 2C-1.147km","2025-06-05 09:00","2025-06-16 18:00","2025-06-04 09:00","2025-06-17 18:00","연속"]
[297,"강원","직할","춘천S/S #1 BUS","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","춘천S/S  BUS-TIE CB GIS 정밀점검 후 무부하 가압용","2025-06-27 09:00","2025-06-27 18:00","2025-06-27 09:00","2025-06-27 18:00","연속"]
[298,"강원","직할","춘천북춘천#2 T/L","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","춘천S/S  #4M.Tr 1차 GIS 정밀점검 후 무부하 가압용","2025-06-25 09:00","2025-06-25 14:00","2025-06-25 09:00","2025-06-25 14:00","연속"]
[299,"강원","직할","춘천S/S CB 6100","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 춘천S/S  #6100 BUS-TIE GIS 정밀점검","2025-06-25 14:00","2025-06-27 18:00","2025-06-25 14:00","2025-06-27 18:00","연속"]
[300,"강원","태백","정선영월CC T/L","2024~2025년 충주전력지사 송전협력회사 공사","2024~2025년 충주전력지사 송전협력회사 공사 병가구간으로 인한 안전확보( 신제천-영월CC#1)","2025-06-02 07:00","2025-06-04 18:00","2025-06-02 07:00","2025-06-04 18:00","매일"]
[301,"강원","태백","신제천영월CC#2 T/L","2025년 태백전력지사  GIS 정밀점검공사","영월C/C  신제천영월CC#2 T/L GIS 정밀점검","2025-06-09 09:00","2025-06-11 18:00","2025-06-09 09:00","2025-06-11 18:00","연속"]
[302,"강원","태백","신제천영월CC#1 T/L","2025년 태백전력지사  GIS 정밀점검공사","영월C/C  신제천영월CC#1 T/L GIS 정밀점검","2025-06-04 09:00","2025-06-06 18:00","2025-06-04 09:00","2025-06-06 18:00","연속"]
[303,"강원","태백","태백삼척GP#1 T/L","2024~2025년 태백전력지사 송전 협력회사 공사"," 태백-삼척GP#1 T/L 수평추락방지장치 및 폴리머 점퍼지지애자 설치","2025-06-12 07:00","2025-06-24 18:00","2025-06-12 07:00","2025-06-24 18:00","매일"]
[304,"강원","태백","태백영월에코윈드 T/L","2025년 태백전력지사  GIS 정밀점검공사","태백S/S  태백영월에코윈드 T/L GIS 정밀점검","2025-06-16 09:00","2025-06-18 14:00","2025-06-16 09:00","2025-06-18 14:00","연속"]
[305,"강원","태백","태백고한 T/L","2025년 태백전력지사  GIS 정밀점검공사","태백S/S  태백-고한 T/L GIS 정밀점검","2025-06-18 14:00","2025-06-20 18:00","2025-06-18 14:00","2025-06-20 18:00","연속"]
[306,"강원","태백","이원태백 T/L","2025년 태백전력지사  GIS 정밀점검공사","태백S/S  이원-태백 T/L GIS 정밀점검","2025-06-23 09:00","2025-06-25 14:00","2025-06-23 09:00","2025-06-25 14:00","연속"]
[307,"강원","태백","태백삼척GP#1 T/L","2025년 태백전력지사  GIS 정밀점검공사","태백S/S  태백삼척GP#1 T/L GIS 정밀점검","2025-06-25 14:00","2025-06-27 18:00","2025-06-25 14:00","2025-06-27 18:00","연속"]
[308,"충북","직할","진천광혜원#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치(39기), 피뢰기 설치(49기), 아킹혼 설치(1기), 조류착지방지장치 설치(1기)","2025-06-16 07:00","2025-06-20 18:00","2025-06-16 07:00","2025-06-20 18:00","매일"]
[309,"충북","직할","진천광혜원#2 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치(39기), 애자교체(2기), 아킹혼 설치(1기)","2025-06-23 07:00","2025-06-27 18:00","2025-06-23 07:00","2025-06-27 18:00","매일"]
[310,"충북","직할","서운광혜원 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치(39기), 피뢰기 설치(39기), 애자교체(1기), 금구류 정비(1기)","2025-06-16 07:00","2025-06-20 18:00","2025-06-16 07:00","2025-06-20 18:00","매일"]
[311,"충북","직할","신진천S/S #67 BUS","25년 상반기 충북본부 직할 GIS 정밀점검 공사","신진천S/S  #8Sh.C GIS 정밀점검 후 무부하가압용","2025-06-18 15:00","2025-06-18 16:00","2025-06-18 15:00","2025-06-18 16:00","연속"]
[312,"충북","직할","신진천S/S #67 BUS","25년 상반기 충북본부 직할 GIS 정밀점검 공사","신진천S/S  #7Sh.C GIS 정밀점검 후 무부하가압용","2025-06-13 17:00","2025-06-13 18:00","2025-06-13 17:00","2025-06-13 18:00","연속"]
[313,"충북","직할","신진천S/S #67 BUS","25년 상반기 충북본부 직할 GIS 정밀점검 공사","신진천S/S  #3Sh.C GIS 정밀점검 후 무부하가압용","2025-06-11 14:00","2025-06-11 15:00","2025-06-11 14:00","2025-06-11 15:00","연속"]
[314,"충북","직할","신진천문백#2 T/L","25년 상반기 충북본부 직할 GIS 정밀점검 공사"," 신진천-문백#2 T/L GIS 정밀점검","2025-06-04 08:00","2025-06-06 18:00","2025-06-04 08:00","2025-06-06 18:00","연속"]
[315,"충북","청주","남청주S/S #66 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(6월)","2025-06-08 14:00","2025-06-13 18:00","취소","취소","연속"]
[316,"충북","청주","남청주오송#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(무부하가압용_6월)","2025-06-07 14:00","2025-06-08 14:00","취소","취소","연속"]
[317,"충북","청주","남청주S/S #67 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(6월)","2025-06-03 14:00","2025-06-08 14:00","취소","취소","연속"]
[318,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(무부하가압용_6월)","2025-06-02 07:00","2025-06-03 14:00","취소","취소","연속"]
[319,"충북","청주","남청주S/S SEC CB 67660","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(6월)","2025-06-02 07:00","2025-06-13 18:00","취소","취소","연속"]
[320,"충북","청주","남청주S/S #66 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(6월)","2025-06-02 07:00","2025-06-03 14:00","취소","취소","연속"]
[321,"충북","청주","남청주S/S SEC CB 67660","2025년 청주전력지사 170kV GIS 정밀점검공사","남청주S/S #1Sh.C GIS 정밀점검 후 무부하 가압","2025-06-27 09:00","2025-06-27 18:00","2025-06-27 09:00","2025-06-27 18:00","연속"]
[322,"충북","청주","남청주S/S #67 BUS","2025년 청주전력지사 170kV GIS 정밀점검공사","남청주S/S #1Sh.C GIS 정밀점검 후 무부하 가압","2025-06-27 09:00","2025-06-27 18:00","2025-06-27 09:00","2025-06-27 18:00","연속"]
[323,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(무부하가압용_6월)","2025-06-12 14:00","2025-06-13 18:00","취소","취소","연속"]
[324,"충북","청주","남청주S/S SEC CB 62610","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(6월)","2025-06-16 07:00","2025-06-27 18:00","취소","취소","연속"]
[325,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(무부하가압용_6월)","2025-06-16 14:00","2025-06-17 18:00","취소","취소","연속"]
[326,"충북","청주","남청주오송#1 T/L","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(안전이격확보/무부하가압용_6월)","2025-06-17 14:00","2025-06-22 14:00","취소","취소","연속"]
[327,"충북","청주","남청주S/S #62 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(6월)","2025-06-17 14:00","2025-06-22 14:00","취소","취소","연속"]
[328,"충북","청주","남청주S/S #61 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(6월)","2025-06-22 14:00","2025-06-27 18:00","취소","취소","연속"]
[329,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(무부하가압용_6월)","2025-06-26 14:00","2025-06-27 18:00","취소","취소","연속"]
[330,"충북","청주","남청주S/S #61 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(6월)","2025-06-16 07:00","2025-06-17 14:00","취소","취소","연속"]
[331,"충북","청주","옥천보은 T/L","2024~2025년 송전정비 협력회사 총액공사"," 보은분기T/L 추락방지장치 설치(수평설치) 1. 내용 :  옥천-보은T/L 수평 추락방지장치 설치 2. 구간 :  옥천-보은T/L 1~29호","2025-06-23 08:00","2025-07-03 18:00","2025-06-23 08:00","2025-07-03 18:00","매일"]
[332,"충북","청주","화동보은 T/L","2024~2025년 송전정비 협력회사 총액공사"," 보은분기T/L 추락방지장치 설치(수평설치) 1. 내용 :  화동-보은T/L 수평 추락방지장치 설치 2. 구간 :  화동-보은T/L 25~29호","2025-06-19 08:00","2025-06-20 18:00","2025-06-19 08:00","2025-06-20 18:00","매일"]
[333,"충북","청주","북청주봉명#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-06-26 10:00","2025-06-26 18:00","2025-06-26 10:00","2025-06-26 18:00","연속"]
[334,"충북","청주","북청주봉명#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-06-27 10:00","2025-06-27 18:00","2025-06-27 10:00","2025-06-27 18:00","연속"]
[335,"충북","청주","사직S/S CB 6100","25년 청주전력 170kV 정밀점검공사","170kV GIS 정밀점검","2025-06-18 09:00","2025-06-19 18:00","2025-06-18 09:00","2025-06-19 18:00","연속"]
[336,"충북","청주","서청주사직#2 T/L","25년 청주전력 170kV 정밀점검공사","170kV GIS 정밀점검","2025-06-16 09:00","2025-06-17 18:00","2025-06-16 09:00","2025-06-17 18:00","연속"]
[337,"충북","청주","서청주사직#1 T/L"," 서청주-사직T/L 대한전선製 열경화공법 EBG 보강공사","EBG 가스채취 밸브 설치 및 스프링 유니트 점검을 통한 고장예방","2025-06-25 09:00","2025-06-27 18:00","2025-06-25 09:00","2025-06-27 18:00","연속"]
[338,"충북","청주","서청주사직#1 T/L","25년 청주전력 170kV 정밀점검공사","170kV GIS 정밀점검 후 무부하가압","2025-06-19 09:00","2025-06-19 18:00","2025-06-19 09:00","2025-06-19 18:00","연속"]
[339,"충북","청주","사직S/S #2 BUS","25년 청주전력 170kV 정밀점검공사","170kV GIS 정밀점검 후 무부하가압","2025-06-19 09:00","2025-06-19 18:00","2025-06-19 09:00","2025-06-19 18:00","연속"]
[340,"충북","청주","사직북청주#2 T/L","25년 청주전력 170kV 정밀점검공사","170kV GIS 정밀점검","2025-06-11 09:00","2025-06-12 18:00","2025-06-11 09:00","2025-06-12 18:00","연속"]
[341,"충북","청주","신옥천추부#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-06-12 10:00","2025-06-12 18:00","2025-06-12 10:00","2025-06-12 18:00","연속"]
[342,"충북","청주","신옥천추부#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-06-11 10:00","2025-06-11 18:00","2025-06-11 10:00","2025-06-11 18:00","연속"]
[343,"충북","청주","신옥천S/S SEC CB 61620","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-06-18 10:00","2025-06-18 18:00","2025-06-18 10:00","2025-06-18 18:00","연속"]
[344,"충북","청주","신옥천S/S SEC CB 66670","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-06-19 10:00","2025-06-19 18:00","2025-06-19 10:00","2025-06-19 18:00","연속"]
[345,"충북","청주","화동영동 T/L","2024~2025년 송전정비 협력회사 총액공사"," 화동-영동T/L 추락방지장치 설치(수평설치) 1. 내용 : 화동-영동T/L 수평 추락방지장치 설치 2. 구간 :  화동-영동T/L 60~110호  영동분기T/L 1~61호","2025-06-09 08:00","2025-06-18 18:00","2025-06-09 08:00","2025-06-18 18:00","매일"]
[346,"충북","충주","감곡S/S CB 6100","감곡S/S 23kV 장기사용 GIS 대체공사","RTU 철거로 인한 제어 케이블  LID 이설 및 시험","2025-06-12 09:00","2025-06-13 18:00","취소","취소","연속"]
[347,"충북","충주","감곡가남#2 T/L","감곡S/S 23kV 장기사용 GIS 대체공사","RTU 철거로 인한 제어 케이블  LID 이설 및 시험","2025-06-14 09:00","2025-06-15 18:00","2025-06-14 09:00","2025-06-15 18:00","연속"]
[348,"충북","충주","감곡가남#1 T/L","감곡S/S 23kV 장기사용 GIS 대체공사","RTU 철거로 인한 제어 케이블  LID 이설 및 시험","2025-06-06 09:00","2025-06-07 18:00","2025-06-06 09:00","2025-06-07 18:00","연속"]
[349,"충북","충주","금왕남음성#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치(23기)","2025-06-09 07:00","2025-06-12 18:00","2025-06-09 07:00","2025-06-12 18:00","매일"]
[350,"충북","충주","신제천영월CC#2 T/L","2024~2025년 충주전력지사 송전협력회사 공사","수평추락방지장치 설치( 신제천-영월CC#2 T/L No.15,20,26,27,35~75) 및 폴리머지지애자 설치(26,35,59,62,74) 시행","2025-06-09 07:00","2025-06-19 18:00","2025-06-09 07:00","2025-06-19 18:00","매일"]
[351,"충북","충주","신충주S/S #68 BUS","신충주S/S  충주에코파크T/L 증설공사","신충주S/S  충주에코파크T/L 증설공사","2025-06-23 09:00","2025-06-27 18:00","2025-06-23 09:00","2025-06-27 18:00","연속"]
[352,"충북","충주","신충주S/S #63 BUS","신충주S/S  충주에코파크T/L 증설공사","신충주S/S  충주에코파크T/L 증설공사","2025-06-30 09:00","2025-07-03 18:00","2025-06-30 09:00","2025-07-03 18:00","연속"]
[353,"충북","충주","왕암북충주 T/L","2024~2025년 충주전력지사 송전협력회사 공사","압축인류클램프 교체 왕암-북충주T/L(No.18,20,27,35,36,40,42,47,49,53)","2025-06-18 07:00","2025-06-20 18:00","2025-06-18 07:00","2025-06-20 18:00","매일"]
[354,"충북","충주","음성금왕#2 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치(29기), 애자교체(1기), 아킹혼 철거(1기)","2025-06-09 07:00","2025-06-12 18:00","2025-06-09 07:00","2025-06-12 18:00","매일"]
[355,"대전세종충남","대전","금산무주#1 T/L","[송전][즉시가압O]345kV 신옥천-청양등8개T/L 추락방지설치공사","[송전][즉시가압O]345kV 신옥천-청양 등 8개T/L 추락방지 설치공사","2025-06-18 15:30","2025-06-27 10:00","취소","취소","매일"]
[356,"대전세종충남","대전","부여논산#1 T/L","[취소시][가압x]논산S/S 부여-논산#1T/L GIS 정밀점검","[취소시][가압x]논산S/S 부여-논산#1T/L GIS 정밀점검","2025-06-09 09:00","2025-06-10 18:00","2025-06-09 09:00","2025-06-10 18:00","연속"]
[357,"대전세종충남","대전","부여논산#2 T/L","[취소시][가압X]논산S/S 부여-논산#2T/L GIS 정밀점검","[취소시][가압X]논산S/S 부여-논산#2T/L GIS 정밀점검","2025-06-11 09:00","2025-06-12 18:00","2025-06-11 09:00","2025-06-12 18:00","연속"]
[358,"대전세종충남","대전","남대전신흥#1 T/L","[송전]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치 [대전변전] GIS 하자점검(최석기 대리), 차단기 부동작시험(조대권 대리) [대전전자제어] PITR 정기시험(박세기 과장)","2025-06-02 08:00","2025-06-03 18:00","취소","취소","연속"]
[359,"대전세종충남","대전","남대전신흥#2 T/L","[송전]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치 [대전변전] GIS 하자점검(황준하 대리), 차단기 부동작시험(홍성원 대리) [대전전자제어] PITR 정기시험(박세기 과장)","2025-06-04 08:00","2025-06-05 18:00","취소","취소","연속"]
[360,"대전세종충남","대전","남대전신흥#3 T/L","[송전]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치 [대전변전] 차단기 부동작시험(홍성원 대리) [대전전자제어] PITR 정기시험(박세기 과장)","2025-06-09 08:00","2025-06-10 18:00","취소","취소","연속"]
[361,"대전세종충남","대전","신흥동대전#1 T/L","[송전]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치","2025-06-11 08:00","2025-06-12 18:00","취소","취소","연속"]
[362,"대전세종충남","대전","신흥동대전#3 T/L","[송전]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치","2025-06-16 08:00","2025-06-17 18:00","취소","취소","연속"]
[363,"대전세종충남","대전","신흥동대전#2 T/L","[송전]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치","2025-06-13 08:00","2025-06-14 18:00","취소","취소","연속"]
[364,"대전세종충남","서산","신당진당진#2 T/L"," 당진S/S 장기사용 #4M.Tr 교체공사"," 당진S/S 장기사용 #4M.Tr 교체공사 관련 무부하가압","2025-06-26 14:00","2025-06-27 14:00","취소","취소","연속"]
[365,"대전세종충남","서산","당진송악#1 T/L","25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 당진S/S  당진송악#1T/L GIS 보통점검","2025-06-16 09:30","2025-06-16 18:00","2025-06-16 09:30","2025-06-16 18:00","연속"]
[366,"대전세종충남","서산","서산대산#3 T/L","대산S/S  장기사용 GIS 교체공사","대산S/S  장기사용 GIS 교체공사 - 무부하가압","2025-06-01 15:00","2025-06-02 15:00","2025-06-01 15:00","2025-06-02 15:00","연속"]
[367,"대전세종충남","서산","서산대산#3 T/L","대산S/S  장기사용 GIS 교체공사","대산S/S  장기사용 GIS 교체공사 - 무부하가압","2025-06-09 15:00","2025-06-10 15:00","2025-06-09 15:00","2025-06-10 15:00","연속"]
[368,"대전세종충남","서산","서산대산 T/L"," 신성연분기T/L 건설공사"," 신성연-태안T/L(현  대산T/L) No.22(C/T) 조립 위한 가선로 구성","2025-06-03 07:00","2025-06-05 18:00","2025-06-04 07:00","2025-06-06 18:00","연속"]
[369,"대전세종충남","서산","서산홍성 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (서산T/L No.1~135) , 즉시가압(20분 이내) 가능,주말 및 휴일작업 없음","2025-06-02 08:00","2025-06-13 18:00","2025-06-02 08:00","2025-06-13 18:00","매일"]
[370,"대전세종충남","서산","서산대산 T/L"," 신성연분기T/L 건설공사"," 신성연-태안T/L(현  대산T/L) No.22(C/T) 조립 이후 본선로 복구","2025-06-17 07:00","2025-06-19 18:00","2025-06-17 07:00","2025-06-19 18:00","연속"]
[371,"대전세종충남","서산","서산대산 T/L","'25년도 가공송전 순시점검 위탁공사"," 서산-대산T/L 정밀점검 No.15~20, 27~83 [비상시 20분 이내 즉시가압가능]","2025-06-03 08:00","2025-06-05 18:00","취소","취소","매일"]
[372,"대전세종충남","서산","서산성연 T/L"," 신성연분기T/L 건설공사"," 신성연-태안T/L(현  대산T/L) No.22(C/T) 조립 위한 가선로 구성","2025-06-06 07:00","2025-06-08 18:00","2025-06-07 07:00","2025-06-09 18:00","연속"]
[373,"대전세종충남","서산","서산성연 T/L","'25년도 가공송전 순시점검 위탁공사"," 서산-성연T/L 정밀점검 No.15~20  성연분기T/L 정밀점검 No.2~6 [비상시 20분 이내 즉시가압가능]","2025-06-06 08:00","2025-06-08 18:00","취소","취소","매일"]
[374,"대전세종충남","서산","서산성연 T/L"," 신성연분기T/L 건설공사"," 신성연-태안T/L(현  대산T/L) No.22(C/T) 조립 이후 본선로 복구","2025-06-14 07:00","2025-06-16 18:00","2025-06-14 07:00","2025-06-16 18:00","연속"]
[375,"대전세종충남","서산","서산대산 T/L","'25년도 가공송전 순시점검 위탁공사"," 서산-대산T/L 정밀점검 No.15~20, 27~83 [비상시 20분 이내 즉시가압가능]","2025-06-17 08:00","2025-06-19 18:00","취소","취소","매일"]
[376,"대전세종충남","서산","대산석문#1 T/L","석문S/S  가스공사T/L GIS 증설공사","석문S/S  가스공사T/L #2BUS용 GIS 무부하 가압","2025-06-13 15:00","2025-06-14 15:00","2025-06-13 15:00","2025-06-14 15:00","연속"]
[377,"대전세종충남","서산","대산석문#1 T/L","석문S/S  가스공사T/L GIS 증설공사","석문S/S  가스공사T/L #1BUS측 GIS 무부하가압","2025-06-10 15:00","2025-06-11 15:00","2025-06-10 15:00","2025-06-11 15:00","연속"]
[378,"대전세종충남","서산","합덕송악#1 T/L","25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 송악S/S  합덕송악#1T/L GIS 보통점검","2025-06-30 09:30","2025-06-30 18:00","2025-06-30 09:30","2025-06-30 18:00","연속"]
[379,"대전세종충남","서산","신당진당진#1 T/L","25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 신당진S/S  신당진당진#1T/L GIS 보통점검","2025-06-23 09:30","2025-06-23 18:00","2025-06-23 09:30","2025-06-23 18:00","연속"]
[380,"대전세종충남","서산","태안T/P CB 6100","25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 태안T/P  6100 GIS 보통점검","2025-06-10 09:30","2025-06-10 18:00","2025-06-10 09:30","2025-06-10 18:00","연속"]
[381,"대전세종충남","세종","신풍공주#1 T/L","[즉시가압O]  신풍-공주T/L 철구 추락방지장치 설치","철구 승주 작업자의 안전을 위해 신풍-공주T/L 철구추락방지 장치를 설치","2025-06-03 07:00","2025-06-03 18:00","2025-06-04 07:00","2025-06-04 18:00","연속"]
[382,"대전세종충남","세종","신풍공주#2 T/L","[즉시가압O]  신풍-공주T/L 철구 추락방지장치 설치","철구 승주 작업자의 안전을 위해 신풍-공주T/L 철구추락방지 장치를 설치","2025-06-04 07:00","2025-06-04 18:00","2025-06-05 07:00","2025-06-05 18:00","연속"]
[383,"대전세종충남","세종","덕진유성#1 T/L","(5월 신청취소시, 4회선동시) 덕진-유성#1T/L 정밀점검"," 덕진-유성#1T/L 정밀점검(덕진-공주#1 동시휴전)","2025-06-09 09:00","2025-06-13 18:00","2025-06-09 09:00","2025-06-13 18:00","매일"]
[384,"대전세종충남","세종","덕진공주#1 T/L","(5월 신청취소시, 4회선동시) 덕진-공주#1T/L 정밀점검"," 덕진-공주#1T/L 정밀점검(덕진유성#1 동시휴전, 주말작업 미시행)","2025-06-09 09:00","2025-06-16 18:00","취소","취소","매일"]
[385,"대전세종충남","세종","덕진유성#2 T/L","(5월 신청취소시, 4회선동시) 덕진-유성#2T/L 정밀점검"," 덕진-유성#2T/L 정밀점검(덕진-공주#2 동시휴전, 주말작업 미시행)","2025-06-17 09:00","2025-06-24 18:00","2025-06-17 09:00","2025-06-24 18:00","매일"]
[386,"대전세종충남","세종","덕진공주#2 T/L","(5월 신청취소시, 4회선동시) 덕진-공주#2T/L 정밀점검"," 덕진-공주#2T/L 정밀점검(덕진유성#2 동시휴전,주말작업 미시행)","2025-06-17 09:00","2025-06-24 18:00","취소","취소","매일"]
[387,"대전세종충남","세종","월산서세종 T/L","월산S/S  장기사용 GIS 교체공사 (무부하가압)","월산S/S  장기사용 GIS 교체공사 (무부하가압)","2025-06-12 14:00","2025-06-13 14:00","2025-06-12 14:00","2025-06-13 14:00","연속"]
[388,"대전세종충남","세종","세종월산#2 T/L","[즉시가압X]  세종-월산T/L 불량애자 교체공사","균열이 지속발생되는 동일 Lot 번호의 불량애자 교체를 시행하여 철탑과 전선간 절연 안정성 호가보를 위함","2025-06-11 07:00","2025-06-12 18:00","2025-06-11 07:00","2025-06-12 18:00","매일"]
[389,"대전세종충남","세종","세종월산#1 T/L","[즉시가압X]  세종-월산T/L 불량애자 교체공사","균열이 지속발생되는 동일 Lot 번호의 불량애자 교체를 시행하여 철탑과 전선간 절연 안정성 호가보를 위함","2025-06-09 07:00","2025-06-10 18:00","2025-06-09 07:00","2025-06-10 18:00","매일"]
[390,"대전세종충남","세종","월산서세종 T/L","월산S/S  장기사용 GIS 교체공사 (무부하가압)","월산S/S  장기사용 GIS 교체공사 (무부하가압)","2025-06-19 14:00","2025-06-20 14:00","2025-06-19 14:00","2025-06-20 14:00","연속"]
[391,"대전세종충남","세종","조치원전의#1 T/L","[송전] 조치원-전의T/L 안전이격 및 전력선 교체공사","○  조치원-전의T/L 안전이격 및 전력선 교체공사 - 지지물 교체 : No.25,33,34 - 용량증대 전선교체 : 조치원S/S~전의S/S","2025-06-15 07:00","2025-07-02 18:00","2025-06-15 07:00","2025-07-02 18:00","연속"]
[392,"대전세종충남","세종","조치원월산 T/L","[즉시가압O]  조치원-월산T/L 피뢰기 설치공사","수용가 인근 철탑에 피뢰기 설치를 하여 낙뢰고장으로 인한 고장방지를 위함","2025-06-04 07:00","2025-06-04 18:00","2025-06-04 07:00","2025-06-04 18:00","연속"]
[393,"대전세종충남","직할","대덕둔지 T/L","2024~2025년 직할 변전협력회사 공사"," GIS 보통점검","2025-06-12 09:00","2025-06-12 18:00","2025-06-12 09:00","2025-06-12 18:00","연속"]
[394,"대전세종충남","직할","대화둔산#2 T/L","[즉시가압O]24-25년 직할 변전협력회사 공사","ㅁ대화-둔산#2T/L GIS 보통점검","2025-06-10 09:00","2025-06-10 18:00","2025-06-10 09:00","2025-06-10 18:00","연속"]
[395,"대전세종충남","직할","대화둔산#1 T/L","[즉시가압O]24-25년 직할 변전협력회사 공사","ㅁ대화-둔산#1T/L GIS 보통점검 ㅁ전자변 교체","2025-06-09 09:00","2025-06-09 18:00","2025-06-09 09:00","2025-06-09 18:00","연속"]
[396,"대전세종충남","직할","송강신일#2 T/L","(5월 취소시)송강,신일S/S 송강-신일#2T/L 보호반 대체공사","송강,신일S/S 송강-신일#2T/L 송전선로 보호반 대체","2025-06-06 08:00","2025-06-08 18:00","취소","취소","연속"]
[397,"대전세종충남","천안","둔포석곡#1 T/L","(즉시가압가능)둔포S/S 둔포-석곡#1T/L GIS 보통점검(매일)","(즉시가압가능)둔포S/S 둔포-석곡#1T/L GIS 보통점검(매일)","2025-06-09 09:00","2025-06-10 18:00","2025-06-09 09:00","2025-06-10 18:00","연속"]
[398,"대전세종충남","천안","둔포석곡#2 T/L","(즉시가압가능)둔포S/S 둔포-석곡#2T/L GIS 보통점검(매일)","(즉시가압가능)둔포S/S 둔포-석곡#2T/L GIS 보통점검(매일)","2025-06-11 09:00","2025-06-12 18:00","2025-06-11 09:00","2025-06-12 18:00","연속"]
[399,"대전세종충남","천안","불당서천안#1 T/L","(즉시가압가능)불당S/S  불당-서천안#1T/L GIS 보통점검","(즉시가압가능)불당S/S  불당-서천안#1T/L GIS 보통점검","2025-06-27 09:00","2025-06-27 18:00","2025-06-27 09:00","2025-06-27 18:00","연속"]
[400,"대전세종충남","천안","아산합덕#1 T/L"," 아산-합덕T/L 추락방지장치 설치공사(4회선)","[즉시가압가능] 아산-합덕T/L No. 1 ~ 53 추락방지장치 설치 [병가철탑](상단)신서산-아산#1No.74~113,(하단)아산-합덕#1No.13~52","2025-06-02 07:00","2025-06-05 18:00","2025-06-02 07:00","2025-06-05 18:00","매일"]
[401,"대전세종충남","천안","아산S/S SEC CB 65660","아산S/S  65-66 GIS 불량 PD센서 교체","(즉시가압불가)(5월취소시)아산S/S  65-66 GIS 불량 PD센서 교체","2025-06-02 09:00","2025-06-03 18:00","취소","취소","연속"]
[402,"대전세종충남","천안","아산S/S #66 BUS","아산S/S  65-66 GIS 불량 PD센서 교체","(즉시가압불가)(5월취소시)아산S/S  65-66 GIS 불량 PD센서 교체","2025-06-02 09:00","2025-06-03 18:00","취소","취소","연속"]
[403,"대전세종충남","천안","아산합덕#1 T/L","아산S/S  아산합덕#1T/L GIS 불량 PD센서 교체","(즉시가압불가)(5월취소시)아산S/S  아산합덕#1T/L GIS 불량 PD센서 교체","2025-06-04 09:00","2025-06-05 18:00","취소","취소","연속"]
[404,"대전세종충남","천안","아산S/S #65 BUS","아산S/S  아산합덕#1T/L GIS 불량 PD센서 교체","(즉시가압불가)(5월취소시)아산S/S  아산합덕#1T/L GIS 불량 PD센서 교체","2025-06-04 09:00","2025-06-05 18:00","취소","취소","연속"]
[405,"대전세종충남","천안","아산예산#1 T/L"," 아산-예산T/L 추락방지장치 설치공사","[즉시가압가능] 아산-예산T/L No. 1 ~ 48 추락방지장치 설치","2025-06-16 07:00","2025-06-20 18:00","2025-06-16 07:00","2025-06-20 18:00","매일"]
[406,"대전세종충남","천안","아산합덕#2 T/L"," 아산-합덕T/L 추락방지장치 설치공사(4회선)","[즉시가압가능] 아산-합덕T/L No. 1 ~ 53 추락방지장치 설치 [병가철탑](상단)신서산-아산#2No.74~113,(하단)아산-합덕#2No.13~52","2025-06-09 07:00","2025-06-12 18:00","2025-06-09 07:00","2025-06-12 18:00","매일"]
[407,"대전세종충남","천안","아산예산#2 T/L","(5월취소시) 아산-예산#2T/L 노후 보호배전반 대체","(5월취소시)(즉시가압불가)(장기미교체 대상) 아산-예산#2T/L 노후 보호배전반 대체","2025-06-23 09:00","2025-06-26 18:00","취소","취소","연속"]
[408,"대전세종충남","천안","아산예산#1 T/L"," 아산-예산#1T/L 노후 보호배전반 대체","(즉시가압불가)(장기미교체 대상) 아산-예산#1T/L 노후 보호배전반 대체","2025-06-16 09:00","2025-06-20 18:00","취소","취소","연속"]
[409,"대전세종충남","천안","아산온양#2 T/L","(즉시가압가능)온양S/S  아산-온양#2T/L GIS 하자점검","(즉시가압가능)온양S/S  아산-온양#2T/L GIS 하자점검","2025-06-07 09:00","2025-06-07 18:00","2025-06-07 09:00","2025-06-07 18:00","연속"]
[410,"대전세종충남","천안","아산온양#1 T/L","(즉시가압가능)온양S/S  아산-온양#1T/L GIS 하자점검","(즉시가압가능)온양S/S  아산-온양#1T/L GIS 하자점검","2025-06-06 09:00","2025-06-06 18:00","2025-06-06 09:00","2025-06-06 18:00","연속"]
[411,"대전세종충남","천안","천안전의#1 T/L","(즉시가압가능)천안S/S  천안-전의#1T/L GIS 보통점검","(즉시가압가능)천안S/S  천안-전의#1T/L GIS 보통점검","2025-06-04 09:00","2025-06-04 18:00","취소","취소","연속"]
[412,"대전세종충남","천안","천안전의#2 T/L","(즉시가압가능)천안S/S  천안-전의#2T/L GIS 보통점검","(즉시가압가능)천안S/S  천안-전의#2T/L GIS 보통점검","2025-06-05 09:00","2025-06-05 18:00","취소","취소","연속"]
[413,"대전세종충남","천안","천안전의#2 T/L"," 소정분기T/L 건설사업","기) 천안-전의T/L No. 29 ~ 신) 소정S/S (가선공사) 신) 소정S/S ~ 기) 천안-전의T/L No.31 (가선공사) 기) 천안-전의T/L No. 32 철탑보강","2025-06-01 07:00","2025-06-13 18:00","2025-06-01 07:00","2025-06-13 18:00","연속"]
[414,"대전세종충남","천안","천안전의#1 T/L"," 소정분기T/L 건설사업","기) 천안-전의T/L No. 29 ~ 신) 소정S/S (가선공사) 신) 소정S/S ~ 기) 천안-전의T/L No.31 (가선공사) 기) 천안-전의T/L No. 32 철탑보강","2025-06-01 07:00","2025-06-13 18:00","2025-06-01 07:00","2025-06-13 18:00","연속"]
[415,"대전세종충남","천안","풍세장재#1 T/L","(즉시가압가능)풍세S/S 풍세-장재#1T/L GIS 보통점검","(즉시가압가능)풍세S/S 풍세-장재#1T/L GIS 보통점검","2025-06-13 09:00","2025-06-13 18:00","2025-06-13 09:00","2025-06-13 18:00","연속"]
[416,"대전세종충남","천안","풍세장재#2 T/L","(즉시가압가능)풍세S/S 풍세-장재#2T/L GIS 보통점검","(즉시가압가능)풍세S/S 풍세-장재#2T/L GIS 보통점검","2025-06-16 09:00","2025-06-16 18:00","2025-06-16 09:00","2025-06-16 18:00","연속"]
[417,"대전세종충남","청양","관창보령CC T/L","[송전]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치 [송전] PD 집합반 설치공사","2025-06-23 07:30","2025-06-24 18:00","2025-06-23 07:30","2025-06-24 18:00","연속"]
[418,"대전세종충남","청양","관창보령TP T/L","[송전]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치 [송전] PD 집합반 설치공사","2025-06-19 07:30","2025-06-20 18:00","2025-06-19 07:30","2025-06-20 18:00","연속"]
[419,"대전세종충남","청양","관창보령CC T/L","[송전][즉시가압O]  관창-보령복합T/L 점퍼지지애자 설치"," 관창-보령복합T/L 폴리머 점퍼지지애자 설치","2025-06-23 07:30","2025-06-24 18:00","취소","취소","매일"]
[420,"대전세종충남","청양","관창보령TP T/L","[송전][즉시가압O]  관창-보령화력T/L 점퍼지지애자 설치"," 관창-보령화력T/L 폴리머 점퍼지지애자 설치","2025-06-19 07:30","2025-06-20 18:00","취소","취소","매일"]
[421,"대전세종충남","청양","은하홍성#2 T/L","정밀점검(은하홍성#2)","철탑(48기), 전력선(54경간), 애자금구류 승탑점검","2025-06-18 07:00","2025-06-20 18:00","2025-06-18 07:00","2025-06-20 18:00","매일"]
[422,"대전세종충남","청양","은하홍성#1 T/L","정밀점검(은하홍성#1)","철탑(48기), 전력선(54경간), 애자금구류 승탐점검","2025-06-25 09:00","2025-06-27 18:00","2025-06-25 09:00","2025-06-27 18:00","매일"]
[423,"대전세종충남","청양","청양은하#2 T/L","정밀점검(청양은하#2)","철탑(62기), 전력선(90경간), 애자금구류 승탑점검","2025-06-23 07:00","2025-06-26 18:00","2025-06-23 07:00","2025-06-26 18:00","매일"]
[424,"대전세종충남","청양","청양은하#1 T/L","정밀점검(청양은하#1)","철탑(62기), 전력선(90경간), 애자금구류 승탑점검","2025-06-16 07:00","2025-06-19 18:00","2025-06-16 07:00","2025-06-19 18:00","매일"]
[425,"대전세종충남","청양","동군산장항#1 T/L","[변전총액]청양P/O 변전협력회사 총액공사"," 동군산-장항#1T/L 차단기 조작시험 - 87보호계전기 통신 오류 점검","2025-06-19 09:00","2025-06-19 18:00","취소","취소","연속"]
[426,"대전세종충남","청양","청양S/S #61 BUS","[변전공사] 청양S/S  #1,2Sh.C 및 보호반 교체공사","[변전공사] 청양S/S  #1,2Sh.C 및 보호반 교체공사(무부하가압)","2025-06-24 18:00","2025-06-26 18:00","2025-06-24 18:00","2025-06-26 18:00","연속"]
[427,"대전세종충남","청양","청양S/S CB 6200","[변전공사] 청양S/S  #1,2Sh.C 및 보호반 교체공사","[변전공사] 청양S/S  #1,2Sh.C 및 보호반 교체공사(무부하가압)","2025-06-24 18:00","2025-06-26 18:00","2025-06-24 18:00","2025-06-26 18:00","연속"]
[428,"전북","군산","군산서군산#2 T/L","군산P/O 170kV GIS 정밀점검공사(중복)","군산P/O 170kV GIS 정밀점검공사","2025-06-18 09:00","2025-06-20 18:00","취소","취소","연속"]
[429,"전북","군산","군산이리#2 T/L"," 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2025-06-11 07:00","2025-06-16 18:00","2025-06-11 07:00","2025-06-16 18:00","연속"]
[430,"전북","군산","군산영등#2 T/L"," 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2025-06-11 07:00","2025-06-16 18:00","2025-06-11 07:00","2025-06-16 18:00","연속"]
[431,"전북","군산","군산서군산#1 T/L","군산P/O 170kV GIS 정밀점검공사(중복)","군산P/O 170kV GIS 정밀점검공사","2025-06-09 09:00","2025-06-11 18:00","취소","취소","연속"]
[432,"전북","군산","군산영등#2 T/L","'25년 군산전력지사 가공송전협력회사공사"," 군산-영등T/L 소도체 이도조정공사","2025-06-18 09:00","2025-06-18 18:00","취소","취소","연속"]
[433,"전북","군산","군산영등#1 T/L","'25년 군산전력지사 가공송전협력회사공사"," 군산-영등T/L 소도체 이도조정공사","2025-06-17 09:00","2025-06-17 18:00","취소","취소","연속"]
[434,"전북","군산","동군산군산CC#1 T/L","24~25년 군산전력지사 변전협력회사 총액공사","-노후배전반 대체 공사","2025-06-04 09:00","2025-06-05 18:00","2025-06-04 09:00","2025-06-05 18:00","연속"]
[435,"전북","군산","동군산장항#1 T/L","효성제 170kV GIS 차단기 주접점 교체공사(중복)","동군산S/S 동군산-장항#1T/L 효성제 170kV GIS 차단기 주접점 교체공사","2025-06-23 09:00","2025-06-25 18:00","2025-06-23 09:00","2025-06-25 18:00","연속"]
[436,"전북","군산","동군산군산CC#3 T/L","군산P/O 이상 차단기 점검공사","군산P/O 이상 차단기 점검공사","2025-06-30 09:00","2025-06-30 18:00","2025-06-30 09:00","2025-06-30 18:00","연속"]
[437,"전북","군산","동군산군산CC#2 T/L","24~25년 군산전력지사 변전협력회사 총액공사","-노후배전반 대체 공사","2025-06-26 09:00","2025-06-27 18:00","2025-06-26 09:00","2025-06-27 18:00","연속"]
[438,"전북","군산","군공소룡#1 T/L","군산P/O 170kV GIS 정밀점검공사","6100BUSTIE 무부하가압용","2025-06-24 16:00","2025-06-24 17:00","2025-06-24 16:00","2025-06-24 17:00","연속"]
[439,"전북","군산","서군산소룡#1 T/L","군산P/O 170kV GIS 정밀점검공사","군산P/O 170kV GIS 정밀점검공사","2025-06-16 09:00","2025-06-17 18:00","취소","취소","연속"]
[440,"전북","군산","서군산소룡#2 T/L","군산P/O 170kV GIS 정밀점검공사","군산P/O 170kV GIS 정밀점검공사","2025-06-12 09:00","2025-06-13 18:00","취소","취소","연속"]
[441,"전북","군산","영등낭산#2 T/L","'25년 군산전력지사 가공송전협력회사공사"," 군산-영등T/L 소도체 이도조정공사","2025-06-17 09:00","2025-06-17 18:00","취소","취소","연속"]
[442,"전북","군산","영등낭산#1 T/L","'25년 군산전력지사 가공송전협력회사공사"," 군산-영등T/L 소도체 이도조정공사","2025-06-18 09:00","2025-06-18 18:00","취소","취소","연속"]
[443,"전북","군산","영등팔봉#1 T/L","군산P/O  이상 차단기 보통점검공사","차단기 보통점검공사","2025-06-26 09:00","2025-06-26 13:00","취소","취소","연속"]
[444,"전북","군산","영등팔봉#2 T/L","군산P/O  이상 차단기 보통점검공사","차단기 보통점검공사","2025-06-26 13:00","2025-06-26 18:00","취소","취소","연속"]
[445,"전북","군산","이리백산#1 T/L","군산P/O 170kV GIS 정밀점검공사","군산P/O 170kV GIS 정밀점검공사","2025-06-09 09:00","2025-06-10 18:00","취소","취소","연속"]
[446,"전북","군산","군산이리#1 T/L","군산P/O 170kV GIS 정밀점검공사","군산P/O 170kV GIS 정밀점검공사","2025-06-19 09:00","2025-06-20 18:00","취소","취소","연속"]
[447,"전북","군산","이리백산#2 T/L","군산P/O 170kV GIS 정밀점검공사","군산P/O 170kV GIS 정밀점검공사","2025-06-11 09:00","2025-06-12 18:00","취소","취소","연속"]
[448,"전북","군산","팔봉왕궁#1 T/L","군산P/O 170kV GIS 정밀점검공사(중복)","군산P/O 170kV GIS 정밀점검공사","2025-06-02 09:00","2025-06-03 18:00","취소","취소","연속"]
[449,"전북","군산","팔봉왕궁#2 T/L","군산P/O 170kV GIS 정밀점검공사(중복)","군산P/O 170kV GIS 정밀점검공사","2025-06-12 09:00","2025-06-13 18:00","취소","취소","연속"]
[450,"전북","김제","소성고창#1 T/L"," 고창-영광T/L No.45~142 선종교체공사","○  고창-영광T/L 선종교체공사 - No.45~142 전력선 교체(ACSR 330㎟ -> ASCC 430㎟)","2025-06-26 07:00","2025-06-26 18:00","취소","취소","연속"]
[451,"전북","김제","소성고창#2 T/L"," 서홍농개폐소 건설공사(고창-홍농분기,고객시공)","○ 내용 :  고창-서홍농T/L, 서홍농-홍농#2T/L 앵글측정 및 서홍농개폐소 무부하가압","2025-06-23 14:00","2025-06-24 15:00","취소","취소","연속"]
[452,"전북","김제","고창홍농 T/L"," 고창-영광T/L No.45~142 선종교체공사","○  고창-영광T/L 선종교체공사 - No.45~142 전력선 교체(ACSR 330㎟ -> ASCC 430㎟)","2025-06-16 07:00","2025-07-09 18:00","취소","취소","연속"]
[453,"전북","김제","소성고창#2 T/L"," 고창-영광T/L No.45~142 선종교체공사","○  고창-영광T/L 선종교체공사 - No.45~142 전력선 교체(ACSR 330㎟ -> ASCC 430㎟)","2025-06-16 07:00","2025-06-26 18:00","취소","취소","연속"]
[454,"전북","김제","김제칠보HP T/L","'25년 가공송전 순시점검 위탁공사","정밀점검","2025-06-04 09:00","2025-06-04 18:00","2025-06-04 09:00","2025-06-04 18:00","연속"]
[455,"전북","김제","담양김제 T/L","'25년 가공송전 순시점검 위탁공사","정밀점검","2025-06-10 09:00","2025-06-10 18:00","2025-06-10 09:00","2025-06-10 18:00","연속"]
[456,"전북","김제","부안동부안#1 T/L","모선구분차단기 설치공사(PT&ES 무부하가압)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-06-25 15:00","2025-06-26 15:00","취소","취소","연속"]
[457,"전북","김제","부안동부안#1 T/L","모선구분차단기 설치공사(6200 무부하가압)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-06-16 15:00","2025-06-17 15:00","취소","취소","연속"]
[458,"전북","김제","부안동부안#1 T/L","모선구분차단기 설치공사(PT&ES 무부하가압)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-06-20 15:00","2025-06-21 15:00","취소","취소","연속"]
[459,"전북","김제","부안동부안#1 T/L","모선구분차단기 설치공사(6200 무부하가압)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-06-11 15:00","2025-06-12 15:00","취소","취소","연속"]
[460,"전북","김제","김제부안#1 T/L","모선구분차단기 설치(PT&ES)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-06-18 09:00","2025-06-26 18:00","취소","취소","연속"]
[461,"전북","김제","김제부안#2 T/L","모선구분차단기 설치(6200)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-06-09 09:00","2025-06-17 18:00","취소","취소","연속"]
[462,"전북","김제","신김제동전주#1 T/L"," 완산S/S 및 분기T/L 건설공사","○ 송전분야 - 작업내용 : 케이블타워 조립, 전선이동, 지중케이블 연결 ○ 변전분야 - 작업내용 : 보호반 이설․설치, 대국시험, 변전기기 무부하 가압 및 PD측정, 실부하 가압","2025-06-13 07:00","2025-06-22 18:00","취소","취소","연속"]
[463,"전북","김제","신김제정공#2 T/L","'25년 가공송전 순시점검 위탁공사","가공지선 보수작업","2025-06-05 09:00","2025-06-05 18:00","2025-06-05 09:00","2025-06-05 18:00","연속"]
[464,"전북","김제","신김제동전주#2 T/L"," 완산분기T/L 건설공사","- 작업내용 : #2T/L 전선이동 (가선로 → 신설선로) - 작업구간 : No.38 ~ No.39 - 위 치 : 전주시 완산구 석구동 일원 - 규 모 : ACSR410㎟ × 2B × 4C (0.81km, 지지물 4기)","2025-06-09 07:00","2025-06-12 18:00","취소","취소","연속"]
[465,"전북","김제","신김제동전주#2 T/L"," 완산S/S 및 분기T/L 건설공사","○ 송전분야 - 작업내용 : 전선이동, 지중케이블 연결 ○ 변전분야 - 작업내용 : 보호반 이설/설치, 대국시험, 변전기기 무부하 가압 및 PD측정, 실부하 가압","2025-06-23 07:00","2025-07-02 18:00","취소","취소","연속"]
[466,"전북","김제","정주동부안#1 T/L","정주S/S 정주-동부안#1T/L GIS 정밀점검(연속)","정주S/S 정주-동부안#1T/L GIS 정밀점검(연속)","2025-06-09 09:00","2025-06-10 18:00","취소","취소","연속"]
[467,"전북","직할","동전주태평#1 T/L","동전주S/S  동전주-태평#1T/L GIS 정밀점검","동전주S/S  동전주-태평#1T/L GIS 정밀점검","2025-06-16 09:00","2025-06-19 18:00","취소","취소","연속"]
[468,"전북","직할","신김제동전주#2 T/L","'25년도 변전설비 기타기기 보통점검","CVT, LA 보통점검","2025-06-27 09:00","2025-06-27 18:00","2025-06-27 09:00","2025-06-27 18:00","연속"]
[469,"전북","직할","신김제동전주#1 T/L","'25년도 변전설비 기타기기 보통점검","CVT, LA 보통점검","2025-06-26 09:00","2025-06-26 18:00","2025-06-26 09:00","2025-06-26 18:00","연속"]
[470,"전북","직할","왕궁봉동#2 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-06-23 08:00","2025-06-23 18:00","취소","취소","매일"]
[471,"전북","직할","왕궁봉동#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-06-20 08:00","2025-06-20 18:00","취소","취소","매일"]
[472,"전북","직할","북전주S/S #1 BUS","북전주-봉동#2TL 1DS 모선부 정밀점검","북전주-봉동#2TL 1DS 모선부 정밀점검","2025-06-30 09:00","2025-07-01 18:00","2025-06-30 09:00","2025-07-01 18:00","연속"]
[473,"전북","직할","북전주봉동#2 T/L","북전주-봉동#2T/L GIS 정밀점검","CB, DS 정밀점검","2025-06-30 09:00","2025-07-04 18:00","취소","취소","연속"]
[474,"전북","직할","북전주진안 T/L","'25년도 변전설비 기타기기 보통점검","CVT, LA 보통점검","2025-06-09 09:00","2025-06-09 18:00","취소","취소","연속"]
[475,"전북","직할","북전주봉동#1 T/L","북전주S/S  북전주-봉동#1T/L 송전선로 보호반 대체","북전주S/S  북전주-봉동#1T/L 송전선로 보호반 대체","2025-06-24 09:00","2025-06-27 18:00","취소","취소","연속"]
[476,"전북","직할","전주서곡#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-06-17 08:00","2025-06-18 18:00","취소","취소","매일"]
[477,"전북","직할","전주서곡#2 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-06-19 08:00","2025-06-20 18:00","취소","취소","매일"]
[478,"전북","직할","탄소전주#1 T/L"," 전주S/S #3M.Tr 교체공사","○  전력용변압기(45/60MVA * 1대) * 1Bank 철거 ○  전력용변압기(15/20MVA * 3대) * 1Bank 재사용철거 및 설치 ○  전력용변압기(15/20MVA * 3대) * 1Bank 정밀점검 ○ 기타 부대작업 * 1식","2025-06-24 16:00","2025-06-25 16:00","2025-06-24 16:00","2025-06-25 16:00","연속"]
[479,"전북","직할","동전주태평#2 T/L","태평S/S  장기사용 GIS 교체공사","170kV GIS × 6CCT 교체(T/L 2CCT, T/R 3CCT, B/T 1CCT)","2025-06-04 09:00","2025-07-09 18:00","취소","취소","연속"]
[480,"전북","직할","서곡태평#1 T/L","태평S/S  장기사용 GIS 교체공사(시험가압)","170kV GIS × 6CCT 교체(T/L 2CCT, T/R 3CCT, B/T 1CCT)","2025-06-16 18:00","2025-06-17 18:00","취소","취소","연속"]
[481,"전북","직할","서곡태평#1 T/L","태평S/S  장기사용 GIS 교체공사(시험가압)","170kV GIS × 6CCT 교체(T/L 2CCT, T/R 3CCT, B/T 1CCT)","2025-06-23 18:00","2025-06-24 18:00","취소","취소","연속"]
[482,"전북","김제","고창영광 T/L","  고창-영광T/L 선종교체공사","  고창-영광T/L 선종교체공사","2025-06-23 07:00","2025-07-28 18:00","2025-06-23 07:00","2025-07-28 18:00","연속"]
[483,"광주전남","강진","강진장흥#2 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","강진-장흥#2T/L 피뢰기설치","2025-06-23 07:00","2025-06-27 18:00","취소","취소","매일"]
[484,"광주전남","강진","금정강진#1 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","금정-강진#1 및 강진-장흥#2(병가구간) 피뢰기 설치","2025-06-23 07:00","2025-06-24 18:00","취소","취소","매일"]
[485,"광주전남","강진","금정강진#1 T/L"," 금정-강진T/L OPGW 불량구간 교체공사","금정-강진T/L OPGW 불량구간 교체(강진-장흥 병가구간 포함)","2025-06-16 07:00","2025-06-20 18:00","취소","취소","매일"]
[486,"광주전남","강진","강진남창#2 T/L"," 영신분기T/L 건설공사","○ 임시선로 → 본선로 공중이동 - (NO.53 - 가철탑 - NO.54) → (NO.53 - C/T#1 , C/T#2 - NO.54) ○ 무부하 시험 및 사용 전 검사","2025-06-16 07:00","2025-06-27 18:00","2025-06-16 07:00","2025-06-27 18:00","연속"]
[487,"광주전남","강진","강진장흥#2 T/L"," 금정-강진T/L OPGW 불량구간 교체공사","금정-강진T/L OPGW 불량구간 교체(강진-장흥 병가구간 포함)","2025-06-16 01:00","2025-06-20 11:00","취소","취소","연속"]
[488,"광주전남","강진","강진장흥#2 T/L","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","- 170kV GIS 보통점검","2025-06-10 10:00","2025-06-10 14:00","2025-06-10 10:00","2025-06-10 14:00","연속"]
[489,"광주전남","강진","신강진강진#1 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","신강진-강진#1 피뢰기 설치","2025-06-04 07:00","2025-06-05 18:00","취소","취소","매일"]
[490,"광주전남","강진","강진남창#1 T/L"," 영신분기T/L 건설공사","○ 임시선로 → 본선로 공중이동 - (NO.53 - 가철탑 - NO.54) → (NO.53 - C/T#1 , C/T#2 - NO.54) ○ 무부하 시험 및 사용 전 검사","2025-06-02 07:00","2025-06-13 18:00","2025-06-02 07:00","2025-06-13 18:00","연속"]
[491,"광주전남","강진","강진남창#1 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","신강진-강진#1(병가구간) 피뢰기 설치","2025-06-04 07:00","2025-06-05 18:00","취소","취소","매일"]
[492,"광주전남","강진","나주엄다#1 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.6.11(수) 08:00 ~ 25.6.12(목) 18:00 4. 작업구간 :  나주-엄다#1T/L No.9~17 (母선로 :  왕곡-나주#1T/L No.6~14)","2025-06-11 08:00","2025-06-12 18:00","취소","취소","매일"]
[493,"광주전남","강진","나주영암#1 T/L","2025년 가공송전 순시점검 위탁공사","나주-영암#1T/L 정밀점검 (영암-금정#2T/L, 나주-금천#2T/L 병가선로)","2025-06-11 09:00","2025-06-20 18:00","2025-06-18 09:00","2025-06-28 18:00","매일"]
[494,"광주전남","강진","나주엄다#2 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.6.16(월) 08:00 ~ 25.6.17(화) 18:00 4. 작업구간 :  나주-엄다#2T/L No.9~17 (母선로 :  왕곡-나주#2T/L No.6~14)","2025-06-16 08:00","2025-06-17 18:00","취소","취소","매일"]
[495,"광주전남","강진","나주금천#2 T/L","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","- 170kV GIS 보통점검","2025-06-13 10:00","2025-06-13 14:00","취소","취소","연속"]
[496,"광주전남","강진","나주금천#2 T/L","2025년 가공송전 순시점검 위탁공사","나주-영암#1T/L 정밀점검(안전이격 확보) (나주-영암#1T/L 병가선로)","2025-06-17 09:00","2025-06-20 18:00","2025-06-24 09:00","2025-06-27 18:00","매일"]
[497,"광주전남","강진","남창S/S 모선연계T/L CB","남창S/S 남창-해남C/S 인출변경 공사","남창-해남C/S 인출변경 × 1식","2025-06-25 07:00","2025-06-29 15:00","2025-06-25 07:00","2025-06-29 15:00","연속"]
[498,"광주전남","강진","남창해남CS#2 T/L","남창S/S 남창-해남C/S 인출변경 공사","남창-해남C/S 인출변경 × 1식","2025-06-23 09:00","2025-06-25 15:00","2025-06-23 09:00","2025-06-25 15:00","연속"]
[499,"광주전남","강진","남창해남CS#1 T/L","남창S/S 남창-해남C/S 인출변경 공사","남창-해남C/S 인출변경 × 1식","2025-06-25 07:00","2025-06-29 15:00","2025-06-25 07:00","2025-06-29 15:00","연속"]
[500,"광주전남","강진","신강진대불#2 T/L","2024~25년 강진전력지사 송전협력회사 공사","신강진-대불#2T/L 가공지선 교체 (40~42호)","2025-06-24 07:00","2025-06-24 18:00","취소","취소","매일"]
[501,"광주전남","강진","영암금정#2 T/L","2025년 가공송전 순시점검 위탁공사","영암-금정#2T/L 정밀점검 (나주-영암#1T/L 병가선로)","2025-06-09 09:00","2025-06-16 18:00","2025-06-16 09:00","2025-06-23 18:00","매일"]
[502,"광주전남","강진","장흥벌교 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","장흥-벌교 및 강진-장흥#2(병가구간) 피뢰기 설치","2025-06-25 07:00","2025-07-03 18:00","취소","취소","매일"]
[503,"광주전남","강진","해남해남CS#1 T/L","2024~25년 강진전력지사 송전협력회사 공사","수평 추락방지장치 설치","2025-06-25 07:00","2025-07-02 18:00","취소","취소","매일"]
[504,"광주전남","강진","화원진도#2 T/L","2025년 가공송전 순시점검 위탁공사","화원-진도#2T/L 정밀점검","2025-06-23 09:00","2025-06-25 18:00","취소","취소","매일"]
[505,"광주전남","강진","화원안좌#2 T/L","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","- 170kV GIS 보통점검","2025-06-17 14:00","2025-06-17 18:00","취소","취소","연속"]
[506,"광주전남","강진","화원안좌#1 T/L","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","- 170kV GIS 보통점검","2025-06-17 10:00","2025-06-17 14:00","취소","취소","연속"]
[507,"광주전남","광주","북광주계림#2 T/L","계림S/S  GIS 교체공사(2차분)","계림S/S  GIS 교체공사(2차분)","2025-06-15 09:00","2025-06-15 18:00","2025-06-15 09:00","2025-06-15 18:00","연속"]
[508,"광주전남","광주","북광주계림#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 북광주-계림#2T/L 조작시험","2025-06-16 14:00","2025-06-16 16:00","2025-06-16 14:00","2025-06-16 16:00","연속"]
[509,"광주전남","광주","북광주계림#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 북광주-계림#1T/L 조작시험","2025-06-16 10:00","2025-06-16 14:00","2025-06-16 10:00","2025-06-16 14:00","연속"]
[510,"광주전남","광주","북광주계림#2 T/L","계림S/S  GIS 교체공사(2차분)","계림S/S  GIS 교체공사(2차분)","2025-06-08 09:00","2025-06-08 18:00","2025-06-08 09:00","2025-06-08 18:00","연속"]
[511,"광주전남","광주","계림승주#2 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 계림-승주#2 T/L 피뢰기 설치 - 대상 : 1~3, 17~107호 (총 99기) - 병가구간 : 3호 (신광주-계림#1,#2 병가), 99~106호(순천-승주#1 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-06-02 07:00","2025-06-17 18:00","2025-06-02 07:00","2025-06-17 18:00","매일"]
[512,"광주전남","광주","곡성구례#1 T/L","2024~25년 광주전력지사 송전 협력회사공사"," 곡성-구례T/L 폴리머점퍼지지애자 설치공사","2025-06-02 07:00","2025-06-09 18:00","취소","취소","매일"]
[513,"광주전남","광주","곡성구례#2 T/L","2024~25년 광주전력지사 송전 협력회사공사"," 곡성-구례T/L 폴리머점퍼지지애자 설치공사","2025-06-10 07:00","2025-06-16 18:00","취소","취소","매일"]
[514,"광주전남","광주","계림남광주 T/L"," 남광주C/T 이설공사"," 남광주C/T(58호) 신설시 안전이격확보 휴전","2025-06-16 00:07","2025-06-17 18:00","취소","취소","매일"]
[515,"광주전남","광주","남광주소태 T/L"," 남광주C/T 이설공사"," 남광주C/T(58호) 신설시 안전이격확보 휴전","2025-06-16 00:07","2025-06-17 18:00","취소","취소","매일"]
[516,"광주전남","광주","정공담양 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 담양-일곡#2 T/L 피뢰기 설치 (병가) - 대상 : 1~16, 173~189, 193~228호 (총 71기) - 병가구간 : 2~15호 (담양-정공 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-06-25 07:00","2025-06-26 18:00","취소","취소","매일"]
[517,"광주전남","광주","신광주S/S CB 6444","2025년 광주전력지사 170kV GIS 점검 공사","1. 2025년 광주전력지사 변전협력회사 공사 - 신광주S/S 345kV #4M.Tr 7800CB, 7872CB 조작시험 2. (발주) 2025년 광주전력지사 170kV GIS 점검공사 -  #4M.Tr 2차 GIS 보통점검","2025-06-16 09:00","2025-06-16 18:00","취소","취소","연속"]
[518,"광주전남","광주","신광주계림#2 T/L","2024~25년 광주전력지사 송전 협력회사공사(추락방지)"," 신광주-계림T/L 추락방지장치설치공사 No.16~27.2호","2025-06-19 07:00","2025-06-19 18:00","2025-06-19 07:00","2025-06-19 18:00","연속"]
[519,"광주전남","광주","신광주계림#1 T/L","2024~25년 광주전력지사 송전 협력회사공사(추락방지)"," 신광주-계림T/L 추락방지장치설치공사 No.16~27.2호","2025-06-18 07:00","2025-06-18 18:00","2025-06-18 07:00","2025-06-18 18:00","연속"]
[520,"광주전남","광주","신화순화순#2 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 피뢰기갭혼교체 시행 -  신화순-화순 #2 T/L 1~5, 10~57호","2025-06-12 08:00","2025-06-18 18:00","취소","취소","매일"]
[521,"광주전남","광주","신화순화순#1 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 피뢰기갭혼교체 시행 -  신화순-화순#1T/L 1~5, 10~57호","2025-06-04 08:00","2025-06-11 18:00","취소","취소","매일"]
[522,"광주전남","광주","담양일곡#1 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2. 2025년 광주전력지사 170kV GIS 점검공사 - 일곡S/S  담양-일곡#1T/L 보통점검","2025-06-20 09:00","2025-06-20 18:00","취소","취소","연속"]
[523,"광주전남","광주","담양일곡#2 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 담양-일곡#2 T/L 피뢰기 설치 - 대상 : 1~16, 173~189, 193~228호 (총 71기) - 병가구간 : 2~15호 (담양-정공 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-06-25 07:00","2025-06-30 18:00","취소","취소","매일"]
[524,"광주전남","광주","하남장성#1 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 장성-영광#2 T/L 피뢰기 설치(병가) - 대상 : 1~15, 21~68호 (총 64기) - 병가구간 : 2~15호 (하남-장성#1 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-06-18 07:00","2025-06-19 18:00","취소","취소","매일"]
[525,"광주전남","광주","장성영광#2 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 장성-영광#2 T/L 피뢰기 설치 - 대상 : 1~15, 21~68호 (총 64기) - 병가구간 : 2~15호 (하남-장성 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-06-18 07:00","2025-06-24 18:00","취소","취소","매일"]
[526,"광주전남","광주","신광주장성#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","-신광주-장성#1T/L 170kV GIS 조작시험","2025-06-13 15:00","2025-06-13 18:00","2025-06-13 15:00","2025-06-13 18:00","연속"]
[527,"광주전남","광주","계림충장#3 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 계림-충장#3T/L 170kV GIS 조작시험","2025-06-11 14:00","2025-06-11 16:00","2025-06-11 14:00","2025-06-11 16:00","연속"]
[528,"광주전남","광주","계림충장#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 계림-충장S/S #2T/L 170kV GIS 조작시험","2025-06-11 10:00","2025-06-11 14:00","2025-06-11 10:00","2025-06-11 14:00","연속"]
[529,"광주전남","광주","충장농성#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 충장-농성#2T/L 170kV GIS 조작시험","2025-06-10 14:00","2025-06-10 16:00","2025-06-10 14:00","2025-06-10 16:00","연속"]
[530,"광주전남","광주","충장농성#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 충장-농성#1T/L 170kV GIS 조작시험","2025-06-10 10:00","2025-06-10 14:00","2025-06-10 10:00","2025-06-10 14:00","연속"]
[531,"광주전남","광주","계림충장#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 계림-충장#1T/L 170kV GIS 조작시험","2025-06-12 10:00","2025-06-12 16:00","2025-06-12 10:00","2025-06-12 16:00","연속"]
[532,"광주전남","목포","목포북항#2 T/L","2024~2025년 목포전력지사 변전협력회사 총액공사","목포-북항#2T/L GIS 보통점검","2025-06-16 10:00","2025-06-16 18:00","취소","취소","연속"]
[533,"광주전남","목포","화원안좌#2 T/L","24~25년 목포전력지사 송전협력회사 공사","1. 공사명 : 고정형 폴리머 점퍼지지애자 설치 2. 공사내용  화원-안좌T/L 고정형폴리머 점퍼지지애자 설치 3. 공사구간  화원-안좌#2 No.5~46(7기)","2025-06-19 07:30","2025-06-20 17:00","취소","취소","매일"]
[534,"광주전남","목포","안좌읍동#2 T/L CB","2024~2025년 목포전력지사 변전협력회사 총액공사","안좌-읍동#2T/L GIS 보통점검","2025-06-18 10:00","2025-06-18 18:00","2025-06-18 10:00","2025-06-18 18:00","연속"]
[535,"광주전남","목포","안좌읍동 T/L CB","2024~2025년 목포전력지사 변전협력회사 총액공사","안좌-(임시)읍동T/L GIS 보통점검","2025-06-17 10:00","2025-06-17 18:00","2025-06-17 10:00","2025-06-17 18:00","연속"]
[536,"광주전남","목포","화원안좌#1 T/L","24~25년 목포전력지사 송전협력회사 공사","1. 공사명 : 고정형 폴리머 점퍼지지애자 설치 2. 공사내용  화원-안좌T/L 고정형폴리머 점퍼지지애자 설치 3. 공사구간  화원-안좌#1 No.1~47(11기)","2025-06-16 07:30","2025-06-18 17:00","취소","취소","매일"]
[537,"광주전남","목포","엄다무안햇빛#1 T/L","24~25년 목포전력지사 송전협력회사 공사","1. 공사명 : 고정형 폴리머 점퍼지지애자 설치 2. 공사내용  엄다-무안햇빛T/L 고정형폴리머 점퍼지지애자 설치 3. 공사구간  엄다-무안햇빛#1 No.4~39(13기)","2025-06-02 07:30","2025-06-05 17:00","취소","취소","매일"]
[538,"광주전남","목포","나주엄다#1 T/L","24~25년 목포전력지사 송전협력회사 공사(피뢰기 설치)"," 나주-엄다T/L 피뢰기 설치(116기)","2025-06-02 08:00","2025-06-11 18:00","취소","취소","매일"]
[539,"광주전남","목포","엄다무안햇빛#2 T/L","24~25년 목포전력지사 송전협력회사 공사","1. 공사명 : 고정형 폴리머 점퍼지지애자 설치 2. 공사내용  엄다-무안햇빛T/L 고정형폴리머 점퍼지지애자 설치 3. 공사구간  엄다-무안햇빛#2 No.2~41(14기)","2025-06-06 07:30","2025-06-11 17:00","취소","취소","매일"]
[540,"광주전남","목포","엄다목포#2 T/L","24~25년 목포전력지사 송전협력회사 공사(피뢰기 설치)"," 나주-엄다T/L 피뢰기 설치 병가구간 휴전 및  엄다-목포T/L 피뢰기 설치","2025-06-09 08:00","2025-06-17 18:00","취소","취소","매일"]
[541,"광주전남","목포","나주엄다#1 T/L","2024~2025년 목포전력지사 변전협력회사 총액공사","나주-엄다#1T/L GIS 보통점검","2025-06-09 10:00","2025-06-09 18:00","취소","취소","연속"]
[542,"광주전남","목포","나주엄다#2 T/L","2024~2025년 목포전력지사 변전협력회사 총액공사","나주-엄다#2T/L GIS 보통점검","2025-06-10 10:00","2025-06-10 18:00","취소","취소","연속"]
[543,"광주전남","목포","엄다목포#1 T/L","2024~2025년 목포전력지사 변전협력회사 총액공사","엄다-목포#1T/L GIS 보통점검","2025-06-11 10:00","2025-06-11 18:00","취소","취소","연속"]
[544,"광주전남","목포","엄다목포#2 T/L","2024~2025년 목포전력지사 변전협력회사 총액공사","엄다-목포#2T/L GIS 보통점검","2025-06-12 10:00","2025-06-12 18:00","취소","취소","연속"]
[545,"광주전남","목포","장성영광#1 T/L","고창-홍농T/L 선종교체공사","공사명 :  영광-홍농 등 4개T/L 선종교체공사 교체구간 : 고창-홍농T/L 41~45호, 45~41호(10기분)","2025-06-27 07:00","2025-07-09 18:00","2025-06-27 07:00","2025-07-09 18:00","연속"]
[546,"광주전남","목포","장성영광#1 T/L","24~25년 목포전력지사 송전협력회사 공사","1. 공사명 : 고정형 폴리머 점퍼지지애자 설치 2. 공사내용  영광-홍농T/L 고정형폴리머점퍼지지애자 설치 3. 공사구간  영광-홍농 No.7~68(17기) ( 장성-영광T/L 병가구간 포함) 병가구간 휴전","2025-06-04 07:30","2025-06-05 17:00","취소","취소","매일"]
[547,"광주전남","목포","영광홍농 T/L"," 서홍농개폐소 건설공사(영광-홍농분기,고객시공)","○ 구간 :  영광-홍농T/L 61~64호 ○ 내용 : 철탑 2기 신설, 기설철탑 2기 보강 및 전력선 교체, 개폐소 계통연계, OPGW 공사, 보호배전반 교체 등","2025-06-13 07:00","2025-06-18 18:00","2025-06-13 07:00","2025-06-18 18:00","연속"]
[548,"광주전남","목포","영광홍농 T/L","24~25년 목포전력지사 송전협력회사 공사","1. 공사명 : 고정형 폴리머 점퍼지지애자 설치 2. 공사내용  영광-홍농T/L 고정형폴리머점퍼지지애자 설치 3. 공사구간  영광-홍농 No.7~68(17기) ( 장성-영광T/L 병가구간 포함)","2025-06-02 07:30","2025-06-06 17:00","취소","취소","매일"]
[549,"광주전남","목포","장성영광#1 T/L"," 서홍농개폐소 건설공사(영광-홍농분기,고객시공)","○ 내용 :  영광-서홍농T/L, 서홍농-홍농#1T/L 앵글측정 및 서홍농개폐소 무부하가압","2025-06-17 14:00","2025-06-18 15:00","2025-06-17 14:00","2025-06-18 15:00","연속"]
[550,"광주전남","목포","장성영광#1 T/L","2024~2025년 목포전력지사 변전협력회사 총액공사","장성-영광#1T/L GIS 보통점검","2025-06-09 10:00","2025-06-09 18:00","취소","취소","연속"]
[551,"광주전남","목포","장성영광#2 T/L","2024~2025년 목포전력지사 변전협력회사 총액공사","장성-영광#2T/L GIS 보통점검","2025-06-10 10:00","2025-06-10 18:00","취소","취소","연속"]
[552,"광주전남","목포","고창홍농 T/L"," 서홍농개폐소 건설공사(고창-홍농분기,고객시공)","○ 구간 :  고창-홍농T/L 61~64호 ○ 내용 : 철탑 2기 신설, 기설철탑 2기 철거, 기설철탑 2기 보강 및 전력선 교체, 개폐소 계통연계, OPGW 공사, 보호배전반 교체 등","2025-06-19 07:00","2025-06-24 18:00","2025-06-19 07:00","2025-06-24 18:00","연속"]
[553,"광주전남","목포","고창홍농 T/L","24~25년 목포전력지사 송전협력회사 공사","1. 공사명 : 고정형 폴리머 점퍼지지애자 설치 2. 공사내용  고창-홍농T/L 고정형폴리머점퍼지지애자 설치 3. 공사구간  고창-홍농 No.42~66(6기)","2025-06-09 07:30","2025-06-10 17:00","취소","취소","매일"]
[554,"광주전남","순천","세풍율촌#2 T/L","조작불량관련 기계적 접점 교체","조작불량관련 기계적 접점 교체","2025-06-05 14:00","2025-06-05 18:00","2025-06-05 14:00","2025-06-05 18:00","연속"]
[555,"광주전남","순천","황금세풍#1 T/L CB","조작불량관련 기계적 접점 교체","조작불량관련 기계적 접점 교체","2025-06-04 14:00","2025-06-04 18:00","2025-06-04 14:00","2025-06-04 18:00","연속"]
[556,"광주전남","순천","백운세풍#2 T/L","조작불량관련 기계적 접점 교체","조작불량관련 기계적 접점 교체","2025-06-04 10:00","2025-06-04 14:00","2025-06-04 10:00","2025-06-04 14:00","연속"]
[557,"광주전남","순천","세풍율촌#1 T/L","조작불량관련 기계적 접점 교체","조작불량관련 기계적 접점 교체","2025-06-05 10:00","2025-06-05 14:00","2025-06-05 10:00","2025-06-05 14:00","연속"]
[558,"광주전남","순천","승주서순천 T/L"," 승주-서순천 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (승주-서순천, 화순-승주2(통보분) 병가) (3일 휴일 미작업)","2025-06-02 07:00","2025-06-05 18:00","취소","취소","매일"]
[559,"광주전남","순천","승주주암HP T/L"," 승주-서순천 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (승주-주암HP, 화순-승주1(통보분) 병가)","2025-06-09 07:00","2025-06-12 18:00","취소","취소","매일"]
[560,"광주전남","순천","여천여수#2 T/L"," 여수-소라 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여수-소라2, 여천-여수2 병가)","2025-06-30 07:00","2025-06-30 18:00","2025-06-30 18:00","2025-07-01 07:00","연속"]
[561,"광주전남","순천","여수소라#1 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-06-18 10:00","2025-06-19 10:00","2025-06-18 18:00","2025-06-19 09:00","연속"]
[562,"광주전남","순천","여천여수#1 T/L"," 여수-소라 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여수-소라1, 여천-여수1 병가)","2025-06-18 07:00","2025-06-18 18:00","2025-06-18 18:00","2025-06-19 07:00","연속"]
[563,"광주전남","순천","여수소라#1 T/L"," 여수-소라 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여수-소라1, 여천-여수1 병가)","2025-06-18 07:00","2025-06-18 18:00","취소","취소","연속"]
[564,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - 안전이격휴전","2025-06-12 10:00","2025-06-12 17:00","2025-06-12 18:00","2025-06-12 21:00","연속"]
[565,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - 안전이격휴전","2025-06-11 10:00","2025-06-11 17:00","2025-06-11 18:00","2025-06-11 21:00","연속"]
[566,"광주전남","순천","여천여수#1 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-06-05 09:00","2025-06-27 18:00","취소","취소","연속"]
[567,"광주전남","순천","여수소라#2 T/L"," 여수-소라 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여수-소라2, 여천-여수2 병가)","2025-06-30 07:00","2025-06-30 18:00","취소","취소","연속"]
[568,"광주전남","순천","용성여수산단#2 T/L"," 용성-여수산단#2T/L #1DS 가스누기 해소공사"," 용성-여수산단#2T/L #1DS 가스누기 해소공사","2025-06-04 09:00","2025-06-05 18:00","취소","취소","연속"]
[569,"광주전남","순천","여수TP화치#1 T/L","2025년 순천전력지사 362kV,170kV GIS 정밀점검공사","여수화력S/S 여수TP-화치#1T/L GIS 정밀점검","2025-06-11 09:00","2025-06-12 18:00","2025-06-11 09:00","2025-06-12 18:00","연속"]
[570,"광주전남","순천","여수T/P #65 BUS","GS 칼텍스 여수#2T/L #2DS 가스누기해소 공사","#2DS 가스누기해소 공사","2025-06-09 09:00","2025-06-10 18:00","취소","취소","연속"]
[571,"광주전남","순천","여천여수#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여천-호남TP2, 여천-여수1 병가)","2025-06-23 07:00","2025-06-27 18:00","취소","취소","매일"]
[572,"광주전남","순천","여천호남TP#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여천-호남TP2, 여천-여수1 병가)","2025-06-23 07:00","2025-06-27 18:00","2025-06-23 07:00","2025-06-27 18:00","매일"]
[573,"광주전남","순천","여수TP용성#1 T/L"," 여수TP-용성 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여수TP-용성1, 용성-여수산단1 병가)","2025-06-13 07:00","2025-06-13 18:00","취소","취소","연속"]
[574,"광주전남","순천","여수TP용성#2 T/L"," 여수TP-용성 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여수TP-용성2, 용성-여수산단2 병가)","2025-06-05 07:00","2025-06-05 18:00","취소","취소","연속"]
[575,"광주전남","순천","용성여수산단#2 T/L"," 여수TP-용성 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여수TP-용성2, 용성-여수산단2 병가)","2025-06-05 07:00","2025-06-05 18:00","취소","취소","연속"]
[576,"광주전남","순천","용성여수산단#1 T/L"," 여수TP-용성 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여수TP-용성1, 용성-여수산단1 병가)","2025-06-13 07:00","2025-06-13 18:00","취소","취소","연속"]
[577,"광주전남","순천","여수TP용성#1 T/L","GIS 불량 유압력계 교체","GIS 불량 유압력계 교체","2025-06-13 09:00","2025-06-13 18:00","취소","취소","연속"]
[578,"광주전남","순천","율촌화치#2 T/L","율촌-여수산단#1 T/L 정밀점검","율촌-여수산단#1 T/L 정밀점검 총 51기 - 병가선로 휴전신청","2025-06-23 09:00","2025-06-27 18:00","2025-06-23 09:00","2025-06-27 18:00","매일"]
[579,"광주전남","순천","율촌여수산단#1 T/L","율촌-여수산단#1 T/L 정밀점검","율촌-여수산단#1 T/L 정밀점검 총 51기","2025-06-23 09:00","2025-06-27 18:00","취소","취소","매일"]
[580,"광주전남","순천","율촌여수산단#2 T/L","율촌-여수산단#2 T/L 정밀점검","율촌-여수산단#2 T/L 정밀점검 총 51기","2025-06-16 09:00","2025-06-20 18:00","취소","취소","매일"]
[581,"광주전남","순천","율촌화치#1 T/L","율촌-여수산단#2 T/L 정밀점검","율촌-여수산단#2 T/L 정밀점검 총 51기 - 병가선로 휴전신청","2025-06-16 09:00","2025-06-20 18:00","2025-06-16 09:00","2025-06-20 18:00","매일"]
[582,"광주전남","순천","율촌민자#2 T/L"," 율촌민자 T/L 추락방지시설 설치공사","수평추락방지시설 설치","2025-06-04 07:00","2025-06-04 18:00","2025-06-04 07:00","2025-06-04 18:00","연속"]
[583,"광주전남","순천","율촌민자#1 T/L"," 율촌민자 T/L 추락방지시설 설치공사","수평추락방지시설 설치","2025-06-02 07:00","2025-06-02 18:00","2025-06-02 07:00","2025-06-02 18:00","연속"]
[584,"광주전남","순천","태금하동화력 T/L","효성제 170kv gis 부품 교체 시행","효성제 170kv gis 부품 교체 시행(즉시가압 불가)","2025-06-13 09:00","2025-06-13 18:00","2025-06-13 09:00","2025-06-13 18:00","연속"]
[585,"광주전남","직할","남광주금천#2 T/L"," 남광주-금천T/L 지장송전선로 이설공사","○ 설치 : 관형지지물 1기, 전력선 0.51km ○ 기타 : 병가선로 안전이격 휴전 시행(매일)","2025-06-11 07:00","2025-06-13 18:00","2025-06-13 06:00","2025-06-13 17:00","매일"]
[586,"광주전남","직할","남광주금천#1 T/L"," 남광주-금천T/L 지장송전선로 이설공사","○ 설치 : 관형지지물 1기, 전력선 0.51km ○ 기타 : 병가선로 안전이격 휴전 시행(매일)","2025-06-02 07:00","2025-06-04 18:00","2025-06-04 06:00","2025-06-06 17:00","연속"]
[587,"광주전남","직할","나주금천#2 T/L"," 남광주-금천T/L 지장송전선로 이설공사","○ 설치 : 관형지지물 1기, 전력선 0.51km ○ 기타 : 병가선로 안전이격 휴전 시행(매일)","2025-06-02 07:00","2025-06-04 18:00","2025-06-04 06:00","2025-06-06 17:00","매일"]
[588,"광주전남","직할","나주금천#2 T/L"," 남광주-금천T/L 지장송전선로 이설공사","○ 설치 : 관형지지물 1기, 전력선 0.51km ○ 기타 : 병가선로 안전이격 휴전 시행(매일)","2025-06-05 07:00","2025-06-07 18:00","2025-06-09 06:00","2025-06-09 17:00","연속"]
[589,"광주전남","직할","남광주금천#1 T/L"," 남광주-금천T/L 지장송전선로 이설공사","○ 설치 : 관형지지물 1기, 전력선 0.51km ○ 기타 : 병가선로 안전이격 휴전 시행(매일)","2025-06-05 07:00","2025-06-07 18:00","2025-06-09 06:00","2025-06-09 17:00","매일"]
[590,"광주전남","직할","나주금천#1 T/L"," 남광주-금천T/L 지장송전선로 이설공사","○ 설치 : 관형지지물 1기, 전력선 0.51km ○ 기타 : 병가선로 안전이격 휴전 시행(매일)","2025-06-08 07:00","2025-06-10 18:00","2025-06-10 06:00","2025-06-12 17:00","매일"]
[591,"광주전남","직할","남광주금천#2 T/L"," 남광주-금천T/L 지장송전선로 이설공사","○ 설치 : 관형지지물 1기, 전력선 0.51km ○ 기타 : 병가선로 안전이격 휴전 시행(매일)","2025-06-08 07:00","2025-06-10 18:00","2025-06-10 06:00","2025-06-12 17:00","연속"]
[592,"광주전남","직할","나주금천#1 T/L"," 남광주-금천T/L 지장송전선로 이설공사","○ 설치 : 관형지지물 1기, 전력선 0.51km ○ 기타 : 병가선로 안전이격 휴전 시행(매일)","2025-06-11 07:00","2025-06-13 18:00","2025-06-13 06:00","2025-06-13 17:00","연속"]
[593,"광주전남","직할","매월화정#2 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검","2025-06-25 09:00","2025-06-26 18:00","취소","취소","연속"]
[594,"광주전남","직할","매월화정#1 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검","2025-06-23 09:00","2025-06-24 18:00","취소","취소","연속"]
[595,"광주전남","직할","일곡비아#1 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검","2025-06-16 09:00","2025-06-20 18:00","2025-06-16 09:00","2025-06-20 18:00","연속"]
[596,"광주전남","직할","왕곡나주#1 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.6.11(수) 08:00 ~ 25.6.13(금) 18:00 4. 작업구간 :  왕곡-나주#1T/L No.1~20 5. 작업내용 : 정밀점검","2025-06-11 08:00","2025-06-13 18:00","2025-06-11 08:00","2025-06-13 18:00","매일"]
[597,"광주전남","직할","왕곡나주#2 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.6.16(월) 08:00 ~ 25.6.18(수) 18:00 4. 작업구간 :  왕곡-나주#2T/L No.1~20 5. 작업내용 : 정밀점검","2025-06-16 08:00","2025-06-18 18:00","2025-06-16 08:00","2025-06-18 18:00","매일"]
[598,"광주전남","직할","하남장성#2 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검","2025-06-30 14:00","2025-06-30 18:00","2025-06-30 14:00","2025-06-30 18:00","연속"]
[599,"광주전남","직할","비아하남#1 T/L"," 첨단분기 T/L 건설공사","ㅁ  첨단분기 T/L 건설공사 ㅇ 관형지지물(C/T) 상부재(1단) 조립","2025-06-10 07:00","2025-06-10 18:00","취소","취소","연속"]
[600,"광주전남","직할","하남장성#1 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검","2025-06-30 09:00","2025-06-30 14:00","2025-06-30 09:00","2025-06-30 14:00","연속"]
[601,"광주전남","직할","하남장성#2 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 애자련 보강 작업구간 : 하남-장성T/L 2호","2025-06-03 07:00","2025-06-03 18:00","2025-06-04 07:00","2025-06-04 18:00","연속"]
[602,"광주전남","직할","하남장성#1 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 애자련 보강 작업구간 : 하남-장성T/L 2호","2025-06-02 07:00","2025-06-02 18:00","취소","취소","연속"]
[603,"대구","경산","진량노변 T/L"," 진량-노변T/L 지중송전 피뢰기 열화진단 및 EBA절연유 채유","지중송전 피뢰기 점검 및 EBA절연유 채유","2025-06-16 09:00","2025-06-17 18:00","2025-06-16 09:00","2025-06-17 18:00","연속"]
[604,"대구","달성","고령다산#1 T/L","#60-65 BUS SEC GIS 정밀점검 관련 무부하가압 휴전","#60-65 BUS SEC GIS 정밀점검 관련 무부하가압 휴전","2025-06-19 17:00","2025-06-19 18:00","2025-06-19 17:00","2025-06-19 18:00","연속"]
[605,"대구","달성","고령서구지#1 T/L","고령-서구지#1T/L GIS 보통점검","고령-서구지#1T/L GIS 보통점검","2025-06-20 09:00","2025-06-20 18:00","2025-06-20 09:00","2025-06-20 18:00","연속"]
[606,"대구","달성","고령S/S SEC CB 60610","#60-61BUS SEC GIS 정밀점검","#60-61BUS SEC GIS 정밀점검","2025-06-23 09:00","2025-06-24 18:00","2025-06-23 09:00","2025-06-24 18:00","연속"]
[607,"대구","달성","고령S/S CB 6100","#60-65 BUS SEC GIS 정밀점검","#60-65 BUS SEC GIS 정밀점검","2025-06-18 09:00","2025-06-19 18:00","2025-06-18 09:00","2025-06-19 18:00","연속"]
[608,"대구","달성","고령다산#1 T/L","#60-61BUS SEC GIS 정밀점검 관련 무부하가압 휴전","#60-61BUS SEC GIS 정밀점검 관련 무부하가압 휴전","2025-06-24 17:00","2025-06-24 18:00","2025-06-24 17:00","2025-06-24 18:00","연속"]
[609,"대구","달성","고령다산#2 T/L","고령-다산#2/TL 정밀점검","고령-다산#2/TL 정밀점검","2025-06-16 09:00","2025-06-17 18:00","2025-06-16 09:00","2025-06-17 18:00","연속"]
[610,"대구","달성","고령S/S SEC CB 65660","#65-66BUS SEC GIS 정밀점검","#65-66BUS SEC GIS 정밀점검","2025-06-25 09:00","2025-06-26 18:00","2025-06-25 09:00","2025-06-26 18:00","연속"]
[611,"대구","달성","고령다산#2 T/L","#65-66BUS SEC GIS 정밀점검 관련 무부하가압 휴전","#65-66BUS SEC GIS 정밀점검 관련 무부하가압 휴전","2025-06-26 17:00","2025-06-26 18:00","2025-06-26 17:00","2025-06-26 18:00","연속"]
[612,"대구","달성","고령서구지#2 T/L","고령-서구지#2T/L GIS 보통점검","고령-서구지#2T/L GIS 보통점검","2025-06-27 09:00","2025-06-27 18:00","2025-06-13 09:00","2025-06-13 18:00","연속"]
[613,"대구","달성","고령다산#1 T/L","2025년 가공송전 순시점검 위탁공사[정밀점검]"," 고령-다산 #1T/L 정밀점검(2~12호)","2025-06-09 08:00","2025-06-10 18:00","2025-06-09 08:00","2025-06-10 18:00","연속"]
[614,"대구","달성","고령쌍림#1 T/L","2025년 가공송전 순시점검 위탁공사[정밀점검]"," 고령-쌍림 #1T/L 정밀점검(2~63호) 및 피뢰기 갭혼 촉 하자 교체시행 - 주말제외 연속휴전","2025-06-09 08:00","2025-06-18 18:00","취소","취소","연속"]
[615,"대구","달성","고령다산#1 T/L","#1M.TR 정밀점검 관련 무부하가압 휴전","#1M.TR 정밀점검 관련 무부하가압 휴전","2025-06-13 17:00","2025-06-13 18:00","2025-06-13 17:00","2025-06-13 18:00","연속"]
[616,"대구","달성","다사달서 T/L","강창-달서T/L LA대체 관련 안전확보휴전","강창-달서T/L LA대체 관련 안전확보휴전","2025-06-05 09:00","2025-06-05 18:00","2025-06-05 09:00","2025-06-05 18:00","연속"]
[617,"대구","달성","상인S/S #1 BUS","상인S/S  GIS 교체공사(4차)","○상인S/S  GIS 교체공사(4차) - 상인봉덕#2T/L + #1M.Tr 1차 GIS 교체","2025-06-16 09:00","2025-06-27 14:00","2025-06-19 09:00","2025-06-20 09:00","연속"]
[618,"대구","달성","상인봉덕#2 T/L","상인S/S  GIS 교체공사(4차)","○상인S/S  GIS 교체공사(4차) - 상인봉덕#2T/L + #1M.Tr 1차 GIS 교체","2025-06-04 09:00","2025-06-27 16:00","2025-06-04 09:00","2025-06-21 16:00","연속"]
[619,"대구","달성","구지서구지#1 T/L","#60-65BUS TIE GIS 정밀점검 관련 무부하가압 휴전","#60-65BUS TIE GIS 정밀점검 관련 무부하가압 휴전","2025-06-05 17:00","2025-06-05 18:00","2025-06-05 17:00","2025-06-05 18:00","연속"]
[620,"대구","달성","성서지역난방공사#2 T/L CB","GIS 초기점검","GIS 초기점검","2025-06-02 09:00","2025-06-02 18:00","2025-06-02 09:00","2025-06-02 18:00","연속"]
[621,"대구","달성","강창성서#1 T/L","강창-성서#1T/L 피뢰기대체","강창-성서#1T/L 피뢰기대체","2025-06-04 09:00","2025-06-04 18:00","2025-06-04 09:00","2025-06-04 18:00","연속"]
[622,"대구","달성","쌍림합천#2 T/L","2025년 가공송전 순시점검 위탁공사[정밀점검]"," 쌍림-합천 #2T/L 정밀점검(1~22호)","2025-06-18 08:00","2025-06-20 18:00","취소","취소","연속"]
[623,"대구","칠곡","어모김천#1 T/L"," 김천S/S 현대화공사","○  GIS 김천-금릉#1T/L 스페이서 교체(무부하가압)","2025-06-12 14:00","2025-06-13 18:00","2025-06-20 18:00","2025-06-21 18:00","연속"]
[624,"대구","칠곡","남구미농소#2 T/L","농소S/S  모선보호반 대체(연동시험)","농소S/S  모선보호반 대체(연동시험)","2025-06-19 17:00","2025-06-19 18:00","2025-06-19 17:00","2025-06-19 18:00","연속"]
[625,"대구","칠곡","농소김천#2 T/L","농소S/S  모선보호반 대체(연동시험)","농소S/S  모선보호반 대체(연동시험)","2025-06-19 14:00","2025-06-19 15:00","2025-06-19 14:00","2025-06-19 15:00","연속"]
[626,"대구","칠곡","농소김천#1 T/L","농소S/S  모선보호반 대체(연동시험)","농소S/S  모선보호반 대체(연동시험)","2025-06-19 10:30","2025-06-19 11:30","2025-06-19 10:30","2025-06-19 11:30","연속"]
[627,"대구","칠곡","남구미농소#1 T/L","농소S/S  모선보호반 대체(연동시험)","농소S/S  모선보호반 대체(연동시험)","2025-06-19 16:00","2025-06-19 17:00","2025-06-19 16:00","2025-06-19 17:00","연속"]
[628,"대구","칠곡","북대구관음#1 T/L","2025년 칠곡전력지사 가공송전 순시점검 위탁공사"," 북대구-관음#1T/L 정밀점검 -  북대구-관음#1T/ No.1~55","2025-06-09 09:00","2025-06-18 18:00","2025-06-09 09:00","2025-06-18 18:00","연속"]
[629,"대구","칠곡","북대구관음#2 T/L","2025년 칠곡전력지사 가공송전 순시점검 위탁공사"," 북대구-관음#2T/L 정밀점검 -  북대구-관음#2T/L No.1~55","2025-06-18 09:00","2025-06-27 18:00","2025-06-18 09:00","2025-06-27 18:00","연속"]
[630,"대구","포항","아화건천#1 T/L","2024~25년도 포항전력지사 변전총액공사","아화, 건천S/S 아화-건천#1T/L 보호반 대체","2025-06-09 09:00","2025-06-11 18:00","취소","취소","연속"]
[631,"대구","포항","울주외동#1 T/L","2024~25년 포항전력지사 변전협력회사 공사","외동S/S 617 GIS 보통점검","2025-06-23 09:00","2025-06-23 14:00","2025-06-23 09:00","2025-06-23 14:00","연속"]
[632,"대구","포항","울주입실#2 T/L"," 신영일-천북 등 19개 T/L 추락방지장치 설치공사"," 울주-입실#2T/L 추락방지장치 설치공사","2025-06-04 07:00","2025-06-09 18:00","2025-06-04 07:00","2025-06-09 18:00","연속"]
[633,"대구","포항","건천천북#2 T/L","2024~25년도 포항전력지사 변전총액공사","건천-천북#2T/L LA,PT 보통점검","2025-06-04 09:00","2025-06-04 18:00","2025-06-04 09:00","2025-06-04 18:00","연속"]
[634,"경북","구미","동상주점촌#2 T/L","2025년 구미전력지사 154㎸ GIS 정밀점검 및 보통점검 공사","- GIS 보통점검 - 상부BUS 가스압력계 교체","2025-06-11 09:00","2025-06-11 18:00","2025-06-11 09:00","2025-06-11 18:00","연속"]
[635,"경북","구미","상주화동#1 T/L","2025년 가공송전 순시점검 위탁공사(정밀점검)"," 상주-화동#1T/L 정밀점검","2025-06-09 09:00","2025-06-13 18:00","취소","취소","연속"]
[636,"경북","구미","화동보은 T/L","2025년 가공송전 순시점검 위탁공사(초기점검)"," 화동-보은T/L NO.138~화동ST 초기점검","2025-06-13 09:00","2025-06-13 18:00","취소","취소","연속"]
[637,"경북","구미","상주화동#2 T/L","2025년 가공송전 순시점검 위탁공사(정밀점검)"," 상주-화동#2T/L 정밀점검","2025-06-16 09:00","2025-06-20 18:00","취소","취소","연속"]
[638,"경북","구미","화동영동 T/L","2024-2025년도 구미전력지사 가공송전협력회사 공사"," 화동-영동T/L 수평 추락방지장치 설치","2025-06-20 07:30","2025-06-27 18:00","취소","취소","연속"]
[639,"경북","영주","문경단양 T/L","2025년 영주전력지사  GIS 정밀점검공사","GIS 정밀점검 후 무부하가압","2025-06-07 09:00","2025-06-07 18:00","2025-06-07 09:00","2025-06-07 18:00","연속"]
[640,"경북","영주","예천점촌#1 T/L","2024-25년 영주전력지사 변전협력회사 총액공사","점촌S/S 예천-점촌#1T/L - 부분방전 개소 원인파악 예천S/S 예천-점촌#1T/L -COMFAIL 관련 보조계전기 교체","2025-06-17 09:00","2025-06-17 18:00","취소","취소","연속"]
[641,"경북","영주","신영주예천#2 T/L","24-25년 영주전력지사 변전협력회사 총액공사","- 신영주-예천#2T/L LA A,B,C 하자점검 - PT A 하자점검","2025-06-16 09:00","2025-06-16 18:00","취소","취소","연속"]
[642,"경북","영주","동상주점촌#2 T/L","2025년 영주전력지사  GIS 정밀점검공사","GIS 정밀점검 후 무부하가압","2025-06-18 09:00","2025-06-18 18:00","2025-06-18 09:00","2025-06-18 18:00","연속"]
[643,"경북","직할","현종산풍력평해#2 T/L","24~25년 경북직할가공송전협력회사공사","Gantry Tower 안전발판 설치","2025-06-30 12:00","2025-06-30 18:00","2025-06-30 12:00","2025-06-30 18:00","연속"]
[644,"경북","직할","풍산안동CC#2 T/L","24~25년 경북본부 직할 변전협력회사 공사","GIS 조작시험","2025-06-23 10:00","2025-06-23 15:00","취소","취소","연속"]
[645,"부산울산","동부산","명례장안 T/L","2025년 가공송전 순시점검 위탁공사"," 명례-장안T/L 정밀점검","2025-06-09 09:00","2025-06-11 18:00","2025-06-09 09:00","2025-06-11 18:00","연속"]
[646,"부산울산","동부산","명례장안 T/L","장안S/S  신규수용공사","170kV GIS 1CCT 증설 - 시험가압선로","2025-06-23 13:00","2025-06-24 18:00","2025-06-23 13:00","2025-06-24 18:00","연속"]
[647,"부산울산","동부산","명례장안 T/L","장안S/S  신규수용공사","170kV GIS 1CCT 증설 - 시험가압선로","2025-06-19 18:00","2025-06-20 18:00","2025-06-19 18:00","2025-06-20 18:00","연속"]
[648,"부산울산","동부산","명례장안 T/L","장안S/S  신규수용공사","170kV GIS 1CCT 증설 -시험가압선로","2025-06-12 18:00","2025-06-13 18:00","2025-06-12 18:00","2025-06-13 18:00","연속"]
[649,"부산울산","동부산","시랑좌동#2 T/L","좌동S/S  GIS 교체공사","좌동S/S 627,6100,6233 GIS 대체","2025-06-01 09:00","2025-07-03 18:00","2025-06-02 08:00","2025-07-03 18:00","연속"]
[650,"부산울산","동부산","좌동S/S #2 BUS","좌동S/S  GIS 교체공사","좌동S/S 627,6100,6233 GIS 2BUS, 2DS 부 대체","2025-06-19 09:00","2025-06-28 18:00","2025-06-19 16:00","2025-06-28 18:00","연속"]
[651,"부산울산","동부산","좌동S/S #1 BUS","좌동S/S  GIS 교체공사","좌동S/S 627,6100,6233 GIS 1BUS, 1DS, CB 부 대체","2025-06-05 09:00","2025-06-18 18:00","2025-06-06 08:30","2025-06-19 16:00","연속"]
[652,"부산울산","동부산","좌동S/S CB 6100","좌동S/S  GIS 교체공사","좌동S/S 627,6100,6233 GIS 대체","2025-06-01 09:00","2025-07-03 18:00","2025-06-01 09:00","2025-07-03 18:00","연속"]
[653,"부산울산","북부산","구포S/S CB 6100","24-25년 북부산전력지사 변전협력회사 공사","구포S/S 6100B/T 점검","2025-06-12 09:00","2025-06-13 18:00","2025-06-12 09:00","2025-06-12 18:00","연속"]
[654,"부산울산","북부산","북부산구포#3 T/L","24-25년 북부산전력지사 변전협력회사 공사","구포S/S 6100B/T 점검 관련 시험가압 선로","2025-06-13 17:00","2025-06-13 18:00","2025-06-12 17:00","2025-06-12 18:00","연속"]
[655,"부산울산","북부산","언양산막#2 T/L","25년 북부산전력지사 장기사용  GIS 대체공사","산막S/S 양산-산막#2T/L GIS 대체공사관련 시험가압선로","2025-06-12 17:00","2025-06-12 18:00","2025-06-12 17:00","2025-06-12 18:00","연속"]
[656,"부산울산","북부산","양산산막#2 T/L","25년 북부산전력지사 장기사용  GIS 대체공사","산막S/S 양산-산막#2T/L GIS 대체공사","2025-06-11 09:00","2025-06-25 18:00","2025-06-11 09:00","2025-06-25 18:00","연속"]
[657,"부산울산","북부산","서창산막#2 T/L","산막S/S  장기사용 GIS 대체공사","산막S/S  양산-산막#2T/L GIS 대체공사관련 안전이격선로","2025-06-13 09:00","2025-06-13 18:00","2025-06-11 09:00","2025-06-13 18:00","매일"]
[658,"부산울산","북부산","서창산막#2 T/L","산막S/S  장기사용 GIS 대체공사","산막S/S  양산-산막#2T/L GIS 대체공사관련 안전이격선로","2025-06-22 09:00","2025-06-22 18:00","2025-06-22 09:00","2025-06-22 18:00","연속"]
[659,"부산울산","북부산","언양산막#2 T/L","25년 북부산전력지사 장기사용  GIS 대체공사","산막S/S 양산-산막#2T/L GIS 대체공사관련 시험가압선로","2025-06-16 18:00","2025-06-17 18:00","2025-06-16 18:00","2025-06-17 18:00","연속"]
[660,"부산울산","북부산","양산삼랑진PP T/L","2024-2025년 북부산전력지사 가공송전협력회사 공사","압축인류클램프교체, SB댐퍼 설치 -No.0.01,6,12","2025-06-09 08:00","2025-06-09 18:00","취소","취소","연속"]
[661,"부산울산","북부산","북부산삼랑진PP T/L","2024-2025년 북부산전력지사 가공송전협력회사 공사","압축인류클램프교체, SB댐퍼 설치 안전이격확보휴전","2025-06-09 08:00","2025-06-09 18:00","취소","취소","연속"]
[662,"부산울산","북부산","북부산양산 T/L","25년 북부산전력지사  GIS 정밀점검","양산S/S 6133 GIS 정밀점검 -시험가압선로 : 북부산-양산T/L","2025-06-10 17:00","2025-06-10 18:00","2025-06-10 17:00","2025-06-10 18:00","연속"]
[663,"부산울산","북부산","양산산막#1 T/L","25년 북부산전력지사  GIS 정밀점검","양산S/S 양산-산막#1T/L GIS 정밀점검","2025-06-26 09:00","2025-07-27 18:00","2025-06-26 09:00","2025-07-27 18:00","연속"]
[664,"부산울산","북부산","북부산양산 T/L","25년 북부산전력지사  GIS 정밀점검","양산S/S 북부산-양산T/L GIS 정밀점검","2025-06-04 09:00","2025-06-05 18:00","2025-06-04 09:00","2025-06-05 18:00","연속"]
[665,"부산울산","북부산","양산산막#1 T/L","2024-2025년 북부산전력지사 가공송전협력회사 공사","고정형 폴리머 점퍼지지애자 설치 안전이격확보휴전","2025-06-10 08:00","2025-06-10 18:00","2025-06-10 08:00","2025-06-10 18:00","연속"]
[666,"부산울산","북부산","양산산막#2 T/L","2024-2025년 북부산전력지사 가공송전협력회사 공사","고정형 폴리머 점퍼지지애자 설치 No.9,24","2025-06-10 08:00","2025-06-10 18:00","2025-06-10 08:00","2025-06-10 18:00","연속"]
[667,"부산울산","북부산","서부산엄궁#1 T/L","24-25년 북부산전력지사 변전총액공사","엄궁S/S 서부산-엄궁#1T/L 조작시험","2025-06-10 09:00","2025-06-10 14:00","취소","취소","연속"]
[668,"부산울산","북부산","모라엄궁#2 T/L","24-25년 북부산전력지사 변전총액공사","엄궁S/S 모라-엄궁#1T/L 조작시험","2025-06-13 09:00","2025-06-13 18:00","2025-06-13 09:00","2025-06-13 18:00","연속"]
[669,"부산울산","북부산","서부산엄궁#2 T/L","24-25년 북부산전력지사 변전총액공사","엄궁S/S 서부산-엄궁#2T/L 조작시험","2025-06-10 14:00","2025-06-10 18:00","취소","취소","연속"]
[670,"부산울산","북부산","학장개금#1 T/L","24-25년 북부산전력지사 변전총액공사","학장S/S  학장-개금#1T/L GIS 보통점검","2025-06-17 09:00","2025-06-17 18:00","취소","취소","연속"]
[671,"부산울산","북부산","엄궁학장#1 T/L","24-25년 북부산전력지사 변전총액공사","학장S/S 엄궁-학장#1T/L GIS 보통점검","2025-06-04 09:00","2025-06-04 18:00","취소","취소","연속"]
[672,"부산울산","북부산","엄궁학장#2 T/L","24-25년 북부산전력지사 변전총액공사","학장S/S 엄궁-학장#2T/L GIS 보통점검","2025-06-05 09:00","2025-06-05 18:00","취소","취소","연속"]
[673,"부산울산","서부산","신녹산S/S #1 Sh.C CB","신녹산S/S 345kV #1M.Tr 증설공사","신녹산S/S  Sh.C 이설","2025-06-09 09:00","2025-07-11 18:00","2025-06-09 09:00","2025-07-11 18:00","연속"]
[674,"부산울산","서부산","신녹산명지#1 T/L","신녹산S/S 345kV #1M.Tr 증설공사"," 신녹산-명지#1T/L 이설","2025-06-16 09:00","2025-08-08 18:00","2025-06-16 09:00","2025-08-08 18:00","연속"]
[675,"부산울산","서부산","신녹산녹산#1 T/L","신녹산S/S 345kV #1M.Tr 증설공사"," Sh.C 설치(무부하 시험가압)","2025-06-28 18:00","2025-06-29 18:00","2025-06-28 18:00","2025-06-29 18:00","연속"]
[676,"부산울산","서부산","신녹산녹산#1 T/L","신녹산S/S 345kV #1M.Tr 증설공사"," 신녹산-명지#1T/L 철거 및 Sh.C 설치(무부하 시험가압)","2025-06-24 18:00","2025-06-25 18:00","2025-06-24 18:00","2025-06-25 18:00","연속"]
[677,"부산울산","서부산","신녹산녹산#1 T/L","신녹산S/S 345kV #1M.Tr 증설공사"," 신녹산-명지#1T/L 철거(무부하 시험가압)","2025-06-18 18:00","2025-06-19 18:00","2025-06-18 18:00","2025-06-19 18:00","연속"]
[678,"부산울산","울산","반천언양#2 T/L","동부산전력 가공송전협력회사 공사","추락방지장치 설치","2025-06-05 07:00","2025-06-05 18:00","2025-06-05 07:00","2025-06-05 18:00","연속"]
[679,"부산울산","울산","반천언양#1 T/L","동부산전력 가공송전협력회사 공사","추락방지장치 설치","2025-06-11 07:00","2025-06-11 18:00","2025-06-16 07:00","2025-06-16 18:00","연속"]
[680,"부산울산","울산","방어진영남TP#1 T/L","25년 울산전력지사 개폐장치 정밀점검 공사","- #3M.Tr 1차 GIS 정밀점검 시험가압(1HR)","2025-06-05 17:00","2025-06-05 18:00","2025-06-05 17:00","2025-06-05 18:00","연속"]
[681,"부산울산","울산","남울산신온산#1 T/L","2025년 가공송전 순시점검 위탁공사(울산)"," 남울산-신온산#1T/L 초기점검 - 구간 : 5~16호 - 병가 : 5~16호(345kV 울주-울산TP#2T/L 15~26호)","2025-06-04 08:00","2025-06-05 18:00","2025-06-04 08:00","2025-06-05 18:00","연속"]
[682,"부산울산","울산","신온산S/S SEC CB 60610","25년 울산전력지사 변전협력회사 공사","- GIS 보통점검","2025-06-11 09:00","2025-06-11 18:00","2025-06-11 09:00","2025-06-11 18:00","연속"]
[683,"부산울산","울산","울산영남TP#2 T/L","25년 울산전력지사 개폐장치 정밀점검 공사"," MAIN Tr G1 1차 GIS(6133) 시험가압","2025-06-14 17:00","2025-06-14 18:00","2025-06-14 17:00","2025-06-14 18:00","연속"]
[684,"부산울산","울산","온산처용#1 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산 #2T/L 철거 및 임시 BUS TIE 설치","2025-06-19 16:00","2025-06-20 16:00","2025-06-19 16:00","2025-06-20 16:00","연속"]
[685,"부산울산","울산","온산처용#1 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산 #2T/L 철거 및 임시 BUS TIE 설치","2025-06-26 16:00","2025-06-27 18:00","2025-06-26 16:00","2025-06-27 18:00","연속"]
[686,"부산울산","울산","온산처용#2 T/L","2024-2025년 울산전력지사 가공송전협력회사 공사","[불량애자교체 공사] 1) 내용: 온산-처용#2 4호 상단 파손애자(1장) 교체 2) 시행 : 한일전력(주)","2025-06-20 08:00","2025-06-20 12:00","2025-06-20 08:00","2025-06-20 12:00","연속"]
[687,"부산울산","울산","온산처용#1 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산 #2T/L 철거 및 임시 BUS TIE 설치","2025-06-13 16:00","2025-06-14 16:00","2025-06-13 16:00","2025-06-14 16:00","연속"]
[688,"부산울산","울산","온산처용#1 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산 #2T/L 철거 및 임시 BUS TIE 설치","2025-06-09 16:00","2025-06-09 17:00","2025-06-09 16:00","2025-06-09 17:00","연속"]
[689,"부산울산","울산","울산매암 T/L","울산S/S  BASF T/L GIS 대체공사","- BASF T/L GIS 대체공사","2025-06-01 15:00","2025-06-02 15:00","2025-06-01 18:00","2025-06-02 18:00","연속"]
[690,"부산울산","울산","울산매암 T/L","울산S/S  BASF T/L GIS 대체공사","- BASF T/L GIS 대체공사 시험가압 24Hr","2025-06-04 15:00","2025-06-05 18:00","2025-06-06 18:00","2025-06-07 20:00","연속"]
[691,"부산울산","울산","신울산웅촌#2 T/L","25년 울산전력지사 개폐장치 정밀점검 공사","#2Sh.C MAIN GIS 정밀점검(6279) 시험가압","2025-06-12 17:00","2025-06-12 18:00","2025-06-12 17:00","2025-06-12 18:00","연속"]
[692,"부산울산","울산","신울산웅촌#1 T/L","25년 울산전력지사 개폐장치 정밀점검 공사","#1Sh.C MAIN GIS 정밀점검(6179) 시험가압","2025-06-10 17:00","2025-06-10 18:00","2025-06-10 17:00","2025-06-10 18:00","연속"]
[693,"부산울산","울산","직동반천#1 T/L","동부산전력 가공송전협력회사 공사","추락방지장치 설치","2025-06-05 07:00","2025-06-05 18:00","2025-06-05 07:00","2025-06-05 18:00","연속"]
[694,"부산울산","울산","직동반천#2 T/L","동부산전력 가공송전협력회사 공사","추락방지장치 설치","2025-06-11 07:00","2025-06-11 18:00","2025-06-16 07:00","2025-06-16 18:00","연속"]
[695,"부산울산","직할","양정범천 T/L","25년 직할 상반기 170kV GIS 정밀점검공사","범천S/S 고속철도#1T/L GIS 정밀점검 시험가압용","2025-06-19 16:00","2025-06-19 17:00","2025-06-19 16:00","2025-06-19 17:00","연속"]
[696,"부산울산","직할","양정범천 T/L","25년 직할 상반기 170kV GIS 정밀점검공사","범천S/S 고속철도#2T/L GIS 정밀점검 시험가압용","2025-06-17 16:00","2025-06-17 17:00","2025-06-17 16:00","2025-06-17 17:00","연속"]
[697,"경남","김해송변전부","김해어방#2 T/L","김해S/S #4M.Tr 1차 GIS 정밀점검(시험가압용)","김해S/S #4M.Tr 1차 GIS 정밀점검(시험가압용)","2025-06-05 16:00","2025-06-05 18:00","2025-06-05 16:00","2025-06-05 18:00","연속"]
[698,"경남","김해송변전부","김해어방#1 T/L","김해S/S  BUS-TIE GIS 정밀점검(시험가압용)","김해S/S  BUS-TIE GIS 정밀점검(시험가압용)","2025-06-01 16:00","2025-06-01 18:00","2025-06-01 16:00","2025-06-01 18:00","연속"]
[699,"경남","김해송변전부","김해어방#2 T/L","김해S/S  BUS-TIE GIS 정밀점검(일시절체용)","김해S/S  BUS-TIE GIS 정밀점검(일시절체용) - BUS TIE GIS 정밀점검중이기 때문에 모선절체 불가 / 시험가압 조작전, 모선 절체를 위한 차단기 일시개방","2025-06-01 15:00","2025-06-01 16:00","2025-06-01 15:00","2025-06-01 16:00","연속"]
[700,"경남","김해송변전부","매리김해#1 T/L","매리S/S 매리-김해#1T/L GIS 보통점검","매리S/S 매리-김해#1T/L GIS 보통점검 (병행)김해S/S 매리-김해#1T/L 조작시험","2025-06-21 09:30","2025-06-21 17:30","2025-06-21 09:30","2025-06-21 17:30","연속"]
[701,"경남","김해송변전부","삼계어방#1 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","폴리머지지애자 교체 공사 안전이격","2025-06-08 07:00","2025-06-08 18:00","2025-06-08 07:00","2025-06-08 18:00","연속"]
[702,"경남","김해송변전부","주촌삼계#2 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","폴리머지지애자 교체 공사 안전이격","2025-06-08 07:00","2025-06-08 18:00","2025-06-08 07:00","2025-06-08 18:00","연속"]
[703,"경남","김해송변전부","신김해진례#2 T/L","신김해S/S 신김해-진례#2T/L GIS 정밀점검","신김해S/S 신김해-진례#2T/L GIS 정밀점검 (병행) LA,PT 보통점검","2025-06-14 08:00","2025-06-15 18:00","취소","취소","연속"]
[704,"경남","김해송변전부","신김해진례#1 T/L","신김해S/S 신김해-진례#1T/L GIS 정밀점검","신김해S/S 신김해-진례#1T/L GIS 정밀점검 (병행) LA,PT 보통점검","2025-06-07 08:00","2025-06-08 18:00","취소","취소","연속"]
[705,"경남","김해송변전부","신김해삼정#2 T/L"," 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사"," 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","2025-06-14 07:00","2025-06-14 18:00","2025-06-14 07:00","2025-06-14 18:00","연속"]
[706,"경남","김해송변전부","신김해주촌#1 T/L"," 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사"," 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","2025-06-14 07:00","2025-06-14 18:00","2025-06-14 07:00","2025-06-14 18:00","연속"]
[707,"경남","김해송변전부","진영한림정#1 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","피뢰기 설치 및추락방지장치 설치 공사","2025-06-07 07:00","2025-06-07 12:00","2025-06-07 07:00","2025-06-07 12:00","연속"]
[708,"경남","김해송변전부","진례진영#2 T/L","진영S/S  진례-진영#2T/L ES 조작불량 조치","진영S/S  진례-진영#2T/L ES 조작불량 조치 - 선로측 ES 조작함 내부 보조계전기 교체","2025-06-22 09:30","2025-06-22 17:30","2025-06-22 09:30","2025-06-22 17:30","연속"]
[709,"경남","김해송변전부","진영수산#2 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","추락방지장치 설치 공사","2025-06-07 07:00","2025-06-07 18:00","2025-06-07 07:00","2025-06-07 18:00","연속"]
[710,"경남","김해송변전부","진영한림정#2 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","추락방지장치 설치 공사","2025-06-07 12:00","2025-06-07 18:00","2025-06-07 12:00","2025-06-07 18:00","연속"]
[711,"경남","김해송변전부","한림정삼계#2 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","추락방지장치 설치 및 폴리머지지애자 교체 공사","2025-06-07 07:00","2025-06-08 18:00","2025-06-07 07:00","2025-06-08 18:00","매일"]
[712,"경남","직할","녹공마천#2 T/L"," 녹공-마천#2T/L 피뢰기 열화진단","25~26년 지중송전 협력회사 공사  녹공-마천#2T/L 피뢰기 열화진단","2025-06-04 09:00","2025-06-05 18:00","취소","취소","매일"]
[713,"경남","진주","진주개양#1 T/L"," 진주-개양#1T/L EBA 절연유 채유","25~26년 지중송전 협력회사 공사  진주-개양#1T/L EBA 절연유 채유","2025-06-17 09:00","2025-06-18 18:00","취소","취소","매일"]
[714,"경남","진주","진주개양#2 T/L"," 진주-개양#2T/L EBA 절연유 채유","25~26년 지중송전 협력회사 공사  진주-개양#2T/L EBA 절연유 채유","2025-06-19 09:00","2025-06-20 18:00","취소","취소","매일"]
[715,"경남","진주","함양거창#2 T/L","거창S/S  함양-거창#2T/L GIS 조작시험 등","거창S/S  함양-거창#2T/L GIS 조작시험 및 LA(A,B,C) 하자점검","2025-06-26 10:00","2025-06-26 16:00","2025-06-20 10:00","2025-06-20 16:00","연속"]
[716,"경남","진주","의령함양 T/L","의령S/S  의령-함양T/L GIS 조작시험 등","의령S/S  의령-함양T/L GIS 조작시험 및 LA(A,B,C) 하자점검, PT 보통점검","2025-06-27 10:00","2025-06-27 16:00","취소","취소","연속"]
[717,"경남","진주","동진주진주#2 T/L","진주S/S  동진주-진주#2T/L GIS 하자점검","진주S/S  동진주-진주#2T/L GIS 하자점검","2025-06-14 10:00","2025-06-14 17:00","2025-06-14 10:00","2025-06-14 17:00","연속"]
[718,"경남","진주","진주개양#1 T/L","진주S/S  진주-개양#1T/L GIS 하자점검","진주S/S  진주-개양#1T/L GIS 하자점검","2025-06-15 10:00","2025-06-15 17:00","2025-06-15 10:00","2025-06-15 17:00","연속"]
[719,"경남","진주","태금하동#1 T/L"," 하동-남해 #2T/L, 태금-하동T/L 폴리머지지애자 설치"," 하동-남해 #2T/L, 태금-하동T/L 폴리머지지애자 신규 설치(매일) - 19기 설치","2025-06-09 07:00","2025-06-13 18:00","2025-06-09 07:00","2025-06-13 18:00","매일"]
[720,"경남","통영","고성거류 T/L"," 고성분기T/L 추락방지장치 설치공사"," 고성분기T/L 추락방지장치 설치공사","2025-06-07 07:00","2025-06-07 18:00","2025-06-07 07:00","2025-06-07 18:00","연속"]
[721,"경남","통영","거류거제#1 T/L"," 거류-거제#1 T/L 추락방지장치 설치공사"," 거류-거제#1 T/L 추락방지장치 설치공사","2025-06-15 07:00","2025-06-15 18:00","2025-06-15 07:00","2025-06-15 18:00","연속"]
[722,"경남","통영","고성거류 T/L"," 고성()-거류 T/L 수평추락방지장치 설치공사"," 고성()-거류 T/L 수평추락방지장치 설치공사","2025-06-16 07:00","2025-06-17 18:00","2025-06-16 07:00","2025-06-17 18:00","매일"]
[723,"경남","통영","거류통영#2 T/L"," 거류-통영#2 T/L 수평추락방지장치 설치공사"," 거류-통영#2 T/L 수평추락방지장치 설치공사","2025-06-28 07:00","2025-06-29 18:00","2025-06-28 07:00","2025-06-29 18:00","매일"]
[724,"경남","통영","신고성거류#1 T/L"," 고성-통영복합#1T/L 추락방지장치 설치공사"," 고성-통영복합#1T/L 추락방지장치 설치공사(병가)","2025-06-08 07:00","2025-06-08 18:00","2025-06-08 07:00","2025-06-08 18:00","연속"]
[725,"경남","통영","거류거제#2 T/L"," 거류-거제#2 T/L 추락방지장치 설치공사"," 거류-거제#2 T/L 추락방지장치 설치공사","2025-06-21 07:00","2025-06-22 18:00","2025-06-21 07:00","2025-06-22 18:00","매일"]
[726,"경남","통영","거류거제#1 T/L","거제S/S 인출 송전선로 임시선로 구성공사(요청자시행, 1차)"," 거제S/S 인출 송전선로 임시선로 구성공사(요청자시행) ○  거류-거제#1T/L 78호 ~ 가철탑 2호 전력선 설치 ○  거류-거제#1T/L 78 ~ 79호 전력선 철거","2025-06-01 07:00","2025-06-01 18:00","2025-06-01 07:00","2025-06-01 18:00","연속"]
[727,"경남","통영","통영거제#2 T/L","거제S/S 인출 송전선로 임시선로 구성공사(요청자시행, 2차)"," 거제S/S 인출 송전선로 임시선로 구성공사(요청자시행) ○  통영-거제#2T/L 70호 ~ 가철탑 2호 전력선(중,하단) 설치 ○  통영-거제#2T/L 70 ~ 71호 전력선 철거","2025-06-08 07:00","2025-06-08 18:00","2025-06-08 07:00","2025-06-08 18:00","연속"]
[728,"경남","통영","거류거제#1 T/L","거제S/S 인출 송전선로 임시선로 구성공사(요청자시행, 2차)"," 거제S/S 인출 송전선로 임시선로 구성공사(요청자시행) ○  거류-거제#1T/L 78호 ~ 가철탑 2호 전력선 설치 ○  거류-거제#1T/L 78 ~ 79호 전력선 철거","2025-06-08 07:00","2025-06-08 18:00","2025-06-08 07:00","2025-06-08 18:00","연속"]
[729,"경남","통영","통영거제#1 T/L"," 통영-거제#1T/L 피뢰기 열화진단","25~26년 지중송전 협력회사 공사  통영-거제#1T/L 피뢰기 열화진단","2025-06-14 09:00","2025-06-14 12:00","2025-06-14 09:00","2025-06-14 12:00","연속"]
[730,"경남","통영","통영거제#2 T/L"," 통영-거제#2T/L 피뢰기 열화진단","25~26년 지중송전 협력회사 공사  통영-거제#2T/L 피뢰기 열화진단","2025-06-14 12:00","2025-06-14 16:00","2025-06-14 12:00","2025-06-14 16:00","연속"]
[731,"경남","통영","통영거제#2 T/L","거제S/S 인출 송전선로 임시선로 구성공사(요청자시행, 1차)"," 거제S/S 인출 송전선로 임시선로 구성공사(요청자시행) ○  통영-거제#2T/L 70호 ~ 가철탑 2호 전력선(중,하단) 설치 ○  통영-거제#2T/L 70 ~ 71호 전력선 철거","2025-06-01 07:00","2025-06-01 18:00","2025-06-01 07:00","2025-06-01 18:00","연속"]
[732,"경남","통영","신고성고성 T/L"," 고성분기T/L 추락방지장치 설치공사"," 고성분기T/L 추락방지장치 설치공사","2025-06-14 07:00","2025-06-14 18:00","2025-06-14 07:00","2025-06-14 18:00","연속"]
[733,"경남","통영","신고성거류#3 T/L"," 신고성-거류#3 T/L 수평추락방지장치 설치공사"," 신고성-거류#3 T/L 수평추락방지장치 설치공사","2025-06-02 07:00","2025-06-05 18:00","취소","취소","매일"]
[734,"경남","통영","신고성거류#3 T/L"," 신고성-거류#3 T/L 수평추락방지장치 설치공사"," 신고성-거류#3 T/L 수평추락방지장치 설치공사","2025-06-09 07:00","2025-06-13 18:00","취소","취소","매일"]
[735,"경남","통영","신고성고성 T/L"," 신고성고성 T/L 수평추락방지장치 설치공사"," 신고성고성 T/L 수평추락방지장치 설치공사","2025-06-18 07:00","2025-06-20 18:00","취소","취소","매일"]
[736,"경남","통영","신고성고성 T/L"," 신고성고성 T/L 수평추락방지장치 설치공사"," 신고성고성 T/L 수평추락방지장치 설치공사","2025-06-23 07:00","2025-06-27 18:00","취소","취소","매일"]
[737,"경남","통영","고성통영CC#1 T/L"," 고성분기T/L 추락방지장치 설치공사"," 고성분기T/L 추락방지장치 설치공사","2025-06-14 07:00","2025-06-14 18:00","2025-06-14 07:00","2025-06-14 18:00","연속"]
[738,"경남","통영","고성통영CC#1 T/L"," 고성-통영복합#1T/L 추락방지장치 설치공사"," 고성-통영복합#1T/L 추락방지장치 설치공사","2025-06-08 07:00","2025-06-08 18:00","2025-06-08 07:00","2025-06-08 18:00","연속"]
[739,"경남","통영","고성통영CC#2 T/L"," 고성분기T/L 추락방지장치 설치공사"," 고성분기T/L 추락방지장치 설치공사","2025-06-07 07:00","2025-06-07 18:00","2025-06-07 07:00","2025-06-07 18:00","연속"]
[740,"경남","함안","가야사봉#2 T/L"," 가야-사봉#2T/L 수평 추락방지장치 설치"," 가야-사봉#2T/L 40~52기(13기) 수평형 추락방지장치(와이어형) 설치","2025-06-07 07:00","2025-06-08 18:00","취소","취소","매일"]
[741,"경남","함안","가야사봉#1 T/L"," 가야-사봉#1T/L 수평 추락방지장치 설치"," 가야-사봉#1T/L 40~52기(13기) 수평형 추락방지장치(와이어형) 설치","2025-06-07 07:00","2025-06-08 18:00","취소","취소","매일"]
[742,"경남","함안","가야사봉#1 T/L"," 가야-사봉#1T/L 수평 추락방지장치 설치"," 가야-사봉#1T/L 40~52기(13기) 수평형 추락방지장치(와이어형) 설치","2025-06-14 07:00","2025-06-15 18:00","취소","취소","매일"]
[743,"경남","함안","가야사봉#2 T/L"," 가야-사봉#2T/L 수평 추락방지장치 설치"," 가야-사봉#2T/L 40~52기(13기) 수평형 추락방지장치(와이어형) 설치","2025-06-14 07:00","2025-06-15 18:00","취소","취소","매일"]
[744,"경남","함안","부북밀양#2 T/L","밀양S/S  부북밀양#2 T/L GIS 보통점검","밀양S/S  부북밀양#2 T/L GIS 보통점검","2025-06-24 09:30","2025-06-24 17:30","2025-06-24 09:30","2025-06-24 17:30","연속"]
[745,"경남","함안","부북밀양#1 T/L","밀양S/S  부북밀양#1 T/L GIS 보통점검","밀양S/S  부북밀양#1 T/L GIS 보통점검","2025-06-23 09:30","2025-06-23 17:30","2025-06-23 09:30","2025-06-23 17:30","연속"]
[746,"경남","함안","중리가야#1 T/L"," 중리-가야#1T/L 피뢰기 설치공사"," 중리-가야#1T/L 11~52호(42기) 피뢰기 설치","2025-06-17 07:00","2025-06-20 18:00","2025-06-17 07:00","2025-06-20 18:00","매일"]
[747,"경남","함안","신마산중리#2 T/L"," 신마산-중리#2T/L 피뢰기 설치공사"," 신마산-중리#2T/L 9~32호(24기) 피뢰기 설치","2025-06-16 07:00","2025-06-17 18:00","2025-06-16 07:00","2025-06-17 18:00","매일"]
[748,"경남","함안","중리가야#2 T/L"," 중리-가야#2T/L 피뢰기 설치공사"," 중리-가야#2T/L 44호(1기) 피뢰기 설치 및 4회선 병가철탑(수직배열) 동시휴전","2025-06-18 07:00","2025-06-18 18:00","취소","취소","연속"]
[749,"경남","함안","창녕초동#1 T/L","초동S/S  창녕초동#1 T/L GIS 보통점검","초동S/S  창녕초동#1 T/L GIS 보통점검","2025-06-11 09:30","2025-06-11 17:30","2025-06-11 09:30","2025-06-11 17:30","연속"]