{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":23,"n_cols":12,"rows_kept":23,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2],[2,11,3,11]]}
["2025년도 7월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신안성신가평 T/L"," 신안성-신가평 등 12개T/L 추락방지시설 설치공사"," 신안성-신가평T/L 고광도 항공장애등 설치 : No.131,132,146,147","2025-07-21 07:00","2025-07-25 18:00","취소","취소","연속"]
[2,"대전세종충남","서산","당진T/P M.Tr","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압불가) 당진화력S/S  #1Tie.Tr 정밀점검","2025-07-15 09:00","2025-08-15 18:00","취소","취소","연속"]
[3,"대전세종충남","서산","신서산S/S #3 M.Tr","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압불가) 신서산S/S  #3M.Tr 정밀점검","2025-07-01 09:00","2025-08-01 18:00","취소","취소","연속"]
{"$rows_empty":15}
[{"$nulls":5}," "]

{"sheet":"345설비","index":1,"n_rows":193,"n_cols":12,"rows_kept":193,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2025년도 7월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","중부S/S #1 M.Tr","2025년 중부전력지사 변전협력회사 공사","PT점검","2025-07-14 10:00","2025-07-15 18:00","2025-07-14 10:00","2025-07-15 18:00","연속"]
[2,"남서울","강남","신양재S/S #4 Sh.R CB","24-25년도 강남전력지사 변전협력회사 총액공사","- 신양재S/S #74Bay B/F PNL 교체공사 - #4Sh.R용 CB 내부부품 교체공사","2025-07-21 09:00","2025-07-26 18:00","2025-07-21 09:00","2025-07-26 18:00","연속"]
[3,"남서울","강남","신양재S/S #2 BUS","24-25년도 강남전력지사 변전협력회사 총액공사","- #4Sh.R용 CB 내부부품 교체공사 무부하가압","2025-07-25 20:00","2025-07-26 18:00","2025-07-25 20:00","2025-07-26 18:00","연속"]
[4,"남서울","강남","신양재S/S #2 M.Tr","24-25년도 강남전력지사 변전협력회사 총액공사","- #4Sh.R용 CB 내부부품 교체공사 무부하가압","2025-07-25 20:00","2025-07-26 18:00","2025-07-25 20:00","2025-07-26 18:00","연속"]
[5,"남서울","강남","신성남신양재#2 T/L","24-25년도 강남전력지사 변전협력회사 총액공사","- #4Sh.R용 CB 내부부품 교체공사 무부하가압","2025-07-25 20:00","2025-07-26 18:00","2025-07-25 20:00","2025-07-26 18:00","연속"]
[6,"남서울","강남","신양재S/S #3 Sh.R CB","24-25년도 강남전력지사 변전협력회사 총액공사","신양재S/S #74Bay B/F PNL 교체공사","2025-07-21 09:00","2025-07-25 18:00","2025-07-21 09:00","2025-07-25 18:00","연속"]
[7,"남서울","동서울","곤지암동서울#2 T/L","'25년 동서울전력지사 가공송전 순시점검 위탁공사"," 곤지암-동서울T/L 지장이설구간 초기점검","2025-07-30 09:00","2025-07-30 18:00","취소","취소","연속"]
[8,"남서울","동서울","곤지암동서울#1 T/L","24~25년도 동서울전력지사 가공송전 협력회사 공사","피뢰기 설치공사","2025-07-22 09:00","2025-07-29 18:00","취소","취소","연속"]
[9,"남서울","동서울","동서울S/S #3 Sh.R CB","2024-2025년도 동서울전력지사 변전협력회사 총액공사","동서울S/S #Sh.R 인출 CB 개폐제어기 점검(7A79)","2025-07-01 09:00","2025-07-02 18:00","2025-07-01 09:00","2025-07-02 18:00","연속"]
[10,"남서울","영등포","서서울신광명#2 T/L"," 서서울-신광명T/L 임시철탑 이설 및 보강공사","No.25 철탑보강, No.26 임시이설, No.27 철탑 인클로징","2025-07-08 09:00","2025-07-13 18:00","2025-07-08 09:00","2025-07-13 18:00","연속"]
[11,"남서울","영등포","서서울신광명#1 T/L"," 서서울-신광명T/L 임시철탑 이설 및 보강공사","No.25 철탑보강, No.26 임시이설, No.27 철탑 인클로징","2025-07-01 09:00","2025-07-07 18:00","2025-07-01 09:00","2025-07-07 18:00","연속"]
[12,"인천","부평","서인천C/C #1 Sh.R CB","서인천복합S/Y  #1 Sh.R 1차 GIS 정밀점검","서인천복합S/Y  #1 Sh.R 1차 GIS 정밀점검","2025-07-07 09:00","2025-07-11 18:00","2025-07-07 09:00","2025-07-11 18:00","연속"]
[13,"인천","부평","신가좌S/S #2 M.Tr","신가좌S/S 345㎸ 용량부족 GIS 교체공사","신가좌S/S 75BUS 무부하 가압용(24H)","2025-07-26 18:00","2025-07-27 18:00","취소","취소","연속"]
[14,"인천","부평","신가좌S/S #3 M.Tr","신가좌S/S 345㎸ 용량부족 GIS 교체공사","신가좌S/S 75BUS 무부하 가압용(24H)","2025-07-26 18:00","2025-07-27 18:00","취소","취소","연속"]
[15,"인천","부평","신가좌S/S #4 M.Tr","신가좌S/S 345㎸ 용량부족 GIS 교체공사","신가좌S/S 75BUS 무부하 가압용(24H)","2025-07-26 18:00","2025-07-27 18:00","취소","취소","연속"]
[16,"경기북부","고양","신덕은S/S #3 M.Tr","24-25년 고양전력 변전협력회사 공사","신덕은S/S  #3M.Tr GPT 보통점검","2025-07-21 09:00","2025-07-21 18:00","취소","취소","연속"]
[17,"경기북부","고양","신덕은S/S #2 M.Tr","24-25년 고양전력 변전협력회사 공사","신덕은S/S  #2M.Tr 3차 LA 보통점검","2025-07-07 09:00","2025-07-08 18:00","취소","취소","연속"]
[18,"경기북부","고양","신덕은S/S #1 M.Tr","24-25년 고양전력 변전협력회사 공사","신덕은S/S  #1M.Tr 본체 및 3차 LA 보통점검","2025-07-16 09:00","2025-07-18 18:00","취소","취소","연속"]
[19,"경기북부","구리","미금S/S #2 Sh.R CB"," 미금 용량부족 차단기 대체공사(#1,2Sh.R 직결)"," #1,2Sh.R - 미금성동#1T/L 직결","2025-07-07 09:00","2025-07-25 18:00","2025-07-07 09:00","2025-07-25 18:00","연속"]
[20,"경기북부","구리","미금S/S #5 Sh.R CB"," 미금 용량부족 차단기 대체공사(#1,2Sh.R 직결)"," #1,2Sh.R - 미금성동#1T/L 직결","2025-07-07 09:00","2025-07-11 18:00","2025-07-07 09:00","2025-07-11 18:00","연속"]
[21,"경기북부","구리","미금S/S #1 Sh.R CB"," 미금 용량부족 차단기 대체공사(#1,2Sh.R 직결)"," #1,2Sh.R - 미금성동#1T/L 직결","2025-07-07 09:00","2025-07-25 18:00","2025-07-07 09:00","2025-07-25 18:00","연속"]
[22,"경기북부","구리","미금성동#1 T/L"," 미금 용량부족 차단기 대체공사(#1,2Sh.R 직결)"," #1,2Sh.R - 미금성동#1T/L 직결","2025-07-07 09:00","2025-07-25 18:00","2025-07-07 09:00","2025-07-25 18:00","연속"]
[23,"경기북부","구리","미금S/S CB 7079"," 미금 용량부족 차단기 대체공사(#1,2Sh.R 직결)"," #1,2Sh.R - 미금성동#1T/L 직결","2025-07-07 09:00","2025-07-11 18:00","2025-07-07 09:00","2025-07-11 18:00","연속"]
[24,"경기북부","구리","신가평S/S #70 BUS","신가평S/S #70BUS 벨로우즈 교체","신가평S/S #70BUS 벨로우즈 교체(4EA)","2025-07-01 09:00","2025-07-11 18:00","2025-07-01 09:00","2025-07-11 18:00","연속"]
[25,"경기북부","직할","양주S/S #3 M.Tr","양주S/S 동두천CC-양주T/L 증설공사(무부하용)"," CB 증설 2대, CLR 설치 2조","2025-07-13 09:00","2025-07-13 18:00","2025-07-13 09:00","2025-07-13 18:00","연속"]
[26,"경기북부","직할","신파주양주#2 T/L","양주S/S 동두천CC-양주T/L 증설공사(무부하용)"," CB 증설 2대, CLR 설치 2조","2025-07-13 09:00","2025-07-13 18:00","2025-07-13 09:00","2025-07-13 18:00","연속"]
[27,"경기북부","직할","양주S/S CB 7300","양주S/S 동두천CC-양주T/L 증설공사"," CB 증설 2대, CLR 설치 2조 (CB 7300)","2025-07-12 09:00","2025-12-31 18:00","2025-07-12 09:00","2025-12-31 18:00","연속"]
[28,"경기북부","직할","양주S/S #2 BUS","양주S/S 동두천CC-양주T/L 증설공사"," CB 증설 2대, CLR 설치 2조","2025-07-12 09:00","2025-07-13 18:00","2025-07-12 09:00","2025-07-13 18:00","연속"]
[29,"경기북부","직할","양주S/S STATCOM CB","양주S/S STATCOM 제어케이블 교체","양주S/S STATCOM 컨버터블럭용 제어케이블 임시접속분 신품 교체 (철거, 설치)","2025-07-09 09:00","2025-07-11 18:00","2025-07-09 09:00","2025-07-11 18:00","연속"]
[30,"경기북부","직할","양주S/S CB 7700","양주S/S STATCOM 제어케이블 교체","양주S/S STATCOM 컨버터블럭용 제어케이블 임시접속분 신품 교체 (철거, 설치)","2025-07-09 09:00","2025-07-11 18:00","2025-07-09 09:00","2025-07-11 18:00","연속"]
[31,"경기북부","직할","양주S/S CB 7500","양주S/S 동두천CC-양주T/L 증설공사"," CB 증설 2대, CLR 설치 2조","2025-07-28 09:00","2025-12-31 18:00","2025-07-28 09:00","2025-12-31 18:00","연속"]
[32,"경기","동부","곤지암여주복합#2 T/L","추락방지장치 설치공사(곤지암여주CC #2)","곤지암여주CC #2T/L 추락방지장치 설치 80기(잔여 7기)","2025-07-31 07:00","2025-07-31 18:00","취소","취소","연속"]
[33,"경기","동부","곤지암여주복합#1 T/L","추락방지장치 설치공사(곤지암여주CC #1)","곤지암여주CC #1T/L 추락방지장치 설치 80기(잔여 18기)","2025-07-24 07:00","2025-07-25 18:00","취소","취소","연속"]
[34,"경기","동부","신충주여주복합#2 T/L","추락방지장치 설치공사(신충주여주복합#2T/L)","신충주여주복합#2T/L 추락방지장치 설치 39기","2025-07-28 07:00","2025-07-30 18:00","취소","취소","연속"]
[35,"경기","동부","신제천신충주T#1 T/L","추락방지장치 설치공사(신제천-여주CC)","신제천 여주CC 추락방지장치 설치 39기","2025-07-21 07:00","2025-07-23 18:00","취소","취소","연속"]
[36,"경기","성남","신성남S/S CB 7271","2025년 성남전력 변전협력회사 총액공사","7291-1ES B상 코일교체","2025-07-02 09:00","2025-07-02 18:00","2025-07-02 09:00","2025-07-02 18:00","연속"]
[37,"경기","성남","신성남S/S STATCOM CB","2025년 성남전력 statcom 보통점검 공사","statcom 보통점검","2025-07-28 09:00","2025-08-08 18:00","2025-07-28 09:00","2025-08-08 18:00","연속"]
[38,"경기","성남","신성남S/S CB 7072","2025년 성남전력 statcom 보통점검 공사","statcom 보통점검","2025-07-28 09:00","2025-08-08 18:00","2025-07-28 09:00","2025-08-08 18:00","연속"]
[39,"경기","성남","신성남S/S CB 7000","2025년 성남전력 statcom 보통점검 공사","statcom 보통점검","2025-07-28 09:00","2025-08-08 18:00","2025-07-28 09:00","2025-08-08 18:00","연속"]
[40,"경기","성남","신안성S/S CB 7B79","2025년 성남전력 변전협력회사 총액공사","7B79 gis 조작시험","2025-07-04 09:00","2025-07-04 18:00","2025-07-04 09:00","2025-07-04 18:00","연속"]
[41,"경기","성남","신안성S/S CB 7B71","2025년 성남전력 변전협력회사 총액공사","7B71 gis 보통점검, 절연열화","2025-07-04 09:00","2025-07-04 18:00","2025-07-04 09:00","2025-07-04 18:00","연속"]
[42,"경기","성남","신안성S/S CB 7979","2025년 성남전력 변전협력회사 총액공사","7979 gis 조작시험","2025-07-03 09:00","2025-07-03 18:00","2025-07-03 09:00","2025-07-03 18:00","연속"]
[43,"경기","성남","신안성S/S CB 7971","2025년 성남전력 변전협력회사 총액공사","7971 gis 보통점검, 절연열화","2025-07-03 09:00","2025-07-03 18:00","2025-07-03 09:00","2025-07-03 18:00","연속"]
[44,"경기","성남","신안성S/S CB 7771","2025년 성남전력 변전협력회사 총액공사","7771 gis 보통점검, 절연열화","2025-07-02 09:00","2025-07-02 18:00","2025-07-02 09:00","2025-07-02 18:00","연속"]
[45,"경기","평택","고덕S/S CB 7300","2025년 평택전력 변전협력회사 총액공사(고덕SS 7300)","고덕S/S  7300 C상 GIS 유압조작기 누유보수","2025-07-09 09:00","2025-07-09 14:00","2025-07-09 09:00","2025-07-09 14:00","연속"]
[46,"경기","평택","고덕S/S CB 7672","2025년 평택전력 변전협력회사 총액공사(고덕SS 7672)","고덕S/S  7672 C상 GIS 유압조작기 누유보수","2025-07-09 14:00","2025-07-09 18:00","2025-07-09 14:00","2025-07-09 18:00","연속"]
[47,"강원","강릉","신양양S/S #2 M.Tr","신양양S/S STATCOM용 #2S.Tr 사용전검사","STATCOM용 #2S.Tr 사용전검사(#2M.Tr 3차 SIS 포함)","2025-07-01 08:00","2025-07-01 17:00","2025-07-01 08:00","2025-07-01 17:00","연속"]
[48,"충북","직할","신진천S/S #3 M.Tr","24-25년 충북직할 변전협력회사 총액공사","신진천변전소  #3M.Tr 보통점검","2025-07-02 09:00","2025-07-04 18:00","2025-07-02 09:00","2025-07-04 18:00","연속"]
[49,"충북","충주","신제천S/S #3 M.Tr","신제천S/S  #3 M.Tr CT비 최대탭 정정","신제천S/S  #3 M.Tr CT비 최대탭 정정","2025-07-03 14:00","2025-07-03 17:00","2025-07-03 14:00","2025-07-03 17:00","연속"]
[50,"충북","충주","신충주S/S #4 M.Tr","신충주S/S 154kV 충주에코파크T/L 증설공사","신충주S/S 154kV 충주에코파크T/L 증설공사(#1BUS 무부하 가압용)","2025-07-03 09:00","2025-07-04 18:00","2025-07-03 09:00","2025-07-04 18:00","연속"]
[51,"충북","충주","신제천신충주T#1 T/L"," 신용인-동서울 등 16개 T/L 추락방지장치 설치공사"," 신제천-여주CC T/L 추락방지장치 설치공사 - 신제천-여주CC 연계선로로 인한 휴전(신충주 T분기 실작업 없음)","2025-07-28 07:00","2025-07-30 18:00","취소","취소","연속"]
[52,"대전세종충남","대전","신계룡청양 T/L","[송전][오전만][즉시가압O] 신옥천-청양 등 추락방지설치공사","[송전][오전만][즉시가압O] 신옥천-청양 등 추락방지설치공사","2025-07-14 07:00","2025-07-22 11:00","2025-07-14 07:00","2025-07-22 11:00","매일"]
[53,"대전세종충남","서산","당진T/P CB 7272","당진화력S/S  차단기 조작시험","(즉시가압 가능) 당진화력S/S  2호기 1차 차단기 개폐타임 측정","2025-07-03 09:00","2025-07-03 18:00","2025-07-03 09:00","2025-07-03 18:00","연속"]
[54,"대전세종충남","서산","북당진현대제철 T/L"," 신송산분기T/L 건설공사","No.70 전선 이동(가철탑→본철탑) No.69∼No.71 전선 교체","2025-07-15 07:00","2025-07-27 18:00","2025-07-15 07:00","2025-07-27 18:00","연속"]
[55,"대전세종충남","서산","북당진S/S CB 7300","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 북당진S/S 7300 GIS 보통점검","2025-07-10 09:30","2025-07-11 18:00","2025-07-10 09:30","2025-07-11 18:00","연속"]
[56,"대전세종충남","서산","북당진S/S CB 7600","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 북당진S/S 7671 GIS 보통점검 - 7671 GIS 보호기능 없으므로, 7600 GIS 동시휴전 필요","2025-07-01 09:30","2025-07-02 18:00","2025-07-01 09:30","2025-07-02 18:00","연속"]
[57,"대전세종충남","서산","북당진S/S CB 7271","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 북당진S/S 7271 GIS 보통점검","2025-07-03 09:30","2025-07-04 18:00","2025-07-03 09:30","2025-07-04 18:00","연속"]
[58,"대전세종충남","서산","북당진S/S CB 7371","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 북당진S/S 7371 GIS 보통점검","2025-07-08 09:30","2025-07-09 18:00","2025-07-08 09:30","2025-07-09 18:00","연속"]
[59,"대전세종충남","서산","북당진S/S CB 7671","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 북당진S/S 7671 GIS 보통점검","2025-07-01 09:30","2025-07-02 18:00","2025-07-01 09:30","2025-07-02 18:00","연속"]
[60,"대전세종충남","서산","신당진개폐소현대제철 T/L"," 신송산분기T/L 건설공사","No.70 전선 이동(가철탑→본철탑) No.69∼No.71 전선 교체","2025-07-01 07:00","2025-07-13 18:00","2025-07-01 07:00","2025-07-13 18:00","연속"]
[61,"대전세종충남","서산","신당진개폐소 CB 7A72","신당진S/S  차단기 조작시험","(즉시가압 가능) 신당진S/S  신당진-연락#1T/L 차단기 개폐타임 측정","2025-07-09 09:00","2025-07-09 18:00","2025-07-09 09:00","2025-07-09 18:00","연속"]
[62,"대전세종충남","서산","신당진개폐소현대제철 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#1T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-태안화력#1T/L 병가선로,  신당진개폐소-태안화력#1T/L 휴전 미승인시 휴전 취소 요청","2025-07-28 08:00","2025-07-28 18:00","2025-07-28 08:00","2025-07-28 18:00","연속"]
[63,"대전세종충남","서산","신당진개폐소태안TP#1 T/L","24~25 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#1T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-현대제철T/L 병가선로,  신당진개폐소-현대제철T/L 휴전 미승인시 휴전 취소 요청","2025-07-28 08:00","2025-07-28 18:00","2025-07-28 08:00","2025-07-28 18:00","연속"]
[64,"대전세종충남","서산","신당진개폐소북당진 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.126~127(1경간) *즉시가압가능(20분이내) * 신당진개폐소-태안화력#2T/L 병가선로,  신당진개폐소-태안화력#2T/L 휴전 미승인시 휴전 취소 요청","2025-07-29 08:00","2025-07-29 13:00","2025-07-29 08:00","2025-07-29 13:00","연속"]
[65,"대전세종충남","서산","신당진개폐소태안TP#2 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-북당진T/L 병가 및  신당진개폐소-현대제철 교차구간,  신당진개폐소-북당진T/L 및 신당진개폐소-현대제철 휴전 미승인시 휴전 취소 요청","2025-07-29 08:00","2025-07-29 18:00","2025-07-29 08:00","2025-07-29 18:00","연속"]
[66,"대전세종충남","서산","신당진개폐소현대제철 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.125~126(1경간) *즉시가압가능(20분이내) * 신당진개폐소-태안화력#2T/L 교차선로,  신당진개폐소-태안화력#2T/L 휴전 미승인시 휴전 취소 요청","2025-07-29 13:00","2025-07-29 18:00","2025-07-29 13:00","2025-07-29 18:00","연속"]
[67,"대전세종충남","서산","태안T/P CB 7671","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 태안화력S/S 7671 GIS 보통점검","2025-07-15 09:30","2025-07-16 18:00","2025-07-15 09:30","2025-07-16 18:00","연속"]
[68,"대전세종충남","세종","세종S/S #2 BUS","세종S/S  #1,2Sh.R 증설공사","○  GIS 주모선 도킹 ○ #2BUS 인터록시험 ○ #2BUS 무부하가압 ○ 신설기기 상확인","2025-07-07 09:00","2025-07-11 15:00","2025-07-07 09:00","2025-07-11 15:00","연속"]
[69,"대전세종충남","천안","신온양서서울#1 T/L","(6월 취소시)신온양S/S  #78Bay B/F PNL 대체","(6월 취소시)(즉시가압불가)신온양S/S  #78Bay 노후 B/F PNL 대체","2025-07-21 09:00","2025-07-25 18:00","2025-07-21 09:00","2025-07-25 18:00","연속"]
[70,"대전세종충남","천안","신온양S/S #4 M.Tr","(6월 취소시)신온양S/S  #77Bay B/F PNL 대체","(6월 취소시)(즉시가압불가)(장기미교체 대상)신온양S/S  #77Bay 노후 B/F PNL 대채","2025-07-14 09:00","2025-07-18 18:00","2025-07-14 09:00","2025-07-18 18:00","연속"]
[71,"대전세종충남","천안","신온양서서울#2 T/L","(6월 취소시)신온양S/S  #77Bay B/F PNL 대체","(6월 취소시)(즉시가압불가)(장기미교체 대상)신온양S/S  #77Bay 노후 B/F PNL 대체","2025-07-14 09:00","2025-07-18 18:00","2025-07-14 09:00","2025-07-18 18:00","연속"]
[72,"대전세종충남","천안","신온양S/S #4 M.Tr","(6월 취소시) 신온양S/S  #4M.Tr 부싱절연유 채유","(6월 취소시)(즉시가압 가능) 신온양S/S  #4M.Tr 부싱절연유 채유","2025-07-14 09:00","2025-07-14 18:00","2025-07-07 09:00","2025-07-07 18:00","연속"]
[73,"대전세종충남","천안","신온양S/S CB 7671","신온양S/S 청양-신온양#2T/L 7671 CB 개폐타임 측정","(즉시가압가능)신온양S/S 청양-신온양#2T/L 7671 CB 개폐타임 측정","2025-07-08 14:00","2025-07-08 18:00","2025-07-08 14:00","2025-07-08 18:00","연속"]
[74,"대전세종충남","천안","신온양S/S CB 7600","신온양S/S 청양-신온양#2T/L TIE 7600 CB 개폐타임 측정","(즉시가압 가능)신온양S/S 청양-신온양#2T/L TIE 7600 CB 개폐타임 측정","2025-07-08 09:00","2025-07-08 14:00","2025-07-08 09:00","2025-07-08 14:00","연속"]
[75,"대전세종충남","천안","신온양S/S CB 7800","'25년 천안P/O GIS 정밀 및 보통점검 공사","(즉시가압가능)신온양S/S  신온양서서울#1T/L-신온양신탕정#2T/L TIE GIS(7800) 보통점검","2025-07-04 09:00","2025-07-04 18:00","2025-07-04 09:00","2025-07-04 18:00","연속"]
[76,"대전세종충남","천안","신온양S/S CB 7900","'25년 천안P/O GIS 정밀 및 보통점검 공사","(즉시가압가능)신온양S/S  신온양-신탕정#1T/L TIE GIS(7900) 보통점검","2025-07-03 09:00","2025-07-03 18:00","2025-07-03 09:00","2025-07-03 18:00","연속"]
[77,"대전세종충남","천안","신온양신탕정#2 T/L","(6월 취소시)  신온양신탕정#2T/L 보호반 대체","(6월 취소시)(즉시가압불가)(장기미교체대상)신온양S/S #78B/F 보호반,신온양, 신탕정S/S  신온양신탕정#2T/L 보호반 대체 +(신온양-서서울#1T/L 휴전 취소시)  신온양신탕정#2T/L 보호반 대체","2025-07-21 09:00","2025-07-25 18:00","2025-07-21 09:00","2025-07-25 18:00","연속"]
[78,"대전세종충남","천안","아산S/S CB 7700","'25년 천안P/O GIS 정밀 및 보통점검 공사","(즉시가압가능)아산S/S  #3M.Tr 1차 BUS-TIE GIS(7700) 보통점검","2025-07-02 09:00","2025-07-02 18:00","2025-07-02 09:00","2025-07-02 18:00","연속"]
[79,"대전세종충남","청양","보령T/P CB 7672","청양P/O 변전협력 총액공사(보령화력 7672 보통)","청양P/O 변전협력 총액공사(보령화력 7672 보통)","2025-07-08 09:00","2025-07-08 18:00","2025-07-08 09:00","2025-07-08 18:00","연속"]
[80,"대전세종충남","청양","보령T/P CB 7171","[변전총액] 청양P/O 변전협력 총액공사","보령화력  #1M.Tr 1차 GIS 보통점검 (7171)","2025-07-07 09:00","2025-07-07 18:00","2025-07-07 09:00","2025-07-07 18:00","연속"]
[81,"대전세종충남","청양","청양S/S CB 7300","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  청양신탕정#1-청양군산#2T/L TIE GIS 차단기 조작시험 (7300)","2025-07-11 09:00","2025-07-11 14:00","2025-07-11 09:00","2025-07-11 14:00","연속"]
[82,"대전세종충남","청양","청양S/S CB 7272","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  청양-보령복합T/L GIS 차단기 조작시험 (7272)","2025-07-10 14:00","2025-07-10 18:00","2025-07-10 14:00","2025-07-10 18:00","연속"]
[83,"대전세종충남","청양","청양S/S CB 7400","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  신옥천청양-청양군산#1T/L TIE GIS 차단기 조작시험 (7400)","2025-07-14 09:00","2025-07-14 14:00","2025-07-14 09:00","2025-07-14 14:00","연속"]
[84,"대전세종충남","청양","청양S/S CB 7471","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  신옥천-청양T/L GIS 차단기 조작시험 (7471)","2025-07-14 14:00","2025-07-14 18:00","2025-07-14 14:00","2025-07-14 18:00","연속"]
[85,"대전세종충남","청양","청양S/S CB 7571","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  청양-신탕정#2T/L GIS 차단기 조작시험 (7571)","2025-07-15 14:00","2025-07-15 18:00","2025-07-15 14:00","2025-07-15 18:00","연속"]
[86,"대전세종충남","청양","청양S/S CB 7100","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  신계룡청양-청양보령화력#1T/L TIE GIS 차단기 조작시험 (7100)","2025-07-09 09:00","2025-07-09 14:00","2025-07-09 09:00","2025-07-09 14:00","연속"]
[87,"대전세종충남","청양","청양S/S CB 7172","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  청양-보령화력#1T/L GIS 차단기 조작시험 (7172)","2025-07-09 14:00","2025-07-09 18:00","2025-07-09 14:00","2025-07-09 18:00","연속"]
[88,"대전세종충남","청양","청양S/S CB 7271","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  청양-신보령T/L GIS 차단기 조작시험 (7271)","2025-07-16 09:00","2025-07-16 14:00","2025-07-16 09:00","2025-07-16 14:00","연속"]
[89,"대전세종충남","청양","청양S/S CB 7672","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  청양-보령화력#2T/L GIS 차단기 조작시험 (7672)","2025-07-16 14:00","2025-07-16 18:00","2025-07-16 14:00","2025-07-16 18:00","연속"]
[90,"대전세종충남","청양","청양S/S SEC CB 70710","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  #70-#71 SEC GIS 차단기 조작시험 (70-71)","2025-07-17 09:00","2025-07-17 14:00","2025-07-17 09:00","2025-07-17 14:00","연속"]
[91,"대전세종충남","청양","청양S/S SEC CB 75760","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  #75-#76 SEC GIS 차단기 조작시험 (75-76)","2025-07-17 14:00","2025-07-17 18:00","2025-07-17 14:00","2025-07-17 18:00","연속"]
[92,"대전세종충남","청양","청양S/S #1 M.Tr","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  #1M.Tr 1,2차 부싱유채유 및 기타설비 점검","2025-07-01 09:00","2025-07-03 18:00","2025-07-01 09:00","2025-07-03 18:00","연속"]
[93,"대전세종충남","청양","청양S/S CB 7500","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  청양신탕정#2T/L-TIE GIS 차단기 조작시험 (7500)","2025-07-15 09:00","2025-07-15 14:00","2025-07-15 09:00","2025-07-15 14:00","연속"]
[94,"대전세종충남","청양","청양S/S CB 7200","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  청양신보령-청양보령복합T/L TIE GIS 차단기 조작시험 (7200)","2025-07-10 14:00","2025-07-10 18:00","2025-07-10 14:00","2025-07-10 18:00","연속"]
[95,"대전세종충남","청양","청양S/S CB 7372","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  청양-군산#2T/L GIS 차단기 조작시험 (7372)","2025-07-11 14:00","2025-07-11 18:00","2025-07-11 14:00","2025-07-11 18:00","연속"]
[96,"전북","군산","군산S/S #1 Sh.R CB","군산변전소  GIS 대체공사(기기) (중복)","○ 362kV GIS 4000A 40kA × 10CB(50kA) 교체 ○ 기타 부대공사 × 1식","2025-07-22 18:00","2025-07-23 18:00","2025-07-22 18:00","2025-07-23 18:00","연속"]
[97,"전북","군산","군산S/S #75 BUS","군산변전소  GIS 대체공사","○ 362kV GIS 40kA 4000A × 10CB(PT Bay 포함) 철거 ○ 362kV GIS 50kA 4000A × 10CB(PT Bay 포함) 설치 ○ 기초 BaseChennel × 4Bay분 설치 ○ 기타부대공사 × 1식","2025-07-24 09:00","2025-08-02 18:00","2025-07-24 09:00","2025-08-02 18:00","연속"]
[98,"전북","군산","군산S/S #70 BUS","군산변전소  GIS 대체공사","○ 362kV GIS 40kA 4000A × 10CB(PT Bay 포함) 철거 ○ 362kV GIS 50kA 4000A × 10CB(PT Bay 포함) 설치 ○ 기초 BaseChennel × 4Bay분 설치 ○ 기타부대공사 × 1식","2025-07-14 09:00","2025-07-23 18:00","2025-07-14 09:00","2025-07-23 18:00","연속"]
[99,"전북","김제","신김제한빛NP#1 T/L"," 신김제- 한빛 #1T/L GIS 차단기 조작시험","차단기 조작시험","2025-07-11 09:00","2025-07-11 11:00","2025-07-11 09:00","2025-07-11 11:00","연속"]
[100,"전북","직할","신남원의령#1 T/L","'25년 가공송전 순시점검 위탁공사(중복)","○ 정밀점검 : No.137~180","2025-07-14 08:00","2025-07-17 18:00","2025-07-14 08:00","2025-07-17 18:00","연속"]
[101,"전북","직할","신남원광양#1 T/L","신남원S/S 75BAY B/F PNL 개조작업","- 75BAY  #2M.Tr 증설에 따른 B/F PNL 개조","2025-07-28 09:00","2025-08-01 18:00","2025-07-28 09:00","2025-08-01 18:00","연속"]
[102,"전북","직할","신옥천신남원#2 T/L"," 신옥천-신남원 등 3개T/L 수평추락방지시설 설치공사"," 신옥천-신남원#1T/L 1~178호","2025-07-18 07:30","2025-07-28 17:00","2025-07-18 07:30","2025-07-28 17:00","연속"]
[103,"전북","직할","신남원의령#2 T/L","'25년 가공송전 순시점검 위탁공사(중복)","○ 정밀점검 : No.137~180","2025-07-21 08:00","2025-07-25 18:00","2025-07-21 08:00","2025-07-25 18:00","연속"]
[104,"전북","직할","신남원신광주#1 T/L","'24~'25년 전북직할 가공송전 협력회사 공사(계속)","○  신남원-신광주T/L 피뢰기 설치공사(계속) - No.1~115","2025-07-11 07:30","2025-07-18 18:00","2025-07-11 07:30","2025-07-18 18:00","매일"]
[105,"전북","직할","신옥천신남원#1 T/L"," 신옥천-신남원 등 3개T/L 수평추락방지시설 설치공사"," 신옥천-신남원#1T/L 1~178호","2025-07-07 07:30","2025-07-17 17:00","2025-07-07 07:30","2025-07-17 17:00","연속"]
[106,"전북","직할","신남원신광주#2 T/L","'24~'25년 전북직할 가공송전 협력회사 공사(계속)","○  신남원-신광주T/L 피뢰기 설치공사(계속) - No.1~115","2025-07-19 07:30","2025-07-26 18:00","2025-07-19 07:30","2025-07-26 18:00","매일"]
[107,"광주전남","강진","신강진S/S #1 M.Tr","2024-2025년 강진전력지사 변전협력회사 공사","부싱 절연유 분석결과 불량(정상 기준 농도 초과)에 따른 추적분석(3개월/1회) 시행 가. 신강진S/S #1M.Tr  A, B, C 부싱 절연유 채유 나. 신강진S/S #1M.Tr 154kV A, B, C 부싱 절연유 채유 ※ 거래소 요청 시 휴전일정 협의 가능","2025-07-01 13:30","2025-07-01 18:00","2025-07-01 13:30","2025-07-01 18:00","연속"]
[108,"광주전남","강진","신강진S/S #2 M.Tr","2024-2025년 강진전력지사 변전협력회사 공사","부싱 절연유 분석결과 불량(정상 기준 농도 초과)에 따른 추적분석(3개월/1회) 시행 가. 신강진S/S #2M.Tr  C 부싱 절연유 채유 나. 신강진S/S #2M.Tr 154kV A, B, C 부싱 절연유 채유 ※ 거래소 요청 시 휴전일정 협의 가능","2025-07-01 08:00","2025-07-01 13:00","2025-07-01 08:00","2025-07-01 13:00","연속"]
[109,"광주전남","강진","신강진S/S #3 M.Tr","2024-2025년 강진전력지사 변전협력회사 공사","가. 신강진S/S #3M.Tr, B, C 보통점검 나. 신강진S/S #3M.Tr 2차 LA A,B,C 보통점검 ※ 거래소 요청 시 휴전일정 협의 가능","2025-07-14 08:00","2025-07-15 18:00","2025-07-14 08:00","2025-07-15 18:00","연속"]
[110,"광주전남","강진","신강진S/S #1 M.Tr","2024-2025년 강진전력지사 변전협력회사 공사","가. 신강진S/S #1M.Tr,B,C상 보통점검 ※ 거래소 요청 시 휴전일정 협의 가능","2025-07-16 08:00","2025-07-17 18:00","2025-07-16 08:00","2025-07-17 18:00","연속"]
[111,"광주전남","강진","신강진S/S CB 7271","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","-362kV GIS 보통점검","2025-07-24 17:00","2025-07-24 22:00","2025-07-24 17:00","2025-07-24 22:00","연속"]
[112,"광주전남","강진","신강진광양#1 T/L","'24~25년 강진전력지사 변전협력회사 공사","신강진S/S  74Bay B/F반 교체","2025-07-07 08:00","2025-07-18 18:00","2025-07-07 08:00","2025-07-18 18:00","연속"]
[113,"광주전남","강진","신강진S/S #3 M.Tr","'24~25년 강진전력지사 변전협력회사 공사","신강진S/S  74Bay B/F반 교체","2025-07-07 08:00","2025-07-18 18:00","2025-07-07 08:00","2025-07-18 18:00","연속"]
[114,"광주전남","강진","신화순신강진#1 T/L","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","-362kV GIS 보통점검","2025-07-22 17:00","2025-07-22 22:00","2025-07-22 17:00","2025-07-22 22:00","연속"]
[115,"광주전남","강진","신화순신강진#2 T/L","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","-362kV GIS 보통점검","2025-07-23 17:00","2025-07-23 22:00","2025-07-23 17:00","2025-07-23 22:00","연속"]
[116,"광주전남","광주","신광주S/S CB 7600","피앤씨테크 보호반 성능개선","신광주S/S  76Bay B/F PNL 보호반 성능개선","2025-07-14 08:00","2025-07-14 18:00","2025-07-14 08:00","2025-07-14 18:00","연속"]
[117,"광주전남","광주","신광주S/S CB 7672","피앤씨테크 보호반 성능개선","신광주S/S  76Bay B/F PNL 보호반 성능개선","2025-07-14 08:00","2025-07-14 18:00","2025-07-14 08:00","2025-07-14 18:00","연속"]
[118,"광주전남","광주","신광주S/S #2 M.Tr","'25년 광주전력지사 변전협력회사 공사","신광주S/S #2M.Tr 초기점검","2025-07-14 09:00","2025-07-16 18:00","2025-07-14 09:00","2025-07-16 18:00","연속"]
[119,"광주전남","광주","신광주S/S #2 BUS","장기사용  #2BUS 모선보호반 교체","장기사용  #2BUS 모선보호반 교체","2025-07-17 08:00","2025-07-19 18:00","취소","취소","연속"]
[120,"광주전남","광주","신남원신광주#2 T/L","2024-2025년도 광주전력지사 변전협력회사 총액공사","신광주SS 신남원-신광주2TL LA, CVT A,B,C상 보통점검","2025-07-17 09:00","2025-07-17 18:00","취소","취소","연속"]
[121,"광주전남","광주","신광주S/S #3 M.Tr","3M.Tr 변압기보호반 장기사용 교체","3M.Tr 변압기보호반 장기사용 교체","2025-07-21 08:00","2025-07-25 18:00","2025-07-21 08:00","2025-07-25 18:00","연속"]
[122,"광주전남","광주","신남원신광주#1 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 조류착지방지장치 설치 시행 - 신남원-신광주#1 116~164호","2025-07-01 08:00","2025-07-07 18:00","취소","취소","매일"]
[123,"광주전남","광주","신광주S/S CB 7200","2024-2025년도 광주전력지사 변전협력회사 총액공사","신광주변전소 72BAY B/F PNL 대체","2025-07-21 09:00","2025-07-25 18:00","2025-07-21 09:00","2025-07-25 18:00","연속"]
[124,"광주전남","광주","신광주S/S CB 7671","피앤씨테크 보호반 성능개선","신광주S/S  76Bay B/F PNL 보호반 성능개선","2025-07-14 08:00","2025-07-14 18:00","2025-07-14 08:00","2025-07-14 18:00","연속"]
[125,"광주전남","광주","신광주S/S #1 BUS","장기사용  #1BUS 모선보호반 교체","장기사용  #1BUS 모선보호반 교체","2025-07-14 08:00","2025-07-16 18:00","취소","취소","연속"]
[126,"광주전남","광주","신광주S/S #1 Sh.R CB","'25년 광주전력지사 변전협력회사 공사","신광주S/S  #1Sh.R 송유풍냉식 냉각장치 세정","2025-07-10 09:00","2025-07-10 18:00","2025-07-10 09:00","2025-07-10 18:00","연속"]
[127,"광주전남","광주","신남원신광주#2 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 조류착지방지장치 설치 시행 - 신남원-신광주#2 116~164호","2025-07-08 08:00","2025-07-14 18:00","취소","취소","매일"]
[128,"광주전남","광주","신광주S/S CB 7271","2024-2025년도 광주전력지사 변전협력회사 총액공사","신광주변전소 72BAY B/F PNL 대체","2025-07-21 09:00","2025-07-25 18:00","2025-07-21 09:00","2025-07-25 18:00","연속"]
[129,"광주전남","광주","신화순S/S #3 M.Tr","2024-2025년도 광주전력지사 변전협력공사 총액공사","신화순변전소 75BAY B/F반 PNL 대체 - 7200, 7572, 6433, 4384, 4389-1,2CB 휴전 - (신)B/F PNL 설치 및 제어케이블 결선 - (주)PNL 철거 - 조작 및 연동시험 등","2025-07-21 08:00","2025-07-25 18:00","2025-07-21 08:00","2025-07-25 18:00","연속"]
[130,"광주전남","광주","신화순S/S #2 M.Tr","2024-2025년도 광주전력지사 변전협력회사 총액공사","신화순변전소 2MTr 1,2차 LA A,B,C상 하자점검","2025-07-04 08:00","2025-07-04 18:00","2025-07-04 08:00","2025-07-04 18:00","연속"]
[131,"광주전남","광주","신화순S/S #1 Sh.R CB","'25년 광주전력지사 변전협력회사 공사","신화순S/S  #1Sh.R 송유풍냉식 냉각장치 세정","2025-07-07 09:00","2025-07-07 18:00","2025-07-07 09:00","2025-07-07 18:00","연속"]
[132,"광주전남","목포","신남원한빛NP#1 T/L","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","- 362kV GIS(40kA 4000A #2BUS) 철거 × 1식 - 362kV GIS(63kA 6300A #2BUS) 설치 × 1식 - 제어케이블 분리 및 결선 × 1식 - 기타 부대공사","2025-07-11 19:00","2025-07-15 06:00","취소","취소","매일"]
[133,"광주전남","목포","한빛1NP한빛2NP#1 T/L","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","- 362kV GIS(40kA 4000A #2BUS) 철거 × 1식 - 362kV GIS(63kA 6300A #2BUS) 설치 × 1식 - 제어케이블 분리 및 결선 × 1식 - 기타 부대공사","2025-07-21 19:00","2025-07-25 06:00","취소","취소","매일"]
[134,"광주전남","목포","신남원한빛NP#2 T/L","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","- 362kV GIS(40kA 4000A #2BUS) 철거 × 1식 - 362kV GIS(63kA 6300A #2BUS) 설치 × 1식 - 제어케이블 분리 및 결선 × 1식 - 기타 부대공사","2025-07-04 19:00","2025-07-11 06:00","취소","취소","매일"]
[135,"광주전남","목포","한빛1NP한빛2NP#2 T/L","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","- 362kV GIS(40kA 4000A #2BUS) 철거 × 1식 - 362kV GIS(63kA 6300A #2BUS) 설치 × 1식 - 제어케이블 분리 및 결선 × 1식 - 기타 부대공사","2025-07-15 19:00","2025-07-19 06:00","취소","취소","매일"]
[136,"광주전남","순천","광양CC여수TP#1 T/L"," 광양CC-여수TPT/L 폴리머점퍼지지애자 설치공사","광양CC-여수TP #1T/L 폴리머점퍼지지애자 설치","2025-07-14 07:00","2025-07-17 18:00","2025-07-14 07:00","2025-07-17 18:00","매일"]
[137,"광주전남","순천","광양CC여수TP#2 T/L"," 광양CC-여수TPT/L 폴리머점퍼지지애자 설치공사","광양CC-여수TP #2T/L 폴리머점퍼지지애자 설치","2025-07-18 07:00","2025-07-18 18:00","2025-07-18 07:00","2025-07-18 18:00","연속"]
[138,"광주전남","순천","광양여수TP T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양1, 광양-여수TP 병가)","2025-07-22 07:00","2025-07-25 18:00","2025-07-22 07:00","2025-07-25 18:00","매일"]
[139,"광주전남","순천","신남원광양#1 T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양1, 광양-여수TP 병가)","2025-07-22 07:00","2025-07-25 18:00","취소","취소","매일"]
[140,"광주전남","순천","광양하동TP#2 T/L"," 광양-하동TP T/L 추락방지시설 설치공사","수평추락방지 설치","2025-07-28 07:00","2025-07-31 18:00","취소","취소","매일"]
[141,"광주전남","순천","신남원광양#2 T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양2, 광양-율촌CC 병가)","2025-07-28 07:00","2025-07-31 18:00","2025-07-28 07:00","2025-07-31 18:00","매일"]
[142,"광주전남","순천","광양S/S #2 M.Tr","25년 순천전력지사 부싱절연유 채유","광양S/S #2M.Tr 절연유 이상 관련 부싱절연유 채유","2025-07-29 09:00","2025-07-29 18:00","2025-07-29 09:00","2025-07-29 18:00","연속"]
[143,"광주전남","순천","광양율촌CC T/L"," 광양-여수TPT/L 폴리머점퍼지지애자 설치공사","광양-율촌CC 폴리머점퍼지지애자 설치 (광양율촌CC,신남원광양2 병가)","2025-07-30 07:00","2025-07-31 18:00","2025-07-30 07:00","2025-07-31 18:00","매일"]
[144,"광주전남","순천","신남원광양#2 T/L"," 광양-여수TPT/L 폴리머점퍼지지애자 설치공사","광양-율촌CC 폴리머점퍼지지애자 설치 (광양율촌CC,신남원광양2 병가)","2025-07-30 07:00","2025-07-31 18:00","2025-07-30 07:00","2025-07-31 18:00","매일"]
[145,"광주전남","순천","광양여수TP T/L"," 광양-여수TPT/L 폴리머점퍼지지애자 설치공사","광양-여수TP 폴리머점퍼지지애자 설치","2025-07-21 07:00","2025-07-25 18:00","2025-07-21 07:00","2025-07-25 18:00","매일"]
[146,"광주전남","순천","신강진광양#2 T/L"," 신강진-광양 T/L 추락방지시설 설치공사","수평추락방지시설 설치","2025-07-14 07:00","2025-07-18 18:00","2025-07-14 07:00","2025-07-18 18:00","매일"]
[147,"광주전남","순천","광양율촌CC T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양2, 광양-율촌CC 병가)","2025-07-28 07:00","2025-07-31 18:00","2025-07-28 07:00","2025-07-31 18:00","매일"]
[148,"광주전남","순천","신강진광양#1 T/L"," 신강진-광양 T/L 추락방지시설 설치공사","수평추락방지시설 설치","2025-07-07 07:00","2025-07-11 18:00","2025-07-07 07:00","2025-07-11 18:00","매일"]
[149,"광주전남","순천","율촌CC여수TP T/L"," 광양-여수TPT/L 폴리머점퍼지지애자 설치공사","율촌CC-여수TP 폴리머점퍼지지애자 설치","2025-07-28 07:00","2025-07-29 18:00","2025-07-28 07:00","2025-07-29 18:00","매일"]
[150,"대구","달성","고령의령#2 T/L","[TEST] 고령S/S 7471 CB부 정밀 무부하가압선로","[TEST] 고령S/S 7471 CB부 정밀 무부하가압선로","2025-07-16 17:00","2025-07-16 18:00","2025-07-18 17:00","2025-07-18 18:00","연속"]
[151,"대구","달성","고령의령#1 T/L","[TEST] 고령S/S 7371 CB부 정밀 무부하가압선로","[TEST] 고령S/S 7371 CB부 정밀 무부하가압선로","2025-07-23 17:00","2025-07-23 18:00","2025-07-25 17:00","2025-07-25 18:00","연속"]
[152,"대구","달성","고령의령#1 T/L","[TEST] 고령S/S 7300 CB부 정밀 무부하가압선로","[TEST] 고령S/S 7300 CB부 정밀 무부하가압선로","2025-07-19 17:00","2025-07-19 18:00","취소","취소","연속"]
[153,"대구","달성","대구S/S #1 BUS","#1SH.R GIS 정밀점검 관련 무부하선로 휴전","#1SH.R GIS 정밀점검 관련 무부하선로 휴전","2025-07-11 17:00","2025-07-11 18:00","2025-07-11 17:00","2025-07-11 18:00","연속"]
[154,"대구","달성","신경산대구#1 T/L","#1SH.R GIS 정밀점검 관련 무부하선로 휴전","#1SH.R GIS 정밀점검 관련 무부하선로 휴전","2025-07-11 17:00","2025-07-11 18:00","2025-07-11 17:00","2025-07-11 18:00","연속"]
[155,"대구","달성","대구S/S #1 Sh.R CB","#1SH.R GIS 정밀점검","#1SH.R GIS 정밀점검","2025-07-07 09:00","2025-07-11 18:00","2025-07-07 09:00","2025-07-11 18:00","연속"]
[156,"대구","달성","대구S/S #2 BUS","#2SH.R GIS 정밀점검 관련 무부하선로 휴전","#2SH.R GIS 정밀점검 관련 무부하선로 휴전","2025-07-05 07:00","2025-07-05 08:00","2025-07-05 07:00","2025-07-05 08:00","연속"]
[157,"대구","달성","북경남대구#1 T/L","#2SH.R GIS 정밀점검 관련 무부하선로 휴전","#2SH.R GIS 정밀점검 관련 무부하선로 휴전","2025-07-05 07:00","2025-07-05 08:00","2025-07-05 07:00","2025-07-05 08:00","연속"]
[158,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S  주변압기측 현대화 공사","철공진 관려 주변압기 3차측 회로 변경","2025-07-03 09:00","2025-07-03 18:00","취소","취소","연속"]
[159,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S  주변압기측 현대화 공사","철공진 관려 주변압기 3차측 회로 변경","2025-07-04 09:00","2025-07-04 18:00","취소","취소","연속"]
[160,"대구","칠곡","서대구S/S #3 M.Tr"," 서대구S/S 현대화 관련 전력구공사","(안전확보) 8회선 전력구 1,025m 설치, 환기구 12개소 등","2025-07-07 08:00","2025-07-15 18:00","2025-07-07 08:00","2025-07-15 18:00","연속"]
[161,"대구","칠곡","서대구S/S #2 M.Tr"," 서대구S/S 현대화 관련 전력구공사","(안전확보) 8회선 전력구 1,025m 설치, 환기구 12개소 등","2025-07-21 08:00","2025-07-29 18:00","2025-07-21 08:00","2025-07-29 18:00","연속"]
[162,"대구","포항","신포항신월성NP#4 T/L","2024~25년도 포항전력지사 변전협력회사 공사","신월성S/Y, 신포항S/S 신포항-신월성#4T/L 보호반 대체공사 신포항S/S 72Bay B/F 대체공사","2025-07-22 09:00","2025-08-05 18:00","2025-07-22 09:00","2025-08-05 18:00","연속"]
[163,"대구","포항","신월성N/P CB 7100","2024~25년도 포항전력지사 변전협력회사 공사","신월성S/Y, 신포항S/S 신포항-신월성#4T/L 보호반 대체공사 및 신월성 #2MO.Tr 오버홀","2025-07-22 09:00","2025-08-05 18:00","2025-07-22 09:00","2025-08-05 18:00","연속"]
[164,"대구","포항","신포항신영일 T/L","2024~25년 포항전력지사 변전협력회사 공사","신포항S/S 7171, 7100 GCB 조작시험 / LA, PT 보통점검 신영일S/S 7771 GIS 조작시험 / LA, PT 하자점검","2025-07-08 09:00","2025-07-09 18:00","취소","취소","연속"]
[165,"대구","포항","신울산월성NP#1 T/L","월성N/P 연계  GIS 용량대체공사(77Bay 대체)","월성N/P 연계  GIS 용량대체공사 ○  GIS × 18CB 대체 ○ 보호반 설치 및 이설 × 1식 ○ 제어케이블 포설 및 결선 × 1식 ○ 기타 부대공사 × 1식","2025-07-18 09:00","2025-09-17 18:00","2025-07-18 09:00","2025-09-17 18:00","연속"]
[166,"대구","포항","월성N/P CB 7772","월성N/P 연계  GIS 용량대체공사(77Bay 대체)","월성N/P 연계  GIS 용량대체공사 ○  GIS × 18CB 대체 ○ 보호반 설치 및 이설 × 1식 ○ 제어케이블 포설 및 결선 × 1식 ○ 기타 부대공사 × 1식","2025-07-18 09:00","2025-09-17 18:00","2025-07-18 09:00","2025-09-17 18:00","연속"]
[167,"대구","포항","월성N/P #71 BUS","월성N/P 연계  GIS 용량대체공사(77Bay 대체)","월성N/P 연계  GIS 용량대체공사 ○  GIS × 18CB 대체 ○ 보호반 설치 및 이설 × 1식 ○ 제어케이블 포설 및 결선 × 1식 ○ 기타 부대공사 × 1식","2025-07-18 09:00","2025-08-01 09:00","2025-07-18 09:00","2025-08-01 09:00","연속"]
[168,"대구","포항","월성N/P SEC CB 70710","월성N/P 연계  GIS 용량대체공사(77Bay 대체)","월성N/P 연계  GIS 용량대체공사 ○  GIS × 18CB 대체 ○ 보호반 설치 및 이설 × 1식 ○ 제어케이블 포설 및 결선 × 1식 ○ 기타 부대공사 × 1식","2025-07-31 14:00","2025-08-01 14:00","2025-07-31 14:00","2025-08-01 14:00","연속"]
[169,"경북","영주","신영주S/S CB 7500","2025년 영주전력지사  GIS 정밀점검","GIS 정밀점검","2025-07-28 09:00","2025-07-30 18:00","2025-07-28 09:00","2025-07-30 18:00","연속"]
[170,"경북","영주","신영주S/S CB 7300","2025년 영주전력지사  GIS 정밀점검","GIS 정밀점검","2025-07-14 09:00","2025-07-16 18:00","2025-07-14 09:00","2025-07-16 18:00","연속"]
[171,"경북","영주","신영주S/S CB 7371","2025년 영주전력지사  GIS 정밀점검","GIS 정밀점검","2025-07-07 09:00","2025-07-09 18:00","2025-07-07 09:00","2025-07-09 18:00","연속"]
[172,"경북","영주","신영주S/S CB 7571","2025년 영주전력지사  GIS 정밀점검","GIS 정밀점검","2025-07-21 09:00","2025-07-23 18:00","2025-07-21 09:00","2025-07-23 18:00","연속"]
[173,"경북","직할","신영일안동CC T/L","24-25년 경북직할 송전협력회사 공사","추락방지장치 설치공사","2025-07-07 00:07","2025-07-11 18:00","취소","취소","매일"]
[174,"경북","직할","신영주안동CC T/L","24-25년 경북직할 송전협력회사 공사","추락방지장치 설치공사","2025-07-01 09:00","2025-07-04 18:00","취소","취소","매일"]
[175,"경북","직할","신영주청송PP T/L"," 청송분기 T/L 불량애자 교체공사","-  신영주청송PP 불량애자 교체","2025-07-28 09:00","2025-08-28 18:00","취소","취소","매일"]
[176,"부산울산","북부산","북부산S/S CB 7A71","북부산S/S  STATCOM 초기점검","북부산S/S  STATCOM 초기점검","2025-07-07 09:00","2025-07-25 18:00","취소","취소","연속"]
[177,"부산울산","북부산","북부산S/S CB 7A00","북부산S/S  STATCOM 초기점검","북부산S/S  STATCOM 초기점검","2025-07-07 09:00","2025-07-25 18:00","취소","취소","연속"]
[178,"부산울산","북부산","북부산S/S #4 M.Tr","24-25년 북부산전력지사 변전총액공사","북부산S/S  #4M.Tr 철탑추락방지설치","2025-07-01 09:00","2025-07-02 18:00","취소","취소","연속"]
[179,"부산울산","북부산","북부산S/S #1 M.Tr","24-25년 북부산전력지사 변전총액공사","북부산S/S  #1M.Tr 철탑추락방지설치","2025-07-03 09:00","2025-07-04 18:00","취소","취소","연속"]
[180,"부산울산","직할","신대연S/S #2 Sh.R CB","24-25년 직할 변전협력회사 공사","신대연S/S  Sh.R B/F 보호반 교체","2025-07-01 09:00","2025-07-04 18:00","2025-07-01 09:00","2025-07-04 18:00","연속"]
[181,"부산울산","직할","신대연S/S #1 Sh.R CB","24-25년 직할 변전협력회사 공사","신대연S/S  Sh.R B/F 보호반 교체","2025-07-01 09:00","2025-07-04 18:00","2025-07-01 09:00","2025-07-04 18:00","연속"]
[182,"부산울산","동부산","신양산S/S #1 BUS","신양산S/S  용량부족차단기 교체공사","73BAY GIS 설치","2025-07-26 08:00","2025-07-27 18:00","2025-07-26 08:00","2025-07-27 18:00","연속"]
[183,"경남","김해송변전부","신김해S/S #4 M.Tr","신김해S/S 종합예방시스템 설치공사","- 신김해S/S  #4M.Tr 부싱시험탭 설치","2025-07-07 09:00","2025-07-08 14:00","취소","취소","연속"]
[184,"경남","김해송변전부","신김해S/S #1 M.Tr","신김해S/S 종합예방시스템 설치공사","- 신김해S/S  #1M.Tr 부싱시험탭 설치","2025-07-01 09:00","2025-07-02 14:00","2025-07-29 09:00","2025-07-30 14:00","연속"]
[185,"경남","김해송변전부","신김해S/S #5 M.Tr","신김해S/S 76Bay B/F반 PNL 대체공사","신김해S/S 76Bay B/F반 PNL 대체공사 (병행)신김해S/S  #5M.Tr 부싱시험탭 설치","2025-07-08 14:00","2025-07-11 18:00","2025-07-08 14:00","2025-07-11 18:00","연속"]
[186,"경남","김해송변전부","신김해S/S #3 M.Tr","신김해S/S 종합예방시스템 설치공사","- 신김해S/S  #3M.Tr 부싱시험탭 설치","2025-07-04 09:00","2025-07-05 14:00","취소","취소","연속"]
[187,"경남","김해송변전부","신김해S/S #2 M.Tr","신김해S/S 종합예방시스템 설치공사","- 신김해S/S  #2M.Tr 부싱시험탭 설치","2025-07-02 14:00","2025-07-03 18:00","2025-07-30 14:00","2025-07-31 18:00","연속"]
[188,"경남","통영","신고성S/S #1 M.Tr","신고성S/S  M.Tr 3차측 현대화 공사","신고성S/S  M.Tr 3차측 현대화 공사 1. 예비S.Tr 철거 2. 4125,4225 DS 철거 및 AL관 시공","2025-07-03 09:00","2025-07-04 18:00","2025-07-03 09:00","2025-07-04 18:00","연속"]
[189,"경남","통영","신고성S/S #4 M.Tr","신고성S/S  M.Tr 3차측 현대화 공사","신고성S/S  M.Tr 3차측 현대화 공사 1. 예비모선 연결용 점퍼선 설치 2. 4325 DS 철거 및 AL관 시공","2025-07-01 09:00","2025-07-02 18:00","2025-07-01 09:00","2025-07-02 18:00","연속"]

{"sheet":"154설비","index":2,"n_rows":264,"n_cols":12,"rows_kept":264,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2],[2,11,3,11]]}
["2025년도 7월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성수뚝도#1 T/L","2025년 성동P/O 변전협력회사 공사","43PDA 교체","2025-07-07 09:00","2025-07-07 18:00","2025-07-07 09:00","2025-07-07 18:00","연속"]
[2,"서울","성동","방학창동#2 T/L","2025년 성동P/O 170kV GIS 정밀점검","170kV GIS 정밀점검","2025-07-09 14:00","2025-07-09 18:00","2025-07-09 14:00","2025-07-09 18:00","연속"]
[3,"서울","성동","방학창동#2 T/L","2025년 성동P/O 170kV GIS 정밀점검","170kV GIS 정밀점검","2025-07-08 09:00","2025-07-08 14:00","2025-07-08 09:00","2025-07-08 14:00","연속"]
[4,"서울","성동","방학S/S CB 6100","2025년 성동P/O 170kV GIS 정밀점검","170kV GIS 정밀점검","2025-07-07 09:00","2025-07-09 18:00","2025-07-07 09:00","2025-07-09 18:00","연속"]
[5,"서울","성동","방학창동#2 T/L","2025년 성동P/O 170kV GIS 정밀점검","170kV GIS 정밀점검","2025-07-15 09:00","2025-07-15 14:00","2025-07-15 09:00","2025-07-15 14:00","연속"]
[6,"서울","성동","장암방학#2 T/L","2025년 성동P/O 170kV GIS 정밀점검","170kV GIS 정밀점검","2025-07-14 09:00","2025-07-16 18:00","2025-07-14 09:00","2025-07-16 18:00","연속"]
[7,"서울","성동","방학창동#2 T/L","2025년 성동P/O 170kV GIS 정밀점검","170kV GIS 정밀점검","2025-07-01 09:00","2025-07-01 18:00","2025-07-01 09:00","2025-07-01 18:00","연속"]
[8,"서울","성동","수유미아#2 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 초기점검","2025-07-02 09:00","2025-07-02 18:00","2025-07-02 09:00","2025-07-02 18:00","연속"]
[9,"서울","성동","창동쌍문#1 T/L","2025 성동전력지사 변전협력회사 공사","- 170kV GIS 보통점검","2025-07-03 09:00","2025-07-03 18:00","2025-07-03 09:00","2025-07-03 18:00","연속"]
[10,"서울","성동","쌍문수유#2 T/L","2025년 성동P/O 170kV GIS 정밀점검 공사","- 170kV GIS 정밀점검(쌍문S/S) - 170kV GIS 초기점검(수유S/S)","2025-07-01 09:00","2025-07-03 18:00","2025-07-01 09:00","2025-07-03 18:00","연속"]
[11,"서울","성동","쌍문수유#1 T/L","2025년 성동P/O 170kV GIS 정밀점검 공사","- 170kV GIS 정밀점검(양단S/S)","2025-07-01 09:00","2025-07-03 18:00","2025-07-01 09:00","2025-07-03 18:00","연속"]
[12,"서울","성동","창동쌍문#2 T/L","2025 성동전력지사 변전협력회사 공사","- 170kV GIS 보통점검","2025-07-04 09:00","2025-07-04 18:00","2025-07-04 09:00","2025-07-04 18:00","연속"]
[13,"서울","직할","옥인운니#1 T/L","25년 직할 변전정비협력회사 총액공사","GIS 보통점검","2025-07-10 10:00","2025-07-10 17:00","2025-07-10 10:00","2025-07-10 17:00","연속"]
[14,"서울","직할","옥인운니#2 T/L","25년 직할 변전정비협력회사 총액공사","GIS 보통점검","2025-07-11 10:00","2025-07-11 17:00","2025-07-11 10:00","2025-07-11 17:00","연속"]
[15,"남서울","동서울","탄천대치#2 T/L","2025년도 동서울전력지사 170kV GIS 정밀점검","탄천S/S 탄천-선릉#2T/L GIS 정밀점검","2025-07-02 09:00","2025-07-03 18:00","2025-07-02 09:00","2025-07-03 18:00","연속"]
[16,"경기","평택","포승평택TP#2 T/L"," 북현덕분기 2차 전력구공사","수직구 2개소, 개착식 전력구157m, semishield 202m 구조물공사 완료 후 가시설 철거","2025-07-10 09:00","2025-07-10 18:00","2025-07-06 09:00","2025-07-06 18:00","연속"]
[17,"경기","평택","포승평택TP#1 T/L"," 북현덕분기 2차 전력구공사","수직구 2개소, 개착식 전력구157m, semishield 202m 구조물 공사 완료 후 가시설 철거","2025-07-09 09:00","2025-07-09 18:00","2025-07-05 09:00","2025-07-05 18:00","연속"]
[18,"강원","동해","동해S/S #67 BUS","170kV GIS 정밀점검 무부하가압용"," 한라T/L 정밀점검 무부하 가압용","2025-07-16 09:00","2025-07-16 18:00","2025-07-16 09:00","2025-07-16 18:00","연속"]
[19,"강원","동해","울진삼척GP#2 T/L","170kV GIS정밀점검 무부하가압용","170kV LNG T/L GIS정밀점검 무부하가압용","2025-07-23 09:00","2025-07-23 18:00","2025-07-23 09:00","2025-07-23 18:00","연속"]
[20,"강원","동해","삼척동해TP T/L"," 동해화력T/L EBG 가스채취밸브 설치공사","- 이원-동해TP, 삼척-동해TP 각 EBG 6상 가스채취밸브 설치(총 12상)","2025-07-03 08:00","2025-07-04 18:00","2025-07-03 08:00","2025-07-04 18:00","연속"]
[21,"강원","동해","동해이원#2 T/L","170kV GIS정밀점검 무부하가압용"," 한라T/L GIS정밀점검 무부하가압용","2025-07-16 09:00","2025-07-16 18:00","2025-07-16 09:00","2025-07-16 18:00","연속"]
[22,"강원","동해","이원동해TP T/L","2025년 동해전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2025-07-07 09:00","2025-07-10 18:00","2025-07-07 09:00","2025-07-10 18:00","연속"]
[23,"강원","직할","남춘천춘천 T/L","2024~2025년 강원본부 직할 송전협력회사 공사","조류착지방지장치 및 항공장애표시구 설치","2025-07-08 07:30","2025-07-11 18:00","취소","취소","매일"]
[24,"강원","태백","태백S/S #60 BUS","2025년 태백전력지사  GIS 정밀점검공사","태백S/S  1Sh.C GIS 정밀점검 무부하가압용","2025-07-04 09:00","2025-07-04 18:00","2025-07-04 09:00","2025-07-04 18:00","연속"]
[25,"강원","태백","태백S/S #61 BUS","2025년 태백전력지사  GIS 정밀점검공사","태백S/S  1Sh.C GIS 정밀점검 무부하가압용","2025-07-09 09:00","2025-07-09 14:00","2025-07-09 09:00","2025-07-09 14:00","연속"]
[26,"강원","태백","태백S/S #61 BUS","2025년 태백전력지사  GIS 정밀점검공사","태백S/S  1Sh.C GIS 정밀점검 무부하가압용","2025-07-11 09:00","2025-07-11 18:00","2025-07-11 09:00","2025-07-11 18:00","연속"]
[27,"충북","청주","남청주오송#1 T/L","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(안전이격확보/무부하가압용_7월)","2025-07-17 14:00","2025-07-22 14:00","취소","취소","연속"]
[28,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(무부하가압용_7월)","2025-07-16 14:00","2025-07-17 18:00","취소","취소","연속"]
[29,"충북","청주","남청주S/S #61 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(7월)","2025-07-16 07:00","2025-07-17 14:00","취소","취소","연속"]
[30,"충북","청주","남청주S/S SEC CB 62610","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(7월)","2025-07-16 07:00","2025-07-27 18:00","취소","취소","연속"]
[31,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(무부하가압용_7월)","2025-07-26 14:00","2025-07-27 18:00","취소","취소","연속"]
[32,"충북","청주","남청주S/S #61 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(7월)","2025-07-22 14:00","2025-07-27 18:00","취소","취소","연속"]
[33,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(무부하가압용_7월)","2025-07-12 14:00","2025-07-13 18:00","취소","취소","연속"]
[34,"충북","청주","남청주S/S #66 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(7월)","2025-07-02 07:00","2025-07-03 14:00","취소","취소","연속"]
[35,"충북","청주","남청주S/S SEC CB 67660","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(7월)","2025-07-02 07:00","2025-07-13 18:00","취소","취소","연속"]
[36,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(무부하가압용_7월)","2025-07-02 07:00","2025-07-03 14:00","취소","취소","연속"]
[37,"충북","청주","남청주S/S #67 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(7월)","2025-07-03 14:00","2025-07-08 14:00","취소","취소","연속"]
[38,"충북","청주","남청주오송#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(무부하가압용_7월)","2025-07-07 14:00","2025-07-08 14:00","취소","취소","연속"]
[39,"충북","청주","남청주S/S #66 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(7월)","2025-07-08 14:00","2025-07-13 18:00","취소","취소","연속"]
[40,"충북","청주","남청주S/S #62 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(7월)","2025-07-17 14:00","2025-07-22 14:00","취소","취소","연속"]
[41,"충북","청주","신옥천S/S SEC CB 61620","신옥천S/S  #61-#66BUS 모선보호반 대체","신옥천S/S  #61-#66BUS 모선보호반 대체","2025-07-07 09:00","2025-07-10 18:00","취소","취소","연속"]
[42,"충북","청주","신옥천S/S CB 6200","신옥천S/S  #61-#66BUS 모선보호반 대체","신옥천S/S  #61-#66BUS 모선보호반 대체","2025-07-07 09:00","2025-07-10 18:00","취소","취소","연속"]
[43,"충북","청주","신옥천S/S SEC CB 66670","신옥천S/S  #61-#66BUS 모선보호반 대체","신옥천S/S  #61-#66BUS 모선보호반 대체","2025-07-07 09:00","2025-07-10 18:00","취소","취소","연속"]
[44,"충북","청주","신옥천S/S SEC CB 65660","신옥천S/S  #61-#66BUS 모선보호반 대체","신옥천S/S  #61-#66BUS 모선보호반 대체","2025-07-07 09:00","2025-07-10 18:00","취소","취소","연속"]
[45,"충북","청주","신옥천S/S SEC CB 60610","신옥천S/S  #61-#66BUS 모선보호반 대체","신옥천S/S  #61-#66BUS 모선보호반 대체","2025-07-07 09:00","2025-07-10 18:00","취소","취소","연속"]
[46,"충북","청주","옥천영동 T/L","2024~2025년 송전정비 협력회사 총액공사"," 옥천-영동T/L 추락방지장치 설치(수평설치) 1. 내용 : 옥천-영동T/L 수평 추락방지장치 설치 2. 구간 :  영동분기T/L 1~61호","2025-07-07 08:00","2025-07-15 18:00","취소","취소","연속"]
[47,"충북","청주","화동영동 T/L","2024~2025년 송전정비 협력회사 총액공사"," 화동-영동T/L 추락방지장치 설치(수평설치) 1. 내용 : 화동-영동T/L 수평 추락방지장치 설치 2. 구간 :  화동-영동T/L 60~110호  영동분기T/L 1~61호","2025-07-16 08:00","2025-07-25 18:00","취소","취소","연속"]
[48,"충북","충주","풍동음성#2 T/L"," 풍동S/S 외벽 리모델링 공사","공사 목적 : 화재에 취약한 외벽 드라이비트 마감재를 교체하여 화재 확산 방지 및 설비피해를 예방하고자 함. - 시스템비계 설치 및 해체 : 2,815m2 - 외벽드라이비트 마감재 철거 : 1,808m2 - 신설 마감재 설치 : 1,808m2","2025-07-21 09:00","2025-08-01 18:00","취소","취소","연속"]
[49,"충북","충주","충주풍동 T/L"," 풍동S/S 외벽 리모델링 공사","공사 목적 : 화재에 취약한 외벽 드라이비트 마감재를 교체하여 화재 확산 방지 및 설비피해를 예방하고자 함. - 시스템비계 설치 및 해체 : 2,815m2 - 외벽드라이비트 마감재 철거 : 1,808m2 - 신설 마감재 설치 : 1,808m2","2025-07-07 09:00","2025-07-18 18:00","취소","취소","연속"]
[50,"충북","충주","풍동장연 T/L"," 풍동S/S 외벽 리모델링 공사","공사 목적 : 화재에 취약한 외벽 드라이비트 마감재를 교체하여 화재 확산 방지 및 설비피해를 예방하고자 함. - 시스템비계 설치 및 해체 : 2,815m2 - 외벽드라이비트 마감재 철거 : 1,808m2 - 신설 마감재 설치 : 1,808m2","2025-07-07 09:00","2025-07-18 18:00","취소","취소","연속"]
[51,"충북","충주","풍동음성#1 T/L"," 풍동S/S 외벽 리모델링 공사","공사 목적 : 화재에 취약한 외벽 드라이비트 마감재를 교체하여 화재 확산 방지 및 설비피해를 예방하고자 함. - 시스템비계 설치 및 해체 : 2,815m2 - 외벽드라이비트 마감재 철거 : 1,808m2 - 신설 마감재 설치 : 1,808m2","2025-07-21 09:00","2025-08-01 18:00","취소","취소","연속"]
[52,"대전세종충남","대전","금산무주#2 T/L","[송전][오전만][즉시가압O]345kV 신옥천-청양 등 추락방지설치공사","[송전][오전만][즉시가압O]345kV 신옥천-청양 등 추락방지설치공사","2025-07-23 07:00","2025-07-25 11:00","취소","취소","매일"]
[53,"대전세종충남","대전","신계룡두마#2 T/L","[취소시][가압X]신계룡,두마S/S 신계룡-두마#2T/L GIS 보통점검","[취소시][가압X]신계룡,두마S/S 신계룡-두마#2T/L GIS 보통점검","2025-07-28 09:00","2025-07-28 18:00","취소","취소","연속"]
[54,"대전세종충남","대전","신계룡두마#1 T/L","[취소시][가압X]신계룡,두마S/S 신계룡-두마#1T/L GIS 보통점검","[취소시][가압X]신계룡,두마S/S 신계룡-두마#1T/L GIS 보통점검","2025-07-07 09:00","2025-07-07 18:00","취소","취소","연속"]
[55,"대전세종충남","대전","신계룡두마#1 T/L","신계룡,두마S/S  신계룡-두마#1T/L 보호반교체","신계룡,두마S/S  신계룡-두마#1T/L 보호반교체","2025-07-07 09:00","2025-07-10 18:00","취소","취소","연속"]
[56,"대전세종충남","대전","신계룡은진#1 T/L","[송전][오전만][즉시가압O]345kV 신옥천-청양 등 추락방지설치공사","[송전][오전만][즉시가압O]345kV 신옥천-청양 등 추락방지설치공사","2025-07-01 07:00","2025-07-11 11:00","취소","취소","매일"]
[57,"대전세종충남","대전","신계룡두마#2 T/L","신계룡,두마S/S  신계룡-두마#2T/L 보호반교체","신계룡,두마S/S  신계룡-두마#2T/L 보호반교체","2025-07-28 09:00","2025-07-30 18:00","취소","취소","연속"]
[58,"대전세종충남","대전","신옥천용운#1 T/L","(즉시가압O)용운S/S  신옥천-용운#1T/L ES 락핀 점검","용운S/S  신옥천-용운#1T/L ES 락핀 점검","2025-07-14 09:00","2025-07-14 18:00","취소","취소","연속"]
[59,"대전세종충남","서산","신당진당진#2 T/L"," 당진S/S 장기사용 #4M.Tr 교체공사"," 당진S/S 장기사용 #4M.Tr 교체공사 관련 무부하가압","2025-07-07 10:00","2025-07-08 10:00","2025-07-07 10:00","2025-07-08 10:00","연속"]
[60,"대전세종충남","서산","서산태안#2 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.15~80), 즉시가압(20분 이내)가능, 주말작업 없음","2025-07-15 08:00","2025-07-22 18:00","취소","취소","매일"]
[61,"대전세종충남","서산","서산태안#1 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.15~80), 즉시가압(20분 이내)가능, 주말작업 없음","2025-07-07 08:00","2025-07-14 18:00","취소","취소","매일"]
[62,"대전세종충남","세종","조치원전의#2 T/L","[송전] 조치원-전의T/L 안전이격 및 전력선 교체공사","○  조치원-전의T/L 안전이격 및 전력선 교체공사 - 지지물 교체 : No.25,33,34 - 용량증대 전선교체 : 조치원S/S~전의S/S","2025-07-02 07:00","2025-07-09 18:00","2025-07-02 07:00","2025-07-09 18:00","연속"]
[63,"대전세종충남","직할","동대전신탄진#2 T/L","2025년 직할 관내S/S 170kV GIS 정밀점검공사","동대전S/S 동대전-신탄진#2T/L GIS 정밀점검","2025-07-16 08:00","2025-07-17 18:00","2025-07-16 08:00","2025-07-17 18:00","연속"]
[64,"대전세종충남","직할","동대전신탄진#1 T/L","2025년 직할 관내S/S 170kV GIS 정밀점검공사","동대전S/S 동대전-신탄진#1T/L GIS 정밀점검","2025-07-14 08:00","2025-07-15 18:00","2025-07-14 08:00","2025-07-15 18:00","연속"]
[65,"대전세종충남","직할","둔곡송강#2 T/L","송강S/S  둔곡-송강#2T/L GIS 보통점검","송강S/S  둔곡-송강#2T/L GIS 보통점검","2025-07-18 09:00","2025-07-18 18:00","취소","취소","연속"]
[66,"대전세종충남","천안","아산예산#2 T/L","(6월취소시) 아산-예산#2T/L 노후 보호배전반 대체","(6월취소시)(즉시가압불가)(장기미교체 대상) 아산-예산#2T/L 노후 보호배전반 대체","2025-07-07 09:00","2025-07-10 18:00","취소","취소","연속"]
[67,"대전세종충남","천안","아산예산#1 T/L","(6월 취소시) 아산-예산#1T/L 노후 보호배전반 대체","(6월 취소시)(즉시가압불가)(장기미교체 대상) 아산-예산#1T/L 노후 보호배전반 대체","2025-07-01 09:00","2025-07-04 18:00","취소","취소","연속"]
[68,"대전세종충남","청양","관창대천#1 T/L","[변전총액] 청양P/O 변전협력 총액공사","관창S/S 170kV 관창-대천#1T/L 조작시험 및 피뢰기 보통점검","2025-07-07 09:00","2025-07-07 14:00","취소","취소","연속"]
[69,"대전세종충남","청양","관창대천#2 T/L","[변전총액] 청양P/O 변전협력 총액공사","관창S/S 170kV 관창-대천#2T/L GIS 및 피뢰기 보통점검","2025-07-07 14:00","2025-07-07 18:00","취소","취소","연속"]
[70,"대전세종충남","청양","청양보령CC T/L","[변전총액] 청양P/O 변전협력 총액공사","보령T/P 170kV 보령복합T/L 조작시험 및 전자변교체","2025-07-09 09:00","2025-07-09 18:00","취소","취소","연속"]
[71,"대전세종충남","청양","옥산장항#2 T/L","[변전총액] 청양P/O 변전협력 총액공사","옥산S/S 170kV 옥산-장항#2T/L GIS 및 CVT 보통점검","2025-07-11 09:00","2025-07-11 18:00","취소","취소","연속"]
[72,"대전세종충남","청양","신서천옥산#2 T/L","[변전총액] 청양P/O 변전협력 총액공사","옥산S/S 170kV 옥산-서천화력#2T/L 보통점검","2025-07-10 09:00","2025-07-10 18:00","취소","취소","연속"]
[73,"대전세종충남","청양","은하홍성#2 T/L","[변전총액] 청양P/O 변전협력 총액공사","ㅁ은하-홍성#2T/L 보호배전반 교체(은하S/S , 홍성S/S)","2025-07-09 09:00","2025-07-11 18:00","취소","취소","연속"]
[74,"대전세종충남","청양","동군산장항#2 T/L","[변전총액] 청양P/O 변전협력 총액공사","장항S/S 170kV 동군산-장항#2T/L 조작시험 및 피뢰기 보통점검","2025-07-17 09:00","2025-07-17 18:00","취소","취소","연속"]
[75,"전북","군산","군산영등#1 T/L","'25년 군산전력지사 가공송전협력회사공사"," 군산-영등T/L 소도체 이도조정공사","2025-07-22 07:00","2025-07-22 18:00","취소","취소","연속"]
[76,"전북","군산","내초군장#1 T/L","24~25년 군산전력지사 변전협력회사 총액공사","-노후배전반 대체공사(내초-군장#1T/L 양단)","2025-07-23 09:00","2025-07-25 18:00","2025-07-23 09:00","2025-07-25 18:00","연속"]
[77,"전북","군산","내초군장#2 T/L","24~25년 군산전력지사 변전협력회사 총액공사","-노후배전반 대체공사(내초-군장#2T/L 양단)","2025-07-28 09:00","2025-07-30 18:00","2025-07-28 09:00","2025-07-30 18:00","연속"]
[78,"전북","군산","서군산소룡#2 T/L","군산P/O 이상 차단기 하자점검","서군산S/S  서군산-소룡#1,2 T/L 차단기 하자점검","2025-07-02 09:00","2025-07-02 18:00","취소","취소","연속"]
[79,"전북","군산","서군산소룡#1 T/L","군산P/O 이상 차단기 하자점검","서군산S/S  서군산-소룡#1,2 T/L 차단기 하자점검","2025-07-03 09:00","2025-07-03 18:00","취소","취소","연속"]
[80,"전북","군산","영등팔봉#1 T/L"," 영등S/S 혼용운영시스템 설치공사","혼용화 관련 제어케이블 이설 [RTU↔GIS]☞[LID↔GIS] 이설 후 SCADA 연동시험 시행","2025-07-24 09:00","2025-07-25 18:00","2025-07-24 09:00","2025-07-25 18:00","연속"]
[81,"전북","군산","영등낭산#2 T/L"," 영등S/S 혼용운영시스템 설치공사","혼용화 관련 제어케이블 이설 [RTU↔GIS]☞[LID↔GIS] 이설 후 SCADA 연동시험 시행","2025-07-22 09:00","2025-07-23 18:00","2025-07-22 09:00","2025-07-23 18:00","연속"]
[82,"전북","군산","영등낭산#1 T/L"," 영등S/S 혼용운영시스템 설치공사","혼용화 관련 제어케이블 이설 [RTU↔GIS]☞[LID↔GIS] 이설 후 SCADA 연동시험 시행","2025-07-30 09:00","2025-07-31 18:00","2025-07-30 09:00","2025-07-31 18:00","연속"]
[83,"전북","군산","군산영등#1 T/L"," 영등S/S 혼용운영시스템 설치공사","혼용화 관련 제어케이블 이설 [RTU↔GIS]☞[LID↔GIS] 이설 후 SCADA 연동시험 시행","2025-07-10 09:00","2025-07-11 18:00","취소","취소","연속"]
[84,"전북","군산","군산영등#2 T/L","'25년 군산전력지사 가공송전협력회사공사"," 군산-영등T/L 소도체 이도조정공사","2025-07-04 07:00","2025-07-04 18:00","취소","취소","연속"]
[85,"전북","군산","영등팔봉#2 T/L"," 영등S/S 혼용운영시스템 설치공사","혼용화 관련 제어케이블 이설 [RTU↔GIS]☞[LID↔GIS] 이설 후 SCADA 연동시험 시행","2025-07-28 09:00","2025-07-29 18:00","2025-07-28 09:00","2025-07-29 18:00","연속"]
[86,"전북","군산","영등낭산#1 T/L","'25년 군산전력지사 가공송전협력회사공사"," 군산-영등T/L 소도체 이도조정공사","2025-07-04 07:00","2025-07-04 18:00","2025-07-04 07:00","2025-07-04 18:00","연속"]
[87,"전북","군산","탄소이리#1 T/L","'24~25년 군산전력 가공송전협력업체 공사"," 이리-탄소T/L 피뢰기 설치공사 No.1~63","2025-07-07 15:00","2025-07-11 10:00","취소","취소","연속"]
[88,"전북","군산","은진함열#1 T/L","24~25년 군산전력지사 변전협력회사 총액공사","-노후배전반 대체공사(은진-함열#1T/L 양단)","2025-07-01 09:00","2025-07-03 18:00","취소","취소","연속"]
[89,"전북","김제","소성고창#1 T/L"," 고창-영광T/L No.45~142 선종교체공사","○  고창-영광T/L 선종교체공사 - No.45~142 전력선 교체(ACSR 330㎟ -> ASCC 430㎟)","2025-07-14 07:00","2025-07-23 18:00","2025-07-14 07:00","2025-07-23 18:00","연속"]
[90,"전북","김제","김제S/S #1 EM.Tr CB","25년 김제 FR-ESS 정밀점검","25년 김제 FR-ESS 정밀점검","2025-07-07 09:00","2025-07-11 18:00","2025-07-07 09:00","2025-07-11 18:00","연속"]
[91,"전북","김제","부안동부안#1 T/L","모선구분차단기 설치공사(6200 무부하가압)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-07-24 15:00","2025-07-25 15:00","2025-07-24 15:00","2025-07-25 15:00","연속"]
[92,"전북","김제","부안동부안#2 T/L","모선구분차단기 설치공사(6200 무부하가압)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-07-29 15:00","2025-07-30 15:00","2025-07-29 15:00","2025-07-30 15:00","연속"]
[93,"전북","김제","김제부안#1 T/L","모선구분차단기 설치(PT&ES)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-07-31 09:00","2025-08-08 18:00","취소","취소","연속"]
[94,"전북","김제","김제부안#2 T/L","모선구분차단기 설치(6200)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-07-22 09:00","2025-07-30 18:00","취소","취소","연속"]
[95,"전북","김제","신김제동전주#2 T/L"," 완산분기T/L 건설공사","- 작업내용 : #2T/L 전선 긴선(케이블타워) - 위치 : 전주시 완산구 석구동 일원 - 규모 : ACSR410㎟ × 2B × 4C (0.81km, 지지물4기)","2025-07-25 07:00","2025-07-28 18:00","취소","취소","연속"]
[96,"전북","김제","신김제동전주#2 T/L"," 완산분기T/L 건설공사","- 작업내용 : #2T/L 전선이동 (가선로 → 본선로) - 위치 : 전주시 완산구 석구동 일원 - 규모 : ACSR410㎟ × 2B × 4C (0.81km, 지지물4기)","2025-07-14 07:00","2025-07-18 18:00","취소","취소","연속"]
[97,"전북","김제","신김제동전주#1 T/L"," 완산분기T/L 건설공사","- 작업내용 : #1T/L 전선이동 (가선로 → 본선로), 케이블타워 조립 및 전선긴선 - 위치 : 전주시 완산구 석구동 일원 - 규모 : ACSR410㎟ × 2B × 4C (0.81km, 지지물4기)","2025-07-19 07:00","2025-07-24 18:00","취소","취소","연속"]
[98,"전북","직할","동전주태평#1 T/L","동전주-태평#1T/L GIS 정밀점검","CB, DS 정밀점검","2025-07-07 09:00","2025-07-10 18:00","2025-07-07 09:00","2025-07-10 18:00","연속"]
[99,"전북","직할","무주진안 T/L"," #1Sh.C GIS 정밀점검관련 무부하 가압"," #1Sh.C GIS 정밀점검관련 무부하 가압","2025-07-04 14:00","2025-07-04 18:00","취소","취소","연속"]
[100,"전북","직할","무주용담수력 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사(계속)","○ 수평 추락방지시설 설치 -  북전주-진안T/L No.50~104 -  무주분기T/L No.1~45","2025-07-10 07:30","2025-07-16 18:00","취소","취소","연속"]
[101,"전북","직할","북전주진안 T/L","북전주-진안T/L GIS 정밀점검","CB 정밀점검","2025-07-25 09:00","2025-07-26 18:00","취소","취소","연속"]
[102,"전북","직할","북전주용담수력 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사(계속)","○ 수평 추락방지시설 설치 : No.1~50","2025-07-17 07:30","2025-07-20 18:00","취소","취소","연속"]
[103,"전북","직할","북전주S/S #1 BUS","북전주-진안T/L GIS 정밀점검","CB 정밀점검","2025-07-25 09:00","2025-07-26 18:00","취소","취소","연속"]
[104,"전북","직할","신남원S/S #5 EM.Tr CB","신남원 ESS 변전설비 #5EM.Bank 초기점검","변압기 1대, 170gis 1대, 23kV gis 8대, EP.Tr 7대","2025-07-14 09:00","2025-07-18 18:00","2025-07-14 09:00","2025-07-18 18:00","연속"]
[105,"전북","직할","신남원S/S #6 EM.Tr CB","ESS EM.Tr 96TC IED 업데이트","작업사유 : 전압이상 경보 설정값 변경 작업내용 : 제작사 IED 업데이트 후 계통시험팀 시험 소요시간 : EM.Tr당 2시간(즉시 가압가능). 끝.","2025-07-01 14:00","2025-07-01 16:00","2025-07-01 14:00","2025-07-01 16:00","연속"]
[106,"전북","직할","신남원S/S #5 EM.Tr CB","ESS EM.Tr 96TC IED 업데이트","작업사유 : 전압이상 경보 설정값 변경 작업내용 : 제작사 IED 업데이트 후 계통시험팀 시험 소요시간 : EM.Tr당 2시간(즉시 가압가능). 끝.","2025-07-01 12:00","2025-07-01 14:00","2025-07-01 12:00","2025-07-01 14:00","연속"]
[107,"전북","직할","신남원S/S #4 EM.Tr CB","ESS EM.Tr 96TC IED 업데이트","작업사유 : 전압이상 경보 설정값 변경 작업내용 : 제작사 IED 업데이트 후 계통시험팀 시험 소요시간 : EM.Tr당 2시간(즉시 가압가능). 끝.","2025-07-01 10:00","2025-07-01 12:00","2025-07-01 10:00","2025-07-01 12:00","연속"]
[108,"전북","직할","신남원S/S #6 EM.Tr CB","신남원 ESS 변전설비 #6EM.Bank 초기점검","변압기 1대, 170gis 1대, 23kV gis 8대, EP.Tr 7대","2025-07-21 09:00","2025-07-25 18:00","2025-07-21 09:00","2025-07-25 18:00","연속"]
[109,"전북","직할","탄소전주#1 T/L","전주S/S 6100 TIE GIS 정밀점검관련 무부하가압","전주S/S 6100 TIE GIS 정밀점검관련 무부하가압","2025-07-01 14:00","2025-07-01 18:00","2025-07-01 14:00","2025-07-01 18:00","연속"]
[110,"전북","직할","전주서곡#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-07-14 08:00","2025-07-15 18:00","2025-07-14 08:00","2025-07-15 18:00","매일"]
[111,"전북","직할","탄소전주#1 T/L","전주S/S 6100 TIE GIS 정밀점검관련 무부하가압","전주S/S 6100 TIE GIS 정밀점검관련 무부하가압","2025-07-04 14:00","2025-07-04 18:00","2025-07-04 14:00","2025-07-04 18:00","연속"]
[112,"전북","직할","탄소전주#1 T/L"," 전주S/S #3M.Tr 교체공사","○  전력용변압기(45/60MVA * 1대) * 1Bank 철거 ○  전력용변압기(15/20MVA * 3대) * 1Bank 재사용철거 및 설치 ○  전력용변압기(15/20MVA * 3대) * 1Bank 정밀점검 ○ 기타 부대작업 * 1식","2025-07-02 16:00","2025-07-03 16:00","2025-07-02 16:00","2025-07-03 16:00","연속"]
[113,"전북","직할","전주서곡#2 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-07-16 08:00","2025-07-17 18:00","2025-07-16 08:00","2025-07-17 18:00","매일"]
[114,"전북","직할","진안장수#2 T/L","345kV 신옥천-신남원 등 3개T/L 수평추락방지시설 설치공사","345kV 신옥천-신남원#1T/L 1~178호 설치 관련 진안장수#2 No.46 병가구간 작업을 위한 휴전시행","2025-07-04 07:30","2025-07-06 17:00","취소","취소","매일"]
[115,"전북","직할","무주진안 T/L","무주-진안T/L GIS 정밀점검","CB, DS 정밀점검","2025-07-28 09:00","2025-07-31 18:00","취소","취소","연속"]
[116,"전북","직할","북전주진안 T/L","북전주-진안T/L GIS 정밀점검","CB, DS 정밀점검","2025-07-21 09:00","2025-07-24 18:00","취소","취소","연속"]
[117,"전북","직할","진안장수#1 T/L","345kV 신옥천-신남원 등 3개T/L 수평추락방지시설 설치공사","345kV 신옥천-신남원#2T/L 1~178호 설치 관련 진안장수#1 No.46 병가구간 작업을 위한 휴전시행","2025-07-21 07:30","2025-07-23 17:00","취소","취소","매일"]
[118,"전북","직할","탄소전주#2 T/L","세니온제 제어IED 성능개선","세니온제 제어IED 성능개선","2025-07-01 08:00","2025-07-01 12:00","2025-07-01 08:00","2025-07-01 12:00","연속"]
[119,"광주전남","강진","금정강진#1 T/L"," 강진-장흥 등 5개T/L 피뢰기 및 추락방지장치 설치공사","금정-강진T/L, 장흥-벌교T/L 피뢰기 설치","2025-07-07 07:00","2025-07-08 18:00","취소","취소","연속"]
[120,"광주전남","강진","금정강진#1 T/L"," 금정-강진T/L OPGW 불량구간 교체공사","금정-강진T/L OPGW 불량구간 교체(강진-장흥 병가구간 포함)","2025-07-07 07:00","2025-07-11 18:00","취소","취소","연속"]
[121,"광주전남","강진","강진남창#1 T/L"," 강진-장흥 등 5개T/L 피뢰기 및 추락방지장치 설치공사"," 신강진-강진T/L 피뢰기 설치 (4회선구간 휴전)","2025-07-28 07:00","2025-07-29 18:00","취소","취소","연속"]
[122,"광주전남","강진","신강진강진#1 T/L"," 강진-장흥 등 5개T/L 피뢰기 및 추락방지장치 설치공사","신강진-강진#1 피뢰기 설치","2025-07-28 07:00","2025-07-29 18:00","취소","취소","연속"]
[123,"광주전남","강진","강진장흥#2 T/L"," 강진-장흥 등 5개T/L 피뢰기 및 추락방지장치 설치공사"," 강진-장흥#2T/L No.1~59 피뢰기 설치 (60기)","2025-07-07 07:00","2025-07-11 18:00","취소","취소","연속"]
[124,"광주전남","강진","강진장흥#2 T/L"," 금정-강진T/L OPGW 불량구간 교체공사","금정-강진T/L OPGW 불량구간 교체(강진-장흥 병가구간 포함)","2025-07-07 01:00","2025-07-11 11:00","취소","취소","연속"]
[125,"광주전남","강진","나주영암#2 T/L","2025년 가공송전 순시점검 위탁공사","나주-영암#2T/L 정밀점검 (영암-금정#1T/L, 나주-금천#1T/L 병가선로)(1시간 내 가압 가능)","2025-07-15 07:00","2025-07-25 18:00","취소","취소","매일"]
[126,"광주전남","강진","나주금천#1 T/L","2025년 가공송전 순시점검 위탁공사","나주-영암#2T/L 정밀점검(안전이격 확보) (나주-영암#2T/L 병가선로)(1시간 내 가압 가능)","2025-07-22 07:00","2025-07-25 18:00","취소","취소","매일"]
[127,"광주전남","강진","대불삼호#2 T/L","24~25년 강진전력지사 변전협력회사 공사","(즉시가압 가능),(휴전 일시 변동가능함, 16시 이후 등) -대불S/S 대불-삼호#2T/L GIS 조작시험","2025-07-04 09:00","2025-07-04 18:00","2025-07-04 18:00","2025-07-04 24:00","연속"]
[128,"광주전남","강진","삼호화원#2 T/L"," 삼호-화원 지중T/L(복도체화) 건설공사"," XLPE 2000㎟(S) × 6.8km → XLPE 2000㎟(D) × 6.8km","2025-07-21 09:00","2025-08-29 18:00","취소","취소","연속"]
[129,"광주전남","강진","신강진강진#2 T/L","'25년 강진전력지사 효성제 170kV GIS 개선공사","-170kV GIS 개선공사 (2단래치 및 베어링 교체)","2025-07-04 16:00","2025-07-04 20:00","취소","취소","연속"]
[130,"광주전남","강진","신강진해남#2 T/L","2025년 강진전력지사 효성제 170kV GIS 개선공사","2025년 강진전력지사 효성제 170kV GIS 개선공사 - 베어링 및 레치 신품 교체","2025-07-02 16:00","2025-07-02 20:00","2025-07-02 18:00","2025-07-02 22:00","연속"]
[131,"광주전남","강진","신강진대불#2 T/L","2024~2025년 강진전력지사 송전협력회사 공사","가공지선 불량개소 정비 공사(40~42호 가공지선 교체)","2025-07-29 07:00","2025-07-29 18:00","취소","취소","매일"]
[132,"광주전남","강진","영암금정#1 T/L","2025년 가공송전 순시점검 위탁공사","영암-금정#1T/L 정밀점검 (나주-영암#2T/L 병가선로)(1시간 내 가압 가능)","2025-07-14 07:00","2025-07-21 18:00","취소","취소","매일"]
[133,"광주전남","강진","장흥보성 T/L","24~25년 강진전력지사 변전협력회사 공사","(즉시가압 가능),(휴전 일시 변동가능함, 16시 이후 등) -장흥S/S 장흥-보성T/L GIS CB 접점 점검","2025-07-03 09:00","2025-07-03 18:00","2025-07-03 18:00","2025-07-03 24:00","연속"]
[134,"광주전남","강진","장흥벌교 T/L"," 강진-장흥 등 5개T/L 피뢰기 및 추락방지장치 설치공사"," 강진-장흥#2T/L 및 장흥-벌교T/L 피뢰기 설치 - 강진-장흥T/L 4회선 구간(54~58호) 작업 시  장흥-벌교T/L 병행휴전","2025-07-09 07:00","2025-07-17 18:00","취소","취소","연속"]
[135,"광주전남","강진","해남진도#2 T/L","2025년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","- 170kV GIS 보통점검 - 효성제 170kV GIS 개선 등","2025-07-01 16:00","2025-07-01 20:00","취소","취소","연속"]
[136,"광주전남","강진","화원진도#1 T/L","2025년 가공송전 순시점검 위탁공사","화원-진도#1T/L 정밀점검 (1시간 내 가압 가능)","2025-07-08 09:00","2025-07-11 18:00","취소","취소","매일"]
[137,"광주전남","광주","계림승주#2 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 계림-승주#2 T/L 피뢰기 설치 - 대상 : 1~3, 17~107호 (총 99기) - 병가구간 : 3호 (신광주-계림#1,#2 병가), 99~106호(순천-승주#1 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-07-01 07:00","2025-07-11 18:00","2025-07-01 07:00","2025-07-11 18:00","매일"]
[138,"광주전남","광주","계림S/S #66 BUS","계림S/S  GIS 교체공사(11차)","계림S/S  GIS 교체공사(11차)","2025-07-26 09:00","2025-07-27 18:00","취소","취소","연속"]
[139,"광주전남","광주","북광주계림#2 T/L","계림S/S  GIS 교체공사(11차)","무부하가압용","2025-07-25 09:00","2025-07-28 18:00","취소","취소","연속"]
[140,"광주전남","광주","북광주계림#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 북광주-계림#2T/L 조작시험","2025-07-14 14:00","2025-07-14 16:00","취소","취소","연속"]
[141,"광주전남","광주","북광주계림#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 북광주-계림#1T/L 조작시험","2025-07-14 10:00","2025-07-14 14:00","취소","취소","연속"]
[142,"광주전남","광주","북광주계림#2 T/L","계림S/S  GIS 교체공사(11차)","무부하가압용","2025-07-13 09:00","2025-07-13 18:00","취소","취소","연속"]
[143,"광주전남","광주","계림S/S #66 BUS","계림S/S  GIS 교체공사(11차)","계림S/S  GIS 교체공사(11차)","2025-07-11 18:00","2025-07-13 09:00","취소","취소","연속"]
[144,"광주전남","광주","계림S/S SEC CB 66650","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2025-07-09 09:00","2025-07-11 18:00","취소","취소","연속"]
[145,"광주전남","광주","계림S/S CB 6100","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2025-07-07 09:00","2025-07-11 18:00","취소","취소","연속"]
[146,"광주전남","광주","계림S/S SEC CB 61600","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2025-07-07 09:00","2025-07-09 18:00","취소","취소","연속"]
[147,"광주전남","광주","신광주계림#2 T/L","계림S/S  GIS 교체공사(11차)","계림S/S  GIS 교체공사(11차)","2025-07-04 09:00","2025-07-28 18:00","취소","취소","연속"]
[148,"광주전남","광주","계림S/S #66 BUS","계림S/S  GIS 교체공사(11차)","계림S/S  GIS 교체공사(11차)","2025-07-04 18:00","2025-07-04 22:00","취소","취소","연속"]
[149,"광주전남","광주","계림S/S #61 BUS","계림S/S  GIS 교체공사(11차)","계림S/S  GIS 교체공사(11차)","2025-07-04 22:00","2025-07-07 09:00","취소","취소","연속"]
[150,"광주전남","광주","북광주계림#2 T/L","계림S/S  GIS 교체공사(11차)","무부하가압용","2025-07-06 09:00","2025-07-06 18:00","취소","취소","연속"]
[151,"광주전남","광주","계림남광주 T/L"," 남광주C/T 이설공사"," 남광주C/T(58호) 신설시 안전이격확보 휴전","2025-07-01 07:00","2025-07-02 18:00","취소","취소","매일"]
[152,"광주전남","광주","남광주소태 T/L"," 남광주C/T 이설공사"," 남광주C/T(58호) 신설시 안전이격확보 휴전","2025-07-01 07:00","2025-07-02 18:00","취소","취소","매일"]
[153,"광주전남","광주","담양김제 T/L","2024~25년 광주전력지사 송전 협력회사공사(피뢰기)"," 담양-김제T/L 피뢰기설치공사 NO.1~33호)","2025-07-07 07:00","2025-07-09 18:00","취소","취소","매일"]
[154,"광주전남","광주","정공담양 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 담양-일곡#2 T/L 피뢰기 설치 (병가) - 대상 : 1~16, 173~189, 193~228호 (총 71기) - 병가구간 : 2~15호 (담양-정공 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-07-21 07:00","2025-07-22 18:00","취소","취소","매일"]
[155,"광주전남","광주","신광주장성#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S  신광주-장성#2T/L GIS 정밀점검","2025-07-21 09:00","2025-07-23 18:00","취소","취소","연속"]
[156,"광주전남","광주","신광주S/S CB 6200","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S #2BUSTIE 보통점검","2025-07-04 09:00","2025-07-04 18:00","2025-07-04 09:00","2025-07-04 18:00","매일"]
[157,"광주전남","광주","신광주장성#2 T/L","2024~25년 광주전력지사 송전 협력회사공사(가공지선)"," 신광주-장성T/L 63~66호 가공지선 교체공사","2025-07-01 07:00","2025-07-01 18:00","취소","취소","연속"]
[158,"광주전남","광주","신광주S/S CB 6100","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S #1 BUSTIE 보통점검","2025-07-03 09:00","2025-07-03 18:00","2025-07-03 09:00","2025-07-03 18:00","매일"]
[159,"광주전남","광주","신광주S/S SEC CB 65660","2025년 광주전력지사 170kV GIS 점검 공사","1. 2025년 광주전력지사 170kV GIS 점검공사 - 신광주S/S  65-66 BUS SEC 보통점검","2025-07-08 09:00","2025-07-08 18:00","2025-07-08 09:00","2025-07-08 18:00","매일"]
[160,"광주전남","광주","신광주S/S SEC CB 60610","2025년 광주전력지사 170kV GIS 점검 공사","1. 2025년 광주전력지사 170kV GIS 점검공사 - 신광주S/S  60-61 BUS SEC 보통점검","2025-07-07 09:00","2025-07-07 18:00","2025-07-07 09:00","2025-07-07 18:00","매일"]
[161,"광주전남","광주","신화순화순#2 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 피뢰기갭혼교체 시행 -  신화순-화순#2T/L 1~5, 10~57호","2025-07-25 08:00","2025-07-31 18:00","2025-07-25 08:00","2025-07-31 18:00","매일"]
[162,"광주전남","광주","신화순화순#1 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 피뢰기갭혼교체 시행 -  신화순-화순#1T/L 1~5, 10~57호","2025-07-18 08:00","2025-07-24 18:00","2025-07-18 08:00","2025-07-24 18:00","매일"]
[163,"광주전남","광주","담양일곡#2 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 담양-일곡#2 T/L 피뢰기 설치 - 대상 : 1~16, 173~189, 193~228호 (총 71기) - 병가구간 : 2~15호 (담양-정공 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-07-21 07:00","2025-07-25 18:00","취소","취소","매일"]
[164,"광주전남","광주","장성영광#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 장성S/S  장성-영광#2T/L GIS보통점검","2025-07-24 09:00","2025-07-24 18:00","취소","취소","연속"]
[165,"광주전남","광주","신광주장성#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 장성S/S  신광주-장성#2T/L GIS보통점검","2025-07-22 09:00","2025-07-22 18:00","취소","취소","연속"]
[166,"광주전남","광주","장성영광#2 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 장성-영광#2 T/L 피뢰기 설치 - 대상 : 1~15, 21~68호 (총 64기) - 병가구간 : 2~15호 (하남-장성 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-07-14 07:00","2025-07-18 18:00","취소","취소","매일"]
[167,"광주전남","광주","하남장성#1 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 장성-영광#2 T/L 피뢰기 설치(병가) - 대상 : 1~15, 21~68호 (총 64기) - 병가구간 : 2~15호 (하남-장성#1 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-07-14 07:00","2025-07-15 18:00","취소","취소","매일"]
[168,"광주전남","광주","장성영광#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","-장성-영광#1T/L 170kV GIS 조작시험","2025-07-11 10:00","2025-07-11 16:00","취소","취소","연속"]
[169,"광주전남","광주","계림충장#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 계림-충장S/S #2T/L 170kV GIS 조작시험","2025-07-09 10:00","2025-07-09 14:00","취소","취소","연속"]
[170,"광주전남","광주","충장농성#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 충장-농성#1T/L 170kV GIS 조작시험","2025-07-08 10:00","2025-07-08 14:00","취소","취소","연속"]
[171,"광주전남","광주","충장농성#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 충장-농성#2T/L 170kV GIS 조작시험","2025-07-08 14:00","2025-07-08 16:00","취소","취소","연속"]
[172,"광주전남","광주","계림충장#3 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 계림-충장#3T/L 170kV GIS 조작시험","2025-07-09 14:00","2025-07-09 16:00","취소","취소","연속"]
[173,"광주전남","광주","계림충장#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 계림-충장#1T/L 170kV GIS 조작시험","2025-07-10 10:00","2025-07-10 13:00","취소","취소","연속"]
[174,"광주전남","광주","신화순화순#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 화순S/S  신화순-화순#2T/L GIS 정밀점검","2025-07-14 09:00","2025-07-16 18:00","2025-07-14 09:00","2025-07-16 18:00","연속"]
[175,"광주전남","광주","신화순화순#1 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 화순S/S  신화순-화순#1T/L GIS 정밀점검","2025-07-09 09:00","2025-07-11 18:00","2025-07-09 09:00","2025-07-11 18:00","연속"]
[176,"광주전남","목포","남악북항#1 T/L","북항변전소 건축설비 보수 공사","변전소 외벽 마감재 고정 (일정 변경가능)","2025-07-16 09:00","2025-07-16 18:00","취소","취소","연속"]
[177,"광주전남","목포","남악북항#2 T/L","북항변전소 건축설비 보수 공사","변전소 외벽 마감재 고정 (일정 변경가능)","2025-07-15 09:00","2025-07-15 18:00","취소","취소","연속"]
[178,"광주전남","목포","목포북항#2 T/L","북항변전소 건축설비 보수 공사","변전소 외벽 마감재 고정 (일정 변경가능)","2025-07-15 09:00","2025-07-15 18:00","취소","취소","연속"]
[179,"광주전남","목포","목포북항#1 T/L","북항변전소 건축설비 보수 공사","변전소 외벽 마감재 고정 (일정 변경가능)","2025-07-16 09:00","2025-07-16 18:00","취소","취소","연속"]
[180,"광주전남","목포","장성영광#2 T/L"," 영광-홍농 등 4개T/L 선종교체공사","대상구간 :  고창-영광T/L 1~45호 공사내용 : 용량증대 선종교체공사","2025-07-24 00:07","2025-08-12 18:00","2025-07-24 00:07","2025-08-12 18:00","연속"]
[181,"광주전남","순천","광양백운#1 T/L","광양-백운 #1T/L 정밀점검","○ 광양-백운 #1T/L 정밀점검 - 광양S/S ~ 백운S/S , 총 20기","2025-07-07 09:00","2025-07-09 18:00","취소","취소","매일"]
[182,"광주전남","순천","화순승주#1 T/L"," 순천-승주 T/L"," 순천-승주 T/L 정밀점검 병가선로 - 대상 : No.1~172호(89기)","2025-07-01 09:00","2025-07-01 18:00","취소","취소","연속"]
[183,"광주전남","순천","승주서순천 T/L"," 승주-서순천 T/L 추락방지시설 설치공사","4회선 수평추락방지 설치 (승주-서순천, 화순-승주2(통보분) 병가)","2025-07-07 07:00","2025-07-11 18:00","취소","취소","매일"]
[184,"광주전남","순천","승주주암HP T/L"," 승주-서순천 T/L 추락방지시설 설치공사","4회선 수평추락방지 설치 (승주-주암HP, 화순-승주1(통보분) 병가)","2025-07-14 07:00","2025-07-18 18:00","취소","취소","매일"]
[185,"광주전남","순천","화순승주#2 T/L"," 순천-승주 T/L"," 순천-승주 T/L 정밀점검 병가선로 - 대상 : No.1~172호(89기)","2025-07-14 09:00","2025-07-14 18:00","취소","취소","연속"]
[186,"광주전남","순천","순천승주#1 T/L"," 순천-승주 T/L"," 순천-승주 T/L 정밀점검 - 대상 : No.1~172호(89기)","2025-07-14 09:00","2025-07-25 18:00","취소","취소","매일"]
[187,"광주전남","순천","계림승주#2 T/L"," 순천-승주 T/L"," 순천-승주 T/L 정밀점검 병가선로 - 대상 : No.1~172호(89기)","2025-07-14 09:00","2025-07-14 18:00","취소","취소","연속"]
[188,"광주전남","순천","계림승주#1 T/L"," 순천-승주 T/L"," 순천-승주 T/L 정밀점검 병가선로 - 대상 : No.1~172호(89기)","2025-07-01 09:00","2025-07-01 18:00","취소","취소","연속"]
[189,"광주전남","순천","순천승주#2 T/L"," 순천-승주 T/L"," 순천-승주 T/L 정밀점검 병가선로 - 대상 : No.1~172호(89기)","2025-07-01 09:00","2025-07-11 18:00","취소","취소","매일"]
[190,"광주전남","순천","여수소라#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수-소라#1,2T/L 보호배전반 엔지니어링","2025-07-03 15:00","2025-07-04 10:00","2025-07-03 18:00","2025-07-04 09:00","연속"]
[191,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - 무부하가압용","2025-07-26 16:00","2025-07-26 17:00","2025-07-26 18:00","2025-07-26 19:00","연속"]
[192,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - 무부하가압용","2025-07-25 18:00","2025-07-26 09:00","2025-07-25 18:00","2025-07-26 09:00","연속"]
[193,"광주전남","순천","여수소라#1 T/L","여수S/S  이하 장기사용 GIS 교체공사(2차)","○ 여수S/S  장기사용 GIS 교체공사(2차) - 무부하가압용","2025-07-17 18:00","2025-07-18 09:00","2025-07-17 18:00","2025-07-18 09:00","연속"]
[194,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - 무부하가압용","2025-07-17 18:00","2025-07-18 09:00","2025-07-17 18:00","2025-07-18 09:00","연속"]
[195,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - 안전이격휴전","2025-07-12 10:00","2025-07-12 17:00","2025-07-12 18:00","2025-07-13 09:00","연속"]
[196,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - 안전이격휴전","2025-07-11 10:00","2025-07-11 17:00","2025-07-11 18:00","2025-07-11 09:00","연속"]
[197,"광주전남","순천","여수소라#1 T/L"," 여수-소라 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여수-소라1, 여천-여수1 병가)","2025-07-03 07:00","2025-07-04 18:00","취소","취소","매일"]
[198,"광주전남","순천","여수소라#1 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수-소라#1,2T/L 보호배전반 엔지니어링","2025-07-01 15:00","2025-07-02 10:00","2025-07-01 18:00","2025-07-02 09:00","연속"]
[199,"광주전남","순천","여수소라#2 T/L"," 여수-소라 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여수-소라1, 여천-여수1 병가)","2025-07-07 07:00","2025-07-08 18:00","취소","취소","매일"]
[200,"광주전남","순천","여수S/S CB 6100","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #3M.Tr 1차 GIS 교체, #6200BUS-TIE 이설","2025-07-07 09:00","2025-07-26 18:00","취소","취소","연속"]
[201,"광주전남","순천","여천여수#1 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-07-07 09:00","2025-07-26 18:00","취소","취소","연속"]
[202,"광주전남","순천","율촌여수산단#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여수산단 율촌-여수산단#2T/L GIS 보통점검","2025-07-07 09:00","2025-07-07 18:00","취소","취소","연속"]
[203,"광주전남","순천","여수TP용성#1 T/L","24-25년 순천전력지사 변전협력회사 공사","여수화력,용성S/S 여수TP-용성#1T/L GIS 보통점검","2025-07-03 09:00","2025-07-03 18:00","취소","취소","연속"]
[204,"광주전남","순천","여수TP용성#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여수화력,용성S/S 여수TP-용성#2T/L GIS 보통점검","2025-07-04 09:00","2025-07-04 18:00","취소","취소","연속"]
[205,"광주전남","순천","호남TP여수TP#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (2호 : 여천-호남TP1, 호남TP-여수TP1 병가)","2025-07-10 07:00","2025-07-10 18:00","취소","취소","연속"]
[206,"광주전남","순천","여수TP여천#1 T/L","24-25년 순천전력지사 변전협력회사 공사","여천S/S 여수TP-여천#1T/L GIS 조작시험","2025-07-01 09:00","2025-07-01 18:00","취소","취소","연속"]
[207,"광주전남","순천","호남TP여수TP#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (2호 : 여천-호남TP2, 호남TP-여수TP2 병가)","2025-07-01 07:00","2025-07-01 18:00","취소","취소","연속"]
[208,"광주전남","순천","여수TP여천#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여천S/S 여수TP-여천#2T/L GIS 전자변 교체, 여수화력S/S 여수TP-여천#2T/L GIS 보통점검","2025-07-02 09:00","2025-07-02 18:00","취소","취소","연속"]
[209,"광주전남","순천","여천호남TP#1 T/L","여천S/S  이하 GIS 교체공사","여천S/S  이하 GIS 교체공사 기기기초 터파기를 위한 안전이격 휴전 신청 매일휴전 / 즉시가압 가능 조건임","2025-07-28 09:00","2025-07-31 18:00","취소","취소","매일"]
[210,"광주전남","순천","여천여수#1 T/L","여천S/S  이하 GIS 교체공사","여천S/S  이하 GIS 교체공사 기기기초 터파기를 위한 안전이격 휴전 신청 매일휴전 / 즉시가압 가능 조건임","2025-07-21 09:00","2025-07-25 18:00","취소","취소","매일"]
[211,"광주전남","순천","여천여수#2 T/L","여천S/S  이하 GIS 교체공사","여천S/S  이하 GIS 교체공사 기기기초 터파기를 위한 안전이격 휴전 신청 매일휴전 / 즉시가압 가능 조건임","2025-07-14 09:00","2025-07-18 18:00","취소","취소","매일"]
[212,"광주전남","순천","여수TP여천#1 T/L","여천S/S  이하 GIS 교체공사","여천S/S  이하 GIS 교체공사 기기기초 터파기를 위한 안전이격 휴전 신청 매일휴전 / 즉시가압 가능 조건임","2025-07-07 09:00","2025-07-11 18:00","취소","취소","매일"]
[213,"광주전남","순천","여천여수#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여천-호남TP1, 여천-여수2 병가)","2025-07-07 07:00","2025-07-08 18:00","취소","취소","매일"]
[214,"광주전남","순천","여천호남TP#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여천-호남TP1, 여천-여수2 병가)","2025-07-07 07:00","2025-07-10 18:00","취소","취소","매일"]
[215,"광주전남","순천","여수TP여천#2 T/L","여천S/S  이하 GIS 교체공사","여천S/S  이하 GIS 교체공사 기기기초 터파기를 위한 안전이격 휴전 신청 매일휴전 / 즉시가압 가능 조건임","2025-07-01 09:00","2025-07-04 18:00","취소","취소","매일"]
[216,"광주전남","순천","여천호남TP#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여천-호남TP2, 여천-여수1 병가)","2025-07-01 07:00","2025-07-04 18:00","취소","취소","매일"]
[217,"광주전남","순천","여천여수#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여천-호남TP2, 여천-여수1 병가)","2025-07-03 07:00","2025-07-04 18:00","취소","취소","매일"]
[218,"광주전남","순천","여수TP용성#2 T/L"," 여수TP-용성 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여수TP-용성2, 용성-여수산단2 병가)","2025-07-25 13:00","2025-07-25 18:00","취소","취소","연속"]
[219,"광주전남","순천","용성여수산단#2 T/L"," 여수TP-용성 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여수TP-용성2, 용성-여수산단2 병가)","2025-07-25 13:00","2025-07-25 18:00","취소","취소","연속"]
[220,"광주전남","순천","여수TP용성#1 T/L"," 여수TP-용성 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여수TP-용성1, 용성-여수산단1 병가)","2025-07-25 07:00","2025-07-25 13:00","취소","취소","연속"]
[221,"광주전남","순천","용성여수산단#1 T/L"," 여수TP-용성 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여수TP-용성1, 용성-여수산단1 병가)","2025-07-25 07:00","2025-07-25 13:00","취소","취소","연속"]
[222,"광주전남","순천","순천율촌#2 T/L"," 율촌-화치 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (68호:율촌-화치1,순천-율촌2 병가)","2025-07-21 07:00","2025-07-21 18:00","2025-07-21 07:00","2025-07-21 18:00","연속"]
[223,"광주전남","순천","율촌민자#1 T/L"," 율촌민자 T/L 추락방지시설 설치공사","수평추락방지시설 설치","2025-07-07 07:00","2025-07-07 18:00","취소","취소","연속"]
[224,"광주전남","순천","율촌화치#1 T/L"," 율촌-화치 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (율촌-화치1, 율촌-여수산단2 병가)","2025-07-21 07:00","2025-07-25 18:00","2025-07-21 07:00","2025-07-25 18:00","매일"]
[225,"광주전남","순천","순천율촌#1 T/L"," 율촌-화치 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (68호:율촌-화치2,순천-율촌1 병가)","2025-07-18 07:00","2025-07-18 18:00","2025-07-18 07:00","2025-07-18 18:00","연속"]
[226,"광주전남","순천","율촌여수산단#1 T/L"," 율촌-여수산단 T/L 추락방지시설 설치공사","수평추락방지시설 설치","2025-07-14 07:00","2025-07-18 18:00","취소","취소","매일"]
[227,"광주전남","순천","율촌화치#2 T/L"," 율촌-화치 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (율촌-화치2, 율촌-여수산단1 병가)","2025-07-14 07:00","2025-07-18 18:00","2025-07-14 07:00","2025-07-18 18:00","매일"]
[228,"광주전남","순천","율촌민자#2 T/L"," 율촌민자 T/L 추락방지시설 설치공사","수평추락방지시설 설치","2025-07-08 07:00","2025-07-08 18:00","취소","취소","연속"]
[229,"광주전남","순천","율촌여수산단#2 T/L"," 율촌-여수산단 T/L 추락방지시설 설치공사","수평추락방지시설 설치","2025-07-21 07:00","2025-07-25 18:00","취소","취소","매일"]
[230,"대구","경산","경산S/S #1 EM.Tr CB","'25년 경산전력 GIS 정밀점검공사","GIS 정밀점검","2025-07-07 09:30","2025-07-08 18:00","2025-07-03 09:30","2025-07-04 18:00","연속"]
[231,"대구","경산","경산자인#1 T/L","'25년 경산전력 GIS 정밀점검공사","GIS 정밀점검(무부하 가압선로)","2025-07-08 17:00","2025-07-08 18:00","2025-07-04 17:00","2025-07-04 18:00","연속"]
[232,"대구","경산","안심반야월#1 T/L","'25년 경산전력 GIS 정밀점검공사","GIS 정밀점검(무부하 가압선로)","2025-07-10 17:00","2025-07-10 18:00","2025-07-10 17:00","2025-07-10 18:00","연속"]
[233,"대구","경산","영천복선전철#1 T/L CB","'25년 경산전력 GIS 정밀점검공사","GIS 정밀점검","2025-07-14 09:30","2025-07-15 18:00","2025-07-14 09:30","2025-07-15 18:00","연속"]
[234,"대구","경산","영천복선전철#2 T/L CB","'25년 경산전력 GIS 정밀점검공사","GIS 정밀점검","2025-07-16 09:30","2025-07-17 18:00","2025-07-16 09:30","2025-07-17 18:00","연속"]
[235,"대구","경산","청통영천#2 T/L","'25년 경산전력 GIS 정밀점검공사","GIS 정밀점검(무부하 가압선로)","2025-07-17 17:00","2025-07-17 18:00","2025-07-17 17:00","2025-07-17 18:00","연속"]
[236,"대구","경산","청통영천#1 T/L","'25년 경산전력 GIS 정밀점검공사","GIS 정밀점검(무부하 가압선로)","2025-07-15 17:00","2025-07-15 18:00","2025-07-15 17:00","2025-07-15 18:00","연속"]
[237,"대구","달성","상인봉덕#1 T/L","[TEST] 봉덕 #3M.TR 정밀 무부하가압선로","[TEST] 봉덕 #3M.TR 정밀 무부하가압선로","2025-07-08 17:00","2025-07-08 18:00","취소","취소","연속"]
[238,"대구","달성","상인봉덕#1 T/L","[TEST] 봉덕 #1M.TR 정밀 무부하가압선로","[TEST] 봉덕 #1M.TR 정밀 무부하가압선로","2025-07-03 17:00","2025-07-03 18:00","취소","취소","연속"]
[239,"대구","달성","상인봉덕#1 T/L","[TEST] 봉덕 #60-65BUS TIE 정밀 무부하가압선로","[TEST] 봉덕 #60-65BUS TIE 정밀 무부하가압선로","2025-07-01 17:00","2025-07-01 18:00","2025-07-01 17:00","2025-07-01 18:00","연속"]
[240,"대구","달성","팔달서침산#1 T/L","GIS 정밀점검","GIS 정밀점검","2025-07-21 09:00","2025-07-22 18:00","2025-07-21 09:00","2025-07-22 18:00","연속"]
[241,"대구","달성","팔달서침산#2 T/L","GIS 정밀점검","GIS 정밀점검","2025-07-23 09:00","2025-07-24 18:00","2025-07-23 09:00","2025-07-24 18:00","연속"]
[242,"대구","칠곡","성주금릉#1 T/L","신옥천-북경남 등 8개T/L 수평 추락방지장치 설치공사"," 성주-금릉#1T/L 수평 추락방지장치 설치공사","2025-07-02 07:00","2025-07-16 18:00","2025-07-02 07:00","2025-07-16 18:00","연속"]
[243,"대구","칠곡","성주금릉#2 T/L","신옥천-북경남 등 8개T/L 수평 추락방지장치 설치공사"," 성주-금릉#2T/L 수평 추락방지장치 설치공사","2025-07-17 07:00","2025-07-31 18:00","2025-07-17 07:00","2025-07-31 18:00","연속"]
[244,"대구","포항","청하영덕#1 T/L","2024~25년도 포항전력지사 변전협력회사 공사","청하S/S 청하-영덕#1T/L GIS 보통점검","2025-07-15 09:00","2025-07-15 14:00","2025-07-15 09:00","2025-07-15 14:00","연속"]
[245,"대구","포항","청하영덕#2 T/L","2024~25년도 포항전력지사 변전협력회사 공사","청하S/S 청하-영덕#2T/L GIS 보통점검","2025-07-15 14:00","2025-07-15 18:00","2025-07-15 14:00","2025-07-15 18:00","연속"]
[246,"경북","구미","남인동인동#1 T/L","남인동S/S  LS인동T/L 교체공사","남인동S/S  LS인동T/L 교체공사_무부하가압","2025-07-27 18:00","2025-07-28 13:00","2025-07-27 18:00","2025-07-28 13:00","연속"]
[247,"경북","구미","남인동S/S LS인동T/L CB","남인동S/S  LS인동T/L 교체공사","남인동S/S  LS인동T/L 교체공사","2025-07-27 08:30","2025-08-10 18:00","2025-07-27 08:30","2025-08-10 18:00","연속"]
[248,"경북","직할","안동풍산 T/L","24-25년 경북직할 송전협력회사 공사","추락방지장치 설치공사","2025-07-14 07:00","2025-07-18 18:00","취소","취소","매일"]
[249,"부산울산","동부산","명례장안 T/L","장안S/S  신규수용공사","170kV GIS 1CCT 증설 - 시험가압선로","2025-07-07 13:00","2025-07-08 18:00","2025-07-07 13:00","2025-07-08 18:00","연속"]
[250,"부산울산","북부산","삼랑진S/Y #60 BUS","25년 북부산전력지사  GIS 정밀점검","삼랑진S/Y  #1M.Tr GIS 정밀점검","2025-07-04 17:00","2025-07-04 18:00","2025-07-04 17:00","2025-07-04 18:00","연속"]
[251,"부산울산","북부산","물금삼랑진PP#1 T/L","25년 북부산전력지사  GIS 정밀점검","삼랑진S/Y  #1M.Tr GIS 정밀점검","2025-07-04 17:00","2025-07-04 18:00","2025-07-04 17:00","2025-07-04 18:00","연속"]
[252,"부산울산","북부산","물금삼랑진PP#2 T/L","25년 북부산전력지사  GIS 정밀점검","삼랑진S/Y  물금-삼랑진PP #2T/L GIS 정밀점검","2025-07-07 09:00","2025-07-08 18:00","2025-07-07 09:00","2025-07-08 18:00","연속"]
[253,"부산울산","북부산","삼랑진S/Y #1M.Tr 1차 CB","25년 북부산전력지사  GIS 정밀점검","삼랑진S/Y  #1M.Tr GIS 정밀점검","2025-07-03 09:00","2025-07-04 18:00","2025-07-03 09:00","2025-07-04 18:00","연속"]
[254,"부산울산","북부산","물금삼랑진PP#1 T/L","25년 북부산전력지사  GIS 정밀점검","삼랑진S/Y  물금-삼랑진PP #1T/L GIS 정밀점검","2025-07-09 09:00","2025-07-10 18:00","2025-07-03 09:00","2025-07-04 18:00","연속"]
[255,"부산울산","북부산","양산삼랑진PP T/L","25년 북부산전력지사  GIS 정밀점검","삼랑진S/Y  양산-삼랑진PP T/L GIS 정밀점검","2025-07-14 09:00","2025-07-15 18:00","취소","취소","연속"]
[256,"부산울산","북부산","북부산삼랑진PP T/L","25년 북부산전력지사  GIS 정밀점검","삼랑진S/Y  북부산-삼랑진PP T/L GIS 정밀점검","2025-07-11 09:00","2025-07-12 18:00","취소","취소","연속"]
[257,"부산울산","북부산","양산산막#2 T/L","25년 북부산전력지사  GIS 정밀점검","양산S/S 6100B/T 시험가압선로","2025-07-01 17:00","2025-07-01 18:00","2025-07-02 17:00","2025-07-02 18:00","연속"]
[258,"부산울산","서부산","신녹산명지#2 T/L","신녹산S/S 345kV #1M.Tr 증설공사"," 신녹산-명지#1T/L 설치(감압)","2025-07-07 09:00","2025-07-12 18:00","2025-07-07 09:00","2025-07-12 18:00","연속"]
[259,"부산울산","서부산","신녹산녹산#1 T/L","신녹산S/S 345kV #1M.Tr 증설공사"," Sh.C 설치(무부하 시험가압)","2025-07-01 18:00","2025-07-02 19:00","2025-07-01 18:00","2025-07-02 19:00","연속"]
[260,"경남","함안","부북S/S ESS #2EM.Tr CB"," 부북S/S ESS 건설공사","#2 EM.Tr 누유 점검 및 조치","2025-07-07 10:00","2025-07-19 15:00","2025-07-07 10:00","2025-07-19 15:00","연속"]